## Project Management
Activity | Mean | Standard Deviation | Variance
A | 6 | 2
B | 9 | 1 | 1
C | 8 | 2
D | 7 | 2 | 4
E | 10 | 3 | 9
F | 12 | 3 | 9
Prove that Activities B, D, E and F are critical; but A and C not critical!
| Variance of the Project= |  | 23
| STD of the project (stdp) = |  | 0.75277
| Project Expected Time = |  | 52
check three different ways
P(T<40days) = P( (T-meanp)/std < (40-38)/4.80 ) = P(Z <.42)
40 |  |  |  | -15.9411 | 1.643e-55% | 1.643e-55% | 1.643e-55%
P(T>45 days)=1-P(T<=45days)
| = | 1-P(Z<=(45-38)/4.80 ) = 1- P(Z<=1.46)
45 |  |  |  | -9.299 | 100% | 100% | 100%
Reference: Wayne W.L., 2001, Simulation Modeling, pg 111-119
Note on F18: Ozdogru, Unsal: Z value
Note on F22: Ozdogru, Unsal: Z value
by the property of Normal distribution

## critical path
A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4
-0.32484 | 5.8376 | 1.6752 | 0.67516 | 0.51273 | 2.5127 | 5.8376 | 6.5127 | 7.5127 | 10.0255
3.9593 | 7.9796 | 5.9593 | 4.9593 | 6.9389 | 8.9389 | 7.9796 | 12.9389 | 19.8778 | 28.8168
6.3046 | 9.1523 | 8.3046 | 7.3046 | 10.457 | 12.457 | 9.1523 | 16.457 | 26.9139 | 39.3709
8.2062 | 10.1031 | 10.2062 | 9.2062 | 13.3094 | 15.3094 | 10.1031 | 19.3094 | 32.6187 | 47.9281
4.8148 | 8.4074 | 6.8148 | 5.8148 | 8.2222 | 10.2222 | 8.4074 | 14.2222 | 22.4444 | 32.6666
8.5173 | 10.2586 | 10.5173 | 9.5173 | 13.7759 | 15.7759 | 10.2586 | 19.7759 | 33.5518 | 49.3277
7.0746 | 9.5373 | 9.0746 | 8.0746 | 11.6118 | 13.6118 | 9.5373 | 17.6118 | 29.2237 | 42.8355
8.416 | 10.208 | 10.416 | 9.416 | 13.6239 | 15.6239 | 10.208 | 19.6239 | 33.2479 | 48.8718
8.9462 | 10.4731 | 10.9462 | 9.9462 | 14.4194 | 16.4194 | 10.4731 | 20.4194 | 34.8387 | 51.2581
5.8459 | 8.9229 | 7.8459 | 6.8459 | 9.7688 | 11.7688 | 8.9229 | 15.7688 | 25.5377 | 37.3065
5.2305 | 8.6152 | 7.2305 | 6.2305 | 8.8457 | 10.8457 | 8.6152 | 14.8457 | 23.6914 | 34.5372
9.1373 | 10.5687 | 11.1373 | 10.1373 | 14.706 | 16.706 | 10.5687 | 20.706 | 35.412 | 52.118
3.3969 | 7.6984 | 5.3969 | 4.3969 | 6.0953 | 8.0953 | 7.6984 | 12.0953 | 18.1907 | 26.286
5.7851 | 8.8925 | 7.7851 | 6.7851 | 9.6776 | 11.6776 | 8.8925 | 15.6776 | 25.3552 | 37.0328
5.2086 | 8.6043 | 7.2086 | 6.2086 | 8.8129 | 10.8129 | 8.6043 | 14.8129 | 23.6258 | 34.4387
9.7622 | 10.8811 | 11.7622 | 10.7622 | 15.6432 | 17.6432 | 10.8811 | 21.6432 | 37.2865 | 54.9297
3.5986 | 7.7993 | 5.5986 | 4.5986 | 6.398 | 8.398 | 7.7993 | 12.398 | 18.7959 | 27.1939
7.4765 | 9.7382 | 9.4765 | 8.4765 | 12.2147 | 14.2147 | 9.7382 | 18.2147 | 30.4295 | 44.6442
5.1836 | 8.5918 | 7.1836 | 6.1836 | 8.7754 | 10.7754 | 8.5918 | 14.7754 | 23.5508 | 34.3262
6.9591 | 9.4795 | 8.9591 | 7.9591 | 11.4386 | 13.4386 | 9.4795 | 17.4386 | 28.8773 | 42.3159
7.3402 | 9.6701 | 9.3402 | 8.3402 | 12.0102 | 14.0102 | 9.6701 | 18.0102 | 30.0205 | 44.0307
6.9202 | 9.4601 | 8.9202 | 7.9202 | 11.3802 | 13.3802 | 9.4601 | 17.3802 | 28.7605 | 42.1407
8.5367 | 10.2684 | 10.5367 | 9.5367 | 13.8051 | 15.8051 | 10.2684 | 19.8051 | 33.6101 | 49.4152
2.5804 | 7.2902 | 4.5804 | 3.5804 | 4.8705 | 6.8705 | 7.2902 | 10.8705 | 15.7411 | 22.6116
6.5936 | 9.2968 | 8.5936 | 7.5936 | 10.8904 | 12.8904 | 9.2968 | 16.8904 | 27.7808 | 40.6712
7.008 | 9.504 | 9.008 | 8.008 | 11.5121 | 13.5121 | 9.504 | 17.5121 | 29.0241 | 42.5362
4.2915 | 8.1458 | 6.2915 | 5.2915 | 7.4373 | 9.4373 | 8.1458 | 13.4373 | 20.8746 | 30.3119
5.4512 | 8.7256 | 7.4512 | 6.4512 | 9.1769 | 11.1769 | 8.7256 | 15.1769 | 24.3537 | 35.5306
6.5064 | 9.2532 | 8.5064 | 7.5064 | 10.7595 | 12.7595 | 9.2532 | 16.7595 | 27.5191 | 40.2786
3.6406 | 7.8203 | 5.6406 | 4.6406 | 6.4609 | 8.4609 | 7.8203 | 12.4609 | 18.9218 | 27.3827
2.298 | 7.149 | 4.298 | 3.298 | 4.4469 | 6.4469 | 7.149 | 10.4469 | 14.8939 | 21.3408
4.4543 | 8.2271 | 6.4543 | 5.4543 | 7.6814 | 9.6814 | 8.2271 | 13.6814 | 21.3629 | 31.0443
4.6213 | 8.3106 | 6.6213 | 5.6213 | 7.9319 | 9.9319 | 8.3106 | 13.9319 | 21.8639 | 31.7958
7.3267 | 9.6634 | 9.3267 | 8.3267 | 11.9901 | 13.9901 | 9.6634 | 17.9901 | 29.9802 | 43.9703
6.5492 | 9.2746 | 8.5492 | 7.5492 | 10.8238 | 12.8238 | 9.2746 | 16.8238 | 27.6476 | 40.4714
7.857 | 9.9285 | 9.857 | 8.857 | 12.7855 | 14.7855 | 9.9285 | 18.7855 | 31.5709 | 46.3564
4.737 | 8.3685 | 6.737 | 5.737 | 8.1055 | 10.1055 | 8.3685 | 14.1055 | 22.211 | 32.3165
6.7225 | 9.3613 | 8.7225 | 7.7225 | 11.0838 | 13.0838 | 9.3613 | 17.0838 | 28.1676 | 41.2514
3.4789 | 7.7395 | 5.4789 | 4.4789 | 6.2184 | 8.2184 | 7.7395 | 12.2184 | 18.4368 | 26.6552
6.17 | 9.085 | 8.17 | 7.17 | 10.255 | 12.255 | 9.085 | 16.255 | 26.51 | 38.765
7.0712 | 9.5356 | 9.0712 | 8.0712 | 11.6069 | 13.6069 | 9.5356 | 17.6069 | 29.2137 | 42.8206
4.6825 | 8.3413 | 6.6825 | 5.6825 | 8.0238 | 10.0238 | 8.3413 | 14.0238 | 22.0475 | 32.0713
4.7503 | 8.3752 | 6.7503 | 5.7503 | 8.1255 | 10.1255 | 8.3752 | 14.1255 | 22.251 | 32.3765
5.1509 | 8.5755 | 7.1509 | 6.1509 | 8.7264 | 10.7264 | 8.5755 | 14.7264 | 23.4527 | 34.1791
3.943 | 7.9715 | 5.943 | 4.943 | 6.9145 | 8.9145 | 7.9715 | 12.9145 | 19.829 | 28.7435
4.7658 | 8.3829 | 6.7658 | 5.7658 | 8.1487 | 10.1487 | 8.3829 | 14.1487 | 22.2975 | 32.4462
4.0394 | 8.0197 | 6.0394 | 5.0394 | 7.0591 | 9.0591 | 8.0197 | 13.0591 | 20.1183 | 29.1774
5.853 | 8.9265 | 7.853 | 6.853 | 9.7796 | 11.7796 | 8.9265 | 15.7796 | 25.5591 | 37.3387
4.7804 | 8.3902 | 6.7804 | 5.7804 | 8.1706 | 10.1706 | 8.3902 | 14.1706 | 22.3412 | 32.5118
6.723 | 9.3615 | 8.723 | 7.723 | 11.0845 | 13.0845 | 9.3615 | 17.0845 | 28.1691 | 41.2536
6.7678 | 9.3839 | 8.7678 | 7.7678 | 11.1517 | 13.1517 | 9.3839 | 17.1517 | 28.3035 | 41.4552
7.4987 | 9.7493 | 9.4987 | 8.4987 | 12.248 | 14.248 | 9.7493 | 18.248 | 30.4961 | 44.7441
7.5272 | 9.7636 | 9.5272 | 8.5272 | 12.2908 | 14.2908 | 9.7636 | 18.2908 | 30.5815 | 44.8723
5.9533 | 8.9766 | 7.9533 | 6.9533 | 9.9299 | 11.9299 | 8.9766 | 15.9299 | 25.8599 | 37.7898
8.9004 | 10.4502 | 10.9004 | 9.9004 | 14.3506 | 16.3506 | 10.4502 | 20.3506 | 34.7012 | 51.0517
6.7745 | 9.3873 | 8.7745 | 7.7745 | 11.1618 | 13.1618 | 9.3873 | 17.1618 | 28.3236 | 41.4854
6.78 | 9.39 | 8.78 | 7.78 | 11.1701 | 13.1701 | 9.39 | 17.1701 | 28.3401 | 41.5102
7.4491 | 9.7245 | 9.4491 | 8.4491 | 12.1736 | 14.1736 | 9.7245 | 18.1736 | 30.3472 | 44.5207
8.8211 | 10.4105 | 10.8211 | 9.8211 | 14.2316 | 16.2316 | 10.4105 | 20.2316 | 34.4633 | 50.6949
2.8291 | 7.4146 | 4.8291 | 3.8291 | 5.2437 | 7.2437 | 7.4146 | 11.2437 | 16.4873 | 23.731
5.8259 | 8.9129 | 7.8259 | 6.8259 | 9.7388 | 11.7388 | 8.9129 | 15.7388 | 25.4776 | 37.2164
5.7602 | 8.8801 | 7.7602 | 6.7602 | 9.6404 | 11.6404 | 8.8801 | 15.6404 | 25.2807 | 36.9211
6.6595 | 9.3297 | 8.6595 | 7.6595 | 10.9892 | 12.9892 | 9.3297 | 16.9892 | 27.9784 | 40.9675
8.6011 | 10.3006 | 10.6011 | 9.6011 | 13.9017 | 15.9017 | 10.3006 | 19.9017 | 33.8033 | 49.705
6.848 | 9.424 | 8.848 | 7.848 | 11.272 | 13.272 | 9.424 | 17.272 | 28.5439 | 41.8159
5.4812 | 8.7406 | 7.4812 | 6.4812 | 9.2218 | 11.2218 | 8.7406 | 15.2218 | 24.4437 | 35.6655
6.5819 | 9.2909 | 8.5819 | 7.5819 | 10.8728 | 12.8728 | 9.2909 | 16.8728 | 27.7456 | 40.6184
3.0966 | 7.5483 | 5.0966 | 4.0966 | 5.6448 | 7.6448 | 7.5483 | 11.6448 | 17.2897 | 24.9345
7.5203 | 9.7602 | 9.5203 | 8.5203 | 12.2805 | 14.2805 | 9.7602 | 18.2805 | 30.561 | 44.8416
5.3622 | 8.6811 | 7.3622 | 6.3622 | 9.0433 | 11.0433 | 8.6811 | 15.0433 | 24.0867 | 35.13
3.0589 | 7.5295 | 5.0589 | 4.0589 | 5.5884 | 7.5884 | 7.5295 | 11.5884 | 17.1768 | 24.7653
5.5666 | 8.7833 | 7.5666 | 6.5666 | 9.3498 | 11.3498 | 8.7833 | 15.3498 | 24.6997 | 36.0495
7.0962 | 9.5481 | 9.0962 | 8.0962 | 11.6442 | 13.6442 | 9.5481 | 17.6442 | 29.2885 | 42.9327
5.3982 | 8.6991 | 7.3982 | 6.3982 | 9.0973 | 11.0973 | 8.6991 | 15.0973 | 24.1946 | 35.2919
9.911 | 10.9555 | 11.911 | 10.911 | 15.8666 | 17.8666 | 10.9555 | 21.8666 | 37.7331 | 55.5997
5.7213 | 8.8606 | 7.7213 | 6.7213 | 9.5819 | 11.5819 | 8.8606 | 15.5819 | 25.1638 | 36.7458
3.4139 | 7.7069 | 5.4139 | 4.4139 | 6.1208 | 8.1208 | 7.7069 | 12.1208 | 18.2416 | 26.3625
1.2177 | 6.6089 | 3.2177 | 2.2177 | 2.8266 | 4.8266 | 6.6089 | 8.8266 | 11.6532 | 16.4798
3.9393 | 7.9697 | 5.9393 | 4.9393 | 6.909 | 8.909 | 7.9697 | 12.909 | 19.818 | 28.727
1.9111 | 6.9556 | 3.9111 | 2.9111 | 3.8667 | 5.8667 | 6.9556 | 9.8667 | 13.7333 | 19.6
7.5561 | 9.778 | 9.5561 | 8.5561 | 12.3341 | 14.3341 | 9.778 | 18.3341 | 30.6683 | 45.0024
6.1834 | 9.0917 | 8.1834 | 7.1834 | 10.2751 | 12.2751 | 9.0917 | 16.2751 | 26.5503 | 38.8254
6.4385 | 9.2192 | 8.4385 | 7.4385 | 10.6577 | 12.6577 | 9.2192 | 16.6577 | 27.3155 | 39.9732
8.0349 | 10.0174 | 10.0349 | 9.0349 | 13.0523 | 15.0523 | 10.0174 | 19.0523 | 32.1047 | 47.157
7.867 | 9.9335 | 9.867 | 8.867 | 12.8004 | 14.8004 | 9.9335 | 18.8004 | 31.6009 | 46.4013
9.377 | 10.6885 | 11.377 | 10.377 | 15.0655 | 17.0655 | 10.6885 | 21.0655 | 36.131 | 53.1965
6.6239 | 9.3119 | 8.6239 | 7.6239 | 10.9358 | 12.9358 | 9.3119 | 16.9358 | 27.8716 | 40.8073
6.2069 | 9.1035 | 8.2069 | 7.2069 | 10.3104 | 12.3104 | 9.1035 | 16.3104 | 26.6207 | 38.9311
9.2106 | 10.6053 | 11.2106 | 10.2106 | 14.816 | 16.816 | 10.6053 | 20.816 | 35.6319 | 52.4479
8.1358 | 10.0679 | 10.1358 | 9.1358 | 13.2038 | 15.2038 | 10.0679 | 19.2038 | 32.4075 | 47.6113
5.0617 | 8.5309 | 7.0617 | 6.0617 | 8.5926 | 10.5926 | 8.5309 | 14.5926 | 23.1852 | 33.7778
6.6753 | 9.3376 | 8.6753 | 7.6753 | 11.0129 | 13.0129 | 9.3376 | 17.0129 | 28.0258 | 41.0388
3.4542 | 7.7271 | 5.4542 | 4.4542 | 6.1813 | 8.1813 | 7.7271 | 12.1813 | 18.3625 | 26.5438
5.1056 | 8.5528 | 7.1056 | 6.1056 | 8.6584 | 10.6584 | 8.5528 | 14.6584 | 23.3169 | 33.9753
3.5613 | 7.7807 | 5.5613 | 4.5613 | 6.342 | 8.342 | 7.7807 | 12.342 | 18.684 | 27.026
6.4972 | 9.2486 | 8.4972 | 7.4972 | 10.7457 | 12.7457 | 9.2486 | 16.7457 | 27.4915 | 40.2372
4.3738 | 8.1869 | 6.3738 | 5.3738 | 7.5607 | 9.5607 | 8.1869 | 13.5607 | 21.1213 | 30.682
3.9362 | 7.9681 | 5.9362 | 4.9362 | 6.9044 | 8.9044 | 7.9681 | 12.9044 | 19.8087 | 28.7131
8.9776 | 10.4888 | 10.9776 | 9.9776 | 14.4663 | 16.4663 | 10.4888 | 20.4663 | 34.9327 | 51.399
6.1982 | 9.0991 | 8.1982 | 7.1982 | 10.2972 | 12.2972 | 9.0991 | 16.2972 | 26.5945 | 38.8917
7.228 | 9.614 | 9.228 | 8.228 | 11.842 | 13.842 | 9.614 | 17.842 | 29.6841 | 43.5261
7.6249 | 9.8125 | 9.6249 | 8.6249 | 12.4374 | 14.4374 | 9.8125 | 18.4374 | 30.8748 | 45.3122
7.173 | 9.5865 | 9.173 | 8.173 | 11.7596 | 13.7596 | 9.5865 | 17.7596 | 29.5191 | 43.2787
7.9303 | 9.9652 | 9.9303 | 8.9303 | 12.8955 | 14.8955 | 9.9652 | 18.8955 | 31.791 | 46.6865
5.3469 | 8.6734 | 7.3469 | 6.3469 | 9.0203 | 11.0203 | 8.6734 | 15.0203 | 24.0406 | 35.0609
4.0556 | 8.0278 | 6.0556 | 5.0556 | 7.0835 | 9.0835 | 8.0278 | 13.0835 | 20.1669 | 29.2504
4.5911 | 8.2955 | 6.5911 | 5.5911 | 7.8866 | 9.8866 | 8.2955 | 13.8866 | 21.7732 | 31.6599
4.982 | 8.491 | 6.982 | 5.982 | 8.473 | 10.473 | 8.491 | 14.473 | 22.946 | 33.419
5.7233 | 8.8617 | 7.7233 | 6.7233 | 9.585 | 11.585 | 8.8617 | 15.585 | 25.1699 | 36.7549
8.0559 | 10.0279 | 10.0559 | 9.0559 | 13.0838 | 15.0838 | 10.0279 | 19.0838 | 32.1677 | 47.2515
6.1811 | 9.0906 | 8.1811 | 7.1811 | 10.2717 | 12.2717 | 9.0906 | 16.2717 | 26.5433 | 38.815
7.9025 | 9.9513 | 9.9025 | 8.9025 | 12.8538 | 14.8538 | 9.9513 | 18.8538 | 31.7076 | 46.5614
5.791 | 8.8955 | 7.791 | 6.791 | 9.6865 | 11.6865 | 8.8955 | 15.6865 | 25.373 | 37.0595
3.1031 | 7.5516 | 5.1031 | 4.1031 | 5.6547 | 7.6547 | 7.5516 | 11.6547 | 17.3094 | 24.9641
5.9244 | 8.9622 | 7.9244 | 6.9244 | 9.8866 | 11.8866 | 8.9622 | 15.8866 | 25.7733 | 37.6599
4.3449 | 8.1724 | 6.3449 | 5.3449 | 7.5173 | 9.5173 | 8.1724 | 13.5173 | 21.0347 | 30.552
9.9817 | 10.9909 | 11.9817 | 10.9817 | 15.9726 | 17.9726 | 10.9909 | 21.9726 | 37.9452 | 55.9178
4.8054 | 8.4027 | 6.8054 | 5.8054 | 8.2081 | 10.2081 | 8.4027 | 14.2081 | 22.4162 | 32.6242
5.8545 | 8.9272 | 7.8545 | 6.8545 | 9.7817 | 11.7817 | 8.9272 | 15.7817 | 25.5634 | 37.3451
2.5602 | 7.2801 | 4.5602 | 3.5602 | 4.8403 | 6.8403 | 7.2801 | 10.8403 | 15.6807 | 22.521
3.4258 | 7.7129 | 5.4258 | 4.4258 | 6.1388 | 8.1388 | 7.7129 | 12.1388 | 18.2775 | 26.4163
5.7932 | 8.8966 | 7.7932 | 6.7932 | 9.6897 | 11.6897 | 8.8966 | 15.6897 | 25.3795 | 37.0692
4.951 | 8.4755 | 6.951 | 5.951 | 8.4265 | 10.4265 | 8.4755 | 14.4265 | 22.8529 | 33.2794
5.6438 | 8.8219 | 7.6438 | 6.6438 | 9.4657 | 11.4657 | 8.8219 | 15.4657 | 24.9315 | 36.3972
6.9783 | 9.4891 | 8.9783 | 7.9783 | 11.4674 | 13.4674 | 9.4891 | 17.4674 | 28.9348 | 42.4023
10.192 | 11.096 | 12.192 | 11.192 | 16.288 | 18.288 | 11.096 | 22.288 | 38.576 | 56.864
7.611 | 9.8055 | 9.611 | 8.611 | 12.4165 | 14.4165 | 9.8055 | 18.4165 | 30.8329 | 45.2494
10.7379 | 11.3689 | 12.7379 | 11.7379 | 17.1068 | 19.1068 | 11.3689 | 23.1068 | 40.2137 | 59.3205
3.3134 | 7.6567 | 5.3134 | 4.3134 | 5.9702 | 7.9702 | 7.6567 | 11.9702 | 17.9403 | 25.9105
7.374 | 9.687 | 9.374 | 8.374 | 12.061 | 14.061 | 9.687 | 18.061 | 30.1219 | 44.1829
7.0434 | 9.5217 | 9.0434 | 8.0434 | 11.5652 | 13.5652 | 9.5217 | 17.5652 | 29.1303 | 42.6955
4.3583 | 8.1792 | 6.3583 | 5.3583 | 7.5375 | 9.5375 | 8.1792 | 13.5375 | 21.075 | 30.6124
2.3368 | 7.1684 | 4.3368 | 3.3368 | 4.5052 | 6.5052 | 7.1684 | 10.5052 | 15.0104 | 21.5156
3.7904 | 7.8952 | 5.7904 | 4.7904 | 6.6856 | 8.6856 | 7.8952 | 12.6856 | 19.3711 | 28.0567
6.4113 | 9.2057 | 8.4113 | 7.4113 | 10.617 | 12.617 | 9.2057 | 16.617 | 27.2339 | 39.8509
7.4944 | 9.7472 | 9.4944 | 8.4944 | 12.2416 | 14.2416 | 9.7472 | 18.2416 | 30.4833 | 44.7249
9.8897 | 10.9448 | 11.8897 | 10.8897 | 15.8345 | 17.8345 | 10.9448 | 21.8345 | 37.6691 | 55.5036
7.3698 | 9.6849 | 9.3698 | 8.3698 | 12.0547 | 14.0547 | 9.6849 | 18.0547 | 30.1095 | 44.1642
7.1577 | 9.5789 | 9.1577 | 8.1577 | 11.7366 | 13.7366 | 9.5789 | 17.7366 | 29.4732 | 43.2099
6.2896 | 9.1448 | 8.2896 | 7.2896 | 10.4344 | 12.4344 | 9.1448 | 16.4344 | 26.8688 | 39.3032
1.4096 | 6.7048 | 3.4096 | 2.4096 | 3.1144 | 5.1144 | 6.7048 | 9.1144 | 12.2288 | 17.3432
6.2053 | 9.1027 | 8.2053 | 7.2053 | 10.308 | 12.308 | 9.1027 | 16.308 | 26.6159 | 38.9239
6.5827 | 9.2914 | 8.5827 | 7.5827 | 10.8741 | 12.8741 | 9.2914 | 16.8741 | 27.7482 | 40.6223
7.7941 | 9.8971 | 9.7941 | 8.7941 | 12.6912 | 14.6912 | 9.8971 | 18.6912 | 31.3824 | 46.0735
5.123 | 8.5615 | 7.123 | 6.123 | 8.6845 | 10.6845 | 8.5615 | 14.6845 | 23.369 | 34.0534
8.317 | 10.1585 | 10.317 | 9.317 | 13.4755 | 15.4755 | 10.1585 | 19.4755 | 32.951 | 48.4265
4.1843 | 8.0921 | 6.1843 | 5.1843 | 7.2764 | 9.2764 | 8.0921 | 13.2764 | 20.5529 | 29.8293
5.9492 | 8.9746 | 7.9492 | 6.9492 | 9.9238 | 11.9238 | 8.9746 | 15.9238 | 25.8476 | 37.7714
4.4054 | 8.2027 | 6.4054 | 5.4054 | 7.6081 | 9.6081 | 8.2027 | 13.6081 | 21.2162 | 30.8244
8.0854 | 10.0427 | 10.0854 | 9.0854 | 13.1281 | 15.1281 | 10.0427 | 19.1281 | 32.2562 | 47.3843
5.5091 | 8.7545 | 7.5091 | 6.5091 | 9.2636 | 11.2636 | 8.7545 | 15.2636 | 24.5273 | 35.7909
3.5418 | 7.7709 | 5.5418 | 4.5418 | 6.3127 | 8.3127 | 7.7709 | 12.3127 | 18.6253 | 26.938
6.5227 | 9.2613 | 8.5227 | 7.5227 | 10.784 | 12.784 | 9.2613 | 16.784 | 27.568 | 40.352
9.9449 | 10.9724 | 11.9449 | 10.9449 | 15.9173 | 17.9173 | 10.9724 | 21.9173 | 37.8346 | 55.7519
8.8786 | 10.4393 | 10.8786 | 9.8786 | 14.3179 | 16.3179 | 10.4393 | 20.3179 | 34.6358 | 50.9537
8.9064 | 10.4532 | 10.9064 | 9.9064 | 14.3596 | 16.3596 | 10.4532 | 20.3596 | 34.7192 | 51.0788
6.8865 | 9.4433 | 8.8865 | 7.8865 | 11.3298 | 13.3298 | 9.4433 | 17.3298 | 28.6596 | 41.9895
3.7029 | 7.8515 | 5.7029 | 4.7029 | 6.5544 | 8.5544 | 7.8515 | 12.5544 | 19.1088 | 27.6632
4.0389 | 8.0194 | 6.0389 | 5.0389 | 7.0583 | 9.0583 | 8.0194 | 13.0583 | 20.1166 | 29.1749
4.993 | 8.4965 | 6.993 | 5.993 | 8.4894 | 10.4894 | 8.4965 | 14.4894 | 22.9789 | 33.4683
7.5727 | 9.7864 | 9.5727 | 8.5727 | 12.3591 | 14.3591 | 9.7864 | 18.3591 | 30.7182 | 45.0774
6.7339 | 9.367 | 8.7339 | 7.7339 | 11.1009 | 13.1009 | 9.367 | 17.1009 | 28.2018 | 41.3028
8.9729 | 10.4864 | 10.9729 | 9.9729 | 14.4593 | 16.4593 | 10.4864 | 20.4593 | 34.9186 | 51.3779
5.0927 | 8.5463 | 7.0927 | 6.0927 | 8.639 | 10.639 | 8.5463 | 14.639 | 23.278 | 33.917
7.9686 | 9.9843 | 9.9686 | 8.9686 | 12.9529 | 14.9529 | 9.9843 | 18.9529 | 31.9059 | 46.8588
4.0706 | 8.0353 | 6.0706 | 5.0706 | 7.1059 | 9.1059 | 8.0353 | 13.1059 | 20.2119 | 29.3178
6.7692 | 9.3846 | 8.7692 | 7.7692 | 11.1539 | 13.1539 | 9.3846 | 17.1539 | 28.3077 | 41.4616
4.3317 | 8.1659 | 6.3317 | 5.3317 | 7.4976 | 9.4976 | 8.1659 | 13.4976 | 20.9952 | 30.4928
7.3407 | 9.6703 | 9.3407 | 8.3407 | 12.011 | 14.011 | 9.6703 | 18.011 | 30.022 | 44.033
2.2761 | 7.138 | 4.2761 | 3.2761 | 4.4141 | 6.4141 | 7.138 | 10.4141 | 14.8282 | 21.2423
3.6385 | 7.8193 | 5.6385 | 4.6385 | 6.4578 | 8.4578 | 7.8193 | 12.4578 | 18.9156 | 27.3733
6.3265 | 9.1632 | 8.3265 | 7.3265 | 10.4897 | 12.4897 | 9.1632 | 16.4897 | 26.9795 | 39.4692
4.4377 | 8.2189 | 6.4377 | 5.4377 | 7.6566 | 9.6566 | 8.2189 | 13.6566 | 21.3132 | 30.9698
4.4546 | 8.2273 | 6.4546 | 5.4546 | 7.682 | 9.682 | 8.2273 | 13.682 | 21.3639 | 31.0459
3.5077 | 7.7539 | 5.5077 | 4.5077 | 6.2616 | 8.2616 | 7.7539 | 12.2616 | 18.5232 | 26.7847
6.1702 | 9.0851 | 8.1702 | 7.1702 | 10.2553 | 12.2553 | 9.0851 | 16.2553 | 26.5105 | 38.7658
4.9841 | 8.492 | 6.9841 | 5.9841 | 8.4761 | 10.4761 | 8.492 | 14.4761 | 22.9522 | 33.4283
6.0548 | 9.0274 | 8.0548 | 7.0548 | 10.0823 | 12.0823 | 9.0274 | 16.0823 | 26.1645 | 38.2468
5.0383 | 8.5192 | 7.0383 | 6.0383 | 8.5575 | 10.5575 | 8.5192 | 14.5575 | 23.115 | 33.6725
6.1542 | 9.0771 | 8.1542 | 7.1542 | 10.2313 | 12.2313 | 9.0771 | 16.2313 | 26.4626 | 38.6939
9.3375 | 10.6687 | 11.3375 | 10.3375 | 15.0062 | 17.0062 | 10.6687 | 21.0062 | 36.0124 | 53.0186
4.5224 | 8.2612 | 6.5224 | 5.5224 | 7.7836 | 9.7836 | 8.2612 | 13.7836 | 21.5673 | 31.3509
8.5012 | 10.2506 | 10.5012 | 9.5012 | 13.7518 | 15.7518 | 10.2506 | 19.7518 | 33.5036 | 49.2553
4.0713 | 8.0357 | 6.0713 | 5.0713 | 7.107 | 9.107 | 8.0357 | 13.107 | 20.214 | 29.321
4.0486 | 8.0243 | 6.0486 | 5.0486 | 7.0729 | 9.0729 | 8.0243 | 13.0729 | 20.1458 | 29.2187
6.1246 | 9.0623 | 8.1246 | 7.1246 | 10.1869 | 12.1869 | 9.0623 | 16.1869 | 26.3738 | 38.5607
9.4838 | 10.7419 | 11.4838 | 10.4838 | 15.2257 | 17.2257 | 10.7419 | 21.2257 | 36.4514 | 53.6771
8.4765 | 10.2383 | 10.4765 | 9.4765 | 13.7148 | 15.7148 | 10.2383 | 19.7148 | 33.4295 | 49.1443
1.5208 | 6.7604 | 3.5208 | 2.5208 | 3.2813 | 5.2813 | 6.7604 | 9.2813 | 12.5625 | 17.8438
3.2682 | 7.6341 | 5.2682 | 4.2682 | 5.9023 | 7.9023 | 7.6341 | 11.9023 | 17.8045 | 25.7068
3.7112 | 7.8556 | 5.7112 | 4.7112 | 6.5669 | 8.5669 | 7.8556 | 12.5669 | 19.1337 | 27.7006
6.4839 | 9.2419 | 8.4839 | 7.4839 | 10.7258 | 12.7258 | 9.2419 | 16.7258 | 27.4517 | 40.1775
2.484 | 7.242 | 4.484 | 3.484 | 4.726 | 6.726 | 7.242 | 10.726 | 15.452 | 22.178
7.3879 | 9.694 | 9.3879 | 8.3879 | 12.0819 | 14.0819 | 9.694 | 18.0819 | 30.1638 | 44.2457
6.4261 | 9.213 | 8.4261 | 7.4261 | 10.6391 | 12.6391 | 9.213 | 16.6391 | 27.2783 | 39.9174
4.4858 | 8.2429 | 6.4858 | 5.4858 | 7.7287 | 9.7287 | 8.2429 | 13.7287 | 21.4575 | 31.1862
3.8099 | 7.9049 | 5.8099 | 4.8099 | 6.7148 | 8.7148 | 7.9049 | 12.7148 | 19.4296 | 28.1444
4.7977 | 8.3989 | 6.7977 | 5.7977 | 8.1966 | 10.1966 | 8.3989 | 14.1966 | 22.3931 | 32.5897
8.9975 | 10.4988 | 10.9975 | 9.9975 | 14.4963 | 16.4963 | 10.4988 | 20.4963 | 34.9926 | 51.4888
5.8481 | 8.9241 | 7.8481 | 6.8481 | 9.7722 | 11.7722 | 8.9241 | 15.7722 | 25.5444 | 37.3167
8.5415 | 10.2708 | 10.5415 | 9.5415 | 13.8123 | 15.8123 | 10.2708 | 19.8123 | 33.6245 | 49.4368
4.4601 | 8.2301 | 6.4601 | 5.4601 | 7.6902 | 9.6902 | 8.2301 | 13.6902 | 21.3803 | 31.0705
7.1335 | 9.5667 | 9.1335 | 8.1335 | 11.7002 | 13.7002 | 9.5667 | 17.7002 | 29.4004 | 43.1005
5.7056 | 8.8528 | 7.7056 | 6.7056 | 9.5584 | 11.5584 | 8.8528 | 15.5584 | 25.1169 | 36.6753
3.7183 | 7.8592 | 5.7183 | 4.7183 | 6.5775 | 8.5775 | 7.8592 | 12.5775 | 19.1549 | 27.7324
8.9759 | 10.488 | 10.9759 | 9.9759 | 14.4639 | 16.4639 | 10.488 | 20.4639 | 34.9278 | 51.3917
7.3026 | 9.6513 | 9.3026 | 8.3026 | 11.9539 | 13.9539 | 9.6513 | 17.9539 | 29.9078 | 43.8617
5.7156 | 8.8578 | 7.7156 | 6.7156 | 9.5734 | 11.5734 | 8.8578 | 15.5734 | 25.1469 | 36.7203
5.1936 | 8.5968 | 7.1936 | 6.1936 | 8.7903 | 10.7903 | 8.5968 | 14.7903 | 23.5807 | 34.371
5.508 | 8.754 | 7.508 | 6.508 | 9.2621 | 11.2621 | 8.754 | 15.2621 | 24.5241 | 35.7862
6.889 | 9.4445 | 8.889 | 7.889 | 11.3335 | 13.3335 | 9.4445 | 17.3335 | 28.6671 | 42.0006
6.8062 | 9.4031 | 8.8062 | 7.8062 | 11.2094 | 13.2094 | 9.4031 | 17.2094 | 28.4187 | 41.6281
0.67283 | 6.3364 | 2.6728 | 1.6728 | 2.0093 | 4.0093 | 6.3364 | 8.0093 | 10.0185 | 14.0278
9.912 | 10.956 | 11.912 | 10.912 | 15.868 | 17.868 | 10.956 | 21.868 | 37.7361 | 55.6041
8.8986 | 10.4493 | 10.8986 | 9.8986 | 14.3479 | 16.3479 | 10.4493 | 20.3479 | 34.6958 | 51.0438
6.3234 | 9.1617 | 8.3234 | 7.3234 | 10.4851 | 12.4851 | 9.1617 | 16.4851 | 26.9703 | 39.4554
3.0784 | 7.5392 | 5.0784 | 4.0784 | 5.6175 | 7.6175 | 7.5392 | 11.6175 | 17.2351 | 24.8526
6.7898 | 9.3949 | 8.7898 | 7.7898 | 11.1847 | 13.1847 | 9.3949 | 17.1847 | 28.3695 | 41.5542
4.1042 | 8.0521 | 6.1042 | 5.1042 | 7.1563 | 9.1563 | 8.0521 | 13.1563 | 20.3126 | 29.4689
8.6722 | 10.3361 | 10.6722 | 9.6722 | 14.0083 | 16.0083 | 10.3361 | 20.0083 | 34.0166 | 50.0248
6.5228 | 9.2614 | 8.5228 | 7.5228 | 10.7842 | 12.7842 | 9.2614 | 16.7842 | 27.5685 | 40.3527
5.9937 | 8.9968 | 7.9937 | 6.9937 | 9.9905 | 11.9905 | 8.9968 | 15.9905 | 25.9811 | 37.9716
5.1327 | 8.5664 | 7.1327 | 6.1327 | 8.6991 | 10.6991 | 8.5664 | 14.6991 | 23.3981 | 34.0972
6.0972 | 9.0486 | 8.0972 | 7.0972 | 10.1458 | 12.1458 | 9.0486 | 16.1458 | 26.2917 | 38.4375
5.1872 | 8.5936 | 7.1872 | 6.1872 | 8.7809 | 10.7809 | 8.5936 | 14.7809 | 23.5617 | 34.3426
8.4996 | 10.2498 | 10.4996 | 9.4996 | 13.7494 | 15.7494 | 10.2498 | 19.7494 | 33.4989 | 49.2483
7.4639 | 9.732 | 9.4639 | 8.4639 | 12.1959 | 14.1959 | 9.732 | 18.1959 | 30.3918 | 44.5877
4.3516 | 8.1758 | 6.3516 | 5.3516 | 7.5274 | 9.5274 | 8.1758 | 13.5274 | 21.0548 | 30.5822
9.4009 | 10.7004 | 11.4009 | 10.4009 | 15.1013 | 17.1013 | 10.7004 | 21.1013 | 36.2026 | 53.3038
6.8435 | 9.4217 | 8.8435 | 7.8435 | 11.2652 | 13.2652 | 9.4217 | 17.2652 | 28.5304 | 41.7956
6.4462 | 9.2231 | 8.4462 | 7.4462 | 10.6693 | 12.6693 | 9.2231 | 16.6693 | 27.3385 | 40.0078
0.20077 | 6.1004 | 2.2008 | 1.2008 | 1.3012 | 3.3012 | 6.1004 | 7.3012 | 8.6023 | 11.9035
5.4665 | 8.7332 | 7.4665 | 6.4665 | 9.1997 | 11.1997 | 8.7332 | 15.1997 | 24.3995 | 35.5992
8.8034 | 10.4017 | 10.8034 | 9.8034 | 14.2052 | 16.2052 | 10.4017 | 20.2052 | 34.4103 | 50.6155
2.3695 | 7.1848 | 4.3695 | 3.3695 | 4.5543 | 6.5543 | 7.1848 | 10.5543 | 15.1086 | 21.6629
9.0481 | 10.524 | 11.0481 | 10.0481 | 14.5721 | 16.5721 | 10.524 | 20.5721 | 35.1442 | 51.7163
6.2675 | 9.1337 | 8.2675 | 7.2675 | 10.4012 | 12.4012 | 9.1337 | 16.4012 | 26.8025 | 39.2037
6.5188 | 9.2594 | 8.5188 | 7.5188 | 10.7782 | 12.7782 | 9.2594 | 16.7782 | 27.5565 | 40.3347
6.3693 | 9.1846 | 8.3693 | 7.3693 | 10.5539 | 12.5539 | 9.1846 | 16.5539 | 27.1078 | 39.6617
5.8291 | 8.9145 | 7.8291 | 6.8291 | 9.7436 | 11.7436 | 8.9145 | 15.7436 | 25.4872 | 37.2308
3.9307 | 7.9653 | 5.9307 | 4.9307 | 6.896 | 8.896 | 7.9653 | 12.896 | 19.792 | 28.688
9.8395 | 10.9198 | 11.8395 | 10.8395 | 15.7593 | 17.7593 | 10.9198 | 21.7593 | 37.5186 | 55.2779
7.369 | 9.6845 | 9.369 | 8.369 | 12.0536 | 14.0536 | 9.6845 | 18.0536 | 30.1071 | 44.1607
6.8523 | 9.4261 | 8.8523 | 7.8523 | 11.2784 | 13.2784 | 9.4261 | 17.2784 | 28.5568 | 41.8351
6.0793 | 9.0396 | 8.0793 | 7.0793 | 10.1189 | 12.1189 | 9.0396 | 16.1189 | 26.2378 | 38.3567
3.9433 | 7.9717 | 5.9433 | 4.9433 | 6.915 | 8.915 | 7.9717 | 12.915 | 19.83 | 28.745
8.7022 | 10.3511 | 10.7022 | 9.7022 | 14.0532 | 16.0532 | 10.3511 | 20.0532 | 34.1065 | 50.1597
5.2855 | 8.6427 | 7.2855 | 6.2855 | 8.9282 | 10.9282 | 8.6427 | 14.9282 | 23.8564 | 34.7846
2.6873 | 7.3437 | 4.6873 | 3.6873 | 5.031 | 7.031 | 7.3437 | 11.031 | 16.062 | 23.093
6.6904 | 9.3452 | 8.6904 | 7.6904 | 11.0357 | 13.0357 | 9.3452 | 17.0357 | 28.0713 | 41.107
2.8821 | 7.4411 | 4.8821 | 3.8821 | 5.3232 | 7.3232 | 7.4411 | 11.3232 | 16.6463 | 23.9695
3.2924 | 7.6462 | 5.2924 | 4.2924 | 5.9386 | 7.9386 | 7.6462 | 11.9386 | 17.8772 | 25.8158
5.1488 | 8.5744 | 7.1488 | 6.1488 | 8.7232 | 10.7232 | 8.5744 | 14.7232 | 23.4464 | 34.1696
7.2469 | 9.6234 | 9.2469 | 8.2469 | 11.8703 | 13.8703 | 9.6234 | 17.8703 | 29.7406 | 43.6109
8.7803 | 10.3902 | 10.7803 | 9.7803 | 14.1705 | 16.1705 | 10.3902 | 20.1705 | 34.3409 | 50.5114
7.4934 | 9.7467 | 9.4934 | 8.4934 | 12.24 | 14.24 | 9.7467 | 18.24 | 30.4801 | 44.7201
4.6474 | 8.3237 | 6.6474 | 5.6474 | 7.9711 | 9.9711 | 8.3237 | 13.9711 | 21.9422 | 31.9133
2.825 | 7.4125 | 4.825 | 3.825 | 5.2375 | 7.2375 | 7.4125 | 11.2375 | 16.4749 | 23.7124
6.1314 | 9.0657 | 8.1314 | 7.1314 | 10.1971 | 12.1971 | 9.0657 | 16.1971 | 26.3941 | 38.5912
6.7276 | 9.3638 | 8.7276 | 7.7276 | 11.0913 | 13.0913 | 9.3638 | 17.0913 | 28.1827 | 41.274
8.4751 | 10.2376 | 10.4751 | 9.4751 | 13.7127 | 15.7127 | 10.2376 | 19.7127 | 33.4254 | 49.1381
8.2603 | 10.1302 | 10.2603 | 9.2603 | 13.3905 | 15.3905 | 10.1302 | 19.3905 | 32.781 | 48.1714
5.7733 | 8.8867 | 7.7733 | 6.7733 | 9.66 | 11.66 | 8.8867 | 15.66 | 25.32 | 36.9799
4.1212 | 8.0606 | 6.1212 | 5.1212 | 7.1818 | 9.1818 | 8.0606 | 13.1818 | 20.3636 | 29.5453
5.4958 | 8.7479 | 7.4958 | 6.4958 | 9.2437 | 11.2437 | 8.7479 | 15.2437 | 24.4875 | 35.7312
9.4378 | 10.7189 | 11.4378 | 10.4378 | 15.1567 | 17.1567 | 10.7189 | 21.1567 | 36.3134 | 53.4701
5.4164 | 8.7082 | 7.4164 | 6.4164 | 9.1246 | 11.1246 | 8.7082 | 15.1246 | 24.2492 | 35.3737
5.2546 | 8.6273 | 7.2546 | 6.2546 | 8.8819 | 10.8819 | 8.6273 | 14.8819 | 23.7637 | 34.6456
3.5047 | 7.7524 | 5.5047 | 4.5047 | 6.2571 | 8.2571 | 7.7524 | 12.2571 | 18.5141 | 26.7712
8.3734 | 10.1867 | 10.3734 | 9.3734 | 13.5601 | 15.5601 | 10.1867 | 19.5601 | 33.1201 | 48.6802
4.4282 | 8.2141 | 6.4282 | 5.4282 | 7.6423 | 9.6423 | 8.2141 | 13.6423 | 21.2847 | 30.927
7.3775 | 9.6887 | 9.3775 | 8.3775 | 12.0662 | 14.0662 | 9.6887 | 18.0662 | 30.1324 | 44.1986
10.3593 | 11.1797 | 12.3593 | 11.3593 | 16.539 | 18.539 | 11.1797 | 22.539 | 39.078 | 57.6169
8.8301 | 10.4151 | 10.8301 | 9.8301 | 14.2452 | 16.2452 | 10.4151 | 20.2452 | 34.4903 | 50.7355
4.4346 | 8.2173 | 6.4346 | 5.4346 | 7.6519 | 9.6519 | 8.2173 | 13.6519 | 21.3037 | 30.9556
5.5114 | 8.7557 | 7.5114 | 6.5114 | 9.2671 | 11.2671 | 8.7557 | 15.2671 | 24.5343 | 35.8014
6.9724 | 9.4862 | 8.9724 | 7.9724 | 11.4586 | 13.4586 | 9.4862 | 17.4586 | 28.9171 | 42.3757
5.4232 | 8.7116 | 7.4232 | 6.4232 | 9.1348 | 11.1348 | 8.7116 | 15.1348 | 24.2696 | 35.4044
4.6256 | 8.3128 | 6.6256 | 5.6256 | 7.9384 | 9.9384 | 8.3128 | 13.9384 | 21.8769 | 31.8153
4.4256 | 8.2128 | 6.4256 | 5.4256 | 7.6385 | 9.6385 | 8.2128 | 13.6385 | 21.2769 | 30.9154
5.4764 | 8.7382 | 7.4764 | 6.4764 | 9.2147 | 11.2147 | 8.7382 | 15.2147 | 24.4293 | 35.644
3.7625 | 7.8812 | 5.7625 | 4.7625 | 6.6437 | 8.6437 | 7.8812 | 12.6437 | 19.2875 | 27.9312
4.1874 | 8.0937 | 6.1874 | 5.1874 | 7.281 | 9.281 | 8.0937 | 13.281 | 20.5621 | 29.8431
5.0846 | 8.5423 | 7.0846 | 6.0846 | 8.6269 | 10.6269 | 8.5423 | 14.6269 | 23.2537 | 33.8806
5.5213 | 8.7607 | 7.5213 | 6.5213 | 9.282 | 11.282 | 8.7607 | 15.282 | 24.564 | 35.846
9.8412 | 10.9206 | 11.8412 | 10.8412 | 15.7618 | 17.7618 | 10.9206 | 21.7618 | 37.5236 | 55.2855
6.7464 | 9.3732 | 8.7464 | 7.7464 | 11.1195 | 13.1195 | 9.3732 | 17.1195 | 28.2391 | 41.3586
7.7882 | 9.8941 | 9.7882 | 8.7882 | 12.6823 | 14.6823 | 9.8941 | 18.6823 | 31.3647 | 46.047
3.4484 | 7.7242 | 5.4484 | 4.4484 | 6.1726 | 8.1726 | 7.7242 | 12.1726 | 18.3451 | 26.5177
6.9806 | 9.4903 | 8.9806 | 7.9806 | 11.4709 | 13.4709 | 9.4903 | 17.4709 | 28.9418 | 42.4126
7.952 | 9.976 | 9.952 | 8.952 | 12.928 | 14.928 | 9.976 | 18.928 | 31.8561 | 46.7841
7.4983 | 9.7492 | 9.4983 | 8.4983 | 12.2475 | 14.2475 | 9.7492 | 18.2475 | 30.4949 | 44.7424
7.6387 | 9.8193 | 9.6387 | 8.6387 | 12.458 | 14.458 | 9.8193 | 18.458 | 30.916 | 45.3739
7.1471 | 9.5736 | 9.1471 | 8.1471 | 11.7207 | 13.7207 | 9.5736 | 17.7207 | 29.4413 | 43.162
5.2826 | 8.6413 | 7.2826 | 6.2826 | 8.924 | 10.924 | 8.6413 | 14.924 | 23.8479 | 34.7719
4.0416 | 8.0208 | 6.0416 | 5.0416 | 7.0624 | 9.0624 | 8.0208 | 13.0624 | 20.1247 | 29.1871
9.1275 | 10.5638 | 11.1275 | 10.1275 | 14.6913 | 16.6913 | 10.5638 | 20.6913 | 35.3826 | 52.0739
5.8582 | 8.9291 | 7.8582 | 6.8582 | 9.7873 | 11.7873 | 8.9291 | 15.7873 | 25.5747 | 37.362
6.5105 | 9.2552 | 8.5105 | 7.5105 | 10.7657 | 12.7657 | 9.2552 | 16.7657 | 27.5314 | 40.2971
5.8845 | 8.9423 | 7.8845 | 6.8845 | 9.8268 | 11.8268 | 8.9423 | 15.8268 | 25.6536 | 37.4804
6.6335 | 9.3167 | 8.6335 | 7.6335 | 10.9502 | 12.9502 | 9.3167 | 16.9502 | 27.9005 | 40.8507
4.9168 | 8.4584 | 6.9168 | 5.9168 | 8.3752 | 10.3752 | 8.4584 | 14.3752 | 22.7503 | 33.1255
9.3304 | 10.6652 | 11.3304 | 10.3304 | 14.9956 | 16.9956 | 10.6652 | 20.9956 | 35.9912 | 52.9869
5.1914 | 8.5957 | 7.1914 | 6.1914 | 8.7871 | 10.7871 | 8.5957 | 14.7871 | 23.5741 | 34.3612
6.7387 | 9.3693 | 8.7387 | 7.7387 | 11.108 | 13.108 | 9.3693 | 17.108 | 28.2161 | 41.3241
7.8434 | 9.9217 | 9.8434 | 8.8434 | 12.7652 | 14.7652 | 9.9217 | 18.7652 | 31.5303 | 46.2955
7.0532 | 9.5266 | 9.0532 | 8.0532 | 11.5799 | 13.5799 | 9.5266 | 17.5799 | 29.1597 | 42.7396
8.328 | 10.164 | 10.328 | 9.328 | 13.492 | 15.492 | 10.164 | 19.492 | 32.984 | 48.476
10.2615 | 11.1307 | 12.2615 | 11.2615 | 16.3922 | 18.3922 | 11.1307 | 22.3922 | 38.7844 | 57.1766
7.3095 | 9.6548 | 9.3095 | 8.3095 | 11.9643 | 13.9643 | 9.6548 | 17.9643 | 29.9286 | 43.893
4.6952 | 8.3476 | 6.6952 | 5.6952 | 8.0428 | 10.0428 | 8.3476 | 14.0428 | 22.0856 | 32.1284
6.5708 | 9.2854 | 8.5708 | 7.5708 | 10.8562 | 12.8562 | 9.2854 | 16.8562 | 27.7123 | 40.5685
5.4473 | 8.7236 | 7.4473 | 6.4473 | 9.1709 | 11.1709 | 8.7236 | 15.1709 | 24.3418 | 35.5127
7.6753 | 9.8377 | 9.6753 | 8.6753 | 12.513 | 14.513 | 9.8377 | 18.513 | 31.026 | 45.539
9.6671 | 10.8335 | 11.6671 | 10.6671 | 15.5006 | 17.5006 | 10.8335 | 21.5006 | 37.0012 | 54.5019
4.9451 | 8.4726 | 6.9451 | 5.9451 | 8.4177 | 10.4177 | 8.4726 | 14.4177 | 22.8353 | 33.253
4.9771 | 8.4886 | 6.9771 | 5.9771 | 8.4657 | 10.4657 | 8.4886 | 14.4657 | 22.9314 | 33.3972
4.0819 | 8.041 | 6.0819 | 5.0819 | 7.1229 | 9.1229 | 8.041 | 13.1229 | 20.2458 | 29.3687
6.1632 | 9.0816 | 8.1632 | 7.1632 | 10.2448 | 12.2448 | 9.0816 | 16.2448 | 26.4896 | 38.7344
1.9933 | 6.9966 | 3.9933 | 2.9933 | 3.9899 | 5.9899 | 6.9966 | 9.9899 | 13.9799 | 19.9698
5.1012 | 8.5506 | 7.1012 | 6.1012 | 8.6518 | 10.6518 | 8.5506 | 14.6518 | 23.3036 | 33.9554
6.9555 | 9.4777 | 8.9555 | 7.9555 | 11.4332 | 13.4332 | 9.4777 | 17.4332 | 28.8664 | 42.2996
8.5592 | 10.2796 | 10.5592 | 9.5592 | 13.8389 | 15.8389 | 10.2796 | 19.8389 | 33.6777 | 49.5166
6.5105 | 9.2552 | 8.5105 | 7.5105 | 10.7657 | 12.7657 | 9.2552 | 16.7657 | 27.5315 | 40.2972
6.1667 | 9.0834 | 8.1667 | 7.1667 | 10.2501 | 12.2501 | 9.0834 | 16.2501 | 26.5002 | 38.7503
8.1147 | 10.0574 | 10.1147 | 9.1147 | 13.1721 | 15.1721 | 10.0574 | 19.1721 | 32.3442 | 47.5163
3.1051 | 7.5526 | 5.1051 | 4.1051 | 5.6577 | 7.6577 | 7.5526 | 11.6577 | 17.3153 | 24.973
7.7699 | 9.885 | 9.7699 | 8.7699 | 12.6549 | 14.6549 | 9.885 | 18.6549 | 31.3098 | 45.9647
7.7437 | 9.8719 | 9.7437 | 8.7437 | 12.6156 | 14.6156 | 9.8719 | 18.6156 | 31.2312 | 45.8468
3.2528 | 7.6264 | 5.2528 | 4.2528 | 5.8791 | 7.8791 | 7.6264 | 11.8791 | 17.7583 | 25.6374
8.3933 | 10.1966 | 10.3933 | 9.3933 | 13.5899 | 15.5899 | 10.1966 | 19.5899 | 33.1798 | 48.7697
1.9955 | 6.9977 | 3.9955 | 2.9955 | 3.9932 | 5.9932 | 6.9977 | 9.9932 | 13.9864 | 19.9796
4.9613 | 8.4807 | 6.9613 | 5.9613 | 8.442 | 10.442 | 8.4807 | 14.442 | 22.8839 | 33.3259
6.9724 | 9.4862 | 8.9724 | 7.9724 | 11.4587 | 13.4587 | 9.4862 | 17.4587 | 28.9173 | 42.376
6.4531 | 9.2266 | 8.4531 | 7.4531 | 10.6797 | 12.6797 | 9.2266 | 16.6797 | 27.3594 | 40.0392
7.5656 | 9.7828 | 9.5656 | 8.5656 | 12.3483 | 14.3483 | 9.7828 | 18.3483 | 30.6967 | 45.045
8.9413 | 10.4706 | 10.9413 | 9.9413 | 14.4119 | 16.4119 | 10.4706 | 20.4119 | 34.8238 | 51.2357
7.8795 | 9.9397 | 9.8795 | 8.8795 | 12.8192 | 14.8192 | 9.9397 | 18.8192 | 31.6384 | 46.4575
9.8929 | 10.9465 | 11.8929 | 10.8929 | 15.8394 | 17.8394 | 10.9465 | 21.8394 | 37.6788 | 55.5182
5.453 | 8.7265 | 7.453 | 6.453 | 9.1794 | 11.1794 | 8.7265 | 15.1794 | 24.3589 | 35.5383
4.1572 | 8.0786 | 6.1572 | 5.1572 | 7.2357 | 9.2357 | 8.0786 | 13.2357 | 20.4715 | 29.7072
6.6304 | 9.3152 | 8.6304 | 7.6304 | 10.9456 | 12.9456 | 9.3152 | 16.9456 | 27.8912 | 40.8367
5.4603 | 8.7301 | 7.4603 | 6.4603 | 9.1904 | 11.1904 | 8.7301 | 15.1904 | 24.3809 | 35.5713
8.1682 | 10.0841 | 10.1682 | 9.1682 | 13.2523 | 15.2523 | 10.0841 | 19.2523 | 32.5045 | 47.7568
3.1459 | 7.5729 | 5.1459 | 4.1459 | 5.7188 | 7.7188 | 7.5729 | 11.7188 | 17.4377 | 25.1565
5.876 | 8.938 | 7.876 | 6.876 | 9.814 | 11.814 | 8.938 | 15.814 | 25.628 | 37.442
3.0444 | 7.5222 | 5.0444 | 4.0444 | 5.5667 | 7.5667 | 7.5222 | 11.5667 | 17.1333 | 24.7
1.7266 | 6.8633 | 3.7266 | 2.7266 | 3.59 | 5.59 | 6.8633 | 9.59 | 13.1799 | 18.7699
3.978 | 7.989 | 5.978 | 4.978 | 6.967 | 8.967 | 7.989 | 12.967 | 19.934 | 28.901
2.5753 | 7.2877 | 4.5753 | 3.5753 | 4.863 | 6.863 | 7.2877 | 10.863 | 15.726 | 22.589
7.1333 | 9.5667 | 9.1333 | 8.1333 | 11.7 | 13.7 | 9.5667 | 17.7 | 29.4 | 43.1
3.7989 | 7.8995 | 5.7989 | 4.7989 | 6.6984 | 8.6984 | 7.8995 | 12.6984 | 19.3968 | 28.0952
4.1942 | 8.0971 | 6.1942 | 5.1942 | 7.2913 | 9.2913 | 8.0971 | 13.2913 | 20.5826 | 29.8739
6.3221 | 9.161 | 8.3221 | 7.3221 | 10.4831 | 12.4831 | 9.161 | 16.4831 | 26.9663 | 39.4494
6.7721 | 9.386 | 8.7721 | 7.7721 | 11.1581 | 13.1581 | 9.386 | 17.1581 | 28.3163 | 41.4744
2.4844 | 7.2422 | 4.4844 | 3.4844 | 4.7265 | 6.7265 | 7.2422 | 10.7265 | 15.4531 | 22.1796
1.3352 | 6.6676 | 3.3352 | 2.3352 | 3.0029 | 5.0029 | 6.6676 | 9.0029 | 12.0057 | 17.0086
5.3983 | 8.6991 | 7.3983 | 6.3983 | 9.0974 | 11.0974 | 8.6991 | 15.0974 | 24.1948 | 35.2922
4.0997 | 8.0498 | 6.0997 | 5.0997 | 7.1495 | 9.1495 | 8.0498 | 13.1495 | 20.2991 | 29.4486
4.8389 | 8.4194 | 6.8389 | 5.8389 | 8.2583 | 10.2583 | 8.4194 | 14.2583 | 22.5167 | 32.775
8.8632 | 10.4316 | 10.8632 | 9.8632 | 14.2948 | 16.2948 | 10.4316 | 20.2948 | 34.5896 | 50.8844
5.9752 | 8.9876 | 7.9752 | 6.9752 | 9.9628 | 11.9628 | 8.9876 | 15.9628 | 25.9257 | 37.8885
5.6012 | 8.8006 | 7.6012 | 6.6012 | 9.4018 | 11.4018 | 8.8006 | 15.4018 | 24.8036 | 36.2054
4.939 | 8.4695 | 6.939 | 5.939 | 8.4086 | 10.4086 | 8.4695 | 14.4086 | 22.8171 | 33.2257
6.5777 | 9.2889 | 8.5777 | 7.5777 | 10.8666 | 12.8666 | 9.2889 | 16.8666 | 27.7332 | 40.5998
7.5768 | 9.7884 | 9.5768 | 8.5768 | 12.3652 | 14.3652 | 9.7884 | 18.3652 | 30.7305 | 45.0957
6.8322 | 9.4161 | 8.8322 | 7.8322 | 11.2483 | 13.2483 | 9.4161 | 17.2483 | 28.4966 | 41.7449
1.2409 | 6.6205 | 3.2409 | 2.2409 | 2.8614 | 4.8614 | 6.6205 | 8.8614 | 11.7228 | 16.5842
6.8982 | 9.4491 | 8.8982 | 7.8982 | 11.3473 | 13.3473 | 9.4491 | 17.3473 | 28.6945 | 42.0418
5.4805 | 8.7403 | 7.4805 | 6.4805 | 9.2208 | 11.2208 | 8.7403 | 15.2208 | 24.4416 | 35.6624
5.5055 | 8.7528 | 7.5055 | 6.5055 | 9.2583 | 11.2583 | 8.7528 | 15.2583 | 24.5166 | 35.775
6.3791 | 9.1895 | 8.3791 | 7.3791 | 10.5686 | 12.5686 | 9.1895 | 16.5686 | 27.1372 | 39.7057
7.1075 | 9.5538 | 9.1075 | 8.1075 | 11.6613 | 13.6613 | 9.5538 | 17.6613 | 29.3226 | 42.984
4.3758 | 8.1879 | 6.3758 | 5.3758 | 7.5637 | 9.5637 | 8.1879 | 13.5637 | 21.1275 | 30.6912
3.1194 | 7.5597 | 5.1194 | 4.1194 | 5.6791 | 7.6791 | 7.5597 | 11.6791 | 17.3582 | 25.0373
7.0201 | 9.5101 | 9.0201 | 8.0201 | 11.5302 | 13.5302 | 9.5101 | 17.5302 | 29.0604 | 42.5905
7.5622 | 9.7811 | 9.5622 | 8.5622 | 12.3433 | 14.3433 | 9.7811 | 18.3433 | 30.6866 | 45.03 | #REF! | chance that the project will take less than 40 days
6.846 | 9.423 | 8.846 | 7.846 | 11.2689 | 13.2689 | 9.423 | 17.2689 | 28.5379 | 41.8068
4.6009 | 8.3005 | 6.6009 | 5.6009 | 7.9014 | 9.9014 | 8.3005 | 13.9014 | 21.8028 | 31.7043
4.0996 | 8.0498 | 6.0996 | 5.0996 | 7.1495 | 9.1495 | 8.0498 | 13.1495 | 20.2989 | 29.4484
3.9553 | 7.9776 | 5.9553 | 4.9553 | 6.9329 | 8.9329 | 7.9776 | 12.9329 | 19.8658 | 28.7987
6.3421 | 9.1711 | 8.3421 | 7.3421 | 10.5132 | 12.5132 | 9.1711 | 16.5132 | 27.0264 | 39.5396
9.3127 | 10.6563 | 11.3127 | 10.3127 | 14.969 | 16.969 | 10.6563 | 20.969 | 35.9381 | 52.9071
5.4219 | 8.711 | 7.4219 | 6.4219 | 9.1329 | 11.1329 | 8.711 | 15.1329 | 24.2657 | 35.3986
3.6288 | 7.8144 | 5.6288 | 4.6288 | 6.4432 | 8.4432 | 7.8144 | 12.4432 | 18.8865 | 27.3297
5.6238 | 8.8119 | 7.6238 | 6.6238 | 9.4356 | 11.4356 | 8.8119 | 15.4356 | 24.8713 | 36.3069
6.3482 | 9.1741 | 8.3482 | 7.3482 | 10.5223 | 12.5223 | 9.1741 | 16.5223 | 27.0446 | 39.5669
10.7899 | 11.3949 | 12.7899 | 11.7899 | 17.1848 | 19.1848 | 11.3949 | 23.1848 | 40.3696 | 59.5544
4.9975 | 8.4988 | 6.9975 | 5.9975 | 8.4963 | 10.4963 | 8.4988 | 14.4963 | 22.9926 | 33.489
5.1208 | 8.5604 | 7.1208 | 6.1208 | 8.6812 | 10.6812 | 8.5604 | 14.6812 | 23.3625 | 34.0437
4.9466 | 8.4733 | 6.9466 | 5.9466 | 8.4199 | 10.4199 | 8.4733 | 14.4199 | 22.8398 | 33.2597
6.8683 | 9.4342 | 8.8683 | 7.8683 | 11.3025 | 13.3025 | 9.4342 | 17.3025 | 28.605 | 41.9075
6.7307 | 9.3653 | 8.7307 | 7.7307 | 11.096 | 13.096 | 9.3653 | 17.096 | 28.192 | 41.288
6.6858 | 9.3429 | 8.6858 | 7.6858 | 11.0287 | 13.0287 | 9.3429 | 17.0287 | 28.0575 | 41.0862
5.8933 | 8.9466 | 7.8933 | 6.8933 | 9.8399 | 11.8399 | 8.9466 | 15.8399 | 25.6798 | 37.5197
8.0544 | 10.0272 | 10.0544 | 9.0544 | 13.0817 | 15.0817 | 10.0272 | 19.0817 | 32.1633 | 47.245
6.9633 | 9.4817 | 8.9633 | 7.9633 | 11.445 | 13.445 | 9.4817 | 17.445 | 28.89 | 42.335
5.5051 | 8.7525 | 7.5051 | 6.5051 | 9.2576 | 11.2576 | 8.7525 | 15.2576 | 24.5152 | 35.7727
9.8582 | 10.9291 | 11.8582 | 10.8582 | 15.7873 | 17.7873 | 10.9291 | 21.7873 | 37.5746 | 55.3619
6.417 | 9.2085 | 8.417 | 7.417 | 10.6256 | 12.6256 | 9.2085 | 16.6256 | 27.2511 | 39.8767
6.3882 | 9.1941 | 8.3882 | 7.3882 | 10.5822 | 12.5822 | 9.1941 | 16.5822 | 27.1645 | 39.7467
6.9699 | 9.4849 | 8.9699 | 7.9699 | 11.4548 | 13.4548 | 9.4849 | 17.4548 | 28.9096 | 42.3644
8.6251 | 10.3126 | 10.6251 | 9.6251 | 13.9377 | 15.9377 | 10.3126 | 19.9377 | 33.8753 | 49.813
8.9815 | 10.4907 | 10.9815 | 9.9815 | 14.4722 | 16.4722 | 10.4907 | 20.4722 | 34.9444 | 51.4166
8.2166 | 10.1083 | 10.2166 | 9.2166 | 13.3248 | 15.3248 | 10.1083 | 19.3248 | 32.6497 | 47.9745
2.2054 | 7.1027 | 4.2054 | 3.2054 | 4.308 | 6.308 | 7.1027 | 10.308 | 14.6161 | 20.9241
6.4717 | 9.2358 | 8.4717 | 7.4717 | 10.7075 | 12.7075 | 9.2358 | 16.7075 | 27.415 | 40.1224
4.2513 | 8.1257 | 6.2513 | 5.2513 | 7.377 | 9.377 | 8.1257 | 13.377 | 20.754 | 30.131
6.5595 | 9.2797 | 8.5595 | 7.5595 | 10.8392 | 12.8392 | 9.2797 | 16.8392 | 27.6785 | 40.5177
1.7548 | 6.8774 | 3.7548 | 2.7548 | 3.6322 | 5.6322 | 6.8774 | 9.6322 | 13.2644 | 18.8966
9.0243 | 10.5121 | 11.0243 | 10.0243 | 14.5364 | 16.5364 | 10.5121 | 20.5364 | 35.0729 | 51.6093
5.3876 | 8.6938 | 7.3876 | 6.3876 | 9.0814 | 11.0814 | 8.6938 | 15.0814 | 24.1628 | 35.2443
3.3907 | 7.6954 | 5.3907 | 4.3907 | 6.0861 | 8.0861 | 7.6954 | 12.0861 | 18.1721 | 26.2582
6.445 | 9.2225 | 8.445 | 7.445 | 10.6675 | 12.6675 | 9.2225 | 16.6675 | 27.3349 | 40.0024
3.0261 | 7.5131 | 5.0261 | 4.0261 | 5.5392 | 7.5392 | 7.5131 | 11.5392 | 17.0783 | 24.6175
6.1399 | 9.0699 | 8.1399 | 7.1399 | 10.2098 | 12.2098 | 9.0699 | 16.2098 | 26.4196 | 38.6295
2.9477 | 7.4739 | 4.9477 | 3.9477 | 5.4216 | 7.4216 | 7.4739 | 11.4216 | 16.8432 | 24.2647
2.1588 | 7.0794 | 4.1588 | 3.1588 | 4.2382 | 6.2382 | 7.0794 | 10.2382 | 14.4765 | 20.7147
5.37 | 8.685 | 7.37 | 6.37 | 9.0549 | 11.0549 | 8.685 | 15.0549 | 24.1099 | 35.1648
7.0615 | 9.5308 | 9.0615 | 8.0615 | 11.5923 | 13.5923 | 9.5308 | 17.5923 | 29.1846 | 42.7769
2.8948 | 7.4474 | 4.8948 | 3.8948 | 5.3422 | 7.3422 | 7.4474 | 11.3422 | 16.6844 | 24.0266
7.5473 | 9.7737 | 9.5473 | 8.5473 | 12.321 | 14.321 | 9.7737 | 18.321 | 30.6419 | 44.9629
7.1431 | 9.5716 | 9.1431 | 8.1431 | 11.7147 | 13.7147 | 9.5716 | 17.7147 | 29.4293 | 43.144
12.0964 | 12.0482 | 14.0964 | 13.0964 | 19.1446 | 21.1446 | 12.0964 | 25.1928 | 44.3373 | 65.4819
6.765 | 9.3825 | 8.765 | 7.765 | 11.1475 | 13.1475 | 9.3825 | 17.1475 | 28.2951 | 41.4426
2.2718 | 7.1359 | 4.2718 | 3.2718 | 4.4077 | 6.4077 | 7.1359 | 10.4077 | 14.8153 | 21.223
6.4769 | 9.2385 | 8.4769 | 7.4769 | 10.7154 | 12.7154 | 9.2385 | 16.7154 | 27.4308 | 40.1462
5.3268 | 8.6634 | 7.3268 | 6.3268 | 8.9902 | 10.9902 | 8.6634 | 14.9902 | 23.9805 | 34.9707
6.3209 | 9.1605 | 8.3209 | 7.3209 | 10.4814 | 12.4814 | 9.1605 | 16.4814 | 26.9627 | 39.4441
7.5282 | 9.7641 | 9.5282 | 8.5282 | 12.2923 | 14.2923 | 9.7641 | 18.2923 | 30.5847 | 44.877
3.6141 | 7.8071 | 5.6141 | 4.6141 | 6.4212 | 8.4212 | 7.8071 | 12.4212 | 18.8424 | 27.2636
3.6248 | 7.8124 | 5.6248 | 4.6248 | 6.4372 | 8.4372 | 7.8124 | 12.4372 | 18.8744 | 27.3116
7.3335 | 9.6667 | 9.3335 | 8.3335 | 12.0002 | 14.0002 | 9.6667 | 18.0002 | 30.0004 | 44.0006
6.9821 | 9.491 | 8.9821 | 7.9821 | 11.4731 | 13.4731 | 9.491 | 17.4731 | 28.9462 | 42.4193
4.583 | 8.2915 | 6.583 | 5.583 | 7.8745 | 9.8745 | 8.2915 | 13.8745 | 21.749 | 31.6234
4.0577 | 8.0289 | 6.0577 | 5.0577 | 7.0866 | 9.0866 | 8.0289 | 13.0866 | 20.1732 | 29.2598
6.6071 | 9.3035 | 8.6071 | 7.6071 | 10.9106 | 12.9106 | 9.3035 | 16.9106 | 27.8213 | 40.7319
9.0369 | 10.5184 | 11.0369 | 10.0369 | 14.5553 | 16.5553 | 10.5184 | 20.5553 | 35.1106 | 51.6659
7.3809 | 9.6904 | 9.3809 | 8.3809 | 12.0713 | 14.0713 | 9.6904 | 18.0713 | 30.1426 | 44.2139
9.6282 | 10.8141 | 11.6282 | 10.6282 | 15.4423 | 17.4423 | 10.8141 | 21.4423 | 36.8847 | 54.327
6.5968 | 9.2984 | 8.5968 | 7.5968 | 10.8952 | 12.8952 | 9.2984 | 16.8952 | 27.7903 | 40.6855
8.5168 | 10.2584 | 10.5168 | 9.5168 | 13.7751 | 15.7751 | 10.2584 | 19.7751 | 33.5503 | 49.3254
9.0004 | 10.5002 | 11.0004 | 10.0004 | 14.5006 | 16.5006 | 10.5002 | 20.5006 | 35.0013 | 51.5019
6.6461 | 9.3231 | 8.6461 | 7.6461 | 10.9692 | 12.9692 | 9.3231 | 16.9692 | 27.9384 | 40.9076
6.2957 | 9.1479 | 8.2957 | 7.2957 | 10.4436 | 12.4436 | 9.1479 | 16.4436 | 26.8871 | 39.3307
4.6554 | 8.3277 | 6.6554 | 5.6554 | 7.983 | 9.983 | 8.3277 | 13.983 | 21.9661 | 31.9491
5.1508 | 8.5754 | 7.1508 | 6.1508 | 8.7262 | 10.7262 | 8.5754 | 14.7262 | 23.4524 | 34.1786
7.8893 | 9.9446 | 9.8893 | 8.8893 | 12.8339 | 14.8339 | 9.9446 | 18.8339 | 31.6679 | 46.5018
3.7649 | 7.8824 | 5.7649 | 4.7649 | 6.6473 | 8.6473 | 7.8824 | 12.6473 | 19.2946 | 27.9418
5.558 | 8.779 | 7.558 | 6.558 | 9.337 | 11.337 | 8.779 | 15.337 | 24.6741 | 36.0111
7.42 | 9.71 | 9.42 | 8.42 | 12.13 | 14.13 | 9.71 | 18.13 | 30.26 | 44.39
6.472 | 9.236 | 8.472 | 7.472 | 10.708 | 12.708 | 9.236 | 16.708 | 27.416 | 40.124
4.871 | 8.4355 | 6.871 | 5.871 | 8.3066 | 10.3066 | 8.4355 | 14.3066 | 22.6131 | 32.9197
5.508 | 8.754 | 7.508 | 6.508 | 9.2621 | 11.2621 | 8.754 | 15.2621 | 24.5241 | 35.7862
7.0059 | 9.5029 | 9.0059 | 8.0059 | 11.5088 | 13.5088 | 9.5029 | 17.5088 | 29.0177 | 42.5265
7.757 | 9.8785 | 9.757 | 8.757 | 12.6355 | 14.6355 | 9.8785 | 18.6355 | 31.271 | 45.9065
5.623 | 8.8115 | 7.623 | 6.623 | 9.4344 | 11.4344 | 8.8115 | 15.4344 | 24.8689 | 36.3033
8.5794 | 10.2897 | 10.5794 | 9.5794 | 13.869 | 15.869 | 10.2897 | 19.869 | 33.7381 | 49.6071
3.9507 | 7.9753 | 5.9507 | 4.9507 | 6.926 | 8.926 | 7.9753 | 12.926 | 19.852 | 28.778
5.6655 | 8.8328 | 7.6655 | 6.6655 | 9.4983 | 11.4983 | 8.8328 | 15.4983 | 24.9965 | 36.4948
4.9787 | 8.4894 | 6.9787 | 5.9787 | 8.4681 | 10.4681 | 8.4894 | 14.4681 | 22.9362 | 33.4042
7.6227 | 9.8114 | 9.6227 | 8.6227 | 12.4341 | 14.4341 | 9.8114 | 18.4341 | 30.8682 | 45.3023
5.7922 | 8.8961 | 7.7922 | 6.7922 | 9.6883 | 11.6883 | 8.8961 | 15.6883 | 25.3766 | 37.0649
2.9192 | 7.4596 | 4.9192 | 3.9192 | 5.3788 | 7.3788 | 7.4596 | 11.3788 | 16.7575 | 24.1363
5.928 | 8.964 | 7.928 | 6.928 | 9.892 | 11.892 | 8.964 | 15.892 | 25.784 | 37.676
4.208 | 8.104 | 6.208 | 5.208 | 7.312 | 9.312 | 8.104 | 13.312 | 20.6239 | 29.9359
5.2939 | 8.6469 | 7.2939 | 6.2939 | 8.9408 | 10.9408 | 8.6469 | 14.9408 | 23.8817 | 34.8225
6.2531 | 9.1265 | 8.2531 | 7.2531 | 10.3796 | 12.3796 | 9.1265 | 16.3796 | 26.7592 | 39.1388
6.8091 | 9.4046 | 8.8091 | 7.8091 | 11.2137 | 13.2137 | 9.4046 | 17.2137 | 28.4274 | 41.6412
9.4171 | 10.7085 | 11.4171 | 10.4171 | 15.1256 | 17.1256 | 10.7085 | 21.1256 | 36.2512 | 53.3767
5.3234 | 8.6617 | 7.3234 | 6.3234 | 8.9851 | 10.9851 | 8.6617 | 14.9851 | 23.9702 | 34.9553
7.0344 | 9.5172 | 9.0344 | 8.0344 | 11.5515 | 13.5515 | 9.5172 | 17.5515 | 29.1031 | 42.6546
6.5479 | 9.2739 | 8.5479 | 7.5479 | 10.8218 | 12.8218 | 9.2739 | 16.8218 | 27.6437 | 40.4655
6.4934 | 9.2467 | 8.4934 | 7.4934 | 10.7401 | 12.7401 | 9.2467 | 16.7401 | 27.4801 | 40.2202
9.043 | 10.5215 | 11.043 | 10.043 | 14.5645 | 16.5645 | 10.5215 | 20.5645 | 35.1289 | 51.6934
4.2503 | 8.1252 | 6.2503 | 5.2503 | 7.3755 | 9.3755 | 8.1252 | 13.3755 | 20.7509 | 30.1264
4.6551 | 8.3276 | 6.6551 | 5.6551 | 7.9827 | 9.9827 | 8.3276 | 13.9827 | 21.9654 | 31.9481
7.2956 | 9.6478 | 9.2956 | 8.2956 | 11.9435 | 13.9435 | 9.6478 | 17.9435 | 29.8869 | 43.8304
6.1556 | 9.0778 | 8.1556 | 7.1556 | 10.2334 | 12.2334 | 9.0778 | 16.2334 | 26.4668 | 38.7002
6.6144 | 9.3072 | 8.6144 | 7.6144 | 10.9216 | 12.9216 | 9.3072 | 16.9216 | 27.8432 | 40.7648
5.303 | 8.6515 | 7.303 | 6.303 | 8.9545 | 10.9545 | 8.6515 | 14.9545 | 23.9091 | 34.8636
5.1456 | 8.5728 | 7.1456 | 6.1456 | 8.7184 | 10.7184 | 8.5728 | 14.7184 | 23.4369 | 34.1553
9.5864 | 10.7932 | 11.5864 | 10.5864 | 15.3796 | 17.3796 | 10.7932 | 21.3796 | 36.7592 | 54.1388
2.3841 | 7.1921 | 4.3841 | 3.3841 | 4.5762 | 6.5762 | 7.1921 | 10.5762 | 15.1524 | 21.7285
5.619 | 8.8095 | 7.619 | 6.619 | 9.4285 | 11.4285 | 8.8095 | 15.4285 | 24.8571 | 36.2856
9.1739 | 10.587 | 11.1739 | 10.1739 | 14.7609 | 16.7609 | 10.587 | 20.7609 | 35.5217 | 52.2826
5.5091 | 8.7545 | 7.5091 | 6.5091 | 9.2636 | 11.2636 | 8.7545 | 15.2636 | 24.5272 | 35.7908
1.6872 | 6.8436 | 3.6872 | 2.6872 | 3.5309 | 5.5309 | 6.8436 | 9.5309 | 13.0617 | 18.5926
9.6443 | 10.8221 | 11.6443 | 10.6443 | 15.4664 | 17.4664 | 10.8221 | 21.4664 | 36.9328 | 54.3992 | #REF!
8.6989 | 10.3495 | 10.6989 | 9.6989 | 14.0484 | 16.0484 | 10.3495 | 20.0484 | 34.0968 | 50.1452
11.2292 | 11.6146 | 13.2292 | 12.2292 | 17.8437 | 19.8437 | 11.6146 | 23.8437 | 41.6875 | 61.5312
8.8814 | 10.4407 | 10.8814 | 9.8814 | 14.322 | 16.322 | 10.4407 | 20.322 | 34.6441 | 50.9661
4.2468 | 8.1234 | 6.2468 | 5.2468 | 7.3702 | 9.3702 | 8.1234 | 13.3702 | 20.7403 | 30.1105
4.0644 | 8.0322 | 6.0644 | 5.0644 | 7.0967 | 9.0967 | 8.0322 | 13.0967 | 20.1933 | 29.29
6.9188 | 9.4594 | 8.9188 | 7.9188 | 11.3781 | 13.3781 | 9.4594 | 17.3781 | 28.7563 | 42.1344
6.6996 | 9.3498 | 8.6996 | 7.6996 | 11.0495 | 13.0495 | 9.3498 | 17.0495 | 28.0989 | 41.1484
2.8424 | 7.4212 | 4.8424 | 3.8424 | 5.2635 | 7.2635 | 7.4212 | 11.2635 | 16.5271 | 23.7906
4.0657 | 8.0328 | 6.0657 | 5.0657 | 7.0985 | 9.0985 | 8.0328 | 13.0985 | 20.197 | 29.2955
4.7146 | 8.3573 | 6.7146 | 5.7146 | 8.0719 | 10.0719 | 8.3573 | 14.0719 | 22.1437 | 32.2156
4.7268 | 8.3634 | 6.7268 | 5.7268 | 8.0902 | 10.0902 | 8.3634 | 14.0902 | 22.1804 | 32.2706
6.8306 | 9.4153 | 8.8306 | 7.8306 | 11.2459 | 13.2459 | 9.4153 | 17.2459 | 28.4919 | 41.7378
3.8975 | 7.9488 | 5.8975 | 4.8975 | 6.8463 | 8.8463 | 7.9488 | 12.8463 | 19.6926 | 28.5389
5.9003 | 8.9501 | 7.9003 | 6.9003 | 9.8504 | 11.8504 | 8.9501 | 15.8504 | 25.7009 | 37.5513
5.3318 | 8.6659 | 7.3318 | 6.3318 | 8.9977 | 10.9977 | 8.6659 | 14.9977 | 23.9954 | 34.993
4.9579 | 8.4789 | 6.9579 | 5.9579 | 8.4368 | 10.4368 | 8.4789 | 14.4368 | 22.8736 | 33.3104
6.4693 | 9.2346 | 8.4693 | 7.4693 | 10.7039 | 12.7039 | 9.2346 | 16.7039 | 27.4078 | 40.1117
5.5471 | 8.7735 | 7.5471 | 6.5471 | 9.3206 | 11.3206 | 8.7735 | 15.3206 | 24.6413 | 35.9619
9.9466 | 10.9733 | 11.9466 | 10.9466 | 15.9199 | 17.9199 | 10.9733 | 21.9199 | 37.8399 | 55.7598
7.4375 | 9.7188 | 9.4375 | 8.4375 | 12.1563 | 14.1563 | 9.7188 | 18.1563 | 30.3126 | 44.469
4.3121 | 8.1561 | 6.3121 | 5.3121 | 7.4682 | 9.4682 | 8.1561 | 13.4682 | 20.9364 | 30.4045
5.9724 | 8.9862 | 7.9724 | 6.9724 | 9.9586 | 11.9586 | 8.9862 | 15.9586 | 25.9171 | 37.8757
8.7536 | 10.3768 | 10.7536 | 9.7536 | 14.1304 | 16.1304 | 10.3768 | 20.1304 | 34.2609 | 50.3913
5.5862 | 8.7931 | 7.5862 | 6.5862 | 9.3793 | 11.3793 | 8.7931 | 15.3793 | 24.7586 | 36.138
3.4881 | 7.744 | 5.4881 | 4.4881 | 6.2321 | 8.2321 | 7.744 | 12.2321 | 18.4642 | 26.6963
5.5062 | 8.7531 | 7.5062 | 6.5062 | 9.2593 | 11.2593 | 8.7531 | 15.2593 | 24.5187 | 35.778
7.6439 | 9.822 | 9.6439 | 8.6439 | 12.4659 | 14.4659 | 9.822 | 18.4659 | 30.9318 | 45.3977
5.254 | 8.627 | 7.254 | 6.254 | 8.8809 | 10.8809 | 8.627 | 14.8809 | 23.7619 | 34.6428
4.2232 | 8.1116 | 6.2232 | 5.2232 | 7.3348 | 9.3348 | 8.1116 | 13.3348 | 20.6696 | 30.0044
6.8151 | 9.4076 | 8.8151 | 7.8151 | 11.2227 | 13.2227 | 9.4076 | 17.2227 | 28.4453 | 41.668
5.3333 | 8.6667 | 7.3333 | 6.3333 | 9 | 11 | 8.6667 | 15 | 24 | 34.9999
4.0377 | 8.0189 | 6.0377 | 5.0377 | 7.0566 | 9.0566 | 8.0189 | 13.0566 | 20.1131 | 29.1697
8.7767 | 10.3884 | 10.7767 | 9.7767 | 14.1651 | 16.1651 | 10.3884 | 20.1651 | 34.3302 | 50.4953
4.2765 | 8.1383 | 6.2765 | 5.2765 | 7.4148 | 9.4148 | 8.1383 | 13.4148 | 20.8296 | 30.2443
6.1788 | 9.0894 | 8.1788 | 7.1788 | 10.2683 | 12.2683 | 9.0894 | 16.2683 | 26.5365 | 38.8048
4.8286 | 8.4143 | 6.8286 | 5.8286 | 8.2429 | 10.2429 | 8.4143 | 14.2429 | 22.4857 | 32.7286
7.1539 | 9.577 | 9.1539 | 8.1539 | 11.7309 | 13.7309 | 9.577 | 17.7309 | 29.4618 | 43.1927
7.5051 | 9.7525 | 9.5051 | 8.5051 | 12.2576 | 14.2576 | 9.7525 | 18.2576 | 30.5152 | 44.7728
8.6284 | 10.3142 | 10.6284 | 9.6284 | 13.9426 | 15.9426 | 10.3142 | 19.9426 | 33.8852 | 49.8278
6.4705 | 9.2352 | 8.4705 | 7.4705 | 10.7057 | 12.7057 | 9.2352 | 16.7057 | 27.4114 | 40.1171
5.1058 | 8.5529 | 7.1058 | 6.1058 | 8.6586 | 10.6586 | 8.5529 | 14.6586 | 23.3173 | 33.9759
6.1713 | 9.0857 | 8.1713 | 7.1713 | 10.257 | 12.257 | 9.0857 | 16.257 | 26.514 | 38.7709
3.8207 | 7.9104 | 5.8207 | 4.8207 | 6.7311 | 8.7311 | 7.9104 | 12.7311 | 19.4621 | 28.1932
4.6634 | 8.3317 | 6.6634 | 5.6634 | 7.9952 | 9.9952 | 8.3317 | 13.9952 | 21.9903 | 31.9855
9.839 | 10.9195 | 11.839 | 10.839 | 15.7585 | 17.7585 | 10.9195 | 21.7585 | 37.5171 | 55.2756
5.9254 | 8.9627 | 7.9254 | 6.9254 | 9.8881 | 11.8881 | 8.9627 | 15.8881 | 25.7762 | 37.6643
5.9787 | 8.9893 | 7.9787 | 6.9787 | 9.968 | 11.968 | 8.9893 | 15.968 | 25.936 | 37.9041
2.3372 | 7.1686 | 4.3372 | 3.3372 | 4.5058 | 6.5058 | 7.1686 | 10.5058 | 15.0116 | 21.5174
5.4146 | 8.7073 | 7.4146 | 6.4146 | 9.1219 | 11.1219 | 8.7073 | 15.1219 | 24.2438 | 35.3657
6.6838 | 9.3419 | 8.6838 | 7.6838 | 11.0257 | 13.0257 | 9.3419 | 17.0257 | 28.0514 | 41.077
1.2105 | 6.6053 | 3.2105 | 2.2105 | 2.8158 | 4.8158 | 6.6053 | 8.8158 | 11.6316 | 16.4474
7.4824 | 9.7412 | 9.4824 | 8.4824 | 12.2237 | 14.2237 | 9.7412 | 18.2237 | 30.4473 | 44.671
6.0927 | 9.0463 | 8.0927 | 7.0927 | 10.139 | 12.139 | 9.0463 | 16.139 | 26.2781 | 38.4171
3.9913 | 7.9956 | 5.9913 | 4.9913 | 6.9869 | 8.9869 | 7.9956 | 12.9869 | 19.9739 | 28.9608
8.1269 | 10.0635 | 10.1269 | 9.1269 | 13.1904 | 15.1904 | 10.0635 | 19.1904 | 32.3808 | 47.5712
5.4364 | 8.7182 | 7.4364 | 6.4364 | 9.1546 | 11.1546 | 8.7182 | 15.1546 | 24.3092 | 35.4638
7.1821 | 9.591 | 9.1821 | 8.1821 | 11.7731 | 13.7731 | 9.591 | 17.7731 | 29.5463 | 43.3194
5.2544 | 8.6272 | 7.2544 | 6.2544 | 8.8816 | 10.8816 | 8.6272 | 14.8816 | 23.7633 | 34.6449
6.9219 | 9.461 | 8.9219 | 7.9219 | 11.3829 | 13.3829 | 9.461 | 17.3829 | 28.7658 | 42.1486
4.2326 | 8.1163 | 6.2326 | 5.2326 | 7.3488 | 9.3488 | 8.1163 | 13.3488 | 20.6977 | 30.0465
7.8659 | 9.9329 | 9.8659 | 8.8659 | 12.7988 | 14.7988 | 9.9329 | 18.7988 | 31.5977 | 46.3965
6.8237 | 9.4119 | 8.8237 | 7.8237 | 11.2356 | 13.2356 | 9.4119 | 17.2356 | 28.4712 | 41.7068
10.0714 | 11.0357 | 12.0714 | 11.0714 | 16.1071 | 18.1071 | 11.0357 | 22.1071 | 38.2142 | 56.3213
8.6333 | 10.3167 | 10.6333 | 9.6333 | 13.95 | 15.95 | 10.3167 | 19.95 | 33.8999 | 49.8499
6.1212 | 9.0606 | 8.1212 | 7.1212 | 10.1818 | 12.1818 | 9.0606 | 16.1818 | 26.3636 | 38.5454
6.3032 | 9.1516 | 8.3032 | 7.3032 | 10.4548 | 12.4548 | 9.1516 | 16.4548 | 26.9097 | 39.3645
4.3758 | 8.1879 | 6.3758 | 5.3758 | 7.5637 | 9.5637 | 8.1879 | 13.5637 | 21.1273 | 30.691
9.2988 | 10.6494 | 11.2988 | 10.2988 | 14.9482 | 16.9482 | 10.6494 | 20.9482 | 35.8964 | 52.8446
6.0363 | 9.0181 | 8.0363 | 7.0363 | 10.0544 | 12.0544 | 9.0181 | 16.0544 | 26.1089 | 38.1633
4.0855 | 8.0427 | 6.0855 | 5.0855 | 7.1282 | 9.1282 | 8.0427 | 13.1282 | 20.2564 | 29.3846
2.5889 | 7.2945 | 4.5889 | 3.5889 | 4.8834 | 6.8834 | 7.2945 | 10.8834 | 15.7668 | 22.6502
5.0002 | 8.5001 | 7.0002 | 6.0002 | 8.5003 | 10.5003 | 8.5001 | 14.5003 | 23.0006 | 33.5009
3.9935 | 7.9967 | 5.9935 | 4.9935 | 6.9902 | 8.9902 | 7.9967 | 12.9902 | 19.9804 | 28.9706
4.5745 | 8.2872 | 6.5745 | 5.5745 | 7.8617 | 9.8617 | 8.2872 | 13.8617 | 21.7234 | 31.5851
9.9779 | 10.9889 | 11.9779 | 10.9779 | 15.9668 | 17.9668 | 10.9889 | 21.9668 | 37.9337 | 55.9005
5.9845 | 8.9923 | 7.9845 | 6.9845 | 9.9768 | 11.9768 | 8.9923 | 15.9768 | 25.9536 | 37.9304
6.7095 | 9.3548 | 8.7095 | 7.7095 | 11.0643 | 13.0643 | 9.3548 | 17.0643 | 28.1286 | 41.1928
4.33 | 8.165 | 6.33 | 5.33 | 7.4951 | 9.4951 | 8.165 | 13.4951 | 20.9901 | 30.4852
7.3109 | 9.6554 | 9.3109 | 8.3109 | 11.9663 | 13.9663 | 9.6554 | 17.9663 | 29.9327 | 43.899
8.3704 | 10.1852 | 10.3704 | 9.3704 | 13.5557 | 15.5557 | 10.1852 | 19.5557 | 33.1113 | 48.667
5.3059 | 8.6529 | 7.3059 | 6.3059 | 8.9588 | 10.9588 | 8.6529 | 14.9588 | 23.9177 | 34.8765
5.3629 | 8.6814 | 7.3629 | 6.3629 | 9.0443 | 11.0443 | 8.6814 | 15.0443 | 24.0887 | 35.133
3.9816 | 7.9908 | 5.9816 | 4.9816 | 6.9725 | 8.9725 | 7.9908 | 12.9725 | 19.9449 | 28.9174
5.3166 | 8.6583 | 7.3166 | 6.3166 | 8.9749 | 10.9749 | 8.6583 | 14.9749 | 23.9499 | 34.9248
4.8471 | 8.4235 | 6.8471 | 5.8471 | 8.2706 | 10.2706 | 8.4235 | 14.2706 | 22.5412 | 32.8118
3.4432 | 7.7216 | 5.4432 | 4.4432 | 6.1648 | 8.1648 | 7.7216 | 12.1648 | 18.3295 | 26.4943
9.9646 | 10.9823 | 11.9646 | 10.9646 | 15.9469 | 17.9469 | 10.9823 | 21.9469 | 37.8938 | 55.8407
4.8739 | 8.4369 | 6.8739 | 5.8739 | 8.3108 | 10.3108 | 8.4369 | 14.3108 | 22.6217 | 32.9325
6.177 | 9.0885 | 8.177 | 7.177 | 10.2655 | 12.2655 | 9.0885 | 16.2655 | 26.531 | 38.7965
3.7875 | 7.8937 | 5.7875 | 4.7875 | 6.6812 | 8.6812 | 7.8937 | 12.6812 | 19.3625 | 28.0437
5.0807 | 8.5403 | 7.0807 | 6.0807 | 8.621 | 10.621 | 8.5403 | 14.621 | 23.242 | 33.863
6.5686 | 9.2843 | 8.5686 | 7.5686 | 10.8529 | 12.8529 | 9.2843 | 16.8529 | 27.7059 | 40.5588
5.8438 | 8.9219 | 7.8438 | 6.8438 | 9.7658 | 11.7658 | 8.9219 | 15.7658 | 25.5315 | 37.2973
6.0958 | 9.0479 | 8.0958 | 7.0958 | 10.1438 | 12.1438 | 9.0479 | 16.1438 | 26.2875 | 38.4313
6.9493 | 9.4746 | 8.9493 | 7.9493 | 11.4239 | 13.4239 | 9.4746 | 17.4239 | 28.8478 | 42.2717
5.2162 | 8.6081 | 7.2162 | 6.2162 | 8.8242 | 10.8242 | 8.6081 | 14.8242 | 23.6485 | 34.4727
5.5135 | 8.7568 | 7.5135 | 6.5135 | 9.2703 | 11.2703 | 8.7568 | 15.2703 | 24.5406 | 35.8109
6.4323 | 9.2162 | 8.4323 | 7.4323 | 10.6485 | 12.6485 | 9.2162 | 16.6485 | 27.2969 | 39.9454
6.5298 | 9.2649 | 8.5298 | 7.5298 | 10.7947 | 12.7947 | 9.2649 | 16.7947 | 27.5894 | 40.3841
3.6047 | 7.8023 | 5.6047 | 4.6047 | 6.407 | 8.407 | 7.8023 | 12.407 | 18.814 | 27.221
6.5074 | 9.2537 | 8.5074 | 7.5074 | 10.761 | 12.761 | 9.2537 | 16.761 | 27.5221 | 40.2831
5.3909 | 8.6955 | 7.3909 | 6.3909 | 9.0864 | 11.0864 | 8.6955 | 15.0864 | 24.1728 | 35.2592
7.3437 | 9.6719 | 9.3437 | 8.3437 | 12.0156 | 14.0156 | 9.6719 | 18.0156 | 30.0312 | 44.0468
4.6308 | 8.3154 | 6.6308 | 5.6308 | 7.9462 | 9.9462 | 8.3154 | 13.9462 | 21.8924 | 31.8386
9.6453 | 10.8227 | 11.6453 | 10.6453 | 15.468 | 17.468 | 10.8227 | 21.468 | 36.936 | 54.404
6.4225 | 9.2112 | 8.4225 | 7.4225 | 10.6337 | 12.6337 | 9.2112 | 16.6337 | 27.2675 | 39.9012
5.6668 | 8.8334 | 7.6668 | 6.6668 | 9.5002 | 11.5002 | 8.8334 | 15.5002 | 25.0004 | 36.5007
6.74 | 9.37 | 8.74 | 7.74 | 11.11 | 13.11 | 9.37 | 17.11 | 28.22 | 41.3301
9.1685 | 10.5842 | 11.1685 | 10.1685 | 14.7527 | 16.7527 | 10.5842 | 20.7527 | 35.5054 | 52.258
4.3763 | 8.1881 | 6.3763 | 5.3763 | 7.5644 | 9.5644 | 8.1881 | 13.5644 | 21.1288 | 30.6933
4.1411 | 8.0705 | 6.1411 | 5.1411 | 7.2116 | 9.2116 | 8.0705 | 13.2116 | 20.4233 | 29.6349
6.171 | 9.0855 | 8.171 | 7.171 | 10.2565 | 12.2565 | 9.0855 | 16.2565 | 26.5131 | 38.7696
3.8576 | 7.9288 | 5.8576 | 4.8576 | 6.7865 | 8.7865 | 7.9288 | 12.7865 | 19.5729 | 28.3594
5.1285 | 8.5643 | 7.1285 | 6.1285 | 8.6928 | 10.6928 | 8.5643 | 14.6928 | 23.3855 | 34.0783
7.0864 | 9.5432 | 9.0864 | 8.0864 | 11.6296 | 13.6296 | 9.5432 | 17.6296 | 29.2592 | 42.8887
4.1163 | 8.0582 | 6.1163 | 5.1163 | 7.1745 | 9.1745 | 8.0582 | 13.1745 | 20.349 | 29.5235
8.9564 | 10.4782 | 10.9564 | 9.9564 | 14.4346 | 16.4346 | 10.4782 | 20.4346 | 34.8692 | 51.3037
8.7441 | 10.3721 | 10.7441 | 9.7441 | 14.1162 | 16.1162 | 10.3721 | 20.1162 | 34.2324 | 50.3486
2.74 | 7.37 | 4.74 | 3.74 | 5.1101 | 7.1101 | 7.37 | 11.1101 | 16.2201 | 23.3302
5.7804 | 8.8902 | 7.7804 | 6.7804 | 9.6707 | 11.6707 | 8.8902 | 15.6707 | 25.3413 | 37.012
8.5548 | 10.2774 | 10.5548 | 9.5548 | 13.8321 | 15.8321 | 10.2774 | 19.8321 | 33.6643 | 49.4964
9.7354 | 10.8677 | 11.7354 | 10.7354 | 15.6031 | 17.6031 | 10.8677 | 21.6031 | 37.2063 | 54.8094
6.7498 | 9.3749 | 8.7498 | 7.7498 | 11.1247 | 13.1247 | 9.3749 | 17.1247 | 28.2493 | 41.374
5.8147 | 8.9074 | 7.8147 | 6.8147 | 9.7221 | 11.7221 | 8.9074 | 15.7221 | 25.4441 | 37.1662
4.1528 | 8.0764 | 6.1528 | 5.1528 | 7.2293 | 9.2293 | 8.0764 | 13.2293 | 20.4585 | 29.6878
3.9873 | 7.9937 | 5.9873 | 4.9873 | 6.981 | 8.981 | 7.9937 | 12.981 | 19.962 | 28.943
7.9613 | 9.9807 | 9.9613 | 8.9613 | 12.942 | 14.942 | 9.9807 | 18.942 | 31.8839 | 46.8259
2.9631 | 7.4816 | 4.9631 | 3.9631 | 5.4447 | 7.4447 | 7.4816 | 11.4447 | 16.8894 | 24.3341
4.718 | 8.359 | 6.718 | 5.718 | 8.077 | 10.077 | 8.359 | 14.077 | 22.154 | 32.231
6.5567 | 9.2783 | 8.5567 | 7.5567 | 10.835 | 12.835 | 9.2783 | 16.835 | 27.67 | 40.5051
9.2868 | 10.6434 | 11.2868 | 10.2868 | 14.9302 | 16.9302 | 10.6434 | 20.9302 | 35.8604 | 52.7905
3.6374 | 7.8187 | 5.6374 | 4.6374 | 6.4561 | 8.4561 | 7.8187 | 12.4561 | 18.9123 | 27.3684
7.1885 | 9.5943 | 9.1885 | 8.1885 | 11.7828 | 13.7828 | 9.5943 | 17.7828 | 29.5656 | 43.3484
5.7584 | 8.8792 | 7.7584 | 6.7584 | 9.6376 | 11.6376 | 8.8792 | 15.6376 | 25.2751 | 36.9127
5.6182 | 8.8091 | 7.6182 | 6.6182 | 9.4274 | 11.4274 | 8.8091 | 15.4274 | 24.8547 | 36.2821
5.3742 | 8.6871 | 7.3742 | 6.3742 | 9.0613 | 11.0613 | 8.6871 | 15.0613 | 24.1225 | 35.1838
4.0427 | 8.0214 | 6.0427 | 5.0427 | 7.0641 | 9.0641 | 8.0214 | 13.0641 | 20.1282 | 29.1922
5.0499 | 8.525 | 7.0499 | 6.0499 | 8.5749 | 10.5749 | 8.525 | 14.5749 | 23.1497 | 33.7246
4.0014 | 8.0007 | 6.0014 | 5.0014 | 7.002 | 9.002 | 8.0007 | 13.002 | 20.0041 | 29.0061
4.888 | 8.444 | 6.888 | 5.888 | 8.332 | 10.332 | 8.444 | 14.332 | 22.664 | 32.9959
9.4534 | 10.7267 | 11.4534 | 10.4534 | 15.18 | 17.18 | 10.7267 | 21.18 | 36.3601 | 53.5401
4.3719 | 8.186 | 6.3719 | 5.3719 | 7.5579 | 9.5579 | 8.186 | 13.5579 | 21.1157 | 30.6736
6.7859 | 9.393 | 8.7859 | 7.7859 | 11.1789 | 13.1789 | 9.393 | 17.1789 | 28.3578 | 41.5367
2.921 | 7.4605 | 4.921 | 3.921 | 5.3815 | 7.3815 | 7.4605 | 11.3815 | 16.763 | 24.1445
5.273 | 8.6365 | 7.273 | 6.273 | 8.9094 | 10.9094 | 8.6365 | 14.9094 | 23.8189 | 34.7283
7.2406 | 9.6203 | 9.2406 | 8.2406 | 11.8609 | 13.8609 | 9.6203 | 17.8609 | 29.7219 | 43.5828
6.9972 | 9.4986 | 8.9972 | 7.9972 | 11.4958 | 13.4958 | 9.4986 | 17.4958 | 28.9915 | 42.4873
2.7682 | 7.3841 | 4.7682 | 3.7682 | 5.1523 | 7.1523 | 7.3841 | 11.1523 | 16.3046 | 23.4569
7.3579 | 9.679 | 9.3579 | 8.3579 | 12.0369 | 14.0369 | 9.679 | 18.0369 | 30.0738 | 44.1108
4.0153 | 8.0077 | 6.0153 | 5.0153 | 7.023 | 9.023 | 8.0077 | 13.023 | 20.046 | 29.0691
7.981 | 9.9905 | 9.981 | 8.981 | 12.9716 | 14.9716 | 9.9905 | 18.9716 | 31.9431 | 46.9147
7.4117 | 9.7058 | 9.4117 | 8.4117 | 12.1175 | 14.1175 | 9.7058 | 18.1175 | 30.2351 | 44.3526
9.3358 | 10.6679 | 11.3358 | 10.3358 | 15.0036 | 17.0036 | 10.6679 | 21.0036 | 36.0073 | 53.0109
7.7372 | 9.8686 | 9.7372 | 8.7372 | 12.6059 | 14.6059 | 9.8686 | 18.6059 | 31.2117 | 45.8176
4.255 | 8.1275 | 6.255 | 5.255 | 7.3826 | 9.3826 | 8.1275 | 13.3826 | 20.7651 | 30.1477
3.1525 | 7.5763 | 5.1525 | 4.1525 | 5.7288 | 7.7288 | 7.5763 | 11.7288 | 17.4576 | 25.1864
6.2043 | 9.1021 | 8.2043 | 7.2043 | 10.3064 | 12.3064 | 9.1021 | 16.3064 | 26.6128 | 38.9192
3.9566 | 7.9783 | 5.9566 | 4.9566 | 6.9349 | 8.9349 | 7.9783 | 12.9349 | 19.8699 | 28.8048
4.8382 | 8.4191 | 6.8382 | 5.8382 | 8.2573 | 10.2573 | 8.4191 | 14.2573 | 22.5146 | 32.7718
8.832 | 10.416 | 10.832 | 9.832 | 14.248 | 16.248 | 10.416 | 20.248 | 34.496 | 50.744
6.1256 | 9.0628 | 8.1256 | 7.1256 | 10.1883 | 12.1883 | 9.0628 | 16.1883 | 26.3767 | 38.565
3.7788 | 7.8894 | 5.7788 | 4.7788 | 6.6682 | 8.6682 | 7.8894 | 12.6682 | 19.3364 | 28.0046
6.2079 | 9.1039 | 8.2079 | 7.2079 | 10.3118 | 12.3118 | 9.1039 | 16.3118 | 26.6236 | 38.9354
3.5199 | 7.7599 | 5.5199 | 4.5199 | 6.2798 | 8.2798 | 7.7599 | 12.2798 | 18.5596 | 26.8395
5.2902 | 8.6451 | 7.2902 | 6.2902 | 8.9353 | 10.9353 | 8.6451 | 14.9353 | 23.8707 | 34.806
0.22536 | 6.1127 | 2.2254 | 1.2254 | 1.338 | 3.338 | 6.1127 | 7.338 | 8.6761 | 12.0141
6.7913 | 9.3957 | 8.7913 | 7.7913 | 11.187 | 13.187 | 9.3957 | 17.187 | 28.374 | 41.5611
8.3235 | 10.1617 | 10.3235 | 9.3235 | 13.4852 | 15.4852 | 10.1617 | 19.4852 | 32.9704 | 48.4556
4.5906 | 8.2953 | 6.5906 | 5.5906 | 7.886 | 9.886 | 8.2953 | 13.886 | 21.7719 | 31.6579
3.9131 | 7.9566 | 5.9131 | 4.9131 | 6.8697 | 8.8697 | 7.9566 | 12.8697 | 19.7394 | 28.609
6.9782 | 9.4891 | 8.9782 | 7.9782 | 11.4673 | 13.4673 | 9.4891 | 17.4673 | 28.9346 | 42.4018
6.9963 | 9.4981 | 8.9963 | 7.9963 | 11.4944 | 13.4944 | 9.4981 | 17.4944 | 28.9889 | 42.4833
5.7612 | 8.8806 | 7.7612 | 6.7612 | 9.6418 | 11.6418 | 8.8806 | 15.6418 | 25.2835 | 36.9253
7.1508 | 9.5754 | 9.1508 | 8.1508 | 11.7262 | 13.7262 | 9.5754 | 17.7262 | 29.4524 | 43.1786
8.0391 | 10.0196 | 10.0391 | 9.0391 | 13.0587 | 15.0587 | 10.0196 | 19.0587 | 32.1174 | 47.1761
4.834 | 8.417 | 6.834 | 5.834 | 8.2511 | 10.2511 | 8.417 | 14.2511 | 22.5021 | 32.7532
4.3051 | 8.1526 | 6.3051 | 5.3051 | 7.4577 | 9.4577 | 8.1526 | 13.4577 | 20.9154 | 30.3731
3.4266 | 7.7133 | 5.4266 | 4.4266 | 6.1399 | 8.1399 | 7.7133 | 12.1399 | 18.2798 | 26.4198
6.4406 | 9.2203 | 8.4406 | 7.4406 | 10.6608 | 12.6608 | 9.2203 | 16.6608 | 27.3217 | 39.9825
6.6586 | 9.3293 | 8.6586 | 7.6586 | 10.9878 | 12.9878 | 9.3293 | 16.9878 | 27.9757 | 40.9635
3.0639 | 7.532 | 5.0639 | 4.0639 | 5.5959 | 7.5959 | 7.532 | 11.5959 | 17.1918 | 24.7877
3.5654 | 7.7827 | 5.5654 | 4.5654 | 6.3482 | 8.3482 | 7.7827 | 12.3482 | 18.6963 | 27.0445
4.057 | 8.0285 | 6.057 | 5.057 | 7.0855 | 9.0855 | 8.0285 | 13.0855 | 20.1709 | 29.2564
1.4505 | 6.7252 | 3.4505 | 2.4505 | 3.1757 | 5.1757 | 6.7252 | 9.1757 | 12.3514 | 17.527
6.5149 | 9.2574 | 8.5149 | 7.5149 | 10.7723 | 12.7723 | 9.2574 | 16.7723 | 27.5446 | 40.3169
7.2334 | 9.6167 | 9.2334 | 8.2334 | 11.8501 | 13.8501 | 9.6167 | 17.8501 | 29.7001 | 43.5502
6.6848 | 9.3424 | 8.6848 | 7.6848 | 11.0272 | 13.0272 | 9.3424 | 17.0272 | 28.0543 | 41.0815
3.5748 | 7.7874 | 5.5748 | 4.5748 | 6.3623 | 8.3623 | 7.7874 | 12.3623 | 18.7245 | 27.0868
4.5511 | 8.2755 | 6.5511 | 5.5511 | 7.8266 | 9.8266 | 8.2755 | 13.8266 | 21.6532 | 31.4798
5.3338 | 8.6669 | 7.3338 | 6.3338 | 9.0007 | 11.0007 | 8.6669 | 15.0007 | 24.0014 | 35.0022
7.2404 | 9.6202 | 9.2404 | 8.2404 | 11.8606 | 13.8606 | 9.6202 | 17.8606 | 29.7211 | 43.5817
10.1468 | 11.0734 | 12.1468 | 11.1468 | 16.2203 | 18.2203 | 11.0734 | 22.2203 | 38.4405 | 56.6608
6.2529 | 9.1264 | 8.2529 | 7.2529 | 10.3793 | 12.3793 | 9.1264 | 16.3793 | 26.7586 | 39.1379
9.755 | 10.8775 | 11.755 | 10.755 | 15.6326 | 17.6326 | 10.8775 | 21.6326 | 37.2651 | 54.8977
2.6007 | 7.3004 | 4.6007 | 3.6007 | 4.9011 | 6.9011 | 7.3004 | 10.9011 | 15.8022 | 22.7034
6.491 | 9.2455 | 8.491 | 7.491 | 10.7365 | 12.7365 | 9.2455 | 16.7365 | 27.4729 | 40.2094
3.7051 | 7.8525 | 5.7051 | 4.7051 | 6.5576 | 8.5576 | 7.8525 | 12.5576 | 19.1153 | 27.6729
8.8596 | 10.4298 | 10.8596 | 9.8596 | 14.2894 | 16.2894 | 10.4298 | 20.2894 | 34.5788 | 50.8682
4.0418 | 8.0209 | 6.0418 | 5.0418 | 7.0627 | 9.0627 | 8.0209 | 13.0627 | 20.1254 | 29.1881
5.4082 | 8.7041 | 7.4082 | 6.4082 | 9.1122 | 11.1122 | 8.7041 | 15.1122 | 24.2245 | 35.3367
9.0073 | 10.5036 | 11.0073 | 10.0073 | 14.5109 | 16.5109 | 10.5036 | 20.5109 | 35.0219 | 51.5328
3.2126 | 7.6063 | 5.2126 | 4.2126 | 5.8188 | 7.8188 | 7.6063 | 11.8188 | 17.6377 | 25.4565
3.8567 | 7.9284 | 5.8567 | 4.8567 | 6.7851 | 8.7851 | 7.9284 | 12.7851 | 19.5702 | 28.3553
6.5668 | 9.2834 | 8.5668 | 7.5668 | 10.8501 | 12.8501 | 9.2834 | 16.8501 | 27.7003 | 40.5504
5.6779 | 8.839 | 7.6779 | 6.6779 | 9.5169 | 11.5169 | 8.839 | 15.5169 | 25.0337 | 36.5506
5.0931 | 8.5465 | 7.0931 | 6.0931 | 8.6396 | 10.6396 | 8.5465 | 14.6396 | 23.2793 | 33.9189
3.8637 | 7.9319 | 5.8637 | 4.8637 | 6.7956 | 8.7956 | 7.9319 | 12.7956 | 19.5912 | 28.3868
8.1234 | 10.0617 | 10.1234 | 9.1234 | 13.1851 | 15.1851 | 10.0617 | 19.1851 | 32.3703 | 47.5554
7.0773 | 9.5386 | 9.0773 | 8.0773 | 11.6159 | 13.6159 | 9.5386 | 17.6159 | 29.2318 | 42.8477
7.3068 | 9.6534 | 9.3068 | 8.3068 | 11.9602 | 13.9602 | 9.6534 | 17.9602 | 29.9205 | 43.8807
8.2874 | 10.1437 | 10.2874 | 9.2874 | 13.4311 | 15.4311 | 10.1437 | 19.4311 | 32.8623 | 48.2934
3.1034 | 7.5517 | 5.1034 | 4.1034 | 5.6551 | 7.6551 | 7.5517 | 11.6551 | 17.3102 | 24.9653
7.6587 | 9.8293 | 9.6587 | 8.6587 | 12.488 | 14.488 | 9.8293 | 18.488 | 30.976 | 45.464
6.0628 | 9.0314 | 8.0628 | 7.0628 | 10.0943 | 12.0943 | 9.0314 | 16.0943 | 26.1885 | 38.2828
3.9967 | 7.9984 | 5.9967 | 4.9967 | 6.9951 | 8.9951 | 7.9984 | 12.9951 | 19.9902 | 28.9853
8.4404 | 10.2202 | 10.4404 | 9.4404 | 13.6606 | 15.6606 | 10.2202 | 19.6606 | 33.3212 | 48.9817
3.7597 | 7.8798 | 5.7597 | 4.7597 | 6.6395 | 8.6395 | 7.8798 | 12.6395 | 19.279 | 27.9185
3.6668 | 7.8334 | 5.6668 | 4.6668 | 6.5002 | 8.5002 | 7.8334 | 12.5002 | 19.0005 | 27.5007
4.5056 | 8.2528 | 6.5056 | 5.5056 | 7.7584 | 9.7584 | 8.2528 | 13.7584 | 21.5168 | 31.2752
3.8066 | 7.9033 | 5.8066 | 4.8066 | 6.7098 | 8.7098 | 7.9033 | 12.7098 | 19.4197 | 28.1295
4.057 | 8.0285 | 6.057 | 5.057 | 7.0856 | 9.0856 | 8.0285 | 13.0856 | 20.1711 | 29.2567
4.0248 | 8.0124 | 6.0248 | 5.0248 | 7.0372 | 9.0372 | 8.0124 | 13.0372 | 20.0743 | 29.1115
4.3617 | 8.1808 | 6.3617 | 5.3617 | 7.5425 | 9.5425 | 8.1808 | 13.5425 | 21.085 | 30.6275
2.9596 | 7.4798 | 4.9596 | 3.9596 | 5.4394 | 7.4394 | 7.4798 | 11.4394 | 16.8788 | 24.3181
6.0298 | 9.0149 | 8.0298 | 7.0298 | 10.0448 | 12.0448 | 9.0149 | 16.0448 | 26.0895 | 38.1343
6.0714 | 9.0357 | 8.0714 | 7.0714 | 10.1071 | 12.1071 | 9.0357 | 16.1071 | 26.2141 | 38.3212
7.1541 | 9.5771 | 9.1541 | 8.1541 | 11.7312 | 13.7312 | 9.5771 | 17.7312 | 29.4624 | 43.1936
4.933 | 8.4665 | 6.933 | 5.933 | 8.3996 | 10.3996 | 8.4665 | 14.3996 | 22.7991 | 33.1987
4.1916 | 8.0958 | 6.1916 | 5.1916 | 7.2874 | 9.2874 | 8.0958 | 13.2874 | 20.5748 | 29.8621
7.147 | 9.5735 | 9.147 | 8.147 | 11.7205 | 13.7205 | 9.5735 | 17.7205 | 29.4411 | 43.1616
3.5581 | 7.7791 | 5.5581 | 4.5581 | 6.3372 | 8.3372 | 7.7791 | 12.3372 | 18.6744 | 27.0116
6.1262 | 9.0631 | 8.1262 | 7.1262 | 10.1893 | 12.1893 | 9.0631 | 16.1893 | 26.3785 | 38.5678
4.3383 | 8.1692 | 6.3383 | 5.3383 | 7.5075 | 9.5075 | 8.1692 | 13.5075 | 21.0149 | 30.5224
5.0357 | 8.5178 | 7.0357 | 6.0357 | 8.5535 | 10.5535 | 8.5178 | 14.5535 | 23.1071 | 33.6606
6.8694 | 9.4347 | 8.8694 | 7.8694 | 11.3041 | 13.3041 | 9.4347 | 17.3041 | 28.6083 | 41.9124
1.534 | 6.767 | 3.534 | 2.534 | 3.301 | 5.301 | 6.767 | 9.301 | 12.6021 | 17.9031
7.0464 | 9.5232 | 9.0464 | 8.0464 | 11.5695 | 13.5695 | 9.5232 | 17.5695 | 29.1391 | 42.7086
7.3728 | 9.6864 | 9.3728 | 8.3728 | 12.0592 | 14.0592 | 9.6864 | 18.0592 | 30.1185 | 44.1777
6.9632 | 9.4816 | 8.9632 | 7.9632 | 11.4448 | 13.4448 | 9.4816 | 17.4448 | 28.8895 | 42.3343
10.0391 | 11.0196 | 12.0391 | 11.0391 | 16.0587 | 18.0587 | 11.0196 | 22.0587 | 38.1174 | 56.176
2.6093 | 7.3047 | 4.6093 | 3.6093 | 4.914 | 6.914 | 7.3047 | 10.914 | 15.828 | 22.742
5.5955 | 8.7978 | 7.5955 | 6.5955 | 9.3933 | 11.3933 | 8.7978 | 15.3933 | 24.7866 | 36.1798
6.8506 | 9.4253 | 8.8506 | 7.8506 | 11.2759 | 13.2759 | 9.4253 | 17.2759 | 28.5519 | 41.8278
6.2706 | 9.1353 | 8.2706 | 7.2706 | 10.4059 | 12.4059 | 9.1353 | 16.4059 | 26.8119 | 39.2178
1.3749 | 6.6874 | 3.3749 | 2.3749 | 3.0623 | 5.0623 | 6.6874 | 9.0623 | 12.1246 | 17.1869
5.1584 | 8.5792 | 7.1584 | 6.1584 | 8.7376 | 10.7376 | 8.5792 | 14.7376 | 23.4751 | 34.2127
2.6899 | 7.345 | 4.6899 | 3.6899 | 5.0349 | 7.0349 | 7.345 | 11.0349 | 16.0697 | 23.1046
7.8723 | 9.9362 | 9.8723 | 8.8723 | 12.8085 | 14.8085 | 9.9362 | 18.8085 | 31.6169 | 46.4254
6.2022 | 9.1011 | 8.2022 | 7.2022 | 10.3034 | 12.3034 | 9.1011 | 16.3034 | 26.6067 | 38.9101
5.2262 | 8.6131 | 7.2262 | 6.2262 | 8.8394 | 10.8394 | 8.6131 | 14.8394 | 23.6787 | 34.5181
7.3341 | 9.667 | 9.3341 | 8.3341 | 12.0011 | 14.0011 | 9.667 | 18.0011 | 30.0022 | 44.0033
4.9525 | 8.4763 | 6.9525 | 5.9525 | 8.4288 | 10.4288 | 8.4763 | 14.4288 | 22.8576 | 33.2864
2.0881 | 7.0441 | 4.0881 | 3.0881 | 4.1322 | 6.1322 | 7.0441 | 10.1322 | 14.2644 | 20.3966
3.9195 | 7.9597 | 5.9195 | 4.9195 | 6.8792 | 8.8792 | 7.9597 | 12.8792 | 19.7585 | 28.6377
3.6272 | 7.8136 | 5.6272 | 4.6272 | 6.4408 | 8.4408 | 7.8136 | 12.4408 | 18.8816 | 27.3224
7.2947 | 9.6474 | 9.2947 | 8.2947 | 11.9421 | 13.9421 | 9.6474 | 17.9421 | 29.8841 | 43.8262
2.1455 | 7.0728 | 4.1455 | 3.1455 | 4.2183 | 6.2183 | 7.0728 | 10.2183 | 14.4366 | 20.6549
5.3279 | 8.6639 | 7.3279 | 6.3279 | 8.9918 | 10.9918 | 8.6639 | 14.9918 | 23.9837 | 34.9755
9.3314 | 10.6657 | 11.3314 | 10.3314 | 14.9971 | 16.9971 | 10.6657 | 20.9971 | 35.9941 | 52.9912
3.8591 | 7.9296 | 5.8591 | 4.8591 | 6.7887 | 8.7887 | 7.9296 | 12.7887 | 19.5774 | 28.3661
3.9396 | 7.9698 | 5.9396 | 4.9396 | 6.9093 | 8.9093 | 7.9698 | 12.9093 | 19.8187 | 28.728
5.9075 | 8.9538 | 7.9075 | 6.9075 | 9.8613 | 11.8613 | 8.9538 | 15.8613 | 25.7226 | 37.5839
6.4736 | 9.2368 | 8.4736 | 7.4736 | 10.7104 | 12.7104 | 9.2368 | 16.7104 | 27.4208 | 40.1312
6.1772 | 9.0886 | 8.1772 | 7.1772 | 10.2658 | 12.2658 | 9.0886 | 16.2658 | 26.5317 | 38.7975
8.3162 | 10.1581 | 10.3162 | 9.3162 | 13.4744 | 15.4744 | 10.1581 | 19.4744 | 32.9487 | 48.4231
8.4837 | 10.2419 | 10.4837 | 9.4837 | 13.7256 | 15.7256 | 10.2419 | 19.7256 | 33.4512 | 49.1768
4.6072 | 8.3036 | 6.6072 | 5.6072 | 7.9108 | 9.9108 | 8.3036 | 13.9108 | 21.8217 | 31.7325
6.9466 | 9.4733 | 8.9466 | 7.9466 | 11.4199 | 13.4199 | 9.4733 | 17.4199 | 28.8397 | 42.2596
4.9222 | 8.4611 | 6.9222 | 5.9222 | 8.3833 | 10.3833 | 8.4611 | 14.3833 | 22.7666 | 33.1498
6.7574 | 9.3787 | 8.7574 | 7.7574 | 11.1361 | 13.1361 | 9.3787 | 17.1361 | 28.2722 | 41.4082
4.633 | 8.3165 | 6.633 | 5.633 | 7.9494 | 9.9494 | 8.3165 | 13.9494 | 21.8989 | 31.8483
6.7659 | 9.3829 | 8.7659 | 7.7659 | 11.1488 | 13.1488 | 9.3829 | 17.1488 | 28.2977 | 41.4465
7.5034 | 9.7517 | 9.5034 | 8.5034 | 12.2551 | 14.2551 | 9.7517 | 18.2551 | 30.5101 | 44.7652
6.5977 | 9.2989 | 8.5977 | 7.5977 | 10.8966 | 12.8966 | 9.2989 | 16.8966 | 27.7932 | 40.6898
10.4265 | 11.2133 | 12.4265 | 11.4265 | 16.6398 | 18.6398 | 11.2133 | 22.6398 | 39.2796 | 57.9195
3.714 | 7.857 | 5.714 | 4.714 | 6.571 | 8.571 | 7.857 | 12.571 | 19.1421 | 27.7131
5.7873 | 8.8936 | 7.7873 | 6.7873 | 9.6809 | 11.6809 | 8.8936 | 15.6809 | 25.3618 | 37.0428
7.0859 | 9.543 | 9.0859 | 8.0859 | 11.6289 | 13.6289 | 9.543 | 17.6289 | 29.2577 | 42.8866
7.4262 | 9.7131 | 9.4262 | 8.4262 | 12.1394 | 14.1394 | 9.7131 | 18.1394 | 30.2787 | 44.4181
8.0811 | 10.0406 | 10.0811 | 9.0811 | 13.1217 | 15.1217 | 10.0406 | 19.1217 | 32.2433 | 47.365
3.1327 | 7.5663 | 5.1327 | 4.1327 | 5.699 | 7.699 | 7.5663 | 11.699 | 17.398 | 25.0971
6.3051 | 9.1525 | 8.3051 | 7.3051 | 10.4576 | 12.4576 | 9.1525 | 16.4576 | 26.9152 | 39.3728
5.055 | 8.5275 | 7.055 | 6.055 | 8.5826 | 10.5826 | 8.5275 | 14.5826 | 23.1651 | 33.7477
6.1435 | 9.0718 | 8.1435 | 7.1435 | 10.2153 | 12.2153 | 9.0718 | 16.2153 | 26.4306 | 38.6459
4.6397 | 8.3198 | 6.6397 | 5.6397 | 7.9595 | 9.9595 | 8.3198 | 13.9595 | 21.919 | 31.8784
5.7358 | 8.8679 | 7.7358 | 6.7358 | 9.6037 | 11.6037 | 8.8679 | 15.6037 | 25.2075 | 36.8112
5.6716 | 8.8358 | 7.6716 | 6.6716 | 9.5074 | 11.5074 | 8.8358 | 15.5074 | 25.0148 | 36.5222
5.8039 | 8.902 | 7.8039 | 6.8039 | 9.7059 | 11.7059 | 8.902 | 15.7059 | 25.4118 | 37.1176
4.2001 | 8.1001 | 6.2001 | 5.2001 | 7.3002 | 9.3002 | 8.1001 | 13.3002 | 20.6003 | 29.9005
7.2835 | 9.6418 | 9.2835 | 8.2835 | 11.9253 | 13.9253 | 9.6418 | 17.9253 | 29.8505 | 43.7758
5.9561 | 8.978 | 7.9561 | 6.9561 | 9.9341 | 11.9341 | 8.978 | 15.9341 | 25.8682 | 37.8023
4.4582 | 8.2291 | 6.4582 | 5.4582 | 7.6873 | 9.6873 | 8.2291 | 13.6873 | 21.3746 | 31.0619
9.4554 | 10.7277 | 11.4554 | 10.4554 | 15.1831 | 17.1831 | 10.7277 | 21.1831 | 36.3663 | 53.5494
7.4928 | 9.7464 | 9.4928 | 8.4928 | 12.2393 | 14.2393 | 9.7464 | 18.2393 | 30.4785 | 44.7178
8.881 | 10.4405 | 10.881 | 9.881 | 14.3215 | 16.3215 | 10.4405 | 20.3215 | 34.6431 | 50.9646
7.7568 | 9.8784 | 9.7568 | 8.7568 | 12.6353 | 14.6353 | 9.8784 | 18.6353 | 31.2705 | 45.9058
2.9043 | 7.4522 | 4.9043 | 3.9043 | 5.3565 | 7.3565 | 7.4522 | 11.3565 | 16.7129 | 24.0694
5.3388 | 8.6694 | 7.3388 | 6.3388 | 9.0081 | 11.0081 | 8.6694 | 15.0081 | 24.0163 | 35.0244
5.5621 | 8.7811 | 7.5621 | 6.5621 | 9.3432 | 11.3432 | 8.7811 | 15.3432 | 24.6864 | 36.0296
4.4878 | 8.2439 | 6.4878 | 5.4878 | 7.7317 | 9.7317 | 8.2439 | 13.7317 | 21.4634 | 31.1951
3.7421 | 7.8711 | 5.7421 | 4.7421 | 6.6132 | 8.6132 | 7.8711 | 12.6132 | 19.2263 | 27.8395
7.9302 | 9.9651 | 9.9302 | 8.9302 | 12.8953 | 14.8953 | 9.9651 | 18.8953 | 31.7905 | 46.6858
1.6191 | 6.8096 | 3.6191 | 2.6191 | 3.4287 | 5.4287 | 6.8096 | 9.4287 | 12.8574 | 18.2862
5.7064 | 8.8532 | 7.7064 | 6.7064 | 9.5596 | 11.5596 | 8.8532 | 15.5596 | 25.1192 | 36.6788
7.4495 | 9.7247 | 9.4495 | 8.4495 | 12.1742 | 14.1742 | 9.7247 | 18.1742 | 30.3484 | 44.5225
9.2742 | 10.6371 | 11.2742 | 10.2742 | 14.9113 | 16.9113 | 10.6371 | 20.9113 | 35.8226 | 52.7339
3.6679 | 7.8339 | 5.6679 | 4.6679 | 6.5018 | 8.5018 | 7.8339 | 12.5018 | 19.0036 | 27.5054
0.79769 | 6.3988 | 2.7977 | 1.7977 | 2.1965 | 4.1965 | 6.3988 | 8.1965 | 10.3931 | 14.5896
3.1848 | 7.5924 | 5.1848 | 4.1848 | 5.7772 | 7.7772 | 7.5924 | 11.7772 | 17.5544 | 25.3316
4.6142 | 8.3071 | 6.6142 | 5.6142 | 7.9214 | 9.9214 | 8.3071 | 13.9214 | 21.8427 | 31.7641
3.8428 | 7.9214 | 5.8428 | 4.8428 | 6.7641 | 8.7641 | 7.9214 | 12.7641 | 19.5283 | 28.2924
5.1024 | 8.5512 | 7.1024 | 6.1024 | 8.6535 | 10.6535 | 8.5512 | 14.6535 | 23.3071 | 33.9606 | 20% chance that the project will take 30 days or less
4.4655 | 8.2327 | 6.4655 | 5.4655 | 7.6982 | 9.6982 | 8.2327 | 13.6982 | 21.3965 | 31.0947
4.0289 | 8.0145 | 6.0289 | 5.0289 | 7.0434 | 9.0434 | 8.0145 | 13.0434 | 20.0867 | 29.1301
7.1646 | 9.5823 | 9.1646 | 8.1646 | 11.7469 | 13.7469 | 9.5823 | 17.7469 | 29.4938 | 43.2407
9.2783 | 10.6391 | 11.2783 | 10.2783 | 14.9174 | 16.9174 | 10.6391 | 20.9174 | 35.8348 | 52.7522
6.9702 | 9.4851 | 8.9702 | 7.9702 | 11.4553 | 13.4553 | 9.4851 | 17.4553 | 28.9106 | 42.3659
8.7728 | 10.3864 | 10.7728 | 9.7728 | 14.1592 | 16.1592 | 10.3864 | 20.1592 | 34.3184 | 50.4777
4.2408 | 8.1204 | 6.2408 | 5.2408 | 7.3612 | 9.3612 | 8.1204 | 13.3612 | 20.7224 | 30.0836
6.3376 | 9.1688 | 8.3376 | 7.3376 | 10.5064 | 12.5064 | 9.1688 | 16.5064 | 27.0128 | 39.5192
10.4613 | 11.2307 | 12.4613 | 11.4613 | 16.692 | 18.692 | 11.2307 | 22.692 | 39.384 | 58.076
0.66258 | 6.3313 | 2.6626 | 1.6626 | 1.9939 | 3.9939 | 6.3313 | 7.9939 | 9.9877 | 13.9816
10.4087 | 11.2044 | 12.4087 | 11.4087 | 16.6131 | 18.6131 | 11.2044 | 22.6131 | 39.2262 | 57.8392
8.7381 | 10.369 | 10.7381 | 9.7381 | 14.1071 | 16.1071 | 10.369 | 20.1071 | 34.2142 | 50.3212
3.1683 | 7.5841 | 5.1683 | 4.1683 | 5.7524 | 7.7524 | 7.5841 | 11.7524 | 17.5048 | 25.2573
7.7445 | 9.8723 | 9.7445 | 8.7445 | 12.6168 | 14.6168 | 9.8723 | 18.6168 | 31.2336 | 45.8504
9.3878 | 10.6939 | 11.3878 | 10.3878 | 15.0817 | 17.0817 | 10.6939 | 21.0817 | 36.1635 | 53.2452
5.023 | 8.5115 | 7.023 | 6.023 | 8.5345 | 10.5345 | 8.5115 | 14.5345 | 23.0691 | 33.6036
8.4739 | 10.2369 | 10.4739 | 9.4739 | 13.7108 | 15.7108 | 10.2369 | 19.7108 | 33.4216 | 49.1324
8.7597 | 10.3798 | 10.7597 | 9.7597 | 14.1395 | 16.1395 | 10.3798 | 20.1395 | 34.2791 | 50.4186
4.8751 | 8.4376 | 6.8751 | 5.8751 | 8.3127 | 10.3127 | 8.4376 | 14.3127 | 22.6253 | 32.938
1.4437 | 6.7218 | 3.4437 | 2.4437 | 3.1655 | 5.1655 | 6.7218 | 9.1655 | 12.3311 | 17.4966
8.6329 | 10.3164 | 10.6329 | 9.6329 | 13.9493 | 15.9493 | 10.3164 | 19.9493 | 33.8987 | 49.848
9.0754 | 10.5377 | 11.0754 | 10.0754 | 14.6132 | 16.6132 | 10.5377 | 20.6132 | 35.2263 | 51.8395
10.3567 | 11.1783 | 12.3567 | 11.3567 | 16.535 | 18.535 | 11.1783 | 22.535 | 39.0701 | 57.6051
3.4698 | 7.7349 | 5.4698 | 4.4698 | 6.2046 | 8.2046 | 7.7349 | 12.2046 | 18.4093 | 26.6139
6.9334 | 9.4667 | 8.9334 | 7.9334 | 11.4 | 13.4 | 9.4667 | 17.4 | 28.8001 | 42.2001
6.7322 | 9.3661 | 8.7322 | 7.7322 | 11.0983 | 13.0983 | 9.3661 | 17.0983 | 28.1966 | 41.2949
5.8459 | 8.9229 | 7.8459 | 6.8459 | 9.7688 | 11.7688 | 8.9229 | 15.7688 | 25.5376 | 37.3064
4.7205 | 8.3602 | 6.7205 | 5.7205 | 8.0807 | 10.0807 | 8.3602 | 14.0807 | 22.1614 | 32.242
4.978 | 8.489 | 6.978 | 5.978 | 8.4671 | 10.4671 | 8.489 | 14.4671 | 22.9341 | 33.4012
7.8245 | 9.9122 | 9.8245 | 8.8245 | 12.7367 | 14.7367 | 9.9122 | 18.7367 | 31.4734 | 46.2102
9.0442 | 10.5221 | 11.0442 | 10.0442 | 14.5664 | 16.5664 | 10.5221 | 20.5664 | 35.1327 | 51.6991
6.103 | 9.0515 | 8.103 | 7.103 | 10.1545 | 12.1545 | 9.0515 | 16.1545 | 26.309 | 38.4635
6.7836 | 9.3918 | 8.7836 | 7.7836 | 11.1754 | 13.1754 | 9.3918 | 17.1754 | 28.3508 | 41.5262
7.9996 | 9.9998 | 9.9996 | 8.9996 | 12.9994 | 14.9994 | 9.9998 | 18.9994 | 31.9988 | 46.9981
6.7548 | 9.3774 | 8.7548 | 7.7548 | 11.1323 | 13.1323 | 9.3774 | 17.1323 | 28.2645 | 41.3968
4.9916 | 8.4958 | 6.9916 | 5.9916 | 8.4874 | 10.4874 | 8.4958 | 14.4874 | 22.9748 | 33.4622
7.3393 | 9.6696 | 9.3393 | 8.3393 | 12.0089 | 14.0089 | 9.6696 | 18.0089 | 30.0178 | 44.0267
4.7254 | 8.3627 | 6.7254 | 5.7254 | 8.0881 | 10.0881 | 8.3627 | 14.0881 | 22.1761 | 32.2642
7.3984 | 9.6992 | 9.3984 | 8.3984 | 12.0976 | 14.0976 | 9.6992 | 18.0976 | 30.1953 | 44.2929
4.1227 | 8.0614 | 6.1227 | 5.1227 | 7.1841 | 9.1841 | 8.0614 | 13.1841 | 20.3681 | 29.5522
6.9476 | 9.4738 | 8.9476 | 7.9476 | 11.4214 | 13.4214 | 9.4738 | 17.4214 | 28.8428 | 42.2641
5.1213 | 8.5607 | 7.1213 | 6.1213 | 8.682 | 10.682 | 8.5607 | 14.682 | 23.3639 | 34.0459
7.439 | 9.7195 | 9.439 | 8.439 | 12.1584 | 14.1584 | 9.7195 | 18.1584 | 30.3169 | 44.4753
8.1499 | 10.0749 | 10.1499 | 9.1499 | 13.2248 | 15.2248 | 10.0749 | 19.2248 | 32.4496 | 47.6744
7.6971 | 9.8485 | 9.6971 | 8.6971 | 12.5456 | 14.5456 | 9.8485 | 18.5456 | 31.0913 | 45.6369
3.3984 | 7.6992 | 5.3984 | 4.3984 | 6.0976 | 8.0976 | 7.6992 | 12.0976 | 18.1951 | 26.2927
6.4452 | 9.2226 | 8.4452 | 7.4452 | 10.6678 | 12.6678 | 9.2226 | 16.6678 | 27.3357 | 40.0035
8.317 | 10.1585 | 10.317 | 9.317 | 13.4754 | 15.4754 | 10.1585 | 19.4754 | 32.9509 | 48.4263
3.6489 | 7.8244 | 5.6489 | 4.6489 | 6.4733 | 8.4733 | 7.8244 | 12.4733 | 18.9466 | 27.4198
8.2439 | 10.1219 | 10.2439 | 9.2439 | 13.3658 | 15.3658 | 10.1219 | 19.3658 | 32.7317 | 48.0975
4.5875 | 8.2937 | 6.5875 | 5.5875 | 7.8812 | 9.8812 | 8.2937 | 13.8812 | 21.7625 | 31.6437
8.8279 | 10.4139 | 10.8279 | 9.8279 | 14.2418 | 16.2418 | 10.4139 | 20.2418 | 34.4836 | 50.7253
5.636 | 8.818 | 7.636 | 6.636 | 9.454 | 11.454 | 8.818 | 15.454 | 24.908 | 36.362
8.4249 | 10.2124 | 10.4249 | 9.4249 | 13.6373 | 15.6373 | 10.2124 | 19.6373 | 33.2747 | 48.912
5.2353 | 8.6176 | 7.2353 | 6.2353 | 8.8529 | 10.8529 | 8.6176 | 14.8529 | 23.7058 | 34.5587
8.1883 | 10.0942 | 10.1883 | 9.1883 | 13.2825 | 15.2825 | 10.0942 | 19.2825 | 32.5649 | 47.8474
5.4272 | 8.7136 | 7.4272 | 6.4272 | 9.1408 | 11.1408 | 8.7136 | 15.1408 | 24.2816 | 35.4223
3.0993 | 7.5496 | 5.0993 | 4.0993 | 5.6489 | 7.6489 | 7.5496 | 11.6489 | 17.2979 | 24.9468
9.643 | 10.8215 | 11.643 | 10.643 | 15.4644 | 17.4644 | 10.8215 | 21.4644 | 36.9289 | 54.3933
3.1333 | 7.5666 | 5.1333 | 4.1333 | 5.6999 | 7.6999 | 7.5666 | 11.6999 | 17.3999 | 25.0998
4.86 | 8.43 | 6.86 | 5.86 | 8.2901 | 10.2901 | 8.43 | 14.2901 | 22.5801 | 32.8702
1.4969 | 6.7484 | 3.4969 | 2.4969 | 3.2453 | 5.2453 | 6.7484 | 9.2453 | 12.4906 | 17.7359
6.6087 | 9.3043 | 8.6087 | 7.6087 | 10.913 | 12.913 | 9.3043 | 16.913 | 27.826 | 40.739
0.19349 | 6.0967 | 2.1935 | 1.1935 | 1.2902 | 3.2902 | 6.0967 | 7.2902 | 8.5805 | 11.8707
2.3013 | 7.1507 | 4.3013 | 3.3013 | 4.452 | 6.452 | 7.1507 | 10.452 | 14.9039 | 21.3559
4.636 | 8.318 | 6.636 | 5.636 | 7.954 | 9.954 | 8.318 | 13.954 | 21.9081 | 31.8621
7.8136 | 9.9068 | 9.8136 | 8.8136 | 12.7204 | 14.7204 | 9.9068 | 18.7204 | 31.4408 | 46.1612
7.9975 | 9.9987 | 9.9975 | 8.9975 | 12.9962 | 14.9962 | 9.9987 | 18.9962 | 31.9924 | 46.9886
5.0423 | 8.5211 | 7.0423 | 6.0423 | 8.5634 | 10.5634 | 8.5211 | 14.5634 | 23.1269 | 33.6903
5.2153 | 8.6077 | 7.2153 | 6.2153 | 8.823 | 10.823 | 8.6077 | 14.823 | 23.646 | 34.4689
7.7411 | 9.8705 | 9.7411 | 8.7411 | 12.6116 | 14.6116 | 9.8705 | 18.6116 | 31.2232 | 45.8347
9.2544 | 10.6272 | 11.2544 | 10.2544 | 14.8816 | 16.8816 | 10.6272 | 20.8816 | 35.7633 | 52.6449
6.6676 | 9.3338 | 8.6676 | 7.6676 | 11.0015 | 13.0015 | 9.3338 | 17.0015 | 28.0029 | 41.0044
8.7053 | 10.3526 | 10.7053 | 9.7053 | 14.0579 | 16.0579 | 10.3526 | 20.0579 | 34.1159 | 50.1738
6.3422 | 9.1711 | 8.3422 | 7.3422 | 10.5132 | 12.5132 | 9.1711 | 16.5132 | 27.0265 | 39.5397
2.1402 | 7.0701 | 4.1402 | 3.1402 | 4.2102 | 6.2102 | 7.0701 | 10.2102 | 14.4205 | 20.6307
6.3398 | 9.1699 | 8.3398 | 7.3398 | 10.5097 | 12.5097 | 9.1699 | 16.5097 | 27.0195 | 39.5292
4.8799 | 8.44 | 6.8799 | 5.8799 | 8.3199 | 10.3199 | 8.44 | 14.3199 | 22.6398 | 32.9597
7.8328 | 9.9164 | 9.8328 | 8.8328 | 12.7492 | 14.7492 | 9.9164 | 18.7492 | 31.4983 | 46.2475
4.5334 | 8.2667 | 6.5334 | 5.5334 | 7.8001 | 9.8001 | 8.2667 | 13.8001 | 21.6003 | 31.4004
1.5633 | 6.7816 | 3.5633 | 2.5633 | 3.3449 | 5.3449 | 6.7816 | 9.3449 | 12.6898 | 18.0347
9.238 | 10.619 | 11.238 | 10.238 | 14.857 | 16.857 | 10.619 | 20.857 | 35.714 | 52.571
8.3374 | 10.1687 | 10.3374 | 9.3374 | 13.5062 | 15.5062 | 10.1687 | 19.5062 | 33.0123 | 48.5185
1.8786 | 6.9393 | 3.8786 | 2.8786 | 3.818 | 5.818 | 6.9393 | 9.818 | 13.6359 | 19.4539
6.2012 | 9.1006 | 8.2012 | 7.2012 | 10.3018 | 12.3018 | 9.1006 | 16.3018 | 26.6035 | 38.9053
7.7312 | 9.8656 | 9.7312 | 8.7312 | 12.5968 | 14.5968 | 9.8656 | 18.5968 | 31.1936 | 45.7904
4.7984 | 8.3992 | 6.7984 | 5.7984 | 8.1976 | 10.1976 | 8.3992 | 14.1976 | 22.3952 | 32.5929
8.9196 | 10.4598 | 10.9196 | 9.9196 | 14.3793 | 16.3793 | 10.4598 | 20.3793 | 34.7587 | 51.138
9.3436 | 10.6718 | 11.3436 | 10.3436 | 15.0154 | 17.0154 | 10.6718 | 21.0154 | 36.0308 | 53.0462
5.1653 | 8.5827 | 7.1653 | 6.1653 | 8.748 | 10.748 | 8.5827 | 14.748 | 23.496 | 34.244
5.6215 | 8.8107 | 7.6215 | 6.6215 | 9.4322 | 11.4322 | 8.8107 | 15.4322 | 24.8644 | 36.2965
9.5198 | 10.7599 | 11.5198 | 10.5198 | 15.2797 | 17.2797 | 10.7599 | 21.2797 | 36.5595 | 53.8392
10.0229 | 11.0114 | 12.0229 | 11.0229 | 16.0343 | 18.0343 | 11.0114 | 22.0343 | 38.0686 | 56.1029
8.6306 | 10.3153 | 10.6306 | 9.6306 | 13.9458 | 15.9458 | 10.3153 | 19.9458 | 33.8917 | 49.8375
6.7681 | 9.384 | 8.7681 | 7.7681 | 11.1521 | 13.1521 | 9.384 | 17.1521 | 28.3042 | 41.4562
5.9488 | 8.9744 | 7.9488 | 6.9488 | 9.9232 | 11.9232 | 8.9744 | 15.9232 | 25.8464 | 37.7696
8.6032 | 10.3016 | 10.6032 | 9.6032 | 13.9049 | 15.9049 | 10.3016 | 19.9049 | 33.8097 | 49.7146
7.2646 | 9.6323 | 9.2646 | 8.2646 | 11.8969 | 13.8969 | 9.6323 | 17.8969 | 29.7938 | 43.6907
7.4592 | 9.7296 | 9.4592 | 8.4592 | 12.1887 | 14.1887 | 9.7296 | 18.1887 | 30.3775 | 44.5662
9.2906 | 10.6453 | 11.2906 | 10.2906 | 14.9359 | 16.9359 | 10.6453 | 20.9359 | 35.8718 | 52.8077
5.6507 | 8.8253 | 7.6507 | 6.6507 | 9.476 | 11.476 | 8.8253 | 15.476 | 24.9521 | 36.4281
5.277 | 8.6385 | 7.277 | 6.277 | 8.9155 | 10.9155 | 8.6385 | 14.9155 | 23.8311 | 34.7466
5.9486 | 8.9743 | 7.9486 | 6.9486 | 9.9229 | 11.9229 | 8.9743 | 15.9229 | 25.8458 | 37.7686
3.9488 | 7.9744 | 5.9488 | 4.9488 | 6.9232 | 8.9232 | 7.9744 | 12.9232 | 19.8463 | 28.7695
6.967 | 9.4835 | 8.967 | 7.967 | 11.4505 | 13.4505 | 9.4835 | 17.4505 | 28.9011 | 42.3516
5.6804 | 8.8402 | 7.6804 | 6.6804 | 9.5206 | 11.5206 | 8.8402 | 15.5206 | 25.0411 | 36.5617
5.8489 | 8.9244 | 7.8489 | 6.8489 | 9.7733 | 11.7733 | 8.9244 | 15.7733 | 25.5467 | 37.32
5.5667 | 8.7834 | 7.5667 | 6.5667 | 9.3501 | 11.3501 | 8.7834 | 15.3501 | 24.7002 | 36.0503
4.4888 | 8.2444 | 6.4888 | 5.4888 | 7.7331 | 9.7331 | 8.2444 | 13.7331 | 21.4663 | 31.1994
6.296 | 9.148 | 8.296 | 7.296 | 10.4439 | 12.4439 | 9.148 | 16.4439 | 26.8879 | 39.3318
3.229 | 7.6145 | 5.229 | 4.229 | 5.8436 | 7.8436 | 7.6145 | 11.8436 | 17.6871 | 25.5307
4.2843 | 8.1422 | 6.2843 | 5.2843 | 7.4265 | 9.4265 | 8.1422 | 13.4265 | 20.853 | 30.2795
6.7877 | 9.3938 | 8.7877 | 7.7877 | 11.1815 | 13.1815 | 9.3938 | 17.1815 | 28.363 | 41.5445
5.7262 | 8.8631 | 7.7262 | 6.7262 | 9.5893 | 11.5893 | 8.8631 | 15.5893 | 25.1786 | 36.7679
5.5621 | 8.7811 | 7.5621 | 6.5621 | 9.3432 | 11.3432 | 8.7811 | 15.3432 | 24.6863 | 36.0295
3.4367 | 7.7183 | 5.4367 | 4.4367 | 6.155 | 8.155 | 7.7183 | 12.155 | 18.31 | 26.465
5.3088 | 8.6544 | 7.3088 | 6.3088 | 8.9631 | 10.9631 | 8.6544 | 14.9631 | 23.9263 | 34.8894
5.6934 | 8.8467 | 7.6934 | 6.6934 | 9.54 | 11.54 | 8.8467 | 15.54 | 25.0801 | 36.6201
5.8089 | 8.9045 | 7.8089 | 6.8089 | 9.7134 | 11.7134 | 8.9045 | 15.7134 | 25.4268 | 37.1401
8.2504 | 10.1252 | 10.2504 | 9.2504 | 13.3756 | 15.3756 | 10.1252 | 19.3756 | 32.7511 | 48.1267
7.7162 | 9.8581 | 9.7162 | 8.7162 | 12.5744 | 14.5744 | 9.8581 | 18.5744 | 31.1487 | 45.7231
6.9447 | 9.4723 | 8.9447 | 7.9447 | 11.417 | 13.417 | 9.4723 | 17.417 | 28.834 | 42.251
6.4412 | 9.2206 | 8.4412 | 7.4412 | 10.6617 | 12.6617 | 9.2206 | 16.6617 | 27.3235 | 39.9852
6.4323 | 9.2162 | 8.4323 | 7.4323 | 10.6485 | 12.6485 | 9.2162 | 16.6485 | 27.2969 | 39.9454
6.4928 | 9.2464 | 8.4928 | 7.4928 | 10.7392 | 12.7392 | 9.2464 | 16.7392 | 27.4785 | 40.2177
3.9532 | 7.9766 | 5.9532 | 4.9532 | 6.9298 | 8.9298 | 7.9766 | 12.9298 | 19.8596 | 28.7894
5.9402 | 8.9701 | 7.9402 | 6.9402 | 9.9103 | 11.9103 | 8.9701 | 15.9103 | 25.8206 | 37.731
3.3361 | 7.6681 | 5.3361 | 4.3361 | 6.0042 | 8.0042 | 7.6681 | 12.0042 | 18.0084 | 26.0127
8.2102 | 10.1051 | 10.2102 | 9.2102 | 13.3154 | 15.3154 | 10.1051 | 19.3154 | 32.6307 | 47.9461
6.2818 | 9.1409 | 8.2818 | 7.2818 | 10.4227 | 12.4227 | 9.1409 | 16.4227 | 26.8453 | 39.268
2.9093 | 7.4547 | 4.9093 | 3.9093 | 5.364 | 7.364 | 7.4547 | 11.364 | 16.728 | 24.092
5.7942 | 8.8971 | 7.7942 | 6.7942 | 9.6914 | 11.6914 | 8.8971 | 15.6914 | 25.3827 | 37.0741
8.7512 | 10.3756 | 10.7512 | 9.7512 | 14.1267 | 16.1267 | 10.3756 | 20.1267 | 34.2535 | 50.3802
4.3479 | 8.174 | 6.3479 | 5.3479 | 7.5219 | 9.5219 | 8.174 | 13.5219 | 21.0437 | 30.5656
4.2408 | 8.1204 | 6.2408 | 5.2408 | 7.3612 | 9.3612 | 8.1204 | 13.3612 | 20.7223 | 30.0835
6.0035 | 9.0018 | 8.0035 | 7.0035 | 10.0053 | 12.0053 | 9.0018 | 16.0053 | 26.0106 | 38.0159
5.1528 | 8.5764 | 7.1528 | 6.1528 | 8.7292 | 10.7292 | 8.5764 | 14.7292 | 23.4584 | 34.1877
0.74596 | 6.373 | 2.746 | 1.746 | 2.1189 | 4.1189 | 6.373 | 8.1189 | 10.2379 | 14.3568
5.4154 | 8.7077 | 7.4154 | 6.4154 | 9.1231 | 11.1231 | 8.7077 | 15.1231 | 24.2463 | 35.3694
4.619 | 8.3095 | 6.619 | 5.619 | 7.9285 | 9.9285 | 8.3095 | 13.9285 | 21.8569 | 31.7854
6.6018 | 9.3009 | 8.6018 | 7.6018 | 10.9028 | 12.9028 | 9.3009 | 16.9028 | 27.8055 | 40.7083
3.9475 | 7.9738 | 5.9475 | 4.9475 | 6.9213 | 8.9213 | 7.9738 | 12.9213 | 19.8426 | 28.7639
4.6839 | 8.3419 | 6.6839 | 5.6839 | 8.0258 | 10.0258 | 8.3419 | 14.0258 | 22.0516 | 32.0774
9.3878 | 10.6939 | 11.3878 | 10.3878 | 15.0817 | 17.0817 | 10.6939 | 21.0817 | 36.1634 | 53.2452
4.9761 | 8.4881 | 6.9761 | 5.9761 | 8.4642 | 10.4642 | 8.4881 | 14.4642 | 22.9283 | 33.3925
3.6458 | 7.8229 | 5.6458 | 4.6458 | 6.4687 | 8.4687 | 7.8229 | 12.4687 | 18.9374 | 27.4061
7.3652 | 9.6826 | 9.3652 | 8.3652 | 12.0478 | 14.0478 | 9.6826 | 18.0478 | 30.0956 | 44.1433
5.5501 | 8.7751 | 7.5501 | 6.5501 | 9.3252 | 11.3252 | 8.7751 | 15.3252 | 24.6504 | 35.9756
9.1422 | 10.5711 | 11.1422 | 10.1422 | 14.7134 | 16.7134 | 10.5711 | 20.7134 | 35.4267 | 52.1401
8.6099 | 10.305 | 10.6099 | 9.6099 | 13.9149 | 15.9149 | 10.305 | 19.9149 | 33.8297 | 49.7446
4.9848 | 8.4924 | 6.9848 | 5.9848 | 8.4772 | 10.4772 | 8.4924 | 14.4772 | 22.9545 | 33.4317
7.565 | 9.7825 | 9.565 | 8.565 | 12.3474 | 14.3474 | 9.7825 | 18.3474 | 30.6949 | 45.0423
5.7244 | 8.8622 | 7.7244 | 6.7244 | 9.5867 | 11.5867 | 8.8622 | 15.5867 | 25.1733 | 36.76
6.3968 | 9.1984 | 8.3968 | 7.3968 | 10.5952 | 12.5952 | 9.1984 | 16.5952 | 27.1904 | 39.7855
2.6741 | 7.3371 | 4.6741 | 3.6741 | 5.0112 | 7.0112 | 7.3371 | 11.0112 | 16.0224 | 23.0336
5.9248 | 8.9624 | 7.9248 | 6.9248 | 9.8873 | 11.8873 | 8.9624 | 15.8873 | 25.7745 | 37.6618
6.4691 | 9.2345 | 8.4691 | 7.4691 | 10.7036 | 12.7036 | 9.2345 | 16.7036 | 27.4073 | 40.1109
7.9171 | 9.9585 | 9.9171 | 8.9171 | 12.8756 | 14.8756 | 9.9585 | 18.8756 | 31.7513 | 46.6269
5.5816 | 8.7908 | 7.5816 | 6.5816 | 9.3725 | 11.3725 | 8.7908 | 15.3725 | 24.7449 | 36.1174
3.463 | 7.7315 | 5.463 | 4.463 | 6.1944 | 8.1944 | 7.7315 | 12.1944 | 18.3889 | 26.5833
5.7887 | 8.8944 | 7.7887 | 6.7887 | 9.6831 | 11.6831 | 8.8944 | 15.6831 | 25.3662 | 37.0493
6.1546 | 9.0773 | 8.1546 | 7.1546 | 10.2319 | 12.2319 | 9.0773 | 16.2319 | 26.4638 | 38.6958
5.163 | 8.5815 | 7.163 | 6.163 | 8.7444 | 10.7444 | 8.5815 | 14.7444 | 23.4889 | 34.2333
3.7331 | 7.8665 | 5.7331 | 4.7331 | 6.5996 | 8.5996 | 7.8665 | 12.5996 | 19.1992 | 27.7988
8.1549 | 10.0774 | 10.1549 | 9.1549 | 13.2323 | 15.2323 | 10.0774 | 19.2323 | 32.4646 | 47.6969
4.3398 | 8.1699 | 6.3398 | 5.3398 | 7.5097 | 9.5097 | 8.1699 | 13.5097 | 21.0194 | 30.5291
8.4702 | 10.2351 | 10.4702 | 9.4702 | 13.7053 | 15.7053 | 10.2351 | 19.7053 | 33.4105 | 49.1158
3.9037 | 7.9519 | 5.9037 | 4.9037 | 6.8556 | 8.8556 | 7.9519 | 12.8556 | 19.7112 | 28.5668
5.8388 | 8.9194 | 7.8388 | 6.8388 | 9.7582 | 11.7582 | 8.9194 | 15.7582 | 25.5165 | 37.2747
7.493 | 9.7465 | 9.493 | 8.493 | 12.2395 | 14.2395 | 9.7465 | 18.2395 | 30.479 | 44.7184
4.9927 | 8.4963 | 6.9927 | 5.9927 | 8.489 | 10.489 | 8.4963 | 14.489 | 22.978 | 33.4669
8.3457 | 10.1729 | 10.3457 | 9.3457 | 13.5186 | 15.5186 | 10.1729 | 19.5186 | 33.0371 | 48.5557
10.0861 | 11.043 | 12.0861 | 11.0861 | 16.1291 | 18.1291 | 11.043 | 22.1291 | 38.2582 | 56.3873
2.6271 | 7.3136 | 4.6271 | 3.6271 | 4.9407 | 6.9407 | 7.3136 | 10.9407 | 15.8814 | 22.8221
7.0962 | 9.5481 | 9.0962 | 8.0962 | 11.6443 | 13.6443 | 9.5481 | 17.6443 | 29.2885 | 42.9328
5.8452 | 8.9226 | 7.8452 | 6.8452 | 9.7678 | 11.7678 | 8.9226 | 15.7678 | 25.5355 | 37.3033
10.5641 | 11.2821 | 12.5641 | 11.5641 | 16.8462 | 18.8462 | 11.2821 | 22.8462 | 39.6924 | 58.5386
2.6054 | 7.3027 | 4.6054 | 3.6054 | 4.9081 | 6.9081 | 7.3027 | 10.9081 | 15.8163 | 22.7244
4.9665 | 8.4833 | 6.9665 | 5.9665 | 8.4498 | 10.4498 | 8.4833 | 14.4498 | 22.8996 | 33.3493
9.3474 | 10.6737 | 11.3474 | 10.3474 | 15.0211 | 17.0211 | 10.6737 | 21.0211 | 36.0422 | 53.0634
5.9379 | 8.969 | 7.9379 | 6.9379 | 9.9069 | 11.9069 | 8.969 | 15.9069 | 25.8138 | 37.7207
5.5692 | 8.7846 | 7.5692 | 6.5692 | 9.3538 | 11.3538 | 8.7846 | 15.3538 | 24.7076 | 36.0614
5.1908 | 8.5954 | 7.1908 | 6.1908 | 8.7862 | 10.7862 | 8.5954 | 14.7862 | 23.5724 | 34.3587
8.7941 | 10.397 | 10.7941 | 9.7941 | 14.1911 | 16.1911 | 10.397 | 20.1911 | 34.3822 | 50.5733
4.5682 | 8.2841 | 6.5682 | 5.5682 | 7.8524 | 9.8524 | 8.2841 | 13.8524 | 21.7047 | 31.5571
7.66 | 9.83 | 9.66 | 8.66 | 12.49 | 14.49 | 9.83 | 18.49 | 30.98 | 45.47
6.8619 | 9.431 | 8.8619 | 7.8619 | 11.2929 | 13.2929 | 9.431 | 17.2929 | 28.5858 | 41.8788
4.1334 | 8.0667 | 6.1334 | 5.1334 | 7.2 | 9.2 | 8.0667 | 13.2 | 20.4001 | 29.6001
7.1882 | 9.5941 | 9.1882 | 8.1882 | 11.7823 | 13.7823 | 9.5941 | 17.7823 | 29.5647 | 43.347
6.5105 | 9.2553 | 8.5105 | 7.5105 | 10.7658 | 12.7658 | 9.2553 | 16.7658 | 27.5316 | 40.2974
6.7038 | 9.3519 | 8.7038 | 7.7038 | 11.0557 | 13.0557 | 9.3519 | 17.0557 | 28.1115 | 41.1672
4.6732 | 8.3366 | 6.6732 | 5.6732 | 8.0099 | 10.0099 | 8.3366 | 14.0099 | 22.0197 | 32.0296
4.9097 | 8.4549 | 6.9097 | 5.9097 | 8.3646 | 10.3646 | 8.4549 | 14.3646 | 22.7292 | 33.0938
6.6014 | 9.3007 | 8.6014 | 7.6014 | 10.902 | 12.902 | 9.3007 | 16.902 | 27.8041 | 40.7061
6.4841 | 9.2421 | 8.4841 | 7.4841 | 10.7262 | 12.7262 | 9.2421 | 16.7262 | 27.4524 | 40.1785
7.7612 | 9.8806 | 9.7612 | 8.7612 | 12.6418 | 14.6418 | 9.8806 | 18.6418 | 31.2836 | 45.9254
10.5814 | 11.2907 | 12.5814 | 11.5814 | 16.8721 | 18.8721 | 11.2907 | 22.8721 | 39.7442 | 58.6164
4.8892 | 8.4446 | 6.8892 | 5.8892 | 8.3337 | 10.3337 | 8.4446 | 14.3337 | 22.6675 | 33.0012
5.0805 | 8.5403 | 7.0805 | 6.0805 | 8.6208 | 10.6208 | 8.5403 | 14.6208 | 23.2415 | 33.8623
[6 empty] | 0 | 0 | Average | #VALUE!

## test activity A
A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | diff
-0.32484 | 5.8376 | 1.6752 | 0.67516 | 0.51273 | 2.5127 | 5.8376 | 6.5127 | 7.5127 | 10.0255 | -0.31484 | 5.8476 | 1.6752 | 0.67516 | 0.51273 | 2.5127 | 5.8476 | 6.5227 | 7.5227 | 10.0355 | 0.01
3.9593 | 7.9796 | 5.9593 | 4.9593 | 6.9389 | 8.9389 | 7.9796 | 12.9389 | 19.8778 | 28.8168 | 3.9693 | 7.9896 | 5.9593 | 4.9593 | 6.9389 | 8.9389 | 7.9896 | 12.9489 | 19.8878 | 28.8268 | 0.01
6.3046 | 9.1523 | 8.3046 | 7.3046 | 10.457 | 12.457 | 9.1523 | 16.457 | 26.9139 | 39.3709 | 6.3146 | 9.1623 | 8.3046 | 7.3046 | 10.457 | 12.457 | 9.1623 | 16.467 | 26.9239 | 39.3809 | 0.01
8.2062 | 10.1031 | 10.2062 | 9.2062 | 13.3094 | 15.3094 | 10.1031 | 19.3094 | 32.6187 | 47.9281 | 8.2162 | 10.1131 | 10.2062 | 9.2062 | 13.3094 | 15.3094 | 10.1131 | 19.3194 | 32.6287 | 47.9381 | 0.01
4.8148 | 8.4074 | 6.8148 | 5.8148 | 8.2222 | 10.2222 | 8.4074 | 14.2222 | 22.4444 | 32.6666 | 4.8248 | 8.4174 | 6.8148 | 5.8148 | 8.2222 | 10.2222 | 8.4174 | 14.2322 | 22.4544 | 32.6766 | 0.01
8.5173 | 10.2586 | 10.5173 | 9.5173 | 13.7759 | 15.7759 | 10.2586 | 19.7759 | 33.5518 | 49.3277 | 8.5273 | 10.2686 | 10.5173 | 9.5173 | 13.7759 | 15.7759 | 10.2686 | 19.7859 | 33.5618 | 49.3377 | 0.01
7.0746 | 9.5373 | 9.0746 | 8.0746 | 11.6118 | 13.6118 | 9.5373 | 17.6118 | 29.2237 | 42.8355 | 7.0846 | 9.5473 | 9.0746 | 8.0746 | 11.6118 | 13.6118 | 9.5473 | 17.6218 | 29.2337 | 42.8455 | 0.01
8.416 | 10.208 | 10.416 | 9.416 | 13.6239 | 15.6239 | 10.208 | 19.6239 | 33.2479 | 48.8718 | 8.426 | 10.218 | 10.416 | 9.416 | 13.6239 | 15.6239 | 10.218 | 19.6339 | 33.2579 | 48.8818 | 0.01
8.9462 | 10.4731 | 10.9462 | 9.9462 | 14.4194 | 16.4194 | 10.4731 | 20.4194 | 34.8387 | 51.2581 | 8.9562 | 10.4831 | 10.9462 | 9.9462 | 14.4194 | 16.4194 | 10.4831 | 20.4294 | 34.8487 | 51.2681 | 0.01
5.8459 | 8.9229 | 7.8459 | 6.8459 | 9.7688 | 11.7688 | 8.9229 | 15.7688 | 25.5377 | 37.3065 | 5.8559 | 8.9329 | 7.8459 | 6.8459 | 9.7688 | 11.7688 | 8.9329 | 15.7788 | 25.5477 | 37.3165 | 0.01
5.2305 | 8.6152 | 7.2305 | 6.2305 | 8.8457 | 10.8457 | 8.6152 | 14.8457 | 23.6914 | 34.5372 | 5.2405 | 8.6252 | 7.2305 | 6.2305 | 8.8457 | 10.8457 | 8.6252 | 14.8557 | 23.7014 | 34.5472 | 0.01
9.1373 | 10.5687 | 11.1373 | 10.1373 | 14.706 | 16.706 | 10.5687 | 20.706 | 35.412 | 52.118 | 9.1473 | 10.5787 | 11.1373 | 10.1373 | 14.706 | 16.706 | 10.5787 | 20.716 | 35.422 | 52.128 | 0.01
3.3969 | 7.6984 | 5.3969 | 4.3969 | 6.0953 | 8.0953 | 7.6984 | 12.0953 | 18.1907 | 26.286 | 3.4069 | 7.7084 | 5.3969 | 4.3969 | 6.0953 | 8.0953 | 7.7084 | 12.1053 | 18.2007 | 26.296 | 0.01
5.7851 | 8.8925 | 7.7851 | 6.7851 | 9.6776 | 11.6776 | 8.8925 | 15.6776 | 25.3552 | 37.0328 | 5.7951 | 8.9025 | 7.7851 | 6.7851 | 9.6776 | 11.6776 | 8.9025 | 15.6876 | 25.3652 | 37.0428 | 0.01
5.2086 | 8.6043 | 7.2086 | 6.2086 | 8.8129 | 10.8129 | 8.6043 | 14.8129 | 23.6258 | 34.4387 | 5.2186 | 8.6143 | 7.2086 | 6.2086 | 8.8129 | 10.8129 | 8.6143 | 14.8229 | 23.6358 | 34.4487 | 0.01
9.7622 | 10.8811 | 11.7622 | 10.7622 | 15.6432 | 17.6432 | 10.8811 | 21.6432 | 37.2865 | 54.9297 | 9.7722 | 10.8911 | 11.7622 | 10.7622 | 15.6432 | 17.6432 | 10.8911 | 21.6532 | 37.2965 | 54.9397 | 0.01
3.5986 | 7.7993 | 5.5986 | 4.5986 | 6.398 | 8.398 | 7.7993 | 12.398 | 18.7959 | 27.1939 | 3.6086 | 7.8093 | 5.5986 | 4.5986 | 6.398 | 8.398 | 7.8093 | 12.408 | 18.8059 | 27.2039 | 0.01
7.4765 | 9.7382 | 9.4765 | 8.4765 | 12.2147 | 14.2147 | 9.7382 | 18.2147 | 30.4295 | 44.6442 | 7.4865 | 9.7482 | 9.4765 | 8.4765 | 12.2147 | 14.2147 | 9.7482 | 18.2247 | 30.4395 | 44.6542 | 0.01
5.1836 | 8.5918 | 7.1836 | 6.1836 | 8.7754 | 10.7754 | 8.5918 | 14.7754 | 23.5508 | 34.3262 | 5.1936 | 8.6018 | 7.1836 | 6.1836 | 8.7754 | 10.7754 | 8.6018 | 14.7854 | 23.5608 | 34.3362 | 0.01
6.9591 | 9.4795 | 8.9591 | 7.9591 | 11.4386 | 13.4386 | 9.4795 | 17.4386 | 28.8773 | 42.3159 | 6.9691 | 9.4895 | 8.9591 | 7.9591 | 11.4386 | 13.4386 | 9.4895 | 17.4486 | 28.8873 | 42.3259 | 0.01
7.3402 | 9.6701 | 9.3402 | 8.3402 | 12.0102 | 14.0102 | 9.6701 | 18.0102 | 30.0205 | 44.0307 | 7.3502 | 9.6801 | 9.3402 | 8.3402 | 12.0102 | 14.0102 | 9.6801 | 18.0202 | 30.0305 | 44.0407 | 0.01
6.9202 | 9.4601 | 8.9202 | 7.9202 | 11.3802 | 13.3802 | 9.4601 | 17.3802 | 28.7605 | 42.1407 | 6.9302 | 9.4701 | 8.9202 | 7.9202 | 11.3802 | 13.3802 | 9.4701 | 17.3902 | 28.7705 | 42.1507 | 0.01
8.5367 | 10.2684 | 10.5367 | 9.5367 | 13.8051 | 15.8051 | 10.2684 | 19.8051 | 33.6101 | 49.4152 | 8.5467 | 10.2784 | 10.5367 | 9.5367 | 13.8051 | 15.8051 | 10.2784 | 19.8151 | 33.6201 | 49.4252 | 0.01
2.5804 | 7.2902 | 4.5804 | 3.5804 | 4.8705 | 6.8705 | 7.2902 | 10.8705 | 15.7411 | 22.6116 | 2.5904 | 7.3002 | 4.5804 | 3.5804 | 4.8705 | 6.8705 | 7.3002 | 10.8805 | 15.7511 | 22.6216 | 0.01
6.5936 | 9.2968 | 8.5936 | 7.5936 | 10.8904 | 12.8904 | 9.2968 | 16.8904 | 27.7808 | 40.6712 | 6.6036 | 9.3068 | 8.5936 | 7.5936 | 10.8904 | 12.8904 | 9.3068 | 16.9004 | 27.7908 | 40.6812 | 0.01
7.008 | 9.504 | 9.008 | 8.008 | 11.5121 | 13.5121 | 9.504 | 17.5121 | 29.0241 | 42.5362 | 7.018 | 9.514 | 9.008 | 8.008 | 11.5121 | 13.5121 | 9.514 | 17.5221 | 29.0341 | 42.5462 | 0.01
4.2915 | 8.1458 | 6.2915 | 5.2915 | 7.4373 | 9.4373 | 8.1458 | 13.4373 | 20.8746 | 30.3119 | 4.3015 | 8.1558 | 6.2915 | 5.2915 | 7.4373 | 9.4373 | 8.1558 | 13.4473 | 20.8846 | 30.3219 | 0.01
5.4512 | 8.7256 | 7.4512 | 6.4512 | 9.1769 | 11.1769 | 8.7256 | 15.1769 | 24.3537 | 35.5306 | 5.4612 | 8.7356 | 7.4512 | 6.4512 | 9.1769 | 11.1769 | 8.7356 | 15.1869 | 24.3637 | 35.5406 | 0.01
6.5064 | 9.2532 | 8.5064 | 7.5064 | 10.7595 | 12.7595 | 9.2532 | 16.7595 | 27.5191 | 40.2786 | 6.5164 | 9.2632 | 8.5064 | 7.5064 | 10.7595 | 12.7595 | 9.2632 | 16.7695 | 27.5291 | 40.2886 | 0.01
3.6406 | 7.8203 | 5.6406 | 4.6406 | 6.4609 | 8.4609 | 7.8203 | 12.4609 | 18.9218 | 27.3827 | 3.6506 | 7.8303 | 5.6406 | 4.6406 | 6.4609 | 8.4609 | 7.8303 | 12.4709 | 18.9318 | 27.3927 | 0.01
2.298 | 7.149 | 4.298 | 3.298 | 4.4469 | 6.4469 | 7.149 | 10.4469 | 14.8939 | 21.3408 | 2.308 | 7.159 | 4.298 | 3.298 | 4.4469 | 6.4469 | 7.159 | 10.4569 | 14.9039 | 21.3508 | 0.01
4.4543 | 8.2271 | 6.4543 | 5.4543 | 7.6814 | 9.6814 | 8.2271 | 13.6814 | 21.3629 | 31.0443 | 4.4643 | 8.2371 | 6.4543 | 5.4543 | 7.6814 | 9.6814 | 8.2371 | 13.6914 | 21.3729 | 31.0543 | 0.01
4.6213 | 8.3106 | 6.6213 | 5.6213 | 7.9319 | 9.9319 | 8.3106 | 13.9319 | 21.8639 | 31.7958 | 4.6313 | 8.3206 | 6.6213 | 5.6213 | 7.9319 | 9.9319 | 8.3206 | 13.9419 | 21.8739 | 31.8058 | 0.01
7.3267 | 9.6634 | 9.3267 | 8.3267 | 11.9901 | 13.9901 | 9.6634 | 17.9901 | 29.9802 | 43.9703 | 7.3367 | 9.6734 | 9.3267 | 8.3267 | 11.9901 | 13.9901 | 9.6734 | 18.0001 | 29.9902 | 43.9803 | 0.01
6.5492 | 9.2746 | 8.5492 | 7.5492 | 10.8238 | 12.8238 | 9.2746 | 16.8238 | 27.6476 | 40.4714 | 6.5592 | 9.2846 | 8.5492 | 7.5492 | 10.8238 | 12.8238 | 9.2846 | 16.8338 | 27.6576 | 40.4814 | 0.01
7.857 | 9.9285 | 9.857 | 8.857 | 12.7855 | 14.7855 | 9.9285 | 18.7855 | 31.5709 | 46.3564 | 7.867 | 9.9385 | 9.857 | 8.857 | 12.7855 | 14.7855 | 9.9385 | 18.7955 | 31.5809 | 46.3664 | 0.01
4.737 | 8.3685 | 6.737 | 5.737 | 8.1055 | 10.1055 | 8.3685 | 14.1055 | 22.211 | 32.3165 | 4.747 | 8.3785 | 6.737 | 5.737 | 8.1055 | 10.1055 | 8.3785 | 14.1155 | 22.221 | 32.3265 | 0.01
6.7225 | 9.3613 | 8.7225 | 7.7225 | 11.0838 | 13.0838 | 9.3613 | 17.0838 | 28.1676 | 41.2514 | 6.7325 | 9.3713 | 8.7225 | 7.7225 | 11.0838 | 13.0838 | 9.3713 | 17.0938 | 28.1776 | 41.2614 | 0.01
3.4789 | 7.7395 | 5.4789 | 4.4789 | 6.2184 | 8.2184 | 7.7395 | 12.2184 | 18.4368 | 26.6552 | 3.4889 | 7.7495 | 5.4789 | 4.4789 | 6.2184 | 8.2184 | 7.7495 | 12.2284 | 18.4468 | 26.6652 | 0.01
6.17 | 9.085 | 8.17 | 7.17 | 10.255 | 12.255 | 9.085 | 16.255 | 26.51 | 38.765 | 6.18 | 9.095 | 8.17 | 7.17 | 10.255 | 12.255 | 9.095 | 16.265 | 26.52 | 38.775 | 0.01
7.0712 | 9.5356 | 9.0712 | 8.0712 | 11.6069 | 13.6069 | 9.5356 | 17.6069 | 29.2137 | 42.8206 | 7.0812 | 9.5456 | 9.0712 | 8.0712 | 11.6069 | 13.6069 | 9.5456 | 17.6169 | 29.2237 | 42.8306 | 0.01
4.6825 | 8.3413 | 6.6825 | 5.6825 | 8.0238 | 10.0238 | 8.3413 | 14.0238 | 22.0475 | 32.0713 | 4.6925 | 8.3513 | 6.6825 | 5.6825 | 8.0238 | 10.0238 | 8.3513 | 14.0338 | 22.0575 | 32.0813 | 0.01
4.7503 | 8.3752 | 6.7503 | 5.7503 | 8.1255 | 10.1255 | 8.3752 | 14.1255 | 22.251 | 32.3765 | 4.7603 | 8.3852 | 6.7503 | 5.7503 | 8.1255 | 10.1255 | 8.3852 | 14.1355 | 22.261 | 32.3865 | 0.01
5.1509 | 8.5755 | 7.1509 | 6.1509 | 8.7264 | 10.7264 | 8.5755 | 14.7264 | 23.4527 | 34.1791 | 5.1609 | 8.5855 | 7.1509 | 6.1509 | 8.7264 | 10.7264 | 8.5855 | 14.7364 | 23.4627 | 34.1891 | 0.01
3.943 | 7.9715 | 5.943 | 4.943 | 6.9145 | 8.9145 | 7.9715 | 12.9145 | 19.829 | 28.7435 | 3.953 | 7.9815 | 5.943 | 4.943 | 6.9145 | 8.9145 | 7.9815 | 12.9245 | 19.839 | 28.7535 | 0.01
4.7658 | 8.3829 | 6.7658 | 5.7658 | 8.1487 | 10.1487 | 8.3829 | 14.1487 | 22.2975 | 32.4462 | 4.7758 | 8.3929 | 6.7658 | 5.7658 | 8.1487 | 10.1487 | 8.3929 | 14.1587 | 22.3075 | 32.4562 | 0.01
4.0394 | 8.0197 | 6.0394 | 5.0394 | 7.0591 | 9.0591 | 8.0197 | 13.0591 | 20.1183 | 29.1774 | 4.0494 | 8.0297 | 6.0394 | 5.0394 | 7.0591 | 9.0591 | 8.0297 | 13.0691 | 20.1283 | 29.1874 | 0.01
5.853 | 8.9265 | 7.853 | 6.853 | 9.7796 | 11.7796 | 8.9265 | 15.7796 | 25.5591 | 37.3387 | 5.863 | 8.9365 | 7.853 | 6.853 | 9.7796 | 11.7796 | 8.9365 | 15.7896 | 25.5691 | 37.3487 | 0.01
4.7804 | 8.3902 | 6.7804 | 5.7804 | 8.1706 | 10.1706 | 8.3902 | 14.1706 | 22.3412 | 32.5118 | 4.7904 | 8.4002 | 6.7804 | 5.7804 | 8.1706 | 10.1706 | 8.4002 | 14.1806 | 22.3512 | 32.5218 | 0.01
6.723 | 9.3615 | 8.723 | 7.723 | 11.0845 | 13.0845 | 9.3615 | 17.0845 | 28.1691 | 41.2536 | 6.733 | 9.3715 | 8.723 | 7.723 | 11.0845 | 13.0845 | 9.3715 | 17.0945 | 28.1791 | 41.2636 | 0.01
6.7678 | 9.3839 | 8.7678 | 7.7678 | 11.1517 | 13.1517 | 9.3839 | 17.1517 | 28.3035 | 41.4552 | 6.7778 | 9.3939 | 8.7678 | 7.7678 | 11.1517 | 13.1517 | 9.3939 | 17.1617 | 28.3135 | 41.4652 | 0.01
7.4987 | 9.7493 | 9.4987 | 8.4987 | 12.248 | 14.248 | 9.7493 | 18.248 | 30.4961 | 44.7441 | 7.5087 | 9.7593 | 9.4987 | 8.4987 | 12.248 | 14.248 | 9.7593 | 18.258 | 30.5061 | 44.7541 | 0.01
7.5272 | 9.7636 | 9.5272 | 8.5272 | 12.2908 | 14.2908 | 9.7636 | 18.2908 | 30.5815 | 44.8723 | 7.5372 | 9.7736 | 9.5272 | 8.5272 | 12.2908 | 14.2908 | 9.7736 | 18.3008 | 30.5915 | 44.8823 | 0.01
5.9533 | 8.9766 | 7.9533 | 6.9533 | 9.9299 | 11.9299 | 8.9766 | 15.9299 | 25.8599 | 37.7898 | 5.9633 | 8.9866 | 7.9533 | 6.9533 | 9.9299 | 11.9299 | 8.9866 | 15.9399 | 25.8699 | 37.7998 | 0.01
8.9004 | 10.4502 | 10.9004 | 9.9004 | 14.3506 | 16.3506 | 10.4502 | 20.3506 | 34.7012 | 51.0517 | 8.9104 | 10.4602 | 10.9004 | 9.9004 | 14.3506 | 16.3506 | 10.4602 | 20.3606 | 34.7112 | 51.0617 | 0.01
6.7745 | 9.3873 | 8.7745 | 7.7745 | 11.1618 | 13.1618 | 9.3873 | 17.1618 | 28.3236 | 41.4854 | 6.7845 | 9.3973 | 8.7745 | 7.7745 | 11.1618 | 13.1618 | 9.3973 | 17.1718 | 28.3336 | 41.4954 | 0.01
6.78 | 9.39 | 8.78 | 7.78 | 11.1701 | 13.1701 | 9.39 | 17.1701 | 28.3401 | 41.5102 | 6.79 | 9.4 | 8.78 | 7.78 | 11.1701 | 13.1701 | 9.4 | 17.1801 | 28.3501 | 41.5202 | 0.01
7.4491 | 9.7245 | 9.4491 | 8.4491 | 12.1736 | 14.1736 | 9.7245 | 18.1736 | 30.3472 | 44.5207 | 7.4591 | 9.7345 | 9.4491 | 8.4491 | 12.1736 | 14.1736 | 9.7345 | 18.1836 | 30.3572 | 44.5307 | 0.01
8.8211 | 10.4105 | 10.8211 | 9.8211 | 14.2316 | 16.2316 | 10.4105 | 20.2316 | 34.4633 | 50.6949 | 8.8311 | 10.4205 | 10.8211 | 9.8211 | 14.2316 | 16.2316 | 10.4205 | 20.2416 | 34.4733 | 50.7049 | 0.01
2.8291 | 7.4146 | 4.8291 | 3.8291 | 5.2437 | 7.2437 | 7.4146 | 11.2437 | 16.4873 | 23.731 | 2.8391 | 7.4246 | 4.8291 | 3.8291 | 5.2437 | 7.2437 | 7.4246 | 11.2537 | 16.4973 | 23.741 | 0.01
5.8259 | 8.9129 | 7.8259 | 6.8259 | 9.7388 | 11.7388 | 8.9129 | 15.7388 | 25.4776 | 37.2164 | 5.8359 | 8.9229 | 7.8259 | 6.8259 | 9.7388 | 11.7388 | 8.9229 | 15.7488 | 25.4876 | 37.2264 | 0.01
5.7602 | 8.8801 | 7.7602 | 6.7602 | 9.6404 | 11.6404 | 8.8801 | 15.6404 | 25.2807 | 36.9211 | 5.7702 | 8.8901 | 7.7602 | 6.7602 | 9.6404 | 11.6404 | 8.8901 | 15.6504 | 25.2907 | 36.9311 | 0.01
6.6595 | 9.3297 | 8.6595 | 7.6595 | 10.9892 | 12.9892 | 9.3297 | 16.9892 | 27.9784 | 40.9675 | 6.6695 | 9.3397 | 8.6595 | 7.6595 | 10.9892 | 12.9892 | 9.3397 | 16.9992 | 27.9884 | 40.9775 | 0.01
8.6011 | 10.3006 | 10.6011 | 9.6011 | 13.9017 | 15.9017 | 10.3006 | 19.9017 | 33.8033 | 49.705 | 8.6111 | 10.3106 | 10.6011 | 9.6011 | 13.9017 | 15.9017 | 10.3106 | 19.9117 | 33.8133 | 49.715 | 0.01
6.848 | 9.424 | 8.848 | 7.848 | 11.272 | 13.272 | 9.424 | 17.272 | 28.5439 | 41.8159 | 6.858 | 9.434 | 8.848 | 7.848 | 11.272 | 13.272 | 9.434 | 17.282 | 28.5539 | 41.8259 | 0.01
5.4812 | 8.7406 | 7.4812 | 6.4812 | 9.2218 | 11.2218 | 8.7406 | 15.2218 | 24.4437 | 35.6655 | 5.4912 | 8.7506 | 7.4812 | 6.4812 | 9.2218 | 11.2218 | 8.7506 | 15.2318 | 24.4537 | 35.6755 | 0.01
6.5819 | 9.2909 | 8.5819 | 7.5819 | 10.8728 | 12.8728 | 9.2909 | 16.8728 | 27.7456 | 40.6184 | 6.5919 | 9.3009 | 8.5819 | 7.5819 | 10.8728 | 12.8728 | 9.3009 | 16.8828 | 27.7556 | 40.6284 | 0.01
3.0966 | 7.5483 | 5.0966 | 4.0966 | 5.6448 | 7.6448 | 7.5483 | 11.6448 | 17.2897 | 24.9345 | 3.1066 | 7.5583 | 5.0966 | 4.0966 | 5.6448 | 7.6448 | 7.5583 | 11.6548 | 17.2997 | 24.9445 | 0.01
7.5203 | 9.7602 | 9.5203 | 8.5203 | 12.2805 | 14.2805 | 9.7602 | 18.2805 | 30.561 | 44.8416 | 7.5303 | 9.7702 | 9.5203 | 8.5203 | 12.2805 | 14.2805 | 9.7702 | 18.2905 | 30.571 | 44.8516 | 0.01
5.3622 | 8.6811 | 7.3622 | 6.3622 | 9.0433 | 11.0433 | 8.6811 | 15.0433 | 24.0867 | 35.13 | 5.3722 | 8.6911 | 7.3622 | 6.3622 | 9.0433 | 11.0433 | 8.6911 | 15.0533 | 24.0967 | 35.14 | 0.01
3.0589 | 7.5295 | 5.0589 | 4.0589 | 5.5884 | 7.5884 | 7.5295 | 11.5884 | 17.1768 | 24.7653 | 3.0689 | 7.5395 | 5.0589 | 4.0589 | 5.5884 | 7.5884 | 7.5395 | 11.5984 | 17.1868 | 24.7753 | 0.01
5.5666 | 8.7833 | 7.5666 | 6.5666 | 9.3498 | 11.3498 | 8.7833 | 15.3498 | 24.6997 | 36.0495 | 5.5766 | 8.7933 | 7.5666 | 6.5666 | 9.3498 | 11.3498 | 8.7933 | 15.3598 | 24.7097 | 36.0595 | 0.01
7.0962 | 9.5481 | 9.0962 | 8.0962 | 11.6442 | 13.6442 | 9.5481 | 17.6442 | 29.2885 | 42.9327 | 7.1062 | 9.5581 | 9.0962 | 8.0962 | 11.6442 | 13.6442 | 9.5581 | 17.6542 | 29.2985 | 42.9427 | 0.01
5.3982 | 8.6991 | 7.3982 | 6.3982 | 9.0973 | 11.0973 | 8.6991 | 15.0973 | 24.1946 | 35.2919 | 5.4082 | 8.7091 | 7.3982 | 6.3982 | 9.0973 | 11.0973 | 8.7091 | 15.1073 | 24.2046 | 35.3019 | 0.01
9.911 | 10.9555 | 11.911 | 10.911 | 15.8666 | 17.8666 | 10.9555 | 21.8666 | 37.7331 | 55.5997 | 9.921 | 10.9655 | 11.911 | 10.911 | 15.8666 | 17.8666 | 10.9655 | 21.8766 | 37.7431 | 55.6097 | 0.01
5.7213 | 8.8606 | 7.7213 | 6.7213 | 9.5819 | 11.5819 | 8.8606 | 15.5819 | 25.1638 | 36.7458 | 5.7313 | 8.8706 | 7.7213 | 6.7213 | 9.5819 | 11.5819 | 8.8706 | 15.5919 | 25.1738 | 36.7558 | 0.01
3.4139 | 7.7069 | 5.4139 | 4.4139 | 6.1208 | 8.1208 | 7.7069 | 12.1208 | 18.2416 | 26.3625 | 3.4239 | 7.7169 | 5.4139 | 4.4139 | 6.1208 | 8.1208 | 7.7169 | 12.1308 | 18.2516 | 26.3725 | 0.01
1.2177 | 6.6089 | 3.2177 | 2.2177 | 2.8266 | 4.8266 | 6.6089 | 8.8266 | 11.6532 | 16.4798 | 1.2277 | 6.6189 | 3.2177 | 2.2177 | 2.8266 | 4.8266 | 6.6189 | 8.8366 | 11.6632 | 16.4898 | 0.01
3.9393 | 7.9697 | 5.9393 | 4.9393 | 6.909 | 8.909 | 7.9697 | 12.909 | 19.818 | 28.727 | 3.9493 | 7.9797 | 5.9393 | 4.9393 | 6.909 | 8.909 | 7.9797 | 12.919 | 19.828 | 28.737 | 0.01
1.9111 | 6.9556 | 3.9111 | 2.9111 | 3.8667 | 5.8667 | 6.9556 | 9.8667 | 13.7333 | 19.6 | 1.9211 | 6.9656 | 3.9111 | 2.9111 | 3.8667 | 5.8667 | 6.9656 | 9.8767 | 13.7433 | 19.61 | 0.01
7.5561 | 9.778 | 9.5561 | 8.5561 | 12.3341 | 14.3341 | 9.778 | 18.3341 | 30.6683 | 45.0024 | 7.5661 | 9.788 | 9.5561 | 8.5561 | 12.3341 | 14.3341 | 9.788 | 18.3441 | 30.6783 | 45.0124 | 0.01
6.1834 | 9.0917 | 8.1834 | 7.1834 | 10.2751 | 12.2751 | 9.0917 | 16.2751 | 26.5503 | 38.8254 | 6.1934 | 9.1017 | 8.1834 | 7.1834 | 10.2751 | 12.2751 | 9.1017 | 16.2851 | 26.5603 | 38.8354 | 0.01
6.4385 | 9.2192 | 8.4385 | 7.4385 | 10.6577 | 12.6577 | 9.2192 | 16.6577 | 27.3155 | 39.9732 | 6.4485 | 9.2292 | 8.4385 | 7.4385 | 10.6577 | 12.6577 | 9.2292 | 16.6677 | 27.3255 | 39.9832 | 0.01
8.0349 | 10.0174 | 10.0349 | 9.0349 | 13.0523 | 15.0523 | 10.0174 | 19.0523 | 32.1047 | 47.157 | 8.0449 | 10.0274 | 10.0349 | 9.0349 | 13.0523 | 15.0523 | 10.0274 | 19.0623 | 32.1147 | 47.167 | 0.01
7.867 | 9.9335 | 9.867 | 8.867 | 12.8004 | 14.8004 | 9.9335 | 18.8004 | 31.6009 | 46.4013 | 7.877 | 9.9435 | 9.867 | 8.867 | 12.8004 | 14.8004 | 9.9435 | 18.8104 | 31.6109 | 46.4113 | 0.01
9.377 | 10.6885 | 11.377 | 10.377 | 15.0655 | 17.0655 | 10.6885 | 21.0655 | 36.131 | 53.1965 | 9.387 | 10.6985 | 11.377 | 10.377 | 15.0655 | 17.0655 | 10.6985 | 21.0755 | 36.141 | 53.2065 | 0.01
6.6239 | 9.3119 | 8.6239 | 7.6239 | 10.9358 | 12.9358 | 9.3119 | 16.9358 | 27.8716 | 40.8073 | 6.6339 | 9.3219 | 8.6239 | 7.6239 | 10.9358 | 12.9358 | 9.3219 | 16.9458 | 27.8816 | 40.8173 | 0.01
6.2069 | 9.1035 | 8.2069 | 7.2069 | 10.3104 | 12.3104 | 9.1035 | 16.3104 | 26.6207 | 38.9311 | 6.2169 | 9.1135 | 8.2069 | 7.2069 | 10.3104 | 12.3104 | 9.1135 | 16.3204 | 26.6307 | 38.9411 | 0.01
9.2106 | 10.6053 | 11.2106 | 10.2106 | 14.816 | 16.816 | 10.6053 | 20.816 | 35.6319 | 52.4479 | 9.2206 | 10.6153 | 11.2106 | 10.2106 | 14.816 | 16.816 | 10.6153 | 20.826 | 35.6419 | 52.4579 | 0.01
8.1358 | 10.0679 | 10.1358 | 9.1358 | 13.2038 | 15.2038 | 10.0679 | 19.2038 | 32.4075 | 47.6113 | 8.1458 | 10.0779 | 10.1358 | 9.1358 | 13.2038 | 15.2038 | 10.0779 | 19.2138 | 32.4175 | 47.6213 | 0.01
5.0617 | 8.5309 | 7.0617 | 6.0617 | 8.5926 | 10.5926 | 8.5309 | 14.5926 | 23.1852 | 33.7778 | 5.0717 | 8.5409 | 7.0617 | 6.0617 | 8.5926 | 10.5926 | 8.5409 | 14.6026 | 23.1952 | 33.7878 | 0.01
6.6753 | 9.3376 | 8.6753 | 7.6753 | 11.0129 | 13.0129 | 9.3376 | 17.0129 | 28.0258 | 41.0388 | 6.6853 | 9.3476 | 8.6753 | 7.6753 | 11.0129 | 13.0129 | 9.3476 | 17.0229 | 28.0358 | 41.0488 | 0.01
3.4542 | 7.7271 | 5.4542 | 4.4542 | 6.1813 | 8.1813 | 7.7271 | 12.1813 | 18.3625 | 26.5438 | 3.4642 | 7.7371 | 5.4542 | 4.4542 | 6.1813 | 8.1813 | 7.7371 | 12.1913 | 18.3725 | 26.5538 | 0.01
5.1056 | 8.5528 | 7.1056 | 6.1056 | 8.6584 | 10.6584 | 8.5528 | 14.6584 | 23.3169 | 33.9753 | 5.1156 | 8.5628 | 7.1056 | 6.1056 | 8.6584 | 10.6584 | 8.5628 | 14.6684 | 23.3269 | 33.9853 | 0.01
3.5613 | 7.7807 | 5.5613 | 4.5613 | 6.342 | 8.342 | 7.7807 | 12.342 | 18.684 | 27.026 | 3.5713 | 7.7907 | 5.5613 | 4.5613 | 6.342 | 8.342 | 7.7907 | 12.352 | 18.694 | 27.036 | 0.01
6.4972 | 9.2486 | 8.4972 | 7.4972 | 10.7457 | 12.7457 | 9.2486 | 16.7457 | 27.4915 | 40.2372 | 6.5072 | 9.2586 | 8.4972 | 7.4972 | 10.7457 | 12.7457 | 9.2586 | 16.7557 | 27.5015 | 40.2472 | 0.01
4.3738 | 8.1869 | 6.3738 | 5.3738 | 7.5607 | 9.5607 | 8.1869 | 13.5607 | 21.1213 | 30.682 | 4.3838 | 8.1969 | 6.3738 | 5.3738 | 7.5607 | 9.5607 | 8.1969 | 13.5707 | 21.1313 | 30.692 | 0.01
3.9362 | 7.9681 | 5.9362 | 4.9362 | 6.9044 | 8.9044 | 7.9681 | 12.9044 | 19.8087 | 28.7131 | 3.9462 | 7.9781 | 5.9362 | 4.9362 | 6.9044 | 8.9044 | 7.9781 | 12.9144 | 19.8187 | 28.7231 | 0.01
8.9776 | 10.4888 | 10.9776 | 9.9776 | 14.4663 | 16.4663 | 10.4888 | 20.4663 | 34.9327 | 51.399 | 8.9876 | 10.4988 | 10.9776 | 9.9776 | 14.4663 | 16.4663 | 10.4988 | 20.4763 | 34.9427 | 51.409 | 0.01
6.1982 | 9.0991 | 8.1982 | 7.1982 | 10.2972 | 12.2972 | 9.0991 | 16.2972 | 26.5945 | 38.8917 | 6.2082 | 9.1091 | 8.1982 | 7.1982 | 10.2972 | 12.2972 | 9.1091 | 16.3072 | 26.6045 | 38.9017 | 0.01
7.228 | 9.614 | 9.228 | 8.228 | 11.842 | 13.842 | 9.614 | 17.842 | 29.6841 | 43.5261 | 7.238 | 9.624 | 9.228 | 8.228 | 11.842 | 13.842 | 9.624 | 17.852 | 29.6941 | 43.5361 | 0.01
7.6249 | 9.8125 | 9.6249 | 8.6249 | 12.4374 | 14.4374 | 9.8125 | 18.4374 | 30.8748 | 45.3122 | 7.6349 | 9.8225 | 9.6249 | 8.6249 | 12.4374 | 14.4374 | 9.8225 | 18.4474 | 30.8848 | 45.3222 | 0.01
7.173 | 9.5865 | 9.173 | 8.173 | 11.7596 | 13.7596 | 9.5865 | 17.7596 | 29.5191 | 43.2787 | 7.183 | 9.5965 | 9.173 | 8.173 | 11.7596 | 13.7596 | 9.5965 | 17.7696 | 29.5291 | 43.2887 | 0.01
7.9303 | 9.9652 | 9.9303 | 8.9303 | 12.8955 | 14.8955 | 9.9652 | 18.8955 | 31.791 | 46.6865 | 7.9403 | 9.9752 | 9.9303 | 8.9303 | 12.8955 | 14.8955 | 9.9752 | 18.9055 | 31.801 | 46.6965 | 0.01
5.3469 | 8.6734 | 7.3469 | 6.3469 | 9.0203 | 11.0203 | 8.6734 | 15.0203 | 24.0406 | 35.0609 | 5.3569 | 8.6834 | 7.3469 | 6.3469 | 9.0203 | 11.0203 | 8.6834 | 15.0303 | 24.0506 | 35.0709 | 0.01
4.0556 | 8.0278 | 6.0556 | 5.0556 | 7.0835 | 9.0835 | 8.0278 | 13.0835 | 20.1669 | 29.2504 | 4.0656 | 8.0378 | 6.0556 | 5.0556 | 7.0835 | 9.0835 | 8.0378 | 13.0935 | 20.1769 | 29.2604 | 0.01
4.5911 | 8.2955 | 6.5911 | 5.5911 | 7.8866 | 9.8866 | 8.2955 | 13.8866 | 21.7732 | 31.6599 | 4.6011 | 8.3055 | 6.5911 | 5.5911 | 7.8866 | 9.8866 | 8.3055 | 13.8966 | 21.7832 | 31.6699 | 0.01
4.982 | 8.491 | 6.982 | 5.982 | 8.473 | 10.473 | 8.491 | 14.473 | 22.946 | 33.419 | 4.992 | 8.501 | 6.982 | 5.982 | 8.473 | 10.473 | 8.501 | 14.483 | 22.956 | 33.429 | 0.01
5.7233 | 8.8617 | 7.7233 | 6.7233 | 9.585 | 11.585 | 8.8617 | 15.585 | 25.1699 | 36.7549 | 5.7333 | 8.8717 | 7.7233 | 6.7233 | 9.585 | 11.585 | 8.8717 | 15.595 | 25.1799 | 36.7649 | 0.01
8.0559 | 10.0279 | 10.0559 | 9.0559 | 13.0838 | 15.0838 | 10.0279 | 19.0838 | 32.1677 | 47.2515 | 8.0659 | 10.0379 | 10.0559 | 9.0559 | 13.0838 | 15.0838 | 10.0379 | 19.0938 | 32.1777 | 47.2615 | 0.01
6.1811 | 9.0906 | 8.1811 | 7.1811 | 10.2717 | 12.2717 | 9.0906 | 16.2717 | 26.5433 | 38.815 | 6.1911 | 9.1006 | 8.1811 | 7.1811 | 10.2717 | 12.2717 | 9.1006 | 16.2817 | 26.5533 | 38.825 | 0.01
7.9025 | 9.9513 | 9.9025 | 8.9025 | 12.8538 | 14.8538 | 9.9513 | 18.8538 | 31.7076 | 46.5614 | 7.9125 | 9.9613 | 9.9025 | 8.9025 | 12.8538 | 14.8538 | 9.9613 | 18.8638 | 31.7176 | 46.5714 | 0.01
5.791 | 8.8955 | 7.791 | 6.791 | 9.6865 | 11.6865 | 8.8955 | 15.6865 | 25.373 | 37.0595 | 5.801 | 8.9055 | 7.791 | 6.791 | 9.6865 | 11.6865 | 8.9055 | 15.6965 | 25.383 | 37.0695 | 0.01
3.1031 | 7.5516 | 5.1031 | 4.1031 | 5.6547 | 7.6547 | 7.5516 | 11.6547 | 17.3094 | 24.9641 | 3.1131 | 7.5616 | 5.1031 | 4.1031 | 5.6547 | 7.6547 | 7.5616 | 11.6647 | 17.3194 | 24.9741 | 0.01
5.9244 | 8.9622 | 7.9244 | 6.9244 | 9.8866 | 11.8866 | 8.9622 | 15.8866 | 25.7733 | 37.6599 | 5.9344 | 8.9722 | 7.9244 | 6.9244 | 9.8866 | 11.8866 | 8.9722 | 15.8966 | 25.7833 | 37.6699 | 0.01
4.3449 | 8.1724 | 6.3449 | 5.3449 | 7.5173 | 9.5173 | 8.1724 | 13.5173 | 21.0347 | 30.552 | 4.3549 | 8.1824 | 6.3449 | 5.3449 | 7.5173 | 9.5173 | 8.1824 | 13.5273 | 21.0447 | 30.562 | 0.01
9.9817 | 10.9909 | 11.9817 | 10.9817 | 15.9726 | 17.9726 | 10.9909 | 21.9726 | 37.9452 | 55.9178 | 9.9917 | 11.0009 | 11.9817 | 10.9817 | 15.9726 | 17.9726 | 11.0009 | 21.9826 | 37.9552 | 55.9278 | 0.01
4.8054 | 8.4027 | 6.8054 | 5.8054 | 8.2081 | 10.2081 | 8.4027 | 14.2081 | 22.4162 | 32.6242 | 4.8154 | 8.4127 | 6.8054 | 5.8054 | 8.2081 | 10.2081 | 8.4127 | 14.2181 | 22.4262 | 32.6342 | 0.01
5.8545 | 8.9272 | 7.8545 | 6.8545 | 9.7817 | 11.7817 | 8.9272 | 15.7817 | 25.5634 | 37.3451 | 5.8645 | 8.9372 | 7.8545 | 6.8545 | 9.7817 | 11.7817 | 8.9372 | 15.7917 | 25.5734 | 37.3551 | 0.01
2.5602 | 7.2801 | 4.5602 | 3.5602 | 4.8403 | 6.8403 | 7.2801 | 10.8403 | 15.6807 | 22.521 | 2.5702 | 7.2901 | 4.5602 | 3.5602 | 4.8403 | 6.8403 | 7.2901 | 10.8503 | 15.6907 | 22.531 | 0.01
3.4258 | 7.7129 | 5.4258 | 4.4258 | 6.1388 | 8.1388 | 7.7129 | 12.1388 | 18.2775 | 26.4163 | 3.4358 | 7.7229 | 5.4258 | 4.4258 | 6.1388 | 8.1388 | 7.7229 | 12.1488 | 18.2875 | 26.4263 | 0.01
5.7932 | 8.8966 | 7.7932 | 6.7932 | 9.6897 | 11.6897 | 8.8966 | 15.6897 | 25.3795 | 37.0692 | 5.8032 | 8.9066 | 7.7932 | 6.7932 | 9.6897 | 11.6897 | 8.9066 | 15.6997 | 25.3895 | 37.0792 | 0.01
4.951 | 8.4755 | 6.951 | 5.951 | 8.4265 | 10.4265 | 8.4755 | 14.4265 | 22.8529 | 33.2794 | 4.961 | 8.4855 | 6.951 | 5.951 | 8.4265 | 10.4265 | 8.4855 | 14.4365 | 22.8629 | 33.2894 | 0.01
5.6438 | 8.8219 | 7.6438 | 6.6438 | 9.4657 | 11.4657 | 8.8219 | 15.4657 | 24.9315 | 36.3972 | 5.6538 | 8.8319 | 7.6438 | 6.6438 | 9.4657 | 11.4657 | 8.8319 | 15.4757 | 24.9415 | 36.4072 | 0.01
6.9783 | 9.4891 | 8.9783 | 7.9783 | 11.4674 | 13.4674 | 9.4891 | 17.4674 | 28.9348 | 42.4023 | 6.9883 | 9.4991 | 8.9783 | 7.9783 | 11.4674 | 13.4674 | 9.4991 | 17.4774 | 28.9448 | 42.4123 | 0.01
10.192 | 11.096 | 12.192 | 11.192 | 16.288 | 18.288 | 11.096 | 22.288 | 38.576 | 56.864 | 10.202 | 11.106 | 12.192 | 11.192 | 16.288 | 18.288 | 11.106 | 22.298 | 38.586 | 56.874 | 0.01
7.611 | 9.8055 | 9.611 | 8.611 | 12.4165 | 14.4165 | 9.8055 | 18.4165 | 30.8329 | 45.2494 | 7.621 | 9.8155 | 9.611 | 8.611 | 12.4165 | 14.4165 | 9.8155 | 18.4265 | 30.8429 | 45.2594 | 0.01
10.7379 | 11.3689 | 12.7379 | 11.7379 | 17.1068 | 19.1068 | 11.3689 | 23.1068 | 40.2137 | 59.3205 | 10.7479 | 11.3789 | 12.7379 | 11.7379 | 17.1068 | 19.1068 | 11.3789 | 23.1168 | 40.2237 | 59.3305 | 0.01
3.3134 | 7.6567 | 5.3134 | 4.3134 | 5.9702 | 7.9702 | 7.6567 | 11.9702 | 17.9403 | 25.9105 | 3.3234 | 7.6667 | 5.3134 | 4.3134 | 5.9702 | 7.9702 | 7.6667 | 11.9802 | 17.9503 | 25.9205 | 0.01
7.374 | 9.687 | 9.374 | 8.374 | 12.061 | 14.061 | 9.687 | 18.061 | 30.1219 | 44.1829 | 7.384 | 9.697 | 9.374 | 8.374 | 12.061 | 14.061 | 9.697 | 18.071 | 30.1319 | 44.1929 | 0.01
7.0434 | 9.5217 | 9.0434 | 8.0434 | 11.5652 | 13.5652 | 9.5217 | 17.5652 | 29.1303 | 42.6955 | 7.0534 | 9.5317 | 9.0434 | 8.0434 | 11.5652 | 13.5652 | 9.5317 | 17.5752 | 29.1403 | 42.7055 | 0.01
4.3583 | 8.1792 | 6.3583 | 5.3583 | 7.5375 | 9.5375 | 8.1792 | 13.5375 | 21.075 | 30.6124 | 4.3683 | 8.1892 | 6.3583 | 5.3583 | 7.5375 | 9.5375 | 8.1892 | 13.5475 | 21.085 | 30.6224 | 0.01
2.3368 | 7.1684 | 4.3368 | 3.3368 | 4.5052 | 6.5052 | 7.1684 | 10.5052 | 15.0104 | 21.5156 | 2.3468 | 7.1784 | 4.3368 | 3.3368 | 4.5052 | 6.5052 | 7.1784 | 10.5152 | 15.0204 | 21.5256 | 0.01
3.7904 | 7.8952 | 5.7904 | 4.7904 | 6.6856 | 8.6856 | 7.8952 | 12.6856 | 19.3711 | 28.0567 | 3.8004 | 7.9052 | 5.7904 | 4.7904 | 6.6856 | 8.6856 | 7.9052 | 12.6956 | 19.3811 | 28.0667 | 0.01
6.4113 | 9.2057 | 8.4113 | 7.4113 | 10.617 | 12.617 | 9.2057 | 16.617 | 27.2339 | 39.8509 | 6.4213 | 9.2157 | 8.4113 | 7.4113 | 10.617 | 12.617 | 9.2157 | 16.627 | 27.2439 | 39.8609 | 0.01
7.4944 | 9.7472 | 9.4944 | 8.4944 | 12.2416 | 14.2416 | 9.7472 | 18.2416 | 30.4833 | 44.7249 | 7.5044 | 9.7572 | 9.4944 | 8.4944 | 12.2416 | 14.2416 | 9.7572 | 18.2516 | 30.4933 | 44.7349 | 0.01
9.8897 | 10.9448 | 11.8897 | 10.8897 | 15.8345 | 17.8345 | 10.9448 | 21.8345 | 37.6691 | 55.5036 | 9.8997 | 10.9548 | 11.8897 | 10.8897 | 15.8345 | 17.8345 | 10.9548 | 21.8445 | 37.6791 | 55.5136 | 0.01
7.3698 | 9.6849 | 9.3698 | 8.3698 | 12.0547 | 14.0547 | 9.6849 | 18.0547 | 30.1095 | 44.1642 | 7.3798 | 9.6949 | 9.3698 | 8.3698 | 12.0547 | 14.0547 | 9.6949 | 18.0647 | 30.1195 | 44.1742 | 0.01
7.1577 | 9.5789 | 9.1577 | 8.1577 | 11.7366 | 13.7366 | 9.5789 | 17.7366 | 29.4732 | 43.2099 | 7.1677 | 9.5889 | 9.1577 | 8.1577 | 11.7366 | 13.7366 | 9.5889 | 17.7466 | 29.4832 | 43.2199 | 0.01
6.2896 | 9.1448 | 8.2896 | 7.2896 | 10.4344 | 12.4344 | 9.1448 | 16.4344 | 26.8688 | 39.3032 | 6.2996 | 9.1548 | 8.2896 | 7.2896 | 10.4344 | 12.4344 | 9.1548 | 16.4444 | 26.8788 | 39.3132 | 0.01
1.4096 | 6.7048 | 3.4096 | 2.4096 | 3.1144 | 5.1144 | 6.7048 | 9.1144 | 12.2288 | 17.3432 | 1.4196 | 6.7148 | 3.4096 | 2.4096 | 3.1144 | 5.1144 | 6.7148 | 9.1244 | 12.2388 | 17.3532 | 0.01
6.2053 | 9.1027 | 8.2053 | 7.2053 | 10.308 | 12.308 | 9.1027 | 16.308 | 26.6159 | 38.9239 | 6.2153 | 9.1127 | 8.2053 | 7.2053 | 10.308 | 12.308 | 9.1127 | 16.318 | 26.6259 | 38.9339 | 0.01
6.5827 | 9.2914 | 8.5827 | 7.5827 | 10.8741 | 12.8741 | 9.2914 | 16.8741 | 27.7482 | 40.6223 | 6.5927 | 9.3014 | 8.5827 | 7.5827 | 10.8741 | 12.8741 | 9.3014 | 16.8841 | 27.7582 | 40.6323 | 0.01
7.7941 | 9.8971 | 9.7941 | 8.7941 | 12.6912 | 14.6912 | 9.8971 | 18.6912 | 31.3824 | 46.0735 | 7.8041 | 9.9071 | 9.7941 | 8.7941 | 12.6912 | 14.6912 | 9.9071 | 18.7012 | 31.3924 | 46.0835 | 0.01
5.123 | 8.5615 | 7.123 | 6.123 | 8.6845 | 10.6845 | 8.5615 | 14.6845 | 23.369 | 34.0534 | 5.133 | 8.5715 | 7.123 | 6.123 | 8.6845 | 10.6845 | 8.5715 | 14.6945 | 23.379 | 34.0634 | 0.01
8.317 | 10.1585 | 10.317 | 9.317 | 13.4755 | 15.4755 | 10.1585 | 19.4755 | 32.951 | 48.4265 | 8.327 | 10.1685 | 10.317 | 9.317 | 13.4755 | 15.4755 | 10.1685 | 19.4855 | 32.961 | 48.4365 | 0.01
4.1843 | 8.0921 | 6.1843 | 5.1843 | 7.2764 | 9.2764 | 8.0921 | 13.2764 | 20.5529 | 29.8293 | 4.1943 | 8.1021 | 6.1843 | 5.1843 | 7.2764 | 9.2764 | 8.1021 | 13.2864 | 20.5629 | 29.8393 | 0.01
5.9492 | 8.9746 | 7.9492 | 6.9492 | 9.9238 | 11.9238 | 8.9746 | 15.9238 | 25.8476 | 37.7714 | 5.9592 | 8.9846 | 7.9492 | 6.9492 | 9.9238 | 11.9238 | 8.9846 | 15.9338 | 25.8576 | 37.7814 | 0.01
4.4054 | 8.2027 | 6.4054 | 5.4054 | 7.6081 | 9.6081 | 8.2027 | 13.6081 | 21.2162 | 30.8244 | 4.4154 | 8.2127 | 6.4054 | 5.4054 | 7.6081 | 9.6081 | 8.2127 | 13.6181 | 21.2262 | 30.8344 | 0.01
8.0854 | 10.0427 | 10.0854 | 9.0854 | 13.1281 | 15.1281 | 10.0427 | 19.1281 | 32.2562 | 47.3843 | 8.0954 | 10.0527 | 10.0854 | 9.0854 | 13.1281 | 15.1281 | 10.0527 | 19.1381 | 32.2662 | 47.3943 | 0.01
5.5091 | 8.7545 | 7.5091 | 6.5091 | 9.2636 | 11.2636 | 8.7545 | 15.2636 | 24.5273 | 35.7909 | 5.5191 | 8.7645 | 7.5091 | 6.5091 | 9.2636 | 11.2636 | 8.7645 | 15.2736 | 24.5373 | 35.8009 | 0.01
3.5418 | 7.7709 | 5.5418 | 4.5418 | 6.3127 | 8.3127 | 7.7709 | 12.3127 | 18.6253 | 26.938 | 3.5518 | 7.7809 | 5.5418 | 4.5418 | 6.3127 | 8.3127 | 7.7809 | 12.3227 | 18.6353 | 26.948 | 0.01
6.5227 | 9.2613 | 8.5227 | 7.5227 | 10.784 | 12.784 | 9.2613 | 16.784 | 27.568 | 40.352 | 6.5327 | 9.2713 | 8.5227 | 7.5227 | 10.784 | 12.784 | 9.2713 | 16.794 | 27.578 | 40.362 | 0.01
9.9449 | 10.9724 | 11.9449 | 10.9449 | 15.9173 | 17.9173 | 10.9724 | 21.9173 | 37.8346 | 55.7519 | 9.9549 | 10.9824 | 11.9449 | 10.9449 | 15.9173 | 17.9173 | 10.9824 | 21.9273 | 37.8446 | 55.7619 | 0.01
8.8786 | 10.4393 | 10.8786 | 9.8786 | 14.3179 | 16.3179 | 10.4393 | 20.3179 | 34.6358 | 50.9537 | 8.8886 | 10.4493 | 10.8786 | 9.8786 | 14.3179 | 16.3179 | 10.4493 | 20.3279 | 34.6458 | 50.9637 | 0.01
8.9064 | 10.4532 | 10.9064 | 9.9064 | 14.3596 | 16.3596 | 10.4532 | 20.3596 | 34.7192 | 51.0788 | 8.9164 | 10.4632 | 10.9064 | 9.9064 | 14.3596 | 16.3596 | 10.4632 | 20.3696 | 34.7292 | 51.0888 | 0.01
6.8865 | 9.4433 | 8.8865 | 7.8865 | 11.3298 | 13.3298 | 9.4433 | 17.3298 | 28.6596 | 41.9895 | 6.8965 | 9.4533 | 8.8865 | 7.8865 | 11.3298 | 13.3298 | 9.4533 | 17.3398 | 28.6696 | 41.9995 | 0.01
3.7029 | 7.8515 | 5.7029 | 4.7029 | 6.5544 | 8.5544 | 7.8515 | 12.5544 | 19.1088 | 27.6632 | 3.7129 | 7.8615 | 5.7029 | 4.7029 | 6.5544 | 8.5544 | 7.8615 | 12.5644 | 19.1188 | 27.6732 | 0.01
4.0389 | 8.0194 | 6.0389 | 5.0389 | 7.0583 | 9.0583 | 8.0194 | 13.0583 | 20.1166 | 29.1749 | 4.0489 | 8.0294 | 6.0389 | 5.0389 | 7.0583 | 9.0583 | 8.0294 | 13.0683 | 20.1266 | 29.1849 | 0.01
4.993 | 8.4965 | 6.993 | 5.993 | 8.4894 | 10.4894 | 8.4965 | 14.4894 | 22.9789 | 33.4683 | 5.003 | 8.5065 | 6.993 | 5.993 | 8.4894 | 10.4894 | 8.5065 | 14.4994 | 22.9889 | 33.4783 | 0.01
7.5727 | 9.7864 | 9.5727 | 8.5727 | 12.3591 | 14.3591 | 9.7864 | 18.3591 | 30.7182 | 45.0774 | 7.5827 | 9.7964 | 9.5727 | 8.5727 | 12.3591 | 14.3591 | 9.7964 | 18.3691 | 30.7282 | 45.0874 | 0.01
6.7339 | 9.367 | 8.7339 | 7.7339 | 11.1009 | 13.1009 | 9.367 | 17.1009 | 28.2018 | 41.3028 | 6.7439 | 9.377 | 8.7339 | 7.7339 | 11.1009 | 13.1009 | 9.377 | 17.1109 | 28.2118 | 41.3128 | 0.01
8.9729 | 10.4864 | 10.9729 | 9.9729 | 14.4593 | 16.4593 | 10.4864 | 20.4593 | 34.9186 | 51.3779 | 8.9829 | 10.4964 | 10.9729 | 9.9729 | 14.4593 | 16.4593 | 10.4964 | 20.4693 | 34.9286 | 51.3879 | 0.01
5.0927 | 8.5463 | 7.0927 | 6.0927 | 8.639 | 10.639 | 8.5463 | 14.639 | 23.278 | 33.917 | 5.1027 | 8.5563 | 7.0927 | 6.0927 | 8.639 | 10.639 | 8.5563 | 14.649 | 23.288 | 33.927 | 0.01
7.9686 | 9.9843 | 9.9686 | 8.9686 | 12.9529 | 14.9529 | 9.9843 | 18.9529 | 31.9059 | 46.8588 | 7.9786 | 9.9943 | 9.9686 | 8.9686 | 12.9529 | 14.9529 | 9.9943 | 18.9629 | 31.9159 | 46.8688 | 0.01
4.0706 | 8.0353 | 6.0706 | 5.0706 | 7.1059 | 9.1059 | 8.0353 | 13.1059 | 20.2119 | 29.3178 | 4.0806 | 8.0453 | 6.0706 | 5.0706 | 7.1059 | 9.1059 | 8.0453 | 13.1159 | 20.2219 | 29.3278 | 0.01
6.7692 | 9.3846 | 8.7692 | 7.7692 | 11.1539 | 13.1539 | 9.3846 | 17.1539 | 28.3077 | 41.4616 | 6.7792 | 9.3946 | 8.7692 | 7.7692 | 11.1539 | 13.1539 | 9.3946 | 17.1639 | 28.3177 | 41.4716 | 0.01
4.3317 | 8.1659 | 6.3317 | 5.3317 | 7.4976 | 9.4976 | 8.1659 | 13.4976 | 20.9952 | 30.4928 | 4.3417 | 8.1759 | 6.3317 | 5.3317 | 7.4976 | 9.4976 | 8.1759 | 13.5076 | 21.0052 | 30.5028 | 0.01
7.3407 | 9.6703 | 9.3407 | 8.3407 | 12.011 | 14.011 | 9.6703 | 18.011 | 30.022 | 44.033 | 7.3507 | 9.6803 | 9.3407 | 8.3407 | 12.011 | 14.011 | 9.6803 | 18.021 | 30.032 | 44.043 | 0.01
2.2761 | 7.138 | 4.2761 | 3.2761 | 4.4141 | 6.4141 | 7.138 | 10.4141 | 14.8282 | 21.2423 | 2.2861 | 7.148 | 4.2761 | 3.2761 | 4.4141 | 6.4141 | 7.148 | 10.4241 | 14.8382 | 21.2523 | 0.01
3.6385 | 7.8193 | 5.6385 | 4.6385 | 6.4578 | 8.4578 | 7.8193 | 12.4578 | 18.9156 | 27.3733 | 3.6485 | 7.8293 | 5.6385 | 4.6385 | 6.4578 | 8.4578 | 7.8293 | 12.4678 | 18.9256 | 27.3833 | 0.01
6.3265 | 9.1632 | 8.3265 | 7.3265 | 10.4897 | 12.4897 | 9.1632 | 16.4897 | 26.9795 | 39.4692 | 6.3365 | 9.1732 | 8.3265 | 7.3265 | 10.4897 | 12.4897 | 9.1732 | 16.4997 | 26.9895 | 39.4792 | 0.01
4.4377 | 8.2189 | 6.4377 | 5.4377 | 7.6566 | 9.6566 | 8.2189 | 13.6566 | 21.3132 | 30.9698 | 4.4477 | 8.2289 | 6.4377 | 5.4377 | 7.6566 | 9.6566 | 8.2289 | 13.6666 | 21.3232 | 30.9798 | 0.01
4.4546 | 8.2273 | 6.4546 | 5.4546 | 7.682 | 9.682 | 8.2273 | 13.682 | 21.3639 | 31.0459 | 4.4646 | 8.2373 | 6.4546 | 5.4546 | 7.682 | 9.682 | 8.2373 | 13.692 | 21.3739 | 31.0559 | 0.01
3.5077 | 7.7539 | 5.5077 | 4.5077 | 6.2616 | 8.2616 | 7.7539 | 12.2616 | 18.5232 | 26.7847 | 3.5177 | 7.7639 | 5.5077 | 4.5077 | 6.2616 | 8.2616 | 7.7639 | 12.2716 | 18.5332 | 26.7947 | 0.01
6.1702 | 9.0851 | 8.1702 | 7.1702 | 10.2553 | 12.2553 | 9.0851 | 16.2553 | 26.5105 | 38.7658 | 6.1802 | 9.0951 | 8.1702 | 7.1702 | 10.2553 | 12.2553 | 9.0951 | 16.2653 | 26.5205 | 38.7758 | 0.01
4.9841 | 8.492 | 6.9841 | 5.9841 | 8.4761 | 10.4761 | 8.492 | 14.4761 | 22.9522 | 33.4283 | 4.9941 | 8.502 | 6.9841 | 5.9841 | 8.4761 | 10.4761 | 8.502 | 14.4861 | 22.9622 | 33.4383 | 0.01
6.0548 | 9.0274 | 8.0548 | 7.0548 | 10.0823 | 12.0823 | 9.0274 | 16.0823 | 26.1645 | 38.2468 | 6.0648 | 9.0374 | 8.0548 | 7.0548 | 10.0823 | 12.0823 | 9.0374 | 16.0923 | 26.1745 | 38.2568 | 0.01
5.0383 | 8.5192 | 7.0383 | 6.0383 | 8.5575 | 10.5575 | 8.5192 | 14.5575 | 23.115 | 33.6725 | 5.0483 | 8.5292 | 7.0383 | 6.0383 | 8.5575 | 10.5575 | 8.5292 | 14.5675 | 23.125 | 33.6825 | 0.01
6.1542 | 9.0771 | 8.1542 | 7.1542 | 10.2313 | 12.2313 | 9.0771 | 16.2313 | 26.4626 | 38.6939 | 6.1642 | 9.0871 | 8.1542 | 7.1542 | 10.2313 | 12.2313 | 9.0871 | 16.2413 | 26.4726 | 38.7039 | 0.01
9.3375 | 10.6687 | 11.3375 | 10.3375 | 15.0062 | 17.0062 | 10.6687 | 21.0062 | 36.0124 | 53.0186 | 9.3475 | 10.6787 | 11.3375 | 10.3375 | 15.0062 | 17.0062 | 10.6787 | 21.0162 | 36.0224 | 53.0286 | 0.01
4.5224 | 8.2612 | 6.5224 | 5.5224 | 7.7836 | 9.7836 | 8.2612 | 13.7836 | 21.5673 | 31.3509 | 4.5324 | 8.2712 | 6.5224 | 5.5224 | 7.7836 | 9.7836 | 8.2712 | 13.7936 | 21.5773 | 31.3609 | 0.01
8.5012 | 10.2506 | 10.5012 | 9.5012 | 13.7518 | 15.7518 | 10.2506 | 19.7518 | 33.5036 | 49.2553 | 8.5112 | 10.2606 | 10.5012 | 9.5012 | 13.7518 | 15.7518 | 10.2606 | 19.7618 | 33.5136 | 49.2653 | 0.01
4.0713 | 8.0357 | 6.0713 | 5.0713 | 7.107 | 9.107 | 8.0357 | 13.107 | 20.214 | 29.321 | 4.0813 | 8.0457 | 6.0713 | 5.0713 | 7.107 | 9.107 | 8.0457 | 13.117 | 20.224 | 29.331 | 0.01
4.0486 | 8.0243 | 6.0486 | 5.0486 | 7.0729 | 9.0729 | 8.0243 | 13.0729 | 20.1458 | 29.2187 | 4.0586 | 8.0343 | 6.0486 | 5.0486 | 7.0729 | 9.0729 | 8.0343 | 13.0829 | 20.1558 | 29.2287 | 0.01
6.1246 | 9.0623 | 8.1246 | 7.1246 | 10.1869 | 12.1869 | 9.0623 | 16.1869 | 26.3738 | 38.5607 | 6.1346 | 9.0723 | 8.1246 | 7.1246 | 10.1869 | 12.1869 | 9.0723 | 16.1969 | 26.3838 | 38.5707 | 0.01
9.4838 | 10.7419 | 11.4838 | 10.4838 | 15.2257 | 17.2257 | 10.7419 | 21.2257 | 36.4514 | 53.6771 | 9.4938 | 10.7519 | 11.4838 | 10.4838 | 15.2257 | 17.2257 | 10.7519 | 21.2357 | 36.4614 | 53.6871 | 0.01
8.4765 | 10.2383 | 10.4765 | 9.4765 | 13.7148 | 15.7148 | 10.2383 | 19.7148 | 33.4295 | 49.1443 | 8.4865 | 10.2483 | 10.4765 | 9.4765 | 13.7148 | 15.7148 | 10.2483 | 19.7248 | 33.4395 | 49.1543 | 0.01
1.5208 | 6.7604 | 3.5208 | 2.5208 | 3.2813 | 5.2813 | 6.7604 | 9.2813 | 12.5625 | 17.8438 | 1.5308 | 6.7704 | 3.5208 | 2.5208 | 3.2813 | 5.2813 | 6.7704 | 9.2913 | 12.5725 | 17.8538 | 0.01
3.2682 | 7.6341 | 5.2682 | 4.2682 | 5.9023 | 7.9023 | 7.6341 | 11.9023 | 17.8045 | 25.7068 | 3.2782 | 7.6441 | 5.2682 | 4.2682 | 5.9023 | 7.9023 | 7.6441 | 11.9123 | 17.8145 | 25.7168 | 0.01
3.7112 | 7.8556 | 5.7112 | 4.7112 | 6.5669 | 8.5669 | 7.8556 | 12.5669 | 19.1337 | 27.7006 | 3.7212 | 7.8656 | 5.7112 | 4.7112 | 6.5669 | 8.5669 | 7.8656 | 12.5769 | 19.1437 | 27.7106 | 0.01
6.4839 | 9.2419 | 8.4839 | 7.4839 | 10.7258 | 12.7258 | 9.2419 | 16.7258 | 27.4517 | 40.1775 | 6.4939 | 9.2519 | 8.4839 | 7.4839 | 10.7258 | 12.7258 | 9.2519 | 16.7358 | 27.4617 | 40.1875 | 0.01
2.484 | 7.242 | 4.484 | 3.484 | 4.726 | 6.726 | 7.242 | 10.726 | 15.452 | 22.178 | 2.494 | 7.252 | 4.484 | 3.484 | 4.726 | 6.726 | 7.252 | 10.736 | 15.462 | 22.188 | 0.01
7.3879 | 9.694 | 9.3879 | 8.3879 | 12.0819 | 14.0819 | 9.694 | 18.0819 | 30.1638 | 44.2457 | 7.3979 | 9.704 | 9.3879 | 8.3879 | 12.0819 | 14.0819 | 9.704 | 18.0919 | 30.1738 | 44.2557 | 0.01
6.4261 | 9.213 | 8.4261 | 7.4261 | 10.6391 | 12.6391 | 9.213 | 16.6391 | 27.2783 | 39.9174 | 6.4361 | 9.223 | 8.4261 | 7.4261 | 10.6391 | 12.6391 | 9.223 | 16.6491 | 27.2883 | 39.9274 | 0.01
4.4858 | 8.2429 | 6.4858 | 5.4858 | 7.7287 | 9.7287 | 8.2429 | 13.7287 | 21.4575 | 31.1862 | 4.4958 | 8.2529 | 6.4858 | 5.4858 | 7.7287 | 9.7287 | 8.2529 | 13.7387 | 21.4675 | 31.1962 | 0.01
3.8099 | 7.9049 | 5.8099 | 4.8099 | 6.7148 | 8.7148 | 7.9049 | 12.7148 | 19.4296 | 28.1444 | 3.8199 | 7.9149 | 5.8099 | 4.8099 | 6.7148 | 8.7148 | 7.9149 | 12.7248 | 19.4396 | 28.1544 | 0.01
4.7977 | 8.3989 | 6.7977 | 5.7977 | 8.1966 | 10.1966 | 8.3989 | 14.1966 | 22.3931 | 32.5897 | 4.8077 | 8.4089 | 6.7977 | 5.7977 | 8.1966 | 10.1966 | 8.4089 | 14.2066 | 22.4031 | 32.5997 | 0.01
8.9975 | 10.4988 | 10.9975 | 9.9975 | 14.4963 | 16.4963 | 10.4988 | 20.4963 | 34.9926 | 51.4888 | 9.0075 | 10.5088 | 10.9975 | 9.9975 | 14.4963 | 16.4963 | 10.5088 | 20.5063 | 35.0026 | 51.4988 | 0.01
5.8481 | 8.9241 | 7.8481 | 6.8481 | 9.7722 | 11.7722 | 8.9241 | 15.7722 | 25.5444 | 37.3167 | 5.8581 | 8.9341 | 7.8481 | 6.8481 | 9.7722 | 11.7722 | 8.9341 | 15.7822 | 25.5544 | 37.3267 | 0.01
8.5415 | 10.2708 | 10.5415 | 9.5415 | 13.8123 | 15.8123 | 10.2708 | 19.8123 | 33.6245 | 49.4368 | 8.5515 | 10.2808 | 10.5415 | 9.5415 | 13.8123 | 15.8123 | 10.2808 | 19.8223 | 33.6345 | 49.4468 | 0.01
4.4601 | 8.2301 | 6.4601 | 5.4601 | 7.6902 | 9.6902 | 8.2301 | 13.6902 | 21.3803 | 31.0705 | 4.4701 | 8.2401 | 6.4601 | 5.4601 | 7.6902 | 9.6902 | 8.2401 | 13.7002 | 21.3903 | 31.0805 | 0.01
7.1335 | 9.5667 | 9.1335 | 8.1335 | 11.7002 | 13.7002 | 9.5667 | 17.7002 | 29.4004 | 43.1005 | 7.1435 | 9.5767 | 9.1335 | 8.1335 | 11.7002 | 13.7002 | 9.5767 | 17.7102 | 29.4104 | 43.1105 | 0.01
5.7056 | 8.8528 | 7.7056 | 6.7056 | 9.5584 | 11.5584 | 8.8528 | 15.5584 | 25.1169 | 36.6753 | 5.7156 | 8.8628 | 7.7056 | 6.7056 | 9.5584 | 11.5584 | 8.8628 | 15.5684 | 25.1269 | 36.6853 | 0.01
3.7183 | 7.8592 | 5.7183 | 4.7183 | 6.5775 | 8.5775 | 7.8592 | 12.5775 | 19.1549 | 27.7324 | 3.7283 | 7.8692 | 5.7183 | 4.7183 | 6.5775 | 8.5775 | 7.8692 | 12.5875 | 19.1649 | 27.7424 | 0.01
8.9759 | 10.488 | 10.9759 | 9.9759 | 14.4639 | 16.4639 | 10.488 | 20.4639 | 34.9278 | 51.3917 | 8.9859 | 10.498 | 10.9759 | 9.9759 | 14.4639 | 16.4639 | 10.498 | 20.4739 | 34.9378 | 51.4017 | 0.01
7.3026 | 9.6513 | 9.3026 | 8.3026 | 11.9539 | 13.9539 | 9.6513 | 17.9539 | 29.9078 | 43.8617 | 7.3126 | 9.6613 | 9.3026 | 8.3026 | 11.9539 | 13.9539 | 9.6613 | 17.9639 | 29.9178 | 43.8717 | 0.01
5.7156 | 8.8578 | 7.7156 | 6.7156 | 9.5734 | 11.5734 | 8.8578 | 15.5734 | 25.1469 | 36.7203 | 5.7256 | 8.8678 | 7.7156 | 6.7156 | 9.5734 | 11.5734 | 8.8678 | 15.5834 | 25.1569 | 36.7303 | 0.01
5.1936 | 8.5968 | 7.1936 | 6.1936 | 8.7903 | 10.7903 | 8.5968 | 14.7903 | 23.5807 | 34.371 | 5.2036 | 8.6068 | 7.1936 | 6.1936 | 8.7903 | 10.7903 | 8.6068 | 14.8003 | 23.5907 | 34.381 | 0.01
5.508 | 8.754 | 7.508 | 6.508 | 9.2621 | 11.2621 | 8.754 | 15.2621 | 24.5241 | 35.7862 | 5.518 | 8.764 | 7.508 | 6.508 | 9.2621 | 11.2621 | 8.764 | 15.2721 | 24.5341 | 35.7962 | 0.01
6.889 | 9.4445 | 8.889 | 7.889 | 11.3335 | 13.3335 | 9.4445 | 17.3335 | 28.6671 | 42.0006 | 6.899 | 9.4545 | 8.889 | 7.889 | 11.3335 | 13.3335 | 9.4545 | 17.3435 | 28.6771 | 42.0106 | 0.01
6.8062 | 9.4031 | 8.8062 | 7.8062 | 11.2094 | 13.2094 | 9.4031 | 17.2094 | 28.4187 | 41.6281 | 6.8162 | 9.4131 | 8.8062 | 7.8062 | 11.2094 | 13.2094 | 9.4131 | 17.2194 | 28.4287 | 41.6381 | 0.01
0.67283 | 6.3364 | 2.6728 | 1.6728 | 2.0093 | 4.0093 | 6.3364 | 8.0093 | 10.0185 | 14.0278 | 0.68283 | 6.3464 | 2.6728 | 1.6728 | 2.0093 | 4.0093 | 6.3464 | 8.0193 | 10.0285 | 14.0378 | 0.01
9.912 | 10.956 | 11.912 | 10.912 | 15.868 | 17.868 | 10.956 | 21.868 | 37.7361 | 55.6041 | 9.922 | 10.966 | 11.912 | 10.912 | 15.868 | 17.868 | 10.966 | 21.878 | 37.7461 | 55.6141 | 0.01
8.8986 | 10.4493 | 10.8986 | 9.8986 | 14.3479 | 16.3479 | 10.4493 | 20.3479 | 34.6958 | 51.0438 | 8.9086 | 10.4593 | 10.8986 | 9.8986 | 14.3479 | 16.3479 | 10.4593 | 20.3579 | 34.7058 | 51.0538 | 0.01
6.3234 | 9.1617 | 8.3234 | 7.3234 | 10.4851 | 12.4851 | 9.1617 | 16.4851 | 26.9703 | 39.4554 | 6.3334 | 9.1717 | 8.3234 | 7.3234 | 10.4851 | 12.4851 | 9.1717 | 16.4951 | 26.9803 | 39.4654 | 0.01
3.0784 | 7.5392 | 5.0784 | 4.0784 | 5.6175 | 7.6175 | 7.5392 | 11.6175 | 17.2351 | 24.8526 | 3.0884 | 7.5492 | 5.0784 | 4.0784 | 5.6175 | 7.6175 | 7.5492 | 11.6275 | 17.2451 | 24.8626 | 0.01
6.7898 | 9.3949 | 8.7898 | 7.7898 | 11.1847 | 13.1847 | 9.3949 | 17.1847 | 28.3695 | 41.5542 | 6.7998 | 9.4049 | 8.7898 | 7.7898 | 11.1847 | 13.1847 | 9.4049 | 17.1947 | 28.3795 | 41.5642 | 0.01
4.1042 | 8.0521 | 6.1042 | 5.1042 | 7.1563 | 9.1563 | 8.0521 | 13.1563 | 20.3126 | 29.4689 | 4.1142 | 8.0621 | 6.1042 | 5.1042 | 7.1563 | 9.1563 | 8.0621 | 13.1663 | 20.3226 | 29.4789 | 0.01
8.6722 | 10.3361 | 10.6722 | 9.6722 | 14.0083 | 16.0083 | 10.3361 | 20.0083 | 34.0166 | 50.0248 | 8.6822 | 10.3461 | 10.6722 | 9.6722 | 14.0083 | 16.0083 | 10.3461 | 20.0183 | 34.0266 | 50.0348 | 0.01
6.5228 | 9.2614 | 8.5228 | 7.5228 | 10.7842 | 12.7842 | 9.2614 | 16.7842 | 27.5685 | 40.3527 | 6.5328 | 9.2714 | 8.5228 | 7.5228 | 10.7842 | 12.7842 | 9.2714 | 16.7942 | 27.5785 | 40.3627 | 0.01
5.9937 | 8.9968 | 7.9937 | 6.9937 | 9.9905 | 11.9905 | 8.9968 | 15.9905 | 25.9811 | 37.9716 | 6.0037 | 9.0068 | 7.9937 | 6.9937 | 9.9905 | 11.9905 | 9.0068 | 16.0005 | 25.9911 | 37.9816 | 0.01
5.1327 | 8.5664 | 7.1327 | 6.1327 | 8.6991 | 10.6991 | 8.5664 | 14.6991 | 23.3981 | 34.0972 | 5.1427 | 8.5764 | 7.1327 | 6.1327 | 8.6991 | 10.6991 | 8.5764 | 14.7091 | 23.4081 | 34.1072 | 0.01
6.0972 | 9.0486 | 8.0972 | 7.0972 | 10.1458 | 12.1458 | 9.0486 | 16.1458 | 26.2917 | 38.4375 | 6.1072 | 9.0586 | 8.0972 | 7.0972 | 10.1458 | 12.1458 | 9.0586 | 16.1558 | 26.3017 | 38.4475 | 0.01
5.1872 | 8.5936 | 7.1872 | 6.1872 | 8.7809 | 10.7809 | 8.5936 | 14.7809 | 23.5617 | 34.3426 | 5.1972 | 8.6036 | 7.1872 | 6.1872 | 8.7809 | 10.7809 | 8.6036 | 14.7909 | 23.5717 | 34.3526 | 0.01
8.4996 | 10.2498 | 10.4996 | 9.4996 | 13.7494 | 15.7494 | 10.2498 | 19.7494 | 33.4989 | 49.2483 | 8.5096 | 10.2598 | 10.4996 | 9.4996 | 13.7494 | 15.7494 | 10.2598 | 19.7594 | 33.5089 | 49.2583 | 0.01
7.4639 | 9.732 | 9.4639 | 8.4639 | 12.1959 | 14.1959 | 9.732 | 18.1959 | 30.3918 | 44.5877 | 7.4739 | 9.742 | 9.4639 | 8.4639 | 12.1959 | 14.1959 | 9.742 | 18.2059 | 30.4018 | 44.5977 | 0.01
4.3516 | 8.1758 | 6.3516 | 5.3516 | 7.5274 | 9.5274 | 8.1758 | 13.5274 | 21.0548 | 30.5822 | 4.3616 | 8.1858 | 6.3516 | 5.3516 | 7.5274 | 9.5274 | 8.1858 | 13.5374 | 21.0648 | 30.5922 | 0.01
9.4009 | 10.7004 | 11.4009 | 10.4009 | 15.1013 | 17.1013 | 10.7004 | 21.1013 | 36.2026 | 53.3038 | 9.4109 | 10.7104 | 11.4009 | 10.4009 | 15.1013 | 17.1013 | 10.7104 | 21.1113 | 36.2126 | 53.3138 | 0.01
6.8435 | 9.4217 | 8.8435 | 7.8435 | 11.2652 | 13.2652 | 9.4217 | 17.2652 | 28.5304 | 41.7956 | 6.8535 | 9.4317 | 8.8435 | 7.8435 | 11.2652 | 13.2652 | 9.4317 | 17.2752 | 28.5404 | 41.8056 | 0.01
6.4462 | 9.2231 | 8.4462 | 7.4462 | 10.6693 | 12.6693 | 9.2231 | 16.6693 | 27.3385 | 40.0078 | 6.4562 | 9.2331 | 8.4462 | 7.4462 | 10.6693 | 12.6693 | 9.2331 | 16.6793 | 27.3485 | 40.0178 | 0.01
0.20077 | 6.1004 | 2.2008 | 1.2008 | 1.3012 | 3.3012 | 6.1004 | 7.3012 | 8.6023 | 11.9035 | 0.21077 | 6.1104 | 2.2008 | 1.2008 | 1.3012 | 3.3012 | 6.1104 | 7.3112 | 8.6123 | 11.9135 | 0.01
5.4665 | 8.7332 | 7.4665 | 6.4665 | 9.1997 | 11.1997 | 8.7332 | 15.1997 | 24.3995 | 35.5992 | 5.4765 | 8.7432 | 7.4665 | 6.4665 | 9.1997 | 11.1997 | 8.7432 | 15.2097 | 24.4095 | 35.6092 | 0.01
8.8034 | 10.4017 | 10.8034 | 9.8034 | 14.2052 | 16.2052 | 10.4017 | 20.2052 | 34.4103 | 50.6155 | 8.8134 | 10.4117 | 10.8034 | 9.8034 | 14.2052 | 16.2052 | 10.4117 | 20.2152 | 34.4203 | 50.6255 | 0.01
2.3695 | 7.1848 | 4.3695 | 3.3695 | 4.5543 | 6.5543 | 7.1848 | 10.5543 | 15.1086 | 21.6629 | 2.3795 | 7.1948 | 4.3695 | 3.3695 | 4.5543 | 6.5543 | 7.1948 | 10.5643 | 15.1186 | 21.6729 | 0.01
9.0481 | 10.524 | 11.0481 | 10.0481 | 14.5721 | 16.5721 | 10.524 | 20.5721 | 35.1442 | 51.7163 | 9.0581 | 10.534 | 11.0481 | 10.0481 | 14.5721 | 16.5721 | 10.534 | 20.5821 | 35.1542 | 51.7263 | 0.01
6.2675 | 9.1337 | 8.2675 | 7.2675 | 10.4012 | 12.4012 | 9.1337 | 16.4012 | 26.8025 | 39.2037 | 6.2775 | 9.1437 | 8.2675 | 7.2675 | 10.4012 | 12.4012 | 9.1437 | 16.4112 | 26.8125 | 39.2137 | 0.01
6.5188 | 9.2594 | 8.5188 | 7.5188 | 10.7782 | 12.7782 | 9.2594 | 16.7782 | 27.5565 | 40.3347 | 6.5288 | 9.2694 | 8.5188 | 7.5188 | 10.7782 | 12.7782 | 9.2694 | 16.7882 | 27.5665 | 40.3447 | 0.01
6.3693 | 9.1846 | 8.3693 | 7.3693 | 10.5539 | 12.5539 | 9.1846 | 16.5539 | 27.1078 | 39.6617 | 6.3793 | 9.1946 | 8.3693 | 7.3693 | 10.5539 | 12.5539 | 9.1946 | 16.5639 | 27.1178 | 39.6717 | 0.01
5.8291 | 8.9145 | 7.8291 | 6.8291 | 9.7436 | 11.7436 | 8.9145 | 15.7436 | 25.4872 | 37.2308 | 5.8391 | 8.9245 | 7.8291 | 6.8291 | 9.7436 | 11.7436 | 8.9245 | 15.7536 | 25.4972 | 37.2408 | 0.01
3.9307 | 7.9653 | 5.9307 | 4.9307 | 6.896 | 8.896 | 7.9653 | 12.896 | 19.792 | 28.688 | 3.9407 | 7.9753 | 5.9307 | 4.9307 | 6.896 | 8.896 | 7.9753 | 12.906 | 19.802 | 28.698 | 0.01
9.8395 | 10.9198 | 11.8395 | 10.8395 | 15.7593 | 17.7593 | 10.9198 | 21.7593 | 37.5186 | 55.2779 | 9.8495 | 10.9298 | 11.8395 | 10.8395 | 15.7593 | 17.7593 | 10.9298 | 21.7693 | 37.5286 | 55.2879 | 0.01
7.369 | 9.6845 | 9.369 | 8.369 | 12.0536 | 14.0536 | 9.6845 | 18.0536 | 30.1071 | 44.1607 | 7.379 | 9.6945 | 9.369 | 8.369 | 12.0536 | 14.0536 | 9.6945 | 18.0636 | 30.1171 | 44.1707 | 0.01
6.8523 | 9.4261 | 8.8523 | 7.8523 | 11.2784 | 13.2784 | 9.4261 | 17.2784 | 28.5568 | 41.8351 | 6.8623 | 9.4361 | 8.8523 | 7.8523 | 11.2784 | 13.2784 | 9.4361 | 17.2884 | 28.5668 | 41.8451 | 0.01
6.0793 | 9.0396 | 8.0793 | 7.0793 | 10.1189 | 12.1189 | 9.0396 | 16.1189 | 26.2378 | 38.3567 | 6.0893 | 9.0496 | 8.0793 | 7.0793 | 10.1189 | 12.1189 | 9.0496 | 16.1289 | 26.2478 | 38.3667 | 0.01
3.9433 | 7.9717 | 5.9433 | 4.9433 | 6.915 | 8.915 | 7.9717 | 12.915 | 19.83 | 28.745 | 3.9533 | 7.9817 | 5.9433 | 4.9433 | 6.915 | 8.915 | 7.9817 | 12.925 | 19.84 | 28.755 | 0.01
8.7022 | 10.3511 | 10.7022 | 9.7022 | 14.0532 | 16.0532 | 10.3511 | 20.0532 | 34.1065 | 50.1597 | 8.7122 | 10.3611 | 10.7022 | 9.7022 | 14.0532 | 16.0532 | 10.3611 | 20.0632 | 34.1165 | 50.1697 | 0.01
5.2855 | 8.6427 | 7.2855 | 6.2855 | 8.9282 | 10.9282 | 8.6427 | 14.9282 | 23.8564 | 34.7846 | 5.2955 | 8.6527 | 7.2855 | 6.2855 | 8.9282 | 10.9282 | 8.6527 | 14.9382 | 23.8664 | 34.7946 | 0.01
2.6873 | 7.3437 | 4.6873 | 3.6873 | 5.031 | 7.031 | 7.3437 | 11.031 | 16.062 | 23.093 | 2.6973 | 7.3537 | 4.6873 | 3.6873 | 5.031 | 7.031 | 7.3537 | 11.041 | 16.072 | 23.103 | 0.01
6.6904 | 9.3452 | 8.6904 | 7.6904 | 11.0357 | 13.0357 | 9.3452 | 17.0357 | 28.0713 | 41.107 | 6.7004 | 9.3552 | 8.6904 | 7.6904 | 11.0357 | 13.0357 | 9.3552 | 17.0457 | 28.0813 | 41.117 | 0.01
2.8821 | 7.4411 | 4.8821 | 3.8821 | 5.3232 | 7.3232 | 7.4411 | 11.3232 | 16.6463 | 23.9695 | 2.8921 | 7.4511 | 4.8821 | 3.8821 | 5.3232 | 7.3232 | 7.4511 | 11.3332 | 16.6563 | 23.9795 | 0.01
3.2924 | 7.6462 | 5.2924 | 4.2924 | 5.9386 | 7.9386 | 7.6462 | 11.9386 | 17.8772 | 25.8158 | 3.3024 | 7.6562 | 5.2924 | 4.2924 | 5.9386 | 7.9386 | 7.6562 | 11.9486 | 17.8872 | 25.8258 | 0.01
5.1488 | 8.5744 | 7.1488 | 6.1488 | 8.7232 | 10.7232 | 8.5744 | 14.7232 | 23.4464 | 34.1696 | 5.1588 | 8.5844 | 7.1488 | 6.1488 | 8.7232 | 10.7232 | 8.5844 | 14.7332 | 23.4564 | 34.1796 | 0.01
7.2469 | 9.6234 | 9.2469 | 8.2469 | 11.8703 | 13.8703 | 9.6234 | 17.8703 | 29.7406 | 43.6109 | 7.2569 | 9.6334 | 9.2469 | 8.2469 | 11.8703 | 13.8703 | 9.6334 | 17.8803 | 29.7506 | 43.6209 | 0.01
8.7803 | 10.3902 | 10.7803 | 9.7803 | 14.1705 | 16.1705 | 10.3902 | 20.1705 | 34.3409 | 50.5114 | 8.7903 | 10.4002 | 10.7803 | 9.7803 | 14.1705 | 16.1705 | 10.4002 | 20.1805 | 34.3509 | 50.5214 | 0.01
7.4934 | 9.7467 | 9.4934 | 8.4934 | 12.24 | 14.24 | 9.7467 | 18.24 | 30.4801 | 44.7201 | 7.5034 | 9.7567 | 9.4934 | 8.4934 | 12.24 | 14.24 | 9.7567 | 18.25 | 30.4901 | 44.7301 | 0.01
4.6474 | 8.3237 | 6.6474 | 5.6474 | 7.9711 | 9.9711 | 8.3237 | 13.9711 | 21.9422 | 31.9133 | 4.6574 | 8.3337 | 6.6474 | 5.6474 | 7.9711 | 9.9711 | 8.3337 | 13.9811 | 21.9522 | 31.9233 | 0.01
2.825 | 7.4125 | 4.825 | 3.825 | 5.2375 | 7.2375 | 7.4125 | 11.2375 | 16.4749 | 23.7124 | 2.835 | 7.4225 | 4.825 | 3.825 | 5.2375 | 7.2375 | 7.4225 | 11.2475 | 16.4849 | 23.7224 | 0.01
6.1314 | 9.0657 | 8.1314 | 7.1314 | 10.1971 | 12.1971 | 9.0657 | 16.1971 | 26.3941 | 38.5912 | 6.1414 | 9.0757 | 8.1314 | 7.1314 | 10.1971 | 12.1971 | 9.0757 | 16.2071 | 26.4041 | 38.6012 | 0.01
6.7276 | 9.3638 | 8.7276 | 7.7276 | 11.0913 | 13.0913 | 9.3638 | 17.0913 | 28.1827 | 41.274 | 6.7376 | 9.3738 | 8.7276 | 7.7276 | 11.0913 | 13.0913 | 9.3738 | 17.1013 | 28.1927 | 41.284 | 0.01
8.4751 | 10.2376 | 10.4751 | 9.4751 | 13.7127 | 15.7127 | 10.2376 | 19.7127 | 33.4254 | 49.1381 | 8.4851 | 10.2476 | 10.4751 | 9.4751 | 13.7127 | 15.7127 | 10.2476 | 19.7227 | 33.4354 | 49.1481 | 0.01
8.2603 | 10.1302 | 10.2603 | 9.2603 | 13.3905 | 15.3905 | 10.1302 | 19.3905 | 32.781 | 48.1714 | 8.2703 | 10.1402 | 10.2603 | 9.2603 | 13.3905 | 15.3905 | 10.1402 | 19.4005 | 32.791 | 48.1814 | 0.01
5.7733 | 8.8867 | 7.7733 | 6.7733 | 9.66 | 11.66 | 8.8867 | 15.66 | 25.32 | 36.9799 | 5.7833 | 8.8967 | 7.7733 | 6.7733 | 9.66 | 11.66 | 8.8967 | 15.67 | 25.33 | 36.9899 | 0.01
4.1212 | 8.0606 | 6.1212 | 5.1212 | 7.1818 | 9.1818 | 8.0606 | 13.1818 | 20.3636 | 29.5453 | 4.1312 | 8.0706 | 6.1212 | 5.1212 | 7.1818 | 9.1818 | 8.0706 | 13.1918 | 20.3736 | 29.5553 | 0.01
5.4958 | 8.7479 | 7.4958 | 6.4958 | 9.2437 | 11.2437 | 8.7479 | 15.2437 | 24.4875 | 35.7312 | 5.5058 | 8.7579 | 7.4958 | 6.4958 | 9.2437 | 11.2437 | 8.7579 | 15.2537 | 24.4975 | 35.7412 | 0.01
9.4378 | 10.7189 | 11.4378 | 10.4378 | 15.1567 | 17.1567 | 10.7189 | 21.1567 | 36.3134 | 53.4701 | 9.4478 | 10.7289 | 11.4378 | 10.4378 | 15.1567 | 17.1567 | 10.7289 | 21.1667 | 36.3234 | 53.4801 | 0.01
5.4164 | 8.7082 | 7.4164 | 6.4164 | 9.1246 | 11.1246 | 8.7082 | 15.1246 | 24.2492 | 35.3737 | 5.4264 | 8.7182 | 7.4164 | 6.4164 | 9.1246 | 11.1246 | 8.7182 | 15.1346 | 24.2592 | 35.3837 | 0.01
5.2546 | 8.6273 | 7.2546 | 6.2546 | 8.8819 | 10.8819 | 8.6273 | 14.8819 | 23.7637 | 34.6456 | 5.2646 | 8.6373 | 7.2546 | 6.2546 | 8.8819 | 10.8819 | 8.6373 | 14.8919 | 23.7737 | 34.6556 | 0.01
3.5047 | 7.7524 | 5.5047 | 4.5047 | 6.2571 | 8.2571 | 7.7524 | 12.2571 | 18.5141 | 26.7712 | 3.5147 | 7.7624 | 5.5047 | 4.5047 | 6.2571 | 8.2571 | 7.7624 | 12.2671 | 18.5241 | 26.7812 | 0.01
8.3734 | 10.1867 | 10.3734 | 9.3734 | 13.5601 | 15.5601 | 10.1867 | 19.5601 | 33.1201 | 48.6802 | 8.3834 | 10.1967 | 10.3734 | 9.3734 | 13.5601 | 15.5601 | 10.1967 | 19.5701 | 33.1301 | 48.6902 | 0.01
4.4282 | 8.2141 | 6.4282 | 5.4282 | 7.6423 | 9.6423 | 8.2141 | 13.6423 | 21.2847 | 30.927 | 4.4382 | 8.2241 | 6.4282 | 5.4282 | 7.6423 | 9.6423 | 8.2241 | 13.6523 | 21.2947 | 30.937 | 0.01
7.3775 | 9.6887 | 9.3775 | 8.3775 | 12.0662 | 14.0662 | 9.6887 | 18.0662 | 30.1324 | 44.1986 | 7.3875 | 9.6987 | 9.3775 | 8.3775 | 12.0662 | 14.0662 | 9.6987 | 18.0762 | 30.1424 | 44.2086 | 0.01
10.3593 | 11.1797 | 12.3593 | 11.3593 | 16.539 | 18.539 | 11.1797 | 22.539 | 39.078 | 57.6169 | 10.3693 | 11.1897 | 12.3593 | 11.3593 | 16.539 | 18.539 | 11.1897 | 22.549 | 39.088 | 57.6269 | 0.01
8.8301 | 10.4151 | 10.8301 | 9.8301 | 14.2452 | 16.2452 | 10.4151 | 20.2452 | 34.4903 | 50.7355 | 8.8401 | 10.4251 | 10.8301 | 9.8301 | 14.2452 | 16.2452 | 10.4251 | 20.2552 | 34.5003 | 50.7455 | 0.01
4.4346 | 8.2173 | 6.4346 | 5.4346 | 7.6519 | 9.6519 | 8.2173 | 13.6519 | 21.3037 | 30.9556 | 4.4446 | 8.2273 | 6.4346 | 5.4346 | 7.6519 | 9.6519 | 8.2273 | 13.6619 | 21.3137 | 30.9656 | 0.01
5.5114 | 8.7557 | 7.5114 | 6.5114 | 9.2671 | 11.2671 | 8.7557 | 15.2671 | 24.5343 | 35.8014 | 5.5214 | 8.7657 | 7.5114 | 6.5114 | 9.2671 | 11.2671 | 8.7657 | 15.2771 | 24.5443 | 35.8114 | 0.01
6.9724 | 9.4862 | 8.9724 | 7.9724 | 11.4586 | 13.4586 | 9.4862 | 17.4586 | 28.9171 | 42.3757 | 6.9824 | 9.4962 | 8.9724 | 7.9724 | 11.4586 | 13.4586 | 9.4962 | 17.4686 | 28.9271 | 42.3857 | 0.01
5.4232 | 8.7116 | 7.4232 | 6.4232 | 9.1348 | 11.1348 | 8.7116 | 15.1348 | 24.2696 | 35.4044 | 5.4332 | 8.7216 | 7.4232 | 6.4232 | 9.1348 | 11.1348 | 8.7216 | 15.1448 | 24.2796 | 35.4144 | 0.01
4.6256 | 8.3128 | 6.6256 | 5.6256 | 7.9384 | 9.9384 | 8.3128 | 13.9384 | 21.8769 | 31.8153 | 4.6356 | 8.3228 | 6.6256 | 5.6256 | 7.9384 | 9.9384 | 8.3228 | 13.9484 | 21.8869 | 31.8253 | 0.01
4.4256 | 8.2128 | 6.4256 | 5.4256 | 7.6385 | 9.6385 | 8.2128 | 13.6385 | 21.2769 | 30.9154 | 4.4356 | 8.2228 | 6.4256 | 5.4256 | 7.6385 | 9.6385 | 8.2228 | 13.6485 | 21.2869 | 30.9254 | 0.01
5.4764 | 8.7382 | 7.4764 | 6.4764 | 9.2147 | 11.2147 | 8.7382 | 15.2147 | 24.4293 | 35.644 | 5.4864 | 8.7482 | 7.4764 | 6.4764 | 9.2147 | 11.2147 | 8.7482 | 15.2247 | 24.4393 | 35.654 | 0.01
3.7625 | 7.8812 | 5.7625 | 4.7625 | 6.6437 | 8.6437 | 7.8812 | 12.6437 | 19.2875 | 27.9312 | 3.7725 | 7.8912 | 5.7625 | 4.7625 | 6.6437 | 8.6437 | 7.8912 | 12.6537 | 19.2975 | 27.9412 | 0.01
4.1874 | 8.0937 | 6.1874 | 5.1874 | 7.281 | 9.281 | 8.0937 | 13.281 | 20.5621 | 29.8431 | 4.1974 | 8.1037 | 6.1874 | 5.1874 | 7.281 | 9.281 | 8.1037 | 13.291 | 20.5721 | 29.8531 | 0.01
5.0846 | 8.5423 | 7.0846 | 6.0846 | 8.6269 | 10.6269 | 8.5423 | 14.6269 | 23.2537 | 33.8806 | 5.0946 | 8.5523 | 7.0846 | 6.0846 | 8.6269 | 10.6269 | 8.5523 | 14.6369 | 23.2637 | 33.8906 | 0.01
5.5213 | 8.7607 | 7.5213 | 6.5213 | 9.282 | 11.282 | 8.7607 | 15.282 | 24.564 | 35.846 | 5.5313 | 8.7707 | 7.5213 | 6.5213 | 9.282 | 11.282 | 8.7707 | 15.292 | 24.574 | 35.856 | 0.01
9.8412 | 10.9206 | 11.8412 | 10.8412 | 15.7618 | 17.7618 | 10.9206 | 21.7618 | 37.5236 | 55.2855 | 9.8512 | 10.9306 | 11.8412 | 10.8412 | 15.7618 | 17.7618 | 10.9306 | 21.7718 | 37.5336 | 55.2955 | 0.01
6.7464 | 9.3732 | 8.7464 | 7.7464 | 11.1195 | 13.1195 | 9.3732 | 17.1195 | 28.2391 | 41.3586 | 6.7564 | 9.3832 | 8.7464 | 7.7464 | 11.1195 | 13.1195 | 9.3832 | 17.1295 | 28.2491 | 41.3686 | 0.01
7.7882 | 9.8941 | 9.7882 | 8.7882 | 12.6823 | 14.6823 | 9.8941 | 18.6823 | 31.3647 | 46.047 | 7.7982 | 9.9041 | 9.7882 | 8.7882 | 12.6823 | 14.6823 | 9.9041 | 18.6923 | 31.3747 | 46.057 | 0.01
3.4484 | 7.7242 | 5.4484 | 4.4484 | 6.1726 | 8.1726 | 7.7242 | 12.1726 | 18.3451 | 26.5177 | 3.4584 | 7.7342 | 5.4484 | 4.4484 | 6.1726 | 8.1726 | 7.7342 | 12.1826 | 18.3551 | 26.5277 | 0.01
6.9806 | 9.4903 | 8.9806 | 7.9806 | 11.4709 | 13.4709 | 9.4903 | 17.4709 | 28.9418 | 42.4126 | 6.9906 | 9.5003 | 8.9806 | 7.9806 | 11.4709 | 13.4709 | 9.5003 | 17.4809 | 28.9518 | 42.4226 | 0.01
7.952 | 9.976 | 9.952 | 8.952 | 12.928 | 14.928 | 9.976 | 18.928 | 31.8561 | 46.7841 | 7.962 | 9.986 | 9.952 | 8.952 | 12.928 | 14.928 | 9.986 | 18.938 | 31.8661 | 46.7941 | 0.01
7.4983 | 9.7492 | 9.4983 | 8.4983 | 12.2475 | 14.2475 | 9.7492 | 18.2475 | 30.4949 | 44.7424 | 7.5083 | 9.7592 | 9.4983 | 8.4983 | 12.2475 | 14.2475 | 9.7592 | 18.2575 | 30.5049 | 44.7524 | 0.01
7.6387 | 9.8193 | 9.6387 | 8.6387 | 12.458 | 14.458 | 9.8193 | 18.458 | 30.916 | 45.3739 | 7.6487 | 9.8293 | 9.6387 | 8.6387 | 12.458 | 14.458 | 9.8293 | 18.468 | 30.926 | 45.3839 | 0.01
7.1471 | 9.5736 | 9.1471 | 8.1471 | 11.7207 | 13.7207 | 9.5736 | 17.7207 | 29.4413 | 43.162 | 7.1571 | 9.5836 | 9.1471 | 8.1471 | 11.7207 | 13.7207 | 9.5836 | 17.7307 | 29.4513 | 43.172 | 0.01
5.2826 | 8.6413 | 7.2826 | 6.2826 | 8.924 | 10.924 | 8.6413 | 14.924 | 23.8479 | 34.7719 | 5.2926 | 8.6513 | 7.2826 | 6.2826 | 8.924 | 10.924 | 8.6513 | 14.934 | 23.8579 | 34.7819 | 0.01
4.0416 | 8.0208 | 6.0416 | 5.0416 | 7.0624 | 9.0624 | 8.0208 | 13.0624 | 20.1247 | 29.1871 | 4.0516 | 8.0308 | 6.0416 | 5.0416 | 7.0624 | 9.0624 | 8.0308 | 13.0724 | 20.1347 | 29.1971 | 0.01
9.1275 | 10.5638 | 11.1275 | 10.1275 | 14.6913 | 16.6913 | 10.5638 | 20.6913 | 35.3826 | 52.0739 | 9.1375 | 10.5738 | 11.1275 | 10.1275 | 14.6913 | 16.6913 | 10.5738 | 20.7013 | 35.3926 | 52.0839 | 0.01
5.8582 | 8.9291 | 7.8582 | 6.8582 | 9.7873 | 11.7873 | 8.9291 | 15.7873 | 25.5747 | 37.362 | 5.8682 | 8.9391 | 7.8582 | 6.8582 | 9.7873 | 11.7873 | 8.9391 | 15.7973 | 25.5847 | 37.372 | 0.01
6.5105 | 9.2552 | 8.5105 | 7.5105 | 10.7657 | 12.7657 | 9.2552 | 16.7657 | 27.5314 | 40.2971 | 6.5205 | 9.2652 | 8.5105 | 7.5105 | 10.7657 | 12.7657 | 9.2652 | 16.7757 | 27.5414 | 40.3071 | 0.01
5.8845 | 8.9423 | 7.8845 | 6.8845 | 9.8268 | 11.8268 | 8.9423 | 15.8268 | 25.6536 | 37.4804 | 5.8945 | 8.9523 | 7.8845 | 6.8845 | 9.8268 | 11.8268 | 8.9523 | 15.8368 | 25.6636 | 37.4904 | 0.01
6.6335 | 9.3167 | 8.6335 | 7.6335 | 10.9502 | 12.9502 | 9.3167 | 16.9502 | 27.9005 | 40.8507 | 6.6435 | 9.3267 | 8.6335 | 7.6335 | 10.9502 | 12.9502 | 9.3267 | 16.9602 | 27.9105 | 40.8607 | 0.01
4.9168 | 8.4584 | 6.9168 | 5.9168 | 8.3752 | 10.3752 | 8.4584 | 14.3752 | 22.7503 | 33.1255 | 4.9268 | 8.4684 | 6.9168 | 5.9168 | 8.3752 | 10.3752 | 8.4684 | 14.3852 | 22.7603 | 33.1355 | 0.01
9.3304 | 10.6652 | 11.3304 | 10.3304 | 14.9956 | 16.9956 | 10.6652 | 20.9956 | 35.9912 | 52.9869 | 9.3404 | 10.6752 | 11.3304 | 10.3304 | 14.9956 | 16.9956 | 10.6752 | 21.0056 | 36.0012 | 52.9969 | 0.01
5.1914 | 8.5957 | 7.1914 | 6.1914 | 8.7871 | 10.7871 | 8.5957 | 14.7871 | 23.5741 | 34.3612 | 5.2014 | 8.6057 | 7.1914 | 6.1914 | 8.7871 | 10.7871 | 8.6057 | 14.7971 | 23.5841 | 34.3712 | 0.01
6.7387 | 9.3693 | 8.7387 | 7.7387 | 11.108 | 13.108 | 9.3693 | 17.108 | 28.2161 | 41.3241 | 6.7487 | 9.3793 | 8.7387 | 7.7387 | 11.108 | 13.108 | 9.3793 | 17.118 | 28.2261 | 41.3341 | 0.01
7.8434 | 9.9217 | 9.8434 | 8.8434 | 12.7652 | 14.7652 | 9.9217 | 18.7652 | 31.5303 | 46.2955 | 7.8534 | 9.9317 | 9.8434 | 8.8434 | 12.7652 | 14.7652 | 9.9317 | 18.7752 | 31.5403 | 46.3055 | 0.01
7.0532 | 9.5266 | 9.0532 | 8.0532 | 11.5799 | 13.5799 | 9.5266 | 17.5799 | 29.1597 | 42.7396 | 7.0632 | 9.5366 | 9.0532 | 8.0532 | 11.5799 | 13.5799 | 9.5366 | 17.5899 | 29.1697 | 42.7496 | 0.01
8.328 | 10.164 | 10.328 | 9.328 | 13.492 | 15.492 | 10.164 | 19.492 | 32.984 | 48.476 | 8.338 | 10.174 | 10.328 | 9.328 | 13.492 | 15.492 | 10.174 | 19.502 | 32.994 | 48.486 | 0.01
10.2615 | 11.1307 | 12.2615 | 11.2615 | 16.3922 | 18.3922 | 11.1307 | 22.3922 | 38.7844 | 57.1766 | 10.2715 | 11.1407 | 12.2615 | 11.2615 | 16.3922 | 18.3922 | 11.1407 | 22.4022 | 38.7944 | 57.1866 | 0.01
7.3095 | 9.6548 | 9.3095 | 8.3095 | 11.9643 | 13.9643 | 9.6548 | 17.9643 | 29.9286 | 43.893 | 7.3195 | 9.6648 | 9.3095 | 8.3095 | 11.9643 | 13.9643 | 9.6648 | 17.9743 | 29.9386 | 43.903 | 0.01
4.6952 | 8.3476 | 6.6952 | 5.6952 | 8.0428 | 10.0428 | 8.3476 | 14.0428 | 22.0856 | 32.1284 | 4.7052 | 8.3576 | 6.6952 | 5.6952 | 8.0428 | 10.0428 | 8.3576 | 14.0528 | 22.0956 | 32.1384 | 0.01
6.5708 | 9.2854 | 8.5708 | 7.5708 | 10.8562 | 12.8562 | 9.2854 | 16.8562 | 27.7123 | 40.5685 | 6.5808 | 9.2954 | 8.5708 | 7.5708 | 10.8562 | 12.8562 | 9.2954 | 16.8662 | 27.7223 | 40.5785 | 0.01
5.4473 | 8.7236 | 7.4473 | 6.4473 | 9.1709 | 11.1709 | 8.7236 | 15.1709 | 24.3418 | 35.5127 | 5.4573 | 8.7336 | 7.4473 | 6.4473 | 9.1709 | 11.1709 | 8.7336 | 15.1809 | 24.3518 | 35.5227 | 0.01
7.6753 | 9.8377 | 9.6753 | 8.6753 | 12.513 | 14.513 | 9.8377 | 18.513 | 31.026 | 45.539 | 7.6853 | 9.8477 | 9.6753 | 8.6753 | 12.513 | 14.513 | 9.8477 | 18.523 | 31.036 | 45.549 | 0.01
9.6671 | 10.8335 | 11.6671 | 10.6671 | 15.5006 | 17.5006 | 10.8335 | 21.5006 | 37.0012 | 54.5019 | 9.6771 | 10.8435 | 11.6671 | 10.6671 | 15.5006 | 17.5006 | 10.8435 | 21.5106 | 37.0112 | 54.5119 | 0.01
4.9451 | 8.4726 | 6.9451 | 5.9451 | 8.4177 | 10.4177 | 8.4726 | 14.4177 | 22.8353 | 33.253 | 4.9551 | 8.4826 | 6.9451 | 5.9451 | 8.4177 | 10.4177 | 8.4826 | 14.4277 | 22.8453 | 33.263 | 0.01
4.9771 | 8.4886 | 6.9771 | 5.9771 | 8.4657 | 10.4657 | 8.4886 | 14.4657 | 22.9314 | 33.3972 | 4.9871 | 8.4986 | 6.9771 | 5.9771 | 8.4657 | 10.4657 | 8.4986 | 14.4757 | 22.9414 | 33.4072 | 0.01
4.0819 | 8.041 | 6.0819 | 5.0819 | 7.1229 | 9.1229 | 8.041 | 13.1229 | 20.2458 | 29.3687 | 4.0919 | 8.051 | 6.0819 | 5.0819 | 7.1229 | 9.1229 | 8.051 | 13.1329 | 20.2558 | 29.3787 | 0.01
6.1632 | 9.0816 | 8.1632 | 7.1632 | 10.2448 | 12.2448 | 9.0816 | 16.2448 | 26.4896 | 38.7344 | 6.1732 | 9.0916 | 8.1632 | 7.1632 | 10.2448 | 12.2448 | 9.0916 | 16.2548 | 26.4996 | 38.7444 | 0.01
1.9933 | 6.9966 | 3.9933 | 2.9933 | 3.9899 | 5.9899 | 6.9966 | 9.9899 | 13.9799 | 19.9698 | 2.0033 | 7.0066 | 3.9933 | 2.9933 | 3.9899 | 5.9899 | 7.0066 | 9.9999 | 13.9899 | 19.9798 | 0.01
5.1012 | 8.5506 | 7.1012 | 6.1012 | 8.6518 | 10.6518 | 8.5506 | 14.6518 | 23.3036 | 33.9554 | 5.1112 | 8.5606 | 7.1012 | 6.1012 | 8.6518 | 10.6518 | 8.5606 | 14.6618 | 23.3136 | 33.9654 | 0.01
6.9555 | 9.4777 | 8.9555 | 7.9555 | 11.4332 | 13.4332 | 9.4777 | 17.4332 | 28.8664 | 42.2996 | 6.9655 | 9.4877 | 8.9555 | 7.9555 | 11.4332 | 13.4332 | 9.4877 | 17.4432 | 28.8764 | 42.3096 | 0.01
8.5592 | 10.2796 | 10.5592 | 9.5592 | 13.8389 | 15.8389 | 10.2796 | 19.8389 | 33.6777 | 49.5166 | 8.5692 | 10.2896 | 10.5592 | 9.5592 | 13.8389 | 15.8389 | 10.2896 | 19.8489 | 33.6877 | 49.5266 | 0.01
6.5105 | 9.2552 | 8.5105 | 7.5105 | 10.7657 | 12.7657 | 9.2552 | 16.7657 | 27.5315 | 40.2972 | 6.5205 | 9.2652 | 8.5105 | 7.5105 | 10.7657 | 12.7657 | 9.2652 | 16.7757 | 27.5415 | 40.3072 | 0.01
6.1667 | 9.0834 | 8.1667 | 7.1667 | 10.2501 | 12.2501 | 9.0834 | 16.2501 | 26.5002 | 38.7503 | 6.1767 | 9.0934 | 8.1667 | 7.1667 | 10.2501 | 12.2501 | 9.0934 | 16.2601 | 26.5102 | 38.7603 | 0.01
8.1147 | 10.0574 | 10.1147 | 9.1147 | 13.1721 | 15.1721 | 10.0574 | 19.1721 | 32.3442 | 47.5163 | 8.1247 | 10.0674 | 10.1147 | 9.1147 | 13.1721 | 15.1721 | 10.0674 | 19.1821 | 32.3542 | 47.5263 | 0.01
3.1051 | 7.5526 | 5.1051 | 4.1051 | 5.6577 | 7.6577 | 7.5526 | 11.6577 | 17.3153 | 24.973 | 3.1151 | 7.5626 | 5.1051 | 4.1051 | 5.6577 | 7.6577 | 7.5626 | 11.6677 | 17.3253 | 24.983 | 0.01
7.7699 | 9.885 | 9.7699 | 8.7699 | 12.6549 | 14.6549 | 9.885 | 18.6549 | 31.3098 | 45.9647 | 7.7799 | 9.895 | 9.7699 | 8.7699 | 12.6549 | 14.6549 | 9.895 | 18.6649 | 31.3198 | 45.9747 | 0.01
7.7437 | 9.8719 | 9.7437 | 8.7437 | 12.6156 | 14.6156 | 9.8719 | 18.6156 | 31.2312 | 45.8468 | 7.7537 | 9.8819 | 9.7437 | 8.7437 | 12.6156 | 14.6156 | 9.8819 | 18.6256 | 31.2412 | 45.8568 | 0.01
3.2528 | 7.6264 | 5.2528 | 4.2528 | 5.8791 | 7.8791 | 7.6264 | 11.8791 | 17.7583 | 25.6374 | 3.2628 | 7.6364 | 5.2528 | 4.2528 | 5.8791 | 7.8791 | 7.6364 | 11.8891 | 17.7683 | 25.6474 | 0.01
8.3933 | 10.1966 | 10.3933 | 9.3933 | 13.5899 | 15.5899 | 10.1966 | 19.5899 | 33.1798 | 48.7697 | 8.4033 | 10.2066 | 10.3933 | 9.3933 | 13.5899 | 15.5899 | 10.2066 | 19.5999 | 33.1898 | 48.7797 | 0.01
1.9955 | 6.9977 | 3.9955 | 2.9955 | 3.9932 | 5.9932 | 6.9977 | 9.9932 | 13.9864 | 19.9796 | 2.0055 | 7.0077 | 3.9955 | 2.9955 | 3.9932 | 5.9932 | 7.0077 | 10.0032 | 13.9964 | 19.9896 | 0.01
4.9613 | 8.4807 | 6.9613 | 5.9613 | 8.442 | 10.442 | 8.4807 | 14.442 | 22.8839 | 33.3259 | 4.9713 | 8.4907 | 6.9613 | 5.9613 | 8.442 | 10.442 | 8.4907 | 14.452 | 22.8939 | 33.3359 | 0.01
6.9724 | 9.4862 | 8.9724 | 7.9724 | 11.4587 | 13.4587 | 9.4862 | 17.4587 | 28.9173 | 42.376 | 6.9824 | 9.4962 | 8.9724 | 7.9724 | 11.4587 | 13.4587 | 9.4962 | 17.4687 | 28.9273 | 42.386 | 0.01
6.4531 | 9.2266 | 8.4531 | 7.4531 | 10.6797 | 12.6797 | 9.2266 | 16.6797 | 27.3594 | 40.0392 | 6.4631 | 9.2366 | 8.4531 | 7.4531 | 10.6797 | 12.6797 | 9.2366 | 16.6897 | 27.3694 | 40.0492 | 0.01
7.5656 | 9.7828 | 9.5656 | 8.5656 | 12.3483 | 14.3483 | 9.7828 | 18.3483 | 30.6967 | 45.045 | 7.5756 | 9.7928 | 9.5656 | 8.5656 | 12.3483 | 14.3483 | 9.7928 | 18.3583 | 30.7067 | 45.055 | 0.01
8.9413 | 10.4706 | 10.9413 | 9.9413 | 14.4119 | 16.4119 | 10.4706 | 20.4119 | 34.8238 | 51.2357 | 8.9513 | 10.4806 | 10.9413 | 9.9413 | 14.4119 | 16.4119 | 10.4806 | 20.4219 | 34.8338 | 51.2457 | 0.01
7.8795 | 9.9397 | 9.8795 | 8.8795 | 12.8192 | 14.8192 | 9.9397 | 18.8192 | 31.6384 | 46.4575 | 7.8895 | 9.9497 | 9.8795 | 8.8795 | 12.8192 | 14.8192 | 9.9497 | 18.8292 | 31.6484 | 46.4675 | 0.01
9.8929 | 10.9465 | 11.8929 | 10.8929 | 15.8394 | 17.8394 | 10.9465 | 21.8394 | 37.6788 | 55.5182 | 9.9029 | 10.9565 | 11.8929 | 10.8929 | 15.8394 | 17.8394 | 10.9565 | 21.8494 | 37.6888 | 55.5282 | 0.01
5.453 | 8.7265 | 7.453 | 6.453 | 9.1794 | 11.1794 | 8.7265 | 15.1794 | 24.3589 | 35.5383 | 5.463 | 8.7365 | 7.453 | 6.453 | 9.1794 | 11.1794 | 8.7365 | 15.1894 | 24.3689 | 35.5483 | 0.01
4.1572 | 8.0786 | 6.1572 | 5.1572 | 7.2357 | 9.2357 | 8.0786 | 13.2357 | 20.4715 | 29.7072 | 4.1672 | 8.0886 | 6.1572 | 5.1572 | 7.2357 | 9.2357 | 8.0886 | 13.2457 | 20.4815 | 29.7172 | 0.01
6.6304 | 9.3152 | 8.6304 | 7.6304 | 10.9456 | 12.9456 | 9.3152 | 16.9456 | 27.8912 | 40.8367 | 6.6404 | 9.3252 | 8.6304 | 7.6304 | 10.9456 | 12.9456 | 9.3252 | 16.9556 | 27.9012 | 40.8467 | 0.01
5.4603 | 8.7301 | 7.4603 | 6.4603 | 9.1904 | 11.1904 | 8.7301 | 15.1904 | 24.3809 | 35.5713 | 5.4703 | 8.7401 | 7.4603 | 6.4603 | 9.1904 | 11.1904 | 8.7401 | 15.2004 | 24.3909 | 35.5813 | 0.01
8.1682 | 10.0841 | 10.1682 | 9.1682 | 13.2523 | 15.2523 | 10.0841 | 19.2523 | 32.5045 | 47.7568 | 8.1782 | 10.0941 | 10.1682 | 9.1682 | 13.2523 | 15.2523 | 10.0941 | 19.2623 | 32.5145 | 47.7668 | 0.01
3.1459 | 7.5729 | 5.1459 | 4.1459 | 5.7188 | 7.7188 | 7.5729 | 11.7188 | 17.4377 | 25.1565 | 3.1559 | 7.5829 | 5.1459 | 4.1459 | 5.7188 | 7.7188 | 7.5829 | 11.7288 | 17.4477 | 25.1665 | 0.01
5.876 | 8.938 | 7.876 | 6.876 | 9.814 | 11.814 | 8.938 | 15.814 | 25.628 | 37.442 | 5.886 | 8.948 | 7.876 | 6.876 | 9.814 | 11.814 | 8.948 | 15.824 | 25.638 | 37.452 | 0.01
3.0444 | 7.5222 | 5.0444 | 4.0444 | 5.5667 | 7.5667 | 7.5222 | 11.5667 | 17.1333 | 24.7 | 3.0544 | 7.5322 | 5.0444 | 4.0444 | 5.5667 | 7.5667 | 7.5322 | 11.5767 | 17.1433 | 24.71 | 0.01
1.7266 | 6.8633 | 3.7266 | 2.7266 | 3.59 | 5.59 | 6.8633 | 9.59 | 13.1799 | 18.7699 | 1.7366 | 6.8733 | 3.7266 | 2.7266 | 3.59 | 5.59 | 6.8733 | 9.6 | 13.1899 | 18.7799 | 0.01
3.978 | 7.989 | 5.978 | 4.978 | 6.967 | 8.967 | 7.989 | 12.967 | 19.934 | 28.901 | 3.988 | 7.999 | 5.978 | 4.978 | 6.967 | 8.967 | 7.999 | 12.977 | 19.944 | 28.911 | 0.01
2.5753 | 7.2877 | 4.5753 | 3.5753 | 4.863 | 6.863 | 7.2877 | 10.863 | 15.726 | 22.589 | 2.5853 | 7.2977 | 4.5753 | 3.5753 | 4.863 | 6.863 | 7.2977 | 10.873 | 15.736 | 22.599 | 0.01
7.1333 | 9.5667 | 9.1333 | 8.1333 | 11.7 | 13.7 | 9.5667 | 17.7 | 29.4 | 43.1 | 7.1433 | 9.5767 | 9.1333 | 8.1333 | 11.7 | 13.7 | 9.5767 | 17.71 | 29.41 | 43.11 | 0.01
3.7989 | 7.8995 | 5.7989 | 4.7989 | 6.6984 | 8.6984 | 7.8995 | 12.6984 | 19.3968 | 28.0952 | 3.8089 | 7.9095 | 5.7989 | 4.7989 | 6.6984 | 8.6984 | 7.9095 | 12.7084 | 19.4068 | 28.1052 | 0.01
4.1942 | 8.0971 | 6.1942 | 5.1942 | 7.2913 | 9.2913 | 8.0971 | 13.2913 | 20.5826 | 29.8739 | 4.2042 | 8.1071 | 6.1942 | 5.1942 | 7.2913 | 9.2913 | 8.1071 | 13.3013 | 20.5926 | 29.8839 | 0.01
6.3221 | 9.161 | 8.3221 | 7.3221 | 10.4831 | 12.4831 | 9.161 | 16.4831 | 26.9663 | 39.4494 | 6.3321 | 9.171 | 8.3221 | 7.3221 | 10.4831 | 12.4831 | 9.171 | 16.4931 | 26.9763 | 39.4594 | 0.01
6.7721 | 9.386 | 8.7721 | 7.7721 | 11.1581 | 13.1581 | 9.386 | 17.1581 | 28.3163 | 41.4744 | 6.7821 | 9.396 | 8.7721 | 7.7721 | 11.1581 | 13.1581 | 9.396 | 17.1681 | 28.3263 | 41.4844 | 0.01
2.4844 | 7.2422 | 4.4844 | 3.4844 | 4.7265 | 6.7265 | 7.2422 | 10.7265 | 15.4531 | 22.1796 | 2.4944 | 7.2522 | 4.4844 | 3.4844 | 4.7265 | 6.7265 | 7.2522 | 10.7365 | 15.4631 | 22.1896 | 0.01
1.3352 | 6.6676 | 3.3352 | 2.3352 | 3.0029 | 5.0029 | 6.6676 | 9.0029 | 12.0057 | 17.0086 | 1.3452 | 6.6776 | 3.3352 | 2.3352 | 3.0029 | 5.0029 | 6.6776 | 9.0129 | 12.0157 | 17.0186 | 0.01
5.3983 | 8.6991 | 7.3983 | 6.3983 | 9.0974 | 11.0974 | 8.6991 | 15.0974 | 24.1948 | 35.2922 | 5.4083 | 8.7091 | 7.3983 | 6.3983 | 9.0974 | 11.0974 | 8.7091 | 15.1074 | 24.2048 | 35.3022 | 0.01
4.0997 | 8.0498 | 6.0997 | 5.0997 | 7.1495 | 9.1495 | 8.0498 | 13.1495 | 20.2991 | 29.4486 | 4.1097 | 8.0598 | 6.0997 | 5.0997 | 7.1495 | 9.1495 | 8.0598 | 13.1595 | 20.3091 | 29.4586 | 0.01
4.8389 | 8.4194 | 6.8389 | 5.8389 | 8.2583 | 10.2583 | 8.4194 | 14.2583 | 22.5167 | 32.775 | 4.8489 | 8.4294 | 6.8389 | 5.8389 | 8.2583 | 10.2583 | 8.4294 | 14.2683 | 22.5267 | 32.785 | 0.01
8.8632 | 10.4316 | 10.8632 | 9.8632 | 14.2948 | 16.2948 | 10.4316 | 20.2948 | 34.5896 | 50.8844 | 8.8732 | 10.4416 | 10.8632 | 9.8632 | 14.2948 | 16.2948 | 10.4416 | 20.3048 | 34.5996 | 50.8944 | 0.01
5.9752 | 8.9876 | 7.9752 | 6.9752 | 9.9628 | 11.9628 | 8.9876 | 15.9628 | 25.9257 | 37.8885 | 5.9852 | 8.9976 | 7.9752 | 6.9752 | 9.9628 | 11.9628 | 8.9976 | 15.9728 | 25.9357 | 37.8985 | 0.01
5.6012 | 8.8006 | 7.6012 | 6.6012 | 9.4018 | 11.4018 | 8.8006 | 15.4018 | 24.8036 | 36.2054 | 5.6112 | 8.8106 | 7.6012 | 6.6012 | 9.4018 | 11.4018 | 8.8106 | 15.4118 | 24.8136 | 36.2154 | 0.01
4.939 | 8.4695 | 6.939 | 5.939 | 8.4086 | 10.4086 | 8.4695 | 14.4086 | 22.8171 | 33.2257 | 4.949 | 8.4795 | 6.939 | 5.939 | 8.4086 | 10.4086 | 8.4795 | 14.4186 | 22.8271 | 33.2357 | 0.01
6.5777 | 9.2889 | 8.5777 | 7.5777 | 10.8666 | 12.8666 | 9.2889 | 16.8666 | 27.7332 | 40.5998 | 6.5877 | 9.2989 | 8.5777 | 7.5777 | 10.8666 | 12.8666 | 9.2989 | 16.8766 | 27.7432 | 40.6098 | 0.01
7.5768 | 9.7884 | 9.5768 | 8.5768 | 12.3652 | 14.3652 | 9.7884 | 18.3652 | 30.7305 | 45.0957 | 7.5868 | 9.7984 | 9.5768 | 8.5768 | 12.3652 | 14.3652 | 9.7984 | 18.3752 | 30.7405 | 45.1057 | 0.01
6.8322 | 9.4161 | 8.8322 | 7.8322 | 11.2483 | 13.2483 | 9.4161 | 17.2483 | 28.4966 | 41.7449 | 6.8422 | 9.4261 | 8.8322 | 7.8322 | 11.2483 | 13.2483 | 9.4261 | 17.2583 | 28.5066 | 41.7549 | 0.01
1.2409 | 6.6205 | 3.2409 | 2.2409 | 2.8614 | 4.8614 | 6.6205 | 8.8614 | 11.7228 | 16.5842 | 1.2509 | 6.6305 | 3.2409 | 2.2409 | 2.8614 | 4.8614 | 6.6305 | 8.8714 | 11.7328 | 16.5942 | 0.01
6.8982 | 9.4491 | 8.8982 | 7.8982 | 11.3473 | 13.3473 | 9.4491 | 17.3473 | 28.6945 | 42.0418 | 6.9082 | 9.4591 | 8.8982 | 7.8982 | 11.3473 | 13.3473 | 9.4591 | 17.3573 | 28.7045 | 42.0518 | 0.01
5.4805 | 8.7403 | 7.4805 | 6.4805 | 9.2208 | 11.2208 | 8.7403 | 15.2208 | 24.4416 | 35.6624 | 5.4905 | 8.7503 | 7.4805 | 6.4805 | 9.2208 | 11.2208 | 8.7503 | 15.2308 | 24.4516 | 35.6724 | 0.01
5.5055 | 8.7528 | 7.5055 | 6.5055 | 9.2583 | 11.2583 | 8.7528 | 15.2583 | 24.5166 | 35.775 | 5.5155 | 8.7628 | 7.5055 | 6.5055 | 9.2583 | 11.2583 | 8.7628 | 15.2683 | 24.5266 | 35.785 | 0.01
6.3791 | 9.1895 | 8.3791 | 7.3791 | 10.5686 | 12.5686 | 9.1895 | 16.5686 | 27.1372 | 39.7057 | 6.3891 | 9.1995 | 8.3791 | 7.3791 | 10.5686 | 12.5686 | 9.1995 | 16.5786 | 27.1472 | 39.7157 | 0.01
7.1075 | 9.5538 | 9.1075 | 8.1075 | 11.6613 | 13.6613 | 9.5538 | 17.6613 | 29.3226 | 42.984 | 7.1175 | 9.5638 | 9.1075 | 8.1075 | 11.6613 | 13.6613 | 9.5638 | 17.6713 | 29.3326 | 42.994 | 0.01
4.3758 | 8.1879 | 6.3758 | 5.3758 | 7.5637 | 9.5637 | 8.1879 | 13.5637 | 21.1275 | 30.6912 | 4.3858 | 8.1979 | 6.3758 | 5.3758 | 7.5637 | 9.5637 | 8.1979 | 13.5737 | 21.1375 | 30.7012 | 0.01
3.1194 | 7.5597 | 5.1194 | 4.1194 | 5.6791 | 7.6791 | 7.5597 | 11.6791 | 17.3582 | 25.0373 | 3.1294 | 7.5697 | 5.1194 | 4.1194 | 5.6791 | 7.6791 | 7.5697 | 11.6891 | 17.3682 | 25.0473 | 0.01
7.0201 | 9.5101 | 9.0201 | 8.0201 | 11.5302 | 13.5302 | 9.5101 | 17.5302 | 29.0604 | 42.5905 | 7.0301 | 9.5201 | 9.0201 | 8.0201 | 11.5302 | 13.5302 | 9.5201 | 17.5402 | 29.0704 | 42.6005 | 0.01
7.5622 | 9.7811 | 9.5622 | 8.5622 | 12.3433 | 14.3433 | 9.7811 | 18.3433 | 30.6866 | 45.03 | 7.5722 | 9.7911 | 9.5622 | 8.5622 | 12.3433 | 14.3433 | 9.7911 | 18.3533 | 30.6966 | 45.04 | 0.01
6.846 | 9.423 | 8.846 | 7.846 | 11.2689 | 13.2689 | 9.423 | 17.2689 | 28.5379 | 41.8068 | 6.856 | 9.433 | 8.846 | 7.846 | 11.2689 | 13.2689 | 9.433 | 17.2789 | 28.5479 | 41.8168 | 0.01
4.6009 | 8.3005 | 6.6009 | 5.6009 | 7.9014 | 9.9014 | 8.3005 | 13.9014 | 21.8028 | 31.7043 | 4.6109 | 8.3105 | 6.6009 | 5.6009 | 7.9014 | 9.9014 | 8.3105 | 13.9114 | 21.8128 | 31.7143 | 0.01
4.0996 | 8.0498 | 6.0996 | 5.0996 | 7.1495 | 9.1495 | 8.0498 | 13.1495 | 20.2989 | 29.4484 | 4.1096 | 8.0598 | 6.0996 | 5.0996 | 7.1495 | 9.1495 | 8.0598 | 13.1595 | 20.3089 | 29.4584 | 0.01
3.9553 | 7.9776 | 5.9553 | 4.9553 | 6.9329 | 8.9329 | 7.9776 | 12.9329 | 19.8658 | 28.7987 | 3.9653 | 7.9876 | 5.9553 | 4.9553 | 6.9329 | 8.9329 | 7.9876 | 12.9429 | 19.8758 | 28.8087 | 0.01
6.3421 | 9.1711 | 8.3421 | 7.3421 | 10.5132 | 12.5132 | 9.1711 | 16.5132 | 27.0264 | 39.5396 | 6.3521 | 9.1811 | 8.3421 | 7.3421 | 10.5132 | 12.5132 | 9.1811 | 16.5232 | 27.0364 | 39.5496 | 0.01
9.3127 | 10.6563 | 11.3127 | 10.3127 | 14.969 | 16.969 | 10.6563 | 20.969 | 35.9381 | 52.9071 | 9.3227 | 10.6663 | 11.3127 | 10.3127 | 14.969 | 16.969 | 10.6663 | 20.979 | 35.9481 | 52.9171 | 0.01
5.4219 | 8.711 | 7.4219 | 6.4219 | 9.1329 | 11.1329 | 8.711 | 15.1329 | 24.2657 | 35.3986 | 5.4319 | 8.721 | 7.4219 | 6.4219 | 9.1329 | 11.1329 | 8.721 | 15.1429 | 24.2757 | 35.4086 | 0.01
3.6288 | 7.8144 | 5.6288 | 4.6288 | 6.4432 | 8.4432 | 7.8144 | 12.4432 | 18.8865 | 27.3297 | 3.6388 | 7.8244 | 5.6288 | 4.6288 | 6.4432 | 8.4432 | 7.8244 | 12.4532 | 18.8965 | 27.3397 | 0.01
5.6238 | 8.8119 | 7.6238 | 6.6238 | 9.4356 | 11.4356 | 8.8119 | 15.4356 | 24.8713 | 36.3069 | 5.6338 | 8.8219 | 7.6238 | 6.6238 | 9.4356 | 11.4356 | 8.8219 | 15.4456 | 24.8813 | 36.3169 | 0.01
6.3482 | 9.1741 | 8.3482 | 7.3482 | 10.5223 | 12.5223 | 9.1741 | 16.5223 | 27.0446 | 39.5669 | 6.3582 | 9.1841 | 8.3482 | 7.3482 | 10.5223 | 12.5223 | 9.1841 | 16.5323 | 27.0546 | 39.5769 | 0.01
10.7899 | 11.3949 | 12.7899 | 11.7899 | 17.1848 | 19.1848 | 11.3949 | 23.1848 | 40.3696 | 59.5544 | 10.7999 | 11.4049 | 12.7899 | 11.7899 | 17.1848 | 19.1848 | 11.4049 | 23.1948 | 40.3796 | 59.5644 | 0.01
4.9975 | 8.4988 | 6.9975 | 5.9975 | 8.4963 | 10.4963 | 8.4988 | 14.4963 | 22.9926 | 33.489 | 5.0075 | 8.5088 | 6.9975 | 5.9975 | 8.4963 | 10.4963 | 8.5088 | 14.5063 | 23.0026 | 33.499 | 0.01
5.1208 | 8.5604 | 7.1208 | 6.1208 | 8.6812 | 10.6812 | 8.5604 | 14.6812 | 23.3625 | 34.0437 | 5.1308 | 8.5704 | 7.1208 | 6.1208 | 8.6812 | 10.6812 | 8.5704 | 14.6912 | 23.3725 | 34.0537 | 0.01
4.9466 | 8.4733 | 6.9466 | 5.9466 | 8.4199 | 10.4199 | 8.4733 | 14.4199 | 22.8398 | 33.2597 | 4.9566 | 8.4833 | 6.9466 | 5.9466 | 8.4199 | 10.4199 | 8.4833 | 14.4299 | 22.8498 | 33.2697 | 0.01
6.8683 | 9.4342 | 8.8683 | 7.8683 | 11.3025 | 13.3025 | 9.4342 | 17.3025 | 28.605 | 41.9075 | 6.8783 | 9.4442 | 8.8683 | 7.8683 | 11.3025 | 13.3025 | 9.4442 | 17.3125 | 28.615 | 41.9175 | 0.01
6.7307 | 9.3653 | 8.7307 | 7.7307 | 11.096 | 13.096 | 9.3653 | 17.096 | 28.192 | 41.288 | 6.7407 | 9.3753 | 8.7307 | 7.7307 | 11.096 | 13.096 | 9.3753 | 17.106 | 28.202 | 41.298 | 0.01
6.6858 | 9.3429 | 8.6858 | 7.6858 | 11.0287 | 13.0287 | 9.3429 | 17.0287 | 28.0575 | 41.0862 | 6.6958 | 9.3529 | 8.6858 | 7.6858 | 11.0287 | 13.0287 | 9.3529 | 17.0387 | 28.0675 | 41.0962 | 0.01
5.8933 | 8.9466 | 7.8933 | 6.8933 | 9.8399 | 11.8399 | 8.9466 | 15.8399 | 25.6798 | 37.5197 | 5.9033 | 8.9566 | 7.8933 | 6.8933 | 9.8399 | 11.8399 | 8.9566 | 15.8499 | 25.6898 | 37.5297 | 0.01
8.0544 | 10.0272 | 10.0544 | 9.0544 | 13.0817 | 15.0817 | 10.0272 | 19.0817 | 32.1633 | 47.245 | 8.0644 | 10.0372 | 10.0544 | 9.0544 | 13.0817 | 15.0817 | 10.0372 | 19.0917 | 32.1733 | 47.255 | 0.01
6.9633 | 9.4817 | 8.9633 | 7.9633 | 11.445 | 13.445 | 9.4817 | 17.445 | 28.89 | 42.335 | 6.9733 | 9.4917 | 8.9633 | 7.9633 | 11.445 | 13.445 | 9.4917 | 17.455 | 28.9 | 42.345 | 0.01
5.5051 | 8.7525 | 7.5051 | 6.5051 | 9.2576 | 11.2576 | 8.7525 | 15.2576 | 24.5152 | 35.7727 | 5.5151 | 8.7625 | 7.5051 | 6.5051 | 9.2576 | 11.2576 | 8.7625 | 15.2676 | 24.5252 | 35.7827 | 0.01
9.8582 | 10.9291 | 11.8582 | 10.8582 | 15.7873 | 17.7873 | 10.9291 | 21.7873 | 37.5746 | 55.3619 | 9.8682 | 10.9391 | 11.8582 | 10.8582 | 15.7873 | 17.7873 | 10.9391 | 21.7973 | 37.5846 | 55.3719 | 0.01
6.417 | 9.2085 | 8.417 | 7.417 | 10.6256 | 12.6256 | 9.2085 | 16.6256 | 27.2511 | 39.8767 | 6.427 | 9.2185 | 8.417 | 7.417 | 10.6256 | 12.6256 | 9.2185 | 16.6356 | 27.2611 | 39.8867 | 0.01
6.3882 | 9.1941 | 8.3882 | 7.3882 | 10.5822 | 12.5822 | 9.1941 | 16.5822 | 27.1645 | 39.7467 | 6.3982 | 9.2041 | 8.3882 | 7.3882 | 10.5822 | 12.5822 | 9.2041 | 16.5922 | 27.1745 | 39.7567 | 0.01
6.9699 | 9.4849 | 8.9699 | 7.9699 | 11.4548 | 13.4548 | 9.4849 | 17.4548 | 28.9096 | 42.3644 | 6.9799 | 9.4949 | 8.9699 | 7.9699 | 11.4548 | 13.4548 | 9.4949 | 17.4648 | 28.9196 | 42.3744 | 0.01
8.6251 | 10.3126 | 10.6251 | 9.6251 | 13.9377 | 15.9377 | 10.3126 | 19.9377 | 33.8753 | 49.813 | 8.6351 | 10.3226 | 10.6251 | 9.6251 | 13.9377 | 15.9377 | 10.3226 | 19.9477 | 33.8853 | 49.823 | 0.01
8.9815 | 10.4907 | 10.9815 | 9.9815 | 14.4722 | 16.4722 | 10.4907 | 20.4722 | 34.9444 | 51.4166 | 8.9915 | 10.5007 | 10.9815 | 9.9815 | 14.4722 | 16.4722 | 10.5007 | 20.4822 | 34.9544 | 51.4266 | 0.01
8.2166 | 10.1083 | 10.2166 | 9.2166 | 13.3248 | 15.3248 | 10.1083 | 19.3248 | 32.6497 | 47.9745 | 8.2266 | 10.1183 | 10.2166 | 9.2166 | 13.3248 | 15.3248 | 10.1183 | 19.3348 | 32.6597 | 47.9845 | 0.01
2.2054 | 7.1027 | 4.2054 | 3.2054 | 4.308 | 6.308 | 7.1027 | 10.308 | 14.6161 | 20.9241 | 2.2154 | 7.1127 | 4.2054 | 3.2054 | 4.308 | 6.308 | 7.1127 | 10.318 | 14.6261 | 20.9341 | 0.01
6.4717 | 9.2358 | 8.4717 | 7.4717 | 10.7075 | 12.7075 | 9.2358 | 16.7075 | 27.415 | 40.1224 | 6.4817 | 9.2458 | 8.4717 | 7.4717 | 10.7075 | 12.7075 | 9.2458 | 16.7175 | 27.425 | 40.1324 | 0.01
4.2513 | 8.1257 | 6.2513 | 5.2513 | 7.377 | 9.377 | 8.1257 | 13.377 | 20.754 | 30.131 | 4.2613 | 8.1357 | 6.2513 | 5.2513 | 7.377 | 9.377 | 8.1357 | 13.387 | 20.764 | 30.141 | 0.01
6.5595 | 9.2797 | 8.5595 | 7.5595 | 10.8392 | 12.8392 | 9.2797 | 16.8392 | 27.6785 | 40.5177 | 6.5695 | 9.2897 | 8.5595 | 7.5595 | 10.8392 | 12.8392 | 9.2897 | 16.8492 | 27.6885 | 40.5277 | 0.01
1.7548 | 6.8774 | 3.7548 | 2.7548 | 3.6322 | 5.6322 | 6.8774 | 9.6322 | 13.2644 | 18.8966 | 1.7648 | 6.8874 | 3.7548 | 2.7548 | 3.6322 | 5.6322 | 6.8874 | 9.6422 | 13.2744 | 18.9066 | 0.01
9.0243 | 10.5121 | 11.0243 | 10.0243 | 14.5364 | 16.5364 | 10.5121 | 20.5364 | 35.0729 | 51.6093 | 9.0343 | 10.5221 | 11.0243 | 10.0243 | 14.5364 | 16.5364 | 10.5221 | 20.5464 | 35.0829 | 51.6193 | 0.01
5.3876 | 8.6938 | 7.3876 | 6.3876 | 9.0814 | 11.0814 | 8.6938 | 15.0814 | 24.1628 | 35.2443 | 5.3976 | 8.7038 | 7.3876 | 6.3876 | 9.0814 | 11.0814 | 8.7038 | 15.0914 | 24.1728 | 35.2543 | 0.01
3.3907 | 7.6954 | 5.3907 | 4.3907 | 6.0861 | 8.0861 | 7.6954 | 12.0861 | 18.1721 | 26.2582 | 3.4007 | 7.7054 | 5.3907 | 4.3907 | 6.0861 | 8.0861 | 7.7054 | 12.0961 | 18.1821 | 26.2682 | 0.01
6.445 | 9.2225 | 8.445 | 7.445 | 10.6675 | 12.6675 | 9.2225 | 16.6675 | 27.3349 | 40.0024 | 6.455 | 9.2325 | 8.445 | 7.445 | 10.6675 | 12.6675 | 9.2325 | 16.6775 | 27.3449 | 40.0124 | 0.01
3.0261 | 7.5131 | 5.0261 | 4.0261 | 5.5392 | 7.5392 | 7.5131 | 11.5392 | 17.0783 | 24.6175 | 3.0361 | 7.5231 | 5.0261 | 4.0261 | 5.5392 | 7.5392 | 7.5231 | 11.5492 | 17.0883 | 24.6275 | 0.01
6.1399 | 9.0699 | 8.1399 | 7.1399 | 10.2098 | 12.2098 | 9.0699 | 16.2098 | 26.4196 | 38.6295 | 6.1499 | 9.0799 | 8.1399 | 7.1399 | 10.2098 | 12.2098 | 9.0799 | 16.2198 | 26.4296 | 38.6395 | 0.01
2.9477 | 7.4739 | 4.9477 | 3.9477 | 5.4216 | 7.4216 | 7.4739 | 11.4216 | 16.8432 | 24.2647 | 2.9577 | 7.4839 | 4.9477 | 3.9477 | 5.4216 | 7.4216 | 7.4839 | 11.4316 | 16.8532 | 24.2747 | 0.01
2.1588 | 7.0794 | 4.1588 | 3.1588 | 4.2382 | 6.2382 | 7.0794 | 10.2382 | 14.4765 | 20.7147 | 2.1688 | 7.0894 | 4.1588 | 3.1588 | 4.2382 | 6.2382 | 7.0894 | 10.2482 | 14.4865 | 20.7247 | 0.01
5.37 | 8.685 | 7.37 | 6.37 | 9.0549 | 11.0549 | 8.685 | 15.0549 | 24.1099 | 35.1648 | 5.38 | 8.695 | 7.37 | 6.37 | 9.0549 | 11.0549 | 8.695 | 15.0649 | 24.1199 | 35.1748 | 0.01
7.0615 | 9.5308 | 9.0615 | 8.0615 | 11.5923 | 13.5923 | 9.5308 | 17.5923 | 29.1846 | 42.7769 | 7.0715 | 9.5408 | 9.0615 | 8.0615 | 11.5923 | 13.5923 | 9.5408 | 17.6023 | 29.1946 | 42.7869 | 0.01
2.8948 | 7.4474 | 4.8948 | 3.8948 | 5.3422 | 7.3422 | 7.4474 | 11.3422 | 16.6844 | 24.0266 | 2.9048 | 7.4574 | 4.8948 | 3.8948 | 5.3422 | 7.3422 | 7.4574 | 11.3522 | 16.6944 | 24.0366 | 0.01
7.5473 | 9.7737 | 9.5473 | 8.5473 | 12.321 | 14.321 | 9.7737 | 18.321 | 30.6419 | 44.9629 | 7.5573 | 9.7837 | 9.5473 | 8.5473 | 12.321 | 14.321 | 9.7837 | 18.331 | 30.6519 | 44.9729 | 0.01
7.1431 | 9.5716 | 9.1431 | 8.1431 | 11.7147 | 13.7147 | 9.5716 | 17.7147 | 29.4293 | 43.144 | 7.1531 | 9.5816 | 9.1431 | 8.1431 | 11.7147 | 13.7147 | 9.5816 | 17.7247 | 29.4393 | 43.154 | 0.01
12.0964 | 12.0482 | 14.0964 | 13.0964 | 19.1446 | 21.1446 | 12.0964 | 25.1928 | 44.3373 | 65.4819 | 12.1064 | 12.0582 | 14.0964 | 13.0964 | 19.1446 | 21.1446 | 12.1064 | 25.2028 | 44.3473 | 65.4919 | 0.01
6.765 | 9.3825 | 8.765 | 7.765 | 11.1475 | 13.1475 | 9.3825 | 17.1475 | 28.2951 | 41.4426 | 6.775 | 9.3925 | 8.765 | 7.765 | 11.1475 | 13.1475 | 9.3925 | 17.1575 | 28.3051 | 41.4526 | 0.01
2.2718 | 7.1359 | 4.2718 | 3.2718 | 4.4077 | 6.4077 | 7.1359 | 10.4077 | 14.8153 | 21.223 | 2.2818 | 7.1459 | 4.2718 | 3.2718 | 4.4077 | 6.4077 | 7.1459 | 10.4177 | 14.8253 | 21.233 | 0.01
6.4769 | 9.2385 | 8.4769 | 7.4769 | 10.7154 | 12.7154 | 9.2385 | 16.7154 | 27.4308 | 40.1462 | 6.4869 | 9.2485 | 8.4769 | 7.4769 | 10.7154 | 12.7154 | 9.2485 | 16.7254 | 27.4408 | 40.1562 | 0.01
5.3268 | 8.6634 | 7.3268 | 6.3268 | 8.9902 | 10.9902 | 8.6634 | 14.9902 | 23.9805 | 34.9707 | 5.3368 | 8.6734 | 7.3268 | 6.3268 | 8.9902 | 10.9902 | 8.6734 | 15.0002 | 23.9905 | 34.9807 | 0.01
6.3209 | 9.1605 | 8.3209 | 7.3209 | 10.4814 | 12.4814 | 9.1605 | 16.4814 | 26.9627 | 39.4441 | 6.3309 | 9.1705 | 8.3209 | 7.3209 | 10.4814 | 12.4814 | 9.1705 | 16.4914 | 26.9727 | 39.4541 | 0.01
7.5282 | 9.7641 | 9.5282 | 8.5282 | 12.2923 | 14.2923 | 9.7641 | 18.2923 | 30.5847 | 44.877 | 7.5382 | 9.7741 | 9.5282 | 8.5282 | 12.2923 | 14.2923 | 9.7741 | 18.3023 | 30.5947 | 44.887 | 0.01
3.6141 | 7.8071 | 5.6141 | 4.6141 | 6.4212 | 8.4212 | 7.8071 | 12.4212 | 18.8424 | 27.2636 | 3.6241 | 7.8171 | 5.6141 | 4.6141 | 6.4212 | 8.4212 | 7.8171 | 12.4312 | 18.8524 | 27.2736 | 0.01
3.6248 | 7.8124 | 5.6248 | 4.6248 | 6.4372 | 8.4372 | 7.8124 | 12.4372 | 18.8744 | 27.3116 | 3.6348 | 7.8224 | 5.6248 | 4.6248 | 6.4372 | 8.4372 | 7.8224 | 12.4472 | 18.8844 | 27.3216 | 0.01
7.3335 | 9.6667 | 9.3335 | 8.3335 | 12.0002 | 14.0002 | 9.6667 | 18.0002 | 30.0004 | 44.0006 | 7.3435 | 9.6767 | 9.3335 | 8.3335 | 12.0002 | 14.0002 | 9.6767 | 18.0102 | 30.0104 | 44.0106 | 0.01
6.9821 | 9.491 | 8.9821 | 7.9821 | 11.4731 | 13.4731 | 9.491 | 17.4731 | 28.9462 | 42.4193 | 6.9921 | 9.501 | 8.9821 | 7.9821 | 11.4731 | 13.4731 | 9.501 | 17.4831 | 28.9562 | 42.4293 | 0.01
4.583 | 8.2915 | 6.583 | 5.583 | 7.8745 | 9.8745 | 8.2915 | 13.8745 | 21.749 | 31.6234 | 4.593 | 8.3015 | 6.583 | 5.583 | 7.8745 | 9.8745 | 8.3015 | 13.8845 | 21.759 | 31.6334 | 0.01
4.0577 | 8.0289 | 6.0577 | 5.0577 | 7.0866 | 9.0866 | 8.0289 | 13.0866 | 20.1732 | 29.2598 | 4.0677 | 8.0389 | 6.0577 | 5.0577 | 7.0866 | 9.0866 | 8.0389 | 13.0966 | 20.1832 | 29.2698 | 0.01
6.6071 | 9.3035 | 8.6071 | 7.6071 | 10.9106 | 12.9106 | 9.3035 | 16.9106 | 27.8213 | 40.7319 | 6.6171 | 9.3135 | 8.6071 | 7.6071 | 10.9106 | 12.9106 | 9.3135 | 16.9206 | 27.8313 | 40.7419 | 0.01
9.0369 | 10.5184 | 11.0369 | 10.0369 | 14.5553 | 16.5553 | 10.5184 | 20.5553 | 35.1106 | 51.6659 | 9.0469 | 10.5284 | 11.0369 | 10.0369 | 14.5553 | 16.5553 | 10.5284 | 20.5653 | 35.1206 | 51.6759 | 0.01
7.3809 | 9.6904 | 9.3809 | 8.3809 | 12.0713 | 14.0713 | 9.6904 | 18.0713 | 30.1426 | 44.2139 | 7.3909 | 9.7004 | 9.3809 | 8.3809 | 12.0713 | 14.0713 | 9.7004 | 18.0813 | 30.1526 | 44.2239 | 0.01
9.6282 | 10.8141 | 11.6282 | 10.6282 | 15.4423 | 17.4423 | 10.8141 | 21.4423 | 36.8847 | 54.327 | 9.6382 | 10.8241 | 11.6282 | 10.6282 | 15.4423 | 17.4423 | 10.8241 | 21.4523 | 36.8947 | 54.337 | 0.01
6.5968 | 9.2984 | 8.5968 | 7.5968 | 10.8952 | 12.8952 | 9.2984 | 16.8952 | 27.7903 | 40.6855 | 6.6068 | 9.3084 | 8.5968 | 7.5968 | 10.8952 | 12.8952 | 9.3084 | 16.9052 | 27.8003 | 40.6955 | 0.01
8.5168 | 10.2584 | 10.5168 | 9.5168 | 13.7751 | 15.7751 | 10.2584 | 19.7751 | 33.5503 | 49.3254 | 8.5268 | 10.2684 | 10.5168 | 9.5168 | 13.7751 | 15.7751 | 10.2684 | 19.7851 | 33.5603 | 49.3354 | 0.01
9.0004 | 10.5002 | 11.0004 | 10.0004 | 14.5006 | 16.5006 | 10.5002 | 20.5006 | 35.0013 | 51.5019 | 9.0104 | 10.5102 | 11.0004 | 10.0004 | 14.5006 | 16.5006 | 10.5102 | 20.5106 | 35.0113 | 51.5119 | 0.01
6.6461 | 9.3231 | 8.6461 | 7.6461 | 10.9692 | 12.9692 | 9.3231 | 16.9692 | 27.9384 | 40.9076 | 6.6561 | 9.3331 | 8.6461 | 7.6461 | 10.9692 | 12.9692 | 9.3331 | 16.9792 | 27.9484 | 40.9176 | 0.01
6.2957 | 9.1479 | 8.2957 | 7.2957 | 10.4436 | 12.4436 | 9.1479 | 16.4436 | 26.8871 | 39.3307 | 6.3057 | 9.1579 | 8.2957 | 7.2957 | 10.4436 | 12.4436 | 9.1579 | 16.4536 | 26.8971 | 39.3407 | 0.01
4.6554 | 8.3277 | 6.6554 | 5.6554 | 7.983 | 9.983 | 8.3277 | 13.983 | 21.9661 | 31.9491 | 4.6654 | 8.3377 | 6.6554 | 5.6554 | 7.983 | 9.983 | 8.3377 | 13.993 | 21.9761 | 31.9591 | 0.01
5.1508 | 8.5754 | 7.1508 | 6.1508 | 8.7262 | 10.7262 | 8.5754 | 14.7262 | 23.4524 | 34.1786 | 5.1608 | 8.5854 | 7.1508 | 6.1508 | 8.7262 | 10.7262 | 8.5854 | 14.7362 | 23.4624 | 34.1886 | 0.01
7.8893 | 9.9446 | 9.8893 | 8.8893 | 12.8339 | 14.8339 | 9.9446 | 18.8339 | 31.6679 | 46.5018 | 7.8993 | 9.9546 | 9.8893 | 8.8893 | 12.8339 | 14.8339 | 9.9546 | 18.8439 | 31.6779 | 46.5118 | 0.01
3.7649 | 7.8824 | 5.7649 | 4.7649 | 6.6473 | 8.6473 | 7.8824 | 12.6473 | 19.2946 | 27.9418 | 3.7749 | 7.8924 | 5.7649 | 4.7649 | 6.6473 | 8.6473 | 7.8924 | 12.6573 | 19.3046 | 27.9518 | 0.01
5.558 | 8.779 | 7.558 | 6.558 | 9.337 | 11.337 | 8.779 | 15.337 | 24.6741 | 36.0111 | 5.568 | 8.789 | 7.558 | 6.558 | 9.337 | 11.337 | 8.789 | 15.347 | 24.6841 | 36.0211 | 0.01
7.42 | 9.71 | 9.42 | 8.42 | 12.13 | 14.13 | 9.71 | 18.13 | 30.26 | 44.39 | 7.43 | 9.72 | 9.42 | 8.42 | 12.13 | 14.13 | 9.72 | 18.14 | 30.27 | 44.4 | 0.01
6.472 | 9.236 | 8.472 | 7.472 | 10.708 | 12.708 | 9.236 | 16.708 | 27.416 | 40.124 | 6.482 | 9.246 | 8.472 | 7.472 | 10.708 | 12.708 | 9.246 | 16.718 | 27.426 | 40.134 | 0.01
4.871 | 8.4355 | 6.871 | 5.871 | 8.3066 | 10.3066 | 8.4355 | 14.3066 | 22.6131 | 32.9197 | 4.881 | 8.4455 | 6.871 | 5.871 | 8.3066 | 10.3066 | 8.4455 | 14.3166 | 22.6231 | 32.9297 | 0.01
5.508 | 8.754 | 7.508 | 6.508 | 9.2621 | 11.2621 | 8.754 | 15.2621 | 24.5241 | 35.7862 | 5.518 | 8.764 | 7.508 | 6.508 | 9.2621 | 11.2621 | 8.764 | 15.2721 | 24.5341 | 35.7962 | 0.01
7.0059 | 9.5029 | 9.0059 | 8.0059 | 11.5088 | 13.5088 | 9.5029 | 17.5088 | 29.0177 | 42.5265 | 7.0159 | 9.5129 | 9.0059 | 8.0059 | 11.5088 | 13.5088 | 9.5129 | 17.5188 | 29.0277 | 42.5365 | 0.01
7.757 | 9.8785 | 9.757 | 8.757 | 12.6355 | 14.6355 | 9.8785 | 18.6355 | 31.271 | 45.9065 | 7.767 | 9.8885 | 9.757 | 8.757 | 12.6355 | 14.6355 | 9.8885 | 18.6455 | 31.281 | 45.9165 | 0.01
5.623 | 8.8115 | 7.623 | 6.623 | 9.4344 | 11.4344 | 8.8115 | 15.4344 | 24.8689 | 36.3033 | 5.633 | 8.8215 | 7.623 | 6.623 | 9.4344 | 11.4344 | 8.8215 | 15.4444 | 24.8789 | 36.3133 | 0.01
8.5794 | 10.2897 | 10.5794 | 9.5794 | 13.869 | 15.869 | 10.2897 | 19.869 | 33.7381 | 49.6071 | 8.5894 | 10.2997 | 10.5794 | 9.5794 | 13.869 | 15.869 | 10.2997 | 19.879 | 33.7481 | 49.6171 | 0.01
3.9507 | 7.9753 | 5.9507 | 4.9507 | 6.926 | 8.926 | 7.9753 | 12.926 | 19.852 | 28.778 | 3.9607 | 7.9853 | 5.9507 | 4.9507 | 6.926 | 8.926 | 7.9853 | 12.936 | 19.862 | 28.788 | 0.01
5.6655 | 8.8328 | 7.6655 | 6.6655 | 9.4983 | 11.4983 | 8.8328 | 15.4983 | 24.9965 | 36.4948 | 5.6755 | 8.8428 | 7.6655 | 6.6655 | 9.4983 | 11.4983 | 8.8428 | 15.5083 | 25.0065 | 36.5048 | 0.01
4.9787 | 8.4894 | 6.9787 | 5.9787 | 8.4681 | 10.4681 | 8.4894 | 14.4681 | 22.9362 | 33.4042 | 4.9887 | 8.4994 | 6.9787 | 5.9787 | 8.4681 | 10.4681 | 8.4994 | 14.4781 | 22.9462 | 33.4142 | 0.01
7.6227 | 9.8114 | 9.6227 | 8.6227 | 12.4341 | 14.4341 | 9.8114 | 18.4341 | 30.8682 | 45.3023 | 7.6327 | 9.8214 | 9.6227 | 8.6227 | 12.4341 | 14.4341 | 9.8214 | 18.4441 | 30.8782 | 45.3123 | 0.01
5.7922 | 8.8961 | 7.7922 | 6.7922 | 9.6883 | 11.6883 | 8.8961 | 15.6883 | 25.3766 | 37.0649 | 5.8022 | 8.9061 | 7.7922 | 6.7922 | 9.6883 | 11.6883 | 8.9061 | 15.6983 | 25.3866 | 37.0749 | 0.01
2.9192 | 7.4596 | 4.9192 | 3.9192 | 5.3788 | 7.3788 | 7.4596 | 11.3788 | 16.7575 | 24.1363 | 2.9292 | 7.4696 | 4.9192 | 3.9192 | 5.3788 | 7.3788 | 7.4696 | 11.3888 | 16.7675 | 24.1463 | 0.01
5.928 | 8.964 | 7.928 | 6.928 | 9.892 | 11.892 | 8.964 | 15.892 | 25.784 | 37.676 | 5.938 | 8.974 | 7.928 | 6.928 | 9.892 | 11.892 | 8.974 | 15.902 | 25.794 | 37.686 | 0.01
4.208 | 8.104 | 6.208 | 5.208 | 7.312 | 9.312 | 8.104 | 13.312 | 20.6239 | 29.9359 | 4.218 | 8.114 | 6.208 | 5.208 | 7.312 | 9.312 | 8.114 | 13.322 | 20.6339 | 29.9459 | 0.01
5.2939 | 8.6469 | 7.2939 | 6.2939 | 8.9408 | 10.9408 | 8.6469 | 14.9408 | 23.8817 | 34.8225 | 5.3039 | 8.6569 | 7.2939 | 6.2939 | 8.9408 | 10.9408 | 8.6569 | 14.9508 | 23.8917 | 34.8325 | 0.01
6.2531 | 9.1265 | 8.2531 | 7.2531 | 10.3796 | 12.3796 | 9.1265 | 16.3796 | 26.7592 | 39.1388 | 6.2631 | 9.1365 | 8.2531 | 7.2531 | 10.3796 | 12.3796 | 9.1365 | 16.3896 | 26.7692 | 39.1488 | 0.01
6.8091 | 9.4046 | 8.8091 | 7.8091 | 11.2137 | 13.2137 | 9.4046 | 17.2137 | 28.4274 | 41.6412 | 6.8191 | 9.4146 | 8.8091 | 7.8091 | 11.2137 | 13.2137 | 9.4146 | 17.2237 | 28.4374 | 41.6512 | 0.01
9.4171 | 10.7085 | 11.4171 | 10.4171 | 15.1256 | 17.1256 | 10.7085 | 21.1256 | 36.2512 | 53.3767 | 9.4271 | 10.7185 | 11.4171 | 10.4171 | 15.1256 | 17.1256 | 10.7185 | 21.1356 | 36.2612 | 53.3867 | 0.01
5.3234 | 8.6617 | 7.3234 | 6.3234 | 8.9851 | 10.9851 | 8.6617 | 14.9851 | 23.9702 | 34.9553 | 5.3334 | 8.6717 | 7.3234 | 6.3234 | 8.9851 | 10.9851 | 8.6717 | 14.9951 | 23.9802 | 34.9653 | 0.01
7.0344 | 9.5172 | 9.0344 | 8.0344 | 11.5515 | 13.5515 | 9.5172 | 17.5515 | 29.1031 | 42.6546 | 7.0444 | 9.5272 | 9.0344 | 8.0344 | 11.5515 | 13.5515 | 9.5272 | 17.5615 | 29.1131 | 42.6646 | 0.01
6.5479 | 9.2739 | 8.5479 | 7.5479 | 10.8218 | 12.8218 | 9.2739 | 16.8218 | 27.6437 | 40.4655 | 6.5579 | 9.2839 | 8.5479 | 7.5479 | 10.8218 | 12.8218 | 9.2839 | 16.8318 | 27.6537 | 40.4755 | 0.01
6.4934 | 9.2467 | 8.4934 | 7.4934 | 10.7401 | 12.7401 | 9.2467 | 16.7401 | 27.4801 | 40.2202 | 6.5034 | 9.2567 | 8.4934 | 7.4934 | 10.7401 | 12.7401 | 9.2567 | 16.7501 | 27.4901 | 40.2302 | 0.01
9.043 | 10.5215 | 11.043 | 10.043 | 14.5645 | 16.5645 | 10.5215 | 20.5645 | 35.1289 | 51.6934 | 9.053 | 10.5315 | 11.043 | 10.043 | 14.5645 | 16.5645 | 10.5315 | 20.5745 | 35.1389 | 51.7034 | 0.01
4.2503 | 8.1252 | 6.2503 | 5.2503 | 7.3755 | 9.3755 | 8.1252 | 13.3755 | 20.7509 | 30.1264 | 4.2603 | 8.1352 | 6.2503 | 5.2503 | 7.3755 | 9.3755 | 8.1352 | 13.3855 | 20.7609 | 30.1364 | 0.01
4.6551 | 8.3276 | 6.6551 | 5.6551 | 7.9827 | 9.9827 | 8.3276 | 13.9827 | 21.9654 | 31.9481 | 4.6651 | 8.3376 | 6.6551 | 5.6551 | 7.9827 | 9.9827 | 8.3376 | 13.9927 | 21.9754 | 31.9581 | 0.01
7.2956 | 9.6478 | 9.2956 | 8.2956 | 11.9435 | 13.9435 | 9.6478 | 17.9435 | 29.8869 | 43.8304 | 7.3056 | 9.6578 | 9.2956 | 8.2956 | 11.9435 | 13.9435 | 9.6578 | 17.9535 | 29.8969 | 43.8404 | 0.01
6.1556 | 9.0778 | 8.1556 | 7.1556 | 10.2334 | 12.2334 | 9.0778 | 16.2334 | 26.4668 | 38.7002 | 6.1656 | 9.0878 | 8.1556 | 7.1556 | 10.2334 | 12.2334 | 9.0878 | 16.2434 | 26.4768 | 38.7102 | 0.01
6.6144 | 9.3072 | 8.6144 | 7.6144 | 10.9216 | 12.9216 | 9.3072 | 16.9216 | 27.8432 | 40.7648 | 6.6244 | 9.3172 | 8.6144 | 7.6144 | 10.9216 | 12.9216 | 9.3172 | 16.9316 | 27.8532 | 40.7748 | 0.01
5.303 | 8.6515 | 7.303 | 6.303 | 8.9545 | 10.9545 | 8.6515 | 14.9545 | 23.9091 | 34.8636 | 5.313 | 8.6615 | 7.303 | 6.303 | 8.9545 | 10.9545 | 8.6615 | 14.9645 | 23.9191 | 34.8736 | 0.01
5.1456 | 8.5728 | 7.1456 | 6.1456 | 8.7184 | 10.7184 | 8.5728 | 14.7184 | 23.4369 | 34.1553 | 5.1556 | 8.5828 | 7.1456 | 6.1456 | 8.7184 | 10.7184 | 8.5828 | 14.7284 | 23.4469 | 34.1653 | 0.01
9.5864 | 10.7932 | 11.5864 | 10.5864 | 15.3796 | 17.3796 | 10.7932 | 21.3796 | 36.7592 | 54.1388 | 9.5964 | 10.8032 | 11.5864 | 10.5864 | 15.3796 | 17.3796 | 10.8032 | 21.3896 | 36.7692 | 54.1488 | 0.01
2.3841 | 7.1921 | 4.3841 | 3.3841 | 4.5762 | 6.5762 | 7.1921 | 10.5762 | 15.1524 | 21.7285 | 2.3941 | 7.2021 | 4.3841 | 3.3841 | 4.5762 | 6.5762 | 7.2021 | 10.5862 | 15.1624 | 21.7385 | 0.01
5.619 | 8.8095 | 7.619 | 6.619 | 9.4285 | 11.4285 | 8.8095 | 15.4285 | 24.8571 | 36.2856 | 5.629 | 8.8195 | 7.619 | 6.619 | 9.4285 | 11.4285 | 8.8195 | 15.4385 | 24.8671 | 36.2956 | 0.01
9.1739 | 10.587 | 11.1739 | 10.1739 | 14.7609 | 16.7609 | 10.587 | 20.7609 | 35.5217 | 52.2826 | 9.1839 | 10.597 | 11.1739 | 10.1739 | 14.7609 | 16.7609 | 10.597 | 20.7709 | 35.5317 | 52.2926 | 0.01
5.5091 | 8.7545 | 7.5091 | 6.5091 | 9.2636 | 11.2636 | 8.7545 | 15.2636 | 24.5272 | 35.7908 | 5.5191 | 8.7645 | 7.5091 | 6.5091 | 9.2636 | 11.2636 | 8.7645 | 15.2736 | 24.5372 | 35.8008 | 0.01
1.6872 | 6.8436 | 3.6872 | 2.6872 | 3.5309 | 5.5309 | 6.8436 | 9.5309 | 13.0617 | 18.5926 | 1.6972 | 6.8536 | 3.6872 | 2.6872 | 3.5309 | 5.5309 | 6.8536 | 9.5409 | 13.0717 | 18.6026 | 0.01
9.6443 | 10.8221 | 11.6443 | 10.6443 | 15.4664 | 17.4664 | 10.8221 | 21.4664 | 36.9328 | 54.3992 | 9.6543 | 10.8321 | 11.6443 | 10.6443 | 15.4664 | 17.4664 | 10.8321 | 21.4764 | 36.9428 | 54.4092 | 0.01
8.6989 | 10.3495 | 10.6989 | 9.6989 | 14.0484 | 16.0484 | 10.3495 | 20.0484 | 34.0968 | 50.1452 | 8.7089 | 10.3595 | 10.6989 | 9.6989 | 14.0484 | 16.0484 | 10.3595 | 20.0584 | 34.1068 | 50.1552 | 0.01
11.2292 | 11.6146 | 13.2292 | 12.2292 | 17.8437 | 19.8437 | 11.6146 | 23.8437 | 41.6875 | 61.5312 | 11.2392 | 11.6246 | 13.2292 | 12.2292 | 17.8437 | 19.8437 | 11.6246 | 23.8537 | 41.6975 | 61.5412 | 0.01
8.8814 | 10.4407 | 10.8814 | 9.8814 | 14.322 | 16.322 | 10.4407 | 20.322 | 34.6441 | 50.9661 | 8.8914 | 10.4507 | 10.8814 | 9.8814 | 14.322 | 16.322 | 10.4507 | 20.332 | 34.6541 | 50.9761 | 0.01
4.2468 | 8.1234 | 6.2468 | 5.2468 | 7.3702 | 9.3702 | 8.1234 | 13.3702 | 20.7403 | 30.1105 | 4.2568 | 8.1334 | 6.2468 | 5.2468 | 7.3702 | 9.3702 | 8.1334 | 13.3802 | 20.7503 | 30.1205 | 0.01
4.0644 | 8.0322 | 6.0644 | 5.0644 | 7.0967 | 9.0967 | 8.0322 | 13.0967 | 20.1933 | 29.29 | 4.0744 | 8.0422 | 6.0644 | 5.0644 | 7.0967 | 9.0967 | 8.0422 | 13.1067 | 20.2033 | 29.3 | 0.01
6.9188 | 9.4594 | 8.9188 | 7.9188 | 11.3781 | 13.3781 | 9.4594 | 17.3781 | 28.7563 | 42.1344 | 6.9288 | 9.4694 | 8.9188 | 7.9188 | 11.3781 | 13.3781 | 9.4694 | 17.3881 | 28.7663 | 42.1444 | 0.01
6.6996 | 9.3498 | 8.6996 | 7.6996 | 11.0495 | 13.0495 | 9.3498 | 17.0495 | 28.0989 | 41.1484 | 6.7096 | 9.3598 | 8.6996 | 7.6996 | 11.0495 | 13.0495 | 9.3598 | 17.0595 | 28.1089 | 41.1584 | 0.01
2.8424 | 7.4212 | 4.8424 | 3.8424 | 5.2635 | 7.2635 | 7.4212 | 11.2635 | 16.5271 | 23.7906 | 2.8524 | 7.4312 | 4.8424 | 3.8424 | 5.2635 | 7.2635 | 7.4312 | 11.2735 | 16.5371 | 23.8006 | 0.01
4.0657 | 8.0328 | 6.0657 | 5.0657 | 7.0985 | 9.0985 | 8.0328 | 13.0985 | 20.197 | 29.2955 | 4.0757 | 8.0428 | 6.0657 | 5.0657 | 7.0985 | 9.0985 | 8.0428 | 13.1085 | 20.207 | 29.3055 | 0.01
4.7146 | 8.3573 | 6.7146 | 5.7146 | 8.0719 | 10.0719 | 8.3573 | 14.0719 | 22.1437 | 32.2156 | 4.7246 | 8.3673 | 6.7146 | 5.7146 | 8.0719 | 10.0719 | 8.3673 | 14.0819 | 22.1537 | 32.2256 | 0.01
4.7268 | 8.3634 | 6.7268 | 5.7268 | 8.0902 | 10.0902 | 8.3634 | 14.0902 | 22.1804 | 32.2706 | 4.7368 | 8.3734 | 6.7268 | 5.7268 | 8.0902 | 10.0902 | 8.3734 | 14.1002 | 22.1904 | 32.2806 | 0.01
6.8306 | 9.4153 | 8.8306 | 7.8306 | 11.2459 | 13.2459 | 9.4153 | 17.2459 | 28.4919 | 41.7378 | 6.8406 | 9.4253 | 8.8306 | 7.8306 | 11.2459 | 13.2459 | 9.4253 | 17.2559 | 28.5019 | 41.7478 | 0.01
3.8975 | 7.9488 | 5.8975 | 4.8975 | 6.8463 | 8.8463 | 7.9488 | 12.8463 | 19.6926 | 28.5389 | 3.9075 | 7.9588 | 5.8975 | 4.8975 | 6.8463 | 8.8463 | 7.9588 | 12.8563 | 19.7026 | 28.5489 | 0.01
5.9003 | 8.9501 | 7.9003 | 6.9003 | 9.8504 | 11.8504 | 8.9501 | 15.8504 | 25.7009 | 37.5513 | 5.9103 | 8.9601 | 7.9003 | 6.9003 | 9.8504 | 11.8504 | 8.9601 | 15.8604 | 25.7109 | 37.5613 | 0.01
5.3318 | 8.6659 | 7.3318 | 6.3318 | 8.9977 | 10.9977 | 8.6659 | 14.9977 | 23.9954 | 34.993 | 5.3418 | 8.6759 | 7.3318 | 6.3318 | 8.9977 | 10.9977 | 8.6759 | 15.0077 | 24.0054 | 35.003 | 0.01
4.9579 | 8.4789 | 6.9579 | 5.9579 | 8.4368 | 10.4368 | 8.4789 | 14.4368 | 22.8736 | 33.3104 | 4.9679 | 8.4889 | 6.9579 | 5.9579 | 8.4368 | 10.4368 | 8.4889 | 14.4468 | 22.8836 | 33.3204 | 0.01
6.4693 | 9.2346 | 8.4693 | 7.4693 | 10.7039 | 12.7039 | 9.2346 | 16.7039 | 27.4078 | 40.1117 | 6.4793 | 9.2446 | 8.4693 | 7.4693 | 10.7039 | 12.7039 | 9.2446 | 16.7139 | 27.4178 | 40.1217 | 0.01
5.5471 | 8.7735 | 7.5471 | 6.5471 | 9.3206 | 11.3206 | 8.7735 | 15.3206 | 24.6413 | 35.9619 | 5.5571 | 8.7835 | 7.5471 | 6.5471 | 9.3206 | 11.3206 | 8.7835 | 15.3306 | 24.6513 | 35.9719 | 0.01
9.9466 | 10.9733 | 11.9466 | 10.9466 | 15.9199 | 17.9199 | 10.9733 | 21.9199 | 37.8399 | 55.7598 | 9.9566 | 10.9833 | 11.9466 | 10.9466 | 15.9199 | 17.9199 | 10.9833 | 21.9299 | 37.8499 | 55.7698 | 0.01
7.4375 | 9.7188 | 9.4375 | 8.4375 | 12.1563 | 14.1563 | 9.7188 | 18.1563 | 30.3126 | 44.469 | 7.4475 | 9.7288 | 9.4375 | 8.4375 | 12.1563 | 14.1563 | 9.7288 | 18.1663 | 30.3226 | 44.479 | 0.01
4.3121 | 8.1561 | 6.3121 | 5.3121 | 7.4682 | 9.4682 | 8.1561 | 13.4682 | 20.9364 | 30.4045 | 4.3221 | 8.1661 | 6.3121 | 5.3121 | 7.4682 | 9.4682 | 8.1661 | 13.4782 | 20.9464 | 30.4145 | 0.01
5.9724 | 8.9862 | 7.9724 | 6.9724 | 9.9586 | 11.9586 | 8.9862 | 15.9586 | 25.9171 | 37.8757 | 5.9824 | 8.9962 | 7.9724 | 6.9724 | 9.9586 | 11.9586 | 8.9962 | 15.9686 | 25.9271 | 37.8857 | 0.01
8.7536 | 10.3768 | 10.7536 | 9.7536 | 14.1304 | 16.1304 | 10.3768 | 20.1304 | 34.2609 | 50.3913 | 8.7636 | 10.3868 | 10.7536 | 9.7536 | 14.1304 | 16.1304 | 10.3868 | 20.1404 | 34.2709 | 50.4013 | 0.01
5.5862 | 8.7931 | 7.5862 | 6.5862 | 9.3793 | 11.3793 | 8.7931 | 15.3793 | 24.7586 | 36.138 | 5.5962 | 8.8031 | 7.5862 | 6.5862 | 9.3793 | 11.3793 | 8.8031 | 15.3893 | 24.7686 | 36.148 | 0.01
3.4881 | 7.744 | 5.4881 | 4.4881 | 6.2321 | 8.2321 | 7.744 | 12.2321 | 18.4642 | 26.6963 | 3.4981 | 7.754 | 5.4881 | 4.4881 | 6.2321 | 8.2321 | 7.754 | 12.2421 | 18.4742 | 26.7063 | 0.01
5.5062 | 8.7531 | 7.5062 | 6.5062 | 9.2593 | 11.2593 | 8.7531 | 15.2593 | 24.5187 | 35.778 | 5.5162 | 8.7631 | 7.5062 | 6.5062 | 9.2593 | 11.2593 | 8.7631 | 15.2693 | 24.5287 | 35.788 | 0.01
7.6439 | 9.822 | 9.6439 | 8.6439 | 12.4659 | 14.4659 | 9.822 | 18.4659 | 30.9318 | 45.3977 | 7.6539 | 9.832 | 9.6439 | 8.6439 | 12.4659 | 14.4659 | 9.832 | 18.4759 | 30.9418 | 45.4077 | 0.01
5.254 | 8.627 | 7.254 | 6.254 | 8.8809 | 10.8809 | 8.627 | 14.8809 | 23.7619 | 34.6428 | 5.264 | 8.637 | 7.254 | 6.254 | 8.8809 | 10.8809 | 8.637 | 14.8909 | 23.7719 | 34.6528 | 0.01
4.2232 | 8.1116 | 6.2232 | 5.2232 | 7.3348 | 9.3348 | 8.1116 | 13.3348 | 20.6696 | 30.0044 | 4.2332 | 8.1216 | 6.2232 | 5.2232 | 7.3348 | 9.3348 | 8.1216 | 13.3448 | 20.6796 | 30.0144 | 0.01
6.8151 | 9.4076 | 8.8151 | 7.8151 | 11.2227 | 13.2227 | 9.4076 | 17.2227 | 28.4453 | 41.668 | 6.8251 | 9.4176 | 8.8151 | 7.8151 | 11.2227 | 13.2227 | 9.4176 | 17.2327 | 28.4553 | 41.678 | 0.01
5.3333 | 8.6667 | 7.3333 | 6.3333 | 9 | 11 | 8.6667 | 15 | 24 | 34.9999 | 5.3433 | 8.6767 | 7.3333 | 6.3333 | 9 | 11 | 8.6767 | 15.01 | 24.01 | 35.0099 | 0.01
4.0377 | 8.0189 | 6.0377 | 5.0377 | 7.0566 | 9.0566 | 8.0189 | 13.0566 | 20.1131 | 29.1697 | 4.0477 | 8.0289 | 6.0377 | 5.0377 | 7.0566 | 9.0566 | 8.0289 | 13.0666 | 20.1231 | 29.1797 | 0.01
8.7767 | 10.3884 | 10.7767 | 9.7767 | 14.1651 | 16.1651 | 10.3884 | 20.1651 | 34.3302 | 50.4953 | 8.7867 | 10.3984 | 10.7767 | 9.7767 | 14.1651 | 16.1651 | 10.3984 | 20.1751 | 34.3402 | 50.5053 | 0.01
4.2765 | 8.1383 | 6.2765 | 5.2765 | 7.4148 | 9.4148 | 8.1383 | 13.4148 | 20.8296 | 30.2443 | 4.2865 | 8.1483 | 6.2765 | 5.2765 | 7.4148 | 9.4148 | 8.1483 | 13.4248 | 20.8396 | 30.2543 | 0.01
6.1788 | 9.0894 | 8.1788 | 7.1788 | 10.2683 | 12.2683 | 9.0894 | 16.2683 | 26.5365 | 38.8048 | 6.1888 | 9.0994 | 8.1788 | 7.1788 | 10.2683 | 12.2683 | 9.0994 | 16.2783 | 26.5465 | 38.8148 | 0.01
4.8286 | 8.4143 | 6.8286 | 5.8286 | 8.2429 | 10.2429 | 8.4143 | 14.2429 | 22.4857 | 32.7286 | 4.8386 | 8.4243 | 6.8286 | 5.8286 | 8.2429 | 10.2429 | 8.4243 | 14.2529 | 22.4957 | 32.7386 | 0.01
7.1539 | 9.577 | 9.1539 | 8.1539 | 11.7309 | 13.7309 | 9.577 | 17.7309 | 29.4618 | 43.1927 | 7.1639 | 9.587 | 9.1539 | 8.1539 | 11.7309 | 13.7309 | 9.587 | 17.7409 | 29.4718 | 43.2027 | 0.01
7.5051 | 9.7525 | 9.5051 | 8.5051 | 12.2576 | 14.2576 | 9.7525 | 18.2576 | 30.5152 | 44.7728 | 7.5151 | 9.7625 | 9.5051 | 8.5051 | 12.2576 | 14.2576 | 9.7625 | 18.2676 | 30.5252 | 44.7828 | 0.01
8.6284 | 10.3142 | 10.6284 | 9.6284 | 13.9426 | 15.9426 | 10.3142 | 19.9426 | 33.8852 | 49.8278 | 8.6384 | 10.3242 | 10.6284 | 9.6284 | 13.9426 | 15.9426 | 10.3242 | 19.9526 | 33.8952 | 49.8378 | 0.01
6.4705 | 9.2352 | 8.4705 | 7.4705 | 10.7057 | 12.7057 | 9.2352 | 16.7057 | 27.4114 | 40.1171 | 6.4805 | 9.2452 | 8.4705 | 7.4705 | 10.7057 | 12.7057 | 9.2452 | 16.7157 | 27.4214 | 40.1271 | 0.01
5.1058 | 8.5529 | 7.1058 | 6.1058 | 8.6586 | 10.6586 | 8.5529 | 14.6586 | 23.3173 | 33.9759 | 5.1158 | 8.5629 | 7.1058 | 6.1058 | 8.6586 | 10.6586 | 8.5629 | 14.6686 | 23.3273 | 33.9859 | 0.01
6.1713 | 9.0857 | 8.1713 | 7.1713 | 10.257 | 12.257 | 9.0857 | 16.257 | 26.514 | 38.7709 | 6.1813 | 9.0957 | 8.1713 | 7.1713 | 10.257 | 12.257 | 9.0957 | 16.267 | 26.524 | 38.7809 | 0.01
3.8207 | 7.9104 | 5.8207 | 4.8207 | 6.7311 | 8.7311 | 7.9104 | 12.7311 | 19.4621 | 28.1932 | 3.8307 | 7.9204 | 5.8207 | 4.8207 | 6.7311 | 8.7311 | 7.9204 | 12.7411 | 19.4721 | 28.2032 | 0.01
4.6634 | 8.3317 | 6.6634 | 5.6634 | 7.9952 | 9.9952 | 8.3317 | 13.9952 | 21.9903 | 31.9855 | 4.6734 | 8.3417 | 6.6634 | 5.6634 | 7.9952 | 9.9952 | 8.3417 | 14.0052 | 22.0003 | 31.9955 | 0.01
9.839 | 10.9195 | 11.839 | 10.839 | 15.7585 | 17.7585 | 10.9195 | 21.7585 | 37.5171 | 55.2756 | 9.849 | 10.9295 | 11.839 | 10.839 | 15.7585 | 17.7585 | 10.9295 | 21.7685 | 37.5271 | 55.2856 | 0.01
5.9254 | 8.9627 | 7.9254 | 6.9254 | 9.8881 | 11.8881 | 8.9627 | 15.8881 | 25.7762 | 37.6643 | 5.9354 | 8.9727 | 7.9254 | 6.9254 | 9.8881 | 11.8881 | 8.9727 | 15.8981 | 25.7862 | 37.6743 | 0.01
5.9787 | 8.9893 | 7.9787 | 6.9787 | 9.968 | 11.968 | 8.9893 | 15.968 | 25.936 | 37.9041 | 5.9887 | 8.9993 | 7.9787 | 6.9787 | 9.968 | 11.968 | 8.9993 | 15.978 | 25.946 | 37.9141 | 0.01
2.3372 | 7.1686 | 4.3372 | 3.3372 | 4.5058 | 6.5058 | 7.1686 | 10.5058 | 15.0116 | 21.5174 | 2.3472 | 7.1786 | 4.3372 | 3.3372 | 4.5058 | 6.5058 | 7.1786 | 10.5158 | 15.0216 | 21.5274 | 0.01
5.4146 | 8.7073 | 7.4146 | 6.4146 | 9.1219 | 11.1219 | 8.7073 | 15.1219 | 24.2438 | 35.3657 | 5.4246 | 8.7173 | 7.4146 | 6.4146 | 9.1219 | 11.1219 | 8.7173 | 15.1319 | 24.2538 | 35.3757 | 0.01
6.6838 | 9.3419 | 8.6838 | 7.6838 | 11.0257 | 13.0257 | 9.3419 | 17.0257 | 28.0514 | 41.077 | 6.6938 | 9.3519 | 8.6838 | 7.6838 | 11.0257 | 13.0257 | 9.3519 | 17.0357 | 28.0614 | 41.087 | 0.01
1.2105 | 6.6053 | 3.2105 | 2.2105 | 2.8158 | 4.8158 | 6.6053 | 8.8158 | 11.6316 | 16.4474 | 1.2205 | 6.6153 | 3.2105 | 2.2105 | 2.8158 | 4.8158 | 6.6153 | 8.8258 | 11.6416 | 16.4574 | 0.01
7.4824 | 9.7412 | 9.4824 | 8.4824 | 12.2237 | 14.2237 | 9.7412 | 18.2237 | 30.4473 | 44.671 | 7.4924 | 9.7512 | 9.4824 | 8.4824 | 12.2237 | 14.2237 | 9.7512 | 18.2337 | 30.4573 | 44.681 | 0.01
6.0927 | 9.0463 | 8.0927 | 7.0927 | 10.139 | 12.139 | 9.0463 | 16.139 | 26.2781 | 38.4171 | 6.1027 | 9.0563 | 8.0927 | 7.0927 | 10.139 | 12.139 | 9.0563 | 16.149 | 26.2881 | 38.4271 | 0.01
3.9913 | 7.9956 | 5.9913 | 4.9913 | 6.9869 | 8.9869 | 7.9956 | 12.9869 | 19.9739 | 28.9608 | 4.0013 | 8.0056 | 5.9913 | 4.9913 | 6.9869 | 8.9869 | 8.0056 | 12.9969 | 19.9839 | 28.9708 | 0.01
8.1269 | 10.0635 | 10.1269 | 9.1269 | 13.1904 | 15.1904 | 10.0635 | 19.1904 | 32.3808 | 47.5712 | 8.1369 | 10.0735 | 10.1269 | 9.1269 | 13.1904 | 15.1904 | 10.0735 | 19.2004 | 32.3908 | 47.5812 | 0.01
5.4364 | 8.7182 | 7.4364 | 6.4364 | 9.1546 | 11.1546 | 8.7182 | 15.1546 | 24.3092 | 35.4638 | 5.4464 | 8.7282 | 7.4364 | 6.4364 | 9.1546 | 11.1546 | 8.7282 | 15.1646 | 24.3192 | 35.4738 | 0.01
7.1821 | 9.591 | 9.1821 | 8.1821 | 11.7731 | 13.7731 | 9.591 | 17.7731 | 29.5463 | 43.3194 | 7.1921 | 9.601 | 9.1821 | 8.1821 | 11.7731 | 13.7731 | 9.601 | 17.7831 | 29.5563 | 43.3294 | 0.01
5.2544 | 8.6272 | 7.2544 | 6.2544 | 8.8816 | 10.8816 | 8.6272 | 14.8816 | 23.7633 | 34.6449 | 5.2644 | 8.6372 | 7.2544 | 6.2544 | 8.8816 | 10.8816 | 8.6372 | 14.8916 | 23.7733 | 34.6549 | 0.01
6.9219 | 9.461 | 8.9219 | 7.9219 | 11.3829 | 13.3829 | 9.461 | 17.3829 | 28.7658 | 42.1486 | 6.9319 | 9.471 | 8.9219 | 7.9219 | 11.3829 | 13.3829 | 9.471 | 17.3929 | 28.7758 | 42.1586 | 0.01
4.2326 | 8.1163 | 6.2326 | 5.2326 | 7.3488 | 9.3488 | 8.1163 | 13.3488 | 20.6977 | 30.0465 | 4.2426 | 8.1263 | 6.2326 | 5.2326 | 7.3488 | 9.3488 | 8.1263 | 13.3588 | 20.7077 | 30.0565 | 0.01
7.8659 | 9.9329 | 9.8659 | 8.8659 | 12.7988 | 14.7988 | 9.9329 | 18.7988 | 31.5977 | 46.3965 | 7.8759 | 9.9429 | 9.8659 | 8.8659 | 12.7988 | 14.7988 | 9.9429 | 18.8088 | 31.6077 | 46.4065 | 0.01
6.8237 | 9.4119 | 8.8237 | 7.8237 | 11.2356 | 13.2356 | 9.4119 | 17.2356 | 28.4712 | 41.7068 | 6.8337 | 9.4219 | 8.8237 | 7.8237 | 11.2356 | 13.2356 | 9.4219 | 17.2456 | 28.4812 | 41.7168 | 0.01
10.0714 | 11.0357 | 12.0714 | 11.0714 | 16.1071 | 18.1071 | 11.0357 | 22.1071 | 38.2142 | 56.3213 | 10.0814 | 11.0457 | 12.0714 | 11.0714 | 16.1071 | 18.1071 | 11.0457 | 22.1171 | 38.2242 | 56.3313 | 0.01
8.6333 | 10.3167 | 10.6333 | 9.6333 | 13.95 | 15.95 | 10.3167 | 19.95 | 33.8999 | 49.8499 | 8.6433 | 10.3267 | 10.6333 | 9.6333 | 13.95 | 15.95 | 10.3267 | 19.96 | 33.9099 | 49.8599 | 0.01
6.1212 | 9.0606 | 8.1212 | 7.1212 | 10.1818 | 12.1818 | 9.0606 | 16.1818 | 26.3636 | 38.5454 | 6.1312 | 9.0706 | 8.1212 | 7.1212 | 10.1818 | 12.1818 | 9.0706 | 16.1918 | 26.3736 | 38.5554 | 0.01
6.3032 | 9.1516 | 8.3032 | 7.3032 | 10.4548 | 12.4548 | 9.1516 | 16.4548 | 26.9097 | 39.3645 | 6.3132 | 9.1616 | 8.3032 | 7.3032 | 10.4548 | 12.4548 | 9.1616 | 16.4648 | 26.9197 | 39.3745 | 0.01
4.3758 | 8.1879 | 6.3758 | 5.3758 | 7.5637 | 9.5637 | 8.1879 | 13.5637 | 21.1273 | 30.691 | 4.3858 | 8.1979 | 6.3758 | 5.3758 | 7.5637 | 9.5637 | 8.1979 | 13.5737 | 21.1373 | 30.701 | 0.01
9.2988 | 10.6494 | 11.2988 | 10.2988 | 14.9482 | 16.9482 | 10.6494 | 20.9482 | 35.8964 | 52.8446 | 9.3088 | 10.6594 | 11.2988 | 10.2988 | 14.9482 | 16.9482 | 10.6594 | 20.9582 | 35.9064 | 52.8546 | 0.01
6.0363 | 9.0181 | 8.0363 | 7.0363 | 10.0544 | 12.0544 | 9.0181 | 16.0544 | 26.1089 | 38.1633 | 6.0463 | 9.0281 | 8.0363 | 7.0363 | 10.0544 | 12.0544 | 9.0281 | 16.0644 | 26.1189 | 38.1733 | 0.01
4.0855 | 8.0427 | 6.0855 | 5.0855 | 7.1282 | 9.1282 | 8.0427 | 13.1282 | 20.2564 | 29.3846 | 4.0955 | 8.0527 | 6.0855 | 5.0855 | 7.1282 | 9.1282 | 8.0527 | 13.1382 | 20.2664 | 29.3946 | 0.01
2.5889 | 7.2945 | 4.5889 | 3.5889 | 4.8834 | 6.8834 | 7.2945 | 10.8834 | 15.7668 | 22.6502 | 2.5989 | 7.3045 | 4.5889 | 3.5889 | 4.8834 | 6.8834 | 7.3045 | 10.8934 | 15.7768 | 22.6602 | 0.01
5.0002 | 8.5001 | 7.0002 | 6.0002 | 8.5003 | 10.5003 | 8.5001 | 14.5003 | 23.0006 | 33.5009 | 5.0102 | 8.5101 | 7.0002 | 6.0002 | 8.5003 | 10.5003 | 8.5101 | 14.5103 | 23.0106 | 33.5109 | 0.01
3.9935 | 7.9967 | 5.9935 | 4.9935 | 6.9902 | 8.9902 | 7.9967 | 12.9902 | 19.9804 | 28.9706 | 4.0035 | 8.0067 | 5.9935 | 4.9935 | 6.9902 | 8.9902 | 8.0067 | 13.0002 | 19.9904 | 28.9806 | 0.01
4.5745 | 8.2872 | 6.5745 | 5.5745 | 7.8617 | 9.8617 | 8.2872 | 13.8617 | 21.7234 | 31.5851 | 4.5845 | 8.2972 | 6.5745 | 5.5745 | 7.8617 | 9.8617 | 8.2972 | 13.8717 | 21.7334 | 31.5951 | 0.01
9.9779 | 10.9889 | 11.9779 | 10.9779 | 15.9668 | 17.9668 | 10.9889 | 21.9668 | 37.9337 | 55.9005 | 9.9879 | 10.9989 | 11.9779 | 10.9779 | 15.9668 | 17.9668 | 10.9989 | 21.9768 | 37.9437 | 55.9105 | 0.01
5.9845 | 8.9923 | 7.9845 | 6.9845 | 9.9768 | 11.9768 | 8.9923 | 15.9768 | 25.9536 | 37.9304 | 5.9945 | 9.0023 | 7.9845 | 6.9845 | 9.9768 | 11.9768 | 9.0023 | 15.9868 | 25.9636 | 37.9404 | 0.01
6.7095 | 9.3548 | 8.7095 | 7.7095 | 11.0643 | 13.0643 | 9.3548 | 17.0643 | 28.1286 | 41.1928 | 6.7195 | 9.3648 | 8.7095 | 7.7095 | 11.0643 | 13.0643 | 9.3648 | 17.0743 | 28.1386 | 41.2028 | 0.01
4.33 | 8.165 | 6.33 | 5.33 | 7.4951 | 9.4951 | 8.165 | 13.4951 | 20.9901 | 30.4852 | 4.34 | 8.175 | 6.33 | 5.33 | 7.4951 | 9.4951 | 8.175 | 13.5051 | 21.0001 | 30.4952 | 0.01
7.3109 | 9.6554 | 9.3109 | 8.3109 | 11.9663 | 13.9663 | 9.6554 | 17.9663 | 29.9327 | 43.899 | 7.3209 | 9.6654 | 9.3109 | 8.3109 | 11.9663 | 13.9663 | 9.6654 | 17.9763 | 29.9427 | 43.909 | 0.01
8.3704 | 10.1852 | 10.3704 | 9.3704 | 13.5557 | 15.5557 | 10.1852 | 19.5557 | 33.1113 | 48.667 | 8.3804 | 10.1952 | 10.3704 | 9.3704 | 13.5557 | 15.5557 | 10.1952 | 19.5657 | 33.1213 | 48.677 | 0.01
5.3059 | 8.6529 | 7.3059 | 6.3059 | 8.9588 | 10.9588 | 8.6529 | 14.9588 | 23.9177 | 34.8765 | 5.3159 | 8.6629 | 7.3059 | 6.3059 | 8.9588 | 10.9588 | 8.6629 | 14.9688 | 23.9277 | 34.8865 | 0.01
5.3629 | 8.6814 | 7.3629 | 6.3629 | 9.0443 | 11.0443 | 8.6814 | 15.0443 | 24.0887 | 35.133 | 5.3729 | 8.6914 | 7.3629 | 6.3629 | 9.0443 | 11.0443 | 8.6914 | 15.0543 | 24.0987 | 35.143 | 0.01
3.9816 | 7.9908 | 5.9816 | 4.9816 | 6.9725 | 8.9725 | 7.9908 | 12.9725 | 19.9449 | 28.9174 | 3.9916 | 8.0008 | 5.9816 | 4.9816 | 6.9725 | 8.9725 | 8.0008 | 12.9825 | 19.9549 | 28.9274 | 0.01
5.3166 | 8.6583 | 7.3166 | 6.3166 | 8.9749 | 10.9749 | 8.6583 | 14.9749 | 23.9499 | 34.9248 | 5.3266 | 8.6683 | 7.3166 | 6.3166 | 8.9749 | 10.9749 | 8.6683 | 14.9849 | 23.9599 | 34.9348 | 0.01
4.8471 | 8.4235 | 6.8471 | 5.8471 | 8.2706 | 10.2706 | 8.4235 | 14.2706 | 22.5412 | 32.8118 | 4.8571 | 8.4335 | 6.8471 | 5.8471 | 8.2706 | 10.2706 | 8.4335 | 14.2806 | 22.5512 | 32.8218 | 0.01
3.4432 | 7.7216 | 5.4432 | 4.4432 | 6.1648 | 8.1648 | 7.7216 | 12.1648 | 18.3295 | 26.4943 | 3.4532 | 7.7316 | 5.4432 | 4.4432 | 6.1648 | 8.1648 | 7.7316 | 12.1748 | 18.3395 | 26.5043 | 0.01
9.9646 | 10.9823 | 11.9646 | 10.9646 | 15.9469 | 17.9469 | 10.9823 | 21.9469 | 37.8938 | 55.8407 | 9.9746 | 10.9923 | 11.9646 | 10.9646 | 15.9469 | 17.9469 | 10.9923 | 21.9569 | 37.9038 | 55.8507 | 0.01
4.8739 | 8.4369 | 6.8739 | 5.8739 | 8.3108 | 10.3108 | 8.4369 | 14.3108 | 22.6217 | 32.9325 | 4.8839 | 8.4469 | 6.8739 | 5.8739 | 8.3108 | 10.3108 | 8.4469 | 14.3208 | 22.6317 | 32.9425 | 0.01
6.177 | 9.0885 | 8.177 | 7.177 | 10.2655 | 12.2655 | 9.0885 | 16.2655 | 26.531 | 38.7965 | 6.187 | 9.0985 | 8.177 | 7.177 | 10.2655 | 12.2655 | 9.0985 | 16.2755 | 26.541 | 38.8065 | 0.01
3.7875 | 7.8937 | 5.7875 | 4.7875 | 6.6812 | 8.6812 | 7.8937 | 12.6812 | 19.3625 | 28.0437 | 3.7975 | 7.9037 | 5.7875 | 4.7875 | 6.6812 | 8.6812 | 7.9037 | 12.6912 | 19.3725 | 28.0537 | 0.01
5.0807 | 8.5403 | 7.0807 | 6.0807 | 8.621 | 10.621 | 8.5403 | 14.621 | 23.242 | 33.863 | 5.0907 | 8.5503 | 7.0807 | 6.0807 | 8.621 | 10.621 | 8.5503 | 14.631 | 23.252 | 33.873 | 0.01
6.5686 | 9.2843 | 8.5686 | 7.5686 | 10.8529 | 12.8529 | 9.2843 | 16.8529 | 27.7059 | 40.5588 | 6.5786 | 9.2943 | 8.5686 | 7.5686 | 10.8529 | 12.8529 | 9.2943 | 16.8629 | 27.7159 | 40.5688 | 0.01
5.8438 | 8.9219 | 7.8438 | 6.8438 | 9.7658 | 11.7658 | 8.9219 | 15.7658 | 25.5315 | 37.2973 | 5.8538 | 8.9319 | 7.8438 | 6.8438 | 9.7658 | 11.7658 | 8.9319 | 15.7758 | 25.5415 | 37.3073 | 0.01
6.0958 | 9.0479 | 8.0958 | 7.0958 | 10.1438 | 12.1438 | 9.0479 | 16.1438 | 26.2875 | 38.4313 | 6.1058 | 9.0579 | 8.0958 | 7.0958 | 10.1438 | 12.1438 | 9.0579 | 16.1538 | 26.2975 | 38.4413 | 0.01
6.9493 | 9.4746 | 8.9493 | 7.9493 | 11.4239 | 13.4239 | 9.4746 | 17.4239 | 28.8478 | 42.2717 | 6.9593 | 9.4846 | 8.9493 | 7.9493 | 11.4239 | 13.4239 | 9.4846 | 17.4339 | 28.8578 | 42.2817 | 0.01
5.2162 | 8.6081 | 7.2162 | 6.2162 | 8.8242 | 10.8242 | 8.6081 | 14.8242 | 23.6485 | 34.4727 | 5.2262 | 8.6181 | 7.2162 | 6.2162 | 8.8242 | 10.8242 | 8.6181 | 14.8342 | 23.6585 | 34.4827 | 0.01
5.5135 | 8.7568 | 7.5135 | 6.5135 | 9.2703 | 11.2703 | 8.7568 | 15.2703 | 24.5406 | 35.8109 | 5.5235 | 8.7668 | 7.5135 | 6.5135 | 9.2703 | 11.2703 | 8.7668 | 15.2803 | 24.5506 | 35.8209 | 0.01
6.4323 | 9.2162 | 8.4323 | 7.4323 | 10.6485 | 12.6485 | 9.2162 | 16.6485 | 27.2969 | 39.9454 | 6.4423 | 9.2262 | 8.4323 | 7.4323 | 10.6485 | 12.6485 | 9.2262 | 16.6585 | 27.3069 | 39.9554 | 0.01
6.5298 | 9.2649 | 8.5298 | 7.5298 | 10.7947 | 12.7947 | 9.2649 | 16.7947 | 27.5894 | 40.3841 | 6.5398 | 9.2749 | 8.5298 | 7.5298 | 10.7947 | 12.7947 | 9.2749 | 16.8047 | 27.5994 | 40.3941 | 0.01
3.6047 | 7.8023 | 5.6047 | 4.6047 | 6.407 | 8.407 | 7.8023 | 12.407 | 18.814 | 27.221 | 3.6147 | 7.8123 | 5.6047 | 4.6047 | 6.407 | 8.407 | 7.8123 | 12.417 | 18.824 | 27.231 | 0.01
6.5074 | 9.2537 | 8.5074 | 7.5074 | 10.761 | 12.761 | 9.2537 | 16.761 | 27.5221 | 40.2831 | 6.5174 | 9.2637 | 8.5074 | 7.5074 | 10.761 | 12.761 | 9.2637 | 16.771 | 27.5321 | 40.2931 | 0.01
5.3909 | 8.6955 | 7.3909 | 6.3909 | 9.0864 | 11.0864 | 8.6955 | 15.0864 | 24.1728 | 35.2592 | 5.4009 | 8.7055 | 7.3909 | 6.3909 | 9.0864 | 11.0864 | 8.7055 | 15.0964 | 24.1828 | 35.2692 | 0.01
7.3437 | 9.6719 | 9.3437 | 8.3437 | 12.0156 | 14.0156 | 9.6719 | 18.0156 | 30.0312 | 44.0468 | 7.3537 | 9.6819 | 9.3437 | 8.3437 | 12.0156 | 14.0156 | 9.6819 | 18.0256 | 30.0412 | 44.0568 | 0.01
4.6308 | 8.3154 | 6.6308 | 5.6308 | 7.9462 | 9.9462 | 8.3154 | 13.9462 | 21.8924 | 31.8386 | 4.6408 | 8.3254 | 6.6308 | 5.6308 | 7.9462 | 9.9462 | 8.3254 | 13.9562 | 21.9024 | 31.8486 | 0.01
9.6453 | 10.8227 | 11.6453 | 10.6453 | 15.468 | 17.468 | 10.8227 | 21.468 | 36.936 | 54.404 | 9.6553 | 10.8327 | 11.6453 | 10.6453 | 15.468 | 17.468 | 10.8327 | 21.478 | 36.946 | 54.414 | 0.01
6.4225 | 9.2112 | 8.4225 | 7.4225 | 10.6337 | 12.6337 | 9.2112 | 16.6337 | 27.2675 | 39.9012 | 6.4325 | 9.2212 | 8.4225 | 7.4225 | 10.6337 | 12.6337 | 9.2212 | 16.6437 | 27.2775 | 39.9112 | 0.01
5.6668 | 8.8334 | 7.6668 | 6.6668 | 9.5002 | 11.5002 | 8.8334 | 15.5002 | 25.0004 | 36.5007 | 5.6768 | 8.8434 | 7.6668 | 6.6668 | 9.5002 | 11.5002 | 8.8434 | 15.5102 | 25.0104 | 36.5107 | 0.01
6.74 | 9.37 | 8.74 | 7.74 | 11.11 | 13.11 | 9.37 | 17.11 | 28.22 | 41.3301 | 6.75 | 9.38 | 8.74 | 7.74 | 11.11 | 13.11 | 9.38 | 17.12 | 28.23 | 41.3401 | 0.01
9.1685 | 10.5842 | 11.1685 | 10.1685 | 14.7527 | 16.7527 | 10.5842 | 20.7527 | 35.5054 | 52.258 | 9.1785 | 10.5942 | 11.1685 | 10.1685 | 14.7527 | 16.7527 | 10.5942 | 20.7627 | 35.5154 | 52.268 | 0.01
4.3763 | 8.1881 | 6.3763 | 5.3763 | 7.5644 | 9.5644 | 8.1881 | 13.5644 | 21.1288 | 30.6933 | 4.3863 | 8.1981 | 6.3763 | 5.3763 | 7.5644 | 9.5644 | 8.1981 | 13.5744 | 21.1388 | 30.7033 | 0.01
4.1411 | 8.0705 | 6.1411 | 5.1411 | 7.2116 | 9.2116 | 8.0705 | 13.2116 | 20.4233 | 29.6349 | 4.1511 | 8.0805 | 6.1411 | 5.1411 | 7.2116 | 9.2116 | 8.0805 | 13.2216 | 20.4333 | 29.6449 | 0.01
6.171 | 9.0855 | 8.171 | 7.171 | 10.2565 | 12.2565 | 9.0855 | 16.2565 | 26.5131 | 38.7696 | 6.181 | 9.0955 | 8.171 | 7.171 | 10.2565 | 12.2565 | 9.0955 | 16.2665 | 26.5231 | 38.7796 | 0.01
3.8576 | 7.9288 | 5.8576 | 4.8576 | 6.7865 | 8.7865 | 7.9288 | 12.7865 | 19.5729 | 28.3594 | 3.8676 | 7.9388 | 5.8576 | 4.8576 | 6.7865 | 8.7865 | 7.9388 | 12.7965 | 19.5829 | 28.3694 | 0.01
5.1285 | 8.5643 | 7.1285 | 6.1285 | 8.6928 | 10.6928 | 8.5643 | 14.6928 | 23.3855 | 34.0783 | 5.1385 | 8.5743 | 7.1285 | 6.1285 | 8.6928 | 10.6928 | 8.5743 | 14.7028 | 23.3955 | 34.0883 | 0.01
7.0864 | 9.5432 | 9.0864 | 8.0864 | 11.6296 | 13.6296 | 9.5432 | 17.6296 | 29.2592 | 42.8887 | 7.0964 | 9.5532 | 9.0864 | 8.0864 | 11.6296 | 13.6296 | 9.5532 | 17.6396 | 29.2692 | 42.8987 | 0.01
4.1163 | 8.0582 | 6.1163 | 5.1163 | 7.1745 | 9.1745 | 8.0582 | 13.1745 | 20.349 | 29.5235 | 4.1263 | 8.0682 | 6.1163 | 5.1163 | 7.1745 | 9.1745 | 8.0682 | 13.1845 | 20.359 | 29.5335 | 0.01
8.9564 | 10.4782 | 10.9564 | 9.9564 | 14.4346 | 16.4346 | 10.4782 | 20.4346 | 34.8692 | 51.3037 | 8.9664 | 10.4882 | 10.9564 | 9.9564 | 14.4346 | 16.4346 | 10.4882 | 20.4446 | 34.8792 | 51.3137 | 0.01
8.7441 | 10.3721 | 10.7441 | 9.7441 | 14.1162 | 16.1162 | 10.3721 | 20.1162 | 34.2324 | 50.3486 | 8.7541 | 10.3821 | 10.7441 | 9.7441 | 14.1162 | 16.1162 | 10.3821 | 20.1262 | 34.2424 | 50.3586 | 0.01
2.74 | 7.37 | 4.74 | 3.74 | 5.1101 | 7.1101 | 7.37 | 11.1101 | 16.2201 | 23.3302 | 2.75 | 7.38 | 4.74 | 3.74 | 5.1101 | 7.1101 | 7.38 | 11.1201 | 16.2301 | 23.3402 | 0.01
5.7804 | 8.8902 | 7.7804 | 6.7804 | 9.6707 | 11.6707 | 8.8902 | 15.6707 | 25.3413 | 37.012 | 5.7904 | 8.9002 | 7.7804 | 6.7804 | 9.6707 | 11.6707 | 8.9002 | 15.6807 | 25.3513 | 37.022 | 0.01
8.5548 | 10.2774 | 10.5548 | 9.5548 | 13.8321 | 15.8321 | 10.2774 | 19.8321 | 33.6643 | 49.4964 | 8.5648 | 10.2874 | 10.5548 | 9.5548 | 13.8321 | 15.8321 | 10.2874 | 19.8421 | 33.6743 | 49.5064 | 0.01
9.7354 | 10.8677 | 11.7354 | 10.7354 | 15.6031 | 17.6031 | 10.8677 | 21.6031 | 37.2063 | 54.8094 | 9.7454 | 10.8777 | 11.7354 | 10.7354 | 15.6031 | 17.6031 | 10.8777 | 21.6131 | 37.2163 | 54.8194 | 0.01
6.7498 | 9.3749 | 8.7498 | 7.7498 | 11.1247 | 13.1247 | 9.3749 | 17.1247 | 28.2493 | 41.374 | 6.7598 | 9.3849 | 8.7498 | 7.7498 | 11.1247 | 13.1247 | 9.3849 | 17.1347 | 28.2593 | 41.384 | 0.01
5.8147 | 8.9074 | 7.8147 | 6.8147 | 9.7221 | 11.7221 | 8.9074 | 15.7221 | 25.4441 | 37.1662 | 5.8247 | 8.9174 | 7.8147 | 6.8147 | 9.7221 | 11.7221 | 8.9174 | 15.7321 | 25.4541 | 37.1762 | 0.01
4.1528 | 8.0764 | 6.1528 | 5.1528 | 7.2293 | 9.2293 | 8.0764 | 13.2293 | 20.4585 | 29.6878 | 4.1628 | 8.0864 | 6.1528 | 5.1528 | 7.2293 | 9.2293 | 8.0864 | 13.2393 | 20.4685 | 29.6978 | 0.01
3.9873 | 7.9937 | 5.9873 | 4.9873 | 6.981 | 8.981 | 7.9937 | 12.981 | 19.962 | 28.943 | 3.9973 | 8.0037 | 5.9873 | 4.9873 | 6.981 | 8.981 | 8.0037 | 12.991 | 19.972 | 28.953 | 0.01
7.9613 | 9.9807 | 9.9613 | 8.9613 | 12.942 | 14.942 | 9.9807 | 18.942 | 31.8839 | 46.8259 | 7.9713 | 9.9907 | 9.9613 | 8.9613 | 12.942 | 14.942 | 9.9907 | 18.952 | 31.8939 | 46.8359 | 0.01
2.9631 | 7.4816 | 4.9631 | 3.9631 | 5.4447 | 7.4447 | 7.4816 | 11.4447 | 16.8894 | 24.3341 | 2.9731 | 7.4916 | 4.9631 | 3.9631 | 5.4447 | 7.4447 | 7.4916 | 11.4547 | 16.8994 | 24.3441 | 0.01
4.718 | 8.359 | 6.718 | 5.718 | 8.077 | 10.077 | 8.359 | 14.077 | 22.154 | 32.231 | 4.728 | 8.369 | 6.718 | 5.718 | 8.077 | 10.077 | 8.369 | 14.087 | 22.164 | 32.241 | 0.01
6.5567 | 9.2783 | 8.5567 | 7.5567 | 10.835 | 12.835 | 9.2783 | 16.835 | 27.67 | 40.5051 | 6.5667 | 9.2883 | 8.5567 | 7.5567 | 10.835 | 12.835 | 9.2883 | 16.845 | 27.68 | 40.5151 | 0.01
9.2868 | 10.6434 | 11.2868 | 10.2868 | 14.9302 | 16.9302 | 10.6434 | 20.9302 | 35.8604 | 52.7905 | 9.2968 | 10.6534 | 11.2868 | 10.2868 | 14.9302 | 16.9302 | 10.6534 | 20.9402 | 35.8704 | 52.8005 | 0.01
3.6374 | 7.8187 | 5.6374 | 4.6374 | 6.4561 | 8.4561 | 7.8187 | 12.4561 | 18.9123 | 27.3684 | 3.6474 | 7.8287 | 5.6374 | 4.6374 | 6.4561 | 8.4561 | 7.8287 | 12.4661 | 18.9223 | 27.3784 | 0.01
7.1885 | 9.5943 | 9.1885 | 8.1885 | 11.7828 | 13.7828 | 9.5943 | 17.7828 | 29.5656 | 43.3484 | 7.1985 | 9.6043 | 9.1885 | 8.1885 | 11.7828 | 13.7828 | 9.6043 | 17.7928 | 29.5756 | 43.3584 | 0.01
5.7584 | 8.8792 | 7.7584 | 6.7584 | 9.6376 | 11.6376 | 8.8792 | 15.6376 | 25.2751 | 36.9127 | 5.7684 | 8.8892 | 7.7584 | 6.7584 | 9.6376 | 11.6376 | 8.8892 | 15.6476 | 25.2851 | 36.9227 | 0.01
5.6182 | 8.8091 | 7.6182 | 6.6182 | 9.4274 | 11.4274 | 8.8091 | 15.4274 | 24.8547 | 36.2821 | 5.6282 | 8.8191 | 7.6182 | 6.6182 | 9.4274 | 11.4274 | 8.8191 | 15.4374 | 24.8647 | 36.2921 | 0.01
5.3742 | 8.6871 | 7.3742 | 6.3742 | 9.0613 | 11.0613 | 8.6871 | 15.0613 | 24.1225 | 35.1838 | 5.3842 | 8.6971 | 7.3742 | 6.3742 | 9.0613 | 11.0613 | 8.6971 | 15.0713 | 24.1325 | 35.1938 | 0.01
4.0427 | 8.0214 | 6.0427 | 5.0427 | 7.0641 | 9.0641 | 8.0214 | 13.0641 | 20.1282 | 29.1922 | 4.0527 | 8.0314 | 6.0427 | 5.0427 | 7.0641 | 9.0641 | 8.0314 | 13.0741 | 20.1382 | 29.2022 | 0.01
5.0499 | 8.525 | 7.0499 | 6.0499 | 8.5749 | 10.5749 | 8.525 | 14.5749 | 23.1497 | 33.7246 | 5.0599 | 8.535 | 7.0499 | 6.0499 | 8.5749 | 10.5749 | 8.535 | 14.5849 | 23.1597 | 33.7346 | 0.01
4.0014 | 8.0007 | 6.0014 | 5.0014 | 7.002 | 9.002 | 8.0007 | 13.002 | 20.0041 | 29.0061 | 4.0114 | 8.0107 | 6.0014 | 5.0014 | 7.002 | 9.002 | 8.0107 | 13.012 | 20.0141 | 29.0161 | 0.01
4.888 | 8.444 | 6.888 | 5.888 | 8.332 | 10.332 | 8.444 | 14.332 | 22.664 | 32.9959 | 4.898 | 8.454 | 6.888 | 5.888 | 8.332 | 10.332 | 8.454 | 14.342 | 22.674 | 33.0059 | 0.01
9.4534 | 10.7267 | 11.4534 | 10.4534 | 15.18 | 17.18 | 10.7267 | 21.18 | 36.3601 | 53.5401 | 9.4634 | 10.7367 | 11.4534 | 10.4534 | 15.18 | 17.18 | 10.7367 | 21.19 | 36.3701 | 53.5501 | 0.01
4.3719 | 8.186 | 6.3719 | 5.3719 | 7.5579 | 9.5579 | 8.186 | 13.5579 | 21.1157 | 30.6736 | 4.3819 | 8.196 | 6.3719 | 5.3719 | 7.5579 | 9.5579 | 8.196 | 13.5679 | 21.1257 | 30.6836 | 0.01
6.7859 | 9.393 | 8.7859 | 7.7859 | 11.1789 | 13.1789 | 9.393 | 17.1789 | 28.3578 | 41.5367 | 6.7959 | 9.403 | 8.7859 | 7.7859 | 11.1789 | 13.1789 | 9.403 | 17.1889 | 28.3678 | 41.5467 | 0.01
2.921 | 7.4605 | 4.921 | 3.921 | 5.3815 | 7.3815 | 7.4605 | 11.3815 | 16.763 | 24.1445 | 2.931 | 7.4705 | 4.921 | 3.921 | 5.3815 | 7.3815 | 7.4705 | 11.3915 | 16.773 | 24.1545 | 0.01
5.273 | 8.6365 | 7.273 | 6.273 | 8.9094 | 10.9094 | 8.6365 | 14.9094 | 23.8189 | 34.7283 | 5.283 | 8.6465 | 7.273 | 6.273 | 8.9094 | 10.9094 | 8.6465 | 14.9194 | 23.8289 | 34.7383 | 0.01
7.2406 | 9.6203 | 9.2406 | 8.2406 | 11.8609 | 13.8609 | 9.6203 | 17.8609 | 29.7219 | 43.5828 | 7.2506 | 9.6303 | 9.2406 | 8.2406 | 11.8609 | 13.8609 | 9.6303 | 17.8709 | 29.7319 | 43.5928 | 0.01
6.9972 | 9.4986 | 8.9972 | 7.9972 | 11.4958 | 13.4958 | 9.4986 | 17.4958 | 28.9915 | 42.4873 | 7.0072 | 9.5086 | 8.9972 | 7.9972 | 11.4958 | 13.4958 | 9.5086 | 17.5058 | 29.0015 | 42.4973 | 0.01
2.7682 | 7.3841 | 4.7682 | 3.7682 | 5.1523 | 7.1523 | 7.3841 | 11.1523 | 16.3046 | 23.4569 | 2.7782 | 7.3941 | 4.7682 | 3.7682 | 5.1523 | 7.1523 | 7.3941 | 11.1623 | 16.3146 | 23.4669 | 0.01
7.3579 | 9.679 | 9.3579 | 8.3579 | 12.0369 | 14.0369 | 9.679 | 18.0369 | 30.0738 | 44.1108 | 7.3679 | 9.689 | 9.3579 | 8.3579 | 12.0369 | 14.0369 | 9.689 | 18.0469 | 30.0838 | 44.1208 | 0.01
4.0153 | 8.0077 | 6.0153 | 5.0153 | 7.023 | 9.023 | 8.0077 | 13.023 | 20.046 | 29.0691 | 4.0253 | 8.0177 | 6.0153 | 5.0153 | 7.023 | 9.023 | 8.0177 | 13.033 | 20.056 | 29.0791 | 0.01
7.981 | 9.9905 | 9.981 | 8.981 | 12.9716 | 14.9716 | 9.9905 | 18.9716 | 31.9431 | 46.9147 | 7.991 | 10.0005 | 9.981 | 8.981 | 12.9716 | 14.9716 | 10.0005 | 18.9816 | 31.9531 | 46.9247 | 0.01
7.4117 | 9.7058 | 9.4117 | 8.4117 | 12.1175 | 14.1175 | 9.7058 | 18.1175 | 30.2351 | 44.3526 | 7.4217 | 9.7158 | 9.4117 | 8.4117 | 12.1175 | 14.1175 | 9.7158 | 18.1275 | 30.2451 | 44.3626 | 0.01
9.3358 | 10.6679 | 11.3358 | 10.3358 | 15.0036 | 17.0036 | 10.6679 | 21.0036 | 36.0073 | 53.0109 | 9.3458 | 10.6779 | 11.3358 | 10.3358 | 15.0036 | 17.0036 | 10.6779 | 21.0136 | 36.0173 | 53.0209 | 0.01
7.7372 | 9.8686 | 9.7372 | 8.7372 | 12.6059 | 14.6059 | 9.8686 | 18.6059 | 31.2117 | 45.8176 | 7.7472 | 9.8786 | 9.7372 | 8.7372 | 12.6059 | 14.6059 | 9.8786 | 18.6159 | 31.2217 | 45.8276 | 0.01
4.255 | 8.1275 | 6.255 | 5.255 | 7.3826 | 9.3826 | 8.1275 | 13.3826 | 20.7651 | 30.1477 | 4.265 | 8.1375 | 6.255 | 5.255 | 7.3826 | 9.3826 | 8.1375 | 13.3926 | 20.7751 | 30.1577 | 0.01
3.1525 | 7.5763 | 5.1525 | 4.1525 | 5.7288 | 7.7288 | 7.5763 | 11.7288 | 17.4576 | 25.1864 | 3.1625 | 7.5863 | 5.1525 | 4.1525 | 5.7288 | 7.7288 | 7.5863 | 11.7388 | 17.4676 | 25.1964 | 0.01
6.2043 | 9.1021 | 8.2043 | 7.2043 | 10.3064 | 12.3064 | 9.1021 | 16.3064 | 26.6128 | 38.9192 | 6.2143 | 9.1121 | 8.2043 | 7.2043 | 10.3064 | 12.3064 | 9.1121 | 16.3164 | 26.6228 | 38.9292 | 0.01
3.9566 | 7.9783 | 5.9566 | 4.9566 | 6.9349 | 8.9349 | 7.9783 | 12.9349 | 19.8699 | 28.8048 | 3.9666 | 7.9883 | 5.9566 | 4.9566 | 6.9349 | 8.9349 | 7.9883 | 12.9449 | 19.8799 | 28.8148 | 0.01
4.8382 | 8.4191 | 6.8382 | 5.8382 | 8.2573 | 10.2573 | 8.4191 | 14.2573 | 22.5146 | 32.7718 | 4.8482 | 8.4291 | 6.8382 | 5.8382 | 8.2573 | 10.2573 | 8.4291 | 14.2673 | 22.5246 | 32.7818 | 0.01
8.832 | 10.416 | 10.832 | 9.832 | 14.248 | 16.248 | 10.416 | 20.248 | 34.496 | 50.744 | 8.842 | 10.426 | 10.832 | 9.832 | 14.248 | 16.248 | 10.426 | 20.258 | 34.506 | 50.754 | 0.01
6.1256 | 9.0628 | 8.1256 | 7.1256 | 10.1883 | 12.1883 | 9.0628 | 16.1883 | 26.3767 | 38.565 | 6.1356 | 9.0728 | 8.1256 | 7.1256 | 10.1883 | 12.1883 | 9.0728 | 16.1983 | 26.3867 | 38.575 | 0.01
3.7788 | 7.8894 | 5.7788 | 4.7788 | 6.6682 | 8.6682 | 7.8894 | 12.6682 | 19.3364 | 28.0046 | 3.7888 | 7.8994 | 5.7788 | 4.7788 | 6.6682 | 8.6682 | 7.8994 | 12.6782 | 19.3464 | 28.0146 | 0.01
6.2079 | 9.1039 | 8.2079 | 7.2079 | 10.3118 | 12.3118 | 9.1039 | 16.3118 | 26.6236 | 38.9354 | 6.2179 | 9.1139 | 8.2079 | 7.2079 | 10.3118 | 12.3118 | 9.1139 | 16.3218 | 26.6336 | 38.9454 | 0.01
3.5199 | 7.7599 | 5.5199 | 4.5199 | 6.2798 | 8.2798 | 7.7599 | 12.2798 | 18.5596 | 26.8395 | 3.5299 | 7.7699 | 5.5199 | 4.5199 | 6.2798 | 8.2798 | 7.7699 | 12.2898 | 18.5696 | 26.8495 | 0.01
5.2902 | 8.6451 | 7.2902 | 6.2902 | 8.9353 | 10.9353 | 8.6451 | 14.9353 | 23.8707 | 34.806 | 5.3002 | 8.6551 | 7.2902 | 6.2902 | 8.9353 | 10.9353 | 8.6551 | 14.9453 | 23.8807 | 34.816 | 0.01
0.22536 | 6.1127 | 2.2254 | 1.2254 | 1.338 | 3.338 | 6.1127 | 7.338 | 8.6761 | 12.0141 | 0.23536 | 6.1227 | 2.2254 | 1.2254 | 1.338 | 3.338 | 6.1227 | 7.348 | 8.6861 | 12.0241 | 0.01
6.7913 | 9.3957 | 8.7913 | 7.7913 | 11.187 | 13.187 | 9.3957 | 17.187 | 28.374 | 41.5611 | 6.8013 | 9.4057 | 8.7913 | 7.7913 | 11.187 | 13.187 | 9.4057 | 17.197 | 28.384 | 41.5711 | 0.01
8.3235 | 10.1617 | 10.3235 | 9.3235 | 13.4852 | 15.4852 | 10.1617 | 19.4852 | 32.9704 | 48.4556 | 8.3335 | 10.1717 | 10.3235 | 9.3235 | 13.4852 | 15.4852 | 10.1717 | 19.4952 | 32.9804 | 48.4656 | 0.01
4.5906 | 8.2953 | 6.5906 | 5.5906 | 7.886 | 9.886 | 8.2953 | 13.886 | 21.7719 | 31.6579 | 4.6006 | 8.3053 | 6.5906 | 5.5906 | 7.886 | 9.886 | 8.3053 | 13.896 | 21.7819 | 31.6679 | 0.01
3.9131 | 7.9566 | 5.9131 | 4.9131 | 6.8697 | 8.8697 | 7.9566 | 12.8697 | 19.7394 | 28.609 | 3.9231 | 7.9666 | 5.9131 | 4.9131 | 6.8697 | 8.8697 | 7.9666 | 12.8797 | 19.7494 | 28.619 | 0.01
6.9782 | 9.4891 | 8.9782 | 7.9782 | 11.4673 | 13.4673 | 9.4891 | 17.4673 | 28.9346 | 42.4018 | 6.9882 | 9.4991 | 8.9782 | 7.9782 | 11.4673 | 13.4673 | 9.4991 | 17.4773 | 28.9446 | 42.4118 | 0.01
6.9963 | 9.4981 | 8.9963 | 7.9963 | 11.4944 | 13.4944 | 9.4981 | 17.4944 | 28.9889 | 42.4833 | 7.0063 | 9.5081 | 8.9963 | 7.9963 | 11.4944 | 13.4944 | 9.5081 | 17.5044 | 28.9989 | 42.4933 | 0.01
5.7612 | 8.8806 | 7.7612 | 6.7612 | 9.6418 | 11.6418 | 8.8806 | 15.6418 | 25.2835 | 36.9253 | 5.7712 | 8.8906 | 7.7612 | 6.7612 | 9.6418 | 11.6418 | 8.8906 | 15.6518 | 25.2935 | 36.9353 | 0.01
7.1508 | 9.5754 | 9.1508 | 8.1508 | 11.7262 | 13.7262 | 9.5754 | 17.7262 | 29.4524 | 43.1786 | 7.1608 | 9.5854 | 9.1508 | 8.1508 | 11.7262 | 13.7262 | 9.5854 | 17.7362 | 29.4624 | 43.1886 | 0.01
8.0391 | 10.0196 | 10.0391 | 9.0391 | 13.0587 | 15.0587 | 10.0196 | 19.0587 | 32.1174 | 47.1761 | 8.0491 | 10.0296 | 10.0391 | 9.0391 | 13.0587 | 15.0587 | 10.0296 | 19.0687 | 32.1274 | 47.1861 | 0.01
4.834 | 8.417 | 6.834 | 5.834 | 8.2511 | 10.2511 | 8.417 | 14.2511 | 22.5021 | 32.7532 | 4.844 | 8.427 | 6.834 | 5.834 | 8.2511 | 10.2511 | 8.427 | 14.2611 | 22.5121 | 32.7632 | 0.01
4.3051 | 8.1526 | 6.3051 | 5.3051 | 7.4577 | 9.4577 | 8.1526 | 13.4577 | 20.9154 | 30.3731 | 4.3151 | 8.1626 | 6.3051 | 5.3051 | 7.4577 | 9.4577 | 8.1626 | 13.4677 | 20.9254 | 30.3831 | 0.01
3.4266 | 7.7133 | 5.4266 | 4.4266 | 6.1399 | 8.1399 | 7.7133 | 12.1399 | 18.2798 | 26.4198 | 3.4366 | 7.7233 | 5.4266 | 4.4266 | 6.1399 | 8.1399 | 7.7233 | 12.1499 | 18.2898 | 26.4298 | 0.01
6.4406 | 9.2203 | 8.4406 | 7.4406 | 10.6608 | 12.6608 | 9.2203 | 16.6608 | 27.3217 | 39.9825 | 6.4506 | 9.2303 | 8.4406 | 7.4406 | 10.6608 | 12.6608 | 9.2303 | 16.6708 | 27.3317 | 39.9925 | 0.01
6.6586 | 9.3293 | 8.6586 | 7.6586 | 10.9878 | 12.9878 | 9.3293 | 16.9878 | 27.9757 | 40.9635 | 6.6686 | 9.3393 | 8.6586 | 7.6586 | 10.9878 | 12.9878 | 9.3393 | 16.9978 | 27.9857 | 40.9735 | 0.01
3.0639 | 7.532 | 5.0639 | 4.0639 | 5.5959 | 7.5959 | 7.532 | 11.5959 | 17.1918 | 24.7877 | 3.0739 | 7.542 | 5.0639 | 4.0639 | 5.5959 | 7.5959 | 7.542 | 11.6059 | 17.2018 | 24.7977 | 0.01
3.5654 | 7.7827 | 5.5654 | 4.5654 | 6.3482 | 8.3482 | 7.7827 | 12.3482 | 18.6963 | 27.0445 | 3.5754 | 7.7927 | 5.5654 | 4.5654 | 6.3482 | 8.3482 | 7.7927 | 12.3582 | 18.7063 | 27.0545 | 0.01
4.057 | 8.0285 | 6.057 | 5.057 | 7.0855 | 9.0855 | 8.0285 | 13.0855 | 20.1709 | 29.2564 | 4.067 | 8.0385 | 6.057 | 5.057 | 7.0855 | 9.0855 | 8.0385 | 13.0955 | 20.1809 | 29.2664 | 0.01
1.4505 | 6.7252 | 3.4505 | 2.4505 | 3.1757 | 5.1757 | 6.7252 | 9.1757 | 12.3514 | 17.527 | 1.4605 | 6.7352 | 3.4505 | 2.4505 | 3.1757 | 5.1757 | 6.7352 | 9.1857 | 12.3614 | 17.537 | 0.01
6.5149 | 9.2574 | 8.5149 | 7.5149 | 10.7723 | 12.7723 | 9.2574 | 16.7723 | 27.5446 | 40.3169 | 6.5249 | 9.2674 | 8.5149 | 7.5149 | 10.7723 | 12.7723 | 9.2674 | 16.7823 | 27.5546 | 40.3269 | 0.01
7.2334 | 9.6167 | 9.2334 | 8.2334 | 11.8501 | 13.8501 | 9.6167 | 17.8501 | 29.7001 | 43.5502 | 7.2434 | 9.6267 | 9.2334 | 8.2334 | 11.8501 | 13.8501 | 9.6267 | 17.8601 | 29.7101 | 43.5602 | 0.01
6.6848 | 9.3424 | 8.6848 | 7.6848 | 11.0272 | 13.0272 | 9.3424 | 17.0272 | 28.0543 | 41.0815 | 6.6948 | 9.3524 | 8.6848 | 7.6848 | 11.0272 | 13.0272 | 9.3524 | 17.0372 | 28.0643 | 41.0915 | 0.01
3.5748 | 7.7874 | 5.5748 | 4.5748 | 6.3623 | 8.3623 | 7.7874 | 12.3623 | 18.7245 | 27.0868 | 3.5848 | 7.7974 | 5.5748 | 4.5748 | 6.3623 | 8.3623 | 7.7974 | 12.3723 | 18.7345 | 27.0968 | 0.01
4.5511 | 8.2755 | 6.5511 | 5.5511 | 7.8266 | 9.8266 | 8.2755 | 13.8266 | 21.6532 | 31.4798 | 4.5611 | 8.2855 | 6.5511 | 5.5511 | 7.8266 | 9.8266 | 8.2855 | 13.8366 | 21.6632 | 31.4898 | 0.01
5.3338 | 8.6669 | 7.3338 | 6.3338 | 9.0007 | 11.0007 | 8.6669 | 15.0007 | 24.0014 | 35.0022 | 5.3438 | 8.6769 | 7.3338 | 6.3338 | 9.0007 | 11.0007 | 8.6769 | 15.0107 | 24.0114 | 35.0122 | 0.01
7.2404 | 9.6202 | 9.2404 | 8.2404 | 11.8606 | 13.8606 | 9.6202 | 17.8606 | 29.7211 | 43.5817 | 7.2504 | 9.6302 | 9.2404 | 8.2404 | 11.8606 | 13.8606 | 9.6302 | 17.8706 | 29.7311 | 43.5917 | 0.01
10.1468 | 11.0734 | 12.1468 | 11.1468 | 16.2203 | 18.2203 | 11.0734 | 22.2203 | 38.4405 | 56.6608 | 10.1568 | 11.0834 | 12.1468 | 11.1468 | 16.2203 | 18.2203 | 11.0834 | 22.2303 | 38.4505 | 56.6708 | 0.01
6.2529 | 9.1264 | 8.2529 | 7.2529 | 10.3793 | 12.3793 | 9.1264 | 16.3793 | 26.7586 | 39.1379 | 6.2629 | 9.1364 | 8.2529 | 7.2529 | 10.3793 | 12.3793 | 9.1364 | 16.3893 | 26.7686 | 39.1479 | 0.01
9.755 | 10.8775 | 11.755 | 10.755 | 15.6326 | 17.6326 | 10.8775 | 21.6326 | 37.2651 | 54.8977 | 9.765 | 10.8875 | 11.755 | 10.755 | 15.6326 | 17.6326 | 10.8875 | 21.6426 | 37.2751 | 54.9077 | 0.01
2.6007 | 7.3004 | 4.6007 | 3.6007 | 4.9011 | 6.9011 | 7.3004 | 10.9011 | 15.8022 | 22.7034 | 2.6107 | 7.3104 | 4.6007 | 3.6007 | 4.9011 | 6.9011 | 7.3104 | 10.9111 | 15.8122 | 22.7134 | 0.01
6.491 | 9.2455 | 8.491 | 7.491 | 10.7365 | 12.7365 | 9.2455 | 16.7365 | 27.4729 | 40.2094 | 6.501 | 9.2555 | 8.491 | 7.491 | 10.7365 | 12.7365 | 9.2555 | 16.7465 | 27.4829 | 40.2194 | 0.01
3.7051 | 7.8525 | 5.7051 | 4.7051 | 6.5576 | 8.5576 | 7.8525 | 12.5576 | 19.1153 | 27.6729 | 3.7151 | 7.8625 | 5.7051 | 4.7051 | 6.5576 | 8.5576 | 7.8625 | 12.5676 | 19.1253 | 27.6829 | 0.01
8.8596 | 10.4298 | 10.8596 | 9.8596 | 14.2894 | 16.2894 | 10.4298 | 20.2894 | 34.5788 | 50.8682 | 8.8696 | 10.4398 | 10.8596 | 9.8596 | 14.2894 | 16.2894 | 10.4398 | 20.2994 | 34.5888 | 50.8782 | 0.01
4.0418 | 8.0209 | 6.0418 | 5.0418 | 7.0627 | 9.0627 | 8.0209 | 13.0627 | 20.1254 | 29.1881 | 4.0518 | 8.0309 | 6.0418 | 5.0418 | 7.0627 | 9.0627 | 8.0309 | 13.0727 | 20.1354 | 29.1981 | 0.01
5.4082 | 8.7041 | 7.4082 | 6.4082 | 9.1122 | 11.1122 | 8.7041 | 15.1122 | 24.2245 | 35.3367 | 5.4182 | 8.7141 | 7.4082 | 6.4082 | 9.1122 | 11.1122 | 8.7141 | 15.1222 | 24.2345 | 35.3467 | 0.01
9.0073 | 10.5036 | 11.0073 | 10.0073 | 14.5109 | 16.5109 | 10.5036 | 20.5109 | 35.0219 | 51.5328 | 9.0173 | 10.5136 | 11.0073 | 10.0073 | 14.5109 | 16.5109 | 10.5136 | 20.5209 | 35.0319 | 51.5428 | 0.01
3.2126 | 7.6063 | 5.2126 | 4.2126 | 5.8188 | 7.8188 | 7.6063 | 11.8188 | 17.6377 | 25.4565 | 3.2226 | 7.6163 | 5.2126 | 4.2126 | 5.8188 | 7.8188 | 7.6163 | 11.8288 | 17.6477 | 25.4665 | 0.01
3.8567 | 7.9284 | 5.8567 | 4.8567 | 6.7851 | 8.7851 | 7.9284 | 12.7851 | 19.5702 | 28.3553 | 3.8667 | 7.9384 | 5.8567 | 4.8567 | 6.7851 | 8.7851 | 7.9384 | 12.7951 | 19.5802 | 28.3653 | 0.01
6.5668 | 9.2834 | 8.5668 | 7.5668 | 10.8501 | 12.8501 | 9.2834 | 16.8501 | 27.7003 | 40.5504 | 6.5768 | 9.2934 | 8.5668 | 7.5668 | 10.8501 | 12.8501 | 9.2934 | 16.8601 | 27.7103 | 40.5604 | 0.01
5.6779 | 8.839 | 7.6779 | 6.6779 | 9.5169 | 11.5169 | 8.839 | 15.5169 | 25.0337 | 36.5506 | 5.6879 | 8.849 | 7.6779 | 6.6779 | 9.5169 | 11.5169 | 8.849 | 15.5269 | 25.0437 | 36.5606 | 0.01
5.0931 | 8.5465 | 7.0931 | 6.0931 | 8.6396 | 10.6396 | 8.5465 | 14.6396 | 23.2793 | 33.9189 | 5.1031 | 8.5565 | 7.0931 | 6.0931 | 8.6396 | 10.6396 | 8.5565 | 14.6496 | 23.2893 | 33.9289 | 0.01
3.8637 | 7.9319 | 5.8637 | 4.8637 | 6.7956 | 8.7956 | 7.9319 | 12.7956 | 19.5912 | 28.3868 | 3.8737 | 7.9419 | 5.8637 | 4.8637 | 6.7956 | 8.7956 | 7.9419 | 12.8056 | 19.6012 | 28.3968 | 0.01
8.1234 | 10.0617 | 10.1234 | 9.1234 | 13.1851 | 15.1851 | 10.0617 | 19.1851 | 32.3703 | 47.5554 | 8.1334 | 10.0717 | 10.1234 | 9.1234 | 13.1851 | 15.1851 | 10.0717 | 19.1951 | 32.3803 | 47.5654 | 0.01
7.0773 | 9.5386 | 9.0773 | 8.0773 | 11.6159 | 13.6159 | 9.5386 | 17.6159 | 29.2318 | 42.8477 | 7.0873 | 9.5486 | 9.0773 | 8.0773 | 11.6159 | 13.6159 | 9.5486 | 17.6259 | 29.2418 | 42.8577 | 0.01
7.3068 | 9.6534 | 9.3068 | 8.3068 | 11.9602 | 13.9602 | 9.6534 | 17.9602 | 29.9205 | 43.8807 | 7.3168 | 9.6634 | 9.3068 | 8.3068 | 11.9602 | 13.9602 | 9.6634 | 17.9702 | 29.9305 | 43.8907 | 0.01
8.2874 | 10.1437 | 10.2874 | 9.2874 | 13.4311 | 15.4311 | 10.1437 | 19.4311 | 32.8623 | 48.2934 | 8.2974 | 10.1537 | 10.2874 | 9.2874 | 13.4311 | 15.4311 | 10.1537 | 19.4411 | 32.8723 | 48.3034 | 0.01
3.1034 | 7.5517 | 5.1034 | 4.1034 | 5.6551 | 7.6551 | 7.5517 | 11.6551 | 17.3102 | 24.9653 | 3.1134 | 7.5617 | 5.1034 | 4.1034 | 5.6551 | 7.6551 | 7.5617 | 11.6651 | 17.3202 | 24.9753 | 0.01
7.6587 | 9.8293 | 9.6587 | 8.6587 | 12.488 | 14.488 | 9.8293 | 18.488 | 30.976 | 45.464 | 7.6687 | 9.8393 | 9.6587 | 8.6587 | 12.488 | 14.488 | 9.8393 | 18.498 | 30.986 | 45.474 | 0.01
6.0628 | 9.0314 | 8.0628 | 7.0628 | 10.0943 | 12.0943 | 9.0314 | 16.0943 | 26.1885 | 38.2828 | 6.0728 | 9.0414 | 8.0628 | 7.0628 | 10.0943 | 12.0943 | 9.0414 | 16.1043 | 26.1985 | 38.2928 | 0.01
3.9967 | 7.9984 | 5.9967 | 4.9967 | 6.9951 | 8.9951 | 7.9984 | 12.9951 | 19.9902 | 28.9853 | 4.0067 | 8.0084 | 5.9967 | 4.9967 | 6.9951 | 8.9951 | 8.0084 | 13.0051 | 20.0002 | 28.9953 | 0.01
8.4404 | 10.2202 | 10.4404 | 9.4404 | 13.6606 | 15.6606 | 10.2202 | 19.6606 | 33.3212 | 48.9817 | 8.4504 | 10.2302 | 10.4404 | 9.4404 | 13.6606 | 15.6606 | 10.2302 | 19.6706 | 33.3312 | 48.9917 | 0.01
3.7597 | 7.8798 | 5.7597 | 4.7597 | 6.6395 | 8.6395 | 7.8798 | 12.6395 | 19.279 | 27.9185 | 3.7697 | 7.8898 | 5.7597 | 4.7597 | 6.6395 | 8.6395 | 7.8898 | 12.6495 | 19.289 | 27.9285 | 0.01
3.6668 | 7.8334 | 5.6668 | 4.6668 | 6.5002 | 8.5002 | 7.8334 | 12.5002 | 19.0005 | 27.5007 | 3.6768 | 7.8434 | 5.6668 | 4.6668 | 6.5002 | 8.5002 | 7.8434 | 12.5102 | 19.0105 | 27.5107 | 0.01
4.5056 | 8.2528 | 6.5056 | 5.5056 | 7.7584 | 9.7584 | 8.2528 | 13.7584 | 21.5168 | 31.2752 | 4.5156 | 8.2628 | 6.5056 | 5.5056 | 7.7584 | 9.7584 | 8.2628 | 13.7684 | 21.5268 | 31.2852 | 0.01
3.8066 | 7.9033 | 5.8066 | 4.8066 | 6.7098 | 8.7098 | 7.9033 | 12.7098 | 19.4197 | 28.1295 | 3.8166 | 7.9133 | 5.8066 | 4.8066 | 6.7098 | 8.7098 | 7.9133 | 12.7198 | 19.4297 | 28.1395 | 0.01
4.057 | 8.0285 | 6.057 | 5.057 | 7.0856 | 9.0856 | 8.0285 | 13.0856 | 20.1711 | 29.2567 | 4.067 | 8.0385 | 6.057 | 5.057 | 7.0856 | 9.0856 | 8.0385 | 13.0956 | 20.1811 | 29.2667 | 0.01
4.0248 | 8.0124 | 6.0248 | 5.0248 | 7.0372 | 9.0372 | 8.0124 | 13.0372 | 20.0743 | 29.1115 | 4.0348 | 8.0224 | 6.0248 | 5.0248 | 7.0372 | 9.0372 | 8.0224 | 13.0472 | 20.0843 | 29.1215 | 0.01
4.3617 | 8.1808 | 6.3617 | 5.3617 | 7.5425 | 9.5425 | 8.1808 | 13.5425 | 21.085 | 30.6275 | 4.3717 | 8.1908 | 6.3617 | 5.3617 | 7.5425 | 9.5425 | 8.1908 | 13.5525 | 21.095 | 30.6375 | 0.01
2.9596 | 7.4798 | 4.9596 | 3.9596 | 5.4394 | 7.4394 | 7.4798 | 11.4394 | 16.8788 | 24.3181 | 2.9696 | 7.4898 | 4.9596 | 3.9596 | 5.4394 | 7.4394 | 7.4898 | 11.4494 | 16.8888 | 24.3281 | 0.01
6.0298 | 9.0149 | 8.0298 | 7.0298 | 10.0448 | 12.0448 | 9.0149 | 16.0448 | 26.0895 | 38.1343 | 6.0398 | 9.0249 | 8.0298 | 7.0298 | 10.0448 | 12.0448 | 9.0249 | 16.0548 | 26.0995 | 38.1443 | 0.01
6.0714 | 9.0357 | 8.0714 | 7.0714 | 10.1071 | 12.1071 | 9.0357 | 16.1071 | 26.2141 | 38.3212 | 6.0814 | 9.0457 | 8.0714 | 7.0714 | 10.1071 | 12.1071 | 9.0457 | 16.1171 | 26.2241 | 38.3312 | 0.01
7.1541 | 9.5771 | 9.1541 | 8.1541 | 11.7312 | 13.7312 | 9.5771 | 17.7312 | 29.4624 | 43.1936 | 7.1641 | 9.5871 | 9.1541 | 8.1541 | 11.7312 | 13.7312 | 9.5871 | 17.7412 | 29.4724 | 43.2036 | 0.01
4.933 | 8.4665 | 6.933 | 5.933 | 8.3996 | 10.3996 | 8.4665 | 14.3996 | 22.7991 | 33.1987 | 4.943 | 8.4765 | 6.933 | 5.933 | 8.3996 | 10.3996 | 8.4765 | 14.4096 | 22.8091 | 33.2087 | 0.01
4.1916 | 8.0958 | 6.1916 | 5.1916 | 7.2874 | 9.2874 | 8.0958 | 13.2874 | 20.5748 | 29.8621 | 4.2016 | 8.1058 | 6.1916 | 5.1916 | 7.2874 | 9.2874 | 8.1058 | 13.2974 | 20.5848 | 29.8721 | 0.01
7.147 | 9.5735 | 9.147 | 8.147 | 11.7205 | 13.7205 | 9.5735 | 17.7205 | 29.4411 | 43.1616 | 7.157 | 9.5835 | 9.147 | 8.147 | 11.7205 | 13.7205 | 9.5835 | 17.7305 | 29.4511 | 43.1716 | 0.01
3.5581 | 7.7791 | 5.5581 | 4.5581 | 6.3372 | 8.3372 | 7.7791 | 12.3372 | 18.6744 | 27.0116 | 3.5681 | 7.7891 | 5.5581 | 4.5581 | 6.3372 | 8.3372 | 7.7891 | 12.3472 | 18.6844 | 27.0216 | 0.01
6.1262 | 9.0631 | 8.1262 | 7.1262 | 10.1893 | 12.1893 | 9.0631 | 16.1893 | 26.3785 | 38.5678 | 6.1362 | 9.0731 | 8.1262 | 7.1262 | 10.1893 | 12.1893 | 9.0731 | 16.1993 | 26.3885 | 38.5778 | 0.01
4.3383 | 8.1692 | 6.3383 | 5.3383 | 7.5075 | 9.5075 | 8.1692 | 13.5075 | 21.0149 | 30.5224 | 4.3483 | 8.1792 | 6.3383 | 5.3383 | 7.5075 | 9.5075 | 8.1792 | 13.5175 | 21.0249 | 30.5324 | 0.01
5.0357 | 8.5178 | 7.0357 | 6.0357 | 8.5535 | 10.5535 | 8.5178 | 14.5535 | 23.1071 | 33.6606 | 5.0457 | 8.5278 | 7.0357 | 6.0357 | 8.5535 | 10.5535 | 8.5278 | 14.5635 | 23.1171 | 33.6706 | 0.01
6.8694 | 9.4347 | 8.8694 | 7.8694 | 11.3041 | 13.3041 | 9.4347 | 17.3041 | 28.6083 | 41.9124 | 6.8794 | 9.4447 | 8.8694 | 7.8694 | 11.3041 | 13.3041 | 9.4447 | 17.3141 | 28.6183 | 41.9224 | 0.01
1.534 | 6.767 | 3.534 | 2.534 | 3.301 | 5.301 | 6.767 | 9.301 | 12.6021 | 17.9031 | 1.544 | 6.777 | 3.534 | 2.534 | 3.301 | 5.301 | 6.777 | 9.311 | 12.6121 | 17.9131 | 0.01
7.0464 | 9.5232 | 9.0464 | 8.0464 | 11.5695 | 13.5695 | 9.5232 | 17.5695 | 29.1391 | 42.7086 | 7.0564 | 9.5332 | 9.0464 | 8.0464 | 11.5695 | 13.5695 | 9.5332 | 17.5795 | 29.1491 | 42.7186 | 0.01
7.3728 | 9.6864 | 9.3728 | 8.3728 | 12.0592 | 14.0592 | 9.6864 | 18.0592 | 30.1185 | 44.1777 | 7.3828 | 9.6964 | 9.3728 | 8.3728 | 12.0592 | 14.0592 | 9.6964 | 18.0692 | 30.1285 | 44.1877 | 0.01
6.9632 | 9.4816 | 8.9632 | 7.9632 | 11.4448 | 13.4448 | 9.4816 | 17.4448 | 28.8895 | 42.3343 | 6.9732 | 9.4916 | 8.9632 | 7.9632 | 11.4448 | 13.4448 | 9.4916 | 17.4548 | 28.8995 | 42.3443 | 0.01
10.0391 | 11.0196 | 12.0391 | 11.0391 | 16.0587 | 18.0587 | 11.0196 | 22.0587 | 38.1174 | 56.176 | 10.0491 | 11.0296 | 12.0391 | 11.0391 | 16.0587 | 18.0587 | 11.0296 | 22.0687 | 38.1274 | 56.186 | 0.01
2.6093 | 7.3047 | 4.6093 | 3.6093 | 4.914 | 6.914 | 7.3047 | 10.914 | 15.828 | 22.742 | 2.6193 | 7.3147 | 4.6093 | 3.6093 | 4.914 | 6.914 | 7.3147 | 10.924 | 15.838 | 22.752 | 0.01
5.5955 | 8.7978 | 7.5955 | 6.5955 | 9.3933 | 11.3933 | 8.7978 | 15.3933 | 24.7866 | 36.1798 | 5.6055 | 8.8078 | 7.5955 | 6.5955 | 9.3933 | 11.3933 | 8.8078 | 15.4033 | 24.7966 | 36.1898 | 0.01
6.8506 | 9.4253 | 8.8506 | 7.8506 | 11.2759 | 13.2759 | 9.4253 | 17.2759 | 28.5519 | 41.8278 | 6.8606 | 9.4353 | 8.8506 | 7.8506 | 11.2759 | 13.2759 | 9.4353 | 17.2859 | 28.5619 | 41.8378 | 0.01
6.2706 | 9.1353 | 8.2706 | 7.2706 | 10.4059 | 12.4059 | 9.1353 | 16.4059 | 26.8119 | 39.2178 | 6.2806 | 9.1453 | 8.2706 | 7.2706 | 10.4059 | 12.4059 | 9.1453 | 16.4159 | 26.8219 | 39.2278 | 0.01
1.3749 | 6.6874 | 3.3749 | 2.3749 | 3.0623 | 5.0623 | 6.6874 | 9.0623 | 12.1246 | 17.1869 | 1.3849 | 6.6974 | 3.3749 | 2.3749 | 3.0623 | 5.0623 | 6.6974 | 9.0723 | 12.1346 | 17.1969 | 0.01
5.1584 | 8.5792 | 7.1584 | 6.1584 | 8.7376 | 10.7376 | 8.5792 | 14.7376 | 23.4751 | 34.2127 | 5.1684 | 8.5892 | 7.1584 | 6.1584 | 8.7376 | 10.7376 | 8.5892 | 14.7476 | 23.4851 | 34.2227 | 0.01
2.6899 | 7.345 | 4.6899 | 3.6899 | 5.0349 | 7.0349 | 7.345 | 11.0349 | 16.0697 | 23.1046 | 2.6999 | 7.355 | 4.6899 | 3.6899 | 5.0349 | 7.0349 | 7.355 | 11.0449 | 16.0797 | 23.1146 | 0.01
7.8723 | 9.9362 | 9.8723 | 8.8723 | 12.8085 | 14.8085 | 9.9362 | 18.8085 | 31.6169 | 46.4254 | 7.8823 | 9.9462 | 9.8723 | 8.8723 | 12.8085 | 14.8085 | 9.9462 | 18.8185 | 31.6269 | 46.4354 | 0.01
6.2022 | 9.1011 | 8.2022 | 7.2022 | 10.3034 | 12.3034 | 9.1011 | 16.3034 | 26.6067 | 38.9101 | 6.2122 | 9.1111 | 8.2022 | 7.2022 | 10.3034 | 12.3034 | 9.1111 | 16.3134 | 26.6167 | 38.9201 | 0.01
5.2262 | 8.6131 | 7.2262 | 6.2262 | 8.8394 | 10.8394 | 8.6131 | 14.8394 | 23.6787 | 34.5181 | 5.2362 | 8.6231 | 7.2262 | 6.2262 | 8.8394 | 10.8394 | 8.6231 | 14.8494 | 23.6887 | 34.5281 | 0.01
7.3341 | 9.667 | 9.3341 | 8.3341 | 12.0011 | 14.0011 | 9.667 | 18.0011 | 30.0022 | 44.0033 | 7.3441 | 9.677 | 9.3341 | 8.3341 | 12.0011 | 14.0011 | 9.677 | 18.0111 | 30.0122 | 44.0133 | 0.01
4.9525 | 8.4763 | 6.9525 | 5.9525 | 8.4288 | 10.4288 | 8.4763 | 14.4288 | 22.8576 | 33.2864 | 4.9625 | 8.4863 | 6.9525 | 5.9525 | 8.4288 | 10.4288 | 8.4863 | 14.4388 | 22.8676 | 33.2964 | 0.01
2.0881 | 7.0441 | 4.0881 | 3.0881 | 4.1322 | 6.1322 | 7.0441 | 10.1322 | 14.2644 | 20.3966 | 2.0981 | 7.0541 | 4.0881 | 3.0881 | 4.1322 | 6.1322 | 7.0541 | 10.1422 | 14.2744 | 20.4066 | 0.01
3.9195 | 7.9597 | 5.9195 | 4.9195 | 6.8792 | 8.8792 | 7.9597 | 12.8792 | 19.7585 | 28.6377 | 3.9295 | 7.9697 | 5.9195 | 4.9195 | 6.8792 | 8.8792 | 7.9697 | 12.8892 | 19.7685 | 28.6477 | 0.01
3.6272 | 7.8136 | 5.6272 | 4.6272 | 6.4408 | 8.4408 | 7.8136 | 12.4408 | 18.8816 | 27.3224 | 3.6372 | 7.8236 | 5.6272 | 4.6272 | 6.4408 | 8.4408 | 7.8236 | 12.4508 | 18.8916 | 27.3324 | 0.01
7.2947 | 9.6474 | 9.2947 | 8.2947 | 11.9421 | 13.9421 | 9.6474 | 17.9421 | 29.8841 | 43.8262 | 7.3047 | 9.6574 | 9.2947 | 8.2947 | 11.9421 | 13.9421 | 9.6574 | 17.9521 | 29.8941 | 43.8362 | 0.01
2.1455 | 7.0728 | 4.1455 | 3.1455 | 4.2183 | 6.2183 | 7.0728 | 10.2183 | 14.4366 | 20.6549 | 2.1555 | 7.0828 | 4.1455 | 3.1455 | 4.2183 | 6.2183 | 7.0828 | 10.2283 | 14.4466 | 20.6649 | 0.01
5.3279 | 8.6639 | 7.3279 | 6.3279 | 8.9918 | 10.9918 | 8.6639 | 14.9918 | 23.9837 | 34.9755 | 5.3379 | 8.6739 | 7.3279 | 6.3279 | 8.9918 | 10.9918 | 8.6739 | 15.0018 | 23.9937 | 34.9855 | 0.01
9.3314 | 10.6657 | 11.3314 | 10.3314 | 14.9971 | 16.9971 | 10.6657 | 20.9971 | 35.9941 | 52.9912 | 9.3414 | 10.6757 | 11.3314 | 10.3314 | 14.9971 | 16.9971 | 10.6757 | 21.0071 | 36.0041 | 53.0012 | 0.01
3.8591 | 7.9296 | 5.8591 | 4.8591 | 6.7887 | 8.7887 | 7.9296 | 12.7887 | 19.5774 | 28.3661 | 3.8691 | 7.9396 | 5.8591 | 4.8591 | 6.7887 | 8.7887 | 7.9396 | 12.7987 | 19.5874 | 28.3761 | 0.01
3.9396 | 7.9698 | 5.9396 | 4.9396 | 6.9093 | 8.9093 | 7.9698 | 12.9093 | 19.8187 | 28.728 | 3.9496 | 7.9798 | 5.9396 | 4.9396 | 6.9093 | 8.9093 | 7.9798 | 12.9193 | 19.8287 | 28.738 | 0.01
5.9075 | 8.9538 | 7.9075 | 6.9075 | 9.8613 | 11.8613 | 8.9538 | 15.8613 | 25.7226 | 37.5839 | 5.9175 | 8.9638 | 7.9075 | 6.9075 | 9.8613 | 11.8613 | 8.9638 | 15.8713 | 25.7326 | 37.5939 | 0.01
6.4736 | 9.2368 | 8.4736 | 7.4736 | 10.7104 | 12.7104 | 9.2368 | 16.7104 | 27.4208 | 40.1312 | 6.4836 | 9.2468 | 8.4736 | 7.4736 | 10.7104 | 12.7104 | 9.2468 | 16.7204 | 27.4308 | 40.1412 | 0.01
6.1772 | 9.0886 | 8.1772 | 7.1772 | 10.2658 | 12.2658 | 9.0886 | 16.2658 | 26.5317 | 38.7975 | 6.1872 | 9.0986 | 8.1772 | 7.1772 | 10.2658 | 12.2658 | 9.0986 | 16.2758 | 26.5417 | 38.8075 | 0.01
8.3162 | 10.1581 | 10.3162 | 9.3162 | 13.4744 | 15.4744 | 10.1581 | 19.4744 | 32.9487 | 48.4231 | 8.3262 | 10.1681 | 10.3162 | 9.3162 | 13.4744 | 15.4744 | 10.1681 | 19.4844 | 32.9587 | 48.4331 | 0.01
8.4837 | 10.2419 | 10.4837 | 9.4837 | 13.7256 | 15.7256 | 10.2419 | 19.7256 | 33.4512 | 49.1768 | 8.4937 | 10.2519 | 10.4837 | 9.4837 | 13.7256 | 15.7256 | 10.2519 | 19.7356 | 33.4612 | 49.1868 | 0.01
4.6072 | 8.3036 | 6.6072 | 5.6072 | 7.9108 | 9.9108 | 8.3036 | 13.9108 | 21.8217 | 31.7325 | 4.6172 | 8.3136 | 6.6072 | 5.6072 | 7.9108 | 9.9108 | 8.3136 | 13.9208 | 21.8317 | 31.7425 | 0.01
6.9466 | 9.4733 | 8.9466 | 7.9466 | 11.4199 | 13.4199 | 9.4733 | 17.4199 | 28.8397 | 42.2596 | 6.9566 | 9.4833 | 8.9466 | 7.9466 | 11.4199 | 13.4199 | 9.4833 | 17.4299 | 28.8497 | 42.2696 | 0.01
4.9222 | 8.4611 | 6.9222 | 5.9222 | 8.3833 | 10.3833 | 8.4611 | 14.3833 | 22.7666 | 33.1498 | 4.9322 | 8.4711 | 6.9222 | 5.9222 | 8.3833 | 10.3833 | 8.4711 | 14.3933 | 22.7766 | 33.1598 | 0.01
6.7574 | 9.3787 | 8.7574 | 7.7574 | 11.1361 | 13.1361 | 9.3787 | 17.1361 | 28.2722 | 41.4082 | 6.7674 | 9.3887 | 8.7574 | 7.7574 | 11.1361 | 13.1361 | 9.3887 | 17.1461 | 28.2822 | 41.4182 | 0.01
4.633 | 8.3165 | 6.633 | 5.633 | 7.9494 | 9.9494 | 8.3165 | 13.9494 | 21.8989 | 31.8483 | 4.643 | 8.3265 | 6.633 | 5.633 | 7.9494 | 9.9494 | 8.3265 | 13.9594 | 21.9089 | 31.8583 | 0.01
6.7659 | 9.3829 | 8.7659 | 7.7659 | 11.1488 | 13.1488 | 9.3829 | 17.1488 | 28.2977 | 41.4465 | 6.7759 | 9.3929 | 8.7659 | 7.7659 | 11.1488 | 13.1488 | 9.3929 | 17.1588 | 28.3077 | 41.4565 | 0.01
7.5034 | 9.7517 | 9.5034 | 8.5034 | 12.2551 | 14.2551 | 9.7517 | 18.2551 | 30.5101 | 44.7652 | 7.5134 | 9.7617 | 9.5034 | 8.5034 | 12.2551 | 14.2551 | 9.7617 | 18.2651 | 30.5201 | 44.7752 | 0.01
6.5977 | 9.2989 | 8.5977 | 7.5977 | 10.8966 | 12.8966 | 9.2989 | 16.8966 | 27.7932 | 40.6898 | 6.6077 | 9.3089 | 8.5977 | 7.5977 | 10.8966 | 12.8966 | 9.3089 | 16.9066 | 27.8032 | 40.6998 | 0.01
10.4265 | 11.2133 | 12.4265 | 11.4265 | 16.6398 | 18.6398 | 11.2133 | 22.6398 | 39.2796 | 57.9195 | 10.4365 | 11.2233 | 12.4265 | 11.4265 | 16.6398 | 18.6398 | 11.2233 | 22.6498 | 39.2896 | 57.9295 | 0.01
3.714 | 7.857 | 5.714 | 4.714 | 6.571 | 8.571 | 7.857 | 12.571 | 19.1421 | 27.7131 | 3.724 | 7.867 | 5.714 | 4.714 | 6.571 | 8.571 | 7.867 | 12.581 | 19.1521 | 27.7231 | 0.01
5.7873 | 8.8936 | 7.7873 | 6.7873 | 9.6809 | 11.6809 | 8.8936 | 15.6809 | 25.3618 | 37.0428 | 5.7973 | 8.9036 | 7.7873 | 6.7873 | 9.6809 | 11.6809 | 8.9036 | 15.6909 | 25.3718 | 37.0528 | 0.01
7.0859 | 9.543 | 9.0859 | 8.0859 | 11.6289 | 13.6289 | 9.543 | 17.6289 | 29.2577 | 42.8866 | 7.0959 | 9.553 | 9.0859 | 8.0859 | 11.6289 | 13.6289 | 9.553 | 17.6389 | 29.2677 | 42.8966 | 0.01
7.4262 | 9.7131 | 9.4262 | 8.4262 | 12.1394 | 14.1394 | 9.7131 | 18.1394 | 30.2787 | 44.4181 | 7.4362 | 9.7231 | 9.4262 | 8.4262 | 12.1394 | 14.1394 | 9.7231 | 18.1494 | 30.2887 | 44.4281 | 0.01
8.0811 | 10.0406 | 10.0811 | 9.0811 | 13.1217 | 15.1217 | 10.0406 | 19.1217 | 32.2433 | 47.365 | 8.0911 | 10.0506 | 10.0811 | 9.0811 | 13.1217 | 15.1217 | 10.0506 | 19.1317 | 32.2533 | 47.375 | 0.01
3.1327 | 7.5663 | 5.1327 | 4.1327 | 5.699 | 7.699 | 7.5663 | 11.699 | 17.398 | 25.0971 | 3.1427 | 7.5763 | 5.1327 | 4.1327 | 5.699 | 7.699 | 7.5763 | 11.709 | 17.408 | 25.1071 | 0.01
6.3051 | 9.1525 | 8.3051 | 7.3051 | 10.4576 | 12.4576 | 9.1525 | 16.4576 | 26.9152 | 39.3728 | 6.3151 | 9.1625 | 8.3051 | 7.3051 | 10.4576 | 12.4576 | 9.1625 | 16.4676 | 26.9252 | 39.3828 | 0.01
5.055 | 8.5275 | 7.055 | 6.055 | 8.5826 | 10.5826 | 8.5275 | 14.5826 | 23.1651 | 33.7477 | 5.065 | 8.5375 | 7.055 | 6.055 | 8.5826 | 10.5826 | 8.5375 | 14.5926 | 23.1751 | 33.7577 | 0.01
6.1435 | 9.0718 | 8.1435 | 7.1435 | 10.2153 | 12.2153 | 9.0718 | 16.2153 | 26.4306 | 38.6459 | 6.1535 | 9.0818 | 8.1435 | 7.1435 | 10.2153 | 12.2153 | 9.0818 | 16.2253 | 26.4406 | 38.6559 | 0.01
4.6397 | 8.3198 | 6.6397 | 5.6397 | 7.9595 | 9.9595 | 8.3198 | 13.9595 | 21.919 | 31.8784 | 4.6497 | 8.3298 | 6.6397 | 5.6397 | 7.9595 | 9.9595 | 8.3298 | 13.9695 | 21.929 | 31.8884 | 0.01
5.7358 | 8.8679 | 7.7358 | 6.7358 | 9.6037 | 11.6037 | 8.8679 | 15.6037 | 25.2075 | 36.8112 | 5.7458 | 8.8779 | 7.7358 | 6.7358 | 9.6037 | 11.6037 | 8.8779 | 15.6137 | 25.2175 | 36.8212 | 0.01
5.6716 | 8.8358 | 7.6716 | 6.6716 | 9.5074 | 11.5074 | 8.8358 | 15.5074 | 25.0148 | 36.5222 | 5.6816 | 8.8458 | 7.6716 | 6.6716 | 9.5074 | 11.5074 | 8.8458 | 15.5174 | 25.0248 | 36.5322 | 0.01
5.8039 | 8.902 | 7.8039 | 6.8039 | 9.7059 | 11.7059 | 8.902 | 15.7059 | 25.4118 | 37.1176 | 5.8139 | 8.912 | 7.8039 | 6.8039 | 9.7059 | 11.7059 | 8.912 | 15.7159 | 25.4218 | 37.1276 | 0.01
4.2001 | 8.1001 | 6.2001 | 5.2001 | 7.3002 | 9.3002 | 8.1001 | 13.3002 | 20.6003 | 29.9005 | 4.2101 | 8.1101 | 6.2001 | 5.2001 | 7.3002 | 9.3002 | 8.1101 | 13.3102 | 20.6103 | 29.9105 | 0.01
7.2835 | 9.6418 | 9.2835 | 8.2835 | 11.9253 | 13.9253 | 9.6418 | 17.9253 | 29.8505 | 43.7758 | 7.2935 | 9.6518 | 9.2835 | 8.2835 | 11.9253 | 13.9253 | 9.6518 | 17.9353 | 29.8605 | 43.7858 | 0.01
5.9561 | 8.978 | 7.9561 | 6.9561 | 9.9341 | 11.9341 | 8.978 | 15.9341 | 25.8682 | 37.8023 | 5.9661 | 8.988 | 7.9561 | 6.9561 | 9.9341 | 11.9341 | 8.988 | 15.9441 | 25.8782 | 37.8123 | 0.01
4.4582 | 8.2291 | 6.4582 | 5.4582 | 7.6873 | 9.6873 | 8.2291 | 13.6873 | 21.3746 | 31.0619 | 4.4682 | 8.2391 | 6.4582 | 5.4582 | 7.6873 | 9.6873 | 8.2391 | 13.6973 | 21.3846 | 31.0719 | 0.01
9.4554 | 10.7277 | 11.4554 | 10.4554 | 15.1831 | 17.1831 | 10.7277 | 21.1831 | 36.3663 | 53.5494 | 9.4654 | 10.7377 | 11.4554 | 10.4554 | 15.1831 | 17.1831 | 10.7377 | 21.1931 | 36.3763 | 53.5594 | 0.01
7.4928 | 9.7464 | 9.4928 | 8.4928 | 12.2393 | 14.2393 | 9.7464 | 18.2393 | 30.4785 | 44.7178 | 7.5028 | 9.7564 | 9.4928 | 8.4928 | 12.2393 | 14.2393 | 9.7564 | 18.2493 | 30.4885 | 44.7278 | 0.01
8.881 | 10.4405 | 10.881 | 9.881 | 14.3215 | 16.3215 | 10.4405 | 20.3215 | 34.6431 | 50.9646 | 8.891 | 10.4505 | 10.881 | 9.881 | 14.3215 | 16.3215 | 10.4505 | 20.3315 | 34.6531 | 50.9746 | 0.01
7.7568 | 9.8784 | 9.7568 | 8.7568 | 12.6353 | 14.6353 | 9.8784 | 18.6353 | 31.2705 | 45.9058 | 7.7668 | 9.8884 | 9.7568 | 8.7568 | 12.6353 | 14.6353 | 9.8884 | 18.6453 | 31.2805 | 45.9158 | 0.01
2.9043 | 7.4522 | 4.9043 | 3.9043 | 5.3565 | 7.3565 | 7.4522 | 11.3565 | 16.7129 | 24.0694 | 2.9143 | 7.4622 | 4.9043 | 3.9043 | 5.3565 | 7.3565 | 7.4622 | 11.3665 | 16.7229 | 24.0794 | 0.01
5.3388 | 8.6694 | 7.3388 | 6.3388 | 9.0081 | 11.0081 | 8.6694 | 15.0081 | 24.0163 | 35.0244 | 5.3488 | 8.6794 | 7.3388 | 6.3388 | 9.0081 | 11.0081 | 8.6794 | 15.0181 | 24.0263 | 35.0344 | 0.01
5.5621 | 8.7811 | 7.5621 | 6.5621 | 9.3432 | 11.3432 | 8.7811 | 15.3432 | 24.6864 | 36.0296 | 5.5721 | 8.7911 | 7.5621 | 6.5621 | 9.3432 | 11.3432 | 8.7911 | 15.3532 | 24.6964 | 36.0396 | 0.01
4.4878 | 8.2439 | 6.4878 | 5.4878 | 7.7317 | 9.7317 | 8.2439 | 13.7317 | 21.4634 | 31.1951 | 4.4978 | 8.2539 | 6.4878 | 5.4878 | 7.7317 | 9.7317 | 8.2539 | 13.7417 | 21.4734 | 31.2051 | 0.01
3.7421 | 7.8711 | 5.7421 | 4.7421 | 6.6132 | 8.6132 | 7.8711 | 12.6132 | 19.2263 | 27.8395 | 3.7521 | 7.8811 | 5.7421 | 4.7421 | 6.6132 | 8.6132 | 7.8811 | 12.6232 | 19.2363 | 27.8495 | 0.01
7.9302 | 9.9651 | 9.9302 | 8.9302 | 12.8953 | 14.8953 | 9.9651 | 18.8953 | 31.7905 | 46.6858 | 7.9402 | 9.9751 | 9.9302 | 8.9302 | 12.8953 | 14.8953 | 9.9751 | 18.9053 | 31.8005 | 46.6958 | 0.01
1.6191 | 6.8096 | 3.6191 | 2.6191 | 3.4287 | 5.4287 | 6.8096 | 9.4287 | 12.8574 | 18.2862 | 1.6291 | 6.8196 | 3.6191 | 2.6191 | 3.4287 | 5.4287 | 6.8196 | 9.4387 | 12.8674 | 18.2962 | 0.01
5.7064 | 8.8532 | 7.7064 | 6.7064 | 9.5596 | 11.5596 | 8.8532 | 15.5596 | 25.1192 | 36.6788 | 5.7164 | 8.8632 | 7.7064 | 6.7064 | 9.5596 | 11.5596 | 8.8632 | 15.5696 | 25.1292 | 36.6888 | 0.01
7.4495 | 9.7247 | 9.4495 | 8.4495 | 12.1742 | 14.1742 | 9.7247 | 18.1742 | 30.3484 | 44.5225 | 7.4595 | 9.7347 | 9.4495 | 8.4495 | 12.1742 | 14.1742 | 9.7347 | 18.1842 | 30.3584 | 44.5325 | 0.01
9.2742 | 10.6371 | 11.2742 | 10.2742 | 14.9113 | 16.9113 | 10.6371 | 20.9113 | 35.8226 | 52.7339 | 9.2842 | 10.6471 | 11.2742 | 10.2742 | 14.9113 | 16.9113 | 10.6471 | 20.9213 | 35.8326 | 52.7439 | 0.01
3.6679 | 7.8339 | 5.6679 | 4.6679 | 6.5018 | 8.5018 | 7.8339 | 12.5018 | 19.0036 | 27.5054 | 3.6779 | 7.8439 | 5.6679 | 4.6679 | 6.5018 | 8.5018 | 7.8439 | 12.5118 | 19.0136 | 27.5154 | 0.01
0.79769 | 6.3988 | 2.7977 | 1.7977 | 2.1965 | 4.1965 | 6.3988 | 8.1965 | 10.3931 | 14.5896 | 0.80769 | 6.4088 | 2.7977 | 1.7977 | 2.1965 | 4.1965 | 6.4088 | 8.2065 | 10.4031 | 14.5996 | 0.01
3.1848 | 7.5924 | 5.1848 | 4.1848 | 5.7772 | 7.7772 | 7.5924 | 11.7772 | 17.5544 | 25.3316 | 3.1948 | 7.6024 | 5.1848 | 4.1848 | 5.7772 | 7.7772 | 7.6024 | 11.7872 | 17.5644 | 25.3416 | 0.01
4.6142 | 8.3071 | 6.6142 | 5.6142 | 7.9214 | 9.9214 | 8.3071 | 13.9214 | 21.8427 | 31.7641 | 4.6242 | 8.3171 | 6.6142 | 5.6142 | 7.9214 | 9.9214 | 8.3171 | 13.9314 | 21.8527 | 31.7741 | 0.01
3.8428 | 7.9214 | 5.8428 | 4.8428 | 6.7641 | 8.7641 | 7.9214 | 12.7641 | 19.5283 | 28.2924 | 3.8528 | 7.9314 | 5.8428 | 4.8428 | 6.7641 | 8.7641 | 7.9314 | 12.7741 | 19.5383 | 28.3024 | 0.01
5.1024 | 8.5512 | 7.1024 | 6.1024 | 8.6535 | 10.6535 | 8.5512 | 14.6535 | 23.3071 | 33.9606 | 5.1124 | 8.5612 | 7.1024 | 6.1024 | 8.6535 | 10.6535 | 8.5612 | 14.6635 | 23.3171 | 33.9706 | 0.01
4.4655 | 8.2327 | 6.4655 | 5.4655 | 7.6982 | 9.6982 | 8.2327 | 13.6982 | 21.3965 | 31.0947 | 4.4755 | 8.2427 | 6.4655 | 5.4655 | 7.6982 | 9.6982 | 8.2427 | 13.7082 | 21.4065 | 31.1047 | 0.01
4.0289 | 8.0145 | 6.0289 | 5.0289 | 7.0434 | 9.0434 | 8.0145 | 13.0434 | 20.0867 | 29.1301 | 4.0389 | 8.0245 | 6.0289 | 5.0289 | 7.0434 | 9.0434 | 8.0245 | 13.0534 | 20.0967 | 29.1401 | 0.01
7.1646 | 9.5823 | 9.1646 | 8.1646 | 11.7469 | 13.7469 | 9.5823 | 17.7469 | 29.4938 | 43.2407 | 7.1746 | 9.5923 | 9.1646 | 8.1646 | 11.7469 | 13.7469 | 9.5923 | 17.7569 | 29.5038 | 43.2507 | 0.01
9.2783 | 10.6391 | 11.2783 | 10.2783 | 14.9174 | 16.9174 | 10.6391 | 20.9174 | 35.8348 | 52.7522 | 9.2883 | 10.6491 | 11.2783 | 10.2783 | 14.9174 | 16.9174 | 10.6491 | 20.9274 | 35.8448 | 52.7622 | 0.01
6.9702 | 9.4851 | 8.9702 | 7.9702 | 11.4553 | 13.4553 | 9.4851 | 17.4553 | 28.9106 | 42.3659 | 6.9802 | 9.4951 | 8.9702 | 7.9702 | 11.4553 | 13.4553 | 9.4951 | 17.4653 | 28.9206 | 42.3759 | 0.01
8.7728 | 10.3864 | 10.7728 | 9.7728 | 14.1592 | 16.1592 | 10.3864 | 20.1592 | 34.3184 | 50.4777 | 8.7828 | 10.3964 | 10.7728 | 9.7728 | 14.1592 | 16.1592 | 10.3964 | 20.1692 | 34.3284 | 50.4877 | 0.01
4.2408 | 8.1204 | 6.2408 | 5.2408 | 7.3612 | 9.3612 | 8.1204 | 13.3612 | 20.7224 | 30.0836 | 4.2508 | 8.1304 | 6.2408 | 5.2408 | 7.3612 | 9.3612 | 8.1304 | 13.3712 | 20.7324 | 30.0936 | 0.01
6.3376 | 9.1688 | 8.3376 | 7.3376 | 10.5064 | 12.5064 | 9.1688 | 16.5064 | 27.0128 | 39.5192 | 6.3476 | 9.1788 | 8.3376 | 7.3376 | 10.5064 | 12.5064 | 9.1788 | 16.5164 | 27.0228 | 39.5292 | 0.01
10.4613 | 11.2307 | 12.4613 | 11.4613 | 16.692 | 18.692 | 11.2307 | 22.692 | 39.384 | 58.076 | 10.4713 | 11.2407 | 12.4613 | 11.4613 | 16.692 | 18.692 | 11.2407 | 22.702 | 39.394 | 58.086 | 0.01
0.66258 | 6.3313 | 2.6626 | 1.6626 | 1.9939 | 3.9939 | 6.3313 | 7.9939 | 9.9877 | 13.9816 | 0.67258 | 6.3413 | 2.6626 | 1.6626 | 1.9939 | 3.9939 | 6.3413 | 8.0039 | 9.9977 | 13.9916 | 0.01
10.4087 | 11.2044 | 12.4087 | 11.4087 | 16.6131 | 18.6131 | 11.2044 | 22.6131 | 39.2262 | 57.8392 | 10.4187 | 11.2144 | 12.4087 | 11.4087 | 16.6131 | 18.6131 | 11.2144 | 22.6231 | 39.2362 | 57.8492 | 0.01
8.7381 | 10.369 | 10.7381 | 9.7381 | 14.1071 | 16.1071 | 10.369 | 20.1071 | 34.2142 | 50.3212 | 8.7481 | 10.379 | 10.7381 | 9.7381 | 14.1071 | 16.1071 | 10.379 | 20.1171 | 34.2242 | 50.3312 | 0.01
3.1683 | 7.5841 | 5.1683 | 4.1683 | 5.7524 | 7.7524 | 7.5841 | 11.7524 | 17.5048 | 25.2573 | 3.1783 | 7.5941 | 5.1683 | 4.1683 | 5.7524 | 7.7524 | 7.5941 | 11.7624 | 17.5148 | 25.2673 | 0.01
7.7445 | 9.8723 | 9.7445 | 8.7445 | 12.6168 | 14.6168 | 9.8723 | 18.6168 | 31.2336 | 45.8504 | 7.7545 | 9.8823 | 9.7445 | 8.7445 | 12.6168 | 14.6168 | 9.8823 | 18.6268 | 31.2436 | 45.8604 | 0.01
9.3878 | 10.6939 | 11.3878 | 10.3878 | 15.0817 | 17.0817 | 10.6939 | 21.0817 | 36.1635 | 53.2452 | 9.3978 | 10.7039 | 11.3878 | 10.3878 | 15.0817 | 17.0817 | 10.7039 | 21.0917 | 36.1735 | 53.2552 | 0.01
5.023 | 8.5115 | 7.023 | 6.023 | 8.5345 | 10.5345 | 8.5115 | 14.5345 | 23.0691 | 33.6036 | 5.033 | 8.5215 | 7.023 | 6.023 | 8.5345 | 10.5345 | 8.5215 | 14.5445 | 23.0791 | 33.6136 | 0.01
8.4739 | 10.2369 | 10.4739 | 9.4739 | 13.7108 | 15.7108 | 10.2369 | 19.7108 | 33.4216 | 49.1324 | 8.4839 | 10.2469 | 10.4739 | 9.4739 | 13.7108 | 15.7108 | 10.2469 | 19.7208 | 33.4316 | 49.1424 | 0.01
8.7597 | 10.3798 | 10.7597 | 9.7597 | 14.1395 | 16.1395 | 10.3798 | 20.1395 | 34.2791 | 50.4186 | 8.7697 | 10.3898 | 10.7597 | 9.7597 | 14.1395 | 16.1395 | 10.3898 | 20.1495 | 34.2891 | 50.4286 | 0.01
4.8751 | 8.4376 | 6.8751 | 5.8751 | 8.3127 | 10.3127 | 8.4376 | 14.3127 | 22.6253 | 32.938 | 4.8851 | 8.4476 | 6.8751 | 5.8751 | 8.3127 | 10.3127 | 8.4476 | 14.3227 | 22.6353 | 32.948 | 0.01
1.4437 | 6.7218 | 3.4437 | 2.4437 | 3.1655 | 5.1655 | 6.7218 | 9.1655 | 12.3311 | 17.4966 | 1.4537 | 6.7318 | 3.4437 | 2.4437 | 3.1655 | 5.1655 | 6.7318 | 9.1755 | 12.3411 | 17.5066 | 0.01
8.6329 | 10.3164 | 10.6329 | 9.6329 | 13.9493 | 15.9493 | 10.3164 | 19.9493 | 33.8987 | 49.848 | 8.6429 | 10.3264 | 10.6329 | 9.6329 | 13.9493 | 15.9493 | 10.3264 | 19.9593 | 33.9087 | 49.858 | 0.01
9.0754 | 10.5377 | 11.0754 | 10.0754 | 14.6132 | 16.6132 | 10.5377 | 20.6132 | 35.2263 | 51.8395 | 9.0854 | 10.5477 | 11.0754 | 10.0754 | 14.6132 | 16.6132 | 10.5477 | 20.6232 | 35.2363 | 51.8495 | 0.01
10.3567 | 11.1783 | 12.3567 | 11.3567 | 16.535 | 18.535 | 11.1783 | 22.535 | 39.0701 | 57.6051 | 10.3667 | 11.1883 | 12.3567 | 11.3567 | 16.535 | 18.535 | 11.1883 | 22.545 | 39.0801 | 57.6151 | 0.01
3.4698 | 7.7349 | 5.4698 | 4.4698 | 6.2046 | 8.2046 | 7.7349 | 12.2046 | 18.4093 | 26.6139 | 3.4798 | 7.7449 | 5.4698 | 4.4698 | 6.2046 | 8.2046 | 7.7449 | 12.2146 | 18.4193 | 26.6239 | 0.01
6.9334 | 9.4667 | 8.9334 | 7.9334 | 11.4 | 13.4 | 9.4667 | 17.4 | 28.8001 | 42.2001 | 6.9434 | 9.4767 | 8.9334 | 7.9334 | 11.4 | 13.4 | 9.4767 | 17.41 | 28.8101 | 42.2101 | 0.01
6.7322 | 9.3661 | 8.7322 | 7.7322 | 11.0983 | 13.0983 | 9.3661 | 17.0983 | 28.1966 | 41.2949 | 6.7422 | 9.3761 | 8.7322 | 7.7322 | 11.0983 | 13.0983 | 9.3761 | 17.1083 | 28.2066 | 41.3049 | 0.01
5.8459 | 8.9229 | 7.8459 | 6.8459 | 9.7688 | 11.7688 | 8.9229 | 15.7688 | 25.5376 | 37.3064 | 5.8559 | 8.9329 | 7.8459 | 6.8459 | 9.7688 | 11.7688 | 8.9329 | 15.7788 | 25.5476 | 37.3164 | 0.01
4.7205 | 8.3602 | 6.7205 | 5.7205 | 8.0807 | 10.0807 | 8.3602 | 14.0807 | 22.1614 | 32.242 | 4.7305 | 8.3702 | 6.7205 | 5.7205 | 8.0807 | 10.0807 | 8.3702 | 14.0907 | 22.1714 | 32.252 | 0.01
4.978 | 8.489 | 6.978 | 5.978 | 8.4671 | 10.4671 | 8.489 | 14.4671 | 22.9341 | 33.4012 | 4.988 | 8.499 | 6.978 | 5.978 | 8.4671 | 10.4671 | 8.499 | 14.4771 | 22.9441 | 33.4112 | 0.01
7.8245 | 9.9122 | 9.8245 | 8.8245 | 12.7367 | 14.7367 | 9.9122 | 18.7367 | 31.4734 | 46.2102 | 7.8345 | 9.9222 | 9.8245 | 8.8245 | 12.7367 | 14.7367 | 9.9222 | 18.7467 | 31.4834 | 46.2202 | 0.01
9.0442 | 10.5221 | 11.0442 | 10.0442 | 14.5664 | 16.5664 | 10.5221 | 20.5664 | 35.1327 | 51.6991 | 9.0542 | 10.5321 | 11.0442 | 10.0442 | 14.5664 | 16.5664 | 10.5321 | 20.5764 | 35.1427 | 51.7091 | 0.01
6.103 | 9.0515 | 8.103 | 7.103 | 10.1545 | 12.1545 | 9.0515 | 16.1545 | 26.309 | 38.4635 | 6.113 | 9.0615 | 8.103 | 7.103 | 10.1545 | 12.1545 | 9.0615 | 16.1645 | 26.319 | 38.4735 | 0.01
6.7836 | 9.3918 | 8.7836 | 7.7836 | 11.1754 | 13.1754 | 9.3918 | 17.1754 | 28.3508 | 41.5262 | 6.7936 | 9.4018 | 8.7836 | 7.7836 | 11.1754 | 13.1754 | 9.4018 | 17.1854 | 28.3608 | 41.5362 | 0.01
7.9996 | 9.9998 | 9.9996 | 8.9996 | 12.9994 | 14.9994 | 9.9998 | 18.9994 | 31.9988 | 46.9981 | 8.0096 | 10.0098 | 9.9996 | 8.9996 | 12.9994 | 14.9994 | 10.0098 | 19.0094 | 32.0088 | 47.0081 | 0.01
6.7548 | 9.3774 | 8.7548 | 7.7548 | 11.1323 | 13.1323 | 9.3774 | 17.1323 | 28.2645 | 41.3968 | 6.7648 | 9.3874 | 8.7548 | 7.7548 | 11.1323 | 13.1323 | 9.3874 | 17.1423 | 28.2745 | 41.4068 | 0.01
4.9916 | 8.4958 | 6.9916 | 5.9916 | 8.4874 | 10.4874 | 8.4958 | 14.4874 | 22.9748 | 33.4622 | 5.0016 | 8.5058 | 6.9916 | 5.9916 | 8.4874 | 10.4874 | 8.5058 | 14.4974 | 22.9848 | 33.4722 | 0.01
7.3393 | 9.6696 | 9.3393 | 8.3393 | 12.0089 | 14.0089 | 9.6696 | 18.0089 | 30.0178 | 44.0267 | 7.3493 | 9.6796 | 9.3393 | 8.3393 | 12.0089 | 14.0089 | 9.6796 | 18.0189 | 30.0278 | 44.0367 | 0.01
4.7254 | 8.3627 | 6.7254 | 5.7254 | 8.0881 | 10.0881 | 8.3627 | 14.0881 | 22.1761 | 32.2642 | 4.7354 | 8.3727 | 6.7254 | 5.7254 | 8.0881 | 10.0881 | 8.3727 | 14.0981 | 22.1861 | 32.2742 | 0.01
7.3984 | 9.6992 | 9.3984 | 8.3984 | 12.0976 | 14.0976 | 9.6992 | 18.0976 | 30.1953 | 44.2929 | 7.4084 | 9.7092 | 9.3984 | 8.3984 | 12.0976 | 14.0976 | 9.7092 | 18.1076 | 30.2053 | 44.3029 | 0.01
4.1227 | 8.0614 | 6.1227 | 5.1227 | 7.1841 | 9.1841 | 8.0614 | 13.1841 | 20.3681 | 29.5522 | 4.1327 | 8.0714 | 6.1227 | 5.1227 | 7.1841 | 9.1841 | 8.0714 | 13.1941 | 20.3781 | 29.5622 | 0.01
6.9476 | 9.4738 | 8.9476 | 7.9476 | 11.4214 | 13.4214 | 9.4738 | 17.4214 | 28.8428 | 42.2641 | 6.9576 | 9.4838 | 8.9476 | 7.9476 | 11.4214 | 13.4214 | 9.4838 | 17.4314 | 28.8528 | 42.2741 | 0.01
5.1213 | 8.5607 | 7.1213 | 6.1213 | 8.682 | 10.682 | 8.5607 | 14.682 | 23.3639 | 34.0459 | 5.1313 | 8.5707 | 7.1213 | 6.1213 | 8.682 | 10.682 | 8.5707 | 14.692 | 23.3739 | 34.0559 | 0.01
7.439 | 9.7195 | 9.439 | 8.439 | 12.1584 | 14.1584 | 9.7195 | 18.1584 | 30.3169 | 44.4753 | 7.449 | 9.7295 | 9.439 | 8.439 | 12.1584 | 14.1584 | 9.7295 | 18.1684 | 30.3269 | 44.4853 | 0.01
8.1499 | 10.0749 | 10.1499 | 9.1499 | 13.2248 | 15.2248 | 10.0749 | 19.2248 | 32.4496 | 47.6744 | 8.1599 | 10.0849 | 10.1499 | 9.1499 | 13.2248 | 15.2248 | 10.0849 | 19.2348 | 32.4596 | 47.6844 | 0.01
7.6971 | 9.8485 | 9.6971 | 8.6971 | 12.5456 | 14.5456 | 9.8485 | 18.5456 | 31.0913 | 45.6369 | 7.7071 | 9.8585 | 9.6971 | 8.6971 | 12.5456 | 14.5456 | 9.8585 | 18.5556 | 31.1013 | 45.6469 | 0.01
3.3984 | 7.6992 | 5.3984 | 4.3984 | 6.0976 | 8.0976 | 7.6992 | 12.0976 | 18.1951 | 26.2927 | 3.4084 | 7.7092 | 5.3984 | 4.3984 | 6.0976 | 8.0976 | 7.7092 | 12.1076 | 18.2051 | 26.3027 | 0.01
6.4452 | 9.2226 | 8.4452 | 7.4452 | 10.6678 | 12.6678 | 9.2226 | 16.6678 | 27.3357 | 40.0035 | 6.4552 | 9.2326 | 8.4452 | 7.4452 | 10.6678 | 12.6678 | 9.2326 | 16.6778 | 27.3457 | 40.0135 | 0.01
8.317 | 10.1585 | 10.317 | 9.317 | 13.4754 | 15.4754 | 10.1585 | 19.4754 | 32.9509 | 48.4263 | 8.327 | 10.1685 | 10.317 | 9.317 | 13.4754 | 15.4754 | 10.1685 | 19.4854 | 32.9609 | 48.4363 | 0.01
3.6489 | 7.8244 | 5.6489 | 4.6489 | 6.4733 | 8.4733 | 7.8244 | 12.4733 | 18.9466 | 27.4198 | 3.6589 | 7.8344 | 5.6489 | 4.6489 | 6.4733 | 8.4733 | 7.8344 | 12.4833 | 18.9566 | 27.4298 | 0.01
8.2439 | 10.1219 | 10.2439 | 9.2439 | 13.3658 | 15.3658 | 10.1219 | 19.3658 | 32.7317 | 48.0975 | 8.2539 | 10.1319 | 10.2439 | 9.2439 | 13.3658 | 15.3658 | 10.1319 | 19.3758 | 32.7417 | 48.1075 | 0.01
4.5875 | 8.2937 | 6.5875 | 5.5875 | 7.8812 | 9.8812 | 8.2937 | 13.8812 | 21.7625 | 31.6437 | 4.5975 | 8.3037 | 6.5875 | 5.5875 | 7.8812 | 9.8812 | 8.3037 | 13.8912 | 21.7725 | 31.6537 | 0.01
8.8279 | 10.4139 | 10.8279 | 9.8279 | 14.2418 | 16.2418 | 10.4139 | 20.2418 | 34.4836 | 50.7253 | 8.8379 | 10.4239 | 10.8279 | 9.8279 | 14.2418 | 16.2418 | 10.4239 | 20.2518 | 34.4936 | 50.7353 | 0.01
5.636 | 8.818 | 7.636 | 6.636 | 9.454 | 11.454 | 8.818 | 15.454 | 24.908 | 36.362 | 5.646 | 8.828 | 7.636 | 6.636 | 9.454 | 11.454 | 8.828 | 15.464 | 24.918 | 36.372 | 0.01
8.4249 | 10.2124 | 10.4249 | 9.4249 | 13.6373 | 15.6373 | 10.2124 | 19.6373 | 33.2747 | 48.912 | 8.4349 | 10.2224 | 10.4249 | 9.4249 | 13.6373 | 15.6373 | 10.2224 | 19.6473 | 33.2847 | 48.922 | 0.01
5.2353 | 8.6176 | 7.2353 | 6.2353 | 8.8529 | 10.8529 | 8.6176 | 14.8529 | 23.7058 | 34.5587 | 5.2453 | 8.6276 | 7.2353 | 6.2353 | 8.8529 | 10.8529 | 8.6276 | 14.8629 | 23.7158 | 34.5687 | 0.01
8.1883 | 10.0942 | 10.1883 | 9.1883 | 13.2825 | 15.2825 | 10.0942 | 19.2825 | 32.5649 | 47.8474 | 8.1983 | 10.1042 | 10.1883 | 9.1883 | 13.2825 | 15.2825 | 10.1042 | 19.2925 | 32.5749 | 47.8574 | 0.01
5.4272 | 8.7136 | 7.4272 | 6.4272 | 9.1408 | 11.1408 | 8.7136 | 15.1408 | 24.2816 | 35.4223 | 5.4372 | 8.7236 | 7.4272 | 6.4272 | 9.1408 | 11.1408 | 8.7236 | 15.1508 | 24.2916 | 35.4323 | 0.01
3.0993 | 7.5496 | 5.0993 | 4.0993 | 5.6489 | 7.6489 | 7.5496 | 11.6489 | 17.2979 | 24.9468 | 3.1093 | 7.5596 | 5.0993 | 4.0993 | 5.6489 | 7.6489 | 7.5596 | 11.6589 | 17.3079 | 24.9568 | 0.01
9.643 | 10.8215 | 11.643 | 10.643 | 15.4644 | 17.4644 | 10.8215 | 21.4644 | 36.9289 | 54.3933 | 9.653 | 10.8315 | 11.643 | 10.643 | 15.4644 | 17.4644 | 10.8315 | 21.4744 | 36.9389 | 54.4033 | 0.01
3.1333 | 7.5666 | 5.1333 | 4.1333 | 5.6999 | 7.6999 | 7.5666 | 11.6999 | 17.3999 | 25.0998 | 3.1433 | 7.5766 | 5.1333 | 4.1333 | 5.6999 | 7.6999 | 7.5766 | 11.7099 | 17.4099 | 25.1098 | 0.01
4.86 | 8.43 | 6.86 | 5.86 | 8.2901 | 10.2901 | 8.43 | 14.2901 | 22.5801 | 32.8702 | 4.87 | 8.44 | 6.86 | 5.86 | 8.2901 | 10.2901 | 8.44 | 14.3001 | 22.5901 | 32.8802 | 0.01
1.4969 | 6.7484 | 3.4969 | 2.4969 | 3.2453 | 5.2453 | 6.7484 | 9.2453 | 12.4906 | 17.7359 | 1.5069 | 6.7584 | 3.4969 | 2.4969 | 3.2453 | 5.2453 | 6.7584 | 9.2553 | 12.5006 | 17.7459 | 0.01
6.6087 | 9.3043 | 8.6087 | 7.6087 | 10.913 | 12.913 | 9.3043 | 16.913 | 27.826 | 40.739 | 6.6187 | 9.3143 | 8.6087 | 7.6087 | 10.913 | 12.913 | 9.3143 | 16.923 | 27.836 | 40.749 | 0.01
0.19349 | 6.0967 | 2.1935 | 1.1935 | 1.2902 | 3.2902 | 6.0967 | 7.2902 | 8.5805 | 11.8707 | 0.20349 | 6.1067 | 2.1935 | 1.1935 | 1.2902 | 3.2902 | 6.1067 | 7.3002 | 8.5905 | 11.8807 | 0.01
2.3013 | 7.1507 | 4.3013 | 3.3013 | 4.452 | 6.452 | 7.1507 | 10.452 | 14.9039 | 21.3559 | 2.3113 | 7.1607 | 4.3013 | 3.3013 | 4.452 | 6.452 | 7.1607 | 10.462 | 14.9139 | 21.3659 | 0.01
4.636 | 8.318 | 6.636 | 5.636 | 7.954 | 9.954 | 8.318 | 13.954 | 21.9081 | 31.8621 | 4.646 | 8.328 | 6.636 | 5.636 | 7.954 | 9.954 | 8.328 | 13.964 | 21.9181 | 31.8721 | 0.01
7.8136 | 9.9068 | 9.8136 | 8.8136 | 12.7204 | 14.7204 | 9.9068 | 18.7204 | 31.4408 | 46.1612 | 7.8236 | 9.9168 | 9.8136 | 8.8136 | 12.7204 | 14.7204 | 9.9168 | 18.7304 | 31.4508 | 46.1712 | 0.01
7.9975 | 9.9987 | 9.9975 | 8.9975 | 12.9962 | 14.9962 | 9.9987 | 18.9962 | 31.9924 | 46.9886 | 8.0075 | 10.0087 | 9.9975 | 8.9975 | 12.9962 | 14.9962 | 10.0087 | 19.0062 | 32.0024 | 46.9986 | 0.01
5.0423 | 8.5211 | 7.0423 | 6.0423 | 8.5634 | 10.5634 | 8.5211 | 14.5634 | 23.1269 | 33.6903 | 5.0523 | 8.5311 | 7.0423 | 6.0423 | 8.5634 | 10.5634 | 8.5311 | 14.5734 | 23.1369 | 33.7003 | 0.01
5.2153 | 8.6077 | 7.2153 | 6.2153 | 8.823 | 10.823 | 8.6077 | 14.823 | 23.646 | 34.4689 | 5.2253 | 8.6177 | 7.2153 | 6.2153 | 8.823 | 10.823 | 8.6177 | 14.833 | 23.656 | 34.4789 | 0.01
7.7411 | 9.8705 | 9.7411 | 8.7411 | 12.6116 | 14.6116 | 9.8705 | 18.6116 | 31.2232 | 45.8347 | 7.7511 | 9.8805 | 9.7411 | 8.7411 | 12.6116 | 14.6116 | 9.8805 | 18.6216 | 31.2332 | 45.8447 | 0.01
9.2544 | 10.6272 | 11.2544 | 10.2544 | 14.8816 | 16.8816 | 10.6272 | 20.8816 | 35.7633 | 52.6449 | 9.2644 | 10.6372 | 11.2544 | 10.2544 | 14.8816 | 16.8816 | 10.6372 | 20.8916 | 35.7733 | 52.6549 | 0.01
6.6676 | 9.3338 | 8.6676 | 7.6676 | 11.0015 | 13.0015 | 9.3338 | 17.0015 | 28.0029 | 41.0044 | 6.6776 | 9.3438 | 8.6676 | 7.6676 | 11.0015 | 13.0015 | 9.3438 | 17.0115 | 28.0129 | 41.0144 | 0.01
8.7053 | 10.3526 | 10.7053 | 9.7053 | 14.0579 | 16.0579 | 10.3526 | 20.0579 | 34.1159 | 50.1738 | 8.7153 | 10.3626 | 10.7053 | 9.7053 | 14.0579 | 16.0579 | 10.3626 | 20.0679 | 34.1259 | 50.1838 | 0.01
6.3422 | 9.1711 | 8.3422 | 7.3422 | 10.5132 | 12.5132 | 9.1711 | 16.5132 | 27.0265 | 39.5397 | 6.3522 | 9.1811 | 8.3422 | 7.3422 | 10.5132 | 12.5132 | 9.1811 | 16.5232 | 27.0365 | 39.5497 | 0.01
2.1402 | 7.0701 | 4.1402 | 3.1402 | 4.2102 | 6.2102 | 7.0701 | 10.2102 | 14.4205 | 20.6307 | 2.1502 | 7.0801 | 4.1402 | 3.1402 | 4.2102 | 6.2102 | 7.0801 | 10.2202 | 14.4305 | 20.6407 | 0.01
6.3398 | 9.1699 | 8.3398 | 7.3398 | 10.5097 | 12.5097 | 9.1699 | 16.5097 | 27.0195 | 39.5292 | 6.3498 | 9.1799 | 8.3398 | 7.3398 | 10.5097 | 12.5097 | 9.1799 | 16.5197 | 27.0295 | 39.5392 | 0.01
4.8799 | 8.44 | 6.8799 | 5.8799 | 8.3199 | 10.3199 | 8.44 | 14.3199 | 22.6398 | 32.9597 | 4.8899 | 8.45 | 6.8799 | 5.8799 | 8.3199 | 10.3199 | 8.45 | 14.3299 | 22.6498 | 32.9697 | 0.01
7.8328 | 9.9164 | 9.8328 | 8.8328 | 12.7492 | 14.7492 | 9.9164 | 18.7492 | 31.4983 | 46.2475 | 7.8428 | 9.9264 | 9.8328 | 8.8328 | 12.7492 | 14.7492 | 9.9264 | 18.7592 | 31.5083 | 46.2575 | 0.01
4.5334 | 8.2667 | 6.5334 | 5.5334 | 7.8001 | 9.8001 | 8.2667 | 13.8001 | 21.6003 | 31.4004 | 4.5434 | 8.2767 | 6.5334 | 5.5334 | 7.8001 | 9.8001 | 8.2767 | 13.8101 | 21.6103 | 31.4104 | 0.01
1.5633 | 6.7816 | 3.5633 | 2.5633 | 3.3449 | 5.3449 | 6.7816 | 9.3449 | 12.6898 | 18.0347 | 1.5733 | 6.7916 | 3.5633 | 2.5633 | 3.3449 | 5.3449 | 6.7916 | 9.3549 | 12.6998 | 18.0447 | 0.01
9.238 | 10.619 | 11.238 | 10.238 | 14.857 | 16.857 | 10.619 | 20.857 | 35.714 | 52.571 | 9.248 | 10.629 | 11.238 | 10.238 | 14.857 | 16.857 | 10.629 | 20.867 | 35.724 | 52.581 | 0.01
8.3374 | 10.1687 | 10.3374 | 9.3374 | 13.5062 | 15.5062 | 10.1687 | 19.5062 | 33.0123 | 48.5185 | 8.3474 | 10.1787 | 10.3374 | 9.3374 | 13.5062 | 15.5062 | 10.1787 | 19.5162 | 33.0223 | 48.5285 | 0.01
1.8786 | 6.9393 | 3.8786 | 2.8786 | 3.818 | 5.818 | 6.9393 | 9.818 | 13.6359 | 19.4539 | 1.8886 | 6.9493 | 3.8786 | 2.8786 | 3.818 | 5.818 | 6.9493 | 9.828 | 13.6459 | 19.4639 | 0.01
6.2012 | 9.1006 | 8.2012 | 7.2012 | 10.3018 | 12.3018 | 9.1006 | 16.3018 | 26.6035 | 38.9053 | 6.2112 | 9.1106 | 8.2012 | 7.2012 | 10.3018 | 12.3018 | 9.1106 | 16.3118 | 26.6135 | 38.9153 | 0.01
7.7312 | 9.8656 | 9.7312 | 8.7312 | 12.5968 | 14.5968 | 9.8656 | 18.5968 | 31.1936 | 45.7904 | 7.7412 | 9.8756 | 9.7312 | 8.7312 | 12.5968 | 14.5968 | 9.8756 | 18.6068 | 31.2036 | 45.8004 | 0.01
4.7984 | 8.3992 | 6.7984 | 5.7984 | 8.1976 | 10.1976 | 8.3992 | 14.1976 | 22.3952 | 32.5929 | 4.8084 | 8.4092 | 6.7984 | 5.7984 | 8.1976 | 10.1976 | 8.4092 | 14.2076 | 22.4052 | 32.6029 | 0.01
8.9196 | 10.4598 | 10.9196 | 9.9196 | 14.3793 | 16.3793 | 10.4598 | 20.3793 | 34.7587 | 51.138 | 8.9296 | 10.4698 | 10.9196 | 9.9196 | 14.3793 | 16.3793 | 10.4698 | 20.3893 | 34.7687 | 51.148 | 0.01
9.3436 | 10.6718 | 11.3436 | 10.3436 | 15.0154 | 17.0154 | 10.6718 | 21.0154 | 36.0308 | 53.0462 | 9.3536 | 10.6818 | 11.3436 | 10.3436 | 15.0154 | 17.0154 | 10.6818 | 21.0254 | 36.0408 | 53.0562 | 0.01
5.1653 | 8.5827 | 7.1653 | 6.1653 | 8.748 | 10.748 | 8.5827 | 14.748 | 23.496 | 34.244 | 5.1753 | 8.5927 | 7.1653 | 6.1653 | 8.748 | 10.748 | 8.5927 | 14.758 | 23.506 | 34.254 | 0.01
5.6215 | 8.8107 | 7.6215 | 6.6215 | 9.4322 | 11.4322 | 8.8107 | 15.4322 | 24.8644 | 36.2965 | 5.6315 | 8.8207 | 7.6215 | 6.6215 | 9.4322 | 11.4322 | 8.8207 | 15.4422 | 24.8744 | 36.3065 | 0.01
9.5198 | 10.7599 | 11.5198 | 10.5198 | 15.2797 | 17.2797 | 10.7599 | 21.2797 | 36.5595 | 53.8392 | 9.5298 | 10.7699 | 11.5198 | 10.5198 | 15.2797 | 17.2797 | 10.7699 | 21.2897 | 36.5695 | 53.8492 | 0.01
10.0229 | 11.0114 | 12.0229 | 11.0229 | 16.0343 | 18.0343 | 11.0114 | 22.0343 | 38.0686 | 56.1029 | 10.0329 | 11.0214 | 12.0229 | 11.0229 | 16.0343 | 18.0343 | 11.0214 | 22.0443 | 38.0786 | 56.1129 | 0.01
8.6306 | 10.3153 | 10.6306 | 9.6306 | 13.9458 | 15.9458 | 10.3153 | 19.9458 | 33.8917 | 49.8375 | 8.6406 | 10.3253 | 10.6306 | 9.6306 | 13.9458 | 15.9458 | 10.3253 | 19.9558 | 33.9017 | 49.8475 | 0.01
6.7681 | 9.384 | 8.7681 | 7.7681 | 11.1521 | 13.1521 | 9.384 | 17.1521 | 28.3042 | 41.4562 | 6.7781 | 9.394 | 8.7681 | 7.7681 | 11.1521 | 13.1521 | 9.394 | 17.1621 | 28.3142 | 41.4662 | 0.01
5.9488 | 8.9744 | 7.9488 | 6.9488 | 9.9232 | 11.9232 | 8.9744 | 15.9232 | 25.8464 | 37.7696 | 5.9588 | 8.9844 | 7.9488 | 6.9488 | 9.9232 | 11.9232 | 8.9844 | 15.9332 | 25.8564 | 37.7796 | 0.01
8.6032 | 10.3016 | 10.6032 | 9.6032 | 13.9049 | 15.9049 | 10.3016 | 19.9049 | 33.8097 | 49.7146 | 8.6132 | 10.3116 | 10.6032 | 9.6032 | 13.9049 | 15.9049 | 10.3116 | 19.9149 | 33.8197 | 49.7246 | 0.01
7.2646 | 9.6323 | 9.2646 | 8.2646 | 11.8969 | 13.8969 | 9.6323 | 17.8969 | 29.7938 | 43.6907 | 7.2746 | 9.6423 | 9.2646 | 8.2646 | 11.8969 | 13.8969 | 9.6423 | 17.9069 | 29.8038 | 43.7007 | 0.01
7.4592 | 9.7296 | 9.4592 | 8.4592 | 12.1887 | 14.1887 | 9.7296 | 18.1887 | 30.3775 | 44.5662 | 7.4692 | 9.7396 | 9.4592 | 8.4592 | 12.1887 | 14.1887 | 9.7396 | 18.1987 | 30.3875 | 44.5762 | 0.01
9.2906 | 10.6453 | 11.2906 | 10.2906 | 14.9359 | 16.9359 | 10.6453 | 20.9359 | 35.8718 | 52.8077 | 9.3006 | 10.6553 | 11.2906 | 10.2906 | 14.9359 | 16.9359 | 10.6553 | 20.9459 | 35.8818 | 52.8177 | 0.01
5.6507 | 8.8253 | 7.6507 | 6.6507 | 9.476 | 11.476 | 8.8253 | 15.476 | 24.9521 | 36.4281 | 5.6607 | 8.8353 | 7.6507 | 6.6507 | 9.476 | 11.476 | 8.8353 | 15.486 | 24.9621 | 36.4381 | 0.01
5.277 | 8.6385 | 7.277 | 6.277 | 8.9155 | 10.9155 | 8.6385 | 14.9155 | 23.8311 | 34.7466 | 5.287 | 8.6485 | 7.277 | 6.277 | 8.9155 | 10.9155 | 8.6485 | 14.9255 | 23.8411 | 34.7566 | 0.01
5.9486 | 8.9743 | 7.9486 | 6.9486 | 9.9229 | 11.9229 | 8.9743 | 15.9229 | 25.8458 | 37.7686 | 5.9586 | 8.9843 | 7.9486 | 6.9486 | 9.9229 | 11.9229 | 8.9843 | 15.9329 | 25.8558 | 37.7786 | 0.01
3.9488 | 7.9744 | 5.9488 | 4.9488 | 6.9232 | 8.9232 | 7.9744 | 12.9232 | 19.8463 | 28.7695 | 3.9588 | 7.9844 | 5.9488 | 4.9488 | 6.9232 | 8.9232 | 7.9844 | 12.9332 | 19.8563 | 28.7795 | 0.01
6.967 | 9.4835 | 8.967 | 7.967 | 11.4505 | 13.4505 | 9.4835 | 17.4505 | 28.9011 | 42.3516 | 6.977 | 9.4935 | 8.967 | 7.967 | 11.4505 | 13.4505 | 9.4935 | 17.4605 | 28.9111 | 42.3616 | 0.01
5.6804 | 8.8402 | 7.6804 | 6.6804 | 9.5206 | 11.5206 | 8.8402 | 15.5206 | 25.0411 | 36.5617 | 5.6904 | 8.8502 | 7.6804 | 6.6804 | 9.5206 | 11.5206 | 8.8502 | 15.5306 | 25.0511 | 36.5717 | 0.01
5.8489 | 8.9244 | 7.8489 | 6.8489 | 9.7733 | 11.7733 | 8.9244 | 15.7733 | 25.5467 | 37.32 | 5.8589 | 8.9344 | 7.8489 | 6.8489 | 9.7733 | 11.7733 | 8.9344 | 15.7833 | 25.5567 | 37.33 | 0.01
5.5667 | 8.7834 | 7.5667 | 6.5667 | 9.3501 | 11.3501 | 8.7834 | 15.3501 | 24.7002 | 36.0503 | 5.5767 | 8.7934 | 7.5667 | 6.5667 | 9.3501 | 11.3501 | 8.7934 | 15.3601 | 24.7102 | 36.0603 | 0.01
4.4888 | 8.2444 | 6.4888 | 5.4888 | 7.7331 | 9.7331 | 8.2444 | 13.7331 | 21.4663 | 31.1994 | 4.4988 | 8.2544 | 6.4888 | 5.4888 | 7.7331 | 9.7331 | 8.2544 | 13.7431 | 21.4763 | 31.2094 | 0.01
6.296 | 9.148 | 8.296 | 7.296 | 10.4439 | 12.4439 | 9.148 | 16.4439 | 26.8879 | 39.3318 | 6.306 | 9.158 | 8.296 | 7.296 | 10.4439 | 12.4439 | 9.158 | 16.4539 | 26.8979 | 39.3418 | 0.01
3.229 | 7.6145 | 5.229 | 4.229 | 5.8436 | 7.8436 | 7.6145 | 11.8436 | 17.6871 | 25.5307 | 3.239 | 7.6245 | 5.229 | 4.229 | 5.8436 | 7.8436 | 7.6245 | 11.8536 | 17.6971 | 25.5407 | 0.01
4.2843 | 8.1422 | 6.2843 | 5.2843 | 7.4265 | 9.4265 | 8.1422 | 13.4265 | 20.853 | 30.2795 | 4.2943 | 8.1522 | 6.2843 | 5.2843 | 7.4265 | 9.4265 | 8.1522 | 13.4365 | 20.863 | 30.2895 | 0.01
6.7877 | 9.3938 | 8.7877 | 7.7877 | 11.1815 | 13.1815 | 9.3938 | 17.1815 | 28.363 | 41.5445 | 6.7977 | 9.4038 | 8.7877 | 7.7877 | 11.1815 | 13.1815 | 9.4038 | 17.1915 | 28.373 | 41.5545 | 0.01
5.7262 | 8.8631 | 7.7262 | 6.7262 | 9.5893 | 11.5893 | 8.8631 | 15.5893 | 25.1786 | 36.7679 | 5.7362 | 8.8731 | 7.7262 | 6.7262 | 9.5893 | 11.5893 | 8.8731 | 15.5993 | 25.1886 | 36.7779 | 0.01
5.5621 | 8.7811 | 7.5621 | 6.5621 | 9.3432 | 11.3432 | 8.7811 | 15.3432 | 24.6863 | 36.0295 | 5.5721 | 8.7911 | 7.5621 | 6.5621 | 9.3432 | 11.3432 | 8.7911 | 15.3532 | 24.6963 | 36.0395 | 0.01
3.4367 | 7.7183 | 5.4367 | 4.4367 | 6.155 | 8.155 | 7.7183 | 12.155 | 18.31 | 26.465 | 3.4467 | 7.7283 | 5.4367 | 4.4367 | 6.155 | 8.155 | 7.7283 | 12.165 | 18.32 | 26.475 | 0.01
5.3088 | 8.6544 | 7.3088 | 6.3088 | 8.9631 | 10.9631 | 8.6544 | 14.9631 | 23.9263 | 34.8894 | 5.3188 | 8.6644 | 7.3088 | 6.3088 | 8.9631 | 10.9631 | 8.6644 | 14.9731 | 23.9363 | 34.8994 | 0.01
5.6934 | 8.8467 | 7.6934 | 6.6934 | 9.54 | 11.54 | 8.8467 | 15.54 | 25.0801 | 36.6201 | 5.7034 | 8.8567 | 7.6934 | 6.6934 | 9.54 | 11.54 | 8.8567 | 15.55 | 25.0901 | 36.6301 | 0.01
5.8089 | 8.9045 | 7.8089 | 6.8089 | 9.7134 | 11.7134 | 8.9045 | 15.7134 | 25.4268 | 37.1401 | 5.8189 | 8.9145 | 7.8089 | 6.8089 | 9.7134 | 11.7134 | 8.9145 | 15.7234 | 25.4368 | 37.1501 | 0.01
8.2504 | 10.1252 | 10.2504 | 9.2504 | 13.3756 | 15.3756 | 10.1252 | 19.3756 | 32.7511 | 48.1267 | 8.2604 | 10.1352 | 10.2504 | 9.2504 | 13.3756 | 15.3756 | 10.1352 | 19.3856 | 32.7611 | 48.1367 | 0.01
7.7162 | 9.8581 | 9.7162 | 8.7162 | 12.5744 | 14.5744 | 9.8581 | 18.5744 | 31.1487 | 45.7231 | 7.7262 | 9.8681 | 9.7162 | 8.7162 | 12.5744 | 14.5744 | 9.8681 | 18.5844 | 31.1587 | 45.7331 | 0.01
6.9447 | 9.4723 | 8.9447 | 7.9447 | 11.417 | 13.417 | 9.4723 | 17.417 | 28.834 | 42.251 | 6.9547 | 9.4823 | 8.9447 | 7.9447 | 11.417 | 13.417 | 9.4823 | 17.427 | 28.844 | 42.261 | 0.01
6.4412 | 9.2206 | 8.4412 | 7.4412 | 10.6617 | 12.6617 | 9.2206 | 16.6617 | 27.3235 | 39.9852 | 6.4512 | 9.2306 | 8.4412 | 7.4412 | 10.6617 | 12.6617 | 9.2306 | 16.6717 | 27.3335 | 39.9952 | 0.01
6.4323 | 9.2162 | 8.4323 | 7.4323 | 10.6485 | 12.6485 | 9.2162 | 16.6485 | 27.2969 | 39.9454 | 6.4423 | 9.2262 | 8.4323 | 7.4323 | 10.6485 | 12.6485 | 9.2262 | 16.6585 | 27.3069 | 39.9554 | 0.01
6.4928 | 9.2464 | 8.4928 | 7.4928 | 10.7392 | 12.7392 | 9.2464 | 16.7392 | 27.4785 | 40.2177 | 6.5028 | 9.2564 | 8.4928 | 7.4928 | 10.7392 | 12.7392 | 9.2564 | 16.7492 | 27.4885 | 40.2277 | 0.01
3.9532 | 7.9766 | 5.9532 | 4.9532 | 6.9298 | 8.9298 | 7.9766 | 12.9298 | 19.8596 | 28.7894 | 3.9632 | 7.9866 | 5.9532 | 4.9532 | 6.9298 | 8.9298 | 7.9866 | 12.9398 | 19.8696 | 28.7994 | 0.01
5.9402 | 8.9701 | 7.9402 | 6.9402 | 9.9103 | 11.9103 | 8.9701 | 15.9103 | 25.8206 | 37.731 | 5.9502 | 8.9801 | 7.9402 | 6.9402 | 9.9103 | 11.9103 | 8.9801 | 15.9203 | 25.8306 | 37.741 | 0.01
3.3361 | 7.6681 | 5.3361 | 4.3361 | 6.0042 | 8.0042 | 7.6681 | 12.0042 | 18.0084 | 26.0127 | 3.3461 | 7.6781 | 5.3361 | 4.3361 | 6.0042 | 8.0042 | 7.6781 | 12.0142 | 18.0184 | 26.0227 | 0.01
8.2102 | 10.1051 | 10.2102 | 9.2102 | 13.3154 | 15.3154 | 10.1051 | 19.3154 | 32.6307 | 47.9461 | 8.2202 | 10.1151 | 10.2102 | 9.2102 | 13.3154 | 15.3154 | 10.1151 | 19.3254 | 32.6407 | 47.9561 | 0.01
6.2818 | 9.1409 | 8.2818 | 7.2818 | 10.4227 | 12.4227 | 9.1409 | 16.4227 | 26.8453 | 39.268 | 6.2918 | 9.1509 | 8.2818 | 7.2818 | 10.4227 | 12.4227 | 9.1509 | 16.4327 | 26.8553 | 39.278 | 0.01
2.9093 | 7.4547 | 4.9093 | 3.9093 | 5.364 | 7.364 | 7.4547 | 11.364 | 16.728 | 24.092 | 2.9193 | 7.4647 | 4.9093 | 3.9093 | 5.364 | 7.364 | 7.4647 | 11.374 | 16.738 | 24.102 | 0.01
5.7942 | 8.8971 | 7.7942 | 6.7942 | 9.6914 | 11.6914 | 8.8971 | 15.6914 | 25.3827 | 37.0741 | 5.8042 | 8.9071 | 7.7942 | 6.7942 | 9.6914 | 11.6914 | 8.9071 | 15.7014 | 25.3927 | 37.0841 | 0.01
8.7512 | 10.3756 | 10.7512 | 9.7512 | 14.1267 | 16.1267 | 10.3756 | 20.1267 | 34.2535 | 50.3802 | 8.7612 | 10.3856 | 10.7512 | 9.7512 | 14.1267 | 16.1267 | 10.3856 | 20.1367 | 34.2635 | 50.3902 | 0.01
4.3479 | 8.174 | 6.3479 | 5.3479 | 7.5219 | 9.5219 | 8.174 | 13.5219 | 21.0437 | 30.5656 | 4.3579 | 8.184 | 6.3479 | 5.3479 | 7.5219 | 9.5219 | 8.184 | 13.5319 | 21.0537 | 30.5756 | 0.01
4.2408 | 8.1204 | 6.2408 | 5.2408 | 7.3612 | 9.3612 | 8.1204 | 13.3612 | 20.7223 | 30.0835 | 4.2508 | 8.1304 | 6.2408 | 5.2408 | 7.3612 | 9.3612 | 8.1304 | 13.3712 | 20.7323 | 30.0935 | 0.01
6.0035 | 9.0018 | 8.0035 | 7.0035 | 10.0053 | 12.0053 | 9.0018 | 16.0053 | 26.0106 | 38.0159 | 6.0135 | 9.0118 | 8.0035 | 7.0035 | 10.0053 | 12.0053 | 9.0118 | 16.0153 | 26.0206 | 38.0259 | 0.01
5.1528 | 8.5764 | 7.1528 | 6.1528 | 8.7292 | 10.7292 | 8.5764 | 14.7292 | 23.4584 | 34.1877 | 5.1628 | 8.5864 | 7.1528 | 6.1528 | 8.7292 | 10.7292 | 8.5864 | 14.7392 | 23.4684 | 34.1977 | 0.01
0.74596 | 6.373 | 2.746 | 1.746 | 2.1189 | 4.1189 | 6.373 | 8.1189 | 10.2379 | 14.3568 | 0.75596 | 6.383 | 2.746 | 1.746 | 2.1189 | 4.1189 | 6.383 | 8.1289 | 10.2479 | 14.3668 | 0.01
5.4154 | 8.7077 | 7.4154 | 6.4154 | 9.1231 | 11.1231 | 8.7077 | 15.1231 | 24.2463 | 35.3694 | 5.4254 | 8.7177 | 7.4154 | 6.4154 | 9.1231 | 11.1231 | 8.7177 | 15.1331 | 24.2563 | 35.3794 | 0.01
4.619 | 8.3095 | 6.619 | 5.619 | 7.9285 | 9.9285 | 8.3095 | 13.9285 | 21.8569 | 31.7854 | 4.629 | 8.3195 | 6.619 | 5.619 | 7.9285 | 9.9285 | 8.3195 | 13.9385 | 21.8669 | 31.7954 | 0.01
6.6018 | 9.3009 | 8.6018 | 7.6018 | 10.9028 | 12.9028 | 9.3009 | 16.9028 | 27.8055 | 40.7083 | 6.6118 | 9.3109 | 8.6018 | 7.6018 | 10.9028 | 12.9028 | 9.3109 | 16.9128 | 27.8155 | 40.7183 | 0.01
3.9475 | 7.9738 | 5.9475 | 4.9475 | 6.9213 | 8.9213 | 7.9738 | 12.9213 | 19.8426 | 28.7639 | 3.9575 | 7.9838 | 5.9475 | 4.9475 | 6.9213 | 8.9213 | 7.9838 | 12.9313 | 19.8526 | 28.7739 | 0.01
4.6839 | 8.3419 | 6.6839 | 5.6839 | 8.0258 | 10.0258 | 8.3419 | 14.0258 | 22.0516 | 32.0774 | 4.6939 | 8.3519 | 6.6839 | 5.6839 | 8.0258 | 10.0258 | 8.3519 | 14.0358 | 22.0616 | 32.0874 | 0.01
9.3878 | 10.6939 | 11.3878 | 10.3878 | 15.0817 | 17.0817 | 10.6939 | 21.0817 | 36.1634 | 53.2452 | 9.3978 | 10.7039 | 11.3878 | 10.3878 | 15.0817 | 17.0817 | 10.7039 | 21.0917 | 36.1734 | 53.2552 | 0.01
4.9761 | 8.4881 | 6.9761 | 5.9761 | 8.4642 | 10.4642 | 8.4881 | 14.4642 | 22.9283 | 33.3925 | 4.9861 | 8.4981 | 6.9761 | 5.9761 | 8.4642 | 10.4642 | 8.4981 | 14.4742 | 22.9383 | 33.4025 | 0.01
3.6458 | 7.8229 | 5.6458 | 4.6458 | 6.4687 | 8.4687 | 7.8229 | 12.4687 | 18.9374 | 27.4061 | 3.6558 | 7.8329 | 5.6458 | 4.6458 | 6.4687 | 8.4687 | 7.8329 | 12.4787 | 18.9474 | 27.4161 | 0.01
7.3652 | 9.6826 | 9.3652 | 8.3652 | 12.0478 | 14.0478 | 9.6826 | 18.0478 | 30.0956 | 44.1433 | 7.3752 | 9.6926 | 9.3652 | 8.3652 | 12.0478 | 14.0478 | 9.6926 | 18.0578 | 30.1056 | 44.1533 | 0.01
5.5501 | 8.7751 | 7.5501 | 6.5501 | 9.3252 | 11.3252 | 8.7751 | 15.3252 | 24.6504 | 35.9756 | 5.5601 | 8.7851 | 7.5501 | 6.5501 | 9.3252 | 11.3252 | 8.7851 | 15.3352 | 24.6604 | 35.9856 | 0.01
9.1422 | 10.5711 | 11.1422 | 10.1422 | 14.7134 | 16.7134 | 10.5711 | 20.7134 | 35.4267 | 52.1401 | 9.1522 | 10.5811 | 11.1422 | 10.1422 | 14.7134 | 16.7134 | 10.5811 | 20.7234 | 35.4367 | 52.1501 | 0.01
8.6099 | 10.305 | 10.6099 | 9.6099 | 13.9149 | 15.9149 | 10.305 | 19.9149 | 33.8297 | 49.7446 | 8.6199 | 10.315 | 10.6099 | 9.6099 | 13.9149 | 15.9149 | 10.315 | 19.9249 | 33.8397 | 49.7546 | 0.01
4.9848 | 8.4924 | 6.9848 | 5.9848 | 8.4772 | 10.4772 | 8.4924 | 14.4772 | 22.9545 | 33.4317 | 4.9948 | 8.5024 | 6.9848 | 5.9848 | 8.4772 | 10.4772 | 8.5024 | 14.4872 | 22.9645 | 33.4417 | 0.01
7.565 | 9.7825 | 9.565 | 8.565 | 12.3474 | 14.3474 | 9.7825 | 18.3474 | 30.6949 | 45.0423 | 7.575 | 9.7925 | 9.565 | 8.565 | 12.3474 | 14.3474 | 9.7925 | 18.3574 | 30.7049 | 45.0523 | 0.01
5.7244 | 8.8622 | 7.7244 | 6.7244 | 9.5867 | 11.5867 | 8.8622 | 15.5867 | 25.1733 | 36.76 | 5.7344 | 8.8722 | 7.7244 | 6.7244 | 9.5867 | 11.5867 | 8.8722 | 15.5967 | 25.1833 | 36.77 | 0.01
6.3968 | 9.1984 | 8.3968 | 7.3968 | 10.5952 | 12.5952 | 9.1984 | 16.5952 | 27.1904 | 39.7855 | 6.4068 | 9.2084 | 8.3968 | 7.3968 | 10.5952 | 12.5952 | 9.2084 | 16.6052 | 27.2004 | 39.7955 | 0.01
2.6741 | 7.3371 | 4.6741 | 3.6741 | 5.0112 | 7.0112 | 7.3371 | 11.0112 | 16.0224 | 23.0336 | 2.6841 | 7.3471 | 4.6741 | 3.6741 | 5.0112 | 7.0112 | 7.3471 | 11.0212 | 16.0324 | 23.0436 | 0.01
5.9248 | 8.9624 | 7.9248 | 6.9248 | 9.8873 | 11.8873 | 8.9624 | 15.8873 | 25.7745 | 37.6618 | 5.9348 | 8.9724 | 7.9248 | 6.9248 | 9.8873 | 11.8873 | 8.9724 | 15.8973 | 25.7845 | 37.6718 | 0.01
6.4691 | 9.2345 | 8.4691 | 7.4691 | 10.7036 | 12.7036 | 9.2345 | 16.7036 | 27.4073 | 40.1109 | 6.4791 | 9.2445 | 8.4691 | 7.4691 | 10.7036 | 12.7036 | 9.2445 | 16.7136 | 27.4173 | 40.1209 | 0.01
7.9171 | 9.9585 | 9.9171 | 8.9171 | 12.8756 | 14.8756 | 9.9585 | 18.8756 | 31.7513 | 46.6269 | 7.9271 | 9.9685 | 9.9171 | 8.9171 | 12.8756 | 14.8756 | 9.9685 | 18.8856 | 31.7613 | 46.6369 | 0.01
5.5816 | 8.7908 | 7.5816 | 6.5816 | 9.3725 | 11.3725 | 8.7908 | 15.3725 | 24.7449 | 36.1174 | 5.5916 | 8.8008 | 7.5816 | 6.5816 | 9.3725 | 11.3725 | 8.8008 | 15.3825 | 24.7549 | 36.1274 | 0.01
3.463 | 7.7315 | 5.463 | 4.463 | 6.1944 | 8.1944 | 7.7315 | 12.1944 | 18.3889 | 26.5833 | 3.473 | 7.7415 | 5.463 | 4.463 | 6.1944 | 8.1944 | 7.7415 | 12.2044 | 18.3989 | 26.5933 | 0.01
5.7887 | 8.8944 | 7.7887 | 6.7887 | 9.6831 | 11.6831 | 8.8944 | 15.6831 | 25.3662 | 37.0493 | 5.7987 | 8.9044 | 7.7887 | 6.7887 | 9.6831 | 11.6831 | 8.9044 | 15.6931 | 25.3762 | 37.0593 | 0.01
6.1546 | 9.0773 | 8.1546 | 7.1546 | 10.2319 | 12.2319 | 9.0773 | 16.2319 | 26.4638 | 38.6958 | 6.1646 | 9.0873 | 8.1546 | 7.1546 | 10.2319 | 12.2319 | 9.0873 | 16.2419 | 26.4738 | 38.7058 | 0.01
5.163 | 8.5815 | 7.163 | 6.163 | 8.7444 | 10.7444 | 8.5815 | 14.7444 | 23.4889 | 34.2333 | 5.173 | 8.5915 | 7.163 | 6.163 | 8.7444 | 10.7444 | 8.5915 | 14.7544 | 23.4989 | 34.2433 | 0.01
3.7331 | 7.8665 | 5.7331 | 4.7331 | 6.5996 | 8.5996 | 7.8665 | 12.5996 | 19.1992 | 27.7988 | 3.7431 | 7.8765 | 5.7331 | 4.7331 | 6.5996 | 8.5996 | 7.8765 | 12.6096 | 19.2092 | 27.8088 | 0.01
8.1549 | 10.0774 | 10.1549 | 9.1549 | 13.2323 | 15.2323 | 10.0774 | 19.2323 | 32.4646 | 47.6969 | 8.1649 | 10.0874 | 10.1549 | 9.1549 | 13.2323 | 15.2323 | 10.0874 | 19.2423 | 32.4746 | 47.7069 | 0.01
4.3398 | 8.1699 | 6.3398 | 5.3398 | 7.5097 | 9.5097 | 8.1699 | 13.5097 | 21.0194 | 30.5291 | 4.3498 | 8.1799 | 6.3398 | 5.3398 | 7.5097 | 9.5097 | 8.1799 | 13.5197 | 21.0294 | 30.5391 | 0.01
8.4702 | 10.2351 | 10.4702 | 9.4702 | 13.7053 | 15.7053 | 10.2351 | 19.7053 | 33.4105 | 49.1158 | 8.4802 | 10.2451 | 10.4702 | 9.4702 | 13.7053 | 15.7053 | 10.2451 | 19.7153 | 33.4205 | 49.1258 | 0.01
3.9037 | 7.9519 | 5.9037 | 4.9037 | 6.8556 | 8.8556 | 7.9519 | 12.8556 | 19.7112 | 28.5668 | 3.9137 | 7.9619 | 5.9037 | 4.9037 | 6.8556 | 8.8556 | 7.9619 | 12.8656 | 19.7212 | 28.5768 | 0.01
5.8388 | 8.9194 | 7.8388 | 6.8388 | 9.7582 | 11.7582 | 8.9194 | 15.7582 | 25.5165 | 37.2747 | 5.8488 | 8.9294 | 7.8388 | 6.8388 | 9.7582 | 11.7582 | 8.9294 | 15.7682 | 25.5265 | 37.2847 | 0.01
7.493 | 9.7465 | 9.493 | 8.493 | 12.2395 | 14.2395 | 9.7465 | 18.2395 | 30.479 | 44.7184 | 7.503 | 9.7565 | 9.493 | 8.493 | 12.2395 | 14.2395 | 9.7565 | 18.2495 | 30.489 | 44.7284 | 0.01
4.9927 | 8.4963 | 6.9927 | 5.9927 | 8.489 | 10.489 | 8.4963 | 14.489 | 22.978 | 33.4669 | 5.0027 | 8.5063 | 6.9927 | 5.9927 | 8.489 | 10.489 | 8.5063 | 14.499 | 22.988 | 33.4769 | 0.01
8.3457 | 10.1729 | 10.3457 | 9.3457 | 13.5186 | 15.5186 | 10.1729 | 19.5186 | 33.0371 | 48.5557 | 8.3557 | 10.1829 | 10.3457 | 9.3457 | 13.5186 | 15.5186 | 10.1829 | 19.5286 | 33.0471 | 48.5657 | 0.01
10.0861 | 11.043 | 12.0861 | 11.0861 | 16.1291 | 18.1291 | 11.043 | 22.1291 | 38.2582 | 56.3873 | 10.0961 | 11.053 | 12.0861 | 11.0861 | 16.1291 | 18.1291 | 11.053 | 22.1391 | 38.2682 | 56.3973 | 0.01
2.6271 | 7.3136 | 4.6271 | 3.6271 | 4.9407 | 6.9407 | 7.3136 | 10.9407 | 15.8814 | 22.8221 | 2.6371 | 7.3236 | 4.6271 | 3.6271 | 4.9407 | 6.9407 | 7.3236 | 10.9507 | 15.8914 | 22.8321 | 0.01
7.0962 | 9.5481 | 9.0962 | 8.0962 | 11.6443 | 13.6443 | 9.5481 | 17.6443 | 29.2885 | 42.9328 | 7.1062 | 9.5581 | 9.0962 | 8.0962 | 11.6443 | 13.6443 | 9.5581 | 17.6543 | 29.2985 | 42.9428 | 0.01
5.8452 | 8.9226 | 7.8452 | 6.8452 | 9.7678 | 11.7678 | 8.9226 | 15.7678 | 25.5355 | 37.3033 | 5.8552 | 8.9326 | 7.8452 | 6.8452 | 9.7678 | 11.7678 | 8.9326 | 15.7778 | 25.5455 | 37.3133 | 0.01
10.5641 | 11.2821 | 12.5641 | 11.5641 | 16.8462 | 18.8462 | 11.2821 | 22.8462 | 39.6924 | 58.5386 | 10.5741 | 11.2921 | 12.5641 | 11.5641 | 16.8462 | 18.8462 | 11.2921 | 22.8562 | 39.7024 | 58.5486 | 0.01
2.6054 | 7.3027 | 4.6054 | 3.6054 | 4.9081 | 6.9081 | 7.3027 | 10.9081 | 15.8163 | 22.7244 | 2.6154 | 7.3127 | 4.6054 | 3.6054 | 4.9081 | 6.9081 | 7.3127 | 10.9181 | 15.8263 | 22.7344 | 0.01
4.9665 | 8.4833 | 6.9665 | 5.9665 | 8.4498 | 10.4498 | 8.4833 | 14.4498 | 22.8996 | 33.3493 | 4.9765 | 8.4933 | 6.9665 | 5.9665 | 8.4498 | 10.4498 | 8.4933 | 14.4598 | 22.9096 | 33.3593 | 0.01
9.3474 | 10.6737 | 11.3474 | 10.3474 | 15.0211 | 17.0211 | 10.6737 | 21.0211 | 36.0422 | 53.0634 | 9.3574 | 10.6837 | 11.3474 | 10.3474 | 15.0211 | 17.0211 | 10.6837 | 21.0311 | 36.0522 | 53.0734 | 0.01
5.9379 | 8.969 | 7.9379 | 6.9379 | 9.9069 | 11.9069 | 8.969 | 15.9069 | 25.8138 | 37.7207 | 5.9479 | 8.979 | 7.9379 | 6.9379 | 9.9069 | 11.9069 | 8.979 | 15.9169 | 25.8238 | 37.7307 | 0.01
5.5692 | 8.7846 | 7.5692 | 6.5692 | 9.3538 | 11.3538 | 8.7846 | 15.3538 | 24.7076 | 36.0614 | 5.5792 | 8.7946 | 7.5692 | 6.5692 | 9.3538 | 11.3538 | 8.7946 | 15.3638 | 24.7176 | 36.0714 | 0.01
5.1908 | 8.5954 | 7.1908 | 6.1908 | 8.7862 | 10.7862 | 8.5954 | 14.7862 | 23.5724 | 34.3587 | 5.2008 | 8.6054 | 7.1908 | 6.1908 | 8.7862 | 10.7862 | 8.6054 | 14.7962 | 23.5824 | 34.3687 | 0.01
8.7941 | 10.397 | 10.7941 | 9.7941 | 14.1911 | 16.1911 | 10.397 | 20.1911 | 34.3822 | 50.5733 | 8.8041 | 10.407 | 10.7941 | 9.7941 | 14.1911 | 16.1911 | 10.407 | 20.2011 | 34.3922 | 50.5833 | 0.01
4.5682 | 8.2841 | 6.5682 | 5.5682 | 7.8524 | 9.8524 | 8.2841 | 13.8524 | 21.7047 | 31.5571 | 4.5782 | 8.2941 | 6.5682 | 5.5682 | 7.8524 | 9.8524 | 8.2941 | 13.8624 | 21.7147 | 31.5671 | 0.01
7.66 | 9.83 | 9.66 | 8.66 | 12.49 | 14.49 | 9.83 | 18.49 | 30.98 | 45.47 | 7.67 | 9.84 | 9.66 | 8.66 | 12.49 | 14.49 | 9.84 | 18.5 | 30.99 | 45.48 | 0.01
6.8619 | 9.431 | 8.8619 | 7.8619 | 11.2929 | 13.2929 | 9.431 | 17.2929 | 28.5858 | 41.8788 | 6.8719 | 9.441 | 8.8619 | 7.8619 | 11.2929 | 13.2929 | 9.441 | 17.3029 | 28.5958 | 41.8888 | 0.01
4.1334 | 8.0667 | 6.1334 | 5.1334 | 7.2 | 9.2 | 8.0667 | 13.2 | 20.4001 | 29.6001 | 4.1434 | 8.0767 | 6.1334 | 5.1334 | 7.2 | 9.2 | 8.0767 | 13.21 | 20.4101 | 29.6101 | 0.01
7.1882 | 9.5941 | 9.1882 | 8.1882 | 11.7823 | 13.7823 | 9.5941 | 17.7823 | 29.5647 | 43.347 | 7.1982 | 9.6041 | 9.1882 | 8.1882 | 11.7823 | 13.7823 | 9.6041 | 17.7923 | 29.5747 | 43.357 | 0.01
6.5105 | 9.2553 | 8.5105 | 7.5105 | 10.7658 | 12.7658 | 9.2553 | 16.7658 | 27.5316 | 40.2974 | 6.5205 | 9.2653 | 8.5105 | 7.5105 | 10.7658 | 12.7658 | 9.2653 | 16.7758 | 27.5416 | 40.3074 | 0.01
6.7038 | 9.3519 | 8.7038 | 7.7038 | 11.0557 | 13.0557 | 9.3519 | 17.0557 | 28.1115 | 41.1672 | 6.7138 | 9.3619 | 8.7038 | 7.7038 | 11.0557 | 13.0557 | 9.3619 | 17.0657 | 28.1215 | 41.1772 | 0.01
4.6732 | 8.3366 | 6.6732 | 5.6732 | 8.0099 | 10.0099 | 8.3366 | 14.0099 | 22.0197 | 32.0296 | 4.6832 | 8.3466 | 6.6732 | 5.6732 | 8.0099 | 10.0099 | 8.3466 | 14.0199 | 22.0297 | 32.0396 | 0.01
4.9097 | 8.4549 | 6.9097 | 5.9097 | 8.3646 | 10.3646 | 8.4549 | 14.3646 | 22.7292 | 33.0938 | 4.9197 | 8.4649 | 6.9097 | 5.9097 | 8.3646 | 10.3646 | 8.4649 | 14.3746 | 22.7392 | 33.1038 | 0.01
6.6014 | 9.3007 | 8.6014 | 7.6014 | 10.902 | 12.902 | 9.3007 | 16.902 | 27.8041 | 40.7061 | 6.6114 | 9.3107 | 8.6014 | 7.6014 | 10.902 | 12.902 | 9.3107 | 16.912 | 27.8141 | 40.7161 | 0.01
6.4841 | 9.2421 | 8.4841 | 7.4841 | 10.7262 | 12.7262 | 9.2421 | 16.7262 | 27.4524 | 40.1785 | 6.4941 | 9.2521 | 8.4841 | 7.4841 | 10.7262 | 12.7262 | 9.2521 | 16.7362 | 27.4624 | 40.1885 | 0.01
7.7612 | 9.8806 | 9.7612 | 8.7612 | 12.6418 | 14.6418 | 9.8806 | 18.6418 | 31.2836 | 45.9254 | 7.7712 | 9.8906 | 9.7612 | 8.7612 | 12.6418 | 14.6418 | 9.8906 | 18.6518 | 31.2936 | 45.9354 | 0.01
10.5814 | 11.2907 | 12.5814 | 11.5814 | 16.8721 | 18.8721 | 11.2907 | 22.8721 | 39.7442 | 58.6164 | 10.5914 | 11.3007 | 12.5814 | 11.5814 | 16.8721 | 18.8721 | 11.3007 | 22.8821 | 39.7542 | 58.6264 | 0.01
4.8892 | 8.4446 | 6.8892 | 5.8892 | 8.3337 | 10.3337 | 8.4446 | 14.3337 | 22.6675 | 33.0012 | 4.8992 | 8.4546 | 6.8892 | 5.8892 | 8.3337 | 10.3337 | 8.4546 | 14.3437 | 22.6775 | 33.0112 | 0.01
5.0805 | 8.5403 | 7.0805 | 6.0805 | 8.6208 | 10.6208 | 8.5403 | 14.6208 | 23.2415 | 33.8623 | 5.0905 | 8.5503 | 7.0805 | 6.0805 | 8.6208 | 10.6208 | 8.5503 | 14.6308 | 23.2515 | 33.8723 | 0.01
[8 empty] | Average | 37.9051 | [6 empty] | 0 | 0 | Average | 37.9151 | 100%

## test activity A (2)
A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | diff
-0.32484 | 5.8376 | 1.6752 | 0.67516 | 0.51273 | 2.5127 | 5.8376 | 6.5127 | 7.5127 | 10.0255 | -0.31484 | 5.8476 | 1.6752 | 0.67516 | 0.51273 | 2.5127 | 5.8476 | 6.5227 | 7.5227 | 10.0355 | 0.01
3.9593 | 7.9796 | 5.9593 | 4.9593 | 6.9389 | 8.9389 | 7.9796 | 12.9389 | 19.8778 | 28.8168 | 3.9693 | 7.9896 | 5.9593 | 4.9593 | 6.9389 | 8.9389 | 7.9896 | 12.9489 | 19.8878 | 28.8268 | 0.01
6.3046 | 9.1523 | 8.3046 | 7.3046 | 10.457 | 12.457 | 9.1523 | 16.457 | 26.9139 | 39.3709 | 6.3146 | 9.1623 | 8.3046 | 7.3046 | 10.457 | 12.457 | 9.1623 | 16.467 | 26.9239 | 39.3809 | 0.01
8.2062 | 10.1031 | 10.2062 | 9.2062 | 13.3094 | 15.3094 | 10.1031 | 19.3094 | 32.6187 | 47.9281 | 8.2162 | 10.1131 | 10.2062 | 9.2062 | 13.3094 | 15.3094 | 10.1131 | 19.3194 | 32.6287 | 47.9381 | 0.01
4.8148 | 8.4074 | 6.8148 | 5.8148 | 8.2222 | 10.2222 | 8.4074 | 14.2222 | 22.4444 | 32.6666 | 4.8248 | 8.4174 | 6.8148 | 5.8148 | 8.2222 | 10.2222 | 8.4174 | 14.2322 | 22.4544 | 32.6766 | 0.01
8.5173 | 10.2586 | 10.5173 | 9.5173 | 13.7759 | 15.7759 | 10.2586 | 19.7759 | 33.5518 | 49.3277 | 8.5273 | 10.2686 | 10.5173 | 9.5173 | 13.7759 | 15.7759 | 10.2686 | 19.7859 | 33.5618 | 49.3377 | 0.01
7.0746 | 9.5373 | 9.0746 | 8.0746 | 11.6118 | 13.6118 | 9.5373 | 17.6118 | 29.2237 | 42.8355 | 7.0846 | 9.5473 | 9.0746 | 8.0746 | 11.6118 | 13.6118 | 9.5473 | 17.6218 | 29.2337 | 42.8455 | 0.01
8.416 | 10.208 | 10.416 | 9.416 | 13.6239 | 15.6239 | 10.208 | 19.6239 | 33.2479 | 48.8718 | 8.426 | 10.218 | 10.416 | 9.416 | 13.6239 | 15.6239 | 10.218 | 19.6339 | 33.2579 | 48.8818 | 0.01
8.9462 | 10.4731 | 10.9462 | 9.9462 | 14.4194 | 16.4194 | 10.4731 | 20.4194 | 34.8387 | 51.2581 | 8.9562 | 10.4831 | 10.9462 | 9.9462 | 14.4194 | 16.4194 | 10.4831 | 20.4294 | 34.8487 | 51.2681 | 0.01
5.8459 | 8.9229 | 7.8459 | 6.8459 | 9.7688 | 11.7688 | 8.9229 | 15.7688 | 25.5377 | 37.3065 | 5.8559 | 8.9329 | 7.8459 | 6.8459 | 9.7688 | 11.7688 | 8.9329 | 15.7788 | 25.5477 | 37.3165 | 0.01
5.2305 | 8.6152 | 7.2305 | 6.2305 | 8.8457 | 10.8457 | 8.6152 | 14.8457 | 23.6914 | 34.5372 | 5.2405 | 8.6252 | 7.2305 | 6.2305 | 8.8457 | 10.8457 | 8.6252 | 14.8557 | 23.7014 | 34.5472 | 0.01
9.1373 | 10.5687 | 11.1373 | 10.1373 | 14.706 | 16.706 | 10.5687 | 20.706 | 35.412 | 52.118 | 9.1473 | 10.5787 | 11.1373 | 10.1373 | 14.706 | 16.706 | 10.5787 | 20.716 | 35.422 | 52.128 | 0.01
3.3969 | 7.6984 | 5.3969 | 4.3969 | 6.0953 | 8.0953 | 7.6984 | 12.0953 | 18.1907 | 26.286 | 3.4069 | 7.7084 | 5.3969 | 4.3969 | 6.0953 | 8.0953 | 7.7084 | 12.1053 | 18.2007 | 26.296 | 0.01
5.7851 | 8.8925 | 7.7851 | 6.7851 | 9.6776 | 11.6776 | 8.8925 | 15.6776 | 25.3552 | 37.0328 | 5.7951 | 8.9025 | 7.7851 | 6.7851 | 9.6776 | 11.6776 | 8.9025 | 15.6876 | 25.3652 | 37.0428 | 0.01
5.2086 | 8.6043 | 7.2086 | 6.2086 | 8.8129 | 10.8129 | 8.6043 | 14.8129 | 23.6258 | 34.4387 | 5.2186 | 8.6143 | 7.2086 | 6.2086 | 8.8129 | 10.8129 | 8.6143 | 14.8229 | 23.6358 | 34.4487 | 0.01
9.7622 | 10.8811 | 11.7622 | 10.7622 | 15.6432 | 17.6432 | 10.8811 | 21.6432 | 37.2865 | 54.9297 | 9.7722 | 10.8911 | 11.7622 | 10.7622 | 15.6432 | 17.6432 | 10.8911 | 21.6532 | 37.2965 | 54.9397 | 0.01
3.5986 | 7.7993 | 5.5986 | 4.5986 | 6.398 | 8.398 | 7.7993 | 12.398 | 18.7959 | 27.1939 | 3.6086 | 7.8093 | 5.5986 | 4.5986 | 6.398 | 8.398 | 7.8093 | 12.408 | 18.8059 | 27.2039 | 0.01
7.4765 | 9.7382 | 9.4765 | 8.4765 | 12.2147 | 14.2147 | 9.7382 | 18.2147 | 30.4295 | 44.6442 | 7.4865 | 9.7482 | 9.4765 | 8.4765 | 12.2147 | 14.2147 | 9.7482 | 18.2247 | 30.4395 | 44.6542 | 0.01
5.1836 | 8.5918 | 7.1836 | 6.1836 | 8.7754 | 10.7754 | 8.5918 | 14.7754 | 23.5508 | 34.3262 | 5.1936 | 8.6018 | 7.1836 | 6.1836 | 8.7754 | 10.7754 | 8.6018 | 14.7854 | 23.5608 | 34.3362 | 0.01
6.9591 | 9.4795 | 8.9591 | 7.9591 | 11.4386 | 13.4386 | 9.4795 | 17.4386 | 28.8773 | 42.3159 | 6.9691 | 9.4895 | 8.9591 | 7.9591 | 11.4386 | 13.4386 | 9.4895 | 17.4486 | 28.8873 | 42.3259 | 0.01
7.3402 | 9.6701 | 9.3402 | 8.3402 | 12.0102 | 14.0102 | 9.6701 | 18.0102 | 30.0205 | 44.0307 | 7.3502 | 9.6801 | 9.3402 | 8.3402 | 12.0102 | 14.0102 | 9.6801 | 18.0202 | 30.0305 | 44.0407 | 0.01
6.9202 | 9.4601 | 8.9202 | 7.9202 | 11.3802 | 13.3802 | 9.4601 | 17.3802 | 28.7605 | 42.1407 | 6.9302 | 9.4701 | 8.9202 | 7.9202 | 11.3802 | 13.3802 | 9.4701 | 17.3902 | 28.7705 | 42.1507 | 0.01
8.5367 | 10.2684 | 10.5367 | 9.5367 | 13.8051 | 15.8051 | 10.2684 | 19.8051 | 33.6101 | 49.4152 | 8.5467 | 10.2784 | 10.5367 | 9.5367 | 13.8051 | 15.8051 | 10.2784 | 19.8151 | 33.6201 | 49.4252 | 0.01
2.5804 | 7.2902 | 4.5804 | 3.5804 | 4.8705 | 6.8705 | 7.2902 | 10.8705 | 15.7411 | 22.6116 | 2.5904 | 7.3002 | 4.5804 | 3.5804 | 4.8705 | 6.8705 | 7.3002 | 10.8805 | 15.7511 | 22.6216 | 0.01
6.5936 | 9.2968 | 8.5936 | 7.5936 | 10.8904 | 12.8904 | 9.2968 | 16.8904 | 27.7808 | 40.6712 | 6.6036 | 9.3068 | 8.5936 | 7.5936 | 10.8904 | 12.8904 | 9.3068 | 16.9004 | 27.7908 | 40.6812 | 0.01
7.008 | 9.504 | 9.008 | 8.008 | 11.5121 | 13.5121 | 9.504 | 17.5121 | 29.0241 | 42.5362 | 7.018 | 9.514 | 9.008 | 8.008 | 11.5121 | 13.5121 | 9.514 | 17.5221 | 29.0341 | 42.5462 | 0.01
4.2915 | 8.1458 | 6.2915 | 5.2915 | 7.4373 | 9.4373 | 8.1458 | 13.4373 | 20.8746 | 30.3119 | 4.3015 | 8.1558 | 6.2915 | 5.2915 | 7.4373 | 9.4373 | 8.1558 | 13.4473 | 20.8846 | 30.3219 | 0.01
5.4512 | 8.7256 | 7.4512 | 6.4512 | 9.1769 | 11.1769 | 8.7256 | 15.1769 | 24.3537 | 35.5306 | 5.4612 | 8.7356 | 7.4512 | 6.4512 | 9.1769 | 11.1769 | 8.7356 | 15.1869 | 24.3637 | 35.5406 | 0.01
6.5064 | 9.2532 | 8.5064 | 7.5064 | 10.7595 | 12.7595 | 9.2532 | 16.7595 | 27.5191 | 40.2786 | 6.5164 | 9.2632 | 8.5064 | 7.5064 | 10.7595 | 12.7595 | 9.2632 | 16.7695 | 27.5291 | 40.2886 | 0.01
3.6406 | 7.8203 | 5.6406 | 4.6406 | 6.4609 | 8.4609 | 7.8203 | 12.4609 | 18.9218 | 27.3827 | 3.6506 | 7.8303 | 5.6406 | 4.6406 | 6.4609 | 8.4609 | 7.8303 | 12.4709 | 18.9318 | 27.3927 | 0.01
2.298 | 7.149 | 4.298 | 3.298 | 4.4469 | 6.4469 | 7.149 | 10.4469 | 14.8939 | 21.3408 | 2.308 | 7.159 | 4.298 | 3.298 | 4.4469 | 6.4469 | 7.159 | 10.4569 | 14.9039 | 21.3508 | 0.01
4.4543 | 8.2271 | 6.4543 | 5.4543 | 7.6814 | 9.6814 | 8.2271 | 13.6814 | 21.3629 | 31.0443 | 4.4643 | 8.2371 | 6.4543 | 5.4543 | 7.6814 | 9.6814 | 8.2371 | 13.6914 | 21.3729 | 31.0543 | 0.01
4.6213 | 8.3106 | 6.6213 | 5.6213 | 7.9319 | 9.9319 | 8.3106 | 13.9319 | 21.8639 | 31.7958 | 4.6313 | 8.3206 | 6.6213 | 5.6213 | 7.9319 | 9.9319 | 8.3206 | 13.9419 | 21.8739 | 31.8058 | 0.01
7.3267 | 9.6634 | 9.3267 | 8.3267 | 11.9901 | 13.9901 | 9.6634 | 17.9901 | 29.9802 | 43.9703 | 7.3367 | 9.6734 | 9.3267 | 8.3267 | 11.9901 | 13.9901 | 9.6734 | 18.0001 | 29.9902 | 43.9803 | 0.01
6.5492 | 9.2746 | 8.5492 | 7.5492 | 10.8238 | 12.8238 | 9.2746 | 16.8238 | 27.6476 | 40.4714 | 6.5592 | 9.2846 | 8.5492 | 7.5492 | 10.8238 | 12.8238 | 9.2846 | 16.8338 | 27.6576 | 40.4814 | 0.01
7.857 | 9.9285 | 9.857 | 8.857 | 12.7855 | 14.7855 | 9.9285 | 18.7855 | 31.5709 | 46.3564 | 7.867 | 9.9385 | 9.857 | 8.857 | 12.7855 | 14.7855 | 9.9385 | 18.7955 | 31.5809 | 46.3664 | 0.01
4.737 | 8.3685 | 6.737 | 5.737 | 8.1055 | 10.1055 | 8.3685 | 14.1055 | 22.211 | 32.3165 | 4.747 | 8.3785 | 6.737 | 5.737 | 8.1055 | 10.1055 | 8.3785 | 14.1155 | 22.221 | 32.3265 | 0.01
6.7225 | 9.3613 | 8.7225 | 7.7225 | 11.0838 | 13.0838 | 9.3613 | 17.0838 | 28.1676 | 41.2514 | 6.7325 | 9.3713 | 8.7225 | 7.7225 | 11.0838 | 13.0838 | 9.3713 | 17.0938 | 28.1776 | 41.2614 | 0.01
3.4789 | 7.7395 | 5.4789 | 4.4789 | 6.2184 | 8.2184 | 7.7395 | 12.2184 | 18.4368 | 26.6552 | 3.4889 | 7.7495 | 5.4789 | 4.4789 | 6.2184 | 8.2184 | 7.7495 | 12.2284 | 18.4468 | 26.6652 | 0.01
6.17 | 9.085 | 8.17 | 7.17 | 10.255 | 12.255 | 9.085 | 16.255 | 26.51 | 38.765 | 6.18 | 9.095 | 8.17 | 7.17 | 10.255 | 12.255 | 9.095 | 16.265 | 26.52 | 38.775 | 0.01
7.0712 | 9.5356 | 9.0712 | 8.0712 | 11.6069 | 13.6069 | 9.5356 | 17.6069 | 29.2137 | 42.8206 | 7.0812 | 9.5456 | 9.0712 | 8.0712 | 11.6069 | 13.6069 | 9.5456 | 17.6169 | 29.2237 | 42.8306 | 0.01
4.6825 | 8.3413 | 6.6825 | 5.6825 | 8.0238 | 10.0238 | 8.3413 | 14.0238 | 22.0475 | 32.0713 | 4.6925 | 8.3513 | 6.6825 | 5.6825 | 8.0238 | 10.0238 | 8.3513 | 14.0338 | 22.0575 | 32.0813 | 0.01
4.7503 | 8.3752 | 6.7503 | 5.7503 | 8.1255 | 10.1255 | 8.3752 | 14.1255 | 22.251 | 32.3765 | 4.7603 | 8.3852 | 6.7503 | 5.7503 | 8.1255 | 10.1255 | 8.3852 | 14.1355 | 22.261 | 32.3865 | 0.01
5.1509 | 8.5755 | 7.1509 | 6.1509 | 8.7264 | 10.7264 | 8.5755 | 14.7264 | 23.4527 | 34.1791 | 5.1609 | 8.5855 | 7.1509 | 6.1509 | 8.7264 | 10.7264 | 8.5855 | 14.7364 | 23.4627 | 34.1891 | 0.01
3.943 | 7.9715 | 5.943 | 4.943 | 6.9145 | 8.9145 | 7.9715 | 12.9145 | 19.829 | 28.7435 | 3.953 | 7.9815 | 5.943 | 4.943 | 6.9145 | 8.9145 | 7.9815 | 12.9245 | 19.839 | 28.7535 | 0.01
4.7658 | 8.3829 | 6.7658 | 5.7658 | 8.1487 | 10.1487 | 8.3829 | 14.1487 | 22.2975 | 32.4462 | 4.7758 | 8.3929 | 6.7658 | 5.7658 | 8.1487 | 10.1487 | 8.3929 | 14.1587 | 22.3075 | 32.4562 | 0.01
4.0394 | 8.0197 | 6.0394 | 5.0394 | 7.0591 | 9.0591 | 8.0197 | 13.0591 | 20.1183 | 29.1774 | 4.0494 | 8.0297 | 6.0394 | 5.0394 | 7.0591 | 9.0591 | 8.0297 | 13.0691 | 20.1283 | 29.1874 | 0.01
5.853 | 8.9265 | 7.853 | 6.853 | 9.7796 | 11.7796 | 8.9265 | 15.7796 | 25.5591 | 37.3387 | 5.863 | 8.9365 | 7.853 | 6.853 | 9.7796 | 11.7796 | 8.9365 | 15.7896 | 25.5691 | 37.3487 | 0.01
4.7804 | 8.3902 | 6.7804 | 5.7804 | 8.1706 | 10.1706 | 8.3902 | 14.1706 | 22.3412 | 32.5118 | 4.7904 | 8.4002 | 6.7804 | 5.7804 | 8.1706 | 10.1706 | 8.4002 | 14.1806 | 22.3512 | 32.5218 | 0.01
6.723 | 9.3615 | 8.723 | 7.723 | 11.0845 | 13.0845 | 9.3615 | 17.0845 | 28.1691 | 41.2536 | 6.733 | 9.3715 | 8.723 | 7.723 | 11.0845 | 13.0845 | 9.3715 | 17.0945 | 28.1791 | 41.2636 | 0.01
6.7678 | 9.3839 | 8.7678 | 7.7678 | 11.1517 | 13.1517 | 9.3839 | 17.1517 | 28.3035 | 41.4552 | 6.7778 | 9.3939 | 8.7678 | 7.7678 | 11.1517 | 13.1517 | 9.3939 | 17.1617 | 28.3135 | 41.4652 | 0.01
7.4987 | 9.7493 | 9.4987 | 8.4987 | 12.248 | 14.248 | 9.7493 | 18.248 | 30.4961 | 44.7441 | 7.5087 | 9.7593 | 9.4987 | 8.4987 | 12.248 | 14.248 | 9.7593 | 18.258 | 30.5061 | 44.7541 | 0.01
7.5272 | 9.7636 | 9.5272 | 8.5272 | 12.2908 | 14.2908 | 9.7636 | 18.2908 | 30.5815 | 44.8723 | 7.5372 | 9.7736 | 9.5272 | 8.5272 | 12.2908 | 14.2908 | 9.7736 | 18.3008 | 30.5915 | 44.8823 | 0.01
5.9533 | 8.9766 | 7.9533 | 6.9533 | 9.9299 | 11.9299 | 8.9766 | 15.9299 | 25.8599 | 37.7898 | 5.9633 | 8.9866 | 7.9533 | 6.9533 | 9.9299 | 11.9299 | 8.9866 | 15.9399 | 25.8699 | 37.7998 | 0.01
8.9004 | 10.4502 | 10.9004 | 9.9004 | 14.3506 | 16.3506 | 10.4502 | 20.3506 | 34.7012 | 51.0517 | 8.9104 | 10.4602 | 10.9004 | 9.9004 | 14.3506 | 16.3506 | 10.4602 | 20.3606 | 34.7112 | 51.0617 | 0.01
6.7745 | 9.3873 | 8.7745 | 7.7745 | 11.1618 | 13.1618 | 9.3873 | 17.1618 | 28.3236 | 41.4854 | 6.7845 | 9.3973 | 8.7745 | 7.7745 | 11.1618 | 13.1618 | 9.3973 | 17.1718 | 28.3336 | 41.4954 | 0.01
6.78 | 9.39 | 8.78 | 7.78 | 11.1701 | 13.1701 | 9.39 | 17.1701 | 28.3401 | 41.5102 | 6.79 | 9.4 | 8.78 | 7.78 | 11.1701 | 13.1701 | 9.4 | 17.1801 | 28.3501 | 41.5202 | 0.01
7.4491 | 9.7245 | 9.4491 | 8.4491 | 12.1736 | 14.1736 | 9.7245 | 18.1736 | 30.3472 | 44.5207 | 7.4591 | 9.7345 | 9.4491 | 8.4491 | 12.1736 | 14.1736 | 9.7345 | 18.1836 | 30.3572 | 44.5307 | 0.01
8.8211 | 10.4105 | 10.8211 | 9.8211 | 14.2316 | 16.2316 | 10.4105 | 20.2316 | 34.4633 | 50.6949 | 8.8311 | 10.4205 | 10.8211 | 9.8211 | 14.2316 | 16.2316 | 10.4205 | 20.2416 | 34.4733 | 50.7049 | 0.01
2.8291 | 7.4146 | 4.8291 | 3.8291 | 5.2437 | 7.2437 | 7.4146 | 11.2437 | 16.4873 | 23.731 | 2.8391 | 7.4246 | 4.8291 | 3.8291 | 5.2437 | 7.2437 | 7.4246 | 11.2537 | 16.4973 | 23.741 | 0.01
5.8259 | 8.9129 | 7.8259 | 6.8259 | 9.7388 | 11.7388 | 8.9129 | 15.7388 | 25.4776 | 37.2164 | 5.8359 | 8.9229 | 7.8259 | 6.8259 | 9.7388 | 11.7388 | 8.9229 | 15.7488 | 25.4876 | 37.2264 | 0.01
5.7602 | 8.8801 | 7.7602 | 6.7602 | 9.6404 | 11.6404 | 8.8801 | 15.6404 | 25.2807 | 36.9211 | 5.7702 | 8.8901 | 7.7602 | 6.7602 | 9.6404 | 11.6404 | 8.8901 | 15.6504 | 25.2907 | 36.9311 | 0.01
6.6595 | 9.3297 | 8.6595 | 7.6595 | 10.9892 | 12.9892 | 9.3297 | 16.9892 | 27.9784 | 40.9675 | 6.6695 | 9.3397 | 8.6595 | 7.6595 | 10.9892 | 12.9892 | 9.3397 | 16.9992 | 27.9884 | 40.9775 | 0.01
8.6011 | 10.3006 | 10.6011 | 9.6011 | 13.9017 | 15.9017 | 10.3006 | 19.9017 | 33.8033 | 49.705 | 8.6111 | 10.3106 | 10.6011 | 9.6011 | 13.9017 | 15.9017 | 10.3106 | 19.9117 | 33.8133 | 49.715 | 0.01
6.848 | 9.424 | 8.848 | 7.848 | 11.272 | 13.272 | 9.424 | 17.272 | 28.5439 | 41.8159 | 6.858 | 9.434 | 8.848 | 7.848 | 11.272 | 13.272 | 9.434 | 17.282 | 28.5539 | 41.8259 | 0.01
5.4812 | 8.7406 | 7.4812 | 6.4812 | 9.2218 | 11.2218 | 8.7406 | 15.2218 | 24.4437 | 35.6655 | 5.4912 | 8.7506 | 7.4812 | 6.4812 | 9.2218 | 11.2218 | 8.7506 | 15.2318 | 24.4537 | 35.6755 | 0.01
6.5819 | 9.2909 | 8.5819 | 7.5819 | 10.8728 | 12.8728 | 9.2909 | 16.8728 | 27.7456 | 40.6184 | 6.5919 | 9.3009 | 8.5819 | 7.5819 | 10.8728 | 12.8728 | 9.3009 | 16.8828 | 27.7556 | 40.6284 | 0.01
3.0966 | 7.5483 | 5.0966 | 4.0966 | 5.6448 | 7.6448 | 7.5483 | 11.6448 | 17.2897 | 24.9345 | 3.1066 | 7.5583 | 5.0966 | 4.0966 | 5.6448 | 7.6448 | 7.5583 | 11.6548 | 17.2997 | 24.9445 | 0.01
7.5203 | 9.7602 | 9.5203 | 8.5203 | 12.2805 | 14.2805 | 9.7602 | 18.2805 | 30.561 | 44.8416 | 7.5303 | 9.7702 | 9.5203 | 8.5203 | 12.2805 | 14.2805 | 9.7702 | 18.2905 | 30.571 | 44.8516 | 0.01
5.3622 | 8.6811 | 7.3622 | 6.3622 | 9.0433 | 11.0433 | 8.6811 | 15.0433 | 24.0867 | 35.13 | 5.3722 | 8.6911 | 7.3622 | 6.3622 | 9.0433 | 11.0433 | 8.6911 | 15.0533 | 24.0967 | 35.14 | 0.01
3.0589 | 7.5295 | 5.0589 | 4.0589 | 5.5884 | 7.5884 | 7.5295 | 11.5884 | 17.1768 | 24.7653 | 3.0689 | 7.5395 | 5.0589 | 4.0589 | 5.5884 | 7.5884 | 7.5395 | 11.5984 | 17.1868 | 24.7753 | 0.01
5.5666 | 8.7833 | 7.5666 | 6.5666 | 9.3498 | 11.3498 | 8.7833 | 15.3498 | 24.6997 | 36.0495 | 5.5766 | 8.7933 | 7.5666 | 6.5666 | 9.3498 | 11.3498 | 8.7933 | 15.3598 | 24.7097 | 36.0595 | 0.01
7.0962 | 9.5481 | 9.0962 | 8.0962 | 11.6442 | 13.6442 | 9.5481 | 17.6442 | 29.2885 | 42.9327 | 7.1062 | 9.5581 | 9.0962 | 8.0962 | 11.6442 | 13.6442 | 9.5581 | 17.6542 | 29.2985 | 42.9427 | 0.01
5.3982 | 8.6991 | 7.3982 | 6.3982 | 9.0973 | 11.0973 | 8.6991 | 15.0973 | 24.1946 | 35.2919 | 5.4082 | 8.7091 | 7.3982 | 6.3982 | 9.0973 | 11.0973 | 8.7091 | 15.1073 | 24.2046 | 35.3019 | 0.01
9.911 | 10.9555 | 11.911 | 10.911 | 15.8666 | 17.8666 | 10.9555 | 21.8666 | 37.7331 | 55.5997 | 9.921 | 10.9655 | 11.911 | 10.911 | 15.8666 | 17.8666 | 10.9655 | 21.8766 | 37.7431 | 55.6097 | 0.01
5.7213 | 8.8606 | 7.7213 | 6.7213 | 9.5819 | 11.5819 | 8.8606 | 15.5819 | 25.1638 | 36.7458 | 5.7313 | 8.8706 | 7.7213 | 6.7213 | 9.5819 | 11.5819 | 8.8706 | 15.5919 | 25.1738 | 36.7558 | 0.01
3.4139 | 7.7069 | 5.4139 | 4.4139 | 6.1208 | 8.1208 | 7.7069 | 12.1208 | 18.2416 | 26.3625 | 3.4239 | 7.7169 | 5.4139 | 4.4139 | 6.1208 | 8.1208 | 7.7169 | 12.1308 | 18.2516 | 26.3725 | 0.01
1.2177 | 6.6089 | 3.2177 | 2.2177 | 2.8266 | 4.8266 | 6.6089 | 8.8266 | 11.6532 | 16.4798 | 1.2277 | 6.6189 | 3.2177 | 2.2177 | 2.8266 | 4.8266 | 6.6189 | 8.8366 | 11.6632 | 16.4898 | 0.01
3.9393 | 7.9697 | 5.9393 | 4.9393 | 6.909 | 8.909 | 7.9697 | 12.909 | 19.818 | 28.727 | 3.9493 | 7.9797 | 5.9393 | 4.9393 | 6.909 | 8.909 | 7.9797 | 12.919 | 19.828 | 28.737 | 0.01
1.9111 | 6.9556 | 3.9111 | 2.9111 | 3.8667 | 5.8667 | 6.9556 | 9.8667 | 13.7333 | 19.6 | 1.9211 | 6.9656 | 3.9111 | 2.9111 | 3.8667 | 5.8667 | 6.9656 | 9.8767 | 13.7433 | 19.61 | 0.01
7.5561 | 9.778 | 9.5561 | 8.5561 | 12.3341 | 14.3341 | 9.778 | 18.3341 | 30.6683 | 45.0024 | 7.5661 | 9.788 | 9.5561 | 8.5561 | 12.3341 | 14.3341 | 9.788 | 18.3441 | 30.6783 | 45.0124 | 0.01
6.1834 | 9.0917 | 8.1834 | 7.1834 | 10.2751 | 12.2751 | 9.0917 | 16.2751 | 26.5503 | 38.8254 | 6.1934 | 9.1017 | 8.1834 | 7.1834 | 10.2751 | 12.2751 | 9.1017 | 16.2851 | 26.5603 | 38.8354 | 0.01
6.4385 | 9.2192 | 8.4385 | 7.4385 | 10.6577 | 12.6577 | 9.2192 | 16.6577 | 27.3155 | 39.9732 | 6.4485 | 9.2292 | 8.4385 | 7.4385 | 10.6577 | 12.6577 | 9.2292 | 16.6677 | 27.3255 | 39.9832 | 0.01
8.0349 | 10.0174 | 10.0349 | 9.0349 | 13.0523 | 15.0523 | 10.0174 | 19.0523 | 32.1047 | 47.157 | 8.0449 | 10.0274 | 10.0349 | 9.0349 | 13.0523 | 15.0523 | 10.0274 | 19.0623 | 32.1147 | 47.167 | 0.01
7.867 | 9.9335 | 9.867 | 8.867 | 12.8004 | 14.8004 | 9.9335 | 18.8004 | 31.6009 | 46.4013 | 7.877 | 9.9435 | 9.867 | 8.867 | 12.8004 | 14.8004 | 9.9435 | 18.8104 | 31.6109 | 46.4113 | 0.01
9.377 | 10.6885 | 11.377 | 10.377 | 15.0655 | 17.0655 | 10.6885 | 21.0655 | 36.131 | 53.1965 | 9.387 | 10.6985 | 11.377 | 10.377 | 15.0655 | 17.0655 | 10.6985 | 21.0755 | 36.141 | 53.2065 | 0.01
6.6239 | 9.3119 | 8.6239 | 7.6239 | 10.9358 | 12.9358 | 9.3119 | 16.9358 | 27.8716 | 40.8073 | 6.6339 | 9.3219 | 8.6239 | 7.6239 | 10.9358 | 12.9358 | 9.3219 | 16.9458 | 27.8816 | 40.8173 | 0.01
6.2069 | 9.1035 | 8.2069 | 7.2069 | 10.3104 | 12.3104 | 9.1035 | 16.3104 | 26.6207 | 38.9311 | 6.2169 | 9.1135 | 8.2069 | 7.2069 | 10.3104 | 12.3104 | 9.1135 | 16.3204 | 26.6307 | 38.9411 | 0.01
9.2106 | 10.6053 | 11.2106 | 10.2106 | 14.816 | 16.816 | 10.6053 | 20.816 | 35.6319 | 52.4479 | 9.2206 | 10.6153 | 11.2106 | 10.2106 | 14.816 | 16.816 | 10.6153 | 20.826 | 35.6419 | 52.4579 | 0.01
8.1358 | 10.0679 | 10.1358 | 9.1358 | 13.2038 | 15.2038 | 10.0679 | 19.2038 | 32.4075 | 47.6113 | 8.1458 | 10.0779 | 10.1358 | 9.1358 | 13.2038 | 15.2038 | 10.0779 | 19.2138 | 32.4175 | 47.6213 | 0.01
5.0617 | 8.5309 | 7.0617 | 6.0617 | 8.5926 | 10.5926 | 8.5309 | 14.5926 | 23.1852 | 33.7778 | 5.0717 | 8.5409 | 7.0617 | 6.0617 | 8.5926 | 10.5926 | 8.5409 | 14.6026 | 23.1952 | 33.7878 | 0.01
6.6753 | 9.3376 | 8.6753 | 7.6753 | 11.0129 | 13.0129 | 9.3376 | 17.0129 | 28.0258 | 41.0388 | 6.6853 | 9.3476 | 8.6753 | 7.6753 | 11.0129 | 13.0129 | 9.3476 | 17.0229 | 28.0358 | 41.0488 | 0.01
3.4542 | 7.7271 | 5.4542 | 4.4542 | 6.1813 | 8.1813 | 7.7271 | 12.1813 | 18.3625 | 26.5438 | 3.4642 | 7.7371 | 5.4542 | 4.4542 | 6.1813 | 8.1813 | 7.7371 | 12.1913 | 18.3725 | 26.5538 | 0.01
5.1056 | 8.5528 | 7.1056 | 6.1056 | 8.6584 | 10.6584 | 8.5528 | 14.6584 | 23.3169 | 33.9753 | 5.1156 | 8.5628 | 7.1056 | 6.1056 | 8.6584 | 10.6584 | 8.5628 | 14.6684 | 23.3269 | 33.9853 | 0.01
3.5613 | 7.7807 | 5.5613 | 4.5613 | 6.342 | 8.342 | 7.7807 | 12.342 | 18.684 | 27.026 | 3.5713 | 7.7907 | 5.5613 | 4.5613 | 6.342 | 8.342 | 7.7907 | 12.352 | 18.694 | 27.036 | 0.01
6.4972 | 9.2486 | 8.4972 | 7.4972 | 10.7457 | 12.7457 | 9.2486 | 16.7457 | 27.4915 | 40.2372 | 6.5072 | 9.2586 | 8.4972 | 7.4972 | 10.7457 | 12.7457 | 9.2586 | 16.7557 | 27.5015 | 40.2472 | 0.01
4.3738 | 8.1869 | 6.3738 | 5.3738 | 7.5607 | 9.5607 | 8.1869 | 13.5607 | 21.1213 | 30.682 | 4.3838 | 8.1969 | 6.3738 | 5.3738 | 7.5607 | 9.5607 | 8.1969 | 13.5707 | 21.1313 | 30.692 | 0.01
3.9362 | 7.9681 | 5.9362 | 4.9362 | 6.9044 | 8.9044 | 7.9681 | 12.9044 | 19.8087 | 28.7131 | 3.9462 | 7.9781 | 5.9362 | 4.9362 | 6.9044 | 8.9044 | 7.9781 | 12.9144 | 19.8187 | 28.7231 | 0.01
8.9776 | 10.4888 | 10.9776 | 9.9776 | 14.4663 | 16.4663 | 10.4888 | 20.4663 | 34.9327 | 51.399 | 8.9876 | 10.4988 | 10.9776 | 9.9776 | 14.4663 | 16.4663 | 10.4988 | 20.4763 | 34.9427 | 51.409 | 0.01
6.1982 | 9.0991 | 8.1982 | 7.1982 | 10.2972 | 12.2972 | 9.0991 | 16.2972 | 26.5945 | 38.8917 | 6.2082 | 9.1091 | 8.1982 | 7.1982 | 10.2972 | 12.2972 | 9.1091 | 16.3072 | 26.6045 | 38.9017 | 0.01
7.228 | 9.614 | 9.228 | 8.228 | 11.842 | 13.842 | 9.614 | 17.842 | 29.6841 | 43.5261 | 7.238 | 9.624 | 9.228 | 8.228 | 11.842 | 13.842 | 9.624 | 17.852 | 29.6941 | 43.5361 | 0.01
7.6249 | 9.8125 | 9.6249 | 8.6249 | 12.4374 | 14.4374 | 9.8125 | 18.4374 | 30.8748 | 45.3122 | 7.6349 | 9.8225 | 9.6249 | 8.6249 | 12.4374 | 14.4374 | 9.8225 | 18.4474 | 30.8848 | 45.3222 | 0.01
7.173 | 9.5865 | 9.173 | 8.173 | 11.7596 | 13.7596 | 9.5865 | 17.7596 | 29.5191 | 43.2787 | 7.183 | 9.5965 | 9.173 | 8.173 | 11.7596 | 13.7596 | 9.5965 | 17.7696 | 29.5291 | 43.2887 | 0.01
7.9303 | 9.9652 | 9.9303 | 8.9303 | 12.8955 | 14.8955 | 9.9652 | 18.8955 | 31.791 | 46.6865 | 7.9403 | 9.9752 | 9.9303 | 8.9303 | 12.8955 | 14.8955 | 9.9752 | 18.9055 | 31.801 | 46.6965 | 0.01
5.3469 | 8.6734 | 7.3469 | 6.3469 | 9.0203 | 11.0203 | 8.6734 | 15.0203 | 24.0406 | 35.0609 | 5.3569 | 8.6834 | 7.3469 | 6.3469 | 9.0203 | 11.0203 | 8.6834 | 15.0303 | 24.0506 | 35.0709 | 0.01
4.0556 | 8.0278 | 6.0556 | 5.0556 | 7.0835 | 9.0835 | 8.0278 | 13.0835 | 20.1669 | 29.2504 | 4.0656 | 8.0378 | 6.0556 | 5.0556 | 7.0835 | 9.0835 | 8.0378 | 13.0935 | 20.1769 | 29.2604 | 0.01
4.5911 | 8.2955 | 6.5911 | 5.5911 | 7.8866 | 9.8866 | 8.2955 | 13.8866 | 21.7732 | 31.6599 | 4.6011 | 8.3055 | 6.5911 | 5.5911 | 7.8866 | 9.8866 | 8.3055 | 13.8966 | 21.7832 | 31.6699 | 0.01
4.982 | 8.491 | 6.982 | 5.982 | 8.473 | 10.473 | 8.491 | 14.473 | 22.946 | 33.419 | 4.992 | 8.501 | 6.982 | 5.982 | 8.473 | 10.473 | 8.501 | 14.483 | 22.956 | 33.429 | 0.01
5.7233 | 8.8617 | 7.7233 | 6.7233 | 9.585 | 11.585 | 8.8617 | 15.585 | 25.1699 | 36.7549 | 5.7333 | 8.8717 | 7.7233 | 6.7233 | 9.585 | 11.585 | 8.8717 | 15.595 | 25.1799 | 36.7649 | 0.01
8.0559 | 10.0279 | 10.0559 | 9.0559 | 13.0838 | 15.0838 | 10.0279 | 19.0838 | 32.1677 | 47.2515 | 8.0659 | 10.0379 | 10.0559 | 9.0559 | 13.0838 | 15.0838 | 10.0379 | 19.0938 | 32.1777 | 47.2615 | 0.01
6.1811 | 9.0906 | 8.1811 | 7.1811 | 10.2717 | 12.2717 | 9.0906 | 16.2717 | 26.5433 | 38.815 | 6.1911 | 9.1006 | 8.1811 | 7.1811 | 10.2717 | 12.2717 | 9.1006 | 16.2817 | 26.5533 | 38.825 | 0.01
7.9025 | 9.9513 | 9.9025 | 8.9025 | 12.8538 | 14.8538 | 9.9513 | 18.8538 | 31.7076 | 46.5614 | 7.9125 | 9.9613 | 9.9025 | 8.9025 | 12.8538 | 14.8538 | 9.9613 | 18.8638 | 31.7176 | 46.5714 | 0.01
5.791 | 8.8955 | 7.791 | 6.791 | 9.6865 | 11.6865 | 8.8955 | 15.6865 | 25.373 | 37.0595 | 5.801 | 8.9055 | 7.791 | 6.791 | 9.6865 | 11.6865 | 8.9055 | 15.6965 | 25.383 | 37.0695 | 0.01
3.1031 | 7.5516 | 5.1031 | 4.1031 | 5.6547 | 7.6547 | 7.5516 | 11.6547 | 17.3094 | 24.9641 | 3.1131 | 7.5616 | 5.1031 | 4.1031 | 5.6547 | 7.6547 | 7.5616 | 11.6647 | 17.3194 | 24.9741 | 0.01
5.9244 | 8.9622 | 7.9244 | 6.9244 | 9.8866 | 11.8866 | 8.9622 | 15.8866 | 25.7733 | 37.6599 | 5.9344 | 8.9722 | 7.9244 | 6.9244 | 9.8866 | 11.8866 | 8.9722 | 15.8966 | 25.7833 | 37.6699 | 0.01
4.3449 | 8.1724 | 6.3449 | 5.3449 | 7.5173 | 9.5173 | 8.1724 | 13.5173 | 21.0347 | 30.552 | 4.3549 | 8.1824 | 6.3449 | 5.3449 | 7.5173 | 9.5173 | 8.1824 | 13.5273 | 21.0447 | 30.562 | 0.01
9.9817 | 10.9909 | 11.9817 | 10.9817 | 15.9726 | 17.9726 | 10.9909 | 21.9726 | 37.9452 | 55.9178 | 9.9917 | 11.0009 | 11.9817 | 10.9817 | 15.9726 | 17.9726 | 11.0009 | 21.9826 | 37.9552 | 55.9278 | 0.01
4.8054 | 8.4027 | 6.8054 | 5.8054 | 8.2081 | 10.2081 | 8.4027 | 14.2081 | 22.4162 | 32.6242 | 4.8154 | 8.4127 | 6.8054 | 5.8054 | 8.2081 | 10.2081 | 8.4127 | 14.2181 | 22.4262 | 32.6342 | 0.01
5.8545 | 8.9272 | 7.8545 | 6.8545 | 9.7817 | 11.7817 | 8.9272 | 15.7817 | 25.5634 | 37.3451 | 5.8645 | 8.9372 | 7.8545 | 6.8545 | 9.7817 | 11.7817 | 8.9372 | 15.7917 | 25.5734 | 37.3551 | 0.01
2.5602 | 7.2801 | 4.5602 | 3.5602 | 4.8403 | 6.8403 | 7.2801 | 10.8403 | 15.6807 | 22.521 | 2.5702 | 7.2901 | 4.5602 | 3.5602 | 4.8403 | 6.8403 | 7.2901 | 10.8503 | 15.6907 | 22.531 | 0.01
3.4258 | 7.7129 | 5.4258 | 4.4258 | 6.1388 | 8.1388 | 7.7129 | 12.1388 | 18.2775 | 26.4163 | 3.4358 | 7.7229 | 5.4258 | 4.4258 | 6.1388 | 8.1388 | 7.7229 | 12.1488 | 18.2875 | 26.4263 | 0.01
5.7932 | 8.8966 | 7.7932 | 6.7932 | 9.6897 | 11.6897 | 8.8966 | 15.6897 | 25.3795 | 37.0692 | 5.8032 | 8.9066 | 7.7932 | 6.7932 | 9.6897 | 11.6897 | 8.9066 | 15.6997 | 25.3895 | 37.0792 | 0.01
4.951 | 8.4755 | 6.951 | 5.951 | 8.4265 | 10.4265 | 8.4755 | 14.4265 | 22.8529 | 33.2794 | 4.961 | 8.4855 | 6.951 | 5.951 | 8.4265 | 10.4265 | 8.4855 | 14.4365 | 22.8629 | 33.2894 | 0.01
5.6438 | 8.8219 | 7.6438 | 6.6438 | 9.4657 | 11.4657 | 8.8219 | 15.4657 | 24.9315 | 36.3972 | 5.6538 | 8.8319 | 7.6438 | 6.6438 | 9.4657 | 11.4657 | 8.8319 | 15.4757 | 24.9415 | 36.4072 | 0.01
6.9783 | 9.4891 | 8.9783 | 7.9783 | 11.4674 | 13.4674 | 9.4891 | 17.4674 | 28.9348 | 42.4023 | 6.9883 | 9.4991 | 8.9783 | 7.9783 | 11.4674 | 13.4674 | 9.4991 | 17.4774 | 28.9448 | 42.4123 | 0.01
10.192 | 11.096 | 12.192 | 11.192 | 16.288 | 18.288 | 11.096 | 22.288 | 38.576 | 56.864 | 10.202 | 11.106 | 12.192 | 11.192 | 16.288 | 18.288 | 11.106 | 22.298 | 38.586 | 56.874 | 0.01
7.611 | 9.8055 | 9.611 | 8.611 | 12.4165 | 14.4165 | 9.8055 | 18.4165 | 30.8329 | 45.2494 | 7.621 | 9.8155 | 9.611 | 8.611 | 12.4165 | 14.4165 | 9.8155 | 18.4265 | 30.8429 | 45.2594 | 0.01
10.7379 | 11.3689 | 12.7379 | 11.7379 | 17.1068 | 19.1068 | 11.3689 | 23.1068 | 40.2137 | 59.3205 | 10.7479 | 11.3789 | 12.7379 | 11.7379 | 17.1068 | 19.1068 | 11.3789 | 23.1168 | 40.2237 | 59.3305 | 0.01
3.3134 | 7.6567 | 5.3134 | 4.3134 | 5.9702 | 7.9702 | 7.6567 | 11.9702 | 17.9403 | 25.9105 | 3.3234 | 7.6667 | 5.3134 | 4.3134 | 5.9702 | 7.9702 | 7.6667 | 11.9802 | 17.9503 | 25.9205 | 0.01
7.374 | 9.687 | 9.374 | 8.374 | 12.061 | 14.061 | 9.687 | 18.061 | 30.1219 | 44.1829 | 7.384 | 9.697 | 9.374 | 8.374 | 12.061 | 14.061 | 9.697 | 18.071 | 30.1319 | 44.1929 | 0.01
7.0434 | 9.5217 | 9.0434 | 8.0434 | 11.5652 | 13.5652 | 9.5217 | 17.5652 | 29.1303 | 42.6955 | 7.0534 | 9.5317 | 9.0434 | 8.0434 | 11.5652 | 13.5652 | 9.5317 | 17.5752 | 29.1403 | 42.7055 | 0.01
4.3583 | 8.1792 | 6.3583 | 5.3583 | 7.5375 | 9.5375 | 8.1792 | 13.5375 | 21.075 | 30.6124 | 4.3683 | 8.1892 | 6.3583 | 5.3583 | 7.5375 | 9.5375 | 8.1892 | 13.5475 | 21.085 | 30.6224 | 0.01
2.3368 | 7.1684 | 4.3368 | 3.3368 | 4.5052 | 6.5052 | 7.1684 | 10.5052 | 15.0104 | 21.5156 | 2.3468 | 7.1784 | 4.3368 | 3.3368 | 4.5052 | 6.5052 | 7.1784 | 10.5152 | 15.0204 | 21.5256 | 0.01
3.7904 | 7.8952 | 5.7904 | 4.7904 | 6.6856 | 8.6856 | 7.8952 | 12.6856 | 19.3711 | 28.0567 | 3.8004 | 7.9052 | 5.7904 | 4.7904 | 6.6856 | 8.6856 | 7.9052 | 12.6956 | 19.3811 | 28.0667 | 0.01
6.4113 | 9.2057 | 8.4113 | 7.4113 | 10.617 | 12.617 | 9.2057 | 16.617 | 27.2339 | 39.8509 | 6.4213 | 9.2157 | 8.4113 | 7.4113 | 10.617 | 12.617 | 9.2157 | 16.627 | 27.2439 | 39.8609 | 0.01
7.4944 | 9.7472 | 9.4944 | 8.4944 | 12.2416 | 14.2416 | 9.7472 | 18.2416 | 30.4833 | 44.7249 | 7.5044 | 9.7572 | 9.4944 | 8.4944 | 12.2416 | 14.2416 | 9.7572 | 18.2516 | 30.4933 | 44.7349 | 0.01
9.8897 | 10.9448 | 11.8897 | 10.8897 | 15.8345 | 17.8345 | 10.9448 | 21.8345 | 37.6691 | 55.5036 | 9.8997 | 10.9548 | 11.8897 | 10.8897 | 15.8345 | 17.8345 | 10.9548 | 21.8445 | 37.6791 | 55.5136 | 0.01
7.3698 | 9.6849 | 9.3698 | 8.3698 | 12.0547 | 14.0547 | 9.6849 | 18.0547 | 30.1095 | 44.1642 | 7.3798 | 9.6949 | 9.3698 | 8.3698 | 12.0547 | 14.0547 | 9.6949 | 18.0647 | 30.1195 | 44.1742 | 0.01
7.1577 | 9.5789 | 9.1577 | 8.1577 | 11.7366 | 13.7366 | 9.5789 | 17.7366 | 29.4732 | 43.2099 | 7.1677 | 9.5889 | 9.1577 | 8.1577 | 11.7366 | 13.7366 | 9.5889 | 17.7466 | 29.4832 | 43.2199 | 0.01
6.2896 | 9.1448 | 8.2896 | 7.2896 | 10.4344 | 12.4344 | 9.1448 | 16.4344 | 26.8688 | 39.3032 | 6.2996 | 9.1548 | 8.2896 | 7.2896 | 10.4344 | 12.4344 | 9.1548 | 16.4444 | 26.8788 | 39.3132 | 0.01
1.4096 | 6.7048 | 3.4096 | 2.4096 | 3.1144 | 5.1144 | 6.7048 | 9.1144 | 12.2288 | 17.3432 | 1.4196 | 6.7148 | 3.4096 | 2.4096 | 3.1144 | 5.1144 | 6.7148 | 9.1244 | 12.2388 | 17.3532 | 0.01
6.2053 | 9.1027 | 8.2053 | 7.2053 | 10.308 | 12.308 | 9.1027 | 16.308 | 26.6159 | 38.9239 | 6.2153 | 9.1127 | 8.2053 | 7.2053 | 10.308 | 12.308 | 9.1127 | 16.318 | 26.6259 | 38.9339 | 0.01
6.5827 | 9.2914 | 8.5827 | 7.5827 | 10.8741 | 12.8741 | 9.2914 | 16.8741 | 27.7482 | 40.6223 | 6.5927 | 9.3014 | 8.5827 | 7.5827 | 10.8741 | 12.8741 | 9.3014 | 16.8841 | 27.7582 | 40.6323 | 0.01
7.7941 | 9.8971 | 9.7941 | 8.7941 | 12.6912 | 14.6912 | 9.8971 | 18.6912 | 31.3824 | 46.0735 | 7.8041 | 9.9071 | 9.7941 | 8.7941 | 12.6912 | 14.6912 | 9.9071 | 18.7012 | 31.3924 | 46.0835 | 0.01
5.123 | 8.5615 | 7.123 | 6.123 | 8.6845 | 10.6845 | 8.5615 | 14.6845 | 23.369 | 34.0534 | 5.133 | 8.5715 | 7.123 | 6.123 | 8.6845 | 10.6845 | 8.5715 | 14.6945 | 23.379 | 34.0634 | 0.01
8.317 | 10.1585 | 10.317 | 9.317 | 13.4755 | 15.4755 | 10.1585 | 19.4755 | 32.951 | 48.4265 | 8.327 | 10.1685 | 10.317 | 9.317 | 13.4755 | 15.4755 | 10.1685 | 19.4855 | 32.961 | 48.4365 | 0.01
4.1843 | 8.0921 | 6.1843 | 5.1843 | 7.2764 | 9.2764 | 8.0921 | 13.2764 | 20.5529 | 29.8293 | 4.1943 | 8.1021 | 6.1843 | 5.1843 | 7.2764 | 9.2764 | 8.1021 | 13.2864 | 20.5629 | 29.8393 | 0.01
5.9492 | 8.9746 | 7.9492 | 6.9492 | 9.9238 | 11.9238 | 8.9746 | 15.9238 | 25.8476 | 37.7714 | 5.9592 | 8.9846 | 7.9492 | 6.9492 | 9.9238 | 11.9238 | 8.9846 | 15.9338 | 25.8576 | 37.7814 | 0.01
4.4054 | 8.2027 | 6.4054 | 5.4054 | 7.6081 | 9.6081 | 8.2027 | 13.6081 | 21.2162 | 30.8244 | 4.4154 | 8.2127 | 6.4054 | 5.4054 | 7.6081 | 9.6081 | 8.2127 | 13.6181 | 21.2262 | 30.8344 | 0.01
8.0854 | 10.0427 | 10.0854 | 9.0854 | 13.1281 | 15.1281 | 10.0427 | 19.1281 | 32.2562 | 47.3843 | 8.0954 | 10.0527 | 10.0854 | 9.0854 | 13.1281 | 15.1281 | 10.0527 | 19.1381 | 32.2662 | 47.3943 | 0.01
5.5091 | 8.7545 | 7.5091 | 6.5091 | 9.2636 | 11.2636 | 8.7545 | 15.2636 | 24.5273 | 35.7909 | 5.5191 | 8.7645 | 7.5091 | 6.5091 | 9.2636 | 11.2636 | 8.7645 | 15.2736 | 24.5373 | 35.8009 | 0.01
3.5418 | 7.7709 | 5.5418 | 4.5418 | 6.3127 | 8.3127 | 7.7709 | 12.3127 | 18.6253 | 26.938 | 3.5518 | 7.7809 | 5.5418 | 4.5418 | 6.3127 | 8.3127 | 7.7809 | 12.3227 | 18.6353 | 26.948 | 0.01
6.5227 | 9.2613 | 8.5227 | 7.5227 | 10.784 | 12.784 | 9.2613 | 16.784 | 27.568 | 40.352 | 6.5327 | 9.2713 | 8.5227 | 7.5227 | 10.784 | 12.784 | 9.2713 | 16.794 | 27.578 | 40.362 | 0.01
9.9449 | 10.9724 | 11.9449 | 10.9449 | 15.9173 | 17.9173 | 10.9724 | 21.9173 | 37.8346 | 55.7519 | 9.9549 | 10.9824 | 11.9449 | 10.9449 | 15.9173 | 17.9173 | 10.9824 | 21.9273 | 37.8446 | 55.7619 | 0.01
8.8786 | 10.4393 | 10.8786 | 9.8786 | 14.3179 | 16.3179 | 10.4393 | 20.3179 | 34.6358 | 50.9537 | 8.8886 | 10.4493 | 10.8786 | 9.8786 | 14.3179 | 16.3179 | 10.4493 | 20.3279 | 34.6458 | 50.9637 | 0.01
8.9064 | 10.4532 | 10.9064 | 9.9064 | 14.3596 | 16.3596 | 10.4532 | 20.3596 | 34.7192 | 51.0788 | 8.9164 | 10.4632 | 10.9064 | 9.9064 | 14.3596 | 16.3596 | 10.4632 | 20.3696 | 34.7292 | 51.0888 | 0.01
6.8865 | 9.4433 | 8.8865 | 7.8865 | 11.3298 | 13.3298 | 9.4433 | 17.3298 | 28.6596 | 41.9895 | 6.8965 | 9.4533 | 8.8865 | 7.8865 | 11.3298 | 13.3298 | 9.4533 | 17.3398 | 28.6696 | 41.9995 | 0.01
3.7029 | 7.8515 | 5.7029 | 4.7029 | 6.5544 | 8.5544 | 7.8515 | 12.5544 | 19.1088 | 27.6632 | 3.7129 | 7.8615 | 5.7029 | 4.7029 | 6.5544 | 8.5544 | 7.8615 | 12.5644 | 19.1188 | 27.6732 | 0.01
4.0389 | 8.0194 | 6.0389 | 5.0389 | 7.0583 | 9.0583 | 8.0194 | 13.0583 | 20.1166 | 29.1749 | 4.0489 | 8.0294 | 6.0389 | 5.0389 | 7.0583 | 9.0583 | 8.0294 | 13.0683 | 20.1266 | 29.1849 | 0.01
4.993 | 8.4965 | 6.993 | 5.993 | 8.4894 | 10.4894 | 8.4965 | 14.4894 | 22.9789 | 33.4683 | 5.003 | 8.5065 | 6.993 | 5.993 | 8.4894 | 10.4894 | 8.5065 | 14.4994 | 22.9889 | 33.4783 | 0.01
7.5727 | 9.7864 | 9.5727 | 8.5727 | 12.3591 | 14.3591 | 9.7864 | 18.3591 | 30.7182 | 45.0774 | 7.5827 | 9.7964 | 9.5727 | 8.5727 | 12.3591 | 14.3591 | 9.7964 | 18.3691 | 30.7282 | 45.0874 | 0.01
6.7339 | 9.367 | 8.7339 | 7.7339 | 11.1009 | 13.1009 | 9.367 | 17.1009 | 28.2018 | 41.3028 | 6.7439 | 9.377 | 8.7339 | 7.7339 | 11.1009 | 13.1009 | 9.377 | 17.1109 | 28.2118 | 41.3128 | 0.01
8.9729 | 10.4864 | 10.9729 | 9.9729 | 14.4593 | 16.4593 | 10.4864 | 20.4593 | 34.9186 | 51.3779 | 8.9829 | 10.4964 | 10.9729 | 9.9729 | 14.4593 | 16.4593 | 10.4964 | 20.4693 | 34.9286 | 51.3879 | 0.01
5.0927 | 8.5463 | 7.0927 | 6.0927 | 8.639 | 10.639 | 8.5463 | 14.639 | 23.278 | 33.917 | 5.1027 | 8.5563 | 7.0927 | 6.0927 | 8.639 | 10.639 | 8.5563 | 14.649 | 23.288 | 33.927 | 0.01
7.9686 | 9.9843 | 9.9686 | 8.9686 | 12.9529 | 14.9529 | 9.9843 | 18.9529 | 31.9059 | 46.8588 | 7.9786 | 9.9943 | 9.9686 | 8.9686 | 12.9529 | 14.9529 | 9.9943 | 18.9629 | 31.9159 | 46.8688 | 0.01
4.0706 | 8.0353 | 6.0706 | 5.0706 | 7.1059 | 9.1059 | 8.0353 | 13.1059 | 20.2119 | 29.3178 | 4.0806 | 8.0453 | 6.0706 | 5.0706 | 7.1059 | 9.1059 | 8.0453 | 13.1159 | 20.2219 | 29.3278 | 0.01
6.7692 | 9.3846 | 8.7692 | 7.7692 | 11.1539 | 13.1539 | 9.3846 | 17.1539 | 28.3077 | 41.4616 | 6.7792 | 9.3946 | 8.7692 | 7.7692 | 11.1539 | 13.1539 | 9.3946 | 17.1639 | 28.3177 | 41.4716 | 0.01
4.3317 | 8.1659 | 6.3317 | 5.3317 | 7.4976 | 9.4976 | 8.1659 | 13.4976 | 20.9952 | 30.4928 | 4.3417 | 8.1759 | 6.3317 | 5.3317 | 7.4976 | 9.4976 | 8.1759 | 13.5076 | 21.0052 | 30.5028 | 0.01
7.3407 | 9.6703 | 9.3407 | 8.3407 | 12.011 | 14.011 | 9.6703 | 18.011 | 30.022 | 44.033 | 7.3507 | 9.6803 | 9.3407 | 8.3407 | 12.011 | 14.011 | 9.6803 | 18.021 | 30.032 | 44.043 | 0.01
2.2761 | 7.138 | 4.2761 | 3.2761 | 4.4141 | 6.4141 | 7.138 | 10.4141 | 14.8282 | 21.2423 | 2.2861 | 7.148 | 4.2761 | 3.2761 | 4.4141 | 6.4141 | 7.148 | 10.4241 | 14.8382 | 21.2523 | 0.01
3.6385 | 7.8193 | 5.6385 | 4.6385 | 6.4578 | 8.4578 | 7.8193 | 12.4578 | 18.9156 | 27.3733 | 3.6485 | 7.8293 | 5.6385 | 4.6385 | 6.4578 | 8.4578 | 7.8293 | 12.4678 | 18.9256 | 27.3833 | 0.01
6.3265 | 9.1632 | 8.3265 | 7.3265 | 10.4897 | 12.4897 | 9.1632 | 16.4897 | 26.9795 | 39.4692 | 6.3365 | 9.1732 | 8.3265 | 7.3265 | 10.4897 | 12.4897 | 9.1732 | 16.4997 | 26.9895 | 39.4792 | 0.01
4.4377 | 8.2189 | 6.4377 | 5.4377 | 7.6566 | 9.6566 | 8.2189 | 13.6566 | 21.3132 | 30.9698 | 4.4477 | 8.2289 | 6.4377 | 5.4377 | 7.6566 | 9.6566 | 8.2289 | 13.6666 | 21.3232 | 30.9798 | 0.01
4.4546 | 8.2273 | 6.4546 | 5.4546 | 7.682 | 9.682 | 8.2273 | 13.682 | 21.3639 | 31.0459 | 4.4646 | 8.2373 | 6.4546 | 5.4546 | 7.682 | 9.682 | 8.2373 | 13.692 | 21.3739 | 31.0559 | 0.01
3.5077 | 7.7539 | 5.5077 | 4.5077 | 6.2616 | 8.2616 | 7.7539 | 12.2616 | 18.5232 | 26.7847 | 3.5177 | 7.7639 | 5.5077 | 4.5077 | 6.2616 | 8.2616 | 7.7639 | 12.2716 | 18.5332 | 26.7947 | 0.01
6.1702 | 9.0851 | 8.1702 | 7.1702 | 10.2553 | 12.2553 | 9.0851 | 16.2553 | 26.5105 | 38.7658 | 6.1802 | 9.0951 | 8.1702 | 7.1702 | 10.2553 | 12.2553 | 9.0951 | 16.2653 | 26.5205 | 38.7758 | 0.01
4.9841 | 8.492 | 6.9841 | 5.9841 | 8.4761 | 10.4761 | 8.492 | 14.4761 | 22.9522 | 33.4283 | 4.9941 | 8.502 | 6.9841 | 5.9841 | 8.4761 | 10.4761 | 8.502 | 14.4861 | 22.9622 | 33.4383 | 0.01
6.0548 | 9.0274 | 8.0548 | 7.0548 | 10.0823 | 12.0823 | 9.0274 | 16.0823 | 26.1645 | 38.2468 | 6.0648 | 9.0374 | 8.0548 | 7.0548 | 10.0823 | 12.0823 | 9.0374 | 16.0923 | 26.1745 | 38.2568 | 0.01
5.0383 | 8.5192 | 7.0383 | 6.0383 | 8.5575 | 10.5575 | 8.5192 | 14.5575 | 23.115 | 33.6725 | 5.0483 | 8.5292 | 7.0383 | 6.0383 | 8.5575 | 10.5575 | 8.5292 | 14.5675 | 23.125 | 33.6825 | 0.01
6.1542 | 9.0771 | 8.1542 | 7.1542 | 10.2313 | 12.2313 | 9.0771 | 16.2313 | 26.4626 | 38.6939 | 6.1642 | 9.0871 | 8.1542 | 7.1542 | 10.2313 | 12.2313 | 9.0871 | 16.2413 | 26.4726 | 38.7039 | 0.01
9.3375 | 10.6687 | 11.3375 | 10.3375 | 15.0062 | 17.0062 | 10.6687 | 21.0062 | 36.0124 | 53.0186 | 9.3475 | 10.6787 | 11.3375 | 10.3375 | 15.0062 | 17.0062 | 10.6787 | 21.0162 | 36.0224 | 53.0286 | 0.01
4.5224 | 8.2612 | 6.5224 | 5.5224 | 7.7836 | 9.7836 | 8.2612 | 13.7836 | 21.5673 | 31.3509 | 4.5324 | 8.2712 | 6.5224 | 5.5224 | 7.7836 | 9.7836 | 8.2712 | 13.7936 | 21.5773 | 31.3609 | 0.01
8.5012 | 10.2506 | 10.5012 | 9.5012 | 13.7518 | 15.7518 | 10.2506 | 19.7518 | 33.5036 | 49.2553 | 8.5112 | 10.2606 | 10.5012 | 9.5012 | 13.7518 | 15.7518 | 10.2606 | 19.7618 | 33.5136 | 49.2653 | 0.01
4.0713 | 8.0357 | 6.0713 | 5.0713 | 7.107 | 9.107 | 8.0357 | 13.107 | 20.214 | 29.321 | 4.0813 | 8.0457 | 6.0713 | 5.0713 | 7.107 | 9.107 | 8.0457 | 13.117 | 20.224 | 29.331 | 0.01
4.0486 | 8.0243 | 6.0486 | 5.0486 | 7.0729 | 9.0729 | 8.0243 | 13.0729 | 20.1458 | 29.2187 | 4.0586 | 8.0343 | 6.0486 | 5.0486 | 7.0729 | 9.0729 | 8.0343 | 13.0829 | 20.1558 | 29.2287 | 0.01
6.1246 | 9.0623 | 8.1246 | 7.1246 | 10.1869 | 12.1869 | 9.0623 | 16.1869 | 26.3738 | 38.5607 | 6.1346 | 9.0723 | 8.1246 | 7.1246 | 10.1869 | 12.1869 | 9.0723 | 16.1969 | 26.3838 | 38.5707 | 0.01
9.4838 | 10.7419 | 11.4838 | 10.4838 | 15.2257 | 17.2257 | 10.7419 | 21.2257 | 36.4514 | 53.6771 | 9.4938 | 10.7519 | 11.4838 | 10.4838 | 15.2257 | 17.2257 | 10.7519 | 21.2357 | 36.4614 | 53.6871 | 0.01
8.4765 | 10.2383 | 10.4765 | 9.4765 | 13.7148 | 15.7148 | 10.2383 | 19.7148 | 33.4295 | 49.1443 | 8.4865 | 10.2483 | 10.4765 | 9.4765 | 13.7148 | 15.7148 | 10.2483 | 19.7248 | 33.4395 | 49.1543 | 0.01
1.5208 | 6.7604 | 3.5208 | 2.5208 | 3.2813 | 5.2813 | 6.7604 | 9.2813 | 12.5625 | 17.8438 | 1.5308 | 6.7704 | 3.5208 | 2.5208 | 3.2813 | 5.2813 | 6.7704 | 9.2913 | 12.5725 | 17.8538 | 0.01
3.2682 | 7.6341 | 5.2682 | 4.2682 | 5.9023 | 7.9023 | 7.6341 | 11.9023 | 17.8045 | 25.7068 | 3.2782 | 7.6441 | 5.2682 | 4.2682 | 5.9023 | 7.9023 | 7.6441 | 11.9123 | 17.8145 | 25.7168 | 0.01
3.7112 | 7.8556 | 5.7112 | 4.7112 | 6.5669 | 8.5669 | 7.8556 | 12.5669 | 19.1337 | 27.7006 | 3.7212 | 7.8656 | 5.7112 | 4.7112 | 6.5669 | 8.5669 | 7.8656 | 12.5769 | 19.1437 | 27.7106 | 0.01
6.4839 | 9.2419 | 8.4839 | 7.4839 | 10.7258 | 12.7258 | 9.2419 | 16.7258 | 27.4517 | 40.1775 | 6.4939 | 9.2519 | 8.4839 | 7.4839 | 10.7258 | 12.7258 | 9.2519 | 16.7358 | 27.4617 | 40.1875 | 0.01
2.484 | 7.242 | 4.484 | 3.484 | 4.726 | 6.726 | 7.242 | 10.726 | 15.452 | 22.178 | 2.494 | 7.252 | 4.484 | 3.484 | 4.726 | 6.726 | 7.252 | 10.736 | 15.462 | 22.188 | 0.01
7.3879 | 9.694 | 9.3879 | 8.3879 | 12.0819 | 14.0819 | 9.694 | 18.0819 | 30.1638 | 44.2457 | 7.3979 | 9.704 | 9.3879 | 8.3879 | 12.0819 | 14.0819 | 9.704 | 18.0919 | 30.1738 | 44.2557 | 0.01
6.4261 | 9.213 | 8.4261 | 7.4261 | 10.6391 | 12.6391 | 9.213 | 16.6391 | 27.2783 | 39.9174 | 6.4361 | 9.223 | 8.4261 | 7.4261 | 10.6391 | 12.6391 | 9.223 | 16.6491 | 27.2883 | 39.9274 | 0.01
4.4858 | 8.2429 | 6.4858 | 5.4858 | 7.7287 | 9.7287 | 8.2429 | 13.7287 | 21.4575 | 31.1862 | 4.4958 | 8.2529 | 6.4858 | 5.4858 | 7.7287 | 9.7287 | 8.2529 | 13.7387 | 21.4675 | 31.1962 | 0.01
3.8099 | 7.9049 | 5.8099 | 4.8099 | 6.7148 | 8.7148 | 7.9049 | 12.7148 | 19.4296 | 28.1444 | 3.8199 | 7.9149 | 5.8099 | 4.8099 | 6.7148 | 8.7148 | 7.9149 | 12.7248 | 19.4396 | 28.1544 | 0.01
4.7977 | 8.3989 | 6.7977 | 5.7977 | 8.1966 | 10.1966 | 8.3989 | 14.1966 | 22.3931 | 32.5897 | 4.8077 | 8.4089 | 6.7977 | 5.7977 | 8.1966 | 10.1966 | 8.4089 | 14.2066 | 22.4031 | 32.5997 | 0.01
8.9975 | 10.4988 | 10.9975 | 9.9975 | 14.4963 | 16.4963 | 10.4988 | 20.4963 | 34.9926 | 51.4888 | 9.0075 | 10.5088 | 10.9975 | 9.9975 | 14.4963 | 16.4963 | 10.5088 | 20.5063 | 35.0026 | 51.4988 | 0.01
5.8481 | 8.9241 | 7.8481 | 6.8481 | 9.7722 | 11.7722 | 8.9241 | 15.7722 | 25.5444 | 37.3167 | 5.8581 | 8.9341 | 7.8481 | 6.8481 | 9.7722 | 11.7722 | 8.9341 | 15.7822 | 25.5544 | 37.3267 | 0.01
8.5415 | 10.2708 | 10.5415 | 9.5415 | 13.8123 | 15.8123 | 10.2708 | 19.8123 | 33.6245 | 49.4368 | 8.5515 | 10.2808 | 10.5415 | 9.5415 | 13.8123 | 15.8123 | 10.2808 | 19.8223 | 33.6345 | 49.4468 | 0.01
4.4601 | 8.2301 | 6.4601 | 5.4601 | 7.6902 | 9.6902 | 8.2301 | 13.6902 | 21.3803 | 31.0705 | 4.4701 | 8.2401 | 6.4601 | 5.4601 | 7.6902 | 9.6902 | 8.2401 | 13.7002 | 21.3903 | 31.0805 | 0.01
7.1335 | 9.5667 | 9.1335 | 8.1335 | 11.7002 | 13.7002 | 9.5667 | 17.7002 | 29.4004 | 43.1005 | 7.1435 | 9.5767 | 9.1335 | 8.1335 | 11.7002 | 13.7002 | 9.5767 | 17.7102 | 29.4104 | 43.1105 | 0.01
5.7056 | 8.8528 | 7.7056 | 6.7056 | 9.5584 | 11.5584 | 8.8528 | 15.5584 | 25.1169 | 36.6753 | 5.7156 | 8.8628 | 7.7056 | 6.7056 | 9.5584 | 11.5584 | 8.8628 | 15.5684 | 25.1269 | 36.6853 | 0.01
3.7183 | 7.8592 | 5.7183 | 4.7183 | 6.5775 | 8.5775 | 7.8592 | 12.5775 | 19.1549 | 27.7324 | 3.7283 | 7.8692 | 5.7183 | 4.7183 | 6.5775 | 8.5775 | 7.8692 | 12.5875 | 19.1649 | 27.7424 | 0.01
8.9759 | 10.488 | 10.9759 | 9.9759 | 14.4639 | 16.4639 | 10.488 | 20.4639 | 34.9278 | 51.3917 | 8.9859 | 10.498 | 10.9759 | 9.9759 | 14.4639 | 16.4639 | 10.498 | 20.4739 | 34.9378 | 51.4017 | 0.01
7.3026 | 9.6513 | 9.3026 | 8.3026 | 11.9539 | 13.9539 | 9.6513 | 17.9539 | 29.9078 | 43.8617 | 7.3126 | 9.6613 | 9.3026 | 8.3026 | 11.9539 | 13.9539 | 9.6613 | 17.9639 | 29.9178 | 43.8717 | 0.01
5.7156 | 8.8578 | 7.7156 | 6.7156 | 9.5734 | 11.5734 | 8.8578 | 15.5734 | 25.1469 | 36.7203 | 5.7256 | 8.8678 | 7.7156 | 6.7156 | 9.5734 | 11.5734 | 8.8678 | 15.5834 | 25.1569 | 36.7303 | 0.01
5.1936 | 8.5968 | 7.1936 | 6.1936 | 8.7903 | 10.7903 | 8.5968 | 14.7903 | 23.5807 | 34.371 | 5.2036 | 8.6068 | 7.1936 | 6.1936 | 8.7903 | 10.7903 | 8.6068 | 14.8003 | 23.5907 | 34.381 | 0.01
5.508 | 8.754 | 7.508 | 6.508 | 9.2621 | 11.2621 | 8.754 | 15.2621 | 24.5241 | 35.7862 | 5.518 | 8.764 | 7.508 | 6.508 | 9.2621 | 11.2621 | 8.764 | 15.2721 | 24.5341 | 35.7962 | 0.01
6.889 | 9.4445 | 8.889 | 7.889 | 11.3335 | 13.3335 | 9.4445 | 17.3335 | 28.6671 | 42.0006 | 6.899 | 9.4545 | 8.889 | 7.889 | 11.3335 | 13.3335 | 9.4545 | 17.3435 | 28.6771 | 42.0106 | 0.01
6.8062 | 9.4031 | 8.8062 | 7.8062 | 11.2094 | 13.2094 | 9.4031 | 17.2094 | 28.4187 | 41.6281 | 6.8162 | 9.4131 | 8.8062 | 7.8062 | 11.2094 | 13.2094 | 9.4131 | 17.2194 | 28.4287 | 41.6381 | 0.01
0.67283 | 6.3364 | 2.6728 | 1.6728 | 2.0093 | 4.0093 | 6.3364 | 8.0093 | 10.0185 | 14.0278 | 0.68283 | 6.3464 | 2.6728 | 1.6728 | 2.0093 | 4.0093 | 6.3464 | 8.0193 | 10.0285 | 14.0378 | 0.01
9.912 | 10.956 | 11.912 | 10.912 | 15.868 | 17.868 | 10.956 | 21.868 | 37.7361 | 55.6041 | 9.922 | 10.966 | 11.912 | 10.912 | 15.868 | 17.868 | 10.966 | 21.878 | 37.7461 | 55.6141 | 0.01
8.8986 | 10.4493 | 10.8986 | 9.8986 | 14.3479 | 16.3479 | 10.4493 | 20.3479 | 34.6958 | 51.0438 | 8.9086 | 10.4593 | 10.8986 | 9.8986 | 14.3479 | 16.3479 | 10.4593 | 20.3579 | 34.7058 | 51.0538 | 0.01
6.3234 | 9.1617 | 8.3234 | 7.3234 | 10.4851 | 12.4851 | 9.1617 | 16.4851 | 26.9703 | 39.4554 | 6.3334 | 9.1717 | 8.3234 | 7.3234 | 10.4851 | 12.4851 | 9.1717 | 16.4951 | 26.9803 | 39.4654 | 0.01
3.0784 | 7.5392 | 5.0784 | 4.0784 | 5.6175 | 7.6175 | 7.5392 | 11.6175 | 17.2351 | 24.8526 | 3.0884 | 7.5492 | 5.0784 | 4.0784 | 5.6175 | 7.6175 | 7.5492 | 11.6275 | 17.2451 | 24.8626 | 0.01
6.7898 | 9.3949 | 8.7898 | 7.7898 | 11.1847 | 13.1847 | 9.3949 | 17.1847 | 28.3695 | 41.5542 | 6.7998 | 9.4049 | 8.7898 | 7.7898 | 11.1847 | 13.1847 | 9.4049 | 17.1947 | 28.3795 | 41.5642 | 0.01
4.1042 | 8.0521 | 6.1042 | 5.1042 | 7.1563 | 9.1563 | 8.0521 | 13.1563 | 20.3126 | 29.4689 | 4.1142 | 8.0621 | 6.1042 | 5.1042 | 7.1563 | 9.1563 | 8.0621 | 13.1663 | 20.3226 | 29.4789 | 0.01
8.6722 | 10.3361 | 10.6722 | 9.6722 | 14.0083 | 16.0083 | 10.3361 | 20.0083 | 34.0166 | 50.0248 | 8.6822 | 10.3461 | 10.6722 | 9.6722 | 14.0083 | 16.0083 | 10.3461 | 20.0183 | 34.0266 | 50.0348 | 0.01
6.5228 | 9.2614 | 8.5228 | 7.5228 | 10.7842 | 12.7842 | 9.2614 | 16.7842 | 27.5685 | 40.3527 | 6.5328 | 9.2714 | 8.5228 | 7.5228 | 10.7842 | 12.7842 | 9.2714 | 16.7942 | 27.5785 | 40.3627 | 0.01
5.9937 | 8.9968 | 7.9937 | 6.9937 | 9.9905 | 11.9905 | 8.9968 | 15.9905 | 25.9811 | 37.9716 | 6.0037 | 9.0068 | 7.9937 | 6.9937 | 9.9905 | 11.9905 | 9.0068 | 16.0005 | 25.9911 | 37.9816 | 0.01
5.1327 | 8.5664 | 7.1327 | 6.1327 | 8.6991 | 10.6991 | 8.5664 | 14.6991 | 23.3981 | 34.0972 | 5.1427 | 8.5764 | 7.1327 | 6.1327 | 8.6991 | 10.6991 | 8.5764 | 14.7091 | 23.4081 | 34.1072 | 0.01
6.0972 | 9.0486 | 8.0972 | 7.0972 | 10.1458 | 12.1458 | 9.0486 | 16.1458 | 26.2917 | 38.4375 | 6.1072 | 9.0586 | 8.0972 | 7.0972 | 10.1458 | 12.1458 | 9.0586 | 16.1558 | 26.3017 | 38.4475 | 0.01
5.1872 | 8.5936 | 7.1872 | 6.1872 | 8.7809 | 10.7809 | 8.5936 | 14.7809 | 23.5617 | 34.3426 | 5.1972 | 8.6036 | 7.1872 | 6.1872 | 8.7809 | 10.7809 | 8.6036 | 14.7909 | 23.5717 | 34.3526 | 0.01
8.4996 | 10.2498 | 10.4996 | 9.4996 | 13.7494 | 15.7494 | 10.2498 | 19.7494 | 33.4989 | 49.2483 | 8.5096 | 10.2598 | 10.4996 | 9.4996 | 13.7494 | 15.7494 | 10.2598 | 19.7594 | 33.5089 | 49.2583 | 0.01
7.4639 | 9.732 | 9.4639 | 8.4639 | 12.1959 | 14.1959 | 9.732 | 18.1959 | 30.3918 | 44.5877 | 7.4739 | 9.742 | 9.4639 | 8.4639 | 12.1959 | 14.1959 | 9.742 | 18.2059 | 30.4018 | 44.5977 | 0.01
4.3516 | 8.1758 | 6.3516 | 5.3516 | 7.5274 | 9.5274 | 8.1758 | 13.5274 | 21.0548 | 30.5822 | 4.3616 | 8.1858 | 6.3516 | 5.3516 | 7.5274 | 9.5274 | 8.1858 | 13.5374 | 21.0648 | 30.5922 | 0.01
9.4009 | 10.7004 | 11.4009 | 10.4009 | 15.1013 | 17.1013 | 10.7004 | 21.1013 | 36.2026 | 53.3038 | 9.4109 | 10.7104 | 11.4009 | 10.4009 | 15.1013 | 17.1013 | 10.7104 | 21.1113 | 36.2126 | 53.3138 | 0.01
6.8435 | 9.4217 | 8.8435 | 7.8435 | 11.2652 | 13.2652 | 9.4217 | 17.2652 | 28.5304 | 41.7956 | 6.8535 | 9.4317 | 8.8435 | 7.8435 | 11.2652 | 13.2652 | 9.4317 | 17.2752 | 28.5404 | 41.8056 | 0.01
6.4462 | 9.2231 | 8.4462 | 7.4462 | 10.6693 | 12.6693 | 9.2231 | 16.6693 | 27.3385 | 40.0078 | 6.4562 | 9.2331 | 8.4462 | 7.4462 | 10.6693 | 12.6693 | 9.2331 | 16.6793 | 27.3485 | 40.0178 | 0.01
0.20077 | 6.1004 | 2.2008 | 1.2008 | 1.3012 | 3.3012 | 6.1004 | 7.3012 | 8.6023 | 11.9035 | 0.21077 | 6.1104 | 2.2008 | 1.2008 | 1.3012 | 3.3012 | 6.1104 | 7.3112 | 8.6123 | 11.9135 | 0.01
5.4665 | 8.7332 | 7.4665 | 6.4665 | 9.1997 | 11.1997 | 8.7332 | 15.1997 | 24.3995 | 35.5992 | 5.4765 | 8.7432 | 7.4665 | 6.4665 | 9.1997 | 11.1997 | 8.7432 | 15.2097 | 24.4095 | 35.6092 | 0.01
8.8034 | 10.4017 | 10.8034 | 9.8034 | 14.2052 | 16.2052 | 10.4017 | 20.2052 | 34.4103 | 50.6155 | 8.8134 | 10.4117 | 10.8034 | 9.8034 | 14.2052 | 16.2052 | 10.4117 | 20.2152 | 34.4203 | 50.6255 | 0.01
2.3695 | 7.1848 | 4.3695 | 3.3695 | 4.5543 | 6.5543 | 7.1848 | 10.5543 | 15.1086 | 21.6629 | 2.3795 | 7.1948 | 4.3695 | 3.3695 | 4.5543 | 6.5543 | 7.1948 | 10.5643 | 15.1186 | 21.6729 | 0.01
9.0481 | 10.524 | 11.0481 | 10.0481 | 14.5721 | 16.5721 | 10.524 | 20.5721 | 35.1442 | 51.7163 | 9.0581 | 10.534 | 11.0481 | 10.0481 | 14.5721 | 16.5721 | 10.534 | 20.5821 | 35.1542 | 51.7263 | 0.01
6.2675 | 9.1337 | 8.2675 | 7.2675 | 10.4012 | 12.4012 | 9.1337 | 16.4012 | 26.8025 | 39.2037 | 6.2775 | 9.1437 | 8.2675 | 7.2675 | 10.4012 | 12.4012 | 9.1437 | 16.4112 | 26.8125 | 39.2137 | 0.01
6.5188 | 9.2594 | 8.5188 | 7.5188 | 10.7782 | 12.7782 | 9.2594 | 16.7782 | 27.5565 | 40.3347 | 6.5288 | 9.2694 | 8.5188 | 7.5188 | 10.7782 | 12.7782 | 9.2694 | 16.7882 | 27.5665 | 40.3447 | 0.01
6.3693 | 9.1846 | 8.3693 | 7.3693 | 10.5539 | 12.5539 | 9.1846 | 16.5539 | 27.1078 | 39.6617 | 6.3793 | 9.1946 | 8.3693 | 7.3693 | 10.5539 | 12.5539 | 9.1946 | 16.5639 | 27.1178 | 39.6717 | 0.01
5.8291 | 8.9145 | 7.8291 | 6.8291 | 9.7436 | 11.7436 | 8.9145 | 15.7436 | 25.4872 | 37.2308 | 5.8391 | 8.9245 | 7.8291 | 6.8291 | 9.7436 | 11.7436 | 8.9245 | 15.7536 | 25.4972 | 37.2408 | 0.01
3.9307 | 7.9653 | 5.9307 | 4.9307 | 6.896 | 8.896 | 7.9653 | 12.896 | 19.792 | 28.688 | 3.9407 | 7.9753 | 5.9307 | 4.9307 | 6.896 | 8.896 | 7.9753 | 12.906 | 19.802 | 28.698 | 0.01
9.8395 | 10.9198 | 11.8395 | 10.8395 | 15.7593 | 17.7593 | 10.9198 | 21.7593 | 37.5186 | 55.2779 | 9.8495 | 10.9298 | 11.8395 | 10.8395 | 15.7593 | 17.7593 | 10.9298 | 21.7693 | 37.5286 | 55.2879 | 0.01
7.369 | 9.6845 | 9.369 | 8.369 | 12.0536 | 14.0536 | 9.6845 | 18.0536 | 30.1071 | 44.1607 | 7.379 | 9.6945 | 9.369 | 8.369 | 12.0536 | 14.0536 | 9.6945 | 18.0636 | 30.1171 | 44.1707 | 0.01
6.8523 | 9.4261 | 8.8523 | 7.8523 | 11.2784 | 13.2784 | 9.4261 | 17.2784 | 28.5568 | 41.8351 | 6.8623 | 9.4361 | 8.8523 | 7.8523 | 11.2784 | 13.2784 | 9.4361 | 17.2884 | 28.5668 | 41.8451 | 0.01
6.0793 | 9.0396 | 8.0793 | 7.0793 | 10.1189 | 12.1189 | 9.0396 | 16.1189 | 26.2378 | 38.3567 | 6.0893 | 9.0496 | 8.0793 | 7.0793 | 10.1189 | 12.1189 | 9.0496 | 16.1289 | 26.2478 | 38.3667 | 0.01
3.9433 | 7.9717 | 5.9433 | 4.9433 | 6.915 | 8.915 | 7.9717 | 12.915 | 19.83 | 28.745 | 3.9533 | 7.9817 | 5.9433 | 4.9433 | 6.915 | 8.915 | 7.9817 | 12.925 | 19.84 | 28.755 | 0.01
8.7022 | 10.3511 | 10.7022 | 9.7022 | 14.0532 | 16.0532 | 10.3511 | 20.0532 | 34.1065 | 50.1597 | 8.7122 | 10.3611 | 10.7022 | 9.7022 | 14.0532 | 16.0532 | 10.3611 | 20.0632 | 34.1165 | 50.1697 | 0.01
5.2855 | 8.6427 | 7.2855 | 6.2855 | 8.9282 | 10.9282 | 8.6427 | 14.9282 | 23.8564 | 34.7846 | 5.2955 | 8.6527 | 7.2855 | 6.2855 | 8.9282 | 10.9282 | 8.6527 | 14.9382 | 23.8664 | 34.7946 | 0.01
2.6873 | 7.3437 | 4.6873 | 3.6873 | 5.031 | 7.031 | 7.3437 | 11.031 | 16.062 | 23.093 | 2.6973 | 7.3537 | 4.6873 | 3.6873 | 5.031 | 7.031 | 7.3537 | 11.041 | 16.072 | 23.103 | 0.01
6.6904 | 9.3452 | 8.6904 | 7.6904 | 11.0357 | 13.0357 | 9.3452 | 17.0357 | 28.0713 | 41.107 | 6.7004 | 9.3552 | 8.6904 | 7.6904 | 11.0357 | 13.0357 | 9.3552 | 17.0457 | 28.0813 | 41.117 | 0.01
2.8821 | 7.4411 | 4.8821 | 3.8821 | 5.3232 | 7.3232 | 7.4411 | 11.3232 | 16.6463 | 23.9695 | 2.8921 | 7.4511 | 4.8821 | 3.8821 | 5.3232 | 7.3232 | 7.4511 | 11.3332 | 16.6563 | 23.9795 | 0.01
3.2924 | 7.6462 | 5.2924 | 4.2924 | 5.9386 | 7.9386 | 7.6462 | 11.9386 | 17.8772 | 25.8158 | 3.3024 | 7.6562 | 5.2924 | 4.2924 | 5.9386 | 7.9386 | 7.6562 | 11.9486 | 17.8872 | 25.8258 | 0.01
5.1488 | 8.5744 | 7.1488 | 6.1488 | 8.7232 | 10.7232 | 8.5744 | 14.7232 | 23.4464 | 34.1696 | 5.1588 | 8.5844 | 7.1488 | 6.1488 | 8.7232 | 10.7232 | 8.5844 | 14.7332 | 23.4564 | 34.1796 | 0.01
7.2469 | 9.6234 | 9.2469 | 8.2469 | 11.8703 | 13.8703 | 9.6234 | 17.8703 | 29.7406 | 43.6109 | 7.2569 | 9.6334 | 9.2469 | 8.2469 | 11.8703 | 13.8703 | 9.6334 | 17.8803 | 29.7506 | 43.6209 | 0.01
8.7803 | 10.3902 | 10.7803 | 9.7803 | 14.1705 | 16.1705 | 10.3902 | 20.1705 | 34.3409 | 50.5114 | 8.7903 | 10.4002 | 10.7803 | 9.7803 | 14.1705 | 16.1705 | 10.4002 | 20.1805 | 34.3509 | 50.5214 | 0.01
7.4934 | 9.7467 | 9.4934 | 8.4934 | 12.24 | 14.24 | 9.7467 | 18.24 | 30.4801 | 44.7201 | 7.5034 | 9.7567 | 9.4934 | 8.4934 | 12.24 | 14.24 | 9.7567 | 18.25 | 30.4901 | 44.7301 | 0.01
4.6474 | 8.3237 | 6.6474 | 5.6474 | 7.9711 | 9.9711 | 8.3237 | 13.9711 | 21.9422 | 31.9133 | 4.6574 | 8.3337 | 6.6474 | 5.6474 | 7.9711 | 9.9711 | 8.3337 | 13.9811 | 21.9522 | 31.9233 | 0.01
2.825 | 7.4125 | 4.825 | 3.825 | 5.2375 | 7.2375 | 7.4125 | 11.2375 | 16.4749 | 23.7124 | 2.835 | 7.4225 | 4.825 | 3.825 | 5.2375 | 7.2375 | 7.4225 | 11.2475 | 16.4849 | 23.7224 | 0.01
6.1314 | 9.0657 | 8.1314 | 7.1314 | 10.1971 | 12.1971 | 9.0657 | 16.1971 | 26.3941 | 38.5912 | 6.1414 | 9.0757 | 8.1314 | 7.1314 | 10.1971 | 12.1971 | 9.0757 | 16.2071 | 26.4041 | 38.6012 | 0.01
6.7276 | 9.3638 | 8.7276 | 7.7276 | 11.0913 | 13.0913 | 9.3638 | 17.0913 | 28.1827 | 41.274 | 6.7376 | 9.3738 | 8.7276 | 7.7276 | 11.0913 | 13.0913 | 9.3738 | 17.1013 | 28.1927 | 41.284 | 0.01
8.4751 | 10.2376 | 10.4751 | 9.4751 | 13.7127 | 15.7127 | 10.2376 | 19.7127 | 33.4254 | 49.1381 | 8.4851 | 10.2476 | 10.4751 | 9.4751 | 13.7127 | 15.7127 | 10.2476 | 19.7227 | 33.4354 | 49.1481 | 0.01
8.2603 | 10.1302 | 10.2603 | 9.2603 | 13.3905 | 15.3905 | 10.1302 | 19.3905 | 32.781 | 48.1714 | 8.2703 | 10.1402 | 10.2603 | 9.2603 | 13.3905 | 15.3905 | 10.1402 | 19.4005 | 32.791 | 48.1814 | 0.01
5.7733 | 8.8867 | 7.7733 | 6.7733 | 9.66 | 11.66 | 8.8867 | 15.66 | 25.32 | 36.9799 | 5.7833 | 8.8967 | 7.7733 | 6.7733 | 9.66 | 11.66 | 8.8967 | 15.67 | 25.33 | 36.9899 | 0.01
4.1212 | 8.0606 | 6.1212 | 5.1212 | 7.1818 | 9.1818 | 8.0606 | 13.1818 | 20.3636 | 29.5453 | 4.1312 | 8.0706 | 6.1212 | 5.1212 | 7.1818 | 9.1818 | 8.0706 | 13.1918 | 20.3736 | 29.5553 | 0.01
5.4958 | 8.7479 | 7.4958 | 6.4958 | 9.2437 | 11.2437 | 8.7479 | 15.2437 | 24.4875 | 35.7312 | 5.5058 | 8.7579 | 7.4958 | 6.4958 | 9.2437 | 11.2437 | 8.7579 | 15.2537 | 24.4975 | 35.7412 | 0.01
9.4378 | 10.7189 | 11.4378 | 10.4378 | 15.1567 | 17.1567 | 10.7189 | 21.1567 | 36.3134 | 53.4701 | 9.4478 | 10.7289 | 11.4378 | 10.4378 | 15.1567 | 17.1567 | 10.7289 | 21.1667 | 36.3234 | 53.4801 | 0.01
5.4164 | 8.7082 | 7.4164 | 6.4164 | 9.1246 | 11.1246 | 8.7082 | 15.1246 | 24.2492 | 35.3737 | 5.4264 | 8.7182 | 7.4164 | 6.4164 | 9.1246 | 11.1246 | 8.7182 | 15.1346 | 24.2592 | 35.3837 | 0.01
5.2546 | 8.6273 | 7.2546 | 6.2546 | 8.8819 | 10.8819 | 8.6273 | 14.8819 | 23.7637 | 34.6456 | 5.2646 | 8.6373 | 7.2546 | 6.2546 | 8.8819 | 10.8819 | 8.6373 | 14.8919 | 23.7737 | 34.6556 | 0.01
3.5047 | 7.7524 | 5.5047 | 4.5047 | 6.2571 | 8.2571 | 7.7524 | 12.2571 | 18.5141 | 26.7712 | 3.5147 | 7.7624 | 5.5047 | 4.5047 | 6.2571 | 8.2571 | 7.7624 | 12.2671 | 18.5241 | 26.7812 | 0.01
8.3734 | 10.1867 | 10.3734 | 9.3734 | 13.5601 | 15.5601 | 10.1867 | 19.5601 | 33.1201 | 48.6802 | 8.3834 | 10.1967 | 10.3734 | 9.3734 | 13.5601 | 15.5601 | 10.1967 | 19.5701 | 33.1301 | 48.6902 | 0.01
4.4282 | 8.2141 | 6.4282 | 5.4282 | 7.6423 | 9.6423 | 8.2141 | 13.6423 | 21.2847 | 30.927 | 4.4382 | 8.2241 | 6.4282 | 5.4282 | 7.6423 | 9.6423 | 8.2241 | 13.6523 | 21.2947 | 30.937 | 0.01
7.3775 | 9.6887 | 9.3775 | 8.3775 | 12.0662 | 14.0662 | 9.6887 | 18.0662 | 30.1324 | 44.1986 | 7.3875 | 9.6987 | 9.3775 | 8.3775 | 12.0662 | 14.0662 | 9.6987 | 18.0762 | 30.1424 | 44.2086 | 0.01
10.3593 | 11.1797 | 12.3593 | 11.3593 | 16.539 | 18.539 | 11.1797 | 22.539 | 39.078 | 57.6169 | 10.3693 | 11.1897 | 12.3593 | 11.3593 | 16.539 | 18.539 | 11.1897 | 22.549 | 39.088 | 57.6269 | 0.01
8.8301 | 10.4151 | 10.8301 | 9.8301 | 14.2452 | 16.2452 | 10.4151 | 20.2452 | 34.4903 | 50.7355 | 8.8401 | 10.4251 | 10.8301 | 9.8301 | 14.2452 | 16.2452 | 10.4251 | 20.2552 | 34.5003 | 50.7455 | 0.01
4.4346 | 8.2173 | 6.4346 | 5.4346 | 7.6519 | 9.6519 | 8.2173 | 13.6519 | 21.3037 | 30.9556 | 4.4446 | 8.2273 | 6.4346 | 5.4346 | 7.6519 | 9.6519 | 8.2273 | 13.6619 | 21.3137 | 30.9656 | 0.01
5.5114 | 8.7557 | 7.5114 | 6.5114 | 9.2671 | 11.2671 | 8.7557 | 15.2671 | 24.5343 | 35.8014 | 5.5214 | 8.7657 | 7.5114 | 6.5114 | 9.2671 | 11.2671 | 8.7657 | 15.2771 | 24.5443 | 35.8114 | 0.01
6.9724 | 9.4862 | 8.9724 | 7.9724 | 11.4586 | 13.4586 | 9.4862 | 17.4586 | 28.9171 | 42.3757 | 6.9824 | 9.4962 | 8.9724 | 7.9724 | 11.4586 | 13.4586 | 9.4962 | 17.4686 | 28.9271 | 42.3857 | 0.01
5.4232 | 8.7116 | 7.4232 | 6.4232 | 9.1348 | 11.1348 | 8.7116 | 15.1348 | 24.2696 | 35.4044 | 5.4332 | 8.7216 | 7.4232 | 6.4232 | 9.1348 | 11.1348 | 8.7216 | 15.1448 | 24.2796 | 35.4144 | 0.01
4.6256 | 8.3128 | 6.6256 | 5.6256 | 7.9384 | 9.9384 | 8.3128 | 13.9384 | 21.8769 | 31.8153 | 4.6356 | 8.3228 | 6.6256 | 5.6256 | 7.9384 | 9.9384 | 8.3228 | 13.9484 | 21.8869 | 31.8253 | 0.01
4.4256 | 8.2128 | 6.4256 | 5.4256 | 7.6385 | 9.6385 | 8.2128 | 13.6385 | 21.2769 | 30.9154 | 4.4356 | 8.2228 | 6.4256 | 5.4256 | 7.6385 | 9.6385 | 8.2228 | 13.6485 | 21.2869 | 30.9254 | 0.01
5.4764 | 8.7382 | 7.4764 | 6.4764 | 9.2147 | 11.2147 | 8.7382 | 15.2147 | 24.4293 | 35.644 | 5.4864 | 8.7482 | 7.4764 | 6.4764 | 9.2147 | 11.2147 | 8.7482 | 15.2247 | 24.4393 | 35.654 | 0.01
3.7625 | 7.8812 | 5.7625 | 4.7625 | 6.6437 | 8.6437 | 7.8812 | 12.6437 | 19.2875 | 27.9312 | 3.7725 | 7.8912 | 5.7625 | 4.7625 | 6.6437 | 8.6437 | 7.8912 | 12.6537 | 19.2975 | 27.9412 | 0.01
4.1874 | 8.0937 | 6.1874 | 5.1874 | 7.281 | 9.281 | 8.0937 | 13.281 | 20.5621 | 29.8431 | 4.1974 | 8.1037 | 6.1874 | 5.1874 | 7.281 | 9.281 | 8.1037 | 13.291 | 20.5721 | 29.8531 | 0.01
5.0846 | 8.5423 | 7.0846 | 6.0846 | 8.6269 | 10.6269 | 8.5423 | 14.6269 | 23.2537 | 33.8806 | 5.0946 | 8.5523 | 7.0846 | 6.0846 | 8.6269 | 10.6269 | 8.5523 | 14.6369 | 23.2637 | 33.8906 | 0.01
5.5213 | 8.7607 | 7.5213 | 6.5213 | 9.282 | 11.282 | 8.7607 | 15.282 | 24.564 | 35.846 | 5.5313 | 8.7707 | 7.5213 | 6.5213 | 9.282 | 11.282 | 8.7707 | 15.292 | 24.574 | 35.856 | 0.01
9.8412 | 10.9206 | 11.8412 | 10.8412 | 15.7618 | 17.7618 | 10.9206 | 21.7618 | 37.5236 | 55.2855 | 9.8512 | 10.9306 | 11.8412 | 10.8412 | 15.7618 | 17.7618 | 10.9306 | 21.7718 | 37.5336 | 55.2955 | 0.01
6.7464 | 9.3732 | 8.7464 | 7.7464 | 11.1195 | 13.1195 | 9.3732 | 17.1195 | 28.2391 | 41.3586 | 6.7564 | 9.3832 | 8.7464 | 7.7464 | 11.1195 | 13.1195 | 9.3832 | 17.1295 | 28.2491 | 41.3686 | 0.01
7.7882 | 9.8941 | 9.7882 | 8.7882 | 12.6823 | 14.6823 | 9.8941 | 18.6823 | 31.3647 | 46.047 | 7.7982 | 9.9041 | 9.7882 | 8.7882 | 12.6823 | 14.6823 | 9.9041 | 18.6923 | 31.3747 | 46.057 | 0.01
3.4484 | 7.7242 | 5.4484 | 4.4484 | 6.1726 | 8.1726 | 7.7242 | 12.1726 | 18.3451 | 26.5177 | 3.4584 | 7.7342 | 5.4484 | 4.4484 | 6.1726 | 8.1726 | 7.7342 | 12.1826 | 18.3551 | 26.5277 | 0.01
6.9806 | 9.4903 | 8.9806 | 7.9806 | 11.4709 | 13.4709 | 9.4903 | 17.4709 | 28.9418 | 42.4126 | 6.9906 | 9.5003 | 8.9806 | 7.9806 | 11.4709 | 13.4709 | 9.5003 | 17.4809 | 28.9518 | 42.4226 | 0.01
7.952 | 9.976 | 9.952 | 8.952 | 12.928 | 14.928 | 9.976 | 18.928 | 31.8561 | 46.7841 | 7.962 | 9.986 | 9.952 | 8.952 | 12.928 | 14.928 | 9.986 | 18.938 | 31.8661 | 46.7941 | 0.01
7.4983 | 9.7492 | 9.4983 | 8.4983 | 12.2475 | 14.2475 | 9.7492 | 18.2475 | 30.4949 | 44.7424 | 7.5083 | 9.7592 | 9.4983 | 8.4983 | 12.2475 | 14.2475 | 9.7592 | 18.2575 | 30.5049 | 44.7524 | 0.01
7.6387 | 9.8193 | 9.6387 | 8.6387 | 12.458 | 14.458 | 9.8193 | 18.458 | 30.916 | 45.3739 | 7.6487 | 9.8293 | 9.6387 | 8.6387 | 12.458 | 14.458 | 9.8293 | 18.468 | 30.926 | 45.3839 | 0.01
7.1471 | 9.5736 | 9.1471 | 8.1471 | 11.7207 | 13.7207 | 9.5736 | 17.7207 | 29.4413 | 43.162 | 7.1571 | 9.5836 | 9.1471 | 8.1471 | 11.7207 | 13.7207 | 9.5836 | 17.7307 | 29.4513 | 43.172 | 0.01
5.2826 | 8.6413 | 7.2826 | 6.2826 | 8.924 | 10.924 | 8.6413 | 14.924 | 23.8479 | 34.7719 | 5.2926 | 8.6513 | 7.2826 | 6.2826 | 8.924 | 10.924 | 8.6513 | 14.934 | 23.8579 | 34.7819 | 0.01
4.0416 | 8.0208 | 6.0416 | 5.0416 | 7.0624 | 9.0624 | 8.0208 | 13.0624 | 20.1247 | 29.1871 | 4.0516 | 8.0308 | 6.0416 | 5.0416 | 7.0624 | 9.0624 | 8.0308 | 13.0724 | 20.1347 | 29.1971 | 0.01
9.1275 | 10.5638 | 11.1275 | 10.1275 | 14.6913 | 16.6913 | 10.5638 | 20.6913 | 35.3826 | 52.0739 | 9.1375 | 10.5738 | 11.1275 | 10.1275 | 14.6913 | 16.6913 | 10.5738 | 20.7013 | 35.3926 | 52.0839 | 0.01
5.8582 | 8.9291 | 7.8582 | 6.8582 | 9.7873 | 11.7873 | 8.9291 | 15.7873 | 25.5747 | 37.362 | 5.8682 | 8.9391 | 7.8582 | 6.8582 | 9.7873 | 11.7873 | 8.9391 | 15.7973 | 25.5847 | 37.372 | 0.01
6.5105 | 9.2552 | 8.5105 | 7.5105 | 10.7657 | 12.7657 | 9.2552 | 16.7657 | 27.5314 | 40.2971 | 6.5205 | 9.2652 | 8.5105 | 7.5105 | 10.7657 | 12.7657 | 9.2652 | 16.7757 | 27.5414 | 40.3071 | 0.01
5.8845 | 8.9423 | 7.8845 | 6.8845 | 9.8268 | 11.8268 | 8.9423 | 15.8268 | 25.6536 | 37.4804 | 5.8945 | 8.9523 | 7.8845 | 6.8845 | 9.8268 | 11.8268 | 8.9523 | 15.8368 | 25.6636 | 37.4904 | 0.01
6.6335 | 9.3167 | 8.6335 | 7.6335 | 10.9502 | 12.9502 | 9.3167 | 16.9502 | 27.9005 | 40.8507 | 6.6435 | 9.3267 | 8.6335 | 7.6335 | 10.9502 | 12.9502 | 9.3267 | 16.9602 | 27.9105 | 40.8607 | 0.01
4.9168 | 8.4584 | 6.9168 | 5.9168 | 8.3752 | 10.3752 | 8.4584 | 14.3752 | 22.7503 | 33.1255 | 4.9268 | 8.4684 | 6.9168 | 5.9168 | 8.3752 | 10.3752 | 8.4684 | 14.3852 | 22.7603 | 33.1355 | 0.01
9.3304 | 10.6652 | 11.3304 | 10.3304 | 14.9956 | 16.9956 | 10.6652 | 20.9956 | 35.9912 | 52.9869 | 9.3404 | 10.6752 | 11.3304 | 10.3304 | 14.9956 | 16.9956 | 10.6752 | 21.0056 | 36.0012 | 52.9969 | 0.01
5.1914 | 8.5957 | 7.1914 | 6.1914 | 8.7871 | 10.7871 | 8.5957 | 14.7871 | 23.5741 | 34.3612 | 5.2014 | 8.6057 | 7.1914 | 6.1914 | 8.7871 | 10.7871 | 8.6057 | 14.7971 | 23.5841 | 34.3712 | 0.01
6.7387 | 9.3693 | 8.7387 | 7.7387 | 11.108 | 13.108 | 9.3693 | 17.108 | 28.2161 | 41.3241 | 6.7487 | 9.3793 | 8.7387 | 7.7387 | 11.108 | 13.108 | 9.3793 | 17.118 | 28.2261 | 41.3341 | 0.01
7.8434 | 9.9217 | 9.8434 | 8.8434 | 12.7652 | 14.7652 | 9.9217 | 18.7652 | 31.5303 | 46.2955 | 7.8534 | 9.9317 | 9.8434 | 8.8434 | 12.7652 | 14.7652 | 9.9317 | 18.7752 | 31.5403 | 46.3055 | 0.01
7.0532 | 9.5266 | 9.0532 | 8.0532 | 11.5799 | 13.5799 | 9.5266 | 17.5799 | 29.1597 | 42.7396 | 7.0632 | 9.5366 | 9.0532 | 8.0532 | 11.5799 | 13.5799 | 9.5366 | 17.5899 | 29.1697 | 42.7496 | 0.01
8.328 | 10.164 | 10.328 | 9.328 | 13.492 | 15.492 | 10.164 | 19.492 | 32.984 | 48.476 | 8.338 | 10.174 | 10.328 | 9.328 | 13.492 | 15.492 | 10.174 | 19.502 | 32.994 | 48.486 | 0.01
10.2615 | 11.1307 | 12.2615 | 11.2615 | 16.3922 | 18.3922 | 11.1307 | 22.3922 | 38.7844 | 57.1766 | 10.2715 | 11.1407 | 12.2615 | 11.2615 | 16.3922 | 18.3922 | 11.1407 | 22.4022 | 38.7944 | 57.1866 | 0.01
7.3095 | 9.6548 | 9.3095 | 8.3095 | 11.9643 | 13.9643 | 9.6548 | 17.9643 | 29.9286 | 43.893 | 7.3195 | 9.6648 | 9.3095 | 8.3095 | 11.9643 | 13.9643 | 9.6648 | 17.9743 | 29.9386 | 43.903 | 0.01
4.6952 | 8.3476 | 6.6952 | 5.6952 | 8.0428 | 10.0428 | 8.3476 | 14.0428 | 22.0856 | 32.1284 | 4.7052 | 8.3576 | 6.6952 | 5.6952 | 8.0428 | 10.0428 | 8.3576 | 14.0528 | 22.0956 | 32.1384 | 0.01
6.5708 | 9.2854 | 8.5708 | 7.5708 | 10.8562 | 12.8562 | 9.2854 | 16.8562 | 27.7123 | 40.5685 | 6.5808 | 9.2954 | 8.5708 | 7.5708 | 10.8562 | 12.8562 | 9.2954 | 16.8662 | 27.7223 | 40.5785 | 0.01
5.4473 | 8.7236 | 7.4473 | 6.4473 | 9.1709 | 11.1709 | 8.7236 | 15.1709 | 24.3418 | 35.5127 | 5.4573 | 8.7336 | 7.4473 | 6.4473 | 9.1709 | 11.1709 | 8.7336 | 15.1809 | 24.3518 | 35.5227 | 0.01
7.6753 | 9.8377 | 9.6753 | 8.6753 | 12.513 | 14.513 | 9.8377 | 18.513 | 31.026 | 45.539 | 7.6853 | 9.8477 | 9.6753 | 8.6753 | 12.513 | 14.513 | 9.8477 | 18.523 | 31.036 | 45.549 | 0.01
9.6671 | 10.8335 | 11.6671 | 10.6671 | 15.5006 | 17.5006 | 10.8335 | 21.5006 | 37.0012 | 54.5019 | 9.6771 | 10.8435 | 11.6671 | 10.6671 | 15.5006 | 17.5006 | 10.8435 | 21.5106 | 37.0112 | 54.5119 | 0.01
4.9451 | 8.4726 | 6.9451 | 5.9451 | 8.4177 | 10.4177 | 8.4726 | 14.4177 | 22.8353 | 33.253 | 4.9551 | 8.4826 | 6.9451 | 5.9451 | 8.4177 | 10.4177 | 8.4826 | 14.4277 | 22.8453 | 33.263 | 0.01
4.9771 | 8.4886 | 6.9771 | 5.9771 | 8.4657 | 10.4657 | 8.4886 | 14.4657 | 22.9314 | 33.3972 | 4.9871 | 8.4986 | 6.9771 | 5.9771 | 8.4657 | 10.4657 | 8.4986 | 14.4757 | 22.9414 | 33.4072 | 0.01
4.0819 | 8.041 | 6.0819 | 5.0819 | 7.1229 | 9.1229 | 8.041 | 13.1229 | 20.2458 | 29.3687 | 4.0919 | 8.051 | 6.0819 | 5.0819 | 7.1229 | 9.1229 | 8.051 | 13.1329 | 20.2558 | 29.3787 | 0.01
6.1632 | 9.0816 | 8.1632 | 7.1632 | 10.2448 | 12.2448 | 9.0816 | 16.2448 | 26.4896 | 38.7344 | 6.1732 | 9.0916 | 8.1632 | 7.1632 | 10.2448 | 12.2448 | 9.0916 | 16.2548 | 26.4996 | 38.7444 | 0.01
1.9933 | 6.9966 | 3.9933 | 2.9933 | 3.9899 | 5.9899 | 6.9966 | 9.9899 | 13.9799 | 19.9698 | 2.0033 | 7.0066 | 3.9933 | 2.9933 | 3.9899 | 5.9899 | 7.0066 | 9.9999 | 13.9899 | 19.9798 | 0.01
5.1012 | 8.5506 | 7.1012 | 6.1012 | 8.6518 | 10.6518 | 8.5506 | 14.6518 | 23.3036 | 33.9554 | 5.1112 | 8.5606 | 7.1012 | 6.1012 | 8.6518 | 10.6518 | 8.5606 | 14.6618 | 23.3136 | 33.9654 | 0.01
6.9555 | 9.4777 | 8.9555 | 7.9555 | 11.4332 | 13.4332 | 9.4777 | 17.4332 | 28.8664 | 42.2996 | 6.9655 | 9.4877 | 8.9555 | 7.9555 | 11.4332 | 13.4332 | 9.4877 | 17.4432 | 28.8764 | 42.3096 | 0.01
8.5592 | 10.2796 | 10.5592 | 9.5592 | 13.8389 | 15.8389 | 10.2796 | 19.8389 | 33.6777 | 49.5166 | 8.5692 | 10.2896 | 10.5592 | 9.5592 | 13.8389 | 15.8389 | 10.2896 | 19.8489 | 33.6877 | 49.5266 | 0.01
6.5105 | 9.2552 | 8.5105 | 7.5105 | 10.7657 | 12.7657 | 9.2552 | 16.7657 | 27.5315 | 40.2972 | 6.5205 | 9.2652 | 8.5105 | 7.5105 | 10.7657 | 12.7657 | 9.2652 | 16.7757 | 27.5415 | 40.3072 | 0.01
6.1667 | 9.0834 | 8.1667 | 7.1667 | 10.2501 | 12.2501 | 9.0834 | 16.2501 | 26.5002 | 38.7503 | 6.1767 | 9.0934 | 8.1667 | 7.1667 | 10.2501 | 12.2501 | 9.0934 | 16.2601 | 26.5102 | 38.7603 | 0.01
8.1147 | 10.0574 | 10.1147 | 9.1147 | 13.1721 | 15.1721 | 10.0574 | 19.1721 | 32.3442 | 47.5163 | 8.1247 | 10.0674 | 10.1147 | 9.1147 | 13.1721 | 15.1721 | 10.0674 | 19.1821 | 32.3542 | 47.5263 | 0.01
3.1051 | 7.5526 | 5.1051 | 4.1051 | 5.6577 | 7.6577 | 7.5526 | 11.6577 | 17.3153 | 24.973 | 3.1151 | 7.5626 | 5.1051 | 4.1051 | 5.6577 | 7.6577 | 7.5626 | 11.6677 | 17.3253 | 24.983 | 0.01
7.7699 | 9.885 | 9.7699 | 8.7699 | 12.6549 | 14.6549 | 9.885 | 18.6549 | 31.3098 | 45.9647 | 7.7799 | 9.895 | 9.7699 | 8.7699 | 12.6549 | 14.6549 | 9.895 | 18.6649 | 31.3198 | 45.9747 | 0.01
7.7437 | 9.8719 | 9.7437 | 8.7437 | 12.6156 | 14.6156 | 9.8719 | 18.6156 | 31.2312 | 45.8468 | 7.7537 | 9.8819 | 9.7437 | 8.7437 | 12.6156 | 14.6156 | 9.8819 | 18.6256 | 31.2412 | 45.8568 | 0.01
3.2528 | 7.6264 | 5.2528 | 4.2528 | 5.8791 | 7.8791 | 7.6264 | 11.8791 | 17.7583 | 25.6374 | 3.2628 | 7.6364 | 5.2528 | 4.2528 | 5.8791 | 7.8791 | 7.6364 | 11.8891 | 17.7683 | 25.6474 | 0.01
8.3933 | 10.1966 | 10.3933 | 9.3933 | 13.5899 | 15.5899 | 10.1966 | 19.5899 | 33.1798 | 48.7697 | 8.4033 | 10.2066 | 10.3933 | 9.3933 | 13.5899 | 15.5899 | 10.2066 | 19.5999 | 33.1898 | 48.7797 | 0.01
1.9955 | 6.9977 | 3.9955 | 2.9955 | 3.9932 | 5.9932 | 6.9977 | 9.9932 | 13.9864 | 19.9796 | 2.0055 | 7.0077 | 3.9955 | 2.9955 | 3.9932 | 5.9932 | 7.0077 | 10.0032 | 13.9964 | 19.9896 | 0.01
4.9613 | 8.4807 | 6.9613 | 5.9613 | 8.442 | 10.442 | 8.4807 | 14.442 | 22.8839 | 33.3259 | 4.9713 | 8.4907 | 6.9613 | 5.9613 | 8.442 | 10.442 | 8.4907 | 14.452 | 22.8939 | 33.3359 | 0.01
6.9724 | 9.4862 | 8.9724 | 7.9724 | 11.4587 | 13.4587 | 9.4862 | 17.4587 | 28.9173 | 42.376 | 6.9824 | 9.4962 | 8.9724 | 7.9724 | 11.4587 | 13.4587 | 9.4962 | 17.4687 | 28.9273 | 42.386 | 0.01
6.4531 | 9.2266 | 8.4531 | 7.4531 | 10.6797 | 12.6797 | 9.2266 | 16.6797 | 27.3594 | 40.0392 | 6.4631 | 9.2366 | 8.4531 | 7.4531 | 10.6797 | 12.6797 | 9.2366 | 16.6897 | 27.3694 | 40.0492 | 0.01
7.5656 | 9.7828 | 9.5656 | 8.5656 | 12.3483 | 14.3483 | 9.7828 | 18.3483 | 30.6967 | 45.045 | 7.5756 | 9.7928 | 9.5656 | 8.5656 | 12.3483 | 14.3483 | 9.7928 | 18.3583 | 30.7067 | 45.055 | 0.01
8.9413 | 10.4706 | 10.9413 | 9.9413 | 14.4119 | 16.4119 | 10.4706 | 20.4119 | 34.8238 | 51.2357 | 8.9513 | 10.4806 | 10.9413 | 9.9413 | 14.4119 | 16.4119 | 10.4806 | 20.4219 | 34.8338 | 51.2457 | 0.01
7.8795 | 9.9397 | 9.8795 | 8.8795 | 12.8192 | 14.8192 | 9.9397 | 18.8192 | 31.6384 | 46.4575 | 7.8895 | 9.9497 | 9.8795 | 8.8795 | 12.8192 | 14.8192 | 9.9497 | 18.8292 | 31.6484 | 46.4675 | 0.01
9.8929 | 10.9465 | 11.8929 | 10.8929 | 15.8394 | 17.8394 | 10.9465 | 21.8394 | 37.6788 | 55.5182 | 9.9029 | 10.9565 | 11.8929 | 10.8929 | 15.8394 | 17.8394 | 10.9565 | 21.8494 | 37.6888 | 55.5282 | 0.01
5.453 | 8.7265 | 7.453 | 6.453 | 9.1794 | 11.1794 | 8.7265 | 15.1794 | 24.3589 | 35.5383 | 5.463 | 8.7365 | 7.453 | 6.453 | 9.1794 | 11.1794 | 8.7365 | 15.1894 | 24.3689 | 35.5483 | 0.01
4.1572 | 8.0786 | 6.1572 | 5.1572 | 7.2357 | 9.2357 | 8.0786 | 13.2357 | 20.4715 | 29.7072 | 4.1672 | 8.0886 | 6.1572 | 5.1572 | 7.2357 | 9.2357 | 8.0886 | 13.2457 | 20.4815 | 29.7172 | 0.01
6.6304 | 9.3152 | 8.6304 | 7.6304 | 10.9456 | 12.9456 | 9.3152 | 16.9456 | 27.8912 | 40.8367 | 6.6404 | 9.3252 | 8.6304 | 7.6304 | 10.9456 | 12.9456 | 9.3252 | 16.9556 | 27.9012 | 40.8467 | 0.01
5.4603 | 8.7301 | 7.4603 | 6.4603 | 9.1904 | 11.1904 | 8.7301 | 15.1904 | 24.3809 | 35.5713 | 5.4703 | 8.7401 | 7.4603 | 6.4603 | 9.1904 | 11.1904 | 8.7401 | 15.2004 | 24.3909 | 35.5813 | 0.01
8.1682 | 10.0841 | 10.1682 | 9.1682 | 13.2523 | 15.2523 | 10.0841 | 19.2523 | 32.5045 | 47.7568 | 8.1782 | 10.0941 | 10.1682 | 9.1682 | 13.2523 | 15.2523 | 10.0941 | 19.2623 | 32.5145 | 47.7668 | 0.01
3.1459 | 7.5729 | 5.1459 | 4.1459 | 5.7188 | 7.7188 | 7.5729 | 11.7188 | 17.4377 | 25.1565 | 3.1559 | 7.5829 | 5.1459 | 4.1459 | 5.7188 | 7.7188 | 7.5829 | 11.7288 | 17.4477 | 25.1665 | 0.01
5.876 | 8.938 | 7.876 | 6.876 | 9.814 | 11.814 | 8.938 | 15.814 | 25.628 | 37.442 | 5.886 | 8.948 | 7.876 | 6.876 | 9.814 | 11.814 | 8.948 | 15.824 | 25.638 | 37.452 | 0.01
3.0444 | 7.5222 | 5.0444 | 4.0444 | 5.5667 | 7.5667 | 7.5222 | 11.5667 | 17.1333 | 24.7 | 3.0544 | 7.5322 | 5.0444 | 4.0444 | 5.5667 | 7.5667 | 7.5322 | 11.5767 | 17.1433 | 24.71 | 0.01
1.7266 | 6.8633 | 3.7266 | 2.7266 | 3.59 | 5.59 | 6.8633 | 9.59 | 13.1799 | 18.7699 | 1.7366 | 6.8733 | 3.7266 | 2.7266 | 3.59 | 5.59 | 6.8733 | 9.6 | 13.1899 | 18.7799 | 0.01
3.978 | 7.989 | 5.978 | 4.978 | 6.967 | 8.967 | 7.989 | 12.967 | 19.934 | 28.901 | 3.988 | 7.999 | 5.978 | 4.978 | 6.967 | 8.967 | 7.999 | 12.977 | 19.944 | 28.911 | 0.01
2.5753 | 7.2877 | 4.5753 | 3.5753 | 4.863 | 6.863 | 7.2877 | 10.863 | 15.726 | 22.589 | 2.5853 | 7.2977 | 4.5753 | 3.5753 | 4.863 | 6.863 | 7.2977 | 10.873 | 15.736 | 22.599 | 0.01
7.1333 | 9.5667 | 9.1333 | 8.1333 | 11.7 | 13.7 | 9.5667 | 17.7 | 29.4 | 43.1 | 7.1433 | 9.5767 | 9.1333 | 8.1333 | 11.7 | 13.7 | 9.5767 | 17.71 | 29.41 | 43.11 | 0.01
3.7989 | 7.8995 | 5.7989 | 4.7989 | 6.6984 | 8.6984 | 7.8995 | 12.6984 | 19.3968 | 28.0952 | 3.8089 | 7.9095 | 5.7989 | 4.7989 | 6.6984 | 8.6984 | 7.9095 | 12.7084 | 19.4068 | 28.1052 | 0.01
4.1942 | 8.0971 | 6.1942 | 5.1942 | 7.2913 | 9.2913 | 8.0971 | 13.2913 | 20.5826 | 29.8739 | 4.2042 | 8.1071 | 6.1942 | 5.1942 | 7.2913 | 9.2913 | 8.1071 | 13.3013 | 20.5926 | 29.8839 | 0.01
6.3221 | 9.161 | 8.3221 | 7.3221 | 10.4831 | 12.4831 | 9.161 | 16.4831 | 26.9663 | 39.4494 | 6.3321 | 9.171 | 8.3221 | 7.3221 | 10.4831 | 12.4831 | 9.171 | 16.4931 | 26.9763 | 39.4594 | 0.01
6.7721 | 9.386 | 8.7721 | 7.7721 | 11.1581 | 13.1581 | 9.386 | 17.1581 | 28.3163 | 41.4744 | 6.7821 | 9.396 | 8.7721 | 7.7721 | 11.1581 | 13.1581 | 9.396 | 17.1681 | 28.3263 | 41.4844 | 0.01
2.4844 | 7.2422 | 4.4844 | 3.4844 | 4.7265 | 6.7265 | 7.2422 | 10.7265 | 15.4531 | 22.1796 | 2.4944 | 7.2522 | 4.4844 | 3.4844 | 4.7265 | 6.7265 | 7.2522 | 10.7365 | 15.4631 | 22.1896 | 0.01
1.3352 | 6.6676 | 3.3352 | 2.3352 | 3.0029 | 5.0029 | 6.6676 | 9.0029 | 12.0057 | 17.0086 | 1.3452 | 6.6776 | 3.3352 | 2.3352 | 3.0029 | 5.0029 | 6.6776 | 9.0129 | 12.0157 | 17.0186 | 0.01
5.3983 | 8.6991 | 7.3983 | 6.3983 | 9.0974 | 11.0974 | 8.6991 | 15.0974 | 24.1948 | 35.2922 | 5.4083 | 8.7091 | 7.3983 | 6.3983 | 9.0974 | 11.0974 | 8.7091 | 15.1074 | 24.2048 | 35.3022 | 0.01
4.0997 | 8.0498 | 6.0997 | 5.0997 | 7.1495 | 9.1495 | 8.0498 | 13.1495 | 20.2991 | 29.4486 | 4.1097 | 8.0598 | 6.0997 | 5.0997 | 7.1495 | 9.1495 | 8.0598 | 13.1595 | 20.3091 | 29.4586 | 0.01
4.8389 | 8.4194 | 6.8389 | 5.8389 | 8.2583 | 10.2583 | 8.4194 | 14.2583 | 22.5167 | 32.775 | 4.8489 | 8.4294 | 6.8389 | 5.8389 | 8.2583 | 10.2583 | 8.4294 | 14.2683 | 22.5267 | 32.785 | 0.01
8.8632 | 10.4316 | 10.8632 | 9.8632 | 14.2948 | 16.2948 | 10.4316 | 20.2948 | 34.5896 | 50.8844 | 8.8732 | 10.4416 | 10.8632 | 9.8632 | 14.2948 | 16.2948 | 10.4416 | 20.3048 | 34.5996 | 50.8944 | 0.01
5.9752 | 8.9876 | 7.9752 | 6.9752 | 9.9628 | 11.9628 | 8.9876 | 15.9628 | 25.9257 | 37.8885 | 5.9852 | 8.9976 | 7.9752 | 6.9752 | 9.9628 | 11.9628 | 8.9976 | 15.9728 | 25.9357 | 37.8985 | 0.01
5.6012 | 8.8006 | 7.6012 | 6.6012 | 9.4018 | 11.4018 | 8.8006 | 15.4018 | 24.8036 | 36.2054 | 5.6112 | 8.8106 | 7.6012 | 6.6012 | 9.4018 | 11.4018 | 8.8106 | 15.4118 | 24.8136 | 36.2154 | 0.01
4.939 | 8.4695 | 6.939 | 5.939 | 8.4086 | 10.4086 | 8.4695 | 14.4086 | 22.8171 | 33.2257 | 4.949 | 8.4795 | 6.939 | 5.939 | 8.4086 | 10.4086 | 8.4795 | 14.4186 | 22.8271 | 33.2357 | 0.01
6.5777 | 9.2889 | 8.5777 | 7.5777 | 10.8666 | 12.8666 | 9.2889 | 16.8666 | 27.7332 | 40.5998 | 6.5877 | 9.2989 | 8.5777 | 7.5777 | 10.8666 | 12.8666 | 9.2989 | 16.8766 | 27.7432 | 40.6098 | 0.01
7.5768 | 9.7884 | 9.5768 | 8.5768 | 12.3652 | 14.3652 | 9.7884 | 18.3652 | 30.7305 | 45.0957 | 7.5868 | 9.7984 | 9.5768 | 8.5768 | 12.3652 | 14.3652 | 9.7984 | 18.3752 | 30.7405 | 45.1057 | 0.01
6.8322 | 9.4161 | 8.8322 | 7.8322 | 11.2483 | 13.2483 | 9.4161 | 17.2483 | 28.4966 | 41.7449 | 6.8422 | 9.4261 | 8.8322 | 7.8322 | 11.2483 | 13.2483 | 9.4261 | 17.2583 | 28.5066 | 41.7549 | 0.01
1.2409 | 6.6205 | 3.2409 | 2.2409 | 2.8614 | 4.8614 | 6.6205 | 8.8614 | 11.7228 | 16.5842 | 1.2509 | 6.6305 | 3.2409 | 2.2409 | 2.8614 | 4.8614 | 6.6305 | 8.8714 | 11.7328 | 16.5942 | 0.01
6.8982 | 9.4491 | 8.8982 | 7.8982 | 11.3473 | 13.3473 | 9.4491 | 17.3473 | 28.6945 | 42.0418 | 6.9082 | 9.4591 | 8.8982 | 7.8982 | 11.3473 | 13.3473 | 9.4591 | 17.3573 | 28.7045 | 42.0518 | 0.01
5.4805 | 8.7403 | 7.4805 | 6.4805 | 9.2208 | 11.2208 | 8.7403 | 15.2208 | 24.4416 | 35.6624 | 5.4905 | 8.7503 | 7.4805 | 6.4805 | 9.2208 | 11.2208 | 8.7503 | 15.2308 | 24.4516 | 35.6724 | 0.01
5.5055 | 8.7528 | 7.5055 | 6.5055 | 9.2583 | 11.2583 | 8.7528 | 15.2583 | 24.5166 | 35.775 | 5.5155 | 8.7628 | 7.5055 | 6.5055 | 9.2583 | 11.2583 | 8.7628 | 15.2683 | 24.5266 | 35.785 | 0.01
6.3791 | 9.1895 | 8.3791 | 7.3791 | 10.5686 | 12.5686 | 9.1895 | 16.5686 | 27.1372 | 39.7057 | 6.3891 | 9.1995 | 8.3791 | 7.3791 | 10.5686 | 12.5686 | 9.1995 | 16.5786 | 27.1472 | 39.7157 | 0.01
7.1075 | 9.5538 | 9.1075 | 8.1075 | 11.6613 | 13.6613 | 9.5538 | 17.6613 | 29.3226 | 42.984 | 7.1175 | 9.5638 | 9.1075 | 8.1075 | 11.6613 | 13.6613 | 9.5638 | 17.6713 | 29.3326 | 42.994 | 0.01
4.3758 | 8.1879 | 6.3758 | 5.3758 | 7.5637 | 9.5637 | 8.1879 | 13.5637 | 21.1275 | 30.6912 | 4.3858 | 8.1979 | 6.3758 | 5.3758 | 7.5637 | 9.5637 | 8.1979 | 13.5737 | 21.1375 | 30.7012 | 0.01
3.1194 | 7.5597 | 5.1194 | 4.1194 | 5.6791 | 7.6791 | 7.5597 | 11.6791 | 17.3582 | 25.0373 | 3.1294 | 7.5697 | 5.1194 | 4.1194 | 5.6791 | 7.6791 | 7.5697 | 11.6891 | 17.3682 | 25.0473 | 0.01
7.0201 | 9.5101 | 9.0201 | 8.0201 | 11.5302 | 13.5302 | 9.5101 | 17.5302 | 29.0604 | 42.5905 | 7.0301 | 9.5201 | 9.0201 | 8.0201 | 11.5302 | 13.5302 | 9.5201 | 17.5402 | 29.0704 | 42.6005 | 0.01
7.5622 | 9.7811 | 9.5622 | 8.5622 | 12.3433 | 14.3433 | 9.7811 | 18.3433 | 30.6866 | 45.03 | 7.5722 | 9.7911 | 9.5622 | 8.5622 | 12.3433 | 14.3433 | 9.7911 | 18.3533 | 30.6966 | 45.04 | 0.01
6.846 | 9.423 | 8.846 | 7.846 | 11.2689 | 13.2689 | 9.423 | 17.2689 | 28.5379 | 41.8068 | 6.856 | 9.433 | 8.846 | 7.846 | 11.2689 | 13.2689 | 9.433 | 17.2789 | 28.5479 | 41.8168 | 0.01
4.6009 | 8.3005 | 6.6009 | 5.6009 | 7.9014 | 9.9014 | 8.3005 | 13.9014 | 21.8028 | 31.7043 | 4.6109 | 8.3105 | 6.6009 | 5.6009 | 7.9014 | 9.9014 | 8.3105 | 13.9114 | 21.8128 | 31.7143 | 0.01
4.0996 | 8.0498 | 6.0996 | 5.0996 | 7.1495 | 9.1495 | 8.0498 | 13.1495 | 20.2989 | 29.4484 | 4.1096 | 8.0598 | 6.0996 | 5.0996 | 7.1495 | 9.1495 | 8.0598 | 13.1595 | 20.3089 | 29.4584 | 0.01
3.9553 | 7.9776 | 5.9553 | 4.9553 | 6.9329 | 8.9329 | 7.9776 | 12.9329 | 19.8658 | 28.7987 | 3.9653 | 7.9876 | 5.9553 | 4.9553 | 6.9329 | 8.9329 | 7.9876 | 12.9429 | 19.8758 | 28.8087 | 0.01
6.3421 | 9.1711 | 8.3421 | 7.3421 | 10.5132 | 12.5132 | 9.1711 | 16.5132 | 27.0264 | 39.5396 | 6.3521 | 9.1811 | 8.3421 | 7.3421 | 10.5132 | 12.5132 | 9.1811 | 16.5232 | 27.0364 | 39.5496 | 0.01
9.3127 | 10.6563 | 11.3127 | 10.3127 | 14.969 | 16.969 | 10.6563 | 20.969 | 35.9381 | 52.9071 | 9.3227 | 10.6663 | 11.3127 | 10.3127 | 14.969 | 16.969 | 10.6663 | 20.979 | 35.9481 | 52.9171 | 0.01
5.4219 | 8.711 | 7.4219 | 6.4219 | 9.1329 | 11.1329 | 8.711 | 15.1329 | 24.2657 | 35.3986 | 5.4319 | 8.721 | 7.4219 | 6.4219 | 9.1329 | 11.1329 | 8.721 | 15.1429 | 24.2757 | 35.4086 | 0.01
3.6288 | 7.8144 | 5.6288 | 4.6288 | 6.4432 | 8.4432 | 7.8144 | 12.4432 | 18.8865 | 27.3297 | 3.6388 | 7.8244 | 5.6288 | 4.6288 | 6.4432 | 8.4432 | 7.8244 | 12.4532 | 18.8965 | 27.3397 | 0.01
5.6238 | 8.8119 | 7.6238 | 6.6238 | 9.4356 | 11.4356 | 8.8119 | 15.4356 | 24.8713 | 36.3069 | 5.6338 | 8.8219 | 7.6238 | 6.6238 | 9.4356 | 11.4356 | 8.8219 | 15.4456 | 24.8813 | 36.3169 | 0.01
6.3482 | 9.1741 | 8.3482 | 7.3482 | 10.5223 | 12.5223 | 9.1741 | 16.5223 | 27.0446 | 39.5669 | 6.3582 | 9.1841 | 8.3482 | 7.3482 | 10.5223 | 12.5223 | 9.1841 | 16.5323 | 27.0546 | 39.5769 | 0.01
10.7899 | 11.3949 | 12.7899 | 11.7899 | 17.1848 | 19.1848 | 11.3949 | 23.1848 | 40.3696 | 59.5544 | 10.7999 | 11.4049 | 12.7899 | 11.7899 | 17.1848 | 19.1848 | 11.4049 | 23.1948 | 40.3796 | 59.5644 | 0.01
4.9975 | 8.4988 | 6.9975 | 5.9975 | 8.4963 | 10.4963 | 8.4988 | 14.4963 | 22.9926 | 33.489 | 5.0075 | 8.5088 | 6.9975 | 5.9975 | 8.4963 | 10.4963 | 8.5088 | 14.5063 | 23.0026 | 33.499 | 0.01
5.1208 | 8.5604 | 7.1208 | 6.1208 | 8.6812 | 10.6812 | 8.5604 | 14.6812 | 23.3625 | 34.0437 | 5.1308 | 8.5704 | 7.1208 | 6.1208 | 8.6812 | 10.6812 | 8.5704 | 14.6912 | 23.3725 | 34.0537 | 0.01
4.9466 | 8.4733 | 6.9466 | 5.9466 | 8.4199 | 10.4199 | 8.4733 | 14.4199 | 22.8398 | 33.2597 | 4.9566 | 8.4833 | 6.9466 | 5.9466 | 8.4199 | 10.4199 | 8.4833 | 14.4299 | 22.8498 | 33.2697 | 0.01
6.8683 | 9.4342 | 8.8683 | 7.8683 | 11.3025 | 13.3025 | 9.4342 | 17.3025 | 28.605 | 41.9075 | 6.8783 | 9.4442 | 8.8683 | 7.8683 | 11.3025 | 13.3025 | 9.4442 | 17.3125 | 28.615 | 41.9175 | 0.01
6.7307 | 9.3653 | 8.7307 | 7.7307 | 11.096 | 13.096 | 9.3653 | 17.096 | 28.192 | 41.288 | 6.7407 | 9.3753 | 8.7307 | 7.7307 | 11.096 | 13.096 | 9.3753 | 17.106 | 28.202 | 41.298 | 0.01
6.6858 | 9.3429 | 8.6858 | 7.6858 | 11.0287 | 13.0287 | 9.3429 | 17.0287 | 28.0575 | 41.0862 | 6.6958 | 9.3529 | 8.6858 | 7.6858 | 11.0287 | 13.0287 | 9.3529 | 17.0387 | 28.0675 | 41.0962 | 0.01
5.8933 | 8.9466 | 7.8933 | 6.8933 | 9.8399 | 11.8399 | 8.9466 | 15.8399 | 25.6798 | 37.5197 | 5.9033 | 8.9566 | 7.8933 | 6.8933 | 9.8399 | 11.8399 | 8.9566 | 15.8499 | 25.6898 | 37.5297 | 0.01
8.0544 | 10.0272 | 10.0544 | 9.0544 | 13.0817 | 15.0817 | 10.0272 | 19.0817 | 32.1633 | 47.245 | 8.0644 | 10.0372 | 10.0544 | 9.0544 | 13.0817 | 15.0817 | 10.0372 | 19.0917 | 32.1733 | 47.255 | 0.01
6.9633 | 9.4817 | 8.9633 | 7.9633 | 11.445 | 13.445 | 9.4817 | 17.445 | 28.89 | 42.335 | 6.9733 | 9.4917 | 8.9633 | 7.9633 | 11.445 | 13.445 | 9.4917 | 17.455 | 28.9 | 42.345 | 0.01
5.5051 | 8.7525 | 7.5051 | 6.5051 | 9.2576 | 11.2576 | 8.7525 | 15.2576 | 24.5152 | 35.7727 | 5.5151 | 8.7625 | 7.5051 | 6.5051 | 9.2576 | 11.2576 | 8.7625 | 15.2676 | 24.5252 | 35.7827 | 0.01
9.8582 | 10.9291 | 11.8582 | 10.8582 | 15.7873 | 17.7873 | 10.9291 | 21.7873 | 37.5746 | 55.3619 | 9.8682 | 10.9391 | 11.8582 | 10.8582 | 15.7873 | 17.7873 | 10.9391 | 21.7973 | 37.5846 | 55.3719 | 0.01
6.417 | 9.2085 | 8.417 | 7.417 | 10.6256 | 12.6256 | 9.2085 | 16.6256 | 27.2511 | 39.8767 | 6.427 | 9.2185 | 8.417 | 7.417 | 10.6256 | 12.6256 | 9.2185 | 16.6356 | 27.2611 | 39.8867 | 0.01
6.3882 | 9.1941 | 8.3882 | 7.3882 | 10.5822 | 12.5822 | 9.1941 | 16.5822 | 27.1645 | 39.7467 | 6.3982 | 9.2041 | 8.3882 | 7.3882 | 10.5822 | 12.5822 | 9.2041 | 16.5922 | 27.1745 | 39.7567 | 0.01
6.9699 | 9.4849 | 8.9699 | 7.9699 | 11.4548 | 13.4548 | 9.4849 | 17.4548 | 28.9096 | 42.3644 | 6.9799 | 9.4949 | 8.9699 | 7.9699 | 11.4548 | 13.4548 | 9.4949 | 17.4648 | 28.9196 | 42.3744 | 0.01
8.6251 | 10.3126 | 10.6251 | 9.6251 | 13.9377 | 15.9377 | 10.3126 | 19.9377 | 33.8753 | 49.813 | 8.6351 | 10.3226 | 10.6251 | 9.6251 | 13.9377 | 15.9377 | 10.3226 | 19.9477 | 33.8853 | 49.823 | 0.01
8.9815 | 10.4907 | 10.9815 | 9.9815 | 14.4722 | 16.4722 | 10.4907 | 20.4722 | 34.9444 | 51.4166 | 8.9915 | 10.5007 | 10.9815 | 9.9815 | 14.4722 | 16.4722 | 10.5007 | 20.4822 | 34.9544 | 51.4266 | 0.01
8.2166 | 10.1083 | 10.2166 | 9.2166 | 13.3248 | 15.3248 | 10.1083 | 19.3248 | 32.6497 | 47.9745 | 8.2266 | 10.1183 | 10.2166 | 9.2166 | 13.3248 | 15.3248 | 10.1183 | 19.3348 | 32.6597 | 47.9845 | 0.01
2.2054 | 7.1027 | 4.2054 | 3.2054 | 4.308 | 6.308 | 7.1027 | 10.308 | 14.6161 | 20.9241 | 2.2154 | 7.1127 | 4.2054 | 3.2054 | 4.308 | 6.308 | 7.1127 | 10.318 | 14.6261 | 20.9341 | 0.01
6.4717 | 9.2358 | 8.4717 | 7.4717 | 10.7075 | 12.7075 | 9.2358 | 16.7075 | 27.415 | 40.1224 | 6.4817 | 9.2458 | 8.4717 | 7.4717 | 10.7075 | 12.7075 | 9.2458 | 16.7175 | 27.425 | 40.1324 | 0.01
4.2513 | 8.1257 | 6.2513 | 5.2513 | 7.377 | 9.377 | 8.1257 | 13.377 | 20.754 | 30.131 | 4.2613 | 8.1357 | 6.2513 | 5.2513 | 7.377 | 9.377 | 8.1357 | 13.387 | 20.764 | 30.141 | 0.01
6.5595 | 9.2797 | 8.5595 | 7.5595 | 10.8392 | 12.8392 | 9.2797 | 16.8392 | 27.6785 | 40.5177 | 6.5695 | 9.2897 | 8.5595 | 7.5595 | 10.8392 | 12.8392 | 9.2897 | 16.8492 | 27.6885 | 40.5277 | 0.01
1.7548 | 6.8774 | 3.7548 | 2.7548 | 3.6322 | 5.6322 | 6.8774 | 9.6322 | 13.2644 | 18.8966 | 1.7648 | 6.8874 | 3.7548 | 2.7548 | 3.6322 | 5.6322 | 6.8874 | 9.6422 | 13.2744 | 18.9066 | 0.01
9.0243 | 10.5121 | 11.0243 | 10.0243 | 14.5364 | 16.5364 | 10.5121 | 20.5364 | 35.0729 | 51.6093 | 9.0343 | 10.5221 | 11.0243 | 10.0243 | 14.5364 | 16.5364 | 10.5221 | 20.5464 | 35.0829 | 51.6193 | 0.01
5.3876 | 8.6938 | 7.3876 | 6.3876 | 9.0814 | 11.0814 | 8.6938 | 15.0814 | 24.1628 | 35.2443 | 5.3976 | 8.7038 | 7.3876 | 6.3876 | 9.0814 | 11.0814 | 8.7038 | 15.0914 | 24.1728 | 35.2543 | 0.01
3.3907 | 7.6954 | 5.3907 | 4.3907 | 6.0861 | 8.0861 | 7.6954 | 12.0861 | 18.1721 | 26.2582 | 3.4007 | 7.7054 | 5.3907 | 4.3907 | 6.0861 | 8.0861 | 7.7054 | 12.0961 | 18.1821 | 26.2682 | 0.01
6.445 | 9.2225 | 8.445 | 7.445 | 10.6675 | 12.6675 | 9.2225 | 16.6675 | 27.3349 | 40.0024 | 6.455 | 9.2325 | 8.445 | 7.445 | 10.6675 | 12.6675 | 9.2325 | 16.6775 | 27.3449 | 40.0124 | 0.01
3.0261 | 7.5131 | 5.0261 | 4.0261 | 5.5392 | 7.5392 | 7.5131 | 11.5392 | 17.0783 | 24.6175 | 3.0361 | 7.5231 | 5.0261 | 4.0261 | 5.5392 | 7.5392 | 7.5231 | 11.5492 | 17.0883 | 24.6275 | 0.01
6.1399 | 9.0699 | 8.1399 | 7.1399 | 10.2098 | 12.2098 | 9.0699 | 16.2098 | 26.4196 | 38.6295 | 6.1499 | 9.0799 | 8.1399 | 7.1399 | 10.2098 | 12.2098 | 9.0799 | 16.2198 | 26.4296 | 38.6395 | 0.01
2.9477 | 7.4739 | 4.9477 | 3.9477 | 5.4216 | 7.4216 | 7.4739 | 11.4216 | 16.8432 | 24.2647 | 2.9577 | 7.4839 | 4.9477 | 3.9477 | 5.4216 | 7.4216 | 7.4839 | 11.4316 | 16.8532 | 24.2747 | 0.01
2.1588 | 7.0794 | 4.1588 | 3.1588 | 4.2382 | 6.2382 | 7.0794 | 10.2382 | 14.4765 | 20.7147 | 2.1688 | 7.0894 | 4.1588 | 3.1588 | 4.2382 | 6.2382 | 7.0894 | 10.2482 | 14.4865 | 20.7247 | 0.01
5.37 | 8.685 | 7.37 | 6.37 | 9.0549 | 11.0549 | 8.685 | 15.0549 | 24.1099 | 35.1648 | 5.38 | 8.695 | 7.37 | 6.37 | 9.0549 | 11.0549 | 8.695 | 15.0649 | 24.1199 | 35.1748 | 0.01
7.0615 | 9.5308 | 9.0615 | 8.0615 | 11.5923 | 13.5923 | 9.5308 | 17.5923 | 29.1846 | 42.7769 | 7.0715 | 9.5408 | 9.0615 | 8.0615 | 11.5923 | 13.5923 | 9.5408 | 17.6023 | 29.1946 | 42.7869 | 0.01
2.8948 | 7.4474 | 4.8948 | 3.8948 | 5.3422 | 7.3422 | 7.4474 | 11.3422 | 16.6844 | 24.0266 | 2.9048 | 7.4574 | 4.8948 | 3.8948 | 5.3422 | 7.3422 | 7.4574 | 11.3522 | 16.6944 | 24.0366 | 0.01
7.5473 | 9.7737 | 9.5473 | 8.5473 | 12.321 | 14.321 | 9.7737 | 18.321 | 30.6419 | 44.9629 | 7.5573 | 9.7837 | 9.5473 | 8.5473 | 12.321 | 14.321 | 9.7837 | 18.331 | 30.6519 | 44.9729 | 0.01
7.1431 | 9.5716 | 9.1431 | 8.1431 | 11.7147 | 13.7147 | 9.5716 | 17.7147 | 29.4293 | 43.144 | 7.1531 | 9.5816 | 9.1431 | 8.1431 | 11.7147 | 13.7147 | 9.5816 | 17.7247 | 29.4393 | 43.154 | 0.01
12.0964 | 12.0482 | 14.0964 | 13.0964 | 19.1446 | 21.1446 | 12.0964 | 25.1928 | 44.3373 | 65.4819 | 12.1064 | 12.0582 | 14.0964 | 13.0964 | 19.1446 | 21.1446 | 12.1064 | 25.2028 | 44.3473 | 65.4919 | 0.01
6.765 | 9.3825 | 8.765 | 7.765 | 11.1475 | 13.1475 | 9.3825 | 17.1475 | 28.2951 | 41.4426 | 6.775 | 9.3925 | 8.765 | 7.765 | 11.1475 | 13.1475 | 9.3925 | 17.1575 | 28.3051 | 41.4526 | 0.01
2.2718 | 7.1359 | 4.2718 | 3.2718 | 4.4077 | 6.4077 | 7.1359 | 10.4077 | 14.8153 | 21.223 | 2.2818 | 7.1459 | 4.2718 | 3.2718 | 4.4077 | 6.4077 | 7.1459 | 10.4177 | 14.8253 | 21.233 | 0.01
6.4769 | 9.2385 | 8.4769 | 7.4769 | 10.7154 | 12.7154 | 9.2385 | 16.7154 | 27.4308 | 40.1462 | 6.4869 | 9.2485 | 8.4769 | 7.4769 | 10.7154 | 12.7154 | 9.2485 | 16.7254 | 27.4408 | 40.1562 | 0.01
5.3268 | 8.6634 | 7.3268 | 6.3268 | 8.9902 | 10.9902 | 8.6634 | 14.9902 | 23.9805 | 34.9707 | 5.3368 | 8.6734 | 7.3268 | 6.3268 | 8.9902 | 10.9902 | 8.6734 | 15.0002 | 23.9905 | 34.9807 | 0.01
6.3209 | 9.1605 | 8.3209 | 7.3209 | 10.4814 | 12.4814 | 9.1605 | 16.4814 | 26.9627 | 39.4441 | 6.3309 | 9.1705 | 8.3209 | 7.3209 | 10.4814 | 12.4814 | 9.1705 | 16.4914 | 26.9727 | 39.4541 | 0.01
7.5282 | 9.7641 | 9.5282 | 8.5282 | 12.2923 | 14.2923 | 9.7641 | 18.2923 | 30.5847 | 44.877 | 7.5382 | 9.7741 | 9.5282 | 8.5282 | 12.2923 | 14.2923 | 9.7741 | 18.3023 | 30.5947 | 44.887 | 0.01
3.6141 | 7.8071 | 5.6141 | 4.6141 | 6.4212 | 8.4212 | 7.8071 | 12.4212 | 18.8424 | 27.2636 | 3.6241 | 7.8171 | 5.6141 | 4.6141 | 6.4212 | 8.4212 | 7.8171 | 12.4312 | 18.8524 | 27.2736 | 0.01
3.6248 | 7.8124 | 5.6248 | 4.6248 | 6.4372 | 8.4372 | 7.8124 | 12.4372 | 18.8744 | 27.3116 | 3.6348 | 7.8224 | 5.6248 | 4.6248 | 6.4372 | 8.4372 | 7.8224 | 12.4472 | 18.8844 | 27.3216 | 0.01
7.3335 | 9.6667 | 9.3335 | 8.3335 | 12.0002 | 14.0002 | 9.6667 | 18.0002 | 30.0004 | 44.0006 | 7.3435 | 9.6767 | 9.3335 | 8.3335 | 12.0002 | 14.0002 | 9.6767 | 18.0102 | 30.0104 | 44.0106 | 0.01
6.9821 | 9.491 | 8.9821 | 7.9821 | 11.4731 | 13.4731 | 9.491 | 17.4731 | 28.9462 | 42.4193 | 6.9921 | 9.501 | 8.9821 | 7.9821 | 11.4731 | 13.4731 | 9.501 | 17.4831 | 28.9562 | 42.4293 | 0.01
4.583 | 8.2915 | 6.583 | 5.583 | 7.8745 | 9.8745 | 8.2915 | 13.8745 | 21.749 | 31.6234 | 4.593 | 8.3015 | 6.583 | 5.583 | 7.8745 | 9.8745 | 8.3015 | 13.8845 | 21.759 | 31.6334 | 0.01
4.0577 | 8.0289 | 6.0577 | 5.0577 | 7.0866 | 9.0866 | 8.0289 | 13.0866 | 20.1732 | 29.2598 | 4.0677 | 8.0389 | 6.0577 | 5.0577 | 7.0866 | 9.0866 | 8.0389 | 13.0966 | 20.1832 | 29.2698 | 0.01
6.6071 | 9.3035 | 8.6071 | 7.6071 | 10.9106 | 12.9106 | 9.3035 | 16.9106 | 27.8213 | 40.7319 | 6.6171 | 9.3135 | 8.6071 | 7.6071 | 10.9106 | 12.9106 | 9.3135 | 16.9206 | 27.8313 | 40.7419 | 0.01
9.0369 | 10.5184 | 11.0369 | 10.0369 | 14.5553 | 16.5553 | 10.5184 | 20.5553 | 35.1106 | 51.6659 | 9.0469 | 10.5284 | 11.0369 | 10.0369 | 14.5553 | 16.5553 | 10.5284 | 20.5653 | 35.1206 | 51.6759 | 0.01
7.3809 | 9.6904 | 9.3809 | 8.3809 | 12.0713 | 14.0713 | 9.6904 | 18.0713 | 30.1426 | 44.2139 | 7.3909 | 9.7004 | 9.3809 | 8.3809 | 12.0713 | 14.0713 | 9.7004 | 18.0813 | 30.1526 | 44.2239 | 0.01
9.6282 | 10.8141 | 11.6282 | 10.6282 | 15.4423 | 17.4423 | 10.8141 | 21.4423 | 36.8847 | 54.327 | 9.6382 | 10.8241 | 11.6282 | 10.6282 | 15.4423 | 17.4423 | 10.8241 | 21.4523 | 36.8947 | 54.337 | 0.01
6.5968 | 9.2984 | 8.5968 | 7.5968 | 10.8952 | 12.8952 | 9.2984 | 16.8952 | 27.7903 | 40.6855 | 6.6068 | 9.3084 | 8.5968 | 7.5968 | 10.8952 | 12.8952 | 9.3084 | 16.9052 | 27.8003 | 40.6955 | 0.01
8.5168 | 10.2584 | 10.5168 | 9.5168 | 13.7751 | 15.7751 | 10.2584 | 19.7751 | 33.5503 | 49.3254 | 8.5268 | 10.2684 | 10.5168 | 9.5168 | 13.7751 | 15.7751 | 10.2684 | 19.7851 | 33.5603 | 49.3354 | 0.01
9.0004 | 10.5002 | 11.0004 | 10.0004 | 14.5006 | 16.5006 | 10.5002 | 20.5006 | 35.0013 | 51.5019 | 9.0104 | 10.5102 | 11.0004 | 10.0004 | 14.5006 | 16.5006 | 10.5102 | 20.5106 | 35.0113 | 51.5119 | 0.01
6.6461 | 9.3231 | 8.6461 | 7.6461 | 10.9692 | 12.9692 | 9.3231 | 16.9692 | 27.9384 | 40.9076 | 6.6561 | 9.3331 | 8.6461 | 7.6461 | 10.9692 | 12.9692 | 9.3331 | 16.9792 | 27.9484 | 40.9176 | 0.01
6.2957 | 9.1479 | 8.2957 | 7.2957 | 10.4436 | 12.4436 | 9.1479 | 16.4436 | 26.8871 | 39.3307 | 6.3057 | 9.1579 | 8.2957 | 7.2957 | 10.4436 | 12.4436 | 9.1579 | 16.4536 | 26.8971 | 39.3407 | 0.01
4.6554 | 8.3277 | 6.6554 | 5.6554 | 7.983 | 9.983 | 8.3277 | 13.983 | 21.9661 | 31.9491 | 4.6654 | 8.3377 | 6.6554 | 5.6554 | 7.983 | 9.983 | 8.3377 | 13.993 | 21.9761 | 31.9591 | 0.01
5.1508 | 8.5754 | 7.1508 | 6.1508 | 8.7262 | 10.7262 | 8.5754 | 14.7262 | 23.4524 | 34.1786 | 5.1608 | 8.5854 | 7.1508 | 6.1508 | 8.7262 | 10.7262 | 8.5854 | 14.7362 | 23.4624 | 34.1886 | 0.01
7.8893 | 9.9446 | 9.8893 | 8.8893 | 12.8339 | 14.8339 | 9.9446 | 18.8339 | 31.6679 | 46.5018 | 7.8993 | 9.9546 | 9.8893 | 8.8893 | 12.8339 | 14.8339 | 9.9546 | 18.8439 | 31.6779 | 46.5118 | 0.01
3.7649 | 7.8824 | 5.7649 | 4.7649 | 6.6473 | 8.6473 | 7.8824 | 12.6473 | 19.2946 | 27.9418 | 3.7749 | 7.8924 | 5.7649 | 4.7649 | 6.6473 | 8.6473 | 7.8924 | 12.6573 | 19.3046 | 27.9518 | 0.01
5.558 | 8.779 | 7.558 | 6.558 | 9.337 | 11.337 | 8.779 | 15.337 | 24.6741 | 36.0111 | 5.568 | 8.789 | 7.558 | 6.558 | 9.337 | 11.337 | 8.789 | 15.347 | 24.6841 | 36.0211 | 0.01
7.42 | 9.71 | 9.42 | 8.42 | 12.13 | 14.13 | 9.71 | 18.13 | 30.26 | 44.39 | 7.43 | 9.72 | 9.42 | 8.42 | 12.13 | 14.13 | 9.72 | 18.14 | 30.27 | 44.4 | 0.01
6.472 | 9.236 | 8.472 | 7.472 | 10.708 | 12.708 | 9.236 | 16.708 | 27.416 | 40.124 | 6.482 | 9.246 | 8.472 | 7.472 | 10.708 | 12.708 | 9.246 | 16.718 | 27.426 | 40.134 | 0.01
4.871 | 8.4355 | 6.871 | 5.871 | 8.3066 | 10.3066 | 8.4355 | 14.3066 | 22.6131 | 32.9197 | 4.881 | 8.4455 | 6.871 | 5.871 | 8.3066 | 10.3066 | 8.4455 | 14.3166 | 22.6231 | 32.9297 | 0.01
5.508 | 8.754 | 7.508 | 6.508 | 9.2621 | 11.2621 | 8.754 | 15.2621 | 24.5241 | 35.7862 | 5.518 | 8.764 | 7.508 | 6.508 | 9.2621 | 11.2621 | 8.764 | 15.2721 | 24.5341 | 35.7962 | 0.01
7.0059 | 9.5029 | 9.0059 | 8.0059 | 11.5088 | 13.5088 | 9.5029 | 17.5088 | 29.0177 | 42.5265 | 7.0159 | 9.5129 | 9.0059 | 8.0059 | 11.5088 | 13.5088 | 9.5129 | 17.5188 | 29.0277 | 42.5365 | 0.01
7.757 | 9.8785 | 9.757 | 8.757 | 12.6355 | 14.6355 | 9.8785 | 18.6355 | 31.271 | 45.9065 | 7.767 | 9.8885 | 9.757 | 8.757 | 12.6355 | 14.6355 | 9.8885 | 18.6455 | 31.281 | 45.9165 | 0.01
5.623 | 8.8115 | 7.623 | 6.623 | 9.4344 | 11.4344 | 8.8115 | 15.4344 | 24.8689 | 36.3033 | 5.633 | 8.8215 | 7.623 | 6.623 | 9.4344 | 11.4344 | 8.8215 | 15.4444 | 24.8789 | 36.3133 | 0.01
8.5794 | 10.2897 | 10.5794 | 9.5794 | 13.869 | 15.869 | 10.2897 | 19.869 | 33.7381 | 49.6071 | 8.5894 | 10.2997 | 10.5794 | 9.5794 | 13.869 | 15.869 | 10.2997 | 19.879 | 33.7481 | 49.6171 | 0.01
3.9507 | 7.9753 | 5.9507 | 4.9507 | 6.926 | 8.926 | 7.9753 | 12.926 | 19.852 | 28.778 | 3.9607 | 7.9853 | 5.9507 | 4.9507 | 6.926 | 8.926 | 7.9853 | 12.936 | 19.862 | 28.788 | 0.01
5.6655 | 8.8328 | 7.6655 | 6.6655 | 9.4983 | 11.4983 | 8.8328 | 15.4983 | 24.9965 | 36.4948 | 5.6755 | 8.8428 | 7.6655 | 6.6655 | 9.4983 | 11.4983 | 8.8428 | 15.5083 | 25.0065 | 36.5048 | 0.01
4.9787 | 8.4894 | 6.9787 | 5.9787 | 8.4681 | 10.4681 | 8.4894 | 14.4681 | 22.9362 | 33.4042 | 4.9887 | 8.4994 | 6.9787 | 5.9787 | 8.4681 | 10.4681 | 8.4994 | 14.4781 | 22.9462 | 33.4142 | 0.01
7.6227 | 9.8114 | 9.6227 | 8.6227 | 12.4341 | 14.4341 | 9.8114 | 18.4341 | 30.8682 | 45.3023 | 7.6327 | 9.8214 | 9.6227 | 8.6227 | 12.4341 | 14.4341 | 9.8214 | 18.4441 | 30.8782 | 45.3123 | 0.01
5.7922 | 8.8961 | 7.7922 | 6.7922 | 9.6883 | 11.6883 | 8.8961 | 15.6883 | 25.3766 | 37.0649 | 5.8022 | 8.9061 | 7.7922 | 6.7922 | 9.6883 | 11.6883 | 8.9061 | 15.6983 | 25.3866 | 37.0749 | 0.01
2.9192 | 7.4596 | 4.9192 | 3.9192 | 5.3788 | 7.3788 | 7.4596 | 11.3788 | 16.7575 | 24.1363 | 2.9292 | 7.4696 | 4.9192 | 3.9192 | 5.3788 | 7.3788 | 7.4696 | 11.3888 | 16.7675 | 24.1463 | 0.01
5.928 | 8.964 | 7.928 | 6.928 | 9.892 | 11.892 | 8.964 | 15.892 | 25.784 | 37.676 | 5.938 | 8.974 | 7.928 | 6.928 | 9.892 | 11.892 | 8.974 | 15.902 | 25.794 | 37.686 | 0.01
4.208 | 8.104 | 6.208 | 5.208 | 7.312 | 9.312 | 8.104 | 13.312 | 20.6239 | 29.9359 | 4.218 | 8.114 | 6.208 | 5.208 | 7.312 | 9.312 | 8.114 | 13.322 | 20.6339 | 29.9459 | 0.01
5.2939 | 8.6469 | 7.2939 | 6.2939 | 8.9408 | 10.9408 | 8.6469 | 14.9408 | 23.8817 | 34.8225 | 5.3039 | 8.6569 | 7.2939 | 6.2939 | 8.9408 | 10.9408 | 8.6569 | 14.9508 | 23.8917 | 34.8325 | 0.01
6.2531 | 9.1265 | 8.2531 | 7.2531 | 10.3796 | 12.3796 | 9.1265 | 16.3796 | 26.7592 | 39.1388 | 6.2631 | 9.1365 | 8.2531 | 7.2531 | 10.3796 | 12.3796 | 9.1365 | 16.3896 | 26.7692 | 39.1488 | 0.01
6.8091 | 9.4046 | 8.8091 | 7.8091 | 11.2137 | 13.2137 | 9.4046 | 17.2137 | 28.4274 | 41.6412 | 6.8191 | 9.4146 | 8.8091 | 7.8091 | 11.2137 | 13.2137 | 9.4146 | 17.2237 | 28.4374 | 41.6512 | 0.01
9.4171 | 10.7085 | 11.4171 | 10.4171 | 15.1256 | 17.1256 | 10.7085 | 21.1256 | 36.2512 | 53.3767 | 9.4271 | 10.7185 | 11.4171 | 10.4171 | 15.1256 | 17.1256 | 10.7185 | 21.1356 | 36.2612 | 53.3867 | 0.01
5.3234 | 8.6617 | 7.3234 | 6.3234 | 8.9851 | 10.9851 | 8.6617 | 14.9851 | 23.9702 | 34.9553 | 5.3334 | 8.6717 | 7.3234 | 6.3234 | 8.9851 | 10.9851 | 8.6717 | 14.9951 | 23.9802 | 34.9653 | 0.01
7.0344 | 9.5172 | 9.0344 | 8.0344 | 11.5515 | 13.5515 | 9.5172 | 17.5515 | 29.1031 | 42.6546 | 7.0444 | 9.5272 | 9.0344 | 8.0344 | 11.5515 | 13.5515 | 9.5272 | 17.5615 | 29.1131 | 42.6646 | 0.01
6.5479 | 9.2739 | 8.5479 | 7.5479 | 10.8218 | 12.8218 | 9.2739 | 16.8218 | 27.6437 | 40.4655 | 6.5579 | 9.2839 | 8.5479 | 7.5479 | 10.8218 | 12.8218 | 9.2839 | 16.8318 | 27.6537 | 40.4755 | 0.01
6.4934 | 9.2467 | 8.4934 | 7.4934 | 10.7401 | 12.7401 | 9.2467 | 16.7401 | 27.4801 | 40.2202 | 6.5034 | 9.2567 | 8.4934 | 7.4934 | 10.7401 | 12.7401 | 9.2567 | 16.7501 | 27.4901 | 40.2302 | 0.01
9.043 | 10.5215 | 11.043 | 10.043 | 14.5645 | 16.5645 | 10.5215 | 20.5645 | 35.1289 | 51.6934 | 9.053 | 10.5315 | 11.043 | 10.043 | 14.5645 | 16.5645 | 10.5315 | 20.5745 | 35.1389 | 51.7034 | 0.01
4.2503 | 8.1252 | 6.2503 | 5.2503 | 7.3755 | 9.3755 | 8.1252 | 13.3755 | 20.7509 | 30.1264 | 4.2603 | 8.1352 | 6.2503 | 5.2503 | 7.3755 | 9.3755 | 8.1352 | 13.3855 | 20.7609 | 30.1364 | 0.01
4.6551 | 8.3276 | 6.6551 | 5.6551 | 7.9827 | 9.9827 | 8.3276 | 13.9827 | 21.9654 | 31.9481 | 4.6651 | 8.3376 | 6.6551 | 5.6551 | 7.9827 | 9.9827 | 8.3376 | 13.9927 | 21.9754 | 31.9581 | 0.01
7.2956 | 9.6478 | 9.2956 | 8.2956 | 11.9435 | 13.9435 | 9.6478 | 17.9435 | 29.8869 | 43.8304 | 7.3056 | 9.6578 | 9.2956 | 8.2956 | 11.9435 | 13.9435 | 9.6578 | 17.9535 | 29.8969 | 43.8404 | 0.01
6.1556 | 9.0778 | 8.1556 | 7.1556 | 10.2334 | 12.2334 | 9.0778 | 16.2334 | 26.4668 | 38.7002 | 6.1656 | 9.0878 | 8.1556 | 7.1556 | 10.2334 | 12.2334 | 9.0878 | 16.2434 | 26.4768 | 38.7102 | 0.01
6.6144 | 9.3072 | 8.6144 | 7.6144 | 10.9216 | 12.9216 | 9.3072 | 16.9216 | 27.8432 | 40.7648 | 6.6244 | 9.3172 | 8.6144 | 7.6144 | 10.9216 | 12.9216 | 9.3172 | 16.9316 | 27.8532 | 40.7748 | 0.01
5.303 | 8.6515 | 7.303 | 6.303 | 8.9545 | 10.9545 | 8.6515 | 14.9545 | 23.9091 | 34.8636 | 5.313 | 8.6615 | 7.303 | 6.303 | 8.9545 | 10.9545 | 8.6615 | 14.9645 | 23.9191 | 34.8736 | 0.01
5.1456 | 8.5728 | 7.1456 | 6.1456 | 8.7184 | 10.7184 | 8.5728 | 14.7184 | 23.4369 | 34.1553 | 5.1556 | 8.5828 | 7.1456 | 6.1456 | 8.7184 | 10.7184 | 8.5828 | 14.7284 | 23.4469 | 34.1653 | 0.01
9.5864 | 10.7932 | 11.5864 | 10.5864 | 15.3796 | 17.3796 | 10.7932 | 21.3796 | 36.7592 | 54.1388 | 9.5964 | 10.8032 | 11.5864 | 10.5864 | 15.3796 | 17.3796 | 10.8032 | 21.3896 | 36.7692 | 54.1488 | 0.01
2.3841 | 7.1921 | 4.3841 | 3.3841 | 4.5762 | 6.5762 | 7.1921 | 10.5762 | 15.1524 | 21.7285 | 2.3941 | 7.2021 | 4.3841 | 3.3841 | 4.5762 | 6.5762 | 7.2021 | 10.5862 | 15.1624 | 21.7385 | 0.01
5.619 | 8.8095 | 7.619 | 6.619 | 9.4285 | 11.4285 | 8.8095 | 15.4285 | 24.8571 | 36.2856 | 5.629 | 8.8195 | 7.619 | 6.619 | 9.4285 | 11.4285 | 8.8195 | 15.4385 | 24.8671 | 36.2956 | 0.01
9.1739 | 10.587 | 11.1739 | 10.1739 | 14.7609 | 16.7609 | 10.587 | 20.7609 | 35.5217 | 52.2826 | 9.1839 | 10.597 | 11.1739 | 10.1739 | 14.7609 | 16.7609 | 10.597 | 20.7709 | 35.5317 | 52.2926 | 0.01
5.5091 | 8.7545 | 7.5091 | 6.5091 | 9.2636 | 11.2636 | 8.7545 | 15.2636 | 24.5272 | 35.7908 | 5.5191 | 8.7645 | 7.5091 | 6.5091 | 9.2636 | 11.2636 | 8.7645 | 15.2736 | 24.5372 | 35.8008 | 0.01
1.6872 | 6.8436 | 3.6872 | 2.6872 | 3.5309 | 5.5309 | 6.8436 | 9.5309 | 13.0617 | 18.5926 | 1.6972 | 6.8536 | 3.6872 | 2.6872 | 3.5309 | 5.5309 | 6.8536 | 9.5409 | 13.0717 | 18.6026 | 0.01
9.6443 | 10.8221 | 11.6443 | 10.6443 | 15.4664 | 17.4664 | 10.8221 | 21.4664 | 36.9328 | 54.3992 | 9.6543 | 10.8321 | 11.6443 | 10.6443 | 15.4664 | 17.4664 | 10.8321 | 21.4764 | 36.9428 | 54.4092 | 0.01
8.6989 | 10.3495 | 10.6989 | 9.6989 | 14.0484 | 16.0484 | 10.3495 | 20.0484 | 34.0968 | 50.1452 | 8.7089 | 10.3595 | 10.6989 | 9.6989 | 14.0484 | 16.0484 | 10.3595 | 20.0584 | 34.1068 | 50.1552 | 0.01
11.2292 | 11.6146 | 13.2292 | 12.2292 | 17.8437 | 19.8437 | 11.6146 | 23.8437 | 41.6875 | 61.5312 | 11.2392 | 11.6246 | 13.2292 | 12.2292 | 17.8437 | 19.8437 | 11.6246 | 23.8537 | 41.6975 | 61.5412 | 0.01
8.8814 | 10.4407 | 10.8814 | 9.8814 | 14.322 | 16.322 | 10.4407 | 20.322 | 34.6441 | 50.9661 | 8.8914 | 10.4507 | 10.8814 | 9.8814 | 14.322 | 16.322 | 10.4507 | 20.332 | 34.6541 | 50.9761 | 0.01
4.2468 | 8.1234 | 6.2468 | 5.2468 | 7.3702 | 9.3702 | 8.1234 | 13.3702 | 20.7403 | 30.1105 | 4.2568 | 8.1334 | 6.2468 | 5.2468 | 7.3702 | 9.3702 | 8.1334 | 13.3802 | 20.7503 | 30.1205 | 0.01
4.0644 | 8.0322 | 6.0644 | 5.0644 | 7.0967 | 9.0967 | 8.0322 | 13.0967 | 20.1933 | 29.29 | 4.0744 | 8.0422 | 6.0644 | 5.0644 | 7.0967 | 9.0967 | 8.0422 | 13.1067 | 20.2033 | 29.3 | 0.01
6.9188 | 9.4594 | 8.9188 | 7.9188 | 11.3781 | 13.3781 | 9.4594 | 17.3781 | 28.7563 | 42.1344 | 6.9288 | 9.4694 | 8.9188 | 7.9188 | 11.3781 | 13.3781 | 9.4694 | 17.3881 | 28.7663 | 42.1444 | 0.01
6.6996 | 9.3498 | 8.6996 | 7.6996 | 11.0495 | 13.0495 | 9.3498 | 17.0495 | 28.0989 | 41.1484 | 6.7096 | 9.3598 | 8.6996 | 7.6996 | 11.0495 | 13.0495 | 9.3598 | 17.0595 | 28.1089 | 41.1584 | 0.01
2.8424 | 7.4212 | 4.8424 | 3.8424 | 5.2635 | 7.2635 | 7.4212 | 11.2635 | 16.5271 | 23.7906 | 2.8524 | 7.4312 | 4.8424 | 3.8424 | 5.2635 | 7.2635 | 7.4312 | 11.2735 | 16.5371 | 23.8006 | 0.01
4.0657 | 8.0328 | 6.0657 | 5.0657 | 7.0985 | 9.0985 | 8.0328 | 13.0985 | 20.197 | 29.2955 | 4.0757 | 8.0428 | 6.0657 | 5.0657 | 7.0985 | 9.0985 | 8.0428 | 13.1085 | 20.207 | 29.3055 | 0.01
4.7146 | 8.3573 | 6.7146 | 5.7146 | 8.0719 | 10.0719 | 8.3573 | 14.0719 | 22.1437 | 32.2156 | 4.7246 | 8.3673 | 6.7146 | 5.7146 | 8.0719 | 10.0719 | 8.3673 | 14.0819 | 22.1537 | 32.2256 | 0.01
4.7268 | 8.3634 | 6.7268 | 5.7268 | 8.0902 | 10.0902 | 8.3634 | 14.0902 | 22.1804 | 32.2706 | 4.7368 | 8.3734 | 6.7268 | 5.7268 | 8.0902 | 10.0902 | 8.3734 | 14.1002 | 22.1904 | 32.2806 | 0.01
6.8306 | 9.4153 | 8.8306 | 7.8306 | 11.2459 | 13.2459 | 9.4153 | 17.2459 | 28.4919 | 41.7378 | 6.8406 | 9.4253 | 8.8306 | 7.8306 | 11.2459 | 13.2459 | 9.4253 | 17.2559 | 28.5019 | 41.7478 | 0.01
3.8975 | 7.9488 | 5.8975 | 4.8975 | 6.8463 | 8.8463 | 7.9488 | 12.8463 | 19.6926 | 28.5389 | 3.9075 | 7.9588 | 5.8975 | 4.8975 | 6.8463 | 8.8463 | 7.9588 | 12.8563 | 19.7026 | 28.5489 | 0.01
5.9003 | 8.9501 | 7.9003 | 6.9003 | 9.8504 | 11.8504 | 8.9501 | 15.8504 | 25.7009 | 37.5513 | 5.9103 | 8.9601 | 7.9003 | 6.9003 | 9.8504 | 11.8504 | 8.9601 | 15.8604 | 25.7109 | 37.5613 | 0.01
5.3318 | 8.6659 | 7.3318 | 6.3318 | 8.9977 | 10.9977 | 8.6659 | 14.9977 | 23.9954 | 34.993 | 5.3418 | 8.6759 | 7.3318 | 6.3318 | 8.9977 | 10.9977 | 8.6759 | 15.0077 | 24.0054 | 35.003 | 0.01
4.9579 | 8.4789 | 6.9579 | 5.9579 | 8.4368 | 10.4368 | 8.4789 | 14.4368 | 22.8736 | 33.3104 | 4.9679 | 8.4889 | 6.9579 | 5.9579 | 8.4368 | 10.4368 | 8.4889 | 14.4468 | 22.8836 | 33.3204 | 0.01
6.4693 | 9.2346 | 8.4693 | 7.4693 | 10.7039 | 12.7039 | 9.2346 | 16.7039 | 27.4078 | 40.1117 | 6.4793 | 9.2446 | 8.4693 | 7.4693 | 10.7039 | 12.7039 | 9.2446 | 16.7139 | 27.4178 | 40.1217 | 0.01
5.5471 | 8.7735 | 7.5471 | 6.5471 | 9.3206 | 11.3206 | 8.7735 | 15.3206 | 24.6413 | 35.9619 | 5.5571 | 8.7835 | 7.5471 | 6.5471 | 9.3206 | 11.3206 | 8.7835 | 15.3306 | 24.6513 | 35.9719 | 0.01
9.9466 | 10.9733 | 11.9466 | 10.9466 | 15.9199 | 17.9199 | 10.9733 | 21.9199 | 37.8399 | 55.7598 | 9.9566 | 10.9833 | 11.9466 | 10.9466 | 15.9199 | 17.9199 | 10.9833 | 21.9299 | 37.8499 | 55.7698 | 0.01
7.4375 | 9.7188 | 9.4375 | 8.4375 | 12.1563 | 14.1563 | 9.7188 | 18.1563 | 30.3126 | 44.469 | 7.4475 | 9.7288 | 9.4375 | 8.4375 | 12.1563 | 14.1563 | 9.7288 | 18.1663 | 30.3226 | 44.479 | 0.01
4.3121 | 8.1561 | 6.3121 | 5.3121 | 7.4682 | 9.4682 | 8.1561 | 13.4682 | 20.9364 | 30.4045 | 4.3221 | 8.1661 | 6.3121 | 5.3121 | 7.4682 | 9.4682 | 8.1661 | 13.4782 | 20.9464 | 30.4145 | 0.01
5.9724 | 8.9862 | 7.9724 | 6.9724 | 9.9586 | 11.9586 | 8.9862 | 15.9586 | 25.9171 | 37.8757 | 5.9824 | 8.9962 | 7.9724 | 6.9724 | 9.9586 | 11.9586 | 8.9962 | 15.9686 | 25.9271 | 37.8857 | 0.01
8.7536 | 10.3768 | 10.7536 | 9.7536 | 14.1304 | 16.1304 | 10.3768 | 20.1304 | 34.2609 | 50.3913 | 8.7636 | 10.3868 | 10.7536 | 9.7536 | 14.1304 | 16.1304 | 10.3868 | 20.1404 | 34.2709 | 50.4013 | 0.01
5.5862 | 8.7931 | 7.5862 | 6.5862 | 9.3793 | 11.3793 | 8.7931 | 15.3793 | 24.7586 | 36.138 | 5.5962 | 8.8031 | 7.5862 | 6.5862 | 9.3793 | 11.3793 | 8.8031 | 15.3893 | 24.7686 | 36.148 | 0.01
3.4881 | 7.744 | 5.4881 | 4.4881 | 6.2321 | 8.2321 | 7.744 | 12.2321 | 18.4642 | 26.6963 | 3.4981 | 7.754 | 5.4881 | 4.4881 | 6.2321 | 8.2321 | 7.754 | 12.2421 | 18.4742 | 26.7063 | 0.01
5.5062 | 8.7531 | 7.5062 | 6.5062 | 9.2593 | 11.2593 | 8.7531 | 15.2593 | 24.5187 | 35.778 | 5.5162 | 8.7631 | 7.5062 | 6.5062 | 9.2593 | 11.2593 | 8.7631 | 15.2693 | 24.5287 | 35.788 | 0.01
7.6439 | 9.822 | 9.6439 | 8.6439 | 12.4659 | 14.4659 | 9.822 | 18.4659 | 30.9318 | 45.3977 | 7.6539 | 9.832 | 9.6439 | 8.6439 | 12.4659 | 14.4659 | 9.832 | 18.4759 | 30.9418 | 45.4077 | 0.01
5.254 | 8.627 | 7.254 | 6.254 | 8.8809 | 10.8809 | 8.627 | 14.8809 | 23.7619 | 34.6428 | 5.264 | 8.637 | 7.254 | 6.254 | 8.8809 | 10.8809 | 8.637 | 14.8909 | 23.7719 | 34.6528 | 0.01
4.2232 | 8.1116 | 6.2232 | 5.2232 | 7.3348 | 9.3348 | 8.1116 | 13.3348 | 20.6696 | 30.0044 | 4.2332 | 8.1216 | 6.2232 | 5.2232 | 7.3348 | 9.3348 | 8.1216 | 13.3448 | 20.6796 | 30.0144 | 0.01
6.8151 | 9.4076 | 8.8151 | 7.8151 | 11.2227 | 13.2227 | 9.4076 | 17.2227 | 28.4453 | 41.668 | 6.8251 | 9.4176 | 8.8151 | 7.8151 | 11.2227 | 13.2227 | 9.4176 | 17.2327 | 28.4553 | 41.678 | 0.01
5.3333 | 8.6667 | 7.3333 | 6.3333 | 9 | 11 | 8.6667 | 15 | 24 | 34.9999 | 5.3433 | 8.6767 | 7.3333 | 6.3333 | 9 | 11 | 8.6767 | 15.01 | 24.01 | 35.0099 | 0.01
4.0377 | 8.0189 | 6.0377 | 5.0377 | 7.0566 | 9.0566 | 8.0189 | 13.0566 | 20.1131 | 29.1697 | 4.0477 | 8.0289 | 6.0377 | 5.0377 | 7.0566 | 9.0566 | 8.0289 | 13.0666 | 20.1231 | 29.1797 | 0.01
8.7767 | 10.3884 | 10.7767 | 9.7767 | 14.1651 | 16.1651 | 10.3884 | 20.1651 | 34.3302 | 50.4953 | 8.7867 | 10.3984 | 10.7767 | 9.7767 | 14.1651 | 16.1651 | 10.3984 | 20.1751 | 34.3402 | 50.5053 | 0.01
4.2765 | 8.1383 | 6.2765 | 5.2765 | 7.4148 | 9.4148 | 8.1383 | 13.4148 | 20.8296 | 30.2443 | 4.2865 | 8.1483 | 6.2765 | 5.2765 | 7.4148 | 9.4148 | 8.1483 | 13.4248 | 20.8396 | 30.2543 | 0.01
6.1788 | 9.0894 | 8.1788 | 7.1788 | 10.2683 | 12.2683 | 9.0894 | 16.2683 | 26.5365 | 38.8048 | 6.1888 | 9.0994 | 8.1788 | 7.1788 | 10.2683 | 12.2683 | 9.0994 | 16.2783 | 26.5465 | 38.8148 | 0.01
4.8286 | 8.4143 | 6.8286 | 5.8286 | 8.2429 | 10.2429 | 8.4143 | 14.2429 | 22.4857 | 32.7286 | 4.8386 | 8.4243 | 6.8286 | 5.8286 | 8.2429 | 10.2429 | 8.4243 | 14.2529 | 22.4957 | 32.7386 | 0.01
7.1539 | 9.577 | 9.1539 | 8.1539 | 11.7309 | 13.7309 | 9.577 | 17.7309 | 29.4618 | 43.1927 | 7.1639 | 9.587 | 9.1539 | 8.1539 | 11.7309 | 13.7309 | 9.587 | 17.7409 | 29.4718 | 43.2027 | 0.01
7.5051 | 9.7525 | 9.5051 | 8.5051 | 12.2576 | 14.2576 | 9.7525 | 18.2576 | 30.5152 | 44.7728 | 7.5151 | 9.7625 | 9.5051 | 8.5051 | 12.2576 | 14.2576 | 9.7625 | 18.2676 | 30.5252 | 44.7828 | 0.01
8.6284 | 10.3142 | 10.6284 | 9.6284 | 13.9426 | 15.9426 | 10.3142 | 19.9426 | 33.8852 | 49.8278 | 8.6384 | 10.3242 | 10.6284 | 9.6284 | 13.9426 | 15.9426 | 10.3242 | 19.9526 | 33.8952 | 49.8378 | 0.01
6.4705 | 9.2352 | 8.4705 | 7.4705 | 10.7057 | 12.7057 | 9.2352 | 16.7057 | 27.4114 | 40.1171 | 6.4805 | 9.2452 | 8.4705 | 7.4705 | 10.7057 | 12.7057 | 9.2452 | 16.7157 | 27.4214 | 40.1271 | 0.01
5.1058 | 8.5529 | 7.1058 | 6.1058 | 8.6586 | 10.6586 | 8.5529 | 14.6586 | 23.3173 | 33.9759 | 5.1158 | 8.5629 | 7.1058 | 6.1058 | 8.6586 | 10.6586 | 8.5629 | 14.6686 | 23.3273 | 33.9859 | 0.01
6.1713 | 9.0857 | 8.1713 | 7.1713 | 10.257 | 12.257 | 9.0857 | 16.257 | 26.514 | 38.7709 | 6.1813 | 9.0957 | 8.1713 | 7.1713 | 10.257 | 12.257 | 9.0957 | 16.267 | 26.524 | 38.7809 | 0.01
3.8207 | 7.9104 | 5.8207 | 4.8207 | 6.7311 | 8.7311 | 7.9104 | 12.7311 | 19.4621 | 28.1932 | 3.8307 | 7.9204 | 5.8207 | 4.8207 | 6.7311 | 8.7311 | 7.9204 | 12.7411 | 19.4721 | 28.2032 | 0.01
4.6634 | 8.3317 | 6.6634 | 5.6634 | 7.9952 | 9.9952 | 8.3317 | 13.9952 | 21.9903 | 31.9855 | 4.6734 | 8.3417 | 6.6634 | 5.6634 | 7.9952 | 9.9952 | 8.3417 | 14.0052 | 22.0003 | 31.9955 | 0.01
9.839 | 10.9195 | 11.839 | 10.839 | 15.7585 | 17.7585 | 10.9195 | 21.7585 | 37.5171 | 55.2756 | 9.849 | 10.9295 | 11.839 | 10.839 | 15.7585 | 17.7585 | 10.9295 | 21.7685 | 37.5271 | 55.2856 | 0.01
5.9254 | 8.9627 | 7.9254 | 6.9254 | 9.8881 | 11.8881 | 8.9627 | 15.8881 | 25.7762 | 37.6643 | 5.9354 | 8.9727 | 7.9254 | 6.9254 | 9.8881 | 11.8881 | 8.9727 | 15.8981 | 25.7862 | 37.6743 | 0.01
5.9787 | 8.9893 | 7.9787 | 6.9787 | 9.968 | 11.968 | 8.9893 | 15.968 | 25.936 | 37.9041 | 5.9887 | 8.9993 | 7.9787 | 6.9787 | 9.968 | 11.968 | 8.9993 | 15.978 | 25.946 | 37.9141 | 0.01
2.3372 | 7.1686 | 4.3372 | 3.3372 | 4.5058 | 6.5058 | 7.1686 | 10.5058 | 15.0116 | 21.5174 | 2.3472 | 7.1786 | 4.3372 | 3.3372 | 4.5058 | 6.5058 | 7.1786 | 10.5158 | 15.0216 | 21.5274 | 0.01
5.4146 | 8.7073 | 7.4146 | 6.4146 | 9.1219 | 11.1219 | 8.7073 | 15.1219 | 24.2438 | 35.3657 | 5.4246 | 8.7173 | 7.4146 | 6.4146 | 9.1219 | 11.1219 | 8.7173 | 15.1319 | 24.2538 | 35.3757 | 0.01
6.6838 | 9.3419 | 8.6838 | 7.6838 | 11.0257 | 13.0257 | 9.3419 | 17.0257 | 28.0514 | 41.077 | 6.6938 | 9.3519 | 8.6838 | 7.6838 | 11.0257 | 13.0257 | 9.3519 | 17.0357 | 28.0614 | 41.087 | 0.01
1.2105 | 6.6053 | 3.2105 | 2.2105 | 2.8158 | 4.8158 | 6.6053 | 8.8158 | 11.6316 | 16.4474 | 1.2205 | 6.6153 | 3.2105 | 2.2105 | 2.8158 | 4.8158 | 6.6153 | 8.8258 | 11.6416 | 16.4574 | 0.01
7.4824 | 9.7412 | 9.4824 | 8.4824 | 12.2237 | 14.2237 | 9.7412 | 18.2237 | 30.4473 | 44.671 | 7.4924 | 9.7512 | 9.4824 | 8.4824 | 12.2237 | 14.2237 | 9.7512 | 18.2337 | 30.4573 | 44.681 | 0.01
6.0927 | 9.0463 | 8.0927 | 7.0927 | 10.139 | 12.139 | 9.0463 | 16.139 | 26.2781 | 38.4171 | 6.1027 | 9.0563 | 8.0927 | 7.0927 | 10.139 | 12.139 | 9.0563 | 16.149 | 26.2881 | 38.4271 | 0.01
3.9913 | 7.9956 | 5.9913 | 4.9913 | 6.9869 | 8.9869 | 7.9956 | 12.9869 | 19.9739 | 28.9608 | 4.0013 | 8.0056 | 5.9913 | 4.9913 | 6.9869 | 8.9869 | 8.0056 | 12.9969 | 19.9839 | 28.9708 | 0.01
8.1269 | 10.0635 | 10.1269 | 9.1269 | 13.1904 | 15.1904 | 10.0635 | 19.1904 | 32.3808 | 47.5712 | 8.1369 | 10.0735 | 10.1269 | 9.1269 | 13.1904 | 15.1904 | 10.0735 | 19.2004 | 32.3908 | 47.5812 | 0.01
5.4364 | 8.7182 | 7.4364 | 6.4364 | 9.1546 | 11.1546 | 8.7182 | 15.1546 | 24.3092 | 35.4638 | 5.4464 | 8.7282 | 7.4364 | 6.4364 | 9.1546 | 11.1546 | 8.7282 | 15.1646 | 24.3192 | 35.4738 | 0.01
7.1821 | 9.591 | 9.1821 | 8.1821 | 11.7731 | 13.7731 | 9.591 | 17.7731 | 29.5463 | 43.3194 | 7.1921 | 9.601 | 9.1821 | 8.1821 | 11.7731 | 13.7731 | 9.601 | 17.7831 | 29.5563 | 43.3294 | 0.01
5.2544 | 8.6272 | 7.2544 | 6.2544 | 8.8816 | 10.8816 | 8.6272 | 14.8816 | 23.7633 | 34.6449 | 5.2644 | 8.6372 | 7.2544 | 6.2544 | 8.8816 | 10.8816 | 8.6372 | 14.8916 | 23.7733 | 34.6549 | 0.01
6.9219 | 9.461 | 8.9219 | 7.9219 | 11.3829 | 13.3829 | 9.461 | 17.3829 | 28.7658 | 42.1486 | 6.9319 | 9.471 | 8.9219 | 7.9219 | 11.3829 | 13.3829 | 9.471 | 17.3929 | 28.7758 | 42.1586 | 0.01
4.2326 | 8.1163 | 6.2326 | 5.2326 | 7.3488 | 9.3488 | 8.1163 | 13.3488 | 20.6977 | 30.0465 | 4.2426 | 8.1263 | 6.2326 | 5.2326 | 7.3488 | 9.3488 | 8.1263 | 13.3588 | 20.7077 | 30.0565 | 0.01
7.8659 | 9.9329 | 9.8659 | 8.8659 | 12.7988 | 14.7988 | 9.9329 | 18.7988 | 31.5977 | 46.3965 | 7.8759 | 9.9429 | 9.8659 | 8.8659 | 12.7988 | 14.7988 | 9.9429 | 18.8088 | 31.6077 | 46.4065 | 0.01
6.8237 | 9.4119 | 8.8237 | 7.8237 | 11.2356 | 13.2356 | 9.4119 | 17.2356 | 28.4712 | 41.7068 | 6.8337 | 9.4219 | 8.8237 | 7.8237 | 11.2356 | 13.2356 | 9.4219 | 17.2456 | 28.4812 | 41.7168 | 0.01
10.0714 | 11.0357 | 12.0714 | 11.0714 | 16.1071 | 18.1071 | 11.0357 | 22.1071 | 38.2142 | 56.3213 | 10.0814 | 11.0457 | 12.0714 | 11.0714 | 16.1071 | 18.1071 | 11.0457 | 22.1171 | 38.2242 | 56.3313 | 0.01
8.6333 | 10.3167 | 10.6333 | 9.6333 | 13.95 | 15.95 | 10.3167 | 19.95 | 33.8999 | 49.8499 | 8.6433 | 10.3267 | 10.6333 | 9.6333 | 13.95 | 15.95 | 10.3267 | 19.96 | 33.9099 | 49.8599 | 0.01
6.1212 | 9.0606 | 8.1212 | 7.1212 | 10.1818 | 12.1818 | 9.0606 | 16.1818 | 26.3636 | 38.5454 | 6.1312 | 9.0706 | 8.1212 | 7.1212 | 10.1818 | 12.1818 | 9.0706 | 16.1918 | 26.3736 | 38.5554 | 0.01
6.3032 | 9.1516 | 8.3032 | 7.3032 | 10.4548 | 12.4548 | 9.1516 | 16.4548 | 26.9097 | 39.3645 | 6.3132 | 9.1616 | 8.3032 | 7.3032 | 10.4548 | 12.4548 | 9.1616 | 16.4648 | 26.9197 | 39.3745 | 0.01
4.3758 | 8.1879 | 6.3758 | 5.3758 | 7.5637 | 9.5637 | 8.1879 | 13.5637 | 21.1273 | 30.691 | 4.3858 | 8.1979 | 6.3758 | 5.3758 | 7.5637 | 9.5637 | 8.1979 | 13.5737 | 21.1373 | 30.701 | 0.01
9.2988 | 10.6494 | 11.2988 | 10.2988 | 14.9482 | 16.9482 | 10.6494 | 20.9482 | 35.8964 | 52.8446 | 9.3088 | 10.6594 | 11.2988 | 10.2988 | 14.9482 | 16.9482 | 10.6594 | 20.9582 | 35.9064 | 52.8546 | 0.01
6.0363 | 9.0181 | 8.0363 | 7.0363 | 10.0544 | 12.0544 | 9.0181 | 16.0544 | 26.1089 | 38.1633 | 6.0463 | 9.0281 | 8.0363 | 7.0363 | 10.0544 | 12.0544 | 9.0281 | 16.0644 | 26.1189 | 38.1733 | 0.01
4.0855 | 8.0427 | 6.0855 | 5.0855 | 7.1282 | 9.1282 | 8.0427 | 13.1282 | 20.2564 | 29.3846 | 4.0955 | 8.0527 | 6.0855 | 5.0855 | 7.1282 | 9.1282 | 8.0527 | 13.1382 | 20.2664 | 29.3946 | 0.01
2.5889 | 7.2945 | 4.5889 | 3.5889 | 4.8834 | 6.8834 | 7.2945 | 10.8834 | 15.7668 | 22.6502 | 2.5989 | 7.3045 | 4.5889 | 3.5889 | 4.8834 | 6.8834 | 7.3045 | 10.8934 | 15.7768 | 22.6602 | 0.01
5.0002 | 8.5001 | 7.0002 | 6.0002 | 8.5003 | 10.5003 | 8.5001 | 14.5003 | 23.0006 | 33.5009 | 5.0102 | 8.5101 | 7.0002 | 6.0002 | 8.5003 | 10.5003 | 8.5101 | 14.5103 | 23.0106 | 33.5109 | 0.01
3.9935 | 7.9967 | 5.9935 | 4.9935 | 6.9902 | 8.9902 | 7.9967 | 12.9902 | 19.9804 | 28.9706 | 4.0035 | 8.0067 | 5.9935 | 4.9935 | 6.9902 | 8.9902 | 8.0067 | 13.0002 | 19.9904 | 28.9806 | 0.01
4.5745 | 8.2872 | 6.5745 | 5.5745 | 7.8617 | 9.8617 | 8.2872 | 13.8617 | 21.7234 | 31.5851 | 4.5845 | 8.2972 | 6.5745 | 5.5745 | 7.8617 | 9.8617 | 8.2972 | 13.8717 | 21.7334 | 31.5951 | 0.01
9.9779 | 10.9889 | 11.9779 | 10.9779 | 15.9668 | 17.9668 | 10.9889 | 21.9668 | 37.9337 | 55.9005 | 9.9879 | 10.9989 | 11.9779 | 10.9779 | 15.9668 | 17.9668 | 10.9989 | 21.9768 | 37.9437 | 55.9105 | 0.01
5.9845 | 8.9923 | 7.9845 | 6.9845 | 9.9768 | 11.9768 | 8.9923 | 15.9768 | 25.9536 | 37.9304 | 5.9945 | 9.0023 | 7.9845 | 6.9845 | 9.9768 | 11.9768 | 9.0023 | 15.9868 | 25.9636 | 37.9404 | 0.01
6.7095 | 9.3548 | 8.7095 | 7.7095 | 11.0643 | 13.0643 | 9.3548 | 17.0643 | 28.1286 | 41.1928 | 6.7195 | 9.3648 | 8.7095 | 7.7095 | 11.0643 | 13.0643 | 9.3648 | 17.0743 | 28.1386 | 41.2028 | 0.01
4.33 | 8.165 | 6.33 | 5.33 | 7.4951 | 9.4951 | 8.165 | 13.4951 | 20.9901 | 30.4852 | 4.34 | 8.175 | 6.33 | 5.33 | 7.4951 | 9.4951 | 8.175 | 13.5051 | 21.0001 | 30.4952 | 0.01
7.3109 | 9.6554 | 9.3109 | 8.3109 | 11.9663 | 13.9663 | 9.6554 | 17.9663 | 29.9327 | 43.899 | 7.3209 | 9.6654 | 9.3109 | 8.3109 | 11.9663 | 13.9663 | 9.6654 | 17.9763 | 29.9427 | 43.909 | 0.01
8.3704 | 10.1852 | 10.3704 | 9.3704 | 13.5557 | 15.5557 | 10.1852 | 19.5557 | 33.1113 | 48.667 | 8.3804 | 10.1952 | 10.3704 | 9.3704 | 13.5557 | 15.5557 | 10.1952 | 19.5657 | 33.1213 | 48.677 | 0.01
5.3059 | 8.6529 | 7.3059 | 6.3059 | 8.9588 | 10.9588 | 8.6529 | 14.9588 | 23.9177 | 34.8765 | 5.3159 | 8.6629 | 7.3059 | 6.3059 | 8.9588 | 10.9588 | 8.6629 | 14.9688 | 23.9277 | 34.8865 | 0.01
5.3629 | 8.6814 | 7.3629 | 6.3629 | 9.0443 | 11.0443 | 8.6814 | 15.0443 | 24.0887 | 35.133 | 5.3729 | 8.6914 | 7.3629 | 6.3629 | 9.0443 | 11.0443 | 8.6914 | 15.0543 | 24.0987 | 35.143 | 0.01
3.9816 | 7.9908 | 5.9816 | 4.9816 | 6.9725 | 8.9725 | 7.9908 | 12.9725 | 19.9449 | 28.9174 | 3.9916 | 8.0008 | 5.9816 | 4.9816 | 6.9725 | 8.9725 | 8.0008 | 12.9825 | 19.9549 | 28.9274 | 0.01
5.3166 | 8.6583 | 7.3166 | 6.3166 | 8.9749 | 10.9749 | 8.6583 | 14.9749 | 23.9499 | 34.9248 | 5.3266 | 8.6683 | 7.3166 | 6.3166 | 8.9749 | 10.9749 | 8.6683 | 14.9849 | 23.9599 | 34.9348 | 0.01
4.8471 | 8.4235 | 6.8471 | 5.8471 | 8.2706 | 10.2706 | 8.4235 | 14.2706 | 22.5412 | 32.8118 | 4.8571 | 8.4335 | 6.8471 | 5.8471 | 8.2706 | 10.2706 | 8.4335 | 14.2806 | 22.5512 | 32.8218 | 0.01
3.4432 | 7.7216 | 5.4432 | 4.4432 | 6.1648 | 8.1648 | 7.7216 | 12.1648 | 18.3295 | 26.4943 | 3.4532 | 7.7316 | 5.4432 | 4.4432 | 6.1648 | 8.1648 | 7.7316 | 12.1748 | 18.3395 | 26.5043 | 0.01
9.9646 | 10.9823 | 11.9646 | 10.9646 | 15.9469 | 17.9469 | 10.9823 | 21.9469 | 37.8938 | 55.8407 | 9.9746 | 10.9923 | 11.9646 | 10.9646 | 15.9469 | 17.9469 | 10.9923 | 21.9569 | 37.9038 | 55.8507 | 0.01
4.8739 | 8.4369 | 6.8739 | 5.8739 | 8.3108 | 10.3108 | 8.4369 | 14.3108 | 22.6217 | 32.9325 | 4.8839 | 8.4469 | 6.8739 | 5.8739 | 8.3108 | 10.3108 | 8.4469 | 14.3208 | 22.6317 | 32.9425 | 0.01
6.177 | 9.0885 | 8.177 | 7.177 | 10.2655 | 12.2655 | 9.0885 | 16.2655 | 26.531 | 38.7965 | 6.187 | 9.0985 | 8.177 | 7.177 | 10.2655 | 12.2655 | 9.0985 | 16.2755 | 26.541 | 38.8065 | 0.01
3.7875 | 7.8937 | 5.7875 | 4.7875 | 6.6812 | 8.6812 | 7.8937 | 12.6812 | 19.3625 | 28.0437 | 3.7975 | 7.9037 | 5.7875 | 4.7875 | 6.6812 | 8.6812 | 7.9037 | 12.6912 | 19.3725 | 28.0537 | 0.01
5.0807 | 8.5403 | 7.0807 | 6.0807 | 8.621 | 10.621 | 8.5403 | 14.621 | 23.242 | 33.863 | 5.0907 | 8.5503 | 7.0807 | 6.0807 | 8.621 | 10.621 | 8.5503 | 14.631 | 23.252 | 33.873 | 0.01
6.5686 | 9.2843 | 8.5686 | 7.5686 | 10.8529 | 12.8529 | 9.2843 | 16.8529 | 27.7059 | 40.5588 | 6.5786 | 9.2943 | 8.5686 | 7.5686 | 10.8529 | 12.8529 | 9.2943 | 16.8629 | 27.7159 | 40.5688 | 0.01
5.8438 | 8.9219 | 7.8438 | 6.8438 | 9.7658 | 11.7658 | 8.9219 | 15.7658 | 25.5315 | 37.2973 | 5.8538 | 8.9319 | 7.8438 | 6.8438 | 9.7658 | 11.7658 | 8.9319 | 15.7758 | 25.5415 | 37.3073 | 0.01
6.0958 | 9.0479 | 8.0958 | 7.0958 | 10.1438 | 12.1438 | 9.0479 | 16.1438 | 26.2875 | 38.4313 | 6.1058 | 9.0579 | 8.0958 | 7.0958 | 10.1438 | 12.1438 | 9.0579 | 16.1538 | 26.2975 | 38.4413 | 0.01
6.9493 | 9.4746 | 8.9493 | 7.9493 | 11.4239 | 13.4239 | 9.4746 | 17.4239 | 28.8478 | 42.2717 | 6.9593 | 9.4846 | 8.9493 | 7.9493 | 11.4239 | 13.4239 | 9.4846 | 17.4339 | 28.8578 | 42.2817 | 0.01
5.2162 | 8.6081 | 7.2162 | 6.2162 | 8.8242 | 10.8242 | 8.6081 | 14.8242 | 23.6485 | 34.4727 | 5.2262 | 8.6181 | 7.2162 | 6.2162 | 8.8242 | 10.8242 | 8.6181 | 14.8342 | 23.6585 | 34.4827 | 0.01
5.5135 | 8.7568 | 7.5135 | 6.5135 | 9.2703 | 11.2703 | 8.7568 | 15.2703 | 24.5406 | 35.8109 | 5.5235 | 8.7668 | 7.5135 | 6.5135 | 9.2703 | 11.2703 | 8.7668 | 15.2803 | 24.5506 | 35.8209 | 0.01
6.4323 | 9.2162 | 8.4323 | 7.4323 | 10.6485 | 12.6485 | 9.2162 | 16.6485 | 27.2969 | 39.9454 | 6.4423 | 9.2262 | 8.4323 | 7.4323 | 10.6485 | 12.6485 | 9.2262 | 16.6585 | 27.3069 | 39.9554 | 0.01
6.5298 | 9.2649 | 8.5298 | 7.5298 | 10.7947 | 12.7947 | 9.2649 | 16.7947 | 27.5894 | 40.3841 | 6.5398 | 9.2749 | 8.5298 | 7.5298 | 10.7947 | 12.7947 | 9.2749 | 16.8047 | 27.5994 | 40.3941 | 0.01
3.6047 | 7.8023 | 5.6047 | 4.6047 | 6.407 | 8.407 | 7.8023 | 12.407 | 18.814 | 27.221 | 3.6147 | 7.8123 | 5.6047 | 4.6047 | 6.407 | 8.407 | 7.8123 | 12.417 | 18.824 | 27.231 | 0.01
6.5074 | 9.2537 | 8.5074 | 7.5074 | 10.761 | 12.761 | 9.2537 | 16.761 | 27.5221 | 40.2831 | 6.5174 | 9.2637 | 8.5074 | 7.5074 | 10.761 | 12.761 | 9.2637 | 16.771 | 27.5321 | 40.2931 | 0.01
5.3909 | 8.6955 | 7.3909 | 6.3909 | 9.0864 | 11.0864 | 8.6955 | 15.0864 | 24.1728 | 35.2592 | 5.4009 | 8.7055 | 7.3909 | 6.3909 | 9.0864 | 11.0864 | 8.7055 | 15.0964 | 24.1828 | 35.2692 | 0.01
7.3437 | 9.6719 | 9.3437 | 8.3437 | 12.0156 | 14.0156 | 9.6719 | 18.0156 | 30.0312 | 44.0468 | 7.3537 | 9.6819 | 9.3437 | 8.3437 | 12.0156 | 14.0156 | 9.6819 | 18.0256 | 30.0412 | 44.0568 | 0.01
4.6308 | 8.3154 | 6.6308 | 5.6308 | 7.9462 | 9.9462 | 8.3154 | 13.9462 | 21.8924 | 31.8386 | 4.6408 | 8.3254 | 6.6308 | 5.6308 | 7.9462 | 9.9462 | 8.3254 | 13.9562 | 21.9024 | 31.8486 | 0.01
9.6453 | 10.8227 | 11.6453 | 10.6453 | 15.468 | 17.468 | 10.8227 | 21.468 | 36.936 | 54.404 | 9.6553 | 10.8327 | 11.6453 | 10.6453 | 15.468 | 17.468 | 10.8327 | 21.478 | 36.946 | 54.414 | 0.01
6.4225 | 9.2112 | 8.4225 | 7.4225 | 10.6337 | 12.6337 | 9.2112 | 16.6337 | 27.2675 | 39.9012 | 6.4325 | 9.2212 | 8.4225 | 7.4225 | 10.6337 | 12.6337 | 9.2212 | 16.6437 | 27.2775 | 39.9112 | 0.01
5.6668 | 8.8334 | 7.6668 | 6.6668 | 9.5002 | 11.5002 | 8.8334 | 15.5002 | 25.0004 | 36.5007 | 5.6768 | 8.8434 | 7.6668 | 6.6668 | 9.5002 | 11.5002 | 8.8434 | 15.5102 | 25.0104 | 36.5107 | 0.01
6.74 | 9.37 | 8.74 | 7.74 | 11.11 | 13.11 | 9.37 | 17.11 | 28.22 | 41.3301 | 6.75 | 9.38 | 8.74 | 7.74 | 11.11 | 13.11 | 9.38 | 17.12 | 28.23 | 41.3401 | 0.01
9.1685 | 10.5842 | 11.1685 | 10.1685 | 14.7527 | 16.7527 | 10.5842 | 20.7527 | 35.5054 | 52.258 | 9.1785 | 10.5942 | 11.1685 | 10.1685 | 14.7527 | 16.7527 | 10.5942 | 20.7627 | 35.5154 | 52.268 | 0.01
4.3763 | 8.1881 | 6.3763 | 5.3763 | 7.5644 | 9.5644 | 8.1881 | 13.5644 | 21.1288 | 30.6933 | 4.3863 | 8.1981 | 6.3763 | 5.3763 | 7.5644 | 9.5644 | 8.1981 | 13.5744 | 21.1388 | 30.7033 | 0.01
4.1411 | 8.0705 | 6.1411 | 5.1411 | 7.2116 | 9.2116 | 8.0705 | 13.2116 | 20.4233 | 29.6349 | 4.1511 | 8.0805 | 6.1411 | 5.1411 | 7.2116 | 9.2116 | 8.0805 | 13.2216 | 20.4333 | 29.6449 | 0.01
6.171 | 9.0855 | 8.171 | 7.171 | 10.2565 | 12.2565 | 9.0855 | 16.2565 | 26.5131 | 38.7696 | 6.181 | 9.0955 | 8.171 | 7.171 | 10.2565 | 12.2565 | 9.0955 | 16.2665 | 26.5231 | 38.7796 | 0.01
3.8576 | 7.9288 | 5.8576 | 4.8576 | 6.7865 | 8.7865 | 7.9288 | 12.7865 | 19.5729 | 28.3594 | 3.8676 | 7.9388 | 5.8576 | 4.8576 | 6.7865 | 8.7865 | 7.9388 | 12.7965 | 19.5829 | 28.3694 | 0.01
5.1285 | 8.5643 | 7.1285 | 6.1285 | 8.6928 | 10.6928 | 8.5643 | 14.6928 | 23.3855 | 34.0783 | 5.1385 | 8.5743 | 7.1285 | 6.1285 | 8.6928 | 10.6928 | 8.5743 | 14.7028 | 23.3955 | 34.0883 | 0.01
7.0864 | 9.5432 | 9.0864 | 8.0864 | 11.6296 | 13.6296 | 9.5432 | 17.6296 | 29.2592 | 42.8887 | 7.0964 | 9.5532 | 9.0864 | 8.0864 | 11.6296 | 13.6296 | 9.5532 | 17.6396 | 29.2692 | 42.8987 | 0.01
4.1163 | 8.0582 | 6.1163 | 5.1163 | 7.1745 | 9.1745 | 8.0582 | 13.1745 | 20.349 | 29.5235 | 4.1263 | 8.0682 | 6.1163 | 5.1163 | 7.1745 | 9.1745 | 8.0682 | 13.1845 | 20.359 | 29.5335 | 0.01
8.9564 | 10.4782 | 10.9564 | 9.9564 | 14.4346 | 16.4346 | 10.4782 | 20.4346 | 34.8692 | 51.3037 | 8.9664 | 10.4882 | 10.9564 | 9.9564 | 14.4346 | 16.4346 | 10.4882 | 20.4446 | 34.8792 | 51.3137 | 0.01
8.7441 | 10.3721 | 10.7441 | 9.7441 | 14.1162 | 16.1162 | 10.3721 | 20.1162 | 34.2324 | 50.3486 | 8.7541 | 10.3821 | 10.7441 | 9.7441 | 14.1162 | 16.1162 | 10.3821 | 20.1262 | 34.2424 | 50.3586 | 0.01
2.74 | 7.37 | 4.74 | 3.74 | 5.1101 | 7.1101 | 7.37 | 11.1101 | 16.2201 | 23.3302 | 2.75 | 7.38 | 4.74 | 3.74 | 5.1101 | 7.1101 | 7.38 | 11.1201 | 16.2301 | 23.3402 | 0.01
5.7804 | 8.8902 | 7.7804 | 6.7804 | 9.6707 | 11.6707 | 8.8902 | 15.6707 | 25.3413 | 37.012 | 5.7904 | 8.9002 | 7.7804 | 6.7804 | 9.6707 | 11.6707 | 8.9002 | 15.6807 | 25.3513 | 37.022 | 0.01
8.5548 | 10.2774 | 10.5548 | 9.5548 | 13.8321 | 15.8321 | 10.2774 | 19.8321 | 33.6643 | 49.4964 | 8.5648 | 10.2874 | 10.5548 | 9.5548 | 13.8321 | 15.8321 | 10.2874 | 19.8421 | 33.6743 | 49.5064 | 0.01
9.7354 | 10.8677 | 11.7354 | 10.7354 | 15.6031 | 17.6031 | 10.8677 | 21.6031 | 37.2063 | 54.8094 | 9.7454 | 10.8777 | 11.7354 | 10.7354 | 15.6031 | 17.6031 | 10.8777 | 21.6131 | 37.2163 | 54.8194 | 0.01
6.7498 | 9.3749 | 8.7498 | 7.7498 | 11.1247 | 13.1247 | 9.3749 | 17.1247 | 28.2493 | 41.374 | 6.7598 | 9.3849 | 8.7498 | 7.7498 | 11.1247 | 13.1247 | 9.3849 | 17.1347 | 28.2593 | 41.384 | 0.01
5.8147 | 8.9074 | 7.8147 | 6.8147 | 9.7221 | 11.7221 | 8.9074 | 15.7221 | 25.4441 | 37.1662 | 5.8247 | 8.9174 | 7.8147 | 6.8147 | 9.7221 | 11.7221 | 8.9174 | 15.7321 | 25.4541 | 37.1762 | 0.01
4.1528 | 8.0764 | 6.1528 | 5.1528 | 7.2293 | 9.2293 | 8.0764 | 13.2293 | 20.4585 | 29.6878 | 4.1628 | 8.0864 | 6.1528 | 5.1528 | 7.2293 | 9.2293 | 8.0864 | 13.2393 | 20.4685 | 29.6978 | 0.01
3.9873 | 7.9937 | 5.9873 | 4.9873 | 6.981 | 8.981 | 7.9937 | 12.981 | 19.962 | 28.943 | 3.9973 | 8.0037 | 5.9873 | 4.9873 | 6.981 | 8.981 | 8.0037 | 12.991 | 19.972 | 28.953 | 0.01
7.9613 | 9.9807 | 9.9613 | 8.9613 | 12.942 | 14.942 | 9.9807 | 18.942 | 31.8839 | 46.8259 | 7.9713 | 9.9907 | 9.9613 | 8.9613 | 12.942 | 14.942 | 9.9907 | 18.952 | 31.8939 | 46.8359 | 0.01
2.9631 | 7.4816 | 4.9631 | 3.9631 | 5.4447 | 7.4447 | 7.4816 | 11.4447 | 16.8894 | 24.3341 | 2.9731 | 7.4916 | 4.9631 | 3.9631 | 5.4447 | 7.4447 | 7.4916 | 11.4547 | 16.8994 | 24.3441 | 0.01
4.718 | 8.359 | 6.718 | 5.718 | 8.077 | 10.077 | 8.359 | 14.077 | 22.154 | 32.231 | 4.728 | 8.369 | 6.718 | 5.718 | 8.077 | 10.077 | 8.369 | 14.087 | 22.164 | 32.241 | 0.01
6.5567 | 9.2783 | 8.5567 | 7.5567 | 10.835 | 12.835 | 9.2783 | 16.835 | 27.67 | 40.5051 | 6.5667 | 9.2883 | 8.5567 | 7.5567 | 10.835 | 12.835 | 9.2883 | 16.845 | 27.68 | 40.5151 | 0.01
9.2868 | 10.6434 | 11.2868 | 10.2868 | 14.9302 | 16.9302 | 10.6434 | 20.9302 | 35.8604 | 52.7905 | 9.2968 | 10.6534 | 11.2868 | 10.2868 | 14.9302 | 16.9302 | 10.6534 | 20.9402 | 35.8704 | 52.8005 | 0.01
3.6374 | 7.8187 | 5.6374 | 4.6374 | 6.4561 | 8.4561 | 7.8187 | 12.4561 | 18.9123 | 27.3684 | 3.6474 | 7.8287 | 5.6374 | 4.6374 | 6.4561 | 8.4561 | 7.8287 | 12.4661 | 18.9223 | 27.3784 | 0.01
7.1885 | 9.5943 | 9.1885 | 8.1885 | 11.7828 | 13.7828 | 9.5943 | 17.7828 | 29.5656 | 43.3484 | 7.1985 | 9.6043 | 9.1885 | 8.1885 | 11.7828 | 13.7828 | 9.6043 | 17.7928 | 29.5756 | 43.3584 | 0.01
5.7584 | 8.8792 | 7.7584 | 6.7584 | 9.6376 | 11.6376 | 8.8792 | 15.6376 | 25.2751 | 36.9127 | 5.7684 | 8.8892 | 7.7584 | 6.7584 | 9.6376 | 11.6376 | 8.8892 | 15.6476 | 25.2851 | 36.9227 | 0.01
5.6182 | 8.8091 | 7.6182 | 6.6182 | 9.4274 | 11.4274 | 8.8091 | 15.4274 | 24.8547 | 36.2821 | 5.6282 | 8.8191 | 7.6182 | 6.6182 | 9.4274 | 11.4274 | 8.8191 | 15.4374 | 24.8647 | 36.2921 | 0.01
5.3742 | 8.6871 | 7.3742 | 6.3742 | 9.0613 | 11.0613 | 8.6871 | 15.0613 | 24.1225 | 35.1838 | 5.3842 | 8.6971 | 7.3742 | 6.3742 | 9.0613 | 11.0613 | 8.6971 | 15.0713 | 24.1325 | 35.1938 | 0.01
4.0427 | 8.0214 | 6.0427 | 5.0427 | 7.0641 | 9.0641 | 8.0214 | 13.0641 | 20.1282 | 29.1922 | 4.0527 | 8.0314 | 6.0427 | 5.0427 | 7.0641 | 9.0641 | 8.0314 | 13.0741 | 20.1382 | 29.2022 | 0.01
5.0499 | 8.525 | 7.0499 | 6.0499 | 8.5749 | 10.5749 | 8.525 | 14.5749 | 23.1497 | 33.7246 | 5.0599 | 8.535 | 7.0499 | 6.0499 | 8.5749 | 10.5749 | 8.535 | 14.5849 | 23.1597 | 33.7346 | 0.01
4.0014 | 8.0007 | 6.0014 | 5.0014 | 7.002 | 9.002 | 8.0007 | 13.002 | 20.0041 | 29.0061 | 4.0114 | 8.0107 | 6.0014 | 5.0014 | 7.002 | 9.002 | 8.0107 | 13.012 | 20.0141 | 29.0161 | 0.01
4.888 | 8.444 | 6.888 | 5.888 | 8.332 | 10.332 | 8.444 | 14.332 | 22.664 | 32.9959 | 4.898 | 8.454 | 6.888 | 5.888 | 8.332 | 10.332 | 8.454 | 14.342 | 22.674 | 33.0059 | 0.01
9.4534 | 10.7267 | 11.4534 | 10.4534 | 15.18 | 17.18 | 10.7267 | 21.18 | 36.3601 | 53.5401 | 9.4634 | 10.7367 | 11.4534 | 10.4534 | 15.18 | 17.18 | 10.7367 | 21.19 | 36.3701 | 53.5501 | 0.01
4.3719 | 8.186 | 6.3719 | 5.3719 | 7.5579 | 9.5579 | 8.186 | 13.5579 | 21.1157 | 30.6736 | 4.3819 | 8.196 | 6.3719 | 5.3719 | 7.5579 | 9.5579 | 8.196 | 13.5679 | 21.1257 | 30.6836 | 0.01
6.7859 | 9.393 | 8.7859 | 7.7859 | 11.1789 | 13.1789 | 9.393 | 17.1789 | 28.3578 | 41.5367 | 6.7959 | 9.403 | 8.7859 | 7.7859 | 11.1789 | 13.1789 | 9.403 | 17.1889 | 28.3678 | 41.5467 | 0.01
2.921 | 7.4605 | 4.921 | 3.921 | 5.3815 | 7.3815 | 7.4605 | 11.3815 | 16.763 | 24.1445 | 2.931 | 7.4705 | 4.921 | 3.921 | 5.3815 | 7.3815 | 7.4705 | 11.3915 | 16.773 | 24.1545 | 0.01
5.273 | 8.6365 | 7.273 | 6.273 | 8.9094 | 10.9094 | 8.6365 | 14.9094 | 23.8189 | 34.7283 | 5.283 | 8.6465 | 7.273 | 6.273 | 8.9094 | 10.9094 | 8.6465 | 14.9194 | 23.8289 | 34.7383 | 0.01
7.2406 | 9.6203 | 9.2406 | 8.2406 | 11.8609 | 13.8609 | 9.6203 | 17.8609 | 29.7219 | 43.5828 | 7.2506 | 9.6303 | 9.2406 | 8.2406 | 11.8609 | 13.8609 | 9.6303 | 17.8709 | 29.7319 | 43.5928 | 0.01
6.9972 | 9.4986 | 8.9972 | 7.9972 | 11.4958 | 13.4958 | 9.4986 | 17.4958 | 28.9915 | 42.4873 | 7.0072 | 9.5086 | 8.9972 | 7.9972 | 11.4958 | 13.4958 | 9.5086 | 17.5058 | 29.0015 | 42.4973 | 0.01
2.7682 | 7.3841 | 4.7682 | 3.7682 | 5.1523 | 7.1523 | 7.3841 | 11.1523 | 16.3046 | 23.4569 | 2.7782 | 7.3941 | 4.7682 | 3.7682 | 5.1523 | 7.1523 | 7.3941 | 11.1623 | 16.3146 | 23.4669 | 0.01
7.3579 | 9.679 | 9.3579 | 8.3579 | 12.0369 | 14.0369 | 9.679 | 18.0369 | 30.0738 | 44.1108 | 7.3679 | 9.689 | 9.3579 | 8.3579 | 12.0369 | 14.0369 | 9.689 | 18.0469 | 30.0838 | 44.1208 | 0.01
4.0153 | 8.0077 | 6.0153 | 5.0153 | 7.023 | 9.023 | 8.0077 | 13.023 | 20.046 | 29.0691 | 4.0253 | 8.0177 | 6.0153 | 5.0153 | 7.023 | 9.023 | 8.0177 | 13.033 | 20.056 | 29.0791 | 0.01
7.981 | 9.9905 | 9.981 | 8.981 | 12.9716 | 14.9716 | 9.9905 | 18.9716 | 31.9431 | 46.9147 | 7.991 | 10.0005 | 9.981 | 8.981 | 12.9716 | 14.9716 | 10.0005 | 18.9816 | 31.9531 | 46.9247 | 0.01
7.4117 | 9.7058 | 9.4117 | 8.4117 | 12.1175 | 14.1175 | 9.7058 | 18.1175 | 30.2351 | 44.3526 | 7.4217 | 9.7158 | 9.4117 | 8.4117 | 12.1175 | 14.1175 | 9.7158 | 18.1275 | 30.2451 | 44.3626 | 0.01
9.3358 | 10.6679 | 11.3358 | 10.3358 | 15.0036 | 17.0036 | 10.6679 | 21.0036 | 36.0073 | 53.0109 | 9.3458 | 10.6779 | 11.3358 | 10.3358 | 15.0036 | 17.0036 | 10.6779 | 21.0136 | 36.0173 | 53.0209 | 0.01
7.7372 | 9.8686 | 9.7372 | 8.7372 | 12.6059 | 14.6059 | 9.8686 | 18.6059 | 31.2117 | 45.8176 | 7.7472 | 9.8786 | 9.7372 | 8.7372 | 12.6059 | 14.6059 | 9.8786 | 18.6159 | 31.2217 | 45.8276 | 0.01
4.255 | 8.1275 | 6.255 | 5.255 | 7.3826 | 9.3826 | 8.1275 | 13.3826 | 20.7651 | 30.1477 | 4.265 | 8.1375 | 6.255 | 5.255 | 7.3826 | 9.3826 | 8.1375 | 13.3926 | 20.7751 | 30.1577 | 0.01
3.1525 | 7.5763 | 5.1525 | 4.1525 | 5.7288 | 7.7288 | 7.5763 | 11.7288 | 17.4576 | 25.1864 | 3.1625 | 7.5863 | 5.1525 | 4.1525 | 5.7288 | 7.7288 | 7.5863 | 11.7388 | 17.4676 | 25.1964 | 0.01
6.2043 | 9.1021 | 8.2043 | 7.2043 | 10.3064 | 12.3064 | 9.1021 | 16.3064 | 26.6128 | 38.9192 | 6.2143 | 9.1121 | 8.2043 | 7.2043 | 10.3064 | 12.3064 | 9.1121 | 16.3164 | 26.6228 | 38.9292 | 0.01
3.9566 | 7.9783 | 5.9566 | 4.9566 | 6.9349 | 8.9349 | 7.9783 | 12.9349 | 19.8699 | 28.8048 | 3.9666 | 7.9883 | 5.9566 | 4.9566 | 6.9349 | 8.9349 | 7.9883 | 12.9449 | 19.8799 | 28.8148 | 0.01
4.8382 | 8.4191 | 6.8382 | 5.8382 | 8.2573 | 10.2573 | 8.4191 | 14.2573 | 22.5146 | 32.7718 | 4.8482 | 8.4291 | 6.8382 | 5.8382 | 8.2573 | 10.2573 | 8.4291 | 14.2673 | 22.5246 | 32.7818 | 0.01
8.832 | 10.416 | 10.832 | 9.832 | 14.248 | 16.248 | 10.416 | 20.248 | 34.496 | 50.744 | 8.842 | 10.426 | 10.832 | 9.832 | 14.248 | 16.248 | 10.426 | 20.258 | 34.506 | 50.754 | 0.01
6.1256 | 9.0628 | 8.1256 | 7.1256 | 10.1883 | 12.1883 | 9.0628 | 16.1883 | 26.3767 | 38.565 | 6.1356 | 9.0728 | 8.1256 | 7.1256 | 10.1883 | 12.1883 | 9.0728 | 16.1983 | 26.3867 | 38.575 | 0.01
3.7788 | 7.8894 | 5.7788 | 4.7788 | 6.6682 | 8.6682 | 7.8894 | 12.6682 | 19.3364 | 28.0046 | 3.7888 | 7.8994 | 5.7788 | 4.7788 | 6.6682 | 8.6682 | 7.8994 | 12.6782 | 19.3464 | 28.0146 | 0.01
6.2079 | 9.1039 | 8.2079 | 7.2079 | 10.3118 | 12.3118 | 9.1039 | 16.3118 | 26.6236 | 38.9354 | 6.2179 | 9.1139 | 8.2079 | 7.2079 | 10.3118 | 12.3118 | 9.1139 | 16.3218 | 26.6336 | 38.9454 | 0.01
3.5199 | 7.7599 | 5.5199 | 4.5199 | 6.2798 | 8.2798 | 7.7599 | 12.2798 | 18.5596 | 26.8395 | 3.5299 | 7.7699 | 5.5199 | 4.5199 | 6.2798 | 8.2798 | 7.7699 | 12.2898 | 18.5696 | 26.8495 | 0.01
5.2902 | 8.6451 | 7.2902 | 6.2902 | 8.9353 | 10.9353 | 8.6451 | 14.9353 | 23.8707 | 34.806 | 5.3002 | 8.6551 | 7.2902 | 6.2902 | 8.9353 | 10.9353 | 8.6551 | 14.9453 | 23.8807 | 34.816 | 0.01
0.22536 | 6.1127 | 2.2254 | 1.2254 | 1.338 | 3.338 | 6.1127 | 7.338 | 8.6761 | 12.0141 | 0.23536 | 6.1227 | 2.2254 | 1.2254 | 1.338 | 3.338 | 6.1227 | 7.348 | 8.6861 | 12.0241 | 0.01
6.7913 | 9.3957 | 8.7913 | 7.7913 | 11.187 | 13.187 | 9.3957 | 17.187 | 28.374 | 41.5611 | 6.8013 | 9.4057 | 8.7913 | 7.7913 | 11.187 | 13.187 | 9.4057 | 17.197 | 28.384 | 41.5711 | 0.01
8.3235 | 10.1617 | 10.3235 | 9.3235 | 13.4852 | 15.4852 | 10.1617 | 19.4852 | 32.9704 | 48.4556 | 8.3335 | 10.1717 | 10.3235 | 9.3235 | 13.4852 | 15.4852 | 10.1717 | 19.4952 | 32.9804 | 48.4656 | 0.01
4.5906 | 8.2953 | 6.5906 | 5.5906 | 7.886 | 9.886 | 8.2953 | 13.886 | 21.7719 | 31.6579 | 4.6006 | 8.3053 | 6.5906 | 5.5906 | 7.886 | 9.886 | 8.3053 | 13.896 | 21.7819 | 31.6679 | 0.01
3.9131 | 7.9566 | 5.9131 | 4.9131 | 6.8697 | 8.8697 | 7.9566 | 12.8697 | 19.7394 | 28.609 | 3.9231 | 7.9666 | 5.9131 | 4.9131 | 6.8697 | 8.8697 | 7.9666 | 12.8797 | 19.7494 | 28.619 | 0.01
6.9782 | 9.4891 | 8.9782 | 7.9782 | 11.4673 | 13.4673 | 9.4891 | 17.4673 | 28.9346 | 42.4018 | 6.9882 | 9.4991 | 8.9782 | 7.9782 | 11.4673 | 13.4673 | 9.4991 | 17.4773 | 28.9446 | 42.4118 | 0.01
6.9963 | 9.4981 | 8.9963 | 7.9963 | 11.4944 | 13.4944 | 9.4981 | 17.4944 | 28.9889 | 42.4833 | 7.0063 | 9.5081 | 8.9963 | 7.9963 | 11.4944 | 13.4944 | 9.5081 | 17.5044 | 28.9989 | 42.4933 | 0.01
5.7612 | 8.8806 | 7.7612 | 6.7612 | 9.6418 | 11.6418 | 8.8806 | 15.6418 | 25.2835 | 36.9253 | 5.7712 | 8.8906 | 7.7612 | 6.7612 | 9.6418 | 11.6418 | 8.8906 | 15.6518 | 25.2935 | 36.9353 | 0.01
7.1508 | 9.5754 | 9.1508 | 8.1508 | 11.7262 | 13.7262 | 9.5754 | 17.7262 | 29.4524 | 43.1786 | 7.1608 | 9.5854 | 9.1508 | 8.1508 | 11.7262 | 13.7262 | 9.5854 | 17.7362 | 29.4624 | 43.1886 | 0.01
8.0391 | 10.0196 | 10.0391 | 9.0391 | 13.0587 | 15.0587 | 10.0196 | 19.0587 | 32.1174 | 47.1761 | 8.0491 | 10.0296 | 10.0391 | 9.0391 | 13.0587 | 15.0587 | 10.0296 | 19.0687 | 32.1274 | 47.1861 | 0.01
4.834 | 8.417 | 6.834 | 5.834 | 8.2511 | 10.2511 | 8.417 | 14.2511 | 22.5021 | 32.7532 | 4.844 | 8.427 | 6.834 | 5.834 | 8.2511 | 10.2511 | 8.427 | 14.2611 | 22.5121 | 32.7632 | 0.01
4.3051 | 8.1526 | 6.3051 | 5.3051 | 7.4577 | 9.4577 | 8.1526 | 13.4577 | 20.9154 | 30.3731 | 4.3151 | 8.1626 | 6.3051 | 5.3051 | 7.4577 | 9.4577 | 8.1626 | 13.4677 | 20.9254 | 30.3831 | 0.01
3.4266 | 7.7133 | 5.4266 | 4.4266 | 6.1399 | 8.1399 | 7.7133 | 12.1399 | 18.2798 | 26.4198 | 3.4366 | 7.7233 | 5.4266 | 4.4266 | 6.1399 | 8.1399 | 7.7233 | 12.1499 | 18.2898 | 26.4298 | 0.01
6.4406 | 9.2203 | 8.4406 | 7.4406 | 10.6608 | 12.6608 | 9.2203 | 16.6608 | 27.3217 | 39.9825 | 6.4506 | 9.2303 | 8.4406 | 7.4406 | 10.6608 | 12.6608 | 9.2303 | 16.6708 | 27.3317 | 39.9925 | 0.01
6.6586 | 9.3293 | 8.6586 | 7.6586 | 10.9878 | 12.9878 | 9.3293 | 16.9878 | 27.9757 | 40.9635 | 6.6686 | 9.3393 | 8.6586 | 7.6586 | 10.9878 | 12.9878 | 9.3393 | 16.9978 | 27.9857 | 40.9735 | 0.01
3.0639 | 7.532 | 5.0639 | 4.0639 | 5.5959 | 7.5959 | 7.532 | 11.5959 | 17.1918 | 24.7877 | 3.0739 | 7.542 | 5.0639 | 4.0639 | 5.5959 | 7.5959 | 7.542 | 11.6059 | 17.2018 | 24.7977 | 0.01
3.5654 | 7.7827 | 5.5654 | 4.5654 | 6.3482 | 8.3482 | 7.7827 | 12.3482 | 18.6963 | 27.0445 | 3.5754 | 7.7927 | 5.5654 | 4.5654 | 6.3482 | 8.3482 | 7.7927 | 12.3582 | 18.7063 | 27.0545 | 0.01
4.057 | 8.0285 | 6.057 | 5.057 | 7.0855 | 9.0855 | 8.0285 | 13.0855 | 20.1709 | 29.2564 | 4.067 | 8.0385 | 6.057 | 5.057 | 7.0855 | 9.0855 | 8.0385 | 13.0955 | 20.1809 | 29.2664 | 0.01
1.4505 | 6.7252 | 3.4505 | 2.4505 | 3.1757 | 5.1757 | 6.7252 | 9.1757 | 12.3514 | 17.527 | 1.4605 | 6.7352 | 3.4505 | 2.4505 | 3.1757 | 5.1757 | 6.7352 | 9.1857 | 12.3614 | 17.537 | 0.01
6.5149 | 9.2574 | 8.5149 | 7.5149 | 10.7723 | 12.7723 | 9.2574 | 16.7723 | 27.5446 | 40.3169 | 6.5249 | 9.2674 | 8.5149 | 7.5149 | 10.7723 | 12.7723 | 9.2674 | 16.7823 | 27.5546 | 40.3269 | 0.01
7.2334 | 9.6167 | 9.2334 | 8.2334 | 11.8501 | 13.8501 | 9.6167 | 17.8501 | 29.7001 | 43.5502 | 7.2434 | 9.6267 | 9.2334 | 8.2334 | 11.8501 | 13.8501 | 9.6267 | 17.8601 | 29.7101 | 43.5602 | 0.01
6.6848 | 9.3424 | 8.6848 | 7.6848 | 11.0272 | 13.0272 | 9.3424 | 17.0272 | 28.0543 | 41.0815 | 6.6948 | 9.3524 | 8.6848 | 7.6848 | 11.0272 | 13.0272 | 9.3524 | 17.0372 | 28.0643 | 41.0915 | 0.01
3.5748 | 7.7874 | 5.5748 | 4.5748 | 6.3623 | 8.3623 | 7.7874 | 12.3623 | 18.7245 | 27.0868 | 3.5848 | 7.7974 | 5.5748 | 4.5748 | 6.3623 | 8.3623 | 7.7974 | 12.3723 | 18.7345 | 27.0968 | 0.01
4.5511 | 8.2755 | 6.5511 | 5.5511 | 7.8266 | 9.8266 | 8.2755 | 13.8266 | 21.6532 | 31.4798 | 4.5611 | 8.2855 | 6.5511 | 5.5511 | 7.8266 | 9.8266 | 8.2855 | 13.8366 | 21.6632 | 31.4898 | 0.01
5.3338 | 8.6669 | 7.3338 | 6.3338 | 9.0007 | 11.0007 | 8.6669 | 15.0007 | 24.0014 | 35.0022 | 5.3438 | 8.6769 | 7.3338 | 6.3338 | 9.0007 | 11.0007 | 8.6769 | 15.0107 | 24.0114 | 35.0122 | 0.01
7.2404 | 9.6202 | 9.2404 | 8.2404 | 11.8606 | 13.8606 | 9.6202 | 17.8606 | 29.7211 | 43.5817 | 7.2504 | 9.6302 | 9.2404 | 8.2404 | 11.8606 | 13.8606 | 9.6302 | 17.8706 | 29.7311 | 43.5917 | 0.01
10.1468 | 11.0734 | 12.1468 | 11.1468 | 16.2203 | 18.2203 | 11.0734 | 22.2203 | 38.4405 | 56.6608 | 10.1568 | 11.0834 | 12.1468 | 11.1468 | 16.2203 | 18.2203 | 11.0834 | 22.2303 | 38.4505 | 56.6708 | 0.01
6.2529 | 9.1264 | 8.2529 | 7.2529 | 10.3793 | 12.3793 | 9.1264 | 16.3793 | 26.7586 | 39.1379 | 6.2629 | 9.1364 | 8.2529 | 7.2529 | 10.3793 | 12.3793 | 9.1364 | 16.3893 | 26.7686 | 39.1479 | 0.01
9.755 | 10.8775 | 11.755 | 10.755 | 15.6326 | 17.6326 | 10.8775 | 21.6326 | 37.2651 | 54.8977 | 9.765 | 10.8875 | 11.755 | 10.755 | 15.6326 | 17.6326 | 10.8875 | 21.6426 | 37.2751 | 54.9077 | 0.01
2.6007 | 7.3004 | 4.6007 | 3.6007 | 4.9011 | 6.9011 | 7.3004 | 10.9011 | 15.8022 | 22.7034 | 2.6107 | 7.3104 | 4.6007 | 3.6007 | 4.9011 | 6.9011 | 7.3104 | 10.9111 | 15.8122 | 22.7134 | 0.01
6.491 | 9.2455 | 8.491 | 7.491 | 10.7365 | 12.7365 | 9.2455 | 16.7365 | 27.4729 | 40.2094 | 6.501 | 9.2555 | 8.491 | 7.491 | 10.7365 | 12.7365 | 9.2555 | 16.7465 | 27.4829 | 40.2194 | 0.01
3.7051 | 7.8525 | 5.7051 | 4.7051 | 6.5576 | 8.5576 | 7.8525 | 12.5576 | 19.1153 | 27.6729 | 3.7151 | 7.8625 | 5.7051 | 4.7051 | 6.5576 | 8.5576 | 7.8625 | 12.5676 | 19.1253 | 27.6829 | 0.01
8.8596 | 10.4298 | 10.8596 | 9.8596 | 14.2894 | 16.2894 | 10.4298 | 20.2894 | 34.5788 | 50.8682 | 8.8696 | 10.4398 | 10.8596 | 9.8596 | 14.2894 | 16.2894 | 10.4398 | 20.2994 | 34.5888 | 50.8782 | 0.01
4.0418 | 8.0209 | 6.0418 | 5.0418 | 7.0627 | 9.0627 | 8.0209 | 13.0627 | 20.1254 | 29.1881 | 4.0518 | 8.0309 | 6.0418 | 5.0418 | 7.0627 | 9.0627 | 8.0309 | 13.0727 | 20.1354 | 29.1981 | 0.01
5.4082 | 8.7041 | 7.4082 | 6.4082 | 9.1122 | 11.1122 | 8.7041 | 15.1122 | 24.2245 | 35.3367 | 5.4182 | 8.7141 | 7.4082 | 6.4082 | 9.1122 | 11.1122 | 8.7141 | 15.1222 | 24.2345 | 35.3467 | 0.01
9.0073 | 10.5036 | 11.0073 | 10.0073 | 14.5109 | 16.5109 | 10.5036 | 20.5109 | 35.0219 | 51.5328 | 9.0173 | 10.5136 | 11.0073 | 10.0073 | 14.5109 | 16.5109 | 10.5136 | 20.5209 | 35.0319 | 51.5428 | 0.01
3.2126 | 7.6063 | 5.2126 | 4.2126 | 5.8188 | 7.8188 | 7.6063 | 11.8188 | 17.6377 | 25.4565 | 3.2226 | 7.6163 | 5.2126 | 4.2126 | 5.8188 | 7.8188 | 7.6163 | 11.8288 | 17.6477 | 25.4665 | 0.01
3.8567 | 7.9284 | 5.8567 | 4.8567 | 6.7851 | 8.7851 | 7.9284 | 12.7851 | 19.5702 | 28.3553 | 3.8667 | 7.9384 | 5.8567 | 4.8567 | 6.7851 | 8.7851 | 7.9384 | 12.7951 | 19.5802 | 28.3653 | 0.01
6.5668 | 9.2834 | 8.5668 | 7.5668 | 10.8501 | 12.8501 | 9.2834 | 16.8501 | 27.7003 | 40.5504 | 6.5768 | 9.2934 | 8.5668 | 7.5668 | 10.8501 | 12.8501 | 9.2934 | 16.8601 | 27.7103 | 40.5604 | 0.01
5.6779 | 8.839 | 7.6779 | 6.6779 | 9.5169 | 11.5169 | 8.839 | 15.5169 | 25.0337 | 36.5506 | 5.6879 | 8.849 | 7.6779 | 6.6779 | 9.5169 | 11.5169 | 8.849 | 15.5269 | 25.0437 | 36.5606 | 0.01
5.0931 | 8.5465 | 7.0931 | 6.0931 | 8.6396 | 10.6396 | 8.5465 | 14.6396 | 23.2793 | 33.9189 | 5.1031 | 8.5565 | 7.0931 | 6.0931 | 8.6396 | 10.6396 | 8.5565 | 14.6496 | 23.2893 | 33.9289 | 0.01
3.8637 | 7.9319 | 5.8637 | 4.8637 | 6.7956 | 8.7956 | 7.9319 | 12.7956 | 19.5912 | 28.3868 | 3.8737 | 7.9419 | 5.8637 | 4.8637 | 6.7956 | 8.7956 | 7.9419 | 12.8056 | 19.6012 | 28.3968 | 0.01
8.1234 | 10.0617 | 10.1234 | 9.1234 | 13.1851 | 15.1851 | 10.0617 | 19.1851 | 32.3703 | 47.5554 | 8.1334 | 10.0717 | 10.1234 | 9.1234 | 13.1851 | 15.1851 | 10.0717 | 19.1951 | 32.3803 | 47.5654 | 0.01
7.0773 | 9.5386 | 9.0773 | 8.0773 | 11.6159 | 13.6159 | 9.5386 | 17.6159 | 29.2318 | 42.8477 | 7.0873 | 9.5486 | 9.0773 | 8.0773 | 11.6159 | 13.6159 | 9.5486 | 17.6259 | 29.2418 | 42.8577 | 0.01
7.3068 | 9.6534 | 9.3068 | 8.3068 | 11.9602 | 13.9602 | 9.6534 | 17.9602 | 29.9205 | 43.8807 | 7.3168 | 9.6634 | 9.3068 | 8.3068 | 11.9602 | 13.9602 | 9.6634 | 17.9702 | 29.9305 | 43.8907 | 0.01
8.2874 | 10.1437 | 10.2874 | 9.2874 | 13.4311 | 15.4311 | 10.1437 | 19.4311 | 32.8623 | 48.2934 | 8.2974 | 10.1537 | 10.2874 | 9.2874 | 13.4311 | 15.4311 | 10.1537 | 19.4411 | 32.8723 | 48.3034 | 0.01
3.1034 | 7.5517 | 5.1034 | 4.1034 | 5.6551 | 7.6551 | 7.5517 | 11.6551 | 17.3102 | 24.9653 | 3.1134 | 7.5617 | 5.1034 | 4.1034 | 5.6551 | 7.6551 | 7.5617 | 11.6651 | 17.3202 | 24.9753 | 0.01
7.6587 | 9.8293 | 9.6587 | 8.6587 | 12.488 | 14.488 | 9.8293 | 18.488 | 30.976 | 45.464 | 7.6687 | 9.8393 | 9.6587 | 8.6587 | 12.488 | 14.488 | 9.8393 | 18.498 | 30.986 | 45.474 | 0.01
6.0628 | 9.0314 | 8.0628 | 7.0628 | 10.0943 | 12.0943 | 9.0314 | 16.0943 | 26.1885 | 38.2828 | 6.0728 | 9.0414 | 8.0628 | 7.0628 | 10.0943 | 12.0943 | 9.0414 | 16.1043 | 26.1985 | 38.2928 | 0.01
3.9967 | 7.9984 | 5.9967 | 4.9967 | 6.9951 | 8.9951 | 7.9984 | 12.9951 | 19.9902 | 28.9853 | 4.0067 | 8.0084 | 5.9967 | 4.9967 | 6.9951 | 8.9951 | 8.0084 | 13.0051 | 20.0002 | 28.9953 | 0.01
8.4404 | 10.2202 | 10.4404 | 9.4404 | 13.6606 | 15.6606 | 10.2202 | 19.6606 | 33.3212 | 48.9817 | 8.4504 | 10.2302 | 10.4404 | 9.4404 | 13.6606 | 15.6606 | 10.2302 | 19.6706 | 33.3312 | 48.9917 | 0.01
3.7597 | 7.8798 | 5.7597 | 4.7597 | 6.6395 | 8.6395 | 7.8798 | 12.6395 | 19.279 | 27.9185 | 3.7697 | 7.8898 | 5.7597 | 4.7597 | 6.6395 | 8.6395 | 7.8898 | 12.6495 | 19.289 | 27.9285 | 0.01
3.6668 | 7.8334 | 5.6668 | 4.6668 | 6.5002 | 8.5002 | 7.8334 | 12.5002 | 19.0005 | 27.5007 | 3.6768 | 7.8434 | 5.6668 | 4.6668 | 6.5002 | 8.5002 | 7.8434 | 12.5102 | 19.0105 | 27.5107 | 0.01
4.5056 | 8.2528 | 6.5056 | 5.5056 | 7.7584 | 9.7584 | 8.2528 | 13.7584 | 21.5168 | 31.2752 | 4.5156 | 8.2628 | 6.5056 | 5.5056 | 7.7584 | 9.7584 | 8.2628 | 13.7684 | 21.5268 | 31.2852 | 0.01
3.8066 | 7.9033 | 5.8066 | 4.8066 | 6.7098 | 8.7098 | 7.9033 | 12.7098 | 19.4197 | 28.1295 | 3.8166 | 7.9133 | 5.8066 | 4.8066 | 6.7098 | 8.7098 | 7.9133 | 12.7198 | 19.4297 | 28.1395 | 0.01
4.057 | 8.0285 | 6.057 | 5.057 | 7.0856 | 9.0856 | 8.0285 | 13.0856 | 20.1711 | 29.2567 | 4.067 | 8.0385 | 6.057 | 5.057 | 7.0856 | 9.0856 | 8.0385 | 13.0956 | 20.1811 | 29.2667 | 0.01
4.0248 | 8.0124 | 6.0248 | 5.0248 | 7.0372 | 9.0372 | 8.0124 | 13.0372 | 20.0743 | 29.1115 | 4.0348 | 8.0224 | 6.0248 | 5.0248 | 7.0372 | 9.0372 | 8.0224 | 13.0472 | 20.0843 | 29.1215 | 0.01
4.3617 | 8.1808 | 6.3617 | 5.3617 | 7.5425 | 9.5425 | 8.1808 | 13.5425 | 21.085 | 30.6275 | 4.3717 | 8.1908 | 6.3617 | 5.3617 | 7.5425 | 9.5425 | 8.1908 | 13.5525 | 21.095 | 30.6375 | 0.01
2.9596 | 7.4798 | 4.9596 | 3.9596 | 5.4394 | 7.4394 | 7.4798 | 11.4394 | 16.8788 | 24.3181 | 2.9696 | 7.4898 | 4.9596 | 3.9596 | 5.4394 | 7.4394 | 7.4898 | 11.4494 | 16.8888 | 24.3281 | 0.01
6.0298 | 9.0149 | 8.0298 | 7.0298 | 10.0448 | 12.0448 | 9.0149 | 16.0448 | 26.0895 | 38.1343 | 6.0398 | 9.0249 | 8.0298 | 7.0298 | 10.0448 | 12.0448 | 9.0249 | 16.0548 | 26.0995 | 38.1443 | 0.01
6.0714 | 9.0357 | 8.0714 | 7.0714 | 10.1071 | 12.1071 | 9.0357 | 16.1071 | 26.2141 | 38.3212 | 6.0814 | 9.0457 | 8.0714 | 7.0714 | 10.1071 | 12.1071 | 9.0457 | 16.1171 | 26.2241 | 38.3312 | 0.01
7.1541 | 9.5771 | 9.1541 | 8.1541 | 11.7312 | 13.7312 | 9.5771 | 17.7312 | 29.4624 | 43.1936 | 7.1641 | 9.5871 | 9.1541 | 8.1541 | 11.7312 | 13.7312 | 9.5871 | 17.7412 | 29.4724 | 43.2036 | 0.01
4.933 | 8.4665 | 6.933 | 5.933 | 8.3996 | 10.3996 | 8.4665 | 14.3996 | 22.7991 | 33.1987 | 4.943 | 8.4765 | 6.933 | 5.933 | 8.3996 | 10.3996 | 8.4765 | 14.4096 | 22.8091 | 33.2087 | 0.01
4.1916 | 8.0958 | 6.1916 | 5.1916 | 7.2874 | 9.2874 | 8.0958 | 13.2874 | 20.5748 | 29.8621 | 4.2016 | 8.1058 | 6.1916 | 5.1916 | 7.2874 | 9.2874 | 8.1058 | 13.2974 | 20.5848 | 29.8721 | 0.01
7.147 | 9.5735 | 9.147 | 8.147 | 11.7205 | 13.7205 | 9.5735 | 17.7205 | 29.4411 | 43.1616 | 7.157 | 9.5835 | 9.147 | 8.147 | 11.7205 | 13.7205 | 9.5835 | 17.7305 | 29.4511 | 43.1716 | 0.01
3.5581 | 7.7791 | 5.5581 | 4.5581 | 6.3372 | 8.3372 | 7.7791 | 12.3372 | 18.6744 | 27.0116 | 3.5681 | 7.7891 | 5.5581 | 4.5581 | 6.3372 | 8.3372 | 7.7891 | 12.3472 | 18.6844 | 27.0216 | 0.01
6.1262 | 9.0631 | 8.1262 | 7.1262 | 10.1893 | 12.1893 | 9.0631 | 16.1893 | 26.3785 | 38.5678 | 6.1362 | 9.0731 | 8.1262 | 7.1262 | 10.1893 | 12.1893 | 9.0731 | 16.1993 | 26.3885 | 38.5778 | 0.01
4.3383 | 8.1692 | 6.3383 | 5.3383 | 7.5075 | 9.5075 | 8.1692 | 13.5075 | 21.0149 | 30.5224 | 4.3483 | 8.1792 | 6.3383 | 5.3383 | 7.5075 | 9.5075 | 8.1792 | 13.5175 | 21.0249 | 30.5324 | 0.01
5.0357 | 8.5178 | 7.0357 | 6.0357 | 8.5535 | 10.5535 | 8.5178 | 14.5535 | 23.1071 | 33.6606 | 5.0457 | 8.5278 | 7.0357 | 6.0357 | 8.5535 | 10.5535 | 8.5278 | 14.5635 | 23.1171 | 33.6706 | 0.01
6.8694 | 9.4347 | 8.8694 | 7.8694 | 11.3041 | 13.3041 | 9.4347 | 17.3041 | 28.6083 | 41.9124 | 6.8794 | 9.4447 | 8.8694 | 7.8694 | 11.3041 | 13.3041 | 9.4447 | 17.3141 | 28.6183 | 41.9224 | 0.01
1.534 | 6.767 | 3.534 | 2.534 | 3.301 | 5.301 | 6.767 | 9.301 | 12.6021 | 17.9031 | 1.544 | 6.777 | 3.534 | 2.534 | 3.301 | 5.301 | 6.777 | 9.311 | 12.6121 | 17.9131 | 0.01
7.0464 | 9.5232 | 9.0464 | 8.0464 | 11.5695 | 13.5695 | 9.5232 | 17.5695 | 29.1391 | 42.7086 | 7.0564 | 9.5332 | 9.0464 | 8.0464 | 11.5695 | 13.5695 | 9.5332 | 17.5795 | 29.1491 | 42.7186 | 0.01
7.3728 | 9.6864 | 9.3728 | 8.3728 | 12.0592 | 14.0592 | 9.6864 | 18.0592 | 30.1185 | 44.1777 | 7.3828 | 9.6964 | 9.3728 | 8.3728 | 12.0592 | 14.0592 | 9.6964 | 18.0692 | 30.1285 | 44.1877 | 0.01
6.9632 | 9.4816 | 8.9632 | 7.9632 | 11.4448 | 13.4448 | 9.4816 | 17.4448 | 28.8895 | 42.3343 | 6.9732 | 9.4916 | 8.9632 | 7.9632 | 11.4448 | 13.4448 | 9.4916 | 17.4548 | 28.8995 | 42.3443 | 0.01
10.0391 | 11.0196 | 12.0391 | 11.0391 | 16.0587 | 18.0587 | 11.0196 | 22.0587 | 38.1174 | 56.176 | 10.0491 | 11.0296 | 12.0391 | 11.0391 | 16.0587 | 18.0587 | 11.0296 | 22.0687 | 38.1274 | 56.186 | 0.01
2.6093 | 7.3047 | 4.6093 | 3.6093 | 4.914 | 6.914 | 7.3047 | 10.914 | 15.828 | 22.742 | 2.6193 | 7.3147 | 4.6093 | 3.6093 | 4.914 | 6.914 | 7.3147 | 10.924 | 15.838 | 22.752 | 0.01
5.5955 | 8.7978 | 7.5955 | 6.5955 | 9.3933 | 11.3933 | 8.7978 | 15.3933 | 24.7866 | 36.1798 | 5.6055 | 8.8078 | 7.5955 | 6.5955 | 9.3933 | 11.3933 | 8.8078 | 15.4033 | 24.7966 | 36.1898 | 0.01
6.8506 | 9.4253 | 8.8506 | 7.8506 | 11.2759 | 13.2759 | 9.4253 | 17.2759 | 28.5519 | 41.8278 | 6.8606 | 9.4353 | 8.8506 | 7.8506 | 11.2759 | 13.2759 | 9.4353 | 17.2859 | 28.5619 | 41.8378 | 0.01
6.2706 | 9.1353 | 8.2706 | 7.2706 | 10.4059 | 12.4059 | 9.1353 | 16.4059 | 26.8119 | 39.2178 | 6.2806 | 9.1453 | 8.2706 | 7.2706 | 10.4059 | 12.4059 | 9.1453 | 16.4159 | 26.8219 | 39.2278 | 0.01
1.3749 | 6.6874 | 3.3749 | 2.3749 | 3.0623 | 5.0623 | 6.6874 | 9.0623 | 12.1246 | 17.1869 | 1.3849 | 6.6974 | 3.3749 | 2.3749 | 3.0623 | 5.0623 | 6.6974 | 9.0723 | 12.1346 | 17.1969 | 0.01
5.1584 | 8.5792 | 7.1584 | 6.1584 | 8.7376 | 10.7376 | 8.5792 | 14.7376 | 23.4751 | 34.2127 | 5.1684 | 8.5892 | 7.1584 | 6.1584 | 8.7376 | 10.7376 | 8.5892 | 14.7476 | 23.4851 | 34.2227 | 0.01
2.6899 | 7.345 | 4.6899 | 3.6899 | 5.0349 | 7.0349 | 7.345 | 11.0349 | 16.0697 | 23.1046 | 2.6999 | 7.355 | 4.6899 | 3.6899 | 5.0349 | 7.0349 | 7.355 | 11.0449 | 16.0797 | 23.1146 | 0.01
7.8723 | 9.9362 | 9.8723 | 8.8723 | 12.8085 | 14.8085 | 9.9362 | 18.8085 | 31.6169 | 46.4254 | 7.8823 | 9.9462 | 9.8723 | 8.8723 | 12.8085 | 14.8085 | 9.9462 | 18.8185 | 31.6269 | 46.4354 | 0.01
6.2022 | 9.1011 | 8.2022 | 7.2022 | 10.3034 | 12.3034 | 9.1011 | 16.3034 | 26.6067 | 38.9101 | 6.2122 | 9.1111 | 8.2022 | 7.2022 | 10.3034 | 12.3034 | 9.1111 | 16.3134 | 26.6167 | 38.9201 | 0.01
5.2262 | 8.6131 | 7.2262 | 6.2262 | 8.8394 | 10.8394 | 8.6131 | 14.8394 | 23.6787 | 34.5181 | 5.2362 | 8.6231 | 7.2262 | 6.2262 | 8.8394 | 10.8394 | 8.6231 | 14.8494 | 23.6887 | 34.5281 | 0.01
7.3341 | 9.667 | 9.3341 | 8.3341 | 12.0011 | 14.0011 | 9.667 | 18.0011 | 30.0022 | 44.0033 | 7.3441 | 9.677 | 9.3341 | 8.3341 | 12.0011 | 14.0011 | 9.677 | 18.0111 | 30.0122 | 44.0133 | 0.01
4.9525 | 8.4763 | 6.9525 | 5.9525 | 8.4288 | 10.4288 | 8.4763 | 14.4288 | 22.8576 | 33.2864 | 4.9625 | 8.4863 | 6.9525 | 5.9525 | 8.4288 | 10.4288 | 8.4863 | 14.4388 | 22.8676 | 33.2964 | 0.01
2.0881 | 7.0441 | 4.0881 | 3.0881 | 4.1322 | 6.1322 | 7.0441 | 10.1322 | 14.2644 | 20.3966 | 2.0981 | 7.0541 | 4.0881 | 3.0881 | 4.1322 | 6.1322 | 7.0541 | 10.1422 | 14.2744 | 20.4066 | 0.01
3.9195 | 7.9597 | 5.9195 | 4.9195 | 6.8792 | 8.8792 | 7.9597 | 12.8792 | 19.7585 | 28.6377 | 3.9295 | 7.9697 | 5.9195 | 4.9195 | 6.8792 | 8.8792 | 7.9697 | 12.8892 | 19.7685 | 28.6477 | 0.01
3.6272 | 7.8136 | 5.6272 | 4.6272 | 6.4408 | 8.4408 | 7.8136 | 12.4408 | 18.8816 | 27.3224 | 3.6372 | 7.8236 | 5.6272 | 4.6272 | 6.4408 | 8.4408 | 7.8236 | 12.4508 | 18.8916 | 27.3324 | 0.01
7.2947 | 9.6474 | 9.2947 | 8.2947 | 11.9421 | 13.9421 | 9.6474 | 17.9421 | 29.8841 | 43.8262 | 7.3047 | 9.6574 | 9.2947 | 8.2947 | 11.9421 | 13.9421 | 9.6574 | 17.9521 | 29.8941 | 43.8362 | 0.01
2.1455 | 7.0728 | 4.1455 | 3.1455 | 4.2183 | 6.2183 | 7.0728 | 10.2183 | 14.4366 | 20.6549 | 2.1555 | 7.0828 | 4.1455 | 3.1455 | 4.2183 | 6.2183 | 7.0828 | 10.2283 | 14.4466 | 20.6649 | 0.01
5.3279 | 8.6639 | 7.3279 | 6.3279 | 8.9918 | 10.9918 | 8.6639 | 14.9918 | 23.9837 | 34.9755 | 5.3379 | 8.6739 | 7.3279 | 6.3279 | 8.9918 | 10.9918 | 8.6739 | 15.0018 | 23.9937 | 34.9855 | 0.01
9.3314 | 10.6657 | 11.3314 | 10.3314 | 14.9971 | 16.9971 | 10.6657 | 20.9971 | 35.9941 | 52.9912 | 9.3414 | 10.6757 | 11.3314 | 10.3314 | 14.9971 | 16.9971 | 10.6757 | 21.0071 | 36.0041 | 53.0012 | 0.01
3.8591 | 7.9296 | 5.8591 | 4.8591 | 6.7887 | 8.7887 | 7.9296 | 12.7887 | 19.5774 | 28.3661 | 3.8691 | 7.9396 | 5.8591 | 4.8591 | 6.7887 | 8.7887 | 7.9396 | 12.7987 | 19.5874 | 28.3761 | 0.01
3.9396 | 7.9698 | 5.9396 | 4.9396 | 6.9093 | 8.9093 | 7.9698 | 12.9093 | 19.8187 | 28.728 | 3.9496 | 7.9798 | 5.9396 | 4.9396 | 6.9093 | 8.9093 | 7.9798 | 12.9193 | 19.8287 | 28.738 | 0.01
5.9075 | 8.9538 | 7.9075 | 6.9075 | 9.8613 | 11.8613 | 8.9538 | 15.8613 | 25.7226 | 37.5839 | 5.9175 | 8.9638 | 7.9075 | 6.9075 | 9.8613 | 11.8613 | 8.9638 | 15.8713 | 25.7326 | 37.5939 | 0.01
6.4736 | 9.2368 | 8.4736 | 7.4736 | 10.7104 | 12.7104 | 9.2368 | 16.7104 | 27.4208 | 40.1312 | 6.4836 | 9.2468 | 8.4736 | 7.4736 | 10.7104 | 12.7104 | 9.2468 | 16.7204 | 27.4308 | 40.1412 | 0.01
6.1772 | 9.0886 | 8.1772 | 7.1772 | 10.2658 | 12.2658 | 9.0886 | 16.2658 | 26.5317 | 38.7975 | 6.1872 | 9.0986 | 8.1772 | 7.1772 | 10.2658 | 12.2658 | 9.0986 | 16.2758 | 26.5417 | 38.8075 | 0.01
8.3162 | 10.1581 | 10.3162 | 9.3162 | 13.4744 | 15.4744 | 10.1581 | 19.4744 | 32.9487 | 48.4231 | 8.3262 | 10.1681 | 10.3162 | 9.3162 | 13.4744 | 15.4744 | 10.1681 | 19.4844 | 32.9587 | 48.4331 | 0.01
8.4837 | 10.2419 | 10.4837 | 9.4837 | 13.7256 | 15.7256 | 10.2419 | 19.7256 | 33.4512 | 49.1768 | 8.4937 | 10.2519 | 10.4837 | 9.4837 | 13.7256 | 15.7256 | 10.2519 | 19.7356 | 33.4612 | 49.1868 | 0.01
4.6072 | 8.3036 | 6.6072 | 5.6072 | 7.9108 | 9.9108 | 8.3036 | 13.9108 | 21.8217 | 31.7325 | 4.6172 | 8.3136 | 6.6072 | 5.6072 | 7.9108 | 9.9108 | 8.3136 | 13.9208 | 21.8317 | 31.7425 | 0.01
6.9466 | 9.4733 | 8.9466 | 7.9466 | 11.4199 | 13.4199 | 9.4733 | 17.4199 | 28.8397 | 42.2596 | 6.9566 | 9.4833 | 8.9466 | 7.9466 | 11.4199 | 13.4199 | 9.4833 | 17.4299 | 28.8497 | 42.2696 | 0.01
4.9222 | 8.4611 | 6.9222 | 5.9222 | 8.3833 | 10.3833 | 8.4611 | 14.3833 | 22.7666 | 33.1498 | 4.9322 | 8.4711 | 6.9222 | 5.9222 | 8.3833 | 10.3833 | 8.4711 | 14.3933 | 22.7766 | 33.1598 | 0.01
6.7574 | 9.3787 | 8.7574 | 7.7574 | 11.1361 | 13.1361 | 9.3787 | 17.1361 | 28.2722 | 41.4082 | 6.7674 | 9.3887 | 8.7574 | 7.7574 | 11.1361 | 13.1361 | 9.3887 | 17.1461 | 28.2822 | 41.4182 | 0.01
4.633 | 8.3165 | 6.633 | 5.633 | 7.9494 | 9.9494 | 8.3165 | 13.9494 | 21.8989 | 31.8483 | 4.643 | 8.3265 | 6.633 | 5.633 | 7.9494 | 9.9494 | 8.3265 | 13.9594 | 21.9089 | 31.8583 | 0.01
6.7659 | 9.3829 | 8.7659 | 7.7659 | 11.1488 | 13.1488 | 9.3829 | 17.1488 | 28.2977 | 41.4465 | 6.7759 | 9.3929 | 8.7659 | 7.7659 | 11.1488 | 13.1488 | 9.3929 | 17.1588 | 28.3077 | 41.4565 | 0.01
7.5034 | 9.7517 | 9.5034 | 8.5034 | 12.2551 | 14.2551 | 9.7517 | 18.2551 | 30.5101 | 44.7652 | 7.5134 | 9.7617 | 9.5034 | 8.5034 | 12.2551 | 14.2551 | 9.7617 | 18.2651 | 30.5201 | 44.7752 | 0.01
6.5977 | 9.2989 | 8.5977 | 7.5977 | 10.8966 | 12.8966 | 9.2989 | 16.8966 | 27.7932 | 40.6898 | 6.6077 | 9.3089 | 8.5977 | 7.5977 | 10.8966 | 12.8966 | 9.3089 | 16.9066 | 27.8032 | 40.6998 | 0.01
10.4265 | 11.2133 | 12.4265 | 11.4265 | 16.6398 | 18.6398 | 11.2133 | 22.6398 | 39.2796 | 57.9195 | 10.4365 | 11.2233 | 12.4265 | 11.4265 | 16.6398 | 18.6398 | 11.2233 | 22.6498 | 39.2896 | 57.9295 | 0.01
3.714 | 7.857 | 5.714 | 4.714 | 6.571 | 8.571 | 7.857 | 12.571 | 19.1421 | 27.7131 | 3.724 | 7.867 | 5.714 | 4.714 | 6.571 | 8.571 | 7.867 | 12.581 | 19.1521 | 27.7231 | 0.01
5.7873 | 8.8936 | 7.7873 | 6.7873 | 9.6809 | 11.6809 | 8.8936 | 15.6809 | 25.3618 | 37.0428 | 5.7973 | 8.9036 | 7.7873 | 6.7873 | 9.6809 | 11.6809 | 8.9036 | 15.6909 | 25.3718 | 37.0528 | 0.01
7.0859 | 9.543 | 9.0859 | 8.0859 | 11.6289 | 13.6289 | 9.543 | 17.6289 | 29.2577 | 42.8866 | 7.0959 | 9.553 | 9.0859 | 8.0859 | 11.6289 | 13.6289 | 9.553 | 17.6389 | 29.2677 | 42.8966 | 0.01
7.4262 | 9.7131 | 9.4262 | 8.4262 | 12.1394 | 14.1394 | 9.7131 | 18.1394 | 30.2787 | 44.4181 | 7.4362 | 9.7231 | 9.4262 | 8.4262 | 12.1394 | 14.1394 | 9.7231 | 18.1494 | 30.2887 | 44.4281 | 0.01
8.0811 | 10.0406 | 10.0811 | 9.0811 | 13.1217 | 15.1217 | 10.0406 | 19.1217 | 32.2433 | 47.365 | 8.0911 | 10.0506 | 10.0811 | 9.0811 | 13.1217 | 15.1217 | 10.0506 | 19.1317 | 32.2533 | 47.375 | 0.01
3.1327 | 7.5663 | 5.1327 | 4.1327 | 5.699 | 7.699 | 7.5663 | 11.699 | 17.398 | 25.0971 | 3.1427 | 7.5763 | 5.1327 | 4.1327 | 5.699 | 7.699 | 7.5763 | 11.709 | 17.408 | 25.1071 | 0.01
6.3051 | 9.1525 | 8.3051 | 7.3051 | 10.4576 | 12.4576 | 9.1525 | 16.4576 | 26.9152 | 39.3728 | 6.3151 | 9.1625 | 8.3051 | 7.3051 | 10.4576 | 12.4576 | 9.1625 | 16.4676 | 26.9252 | 39.3828 | 0.01
5.055 | 8.5275 | 7.055 | 6.055 | 8.5826 | 10.5826 | 8.5275 | 14.5826 | 23.1651 | 33.7477 | 5.065 | 8.5375 | 7.055 | 6.055 | 8.5826 | 10.5826 | 8.5375 | 14.5926 | 23.1751 | 33.7577 | 0.01
6.1435 | 9.0718 | 8.1435 | 7.1435 | 10.2153 | 12.2153 | 9.0718 | 16.2153 | 26.4306 | 38.6459 | 6.1535 | 9.0818 | 8.1435 | 7.1435 | 10.2153 | 12.2153 | 9.0818 | 16.2253 | 26.4406 | 38.6559 | 0.01
4.6397 | 8.3198 | 6.6397 | 5.6397 | 7.9595 | 9.9595 | 8.3198 | 13.9595 | 21.919 | 31.8784 | 4.6497 | 8.3298 | 6.6397 | 5.6397 | 7.9595 | 9.9595 | 8.3298 | 13.9695 | 21.929 | 31.8884 | 0.01
5.7358 | 8.8679 | 7.7358 | 6.7358 | 9.6037 | 11.6037 | 8.8679 | 15.6037 | 25.2075 | 36.8112 | 5.7458 | 8.8779 | 7.7358 | 6.7358 | 9.6037 | 11.6037 | 8.8779 | 15.6137 | 25.2175 | 36.8212 | 0.01
5.6716 | 8.8358 | 7.6716 | 6.6716 | 9.5074 | 11.5074 | 8.8358 | 15.5074 | 25.0148 | 36.5222 | 5.6816 | 8.8458 | 7.6716 | 6.6716 | 9.5074 | 11.5074 | 8.8458 | 15.5174 | 25.0248 | 36.5322 | 0.01
5.8039 | 8.902 | 7.8039 | 6.8039 | 9.7059 | 11.7059 | 8.902 | 15.7059 | 25.4118 | 37.1176 | 5.8139 | 8.912 | 7.8039 | 6.8039 | 9.7059 | 11.7059 | 8.912 | 15.7159 | 25.4218 | 37.1276 | 0.01
4.2001 | 8.1001 | 6.2001 | 5.2001 | 7.3002 | 9.3002 | 8.1001 | 13.3002 | 20.6003 | 29.9005 | 4.2101 | 8.1101 | 6.2001 | 5.2001 | 7.3002 | 9.3002 | 8.1101 | 13.3102 | 20.6103 | 29.9105 | 0.01
7.2835 | 9.6418 | 9.2835 | 8.2835 | 11.9253 | 13.9253 | 9.6418 | 17.9253 | 29.8505 | 43.7758 | 7.2935 | 9.6518 | 9.2835 | 8.2835 | 11.9253 | 13.9253 | 9.6518 | 17.9353 | 29.8605 | 43.7858 | 0.01
5.9561 | 8.978 | 7.9561 | 6.9561 | 9.9341 | 11.9341 | 8.978 | 15.9341 | 25.8682 | 37.8023 | 5.9661 | 8.988 | 7.9561 | 6.9561 | 9.9341 | 11.9341 | 8.988 | 15.9441 | 25.8782 | 37.8123 | 0.01
4.4582 | 8.2291 | 6.4582 | 5.4582 | 7.6873 | 9.6873 | 8.2291 | 13.6873 | 21.3746 | 31.0619 | 4.4682 | 8.2391 | 6.4582 | 5.4582 | 7.6873 | 9.6873 | 8.2391 | 13.6973 | 21.3846 | 31.0719 | 0.01
9.4554 | 10.7277 | 11.4554 | 10.4554 | 15.1831 | 17.1831 | 10.7277 | 21.1831 | 36.3663 | 53.5494 | 9.4654 | 10.7377 | 11.4554 | 10.4554 | 15.1831 | 17.1831 | 10.7377 | 21.1931 | 36.3763 | 53.5594 | 0.01
7.4928 | 9.7464 | 9.4928 | 8.4928 | 12.2393 | 14.2393 | 9.7464 | 18.2393 | 30.4785 | 44.7178 | 7.5028 | 9.7564 | 9.4928 | 8.4928 | 12.2393 | 14.2393 | 9.7564 | 18.2493 | 30.4885 | 44.7278 | 0.01
8.881 | 10.4405 | 10.881 | 9.881 | 14.3215 | 16.3215 | 10.4405 | 20.3215 | 34.6431 | 50.9646 | 8.891 | 10.4505 | 10.881 | 9.881 | 14.3215 | 16.3215 | 10.4505 | 20.3315 | 34.6531 | 50.9746 | 0.01
7.7568 | 9.8784 | 9.7568 | 8.7568 | 12.6353 | 14.6353 | 9.8784 | 18.6353 | 31.2705 | 45.9058 | 7.7668 | 9.8884 | 9.7568 | 8.7568 | 12.6353 | 14.6353 | 9.8884 | 18.6453 | 31.2805 | 45.9158 | 0.01
2.9043 | 7.4522 | 4.9043 | 3.9043 | 5.3565 | 7.3565 | 7.4522 | 11.3565 | 16.7129 | 24.0694 | 2.9143 | 7.4622 | 4.9043 | 3.9043 | 5.3565 | 7.3565 | 7.4622 | 11.3665 | 16.7229 | 24.0794 | 0.01
5.3388 | 8.6694 | 7.3388 | 6.3388 | 9.0081 | 11.0081 | 8.6694 | 15.0081 | 24.0163 | 35.0244 | 5.3488 | 8.6794 | 7.3388 | 6.3388 | 9.0081 | 11.0081 | 8.6794 | 15.0181 | 24.0263 | 35.0344 | 0.01
5.5621 | 8.7811 | 7.5621 | 6.5621 | 9.3432 | 11.3432 | 8.7811 | 15.3432 | 24.6864 | 36.0296 | 5.5721 | 8.7911 | 7.5621 | 6.5621 | 9.3432 | 11.3432 | 8.7911 | 15.3532 | 24.6964 | 36.0396 | 0.01
4.4878 | 8.2439 | 6.4878 | 5.4878 | 7.7317 | 9.7317 | 8.2439 | 13.7317 | 21.4634 | 31.1951 | 4.4978 | 8.2539 | 6.4878 | 5.4878 | 7.7317 | 9.7317 | 8.2539 | 13.7417 | 21.4734 | 31.2051 | 0.01
3.7421 | 7.8711 | 5.7421 | 4.7421 | 6.6132 | 8.6132 | 7.8711 | 12.6132 | 19.2263 | 27.8395 | 3.7521 | 7.8811 | 5.7421 | 4.7421 | 6.6132 | 8.6132 | 7.8811 | 12.6232 | 19.2363 | 27.8495 | 0.01
7.9302 | 9.9651 | 9.9302 | 8.9302 | 12.8953 | 14.8953 | 9.9651 | 18.8953 | 31.7905 | 46.6858 | 7.9402 | 9.9751 | 9.9302 | 8.9302 | 12.8953 | 14.8953 | 9.9751 | 18.9053 | 31.8005 | 46.6958 | 0.01
1.6191 | 6.8096 | 3.6191 | 2.6191 | 3.4287 | 5.4287 | 6.8096 | 9.4287 | 12.8574 | 18.2862 | 1.6291 | 6.8196 | 3.6191 | 2.6191 | 3.4287 | 5.4287 | 6.8196 | 9.4387 | 12.8674 | 18.2962 | 0.01
5.7064 | 8.8532 | 7.7064 | 6.7064 | 9.5596 | 11.5596 | 8.8532 | 15.5596 | 25.1192 | 36.6788 | 5.7164 | 8.8632 | 7.7064 | 6.7064 | 9.5596 | 11.5596 | 8.8632 | 15.5696 | 25.1292 | 36.6888 | 0.01
7.4495 | 9.7247 | 9.4495 | 8.4495 | 12.1742 | 14.1742 | 9.7247 | 18.1742 | 30.3484 | 44.5225 | 7.4595 | 9.7347 | 9.4495 | 8.4495 | 12.1742 | 14.1742 | 9.7347 | 18.1842 | 30.3584 | 44.5325 | 0.01
9.2742 | 10.6371 | 11.2742 | 10.2742 | 14.9113 | 16.9113 | 10.6371 | 20.9113 | 35.8226 | 52.7339 | 9.2842 | 10.6471 | 11.2742 | 10.2742 | 14.9113 | 16.9113 | 10.6471 | 20.9213 | 35.8326 | 52.7439 | 0.01
3.6679 | 7.8339 | 5.6679 | 4.6679 | 6.5018 | 8.5018 | 7.8339 | 12.5018 | 19.0036 | 27.5054 | 3.6779 | 7.8439 | 5.6679 | 4.6679 | 6.5018 | 8.5018 | 7.8439 | 12.5118 | 19.0136 | 27.5154 | 0.01
0.79769 | 6.3988 | 2.7977 | 1.7977 | 2.1965 | 4.1965 | 6.3988 | 8.1965 | 10.3931 | 14.5896 | 0.80769 | 6.4088 | 2.7977 | 1.7977 | 2.1965 | 4.1965 | 6.4088 | 8.2065 | 10.4031 | 14.5996 | 0.01
3.1848 | 7.5924 | 5.1848 | 4.1848 | 5.7772 | 7.7772 | 7.5924 | 11.7772 | 17.5544 | 25.3316 | 3.1948 | 7.6024 | 5.1848 | 4.1848 | 5.7772 | 7.7772 | 7.6024 | 11.7872 | 17.5644 | 25.3416 | 0.01
4.6142 | 8.3071 | 6.6142 | 5.6142 | 7.9214 | 9.9214 | 8.3071 | 13.9214 | 21.8427 | 31.7641 | 4.6242 | 8.3171 | 6.6142 | 5.6142 | 7.9214 | 9.9214 | 8.3171 | 13.9314 | 21.8527 | 31.7741 | 0.01
3.8428 | 7.9214 | 5.8428 | 4.8428 | 6.7641 | 8.7641 | 7.9214 | 12.7641 | 19.5283 | 28.2924 | 3.8528 | 7.9314 | 5.8428 | 4.8428 | 6.7641 | 8.7641 | 7.9314 | 12.7741 | 19.5383 | 28.3024 | 0.01
5.1024 | 8.5512 | 7.1024 | 6.1024 | 8.6535 | 10.6535 | 8.5512 | 14.6535 | 23.3071 | 33.9606 | 5.1124 | 8.5612 | 7.1024 | 6.1024 | 8.6535 | 10.6535 | 8.5612 | 14.6635 | 23.3171 | 33.9706 | 0.01
4.4655 | 8.2327 | 6.4655 | 5.4655 | 7.6982 | 9.6982 | 8.2327 | 13.6982 | 21.3965 | 31.0947 | 4.4755 | 8.2427 | 6.4655 | 5.4655 | 7.6982 | 9.6982 | 8.2427 | 13.7082 | 21.4065 | 31.1047 | 0.01
4.0289 | 8.0145 | 6.0289 | 5.0289 | 7.0434 | 9.0434 | 8.0145 | 13.0434 | 20.0867 | 29.1301 | 4.0389 | 8.0245 | 6.0289 | 5.0289 | 7.0434 | 9.0434 | 8.0245 | 13.0534 | 20.0967 | 29.1401 | 0.01
7.1646 | 9.5823 | 9.1646 | 8.1646 | 11.7469 | 13.7469 | 9.5823 | 17.7469 | 29.4938 | 43.2407 | 7.1746 | 9.5923 | 9.1646 | 8.1646 | 11.7469 | 13.7469 | 9.5923 | 17.7569 | 29.5038 | 43.2507 | 0.01
9.2783 | 10.6391 | 11.2783 | 10.2783 | 14.9174 | 16.9174 | 10.6391 | 20.9174 | 35.8348 | 52.7522 | 9.2883 | 10.6491 | 11.2783 | 10.2783 | 14.9174 | 16.9174 | 10.6491 | 20.9274 | 35.8448 | 52.7622 | 0.01
6.9702 | 9.4851 | 8.9702 | 7.9702 | 11.4553 | 13.4553 | 9.4851 | 17.4553 | 28.9106 | 42.3659 | 6.9802 | 9.4951 | 8.9702 | 7.9702 | 11.4553 | 13.4553 | 9.4951 | 17.4653 | 28.9206 | 42.3759 | 0.01
8.7728 | 10.3864 | 10.7728 | 9.7728 | 14.1592 | 16.1592 | 10.3864 | 20.1592 | 34.3184 | 50.4777 | 8.7828 | 10.3964 | 10.7728 | 9.7728 | 14.1592 | 16.1592 | 10.3964 | 20.1692 | 34.3284 | 50.4877 | 0.01
4.2408 | 8.1204 | 6.2408 | 5.2408 | 7.3612 | 9.3612 | 8.1204 | 13.3612 | 20.7224 | 30.0836 | 4.2508 | 8.1304 | 6.2408 | 5.2408 | 7.3612 | 9.3612 | 8.1304 | 13.3712 | 20.7324 | 30.0936 | 0.01
6.3376 | 9.1688 | 8.3376 | 7.3376 | 10.5064 | 12.5064 | 9.1688 | 16.5064 | 27.0128 | 39.5192 | 6.3476 | 9.1788 | 8.3376 | 7.3376 | 10.5064 | 12.5064 | 9.1788 | 16.5164 | 27.0228 | 39.5292 | 0.01
10.4613 | 11.2307 | 12.4613 | 11.4613 | 16.692 | 18.692 | 11.2307 | 22.692 | 39.384 | 58.076 | 10.4713 | 11.2407 | 12.4613 | 11.4613 | 16.692 | 18.692 | 11.2407 | 22.702 | 39.394 | 58.086 | 0.01
0.66258 | 6.3313 | 2.6626 | 1.6626 | 1.9939 | 3.9939 | 6.3313 | 7.9939 | 9.9877 | 13.9816 | 0.67258 | 6.3413 | 2.6626 | 1.6626 | 1.9939 | 3.9939 | 6.3413 | 8.0039 | 9.9977 | 13.9916 | 0.01
10.4087 | 11.2044 | 12.4087 | 11.4087 | 16.6131 | 18.6131 | 11.2044 | 22.6131 | 39.2262 | 57.8392 | 10.4187 | 11.2144 | 12.4087 | 11.4087 | 16.6131 | 18.6131 | 11.2144 | 22.6231 | 39.2362 | 57.8492 | 0.01
8.7381 | 10.369 | 10.7381 | 9.7381 | 14.1071 | 16.1071 | 10.369 | 20.1071 | 34.2142 | 50.3212 | 8.7481 | 10.379 | 10.7381 | 9.7381 | 14.1071 | 16.1071 | 10.379 | 20.1171 | 34.2242 | 50.3312 | 0.01
3.1683 | 7.5841 | 5.1683 | 4.1683 | 5.7524 | 7.7524 | 7.5841 | 11.7524 | 17.5048 | 25.2573 | 3.1783 | 7.5941 | 5.1683 | 4.1683 | 5.7524 | 7.7524 | 7.5941 | 11.7624 | 17.5148 | 25.2673 | 0.01
7.7445 | 9.8723 | 9.7445 | 8.7445 | 12.6168 | 14.6168 | 9.8723 | 18.6168 | 31.2336 | 45.8504 | 7.7545 | 9.8823 | 9.7445 | 8.7445 | 12.6168 | 14.6168 | 9.8823 | 18.6268 | 31.2436 | 45.8604 | 0.01
9.3878 | 10.6939 | 11.3878 | 10.3878 | 15.0817 | 17.0817 | 10.6939 | 21.0817 | 36.1635 | 53.2452 | 9.3978 | 10.7039 | 11.3878 | 10.3878 | 15.0817 | 17.0817 | 10.7039 | 21.0917 | 36.1735 | 53.2552 | 0.01
5.023 | 8.5115 | 7.023 | 6.023 | 8.5345 | 10.5345 | 8.5115 | 14.5345 | 23.0691 | 33.6036 | 5.033 | 8.5215 | 7.023 | 6.023 | 8.5345 | 10.5345 | 8.5215 | 14.5445 | 23.0791 | 33.6136 | 0.01
8.4739 | 10.2369 | 10.4739 | 9.4739 | 13.7108 | 15.7108 | 10.2369 | 19.7108 | 33.4216 | 49.1324 | 8.4839 | 10.2469 | 10.4739 | 9.4739 | 13.7108 | 15.7108 | 10.2469 | 19.7208 | 33.4316 | 49.1424 | 0.01
8.7597 | 10.3798 | 10.7597 | 9.7597 | 14.1395 | 16.1395 | 10.3798 | 20.1395 | 34.2791 | 50.4186 | 8.7697 | 10.3898 | 10.7597 | 9.7597 | 14.1395 | 16.1395 | 10.3898 | 20.1495 | 34.2891 | 50.4286 | 0.01
4.8751 | 8.4376 | 6.8751 | 5.8751 | 8.3127 | 10.3127 | 8.4376 | 14.3127 | 22.6253 | 32.938 | 4.8851 | 8.4476 | 6.8751 | 5.8751 | 8.3127 | 10.3127 | 8.4476 | 14.3227 | 22.6353 | 32.948 | 0.01
1.4437 | 6.7218 | 3.4437 | 2.4437 | 3.1655 | 5.1655 | 6.7218 | 9.1655 | 12.3311 | 17.4966 | 1.4537 | 6.7318 | 3.4437 | 2.4437 | 3.1655 | 5.1655 | 6.7318 | 9.1755 | 12.3411 | 17.5066 | 0.01
8.6329 | 10.3164 | 10.6329 | 9.6329 | 13.9493 | 15.9493 | 10.3164 | 19.9493 | 33.8987 | 49.848 | 8.6429 | 10.3264 | 10.6329 | 9.6329 | 13.9493 | 15.9493 | 10.3264 | 19.9593 | 33.9087 | 49.858 | 0.01
9.0754 | 10.5377 | 11.0754 | 10.0754 | 14.6132 | 16.6132 | 10.5377 | 20.6132 | 35.2263 | 51.8395 | 9.0854 | 10.5477 | 11.0754 | 10.0754 | 14.6132 | 16.6132 | 10.5477 | 20.6232 | 35.2363 | 51.8495 | 0.01
10.3567 | 11.1783 | 12.3567 | 11.3567 | 16.535 | 18.535 | 11.1783 | 22.535 | 39.0701 | 57.6051 | 10.3667 | 11.1883 | 12.3567 | 11.3567 | 16.535 | 18.535 | 11.1883 | 22.545 | 39.0801 | 57.6151 | 0.01
3.4698 | 7.7349 | 5.4698 | 4.4698 | 6.2046 | 8.2046 | 7.7349 | 12.2046 | 18.4093 | 26.6139 | 3.4798 | 7.7449 | 5.4698 | 4.4698 | 6.2046 | 8.2046 | 7.7449 | 12.2146 | 18.4193 | 26.6239 | 0.01
6.9334 | 9.4667 | 8.9334 | 7.9334 | 11.4 | 13.4 | 9.4667 | 17.4 | 28.8001 | 42.2001 | 6.9434 | 9.4767 | 8.9334 | 7.9334 | 11.4 | 13.4 | 9.4767 | 17.41 | 28.8101 | 42.2101 | 0.01
6.7322 | 9.3661 | 8.7322 | 7.7322 | 11.0983 | 13.0983 | 9.3661 | 17.0983 | 28.1966 | 41.2949 | 6.7422 | 9.3761 | 8.7322 | 7.7322 | 11.0983 | 13.0983 | 9.3761 | 17.1083 | 28.2066 | 41.3049 | 0.01
5.8459 | 8.9229 | 7.8459 | 6.8459 | 9.7688 | 11.7688 | 8.9229 | 15.7688 | 25.5376 | 37.3064 | 5.8559 | 8.9329 | 7.8459 | 6.8459 | 9.7688 | 11.7688 | 8.9329 | 15.7788 | 25.5476 | 37.3164 | 0.01
4.7205 | 8.3602 | 6.7205 | 5.7205 | 8.0807 | 10.0807 | 8.3602 | 14.0807 | 22.1614 | 32.242 | 4.7305 | 8.3702 | 6.7205 | 5.7205 | 8.0807 | 10.0807 | 8.3702 | 14.0907 | 22.1714 | 32.252 | 0.01
4.978 | 8.489 | 6.978 | 5.978 | 8.4671 | 10.4671 | 8.489 | 14.4671 | 22.9341 | 33.4012 | 4.988 | 8.499 | 6.978 | 5.978 | 8.4671 | 10.4671 | 8.499 | 14.4771 | 22.9441 | 33.4112 | 0.01
7.8245 | 9.9122 | 9.8245 | 8.8245 | 12.7367 | 14.7367 | 9.9122 | 18.7367 | 31.4734 | 46.2102 | 7.8345 | 9.9222 | 9.8245 | 8.8245 | 12.7367 | 14.7367 | 9.9222 | 18.7467 | 31.4834 | 46.2202 | 0.01
9.0442 | 10.5221 | 11.0442 | 10.0442 | 14.5664 | 16.5664 | 10.5221 | 20.5664 | 35.1327 | 51.6991 | 9.0542 | 10.5321 | 11.0442 | 10.0442 | 14.5664 | 16.5664 | 10.5321 | 20.5764 | 35.1427 | 51.7091 | 0.01
6.103 | 9.0515 | 8.103 | 7.103 | 10.1545 | 12.1545 | 9.0515 | 16.1545 | 26.309 | 38.4635 | 6.113 | 9.0615 | 8.103 | 7.103 | 10.1545 | 12.1545 | 9.0615 | 16.1645 | 26.319 | 38.4735 | 0.01
6.7836 | 9.3918 | 8.7836 | 7.7836 | 11.1754 | 13.1754 | 9.3918 | 17.1754 | 28.3508 | 41.5262 | 6.7936 | 9.4018 | 8.7836 | 7.7836 | 11.1754 | 13.1754 | 9.4018 | 17.1854 | 28.3608 | 41.5362 | 0.01
7.9996 | 9.9998 | 9.9996 | 8.9996 | 12.9994 | 14.9994 | 9.9998 | 18.9994 | 31.9988 | 46.9981 | 8.0096 | 10.0098 | 9.9996 | 8.9996 | 12.9994 | 14.9994 | 10.0098 | 19.0094 | 32.0088 | 47.0081 | 0.01
6.7548 | 9.3774 | 8.7548 | 7.7548 | 11.1323 | 13.1323 | 9.3774 | 17.1323 | 28.2645 | 41.3968 | 6.7648 | 9.3874 | 8.7548 | 7.7548 | 11.1323 | 13.1323 | 9.3874 | 17.1423 | 28.2745 | 41.4068 | 0.01
4.9916 | 8.4958 | 6.9916 | 5.9916 | 8.4874 | 10.4874 | 8.4958 | 14.4874 | 22.9748 | 33.4622 | 5.0016 | 8.5058 | 6.9916 | 5.9916 | 8.4874 | 10.4874 | 8.5058 | 14.4974 | 22.9848 | 33.4722 | 0.01
7.3393 | 9.6696 | 9.3393 | 8.3393 | 12.0089 | 14.0089 | 9.6696 | 18.0089 | 30.0178 | 44.0267 | 7.3493 | 9.6796 | 9.3393 | 8.3393 | 12.0089 | 14.0089 | 9.6796 | 18.0189 | 30.0278 | 44.0367 | 0.01
4.7254 | 8.3627 | 6.7254 | 5.7254 | 8.0881 | 10.0881 | 8.3627 | 14.0881 | 22.1761 | 32.2642 | 4.7354 | 8.3727 | 6.7254 | 5.7254 | 8.0881 | 10.0881 | 8.3727 | 14.0981 | 22.1861 | 32.2742 | 0.01
7.3984 | 9.6992 | 9.3984 | 8.3984 | 12.0976 | 14.0976 | 9.6992 | 18.0976 | 30.1953 | 44.2929 | 7.4084 | 9.7092 | 9.3984 | 8.3984 | 12.0976 | 14.0976 | 9.7092 | 18.1076 | 30.2053 | 44.3029 | 0.01
4.1227 | 8.0614 | 6.1227 | 5.1227 | 7.1841 | 9.1841 | 8.0614 | 13.1841 | 20.3681 | 29.5522 | 4.1327 | 8.0714 | 6.1227 | 5.1227 | 7.1841 | 9.1841 | 8.0714 | 13.1941 | 20.3781 | 29.5622 | 0.01
6.9476 | 9.4738 | 8.9476 | 7.9476 | 11.4214 | 13.4214 | 9.4738 | 17.4214 | 28.8428 | 42.2641 | 6.9576 | 9.4838 | 8.9476 | 7.9476 | 11.4214 | 13.4214 | 9.4838 | 17.4314 | 28.8528 | 42.2741 | 0.01
5.1213 | 8.5607 | 7.1213 | 6.1213 | 8.682 | 10.682 | 8.5607 | 14.682 | 23.3639 | 34.0459 | 5.1313 | 8.5707 | 7.1213 | 6.1213 | 8.682 | 10.682 | 8.5707 | 14.692 | 23.3739 | 34.0559 | 0.01
7.439 | 9.7195 | 9.439 | 8.439 | 12.1584 | 14.1584 | 9.7195 | 18.1584 | 30.3169 | 44.4753 | 7.449 | 9.7295 | 9.439 | 8.439 | 12.1584 | 14.1584 | 9.7295 | 18.1684 | 30.3269 | 44.4853 | 0.01
8.1499 | 10.0749 | 10.1499 | 9.1499 | 13.2248 | 15.2248 | 10.0749 | 19.2248 | 32.4496 | 47.6744 | 8.1599 | 10.0849 | 10.1499 | 9.1499 | 13.2248 | 15.2248 | 10.0849 | 19.2348 | 32.4596 | 47.6844 | 0.01
7.6971 | 9.8485 | 9.6971 | 8.6971 | 12.5456 | 14.5456 | 9.8485 | 18.5456 | 31.0913 | 45.6369 | 7.7071 | 9.8585 | 9.6971 | 8.6971 | 12.5456 | 14.5456 | 9.8585 | 18.5556 | 31.1013 | 45.6469 | 0.01
3.3984 | 7.6992 | 5.3984 | 4.3984 | 6.0976 | 8.0976 | 7.6992 | 12.0976 | 18.1951 | 26.2927 | 3.4084 | 7.7092 | 5.3984 | 4.3984 | 6.0976 | 8.0976 | 7.7092 | 12.1076 | 18.2051 | 26.3027 | 0.01
6.4452 | 9.2226 | 8.4452 | 7.4452 | 10.6678 | 12.6678 | 9.2226 | 16.6678 | 27.3357 | 40.0035 | 6.4552 | 9.2326 | 8.4452 | 7.4452 | 10.6678 | 12.6678 | 9.2326 | 16.6778 | 27.3457 | 40.0135 | 0.01
8.317 | 10.1585 | 10.317 | 9.317 | 13.4754 | 15.4754 | 10.1585 | 19.4754 | 32.9509 | 48.4263 | 8.327 | 10.1685 | 10.317 | 9.317 | 13.4754 | 15.4754 | 10.1685 | 19.4854 | 32.9609 | 48.4363 | 0.01
3.6489 | 7.8244 | 5.6489 | 4.6489 | 6.4733 | 8.4733 | 7.8244 | 12.4733 | 18.9466 | 27.4198 | 3.6589 | 7.8344 | 5.6489 | 4.6489 | 6.4733 | 8.4733 | 7.8344 | 12.4833 | 18.9566 | 27.4298 | 0.01
8.2439 | 10.1219 | 10.2439 | 9.2439 | 13.3658 | 15.3658 | 10.1219 | 19.3658 | 32.7317 | 48.0975 | 8.2539 | 10.1319 | 10.2439 | 9.2439 | 13.3658 | 15.3658 | 10.1319 | 19.3758 | 32.7417 | 48.1075 | 0.01
4.5875 | 8.2937 | 6.5875 | 5.5875 | 7.8812 | 9.8812 | 8.2937 | 13.8812 | 21.7625 | 31.6437 | 4.5975 | 8.3037 | 6.5875 | 5.5875 | 7.8812 | 9.8812 | 8.3037 | 13.8912 | 21.7725 | 31.6537 | 0.01
8.8279 | 10.4139 | 10.8279 | 9.8279 | 14.2418 | 16.2418 | 10.4139 | 20.2418 | 34.4836 | 50.7253 | 8.8379 | 10.4239 | 10.8279 | 9.8279 | 14.2418 | 16.2418 | 10.4239 | 20.2518 | 34.4936 | 50.7353 | 0.01
5.636 | 8.818 | 7.636 | 6.636 | 9.454 | 11.454 | 8.818 | 15.454 | 24.908 | 36.362 | 5.646 | 8.828 | 7.636 | 6.636 | 9.454 | 11.454 | 8.828 | 15.464 | 24.918 | 36.372 | 0.01
8.4249 | 10.2124 | 10.4249 | 9.4249 | 13.6373 | 15.6373 | 10.2124 | 19.6373 | 33.2747 | 48.912 | 8.4349 | 10.2224 | 10.4249 | 9.4249 | 13.6373 | 15.6373 | 10.2224 | 19.6473 | 33.2847 | 48.922 | 0.01
5.2353 | 8.6176 | 7.2353 | 6.2353 | 8.8529 | 10.8529 | 8.6176 | 14.8529 | 23.7058 | 34.5587 | 5.2453 | 8.6276 | 7.2353 | 6.2353 | 8.8529 | 10.8529 | 8.6276 | 14.8629 | 23.7158 | 34.5687 | 0.01
8.1883 | 10.0942 | 10.1883 | 9.1883 | 13.2825 | 15.2825 | 10.0942 | 19.2825 | 32.5649 | 47.8474 | 8.1983 | 10.1042 | 10.1883 | 9.1883 | 13.2825 | 15.2825 | 10.1042 | 19.2925 | 32.5749 | 47.8574 | 0.01
5.4272 | 8.7136 | 7.4272 | 6.4272 | 9.1408 | 11.1408 | 8.7136 | 15.1408 | 24.2816 | 35.4223 | 5.4372 | 8.7236 | 7.4272 | 6.4272 | 9.1408 | 11.1408 | 8.7236 | 15.1508 | 24.2916 | 35.4323 | 0.01
3.0993 | 7.5496 | 5.0993 | 4.0993 | 5.6489 | 7.6489 | 7.5496 | 11.6489 | 17.2979 | 24.9468 | 3.1093 | 7.5596 | 5.0993 | 4.0993 | 5.6489 | 7.6489 | 7.5596 | 11.6589 | 17.3079 | 24.9568 | 0.01
9.643 | 10.8215 | 11.643 | 10.643 | 15.4644 | 17.4644 | 10.8215 | 21.4644 | 36.9289 | 54.3933 | 9.653 | 10.8315 | 11.643 | 10.643 | 15.4644 | 17.4644 | 10.8315 | 21.4744 | 36.9389 | 54.4033 | 0.01
3.1333 | 7.5666 | 5.1333 | 4.1333 | 5.6999 | 7.6999 | 7.5666 | 11.6999 | 17.3999 | 25.0998 | 3.1433 | 7.5766 | 5.1333 | 4.1333 | 5.6999 | 7.6999 | 7.5766 | 11.7099 | 17.4099 | 25.1098 | 0.01
4.86 | 8.43 | 6.86 | 5.86 | 8.2901 | 10.2901 | 8.43 | 14.2901 | 22.5801 | 32.8702 | 4.87 | 8.44 | 6.86 | 5.86 | 8.2901 | 10.2901 | 8.44 | 14.3001 | 22.5901 | 32.8802 | 0.01
1.4969 | 6.7484 | 3.4969 | 2.4969 | 3.2453 | 5.2453 | 6.7484 | 9.2453 | 12.4906 | 17.7359 | 1.5069 | 6.7584 | 3.4969 | 2.4969 | 3.2453 | 5.2453 | 6.7584 | 9.2553 | 12.5006 | 17.7459 | 0.01
6.6087 | 9.3043 | 8.6087 | 7.6087 | 10.913 | 12.913 | 9.3043 | 16.913 | 27.826 | 40.739 | 6.6187 | 9.3143 | 8.6087 | 7.6087 | 10.913 | 12.913 | 9.3143 | 16.923 | 27.836 | 40.749 | 0.01
0.19349 | 6.0967 | 2.1935 | 1.1935 | 1.2902 | 3.2902 | 6.0967 | 7.2902 | 8.5805 | 11.8707 | 0.20349 | 6.1067 | 2.1935 | 1.1935 | 1.2902 | 3.2902 | 6.1067 | 7.3002 | 8.5905 | 11.8807 | 0.01
2.3013 | 7.1507 | 4.3013 | 3.3013 | 4.452 | 6.452 | 7.1507 | 10.452 | 14.9039 | 21.3559 | 2.3113 | 7.1607 | 4.3013 | 3.3013 | 4.452 | 6.452 | 7.1607 | 10.462 | 14.9139 | 21.3659 | 0.01
4.636 | 8.318 | 6.636 | 5.636 | 7.954 | 9.954 | 8.318 | 13.954 | 21.9081 | 31.8621 | 4.646 | 8.328 | 6.636 | 5.636 | 7.954 | 9.954 | 8.328 | 13.964 | 21.9181 | 31.8721 | 0.01
7.8136 | 9.9068 | 9.8136 | 8.8136 | 12.7204 | 14.7204 | 9.9068 | 18.7204 | 31.4408 | 46.1612 | 7.8236 | 9.9168 | 9.8136 | 8.8136 | 12.7204 | 14.7204 | 9.9168 | 18.7304 | 31.4508 | 46.1712 | 0.01
7.9975 | 9.9987 | 9.9975 | 8.9975 | 12.9962 | 14.9962 | 9.9987 | 18.9962 | 31.9924 | 46.9886 | 8.0075 | 10.0087 | 9.9975 | 8.9975 | 12.9962 | 14.9962 | 10.0087 | 19.0062 | 32.0024 | 46.9986 | 0.01
5.0423 | 8.5211 | 7.0423 | 6.0423 | 8.5634 | 10.5634 | 8.5211 | 14.5634 | 23.1269 | 33.6903 | 5.0523 | 8.5311 | 7.0423 | 6.0423 | 8.5634 | 10.5634 | 8.5311 | 14.5734 | 23.1369 | 33.7003 | 0.01
5.2153 | 8.6077 | 7.2153 | 6.2153 | 8.823 | 10.823 | 8.6077 | 14.823 | 23.646 | 34.4689 | 5.2253 | 8.6177 | 7.2153 | 6.2153 | 8.823 | 10.823 | 8.6177 | 14.833 | 23.656 | 34.4789 | 0.01
7.7411 | 9.8705 | 9.7411 | 8.7411 | 12.6116 | 14.6116 | 9.8705 | 18.6116 | 31.2232 | 45.8347 | 7.7511 | 9.8805 | 9.7411 | 8.7411 | 12.6116 | 14.6116 | 9.8805 | 18.6216 | 31.2332 | 45.8447 | 0.01
9.2544 | 10.6272 | 11.2544 | 10.2544 | 14.8816 | 16.8816 | 10.6272 | 20.8816 | 35.7633 | 52.6449 | 9.2644 | 10.6372 | 11.2544 | 10.2544 | 14.8816 | 16.8816 | 10.6372 | 20.8916 | 35.7733 | 52.6549 | 0.01
6.6676 | 9.3338 | 8.6676 | 7.6676 | 11.0015 | 13.0015 | 9.3338 | 17.0015 | 28.0029 | 41.0044 | 6.6776 | 9.3438 | 8.6676 | 7.6676 | 11.0015 | 13.0015 | 9.3438 | 17.0115 | 28.0129 | 41.0144 | 0.01
8.7053 | 10.3526 | 10.7053 | 9.7053 | 14.0579 | 16.0579 | 10.3526 | 20.0579 | 34.1159 | 50.1738 | 8.7153 | 10.3626 | 10.7053 | 9.7053 | 14.0579 | 16.0579 | 10.3626 | 20.0679 | 34.1259 | 50.1838 | 0.01
6.3422 | 9.1711 | 8.3422 | 7.3422 | 10.5132 | 12.5132 | 9.1711 | 16.5132 | 27.0265 | 39.5397 | 6.3522 | 9.1811 | 8.3422 | 7.3422 | 10.5132 | 12.5132 | 9.1811 | 16.5232 | 27.0365 | 39.5497 | 0.01
2.1402 | 7.0701 | 4.1402 | 3.1402 | 4.2102 | 6.2102 | 7.0701 | 10.2102 | 14.4205 | 20.6307 | 2.1502 | 7.0801 | 4.1402 | 3.1402 | 4.2102 | 6.2102 | 7.0801 | 10.2202 | 14.4305 | 20.6407 | 0.01
6.3398 | 9.1699 | 8.3398 | 7.3398 | 10.5097 | 12.5097 | 9.1699 | 16.5097 | 27.0195 | 39.5292 | 6.3498 | 9.1799 | 8.3398 | 7.3398 | 10.5097 | 12.5097 | 9.1799 | 16.5197 | 27.0295 | 39.5392 | 0.01
4.8799 | 8.44 | 6.8799 | 5.8799 | 8.3199 | 10.3199 | 8.44 | 14.3199 | 22.6398 | 32.9597 | 4.8899 | 8.45 | 6.8799 | 5.8799 | 8.3199 | 10.3199 | 8.45 | 14.3299 | 22.6498 | 32.9697 | 0.01
7.8328 | 9.9164 | 9.8328 | 8.8328 | 12.7492 | 14.7492 | 9.9164 | 18.7492 | 31.4983 | 46.2475 | 7.8428 | 9.9264 | 9.8328 | 8.8328 | 12.7492 | 14.7492 | 9.9264 | 18.7592 | 31.5083 | 46.2575 | 0.01
4.5334 | 8.2667 | 6.5334 | 5.5334 | 7.8001 | 9.8001 | 8.2667 | 13.8001 | 21.6003 | 31.4004 | 4.5434 | 8.2767 | 6.5334 | 5.5334 | 7.8001 | 9.8001 | 8.2767 | 13.8101 | 21.6103 | 31.4104 | 0.01
1.5633 | 6.7816 | 3.5633 | 2.5633 | 3.3449 | 5.3449 | 6.7816 | 9.3449 | 12.6898 | 18.0347 | 1.5733 | 6.7916 | 3.5633 | 2.5633 | 3.3449 | 5.3449 | 6.7916 | 9.3549 | 12.6998 | 18.0447 | 0.01
9.238 | 10.619 | 11.238 | 10.238 | 14.857 | 16.857 | 10.619 | 20.857 | 35.714 | 52.571 | 9.248 | 10.629 | 11.238 | 10.238 | 14.857 | 16.857 | 10.629 | 20.867 | 35.724 | 52.581 | 0.01
8.3374 | 10.1687 | 10.3374 | 9.3374 | 13.5062 | 15.5062 | 10.1687 | 19.5062 | 33.0123 | 48.5185 | 8.3474 | 10.1787 | 10.3374 | 9.3374 | 13.5062 | 15.5062 | 10.1787 | 19.5162 | 33.0223 | 48.5285 | 0.01
1.8786 | 6.9393 | 3.8786 | 2.8786 | 3.818 | 5.818 | 6.9393 | 9.818 | 13.6359 | 19.4539 | 1.8886 | 6.9493 | 3.8786 | 2.8786 | 3.818 | 5.818 | 6.9493 | 9.828 | 13.6459 | 19.4639 | 0.01
6.2012 | 9.1006 | 8.2012 | 7.2012 | 10.3018 | 12.3018 | 9.1006 | 16.3018 | 26.6035 | 38.9053 | 6.2112 | 9.1106 | 8.2012 | 7.2012 | 10.3018 | 12.3018 | 9.1106 | 16.3118 | 26.6135 | 38.9153 | 0.01
7.7312 | 9.8656 | 9.7312 | 8.7312 | 12.5968 | 14.5968 | 9.8656 | 18.5968 | 31.1936 | 45.7904 | 7.7412 | 9.8756 | 9.7312 | 8.7312 | 12.5968 | 14.5968 | 9.8756 | 18.6068 | 31.2036 | 45.8004 | 0.01
4.7984 | 8.3992 | 6.7984 | 5.7984 | 8.1976 | 10.1976 | 8.3992 | 14.1976 | 22.3952 | 32.5929 | 4.8084 | 8.4092 | 6.7984 | 5.7984 | 8.1976 | 10.1976 | 8.4092 | 14.2076 | 22.4052 | 32.6029 | 0.01
8.9196 | 10.4598 | 10.9196 | 9.9196 | 14.3793 | 16.3793 | 10.4598 | 20.3793 | 34.7587 | 51.138 | 8.9296 | 10.4698 | 10.9196 | 9.9196 | 14.3793 | 16.3793 | 10.4698 | 20.3893 | 34.7687 | 51.148 | 0.01
9.3436 | 10.6718 | 11.3436 | 10.3436 | 15.0154 | 17.0154 | 10.6718 | 21.0154 | 36.0308 | 53.0462 | 9.3536 | 10.6818 | 11.3436 | 10.3436 | 15.0154 | 17.0154 | 10.6818 | 21.0254 | 36.0408 | 53.0562 | 0.01
5.1653 | 8.5827 | 7.1653 | 6.1653 | 8.748 | 10.748 | 8.5827 | 14.748 | 23.496 | 34.244 | 5.1753 | 8.5927 | 7.1653 | 6.1653 | 8.748 | 10.748 | 8.5927 | 14.758 | 23.506 | 34.254 | 0.01
5.6215 | 8.8107 | 7.6215 | 6.6215 | 9.4322 | 11.4322 | 8.8107 | 15.4322 | 24.8644 | 36.2965 | 5.6315 | 8.8207 | 7.6215 | 6.6215 | 9.4322 | 11.4322 | 8.8207 | 15.4422 | 24.8744 | 36.3065 | 0.01
9.5198 | 10.7599 | 11.5198 | 10.5198 | 15.2797 | 17.2797 | 10.7599 | 21.2797 | 36.5595 | 53.8392 | 9.5298 | 10.7699 | 11.5198 | 10.5198 | 15.2797 | 17.2797 | 10.7699 | 21.2897 | 36.5695 | 53.8492 | 0.01
10.0229 | 11.0114 | 12.0229 | 11.0229 | 16.0343 | 18.0343 | 11.0114 | 22.0343 | 38.0686 | 56.1029 | 10.0329 | 11.0214 | 12.0229 | 11.0229 | 16.0343 | 18.0343 | 11.0214 | 22.0443 | 38.0786 | 56.1129 | 0.01
8.6306 | 10.3153 | 10.6306 | 9.6306 | 13.9458 | 15.9458 | 10.3153 | 19.9458 | 33.8917 | 49.8375 | 8.6406 | 10.3253 | 10.6306 | 9.6306 | 13.9458 | 15.9458 | 10.3253 | 19.9558 | 33.9017 | 49.8475 | 0.01
6.7681 | 9.384 | 8.7681 | 7.7681 | 11.1521 | 13.1521 | 9.384 | 17.1521 | 28.3042 | 41.4562 | 6.7781 | 9.394 | 8.7681 | 7.7681 | 11.1521 | 13.1521 | 9.394 | 17.1621 | 28.3142 | 41.4662 | 0.01
5.9488 | 8.9744 | 7.9488 | 6.9488 | 9.9232 | 11.9232 | 8.9744 | 15.9232 | 25.8464 | 37.7696 | 5.9588 | 8.9844 | 7.9488 | 6.9488 | 9.9232 | 11.9232 | 8.9844 | 15.9332 | 25.8564 | 37.7796 | 0.01
8.6032 | 10.3016 | 10.6032 | 9.6032 | 13.9049 | 15.9049 | 10.3016 | 19.9049 | 33.8097 | 49.7146 | 8.6132 | 10.3116 | 10.6032 | 9.6032 | 13.9049 | 15.9049 | 10.3116 | 19.9149 | 33.8197 | 49.7246 | 0.01
7.2646 | 9.6323 | 9.2646 | 8.2646 | 11.8969 | 13.8969 | 9.6323 | 17.8969 | 29.7938 | 43.6907 | 7.2746 | 9.6423 | 9.2646 | 8.2646 | 11.8969 | 13.8969 | 9.6423 | 17.9069 | 29.8038 | 43.7007 | 0.01
7.4592 | 9.7296 | 9.4592 | 8.4592 | 12.1887 | 14.1887 | 9.7296 | 18.1887 | 30.3775 | 44.5662 | 7.4692 | 9.7396 | 9.4592 | 8.4592 | 12.1887 | 14.1887 | 9.7396 | 18.1987 | 30.3875 | 44.5762 | 0.01
9.2906 | 10.6453 | 11.2906 | 10.2906 | 14.9359 | 16.9359 | 10.6453 | 20.9359 | 35.8718 | 52.8077 | 9.3006 | 10.6553 | 11.2906 | 10.2906 | 14.9359 | 16.9359 | 10.6553 | 20.9459 | 35.8818 | 52.8177 | 0.01
5.6507 | 8.8253 | 7.6507 | 6.6507 | 9.476 | 11.476 | 8.8253 | 15.476 | 24.9521 | 36.4281 | 5.6607 | 8.8353 | 7.6507 | 6.6507 | 9.476 | 11.476 | 8.8353 | 15.486 | 24.9621 | 36.4381 | 0.01
5.277 | 8.6385 | 7.277 | 6.277 | 8.9155 | 10.9155 | 8.6385 | 14.9155 | 23.8311 | 34.7466 | 5.287 | 8.6485 | 7.277 | 6.277 | 8.9155 | 10.9155 | 8.6485 | 14.9255 | 23.8411 | 34.7566 | 0.01
5.9486 | 8.9743 | 7.9486 | 6.9486 | 9.9229 | 11.9229 | 8.9743 | 15.9229 | 25.8458 | 37.7686 | 5.9586 | 8.9843 | 7.9486 | 6.9486 | 9.9229 | 11.9229 | 8.9843 | 15.9329 | 25.8558 | 37.7786 | 0.01
3.9488 | 7.9744 | 5.9488 | 4.9488 | 6.9232 | 8.9232 | 7.9744 | 12.9232 | 19.8463 | 28.7695 | 3.9588 | 7.9844 | 5.9488 | 4.9488 | 6.9232 | 8.9232 | 7.9844 | 12.9332 | 19.8563 | 28.7795 | 0.01
6.967 | 9.4835 | 8.967 | 7.967 | 11.4505 | 13.4505 | 9.4835 | 17.4505 | 28.9011 | 42.3516 | 6.977 | 9.4935 | 8.967 | 7.967 | 11.4505 | 13.4505 | 9.4935 | 17.4605 | 28.9111 | 42.3616 | 0.01
5.6804 | 8.8402 | 7.6804 | 6.6804 | 9.5206 | 11.5206 | 8.8402 | 15.5206 | 25.0411 | 36.5617 | 5.6904 | 8.8502 | 7.6804 | 6.6804 | 9.5206 | 11.5206 | 8.8502 | 15.5306 | 25.0511 | 36.5717 | 0.01
5.8489 | 8.9244 | 7.8489 | 6.8489 | 9.7733 | 11.7733 | 8.9244 | 15.7733 | 25.5467 | 37.32 | 5.8589 | 8.9344 | 7.8489 | 6.8489 | 9.7733 | 11.7733 | 8.9344 | 15.7833 | 25.5567 | 37.33 | 0.01
5.5667 | 8.7834 | 7.5667 | 6.5667 | 9.3501 | 11.3501 | 8.7834 | 15.3501 | 24.7002 | 36.0503 | 5.5767 | 8.7934 | 7.5667 | 6.5667 | 9.3501 | 11.3501 | 8.7934 | 15.3601 | 24.7102 | 36.0603 | 0.01
4.4888 | 8.2444 | 6.4888 | 5.4888 | 7.7331 | 9.7331 | 8.2444 | 13.7331 | 21.4663 | 31.1994 | 4.4988 | 8.2544 | 6.4888 | 5.4888 | 7.7331 | 9.7331 | 8.2544 | 13.7431 | 21.4763 | 31.2094 | 0.01
6.296 | 9.148 | 8.296 | 7.296 | 10.4439 | 12.4439 | 9.148 | 16.4439 | 26.8879 | 39.3318 | 6.306 | 9.158 | 8.296 | 7.296 | 10.4439 | 12.4439 | 9.158 | 16.4539 | 26.8979 | 39.3418 | 0.01
3.229 | 7.6145 | 5.229 | 4.229 | 5.8436 | 7.8436 | 7.6145 | 11.8436 | 17.6871 | 25.5307 | 3.239 | 7.6245 | 5.229 | 4.229 | 5.8436 | 7.8436 | 7.6245 | 11.8536 | 17.6971 | 25.5407 | 0.01
4.2843 | 8.1422 | 6.2843 | 5.2843 | 7.4265 | 9.4265 | 8.1422 | 13.4265 | 20.853 | 30.2795 | 4.2943 | 8.1522 | 6.2843 | 5.2843 | 7.4265 | 9.4265 | 8.1522 | 13.4365 | 20.863 | 30.2895 | 0.01
6.7877 | 9.3938 | 8.7877 | 7.7877 | 11.1815 | 13.1815 | 9.3938 | 17.1815 | 28.363 | 41.5445 | 6.7977 | 9.4038 | 8.7877 | 7.7877 | 11.1815 | 13.1815 | 9.4038 | 17.1915 | 28.373 | 41.5545 | 0.01
5.7262 | 8.8631 | 7.7262 | 6.7262 | 9.5893 | 11.5893 | 8.8631 | 15.5893 | 25.1786 | 36.7679 | 5.7362 | 8.8731 | 7.7262 | 6.7262 | 9.5893 | 11.5893 | 8.8731 | 15.5993 | 25.1886 | 36.7779 | 0.01
5.5621 | 8.7811 | 7.5621 | 6.5621 | 9.3432 | 11.3432 | 8.7811 | 15.3432 | 24.6863 | 36.0295 | 5.5721 | 8.7911 | 7.5621 | 6.5621 | 9.3432 | 11.3432 | 8.7911 | 15.3532 | 24.6963 | 36.0395 | 0.01
3.4367 | 7.7183 | 5.4367 | 4.4367 | 6.155 | 8.155 | 7.7183 | 12.155 | 18.31 | 26.465 | 3.4467 | 7.7283 | 5.4367 | 4.4367 | 6.155 | 8.155 | 7.7283 | 12.165 | 18.32 | 26.475 | 0.01
5.3088 | 8.6544 | 7.3088 | 6.3088 | 8.9631 | 10.9631 | 8.6544 | 14.9631 | 23.9263 | 34.8894 | 5.3188 | 8.6644 | 7.3088 | 6.3088 | 8.9631 | 10.9631 | 8.6644 | 14.9731 | 23.9363 | 34.8994 | 0.01
5.6934 | 8.8467 | 7.6934 | 6.6934 | 9.54 | 11.54 | 8.8467 | 15.54 | 25.0801 | 36.6201 | 5.7034 | 8.8567 | 7.6934 | 6.6934 | 9.54 | 11.54 | 8.8567 | 15.55 | 25.0901 | 36.6301 | 0.01
5.8089 | 8.9045 | 7.8089 | 6.8089 | 9.7134 | 11.7134 | 8.9045 | 15.7134 | 25.4268 | 37.1401 | 5.8189 | 8.9145 | 7.8089 | 6.8089 | 9.7134 | 11.7134 | 8.9145 | 15.7234 | 25.4368 | 37.1501 | 0.01
8.2504 | 10.1252 | 10.2504 | 9.2504 | 13.3756 | 15.3756 | 10.1252 | 19.3756 | 32.7511 | 48.1267 | 8.2604 | 10.1352 | 10.2504 | 9.2504 | 13.3756 | 15.3756 | 10.1352 | 19.3856 | 32.7611 | 48.1367 | 0.01
7.7162 | 9.8581 | 9.7162 | 8.7162 | 12.5744 | 14.5744 | 9.8581 | 18.5744 | 31.1487 | 45.7231 | 7.7262 | 9.8681 | 9.7162 | 8.7162 | 12.5744 | 14.5744 | 9.8681 | 18.5844 | 31.1587 | 45.7331 | 0.01
6.9447 | 9.4723 | 8.9447 | 7.9447 | 11.417 | 13.417 | 9.4723 | 17.417 | 28.834 | 42.251 | 6.9547 | 9.4823 | 8.9447 | 7.9447 | 11.417 | 13.417 | 9.4823 | 17.427 | 28.844 | 42.261 | 0.01
6.4412 | 9.2206 | 8.4412 | 7.4412 | 10.6617 | 12.6617 | 9.2206 | 16.6617 | 27.3235 | 39.9852 | 6.4512 | 9.2306 | 8.4412 | 7.4412 | 10.6617 | 12.6617 | 9.2306 | 16.6717 | 27.3335 | 39.9952 | 0.01
6.4323 | 9.2162 | 8.4323 | 7.4323 | 10.6485 | 12.6485 | 9.2162 | 16.6485 | 27.2969 | 39.9454 | 6.4423 | 9.2262 | 8.4323 | 7.4323 | 10.6485 | 12.6485 | 9.2262 | 16.6585 | 27.3069 | 39.9554 | 0.01
6.4928 | 9.2464 | 8.4928 | 7.4928 | 10.7392 | 12.7392 | 9.2464 | 16.7392 | 27.4785 | 40.2177 | 6.5028 | 9.2564 | 8.4928 | 7.4928 | 10.7392 | 12.7392 | 9.2564 | 16.7492 | 27.4885 | 40.2277 | 0.01
3.9532 | 7.9766 | 5.9532 | 4.9532 | 6.9298 | 8.9298 | 7.9766 | 12.9298 | 19.8596 | 28.7894 | 3.9632 | 7.9866 | 5.9532 | 4.9532 | 6.9298 | 8.9298 | 7.9866 | 12.9398 | 19.8696 | 28.7994 | 0.01
5.9402 | 8.9701 | 7.9402 | 6.9402 | 9.9103 | 11.9103 | 8.9701 | 15.9103 | 25.8206 | 37.731 | 5.9502 | 8.9801 | 7.9402 | 6.9402 | 9.9103 | 11.9103 | 8.9801 | 15.9203 | 25.8306 | 37.741 | 0.01
3.3361 | 7.6681 | 5.3361 | 4.3361 | 6.0042 | 8.0042 | 7.6681 | 12.0042 | 18.0084 | 26.0127 | 3.3461 | 7.6781 | 5.3361 | 4.3361 | 6.0042 | 8.0042 | 7.6781 | 12.0142 | 18.0184 | 26.0227 | 0.01
8.2102 | 10.1051 | 10.2102 | 9.2102 | 13.3154 | 15.3154 | 10.1051 | 19.3154 | 32.6307 | 47.9461 | 8.2202 | 10.1151 | 10.2102 | 9.2102 | 13.3154 | 15.3154 | 10.1151 | 19.3254 | 32.6407 | 47.9561 | 0.01
6.2818 | 9.1409 | 8.2818 | 7.2818 | 10.4227 | 12.4227 | 9.1409 | 16.4227 | 26.8453 | 39.268 | 6.2918 | 9.1509 | 8.2818 | 7.2818 | 10.4227 | 12.4227 | 9.1509 | 16.4327 | 26.8553 | 39.278 | 0.01
2.9093 | 7.4547 | 4.9093 | 3.9093 | 5.364 | 7.364 | 7.4547 | 11.364 | 16.728 | 24.092 | 2.9193 | 7.4647 | 4.9093 | 3.9093 | 5.364 | 7.364 | 7.4647 | 11.374 | 16.738 | 24.102 | 0.01
5.7942 | 8.8971 | 7.7942 | 6.7942 | 9.6914 | 11.6914 | 8.8971 | 15.6914 | 25.3827 | 37.0741 | 5.8042 | 8.9071 | 7.7942 | 6.7942 | 9.6914 | 11.6914 | 8.9071 | 15.7014 | 25.3927 | 37.0841 | 0.01
8.7512 | 10.3756 | 10.7512 | 9.7512 | 14.1267 | 16.1267 | 10.3756 | 20.1267 | 34.2535 | 50.3802 | 8.7612 | 10.3856 | 10.7512 | 9.7512 | 14.1267 | 16.1267 | 10.3856 | 20.1367 | 34.2635 | 50.3902 | 0.01
4.3479 | 8.174 | 6.3479 | 5.3479 | 7.5219 | 9.5219 | 8.174 | 13.5219 | 21.0437 | 30.5656 | 4.3579 | 8.184 | 6.3479 | 5.3479 | 7.5219 | 9.5219 | 8.184 | 13.5319 | 21.0537 | 30.5756 | 0.01
4.2408 | 8.1204 | 6.2408 | 5.2408 | 7.3612 | 9.3612 | 8.1204 | 13.3612 | 20.7223 | 30.0835 | 4.2508 | 8.1304 | 6.2408 | 5.2408 | 7.3612 | 9.3612 | 8.1304 | 13.3712 | 20.7323 | 30.0935 | 0.01
6.0035 | 9.0018 | 8.0035 | 7.0035 | 10.0053 | 12.0053 | 9.0018 | 16.0053 | 26.0106 | 38.0159 | 6.0135 | 9.0118 | 8.0035 | 7.0035 | 10.0053 | 12.0053 | 9.0118 | 16.0153 | 26.0206 | 38.0259 | 0.01
5.1528 | 8.5764 | 7.1528 | 6.1528 | 8.7292 | 10.7292 | 8.5764 | 14.7292 | 23.4584 | 34.1877 | 5.1628 | 8.5864 | 7.1528 | 6.1528 | 8.7292 | 10.7292 | 8.5864 | 14.7392 | 23.4684 | 34.1977 | 0.01
0.74596 | 6.373 | 2.746 | 1.746 | 2.1189 | 4.1189 | 6.373 | 8.1189 | 10.2379 | 14.3568 | 0.75596 | 6.383 | 2.746 | 1.746 | 2.1189 | 4.1189 | 6.383 | 8.1289 | 10.2479 | 14.3668 | 0.01
5.4154 | 8.7077 | 7.4154 | 6.4154 | 9.1231 | 11.1231 | 8.7077 | 15.1231 | 24.2463 | 35.3694 | 5.4254 | 8.7177 | 7.4154 | 6.4154 | 9.1231 | 11.1231 | 8.7177 | 15.1331 | 24.2563 | 35.3794 | 0.01
4.619 | 8.3095 | 6.619 | 5.619 | 7.9285 | 9.9285 | 8.3095 | 13.9285 | 21.8569 | 31.7854 | 4.629 | 8.3195 | 6.619 | 5.619 | 7.9285 | 9.9285 | 8.3195 | 13.9385 | 21.8669 | 31.7954 | 0.01
6.6018 | 9.3009 | 8.6018 | 7.6018 | 10.9028 | 12.9028 | 9.3009 | 16.9028 | 27.8055 | 40.7083 | 6.6118 | 9.3109 | 8.6018 | 7.6018 | 10.9028 | 12.9028 | 9.3109 | 16.9128 | 27.8155 | 40.7183 | 0.01
3.9475 | 7.9738 | 5.9475 | 4.9475 | 6.9213 | 8.9213 | 7.9738 | 12.9213 | 19.8426 | 28.7639 | 3.9575 | 7.9838 | 5.9475 | 4.9475 | 6.9213 | 8.9213 | 7.9838 | 12.9313 | 19.8526 | 28.7739 | 0.01
4.6839 | 8.3419 | 6.6839 | 5.6839 | 8.0258 | 10.0258 | 8.3419 | 14.0258 | 22.0516 | 32.0774 | 4.6939 | 8.3519 | 6.6839 | 5.6839 | 8.0258 | 10.0258 | 8.3519 | 14.0358 | 22.0616 | 32.0874 | 0.01
9.3878 | 10.6939 | 11.3878 | 10.3878 | 15.0817 | 17.0817 | 10.6939 | 21.0817 | 36.1634 | 53.2452 | 9.3978 | 10.7039 | 11.3878 | 10.3878 | 15.0817 | 17.0817 | 10.7039 | 21.0917 | 36.1734 | 53.2552 | 0.01
4.9761 | 8.4881 | 6.9761 | 5.9761 | 8.4642 | 10.4642 | 8.4881 | 14.4642 | 22.9283 | 33.3925 | 4.9861 | 8.4981 | 6.9761 | 5.9761 | 8.4642 | 10.4642 | 8.4981 | 14.4742 | 22.9383 | 33.4025 | 0.01
3.6458 | 7.8229 | 5.6458 | 4.6458 | 6.4687 | 8.4687 | 7.8229 | 12.4687 | 18.9374 | 27.4061 | 3.6558 | 7.8329 | 5.6458 | 4.6458 | 6.4687 | 8.4687 | 7.8329 | 12.4787 | 18.9474 | 27.4161 | 0.01
7.3652 | 9.6826 | 9.3652 | 8.3652 | 12.0478 | 14.0478 | 9.6826 | 18.0478 | 30.0956 | 44.1433 | 7.3752 | 9.6926 | 9.3652 | 8.3652 | 12.0478 | 14.0478 | 9.6926 | 18.0578 | 30.1056 | 44.1533 | 0.01
5.5501 | 8.7751 | 7.5501 | 6.5501 | 9.3252 | 11.3252 | 8.7751 | 15.3252 | 24.6504 | 35.9756 | 5.5601 | 8.7851 | 7.5501 | 6.5501 | 9.3252 | 11.3252 | 8.7851 | 15.3352 | 24.6604 | 35.9856 | 0.01
9.1422 | 10.5711 | 11.1422 | 10.1422 | 14.7134 | 16.7134 | 10.5711 | 20.7134 | 35.4267 | 52.1401 | 9.1522 | 10.5811 | 11.1422 | 10.1422 | 14.7134 | 16.7134 | 10.5811 | 20.7234 | 35.4367 | 52.1501 | 0.01
8.6099 | 10.305 | 10.6099 | 9.6099 | 13.9149 | 15.9149 | 10.305 | 19.9149 | 33.8297 | 49.7446 | 8.6199 | 10.315 | 10.6099 | 9.6099 | 13.9149 | 15.9149 | 10.315 | 19.9249 | 33.8397 | 49.7546 | 0.01
4.9848 | 8.4924 | 6.9848 | 5.9848 | 8.4772 | 10.4772 | 8.4924 | 14.4772 | 22.9545 | 33.4317 | 4.9948 | 8.5024 | 6.9848 | 5.9848 | 8.4772 | 10.4772 | 8.5024 | 14.4872 | 22.9645 | 33.4417 | 0.01
7.565 | 9.7825 | 9.565 | 8.565 | 12.3474 | 14.3474 | 9.7825 | 18.3474 | 30.6949 | 45.0423 | 7.575 | 9.7925 | 9.565 | 8.565 | 12.3474 | 14.3474 | 9.7925 | 18.3574 | 30.7049 | 45.0523 | 0.01
5.7244 | 8.8622 | 7.7244 | 6.7244 | 9.5867 | 11.5867 | 8.8622 | 15.5867 | 25.1733 | 36.76 | 5.7344 | 8.8722 | 7.7244 | 6.7244 | 9.5867 | 11.5867 | 8.8722 | 15.5967 | 25.1833 | 36.77 | 0.01
6.3968 | 9.1984 | 8.3968 | 7.3968 | 10.5952 | 12.5952 | 9.1984 | 16.5952 | 27.1904 | 39.7855 | 6.4068 | 9.2084 | 8.3968 | 7.3968 | 10.5952 | 12.5952 | 9.2084 | 16.6052 | 27.2004 | 39.7955 | 0.01
2.6741 | 7.3371 | 4.6741 | 3.6741 | 5.0112 | 7.0112 | 7.3371 | 11.0112 | 16.0224 | 23.0336 | 2.6841 | 7.3471 | 4.6741 | 3.6741 | 5.0112 | 7.0112 | 7.3471 | 11.0212 | 16.0324 | 23.0436 | 0.01
5.9248 | 8.9624 | 7.9248 | 6.9248 | 9.8873 | 11.8873 | 8.9624 | 15.8873 | 25.7745 | 37.6618 | 5.9348 | 8.9724 | 7.9248 | 6.9248 | 9.8873 | 11.8873 | 8.9724 | 15.8973 | 25.7845 | 37.6718 | 0.01
6.4691 | 9.2345 | 8.4691 | 7.4691 | 10.7036 | 12.7036 | 9.2345 | 16.7036 | 27.4073 | 40.1109 | 6.4791 | 9.2445 | 8.4691 | 7.4691 | 10.7036 | 12.7036 | 9.2445 | 16.7136 | 27.4173 | 40.1209 | 0.01
7.9171 | 9.9585 | 9.9171 | 8.9171 | 12.8756 | 14.8756 | 9.9585 | 18.8756 | 31.7513 | 46.6269 | 7.9271 | 9.9685 | 9.9171 | 8.9171 | 12.8756 | 14.8756 | 9.9685 | 18.8856 | 31.7613 | 46.6369 | 0.01
5.5816 | 8.7908 | 7.5816 | 6.5816 | 9.3725 | 11.3725 | 8.7908 | 15.3725 | 24.7449 | 36.1174 | 5.5916 | 8.8008 | 7.5816 | 6.5816 | 9.3725 | 11.3725 | 8.8008 | 15.3825 | 24.7549 | 36.1274 | 0.01
3.463 | 7.7315 | 5.463 | 4.463 | 6.1944 | 8.1944 | 7.7315 | 12.1944 | 18.3889 | 26.5833 | 3.473 | 7.7415 | 5.463 | 4.463 | 6.1944 | 8.1944 | 7.7415 | 12.2044 | 18.3989 | 26.5933 | 0.01
5.7887 | 8.8944 | 7.7887 | 6.7887 | 9.6831 | 11.6831 | 8.8944 | 15.6831 | 25.3662 | 37.0493 | 5.7987 | 8.9044 | 7.7887 | 6.7887 | 9.6831 | 11.6831 | 8.9044 | 15.6931 | 25.3762 | 37.0593 | 0.01
6.1546 | 9.0773 | 8.1546 | 7.1546 | 10.2319 | 12.2319 | 9.0773 | 16.2319 | 26.4638 | 38.6958 | 6.1646 | 9.0873 | 8.1546 | 7.1546 | 10.2319 | 12.2319 | 9.0873 | 16.2419 | 26.4738 | 38.7058 | 0.01
5.163 | 8.5815 | 7.163 | 6.163 | 8.7444 | 10.7444 | 8.5815 | 14.7444 | 23.4889 | 34.2333 | 5.173 | 8.5915 | 7.163 | 6.163 | 8.7444 | 10.7444 | 8.5915 | 14.7544 | 23.4989 | 34.2433 | 0.01
3.7331 | 7.8665 | 5.7331 | 4.7331 | 6.5996 | 8.5996 | 7.8665 | 12.5996 | 19.1992 | 27.7988 | 3.7431 | 7.8765 | 5.7331 | 4.7331 | 6.5996 | 8.5996 | 7.8765 | 12.6096 | 19.2092 | 27.8088 | 0.01
8.1549 | 10.0774 | 10.1549 | 9.1549 | 13.2323 | 15.2323 | 10.0774 | 19.2323 | 32.4646 | 47.6969 | 8.1649 | 10.0874 | 10.1549 | 9.1549 | 13.2323 | 15.2323 | 10.0874 | 19.2423 | 32.4746 | 47.7069 | 0.01
4.3398 | 8.1699 | 6.3398 | 5.3398 | 7.5097 | 9.5097 | 8.1699 | 13.5097 | 21.0194 | 30.5291 | 4.3498 | 8.1799 | 6.3398 | 5.3398 | 7.5097 | 9.5097 | 8.1799 | 13.5197 | 21.0294 | 30.5391 | 0.01
8.4702 | 10.2351 | 10.4702 | 9.4702 | 13.7053 | 15.7053 | 10.2351 | 19.7053 | 33.4105 | 49.1158 | 8.4802 | 10.2451 | 10.4702 | 9.4702 | 13.7053 | 15.7053 | 10.2451 | 19.7153 | 33.4205 | 49.1258 | 0.01
3.9037 | 7.9519 | 5.9037 | 4.9037 | 6.8556 | 8.8556 | 7.9519 | 12.8556 | 19.7112 | 28.5668 | 3.9137 | 7.9619 | 5.9037 | 4.9037 | 6.8556 | 8.8556 | 7.9619 | 12.8656 | 19.7212 | 28.5768 | 0.01
5.8388 | 8.9194 | 7.8388 | 6.8388 | 9.7582 | 11.7582 | 8.9194 | 15.7582 | 25.5165 | 37.2747 | 5.8488 | 8.9294 | 7.8388 | 6.8388 | 9.7582 | 11.7582 | 8.9294 | 15.7682 | 25.5265 | 37.2847 | 0.01
7.493 | 9.7465 | 9.493 | 8.493 | 12.2395 | 14.2395 | 9.7465 | 18.2395 | 30.479 | 44.7184 | 7.503 | 9.7565 | 9.493 | 8.493 | 12.2395 | 14.2395 | 9.7565 | 18.2495 | 30.489 | 44.7284 | 0.01
4.9927 | 8.4963 | 6.9927 | 5.9927 | 8.489 | 10.489 | 8.4963 | 14.489 | 22.978 | 33.4669 | 5.0027 | 8.5063 | 6.9927 | 5.9927 | 8.489 | 10.489 | 8.5063 | 14.499 | 22.988 | 33.4769 | 0.01
8.3457 | 10.1729 | 10.3457 | 9.3457 | 13.5186 | 15.5186 | 10.1729 | 19.5186 | 33.0371 | 48.5557 | 8.3557 | 10.1829 | 10.3457 | 9.3457 | 13.5186 | 15.5186 | 10.1829 | 19.5286 | 33.0471 | 48.5657 | 0.01
10.0861 | 11.043 | 12.0861 | 11.0861 | 16.1291 | 18.1291 | 11.043 | 22.1291 | 38.2582 | 56.3873 | 10.0961 | 11.053 | 12.0861 | 11.0861 | 16.1291 | 18.1291 | 11.053 | 22.1391 | 38.2682 | 56.3973 | 0.01
2.6271 | 7.3136 | 4.6271 | 3.6271 | 4.9407 | 6.9407 | 7.3136 | 10.9407 | 15.8814 | 22.8221 | 2.6371 | 7.3236 | 4.6271 | 3.6271 | 4.9407 | 6.9407 | 7.3236 | 10.9507 | 15.8914 | 22.8321 | 0.01
7.0962 | 9.5481 | 9.0962 | 8.0962 | 11.6443 | 13.6443 | 9.5481 | 17.6443 | 29.2885 | 42.9328 | 7.1062 | 9.5581 | 9.0962 | 8.0962 | 11.6443 | 13.6443 | 9.5581 | 17.6543 | 29.2985 | 42.9428 | 0.01
5.8452 | 8.9226 | 7.8452 | 6.8452 | 9.7678 | 11.7678 | 8.9226 | 15.7678 | 25.5355 | 37.3033 | 5.8552 | 8.9326 | 7.8452 | 6.8452 | 9.7678 | 11.7678 | 8.9326 | 15.7778 | 25.5455 | 37.3133 | 0.01
10.5641 | 11.2821 | 12.5641 | 11.5641 | 16.8462 | 18.8462 | 11.2821 | 22.8462 | 39.6924 | 58.5386 | 10.5741 | 11.2921 | 12.5641 | 11.5641 | 16.8462 | 18.8462 | 11.2921 | 22.8562 | 39.7024 | 58.5486 | 0.01
2.6054 | 7.3027 | 4.6054 | 3.6054 | 4.9081 | 6.9081 | 7.3027 | 10.9081 | 15.8163 | 22.7244 | 2.6154 | 7.3127 | 4.6054 | 3.6054 | 4.9081 | 6.9081 | 7.3127 | 10.9181 | 15.8263 | 22.7344 | 0.01
4.9665 | 8.4833 | 6.9665 | 5.9665 | 8.4498 | 10.4498 | 8.4833 | 14.4498 | 22.8996 | 33.3493 | 4.9765 | 8.4933 | 6.9665 | 5.9665 | 8.4498 | 10.4498 | 8.4933 | 14.4598 | 22.9096 | 33.3593 | 0.01
9.3474 | 10.6737 | 11.3474 | 10.3474 | 15.0211 | 17.0211 | 10.6737 | 21.0211 | 36.0422 | 53.0634 | 9.3574 | 10.6837 | 11.3474 | 10.3474 | 15.0211 | 17.0211 | 10.6837 | 21.0311 | 36.0522 | 53.0734 | 0.01
5.9379 | 8.969 | 7.9379 | 6.9379 | 9.9069 | 11.9069 | 8.969 | 15.9069 | 25.8138 | 37.7207 | 5.9479 | 8.979 | 7.9379 | 6.9379 | 9.9069 | 11.9069 | 8.979 | 15.9169 | 25.8238 | 37.7307 | 0.01
5.5692 | 8.7846 | 7.5692 | 6.5692 | 9.3538 | 11.3538 | 8.7846 | 15.3538 | 24.7076 | 36.0614 | 5.5792 | 8.7946 | 7.5692 | 6.5692 | 9.3538 | 11.3538 | 8.7946 | 15.3638 | 24.7176 | 36.0714 | 0.01
5.1908 | 8.5954 | 7.1908 | 6.1908 | 8.7862 | 10.7862 | 8.5954 | 14.7862 | 23.5724 | 34.3587 | 5.2008 | 8.6054 | 7.1908 | 6.1908 | 8.7862 | 10.7862 | 8.6054 | 14.7962 | 23.5824 | 34.3687 | 0.01
8.7941 | 10.397 | 10.7941 | 9.7941 | 14.1911 | 16.1911 | 10.397 | 20.1911 | 34.3822 | 50.5733 | 8.8041 | 10.407 | 10.7941 | 9.7941 | 14.1911 | 16.1911 | 10.407 | 20.2011 | 34.3922 | 50.5833 | 0.01
4.5682 | 8.2841 | 6.5682 | 5.5682 | 7.8524 | 9.8524 | 8.2841 | 13.8524 | 21.7047 | 31.5571 | 4.5782 | 8.2941 | 6.5682 | 5.5682 | 7.8524 | 9.8524 | 8.2941 | 13.8624 | 21.7147 | 31.5671 | 0.01
7.66 | 9.83 | 9.66 | 8.66 | 12.49 | 14.49 | 9.83 | 18.49 | 30.98 | 45.47 | 7.67 | 9.84 | 9.66 | 8.66 | 12.49 | 14.49 | 9.84 | 18.5 | 30.99 | 45.48 | 0.01
6.8619 | 9.431 | 8.8619 | 7.8619 | 11.2929 | 13.2929 | 9.431 | 17.2929 | 28.5858 | 41.8788 | 6.8719 | 9.441 | 8.8619 | 7.8619 | 11.2929 | 13.2929 | 9.441 | 17.3029 | 28.5958 | 41.8888 | 0.01
4.1334 | 8.0667 | 6.1334 | 5.1334 | 7.2 | 9.2 | 8.0667 | 13.2 | 20.4001 | 29.6001 | 4.1434 | 8.0767 | 6.1334 | 5.1334 | 7.2 | 9.2 | 8.0767 | 13.21 | 20.4101 | 29.6101 | 0.01
7.1882 | 9.5941 | 9.1882 | 8.1882 | 11.7823 | 13.7823 | 9.5941 | 17.7823 | 29.5647 | 43.347 | 7.1982 | 9.6041 | 9.1882 | 8.1882 | 11.7823 | 13.7823 | 9.6041 | 17.7923 | 29.5747 | 43.357 | 0.01
6.5105 | 9.2553 | 8.5105 | 7.5105 | 10.7658 | 12.7658 | 9.2553 | 16.7658 | 27.5316 | 40.2974 | 6.5205 | 9.2653 | 8.5105 | 7.5105 | 10.7658 | 12.7658 | 9.2653 | 16.7758 | 27.5416 | 40.3074 | 0.01
6.7038 | 9.3519 | 8.7038 | 7.7038 | 11.0557 | 13.0557 | 9.3519 | 17.0557 | 28.1115 | 41.1672 | 6.7138 | 9.3619 | 8.7038 | 7.7038 | 11.0557 | 13.0557 | 9.3619 | 17.0657 | 28.1215 | 41.1772 | 0.01
4.6732 | 8.3366 | 6.6732 | 5.6732 | 8.0099 | 10.0099 | 8.3366 | 14.0099 | 22.0197 | 32.0296 | 4.6832 | 8.3466 | 6.6732 | 5.6732 | 8.0099 | 10.0099 | 8.3466 | 14.0199 | 22.0297 | 32.0396 | 0.01
4.9097 | 8.4549 | 6.9097 | 5.9097 | 8.3646 | 10.3646 | 8.4549 | 14.3646 | 22.7292 | 33.0938 | 4.9197 | 8.4649 | 6.9097 | 5.9097 | 8.3646 | 10.3646 | 8.4649 | 14.3746 | 22.7392 | 33.1038 | 0.01
6.6014 | 9.3007 | 8.6014 | 7.6014 | 10.902 | 12.902 | 9.3007 | 16.902 | 27.8041 | 40.7061 | 6.6114 | 9.3107 | 8.6014 | 7.6014 | 10.902 | 12.902 | 9.3107 | 16.912 | 27.8141 | 40.7161 | 0.01
6.4841 | 9.2421 | 8.4841 | 7.4841 | 10.7262 | 12.7262 | 9.2421 | 16.7262 | 27.4524 | 40.1785 | 6.4941 | 9.2521 | 8.4841 | 7.4841 | 10.7262 | 12.7262 | 9.2521 | 16.7362 | 27.4624 | 40.1885 | 0.01
7.7612 | 9.8806 | 9.7612 | 8.7612 | 12.6418 | 14.6418 | 9.8806 | 18.6418 | 31.2836 | 45.9254 | 7.7712 | 9.8906 | 9.7612 | 8.7612 | 12.6418 | 14.6418 | 9.8906 | 18.6518 | 31.2936 | 45.9354 | 0.01
10.5814 | 11.2907 | 12.5814 | 11.5814 | 16.8721 | 18.8721 | 11.2907 | 22.8721 | 39.7442 | 58.6164 | 10.5914 | 11.3007 | 12.5814 | 11.5814 | 16.8721 | 18.8721 | 11.3007 | 22.8821 | 39.7542 | 58.6264 | 0.01
4.8892 | 8.4446 | 6.8892 | 5.8892 | 8.3337 | 10.3337 | 8.4446 | 14.3337 | 22.6675 | 33.0012 | 4.8992 | 8.4546 | 6.8892 | 5.8892 | 8.3337 | 10.3337 | 8.4546 | 14.3437 | 22.6775 | 33.0112 | 0.01
5.0805 | 8.5403 | 7.0805 | 6.0805 | 8.6208 | 10.6208 | 8.5403 | 14.6208 | 23.2415 | 33.8623 | 5.0905 | 8.5503 | 7.0805 | 6.0805 | 8.6208 | 10.6208 | 8.5503 | 14.6308 | 23.2515 | 33.8723 | 0.01
[8 empty] | Average | 37.9051 | [6 empty] | 0 | 0 | Average | 37.9151 | 100%