## Team Members
Names:
Yelizaveta Semikina
Juhil Patel
Elane De Menezes

## PM
Activity | Predecessor | Mean | Standard Deviation | Variance | Critical?
A Obtain Funding | - | 6 | 0.6 | 0.36 | YES
B Design Building | A | 8 | 1.3 | 1.69 | YES
C Prepare Site | A | 2 | 0.2 | 0.04 | NO
D Lay Foundation | B,C | 2 | 0.3 | 0.09 | YES
E Erects Walls & Roof | D | 3 | 1 | 1 | NO
F Finish Exterior | E | 3 | 0.6 | 0.36 | NO
G Finish Interior | D | 7 | 1.5 | 2.25 | YES
H Landscape Grounds | F,G | 5 | 1.2 | 1.44 | YES
|  | Variance of Project= |  | 5.83
|  | STD of project |  | 2.4145
|  | Expected Time = |  | 28
A)P(T<30 months) = | 0.82832
B)P(T>36 months) = | 3.3133

## RND generation and model
A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4
-12.9745 | 3.8889 | 1.3675 | 1.0513 | -0.16242 | 1.1025 | 2.2564 | 1.2051 | -9.0857 | -8.0344 | -5.778 | -4.5729
-0.12216 | 6.6735 | 1.7959 | 1.6939 | 1.9796 | 2.3878 | 5.4695 | 3.7756 | 6.5514 | 8.2453 | 13.7147 | 17.4903
6.9139 | 8.198 | 2.0305 | 2.0457 | 3.1523 | 3.0914 | 7.2285 | 5.1828 | 15.1119 | 17.1576 | 24.3861 | 29.5689
12.6187 | 9.4341 | 2.2206 | 2.3309 | 4.1031 | 3.6619 | 8.6547 | 6.3237 | 22.0528 | 24.3837 | 33.0384 | 39.3622
2.4444 | 7.2296 | 1.8815 | 1.8222 | 2.4074 | 2.6444 | 6.1111 | 4.2889 | 9.674 | 11.4962 | 17.6073 | 21.8962
13.5518 | 9.6362 | 2.2517 | 2.3776 | 4.2586 | 3.7552 | 8.888 | 6.5104 | 23.188 | 25.5656 | 34.4536 | 40.9639
9.2237 | 8.6985 | 2.1075 | 2.1612 | 3.5373 | 3.3224 | 7.8059 | 5.6447 | 17.9221 | 20.0833 | 27.8892 | 33.5339
13.2479 | 9.5704 | 2.2416 | 2.3624 | 4.208 | 3.7248 | 8.812 | 6.4496 | 22.8182 | 25.1806 | 33.9926 | 40.4422
14.8387 | 9.9151 | 2.2946 | 2.4419 | 4.4731 | 3.8839 | 9.2097 | 6.7677 | 24.7538 | 27.1957 | 36.4054 | 43.1731
5.5377 | 7.8998 | 1.9846 | 1.9769 | 2.9229 | 2.9538 | 6.8844 | 4.9075 | 13.4375 | 15.4144 | 22.2988 | 27.2063
3.6914 | 7.4998 | 1.923 | 1.8846 | 2.6152 | 2.7691 | 6.4229 | 4.5383 | 11.1913 | 13.0758 | 19.4987 | 24.037
15.412 | 10.0393 | 2.3137 | 2.4706 | 4.5687 | 3.9412 | 9.353 | 6.8824 | 25.4513 | 27.9219 | 37.2749 | 44.1573
-1.8093 | 6.308 | 1.7397 | 1.6095 | 1.6984 | 2.2191 | 5.0477 | 3.4381 | 4.4986 | 6.1082 | 11.1558 | 14.594
5.3552 | 7.8603 | 1.9785 | 1.9678 | 2.8925 | 2.9355 | 6.8388 | 4.871 | 13.2155 | 15.1833 | 22.0221 | 26.8931
3.6258 | 7.4856 | 1.9209 | 1.8813 | 2.6043 | 2.7626 | 6.4065 | 4.5252 | 11.1114 | 12.9927 | 19.3991 | 23.9243
17.2865 | 10.4454 | 2.3762 | 2.5643 | 4.8811 | 4.1286 | 9.8216 | 7.2573 | 27.7319 | 30.2962 | 40.1178 | 47.3751
-1.2041 | 6.4391 | 1.7599 | 1.6398 | 1.7993 | 2.2796 | 5.199 | 3.5592 | 5.2351 | 6.8749 | 12.0738 | 15.633
10.4295 | 8.9597 | 2.1476 | 2.2215 | 3.7382 | 3.4429 | 8.1074 | 5.8859 | 19.3892 | 21.6107 | 29.7181 | 35.604
3.5508 | 7.4693 | 1.9184 | 1.8775 | 2.5918 | 2.7551 | 6.3877 | 4.5102 | 11.0202 | 12.8977 | 19.2854 | 23.7956
8.8773 | 8.6234 | 2.0959 | 2.1439 | 3.4795 | 3.2877 | 7.7193 | 5.5755 | 17.5007 | 19.6445 | 27.3638 | 32.9393
10.0205 | 8.8711 | 2.134 | 2.201 | 3.6701 | 3.402 | 8.0051 | 5.8041 | 18.8916 | 21.0926 | 29.0977 | 34.9018
8.7605 | 8.5981 | 2.092 | 2.138 | 3.4601 | 3.276 | 7.6901 | 5.5521 | 17.3586 | 19.4966 | 27.1867 | 32.7388
13.6101 | 9.6489 | 2.2537 | 2.3805 | 4.2684 | 3.761 | 8.9025 | 6.522 | 23.259 | 25.6395 | 34.542 | 41.064
-4.2589 | 5.7772 | 1.658 | 1.4871 | 1.2902 | 1.9741 | 4.4353 | 2.9482 | 1.5183 | 3.0053 | 7.4406 | 10.3888
7.7808 | 8.3858 | 2.0594 | 2.089 | 3.2968 | 3.1781 | 7.4452 | 5.3562 | 16.1666 | 18.2557 | 25.7008 | 31.057
9.0241 | 8.6552 | 2.1008 | 2.1512 | 3.504 | 3.3024 | 7.756 | 5.6048 | 17.6794 | 19.8306 | 27.5866 | 33.1914
0.87462 | 6.8895 | 1.8292 | 1.7437 | 2.1458 | 2.4875 | 5.7187 | 3.9749 | 7.7641 | 9.5079 | 15.2265 | 19.2014
4.3537 | 7.6433 | 1.9451 | 1.9177 | 2.7256 | 2.8354 | 6.5884 | 4.6707 | 11.997 | 13.9147 | 20.5031 | 25.1739
7.5191 | 8.3291 | 2.0506 | 2.076 | 3.2532 | 3.1519 | 7.3798 | 5.3038 | 15.8482 | 17.9242 | 25.3039 | 30.6078
-1.0782 | 6.4664 | 1.7641 | 1.6461 | 1.8203 | 2.2922 | 5.2304 | 3.5844 | 5.3882 | 7.0343 | 12.2647 | 15.8491
-5.1061 | 5.5937 | 1.6298 | 1.4447 | 1.149 | 1.8894 | 4.2235 | 2.7788 | 0.48754 | 1.9322 | 6.1557 | 8.9345
1.3629 | 6.9953 | 1.8454 | 1.7681 | 2.2271 | 2.5363 | 5.8407 | 4.0726 | 8.3582 | 10.1263 | 15.967 | 20.0396
1.8639 | 7.1038 | 1.8621 | 1.7932 | 2.3106 | 2.5864 | 5.966 | 4.1728 | 8.9677 | 10.7609 | 16.7269 | 20.8996
9.9802 | 8.8624 | 2.1327 | 2.199 | 3.6634 | 3.398 | 7.995 | 5.796 | 18.8426 | 21.0416 | 29.0366 | 34.8327
7.6476 | 8.357 | 2.0549 | 2.0824 | 3.2746 | 3.1648 | 7.4119 | 5.3295 | 16.0046 | 18.087 | 25.4989 | 30.8284
11.5709 | 9.207 | 2.1857 | 2.2785 | 3.9285 | 3.5571 | 8.3927 | 6.1142 | 20.778 | 23.0565 | 31.4492 | 37.5634
2.211 | 7.179 | 1.8737 | 1.8105 | 2.3685 | 2.6211 | 6.0527 | 4.2422 | 9.39 | 11.2006 | 17.2533 | 21.4955
8.1676 | 8.4696 | 2.0723 | 2.1084 | 3.3613 | 3.2168 | 7.5419 | 5.4335 | 16.6372 | 18.7456 | 26.2875 | 31.721
-1.5632 | 6.3613 | 1.7479 | 1.6218 | 1.7395 | 2.2437 | 5.1092 | 3.4874 | 4.7981 | 6.42 | 11.5292 | 15.0165
6.51 | 8.1105 | 2.017 | 2.0255 | 3.085 | 3.051 | 7.1275 | 5.102 | 14.6205 | 16.646 | 23.7735 | 28.8754
9.2137 | 8.6963 | 2.1071 | 2.1607 | 3.5356 | 3.3214 | 7.8034 | 5.6427 | 17.91 | 20.0707 | 27.8741 | 33.5169
2.0475 | 7.1436 | 1.8683 | 1.8024 | 2.3413 | 2.6048 | 6.0119 | 4.2095 | 9.1911 | 10.9935 | 17.0054 | 21.2149
2.251 | 7.1877 | 1.875 | 1.8125 | 2.3752 | 2.6251 | 6.0627 | 4.2502 | 9.4387 | 11.2513 | 17.314 | 21.5642
3.4527 | 7.4481 | 1.9151 | 1.8726 | 2.5755 | 2.7453 | 6.3632 | 4.4905 | 10.9008 | 12.7734 | 19.1366 | 23.6272
-0.171 | 6.663 | 1.7943 | 1.6915 | 1.9715 | 2.3829 | 5.4573 | 3.7658 | 6.492 | 8.1834 | 13.6407 | 17.4065
2.2975 | 7.1978 | 1.8766 | 1.8149 | 2.3829 | 2.6297 | 6.0744 | 4.2595 | 9.4953 | 11.3101 | 17.3845 | 21.644
0.11826 | 6.7256 | 1.8039 | 1.7059 | 2.0197 | 2.4118 | 5.5296 | 3.8237 | 6.8439 | 8.5498 | 14.0794 | 17.903
5.5591 | 7.9045 | 1.9853 | 1.978 | 2.9265 | 2.9559 | 6.8898 | 4.9118 | 13.4636 | 15.4416 | 22.3313 | 27.2432
2.3412 | 7.2073 | 1.878 | 1.8171 | 2.3902 | 2.6341 | 6.0853 | 4.2682 | 9.5484 | 11.3655 | 17.4508 | 21.719
8.1691 | 8.47 | 2.0723 | 2.1085 | 3.3615 | 3.2169 | 7.5423 | 5.4338 | 16.639 | 18.7475 | 26.2897 | 31.7235
8.3035 | 8.4991 | 2.0768 | 2.1152 | 3.3839 | 3.2303 | 7.5759 | 5.4607 | 16.8026 | 18.9177 | 26.4936 | 31.9543
10.4961 | 8.9742 | 2.1499 | 2.2248 | 3.7493 | 3.4496 | 8.124 | 5.8992 | 19.4702 | 21.695 | 29.8191 | 35.7183
10.5815 | 8.9927 | 2.1527 | 2.2291 | 3.7636 | 3.4582 | 8.1454 | 5.9163 | 19.5742 | 21.8033 | 29.9486 | 35.8649
5.8599 | 7.9696 | 1.9953 | 1.993 | 2.9766 | 2.986 | 6.965 | 4.972 | 13.8295 | 15.8225 | 22.7875 | 27.7595
14.7012 | 9.8853 | 2.29 | 2.4351 | 4.4502 | 3.8701 | 9.1753 | 6.7402 | 24.5864 | 27.0215 | 36.1968 | 42.937
8.3236 | 8.5034 | 2.0775 | 2.1162 | 3.3873 | 3.2324 | 7.5809 | 5.4647 | 16.827 | 18.9432 | 26.5241 | 31.9888
8.3401 | 8.507 | 2.078 | 2.117 | 3.39 | 3.234 | 7.585 | 5.468 | 16.8471 | 18.9641 | 26.5492 | 32.0172
10.3472 | 8.9419 | 2.1449 | 2.2174 | 3.7245 | 3.4347 | 8.0868 | 5.8694 | 19.289 | 21.5064 | 29.5932 | 35.4626
14.4633 | 9.8337 | 2.2821 | 2.4232 | 4.4105 | 3.8463 | 9.1158 | 6.6927 | 24.297 | 26.7201 | 35.836 | 42.5286
-3.5127 | 5.9389 | 1.6829 | 1.5244 | 1.4146 | 2.0487 | 4.6218 | 3.0975 | 2.4263 | 3.9506 | 8.5725 | 11.6699
5.4776 | 7.8868 | 1.9826 | 1.9739 | 2.9129 | 2.9478 | 6.8694 | 4.8955 | 13.3644 | 15.3383 | 22.2077 | 27.1032
5.2807 | 7.8442 | 1.976 | 1.964 | 2.8801 | 2.9281 | 6.8202 | 4.8561 | 13.1249 | 15.0889 | 21.9091 | 26.7653
7.9784 | 8.4286 | 2.0659 | 2.0989 | 3.3297 | 3.1978 | 7.4946 | 5.3957 | 16.407 | 18.5059 | 26.0005 | 31.3962
13.8033 | 9.6907 | 2.2601 | 2.3902 | 4.3006 | 3.7803 | 8.9508 | 6.5607 | 23.494 | 25.8842 | 34.835 | 41.3957
8.5439 | 8.5512 | 2.0848 | 2.1272 | 3.424 | 3.2544 | 7.636 | 5.5088 | 17.0951 | 19.2223 | 26.8583 | 32.367
4.4437 | 7.6628 | 1.9481 | 1.9222 | 2.7406 | 2.8444 | 6.6109 | 4.6887 | 12.1065 | 14.0287 | 20.6396 | 25.3283
7.7456 | 8.3782 | 2.0582 | 2.0873 | 3.2909 | 3.1746 | 7.4364 | 5.3491 | 16.1238 | 18.2111 | 25.6475 | 30.9967
-2.7103 | 6.1128 | 1.7097 | 1.5645 | 1.5483 | 2.129 | 4.8224 | 3.2579 | 3.4024 | 4.9669 | 9.7893 | 13.0473
10.561 | 8.9882 | 2.152 | 2.2281 | 3.7602 | 3.4561 | 8.1403 | 5.9122 | 19.5493 | 21.7773 | 29.9176 | 35.8298
4.0867 | 7.5855 | 1.9362 | 1.9043 | 2.6811 | 2.8087 | 6.5217 | 4.6173 | 11.6721 | 13.5765 | 20.0982 | 24.7155
-2.8232 | 6.0883 | 1.7059 | 1.5588 | 1.5295 | 2.1177 | 4.7942 | 3.2354 | 3.2652 | 4.824 | 9.6182 | 12.8536
4.6997 | 7.7183 | 1.9567 | 1.935 | 2.7833 | 2.87 | 6.6749 | 4.7399 | 12.418 | 14.353 | 21.0279 | 25.7678
9.2885 | 8.7125 | 2.1096 | 2.1644 | 3.5481 | 3.3288 | 7.8221 | 5.6577 | 18.0009 | 20.1654 | 27.9875 | 33.6452
4.1946 | 7.6088 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5486 | 4.6389 | 11.8034 | 13.7131 | 20.2618 | 24.9007
17.7331 | 10.5422 | 2.3911 | 2.5867 | 4.9555 | 4.1733 | 9.9333 | 7.3466 | 28.2753 | 30.862 | 40.7953 | 48.1419
5.1638 | 7.8188 | 1.9721 | 1.9582 | 2.8606 | 2.9164 | 6.791 | 4.8328 | 12.9827 | 14.9409 | 21.7318 | 26.5646
-1.7584 | 6.319 | 1.7414 | 1.6121 | 1.7069 | 2.2242 | 5.0604 | 3.4483 | 4.5607 | 6.1727 | 11.2331 | 14.6815
-8.3468 | 4.8915 | 1.5218 | 1.2827 | 0.60887 | 1.5653 | 3.4133 | 2.1306 | -3.4553 | -2.1726 | 1.2407 | 3.3713
-0.18201 | 6.6606 | 1.7939 | 1.6909 | 1.9697 | 2.3818 | 5.4545 | 3.7636 | 6.4786 | 8.1695 | 13.624 | 17.3876
-6.2667 | 5.3422 | 1.5911 | 1.3867 | 0.95556 | 1.7733 | 3.9333 | 2.5467 | -0.92444 | 0.46223 | 4.3956 | 6.9422
10.6683 | 9.0115 | 2.1556 | 2.2334 | 3.778 | 3.4668 | 8.1671 | 5.9337 | 19.6798 | 21.9132 | 30.0803 | 36.0139
6.5503 | 8.1192 | 2.0183 | 2.0275 | 3.0917 | 3.055 | 7.1376 | 5.1101 | 14.6695 | 16.697 | 23.8346 | 28.9447
7.3155 | 8.285 | 2.0438 | 2.0658 | 3.2192 | 3.1315 | 7.3289 | 5.2631 | 15.6005 | 17.6663 | 24.9951 | 30.2582
12.1047 | 9.3227 | 2.2035 | 2.3052 | 4.0174 | 3.6105 | 8.5262 | 6.2209 | 21.4274 | 23.7326 | 32.2588 | 38.4797
11.6009 | 9.2135 | 2.1867 | 2.28 | 3.9335 | 3.5601 | 8.4002 | 6.1202 | 20.8144 | 23.0944 | 31.4947 | 37.6148
16.131 | 10.195 | 2.3377 | 2.5065 | 4.6885 | 4.0131 | 9.5327 | 7.0262 | 26.326 | 28.8326 | 38.3653 | 45.3915
7.8716 | 8.4055 | 2.0624 | 2.0936 | 3.3119 | 3.1872 | 7.4679 | 5.3743 | 16.2771 | 18.3706 | 25.8385 | 31.2128
6.6207 | 8.1345 | 2.0207 | 2.031 | 3.1035 | 3.0621 | 7.1552 | 5.1241 | 14.7552 | 16.7863 | 23.9415 | 29.0656
15.6319 | 10.0869 | 2.3211 | 2.4816 | 4.6053 | 3.9632 | 9.408 | 6.9264 | 25.7188 | 28.2004 | 37.6084 | 44.5348
12.4075 | 9.3883 | 2.2136 | 2.3204 | 4.0679 | 3.6408 | 8.6019 | 6.2815 | 21.7958 | 24.1162 | 32.7181 | 38.9996
3.1852 | 7.3901 | 1.9062 | 1.8593 | 2.5309 | 2.7185 | 6.2963 | 4.437 | 10.5753 | 12.4346 | 18.7309 | 23.168
8.0258 | 8.4389 | 2.0675 | 2.1013 | 3.3376 | 3.2026 | 7.5065 | 5.4052 | 16.4648 | 18.5661 | 26.0725 | 31.4777
-1.6375 | 6.3452 | 1.7454 | 1.6181 | 1.7271 | 2.2363 | 5.0906 | 3.4725 | 4.7078 | 6.3259 | 11.4165 | 14.889
3.3169 | 7.4187 | 1.9106 | 1.8658 | 2.5528 | 2.7317 | 6.3292 | 4.4634 | 10.7355 | 12.6014 | 18.9306 | 23.394
-1.316 | 6.4149 | 1.7561 | 1.6342 | 1.7807 | 2.2684 | 5.171 | 3.5368 | 5.0988 | 6.733 | 11.904 | 15.4408
7.4915 | 8.3232 | 2.0497 | 2.0746 | 3.2486 | 3.1491 | 7.3729 | 5.2983 | 15.8146 | 17.8892 | 25.2621 | 30.5603
1.1213 | 6.943 | 1.8374 | 1.7561 | 2.1869 | 2.5121 | 5.7803 | 4.0243 | 8.0643 | 9.8204 | 15.6007 | 19.625
-0.19129 | 6.6586 | 1.7936 | 1.6904 | 1.9681 | 2.3809 | 5.4522 | 3.7617 | 6.4673 | 8.1577 | 13.6099 | 17.3716
14.9327 | 9.9354 | 2.2978 | 2.4466 | 4.4888 | 3.8933 | 9.2332 | 6.7865 | 24.8681 | 27.3147 | 36.5479 | 43.3344
6.5945 | 8.1288 | 2.0198 | 2.0297 | 3.0991 | 3.0594 | 7.1486 | 5.1189 | 14.7233 | 16.753 | 23.9016 | 29.0205
9.6841 | 8.7982 | 2.1228 | 2.1842 | 3.614 | 3.3684 | 7.921 | 5.7368 | 18.4823 | 20.6665 | 28.5875 | 34.3244
10.8748 | 9.0562 | 2.1625 | 2.2437 | 3.8125 | 3.4875 | 8.2187 | 5.975 | 19.931 | 22.1747 | 30.3934 | 36.3684
9.5191 | 8.7625 | 2.1173 | 2.176 | 3.5865 | 3.3519 | 7.8798 | 5.7038 | 18.2816 | 20.4576 | 28.3373 | 34.0412
11.791 | 9.2547 | 2.193 | 2.2896 | 3.9652 | 3.5791 | 8.4478 | 6.1582 | 21.0458 | 23.3353 | 31.7831 | 37.9413
4.0406 | 7.5755 | 1.9347 | 1.902 | 2.6734 | 2.8041 | 6.5101 | 4.6081 | 11.6161 | 13.5181 | 20.0282 | 24.6364
0.16694 | 6.7362 | 1.8056 | 1.7083 | 2.0278 | 2.4167 | 5.5417 | 3.8334 | 6.9031 | 8.6115 | 14.1532 | 17.9866
1.7732 | 7.0842 | 1.8591 | 1.7887 | 2.2955 | 2.5773 | 5.9433 | 4.1546 | 8.8574 | 10.6461 | 16.5894 | 20.7441
2.946 | 7.3383 | 1.8982 | 1.8473 | 2.491 | 2.6946 | 6.2365 | 4.3892 | 10.2843 | 12.1316 | 18.3681 | 22.7573
5.1699 | 7.8202 | 1.9723 | 1.9585 | 2.8617 | 2.917 | 6.7925 | 4.834 | 12.9901 | 14.9486 | 21.7411 | 26.5751
12.1677 | 9.3363 | 2.2056 | 2.3084 | 4.0279 | 3.6168 | 8.5419 | 6.2335 | 21.504 | 23.8124 | 32.3543 | 38.5878
6.5433 | 8.1177 | 2.0181 | 2.0272 | 3.0906 | 3.0543 | 7.1358 | 5.1087 | 14.661 | 16.6882 | 23.824 | 28.9327
11.7076 | 9.2366 | 2.1903 | 2.2854 | 3.9513 | 3.5708 | 8.4269 | 6.1415 | 20.9442 | 23.2296 | 31.6565 | 37.798
5.373 | 7.8641 | 1.9791 | 1.9686 | 2.8955 | 2.9373 | 6.8432 | 4.8746 | 13.2371 | 15.2058 | 22.049 | 26.9236
-2.6906 | 6.117 | 1.7103 | 1.5655 | 1.5516 | 2.1309 | 4.8273 | 3.2619 | 3.4264 | 4.9919 | 9.8193 | 13.0811
5.7733 | 7.9509 | 1.9924 | 1.9887 | 2.9622 | 2.9773 | 6.9433 | 4.9547 | 13.7242 | 15.7128 | 22.6561 | 27.6108
1.0347 | 6.9242 | 1.8345 | 1.7517 | 2.1724 | 2.5035 | 5.7587 | 4.0069 | 7.9588 | 9.7106 | 15.4693 | 19.4762
17.9452 | 10.5881 | 2.3982 | 2.5973 | 4.9909 | 4.1945 | 9.9863 | 7.389 | 28.5333 | 31.1306 | 41.1169 | 48.5059
2.4162 | 7.2235 | 1.8805 | 1.8208 | 2.4027 | 2.6416 | 6.104 | 4.2832 | 9.6397 | 11.4605 | 17.5645 | 21.8477
5.5634 | 7.9054 | 1.9854 | 1.9782 | 2.9272 | 2.9563 | 6.8909 | 4.9127 | 13.4688 | 15.447 | 22.3378 | 27.2505
-4.3193 | 5.7641 | 1.656 | 1.484 | 1.2801 | 1.9681 | 4.4202 | 2.9361 | 1.4448 | 2.9288 | 7.349 | 10.2851
-1.7225 | 6.3268 | 1.7426 | 1.6139 | 1.7129 | 2.2278 | 5.0694 | 3.4555 | 4.6043 | 6.2182 | 11.2876 | 14.7431
5.3795 | 7.8656 | 1.9793 | 1.969 | 2.8966 | 2.9379 | 6.8449 | 4.8759 | 13.245 | 15.214 | 22.0589 | 26.9348
2.8529 | 7.3181 | 1.8951 | 1.8426 | 2.4755 | 2.6853 | 6.2132 | 4.3706 | 10.171 | 12.0137 | 18.2269 | 22.5975
4.9315 | 7.7685 | 1.9644 | 1.9466 | 2.8219 | 2.8931 | 6.7329 | 4.7863 | 12.6999 | 14.6465 | 21.3794 | 26.1657
8.9348 | 8.6359 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7337 | 5.587 | 17.5707 | 19.7175 | 27.4512 | 33.0382
18.576 | 10.7248 | 2.4192 | 2.6288 | 5.096 | 4.2576 | 10.144 | 7.5152 | 29.3008 | 31.9296 | 42.0736 | 49.5888
10.8329 | 9.0471 | 2.1611 | 2.2416 | 3.8055 | 3.4833 | 8.2082 | 5.9666 | 19.88 | 22.1217 | 30.3299 | 36.2965
20.2137 | 11.0796 | 2.4738 | 2.7107 | 5.3689 | 4.4214 | 10.5534 | 7.8427 | 31.2933 | 34.004 | 44.5574 | 52.4001
-2.0597 | 6.2537 | 1.7313 | 1.597 | 1.6567 | 2.194 | 4.9851 | 3.3881 | 4.1941 | 5.7911 | 10.7762 | 14.1642
10.1219 | 8.8931 | 2.1374 | 2.2061 | 3.687 | 3.4122 | 8.0305 | 5.8244 | 19.015 | 21.2211 | 29.2516 | 35.0759
9.1303 | 8.6782 | 2.1043 | 2.1565 | 3.5217 | 3.313 | 7.7826 | 5.6261 | 17.8085 | 19.965 | 27.7476 | 33.3737
1.075 | 6.9329 | 1.8358 | 1.7537 | 2.1792 | 2.5075 | 5.7687 | 4.015 | 8.0079 | 9.7616 | 15.5304 | 19.5454
-4.9896 | 5.6189 | 1.6337 | 1.4505 | 1.1684 | 1.901 | 4.2526 | 2.8021 | 0.62936 | 2.0799 | 6.3325 | 9.1346
-0.62885 | 6.5637 | 1.779 | 1.6686 | 1.8952 | 2.3371 | 5.3428 | 3.6742 | 5.9349 | 7.6035 | 12.9462 | 16.6205
7.2339 | 8.2674 | 2.0411 | 2.0617 | 3.2057 | 3.1234 | 7.3085 | 5.2468 | 15.5013 | 17.563 | 24.8715 | 30.1183
10.4833 | 8.9714 | 2.1494 | 2.2242 | 3.7472 | 3.4483 | 8.1208 | 5.8967 | 19.4547 | 21.6788 | 29.7997 | 35.6963
17.6691 | 10.5283 | 2.389 | 2.5835 | 4.9448 | 4.1669 | 9.9173 | 7.3338 | 28.1974 | 30.7808 | 40.6981 | 48.0319
10.1095 | 8.8904 | 2.137 | 2.2055 | 3.6849 | 3.4109 | 8.0274 | 5.8219 | 18.9999 | 21.2053 | 29.2327 | 35.0546
9.4732 | 8.7525 | 2.1158 | 2.1737 | 3.5789 | 3.3473 | 7.8683 | 5.6946 | 18.2258 | 20.3994 | 28.2677 | 33.9624
6.8688 | 8.1882 | 2.029 | 2.0434 | 3.1448 | 3.0869 | 7.2172 | 5.1738 | 15.057 | 17.1005 | 24.3177 | 29.4914
-7.7712 | 5.0162 | 1.541 | 1.3114 | 0.7048 | 1.6229 | 3.5572 | 2.2458 | -2.755 | -1.4435 | 2.1137 | 4.3594
6.6159 | 8.1335 | 2.0205 | 2.0308 | 3.1027 | 3.0616 | 7.154 | 5.1232 | 14.7494 | 16.7802 | 23.9342 | 29.0574
7.7482 | 8.3788 | 2.0583 | 2.0874 | 3.2914 | 3.1748 | 7.437 | 5.3496 | 16.127 | 18.2144 | 25.6514 | 31.0011
11.3824 | 9.1662 | 2.1794 | 2.2691 | 3.8971 | 3.5382 | 8.3456 | 6.0765 | 20.5485 | 22.8177 | 31.1632 | 37.2397
3.369 | 7.4299 | 1.9123 | 1.8684 | 2.5615 | 2.7369 | 6.3422 | 4.4738 | 10.7989 | 12.6674 | 19.0096 | 23.4834
12.951 | 9.506 | 2.2317 | 2.3475 | 4.1585 | 3.6951 | 8.7377 | 6.3902 | 22.457 | 24.8046 | 33.5423 | 39.9325
0.55287 | 6.8198 | 1.8184 | 1.7276 | 2.0921 | 2.4553 | 5.6382 | 3.9106 | 7.3727 | 9.1003 | 14.7385 | 18.6491
5.8476 | 7.967 | 1.9949 | 1.9924 | 2.9746 | 2.9848 | 6.9619 | 4.9695 | 13.8146 | 15.807 | 22.7689 | 27.7384
1.2162 | 6.9635 | 1.8405 | 1.7608 | 2.2027 | 2.5216 | 5.8041 | 4.0432 | 8.1798 | 9.9406 | 15.7446 | 19.7879
12.2562 | 9.3555 | 2.2085 | 2.3128 | 4.0427 | 3.6256 | 8.564 | 6.2512 | 21.6117 | 23.9245 | 32.4885 | 38.7398
4.5273 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7055 | 12.2082 | 14.1346 | 20.7664 | 25.4718
-1.3747 | 6.4021 | 1.7542 | 1.6313 | 1.7709 | 2.2625 | 5.1563 | 3.5251 | 5.0275 | 6.6587 | 11.815 | 15.3401
7.568 | 8.3397 | 2.0523 | 2.0784 | 3.2613 | 3.1568 | 7.392 | 5.3136 | 15.9077 | 17.9861 | 25.3781 | 30.6917
17.8346 | 10.5642 | 2.3945 | 2.5917 | 4.9724 | 4.1835 | 9.9586 | 7.3669 | 28.3987 | 30.9905 | 40.9491 | 48.316
14.6358 | 9.8711 | 2.2879 | 2.4318 | 4.4393 | 3.8636 | 9.159 | 6.7272 | 24.5069 | 26.9387 | 36.0977 | 42.8248
14.7192 | 9.8892 | 2.2906 | 2.436 | 4.4532 | 3.8719 | 9.1798 | 6.7438 | 24.6084 | 27.0443 | 36.2241 | 42.968
8.6596 | 8.5763 | 2.0887 | 2.133 | 3.4433 | 3.266 | 7.6649 | 5.5319 | 17.2359 | 19.3689 | 27.0338 | 32.5657
-0.8912 | 6.5069 | 1.7703 | 1.6554 | 1.8515 | 2.3109 | 5.2772 | 3.6218 | 5.6157 | 7.2712 | 12.5484 | 16.1701
0.11658 | 6.7253 | 1.8039 | 1.7058 | 2.0194 | 2.4117 | 5.5291 | 3.8233 | 6.8418 | 8.5477 | 14.0768 | 17.9001
2.9789 | 7.3454 | 1.8993 | 1.8489 | 2.4965 | 2.6979 | 6.2447 | 4.3958 | 10.3243 | 12.1733 | 18.418 | 22.8138
10.7182 | 9.0223 | 2.1573 | 2.2359 | 3.7864 | 3.4718 | 8.1796 | 5.9436 | 19.7405 | 21.9764 | 30.156 | 36.0997
8.2018 | 8.4771 | 2.0734 | 2.1101 | 3.367 | 3.2202 | 7.5505 | 5.4404 | 16.6789 | 18.789 | 26.3395 | 31.7798
14.9186 | 9.9324 | 2.2973 | 2.4459 | 4.4864 | 3.8919 | 9.2296 | 6.7837 | 24.8509 | 27.2969 | 36.5265 | 43.3102
3.278 | 7.4102 | 1.9093 | 1.8639 | 2.5463 | 2.7278 | 6.3195 | 4.4556 | 10.6882 | 12.5521 | 18.8716 | 23.3272
11.9059 | 9.2796 | 2.1969 | 2.2953 | 3.9843 | 3.5906 | 8.4765 | 6.1812 | 21.1855 | 23.4808 | 31.9572 | 38.1384
0.21186 | 6.7459 | 1.8071 | 1.7106 | 2.0353 | 2.4212 | 5.553 | 3.8424 | 6.9578 | 8.6684 | 14.2213 | 18.0637
8.3077 | 8.5 | 2.0769 | 2.1154 | 3.3846 | 3.2308 | 7.5769 | 5.4615 | 16.8077 | 18.9231 | 26.5001 | 31.9616
0.99521 | 6.9156 | 1.8332 | 1.7498 | 2.1659 | 2.4995 | 5.7488 | 3.999 | 7.9108 | 9.6606 | 15.4094 | 19.4084
10.022 | 8.8714 | 2.1341 | 2.2011 | 3.6703 | 3.4022 | 8.0055 | 5.8044 | 18.8934 | 21.0945 | 29.1 | 34.9045
-5.1718 | 5.5794 | 1.6276 | 1.4414 | 1.138 | 1.8828 | 4.207 | 2.7656 | 0.4076 | 1.849 | 6.0561 | 8.8217
-1.0844 | 6.465 | 1.7639 | 1.6458 | 1.8193 | 2.2916 | 5.2289 | 3.5831 | 5.3806 | 7.0264 | 12.2553 | 15.8384
6.9795 | 8.2122 | 2.0326 | 2.049 | 3.1632 | 3.0979 | 7.2449 | 5.1959 | 15.1917 | 17.2407 | 24.4855 | 29.6814
1.3132 | 6.9845 | 1.8438 | 1.7657 | 2.2189 | 2.5313 | 5.8283 | 4.0626 | 8.2978 | 10.0634 | 15.8917 | 19.9544
1.3639 | 6.9955 | 1.8455 | 1.7682 | 2.2273 | 2.5364 | 5.841 | 4.0728 | 8.3594 | 10.1276 | 15.9686 | 20.0414
-1.4768 | 6.38 | 1.7508 | 1.6262 | 1.7539 | 2.2523 | 5.1308 | 3.5046 | 4.9032 | 6.5293 | 11.6601 | 15.1648
6.5105 | 8.1106 | 2.017 | 2.0255 | 3.0851 | 3.0511 | 7.1276 | 5.1021 | 14.6211 | 16.6466 | 23.7743 | 28.8764
2.9522 | 7.3396 | 1.8984 | 1.8476 | 2.492 | 2.6952 | 6.238 | 4.3904 | 10.2918 | 12.1394 | 18.3775 | 22.7679
6.1645 | 8.0356 | 2.0055 | 2.0082 | 3.0274 | 3.0165 | 7.0411 | 5.0329 | 14.2002 | 16.2084 | 23.2495 | 28.2824
3.115 | 7.3749 | 1.9038 | 1.8557 | 2.5192 | 2.7115 | 6.2787 | 4.423 | 10.4899 | 12.3457 | 18.6244 | 23.0474
6.4626 | 8.1002 | 2.0154 | 2.0231 | 3.0771 | 3.0463 | 7.1157 | 5.0925 | 14.5628 | 16.586 | 23.7016 | 28.7941
16.0124 | 10.1694 | 2.3337 | 2.5006 | 4.6687 | 4.0012 | 9.5031 | 7.0025 | 26.1817 | 28.6824 | 38.1855 | 45.1879
1.5673 | 7.0396 | 1.8522 | 1.7784 | 2.2612 | 2.5567 | 5.8918 | 4.1135 | 8.6068 | 10.3852 | 16.277 | 20.3904
13.5036 | 9.6258 | 2.2501 | 2.3752 | 4.2506 | 3.7504 | 8.8759 | 6.5007 | 23.1293 | 25.5045 | 34.3804 | 40.8811
0.21402 | 6.7464 | 1.8071 | 1.7107 | 2.0357 | 2.4214 | 5.5535 | 3.8428 | 6.9604 | 8.6711 | 14.2246 | 18.0674
0.14578 | 6.7316 | 1.8049 | 1.7073 | 2.0243 | 2.4146 | 5.5364 | 3.8292 | 6.8774 | 8.5847 | 14.1211 | 17.9503
6.3738 | 8.081 | 2.0125 | 2.0187 | 3.0623 | 3.0374 | 7.0935 | 5.0748 | 14.4548 | 16.4735 | 23.5669 | 28.6417
16.4514 | 10.2645 | 2.3484 | 2.5226 | 4.7419 | 4.0451 | 9.6128 | 7.0903 | 26.7158 | 29.2384 | 38.8513 | 45.9415
13.4295 | 9.6097 | 2.2477 | 2.3715 | 4.2383 | 3.743 | 8.8574 | 6.4859 | 23.0392 | 25.4107 | 34.2681 | 40.754
-7.4375 | 5.0886 | 1.5521 | 1.3281 | 0.76042 | 1.6563 | 3.6406 | 2.3125 | -2.3489 | -1.0208 | 2.6199 | 4.9324
-2.1955 | 6.2243 | 1.7268 | 1.5902 | 1.6341 | 2.1805 | 4.9511 | 3.3609 | 4.0288 | 5.6191 | 10.5702 | 13.9311
-0.86628 | 6.5123 | 1.7711 | 1.6567 | 1.8556 | 2.3134 | 5.2834 | 3.6267 | 5.646 | 7.3027 | 12.5861 | 16.2129
7.4517 | 8.3145 | 2.0484 | 2.0726 | 3.2419 | 3.1452 | 7.3629 | 5.2903 | 15.7662 | 17.8388 | 25.2017 | 30.492
-4.548 | 5.7146 | 1.6484 | 1.4726 | 1.242 | 1.9452 | 4.363 | 2.8904 | 1.1666 | 2.6392 | 7.0022 | 9.8926
10.1638 | 8.9022 | 2.1388 | 2.2082 | 3.694 | 3.4164 | 8.0409 | 5.8328 | 19.066 | 21.2741 | 29.3151 | 35.1479
7.2783 | 8.277 | 2.0426 | 2.0639 | 3.213 | 3.1278 | 7.3196 | 5.2557 | 15.5552 | 17.6191 | 24.9387 | 30.1943
1.4575 | 7.0158 | 1.8486 | 1.7729 | 2.2429 | 2.5457 | 5.8644 | 4.0915 | 8.4732 | 10.2461 | 16.1105 | 20.202
-0.57037 | 6.5764 | 1.781 | 1.6715 | 1.9049 | 2.343 | 5.3574 | 3.6859 | 6.0061 | 7.6775 | 13.0349 | 16.7209
2.3931 | 7.2185 | 1.8798 | 1.8197 | 2.3989 | 2.6393 | 6.0983 | 4.2786 | 9.6116 | 11.4313 | 17.5295 | 21.8082
14.9926 | 9.9484 | 2.2998 | 2.4496 | 4.4988 | 3.8993 | 9.2481 | 6.7985 | 24.941 | 27.3906 | 36.6387 | 43.4372
5.5444 | 7.9013 | 1.9848 | 1.9772 | 2.9241 | 2.9544 | 6.8861 | 4.9089 | 13.4457 | 15.423 | 22.3091 | 27.218
13.6245 | 9.652 | 2.2542 | 2.3812 | 4.2708 | 3.7625 | 8.9061 | 6.5249 | 23.2765 | 25.6577 | 34.5638 | 41.0887
1.3803 | 6.9991 | 1.846 | 1.769 | 2.2301 | 2.538 | 5.8451 | 4.0761 | 8.3794 | 10.1484 | 15.9935 | 20.0695
9.4004 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.8501 | 5.6801 | 18.1371 | 20.3071 | 28.1572 | 33.8373
5.1169 | 7.8087 | 1.9706 | 1.9558 | 2.8528 | 2.9117 | 6.7792 | 4.8234 | 12.9255 | 14.8813 | 21.6606 | 26.4839
-0.84508 | 6.5169 | 1.7718 | 1.6577 | 1.8592 | 2.3155 | 5.2887 | 3.631 | 5.6718 | 7.3296 | 12.6183 | 16.2493
14.9278 | 9.9344 | 2.2976 | 2.4464 | 4.488 | 3.8928 | 9.232 | 6.7856 | 24.8622 | 27.3086 | 36.5405 | 43.3261
9.9078 | 8.8467 | 2.1303 | 2.1954 | 3.6513 | 3.3908 | 7.977 | 5.7816 | 18.7545 | 20.9499 | 28.9268 | 34.7084
5.1469 | 7.8152 | 1.9716 | 1.9573 | 2.8578 | 2.9147 | 6.7867 | 4.8294 | 12.962 | 14.9194 | 21.7061 | 26.5355
3.5807 | 7.4758 | 1.9194 | 1.879 | 2.5968 | 2.7581 | 6.3952 | 4.5161 | 11.0565 | 12.9355 | 19.3307 | 23.8468
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2043 | 14.1305 | 20.7616 | 25.4664
8.6671 | 8.5779 | 2.0889 | 2.1334 | 3.4445 | 3.2667 | 7.6668 | 5.5334 | 17.2449 | 19.3783 | 27.0451 | 32.5785
8.4187 | 8.5241 | 2.0806 | 2.1209 | 3.4031 | 3.2419 | 7.6047 | 5.4837 | 16.9428 | 19.0637 | 26.6684 | 32.1522
-9.9815 | 4.5373 | 1.4673 | 1.2009 | 0.33642 | 1.4019 | 3.0046 | 1.8037 | -5.4442 | -4.2432 | -1.2386 | 0.5651
17.7361 | 10.5428 | 2.3912 | 2.5868 | 4.956 | 4.1736 | 9.934 | 7.3472 | 28.2789 | 30.8657 | 40.7997 | 48.1469
14.6958 | 9.8841 | 2.2899 | 2.4348 | 4.4493 | 3.8696 | 9.174 | 6.7392 | 24.5799 | 27.0147 | 36.1887 | 42.9279
6.9703 | 8.2102 | 2.0323 | 2.0485 | 3.1617 | 3.097 | 7.2426 | 5.1941 | 15.1805 | 17.229 | 24.4716 | 29.6656
-2.7649 | 6.1009 | 1.7078 | 1.5618 | 1.5392 | 2.1235 | 4.8088 | 3.247 | 3.336 | 4.8978 | 9.7066 | 12.9536
8.3695 | 8.5134 | 2.079 | 2.1185 | 3.3949 | 3.2369 | 7.5924 | 5.4739 | 16.8829 | 19.0014 | 26.5937 | 32.0676
0.31258 | 6.7677 | 1.8104 | 1.7156 | 2.0521 | 2.4313 | 5.5781 | 3.8625 | 7.0803 | 8.7959 | 14.3741 | 18.2366
14.0166 | 9.7369 | 2.2672 | 2.4008 | 4.3361 | 3.8017 | 9.0041 | 6.6033 | 23.7535 | 26.1543 | 35.1584 | 41.7618
7.5685 | 8.3398 | 2.0523 | 2.0784 | 3.2614 | 3.1568 | 7.3921 | 5.3137 | 15.9083 | 17.9867 | 25.3788 | 30.6925
5.9811 | 7.9959 | 1.9994 | 1.9991 | 2.9968 | 2.9981 | 6.9953 | 4.9962 | 13.977 | 15.976 | 22.9713 | 27.9675
3.3981 | 7.4363 | 1.9133 | 1.8699 | 2.5664 | 2.7398 | 6.3495 | 4.4796 | 10.8344 | 12.7043 | 19.0538 | 23.5335
6.2917 | 8.0632 | 2.0097 | 2.0146 | 3.0486 | 3.0292 | 7.0729 | 5.0583 | 14.3549 | 16.3695 | 23.4424 | 28.5007
3.5617 | 7.4717 | 1.9187 | 1.8781 | 2.5936 | 2.7562 | 6.3904 | 4.5123 | 11.0334 | 12.9115 | 19.3019 | 23.8143
13.4989 | 9.6248 | 2.25 | 2.3749 | 4.2498 | 3.7499 | 8.8747 | 6.4998 | 23.1236 | 25.4986 | 34.3733 | 40.8731
10.3918 | 8.9516 | 2.1464 | 2.2196 | 3.732 | 3.4392 | 8.098 | 5.8784 | 19.3434 | 21.563 | 29.6609 | 35.5393
1.0548 | 6.9285 | 1.8352 | 1.7527 | 2.1758 | 2.5055 | 5.7637 | 4.011 | 7.9833 | 9.7361 | 15.4998 | 19.5107
16.2026 | 10.2106 | 2.3401 | 2.5101 | 4.7004 | 4.0203 | 9.5506 | 7.0405 | 26.4131 | 28.9233 | 38.4739 | 45.5144
8.5304 | 8.5483 | 2.0843 | 2.1265 | 3.4217 | 3.253 | 7.6326 | 5.5061 | 17.0786 | 19.2052 | 26.8378 | 32.3438
7.3385 | 8.29 | 2.0446 | 2.0669 | 3.2231 | 3.1339 | 7.3346 | 5.2677 | 15.6285 | 17.6955 | 25.0301 | 30.2978
-11.3977 | 4.2305 | 1.4201 | 1.1301 | 0.10039 | 1.2602 | 2.6506 | 1.5205 | -7.1672 | -6.0371 | -3.3865 | -1.866
4.3995 | 7.6532 | 1.9466 | 1.92 | 2.7332 | 2.8399 | 6.5999 | 4.6799 | 12.0527 | 13.9727 | 20.5726 | 25.2525
14.4103 | 9.8222 | 2.2803 | 2.4205 | 4.4017 | 3.841 | 9.1026 | 6.6821 | 24.2325 | 26.6531 | 35.7556 | 42.4377
-4.8914 | 5.6402 | 1.637 | 1.4554 | 1.1848 | 1.9109 | 4.2771 | 2.8217 | 0.74876 | 2.2042 | 6.4813 | 9.3031
15.1442 | 9.9812 | 2.3048 | 2.4572 | 4.524 | 3.9144 | 9.2861 | 6.8288 | 25.1255 | 27.5827 | 36.8687 | 43.6976
6.8025 | 8.1739 | 2.0267 | 2.0401 | 3.1337 | 3.0802 | 7.2006 | 5.1605 | 14.9763 | 17.0165 | 24.2171 | 29.3776
7.5565 | 8.3372 | 2.0519 | 2.0778 | 3.2594 | 3.1556 | 7.3891 | 5.3113 | 15.8937 | 17.9716 | 25.3607 | 30.672
7.1078 | 8.24 | 2.0369 | 2.0554 | 3.1846 | 3.1108 | 7.2769 | 5.2216 | 15.3478 | 17.4032 | 24.6802 | 29.9017
5.4872 | 7.8889 | 1.9829 | 1.9744 | 2.9145 | 2.9487 | 6.8718 | 4.8974 | 13.3761 | 15.3505 | 22.2223 | 27.1197
-0.20801 | 6.6549 | 1.7931 | 1.6896 | 1.9653 | 2.3792 | 5.448 | 3.7584 | 6.4469 | 8.1365 | 13.5845 | 17.3429
17.5186 | 10.4957 | 2.384 | 2.5759 | 4.9198 | 4.1519 | 9.8796 | 7.3037 | 28.0143 | 30.5902 | 40.4698 | 47.7735
10.1071 | 8.8899 | 2.1369 | 2.2054 | 3.6845 | 3.4107 | 8.0268 | 5.8214 | 18.997 | 21.2024 | 29.2292 | 35.0506
8.5568 | 8.554 | 2.0852 | 2.1278 | 3.4261 | 3.2557 | 7.6392 | 5.5114 | 17.1107 | 19.2386 | 26.8777 | 32.3891
6.2378 | 8.0515 | 2.0079 | 2.0119 | 3.0396 | 3.0238 | 7.0594 | 5.0476 | 14.2893 | 16.3012 | 23.3606 | 28.4082
-0.17002 | 6.6632 | 1.7943 | 1.6915 | 1.9717 | 2.383 | 5.4575 | 3.766 | 6.4931 | 8.1846 | 13.6421 | 17.4081
14.1065 | 9.7564 | 2.2702 | 2.4053 | 4.3511 | 3.8106 | 9.0266 | 6.6213 | 23.8629 | 26.2682 | 35.2948 | 41.9161
3.8564 | 7.5356 | 1.9285 | 1.8928 | 2.6427 | 2.7856 | 6.4641 | 4.5713 | 11.392 | 13.2848 | 19.7489 | 24.3202
-3.938 | 5.8468 | 1.6687 | 1.5031 | 1.3437 | 2.0062 | 4.5155 | 3.0124 | 1.9088 | 3.4119 | 7.9273 | 10.9397
8.0713 | 8.4488 | 2.069 | 2.1036 | 3.3452 | 3.2071 | 7.5178 | 5.4143 | 16.5201 | 18.6237 | 26.1415 | 31.5558
-3.3537 | 5.9734 | 1.6882 | 1.5323 | 1.4411 | 2.0646 | 4.6616 | 3.1293 | 2.6197 | 4.152 | 8.8136 | 11.9428
-2.1228 | 6.2401 | 1.7292 | 1.5939 | 1.6462 | 2.1877 | 4.9693 | 3.3754 | 4.1173 | 5.7111 | 10.6804 | 14.0558
3.4464 | 7.4467 | 1.9149 | 1.8723 | 2.5744 | 2.7446 | 6.3616 | 4.4893 | 10.8932 | 12.7655 | 19.1271 | 23.6164
9.7406 | 8.8105 | 2.1247 | 2.187 | 3.6234 | 3.3741 | 7.9351 | 5.7481 | 18.551 | 20.7381 | 28.6732 | 34.4213
14.3409 | 9.8072 | 2.278 | 2.417 | 4.3902 | 3.8341 | 9.0852 | 6.6682 | 24.1481 | 26.5652 | 35.6504 | 42.3186
10.4801 | 8.9707 | 2.1493 | 2.224 | 3.7467 | 3.448 | 8.12 | 5.896 | 19.4508 | 21.6748 | 29.7948 | 35.6908
1.9422 | 7.1208 | 1.8647 | 1.7971 | 2.3237 | 2.5942 | 5.9855 | 4.1884 | 9.063 | 10.8601 | 16.8456 | 21.0341
-3.5251 | 5.9362 | 1.6825 | 1.5237 | 1.4125 | 2.0475 | 4.6187 | 3.095 | 2.4111 | 3.9349 | 8.5536 | 11.6486
6.3941 | 8.0854 | 2.0131 | 2.0197 | 3.0657 | 3.0394 | 7.0985 | 5.0788 | 14.4795 | 16.4992 | 23.5978 | 28.6766
8.1827 | 8.4729 | 2.0728 | 2.1091 | 3.3638 | 3.2183 | 7.5457 | 5.4365 | 16.6556 | 18.7647 | 26.3104 | 31.7469
13.4254 | 9.6088 | 2.2475 | 2.3713 | 4.2376 | 3.7425 | 8.8563 | 6.4851 | 23.0342 | 25.4055 | 34.2618 | 40.7469
12.781 | 9.4692 | 2.226 | 2.339 | 4.1302 | 3.6781 | 8.6952 | 6.3562 | 22.2502 | 24.5892 | 33.2844 | 39.6406
5.32 | 7.8527 | 1.9773 | 1.966 | 2.8867 | 2.932 | 6.83 | 4.864 | 13.1726 | 15.1386 | 21.9686 | 26.8326
0.36357 | 6.7788 | 1.8121 | 1.7182 | 2.0606 | 2.4364 | 5.5909 | 3.8727 | 7.1423 | 8.8605 | 14.4514 | 18.3241
4.4875 | 7.6723 | 1.9496 | 1.9244 | 2.7479 | 2.8487 | 6.6219 | 4.6975 | 12.1597 | 14.0841 | 20.706 | 25.4035
16.3134 | 10.2346 | 2.3438 | 2.5157 | 4.7189 | 4.0313 | 9.5783 | 7.0627 | 26.548 | 29.0636 | 38.642 | 45.7047
4.2492 | 7.6207 | 1.9416 | 1.9125 | 2.7082 | 2.8249 | 6.5623 | 4.6498 | 11.8698 | 13.7823 | 20.3446 | 24.9944
3.7637 | 7.5155 | 1.9255 | 1.8882 | 2.6273 | 2.7764 | 6.4409 | 4.5527 | 11.2792 | 13.1674 | 19.6083 | 24.161
-1.4859 | 6.3781 | 1.7505 | 1.6257 | 1.7524 | 2.2514 | 5.1285 | 3.5028 | 4.8922 | 6.5179 | 11.6464 | 15.1492
13.1201 | 9.5427 | 2.2373 | 2.356 | 4.1867 | 3.712 | 8.78 | 6.424 | 22.6628 | 25.0188 | 33.7988 | 40.2228
1.2847 | 6.9783 | 1.8428 | 1.7642 | 2.2141 | 2.5285 | 5.8212 | 4.0569 | 8.263 | 10.0273 | 15.8484 | 19.9054
10.1324 | 8.8954 | 2.1377 | 2.2066 | 3.6887 | 3.4132 | 8.0331 | 5.8265 | 19.0278 | 21.2344 | 29.2675 | 35.094
19.078 | 10.8336 | 2.4359 | 2.6539 | 5.1797 | 4.3078 | 10.2695 | 7.6156 | 29.9115 | 32.5654 | 42.8349 | 50.4505
14.4903 | 9.8396 | 2.283 | 2.4245 | 4.4151 | 3.849 | 9.1226 | 6.6981 | 24.3299 | 26.7544 | 35.877 | 42.5751
1.3037 | 6.9825 | 1.8435 | 1.7652 | 2.2173 | 2.5304 | 5.8259 | 4.0607 | 8.2862 | 10.0514 | 15.8773 | 19.9381
4.5343 | 7.6824 | 1.9511 | 1.9267 | 2.7557 | 2.8534 | 6.6336 | 4.7069 | 12.2167 | 14.1434 | 20.777 | 25.4838
8.9171 | 8.632 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5834 | 17.5492 | 19.695 | 27.4243 | 33.0077
4.2696 | 7.6251 | 1.9423 | 1.9135 | 2.7116 | 2.827 | 6.5674 | 4.6539 | 11.8947 | 13.8082 | 20.3756 | 25.0295
1.8769 | 7.1067 | 1.8626 | 1.7938 | 2.3128 | 2.5877 | 5.9692 | 4.1754 | 8.9835 | 10.7774 | 16.7466 | 20.922
1.2769 | 6.9767 | 1.8426 | 1.7638 | 2.2128 | 2.5277 | 5.8192 | 4.0554 | 8.2536 | 10.0174 | 15.8367 | 19.8921
4.4293 | 7.6597 | 1.9476 | 1.9215 | 2.7382 | 2.8429 | 6.6073 | 4.6859 | 12.089 | 14.0105 | 20.6178 | 25.3037
-0.71252 | 6.5456 | 1.7762 | 1.6644 | 1.8812 | 2.3287 | 5.3219 | 3.6575 | 5.8331 | 7.4975 | 12.8193 | 16.4768
0.56209 | 6.8218 | 1.8187 | 1.7281 | 2.0937 | 2.4562 | 5.6405 | 3.9124 | 7.3839 | 9.112 | 14.7525 | 18.6649
3.2537 | 7.405 | 1.9085 | 1.8627 | 2.5423 | 2.7254 | 6.3134 | 4.4507 | 10.6587 | 12.5214 | 18.8348 | 23.2856
4.564 | 7.6889 | 1.9521 | 1.9282 | 2.7607 | 2.8564 | 6.641 | 4.7128 | 12.2529 | 14.1811 | 20.8221 | 25.5349
17.5236 | 10.4968 | 2.3841 | 2.5762 | 4.9206 | 4.1524 | 9.8809 | 7.3047 | 28.0204 | 30.5966 | 40.4775 | 47.7823
8.2391 | 8.4851 | 2.0746 | 2.112 | 3.3732 | 3.2239 | 7.5598 | 5.4478 | 16.7242 | 18.8362 | 26.396 | 31.8438
11.3647 | 9.1623 | 2.1788 | 2.2682 | 3.8941 | 3.5365 | 8.3412 | 6.0729 | 20.527 | 22.7953 | 31.1364 | 37.2094
-1.6549 | 6.3414 | 1.7448 | 1.6173 | 1.7242 | 2.2345 | 5.0863 | 3.469 | 4.6866 | 6.3038 | 11.3901 | 14.8591
8.9418 | 8.6374 | 2.0981 | 2.1471 | 3.4903 | 3.2942 | 7.7354 | 5.5884 | 17.5791 | 19.7262 | 27.4617 | 33.05
11.8561 | 9.2688 | 2.1952 | 2.2928 | 3.976 | 3.5856 | 8.464 | 6.1712 | 21.1249 | 23.4177 | 31.8817 | 38.053
10.4949 | 8.9739 | 2.1498 | 2.2247 | 3.7492 | 3.4495 | 8.1237 | 5.899 | 19.4688 | 21.6936 | 29.8173 | 35.7163
10.916 | 9.0651 | 2.1639 | 2.2458 | 3.8193 | 3.4916 | 8.229 | 5.9832 | 19.9811 | 22.2269 | 30.4559 | 36.4391
9.4413 | 8.7456 | 2.1147 | 2.1721 | 3.5736 | 3.3441 | 7.8603 | 5.6883 | 18.1869 | 20.359 | 28.2193 | 33.9076
3.8479 | 7.5337 | 1.9283 | 1.8924 | 2.6413 | 2.7848 | 6.462 | 4.5696 | 11.3817 | 13.2741 | 19.7361 | 24.3056
0.12473 | 6.727 | 1.8042 | 1.7062 | 2.0208 | 2.4125 | 5.5312 | 3.8249 | 6.8518 | 8.558 | 14.0892 | 17.9141
15.3826 | 10.0329 | 2.3128 | 2.4691 | 4.5638 | 3.9383 | 9.3457 | 6.8765 | 25.4155 | 27.8847 | 37.2303 | 44.1068
5.5747 | 7.9078 | 1.9858 | 1.9787 | 2.9291 | 2.9575 | 6.8937 | 4.9149 | 13.4825 | 15.4613 | 22.3549 | 27.2699
7.5314 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8632 | 17.9398 | 25.3227 | 30.629
5.6536 | 7.9249 | 1.9885 | 1.9827 | 2.9423 | 2.9654 | 6.9134 | 4.9307 | 13.5786 | 15.5612 | 22.4746 | 27.4054
7.9005 | 8.4118 | 2.0633 | 2.095 | 3.3167 | 3.19 | 7.4751 | 5.3801 | 16.3122 | 18.4073 | 25.8824 | 31.2625
2.7503 | 7.2959 | 1.8917 | 1.8375 | 2.4584 | 2.675 | 6.1876 | 4.3501 | 10.0462 | 11.8837 | 18.0713 | 22.4213
15.9912 | 10.1648 | 2.333 | 2.4996 | 4.6652 | 3.9991 | 9.4978 | 6.9982 | 26.156 | 28.6556 | 38.1534 | 45.1516
3.5741 | 7.4744 | 1.9191 | 1.8787 | 2.5957 | 2.7574 | 6.3935 | 4.5148 | 11.0485 | 12.9272 | 19.3207 | 23.8356
8.2161 | 8.4802 | 2.0739 | 2.1108 | 3.3693 | 3.2216 | 7.554 | 5.4432 | 16.6962 | 18.8071 | 26.3611 | 31.8043
11.5303 | 9.1982 | 2.1843 | 2.2765 | 3.9217 | 3.553 | 8.3826 | 6.1061 | 20.7286 | 23.0051 | 31.3877 | 37.4937
9.1597 | 8.6846 | 2.1053 | 2.158 | 3.5266 | 3.316 | 7.7899 | 5.6319 | 17.8443 | 20.0023 | 27.7923 | 33.4242
12.984 | 9.5132 | 2.2328 | 2.3492 | 4.164 | 3.6984 | 8.746 | 6.3968 | 22.4972 | 24.8464 | 33.5924 | 39.9892
18.7844 | 10.7699 | 2.4261 | 2.6392 | 5.1307 | 4.2784 | 10.1961 | 7.5569 | 29.5543 | 32.1935 | 42.3896 | 49.9465
9.9286 | 8.8512 | 2.131 | 2.1964 | 3.6548 | 3.3929 | 7.9822 | 5.7857 | 18.7799 | 20.9763 | 28.9585 | 34.7442
2.0856 | 7.1519 | 1.8695 | 1.8043 | 2.3476 | 2.6086 | 6.0214 | 4.2171 | 9.2375 | 11.0418 | 17.0632 | 21.2803
7.7123 | 8.371 | 2.0571 | 2.0856 | 3.2854 | 3.1712 | 7.4281 | 5.3425 | 16.0833 | 18.169 | 25.5971 | 30.9395
4.3418 | 7.6407 | 1.9447 | 1.9171 | 2.7236 | 2.8342 | 6.5855 | 4.6684 | 11.9825 | 13.8996 | 20.4851 | 25.1535
11.026 | 9.089 | 2.1675 | 2.2513 | 3.8377 | 3.5026 | 8.2565 | 6.0052 | 20.115 | 22.3663 | 30.6228 | 36.628
17.0012 | 10.3836 | 2.3667 | 2.5501 | 4.8335 | 4.1001 | 9.7503 | 7.2002 | 27.3849 | 29.9349 | 39.6852 | 46.8855
2.8353 | 7.3143 | 1.8945 | 1.8418 | 2.4726 | 2.6835 | 6.2088 | 4.3671 | 10.1496 | 11.9914 | 18.2002 | 22.5673
2.9314 | 7.3351 | 1.8977 | 1.8466 | 2.4886 | 2.6931 | 6.2329 | 4.3863 | 10.2666 | 12.1132 | 18.346 | 22.7323
0.2458 | 6.7533 | 1.8082 | 1.7123 | 2.041 | 2.4246 | 5.5615 | 3.8492 | 6.9991 | 8.7114 | 14.2728 | 18.122
6.4896 | 8.1061 | 2.0163 | 2.0245 | 3.0816 | 3.049 | 7.1224 | 5.0979 | 14.5957 | 16.6202 | 23.7426 | 28.8405
-6.0201 | 5.3956 | 1.5993 | 1.399 | 0.99665 | 1.798 | 3.995 | 2.596 | -0.62448 | 0.77452 | 4.7695 | 7.3655
3.3036 | 7.4158 | 1.9101 | 1.8652 | 2.5506 | 2.7304 | 6.3259 | 4.4607 | 10.7194 | 12.5846 | 18.9105 | 23.3712
8.8664 | 8.621 | 2.0955 | 2.1433 | 3.4777 | 3.2866 | 7.7166 | 5.5733 | 17.4874 | 19.6307 | 27.3473 | 32.9206
13.6777 | 9.6635 | 2.2559 | 2.3839 | 4.2796 | 3.7678 | 8.9194 | 6.5355 | 23.3412 | 25.7251 | 34.6446 | 41.1801
7.5315 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8633 | 17.9399 | 25.3228 | 30.629
6.5002 | 8.1084 | 2.0167 | 2.025 | 3.0834 | 3.05 | 7.1251 | 5.1 | 14.6086 | 16.6336 | 23.7587 | 28.8587
12.3442 | 9.3746 | 2.2115 | 2.3172 | 4.0574 | 3.6344 | 8.586 | 6.2688 | 21.7187 | 24.036 | 32.622 | 38.8908
-2.6847 | 6.1183 | 1.7105 | 1.5658 | 1.5526 | 2.1315 | 4.8288 | 3.2631 | 3.4337 | 4.9994 | 9.8283 | 13.0913
11.3098 | 9.1505 | 2.177 | 2.2655 | 3.885 | 3.531 | 8.3274 | 6.062 | 20.4602 | 22.7257 | 31.0532 | 37.1151
11.2312 | 9.1334 | 2.1744 | 2.2616 | 3.8719 | 3.5231 | 8.3078 | 6.0462 | 20.3646 | 22.6262 | 30.934 | 36.9802
-2.2417 | 6.2143 | 1.7253 | 1.5879 | 1.6264 | 2.1758 | 4.9396 | 3.3517 | 3.9725 | 5.5605 | 10.5 | 13.8517
13.1798 | 9.5556 | 2.2393 | 2.359 | 4.1966 | 3.718 | 8.795 | 6.436 | 22.7354 | 25.0944 | 33.8894 | 40.3253
-6.0136 | 5.397 | 1.5995 | 1.3993 | 0.99773 | 1.7986 | 3.9966 | 2.5973 | -0.61658 | 0.78274 | 4.7793 | 7.3766
2.8839 | 7.3249 | 1.8961 | 1.8442 | 2.4807 | 2.6884 | 6.221 | 4.3768 | 10.2088 | 12.053 | 18.274 | 22.6508
8.9173 | 8.6321 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5835 | 17.5494 | 19.6953 | 27.4246 | 33.0081
7.3594 | 8.2945 | 2.0453 | 2.068 | 3.2266 | 3.1359 | 7.3399 | 5.2719 | 15.654 | 17.722 | 25.0618 | 30.3337
10.6967 | 9.0176 | 2.1566 | 2.2348 | 3.7828 | 3.4697 | 8.1742 | 5.9393 | 19.7143 | 21.9491 | 30.1233 | 36.0626
14.8238 | 9.9118 | 2.2941 | 2.4412 | 4.4706 | 3.8824 | 9.206 | 6.7648 | 24.7356 | 27.1768 | 36.3828 | 43.1475
11.6384 | 9.2216 | 2.1879 | 2.2819 | 3.9397 | 3.5638 | 8.4096 | 6.1277 | 20.86 | 23.1419 | 31.5515 | 37.6792
17.6788 | 10.5304 | 2.3893 | 2.5839 | 4.9465 | 4.1679 | 9.9197 | 7.3358 | 28.2092 | 30.7931 | 40.7128 | 48.0486
4.3589 | 7.6444 | 1.9453 | 1.9179 | 2.7265 | 2.8359 | 6.5897 | 4.6718 | 12.0033 | 13.9213 | 20.511 | 25.1828
0.47148 | 6.8022 | 1.8157 | 1.7236 | 2.0786 | 2.4471 | 5.6179 | 3.8943 | 7.2736 | 8.9972 | 14.6151 | 18.5094
7.8912 | 8.4097 | 2.063 | 2.0946 | 3.3152 | 3.1891 | 7.4728 | 5.3782 | 16.3009 | 18.3955 | 25.8682 | 31.2465
4.3809 | 7.6492 | 1.946 | 1.919 | 2.7301 | 2.8381 | 6.5952 | 4.6762 | 12.0301 | 13.9491 | 20.5444 | 25.2205
12.5045 | 9.4093 | 2.2168 | 2.3252 | 4.0841 | 3.6505 | 8.6261 | 6.3009 | 21.9138 | 24.2391 | 32.8652 | 39.1661
-2.5623 | 6.1448 | 1.7146 | 1.5719 | 1.5729 | 2.1438 | 4.8594 | 3.2875 | 3.5825 | 5.1544 | 10.0138 | 13.3013
5.628 | 7.9194 | 1.9876 | 1.9814 | 2.938 | 2.9628 | 6.907 | 4.9256 | 13.5474 | 15.5288 | 22.4358 | 27.3614
-2.8667 | 6.0789 | 1.7044 | 1.5567 | 1.5222 | 2.1133 | 4.7833 | 3.2267 | 3.2122 | 4.7689 | 9.5522 | 12.7789
-6.8201 | 5.2223 | 1.5727 | 1.359 | 0.86332 | 1.718 | 3.795 | 2.436 | -1.5977 | -0.23874 | 3.5562 | 5.9922
-0.06598 | 6.6857 | 1.7978 | 1.6967 | 1.989 | 2.3934 | 5.4835 | 3.7868 | 6.6197 | 8.3164 | 13.7999 | 17.5867
-4.274 | 5.774 | 1.6575 | 1.4863 | 1.2877 | 1.9726 | 4.4315 | 2.9452 | 1.4999 | 2.9862 | 7.4177 | 10.3629
9.4 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.85 | 5.68 | 18.1367 | 20.3067 | 28.1567 | 33.8367
-0.6032 | 6.5693 | 1.7799 | 1.6698 | 1.8995 | 2.3397 | 5.3492 | 3.6794 | 5.9661 | 7.6359 | 12.9851 | 16.6645
0.58262 | 6.8262 | 1.8194 | 1.7291 | 2.0971 | 2.4583 | 5.6457 | 3.9165 | 7.4089 | 9.138 | 14.7836 | 18.7002
6.9663 | 8.2094 | 2.0322 | 2.0483 | 3.161 | 3.0966 | 7.2416 | 5.1933 | 15.1756 | 17.2239 | 24.4655 | 29.6587
8.3163 | 8.5019 | 2.0772 | 2.1158 | 3.386 | 3.2316 | 7.5791 | 5.4633 | 16.8181 | 18.9339 | 26.513 | 31.9762
-4.5469 | 5.7148 | 1.6484 | 1.4727 | 1.2422 | 1.9453 | 4.3633 | 2.8906 | 1.1679 | 2.6406 | 7.0038 | 9.8944
-7.9943 | 4.9679 | 1.5335 | 1.3003 | 0.66762 | 1.6006 | 3.5014 | 2.2011 | -3.0264 | -1.7261 | 1.7753 | 3.9765
4.1948 | 7.6089 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5487 | 4.639 | 11.8036 | 13.7134 | 20.2621 | 24.901
0.29908 | 6.7648 | 1.81 | 1.715 | 2.0498 | 2.4299 | 5.5748 | 3.8598 | 7.0639 | 8.7788 | 14.3536 | 18.2134
2.5167 | 7.2453 | 1.8839 | 1.8258 | 2.4194 | 2.6517 | 6.1292 | 4.3033 | 9.762 | 11.5878 | 17.717 | 22.0203
14.5896 | 9.8611 | 2.2863 | 2.4295 | 4.4316 | 3.859 | 9.1474 | 6.7179 | 24.4507 | 26.8802 | 36.0276 | 42.7455
5.9257 | 7.9839 | 1.9975 | 1.9963 | 2.9876 | 2.9926 | 6.9814 | 4.9851 | 13.9095 | 15.9058 | 22.8872 | 27.8724
4.8036 | 7.7408 | 1.9601 | 1.9402 | 2.8006 | 2.8804 | 6.7009 | 4.7607 | 12.5443 | 14.4845 | 21.1854 | 25.9461
2.8171 | 7.3104 | 1.8939 | 1.8409 | 2.4695 | 2.6817 | 6.2043 | 4.3634 | 10.1275 | 11.9683 | 18.1726 | 22.536
7.7332 | 8.3755 | 2.0578 | 2.0867 | 3.2889 | 3.1733 | 7.4333 | 5.3466 | 16.1088 | 18.1954 | 25.6287 | 30.9754
10.7305 | 9.0249 | 2.1577 | 2.2365 | 3.7884 | 3.473 | 8.1826 | 5.9461 | 19.7554 | 21.9919 | 30.1745 | 36.1206
8.4966 | 8.5409 | 2.0832 | 2.1248 | 3.4161 | 3.2497 | 7.6242 | 5.4993 | 17.0375 | 19.1624 | 26.7865 | 32.2858
-8.2772 | 4.9066 | 1.5241 | 1.2861 | 0.62047 | 1.5723 | 3.4307 | 2.1446 | -3.3706 | -2.0844 | 1.3463 | 3.4908
8.6945 | 8.5838 | 2.0898 | 2.1347 | 3.4491 | 3.2695 | 7.6736 | 5.5389 | 17.2783 | 19.413 | 27.0867 | 32.6256
4.4416 | 7.6624 | 1.9481 | 1.9221 | 2.7403 | 2.8442 | 6.6104 | 4.6883 | 12.104 | 14.0261 | 20.6365 | 25.3248
4.5166 | 7.6786 | 1.9506 | 1.9258 | 2.7528 | 2.8517 | 6.6292 | 4.7033 | 12.1953 | 14.1211 | 20.7502 | 25.4536
7.1372 | 8.2464 | 2.0379 | 2.0569 | 3.1895 | 3.1137 | 7.2843 | 5.2274 | 15.3835 | 17.4404 | 24.7247 | 29.9521
9.3226 | 8.7199 | 2.1108 | 2.1661 | 3.5538 | 3.3323 | 7.8307 | 5.6645 | 18.0425 | 20.2087 | 28.0393 | 33.7039
1.1275 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7819 | 4.0255 | 8.0717 | 9.8281 | 15.61 | 19.6355
-2.6418 | 6.1276 | 1.7119 | 1.5679 | 1.5597 | 2.1358 | 4.8395 | 3.2716 | 3.4858 | 5.0537 | 9.8932 | 13.1649
9.0604 | 8.6631 | 2.102 | 2.153 | 3.5101 | 3.306 | 7.7651 | 5.6121 | 17.7234 | 19.8765 | 27.6415 | 33.2536
10.6866 | 9.0154 | 2.1562 | 2.2343 | 3.7811 | 3.4687 | 8.1717 | 5.9373 | 19.7021 | 21.9364 | 30.1081 | 36.0454
8.5379 | 8.5499 | 2.0846 | 2.1269 | 3.423 | 3.2538 | 7.6345 | 5.5076 | 17.0878 | 19.2146 | 26.8491 | 32.3567
1.8028 | 7.0906 | 1.8601 | 1.7901 | 2.3005 | 2.5803 | 5.9507 | 4.1606 | 8.8935 | 10.6836 | 16.6343 | 20.7949
0.2989 | 6.7648 | 1.81 | 1.7149 | 2.0498 | 2.4299 | 5.5747 | 3.8598 | 7.0637 | 8.7786 | 14.3533 | 18.2131
-0.13421 | 6.6709 | 1.7955 | 1.6933 | 1.9776 | 2.3866 | 5.4664 | 3.7732 | 6.5367 | 8.23 | 13.6965 | 17.4696
7.0264 | 8.2224 | 2.0342 | 2.0513 | 3.1711 | 3.1026 | 7.2566 | 5.2053 | 15.2488 | 17.3001 | 24.5567 | 29.762
15.9381 | 10.1533 | 2.3313 | 2.4969 | 4.6563 | 3.9938 | 9.4845 | 6.9876 | 26.0913 | 28.5883 | 38.0728 | 45.0604
4.2657 | 7.6242 | 1.9422 | 1.9133 | 2.711 | 2.8266 | 6.5664 | 4.6531 | 11.89 | 13.8033 | 20.3697 | 25.0229
-1.1135 | 6.4587 | 1.7629 | 1.6443 | 1.8144 | 2.2886 | 5.2216 | 3.5773 | 5.3452 | 6.9896 | 12.2112 | 15.7885
4.8713 | 7.7554 | 1.9624 | 1.9436 | 2.8119 | 2.8871 | 6.7178 | 4.7743 | 12.6267 | 14.5703 | 21.2881 | 26.0624
7.0446 | 8.2263 | 2.0348 | 2.0522 | 3.1741 | 3.1045 | 7.2612 | 5.2089 | 15.2709 | 17.3232 | 24.5843 | 29.7933
20.3696 | 11.1134 | 2.479 | 2.7185 | 5.3949 | 4.437 | 10.5924 | 7.8739 | 31.483 | 34.2015 | 44.7939 | 52.6678
2.9926 | 7.3484 | 1.8998 | 1.8496 | 2.4988 | 2.6993 | 6.2482 | 4.3985 | 10.341 | 12.1907 | 18.4388 | 22.8374
3.3625 | 7.4285 | 1.9121 | 1.8681 | 2.5604 | 2.7362 | 6.3406 | 4.4725 | 10.791 | 12.6591 | 18.9998 | 23.4723
2.8398 | 7.3153 | 1.8947 | 1.842 | 2.4733 | 2.684 | 6.21 | 4.368 | 10.1551 | 11.9971 | 18.207 | 22.575
8.605 | 8.5644 | 2.0868 | 2.1302 | 3.4342 | 3.2605 | 7.6512 | 5.521 | 17.1694 | 19.2996 | 26.9509 | 32.4719
8.192 | 8.4749 | 2.0731 | 2.1096 | 3.3653 | 3.2192 | 7.548 | 5.4384 | 16.6669 | 18.7765 | 26.3245 | 31.7629
8.0575 | 8.4458 | 2.0686 | 2.1029 | 3.3429 | 3.2057 | 7.5144 | 5.4115 | 16.5033 | 18.6062 | 26.1205 | 31.532
5.6798 | 7.9306 | 1.9893 | 1.984 | 2.9466 | 2.968 | 6.92 | 4.936 | 13.6104 | 15.5944 | 22.5144 | 27.4503
12.1633 | 9.3354 | 2.2054 | 2.3082 | 4.0272 | 3.6163 | 8.5408 | 6.2327 | 21.4987 | 23.8069 | 32.3477 | 38.5804
8.89 | 8.6262 | 2.0963 | 2.1445 | 3.4817 | 3.289 | 7.7225 | 5.578 | 17.5161 | 19.6606 | 27.3831 | 32.9611
4.5152 | 7.6783 | 1.9505 | 1.9258 | 2.7525 | 2.8515 | 6.6288 | 4.703 | 12.1935 | 14.1192 | 20.748 | 25.451
17.5746 | 10.5078 | 2.3858 | 2.5787 | 4.9291 | 4.1575 | 9.8937 | 7.3149 | 28.0824 | 30.6612 | 40.5548 | 47.8697
7.2511 | 8.2711 | 2.0417 | 2.0626 | 3.2085 | 3.1251 | 7.3128 | 5.2502 | 15.5222 | 17.5848 | 24.8976 | 30.1478
7.1645 | 8.2523 | 2.0388 | 2.0582 | 3.1941 | 3.1164 | 7.2911 | 5.2329 | 15.4168 | 17.475 | 24.7661 | 29.999
8.9096 | 8.6304 | 2.097 | 2.1455 | 3.4849 | 3.291 | 7.7274 | 5.5819 | 17.54 | 19.6855 | 27.4129 | 32.9948
13.8753 | 9.7063 | 2.2625 | 2.3938 | 4.3126 | 3.7875 | 8.9688 | 6.5751 | 23.5816 | 25.9754 | 34.9442 | 41.5193
14.9444 | 9.938 | 2.2981 | 2.4472 | 4.4907 | 3.8944 | 9.2361 | 6.7889 | 24.8824 | 27.3296 | 36.5657 | 43.3546
12.6497 | 9.4408 | 2.2217 | 2.3325 | 4.1083 | 3.665 | 8.6624 | 6.3299 | 22.0904 | 24.4229 | 33.0853 | 39.4153
-5.3839 | 5.5335 | 1.6205 | 1.4308 | 1.1027 | 1.8616 | 4.154 | 2.7232 | 0.14953 | 1.5803 | 5.7343 | 8.4576
7.415 | 8.3066 | 2.0472 | 2.0707 | 3.2358 | 3.1415 | 7.3537 | 5.283 | 15.7215 | 17.7923 | 25.146 | 30.429
0.75401 | 6.8634 | 1.8251 | 1.7377 | 2.1257 | 2.4754 | 5.6885 | 3.9508 | 7.6174 | 9.3551 | 15.0436 | 18.9944
7.6785 | 8.3637 | 2.0559 | 2.0839 | 3.2797 | 3.1678 | 7.4196 | 5.3357 | 16.0421 | 18.1261 | 25.5457 | 30.8814
-6.7356 | 5.2406 | 1.5755 | 1.3632 | 0.8774 | 1.7264 | 3.8161 | 2.4529 | -1.495 | -0.13174 | 3.6844 | 6.1373
15.0729 | 9.9658 | 2.3024 | 2.4536 | 4.5121 | 3.9073 | 9.2682 | 6.8146 | 25.0387 | 27.4923 | 36.7606 | 43.5751
4.1628 | 7.6019 | 1.9388 | 1.9081 | 2.6938 | 2.8163 | 6.5407 | 4.6326 | 11.7648 | 13.6729 | 20.2136 | 24.8462
-1.8279 | 6.304 | 1.7391 | 1.6086 | 1.6954 | 2.2172 | 5.043 | 3.4344 | 4.4761 | 6.0847 | 11.1277 | 14.5622
7.3349 | 8.2892 | 2.0445 | 2.0667 | 3.2225 | 3.1335 | 7.3337 | 5.267 | 15.6242 | 17.6909 | 25.0246 | 30.2916
-2.9217 | 6.067 | 1.7026 | 1.5539 | 1.5131 | 2.1078 | 4.7696 | 3.2157 | 3.1453 | 4.6992 | 9.4688 | 12.6845
6.4196 | 8.0909 | 2.014 | 2.021 | 3.0699 | 3.042 | 7.1049 | 5.0839 | 14.5106 | 16.5315 | 23.6364 | 28.7204
-3.1568 | 6.016 | 1.6948 | 1.5422 | 1.4739 | 2.0843 | 4.7108 | 3.1686 | 2.8592 | 4.4013 | 9.1121 | 12.2807
-5.5235 | 5.5032 | 1.6159 | 1.4238 | 1.0794 | 1.8476 | 4.1191 | 2.6953 | -0.0203 | 1.4035 | 5.5226 | 8.2179
4.1099 | 7.5905 | 1.937 | 1.9055 | 2.685 | 2.811 | 6.5275 | 4.622 | 11.7004 | 13.6058 | 20.1333 | 24.7553
9.1846 | 8.69 | 2.1062 | 2.1592 | 3.5308 | 3.3185 | 7.7962 | 5.6369 | 17.8746 | 20.0339 | 27.83 | 33.4669
-3.3156 | 5.9816 | 1.6895 | 1.5342 | 1.4474 | 2.0684 | 4.6711 | 3.1369 | 2.666 | 4.2003 | 8.8714 | 12.0082
10.6419 | 9.0057 | 2.1547 | 2.2321 | 3.7737 | 3.4642 | 8.1605 | 5.9284 | 19.6477 | 21.8798 | 30.0402 | 35.9686
9.4293 | 8.743 | 2.1143 | 2.1715 | 3.5716 | 3.3429 | 7.8573 | 5.6859 | 18.1724 | 20.3438 | 28.2012 | 33.8871
24.2891 | 11.9626 | 2.6096 | 2.9145 | 6.0482 | 4.8289 | 11.5723 | 8.6578 | 36.2518 | 39.1662 | 50.7385 | 59.3964
8.2951 | 8.4973 | 2.0765 | 2.1148 | 3.3825 | 3.2295 | 7.5738 | 5.459 | 16.7923 | 18.9071 | 26.4808 | 31.9398
-5.1847 | 5.5767 | 1.6272 | 1.4408 | 1.1359 | 1.8815 | 4.2038 | 2.7631 | 0.392 | 1.8328 | 6.0366 | 8.7997
7.4308 | 8.31 | 2.0477 | 2.0715 | 3.2385 | 3.1431 | 7.3577 | 5.2862 | 15.7408 | 17.8123 | 25.17 | 30.4562
3.9805 | 7.5624 | 1.9327 | 1.899 | 2.6634 | 2.798 | 6.4951 | 4.5961 | 11.5429 | 13.4419 | 19.937 | 24.5331
6.9627 | 8.2086 | 2.0321 | 2.0481 | 3.1605 | 3.0963 | 7.2407 | 5.1925 | 15.1713 | 17.2195 | 24.4602 | 29.6527
10.5847 | 8.9933 | 2.1528 | 2.2292 | 3.7641 | 3.4585 | 8.1462 | 5.9169 | 19.578 | 21.8073 | 29.9534 | 35.8704
-1.1576 | 6.4492 | 1.7614 | 1.6421 | 1.8071 | 2.2842 | 5.2106 | 3.5685 | 5.2915 | 6.9337 | 12.1443 | 15.7127
-1.1256 | 6.4561 | 1.7625 | 1.6437 | 1.8124 | 2.2874 | 5.2186 | 3.5749 | 5.3305 | 6.9742 | 12.1928 | 15.7677
10.0004 | 8.8667 | 2.1333 | 2.2 | 3.6667 | 3.4 | 8.0001 | 5.8001 | 18.8671 | 21.0671 | 29.0672 | 34.8673
8.9462 | 8.6383 | 2.0982 | 2.1473 | 3.491 | 3.2946 | 7.7366 | 5.5892 | 17.5845 | 19.7319 | 27.4684 | 33.0576
1.749 | 7.0789 | 1.8583 | 1.7874 | 2.2915 | 2.5749 | 5.9372 | 4.1498 | 8.8279 | 10.6153 | 16.5526 | 20.7024
0.17321 | 6.7375 | 1.8058 | 1.7087 | 2.0289 | 2.4173 | 5.5433 | 3.8346 | 6.9107 | 8.6194 | 14.1627 | 17.9973
7.8213 | 8.3946 | 2.0607 | 2.0911 | 3.3035 | 3.1821 | 7.4553 | 5.3643 | 16.2159 | 18.3069 | 25.7622 | 31.1265
15.1106 | 9.974 | 2.3037 | 2.4555 | 4.5184 | 3.9111 | 9.2777 | 6.8221 | 25.0846 | 27.5401 | 36.8178 | 43.6399
10.1426 | 8.8976 | 2.1381 | 2.2071 | 3.6904 | 3.4143 | 8.0357 | 5.8285 | 19.0402 | 21.2473 | 29.283 | 35.1115
16.8847 | 10.3583 | 2.3628 | 2.5442 | 4.8141 | 4.0885 | 9.7212 | 7.1769 | 27.243 | 29.7873 | 39.5084 | 46.6854
7.7903 | 8.3879 | 2.0597 | 2.0895 | 3.2984 | 3.179 | 7.4476 | 5.3581 | 16.1782 | 18.2677 | 25.7153 | 31.0734
13.5503 | 9.6359 | 2.2517 | 2.3775 | 4.2584 | 3.755 | 8.8876 | 6.5101 | 23.1862 | 25.5637 | 34.4513 | 40.9613
15.0013 | 9.9503 | 2.3 | 2.4501 | 4.5002 | 3.9001 | 9.2503 | 6.8003 | 24.9515 | 27.4016 | 36.6519 | 43.4522
7.9384 | 8.42 | 2.0646 | 2.0969 | 3.3231 | 3.1938 | 7.4846 | 5.3877 | 16.3584 | 18.4553 | 25.9399 | 31.3276
6.8871 | 8.1922 | 2.0296 | 2.0444 | 3.1479 | 3.0887 | 7.2218 | 5.1774 | 15.0793 | 17.1237 | 24.3455 | 29.5229
1.9661 | 7.126 | 1.8655 | 1.7983 | 2.3277 | 2.5966 | 5.9915 | 4.1932 | 9.0921 | 10.8904 | 16.8819 | 21.0751
3.4524 | 7.448 | 1.9151 | 1.8726 | 2.5754 | 2.7452 | 6.3631 | 4.4905 | 10.9004 | 12.773 | 19.1361 | 23.6266
11.6679 | 9.228 | 2.1889 | 2.2834 | 3.9446 | 3.5668 | 8.417 | 6.1336 | 20.8959 | 23.1793 | 31.5963 | 37.7298
-0.70544 | 6.5472 | 1.7765 | 1.6647 | 1.8824 | 2.3295 | 5.3236 | 3.6589 | 5.8417 | 7.5064 | 12.8301 | 16.489
4.6741 | 7.7127 | 1.9558 | 1.9337 | 2.779 | 2.8674 | 6.6685 | 4.7348 | 12.3868 | 14.3205 | 20.989 | 25.7238
10.26 | 8.923 | 2.142 | 2.213 | 3.71 | 3.426 | 8.065 | 5.852 | 19.183 | 21.396 | 29.461 | 35.313
7.416 | 8.3068 | 2.0472 | 2.0708 | 3.236 | 3.1416 | 7.354 | 5.2832 | 15.7228 | 17.7936 | 25.1476 | 30.4308
2.6131 | 7.2662 | 1.8871 | 1.8307 | 2.4355 | 2.6613 | 6.1533 | 4.3226 | 9.8793 | 11.71 | 17.8633 | 22.1859
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2044 | 14.1306 | 20.7616 | 25.4664
9.0177 | 8.6538 | 2.1006 | 2.1509 | 3.5029 | 3.3018 | 7.7544 | 5.6035 | 17.6715 | 19.8224 | 27.5768 | 33.1803
11.271 | 9.1421 | 2.1757 | 2.2636 | 3.8785 | 3.5271 | 8.3178 | 6.0542 | 20.4131 | 22.6766 | 30.9944 | 37.0486
4.8689 | 7.7549 | 1.9623 | 1.9434 | 2.8115 | 2.8869 | 6.7172 | 4.7738 | 12.6238 | 14.5672 | 21.2844 | 26.0582
13.7381 | 9.6766 | 2.2579 | 2.3869 | 4.2897 | 3.7738 | 8.9345 | 6.5476 | 23.4147 | 25.8016 | 34.7361 | 41.2837
-0.14801 | 6.6679 | 1.7951 | 1.6926 | 1.9753 | 2.3852 | 5.463 | 3.7704 | 6.5199 | 8.2125 | 13.6755 | 17.4459
4.9965 | 7.7826 | 1.9666 | 1.9498 | 2.8328 | 2.8997 | 6.7491 | 4.7993 | 12.7791 | 14.7289 | 21.478 | 26.2773
2.9362 | 7.3362 | 1.8979 | 1.8468 | 2.4894 | 2.6936 | 6.234 | 4.3872 | 10.2723 | 12.1191 | 18.3532 | 22.7404
10.8682 | 9.0548 | 2.1623 | 2.2434 | 3.8114 | 3.4868 | 8.2171 | 5.9736 | 19.923 | 22.1664 | 30.3835 | 36.3571
5.3766 | 7.8649 | 1.9792 | 1.9688 | 2.8961 | 2.9377 | 6.8441 | 4.8753 | 13.2415 | 15.2103 | 22.0545 | 26.9298
-3.2425 | 5.9975 | 1.6919 | 1.5379 | 1.4596 | 2.0758 | 4.6894 | 3.1515 | 2.755 | 4.2928 | 8.9822 | 12.1337
5.784 | 7.9532 | 1.9928 | 1.9892 | 2.964 | 2.9784 | 6.946 | 4.9568 | 13.7372 | 15.7264 | 22.6724 | 27.6292
0.62392 | 6.8352 | 1.8208 | 1.7312 | 2.104 | 2.4624 | 5.656 | 3.9248 | 7.4591 | 9.1903 | 14.8463 | 18.7711
3.8817 | 7.541 | 1.9294 | 1.8941 | 2.6469 | 2.7882 | 6.4704 | 4.5763 | 11.4227 | 13.3168 | 19.7872 | 24.3636
6.7592 | 8.1645 | 2.0253 | 2.038 | 3.1265 | 3.0759 | 7.1898 | 5.1518 | 14.9237 | 16.9617 | 24.1515 | 29.3033
8.4274 | 8.5259 | 2.0809 | 2.1214 | 3.4046 | 3.2427 | 7.6069 | 5.4855 | 16.9534 | 19.0748 | 26.6816 | 32.1671
16.2512 | 10.2211 | 2.3417 | 2.5126 | 4.7085 | 4.0251 | 9.5628 | 7.0502 | 26.4722 | 28.9848 | 38.5476 | 45.5978
3.9702 | 7.5602 | 1.9323 | 1.8985 | 2.6617 | 2.797 | 6.4925 | 4.594 | 11.5304 | 13.4289 | 19.9214 | 24.5155
9.1031 | 8.6723 | 2.1034 | 2.1552 | 3.5172 | 3.3103 | 7.7758 | 5.6206 | 17.7754 | 19.9305 | 27.7063 | 33.3269
7.6437 | 8.3561 | 2.0548 | 2.0822 | 3.2739 | 3.1644 | 7.4109 | 5.3287 | 15.9998 | 18.082 | 25.4929 | 30.8217
7.4801 | 8.3207 | 2.0493 | 2.074 | 3.2467 | 3.148 | 7.37 | 5.296 | 15.8008 | 17.8748 | 25.2449 | 30.5409
15.1289 | 9.9779 | 2.3043 | 2.4564 | 4.5215 | 3.9129 | 9.2822 | 6.8258 | 25.1068 | 27.5633 | 36.8455 | 43.6713
0.75091 | 6.8627 | 1.825 | 1.7375 | 2.1252 | 2.4751 | 5.6877 | 3.9502 | 7.6136 | 9.3512 | 15.0389 | 18.9891
1.9654 | 7.1258 | 1.8655 | 1.7983 | 2.3276 | 2.5965 | 5.9914 | 4.1931 | 9.0912 | 10.8895 | 16.8809 | 21.0739
9.8869 | 8.8422 | 2.1296 | 2.1943 | 3.6478 | 3.3887 | 7.9717 | 5.7774 | 18.7291 | 20.9234 | 28.8951 | 34.6725
6.4668 | 8.1011 | 2.0156 | 2.0233 | 3.0778 | 3.0467 | 7.1167 | 5.0934 | 14.5679 | 16.5913 | 23.708 | 28.8013
7.8432 | 8.3994 | 2.0614 | 2.0922 | 3.3072 | 3.1843 | 7.4608 | 5.3686 | 16.2426 | 18.3348 | 25.7956 | 31.1642
3.9091 | 7.547 | 1.9303 | 1.8955 | 2.6515 | 2.7909 | 6.4773 | 4.5818 | 11.456 | 13.3515 | 19.8288 | 24.4106
3.4369 | 7.4447 | 1.9146 | 1.8718 | 2.5728 | 2.7437 | 6.3592 | 4.4874 | 10.8815 | 12.7533 | 19.1126 | 23.5999
16.7592 | 10.3312 | 2.3586 | 2.538 | 4.7932 | 4.0759 | 9.6898 | 7.1518 | 27.0903 | 29.6283 | 39.3181 | 46.4699
-4.8476 | 5.6497 | 1.6384 | 1.4576 | 1.1921 | 1.9152 | 4.2881 | 2.8305 | 0.80204 | 2.2597 | 6.5478 | 9.3782
4.8571 | 7.7524 | 1.9619 | 1.9429 | 2.8095 | 2.8857 | 6.7143 | 4.7714 | 12.6094 | 14.5523 | 21.2665 | 26.038
15.5217 | 10.063 | 2.3174 | 2.4761 | 4.587 | 3.9522 | 9.3804 | 6.9043 | 25.5847 | 28.0608 | 37.4412 | 44.3456
4.5272 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7054 | 12.2081 | 14.1344 | 20.7662 | 25.4717
-6.9383 | 5.1967 | 1.5687 | 1.3531 | 0.84362 | 1.7062 | 3.7654 | 2.4123 | -1.7415 | -0.38845 | 3.377 | 5.7893
16.9328 | 10.3688 | 2.3644 | 2.5466 | 4.8221 | 4.0933 | 9.7332 | 7.1866 | 27.3016 | 29.8482 | 39.5814 | 46.768
14.0968 | 9.7543 | 2.2699 | 2.4048 | 4.3495 | 3.8097 | 9.0242 | 6.6194 | 23.8511 | 26.2559 | 35.2801 | 41.8995
21.6875 | 11.399 | 2.5229 | 2.7844 | 5.6146 | 4.5687 | 10.9219 | 8.1375 | 33.0864 | 35.8708 | 46.7927 | 54.9302
14.6441 | 9.8729 | 2.2881 | 2.4322 | 4.4407 | 3.8644 | 9.161 | 6.7288 | 24.5169 | 26.9491 | 36.1102 | 42.839
0.7403 | 6.8604 | 1.8247 | 1.737 | 2.1234 | 2.474 | 5.6851 | 3.9481 | 7.6007 | 9.3377 | 15.0228 | 18.9709
0.19334 | 6.7419 | 1.8064 | 1.7097 | 2.0322 | 2.4193 | 5.5483 | 3.8387 | 6.9352 | 8.6449 | 14.1932 | 18.0319
8.7563 | 8.5972 | 2.0919 | 2.1378 | 3.4594 | 3.2756 | 7.6891 | 5.5513 | 17.3534 | 19.4913 | 27.1803 | 32.7316
8.0989 | 8.4548 | 2.07 | 2.1049 | 3.3498 | 3.2099 | 7.5247 | 5.4198 | 16.5537 | 18.6586 | 26.1833 | 31.6031
-3.4729 | 5.9475 | 1.6842 | 1.5264 | 1.4212 | 2.0527 | 4.6318 | 3.1054 | 2.4746 | 4.0009 | 8.6327 | 11.7381
0.19703 | 6.7427 | 1.8066 | 1.7099 | 2.0328 | 2.4197 | 5.5493 | 3.8394 | 6.9397 | 8.6496 | 14.1988 | 18.0382
2.1437 | 7.1645 | 1.8715 | 1.8072 | 2.3573 | 2.6144 | 6.0359 | 4.2287 | 9.3082 | 11.1154 | 17.1513 | 21.38
2.1804 | 7.1724 | 1.8727 | 1.809 | 2.3634 | 2.618 | 6.0451 | 4.2361 | 9.3528 | 11.1618 | 17.2069 | 21.443
8.4919 | 8.5399 | 2.0831 | 2.1246 | 3.4153 | 3.2492 | 7.623 | 5.4984 | 17.0318 | 19.1564 | 26.7793 | 32.2777
-0.30742 | 6.6334 | 1.7898 | 1.6846 | 1.9488 | 2.3693 | 5.4231 | 3.7385 | 6.326 | 8.0106 | 13.4337 | 17.1723
5.7009 | 7.9352 | 1.99 | 1.985 | 2.9501 | 2.9701 | 6.9252 | 4.9402 | 13.6361 | 15.6211 | 22.5463 | 27.4865
3.9954 | 7.5657 | 1.9332 | 1.8998 | 2.6659 | 2.7995 | 6.4988 | 4.5991 | 11.561 | 13.4608 | 19.9596 | 24.5587
2.8736 | 7.3226 | 1.8958 | 1.8437 | 2.4789 | 2.6874 | 6.2184 | 4.3747 | 10.1962 | 12.0399 | 18.2583 | 22.633
7.4078 | 8.305 | 2.0469 | 2.0704 | 3.2346 | 3.1408 | 7.352 | 5.2816 | 15.7128 | 17.7832 | 25.1352 | 30.4167
4.6413 | 7.7056 | 1.9547 | 1.9321 | 2.7735 | 2.8641 | 6.6603 | 4.7283 | 12.3469 | 14.2789 | 20.9392 | 25.6675
17.8399 | 10.5653 | 2.3947 | 2.592 | 4.9733 | 4.184 | 9.96 | 7.368 | 28.4052 | 30.9972 | 40.9571 | 48.3251
10.3126 | 8.9344 | 2.1438 | 2.2156 | 3.7188 | 3.4313 | 8.0782 | 5.8625 | 19.2471 | 21.4627 | 29.5409 | 35.4034
0.93636 | 6.9029 | 1.8312 | 1.7468 | 2.1561 | 2.4936 | 5.7341 | 3.9873 | 7.8392 | 9.5861 | 15.3201 | 19.3074
5.9171 | 7.982 | 1.9972 | 1.9959 | 2.9862 | 2.9917 | 6.9793 | 4.9834 | 13.8992 | 15.8951 | 22.8743 | 27.8578
14.2609 | 9.7899 | 2.2754 | 2.413 | 4.3768 | 3.8261 | 9.0652 | 6.6522 | 24.0507 | 26.4638 | 35.529 | 42.1812
4.7586 | 7.731 | 1.9586 | 1.9379 | 2.7931 | 2.8759 | 6.6897 | 4.7517 | 12.4897 | 14.4276 | 21.1173 | 25.869
-1.5358 | 6.3672 | 1.7488 | 1.6232 | 1.744 | 2.2464 | 5.116 | 3.4928 | 4.8314 | 6.4546 | 11.5707 | 15.0635
4.5187 | 7.6791 | 1.9506 | 1.9259 | 2.7531 | 2.8519 | 6.6297 | 4.7037 | 12.1977 | 14.1237 | 20.7534 | 25.4571
10.9318 | 9.0686 | 2.1644 | 2.2466 | 3.822 | 3.4932 | 8.233 | 5.9864 | 20.0004 | 22.247 | 30.4799 | 36.4663
3.7619 | 7.5151 | 1.9254 | 1.8881 | 2.627 | 2.7762 | 6.4405 | 4.5524 | 11.2769 | 13.165 | 19.6055 | 24.1579
0.66962 | 6.8451 | 1.8223 | 1.7335 | 2.1116 | 2.467 | 5.6674 | 3.9339 | 7.5147 | 9.2482 | 14.9156 | 18.8495
8.4453 | 8.5298 | 2.0815 | 2.1223 | 3.4076 | 3.2445 | 7.6113 | 5.4891 | 16.9752 | 19.0974 | 26.7088 | 32.1978
4 | 7.5667 | 1.9333 | 1.9 | 2.6667 | 2.8 | 6.5 | 4.6 | 11.5666 | 13.4666 | 19.9666 | 24.5666
0.11313 | 6.7245 | 1.8038 | 1.7057 | 2.0189 | 2.4113 | 5.5283 | 3.8226 | 6.8376 | 8.5433 | 14.0716 | 17.8942
14.3302 | 9.8049 | 2.2777 | 2.4165 | 4.3884 | 3.833 | 9.0825 | 6.666 | 24.135 | 26.5516 | 35.6341 | 42.3001
0.82956 | 6.8797 | 1.8277 | 1.7415 | 2.1383 | 2.483 | 5.7074 | 3.9659 | 7.7093 | 9.4508 | 15.1582 | 19.1241
6.5365 | 8.1162 | 2.0179 | 2.0268 | 3.0894 | 3.0537 | 7.1341 | 5.1073 | 14.6528 | 16.6796 | 23.8137 | 28.921
2.4857 | 7.2386 | 1.8829 | 1.8243 | 2.4143 | 2.6486 | 6.1214 | 4.2971 | 9.7243 | 11.5486 | 17.67 | 21.9671
9.4618 | 8.7501 | 2.1154 | 2.1731 | 3.577 | 3.3462 | 7.8655 | 5.6924 | 18.2119 | 20.385 | 28.2504 | 33.9428
10.5152 | 8.9783 | 2.1505 | 2.2258 | 3.7525 | 3.4515 | 8.1288 | 5.903 | 19.4935 | 21.7193 | 29.8481 | 35.7511
13.8852 | 9.7085 | 2.2628 | 2.3943 | 4.3142 | 3.7885 | 8.9713 | 6.577 | 23.5937 | 25.9879 | 34.9592 | 41.5363
7.4114 | 8.3058 | 2.047 | 2.0706 | 3.2352 | 3.1411 | 7.3529 | 5.2823 | 15.7172 | 17.7878 | 25.1406 | 30.4229
3.3173 | 7.4187 | 1.9106 | 1.8659 | 2.5529 | 2.7317 | 6.3293 | 4.4635 | 10.736 | 12.6019 | 18.9312 | 23.3947
6.514 | 8.1114 | 2.0171 | 2.0257 | 3.0857 | 3.0514 | 7.1285 | 5.1028 | 14.6253 | 16.651 | 23.7795 | 28.8823
-0.5379 | 6.5835 | 1.7821 | 1.6731 | 1.9104 | 2.3462 | 5.3655 | 3.6924 | 6.0456 | 7.7187 | 13.0842 | 16.7766
1.9903 | 7.1312 | 1.8663 | 1.7995 | 2.3317 | 2.599 | 5.9976 | 4.1981 | 9.1215 | 10.9211 | 16.9186 | 21.1167
17.5171 | 10.4954 | 2.3839 | 2.5759 | 4.9195 | 4.1517 | 9.8793 | 7.3034 | 28.0125 | 30.5883 | 40.4676 | 47.771
5.7762 | 7.9515 | 1.9925 | 1.9888 | 2.9627 | 2.9776 | 6.9441 | 4.9552 | 13.7277 | 15.7166 | 22.6606 | 27.6159
5.936 | 7.9861 | 1.9979 | 1.9968 | 2.9893 | 2.9936 | 6.984 | 4.9872 | 13.9222 | 15.919 | 22.903 | 27.8902
-4.9884 | 5.6192 | 1.6337 | 1.4506 | 1.1686 | 1.9012 | 4.2529 | 2.8023 | 0.63082 | 2.0814 | 6.3343 | 9.1366
4.2438 | 7.6195 | 1.9415 | 1.9122 | 2.7073 | 2.8244 | 6.561 | 4.6488 | 11.8633 | 13.7755 | 20.3365 | 24.9852
8.0514 | 8.4445 | 2.0684 | 2.1026 | 3.3419 | 3.2051 | 7.5128 | 5.4103 | 16.4958 | 18.5984 | 26.1112 | 31.5215
-8.3684 | 4.8868 | 1.5211 | 1.2816 | 0.60526 | 1.5632 | 3.4079 | 2.1263 | -3.4816 | -2.2 | 1.2079 | 3.3342
10.4473 | 8.9636 | 2.1482 | 2.2224 | 3.7412 | 3.4447 | 8.1118 | 5.8895 | 19.4109 | 21.6333 | 29.7451 | 35.6346
6.2781 | 8.0603 | 2.0093 | 2.0139 | 3.0463 | 3.0278 | 7.0695 | 5.0556 | 14.3383 | 16.3522 | 23.4218 | 28.4774
-0.026116 | 6.6943 | 1.7991 | 1.6987 | 1.9956 | 2.3974 | 5.4935 | 3.7948 | 6.6682 | 8.3669 | 13.8604 | 17.6552
12.3808 | 9.3825 | 2.2127 | 2.319 | 4.0635 | 3.6381 | 8.5952 | 6.2762 | 21.7633 | 24.0823 | 32.6775 | 38.9537
4.3092 | 7.6337 | 1.9436 | 1.9155 | 2.7182 | 2.8309 | 6.5773 | 4.6618 | 11.9428 | 13.8583 | 20.4356 | 25.0974
9.5463 | 8.7684 | 2.1182 | 2.1773 | 3.591 | 3.3546 | 7.8866 | 5.7093 | 18.3146 | 20.492 | 28.3785 | 34.0878
3.7633 | 7.5154 | 1.9254 | 1.8882 | 2.6272 | 2.7763 | 6.4408 | 4.5527 | 11.2787 | 13.1668 | 19.6077 | 24.1603
8.7658 | 8.5992 | 2.0922 | 2.1383 | 3.461 | 3.2766 | 7.6914 | 5.5532 | 17.365 | 19.5033 | 27.1947 | 32.7479
0.69767 | 6.8512 | 1.8233 | 1.7349 | 2.1163 | 2.4698 | 5.6744 | 3.9395 | 7.5488 | 9.2837 | 14.9581 | 18.8977
11.5977 | 9.2128 | 2.1866 | 2.2799 | 3.9329 | 3.5598 | 8.3994 | 6.1195 | 20.8105 | 23.0904 | 31.4898 | 37.6094
8.4712 | 8.5354 | 2.0824 | 2.1236 | 3.4119 | 3.2471 | 7.6178 | 5.4942 | 17.0067 | 19.1302 | 26.748 | 32.2423
18.2142 | 10.6464 | 2.4071 | 2.6107 | 5.0357 | 4.2214 | 10.0536 | 7.4428 | 28.8606 | 31.4713 | 41.5249 | 48.9677
13.8999 | 9.7117 | 2.2633 | 2.395 | 4.3167 | 3.79 | 8.975 | 6.58 | 23.6116 | 26.0066 | 34.9816 | 41.5615
6.3636 | 8.0788 | 2.0121 | 2.0182 | 3.0606 | 3.0364 | 7.0909 | 5.0727 | 14.4424 | 16.4605 | 23.5514 | 28.6242
6.9097 | 8.1971 | 2.0303 | 2.0455 | 3.1516 | 3.091 | 7.2274 | 5.1819 | 15.1068 | 17.1523 | 24.3797 | 29.5616
1.1273 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7818 | 4.0255 | 8.0716 | 9.8279 | 15.6098 | 19.6352
15.8964 | 10.1442 | 2.3299 | 2.4948 | 4.6494 | 3.9896 | 9.4741 | 6.9793 | 26.0407 | 28.5355 | 38.0096 | 44.9889
6.1089 | 8.0236 | 2.0036 | 2.0054 | 3.0181 | 3.0109 | 7.0272 | 5.0218 | 14.1325 | 16.1379 | 23.1651 | 28.1869
0.25643 | 6.7556 | 1.8085 | 1.7128 | 2.0427 | 2.4256 | 5.5641 | 3.8513 | 7.012 | 8.7248 | 14.2889 | 18.1402
-4.2332 | 5.7828 | 1.6589 | 1.4883 | 1.2945 | 1.9767 | 4.4417 | 2.9534 | 1.5496 | 3.038 | 7.4797 | 10.433
3.0006 | 7.3501 | 1.9 | 1.85 | 2.5001 | 2.7001 | 6.2501 | 4.4001 | 10.3507 | 12.2007 | 18.4509 | 22.851
-0.019623 | 6.6957 | 1.7993 | 1.699 | 1.9967 | 2.398 | 5.4951 | 3.7961 | 6.6761 | 8.3751 | 13.8702 | 17.6663
1.7234 | 7.0734 | 1.8574 | 1.7862 | 2.2872 | 2.5723 | 5.9308 | 4.1447 | 8.7968 | 10.583 | 16.5138 | 20.6585
17.9337 | 10.5856 | 2.3978 | 2.5967 | 4.9889 | 4.1934 | 9.9834 | 7.3867 | 28.5193 | 31.116 | 41.0994 | 48.4862
5.9536 | 7.9899 | 1.9985 | 1.9977 | 2.9923 | 2.9954 | 6.9884 | 4.9907 | 13.9435 | 15.9412 | 22.9296 | 27.9203
8.1286 | 8.4612 | 2.071 | 2.1064 | 3.3548 | 3.2129 | 7.5321 | 5.4257 | 16.5897 | 18.6962 | 26.2283 | 31.654
0.99013 | 6.9145 | 1.833 | 1.7495 | 2.165 | 2.499 | 5.7475 | 3.998 | 7.9047 | 9.6542 | 15.4017 | 19.3997
9.9327 | 8.8521 | 2.1311 | 2.1966 | 3.6554 | 3.3933 | 7.9832 | 5.7865 | 18.7847 | 20.9814 | 28.9645 | 34.7511
13.1113 | 9.5408 | 2.237 | 2.3556 | 4.1852 | 3.7111 | 8.7778 | 6.4223 | 22.6521 | 25.0077 | 33.7855 | 40.2078
3.9177 | 7.5488 | 1.9306 | 1.8959 | 2.6529 | 2.7918 | 6.4794 | 4.5835 | 11.4665 | 13.3624 | 19.8418 | 24.4253
4.0887 | 7.5859 | 1.9363 | 1.9044 | 2.6814 | 2.8089 | 6.5222 | 4.6177 | 11.6745 | 13.579 | 20.1011 | 24.7189
-0.055066 | 6.6881 | 1.7982 | 1.6972 | 1.9908 | 2.3945 | 5.4862 | 3.789 | 6.633 | 8.3303 | 13.8165 | 17.6055
3.9499 | 7.5558 | 1.9317 | 1.8975 | 2.6583 | 2.795 | 6.4875 | 4.59 | 11.5057 | 13.4032 | 19.8906 | 24.4806
2.5412 | 7.2506 | 1.8847 | 1.8271 | 2.4235 | 2.6541 | 6.1353 | 4.3082 | 9.7918 | 11.6189 | 17.7542 | 22.0624
-1.6705 | 6.3381 | 1.7443 | 1.6165 | 1.7216 | 2.233 | 5.0824 | 3.4659 | 4.6676 | 6.2841 | 11.3664 | 14.8323
17.8938 | 10.577 | 2.3965 | 2.5947 | 4.9823 | 4.1894 | 9.9734 | 7.3788 | 28.4708 | 31.0655 | 41.0389 | 48.4177
2.6217 | 7.268 | 1.8874 | 1.8311 | 2.4369 | 2.6622 | 6.1554 | 4.3243 | 9.8897 | 11.7208 | 17.8762 | 22.2005
6.531 | 8.1151 | 2.0177 | 2.0266 | 3.0885 | 3.0531 | 7.1328 | 5.1062 | 14.6461 | 16.6726 | 23.8054 | 28.9116
-0.63752 | 6.5619 | 1.7787 | 1.6681 | 1.8937 | 2.3362 | 5.3406 | 3.6725 | 5.9244 | 7.5925 | 12.9331 | 16.6056
3.242 | 7.4024 | 1.9081 | 1.8621 | 2.5403 | 2.7242 | 6.3105 | 4.4484 | 10.6444 | 12.5065 | 18.817 | 23.2654
7.7059 | 8.3696 | 2.0569 | 2.0853 | 3.2843 | 3.1706 | 7.4265 | 5.3412 | 16.0755 | 18.1608 | 25.5873 | 30.9285
5.5315 | 7.8985 | 1.9844 | 1.9766 | 2.9219 | 2.9532 | 6.8829 | 4.9063 | 13.43 | 15.4066 | 22.2895 | 27.1958
6.2875 | 8.0623 | 2.0096 | 2.0144 | 3.0479 | 3.0288 | 7.0719 | 5.0575 | 14.3498 | 16.3642 | 23.4361 | 28.4936
8.8478 | 8.617 | 2.0949 | 2.1424 | 3.4746 | 3.2848 | 7.7119 | 5.5696 | 17.4648 | 19.6072 | 27.3191 | 32.8887
3.6485 | 7.4905 | 1.9216 | 1.8824 | 2.6081 | 2.7648 | 6.4121 | 4.5297 | 11.139 | 13.0214 | 19.4335 | 23.9632
4.5406 | 7.6838 | 1.9514 | 1.927 | 2.7568 | 2.8541 | 6.6352 | 4.7081 | 12.2244 | 14.1515 | 20.7866 | 25.4947
7.2969 | 8.281 | 2.0432 | 2.0648 | 3.2162 | 3.1297 | 7.3242 | 5.2594 | 15.5779 | 17.6428 | 24.967 | 30.2264
7.5894 | 8.3444 | 2.053 | 2.0795 | 3.2649 | 3.1589 | 7.3974 | 5.3179 | 15.9338 | 18.0133 | 25.4106 | 30.7285
-1.186 | 6.443 | 1.7605 | 1.6407 | 1.8023 | 2.2814 | 5.2035 | 3.5628 | 5.257 | 6.8977 | 12.1012 | 15.664
7.5221 | 8.3298 | 2.0507 | 2.0761 | 3.2537 | 3.1522 | 7.3805 | 5.3044 | 15.8519 | 17.928 | 25.3085 | 30.6129
4.1728 | 7.6041 | 1.9391 | 1.9086 | 2.6955 | 2.8173 | 6.5432 | 4.6346 | 11.7769 | 13.6856 | 20.2288 | 24.8633
10.0312 | 8.8734 | 2.1344 | 2.2016 | 3.6719 | 3.4031 | 8.0078 | 5.8062 | 18.9047 | 21.1062 | 29.114 | 34.9203
1.8924 | 7.11 | 1.8631 | 1.7946 | 2.3154 | 2.5892 | 5.9731 | 4.1785 | 9.0025 | 10.7971 | 16.7702 | 20.9487
16.936 | 10.3695 | 2.3645 | 2.5468 | 4.8227 | 4.0936 | 9.734 | 7.1872 | 27.3054 | 29.8522 | 39.5862 | 46.7734
7.2675 | 8.2746 | 2.0422 | 2.0634 | 3.2112 | 3.1267 | 7.3169 | 5.2535 | 15.5421 | 17.6055 | 24.9223 | 30.1758
5.0004 | 7.7834 | 1.9667 | 1.95 | 2.8334 | 2.9 | 6.7501 | 4.8001 | 12.7839 | 14.7339 | 21.484 | 26.2841
8.22 | 8.481 | 2.074 | 2.111 | 3.37 | 3.222 | 7.555 | 5.444 | 16.7011 | 18.8121 | 26.3671 | 31.8111
15.5054 | 10.0595 | 2.3168 | 2.4753 | 4.5842 | 3.9505 | 9.3763 | 6.9011 | 25.5649 | 28.0401 | 37.4165 | 44.3175
1.1288 | 6.9446 | 1.8376 | 1.7564 | 2.1881 | 2.5129 | 5.7822 | 4.0258 | 8.0734 | 9.8299 | 15.6121 | 19.6378
0.42329 | 6.7917 | 1.8141 | 1.7212 | 2.0705 | 2.4423 | 5.6058 | 3.8847 | 7.215 | 8.9362 | 14.542 | 18.4267
6.5131 | 8.1112 | 2.0171 | 2.0257 | 3.0855 | 3.0513 | 7.1283 | 5.1026 | 14.6242 | 16.6499 | 23.7781 | 28.8807
-0.42709 | 6.6075 | 1.7858 | 1.6786 | 1.9288 | 2.3573 | 5.3932 | 3.7146 | 6.1804 | 7.859 | 13.2522 | 16.9668
3.3855 | 7.4335 | 1.9129 | 1.8693 | 2.5643 | 2.7386 | 6.3464 | 4.4771 | 10.8191 | 12.6883 | 19.0347 | 23.5118
9.2592 | 8.7062 | 2.1086 | 2.163 | 3.5432 | 3.3259 | 7.8148 | 5.6518 | 17.9653 | 20.1283 | 27.9431 | 33.5949
0.34898 | 6.7756 | 1.8116 | 1.7174 | 2.0582 | 2.4349 | 5.5872 | 3.8698 | 7.1246 | 8.842 | 14.4293 | 18.2991
14.8692 | 9.9217 | 2.2956 | 2.4435 | 4.4782 | 3.8869 | 9.2173 | 6.7738 | 24.7908 | 27.2343 | 36.4516 | 43.2254
14.2324 | 9.7837 | 2.2744 | 2.4116 | 4.3721 | 3.8232 | 9.0581 | 6.6465 | 24.0161 | 26.4277 | 35.4858 | 42.1323
-3.7799 | 5.881 | 1.674 | 1.511 | 1.37 | 2.022 | 4.555 | 3.044 | 2.1012 | 3.6122 | 8.1672 | 11.2112
5.3413 | 7.8573 | 1.978 | 1.9671 | 2.8902 | 2.9341 | 6.8353 | 4.8683 | 13.1986 | 15.1657 | 22.001 | 26.8693
13.6643 | 9.6606 | 2.2555 | 2.3832 | 4.2774 | 3.7664 | 8.9161 | 6.5329 | 23.3249 | 25.7081 | 34.6242 | 41.157
17.2063 | 10.428 | 2.3735 | 2.5603 | 4.8677 | 4.1206 | 9.8016 | 7.2413 | 27.6343 | 30.1946 | 39.9962 | 47.2374
8.2493 | 8.4874 | 2.075 | 2.1125 | 3.3749 | 3.2249 | 7.5623 | 5.4499 | 16.7367 | 18.8491 | 26.4115 | 31.8613
5.4441 | 7.8796 | 1.9815 | 1.9722 | 2.9074 | 2.9444 | 6.861 | 4.8888 | 13.3237 | 15.2959 | 22.1569 | 27.0457
0.4585 | 6.7993 | 1.8153 | 1.7229 | 2.0764 | 2.4459 | 5.6146 | 3.8917 | 7.2578 | 8.9808 | 14.5954 | 18.4871
-0.038013 | 6.6918 | 1.7987 | 1.6981 | 1.9937 | 2.3962 | 5.4905 | 3.7924 | 6.6538 | 8.3519 | 13.8423 | 17.6347
11.8839 | 9.2749 | 2.1961 | 2.2942 | 3.9807 | 3.5884 | 8.471 | 6.1768 | 21.1588 | 23.453 | 31.924 | 38.1008
-3.1106 | 6.026 | 1.6963 | 1.5445 | 1.4816 | 2.0889 | 4.7224 | 3.1779 | 2.9155 | 4.4599 | 9.1823 | 12.3602
2.154 | 7.1667 | 1.8718 | 1.8077 | 2.359 | 2.6154 | 6.0385 | 4.2308 | 9.3207 | 11.1284 | 17.1669 | 21.3977
7.67 | 8.3618 | 2.0557 | 2.0835 | 3.2783 | 3.167 | 7.4175 | 5.334 | 16.0319 | 18.1154 | 25.5329 | 30.8669
15.8604 | 10.1364 | 2.3287 | 2.493 | 4.6434 | 3.986 | 9.4651 | 6.9721 | 25.9968 | 28.4898 | 37.9549 | 44.927
-1.0877 | 6.4643 | 1.7637 | 1.6456 | 1.8187 | 2.2912 | 5.2281 | 3.5825 | 5.3766 | 7.0222 | 12.2503 | 15.8327
9.5656 | 8.7725 | 2.1189 | 2.1783 | 3.5943 | 3.3566 | 7.8914 | 5.7131 | 18.3381 | 20.5164 | 28.4078 | 34.1209
5.2751 | 7.8429 | 1.9758 | 1.9638 | 2.8792 | 2.9275 | 6.8188 | 4.855 | 13.1181 | 15.0818 | 21.9006 | 26.7557
4.8547 | 7.7519 | 1.9618 | 1.9427 | 2.8091 | 2.8855 | 6.7137 | 4.7709 | 12.6066 | 14.5493 | 21.263 | 26.0339
4.1225 | 7.5932 | 1.9374 | 1.9061 | 2.6871 | 2.8123 | 6.5306 | 4.6245 | 11.7157 | 13.6219 | 20.1525 | 24.777
0.12817 | 6.7278 | 1.8043 | 1.7064 | 2.0214 | 2.4128 | 5.532 | 3.8256 | 6.8559 | 8.5623 | 14.0944 | 17.92
3.1497 | 7.3824 | 1.905 | 1.8575 | 2.525 | 2.715 | 6.2874 | 4.4299 | 10.5322 | 12.3897 | 18.6771 | 23.107
0.004088 | 6.7009 | 1.8001 | 1.7002 | 2.0007 | 2.4004 | 5.501 | 3.8008 | 6.705 | 8.4052 | 13.9062 | 17.707
2.664 | 7.2772 | 1.8888 | 1.8332 | 2.444 | 2.6664 | 6.166 | 4.3328 | 9.9412 | 11.7744 | 17.9403 | 22.2731
16.3601 | 10.2447 | 2.3453 | 2.518 | 4.7267 | 4.036 | 9.59 | 7.072 | 26.6047 | 29.1227 | 38.7127 | 45.7848
1.1157 | 6.9417 | 1.8372 | 1.7558 | 2.186 | 2.5116 | 5.7789 | 4.0231 | 8.0575 | 9.8133 | 15.5922 | 19.6153
8.3578 | 8.5109 | 2.0786 | 2.1179 | 3.393 | 3.2358 | 7.5894 | 5.4716 | 16.8686 | 18.9865 | 26.576 | 32.0475
-3.237 | 5.9986 | 1.6921 | 1.5381 | 1.4605 | 2.0763 | 4.6907 | 3.1526 | 2.7616 | 4.2998 | 8.9905 | 12.1431
3.8189 | 7.5274 | 1.9273 | 1.8909 | 2.6365 | 2.7819 | 6.4547 | 4.5638 | 11.3463 | 13.2373 | 19.692 | 24.2558
9.7219 | 8.8064 | 2.1241 | 2.1861 | 3.6203 | 3.3722 | 7.9305 | 5.7444 | 18.5283 | 20.7144 | 28.6448 | 34.3892
8.9915 | 8.6482 | 2.0997 | 2.1496 | 3.4986 | 3.2992 | 7.7479 | 5.5983 | 17.6397 | 19.7893 | 27.5372 | 33.1355
-3.6954 | 5.8993 | 1.6768 | 1.5152 | 1.3841 | 2.0305 | 4.5762 | 3.0609 | 2.2039 | 3.7192 | 8.2953 | 11.3562
10.0738 | 8.8827 | 2.1358 | 2.2037 | 3.679 | 3.4074 | 8.0185 | 5.8148 | 18.9565 | 21.1602 | 29.1787 | 34.9934
0.046038 | 6.71 | 1.8015 | 1.7023 | 2.0077 | 2.4046 | 5.5115 | 3.8092 | 6.756 | 8.4583 | 13.9698 | 17.779
11.9431 | 9.2877 | 2.1981 | 2.2972 | 3.9905 | 3.5943 | 8.4858 | 6.1886 | 21.2308 | 23.528 | 32.0138 | 38.2024
10.2351 | 8.9176 | 2.1412 | 2.2118 | 3.7058 | 3.4235 | 8.0588 | 5.847 | 19.1527 | 21.3645 | 29.4232 | 35.2703
16.0073 | 10.1682 | 2.3336 | 2.5004 | 4.6679 | 4.0007 | 9.5018 | 7.0015 | 26.1755 | 28.6759 | 38.1777 | 45.1791
11.2117 | 9.1292 | 2.1737 | 2.2606 | 3.8686 | 3.5212 | 8.3029 | 6.0423 | 20.3409 | 22.6015 | 30.9044 | 36.9468
0.7651 | 6.8658 | 1.8255 | 1.7383 | 2.1275 | 2.4765 | 5.6913 | 3.953 | 7.6309 | 9.3691 | 15.0604 | 19.0134
-2.5424 | 6.1491 | 1.7153 | 1.5729 | 1.5763 | 2.1458 | 4.8644 | 3.2915 | 3.6068 | 5.1796 | 10.044 | 13.3356
6.6128 | 8.1328 | 2.0204 | 2.0306 | 3.1021 | 3.0613 | 7.1532 | 5.1226 | 14.7456 | 16.7763 | 23.9295 | 29.052
-0.13011 | 6.6718 | 1.7957 | 1.6935 | 1.9783 | 2.387 | 5.4675 | 3.774 | 6.5417 | 8.2352 | 13.7027 | 17.4766
2.5146 | 7.2448 | 1.8838 | 1.8257 | 2.4191 | 2.6515 | 6.1286 | 4.3029 | 9.7594 | 11.5851 | 17.7138 | 22.0167
14.496 | 9.8408 | 2.2832 | 2.4248 | 4.416 | 3.8496 | 9.124 | 6.6992 | 24.3368 | 26.7616 | 35.8856 | 42.5848
6.3767 | 8.0816 | 2.0126 | 2.0188 | 3.0628 | 3.0377 | 7.0942 | 5.0753 | 14.4583 | 16.4771 | 23.5713 | 28.6466
-0.66363 | 6.5562 | 1.7779 | 1.6668 | 1.8894 | 2.3336 | 5.3341 | 3.6673 | 5.8926 | 7.5594 | 12.8935 | 16.5608
6.6236 | 8.1351 | 2.0208 | 2.0312 | 3.1039 | 3.0624 | 7.1559 | 5.1247 | 14.7587 | 16.7899 | 23.9458 | 29.0705
-1.4404 | 6.3879 | 1.752 | 1.628 | 1.7599 | 2.256 | 5.1399 | 3.5119 | 4.9476 | 6.5755 | 11.7155 | 15.2274
3.8707 | 7.5386 | 1.929 | 1.8935 | 2.6451 | 2.7871 | 6.4677 | 4.5741 | 11.4093 | 13.3029 | 19.7705 | 24.3447
-11.3239 | 4.2465 | 1.4225 | 1.1338 | 0.11268 | 1.2676 | 2.669 | 1.5352 | -7.0774 | -5.9436 | -3.2746 | -1.7394
8.374 | 8.5144 | 2.0791 | 2.1187 | 3.3957 | 3.2374 | 7.5935 | 5.4748 | 16.8884 | 19.0071 | 26.6006 | 32.0754
12.9704 | 9.5102 | 2.2323 | 2.3485 | 4.1617 | 3.697 | 8.7426 | 6.3941 | 22.4806 | 24.8291 | 33.5717 | 39.9658
1.7719 | 7.0839 | 1.8591 | 1.7886 | 2.2953 | 2.5772 | 5.943 | 4.1544 | 8.8558 | 10.6444 | 16.5874 | 20.7418
-0.26064 | 6.6435 | 1.7913 | 1.687 | 1.9566 | 2.3739 | 5.4348 | 3.7479 | 6.3829 | 8.0699 | 13.5047 | 17.2526
8.9346 | 8.6358 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7336 | 5.5869 | 17.5704 | 19.7171 | 27.4507 | 33.0376
8.9889 | 8.6476 | 2.0996 | 2.1494 | 3.4981 | 3.2989 | 7.7472 | 5.5978 | 17.6365 | 19.7859 | 27.5332 | 33.1309
5.2835 | 7.8448 | 1.9761 | 1.9642 | 2.8806 | 2.9284 | 6.8209 | 4.8567 | 13.1283 | 15.0925 | 21.9133 | 26.77
9.4524 | 8.748 | 2.1151 | 2.1726 | 3.5754 | 3.3452 | 7.8631 | 5.6905 | 18.2004 | 20.373 | 28.2361 | 33.9266
12.1174 | 9.3254 | 2.2039 | 2.3059 | 4.0196 | 3.6117 | 8.5294 | 6.2235 | 21.4429 | 23.7487 | 32.2781 | 38.5016
2.5021 | 7.2421 | 1.8834 | 1.8251 | 2.417 | 2.6502 | 6.1255 | 4.3004 | 9.7443 | 11.5694 | 17.6949 | 21.9953
0.91537 | 6.8983 | 1.8305 | 1.7458 | 2.1526 | 2.4915 | 5.7288 | 3.9831 | 7.8137 | 9.5595 | 15.2883 | 19.2714
-1.7202 | 6.3273 | 1.7427 | 1.614 | 1.7133 | 2.228 | 5.07 | 3.456 | 4.6071 | 6.2211 | 11.2911 | 14.7471
7.3217 | 8.2864 | 2.0441 | 2.0661 | 3.2203 | 3.1322 | 7.3304 | 5.2643 | 15.608 | 17.6741 | 25.0046 | 30.2689
7.9757 | 8.4281 | 2.0659 | 2.0988 | 3.3293 | 3.1976 | 7.4939 | 5.3951 | 16.4037 | 18.5025 | 25.9965 | 31.3916
-2.8082 | 6.0916 | 1.7064 | 1.5596 | 1.532 | 2.1192 | 4.798 | 3.2384 | 3.2834 | 4.843 | 9.6409 | 12.8793
-1.3037 | 6.4175 | 1.7565 | 1.6348 | 1.7827 | 2.2696 | 5.1741 | 3.5393 | 5.1139 | 6.7487 | 11.9228 | 15.462
0.17091 | 6.737 | 1.8057 | 1.7085 | 2.0285 | 2.4171 | 5.5427 | 3.8342 | 6.9079 | 8.6165 | 14.1592 | 17.9934
-7.6486 | 5.0428 | 1.545 | 1.3176 | 0.72523 | 1.6351 | 3.5878 | 2.2703 | -2.6058 | -1.2883 | 2.2996 | 4.5698
7.5446 | 8.3347 | 2.0515 | 2.0772 | 3.2574 | 3.1545 | 7.3862 | 5.3089 | 15.8793 | 17.9565 | 25.3427 | 30.6516
9.7001 | 8.8017 | 2.1233 | 2.185 | 3.6167 | 3.37 | 7.925 | 5.74 | 18.5018 | 20.6869 | 28.6119 | 34.3519
8.0543 | 8.4451 | 2.0685 | 2.1027 | 3.3424 | 3.2054 | 7.5136 | 5.4109 | 16.4994 | 18.6021 | 26.1157 | 31.5266
-1.2755 | 6.4236 | 1.7575 | 1.6362 | 1.7874 | 2.2725 | 5.1811 | 3.5449 | 5.1482 | 6.7844 | 11.9655 | 15.5104
1.6532 | 7.0582 | 1.8551 | 1.7827 | 2.2755 | 2.5653 | 5.9133 | 4.1306 | 8.7114 | 10.494 | 16.4073 | 20.538
4.0014 | 7.567 | 1.9334 | 1.9001 | 2.6669 | 2.8001 | 6.5004 | 4.6003 | 11.5684 | 13.4685 | 19.9689 | 24.5692
9.7211 | 8.8062 | 2.124 | 2.1861 | 3.6202 | 3.3721 | 7.9303 | 5.7442 | 18.5273 | 20.7134 | 28.6437 | 34.3879
18.4405 | 10.6954 | 2.4147 | 2.622 | 5.0734 | 4.2441 | 10.1101 | 7.4881 | 29.136 | 31.758 | 41.8681 | 49.3562
6.7586 | 8.1644 | 2.0253 | 2.0379 | 3.1264 | 3.0759 | 7.1896 | 5.1517 | 14.9229 | 16.9609 | 24.1505 | 29.3022
17.2651 | 10.4408 | 2.3755 | 2.5633 | 4.8775 | 4.1265 | 9.8163 | 7.253 | 27.7059 | 30.2692 | 40.0855 | 47.3385
-4.1978 | 5.7905 | 1.6601 | 1.4901 | 1.3004 | 1.9802 | 4.4506 | 2.9604 | 1.5927 | 3.0828 | 7.5334 | 10.4938
7.4729 | 8.3191 | 2.0491 | 2.0736 | 3.2455 | 3.1473 | 7.3682 | 5.2946 | 15.7921 | 17.8657 | 25.2339 | 30.5285
-0.8847 | 6.5083 | 1.7705 | 1.6558 | 1.8525 | 2.3115 | 5.2788 | 3.6231 | 5.6236 | 7.2794 | 12.5582 | 16.1813
14.5788 | 9.8587 | 2.286 | 2.4289 | 4.4298 | 3.8579 | 9.1447 | 6.7158 | 24.4376 | 26.8665 | 36.0112 | 42.727
0.12537 | 6.7272 | 1.8042 | 1.7063 | 2.0209 | 2.4125 | 5.5313 | 3.8251 | 6.8525 | 8.5588 | 14.0901 | 17.9152
4.2245 | 7.6153 | 1.9408 | 1.9112 | 2.7041 | 2.8224 | 6.5561 | 4.6449 | 11.8398 | 13.751 | 20.3071 | 24.952
15.0219 | 9.9547 | 2.3007 | 2.4511 | 4.5036 | 3.9022 | 9.2555 | 6.8044 | 24.9766 | 27.4277 | 36.6832 | 43.4875
-2.3623 | 6.1882 | 1.7213 | 1.5819 | 1.6063 | 2.1638 | 4.9094 | 3.3275 | 3.8258 | 5.4077 | 10.3171 | 13.6446
-0.42982 | 6.6069 | 1.7857 | 1.6785 | 1.9284 | 2.357 | 5.3925 | 3.714 | 6.177 | 7.8556 | 13.2481 | 16.9621
7.7003 | 8.3684 | 2.0567 | 2.085 | 3.2834 | 3.17 | 7.4251 | 5.3401 | 16.0687 | 18.1537 | 25.5788 | 30.9188
5.0337 | 7.7906 | 1.9678 | 1.9517 | 2.839 | 2.9034 | 6.7584 | 4.8067 | 12.8244 | 14.776 | 21.5345 | 26.3412
3.2793 | 7.4105 | 1.9093 | 1.864 | 2.5465 | 2.7279 | 6.3198 | 4.4559 | 10.6898 | 12.5538 | 18.8736 | 23.3294
-0.40881 | 6.6114 | 1.7864 | 1.6796 | 1.9319 | 2.3591 | 5.3978 | 3.7182 | 6.2026 | 7.8822 | 13.28 | 16.9982
12.3703 | 9.3802 | 2.2123 | 2.3185 | 4.0617 | 3.637 | 8.5926 | 6.2741 | 21.7505 | 24.069 | 32.6616 | 38.9356
9.2318 | 8.7002 | 2.1077 | 2.1616 | 3.5386 | 3.3232 | 7.8079 | 5.6464 | 17.932 | 20.0936 | 27.9015 | 33.5479
9.9205 | 8.8494 | 2.1307 | 2.196 | 3.6534 | 3.392 | 7.9801 | 5.7841 | 18.7699 | 20.9659 | 28.946 | 34.7301
12.8623 | 9.4868 | 2.2287 | 2.3431 | 4.1437 | 3.6862 | 8.7156 | 6.3725 | 22.3491 | 24.6922 | 33.4078 | 39.7802
-2.6898 | 6.1172 | 1.7103 | 1.5655 | 1.5517 | 2.131 | 4.8276 | 3.262 | 3.4274 | 4.9929 | 9.8205 | 13.0825
10.976 | 9.0781 | 2.1659 | 2.2488 | 3.8293 | 3.4976 | 8.244 | 5.9952 | 20.0542 | 22.303 | 30.547 | 36.5422
6.1885 | 8.0408 | 2.0063 | 2.0094 | 3.0314 | 3.0189 | 7.0471 | 5.0377 | 14.2294 | 16.2388 | 23.2859 | 28.3237
-0.0097864 | 6.6979 | 1.7997 | 1.6995 | 1.9984 | 2.399 | 5.4976 | 3.798 | 6.6881 | 8.3876 | 13.8852 | 17.6832
13.3212 | 9.5863 | 2.244 | 2.3661 | 4.2202 | 3.7321 | 8.8303 | 6.4642 | 22.9074 | 25.2735 | 34.1038 | 40.568
-0.72099 | 6.5438 | 1.776 | 1.664 | 1.8798 | 2.3279 | 5.3198 | 3.6558 | 5.8228 | 7.4867 | 12.8065 | 16.4623
-0.99952 | 6.4834 | 1.7667 | 1.65 | 1.8334 | 2.3 | 5.2501 | 3.6001 | 5.4839 | 7.1339 | 12.3841 | 15.9842
1.5168 | 7.0286 | 1.8506 | 1.7758 | 2.2528 | 2.5517 | 5.8792 | 4.1034 | 8.5455 | 10.3213 | 16.2005 | 20.3039
-0.58033 | 6.5743 | 1.7807 | 1.671 | 1.9033 | 2.342 | 5.3549 | 3.6839 | 5.9939 | 7.6649 | 13.0198 | 16.7038
0.17113 | 6.7371 | 1.8057 | 1.7086 | 2.0285 | 2.4171 | 5.5428 | 3.8342 | 6.9082 | 8.6168 | 14.1595 | 17.9938
0.074319 | 6.7161 | 1.8025 | 1.7037 | 2.0124 | 2.4074 | 5.5186 | 3.8149 | 6.7904 | 8.4941 | 14.0127 | 17.8276
1.085 | 6.9351 | 1.8362 | 1.7543 | 2.1808 | 2.5085 | 5.7713 | 4.017 | 8.0201 | 9.7744 | 15.5456 | 19.5626
-3.1212 | 6.0237 | 1.696 | 1.5439 | 1.4798 | 2.0879 | 4.7197 | 3.1758 | 2.9025 | 4.4464 | 9.1661 | 12.3419
6.0895 | 8.0194 | 2.003 | 2.0045 | 3.0149 | 3.009 | 7.0224 | 5.0179 | 14.1089 | 16.1134 | 23.1357 | 28.1536
6.2141 | 8.0464 | 2.0071 | 2.0107 | 3.0357 | 3.0214 | 7.0535 | 5.0428 | 14.2605 | 16.2712 | 23.3247 | 28.3676
9.4624 | 8.7502 | 2.1154 | 2.1731 | 3.5771 | 3.3462 | 7.8656 | 5.6925 | 18.2126 | 20.3857 | 28.2513 | 33.9437
2.7991 | 7.3065 | 1.8933 | 1.84 | 2.4665 | 2.6799 | 6.1998 | 4.3598 | 10.1056 | 11.9456 | 18.1454 | 22.5052
0.57475 | 6.8245 | 1.8192 | 1.7287 | 2.0958 | 2.4575 | 5.6437 | 3.915 | 7.3993 | 9.128 | 14.7717 | 18.6867
9.4411 | 8.7456 | 2.1147 | 2.1721 | 3.5735 | 3.3441 | 7.8603 | 5.6882 | 18.1866 | 20.3587 | 28.219 | 33.9072
-1.3256 | 6.4128 | 1.7558 | 1.6337 | 1.7791 | 2.2674 | 5.1686 | 3.5349 | 5.0872 | 6.7209 | 11.8896 | 15.4244
6.3785 | 8.082 | 2.0126 | 2.0189 | 3.0631 | 3.0379 | 7.0946 | 5.0757 | 14.4605 | 16.4794 | 23.5741 | 28.6498
1.0149 | 6.9199 | 1.8338 | 1.7507 | 2.1692 | 2.5015 | 5.7537 | 4.003 | 7.9348 | 9.6856 | 15.4393 | 19.4423
3.1071 | 7.3732 | 1.9036 | 1.8554 | 2.5178 | 2.7107 | 6.2768 | 4.4214 | 10.4803 | 12.3356 | 18.6124 | 23.0338
8.6083 | 8.5651 | 2.0869 | 2.1304 | 3.4347 | 3.2608 | 7.6521 | 5.5217 | 17.1734 | 19.3038 | 26.9559 | 32.4776
-7.3979 | 5.0971 | 1.5534 | 1.3301 | 0.76701 | 1.6602 | 3.6505 | 2.3204 | -2.3008 | -0.97073 | 2.6798 | 5.0002
9.1391 | 8.6801 | 2.1046 | 2.157 | 3.5232 | 3.3139 | 7.7848 | 5.6278 | 17.8192 | 19.9762 | 27.7609 | 33.3887
10.1185 | 8.8923 | 2.1373 | 2.2059 | 3.6864 | 3.4118 | 8.0296 | 5.8237 | 19.0108 | 21.2168 | 29.2464 | 35.0701
8.8895 | 8.6261 | 2.0963 | 2.1445 | 3.4816 | 3.289 | 7.7224 | 5.5779 | 17.5156 | 19.6601 | 27.3825 | 32.9604
18.1174 | 10.6254 | 2.4039 | 2.6059 | 5.0196 | 4.2117 | 10.0293 | 7.4235 | 28.7428 | 31.3487 | 41.378 | 48.8015
-4.172 | 5.7961 | 1.6609 | 1.4914 | 1.3047 | 1.9828 | 4.457 | 2.9656 | 1.6241 | 3.1155 | 7.5725 | 10.5381
4.7866 | 7.7371 | 1.9596 | 1.9393 | 2.7978 | 2.8787 | 6.6966 | 4.7573 | 12.5236 | 14.463 | 21.1596 | 25.9169
8.5519 | 8.5529 | 2.0851 | 2.1276 | 3.4253 | 3.2552 | 7.638 | 5.5104 | 17.1048 | 19.2324 | 26.8704 | 32.3807
6.8119 | 8.1759 | 2.0271 | 2.0406 | 3.1353 | 3.0812 | 7.203 | 5.1624 | 14.9878 | 17.0284 | 24.2313 | 29.3937
-7.8754 | 4.9937 | 1.5375 | 1.3062 | 0.68743 | 1.6125 | 3.5311 | 2.2249 | -2.8818 | -1.5755 | 1.9556 | 4.1805
3.4751 | 7.4529 | 1.9158 | 1.8738 | 2.5792 | 2.7475 | 6.3688 | 4.495 | 10.9281 | 12.8018 | 19.1706 | 23.6656
-3.9303 | 5.8484 | 1.669 | 1.5035 | 1.345 | 2.007 | 4.5174 | 3.0139 | 1.9181 | 3.4216 | 7.9391 | 10.953
11.6169 | 9.217 | 2.1872 | 2.2808 | 3.9362 | 3.5617 | 8.4042 | 6.1234 | 20.8339 | 23.1148 | 31.519 | 37.6424
6.6067 | 8.1315 | 2.0202 | 2.0303 | 3.1011 | 3.0607 | 7.1517 | 5.1213 | 14.7382 | 16.7685 | 23.9202 | 29.0415
3.6787 | 7.4971 | 1.9226 | 1.8839 | 2.6131 | 2.7679 | 6.4197 | 4.5357 | 11.1758 | 13.0597 | 19.4794 | 24.0151
10.0022 | 8.8671 | 2.1334 | 2.2001 | 3.667 | 3.4002 | 8.0005 | 5.8004 | 18.8693 | 21.0694 | 29.07 | 34.8704
2.8576 | 7.3192 | 1.8953 | 1.8429 | 2.4763 | 2.6858 | 6.2144 | 4.3715 | 10.1768 | 12.0197 | 18.2341 | 22.6056
-5.7356 | 5.4573 | 1.6088 | 1.4132 | 1.0441 | 1.8264 | 4.0661 | 2.6529 | -0.2783 | 1.1349 | 5.201 | 7.8539
-0.24152 | 6.6477 | 1.7919 | 1.6879 | 1.9597 | 2.3758 | 5.4396 | 3.7517 | 6.4062 | 8.0941 | 13.5337 | 17.2854
-1.1184 | 6.4577 | 1.7627 | 1.6441 | 1.8136 | 2.2882 | 5.2204 | 3.5763 | 5.3393 | 6.9834 | 12.2038 | 15.7801
9.8841 | 8.8416 | 1.6146 | 2.1942 | 3.6474 | 3.3884 | 7.971 | 5.7768 | 18.7257 | 20.9199 | 28.891 | 34.6678
-5.5634 | 5.4946 | 1.9328 | 1.4218 | 1.0728 | 1.8437 | 4.1091 | 2.6873 | -0.068833 | 1.353 | 5.4621 | 8.1495
3.9837 | 7.5631 | 2.3331 | 1.8992 | 2.6639 | 2.7984 | 6.4959 | 4.5967 | 11.5468 | 13.446 | 19.9419 | 24.5386
15.9941 | 10.1654 | 1.7859 | 2.4997 | 4.6657 | 3.9994 | 9.4985 | 6.9988 | 26.1595 | 28.6592 | 38.1577 | 45.1566
-0.42261 | 6.6084 | 1.794 | 1.6789 | 1.9296 | 2.3577 | 5.3943 | 3.7155 | 6.1858 | 7.8647 | 13.259 | 16.9745
-0.18131 | 6.6607 | 1.9908 | 1.6909 | 1.9698 | 2.3819 | 5.4547 | 3.7637 | 6.4794 | 8.1703 | 13.625 | 17.3887
5.7226 | 7.9399 | 2.0474 | 1.9861 | 2.9538 | 2.9723 | 6.9306 | 4.9445 | 13.6625 | 15.6486 | 22.5792 | 27.5238
7.4208 | 8.3078 | 2.0177 | 2.071 | 3.2368 | 3.1421 | 7.3552 | 5.2842 | 15.7286 | 17.7997 | 25.1549 | 30.439
6.5317 | 8.1152 | 2.2316 | 2.0266 | 3.0886 | 3.0532 | 7.1329 | 5.1063 | 14.6469 | 16.6735 | 23.8064 | 28.9127
12.9487 | 9.5056 | 2.2484 | 2.3474 | 4.1581 | 3.6949 | 8.7372 | 6.3897 | 22.4543 | 24.8017 | 33.5389 | 39.9286
13.4512 | 9.6144 | 1.8607 | 2.3726 | 4.2419 | 3.7451 | 8.8628 | 6.4902 | 23.0656 | 25.4382 | 34.301 | 40.7912
1.8217 | 7.0947 | 2.0947 | 1.7911 | 2.3036 | 2.5822 | 5.9554 | 4.1643 | 8.9164 | 10.7075 | 16.6629 | 20.8272
8.8397 | 8.6153 | 1.8922 | 2.142 | 3.4733 | 3.284 | 7.7099 | 5.5679 | 17.455 | 19.597 | 27.3069 | 32.8748
2.7666 | 7.2994 | 2.0757 | 1.8383 | 2.4611 | 2.6767 | 6.1916 | 4.3533 | 10.066 | 11.9043 | 18.0959 | 22.4493
8.2722 | 8.4923 | 1.8633 | 2.1136 | 3.3787 | 3.2272 | 7.568 | 5.4544 | 16.7645 | 18.8781 | 26.4461 | 31.9006
1.8989 | 7.1114 | 2.0766 | 1.7949 | 2.3165 | 2.5899 | 5.9747 | 4.1798 | 9.0103 | 10.8052 | 16.7799 | 20.9597
8.2977 | 8.4978 | 2.1503 | 2.1149 | 3.3829 | 3.2298 | 7.5744 | 5.4595 | 16.7955 | 18.9104 | 26.4848 | 31.9444
10.5101 | 8.9772 | 2.0598 | 2.2255 | 3.7517 | 3.451 | 8.1275 | 5.902 | 19.4873 | 21.7128 | 29.8404 | 35.7424
7.7932 | 8.3885 | 2.4427 | 2.0897 | 3.2989 | 3.1793 | 7.4483 | 5.3586 | 16.1817 | 18.2714 | 25.7197 | 31.0784
19.2796 | 10.8773 | 1.7714 | 2.664 | 5.2133 | 4.328 | 10.3199 | 7.6559 | 30.1569 | 32.8209 | 43.1408 | 50.7967
-0.85792 | 6.5141 | 1.9787 | 1.6571 | 1.857 | 2.3142 | 5.2855 | 3.6284 | 5.6562 | 7.3133 | 12.5988 | 16.2272
5.3618 | 7.8617 | 2.1086 | 1.9681 | 2.8936 | 2.9362 | 6.8405 | 4.8724 | 13.2236 | 15.1917 | 22.0321 | 26.9045
9.2577 | 8.7058 | 2.1426 | 2.1629 | 3.543 | 3.3258 | 7.8144 | 5.6515 | 17.9635 | 20.1264 | 27.9408 | 33.5924
10.2787 | 8.9271 | 2.2081 | 2.2139 | 3.7131 | 3.4279 | 8.0697 | 5.8557 | 19.2058 | 21.4197 | 29.4894 | 35.3451
12.2433 | 9.3527 | 1.7133 | 2.3122 | 4.0406 | 3.6243 | 8.5608 | 6.2487 | 21.5961 | 23.9082 | 32.4691 | 38.7177
-2.602 | 6.1362 | 2.0305 | 1.5699 | 1.5663 | 2.1398 | 4.8495 | 3.2796 | 3.5343 | 5.1042 | 9.9537 | 13.2333
6.9152 | 8.1983 | 1.9055 | 2.0458 | 3.1525 | 3.0915 | 7.2288 | 5.183 | 15.1135 | 17.1593 | 24.3881 | 29.5711
3.1651 | 7.3858 | 2.0144 | 1.8583 | 2.5275 | 2.7165 | 6.2913 | 4.433 | 10.5509 | 12.4091 | 18.7004 | 23.1334
6.4306 | 8.0933 | 1.864 | 2.0215 | 3.0718 | 3.0431 | 7.1076 | 5.0861 | 14.5239 | 16.5454 | 23.653 | 28.7391
1.919 | 7.1158 | 1.9736 | 1.7959 | 2.3198 | 2.5919 | 5.9797 | 4.1838 | 9.0347 | 10.8307 | 16.8104 | 20.9942
5.2075 | 7.8283 | 1.9672 | 1.9604 | 2.8679 | 2.9207 | 6.8019 | 4.8415 | 13.0358 | 14.9962 | 21.798 | 26.6395
5.0148 | 7.7865 | 1.9804 | 1.9507 | 2.8358 | 2.9015 | 6.7537 | 4.803 | 12.8013 | 14.7521 | 21.5058 | 26.3087
5.4118 | 7.8725 | 1.82 | 1.9706 | 2.902 | 2.9412 | 6.8529 | 4.8824 | 13.2843 | 15.2549 | 22.1078 | 26.9902
0.60033 | 6.8301 | 2.1284 | 1.73 | 2.1001 | 2.46 | 5.6501 | 3.9201 | 7.4304 | 9.1604 | 14.8105 | 18.7306
9.8505 | 8.8343 | 1.9956 | 2.1925 | 3.6418 | 3.3851 | 7.9626 | 5.7701 | 18.6848 | 20.8773 | 28.84 | 34.6101
5.8682 | 7.9714 | 1.8458 | 1.9934 | 2.978 | 2.9868 | 6.9671 | 4.9736 | 13.8396 | 15.8331 | 22.8001 | 27.7737
1.3746 | 6.9978 | 2.3455 | 1.7687 | 2.2291 | 2.5375 | 5.8436 | 4.0749 | 8.3724 | 10.1411 | 15.9848 | 20.0597
16.3663 | 10.246 | 2.1493 | 2.5183 | 4.7277 | 4.0366 | 9.5916 | 7.0733 | 26.6123 | 29.1306 | 38.7222 | 45.7954
10.4785 | 8.9703 | 2.2881 | 2.2239 | 3.7464 | 3.4479 | 8.1196 | 5.8957 | 19.4488 | 21.6728 | 29.7924 | 35.6881
14.6431 | 9.8727 | 2.1757 | 2.4322 | 4.4405 | 3.8643 | 9.1608 | 6.7286 | 24.5157 | 26.9479 | 36.1087 | 42.8373
11.2705 | 9.1419 | 1.6904 | 2.2635 | 3.8784 | 3.5271 | 8.3176 | 6.0541 | 20.4125 | 22.676 | 30.9936 | 37.0477
-3.2871 | 5.9878 | 1.9339 | 1.5356 | 1.4522 | 2.0713 | 4.6782 | 3.1426 | 2.7008 | 4.2364 | 8.9146 | 12.0572
4.0163 | 7.5702 | 1.9562 | 1.9008 | 2.6694 | 2.8016 | 6.5041 | 4.6033 | 11.5865 | 13.4873 | 19.9914 | 24.5946
4.6864 | 7.7154 | 1.8488 | 1.9343 | 2.7811 | 2.8686 | 6.6716 | 4.7373 | 12.4018 | 14.3361 | 21.0078 | 25.745
1.4634 | 7.0171 | 1.7742 | 1.7732 | 2.2439 | 3.5791 | 5.8659 | 4.0927 | 8.4805 | 10.2536 | 16.1195 | 20.2122
-0.77368 | 6.5324 | 2.193 | 1.6613 | 1.8711 | 1.6857 | 5.3066 | 3.6453 | 5.7587 | 7.42 | 12.7266 | 16.3718
11.7905 | 9.2546 | 1.5619 | 2.2895 | 3.9651 | 2.9119 | 8.4476 | 6.1581 | 21.0451 | 23.3346 | 31.7823 | 37.9404
-7.1426 | 5.1524 | 1.9706 | 1.3429 | 0.80957 | 3.4348 | 3.7144 | 2.3715 | -1.9901 | -0.64725 | 3.5972 | 5.9687
5.1192 | 7.8092 | 2.1449 | 1.956 | 2.8532 | 3.9823 | 6.7798 | 4.8238 | 12.9284 | 14.8844 | 21.7198 | 26.5437
10.3484 | 8.9421 | 2.3274 | 2.2174 | 3.7247 | 2.3004 | 8.0871 | 5.8697 | 19.2905 | 21.5079 | 29.595 | 35.4647
15.8226 | 10.1282 | 1.7668 | 2.4911 | 4.6371 | 1.4393 | 9.4556 | 6.9645 | 25.9508 | 28.442 | 37.8976 | 44.8621
-0.99638 | 6.4841 | 1.4798 | 1.6502 | 1.8339 | 2.1554 | 5.2509 | 3.6007 | 5.4877 | 7.1379 | 12.3888 | 15.9895
-9.6069 | 4.6185 | 1.7185 | 1.2197 | 0.39885 | 2.5843 | 4.8886 | 1.8786 | -4.9884 | -3.7688 | 1.1198 | 2.9984
-2.4456 | 6.1701 | 1.8614 | 1.5777 | 1.5924 | 2.3528 | 5.9607 | 3.3109 | 3.7245 | 5.3022 | 11.2629 | 14.5738
1.8427 | 7.0993 | 1.7843 | 1.7921 | 2.3071 | 2.7307 | 5.3821 | 4.1685 | 8.942 | 10.7341 | 16.1162 | 20.2847
-0.47175 | 6.5978 | 1.9102 | 1.6764 | 1.9214 | 2.5396 | 6.3268 | 3.7057 | 6.126 | 7.8025 | 14.1292 | 17.8349
3.3071 | 7.4165 | 1.8465 | 1.7698 | 2.5512 | 2.4087 | 5.8491 | 4.4614 | 10.7236 | 12.4935 | 18.3426 | 22.804
1.3965 | 7.0026 | 1.8029 | 1.7043 | 2.2327 | 3.3494 | 5.5217 | 4.0793 | 8.399 | 10.1034 | 15.6855 | 19.7648
0.08672 | 6.7188 | 2.1165 | 2.1747 | 2.0145 | 3.9835 | 7.8734 | 3.8173 | 6.8055 | 8.9802 | 16.8536 | 20.671
9.4938 | 8.757 | 2.3278 | 2.4917 | 3.5823 | 3.2911 | 9.4587 | 5.6988 | 18.2508 | 20.7425 | 30.2012 | 35.8999
15.8348 | 10.1309 | 2.097 | 2.1455 | 4.6391 | 3.8318 | 7.7276 | 6.967 | 25.9657 | 28.1112 | 36.5822 | 43.5491
8.9106 | 8.6306 | 2.2773 | 2.4159 | 3.4851 | 2.4722 | 9.0796 | 5.5821 | 17.5412 | 19.9571 | 29.0368 | 34.6189
14.3184 | 9.8023 | 1.8241 | 1.7361 | 4.3864 | 3.1013 | 5.6806 | 6.6637 | 24.1208 | 25.8569 | 33.3446 | 40.0083
0.7224 | 6.8565 | 2.0338 | 2.0506 | 2.1204 | 4.3384 | 7.2532 | 3.9445 | 7.5789 | 9.6296 | 16.8828 | 20.8273
7.0128 | 8.2194 | 2.4461 | 2.6692 | 3.1688 | 1.3988 | 10.346 | 5.2026 | 15.2323 | 17.9015 | 28.2475 | 33.45
19.384 | 10.8999 | 1.4663 | 1.1994 | 5.2307 | 4.3226 | 2.9969 | 7.6768 | 30.2838 | 31.4832 | 41.0365 | 48.7133
19.2262 | 4.5307 | 2.4409 | 2.6613 | 0.33129 | 3.8214 | 10.3065 | 1.7975 | 23.7568 | 26.4181 | 36.7247 | 38.5222
14.2142 | 10.8657 | 2.2738 | 2.4107 | 5.2044 | 2.1505 | 9.0535 | 7.6452 | 25.0798 | 27.4905 | 36.5441 | 44.1893
-2.4952 | 9.7797 | 1.7168 | 1.5752 | 4.369 | 3.5234 | 4.8762 | 6.6428 | 7.2846 | 8.8598 | 16.7522 | 23.395
11.2336 | 6.1594 | 2.1745 | 2.2617 | 1.5841 | 4.0163 | 8.3084 | 3.301 | 17.393 | 19.6547 | 27.9631 | 31.2641
16.1635 | 9.134 | 2.3388 | 2.5082 | 3.8723 | 2.7069 | 9.5409 | 6.0467 | 25.2974 | 27.8056 | 37.3465 | 43.3932
3.0691 | 10.2021 | 1.9023 | 1.8535 | 4.2369 | 3.7422 | 6.2673 | 7.0327 | 13.2711 | 15.1246 | 23.1037 | 30.1364
13.4216 | 7.365 | 2.2474 | 2.3711 | 4.3798 | 3.8279 | 8.8554 | 4.4138 | 20.7866 | 23.1577 | 32.0131 | 36.4269
14.2791 | 9.608 | 2.276 | 2.414 | 2.4376 | 2.6625 | 9.0698 | 6.4843 | 23.8871 | 26.301 | 35.3708 | 41.8551
2.6253 | 9.7938 | 1.8875 | 1.8313 | 0.72184 | 1.6331 | 6.1563 | 6.6558 | 12.4191 | 14.2504 | 20.4067 | 27.0625
-7.6689 | 7.2688 | 1.5444 | 1.3166 | 4.3164 | 3.7899 | 3.5828 | 4.3251 | -0.40013 | 0.91643 | 9.0227 | 13.3478
13.8987 | 5.0384 | 2.2633 | 2.3949 | 4.5377 | 3.9226 | 8.9747 | 2.2662 | 18.9371 | 21.332 | 30.3067 | 32.5729
15.2263 | 9.7114 | 2.3075 | 2.4613 | 5.1783 | 4.307 | 9.3066 | 6.5797 | 24.9377 | 27.399 | 36.8844 | 43.4641
19.0701 | 9.999 | 2.4357 | 2.6535 | 1.7349 | 2.2409 | 10.2675 | 6.8453 | 29.0691 | 31.7226 | 41.9902 | 48.8354
-1.5907 | 10.8319 | 1.747 | 1.6205 | 3.4667 | 3.28 | 5.1023 | 7.614 | 9.2411 | 10.8616 | 17.6083 | 25.2223
8.8001 | 6.3553 | 2.0933 | 2.14 | 3.3661 | 3.2197 | 7.7 | 3.4819 | 15.1554 | 17.2954 | 24.9955 | 28.4773
8.1966 | 8.6067 | 2.0732 | 2.1098 | 2.9229 | 2.9538 | 7.5492 | 5.56 | 16.8033 | 18.9131 | 26.4623 | 32.0223
5.5376 | 8.4759 | 1.9846 | 1.9769 | 2.3602 | 2.6161 | 6.8844 | 5.4393 | 14.0135 | 15.9904 | 22.8748 | 28.3141
2.1614 | 7.8998 | 1.872 | 1.8081 | 2.489 | 2.6934 | 6.0403 | 4.9075 | 10.0612 | 11.8692 | 17.9096 | 22.8171
2.9341 | 7.1683 | 1.8978 | 1.8467 | 3.9122 | 3.5473 | 6.2335 | 4.2323 | 10.1024 | 11.9491 | 19.4087 | 23.641
11.4734 | 7.3357 | 2.1824 | 2.2737 | 4.5221 | 3.9133 | 8.3684 | 4.3868 | 18.8092 | 21.0828 | 29.5182 | 33.9051
15.1327 | 9.1859 | 2.3044 | 2.4566 | 3.0515 | 3.0309 | 9.2832 | 6.0947 | 24.3186 | 26.7752 | 36.0584 | 42.1531
6.309 | 9.9788 | 2.0103 | 2.0154 | 3.3918 | 3.2351 | 7.0772 | 6.8265 | 16.2877 | 18.3032 | 25.3804 | 32.207
8.3508 | 8.0669 | 2.0784 | 2.1175 | 3.9998 | 3.5999 | 7.5877 | 5.0618 | 16.4178 | 18.5353 | 26.135 | 31.1968
11.9988 | 8.5093 | 2.2 | 2.2999 | 3.3774 | 3.2265 | 8.4997 | 5.4702 | 20.5081 | 22.808 | 31.3077 | 36.7779
8.2645 | 9.2997 | 2.0755 | 2.1132 | 2.4958 | 2.6975 | 7.5661 | 6.1998 | 17.5643 | 19.6775 | 27.2436 | 33.4434
2.9748 | 8.4906 | 1.8992 | 1.8487 | 3.6696 | 3.4018 | 6.2437 | 5.4529 | 11.4654 | 13.3142 | 20.3856 | 25.8385
10.0178 | 7.3445 | 2.1339 | 2.2009 | 2.3627 | 2.6176 | 8.0044 | 4.395 | 17.3623 | 19.5632 | 27.5677 | 31.9626
2.1761 | 8.8705 | 1.8725 | 1.8088 | 3.6992 | 3.4195 | 6.044 | 5.8036 | 11.0466 | 12.8554 | 19.9742 | 25.7777
10.1953 | 7.1715 | 2.1398 | 2.2098 | 2.0614 | 2.4368 | 8.0488 | 4.2352 | 17.3668 | 19.5765 | 27.6253 | 31.8606
0.36812 | 8.909 | 1.8123 | 1.7184 | 3.4738 | 3.2843 | 5.592 | 5.8391 | 9.2771 | 10.9955 | 17.7536 | 23.5926
8.8428 | 6.7798 | 2.0948 | 2.1421 | 2.5607 | 2.7364 | 7.7107 | 3.8736 | 15.6225 | 17.7647 | 25.4753 | 29.349
3.3639 | 8.6159 | 1.9121 | 1.8682 | 3.7195 | 3.4317 | 6.341 | 5.5686 | 11.9799 | 13.8481 | 20.9992 | 26.5678
10.3169 | 7.4289 | 2.1439 | 2.2158 | 4.0749 | 3.645 | 8.0792 | 4.4728 | 17.7457 | 19.9616 | 28.0408 | 32.5136
12.4496 | 8.9353 | 2.215 | 2.3225 | 3.8485 | 3.5091 | 8.6124 | 5.8634 | 21.3849 | 23.7074 | 32.3198 | 38.1832
11.0913 | 9.3974 | 2.1697 | 2.2546 | 1.6992 | 2.2195 | 8.2728 | 6.2899 | 20.4887 | 22.7433 | 31.0161 | 37.306
-1.8049 | 9.1031 | 1.7398 | 1.6098 | 3.2226 | 3.1336 | 5.0488 | 6.0183 | 7.2982 | 8.908 | 15.2642 | 21.2824
7.3357 | 6.3089 | 2.0445 | 2.0668 | 4.1585 | 3.6951 | 7.3339 | 3.439 | 13.6446 | 15.7114 | 23.565 | 27.004
12.9509 | 8.2894 | 2.2317 | 2.3475 | 1.8244 | 2.2947 | 8.7377 | 5.2671 | 21.2403 | 23.5878 | 32.3255 | 37.5927
-1.0534 | 9.506 | 1.7649 | 1.6473 | 4.1219 | 3.6732 | 5.2366 | 6.3902 | 8.4526 | 10.0999 | 17.895 | 24.2852
12.7317 | 6.4718 | 2.2244 | 2.3366 | 2.2937 | 2.5762 | 8.6829 | 3.5893 | 19.2034 | 21.54 | 30.2229 | 33.8122
1.7625 | 9.4585 | 1.8587 | 1.7881 | 4.4139 | 3.8484 | 5.9406 | 6.3463 | 11.221 | 13.0091 | 21.2714 | 27.6177
14.4836 | 7.0819 | 2.2828 | 2.4242 | 2.818 | 2.8908 | 9.1209 | 4.1525 | 21.5654 | 23.9896 | 33.1105 | 37.263
4.908 | 9.8381 | 1.9636 | 1.9454 | 4.2124 | 3.7275 | 6.727 | 6.6967 | 14.7461 | 16.6915 | 24.6314 | 31.3281
13.2747 | 7.7634 | 2.2425 | 2.3637 | 2.6176 | 2.7706 | 8.8187 | 4.7816 | 21.0381 | 23.4018 | 32.2205 | 37.0021
3.7058 | 9.5762 | 1.9235 | 1.8853 | 4.0942 | 3.6565 | 6.4265 | 6.4549 | 13.282 | 15.1673 | 22.9179 | 29.3729
12.5649 | 7.5029 | 2.2188 | 2.3282 | 2.7136 | 2.8282 | 8.6412 | 4.5412 | 20.0678 | 22.3961 | 31.0373 | 35.5785
4.2816 | 9.4224 | 1.9427 | 1.9141 | 1.5496 | 2.1298 | 6.5704 | 6.313 | 13.704 | 15.618 | 22.1884 | 28.5014
-2.7021 | 7.6277 | 1.7099 | 1.5649 | 4.8215 | 4.0929 | 4.8245 | 4.6563 | 4.9255 | 6.4904 | 15.4048 | 20.0611
16.9289 | 6.1145 | 2.3643 | 2.5464 | 1.5666 | 2.14 | 9.7322 | 3.2596 | 23.0434 | 25.5899 | 35.3221 | 38.5817
-2.6001 | 10.3679 | 1.7133 | 1.57 | 2.43 | 2.658 | 4.85 | 7.1858 | 7.7678 | 9.3378 | 14.4258 | 21.6116
2.5801 | 6.1366 | 1.886 | 1.829 | 0.74844 | 1.6491 | 6.145 | 3.28 | 8.7168 | 10.5458 | 16.6908 | 19.9708
-7.5094 | 7.259 | 1.5497 | 1.3245 | 3.3043 | 3.1826 | 3.6227 | 4.316 | -0.25035 | 1.0742 | 7.5611 | 11.8771
7.826 | 5.073 | 2.0609 | 2.0913 | 0.096747 | 1.258 | 7.4565 | 2.2981 | 12.899 | 14.9903 | 22.4468 | 24.7449
-11.4195 | 8.3956 | 1.4193 | 1.129 | 1.1507 | 1.8904 | 2.6451 | 5.3652 | -3.0239 | -1.8949 | 1.1462 | 6.5114
-5.0961 | 4.2258 | 1.6301 | 1.4452 | 2.318 | 2.5908 | 4.226 | 1.5161 | -0.87032 | 0.57488 | 5.4837 | 6.9998
1.9081 | 5.5958 | 1.8636 | 1.7954 | 3.9068 | 3.5441 | 5.977 | 2.7808 | 7.5039 | 9.2993 | 16.7502 | 19.531
11.4408 | 7.1134 | 2.1814 | 2.272 | 3.9987 | 3.5992 | 8.3602 | 4.1816 | 18.5542 | 20.8263 | 29.1865 | 33.3681
11.9924 | 9.1788 | 2.1997 | 2.2996 | 2.5211 | 2.7127 | 8.4981 | 6.0882 | 21.1712 | 23.4708 | 31.9689 | 38.0571
3.1269 | 9.2983 | 1.9042 | 1.8563 | 2.6077 | 2.7646 | 6.2817 | 6.1985 | 12.4252 | 14.2815 | 20.5633 | 26.7617
3.646 | 7.3775 | 1.9215 | 1.8823 | 3.8705 | 3.5223 | 6.4115 | 4.4254 | 11.0234 | 12.9057 | 20.2986 | 24.724
11.2232 | 7.49 | 2.1741 | 2.2612 | 4.6272 | 3.9763 | 8.3058 | 4.5292 | 18.7131 | 20.9743 | 29.5778 | 34.107
15.7633 | 9.1317 | 2.3254 | 2.4882 | 3.3338 | 3.2003 | 9.4408 | 6.0446 | 24.895 | 27.3831 | 36.8239 | 42.8686
8.0029 | 10.1154 | 2.0668 | 2.1001 | 4.3526 | 3.8116 | 7.5007 | 6.9527 | 18.1183 | 20.2185 | 28.3827 | 35.3354
14.1159 | 8.434 | 2.2705 | 2.4058 | 3.1711 | 3.1026 | 9.029 | 5.4006 | 22.5498 | 24.9556 | 33.9846 | 39.3852
7.0265 | 9.7584 | 2.0342 | 2.0513 | 1.0701 | 1.842 | 7.2566 | 6.6232 | 16.7849 | 18.8362 | 26.0929 | 32.716
-5.5795 | 8.2224 | 1.614 | 1.421 | 3.1699 | 3.1019 | 4.1051 | 5.2053 | 2.6429 | 4.0639 | 10.3358 | 15.5411
7.0195 | 5.4911 | 2.034 | 2.051 | 2.44 | 2.664 | 7.2549 | 2.6841 | 12.5106 | 14.5615 | 21.8164 | 24.5005
2.6398 | 8.2209 | 1.888 | 1.832 | 3.9164 | 3.5498 | 6.1599 | 5.2039 | 10.8607 | 12.6926 | 20.1589 | 25.3627
11.4983 | 7.272 | 2.1833 | 2.2749 | 2.2667 | 2.56 | 8.3746 | 4.328 | 18.7703 | 21.0452 | 29.4197 | 33.7477
1.6003 | 9.1913 | 1.8533 | 1.78 | 0.78163 | 1.669 | 5.9001 | 6.0997 | 10.7916 | 12.5716 | 18.4716 | 24.5713
-7.3102 | 7.0467 | 1.5563 | 1.3345 | 4.619 | 3.9714 | 3.6724 | 4.1201 | -0.26348 | 1.071 | 9.6614 | 13.7815
15.714 | 5.1161 | 2.3238 | 2.4857 | 4.1687 | 3.7012 | 9.4285 | 2.338 | 20.8301 | 23.3158 | 32.7443 | 35.0823
13.0123 | 10.1047 | 2.2337 | 2.3506 | 0.93932 | 1.7636 | 8.7531 | 6.9428 | 23.117 | 25.4677 | 34.2207 | 41.1635
-6.3641 | 9.5193 | 1.5879 | 1.3818 | 3.1006 | 3.0604 | 3.909 | 6.4025 | 3.1553 | 4.5371 | 10.698 | 17.1005
6.6035 | 5.3211 | 2.0201 | 2.0302 | 3.8656 | 3.5194 | 7.1509 | 2.5272 | 11.9246 | 13.9548 | 21.3398 | 23.867
11.1936 | 8.1308 | 2.1731 | 2.2597 | 2.3992 | 2.6395 | 8.2984 | 5.1207 | 19.3244 | 21.584 | 29.8824 | 35.0031
2.3952 | 9.1253 | 1.8798 | 1.8198 | 4.4598 | 3.8759 | 6.0988 | 6.0387 | 11.5205 | 13.3403 | 21.6759 | 27.7146
14.7587 | 7.219 | 2.292 | 2.4379 | 4.6718 | 4.0031 | 9.1897 | 4.279 | 21.9776 | 24.4156 | 33.6053 | 37.8843
16.0308 | 9.8977 | 2.3344 | 2.5015 | 2.5827 | 2.7496 | 9.5077 | 6.7517 | 25.9285 | 28.4301 | 37.9378 | 44.6895
3.496 | 10.1733 | 1.9165 | 1.8748 | 2.8107 | 2.8864 | 6.374 | 7.0062 | 13.6693 | 15.5441 | 21.9181 | 28.9243
4.8644 | 7.4575 | 1.9621 | 1.9432 | 4.7599 | 4.0559 | 6.7161 | 4.4992 | 12.3218 | 14.265 | 23.0809 | 27.5801
16.5595 | 7.7539 | 2.352 | 2.528 | 5.0114 | 4.2069 | 9.6399 | 4.7729 | 24.3134 | 26.8414 | 36.4813 | 41.2541
18.0686 | 10.2879 | 2.4023 | 2.6034 | 4.3153 | 3.7892 | 10.0172 | 7.1119 | 28.3565 | 30.9599 | 40.9771 | 48.089
13.8917 | 10.6149 | 2.2631 | 2.3946 | 3.384 | 3.2304 | 8.9729 | 7.4137 | 24.5065 | 26.9011 | 35.874 | 43.2878
8.3042 | 9.7099 | 2.0768 | 2.1152 | 2.9744 | 2.9846 | 7.576 | 6.5783 | 18.014 | 20.1292 | 27.7053 | 34.2836
5.8464 | 8.4992 | 1.9949 | 1.9923 | 4.3016 | 3.781 | 6.9616 | 5.4608 | 14.3457 | 16.338 | 24.4206 | 29.8814
13.8097 | 7.9667 | 2.2603 | 2.3905 | 3.6323 | 3.3794 | 8.9524 | 4.9693 | 21.7765 | 24.1669 | 33.1194 | 38.0887
9.7938 | 9.6921 | 2.1265 | 2.1897 | 3.7296 | 3.4377 | 7.9485 | 6.5619 | 19.4859 | 21.6756 | 29.6241 | 36.186
10.3775 | 8.822 | 2.1459 | 2.2189 | 4.6453 | 3.9872 | 8.0944 | 5.7588 | 19.1995 | 21.4184 | 30.0509 | 35.8096
15.8718 | 8.9485 | 2.3291 | 2.4936 | 2.8253 | 2.8952 | 9.468 | 5.8755 | 24.8203 | 27.3139 | 36.7818 | 42.6573
4.9521 | 10.1389 | 1.9651 | 1.9476 | 2.6385 | 2.7831 | 6.738 | 6.9744 | 15.091 | 17.0386 | 23.7766 | 30.751
3.8311 | 7.7729 | 1.9277 | 1.8916 | 2.9743 | 2.9846 | 6.4578 | 4.7904 | 11.604 | 13.4956 | 19.9533 | 24.7438
5.8458 | 7.5301 | 1.9949 | 1.9923 | 1.9744 | 2.3846 | 6.9614 | 4.5662 | 13.3758 | 15.3681 | 22.3296 | 26.8958
-0.15369 | 7.9666 | 1.7949 | 1.6923 | 3.4835 | 3.2901 | 5.4616 | 4.9692 | 7.8129 | 9.5052 | 16.2788 | 21.248
8.9011 | 6.6667 | 2.0967 | 2.1451 | 2.8402 | 2.9041 | 7.7253 | 3.7693 | 15.5678 | 17.7128 | 25.4381 | 29.2073
5.0411 | 8.6286 | 1.968 | 1.9521 | 2.9244 | 2.9547 | 6.7603 | 5.5802 | 13.6697 | 15.6217 | 22.382 | 27.9622
5.5467 | 7.7922 | 1.9849 | 1.9773 | 2.7834 | 2.87 | 6.8867 | 4.8082 | 13.3389 | 15.3163 | 22.2029 | 27.0112
4.7002 | 7.9018 | 1.9567 | 1.935 | 2.2444 | 2.5466 | 6.675 | 4.9093 | 12.602 | 14.537 | 21.212 | 26.1214
1.4663 | 7.7184 | 1.8489 | 1.7733 | 3.148 | 3.0888 | 5.8666 | 4.74 | 9.1847 | 10.958 | 17.1947 | 21.9348
6.8879 | 7.0177 | 2.0296 | 2.0444 | 1.6145 | 2.1687 | 7.222 | 4.0933 | 13.9056 | 15.95 | 23.1719 | 27.2652
-2.3129 | 8.1924 | 1.7229 | 1.5844 | 2.1422 | 2.4853 | 4.9218 | 5.1776 | 5.8795 | 7.4639 | 12.3856 | 17.5632
0.85301 | 6.1989 | 1.8284 | 1.7427 | 3.3938 | 3.2363 | 5.7133 | 3.3374 | 7.0519 | 8.7945 | 15.4247 | 18.7621
8.363 | 6.8848 | 2.0788 | 2.1181 | 2.8631 | 2.9179 | 7.5907 | 3.9706 | 15.2478 | 17.366 | 24.9567 | 28.9273
5.1786 | 8.512 | 1.9726 | 1.9589 | 2.7811 | 2.8686 | 6.7946 | 5.4726 | 13.6906 | 15.6495 | 22.4441 | 27.9167
4.6863 | 7.822 | 1.9562 | 1.9343 | 1.7183 | 2.231 | 6.6716 | 4.8357 | 12.5083 | 14.4427 | 21.1142 | 25.95
-1.69 | 7.7154 | 1.7437 | 1.6155 | 2.6544 | 2.7926 | 5.0775 | 4.7373 | 6.0254 | 7.6409 | 13.0879 | 17.8252
3.9263 | 6.3338 | 1.9309 | 1.8963 | 2.8467 | 2.908 | 6.4816 | 3.462 | 10.2601 | 12.1564 | 18.638 | 22.1
5.0801 | 7.5507 | 1.9693 | 1.954 | 2.9045 | 2.9427 | 6.77 | 4.5853 | 12.6307 | 14.5847 | 21.3548 | 25.94
5.4268 | 7.8007 | 1.9809 | 1.9713 | 4.1252 | 3.6751 | 6.8567 | 4.816 | 13.2274 | 15.1988 | 22.9991 | 27.8151
12.7511 | 7.8758 | 2.225 | 2.3376 | 3.8581 | 3.5149 | 8.6878 | 4.8854 | 20.6269 | 22.9645 | 31.6522 | 36.5376
11.1487 | 9.4627 | 2.1716 | 2.2574 | 3.4723 | 3.2834 | 8.2872 | 6.3502 | 20.6114 | 22.8689 | 31.1561 | 37.5063
8.834 | 9.1156 | 2.0945 | 2.1417 | 3.2206 | 3.1323 | 7.7085 | 6.0297 | 17.9496 | 20.0913 | 27.7998 | 33.8295
7.3235 | 8.614 | 2.0441 | 2.0662 | 3.2162 | 3.1297 | 7.3309 | 5.5668 | 15.9375 | 18.0037 | 25.3346 | 30.9014
7.2969 | 8.2868 | 2.0432 | 2.0648 | 3.2464 | 3.1478 | 7.3242 | 5.2647 | 15.5837 | 17.6485 | 24.9727 | 30.2374
7.4785 | 8.281 | 2.0493 | 2.0739 | 1.9766 | 2.386 | 7.3696 | 5.2594 | 15.7595 | 17.8334 | 25.203 | 30.4624
-0.14037 | 8.3203 | 1.7953 | 1.693 | 2.9701 | 2.9821 | 5.4649 | 5.2957 | 8.18 | 9.873 | 15.8251 | 21.1208
5.8206 | 6.6696 | 1.994 | 1.991 | 1.6681 | 2.2008 | 6.9552 | 3.7719 | 12.4902 | 14.4813 | 21.4364 | 25.2083
-1.9916 | 7.9611 | 1.7336 | 1.6004 | 4.1051 | 3.6631 | 5.0021 | 4.9641 | 5.9696 | 7.57 | 15.3382 | 20.3023
12.6307 | 6.2685 | 2.221 | 2.3315 | 3.1409 | 3.0845 | 8.6577 | 3.4017 | 18.8992 | 21.2308 | 29.8884 | 33.2901
6.8453 | 9.4367 | 2.0282 | 2.0423 | 1.4547 | 2.0728 | 7.2113 | 6.3261 | 16.282 | 18.3243 | 25.5356 | 31.8617
-3.272 | 8.1832 | 1.6909 | 1.5364 | 2.8971 | 2.9383 | 4.682 | 5.1691 | 4.9112 | 6.4476 | 12.283 | 17.452
5.3827 | 5.9911 | 1.9794 | 1.9691 | 4.3756 | 3.8253 | 6.8457 | 3.1456 | 11.3738 | 13.3429 | 21.5439 | 24.6895
14.2535 | 7.8663 | 2.2751 | 2.4127 | 2.174 | 2.5044 | 9.0634 | 4.8765 | 22.1197 | 24.5324 | 33.5958 | 38.4723
1.0437 | 9.7882 | 1.8348 | 1.7522 | 2.1204 | 2.4722 | 5.7609 | 6.6507 | 10.832 | 12.5842 | 18.3451 | 24.9958
0.72232 | 6.9261 | 1.8241 | 1.7361 | 3.0018 | 3.0011 | 5.6806 | 4.0087 | 7.6485 | 9.3846 | 15.3874 | 19.3962
6.0106 | 6.8565 | 2.0004 | 2.0005 | 2.5764 | 2.7458 | 7.0026 | 3.9445 | 12.8671 | 14.8676 | 21.8703 | 25.8147
3.4584 | 8.0023 | 1.9153 | 1.8729 | 0.37298 | 1.4238 | 6.3646 | 5.0021 | 11.4607 | 13.3337 | 19.6983 | 24.7004
-9.7621 | 7.4493 | 1.4746 | 1.2119 | 2.7077 | 2.8246 | 3.0595 | 4.4917 | -2.3128 | -1.1009 | 4.4314 | 8.9231
4.2463 | 4.5849 | 1.9415 | 1.9123 | 2.3095 | 2.5857 | 6.5616 | 1.8476 | 8.8311 | 10.7435 | 17.305 | 19.1526
1.8569 | 7.62 | 1.8619 | 1.7928 | 3.3009 | 3.1806 | 5.9642 | 4.6493 | 9.4769 | 11.2698 | 17.7513 | 22.4005
7.8055 | 7.1023 | 2.0602 | 2.0903 | 1.9738 | 2.3843 | 7.4514 | 4.1714 | 14.9079 | 16.9981 | 24.4495 | 28.6209
-0.15737 | 8.3912 | 1.7948 | 1.6921 | 2.3419 | 2.6052 | 5.4607 | 5.3611 | 8.2338 | 9.926 | 15.3866 | 20.7477
2.0516 | 6.6659 | 1.8684 | 1.8026 | 4.6939 | 4.0163 | 6.0129 | 3.7685 | 8.7175 | 10.5201 | 19.2303 | 22.9989
16.1634 | 7.1445 | 2.3388 | 2.5082 | 2.4881 | 2.6928 | 9.5409 | 4.2103 | 23.308 | 25.8161 | 35.357 | 39.5673
2.9283 | 10.2021 | 1.8976 | 1.8464 | 1.8229 | 2.2937 | 6.2321 | 7.0327 | 13.1304 | 14.9768 | 21.2089 | 28.2416
-1.0626 | 7.3345 | 1.7646 | 1.6469 | 3.6826 | 3.4096 | 5.2344 | 4.3857 | 6.2719 | 7.9188 | 15.0109 | 19.3966
10.0956 | 6.4698 | 2.1365 | 2.2048 | 2.7751 | 2.865 | 8.0239 | 3.5875 | 16.5653 | 18.7701 | 26.794 | 30.3815
4.6504 | 8.8874 | 1.955 | 1.9325 | 4.5711 | 3.9427 | 6.6626 | 5.8191 | 13.5378 | 15.4703 | 23.9841 | 29.8032
15.4267 | 7.7076 | 2.3142 | 2.4713 | 4.305 | 3.783 | 9.3567 | 4.7301 | 23.1343 | 25.6057 | 34.9624 | 39.6924
13.8297 | 10.0425 | 2.261 | 2.3915 | 2.4924 | 2.6954 | 8.9574 | 6.8853 | 23.8722 | 26.2637 | 35.2211 | 42.1065
2.9545 | 9.6964 | 1.8985 | 1.8477 | 3.7825 | 3.4695 | 6.2386 | 6.5659 | 12.6509 | 14.4986 | 21.7506 | 28.3166
10.6949 | 7.3401 | 2.1565 | 2.2347 | 2.8622 | 2.9173 | 8.1737 | 4.3909 | 18.035 | 20.2698 | 28.4435 | 32.8344
5.1733 | 9.0172 | 1.9724 | 1.9587 | 3.1984 | 3.119 | 6.7933 | 5.939 | 14.1905 | 16.1492 | 22.9425 | 28.8815
7.1904 | 7.8209 | 2.0397 | 2.0595 | 1.3371 | 2.0022 | 7.2976 | 4.8347 | 15.0112 | 17.0708 | 24.3683 | 29.203
-3.9776 | 8.2579 | 1.6674 | 1.5011 | 2.9624 | 2.9775 | 4.5056 | 5.2381 | 4.2803 | 5.7815 | 11.7213 | 16.9594
5.7745 | 5.8382 | 1.9925 | 1.9887 | 3.2345 | 3.1407 | 6.9436 | 3.0045 | 11.6127 | 13.6015 | 20.5451 | 23.5496
7.4073 | 7.9511 | 2.0469 | 2.0704 | 3.9585 | 3.5751 | 7.3518 | 4.9549 | 15.3584 | 17.4288 | 24.9625 | 29.9174
11.7513 | 8.3049 | 2.1917 | 2.2876 | 2.7908 | 2.8745 | 8.4378 | 5.2815 | 20.0562 | 22.3438 | 30.7816 | 36.063
4.7449 | 9.2461 | 1.9582 | 1.9372 | 1.7315 | 2.2389 | 6.6862 | 6.1503 | 13.991 | 15.9283 | 22.6145 | 28.7648
-1.6111 | 7.7281 | 1.7463 | 1.6194 | 2.8944 | 2.9366 | 5.0972 | 4.749 | 6.1169 | 7.7364 | 13.5674 | 18.3163
5.3662 | 6.3509 | 1.9789 | 1.9683 | 3.0773 | 3.0464 | 6.8415 | 3.4778 | 11.7171 | 13.6854 | 20.527 | 24.0047
6.4638 | 7.8627 | 2.0155 | 2.0232 | 2.5815 | 2.7489 | 7.116 | 4.8732 | 14.3265 | 16.3497 | 23.4657 | 28.3389
3.4889 | 8.1005 | 1.9163 | 1.8744 | 1.8665 | 2.3199 | 6.3722 | 5.0928 | 11.5894 | 13.4638 | 19.836 | 24.9288
-0.80079 | 7.4559 | 1.7733 | 1.66 | 4.0774 | 3.6465 | 5.2998 | 4.4978 | 6.6551 | 8.3151 | 16.039 | 20.5368
12.4646 | 6.5265 | 2.2155 | 2.3232 | 2.1699 | 2.5019 | 8.6161 | 3.6398 | 18.9911 | 21.3143 | 29.9305 | 33.5703
1.0194 | 9.4007 | 1.834 | 1.751 | 4.2351 | 3.7411 | 5.7549 | 6.2929 | 10.4201 | 12.1711 | 20.1472 | 26.4401
13.4105 | 6.9209 | 2.247 | 2.3705 | 1.9519 | 2.3711 | 8.8526 | 4.0039 | 20.3314 | 22.7019 | 31.5546 | 35.5585
-0.28881 | 9.6056 | 1.7904 | 1.6856 | 2.9194 | 2.9516 | 5.4278 | 6.4821 | 9.3168 | 11.0024 | 16.8734 | 23.3555
5.5165 | 6.6374 | 1.9839 | 1.9758 | 3.7465 | 3.4479 | 6.8791 | 3.7422 | 12.1539 | 14.1297 | 21.3241 | 25.0664
10.479 | 7.8952 | 2.1493 | 2.2239 | 2.4963 | 2.6978 | 8.1197 | 4.9033 | 18.3742 | 20.5982 | 28.7179 | 33.6212
2.978 | 8.9704 | 1.8993 | 1.8489 | 4.1729 | 3.7037 | 6.2445 | 5.8958 | 11.9484 | 13.7973 | 21.6739 | 27.5697
13.0371 | 7.3452 | 2.2346 | 2.3519 | 5.043 | 4.2258 | 8.7593 | 4.3956 | 20.3823 | 22.7342 | 32.0031 | 36.3986
18.2582 | 9.5247 | 2.4086 | 2.6129 | 1.3136 | 1.9881 | 10.0646 | 6.4074 | 27.7829 | 30.3958 | 40.4604 | 46.8678
-4.1186 | 10.6559 | 1.6627 | 1.4941 | 3.5481 | 3.3289 | 4.4704 | 7.4516 | 6.5374 | 8.0314 | 14.9084 | 22.36
9.2885 | 5.8076 | 2.1096 | 2.1644 | 2.9226 | 2.9536 | 7.8221 | 2.9763 | 15.0962 | 17.2606 | 25.0828 | 28.059
5.5355 | 8.7125 | 1.9845 | 1.9768 | 5.2821 | 4.3692 | 6.8839 | 5.6577 | 14.2481 | 16.2248 | 25.8761 | 31.5339
19.6924 | 7.8994 | 2.4564 | 2.6846 | 1.3027 | 1.9816 | 10.4231 | 4.9071 | 27.5918 | 30.2764 | 40.6995 | 45.6066
-4.1837 | 10.9667 | 1.6605 | 1.4908 | 2.4833 | 2.69 | 4.4541 | 7.7385 | 6.7829 | 8.2738 | 13.447 | 21.1855
2.8996 | 5.7935 | 1.8967 | 1.845 | 4.6737 | 4.0042 | 6.2249 | 2.9633 | 8.6931 | 10.5381 | 19.216 | 22.1792
16.0422 | 7.3282 | 2.3347 | 2.5021 | 2.969 | 2.9814 | 9.5106 | 4.3799 | 23.3705 | 25.8726 | 35.3831 | 39.7631
5.8138 | 10.1758 | 1.9938 | 1.9907 | 2.7846 | 2.8708 | 6.9534 | 7.0084 | 15.9896 | 17.9803 | 24.9337 | 31.9422
4.7076 | 7.9596 | 1.9569 | 1.9354 | 2.5954 | 2.7572 | 6.6769 | 4.9628 | 12.6673 | 14.6026 | 21.2795 | 26.2423
3.5724 | 7.72 | 1.9191 | 1.8786 | 4.397 | 3.8382 | 6.3931 | 4.7415 | 11.2924 | 13.171 | 21.4063 | 26.1478
14.3822 | 7.474 | 2.2794 | 2.4191 | 2.2841 | 2.5705 | 9.0955 | 4.5145 | 21.8562 | 24.2753 | 33.3709 | 37.8854
1.7047 | 9.8161 | 1.8568 | 1.7852 | 3.83 | 3.498 | 5.9262 | 6.6764 | 11.5209 | 13.3061 | 20.6341 | 27.3105
10.98 | 7.0694 | 2.166 | 2.249 | 3.431 | 3.2586 | 8.245 | 4.1409 | 18.0494 | 20.2984 | 28.5434 | 32.6843
8.5858 | 9.079 | 2.0862 | 2.1293 | 2.0667 | 2.44 | 7.6465 | 5.996 | 17.6648 | 19.7941 | 27.4406 | 33.4366
0.40007 | 8.5603 | 1.8133 | 1.72 | 3.5941 | 3.3565 | 5.6 | 5.5172 | 8.9603 | 10.6803 | 17.6309 | 23.1481
9.5647 | 6.7867 | 2.1188 | 2.1782 | 3.2553 | 3.1532 | 7.8912 | 3.88 | 16.3514 | 18.5296 | 26.4208 | 30.3008
7.5316 | 8.7723 | 2.0511 | 2.0766 | 3.3519 | 3.2111 | 7.3829 | 5.7129 | 16.3039 | 18.3805 | 25.7634 | 31.4763
8.1115 | 8.3318 | 2.0704 | 2.1056 | 2.3366 | 2.602 | 7.5279 | 5.3063 | 16.4433 | 18.5489 | 26.0767 | 31.3831
2.0197 | 8.4575 | 1.8673 | 1.801 | 2.4549 | 2.6729 | 6.0049 | 5.4223 | 10.4772 | 12.2782 | 18.2831 | 23.7054
2.7292 | 7.1376 | 1.891 | 1.8365 | 3.3007 | 3.1804 | 6.1823 | 4.2039 | 9.8668 | 11.7033 | 18.1844 | 22.3883
7.8041 | 7.2913 | 2.0601 | 2.0902 | 3.2421 | 3.1452 | 7.451 | 4.3458 | 15.0954 | 17.1856 | 24.6366 | 28.9825
7.4524 | 8.3909 | 2.0484 | 2.0726 | 3.8806 | 3.5284 | 7.3631 | 5.3608 | 15.8432 | 17.9159 | 25.3248 | 30.6856
11.2836 | 8.3147 | 2.1761 | 2.2642 | 5.2907 | 4.3744 | 8.3209 | 5.2905 | 19.5983 | 21.8625 | 31.5276 | 36.8181
19.7442 | 9.1448 | 2.4581 | 2.6872 | 2.4446 | 2.6667 | 10.4361 | 6.0567 | 28.889 | 31.5762 | 42.0123 | 48.069
2.6675 | 10.9779 | 1.8889 | 1.8334 | 2.5403 | 2.7242 | 6.1669 | 7.7488 | 13.6454 | 15.4788 | 21.6456 | 29.3945
3.2415 | 7.278 | 1.9081 | 1.8621 | 1.9326 | 2.3596 | 6.3104 | 4.3335 | 10.5195 | 12.3816 | 18.692 | 23.0255
-0.40435 | 7.4023 | 1.7865 | 1.6798 | 3.4463 | 3.2678 | 5.3989 | 4.4483 | 6.998 | 8.6778 | 15.3919 | 19.8402
4.7076
3.5724
14.3822
1.7047
10.98
8.5858
0.40007
9.5647
7.5316
8.1115
2.0197
2.7292
7.8041
7.4524
11.2836
19.7442
2.6675
3.2415

## test activity A
A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | diff
-12.9745 | 3.8889 | 1.3675 | 1.0513 | -0.16242 | 1.1025 | 2.2564 | 1.2051 | -9.0857 | -8.0344 | -5.778 | -4.5729 | -12.9645 | 3.8889 | 1.3675 | 1.0513 | -0.16242 | 1.1025 | 2.2564 | 1.2051 | -9.0757 | -8.0244 | -5.768 | -4.5629 | 0.01
-0.12216 | 6.6735 | 1.7959 | 1.6939 | 1.9796 | 2.3878 | 5.4695 | 3.7756 | 6.5514 | 8.2453 | 13.7147 | 17.4903 | -0.11216 | 6.6735 | 1.7959 | 1.6939 | 1.9796 | 2.3878 | 5.4695 | 3.7756 | 6.5614 | 8.2553 | 13.7247 | 17.5003 | 0.01
6.9139 | 8.198 | 2.0305 | 2.0457 | 3.1523 | 3.0914 | 7.2285 | 5.1828 | 15.1119 | 17.1576 | 24.3861 | 29.5689 | 6.9239 | 8.198 | 2.0305 | 2.0457 | 3.1523 | 3.0914 | 7.2285 | 5.1828 | 15.1219 | 17.1676 | 24.3961 | 29.5789 | 0.01
12.6187 | 9.4341 | 2.2206 | 2.3309 | 4.1031 | 3.6619 | 8.6547 | 6.3237 | 22.0528 | 24.3837 | 33.0384 | 39.3622 | 12.6287 | 9.4341 | 2.2206 | 2.3309 | 4.1031 | 3.6619 | 8.6547 | 6.3237 | 22.0628 | 24.3937 | 33.0484 | 39.3722 | 0.01
2.4444 | 7.2296 | 1.8815 | 1.8222 | 2.4074 | 2.6444 | 6.1111 | 4.2889 | 9.674 | 11.4962 | 17.6073 | 21.8962 | 2.4544 | 7.2296 | 1.8815 | 1.8222 | 2.4074 | 2.6444 | 6.1111 | 4.2889 | 9.684 | 11.5062 | 17.6173 | 21.9062 | 0.01
13.5518 | 9.6362 | 2.2517 | 2.3776 | 4.2586 | 3.7552 | 8.888 | 6.5104 | 23.188 | 25.5656 | 34.4536 | 40.9639 | 13.5618 | 9.6362 | 2.2517 | 2.3776 | 4.2586 | 3.7552 | 8.888 | 6.5104 | 23.198 | 25.5756 | 34.4636 | 40.9739 | 0.01
9.2237 | 8.6985 | 2.1075 | 2.1612 | 3.5373 | 3.3224 | 7.8059 | 5.6447 | 17.9221 | 20.0833 | 27.8892 | 33.5339 | 9.2337 | 8.6985 | 2.1075 | 2.1612 | 3.5373 | 3.3224 | 7.8059 | 5.6447 | 17.9321 | 20.0933 | 27.8992 | 33.5439 | 0.01
13.2479 | 9.5704 | 2.2416 | 2.3624 | 4.208 | 3.7248 | 8.812 | 6.4496 | 22.8182 | 25.1806 | 33.9926 | 40.4422 | 13.2579 | 9.5704 | 2.2416 | 2.3624 | 4.208 | 3.7248 | 8.812 | 6.4496 | 22.8282 | 25.1906 | 34.0026 | 40.4522 | 0.01
14.8387 | 9.9151 | 2.2946 | 2.4419 | 4.4731 | 3.8839 | 9.2097 | 6.7677 | 24.7538 | 27.1957 | 36.4054 | 43.1731 | 14.8487 | 9.9151 | 2.2946 | 2.4419 | 4.4731 | 3.8839 | 9.2097 | 6.7677 | 24.7638 | 27.2057 | 36.4154 | 43.1831 | 0.01
5.5377 | 7.8998 | 1.9846 | 1.9769 | 2.9229 | 2.9538 | 6.8844 | 4.9075 | 13.4375 | 15.4144 | 22.2988 | 27.2063 | 5.5477 | 7.8998 | 1.9846 | 1.9769 | 2.9229 | 2.9538 | 6.8844 | 4.9075 | 13.4475 | 15.4244 | 22.3088 | 27.2163 | 0.01
3.6914 | 7.4998 | 1.923 | 1.8846 | 2.6152 | 2.7691 | 6.4229 | 4.5383 | 11.1913 | 13.0758 | 19.4987 | 24.037 | 3.7014 | 7.4998 | 1.923 | 1.8846 | 2.6152 | 2.7691 | 6.4229 | 4.5383 | 11.2013 | 13.0858 | 19.5087 | 24.047 | 0.01
15.412 | 10.0393 | 2.3137 | 2.4706 | 4.5687 | 3.9412 | 9.353 | 6.8824 | 25.4513 | 27.9219 | 37.2749 | 44.1573 | 15.422 | 10.0393 | 2.3137 | 2.4706 | 4.5687 | 3.9412 | 9.353 | 6.8824 | 25.4613 | 27.9319 | 37.2849 | 44.1673 | 0.01
-1.8093 | 6.308 | 1.7397 | 1.6095 | 1.6984 | 2.2191 | 5.0477 | 3.4381 | 4.4986 | 6.1082 | 11.1558 | 14.594 | -1.7993 | 6.308 | 1.7397 | 1.6095 | 1.6984 | 2.2191 | 5.0477 | 3.4381 | 4.5086 | 6.1182 | 11.1658 | 14.604 | 0.01
5.3552 | 7.8603 | 1.9785 | 1.9678 | 2.8925 | 2.9355 | 6.8388 | 4.871 | 13.2155 | 15.1833 | 22.0221 | 26.8931 | 5.3652 | 7.8603 | 1.9785 | 1.9678 | 2.8925 | 2.9355 | 6.8388 | 4.871 | 13.2255 | 15.1933 | 22.0321 | 26.9031 | 0.01
3.6258 | 7.4856 | 1.9209 | 1.8813 | 2.6043 | 2.7626 | 6.4065 | 4.5252 | 11.1114 | 12.9927 | 19.3991 | 23.9243 | 3.6358 | 7.4856 | 1.9209 | 1.8813 | 2.6043 | 2.7626 | 6.4065 | 4.5252 | 11.1214 | 13.0027 | 19.4091 | 23.9343 | 0.01
17.2865 | 10.4454 | 2.3762 | 2.5643 | 4.8811 | 4.1286 | 9.8216 | 7.2573 | 27.7319 | 30.2962 | 40.1178 | 47.3751 | 17.2965 | 10.4454 | 2.3762 | 2.5643 | 4.8811 | 4.1286 | 9.8216 | 7.2573 | 27.7419 | 30.3062 | 40.1278 | 47.3851 | 0.01
-1.2041 | 6.4391 | 1.7599 | 1.6398 | 1.7993 | 2.2796 | 5.199 | 3.5592 | 5.2351 | 6.8749 | 12.0738 | 15.633 | -1.1941 | 6.4391 | 1.7599 | 1.6398 | 1.7993 | 2.2796 | 5.199 | 3.5592 | 5.2451 | 6.8849 | 12.0838 | 15.643 | 0.01
10.4295 | 8.9597 | 2.1476 | 2.2215 | 3.7382 | 3.4429 | 8.1074 | 5.8859 | 19.3892 | 21.6107 | 29.7181 | 35.604 | 10.4395 | 8.9597 | 2.1476 | 2.2215 | 3.7382 | 3.4429 | 8.1074 | 5.8859 | 19.3992 | 21.6207 | 29.7281 | 35.614 | 0.01
3.5508 | 7.4693 | 1.9184 | 1.8775 | 2.5918 | 2.7551 | 6.3877 | 4.5102 | 11.0202 | 12.8977 | 19.2854 | 23.7956 | 3.5608 | 7.4693 | 1.9184 | 1.8775 | 2.5918 | 2.7551 | 6.3877 | 4.5102 | 11.0302 | 12.9077 | 19.2954 | 23.8056 | 0.01
8.8773 | 8.6234 | 2.0959 | 2.1439 | 3.4795 | 3.2877 | 7.7193 | 5.5755 | 17.5007 | 19.6445 | 27.3638 | 32.9393 | 8.8873 | 8.6234 | 2.0959 | 2.1439 | 3.4795 | 3.2877 | 7.7193 | 5.5755 | 17.5107 | 19.6545 | 27.3738 | 32.9493 | 0.01
10.0205 | 8.8711 | 2.134 | 2.201 | 3.6701 | 3.402 | 8.0051 | 5.8041 | 18.8916 | 21.0926 | 29.0977 | 34.9018 | 10.0305 | 8.8711 | 2.134 | 2.201 | 3.6701 | 3.402 | 8.0051 | 5.8041 | 18.9016 | 21.1026 | 29.1077 | 34.9118 | 0.01
8.7605 | 8.5981 | 2.092 | 2.138 | 3.4601 | 3.276 | 7.6901 | 5.5521 | 17.3586 | 19.4966 | 27.1867 | 32.7388 | 8.7705 | 8.5981 | 2.092 | 2.138 | 3.4601 | 3.276 | 7.6901 | 5.5521 | 17.3686 | 19.5066 | 27.1967 | 32.7488 | 0.01
13.6101 | 9.6489 | 2.2537 | 2.3805 | 4.2684 | 3.761 | 8.9025 | 6.522 | 23.259 | 25.6395 | 34.542 | 41.064 | 13.6201 | 9.6489 | 2.2537 | 2.3805 | 4.2684 | 3.761 | 8.9025 | 6.522 | 23.269 | 25.6495 | 34.552 | 41.074 | 0.01
-4.2589 | 5.7772 | 1.658 | 1.4871 | 1.2902 | 1.9741 | 4.4353 | 2.9482 | 1.5183 | 3.0053 | 7.4406 | 10.3888 | -4.2489 | 5.7772 | 1.658 | 1.4871 | 1.2902 | 1.9741 | 4.4353 | 2.9482 | 1.5283 | 3.0153 | 7.4506 | 10.3988 | 0.01
7.7808 | 8.3858 | 2.0594 | 2.089 | 3.2968 | 3.1781 | 7.4452 | 5.3562 | 16.1666 | 18.2557 | 25.7008 | 31.057 | 7.7908 | 8.3858 | 2.0594 | 2.089 | 3.2968 | 3.1781 | 7.4452 | 5.3562 | 16.1766 | 18.2657 | 25.7108 | 31.067 | 0.01
9.0241 | 8.6552 | 2.1008 | 2.1512 | 3.504 | 3.3024 | 7.756 | 5.6048 | 17.6794 | 19.8306 | 27.5866 | 33.1914 | 9.0341 | 8.6552 | 2.1008 | 2.1512 | 3.504 | 3.3024 | 7.756 | 5.6048 | 17.6894 | 19.8406 | 27.5966 | 33.2014 | 0.01
0.87462 | 6.8895 | 1.8292 | 1.7437 | 2.1458 | 2.4875 | 5.7187 | 3.9749 | 7.7641 | 9.5079 | 15.2265 | 19.2014 | 0.88462 | 6.8895 | 1.8292 | 1.7437 | 2.1458 | 2.4875 | 5.7187 | 3.9749 | 7.7741 | 9.5179 | 15.2365 | 19.2114 | 0.01
4.3537 | 7.6433 | 1.9451 | 1.9177 | 2.7256 | 2.8354 | 6.5884 | 4.6707 | 11.997 | 13.9147 | 20.5031 | 25.1739 | 4.3637 | 7.6433 | 1.9451 | 1.9177 | 2.7256 | 2.8354 | 6.5884 | 4.6707 | 12.007 | 13.9247 | 20.5131 | 25.1839 | 0.01
7.5191 | 8.3291 | 2.0506 | 2.076 | 3.2532 | 3.1519 | 7.3798 | 5.3038 | 15.8482 | 17.9242 | 25.3039 | 30.6078 | 7.5291 | 8.3291 | 2.0506 | 2.076 | 3.2532 | 3.1519 | 7.3798 | 5.3038 | 15.8582 | 17.9342 | 25.3139 | 30.6178 | 0.01
-1.0782 | 6.4664 | 1.7641 | 1.6461 | 1.8203 | 2.2922 | 5.2304 | 3.5844 | 5.3882 | 7.0343 | 12.2647 | 15.8491 | -1.0682 | 6.4664 | 1.7641 | 1.6461 | 1.8203 | 2.2922 | 5.2304 | 3.5844 | 5.3982 | 7.0443 | 12.2747 | 15.8591 | 0.01
-5.1061 | 5.5937 | 1.6298 | 1.4447 | 1.149 | 1.8894 | 4.2235 | 2.7788 | 0.48754 | 1.9322 | 6.1557 | 8.9345 | -5.0961 | 5.5937 | 1.6298 | 1.4447 | 1.149 | 1.8894 | 4.2235 | 2.7788 | 0.49754 | 1.9422 | 6.1657 | 8.9445 | 0.01
1.3629 | 6.9953 | 1.8454 | 1.7681 | 2.2271 | 2.5363 | 5.8407 | 4.0726 | 8.3582 | 10.1263 | 15.967 | 20.0396 | 1.3729 | 6.9953 | 1.8454 | 1.7681 | 2.2271 | 2.5363 | 5.8407 | 4.0726 | 8.3682 | 10.1363 | 15.977 | 20.0496 | 0.01
1.8639 | 7.1038 | 1.8621 | 1.7932 | 2.3106 | 2.5864 | 5.966 | 4.1728 | 8.9677 | 10.7609 | 16.7269 | 20.8996 | 1.8739 | 7.1038 | 1.8621 | 1.7932 | 2.3106 | 2.5864 | 5.966 | 4.1728 | 8.9777 | 10.7709 | 16.7369 | 20.9096 | 0.01
9.9802 | 8.8624 | 2.1327 | 2.199 | 3.6634 | 3.398 | 7.995 | 5.796 | 18.8426 | 21.0416 | 29.0366 | 34.8327 | 9.9902 | 8.8624 | 2.1327 | 2.199 | 3.6634 | 3.398 | 7.995 | 5.796 | 18.8526 | 21.0516 | 29.0466 | 34.8427 | 0.01
7.6476 | 8.357 | 2.0549 | 2.0824 | 3.2746 | 3.1648 | 7.4119 | 5.3295 | 16.0046 | 18.087 | 25.4989 | 30.8284 | 7.6576 | 8.357 | 2.0549 | 2.0824 | 3.2746 | 3.1648 | 7.4119 | 5.3295 | 16.0146 | 18.097 | 25.5089 | 30.8384 | 0.01
11.5709 | 9.207 | 2.1857 | 2.2785 | 3.9285 | 3.5571 | 8.3927 | 6.1142 | 20.778 | 23.0565 | 31.4492 | 37.5634 | 11.5809 | 9.207 | 2.1857 | 2.2785 | 3.9285 | 3.5571 | 8.3927 | 6.1142 | 20.788 | 23.0665 | 31.4592 | 37.5734 | 0.01
2.211 | 7.179 | 1.8737 | 1.8105 | 2.3685 | 2.6211 | 6.0527 | 4.2422 | 9.39 | 11.2006 | 17.2533 | 21.4955 | 2.221 | 7.179 | 1.8737 | 1.8105 | 2.3685 | 2.6211 | 6.0527 | 4.2422 | 9.4 | 11.2106 | 17.2633 | 21.5055 | 0.01
8.1676 | 8.4696 | 2.0723 | 2.1084 | 3.3613 | 3.2168 | 7.5419 | 5.4335 | 16.6372 | 18.7456 | 26.2875 | 31.721 | 8.1776 | 8.4696 | 2.0723 | 2.1084 | 3.3613 | 3.2168 | 7.5419 | 5.4335 | 16.6472 | 18.7556 | 26.2975 | 31.731 | 0.01
-1.5632 | 6.3613 | 1.7479 | 1.6218 | 1.7395 | 2.2437 | 5.1092 | 3.4874 | 4.7981 | 6.42 | 11.5292 | 15.0165 | -1.5532 | 6.3613 | 1.7479 | 1.6218 | 1.7395 | 2.2437 | 5.1092 | 3.4874 | 4.8081 | 6.43 | 11.5392 | 15.0265 | 0.01
6.51 | 8.1105 | 2.017 | 2.0255 | 3.085 | 3.051 | 7.1275 | 5.102 | 14.6205 | 16.646 | 23.7735 | 28.8754 | 6.52 | 8.1105 | 2.017 | 2.0255 | 3.085 | 3.051 | 7.1275 | 5.102 | 14.6305 | 16.656 | 23.7835 | 28.8854 | 0.01
9.2137 | 8.6963 | 2.1071 | 2.1607 | 3.5356 | 3.3214 | 7.8034 | 5.6427 | 17.91 | 20.0707 | 27.8741 | 33.5169 | 9.2237 | 8.6963 | 2.1071 | 2.1607 | 3.5356 | 3.3214 | 7.8034 | 5.6427 | 17.92 | 20.0807 | 27.8841 | 33.5269 | 0.01
2.0475 | 7.1436 | 1.8683 | 1.8024 | 2.3413 | 2.6048 | 6.0119 | 4.2095 | 9.1911 | 10.9935 | 17.0054 | 21.2149 | 2.0575 | 7.1436 | 1.8683 | 1.8024 | 2.3413 | 2.6048 | 6.0119 | 4.2095 | 9.2011 | 11.0035 | 17.0154 | 21.2249 | 0.01
2.251 | 7.1877 | 1.875 | 1.8125 | 2.3752 | 2.6251 | 6.0627 | 4.2502 | 9.4387 | 11.2513 | 17.314 | 21.5642 | 2.261 | 7.1877 | 1.875 | 1.8125 | 2.3752 | 2.6251 | 6.0627 | 4.2502 | 9.4487 | 11.2613 | 17.324 | 21.5742 | 0.01
3.4527 | 7.4481 | 1.9151 | 1.8726 | 2.5755 | 2.7453 | 6.3632 | 4.4905 | 10.9008 | 12.7734 | 19.1366 | 23.6272 | 3.4627 | 7.4481 | 1.9151 | 1.8726 | 2.5755 | 2.7453 | 6.3632 | 4.4905 | 10.9108 | 12.7834 | 19.1466 | 23.6372 | 0.01
-0.171 | 6.663 | 1.7943 | 1.6915 | 1.9715 | 2.3829 | 5.4573 | 3.7658 | 6.492 | 8.1834 | 13.6407 | 17.4065 | -0.161 | 6.663 | 1.7943 | 1.6915 | 1.9715 | 2.3829 | 5.4573 | 3.7658 | 6.502 | 8.1934 | 13.6507 | 17.4165 | 0.01
2.2975 | 7.1978 | 1.8766 | 1.8149 | 2.3829 | 2.6297 | 6.0744 | 4.2595 | 9.4953 | 11.3101 | 17.3845 | 21.644 | 2.3075 | 7.1978 | 1.8766 | 1.8149 | 2.3829 | 2.6297 | 6.0744 | 4.2595 | 9.5053 | 11.3201 | 17.3945 | 21.654 | 0.01
0.11826 | 6.7256 | 1.8039 | 1.7059 | 2.0197 | 2.4118 | 5.5296 | 3.8237 | 6.8439 | 8.5498 | 14.0794 | 17.903 | 0.12826 | 6.7256 | 1.8039 | 1.7059 | 2.0197 | 2.4118 | 5.5296 | 3.8237 | 6.8539 | 8.5598 | 14.0894 | 17.913 | 0.01
5.5591 | 7.9045 | 1.9853 | 1.978 | 2.9265 | 2.9559 | 6.8898 | 4.9118 | 13.4636 | 15.4416 | 22.3313 | 27.2432 | 5.5691 | 7.9045 | 1.9853 | 1.978 | 2.9265 | 2.9559 | 6.8898 | 4.9118 | 13.4736 | 15.4516 | 22.3413 | 27.2532 | 0.01
2.3412 | 7.2073 | 1.878 | 1.8171 | 2.3902 | 2.6341 | 6.0853 | 4.2682 | 9.5484 | 11.3655 | 17.4508 | 21.719 | 2.3512 | 7.2073 | 1.878 | 1.8171 | 2.3902 | 2.6341 | 6.0853 | 4.2682 | 9.5584 | 11.3755 | 17.4608 | 21.729 | 0.01
8.1691 | 8.47 | 2.0723 | 2.1085 | 3.3615 | 3.2169 | 7.5423 | 5.4338 | 16.639 | 18.7475 | 26.2897 | 31.7235 | 8.1791 | 8.47 | 2.0723 | 2.1085 | 3.3615 | 3.2169 | 7.5423 | 5.4338 | 16.649 | 18.7575 | 26.2997 | 31.7335 | 0.01
8.3035 | 8.4991 | 2.0768 | 2.1152 | 3.3839 | 3.2303 | 7.5759 | 5.4607 | 16.8026 | 18.9177 | 26.4936 | 31.9543 | 8.3135 | 8.4991 | 2.0768 | 2.1152 | 3.3839 | 3.2303 | 7.5759 | 5.4607 | 16.8126 | 18.9277 | 26.5036 | 31.9643 | 0.01
10.4961 | 8.9742 | 2.1499 | 2.2248 | 3.7493 | 3.4496 | 8.124 | 5.8992 | 19.4702 | 21.695 | 29.8191 | 35.7183 | 10.5061 | 8.9742 | 2.1499 | 2.2248 | 3.7493 | 3.4496 | 8.124 | 5.8992 | 19.4802 | 21.705 | 29.8291 | 35.7283 | 0.01
10.5815 | 8.9927 | 2.1527 | 2.2291 | 3.7636 | 3.4582 | 8.1454 | 5.9163 | 19.5742 | 21.8033 | 29.9486 | 35.8649 | 10.5915 | 8.9927 | 2.1527 | 2.2291 | 3.7636 | 3.4582 | 8.1454 | 5.9163 | 19.5842 | 21.8133 | 29.9586 | 35.8749 | 0.01
5.8599 | 7.9696 | 1.9953 | 1.993 | 2.9766 | 2.986 | 6.965 | 4.972 | 13.8295 | 15.8225 | 22.7875 | 27.7595 | 5.8699 | 7.9696 | 1.9953 | 1.993 | 2.9766 | 2.986 | 6.965 | 4.972 | 13.8395 | 15.8325 | 22.7975 | 27.7695 | 0.01
14.7012 | 9.8853 | 2.29 | 2.4351 | 4.4502 | 3.8701 | 9.1753 | 6.7402 | 24.5864 | 27.0215 | 36.1968 | 42.937 | 14.7112 | 9.8853 | 2.29 | 2.4351 | 4.4502 | 3.8701 | 9.1753 | 6.7402 | 24.5964 | 27.0315 | 36.2068 | 42.947 | 0.01
8.3236 | 8.5034 | 2.0775 | 2.1162 | 3.3873 | 3.2324 | 7.5809 | 5.4647 | 16.827 | 18.9432 | 26.5241 | 31.9888 | 8.3336 | 8.5034 | 2.0775 | 2.1162 | 3.3873 | 3.2324 | 7.5809 | 5.4647 | 16.837 | 18.9532 | 26.5341 | 31.9988 | 0.01
8.3401 | 8.507 | 2.078 | 2.117 | 3.39 | 3.234 | 7.585 | 5.468 | 16.8471 | 18.9641 | 26.5492 | 32.0172 | 8.3501 | 8.507 | 2.078 | 2.117 | 3.39 | 3.234 | 7.585 | 5.468 | 16.8571 | 18.9741 | 26.5592 | 32.0272 | 0.01
10.3472 | 8.9419 | 2.1449 | 2.2174 | 3.7245 | 3.4347 | 8.0868 | 5.8694 | 19.289 | 21.5064 | 29.5932 | 35.4626 | 10.3572 | 8.9419 | 2.1449 | 2.2174 | 3.7245 | 3.4347 | 8.0868 | 5.8694 | 19.299 | 21.5164 | 29.6032 | 35.4726 | 0.01
14.4633 | 9.8337 | 2.2821 | 2.4232 | 4.4105 | 3.8463 | 9.1158 | 6.6927 | 24.297 | 26.7201 | 35.836 | 42.5286 | 14.4733 | 9.8337 | 2.2821 | 2.4232 | 4.4105 | 3.8463 | 9.1158 | 6.6927 | 24.307 | 26.7301 | 35.846 | 42.5386 | 0.01
-3.5127 | 5.9389 | 1.6829 | 1.5244 | 1.4146 | 2.0487 | 4.6218 | 3.0975 | 2.4263 | 3.9506 | 8.5725 | 11.6699 | -3.5027 | 5.9389 | 1.6829 | 1.5244 | 1.4146 | 2.0487 | 4.6218 | 3.0975 | 2.4363 | 3.9606 | 8.5825 | 11.6799 | 0.01
5.4776 | 7.8868 | 1.9826 | 1.9739 | 2.9129 | 2.9478 | 6.8694 | 4.8955 | 13.3644 | 15.3383 | 22.2077 | 27.1032 | 5.4876 | 7.8868 | 1.9826 | 1.9739 | 2.9129 | 2.9478 | 6.8694 | 4.8955 | 13.3744 | 15.3483 | 22.2177 | 27.1132 | 0.01
5.2807 | 7.8442 | 1.976 | 1.964 | 2.8801 | 2.9281 | 6.8202 | 4.8561 | 13.1249 | 15.0889 | 21.9091 | 26.7653 | 5.2907 | 7.8442 | 1.976 | 1.964 | 2.8801 | 2.9281 | 6.8202 | 4.8561 | 13.1349 | 15.0989 | 21.9191 | 26.7753 | 0.01
7.9784 | 8.4286 | 2.0659 | 2.0989 | 3.3297 | 3.1978 | 7.4946 | 5.3957 | 16.407 | 18.5059 | 26.0005 | 31.3962 | 7.9884 | 8.4286 | 2.0659 | 2.0989 | 3.3297 | 3.1978 | 7.4946 | 5.3957 | 16.417 | 18.5159 | 26.0105 | 31.4062 | 0.01
13.8033 | 9.6907 | 2.2601 | 2.3902 | 4.3006 | 3.7803 | 8.9508 | 6.5607 | 23.494 | 25.8842 | 34.835 | 41.3957 | 13.8133 | 9.6907 | 2.2601 | 2.3902 | 4.3006 | 3.7803 | 8.9508 | 6.5607 | 23.504 | 25.8942 | 34.845 | 41.4057 | 0.01
8.5439 | 8.5512 | 2.0848 | 2.1272 | 3.424 | 3.2544 | 7.636 | 5.5088 | 17.0951 | 19.2223 | 26.8583 | 32.367 | 8.5539 | 8.5512 | 2.0848 | 2.1272 | 3.424 | 3.2544 | 7.636 | 5.5088 | 17.1051 | 19.2323 | 26.8683 | 32.377 | 0.01
4.4437 | 7.6628 | 1.9481 | 1.9222 | 2.7406 | 2.8444 | 6.6109 | 4.6887 | 12.1065 | 14.0287 | 20.6396 | 25.3283 | 4.4537 | 7.6628 | 1.9481 | 1.9222 | 2.7406 | 2.8444 | 6.6109 | 4.6887 | 12.1165 | 14.0387 | 20.6496 | 25.3383 | 0.01
7.7456 | 8.3782 | 2.0582 | 2.0873 | 3.2909 | 3.1746 | 7.4364 | 5.3491 | 16.1238 | 18.2111 | 25.6475 | 30.9967 | 7.7556 | 8.3782 | 2.0582 | 2.0873 | 3.2909 | 3.1746 | 7.4364 | 5.3491 | 16.1338 | 18.2211 | 25.6575 | 31.0067 | 0.01
-2.7103 | 6.1128 | 1.7097 | 1.5645 | 1.5483 | 2.129 | 4.8224 | 3.2579 | 3.4024 | 4.9669 | 9.7893 | 13.0473 | -2.7003 | 6.1128 | 1.7097 | 1.5645 | 1.5483 | 2.129 | 4.8224 | 3.2579 | 3.4124 | 4.9769 | 9.7993 | 13.0573 | 0.01
10.561 | 8.9882 | 2.152 | 2.2281 | 3.7602 | 3.4561 | 8.1403 | 5.9122 | 19.5493 | 21.7773 | 29.9176 | 35.8298 | 10.571 | 8.9882 | 2.152 | 2.2281 | 3.7602 | 3.4561 | 8.1403 | 5.9122 | 19.5593 | 21.7873 | 29.9276 | 35.8398 | 0.01
4.0867 | 7.5855 | 1.9362 | 1.9043 | 2.6811 | 2.8087 | 6.5217 | 4.6173 | 11.6721 | 13.5765 | 20.0982 | 24.7155 | 4.0967 | 7.5855 | 1.9362 | 1.9043 | 2.6811 | 2.8087 | 6.5217 | 4.6173 | 11.6821 | 13.5865 | 20.1082 | 24.7255 | 0.01
-2.8232 | 6.0883 | 1.7059 | 1.5588 | 1.5295 | 2.1177 | 4.7942 | 3.2354 | 3.2652 | 4.824 | 9.6182 | 12.8536 | -2.8132 | 6.0883 | 1.7059 | 1.5588 | 1.5295 | 2.1177 | 4.7942 | 3.2354 | 3.2752 | 4.834 | 9.6282 | 12.8636 | 0.01
4.6997 | 7.7183 | 1.9567 | 1.935 | 2.7833 | 2.87 | 6.6749 | 4.7399 | 12.418 | 14.353 | 21.0279 | 25.7678 | 4.7097 | 7.7183 | 1.9567 | 1.935 | 2.7833 | 2.87 | 6.6749 | 4.7399 | 12.428 | 14.363 | 21.0379 | 25.7778 | 0.01
9.2885 | 8.7125 | 2.1096 | 2.1644 | 3.5481 | 3.3288 | 7.8221 | 5.6577 | 18.0009 | 20.1654 | 27.9875 | 33.6452 | 9.2985 | 8.7125 | 2.1096 | 2.1644 | 3.5481 | 3.3288 | 7.8221 | 5.6577 | 18.0109 | 20.1754 | 27.9975 | 33.6552 | 0.01
4.1946 | 7.6088 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5486 | 4.6389 | 11.8034 | 13.7131 | 20.2618 | 24.9007 | 4.2046 | 7.6088 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5486 | 4.6389 | 11.8134 | 13.7231 | 20.2718 | 24.9107 | 0.01
17.7331 | 10.5422 | 2.3911 | 2.5867 | 4.9555 | 4.1733 | 9.9333 | 7.3466 | 28.2753 | 30.862 | 40.7953 | 48.1419 | 17.7431 | 10.5422 | 2.3911 | 2.5867 | 4.9555 | 4.1733 | 9.9333 | 7.3466 | 28.2853 | 30.872 | 40.8053 | 48.1519 | 0.01
5.1638 | 7.8188 | 1.9721 | 1.9582 | 2.8606 | 2.9164 | 6.791 | 4.8328 | 12.9827 | 14.9409 | 21.7318 | 26.5646 | 5.1738 | 7.8188 | 1.9721 | 1.9582 | 2.8606 | 2.9164 | 6.791 | 4.8328 | 12.9927 | 14.9509 | 21.7418 | 26.5746 | 0.01
-1.7584 | 6.319 | 1.7414 | 1.6121 | 1.7069 | 2.2242 | 5.0604 | 3.4483 | 4.5607 | 6.1727 | 11.2331 | 14.6815 | -1.7484 | 6.319 | 1.7414 | 1.6121 | 1.7069 | 2.2242 | 5.0604 | 3.4483 | 4.5707 | 6.1827 | 11.2431 | 14.6915 | 0.01
-8.3468 | 4.8915 | 1.5218 | 1.2827 | 0.60887 | 1.5653 | 3.4133 | 2.1306 | -3.4553 | -2.1726 | 1.2407 | 3.3713 | -8.3368 | 4.8915 | 1.5218 | 1.2827 | 0.60887 | 1.5653 | 3.4133 | 2.1306 | -3.4453 | -2.1626 | 1.2507 | 3.3813 | 0.01
-0.18201 | 6.6606 | 1.7939 | 1.6909 | 1.9697 | 2.3818 | 5.4545 | 3.7636 | 6.4786 | 8.1695 | 13.624 | 17.3876 | -0.17201 | 6.6606 | 1.7939 | 1.6909 | 1.9697 | 2.3818 | 5.4545 | 3.7636 | 6.4886 | 8.1795 | 13.634 | 17.3976 | 0.01
-6.2667 | 5.3422 | 1.5911 | 1.3867 | 0.95556 | 1.7733 | 3.9333 | 2.5467 | -0.92444 | 0.46223 | 4.3956 | 6.9422 | -6.2567 | 5.3422 | 1.5911 | 1.3867 | 0.95556 | 1.7733 | 3.9333 | 2.5467 | -0.91444 | 0.47223 | 4.4056 | 6.9522 | 0.01
10.6683 | 9.0115 | 2.1556 | 2.2334 | 3.778 | 3.4668 | 8.1671 | 5.9337 | 19.6798 | 21.9132 | 30.0803 | 36.0139 | 10.6783 | 9.0115 | 2.1556 | 2.2334 | 3.778 | 3.4668 | 8.1671 | 5.9337 | 19.6898 | 21.9232 | 30.0903 | 36.0239 | 0.01
6.5503 | 8.1192 | 2.0183 | 2.0275 | 3.0917 | 3.055 | 7.1376 | 5.1101 | 14.6695 | 16.697 | 23.8346 | 28.9447 | 6.5603 | 8.1192 | 2.0183 | 2.0275 | 3.0917 | 3.055 | 7.1376 | 5.1101 | 14.6795 | 16.707 | 23.8446 | 28.9547 | 0.01
7.3155 | 8.285 | 2.0438 | 2.0658 | 3.2192 | 3.1315 | 7.3289 | 5.2631 | 15.6005 | 17.6663 | 24.9951 | 30.2582 | 7.3255 | 8.285 | 2.0438 | 2.0658 | 3.2192 | 3.1315 | 7.3289 | 5.2631 | 15.6105 | 17.6763 | 25.0051 | 30.2682 | 0.01
12.1047 | 9.3227 | 2.2035 | 2.3052 | 4.0174 | 3.6105 | 8.5262 | 6.2209 | 21.4274 | 23.7326 | 32.2588 | 38.4797 | 12.1147 | 9.3227 | 2.2035 | 2.3052 | 4.0174 | 3.6105 | 8.5262 | 6.2209 | 21.4374 | 23.7426 | 32.2688 | 38.4897 | 0.01
11.6009 | 9.2135 | 2.1867 | 2.28 | 3.9335 | 3.5601 | 8.4002 | 6.1202 | 20.8144 | 23.0944 | 31.4947 | 37.6148 | 11.6109 | 9.2135 | 2.1867 | 2.28 | 3.9335 | 3.5601 | 8.4002 | 6.1202 | 20.8244 | 23.1044 | 31.5047 | 37.6248 | 0.01
16.131 | 10.195 | 2.3377 | 2.5065 | 4.6885 | 4.0131 | 9.5327 | 7.0262 | 26.326 | 28.8326 | 38.3653 | 45.3915 | 16.141 | 10.195 | 2.3377 | 2.5065 | 4.6885 | 4.0131 | 9.5327 | 7.0262 | 26.336 | 28.8426 | 38.3753 | 45.4015 | 0.01
7.8716 | 8.4055 | 2.0624 | 2.0936 | 3.3119 | 3.1872 | 7.4679 | 5.3743 | 16.2771 | 18.3706 | 25.8385 | 31.2128 | 7.8816 | 8.4055 | 2.0624 | 2.0936 | 3.3119 | 3.1872 | 7.4679 | 5.3743 | 16.2871 | 18.3806 | 25.8485 | 31.2228 | 0.01
6.6207 | 8.1345 | 2.0207 | 2.031 | 3.1035 | 3.0621 | 7.1552 | 5.1241 | 14.7552 | 16.7863 | 23.9415 | 29.0656 | 6.6307 | 8.1345 | 2.0207 | 2.031 | 3.1035 | 3.0621 | 7.1552 | 5.1241 | 14.7652 | 16.7963 | 23.9515 | 29.0756 | 0.01
15.6319 | 10.0869 | 2.3211 | 2.4816 | 4.6053 | 3.9632 | 9.408 | 6.9264 | 25.7188 | 28.2004 | 37.6084 | 44.5348 | 15.6419 | 10.0869 | 2.3211 | 2.4816 | 4.6053 | 3.9632 | 9.408 | 6.9264 | 25.7288 | 28.2104 | 37.6184 | 44.5448 | 0.01
12.4075 | 9.3883 | 2.2136 | 2.3204 | 4.0679 | 3.6408 | 8.6019 | 6.2815 | 21.7958 | 24.1162 | 32.7181 | 38.9996 | 12.4175 | 9.3883 | 2.2136 | 2.3204 | 4.0679 | 3.6408 | 8.6019 | 6.2815 | 21.8058 | 24.1262 | 32.7281 | 39.0096 | 0.01
3.1852 | 7.3901 | 1.9062 | 1.8593 | 2.5309 | 2.7185 | 6.2963 | 4.437 | 10.5753 | 12.4346 | 18.7309 | 23.168 | 3.1952 | 7.3901 | 1.9062 | 1.8593 | 2.5309 | 2.7185 | 6.2963 | 4.437 | 10.5853 | 12.4446 | 18.7409 | 23.178 | 0.01
8.0258 | 8.4389 | 2.0675 | 2.1013 | 3.3376 | 3.2026 | 7.5065 | 5.4052 | 16.4648 | 18.5661 | 26.0725 | 31.4777 | 8.0358 | 8.4389 | 2.0675 | 2.1013 | 3.3376 | 3.2026 | 7.5065 | 5.4052 | 16.4748 | 18.5761 | 26.0825 | 31.4877 | 0.01
-1.6375 | 6.3452 | 1.7454 | 1.6181 | 1.7271 | 2.2363 | 5.0906 | 3.4725 | 4.7078 | 6.3259 | 11.4165 | 14.889 | -1.6275 | 6.3452 | 1.7454 | 1.6181 | 1.7271 | 2.2363 | 5.0906 | 3.4725 | 4.7178 | 6.3359 | 11.4265 | 14.899 | 0.01
3.3169 | 7.4187 | 1.9106 | 1.8658 | 2.5528 | 2.7317 | 6.3292 | 4.4634 | 10.7355 | 12.6014 | 18.9306 | 23.394 | 3.3269 | 7.4187 | 1.9106 | 1.8658 | 2.5528 | 2.7317 | 6.3292 | 4.4634 | 10.7455 | 12.6114 | 18.9406 | 23.404 | 0.01
-1.316 | 6.4149 | 1.7561 | 1.6342 | 1.7807 | 2.2684 | 5.171 | 3.5368 | 5.0988 | 6.733 | 11.904 | 15.4408 | -1.306 | 6.4149 | 1.7561 | 1.6342 | 1.7807 | 2.2684 | 5.171 | 3.5368 | 5.1088 | 6.743 | 11.914 | 15.4508 | 0.01
7.4915 | 8.3232 | 2.0497 | 2.0746 | 3.2486 | 3.1491 | 7.3729 | 5.2983 | 15.8146 | 17.8892 | 25.2621 | 30.5603 | 7.5015 | 8.3232 | 2.0497 | 2.0746 | 3.2486 | 3.1491 | 7.3729 | 5.2983 | 15.8246 | 17.8992 | 25.2721 | 30.5703 | 0.01
1.1213 | 6.943 | 1.8374 | 1.7561 | 2.1869 | 2.5121 | 5.7803 | 4.0243 | 8.0643 | 9.8204 | 15.6007 | 19.625 | 1.1313 | 6.943 | 1.8374 | 1.7561 | 2.1869 | 2.5121 | 5.7803 | 4.0243 | 8.0743 | 9.8304 | 15.6107 | 19.635 | 0.01
-0.19129 | 6.6586 | 1.7936 | 1.6904 | 1.9681 | 2.3809 | 5.4522 | 3.7617 | 6.4673 | 8.1577 | 13.6099 | 17.3716 | -0.18129 | 6.6586 | 1.7936 | 1.6904 | 1.9681 | 2.3809 | 5.4522 | 3.7617 | 6.4773 | 8.1677 | 13.6199 | 17.3816 | 0.01
14.9327 | 9.9354 | 2.2978 | 2.4466 | 4.4888 | 3.8933 | 9.2332 | 6.7865 | 24.8681 | 27.3147 | 36.5479 | 43.3344 | 14.9427 | 9.9354 | 2.2978 | 2.4466 | 4.4888 | 3.8933 | 9.2332 | 6.7865 | 24.8781 | 27.3247 | 36.5579 | 43.3444 | 0.01
6.5945 | 8.1288 | 2.0198 | 2.0297 | 3.0991 | 3.0594 | 7.1486 | 5.1189 | 14.7233 | 16.753 | 23.9016 | 29.0205 | 6.6045 | 8.1288 | 2.0198 | 2.0297 | 3.0991 | 3.0594 | 7.1486 | 5.1189 | 14.7333 | 16.763 | 23.9116 | 29.0305 | 0.01
9.6841 | 8.7982 | 2.1228 | 2.1842 | 3.614 | 3.3684 | 7.921 | 5.7368 | 18.4823 | 20.6665 | 28.5875 | 34.3244 | 9.6941 | 8.7982 | 2.1228 | 2.1842 | 3.614 | 3.3684 | 7.921 | 5.7368 | 18.4923 | 20.6765 | 28.5975 | 34.3344 | 0.01
10.8748 | 9.0562 | 2.1625 | 2.2437 | 3.8125 | 3.4875 | 8.2187 | 5.975 | 19.931 | 22.1747 | 30.3934 | 36.3684 | 10.8848 | 9.0562 | 2.1625 | 2.2437 | 3.8125 | 3.4875 | 8.2187 | 5.975 | 19.941 | 22.1847 | 30.4034 | 36.3784 | 0.01
9.5191 | 8.7625 | 2.1173 | 2.176 | 3.5865 | 3.3519 | 7.8798 | 5.7038 | 18.2816 | 20.4576 | 28.3373 | 34.0412 | 9.5291 | 8.7625 | 2.1173 | 2.176 | 3.5865 | 3.3519 | 7.8798 | 5.7038 | 18.2916 | 20.4676 | 28.3473 | 34.0512 | 0.01
11.791 | 9.2547 | 2.193 | 2.2896 | 3.9652 | 3.5791 | 8.4478 | 6.1582 | 21.0458 | 23.3353 | 31.7831 | 37.9413 | 11.801 | 9.2547 | 2.193 | 2.2896 | 3.9652 | 3.5791 | 8.4478 | 6.1582 | 21.0558 | 23.3453 | 31.7931 | 37.9513 | 0.01
4.0406 | 7.5755 | 1.9347 | 1.902 | 2.6734 | 2.8041 | 6.5101 | 4.6081 | 11.6161 | 13.5181 | 20.0282 | 24.6364 | 4.0506 | 7.5755 | 1.9347 | 1.902 | 2.6734 | 2.8041 | 6.5101 | 4.6081 | 11.6261 | 13.5281 | 20.0382 | 24.6464 | 0.01
0.16694 | 6.7362 | 1.8056 | 1.7083 | 2.0278 | 2.4167 | 5.5417 | 3.8334 | 6.9031 | 8.6115 | 14.1532 | 17.9866 | 0.17694 | 6.7362 | 1.8056 | 1.7083 | 2.0278 | 2.4167 | 5.5417 | 3.8334 | 6.9131 | 8.6215 | 14.1632 | 17.9966 | 0.01
1.7732 | 7.0842 | 1.8591 | 1.7887 | 2.2955 | 2.5773 | 5.9433 | 4.1546 | 8.8574 | 10.6461 | 16.5894 | 20.7441 | 1.7832 | 7.0842 | 1.8591 | 1.7887 | 2.2955 | 2.5773 | 5.9433 | 4.1546 | 8.8674 | 10.6561 | 16.5994 | 20.7541 | 0.01
2.946 | 7.3383 | 1.8982 | 1.8473 | 2.491 | 2.6946 | 6.2365 | 4.3892 | 10.2843 | 12.1316 | 18.3681 | 22.7573 | 2.956 | 7.3383 | 1.8982 | 1.8473 | 2.491 | 2.6946 | 6.2365 | 4.3892 | 10.2943 | 12.1416 | 18.3781 | 22.7673 | 0.01
5.1699 | 7.8202 | 1.9723 | 1.9585 | 2.8617 | 2.917 | 6.7925 | 4.834 | 12.9901 | 14.9486 | 21.7411 | 26.5751 | 5.1799 | 7.8202 | 1.9723 | 1.9585 | 2.8617 | 2.917 | 6.7925 | 4.834 | 13.0001 | 14.9586 | 21.7511 | 26.5851 | 0.01
12.1677 | 9.3363 | 2.2056 | 2.3084 | 4.0279 | 3.6168 | 8.5419 | 6.2335 | 21.504 | 23.8124 | 32.3543 | 38.5878 | 12.1777 | 9.3363 | 2.2056 | 2.3084 | 4.0279 | 3.6168 | 8.5419 | 6.2335 | 21.514 | 23.8224 | 32.3643 | 38.5978 | 0.01
6.5433 | 8.1177 | 2.0181 | 2.0272 | 3.0906 | 3.0543 | 7.1358 | 5.1087 | 14.661 | 16.6882 | 23.824 | 28.9327 | 6.5533 | 8.1177 | 2.0181 | 2.0272 | 3.0906 | 3.0543 | 7.1358 | 5.1087 | 14.671 | 16.6982 | 23.834 | 28.9427 | 0.01
11.7076 | 9.2366 | 2.1903 | 2.2854 | 3.9513 | 3.5708 | 8.4269 | 6.1415 | 20.9442 | 23.2296 | 31.6565 | 37.798 | 11.7176 | 9.2366 | 2.1903 | 2.2854 | 3.9513 | 3.5708 | 8.4269 | 6.1415 | 20.9542 | 23.2396 | 31.6665 | 37.808 | 0.01
5.373 | 7.8641 | 1.9791 | 1.9686 | 2.8955 | 2.9373 | 6.8432 | 4.8746 | 13.2371 | 15.2058 | 22.049 | 26.9236 | 5.383 | 7.8641 | 1.9791 | 1.9686 | 2.8955 | 2.9373 | 6.8432 | 4.8746 | 13.2471 | 15.2158 | 22.059 | 26.9336 | 0.01
-2.6906 | 6.117 | 1.7103 | 1.5655 | 1.5516 | 2.1309 | 4.8273 | 3.2619 | 3.4264 | 4.9919 | 9.8193 | 13.0811 | -2.6806 | 6.117 | 1.7103 | 1.5655 | 1.5516 | 2.1309 | 4.8273 | 3.2619 | 3.4364 | 5.0019 | 9.8293 | 13.0911 | 0.01
5.7733 | 7.9509 | 1.9924 | 1.9887 | 2.9622 | 2.9773 | 6.9433 | 4.9547 | 13.7242 | 15.7128 | 22.6561 | 27.6108 | 5.7833 | 7.9509 | 1.9924 | 1.9887 | 2.9622 | 2.9773 | 6.9433 | 4.9547 | 13.7342 | 15.7228 | 22.6661 | 27.6208 | 0.01
1.0347 | 6.9242 | 1.8345 | 1.7517 | 2.1724 | 2.5035 | 5.7587 | 4.0069 | 7.9588 | 9.7106 | 15.4693 | 19.4762 | 1.0447 | 6.9242 | 1.8345 | 1.7517 | 2.1724 | 2.5035 | 5.7587 | 4.0069 | 7.9688 | 9.7206 | 15.4793 | 19.4862 | 0.01
17.9452 | 10.5881 | 2.3982 | 2.5973 | 4.9909 | 4.1945 | 9.9863 | 7.389 | 28.5333 | 31.1306 | 41.1169 | 48.5059 | 17.9552 | 10.5881 | 2.3982 | 2.5973 | 4.9909 | 4.1945 | 9.9863 | 7.389 | 28.5433 | 31.1406 | 41.1269 | 48.5159 | 0.01
2.4162 | 7.2235 | 1.8805 | 1.8208 | 2.4027 | 2.6416 | 6.104 | 4.2832 | 9.6397 | 11.4605 | 17.5645 | 21.8477 | 2.4262 | 7.2235 | 1.8805 | 1.8208 | 2.4027 | 2.6416 | 6.104 | 4.2832 | 9.6497 | 11.4705 | 17.5745 | 21.8577 | 0.01
5.5634 | 7.9054 | 1.9854 | 1.9782 | 2.9272 | 2.9563 | 6.8909 | 4.9127 | 13.4688 | 15.447 | 22.3378 | 27.2505 | 5.5734 | 7.9054 | 1.9854 | 1.9782 | 2.9272 | 2.9563 | 6.8909 | 4.9127 | 13.4788 | 15.457 | 22.3478 | 27.2605 | 0.01
-4.3193 | 5.7641 | 1.656 | 1.484 | 1.2801 | 1.9681 | 4.4202 | 2.9361 | 1.4448 | 2.9288 | 7.349 | 10.2851 | -4.3093 | 5.7641 | 1.656 | 1.484 | 1.2801 | 1.9681 | 4.4202 | 2.9361 | 1.4548 | 2.9388 | 7.359 | 10.2951 | 0.01
-1.7225 | 6.3268 | 1.7426 | 1.6139 | 1.7129 | 2.2278 | 5.0694 | 3.4555 | 4.6043 | 6.2182 | 11.2876 | 14.7431 | -1.7125 | 6.3268 | 1.7426 | 1.6139 | 1.7129 | 2.2278 | 5.0694 | 3.4555 | 4.6143 | 6.2282 | 11.2976 | 14.7531 | 0.01
5.3795 | 7.8656 | 1.9793 | 1.969 | 2.8966 | 2.9379 | 6.8449 | 4.8759 | 13.245 | 15.214 | 22.0589 | 26.9348 | 5.3895 | 7.8656 | 1.9793 | 1.969 | 2.8966 | 2.9379 | 6.8449 | 4.8759 | 13.255 | 15.224 | 22.0689 | 26.9448 | 0.01
2.8529 | 7.3181 | 1.8951 | 1.8426 | 2.4755 | 2.6853 | 6.2132 | 4.3706 | 10.171 | 12.0137 | 18.2269 | 22.5975 | 2.8629 | 7.3181 | 1.8951 | 1.8426 | 2.4755 | 2.6853 | 6.2132 | 4.3706 | 10.181 | 12.0237 | 18.2369 | 22.6075 | 0.01
4.9315 | 7.7685 | 1.9644 | 1.9466 | 2.8219 | 2.8931 | 6.7329 | 4.7863 | 12.6999 | 14.6465 | 21.3794 | 26.1657 | 4.9415 | 7.7685 | 1.9644 | 1.9466 | 2.8219 | 2.8931 | 6.7329 | 4.7863 | 12.7099 | 14.6565 | 21.3894 | 26.1757 | 0.01
8.9348 | 8.6359 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7337 | 5.587 | 17.5707 | 19.7175 | 27.4512 | 33.0382 | 8.9448 | 8.6359 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7337 | 5.587 | 17.5807 | 19.7275 | 27.4612 | 33.0482 | 0.01
18.576 | 10.7248 | 2.4192 | 2.6288 | 5.096 | 4.2576 | 10.144 | 7.5152 | 29.3008 | 31.9296 | 42.0736 | 49.5888 | 18.586 | 10.7248 | 2.4192 | 2.6288 | 5.096 | 4.2576 | 10.144 | 7.5152 | 29.3108 | 31.9396 | 42.0836 | 49.5988 | 0.01
10.8329 | 9.0471 | 2.1611 | 2.2416 | 3.8055 | 3.4833 | 8.2082 | 5.9666 | 19.88 | 22.1217 | 30.3299 | 36.2965 | 10.8429 | 9.0471 | 2.1611 | 2.2416 | 3.8055 | 3.4833 | 8.2082 | 5.9666 | 19.89 | 22.1317 | 30.3399 | 36.3065 | 0.01
20.2137 | 11.0796 | 2.4738 | 2.7107 | 5.3689 | 4.4214 | 10.5534 | 7.8427 | 31.2933 | 34.004 | 44.5574 | 52.4001 | 20.2237 | 11.0796 | 2.4738 | 2.7107 | 5.3689 | 4.4214 | 10.5534 | 7.8427 | 31.3033 | 34.014 | 44.5674 | 52.4101 | 0.01
-2.0597 | 6.2537 | 1.7313 | 1.597 | 1.6567 | 2.194 | 4.9851 | 3.3881 | 4.1941 | 5.7911 | 10.7762 | 14.1642 | -2.0497 | 6.2537 | 1.7313 | 1.597 | 1.6567 | 2.194 | 4.9851 | 3.3881 | 4.2041 | 5.8011 | 10.7862 | 14.1742 | 0.01
10.1219 | 8.8931 | 2.1374 | 2.2061 | 3.687 | 3.4122 | 8.0305 | 5.8244 | 19.015 | 21.2211 | 29.2516 | 35.0759 | 10.1319 | 8.8931 | 2.1374 | 2.2061 | 3.687 | 3.4122 | 8.0305 | 5.8244 | 19.025 | 21.2311 | 29.2616 | 35.0859 | 0.01
9.1303 | 8.6782 | 2.1043 | 2.1565 | 3.5217 | 3.313 | 7.7826 | 5.6261 | 17.8085 | 19.965 | 27.7476 | 33.3737 | 9.1403 | 8.6782 | 2.1043 | 2.1565 | 3.5217 | 3.313 | 7.7826 | 5.6261 | 17.8185 | 19.975 | 27.7576 | 33.3837 | 0.01
1.075 | 6.9329 | 1.8358 | 1.7537 | 2.1792 | 2.5075 | 5.7687 | 4.015 | 8.0079 | 9.7616 | 15.5304 | 19.5454 | 1.085 | 6.9329 | 1.8358 | 1.7537 | 2.1792 | 2.5075 | 5.7687 | 4.015 | 8.0179 | 9.7716 | 15.5404 | 19.5554 | 0.01
-4.9896 | 5.6189 | 1.6337 | 1.4505 | 1.1684 | 1.901 | 4.2526 | 2.8021 | 0.62936 | 2.0799 | 6.3325 | 9.1346 | -4.9796 | 5.6189 | 1.6337 | 1.4505 | 1.1684 | 1.901 | 4.2526 | 2.8021 | 0.63936 | 2.0899 | 6.3425 | 9.1446 | 0.01
-0.62885 | 6.5637 | 1.779 | 1.6686 | 1.8952 | 2.3371 | 5.3428 | 3.6742 | 5.9349 | 7.6035 | 12.9462 | 16.6205 | -0.61885 | 6.5637 | 1.779 | 1.6686 | 1.8952 | 2.3371 | 5.3428 | 3.6742 | 5.9449 | 7.6135 | 12.9562 | 16.6305 | 0.01
7.2339 | 8.2674 | 2.0411 | 2.0617 | 3.2057 | 3.1234 | 7.3085 | 5.2468 | 15.5013 | 17.563 | 24.8715 | 30.1183 | 7.2439 | 8.2674 | 2.0411 | 2.0617 | 3.2057 | 3.1234 | 7.3085 | 5.2468 | 15.5113 | 17.573 | 24.8815 | 30.1283 | 0.01
10.4833 | 8.9714 | 2.1494 | 2.2242 | 3.7472 | 3.4483 | 8.1208 | 5.8967 | 19.4547 | 21.6788 | 29.7997 | 35.6963 | 10.4933 | 8.9714 | 2.1494 | 2.2242 | 3.7472 | 3.4483 | 8.1208 | 5.8967 | 19.4647 | 21.6888 | 29.8097 | 35.7063 | 0.01
17.6691 | 10.5283 | 2.389 | 2.5835 | 4.9448 | 4.1669 | 9.9173 | 7.3338 | 28.1974 | 30.7808 | 40.6981 | 48.0319 | 17.6791 | 10.5283 | 2.389 | 2.5835 | 4.9448 | 4.1669 | 9.9173 | 7.3338 | 28.2074 | 30.7908 | 40.7081 | 48.0419 | 0.01
10.1095 | 8.8904 | 2.137 | 2.2055 | 3.6849 | 3.4109 | 8.0274 | 5.8219 | 18.9999 | 21.2053 | 29.2327 | 35.0546 | 10.1195 | 8.8904 | 2.137 | 2.2055 | 3.6849 | 3.4109 | 8.0274 | 5.8219 | 19.0099 | 21.2153 | 29.2427 | 35.0646 | 0.01
9.4732 | 8.7525 | 2.1158 | 2.1737 | 3.5789 | 3.3473 | 7.8683 | 5.6946 | 18.2258 | 20.3994 | 28.2677 | 33.9624 | 9.4832 | 8.7525 | 2.1158 | 2.1737 | 3.5789 | 3.3473 | 7.8683 | 5.6946 | 18.2358 | 20.4094 | 28.2777 | 33.9724 | 0.01
6.8688 | 8.1882 | 2.029 | 2.0434 | 3.1448 | 3.0869 | 7.2172 | 5.1738 | 15.057 | 17.1005 | 24.3177 | 29.4914 | 6.8788 | 8.1882 | 2.029 | 2.0434 | 3.1448 | 3.0869 | 7.2172 | 5.1738 | 15.067 | 17.1105 | 24.3277 | 29.5014 | 0.01
-7.7712 | 5.0162 | 1.541 | 1.3114 | 0.7048 | 1.6229 | 3.5572 | 2.2458 | -2.755 | -1.4435 | 2.1137 | 4.3594 | -7.7612 | 5.0162 | 1.541 | 1.3114 | 0.7048 | 1.6229 | 3.5572 | 2.2458 | -2.745 | -1.4335 | 2.1237 | 4.3694 | 0.01
6.6159 | 8.1335 | 2.0205 | 2.0308 | 3.1027 | 3.0616 | 7.154 | 5.1232 | 14.7494 | 16.7802 | 23.9342 | 29.0574 | 6.6259 | 8.1335 | 2.0205 | 2.0308 | 3.1027 | 3.0616 | 7.154 | 5.1232 | 14.7594 | 16.7902 | 23.9442 | 29.0674 | 0.01
7.7482 | 8.3788 | 2.0583 | 2.0874 | 3.2914 | 3.1748 | 7.437 | 5.3496 | 16.127 | 18.2144 | 25.6514 | 31.0011 | 7.7582 | 8.3788 | 2.0583 | 2.0874 | 3.2914 | 3.1748 | 7.437 | 5.3496 | 16.137 | 18.2244 | 25.6614 | 31.0111 | 0.01
11.3824 | 9.1662 | 2.1794 | 2.2691 | 3.8971 | 3.5382 | 8.3456 | 6.0765 | 20.5485 | 22.8177 | 31.1632 | 37.2397 | 11.3924 | 9.1662 | 2.1794 | 2.2691 | 3.8971 | 3.5382 | 8.3456 | 6.0765 | 20.5585 | 22.8277 | 31.1732 | 37.2497 | 0.01
3.369 | 7.4299 | 1.9123 | 1.8684 | 2.5615 | 2.7369 | 6.3422 | 4.4738 | 10.7989 | 12.6674 | 19.0096 | 23.4834 | 3.379 | 7.4299 | 1.9123 | 1.8684 | 2.5615 | 2.7369 | 6.3422 | 4.4738 | 10.8089 | 12.6774 | 19.0196 | 23.4934 | 0.01
12.951 | 9.506 | 2.2317 | 2.3475 | 4.1585 | 3.6951 | 8.7377 | 6.3902 | 22.457 | 24.8046 | 33.5423 | 39.9325 | 12.961 | 9.506 | 2.2317 | 2.3475 | 4.1585 | 3.6951 | 8.7377 | 6.3902 | 22.467 | 24.8146 | 33.5523 | 39.9425 | 0.01
0.55287 | 6.8198 | 1.8184 | 1.7276 | 2.0921 | 2.4553 | 5.6382 | 3.9106 | 7.3727 | 9.1003 | 14.7385 | 18.6491 | 0.56287 | 6.8198 | 1.8184 | 1.7276 | 2.0921 | 2.4553 | 5.6382 | 3.9106 | 7.3827 | 9.1103 | 14.7485 | 18.6591 | 0.01
5.8476 | 7.967 | 1.9949 | 1.9924 | 2.9746 | 2.9848 | 6.9619 | 4.9695 | 13.8146 | 15.807 | 22.7689 | 27.7384 | 5.8576 | 7.967 | 1.9949 | 1.9924 | 2.9746 | 2.9848 | 6.9619 | 4.9695 | 13.8246 | 15.817 | 22.7789 | 27.7484 | 0.01
1.2162 | 6.9635 | 1.8405 | 1.7608 | 2.2027 | 2.5216 | 5.8041 | 4.0432 | 8.1798 | 9.9406 | 15.7446 | 19.7879 | 1.2262 | 6.9635 | 1.8405 | 1.7608 | 2.2027 | 2.5216 | 5.8041 | 4.0432 | 8.1898 | 9.9506 | 15.7546 | 19.7979 | 0.01
12.2562 | 9.3555 | 2.2085 | 2.3128 | 4.0427 | 3.6256 | 8.564 | 6.2512 | 21.6117 | 23.9245 | 32.4885 | 38.7398 | 12.2662 | 9.3555 | 2.2085 | 2.3128 | 4.0427 | 3.6256 | 8.564 | 6.2512 | 21.6217 | 23.9345 | 32.4985 | 38.7498 | 0.01
4.5273 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7055 | 12.2082 | 14.1346 | 20.7664 | 25.4718 | 4.5373 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7055 | 12.2182 | 14.1446 | 20.7764 | 25.4818 | 0.01
-1.3747 | 6.4021 | 1.7542 | 1.6313 | 1.7709 | 2.2625 | 5.1563 | 3.5251 | 5.0275 | 6.6587 | 11.815 | 15.3401 | -1.3647 | 6.4021 | 1.7542 | 1.6313 | 1.7709 | 2.2625 | 5.1563 | 3.5251 | 5.0375 | 6.6687 | 11.825 | 15.3501 | 0.01
7.568 | 8.3397 | 2.0523 | 2.0784 | 3.2613 | 3.1568 | 7.392 | 5.3136 | 15.9077 | 17.9861 | 25.3781 | 30.6917 | 7.578 | 8.3397 | 2.0523 | 2.0784 | 3.2613 | 3.1568 | 7.392 | 5.3136 | 15.9177 | 17.9961 | 25.3881 | 30.7017 | 0.01
17.8346 | 10.5642 | 2.3945 | 2.5917 | 4.9724 | 4.1835 | 9.9586 | 7.3669 | 28.3987 | 30.9905 | 40.9491 | 48.316 | 17.8446 | 10.5642 | 2.3945 | 2.5917 | 4.9724 | 4.1835 | 9.9586 | 7.3669 | 28.4087 | 31.0005 | 40.9591 | 48.326 | 0.01
14.6358 | 9.8711 | 2.2879 | 2.4318 | 4.4393 | 3.8636 | 9.159 | 6.7272 | 24.5069 | 26.9387 | 36.0977 | 42.8248 | 14.6458 | 9.8711 | 2.2879 | 2.4318 | 4.4393 | 3.8636 | 9.159 | 6.7272 | 24.5169 | 26.9487 | 36.1077 | 42.8348 | 0.01
14.7192 | 9.8892 | 2.2906 | 2.436 | 4.4532 | 3.8719 | 9.1798 | 6.7438 | 24.6084 | 27.0443 | 36.2241 | 42.968 | 14.7292 | 9.8892 | 2.2906 | 2.436 | 4.4532 | 3.8719 | 9.1798 | 6.7438 | 24.6184 | 27.0543 | 36.2341 | 42.978 | 0.01
8.6596 | 8.5763 | 2.0887 | 2.133 | 3.4433 | 3.266 | 7.6649 | 5.5319 | 17.2359 | 19.3689 | 27.0338 | 32.5657 | 8.6696 | 8.5763 | 2.0887 | 2.133 | 3.4433 | 3.266 | 7.6649 | 5.5319 | 17.2459 | 19.3789 | 27.0438 | 32.5757 | 0.01
-0.8912 | 6.5069 | 1.7703 | 1.6554 | 1.8515 | 2.3109 | 5.2772 | 3.6218 | 5.6157 | 7.2712 | 12.5484 | 16.1701 | -0.8812 | 6.5069 | 1.7703 | 1.6554 | 1.8515 | 2.3109 | 5.2772 | 3.6218 | 5.6257 | 7.2812 | 12.5584 | 16.1801 | 0.01
0.11658 | 6.7253 | 1.8039 | 1.7058 | 2.0194 | 2.4117 | 5.5291 | 3.8233 | 6.8418 | 8.5477 | 14.0768 | 17.9001 | 0.12658 | 6.7253 | 1.8039 | 1.7058 | 2.0194 | 2.4117 | 5.5291 | 3.8233 | 6.8518 | 8.5577 | 14.0868 | 17.9101 | 0.01
2.9789 | 7.3454 | 1.8993 | 1.8489 | 2.4965 | 2.6979 | 6.2447 | 4.3958 | 10.3243 | 12.1733 | 18.418 | 22.8138 | 2.9889 | 7.3454 | 1.8993 | 1.8489 | 2.4965 | 2.6979 | 6.2447 | 4.3958 | 10.3343 | 12.1833 | 18.428 | 22.8238 | 0.01
10.7182 | 9.0223 | 2.1573 | 2.2359 | 3.7864 | 3.4718 | 8.1796 | 5.9436 | 19.7405 | 21.9764 | 30.156 | 36.0997 | 10.7282 | 9.0223 | 2.1573 | 2.2359 | 3.7864 | 3.4718 | 8.1796 | 5.9436 | 19.7505 | 21.9864 | 30.166 | 36.1097 | 0.01
8.2018 | 8.4771 | 2.0734 | 2.1101 | 3.367 | 3.2202 | 7.5505 | 5.4404 | 16.6789 | 18.789 | 26.3395 | 31.7798 | 8.2118 | 8.4771 | 2.0734 | 2.1101 | 3.367 | 3.2202 | 7.5505 | 5.4404 | 16.6889 | 18.799 | 26.3495 | 31.7898 | 0.01
14.9186 | 9.9324 | 2.2973 | 2.4459 | 4.4864 | 3.8919 | 9.2296 | 6.7837 | 24.8509 | 27.2969 | 36.5265 | 43.3102 | 14.9286 | 9.9324 | 2.2973 | 2.4459 | 4.4864 | 3.8919 | 9.2296 | 6.7837 | 24.8609 | 27.3069 | 36.5365 | 43.3202 | 0.01
3.278 | 7.4102 | 1.9093 | 1.8639 | 2.5463 | 2.7278 | 6.3195 | 4.4556 | 10.6882 | 12.5521 | 18.8716 | 23.3272 | 3.288 | 7.4102 | 1.9093 | 1.8639 | 2.5463 | 2.7278 | 6.3195 | 4.4556 | 10.6982 | 12.5621 | 18.8816 | 23.3372 | 0.01
11.9059 | 9.2796 | 2.1969 | 2.2953 | 3.9843 | 3.5906 | 8.4765 | 6.1812 | 21.1855 | 23.4808 | 31.9572 | 38.1384 | 11.9159 | 9.2796 | 2.1969 | 2.2953 | 3.9843 | 3.5906 | 8.4765 | 6.1812 | 21.1955 | 23.4908 | 31.9672 | 38.1484 | 0.01
0.21186 | 6.7459 | 1.8071 | 1.7106 | 2.0353 | 2.4212 | 5.553 | 3.8424 | 6.9578 | 8.6684 | 14.2213 | 18.0637 | 0.22186 | 6.7459 | 1.8071 | 1.7106 | 2.0353 | 2.4212 | 5.553 | 3.8424 | 6.9678 | 8.6784 | 14.2313 | 18.0737 | 0.01
8.3077 | 8.5 | 2.0769 | 2.1154 | 3.3846 | 3.2308 | 7.5769 | 5.4615 | 16.8077 | 18.9231 | 26.5001 | 31.9616 | 8.3177 | 8.5 | 2.0769 | 2.1154 | 3.3846 | 3.2308 | 7.5769 | 5.4615 | 16.8177 | 18.9331 | 26.5101 | 31.9716 | 0.01
0.99521 | 6.9156 | 1.8332 | 1.7498 | 2.1659 | 2.4995 | 5.7488 | 3.999 | 7.9108 | 9.6606 | 15.4094 | 19.4084 | 1.0052 | 6.9156 | 1.8332 | 1.7498 | 2.1659 | 2.4995 | 5.7488 | 3.999 | 7.9208 | 9.6706 | 15.4194 | 19.4184 | 0.01
10.022 | 8.8714 | 2.1341 | 2.2011 | 3.6703 | 3.4022 | 8.0055 | 5.8044 | 18.8934 | 21.0945 | 29.1 | 34.9045 | 10.032 | 8.8714 | 2.1341 | 2.2011 | 3.6703 | 3.4022 | 8.0055 | 5.8044 | 18.9034 | 21.1045 | 29.11 | 34.9145 | 0.01
-5.1718 | 5.5794 | 1.6276 | 1.4414 | 1.138 | 1.8828 | 4.207 | 2.7656 | 0.4076 | 1.849 | 6.0561 | 8.8217 | -5.1618 | 5.5794 | 1.6276 | 1.4414 | 1.138 | 1.8828 | 4.207 | 2.7656 | 0.4176 | 1.859 | 6.0661 | 8.8317 | 0.01
-1.0844 | 6.465 | 1.7639 | 1.6458 | 1.8193 | 2.2916 | 5.2289 | 3.5831 | 5.3806 | 7.0264 | 12.2553 | 15.8384 | -1.0744 | 6.465 | 1.7639 | 1.6458 | 1.8193 | 2.2916 | 5.2289 | 3.5831 | 5.3906 | 7.0364 | 12.2653 | 15.8484 | 0.01
6.9795 | 8.2122 | 2.0326 | 2.049 | 3.1632 | 3.0979 | 7.2449 | 5.1959 | 15.1917 | 17.2407 | 24.4855 | 29.6814 | 6.9895 | 8.2122 | 2.0326 | 2.049 | 3.1632 | 3.0979 | 7.2449 | 5.1959 | 15.2017 | 17.2507 | 24.4955 | 29.6914 | 0.01
1.3132 | 6.9845 | 1.8438 | 1.7657 | 2.2189 | 2.5313 | 5.8283 | 4.0626 | 8.2978 | 10.0634 | 15.8917 | 19.9544 | 1.3232 | 6.9845 | 1.8438 | 1.7657 | 2.2189 | 2.5313 | 5.8283 | 4.0626 | 8.3078 | 10.0734 | 15.9017 | 19.9644 | 0.01
1.3639 | 6.9955 | 1.8455 | 1.7682 | 2.2273 | 2.5364 | 5.841 | 4.0728 | 8.3594 | 10.1276 | 15.9686 | 20.0414 | 1.3739 | 6.9955 | 1.8455 | 1.7682 | 2.2273 | 2.5364 | 5.841 | 4.0728 | 8.3694 | 10.1376 | 15.9786 | 20.0514 | 0.01
-1.4768 | 6.38 | 1.7508 | 1.6262 | 1.7539 | 2.2523 | 5.1308 | 3.5046 | 4.9032 | 6.5293 | 11.6601 | 15.1648 | -1.4668 | 6.38 | 1.7508 | 1.6262 | 1.7539 | 2.2523 | 5.1308 | 3.5046 | 4.9132 | 6.5393 | 11.6701 | 15.1748 | 0.01
6.5105 | 8.1106 | 2.017 | 2.0255 | 3.0851 | 3.0511 | 7.1276 | 5.1021 | 14.6211 | 16.6466 | 23.7743 | 28.8764 | 6.5205 | 8.1106 | 2.017 | 2.0255 | 3.0851 | 3.0511 | 7.1276 | 5.1021 | 14.6311 | 16.6566 | 23.7843 | 28.8864 | 0.01
2.9522 | 7.3396 | 1.8984 | 1.8476 | 2.492 | 2.6952 | 6.238 | 4.3904 | 10.2918 | 12.1394 | 18.3775 | 22.7679 | 2.9622 | 7.3396 | 1.8984 | 1.8476 | 2.492 | 2.6952 | 6.238 | 4.3904 | 10.3018 | 12.1494 | 18.3875 | 22.7779 | 0.01
6.1645 | 8.0356 | 2.0055 | 2.0082 | 3.0274 | 3.0165 | 7.0411 | 5.0329 | 14.2002 | 16.2084 | 23.2495 | 28.2824 | 6.1745 | 8.0356 | 2.0055 | 2.0082 | 3.0274 | 3.0165 | 7.0411 | 5.0329 | 14.2102 | 16.2184 | 23.2595 | 28.2924 | 0.01
3.115 | 7.3749 | 1.9038 | 1.8557 | 2.5192 | 2.7115 | 6.2787 | 4.423 | 10.4899 | 12.3457 | 18.6244 | 23.0474 | 3.125 | 7.3749 | 1.9038 | 1.8557 | 2.5192 | 2.7115 | 6.2787 | 4.423 | 10.4999 | 12.3557 | 18.6344 | 23.0574 | 0.01
6.4626 | 8.1002 | 2.0154 | 2.0231 | 3.0771 | 3.0463 | 7.1157 | 5.0925 | 14.5628 | 16.586 | 23.7016 | 28.7941 | 6.4726 | 8.1002 | 2.0154 | 2.0231 | 3.0771 | 3.0463 | 7.1157 | 5.0925 | 14.5728 | 16.596 | 23.7116 | 28.8041 | 0.01
16.0124 | 10.1694 | 2.3337 | 2.5006 | 4.6687 | 4.0012 | 9.5031 | 7.0025 | 26.1817 | 28.6824 | 38.1855 | 45.1879 | 16.0224 | 10.1694 | 2.3337 | 2.5006 | 4.6687 | 4.0012 | 9.5031 | 7.0025 | 26.1917 | 28.6924 | 38.1955 | 45.1979 | 0.01
1.5673 | 7.0396 | 1.8522 | 1.7784 | 2.2612 | 2.5567 | 5.8918 | 4.1135 | 8.6068 | 10.3852 | 16.277 | 20.3904 | 1.5773 | 7.0396 | 1.8522 | 1.7784 | 2.2612 | 2.5567 | 5.8918 | 4.1135 | 8.6168 | 10.3952 | 16.287 | 20.4004 | 0.01
13.5036 | 9.6258 | 2.2501 | 2.3752 | 4.2506 | 3.7504 | 8.8759 | 6.5007 | 23.1293 | 25.5045 | 34.3804 | 40.8811 | 13.5136 | 9.6258 | 2.2501 | 2.3752 | 4.2506 | 3.7504 | 8.8759 | 6.5007 | 23.1393 | 25.5145 | 34.3904 | 40.8911 | 0.01
0.21402 | 6.7464 | 1.8071 | 1.7107 | 2.0357 | 2.4214 | 5.5535 | 3.8428 | 6.9604 | 8.6711 | 14.2246 | 18.0674 | 0.22402 | 6.7464 | 1.8071 | 1.7107 | 2.0357 | 2.4214 | 5.5535 | 3.8428 | 6.9704 | 8.6811 | 14.2346 | 18.0774 | 0.01
0.14578 | 6.7316 | 1.8049 | 1.7073 | 2.0243 | 2.4146 | 5.5364 | 3.8292 | 6.8774 | 8.5847 | 14.1211 | 17.9503 | 0.15578 | 6.7316 | 1.8049 | 1.7073 | 2.0243 | 2.4146 | 5.5364 | 3.8292 | 6.8874 | 8.5947 | 14.1311 | 17.9603 | 0.01
6.3738 | 8.081 | 2.0125 | 2.0187 | 3.0623 | 3.0374 | 7.0935 | 5.0748 | 14.4548 | 16.4735 | 23.5669 | 28.6417 | 6.3838 | 8.081 | 2.0125 | 2.0187 | 3.0623 | 3.0374 | 7.0935 | 5.0748 | 14.4648 | 16.4835 | 23.5769 | 28.6517 | 0.01
16.4514 | 10.2645 | 2.3484 | 2.5226 | 4.7419 | 4.0451 | 9.6128 | 7.0903 | 26.7158 | 29.2384 | 38.8513 | 45.9415 | 16.4614 | 10.2645 | 2.3484 | 2.5226 | 4.7419 | 4.0451 | 9.6128 | 7.0903 | 26.7258 | 29.2484 | 38.8613 | 45.9515 | 0.01
13.4295 | 9.6097 | 2.2477 | 2.3715 | 4.2383 | 3.743 | 8.8574 | 6.4859 | 23.0392 | 25.4107 | 34.2681 | 40.754 | 13.4395 | 9.6097 | 2.2477 | 2.3715 | 4.2383 | 3.743 | 8.8574 | 6.4859 | 23.0492 | 25.4207 | 34.2781 | 40.764 | 0.01
-7.4375 | 5.0886 | 1.5521 | 1.3281 | 0.76042 | 1.6563 | 3.6406 | 2.3125 | -2.3489 | -1.0208 | 2.6199 | 4.9324 | -7.4275 | 5.0886 | 1.5521 | 1.3281 | 0.76042 | 1.6563 | 3.6406 | 2.3125 | -2.3389 | -1.0108 | 2.6299 | 4.9424 | 0.01
-2.1955 | 6.2243 | 1.7268 | 1.5902 | 1.6341 | 2.1805 | 4.9511 | 3.3609 | 4.0288 | 5.6191 | 10.5702 | 13.9311 | -2.1855 | 6.2243 | 1.7268 | 1.5902 | 1.6341 | 2.1805 | 4.9511 | 3.3609 | 4.0388 | 5.6291 | 10.5802 | 13.9411 | 0.01
-0.86628 | 6.5123 | 1.7711 | 1.6567 | 1.8556 | 2.3134 | 5.2834 | 3.6267 | 5.646 | 7.3027 | 12.5861 | 16.2129 | -0.85628 | 6.5123 | 1.7711 | 1.6567 | 1.8556 | 2.3134 | 5.2834 | 3.6267 | 5.656 | 7.3127 | 12.5961 | 16.2229 | 0.01
7.4517 | 8.3145 | 2.0484 | 2.0726 | 3.2419 | 3.1452 | 7.3629 | 5.2903 | 15.7662 | 17.8388 | 25.2017 | 30.492 | 7.4617 | 8.3145 | 2.0484 | 2.0726 | 3.2419 | 3.1452 | 7.3629 | 5.2903 | 15.7762 | 17.8488 | 25.2117 | 30.502 | 0.01
-4.548 | 5.7146 | 1.6484 | 1.4726 | 1.242 | 1.9452 | 4.363 | 2.8904 | 1.1666 | 2.6392 | 7.0022 | 9.8926 | -4.538 | 5.7146 | 1.6484 | 1.4726 | 1.242 | 1.9452 | 4.363 | 2.8904 | 1.1766 | 2.6492 | 7.0122 | 9.9026 | 0.01
10.1638 | 8.9022 | 2.1388 | 2.2082 | 3.694 | 3.4164 | 8.0409 | 5.8328 | 19.066 | 21.2741 | 29.3151 | 35.1479 | 10.1738 | 8.9022 | 2.1388 | 2.2082 | 3.694 | 3.4164 | 8.0409 | 5.8328 | 19.076 | 21.2841 | 29.3251 | 35.1579 | 0.01
7.2783 | 8.277 | 2.0426 | 2.0639 | 3.213 | 3.1278 | 7.3196 | 5.2557 | 15.5552 | 17.6191 | 24.9387 | 30.1943 | 7.2883 | 8.277 | 2.0426 | 2.0639 | 3.213 | 3.1278 | 7.3196 | 5.2557 | 15.5652 | 17.6291 | 24.9487 | 30.2043 | 0.01
1.4575 | 7.0158 | 1.8486 | 1.7729 | 2.2429 | 2.5457 | 5.8644 | 4.0915 | 8.4732 | 10.2461 | 16.1105 | 20.202 | 1.4675 | 7.0158 | 1.8486 | 1.7729 | 2.2429 | 2.5457 | 5.8644 | 4.0915 | 8.4832 | 10.2561 | 16.1205 | 20.212 | 0.01
-0.57037 | 6.5764 | 1.781 | 1.6715 | 1.9049 | 2.343 | 5.3574 | 3.6859 | 6.0061 | 7.6775 | 13.0349 | 16.7209 | -0.56037 | 6.5764 | 1.781 | 1.6715 | 1.9049 | 2.343 | 5.3574 | 3.6859 | 6.0161 | 7.6875 | 13.0449 | 16.7309 | 0.01
2.3931 | 7.2185 | 1.8798 | 1.8197 | 2.3989 | 2.6393 | 6.0983 | 4.2786 | 9.6116 | 11.4313 | 17.5295 | 21.8082 | 2.4031 | 7.2185 | 1.8798 | 1.8197 | 2.3989 | 2.6393 | 6.0983 | 4.2786 | 9.6216 | 11.4413 | 17.5395 | 21.8182 | 0.01
14.9926 | 9.9484 | 2.2998 | 2.4496 | 4.4988 | 3.8993 | 9.2481 | 6.7985 | 24.941 | 27.3906 | 36.6387 | 43.4372 | 15.0026 | 9.9484 | 2.2998 | 2.4496 | 4.4988 | 3.8993 | 9.2481 | 6.7985 | 24.951 | 27.4006 | 36.6487 | 43.4472 | 0.01
5.5444 | 7.9013 | 1.9848 | 1.9772 | 2.9241 | 2.9544 | 6.8861 | 4.9089 | 13.4457 | 15.423 | 22.3091 | 27.218 | 5.5544 | 7.9013 | 1.9848 | 1.9772 | 2.9241 | 2.9544 | 6.8861 | 4.9089 | 13.4557 | 15.433 | 22.3191 | 27.228 | 0.01
13.6245 | 9.652 | 2.2542 | 2.3812 | 4.2708 | 3.7625 | 8.9061 | 6.5249 | 23.2765 | 25.6577 | 34.5638 | 41.0887 | 13.6345 | 9.652 | 2.2542 | 2.3812 | 4.2708 | 3.7625 | 8.9061 | 6.5249 | 23.2865 | 25.6677 | 34.5738 | 41.0987 | 0.01
1.3803 | 6.9991 | 1.846 | 1.769 | 2.2301 | 2.538 | 5.8451 | 4.0761 | 8.3794 | 10.1484 | 15.9935 | 20.0695 | 1.3903 | 6.9991 | 1.846 | 1.769 | 2.2301 | 2.538 | 5.8451 | 4.0761 | 8.3894 | 10.1584 | 16.0035 | 20.0795 | 0.01
9.4004 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.8501 | 5.6801 | 18.1371 | 20.3071 | 28.1572 | 33.8373 | 9.4104 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.8501 | 5.6801 | 18.1471 | 20.3171 | 28.1672 | 33.8473 | 0.01
5.1169 | 7.8087 | 1.9706 | 1.9558 | 2.8528 | 2.9117 | 6.7792 | 4.8234 | 12.9255 | 14.8813 | 21.6606 | 26.4839 | 5.1269 | 7.8087 | 1.9706 | 1.9558 | 2.8528 | 2.9117 | 6.7792 | 4.8234 | 12.9355 | 14.8913 | 21.6706 | 26.4939 | 0.01
-0.84508 | 6.5169 | 1.7718 | 1.6577 | 1.8592 | 2.3155 | 5.2887 | 3.631 | 5.6718 | 7.3296 | 12.6183 | 16.2493 | -0.83508 | 6.5169 | 1.7718 | 1.6577 | 1.8592 | 2.3155 | 5.2887 | 3.631 | 5.6818 | 7.3396 | 12.6283 | 16.2593 | 0.01
14.9278 | 9.9344 | 2.2976 | 2.4464 | 4.488 | 3.8928 | 9.232 | 6.7856 | 24.8622 | 27.3086 | 36.5405 | 43.3261 | 14.9378 | 9.9344 | 2.2976 | 2.4464 | 4.488 | 3.8928 | 9.232 | 6.7856 | 24.8722 | 27.3186 | 36.5505 | 43.3361 | 0.01
9.9078 | 8.8467 | 2.1303 | 2.1954 | 3.6513 | 3.3908 | 7.977 | 5.7816 | 18.7545 | 20.9499 | 28.9268 | 34.7084 | 9.9178 | 8.8467 | 2.1303 | 2.1954 | 3.6513 | 3.3908 | 7.977 | 5.7816 | 18.7645 | 20.9599 | 28.9368 | 34.7184 | 0.01
5.1469 | 7.8152 | 1.9716 | 1.9573 | 2.8578 | 2.9147 | 6.7867 | 4.8294 | 12.962 | 14.9194 | 21.7061 | 26.5355 | 5.1569 | 7.8152 | 1.9716 | 1.9573 | 2.8578 | 2.9147 | 6.7867 | 4.8294 | 12.972 | 14.9294 | 21.7161 | 26.5455 | 0.01
3.5807 | 7.4758 | 1.9194 | 1.879 | 2.5968 | 2.7581 | 6.3952 | 4.5161 | 11.0565 | 12.9355 | 19.3307 | 23.8468 | 3.5907 | 7.4758 | 1.9194 | 1.879 | 2.5968 | 2.7581 | 6.3952 | 4.5161 | 11.0665 | 12.9455 | 19.3407 | 23.8568 | 0.01
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2043 | 14.1305 | 20.7616 | 25.4664 | 4.5341 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2143 | 14.1405 | 20.7716 | 25.4764 | 0.01
8.6671 | 8.5779 | 2.0889 | 2.1334 | 3.4445 | 3.2667 | 7.6668 | 5.5334 | 17.2449 | 19.3783 | 27.0451 | 32.5785 | 8.6771 | 8.5779 | 2.0889 | 2.1334 | 3.4445 | 3.2667 | 7.6668 | 5.5334 | 17.2549 | 19.3883 | 27.0551 | 32.5885 | 0.01
8.4187 | 8.5241 | 2.0806 | 2.1209 | 3.4031 | 3.2419 | 7.6047 | 5.4837 | 16.9428 | 19.0637 | 26.6684 | 32.1522 | 8.4287 | 8.5241 | 2.0806 | 2.1209 | 3.4031 | 3.2419 | 7.6047 | 5.4837 | 16.9528 | 19.0737 | 26.6784 | 32.1622 | 0.01
-9.9815 | 4.5373 | 1.4673 | 1.2009 | 0.33642 | 1.4019 | 3.0046 | 1.8037 | -5.4442 | -4.2432 | -1.2386 | 0.5651 | -9.9715 | 4.5373 | 1.4673 | 1.2009 | 0.33642 | 1.4019 | 3.0046 | 1.8037 | -5.4342 | -4.2332 | -1.2286 | 0.5751 | 0.01
17.7361 | 10.5428 | 2.3912 | 2.5868 | 4.956 | 4.1736 | 9.934 | 7.3472 | 28.2789 | 30.8657 | 40.7997 | 48.1469 | 17.7461 | 10.5428 | 2.3912 | 2.5868 | 4.956 | 4.1736 | 9.934 | 7.3472 | 28.2889 | 30.8757 | 40.8097 | 48.1569 | 0.01
14.6958 | 9.8841 | 2.2899 | 2.4348 | 4.4493 | 3.8696 | 9.174 | 6.7392 | 24.5799 | 27.0147 | 36.1887 | 42.9279 | 14.7058 | 9.8841 | 2.2899 | 2.4348 | 4.4493 | 3.8696 | 9.174 | 6.7392 | 24.5899 | 27.0247 | 36.1987 | 42.9379 | 0.01
6.9703 | 8.2102 | 2.0323 | 2.0485 | 3.1617 | 3.097 | 7.2426 | 5.1941 | 15.1805 | 17.229 | 24.4716 | 29.6656 | 6.9803 | 8.2102 | 2.0323 | 2.0485 | 3.1617 | 3.097 | 7.2426 | 5.1941 | 15.1905 | 17.239 | 24.4816 | 29.6756 | 0.01
-2.7649 | 6.1009 | 1.7078 | 1.5618 | 1.5392 | 2.1235 | 4.8088 | 3.247 | 3.336 | 4.8978 | 9.7066 | 12.9536 | -2.7549 | 6.1009 | 1.7078 | 1.5618 | 1.5392 | 2.1235 | 4.8088 | 3.247 | 3.346 | 4.9078 | 9.7166 | 12.9636 | 0.01
8.3695 | 8.5134 | 2.079 | 2.1185 | 3.3949 | 3.2369 | 7.5924 | 5.4739 | 16.8829 | 19.0014 | 26.5937 | 32.0676 | 8.3795 | 8.5134 | 2.079 | 2.1185 | 3.3949 | 3.2369 | 7.5924 | 5.4739 | 16.8929 | 19.0114 | 26.6037 | 32.0776 | 0.01
0.31258 | 6.7677 | 1.8104 | 1.7156 | 2.0521 | 2.4313 | 5.5781 | 3.8625 | 7.0803 | 8.7959 | 14.3741 | 18.2366 | 0.32258 | 6.7677 | 1.8104 | 1.7156 | 2.0521 | 2.4313 | 5.5781 | 3.8625 | 7.0903 | 8.8059 | 14.3841 | 18.2466 | 0.01
14.0166 | 9.7369 | 2.2672 | 2.4008 | 4.3361 | 3.8017 | 9.0041 | 6.6033 | 23.7535 | 26.1543 | 35.1584 | 41.7618 | 14.0266 | 9.7369 | 2.2672 | 2.4008 | 4.3361 | 3.8017 | 9.0041 | 6.6033 | 23.7635 | 26.1643 | 35.1684 | 41.7718 | 0.01
7.5685 | 8.3398 | 2.0523 | 2.0784 | 3.2614 | 3.1568 | 7.3921 | 5.3137 | 15.9083 | 17.9867 | 25.3788 | 30.6925 | 7.5785 | 8.3398 | 2.0523 | 2.0784 | 3.2614 | 3.1568 | 7.3921 | 5.3137 | 15.9183 | 17.9967 | 25.3888 | 30.7025 | 0.01
5.9811 | 7.9959 | 1.9994 | 1.9991 | 2.9968 | 2.9981 | 6.9953 | 4.9962 | 13.977 | 15.976 | 22.9713 | 27.9675 | 5.9911 | 7.9959 | 1.9994 | 1.9991 | 2.9968 | 2.9981 | 6.9953 | 4.9962 | 13.987 | 15.986 | 22.9813 | 27.9775 | 0.01
3.3981 | 7.4363 | 1.9133 | 1.8699 | 2.5664 | 2.7398 | 6.3495 | 4.4796 | 10.8344 | 12.7043 | 19.0538 | 23.5335 | 3.4081 | 7.4363 | 1.9133 | 1.8699 | 2.5664 | 2.7398 | 6.3495 | 4.4796 | 10.8444 | 12.7143 | 19.0638 | 23.5435 | 0.01
6.2917 | 8.0632 | 2.0097 | 2.0146 | 3.0486 | 3.0292 | 7.0729 | 5.0583 | 14.3549 | 16.3695 | 23.4424 | 28.5007 | 6.3017 | 8.0632 | 2.0097 | 2.0146 | 3.0486 | 3.0292 | 7.0729 | 5.0583 | 14.3649 | 16.3795 | 23.4524 | 28.5107 | 0.01
3.5617 | 7.4717 | 1.9187 | 1.8781 | 2.5936 | 2.7562 | 6.3904 | 4.5123 | 11.0334 | 12.9115 | 19.3019 | 23.8143 | 3.5717 | 7.4717 | 1.9187 | 1.8781 | 2.5936 | 2.7562 | 6.3904 | 4.5123 | 11.0434 | 12.9215 | 19.3119 | 23.8243 | 0.01
13.4989 | 9.6248 | 2.25 | 2.3749 | 4.2498 | 3.7499 | 8.8747 | 6.4998 | 23.1236 | 25.4986 | 34.3733 | 40.8731 | 13.5089 | 9.6248 | 2.25 | 2.3749 | 4.2498 | 3.7499 | 8.8747 | 6.4998 | 23.1336 | 25.5086 | 34.3833 | 40.8831 | 0.01
10.3918 | 8.9516 | 2.1464 | 2.2196 | 3.732 | 3.4392 | 8.098 | 5.8784 | 19.3434 | 21.563 | 29.6609 | 35.5393 | 10.4018 | 8.9516 | 2.1464 | 2.2196 | 3.732 | 3.4392 | 8.098 | 5.8784 | 19.3534 | 21.573 | 29.6709 | 35.5493 | 0.01
1.0548 | 6.9285 | 1.8352 | 1.7527 | 2.1758 | 2.5055 | 5.7637 | 4.011 | 7.9833 | 9.7361 | 15.4998 | 19.5107 | 1.0648 | 6.9285 | 1.8352 | 1.7527 | 2.1758 | 2.5055 | 5.7637 | 4.011 | 7.9933 | 9.7461 | 15.5098 | 19.5207 | 0.01
16.2026 | 10.2106 | 2.3401 | 2.5101 | 4.7004 | 4.0203 | 9.5506 | 7.0405 | 26.4131 | 28.9233 | 38.4739 | 45.5144 | 16.2126 | 10.2106 | 2.3401 | 2.5101 | 4.7004 | 4.0203 | 9.5506 | 7.0405 | 26.4231 | 28.9333 | 38.4839 | 45.5244 | 0.01
8.5304 | 8.5483 | 2.0843 | 2.1265 | 3.4217 | 3.253 | 7.6326 | 5.5061 | 17.0786 | 19.2052 | 26.8378 | 32.3438 | 8.5404 | 8.5483 | 2.0843 | 2.1265 | 3.4217 | 3.253 | 7.6326 | 5.5061 | 17.0886 | 19.2152 | 26.8478 | 32.3538 | 0.01
7.3385 | 8.29 | 2.0446 | 2.0669 | 3.2231 | 3.1339 | 7.3346 | 5.2677 | 15.6285 | 17.6955 | 25.0301 | 30.2978 | 7.3485 | 8.29 | 2.0446 | 2.0669 | 3.2231 | 3.1339 | 7.3346 | 5.2677 | 15.6385 | 17.7055 | 25.0401 | 30.3078 | 0.01
-11.3977 | 4.2305 | 1.4201 | 1.1301 | 0.10039 | 1.2602 | 2.6506 | 1.5205 | -7.1672 | -6.0371 | -3.3865 | -1.866 | -11.3877 | 4.2305 | 1.4201 | 1.1301 | 0.10039 | 1.2602 | 2.6506 | 1.5205 | -7.1572 | -6.0271 | -3.3765 | -1.856 | 0.01
4.3995 | 7.6532 | 1.9466 | 1.92 | 2.7332 | 2.8399 | 6.5999 | 4.6799 | 12.0527 | 13.9727 | 20.5726 | 25.2525 | 4.4095 | 7.6532 | 1.9466 | 1.92 | 2.7332 | 2.8399 | 6.5999 | 4.6799 | 12.0627 | 13.9827 | 20.5826 | 25.2625 | 0.01
14.4103 | 9.8222 | 2.2803 | 2.4205 | 4.4017 | 3.841 | 9.1026 | 6.6821 | 24.2325 | 26.6531 | 35.7556 | 42.4377 | 14.4203 | 9.8222 | 2.2803 | 2.4205 | 4.4017 | 3.841 | 9.1026 | 6.6821 | 24.2425 | 26.6631 | 35.7656 | 42.4477 | 0.01
-4.8914 | 5.6402 | 1.637 | 1.4554 | 1.1848 | 1.9109 | 4.2771 | 2.8217 | 0.74876 | 2.2042 | 6.4813 | 9.3031 | -4.8814 | 5.6402 | 1.637 | 1.4554 | 1.1848 | 1.9109 | 4.2771 | 2.8217 | 0.75876 | 2.2142 | 6.4913 | 9.3131 | 0.01
15.1442 | 9.9812 | 2.3048 | 2.4572 | 4.524 | 3.9144 | 9.2861 | 6.8288 | 25.1255 | 27.5827 | 36.8687 | 43.6976 | 15.1542 | 9.9812 | 2.3048 | 2.4572 | 4.524 | 3.9144 | 9.2861 | 6.8288 | 25.1355 | 27.5927 | 36.8787 | 43.7076 | 0.01
6.8025 | 8.1739 | 2.0267 | 2.0401 | 3.1337 | 3.0802 | 7.2006 | 5.1605 | 14.9763 | 17.0165 | 24.2171 | 29.3776 | 6.8125 | 8.1739 | 2.0267 | 2.0401 | 3.1337 | 3.0802 | 7.2006 | 5.1605 | 14.9863 | 17.0265 | 24.2271 | 29.3876 | 0.01
7.5565 | 8.3372 | 2.0519 | 2.0778 | 3.2594 | 3.1556 | 7.3891 | 5.3113 | 15.8937 | 17.9716 | 25.3607 | 30.672 | 7.5665 | 8.3372 | 2.0519 | 2.0778 | 3.2594 | 3.1556 | 7.3891 | 5.3113 | 15.9037 | 17.9816 | 25.3707 | 30.682 | 0.01
7.1078 | 8.24 | 2.0369 | 2.0554 | 3.1846 | 3.1108 | 7.2769 | 5.2216 | 15.3478 | 17.4032 | 24.6802 | 29.9017 | 7.1178 | 8.24 | 2.0369 | 2.0554 | 3.1846 | 3.1108 | 7.2769 | 5.2216 | 15.3578 | 17.4132 | 24.6902 | 29.9117 | 0.01
5.4872 | 7.8889 | 1.9829 | 1.9744 | 2.9145 | 2.9487 | 6.8718 | 4.8974 | 13.3761 | 15.3505 | 22.2223 | 27.1197 | 5.4972 | 7.8889 | 1.9829 | 1.9744 | 2.9145 | 2.9487 | 6.8718 | 4.8974 | 13.3861 | 15.3605 | 22.2323 | 27.1297 | 0.01
-0.20801 | 6.6549 | 1.7931 | 1.6896 | 1.9653 | 2.3792 | 5.448 | 3.7584 | 6.4469 | 8.1365 | 13.5845 | 17.3429 | -0.19801 | 6.6549 | 1.7931 | 1.6896 | 1.9653 | 2.3792 | 5.448 | 3.7584 | 6.4569 | 8.1465 | 13.5945 | 17.3529 | 0.01
17.5186 | 10.4957 | 2.384 | 2.5759 | 4.9198 | 4.1519 | 9.8796 | 7.3037 | 28.0143 | 30.5902 | 40.4698 | 47.7735 | 17.5286 | 10.4957 | 2.384 | 2.5759 | 4.9198 | 4.1519 | 9.8796 | 7.3037 | 28.0243 | 30.6002 | 40.4798 | 47.7835 | 0.01
10.1071 | 8.8899 | 2.1369 | 2.2054 | 3.6845 | 3.4107 | 8.0268 | 5.8214 | 18.997 | 21.2024 | 29.2292 | 35.0506 | 10.1171 | 8.8899 | 2.1369 | 2.2054 | 3.6845 | 3.4107 | 8.0268 | 5.8214 | 19.007 | 21.2124 | 29.2392 | 35.0606 | 0.01
8.5568 | 8.554 | 2.0852 | 2.1278 | 3.4261 | 3.2557 | 7.6392 | 5.5114 | 17.1107 | 19.2386 | 26.8777 | 32.3891 | 8.5668 | 8.554 | 2.0852 | 2.1278 | 3.4261 | 3.2557 | 7.6392 | 5.5114 | 17.1207 | 19.2486 | 26.8877 | 32.3991 | 0.01
6.2378 | 8.0515 | 2.0079 | 2.0119 | 3.0396 | 3.0238 | 7.0594 | 5.0476 | 14.2893 | 16.3012 | 23.3606 | 28.4082 | 6.2478 | 8.0515 | 2.0079 | 2.0119 | 3.0396 | 3.0238 | 7.0594 | 5.0476 | 14.2993 | 16.3112 | 23.3706 | 28.4182 | 0.01
-0.17002 | 6.6632 | 1.7943 | 1.6915 | 1.9717 | 2.383 | 5.4575 | 3.766 | 6.4931 | 8.1846 | 13.6421 | 17.4081 | -0.16002 | 6.6632 | 1.7943 | 1.6915 | 1.9717 | 2.383 | 5.4575 | 3.766 | 6.5031 | 8.1946 | 13.6521 | 17.4181 | 0.01
14.1065 | 9.7564 | 2.2702 | 2.4053 | 4.3511 | 3.8106 | 9.0266 | 6.6213 | 23.8629 | 26.2682 | 35.2948 | 41.9161 | 14.1165 | 9.7564 | 2.2702 | 2.4053 | 4.3511 | 3.8106 | 9.0266 | 6.6213 | 23.8729 | 26.2782 | 35.3048 | 41.9261 | 0.01
3.8564 | 7.5356 | 1.9285 | 1.8928 | 2.6427 | 2.7856 | 6.4641 | 4.5713 | 11.392 | 13.2848 | 19.7489 | 24.3202 | 3.8664 | 7.5356 | 1.9285 | 1.8928 | 2.6427 | 2.7856 | 6.4641 | 4.5713 | 11.402 | 13.2948 | 19.7589 | 24.3302 | 0.01
-3.938 | 5.8468 | 1.6687 | 1.5031 | 1.3437 | 2.0062 | 4.5155 | 3.0124 | 1.9088 | 3.4119 | 7.9273 | 10.9397 | -3.928 | 5.8468 | 1.6687 | 1.5031 | 1.3437 | 2.0062 | 4.5155 | 3.0124 | 1.9188 | 3.4219 | 7.9373 | 10.9497 | 0.01
8.0713 | 8.4488 | 2.069 | 2.1036 | 3.3452 | 3.2071 | 7.5178 | 5.4143 | 16.5201 | 18.6237 | 26.1415 | 31.5558 | 8.0813 | 8.4488 | 2.069 | 2.1036 | 3.3452 | 3.2071 | 7.5178 | 5.4143 | 16.5301 | 18.6337 | 26.1515 | 31.5658 | 0.01
-3.3537 | 5.9734 | 1.6882 | 1.5323 | 1.4411 | 2.0646 | 4.6616 | 3.1293 | 2.6197 | 4.152 | 8.8136 | 11.9428 | -3.3437 | 5.9734 | 1.6882 | 1.5323 | 1.4411 | 2.0646 | 4.6616 | 3.1293 | 2.6297 | 4.162 | 8.8236 | 11.9528 | 0.01
-2.1228 | 6.2401 | 1.7292 | 1.5939 | 1.6462 | 2.1877 | 4.9693 | 3.3754 | 4.1173 | 5.7111 | 10.6804 | 14.0558 | -2.1128 | 6.2401 | 1.7292 | 1.5939 | 1.6462 | 2.1877 | 4.9693 | 3.3754 | 4.1273 | 5.7211 | 10.6904 | 14.0658 | 0.01
3.4464 | 7.4467 | 1.9149 | 1.8723 | 2.5744 | 2.7446 | 6.3616 | 4.4893 | 10.8932 | 12.7655 | 19.1271 | 23.6164 | 3.4564 | 7.4467 | 1.9149 | 1.8723 | 2.5744 | 2.7446 | 6.3616 | 4.4893 | 10.9032 | 12.7755 | 19.1371 | 23.6264 | 0.01
9.7406 | 8.8105 | 2.1247 | 2.187 | 3.6234 | 3.3741 | 7.9351 | 5.7481 | 18.551 | 20.7381 | 28.6732 | 34.4213 | 9.7506 | 8.8105 | 2.1247 | 2.187 | 3.6234 | 3.3741 | 7.9351 | 5.7481 | 18.561 | 20.7481 | 28.6832 | 34.4313 | 0.01
14.3409 | 9.8072 | 2.278 | 2.417 | 4.3902 | 3.8341 | 9.0852 | 6.6682 | 24.1481 | 26.5652 | 35.6504 | 42.3186 | 14.3509 | 9.8072 | 2.278 | 2.417 | 4.3902 | 3.8341 | 9.0852 | 6.6682 | 24.1581 | 26.5752 | 35.6604 | 42.3286 | 0.01
10.4801 | 8.9707 | 2.1493 | 2.224 | 3.7467 | 3.448 | 8.12 | 5.896 | 19.4508 | 21.6748 | 29.7948 | 35.6908 | 10.4901 | 8.9707 | 2.1493 | 2.224 | 3.7467 | 3.448 | 8.12 | 5.896 | 19.4608 | 21.6848 | 29.8048 | 35.7008 | 0.01
1.9422 | 7.1208 | 1.8647 | 1.7971 | 2.3237 | 2.5942 | 5.9855 | 4.1884 | 9.063 | 10.8601 | 16.8456 | 21.0341 | 1.9522 | 7.1208 | 1.8647 | 1.7971 | 2.3237 | 2.5942 | 5.9855 | 4.1884 | 9.073 | 10.8701 | 16.8556 | 21.0441 | 0.01
-3.5251 | 5.9362 | 1.6825 | 1.5237 | 1.4125 | 2.0475 | 4.6187 | 3.095 | 2.4111 | 3.9349 | 8.5536 | 11.6486 | -3.5151 | 5.9362 | 1.6825 | 1.5237 | 1.4125 | 2.0475 | 4.6187 | 3.095 | 2.4211 | 3.9449 | 8.5636 | 11.6586 | 0.01
6.3941 | 8.0854 | 2.0131 | 2.0197 | 3.0657 | 3.0394 | 7.0985 | 5.0788 | 14.4795 | 16.4992 | 23.5978 | 28.6766 | 6.4041 | 8.0854 | 2.0131 | 2.0197 | 3.0657 | 3.0394 | 7.0985 | 5.0788 | 14.4895 | 16.5092 | 23.6078 | 28.6866 | 0.01
8.1827 | 8.4729 | 2.0728 | 2.1091 | 3.3638 | 3.2183 | 7.5457 | 5.4365 | 16.6556 | 18.7647 | 26.3104 | 31.7469 | 8.1927 | 8.4729 | 2.0728 | 2.1091 | 3.3638 | 3.2183 | 7.5457 | 5.4365 | 16.6656 | 18.7747 | 26.3204 | 31.7569 | 0.01
13.4254 | 9.6088 | 2.2475 | 2.3713 | 4.2376 | 3.7425 | 8.8563 | 6.4851 | 23.0342 | 25.4055 | 34.2618 | 40.7469 | 13.4354 | 9.6088 | 2.2475 | 2.3713 | 4.2376 | 3.7425 | 8.8563 | 6.4851 | 23.0442 | 25.4155 | 34.2718 | 40.7569 | 0.01
12.781 | 9.4692 | 2.226 | 2.339 | 4.1302 | 3.6781 | 8.6952 | 6.3562 | 22.2502 | 24.5892 | 33.2844 | 39.6406 | 12.791 | 9.4692 | 2.226 | 2.339 | 4.1302 | 3.6781 | 8.6952 | 6.3562 | 22.2602 | 24.5992 | 33.2944 | 39.6506 | 0.01
5.32 | 7.8527 | 1.9773 | 1.966 | 2.8867 | 2.932 | 6.83 | 4.864 | 13.1726 | 15.1386 | 21.9686 | 26.8326 | 5.33 | 7.8527 | 1.9773 | 1.966 | 2.8867 | 2.932 | 6.83 | 4.864 | 13.1826 | 15.1486 | 21.9786 | 26.8426 | 0.01
0.36357 | 6.7788 | 1.8121 | 1.7182 | 2.0606 | 2.4364 | 5.5909 | 3.8727 | 7.1423 | 8.8605 | 14.4514 | 18.3241 | 0.37357 | 6.7788 | 1.8121 | 1.7182 | 2.0606 | 2.4364 | 5.5909 | 3.8727 | 7.1523 | 8.8705 | 14.4614 | 18.3341 | 0.01
4.4875 | 7.6723 | 1.9496 | 1.9244 | 2.7479 | 2.8487 | 6.6219 | 4.6975 | 12.1597 | 14.0841 | 20.706 | 25.4035 | 4.4975 | 7.6723 | 1.9496 | 1.9244 | 2.7479 | 2.8487 | 6.6219 | 4.6975 | 12.1697 | 14.0941 | 20.716 | 25.4135 | 0.01
16.3134 | 10.2346 | 2.3438 | 2.5157 | 4.7189 | 4.0313 | 9.5783 | 7.0627 | 26.548 | 29.0636 | 38.642 | 45.7047 | 16.3234 | 10.2346 | 2.3438 | 2.5157 | 4.7189 | 4.0313 | 9.5783 | 7.0627 | 26.558 | 29.0736 | 38.652 | 45.7147 | 0.01
4.2492 | 7.6207 | 1.9416 | 1.9125 | 2.7082 | 2.8249 | 6.5623 | 4.6498 | 11.8698 | 13.7823 | 20.3446 | 24.9944 | 4.2592 | 7.6207 | 1.9416 | 1.9125 | 2.7082 | 2.8249 | 6.5623 | 4.6498 | 11.8798 | 13.7923 | 20.3546 | 25.0044 | 0.01
3.7637 | 7.5155 | 1.9255 | 1.8882 | 2.6273 | 2.7764 | 6.4409 | 4.5527 | 11.2792 | 13.1674 | 19.6083 | 24.161 | 3.7737 | 7.5155 | 1.9255 | 1.8882 | 2.6273 | 2.7764 | 6.4409 | 4.5527 | 11.2892 | 13.1774 | 19.6183 | 24.171 | 0.01
-1.4859 | 6.3781 | 1.7505 | 1.6257 | 1.7524 | 2.2514 | 5.1285 | 3.5028 | 4.8922 | 6.5179 | 11.6464 | 15.1492 | -1.4759 | 6.3781 | 1.7505 | 1.6257 | 1.7524 | 2.2514 | 5.1285 | 3.5028 | 4.9022 | 6.5279 | 11.6564 | 15.1592 | 0.01
13.1201 | 9.5427 | 2.2373 | 2.356 | 4.1867 | 3.712 | 8.78 | 6.424 | 22.6628 | 25.0188 | 33.7988 | 40.2228 | 13.1301 | 9.5427 | 2.2373 | 2.356 | 4.1867 | 3.712 | 8.78 | 6.424 | 22.6728 | 25.0288 | 33.8088 | 40.2328 | 0.01
1.2847 | 6.9783 | 1.8428 | 1.7642 | 2.2141 | 2.5285 | 5.8212 | 4.0569 | 8.263 | 10.0273 | 15.8484 | 19.9054 | 1.2947 | 6.9783 | 1.8428 | 1.7642 | 2.2141 | 2.5285 | 5.8212 | 4.0569 | 8.273 | 10.0373 | 15.8584 | 19.9154 | 0.01
10.1324 | 8.8954 | 2.1377 | 2.2066 | 3.6887 | 3.4132 | 8.0331 | 5.8265 | 19.0278 | 21.2344 | 29.2675 | 35.094 | 10.1424 | 8.8954 | 2.1377 | 2.2066 | 3.6887 | 3.4132 | 8.0331 | 5.8265 | 19.0378 | 21.2444 | 29.2775 | 35.104 | 0.01
19.078 | 10.8336 | 2.4359 | 2.6539 | 5.1797 | 4.3078 | 10.2695 | 7.6156 | 29.9115 | 32.5654 | 42.8349 | 50.4505 | 19.088 | 10.8336 | 2.4359 | 2.6539 | 5.1797 | 4.3078 | 10.2695 | 7.6156 | 29.9215 | 32.5754 | 42.8449 | 50.4605 | 0.01
14.4903 | 9.8396 | 2.283 | 2.4245 | 4.4151 | 3.849 | 9.1226 | 6.6981 | 24.3299 | 26.7544 | 35.877 | 42.5751 | 14.5003 | 9.8396 | 2.283 | 2.4245 | 4.4151 | 3.849 | 9.1226 | 6.6981 | 24.3399 | 26.7644 | 35.887 | 42.5851 | 0.01
1.3037 | 6.9825 | 1.8435 | 1.7652 | 2.2173 | 2.5304 | 5.8259 | 4.0607 | 8.2862 | 10.0514 | 15.8773 | 19.9381 | 1.3137 | 6.9825 | 1.8435 | 1.7652 | 2.2173 | 2.5304 | 5.8259 | 4.0607 | 8.2962 | 10.0614 | 15.8873 | 19.9481 | 0.01
4.5343 | 7.6824 | 1.9511 | 1.9267 | 2.7557 | 2.8534 | 6.6336 | 4.7069 | 12.2167 | 14.1434 | 20.777 | 25.4838 | 4.5443 | 7.6824 | 1.9511 | 1.9267 | 2.7557 | 2.8534 | 6.6336 | 4.7069 | 12.2267 | 14.1534 | 20.787 | 25.4938 | 0.01
8.9171 | 8.632 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5834 | 17.5492 | 19.695 | 27.4243 | 33.0077 | 8.9271 | 8.632 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5834 | 17.5592 | 19.705 | 27.4343 | 33.0177 | 0.01
4.2696 | 7.6251 | 1.9423 | 1.9135 | 2.7116 | 2.827 | 6.5674 | 4.6539 | 11.8947 | 13.8082 | 20.3756 | 25.0295 | 4.2796 | 7.6251 | 1.9423 | 1.9135 | 2.7116 | 2.827 | 6.5674 | 4.6539 | 11.9047 | 13.8182 | 20.3856 | 25.0395 | 0.01
1.8769 | 7.1067 | 1.8626 | 1.7938 | 2.3128 | 2.5877 | 5.9692 | 4.1754 | 8.9835 | 10.7774 | 16.7466 | 20.922 | 1.8869 | 7.1067 | 1.8626 | 1.7938 | 2.3128 | 2.5877 | 5.9692 | 4.1754 | 8.9935 | 10.7874 | 16.7566 | 20.932 | 0.01
1.2769 | 6.9767 | 1.8426 | 1.7638 | 2.2128 | 2.5277 | 5.8192 | 4.0554 | 8.2536 | 10.0174 | 15.8367 | 19.8921 | 1.2869 | 6.9767 | 1.8426 | 1.7638 | 2.2128 | 2.5277 | 5.8192 | 4.0554 | 8.2636 | 10.0274 | 15.8467 | 19.9021 | 0.01
4.4293 | 7.6597 | 1.9476 | 1.9215 | 2.7382 | 2.8429 | 6.6073 | 4.6859 | 12.089 | 14.0105 | 20.6178 | 25.3037 | 4.4393 | 7.6597 | 1.9476 | 1.9215 | 2.7382 | 2.8429 | 6.6073 | 4.6859 | 12.099 | 14.0205 | 20.6278 | 25.3137 | 0.01
-0.71252 | 6.5456 | 1.7762 | 1.6644 | 1.8812 | 2.3287 | 5.3219 | 3.6575 | 5.8331 | 7.4975 | 12.8193 | 16.4768 | -0.70252 | 6.5456 | 1.7762 | 1.6644 | 1.8812 | 2.3287 | 5.3219 | 3.6575 | 5.8431 | 7.5075 | 12.8293 | 16.4868 | 0.01
0.56209 | 6.8218 | 1.8187 | 1.7281 | 2.0937 | 2.4562 | 5.6405 | 3.9124 | 7.3839 | 9.112 | 14.7525 | 18.6649 | 0.57209 | 6.8218 | 1.8187 | 1.7281 | 2.0937 | 2.4562 | 5.6405 | 3.9124 | 7.3939 | 9.122 | 14.7625 | 18.6749 | 0.01
3.2537 | 7.405 | 1.9085 | 1.8627 | 2.5423 | 2.7254 | 6.3134 | 4.4507 | 10.6587 | 12.5214 | 18.8348 | 23.2856 | 3.2637 | 7.405 | 1.9085 | 1.8627 | 2.5423 | 2.7254 | 6.3134 | 4.4507 | 10.6687 | 12.5314 | 18.8448 | 23.2956 | 0.01
4.564 | 7.6889 | 1.9521 | 1.9282 | 2.7607 | 2.8564 | 6.641 | 4.7128 | 12.2529 | 14.1811 | 20.8221 | 25.5349 | 4.574 | 7.6889 | 1.9521 | 1.9282 | 2.7607 | 2.8564 | 6.641 | 4.7128 | 12.2629 | 14.1911 | 20.8321 | 25.5449 | 0.01
17.5236 | 10.4968 | 2.3841 | 2.5762 | 4.9206 | 4.1524 | 9.8809 | 7.3047 | 28.0204 | 30.5966 | 40.4775 | 47.7823 | 17.5336 | 10.4968 | 2.3841 | 2.5762 | 4.9206 | 4.1524 | 9.8809 | 7.3047 | 28.0304 | 30.6066 | 40.4875 | 47.7923 | 0.01
8.2391 | 8.4851 | 2.0746 | 2.112 | 3.3732 | 3.2239 | 7.5598 | 5.4478 | 16.7242 | 18.8362 | 26.396 | 31.8438 | 8.2491 | 8.4851 | 2.0746 | 2.112 | 3.3732 | 3.2239 | 7.5598 | 5.4478 | 16.7342 | 18.8462 | 26.406 | 31.8538 | 0.01
11.3647 | 9.1623 | 2.1788 | 2.2682 | 3.8941 | 3.5365 | 8.3412 | 6.0729 | 20.527 | 22.7953 | 31.1364 | 37.2094 | 11.3747 | 9.1623 | 2.1788 | 2.2682 | 3.8941 | 3.5365 | 8.3412 | 6.0729 | 20.537 | 22.8053 | 31.1464 | 37.2194 | 0.01
-1.6549 | 6.3414 | 1.7448 | 1.6173 | 1.7242 | 2.2345 | 5.0863 | 3.469 | 4.6866 | 6.3038 | 11.3901 | 14.8591 | -1.6449 | 6.3414 | 1.7448 | 1.6173 | 1.7242 | 2.2345 | 5.0863 | 3.469 | 4.6966 | 6.3138 | 11.4001 | 14.8691 | 0.01
8.9418 | 8.6374 | 2.0981 | 2.1471 | 3.4903 | 3.2942 | 7.7354 | 5.5884 | 17.5791 | 19.7262 | 27.4617 | 33.05 | 8.9518 | 8.6374 | 2.0981 | 2.1471 | 3.4903 | 3.2942 | 7.7354 | 5.5884 | 17.5891 | 19.7362 | 27.4717 | 33.06 | 0.01
11.8561 | 9.2688 | 2.1952 | 2.2928 | 3.976 | 3.5856 | 8.464 | 6.1712 | 21.1249 | 23.4177 | 31.8817 | 38.053 | 11.8661 | 9.2688 | 2.1952 | 2.2928 | 3.976 | 3.5856 | 8.464 | 6.1712 | 21.1349 | 23.4277 | 31.8917 | 38.063 | 0.01
10.4949 | 8.9739 | 2.1498 | 2.2247 | 3.7492 | 3.4495 | 8.1237 | 5.899 | 19.4688 | 21.6936 | 29.8173 | 35.7163 | 10.5049 | 8.9739 | 2.1498 | 2.2247 | 3.7492 | 3.4495 | 8.1237 | 5.899 | 19.4788 | 21.7036 | 29.8273 | 35.7263 | 0.01
10.916 | 9.0651 | 2.1639 | 2.2458 | 3.8193 | 3.4916 | 8.229 | 5.9832 | 19.9811 | 22.2269 | 30.4559 | 36.4391 | 10.926 | 9.0651 | 2.1639 | 2.2458 | 3.8193 | 3.4916 | 8.229 | 5.9832 | 19.9911 | 22.2369 | 30.4659 | 36.4491 | 0.01
9.4413 | 8.7456 | 2.1147 | 2.1721 | 3.5736 | 3.3441 | 7.8603 | 5.6883 | 18.1869 | 20.359 | 28.2193 | 33.9076 | 9.4513 | 8.7456 | 2.1147 | 2.1721 | 3.5736 | 3.3441 | 7.8603 | 5.6883 | 18.1969 | 20.369 | 28.2293 | 33.9176 | 0.01
3.8479 | 7.5337 | 1.9283 | 1.8924 | 2.6413 | 2.7848 | 6.462 | 4.5696 | 11.3817 | 13.2741 | 19.7361 | 24.3056 | 3.8579 | 7.5337 | 1.9283 | 1.8924 | 2.6413 | 2.7848 | 6.462 | 4.5696 | 11.3917 | 13.2841 | 19.7461 | 24.3156 | 0.01
0.12473 | 6.727 | 1.8042 | 1.7062 | 2.0208 | 2.4125 | 5.5312 | 3.8249 | 6.8518 | 8.558 | 14.0892 | 17.9141 | 0.13473 | 6.727 | 1.8042 | 1.7062 | 2.0208 | 2.4125 | 5.5312 | 3.8249 | 6.8618 | 8.568 | 14.0992 | 17.9241 | 0.01
15.3826 | 10.0329 | 2.3128 | 2.4691 | 4.5638 | 3.9383 | 9.3457 | 6.8765 | 25.4155 | 27.8847 | 37.2303 | 44.1068 | 15.3926 | 10.0329 | 2.3128 | 2.4691 | 4.5638 | 3.9383 | 9.3457 | 6.8765 | 25.4255 | 27.8947 | 37.2403 | 44.1168 | 0.01
5.5747 | 7.9078 | 1.9858 | 1.9787 | 2.9291 | 2.9575 | 6.8937 | 4.9149 | 13.4825 | 15.4613 | 22.3549 | 27.2699 | 5.5847 | 7.9078 | 1.9858 | 1.9787 | 2.9291 | 2.9575 | 6.8937 | 4.9149 | 13.4925 | 15.4713 | 22.3649 | 27.2799 | 0.01
7.5314 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8632 | 17.9398 | 25.3227 | 30.629 | 7.5414 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8732 | 17.9498 | 25.3327 | 30.639 | 0.01
5.6536 | 7.9249 | 1.9885 | 1.9827 | 2.9423 | 2.9654 | 6.9134 | 4.9307 | 13.5786 | 15.5612 | 22.4746 | 27.4054 | 5.6636 | 7.9249 | 1.9885 | 1.9827 | 2.9423 | 2.9654 | 6.9134 | 4.9307 | 13.5886 | 15.5712 | 22.4846 | 27.4154 | 0.01
7.9005 | 8.4118 | 2.0633 | 2.095 | 3.3167 | 3.19 | 7.4751 | 5.3801 | 16.3122 | 18.4073 | 25.8824 | 31.2625 | 7.9105 | 8.4118 | 2.0633 | 2.095 | 3.3167 | 3.19 | 7.4751 | 5.3801 | 16.3222 | 18.4173 | 25.8924 | 31.2725 | 0.01
2.7503 | 7.2959 | 1.8917 | 1.8375 | 2.4584 | 2.675 | 6.1876 | 4.3501 | 10.0462 | 11.8837 | 18.0713 | 22.4213 | 2.7603 | 7.2959 | 1.8917 | 1.8375 | 2.4584 | 2.675 | 6.1876 | 4.3501 | 10.0562 | 11.8937 | 18.0813 | 22.4313 | 0.01
15.9912 | 10.1648 | 2.333 | 2.4996 | 4.6652 | 3.9991 | 9.4978 | 6.9982 | 26.156 | 28.6556 | 38.1534 | 45.1516 | 16.0012 | 10.1648 | 2.333 | 2.4996 | 4.6652 | 3.9991 | 9.4978 | 6.9982 | 26.166 | 28.6656 | 38.1634 | 45.1616 | 0.01
3.5741 | 7.4744 | 1.9191 | 1.8787 | 2.5957 | 2.7574 | 6.3935 | 4.5148 | 11.0485 | 12.9272 | 19.3207 | 23.8356 | 3.5841 | 7.4744 | 1.9191 | 1.8787 | 2.5957 | 2.7574 | 6.3935 | 4.5148 | 11.0585 | 12.9372 | 19.3307 | 23.8456 | 0.01
8.2161 | 8.4802 | 2.0739 | 2.1108 | 3.3693 | 3.2216 | 7.554 | 5.4432 | 16.6962 | 18.8071 | 26.3611 | 31.8043 | 8.2261 | 8.4802 | 2.0739 | 2.1108 | 3.3693 | 3.2216 | 7.554 | 5.4432 | 16.7062 | 18.8171 | 26.3711 | 31.8143 | 0.01
11.5303 | 9.1982 | 2.1843 | 2.2765 | 3.9217 | 3.553 | 8.3826 | 6.1061 | 20.7286 | 23.0051 | 31.3877 | 37.4937 | 11.5403 | 9.1982 | 2.1843 | 2.2765 | 3.9217 | 3.553 | 8.3826 | 6.1061 | 20.7386 | 23.0151 | 31.3977 | 37.5037 | 0.01
9.1597 | 8.6846 | 2.1053 | 2.158 | 3.5266 | 3.316 | 7.7899 | 5.6319 | 17.8443 | 20.0023 | 27.7923 | 33.4242 | 9.1697 | 8.6846 | 2.1053 | 2.158 | 3.5266 | 3.316 | 7.7899 | 5.6319 | 17.8543 | 20.0123 | 27.8023 | 33.4342 | 0.01
12.984 | 9.5132 | 2.2328 | 2.3492 | 4.164 | 3.6984 | 8.746 | 6.3968 | 22.4972 | 24.8464 | 33.5924 | 39.9892 | 12.994 | 9.5132 | 2.2328 | 2.3492 | 4.164 | 3.6984 | 8.746 | 6.3968 | 22.5072 | 24.8564 | 33.6024 | 39.9992 | 0.01
18.7844 | 10.7699 | 2.4261 | 2.6392 | 5.1307 | 4.2784 | 10.1961 | 7.5569 | 29.5543 | 32.1935 | 42.3896 | 49.9465 | 18.7944 | 10.7699 | 2.4261 | 2.6392 | 5.1307 | 4.2784 | 10.1961 | 7.5569 | 29.5643 | 32.2035 | 42.3996 | 49.9565 | 0.01
9.9286 | 8.8512 | 2.131 | 2.1964 | 3.6548 | 3.3929 | 7.9822 | 5.7857 | 18.7799 | 20.9763 | 28.9585 | 34.7442 | 9.9386 | 8.8512 | 2.131 | 2.1964 | 3.6548 | 3.3929 | 7.9822 | 5.7857 | 18.7899 | 20.9863 | 28.9685 | 34.7542 | 0.01
2.0856 | 7.1519 | 1.8695 | 1.8043 | 2.3476 | 2.6086 | 6.0214 | 4.2171 | 9.2375 | 11.0418 | 17.0632 | 21.2803 | 2.0956 | 7.1519 | 1.8695 | 1.8043 | 2.3476 | 2.6086 | 6.0214 | 4.2171 | 9.2475 | 11.0518 | 17.0732 | 21.2903 | 0.01
7.7123 | 8.371 | 2.0571 | 2.0856 | 3.2854 | 3.1712 | 7.4281 | 5.3425 | 16.0833 | 18.169 | 25.5971 | 30.9395 | 7.7223 | 8.371 | 2.0571 | 2.0856 | 3.2854 | 3.1712 | 7.4281 | 5.3425 | 16.0933 | 18.179 | 25.6071 | 30.9495 | 0.01
4.3418 | 7.6407 | 1.9447 | 1.9171 | 2.7236 | 2.8342 | 6.5855 | 4.6684 | 11.9825 | 13.8996 | 20.4851 | 25.1535 | 4.3518 | 7.6407 | 1.9447 | 1.9171 | 2.7236 | 2.8342 | 6.5855 | 4.6684 | 11.9925 | 13.9096 | 20.4951 | 25.1635 | 0.01
11.026 | 9.089 | 2.1675 | 2.2513 | 3.8377 | 3.5026 | 8.2565 | 6.0052 | 20.115 | 22.3663 | 30.6228 | 36.628 | 11.036 | 9.089 | 2.1675 | 2.2513 | 3.8377 | 3.5026 | 8.2565 | 6.0052 | 20.125 | 22.3763 | 30.6328 | 36.638 | 0.01
17.0012 | 10.3836 | 2.3667 | 2.5501 | 4.8335 | 4.1001 | 9.7503 | 7.2002 | 27.3849 | 29.9349 | 39.6852 | 46.8855 | 17.0112 | 10.3836 | 2.3667 | 2.5501 | 4.8335 | 4.1001 | 9.7503 | 7.2002 | 27.3949 | 29.9449 | 39.6952 | 46.8955 | 0.01
2.8353 | 7.3143 | 1.8945 | 1.8418 | 2.4726 | 2.6835 | 6.2088 | 4.3671 | 10.1496 | 11.9914 | 18.2002 | 22.5673 | 2.8453 | 7.3143 | 1.8945 | 1.8418 | 2.4726 | 2.6835 | 6.2088 | 4.3671 | 10.1596 | 12.0014 | 18.2102 | 22.5773 | 0.01
2.9314 | 7.3351 | 1.8977 | 1.8466 | 2.4886 | 2.6931 | 6.2329 | 4.3863 | 10.2666 | 12.1132 | 18.346 | 22.7323 | 2.9414 | 7.3351 | 1.8977 | 1.8466 | 2.4886 | 2.6931 | 6.2329 | 4.3863 | 10.2766 | 12.1232 | 18.356 | 22.7423 | 0.01
0.2458 | 6.7533 | 1.8082 | 1.7123 | 2.041 | 2.4246 | 5.5615 | 3.8492 | 6.9991 | 8.7114 | 14.2728 | 18.122 | 0.2558 | 6.7533 | 1.8082 | 1.7123 | 2.041 | 2.4246 | 5.5615 | 3.8492 | 7.0091 | 8.7214 | 14.2828 | 18.132 | 0.01
6.4896 | 8.1061 | 2.0163 | 2.0245 | 3.0816 | 3.049 | 7.1224 | 5.0979 | 14.5957 | 16.6202 | 23.7426 | 28.8405 | 6.4996 | 8.1061 | 2.0163 | 2.0245 | 3.0816 | 3.049 | 7.1224 | 5.0979 | 14.6057 | 16.6302 | 23.7526 | 28.8505 | 0.01
-6.0201 | 5.3956 | 1.5993 | 1.399 | 0.99665 | 1.798 | 3.995 | 2.596 | -0.62448 | 0.77452 | 4.7695 | 7.3655 | -6.0101 | 5.3956 | 1.5993 | 1.399 | 0.99665 | 1.798 | 3.995 | 2.596 | -0.61448 | 0.78452 | 4.7795 | 7.3755 | 0.01
3.3036 | 7.4158 | 1.9101 | 1.8652 | 2.5506 | 2.7304 | 6.3259 | 4.4607 | 10.7194 | 12.5846 | 18.9105 | 23.3712 | 3.3136 | 7.4158 | 1.9101 | 1.8652 | 2.5506 | 2.7304 | 6.3259 | 4.4607 | 10.7294 | 12.5946 | 18.9205 | 23.3812 | 0.01
8.8664 | 8.621 | 2.0955 | 2.1433 | 3.4777 | 3.2866 | 7.7166 | 5.5733 | 17.4874 | 19.6307 | 27.3473 | 32.9206 | 8.8764 | 8.621 | 2.0955 | 2.1433 | 3.4777 | 3.2866 | 7.7166 | 5.5733 | 17.4974 | 19.6407 | 27.3573 | 32.9306 | 0.01
13.6777 | 9.6635 | 2.2559 | 2.3839 | 4.2796 | 3.7678 | 8.9194 | 6.5355 | 23.3412 | 25.7251 | 34.6446 | 41.1801 | 13.6877 | 9.6635 | 2.2559 | 2.3839 | 4.2796 | 3.7678 | 8.9194 | 6.5355 | 23.3512 | 25.7351 | 34.6546 | 41.1901 | 0.01
7.5315 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8633 | 17.9399 | 25.3228 | 30.629 | 7.5415 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8733 | 17.9499 | 25.3328 | 30.639 | 0.01
6.5002 | 8.1084 | 2.0167 | 2.025 | 3.0834 | 3.05 | 7.1251 | 5.1 | 14.6086 | 16.6336 | 23.7587 | 28.8587 | 6.5102 | 8.1084 | 2.0167 | 2.025 | 3.0834 | 3.05 | 7.1251 | 5.1 | 14.6186 | 16.6436 | 23.7687 | 28.8687 | 0.01
12.3442 | 9.3746 | 2.2115 | 2.3172 | 4.0574 | 3.6344 | 8.586 | 6.2688 | 21.7187 | 24.036 | 32.622 | 38.8908 | 12.3542 | 9.3746 | 2.2115 | 2.3172 | 4.0574 | 3.6344 | 8.586 | 6.2688 | 21.7287 | 24.046 | 32.632 | 38.9008 | 0.01
-2.6847 | 6.1183 | 1.7105 | 1.5658 | 1.5526 | 2.1315 | 4.8288 | 3.2631 | 3.4337 | 4.9994 | 9.8283 | 13.0913 | -2.6747 | 6.1183 | 1.7105 | 1.5658 | 1.5526 | 2.1315 | 4.8288 | 3.2631 | 3.4437 | 5.0094 | 9.8383 | 13.1013 | 0.01
11.3098 | 9.1505 | 2.177 | 2.2655 | 3.885 | 3.531 | 8.3274 | 6.062 | 20.4602 | 22.7257 | 31.0532 | 37.1151 | 11.3198 | 9.1505 | 2.177 | 2.2655 | 3.885 | 3.531 | 8.3274 | 6.062 | 20.4702 | 22.7357 | 31.0632 | 37.1251 | 0.01
11.2312 | 9.1334 | 2.1744 | 2.2616 | 3.8719 | 3.5231 | 8.3078 | 6.0462 | 20.3646 | 22.6262 | 30.934 | 36.9802 | 11.2412 | 9.1334 | 2.1744 | 2.2616 | 3.8719 | 3.5231 | 8.3078 | 6.0462 | 20.3746 | 22.6362 | 30.944 | 36.9902 | 0.01
-2.2417 | 6.2143 | 1.7253 | 1.5879 | 1.6264 | 2.1758 | 4.9396 | 3.3517 | 3.9725 | 5.5605 | 10.5 | 13.8517 | -2.2317 | 6.2143 | 1.7253 | 1.5879 | 1.6264 | 2.1758 | 4.9396 | 3.3517 | 3.9825 | 5.5705 | 10.51 | 13.8617 | 0.01
13.1798 | 9.5556 | 2.2393 | 2.359 | 4.1966 | 3.718 | 8.795 | 6.436 | 22.7354 | 25.0944 | 33.8894 | 40.3253 | 13.1898 | 9.5556 | 2.2393 | 2.359 | 4.1966 | 3.718 | 8.795 | 6.436 | 22.7454 | 25.1044 | 33.8994 | 40.3353 | 0.01
-6.0136 | 5.397 | 1.5995 | 1.3993 | 0.99773 | 1.7986 | 3.9966 | 2.5973 | -0.61658 | 0.78274 | 4.7793 | 7.3766 | -6.0036 | 5.397 | 1.5995 | 1.3993 | 0.99773 | 1.7986 | 3.9966 | 2.5973 | -0.60658 | 0.79274 | 4.7893 | 7.3866 | 0.01
2.8839 | 7.3249 | 1.8961 | 1.8442 | 2.4807 | 2.6884 | 6.221 | 4.3768 | 10.2088 | 12.053 | 18.274 | 22.6508 | 2.8939 | 7.3249 | 1.8961 | 1.8442 | 2.4807 | 2.6884 | 6.221 | 4.3768 | 10.2188 | 12.063 | 18.284 | 22.6608 | 0.01
8.9173 | 8.6321 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5835 | 17.5494 | 19.6953 | 27.4246 | 33.0081 | 8.9273 | 8.6321 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5835 | 17.5594 | 19.7053 | 27.4346 | 33.0181 | 0.01
7.3594 | 8.2945 | 2.0453 | 2.068 | 3.2266 | 3.1359 | 7.3399 | 5.2719 | 15.654 | 17.722 | 25.0618 | 30.3337 | 7.3694 | 8.2945 | 2.0453 | 2.068 | 3.2266 | 3.1359 | 7.3399 | 5.2719 | 15.664 | 17.732 | 25.0718 | 30.3437 | 0.01
10.6967 | 9.0176 | 2.1566 | 2.2348 | 3.7828 | 3.4697 | 8.1742 | 5.9393 | 19.7143 | 21.9491 | 30.1233 | 36.0626 | 10.7067 | 9.0176 | 2.1566 | 2.2348 | 3.7828 | 3.4697 | 8.1742 | 5.9393 | 19.7243 | 21.9591 | 30.1333 | 36.0726 | 0.01
14.8238 | 9.9118 | 2.2941 | 2.4412 | 4.4706 | 3.8824 | 9.206 | 6.7648 | 24.7356 | 27.1768 | 36.3828 | 43.1475 | 14.8338 | 9.9118 | 2.2941 | 2.4412 | 4.4706 | 3.8824 | 9.206 | 6.7648 | 24.7456 | 27.1868 | 36.3928 | 43.1575 | 0.01
11.6384 | 9.2216 | 2.1879 | 2.2819 | 3.9397 | 3.5638 | 8.4096 | 6.1277 | 20.86 | 23.1419 | 31.5515 | 37.6792 | 11.6484 | 9.2216 | 2.1879 | 2.2819 | 3.9397 | 3.5638 | 8.4096 | 6.1277 | 20.87 | 23.1519 | 31.5615 | 37.6892 | 0.01
17.6788 | 10.5304 | 2.3893 | 2.5839 | 4.9465 | 4.1679 | 9.9197 | 7.3358 | 28.2092 | 30.7931 | 40.7128 | 48.0486 | 17.6888 | 10.5304 | 2.3893 | 2.5839 | 4.9465 | 4.1679 | 9.9197 | 7.3358 | 28.2192 | 30.8031 | 40.7228 | 48.0586 | 0.01
4.3589 | 7.6444 | 1.9453 | 1.9179 | 2.7265 | 2.8359 | 6.5897 | 4.6718 | 12.0033 | 13.9213 | 20.511 | 25.1828 | 4.3689 | 7.6444 | 1.9453 | 1.9179 | 2.7265 | 2.8359 | 6.5897 | 4.6718 | 12.0133 | 13.9313 | 20.521 | 25.1928 | 0.01
0.47148 | 6.8022 | 1.8157 | 1.7236 | 2.0786 | 2.4471 | 5.6179 | 3.8943 | 7.2736 | 8.9972 | 14.6151 | 18.5094 | 0.48148 | 6.8022 | 1.8157 | 1.7236 | 2.0786 | 2.4471 | 5.6179 | 3.8943 | 7.2836 | 9.0072 | 14.6251 | 18.5194 | 0.01
7.8912 | 8.4097 | 2.063 | 2.0946 | 3.3152 | 3.1891 | 7.4728 | 5.3782 | 16.3009 | 18.3955 | 25.8682 | 31.2465 | 7.9012 | 8.4097 | 2.063 | 2.0946 | 3.3152 | 3.1891 | 7.4728 | 5.3782 | 16.3109 | 18.4055 | 25.8782 | 31.2565 | 0.01
4.3809 | 7.6492 | 1.946 | 1.919 | 2.7301 | 2.8381 | 6.5952 | 4.6762 | 12.0301 | 13.9491 | 20.5444 | 25.2205 | 4.3909 | 7.6492 | 1.946 | 1.919 | 2.7301 | 2.8381 | 6.5952 | 4.6762 | 12.0401 | 13.9591 | 20.5544 | 25.2305 | 0.01
12.5045 | 9.4093 | 2.2168 | 2.3252 | 4.0841 | 3.6505 | 8.6261 | 6.3009 | 21.9138 | 24.2391 | 32.8652 | 39.1661 | 12.5145 | 9.4093 | 2.2168 | 2.3252 | 4.0841 | 3.6505 | 8.6261 | 6.3009 | 21.9238 | 24.2491 | 32.8752 | 39.1761 | 0.01
-2.5623 | 6.1448 | 1.7146 | 1.5719 | 1.5729 | 2.1438 | 4.8594 | 3.2875 | 3.5825 | 5.1544 | 10.0138 | 13.3013 | -2.5523 | 6.1448 | 1.7146 | 1.5719 | 1.5729 | 2.1438 | 4.8594 | 3.2875 | 3.5925 | 5.1644 | 10.0238 | 13.3113 | 0.01
5.628 | 7.9194 | 1.9876 | 1.9814 | 2.938 | 2.9628 | 6.907 | 4.9256 | 13.5474 | 15.5288 | 22.4358 | 27.3614 | 5.638 | 7.9194 | 1.9876 | 1.9814 | 2.938 | 2.9628 | 6.907 | 4.9256 | 13.5574 | 15.5388 | 22.4458 | 27.3714 | 0.01
-2.8667 | 6.0789 | 1.7044 | 1.5567 | 1.5222 | 2.1133 | 4.7833 | 3.2267 | 3.2122 | 4.7689 | 9.5522 | 12.7789 | -2.8567 | 6.0789 | 1.7044 | 1.5567 | 1.5222 | 2.1133 | 4.7833 | 3.2267 | 3.2222 | 4.7789 | 9.5622 | 12.7889 | 0.01
-6.8201 | 5.2223 | 1.5727 | 1.359 | 0.86332 | 1.718 | 3.795 | 2.436 | -1.5977 | -0.23874 | 3.5562 | 5.9922 | -6.8101 | 5.2223 | 1.5727 | 1.359 | 0.86332 | 1.718 | 3.795 | 2.436 | -1.5877 | -0.22874 | 3.5662 | 6.0022 | 0.01
-0.06598 | 6.6857 | 1.7978 | 1.6967 | 1.989 | 2.3934 | 5.4835 | 3.7868 | 6.6197 | 8.3164 | 13.7999 | 17.5867 | -0.05598 | 6.6857 | 1.7978 | 1.6967 | 1.989 | 2.3934 | 5.4835 | 3.7868 | 6.6297 | 8.3264 | 13.8099 | 17.5967 | 0.01
-4.274 | 5.774 | 1.6575 | 1.4863 | 1.2877 | 1.9726 | 4.4315 | 2.9452 | 1.4999 | 2.9862 | 7.4177 | 10.3629 | -4.264 | 5.774 | 1.6575 | 1.4863 | 1.2877 | 1.9726 | 4.4315 | 2.9452 | 1.5099 | 2.9962 | 7.4277 | 10.3729 | 0.01
9.4 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.85 | 5.68 | 18.1367 | 20.3067 | 28.1567 | 33.8367 | 9.41 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.85 | 5.68 | 18.1467 | 20.3167 | 28.1667 | 33.8467 | 0.01
-0.6032 | 6.5693 | 1.7799 | 1.6698 | 1.8995 | 2.3397 | 5.3492 | 3.6794 | 5.9661 | 7.6359 | 12.9851 | 16.6645 | -0.5932 | 6.5693 | 1.7799 | 1.6698 | 1.8995 | 2.3397 | 5.3492 | 3.6794 | 5.9761 | 7.6459 | 12.9951 | 16.6745 | 0.01
0.58262 | 6.8262 | 1.8194 | 1.7291 | 2.0971 | 2.4583 | 5.6457 | 3.9165 | 7.4089 | 9.138 | 14.7836 | 18.7002 | 0.59262 | 6.8262 | 1.8194 | 1.7291 | 2.0971 | 2.4583 | 5.6457 | 3.9165 | 7.4189 | 9.148 | 14.7936 | 18.7102 | 0.01
6.9663 | 8.2094 | 2.0322 | 2.0483 | 3.161 | 3.0966 | 7.2416 | 5.1933 | 15.1756 | 17.2239 | 24.4655 | 29.6587 | 6.9763 | 8.2094 | 2.0322 | 2.0483 | 3.161 | 3.0966 | 7.2416 | 5.1933 | 15.1856 | 17.2339 | 24.4755 | 29.6687 | 0.01
8.3163 | 8.5019 | 2.0772 | 2.1158 | 3.386 | 3.2316 | 7.5791 | 5.4633 | 16.8181 | 18.9339 | 26.513 | 31.9762 | 8.3263 | 8.5019 | 2.0772 | 2.1158 | 3.386 | 3.2316 | 7.5791 | 5.4633 | 16.8281 | 18.9439 | 26.523 | 31.9862 | 0.01
-4.5469 | 5.7148 | 1.6484 | 1.4727 | 1.2422 | 1.9453 | 4.3633 | 2.8906 | 1.1679 | 2.6406 | 7.0038 | 9.8944 | -4.5369 | 5.7148 | 1.6484 | 1.4727 | 1.2422 | 1.9453 | 4.3633 | 2.8906 | 1.1779 | 2.6506 | 7.0138 | 9.9044 | 0.01
-7.9943 | 4.9679 | 1.5335 | 1.3003 | 0.66762 | 1.6006 | 3.5014 | 2.2011 | -3.0264 | -1.7261 | 1.7753 | 3.9765 | -7.9843 | 4.9679 | 1.5335 | 1.3003 | 0.66762 | 1.6006 | 3.5014 | 2.2011 | -3.0164 | -1.7161 | 1.7853 | 3.9865 | 0.01
4.1948 | 7.6089 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5487 | 4.639 | 11.8036 | 13.7134 | 20.2621 | 24.901 | 4.2048 | 7.6089 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5487 | 4.639 | 11.8136 | 13.7234 | 20.2721 | 24.911 | 0.01
0.29908 | 6.7648 | 1.81 | 1.715 | 2.0498 | 2.4299 | 5.5748 | 3.8598 | 7.0639 | 8.7788 | 14.3536 | 18.2134 | 0.30908 | 6.7648 | 1.81 | 1.715 | 2.0498 | 2.4299 | 5.5748 | 3.8598 | 7.0739 | 8.7888 | 14.3636 | 18.2234 | 0.01
2.5167 | 7.2453 | 1.8839 | 1.8258 | 2.4194 | 2.6517 | 6.1292 | 4.3033 | 9.762 | 11.5878 | 17.717 | 22.0203 | 2.5267 | 7.2453 | 1.8839 | 1.8258 | 2.4194 | 2.6517 | 6.1292 | 4.3033 | 9.772 | 11.5978 | 17.727 | 22.0303 | 0.01
14.5896 | 9.8611 | 2.2863 | 2.4295 | 4.4316 | 3.859 | 9.1474 | 6.7179 | 24.4507 | 26.8802 | 36.0276 | 42.7455 | 14.5996 | 9.8611 | 2.2863 | 2.4295 | 4.4316 | 3.859 | 9.1474 | 6.7179 | 24.4607 | 26.8902 | 36.0376 | 42.7555 | 0.01
5.9257 | 7.9839 | 1.9975 | 1.9963 | 2.9876 | 2.9926 | 6.9814 | 4.9851 | 13.9095 | 15.9058 | 22.8872 | 27.8724 | 5.9357 | 7.9839 | 1.9975 | 1.9963 | 2.9876 | 2.9926 | 6.9814 | 4.9851 | 13.9195 | 15.9158 | 22.8972 | 27.8824 | 0.01
4.8036 | 7.7408 | 1.9601 | 1.9402 | 2.8006 | 2.8804 | 6.7009 | 4.7607 | 12.5443 | 14.4845 | 21.1854 | 25.9461 | 4.8136 | 7.7408 | 1.9601 | 1.9402 | 2.8006 | 2.8804 | 6.7009 | 4.7607 | 12.5543 | 14.4945 | 21.1954 | 25.9561 | 0.01
2.8171 | 7.3104 | 1.8939 | 1.8409 | 2.4695 | 2.6817 | 6.2043 | 4.3634 | 10.1275 | 11.9683 | 18.1726 | 22.536 | 2.8271 | 7.3104 | 1.8939 | 1.8409 | 2.4695 | 2.6817 | 6.2043 | 4.3634 | 10.1375 | 11.9783 | 18.1826 | 22.546 | 0.01
7.7332 | 8.3755 | 2.0578 | 2.0867 | 3.2889 | 3.1733 | 7.4333 | 5.3466 | 16.1088 | 18.1954 | 25.6287 | 30.9754 | 7.7432 | 8.3755 | 2.0578 | 2.0867 | 3.2889 | 3.1733 | 7.4333 | 5.3466 | 16.1188 | 18.2054 | 25.6387 | 30.9854 | 0.01
10.7305 | 9.0249 | 2.1577 | 2.2365 | 3.7884 | 3.473 | 8.1826 | 5.9461 | 19.7554 | 21.9919 | 30.1745 | 36.1206 | 10.7405 | 9.0249 | 2.1577 | 2.2365 | 3.7884 | 3.473 | 8.1826 | 5.9461 | 19.7654 | 22.0019 | 30.1845 | 36.1306 | 0.01
8.4966 | 8.5409 | 2.0832 | 2.1248 | 3.4161 | 3.2497 | 7.6242 | 5.4993 | 17.0375 | 19.1624 | 26.7865 | 32.2858 | 8.5066 | 8.5409 | 2.0832 | 2.1248 | 3.4161 | 3.2497 | 7.6242 | 5.4993 | 17.0475 | 19.1724 | 26.7965 | 32.2958 | 0.01
-8.2772 | 4.9066 | 1.5241 | 1.2861 | 0.62047 | 1.5723 | 3.4307 | 2.1446 | -3.3706 | -2.0844 | 1.3463 | 3.4908 | -8.2672 | 4.9066 | 1.5241 | 1.2861 | 0.62047 | 1.5723 | 3.4307 | 2.1446 | -3.3606 | -2.0744 | 1.3563 | 3.5008 | 0.01
8.6945 | 8.5838 | 2.0898 | 2.1347 | 3.4491 | 3.2695 | 7.6736 | 5.5389 | 17.2783 | 19.413 | 27.0867 | 32.6256 | 8.7045 | 8.5838 | 2.0898 | 2.1347 | 3.4491 | 3.2695 | 7.6736 | 5.5389 | 17.2883 | 19.423 | 27.0967 | 32.6356 | 0.01
4.4416 | 7.6624 | 1.9481 | 1.9221 | 2.7403 | 2.8442 | 6.6104 | 4.6883 | 12.104 | 14.0261 | 20.6365 | 25.3248 | 4.4516 | 7.6624 | 1.9481 | 1.9221 | 2.7403 | 2.8442 | 6.6104 | 4.6883 | 12.114 | 14.0361 | 20.6465 | 25.3348 | 0.01
4.5166 | 7.6786 | 1.9506 | 1.9258 | 2.7528 | 2.8517 | 6.6292 | 4.7033 | 12.1953 | 14.1211 | 20.7502 | 25.4536 | 4.5266 | 7.6786 | 1.9506 | 1.9258 | 2.7528 | 2.8517 | 6.6292 | 4.7033 | 12.2053 | 14.1311 | 20.7602 | 25.4636 | 0.01
7.1372 | 8.2464 | 2.0379 | 2.0569 | 3.1895 | 3.1137 | 7.2843 | 5.2274 | 15.3835 | 17.4404 | 24.7247 | 29.9521 | 7.1472 | 8.2464 | 2.0379 | 2.0569 | 3.1895 | 3.1137 | 7.2843 | 5.2274 | 15.3935 | 17.4504 | 24.7347 | 29.9621 | 0.01
9.3226 | 8.7199 | 2.1108 | 2.1661 | 3.5538 | 3.3323 | 7.8307 | 5.6645 | 18.0425 | 20.2087 | 28.0393 | 33.7039 | 9.3326 | 8.7199 | 2.1108 | 2.1661 | 3.5538 | 3.3323 | 7.8307 | 5.6645 | 18.0525 | 20.2187 | 28.0493 | 33.7139 | 0.01
1.1275 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7819 | 4.0255 | 8.0717 | 9.8281 | 15.61 | 19.6355 | 1.1375 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7819 | 4.0255 | 8.0817 | 9.8381 | 15.62 | 19.6455 | 0.01
-2.6418 | 6.1276 | 1.7119 | 1.5679 | 1.5597 | 2.1358 | 4.8395 | 3.2716 | 3.4858 | 5.0537 | 9.8932 | 13.1649 | -2.6318 | 6.1276 | 1.7119 | 1.5679 | 1.5597 | 2.1358 | 4.8395 | 3.2716 | 3.4958 | 5.0637 | 9.9032 | 13.1749 | 0.01
9.0604 | 8.6631 | 2.102 | 2.153 | 3.5101 | 3.306 | 7.7651 | 5.6121 | 17.7234 | 19.8765 | 27.6415 | 33.2536 | 9.0704 | 8.6631 | 2.102 | 2.153 | 3.5101 | 3.306 | 7.7651 | 5.6121 | 17.7334 | 19.8865 | 27.6515 | 33.2636 | 0.01
10.6866 | 9.0154 | 2.1562 | 2.2343 | 3.7811 | 3.4687 | 8.1717 | 5.9373 | 19.7021 | 21.9364 | 30.1081 | 36.0454 | 10.6966 | 9.0154 | 2.1562 | 2.2343 | 3.7811 | 3.4687 | 8.1717 | 5.9373 | 19.7121 | 21.9464 | 30.1181 | 36.0554 | 0.01
8.5379 | 8.5499 | 2.0846 | 2.1269 | 3.423 | 3.2538 | 7.6345 | 5.5076 | 17.0878 | 19.2146 | 26.8491 | 32.3567 | 8.5479 | 8.5499 | 2.0846 | 2.1269 | 3.423 | 3.2538 | 7.6345 | 5.5076 | 17.0978 | 19.2246 | 26.8591 | 32.3667 | 0.01
1.8028 | 7.0906 | 1.8601 | 1.7901 | 2.3005 | 2.5803 | 5.9507 | 4.1606 | 8.8935 | 10.6836 | 16.6343 | 20.7949 | 1.8128 | 7.0906 | 1.8601 | 1.7901 | 2.3005 | 2.5803 | 5.9507 | 4.1606 | 8.9035 | 10.6936 | 16.6443 | 20.8049 | 0.01
0.2989 | 6.7648 | 1.81 | 1.7149 | 2.0498 | 2.4299 | 5.5747 | 3.8598 | 7.0637 | 8.7786 | 14.3533 | 18.2131 | 0.3089 | 6.7648 | 1.81 | 1.7149 | 2.0498 | 2.4299 | 5.5747 | 3.8598 | 7.0737 | 8.7886 | 14.3633 | 18.2231 | 0.01
-0.13421 | 6.6709 | 1.7955 | 1.6933 | 1.9776 | 2.3866 | 5.4664 | 3.7732 | 6.5367 | 8.23 | 13.6965 | 17.4696 | -0.12421 | 6.6709 | 1.7955 | 1.6933 | 1.9776 | 2.3866 | 5.4664 | 3.7732 | 6.5467 | 8.24 | 13.7065 | 17.4796 | 0.01
7.0264 | 8.2224 | 2.0342 | 2.0513 | 3.1711 | 3.1026 | 7.2566 | 5.2053 | 15.2488 | 17.3001 | 24.5567 | 29.762 | 7.0364 | 8.2224 | 2.0342 | 2.0513 | 3.1711 | 3.1026 | 7.2566 | 5.2053 | 15.2588 | 17.3101 | 24.5667 | 29.772 | 0.01
15.9381 | 10.1533 | 2.3313 | 2.4969 | 4.6563 | 3.9938 | 9.4845 | 6.9876 | 26.0913 | 28.5883 | 38.0728 | 45.0604 | 15.9481 | 10.1533 | 2.3313 | 2.4969 | 4.6563 | 3.9938 | 9.4845 | 6.9876 | 26.1013 | 28.5983 | 38.0828 | 45.0704 | 0.01
4.2657 | 7.6242 | 1.9422 | 1.9133 | 2.711 | 2.8266 | 6.5664 | 4.6531 | 11.89 | 13.8033 | 20.3697 | 25.0229 | 4.2757 | 7.6242 | 1.9422 | 1.9133 | 2.711 | 2.8266 | 6.5664 | 4.6531 | 11.9 | 13.8133 | 20.3797 | 25.0329 | 0.01
-1.1135 | 6.4587 | 1.7629 | 1.6443 | 1.8144 | 2.2886 | 5.2216 | 3.5773 | 5.3452 | 6.9896 | 12.2112 | 15.7885 | -1.1035 | 6.4587 | 1.7629 | 1.6443 | 1.8144 | 2.2886 | 5.2216 | 3.5773 | 5.3552 | 6.9996 | 12.2212 | 15.7985 | 0.01
4.8713 | 7.7554 | 1.9624 | 1.9436 | 2.8119 | 2.8871 | 6.7178 | 4.7743 | 12.6267 | 14.5703 | 21.2881 | 26.0624 | 4.8813 | 7.7554 | 1.9624 | 1.9436 | 2.8119 | 2.8871 | 6.7178 | 4.7743 | 12.6367 | 14.5803 | 21.2981 | 26.0724 | 0.01
7.0446 | 8.2263 | 2.0348 | 2.0522 | 3.1741 | 3.1045 | 7.2612 | 5.2089 | 15.2709 | 17.3232 | 24.5843 | 29.7933 | 7.0546 | 8.2263 | 2.0348 | 2.0522 | 3.1741 | 3.1045 | 7.2612 | 5.2089 | 15.2809 | 17.3332 | 24.5943 | 29.8033 | 0.01
20.3696 | 11.1134 | 2.479 | 2.7185 | 5.3949 | 4.437 | 10.5924 | 7.8739 | 31.483 | 34.2015 | 44.7939 | 52.6678 | 20.3796 | 11.1134 | 2.479 | 2.7185 | 5.3949 | 4.437 | 10.5924 | 7.8739 | 31.493 | 34.2115 | 44.8039 | 52.6778 | 0.01
2.9926 | 7.3484 | 1.8998 | 1.8496 | 2.4988 | 2.6993 | 6.2482 | 4.3985 | 10.341 | 12.1907 | 18.4388 | 22.8374 | 3.0026 | 7.3484 | 1.8998 | 1.8496 | 2.4988 | 2.6993 | 6.2482 | 4.3985 | 10.351 | 12.2007 | 18.4488 | 22.8474 | 0.01
3.3625 | 7.4285 | 1.9121 | 1.8681 | 2.5604 | 2.7362 | 6.3406 | 4.4725 | 10.791 | 12.6591 | 18.9998 | 23.4723 | 3.3725 | 7.4285 | 1.9121 | 1.8681 | 2.5604 | 2.7362 | 6.3406 | 4.4725 | 10.801 | 12.6691 | 19.0098 | 23.4823 | 0.01
2.8398 | 7.3153 | 1.8947 | 1.842 | 2.4733 | 2.684 | 6.21 | 4.368 | 10.1551 | 11.9971 | 18.207 | 22.575 | 2.8498 | 7.3153 | 1.8947 | 1.842 | 2.4733 | 2.684 | 6.21 | 4.368 | 10.1651 | 12.0071 | 18.217 | 22.585 | 0.01
8.605 | 8.5644 | 2.0868 | 2.1302 | 3.4342 | 3.2605 | 7.6512 | 5.521 | 17.1694 | 19.2996 | 26.9509 | 32.4719 | 8.615 | 8.5644 | 2.0868 | 2.1302 | 3.4342 | 3.2605 | 7.6512 | 5.521 | 17.1794 | 19.3096 | 26.9609 | 32.4819 | 0.01
8.192 | 8.4749 | 2.0731 | 2.1096 | 3.3653 | 3.2192 | 7.548 | 5.4384 | 16.6669 | 18.7765 | 26.3245 | 31.7629 | 8.202 | 8.4749 | 2.0731 | 2.1096 | 3.3653 | 3.2192 | 7.548 | 5.4384 | 16.6769 | 18.7865 | 26.3345 | 31.7729 | 0.01
8.0575 | 8.4458 | 2.0686 | 2.1029 | 3.3429 | 3.2057 | 7.5144 | 5.4115 | 16.5033 | 18.6062 | 26.1205 | 31.532 | 8.0675 | 8.4458 | 2.0686 | 2.1029 | 3.3429 | 3.2057 | 7.5144 | 5.4115 | 16.5133 | 18.6162 | 26.1305 | 31.542 | 0.01
5.6798 | 7.9306 | 1.9893 | 1.984 | 2.9466 | 2.968 | 6.92 | 4.936 | 13.6104 | 15.5944 | 22.5144 | 27.4503 | 5.6898 | 7.9306 | 1.9893 | 1.984 | 2.9466 | 2.968 | 6.92 | 4.936 | 13.6204 | 15.6044 | 22.5244 | 27.4603 | 0.01
12.1633 | 9.3354 | 2.2054 | 2.3082 | 4.0272 | 3.6163 | 8.5408 | 6.2327 | 21.4987 | 23.8069 | 32.3477 | 38.5804 | 12.1733 | 9.3354 | 2.2054 | 2.3082 | 4.0272 | 3.6163 | 8.5408 | 6.2327 | 21.5087 | 23.8169 | 32.3577 | 38.5904 | 0.01
8.89 | 8.6262 | 2.0963 | 2.1445 | 3.4817 | 3.289 | 7.7225 | 5.578 | 17.5161 | 19.6606 | 27.3831 | 32.9611 | 8.9 | 8.6262 | 2.0963 | 2.1445 | 3.4817 | 3.289 | 7.7225 | 5.578 | 17.5261 | 19.6706 | 27.3931 | 32.9711 | 0.01
4.5152 | 7.6783 | 1.9505 | 1.9258 | 2.7525 | 2.8515 | 6.6288 | 4.703 | 12.1935 | 14.1192 | 20.748 | 25.451 | 4.5252 | 7.6783 | 1.9505 | 1.9258 | 2.7525 | 2.8515 | 6.6288 | 4.703 | 12.2035 | 14.1292 | 20.758 | 25.461 | 0.01
17.5746 | 10.5078 | 2.3858 | 2.5787 | 4.9291 | 4.1575 | 9.8937 | 7.3149 | 28.0824 | 30.6612 | 40.5548 | 47.8697 | 17.5846 | 10.5078 | 2.3858 | 2.5787 | 4.9291 | 4.1575 | 9.8937 | 7.3149 | 28.0924 | 30.6712 | 40.5648 | 47.8797 | 0.01
7.2511 | 8.2711 | 2.0417 | 2.0626 | 3.2085 | 3.1251 | 7.3128 | 5.2502 | 15.5222 | 17.5848 | 24.8976 | 30.1478 | 7.2611 | 8.2711 | 2.0417 | 2.0626 | 3.2085 | 3.1251 | 7.3128 | 5.2502 | 15.5322 | 17.5948 | 24.9076 | 30.1578 | 0.01
7.1645 | 8.2523 | 2.0388 | 2.0582 | 3.1941 | 3.1164 | 7.2911 | 5.2329 | 15.4168 | 17.475 | 24.7661 | 29.999 | 7.1745 | 8.2523 | 2.0388 | 2.0582 | 3.1941 | 3.1164 | 7.2911 | 5.2329 | 15.4268 | 17.485 | 24.7761 | 30.009 | 0.01
8.9096 | 8.6304 | 2.097 | 2.1455 | 3.4849 | 3.291 | 7.7274 | 5.5819 | 17.54 | 19.6855 | 27.4129 | 32.9948 | 8.9196 | 8.6304 | 2.097 | 2.1455 | 3.4849 | 3.291 | 7.7274 | 5.5819 | 17.55 | 19.6955 | 27.4229 | 33.0048 | 0.01
13.8753 | 9.7063 | 2.2625 | 2.3938 | 4.3126 | 3.7875 | 8.9688 | 6.5751 | 23.5816 | 25.9754 | 34.9442 | 41.5193 | 13.8853 | 9.7063 | 2.2625 | 2.3938 | 4.3126 | 3.7875 | 8.9688 | 6.5751 | 23.5916 | 25.9854 | 34.9542 | 41.5293 | 0.01
14.9444 | 9.938 | 2.2981 | 2.4472 | 4.4907 | 3.8944 | 9.2361 | 6.7889 | 24.8824 | 27.3296 | 36.5657 | 43.3546 | 14.9544 | 9.938 | 2.2981 | 2.4472 | 4.4907 | 3.8944 | 9.2361 | 6.7889 | 24.8924 | 27.3396 | 36.5757 | 43.3646 | 0.01
12.6497 | 9.4408 | 2.2217 | 2.3325 | 4.1083 | 3.665 | 8.6624 | 6.3299 | 22.0904 | 24.4229 | 33.0853 | 39.4153 | 12.6597 | 9.4408 | 2.2217 | 2.3325 | 4.1083 | 3.665 | 8.6624 | 6.3299 | 22.1004 | 24.4329 | 33.0953 | 39.4253 | 0.01
-5.3839 | 5.5335 | 1.6205 | 1.4308 | 1.1027 | 1.8616 | 4.154 | 2.7232 | 0.14953 | 1.5803 | 5.7343 | 8.4576 | -5.3739 | 5.5335 | 1.6205 | 1.4308 | 1.1027 | 1.8616 | 4.154 | 2.7232 | 0.15953 | 1.5903 | 5.7443 | 8.4676 | 0.01
7.415 | 8.3066 | 2.0472 | 2.0707 | 3.2358 | 3.1415 | 7.3537 | 5.283 | 15.7215 | 17.7923 | 25.146 | 30.429 | 7.425 | 8.3066 | 2.0472 | 2.0707 | 3.2358 | 3.1415 | 7.3537 | 5.283 | 15.7315 | 17.8023 | 25.156 | 30.439 | 0.01
0.75401 | 6.8634 | 1.8251 | 1.7377 | 2.1257 | 2.4754 | 5.6885 | 3.9508 | 7.6174 | 9.3551 | 15.0436 | 18.9944 | 0.76401 | 6.8634 | 1.8251 | 1.7377 | 2.1257 | 2.4754 | 5.6885 | 3.9508 | 7.6274 | 9.3651 | 15.0536 | 19.0044 | 0.01
7.6785 | 8.3637 | 2.0559 | 2.0839 | 3.2797 | 3.1678 | 7.4196 | 5.3357 | 16.0421 | 18.1261 | 25.5457 | 30.8814 | 7.6885 | 8.3637 | 2.0559 | 2.0839 | 3.2797 | 3.1678 | 7.4196 | 5.3357 | 16.0521 | 18.1361 | 25.5557 | 30.8914 | 0.01
-6.7356 | 5.2406 | 1.5755 | 1.3632 | 0.8774 | 1.7264 | 3.8161 | 2.4529 | -1.495 | -0.13174 | 3.6844 | 6.1373 | -6.7256 | 5.2406 | 1.5755 | 1.3632 | 0.8774 | 1.7264 | 3.8161 | 2.4529 | -1.485 | -0.12174 | 3.6944 | 6.1473 | 0.01
15.0729 | 9.9658 | 2.3024 | 2.4536 | 4.5121 | 3.9073 | 9.2682 | 6.8146 | 25.0387 | 27.4923 | 36.7606 | 43.5751 | 15.0829 | 9.9658 | 2.3024 | 2.4536 | 4.5121 | 3.9073 | 9.2682 | 6.8146 | 25.0487 | 27.5023 | 36.7706 | 43.5851 | 0.01
4.1628 | 7.6019 | 1.9388 | 1.9081 | 2.6938 | 2.8163 | 6.5407 | 4.6326 | 11.7648 | 13.6729 | 20.2136 | 24.8462 | 4.1728 | 7.6019 | 1.9388 | 1.9081 | 2.6938 | 2.8163 | 6.5407 | 4.6326 | 11.7748 | 13.6829 | 20.2236 | 24.8562 | 0.01
-1.8279 | 6.304 | 1.7391 | 1.6086 | 1.6954 | 2.2172 | 5.043 | 3.4344 | 4.4761 | 6.0847 | 11.1277 | 14.5622 | -1.8179 | 6.304 | 1.7391 | 1.6086 | 1.6954 | 2.2172 | 5.043 | 3.4344 | 4.4861 | 6.0947 | 11.1377 | 14.5722 | 0.01
7.3349 | 8.2892 | 2.0445 | 2.0667 | 3.2225 | 3.1335 | 7.3337 | 5.267 | 15.6242 | 17.6909 | 25.0246 | 30.2916 | 7.3449 | 8.2892 | 2.0445 | 2.0667 | 3.2225 | 3.1335 | 7.3337 | 5.267 | 15.6342 | 17.7009 | 25.0346 | 30.3016 | 0.01
-2.9217 | 6.067 | 1.7026 | 1.5539 | 1.5131 | 2.1078 | 4.7696 | 3.2157 | 3.1453 | 4.6992 | 9.4688 | 12.6845 | -2.9117 | 6.067 | 1.7026 | 1.5539 | 1.5131 | 2.1078 | 4.7696 | 3.2157 | 3.1553 | 4.7092 | 9.4788 | 12.6945 | 0.01
6.4196 | 8.0909 | 2.014 | 2.021 | 3.0699 | 3.042 | 7.1049 | 5.0839 | 14.5106 | 16.5315 | 23.6364 | 28.7204 | 6.4296 | 8.0909 | 2.014 | 2.021 | 3.0699 | 3.042 | 7.1049 | 5.0839 | 14.5206 | 16.5415 | 23.6464 | 28.7304 | 0.01
-3.1568 | 6.016 | 1.6948 | 1.5422 | 1.4739 | 2.0843 | 4.7108 | 3.1686 | 2.8592 | 4.4013 | 9.1121 | 12.2807 | -3.1468 | 6.016 | 1.6948 | 1.5422 | 1.4739 | 2.0843 | 4.7108 | 3.1686 | 2.8692 | 4.4113 | 9.1221 | 12.2907 | 0.01
-5.5235 | 5.5032 | 1.6159 | 1.4238 | 1.0794 | 1.8476 | 4.1191 | 2.6953 | -0.0203 | 1.4035 | 5.5226 | 8.2179 | -5.5135 | 5.5032 | 1.6159 | 1.4238 | 1.0794 | 1.8476 | 4.1191 | 2.6953 | -0.0103 | 1.4135 | 5.5326 | 8.2279 | 0.01
4.1099 | 7.5905 | 1.937 | 1.9055 | 2.685 | 2.811 | 6.5275 | 4.622 | 11.7004 | 13.6058 | 20.1333 | 24.7553 | 4.1199 | 7.5905 | 1.937 | 1.9055 | 2.685 | 2.811 | 6.5275 | 4.622 | 11.7104 | 13.6158 | 20.1433 | 24.7653 | 0.01
9.1846 | 8.69 | 2.1062 | 2.1592 | 3.5308 | 3.3185 | 7.7962 | 5.6369 | 17.8746 | 20.0339 | 27.83 | 33.4669 | 9.1946 | 8.69 | 2.1062 | 2.1592 | 3.5308 | 3.3185 | 7.7962 | 5.6369 | 17.8846 | 20.0439 | 27.84 | 33.4769 | 0.01
-3.3156 | 5.9816 | 1.6895 | 1.5342 | 1.4474 | 2.0684 | 4.6711 | 3.1369 | 2.666 | 4.2003 | 8.8714 | 12.0082 | -3.3056 | 5.9816 | 1.6895 | 1.5342 | 1.4474 | 2.0684 | 4.6711 | 3.1369 | 2.676 | 4.2103 | 8.8814 | 12.0182 | 0.01
10.6419 | 9.0057 | 2.1547 | 2.2321 | 3.7737 | 3.4642 | 8.1605 | 5.9284 | 19.6477 | 21.8798 | 30.0402 | 35.9686 | 10.6519 | 9.0057 | 2.1547 | 2.2321 | 3.7737 | 3.4642 | 8.1605 | 5.9284 | 19.6577 | 21.8898 | 30.0502 | 35.9786 | 0.01
9.4293 | 8.743 | 2.1143 | 2.1715 | 3.5716 | 3.3429 | 7.8573 | 5.6859 | 18.1724 | 20.3438 | 28.2012 | 33.8871 | 9.4393 | 8.743 | 2.1143 | 2.1715 | 3.5716 | 3.3429 | 7.8573 | 5.6859 | 18.1824 | 20.3538 | 28.2112 | 33.8971 | 0.01
24.2891 | 11.9626 | 2.6096 | 2.9145 | 6.0482 | 4.8289 | 11.5723 | 8.6578 | 36.2518 | 39.1662 | 50.7385 | 59.3964 | 24.2991 | 11.9626 | 2.6096 | 2.9145 | 6.0482 | 4.8289 | 11.5723 | 8.6578 | 36.2618 | 39.1762 | 50.7485 | 59.4064 | 0.01
8.2951 | 8.4973 | 2.0765 | 2.1148 | 3.3825 | 3.2295 | 7.5738 | 5.459 | 16.7923 | 18.9071 | 26.4808 | 31.9398 | 8.3051 | 8.4973 | 2.0765 | 2.1148 | 3.3825 | 3.2295 | 7.5738 | 5.459 | 16.8023 | 18.9171 | 26.4908 | 31.9498 | 0.01
-5.1847 | 5.5767 | 1.6272 | 1.4408 | 1.1359 | 1.8815 | 4.2038 | 2.7631 | 0.392 | 1.8328 | 6.0366 | 8.7997 | -5.1747 | 5.5767 | 1.6272 | 1.4408 | 1.1359 | 1.8815 | 4.2038 | 2.7631 | 0.402 | 1.8428 | 6.0466 | 8.8097 | 0.01
7.4308 | 8.31 | 2.0477 | 2.0715 | 3.2385 | 3.1431 | 7.3577 | 5.2862 | 15.7408 | 17.8123 | 25.17 | 30.4562 | 7.4408 | 8.31 | 2.0477 | 2.0715 | 3.2385 | 3.1431 | 7.3577 | 5.2862 | 15.7508 | 17.8223 | 25.18 | 30.4662 | 0.01
3.9805 | 7.5624 | 1.9327 | 1.899 | 2.6634 | 2.798 | 6.4951 | 4.5961 | 11.5429 | 13.4419 | 19.937 | 24.5331 | 3.9905 | 7.5624 | 1.9327 | 1.899 | 2.6634 | 2.798 | 6.4951 | 4.5961 | 11.5529 | 13.4519 | 19.947 | 24.5431 | 0.01
6.9627 | 8.2086 | 2.0321 | 2.0481 | 3.1605 | 3.0963 | 7.2407 | 5.1925 | 15.1713 | 17.2195 | 24.4602 | 29.6527 | 6.9727 | 8.2086 | 2.0321 | 2.0481 | 3.1605 | 3.0963 | 7.2407 | 5.1925 | 15.1813 | 17.2295 | 24.4702 | 29.6627 | 0.01
10.5847 | 8.9933 | 2.1528 | 2.2292 | 3.7641 | 3.4585 | 8.1462 | 5.9169 | 19.578 | 21.8073 | 29.9534 | 35.8704 | 10.5947 | 8.9933 | 2.1528 | 2.2292 | 3.7641 | 3.4585 | 8.1462 | 5.9169 | 19.588 | 21.8173 | 29.9634 | 35.8804 | 0.01
-1.1576 | 6.4492 | 1.7614 | 1.6421 | 1.8071 | 2.2842 | 5.2106 | 3.5685 | 5.2915 | 6.9337 | 12.1443 | 15.7127 | -1.1476 | 6.4492 | 1.7614 | 1.6421 | 1.8071 | 2.2842 | 5.2106 | 3.5685 | 5.3015 | 6.9437 | 12.1543 | 15.7227 | 0.01
-1.1256 | 6.4561 | 1.7625 | 1.6437 | 1.8124 | 2.2874 | 5.2186 | 3.5749 | 5.3305 | 6.9742 | 12.1928 | 15.7677 | -1.1156 | 6.4561 | 1.7625 | 1.6437 | 1.8124 | 2.2874 | 5.2186 | 3.5749 | 5.3405 | 6.9842 | 12.2028 | 15.7777 | 0.01
10.0004 | 8.8667 | 2.1333 | 2.2 | 3.6667 | 3.4 | 8.0001 | 5.8001 | 18.8671 | 21.0671 | 29.0672 | 34.8673 | 10.0104 | 8.8667 | 2.1333 | 2.2 | 3.6667 | 3.4 | 8.0001 | 5.8001 | 18.8771 | 21.0771 | 29.0772 | 34.8773 | 0.01
8.9462 | 8.6383 | 2.0982 | 2.1473 | 3.491 | 3.2946 | 7.7366 | 5.5892 | 17.5845 | 19.7319 | 27.4684 | 33.0576 | 8.9562 | 8.6383 | 2.0982 | 2.1473 | 3.491 | 3.2946 | 7.7366 | 5.5892 | 17.5945 | 19.7419 | 27.4784 | 33.0676 | 0.01
1.749 | 7.0789 | 1.8583 | 1.7874 | 2.2915 | 2.5749 | 5.9372 | 4.1498 | 8.8279 | 10.6153 | 16.5526 | 20.7024 | 1.759 | 7.0789 | 1.8583 | 1.7874 | 2.2915 | 2.5749 | 5.9372 | 4.1498 | 8.8379 | 10.6253 | 16.5626 | 20.7124 | 0.01
0.17321 | 6.7375 | 1.8058 | 1.7087 | 2.0289 | 2.4173 | 5.5433 | 3.8346 | 6.9107 | 8.6194 | 14.1627 | 17.9973 | 0.18321 | 6.7375 | 1.8058 | 1.7087 | 2.0289 | 2.4173 | 5.5433 | 3.8346 | 6.9207 | 8.6294 | 14.1727 | 18.0073 | 0.01
7.8213 | 8.3946 | 2.0607 | 2.0911 | 3.3035 | 3.1821 | 7.4553 | 5.3643 | 16.2159 | 18.3069 | 25.7622 | 31.1265 | 7.8313 | 8.3946 | 2.0607 | 2.0911 | 3.3035 | 3.1821 | 7.4553 | 5.3643 | 16.2259 | 18.3169 | 25.7722 | 31.1365 | 0.01
15.1106 | 9.974 | 2.3037 | 2.4555 | 4.5184 | 3.9111 | 9.2777 | 6.8221 | 25.0846 | 27.5401 | 36.8178 | 43.6399 | 15.1206 | 9.974 | 2.3037 | 2.4555 | 4.5184 | 3.9111 | 9.2777 | 6.8221 | 25.0946 | 27.5501 | 36.8278 | 43.6499 | 0.01
10.1426 | 8.8976 | 2.1381 | 2.2071 | 3.6904 | 3.4143 | 8.0357 | 5.8285 | 19.0402 | 21.2473 | 29.283 | 35.1115 | 10.1526 | 8.8976 | 2.1381 | 2.2071 | 3.6904 | 3.4143 | 8.0357 | 5.8285 | 19.0502 | 21.2573 | 29.293 | 35.1215 | 0.01
16.8847 | 10.3583 | 2.3628 | 2.5442 | 4.8141 | 4.0885 | 9.7212 | 7.1769 | 27.243 | 29.7873 | 39.5084 | 46.6854 | 16.8947 | 10.3583 | 2.3628 | 2.5442 | 4.8141 | 4.0885 | 9.7212 | 7.1769 | 27.253 | 29.7973 | 39.5184 | 46.6954 | 0.01
7.7903 | 8.3879 | 2.0597 | 2.0895 | 3.2984 | 3.179 | 7.4476 | 5.3581 | 16.1782 | 18.2677 | 25.7153 | 31.0734 | 7.8003 | 8.3879 | 2.0597 | 2.0895 | 3.2984 | 3.179 | 7.4476 | 5.3581 | 16.1882 | 18.2777 | 25.7253 | 31.0834 | 0.01
13.5503 | 9.6359 | 2.2517 | 2.3775 | 4.2584 | 3.755 | 8.8876 | 6.5101 | 23.1862 | 25.5637 | 34.4513 | 40.9613 | 13.5603 | 9.6359 | 2.2517 | 2.3775 | 4.2584 | 3.755 | 8.8876 | 6.5101 | 23.1962 | 25.5737 | 34.4613 | 40.9713 | 0.01
15.0013 | 9.9503 | 2.3 | 2.4501 | 4.5002 | 3.9001 | 9.2503 | 6.8003 | 24.9515 | 27.4016 | 36.6519 | 43.4522 | 15.0113 | 9.9503 | 2.3 | 2.4501 | 4.5002 | 3.9001 | 9.2503 | 6.8003 | 24.9615 | 27.4116 | 36.6619 | 43.4622 | 0.01
7.9384 | 8.42 | 2.0646 | 2.0969 | 3.3231 | 3.1938 | 7.4846 | 5.3877 | 16.3584 | 18.4553 | 25.9399 | 31.3276 | 7.9484 | 8.42 | 2.0646 | 2.0969 | 3.3231 | 3.1938 | 7.4846 | 5.3877 | 16.3684 | 18.4653 | 25.9499 | 31.3376 | 0.01
6.8871 | 8.1922 | 2.0296 | 2.0444 | 3.1479 | 3.0887 | 7.2218 | 5.1774 | 15.0793 | 17.1237 | 24.3455 | 29.5229 | 6.8971 | 8.1922 | 2.0296 | 2.0444 | 3.1479 | 3.0887 | 7.2218 | 5.1774 | 15.0893 | 17.1337 | 24.3555 | 29.5329 | 0.01
1.9661 | 7.126 | 1.8655 | 1.7983 | 2.3277 | 2.5966 | 5.9915 | 4.1932 | 9.0921 | 10.8904 | 16.8819 | 21.0751 | 1.9761 | 7.126 | 1.8655 | 1.7983 | 2.3277 | 2.5966 | 5.9915 | 4.1932 | 9.1021 | 10.9004 | 16.8919 | 21.0851 | 0.01
3.4524 | 7.448 | 1.9151 | 1.8726 | 2.5754 | 2.7452 | 6.3631 | 4.4905 | 10.9004 | 12.773 | 19.1361 | 23.6266 | 3.4624 | 7.448 | 1.9151 | 1.8726 | 2.5754 | 2.7452 | 6.3631 | 4.4905 | 10.9104 | 12.783 | 19.1461 | 23.6366 | 0.01
11.6679 | 9.228 | 2.1889 | 2.2834 | 3.9446 | 3.5668 | 8.417 | 6.1336 | 20.8959 | 23.1793 | 31.5963 | 37.7298 | 11.6779 | 9.228 | 2.1889 | 2.2834 | 3.9446 | 3.5668 | 8.417 | 6.1336 | 20.9059 | 23.1893 | 31.6063 | 37.7398 | 0.01
-0.70544 | 6.5472 | 1.7765 | 1.6647 | 1.8824 | 2.3295 | 5.3236 | 3.6589 | 5.8417 | 7.5064 | 12.8301 | 16.489 | -0.69544 | 6.5472 | 1.7765 | 1.6647 | 1.8824 | 2.3295 | 5.3236 | 3.6589 | 5.8517 | 7.5164 | 12.8401 | 16.499 | 0.01
4.6741 | 7.7127 | 1.9558 | 1.9337 | 2.779 | 2.8674 | 6.6685 | 4.7348 | 12.3868 | 14.3205 | 20.989 | 25.7238 | 4.6841 | 7.7127 | 1.9558 | 1.9337 | 2.779 | 2.8674 | 6.6685 | 4.7348 | 12.3968 | 14.3305 | 20.999 | 25.7338 | 0.01
10.26 | 8.923 | 2.142 | 2.213 | 3.71 | 3.426 | 8.065 | 5.852 | 19.183 | 21.396 | 29.461 | 35.313 | 10.27 | 8.923 | 2.142 | 2.213 | 3.71 | 3.426 | 8.065 | 5.852 | 19.193 | 21.406 | 29.471 | 35.323 | 0.01
7.416 | 8.3068 | 2.0472 | 2.0708 | 3.236 | 3.1416 | 7.354 | 5.2832 | 15.7228 | 17.7936 | 25.1476 | 30.4308 | 7.426 | 8.3068 | 2.0472 | 2.0708 | 3.236 | 3.1416 | 7.354 | 5.2832 | 15.7328 | 17.8036 | 25.1576 | 30.4408 | 0.01
2.6131 | 7.2662 | 1.8871 | 1.8307 | 2.4355 | 2.6613 | 6.1533 | 4.3226 | 9.8793 | 11.71 | 17.8633 | 22.1859 | 2.6231 | 7.2662 | 1.8871 | 1.8307 | 2.4355 | 2.6613 | 6.1533 | 4.3226 | 9.8893 | 11.72 | 17.8733 | 22.1959 | 0.01
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2044 | 14.1306 | 20.7616 | 25.4664 | 4.5341 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2144 | 14.1406 | 20.7716 | 25.4764 | 0.01
9.0177 | 8.6538 | 2.1006 | 2.1509 | 3.5029 | 3.3018 | 7.7544 | 5.6035 | 17.6715 | 19.8224 | 27.5768 | 33.1803 | 9.0277 | 8.6538 | 2.1006 | 2.1509 | 3.5029 | 3.3018 | 7.7544 | 5.6035 | 17.6815 | 19.8324 | 27.5868 | 33.1903 | 0.01
11.271 | 9.1421 | 2.1757 | 2.2636 | 3.8785 | 3.5271 | 8.3178 | 6.0542 | 20.4131 | 22.6766 | 30.9944 | 37.0486 | 11.281 | 9.1421 | 2.1757 | 2.2636 | 3.8785 | 3.5271 | 8.3178 | 6.0542 | 20.4231 | 22.6866 | 31.0044 | 37.0586 | 0.01
4.8689 | 7.7549 | 1.9623 | 1.9434 | 2.8115 | 2.8869 | 6.7172 | 4.7738 | 12.6238 | 14.5672 | 21.2844 | 26.0582 | 4.8789 | 7.7549 | 1.9623 | 1.9434 | 2.8115 | 2.8869 | 6.7172 | 4.7738 | 12.6338 | 14.5772 | 21.2944 | 26.0682 | 0.01
13.7381 | 9.6766 | 2.2579 | 2.3869 | 4.2897 | 3.7738 | 8.9345 | 6.5476 | 23.4147 | 25.8016 | 34.7361 | 41.2837 | 13.7481 | 9.6766 | 2.2579 | 2.3869 | 4.2897 | 3.7738 | 8.9345 | 6.5476 | 23.4247 | 25.8116 | 34.7461 | 41.2937 | 0.01
-0.14801 | 6.6679 | 1.7951 | 1.6926 | 1.9753 | 2.3852 | 5.463 | 3.7704 | 6.5199 | 8.2125 | 13.6755 | 17.4459 | -0.13801 | 6.6679 | 1.7951 | 1.6926 | 1.9753 | 2.3852 | 5.463 | 3.7704 | 6.5299 | 8.2225 | 13.6855 | 17.4559 | 0.01
4.9965 | 7.7826 | 1.9666 | 1.9498 | 2.8328 | 2.8997 | 6.7491 | 4.7993 | 12.7791 | 14.7289 | 21.478 | 26.2773 | 5.0065 | 7.7826 | 1.9666 | 1.9498 | 2.8328 | 2.8997 | 6.7491 | 4.7993 | 12.7891 | 14.7389 | 21.488 | 26.2873 | 0.01
2.9362 | 7.3362 | 1.8979 | 1.8468 | 2.4894 | 2.6936 | 6.234 | 4.3872 | 10.2723 | 12.1191 | 18.3532 | 22.7404 | 2.9462 | 7.3362 | 1.8979 | 1.8468 | 2.4894 | 2.6936 | 6.234 | 4.3872 | 10.2823 | 12.1291 | 18.3632 | 22.7504 | 0.01
10.8682 | 9.0548 | 2.1623 | 2.2434 | 3.8114 | 3.4868 | 8.2171 | 5.9736 | 19.923 | 22.1664 | 30.3835 | 36.3571 | 10.8782 | 9.0548 | 2.1623 | 2.2434 | 3.8114 | 3.4868 | 8.2171 | 5.9736 | 19.933 | 22.1764 | 30.3935 | 36.3671 | 0.01
5.3766 | 7.8649 | 1.9792 | 1.9688 | 2.8961 | 2.9377 | 6.8441 | 4.8753 | 13.2415 | 15.2103 | 22.0545 | 26.9298 | 5.3866 | 7.8649 | 1.9792 | 1.9688 | 2.8961 | 2.9377 | 6.8441 | 4.8753 | 13.2515 | 15.2203 | 22.0645 | 26.9398 | 0.01
-3.2425 | 5.9975 | 1.6919 | 1.5379 | 1.4596 | 2.0758 | 4.6894 | 3.1515 | 2.755 | 4.2928 | 8.9822 | 12.1337 | -3.2325 | 5.9975 | 1.6919 | 1.5379 | 1.4596 | 2.0758 | 4.6894 | 3.1515 | 2.765 | 4.3028 | 8.9922 | 12.1437 | 0.01
5.784 | 7.9532 | 1.9928 | 1.9892 | 2.964 | 2.9784 | 6.946 | 4.9568 | 13.7372 | 15.7264 | 22.6724 | 27.6292 | 5.794 | 7.9532 | 1.9928 | 1.9892 | 2.964 | 2.9784 | 6.946 | 4.9568 | 13.7472 | 15.7364 | 22.6824 | 27.6392 | 0.01
0.62392 | 6.8352 | 1.8208 | 1.7312 | 2.104 | 2.4624 | 5.656 | 3.9248 | 7.4591 | 9.1903 | 14.8463 | 18.7711 | 0.63392 | 6.8352 | 1.8208 | 1.7312 | 2.104 | 2.4624 | 5.656 | 3.9248 | 7.4691 | 9.2003 | 14.8563 | 18.7811 | 0.01
3.8817 | 7.541 | 1.9294 | 1.8941 | 2.6469 | 2.7882 | 6.4704 | 4.5763 | 11.4227 | 13.3168 | 19.7872 | 24.3636 | 3.8917 | 7.541 | 1.9294 | 1.8941 | 2.6469 | 2.7882 | 6.4704 | 4.5763 | 11.4327 | 13.3268 | 19.7972 | 24.3736 | 0.01
6.7592 | 8.1645 | 2.0253 | 2.038 | 3.1265 | 3.0759 | 7.1898 | 5.1518 | 14.9237 | 16.9617 | 24.1515 | 29.3033 | 6.7692 | 8.1645 | 2.0253 | 2.038 | 3.1265 | 3.0759 | 7.1898 | 5.1518 | 14.9337 | 16.9717 | 24.1615 | 29.3133 | 0.01
8.4274 | 8.5259 | 2.0809 | 2.1214 | 3.4046 | 3.2427 | 7.6069 | 5.4855 | 16.9534 | 19.0748 | 26.6816 | 32.1671 | 8.4374 | 8.5259 | 2.0809 | 2.1214 | 3.4046 | 3.2427 | 7.6069 | 5.4855 | 16.9634 | 19.0848 | 26.6916 | 32.1771 | 0.01
16.2512 | 10.2211 | 2.3417 | 2.5126 | 4.7085 | 4.0251 | 9.5628 | 7.0502 | 26.4722 | 28.9848 | 38.5476 | 45.5978 | 16.2612 | 10.2211 | 2.3417 | 2.5126 | 4.7085 | 4.0251 | 9.5628 | 7.0502 | 26.4822 | 28.9948 | 38.5576 | 45.6078 | 0.01
3.9702 | 7.5602 | 1.9323 | 1.8985 | 2.6617 | 2.797 | 6.4925 | 4.594 | 11.5304 | 13.4289 | 19.9214 | 24.5155 | 3.9802 | 7.5602 | 1.9323 | 1.8985 | 2.6617 | 2.797 | 6.4925 | 4.594 | 11.5404 | 13.4389 | 19.9314 | 24.5255 | 0.01
9.1031 | 8.6723 | 2.1034 | 2.1552 | 3.5172 | 3.3103 | 7.7758 | 5.6206 | 17.7754 | 19.9305 | 27.7063 | 33.3269 | 9.1131 | 8.6723 | 2.1034 | 2.1552 | 3.5172 | 3.3103 | 7.7758 | 5.6206 | 17.7854 | 19.9405 | 27.7163 | 33.3369 | 0.01
7.6437 | 8.3561 | 2.0548 | 2.0822 | 3.2739 | 3.1644 | 7.4109 | 5.3287 | 15.9998 | 18.082 | 25.4929 | 30.8217 | 7.6537 | 8.3561 | 2.0548 | 2.0822 | 3.2739 | 3.1644 | 7.4109 | 5.3287 | 16.0098 | 18.092 | 25.5029 | 30.8317 | 0.01
7.4801 | 8.3207 | 2.0493 | 2.074 | 3.2467 | 3.148 | 7.37 | 5.296 | 15.8008 | 17.8748 | 25.2449 | 30.5409 | 7.4901 | 8.3207 | 2.0493 | 2.074 | 3.2467 | 3.148 | 7.37 | 5.296 | 15.8108 | 17.8848 | 25.2549 | 30.5509 | 0.01
15.1289 | 9.9779 | 2.3043 | 2.4564 | 4.5215 | 3.9129 | 9.2822 | 6.8258 | 25.1068 | 27.5633 | 36.8455 | 43.6713 | 15.1389 | 9.9779 | 2.3043 | 2.4564 | 4.5215 | 3.9129 | 9.2822 | 6.8258 | 25.1168 | 27.5733 | 36.8555 | 43.6813 | 0.01
0.75091 | 6.8627 | 1.825 | 1.7375 | 2.1252 | 2.4751 | 5.6877 | 3.9502 | 7.6136 | 9.3512 | 15.0389 | 18.9891 | 0.76091 | 6.8627 | 1.825 | 1.7375 | 2.1252 | 2.4751 | 5.6877 | 3.9502 | 7.6236 | 9.3612 | 15.0489 | 18.9991 | 0.01
1.9654 | 7.1258 | 1.8655 | 1.7983 | 2.3276 | 2.5965 | 5.9914 | 4.1931 | 9.0912 | 10.8895 | 16.8809 | 21.0739 | 1.9754 | 7.1258 | 1.8655 | 1.7983 | 2.3276 | 2.5965 | 5.9914 | 4.1931 | 9.1012 | 10.8995 | 16.8909 | 21.0839 | 0.01
9.8869 | 8.8422 | 2.1296 | 2.1943 | 3.6478 | 3.3887 | 7.9717 | 5.7774 | 18.7291 | 20.9234 | 28.8951 | 34.6725 | 9.8969 | 8.8422 | 2.1296 | 2.1943 | 3.6478 | 3.3887 | 7.9717 | 5.7774 | 18.7391 | 20.9334 | 28.9051 | 34.6825 | 0.01
6.4668 | 8.1011 | 2.0156 | 2.0233 | 3.0778 | 3.0467 | 7.1167 | 5.0934 | 14.5679 | 16.5913 | 23.708 | 28.8013 | 6.4768 | 8.1011 | 2.0156 | 2.0233 | 3.0778 | 3.0467 | 7.1167 | 5.0934 | 14.5779 | 16.6013 | 23.718 | 28.8113 | 0.01
7.8432 | 8.3994 | 2.0614 | 2.0922 | 3.3072 | 3.1843 | 7.4608 | 5.3686 | 16.2426 | 18.3348 | 25.7956 | 31.1642 | 7.8532 | 8.3994 | 2.0614 | 2.0922 | 3.3072 | 3.1843 | 7.4608 | 5.3686 | 16.2526 | 18.3448 | 25.8056 | 31.1742 | 0.01
3.9091 | 7.547 | 1.9303 | 1.8955 | 2.6515 | 2.7909 | 6.4773 | 4.5818 | 11.456 | 13.3515 | 19.8288 | 24.4106 | 3.9191 | 7.547 | 1.9303 | 1.8955 | 2.6515 | 2.7909 | 6.4773 | 4.5818 | 11.466 | 13.3615 | 19.8388 | 24.4206 | 0.01
3.4369 | 7.4447 | 1.9146 | 1.8718 | 2.5728 | 2.7437 | 6.3592 | 4.4874 | 10.8815 | 12.7533 | 19.1126 | 23.5999 | 3.4469 | 7.4447 | 1.9146 | 1.8718 | 2.5728 | 2.7437 | 6.3592 | 4.4874 | 10.8915 | 12.7633 | 19.1226 | 23.6099 | 0.01
16.7592 | 10.3312 | 2.3586 | 2.538 | 4.7932 | 4.0759 | 9.6898 | 7.1518 | 27.0903 | 29.6283 | 39.3181 | 46.4699 | 16.7692 | 10.3312 | 2.3586 | 2.538 | 4.7932 | 4.0759 | 9.6898 | 7.1518 | 27.1003 | 29.6383 | 39.3281 | 46.4799 | 0.01
-4.8476 | 5.6497 | 1.6384 | 1.4576 | 1.1921 | 1.9152 | 4.2881 | 2.8305 | 0.80204 | 2.2597 | 6.5478 | 9.3782 | -4.8376 | 5.6497 | 1.6384 | 1.4576 | 1.1921 | 1.9152 | 4.2881 | 2.8305 | 0.81204 | 2.2697 | 6.5578 | 9.3882 | 0.01
4.8571 | 7.7524 | 1.9619 | 1.9429 | 2.8095 | 2.8857 | 6.7143 | 4.7714 | 12.6094 | 14.5523 | 21.2665 | 26.038 | 4.8671 | 7.7524 | 1.9619 | 1.9429 | 2.8095 | 2.8857 | 6.7143 | 4.7714 | 12.6194 | 14.5623 | 21.2765 | 26.048 | 0.01
15.5217 | 10.063 | 2.3174 | 2.4761 | 4.587 | 3.9522 | 9.3804 | 6.9043 | 25.5847 | 28.0608 | 37.4412 | 44.3456 | 15.5317 | 10.063 | 2.3174 | 2.4761 | 4.587 | 3.9522 | 9.3804 | 6.9043 | 25.5947 | 28.0708 | 37.4512 | 44.3556 | 0.01
4.5272 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7054 | 12.2081 | 14.1344 | 20.7662 | 25.4717 | 4.5372 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7054 | 12.2181 | 14.1444 | 20.7762 | 25.4817 | 0.01
-6.9383 | 5.1967 | 1.5687 | 1.3531 | 0.84362 | 1.7062 | 3.7654 | 2.4123 | -1.7415 | -0.38845 | 3.377 | 5.7893 | -6.9283 | 5.1967 | 1.5687 | 1.3531 | 0.84362 | 1.7062 | 3.7654 | 2.4123 | -1.7315 | -0.37845 | 3.387 | 5.7993 | 0.01
16.9328 | 10.3688 | 2.3644 | 2.5466 | 4.8221 | 4.0933 | 9.7332 | 7.1866 | 27.3016 | 29.8482 | 39.5814 | 46.768 | 16.9428 | 10.3688 | 2.3644 | 2.5466 | 4.8221 | 4.0933 | 9.7332 | 7.1866 | 27.3116 | 29.8582 | 39.5914 | 46.778 | 0.01
14.0968 | 9.7543 | 2.2699 | 2.4048 | 4.3495 | 3.8097 | 9.0242 | 6.6194 | 23.8511 | 26.2559 | 35.2801 | 41.8995 | 14.1068 | 9.7543 | 2.2699 | 2.4048 | 4.3495 | 3.8097 | 9.0242 | 6.6194 | 23.8611 | 26.2659 | 35.2901 | 41.9095 | 0.01
21.6875 | 11.399 | 2.5229 | 2.7844 | 5.6146 | 4.5687 | 10.9219 | 8.1375 | 33.0864 | 35.8708 | 46.7927 | 54.9302 | 21.6975 | 11.399 | 2.5229 | 2.7844 | 5.6146 | 4.5687 | 10.9219 | 8.1375 | 33.0964 | 35.8808 | 46.8027 | 54.9402 | 0.01
14.6441 | 9.8729 | 2.2881 | 2.4322 | 4.4407 | 3.8644 | 9.161 | 6.7288 | 24.5169 | 26.9491 | 36.1102 | 42.839 | 14.6541 | 9.8729 | 2.2881 | 2.4322 | 4.4407 | 3.8644 | 9.161 | 6.7288 | 24.5269 | 26.9591 | 36.1202 | 42.849 | 0.01
0.7403 | 6.8604 | 1.8247 | 1.737 | 2.1234 | 2.474 | 5.6851 | 3.9481 | 7.6007 | 9.3377 | 15.0228 | 18.9709 | 0.7503 | 6.8604 | 1.8247 | 1.737 | 2.1234 | 2.474 | 5.6851 | 3.9481 | 7.6107 | 9.3477 | 15.0328 | 18.9809 | 0.01
0.19334 | 6.7419 | 1.8064 | 1.7097 | 2.0322 | 2.4193 | 5.5483 | 3.8387 | 6.9352 | 8.6449 | 14.1932 | 18.0319 | 0.20334 | 6.7419 | 1.8064 | 1.7097 | 2.0322 | 2.4193 | 5.5483 | 3.8387 | 6.9452 | 8.6549 | 14.2032 | 18.0419 | 0.01
8.7563 | 8.5972 | 2.0919 | 2.1378 | 3.4594 | 3.2756 | 7.6891 | 5.5513 | 17.3534 | 19.4913 | 27.1803 | 32.7316 | 8.7663 | 8.5972 | 2.0919 | 2.1378 | 3.4594 | 3.2756 | 7.6891 | 5.5513 | 17.3634 | 19.5013 | 27.1903 | 32.7416 | 0.01
8.0989 | 8.4548 | 2.07 | 2.1049 | 3.3498 | 3.2099 | 7.5247 | 5.4198 | 16.5537 | 18.6586 | 26.1833 | 31.6031 | 8.1089 | 8.4548 | 2.07 | 2.1049 | 3.3498 | 3.2099 | 7.5247 | 5.4198 | 16.5637 | 18.6686 | 26.1933 | 31.6131 | 0.01
-3.4729 | 5.9475 | 1.6842 | 1.5264 | 1.4212 | 2.0527 | 4.6318 | 3.1054 | 2.4746 | 4.0009 | 8.6327 | 11.7381 | -3.4629 | 5.9475 | 1.6842 | 1.5264 | 1.4212 | 2.0527 | 4.6318 | 3.1054 | 2.4846 | 4.0109 | 8.6427 | 11.7481 | 0.01
0.19703 | 6.7427 | 1.8066 | 1.7099 | 2.0328 | 2.4197 | 5.5493 | 3.8394 | 6.9397 | 8.6496 | 14.1988 | 18.0382 | 0.20703 | 6.7427 | 1.8066 | 1.7099 | 2.0328 | 2.4197 | 5.5493 | 3.8394 | 6.9497 | 8.6596 | 14.2088 | 18.0482 | 0.01
2.1437 | 7.1645 | 1.8715 | 1.8072 | 2.3573 | 2.6144 | 6.0359 | 4.2287 | 9.3082 | 11.1154 | 17.1513 | 21.38 | 2.1537 | 7.1645 | 1.8715 | 1.8072 | 2.3573 | 2.6144 | 6.0359 | 4.2287 | 9.3182 | 11.1254 | 17.1613 | 21.39 | 0.01
2.1804 | 7.1724 | 1.8727 | 1.809 | 2.3634 | 2.618 | 6.0451 | 4.2361 | 9.3528 | 11.1618 | 17.2069 | 21.443 | 2.1904 | 7.1724 | 1.8727 | 1.809 | 2.3634 | 2.618 | 6.0451 | 4.2361 | 9.3628 | 11.1718 | 17.2169 | 21.453 | 0.01
8.4919 | 8.5399 | 2.0831 | 2.1246 | 3.4153 | 3.2492 | 7.623 | 5.4984 | 17.0318 | 19.1564 | 26.7793 | 32.2777 | 8.5019 | 8.5399 | 2.0831 | 2.1246 | 3.4153 | 3.2492 | 7.623 | 5.4984 | 17.0418 | 19.1664 | 26.7893 | 32.2877 | 0.01
-0.30742 | 6.6334 | 1.7898 | 1.6846 | 1.9488 | 2.3693 | 5.4231 | 3.7385 | 6.326 | 8.0106 | 13.4337 | 17.1723 | -0.29742 | 6.6334 | 1.7898 | 1.6846 | 1.9488 | 2.3693 | 5.4231 | 3.7385 | 6.336 | 8.0206 | 13.4437 | 17.1823 | 0.01
5.7009 | 7.9352 | 1.99 | 1.985 | 2.9501 | 2.9701 | 6.9252 | 4.9402 | 13.6361 | 15.6211 | 22.5463 | 27.4865 | 5.7109 | 7.9352 | 1.99 | 1.985 | 2.9501 | 2.9701 | 6.9252 | 4.9402 | 13.6461 | 15.6311 | 22.5563 | 27.4965 | 0.01
3.9954 | 7.5657 | 1.9332 | 1.8998 | 2.6659 | 2.7995 | 6.4988 | 4.5991 | 11.561 | 13.4608 | 19.9596 | 24.5587 | 4.0054 | 7.5657 | 1.9332 | 1.8998 | 2.6659 | 2.7995 | 6.4988 | 4.5991 | 11.571 | 13.4708 | 19.9696 | 24.5687 | 0.01
2.8736 | 7.3226 | 1.8958 | 1.8437 | 2.4789 | 2.6874 | 6.2184 | 4.3747 | 10.1962 | 12.0399 | 18.2583 | 22.633 | 2.8836 | 7.3226 | 1.8958 | 1.8437 | 2.4789 | 2.6874 | 6.2184 | 4.3747 | 10.2062 | 12.0499 | 18.2683 | 22.643 | 0.01
7.4078 | 8.305 | 2.0469 | 2.0704 | 3.2346 | 3.1408 | 7.352 | 5.2816 | 15.7128 | 17.7832 | 25.1352 | 30.4167 | 7.4178 | 8.305 | 2.0469 | 2.0704 | 3.2346 | 3.1408 | 7.352 | 5.2816 | 15.7228 | 17.7932 | 25.1452 | 30.4267 | 0.01
4.6413 | 7.7056 | 1.9547 | 1.9321 | 2.7735 | 2.8641 | 6.6603 | 4.7283 | 12.3469 | 14.2789 | 20.9392 | 25.6675 | 4.6513 | 7.7056 | 1.9547 | 1.9321 | 2.7735 | 2.8641 | 6.6603 | 4.7283 | 12.3569 | 14.2889 | 20.9492 | 25.6775 | 0.01
17.8399 | 10.5653 | 2.3947 | 2.592 | 4.9733 | 4.184 | 9.96 | 7.368 | 28.4052 | 30.9972 | 40.9571 | 48.3251 | 17.8499 | 10.5653 | 2.3947 | 2.592 | 4.9733 | 4.184 | 9.96 | 7.368 | 28.4152 | 31.0072 | 40.9671 | 48.3351 | 0.01
10.3126 | 8.9344 | 2.1438 | 2.2156 | 3.7188 | 3.4313 | 8.0782 | 5.8625 | 19.2471 | 21.4627 | 29.5409 | 35.4034 | 10.3226 | 8.9344 | 2.1438 | 2.2156 | 3.7188 | 3.4313 | 8.0782 | 5.8625 | 19.2571 | 21.4727 | 29.5509 | 35.4134 | 0.01
0.93636 | 6.9029 | 1.8312 | 1.7468 | 2.1561 | 2.4936 | 5.7341 | 3.9873 | 7.8392 | 9.5861 | 15.3201 | 19.3074 | 0.94636 | 6.9029 | 1.8312 | 1.7468 | 2.1561 | 2.4936 | 5.7341 | 3.9873 | 7.8492 | 9.5961 | 15.3301 | 19.3174 | 0.01
5.9171 | 7.982 | 1.9972 | 1.9959 | 2.9862 | 2.9917 | 6.9793 | 4.9834 | 13.8992 | 15.8951 | 22.8743 | 27.8578 | 5.9271 | 7.982 | 1.9972 | 1.9959 | 2.9862 | 2.9917 | 6.9793 | 4.9834 | 13.9092 | 15.9051 | 22.8843 | 27.8678 | 0.01
14.2609 | 9.7899 | 2.2754 | 2.413 | 4.3768 | 3.8261 | 9.0652 | 6.6522 | 24.0507 | 26.4638 | 35.529 | 42.1812 | 14.2709 | 9.7899 | 2.2754 | 2.413 | 4.3768 | 3.8261 | 9.0652 | 6.6522 | 24.0607 | 26.4738 | 35.539 | 42.1912 | 0.01
4.7586 | 7.731 | 1.9586 | 1.9379 | 2.7931 | 2.8759 | 6.6897 | 4.7517 | 12.4897 | 14.4276 | 21.1173 | 25.869 | 4.7686 | 7.731 | 1.9586 | 1.9379 | 2.7931 | 2.8759 | 6.6897 | 4.7517 | 12.4997 | 14.4376 | 21.1273 | 25.879 | 0.01
-1.5358 | 6.3672 | 1.7488 | 1.6232 | 1.744 | 2.2464 | 5.116 | 3.4928 | 4.8314 | 6.4546 | 11.5707 | 15.0635 | -1.5258 | 6.3672 | 1.7488 | 1.6232 | 1.744 | 2.2464 | 5.116 | 3.4928 | 4.8414 | 6.4646 | 11.5807 | 15.0735 | 0.01
4.5187 | 7.6791 | 1.9506 | 1.9259 | 2.7531 | 2.8519 | 6.6297 | 4.7037 | 12.1977 | 14.1237 | 20.7534 | 25.4571 | 4.5287 | 7.6791 | 1.9506 | 1.9259 | 2.7531 | 2.8519 | 6.6297 | 4.7037 | 12.2077 | 14.1337 | 20.7634 | 25.4671 | 0.01
10.9318 | 9.0686 | 2.1644 | 2.2466 | 3.822 | 3.4932 | 8.233 | 5.9864 | 20.0004 | 22.247 | 30.4799 | 36.4663 | 10.9418 | 9.0686 | 2.1644 | 2.2466 | 3.822 | 3.4932 | 8.233 | 5.9864 | 20.0104 | 22.257 | 30.4899 | 36.4763 | 0.01
3.7619 | 7.5151 | 1.9254 | 1.8881 | 2.627 | 2.7762 | 6.4405 | 4.5524 | 11.2769 | 13.165 | 19.6055 | 24.1579 | 3.7719 | 7.5151 | 1.9254 | 1.8881 | 2.627 | 2.7762 | 6.4405 | 4.5524 | 11.2869 | 13.175 | 19.6155 | 24.1679 | 0.01
0.66962 | 6.8451 | 1.8223 | 1.7335 | 2.1116 | 2.467 | 5.6674 | 3.9339 | 7.5147 | 9.2482 | 14.9156 | 18.8495 | 0.67962 | 6.8451 | 1.8223 | 1.7335 | 2.1116 | 2.467 | 5.6674 | 3.9339 | 7.5247 | 9.2582 | 14.9256 | 18.8595 | 0.01
8.4453 | 8.5298 | 2.0815 | 2.1223 | 3.4076 | 3.2445 | 7.6113 | 5.4891 | 16.9752 | 19.0974 | 26.7088 | 32.1978 | 8.4553 | 8.5298 | 2.0815 | 2.1223 | 3.4076 | 3.2445 | 7.6113 | 5.4891 | 16.9852 | 19.1074 | 26.7188 | 32.2078 | 0.01
4 | 7.5667 | 1.9333 | 1.9 | 2.6667 | 2.8 | 6.5 | 4.6 | 11.5666 | 13.4666 | 19.9666 | 24.5666 | 4.01 | 7.5667 | 1.9333 | 1.9 | 2.6667 | 2.8 | 6.5 | 4.6 | 11.5766 | 13.4766 | 19.9766 | 24.5766 | 0.01
0.11313 | 6.7245 | 1.8038 | 1.7057 | 2.0189 | 2.4113 | 5.5283 | 3.8226 | 6.8376 | 8.5433 | 14.0716 | 17.8942 | 0.12313 | 6.7245 | 1.8038 | 1.7057 | 2.0189 | 2.4113 | 5.5283 | 3.8226 | 6.8476 | 8.5533 | 14.0816 | 17.9042 | 0.01
14.3302 | 9.8049 | 2.2777 | 2.4165 | 4.3884 | 3.833 | 9.0825 | 6.666 | 24.135 | 26.5516 | 35.6341 | 42.3001 | 14.3402 | 9.8049 | 2.2777 | 2.4165 | 4.3884 | 3.833 | 9.0825 | 6.666 | 24.145 | 26.5616 | 35.6441 | 42.3101 | 0.01
0.82956 | 6.8797 | 1.8277 | 1.7415 | 2.1383 | 2.483 | 5.7074 | 3.9659 | 7.7093 | 9.4508 | 15.1582 | 19.1241 | 0.83956 | 6.8797 | 1.8277 | 1.7415 | 2.1383 | 2.483 | 5.7074 | 3.9659 | 7.7193 | 9.4608 | 15.1682 | 19.1341 | 0.01
6.5365 | 8.1162 | 2.0179 | 2.0268 | 3.0894 | 3.0537 | 7.1341 | 5.1073 | 14.6528 | 16.6796 | 23.8137 | 28.921 | 6.5465 | 8.1162 | 2.0179 | 2.0268 | 3.0894 | 3.0537 | 7.1341 | 5.1073 | 14.6628 | 16.6896 | 23.8237 | 28.931 | 0.01
2.4857 | 7.2386 | 1.8829 | 1.8243 | 2.4143 | 2.6486 | 6.1214 | 4.2971 | 9.7243 | 11.5486 | 17.67 | 21.9671 | 2.4957 | 7.2386 | 1.8829 | 1.8243 | 2.4143 | 2.6486 | 6.1214 | 4.2971 | 9.7343 | 11.5586 | 17.68 | 21.9771 | 0.01
9.4618 | 8.7501 | 2.1154 | 2.1731 | 3.577 | 3.3462 | 7.8655 | 5.6924 | 18.2119 | 20.385 | 28.2504 | 33.9428 | 9.4718 | 8.7501 | 2.1154 | 2.1731 | 3.577 | 3.3462 | 7.8655 | 5.6924 | 18.2219 | 20.395 | 28.2604 | 33.9528 | 0.01
10.5152 | 8.9783 | 2.1505 | 2.2258 | 3.7525 | 3.4515 | 8.1288 | 5.903 | 19.4935 | 21.7193 | 29.8481 | 35.7511 | 10.5252 | 8.9783 | 2.1505 | 2.2258 | 3.7525 | 3.4515 | 8.1288 | 5.903 | 19.5035 | 21.7293 | 29.8581 | 35.7611 | 0.01
13.8852 | 9.7085 | 2.2628 | 2.3943 | 4.3142 | 3.7885 | 8.9713 | 6.577 | 23.5937 | 25.9879 | 34.9592 | 41.5363 | 13.8952 | 9.7085 | 2.2628 | 2.3943 | 4.3142 | 3.7885 | 8.9713 | 6.577 | 23.6037 | 25.9979 | 34.9692 | 41.5463 | 0.01
7.4114 | 8.3058 | 2.047 | 2.0706 | 3.2352 | 3.1411 | 7.3529 | 5.2823 | 15.7172 | 17.7878 | 25.1406 | 30.4229 | 7.4214 | 8.3058 | 2.047 | 2.0706 | 3.2352 | 3.1411 | 7.3529 | 5.2823 | 15.7272 | 17.7978 | 25.1506 | 30.4329 | 0.01
3.3173 | 7.4187 | 1.9106 | 1.8659 | 2.5529 | 2.7317 | 6.3293 | 4.4635 | 10.736 | 12.6019 | 18.9312 | 23.3947 | 3.3273 | 7.4187 | 1.9106 | 1.8659 | 2.5529 | 2.7317 | 6.3293 | 4.4635 | 10.746 | 12.6119 | 18.9412 | 23.4047 | 0.01
6.514 | 8.1114 | 2.0171 | 2.0257 | 3.0857 | 3.0514 | 7.1285 | 5.1028 | 14.6253 | 16.651 | 23.7795 | 28.8823 | 6.524 | 8.1114 | 2.0171 | 2.0257 | 3.0857 | 3.0514 | 7.1285 | 5.1028 | 14.6353 | 16.661 | 23.7895 | 28.8923 | 0.01
-0.5379 | 6.5835 | 1.7821 | 1.6731 | 1.9104 | 2.3462 | 5.3655 | 3.6924 | 6.0456 | 7.7187 | 13.0842 | 16.7766 | -0.5279 | 6.5835 | 1.7821 | 1.6731 | 1.9104 | 2.3462 | 5.3655 | 3.6924 | 6.0556 | 7.7287 | 13.0942 | 16.7866 | 0.01
1.9903 | 7.1312 | 1.8663 | 1.7995 | 2.3317 | 2.599 | 5.9976 | 4.1981 | 9.1215 | 10.9211 | 16.9186 | 21.1167 | 2.0003 | 7.1312 | 1.8663 | 1.7995 | 2.3317 | 2.599 | 5.9976 | 4.1981 | 9.1315 | 10.9311 | 16.9286 | 21.1267 | 0.01
17.5171 | 10.4954 | 2.3839 | 2.5759 | 4.9195 | 4.1517 | 9.8793 | 7.3034 | 28.0125 | 30.5883 | 40.4676 | 47.771 | 17.5271 | 10.4954 | 2.3839 | 2.5759 | 4.9195 | 4.1517 | 9.8793 | 7.3034 | 28.0225 | 30.5983 | 40.4776 | 47.781 | 0.01
5.7762 | 7.9515 | 1.9925 | 1.9888 | 2.9627 | 2.9776 | 6.9441 | 4.9552 | 13.7277 | 15.7166 | 22.6606 | 27.6159 | 5.7862 | 7.9515 | 1.9925 | 1.9888 | 2.9627 | 2.9776 | 6.9441 | 4.9552 | 13.7377 | 15.7266 | 22.6706 | 27.6259 | 0.01
5.936 | 7.9861 | 1.9979 | 1.9968 | 2.9893 | 2.9936 | 6.984 | 4.9872 | 13.9222 | 15.919 | 22.903 | 27.8902 | 5.946 | 7.9861 | 1.9979 | 1.9968 | 2.9893 | 2.9936 | 6.984 | 4.9872 | 13.9322 | 15.929 | 22.913 | 27.9002 | 0.01
-4.9884 | 5.6192 | 1.6337 | 1.4506 | 1.1686 | 1.9012 | 4.2529 | 2.8023 | 0.63082 | 2.0814 | 6.3343 | 9.1366 | -4.9784 | 5.6192 | 1.6337 | 1.4506 | 1.1686 | 1.9012 | 4.2529 | 2.8023 | 0.64082 | 2.0914 | 6.3443 | 9.1466 | 0.01
4.2438 | 7.6195 | 1.9415 | 1.9122 | 2.7073 | 2.8244 | 6.561 | 4.6488 | 11.8633 | 13.7755 | 20.3365 | 24.9852 | 4.2538 | 7.6195 | 1.9415 | 1.9122 | 2.7073 | 2.8244 | 6.561 | 4.6488 | 11.8733 | 13.7855 | 20.3465 | 24.9952 | 0.01
8.0514 | 8.4445 | 2.0684 | 2.1026 | 3.3419 | 3.2051 | 7.5128 | 5.4103 | 16.4958 | 18.5984 | 26.1112 | 31.5215 | 8.0614 | 8.4445 | 2.0684 | 2.1026 | 3.3419 | 3.2051 | 7.5128 | 5.4103 | 16.5058 | 18.6084 | 26.1212 | 31.5315 | 0.01
-8.3684 | 4.8868 | 1.5211 | 1.2816 | 0.60526 | 1.5632 | 3.4079 | 2.1263 | -3.4816 | -2.2 | 1.2079 | 3.3342 | -8.3584 | 4.8868 | 1.5211 | 1.2816 | 0.60526 | 1.5632 | 3.4079 | 2.1263 | -3.4716 | -2.19 | 1.2179 | 3.3442 | 0.01
10.4473 | 8.9636 | 2.1482 | 2.2224 | 3.7412 | 3.4447 | 8.1118 | 5.8895 | 19.4109 | 21.6333 | 29.7451 | 35.6346 | 10.4573 | 8.9636 | 2.1482 | 2.2224 | 3.7412 | 3.4447 | 8.1118 | 5.8895 | 19.4209 | 21.6433 | 29.7551 | 35.6446 | 0.01
6.2781 | 8.0603 | 2.0093 | 2.0139 | 3.0463 | 3.0278 | 7.0695 | 5.0556 | 14.3383 | 16.3522 | 23.4218 | 28.4774 | 6.2881 | 8.0603 | 2.0093 | 2.0139 | 3.0463 | 3.0278 | 7.0695 | 5.0556 | 14.3483 | 16.3622 | 23.4318 | 28.4874 | 0.01
-0.026116 | 6.6943 | 1.7991 | 1.6987 | 1.9956 | 2.3974 | 5.4935 | 3.7948 | 6.6682 | 8.3669 | 13.8604 | 17.6552 | -0.016116 | 6.6943 | 1.7991 | 1.6987 | 1.9956 | 2.3974 | 5.4935 | 3.7948 | 6.6782 | 8.3769 | 13.8704 | 17.6652 | 0.01
12.3808 | 9.3825 | 2.2127 | 2.319 | 4.0635 | 3.6381 | 8.5952 | 6.2762 | 21.7633 | 24.0823 | 32.6775 | 38.9537 | 12.3908 | 9.3825 | 2.2127 | 2.319 | 4.0635 | 3.6381 | 8.5952 | 6.2762 | 21.7733 | 24.0923 | 32.6875 | 38.9637 | 0.01
4.3092 | 7.6337 | 1.9436 | 1.9155 | 2.7182 | 2.8309 | 6.5773 | 4.6618 | 11.9428 | 13.8583 | 20.4356 | 25.0974 | 4.3192 | 7.6337 | 1.9436 | 1.9155 | 2.7182 | 2.8309 | 6.5773 | 4.6618 | 11.9528 | 13.8683 | 20.4456 | 25.1074 | 0.01
9.5463 | 8.7684 | 2.1182 | 2.1773 | 3.591 | 3.3546 | 7.8866 | 5.7093 | 18.3146 | 20.492 | 28.3785 | 34.0878 | 9.5563 | 8.7684 | 2.1182 | 2.1773 | 3.591 | 3.3546 | 7.8866 | 5.7093 | 18.3246 | 20.502 | 28.3885 | 34.0978 | 0.01
3.7633 | 7.5154 | 1.9254 | 1.8882 | 2.6272 | 2.7763 | 6.4408 | 4.5527 | 11.2787 | 13.1668 | 19.6077 | 24.1603 | 3.7733 | 7.5154 | 1.9254 | 1.8882 | 2.6272 | 2.7763 | 6.4408 | 4.5527 | 11.2887 | 13.1768 | 19.6177 | 24.1703 | 0.01
8.7658 | 8.5992 | 2.0922 | 2.1383 | 3.461 | 3.2766 | 7.6914 | 5.5532 | 17.365 | 19.5033 | 27.1947 | 32.7479 | 8.7758 | 8.5992 | 2.0922 | 2.1383 | 3.461 | 3.2766 | 7.6914 | 5.5532 | 17.375 | 19.5133 | 27.2047 | 32.7579 | 0.01
0.69767 | 6.8512 | 1.8233 | 1.7349 | 2.1163 | 2.4698 | 5.6744 | 3.9395 | 7.5488 | 9.2837 | 14.9581 | 18.8977 | 0.70767 | 6.8512 | 1.8233 | 1.7349 | 2.1163 | 2.4698 | 5.6744 | 3.9395 | 7.5588 | 9.2937 | 14.9681 | 18.9077 | 0.01
11.5977 | 9.2128 | 2.1866 | 2.2799 | 3.9329 | 3.5598 | 8.3994 | 6.1195 | 20.8105 | 23.0904 | 31.4898 | 37.6094 | 11.6077 | 9.2128 | 2.1866 | 2.2799 | 3.9329 | 3.5598 | 8.3994 | 6.1195 | 20.8205 | 23.1004 | 31.4998 | 37.6194 | 0.01
8.4712 | 8.5354 | 2.0824 | 2.1236 | 3.4119 | 3.2471 | 7.6178 | 5.4942 | 17.0067 | 19.1302 | 26.748 | 32.2423 | 8.4812 | 8.5354 | 2.0824 | 2.1236 | 3.4119 | 3.2471 | 7.6178 | 5.4942 | 17.0167 | 19.1402 | 26.758 | 32.2523 | 0.01
18.2142 | 10.6464 | 2.4071 | 2.6107 | 5.0357 | 4.2214 | 10.0536 | 7.4428 | 28.8606 | 31.4713 | 41.5249 | 48.9677 | 18.2242 | 10.6464 | 2.4071 | 2.6107 | 5.0357 | 4.2214 | 10.0536 | 7.4428 | 28.8706 | 31.4813 | 41.5349 | 48.9777 | 0.01
13.8999 | 9.7117 | 2.2633 | 2.395 | 4.3167 | 3.79 | 8.975 | 6.58 | 23.6116 | 26.0066 | 34.9816 | 41.5615 | 13.9099 | 9.7117 | 2.2633 | 2.395 | 4.3167 | 3.79 | 8.975 | 6.58 | 23.6216 | 26.0166 | 34.9916 | 41.5715 | 0.01
6.3636 | 8.0788 | 2.0121 | 2.0182 | 3.0606 | 3.0364 | 7.0909 | 5.0727 | 14.4424 | 16.4605 | 23.5514 | 28.6242 | 6.3736 | 8.0788 | 2.0121 | 2.0182 | 3.0606 | 3.0364 | 7.0909 | 5.0727 | 14.4524 | 16.4705 | 23.5614 | 28.6342 | 0.01
6.9097 | 8.1971 | 2.0303 | 2.0455 | 3.1516 | 3.091 | 7.2274 | 5.1819 | 15.1068 | 17.1523 | 24.3797 | 29.5616 | 6.9197 | 8.1971 | 2.0303 | 2.0455 | 3.1516 | 3.091 | 7.2274 | 5.1819 | 15.1168 | 17.1623 | 24.3897 | 29.5716 | 0.01
1.1273 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7818 | 4.0255 | 8.0716 | 9.8279 | 15.6098 | 19.6352 | 1.1373 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7818 | 4.0255 | 8.0816 | 9.8379 | 15.6198 | 19.6452 | 0.01
15.8964 | 10.1442 | 2.3299 | 2.4948 | 4.6494 | 3.9896 | 9.4741 | 6.9793 | 26.0407 | 28.5355 | 38.0096 | 44.9889 | 15.9064 | 10.1442 | 2.3299 | 2.4948 | 4.6494 | 3.9896 | 9.4741 | 6.9793 | 26.0507 | 28.5455 | 38.0196 | 44.9989 | 0.01
6.1089 | 8.0236 | 2.0036 | 2.0054 | 3.0181 | 3.0109 | 7.0272 | 5.0218 | 14.1325 | 16.1379 | 23.1651 | 28.1869 | 6.1189 | 8.0236 | 2.0036 | 2.0054 | 3.0181 | 3.0109 | 7.0272 | 5.0218 | 14.1425 | 16.1479 | 23.1751 | 28.1969 | 0.01
0.25643 | 6.7556 | 1.8085 | 1.7128 | 2.0427 | 2.4256 | 5.5641 | 3.8513 | 7.012 | 8.7248 | 14.2889 | 18.1402 | 0.26643 | 6.7556 | 1.8085 | 1.7128 | 2.0427 | 2.4256 | 5.5641 | 3.8513 | 7.022 | 8.7348 | 14.2989 | 18.1502 | 0.01
-4.2332 | 5.7828 | 1.6589 | 1.4883 | 1.2945 | 1.9767 | 4.4417 | 2.9534 | 1.5496 | 3.038 | 7.4797 | 10.433 | -4.2232 | 5.7828 | 1.6589 | 1.4883 | 1.2945 | 1.9767 | 4.4417 | 2.9534 | 1.5596 | 3.048 | 7.4897 | 10.443 | 0.01
3.0006 | 7.3501 | 1.9 | 1.85 | 2.5001 | 2.7001 | 6.2501 | 4.4001 | 10.3507 | 12.2007 | 18.4509 | 22.851 | 3.0106 | 7.3501 | 1.9 | 1.85 | 2.5001 | 2.7001 | 6.2501 | 4.4001 | 10.3607 | 12.2107 | 18.4609 | 22.861 | 0.01
-0.019623 | 6.6957 | 1.7993 | 1.699 | 1.9967 | 2.398 | 5.4951 | 3.7961 | 6.6761 | 8.3751 | 13.8702 | 17.6663 | -0.0096226 | 6.6957 | 1.7993 | 1.699 | 1.9967 | 2.398 | 5.4951 | 3.7961 | 6.6861 | 8.3851 | 13.8802 | 17.6763 | 0.01
1.7234 | 7.0734 | 1.8574 | 1.7862 | 2.2872 | 2.5723 | 5.9308 | 4.1447 | 8.7968 | 10.583 | 16.5138 | 20.6585 | 1.7334 | 7.0734 | 1.8574 | 1.7862 | 2.2872 | 2.5723 | 5.9308 | 4.1447 | 8.8068 | 10.593 | 16.5238 | 20.6685 | 0.01
17.9337 | 10.5856 | 2.3978 | 2.5967 | 4.9889 | 4.1934 | 9.9834 | 7.3867 | 28.5193 | 31.116 | 41.0994 | 48.4862 | 17.9437 | 10.5856 | 2.3978 | 2.5967 | 4.9889 | 4.1934 | 9.9834 | 7.3867 | 28.5293 | 31.126 | 41.1094 | 48.4962 | 0.01
5.9536 | 7.9899 | 1.9985 | 1.9977 | 2.9923 | 2.9954 | 6.9884 | 4.9907 | 13.9435 | 15.9412 | 22.9296 | 27.9203 | 5.9636 | 7.9899 | 1.9985 | 1.9977 | 2.9923 | 2.9954 | 6.9884 | 4.9907 | 13.9535 | 15.9512 | 22.9396 | 27.9303 | 0.01
8.1286 | 8.4612 | 2.071 | 2.1064 | 3.3548 | 3.2129 | 7.5321 | 5.4257 | 16.5897 | 18.6962 | 26.2283 | 31.654 | 8.1386 | 8.4612 | 2.071 | 2.1064 | 3.3548 | 3.2129 | 7.5321 | 5.4257 | 16.5997 | 18.7062 | 26.2383 | 31.664 | 0.01
0.99013 | 6.9145 | 1.833 | 1.7495 | 2.165 | 2.499 | 5.7475 | 3.998 | 7.9047 | 9.6542 | 15.4017 | 19.3997 | 1.0001 | 6.9145 | 1.833 | 1.7495 | 2.165 | 2.499 | 5.7475 | 3.998 | 7.9147 | 9.6642 | 15.4117 | 19.4097 | 0.01
9.9327 | 8.8521 | 2.1311 | 2.1966 | 3.6554 | 3.3933 | 7.9832 | 5.7865 | 18.7847 | 20.9814 | 28.9645 | 34.7511 | 9.9427 | 8.8521 | 2.1311 | 2.1966 | 3.6554 | 3.3933 | 7.9832 | 5.7865 | 18.7947 | 20.9914 | 28.9745 | 34.7611 | 0.01
13.1113 | 9.5408 | 2.237 | 2.3556 | 4.1852 | 3.7111 | 8.7778 | 6.4223 | 22.6521 | 25.0077 | 33.7855 | 40.2078 | 13.1213 | 9.5408 | 2.237 | 2.3556 | 4.1852 | 3.7111 | 8.7778 | 6.4223 | 22.6621 | 25.0177 | 33.7955 | 40.2178 | 0.01
3.9177 | 7.5488 | 1.9306 | 1.8959 | 2.6529 | 2.7918 | 6.4794 | 4.5835 | 11.4665 | 13.3624 | 19.8418 | 24.4253 | 3.9277 | 7.5488 | 1.9306 | 1.8959 | 2.6529 | 2.7918 | 6.4794 | 4.5835 | 11.4765 | 13.3724 | 19.8518 | 24.4353 | 0.01
4.0887 | 7.5859 | 1.9363 | 1.9044 | 2.6814 | 2.8089 | 6.5222 | 4.6177 | 11.6745 | 13.579 | 20.1011 | 24.7189 | 4.0987 | 7.5859 | 1.9363 | 1.9044 | 2.6814 | 2.8089 | 6.5222 | 4.6177 | 11.6845 | 13.589 | 20.1111 | 24.7289 | 0.01
-0.055066 | 6.6881 | 1.7982 | 1.6972 | 1.9908 | 2.3945 | 5.4862 | 3.789 | 6.633 | 8.3303 | 13.8165 | 17.6055 | -0.045066 | 6.6881 | 1.7982 | 1.6972 | 1.9908 | 2.3945 | 5.4862 | 3.789 | 6.643 | 8.3403 | 13.8265 | 17.6155 | 0.01
3.9499 | 7.5558 | 1.9317 | 1.8975 | 2.6583 | 2.795 | 6.4875 | 4.59 | 11.5057 | 13.4032 | 19.8906 | 24.4806 | 3.9599 | 7.5558 | 1.9317 | 1.8975 | 2.6583 | 2.795 | 6.4875 | 4.59 | 11.5157 | 13.4132 | 19.9006 | 24.4906 | 0.01
2.5412 | 7.2506 | 1.8847 | 1.8271 | 2.4235 | 2.6541 | 6.1353 | 4.3082 | 9.7918 | 11.6189 | 17.7542 | 22.0624 | 2.5512 | 7.2506 | 1.8847 | 1.8271 | 2.4235 | 2.6541 | 6.1353 | 4.3082 | 9.8018 | 11.6289 | 17.7642 | 22.0724 | 0.01
-1.6705 | 6.3381 | 1.7443 | 1.6165 | 1.7216 | 2.233 | 5.0824 | 3.4659 | 4.6676 | 6.2841 | 11.3664 | 14.8323 | -1.6605 | 6.3381 | 1.7443 | 1.6165 | 1.7216 | 2.233 | 5.0824 | 3.4659 | 4.6776 | 6.2941 | 11.3764 | 14.8423 | 0.01
17.8938 | 10.577 | 2.3965 | 2.5947 | 4.9823 | 4.1894 | 9.9734 | 7.3788 | 28.4708 | 31.0655 | 41.0389 | 48.4177 | 17.9038 | 10.577 | 2.3965 | 2.5947 | 4.9823 | 4.1894 | 9.9734 | 7.3788 | 28.4808 | 31.0755 | 41.0489 | 48.4277 | 0.01
2.6217 | 7.268 | 1.8874 | 1.8311 | 2.4369 | 2.6622 | 6.1554 | 4.3243 | 9.8897 | 11.7208 | 17.8762 | 22.2005 | 2.6317 | 7.268 | 1.8874 | 1.8311 | 2.4369 | 2.6622 | 6.1554 | 4.3243 | 9.8997 | 11.7308 | 17.8862 | 22.2105 | 0.01
6.531 | 8.1151 | 2.0177 | 2.0266 | 3.0885 | 3.0531 | 7.1328 | 5.1062 | 14.6461 | 16.6726 | 23.8054 | 28.9116 | 6.541 | 8.1151 | 2.0177 | 2.0266 | 3.0885 | 3.0531 | 7.1328 | 5.1062 | 14.6561 | 16.6826 | 23.8154 | 28.9216 | 0.01
-0.63752 | 6.5619 | 1.7787 | 1.6681 | 1.8937 | 2.3362 | 5.3406 | 3.6725 | 5.9244 | 7.5925 | 12.9331 | 16.6056 | -0.62752 | 6.5619 | 1.7787 | 1.6681 | 1.8937 | 2.3362 | 5.3406 | 3.6725 | 5.9344 | 7.6025 | 12.9431 | 16.6156 | 0.01
3.242 | 7.4024 | 1.9081 | 1.8621 | 2.5403 | 2.7242 | 6.3105 | 4.4484 | 10.6444 | 12.5065 | 18.817 | 23.2654 | 3.252 | 7.4024 | 1.9081 | 1.8621 | 2.5403 | 2.7242 | 6.3105 | 4.4484 | 10.6544 | 12.5165 | 18.827 | 23.2754 | 0.01
7.7059 | 8.3696 | 2.0569 | 2.0853 | 3.2843 | 3.1706 | 7.4265 | 5.3412 | 16.0755 | 18.1608 | 25.5873 | 30.9285 | 7.7159 | 8.3696 | 2.0569 | 2.0853 | 3.2843 | 3.1706 | 7.4265 | 5.3412 | 16.0855 | 18.1708 | 25.5973 | 30.9385 | 0.01
5.5315 | 7.8985 | 1.9844 | 1.9766 | 2.9219 | 2.9532 | 6.8829 | 4.9063 | 13.43 | 15.4066 | 22.2895 | 27.1958 | 5.5415 | 7.8985 | 1.9844 | 1.9766 | 2.9219 | 2.9532 | 6.8829 | 4.9063 | 13.44 | 15.4166 | 22.2995 | 27.2058 | 0.01
6.2875 | 8.0623 | 2.0096 | 2.0144 | 3.0479 | 3.0288 | 7.0719 | 5.0575 | 14.3498 | 16.3642 | 23.4361 | 28.4936 | 6.2975 | 8.0623 | 2.0096 | 2.0144 | 3.0479 | 3.0288 | 7.0719 | 5.0575 | 14.3598 | 16.3742 | 23.4461 | 28.5036 | 0.01
8.8478 | 8.617 | 2.0949 | 2.1424 | 3.4746 | 3.2848 | 7.7119 | 5.5696 | 17.4648 | 19.6072 | 27.3191 | 32.8887 | 8.8578 | 8.617 | 2.0949 | 2.1424 | 3.4746 | 3.2848 | 7.7119 | 5.5696 | 17.4748 | 19.6172 | 27.3291 | 32.8987 | 0.01
3.6485 | 7.4905 | 1.9216 | 1.8824 | 2.6081 | 2.7648 | 6.4121 | 4.5297 | 11.139 | 13.0214 | 19.4335 | 23.9632 | 3.6585 | 7.4905 | 1.9216 | 1.8824 | 2.6081 | 2.7648 | 6.4121 | 4.5297 | 11.149 | 13.0314 | 19.4435 | 23.9732 | 0.01
4.5406 | 7.6838 | 1.9514 | 1.927 | 2.7568 | 2.8541 | 6.6352 | 4.7081 | 12.2244 | 14.1515 | 20.7866 | 25.4947 | 4.5506 | 7.6838 | 1.9514 | 1.927 | 2.7568 | 2.8541 | 6.6352 | 4.7081 | 12.2344 | 14.1615 | 20.7966 | 25.5047 | 0.01
7.2969 | 8.281 | 2.0432 | 2.0648 | 3.2162 | 3.1297 | 7.3242 | 5.2594 | 15.5779 | 17.6428 | 24.967 | 30.2264 | 7.3069 | 8.281 | 2.0432 | 2.0648 | 3.2162 | 3.1297 | 7.3242 | 5.2594 | 15.5879 | 17.6528 | 24.977 | 30.2364 | 0.01
7.5894 | 8.3444 | 2.053 | 2.0795 | 3.2649 | 3.1589 | 7.3974 | 5.3179 | 15.9338 | 18.0133 | 25.4106 | 30.7285 | 7.5994 | 8.3444 | 2.053 | 2.0795 | 3.2649 | 3.1589 | 7.3974 | 5.3179 | 15.9438 | 18.0233 | 25.4206 | 30.7385 | 0.01
-1.186 | 6.443 | 1.7605 | 1.6407 | 1.8023 | 2.2814 | 5.2035 | 3.5628 | 5.257 | 6.8977 | 12.1012 | 15.664 | -1.176 | 6.443 | 1.7605 | 1.6407 | 1.8023 | 2.2814 | 5.2035 | 3.5628 | 5.267 | 6.9077 | 12.1112 | 15.674 | 0.01
7.5221 | 8.3298 | 2.0507 | 2.0761 | 3.2537 | 3.1522 | 7.3805 | 5.3044 | 15.8519 | 17.928 | 25.3085 | 30.6129 | 7.5321 | 8.3298 | 2.0507 | 2.0761 | 3.2537 | 3.1522 | 7.3805 | 5.3044 | 15.8619 | 17.938 | 25.3185 | 30.6229 | 0.01
4.1728 | 7.6041 | 1.9391 | 1.9086 | 2.6955 | 2.8173 | 6.5432 | 4.6346 | 11.7769 | 13.6856 | 20.2288 | 24.8633 | 4.1828 | 7.6041 | 1.9391 | 1.9086 | 2.6955 | 2.8173 | 6.5432 | 4.6346 | 11.7869 | 13.6956 | 20.2388 | 24.8733 | 0.01
10.0312 | 8.8734 | 2.1344 | 2.2016 | 3.6719 | 3.4031 | 8.0078 | 5.8062 | 18.9047 | 21.1062 | 29.114 | 34.9203 | 10.0412 | 8.8734 | 2.1344 | 2.2016 | 3.6719 | 3.4031 | 8.0078 | 5.8062 | 18.9147 | 21.1162 | 29.124 | 34.9303 | 0.01
1.8924 | 7.11 | 1.8631 | 1.7946 | 2.3154 | 2.5892 | 5.9731 | 4.1785 | 9.0025 | 10.7971 | 16.7702 | 20.9487 | 1.9024 | 7.11 | 1.8631 | 1.7946 | 2.3154 | 2.5892 | 5.9731 | 4.1785 | 9.0125 | 10.8071 | 16.7802 | 20.9587 | 0.01
16.936 | 10.3695 | 2.3645 | 2.5468 | 4.8227 | 4.0936 | 9.734 | 7.1872 | 27.3054 | 29.8522 | 39.5862 | 46.7734 | 16.946 | 10.3695 | 2.3645 | 2.5468 | 4.8227 | 4.0936 | 9.734 | 7.1872 | 27.3154 | 29.8622 | 39.5962 | 46.7834 | 0.01
7.2675 | 8.2746 | 2.0422 | 2.0634 | 3.2112 | 3.1267 | 7.3169 | 5.2535 | 15.5421 | 17.6055 | 24.9223 | 30.1758 | 7.2775 | 8.2746 | 2.0422 | 2.0634 | 3.2112 | 3.1267 | 7.3169 | 5.2535 | 15.5521 | 17.6155 | 24.9323 | 30.1858 | 0.01
5.0004 | 7.7834 | 1.9667 | 1.95 | 2.8334 | 2.9 | 6.7501 | 4.8001 | 12.7839 | 14.7339 | 21.484 | 26.2841 | 5.0104 | 7.7834 | 1.9667 | 1.95 | 2.8334 | 2.9 | 6.7501 | 4.8001 | 12.7939 | 14.7439 | 21.494 | 26.2941 | 0.01
8.22 | 8.481 | 2.074 | 2.111 | 3.37 | 3.222 | 7.555 | 5.444 | 16.7011 | 18.8121 | 26.3671 | 31.8111 | 8.23 | 8.481 | 2.074 | 2.111 | 3.37 | 3.222 | 7.555 | 5.444 | 16.7111 | 18.8221 | 26.3771 | 31.8211 | 0.01
15.5054 | 10.0595 | 2.3168 | 2.4753 | 4.5842 | 3.9505 | 9.3763 | 6.9011 | 25.5649 | 28.0401 | 37.4165 | 44.3175 | 15.5154 | 10.0595 | 2.3168 | 2.4753 | 4.5842 | 3.9505 | 9.3763 | 6.9011 | 25.5749 | 28.0501 | 37.4265 | 44.3275 | 0.01
1.1288 | 6.9446 | 1.8376 | 1.7564 | 2.1881 | 2.5129 | 5.7822 | 4.0258 | 8.0734 | 9.8299 | 15.6121 | 19.6378 | 1.1388 | 6.9446 | 1.8376 | 1.7564 | 2.1881 | 2.5129 | 5.7822 | 4.0258 | 8.0834 | 9.8399 | 15.6221 | 19.6478 | 0.01
0.42329 | 6.7917 | 1.8141 | 1.7212 | 2.0705 | 2.4423 | 5.6058 | 3.8847 | 7.215 | 8.9362 | 14.542 | 18.4267 | 0.43329 | 6.7917 | 1.8141 | 1.7212 | 2.0705 | 2.4423 | 5.6058 | 3.8847 | 7.225 | 8.9462 | 14.552 | 18.4367 | 0.01
6.5131 | 8.1112 | 2.0171 | 2.0257 | 3.0855 | 3.0513 | 7.1283 | 5.1026 | 14.6242 | 16.6499 | 23.7781 | 28.8807 | 6.5231 | 8.1112 | 2.0171 | 2.0257 | 3.0855 | 3.0513 | 7.1283 | 5.1026 | 14.6342 | 16.6599 | 23.7881 | 28.8907 | 0.01
-0.42709 | 6.6075 | 1.7858 | 1.6786 | 1.9288 | 2.3573 | 5.3932 | 3.7146 | 6.1804 | 7.859 | 13.2522 | 16.9668 | -0.41709 | 6.6075 | 1.7858 | 1.6786 | 1.9288 | 2.3573 | 5.3932 | 3.7146 | 6.1904 | 7.869 | 13.2622 | 16.9768 | 0.01
3.3855 | 7.4335 | 1.9129 | 1.8693 | 2.5643 | 2.7386 | 6.3464 | 4.4771 | 10.8191 | 12.6883 | 19.0347 | 23.5118 | 3.3955 | 7.4335 | 1.9129 | 1.8693 | 2.5643 | 2.7386 | 6.3464 | 4.4771 | 10.8291 | 12.6983 | 19.0447 | 23.5218 | 0.01
9.2592 | 8.7062 | 2.1086 | 2.163 | 3.5432 | 3.3259 | 7.8148 | 5.6518 | 17.9653 | 20.1283 | 27.9431 | 33.5949 | 9.2692 | 8.7062 | 2.1086 | 2.163 | 3.5432 | 3.3259 | 7.8148 | 5.6518 | 17.9753 | 20.1383 | 27.9531 | 33.6049 | 0.01
0.34898 | 6.7756 | 1.8116 | 1.7174 | 2.0582 | 2.4349 | 5.5872 | 3.8698 | 7.1246 | 8.842 | 14.4293 | 18.2991 | 0.35898 | 6.7756 | 1.8116 | 1.7174 | 2.0582 | 2.4349 | 5.5872 | 3.8698 | 7.1346 | 8.852 | 14.4393 | 18.3091 | 0.01
14.8692 | 9.9217 | 2.2956 | 2.4435 | 4.4782 | 3.8869 | 9.2173 | 6.7738 | 24.7908 | 27.2343 | 36.4516 | 43.2254 | 14.8792 | 9.9217 | 2.2956 | 2.4435 | 4.4782 | 3.8869 | 9.2173 | 6.7738 | 24.8008 | 27.2443 | 36.4616 | 43.2354 | 0.01
14.2324 | 9.7837 | 2.2744 | 2.4116 | 4.3721 | 3.8232 | 9.0581 | 6.6465 | 24.0161 | 26.4277 | 35.4858 | 42.1323 | 14.2424 | 9.7837 | 2.2744 | 2.4116 | 4.3721 | 3.8232 | 9.0581 | 6.6465 | 24.0261 | 26.4377 | 35.4958 | 42.1423 | 0.01
-3.7799 | 5.881 | 1.674 | 1.511 | 1.37 | 2.022 | 4.555 | 3.044 | 2.1012 | 3.6122 | 8.1672 | 11.2112 | -3.7699 | 5.881 | 1.674 | 1.511 | 1.37 | 2.022 | 4.555 | 3.044 | 2.1112 | 3.6222 | 8.1772 | 11.2212 | 0.01
5.3413 | 7.8573 | 1.978 | 1.9671 | 2.8902 | 2.9341 | 6.8353 | 4.8683 | 13.1986 | 15.1657 | 22.001 | 26.8693 | 5.3513 | 7.8573 | 1.978 | 1.9671 | 2.8902 | 2.9341 | 6.8353 | 4.8683 | 13.2086 | 15.1757 | 22.011 | 26.8793 | 0.01
13.6643 | 9.6606 | 2.2555 | 2.3832 | 4.2774 | 3.7664 | 8.9161 | 6.5329 | 23.3249 | 25.7081 | 34.6242 | 41.157 | 13.6743 | 9.6606 | 2.2555 | 2.3832 | 4.2774 | 3.7664 | 8.9161 | 6.5329 | 23.3349 | 25.7181 | 34.6342 | 41.167 | 0.01
17.2063 | 10.428 | 2.3735 | 2.5603 | 4.8677 | 4.1206 | 9.8016 | 7.2413 | 27.6343 | 30.1946 | 39.9962 | 47.2374 | 17.2163 | 10.428 | 2.3735 | 2.5603 | 4.8677 | 4.1206 | 9.8016 | 7.2413 | 27.6443 | 30.2046 | 40.0062 | 47.2474 | 0.01
8.2493 | 8.4874 | 2.075 | 2.1125 | 3.3749 | 3.2249 | 7.5623 | 5.4499 | 16.7367 | 18.8491 | 26.4115 | 31.8613 | 8.2593 | 8.4874 | 2.075 | 2.1125 | 3.3749 | 3.2249 | 7.5623 | 5.4499 | 16.7467 | 18.8591 | 26.4215 | 31.8713 | 0.01
5.4441 | 7.8796 | 1.9815 | 1.9722 | 2.9074 | 2.9444 | 6.861 | 4.8888 | 13.3237 | 15.2959 | 22.1569 | 27.0457 | 5.4541 | 7.8796 | 1.9815 | 1.9722 | 2.9074 | 2.9444 | 6.861 | 4.8888 | 13.3337 | 15.3059 | 22.1669 | 27.0557 | 0.01
0.4585 | 6.7993 | 1.8153 | 1.7229 | 2.0764 | 2.4459 | 5.6146 | 3.8917 | 7.2578 | 8.9808 | 14.5954 | 18.4871 | 0.4685 | 6.7993 | 1.8153 | 1.7229 | 2.0764 | 2.4459 | 5.6146 | 3.8917 | 7.2678 | 8.9908 | 14.6054 | 18.4971 | 0.01
-0.038013 | 6.6918 | 1.7987 | 1.6981 | 1.9937 | 2.3962 | 5.4905 | 3.7924 | 6.6538 | 8.3519 | 13.8423 | 17.6347 | -0.028013 | 6.6918 | 1.7987 | 1.6981 | 1.9937 | 2.3962 | 5.4905 | 3.7924 | 6.6638 | 8.3619 | 13.8523 | 17.6447 | 0.01
11.8839 | 9.2749 | 2.1961 | 2.2942 | 3.9807 | 3.5884 | 8.471 | 6.1768 | 21.1588 | 23.453 | 31.924 | 38.1008 | 11.8939 | 9.2749 | 2.1961 | 2.2942 | 3.9807 | 3.5884 | 8.471 | 6.1768 | 21.1688 | 23.463 | 31.934 | 38.1108 | 0.01
-3.1106 | 6.026 | 1.6963 | 1.5445 | 1.4816 | 2.0889 | 4.7224 | 3.1779 | 2.9155 | 4.4599 | 9.1823 | 12.3602 | -3.1006 | 6.026 | 1.6963 | 1.5445 | 1.4816 | 2.0889 | 4.7224 | 3.1779 | 2.9255 | 4.4699 | 9.1923 | 12.3702 | 0.01
2.154 | 7.1667 | 1.8718 | 1.8077 | 2.359 | 2.6154 | 6.0385 | 4.2308 | 9.3207 | 11.1284 | 17.1669 | 21.3977 | 2.164 | 7.1667 | 1.8718 | 1.8077 | 2.359 | 2.6154 | 6.0385 | 4.2308 | 9.3307 | 11.1384 | 17.1769 | 21.4077 | 0.01
7.67 | 8.3618 | 2.0557 | 2.0835 | 3.2783 | 3.167 | 7.4175 | 5.334 | 16.0319 | 18.1154 | 25.5329 | 30.8669 | 7.68 | 8.3618 | 2.0557 | 2.0835 | 3.2783 | 3.167 | 7.4175 | 5.334 | 16.0419 | 18.1254 | 25.5429 | 30.8769 | 0.01
15.8604 | 10.1364 | 2.3287 | 2.493 | 4.6434 | 3.986 | 9.4651 | 6.9721 | 25.9968 | 28.4898 | 37.9549 | 44.927 | 15.8704 | 10.1364 | 2.3287 | 2.493 | 4.6434 | 3.986 | 9.4651 | 6.9721 | 26.0068 | 28.4998 | 37.9649 | 44.937 | 0.01
-1.0877 | 6.4643 | 1.7637 | 1.6456 | 1.8187 | 2.2912 | 5.2281 | 3.5825 | 5.3766 | 7.0222 | 12.2503 | 15.8327 | -1.0777 | 6.4643 | 1.7637 | 1.6456 | 1.8187 | 2.2912 | 5.2281 | 3.5825 | 5.3866 | 7.0322 | 12.2603 | 15.8427 | 0.01
9.5656 | 8.7725 | 2.1189 | 2.1783 | 3.5943 | 3.3566 | 7.8914 | 5.7131 | 18.3381 | 20.5164 | 28.4078 | 34.1209 | 9.5756 | 8.7725 | 2.1189 | 2.1783 | 3.5943 | 3.3566 | 7.8914 | 5.7131 | 18.3481 | 20.5264 | 28.4178 | 34.1309 | 0.01
5.2751 | 7.8429 | 1.9758 | 1.9638 | 2.8792 | 2.9275 | 6.8188 | 4.855 | 13.1181 | 15.0818 | 21.9006 | 26.7557 | 5.2851 | 7.8429 | 1.9758 | 1.9638 | 2.8792 | 2.9275 | 6.8188 | 4.855 | 13.1281 | 15.0918 | 21.9106 | 26.7657 | 0.01
4.8547 | 7.7519 | 1.9618 | 1.9427 | 2.8091 | 2.8855 | 6.7137 | 4.7709 | 12.6066 | 14.5493 | 21.263 | 26.0339 | 4.8647 | 7.7519 | 1.9618 | 1.9427 | 2.8091 | 2.8855 | 6.7137 | 4.7709 | 12.6166 | 14.5593 | 21.273 | 26.0439 | 0.01
4.1225 | 7.5932 | 1.9374 | 1.9061 | 2.6871 | 2.8123 | 6.5306 | 4.6245 | 11.7157 | 13.6219 | 20.1525 | 24.777 | 4.1325 | 7.5932 | 1.9374 | 1.9061 | 2.6871 | 2.8123 | 6.5306 | 4.6245 | 11.7257 | 13.6319 | 20.1625 | 24.787 | 0.01
0.12817 | 6.7278 | 1.8043 | 1.7064 | 2.0214 | 2.4128 | 5.532 | 3.8256 | 6.8559 | 8.5623 | 14.0944 | 17.92 | 0.13817 | 6.7278 | 1.8043 | 1.7064 | 2.0214 | 2.4128 | 5.532 | 3.8256 | 6.8659 | 8.5723 | 14.1044 | 17.93 | 0.01
3.1497 | 7.3824 | 1.905 | 1.8575 | 2.525 | 2.715 | 6.2874 | 4.4299 | 10.5322 | 12.3897 | 18.6771 | 23.107 | 3.1597 | 7.3824 | 1.905 | 1.8575 | 2.525 | 2.715 | 6.2874 | 4.4299 | 10.5422 | 12.3997 | 18.6871 | 23.117 | 0.01
0.004088 | 6.7009 | 1.8001 | 1.7002 | 2.0007 | 2.4004 | 5.501 | 3.8008 | 6.705 | 8.4052 | 13.9062 | 17.707 | 0.014088 | 6.7009 | 1.8001 | 1.7002 | 2.0007 | 2.4004 | 5.501 | 3.8008 | 6.715 | 8.4152 | 13.9162 | 17.717 | 0.01
2.664 | 7.2772 | 1.8888 | 1.8332 | 2.444 | 2.6664 | 6.166 | 4.3328 | 9.9412 | 11.7744 | 17.9403 | 22.2731 | 2.674 | 7.2772 | 1.8888 | 1.8332 | 2.444 | 2.6664 | 6.166 | 4.3328 | 9.9512 | 11.7844 | 17.9503 | 22.2831 | 0.01
16.3601 | 10.2447 | 2.3453 | 2.518 | 4.7267 | 4.036 | 9.59 | 7.072 | 26.6047 | 29.1227 | 38.7127 | 45.7848 | 16.3701 | 10.2447 | 2.3453 | 2.518 | 4.7267 | 4.036 | 9.59 | 7.072 | 26.6147 | 29.1327 | 38.7227 | 45.7948 | 0.01
1.1157 | 6.9417 | 1.8372 | 1.7558 | 2.186 | 2.5116 | 5.7789 | 4.0231 | 8.0575 | 9.8133 | 15.5922 | 19.6153 | 1.1257 | 6.9417 | 1.8372 | 1.7558 | 2.186 | 2.5116 | 5.7789 | 4.0231 | 8.0675 | 9.8233 | 15.6022 | 19.6253 | 0.01
8.3578 | 8.5109 | 2.0786 | 2.1179 | 3.393 | 3.2358 | 7.5894 | 5.4716 | 16.8686 | 18.9865 | 26.576 | 32.0475 | 8.3678 | 8.5109 | 2.0786 | 2.1179 | 3.393 | 3.2358 | 7.5894 | 5.4716 | 16.8786 | 18.9965 | 26.586 | 32.0575 | 0.01
-3.237 | 5.9986 | 1.6921 | 1.5381 | 1.4605 | 2.0763 | 4.6907 | 3.1526 | 2.7616 | 4.2998 | 8.9905 | 12.1431 | -3.227 | 5.9986 | 1.6921 | 1.5381 | 1.4605 | 2.0763 | 4.6907 | 3.1526 | 2.7716 | 4.3098 | 9.0005 | 12.1531 | 0.01
3.8189 | 7.5274 | 1.9273 | 1.8909 | 2.6365 | 2.7819 | 6.4547 | 4.5638 | 11.3463 | 13.2373 | 19.692 | 24.2558 | 3.8289 | 7.5274 | 1.9273 | 1.8909 | 2.6365 | 2.7819 | 6.4547 | 4.5638 | 11.3563 | 13.2473 | 19.702 | 24.2658 | 0.01
9.7219 | 8.8064 | 2.1241 | 2.1861 | 3.6203 | 3.3722 | 7.9305 | 5.7444 | 18.5283 | 20.7144 | 28.6448 | 34.3892 | 9.7319 | 8.8064 | 2.1241 | 2.1861 | 3.6203 | 3.3722 | 7.9305 | 5.7444 | 18.5383 | 20.7244 | 28.6548 | 34.3992 | 0.01
8.9915 | 8.6482 | 2.0997 | 2.1496 | 3.4986 | 3.2992 | 7.7479 | 5.5983 | 17.6397 | 19.7893 | 27.5372 | 33.1355 | 9.0015 | 8.6482 | 2.0997 | 2.1496 | 3.4986 | 3.2992 | 7.7479 | 5.5983 | 17.6497 | 19.7993 | 27.5472 | 33.1455 | 0.01
-3.6954 | 5.8993 | 1.6768 | 1.5152 | 1.3841 | 2.0305 | 4.5762 | 3.0609 | 2.2039 | 3.7192 | 8.2953 | 11.3562 | -3.6854 | 5.8993 | 1.6768 | 1.5152 | 1.3841 | 2.0305 | 4.5762 | 3.0609 | 2.2139 | 3.7292 | 8.3053 | 11.3662 | 0.01
10.0738 | 8.8827 | 2.1358 | 2.2037 | 3.679 | 3.4074 | 8.0185 | 5.8148 | 18.9565 | 21.1602 | 29.1787 | 34.9934 | 10.0838 | 8.8827 | 2.1358 | 2.2037 | 3.679 | 3.4074 | 8.0185 | 5.8148 | 18.9665 | 21.1702 | 29.1887 | 35.0034 | 0.01
0.046038 | 6.71 | 1.8015 | 1.7023 | 2.0077 | 2.4046 | 5.5115 | 3.8092 | 6.756 | 8.4583 | 13.9698 | 17.779 | 0.056038 | 6.71 | 1.8015 | 1.7023 | 2.0077 | 2.4046 | 5.5115 | 3.8092 | 6.766 | 8.4683 | 13.9798 | 17.789 | 0.01
11.9431 | 9.2877 | 2.1981 | 2.2972 | 3.9905 | 3.5943 | 8.4858 | 6.1886 | 21.2308 | 23.528 | 32.0138 | 38.2024 | 11.9531 | 9.2877 | 2.1981 | 2.2972 | 3.9905 | 3.5943 | 8.4858 | 6.1886 | 21.2408 | 23.538 | 32.0238 | 38.2124 | 0.01
10.2351 | 8.9176 | 2.1412 | 2.2118 | 3.7058 | 3.4235 | 8.0588 | 5.847 | 19.1527 | 21.3645 | 29.4232 | 35.2703 | 10.2451 | 8.9176 | 2.1412 | 2.2118 | 3.7058 | 3.4235 | 8.0588 | 5.847 | 19.1627 | 21.3745 | 29.4332 | 35.2803 | 0.01
16.0073 | 10.1682 | 2.3336 | 2.5004 | 4.6679 | 4.0007 | 9.5018 | 7.0015 | 26.1755 | 28.6759 | 38.1777 | 45.1791 | 16.0173 | 10.1682 | 2.3336 | 2.5004 | 4.6679 | 4.0007 | 9.5018 | 7.0015 | 26.1855 | 28.6859 | 38.1877 | 45.1891 | 0.01
11.2117 | 9.1292 | 2.1737 | 2.2606 | 3.8686 | 3.5212 | 8.3029 | 6.0423 | 20.3409 | 22.6015 | 30.9044 | 36.9468 | 11.2217 | 9.1292 | 2.1737 | 2.2606 | 3.8686 | 3.5212 | 8.3029 | 6.0423 | 20.3509 | 22.6115 | 30.9144 | 36.9568 | 0.01
0.7651 | 6.8658 | 1.8255 | 1.7383 | 2.1275 | 2.4765 | 5.6913 | 3.953 | 7.6309 | 9.3691 | 15.0604 | 19.0134 | 0.7751 | 6.8658 | 1.8255 | 1.7383 | 2.1275 | 2.4765 | 5.6913 | 3.953 | 7.6409 | 9.3791 | 15.0704 | 19.0234 | 0.01
-2.5424 | 6.1491 | 1.7153 | 1.5729 | 1.5763 | 2.1458 | 4.8644 | 3.2915 | 3.6068 | 5.1796 | 10.044 | 13.3356 | -2.5324 | 6.1491 | 1.7153 | 1.5729 | 1.5763 | 2.1458 | 4.8644 | 3.2915 | 3.6168 | 5.1896 | 10.054 | 13.3456 | 0.01
6.6128 | 8.1328 | 2.0204 | 2.0306 | 3.1021 | 3.0613 | 7.1532 | 5.1226 | 14.7456 | 16.7763 | 23.9295 | 29.052 | 6.6228 | 8.1328 | 2.0204 | 2.0306 | 3.1021 | 3.0613 | 7.1532 | 5.1226 | 14.7556 | 16.7863 | 23.9395 | 29.062 | 0.01
-0.13011 | 6.6718 | 1.7957 | 1.6935 | 1.9783 | 2.387 | 5.4675 | 3.774 | 6.5417 | 8.2352 | 13.7027 | 17.4766 | -0.12011 | 6.6718 | 1.7957 | 1.6935 | 1.9783 | 2.387 | 5.4675 | 3.774 | 6.5517 | 8.2452 | 13.7127 | 17.4866 | 0.01
2.5146 | 7.2448 | 1.8838 | 1.8257 | 2.4191 | 2.6515 | 6.1286 | 4.3029 | 9.7594 | 11.5851 | 17.7138 | 22.0167 | 2.5246 | 7.2448 | 1.8838 | 1.8257 | 2.4191 | 2.6515 | 6.1286 | 4.3029 | 9.7694 | 11.5951 | 17.7238 | 22.0267 | 0.01
14.496 | 9.8408 | 2.2832 | 2.4248 | 4.416 | 3.8496 | 9.124 | 6.6992 | 24.3368 | 26.7616 | 35.8856 | 42.5848 | 14.506 | 9.8408 | 2.2832 | 2.4248 | 4.416 | 3.8496 | 9.124 | 6.6992 | 24.3468 | 26.7716 | 35.8956 | 42.5948 | 0.01
6.3767 | 8.0816 | 2.0126 | 2.0188 | 3.0628 | 3.0377 | 7.0942 | 5.0753 | 14.4583 | 16.4771 | 23.5713 | 28.6466 | 6.3867 | 8.0816 | 2.0126 | 2.0188 | 3.0628 | 3.0377 | 7.0942 | 5.0753 | 14.4683 | 16.4871 | 23.5813 | 28.6566 | 0.01
-0.66363 | 6.5562 | 1.7779 | 1.6668 | 1.8894 | 2.3336 | 5.3341 | 3.6673 | 5.8926 | 7.5594 | 12.8935 | 16.5608 | -0.65363 | 6.5562 | 1.7779 | 1.6668 | 1.8894 | 2.3336 | 5.3341 | 3.6673 | 5.9026 | 7.5694 | 12.9035 | 16.5708 | 0.01
6.6236 | 8.1351 | 2.0208 | 2.0312 | 3.1039 | 3.0624 | 7.1559 | 5.1247 | 14.7587 | 16.7899 | 23.9458 | 29.0705 | 6.6336 | 8.1351 | 2.0208 | 2.0312 | 3.1039 | 3.0624 | 7.1559 | 5.1247 | 14.7687 | 16.7999 | 23.9558 | 29.0805 | 0.01
-1.4404 | 6.3879 | 1.752 | 1.628 | 1.7599 | 2.256 | 5.1399 | 3.5119 | 4.9476 | 6.5755 | 11.7155 | 15.2274 | -1.4304 | 6.3879 | 1.752 | 1.628 | 1.7599 | 2.256 | 5.1399 | 3.5119 | 4.9576 | 6.5855 | 11.7255 | 15.2374 | 0.01
3.8707 | 7.5386 | 1.929 | 1.8935 | 2.6451 | 2.7871 | 6.4677 | 4.5741 | 11.4093 | 13.3029 | 19.7705 | 24.3447 | 3.8807 | 7.5386 | 1.929 | 1.8935 | 2.6451 | 2.7871 | 6.4677 | 4.5741 | 11.4193 | 13.3129 | 19.7805 | 24.3547 | 0.01
-11.3239 | 4.2465 | 1.4225 | 1.1338 | 0.11268 | 1.2676 | 2.669 | 1.5352 | -7.0774 | -5.9436 | -3.2746 | -1.7394 | -11.3139 | 4.2465 | 1.4225 | 1.1338 | 0.11268 | 1.2676 | 2.669 | 1.5352 | -7.0674 | -5.9336 | -3.2646 | -1.7294 | 0.01
8.374 | 8.5144 | 2.0791 | 2.1187 | 3.3957 | 3.2374 | 7.5935 | 5.4748 | 16.8884 | 19.0071 | 26.6006 | 32.0754 | 8.384 | 8.5144 | 2.0791 | 2.1187 | 3.3957 | 3.2374 | 7.5935 | 5.4748 | 16.8984 | 19.0171 | 26.6106 | 32.0854 | 0.01
12.9704 | 9.5102 | 2.2323 | 2.3485 | 4.1617 | 3.697 | 8.7426 | 6.3941 | 22.4806 | 24.8291 | 33.5717 | 39.9658 | 12.9804 | 9.5102 | 2.2323 | 2.3485 | 4.1617 | 3.697 | 8.7426 | 6.3941 | 22.4906 | 24.8391 | 33.5817 | 39.9758 | 0.01
1.7719 | 7.0839 | 1.8591 | 1.7886 | 2.2953 | 2.5772 | 5.943 | 4.1544 | 8.8558 | 10.6444 | 16.5874 | 20.7418 | 1.7819 | 7.0839 | 1.8591 | 1.7886 | 2.2953 | 2.5772 | 5.943 | 4.1544 | 8.8658 | 10.6544 | 16.5974 | 20.7518 | 0.01
-0.26064 | 6.6435 | 1.7913 | 1.687 | 1.9566 | 2.3739 | 5.4348 | 3.7479 | 6.3829 | 8.0699 | 13.5047 | 17.2526 | -0.25064 | 6.6435 | 1.7913 | 1.687 | 1.9566 | 2.3739 | 5.4348 | 3.7479 | 6.3929 | 8.0799 | 13.5147 | 17.2626 | 0.01
8.9346 | 8.6358 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7336 | 5.5869 | 17.5704 | 19.7171 | 27.4507 | 33.0376 | 8.9446 | 8.6358 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7336 | 5.5869 | 17.5804 | 19.7271 | 27.4607 | 33.0476 | 0.01
8.9889 | 8.6476 | 2.0996 | 2.1494 | 3.4981 | 3.2989 | 7.7472 | 5.5978 | 17.6365 | 19.7859 | 27.5332 | 33.1309 | 8.9989 | 8.6476 | 2.0996 | 2.1494 | 3.4981 | 3.2989 | 7.7472 | 5.5978 | 17.6465 | 19.7959 | 27.5432 | 33.1409 | 0.01
5.2835 | 7.8448 | 1.9761 | 1.9642 | 2.8806 | 2.9284 | 6.8209 | 4.8567 | 13.1283 | 15.0925 | 21.9133 | 26.77 | 5.2935 | 7.8448 | 1.9761 | 1.9642 | 2.8806 | 2.9284 | 6.8209 | 4.8567 | 13.1383 | 15.1025 | 21.9233 | 26.78 | 0.01
9.4524 | 8.748 | 2.1151 | 2.1726 | 3.5754 | 3.3452 | 7.8631 | 5.6905 | 18.2004 | 20.373 | 28.2361 | 33.9266 | 9.4624 | 8.748 | 2.1151 | 2.1726 | 3.5754 | 3.3452 | 7.8631 | 5.6905 | 18.2104 | 20.383 | 28.2461 | 33.9366 | 0.01
12.1174 | 9.3254 | 2.2039 | 2.3059 | 4.0196 | 3.6117 | 8.5294 | 6.2235 | 21.4429 | 23.7487 | 32.2781 | 38.5016 | 12.1274 | 9.3254 | 2.2039 | 2.3059 | 4.0196 | 3.6117 | 8.5294 | 6.2235 | 21.4529 | 23.7587 | 32.2881 | 38.5116 | 0.01
2.5021 | 7.2421 | 1.8834 | 1.8251 | 2.417 | 2.6502 | 6.1255 | 4.3004 | 9.7443 | 11.5694 | 17.6949 | 21.9953 | 2.5121 | 7.2421 | 1.8834 | 1.8251 | 2.417 | 2.6502 | 6.1255 | 4.3004 | 9.7543 | 11.5794 | 17.7049 | 22.0053 | 0.01
0.91537 | 6.8983 | 1.8305 | 1.7458 | 2.1526 | 2.4915 | 5.7288 | 3.9831 | 7.8137 | 9.5595 | 15.2883 | 19.2714 | 0.92537 | 6.8983 | 1.8305 | 1.7458 | 2.1526 | 2.4915 | 5.7288 | 3.9831 | 7.8237 | 9.5695 | 15.2983 | 19.2814 | 0.01
-1.7202 | 6.3273 | 1.7427 | 1.614 | 1.7133 | 2.228 | 5.07 | 3.456 | 4.6071 | 6.2211 | 11.2911 | 14.7471 | -1.7102 | 6.3273 | 1.7427 | 1.614 | 1.7133 | 2.228 | 5.07 | 3.456 | 4.6171 | 6.2311 | 11.3011 | 14.7571 | 0.01
7.3217 | 8.2864 | 2.0441 | 2.0661 | 3.2203 | 3.1322 | 7.3304 | 5.2643 | 15.608 | 17.6741 | 25.0046 | 30.2689 | 7.3317 | 8.2864 | 2.0441 | 2.0661 | 3.2203 | 3.1322 | 7.3304 | 5.2643 | 15.618 | 17.6841 | 25.0146 | 30.2789 | 0.01
7.9757 | 8.4281 | 2.0659 | 2.0988 | 3.3293 | 3.1976 | 7.4939 | 5.3951 | 16.4037 | 18.5025 | 25.9965 | 31.3916 | 7.9857 | 8.4281 | 2.0659 | 2.0988 | 3.3293 | 3.1976 | 7.4939 | 5.3951 | 16.4137 | 18.5125 | 26.0065 | 31.4016 | 0.01
-2.8082 | 6.0916 | 1.7064 | 1.5596 | 1.532 | 2.1192 | 4.798 | 3.2384 | 3.2834 | 4.843 | 9.6409 | 12.8793 | -2.7982 | 6.0916 | 1.7064 | 1.5596 | 1.532 | 2.1192 | 4.798 | 3.2384 | 3.2934 | 4.853 | 9.6509 | 12.8893 | 0.01
-1.3037 | 6.4175 | 1.7565 | 1.6348 | 1.7827 | 2.2696 | 5.1741 | 3.5393 | 5.1139 | 6.7487 | 11.9228 | 15.462 | -1.2937 | 6.4175 | 1.7565 | 1.6348 | 1.7827 | 2.2696 | 5.1741 | 3.5393 | 5.1239 | 6.7587 | 11.9328 | 15.472 | 0.01
0.17091 | 6.737 | 1.8057 | 1.7085 | 2.0285 | 2.4171 | 5.5427 | 3.8342 | 6.9079 | 8.6165 | 14.1592 | 17.9934 | 0.18091 | 6.737 | 1.8057 | 1.7085 | 2.0285 | 2.4171 | 5.5427 | 3.8342 | 6.9179 | 8.6265 | 14.1692 | 18.0034 | 0.01
-7.6486 | 5.0428 | 1.545 | 1.3176 | 0.72523 | 1.6351 | 3.5878 | 2.2703 | -2.6058 | -1.2883 | 2.2996 | 4.5698 | -7.6386 | 5.0428 | 1.545 | 1.3176 | 0.72523 | 1.6351 | 3.5878 | 2.2703 | -2.5958 | -1.2783 | 2.3096 | 4.5798 | 0.01
7.5446 | 8.3347 | 2.0515 | 2.0772 | 3.2574 | 3.1545 | 7.3862 | 5.3089 | 15.8793 | 17.9565 | 25.3427 | 30.6516 | 7.5546 | 8.3347 | 2.0515 | 2.0772 | 3.2574 | 3.1545 | 7.3862 | 5.3089 | 15.8893 | 17.9665 | 25.3527 | 30.6616 | 0.01
9.7001 | 8.8017 | 2.1233 | 2.185 | 3.6167 | 3.37 | 7.925 | 5.74 | 18.5018 | 20.6869 | 28.6119 | 34.3519 | 9.7101 | 8.8017 | 2.1233 | 2.185 | 3.6167 | 3.37 | 7.925 | 5.74 | 18.5118 | 20.6969 | 28.6219 | 34.3619 | 0.01
8.0543 | 8.4451 | 2.0685 | 2.1027 | 3.3424 | 3.2054 | 7.5136 | 5.4109 | 16.4994 | 18.6021 | 26.1157 | 31.5266 | 8.0643 | 8.4451 | 2.0685 | 2.1027 | 3.3424 | 3.2054 | 7.5136 | 5.4109 | 16.5094 | 18.6121 | 26.1257 | 31.5366 | 0.01
-1.2755 | 6.4236 | 1.7575 | 1.6362 | 1.7874 | 2.2725 | 5.1811 | 3.5449 | 5.1482 | 6.7844 | 11.9655 | 15.5104 | -1.2655 | 6.4236 | 1.7575 | 1.6362 | 1.7874 | 2.2725 | 5.1811 | 3.5449 | 5.1582 | 6.7944 | 11.9755 | 15.5204 | 0.01
1.6532 | 7.0582 | 1.8551 | 1.7827 | 2.2755 | 2.5653 | 5.9133 | 4.1306 | 8.7114 | 10.494 | 16.4073 | 20.538 | 1.6632 | 7.0582 | 1.8551 | 1.7827 | 2.2755 | 2.5653 | 5.9133 | 4.1306 | 8.7214 | 10.504 | 16.4173 | 20.548 | 0.01
4.0014 | 7.567 | 1.9334 | 1.9001 | 2.6669 | 2.8001 | 6.5004 | 4.6003 | 11.5684 | 13.4685 | 19.9689 | 24.5692 | 4.0114 | 7.567 | 1.9334 | 1.9001 | 2.6669 | 2.8001 | 6.5004 | 4.6003 | 11.5784 | 13.4785 | 19.9789 | 24.5792 | 0.01
9.7211 | 8.8062 | 2.124 | 2.1861 | 3.6202 | 3.3721 | 7.9303 | 5.7442 | 18.5273 | 20.7134 | 28.6437 | 34.3879 | 9.7311 | 8.8062 | 2.124 | 2.1861 | 3.6202 | 3.3721 | 7.9303 | 5.7442 | 18.5373 | 20.7234 | 28.6537 | 34.3979 | 0.01
18.4405 | 10.6954 | 2.4147 | 2.622 | 5.0734 | 4.2441 | 10.1101 | 7.4881 | 29.136 | 31.758 | 41.8681 | 49.3562 | 18.4505 | 10.6954 | 2.4147 | 2.622 | 5.0734 | 4.2441 | 10.1101 | 7.4881 | 29.146 | 31.768 | 41.8781 | 49.3662 | 0.01
6.7586 | 8.1644 | 2.0253 | 2.0379 | 3.1264 | 3.0759 | 7.1896 | 5.1517 | 14.9229 | 16.9609 | 24.1505 | 29.3022 | 6.7686 | 8.1644 | 2.0253 | 2.0379 | 3.1264 | 3.0759 | 7.1896 | 5.1517 | 14.9329 | 16.9709 | 24.1605 | 29.3122 | 0.01
17.2651 | 10.4408 | 2.3755 | 2.5633 | 4.8775 | 4.1265 | 9.8163 | 7.253 | 27.7059 | 30.2692 | 40.0855 | 47.3385 | 17.2751 | 10.4408 | 2.3755 | 2.5633 | 4.8775 | 4.1265 | 9.8163 | 7.253 | 27.7159 | 30.2792 | 40.0955 | 47.3485 | 0.01
-4.1978 | 5.7905 | 1.6601 | 1.4901 | 1.3004 | 1.9802 | 4.4506 | 2.9604 | 1.5927 | 3.0828 | 7.5334 | 10.4938 | -4.1878 | 5.7905 | 1.6601 | 1.4901 | 1.3004 | 1.9802 | 4.4506 | 2.9604 | 1.6027 | 3.0928 | 7.5434 | 10.5038 | 0.01
7.4729 | 8.3191 | 2.0491 | 2.0736 | 3.2455 | 3.1473 | 7.3682 | 5.2946 | 15.7921 | 17.8657 | 25.2339 | 30.5285 | 7.4829 | 8.3191 | 2.0491 | 2.0736 | 3.2455 | 3.1473 | 7.3682 | 5.2946 | 15.8021 | 17.8757 | 25.2439 | 30.5385 | 0.01
-0.8847 | 6.5083 | 1.7705 | 1.6558 | 1.8525 | 2.3115 | 5.2788 | 3.6231 | 5.6236 | 7.2794 | 12.5582 | 16.1813 | -0.8747 | 6.5083 | 1.7705 | 1.6558 | 1.8525 | 2.3115 | 5.2788 | 3.6231 | 5.6336 | 7.2894 | 12.5682 | 16.1913 | 0.01
14.5788 | 9.8587 | 2.286 | 2.4289 | 4.4298 | 3.8579 | 9.1447 | 6.7158 | 24.4376 | 26.8665 | 36.0112 | 42.727 | 14.5888 | 9.8587 | 2.286 | 2.4289 | 4.4298 | 3.8579 | 9.1447 | 6.7158 | 24.4476 | 26.8765 | 36.0212 | 42.737 | 0.01
0.12537 | 6.7272 | 1.8042 | 1.7063 | 2.0209 | 2.4125 | 5.5313 | 3.8251 | 6.8525 | 8.5588 | 14.0901 | 17.9152 | 0.13537 | 6.7272 | 1.8042 | 1.7063 | 2.0209 | 2.4125 | 5.5313 | 3.8251 | 6.8625 | 8.5688 | 14.1001 | 17.9252 | 0.01
4.2245 | 7.6153 | 1.9408 | 1.9112 | 2.7041 | 2.8224 | 6.5561 | 4.6449 | 11.8398 | 13.751 | 20.3071 | 24.952 | 4.2345 | 7.6153 | 1.9408 | 1.9112 | 2.7041 | 2.8224 | 6.5561 | 4.6449 | 11.8498 | 13.761 | 20.3171 | 24.962 | 0.01
15.0219 | 9.9547 | 2.3007 | 2.4511 | 4.5036 | 3.9022 | 9.2555 | 6.8044 | 24.9766 | 27.4277 | 36.6832 | 43.4875 | 15.0319 | 9.9547 | 2.3007 | 2.4511 | 4.5036 | 3.9022 | 9.2555 | 6.8044 | 24.9866 | 27.4377 | 36.6932 | 43.4975 | 0.01
-2.3623 | 6.1882 | 1.7213 | 1.5819 | 1.6063 | 2.1638 | 4.9094 | 3.3275 | 3.8258 | 5.4077 | 10.3171 | 13.6446 | -2.3523 | 6.1882 | 1.7213 | 1.5819 | 1.6063 | 2.1638 | 4.9094 | 3.3275 | 3.8358 | 5.4177 | 10.3271 | 13.6546 | 0.01
-0.42982 | 6.6069 | 1.7857 | 1.6785 | 1.9284 | 2.357 | 5.3925 | 3.714 | 6.177 | 7.8556 | 13.2481 | 16.9621 | -0.41982 | 6.6069 | 1.7857 | 1.6785 | 1.9284 | 2.357 | 5.3925 | 3.714 | 6.187 | 7.8656 | 13.2581 | 16.9721 | 0.01
7.7003 | 8.3684 | 2.0567 | 2.085 | 3.2834 | 3.17 | 7.4251 | 5.3401 | 16.0687 | 18.1537 | 25.5788 | 30.9188 | 7.7103 | 8.3684 | 2.0567 | 2.085 | 3.2834 | 3.17 | 7.4251 | 5.3401 | 16.0787 | 18.1637 | 25.5888 | 30.9288 | 0.01
5.0337 | 7.7906 | 1.9678 | 1.9517 | 2.839 | 2.9034 | 6.7584 | 4.8067 | 12.8244 | 14.776 | 21.5345 | 26.3412 | 5.0437 | 7.7906 | 1.9678 | 1.9517 | 2.839 | 2.9034 | 6.7584 | 4.8067 | 12.8344 | 14.786 | 21.5445 | 26.3512 | 0.01
3.2793 | 7.4105 | 1.9093 | 1.864 | 2.5465 | 2.7279 | 6.3198 | 4.4559 | 10.6898 | 12.5538 | 18.8736 | 23.3294 | 3.2893 | 7.4105 | 1.9093 | 1.864 | 2.5465 | 2.7279 | 6.3198 | 4.4559 | 10.6998 | 12.5638 | 18.8836 | 23.3394 | 0.01
-0.40881 | 6.6114 | 1.7864 | 1.6796 | 1.9319 | 2.3591 | 5.3978 | 3.7182 | 6.2026 | 7.8822 | 13.28 | 16.9982 | -0.39881 | 6.6114 | 1.7864 | 1.6796 | 1.9319 | 2.3591 | 5.3978 | 3.7182 | 6.2126 | 7.8922 | 13.29 | 17.0082 | 0.01
12.3703 | 9.3802 | 2.2123 | 2.3185 | 4.0617 | 3.637 | 8.5926 | 6.2741 | 21.7505 | 24.069 | 32.6616 | 38.9356 | 12.3803 | 9.3802 | 2.2123 | 2.3185 | 4.0617 | 3.637 | 8.5926 | 6.2741 | 21.7605 | 24.079 | 32.6716 | 38.9456 | 0.01
9.2318 | 8.7002 | 2.1077 | 2.1616 | 3.5386 | 3.3232 | 7.8079 | 5.6464 | 17.932 | 20.0936 | 27.9015 | 33.5479 | 9.2418 | 8.7002 | 2.1077 | 2.1616 | 3.5386 | 3.3232 | 7.8079 | 5.6464 | 17.942 | 20.1036 | 27.9115 | 33.5579 | 0.01
9.9205 | 8.8494 | 2.1307 | 2.196 | 3.6534 | 3.392 | 7.9801 | 5.7841 | 18.7699 | 20.9659 | 28.946 | 34.7301 | 9.9305 | 8.8494 | 2.1307 | 2.196 | 3.6534 | 3.392 | 7.9801 | 5.7841 | 18.7799 | 20.9759 | 28.956 | 34.7401 | 0.01
12.8623 | 9.4868 | 2.2287 | 2.3431 | 4.1437 | 3.6862 | 8.7156 | 6.3725 | 22.3491 | 24.6922 | 33.4078 | 39.7802 | 12.8723 | 9.4868 | 2.2287 | 2.3431 | 4.1437 | 3.6862 | 8.7156 | 6.3725 | 22.3591 | 24.7022 | 33.4178 | 39.7902 | 0.01
-2.6898 | 6.1172 | 1.7103 | 1.5655 | 1.5517 | 2.131 | 4.8276 | 3.262 | 3.4274 | 4.9929 | 9.8205 | 13.0825 | -2.6798 | 6.1172 | 1.7103 | 1.5655 | 1.5517 | 2.131 | 4.8276 | 3.262 | 3.4374 | 5.0029 | 9.8305 | 13.0925 | 0.01
10.976 | 9.0781 | 2.1659 | 2.2488 | 3.8293 | 3.4976 | 8.244 | 5.9952 | 20.0542 | 22.303 | 30.547 | 36.5422 | 10.986 | 9.0781 | 2.1659 | 2.2488 | 3.8293 | 3.4976 | 8.244 | 5.9952 | 20.0642 | 22.313 | 30.557 | 36.5522 | 0.01
6.1885 | 8.0408 | 2.0063 | 2.0094 | 3.0314 | 3.0189 | 7.0471 | 5.0377 | 14.2294 | 16.2388 | 23.2859 | 28.3237 | 6.1985 | 8.0408 | 2.0063 | 2.0094 | 3.0314 | 3.0189 | 7.0471 | 5.0377 | 14.2394 | 16.2488 | 23.2959 | 28.3337 | 0.01
-0.0097864 | 6.6979 | 1.7997 | 1.6995 | 1.9984 | 2.399 | 5.4976 | 3.798 | 6.6881 | 8.3876 | 13.8852 | 17.6832 | 0.00021362 | 6.6979 | 1.7997 | 1.6995 | 1.9984 | 2.399 | 5.4976 | 3.798 | 6.6981 | 8.3976 | 13.8952 | 17.6932 | 0.01
13.3212 | 9.5863 | 2.244 | 2.3661 | 4.2202 | 3.7321 | 8.8303 | 6.4642 | 22.9074 | 25.2735 | 34.1038 | 40.568 | 13.3312 | 9.5863 | 2.244 | 2.3661 | 4.2202 | 3.7321 | 8.8303 | 6.4642 | 22.9174 | 25.2835 | 34.1138 | 40.578 | 0.01
-0.72099 | 6.5438 | 1.776 | 1.664 | 1.8798 | 2.3279 | 5.3198 | 3.6558 | 5.8228 | 7.4867 | 12.8065 | 16.4623 | -0.71099 | 6.5438 | 1.776 | 1.664 | 1.8798 | 2.3279 | 5.3198 | 3.6558 | 5.8328 | 7.4967 | 12.8165 | 16.4723 | 0.01
-0.99952 | 6.4834 | 1.7667 | 1.65 | 1.8334 | 2.3 | 5.2501 | 3.6001 | 5.4839 | 7.1339 | 12.3841 | 15.9842 | -0.98952 | 6.4834 | 1.7667 | 1.65 | 1.8334 | 2.3 | 5.2501 | 3.6001 | 5.4939 | 7.1439 | 12.3941 | 15.9942 | 0.01
1.5168 | 7.0286 | 1.8506 | 1.7758 | 2.2528 | 2.5517 | 5.8792 | 4.1034 | 8.5455 | 10.3213 | 16.2005 | 20.3039 | 1.5268 | 7.0286 | 1.8506 | 1.7758 | 2.2528 | 2.5517 | 5.8792 | 4.1034 | 8.5555 | 10.3313 | 16.2105 | 20.3139 | 0.01
-0.58033 | 6.5743 | 1.7807 | 1.671 | 1.9033 | 2.342 | 5.3549 | 3.6839 | 5.9939 | 7.6649 | 13.0198 | 16.7038 | -0.57033 | 6.5743 | 1.7807 | 1.671 | 1.9033 | 2.342 | 5.3549 | 3.6839 | 6.0039 | 7.6749 | 13.0298 | 16.7138 | 0.01
0.17113 | 6.7371 | 1.8057 | 1.7086 | 2.0285 | 2.4171 | 5.5428 | 3.8342 | 6.9082 | 8.6168 | 14.1595 | 17.9938 | 0.18113 | 6.7371 | 1.8057 | 1.7086 | 2.0285 | 2.4171 | 5.5428 | 3.8342 | 6.9182 | 8.6268 | 14.1695 | 18.0038 | 0.01
0.074319 | 6.7161 | 1.8025 | 1.7037 | 2.0124 | 2.4074 | 5.5186 | 3.8149 | 6.7904 | 8.4941 | 14.0127 | 17.8276 | 0.084319 | 6.7161 | 1.8025 | 1.7037 | 2.0124 | 2.4074 | 5.5186 | 3.8149 | 6.8004 | 8.5041 | 14.0227 | 17.8376 | 0.01
1.085 | 6.9351 | 1.8362 | 1.7543 | 2.1808 | 2.5085 | 5.7713 | 4.017 | 8.0201 | 9.7744 | 15.5456 | 19.5626 | 1.095 | 6.9351 | 1.8362 | 1.7543 | 2.1808 | 2.5085 | 5.7713 | 4.017 | 8.0301 | 9.7844 | 15.5556 | 19.5726 | 0.01
-3.1212 | 6.0237 | 1.696 | 1.5439 | 1.4798 | 2.0879 | 4.7197 | 3.1758 | 2.9025 | 4.4464 | 9.1661 | 12.3419 | -3.1112 | 6.0237 | 1.696 | 1.5439 | 1.4798 | 2.0879 | 4.7197 | 3.1758 | 2.9125 | 4.4564 | 9.1761 | 12.3519 | 0.01
6.0895 | 8.0194 | 2.003 | 2.0045 | 3.0149 | 3.009 | 7.0224 | 5.0179 | 14.1089 | 16.1134 | 23.1357 | 28.1536 | 6.0995 | 8.0194 | 2.003 | 2.0045 | 3.0149 | 3.009 | 7.0224 | 5.0179 | 14.1189 | 16.1234 | 23.1457 | 28.1636 | 0.01
6.2141 | 8.0464 | 2.0071 | 2.0107 | 3.0357 | 3.0214 | 7.0535 | 5.0428 | 14.2605 | 16.2712 | 23.3247 | 28.3676 | 6.2241 | 8.0464 | 2.0071 | 2.0107 | 3.0357 | 3.0214 | 7.0535 | 5.0428 | 14.2705 | 16.2812 | 23.3347 | 28.3776 | 0.01
9.4624 | 8.7502 | 2.1154 | 2.1731 | 3.5771 | 3.3462 | 7.8656 | 5.6925 | 18.2126 | 20.3857 | 28.2513 | 33.9437 | 9.4724 | 8.7502 | 2.1154 | 2.1731 | 3.5771 | 3.3462 | 7.8656 | 5.6925 | 18.2226 | 20.3957 | 28.2613 | 33.9537 | 0.01
2.7991 | 7.3065 | 1.8933 | 1.84 | 2.4665 | 2.6799 | 6.1998 | 4.3598 | 10.1056 | 11.9456 | 18.1454 | 22.5052 | 2.8091 | 7.3065 | 1.8933 | 1.84 | 2.4665 | 2.6799 | 6.1998 | 4.3598 | 10.1156 | 11.9556 | 18.1554 | 22.5152 | 0.01
0.57475 | 6.8245 | 1.8192 | 1.7287 | 2.0958 | 2.4575 | 5.6437 | 3.915 | 7.3993 | 9.128 | 14.7717 | 18.6867 | 0.58475 | 6.8245 | 1.8192 | 1.7287 | 2.0958 | 2.4575 | 5.6437 | 3.915 | 7.4093 | 9.138 | 14.7817 | 18.6967 | 0.01
9.4411 | 8.7456 | 2.1147 | 2.1721 | 3.5735 | 3.3441 | 7.8603 | 5.6882 | 18.1866 | 20.3587 | 28.219 | 33.9072 | 9.4511 | 8.7456 | 2.1147 | 2.1721 | 3.5735 | 3.3441 | 7.8603 | 5.6882 | 18.1966 | 20.3687 | 28.229 | 33.9172 | 0.01
-1.3256 | 6.4128 | 1.7558 | 1.6337 | 1.7791 | 2.2674 | 5.1686 | 3.5349 | 5.0872 | 6.7209 | 11.8896 | 15.4244 | -1.3156 | 6.4128 | 1.7558 | 1.6337 | 1.7791 | 2.2674 | 5.1686 | 3.5349 | 5.0972 | 6.7309 | 11.8996 | 15.4344 | 0.01
6.3785 | 8.082 | 2.0126 | 2.0189 | 3.0631 | 3.0379 | 7.0946 | 5.0757 | 14.4605 | 16.4794 | 23.5741 | 28.6498 | 6.3885 | 8.082 | 2.0126 | 2.0189 | 3.0631 | 3.0379 | 7.0946 | 5.0757 | 14.4705 | 16.4894 | 23.5841 | 28.6598 | 0.01
1.0149 | 6.9199 | 1.8338 | 1.7507 | 2.1692 | 2.5015 | 5.7537 | 4.003 | 7.9348 | 9.6856 | 15.4393 | 19.4423 | 1.0249 | 6.9199 | 1.8338 | 1.7507 | 2.1692 | 2.5015 | 5.7537 | 4.003 | 7.9448 | 9.6956 | 15.4493 | 19.4523 | 0.01
3.1071 | 7.3732 | 1.9036 | 1.8554 | 2.5178 | 2.7107 | 6.2768 | 4.4214 | 10.4803 | 12.3356 | 18.6124 | 23.0338 | 3.1171 | 7.3732 | 1.9036 | 1.8554 | 2.5178 | 2.7107 | 6.2768 | 4.4214 | 10.4903 | 12.3456 | 18.6224 | 23.0438 | 0.01
8.6083 | 8.5651 | 2.0869 | 2.1304 | 3.4347 | 3.2608 | 7.6521 | 5.5217 | 17.1734 | 19.3038 | 26.9559 | 32.4776 | 8.6183 | 8.5651 | 2.0869 | 2.1304 | 3.4347 | 3.2608 | 7.6521 | 5.5217 | 17.1834 | 19.3138 | 26.9659 | 32.4876 | 0.01
-7.3979 | 5.0971 | 1.5534 | 1.3301 | 0.76701 | 1.6602 | 3.6505 | 2.3204 | -2.3008 | -0.97073 | 2.6798 | 5.0002 | -7.3879 | 5.0971 | 1.5534 | 1.3301 | 0.76701 | 1.6602 | 3.6505 | 2.3204 | -2.2908 | -0.96073 | 2.6898 | 5.0102 | 0.01
9.1391 | 8.6801 | 2.1046 | 2.157 | 3.5232 | 3.3139 | 7.7848 | 5.6278 | 17.8192 | 19.9762 | 27.7609 | 33.3887 | 9.1491 | 8.6801 | 2.1046 | 2.157 | 3.5232 | 3.3139 | 7.7848 | 5.6278 | 17.8292 | 19.9862 | 27.7709 | 33.3987 | 0.01
10.1185 | 8.8923 | 2.1373 | 2.2059 | 3.6864 | 3.4118 | 8.0296 | 5.8237 | 19.0108 | 21.2168 | 29.2464 | 35.0701 | 10.1285 | 8.8923 | 2.1373 | 2.2059 | 3.6864 | 3.4118 | 8.0296 | 5.8237 | 19.0208 | 21.2268 | 29.2564 | 35.0801 | 0.01
8.8895 | 8.6261 | 2.0963 | 2.1445 | 3.4816 | 3.289 | 7.7224 | 5.5779 | 17.5156 | 19.6601 | 27.3825 | 32.9604 | 8.8995 | 8.6261 | 2.0963 | 2.1445 | 3.4816 | 3.289 | 7.7224 | 5.5779 | 17.5256 | 19.6701 | 27.3925 | 32.9704 | 0.01
18.1174 | 10.6254 | 2.4039 | 2.6059 | 5.0196 | 4.2117 | 10.0293 | 7.4235 | 28.7428 | 31.3487 | 41.378 | 48.8015 | 18.1274 | 10.6254 | 2.4039 | 2.6059 | 5.0196 | 4.2117 | 10.0293 | 7.4235 | 28.7528 | 31.3587 | 41.388 | 48.8115 | 0.01
-4.172 | 5.7961 | 1.6609 | 1.4914 | 1.3047 | 1.9828 | 4.457 | 2.9656 | 1.6241 | 3.1155 | 7.5725 | 10.5381 | -4.162 | 5.7961 | 1.6609 | 1.4914 | 1.3047 | 1.9828 | 4.457 | 2.9656 | 1.6341 | 3.1255 | 7.5825 | 10.5481 | 0.01
4.7866 | 7.7371 | 1.9596 | 1.9393 | 2.7978 | 2.8787 | 6.6966 | 4.7573 | 12.5236 | 14.463 | 21.1596 | 25.9169 | 4.7966 | 7.7371 | 1.9596 | 1.9393 | 2.7978 | 2.8787 | 6.6966 | 4.7573 | 12.5336 | 14.473 | 21.1696 | 25.9269 | 0.01
8.5519 | 8.5529 | 2.0851 | 2.1276 | 3.4253 | 3.2552 | 7.638 | 5.5104 | 17.1048 | 19.2324 | 26.8704 | 32.3807 | 8.5619 | 8.5529 | 2.0851 | 2.1276 | 3.4253 | 3.2552 | 7.638 | 5.5104 | 17.1148 | 19.2424 | 26.8804 | 32.3907 | 0.01
6.8119 | 8.1759 | 2.0271 | 2.0406 | 3.1353 | 3.0812 | 7.203 | 5.1624 | 14.9878 | 17.0284 | 24.2313 | 29.3937 | 6.8219 | 8.1759 | 2.0271 | 2.0406 | 3.1353 | 3.0812 | 7.203 | 5.1624 | 14.9978 | 17.0384 | 24.2413 | 29.4037 | 0.01
-7.8754 | 4.9937 | 1.5375 | 1.3062 | 0.68743 | 1.6125 | 3.5311 | 2.2249 | -2.8818 | -1.5755 | 1.9556 | 4.1805 | -7.8654 | 4.9937 | 1.5375 | 1.3062 | 0.68743 | 1.6125 | 3.5311 | 2.2249 | -2.8718 | -1.5655 | 1.9656 | 4.1905 | 0.01
3.4751 | 7.4529 | 1.9158 | 1.8738 | 2.5792 | 2.7475 | 6.3688 | 4.495 | 10.9281 | 12.8018 | 19.1706 | 23.6656 | 3.4851 | 7.4529 | 1.9158 | 1.8738 | 2.5792 | 2.7475 | 6.3688 | 4.495 | 10.9381 | 12.8118 | 19.1806 | 23.6756 | 0.01
-3.9303 | 5.8484 | 1.669 | 1.5035 | 1.345 | 2.007 | 4.5174 | 3.0139 | 1.9181 | 3.4216 | 7.9391 | 10.953 | -3.9203 | 5.8484 | 1.669 | 1.5035 | 1.345 | 2.007 | 4.5174 | 3.0139 | 1.9281 | 3.4316 | 7.9491 | 10.963 | 0.01
11.6169 | 9.217 | 2.1872 | 2.2808 | 3.9362 | 3.5617 | 8.4042 | 6.1234 | 20.8339 | 23.1148 | 31.519 | 37.6424 | 11.6269 | 9.217 | 2.1872 | 2.2808 | 3.9362 | 3.5617 | 8.4042 | 6.1234 | 20.8439 | 23.1248 | 31.529 | 37.6524 | 0.01
6.6067 | 8.1315 | 2.0202 | 2.0303 | 3.1011 | 3.0607 | 7.1517 | 5.1213 | 14.7382 | 16.7685 | 23.9202 | 29.0415 | 6.6167 | 8.1315 | 2.0202 | 2.0303 | 3.1011 | 3.0607 | 7.1517 | 5.1213 | 14.7482 | 16.7785 | 23.9302 | 29.0515 | 0.01
3.6787 | 7.4971 | 1.9226 | 1.8839 | 2.6131 | 2.7679 | 6.4197 | 4.5357 | 11.1758 | 13.0597 | 19.4794 | 24.0151 | 3.6887 | 7.4971 | 1.9226 | 1.8839 | 2.6131 | 2.7679 | 6.4197 | 4.5357 | 11.1858 | 13.0697 | 19.4894 | 24.0251 | 0.01
10.0022 | 8.8671 | 2.1334 | 2.2001 | 3.667 | 3.4002 | 8.0005 | 5.8004 | 18.8693 | 21.0694 | 29.07 | 34.8704 | 10.0122 | 8.8671 | 2.1334 | 2.2001 | 3.667 | 3.4002 | 8.0005 | 5.8004 | 18.8793 | 21.0794 | 29.08 | 34.8804 | 0.01
2.8576 | 7.3192 | 1.8953 | 1.8429 | 2.4763 | 2.6858 | 6.2144 | 4.3715 | 10.1768 | 12.0197 | 18.2341 | 22.6056 | 2.8676 | 7.3192 | 1.8953 | 1.8429 | 2.4763 | 2.6858 | 6.2144 | 4.3715 | 10.1868 | 12.0297 | 18.2441 | 22.6156 | 0.01
-5.7356 | 5.4573 | 1.6088 | 1.4132 | 1.0441 | 1.8264 | 4.0661 | 2.6529 | -0.2783 | 1.1349 | 5.201 | 7.8539 | -5.7256 | 5.4573 | 1.6088 | 1.4132 | 1.0441 | 1.8264 | 4.0661 | 2.6529 | -0.2683 | 1.1449 | 5.211 | 7.8639 | 0.01
-0.24152 | 6.6477 | 1.7919 | 1.6879 | 1.9597 | 2.3758 | 5.4396 | 3.7517 | 6.4062 | 8.0941 | 13.5337 | 17.2854 | -0.23152 | 6.6477 | 1.7919 | 1.6879 | 1.9597 | 2.3758 | 5.4396 | 3.7517 | 6.4162 | 8.1041 | 13.5437 | 17.2954 | 0.01
-1.1184 | 6.4577 | 1.7627 | 1.6441 | 1.8136 | 2.2882 | 5.2204 | 3.5763 | 5.3393 | 6.9834 | 12.2038 | 15.7801 | -1.1084 | 6.4577 | 1.7627 | 1.6441 | 1.8136 | 2.2882 | 5.2204 | 3.5763 | 5.3493 | 6.9934 | 12.2138 | 15.7901 | 0.01
9.8841 | 8.8416 | 1.6146 | 2.1942 | 3.6474 | 3.3884 | 7.971 | 5.7768 | 18.7257 | 20.9199 | 28.891 | 34.6678 | 9.8941 | 8.8416 | 1.6146 | 2.1942 | 3.6474 | 3.3884 | 7.971 | 5.7768 | 18.7357 | 20.9299 | 28.901 | 34.6778 | 0.01
-5.5634 | 5.4946 | 1.9328 | 1.4218 | 1.0728 | 1.8437 | 4.1091 | 2.6873 | -0.068833 | 1.353 | 5.4621 | 8.1495 | -5.5534 | 5.4946 | 1.9328 | 1.4218 | 1.0728 | 1.8437 | 4.1091 | 2.6873 | -0.058833 | 1.363 | 5.4721 | 8.1595 | 0.01
3.9837 | 7.5631 | 2.3331 | 1.8992 | 2.6639 | 2.7984 | 6.4959 | 4.5967 | 11.5468 | 13.446 | 19.9419 | 24.5386 | 3.9937 | 7.5631 | 2.3331 | 1.8992 | 2.6639 | 2.7984 | 6.4959 | 4.5967 | 11.5568 | 13.456 | 19.9519 | 24.5486 | 0.01
15.9941 | 10.1654 | 1.7859 | 2.4997 | 4.6657 | 3.9994 | 9.4985 | 6.9988 | 26.1595 | 28.6592 | 38.1577 | 45.1566 | 16.0041 | 10.1654 | 1.7859 | 2.4997 | 4.6657 | 3.9994 | 9.4985 | 6.9988 | 26.1695 | 28.6692 | 38.1677 | 45.1666 | 0.01
-0.42261 | 6.6084 | 1.794 | 1.6789 | 1.9296 | 2.3577 | 5.3943 | 3.7155 | 6.1858 | 7.8647 | 13.259 | 16.9745 | -0.41261 | 6.6084 | 1.794 | 1.6789 | 1.9296 | 2.3577 | 5.3943 | 3.7155 | 6.1958 | 7.8747 | 13.269 | 16.9845 | 0.01
-0.18131 | 6.6607 | 1.9908 | 1.6909 | 1.9698 | 2.3819 | 5.4547 | 3.7637 | 6.4794 | 8.1703 | 13.625 | 17.3887 | -0.17131 | 6.6607 | 1.9908 | 1.6909 | 1.9698 | 2.3819 | 5.4547 | 3.7637 | 6.4894 | 8.1803 | 13.635 | 17.3987 | 0.01
5.7226 | 7.9399 | 2.0474 | 1.9861 | 2.9538 | 2.9723 | 6.9306 | 4.9445 | 13.6625 | 15.6486 | 22.5792 | 27.5238 | 5.7326 | 7.9399 | 2.0474 | 1.9861 | 2.9538 | 2.9723 | 6.9306 | 4.9445 | 13.6725 | 15.6586 | 22.5892 | 27.5338 | 0.01
7.4208 | 8.3078 | 2.0177 | 2.071 | 3.2368 | 3.1421 | 7.3552 | 5.2842 | 15.7286 | 17.7997 | 25.1549 | 30.439 | 7.4308 | 8.3078 | 2.0177 | 2.071 | 3.2368 | 3.1421 | 7.3552 | 5.2842 | 15.7386 | 17.8097 | 25.1649 | 30.449 | 0.01
6.5317 | 8.1152 | 2.2316 | 2.0266 | 3.0886 | 3.0532 | 7.1329 | 5.1063 | 14.6469 | 16.6735 | 23.8064 | 28.9127 | 6.5417 | 8.1152 | 2.2316 | 2.0266 | 3.0886 | 3.0532 | 7.1329 | 5.1063 | 14.6569 | 16.6835 | 23.8164 | 28.9227 | 0.01
12.9487 | 9.5056 | 2.2484 | 2.3474 | 4.1581 | 3.6949 | 8.7372 | 6.3897 | 22.4543 | 24.8017 | 33.5389 | 39.9286 | 12.9587 | 9.5056 | 2.2484 | 2.3474 | 4.1581 | 3.6949 | 8.7372 | 6.3897 | 22.4643 | 24.8117 | 33.5489 | 39.9386 | 0.01
13.4512 | 9.6144 | 1.8607 | 2.3726 | 4.2419 | 3.7451 | 8.8628 | 6.4902 | 23.0656 | 25.4382 | 34.301 | 40.7912 | 13.4612 | 9.6144 | 1.8607 | 2.3726 | 4.2419 | 3.7451 | 8.8628 | 6.4902 | 23.0756 | 25.4482 | 34.311 | 40.8012 | 0.01
1.8217 | 7.0947 | 2.0947 | 1.7911 | 2.3036 | 2.5822 | 5.9554 | 4.1643 | 8.9164 | 10.7075 | 16.6629 | 20.8272 | 1.8317 | 7.0947 | 2.0947 | 1.7911 | 2.3036 | 2.5822 | 5.9554 | 4.1643 | 8.9264 | 10.7175 | 16.6729 | 20.8372 | 0.01
8.8397 | 8.6153 | 1.8922 | 2.142 | 3.4733 | 3.284 | 7.7099 | 5.5679 | 17.455 | 19.597 | 27.3069 | 32.8748 | 8.8497 | 8.6153 | 1.8922 | 2.142 | 3.4733 | 3.284 | 7.7099 | 5.5679 | 17.465 | 19.607 | 27.3169 | 32.8848 | 0.01
2.7666 | 7.2994 | 2.0757 | 1.8383 | 2.4611 | 2.6767 | 6.1916 | 4.3533 | 10.066 | 11.9043 | 18.0959 | 22.4493 | 2.7766 | 7.2994 | 2.0757 | 1.8383 | 2.4611 | 2.6767 | 6.1916 | 4.3533 | 10.076 | 11.9143 | 18.1059 | 22.4593 | 0.01
8.2722 | 8.4923 | 1.8633 | 2.1136 | 3.3787 | 3.2272 | 7.568 | 5.4544 | 16.7645 | 18.8781 | 26.4461 | 31.9006 | 8.2822 | 8.4923 | 1.8633 | 2.1136 | 3.3787 | 3.2272 | 7.568 | 5.4544 | 16.7745 | 18.8881 | 26.4561 | 31.9106 | 0.01
1.8989 | 7.1114 | 2.0766 | 1.7949 | 2.3165 | 2.5899 | 5.9747 | 4.1798 | 9.0103 | 10.8052 | 16.7799 | 20.9597 | 1.9089 | 7.1114 | 2.0766 | 1.7949 | 2.3165 | 2.5899 | 5.9747 | 4.1798 | 9.0203 | 10.8152 | 16.7899 | 20.9697 | 0.01
8.2977 | 8.4978 | 2.1503 | 2.1149 | 3.3829 | 3.2298 | 7.5744 | 5.4595 | 16.7955 | 18.9104 | 26.4848 | 31.9444 | 8.3077 | 8.4978 | 2.1503 | 2.1149 | 3.3829 | 3.2298 | 7.5744 | 5.4595 | 16.8055 | 18.9204 | 26.4948 | 31.9544 | 0.01
10.5101 | 8.9772 | 2.0598 | 2.2255 | 3.7517 | 3.451 | 8.1275 | 5.902 | 19.4873 | 21.7128 | 29.8404 | 35.7424 | 10.5201 | 8.9772 | 2.0598 | 2.2255 | 3.7517 | 3.451 | 8.1275 | 5.902 | 19.4973 | 21.7228 | 29.8504 | 35.7524 | 0.01
7.7932 | 8.3885 | 2.4427 | 2.0897 | 3.2989 | 3.1793 | 7.4483 | 5.3586 | 16.1817 | 18.2714 | 25.7197 | 31.0784 | 7.8032 | 8.3885 | 2.4427 | 2.0897 | 3.2989 | 3.1793 | 7.4483 | 5.3586 | 16.1917 | 18.2814 | 25.7297 | 31.0884 | 0.01
19.2796 | 10.8773 | 1.7714 | 2.664 | 5.2133 | 4.328 | 10.3199 | 7.6559 | 30.1569 | 32.8209 | 43.1408 | 50.7967 | 19.2896 | 10.8773 | 1.7714 | 2.664 | 5.2133 | 4.328 | 10.3199 | 7.6559 | 30.1669 | 32.8309 | 43.1508 | 50.8067 | 0.01
-0.85792 | 6.5141 | 1.9787 | 1.6571 | 1.857 | 2.3142 | 5.2855 | 3.6284 | 5.6562 | 7.3133 | 12.5988 | 16.2272 | -0.84792 | 6.5141 | 1.9787 | 1.6571 | 1.857 | 2.3142 | 5.2855 | 3.6284 | 5.6662 | 7.3233 | 12.6088 | 16.2372 | 0.01
5.3618 | 7.8617 | 2.1086 | 1.9681 | 2.8936 | 2.9362 | 6.8405 | 4.8724 | 13.2236 | 15.1917 | 22.0321 | 26.9045 | 5.3718 | 7.8617 | 2.1086 | 1.9681 | 2.8936 | 2.9362 | 6.8405 | 4.8724 | 13.2336 | 15.2017 | 22.0421 | 26.9145 | 0.01
9.2577 | 8.7058 | 2.1426 | 2.1629 | 3.543 | 3.3258 | 7.8144 | 5.6515 | 17.9635 | 20.1264 | 27.9408 | 33.5924 | 9.2677 | 8.7058 | 2.1426 | 2.1629 | 3.543 | 3.3258 | 7.8144 | 5.6515 | 17.9735 | 20.1364 | 27.9508 | 33.6024 | 0.01
10.2787 | 8.9271 | 2.2081 | 2.2139 | 3.7131 | 3.4279 | 8.0697 | 5.8557 | 19.2058 | 21.4197 | 29.4894 | 35.3451 | 10.2887 | 8.9271 | 2.2081 | 2.2139 | 3.7131 | 3.4279 | 8.0697 | 5.8557 | 19.2158 | 21.4297 | 29.4994 | 35.3551 | 0.01
12.2433 | 9.3527 | 1.7133 | 2.3122 | 4.0406 | 3.6243 | 8.5608 | 6.2487 | 21.5961 | 23.9082 | 32.4691 | 38.7177 | 12.2533 | 9.3527 | 1.7133 | 2.3122 | 4.0406 | 3.6243 | 8.5608 | 6.2487 | 21.6061 | 23.9182 | 32.4791 | 38.7277 | 0.01
-2.602 | 6.1362 | 2.0305 | 1.5699 | 1.5663 | 2.1398 | 4.8495 | 3.2796 | 3.5343 | 5.1042 | 9.9537 | 13.2333 | -2.592 | 6.1362 | 2.0305 | 1.5699 | 1.5663 | 2.1398 | 4.8495 | 3.2796 | 3.5443 | 5.1142 | 9.9637 | 13.2433 | 0.01
6.9152 | 8.1983 | 1.9055 | 2.0458 | 3.1525 | 3.0915 | 7.2288 | 5.183 | 15.1135 | 17.1593 | 24.3881 | 29.5711 | 6.9252 | 8.1983 | 1.9055 | 2.0458 | 3.1525 | 3.0915 | 7.2288 | 5.183 | 15.1235 | 17.1693 | 24.3981 | 29.5811 | 0.01
3.1651 | 7.3858 | 2.0144 | 1.8583 | 2.5275 | 2.7165 | 6.2913 | 4.433 | 10.5509 | 12.4091 | 18.7004 | 23.1334 | 3.1751 | 7.3858 | 2.0144 | 1.8583 | 2.5275 | 2.7165 | 6.2913 | 4.433 | 10.5609 | 12.4191 | 18.7104 | 23.1434 | 0.01
6.4306 | 8.0933 | 1.864 | 2.0215 | 3.0718 | 3.0431 | 7.1076 | 5.0861 | 14.5239 | 16.5454 | 23.653 | 28.7391 | 6.4406 | 8.0933 | 1.864 | 2.0215 | 3.0718 | 3.0431 | 7.1076 | 5.0861 | 14.5339 | 16.5554 | 23.663 | 28.7491 | 0.01
1.919 | 7.1158 | 1.9736 | 1.7959 | 2.3198 | 2.5919 | 5.9797 | 4.1838 | 9.0347 | 10.8307 | 16.8104 | 20.9942 | 1.929 | 7.1158 | 1.9736 | 1.7959 | 2.3198 | 2.5919 | 5.9797 | 4.1838 | 9.0447 | 10.8407 | 16.8204 | 21.0042 | 0.01
5.2075 | 7.8283 | 1.9672 | 1.9604 | 2.8679 | 2.9207 | 6.8019 | 4.8415 | 13.0358 | 14.9962 | 21.798 | 26.6395 | 5.2175 | 7.8283 | 1.9672 | 1.9604 | 2.8679 | 2.9207 | 6.8019 | 4.8415 | 13.0458 | 15.0062 | 21.808 | 26.6495 | 0.01
5.0148 | 7.7865 | 1.9804 | 1.9507 | 2.8358 | 2.9015 | 6.7537 | 4.803 | 12.8013 | 14.7521 | 21.5058 | 26.3087 | 5.0248 | 7.7865 | 1.9804 | 1.9507 | 2.8358 | 2.9015 | 6.7537 | 4.803 | 12.8113 | 14.7621 | 21.5158 | 26.3187 | 0.01
5.4118 | 7.8725 | 1.82 | 1.9706 | 2.902 | 2.9412 | 6.8529 | 4.8824 | 13.2843 | 15.2549 | 22.1078 | 26.9902 | 5.4218 | 7.8725 | 1.82 | 1.9706 | 2.902 | 2.9412 | 6.8529 | 4.8824 | 13.2943 | 15.2649 | 22.1178 | 27.0002 | 0.01
0.60033 | 6.8301 | 2.1284 | 1.73 | 2.1001 | 2.46 | 5.6501 | 3.9201 | 7.4304 | 9.1604 | 14.8105 | 18.7306 | 0.61033 | 6.8301 | 2.1284 | 1.73 | 2.1001 | 2.46 | 5.6501 | 3.9201 | 7.4404 | 9.1704 | 14.8205 | 18.7406 | 0.01
9.8505 | 8.8343 | 1.9956 | 2.1925 | 3.6418 | 3.3851 | 7.9626 | 5.7701 | 18.6848 | 20.8773 | 28.84 | 34.6101 | 9.8605 | 8.8343 | 1.9956 | 2.1925 | 3.6418 | 3.3851 | 7.9626 | 5.7701 | 18.6948 | 20.8873 | 28.85 | 34.6201 | 0.01
5.8682 | 7.9714 | 1.8458 | 1.9934 | 2.978 | 2.9868 | 6.9671 | 4.9736 | 13.8396 | 15.8331 | 22.8001 | 27.7737 | 5.8782 | 7.9714 | 1.8458 | 1.9934 | 2.978 | 2.9868 | 6.9671 | 4.9736 | 13.8496 | 15.8431 | 22.8101 | 27.7837 | 0.01
1.3746 | 6.9978 | 2.3455 | 1.7687 | 2.2291 | 2.5375 | 5.8436 | 4.0749 | 8.3724 | 10.1411 | 15.9848 | 20.0597 | 1.3846 | 6.9978 | 2.3455 | 1.7687 | 2.2291 | 2.5375 | 5.8436 | 4.0749 | 8.3824 | 10.1511 | 15.9948 | 20.0697 | 0.01
16.3663 | 10.246 | 2.1493 | 2.5183 | 4.7277 | 4.0366 | 9.5916 | 7.0733 | 26.6123 | 29.1306 | 38.7222 | 45.7954 | 16.3763 | 10.246 | 2.1493 | 2.5183 | 4.7277 | 4.0366 | 9.5916 | 7.0733 | 26.6223 | 29.1406 | 38.7322 | 45.8054 | 0.01
10.4785 | 8.9703 | 2.2881 | 2.2239 | 3.7464 | 3.4479 | 8.1196 | 5.8957 | 19.4488 | 21.6728 | 29.7924 | 35.6881 | 10.4885 | 8.9703 | 2.2881 | 2.2239 | 3.7464 | 3.4479 | 8.1196 | 5.8957 | 19.4588 | 21.6828 | 29.8024 | 35.6981 | 0.01
14.6431 | 9.8727 | 2.1757 | 2.4322 | 4.4405 | 3.8643 | 9.1608 | 6.7286 | 24.5157 | 26.9479 | 36.1087 | 42.8373 | 14.6531 | 9.8727 | 2.1757 | 2.4322 | 4.4405 | 3.8643 | 9.1608 | 6.7286 | 24.5257 | 26.9579 | 36.1187 | 42.8473 | 0.01
11.2705 | 9.1419 | 1.6904 | 2.2635 | 3.8784 | 3.5271 | 8.3176 | 6.0541 | 20.4125 | 22.676 | 30.9936 | 37.0477 | 11.2805 | 9.1419 | 1.6904 | 2.2635 | 3.8784 | 3.5271 | 8.3176 | 6.0541 | 20.4225 | 22.686 | 31.0036 | 37.0577 | 0.01
-3.2871 | 5.9878 | 1.9339 | 1.5356 | 1.4522 | 2.0713 | 4.6782 | 3.1426 | 2.7008 | 4.2364 | 8.9146 | 12.0572 | -3.2771 | 5.9878 | 1.9339 | 1.5356 | 1.4522 | 2.0713 | 4.6782 | 3.1426 | 2.7108 | 4.2464 | 8.9246 | 12.0672 | 0.01
4.0163 | 7.5702 | 1.9562 | 1.9008 | 2.6694 | 2.8016 | 6.5041 | 4.6033 | 11.5865 | 13.4873 | 19.9914 | 24.5946 | 4.0263 | 7.5702 | 1.9562 | 1.9008 | 2.6694 | 2.8016 | 6.5041 | 4.6033 | 11.5965 | 13.4973 | 20.0014 | 24.6046 | 0.01
4.6864 | 7.7154 | 1.8488 | 1.9343 | 2.7811 | 2.8686 | 6.6716 | 4.7373 | 12.4018 | 14.3361 | 21.0078 | 25.745 | 4.6964 | 7.7154 | 1.8488 | 1.9343 | 2.7811 | 2.8686 | 6.6716 | 4.7373 | 12.4118 | 14.3461 | 21.0178 | 25.755 | 0.01
1.4634 | 7.0171 | 1.7742 | 1.7732 | 2.2439 | 3.5791 | 5.8659 | 4.0927 | 8.4805 | 10.2536 | 16.1195 | 20.2122 | 1.4734 | 7.0171 | 1.7742 | 1.7732 | 2.2439 | 3.5791 | 5.8659 | 4.0927 | 8.4905 | 10.2636 | 16.1295 | 20.2222 | 0.01
-0.77368 | 6.5324 | 2.193 | 1.6613 | 1.8711 | 1.6857 | 5.3066 | 3.6453 | 5.7587 | 7.42 | 12.7266 | 16.3718 | -0.76368 | 6.5324 | 2.193 | 1.6613 | 1.8711 | 1.6857 | 5.3066 | 3.6453 | 5.7687 | 7.43 | 12.7366 | 16.3818 | 0.01
11.7905 | 9.2546 | 1.5619 | 2.2895 | 3.9651 | 2.9119 | 8.4476 | 6.1581 | 21.0451 | 23.3346 | 31.7823 | 37.9404 | 11.8005 | 9.2546 | 1.5619 | 2.2895 | 3.9651 | 2.9119 | 8.4476 | 6.1581 | 21.0551 | 23.3446 | 31.7923 | 37.9504 | 0.01
-7.1426 | 5.1524 | 1.9706 | 1.3429 | 0.80957 | 3.4348 | 3.7144 | 2.3715 | -1.9901 | -0.64725 | 3.5972 | 5.9687 | -7.1326 | 5.1524 | 1.9706 | 1.3429 | 0.80957 | 3.4348 | 3.7144 | 2.3715 | -1.9801 | -0.63725 | 3.6072 | 5.9787 | 0.01
5.1192 | 7.8092 | 2.1449 | 1.956 | 2.8532 | 3.9823 | 6.7798 | 4.8238 | 12.9284 | 14.8844 | 21.7198 | 26.5437 | 5.1292 | 7.8092 | 2.1449 | 1.956 | 2.8532 | 3.9823 | 6.7798 | 4.8238 | 12.9384 | 14.8944 | 21.7298 | 26.5537 | 0.01
10.3484 | 8.9421 | 2.3274 | 2.2174 | 3.7247 | 2.3004 | 8.0871 | 5.8697 | 19.2905 | 21.5079 | 29.595 | 35.4647 | 10.3584 | 8.9421 | 2.3274 | 2.2174 | 3.7247 | 2.3004 | 8.0871 | 5.8697 | 19.3005 | 21.5179 | 29.605 | 35.4747 | 0.01
15.8226 | 10.1282 | 1.7668 | 2.4911 | 4.6371 | 1.4393 | 9.4556 | 6.9645 | 25.9508 | 28.442 | 37.8976 | 44.8621 | 15.8326 | 10.1282 | 1.7668 | 2.4911 | 4.6371 | 1.4393 | 9.4556 | 6.9645 | 25.9608 | 28.452 | 37.9076 | 44.8721 | 0.01
-0.99638 | 6.4841 | 1.4798 | 1.6502 | 1.8339 | 2.1554 | 5.2509 | 3.6007 | 5.4877 | 7.1379 | 12.3888 | 15.9895 | -0.98638 | 6.4841 | 1.4798 | 1.6502 | 1.8339 | 2.1554 | 5.2509 | 3.6007 | 5.4977 | 7.1479 | 12.3988 | 15.9995 | 0.01
-9.6069 | 4.6185 | 1.7185 | 1.2197 | 0.39885 | 2.5843 | 4.8886 | 1.8786 | -4.9884 | -3.7688 | 1.1198 | 2.9984 | -9.5969 | 4.6185 | 1.7185 | 1.2197 | 0.39885 | 2.5843 | 4.8886 | 1.8786 | -4.9784 | -3.7588 | 1.1298 | 3.0084 | 0.01
-2.4456 | 6.1701 | 1.8614 | 1.5777 | 1.5924 | 2.3528 | 5.9607 | 3.3109 | 3.7245 | 5.3022 | 11.2629 | 14.5738 | -2.4356 | 6.1701 | 1.8614 | 1.5777 | 1.5924 | 2.3528 | 5.9607 | 3.3109 | 3.7345 | 5.3122 | 11.2729 | 14.5838 | 0.01
1.8427 | 7.0993 | 1.7843 | 1.7921 | 2.3071 | 2.7307 | 5.3821 | 4.1685 | 8.942 | 10.7341 | 16.1162 | 20.2847 | 1.8527 | 7.0993 | 1.7843 | 1.7921 | 2.3071 | 2.7307 | 5.3821 | 4.1685 | 8.952 | 10.7441 | 16.1262 | 20.2947 | 0.01
-0.47175 | 6.5978 | 1.9102 | 1.6764 | 1.9214 | 2.5396 | 6.3268 | 3.7057 | 6.126 | 7.8025 | 14.1292 | 17.8349 | -0.46175 | 6.5978 | 1.9102 | 1.6764 | 1.9214 | 2.5396 | 6.3268 | 3.7057 | 6.136 | 7.8125 | 14.1392 | 17.8449 | 0.01
3.3071 | 7.4165 | 1.8465 | 1.7698 | 2.5512 | 2.4087 | 5.8491 | 4.4614 | 10.7236 | 12.4935 | 18.3426 | 22.804 | 3.3171 | 7.4165 | 1.8465 | 1.7698 | 2.5512 | 2.4087 | 5.8491 | 4.4614 | 10.7336 | 12.5035 | 18.3526 | 22.814 | 0.01
1.3965 | 7.0026 | 1.8029 | 1.7043 | 2.2327 | 3.3494 | 5.5217 | 4.0793 | 8.399 | 10.1034 | 15.6855 | 19.7648 | 1.4065 | 7.0026 | 1.8029 | 1.7043 | 2.2327 | 3.3494 | 5.5217 | 4.0793 | 8.409 | 10.1134 | 15.6955 | 19.7748 | 0.01
0.08672 | 6.7188 | 2.1165 | 2.1747 | 2.0145 | 3.9835 | 7.8734 | 3.8173 | 6.8055 | 8.9802 | 16.8536 | 20.671 | 0.09672 | 6.7188 | 2.1165 | 2.1747 | 2.0145 | 3.9835 | 7.8734 | 3.8173 | 6.8155 | 8.9902 | 16.8636 | 20.681 | 0.01
9.4938 | 8.757 | 2.3278 | 2.4917 | 3.5823 | 3.2911 | 9.4587 | 5.6988 | 18.2508 | 20.7425 | 30.2012 | 35.8999 | 9.5038 | 8.757 | 2.3278 | 2.4917 | 3.5823 | 3.2911 | 9.4587 | 5.6988 | 18.2608 | 20.7525 | 30.2112 | 35.9099 | 0.01
15.8348 | 10.1309 | 2.097 | 2.1455 | 4.6391 | 3.8318 | 7.7276 | 6.967 | 25.9657 | 28.1112 | 36.5822 | 43.5491 | 15.8448 | 10.1309 | 2.097 | 2.1455 | 4.6391 | 3.8318 | 7.7276 | 6.967 | 25.9757 | 28.1212 | 36.5922 | 43.5591 | 0.01
8.9106 | 8.6306 | 2.2773 | 2.4159 | 3.4851 | 2.4722 | 9.0796 | 5.5821 | 17.5412 | 19.9571 | 29.0368 | 34.6189 | 8.9206 | 8.6306 | 2.2773 | 2.4159 | 3.4851 | 2.4722 | 9.0796 | 5.5821 | 17.5512 | 19.9671 | 29.0468 | 34.6289 | 0.01
14.3184 | 9.8023 | 1.8241 | 1.7361 | 4.3864 | 3.1013 | 5.6806 | 6.6637 | 24.1208 | 25.8569 | 33.3446 | 40.0083 | 14.3284 | 9.8023 | 1.8241 | 1.7361 | 4.3864 | 3.1013 | 5.6806 | 6.6637 | 24.1308 | 25.8669 | 33.3546 | 40.0183 | 0.01
0.7224 | 6.8565 | 2.0338 | 2.0506 | 2.1204 | 4.3384 | 7.2532 | 3.9445 | 7.5789 | 9.6296 | 16.8828 | 20.8273 | 0.7324 | 6.8565 | 2.0338 | 2.0506 | 2.1204 | 4.3384 | 7.2532 | 3.9445 | 7.5889 | 9.6396 | 16.8928 | 20.8373 | 0.01
7.0128 | 8.2194 | 2.4461 | 2.6692 | 3.1688 | 1.3988 | 10.346 | 5.2026 | 15.2323 | 17.9015 | 28.2475 | 33.45 | 7.0228 | 8.2194 | 2.4461 | 2.6692 | 3.1688 | 1.3988 | 10.346 | 5.2026 | 15.2423 | 17.9115 | 28.2575 | 33.46 | 0.01
19.384 | 10.8999 | 1.4663 | 1.1994 | 5.2307 | 4.3226 | 2.9969 | 7.6768 | 30.2838 | 31.4832 | 41.0365 | 48.7133 | 19.394 | 10.8999 | 1.4663 | 1.1994 | 5.2307 | 4.3226 | 2.9969 | 7.6768 | 30.2938 | 31.4932 | 41.0465 | 48.7233 | 0.01
19.2262 | 4.5307 | 2.4409 | 2.6613 | 0.33129 | 3.8214 | 10.3065 | 1.7975 | 23.7568 | 26.4181 | 36.7247 | 38.5222 | 19.2362 | 4.5307 | 2.4409 | 2.6613 | 0.33129 | 3.8214 | 10.3065 | 1.7975 | 23.7668 | 26.4281 | 36.7347 | 38.5322 | 0.01
14.2142 | 10.8657 | 2.2738 | 2.4107 | 5.2044 | 2.1505 | 9.0535 | 7.6452 | 25.0798 | 27.4905 | 36.5441 | 44.1893 | 14.2242 | 10.8657 | 2.2738 | 2.4107 | 5.2044 | 2.1505 | 9.0535 | 7.6452 | 25.0898 | 27.5005 | 36.5541 | 44.1993 | 0.01
-2.4952 | 9.7797 | 1.7168 | 1.5752 | 4.369 | 3.5234 | 4.8762 | 6.6428 | 7.2846 | 8.8598 | 16.7522 | 23.395 | -2.4852 | 9.7797 | 1.7168 | 1.5752 | 4.369 | 3.5234 | 4.8762 | 6.6428 | 7.2946 | 8.8698 | 16.7622 | 23.405 | 0.01
11.2336 | 6.1594 | 2.1745 | 2.2617 | 1.5841 | 4.0163 | 8.3084 | 3.301 | 17.393 | 19.6547 | 27.9631 | 31.2641 | 11.2436 | 6.1594 | 2.1745 | 2.2617 | 1.5841 | 4.0163 | 8.3084 | 3.301 | 17.403 | 19.6647 | 27.9731 | 31.2741 | 0.01
16.1635 | 9.134 | 2.3388 | 2.5082 | 3.8723 | 2.7069 | 9.5409 | 6.0467 | 25.2974 | 27.8056 | 37.3465 | 43.3932 | 16.1735 | 9.134 | 2.3388 | 2.5082 | 3.8723 | 2.7069 | 9.5409 | 6.0467 | 25.3074 | 27.8156 | 37.3565 | 43.4032 | 0.01
3.0691 | 10.2021 | 1.9023 | 1.8535 | 4.2369 | 3.7422 | 6.2673 | 7.0327 | 13.2711 | 15.1246 | 23.1037 | 30.1364 | 3.0791 | 10.2021 | 1.9023 | 1.8535 | 4.2369 | 3.7422 | 6.2673 | 7.0327 | 13.2811 | 15.1346 | 23.1137 | 30.1464 | 0.01
13.4216 | 7.365 | 2.2474 | 2.3711 | 4.3798 | 3.8279 | 8.8554 | 4.4138 | 20.7866 | 23.1577 | 32.0131 | 36.4269 | 13.4316 | 7.365 | 2.2474 | 2.3711 | 4.3798 | 3.8279 | 8.8554 | 4.4138 | 20.7966 | 23.1677 | 32.0231 | 36.4369 | 0.01
14.2791 | 9.608 | 2.276 | 2.414 | 2.4376 | 2.6625 | 9.0698 | 6.4843 | 23.8871 | 26.301 | 35.3708 | 41.8551 | 14.2891 | 9.608 | 2.276 | 2.414 | 2.4376 | 2.6625 | 9.0698 | 6.4843 | 23.8971 | 26.311 | 35.3808 | 41.8651 | 0.01
2.6253 | 9.7938 | 1.8875 | 1.8313 | 0.72184 | 1.6331 | 6.1563 | 6.6558 | 12.4191 | 14.2504 | 20.4067 | 27.0625 | 2.6353 | 9.7938 | 1.8875 | 1.8313 | 0.72184 | 1.6331 | 6.1563 | 6.6558 | 12.4291 | 14.2604 | 20.4167 | 27.0725 | 0.01
-7.6689 | 7.2688 | 1.5444 | 1.3166 | 4.3164 | 3.7899 | 3.5828 | 4.3251 | -0.40013 | 0.91643 | 9.0227 | 13.3478 | -7.6589 | 7.2688 | 1.5444 | 1.3166 | 4.3164 | 3.7899 | 3.5828 | 4.3251 | -0.39013 | 0.92643 | 9.0327 | 13.3578 | 0.01
13.8987 | 5.0384 | 2.2633 | 2.3949 | 4.5377 | 3.9226 | 8.9747 | 2.2662 | 18.9371 | 21.332 | 30.3067 | 32.5729 | 13.9087 | 5.0384 | 2.2633 | 2.3949 | 4.5377 | 3.9226 | 8.9747 | 2.2662 | 18.9471 | 21.342 | 30.3167 | 32.5829 | 0.01
15.2263 | 9.7114 | 2.3075 | 2.4613 | 5.1783 | 4.307 | 9.3066 | 6.5797 | 24.9377 | 27.399 | 36.8844 | 43.4641 | 15.2363 | 9.7114 | 2.3075 | 2.4613 | 5.1783 | 4.307 | 9.3066 | 6.5797 | 24.9477 | 27.409 | 36.8944 | 43.4741 | 0.01
19.0701 | 9.999 | 2.4357 | 2.6535 | 1.7349 | 2.2409 | 10.2675 | 6.8453 | 29.0691 | 31.7226 | 41.9902 | 48.8354 | 19.0801 | 9.999 | 2.4357 | 2.6535 | 1.7349 | 2.2409 | 10.2675 | 6.8453 | 29.0791 | 31.7326 | 42.0002 | 48.8454 | 0.01
-1.5907 | 10.8319 | 1.747 | 1.6205 | 3.4667 | 3.28 | 5.1023 | 7.614 | 9.2411 | 10.8616 | 17.6083 | 25.2223 | -1.5807 | 10.8319 | 1.747 | 1.6205 | 3.4667 | 3.28 | 5.1023 | 7.614 | 9.2511 | 10.8716 | 17.6183 | 25.2323 | 0.01
8.8001 | 6.3553 | 2.0933 | 2.14 | 3.3661 | 3.2197 | 7.7 | 3.4819 | 15.1554 | 17.2954 | 24.9955 | 28.4773 | 8.8101 | 6.3553 | 2.0933 | 2.14 | 3.3661 | 3.2197 | 7.7 | 3.4819 | 15.1654 | 17.3054 | 25.0055 | 28.4873 | 0.01
8.1966 | 8.6067 | 2.0732 | 2.1098 | 2.9229 | 2.9538 | 7.5492 | 5.56 | 16.8033 | 18.9131 | 26.4623 | 32.0223 | 8.2066 | 8.6067 | 2.0732 | 2.1098 | 2.9229 | 2.9538 | 7.5492 | 5.56 | 16.8133 | 18.9231 | 26.4723 | 32.0323 | 0.01
5.5376 | 8.4759 | 1.9846 | 1.9769 | 2.3602 | 2.6161 | 6.8844 | 5.4393 | 14.0135 | 15.9904 | 22.8748 | 28.3141 | 5.5476 | 8.4759 | 1.9846 | 1.9769 | 2.3602 | 2.6161 | 6.8844 | 5.4393 | 14.0235 | 16.0004 | 22.8848 | 28.3241 | 0.01
2.1614 | 7.8998 | 1.872 | 1.8081 | 2.489 | 2.6934 | 6.0403 | 4.9075 | 10.0612 | 11.8692 | 17.9096 | 22.8171 | 2.1714 | 7.8998 | 1.872 | 1.8081 | 2.489 | 2.6934 | 6.0403 | 4.9075 | 10.0712 | 11.8792 | 17.9196 | 22.8271 | 0.01
2.9341 | 7.1683 | 1.8978 | 1.8467 | 3.9122 | 3.5473 | 6.2335 | 4.2323 | 10.1024 | 11.9491 | 19.4087 | 23.641 | 2.9441 | 7.1683 | 1.8978 | 1.8467 | 3.9122 | 3.5473 | 6.2335 | 4.2323 | 10.1124 | 11.9591 | 19.4187 | 23.651 | 0.01
11.4734 | 7.3357 | 2.1824 | 2.2737 | 4.5221 | 3.9133 | 8.3684 | 4.3868 | 18.8092 | 21.0828 | 29.5182 | 33.9051 | 11.4834 | 7.3357 | 2.1824 | 2.2737 | 4.5221 | 3.9133 | 8.3684 | 4.3868 | 18.8192 | 21.0928 | 29.5282 | 33.9151 | 0.01
15.1327 | 9.1859 | 2.3044 | 2.4566 | 3.0515 | 3.0309 | 9.2832 | 6.0947 | 24.3186 | 26.7752 | 36.0584 | 42.1531 | 15.1427 | 9.1859 | 2.3044 | 2.4566 | 3.0515 | 3.0309 | 9.2832 | 6.0947 | 24.3286 | 26.7852 | 36.0684 | 42.1631 | 0.01
6.309 | 9.9788 | 2.0103 | 2.0154 | 3.3918 | 3.2351 | 7.0772 | 6.8265 | 16.2877 | 18.3032 | 25.3804 | 32.207 | 6.319 | 9.9788 | 2.0103 | 2.0154 | 3.3918 | 3.2351 | 7.0772 | 6.8265 | 16.2977 | 18.3132 | 25.3904 | 32.217 | 0.01
8.3508 | 8.0669 | 2.0784 | 2.1175 | 3.9998 | 3.5999 | 7.5877 | 5.0618 | 16.4178 | 18.5353 | 26.135 | 31.1968 | 8.3608 | 8.0669 | 2.0784 | 2.1175 | 3.9998 | 3.5999 | 7.5877 | 5.0618 | 16.4278 | 18.5453 | 26.145 | 31.2068 | 0.01
11.9988 | 8.5093 | 2.2 | 2.2999 | 3.3774 | 3.2265 | 8.4997 | 5.4702 | 20.5081 | 22.808 | 31.3077 | 36.7779 | 12.0088 | 8.5093 | 2.2 | 2.2999 | 3.3774 | 3.2265 | 8.4997 | 5.4702 | 20.5181 | 22.818 | 31.3177 | 36.7879 | 0.01
8.2645 | 9.2997 | 2.0755 | 2.1132 | 2.4958 | 2.6975 | 7.5661 | 6.1998 | 17.5643 | 19.6775 | 27.2436 | 33.4434 | 8.2745 | 9.2997 | 2.0755 | 2.1132 | 2.4958 | 2.6975 | 7.5661 | 6.1998 | 17.5743 | 19.6875 | 27.2536 | 33.4534 | 0.01
2.9748 | 8.4906 | 1.8992 | 1.8487 | 3.6696 | 3.4018 | 6.2437 | 5.4529 | 11.4654 | 13.3142 | 20.3856 | 25.8385 | 2.9848 | 8.4906 | 1.8992 | 1.8487 | 3.6696 | 3.4018 | 6.2437 | 5.4529 | 11.4754 | 13.3242 | 20.3956 | 25.8485 | 0.01
10.0178 | 7.3445 | 2.1339 | 2.2009 | 2.3627 | 2.6176 | 8.0044 | 4.395 | 17.3623 | 19.5632 | 27.5677 | 31.9626 | 10.0278 | 7.3445 | 2.1339 | 2.2009 | 2.3627 | 2.6176 | 8.0044 | 4.395 | 17.3723 | 19.5732 | 27.5777 | 31.9726 | 0.01
2.1761 | 8.8705 | 1.8725 | 1.8088 | 3.6992 | 3.4195 | 6.044 | 5.8036 | 11.0466 | 12.8554 | 19.9742 | 25.7777 | 2.1861 | 8.8705 | 1.8725 | 1.8088 | 3.6992 | 3.4195 | 6.044 | 5.8036 | 11.0566 | 12.8654 | 19.9842 | 25.7877 | 0.01
10.1953 | 7.1715 | 2.1398 | 2.2098 | 2.0614 | 2.4368 | 8.0488 | 4.2352 | 17.3668 | 19.5765 | 27.6253 | 31.8606 | 10.2053 | 7.1715 | 2.1398 | 2.2098 | 2.0614 | 2.4368 | 8.0488 | 4.2352 | 17.3768 | 19.5865 | 27.6353 | 31.8706 | 0.01
0.36812 | 8.909 | 1.8123 | 1.7184 | 3.4738 | 3.2843 | 5.592 | 5.8391 | 9.2771 | 10.9955 | 17.7536 | 23.5926 | 0.37812 | 8.909 | 1.8123 | 1.7184 | 3.4738 | 3.2843 | 5.592 | 5.8391 | 9.2871 | 11.0055 | 17.7636 | 23.6026 | 0.01
8.8428 | 6.7798 | 2.0948 | 2.1421 | 2.5607 | 2.7364 | 7.7107 | 3.8736 | 15.6225 | 17.7647 | 25.4753 | 29.349 | 8.8528 | 6.7798 | 2.0948 | 2.1421 | 2.5607 | 2.7364 | 7.7107 | 3.8736 | 15.6325 | 17.7747 | 25.4853 | 29.359 | 0.01
3.3639 | 8.6159 | 1.9121 | 1.8682 | 3.7195 | 3.4317 | 6.341 | 5.5686 | 11.9799 | 13.8481 | 20.9992 | 26.5678 | 3.3739 | 8.6159 | 1.9121 | 1.8682 | 3.7195 | 3.4317 | 6.341 | 5.5686 | 11.9899 | 13.8581 | 21.0092 | 26.5778 | 0.01
10.3169 | 7.4289 | 2.1439 | 2.2158 | 4.0749 | 3.645 | 8.0792 | 4.4728 | 17.7457 | 19.9616 | 28.0408 | 32.5136 | 10.3269 | 7.4289 | 2.1439 | 2.2158 | 4.0749 | 3.645 | 8.0792 | 4.4728 | 17.7557 | 19.9716 | 28.0508 | 32.5236 | 0.01
12.4496 | 8.9353 | 2.215 | 2.3225 | 3.8485 | 3.5091 | 8.6124 | 5.8634 | 21.3849 | 23.7074 | 32.3198 | 38.1832 | 12.4596 | 8.9353 | 2.215 | 2.3225 | 3.8485 | 3.5091 | 8.6124 | 5.8634 | 21.3949 | 23.7174 | 32.3298 | 38.1932 | 0.01
11.0913 | 9.3974 | 2.1697 | 2.2546 | 1.6992 | 2.2195 | 8.2728 | 6.2899 | 20.4887 | 22.7433 | 31.0161 | 37.306 | 11.1013 | 9.3974 | 2.1697 | 2.2546 | 1.6992 | 2.2195 | 8.2728 | 6.2899 | 20.4987 | 22.7533 | 31.0261 | 37.316 | 0.01
-1.8049 | 9.1031 | 1.7398 | 1.6098 | 3.2226 | 3.1336 | 5.0488 | 6.0183 | 7.2982 | 8.908 | 15.2642 | 21.2824 | -1.7949 | 9.1031 | 1.7398 | 1.6098 | 3.2226 | 3.1336 | 5.0488 | 6.0183 | 7.3082 | 8.918 | 15.2742 | 21.2924 | 0.01
7.3357 | 6.3089 | 2.0445 | 2.0668 | 4.1585 | 3.6951 | 7.3339 | 3.439 | 13.6446 | 15.7114 | 23.565 | 27.004 | 7.3457 | 6.3089 | 2.0445 | 2.0668 | 4.1585 | 3.6951 | 7.3339 | 3.439 | 13.6546 | 15.7214 | 23.575 | 27.014 | 0.01
12.9509 | 8.2894 | 2.2317 | 2.3475 | 1.8244 | 2.2947 | 8.7377 | 5.2671 | 21.2403 | 23.5878 | 32.3255 | 37.5927 | 12.9609 | 8.2894 | 2.2317 | 2.3475 | 1.8244 | 2.2947 | 8.7377 | 5.2671 | 21.2503 | 23.5978 | 32.3355 | 37.6027 | 0.01
-1.0534 | 9.506 | 1.7649 | 1.6473 | 4.1219 | 3.6732 | 5.2366 | 6.3902 | 8.4526 | 10.0999 | 17.895 | 24.2852 | -1.0434 | 9.506 | 1.7649 | 1.6473 | 4.1219 | 3.6732 | 5.2366 | 6.3902 | 8.4626 | 10.1099 | 17.905 | 24.2952 | 0.01
12.7317 | 6.4718 | 2.2244 | 2.3366 | 2.2937 | 2.5762 | 8.6829 | 3.5893 | 19.2034 | 21.54 | 30.2229 | 33.8122 | 12.7417 | 6.4718 | 2.2244 | 2.3366 | 2.2937 | 2.5762 | 8.6829 | 3.5893 | 19.2134 | 21.55 | 30.2329 | 33.8222 | 0.01
1.7625 | 9.4585 | 1.8587 | 1.7881 | 4.4139 | 3.8484 | 5.9406 | 6.3463 | 11.221 | 13.0091 | 21.2714 | 27.6177 | 1.7725 | 9.4585 | 1.8587 | 1.7881 | 4.4139 | 3.8484 | 5.9406 | 6.3463 | 11.231 | 13.0191 | 21.2814 | 27.6277 | 0.01
14.4836 | 7.0819 | 2.2828 | 2.4242 | 2.818 | 2.8908 | 9.1209 | 4.1525 | 21.5654 | 23.9896 | 33.1105 | 37.263 | 14.4936 | 7.0819 | 2.2828 | 2.4242 | 2.818 | 2.8908 | 9.1209 | 4.1525 | 21.5754 | 23.9996 | 33.1205 | 37.273 | 0.01
4.908 | 9.8381 | 1.9636 | 1.9454 | 4.2124 | 3.7275 | 6.727 | 6.6967 | 14.7461 | 16.6915 | 24.6314 | 31.3281 | 4.918 | 9.8381 | 1.9636 | 1.9454 | 4.2124 | 3.7275 | 6.727 | 6.6967 | 14.7561 | 16.7015 | 24.6414 | 31.3381 | 0.01
13.2747 | 7.7634 | 2.2425 | 2.3637 | 2.6176 | 2.7706 | 8.8187 | 4.7816 | 21.0381 | 23.4018 | 32.2205 | 37.0021 | 13.2847 | 7.7634 | 2.2425 | 2.3637 | 2.6176 | 2.7706 | 8.8187 | 4.7816 | 21.0481 | 23.4118 | 32.2305 | 37.0121 | 0.01
3.7058 | 9.5762 | 1.9235 | 1.8853 | 4.0942 | 3.6565 | 6.4265 | 6.4549 | 13.282 | 15.1673 | 22.9179 | 29.3729 | 3.7158 | 9.5762 | 1.9235 | 1.8853 | 4.0942 | 3.6565 | 6.4265 | 6.4549 | 13.292 | 15.1773 | 22.9279 | 29.3829 | 0.01
12.5649 | 7.5029 | 2.2188 | 2.3282 | 2.7136 | 2.8282 | 8.6412 | 4.5412 | 20.0678 | 22.3961 | 31.0373 | 35.5785 | 12.5749 | 7.5029 | 2.2188 | 2.3282 | 2.7136 | 2.8282 | 8.6412 | 4.5412 | 20.0778 | 22.4061 | 31.0473 | 35.5885 | 0.01
4.2816 | 9.4224 | 1.9427 | 1.9141 | 1.5496 | 2.1298 | 6.5704 | 6.313 | 13.704 | 15.618 | 22.1884 | 28.5014 | 4.2916 | 9.4224 | 1.9427 | 1.9141 | 1.5496 | 2.1298 | 6.5704 | 6.313 | 13.714 | 15.628 | 22.1984 | 28.5114 | 0.01
-2.7021 | 7.6277 | 1.7099 | 1.5649 | 4.8215 | 4.0929 | 4.8245 | 4.6563 | 4.9255 | 6.4904 | 15.4048 | 20.0611 | -2.6921 | 7.6277 | 1.7099 | 1.5649 | 4.8215 | 4.0929 | 4.8245 | 4.6563 | 4.9355 | 6.5004 | 15.4148 | 20.0711 | 0.01
16.9289 | 6.1145 | 2.3643 | 2.5464 | 1.5666 | 2.14 | 9.7322 | 3.2596 | 23.0434 | 25.5899 | 35.3221 | 38.5817 | 16.9389 | 6.1145 | 2.3643 | 2.5464 | 1.5666 | 2.14 | 9.7322 | 3.2596 | 23.0534 | 25.5999 | 35.3321 | 38.5917 | 0.01
-2.6001 | 10.3679 | 1.7133 | 1.57 | 2.43 | 2.658 | 4.85 | 7.1858 | 7.7678 | 9.3378 | 14.4258 | 21.6116 | -2.5901 | 10.3679 | 1.7133 | 1.57 | 2.43 | 2.658 | 4.85 | 7.1858 | 7.7778 | 9.3478 | 14.4358 | 21.6216 | 0.01
2.5801 | 6.1366 | 1.886 | 1.829 | 0.74844 | 1.6491 | 6.145 | 3.28 | 8.7168 | 10.5458 | 16.6908 | 19.9708 | 2.5901 | 6.1366 | 1.886 | 1.829 | 0.74844 | 1.6491 | 6.145 | 3.28 | 8.7268 | 10.5558 | 16.7008 | 19.9808 | 0.01
-7.5094 | 7.259 | 1.5497 | 1.3245 | 3.3043 | 3.1826 | 3.6227 | 4.316 | -0.25035 | 1.0742 | 7.5611 | 11.8771 | -7.4994 | 7.259 | 1.5497 | 1.3245 | 3.3043 | 3.1826 | 3.6227 | 4.316 | -0.24035 | 1.0842 | 7.5711 | 11.8871 | 0.01
7.826 | 5.073 | 2.0609 | 2.0913 | 0.096747 | 1.258 | 7.4565 | 2.2981 | 12.899 | 14.9903 | 22.4468 | 24.7449 | 7.836 | 5.073 | 2.0609 | 2.0913 | 0.096747 | 1.258 | 7.4565 | 2.2981 | 12.909 | 15.0003 | 22.4568 | 24.7549 | 0.01
-11.4195 | 8.3956 | 1.4193 | 1.129 | 1.1507 | 1.8904 | 2.6451 | 5.3652 | -3.0239 | -1.8949 | 1.1462 | 6.5114 | -11.4095 | 8.3956 | 1.4193 | 1.129 | 1.1507 | 1.8904 | 2.6451 | 5.3652 | -3.0139 | -1.8849 | 1.1562 | 6.5214 | 0.01
-5.0961 | 4.2258 | 1.6301 | 1.4452 | 2.318 | 2.5908 | 4.226 | 1.5161 | -0.87032 | 0.57488 | 5.4837 | 6.9998 | -5.0861 | 4.2258 | 1.6301 | 1.4452 | 2.318 | 2.5908 | 4.226 | 1.5161 | -0.86032 | 0.58488 | 5.4937 | 7.0098 | 0.01
1.9081 | 5.5958 | 1.8636 | 1.7954 | 3.9068 | 3.5441 | 5.977 | 2.7808 | 7.5039 | 9.2993 | 16.7502 | 19.531 | 1.9181 | 5.5958 | 1.8636 | 1.7954 | 3.9068 | 3.5441 | 5.977 | 2.7808 | 7.5139 | 9.3093 | 16.7602 | 19.541 | 0.01
11.4408 | 7.1134 | 2.1814 | 2.272 | 3.9987 | 3.5992 | 8.3602 | 4.1816 | 18.5542 | 20.8263 | 29.1865 | 33.3681 | 11.4508 | 7.1134 | 2.1814 | 2.272 | 3.9987 | 3.5992 | 8.3602 | 4.1816 | 18.5642 | 20.8363 | 29.1965 | 33.3781 | 0.01
11.9924 | 9.1788 | 2.1997 | 2.2996 | 2.5211 | 2.7127 | 8.4981 | 6.0882 | 21.1712 | 23.4708 | 31.9689 | 38.0571 | 12.0024 | 9.1788 | 2.1997 | 2.2996 | 2.5211 | 2.7127 | 8.4981 | 6.0882 | 21.1812 | 23.4808 | 31.9789 | 38.0671 | 0.01
3.1269 | 9.2983 | 1.9042 | 1.8563 | 2.6077 | 2.7646 | 6.2817 | 6.1985 | 12.4252 | 14.2815 | 20.5633 | 26.7617 | 3.1369 | 9.2983 | 1.9042 | 1.8563 | 2.6077 | 2.7646 | 6.2817 | 6.1985 | 12.4352 | 14.2915 | 20.5733 | 26.7717 | 0.01
3.646 | 7.3775 | 1.9215 | 1.8823 | 3.8705 | 3.5223 | 6.4115 | 4.4254 | 11.0234 | 12.9057 | 20.2986 | 24.724 | 3.656 | 7.3775 | 1.9215 | 1.8823 | 3.8705 | 3.5223 | 6.4115 | 4.4254 | 11.0334 | 12.9157 | 20.3086 | 24.734 | 0.01
11.2232 | 7.49 | 2.1741 | 2.2612 | 4.6272 | 3.9763 | 8.3058 | 4.5292 | 18.7131 | 20.9743 | 29.5778 | 34.107 | 11.2332 | 7.49 | 2.1741 | 2.2612 | 4.6272 | 3.9763 | 8.3058 | 4.5292 | 18.7231 | 20.9843 | 29.5878 | 34.117 | 0.01
15.7633 | 9.1317 | 2.3254 | 2.4882 | 3.3338 | 3.2003 | 9.4408 | 6.0446 | 24.895 | 27.3831 | 36.8239 | 42.8686 | 15.7733 | 9.1317 | 2.3254 | 2.4882 | 3.3338 | 3.2003 | 9.4408 | 6.0446 | 24.905 | 27.3931 | 36.8339 | 42.8786 | 0.01
8.0029 | 10.1154 | 2.0668 | 2.1001 | 4.3526 | 3.8116 | 7.5007 | 6.9527 | 18.1183 | 20.2185 | 28.3827 | 35.3354 | 8.0129 | 10.1154 | 2.0668 | 2.1001 | 4.3526 | 3.8116 | 7.5007 | 6.9527 | 18.1283 | 20.2285 | 28.3927 | 35.3454 | 0.01
14.1159 | 8.434 | 2.2705 | 2.4058 | 3.1711 | 3.1026 | 9.029 | 5.4006 | 22.5498 | 24.9556 | 33.9846 | 39.3852 | 14.1259 | 8.434 | 2.2705 | 2.4058 | 3.1711 | 3.1026 | 9.029 | 5.4006 | 22.5598 | 24.9656 | 33.9946 | 39.3952 | 0.01
7.0265 | 9.7584 | 2.0342 | 2.0513 | 1.0701 | 1.842 | 7.2566 | 6.6232 | 16.7849 | 18.8362 | 26.0929 | 32.716 | 7.0365 | 9.7584 | 2.0342 | 2.0513 | 1.0701 | 1.842 | 7.2566 | 6.6232 | 16.7949 | 18.8462 | 26.1029 | 32.726 | 0.01
-5.5795 | 8.2224 | 1.614 | 1.421 | 3.1699 | 3.1019 | 4.1051 | 5.2053 | 2.6429 | 4.0639 | 10.3358 | 15.5411 | -5.5695 | 8.2224 | 1.614 | 1.421 | 3.1699 | 3.1019 | 4.1051 | 5.2053 | 2.6529 | 4.0739 | 10.3458 | 15.5511 | 0.01
7.0195 | 5.4911 | 2.034 | 2.051 | 2.44 | 2.664 | 7.2549 | 2.6841 | 12.5106 | 14.5615 | 21.8164 | 24.5005 | 7.0295 | 5.4911 | 2.034 | 2.051 | 2.44 | 2.664 | 7.2549 | 2.6841 | 12.5206 | 14.5715 | 21.8264 | 24.5105 | 0.01
2.6398 | 8.2209 | 1.888 | 1.832 | 3.9164 | 3.5498 | 6.1599 | 5.2039 | 10.8607 | 12.6926 | 20.1589 | 25.3627 | 2.6498 | 8.2209 | 1.888 | 1.832 | 3.9164 | 3.5498 | 6.1599 | 5.2039 | 10.8707 | 12.7026 | 20.1689 | 25.3727 | 0.01
11.4983 | 7.272 | 2.1833 | 2.2749 | 2.2667 | 2.56 | 8.3746 | 4.328 | 18.7703 | 21.0452 | 29.4197 | 33.7477 | 11.5083 | 7.272 | 2.1833 | 2.2749 | 2.2667 | 2.56 | 8.3746 | 4.328 | 18.7803 | 21.0552 | 29.4297 | 33.7577 | 0.01
1.6003 | 9.1913 | 1.8533 | 1.78 | 0.78163 | 1.669 | 5.9001 | 6.0997 | 10.7916 | 12.5716 | 18.4716 | 24.5713 | 1.6103 | 9.1913 | 1.8533 | 1.78 | 0.78163 | 1.669 | 5.9001 | 6.0997 | 10.8016 | 12.5816 | 18.4816 | 24.5813 | 0.01
-7.3102 | 7.0467 | 1.5563 | 1.3345 | 4.619 | 3.9714 | 3.6724 | 4.1201 | -0.26348 | 1.071 | 9.6614 | 13.7815 | -7.3002 | 7.0467 | 1.5563 | 1.3345 | 4.619 | 3.9714 | 3.6724 | 4.1201 | -0.25348 | 1.081 | 9.6714 | 13.7915 | 0.01
15.714 | 5.1161 | 2.3238 | 2.4857 | 4.1687 | 3.7012 | 9.4285 | 2.338 | 20.8301 | 23.3158 | 32.7443 | 35.0823 | 15.724 | 5.1161 | 2.3238 | 2.4857 | 4.1687 | 3.7012 | 9.4285 | 2.338 | 20.8401 | 23.3258 | 32.7543 | 35.0923 | 0.01
13.0123 | 10.1047 | 2.2337 | 2.3506 | 0.93932 | 1.7636 | 8.7531 | 6.9428 | 23.117 | 25.4677 | 34.2207 | 41.1635 | 13.0223 | 10.1047 | 2.2337 | 2.3506 | 0.93932 | 1.7636 | 8.7531 | 6.9428 | 23.127 | 25.4777 | 34.2307 | 41.1735 | 0.01
-6.3641 | 9.5193 | 1.5879 | 1.3818 | 3.1006 | 3.0604 | 3.909 | 6.4025 | 3.1553 | 4.5371 | 10.698 | 17.1005 | -6.3541 | 9.5193 | 1.5879 | 1.3818 | 3.1006 | 3.0604 | 3.909 | 6.4025 | 3.1653 | 4.5471 | 10.708 | 17.1105 | 0.01
6.6035 | 5.3211 | 2.0201 | 2.0302 | 3.8656 | 3.5194 | 7.1509 | 2.5272 | 11.9246 | 13.9548 | 21.3398 | 23.867 | 6.6135 | 5.3211 | 2.0201 | 2.0302 | 3.8656 | 3.5194 | 7.1509 | 2.5272 | 11.9346 | 13.9648 | 21.3498 | 23.877 | 0.01
11.1936 | 8.1308 | 2.1731 | 2.2597 | 2.3992 | 2.6395 | 8.2984 | 5.1207 | 19.3244 | 21.584 | 29.8824 | 35.0031 | 11.2036 | 8.1308 | 2.1731 | 2.2597 | 2.3992 | 2.6395 | 8.2984 | 5.1207 | 19.3344 | 21.594 | 29.8924 | 35.0131 | 0.01
2.3952 | 9.1253 | 1.8798 | 1.8198 | 4.4598 | 3.8759 | 6.0988 | 6.0387 | 11.5205 | 13.3403 | 21.6759 | 27.7146 | 2.4052 | 9.1253 | 1.8798 | 1.8198 | 4.4598 | 3.8759 | 6.0988 | 6.0387 | 11.5305 | 13.3503 | 21.6859 | 27.7246 | 0.01
14.7587 | 7.219 | 2.292 | 2.4379 | 4.6718 | 4.0031 | 9.1897 | 4.279 | 21.9776 | 24.4156 | 33.6053 | 37.8843 | 14.7687 | 7.219 | 2.292 | 2.4379 | 4.6718 | 4.0031 | 9.1897 | 4.279 | 21.9876 | 24.4256 | 33.6153 | 37.8943 | 0.01
16.0308 | 9.8977 | 2.3344 | 2.5015 | 2.5827 | 2.7496 | 9.5077 | 6.7517 | 25.9285 | 28.4301 | 37.9378 | 44.6895 | 16.0408 | 9.8977 | 2.3344 | 2.5015 | 2.5827 | 2.7496 | 9.5077 | 6.7517 | 25.9385 | 28.4401 | 37.9478 | 44.6995 | 0.01
3.496 | 10.1733 | 1.9165 | 1.8748 | 2.8107 | 2.8864 | 6.374 | 7.0062 | 13.6693 | 15.5441 | 21.9181 | 28.9243 | 3.506 | 10.1733 | 1.9165 | 1.8748 | 2.8107 | 2.8864 | 6.374 | 7.0062 | 13.6793 | 15.5541 | 21.9281 | 28.9343 | 0.01
4.8644 | 7.4575 | 1.9621 | 1.9432 | 4.7599 | 4.0559 | 6.7161 | 4.4992 | 12.3218 | 14.265 | 23.0809 | 27.5801 | 4.8744 | 7.4575 | 1.9621 | 1.9432 | 4.7599 | 4.0559 | 6.7161 | 4.4992 | 12.3318 | 14.275 | 23.0909 | 27.5901 | 0.01
16.5595 | 7.7539 | 2.352 | 2.528 | 5.0114 | 4.2069 | 9.6399 | 4.7729 | 24.3134 | 26.8414 | 36.4813 | 41.2541 | 16.5695 | 7.7539 | 2.352 | 2.528 | 5.0114 | 4.2069 | 9.6399 | 4.7729 | 24.3234 | 26.8514 | 36.4913 | 41.2641 | 0.01
18.0686 | 10.2879 | 2.4023 | 2.6034 | 4.3153 | 3.7892 | 10.0172 | 7.1119 | 28.3565 | 30.9599 | 40.9771 | 48.089 | 18.0786 | 10.2879 | 2.4023 | 2.6034 | 4.3153 | 3.7892 | 10.0172 | 7.1119 | 28.3665 | 30.9699 | 40.9871 | 48.099 | 0.01
13.8917 | 10.6149 | 2.2631 | 2.3946 | 3.384 | 3.2304 | 8.9729 | 7.4137 | 24.5065 | 26.9011 | 35.874 | 43.2878 | 13.9017 | 10.6149 | 2.2631 | 2.3946 | 3.384 | 3.2304 | 8.9729 | 7.4137 | 24.5165 | 26.9111 | 35.884 | 43.2978 | 0.01
8.3042 | 9.7099 | 2.0768 | 2.1152 | 2.9744 | 2.9846 | 7.576 | 6.5783 | 18.014 | 20.1292 | 27.7053 | 34.2836 | 8.3142 | 9.7099 | 2.0768 | 2.1152 | 2.9744 | 2.9846 | 7.576 | 6.5783 | 18.024 | 20.1392 | 27.7153 | 34.2936 | 0.01
5.8464 | 8.4992 | 1.9949 | 1.9923 | 4.3016 | 3.781 | 6.9616 | 5.4608 | 14.3457 | 16.338 | 24.4206 | 29.8814 | 5.8564 | 8.4992 | 1.9949 | 1.9923 | 4.3016 | 3.781 | 6.9616 | 5.4608 | 14.3557 | 16.348 | 24.4306 | 29.8914 | 0.01
13.8097 | 7.9667 | 2.2603 | 2.3905 | 3.6323 | 3.3794 | 8.9524 | 4.9693 | 21.7765 | 24.1669 | 33.1194 | 38.0887 | 13.8197 | 7.9667 | 2.2603 | 2.3905 | 3.6323 | 3.3794 | 8.9524 | 4.9693 | 21.7865 | 24.1769 | 33.1294 | 38.0987 | 0.01
9.7938 | 9.6921 | 2.1265 | 2.1897 | 3.7296 | 3.4377 | 7.9485 | 6.5619 | 19.4859 | 21.6756 | 29.6241 | 36.186 | 9.8038 | 9.6921 | 2.1265 | 2.1897 | 3.7296 | 3.4377 | 7.9485 | 6.5619 | 19.4959 | 21.6856 | 29.6341 | 36.196 | 0.01
10.3775 | 8.822 | 2.1459 | 2.2189 | 4.6453 | 3.9872 | 8.0944 | 5.7588 | 19.1995 | 21.4184 | 30.0509 | 35.8096 | 10.3875 | 8.822 | 2.1459 | 2.2189 | 4.6453 | 3.9872 | 8.0944 | 5.7588 | 19.2095 | 21.4284 | 30.0609 | 35.8196 | 0.01
15.8718 | 8.9485 | 2.3291 | 2.4936 | 2.8253 | 2.8952 | 9.468 | 5.8755 | 24.8203 | 27.3139 | 36.7818 | 42.6573 | 15.8818 | 8.9485 | 2.3291 | 2.4936 | 2.8253 | 2.8952 | 9.468 | 5.8755 | 24.8303 | 27.3239 | 36.7918 | 42.6673 | 0.01
4.9521 | 10.1389 | 1.9651 | 1.9476 | 2.6385 | 2.7831 | 6.738 | 6.9744 | 15.091 | 17.0386 | 23.7766 | 30.751 | 4.9621 | 10.1389 | 1.9651 | 1.9476 | 2.6385 | 2.7831 | 6.738 | 6.9744 | 15.101 | 17.0486 | 23.7866 | 30.761 | 0.01
3.8311 | 7.7729 | 1.9277 | 1.8916 | 2.9743 | 2.9846 | 6.4578 | 4.7904 | 11.604 | 13.4956 | 19.9533 | 24.7438 | 3.8411 | 7.7729 | 1.9277 | 1.8916 | 2.9743 | 2.9846 | 6.4578 | 4.7904 | 11.614 | 13.5056 | 19.9633 | 24.7538 | 0.01
5.8458 | 7.5301 | 1.9949 | 1.9923 | 1.9744 | 2.3846 | 6.9614 | 4.5662 | 13.3758 | 15.3681 | 22.3296 | 26.8958 | 5.8558 | 7.5301 | 1.9949 | 1.9923 | 1.9744 | 2.3846 | 6.9614 | 4.5662 | 13.3858 | 15.3781 | 22.3396 | 26.9058 | 0.01
-0.15369 | 7.9666 | 1.7949 | 1.6923 | 3.4835 | 3.2901 | 5.4616 | 4.9692 | 7.8129 | 9.5052 | 16.2788 | 21.248 | -0.14369 | 7.9666 | 1.7949 | 1.6923 | 3.4835 | 3.2901 | 5.4616 | 4.9692 | 7.8229 | 9.5152 | 16.2888 | 21.258 | 0.01
8.9011 | 6.6667 | 2.0967 | 2.1451 | 2.8402 | 2.9041 | 7.7253 | 3.7693 | 15.5678 | 17.7128 | 25.4381 | 29.2073 | 8.9111 | 6.6667 | 2.0967 | 2.1451 | 2.8402 | 2.9041 | 7.7253 | 3.7693 | 15.5778 | 17.7228 | 25.4481 | 29.2173 | 0.01
5.0411 | 8.6286 | 1.968 | 1.9521 | 2.9244 | 2.9547 | 6.7603 | 5.5802 | 13.6697 | 15.6217 | 22.382 | 27.9622 | 5.0511 | 8.6286 | 1.968 | 1.9521 | 2.9244 | 2.9547 | 6.7603 | 5.5802 | 13.6797 | 15.6317 | 22.392 | 27.9722 | 0.01
5.5467 | 7.7922 | 1.9849 | 1.9773 | 2.7834 | 2.87 | 6.8867 | 4.8082 | 13.3389 | 15.3163 | 22.2029 | 27.0112 | 5.5567 | 7.7922 | 1.9849 | 1.9773 | 2.7834 | 2.87 | 6.8867 | 4.8082 | 13.3489 | 15.3263 | 22.2129 | 27.0212 | 0.01
4.7002 | 7.9018 | 1.9567 | 1.935 | 2.2444 | 2.5466 | 6.675 | 4.9093 | 12.602 | 14.537 | 21.212 | 26.1214 | 4.7102 | 7.9018 | 1.9567 | 1.935 | 2.2444 | 2.5466 | 6.675 | 4.9093 | 12.612 | 14.547 | 21.222 | 26.1314 | 0.01
1.4663 | 7.7184 | 1.8489 | 1.7733 | 3.148 | 3.0888 | 5.8666 | 4.74 | 9.1847 | 10.958 | 17.1947 | 21.9348 | 1.4763 | 7.7184 | 1.8489 | 1.7733 | 3.148 | 3.0888 | 5.8666 | 4.74 | 9.1947 | 10.968 | 17.2047 | 21.9448 | 0.01
6.8879 | 7.0177 | 2.0296 | 2.0444 | 1.6145 | 2.1687 | 7.222 | 4.0933 | 13.9056 | 15.95 | 23.1719 | 27.2652 | 6.8979 | 7.0177 | 2.0296 | 2.0444 | 1.6145 | 2.1687 | 7.222 | 4.0933 | 13.9156 | 15.96 | 23.1819 | 27.2752 | 0.01
-2.3129 | 8.1924 | 1.7229 | 1.5844 | 2.1422 | 2.4853 | 4.9218 | 5.1776 | 5.8795 | 7.4639 | 12.3856 | 17.5632 | -2.3029 | 8.1924 | 1.7229 | 1.5844 | 2.1422 | 2.4853 | 4.9218 | 5.1776 | 5.8895 | 7.4739 | 12.3956 | 17.5732 | 0.01
0.85301 | 6.1989 | 1.8284 | 1.7427 | 3.3938 | 3.2363 | 5.7133 | 3.3374 | 7.0519 | 8.7945 | 15.4247 | 18.7621 | 0.86301 | 6.1989 | 1.8284 | 1.7427 | 3.3938 | 3.2363 | 5.7133 | 3.3374 | 7.0619 | 8.8045 | 15.4347 | 18.7721 | 0.01
8.363 | 6.8848 | 2.0788 | 2.1181 | 2.8631 | 2.9179 | 7.5907 | 3.9706 | 15.2478 | 17.366 | 24.9567 | 28.9273 | 8.373 | 6.8848 | 2.0788 | 2.1181 | 2.8631 | 2.9179 | 7.5907 | 3.9706 | 15.2578 | 17.376 | 24.9667 | 28.9373 | 0.01
5.1786 | 8.512 | 1.9726 | 1.9589 | 2.7811 | 2.8686 | 6.7946 | 5.4726 | 13.6906 | 15.6495 | 22.4441 | 27.9167 | 5.1886 | 8.512 | 1.9726 | 1.9589 | 2.7811 | 2.8686 | 6.7946 | 5.4726 | 13.7006 | 15.6595 | 22.4541 | 27.9267 | 0.01
4.6863 | 7.822 | 1.9562 | 1.9343 | 1.7183 | 2.231 | 6.6716 | 4.8357 | 12.5083 | 14.4427 | 21.1142 | 25.95 | 4.6963 | 7.822 | 1.9562 | 1.9343 | 1.7183 | 2.231 | 6.6716 | 4.8357 | 12.5183 | 14.4527 | 21.1242 | 25.96 | 0.01
-1.69 | 7.7154 | 1.7437 | 1.6155 | 2.6544 | 2.7926 | 5.0775 | 4.7373 | 6.0254 | 7.6409 | 13.0879 | 17.8252 | -1.68 | 7.7154 | 1.7437 | 1.6155 | 2.6544 | 2.7926 | 5.0775 | 4.7373 | 6.0354 | 7.6509 | 13.0979 | 17.8352 | 0.01
3.9263 | 6.3338 | 1.9309 | 1.8963 | 2.8467 | 2.908 | 6.4816 | 3.462 | 10.2601 | 12.1564 | 18.638 | 22.1 | 3.9363 | 6.3338 | 1.9309 | 1.8963 | 2.8467 | 2.908 | 6.4816 | 3.462 | 10.2701 | 12.1664 | 18.648 | 22.11 | 0.01
5.0801 | 7.5507 | 1.9693 | 1.954 | 2.9045 | 2.9427 | 6.77 | 4.5853 | 12.6307 | 14.5847 | 21.3548 | 25.94 | 5.0901 | 7.5507 | 1.9693 | 1.954 | 2.9045 | 2.9427 | 6.77 | 4.5853 | 12.6407 | 14.5947 | 21.3648 | 25.95 | 0.01
5.4268 | 7.8007 | 1.9809 | 1.9713 | 4.1252 | 3.6751 | 6.8567 | 4.816 | 13.2274 | 15.1988 | 22.9991 | 27.8151 | 5.4368 | 7.8007 | 1.9809 | 1.9713 | 4.1252 | 3.6751 | 6.8567 | 4.816 | 13.2374 | 15.2088 | 23.0091 | 27.8251 | 0.01
12.7511 | 7.8758 | 2.225 | 2.3376 | 3.8581 | 3.5149 | 8.6878 | 4.8854 | 20.6269 | 22.9645 | 31.6522 | 36.5376 | 12.7611 | 7.8758 | 2.225 | 2.3376 | 3.8581 | 3.5149 | 8.6878 | 4.8854 | 20.6369 | 22.9745 | 31.6622 | 36.5476 | 0.01
11.1487 | 9.4627 | 2.1716 | 2.2574 | 3.4723 | 3.2834 | 8.2872 | 6.3502 | 20.6114 | 22.8689 | 31.1561 | 37.5063 | 11.1587 | 9.4627 | 2.1716 | 2.2574 | 3.4723 | 3.2834 | 8.2872 | 6.3502 | 20.6214 | 22.8789 | 31.1661 | 37.5163 | 0.01
8.834 | 9.1156 | 2.0945 | 2.1417 | 3.2206 | 3.1323 | 7.7085 | 6.0297 | 17.9496 | 20.0913 | 27.7998 | 33.8295 | 8.844 | 9.1156 | 2.0945 | 2.1417 | 3.2206 | 3.1323 | 7.7085 | 6.0297 | 17.9596 | 20.1013 | 27.8098 | 33.8395 | 0.01
7.3235 | 8.614 | 2.0441 | 2.0662 | 3.2162 | 3.1297 | 7.3309 | 5.5668 | 15.9375 | 18.0037 | 25.3346 | 30.9014 | 7.3335 | 8.614 | 2.0441 | 2.0662 | 3.2162 | 3.1297 | 7.3309 | 5.5668 | 15.9475 | 18.0137 | 25.3446 | 30.9114 | 0.01
7.2969 | 8.2868 | 2.0432 | 2.0648 | 3.2464 | 3.1478 | 7.3242 | 5.2647 | 15.5837 | 17.6485 | 24.9727 | 30.2374 | 7.3069 | 8.2868 | 2.0432 | 2.0648 | 3.2464 | 3.1478 | 7.3242 | 5.2647 | 15.5937 | 17.6585 | 24.9827 | 30.2474 | 0.01
7.4785 | 8.281 | 2.0493 | 2.0739 | 1.9766 | 2.386 | 7.3696 | 5.2594 | 15.7595 | 17.8334 | 25.203 | 30.4624 | 7.4885 | 8.281 | 2.0493 | 2.0739 | 1.9766 | 2.386 | 7.3696 | 5.2594 | 15.7695 | 17.8434 | 25.213 | 30.4724 | 0.01
-0.14037 | 8.3203 | 1.7953 | 1.693 | 2.9701 | 2.9821 | 5.4649 | 5.2957 | 8.18 | 9.873 | 15.8251 | 21.1208 | -0.13037 | 8.3203 | 1.7953 | 1.693 | 2.9701 | 2.9821 | 5.4649 | 5.2957 | 8.19 | 9.883 | 15.8351 | 21.1308 | 0.01
5.8206 | 6.6696 | 1.994 | 1.991 | 1.6681 | 2.2008 | 6.9552 | 3.7719 | 12.4902 | 14.4813 | 21.4364 | 25.2083 | 5.8306 | 6.6696 | 1.994 | 1.991 | 1.6681 | 2.2008 | 6.9552 | 3.7719 | 12.5002 | 14.4913 | 21.4464 | 25.2183 | 0.01
-1.9916 | 7.9611 | 1.7336 | 1.6004 | 4.1051 | 3.6631 | 5.0021 | 4.9641 | 5.9696 | 7.57 | 15.3382 | 20.3023 | -1.9816 | 7.9611 | 1.7336 | 1.6004 | 4.1051 | 3.6631 | 5.0021 | 4.9641 | 5.9796 | 7.58 | 15.3482 | 20.3123 | 0.01
12.6307 | 6.2685 | 2.221 | 2.3315 | 3.1409 | 3.0845 | 8.6577 | 3.4017 | 18.8992 | 21.2308 | 29.8884 | 33.2901 | 12.6407 | 6.2685 | 2.221 | 2.3315 | 3.1409 | 3.0845 | 8.6577 | 3.4017 | 18.9092 | 21.2408 | 29.8984 | 33.3001 | 0.01
6.8453 | 9.4367 | 2.0282 | 2.0423 | 1.4547 | 2.0728 | 7.2113 | 6.3261 | 16.282 | 18.3243 | 25.5356 | 31.8617 | 6.8553 | 9.4367 | 2.0282 | 2.0423 | 1.4547 | 2.0728 | 7.2113 | 6.3261 | 16.292 | 18.3343 | 25.5456 | 31.8717 | 0.01
-3.272 | 8.1832 | 1.6909 | 1.5364 | 2.8971 | 2.9383 | 4.682 | 5.1691 | 4.9112 | 6.4476 | 12.283 | 17.452 | -3.262 | 8.1832 | 1.6909 | 1.5364 | 2.8971 | 2.9383 | 4.682 | 5.1691 | 4.9212 | 6.4576 | 12.293 | 17.462 | 0.01
5.3827 | 5.9911 | 1.9794 | 1.9691 | 4.3756 | 3.8253 | 6.8457 | 3.1456 | 11.3738 | 13.3429 | 21.5439 | 24.6895 | 5.3927 | 5.9911 | 1.9794 | 1.9691 | 4.3756 | 3.8253 | 6.8457 | 3.1456 | 11.3838 | 13.3529 | 21.5539 | 24.6995 | 0.01
14.2535 | 7.8663 | 2.2751 | 2.4127 | 2.174 | 2.5044 | 9.0634 | 4.8765 | 22.1197 | 24.5324 | 33.5958 | 38.4723 | 14.2635 | 7.8663 | 2.2751 | 2.4127 | 2.174 | 2.5044 | 9.0634 | 4.8765 | 22.1297 | 24.5424 | 33.6058 | 38.4823 | 0.01
1.0437 | 9.7882 | 1.8348 | 1.7522 | 2.1204 | 2.4722 | 5.7609 | 6.6507 | 10.832 | 12.5842 | 18.3451 | 24.9958 | 1.0537 | 9.7882 | 1.8348 | 1.7522 | 2.1204 | 2.4722 | 5.7609 | 6.6507 | 10.842 | 12.5942 | 18.3551 | 25.0058 | 0.01
0.72232 | 6.9261 | 1.8241 | 1.7361 | 3.0018 | 3.0011 | 5.6806 | 4.0087 | 7.6485 | 9.3846 | 15.3874 | 19.3962 | 0.73232 | 6.9261 | 1.8241 | 1.7361 | 3.0018 | 3.0011 | 5.6806 | 4.0087 | 7.6585 | 9.3946 | 15.3974 | 19.4062 | 0.01
6.0106 | 6.8565 | 2.0004 | 2.0005 | 2.5764 | 2.7458 | 7.0026 | 3.9445 | 12.8671 | 14.8676 | 21.8703 | 25.8147 | 6.0206 | 6.8565 | 2.0004 | 2.0005 | 2.5764 | 2.7458 | 7.0026 | 3.9445 | 12.8771 | 14.8776 | 21.8803 | 25.8247 | 0.01
3.4584 | 8.0023 | 1.9153 | 1.8729 | 0.37298 | 1.4238 | 6.3646 | 5.0021 | 11.4607 | 13.3337 | 19.6983 | 24.7004 | 3.4684 | 8.0023 | 1.9153 | 1.8729 | 0.37298 | 1.4238 | 6.3646 | 5.0021 | 11.4707 | 13.3437 | 19.7083 | 24.7104 | 0.01
-9.7621 | 7.4493 | 1.4746 | 1.2119 | 2.7077 | 2.8246 | 3.0595 | 4.4917 | -2.3128 | -1.1009 | 4.4314 | 8.9231 | -9.7521 | 7.4493 | 1.4746 | 1.2119 | 2.7077 | 2.8246 | 3.0595 | 4.4917 | -2.3028 | -1.0909 | 4.4414 | 8.9331 | 0.01
4.2463 | 4.5849 | 1.9415 | 1.9123 | 2.3095 | 2.5857 | 6.5616 | 1.8476 | 8.8311 | 10.7435 | 17.305 | 19.1526 | 4.2563 | 4.5849 | 1.9415 | 1.9123 | 2.3095 | 2.5857 | 6.5616 | 1.8476 | 8.8411 | 10.7535 | 17.315 | 19.1626 | 0.01
1.8569 | 7.62 | 1.8619 | 1.7928 | 3.3009 | 3.1806 | 5.9642 | 4.6493 | 9.4769 | 11.2698 | 17.7513 | 22.4005 | 1.8669 | 7.62 | 1.8619 | 1.7928 | 3.3009 | 3.1806 | 5.9642 | 4.6493 | 9.4869 | 11.2798 | 17.7613 | 22.4105 | 0.01
7.8055 | 7.1023 | 2.0602 | 2.0903 | 1.9738 | 2.3843 | 7.4514 | 4.1714 | 14.9079 | 16.9981 | 24.4495 | 28.6209 | 7.8155 | 7.1023 | 2.0602 | 2.0903 | 1.9738 | 2.3843 | 7.4514 | 4.1714 | 14.9179 | 17.0081 | 24.4595 | 28.6309 | 0.01
-0.15737 | 8.3912 | 1.7948 | 1.6921 | 2.3419 | 2.6052 | 5.4607 | 5.3611 | 8.2338 | 9.926 | 15.3866 | 20.7477 | -0.14737 | 8.3912 | 1.7948 | 1.6921 | 2.3419 | 2.6052 | 5.4607 | 5.3611 | 8.2438 | 9.936 | 15.3966 | 20.7577 | 0.01
2.0516 | 6.6659 | 1.8684 | 1.8026 | 4.6939 | 4.0163 | 6.0129 | 3.7685 | 8.7175 | 10.5201 | 19.2303 | 22.9989 | 2.0616 | 6.6659 | 1.8684 | 1.8026 | 4.6939 | 4.0163 | 6.0129 | 3.7685 | 8.7275 | 10.5301 | 19.2403 | 23.0089 | 0.01
16.1634 | 7.1445 | 2.3388 | 2.5082 | 2.4881 | 2.6928 | 9.5409 | 4.2103 | 23.308 | 25.8161 | 35.357 | 39.5673 | 16.1734 | 7.1445 | 2.3388 | 2.5082 | 2.4881 | 2.6928 | 9.5409 | 4.2103 | 23.318 | 25.8261 | 35.367 | 39.5773 | 0.01
2.9283 | 10.2021 | 1.8976 | 1.8464 | 1.8229 | 2.2937 | 6.2321 | 7.0327 | 13.1304 | 14.9768 | 21.2089 | 28.2416 | 2.9383 | 10.2021 | 1.8976 | 1.8464 | 1.8229 | 2.2937 | 6.2321 | 7.0327 | 13.1404 | 14.9868 | 21.2189 | 28.2516 | 0.01
-1.0626 | 7.3345 | 1.7646 | 1.6469 | 3.6826 | 3.4096 | 5.2344 | 4.3857 | 6.2719 | 7.9188 | 15.0109 | 19.3966 | -1.0526 | 7.3345 | 1.7646 | 1.6469 | 3.6826 | 3.4096 | 5.2344 | 4.3857 | 6.2819 | 7.9288 | 15.0209 | 19.4066 | 0.01
10.0956 | 6.4698 | 2.1365 | 2.2048 | 2.7751 | 2.865 | 8.0239 | 3.5875 | 16.5653 | 18.7701 | 26.794 | 30.3815 | 10.1056 | 6.4698 | 2.1365 | 2.2048 | 2.7751 | 2.865 | 8.0239 | 3.5875 | 16.5753 | 18.7801 | 26.804 | 30.3915 | 0.01
4.6504 | 8.8874 | 1.955 | 1.9325 | 4.5711 | 3.9427 | 6.6626 | 5.8191 | 13.5378 | 15.4703 | 23.9841 | 29.8032 | 4.6604 | 8.8874 | 1.955 | 1.9325 | 4.5711 | 3.9427 | 6.6626 | 5.8191 | 13.5478 | 15.4803 | 23.9941 | 29.8132 | 0.01
15.4267 | 7.7076 | 2.3142 | 2.4713 | 4.305 | 3.783 | 9.3567 | 4.7301 | 23.1343 | 25.6057 | 34.9624 | 39.6924 | 15.4367 | 7.7076 | 2.3142 | 2.4713 | 4.305 | 3.783 | 9.3567 | 4.7301 | 23.1443 | 25.6157 | 34.9724 | 39.7024 | 0.01
13.8297 | 10.0425 | 2.261 | 2.3915 | 2.4924 | 2.6954 | 8.9574 | 6.8853 | 23.8722 | 26.2637 | 35.2211 | 42.1065 | 13.8397 | 10.0425 | 2.261 | 2.3915 | 2.4924 | 2.6954 | 8.9574 | 6.8853 | 23.8822 | 26.2737 | 35.2311 | 42.1165 | 0.01
2.9545 | 9.6964 | 1.8985 | 1.8477 | 3.7825 | 3.4695 | 6.2386 | 6.5659 | 12.6509 | 14.4986 | 21.7506 | 28.3166 | 2.9645 | 9.6964 | 1.8985 | 1.8477 | 3.7825 | 3.4695 | 6.2386 | 6.5659 | 12.6609 | 14.5086 | 21.7606 | 28.3266 | 0.01
10.6949 | 7.3401 | 2.1565 | 2.2347 | 2.8622 | 2.9173 | 8.1737 | 4.3909 | 18.035 | 20.2698 | 28.4435 | 32.8344 | 10.7049 | 7.3401 | 2.1565 | 2.2347 | 2.8622 | 2.9173 | 8.1737 | 4.3909 | 18.045 | 20.2798 | 28.4535 | 32.8444 | 0.01
5.1733 | 9.0172 | 1.9724 | 1.9587 | 3.1984 | 3.119 | 6.7933 | 5.939 | 14.1905 | 16.1492 | 22.9425 | 28.8815 | 5.1833 | 9.0172 | 1.9724 | 1.9587 | 3.1984 | 3.119 | 6.7933 | 5.939 | 14.2005 | 16.1592 | 22.9525 | 28.8915 | 0.01
7.1904 | 7.8209 | 2.0397 | 2.0595 | 1.3371 | 2.0022 | 7.2976 | 4.8347 | 15.0112 | 17.0708 | 24.3683 | 29.203 | 7.2004 | 7.8209 | 2.0397 | 2.0595 | 1.3371 | 2.0022 | 7.2976 | 4.8347 | 15.0212 | 17.0808 | 24.3783 | 29.213 | 0.01
-3.9776 | 8.2579 | 1.6674 | 1.5011 | 2.9624 | 2.9775 | 4.5056 | 5.2381 | 4.2803 | 5.7815 | 11.7213 | 16.9594 | -3.9676 | 8.2579 | 1.6674 | 1.5011 | 2.9624 | 2.9775 | 4.5056 | 5.2381 | 4.2903 | 5.7915 | 11.7313 | 16.9694 | 0.01
5.7745 | 5.8382 | 1.9925 | 1.9887 | 3.2345 | 3.1407 | 6.9436 | 3.0045 | 11.6127 | 13.6015 | 20.5451 | 23.5496 | 5.7845 | 5.8382 | 1.9925 | 1.9887 | 3.2345 | 3.1407 | 6.9436 | 3.0045 | 11.6227 | 13.6115 | 20.5551 | 23.5596 | 0.01
7.4073 | 7.9511 | 2.0469 | 2.0704 | 3.9585 | 3.5751 | 7.3518 | 4.9549 | 15.3584 | 17.4288 | 24.9625 | 29.9174 | 7.4173 | 7.9511 | 2.0469 | 2.0704 | 3.9585 | 3.5751 | 7.3518 | 4.9549 | 15.3684 | 17.4388 | 24.9725 | 29.9274 | 0.01
11.7513 | 8.3049 | 2.1917 | 2.2876 | 2.7908 | 2.8745 | 8.4378 | 5.2815 | 20.0562 | 22.3438 | 30.7816 | 36.063 | 11.7613 | 8.3049 | 2.1917 | 2.2876 | 2.7908 | 2.8745 | 8.4378 | 5.2815 | 20.0662 | 22.3538 | 30.7916 | 36.073 | 0.01
4.7449 | 9.2461 | 1.9582 | 1.9372 | 1.7315 | 2.2389 | 6.6862 | 6.1503 | 13.991 | 15.9283 | 22.6145 | 28.7648 | 4.7549 | 9.2461 | 1.9582 | 1.9372 | 1.7315 | 2.2389 | 6.6862 | 6.1503 | 14.001 | 15.9383 | 22.6245 | 28.7748 | 0.01
-1.6111 | 7.7281 | 1.7463 | 1.6194 | 2.8944 | 2.9366 | 5.0972 | 4.749 | 6.1169 | 7.7364 | 13.5674 | 18.3163 | -1.6011 | 7.7281 | 1.7463 | 1.6194 | 2.8944 | 2.9366 | 5.0972 | 4.749 | 6.1269 | 7.7464 | 13.5774 | 18.3263 | 0.01
5.3662 | 6.3509 | 1.9789 | 1.9683 | 3.0773 | 3.0464 | 6.8415 | 3.4778 | 11.7171 | 13.6854 | 20.527 | 24.0047 | 5.3762 | 6.3509 | 1.9789 | 1.9683 | 3.0773 | 3.0464 | 6.8415 | 3.4778 | 11.7271 | 13.6954 | 20.537 | 24.0147 | 0.01
6.4638 | 7.8627 | 2.0155 | 2.0232 | 2.5815 | 2.7489 | 7.116 | 4.8732 | 14.3265 | 16.3497 | 23.4657 | 28.3389 | 6.4738 | 7.8627 | 2.0155 | 2.0232 | 2.5815 | 2.7489 | 7.116 | 4.8732 | 14.3365 | 16.3597 | 23.4757 | 28.3489 | 0.01
3.4889 | 8.1005 | 1.9163 | 1.8744 | 1.8665 | 2.3199 | 6.3722 | 5.0928 | 11.5894 | 13.4638 | 19.836 | 24.9288 | 3.4989 | 8.1005 | 1.9163 | 1.8744 | 1.8665 | 2.3199 | 6.3722 | 5.0928 | 11.5994 | 13.4738 | 19.846 | 24.9388 | 0.01
-0.80079 | 7.4559 | 1.7733 | 1.66 | 4.0774 | 3.6465 | 5.2998 | 4.4978 | 6.6551 | 8.3151 | 16.039 | 20.5368 | -0.79079 | 7.4559 | 1.7733 | 1.66 | 4.0774 | 3.6465 | 5.2998 | 4.4978 | 6.6651 | 8.3251 | 16.049 | 20.5468 | 0.01
12.4646 | 6.5265 | 2.2155 | 2.3232 | 2.1699 | 2.5019 | 8.6161 | 3.6398 | 18.9911 | 21.3143 | 29.9305 | 33.5703 | 12.4746 | 6.5265 | 2.2155 | 2.3232 | 2.1699 | 2.5019 | 8.6161 | 3.6398 | 19.0011 | 21.3243 | 29.9405 | 33.5803 | 0.01
1.0194 | 9.4007 | 1.834 | 1.751 | 4.2351 | 3.7411 | 5.7549 | 6.2929 | 10.4201 | 12.1711 | 20.1472 | 26.4401 | 1.0294 | 9.4007 | 1.834 | 1.751 | 4.2351 | 3.7411 | 5.7549 | 6.2929 | 10.4301 | 12.1811 | 20.1572 | 26.4501 | 0.01
13.4105 | 6.9209 | 2.247 | 2.3705 | 1.9519 | 2.3711 | 8.8526 | 4.0039 | 20.3314 | 22.7019 | 31.5546 | 35.5585 | 13.4205 | 6.9209 | 2.247 | 2.3705 | 1.9519 | 2.3711 | 8.8526 | 4.0039 | 20.3414 | 22.7119 | 31.5646 | 35.5685 | 0.01
-0.28881 | 9.6056 | 1.7904 | 1.6856 | 2.9194 | 2.9516 | 5.4278 | 6.4821 | 9.3168 | 11.0024 | 16.8734 | 23.3555 | -0.27881 | 9.6056 | 1.7904 | 1.6856 | 2.9194 | 2.9516 | 5.4278 | 6.4821 | 9.3268 | 11.0124 | 16.8834 | 23.3655 | 0.01
5.5165 | 6.6374 | 1.9839 | 1.9758 | 3.7465 | 3.4479 | 6.8791 | 3.7422 | 12.1539 | 14.1297 | 21.3241 | 25.0664 | 5.5265 | 6.6374 | 1.9839 | 1.9758 | 3.7465 | 3.4479 | 6.8791 | 3.7422 | 12.1639 | 14.1397 | 21.3341 | 25.0764 | 0.01
10.479 | 7.8952 | 2.1493 | 2.2239 | 2.4963 | 2.6978 | 8.1197 | 4.9033 | 18.3742 | 20.5982 | 28.7179 | 33.6212 | 10.489 | 7.8952 | 2.1493 | 2.2239 | 2.4963 | 2.6978 | 8.1197 | 4.9033 | 18.3842 | 20.6082 | 28.7279 | 33.6312 | 0.01
2.978 | 8.9704 | 1.8993 | 1.8489 | 4.1729 | 3.7037 | 6.2445 | 5.8958 | 11.9484 | 13.7973 | 21.6739 | 27.5697 | 2.988 | 8.9704 | 1.8993 | 1.8489 | 4.1729 | 3.7037 | 6.2445 | 5.8958 | 11.9584 | 13.8073 | 21.6839 | 27.5797 | 0.01
13.0371 | 7.3452 | 2.2346 | 2.3519 | 5.043 | 4.2258 | 8.7593 | 4.3956 | 20.3823 | 22.7342 | 32.0031 | 36.3986 | 13.0471 | 7.3452 | 2.2346 | 2.3519 | 5.043 | 4.2258 | 8.7593 | 4.3956 | 20.3923 | 22.7442 | 32.0131 | 36.4086 | 0.01
18.2582 | 9.5247 | 2.4086 | 2.6129 | 1.3136 | 1.9881 | 10.0646 | 6.4074 | 27.7829 | 30.3958 | 40.4604 | 46.8678 | 18.2682 | 9.5247 | 2.4086 | 2.6129 | 1.3136 | 1.9881 | 10.0646 | 6.4074 | 27.7929 | 30.4058 | 40.4704 | 46.8778 | 0.01
-4.1186 | 10.6559 | 1.6627 | 1.4941 | 3.5481 | 3.3289 | 4.4704 | 7.4516 | 6.5374 | 8.0314 | 14.9084 | 22.36 | -4.1086 | 10.6559 | 1.6627 | 1.4941 | 3.5481 | 3.3289 | 4.4704 | 7.4516 | 6.5474 | 8.0414 | 14.9184 | 22.37 | 0.01
9.2885 | 5.8076 | 2.1096 | 2.1644 | 2.9226 | 2.9536 | 7.8221 | 2.9763 | 15.0962 | 17.2606 | 25.0828 | 28.059 | 9.2985 | 5.8076 | 2.1096 | 2.1644 | 2.9226 | 2.9536 | 7.8221 | 2.9763 | 15.1062 | 17.2706 | 25.0928 | 28.069 | 0.01
5.5355 | 8.7125 | 1.9845 | 1.9768 | 5.2821 | 4.3692 | 6.8839 | 5.6577 | 14.2481 | 16.2248 | 25.8761 | 31.5339 | 5.5455 | 8.7125 | 1.9845 | 1.9768 | 5.2821 | 4.3692 | 6.8839 | 5.6577 | 14.2581 | 16.2348 | 25.8861 | 31.5439 | 0.01
19.6924 | 7.8994 | 2.4564 | 2.6846 | 1.3027 | 1.9816 | 10.4231 | 4.9071 | 27.5918 | 30.2764 | 40.6995 | 45.6066 | 19.7024 | 7.8994 | 2.4564 | 2.6846 | 1.3027 | 1.9816 | 10.4231 | 4.9071 | 27.6018 | 30.2864 | 40.7095 | 45.6166 | 0.01
-4.1837 | 10.9667 | 1.6605 | 1.4908 | 2.4833 | 2.69 | 4.4541 | 7.7385 | 6.7829 | 8.2738 | 13.447 | 21.1855 | -4.1737 | 10.9667 | 1.6605 | 1.4908 | 2.4833 | 2.69 | 4.4541 | 7.7385 | 6.7929 | 8.2838 | 13.457 | 21.1955 | 0.01
2.8996 | 5.7935 | 1.8967 | 1.845 | 4.6737 | 4.0042 | 6.2249 | 2.9633 | 8.6931 | 10.5381 | 19.216 | 22.1792 | 2.9096 | 5.7935 | 1.8967 | 1.845 | 4.6737 | 4.0042 | 6.2249 | 2.9633 | 8.7031 | 10.5481 | 19.226 | 22.1892 | 0.01
16.0422 | 7.3282 | 2.3347 | 2.5021 | 2.969 | 2.9814 | 9.5106 | 4.3799 | 23.3705 | 25.8726 | 35.3831 | 39.7631 | 16.0522 | 7.3282 | 2.3347 | 2.5021 | 2.969 | 2.9814 | 9.5106 | 4.3799 | 23.3805 | 25.8826 | 35.3931 | 39.7731 | 0.01
5.8138 | 10.1758 | 1.9938 | 1.9907 | 2.7846 | 2.8708 | 6.9534 | 7.0084 | 15.9896 | 17.9803 | 24.9337 | 31.9422 | 5.8238 | 10.1758 | 1.9938 | 1.9907 | 2.7846 | 2.8708 | 6.9534 | 7.0084 | 15.9996 | 17.9903 | 24.9437 | 31.9522 | 0.01
4.7076 | 7.9596 | 1.9569 | 1.9354 | 2.5954 | 2.7572 | 6.6769 | 4.9628 | 12.6673 | 14.6026 | 21.2795 | 26.2423 | 4.7176 | 7.9596 | 1.9569 | 1.9354 | 2.5954 | 2.7572 | 6.6769 | 4.9628 | 12.6773 | 14.6126 | 21.2895 | 26.2523 | 0.01
3.5724 | 7.72 | 1.9191 | 1.8786 | 4.397 | 3.8382 | 6.3931 | 4.7415 | 11.2924 | 13.171 | 21.4063 | 26.1478 | 3.5824 | 7.72 | 1.9191 | 1.8786 | 4.397 | 3.8382 | 6.3931 | 4.7415 | 11.3024 | 13.181 | 21.4163 | 26.1578 | 0.01
14.3822 | 7.474 | 2.2794 | 2.4191 | 2.2841 | 2.5705 | 9.0955 | 4.5145 | 21.8562 | 24.2753 | 33.3709 | 37.8854 | 14.3922 | 7.474 | 2.2794 | 2.4191 | 2.2841 | 2.5705 | 9.0955 | 4.5145 | 21.8662 | 24.2853 | 33.3809 | 37.8954 | 0.01
1.7047 | 9.8161 | 1.8568 | 1.7852 | 3.83 | 3.498 | 5.9262 | 6.6764 | 11.5209 | 13.3061 | 20.6341 | 27.3105 | 1.7147 | 9.8161 | 1.8568 | 1.7852 | 3.83 | 3.498 | 5.9262 | 6.6764 | 11.5309 | 13.3161 | 20.6441 | 27.3205 | 0.01
10.98 | 7.0694 | 2.166 | 2.249 | 3.431 | 3.2586 | 8.245 | 4.1409 | 18.0494 | 20.2984 | 28.5434 | 32.6843 | 10.99 | 7.0694 | 2.166 | 2.249 | 3.431 | 3.2586 | 8.245 | 4.1409 | 18.0594 | 20.3084 | 28.5534 | 32.6943 | 0.01
8.5858 | 9.079 | 2.0862 | 2.1293 | 2.0667 | 2.44 | 7.6465 | 5.996 | 17.6648 | 19.7941 | 27.4406 | 33.4366 | 8.5958 | 9.079 | 2.0862 | 2.1293 | 2.0667 | 2.44 | 7.6465 | 5.996 | 17.6748 | 19.8041 | 27.4506 | 33.4466 | 0.01
0.40007 | 8.5603 | 1.8133 | 1.72 | 3.5941 | 3.3565 | 5.6 | 5.5172 | 8.9603 | 10.6803 | 17.6309 | 23.1481 | 0.41007 | 8.5603 | 1.8133 | 1.72 | 3.5941 | 3.3565 | 5.6 | 5.5172 | 8.9703 | 10.6903 | 17.6409 | 23.1581 | 0.01
9.5647 | 6.7867 | 2.1188 | 2.1782 | 3.2553 | 3.1532 | 7.8912 | 3.88 | 16.3514 | 18.5296 | 26.4208 | 30.3008 | 9.5747 | 6.7867 | 2.1188 | 2.1782 | 3.2553 | 3.1532 | 7.8912 | 3.88 | 16.3614 | 18.5396 | 26.4308 | 30.3108 | 0.01
7.5316 | 8.7723 | 2.0511 | 2.0766 | 3.3519 | 3.2111 | 7.3829 | 5.7129 | 16.3039 | 18.3805 | 25.7634 | 31.4763 | 7.5416 | 8.7723 | 2.0511 | 2.0766 | 3.3519 | 3.2111 | 7.3829 | 5.7129 | 16.3139 | 18.3905 | 25.7734 | 31.4863 | 0.01
8.1115 | 8.3318 | 2.0704 | 2.1056 | 2.3366 | 2.602 | 7.5279 | 5.3063 | 16.4433 | 18.5489 | 26.0767 | 31.3831 | 8.1215 | 8.3318 | 2.0704 | 2.1056 | 2.3366 | 2.602 | 7.5279 | 5.3063 | 16.4533 | 18.5589 | 26.0867 | 31.3931 | 0.01
2.0197 | 8.4575 | 1.8673 | 1.801 | 2.4549 | 2.6729 | 6.0049 | 5.4223 | 10.4772 | 12.2782 | 18.2831 | 23.7054 | 2.0297 | 8.4575 | 1.8673 | 1.801 | 2.4549 | 2.6729 | 6.0049 | 5.4223 | 10.4872 | 12.2882 | 18.2931 | 23.7154 | 0.01
2.7292 | 7.1376 | 1.891 | 1.8365 | 3.3007 | 3.1804 | 6.1823 | 4.2039 | 9.8668 | 11.7033 | 18.1844 | 22.3883 | 2.7392 | 7.1376 | 1.891 | 1.8365 | 3.3007 | 3.1804 | 6.1823 | 4.2039 | 9.8768 | 11.7133 | 18.1944 | 22.3983 | 0.01
7.8041 | 7.2913 | 2.0601 | 2.0902 | 3.2421 | 3.1452 | 7.451 | 4.3458 | 15.0954 | 17.1856 | 24.6366 | 28.9825 | 7.8141 | 7.2913 | 2.0601 | 2.0902 | 3.2421 | 3.1452 | 7.451 | 4.3458 | 15.1054 | 17.1956 | 24.6466 | 28.9925 | 0.01
7.4524 | 8.3909 | 2.0484 | 2.0726 | 3.8806 | 3.5284 | 7.3631 | 5.3608 | 15.8432 | 17.9159 | 25.3248 | 30.6856 | 7.4624 | 8.3909 | 2.0484 | 2.0726 | 3.8806 | 3.5284 | 7.3631 | 5.3608 | 15.8532 | 17.9259 | 25.3348 | 30.6956 | 0.01
11.2836 | 8.3147 | 2.1761 | 2.2642 | 5.2907 | 4.3744 | 8.3209 | 5.2905 | 19.5983 | 21.8625 | 31.5276 | 36.8181 | 11.2936 | 8.3147 | 2.1761 | 2.2642 | 5.2907 | 4.3744 | 8.3209 | 5.2905 | 19.6083 | 21.8725 | 31.5376 | 36.8281 | 0.01
19.7442 | 9.1448 | 2.4581 | 2.6872 | 2.4446 | 2.6667 | 10.4361 | 6.0567 | 28.889 | 31.5762 | 42.0123 | 48.069 | 19.7542 | 9.1448 | 2.4581 | 2.6872 | 2.4446 | 2.6667 | 10.4361 | 6.0567 | 28.899 | 31.5862 | 42.0223 | 48.079 | 0.01
2.6675 | 10.9779 | 1.8889 | 1.8334 | 2.5403 | 2.7242 | 6.1669 | 7.7488 | 13.6454 | 15.4788 | 21.6456 | 29.3945 | 2.6775 | 10.9779 | 1.8889 | 1.8334 | 2.5403 | 2.7242 | 6.1669 | 7.7488 | 13.6554 | 15.4888 | 21.6556 | 29.4045 | 0.01
3.2415 | 7.278 | 1.9081 | 1.8621 | 1.9326 | 2.3596 | 6.3104 | 4.3335 | 10.5195 | 12.3816 | 18.692 | 23.0255 | 3.2515 | 7.278 | 1.9081 | 1.8621 | 1.9326 | 2.3596 | 6.3104 | 4.3335 | 10.5295 | 12.3916 | 18.702 | 23.0355 | 0.01
-0.40435 | 7.4023 | 1.7865 | 1.6798 | 3.4463 | 3.2678 | 5.3989 | 4.4483 | 6.998 | 8.6778 | 15.3919 | 19.8402 | -0.39435 | 7.4023 | 1.7865 | 1.6798 | 3.4463 | 3.2678 | 5.3989 | 4.4483 | 7.008 | 8.6878 | 15.4019 | 19.8502 | 0.01
1

## test activity B
A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | diff
-12.9745 | 3.8889 | 1.3675 | 1.0513 | -0.16242 | 1.1025 | 2.2564 | 1.2051 | -9.0857 | -8.0344 | -5.778 | -4.5729 | -12.9745 | 3.8989 | 1.3675 | 1.0513 | -0.16242 | 1.1025 | 2.2564 | 1.2051 | -9.0757 | -8.0244 | -5.768 | -4.5629 | 0.01
-0.12216 | 6.6735 | 1.7959 | 1.6939 | 1.9796 | 2.3878 | 5.4695 | 3.7756 | 6.5514 | 8.2453 | 13.7147 | 17.4903 | -0.12216 | 6.6835 | 1.7959 | 1.6939 | 1.9796 | 2.3878 | 5.4695 | 3.7756 | 6.5614 | 8.2553 | 13.7247 | 17.5003 | 0.01
6.9139 | 8.198 | 2.0305 | 2.0457 | 3.1523 | 3.0914 | 7.2285 | 5.1828 | 15.1119 | 17.1576 | 24.3861 | 29.5689 | 6.9139 | 8.208 | 2.0305 | 2.0457 | 3.1523 | 3.0914 | 7.2285 | 5.1828 | 15.1219 | 17.1676 | 24.3961 | 29.5789 | 0.01
12.6187 | 9.4341 | 2.2206 | 2.3309 | 4.1031 | 3.6619 | 8.6547 | 6.3237 | 22.0528 | 24.3837 | 33.0384 | 39.3622 | 12.6187 | 9.4441 | 2.2206 | 2.3309 | 4.1031 | 3.6619 | 8.6547 | 6.3237 | 22.0628 | 24.3937 | 33.0484 | 39.3722 | 0.01
2.4444 | 7.2296 | 1.8815 | 1.8222 | 2.4074 | 2.6444 | 6.1111 | 4.2889 | 9.674 | 11.4962 | 17.6073 | 21.8962 | 2.4444 | 7.2396 | 1.8815 | 1.8222 | 2.4074 | 2.6444 | 6.1111 | 4.2889 | 9.684 | 11.5062 | 17.6173 | 21.9062 | 0.01
13.5518 | 9.6362 | 2.2517 | 2.3776 | 4.2586 | 3.7552 | 8.888 | 6.5104 | 23.188 | 25.5656 | 34.4536 | 40.9639 | 13.5518 | 9.6462 | 2.2517 | 2.3776 | 4.2586 | 3.7552 | 8.888 | 6.5104 | 23.198 | 25.5756 | 34.4636 | 40.9739 | 0.01
9.2237 | 8.6985 | 2.1075 | 2.1612 | 3.5373 | 3.3224 | 7.8059 | 5.6447 | 17.9221 | 20.0833 | 27.8892 | 33.5339 | 9.2237 | 8.7085 | 2.1075 | 2.1612 | 3.5373 | 3.3224 | 7.8059 | 5.6447 | 17.9321 | 20.0933 | 27.8992 | 33.5439 | 0.01
13.2479 | 9.5704 | 2.2416 | 2.3624 | 4.208 | 3.7248 | 8.812 | 6.4496 | 22.8182 | 25.1806 | 33.9926 | 40.4422 | 13.2479 | 9.5804 | 2.2416 | 2.3624 | 4.208 | 3.7248 | 8.812 | 6.4496 | 22.8282 | 25.1906 | 34.0026 | 40.4522 | 0.01
14.8387 | 9.9151 | 2.2946 | 2.4419 | 4.4731 | 3.8839 | 9.2097 | 6.7677 | 24.7538 | 27.1957 | 36.4054 | 43.1731 | 14.8387 | 9.9251 | 2.2946 | 2.4419 | 4.4731 | 3.8839 | 9.2097 | 6.7677 | 24.7638 | 27.2057 | 36.4154 | 43.1831 | 0.01
5.5377 | 7.8998 | 1.9846 | 1.9769 | 2.9229 | 2.9538 | 6.8844 | 4.9075 | 13.4375 | 15.4144 | 22.2988 | 27.2063 | 5.5377 | 7.9098 | 1.9846 | 1.9769 | 2.9229 | 2.9538 | 6.8844 | 4.9075 | 13.4475 | 15.4244 | 22.3088 | 27.2163 | 0.01
3.6914 | 7.4998 | 1.923 | 1.8846 | 2.6152 | 2.7691 | 6.4229 | 4.5383 | 11.1913 | 13.0758 | 19.4987 | 24.037 | 3.6914 | 7.5098 | 1.923 | 1.8846 | 2.6152 | 2.7691 | 6.4229 | 4.5383 | 11.2013 | 13.0858 | 19.5087 | 24.047 | 0.01
15.412 | 10.0393 | 2.3137 | 2.4706 | 4.5687 | 3.9412 | 9.353 | 6.8824 | 25.4513 | 27.9219 | 37.2749 | 44.1573 | 15.412 | 10.0493 | 2.3137 | 2.4706 | 4.5687 | 3.9412 | 9.353 | 6.8824 | 25.4613 | 27.9319 | 37.2849 | 44.1673 | 0.01
-1.8093 | 6.308 | 1.7397 | 1.6095 | 1.6984 | 2.2191 | 5.0477 | 3.4381 | 4.4986 | 6.1082 | 11.1558 | 14.594 | -1.8093 | 6.318 | 1.7397 | 1.6095 | 1.6984 | 2.2191 | 5.0477 | 3.4381 | 4.5086 | 6.1182 | 11.1658 | 14.604 | 0.01
5.3552 | 7.8603 | 1.9785 | 1.9678 | 2.8925 | 2.9355 | 6.8388 | 4.871 | 13.2155 | 15.1833 | 22.0221 | 26.8931 | 5.3552 | 7.8703 | 1.9785 | 1.9678 | 2.8925 | 2.9355 | 6.8388 | 4.871 | 13.2255 | 15.1933 | 22.0321 | 26.9031 | 0.01
3.6258 | 7.4856 | 1.9209 | 1.8813 | 2.6043 | 2.7626 | 6.4065 | 4.5252 | 11.1114 | 12.9927 | 19.3991 | 23.9243 | 3.6258 | 7.4956 | 1.9209 | 1.8813 | 2.6043 | 2.7626 | 6.4065 | 4.5252 | 11.1214 | 13.0027 | 19.4091 | 23.9343 | 0.01
17.2865 | 10.4454 | 2.3762 | 2.5643 | 4.8811 | 4.1286 | 9.8216 | 7.2573 | 27.7319 | 30.2962 | 40.1178 | 47.3751 | 17.2865 | 10.4554 | 2.3762 | 2.5643 | 4.8811 | 4.1286 | 9.8216 | 7.2573 | 27.7419 | 30.3062 | 40.1278 | 47.3851 | 0.01
-1.2041 | 6.4391 | 1.7599 | 1.6398 | 1.7993 | 2.2796 | 5.199 | 3.5592 | 5.2351 | 6.8749 | 12.0738 | 15.633 | -1.2041 | 6.4491 | 1.7599 | 1.6398 | 1.7993 | 2.2796 | 5.199 | 3.5592 | 5.2451 | 6.8849 | 12.0838 | 15.643 | 0.01
10.4295 | 8.9597 | 2.1476 | 2.2215 | 3.7382 | 3.4429 | 8.1074 | 5.8859 | 19.3892 | 21.6107 | 29.7181 | 35.604 | 10.4295 | 8.9697 | 2.1476 | 2.2215 | 3.7382 | 3.4429 | 8.1074 | 5.8859 | 19.3992 | 21.6207 | 29.7281 | 35.614 | 0.01
3.5508 | 7.4693 | 1.9184 | 1.8775 | 2.5918 | 2.7551 | 6.3877 | 4.5102 | 11.0202 | 12.8977 | 19.2854 | 23.7956 | 3.5508 | 7.4793 | 1.9184 | 1.8775 | 2.5918 | 2.7551 | 6.3877 | 4.5102 | 11.0302 | 12.9077 | 19.2954 | 23.8056 | 0.01
8.8773 | 8.6234 | 2.0959 | 2.1439 | 3.4795 | 3.2877 | 7.7193 | 5.5755 | 17.5007 | 19.6445 | 27.3638 | 32.9393 | 8.8773 | 8.6334 | 2.0959 | 2.1439 | 3.4795 | 3.2877 | 7.7193 | 5.5755 | 17.5107 | 19.6545 | 27.3738 | 32.9493 | 0.01
10.0205 | 8.8711 | 2.134 | 2.201 | 3.6701 | 3.402 | 8.0051 | 5.8041 | 18.8916 | 21.0926 | 29.0977 | 34.9018 | 10.0205 | 8.8811 | 2.134 | 2.201 | 3.6701 | 3.402 | 8.0051 | 5.8041 | 18.9016 | 21.1026 | 29.1077 | 34.9118 | 0.01
8.7605 | 8.5981 | 2.092 | 2.138 | 3.4601 | 3.276 | 7.6901 | 5.5521 | 17.3586 | 19.4966 | 27.1867 | 32.7388 | 8.7605 | 8.6081 | 2.092 | 2.138 | 3.4601 | 3.276 | 7.6901 | 5.5521 | 17.3686 | 19.5066 | 27.1967 | 32.7488 | 0.01
13.6101 | 9.6489 | 2.2537 | 2.3805 | 4.2684 | 3.761 | 8.9025 | 6.522 | 23.259 | 25.6395 | 34.542 | 41.064 | 13.6101 | 9.6589 | 2.2537 | 2.3805 | 4.2684 | 3.761 | 8.9025 | 6.522 | 23.269 | 25.6495 | 34.552 | 41.074 | 0.01
-4.2589 | 5.7772 | 1.658 | 1.4871 | 1.2902 | 1.9741 | 4.4353 | 2.9482 | 1.5183 | 3.0053 | 7.4406 | 10.3888 | -4.2589 | 5.7872 | 1.658 | 1.4871 | 1.2902 | 1.9741 | 4.4353 | 2.9482 | 1.5283 | 3.0153 | 7.4506 | 10.3988 | 0.01
7.7808 | 8.3858 | 2.0594 | 2.089 | 3.2968 | 3.1781 | 7.4452 | 5.3562 | 16.1666 | 18.2557 | 25.7008 | 31.057 | 7.7808 | 8.3958 | 2.0594 | 2.089 | 3.2968 | 3.1781 | 7.4452 | 5.3562 | 16.1766 | 18.2657 | 25.7108 | 31.067 | 0.01
9.0241 | 8.6552 | 2.1008 | 2.1512 | 3.504 | 3.3024 | 7.756 | 5.6048 | 17.6794 | 19.8306 | 27.5866 | 33.1914 | 9.0241 | 8.6652 | 2.1008 | 2.1512 | 3.504 | 3.3024 | 7.756 | 5.6048 | 17.6894 | 19.8406 | 27.5966 | 33.2014 | 0.01
0.87462 | 6.8895 | 1.8292 | 1.7437 | 2.1458 | 2.4875 | 5.7187 | 3.9749 | 7.7641 | 9.5079 | 15.2265 | 19.2014 | 0.87462 | 6.8995 | 1.8292 | 1.7437 | 2.1458 | 2.4875 | 5.7187 | 3.9749 | 7.7741 | 9.5179 | 15.2365 | 19.2114 | 0.01
4.3537 | 7.6433 | 1.9451 | 1.9177 | 2.7256 | 2.8354 | 6.5884 | 4.6707 | 11.997 | 13.9147 | 20.5031 | 25.1739 | 4.3537 | 7.6533 | 1.9451 | 1.9177 | 2.7256 | 2.8354 | 6.5884 | 4.6707 | 12.007 | 13.9247 | 20.5131 | 25.1839 | 0.01
7.5191 | 8.3291 | 2.0506 | 2.076 | 3.2532 | 3.1519 | 7.3798 | 5.3038 | 15.8482 | 17.9242 | 25.3039 | 30.6078 | 7.5191 | 8.3391 | 2.0506 | 2.076 | 3.2532 | 3.1519 | 7.3798 | 5.3038 | 15.8582 | 17.9342 | 25.3139 | 30.6178 | 0.01
-1.0782 | 6.4664 | 1.7641 | 1.6461 | 1.8203 | 2.2922 | 5.2304 | 3.5844 | 5.3882 | 7.0343 | 12.2647 | 15.8491 | -1.0782 | 6.4764 | 1.7641 | 1.6461 | 1.8203 | 2.2922 | 5.2304 | 3.5844 | 5.3982 | 7.0443 | 12.2747 | 15.8591 | 0.01
-5.1061 | 5.5937 | 1.6298 | 1.4447 | 1.149 | 1.8894 | 4.2235 | 2.7788 | 0.48754 | 1.9322 | 6.1557 | 8.9345 | -5.1061 | 5.6037 | 1.6298 | 1.4447 | 1.149 | 1.8894 | 4.2235 | 2.7788 | 0.49754 | 1.9422 | 6.1657 | 8.9445 | 0.01
1.3629 | 6.9953 | 1.8454 | 1.7681 | 2.2271 | 2.5363 | 5.8407 | 4.0726 | 8.3582 | 10.1263 | 15.967 | 20.0396 | 1.3629 | 7.0053 | 1.8454 | 1.7681 | 2.2271 | 2.5363 | 5.8407 | 4.0726 | 8.3682 | 10.1363 | 15.977 | 20.0496 | 0.01
1.8639 | 7.1038 | 1.8621 | 1.7932 | 2.3106 | 2.5864 | 5.966 | 4.1728 | 8.9677 | 10.7609 | 16.7269 | 20.8996 | 1.8639 | 7.1138 | 1.8621 | 1.7932 | 2.3106 | 2.5864 | 5.966 | 4.1728 | 8.9777 | 10.7709 | 16.7369 | 20.9096 | 0.01
9.9802 | 8.8624 | 2.1327 | 2.199 | 3.6634 | 3.398 | 7.995 | 5.796 | 18.8426 | 21.0416 | 29.0366 | 34.8327 | 9.9802 | 8.8724 | 2.1327 | 2.199 | 3.6634 | 3.398 | 7.995 | 5.796 | 18.8526 | 21.0516 | 29.0466 | 34.8427 | 0.01
7.6476 | 8.357 | 2.0549 | 2.0824 | 3.2746 | 3.1648 | 7.4119 | 5.3295 | 16.0046 | 18.087 | 25.4989 | 30.8284 | 7.6476 | 8.367 | 2.0549 | 2.0824 | 3.2746 | 3.1648 | 7.4119 | 5.3295 | 16.0146 | 18.097 | 25.5089 | 30.8384 | 0.01
11.5709 | 9.207 | 2.1857 | 2.2785 | 3.9285 | 3.5571 | 8.3927 | 6.1142 | 20.778 | 23.0565 | 31.4492 | 37.5634 | 11.5709 | 9.217 | 2.1857 | 2.2785 | 3.9285 | 3.5571 | 8.3927 | 6.1142 | 20.788 | 23.0665 | 31.4592 | 37.5734 | 0.01
2.211 | 7.179 | 1.8737 | 1.8105 | 2.3685 | 2.6211 | 6.0527 | 4.2422 | 9.39 | 11.2006 | 17.2533 | 21.4955 | 2.211 | 7.189 | 1.8737 | 1.8105 | 2.3685 | 2.6211 | 6.0527 | 4.2422 | 9.4 | 11.2106 | 17.2633 | 21.5055 | 0.01
8.1676 | 8.4696 | 2.0723 | 2.1084 | 3.3613 | 3.2168 | 7.5419 | 5.4335 | 16.6372 | 18.7456 | 26.2875 | 31.721 | 8.1676 | 8.4796 | 2.0723 | 2.1084 | 3.3613 | 3.2168 | 7.5419 | 5.4335 | 16.6472 | 18.7556 | 26.2975 | 31.731 | 0.01
-1.5632 | 6.3613 | 1.7479 | 1.6218 | 1.7395 | 2.2437 | 5.1092 | 3.4874 | 4.7981 | 6.42 | 11.5292 | 15.0165 | -1.5632 | 6.3713 | 1.7479 | 1.6218 | 1.7395 | 2.2437 | 5.1092 | 3.4874 | 4.8081 | 6.43 | 11.5392 | 15.0265 | 0.01
6.51 | 8.1105 | 2.017 | 2.0255 | 3.085 | 3.051 | 7.1275 | 5.102 | 14.6205 | 16.646 | 23.7735 | 28.8754 | 6.51 | 8.1205 | 2.017 | 2.0255 | 3.085 | 3.051 | 7.1275 | 5.102 | 14.6305 | 16.656 | 23.7835 | 28.8854 | 0.01
9.2137 | 8.6963 | 2.1071 | 2.1607 | 3.5356 | 3.3214 | 7.8034 | 5.6427 | 17.91 | 20.0707 | 27.8741 | 33.5169 | 9.2137 | 8.7063 | 2.1071 | 2.1607 | 3.5356 | 3.3214 | 7.8034 | 5.6427 | 17.92 | 20.0807 | 27.8841 | 33.5269 | 0.01
2.0475 | 7.1436 | 1.8683 | 1.8024 | 2.3413 | 2.6048 | 6.0119 | 4.2095 | 9.1911 | 10.9935 | 17.0054 | 21.2149 | 2.0475 | 7.1536 | 1.8683 | 1.8024 | 2.3413 | 2.6048 | 6.0119 | 4.2095 | 9.2011 | 11.0035 | 17.0154 | 21.2249 | 0.01
2.251 | 7.1877 | 1.875 | 1.8125 | 2.3752 | 2.6251 | 6.0627 | 4.2502 | 9.4387 | 11.2513 | 17.314 | 21.5642 | 2.251 | 7.1977 | 1.875 | 1.8125 | 2.3752 | 2.6251 | 6.0627 | 4.2502 | 9.4487 | 11.2613 | 17.324 | 21.5742 | 0.01
3.4527 | 7.4481 | 1.9151 | 1.8726 | 2.5755 | 2.7453 | 6.3632 | 4.4905 | 10.9008 | 12.7734 | 19.1366 | 23.6272 | 3.4527 | 7.4581 | 1.9151 | 1.8726 | 2.5755 | 2.7453 | 6.3632 | 4.4905 | 10.9108 | 12.7834 | 19.1466 | 23.6372 | 0.01
-0.171 | 6.663 | 1.7943 | 1.6915 | 1.9715 | 2.3829 | 5.4573 | 3.7658 | 6.492 | 8.1834 | 13.6407 | 17.4065 | -0.171 | 6.673 | 1.7943 | 1.6915 | 1.9715 | 2.3829 | 5.4573 | 3.7658 | 6.502 | 8.1934 | 13.6507 | 17.4165 | 0.01
2.2975 | 7.1978 | 1.8766 | 1.8149 | 2.3829 | 2.6297 | 6.0744 | 4.2595 | 9.4953 | 11.3101 | 17.3845 | 21.644 | 2.2975 | 7.2078 | 1.8766 | 1.8149 | 2.3829 | 2.6297 | 6.0744 | 4.2595 | 9.5053 | 11.3201 | 17.3945 | 21.654 | 0.01
0.11826 | 6.7256 | 1.8039 | 1.7059 | 2.0197 | 2.4118 | 5.5296 | 3.8237 | 6.8439 | 8.5498 | 14.0794 | 17.903 | 0.11826 | 6.7356 | 1.8039 | 1.7059 | 2.0197 | 2.4118 | 5.5296 | 3.8237 | 6.8539 | 8.5598 | 14.0894 | 17.913 | 0.01
5.5591 | 7.9045 | 1.9853 | 1.978 | 2.9265 | 2.9559 | 6.8898 | 4.9118 | 13.4636 | 15.4416 | 22.3313 | 27.2432 | 5.5591 | 7.9145 | 1.9853 | 1.978 | 2.9265 | 2.9559 | 6.8898 | 4.9118 | 13.4736 | 15.4516 | 22.3413 | 27.2532 | 0.01
2.3412 | 7.2073 | 1.878 | 1.8171 | 2.3902 | 2.6341 | 6.0853 | 4.2682 | 9.5484 | 11.3655 | 17.4508 | 21.719 | 2.3412 | 7.2173 | 1.878 | 1.8171 | 2.3902 | 2.6341 | 6.0853 | 4.2682 | 9.5584 | 11.3755 | 17.4608 | 21.729 | 0.01
8.1691 | 8.47 | 2.0723 | 2.1085 | 3.3615 | 3.2169 | 7.5423 | 5.4338 | 16.639 | 18.7475 | 26.2897 | 31.7235 | 8.1691 | 8.48 | 2.0723 | 2.1085 | 3.3615 | 3.2169 | 7.5423 | 5.4338 | 16.649 | 18.7575 | 26.2997 | 31.7335 | 0.01
8.3035 | 8.4991 | 2.0768 | 2.1152 | 3.3839 | 3.2303 | 7.5759 | 5.4607 | 16.8026 | 18.9177 | 26.4936 | 31.9543 | 8.3035 | 8.5091 | 2.0768 | 2.1152 | 3.3839 | 3.2303 | 7.5759 | 5.4607 | 16.8126 | 18.9277 | 26.5036 | 31.9643 | 0.01
10.4961 | 8.9742 | 2.1499 | 2.2248 | 3.7493 | 3.4496 | 8.124 | 5.8992 | 19.4702 | 21.695 | 29.8191 | 35.7183 | 10.4961 | 8.9842 | 2.1499 | 2.2248 | 3.7493 | 3.4496 | 8.124 | 5.8992 | 19.4802 | 21.705 | 29.8291 | 35.7283 | 0.01
10.5815 | 8.9927 | 2.1527 | 2.2291 | 3.7636 | 3.4582 | 8.1454 | 5.9163 | 19.5742 | 21.8033 | 29.9486 | 35.8649 | 10.5815 | 9.0027 | 2.1527 | 2.2291 | 3.7636 | 3.4582 | 8.1454 | 5.9163 | 19.5842 | 21.8133 | 29.9586 | 35.8749 | 0.01
5.8599 | 7.9696 | 1.9953 | 1.993 | 2.9766 | 2.986 | 6.965 | 4.972 | 13.8295 | 15.8225 | 22.7875 | 27.7595 | 5.8599 | 7.9796 | 1.9953 | 1.993 | 2.9766 | 2.986 | 6.965 | 4.972 | 13.8395 | 15.8325 | 22.7975 | 27.7695 | 0.01
14.7012 | 9.8853 | 2.29 | 2.4351 | 4.4502 | 3.8701 | 9.1753 | 6.7402 | 24.5864 | 27.0215 | 36.1968 | 42.937 | 14.7012 | 9.8953 | 2.29 | 2.4351 | 4.4502 | 3.8701 | 9.1753 | 6.7402 | 24.5964 | 27.0315 | 36.2068 | 42.947 | 0.01
8.3236 | 8.5034 | 2.0775 | 2.1162 | 3.3873 | 3.2324 | 7.5809 | 5.4647 | 16.827 | 18.9432 | 26.5241 | 31.9888 | 8.3236 | 8.5134 | 2.0775 | 2.1162 | 3.3873 | 3.2324 | 7.5809 | 5.4647 | 16.837 | 18.9532 | 26.5341 | 31.9988 | 0.01
8.3401 | 8.507 | 2.078 | 2.117 | 3.39 | 3.234 | 7.585 | 5.468 | 16.8471 | 18.9641 | 26.5492 | 32.0172 | 8.3401 | 8.517 | 2.078 | 2.117 | 3.39 | 3.234 | 7.585 | 5.468 | 16.8571 | 18.9741 | 26.5592 | 32.0272 | 0.01
10.3472 | 8.9419 | 2.1449 | 2.2174 | 3.7245 | 3.4347 | 8.0868 | 5.8694 | 19.289 | 21.5064 | 29.5932 | 35.4626 | 10.3472 | 8.9519 | 2.1449 | 2.2174 | 3.7245 | 3.4347 | 8.0868 | 5.8694 | 19.299 | 21.5164 | 29.6032 | 35.4726 | 0.01
14.4633 | 9.8337 | 2.2821 | 2.4232 | 4.4105 | 3.8463 | 9.1158 | 6.6927 | 24.297 | 26.7201 | 35.836 | 42.5286 | 14.4633 | 9.8437 | 2.2821 | 2.4232 | 4.4105 | 3.8463 | 9.1158 | 6.6927 | 24.307 | 26.7301 | 35.846 | 42.5386 | 0.01
-3.5127 | 5.9389 | 1.6829 | 1.5244 | 1.4146 | 2.0487 | 4.6218 | 3.0975 | 2.4263 | 3.9506 | 8.5725 | 11.6699 | -3.5127 | 5.9489 | 1.6829 | 1.5244 | 1.4146 | 2.0487 | 4.6218 | 3.0975 | 2.4363 | 3.9606 | 8.5825 | 11.6799 | 0.01
5.4776 | 7.8868 | 1.9826 | 1.9739 | 2.9129 | 2.9478 | 6.8694 | 4.8955 | 13.3644 | 15.3383 | 22.2077 | 27.1032 | 5.4776 | 7.8968 | 1.9826 | 1.9739 | 2.9129 | 2.9478 | 6.8694 | 4.8955 | 13.3744 | 15.3483 | 22.2177 | 27.1132 | 0.01
5.2807 | 7.8442 | 1.976 | 1.964 | 2.8801 | 2.9281 | 6.8202 | 4.8561 | 13.1249 | 15.0889 | 21.9091 | 26.7653 | 5.2807 | 7.8542 | 1.976 | 1.964 | 2.8801 | 2.9281 | 6.8202 | 4.8561 | 13.1349 | 15.0989 | 21.9191 | 26.7753 | 0.01
7.9784 | 8.4286 | 2.0659 | 2.0989 | 3.3297 | 3.1978 | 7.4946 | 5.3957 | 16.407 | 18.5059 | 26.0005 | 31.3962 | 7.9784 | 8.4386 | 2.0659 | 2.0989 | 3.3297 | 3.1978 | 7.4946 | 5.3957 | 16.417 | 18.5159 | 26.0105 | 31.4062 | 0.01
13.8033 | 9.6907 | 2.2601 | 2.3902 | 4.3006 | 3.7803 | 8.9508 | 6.5607 | 23.494 | 25.8842 | 34.835 | 41.3957 | 13.8033 | 9.7007 | 2.2601 | 2.3902 | 4.3006 | 3.7803 | 8.9508 | 6.5607 | 23.504 | 25.8942 | 34.845 | 41.4057 | 0.01
8.5439 | 8.5512 | 2.0848 | 2.1272 | 3.424 | 3.2544 | 7.636 | 5.5088 | 17.0951 | 19.2223 | 26.8583 | 32.367 | 8.5439 | 8.5612 | 2.0848 | 2.1272 | 3.424 | 3.2544 | 7.636 | 5.5088 | 17.1051 | 19.2323 | 26.8683 | 32.377 | 0.01
4.4437 | 7.6628 | 1.9481 | 1.9222 | 2.7406 | 2.8444 | 6.6109 | 4.6887 | 12.1065 | 14.0287 | 20.6396 | 25.3283 | 4.4437 | 7.6728 | 1.9481 | 1.9222 | 2.7406 | 2.8444 | 6.6109 | 4.6887 | 12.1165 | 14.0387 | 20.6496 | 25.3383 | 0.01
7.7456 | 8.3782 | 2.0582 | 2.0873 | 3.2909 | 3.1746 | 7.4364 | 5.3491 | 16.1238 | 18.2111 | 25.6475 | 30.9967 | 7.7456 | 8.3882 | 2.0582 | 2.0873 | 3.2909 | 3.1746 | 7.4364 | 5.3491 | 16.1338 | 18.2211 | 25.6575 | 31.0067 | 0.01
-2.7103 | 6.1128 | 1.7097 | 1.5645 | 1.5483 | 2.129 | 4.8224 | 3.2579 | 3.4024 | 4.9669 | 9.7893 | 13.0473 | -2.7103 | 6.1228 | 1.7097 | 1.5645 | 1.5483 | 2.129 | 4.8224 | 3.2579 | 3.4124 | 4.9769 | 9.7993 | 13.0573 | 0.01
10.561 | 8.9882 | 2.152 | 2.2281 | 3.7602 | 3.4561 | 8.1403 | 5.9122 | 19.5493 | 21.7773 | 29.9176 | 35.8298 | 10.561 | 8.9982 | 2.152 | 2.2281 | 3.7602 | 3.4561 | 8.1403 | 5.9122 | 19.5593 | 21.7873 | 29.9276 | 35.8398 | 0.01
4.0867 | 7.5855 | 1.9362 | 1.9043 | 2.6811 | 2.8087 | 6.5217 | 4.6173 | 11.6721 | 13.5765 | 20.0982 | 24.7155 | 4.0867 | 7.5955 | 1.9362 | 1.9043 | 2.6811 | 2.8087 | 6.5217 | 4.6173 | 11.6821 | 13.5865 | 20.1082 | 24.7255 | 0.01
-2.8232 | 6.0883 | 1.7059 | 1.5588 | 1.5295 | 2.1177 | 4.7942 | 3.2354 | 3.2652 | 4.824 | 9.6182 | 12.8536 | -2.8232 | 6.0983 | 1.7059 | 1.5588 | 1.5295 | 2.1177 | 4.7942 | 3.2354 | 3.2752 | 4.834 | 9.6282 | 12.8636 | 0.01
4.6997 | 7.7183 | 1.9567 | 1.935 | 2.7833 | 2.87 | 6.6749 | 4.7399 | 12.418 | 14.353 | 21.0279 | 25.7678 | 4.6997 | 7.7283 | 1.9567 | 1.935 | 2.7833 | 2.87 | 6.6749 | 4.7399 | 12.428 | 14.363 | 21.0379 | 25.7778 | 0.01
9.2885 | 8.7125 | 2.1096 | 2.1644 | 3.5481 | 3.3288 | 7.8221 | 5.6577 | 18.0009 | 20.1654 | 27.9875 | 33.6452 | 9.2885 | 8.7225 | 2.1096 | 2.1644 | 3.5481 | 3.3288 | 7.8221 | 5.6577 | 18.0109 | 20.1754 | 27.9975 | 33.6552 | 0.01
4.1946 | 7.6088 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5486 | 4.6389 | 11.8034 | 13.7131 | 20.2618 | 24.9007 | 4.1946 | 7.6188 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5486 | 4.6389 | 11.8134 | 13.7231 | 20.2718 | 24.9107 | 0.01
17.7331 | 10.5422 | 2.3911 | 2.5867 | 4.9555 | 4.1733 | 9.9333 | 7.3466 | 28.2753 | 30.862 | 40.7953 | 48.1419 | 17.7331 | 10.5522 | 2.3911 | 2.5867 | 4.9555 | 4.1733 | 9.9333 | 7.3466 | 28.2853 | 30.872 | 40.8053 | 48.1519 | 0.01
5.1638 | 7.8188 | 1.9721 | 1.9582 | 2.8606 | 2.9164 | 6.791 | 4.8328 | 12.9827 | 14.9409 | 21.7318 | 26.5646 | 5.1638 | 7.8288 | 1.9721 | 1.9582 | 2.8606 | 2.9164 | 6.791 | 4.8328 | 12.9927 | 14.9509 | 21.7418 | 26.5746 | 0.01
-1.7584 | 6.319 | 1.7414 | 1.6121 | 1.7069 | 2.2242 | 5.0604 | 3.4483 | 4.5607 | 6.1727 | 11.2331 | 14.6815 | -1.7584 | 6.329 | 1.7414 | 1.6121 | 1.7069 | 2.2242 | 5.0604 | 3.4483 | 4.5707 | 6.1827 | 11.2431 | 14.6915 | 0.01
-8.3468 | 4.8915 | 1.5218 | 1.2827 | 0.60887 | 1.5653 | 3.4133 | 2.1306 | -3.4553 | -2.1726 | 1.2407 | 3.3713 | -8.3468 | 4.9015 | 1.5218 | 1.2827 | 0.60887 | 1.5653 | 3.4133 | 2.1306 | -3.4453 | -2.1626 | 1.2507 | 3.3813 | 0.01
-0.18201 | 6.6606 | 1.7939 | 1.6909 | 1.9697 | 2.3818 | 5.4545 | 3.7636 | 6.4786 | 8.1695 | 13.624 | 17.3876 | -0.18201 | 6.6706 | 1.7939 | 1.6909 | 1.9697 | 2.3818 | 5.4545 | 3.7636 | 6.4886 | 8.1795 | 13.634 | 17.3976 | 0.01
-6.2667 | 5.3422 | 1.5911 | 1.3867 | 0.95556 | 1.7733 | 3.9333 | 2.5467 | -0.92444 | 0.46223 | 4.3956 | 6.9422 | -6.2667 | 5.3522 | 1.5911 | 1.3867 | 0.95556 | 1.7733 | 3.9333 | 2.5467 | -0.91444 | 0.47223 | 4.4056 | 6.9522 | 0.01
10.6683 | 9.0115 | 2.1556 | 2.2334 | 3.778 | 3.4668 | 8.1671 | 5.9337 | 19.6798 | 21.9132 | 30.0803 | 36.0139 | 10.6683 | 9.0215 | 2.1556 | 2.2334 | 3.778 | 3.4668 | 8.1671 | 5.9337 | 19.6898 | 21.9232 | 30.0903 | 36.0239 | 0.01
6.5503 | 8.1192 | 2.0183 | 2.0275 | 3.0917 | 3.055 | 7.1376 | 5.1101 | 14.6695 | 16.697 | 23.8346 | 28.9447 | 6.5503 | 8.1292 | 2.0183 | 2.0275 | 3.0917 | 3.055 | 7.1376 | 5.1101 | 14.6795 | 16.707 | 23.8446 | 28.9547 | 0.01
7.3155 | 8.285 | 2.0438 | 2.0658 | 3.2192 | 3.1315 | 7.3289 | 5.2631 | 15.6005 | 17.6663 | 24.9951 | 30.2582 | 7.3155 | 8.295 | 2.0438 | 2.0658 | 3.2192 | 3.1315 | 7.3289 | 5.2631 | 15.6105 | 17.6763 | 25.0051 | 30.2682 | 0.01
12.1047 | 9.3227 | 2.2035 | 2.3052 | 4.0174 | 3.6105 | 8.5262 | 6.2209 | 21.4274 | 23.7326 | 32.2588 | 38.4797 | 12.1047 | 9.3327 | 2.2035 | 2.3052 | 4.0174 | 3.6105 | 8.5262 | 6.2209 | 21.4374 | 23.7426 | 32.2688 | 38.4897 | 0.01
11.6009 | 9.2135 | 2.1867 | 2.28 | 3.9335 | 3.5601 | 8.4002 | 6.1202 | 20.8144 | 23.0944 | 31.4947 | 37.6148 | 11.6009 | 9.2235 | 2.1867 | 2.28 | 3.9335 | 3.5601 | 8.4002 | 6.1202 | 20.8244 | 23.1044 | 31.5047 | 37.6248 | 0.01
16.131 | 10.195 | 2.3377 | 2.5065 | 4.6885 | 4.0131 | 9.5327 | 7.0262 | 26.326 | 28.8326 | 38.3653 | 45.3915 | 16.131 | 10.205 | 2.3377 | 2.5065 | 4.6885 | 4.0131 | 9.5327 | 7.0262 | 26.336 | 28.8426 | 38.3753 | 45.4015 | 0.01
7.8716 | 8.4055 | 2.0624 | 2.0936 | 3.3119 | 3.1872 | 7.4679 | 5.3743 | 16.2771 | 18.3706 | 25.8385 | 31.2128 | 7.8716 | 8.4155 | 2.0624 | 2.0936 | 3.3119 | 3.1872 | 7.4679 | 5.3743 | 16.2871 | 18.3806 | 25.8485 | 31.2228 | 0.01
6.6207 | 8.1345 | 2.0207 | 2.031 | 3.1035 | 3.0621 | 7.1552 | 5.1241 | 14.7552 | 16.7863 | 23.9415 | 29.0656 | 6.6207 | 8.1445 | 2.0207 | 2.031 | 3.1035 | 3.0621 | 7.1552 | 5.1241 | 14.7652 | 16.7963 | 23.9515 | 29.0756 | 0.01
15.6319 | 10.0869 | 2.3211 | 2.4816 | 4.6053 | 3.9632 | 9.408 | 6.9264 | 25.7188 | 28.2004 | 37.6084 | 44.5348 | 15.6319 | 10.0969 | 2.3211 | 2.4816 | 4.6053 | 3.9632 | 9.408 | 6.9264 | 25.7288 | 28.2104 | 37.6184 | 44.5448 | 0.01
12.4075 | 9.3883 | 2.2136 | 2.3204 | 4.0679 | 3.6408 | 8.6019 | 6.2815 | 21.7958 | 24.1162 | 32.7181 | 38.9996 | 12.4075 | 9.3983 | 2.2136 | 2.3204 | 4.0679 | 3.6408 | 8.6019 | 6.2815 | 21.8058 | 24.1262 | 32.7281 | 39.0096 | 0.01
3.1852 | 7.3901 | 1.9062 | 1.8593 | 2.5309 | 2.7185 | 6.2963 | 4.437 | 10.5753 | 12.4346 | 18.7309 | 23.168 | 3.1852 | 7.4001 | 1.9062 | 1.8593 | 2.5309 | 2.7185 | 6.2963 | 4.437 | 10.5853 | 12.4446 | 18.7409 | 23.178 | 0.01
8.0258 | 8.4389 | 2.0675 | 2.1013 | 3.3376 | 3.2026 | 7.5065 | 5.4052 | 16.4648 | 18.5661 | 26.0725 | 31.4777 | 8.0258 | 8.4489 | 2.0675 | 2.1013 | 3.3376 | 3.2026 | 7.5065 | 5.4052 | 16.4748 | 18.5761 | 26.0825 | 31.4877 | 0.01
-1.6375 | 6.3452 | 1.7454 | 1.6181 | 1.7271 | 2.2363 | 5.0906 | 3.4725 | 4.7078 | 6.3259 | 11.4165 | 14.889 | -1.6375 | 6.3552 | 1.7454 | 1.6181 | 1.7271 | 2.2363 | 5.0906 | 3.4725 | 4.7178 | 6.3359 | 11.4265 | 14.899 | 0.01
3.3169 | 7.4187 | 1.9106 | 1.8658 | 2.5528 | 2.7317 | 6.3292 | 4.4634 | 10.7355 | 12.6014 | 18.9306 | 23.394 | 3.3169 | 7.4287 | 1.9106 | 1.8658 | 2.5528 | 2.7317 | 6.3292 | 4.4634 | 10.7455 | 12.6114 | 18.9406 | 23.404 | 0.01
-1.316 | 6.4149 | 1.7561 | 1.6342 | 1.7807 | 2.2684 | 5.171 | 3.5368 | 5.0988 | 6.733 | 11.904 | 15.4408 | -1.316 | 6.4249 | 1.7561 | 1.6342 | 1.7807 | 2.2684 | 5.171 | 3.5368 | 5.1088 | 6.743 | 11.914 | 15.4508 | 0.01
7.4915 | 8.3232 | 2.0497 | 2.0746 | 3.2486 | 3.1491 | 7.3729 | 5.2983 | 15.8146 | 17.8892 | 25.2621 | 30.5603 | 7.4915 | 8.3332 | 2.0497 | 2.0746 | 3.2486 | 3.1491 | 7.3729 | 5.2983 | 15.8246 | 17.8992 | 25.2721 | 30.5703 | 0.01
1.1213 | 6.943 | 1.8374 | 1.7561 | 2.1869 | 2.5121 | 5.7803 | 4.0243 | 8.0643 | 9.8204 | 15.6007 | 19.625 | 1.1213 | 6.953 | 1.8374 | 1.7561 | 2.1869 | 2.5121 | 5.7803 | 4.0243 | 8.0743 | 9.8304 | 15.6107 | 19.635 | 0.01
-0.19129 | 6.6586 | 1.7936 | 1.6904 | 1.9681 | 2.3809 | 5.4522 | 3.7617 | 6.4673 | 8.1577 | 13.6099 | 17.3716 | -0.19129 | 6.6686 | 1.7936 | 1.6904 | 1.9681 | 2.3809 | 5.4522 | 3.7617 | 6.4773 | 8.1677 | 13.6199 | 17.3816 | 0.01
14.9327 | 9.9354 | 2.2978 | 2.4466 | 4.4888 | 3.8933 | 9.2332 | 6.7865 | 24.8681 | 27.3147 | 36.5479 | 43.3344 | 14.9327 | 9.9454 | 2.2978 | 2.4466 | 4.4888 | 3.8933 | 9.2332 | 6.7865 | 24.8781 | 27.3247 | 36.5579 | 43.3444 | 0.01
6.5945 | 8.1288 | 2.0198 | 2.0297 | 3.0991 | 3.0594 | 7.1486 | 5.1189 | 14.7233 | 16.753 | 23.9016 | 29.0205 | 6.5945 | 8.1388 | 2.0198 | 2.0297 | 3.0991 | 3.0594 | 7.1486 | 5.1189 | 14.7333 | 16.763 | 23.9116 | 29.0305 | 0.01
9.6841 | 8.7982 | 2.1228 | 2.1842 | 3.614 | 3.3684 | 7.921 | 5.7368 | 18.4823 | 20.6665 | 28.5875 | 34.3244 | 9.6841 | 8.8082 | 2.1228 | 2.1842 | 3.614 | 3.3684 | 7.921 | 5.7368 | 18.4923 | 20.6765 | 28.5975 | 34.3344 | 0.01
10.8748 | 9.0562 | 2.1625 | 2.2437 | 3.8125 | 3.4875 | 8.2187 | 5.975 | 19.931 | 22.1747 | 30.3934 | 36.3684 | 10.8748 | 9.0662 | 2.1625 | 2.2437 | 3.8125 | 3.4875 | 8.2187 | 5.975 | 19.941 | 22.1847 | 30.4034 | 36.3784 | 0.01
9.5191 | 8.7625 | 2.1173 | 2.176 | 3.5865 | 3.3519 | 7.8798 | 5.7038 | 18.2816 | 20.4576 | 28.3373 | 34.0412 | 9.5191 | 8.7725 | 2.1173 | 2.176 | 3.5865 | 3.3519 | 7.8798 | 5.7038 | 18.2916 | 20.4676 | 28.3473 | 34.0512 | 0.01
11.791 | 9.2547 | 2.193 | 2.2896 | 3.9652 | 3.5791 | 8.4478 | 6.1582 | 21.0458 | 23.3353 | 31.7831 | 37.9413 | 11.791 | 9.2647 | 2.193 | 2.2896 | 3.9652 | 3.5791 | 8.4478 | 6.1582 | 21.0558 | 23.3453 | 31.7931 | 37.9513 | 0.01
4.0406 | 7.5755 | 1.9347 | 1.902 | 2.6734 | 2.8041 | 6.5101 | 4.6081 | 11.6161 | 13.5181 | 20.0282 | 24.6364 | 4.0406 | 7.5855 | 1.9347 | 1.902 | 2.6734 | 2.8041 | 6.5101 | 4.6081 | 11.6261 | 13.5281 | 20.0382 | 24.6464 | 0.01
0.16694 | 6.7362 | 1.8056 | 1.7083 | 2.0278 | 2.4167 | 5.5417 | 3.8334 | 6.9031 | 8.6115 | 14.1532 | 17.9866 | 0.16694 | 6.7462 | 1.8056 | 1.7083 | 2.0278 | 2.4167 | 5.5417 | 3.8334 | 6.9131 | 8.6215 | 14.1632 | 17.9966 | 0.01
1.7732 | 7.0842 | 1.8591 | 1.7887 | 2.2955 | 2.5773 | 5.9433 | 4.1546 | 8.8574 | 10.6461 | 16.5894 | 20.7441 | 1.7732 | 7.0942 | 1.8591 | 1.7887 | 2.2955 | 2.5773 | 5.9433 | 4.1546 | 8.8674 | 10.6561 | 16.5994 | 20.7541 | 0.01
2.946 | 7.3383 | 1.8982 | 1.8473 | 2.491 | 2.6946 | 6.2365 | 4.3892 | 10.2843 | 12.1316 | 18.3681 | 22.7573 | 2.946 | 7.3483 | 1.8982 | 1.8473 | 2.491 | 2.6946 | 6.2365 | 4.3892 | 10.2943 | 12.1416 | 18.3781 | 22.7673 | 0.01
5.1699 | 7.8202 | 1.9723 | 1.9585 | 2.8617 | 2.917 | 6.7925 | 4.834 | 12.9901 | 14.9486 | 21.7411 | 26.5751 | 5.1699 | 7.8302 | 1.9723 | 1.9585 | 2.8617 | 2.917 | 6.7925 | 4.834 | 13.0001 | 14.9586 | 21.7511 | 26.5851 | 0.01
12.1677 | 9.3363 | 2.2056 | 2.3084 | 4.0279 | 3.6168 | 8.5419 | 6.2335 | 21.504 | 23.8124 | 32.3543 | 38.5878 | 12.1677 | 9.3463 | 2.2056 | 2.3084 | 4.0279 | 3.6168 | 8.5419 | 6.2335 | 21.514 | 23.8224 | 32.3643 | 38.5978 | 0.01
6.5433 | 8.1177 | 2.0181 | 2.0272 | 3.0906 | 3.0543 | 7.1358 | 5.1087 | 14.661 | 16.6882 | 23.824 | 28.9327 | 6.5433 | 8.1277 | 2.0181 | 2.0272 | 3.0906 | 3.0543 | 7.1358 | 5.1087 | 14.671 | 16.6982 | 23.834 | 28.9427 | 0.01
11.7076 | 9.2366 | 2.1903 | 2.2854 | 3.9513 | 3.5708 | 8.4269 | 6.1415 | 20.9442 | 23.2296 | 31.6565 | 37.798 | 11.7076 | 9.2466 | 2.1903 | 2.2854 | 3.9513 | 3.5708 | 8.4269 | 6.1415 | 20.9542 | 23.2396 | 31.6665 | 37.808 | 0.01
5.373 | 7.8641 | 1.9791 | 1.9686 | 2.8955 | 2.9373 | 6.8432 | 4.8746 | 13.2371 | 15.2058 | 22.049 | 26.9236 | 5.373 | 7.8741 | 1.9791 | 1.9686 | 2.8955 | 2.9373 | 6.8432 | 4.8746 | 13.2471 | 15.2158 | 22.059 | 26.9336 | 0.01
-2.6906 | 6.117 | 1.7103 | 1.5655 | 1.5516 | 2.1309 | 4.8273 | 3.2619 | 3.4264 | 4.9919 | 9.8193 | 13.0811 | -2.6906 | 6.127 | 1.7103 | 1.5655 | 1.5516 | 2.1309 | 4.8273 | 3.2619 | 3.4364 | 5.0019 | 9.8293 | 13.0911 | 0.01
5.7733 | 7.9509 | 1.9924 | 1.9887 | 2.9622 | 2.9773 | 6.9433 | 4.9547 | 13.7242 | 15.7128 | 22.6561 | 27.6108 | 5.7733 | 7.9609 | 1.9924 | 1.9887 | 2.9622 | 2.9773 | 6.9433 | 4.9547 | 13.7342 | 15.7228 | 22.6661 | 27.6208 | 0.01
1.0347 | 6.9242 | 1.8345 | 1.7517 | 2.1724 | 2.5035 | 5.7587 | 4.0069 | 7.9588 | 9.7106 | 15.4693 | 19.4762 | 1.0347 | 6.9342 | 1.8345 | 1.7517 | 2.1724 | 2.5035 | 5.7587 | 4.0069 | 7.9688 | 9.7206 | 15.4793 | 19.4862 | 0.01
17.9452 | 10.5881 | 2.3982 | 2.5973 | 4.9909 | 4.1945 | 9.9863 | 7.389 | 28.5333 | 31.1306 | 41.1169 | 48.5059 | 17.9452 | 10.5981 | 2.3982 | 2.5973 | 4.9909 | 4.1945 | 9.9863 | 7.389 | 28.5433 | 31.1406 | 41.1269 | 48.5159 | 0.01
2.4162 | 7.2235 | 1.8805 | 1.8208 | 2.4027 | 2.6416 | 6.104 | 4.2832 | 9.6397 | 11.4605 | 17.5645 | 21.8477 | 2.4162 | 7.2335 | 1.8805 | 1.8208 | 2.4027 | 2.6416 | 6.104 | 4.2832 | 9.6497 | 11.4705 | 17.5745 | 21.8577 | 0.01
5.5634 | 7.9054 | 1.9854 | 1.9782 | 2.9272 | 2.9563 | 6.8909 | 4.9127 | 13.4688 | 15.447 | 22.3378 | 27.2505 | 5.5634 | 7.9154 | 1.9854 | 1.9782 | 2.9272 | 2.9563 | 6.8909 | 4.9127 | 13.4788 | 15.457 | 22.3478 | 27.2605 | 0.01
-4.3193 | 5.7641 | 1.656 | 1.484 | 1.2801 | 1.9681 | 4.4202 | 2.9361 | 1.4448 | 2.9288 | 7.349 | 10.2851 | -4.3193 | 5.7741 | 1.656 | 1.484 | 1.2801 | 1.9681 | 4.4202 | 2.9361 | 1.4548 | 2.9388 | 7.359 | 10.2951 | 0.01
-1.7225 | 6.3268 | 1.7426 | 1.6139 | 1.7129 | 2.2278 | 5.0694 | 3.4555 | 4.6043 | 6.2182 | 11.2876 | 14.7431 | -1.7225 | 6.3368 | 1.7426 | 1.6139 | 1.7129 | 2.2278 | 5.0694 | 3.4555 | 4.6143 | 6.2282 | 11.2976 | 14.7531 | 0.01
5.3795 | 7.8656 | 1.9793 | 1.969 | 2.8966 | 2.9379 | 6.8449 | 4.8759 | 13.245 | 15.214 | 22.0589 | 26.9348 | 5.3795 | 7.8756 | 1.9793 | 1.969 | 2.8966 | 2.9379 | 6.8449 | 4.8759 | 13.255 | 15.224 | 22.0689 | 26.9448 | 0.01
2.8529 | 7.3181 | 1.8951 | 1.8426 | 2.4755 | 2.6853 | 6.2132 | 4.3706 | 10.171 | 12.0137 | 18.2269 | 22.5975 | 2.8529 | 7.3281 | 1.8951 | 1.8426 | 2.4755 | 2.6853 | 6.2132 | 4.3706 | 10.181 | 12.0237 | 18.2369 | 22.6075 | 0.01
4.9315 | 7.7685 | 1.9644 | 1.9466 | 2.8219 | 2.8931 | 6.7329 | 4.7863 | 12.6999 | 14.6465 | 21.3794 | 26.1657 | 4.9315 | 7.7785 | 1.9644 | 1.9466 | 2.8219 | 2.8931 | 6.7329 | 4.7863 | 12.7099 | 14.6565 | 21.3894 | 26.1757 | 0.01
8.9348 | 8.6359 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7337 | 5.587 | 17.5707 | 19.7175 | 27.4512 | 33.0382 | 8.9348 | 8.6459 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7337 | 5.587 | 17.5807 | 19.7275 | 27.4612 | 33.0482 | 0.01
18.576 | 10.7248 | 2.4192 | 2.6288 | 5.096 | 4.2576 | 10.144 | 7.5152 | 29.3008 | 31.9296 | 42.0736 | 49.5888 | 18.576 | 10.7348 | 2.4192 | 2.6288 | 5.096 | 4.2576 | 10.144 | 7.5152 | 29.3108 | 31.9396 | 42.0836 | 49.5988 | 0.01
10.8329 | 9.0471 | 2.1611 | 2.2416 | 3.8055 | 3.4833 | 8.2082 | 5.9666 | 19.88 | 22.1217 | 30.3299 | 36.2965 | 10.8329 | 9.0571 | 2.1611 | 2.2416 | 3.8055 | 3.4833 | 8.2082 | 5.9666 | 19.89 | 22.1317 | 30.3399 | 36.3065 | 0.01
20.2137 | 11.0796 | 2.4738 | 2.7107 | 5.3689 | 4.4214 | 10.5534 | 7.8427 | 31.2933 | 34.004 | 44.5574 | 52.4001 | 20.2137 | 11.0896 | 2.4738 | 2.7107 | 5.3689 | 4.4214 | 10.5534 | 7.8427 | 31.3033 | 34.014 | 44.5674 | 52.4101 | 0.01
-2.0597 | 6.2537 | 1.7313 | 1.597 | 1.6567 | 2.194 | 4.9851 | 3.3881 | 4.1941 | 5.7911 | 10.7762 | 14.1642 | -2.0597 | 6.2637 | 1.7313 | 1.597 | 1.6567 | 2.194 | 4.9851 | 3.3881 | 4.2041 | 5.8011 | 10.7862 | 14.1742 | 0.01
10.1219 | 8.8931 | 2.1374 | 2.2061 | 3.687 | 3.4122 | 8.0305 | 5.8244 | 19.015 | 21.2211 | 29.2516 | 35.0759 | 10.1219 | 8.9031 | 2.1374 | 2.2061 | 3.687 | 3.4122 | 8.0305 | 5.8244 | 19.025 | 21.2311 | 29.2616 | 35.0859 | 0.01
9.1303 | 8.6782 | 2.1043 | 2.1565 | 3.5217 | 3.313 | 7.7826 | 5.6261 | 17.8085 | 19.965 | 27.7476 | 33.3737 | 9.1303 | 8.6882 | 2.1043 | 2.1565 | 3.5217 | 3.313 | 7.7826 | 5.6261 | 17.8185 | 19.975 | 27.7576 | 33.3837 | 0.01
1.075 | 6.9329 | 1.8358 | 1.7537 | 2.1792 | 2.5075 | 5.7687 | 4.015 | 8.0079 | 9.7616 | 15.5304 | 19.5454 | 1.075 | 6.9429 | 1.8358 | 1.7537 | 2.1792 | 2.5075 | 5.7687 | 4.015 | 8.0179 | 9.7716 | 15.5404 | 19.5554 | 0.01
-4.9896 | 5.6189 | 1.6337 | 1.4505 | 1.1684 | 1.901 | 4.2526 | 2.8021 | 0.62936 | 2.0799 | 6.3325 | 9.1346 | -4.9896 | 5.6289 | 1.6337 | 1.4505 | 1.1684 | 1.901 | 4.2526 | 2.8021 | 0.63936 | 2.0899 | 6.3425 | 9.1446 | 0.01
-0.62885 | 6.5637 | 1.779 | 1.6686 | 1.8952 | 2.3371 | 5.3428 | 3.6742 | 5.9349 | 7.6035 | 12.9462 | 16.6205 | -0.62885 | 6.5737 | 1.779 | 1.6686 | 1.8952 | 2.3371 | 5.3428 | 3.6742 | 5.9449 | 7.6135 | 12.9562 | 16.6305 | 0.01
7.2339 | 8.2674 | 2.0411 | 2.0617 | 3.2057 | 3.1234 | 7.3085 | 5.2468 | 15.5013 | 17.563 | 24.8715 | 30.1183 | 7.2339 | 8.2774 | 2.0411 | 2.0617 | 3.2057 | 3.1234 | 7.3085 | 5.2468 | 15.5113 | 17.573 | 24.8815 | 30.1283 | 0.01
10.4833 | 8.9714 | 2.1494 | 2.2242 | 3.7472 | 3.4483 | 8.1208 | 5.8967 | 19.4547 | 21.6788 | 29.7997 | 35.6963 | 10.4833 | 8.9814 | 2.1494 | 2.2242 | 3.7472 | 3.4483 | 8.1208 | 5.8967 | 19.4647 | 21.6888 | 29.8097 | 35.7063 | 0.01
17.6691 | 10.5283 | 2.389 | 2.5835 | 4.9448 | 4.1669 | 9.9173 | 7.3338 | 28.1974 | 30.7808 | 40.6981 | 48.0319 | 17.6691 | 10.5383 | 2.389 | 2.5835 | 4.9448 | 4.1669 | 9.9173 | 7.3338 | 28.2074 | 30.7908 | 40.7081 | 48.0419 | 0.01
10.1095 | 8.8904 | 2.137 | 2.2055 | 3.6849 | 3.4109 | 8.0274 | 5.8219 | 18.9999 | 21.2053 | 29.2327 | 35.0546 | 10.1095 | 8.9004 | 2.137 | 2.2055 | 3.6849 | 3.4109 | 8.0274 | 5.8219 | 19.0099 | 21.2153 | 29.2427 | 35.0646 | 0.01
9.4732 | 8.7525 | 2.1158 | 2.1737 | 3.5789 | 3.3473 | 7.8683 | 5.6946 | 18.2258 | 20.3994 | 28.2677 | 33.9624 | 9.4732 | 8.7625 | 2.1158 | 2.1737 | 3.5789 | 3.3473 | 7.8683 | 5.6946 | 18.2358 | 20.4094 | 28.2777 | 33.9724 | 0.01
6.8688 | 8.1882 | 2.029 | 2.0434 | 3.1448 | 3.0869 | 7.2172 | 5.1738 | 15.057 | 17.1005 | 24.3177 | 29.4914 | 6.8688 | 8.1982 | 2.029 | 2.0434 | 3.1448 | 3.0869 | 7.2172 | 5.1738 | 15.067 | 17.1105 | 24.3277 | 29.5014 | 0.01
-7.7712 | 5.0162 | 1.541 | 1.3114 | 0.7048 | 1.6229 | 3.5572 | 2.2458 | -2.755 | -1.4435 | 2.1137 | 4.3594 | -7.7712 | 5.0262 | 1.541 | 1.3114 | 0.7048 | 1.6229 | 3.5572 | 2.2458 | -2.745 | -1.4335 | 2.1237 | 4.3694 | 0.01
6.6159 | 8.1335 | 2.0205 | 2.0308 | 3.1027 | 3.0616 | 7.154 | 5.1232 | 14.7494 | 16.7802 | 23.9342 | 29.0574 | 6.6159 | 8.1435 | 2.0205 | 2.0308 | 3.1027 | 3.0616 | 7.154 | 5.1232 | 14.7594 | 16.7902 | 23.9442 | 29.0674 | 0.01
7.7482 | 8.3788 | 2.0583 | 2.0874 | 3.2914 | 3.1748 | 7.437 | 5.3496 | 16.127 | 18.2144 | 25.6514 | 31.0011 | 7.7482 | 8.3888 | 2.0583 | 2.0874 | 3.2914 | 3.1748 | 7.437 | 5.3496 | 16.137 | 18.2244 | 25.6614 | 31.0111 | 0.01
11.3824 | 9.1662 | 2.1794 | 2.2691 | 3.8971 | 3.5382 | 8.3456 | 6.0765 | 20.5485 | 22.8177 | 31.1632 | 37.2397 | 11.3824 | 9.1762 | 2.1794 | 2.2691 | 3.8971 | 3.5382 | 8.3456 | 6.0765 | 20.5585 | 22.8277 | 31.1732 | 37.2497 | 0.01
3.369 | 7.4299 | 1.9123 | 1.8684 | 2.5615 | 2.7369 | 6.3422 | 4.4738 | 10.7989 | 12.6674 | 19.0096 | 23.4834 | 3.369 | 7.4399 | 1.9123 | 1.8684 | 2.5615 | 2.7369 | 6.3422 | 4.4738 | 10.8089 | 12.6774 | 19.0196 | 23.4934 | 0.01
12.951 | 9.506 | 2.2317 | 2.3475 | 4.1585 | 3.6951 | 8.7377 | 6.3902 | 22.457 | 24.8046 | 33.5423 | 39.9325 | 12.951 | 9.516 | 2.2317 | 2.3475 | 4.1585 | 3.6951 | 8.7377 | 6.3902 | 22.467 | 24.8146 | 33.5523 | 39.9425 | 0.01
0.55287 | 6.8198 | 1.8184 | 1.7276 | 2.0921 | 2.4553 | 5.6382 | 3.9106 | 7.3727 | 9.1003 | 14.7385 | 18.6491 | 0.55287 | 6.8298 | 1.8184 | 1.7276 | 2.0921 | 2.4553 | 5.6382 | 3.9106 | 7.3827 | 9.1103 | 14.7485 | 18.6591 | 0.01
5.8476 | 7.967 | 1.9949 | 1.9924 | 2.9746 | 2.9848 | 6.9619 | 4.9695 | 13.8146 | 15.807 | 22.7689 | 27.7384 | 5.8476 | 7.977 | 1.9949 | 1.9924 | 2.9746 | 2.9848 | 6.9619 | 4.9695 | 13.8246 | 15.817 | 22.7789 | 27.7484 | 0.01
1.2162 | 6.9635 | 1.8405 | 1.7608 | 2.2027 | 2.5216 | 5.8041 | 4.0432 | 8.1798 | 9.9406 | 15.7446 | 19.7879 | 1.2162 | 6.9735 | 1.8405 | 1.7608 | 2.2027 | 2.5216 | 5.8041 | 4.0432 | 8.1898 | 9.9506 | 15.7546 | 19.7979 | 0.01
12.2562 | 9.3555 | 2.2085 | 2.3128 | 4.0427 | 3.6256 | 8.564 | 6.2512 | 21.6117 | 23.9245 | 32.4885 | 38.7398 | 12.2562 | 9.3655 | 2.2085 | 2.3128 | 4.0427 | 3.6256 | 8.564 | 6.2512 | 21.6217 | 23.9345 | 32.4985 | 38.7498 | 0.01
4.5273 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7055 | 12.2082 | 14.1346 | 20.7664 | 25.4718 | 4.5273 | 7.6909 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7055 | 12.2182 | 14.1446 | 20.7764 | 25.4818 | 0.01
-1.3747 | 6.4021 | 1.7542 | 1.6313 | 1.7709 | 2.2625 | 5.1563 | 3.5251 | 5.0275 | 6.6587 | 11.815 | 15.3401 | -1.3747 | 6.4121 | 1.7542 | 1.6313 | 1.7709 | 2.2625 | 5.1563 | 3.5251 | 5.0375 | 6.6687 | 11.825 | 15.3501 | 0.01
7.568 | 8.3397 | 2.0523 | 2.0784 | 3.2613 | 3.1568 | 7.392 | 5.3136 | 15.9077 | 17.9861 | 25.3781 | 30.6917 | 7.568 | 8.3497 | 2.0523 | 2.0784 | 3.2613 | 3.1568 | 7.392 | 5.3136 | 15.9177 | 17.9961 | 25.3881 | 30.7017 | 0.01
17.8346 | 10.5642 | 2.3945 | 2.5917 | 4.9724 | 4.1835 | 9.9586 | 7.3669 | 28.3987 | 30.9905 | 40.9491 | 48.316 | 17.8346 | 10.5742 | 2.3945 | 2.5917 | 4.9724 | 4.1835 | 9.9586 | 7.3669 | 28.4087 | 31.0005 | 40.9591 | 48.326 | 0.01
14.6358 | 9.8711 | 2.2879 | 2.4318 | 4.4393 | 3.8636 | 9.159 | 6.7272 | 24.5069 | 26.9387 | 36.0977 | 42.8248 | 14.6358 | 9.8811 | 2.2879 | 2.4318 | 4.4393 | 3.8636 | 9.159 | 6.7272 | 24.5169 | 26.9487 | 36.1077 | 42.8348 | 0.01
14.7192 | 9.8892 | 2.2906 | 2.436 | 4.4532 | 3.8719 | 9.1798 | 6.7438 | 24.6084 | 27.0443 | 36.2241 | 42.968 | 14.7192 | 9.8992 | 2.2906 | 2.436 | 4.4532 | 3.8719 | 9.1798 | 6.7438 | 24.6184 | 27.0543 | 36.2341 | 42.978 | 0.01
8.6596 | 8.5763 | 2.0887 | 2.133 | 3.4433 | 3.266 | 7.6649 | 5.5319 | 17.2359 | 19.3689 | 27.0338 | 32.5657 | 8.6596 | 8.5863 | 2.0887 | 2.133 | 3.4433 | 3.266 | 7.6649 | 5.5319 | 17.2459 | 19.3789 | 27.0438 | 32.5757 | 0.01
-0.8912 | 6.5069 | 1.7703 | 1.6554 | 1.8515 | 2.3109 | 5.2772 | 3.6218 | 5.6157 | 7.2712 | 12.5484 | 16.1701 | -0.8912 | 6.5169 | 1.7703 | 1.6554 | 1.8515 | 2.3109 | 5.2772 | 3.6218 | 5.6257 | 7.2812 | 12.5584 | 16.1801 | 0.01
0.11658 | 6.7253 | 1.8039 | 1.7058 | 2.0194 | 2.4117 | 5.5291 | 3.8233 | 6.8418 | 8.5477 | 14.0768 | 17.9001 | 0.11658 | 6.7353 | 1.8039 | 1.7058 | 2.0194 | 2.4117 | 5.5291 | 3.8233 | 6.8518 | 8.5577 | 14.0868 | 17.9101 | 0.01
2.9789 | 7.3454 | 1.8993 | 1.8489 | 2.4965 | 2.6979 | 6.2447 | 4.3958 | 10.3243 | 12.1733 | 18.418 | 22.8138 | 2.9789 | 7.3554 | 1.8993 | 1.8489 | 2.4965 | 2.6979 | 6.2447 | 4.3958 | 10.3343 | 12.1833 | 18.428 | 22.8238 | 0.01
10.7182 | 9.0223 | 2.1573 | 2.2359 | 3.7864 | 3.4718 | 8.1796 | 5.9436 | 19.7405 | 21.9764 | 30.156 | 36.0997 | 10.7182 | 9.0323 | 2.1573 | 2.2359 | 3.7864 | 3.4718 | 8.1796 | 5.9436 | 19.7505 | 21.9864 | 30.166 | 36.1097 | 0.01
8.2018 | 8.4771 | 2.0734 | 2.1101 | 3.367 | 3.2202 | 7.5505 | 5.4404 | 16.6789 | 18.789 | 26.3395 | 31.7798 | 8.2018 | 8.4871 | 2.0734 | 2.1101 | 3.367 | 3.2202 | 7.5505 | 5.4404 | 16.6889 | 18.799 | 26.3495 | 31.7898 | 0.01
14.9186 | 9.9324 | 2.2973 | 2.4459 | 4.4864 | 3.8919 | 9.2296 | 6.7837 | 24.8509 | 27.2969 | 36.5265 | 43.3102 | 14.9186 | 9.9424 | 2.2973 | 2.4459 | 4.4864 | 3.8919 | 9.2296 | 6.7837 | 24.8609 | 27.3069 | 36.5365 | 43.3202 | 0.01
3.278 | 7.4102 | 1.9093 | 1.8639 | 2.5463 | 2.7278 | 6.3195 | 4.4556 | 10.6882 | 12.5521 | 18.8716 | 23.3272 | 3.278 | 7.4202 | 1.9093 | 1.8639 | 2.5463 | 2.7278 | 6.3195 | 4.4556 | 10.6982 | 12.5621 | 18.8816 | 23.3372 | 0.01
11.9059 | 9.2796 | 2.1969 | 2.2953 | 3.9843 | 3.5906 | 8.4765 | 6.1812 | 21.1855 | 23.4808 | 31.9572 | 38.1384 | 11.9059 | 9.2896 | 2.1969 | 2.2953 | 3.9843 | 3.5906 | 8.4765 | 6.1812 | 21.1955 | 23.4908 | 31.9672 | 38.1484 | 0.01
0.21186 | 6.7459 | 1.8071 | 1.7106 | 2.0353 | 2.4212 | 5.553 | 3.8424 | 6.9578 | 8.6684 | 14.2213 | 18.0637 | 0.21186 | 6.7559 | 1.8071 | 1.7106 | 2.0353 | 2.4212 | 5.553 | 3.8424 | 6.9678 | 8.6784 | 14.2313 | 18.0737 | 0.01
8.3077 | 8.5 | 2.0769 | 2.1154 | 3.3846 | 3.2308 | 7.5769 | 5.4615 | 16.8077 | 18.9231 | 26.5001 | 31.9616 | 8.3077 | 8.51 | 2.0769 | 2.1154 | 3.3846 | 3.2308 | 7.5769 | 5.4615 | 16.8177 | 18.9331 | 26.5101 | 31.9716 | 0.01
0.99521 | 6.9156 | 1.8332 | 1.7498 | 2.1659 | 2.4995 | 5.7488 | 3.999 | 7.9108 | 9.6606 | 15.4094 | 19.4084 | 0.99521 | 6.9256 | 1.8332 | 1.7498 | 2.1659 | 2.4995 | 5.7488 | 3.999 | 7.9208 | 9.6706 | 15.4194 | 19.4184 | 0.01
10.022 | 8.8714 | 2.1341 | 2.2011 | 3.6703 | 3.4022 | 8.0055 | 5.8044 | 18.8934 | 21.0945 | 29.1 | 34.9045 | 10.022 | 8.8814 | 2.1341 | 2.2011 | 3.6703 | 3.4022 | 8.0055 | 5.8044 | 18.9034 | 21.1045 | 29.11 | 34.9145 | 0.01
-5.1718 | 5.5794 | 1.6276 | 1.4414 | 1.138 | 1.8828 | 4.207 | 2.7656 | 0.4076 | 1.849 | 6.0561 | 8.8217 | -5.1718 | 5.5894 | 1.6276 | 1.4414 | 1.138 | 1.8828 | 4.207 | 2.7656 | 0.4176 | 1.859 | 6.0661 | 8.8317 | 0.01
-1.0844 | 6.465 | 1.7639 | 1.6458 | 1.8193 | 2.2916 | 5.2289 | 3.5831 | 5.3806 | 7.0264 | 12.2553 | 15.8384 | -1.0844 | 6.475 | 1.7639 | 1.6458 | 1.8193 | 2.2916 | 5.2289 | 3.5831 | 5.3906 | 7.0364 | 12.2653 | 15.8484 | 0.01
6.9795 | 8.2122 | 2.0326 | 2.049 | 3.1632 | 3.0979 | 7.2449 | 5.1959 | 15.1917 | 17.2407 | 24.4855 | 29.6814 | 6.9795 | 8.2222 | 2.0326 | 2.049 | 3.1632 | 3.0979 | 7.2449 | 5.1959 | 15.2017 | 17.2507 | 24.4955 | 29.6914 | 0.01
1.3132 | 6.9845 | 1.8438 | 1.7657 | 2.2189 | 2.5313 | 5.8283 | 4.0626 | 8.2978 | 10.0634 | 15.8917 | 19.9544 | 1.3132 | 6.9945 | 1.8438 | 1.7657 | 2.2189 | 2.5313 | 5.8283 | 4.0626 | 8.3078 | 10.0734 | 15.9017 | 19.9644 | 0.01
1.3639 | 6.9955 | 1.8455 | 1.7682 | 2.2273 | 2.5364 | 5.841 | 4.0728 | 8.3594 | 10.1276 | 15.9686 | 20.0414 | 1.3639 | 7.0055 | 1.8455 | 1.7682 | 2.2273 | 2.5364 | 5.841 | 4.0728 | 8.3694 | 10.1376 | 15.9786 | 20.0514 | 0.01
-1.4768 | 6.38 | 1.7508 | 1.6262 | 1.7539 | 2.2523 | 5.1308 | 3.5046 | 4.9032 | 6.5293 | 11.6601 | 15.1648 | -1.4768 | 6.39 | 1.7508 | 1.6262 | 1.7539 | 2.2523 | 5.1308 | 3.5046 | 4.9132 | 6.5393 | 11.6701 | 15.1748 | 0.01
6.5105 | 8.1106 | 2.017 | 2.0255 | 3.0851 | 3.0511 | 7.1276 | 5.1021 | 14.6211 | 16.6466 | 23.7743 | 28.8764 | 6.5105 | 8.1206 | 2.017 | 2.0255 | 3.0851 | 3.0511 | 7.1276 | 5.1021 | 14.6311 | 16.6566 | 23.7843 | 28.8864 | 0.01
2.9522 | 7.3396 | 1.8984 | 1.8476 | 2.492 | 2.6952 | 6.238 | 4.3904 | 10.2918 | 12.1394 | 18.3775 | 22.7679 | 2.9522 | 7.3496 | 1.8984 | 1.8476 | 2.492 | 2.6952 | 6.238 | 4.3904 | 10.3018 | 12.1494 | 18.3875 | 22.7779 | 0.01
6.1645 | 8.0356 | 2.0055 | 2.0082 | 3.0274 | 3.0165 | 7.0411 | 5.0329 | 14.2002 | 16.2084 | 23.2495 | 28.2824 | 6.1645 | 8.0456 | 2.0055 | 2.0082 | 3.0274 | 3.0165 | 7.0411 | 5.0329 | 14.2102 | 16.2184 | 23.2595 | 28.2924 | 0.01
3.115 | 7.3749 | 1.9038 | 1.8557 | 2.5192 | 2.7115 | 6.2787 | 4.423 | 10.4899 | 12.3457 | 18.6244 | 23.0474 | 3.115 | 7.3849 | 1.9038 | 1.8557 | 2.5192 | 2.7115 | 6.2787 | 4.423 | 10.4999 | 12.3557 | 18.6344 | 23.0574 | 0.01
6.4626 | 8.1002 | 2.0154 | 2.0231 | 3.0771 | 3.0463 | 7.1157 | 5.0925 | 14.5628 | 16.586 | 23.7016 | 28.7941 | 6.4626 | 8.1102 | 2.0154 | 2.0231 | 3.0771 | 3.0463 | 7.1157 | 5.0925 | 14.5728 | 16.596 | 23.7116 | 28.8041 | 0.01
16.0124 | 10.1694 | 2.3337 | 2.5006 | 4.6687 | 4.0012 | 9.5031 | 7.0025 | 26.1817 | 28.6824 | 38.1855 | 45.1879 | 16.0124 | 10.1794 | 2.3337 | 2.5006 | 4.6687 | 4.0012 | 9.5031 | 7.0025 | 26.1917 | 28.6924 | 38.1955 | 45.1979 | 0.01
1.5673 | 7.0396 | 1.8522 | 1.7784 | 2.2612 | 2.5567 | 5.8918 | 4.1135 | 8.6068 | 10.3852 | 16.277 | 20.3904 | 1.5673 | 7.0496 | 1.8522 | 1.7784 | 2.2612 | 2.5567 | 5.8918 | 4.1135 | 8.6168 | 10.3952 | 16.287 | 20.4004 | 0.01
13.5036 | 9.6258 | 2.2501 | 2.3752 | 4.2506 | 3.7504 | 8.8759 | 6.5007 | 23.1293 | 25.5045 | 34.3804 | 40.8811 | 13.5036 | 9.6358 | 2.2501 | 2.3752 | 4.2506 | 3.7504 | 8.8759 | 6.5007 | 23.1393 | 25.5145 | 34.3904 | 40.8911 | 0.01
0.21402 | 6.7464 | 1.8071 | 1.7107 | 2.0357 | 2.4214 | 5.5535 | 3.8428 | 6.9604 | 8.6711 | 14.2246 | 18.0674 | 0.21402 | 6.7564 | 1.8071 | 1.7107 | 2.0357 | 2.4214 | 5.5535 | 3.8428 | 6.9704 | 8.6811 | 14.2346 | 18.0774 | 0.01
0.14578 | 6.7316 | 1.8049 | 1.7073 | 2.0243 | 2.4146 | 5.5364 | 3.8292 | 6.8774 | 8.5847 | 14.1211 | 17.9503 | 0.14578 | 6.7416 | 1.8049 | 1.7073 | 2.0243 | 2.4146 | 5.5364 | 3.8292 | 6.8874 | 8.5947 | 14.1311 | 17.9603 | 0.01
6.3738 | 8.081 | 2.0125 | 2.0187 | 3.0623 | 3.0374 | 7.0935 | 5.0748 | 14.4548 | 16.4735 | 23.5669 | 28.6417 | 6.3738 | 8.091 | 2.0125 | 2.0187 | 3.0623 | 3.0374 | 7.0935 | 5.0748 | 14.4648 | 16.4835 | 23.5769 | 28.6517 | 0.01
16.4514 | 10.2645 | 2.3484 | 2.5226 | 4.7419 | 4.0451 | 9.6128 | 7.0903 | 26.7158 | 29.2384 | 38.8513 | 45.9415 | 16.4514 | 10.2745 | 2.3484 | 2.5226 | 4.7419 | 4.0451 | 9.6128 | 7.0903 | 26.7258 | 29.2484 | 38.8613 | 45.9515 | 0.01
13.4295 | 9.6097 | 2.2477 | 2.3715 | 4.2383 | 3.743 | 8.8574 | 6.4859 | 23.0392 | 25.4107 | 34.2681 | 40.754 | 13.4295 | 9.6197 | 2.2477 | 2.3715 | 4.2383 | 3.743 | 8.8574 | 6.4859 | 23.0492 | 25.4207 | 34.2781 | 40.764 | 0.01
-7.4375 | 5.0886 | 1.5521 | 1.3281 | 0.76042 | 1.6563 | 3.6406 | 2.3125 | -2.3489 | -1.0208 | 2.6199 | 4.9324 | -7.4375 | 5.0986 | 1.5521 | 1.3281 | 0.76042 | 1.6563 | 3.6406 | 2.3125 | -2.3389 | -1.0108 | 2.6299 | 4.9424 | 0.01
-2.1955 | 6.2243 | 1.7268 | 1.5902 | 1.6341 | 2.1805 | 4.9511 | 3.3609 | 4.0288 | 5.6191 | 10.5702 | 13.9311 | -2.1955 | 6.2343 | 1.7268 | 1.5902 | 1.6341 | 2.1805 | 4.9511 | 3.3609 | 4.0388 | 5.6291 | 10.5802 | 13.9411 | 0.01
-0.86628 | 6.5123 | 1.7711 | 1.6567 | 1.8556 | 2.3134 | 5.2834 | 3.6267 | 5.646 | 7.3027 | 12.5861 | 16.2129 | -0.86628 | 6.5223 | 1.7711 | 1.6567 | 1.8556 | 2.3134 | 5.2834 | 3.6267 | 5.656 | 7.3127 | 12.5961 | 16.2229 | 0.01
7.4517 | 8.3145 | 2.0484 | 2.0726 | 3.2419 | 3.1452 | 7.3629 | 5.2903 | 15.7662 | 17.8388 | 25.2017 | 30.492 | 7.4517 | 8.3245 | 2.0484 | 2.0726 | 3.2419 | 3.1452 | 7.3629 | 5.2903 | 15.7762 | 17.8488 | 25.2117 | 30.502 | 0.01
-4.548 | 5.7146 | 1.6484 | 1.4726 | 1.242 | 1.9452 | 4.363 | 2.8904 | 1.1666 | 2.6392 | 7.0022 | 9.8926 | -4.548 | 5.7246 | 1.6484 | 1.4726 | 1.242 | 1.9452 | 4.363 | 2.8904 | 1.1766 | 2.6492 | 7.0122 | 9.9026 | 0.01
10.1638 | 8.9022 | 2.1388 | 2.2082 | 3.694 | 3.4164 | 8.0409 | 5.8328 | 19.066 | 21.2741 | 29.3151 | 35.1479 | 10.1638 | 8.9122 | 2.1388 | 2.2082 | 3.694 | 3.4164 | 8.0409 | 5.8328 | 19.076 | 21.2841 | 29.3251 | 35.1579 | 0.01
7.2783 | 8.277 | 2.0426 | 2.0639 | 3.213 | 3.1278 | 7.3196 | 5.2557 | 15.5552 | 17.6191 | 24.9387 | 30.1943 | 7.2783 | 8.287 | 2.0426 | 2.0639 | 3.213 | 3.1278 | 7.3196 | 5.2557 | 15.5652 | 17.6291 | 24.9487 | 30.2043 | 0.01
1.4575 | 7.0158 | 1.8486 | 1.7729 | 2.2429 | 2.5457 | 5.8644 | 4.0915 | 8.4732 | 10.2461 | 16.1105 | 20.202 | 1.4575 | 7.0258 | 1.8486 | 1.7729 | 2.2429 | 2.5457 | 5.8644 | 4.0915 | 8.4832 | 10.2561 | 16.1205 | 20.212 | 0.01
-0.57037 | 6.5764 | 1.781 | 1.6715 | 1.9049 | 2.343 | 5.3574 | 3.6859 | 6.0061 | 7.6775 | 13.0349 | 16.7209 | -0.57037 | 6.5864 | 1.781 | 1.6715 | 1.9049 | 2.343 | 5.3574 | 3.6859 | 6.0161 | 7.6875 | 13.0449 | 16.7309 | 0.01
2.3931 | 7.2185 | 1.8798 | 1.8197 | 2.3989 | 2.6393 | 6.0983 | 4.2786 | 9.6116 | 11.4313 | 17.5295 | 21.8082 | 2.3931 | 7.2285 | 1.8798 | 1.8197 | 2.3989 | 2.6393 | 6.0983 | 4.2786 | 9.6216 | 11.4413 | 17.5395 | 21.8182 | 0.01
14.9926 | 9.9484 | 2.2998 | 2.4496 | 4.4988 | 3.8993 | 9.2481 | 6.7985 | 24.941 | 27.3906 | 36.6387 | 43.4372 | 14.9926 | 9.9584 | 2.2998 | 2.4496 | 4.4988 | 3.8993 | 9.2481 | 6.7985 | 24.951 | 27.4006 | 36.6487 | 43.4472 | 0.01
5.5444 | 7.9013 | 1.9848 | 1.9772 | 2.9241 | 2.9544 | 6.8861 | 4.9089 | 13.4457 | 15.423 | 22.3091 | 27.218 | 5.5444 | 7.9113 | 1.9848 | 1.9772 | 2.9241 | 2.9544 | 6.8861 | 4.9089 | 13.4557 | 15.433 | 22.3191 | 27.228 | 0.01
13.6245 | 9.652 | 2.2542 | 2.3812 | 4.2708 | 3.7625 | 8.9061 | 6.5249 | 23.2765 | 25.6577 | 34.5638 | 41.0887 | 13.6245 | 9.662 | 2.2542 | 2.3812 | 4.2708 | 3.7625 | 8.9061 | 6.5249 | 23.2865 | 25.6677 | 34.5738 | 41.0987 | 0.01
1.3803 | 6.9991 | 1.846 | 1.769 | 2.2301 | 2.538 | 5.8451 | 4.0761 | 8.3794 | 10.1484 | 15.9935 | 20.0695 | 1.3803 | 7.0091 | 1.846 | 1.769 | 2.2301 | 2.538 | 5.8451 | 4.0761 | 8.3894 | 10.1584 | 16.0035 | 20.0795 | 0.01
9.4004 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.8501 | 5.6801 | 18.1371 | 20.3071 | 28.1572 | 33.8373 | 9.4004 | 8.7467 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.8501 | 5.6801 | 18.1471 | 20.3171 | 28.1672 | 33.8473 | 0.01
5.1169 | 7.8087 | 1.9706 | 1.9558 | 2.8528 | 2.9117 | 6.7792 | 4.8234 | 12.9255 | 14.8813 | 21.6606 | 26.4839 | 5.1169 | 7.8187 | 1.9706 | 1.9558 | 2.8528 | 2.9117 | 6.7792 | 4.8234 | 12.9355 | 14.8913 | 21.6706 | 26.4939 | 0.01
-0.84508 | 6.5169 | 1.7718 | 1.6577 | 1.8592 | 2.3155 | 5.2887 | 3.631 | 5.6718 | 7.3296 | 12.6183 | 16.2493 | -0.84508 | 6.5269 | 1.7718 | 1.6577 | 1.8592 | 2.3155 | 5.2887 | 3.631 | 5.6818 | 7.3396 | 12.6283 | 16.2593 | 0.01
14.9278 | 9.9344 | 2.2976 | 2.4464 | 4.488 | 3.8928 | 9.232 | 6.7856 | 24.8622 | 27.3086 | 36.5405 | 43.3261 | 14.9278 | 9.9444 | 2.2976 | 2.4464 | 4.488 | 3.8928 | 9.232 | 6.7856 | 24.8722 | 27.3186 | 36.5505 | 43.3361 | 0.01
9.9078 | 8.8467 | 2.1303 | 2.1954 | 3.6513 | 3.3908 | 7.977 | 5.7816 | 18.7545 | 20.9499 | 28.9268 | 34.7084 | 9.9078 | 8.8567 | 2.1303 | 2.1954 | 3.6513 | 3.3908 | 7.977 | 5.7816 | 18.7645 | 20.9599 | 28.9368 | 34.7184 | 0.01
5.1469 | 7.8152 | 1.9716 | 1.9573 | 2.8578 | 2.9147 | 6.7867 | 4.8294 | 12.962 | 14.9194 | 21.7061 | 26.5355 | 5.1469 | 7.8252 | 1.9716 | 1.9573 | 2.8578 | 2.9147 | 6.7867 | 4.8294 | 12.972 | 14.9294 | 21.7161 | 26.5455 | 0.01
3.5807 | 7.4758 | 1.9194 | 1.879 | 2.5968 | 2.7581 | 6.3952 | 4.5161 | 11.0565 | 12.9355 | 19.3307 | 23.8468 | 3.5807 | 7.4858 | 1.9194 | 1.879 | 2.5968 | 2.7581 | 6.3952 | 4.5161 | 11.0665 | 12.9455 | 19.3407 | 23.8568 | 0.01
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2043 | 14.1305 | 20.7616 | 25.4664 | 4.5241 | 7.6902 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2143 | 14.1405 | 20.7716 | 25.4764 | 0.01
8.6671 | 8.5779 | 2.0889 | 2.1334 | 3.4445 | 3.2667 | 7.6668 | 5.5334 | 17.2449 | 19.3783 | 27.0451 | 32.5785 | 8.6671 | 8.5879 | 2.0889 | 2.1334 | 3.4445 | 3.2667 | 7.6668 | 5.5334 | 17.2549 | 19.3883 | 27.0551 | 32.5885 | 0.01
8.4187 | 8.5241 | 2.0806 | 2.1209 | 3.4031 | 3.2419 | 7.6047 | 5.4837 | 16.9428 | 19.0637 | 26.6684 | 32.1522 | 8.4187 | 8.5341 | 2.0806 | 2.1209 | 3.4031 | 3.2419 | 7.6047 | 5.4837 | 16.9528 | 19.0737 | 26.6784 | 32.1622 | 0.01
-9.9815 | 4.5373 | 1.4673 | 1.2009 | 0.33642 | 1.4019 | 3.0046 | 1.8037 | -5.4442 | -4.2432 | -1.2386 | 0.5651 | -9.9815 | 4.5473 | 1.4673 | 1.2009 | 0.33642 | 1.4019 | 3.0046 | 1.8037 | -5.4342 | -4.2332 | -1.2286 | 0.5751 | 0.01
17.7361 | 10.5428 | 2.3912 | 2.5868 | 4.956 | 4.1736 | 9.934 | 7.3472 | 28.2789 | 30.8657 | 40.7997 | 48.1469 | 17.7361 | 10.5528 | 2.3912 | 2.5868 | 4.956 | 4.1736 | 9.934 | 7.3472 | 28.2889 | 30.8757 | 40.8097 | 48.1569 | 0.01
14.6958 | 9.8841 | 2.2899 | 2.4348 | 4.4493 | 3.8696 | 9.174 | 6.7392 | 24.5799 | 27.0147 | 36.1887 | 42.9279 | 14.6958 | 9.8941 | 2.2899 | 2.4348 | 4.4493 | 3.8696 | 9.174 | 6.7392 | 24.5899 | 27.0247 | 36.1987 | 42.9379 | 0.01
6.9703 | 8.2102 | 2.0323 | 2.0485 | 3.1617 | 3.097 | 7.2426 | 5.1941 | 15.1805 | 17.229 | 24.4716 | 29.6656 | 6.9703 | 8.2202 | 2.0323 | 2.0485 | 3.1617 | 3.097 | 7.2426 | 5.1941 | 15.1905 | 17.239 | 24.4816 | 29.6756 | 0.01
-2.7649 | 6.1009 | 1.7078 | 1.5618 | 1.5392 | 2.1235 | 4.8088 | 3.247 | 3.336 | 4.8978 | 9.7066 | 12.9536 | -2.7649 | 6.1109 | 1.7078 | 1.5618 | 1.5392 | 2.1235 | 4.8088 | 3.247 | 3.346 | 4.9078 | 9.7166 | 12.9636 | 0.01
8.3695 | 8.5134 | 2.079 | 2.1185 | 3.3949 | 3.2369 | 7.5924 | 5.4739 | 16.8829 | 19.0014 | 26.5937 | 32.0676 | 8.3695 | 8.5234 | 2.079 | 2.1185 | 3.3949 | 3.2369 | 7.5924 | 5.4739 | 16.8929 | 19.0114 | 26.6037 | 32.0776 | 0.01
0.31258 | 6.7677 | 1.8104 | 1.7156 | 2.0521 | 2.4313 | 5.5781 | 3.8625 | 7.0803 | 8.7959 | 14.3741 | 18.2366 | 0.31258 | 6.7777 | 1.8104 | 1.7156 | 2.0521 | 2.4313 | 5.5781 | 3.8625 | 7.0903 | 8.8059 | 14.3841 | 18.2466 | 0.01
14.0166 | 9.7369 | 2.2672 | 2.4008 | 4.3361 | 3.8017 | 9.0041 | 6.6033 | 23.7535 | 26.1543 | 35.1584 | 41.7618 | 14.0166 | 9.7469 | 2.2672 | 2.4008 | 4.3361 | 3.8017 | 9.0041 | 6.6033 | 23.7635 | 26.1643 | 35.1684 | 41.7718 | 0.01
7.5685 | 8.3398 | 2.0523 | 2.0784 | 3.2614 | 3.1568 | 7.3921 | 5.3137 | 15.9083 | 17.9867 | 25.3788 | 30.6925 | 7.5685 | 8.3498 | 2.0523 | 2.0784 | 3.2614 | 3.1568 | 7.3921 | 5.3137 | 15.9183 | 17.9967 | 25.3888 | 30.7025 | 0.01
5.9811 | 7.9959 | 1.9994 | 1.9991 | 2.9968 | 2.9981 | 6.9953 | 4.9962 | 13.977 | 15.976 | 22.9713 | 27.9675 | 5.9811 | 8.0059 | 1.9994 | 1.9991 | 2.9968 | 2.9981 | 6.9953 | 4.9962 | 13.987 | 15.986 | 22.9813 | 27.9775 | 0.01
3.3981 | 7.4363 | 1.9133 | 1.8699 | 2.5664 | 2.7398 | 6.3495 | 4.4796 | 10.8344 | 12.7043 | 19.0538 | 23.5335 | 3.3981 | 7.4463 | 1.9133 | 1.8699 | 2.5664 | 2.7398 | 6.3495 | 4.4796 | 10.8444 | 12.7143 | 19.0638 | 23.5435 | 0.01
6.2917 | 8.0632 | 2.0097 | 2.0146 | 3.0486 | 3.0292 | 7.0729 | 5.0583 | 14.3549 | 16.3695 | 23.4424 | 28.5007 | 6.2917 | 8.0732 | 2.0097 | 2.0146 | 3.0486 | 3.0292 | 7.0729 | 5.0583 | 14.3649 | 16.3795 | 23.4524 | 28.5107 | 0.01
3.5617 | 7.4717 | 1.9187 | 1.8781 | 2.5936 | 2.7562 | 6.3904 | 4.5123 | 11.0334 | 12.9115 | 19.3019 | 23.8143 | 3.5617 | 7.4817 | 1.9187 | 1.8781 | 2.5936 | 2.7562 | 6.3904 | 4.5123 | 11.0434 | 12.9215 | 19.3119 | 23.8243 | 0.01
13.4989 | 9.6248 | 2.25 | 2.3749 | 4.2498 | 3.7499 | 8.8747 | 6.4998 | 23.1236 | 25.4986 | 34.3733 | 40.8731 | 13.4989 | 9.6348 | 2.25 | 2.3749 | 4.2498 | 3.7499 | 8.8747 | 6.4998 | 23.1336 | 25.5086 | 34.3833 | 40.8831 | 0.01
10.3918 | 8.9516 | 2.1464 | 2.2196 | 3.732 | 3.4392 | 8.098 | 5.8784 | 19.3434 | 21.563 | 29.6609 | 35.5393 | 10.3918 | 8.9616 | 2.1464 | 2.2196 | 3.732 | 3.4392 | 8.098 | 5.8784 | 19.3534 | 21.573 | 29.6709 | 35.5493 | 0.01
1.0548 | 6.9285 | 1.8352 | 1.7527 | 2.1758 | 2.5055 | 5.7637 | 4.011 | 7.9833 | 9.7361 | 15.4998 | 19.5107 | 1.0548 | 6.9385 | 1.8352 | 1.7527 | 2.1758 | 2.5055 | 5.7637 | 4.011 | 7.9933 | 9.7461 | 15.5098 | 19.5207 | 0.01
16.2026 | 10.2106 | 2.3401 | 2.5101 | 4.7004 | 4.0203 | 9.5506 | 7.0405 | 26.4131 | 28.9233 | 38.4739 | 45.5144 | 16.2026 | 10.2206 | 2.3401 | 2.5101 | 4.7004 | 4.0203 | 9.5506 | 7.0405 | 26.4231 | 28.9333 | 38.4839 | 45.5244 | 0.01
8.5304 | 8.5483 | 2.0843 | 2.1265 | 3.4217 | 3.253 | 7.6326 | 5.5061 | 17.0786 | 19.2052 | 26.8378 | 32.3438 | 8.5304 | 8.5583 | 2.0843 | 2.1265 | 3.4217 | 3.253 | 7.6326 | 5.5061 | 17.0886 | 19.2152 | 26.8478 | 32.3538 | 0.01
7.3385 | 8.29 | 2.0446 | 2.0669 | 3.2231 | 3.1339 | 7.3346 | 5.2677 | 15.6285 | 17.6955 | 25.0301 | 30.2978 | 7.3385 | 8.3 | 2.0446 | 2.0669 | 3.2231 | 3.1339 | 7.3346 | 5.2677 | 15.6385 | 17.7055 | 25.0401 | 30.3078 | 0.01
-11.3977 | 4.2305 | 1.4201 | 1.1301 | 0.10039 | 1.2602 | 2.6506 | 1.5205 | -7.1672 | -6.0371 | -3.3865 | -1.866 | -11.3977 | 4.2405 | 1.4201 | 1.1301 | 0.10039 | 1.2602 | 2.6506 | 1.5205 | -7.1572 | -6.0271 | -3.3765 | -1.856 | 0.01
4.3995 | 7.6532 | 1.9466 | 1.92 | 2.7332 | 2.8399 | 6.5999 | 4.6799 | 12.0527 | 13.9727 | 20.5726 | 25.2525 | 4.3995 | 7.6632 | 1.9466 | 1.92 | 2.7332 | 2.8399 | 6.5999 | 4.6799 | 12.0627 | 13.9827 | 20.5826 | 25.2625 | 0.01
14.4103 | 9.8222 | 2.2803 | 2.4205 | 4.4017 | 3.841 | 9.1026 | 6.6821 | 24.2325 | 26.6531 | 35.7556 | 42.4377 | 14.4103 | 9.8322 | 2.2803 | 2.4205 | 4.4017 | 3.841 | 9.1026 | 6.6821 | 24.2425 | 26.6631 | 35.7656 | 42.4477 | 0.01
-4.8914 | 5.6402 | 1.637 | 1.4554 | 1.1848 | 1.9109 | 4.2771 | 2.8217 | 0.74876 | 2.2042 | 6.4813 | 9.3031 | -4.8914 | 5.6502 | 1.637 | 1.4554 | 1.1848 | 1.9109 | 4.2771 | 2.8217 | 0.75876 | 2.2142 | 6.4913 | 9.3131 | 0.01
15.1442 | 9.9812 | 2.3048 | 2.4572 | 4.524 | 3.9144 | 9.2861 | 6.8288 | 25.1255 | 27.5827 | 36.8687 | 43.6976 | 15.1442 | 9.9912 | 2.3048 | 2.4572 | 4.524 | 3.9144 | 9.2861 | 6.8288 | 25.1355 | 27.5927 | 36.8787 | 43.7076 | 0.01
6.8025 | 8.1739 | 2.0267 | 2.0401 | 3.1337 | 3.0802 | 7.2006 | 5.1605 | 14.9763 | 17.0165 | 24.2171 | 29.3776 | 6.8025 | 8.1839 | 2.0267 | 2.0401 | 3.1337 | 3.0802 | 7.2006 | 5.1605 | 14.9863 | 17.0265 | 24.2271 | 29.3876 | 0.01
7.5565 | 8.3372 | 2.0519 | 2.0778 | 3.2594 | 3.1556 | 7.3891 | 5.3113 | 15.8937 | 17.9716 | 25.3607 | 30.672 | 7.5565 | 8.3472 | 2.0519 | 2.0778 | 3.2594 | 3.1556 | 7.3891 | 5.3113 | 15.9037 | 17.9816 | 25.3707 | 30.682 | 0.01
7.1078 | 8.24 | 2.0369 | 2.0554 | 3.1846 | 3.1108 | 7.2769 | 5.2216 | 15.3478 | 17.4032 | 24.6802 | 29.9017 | 7.1078 | 8.25 | 2.0369 | 2.0554 | 3.1846 | 3.1108 | 7.2769 | 5.2216 | 15.3578 | 17.4132 | 24.6902 | 29.9117 | 0.01
5.4872 | 7.8889 | 1.9829 | 1.9744 | 2.9145 | 2.9487 | 6.8718 | 4.8974 | 13.3761 | 15.3505 | 22.2223 | 27.1197 | 5.4872 | 7.8989 | 1.9829 | 1.9744 | 2.9145 | 2.9487 | 6.8718 | 4.8974 | 13.3861 | 15.3605 | 22.2323 | 27.1297 | 0.01
-0.20801 | 6.6549 | 1.7931 | 1.6896 | 1.9653 | 2.3792 | 5.448 | 3.7584 | 6.4469 | 8.1365 | 13.5845 | 17.3429 | -0.20801 | 6.6649 | 1.7931 | 1.6896 | 1.9653 | 2.3792 | 5.448 | 3.7584 | 6.4569 | 8.1465 | 13.5945 | 17.3529 | 0.01
17.5186 | 10.4957 | 2.384 | 2.5759 | 4.9198 | 4.1519 | 9.8796 | 7.3037 | 28.0143 | 30.5902 | 40.4698 | 47.7735 | 17.5186 | 10.5057 | 2.384 | 2.5759 | 4.9198 | 4.1519 | 9.8796 | 7.3037 | 28.0243 | 30.6002 | 40.4798 | 47.7835 | 0.01
10.1071 | 8.8899 | 2.1369 | 2.2054 | 3.6845 | 3.4107 | 8.0268 | 5.8214 | 18.997 | 21.2024 | 29.2292 | 35.0506 | 10.1071 | 8.8999 | 2.1369 | 2.2054 | 3.6845 | 3.4107 | 8.0268 | 5.8214 | 19.007 | 21.2124 | 29.2392 | 35.0606 | 0.01
8.5568 | 8.554 | 2.0852 | 2.1278 | 3.4261 | 3.2557 | 7.6392 | 5.5114 | 17.1107 | 19.2386 | 26.8777 | 32.3891 | 8.5568 | 8.564 | 2.0852 | 2.1278 | 3.4261 | 3.2557 | 7.6392 | 5.5114 | 17.1207 | 19.2486 | 26.8877 | 32.3991 | 0.01
6.2378 | 8.0515 | 2.0079 | 2.0119 | 3.0396 | 3.0238 | 7.0594 | 5.0476 | 14.2893 | 16.3012 | 23.3606 | 28.4082 | 6.2378 | 8.0615 | 2.0079 | 2.0119 | 3.0396 | 3.0238 | 7.0594 | 5.0476 | 14.2993 | 16.3112 | 23.3706 | 28.4182 | 0.01
-0.17002 | 6.6632 | 1.7943 | 1.6915 | 1.9717 | 2.383 | 5.4575 | 3.766 | 6.4931 | 8.1846 | 13.6421 | 17.4081 | -0.17002 | 6.6732 | 1.7943 | 1.6915 | 1.9717 | 2.383 | 5.4575 | 3.766 | 6.5031 | 8.1946 | 13.6521 | 17.4181 | 0.01
14.1065 | 9.7564 | 2.2702 | 2.4053 | 4.3511 | 3.8106 | 9.0266 | 6.6213 | 23.8629 | 26.2682 | 35.2948 | 41.9161 | 14.1065 | 9.7664 | 2.2702 | 2.4053 | 4.3511 | 3.8106 | 9.0266 | 6.6213 | 23.8729 | 26.2782 | 35.3048 | 41.9261 | 0.01
3.8564 | 7.5356 | 1.9285 | 1.8928 | 2.6427 | 2.7856 | 6.4641 | 4.5713 | 11.392 | 13.2848 | 19.7489 | 24.3202 | 3.8564 | 7.5456 | 1.9285 | 1.8928 | 2.6427 | 2.7856 | 6.4641 | 4.5713 | 11.402 | 13.2948 | 19.7589 | 24.3302 | 0.01
-3.938 | 5.8468 | 1.6687 | 1.5031 | 1.3437 | 2.0062 | 4.5155 | 3.0124 | 1.9088 | 3.4119 | 7.9273 | 10.9397 | -3.938 | 5.8568 | 1.6687 | 1.5031 | 1.3437 | 2.0062 | 4.5155 | 3.0124 | 1.9188 | 3.4219 | 7.9373 | 10.9497 | 0.01
8.0713 | 8.4488 | 2.069 | 2.1036 | 3.3452 | 3.2071 | 7.5178 | 5.4143 | 16.5201 | 18.6237 | 26.1415 | 31.5558 | 8.0713 | 8.4588 | 2.069 | 2.1036 | 3.3452 | 3.2071 | 7.5178 | 5.4143 | 16.5301 | 18.6337 | 26.1515 | 31.5658 | 0.01
-3.3537 | 5.9734 | 1.6882 | 1.5323 | 1.4411 | 2.0646 | 4.6616 | 3.1293 | 2.6197 | 4.152 | 8.8136 | 11.9428 | -3.3537 | 5.9834 | 1.6882 | 1.5323 | 1.4411 | 2.0646 | 4.6616 | 3.1293 | 2.6297 | 4.162 | 8.8236 | 11.9528 | 0.01
-2.1228 | 6.2401 | 1.7292 | 1.5939 | 1.6462 | 2.1877 | 4.9693 | 3.3754 | 4.1173 | 5.7111 | 10.6804 | 14.0558 | -2.1228 | 6.2501 | 1.7292 | 1.5939 | 1.6462 | 2.1877 | 4.9693 | 3.3754 | 4.1273 | 5.7211 | 10.6904 | 14.0658 | 0.01
3.4464 | 7.4467 | 1.9149 | 1.8723 | 2.5744 | 2.7446 | 6.3616 | 4.4893 | 10.8932 | 12.7655 | 19.1271 | 23.6164 | 3.4464 | 7.4567 | 1.9149 | 1.8723 | 2.5744 | 2.7446 | 6.3616 | 4.4893 | 10.9032 | 12.7755 | 19.1371 | 23.6264 | 0.01
9.7406 | 8.8105 | 2.1247 | 2.187 | 3.6234 | 3.3741 | 7.9351 | 5.7481 | 18.551 | 20.7381 | 28.6732 | 34.4213 | 9.7406 | 8.8205 | 2.1247 | 2.187 | 3.6234 | 3.3741 | 7.9351 | 5.7481 | 18.561 | 20.7481 | 28.6832 | 34.4313 | 0.01
14.3409 | 9.8072 | 2.278 | 2.417 | 4.3902 | 3.8341 | 9.0852 | 6.6682 | 24.1481 | 26.5652 | 35.6504 | 42.3186 | 14.3409 | 9.8172 | 2.278 | 2.417 | 4.3902 | 3.8341 | 9.0852 | 6.6682 | 24.1581 | 26.5752 | 35.6604 | 42.3286 | 0.01
10.4801 | 8.9707 | 2.1493 | 2.224 | 3.7467 | 3.448 | 8.12 | 5.896 | 19.4508 | 21.6748 | 29.7948 | 35.6908 | 10.4801 | 8.9807 | 2.1493 | 2.224 | 3.7467 | 3.448 | 8.12 | 5.896 | 19.4608 | 21.6848 | 29.8048 | 35.7008 | 0.01
1.9422 | 7.1208 | 1.8647 | 1.7971 | 2.3237 | 2.5942 | 5.9855 | 4.1884 | 9.063 | 10.8601 | 16.8456 | 21.0341 | 1.9422 | 7.1308 | 1.8647 | 1.7971 | 2.3237 | 2.5942 | 5.9855 | 4.1884 | 9.073 | 10.8701 | 16.8556 | 21.0441 | 0.01
-3.5251 | 5.9362 | 1.6825 | 1.5237 | 1.4125 | 2.0475 | 4.6187 | 3.095 | 2.4111 | 3.9349 | 8.5536 | 11.6486 | -3.5251 | 5.9462 | 1.6825 | 1.5237 | 1.4125 | 2.0475 | 4.6187 | 3.095 | 2.4211 | 3.9449 | 8.5636 | 11.6586 | 0.01
6.3941 | 8.0854 | 2.0131 | 2.0197 | 3.0657 | 3.0394 | 7.0985 | 5.0788 | 14.4795 | 16.4992 | 23.5978 | 28.6766 | 6.3941 | 8.0954 | 2.0131 | 2.0197 | 3.0657 | 3.0394 | 7.0985 | 5.0788 | 14.4895 | 16.5092 | 23.6078 | 28.6866 | 0.01
8.1827 | 8.4729 | 2.0728 | 2.1091 | 3.3638 | 3.2183 | 7.5457 | 5.4365 | 16.6556 | 18.7647 | 26.3104 | 31.7469 | 8.1827 | 8.4829 | 2.0728 | 2.1091 | 3.3638 | 3.2183 | 7.5457 | 5.4365 | 16.6656 | 18.7747 | 26.3204 | 31.7569 | 0.01
13.4254 | 9.6088 | 2.2475 | 2.3713 | 4.2376 | 3.7425 | 8.8563 | 6.4851 | 23.0342 | 25.4055 | 34.2618 | 40.7469 | 13.4254 | 9.6188 | 2.2475 | 2.3713 | 4.2376 | 3.7425 | 8.8563 | 6.4851 | 23.0442 | 25.4155 | 34.2718 | 40.7569 | 0.01
12.781 | 9.4692 | 2.226 | 2.339 | 4.1302 | 3.6781 | 8.6952 | 6.3562 | 22.2502 | 24.5892 | 33.2844 | 39.6406 | 12.781 | 9.4792 | 2.226 | 2.339 | 4.1302 | 3.6781 | 8.6952 | 6.3562 | 22.2602 | 24.5992 | 33.2944 | 39.6506 | 0.01
5.32 | 7.8527 | 1.9773 | 1.966 | 2.8867 | 2.932 | 6.83 | 4.864 | 13.1726 | 15.1386 | 21.9686 | 26.8326 | 5.32 | 7.8627 | 1.9773 | 1.966 | 2.8867 | 2.932 | 6.83 | 4.864 | 13.1826 | 15.1486 | 21.9786 | 26.8426 | 0.01
0.36357 | 6.7788 | 1.8121 | 1.7182 | 2.0606 | 2.4364 | 5.5909 | 3.8727 | 7.1423 | 8.8605 | 14.4514 | 18.3241 | 0.36357 | 6.7888 | 1.8121 | 1.7182 | 2.0606 | 2.4364 | 5.5909 | 3.8727 | 7.1523 | 8.8705 | 14.4614 | 18.3341 | 0.01
4.4875 | 7.6723 | 1.9496 | 1.9244 | 2.7479 | 2.8487 | 6.6219 | 4.6975 | 12.1597 | 14.0841 | 20.706 | 25.4035 | 4.4875 | 7.6823 | 1.9496 | 1.9244 | 2.7479 | 2.8487 | 6.6219 | 4.6975 | 12.1697 | 14.0941 | 20.716 | 25.4135 | 0.01
16.3134 | 10.2346 | 2.3438 | 2.5157 | 4.7189 | 4.0313 | 9.5783 | 7.0627 | 26.548 | 29.0636 | 38.642 | 45.7047 | 16.3134 | 10.2446 | 2.3438 | 2.5157 | 4.7189 | 4.0313 | 9.5783 | 7.0627 | 26.558 | 29.0736 | 38.652 | 45.7147 | 0.01
4.2492 | 7.6207 | 1.9416 | 1.9125 | 2.7082 | 2.8249 | 6.5623 | 4.6498 | 11.8698 | 13.7823 | 20.3446 | 24.9944 | 4.2492 | 7.6307 | 1.9416 | 1.9125 | 2.7082 | 2.8249 | 6.5623 | 4.6498 | 11.8798 | 13.7923 | 20.3546 | 25.0044 | 0.01
3.7637 | 7.5155 | 1.9255 | 1.8882 | 2.6273 | 2.7764 | 6.4409 | 4.5527 | 11.2792 | 13.1674 | 19.6083 | 24.161 | 3.7637 | 7.5255 | 1.9255 | 1.8882 | 2.6273 | 2.7764 | 6.4409 | 4.5527 | 11.2892 | 13.1774 | 19.6183 | 24.171 | 0.01
-1.4859 | 6.3781 | 1.7505 | 1.6257 | 1.7524 | 2.2514 | 5.1285 | 3.5028 | 4.8922 | 6.5179 | 11.6464 | 15.1492 | -1.4859 | 6.3881 | 1.7505 | 1.6257 | 1.7524 | 2.2514 | 5.1285 | 3.5028 | 4.9022 | 6.5279 | 11.6564 | 15.1592 | 0.01
13.1201 | 9.5427 | 2.2373 | 2.356 | 4.1867 | 3.712 | 8.78 | 6.424 | 22.6628 | 25.0188 | 33.7988 | 40.2228 | 13.1201 | 9.5527 | 2.2373 | 2.356 | 4.1867 | 3.712 | 8.78 | 6.424 | 22.6728 | 25.0288 | 33.8088 | 40.2328 | 0.01
1.2847 | 6.9783 | 1.8428 | 1.7642 | 2.2141 | 2.5285 | 5.8212 | 4.0569 | 8.263 | 10.0273 | 15.8484 | 19.9054 | 1.2847 | 6.9883 | 1.8428 | 1.7642 | 2.2141 | 2.5285 | 5.8212 | 4.0569 | 8.273 | 10.0373 | 15.8584 | 19.9154 | 0.01
10.1324 | 8.8954 | 2.1377 | 2.2066 | 3.6887 | 3.4132 | 8.0331 | 5.8265 | 19.0278 | 21.2344 | 29.2675 | 35.094 | 10.1324 | 8.9054 | 2.1377 | 2.2066 | 3.6887 | 3.4132 | 8.0331 | 5.8265 | 19.0378 | 21.2444 | 29.2775 | 35.104 | 0.01
19.078 | 10.8336 | 2.4359 | 2.6539 | 5.1797 | 4.3078 | 10.2695 | 7.6156 | 29.9115 | 32.5654 | 42.8349 | 50.4505 | 19.078 | 10.8436 | 2.4359 | 2.6539 | 5.1797 | 4.3078 | 10.2695 | 7.6156 | 29.9215 | 32.5754 | 42.8449 | 50.4605 | 0.01
14.4903 | 9.8396 | 2.283 | 2.4245 | 4.4151 | 3.849 | 9.1226 | 6.6981 | 24.3299 | 26.7544 | 35.877 | 42.5751 | 14.4903 | 9.8496 | 2.283 | 2.4245 | 4.4151 | 3.849 | 9.1226 | 6.6981 | 24.3399 | 26.7644 | 35.887 | 42.5851 | 0.01
1.3037 | 6.9825 | 1.8435 | 1.7652 | 2.2173 | 2.5304 | 5.8259 | 4.0607 | 8.2862 | 10.0514 | 15.8773 | 19.9381 | 1.3037 | 6.9925 | 1.8435 | 1.7652 | 2.2173 | 2.5304 | 5.8259 | 4.0607 | 8.2962 | 10.0614 | 15.8873 | 19.9481 | 0.01
4.5343 | 7.6824 | 1.9511 | 1.9267 | 2.7557 | 2.8534 | 6.6336 | 4.7069 | 12.2167 | 14.1434 | 20.777 | 25.4838 | 4.5343 | 7.6924 | 1.9511 | 1.9267 | 2.7557 | 2.8534 | 6.6336 | 4.7069 | 12.2267 | 14.1534 | 20.787 | 25.4938 | 0.01
8.9171 | 8.632 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5834 | 17.5492 | 19.695 | 27.4243 | 33.0077 | 8.9171 | 8.642 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5834 | 17.5592 | 19.705 | 27.4343 | 33.0177 | 0.01
4.2696 | 7.6251 | 1.9423 | 1.9135 | 2.7116 | 2.827 | 6.5674 | 4.6539 | 11.8947 | 13.8082 | 20.3756 | 25.0295 | 4.2696 | 7.6351 | 1.9423 | 1.9135 | 2.7116 | 2.827 | 6.5674 | 4.6539 | 11.9047 | 13.8182 | 20.3856 | 25.0395 | 0.01
1.8769 | 7.1067 | 1.8626 | 1.7938 | 2.3128 | 2.5877 | 5.9692 | 4.1754 | 8.9835 | 10.7774 | 16.7466 | 20.922 | 1.8769 | 7.1167 | 1.8626 | 1.7938 | 2.3128 | 2.5877 | 5.9692 | 4.1754 | 8.9935 | 10.7874 | 16.7566 | 20.932 | 0.01
1.2769 | 6.9767 | 1.8426 | 1.7638 | 2.2128 | 2.5277 | 5.8192 | 4.0554 | 8.2536 | 10.0174 | 15.8367 | 19.8921 | 1.2769 | 6.9867 | 1.8426 | 1.7638 | 2.2128 | 2.5277 | 5.8192 | 4.0554 | 8.2636 | 10.0274 | 15.8467 | 19.9021 | 0.01
4.4293 | 7.6597 | 1.9476 | 1.9215 | 2.7382 | 2.8429 | 6.6073 | 4.6859 | 12.089 | 14.0105 | 20.6178 | 25.3037 | 4.4293 | 7.6697 | 1.9476 | 1.9215 | 2.7382 | 2.8429 | 6.6073 | 4.6859 | 12.099 | 14.0205 | 20.6278 | 25.3137 | 0.01
-0.71252 | 6.5456 | 1.7762 | 1.6644 | 1.8812 | 2.3287 | 5.3219 | 3.6575 | 5.8331 | 7.4975 | 12.8193 | 16.4768 | -0.71252 | 6.5556 | 1.7762 | 1.6644 | 1.8812 | 2.3287 | 5.3219 | 3.6575 | 5.8431 | 7.5075 | 12.8293 | 16.4868 | 0.01
0.56209 | 6.8218 | 1.8187 | 1.7281 | 2.0937 | 2.4562 | 5.6405 | 3.9124 | 7.3839 | 9.112 | 14.7525 | 18.6649 | 0.56209 | 6.8318 | 1.8187 | 1.7281 | 2.0937 | 2.4562 | 5.6405 | 3.9124 | 7.3939 | 9.122 | 14.7625 | 18.6749 | 0.01
3.2537 | 7.405 | 1.9085 | 1.8627 | 2.5423 | 2.7254 | 6.3134 | 4.4507 | 10.6587 | 12.5214 | 18.8348 | 23.2856 | 3.2537 | 7.415 | 1.9085 | 1.8627 | 2.5423 | 2.7254 | 6.3134 | 4.4507 | 10.6687 | 12.5314 | 18.8448 | 23.2956 | 0.01
4.564 | 7.6889 | 1.9521 | 1.9282 | 2.7607 | 2.8564 | 6.641 | 4.7128 | 12.2529 | 14.1811 | 20.8221 | 25.5349 | 4.564 | 7.6989 | 1.9521 | 1.9282 | 2.7607 | 2.8564 | 6.641 | 4.7128 | 12.2629 | 14.1911 | 20.8321 | 25.5449 | 0.01
17.5236 | 10.4968 | 2.3841 | 2.5762 | 4.9206 | 4.1524 | 9.8809 | 7.3047 | 28.0204 | 30.5966 | 40.4775 | 47.7823 | 17.5236 | 10.5068 | 2.3841 | 2.5762 | 4.9206 | 4.1524 | 9.8809 | 7.3047 | 28.0304 | 30.6066 | 40.4875 | 47.7923 | 0.01
8.2391 | 8.4851 | 2.0746 | 2.112 | 3.3732 | 3.2239 | 7.5598 | 5.4478 | 16.7242 | 18.8362 | 26.396 | 31.8438 | 8.2391 | 8.4951 | 2.0746 | 2.112 | 3.3732 | 3.2239 | 7.5598 | 5.4478 | 16.7342 | 18.8462 | 26.406 | 31.8538 | 0.01
11.3647 | 9.1623 | 2.1788 | 2.2682 | 3.8941 | 3.5365 | 8.3412 | 6.0729 | 20.527 | 22.7953 | 31.1364 | 37.2094 | 11.3647 | 9.1723 | 2.1788 | 2.2682 | 3.8941 | 3.5365 | 8.3412 | 6.0729 | 20.537 | 22.8053 | 31.1464 | 37.2194 | 0.01
-1.6549 | 6.3414 | 1.7448 | 1.6173 | 1.7242 | 2.2345 | 5.0863 | 3.469 | 4.6866 | 6.3038 | 11.3901 | 14.8591 | -1.6549 | 6.3514 | 1.7448 | 1.6173 | 1.7242 | 2.2345 | 5.0863 | 3.469 | 4.6966 | 6.3138 | 11.4001 | 14.8691 | 0.01
8.9418 | 8.6374 | 2.0981 | 2.1471 | 3.4903 | 3.2942 | 7.7354 | 5.5884 | 17.5791 | 19.7262 | 27.4617 | 33.05 | 8.9418 | 8.6474 | 2.0981 | 2.1471 | 3.4903 | 3.2942 | 7.7354 | 5.5884 | 17.5891 | 19.7362 | 27.4717 | 33.06 | 0.01
11.8561 | 9.2688 | 2.1952 | 2.2928 | 3.976 | 3.5856 | 8.464 | 6.1712 | 21.1249 | 23.4177 | 31.8817 | 38.053 | 11.8561 | 9.2788 | 2.1952 | 2.2928 | 3.976 | 3.5856 | 8.464 | 6.1712 | 21.1349 | 23.4277 | 31.8917 | 38.063 | 0.01
10.4949 | 8.9739 | 2.1498 | 2.2247 | 3.7492 | 3.4495 | 8.1237 | 5.899 | 19.4688 | 21.6936 | 29.8173 | 35.7163 | 10.4949 | 8.9839 | 2.1498 | 2.2247 | 3.7492 | 3.4495 | 8.1237 | 5.899 | 19.4788 | 21.7036 | 29.8273 | 35.7263 | 0.01
10.916 | 9.0651 | 2.1639 | 2.2458 | 3.8193 | 3.4916 | 8.229 | 5.9832 | 19.9811 | 22.2269 | 30.4559 | 36.4391 | 10.916 | 9.0751 | 2.1639 | 2.2458 | 3.8193 | 3.4916 | 8.229 | 5.9832 | 19.9911 | 22.2369 | 30.4659 | 36.4491 | 0.01
9.4413 | 8.7456 | 2.1147 | 2.1721 | 3.5736 | 3.3441 | 7.8603 | 5.6883 | 18.1869 | 20.359 | 28.2193 | 33.9076 | 9.4413 | 8.7556 | 2.1147 | 2.1721 | 3.5736 | 3.3441 | 7.8603 | 5.6883 | 18.1969 | 20.369 | 28.2293 | 33.9176 | 0.01
3.8479 | 7.5337 | 1.9283 | 1.8924 | 2.6413 | 2.7848 | 6.462 | 4.5696 | 11.3817 | 13.2741 | 19.7361 | 24.3056 | 3.8479 | 7.5437 | 1.9283 | 1.8924 | 2.6413 | 2.7848 | 6.462 | 4.5696 | 11.3917 | 13.2841 | 19.7461 | 24.3156 | 0.01
0.12473 | 6.727 | 1.8042 | 1.7062 | 2.0208 | 2.4125 | 5.5312 | 3.8249 | 6.8518 | 8.558 | 14.0892 | 17.9141 | 0.12473 | 6.737 | 1.8042 | 1.7062 | 2.0208 | 2.4125 | 5.5312 | 3.8249 | 6.8618 | 8.568 | 14.0992 | 17.9241 | 0.01
15.3826 | 10.0329 | 2.3128 | 2.4691 | 4.5638 | 3.9383 | 9.3457 | 6.8765 | 25.4155 | 27.8847 | 37.2303 | 44.1068 | 15.3826 | 10.0429 | 2.3128 | 2.4691 | 4.5638 | 3.9383 | 9.3457 | 6.8765 | 25.4255 | 27.8947 | 37.2403 | 44.1168 | 0.01
5.5747 | 7.9078 | 1.9858 | 1.9787 | 2.9291 | 2.9575 | 6.8937 | 4.9149 | 13.4825 | 15.4613 | 22.3549 | 27.2699 | 5.5747 | 7.9178 | 1.9858 | 1.9787 | 2.9291 | 2.9575 | 6.8937 | 4.9149 | 13.4925 | 15.4713 | 22.3649 | 27.2799 | 0.01
7.5314 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8632 | 17.9398 | 25.3227 | 30.629 | 7.5314 | 8.3418 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8732 | 17.9498 | 25.3327 | 30.639 | 0.01
5.6536 | 7.9249 | 1.9885 | 1.9827 | 2.9423 | 2.9654 | 6.9134 | 4.9307 | 13.5786 | 15.5612 | 22.4746 | 27.4054 | 5.6536 | 7.9349 | 1.9885 | 1.9827 | 2.9423 | 2.9654 | 6.9134 | 4.9307 | 13.5886 | 15.5712 | 22.4846 | 27.4154 | 0.01
7.9005 | 8.4118 | 2.0633 | 2.095 | 3.3167 | 3.19 | 7.4751 | 5.3801 | 16.3122 | 18.4073 | 25.8824 | 31.2625 | 7.9005 | 8.4218 | 2.0633 | 2.095 | 3.3167 | 3.19 | 7.4751 | 5.3801 | 16.3222 | 18.4173 | 25.8924 | 31.2725 | 0.01
2.7503 | 7.2959 | 1.8917 | 1.8375 | 2.4584 | 2.675 | 6.1876 | 4.3501 | 10.0462 | 11.8837 | 18.0713 | 22.4213 | 2.7503 | 7.3059 | 1.8917 | 1.8375 | 2.4584 | 2.675 | 6.1876 | 4.3501 | 10.0562 | 11.8937 | 18.0813 | 22.4313 | 0.01
15.9912 | 10.1648 | 2.333 | 2.4996 | 4.6652 | 3.9991 | 9.4978 | 6.9982 | 26.156 | 28.6556 | 38.1534 | 45.1516 | 15.9912 | 10.1748 | 2.333 | 2.4996 | 4.6652 | 3.9991 | 9.4978 | 6.9982 | 26.166 | 28.6656 | 38.1634 | 45.1616 | 0.01
3.5741 | 7.4744 | 1.9191 | 1.8787 | 2.5957 | 2.7574 | 6.3935 | 4.5148 | 11.0485 | 12.9272 | 19.3207 | 23.8356 | 3.5741 | 7.4844 | 1.9191 | 1.8787 | 2.5957 | 2.7574 | 6.3935 | 4.5148 | 11.0585 | 12.9372 | 19.3307 | 23.8456 | 0.01
8.2161 | 8.4802 | 2.0739 | 2.1108 | 3.3693 | 3.2216 | 7.554 | 5.4432 | 16.6962 | 18.8071 | 26.3611 | 31.8043 | 8.2161 | 8.4902 | 2.0739 | 2.1108 | 3.3693 | 3.2216 | 7.554 | 5.4432 | 16.7062 | 18.8171 | 26.3711 | 31.8143 | 0.01
11.5303 | 9.1982 | 2.1843 | 2.2765 | 3.9217 | 3.553 | 8.3826 | 6.1061 | 20.7286 | 23.0051 | 31.3877 | 37.4937 | 11.5303 | 9.2082 | 2.1843 | 2.2765 | 3.9217 | 3.553 | 8.3826 | 6.1061 | 20.7386 | 23.0151 | 31.3977 | 37.5037 | 0.01
9.1597 | 8.6846 | 2.1053 | 2.158 | 3.5266 | 3.316 | 7.7899 | 5.6319 | 17.8443 | 20.0023 | 27.7923 | 33.4242 | 9.1597 | 8.6946 | 2.1053 | 2.158 | 3.5266 | 3.316 | 7.7899 | 5.6319 | 17.8543 | 20.0123 | 27.8023 | 33.4342 | 0.01
12.984 | 9.5132 | 2.2328 | 2.3492 | 4.164 | 3.6984 | 8.746 | 6.3968 | 22.4972 | 24.8464 | 33.5924 | 39.9892 | 12.984 | 9.5232 | 2.2328 | 2.3492 | 4.164 | 3.6984 | 8.746 | 6.3968 | 22.5072 | 24.8564 | 33.6024 | 39.9992 | 0.01
18.7844 | 10.7699 | 2.4261 | 2.6392 | 5.1307 | 4.2784 | 10.1961 | 7.5569 | 29.5543 | 32.1935 | 42.3896 | 49.9465 | 18.7844 | 10.7799 | 2.4261 | 2.6392 | 5.1307 | 4.2784 | 10.1961 | 7.5569 | 29.5643 | 32.2035 | 42.3996 | 49.9565 | 0.01
9.9286 | 8.8512 | 2.131 | 2.1964 | 3.6548 | 3.3929 | 7.9822 | 5.7857 | 18.7799 | 20.9763 | 28.9585 | 34.7442 | 9.9286 | 8.8612 | 2.131 | 2.1964 | 3.6548 | 3.3929 | 7.9822 | 5.7857 | 18.7899 | 20.9863 | 28.9685 | 34.7542 | 0.01
2.0856 | 7.1519 | 1.8695 | 1.8043 | 2.3476 | 2.6086 | 6.0214 | 4.2171 | 9.2375 | 11.0418 | 17.0632 | 21.2803 | 2.0856 | 7.1619 | 1.8695 | 1.8043 | 2.3476 | 2.6086 | 6.0214 | 4.2171 | 9.2475 | 11.0518 | 17.0732 | 21.2903 | 0.01
7.7123 | 8.371 | 2.0571 | 2.0856 | 3.2854 | 3.1712 | 7.4281 | 5.3425 | 16.0833 | 18.169 | 25.5971 | 30.9395 | 7.7123 | 8.381 | 2.0571 | 2.0856 | 3.2854 | 3.1712 | 7.4281 | 5.3425 | 16.0933 | 18.179 | 25.6071 | 30.9495 | 0.01
4.3418 | 7.6407 | 1.9447 | 1.9171 | 2.7236 | 2.8342 | 6.5855 | 4.6684 | 11.9825 | 13.8996 | 20.4851 | 25.1535 | 4.3418 | 7.6507 | 1.9447 | 1.9171 | 2.7236 | 2.8342 | 6.5855 | 4.6684 | 11.9925 | 13.9096 | 20.4951 | 25.1635 | 0.01
11.026 | 9.089 | 2.1675 | 2.2513 | 3.8377 | 3.5026 | 8.2565 | 6.0052 | 20.115 | 22.3663 | 30.6228 | 36.628 | 11.026 | 9.099 | 2.1675 | 2.2513 | 3.8377 | 3.5026 | 8.2565 | 6.0052 | 20.125 | 22.3763 | 30.6328 | 36.638 | 0.01
17.0012 | 10.3836 | 2.3667 | 2.5501 | 4.8335 | 4.1001 | 9.7503 | 7.2002 | 27.3849 | 29.9349 | 39.6852 | 46.8855 | 17.0012 | 10.3936 | 2.3667 | 2.5501 | 4.8335 | 4.1001 | 9.7503 | 7.2002 | 27.3949 | 29.9449 | 39.6952 | 46.8955 | 0.01
2.8353 | 7.3143 | 1.8945 | 1.8418 | 2.4726 | 2.6835 | 6.2088 | 4.3671 | 10.1496 | 11.9914 | 18.2002 | 22.5673 | 2.8353 | 7.3243 | 1.8945 | 1.8418 | 2.4726 | 2.6835 | 6.2088 | 4.3671 | 10.1596 | 12.0014 | 18.2102 | 22.5773 | 0.01
2.9314 | 7.3351 | 1.8977 | 1.8466 | 2.4886 | 2.6931 | 6.2329 | 4.3863 | 10.2666 | 12.1132 | 18.346 | 22.7323 | 2.9314 | 7.3451 | 1.8977 | 1.8466 | 2.4886 | 2.6931 | 6.2329 | 4.3863 | 10.2766 | 12.1232 | 18.356 | 22.7423 | 0.01
0.2458 | 6.7533 | 1.8082 | 1.7123 | 2.041 | 2.4246 | 5.5615 | 3.8492 | 6.9991 | 8.7114 | 14.2728 | 18.122 | 0.2458 | 6.7633 | 1.8082 | 1.7123 | 2.041 | 2.4246 | 5.5615 | 3.8492 | 7.0091 | 8.7214 | 14.2828 | 18.132 | 0.01
6.4896 | 8.1061 | 2.0163 | 2.0245 | 3.0816 | 3.049 | 7.1224 | 5.0979 | 14.5957 | 16.6202 | 23.7426 | 28.8405 | 6.4896 | 8.1161 | 2.0163 | 2.0245 | 3.0816 | 3.049 | 7.1224 | 5.0979 | 14.6057 | 16.6302 | 23.7526 | 28.8505 | 0.01
-6.0201 | 5.3956 | 1.5993 | 1.399 | 0.99665 | 1.798 | 3.995 | 2.596 | -0.62448 | 0.77452 | 4.7695 | 7.3655 | -6.0201 | 5.4056 | 1.5993 | 1.399 | 0.99665 | 1.798 | 3.995 | 2.596 | -0.61448 | 0.78452 | 4.7795 | 7.3755 | 0.01
3.3036 | 7.4158 | 1.9101 | 1.8652 | 2.5506 | 2.7304 | 6.3259 | 4.4607 | 10.7194 | 12.5846 | 18.9105 | 23.3712 | 3.3036 | 7.4258 | 1.9101 | 1.8652 | 2.5506 | 2.7304 | 6.3259 | 4.4607 | 10.7294 | 12.5946 | 18.9205 | 23.3812 | 0.01
8.8664 | 8.621 | 2.0955 | 2.1433 | 3.4777 | 3.2866 | 7.7166 | 5.5733 | 17.4874 | 19.6307 | 27.3473 | 32.9206 | 8.8664 | 8.631 | 2.0955 | 2.1433 | 3.4777 | 3.2866 | 7.7166 | 5.5733 | 17.4974 | 19.6407 | 27.3573 | 32.9306 | 0.01
13.6777 | 9.6635 | 2.2559 | 2.3839 | 4.2796 | 3.7678 | 8.9194 | 6.5355 | 23.3412 | 25.7251 | 34.6446 | 41.1801 | 13.6777 | 9.6735 | 2.2559 | 2.3839 | 4.2796 | 3.7678 | 8.9194 | 6.5355 | 23.3512 | 25.7351 | 34.6546 | 41.1901 | 0.01
7.5315 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8633 | 17.9399 | 25.3228 | 30.629 | 7.5315 | 8.3418 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8733 | 17.9499 | 25.3328 | 30.639 | 0.01
6.5002 | 8.1084 | 2.0167 | 2.025 | 3.0834 | 3.05 | 7.1251 | 5.1 | 14.6086 | 16.6336 | 23.7587 | 28.8587 | 6.5002 | 8.1184 | 2.0167 | 2.025 | 3.0834 | 3.05 | 7.1251 | 5.1 | 14.6186 | 16.6436 | 23.7687 | 28.8687 | 0.01
12.3442 | 9.3746 | 2.2115 | 2.3172 | 4.0574 | 3.6344 | 8.586 | 6.2688 | 21.7187 | 24.036 | 32.622 | 38.8908 | 12.3442 | 9.3846 | 2.2115 | 2.3172 | 4.0574 | 3.6344 | 8.586 | 6.2688 | 21.7287 | 24.046 | 32.632 | 38.9008 | 0.01
-2.6847 | 6.1183 | 1.7105 | 1.5658 | 1.5526 | 2.1315 | 4.8288 | 3.2631 | 3.4337 | 4.9994 | 9.8283 | 13.0913 | -2.6847 | 6.1283 | 1.7105 | 1.5658 | 1.5526 | 2.1315 | 4.8288 | 3.2631 | 3.4437 | 5.0094 | 9.8383 | 13.1013 | 0.01
11.3098 | 9.1505 | 2.177 | 2.2655 | 3.885 | 3.531 | 8.3274 | 6.062 | 20.4602 | 22.7257 | 31.0532 | 37.1151 | 11.3098 | 9.1605 | 2.177 | 2.2655 | 3.885 | 3.531 | 8.3274 | 6.062 | 20.4702 | 22.7357 | 31.0632 | 37.1251 | 0.01
11.2312 | 9.1334 | 2.1744 | 2.2616 | 3.8719 | 3.5231 | 8.3078 | 6.0462 | 20.3646 | 22.6262 | 30.934 | 36.9802 | 11.2312 | 9.1434 | 2.1744 | 2.2616 | 3.8719 | 3.5231 | 8.3078 | 6.0462 | 20.3746 | 22.6362 | 30.944 | 36.9902 | 0.01
-2.2417 | 6.2143 | 1.7253 | 1.5879 | 1.6264 | 2.1758 | 4.9396 | 3.3517 | 3.9725 | 5.5605 | 10.5 | 13.8517 | -2.2417 | 6.2243 | 1.7253 | 1.5879 | 1.6264 | 2.1758 | 4.9396 | 3.3517 | 3.9825 | 5.5705 | 10.51 | 13.8617 | 0.01
13.1798 | 9.5556 | 2.2393 | 2.359 | 4.1966 | 3.718 | 8.795 | 6.436 | 22.7354 | 25.0944 | 33.8894 | 40.3253 | 13.1798 | 9.5656 | 2.2393 | 2.359 | 4.1966 | 3.718 | 8.795 | 6.436 | 22.7454 | 25.1044 | 33.8994 | 40.3353 | 0.01
-6.0136 | 5.397 | 1.5995 | 1.3993 | 0.99773 | 1.7986 | 3.9966 | 2.5973 | -0.61658 | 0.78274 | 4.7793 | 7.3766 | -6.0136 | 5.407 | 1.5995 | 1.3993 | 0.99773 | 1.7986 | 3.9966 | 2.5973 | -0.60658 | 0.79274 | 4.7893 | 7.3866 | 0.01
2.8839 | 7.3249 | 1.8961 | 1.8442 | 2.4807 | 2.6884 | 6.221 | 4.3768 | 10.2088 | 12.053 | 18.274 | 22.6508 | 2.8839 | 7.3349 | 1.8961 | 1.8442 | 2.4807 | 2.6884 | 6.221 | 4.3768 | 10.2188 | 12.063 | 18.284 | 22.6608 | 0.01
8.9173 | 8.6321 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5835 | 17.5494 | 19.6953 | 27.4246 | 33.0081 | 8.9173 | 8.6421 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5835 | 17.5594 | 19.7053 | 27.4346 | 33.0181 | 0.01
7.3594 | 8.2945 | 2.0453 | 2.068 | 3.2266 | 3.1359 | 7.3399 | 5.2719 | 15.654 | 17.722 | 25.0618 | 30.3337 | 7.3594 | 8.3045 | 2.0453 | 2.068 | 3.2266 | 3.1359 | 7.3399 | 5.2719 | 15.664 | 17.732 | 25.0718 | 30.3437 | 0.01
10.6967 | 9.0176 | 2.1566 | 2.2348 | 3.7828 | 3.4697 | 8.1742 | 5.9393 | 19.7143 | 21.9491 | 30.1233 | 36.0626 | 10.6967 | 9.0276 | 2.1566 | 2.2348 | 3.7828 | 3.4697 | 8.1742 | 5.9393 | 19.7243 | 21.9591 | 30.1333 | 36.0726 | 0.01
14.8238 | 9.9118 | 2.2941 | 2.4412 | 4.4706 | 3.8824 | 9.206 | 6.7648 | 24.7356 | 27.1768 | 36.3828 | 43.1475 | 14.8238 | 9.9218 | 2.2941 | 2.4412 | 4.4706 | 3.8824 | 9.206 | 6.7648 | 24.7456 | 27.1868 | 36.3928 | 43.1575 | 0.01
11.6384 | 9.2216 | 2.1879 | 2.2819 | 3.9397 | 3.5638 | 8.4096 | 6.1277 | 20.86 | 23.1419 | 31.5515 | 37.6792 | 11.6384 | 9.2316 | 2.1879 | 2.2819 | 3.9397 | 3.5638 | 8.4096 | 6.1277 | 20.87 | 23.1519 | 31.5615 | 37.6892 | 0.01
17.6788 | 10.5304 | 2.3893 | 2.5839 | 4.9465 | 4.1679 | 9.9197 | 7.3358 | 28.2092 | 30.7931 | 40.7128 | 48.0486 | 17.6788 | 10.5404 | 2.3893 | 2.5839 | 4.9465 | 4.1679 | 9.9197 | 7.3358 | 28.2192 | 30.8031 | 40.7228 | 48.0586 | 0.01
4.3589 | 7.6444 | 1.9453 | 1.9179 | 2.7265 | 2.8359 | 6.5897 | 4.6718 | 12.0033 | 13.9213 | 20.511 | 25.1828 | 4.3589 | 7.6544 | 1.9453 | 1.9179 | 2.7265 | 2.8359 | 6.5897 | 4.6718 | 12.0133 | 13.9313 | 20.521 | 25.1928 | 0.01
0.47148 | 6.8022 | 1.8157 | 1.7236 | 2.0786 | 2.4471 | 5.6179 | 3.8943 | 7.2736 | 8.9972 | 14.6151 | 18.5094 | 0.47148 | 6.8122 | 1.8157 | 1.7236 | 2.0786 | 2.4471 | 5.6179 | 3.8943 | 7.2836 | 9.0072 | 14.6251 | 18.5194 | 0.01
7.8912 | 8.4097 | 2.063 | 2.0946 | 3.3152 | 3.1891 | 7.4728 | 5.3782 | 16.3009 | 18.3955 | 25.8682 | 31.2465 | 7.8912 | 8.4197 | 2.063 | 2.0946 | 3.3152 | 3.1891 | 7.4728 | 5.3782 | 16.3109 | 18.4055 | 25.8782 | 31.2565 | 0.01
4.3809 | 7.6492 | 1.946 | 1.919 | 2.7301 | 2.8381 | 6.5952 | 4.6762 | 12.0301 | 13.9491 | 20.5444 | 25.2205 | 4.3809 | 7.6592 | 1.946 | 1.919 | 2.7301 | 2.8381 | 6.5952 | 4.6762 | 12.0401 | 13.9591 | 20.5544 | 25.2305 | 0.01
12.5045 | 9.4093 | 2.2168 | 2.3252 | 4.0841 | 3.6505 | 8.6261 | 6.3009 | 21.9138 | 24.2391 | 32.8652 | 39.1661 | 12.5045 | 9.4193 | 2.2168 | 2.3252 | 4.0841 | 3.6505 | 8.6261 | 6.3009 | 21.9238 | 24.2491 | 32.8752 | 39.1761 | 0.01
-2.5623 | 6.1448 | 1.7146 | 1.5719 | 1.5729 | 2.1438 | 4.8594 | 3.2875 | 3.5825 | 5.1544 | 10.0138 | 13.3013 | -2.5623 | 6.1548 | 1.7146 | 1.5719 | 1.5729 | 2.1438 | 4.8594 | 3.2875 | 3.5925 | 5.1644 | 10.0238 | 13.3113 | 0.01
5.628 | 7.9194 | 1.9876 | 1.9814 | 2.938 | 2.9628 | 6.907 | 4.9256 | 13.5474 | 15.5288 | 22.4358 | 27.3614 | 5.628 | 7.9294 | 1.9876 | 1.9814 | 2.938 | 2.9628 | 6.907 | 4.9256 | 13.5574 | 15.5388 | 22.4458 | 27.3714 | 0.01
-2.8667 | 6.0789 | 1.7044 | 1.5567 | 1.5222 | 2.1133 | 4.7833 | 3.2267 | 3.2122 | 4.7689 | 9.5522 | 12.7789 | -2.8667 | 6.0889 | 1.7044 | 1.5567 | 1.5222 | 2.1133 | 4.7833 | 3.2267 | 3.2222 | 4.7789 | 9.5622 | 12.7889 | 0.01
-6.8201 | 5.2223 | 1.5727 | 1.359 | 0.86332 | 1.718 | 3.795 | 2.436 | -1.5977 | -0.23874 | 3.5562 | 5.9922 | -6.8201 | 5.2323 | 1.5727 | 1.359 | 0.86332 | 1.718 | 3.795 | 2.436 | -1.5877 | -0.22874 | 3.5662 | 6.0022 | 0.01
-0.06598 | 6.6857 | 1.7978 | 1.6967 | 1.989 | 2.3934 | 5.4835 | 3.7868 | 6.6197 | 8.3164 | 13.7999 | 17.5867 | -0.06598 | 6.6957 | 1.7978 | 1.6967 | 1.989 | 2.3934 | 5.4835 | 3.7868 | 6.6297 | 8.3264 | 13.8099 | 17.5967 | 0.01
-4.274 | 5.774 | 1.6575 | 1.4863 | 1.2877 | 1.9726 | 4.4315 | 2.9452 | 1.4999 | 2.9862 | 7.4177 | 10.3629 | -4.274 | 5.784 | 1.6575 | 1.4863 | 1.2877 | 1.9726 | 4.4315 | 2.9452 | 1.5099 | 2.9962 | 7.4277 | 10.3729 | 0.01
9.4 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.85 | 5.68 | 18.1367 | 20.3067 | 28.1567 | 33.8367 | 9.4 | 8.7467 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.85 | 5.68 | 18.1467 | 20.3167 | 28.1667 | 33.8467 | 0.01
-0.6032 | 6.5693 | 1.7799 | 1.6698 | 1.8995 | 2.3397 | 5.3492 | 3.6794 | 5.9661 | 7.6359 | 12.9851 | 16.6645 | -0.6032 | 6.5793 | 1.7799 | 1.6698 | 1.8995 | 2.3397 | 5.3492 | 3.6794 | 5.9761 | 7.6459 | 12.9951 | 16.6745 | 0.01
0.58262 | 6.8262 | 1.8194 | 1.7291 | 2.0971 | 2.4583 | 5.6457 | 3.9165 | 7.4089 | 9.138 | 14.7836 | 18.7002 | 0.58262 | 6.8362 | 1.8194 | 1.7291 | 2.0971 | 2.4583 | 5.6457 | 3.9165 | 7.4189 | 9.148 | 14.7936 | 18.7102 | 0.01
6.9663 | 8.2094 | 2.0322 | 2.0483 | 3.161 | 3.0966 | 7.2416 | 5.1933 | 15.1756 | 17.2239 | 24.4655 | 29.6587 | 6.9663 | 8.2194 | 2.0322 | 2.0483 | 3.161 | 3.0966 | 7.2416 | 5.1933 | 15.1856 | 17.2339 | 24.4755 | 29.6687 | 0.01
8.3163 | 8.5019 | 2.0772 | 2.1158 | 3.386 | 3.2316 | 7.5791 | 5.4633 | 16.8181 | 18.9339 | 26.513 | 31.9762 | 8.3163 | 8.5119 | 2.0772 | 2.1158 | 3.386 | 3.2316 | 7.5791 | 5.4633 | 16.8281 | 18.9439 | 26.523 | 31.9862 | 0.01
-4.5469 | 5.7148 | 1.6484 | 1.4727 | 1.2422 | 1.9453 | 4.3633 | 2.8906 | 1.1679 | 2.6406 | 7.0038 | 9.8944 | -4.5469 | 5.7248 | 1.6484 | 1.4727 | 1.2422 | 1.9453 | 4.3633 | 2.8906 | 1.1779 | 2.6506 | 7.0138 | 9.9044 | 0.01
-7.9943 | 4.9679 | 1.5335 | 1.3003 | 0.66762 | 1.6006 | 3.5014 | 2.2011 | -3.0264 | -1.7261 | 1.7753 | 3.9765 | -7.9943 | 4.9779 | 1.5335 | 1.3003 | 0.66762 | 1.6006 | 3.5014 | 2.2011 | -3.0164 | -1.7161 | 1.7853 | 3.9865 | 0.01
4.1948 | 7.6089 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5487 | 4.639 | 11.8036 | 13.7134 | 20.2621 | 24.901 | 4.1948 | 7.6189 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5487 | 4.639 | 11.8136 | 13.7234 | 20.2721 | 24.911 | 0.01
0.29908 | 6.7648 | 1.81 | 1.715 | 2.0498 | 2.4299 | 5.5748 | 3.8598 | 7.0639 | 8.7788 | 14.3536 | 18.2134 | 0.29908 | 6.7748 | 1.81 | 1.715 | 2.0498 | 2.4299 | 5.5748 | 3.8598 | 7.0739 | 8.7888 | 14.3636 | 18.2234 | 0.01
2.5167 | 7.2453 | 1.8839 | 1.8258 | 2.4194 | 2.6517 | 6.1292 | 4.3033 | 9.762 | 11.5878 | 17.717 | 22.0203 | 2.5167 | 7.2553 | 1.8839 | 1.8258 | 2.4194 | 2.6517 | 6.1292 | 4.3033 | 9.772 | 11.5978 | 17.727 | 22.0303 | 0.01
14.5896 | 9.8611 | 2.2863 | 2.4295 | 4.4316 | 3.859 | 9.1474 | 6.7179 | 24.4507 | 26.8802 | 36.0276 | 42.7455 | 14.5896 | 9.8711 | 2.2863 | 2.4295 | 4.4316 | 3.859 | 9.1474 | 6.7179 | 24.4607 | 26.8902 | 36.0376 | 42.7555 | 0.01
5.9257 | 7.9839 | 1.9975 | 1.9963 | 2.9876 | 2.9926 | 6.9814 | 4.9851 | 13.9095 | 15.9058 | 22.8872 | 27.8724 | 5.9257 | 7.9939 | 1.9975 | 1.9963 | 2.9876 | 2.9926 | 6.9814 | 4.9851 | 13.9195 | 15.9158 | 22.8972 | 27.8824 | 0.01
4.8036 | 7.7408 | 1.9601 | 1.9402 | 2.8006 | 2.8804 | 6.7009 | 4.7607 | 12.5443 | 14.4845 | 21.1854 | 25.9461 | 4.8036 | 7.7508 | 1.9601 | 1.9402 | 2.8006 | 2.8804 | 6.7009 | 4.7607 | 12.5543 | 14.4945 | 21.1954 | 25.9561 | 0.01
2.8171 | 7.3104 | 1.8939 | 1.8409 | 2.4695 | 2.6817 | 6.2043 | 4.3634 | 10.1275 | 11.9683 | 18.1726 | 22.536 | 2.8171 | 7.3204 | 1.8939 | 1.8409 | 2.4695 | 2.6817 | 6.2043 | 4.3634 | 10.1375 | 11.9783 | 18.1826 | 22.546 | 0.01
7.7332 | 8.3755 | 2.0578 | 2.0867 | 3.2889 | 3.1733 | 7.4333 | 5.3466 | 16.1088 | 18.1954 | 25.6287 | 30.9754 | 7.7332 | 8.3855 | 2.0578 | 2.0867 | 3.2889 | 3.1733 | 7.4333 | 5.3466 | 16.1188 | 18.2054 | 25.6387 | 30.9854 | 0.01
10.7305 | 9.0249 | 2.1577 | 2.2365 | 3.7884 | 3.473 | 8.1826 | 5.9461 | 19.7554 | 21.9919 | 30.1745 | 36.1206 | 10.7305 | 9.0349 | 2.1577 | 2.2365 | 3.7884 | 3.473 | 8.1826 | 5.9461 | 19.7654 | 22.0019 | 30.1845 | 36.1306 | 0.01
8.4966 | 8.5409 | 2.0832 | 2.1248 | 3.4161 | 3.2497 | 7.6242 | 5.4993 | 17.0375 | 19.1624 | 26.7865 | 32.2858 | 8.4966 | 8.5509 | 2.0832 | 2.1248 | 3.4161 | 3.2497 | 7.6242 | 5.4993 | 17.0475 | 19.1724 | 26.7965 | 32.2958 | 0.01
-8.2772 | 4.9066 | 1.5241 | 1.2861 | 0.62047 | 1.5723 | 3.4307 | 2.1446 | -3.3706 | -2.0844 | 1.3463 | 3.4908 | -8.2772 | 4.9166 | 1.5241 | 1.2861 | 0.62047 | 1.5723 | 3.4307 | 2.1446 | -3.3606 | -2.0744 | 1.3563 | 3.5008 | 0.01
8.6945 | 8.5838 | 2.0898 | 2.1347 | 3.4491 | 3.2695 | 7.6736 | 5.5389 | 17.2783 | 19.413 | 27.0867 | 32.6256 | 8.6945 | 8.5938 | 2.0898 | 2.1347 | 3.4491 | 3.2695 | 7.6736 | 5.5389 | 17.2883 | 19.423 | 27.0967 | 32.6356 | 0.01
4.4416 | 7.6624 | 1.9481 | 1.9221 | 2.7403 | 2.8442 | 6.6104 | 4.6883 | 12.104 | 14.0261 | 20.6365 | 25.3248 | 4.4416 | 7.6724 | 1.9481 | 1.9221 | 2.7403 | 2.8442 | 6.6104 | 4.6883 | 12.114 | 14.0361 | 20.6465 | 25.3348 | 0.01
4.5166 | 7.6786 | 1.9506 | 1.9258 | 2.7528 | 2.8517 | 6.6292 | 4.7033 | 12.1953 | 14.1211 | 20.7502 | 25.4536 | 4.5166 | 7.6886 | 1.9506 | 1.9258 | 2.7528 | 2.8517 | 6.6292 | 4.7033 | 12.2053 | 14.1311 | 20.7602 | 25.4636 | 0.01
7.1372 | 8.2464 | 2.0379 | 2.0569 | 3.1895 | 3.1137 | 7.2843 | 5.2274 | 15.3835 | 17.4404 | 24.7247 | 29.9521 | 7.1372 | 8.2564 | 2.0379 | 2.0569 | 3.1895 | 3.1137 | 7.2843 | 5.2274 | 15.3935 | 17.4504 | 24.7347 | 29.9621 | 0.01
9.3226 | 8.7199 | 2.1108 | 2.1661 | 3.5538 | 3.3323 | 7.8307 | 5.6645 | 18.0425 | 20.2087 | 28.0393 | 33.7039 | 9.3226 | 8.7299 | 2.1108 | 2.1661 | 3.5538 | 3.3323 | 7.8307 | 5.6645 | 18.0525 | 20.2187 | 28.0493 | 33.7139 | 0.01
1.1275 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7819 | 4.0255 | 8.0717 | 9.8281 | 15.61 | 19.6355 | 1.1275 | 6.9543 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7819 | 4.0255 | 8.0817 | 9.8381 | 15.62 | 19.6455 | 0.01
-2.6418 | 6.1276 | 1.7119 | 1.5679 | 1.5597 | 2.1358 | 4.8395 | 3.2716 | 3.4858 | 5.0537 | 9.8932 | 13.1649 | -2.6418 | 6.1376 | 1.7119 | 1.5679 | 1.5597 | 2.1358 | 4.8395 | 3.2716 | 3.4958 | 5.0637 | 9.9032 | 13.1749 | 0.01
9.0604 | 8.6631 | 2.102 | 2.153 | 3.5101 | 3.306 | 7.7651 | 5.6121 | 17.7234 | 19.8765 | 27.6415 | 33.2536 | 9.0604 | 8.6731 | 2.102 | 2.153 | 3.5101 | 3.306 | 7.7651 | 5.6121 | 17.7334 | 19.8865 | 27.6515 | 33.2636 | 0.01
10.6866 | 9.0154 | 2.1562 | 2.2343 | 3.7811 | 3.4687 | 8.1717 | 5.9373 | 19.7021 | 21.9364 | 30.1081 | 36.0454 | 10.6866 | 9.0254 | 2.1562 | 2.2343 | 3.7811 | 3.4687 | 8.1717 | 5.9373 | 19.7121 | 21.9464 | 30.1181 | 36.0554 | 0.01
8.5379 | 8.5499 | 2.0846 | 2.1269 | 3.423 | 3.2538 | 7.6345 | 5.5076 | 17.0878 | 19.2146 | 26.8491 | 32.3567 | 8.5379 | 8.5599 | 2.0846 | 2.1269 | 3.423 | 3.2538 | 7.6345 | 5.5076 | 17.0978 | 19.2246 | 26.8591 | 32.3667 | 0.01
1.8028 | 7.0906 | 1.8601 | 1.7901 | 2.3005 | 2.5803 | 5.9507 | 4.1606 | 8.8935 | 10.6836 | 16.6343 | 20.7949 | 1.8028 | 7.1006 | 1.8601 | 1.7901 | 2.3005 | 2.5803 | 5.9507 | 4.1606 | 8.9035 | 10.6936 | 16.6443 | 20.8049 | 0.01
0.2989 | 6.7648 | 1.81 | 1.7149 | 2.0498 | 2.4299 | 5.5747 | 3.8598 | 7.0637 | 8.7786 | 14.3533 | 18.2131 | 0.2989 | 6.7748 | 1.81 | 1.7149 | 2.0498 | 2.4299 | 5.5747 | 3.8598 | 7.0737 | 8.7886 | 14.3633 | 18.2231 | 0.01
-0.13421 | 6.6709 | 1.7955 | 1.6933 | 1.9776 | 2.3866 | 5.4664 | 3.7732 | 6.5367 | 8.23 | 13.6965 | 17.4696 | -0.13421 | 6.6809 | 1.7955 | 1.6933 | 1.9776 | 2.3866 | 5.4664 | 3.7732 | 6.5467 | 8.24 | 13.7065 | 17.4796 | 0.01
7.0264 | 8.2224 | 2.0342 | 2.0513 | 3.1711 | 3.1026 | 7.2566 | 5.2053 | 15.2488 | 17.3001 | 24.5567 | 29.762 | 7.0264 | 8.2324 | 2.0342 | 2.0513 | 3.1711 | 3.1026 | 7.2566 | 5.2053 | 15.2588 | 17.3101 | 24.5667 | 29.772 | 0.01
15.9381 | 10.1533 | 2.3313 | 2.4969 | 4.6563 | 3.9938 | 9.4845 | 6.9876 | 26.0913 | 28.5883 | 38.0728 | 45.0604 | 15.9381 | 10.1633 | 2.3313 | 2.4969 | 4.6563 | 3.9938 | 9.4845 | 6.9876 | 26.1013 | 28.5983 | 38.0828 | 45.0704 | 0.01
4.2657 | 7.6242 | 1.9422 | 1.9133 | 2.711 | 2.8266 | 6.5664 | 4.6531 | 11.89 | 13.8033 | 20.3697 | 25.0229 | 4.2657 | 7.6342 | 1.9422 | 1.9133 | 2.711 | 2.8266 | 6.5664 | 4.6531 | 11.9 | 13.8133 | 20.3797 | 25.0329 | 0.01
-1.1135 | 6.4587 | 1.7629 | 1.6443 | 1.8144 | 2.2886 | 5.2216 | 3.5773 | 5.3452 | 6.9896 | 12.2112 | 15.7885 | -1.1135 | 6.4687 | 1.7629 | 1.6443 | 1.8144 | 2.2886 | 5.2216 | 3.5773 | 5.3552 | 6.9996 | 12.2212 | 15.7985 | 0.01
4.8713 | 7.7554 | 1.9624 | 1.9436 | 2.8119 | 2.8871 | 6.7178 | 4.7743 | 12.6267 | 14.5703 | 21.2881 | 26.0624 | 4.8713 | 7.7654 | 1.9624 | 1.9436 | 2.8119 | 2.8871 | 6.7178 | 4.7743 | 12.6367 | 14.5803 | 21.2981 | 26.0724 | 0.01
7.0446 | 8.2263 | 2.0348 | 2.0522 | 3.1741 | 3.1045 | 7.2612 | 5.2089 | 15.2709 | 17.3232 | 24.5843 | 29.7933 | 7.0446 | 8.2363 | 2.0348 | 2.0522 | 3.1741 | 3.1045 | 7.2612 | 5.2089 | 15.2809 | 17.3332 | 24.5943 | 29.8033 | 0.01
20.3696 | 11.1134 | 2.479 | 2.7185 | 5.3949 | 4.437 | 10.5924 | 7.8739 | 31.483 | 34.2015 | 44.7939 | 52.6678 | 20.3696 | 11.1234 | 2.479 | 2.7185 | 5.3949 | 4.437 | 10.5924 | 7.8739 | 31.493 | 34.2115 | 44.8039 | 52.6778 | 0.01
2.9926 | 7.3484 | 1.8998 | 1.8496 | 2.4988 | 2.6993 | 6.2482 | 4.3985 | 10.341 | 12.1907 | 18.4388 | 22.8374 | 2.9926 | 7.3584 | 1.8998 | 1.8496 | 2.4988 | 2.6993 | 6.2482 | 4.3985 | 10.351 | 12.2007 | 18.4488 | 22.8474 | 0.01
3.3625 | 7.4285 | 1.9121 | 1.8681 | 2.5604 | 2.7362 | 6.3406 | 4.4725 | 10.791 | 12.6591 | 18.9998 | 23.4723 | 3.3625 | 7.4385 | 1.9121 | 1.8681 | 2.5604 | 2.7362 | 6.3406 | 4.4725 | 10.801 | 12.6691 | 19.0098 | 23.4823 | 0.01
2.8398 | 7.3153 | 1.8947 | 1.842 | 2.4733 | 2.684 | 6.21 | 4.368 | 10.1551 | 11.9971 | 18.207 | 22.575 | 2.8398 | 7.3253 | 1.8947 | 1.842 | 2.4733 | 2.684 | 6.21 | 4.368 | 10.1651 | 12.0071 | 18.217 | 22.585 | 0.01
8.605 | 8.5644 | 2.0868 | 2.1302 | 3.4342 | 3.2605 | 7.6512 | 5.521 | 17.1694 | 19.2996 | 26.9509 | 32.4719 | 8.605 | 8.5744 | 2.0868 | 2.1302 | 3.4342 | 3.2605 | 7.6512 | 5.521 | 17.1794 | 19.3096 | 26.9609 | 32.4819 | 0.01
8.192 | 8.4749 | 2.0731 | 2.1096 | 3.3653 | 3.2192 | 7.548 | 5.4384 | 16.6669 | 18.7765 | 26.3245 | 31.7629 | 8.192 | 8.4849 | 2.0731 | 2.1096 | 3.3653 | 3.2192 | 7.548 | 5.4384 | 16.6769 | 18.7865 | 26.3345 | 31.7729 | 0.01
8.0575 | 8.4458 | 2.0686 | 2.1029 | 3.3429 | 3.2057 | 7.5144 | 5.4115 | 16.5033 | 18.6062 | 26.1205 | 31.532 | 8.0575 | 8.4558 | 2.0686 | 2.1029 | 3.3429 | 3.2057 | 7.5144 | 5.4115 | 16.5133 | 18.6162 | 26.1305 | 31.542 | 0.01
5.6798 | 7.9306 | 1.9893 | 1.984 | 2.9466 | 2.968 | 6.92 | 4.936 | 13.6104 | 15.5944 | 22.5144 | 27.4503 | 5.6798 | 7.9406 | 1.9893 | 1.984 | 2.9466 | 2.968 | 6.92 | 4.936 | 13.6204 | 15.6044 | 22.5244 | 27.4603 | 0.01
12.1633 | 9.3354 | 2.2054 | 2.3082 | 4.0272 | 3.6163 | 8.5408 | 6.2327 | 21.4987 | 23.8069 | 32.3477 | 38.5804 | 12.1633 | 9.3454 | 2.2054 | 2.3082 | 4.0272 | 3.6163 | 8.5408 | 6.2327 | 21.5087 | 23.8169 | 32.3577 | 38.5904 | 0.01
8.89 | 8.6262 | 2.0963 | 2.1445 | 3.4817 | 3.289 | 7.7225 | 5.578 | 17.5161 | 19.6606 | 27.3831 | 32.9611 | 8.89 | 8.6362 | 2.0963 | 2.1445 | 3.4817 | 3.289 | 7.7225 | 5.578 | 17.5261 | 19.6706 | 27.3931 | 32.9711 | 0.01
4.5152 | 7.6783 | 1.9505 | 1.9258 | 2.7525 | 2.8515 | 6.6288 | 4.703 | 12.1935 | 14.1192 | 20.748 | 25.451 | 4.5152 | 7.6883 | 1.9505 | 1.9258 | 2.7525 | 2.8515 | 6.6288 | 4.703 | 12.2035 | 14.1292 | 20.758 | 25.461 | 0.01
17.5746 | 10.5078 | 2.3858 | 2.5787 | 4.9291 | 4.1575 | 9.8937 | 7.3149 | 28.0824 | 30.6612 | 40.5548 | 47.8697 | 17.5746 | 10.5178 | 2.3858 | 2.5787 | 4.9291 | 4.1575 | 9.8937 | 7.3149 | 28.0924 | 30.6712 | 40.5648 | 47.8797 | 0.01
7.2511 | 8.2711 | 2.0417 | 2.0626 | 3.2085 | 3.1251 | 7.3128 | 5.2502 | 15.5222 | 17.5848 | 24.8976 | 30.1478 | 7.2511 | 8.2811 | 2.0417 | 2.0626 | 3.2085 | 3.1251 | 7.3128 | 5.2502 | 15.5322 | 17.5948 | 24.9076 | 30.1578 | 0.01
7.1645 | 8.2523 | 2.0388 | 2.0582 | 3.1941 | 3.1164 | 7.2911 | 5.2329 | 15.4168 | 17.475 | 24.7661 | 29.999 | 7.1645 | 8.2623 | 2.0388 | 2.0582 | 3.1941 | 3.1164 | 7.2911 | 5.2329 | 15.4268 | 17.485 | 24.7761 | 30.009 | 0.01
8.9096 | 8.6304 | 2.097 | 2.1455 | 3.4849 | 3.291 | 7.7274 | 5.5819 | 17.54 | 19.6855 | 27.4129 | 32.9948 | 8.9096 | 8.6404 | 2.097 | 2.1455 | 3.4849 | 3.291 | 7.7274 | 5.5819 | 17.55 | 19.6955 | 27.4229 | 33.0048 | 0.01
13.8753 | 9.7063 | 2.2625 | 2.3938 | 4.3126 | 3.7875 | 8.9688 | 6.5751 | 23.5816 | 25.9754 | 34.9442 | 41.5193 | 13.8753 | 9.7163 | 2.2625 | 2.3938 | 4.3126 | 3.7875 | 8.9688 | 6.5751 | 23.5916 | 25.9854 | 34.9542 | 41.5293 | 0.01
14.9444 | 9.938 | 2.2981 | 2.4472 | 4.4907 | 3.8944 | 9.2361 | 6.7889 | 24.8824 | 27.3296 | 36.5657 | 43.3546 | 14.9444 | 9.948 | 2.2981 | 2.4472 | 4.4907 | 3.8944 | 9.2361 | 6.7889 | 24.8924 | 27.3396 | 36.5757 | 43.3646 | 0.01
12.6497 | 9.4408 | 2.2217 | 2.3325 | 4.1083 | 3.665 | 8.6624 | 6.3299 | 22.0904 | 24.4229 | 33.0853 | 39.4153 | 12.6497 | 9.4508 | 2.2217 | 2.3325 | 4.1083 | 3.665 | 8.6624 | 6.3299 | 22.1004 | 24.4329 | 33.0953 | 39.4253 | 0.01
-5.3839 | 5.5335 | 1.6205 | 1.4308 | 1.1027 | 1.8616 | 4.154 | 2.7232 | 0.14953 | 1.5803 | 5.7343 | 8.4576 | -5.3839 | 5.5435 | 1.6205 | 1.4308 | 1.1027 | 1.8616 | 4.154 | 2.7232 | 0.15953 | 1.5903 | 5.7443 | 8.4676 | 0.01
7.415 | 8.3066 | 2.0472 | 2.0707 | 3.2358 | 3.1415 | 7.3537 | 5.283 | 15.7215 | 17.7923 | 25.146 | 30.429 | 7.415 | 8.3166 | 2.0472 | 2.0707 | 3.2358 | 3.1415 | 7.3537 | 5.283 | 15.7315 | 17.8023 | 25.156 | 30.439 | 0.01
0.75401 | 6.8634 | 1.8251 | 1.7377 | 2.1257 | 2.4754 | 5.6885 | 3.9508 | 7.6174 | 9.3551 | 15.0436 | 18.9944 | 0.75401 | 6.8734 | 1.8251 | 1.7377 | 2.1257 | 2.4754 | 5.6885 | 3.9508 | 7.6274 | 9.3651 | 15.0536 | 19.0044 | 0.01
7.6785 | 8.3637 | 2.0559 | 2.0839 | 3.2797 | 3.1678 | 7.4196 | 5.3357 | 16.0421 | 18.1261 | 25.5457 | 30.8814 | 7.6785 | 8.3737 | 2.0559 | 2.0839 | 3.2797 | 3.1678 | 7.4196 | 5.3357 | 16.0521 | 18.1361 | 25.5557 | 30.8914 | 0.01
-6.7356 | 5.2406 | 1.5755 | 1.3632 | 0.8774 | 1.7264 | 3.8161 | 2.4529 | -1.495 | -0.13174 | 3.6844 | 6.1373 | -6.7356 | 5.2506 | 1.5755 | 1.3632 | 0.8774 | 1.7264 | 3.8161 | 2.4529 | -1.485 | -0.12174 | 3.6944 | 6.1473 | 0.01
15.0729 | 9.9658 | 2.3024 | 2.4536 | 4.5121 | 3.9073 | 9.2682 | 6.8146 | 25.0387 | 27.4923 | 36.7606 | 43.5751 | 15.0729 | 9.9758 | 2.3024 | 2.4536 | 4.5121 | 3.9073 | 9.2682 | 6.8146 | 25.0487 | 27.5023 | 36.7706 | 43.5851 | 0.01
4.1628 | 7.6019 | 1.9388 | 1.9081 | 2.6938 | 2.8163 | 6.5407 | 4.6326 | 11.7648 | 13.6729 | 20.2136 | 24.8462 | 4.1628 | 7.6119 | 1.9388 | 1.9081 | 2.6938 | 2.8163 | 6.5407 | 4.6326 | 11.7748 | 13.6829 | 20.2236 | 24.8562 | 0.01
-1.8279 | 6.304 | 1.7391 | 1.6086 | 1.6954 | 2.2172 | 5.043 | 3.4344 | 4.4761 | 6.0847 | 11.1277 | 14.5622 | -1.8279 | 6.314 | 1.7391 | 1.6086 | 1.6954 | 2.2172 | 5.043 | 3.4344 | 4.4861 | 6.0947 | 11.1377 | 14.5722 | 0.01
7.3349 | 8.2892 | 2.0445 | 2.0667 | 3.2225 | 3.1335 | 7.3337 | 5.267 | 15.6242 | 17.6909 | 25.0246 | 30.2916 | 7.3349 | 8.2992 | 2.0445 | 2.0667 | 3.2225 | 3.1335 | 7.3337 | 5.267 | 15.6342 | 17.7009 | 25.0346 | 30.3016 | 0.01
-2.9217 | 6.067 | 1.7026 | 1.5539 | 1.5131 | 2.1078 | 4.7696 | 3.2157 | 3.1453 | 4.6992 | 9.4688 | 12.6845 | -2.9217 | 6.077 | 1.7026 | 1.5539 | 1.5131 | 2.1078 | 4.7696 | 3.2157 | 3.1553 | 4.7092 | 9.4788 | 12.6945 | 0.01
6.4196 | 8.0909 | 2.014 | 2.021 | 3.0699 | 3.042 | 7.1049 | 5.0839 | 14.5106 | 16.5315 | 23.6364 | 28.7204 | 6.4196 | 8.1009 | 2.014 | 2.021 | 3.0699 | 3.042 | 7.1049 | 5.0839 | 14.5206 | 16.5415 | 23.6464 | 28.7304 | 0.01
-3.1568 | 6.016 | 1.6948 | 1.5422 | 1.4739 | 2.0843 | 4.7108 | 3.1686 | 2.8592 | 4.4013 | 9.1121 | 12.2807 | -3.1568 | 6.026 | 1.6948 | 1.5422 | 1.4739 | 2.0843 | 4.7108 | 3.1686 | 2.8692 | 4.4113 | 9.1221 | 12.2907 | 0.01
-5.5235 | 5.5032 | 1.6159 | 1.4238 | 1.0794 | 1.8476 | 4.1191 | 2.6953 | -0.0203 | 1.4035 | 5.5226 | 8.2179 | -5.5235 | 5.5132 | 1.6159 | 1.4238 | 1.0794 | 1.8476 | 4.1191 | 2.6953 | -0.0103 | 1.4135 | 5.5326 | 8.2279 | 0.01
4.1099 | 7.5905 | 1.937 | 1.9055 | 2.685 | 2.811 | 6.5275 | 4.622 | 11.7004 | 13.6058 | 20.1333 | 24.7553 | 4.1099 | 7.6005 | 1.937 | 1.9055 | 2.685 | 2.811 | 6.5275 | 4.622 | 11.7104 | 13.6158 | 20.1433 | 24.7653 | 0.01
9.1846 | 8.69 | 2.1062 | 2.1592 | 3.5308 | 3.3185 | 7.7962 | 5.6369 | 17.8746 | 20.0339 | 27.83 | 33.4669 | 9.1846 | 8.7 | 2.1062 | 2.1592 | 3.5308 | 3.3185 | 7.7962 | 5.6369 | 17.8846 | 20.0439 | 27.84 | 33.4769 | 0.01
-3.3156 | 5.9816 | 1.6895 | 1.5342 | 1.4474 | 2.0684 | 4.6711 | 3.1369 | 2.666 | 4.2003 | 8.8714 | 12.0082 | -3.3156 | 5.9916 | 1.6895 | 1.5342 | 1.4474 | 2.0684 | 4.6711 | 3.1369 | 2.676 | 4.2103 | 8.8814 | 12.0182 | 0.01
10.6419 | 9.0057 | 2.1547 | 2.2321 | 3.7737 | 3.4642 | 8.1605 | 5.9284 | 19.6477 | 21.8798 | 30.0402 | 35.9686 | 10.6419 | 9.0157 | 2.1547 | 2.2321 | 3.7737 | 3.4642 | 8.1605 | 5.9284 | 19.6577 | 21.8898 | 30.0502 | 35.9786 | 0.01
9.4293 | 8.743 | 2.1143 | 2.1715 | 3.5716 | 3.3429 | 7.8573 | 5.6859 | 18.1724 | 20.3438 | 28.2012 | 33.8871 | 9.4293 | 8.753 | 2.1143 | 2.1715 | 3.5716 | 3.3429 | 7.8573 | 5.6859 | 18.1824 | 20.3538 | 28.2112 | 33.8971 | 0.01
24.2891 | 11.9626 | 2.6096 | 2.9145 | 6.0482 | 4.8289 | 11.5723 | 8.6578 | 36.2518 | 39.1662 | 50.7385 | 59.3964 | 24.2891 | 11.9726 | 2.6096 | 2.9145 | 6.0482 | 4.8289 | 11.5723 | 8.6578 | 36.2618 | 39.1762 | 50.7485 | 59.4064 | 0.01
8.2951 | 8.4973 | 2.0765 | 2.1148 | 3.3825 | 3.2295 | 7.5738 | 5.459 | 16.7923 | 18.9071 | 26.4808 | 31.9398 | 8.2951 | 8.5073 | 2.0765 | 2.1148 | 3.3825 | 3.2295 | 7.5738 | 5.459 | 16.8023 | 18.9171 | 26.4908 | 31.9498 | 0.01
-5.1847 | 5.5767 | 1.6272 | 1.4408 | 1.1359 | 1.8815 | 4.2038 | 2.7631 | 0.392 | 1.8328 | 6.0366 | 8.7997 | -5.1847 | 5.5867 | 1.6272 | 1.4408 | 1.1359 | 1.8815 | 4.2038 | 2.7631 | 0.402 | 1.8428 | 6.0466 | 8.8097 | 0.01
7.4308 | 8.31 | 2.0477 | 2.0715 | 3.2385 | 3.1431 | 7.3577 | 5.2862 | 15.7408 | 17.8123 | 25.17 | 30.4562 | 7.4308 | 8.32 | 2.0477 | 2.0715 | 3.2385 | 3.1431 | 7.3577 | 5.2862 | 15.7508 | 17.8223 | 25.18 | 30.4662 | 0.01
3.9805 | 7.5624 | 1.9327 | 1.899 | 2.6634 | 2.798 | 6.4951 | 4.5961 | 11.5429 | 13.4419 | 19.937 | 24.5331 | 3.9805 | 7.5724 | 1.9327 | 1.899 | 2.6634 | 2.798 | 6.4951 | 4.5961 | 11.5529 | 13.4519 | 19.947 | 24.5431 | 0.01
6.9627 | 8.2086 | 2.0321 | 2.0481 | 3.1605 | 3.0963 | 7.2407 | 5.1925 | 15.1713 | 17.2195 | 24.4602 | 29.6527 | 6.9627 | 8.2186 | 2.0321 | 2.0481 | 3.1605 | 3.0963 | 7.2407 | 5.1925 | 15.1813 | 17.2295 | 24.4702 | 29.6627 | 0.01
10.5847 | 8.9933 | 2.1528 | 2.2292 | 3.7641 | 3.4585 | 8.1462 | 5.9169 | 19.578 | 21.8073 | 29.9534 | 35.8704 | 10.5847 | 9.0033 | 2.1528 | 2.2292 | 3.7641 | 3.4585 | 8.1462 | 5.9169 | 19.588 | 21.8173 | 29.9634 | 35.8804 | 0.01
-1.1576 | 6.4492 | 1.7614 | 1.6421 | 1.8071 | 2.2842 | 5.2106 | 3.5685 | 5.2915 | 6.9337 | 12.1443 | 15.7127 | -1.1576 | 6.4592 | 1.7614 | 1.6421 | 1.8071 | 2.2842 | 5.2106 | 3.5685 | 5.3015 | 6.9437 | 12.1543 | 15.7227 | 0.01
-1.1256 | 6.4561 | 1.7625 | 1.6437 | 1.8124 | 2.2874 | 5.2186 | 3.5749 | 5.3305 | 6.9742 | 12.1928 | 15.7677 | -1.1256 | 6.4661 | 1.7625 | 1.6437 | 1.8124 | 2.2874 | 5.2186 | 3.5749 | 5.3405 | 6.9842 | 12.2028 | 15.7777 | 0.01
10.0004 | 8.8667 | 2.1333 | 2.2 | 3.6667 | 3.4 | 8.0001 | 5.8001 | 18.8671 | 21.0671 | 29.0672 | 34.8673 | 10.0004 | 8.8767 | 2.1333 | 2.2 | 3.6667 | 3.4 | 8.0001 | 5.8001 | 18.8771 | 21.0771 | 29.0772 | 34.8773 | 0.01
8.9462 | 8.6383 | 2.0982 | 2.1473 | 3.491 | 3.2946 | 7.7366 | 5.5892 | 17.5845 | 19.7319 | 27.4684 | 33.0576 | 8.9462 | 8.6483 | 2.0982 | 2.1473 | 3.491 | 3.2946 | 7.7366 | 5.5892 | 17.5945 | 19.7419 | 27.4784 | 33.0676 | 0.01
1.749 | 7.0789 | 1.8583 | 1.7874 | 2.2915 | 2.5749 | 5.9372 | 4.1498 | 8.8279 | 10.6153 | 16.5526 | 20.7024 | 1.749 | 7.0889 | 1.8583 | 1.7874 | 2.2915 | 2.5749 | 5.9372 | 4.1498 | 8.8379 | 10.6253 | 16.5626 | 20.7124 | 0.01
0.17321 | 6.7375 | 1.8058 | 1.7087 | 2.0289 | 2.4173 | 5.5433 | 3.8346 | 6.9107 | 8.6194 | 14.1627 | 17.9973 | 0.17321 | 6.7475 | 1.8058 | 1.7087 | 2.0289 | 2.4173 | 5.5433 | 3.8346 | 6.9207 | 8.6294 | 14.1727 | 18.0073 | 0.01
7.8213 | 8.3946 | 2.0607 | 2.0911 | 3.3035 | 3.1821 | 7.4553 | 5.3643 | 16.2159 | 18.3069 | 25.7622 | 31.1265 | 7.8213 | 8.4046 | 2.0607 | 2.0911 | 3.3035 | 3.1821 | 7.4553 | 5.3643 | 16.2259 | 18.3169 | 25.7722 | 31.1365 | 0.01
15.1106 | 9.974 | 2.3037 | 2.4555 | 4.5184 | 3.9111 | 9.2777 | 6.8221 | 25.0846 | 27.5401 | 36.8178 | 43.6399 | 15.1106 | 9.984 | 2.3037 | 2.4555 | 4.5184 | 3.9111 | 9.2777 | 6.8221 | 25.0946 | 27.5501 | 36.8278 | 43.6499 | 0.01
10.1426 | 8.8976 | 2.1381 | 2.2071 | 3.6904 | 3.4143 | 8.0357 | 5.8285 | 19.0402 | 21.2473 | 29.283 | 35.1115 | 10.1426 | 8.9076 | 2.1381 | 2.2071 | 3.6904 | 3.4143 | 8.0357 | 5.8285 | 19.0502 | 21.2573 | 29.293 | 35.1215 | 0.01
16.8847 | 10.3583 | 2.3628 | 2.5442 | 4.8141 | 4.0885 | 9.7212 | 7.1769 | 27.243 | 29.7873 | 39.5084 | 46.6854 | 16.8847 | 10.3683 | 2.3628 | 2.5442 | 4.8141 | 4.0885 | 9.7212 | 7.1769 | 27.253 | 29.7973 | 39.5184 | 46.6954 | 0.01
7.7903 | 8.3879 | 2.0597 | 2.0895 | 3.2984 | 3.179 | 7.4476 | 5.3581 | 16.1782 | 18.2677 | 25.7153 | 31.0734 | 7.7903 | 8.3979 | 2.0597 | 2.0895 | 3.2984 | 3.179 | 7.4476 | 5.3581 | 16.1882 | 18.2777 | 25.7253 | 31.0834 | 0.01
13.5503 | 9.6359 | 2.2517 | 2.3775 | 4.2584 | 3.755 | 8.8876 | 6.5101 | 23.1862 | 25.5637 | 34.4513 | 40.9613 | 13.5503 | 9.6459 | 2.2517 | 2.3775 | 4.2584 | 3.755 | 8.8876 | 6.5101 | 23.1962 | 25.5737 | 34.4613 | 40.9713 | 0.01
15.0013 | 9.9503 | 2.3 | 2.4501 | 4.5002 | 3.9001 | 9.2503 | 6.8003 | 24.9515 | 27.4016 | 36.6519 | 43.4522 | 15.0013 | 9.9603 | 2.3 | 2.4501 | 4.5002 | 3.9001 | 9.2503 | 6.8003 | 24.9615 | 27.4116 | 36.6619 | 43.4622 | 0.01
7.9384 | 8.42 | 2.0646 | 2.0969 | 3.3231 | 3.1938 | 7.4846 | 5.3877 | 16.3584 | 18.4553 | 25.9399 | 31.3276 | 7.9384 | 8.43 | 2.0646 | 2.0969 | 3.3231 | 3.1938 | 7.4846 | 5.3877 | 16.3684 | 18.4653 | 25.9499 | 31.3376 | 0.01
6.8871 | 8.1922 | 2.0296 | 2.0444 | 3.1479 | 3.0887 | 7.2218 | 5.1774 | 15.0793 | 17.1237 | 24.3455 | 29.5229 | 6.8871 | 8.2022 | 2.0296 | 2.0444 | 3.1479 | 3.0887 | 7.2218 | 5.1774 | 15.0893 | 17.1337 | 24.3555 | 29.5329 | 0.01
1.9661 | 7.126 | 1.8655 | 1.7983 | 2.3277 | 2.5966 | 5.9915 | 4.1932 | 9.0921 | 10.8904 | 16.8819 | 21.0751 | 1.9661 | 7.136 | 1.8655 | 1.7983 | 2.3277 | 2.5966 | 5.9915 | 4.1932 | 9.1021 | 10.9004 | 16.8919 | 21.0851 | 0.01
3.4524 | 7.448 | 1.9151 | 1.8726 | 2.5754 | 2.7452 | 6.3631 | 4.4905 | 10.9004 | 12.773 | 19.1361 | 23.6266 | 3.4524 | 7.458 | 1.9151 | 1.8726 | 2.5754 | 2.7452 | 6.3631 | 4.4905 | 10.9104 | 12.783 | 19.1461 | 23.6366 | 0.01
11.6679 | 9.228 | 2.1889 | 2.2834 | 3.9446 | 3.5668 | 8.417 | 6.1336 | 20.8959 | 23.1793 | 31.5963 | 37.7298 | 11.6679 | 9.238 | 2.1889 | 2.2834 | 3.9446 | 3.5668 | 8.417 | 6.1336 | 20.9059 | 23.1893 | 31.6063 | 37.7398 | 0.01
-0.70544 | 6.5472 | 1.7765 | 1.6647 | 1.8824 | 2.3295 | 5.3236 | 3.6589 | 5.8417 | 7.5064 | 12.8301 | 16.489 | -0.70544 | 6.5572 | 1.7765 | 1.6647 | 1.8824 | 2.3295 | 5.3236 | 3.6589 | 5.8517 | 7.5164 | 12.8401 | 16.499 | 0.01
4.6741 | 7.7127 | 1.9558 | 1.9337 | 2.779 | 2.8674 | 6.6685 | 4.7348 | 12.3868 | 14.3205 | 20.989 | 25.7238 | 4.6741 | 7.7227 | 1.9558 | 1.9337 | 2.779 | 2.8674 | 6.6685 | 4.7348 | 12.3968 | 14.3305 | 20.999 | 25.7338 | 0.01
10.26 | 8.923 | 2.142 | 2.213 | 3.71 | 3.426 | 8.065 | 5.852 | 19.183 | 21.396 | 29.461 | 35.313 | 10.26 | 8.933 | 2.142 | 2.213 | 3.71 | 3.426 | 8.065 | 5.852 | 19.193 | 21.406 | 29.471 | 35.323 | 0.01
7.416 | 8.3068 | 2.0472 | 2.0708 | 3.236 | 3.1416 | 7.354 | 5.2832 | 15.7228 | 17.7936 | 25.1476 | 30.4308 | 7.416 | 8.3168 | 2.0472 | 2.0708 | 3.236 | 3.1416 | 7.354 | 5.2832 | 15.7328 | 17.8036 | 25.1576 | 30.4408 | 0.01
2.6131 | 7.2662 | 1.8871 | 1.8307 | 2.4355 | 2.6613 | 6.1533 | 4.3226 | 9.8793 | 11.71 | 17.8633 | 22.1859 | 2.6131 | 7.2762 | 1.8871 | 1.8307 | 2.4355 | 2.6613 | 6.1533 | 4.3226 | 9.8893 | 11.72 | 17.8733 | 22.1959 | 0.01
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2044 | 14.1306 | 20.7616 | 25.4664 | 4.5241 | 7.6902 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2144 | 14.1406 | 20.7716 | 25.4764 | 0.01
9.0177 | 8.6538 | 2.1006 | 2.1509 | 3.5029 | 3.3018 | 7.7544 | 5.6035 | 17.6715 | 19.8224 | 27.5768 | 33.1803 | 9.0177 | 8.6638 | 2.1006 | 2.1509 | 3.5029 | 3.3018 | 7.7544 | 5.6035 | 17.6815 | 19.8324 | 27.5868 | 33.1903 | 0.01
11.271 | 9.1421 | 2.1757 | 2.2636 | 3.8785 | 3.5271 | 8.3178 | 6.0542 | 20.4131 | 22.6766 | 30.9944 | 37.0486 | 11.271 | 9.1521 | 2.1757 | 2.2636 | 3.8785 | 3.5271 | 8.3178 | 6.0542 | 20.4231 | 22.6866 | 31.0044 | 37.0586 | 0.01
4.8689 | 7.7549 | 1.9623 | 1.9434 | 2.8115 | 2.8869 | 6.7172 | 4.7738 | 12.6238 | 14.5672 | 21.2844 | 26.0582 | 4.8689 | 7.7649 | 1.9623 | 1.9434 | 2.8115 | 2.8869 | 6.7172 | 4.7738 | 12.6338 | 14.5772 | 21.2944 | 26.0682 | 0.01
13.7381 | 9.6766 | 2.2579 | 2.3869 | 4.2897 | 3.7738 | 8.9345 | 6.5476 | 23.4147 | 25.8016 | 34.7361 | 41.2837 | 13.7381 | 9.6866 | 2.2579 | 2.3869 | 4.2897 | 3.7738 | 8.9345 | 6.5476 | 23.4247 | 25.8116 | 34.7461 | 41.2937 | 0.01
-0.14801 | 6.6679 | 1.7951 | 1.6926 | 1.9753 | 2.3852 | 5.463 | 3.7704 | 6.5199 | 8.2125 | 13.6755 | 17.4459 | -0.14801 | 6.6779 | 1.7951 | 1.6926 | 1.9753 | 2.3852 | 5.463 | 3.7704 | 6.5299 | 8.2225 | 13.6855 | 17.4559 | 0.01
4.9965 | 7.7826 | 1.9666 | 1.9498 | 2.8328 | 2.8997 | 6.7491 | 4.7993 | 12.7791 | 14.7289 | 21.478 | 26.2773 | 4.9965 | 7.7926 | 1.9666 | 1.9498 | 2.8328 | 2.8997 | 6.7491 | 4.7993 | 12.7891 | 14.7389 | 21.488 | 26.2873 | 0.01
2.9362 | 7.3362 | 1.8979 | 1.8468 | 2.4894 | 2.6936 | 6.234 | 4.3872 | 10.2723 | 12.1191 | 18.3532 | 22.7404 | 2.9362 | 7.3462 | 1.8979 | 1.8468 | 2.4894 | 2.6936 | 6.234 | 4.3872 | 10.2823 | 12.1291 | 18.3632 | 22.7504 | 0.01
10.8682 | 9.0548 | 2.1623 | 2.2434 | 3.8114 | 3.4868 | 8.2171 | 5.9736 | 19.923 | 22.1664 | 30.3835 | 36.3571 | 10.8682 | 9.0648 | 2.1623 | 2.2434 | 3.8114 | 3.4868 | 8.2171 | 5.9736 | 19.933 | 22.1764 | 30.3935 | 36.3671 | 0.01
5.3766 | 7.8649 | 1.9792 | 1.9688 | 2.8961 | 2.9377 | 6.8441 | 4.8753 | 13.2415 | 15.2103 | 22.0545 | 26.9298 | 5.3766 | 7.8749 | 1.9792 | 1.9688 | 2.8961 | 2.9377 | 6.8441 | 4.8753 | 13.2515 | 15.2203 | 22.0645 | 26.9398 | 0.01
-3.2425 | 5.9975 | 1.6919 | 1.5379 | 1.4596 | 2.0758 | 4.6894 | 3.1515 | 2.755 | 4.2928 | 8.9822 | 12.1337 | -3.2425 | 6.0075 | 1.6919 | 1.5379 | 1.4596 | 2.0758 | 4.6894 | 3.1515 | 2.765 | 4.3028 | 8.9922 | 12.1437 | 0.01
5.784 | 7.9532 | 1.9928 | 1.9892 | 2.964 | 2.9784 | 6.946 | 4.9568 | 13.7372 | 15.7264 | 22.6724 | 27.6292 | 5.784 | 7.9632 | 1.9928 | 1.9892 | 2.964 | 2.9784 | 6.946 | 4.9568 | 13.7472 | 15.7364 | 22.6824 | 27.6392 | 0.01
0.62392 | 6.8352 | 1.8208 | 1.7312 | 2.104 | 2.4624 | 5.656 | 3.9248 | 7.4591 | 9.1903 | 14.8463 | 18.7711 | 0.62392 | 6.8452 | 1.8208 | 1.7312 | 2.104 | 2.4624 | 5.656 | 3.9248 | 7.4691 | 9.2003 | 14.8563 | 18.7811 | 0.01
3.8817 | 7.541 | 1.9294 | 1.8941 | 2.6469 | 2.7882 | 6.4704 | 4.5763 | 11.4227 | 13.3168 | 19.7872 | 24.3636 | 3.8817 | 7.551 | 1.9294 | 1.8941 | 2.6469 | 2.7882 | 6.4704 | 4.5763 | 11.4327 | 13.3268 | 19.7972 | 24.3736 | 0.01
6.7592 | 8.1645 | 2.0253 | 2.038 | 3.1265 | 3.0759 | 7.1898 | 5.1518 | 14.9237 | 16.9617 | 24.1515 | 29.3033 | 6.7592 | 8.1745 | 2.0253 | 2.038 | 3.1265 | 3.0759 | 7.1898 | 5.1518 | 14.9337 | 16.9717 | 24.1615 | 29.3133 | 0.01
8.4274 | 8.5259 | 2.0809 | 2.1214 | 3.4046 | 3.2427 | 7.6069 | 5.4855 | 16.9534 | 19.0748 | 26.6816 | 32.1671 | 8.4274 | 8.5359 | 2.0809 | 2.1214 | 3.4046 | 3.2427 | 7.6069 | 5.4855 | 16.9634 | 19.0848 | 26.6916 | 32.1771 | 0.01
16.2512 | 10.2211 | 2.3417 | 2.5126 | 4.7085 | 4.0251 | 9.5628 | 7.0502 | 26.4722 | 28.9848 | 38.5476 | 45.5978 | 16.2512 | 10.2311 | 2.3417 | 2.5126 | 4.7085 | 4.0251 | 9.5628 | 7.0502 | 26.4822 | 28.9948 | 38.5576 | 45.6078 | 0.01
3.9702 | 7.5602 | 1.9323 | 1.8985 | 2.6617 | 2.797 | 6.4925 | 4.594 | 11.5304 | 13.4289 | 19.9214 | 24.5155 | 3.9702 | 7.5702 | 1.9323 | 1.8985 | 2.6617 | 2.797 | 6.4925 | 4.594 | 11.5404 | 13.4389 | 19.9314 | 24.5255 | 0.01
9.1031 | 8.6723 | 2.1034 | 2.1552 | 3.5172 | 3.3103 | 7.7758 | 5.6206 | 17.7754 | 19.9305 | 27.7063 | 33.3269 | 9.1031 | 8.6823 | 2.1034 | 2.1552 | 3.5172 | 3.3103 | 7.7758 | 5.6206 | 17.7854 | 19.9405 | 27.7163 | 33.3369 | 0.01
7.6437 | 8.3561 | 2.0548 | 2.0822 | 3.2739 | 3.1644 | 7.4109 | 5.3287 | 15.9998 | 18.082 | 25.4929 | 30.8217 | 7.6437 | 8.3661 | 2.0548 | 2.0822 | 3.2739 | 3.1644 | 7.4109 | 5.3287 | 16.0098 | 18.092 | 25.5029 | 30.8317 | 0.01
7.4801 | 8.3207 | 2.0493 | 2.074 | 3.2467 | 3.148 | 7.37 | 5.296 | 15.8008 | 17.8748 | 25.2449 | 30.5409 | 7.4801 | 8.3307 | 2.0493 | 2.074 | 3.2467 | 3.148 | 7.37 | 5.296 | 15.8108 | 17.8848 | 25.2549 | 30.5509 | 0.01
15.1289 | 9.9779 | 2.3043 | 2.4564 | 4.5215 | 3.9129 | 9.2822 | 6.8258 | 25.1068 | 27.5633 | 36.8455 | 43.6713 | 15.1289 | 9.9879 | 2.3043 | 2.4564 | 4.5215 | 3.9129 | 9.2822 | 6.8258 | 25.1168 | 27.5733 | 36.8555 | 43.6813 | 0.01
0.75091 | 6.8627 | 1.825 | 1.7375 | 2.1252 | 2.4751 | 5.6877 | 3.9502 | 7.6136 | 9.3512 | 15.0389 | 18.9891 | 0.75091 | 6.8727 | 1.825 | 1.7375 | 2.1252 | 2.4751 | 5.6877 | 3.9502 | 7.6236 | 9.3612 | 15.0489 | 18.9991 | 0.01
1.9654 | 7.1258 | 1.8655 | 1.7983 | 2.3276 | 2.5965 | 5.9914 | 4.1931 | 9.0912 | 10.8895 | 16.8809 | 21.0739 | 1.9654 | 7.1358 | 1.8655 | 1.7983 | 2.3276 | 2.5965 | 5.9914 | 4.1931 | 9.1012 | 10.8995 | 16.8909 | 21.0839 | 0.01
9.8869 | 8.8422 | 2.1296 | 2.1943 | 3.6478 | 3.3887 | 7.9717 | 5.7774 | 18.7291 | 20.9234 | 28.8951 | 34.6725 | 9.8869 | 8.8522 | 2.1296 | 2.1943 | 3.6478 | 3.3887 | 7.9717 | 5.7774 | 18.7391 | 20.9334 | 28.9051 | 34.6825 | 0.01
6.4668 | 8.1011 | 2.0156 | 2.0233 | 3.0778 | 3.0467 | 7.1167 | 5.0934 | 14.5679 | 16.5913 | 23.708 | 28.8013 | 6.4668 | 8.1111 | 2.0156 | 2.0233 | 3.0778 | 3.0467 | 7.1167 | 5.0934 | 14.5779 | 16.6013 | 23.718 | 28.8113 | 0.01
7.8432 | 8.3994 | 2.0614 | 2.0922 | 3.3072 | 3.1843 | 7.4608 | 5.3686 | 16.2426 | 18.3348 | 25.7956 | 31.1642 | 7.8432 | 8.4094 | 2.0614 | 2.0922 | 3.3072 | 3.1843 | 7.4608 | 5.3686 | 16.2526 | 18.3448 | 25.8056 | 31.1742 | 0.01
3.9091 | 7.547 | 1.9303 | 1.8955 | 2.6515 | 2.7909 | 6.4773 | 4.5818 | 11.456 | 13.3515 | 19.8288 | 24.4106 | 3.9091 | 7.557 | 1.9303 | 1.8955 | 2.6515 | 2.7909 | 6.4773 | 4.5818 | 11.466 | 13.3615 | 19.8388 | 24.4206 | 0.01
3.4369 | 7.4447 | 1.9146 | 1.8718 | 2.5728 | 2.7437 | 6.3592 | 4.4874 | 10.8815 | 12.7533 | 19.1126 | 23.5999 | 3.4369 | 7.4547 | 1.9146 | 1.8718 | 2.5728 | 2.7437 | 6.3592 | 4.4874 | 10.8915 | 12.7633 | 19.1226 | 23.6099 | 0.01
16.7592 | 10.3312 | 2.3586 | 2.538 | 4.7932 | 4.0759 | 9.6898 | 7.1518 | 27.0903 | 29.6283 | 39.3181 | 46.4699 | 16.7592 | 10.3412 | 2.3586 | 2.538 | 4.7932 | 4.0759 | 9.6898 | 7.1518 | 27.1003 | 29.6383 | 39.3281 | 46.4799 | 0.01
-4.8476 | 5.6497 | 1.6384 | 1.4576 | 1.1921 | 1.9152 | 4.2881 | 2.8305 | 0.80204 | 2.2597 | 6.5478 | 9.3782 | -4.8476 | 5.6597 | 1.6384 | 1.4576 | 1.1921 | 1.9152 | 4.2881 | 2.8305 | 0.81204 | 2.2697 | 6.5578 | 9.3882 | 0.01
4.8571 | 7.7524 | 1.9619 | 1.9429 | 2.8095 | 2.8857 | 6.7143 | 4.7714 | 12.6094 | 14.5523 | 21.2665 | 26.038 | 4.8571 | 7.7624 | 1.9619 | 1.9429 | 2.8095 | 2.8857 | 6.7143 | 4.7714 | 12.6194 | 14.5623 | 21.2765 | 26.048 | 0.01
15.5217 | 10.063 | 2.3174 | 2.4761 | 4.587 | 3.9522 | 9.3804 | 6.9043 | 25.5847 | 28.0608 | 37.4412 | 44.3456 | 15.5217 | 10.073 | 2.3174 | 2.4761 | 4.587 | 3.9522 | 9.3804 | 6.9043 | 25.5947 | 28.0708 | 37.4512 | 44.3556 | 0.01
4.5272 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7054 | 12.2081 | 14.1344 | 20.7662 | 25.4717 | 4.5272 | 7.6909 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7054 | 12.2181 | 14.1444 | 20.7762 | 25.4817 | 0.01
-6.9383 | 5.1967 | 1.5687 | 1.3531 | 0.84362 | 1.7062 | 3.7654 | 2.4123 | -1.7415 | -0.38845 | 3.377 | 5.7893 | -6.9383 | 5.2067 | 1.5687 | 1.3531 | 0.84362 | 1.7062 | 3.7654 | 2.4123 | -1.7315 | -0.37845 | 3.387 | 5.7993 | 0.01
16.9328 | 10.3688 | 2.3644 | 2.5466 | 4.8221 | 4.0933 | 9.7332 | 7.1866 | 27.3016 | 29.8482 | 39.5814 | 46.768 | 16.9328 | 10.3788 | 2.3644 | 2.5466 | 4.8221 | 4.0933 | 9.7332 | 7.1866 | 27.3116 | 29.8582 | 39.5914 | 46.778 | 0.01
14.0968 | 9.7543 | 2.2699 | 2.4048 | 4.3495 | 3.8097 | 9.0242 | 6.6194 | 23.8511 | 26.2559 | 35.2801 | 41.8995 | 14.0968 | 9.7643 | 2.2699 | 2.4048 | 4.3495 | 3.8097 | 9.0242 | 6.6194 | 23.8611 | 26.2659 | 35.2901 | 41.9095 | 0.01
21.6875 | 11.399 | 2.5229 | 2.7844 | 5.6146 | 4.5687 | 10.9219 | 8.1375 | 33.0864 | 35.8708 | 46.7927 | 54.9302 | 21.6875 | 11.409 | 2.5229 | 2.7844 | 5.6146 | 4.5687 | 10.9219 | 8.1375 | 33.0964 | 35.8808 | 46.8027 | 54.9402 | 0.01
14.6441 | 9.8729 | 2.2881 | 2.4322 | 4.4407 | 3.8644 | 9.161 | 6.7288 | 24.5169 | 26.9491 | 36.1102 | 42.839 | 14.6441 | 9.8829 | 2.2881 | 2.4322 | 4.4407 | 3.8644 | 9.161 | 6.7288 | 24.5269 | 26.9591 | 36.1202 | 42.849 | 0.01
0.7403 | 6.8604 | 1.8247 | 1.737 | 2.1234 | 2.474 | 5.6851 | 3.9481 | 7.6007 | 9.3377 | 15.0228 | 18.9709 | 0.7403 | 6.8704 | 1.8247 | 1.737 | 2.1234 | 2.474 | 5.6851 | 3.9481 | 7.6107 | 9.3477 | 15.0328 | 18.9809 | 0.01
0.19334 | 6.7419 | 1.8064 | 1.7097 | 2.0322 | 2.4193 | 5.5483 | 3.8387 | 6.9352 | 8.6449 | 14.1932 | 18.0319 | 0.19334 | 6.7519 | 1.8064 | 1.7097 | 2.0322 | 2.4193 | 5.5483 | 3.8387 | 6.9452 | 8.6549 | 14.2032 | 18.0419 | 0.01
8.7563 | 8.5972 | 2.0919 | 2.1378 | 3.4594 | 3.2756 | 7.6891 | 5.5513 | 17.3534 | 19.4913 | 27.1803 | 32.7316 | 8.7563 | 8.6072 | 2.0919 | 2.1378 | 3.4594 | 3.2756 | 7.6891 | 5.5513 | 17.3634 | 19.5013 | 27.1903 | 32.7416 | 0.01
8.0989 | 8.4548 | 2.07 | 2.1049 | 3.3498 | 3.2099 | 7.5247 | 5.4198 | 16.5537 | 18.6586 | 26.1833 | 31.6031 | 8.0989 | 8.4648 | 2.07 | 2.1049 | 3.3498 | 3.2099 | 7.5247 | 5.4198 | 16.5637 | 18.6686 | 26.1933 | 31.6131 | 0.01
-3.4729 | 5.9475 | 1.6842 | 1.5264 | 1.4212 | 2.0527 | 4.6318 | 3.1054 | 2.4746 | 4.0009 | 8.6327 | 11.7381 | -3.4729 | 5.9575 | 1.6842 | 1.5264 | 1.4212 | 2.0527 | 4.6318 | 3.1054 | 2.4846 | 4.0109 | 8.6427 | 11.7481 | 0.01
0.19703 | 6.7427 | 1.8066 | 1.7099 | 2.0328 | 2.4197 | 5.5493 | 3.8394 | 6.9397 | 8.6496 | 14.1988 | 18.0382 | 0.19703 | 6.7527 | 1.8066 | 1.7099 | 2.0328 | 2.4197 | 5.5493 | 3.8394 | 6.9497 | 8.6596 | 14.2088 | 18.0482 | 0.01
2.1437 | 7.1645 | 1.8715 | 1.8072 | 2.3573 | 2.6144 | 6.0359 | 4.2287 | 9.3082 | 11.1154 | 17.1513 | 21.38 | 2.1437 | 7.1745 | 1.8715 | 1.8072 | 2.3573 | 2.6144 | 6.0359 | 4.2287 | 9.3182 | 11.1254 | 17.1613 | 21.39 | 0.01
2.1804 | 7.1724 | 1.8727 | 1.809 | 2.3634 | 2.618 | 6.0451 | 4.2361 | 9.3528 | 11.1618 | 17.2069 | 21.443 | 2.1804 | 7.1824 | 1.8727 | 1.809 | 2.3634 | 2.618 | 6.0451 | 4.2361 | 9.3628 | 11.1718 | 17.2169 | 21.453 | 0.01
8.4919 | 8.5399 | 2.0831 | 2.1246 | 3.4153 | 3.2492 | 7.623 | 5.4984 | 17.0318 | 19.1564 | 26.7793 | 32.2777 | 8.4919 | 8.5499 | 2.0831 | 2.1246 | 3.4153 | 3.2492 | 7.623 | 5.4984 | 17.0418 | 19.1664 | 26.7893 | 32.2877 | 0.01
-0.30742 | 6.6334 | 1.7898 | 1.6846 | 1.9488 | 2.3693 | 5.4231 | 3.7385 | 6.326 | 8.0106 | 13.4337 | 17.1723 | -0.30742 | 6.6434 | 1.7898 | 1.6846 | 1.9488 | 2.3693 | 5.4231 | 3.7385 | 6.336 | 8.0206 | 13.4437 | 17.1823 | 0.01
5.7009 | 7.9352 | 1.99 | 1.985 | 2.9501 | 2.9701 | 6.9252 | 4.9402 | 13.6361 | 15.6211 | 22.5463 | 27.4865 | 5.7009 | 7.9452 | 1.99 | 1.985 | 2.9501 | 2.9701 | 6.9252 | 4.9402 | 13.6461 | 15.6311 | 22.5563 | 27.4965 | 0.01
3.9954 | 7.5657 | 1.9332 | 1.8998 | 2.6659 | 2.7995 | 6.4988 | 4.5991 | 11.561 | 13.4608 | 19.9596 | 24.5587 | 3.9954 | 7.5757 | 1.9332 | 1.8998 | 2.6659 | 2.7995 | 6.4988 | 4.5991 | 11.571 | 13.4708 | 19.9696 | 24.5687 | 0.01
2.8736 | 7.3226 | 1.8958 | 1.8437 | 2.4789 | 2.6874 | 6.2184 | 4.3747 | 10.1962 | 12.0399 | 18.2583 | 22.633 | 2.8736 | 7.3326 | 1.8958 | 1.8437 | 2.4789 | 2.6874 | 6.2184 | 4.3747 | 10.2062 | 12.0499 | 18.2683 | 22.643 | 0.01
7.4078 | 8.305 | 2.0469 | 2.0704 | 3.2346 | 3.1408 | 7.352 | 5.2816 | 15.7128 | 17.7832 | 25.1352 | 30.4167 | 7.4078 | 8.315 | 2.0469 | 2.0704 | 3.2346 | 3.1408 | 7.352 | 5.2816 | 15.7228 | 17.7932 | 25.1452 | 30.4267 | 0.01
4.6413 | 7.7056 | 1.9547 | 1.9321 | 2.7735 | 2.8641 | 6.6603 | 4.7283 | 12.3469 | 14.2789 | 20.9392 | 25.6675 | 4.6413 | 7.7156 | 1.9547 | 1.9321 | 2.7735 | 2.8641 | 6.6603 | 4.7283 | 12.3569 | 14.2889 | 20.9492 | 25.6775 | 0.01
17.8399 | 10.5653 | 2.3947 | 2.592 | 4.9733 | 4.184 | 9.96 | 7.368 | 28.4052 | 30.9972 | 40.9571 | 48.3251 | 17.8399 | 10.5753 | 2.3947 | 2.592 | 4.9733 | 4.184 | 9.96 | 7.368 | 28.4152 | 31.0072 | 40.9671 | 48.3351 | 0.01
10.3126 | 8.9344 | 2.1438 | 2.2156 | 3.7188 | 3.4313 | 8.0782 | 5.8625 | 19.2471 | 21.4627 | 29.5409 | 35.4034 | 10.3126 | 8.9444 | 2.1438 | 2.2156 | 3.7188 | 3.4313 | 8.0782 | 5.8625 | 19.2571 | 21.4727 | 29.5509 | 35.4134 | 0.01
0.93636 | 6.9029 | 1.8312 | 1.7468 | 2.1561 | 2.4936 | 5.7341 | 3.9873 | 7.8392 | 9.5861 | 15.3201 | 19.3074 | 0.93636 | 6.9129 | 1.8312 | 1.7468 | 2.1561 | 2.4936 | 5.7341 | 3.9873 | 7.8492 | 9.5961 | 15.3301 | 19.3174 | 0.01
5.9171 | 7.982 | 1.9972 | 1.9959 | 2.9862 | 2.9917 | 6.9793 | 4.9834 | 13.8992 | 15.8951 | 22.8743 | 27.8578 | 5.9171 | 7.992 | 1.9972 | 1.9959 | 2.9862 | 2.9917 | 6.9793 | 4.9834 | 13.9092 | 15.9051 | 22.8843 | 27.8678 | 0.01
14.2609 | 9.7899 | 2.2754 | 2.413 | 4.3768 | 3.8261 | 9.0652 | 6.6522 | 24.0507 | 26.4638 | 35.529 | 42.1812 | 14.2609 | 9.7999 | 2.2754 | 2.413 | 4.3768 | 3.8261 | 9.0652 | 6.6522 | 24.0607 | 26.4738 | 35.539 | 42.1912 | 0.01
4.7586 | 7.731 | 1.9586 | 1.9379 | 2.7931 | 2.8759 | 6.6897 | 4.7517 | 12.4897 | 14.4276 | 21.1173 | 25.869 | 4.7586 | 7.741 | 1.9586 | 1.9379 | 2.7931 | 2.8759 | 6.6897 | 4.7517 | 12.4997 | 14.4376 | 21.1273 | 25.879 | 0.01
-1.5358 | 6.3672 | 1.7488 | 1.6232 | 1.744 | 2.2464 | 5.116 | 3.4928 | 4.8314 | 6.4546 | 11.5707 | 15.0635 | -1.5358 | 6.3772 | 1.7488 | 1.6232 | 1.744 | 2.2464 | 5.116 | 3.4928 | 4.8414 | 6.4646 | 11.5807 | 15.0735 | 0.01
4.5187 | 7.6791 | 1.9506 | 1.9259 | 2.7531 | 2.8519 | 6.6297 | 4.7037 | 12.1977 | 14.1237 | 20.7534 | 25.4571 | 4.5187 | 7.6891 | 1.9506 | 1.9259 | 2.7531 | 2.8519 | 6.6297 | 4.7037 | 12.2077 | 14.1337 | 20.7634 | 25.4671 | 0.01
10.9318 | 9.0686 | 2.1644 | 2.2466 | 3.822 | 3.4932 | 8.233 | 5.9864 | 20.0004 | 22.247 | 30.4799 | 36.4663 | 10.9318 | 9.0786 | 2.1644 | 2.2466 | 3.822 | 3.4932 | 8.233 | 5.9864 | 20.0104 | 22.257 | 30.4899 | 36.4763 | 0.01
3.7619 | 7.5151 | 1.9254 | 1.8881 | 2.627 | 2.7762 | 6.4405 | 4.5524 | 11.2769 | 13.165 | 19.6055 | 24.1579 | 3.7619 | 7.5251 | 1.9254 | 1.8881 | 2.627 | 2.7762 | 6.4405 | 4.5524 | 11.2869 | 13.175 | 19.6155 | 24.1679 | 0.01
0.66962 | 6.8451 | 1.8223 | 1.7335 | 2.1116 | 2.467 | 5.6674 | 3.9339 | 7.5147 | 9.2482 | 14.9156 | 18.8495 | 0.66962 | 6.8551 | 1.8223 | 1.7335 | 2.1116 | 2.467 | 5.6674 | 3.9339 | 7.5247 | 9.2582 | 14.9256 | 18.8595 | 0.01
8.4453 | 8.5298 | 2.0815 | 2.1223 | 3.4076 | 3.2445 | 7.6113 | 5.4891 | 16.9752 | 19.0974 | 26.7088 | 32.1978 | 8.4453 | 8.5398 | 2.0815 | 2.1223 | 3.4076 | 3.2445 | 7.6113 | 5.4891 | 16.9852 | 19.1074 | 26.7188 | 32.2078 | 0.01
4 | 7.5667 | 1.9333 | 1.9 | 2.6667 | 2.8 | 6.5 | 4.6 | 11.5666 | 13.4666 | 19.9666 | 24.5666 | 4 | 7.5767 | 1.9333 | 1.9 | 2.6667 | 2.8 | 6.5 | 4.6 | 11.5766 | 13.4766 | 19.9766 | 24.5766 | 0.01
0.11313 | 6.7245 | 1.8038 | 1.7057 | 2.0189 | 2.4113 | 5.5283 | 3.8226 | 6.8376 | 8.5433 | 14.0716 | 17.8942 | 0.11313 | 6.7345 | 1.8038 | 1.7057 | 2.0189 | 2.4113 | 5.5283 | 3.8226 | 6.8476 | 8.5533 | 14.0816 | 17.9042 | 0.01
14.3302 | 9.8049 | 2.2777 | 2.4165 | 4.3884 | 3.833 | 9.0825 | 6.666 | 24.135 | 26.5516 | 35.6341 | 42.3001 | 14.3302 | 9.8149 | 2.2777 | 2.4165 | 4.3884 | 3.833 | 9.0825 | 6.666 | 24.145 | 26.5616 | 35.6441 | 42.3101 | 0.01
0.82956 | 6.8797 | 1.8277 | 1.7415 | 2.1383 | 2.483 | 5.7074 | 3.9659 | 7.7093 | 9.4508 | 15.1582 | 19.1241 | 0.82956 | 6.8897 | 1.8277 | 1.7415 | 2.1383 | 2.483 | 5.7074 | 3.9659 | 7.7193 | 9.4608 | 15.1682 | 19.1341 | 0.01
6.5365 | 8.1162 | 2.0179 | 2.0268 | 3.0894 | 3.0537 | 7.1341 | 5.1073 | 14.6528 | 16.6796 | 23.8137 | 28.921 | 6.5365 | 8.1262 | 2.0179 | 2.0268 | 3.0894 | 3.0537 | 7.1341 | 5.1073 | 14.6628 | 16.6896 | 23.8237 | 28.931 | 0.01
2.4857 | 7.2386 | 1.8829 | 1.8243 | 2.4143 | 2.6486 | 6.1214 | 4.2971 | 9.7243 | 11.5486 | 17.67 | 21.9671 | 2.4857 | 7.2486 | 1.8829 | 1.8243 | 2.4143 | 2.6486 | 6.1214 | 4.2971 | 9.7343 | 11.5586 | 17.68 | 21.9771 | 0.01
9.4618 | 8.7501 | 2.1154 | 2.1731 | 3.577 | 3.3462 | 7.8655 | 5.6924 | 18.2119 | 20.385 | 28.2504 | 33.9428 | 9.4618 | 8.7601 | 2.1154 | 2.1731 | 3.577 | 3.3462 | 7.8655 | 5.6924 | 18.2219 | 20.395 | 28.2604 | 33.9528 | 0.01
10.5152 | 8.9783 | 2.1505 | 2.2258 | 3.7525 | 3.4515 | 8.1288 | 5.903 | 19.4935 | 21.7193 | 29.8481 | 35.7511 | 10.5152 | 8.9883 | 2.1505 | 2.2258 | 3.7525 | 3.4515 | 8.1288 | 5.903 | 19.5035 | 21.7293 | 29.8581 | 35.7611 | 0.01
13.8852 | 9.7085 | 2.2628 | 2.3943 | 4.3142 | 3.7885 | 8.9713 | 6.577 | 23.5937 | 25.9879 | 34.9592 | 41.5363 | 13.8852 | 9.7185 | 2.2628 | 2.3943 | 4.3142 | 3.7885 | 8.9713 | 6.577 | 23.6037 | 25.9979 | 34.9692 | 41.5463 | 0.01
7.4114 | 8.3058 | 2.047 | 2.0706 | 3.2352 | 3.1411 | 7.3529 | 5.2823 | 15.7172 | 17.7878 | 25.1406 | 30.4229 | 7.4114 | 8.3158 | 2.047 | 2.0706 | 3.2352 | 3.1411 | 7.3529 | 5.2823 | 15.7272 | 17.7978 | 25.1506 | 30.4329 | 0.01
3.3173 | 7.4187 | 1.9106 | 1.8659 | 2.5529 | 2.7317 | 6.3293 | 4.4635 | 10.736 | 12.6019 | 18.9312 | 23.3947 | 3.3173 | 7.4287 | 1.9106 | 1.8659 | 2.5529 | 2.7317 | 6.3293 | 4.4635 | 10.746 | 12.6119 | 18.9412 | 23.4047 | 0.01
6.514 | 8.1114 | 2.0171 | 2.0257 | 3.0857 | 3.0514 | 7.1285 | 5.1028 | 14.6253 | 16.651 | 23.7795 | 28.8823 | 6.514 | 8.1214 | 2.0171 | 2.0257 | 3.0857 | 3.0514 | 7.1285 | 5.1028 | 14.6353 | 16.661 | 23.7895 | 28.8923 | 0.01
-0.5379 | 6.5835 | 1.7821 | 1.6731 | 1.9104 | 2.3462 | 5.3655 | 3.6924 | 6.0456 | 7.7187 | 13.0842 | 16.7766 | -0.5379 | 6.5935 | 1.7821 | 1.6731 | 1.9104 | 2.3462 | 5.3655 | 3.6924 | 6.0556 | 7.7287 | 13.0942 | 16.7866 | 0.01
1.9903 | 7.1312 | 1.8663 | 1.7995 | 2.3317 | 2.599 | 5.9976 | 4.1981 | 9.1215 | 10.9211 | 16.9186 | 21.1167 | 1.9903 | 7.1412 | 1.8663 | 1.7995 | 2.3317 | 2.599 | 5.9976 | 4.1981 | 9.1315 | 10.9311 | 16.9286 | 21.1267 | 0.01
17.5171 | 10.4954 | 2.3839 | 2.5759 | 4.9195 | 4.1517 | 9.8793 | 7.3034 | 28.0125 | 30.5883 | 40.4676 | 47.771 | 17.5171 | 10.5054 | 2.3839 | 2.5759 | 4.9195 | 4.1517 | 9.8793 | 7.3034 | 28.0225 | 30.5983 | 40.4776 | 47.781 | 0.01
5.7762 | 7.9515 | 1.9925 | 1.9888 | 2.9627 | 2.9776 | 6.9441 | 4.9552 | 13.7277 | 15.7166 | 22.6606 | 27.6159 | 5.7762 | 7.9615 | 1.9925 | 1.9888 | 2.9627 | 2.9776 | 6.9441 | 4.9552 | 13.7377 | 15.7266 | 22.6706 | 27.6259 | 0.01
5.936 | 7.9861 | 1.9979 | 1.9968 | 2.9893 | 2.9936 | 6.984 | 4.9872 | 13.9222 | 15.919 | 22.903 | 27.8902 | 5.936 | 7.9961 | 1.9979 | 1.9968 | 2.9893 | 2.9936 | 6.984 | 4.9872 | 13.9322 | 15.929 | 22.913 | 27.9002 | 0.01
-4.9884 | 5.6192 | 1.6337 | 1.4506 | 1.1686 | 1.9012 | 4.2529 | 2.8023 | 0.63082 | 2.0814 | 6.3343 | 9.1366 | -4.9884 | 5.6292 | 1.6337 | 1.4506 | 1.1686 | 1.9012 | 4.2529 | 2.8023 | 0.64082 | 2.0914 | 6.3443 | 9.1466 | 0.01
4.2438 | 7.6195 | 1.9415 | 1.9122 | 2.7073 | 2.8244 | 6.561 | 4.6488 | 11.8633 | 13.7755 | 20.3365 | 24.9852 | 4.2438 | 7.6295 | 1.9415 | 1.9122 | 2.7073 | 2.8244 | 6.561 | 4.6488 | 11.8733 | 13.7855 | 20.3465 | 24.9952 | 0.01
8.0514 | 8.4445 | 2.0684 | 2.1026 | 3.3419 | 3.2051 | 7.5128 | 5.4103 | 16.4958 | 18.5984 | 26.1112 | 31.5215 | 8.0514 | 8.4545 | 2.0684 | 2.1026 | 3.3419 | 3.2051 | 7.5128 | 5.4103 | 16.5058 | 18.6084 | 26.1212 | 31.5315 | 0.01
-8.3684 | 4.8868 | 1.5211 | 1.2816 | 0.60526 | 1.5632 | 3.4079 | 2.1263 | -3.4816 | -2.2 | 1.2079 | 3.3342 | -8.3684 | 4.8968 | 1.5211 | 1.2816 | 0.60526 | 1.5632 | 3.4079 | 2.1263 | -3.4716 | -2.19 | 1.2179 | 3.3442 | 0.01
10.4473 | 8.9636 | 2.1482 | 2.2224 | 3.7412 | 3.4447 | 8.1118 | 5.8895 | 19.4109 | 21.6333 | 29.7451 | 35.6346 | 10.4473 | 8.9736 | 2.1482 | 2.2224 | 3.7412 | 3.4447 | 8.1118 | 5.8895 | 19.4209 | 21.6433 | 29.7551 | 35.6446 | 0.01
6.2781 | 8.0603 | 2.0093 | 2.0139 | 3.0463 | 3.0278 | 7.0695 | 5.0556 | 14.3383 | 16.3522 | 23.4218 | 28.4774 | 6.2781 | 8.0703 | 2.0093 | 2.0139 | 3.0463 | 3.0278 | 7.0695 | 5.0556 | 14.3483 | 16.3622 | 23.4318 | 28.4874 | 0.01
-0.026116 | 6.6943 | 1.7991 | 1.6987 | 1.9956 | 2.3974 | 5.4935 | 3.7948 | 6.6682 | 8.3669 | 13.8604 | 17.6552 | -0.026116 | 6.7043 | 1.7991 | 1.6987 | 1.9956 | 2.3974 | 5.4935 | 3.7948 | 6.6782 | 8.3769 | 13.8704 | 17.6652 | 0.01
12.3808 | 9.3825 | 2.2127 | 2.319 | 4.0635 | 3.6381 | 8.5952 | 6.2762 | 21.7633 | 24.0823 | 32.6775 | 38.9537 | 12.3808 | 9.3925 | 2.2127 | 2.319 | 4.0635 | 3.6381 | 8.5952 | 6.2762 | 21.7733 | 24.0923 | 32.6875 | 38.9637 | 0.01
4.3092 | 7.6337 | 1.9436 | 1.9155 | 2.7182 | 2.8309 | 6.5773 | 4.6618 | 11.9428 | 13.8583 | 20.4356 | 25.0974 | 4.3092 | 7.6437 | 1.9436 | 1.9155 | 2.7182 | 2.8309 | 6.5773 | 4.6618 | 11.9528 | 13.8683 | 20.4456 | 25.1074 | 0.01
9.5463 | 8.7684 | 2.1182 | 2.1773 | 3.591 | 3.3546 | 7.8866 | 5.7093 | 18.3146 | 20.492 | 28.3785 | 34.0878 | 9.5463 | 8.7784 | 2.1182 | 2.1773 | 3.591 | 3.3546 | 7.8866 | 5.7093 | 18.3246 | 20.502 | 28.3885 | 34.0978 | 0.01
3.7633 | 7.5154 | 1.9254 | 1.8882 | 2.6272 | 2.7763 | 6.4408 | 4.5527 | 11.2787 | 13.1668 | 19.6077 | 24.1603 | 3.7633 | 7.5254 | 1.9254 | 1.8882 | 2.6272 | 2.7763 | 6.4408 | 4.5527 | 11.2887 | 13.1768 | 19.6177 | 24.1703 | 0.01
8.7658 | 8.5992 | 2.0922 | 2.1383 | 3.461 | 3.2766 | 7.6914 | 5.5532 | 17.365 | 19.5033 | 27.1947 | 32.7479 | 8.7658 | 8.6092 | 2.0922 | 2.1383 | 3.461 | 3.2766 | 7.6914 | 5.5532 | 17.375 | 19.5133 | 27.2047 | 32.7579 | 0.01
0.69767 | 6.8512 | 1.8233 | 1.7349 | 2.1163 | 2.4698 | 5.6744 | 3.9395 | 7.5488 | 9.2837 | 14.9581 | 18.8977 | 0.69767 | 6.8612 | 1.8233 | 1.7349 | 2.1163 | 2.4698 | 5.6744 | 3.9395 | 7.5588 | 9.2937 | 14.9681 | 18.9077 | 0.01
11.5977 | 9.2128 | 2.1866 | 2.2799 | 3.9329 | 3.5598 | 8.3994 | 6.1195 | 20.8105 | 23.0904 | 31.4898 | 37.6094 | 11.5977 | 9.2228 | 2.1866 | 2.2799 | 3.9329 | 3.5598 | 8.3994 | 6.1195 | 20.8205 | 23.1004 | 31.4998 | 37.6194 | 0.01
8.4712 | 8.5354 | 2.0824 | 2.1236 | 3.4119 | 3.2471 | 7.6178 | 5.4942 | 17.0067 | 19.1302 | 26.748 | 32.2423 | 8.4712 | 8.5454 | 2.0824 | 2.1236 | 3.4119 | 3.2471 | 7.6178 | 5.4942 | 17.0167 | 19.1402 | 26.758 | 32.2523 | 0.01
18.2142 | 10.6464 | 2.4071 | 2.6107 | 5.0357 | 4.2214 | 10.0536 | 7.4428 | 28.8606 | 31.4713 | 41.5249 | 48.9677 | 18.2142 | 10.6564 | 2.4071 | 2.6107 | 5.0357 | 4.2214 | 10.0536 | 7.4428 | 28.8706 | 31.4813 | 41.5349 | 48.9777 | 0.01
13.8999 | 9.7117 | 2.2633 | 2.395 | 4.3167 | 3.79 | 8.975 | 6.58 | 23.6116 | 26.0066 | 34.9816 | 41.5615 | 13.8999 | 9.7217 | 2.2633 | 2.395 | 4.3167 | 3.79 | 8.975 | 6.58 | 23.6216 | 26.0166 | 34.9916 | 41.5715 | 0.01
6.3636 | 8.0788 | 2.0121 | 2.0182 | 3.0606 | 3.0364 | 7.0909 | 5.0727 | 14.4424 | 16.4605 | 23.5514 | 28.6242 | 6.3636 | 8.0888 | 2.0121 | 2.0182 | 3.0606 | 3.0364 | 7.0909 | 5.0727 | 14.4524 | 16.4705 | 23.5614 | 28.6342 | 0.01
6.9097 | 8.1971 | 2.0303 | 2.0455 | 3.1516 | 3.091 | 7.2274 | 5.1819 | 15.1068 | 17.1523 | 24.3797 | 29.5616 | 6.9097 | 8.2071 | 2.0303 | 2.0455 | 3.1516 | 3.091 | 7.2274 | 5.1819 | 15.1168 | 17.1623 | 24.3897 | 29.5716 | 0.01
1.1273 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7818 | 4.0255 | 8.0716 | 9.8279 | 15.6098 | 19.6352 | 1.1273 | 6.9543 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7818 | 4.0255 | 8.0816 | 9.8379 | 15.6198 | 19.6452 | 0.01
15.8964 | 10.1442 | 2.3299 | 2.4948 | 4.6494 | 3.9896 | 9.4741 | 6.9793 | 26.0407 | 28.5355 | 38.0096 | 44.9889 | 15.8964 | 10.1542 | 2.3299 | 2.4948 | 4.6494 | 3.9896 | 9.4741 | 6.9793 | 26.0507 | 28.5455 | 38.0196 | 44.9989 | 0.01
6.1089 | 8.0236 | 2.0036 | 2.0054 | 3.0181 | 3.0109 | 7.0272 | 5.0218 | 14.1325 | 16.1379 | 23.1651 | 28.1869 | 6.1089 | 8.0336 | 2.0036 | 2.0054 | 3.0181 | 3.0109 | 7.0272 | 5.0218 | 14.1425 | 16.1479 | 23.1751 | 28.1969 | 0.01
0.25643 | 6.7556 | 1.8085 | 1.7128 | 2.0427 | 2.4256 | 5.5641 | 3.8513 | 7.012 | 8.7248 | 14.2889 | 18.1402 | 0.25643 | 6.7656 | 1.8085 | 1.7128 | 2.0427 | 2.4256 | 5.5641 | 3.8513 | 7.022 | 8.7348 | 14.2989 | 18.1502 | 0.01
-4.2332 | 5.7828 | 1.6589 | 1.4883 | 1.2945 | 1.9767 | 4.4417 | 2.9534 | 1.5496 | 3.038 | 7.4797 | 10.433 | -4.2332 | 5.7928 | 1.6589 | 1.4883 | 1.2945 | 1.9767 | 4.4417 | 2.9534 | 1.5596 | 3.048 | 7.4897 | 10.443 | 0.01
3.0006 | 7.3501 | 1.9 | 1.85 | 2.5001 | 2.7001 | 6.2501 | 4.4001 | 10.3507 | 12.2007 | 18.4509 | 22.851 | 3.0006 | 7.3601 | 1.9 | 1.85 | 2.5001 | 2.7001 | 6.2501 | 4.4001 | 10.3607 | 12.2107 | 18.4609 | 22.861 | 0.01
-0.019623 | 6.6957 | 1.7993 | 1.699 | 1.9967 | 2.398 | 5.4951 | 3.7961 | 6.6761 | 8.3751 | 13.8702 | 17.6663 | -0.019623 | 6.7057 | 1.7993 | 1.699 | 1.9967 | 2.398 | 5.4951 | 3.7961 | 6.6861 | 8.3851 | 13.8802 | 17.6763 | 0.01
1.7234 | 7.0734 | 1.8574 | 1.7862 | 2.2872 | 2.5723 | 5.9308 | 4.1447 | 8.7968 | 10.583 | 16.5138 | 20.6585 | 1.7234 | 7.0834 | 1.8574 | 1.7862 | 2.2872 | 2.5723 | 5.9308 | 4.1447 | 8.8068 | 10.593 | 16.5238 | 20.6685 | 0.01
17.9337 | 10.5856 | 2.3978 | 2.5967 | 4.9889 | 4.1934 | 9.9834 | 7.3867 | 28.5193 | 31.116 | 41.0994 | 48.4862 | 17.9337 | 10.5956 | 2.3978 | 2.5967 | 4.9889 | 4.1934 | 9.9834 | 7.3867 | 28.5293 | 31.126 | 41.1094 | 48.4962 | 0.01
5.9536 | 7.9899 | 1.9985 | 1.9977 | 2.9923 | 2.9954 | 6.9884 | 4.9907 | 13.9435 | 15.9412 | 22.9296 | 27.9203 | 5.9536 | 7.9999 | 1.9985 | 1.9977 | 2.9923 | 2.9954 | 6.9884 | 4.9907 | 13.9535 | 15.9512 | 22.9396 | 27.9303 | 0.01
8.1286 | 8.4612 | 2.071 | 2.1064 | 3.3548 | 3.2129 | 7.5321 | 5.4257 | 16.5897 | 18.6962 | 26.2283 | 31.654 | 8.1286 | 8.4712 | 2.071 | 2.1064 | 3.3548 | 3.2129 | 7.5321 | 5.4257 | 16.5997 | 18.7062 | 26.2383 | 31.664 | 0.01
0.99013 | 6.9145 | 1.833 | 1.7495 | 2.165 | 2.499 | 5.7475 | 3.998 | 7.9047 | 9.6542 | 15.4017 | 19.3997 | 0.99013 | 6.9245 | 1.833 | 1.7495 | 2.165 | 2.499 | 5.7475 | 3.998 | 7.9147 | 9.6642 | 15.4117 | 19.4097 | 0.01
9.9327 | 8.8521 | 2.1311 | 2.1966 | 3.6554 | 3.3933 | 7.9832 | 5.7865 | 18.7847 | 20.9814 | 28.9645 | 34.7511 | 9.9327 | 8.8621 | 2.1311 | 2.1966 | 3.6554 | 3.3933 | 7.9832 | 5.7865 | 18.7947 | 20.9914 | 28.9745 | 34.7611 | 0.01
13.1113 | 9.5408 | 2.237 | 2.3556 | 4.1852 | 3.7111 | 8.7778 | 6.4223 | 22.6521 | 25.0077 | 33.7855 | 40.2078 | 13.1113 | 9.5508 | 2.237 | 2.3556 | 4.1852 | 3.7111 | 8.7778 | 6.4223 | 22.6621 | 25.0177 | 33.7955 | 40.2178 | 0.01
3.9177 | 7.5488 | 1.9306 | 1.8959 | 2.6529 | 2.7918 | 6.4794 | 4.5835 | 11.4665 | 13.3624 | 19.8418 | 24.4253 | 3.9177 | 7.5588 | 1.9306 | 1.8959 | 2.6529 | 2.7918 | 6.4794 | 4.5835 | 11.4765 | 13.3724 | 19.8518 | 24.4353 | 0.01
4.0887 | 7.5859 | 1.9363 | 1.9044 | 2.6814 | 2.8089 | 6.5222 | 4.6177 | 11.6745 | 13.579 | 20.1011 | 24.7189 | 4.0887 | 7.5959 | 1.9363 | 1.9044 | 2.6814 | 2.8089 | 6.5222 | 4.6177 | 11.6845 | 13.589 | 20.1111 | 24.7289 | 0.01
-0.055066 | 6.6881 | 1.7982 | 1.6972 | 1.9908 | 2.3945 | 5.4862 | 3.789 | 6.633 | 8.3303 | 13.8165 | 17.6055 | -0.055066 | 6.6981 | 1.7982 | 1.6972 | 1.9908 | 2.3945 | 5.4862 | 3.789 | 6.643 | 8.3403 | 13.8265 | 17.6155 | 0.01
3.9499 | 7.5558 | 1.9317 | 1.8975 | 2.6583 | 2.795 | 6.4875 | 4.59 | 11.5057 | 13.4032 | 19.8906 | 24.4806 | 3.9499 | 7.5658 | 1.9317 | 1.8975 | 2.6583 | 2.795 | 6.4875 | 4.59 | 11.5157 | 13.4132 | 19.9006 | 24.4906 | 0.01
2.5412 | 7.2506 | 1.8847 | 1.8271 | 2.4235 | 2.6541 | 6.1353 | 4.3082 | 9.7918 | 11.6189 | 17.7542 | 22.0624 | 2.5412 | 7.2606 | 1.8847 | 1.8271 | 2.4235 | 2.6541 | 6.1353 | 4.3082 | 9.8018 | 11.6289 | 17.7642 | 22.0724 | 0.01
-1.6705 | 6.3381 | 1.7443 | 1.6165 | 1.7216 | 2.233 | 5.0824 | 3.4659 | 4.6676 | 6.2841 | 11.3664 | 14.8323 | -1.6705 | 6.3481 | 1.7443 | 1.6165 | 1.7216 | 2.233 | 5.0824 | 3.4659 | 4.6776 | 6.2941 | 11.3764 | 14.8423 | 0.01
17.8938 | 10.577 | 2.3965 | 2.5947 | 4.9823 | 4.1894 | 9.9734 | 7.3788 | 28.4708 | 31.0655 | 41.0389 | 48.4177 | 17.8938 | 10.587 | 2.3965 | 2.5947 | 4.9823 | 4.1894 | 9.9734 | 7.3788 | 28.4808 | 31.0755 | 41.0489 | 48.4277 | 0.01
2.6217 | 7.268 | 1.8874 | 1.8311 | 2.4369 | 2.6622 | 6.1554 | 4.3243 | 9.8897 | 11.7208 | 17.8762 | 22.2005 | 2.6217 | 7.278 | 1.8874 | 1.8311 | 2.4369 | 2.6622 | 6.1554 | 4.3243 | 9.8997 | 11.7308 | 17.8862 | 22.2105 | 0.01
6.531 | 8.1151 | 2.0177 | 2.0266 | 3.0885 | 3.0531 | 7.1328 | 5.1062 | 14.6461 | 16.6726 | 23.8054 | 28.9116 | 6.531 | 8.1251 | 2.0177 | 2.0266 | 3.0885 | 3.0531 | 7.1328 | 5.1062 | 14.6561 | 16.6826 | 23.8154 | 28.9216 | 0.01
-0.63752 | 6.5619 | 1.7787 | 1.6681 | 1.8937 | 2.3362 | 5.3406 | 3.6725 | 5.9244 | 7.5925 | 12.9331 | 16.6056 | -0.63752 | 6.5719 | 1.7787 | 1.6681 | 1.8937 | 2.3362 | 5.3406 | 3.6725 | 5.9344 | 7.6025 | 12.9431 | 16.6156 | 0.01
3.242 | 7.4024 | 1.9081 | 1.8621 | 2.5403 | 2.7242 | 6.3105 | 4.4484 | 10.6444 | 12.5065 | 18.817 | 23.2654 | 3.242 | 7.4124 | 1.9081 | 1.8621 | 2.5403 | 2.7242 | 6.3105 | 4.4484 | 10.6544 | 12.5165 | 18.827 | 23.2754 | 0.01
7.7059 | 8.3696 | 2.0569 | 2.0853 | 3.2843 | 3.1706 | 7.4265 | 5.3412 | 16.0755 | 18.1608 | 25.5873 | 30.9285 | 7.7059 | 8.3796 | 2.0569 | 2.0853 | 3.2843 | 3.1706 | 7.4265 | 5.3412 | 16.0855 | 18.1708 | 25.5973 | 30.9385 | 0.01
5.5315 | 7.8985 | 1.9844 | 1.9766 | 2.9219 | 2.9532 | 6.8829 | 4.9063 | 13.43 | 15.4066 | 22.2895 | 27.1958 | 5.5315 | 7.9085 | 1.9844 | 1.9766 | 2.9219 | 2.9532 | 6.8829 | 4.9063 | 13.44 | 15.4166 | 22.2995 | 27.2058 | 0.01
6.2875 | 8.0623 | 2.0096 | 2.0144 | 3.0479 | 3.0288 | 7.0719 | 5.0575 | 14.3498 | 16.3642 | 23.4361 | 28.4936 | 6.2875 | 8.0723 | 2.0096 | 2.0144 | 3.0479 | 3.0288 | 7.0719 | 5.0575 | 14.3598 | 16.3742 | 23.4461 | 28.5036 | 0.01
8.8478 | 8.617 | 2.0949 | 2.1424 | 3.4746 | 3.2848 | 7.7119 | 5.5696 | 17.4648 | 19.6072 | 27.3191 | 32.8887 | 8.8478 | 8.627 | 2.0949 | 2.1424 | 3.4746 | 3.2848 | 7.7119 | 5.5696 | 17.4748 | 19.6172 | 27.3291 | 32.8987 | 0.01
3.6485 | 7.4905 | 1.9216 | 1.8824 | 2.6081 | 2.7648 | 6.4121 | 4.5297 | 11.139 | 13.0214 | 19.4335 | 23.9632 | 3.6485 | 7.5005 | 1.9216 | 1.8824 | 2.6081 | 2.7648 | 6.4121 | 4.5297 | 11.149 | 13.0314 | 19.4435 | 23.9732 | 0.01
4.5406 | 7.6838 | 1.9514 | 1.927 | 2.7568 | 2.8541 | 6.6352 | 4.7081 | 12.2244 | 14.1515 | 20.7866 | 25.4947 | 4.5406 | 7.6938 | 1.9514 | 1.927 | 2.7568 | 2.8541 | 6.6352 | 4.7081 | 12.2344 | 14.1615 | 20.7966 | 25.5047 | 0.01
7.2969 | 8.281 | 2.0432 | 2.0648 | 3.2162 | 3.1297 | 7.3242 | 5.2594 | 15.5779 | 17.6428 | 24.967 | 30.2264 | 7.2969 | 8.291 | 2.0432 | 2.0648 | 3.2162 | 3.1297 | 7.3242 | 5.2594 | 15.5879 | 17.6528 | 24.977 | 30.2364 | 0.01
7.5894 | 8.3444 | 2.053 | 2.0795 | 3.2649 | 3.1589 | 7.3974 | 5.3179 | 15.9338 | 18.0133 | 25.4106 | 30.7285 | 7.5894 | 8.3544 | 2.053 | 2.0795 | 3.2649 | 3.1589 | 7.3974 | 5.3179 | 15.9438 | 18.0233 | 25.4206 | 30.7385 | 0.01
-1.186 | 6.443 | 1.7605 | 1.6407 | 1.8023 | 2.2814 | 5.2035 | 3.5628 | 5.257 | 6.8977 | 12.1012 | 15.664 | -1.186 | 6.453 | 1.7605 | 1.6407 | 1.8023 | 2.2814 | 5.2035 | 3.5628 | 5.267 | 6.9077 | 12.1112 | 15.674 | 0.01
7.5221 | 8.3298 | 2.0507 | 2.0761 | 3.2537 | 3.1522 | 7.3805 | 5.3044 | 15.8519 | 17.928 | 25.3085 | 30.6129 | 7.5221 | 8.3398 | 2.0507 | 2.0761 | 3.2537 | 3.1522 | 7.3805 | 5.3044 | 15.8619 | 17.938 | 25.3185 | 30.6229 | 0.01
4.1728 | 7.6041 | 1.9391 | 1.9086 | 2.6955 | 2.8173 | 6.5432 | 4.6346 | 11.7769 | 13.6856 | 20.2288 | 24.8633 | 4.1728 | 7.6141 | 1.9391 | 1.9086 | 2.6955 | 2.8173 | 6.5432 | 4.6346 | 11.7869 | 13.6956 | 20.2388 | 24.8733 | 0.01
10.0312 | 8.8734 | 2.1344 | 2.2016 | 3.6719 | 3.4031 | 8.0078 | 5.8062 | 18.9047 | 21.1062 | 29.114 | 34.9203 | 10.0312 | 8.8834 | 2.1344 | 2.2016 | 3.6719 | 3.4031 | 8.0078 | 5.8062 | 18.9147 | 21.1162 | 29.124 | 34.9303 | 0.01
1.8924 | 7.11 | 1.8631 | 1.7946 | 2.3154 | 2.5892 | 5.9731 | 4.1785 | 9.0025 | 10.7971 | 16.7702 | 20.9487 | 1.8924 | 7.12 | 1.8631 | 1.7946 | 2.3154 | 2.5892 | 5.9731 | 4.1785 | 9.0125 | 10.8071 | 16.7802 | 20.9587 | 0.01
16.936 | 10.3695 | 2.3645 | 2.5468 | 4.8227 | 4.0936 | 9.734 | 7.1872 | 27.3054 | 29.8522 | 39.5862 | 46.7734 | 16.936 | 10.3795 | 2.3645 | 2.5468 | 4.8227 | 4.0936 | 9.734 | 7.1872 | 27.3154 | 29.8622 | 39.5962 | 46.7834 | 0.01
7.2675 | 8.2746 | 2.0422 | 2.0634 | 3.2112 | 3.1267 | 7.3169 | 5.2535 | 15.5421 | 17.6055 | 24.9223 | 30.1758 | 7.2675 | 8.2846 | 2.0422 | 2.0634 | 3.2112 | 3.1267 | 7.3169 | 5.2535 | 15.5521 | 17.6155 | 24.9323 | 30.1858 | 0.01
5.0004 | 7.7834 | 1.9667 | 1.95 | 2.8334 | 2.9 | 6.7501 | 4.8001 | 12.7839 | 14.7339 | 21.484 | 26.2841 | 5.0004 | 7.7934 | 1.9667 | 1.95 | 2.8334 | 2.9 | 6.7501 | 4.8001 | 12.7939 | 14.7439 | 21.494 | 26.2941 | 0.01
8.22 | 8.481 | 2.074 | 2.111 | 3.37 | 3.222 | 7.555 | 5.444 | 16.7011 | 18.8121 | 26.3671 | 31.8111 | 8.22 | 8.491 | 2.074 | 2.111 | 3.37 | 3.222 | 7.555 | 5.444 | 16.7111 | 18.8221 | 26.3771 | 31.8211 | 0.01
15.5054 | 10.0595 | 2.3168 | 2.4753 | 4.5842 | 3.9505 | 9.3763 | 6.9011 | 25.5649 | 28.0401 | 37.4165 | 44.3175 | 15.5054 | 10.0695 | 2.3168 | 2.4753 | 4.5842 | 3.9505 | 9.3763 | 6.9011 | 25.5749 | 28.0501 | 37.4265 | 44.3275 | 0.01
1.1288 | 6.9446 | 1.8376 | 1.7564 | 2.1881 | 2.5129 | 5.7822 | 4.0258 | 8.0734 | 9.8299 | 15.6121 | 19.6378 | 1.1288 | 6.9546 | 1.8376 | 1.7564 | 2.1881 | 2.5129 | 5.7822 | 4.0258 | 8.0834 | 9.8399 | 15.6221 | 19.6478 | 0.01
0.42329 | 6.7917 | 1.8141 | 1.7212 | 2.0705 | 2.4423 | 5.6058 | 3.8847 | 7.215 | 8.9362 | 14.542 | 18.4267 | 0.42329 | 6.8017 | 1.8141 | 1.7212 | 2.0705 | 2.4423 | 5.6058 | 3.8847 | 7.225 | 8.9462 | 14.552 | 18.4367 | 0.01
6.5131 | 8.1112 | 2.0171 | 2.0257 | 3.0855 | 3.0513 | 7.1283 | 5.1026 | 14.6242 | 16.6499 | 23.7781 | 28.8807 | 6.5131 | 8.1212 | 2.0171 | 2.0257 | 3.0855 | 3.0513 | 7.1283 | 5.1026 | 14.6342 | 16.6599 | 23.7881 | 28.8907 | 0.01
-0.42709 | 6.6075 | 1.7858 | 1.6786 | 1.9288 | 2.3573 | 5.3932 | 3.7146 | 6.1804 | 7.859 | 13.2522 | 16.9668 | -0.42709 | 6.6175 | 1.7858 | 1.6786 | 1.9288 | 2.3573 | 5.3932 | 3.7146 | 6.1904 | 7.869 | 13.2622 | 16.9768 | 0.01
3.3855 | 7.4335 | 1.9129 | 1.8693 | 2.5643 | 2.7386 | 6.3464 | 4.4771 | 10.8191 | 12.6883 | 19.0347 | 23.5118 | 3.3855 | 7.4435 | 1.9129 | 1.8693 | 2.5643 | 2.7386 | 6.3464 | 4.4771 | 10.8291 | 12.6983 | 19.0447 | 23.5218 | 0.01
9.2592 | 8.7062 | 2.1086 | 2.163 | 3.5432 | 3.3259 | 7.8148 | 5.6518 | 17.9653 | 20.1283 | 27.9431 | 33.5949 | 9.2592 | 8.7162 | 2.1086 | 2.163 | 3.5432 | 3.3259 | 7.8148 | 5.6518 | 17.9753 | 20.1383 | 27.9531 | 33.6049 | 0.01
0.34898 | 6.7756 | 1.8116 | 1.7174 | 2.0582 | 2.4349 | 5.5872 | 3.8698 | 7.1246 | 8.842 | 14.4293 | 18.2991 | 0.34898 | 6.7856 | 1.8116 | 1.7174 | 2.0582 | 2.4349 | 5.5872 | 3.8698 | 7.1346 | 8.852 | 14.4393 | 18.3091 | 0.01
14.8692 | 9.9217 | 2.2956 | 2.4435 | 4.4782 | 3.8869 | 9.2173 | 6.7738 | 24.7908 | 27.2343 | 36.4516 | 43.2254 | 14.8692 | 9.9317 | 2.2956 | 2.4435 | 4.4782 | 3.8869 | 9.2173 | 6.7738 | 24.8008 | 27.2443 | 36.4616 | 43.2354 | 0.01
14.2324 | 9.7837 | 2.2744 | 2.4116 | 4.3721 | 3.8232 | 9.0581 | 6.6465 | 24.0161 | 26.4277 | 35.4858 | 42.1323 | 14.2324 | 9.7937 | 2.2744 | 2.4116 | 4.3721 | 3.8232 | 9.0581 | 6.6465 | 24.0261 | 26.4377 | 35.4958 | 42.1423 | 0.01
-3.7799 | 5.881 | 1.674 | 1.511 | 1.37 | 2.022 | 4.555 | 3.044 | 2.1012 | 3.6122 | 8.1672 | 11.2112 | -3.7799 | 5.891 | 1.674 | 1.511 | 1.37 | 2.022 | 4.555 | 3.044 | 2.1112 | 3.6222 | 8.1772 | 11.2212 | 0.01
5.3413 | 7.8573 | 1.978 | 1.9671 | 2.8902 | 2.9341 | 6.8353 | 4.8683 | 13.1986 | 15.1657 | 22.001 | 26.8693 | 5.3413 | 7.8673 | 1.978 | 1.9671 | 2.8902 | 2.9341 | 6.8353 | 4.8683 | 13.2086 | 15.1757 | 22.011 | 26.8793 | 0.01
13.6643 | 9.6606 | 2.2555 | 2.3832 | 4.2774 | 3.7664 | 8.9161 | 6.5329 | 23.3249 | 25.7081 | 34.6242 | 41.157 | 13.6643 | 9.6706 | 2.2555 | 2.3832 | 4.2774 | 3.7664 | 8.9161 | 6.5329 | 23.3349 | 25.7181 | 34.6342 | 41.167 | 0.01
17.2063 | 10.428 | 2.3735 | 2.5603 | 4.8677 | 4.1206 | 9.8016 | 7.2413 | 27.6343 | 30.1946 | 39.9962 | 47.2374 | 17.2063 | 10.438 | 2.3735 | 2.5603 | 4.8677 | 4.1206 | 9.8016 | 7.2413 | 27.6443 | 30.2046 | 40.0062 | 47.2474 | 0.01
8.2493 | 8.4874 | 2.075 | 2.1125 | 3.3749 | 3.2249 | 7.5623 | 5.4499 | 16.7367 | 18.8491 | 26.4115 | 31.8613 | 8.2493 | 8.4974 | 2.075 | 2.1125 | 3.3749 | 3.2249 | 7.5623 | 5.4499 | 16.7467 | 18.8591 | 26.4215 | 31.8713 | 0.01
5.4441 | 7.8796 | 1.9815 | 1.9722 | 2.9074 | 2.9444 | 6.861 | 4.8888 | 13.3237 | 15.2959 | 22.1569 | 27.0457 | 5.4441 | 7.8896 | 1.9815 | 1.9722 | 2.9074 | 2.9444 | 6.861 | 4.8888 | 13.3337 | 15.3059 | 22.1669 | 27.0557 | 0.01
0.4585 | 6.7993 | 1.8153 | 1.7229 | 2.0764 | 2.4459 | 5.6146 | 3.8917 | 7.2578 | 8.9808 | 14.5954 | 18.4871 | 0.4585 | 6.8093 | 1.8153 | 1.7229 | 2.0764 | 2.4459 | 5.6146 | 3.8917 | 7.2678 | 8.9908 | 14.6054 | 18.4971 | 0.01
-0.038013 | 6.6918 | 1.7987 | 1.6981 | 1.9937 | 2.3962 | 5.4905 | 3.7924 | 6.6538 | 8.3519 | 13.8423 | 17.6347 | -0.038013 | 6.7018 | 1.7987 | 1.6981 | 1.9937 | 2.3962 | 5.4905 | 3.7924 | 6.6638 | 8.3619 | 13.8523 | 17.6447 | 0.01
11.8839 | 9.2749 | 2.1961 | 2.2942 | 3.9807 | 3.5884 | 8.471 | 6.1768 | 21.1588 | 23.453 | 31.924 | 38.1008 | 11.8839 | 9.2849 | 2.1961 | 2.2942 | 3.9807 | 3.5884 | 8.471 | 6.1768 | 21.1688 | 23.463 | 31.934 | 38.1108 | 0.01
-3.1106 | 6.026 | 1.6963 | 1.5445 | 1.4816 | 2.0889 | 4.7224 | 3.1779 | 2.9155 | 4.4599 | 9.1823 | 12.3602 | -3.1106 | 6.036 | 1.6963 | 1.5445 | 1.4816 | 2.0889 | 4.7224 | 3.1779 | 2.9255 | 4.4699 | 9.1923 | 12.3702 | 0.01
2.154 | 7.1667 | 1.8718 | 1.8077 | 2.359 | 2.6154 | 6.0385 | 4.2308 | 9.3207 | 11.1284 | 17.1669 | 21.3977 | 2.154 | 7.1767 | 1.8718 | 1.8077 | 2.359 | 2.6154 | 6.0385 | 4.2308 | 9.3307 | 11.1384 | 17.1769 | 21.4077 | 0.01
7.67 | 8.3618 | 2.0557 | 2.0835 | 3.2783 | 3.167 | 7.4175 | 5.334 | 16.0319 | 18.1154 | 25.5329 | 30.8669 | 7.67 | 8.3718 | 2.0557 | 2.0835 | 3.2783 | 3.167 | 7.4175 | 5.334 | 16.0419 | 18.1254 | 25.5429 | 30.8769 | 0.01
15.8604 | 10.1364 | 2.3287 | 2.493 | 4.6434 | 3.986 | 9.4651 | 6.9721 | 25.9968 | 28.4898 | 37.9549 | 44.927 | 15.8604 | 10.1464 | 2.3287 | 2.493 | 4.6434 | 3.986 | 9.4651 | 6.9721 | 26.0068 | 28.4998 | 37.9649 | 44.937 | 0.01
-1.0877 | 6.4643 | 1.7637 | 1.6456 | 1.8187 | 2.2912 | 5.2281 | 3.5825 | 5.3766 | 7.0222 | 12.2503 | 15.8327 | -1.0877 | 6.4743 | 1.7637 | 1.6456 | 1.8187 | 2.2912 | 5.2281 | 3.5825 | 5.3866 | 7.0322 | 12.2603 | 15.8427 | 0.01
9.5656 | 8.7725 | 2.1189 | 2.1783 | 3.5943 | 3.3566 | 7.8914 | 5.7131 | 18.3381 | 20.5164 | 28.4078 | 34.1209 | 9.5656 | 8.7825 | 2.1189 | 2.1783 | 3.5943 | 3.3566 | 7.8914 | 5.7131 | 18.3481 | 20.5264 | 28.4178 | 34.1309 | 0.01
5.2751 | 7.8429 | 1.9758 | 1.9638 | 2.8792 | 2.9275 | 6.8188 | 4.855 | 13.1181 | 15.0818 | 21.9006 | 26.7557 | 5.2751 | 7.8529 | 1.9758 | 1.9638 | 2.8792 | 2.9275 | 6.8188 | 4.855 | 13.1281 | 15.0918 | 21.9106 | 26.7657 | 0.01
4.8547 | 7.7519 | 1.9618 | 1.9427 | 2.8091 | 2.8855 | 6.7137 | 4.7709 | 12.6066 | 14.5493 | 21.263 | 26.0339 | 4.8547 | 7.7619 | 1.9618 | 1.9427 | 2.8091 | 2.8855 | 6.7137 | 4.7709 | 12.6166 | 14.5593 | 21.273 | 26.0439 | 0.01
4.1225 | 7.5932 | 1.9374 | 1.9061 | 2.6871 | 2.8123 | 6.5306 | 4.6245 | 11.7157 | 13.6219 | 20.1525 | 24.777 | 4.1225 | 7.6032 | 1.9374 | 1.9061 | 2.6871 | 2.8123 | 6.5306 | 4.6245 | 11.7257 | 13.6319 | 20.1625 | 24.787 | 0.01
0.12817 | 6.7278 | 1.8043 | 1.7064 | 2.0214 | 2.4128 | 5.532 | 3.8256 | 6.8559 | 8.5623 | 14.0944 | 17.92 | 0.12817 | 6.7378 | 1.8043 | 1.7064 | 2.0214 | 2.4128 | 5.532 | 3.8256 | 6.8659 | 8.5723 | 14.1044 | 17.93 | 0.01
3.1497 | 7.3824 | 1.905 | 1.8575 | 2.525 | 2.715 | 6.2874 | 4.4299 | 10.5322 | 12.3897 | 18.6771 | 23.107 | 3.1497 | 7.3924 | 1.905 | 1.8575 | 2.525 | 2.715 | 6.2874 | 4.4299 | 10.5422 | 12.3997 | 18.6871 | 23.117 | 0.01
0.004088 | 6.7009 | 1.8001 | 1.7002 | 2.0007 | 2.4004 | 5.501 | 3.8008 | 6.705 | 8.4052 | 13.9062 | 17.707 | 0.004088 | 6.7109 | 1.8001 | 1.7002 | 2.0007 | 2.4004 | 5.501 | 3.8008 | 6.715 | 8.4152 | 13.9162 | 17.717 | 0.01
2.664 | 7.2772 | 1.8888 | 1.8332 | 2.444 | 2.6664 | 6.166 | 4.3328 | 9.9412 | 11.7744 | 17.9403 | 22.2731 | 2.664 | 7.2872 | 1.8888 | 1.8332 | 2.444 | 2.6664 | 6.166 | 4.3328 | 9.9512 | 11.7844 | 17.9503 | 22.2831 | 0.01
16.3601 | 10.2447 | 2.3453 | 2.518 | 4.7267 | 4.036 | 9.59 | 7.072 | 26.6047 | 29.1227 | 38.7127 | 45.7848 | 16.3601 | 10.2547 | 2.3453 | 2.518 | 4.7267 | 4.036 | 9.59 | 7.072 | 26.6147 | 29.1327 | 38.7227 | 45.7948 | 0.01
1.1157 | 6.9417 | 1.8372 | 1.7558 | 2.186 | 2.5116 | 5.7789 | 4.0231 | 8.0575 | 9.8133 | 15.5922 | 19.6153 | 1.1157 | 6.9517 | 1.8372 | 1.7558 | 2.186 | 2.5116 | 5.7789 | 4.0231 | 8.0675 | 9.8233 | 15.6022 | 19.6253 | 0.01
8.3578 | 8.5109 | 2.0786 | 2.1179 | 3.393 | 3.2358 | 7.5894 | 5.4716 | 16.8686 | 18.9865 | 26.576 | 32.0475 | 8.3578 | 8.5209 | 2.0786 | 2.1179 | 3.393 | 3.2358 | 7.5894 | 5.4716 | 16.8786 | 18.9965 | 26.586 | 32.0575 | 0.01
-3.237 | 5.9986 | 1.6921 | 1.5381 | 1.4605 | 2.0763 | 4.6907 | 3.1526 | 2.7616 | 4.2998 | 8.9905 | 12.1431 | -3.237 | 6.0086 | 1.6921 | 1.5381 | 1.4605 | 2.0763 | 4.6907 | 3.1526 | 2.7716 | 4.3098 | 9.0005 | 12.1531 | 0.01
3.8189 | 7.5274 | 1.9273 | 1.8909 | 2.6365 | 2.7819 | 6.4547 | 4.5638 | 11.3463 | 13.2373 | 19.692 | 24.2558 | 3.8189 | 7.5374 | 1.9273 | 1.8909 | 2.6365 | 2.7819 | 6.4547 | 4.5638 | 11.3563 | 13.2473 | 19.702 | 24.2658 | 0.01
9.7219 | 8.8064 | 2.1241 | 2.1861 | 3.6203 | 3.3722 | 7.9305 | 5.7444 | 18.5283 | 20.7144 | 28.6448 | 34.3892 | 9.7219 | 8.8164 | 2.1241 | 2.1861 | 3.6203 | 3.3722 | 7.9305 | 5.7444 | 18.5383 | 20.7244 | 28.6548 | 34.3992 | 0.01
8.9915 | 8.6482 | 2.0997 | 2.1496 | 3.4986 | 3.2992 | 7.7479 | 5.5983 | 17.6397 | 19.7893 | 27.5372 | 33.1355 | 8.9915 | 8.6582 | 2.0997 | 2.1496 | 3.4986 | 3.2992 | 7.7479 | 5.5983 | 17.6497 | 19.7993 | 27.5472 | 33.1455 | 0.01
-3.6954 | 5.8993 | 1.6768 | 1.5152 | 1.3841 | 2.0305 | 4.5762 | 3.0609 | 2.2039 | 3.7192 | 8.2953 | 11.3562 | -3.6954 | 5.9093 | 1.6768 | 1.5152 | 1.3841 | 2.0305 | 4.5762 | 3.0609 | 2.2139 | 3.7292 | 8.3053 | 11.3662 | 0.01
10.0738 | 8.8827 | 2.1358 | 2.2037 | 3.679 | 3.4074 | 8.0185 | 5.8148 | 18.9565 | 21.1602 | 29.1787 | 34.9934 | 10.0738 | 8.8927 | 2.1358 | 2.2037 | 3.679 | 3.4074 | 8.0185 | 5.8148 | 18.9665 | 21.1702 | 29.1887 | 35.0034 | 0.01
0.046038 | 6.71 | 1.8015 | 1.7023 | 2.0077 | 2.4046 | 5.5115 | 3.8092 | 6.756 | 8.4583 | 13.9698 | 17.779 | 0.046038 | 6.72 | 1.8015 | 1.7023 | 2.0077 | 2.4046 | 5.5115 | 3.8092 | 6.766 | 8.4683 | 13.9798 | 17.789 | 0.01
11.9431 | 9.2877 | 2.1981 | 2.2972 | 3.9905 | 3.5943 | 8.4858 | 6.1886 | 21.2308 | 23.528 | 32.0138 | 38.2024 | 11.9431 | 9.2977 | 2.1981 | 2.2972 | 3.9905 | 3.5943 | 8.4858 | 6.1886 | 21.2408 | 23.538 | 32.0238 | 38.2124 | 0.01
10.2351 | 8.9176 | 2.1412 | 2.2118 | 3.7058 | 3.4235 | 8.0588 | 5.847 | 19.1527 | 21.3645 | 29.4232 | 35.2703 | 10.2351 | 8.9276 | 2.1412 | 2.2118 | 3.7058 | 3.4235 | 8.0588 | 5.847 | 19.1627 | 21.3745 | 29.4332 | 35.2803 | 0.01
16.0073 | 10.1682 | 2.3336 | 2.5004 | 4.6679 | 4.0007 | 9.5018 | 7.0015 | 26.1755 | 28.6759 | 38.1777 | 45.1791 | 16.0073 | 10.1782 | 2.3336 | 2.5004 | 4.6679 | 4.0007 | 9.5018 | 7.0015 | 26.1855 | 28.6859 | 38.1877 | 45.1891 | 0.01
11.2117 | 9.1292 | 2.1737 | 2.2606 | 3.8686 | 3.5212 | 8.3029 | 6.0423 | 20.3409 | 22.6015 | 30.9044 | 36.9468 | 11.2117 | 9.1392 | 2.1737 | 2.2606 | 3.8686 | 3.5212 | 8.3029 | 6.0423 | 20.3509 | 22.6115 | 30.9144 | 36.9568 | 0.01
0.7651 | 6.8658 | 1.8255 | 1.7383 | 2.1275 | 2.4765 | 5.6913 | 3.953 | 7.6309 | 9.3691 | 15.0604 | 19.0134 | 0.7651 | 6.8758 | 1.8255 | 1.7383 | 2.1275 | 2.4765 | 5.6913 | 3.953 | 7.6409 | 9.3791 | 15.0704 | 19.0234 | 0.01
-2.5424 | 6.1491 | 1.7153 | 1.5729 | 1.5763 | 2.1458 | 4.8644 | 3.2915 | 3.6068 | 5.1796 | 10.044 | 13.3356 | -2.5424 | 6.1591 | 1.7153 | 1.5729 | 1.5763 | 2.1458 | 4.8644 | 3.2915 | 3.6168 | 5.1896 | 10.054 | 13.3456 | 0.01
6.6128 | 8.1328 | 2.0204 | 2.0306 | 3.1021 | 3.0613 | 7.1532 | 5.1226 | 14.7456 | 16.7763 | 23.9295 | 29.052 | 6.6128 | 8.1428 | 2.0204 | 2.0306 | 3.1021 | 3.0613 | 7.1532 | 5.1226 | 14.7556 | 16.7863 | 23.9395 | 29.062 | 0.01
-0.13011 | 6.6718 | 1.7957 | 1.6935 | 1.9783 | 2.387 | 5.4675 | 3.774 | 6.5417 | 8.2352 | 13.7027 | 17.4766 | -0.13011 | 6.6818 | 1.7957 | 1.6935 | 1.9783 | 2.387 | 5.4675 | 3.774 | 6.5517 | 8.2452 | 13.7127 | 17.4866 | 0.01
2.5146 | 7.2448 | 1.8838 | 1.8257 | 2.4191 | 2.6515 | 6.1286 | 4.3029 | 9.7594 | 11.5851 | 17.7138 | 22.0167 | 2.5146 | 7.2548 | 1.8838 | 1.8257 | 2.4191 | 2.6515 | 6.1286 | 4.3029 | 9.7694 | 11.5951 | 17.7238 | 22.0267 | 0.01
14.496 | 9.8408 | 2.2832 | 2.4248 | 4.416 | 3.8496 | 9.124 | 6.6992 | 24.3368 | 26.7616 | 35.8856 | 42.5848 | 14.496 | 9.8508 | 2.2832 | 2.4248 | 4.416 | 3.8496 | 9.124 | 6.6992 | 24.3468 | 26.7716 | 35.8956 | 42.5948 | 0.01
6.3767 | 8.0816 | 2.0126 | 2.0188 | 3.0628 | 3.0377 | 7.0942 | 5.0753 | 14.4583 | 16.4771 | 23.5713 | 28.6466 | 6.3767 | 8.0916 | 2.0126 | 2.0188 | 3.0628 | 3.0377 | 7.0942 | 5.0753 | 14.4683 | 16.4871 | 23.5813 | 28.6566 | 0.01
-0.66363 | 6.5562 | 1.7779 | 1.6668 | 1.8894 | 2.3336 | 5.3341 | 3.6673 | 5.8926 | 7.5594 | 12.8935 | 16.5608 | -0.66363 | 6.5662 | 1.7779 | 1.6668 | 1.8894 | 2.3336 | 5.3341 | 3.6673 | 5.9026 | 7.5694 | 12.9035 | 16.5708 | 0.01
6.6236 | 8.1351 | 2.0208 | 2.0312 | 3.1039 | 3.0624 | 7.1559 | 5.1247 | 14.7587 | 16.7899 | 23.9458 | 29.0705 | 6.6236 | 8.1451 | 2.0208 | 2.0312 | 3.1039 | 3.0624 | 7.1559 | 5.1247 | 14.7687 | 16.7999 | 23.9558 | 29.0805 | 0.01
-1.4404 | 6.3879 | 1.752 | 1.628 | 1.7599 | 2.256 | 5.1399 | 3.5119 | 4.9476 | 6.5755 | 11.7155 | 15.2274 | -1.4404 | 6.3979 | 1.752 | 1.628 | 1.7599 | 2.256 | 5.1399 | 3.5119 | 4.9576 | 6.5855 | 11.7255 | 15.2374 | 0.01
3.8707 | 7.5386 | 1.929 | 1.8935 | 2.6451 | 2.7871 | 6.4677 | 4.5741 | 11.4093 | 13.3029 | 19.7705 | 24.3447 | 3.8707 | 7.5486 | 1.929 | 1.8935 | 2.6451 | 2.7871 | 6.4677 | 4.5741 | 11.4193 | 13.3129 | 19.7805 | 24.3547 | 0.01
-11.3239 | 4.2465 | 1.4225 | 1.1338 | 0.11268 | 1.2676 | 2.669 | 1.5352 | -7.0774 | -5.9436 | -3.2746 | -1.7394 | -11.3239 | 4.2565 | 1.4225 | 1.1338 | 0.11268 | 1.2676 | 2.669 | 1.5352 | -7.0674 | -5.9336 | -3.2646 | -1.7294 | 0.01
8.374 | 8.5144 | 2.0791 | 2.1187 | 3.3957 | 3.2374 | 7.5935 | 5.4748 | 16.8884 | 19.0071 | 26.6006 | 32.0754 | 8.374 | 8.5244 | 2.0791 | 2.1187 | 3.3957 | 3.2374 | 7.5935 | 5.4748 | 16.8984 | 19.0171 | 26.6106 | 32.0854 | 0.01
12.9704 | 9.5102 | 2.2323 | 2.3485 | 4.1617 | 3.697 | 8.7426 | 6.3941 | 22.4806 | 24.8291 | 33.5717 | 39.9658 | 12.9704 | 9.5202 | 2.2323 | 2.3485 | 4.1617 | 3.697 | 8.7426 | 6.3941 | 22.4906 | 24.8391 | 33.5817 | 39.9758 | 0.01
1.7719 | 7.0839 | 1.8591 | 1.7886 | 2.2953 | 2.5772 | 5.943 | 4.1544 | 8.8558 | 10.6444 | 16.5874 | 20.7418 | 1.7719 | 7.0939 | 1.8591 | 1.7886 | 2.2953 | 2.5772 | 5.943 | 4.1544 | 8.8658 | 10.6544 | 16.5974 | 20.7518 | 0.01
-0.26064 | 6.6435 | 1.7913 | 1.687 | 1.9566 | 2.3739 | 5.4348 | 3.7479 | 6.3829 | 8.0699 | 13.5047 | 17.2526 | -0.26064 | 6.6535 | 1.7913 | 1.687 | 1.9566 | 2.3739 | 5.4348 | 3.7479 | 6.3929 | 8.0799 | 13.5147 | 17.2626 | 0.01
8.9346 | 8.6358 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7336 | 5.5869 | 17.5704 | 19.7171 | 27.4507 | 33.0376 | 8.9346 | 8.6458 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7336 | 5.5869 | 17.5804 | 19.7271 | 27.4607 | 33.0476 | 0.01
8.9889 | 8.6476 | 2.0996 | 2.1494 | 3.4981 | 3.2989 | 7.7472 | 5.5978 | 17.6365 | 19.7859 | 27.5332 | 33.1309 | 8.9889 | 8.6576 | 2.0996 | 2.1494 | 3.4981 | 3.2989 | 7.7472 | 5.5978 | 17.6465 | 19.7959 | 27.5432 | 33.1409 | 0.01
5.2835 | 7.8448 | 1.9761 | 1.9642 | 2.8806 | 2.9284 | 6.8209 | 4.8567 | 13.1283 | 15.0925 | 21.9133 | 26.77 | 5.2835 | 7.8548 | 1.9761 | 1.9642 | 2.8806 | 2.9284 | 6.8209 | 4.8567 | 13.1383 | 15.1025 | 21.9233 | 26.78 | 0.01
9.4524 | 8.748 | 2.1151 | 2.1726 | 3.5754 | 3.3452 | 7.8631 | 5.6905 | 18.2004 | 20.373 | 28.2361 | 33.9266 | 9.4524 | 8.758 | 2.1151 | 2.1726 | 3.5754 | 3.3452 | 7.8631 | 5.6905 | 18.2104 | 20.383 | 28.2461 | 33.9366 | 0.01
12.1174 | 9.3254 | 2.2039 | 2.3059 | 4.0196 | 3.6117 | 8.5294 | 6.2235 | 21.4429 | 23.7487 | 32.2781 | 38.5016 | 12.1174 | 9.3354 | 2.2039 | 2.3059 | 4.0196 | 3.6117 | 8.5294 | 6.2235 | 21.4529 | 23.7587 | 32.2881 | 38.5116 | 0.01
2.5021 | 7.2421 | 1.8834 | 1.8251 | 2.417 | 2.6502 | 6.1255 | 4.3004 | 9.7443 | 11.5694 | 17.6949 | 21.9953 | 2.5021 | 7.2521 | 1.8834 | 1.8251 | 2.417 | 2.6502 | 6.1255 | 4.3004 | 9.7543 | 11.5794 | 17.7049 | 22.0053 | 0.01
0.91537 | 6.8983 | 1.8305 | 1.7458 | 2.1526 | 2.4915 | 5.7288 | 3.9831 | 7.8137 | 9.5595 | 15.2883 | 19.2714 | 0.91537 | 6.9083 | 1.8305 | 1.7458 | 2.1526 | 2.4915 | 5.7288 | 3.9831 | 7.8237 | 9.5695 | 15.2983 | 19.2814 | 0.01
-1.7202 | 6.3273 | 1.7427 | 1.614 | 1.7133 | 2.228 | 5.07 | 3.456 | 4.6071 | 6.2211 | 11.2911 | 14.7471 | -1.7202 | 6.3373 | 1.7427 | 1.614 | 1.7133 | 2.228 | 5.07 | 3.456 | 4.6171 | 6.2311 | 11.3011 | 14.7571 | 0.01
7.3217 | 8.2864 | 2.0441 | 2.0661 | 3.2203 | 3.1322 | 7.3304 | 5.2643 | 15.608 | 17.6741 | 25.0046 | 30.2689 | 7.3217 | 8.2964 | 2.0441 | 2.0661 | 3.2203 | 3.1322 | 7.3304 | 5.2643 | 15.618 | 17.6841 | 25.0146 | 30.2789 | 0.01
7.9757 | 8.4281 | 2.0659 | 2.0988 | 3.3293 | 3.1976 | 7.4939 | 5.3951 | 16.4037 | 18.5025 | 25.9965 | 31.3916 | 7.9757 | 8.4381 | 2.0659 | 2.0988 | 3.3293 | 3.1976 | 7.4939 | 5.3951 | 16.4137 | 18.5125 | 26.0065 | 31.4016 | 0.01
-2.8082 | 6.0916 | 1.7064 | 1.5596 | 1.532 | 2.1192 | 4.798 | 3.2384 | 3.2834 | 4.843 | 9.6409 | 12.8793 | -2.8082 | 6.1016 | 1.7064 | 1.5596 | 1.532 | 2.1192 | 4.798 | 3.2384 | 3.2934 | 4.853 | 9.6509 | 12.8893 | 0.01
-1.3037 | 6.4175 | 1.7565 | 1.6348 | 1.7827 | 2.2696 | 5.1741 | 3.5393 | 5.1139 | 6.7487 | 11.9228 | 15.462 | -1.3037 | 6.4275 | 1.7565 | 1.6348 | 1.7827 | 2.2696 | 5.1741 | 3.5393 | 5.1239 | 6.7587 | 11.9328 | 15.472 | 0.01
0.17091 | 6.737 | 1.8057 | 1.7085 | 2.0285 | 2.4171 | 5.5427 | 3.8342 | 6.9079 | 8.6165 | 14.1592 | 17.9934 | 0.17091 | 6.747 | 1.8057 | 1.7085 | 2.0285 | 2.4171 | 5.5427 | 3.8342 | 6.9179 | 8.6265 | 14.1692 | 18.0034 | 0.01
-7.6486 | 5.0428 | 1.545 | 1.3176 | 0.72523 | 1.6351 | 3.5878 | 2.2703 | -2.6058 | -1.2883 | 2.2996 | 4.5698 | -7.6486 | 5.0528 | 1.545 | 1.3176 | 0.72523 | 1.6351 | 3.5878 | 2.2703 | -2.5958 | -1.2783 | 2.3096 | 4.5798 | 0.01
7.5446 | 8.3347 | 2.0515 | 2.0772 | 3.2574 | 3.1545 | 7.3862 | 5.3089 | 15.8793 | 17.9565 | 25.3427 | 30.6516 | 7.5446 | 8.3447 | 2.0515 | 2.0772 | 3.2574 | 3.1545 | 7.3862 | 5.3089 | 15.8893 | 17.9665 | 25.3527 | 30.6616 | 0.01
9.7001 | 8.8017 | 2.1233 | 2.185 | 3.6167 | 3.37 | 7.925 | 5.74 | 18.5018 | 20.6869 | 28.6119 | 34.3519 | 9.7001 | 8.8117 | 2.1233 | 2.185 | 3.6167 | 3.37 | 7.925 | 5.74 | 18.5118 | 20.6969 | 28.6219 | 34.3619 | 0.01
8.0543 | 8.4451 | 2.0685 | 2.1027 | 3.3424 | 3.2054 | 7.5136 | 5.4109 | 16.4994 | 18.6021 | 26.1157 | 31.5266 | 8.0543 | 8.4551 | 2.0685 | 2.1027 | 3.3424 | 3.2054 | 7.5136 | 5.4109 | 16.5094 | 18.6121 | 26.1257 | 31.5366 | 0.01
-1.2755 | 6.4236 | 1.7575 | 1.6362 | 1.7874 | 2.2725 | 5.1811 | 3.5449 | 5.1482 | 6.7844 | 11.9655 | 15.5104 | -1.2755 | 6.4336 | 1.7575 | 1.6362 | 1.7874 | 2.2725 | 5.1811 | 3.5449 | 5.1582 | 6.7944 | 11.9755 | 15.5204 | 0.01
1.6532 | 7.0582 | 1.8551 | 1.7827 | 2.2755 | 2.5653 | 5.9133 | 4.1306 | 8.7114 | 10.494 | 16.4073 | 20.538 | 1.6532 | 7.0682 | 1.8551 | 1.7827 | 2.2755 | 2.5653 | 5.9133 | 4.1306 | 8.7214 | 10.504 | 16.4173 | 20.548 | 0.01
4.0014 | 7.567 | 1.9334 | 1.9001 | 2.6669 | 2.8001 | 6.5004 | 4.6003 | 11.5684 | 13.4685 | 19.9689 | 24.5692 | 4.0014 | 7.577 | 1.9334 | 1.9001 | 2.6669 | 2.8001 | 6.5004 | 4.6003 | 11.5784 | 13.4785 | 19.9789 | 24.5792 | 0.01
9.7211 | 8.8062 | 2.124 | 2.1861 | 3.6202 | 3.3721 | 7.9303 | 5.7442 | 18.5273 | 20.7134 | 28.6437 | 34.3879 | 9.7211 | 8.8162 | 2.124 | 2.1861 | 3.6202 | 3.3721 | 7.9303 | 5.7442 | 18.5373 | 20.7234 | 28.6537 | 34.3979 | 0.01
18.4405 | 10.6954 | 2.4147 | 2.622 | 5.0734 | 4.2441 | 10.1101 | 7.4881 | 29.136 | 31.758 | 41.8681 | 49.3562 | 18.4405 | 10.7054 | 2.4147 | 2.622 | 5.0734 | 4.2441 | 10.1101 | 7.4881 | 29.146 | 31.768 | 41.8781 | 49.3662 | 0.01
6.7586 | 8.1644 | 2.0253 | 2.0379 | 3.1264 | 3.0759 | 7.1896 | 5.1517 | 14.9229 | 16.9609 | 24.1505 | 29.3022 | 6.7586 | 8.1744 | 2.0253 | 2.0379 | 3.1264 | 3.0759 | 7.1896 | 5.1517 | 14.9329 | 16.9709 | 24.1605 | 29.3122 | 0.01
17.2651 | 10.4408 | 2.3755 | 2.5633 | 4.8775 | 4.1265 | 9.8163 | 7.253 | 27.7059 | 30.2692 | 40.0855 | 47.3385 | 17.2651 | 10.4508 | 2.3755 | 2.5633 | 4.8775 | 4.1265 | 9.8163 | 7.253 | 27.7159 | 30.2792 | 40.0955 | 47.3485 | 0.01
-4.1978 | 5.7905 | 1.6601 | 1.4901 | 1.3004 | 1.9802 | 4.4506 | 2.9604 | 1.5927 | 3.0828 | 7.5334 | 10.4938 | -4.1978 | 5.8005 | 1.6601 | 1.4901 | 1.3004 | 1.9802 | 4.4506 | 2.9604 | 1.6027 | 3.0928 | 7.5434 | 10.5038 | 0.01
7.4729 | 8.3191 | 2.0491 | 2.0736 | 3.2455 | 3.1473 | 7.3682 | 5.2946 | 15.7921 | 17.8657 | 25.2339 | 30.5285 | 7.4729 | 8.3291 | 2.0491 | 2.0736 | 3.2455 | 3.1473 | 7.3682 | 5.2946 | 15.8021 | 17.8757 | 25.2439 | 30.5385 | 0.01
-0.8847 | 6.5083 | 1.7705 | 1.6558 | 1.8525 | 2.3115 | 5.2788 | 3.6231 | 5.6236 | 7.2794 | 12.5582 | 16.1813 | -0.8847 | 6.5183 | 1.7705 | 1.6558 | 1.8525 | 2.3115 | 5.2788 | 3.6231 | 5.6336 | 7.2894 | 12.5682 | 16.1913 | 0.01
14.5788 | 9.8587 | 2.286 | 2.4289 | 4.4298 | 3.8579 | 9.1447 | 6.7158 | 24.4376 | 26.8665 | 36.0112 | 42.727 | 14.5788 | 9.8687 | 2.286 | 2.4289 | 4.4298 | 3.8579 | 9.1447 | 6.7158 | 24.4476 | 26.8765 | 36.0212 | 42.737 | 0.01
0.12537 | 6.7272 | 1.8042 | 1.7063 | 2.0209 | 2.4125 | 5.5313 | 3.8251 | 6.8525 | 8.5588 | 14.0901 | 17.9152 | 0.12537 | 6.7372 | 1.8042 | 1.7063 | 2.0209 | 2.4125 | 5.5313 | 3.8251 | 6.8625 | 8.5688 | 14.1001 | 17.9252 | 0.01
4.2245 | 7.6153 | 1.9408 | 1.9112 | 2.7041 | 2.8224 | 6.5561 | 4.6449 | 11.8398 | 13.751 | 20.3071 | 24.952 | 4.2245 | 7.6253 | 1.9408 | 1.9112 | 2.7041 | 2.8224 | 6.5561 | 4.6449 | 11.8498 | 13.761 | 20.3171 | 24.962 | 0.01
15.0219 | 9.9547 | 2.3007 | 2.4511 | 4.5036 | 3.9022 | 9.2555 | 6.8044 | 24.9766 | 27.4277 | 36.6832 | 43.4875 | 15.0219 | 9.9647 | 2.3007 | 2.4511 | 4.5036 | 3.9022 | 9.2555 | 6.8044 | 24.9866 | 27.4377 | 36.6932 | 43.4975 | 0.01
-2.3623 | 6.1882 | 1.7213 | 1.5819 | 1.6063 | 2.1638 | 4.9094 | 3.3275 | 3.8258 | 5.4077 | 10.3171 | 13.6446 | -2.3623 | 6.1982 | 1.7213 | 1.5819 | 1.6063 | 2.1638 | 4.9094 | 3.3275 | 3.8358 | 5.4177 | 10.3271 | 13.6546 | 0.01
-0.42982 | 6.6069 | 1.7857 | 1.6785 | 1.9284 | 2.357 | 5.3925 | 3.714 | 6.177 | 7.8556 | 13.2481 | 16.9621 | -0.42982 | 6.6169 | 1.7857 | 1.6785 | 1.9284 | 2.357 | 5.3925 | 3.714 | 6.187 | 7.8656 | 13.2581 | 16.9721 | 0.01
7.7003 | 8.3684 | 2.0567 | 2.085 | 3.2834 | 3.17 | 7.4251 | 5.3401 | 16.0687 | 18.1537 | 25.5788 | 30.9188 | 7.7003 | 8.3784 | 2.0567 | 2.085 | 3.2834 | 3.17 | 7.4251 | 5.3401 | 16.0787 | 18.1637 | 25.5888 | 30.9288 | 0.01
5.0337 | 7.7906 | 1.9678 | 1.9517 | 2.839 | 2.9034 | 6.7584 | 4.8067 | 12.8244 | 14.776 | 21.5345 | 26.3412 | 5.0337 | 7.8006 | 1.9678 | 1.9517 | 2.839 | 2.9034 | 6.7584 | 4.8067 | 12.8344 | 14.786 | 21.5445 | 26.3512 | 0.01
3.2793 | 7.4105 | 1.9093 | 1.864 | 2.5465 | 2.7279 | 6.3198 | 4.4559 | 10.6898 | 12.5538 | 18.8736 | 23.3294 | 3.2793 | 7.4205 | 1.9093 | 1.864 | 2.5465 | 2.7279 | 6.3198 | 4.4559 | 10.6998 | 12.5638 | 18.8836 | 23.3394 | 0.01
-0.40881 | 6.6114 | 1.7864 | 1.6796 | 1.9319 | 2.3591 | 5.3978 | 3.7182 | 6.2026 | 7.8822 | 13.28 | 16.9982 | -0.40881 | 6.6214 | 1.7864 | 1.6796 | 1.9319 | 2.3591 | 5.3978 | 3.7182 | 6.2126 | 7.8922 | 13.29 | 17.0082 | 0.01
12.3703 | 9.3802 | 2.2123 | 2.3185 | 4.0617 | 3.637 | 8.5926 | 6.2741 | 21.7505 | 24.069 | 32.6616 | 38.9356 | 12.3703 | 9.3902 | 2.2123 | 2.3185 | 4.0617 | 3.637 | 8.5926 | 6.2741 | 21.7605 | 24.079 | 32.6716 | 38.9456 | 0.01
9.2318 | 8.7002 | 2.1077 | 2.1616 | 3.5386 | 3.3232 | 7.8079 | 5.6464 | 17.932 | 20.0936 | 27.9015 | 33.5479 | 9.2318 | 8.7102 | 2.1077 | 2.1616 | 3.5386 | 3.3232 | 7.8079 | 5.6464 | 17.942 | 20.1036 | 27.9115 | 33.5579 | 0.01
9.9205 | 8.8494 | 2.1307 | 2.196 | 3.6534 | 3.392 | 7.9801 | 5.7841 | 18.7699 | 20.9659 | 28.946 | 34.7301 | 9.9205 | 8.8594 | 2.1307 | 2.196 | 3.6534 | 3.392 | 7.9801 | 5.7841 | 18.7799 | 20.9759 | 28.956 | 34.7401 | 0.01
12.8623 | 9.4868 | 2.2287 | 2.3431 | 4.1437 | 3.6862 | 8.7156 | 6.3725 | 22.3491 | 24.6922 | 33.4078 | 39.7802 | 12.8623 | 9.4968 | 2.2287 | 2.3431 | 4.1437 | 3.6862 | 8.7156 | 6.3725 | 22.3591 | 24.7022 | 33.4178 | 39.7902 | 0.01
-2.6898 | 6.1172 | 1.7103 | 1.5655 | 1.5517 | 2.131 | 4.8276 | 3.262 | 3.4274 | 4.9929 | 9.8205 | 13.0825 | -2.6898 | 6.1272 | 1.7103 | 1.5655 | 1.5517 | 2.131 | 4.8276 | 3.262 | 3.4374 | 5.0029 | 9.8305 | 13.0925 | 0.01
10.976 | 9.0781 | 2.1659 | 2.2488 | 3.8293 | 3.4976 | 8.244 | 5.9952 | 20.0542 | 22.303 | 30.547 | 36.5422 | 10.976 | 9.0881 | 2.1659 | 2.2488 | 3.8293 | 3.4976 | 8.244 | 5.9952 | 20.0642 | 22.313 | 30.557 | 36.5522 | 0.01
6.1885 | 8.0408 | 2.0063 | 2.0094 | 3.0314 | 3.0189 | 7.0471 | 5.0377 | 14.2294 | 16.2388 | 23.2859 | 28.3237 | 6.1885 | 8.0508 | 2.0063 | 2.0094 | 3.0314 | 3.0189 | 7.0471 | 5.0377 | 14.2394 | 16.2488 | 23.2959 | 28.3337 | 0.01
-0.0097864 | 6.6979 | 1.7997 | 1.6995 | 1.9984 | 2.399 | 5.4976 | 3.798 | 6.6881 | 8.3876 | 13.8852 | 17.6832 | -0.0097864 | 6.7079 | 1.7997 | 1.6995 | 1.9984 | 2.399 | 5.4976 | 3.798 | 6.6981 | 8.3976 | 13.8952 | 17.6932 | 0.01
13.3212 | 9.5863 | 2.244 | 2.3661 | 4.2202 | 3.7321 | 8.8303 | 6.4642 | 22.9074 | 25.2735 | 34.1038 | 40.568 | 13.3212 | 9.5963 | 2.244 | 2.3661 | 4.2202 | 3.7321 | 8.8303 | 6.4642 | 22.9174 | 25.2835 | 34.1138 | 40.578 | 0.01
-0.72099 | 6.5438 | 1.776 | 1.664 | 1.8798 | 2.3279 | 5.3198 | 3.6558 | 5.8228 | 7.4867 | 12.8065 | 16.4623 | -0.72099 | 6.5538 | 1.776 | 1.664 | 1.8798 | 2.3279 | 5.3198 | 3.6558 | 5.8328 | 7.4967 | 12.8165 | 16.4723 | 0.01
-0.99952 | 6.4834 | 1.7667 | 1.65 | 1.8334 | 2.3 | 5.2501 | 3.6001 | 5.4839 | 7.1339 | 12.3841 | 15.9842 | -0.99952 | 6.4934 | 1.7667 | 1.65 | 1.8334 | 2.3 | 5.2501 | 3.6001 | 5.4939 | 7.1439 | 12.3941 | 15.9942 | 0.01
1.5168 | 7.0286 | 1.8506 | 1.7758 | 2.2528 | 2.5517 | 5.8792 | 4.1034 | 8.5455 | 10.3213 | 16.2005 | 20.3039 | 1.5168 | 7.0386 | 1.8506 | 1.7758 | 2.2528 | 2.5517 | 5.8792 | 4.1034 | 8.5555 | 10.3313 | 16.2105 | 20.3139 | 0.01
-0.58033 | 6.5743 | 1.7807 | 1.671 | 1.9033 | 2.342 | 5.3549 | 3.6839 | 5.9939 | 7.6649 | 13.0198 | 16.7038 | -0.58033 | 6.5843 | 1.7807 | 1.671 | 1.9033 | 2.342 | 5.3549 | 3.6839 | 6.0039 | 7.6749 | 13.0298 | 16.7138 | 0.01
0.17113 | 6.7371 | 1.8057 | 1.7086 | 2.0285 | 2.4171 | 5.5428 | 3.8342 | 6.9082 | 8.6168 | 14.1595 | 17.9938 | 0.17113 | 6.7471 | 1.8057 | 1.7086 | 2.0285 | 2.4171 | 5.5428 | 3.8342 | 6.9182 | 8.6268 | 14.1695 | 18.0038 | 0.01
0.074319 | 6.7161 | 1.8025 | 1.7037 | 2.0124 | 2.4074 | 5.5186 | 3.8149 | 6.7904 | 8.4941 | 14.0127 | 17.8276 | 0.074319 | 6.7261 | 1.8025 | 1.7037 | 2.0124 | 2.4074 | 5.5186 | 3.8149 | 6.8004 | 8.5041 | 14.0227 | 17.8376 | 0.01
1.085 | 6.9351 | 1.8362 | 1.7543 | 2.1808 | 2.5085 | 5.7713 | 4.017 | 8.0201 | 9.7744 | 15.5456 | 19.5626 | 1.085 | 6.9451 | 1.8362 | 1.7543 | 2.1808 | 2.5085 | 5.7713 | 4.017 | 8.0301 | 9.7844 | 15.5556 | 19.5726 | 0.01
-3.1212 | 6.0237 | 1.696 | 1.5439 | 1.4798 | 2.0879 | 4.7197 | 3.1758 | 2.9025 | 4.4464 | 9.1661 | 12.3419 | -3.1212 | 6.0337 | 1.696 | 1.5439 | 1.4798 | 2.0879 | 4.7197 | 3.1758 | 2.9125 | 4.4564 | 9.1761 | 12.3519 | 0.01
6.0895 | 8.0194 | 2.003 | 2.0045 | 3.0149 | 3.009 | 7.0224 | 5.0179 | 14.1089 | 16.1134 | 23.1357 | 28.1536 | 6.0895 | 8.0294 | 2.003 | 2.0045 | 3.0149 | 3.009 | 7.0224 | 5.0179 | 14.1189 | 16.1234 | 23.1457 | 28.1636 | 0.01
6.2141 | 8.0464 | 2.0071 | 2.0107 | 3.0357 | 3.0214 | 7.0535 | 5.0428 | 14.2605 | 16.2712 | 23.3247 | 28.3676 | 6.2141 | 8.0564 | 2.0071 | 2.0107 | 3.0357 | 3.0214 | 7.0535 | 5.0428 | 14.2705 | 16.2812 | 23.3347 | 28.3776 | 0.01
9.4624 | 8.7502 | 2.1154 | 2.1731 | 3.5771 | 3.3462 | 7.8656 | 5.6925 | 18.2126 | 20.3857 | 28.2513 | 33.9437 | 9.4624 | 8.7602 | 2.1154 | 2.1731 | 3.5771 | 3.3462 | 7.8656 | 5.6925 | 18.2226 | 20.3957 | 28.2613 | 33.9537 | 0.01
2.7991 | 7.3065 | 1.8933 | 1.84 | 2.4665 | 2.6799 | 6.1998 | 4.3598 | 10.1056 | 11.9456 | 18.1454 | 22.5052 | 2.7991 | 7.3165 | 1.8933 | 1.84 | 2.4665 | 2.6799 | 6.1998 | 4.3598 | 10.1156 | 11.9556 | 18.1554 | 22.5152 | 0.01
0.57475 | 6.8245 | 1.8192 | 1.7287 | 2.0958 | 2.4575 | 5.6437 | 3.915 | 7.3993 | 9.128 | 14.7717 | 18.6867 | 0.57475 | 6.8345 | 1.8192 | 1.7287 | 2.0958 | 2.4575 | 5.6437 | 3.915 | 7.4093 | 9.138 | 14.7817 | 18.6967 | 0.01
9.4411 | 8.7456 | 2.1147 | 2.1721 | 3.5735 | 3.3441 | 7.8603 | 5.6882 | 18.1866 | 20.3587 | 28.219 | 33.9072 | 9.4411 | 8.7556 | 2.1147 | 2.1721 | 3.5735 | 3.3441 | 7.8603 | 5.6882 | 18.1966 | 20.3687 | 28.229 | 33.9172 | 0.01
-1.3256 | 6.4128 | 1.7558 | 1.6337 | 1.7791 | 2.2674 | 5.1686 | 3.5349 | 5.0872 | 6.7209 | 11.8896 | 15.4244 | -1.3256 | 6.4228 | 1.7558 | 1.6337 | 1.7791 | 2.2674 | 5.1686 | 3.5349 | 5.0972 | 6.7309 | 11.8996 | 15.4344 | 0.01
6.3785 | 8.082 | 2.0126 | 2.0189 | 3.0631 | 3.0379 | 7.0946 | 5.0757 | 14.4605 | 16.4794 | 23.5741 | 28.6498 | 6.3785 | 8.092 | 2.0126 | 2.0189 | 3.0631 | 3.0379 | 7.0946 | 5.0757 | 14.4705 | 16.4894 | 23.5841 | 28.6598 | 0.01
1.0149 | 6.9199 | 1.8338 | 1.7507 | 2.1692 | 2.5015 | 5.7537 | 4.003 | 7.9348 | 9.6856 | 15.4393 | 19.4423 | 1.0149 | 6.9299 | 1.8338 | 1.7507 | 2.1692 | 2.5015 | 5.7537 | 4.003 | 7.9448 | 9.6956 | 15.4493 | 19.4523 | 0.01
3.1071 | 7.3732 | 1.9036 | 1.8554 | 2.5178 | 2.7107 | 6.2768 | 4.4214 | 10.4803 | 12.3356 | 18.6124 | 23.0338 | 3.1071 | 7.3832 | 1.9036 | 1.8554 | 2.5178 | 2.7107 | 6.2768 | 4.4214 | 10.4903 | 12.3456 | 18.6224 | 23.0438 | 0.01
8.6083 | 8.5651 | 2.0869 | 2.1304 | 3.4347 | 3.2608 | 7.6521 | 5.5217 | 17.1734 | 19.3038 | 26.9559 | 32.4776 | 8.6083 | 8.5751 | 2.0869 | 2.1304 | 3.4347 | 3.2608 | 7.6521 | 5.5217 | 17.1834 | 19.3138 | 26.9659 | 32.4876 | 0.01
-7.3979 | 5.0971 | 1.5534 | 1.3301 | 0.76701 | 1.6602 | 3.6505 | 2.3204 | -2.3008 | -0.97073 | 2.6798 | 5.0002 | -7.3979 | 5.1071 | 1.5534 | 1.3301 | 0.76701 | 1.6602 | 3.6505 | 2.3204 | -2.2908 | -0.96073 | 2.6898 | 5.0102 | 0.01
9.1391 | 8.6801 | 2.1046 | 2.157 | 3.5232 | 3.3139 | 7.7848 | 5.6278 | 17.8192 | 19.9762 | 27.7609 | 33.3887 | 9.1391 | 8.6901 | 2.1046 | 2.157 | 3.5232 | 3.3139 | 7.7848 | 5.6278 | 17.8292 | 19.9862 | 27.7709 | 33.3987 | 0.01
10.1185 | 8.8923 | 2.1373 | 2.2059 | 3.6864 | 3.4118 | 8.0296 | 5.8237 | 19.0108 | 21.2168 | 29.2464 | 35.0701 | 10.1185 | 8.9023 | 2.1373 | 2.2059 | 3.6864 | 3.4118 | 8.0296 | 5.8237 | 19.0208 | 21.2268 | 29.2564 | 35.0801 | 0.01
8.8895 | 8.6261 | 2.0963 | 2.1445 | 3.4816 | 3.289 | 7.7224 | 5.5779 | 17.5156 | 19.6601 | 27.3825 | 32.9604 | 8.8895 | 8.6361 | 2.0963 | 2.1445 | 3.4816 | 3.289 | 7.7224 | 5.5779 | 17.5256 | 19.6701 | 27.3925 | 32.9704 | 0.01
18.1174 | 10.6254 | 2.4039 | 2.6059 | 5.0196 | 4.2117 | 10.0293 | 7.4235 | 28.7428 | 31.3487 | 41.378 | 48.8015 | 18.1174 | 10.6354 | 2.4039 | 2.6059 | 5.0196 | 4.2117 | 10.0293 | 7.4235 | 28.7528 | 31.3587 | 41.388 | 48.8115 | 0.01
-4.172 | 5.7961 | 1.6609 | 1.4914 | 1.3047 | 1.9828 | 4.457 | 2.9656 | 1.6241 | 3.1155 | 7.5725 | 10.5381 | -4.172 | 5.8061 | 1.6609 | 1.4914 | 1.3047 | 1.9828 | 4.457 | 2.9656 | 1.6341 | 3.1255 | 7.5825 | 10.5481 | 0.01
4.7866 | 7.7371 | 1.9596 | 1.9393 | 2.7978 | 2.8787 | 6.6966 | 4.7573 | 12.5236 | 14.463 | 21.1596 | 25.9169 | 4.7866 | 7.7471 | 1.9596 | 1.9393 | 2.7978 | 2.8787 | 6.6966 | 4.7573 | 12.5336 | 14.473 | 21.1696 | 25.9269 | 0.01
8.5519 | 8.5529 | 2.0851 | 2.1276 | 3.4253 | 3.2552 | 7.638 | 5.5104 | 17.1048 | 19.2324 | 26.8704 | 32.3807 | 8.5519 | 8.5629 | 2.0851 | 2.1276 | 3.4253 | 3.2552 | 7.638 | 5.5104 | 17.1148 | 19.2424 | 26.8804 | 32.3907 | 0.01
6.8119 | 8.1759 | 2.0271 | 2.0406 | 3.1353 | 3.0812 | 7.203 | 5.1624 | 14.9878 | 17.0284 | 24.2313 | 29.3937 | 6.8119 | 8.1859 | 2.0271 | 2.0406 | 3.1353 | 3.0812 | 7.203 | 5.1624 | 14.9978 | 17.0384 | 24.2413 | 29.4037 | 0.01
-7.8754 | 4.9937 | 1.5375 | 1.3062 | 0.68743 | 1.6125 | 3.5311 | 2.2249 | -2.8818 | -1.5755 | 1.9556 | 4.1805 | -7.8754 | 5.0037 | 1.5375 | 1.3062 | 0.68743 | 1.6125 | 3.5311 | 2.2249 | -2.8718 | -1.5655 | 1.9656 | 4.1905 | 0.01
3.4751 | 7.4529 | 1.9158 | 1.8738 | 2.5792 | 2.7475 | 6.3688 | 4.495 | 10.9281 | 12.8018 | 19.1706 | 23.6656 | 3.4751 | 7.4629 | 1.9158 | 1.8738 | 2.5792 | 2.7475 | 6.3688 | 4.495 | 10.9381 | 12.8118 | 19.1806 | 23.6756 | 0.01
-3.9303 | 5.8484 | 1.669 | 1.5035 | 1.345 | 2.007 | 4.5174 | 3.0139 | 1.9181 | 3.4216 | 7.9391 | 10.953 | -3.9303 | 5.8584 | 1.669 | 1.5035 | 1.345 | 2.007 | 4.5174 | 3.0139 | 1.9281 | 3.4316 | 7.9491 | 10.963 | 0.01
11.6169 | 9.217 | 2.1872 | 2.2808 | 3.9362 | 3.5617 | 8.4042 | 6.1234 | 20.8339 | 23.1148 | 31.519 | 37.6424 | 11.6169 | 9.227 | 2.1872 | 2.2808 | 3.9362 | 3.5617 | 8.4042 | 6.1234 | 20.8439 | 23.1248 | 31.529 | 37.6524 | 0.01
6.6067 | 8.1315 | 2.0202 | 2.0303 | 3.1011 | 3.0607 | 7.1517 | 5.1213 | 14.7382 | 16.7685 | 23.9202 | 29.0415 | 6.6067 | 8.1415 | 2.0202 | 2.0303 | 3.1011 | 3.0607 | 7.1517 | 5.1213 | 14.7482 | 16.7785 | 23.9302 | 29.0515 | 0.01
3.6787 | 7.4971 | 1.9226 | 1.8839 | 2.6131 | 2.7679 | 6.4197 | 4.5357 | 11.1758 | 13.0597 | 19.4794 | 24.0151 | 3.6787 | 7.5071 | 1.9226 | 1.8839 | 2.6131 | 2.7679 | 6.4197 | 4.5357 | 11.1858 | 13.0697 | 19.4894 | 24.0251 | 0.01
10.0022 | 8.8671 | 2.1334 | 2.2001 | 3.667 | 3.4002 | 8.0005 | 5.8004 | 18.8693 | 21.0694 | 29.07 | 34.8704 | 10.0022 | 8.8771 | 2.1334 | 2.2001 | 3.667 | 3.4002 | 8.0005 | 5.8004 | 18.8793 | 21.0794 | 29.08 | 34.8804 | 0.01
2.8576 | 7.3192 | 1.8953 | 1.8429 | 2.4763 | 2.6858 | 6.2144 | 4.3715 | 10.1768 | 12.0197 | 18.2341 | 22.6056 | 2.8576 | 7.3292 | 1.8953 | 1.8429 | 2.4763 | 2.6858 | 6.2144 | 4.3715 | 10.1868 | 12.0297 | 18.2441 | 22.6156 | 0.01
-5.7356 | 5.4573 | 1.6088 | 1.4132 | 1.0441 | 1.8264 | 4.0661 | 2.6529 | -0.2783 | 1.1349 | 5.201 | 7.8539 | -5.7356 | 5.4673 | 1.6088 | 1.4132 | 1.0441 | 1.8264 | 4.0661 | 2.6529 | -0.2683 | 1.1449 | 5.211 | 7.8639 | 0.01
-0.24152 | 6.6477 | 1.7919 | 1.6879 | 1.9597 | 2.3758 | 5.4396 | 3.7517 | 6.4062 | 8.0941 | 13.5337 | 17.2854 | -0.24152 | 6.6577 | 1.7919 | 1.6879 | 1.9597 | 2.3758 | 5.4396 | 3.7517 | 6.4162 | 8.1041 | 13.5437 | 17.2954 | 0.01
-1.1184 | 6.4577 | 1.7627 | 1.6441 | 1.8136 | 2.2882 | 5.2204 | 3.5763 | 5.3393 | 6.9834 | 12.2038 | 15.7801 | -1.1184 | 6.4677 | 1.7627 | 1.6441 | 1.8136 | 2.2882 | 5.2204 | 3.5763 | 5.3493 | 6.9934 | 12.2138 | 15.7901 | 0.01
9.8841 | 8.8416 | 1.6146 | 2.1942 | 3.6474 | 3.3884 | 7.971 | 5.7768 | 18.7257 | 20.9199 | 28.891 | 34.6678 | 9.8841 | 8.8516 | 1.6146 | 2.1942 | 3.6474 | 3.3884 | 7.971 | 5.7768 | 18.7357 | 20.9299 | 28.901 | 34.6778 | 0.01
-5.5634 | 5.4946 | 1.9328 | 1.4218 | 1.0728 | 1.8437 | 4.1091 | 2.6873 | -0.068833 | 1.353 | 5.4621 | 8.1495 | -5.5634 | 5.5046 | 1.9328 | 1.4218 | 1.0728 | 1.8437 | 4.1091 | 2.6873 | -0.058833 | 1.363 | 5.4721 | 8.1595 | 0.01
3.9837 | 7.5631 | 2.3331 | 1.8992 | 2.6639 | 2.7984 | 6.4959 | 4.5967 | 11.5468 | 13.446 | 19.9419 | 24.5386 | 3.9837 | 7.5731 | 2.3331 | 1.8992 | 2.6639 | 2.7984 | 6.4959 | 4.5967 | 11.5568 | 13.456 | 19.9519 | 24.5486 | 0.01
15.9941 | 10.1654 | 1.7859 | 2.4997 | 4.6657 | 3.9994 | 9.4985 | 6.9988 | 26.1595 | 28.6592 | 38.1577 | 45.1566 | 15.9941 | 10.1754 | 1.7859 | 2.4997 | 4.6657 | 3.9994 | 9.4985 | 6.9988 | 26.1695 | 28.6692 | 38.1677 | 45.1666 | 0.01
-0.42261 | 6.6084 | 1.794 | 1.6789 | 1.9296 | 2.3577 | 5.3943 | 3.7155 | 6.1858 | 7.8647 | 13.259 | 16.9745 | -0.42261 | 6.6184 | 1.794 | 1.6789 | 1.9296 | 2.3577 | 5.3943 | 3.7155 | 6.1958 | 7.8747 | 13.269 | 16.9845 | 0.01
-0.18131 | 6.6607 | 1.9908 | 1.6909 | 1.9698 | 2.3819 | 5.4547 | 3.7637 | 6.4794 | 8.1703 | 13.625 | 17.3887 | -0.18131 | 6.6707 | 1.9908 | 1.6909 | 1.9698 | 2.3819 | 5.4547 | 3.7637 | 6.4894 | 8.1803 | 13.635 | 17.3987 | 0.01
5.7226 | 7.9399 | 2.0474 | 1.9861 | 2.9538 | 2.9723 | 6.9306 | 4.9445 | 13.6625 | 15.6486 | 22.5792 | 27.5238 | 5.7226 | 7.9499 | 2.0474 | 1.9861 | 2.9538 | 2.9723 | 6.9306 | 4.9445 | 13.6725 | 15.6586 | 22.5892 | 27.5338 | 0.01
7.4208 | 8.3078 | 2.0177 | 2.071 | 3.2368 | 3.1421 | 7.3552 | 5.2842 | 15.7286 | 17.7997 | 25.1549 | 30.439 | 7.4208 | 8.3178 | 2.0177 | 2.071 | 3.2368 | 3.1421 | 7.3552 | 5.2842 | 15.7386 | 17.8097 | 25.1649 | 30.449 | 0.01
6.5317 | 8.1152 | 2.2316 | 2.0266 | 3.0886 | 3.0532 | 7.1329 | 5.1063 | 14.6469 | 16.6735 | 23.8064 | 28.9127 | 6.5317 | 8.1252 | 2.2316 | 2.0266 | 3.0886 | 3.0532 | 7.1329 | 5.1063 | 14.6569 | 16.6835 | 23.8164 | 28.9227 | 0.01
12.9487 | 9.5056 | 2.2484 | 2.3474 | 4.1581 | 3.6949 | 8.7372 | 6.3897 | 22.4543 | 24.8017 | 33.5389 | 39.9286 | 12.9487 | 9.5156 | 2.2484 | 2.3474 | 4.1581 | 3.6949 | 8.7372 | 6.3897 | 22.4643 | 24.8117 | 33.5489 | 39.9386 | 0.01
13.4512 | 9.6144 | 1.8607 | 2.3726 | 4.2419 | 3.7451 | 8.8628 | 6.4902 | 23.0656 | 25.4382 | 34.301 | 40.7912 | 13.4512 | 9.6244 | 1.8607 | 2.3726 | 4.2419 | 3.7451 | 8.8628 | 6.4902 | 23.0756 | 25.4482 | 34.311 | 40.8012 | 0.01
1.8217 | 7.0947 | 2.0947 | 1.7911 | 2.3036 | 2.5822 | 5.9554 | 4.1643 | 8.9164 | 10.7075 | 16.6629 | 20.8272 | 1.8217 | 7.1047 | 2.0947 | 1.7911 | 2.3036 | 2.5822 | 5.9554 | 4.1643 | 8.9264 | 10.7175 | 16.6729 | 20.8372 | 0.01
8.8397 | 8.6153 | 1.8922 | 2.142 | 3.4733 | 3.284 | 7.7099 | 5.5679 | 17.455 | 19.597 | 27.3069 | 32.8748 | 8.8397 | 8.6253 | 1.8922 | 2.142 | 3.4733 | 3.284 | 7.7099 | 5.5679 | 17.465 | 19.607 | 27.3169 | 32.8848 | 0.01
2.7666 | 7.2994 | 2.0757 | 1.8383 | 2.4611 | 2.6767 | 6.1916 | 4.3533 | 10.066 | 11.9043 | 18.0959 | 22.4493 | 2.7666 | 7.3094 | 2.0757 | 1.8383 | 2.4611 | 2.6767 | 6.1916 | 4.3533 | 10.076 | 11.9143 | 18.1059 | 22.4593 | 0.01
8.2722 | 8.4923 | 1.8633 | 2.1136 | 3.3787 | 3.2272 | 7.568 | 5.4544 | 16.7645 | 18.8781 | 26.4461 | 31.9006 | 8.2722 | 8.5023 | 1.8633 | 2.1136 | 3.3787 | 3.2272 | 7.568 | 5.4544 | 16.7745 | 18.8881 | 26.4561 | 31.9106 | 0.01
1.8989 | 7.1114 | 2.0766 | 1.7949 | 2.3165 | 2.5899 | 5.9747 | 4.1798 | 9.0103 | 10.8052 | 16.7799 | 20.9597 | 1.8989 | 7.1214 | 2.0766 | 1.7949 | 2.3165 | 2.5899 | 5.9747 | 4.1798 | 9.0203 | 10.8152 | 16.7899 | 20.9697 | 0.01
8.2977 | 8.4978 | 2.1503 | 2.1149 | 3.3829 | 3.2298 | 7.5744 | 5.4595 | 16.7955 | 18.9104 | 26.4848 | 31.9444 | 8.2977 | 8.5078 | 2.1503 | 2.1149 | 3.3829 | 3.2298 | 7.5744 | 5.4595 | 16.8055 | 18.9204 | 26.4948 | 31.9544 | 0.01
10.5101 | 8.9772 | 2.0598 | 2.2255 | 3.7517 | 3.451 | 8.1275 | 5.902 | 19.4873 | 21.7128 | 29.8404 | 35.7424 | 10.5101 | 8.9872 | 2.0598 | 2.2255 | 3.7517 | 3.451 | 8.1275 | 5.902 | 19.4973 | 21.7228 | 29.8504 | 35.7524 | 0.01
7.7932 | 8.3885 | 2.4427 | 2.0897 | 3.2989 | 3.1793 | 7.4483 | 5.3586 | 16.1817 | 18.2714 | 25.7197 | 31.0784 | 7.7932 | 8.3985 | 2.4427 | 2.0897 | 3.2989 | 3.1793 | 7.4483 | 5.3586 | 16.1917 | 18.2814 | 25.7297 | 31.0884 | 0.01
19.2796 | 10.8773 | 1.7714 | 2.664 | 5.2133 | 4.328 | 10.3199 | 7.6559 | 30.1569 | 32.8209 | 43.1408 | 50.7967 | 19.2796 | 10.8873 | 1.7714 | 2.664 | 5.2133 | 4.328 | 10.3199 | 7.6559 | 30.1669 | 32.8309 | 43.1508 | 50.8067 | 0.01
-0.85792 | 6.5141 | 1.9787 | 1.6571 | 1.857 | 2.3142 | 5.2855 | 3.6284 | 5.6562 | 7.3133 | 12.5988 | 16.2272 | -0.85792 | 6.5241 | 1.9787 | 1.6571 | 1.857 | 2.3142 | 5.2855 | 3.6284 | 5.6662 | 7.3233 | 12.6088 | 16.2372 | 0.01
5.3618 | 7.8617 | 2.1086 | 1.9681 | 2.8936 | 2.9362 | 6.8405 | 4.8724 | 13.2236 | 15.1917 | 22.0321 | 26.9045 | 5.3618 | 7.8717 | 2.1086 | 1.9681 | 2.8936 | 2.9362 | 6.8405 | 4.8724 | 13.2336 | 15.2017 | 22.0421 | 26.9145 | 0.01
9.2577 | 8.7058 | 2.1426 | 2.1629 | 3.543 | 3.3258 | 7.8144 | 5.6515 | 17.9635 | 20.1264 | 27.9408 | 33.5924 | 9.2577 | 8.7158 | 2.1426 | 2.1629 | 3.543 | 3.3258 | 7.8144 | 5.6515 | 17.9735 | 20.1364 | 27.9508 | 33.6024 | 0.01
10.2787 | 8.9271 | 2.2081 | 2.2139 | 3.7131 | 3.4279 | 8.0697 | 5.8557 | 19.2058 | 21.4197 | 29.4894 | 35.3451 | 10.2787 | 8.9371 | 2.2081 | 2.2139 | 3.7131 | 3.4279 | 8.0697 | 5.8557 | 19.2158 | 21.4297 | 29.4994 | 35.3551 | 0.01
12.2433 | 9.3527 | 1.7133 | 2.3122 | 4.0406 | 3.6243 | 8.5608 | 6.2487 | 21.5961 | 23.9082 | 32.4691 | 38.7177 | 12.2433 | 9.3627 | 1.7133 | 2.3122 | 4.0406 | 3.6243 | 8.5608 | 6.2487 | 21.6061 | 23.9182 | 32.4791 | 38.7277 | 0.01
-2.602 | 6.1362 | 2.0305 | 1.5699 | 1.5663 | 2.1398 | 4.8495 | 3.2796 | 3.5343 | 5.1042 | 9.9537 | 13.2333 | -2.602 | 6.1462 | 2.0305 | 1.5699 | 1.5663 | 2.1398 | 4.8495 | 3.2796 | 3.5443 | 5.1142 | 9.9637 | 13.2433 | 0.01
6.9152 | 8.1983 | 1.9055 | 2.0458 | 3.1525 | 3.0915 | 7.2288 | 5.183 | 15.1135 | 17.1593 | 24.3881 | 29.5711 | 6.9152 | 8.2083 | 1.9055 | 2.0458 | 3.1525 | 3.0915 | 7.2288 | 5.183 | 15.1235 | 17.1693 | 24.3981 | 29.5811 | 0.01
3.1651 | 7.3858 | 2.0144 | 1.8583 | 2.5275 | 2.7165 | 6.2913 | 4.433 | 10.5509 | 12.4091 | 18.7004 | 23.1334 | 3.1651 | 7.3958 | 2.0144 | 1.8583 | 2.5275 | 2.7165 | 6.2913 | 4.433 | 10.5609 | 12.4191 | 18.7104 | 23.1434 | 0.01
6.4306 | 8.0933 | 1.864 | 2.0215 | 3.0718 | 3.0431 | 7.1076 | 5.0861 | 14.5239 | 16.5454 | 23.653 | 28.7391 | 6.4306 | 8.1033 | 1.864 | 2.0215 | 3.0718 | 3.0431 | 7.1076 | 5.0861 | 14.5339 | 16.5554 | 23.663 | 28.7491 | 0.01
1.919 | 7.1158 | 1.9736 | 1.7959 | 2.3198 | 2.5919 | 5.9797 | 4.1838 | 9.0347 | 10.8307 | 16.8104 | 20.9942 | 1.919 | 7.1258 | 1.9736 | 1.7959 | 2.3198 | 2.5919 | 5.9797 | 4.1838 | 9.0447 | 10.8407 | 16.8204 | 21.0042 | 0.01
5.2075 | 7.8283 | 1.9672 | 1.9604 | 2.8679 | 2.9207 | 6.8019 | 4.8415 | 13.0358 | 14.9962 | 21.798 | 26.6395 | 5.2075 | 7.8383 | 1.9672 | 1.9604 | 2.8679 | 2.9207 | 6.8019 | 4.8415 | 13.0458 | 15.0062 | 21.808 | 26.6495 | 0.01
5.0148 | 7.7865 | 1.9804 | 1.9507 | 2.8358 | 2.9015 | 6.7537 | 4.803 | 12.8013 | 14.7521 | 21.5058 | 26.3087 | 5.0148 | 7.7965 | 1.9804 | 1.9507 | 2.8358 | 2.9015 | 6.7537 | 4.803 | 12.8113 | 14.7621 | 21.5158 | 26.3187 | 0.01
5.4118 | 7.8725 | 1.82 | 1.9706 | 2.902 | 2.9412 | 6.8529 | 4.8824 | 13.2843 | 15.2549 | 22.1078 | 26.9902 | 5.4118 | 7.8825 | 1.82 | 1.9706 | 2.902 | 2.9412 | 6.8529 | 4.8824 | 13.2943 | 15.2649 | 22.1178 | 27.0002 | 0.01
0.60033 | 6.8301 | 2.1284 | 1.73 | 2.1001 | 2.46 | 5.6501 | 3.9201 | 7.4304 | 9.1604 | 14.8105 | 18.7306 | 0.60033 | 6.8401 | 2.1284 | 1.73 | 2.1001 | 2.46 | 5.6501 | 3.9201 | 7.4404 | 9.1704 | 14.8205 | 18.7406 | 0.01
9.8505 | 8.8343 | 1.9956 | 2.1925 | 3.6418 | 3.3851 | 7.9626 | 5.7701 | 18.6848 | 20.8773 | 28.84 | 34.6101 | 9.8505 | 8.8443 | 1.9956 | 2.1925 | 3.6418 | 3.3851 | 7.9626 | 5.7701 | 18.6948 | 20.8873 | 28.85 | 34.6201 | 0.01
5.8682 | 7.9714 | 1.8458 | 1.9934 | 2.978 | 2.9868 | 6.9671 | 4.9736 | 13.8396 | 15.8331 | 22.8001 | 27.7737 | 5.8682 | 7.9814 | 1.8458 | 1.9934 | 2.978 | 2.9868 | 6.9671 | 4.9736 | 13.8496 | 15.8431 | 22.8101 | 27.7837 | 0.01
1.3746 | 6.9978 | 2.3455 | 1.7687 | 2.2291 | 2.5375 | 5.8436 | 4.0749 | 8.3724 | 10.1411 | 15.9848 | 20.0597 | 1.3746 | 7.0078 | 2.3455 | 1.7687 | 2.2291 | 2.5375 | 5.8436 | 4.0749 | 8.3824 | 10.1511 | 15.9948 | 20.0697 | 0.01
16.3663 | 10.246 | 2.1493 | 2.5183 | 4.7277 | 4.0366 | 9.5916 | 7.0733 | 26.6123 | 29.1306 | 38.7222 | 45.7954 | 16.3663 | 10.256 | 2.1493 | 2.5183 | 4.7277 | 4.0366 | 9.5916 | 7.0733 | 26.6223 | 29.1406 | 38.7322 | 45.8054 | 0.01
10.4785 | 8.9703 | 2.2881 | 2.2239 | 3.7464 | 3.4479 | 8.1196 | 5.8957 | 19.4488 | 21.6728 | 29.7924 | 35.6881 | 10.4785 | 8.9803 | 2.2881 | 2.2239 | 3.7464 | 3.4479 | 8.1196 | 5.8957 | 19.4588 | 21.6828 | 29.8024 | 35.6981 | 0.01
14.6431 | 9.8727 | 2.1757 | 2.4322 | 4.4405 | 3.8643 | 9.1608 | 6.7286 | 24.5157 | 26.9479 | 36.1087 | 42.8373 | 14.6431 | 9.8827 | 2.1757 | 2.4322 | 4.4405 | 3.8643 | 9.1608 | 6.7286 | 24.5257 | 26.9579 | 36.1187 | 42.8473 | 0.01
11.2705 | 9.1419 | 1.6904 | 2.2635 | 3.8784 | 3.5271 | 8.3176 | 6.0541 | 20.4125 | 22.676 | 30.9936 | 37.0477 | 11.2705 | 9.1519 | 1.6904 | 2.2635 | 3.8784 | 3.5271 | 8.3176 | 6.0541 | 20.4225 | 22.686 | 31.0036 | 37.0577 | 0.01
-3.2871 | 5.9878 | 1.9339 | 1.5356 | 1.4522 | 2.0713 | 4.6782 | 3.1426 | 2.7008 | 4.2364 | 8.9146 | 12.0572 | -3.2871 | 5.9978 | 1.9339 | 1.5356 | 1.4522 | 2.0713 | 4.6782 | 3.1426 | 2.7108 | 4.2464 | 8.9246 | 12.0672 | 0.01
4.0163 | 7.5702 | 1.9562 | 1.9008 | 2.6694 | 2.8016 | 6.5041 | 4.6033 | 11.5865 | 13.4873 | 19.9914 | 24.5946 | 4.0163 | 7.5802 | 1.9562 | 1.9008 | 2.6694 | 2.8016 | 6.5041 | 4.6033 | 11.5965 | 13.4973 | 20.0014 | 24.6046 | 0.01
4.6864 | 7.7154 | 1.8488 | 1.9343 | 2.7811 | 2.8686 | 6.6716 | 4.7373 | 12.4018 | 14.3361 | 21.0078 | 25.745 | 4.6864 | 7.7254 | 1.8488 | 1.9343 | 2.7811 | 2.8686 | 6.6716 | 4.7373 | 12.4118 | 14.3461 | 21.0178 | 25.755 | 0.01
1.4634 | 7.0171 | 1.7742 | 1.7732 | 2.2439 | 3.5791 | 5.8659 | 4.0927 | 8.4805 | 10.2536 | 16.1195 | 20.2122 | 1.4634 | 7.0271 | 1.7742 | 1.7732 | 2.2439 | 3.5791 | 5.8659 | 4.0927 | 8.4905 | 10.2636 | 16.1295 | 20.2222 | 0.01
-0.77368 | 6.5324 | 2.193 | 1.6613 | 1.8711 | 1.6857 | 5.3066 | 3.6453 | 5.7587 | 7.42 | 12.7266 | 16.3718 | -0.77368 | 6.5424 | 2.193 | 1.6613 | 1.8711 | 1.6857 | 5.3066 | 3.6453 | 5.7687 | 7.43 | 12.7366 | 16.3818 | 0.01
11.7905 | 9.2546 | 1.5619 | 2.2895 | 3.9651 | 2.9119 | 8.4476 | 6.1581 | 21.0451 | 23.3346 | 31.7823 | 37.9404 | 11.7905 | 9.2646 | 1.5619 | 2.2895 | 3.9651 | 2.9119 | 8.4476 | 6.1581 | 21.0551 | 23.3446 | 31.7923 | 37.9504 | 0.01
-7.1426 | 5.1524 | 1.9706 | 1.3429 | 0.80957 | 3.4348 | 3.7144 | 2.3715 | -1.9901 | -0.64725 | 3.5972 | 5.9687 | -7.1426 | 5.1624 | 1.9706 | 1.3429 | 0.80957 | 3.4348 | 3.7144 | 2.3715 | -1.9801 | -0.63725 | 3.6072 | 5.9787 | 0.01
5.1192 | 7.8092 | 2.1449 | 1.956 | 2.8532 | 3.9823 | 6.7798 | 4.8238 | 12.9284 | 14.8844 | 21.7198 | 26.5437 | 5.1192 | 7.8192 | 2.1449 | 1.956 | 2.8532 | 3.9823 | 6.7798 | 4.8238 | 12.9384 | 14.8944 | 21.7298 | 26.5537 | 0.01
10.3484 | 8.9421 | 2.3274 | 2.2174 | 3.7247 | 2.3004 | 8.0871 | 5.8697 | 19.2905 | 21.5079 | 29.595 | 35.4647 | 10.3484 | 8.9521 | 2.3274 | 2.2174 | 3.7247 | 2.3004 | 8.0871 | 5.8697 | 19.3005 | 21.5179 | 29.605 | 35.4747 | 0.01
15.8226 | 10.1282 | 1.7668 | 2.4911 | 4.6371 | 1.4393 | 9.4556 | 6.9645 | 25.9508 | 28.442 | 37.8976 | 44.8621 | 15.8226 | 10.1382 | 1.7668 | 2.4911 | 4.6371 | 1.4393 | 9.4556 | 6.9645 | 25.9608 | 28.452 | 37.9076 | 44.8721 | 0.01
-0.99638 | 6.4841 | 1.4798 | 1.6502 | 1.8339 | 2.1554 | 5.2509 | 3.6007 | 5.4877 | 7.1379 | 12.3888 | 15.9895 | -0.99638 | 6.4941 | 1.4798 | 1.6502 | 1.8339 | 2.1554 | 5.2509 | 3.6007 | 5.4977 | 7.1479 | 12.3988 | 15.9995 | 0.01
-9.6069 | 4.6185 | 1.7185 | 1.2197 | 0.39885 | 2.5843 | 4.8886 | 1.8786 | -4.9884 | -3.7688 | 1.1198 | 2.9984 | -9.6069 | 4.6285 | 1.7185 | 1.2197 | 0.39885 | 2.5843 | 4.8886 | 1.8786 | -4.9784 | -3.7588 | 1.1298 | 3.0084 | 0.01
-2.4456 | 6.1701 | 1.8614 | 1.5777 | 1.5924 | 2.3528 | 5.9607 | 3.3109 | 3.7245 | 5.3022 | 11.2629 | 14.5738 | -2.4456 | 6.1801 | 1.8614 | 1.5777 | 1.5924 | 2.3528 | 5.9607 | 3.3109 | 3.7345 | 5.3122 | 11.2729 | 14.5838 | 0.01
1.8427 | 7.0993 | 1.7843 | 1.7921 | 2.3071 | 2.7307 | 5.3821 | 4.1685 | 8.942 | 10.7341 | 16.1162 | 20.2847 | 1.8427 | 7.1093 | 1.7843 | 1.7921 | 2.3071 | 2.7307 | 5.3821 | 4.1685 | 8.952 | 10.7441 | 16.1262 | 20.2947 | 0.01
-0.47175 | 6.5978 | 1.9102 | 1.6764 | 1.9214 | 2.5396 | 6.3268 | 3.7057 | 6.126 | 7.8025 | 14.1292 | 17.8349 | -0.47175 | 6.6078 | 1.9102 | 1.6764 | 1.9214 | 2.5396 | 6.3268 | 3.7057 | 6.136 | 7.8125 | 14.1392 | 17.8449 | 0.01
3.3071 | 7.4165 | 1.8465 | 1.7698 | 2.5512 | 2.4087 | 5.8491 | 4.4614 | 10.7236 | 12.4935 | 18.3426 | 22.804 | 3.3071 | 7.4265 | 1.8465 | 1.7698 | 2.5512 | 2.4087 | 5.8491 | 4.4614 | 10.7336 | 12.5035 | 18.3526 | 22.814 | 0.01
1.3965 | 7.0026 | 1.8029 | 1.7043 | 2.2327 | 3.3494 | 5.5217 | 4.0793 | 8.399 | 10.1034 | 15.6855 | 19.7648 | 1.3965 | 7.0126 | 1.8029 | 1.7043 | 2.2327 | 3.3494 | 5.5217 | 4.0793 | 8.409 | 10.1134 | 15.6955 | 19.7748 | 0.01
0.08672 | 6.7188 | 2.1165 | 2.1747 | 2.0145 | 3.9835 | 7.8734 | 3.8173 | 6.8055 | 8.9802 | 16.8536 | 20.671 | 0.08672 | 6.7288 | 2.1165 | 2.1747 | 2.0145 | 3.9835 | 7.8734 | 3.8173 | 6.8155 | 8.9902 | 16.8636 | 20.681 | 0.01
9.4938 | 8.757 | 2.3278 | 2.4917 | 3.5823 | 3.2911 | 9.4587 | 5.6988 | 18.2508 | 20.7425 | 30.2012 | 35.8999 | 9.4938 | 8.767 | 2.3278 | 2.4917 | 3.5823 | 3.2911 | 9.4587 | 5.6988 | 18.2608 | 20.7525 | 30.2112 | 35.9099 | 0.01
15.8348 | 10.1309 | 2.097 | 2.1455 | 4.6391 | 3.8318 | 7.7276 | 6.967 | 25.9657 | 28.1112 | 36.5822 | 43.5491 | 15.8348 | 10.1409 | 2.097 | 2.1455 | 4.6391 | 3.8318 | 7.7276 | 6.967 | 25.9757 | 28.1212 | 36.5922 | 43.5591 | 0.01
8.9106 | 8.6306 | 2.2773 | 2.4159 | 3.4851 | 2.4722 | 9.0796 | 5.5821 | 17.5412 | 19.9571 | 29.0368 | 34.6189 | 8.9106 | 8.6406 | 2.2773 | 2.4159 | 3.4851 | 2.4722 | 9.0796 | 5.5821 | 17.5512 | 19.9671 | 29.0468 | 34.6289 | 0.01
14.3184 | 9.8023 | 1.8241 | 1.7361 | 4.3864 | 3.1013 | 5.6806 | 6.6637 | 24.1208 | 25.8569 | 33.3446 | 40.0083 | 14.3184 | 9.8123 | 1.8241 | 1.7361 | 4.3864 | 3.1013 | 5.6806 | 6.6637 | 24.1308 | 25.8669 | 33.3546 | 40.0183 | 0.01
0.7224 | 6.8565 | 2.0338 | 2.0506 | 2.1204 | 4.3384 | 7.2532 | 3.9445 | 7.5789 | 9.6296 | 16.8828 | 20.8273 | 0.7224 | 6.8665 | 2.0338 | 2.0506 | 2.1204 | 4.3384 | 7.2532 | 3.9445 | 7.5889 | 9.6396 | 16.8928 | 20.8373 | 0.01
7.0128 | 8.2194 | 2.4461 | 2.6692 | 3.1688 | 1.3988 | 10.346 | 5.2026 | 15.2323 | 17.9015 | 28.2475 | 33.45 | 7.0128 | 8.2294 | 2.4461 | 2.6692 | 3.1688 | 1.3988 | 10.346 | 5.2026 | 15.2423 | 17.9115 | 28.2575 | 33.46 | 0.01
19.384 | 10.8999 | 1.4663 | 1.1994 | 5.2307 | 4.3226 | 2.9969 | 7.6768 | 30.2838 | 31.4832 | 41.0365 | 48.7133 | 19.384 | 10.9099 | 1.4663 | 1.1994 | 5.2307 | 4.3226 | 2.9969 | 7.6768 | 30.2938 | 31.4932 | 41.0465 | 48.7233 | 0.01
19.2262 | 4.5307 | 2.4409 | 2.6613 | 0.33129 | 3.8214 | 10.3065 | 1.7975 | 23.7568 | 26.4181 | 36.7247 | 38.5222 | 19.2262 | 4.5407 | 2.4409 | 2.6613 | 0.33129 | 3.8214 | 10.3065 | 1.7975 | 23.7668 | 26.4281 | 36.7347 | 38.5322 | 0.01
14.2142 | 10.8657 | 2.2738 | 2.4107 | 5.2044 | 2.1505 | 9.0535 | 7.6452 | 25.0798 | 27.4905 | 36.5441 | 44.1893 | 14.2142 | 10.8757 | 2.2738 | 2.4107 | 5.2044 | 2.1505 | 9.0535 | 7.6452 | 25.0898 | 27.5005 | 36.5541 | 44.1993 | 0.01
-2.4952 | 9.7797 | 1.7168 | 1.5752 | 4.369 | 3.5234 | 4.8762 | 6.6428 | 7.2846 | 8.8598 | 16.7522 | 23.395 | -2.4952 | 9.7897 | 1.7168 | 1.5752 | 4.369 | 3.5234 | 4.8762 | 6.6428 | 7.2946 | 8.8698 | 16.7622 | 23.405 | 0.01
11.2336 | 6.1594 | 2.1745 | 2.2617 | 1.5841 | 4.0163 | 8.3084 | 3.301 | 17.393 | 19.6547 | 27.9631 | 31.2641 | 11.2336 | 6.1694 | 2.1745 | 2.2617 | 1.5841 | 4.0163 | 8.3084 | 3.301 | 17.403 | 19.6647 | 27.9731 | 31.2741 | 0.01
16.1635 | 9.134 | 2.3388 | 2.5082 | 3.8723 | 2.7069 | 9.5409 | 6.0467 | 25.2974 | 27.8056 | 37.3465 | 43.3932 | 16.1635 | 9.144 | 2.3388 | 2.5082 | 3.8723 | 2.7069 | 9.5409 | 6.0467 | 25.3074 | 27.8156 | 37.3565 | 43.4032 | 0.01
3.0691 | 10.2021 | 1.9023 | 1.8535 | 4.2369 | 3.7422 | 6.2673 | 7.0327 | 13.2711 | 15.1246 | 23.1037 | 30.1364 | 3.0691 | 10.2121 | 1.9023 | 1.8535 | 4.2369 | 3.7422 | 6.2673 | 7.0327 | 13.2811 | 15.1346 | 23.1137 | 30.1464 | 0.01
13.4216 | 7.365 | 2.2474 | 2.3711 | 4.3798 | 3.8279 | 8.8554 | 4.4138 | 20.7866 | 23.1577 | 32.0131 | 36.4269 | 13.4216 | 7.375 | 2.2474 | 2.3711 | 4.3798 | 3.8279 | 8.8554 | 4.4138 | 20.7966 | 23.1677 | 32.0231 | 36.4369 | 0.01
14.2791 | 9.608 | 2.276 | 2.414 | 2.4376 | 2.6625 | 9.0698 | 6.4843 | 23.8871 | 26.301 | 35.3708 | 41.8551 | 14.2791 | 9.618 | 2.276 | 2.414 | 2.4376 | 2.6625 | 9.0698 | 6.4843 | 23.8971 | 26.311 | 35.3808 | 41.8651 | 0.01
2.6253 | 9.7938 | 1.8875 | 1.8313 | 0.72184 | 1.6331 | 6.1563 | 6.6558 | 12.4191 | 14.2504 | 20.4067 | 27.0625 | 2.6253 | 9.8038 | 1.8875 | 1.8313 | 0.72184 | 1.6331 | 6.1563 | 6.6558 | 12.4291 | 14.2604 | 20.4167 | 27.0725 | 0.01
-7.6689 | 7.2688 | 1.5444 | 1.3166 | 4.3164 | 3.7899 | 3.5828 | 4.3251 | -0.40013 | 0.91643 | 9.0227 | 13.3478 | -7.6689 | 7.2788 | 1.5444 | 1.3166 | 4.3164 | 3.7899 | 3.5828 | 4.3251 | -0.39013 | 0.92643 | 9.0327 | 13.3578 | 0.01
13.8987 | 5.0384 | 2.2633 | 2.3949 | 4.5377 | 3.9226 | 8.9747 | 2.2662 | 18.9371 | 21.332 | 30.3067 | 32.5729 | 13.8987 | 5.0484 | 2.2633 | 2.3949 | 4.5377 | 3.9226 | 8.9747 | 2.2662 | 18.9471 | 21.342 | 30.3167 | 32.5829 | 0.01
15.2263 | 9.7114 | 2.3075 | 2.4613 | 5.1783 | 4.307 | 9.3066 | 6.5797 | 24.9377 | 27.399 | 36.8844 | 43.4641 | 15.2263 | 9.7214 | 2.3075 | 2.4613 | 5.1783 | 4.307 | 9.3066 | 6.5797 | 24.9477 | 27.409 | 36.8944 | 43.4741 | 0.01
19.0701 | 9.999 | 2.4357 | 2.6535 | 1.7349 | 2.2409 | 10.2675 | 6.8453 | 29.0691 | 31.7226 | 41.9902 | 48.8354 | 19.0701 | 10.009 | 2.4357 | 2.6535 | 1.7349 | 2.2409 | 10.2675 | 6.8453 | 29.0791 | 31.7326 | 42.0002 | 48.8454 | 0.01
-1.5907 | 10.8319 | 1.747 | 1.6205 | 3.4667 | 3.28 | 5.1023 | 7.614 | 9.2411 | 10.8616 | 17.6083 | 25.2223 | -1.5907 | 10.8419 | 1.747 | 1.6205 | 3.4667 | 3.28 | 5.1023 | 7.614 | 9.2511 | 10.8716 | 17.6183 | 25.2323 | 0.01
8.8001 | 6.3553 | 2.0933 | 2.14 | 3.3661 | 3.2197 | 7.7 | 3.4819 | 15.1554 | 17.2954 | 24.9955 | 28.4773 | 8.8001 | 6.3653 | 2.0933 | 2.14 | 3.3661 | 3.2197 | 7.7 | 3.4819 | 15.1654 | 17.3054 | 25.0055 | 28.4873 | 0.01
8.1966 | 8.6067 | 2.0732 | 2.1098 | 2.9229 | 2.9538 | 7.5492 | 5.56 | 16.8033 | 18.9131 | 26.4623 | 32.0223 | 8.1966 | 8.6167 | 2.0732 | 2.1098 | 2.9229 | 2.9538 | 7.5492 | 5.56 | 16.8133 | 18.9231 | 26.4723 | 32.0323 | 0.01
5.5376 | 8.4759 | 1.9846 | 1.9769 | 2.3602 | 2.6161 | 6.8844 | 5.4393 | 14.0135 | 15.9904 | 22.8748 | 28.3141 | 5.5376 | 8.4859 | 1.9846 | 1.9769 | 2.3602 | 2.6161 | 6.8844 | 5.4393 | 14.0235 | 16.0004 | 22.8848 | 28.3241 | 0.01
2.1614 | 7.8998 | 1.872 | 1.8081 | 2.489 | 2.6934 | 6.0403 | 4.9075 | 10.0612 | 11.8692 | 17.9096 | 22.8171 | 2.1614 | 7.9098 | 1.872 | 1.8081 | 2.489 | 2.6934 | 6.0403 | 4.9075 | 10.0712 | 11.8792 | 17.9196 | 22.8271 | 0.01
2.9341 | 7.1683 | 1.8978 | 1.8467 | 3.9122 | 3.5473 | 6.2335 | 4.2323 | 10.1024 | 11.9491 | 19.4087 | 23.641 | 2.9341 | 7.1783 | 1.8978 | 1.8467 | 3.9122 | 3.5473 | 6.2335 | 4.2323 | 10.1124 | 11.9591 | 19.4187 | 23.651 | 0.01
11.4734 | 7.3357 | 2.1824 | 2.2737 | 4.5221 | 3.9133 | 8.3684 | 4.3868 | 18.8092 | 21.0828 | 29.5182 | 33.9051 | 11.4734 | 7.3457 | 2.1824 | 2.2737 | 4.5221 | 3.9133 | 8.3684 | 4.3868 | 18.8192 | 21.0928 | 29.5282 | 33.9151 | 0.01
15.1327 | 9.1859 | 2.3044 | 2.4566 | 3.0515 | 3.0309 | 9.2832 | 6.0947 | 24.3186 | 26.7752 | 36.0584 | 42.1531 | 15.1327 | 9.1959 | 2.3044 | 2.4566 | 3.0515 | 3.0309 | 9.2832 | 6.0947 | 24.3286 | 26.7852 | 36.0684 | 42.1631 | 0.01
6.309 | 9.9788 | 2.0103 | 2.0154 | 3.3918 | 3.2351 | 7.0772 | 6.8265 | 16.2877 | 18.3032 | 25.3804 | 32.207 | 6.309 | 9.9888 | 2.0103 | 2.0154 | 3.3918 | 3.2351 | 7.0772 | 6.8265 | 16.2977 | 18.3132 | 25.3904 | 32.217 | 0.01
8.3508 | 8.0669 | 2.0784 | 2.1175 | 3.9998 | 3.5999 | 7.5877 | 5.0618 | 16.4178 | 18.5353 | 26.135 | 31.1968 | 8.3508 | 8.0769 | 2.0784 | 2.1175 | 3.9998 | 3.5999 | 7.5877 | 5.0618 | 16.4278 | 18.5453 | 26.145 | 31.2068 | 0.01
11.9988 | 8.5093 | 2.2 | 2.2999 | 3.3774 | 3.2265 | 8.4997 | 5.4702 | 20.5081 | 22.808 | 31.3077 | 36.7779 | 11.9988 | 8.5193 | 2.2 | 2.2999 | 3.3774 | 3.2265 | 8.4997 | 5.4702 | 20.5181 | 22.818 | 31.3177 | 36.7879 | 0.01
8.2645 | 9.2997 | 2.0755 | 2.1132 | 2.4958 | 2.6975 | 7.5661 | 6.1998 | 17.5643 | 19.6775 | 27.2436 | 33.4434 | 8.2645 | 9.3097 | 2.0755 | 2.1132 | 2.4958 | 2.6975 | 7.5661 | 6.1998 | 17.5743 | 19.6875 | 27.2536 | 33.4534 | 0.01
2.9748 | 8.4906 | 1.8992 | 1.8487 | 3.6696 | 3.4018 | 6.2437 | 5.4529 | 11.4654 | 13.3142 | 20.3856 | 25.8385 | 2.9748 | 8.5006 | 1.8992 | 1.8487 | 3.6696 | 3.4018 | 6.2437 | 5.4529 | 11.4754 | 13.3242 | 20.3956 | 25.8485 | 0.01
10.0178 | 7.3445 | 2.1339 | 2.2009 | 2.3627 | 2.6176 | 8.0044 | 4.395 | 17.3623 | 19.5632 | 27.5677 | 31.9626 | 10.0178 | 7.3545 | 2.1339 | 2.2009 | 2.3627 | 2.6176 | 8.0044 | 4.395 | 17.3723 | 19.5732 | 27.5777 | 31.9726 | 0.01
2.1761 | 8.8705 | 1.8725 | 1.8088 | 3.6992 | 3.4195 | 6.044 | 5.8036 | 11.0466 | 12.8554 | 19.9742 | 25.7777 | 2.1761 | 8.8805 | 1.8725 | 1.8088 | 3.6992 | 3.4195 | 6.044 | 5.8036 | 11.0566 | 12.8654 | 19.9842 | 25.7877 | 0.01
10.1953 | 7.1715 | 2.1398 | 2.2098 | 2.0614 | 2.4368 | 8.0488 | 4.2352 | 17.3668 | 19.5765 | 27.6253 | 31.8606 | 10.1953 | 7.1815 | 2.1398 | 2.2098 | 2.0614 | 2.4368 | 8.0488 | 4.2352 | 17.3768 | 19.5865 | 27.6353 | 31.8706 | 0.01
0.36812 | 8.909 | 1.8123 | 1.7184 | 3.4738 | 3.2843 | 5.592 | 5.8391 | 9.2771 | 10.9955 | 17.7536 | 23.5926 | 0.36812 | 8.919 | 1.8123 | 1.7184 | 3.4738 | 3.2843 | 5.592 | 5.8391 | 9.2871 | 11.0055 | 17.7636 | 23.6026 | 0.01
8.8428 | 6.7798 | 2.0948 | 2.1421 | 2.5607 | 2.7364 | 7.7107 | 3.8736 | 15.6225 | 17.7647 | 25.4753 | 29.349 | 8.8428 | 6.7898 | 2.0948 | 2.1421 | 2.5607 | 2.7364 | 7.7107 | 3.8736 | 15.6325 | 17.7747 | 25.4853 | 29.359 | 0.01
3.3639 | 8.6159 | 1.9121 | 1.8682 | 3.7195 | 3.4317 | 6.341 | 5.5686 | 11.9799 | 13.8481 | 20.9992 | 26.5678 | 3.3639 | 8.6259 | 1.9121 | 1.8682 | 3.7195 | 3.4317 | 6.341 | 5.5686 | 11.9899 | 13.8581 | 21.0092 | 26.5778 | 0.01
10.3169 | 7.4289 | 2.1439 | 2.2158 | 4.0749 | 3.645 | 8.0792 | 4.4728 | 17.7457 | 19.9616 | 28.0408 | 32.5136 | 10.3169 | 7.4389 | 2.1439 | 2.2158 | 4.0749 | 3.645 | 8.0792 | 4.4728 | 17.7557 | 19.9716 | 28.0508 | 32.5236 | 0.01
12.4496 | 8.9353 | 2.215 | 2.3225 | 3.8485 | 3.5091 | 8.6124 | 5.8634 | 21.3849 | 23.7074 | 32.3198 | 38.1832 | 12.4496 | 8.9453 | 2.215 | 2.3225 | 3.8485 | 3.5091 | 8.6124 | 5.8634 | 21.3949 | 23.7174 | 32.3298 | 38.1932 | 0.01
11.0913 | 9.3974 | 2.1697 | 2.2546 | 1.6992 | 2.2195 | 8.2728 | 6.2899 | 20.4887 | 22.7433 | 31.0161 | 37.306 | 11.0913 | 9.4074 | 2.1697 | 2.2546 | 1.6992 | 2.2195 | 8.2728 | 6.2899 | 20.4987 | 22.7533 | 31.0261 | 37.316 | 0.01
-1.8049 | 9.1031 | 1.7398 | 1.6098 | 3.2226 | 3.1336 | 5.0488 | 6.0183 | 7.2982 | 8.908 | 15.2642 | 21.2824 | -1.8049 | 9.1131 | 1.7398 | 1.6098 | 3.2226 | 3.1336 | 5.0488 | 6.0183 | 7.3082 | 8.918 | 15.2742 | 21.2924 | 0.01
7.3357 | 6.3089 | 2.0445 | 2.0668 | 4.1585 | 3.6951 | 7.3339 | 3.439 | 13.6446 | 15.7114 | 23.565 | 27.004 | 7.3357 | 6.3189 | 2.0445 | 2.0668 | 4.1585 | 3.6951 | 7.3339 | 3.439 | 13.6546 | 15.7214 | 23.575 | 27.014 | 0.01
12.9509 | 8.2894 | 2.2317 | 2.3475 | 1.8244 | 2.2947 | 8.7377 | 5.2671 | 21.2403 | 23.5878 | 32.3255 | 37.5927 | 12.9509 | 8.2994 | 2.2317 | 2.3475 | 1.8244 | 2.2947 | 8.7377 | 5.2671 | 21.2503 | 23.5978 | 32.3355 | 37.6027 | 0.01
-1.0534 | 9.506 | 1.7649 | 1.6473 | 4.1219 | 3.6732 | 5.2366 | 6.3902 | 8.4526 | 10.0999 | 17.895 | 24.2852 | -1.0534 | 9.516 | 1.7649 | 1.6473 | 4.1219 | 3.6732 | 5.2366 | 6.3902 | 8.4626 | 10.1099 | 17.905 | 24.2952 | 0.01
12.7317 | 6.4718 | 2.2244 | 2.3366 | 2.2937 | 2.5762 | 8.6829 | 3.5893 | 19.2034 | 21.54 | 30.2229 | 33.8122 | 12.7317 | 6.4818 | 2.2244 | 2.3366 | 2.2937 | 2.5762 | 8.6829 | 3.5893 | 19.2134 | 21.55 | 30.2329 | 33.8222 | 0.01
1.7625 | 9.4585 | 1.8587 | 1.7881 | 4.4139 | 3.8484 | 5.9406 | 6.3463 | 11.221 | 13.0091 | 21.2714 | 27.6177 | 1.7625 | 9.4685 | 1.8587 | 1.7881 | 4.4139 | 3.8484 | 5.9406 | 6.3463 | 11.231 | 13.0191 | 21.2814 | 27.6277 | 0.01
14.4836 | 7.0819 | 2.2828 | 2.4242 | 2.818 | 2.8908 | 9.1209 | 4.1525 | 21.5654 | 23.9896 | 33.1105 | 37.263 | 14.4836 | 7.0919 | 2.2828 | 2.4242 | 2.818 | 2.8908 | 9.1209 | 4.1525 | 21.5754 | 23.9996 | 33.1205 | 37.273 | 0.01
4.908 | 9.8381 | 1.9636 | 1.9454 | 4.2124 | 3.7275 | 6.727 | 6.6967 | 14.7461 | 16.6915 | 24.6314 | 31.3281 | 4.908 | 9.8481 | 1.9636 | 1.9454 | 4.2124 | 3.7275 | 6.727 | 6.6967 | 14.7561 | 16.7015 | 24.6414 | 31.3381 | 0.01
13.2747 | 7.7634 | 2.2425 | 2.3637 | 2.6176 | 2.7706 | 8.8187 | 4.7816 | 21.0381 | 23.4018 | 32.2205 | 37.0021 | 13.2747 | 7.7734 | 2.2425 | 2.3637 | 2.6176 | 2.7706 | 8.8187 | 4.7816 | 21.0481 | 23.4118 | 32.2305 | 37.0121 | 0.01
3.7058 | 9.5762 | 1.9235 | 1.8853 | 4.0942 | 3.6565 | 6.4265 | 6.4549 | 13.282 | 15.1673 | 22.9179 | 29.3729 | 3.7058 | 9.5862 | 1.9235 | 1.8853 | 4.0942 | 3.6565 | 6.4265 | 6.4549 | 13.292 | 15.1773 | 22.9279 | 29.3829 | 0.01
12.5649 | 7.5029 | 2.2188 | 2.3282 | 2.7136 | 2.8282 | 8.6412 | 4.5412 | 20.0678 | 22.3961 | 31.0373 | 35.5785 | 12.5649 | 7.5129 | 2.2188 | 2.3282 | 2.7136 | 2.8282 | 8.6412 | 4.5412 | 20.0778 | 22.4061 | 31.0473 | 35.5885 | 0.01
4.2816 | 9.4224 | 1.9427 | 1.9141 | 1.5496 | 2.1298 | 6.5704 | 6.313 | 13.704 | 15.618 | 22.1884 | 28.5014 | 4.2816 | 9.4324 | 1.9427 | 1.9141 | 1.5496 | 2.1298 | 6.5704 | 6.313 | 13.714 | 15.628 | 22.1984 | 28.5114 | 0.01
-2.7021 | 7.6277 | 1.7099 | 1.5649 | 4.8215 | 4.0929 | 4.8245 | 4.6563 | 4.9255 | 6.4904 | 15.4048 | 20.0611 | -2.7021 | 7.6377 | 1.7099 | 1.5649 | 4.8215 | 4.0929 | 4.8245 | 4.6563 | 4.9355 | 6.5004 | 15.4148 | 20.0711 | 0.01
16.9289 | 6.1145 | 2.3643 | 2.5464 | 1.5666 | 2.14 | 9.7322 | 3.2596 | 23.0434 | 25.5899 | 35.3221 | 38.5817 | 16.9289 | 6.1245 | 2.3643 | 2.5464 | 1.5666 | 2.14 | 9.7322 | 3.2596 | 23.0534 | 25.5999 | 35.3321 | 38.5917 | 0.01
-2.6001 | 10.3679 | 1.7133 | 1.57 | 2.43 | 2.658 | 4.85 | 7.1858 | 7.7678 | 9.3378 | 14.4258 | 21.6116 | -2.6001 | 10.3779 | 1.7133 | 1.57 | 2.43 | 2.658 | 4.85 | 7.1858 | 7.7778 | 9.3478 | 14.4358 | 21.6216 | 0.01
2.5801 | 6.1366 | 1.886 | 1.829 | 0.74844 | 1.6491 | 6.145 | 3.28 | 8.7168 | 10.5458 | 16.6908 | 19.9708 | 2.5801 | 6.1466 | 1.886 | 1.829 | 0.74844 | 1.6491 | 6.145 | 3.28 | 8.7268 | 10.5558 | 16.7008 | 19.9808 | 0.01
-7.5094 | 7.259 | 1.5497 | 1.3245 | 3.3043 | 3.1826 | 3.6227 | 4.316 | -0.25035 | 1.0742 | 7.5611 | 11.8771 | -7.5094 | 7.269 | 1.5497 | 1.3245 | 3.3043 | 3.1826 | 3.6227 | 4.316 | -0.24035 | 1.0842 | 7.5711 | 11.8871 | 0.01
7.826 | 5.073 | 2.0609 | 2.0913 | 0.096747 | 1.258 | 7.4565 | 2.2981 | 12.899 | 14.9903 | 22.4468 | 24.7449 | 7.826 | 5.083 | 2.0609 | 2.0913 | 0.096747 | 1.258 | 7.4565 | 2.2981 | 12.909 | 15.0003 | 22.4568 | 24.7549 | 0.01
-11.4195 | 8.3956 | 1.4193 | 1.129 | 1.1507 | 1.8904 | 2.6451 | 5.3652 | -3.0239 | -1.8949 | 1.1462 | 6.5114 | -11.4195 | 8.4056 | 1.4193 | 1.129 | 1.1507 | 1.8904 | 2.6451 | 5.3652 | -3.0139 | -1.8849 | 1.1562 | 6.5214 | 0.01
-5.0961 | 4.2258 | 1.6301 | 1.4452 | 2.318 | 2.5908 | 4.226 | 1.5161 | -0.87032 | 0.57488 | 5.4837 | 6.9998 | -5.0961 | 4.2358 | 1.6301 | 1.4452 | 2.318 | 2.5908 | 4.226 | 1.5161 | -0.86032 | 0.58488 | 5.4937 | 7.0098 | 0.01
1.9081 | 5.5958 | 1.8636 | 1.7954 | 3.9068 | 3.5441 | 5.977 | 2.7808 | 7.5039 | 9.2993 | 16.7502 | 19.531 | 1.9081 | 5.6058 | 1.8636 | 1.7954 | 3.9068 | 3.5441 | 5.977 | 2.7808 | 7.5139 | 9.3093 | 16.7602 | 19.541 | 0.01
11.4408 | 7.1134 | 2.1814 | 2.272 | 3.9987 | 3.5992 | 8.3602 | 4.1816 | 18.5542 | 20.8263 | 29.1865 | 33.3681 | 11.4408 | 7.1234 | 2.1814 | 2.272 | 3.9987 | 3.5992 | 8.3602 | 4.1816 | 18.5642 | 20.8363 | 29.1965 | 33.3781 | 0.01
11.9924 | 9.1788 | 2.1997 | 2.2996 | 2.5211 | 2.7127 | 8.4981 | 6.0882 | 21.1712 | 23.4708 | 31.9689 | 38.0571 | 11.9924 | 9.1888 | 2.1997 | 2.2996 | 2.5211 | 2.7127 | 8.4981 | 6.0882 | 21.1812 | 23.4808 | 31.9789 | 38.0671 | 0.01
3.1269 | 9.2983 | 1.9042 | 1.8563 | 2.6077 | 2.7646 | 6.2817 | 6.1985 | 12.4252 | 14.2815 | 20.5633 | 26.7617 | 3.1269 | 9.3083 | 1.9042 | 1.8563 | 2.6077 | 2.7646 | 6.2817 | 6.1985 | 12.4352 | 14.2915 | 20.5733 | 26.7717 | 0.01
3.646 | 7.3775 | 1.9215 | 1.8823 | 3.8705 | 3.5223 | 6.4115 | 4.4254 | 11.0234 | 12.9057 | 20.2986 | 24.724 | 3.646 | 7.3875 | 1.9215 | 1.8823 | 3.8705 | 3.5223 | 6.4115 | 4.4254 | 11.0334 | 12.9157 | 20.3086 | 24.734 | 0.01
11.2232 | 7.49 | 2.1741 | 2.2612 | 4.6272 | 3.9763 | 8.3058 | 4.5292 | 18.7131 | 20.9743 | 29.5778 | 34.107 | 11.2232 | 7.5 | 2.1741 | 2.2612 | 4.6272 | 3.9763 | 8.3058 | 4.5292 | 18.7231 | 20.9843 | 29.5878 | 34.117 | 0.01
15.7633 | 9.1317 | 2.3254 | 2.4882 | 3.3338 | 3.2003 | 9.4408 | 6.0446 | 24.895 | 27.3831 | 36.8239 | 42.8686 | 15.7633 | 9.1417 | 2.3254 | 2.4882 | 3.3338 | 3.2003 | 9.4408 | 6.0446 | 24.905 | 27.3931 | 36.8339 | 42.8786 | 0.01
8.0029 | 10.1154 | 2.0668 | 2.1001 | 4.3526 | 3.8116 | 7.5007 | 6.9527 | 18.1183 | 20.2185 | 28.3827 | 35.3354 | 8.0029 | 10.1254 | 2.0668 | 2.1001 | 4.3526 | 3.8116 | 7.5007 | 6.9527 | 18.1283 | 20.2285 | 28.3927 | 35.3454 | 0.01
14.1159 | 8.434 | 2.2705 | 2.4058 | 3.1711 | 3.1026 | 9.029 | 5.4006 | 22.5498 | 24.9556 | 33.9846 | 39.3852 | 14.1159 | 8.444 | 2.2705 | 2.4058 | 3.1711 | 3.1026 | 9.029 | 5.4006 | 22.5598 | 24.9656 | 33.9946 | 39.3952 | 0.01
7.0265 | 9.7584 | 2.0342 | 2.0513 | 1.0701 | 1.842 | 7.2566 | 6.6232 | 16.7849 | 18.8362 | 26.0929 | 32.716 | 7.0265 | 9.7684 | 2.0342 | 2.0513 | 1.0701 | 1.842 | 7.2566 | 6.6232 | 16.7949 | 18.8462 | 26.1029 | 32.726 | 0.01
-5.5795 | 8.2224 | 1.614 | 1.421 | 3.1699 | 3.1019 | 4.1051 | 5.2053 | 2.6429 | 4.0639 | 10.3358 | 15.5411 | -5.5795 | 8.2324 | 1.614 | 1.421 | 3.1699 | 3.1019 | 4.1051 | 5.2053 | 2.6529 | 4.0739 | 10.3458 | 15.5511 | 0.01
7.0195 | 5.4911 | 2.034 | 2.051 | 2.44 | 2.664 | 7.2549 | 2.6841 | 12.5106 | 14.5615 | 21.8164 | 24.5005 | 7.0195 | 5.5011 | 2.034 | 2.051 | 2.44 | 2.664 | 7.2549 | 2.6841 | 12.5206 | 14.5715 | 21.8264 | 24.5105 | 0.01
2.6398 | 8.2209 | 1.888 | 1.832 | 3.9164 | 3.5498 | 6.1599 | 5.2039 | 10.8607 | 12.6926 | 20.1589 | 25.3627 | 2.6398 | 8.2309 | 1.888 | 1.832 | 3.9164 | 3.5498 | 6.1599 | 5.2039 | 10.8707 | 12.7026 | 20.1689 | 25.3727 | 0.01
11.4983 | 7.272 | 2.1833 | 2.2749 | 2.2667 | 2.56 | 8.3746 | 4.328 | 18.7703 | 21.0452 | 29.4197 | 33.7477 | 11.4983 | 7.282 | 2.1833 | 2.2749 | 2.2667 | 2.56 | 8.3746 | 4.328 | 18.7803 | 21.0552 | 29.4297 | 33.7577 | 0.01
1.6003 | 9.1913 | 1.8533 | 1.78 | 0.78163 | 1.669 | 5.9001 | 6.0997 | 10.7916 | 12.5716 | 18.4716 | 24.5713 | 1.6003 | 9.2013 | 1.8533 | 1.78 | 0.78163 | 1.669 | 5.9001 | 6.0997 | 10.8016 | 12.5816 | 18.4816 | 24.5813 | 0.01
-7.3102 | 7.0467 | 1.5563 | 1.3345 | 4.619 | 3.9714 | 3.6724 | 4.1201 | -0.26348 | 1.071 | 9.6614 | 13.7815 | -7.3102 | 7.0567 | 1.5563 | 1.3345 | 4.619 | 3.9714 | 3.6724 | 4.1201 | -0.25348 | 1.081 | 9.6714 | 13.7915 | 0.01
15.714 | 5.1161 | 2.3238 | 2.4857 | 4.1687 | 3.7012 | 9.4285 | 2.338 | 20.8301 | 23.3158 | 32.7443 | 35.0823 | 15.714 | 5.1261 | 2.3238 | 2.4857 | 4.1687 | 3.7012 | 9.4285 | 2.338 | 20.8401 | 23.3258 | 32.7543 | 35.0923 | 0.01
13.0123 | 10.1047 | 2.2337 | 2.3506 | 0.93932 | 1.7636 | 8.7531 | 6.9428 | 23.117 | 25.4677 | 34.2207 | 41.1635 | 13.0123 | 10.1147 | 2.2337 | 2.3506 | 0.93932 | 1.7636 | 8.7531 | 6.9428 | 23.127 | 25.4777 | 34.2307 | 41.1735 | 0.01
-6.3641 | 9.5193 | 1.5879 | 1.3818 | 3.1006 | 3.0604 | 3.909 | 6.4025 | 3.1553 | 4.5371 | 10.698 | 17.1005 | -6.3641 | 9.5293 | 1.5879 | 1.3818 | 3.1006 | 3.0604 | 3.909 | 6.4025 | 3.1653 | 4.5471 | 10.708 | 17.1105 | 0.01
6.6035 | 5.3211 | 2.0201 | 2.0302 | 3.8656 | 3.5194 | 7.1509 | 2.5272 | 11.9246 | 13.9548 | 21.3398 | 23.867 | 6.6035 | 5.3311 | 2.0201 | 2.0302 | 3.8656 | 3.5194 | 7.1509 | 2.5272 | 11.9346 | 13.9648 | 21.3498 | 23.877 | 0.01
11.1936 | 8.1308 | 2.1731 | 2.2597 | 2.3992 | 2.6395 | 8.2984 | 5.1207 | 19.3244 | 21.584 | 29.8824 | 35.0031 | 11.1936 | 8.1408 | 2.1731 | 2.2597 | 2.3992 | 2.6395 | 8.2984 | 5.1207 | 19.3344 | 21.594 | 29.8924 | 35.0131 | 0.01
2.3952 | 9.1253 | 1.8798 | 1.8198 | 4.4598 | 3.8759 | 6.0988 | 6.0387 | 11.5205 | 13.3403 | 21.6759 | 27.7146 | 2.3952 | 9.1353 | 1.8798 | 1.8198 | 4.4598 | 3.8759 | 6.0988 | 6.0387 | 11.5305 | 13.3503 | 21.6859 | 27.7246 | 0.01
14.7587 | 7.219 | 2.292 | 2.4379 | 4.6718 | 4.0031 | 9.1897 | 4.279 | 21.9776 | 24.4156 | 33.6053 | 37.8843 | 14.7587 | 7.229 | 2.292 | 2.4379 | 4.6718 | 4.0031 | 9.1897 | 4.279 | 21.9876 | 24.4256 | 33.6153 | 37.8943 | 0.01
16.0308 | 9.8977 | 2.3344 | 2.5015 | 2.5827 | 2.7496 | 9.5077 | 6.7517 | 25.9285 | 28.4301 | 37.9378 | 44.6895 | 16.0308 | 9.9077 | 2.3344 | 2.5015 | 2.5827 | 2.7496 | 9.5077 | 6.7517 | 25.9385 | 28.4401 | 37.9478 | 44.6995 | 0.01
3.496 | 10.1733 | 1.9165 | 1.8748 | 2.8107 | 2.8864 | 6.374 | 7.0062 | 13.6693 | 15.5441 | 21.9181 | 28.9243 | 3.496 | 10.1833 | 1.9165 | 1.8748 | 2.8107 | 2.8864 | 6.374 | 7.0062 | 13.6793 | 15.5541 | 21.9281 | 28.9343 | 0.01
4.8644 | 7.4575 | 1.9621 | 1.9432 | 4.7599 | 4.0559 | 6.7161 | 4.4992 | 12.3218 | 14.265 | 23.0809 | 27.5801 | 4.8644 | 7.4675 | 1.9621 | 1.9432 | 4.7599 | 4.0559 | 6.7161 | 4.4992 | 12.3318 | 14.275 | 23.0909 | 27.5901 | 0.01
16.5595 | 7.7539 | 2.352 | 2.528 | 5.0114 | 4.2069 | 9.6399 | 4.7729 | 24.3134 | 26.8414 | 36.4813 | 41.2541 | 16.5595 | 7.7639 | 2.352 | 2.528 | 5.0114 | 4.2069 | 9.6399 | 4.7729 | 24.3234 | 26.8514 | 36.4913 | 41.2641 | 0.01
18.0686 | 10.2879 | 2.4023 | 2.6034 | 4.3153 | 3.7892 | 10.0172 | 7.1119 | 28.3565 | 30.9599 | 40.9771 | 48.089 | 18.0686 | 10.2979 | 2.4023 | 2.6034 | 4.3153 | 3.7892 | 10.0172 | 7.1119 | 28.3665 | 30.9699 | 40.9871 | 48.099 | 0.01
13.8917 | 10.6149 | 2.2631 | 2.3946 | 3.384 | 3.2304 | 8.9729 | 7.4137 | 24.5065 | 26.9011 | 35.874 | 43.2878 | 13.8917 | 10.6249 | 2.2631 | 2.3946 | 3.384 | 3.2304 | 8.9729 | 7.4137 | 24.5165 | 26.9111 | 35.884 | 43.2978 | 0.01
8.3042 | 9.7099 | 2.0768 | 2.1152 | 2.9744 | 2.9846 | 7.576 | 6.5783 | 18.014 | 20.1292 | 27.7053 | 34.2836 | 8.3042 | 9.7199 | 2.0768 | 2.1152 | 2.9744 | 2.9846 | 7.576 | 6.5783 | 18.024 | 20.1392 | 27.7153 | 34.2936 | 0.01
5.8464 | 8.4992 | 1.9949 | 1.9923 | 4.3016 | 3.781 | 6.9616 | 5.4608 | 14.3457 | 16.338 | 24.4206 | 29.8814 | 5.8464 | 8.5092 | 1.9949 | 1.9923 | 4.3016 | 3.781 | 6.9616 | 5.4608 | 14.3557 | 16.348 | 24.4306 | 29.8914 | 0.01
13.8097 | 7.9667 | 2.2603 | 2.3905 | 3.6323 | 3.3794 | 8.9524 | 4.9693 | 21.7765 | 24.1669 | 33.1194 | 38.0887 | 13.8097 | 7.9767 | 2.2603 | 2.3905 | 3.6323 | 3.3794 | 8.9524 | 4.9693 | 21.7865 | 24.1769 | 33.1294 | 38.0987 | 0.01
9.7938 | 9.6921 | 2.1265 | 2.1897 | 3.7296 | 3.4377 | 7.9485 | 6.5619 | 19.4859 | 21.6756 | 29.6241 | 36.186 | 9.7938 | 9.7021 | 2.1265 | 2.1897 | 3.7296 | 3.4377 | 7.9485 | 6.5619 | 19.4959 | 21.6856 | 29.6341 | 36.196 | 0.01
10.3775 | 8.822 | 2.1459 | 2.2189 | 4.6453 | 3.9872 | 8.0944 | 5.7588 | 19.1995 | 21.4184 | 30.0509 | 35.8096 | 10.3775 | 8.832 | 2.1459 | 2.2189 | 4.6453 | 3.9872 | 8.0944 | 5.7588 | 19.2095 | 21.4284 | 30.0609 | 35.8196 | 0.01
15.8718 | 8.9485 | 2.3291 | 2.4936 | 2.8253 | 2.8952 | 9.468 | 5.8755 | 24.8203 | 27.3139 | 36.7818 | 42.6573 | 15.8718 | 8.9585 | 2.3291 | 2.4936 | 2.8253 | 2.8952 | 9.468 | 5.8755 | 24.8303 | 27.3239 | 36.7918 | 42.6673 | 0.01
4.9521 | 10.1389 | 1.9651 | 1.9476 | 2.6385 | 2.7831 | 6.738 | 6.9744 | 15.091 | 17.0386 | 23.7766 | 30.751 | 4.9521 | 10.1489 | 1.9651 | 1.9476 | 2.6385 | 2.7831 | 6.738 | 6.9744 | 15.101 | 17.0486 | 23.7866 | 30.761 | 0.01
3.8311 | 7.7729 | 1.9277 | 1.8916 | 2.9743 | 2.9846 | 6.4578 | 4.7904 | 11.604 | 13.4956 | 19.9533 | 24.7438 | 3.8311 | 7.7829 | 1.9277 | 1.8916 | 2.9743 | 2.9846 | 6.4578 | 4.7904 | 11.614 | 13.5056 | 19.9633 | 24.7538 | 0.01
5.8458 | 7.5301 | 1.9949 | 1.9923 | 1.9744 | 2.3846 | 6.9614 | 4.5662 | 13.3758 | 15.3681 | 22.3296 | 26.8958 | 5.8458 | 7.5401 | 1.9949 | 1.9923 | 1.9744 | 2.3846 | 6.9614 | 4.5662 | 13.3858 | 15.3781 | 22.3396 | 26.9058 | 0.01
-0.15369 | 7.9666 | 1.7949 | 1.6923 | 3.4835 | 3.2901 | 5.4616 | 4.9692 | 7.8129 | 9.5052 | 16.2788 | 21.248 | -0.15369 | 7.9766 | 1.7949 | 1.6923 | 3.4835 | 3.2901 | 5.4616 | 4.9692 | 7.8229 | 9.5152 | 16.2888 | 21.258 | 0.01
8.9011 | 6.6667 | 2.0967 | 2.1451 | 2.8402 | 2.9041 | 7.7253 | 3.7693 | 15.5678 | 17.7128 | 25.4381 | 29.2073 | 8.9011 | 6.6767 | 2.0967 | 2.1451 | 2.8402 | 2.9041 | 7.7253 | 3.7693 | 15.5778 | 17.7228 | 25.4481 | 29.2173 | 0.01
5.0411 | 8.6286 | 1.968 | 1.9521 | 2.9244 | 2.9547 | 6.7603 | 5.5802 | 13.6697 | 15.6217 | 22.382 | 27.9622 | 5.0411 | 8.6386 | 1.968 | 1.9521 | 2.9244 | 2.9547 | 6.7603 | 5.5802 | 13.6797 | 15.6317 | 22.392 | 27.9722 | 0.01
5.5467 | 7.7922 | 1.9849 | 1.9773 | 2.7834 | 2.87 | 6.8867 | 4.8082 | 13.3389 | 15.3163 | 22.2029 | 27.0112 | 5.5467 | 7.8022 | 1.9849 | 1.9773 | 2.7834 | 2.87 | 6.8867 | 4.8082 | 13.3489 | 15.3263 | 22.2129 | 27.0212 | 0.01
4.7002 | 7.9018 | 1.9567 | 1.935 | 2.2444 | 2.5466 | 6.675 | 4.9093 | 12.602 | 14.537 | 21.212 | 26.1214 | 4.7002 | 7.9118 | 1.9567 | 1.935 | 2.2444 | 2.5466 | 6.675 | 4.9093 | 12.612 | 14.547 | 21.222 | 26.1314 | 0.01
1.4663 | 7.7184 | 1.8489 | 1.7733 | 3.148 | 3.0888 | 5.8666 | 4.74 | 9.1847 | 10.958 | 17.1947 | 21.9348 | 1.4663 | 7.7284 | 1.8489 | 1.7733 | 3.148 | 3.0888 | 5.8666 | 4.74 | 9.1947 | 10.968 | 17.2047 | 21.9448 | 0.01
6.8879 | 7.0177 | 2.0296 | 2.0444 | 1.6145 | 2.1687 | 7.222 | 4.0933 | 13.9056 | 15.95 | 23.1719 | 27.2652 | 6.8879 | 7.0277 | 2.0296 | 2.0444 | 1.6145 | 2.1687 | 7.222 | 4.0933 | 13.9156 | 15.96 | 23.1819 | 27.2752 | 0.01
-2.3129 | 8.1924 | 1.7229 | 1.5844 | 2.1422 | 2.4853 | 4.9218 | 5.1776 | 5.8795 | 7.4639 | 12.3856 | 17.5632 | -2.3129 | 8.2024 | 1.7229 | 1.5844 | 2.1422 | 2.4853 | 4.9218 | 5.1776 | 5.8895 | 7.4739 | 12.3956 | 17.5732 | 0.01
0.85301 | 6.1989 | 1.8284 | 1.7427 | 3.3938 | 3.2363 | 5.7133 | 3.3374 | 7.0519 | 8.7945 | 15.4247 | 18.7621 | 0.85301 | 6.2089 | 1.8284 | 1.7427 | 3.3938 | 3.2363 | 5.7133 | 3.3374 | 7.0619 | 8.8045 | 15.4347 | 18.7721 | 0.01
8.363 | 6.8848 | 2.0788 | 2.1181 | 2.8631 | 2.9179 | 7.5907 | 3.9706 | 15.2478 | 17.366 | 24.9567 | 28.9273 | 8.363 | 6.8948 | 2.0788 | 2.1181 | 2.8631 | 2.9179 | 7.5907 | 3.9706 | 15.2578 | 17.376 | 24.9667 | 28.9373 | 0.01
5.1786 | 8.512 | 1.9726 | 1.9589 | 2.7811 | 2.8686 | 6.7946 | 5.4726 | 13.6906 | 15.6495 | 22.4441 | 27.9167 | 5.1786 | 8.522 | 1.9726 | 1.9589 | 2.7811 | 2.8686 | 6.7946 | 5.4726 | 13.7006 | 15.6595 | 22.4541 | 27.9267 | 0.01
4.6863 | 7.822 | 1.9562 | 1.9343 | 1.7183 | 2.231 | 6.6716 | 4.8357 | 12.5083 | 14.4427 | 21.1142 | 25.95 | 4.6863 | 7.832 | 1.9562 | 1.9343 | 1.7183 | 2.231 | 6.6716 | 4.8357 | 12.5183 | 14.4527 | 21.1242 | 25.96 | 0.01
-1.69 | 7.7154 | 1.7437 | 1.6155 | 2.6544 | 2.7926 | 5.0775 | 4.7373 | 6.0254 | 7.6409 | 13.0879 | 17.8252 | -1.69 | 7.7254 | 1.7437 | 1.6155 | 2.6544 | 2.7926 | 5.0775 | 4.7373 | 6.0354 | 7.6509 | 13.0979 | 17.8352 | 0.01
3.9263 | 6.3338 | 1.9309 | 1.8963 | 2.8467 | 2.908 | 6.4816 | 3.462 | 10.2601 | 12.1564 | 18.638 | 22.1 | 3.9263 | 6.3438 | 1.9309 | 1.8963 | 2.8467 | 2.908 | 6.4816 | 3.462 | 10.2701 | 12.1664 | 18.648 | 22.11 | 0.01
5.0801 | 7.5507 | 1.9693 | 1.954 | 2.9045 | 2.9427 | 6.77 | 4.5853 | 12.6307 | 14.5847 | 21.3548 | 25.94 | 5.0801 | 7.5607 | 1.9693 | 1.954 | 2.9045 | 2.9427 | 6.77 | 4.5853 | 12.6407 | 14.5947 | 21.3648 | 25.95 | 0.01
5.4268 | 7.8007 | 1.9809 | 1.9713 | 4.1252 | 3.6751 | 6.8567 | 4.816 | 13.2274 | 15.1988 | 22.9991 | 27.8151 | 5.4268 | 7.8107 | 1.9809 | 1.9713 | 4.1252 | 3.6751 | 6.8567 | 4.816 | 13.2374 | 15.2088 | 23.0091 | 27.8251 | 0.01
12.7511 | 7.8758 | 2.225 | 2.3376 | 3.8581 | 3.5149 | 8.6878 | 4.8854 | 20.6269 | 22.9645 | 31.6522 | 36.5376 | 12.7511 | 7.8858 | 2.225 | 2.3376 | 3.8581 | 3.5149 | 8.6878 | 4.8854 | 20.6369 | 22.9745 | 31.6622 | 36.5476 | 0.01
11.1487 | 9.4627 | 2.1716 | 2.2574 | 3.4723 | 3.2834 | 8.2872 | 6.3502 | 20.6114 | 22.8689 | 31.1561 | 37.5063 | 11.1487 | 9.4727 | 2.1716 | 2.2574 | 3.4723 | 3.2834 | 8.2872 | 6.3502 | 20.6214 | 22.8789 | 31.1661 | 37.5163 | 0.01
8.834 | 9.1156 | 2.0945 | 2.1417 | 3.2206 | 3.1323 | 7.7085 | 6.0297 | 17.9496 | 20.0913 | 27.7998 | 33.8295 | 8.834 | 9.1256 | 2.0945 | 2.1417 | 3.2206 | 3.1323 | 7.7085 | 6.0297 | 17.9596 | 20.1013 | 27.8098 | 33.8395 | 0.01
7.3235 | 8.614 | 2.0441 | 2.0662 | 3.2162 | 3.1297 | 7.3309 | 5.5668 | 15.9375 | 18.0037 | 25.3346 | 30.9014 | 7.3235 | 8.624 | 2.0441 | 2.0662 | 3.2162 | 3.1297 | 7.3309 | 5.5668 | 15.9475 | 18.0137 | 25.3446 | 30.9114 | 0.01
7.2969 | 8.2868 | 2.0432 | 2.0648 | 3.2464 | 3.1478 | 7.3242 | 5.2647 | 15.5837 | 17.6485 | 24.9727 | 30.2374 | 7.2969 | 8.2968 | 2.0432 | 2.0648 | 3.2464 | 3.1478 | 7.3242 | 5.2647 | 15.5937 | 17.6585 | 24.9827 | 30.2474 | 0.01
7.4785 | 8.281 | 2.0493 | 2.0739 | 1.9766 | 2.386 | 7.3696 | 5.2594 | 15.7595 | 17.8334 | 25.203 | 30.4624 | 7.4785 | 8.291 | 2.0493 | 2.0739 | 1.9766 | 2.386 | 7.3696 | 5.2594 | 15.7695 | 17.8434 | 25.213 | 30.4724 | 0.01
-0.14037 | 8.3203 | 1.7953 | 1.693 | 2.9701 | 2.9821 | 5.4649 | 5.2957 | 8.18 | 9.873 | 15.8251 | 21.1208 | -0.14037 | 8.3303 | 1.7953 | 1.693 | 2.9701 | 2.9821 | 5.4649 | 5.2957 | 8.19 | 9.883 | 15.8351 | 21.1308 | 0.01
5.8206 | 6.6696 | 1.994 | 1.991 | 1.6681 | 2.2008 | 6.9552 | 3.7719 | 12.4902 | 14.4813 | 21.4364 | 25.2083 | 5.8206 | 6.6796 | 1.994 | 1.991 | 1.6681 | 2.2008 | 6.9552 | 3.7719 | 12.5002 | 14.4913 | 21.4464 | 25.2183 | 0.01
-1.9916 | 7.9611 | 1.7336 | 1.6004 | 4.1051 | 3.6631 | 5.0021 | 4.9641 | 5.9696 | 7.57 | 15.3382 | 20.3023 | -1.9916 | 7.9711 | 1.7336 | 1.6004 | 4.1051 | 3.6631 | 5.0021 | 4.9641 | 5.9796 | 7.58 | 15.3482 | 20.3123 | 0.01
12.6307 | 6.2685 | 2.221 | 2.3315 | 3.1409 | 3.0845 | 8.6577 | 3.4017 | 18.8992 | 21.2308 | 29.8884 | 33.2901 | 12.6307 | 6.2785 | 2.221 | 2.3315 | 3.1409 | 3.0845 | 8.6577 | 3.4017 | 18.9092 | 21.2408 | 29.8984 | 33.3001 | 0.01
6.8453 | 9.4367 | 2.0282 | 2.0423 | 1.4547 | 2.0728 | 7.2113 | 6.3261 | 16.282 | 18.3243 | 25.5356 | 31.8617 | 6.8453 | 9.4467 | 2.0282 | 2.0423 | 1.4547 | 2.0728 | 7.2113 | 6.3261 | 16.292 | 18.3343 | 25.5456 | 31.8717 | 0.01
-3.272 | 8.1832 | 1.6909 | 1.5364 | 2.8971 | 2.9383 | 4.682 | 5.1691 | 4.9112 | 6.4476 | 12.283 | 17.452 | -3.272 | 8.1932 | 1.6909 | 1.5364 | 2.8971 | 2.9383 | 4.682 | 5.1691 | 4.9212 | 6.4576 | 12.293 | 17.462 | 0.01
5.3827 | 5.9911 | 1.9794 | 1.9691 | 4.3756 | 3.8253 | 6.8457 | 3.1456 | 11.3738 | 13.3429 | 21.5439 | 24.6895 | 5.3827 | 6.0011 | 1.9794 | 1.9691 | 4.3756 | 3.8253 | 6.8457 | 3.1456 | 11.3838 | 13.3529 | 21.5539 | 24.6995 | 0.01
14.2535 | 7.8663 | 2.2751 | 2.4127 | 2.174 | 2.5044 | 9.0634 | 4.8765 | 22.1197 | 24.5324 | 33.5958 | 38.4723 | 14.2535 | 7.8763 | 2.2751 | 2.4127 | 2.174 | 2.5044 | 9.0634 | 4.8765 | 22.1297 | 24.5424 | 33.6058 | 38.4823 | 0.01
1.0437 | 9.7882 | 1.8348 | 1.7522 | 2.1204 | 2.4722 | 5.7609 | 6.6507 | 10.832 | 12.5842 | 18.3451 | 24.9958 | 1.0437 | 9.7982 | 1.8348 | 1.7522 | 2.1204 | 2.4722 | 5.7609 | 6.6507 | 10.842 | 12.5942 | 18.3551 | 25.0058 | 0.01
0.72232 | 6.9261 | 1.8241 | 1.7361 | 3.0018 | 3.0011 | 5.6806 | 4.0087 | 7.6485 | 9.3846 | 15.3874 | 19.3962 | 0.72232 | 6.9361 | 1.8241 | 1.7361 | 3.0018 | 3.0011 | 5.6806 | 4.0087 | 7.6585 | 9.3946 | 15.3974 | 19.4062 | 0.01
6.0106 | 6.8565 | 2.0004 | 2.0005 | 2.5764 | 2.7458 | 7.0026 | 3.9445 | 12.8671 | 14.8676 | 21.8703 | 25.8147 | 6.0106 | 6.8665 | 2.0004 | 2.0005 | 2.5764 | 2.7458 | 7.0026 | 3.9445 | 12.8771 | 14.8776 | 21.8803 | 25.8247 | 0.01
3.4584 | 8.0023 | 1.9153 | 1.8729 | 0.37298 | 1.4238 | 6.3646 | 5.0021 | 11.4607 | 13.3337 | 19.6983 | 24.7004 | 3.4584 | 8.0123 | 1.9153 | 1.8729 | 0.37298 | 1.4238 | 6.3646 | 5.0021 | 11.4707 | 13.3437 | 19.7083 | 24.7104 | 0.01
-9.7621 | 7.4493 | 1.4746 | 1.2119 | 2.7077 | 2.8246 | 3.0595 | 4.4917 | -2.3128 | -1.1009 | 4.4314 | 8.9231 | -9.7621 | 7.4593 | 1.4746 | 1.2119 | 2.7077 | 2.8246 | 3.0595 | 4.4917 | -2.3028 | -1.0909 | 4.4414 | 8.9331 | 0.01
4.2463 | 4.5849 | 1.9415 | 1.9123 | 2.3095 | 2.5857 | 6.5616 | 1.8476 | 8.8311 | 10.7435 | 17.305 | 19.1526 | 4.2463 | 4.5949 | 1.9415 | 1.9123 | 2.3095 | 2.5857 | 6.5616 | 1.8476 | 8.8411 | 10.7535 | 17.315 | 19.1626 | 0.01
1.8569 | 7.62 | 1.8619 | 1.7928 | 3.3009 | 3.1806 | 5.9642 | 4.6493 | 9.4769 | 11.2698 | 17.7513 | 22.4005 | 1.8569 | 7.63 | 1.8619 | 1.7928 | 3.3009 | 3.1806 | 5.9642 | 4.6493 | 9.4869 | 11.2798 | 17.7613 | 22.4105 | 0.01
7.8055 | 7.1023 | 2.0602 | 2.0903 | 1.9738 | 2.3843 | 7.4514 | 4.1714 | 14.9079 | 16.9981 | 24.4495 | 28.6209 | 7.8055 | 7.1123 | 2.0602 | 2.0903 | 1.9738 | 2.3843 | 7.4514 | 4.1714 | 14.9179 | 17.0081 | 24.4595 | 28.6309 | 0.01
-0.15737 | 8.3912 | 1.7948 | 1.6921 | 2.3419 | 2.6052 | 5.4607 | 5.3611 | 8.2338 | 9.926 | 15.3866 | 20.7477 | -0.15737 | 8.4012 | 1.7948 | 1.6921 | 2.3419 | 2.6052 | 5.4607 | 5.3611 | 8.2438 | 9.936 | 15.3966 | 20.7577 | 0.01
2.0516 | 6.6659 | 1.8684 | 1.8026 | 4.6939 | 4.0163 | 6.0129 | 3.7685 | 8.7175 | 10.5201 | 19.2303 | 22.9989 | 2.0516 | 6.6759 | 1.8684 | 1.8026 | 4.6939 | 4.0163 | 6.0129 | 3.7685 | 8.7275 | 10.5301 | 19.2403 | 23.0089 | 0.01
16.1634 | 7.1445 | 2.3388 | 2.5082 | 2.4881 | 2.6928 | 9.5409 | 4.2103 | 23.308 | 25.8161 | 35.357 | 39.5673 | 16.1634 | 7.1545 | 2.3388 | 2.5082 | 2.4881 | 2.6928 | 9.5409 | 4.2103 | 23.318 | 25.8261 | 35.367 | 39.5773 | 0.01
2.9283 | 10.2021 | 1.8976 | 1.8464 | 1.8229 | 2.2937 | 6.2321 | 7.0327 | 13.1304 | 14.9768 | 21.2089 | 28.2416 | 2.9283 | 10.2121 | 1.8976 | 1.8464 | 1.8229 | 2.2937 | 6.2321 | 7.0327 | 13.1404 | 14.9868 | 21.2189 | 28.2516 | 0.01
-1.0626 | 7.3345 | 1.7646 | 1.6469 | 3.6826 | 3.4096 | 5.2344 | 4.3857 | 6.2719 | 7.9188 | 15.0109 | 19.3966 | -1.0626 | 7.3445 | 1.7646 | 1.6469 | 3.6826 | 3.4096 | 5.2344 | 4.3857 | 6.2819 | 7.9288 | 15.0209 | 19.4066 | 0.01
10.0956 | 6.4698 | 2.1365 | 2.2048 | 2.7751 | 2.865 | 8.0239 | 3.5875 | 16.5653 | 18.7701 | 26.794 | 30.3815 | 10.0956 | 6.4798 | 2.1365 | 2.2048 | 2.7751 | 2.865 | 8.0239 | 3.5875 | 16.5753 | 18.7801 | 26.804 | 30.3915 | 0.01
4.6504 | 8.8874 | 1.955 | 1.9325 | 4.5711 | 3.9427 | 6.6626 | 5.8191 | 13.5378 | 15.4703 | 23.9841 | 29.8032 | 4.6504 | 8.8974 | 1.955 | 1.9325 | 4.5711 | 3.9427 | 6.6626 | 5.8191 | 13.5478 | 15.4803 | 23.9941 | 29.8132 | 0.01
15.4267 | 7.7076 | 2.3142 | 2.4713 | 4.305 | 3.783 | 9.3567 | 4.7301 | 23.1343 | 25.6057 | 34.9624 | 39.6924 | 15.4267 | 7.7176 | 2.3142 | 2.4713 | 4.305 | 3.783 | 9.3567 | 4.7301 | 23.1443 | 25.6157 | 34.9724 | 39.7024 | 0.01
13.8297 | 10.0425 | 2.261 | 2.3915 | 2.4924 | 2.6954 | 8.9574 | 6.8853 | 23.8722 | 26.2637 | 35.2211 | 42.1065 | 13.8297 | 10.0525 | 2.261 | 2.3915 | 2.4924 | 2.6954 | 8.9574 | 6.8853 | 23.8822 | 26.2737 | 35.2311 | 42.1165 | 0.01
2.9545 | 9.6964 | 1.8985 | 1.8477 | 3.7825 | 3.4695 | 6.2386 | 6.5659 | 12.6509 | 14.4986 | 21.7506 | 28.3166 | 2.9545 | 9.7064 | 1.8985 | 1.8477 | 3.7825 | 3.4695 | 6.2386 | 6.5659 | 12.6609 | 14.5086 | 21.7606 | 28.3266 | 0.01
10.6949 | 7.3401 | 2.1565 | 2.2347 | 2.8622 | 2.9173 | 8.1737 | 4.3909 | 18.035 | 20.2698 | 28.4435 | 32.8344 | 10.6949 | 7.3501 | 2.1565 | 2.2347 | 2.8622 | 2.9173 | 8.1737 | 4.3909 | 18.045 | 20.2798 | 28.4535 | 32.8444 | 0.01
5.1733 | 9.0172 | 1.9724 | 1.9587 | 3.1984 | 3.119 | 6.7933 | 5.939 | 14.1905 | 16.1492 | 22.9425 | 28.8815 | 5.1733 | 9.0272 | 1.9724 | 1.9587 | 3.1984 | 3.119 | 6.7933 | 5.939 | 14.2005 | 16.1592 | 22.9525 | 28.8915 | 0.01
7.1904 | 7.8209 | 2.0397 | 2.0595 | 1.3371 | 2.0022 | 7.2976 | 4.8347 | 15.0112 | 17.0708 | 24.3683 | 29.203 | 7.1904 | 7.8309 | 2.0397 | 2.0595 | 1.3371 | 2.0022 | 7.2976 | 4.8347 | 15.0212 | 17.0808 | 24.3783 | 29.213 | 0.01
-3.9776 | 8.2579 | 1.6674 | 1.5011 | 2.9624 | 2.9775 | 4.5056 | 5.2381 | 4.2803 | 5.7815 | 11.7213 | 16.9594 | -3.9776 | 8.2679 | 1.6674 | 1.5011 | 2.9624 | 2.9775 | 4.5056 | 5.2381 | 4.2903 | 5.7915 | 11.7313 | 16.9694 | 0.01
5.7745 | 5.8382 | 1.9925 | 1.9887 | 3.2345 | 3.1407 | 6.9436 | 3.0045 | 11.6127 | 13.6015 | 20.5451 | 23.5496 | 5.7745 | 5.8482 | 1.9925 | 1.9887 | 3.2345 | 3.1407 | 6.9436 | 3.0045 | 11.6227 | 13.6115 | 20.5551 | 23.5596 | 0.01
7.4073 | 7.9511 | 2.0469 | 2.0704 | 3.9585 | 3.5751 | 7.3518 | 4.9549 | 15.3584 | 17.4288 | 24.9625 | 29.9174 | 7.4073 | 7.9611 | 2.0469 | 2.0704 | 3.9585 | 3.5751 | 7.3518 | 4.9549 | 15.3684 | 17.4388 | 24.9725 | 29.9274 | 0.01
11.7513 | 8.3049 | 2.1917 | 2.2876 | 2.7908 | 2.8745 | 8.4378 | 5.2815 | 20.0562 | 22.3438 | 30.7816 | 36.063 | 11.7513 | 8.3149 | 2.1917 | 2.2876 | 2.7908 | 2.8745 | 8.4378 | 5.2815 | 20.0662 | 22.3538 | 30.7916 | 36.073 | 0.01
4.7449 | 9.2461 | 1.9582 | 1.9372 | 1.7315 | 2.2389 | 6.6862 | 6.1503 | 13.991 | 15.9283 | 22.6145 | 28.7648 | 4.7449 | 9.2561 | 1.9582 | 1.9372 | 1.7315 | 2.2389 | 6.6862 | 6.1503 | 14.001 | 15.9383 | 22.6245 | 28.7748 | 0.01
-1.6111 | 7.7281 | 1.7463 | 1.6194 | 2.8944 | 2.9366 | 5.0972 | 4.749 | 6.1169 | 7.7364 | 13.5674 | 18.3163 | -1.6111 | 7.7381 | 1.7463 | 1.6194 | 2.8944 | 2.9366 | 5.0972 | 4.749 | 6.1269 | 7.7464 | 13.5774 | 18.3263 | 0.01
5.3662 | 6.3509 | 1.9789 | 1.9683 | 3.0773 | 3.0464 | 6.8415 | 3.4778 | 11.7171 | 13.6854 | 20.527 | 24.0047 | 5.3662 | 6.3609 | 1.9789 | 1.9683 | 3.0773 | 3.0464 | 6.8415 | 3.4778 | 11.7271 | 13.6954 | 20.537 | 24.0147 | 0.01
6.4638 | 7.8627 | 2.0155 | 2.0232 | 2.5815 | 2.7489 | 7.116 | 4.8732 | 14.3265 | 16.3497 | 23.4657 | 28.3389 | 6.4638 | 7.8727 | 2.0155 | 2.0232 | 2.5815 | 2.7489 | 7.116 | 4.8732 | 14.3365 | 16.3597 | 23.4757 | 28.3489 | 0.01
3.4889 | 8.1005 | 1.9163 | 1.8744 | 1.8665 | 2.3199 | 6.3722 | 5.0928 | 11.5894 | 13.4638 | 19.836 | 24.9288 | 3.4889 | 8.1105 | 1.9163 | 1.8744 | 1.8665 | 2.3199 | 6.3722 | 5.0928 | 11.5994 | 13.4738 | 19.846 | 24.9388 | 0.01
-0.80079 | 7.4559 | 1.7733 | 1.66 | 4.0774 | 3.6465 | 5.2998 | 4.4978 | 6.6551 | 8.3151 | 16.039 | 20.5368 | -0.80079 | 7.4659 | 1.7733 | 1.66 | 4.0774 | 3.6465 | 5.2998 | 4.4978 | 6.6651 | 8.3251 | 16.049 | 20.5468 | 0.01
12.4646 | 6.5265 | 2.2155 | 2.3232 | 2.1699 | 2.5019 | 8.6161 | 3.6398 | 18.9911 | 21.3143 | 29.9305 | 33.5703 | 12.4646 | 6.5365 | 2.2155 | 2.3232 | 2.1699 | 2.5019 | 8.6161 | 3.6398 | 19.0011 | 21.3243 | 29.9405 | 33.5803 | 0.01
1.0194 | 9.4007 | 1.834 | 1.751 | 4.2351 | 3.7411 | 5.7549 | 6.2929 | 10.4201 | 12.1711 | 20.1472 | 26.4401 | 1.0194 | 9.4107 | 1.834 | 1.751 | 4.2351 | 3.7411 | 5.7549 | 6.2929 | 10.4301 | 12.1811 | 20.1572 | 26.4501 | 0.01
13.4105 | 6.9209 | 2.247 | 2.3705 | 1.9519 | 2.3711 | 8.8526 | 4.0039 | 20.3314 | 22.7019 | 31.5546 | 35.5585 | 13.4105 | 6.9309 | 2.247 | 2.3705 | 1.9519 | 2.3711 | 8.8526 | 4.0039 | 20.3414 | 22.7119 | 31.5646 | 35.5685 | 0.01
-0.28881 | 9.6056 | 1.7904 | 1.6856 | 2.9194 | 2.9516 | 5.4278 | 6.4821 | 9.3168 | 11.0024 | 16.8734 | 23.3555 | -0.28881 | 9.6156 | 1.7904 | 1.6856 | 2.9194 | 2.9516 | 5.4278 | 6.4821 | 9.3268 | 11.0124 | 16.8834 | 23.3655 | 0.01
5.5165 | 6.6374 | 1.9839 | 1.9758 | 3.7465 | 3.4479 | 6.8791 | 3.7422 | 12.1539 | 14.1297 | 21.3241 | 25.0664 | 5.5165 | 6.6474 | 1.9839 | 1.9758 | 3.7465 | 3.4479 | 6.8791 | 3.7422 | 12.1639 | 14.1397 | 21.3341 | 25.0764 | 0.01
10.479 | 7.8952 | 2.1493 | 2.2239 | 2.4963 | 2.6978 | 8.1197 | 4.9033 | 18.3742 | 20.5982 | 28.7179 | 33.6212 | 10.479 | 7.9052 | 2.1493 | 2.2239 | 2.4963 | 2.6978 | 8.1197 | 4.9033 | 18.3842 | 20.6082 | 28.7279 | 33.6312 | 0.01
2.978 | 8.9704 | 1.8993 | 1.8489 | 4.1729 | 3.7037 | 6.2445 | 5.8958 | 11.9484 | 13.7973 | 21.6739 | 27.5697 | 2.978 | 8.9804 | 1.8993 | 1.8489 | 4.1729 | 3.7037 | 6.2445 | 5.8958 | 11.9584 | 13.8073 | 21.6839 | 27.5797 | 0.01
13.0371 | 7.3452 | 2.2346 | 2.3519 | 5.043 | 4.2258 | 8.7593 | 4.3956 | 20.3823 | 22.7342 | 32.0031 | 36.3986 | 13.0371 | 7.3552 | 2.2346 | 2.3519 | 5.043 | 4.2258 | 8.7593 | 4.3956 | 20.3923 | 22.7442 | 32.0131 | 36.4086 | 0.01
18.2582 | 9.5247 | 2.4086 | 2.6129 | 1.3136 | 1.9881 | 10.0646 | 6.4074 | 27.7829 | 30.3958 | 40.4604 | 46.8678 | 18.2582 | 9.5347 | 2.4086 | 2.6129 | 1.3136 | 1.9881 | 10.0646 | 6.4074 | 27.7929 | 30.4058 | 40.4704 | 46.8778 | 0.01
-4.1186 | 10.6559 | 1.6627 | 1.4941 | 3.5481 | 3.3289 | 4.4704 | 7.4516 | 6.5374 | 8.0314 | 14.9084 | 22.36 | -4.1186 | 10.6659 | 1.6627 | 1.4941 | 3.5481 | 3.3289 | 4.4704 | 7.4516 | 6.5474 | 8.0414 | 14.9184 | 22.37 | 0.01
9.2885 | 5.8076 | 2.1096 | 2.1644 | 2.9226 | 2.9536 | 7.8221 | 2.9763 | 15.0962 | 17.2606 | 25.0828 | 28.059 | 9.2885 | 5.8176 | 2.1096 | 2.1644 | 2.9226 | 2.9536 | 7.8221 | 2.9763 | 15.1062 | 17.2706 | 25.0928 | 28.069 | 0.01
5.5355 | 8.7125 | 1.9845 | 1.9768 | 5.2821 | 4.3692 | 6.8839 | 5.6577 | 14.2481 | 16.2248 | 25.8761 | 31.5339 | 5.5355 | 8.7225 | 1.9845 | 1.9768 | 5.2821 | 4.3692 | 6.8839 | 5.6577 | 14.2581 | 16.2348 | 25.8861 | 31.5439 | 0.01
19.6924 | 7.8994 | 2.4564 | 2.6846 | 1.3027 | 1.9816 | 10.4231 | 4.9071 | 27.5918 | 30.2764 | 40.6995 | 45.6066 | 19.6924 | 7.9094 | 2.4564 | 2.6846 | 1.3027 | 1.9816 | 10.4231 | 4.9071 | 27.6018 | 30.2864 | 40.7095 | 45.6166 | 0.01
-4.1837 | 10.9667 | 1.6605 | 1.4908 | 2.4833 | 2.69 | 4.4541 | 7.7385 | 6.7829 | 8.2738 | 13.447 | 21.1855 | -4.1837 | 10.9767 | 1.6605 | 1.4908 | 2.4833 | 2.69 | 4.4541 | 7.7385 | 6.7929 | 8.2838 | 13.457 | 21.1955 | 0.01
2.8996 | 5.7935 | 1.8967 | 1.845 | 4.6737 | 4.0042 | 6.2249 | 2.9633 | 8.6931 | 10.5381 | 19.216 | 22.1792 | 2.8996 | 5.8035 | 1.8967 | 1.845 | 4.6737 | 4.0042 | 6.2249 | 2.9633 | 8.7031 | 10.5481 | 19.226 | 22.1892 | 0.01
16.0422 | 7.3282 | 2.3347 | 2.5021 | 2.969 | 2.9814 | 9.5106 | 4.3799 | 23.3705 | 25.8726 | 35.3831 | 39.7631 | 16.0422 | 7.3382 | 2.3347 | 2.5021 | 2.969 | 2.9814 | 9.5106 | 4.3799 | 23.3805 | 25.8826 | 35.3931 | 39.7731 | 0.01
5.8138 | 10.1758 | 1.9938 | 1.9907 | 2.7846 | 2.8708 | 6.9534 | 7.0084 | 15.9896 | 17.9803 | 24.9337 | 31.9422 | 5.8138 | 10.1858 | 1.9938 | 1.9907 | 2.7846 | 2.8708 | 6.9534 | 7.0084 | 15.9996 | 17.9903 | 24.9437 | 31.9522 | 0.01
4.7076 | 7.9596 | 1.9569 | 1.9354 | 2.5954 | 2.7572 | 6.6769 | 4.9628 | 12.6673 | 14.6026 | 21.2795 | 26.2423 | 4.7076 | 7.9696 | 1.9569 | 1.9354 | 2.5954 | 2.7572 | 6.6769 | 4.9628 | 12.6773 | 14.6126 | 21.2895 | 26.2523 | 0.01
3.5724 | 7.72 | 1.9191 | 1.8786 | 4.397 | 3.8382 | 6.3931 | 4.7415 | 11.2924 | 13.171 | 21.4063 | 26.1478 | 3.5724 | 7.73 | 1.9191 | 1.8786 | 4.397 | 3.8382 | 6.3931 | 4.7415 | 11.3024 | 13.181 | 21.4163 | 26.1578 | 0.01
14.3822 | 7.474 | 2.2794 | 2.4191 | 2.2841 | 2.5705 | 9.0955 | 4.5145 | 21.8562 | 24.2753 | 33.3709 | 37.8854 | 14.3822 | 7.484 | 2.2794 | 2.4191 | 2.2841 | 2.5705 | 9.0955 | 4.5145 | 21.8662 | 24.2853 | 33.3809 | 37.8954 | 0.01
1.7047 | 9.8161 | 1.8568 | 1.7852 | 3.83 | 3.498 | 5.9262 | 6.6764 | 11.5209 | 13.3061 | 20.6341 | 27.3105 | 1.7047 | 9.8261 | 1.8568 | 1.7852 | 3.83 | 3.498 | 5.9262 | 6.6764 | 11.5309 | 13.3161 | 20.6441 | 27.3205 | 0.01
10.98 | 7.0694 | 2.166 | 2.249 | 3.431 | 3.2586 | 8.245 | 4.1409 | 18.0494 | 20.2984 | 28.5434 | 32.6843 | 10.98 | 7.0794 | 2.166 | 2.249 | 3.431 | 3.2586 | 8.245 | 4.1409 | 18.0594 | 20.3084 | 28.5534 | 32.6943 | 0.01
8.5858 | 9.079 | 2.0862 | 2.1293 | 2.0667 | 2.44 | 7.6465 | 5.996 | 17.6648 | 19.7941 | 27.4406 | 33.4366 | 8.5858 | 9.089 | 2.0862 | 2.1293 | 2.0667 | 2.44 | 7.6465 | 5.996 | 17.6748 | 19.8041 | 27.4506 | 33.4466 | 0.01
0.40007 | 8.5603 | 1.8133 | 1.72 | 3.5941 | 3.3565 | 5.6 | 5.5172 | 8.9603 | 10.6803 | 17.6309 | 23.1481 | 0.40007 | 8.5703 | 1.8133 | 1.72 | 3.5941 | 3.3565 | 5.6 | 5.5172 | 8.9703 | 10.6903 | 17.6409 | 23.1581 | 0.01
9.5647 | 6.7867 | 2.1188 | 2.1782 | 3.2553 | 3.1532 | 7.8912 | 3.88 | 16.3514 | 18.5296 | 26.4208 | 30.3008 | 9.5647 | 6.7967 | 2.1188 | 2.1782 | 3.2553 | 3.1532 | 7.8912 | 3.88 | 16.3614 | 18.5396 | 26.4308 | 30.3108 | 0.01
7.5316 | 8.7723 | 2.0511 | 2.0766 | 3.3519 | 3.2111 | 7.3829 | 5.7129 | 16.3039 | 18.3805 | 25.7634 | 31.4763 | 7.5316 | 8.7823 | 2.0511 | 2.0766 | 3.3519 | 3.2111 | 7.3829 | 5.7129 | 16.3139 | 18.3905 | 25.7734 | 31.4863 | 0.01
8.1115 | 8.3318 | 2.0704 | 2.1056 | 2.3366 | 2.602 | 7.5279 | 5.3063 | 16.4433 | 18.5489 | 26.0767 | 31.3831 | 8.1115 | 8.3418 | 2.0704 | 2.1056 | 2.3366 | 2.602 | 7.5279 | 5.3063 | 16.4533 | 18.5589 | 26.0867 | 31.3931 | 0.01
2.0197 | 8.4575 | 1.8673 | 1.801 | 2.4549 | 2.6729 | 6.0049 | 5.4223 | 10.4772 | 12.2782 | 18.2831 | 23.7054 | 2.0197 | 8.4675 | 1.8673 | 1.801 | 2.4549 | 2.6729 | 6.0049 | 5.4223 | 10.4872 | 12.2882 | 18.2931 | 23.7154 | 0.01
2.7292 | 7.1376 | 1.891 | 1.8365 | 3.3007 | 3.1804 | 6.1823 | 4.2039 | 9.8668 | 11.7033 | 18.1844 | 22.3883 | 2.7292 | 7.1476 | 1.891 | 1.8365 | 3.3007 | 3.1804 | 6.1823 | 4.2039 | 9.8768 | 11.7133 | 18.1944 | 22.3983 | 0.01
7.8041 | 7.2913 | 2.0601 | 2.0902 | 3.2421 | 3.1452 | 7.451 | 4.3458 | 15.0954 | 17.1856 | 24.6366 | 28.9825 | 7.8041 | 7.3013 | 2.0601 | 2.0902 | 3.2421 | 3.1452 | 7.451 | 4.3458 | 15.1054 | 17.1956 | 24.6466 | 28.9925 | 0.01
7.4524 | 8.3909 | 2.0484 | 2.0726 | 3.8806 | 3.5284 | 7.3631 | 5.3608 | 15.8432 | 17.9159 | 25.3248 | 30.6856 | 7.4524 | 8.4009 | 2.0484 | 2.0726 | 3.8806 | 3.5284 | 7.3631 | 5.3608 | 15.8532 | 17.9259 | 25.3348 | 30.6956 | 0.01
11.2836 | 8.3147 | 2.1761 | 2.2642 | 5.2907 | 4.3744 | 8.3209 | 5.2905 | 19.5983 | 21.8625 | 31.5276 | 36.8181 | 11.2836 | 8.3247 | 2.1761 | 2.2642 | 5.2907 | 4.3744 | 8.3209 | 5.2905 | 19.6083 | 21.8725 | 31.5376 | 36.8281 | 0.01
19.7442 | 9.1448 | 2.4581 | 2.6872 | 2.4446 | 2.6667 | 10.4361 | 6.0567 | 28.889 | 31.5762 | 42.0123 | 48.069 | 19.7442 | 9.1548 | 2.4581 | 2.6872 | 2.4446 | 2.6667 | 10.4361 | 6.0567 | 28.899 | 31.5862 | 42.0223 | 48.079 | 0.01
2.6675 | 10.9779 | 1.8889 | 1.8334 | 2.5403 | 2.7242 | 6.1669 | 7.7488 | 13.6454 | 15.4788 | 21.6456 | 29.3945 | 2.6675 | 10.9879 | 1.8889 | 1.8334 | 2.5403 | 2.7242 | 6.1669 | 7.7488 | 13.6554 | 15.4888 | 21.6556 | 29.4045 | 0.01
3.2415 | 7.278 | 1.9081 | 1.8621 | 1.9326 | 2.3596 | 6.3104 | 4.3335 | 10.5195 | 12.3816 | 18.692 | 23.0255 | 3.2415 | 7.288 | 1.9081 | 1.8621 | 1.9326 | 2.3596 | 6.3104 | 4.3335 | 10.5295 | 12.3916 | 18.702 | 23.0355 | 0.01
-0.40435 | 7.4023 | 1.7865 | 1.6798 | 3.4463 | 3.2678 | 5.3989 | 4.4483 | 6.998 | 8.6778 | 15.3919 | 19.8402 | -0.40435 | 7.4123 | 1.7865 | 1.6798 | 3.4463 | 3.2678 | 5.3989 | 4.4483 | 7.008 | 8.6878 | 15.4019 | 19.8502 | 0.01
1

## test activity C
A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | diff
-12.9745 | 3.8889 | 1.3675 | 1.0513 | -0.16242 | 1.1025 | 2.2564 | 1.2051 | -9.0857 | -8.0344 | -5.778 | -4.5729 | -12.9745 | 3.8889 | 1.3775 | 1.0513 | -0.16242 | 1.1025 | 2.2564 | 1.2051 | -9.0857 | -8.0344 | -5.778 | -4.5729 | 0
-0.12216 | 6.6735 | 1.7959 | 1.6939 | 1.9796 | 2.3878 | 5.4695 | 3.7756 | 6.5514 | 8.2453 | 13.7147 | 17.4903 | -0.12216 | 6.6735 | 1.8059 | 1.6939 | 1.9796 | 2.3878 | 5.4695 | 3.7756 | 6.5514 | 8.2453 | 13.7147 | 17.4903 | 0
6.9139 | 8.198 | 2.0305 | 2.0457 | 3.1523 | 3.0914 | 7.2285 | 5.1828 | 15.1119 | 17.1576 | 24.3861 | 29.5689 | 6.9139 | 8.198 | 2.0405 | 2.0457 | 3.1523 | 3.0914 | 7.2285 | 5.1828 | 15.1119 | 17.1576 | 24.3861 | 29.5689 | 0
12.6187 | 9.4341 | 2.2206 | 2.3309 | 4.1031 | 3.6619 | 8.6547 | 6.3237 | 22.0528 | 24.3837 | 33.0384 | 39.3622 | 12.6187 | 9.4341 | 2.2306 | 2.3309 | 4.1031 | 3.6619 | 8.6547 | 6.3237 | 22.0528 | 24.3837 | 33.0384 | 39.3622 | 0
2.4444 | 7.2296 | 1.8815 | 1.8222 | 2.4074 | 2.6444 | 6.1111 | 4.2889 | 9.674 | 11.4962 | 17.6073 | 21.8962 | 2.4444 | 7.2296 | 1.8915 | 1.8222 | 2.4074 | 2.6444 | 6.1111 | 4.2889 | 9.674 | 11.4962 | 17.6073 | 21.8962 | 0
13.5518 | 9.6362 | 2.2517 | 2.3776 | 4.2586 | 3.7552 | 8.888 | 6.5104 | 23.188 | 25.5656 | 34.4536 | 40.9639 | 13.5518 | 9.6362 | 2.2617 | 2.3776 | 4.2586 | 3.7552 | 8.888 | 6.5104 | 23.188 | 25.5656 | 34.4536 | 40.9639 | 0
9.2237 | 8.6985 | 2.1075 | 2.1612 | 3.5373 | 3.3224 | 7.8059 | 5.6447 | 17.9221 | 20.0833 | 27.8892 | 33.5339 | 9.2237 | 8.6985 | 2.1175 | 2.1612 | 3.5373 | 3.3224 | 7.8059 | 5.6447 | 17.9221 | 20.0833 | 27.8892 | 33.5339 | 0
13.2479 | 9.5704 | 2.2416 | 2.3624 | 4.208 | 3.7248 | 8.812 | 6.4496 | 22.8182 | 25.1806 | 33.9926 | 40.4422 | 13.2479 | 9.5704 | 2.2516 | 2.3624 | 4.208 | 3.7248 | 8.812 | 6.4496 | 22.8182 | 25.1806 | 33.9926 | 40.4422 | 0
14.8387 | 9.9151 | 2.2946 | 2.4419 | 4.4731 | 3.8839 | 9.2097 | 6.7677 | 24.7538 | 27.1957 | 36.4054 | 43.1731 | 14.8387 | 9.9151 | 2.3046 | 2.4419 | 4.4731 | 3.8839 | 9.2097 | 6.7677 | 24.7538 | 27.1957 | 36.4054 | 43.1731 | 0
5.5377 | 7.8998 | 1.9846 | 1.9769 | 2.9229 | 2.9538 | 6.8844 | 4.9075 | 13.4375 | 15.4144 | 22.2988 | 27.2063 | 5.5377 | 7.8998 | 1.9946 | 1.9769 | 2.9229 | 2.9538 | 6.8844 | 4.9075 | 13.4375 | 15.4144 | 22.2988 | 27.2063 | 0
3.6914 | 7.4998 | 1.923 | 1.8846 | 2.6152 | 2.7691 | 6.4229 | 4.5383 | 11.1913 | 13.0758 | 19.4987 | 24.037 | 3.6914 | 7.4998 | 1.933 | 1.8846 | 2.6152 | 2.7691 | 6.4229 | 4.5383 | 11.1913 | 13.0758 | 19.4987 | 24.037 | 0
15.412 | 10.0393 | 2.3137 | 2.4706 | 4.5687 | 3.9412 | 9.353 | 6.8824 | 25.4513 | 27.9219 | 37.2749 | 44.1573 | 15.412 | 10.0393 | 2.3237 | 2.4706 | 4.5687 | 3.9412 | 9.353 | 6.8824 | 25.4513 | 27.9219 | 37.2749 | 44.1573 | 0
-1.8093 | 6.308 | 1.7397 | 1.6095 | 1.6984 | 2.2191 | 5.0477 | 3.4381 | 4.4986 | 6.1082 | 11.1558 | 14.594 | -1.8093 | 6.308 | 1.7497 | 1.6095 | 1.6984 | 2.2191 | 5.0477 | 3.4381 | 4.4986 | 6.1082 | 11.1558 | 14.594 | 0
5.3552 | 7.8603 | 1.9785 | 1.9678 | 2.8925 | 2.9355 | 6.8388 | 4.871 | 13.2155 | 15.1833 | 22.0221 | 26.8931 | 5.3552 | 7.8603 | 1.9885 | 1.9678 | 2.8925 | 2.9355 | 6.8388 | 4.871 | 13.2155 | 15.1833 | 22.0221 | 26.8931 | 0
3.6258 | 7.4856 | 1.9209 | 1.8813 | 2.6043 | 2.7626 | 6.4065 | 4.5252 | 11.1114 | 12.9927 | 19.3991 | 23.9243 | 3.6258 | 7.4856 | 1.9309 | 1.8813 | 2.6043 | 2.7626 | 6.4065 | 4.5252 | 11.1114 | 12.9927 | 19.3991 | 23.9243 | 0
17.2865 | 10.4454 | 2.3762 | 2.5643 | 4.8811 | 4.1286 | 9.8216 | 7.2573 | 27.7319 | 30.2962 | 40.1178 | 47.3751 | 17.2865 | 10.4454 | 2.3862 | 2.5643 | 4.8811 | 4.1286 | 9.8216 | 7.2573 | 27.7319 | 30.2962 | 40.1178 | 47.3751 | 0
-1.2041 | 6.4391 | 1.7599 | 1.6398 | 1.7993 | 2.2796 | 5.199 | 3.5592 | 5.2351 | 6.8749 | 12.0738 | 15.633 | -1.2041 | 6.4391 | 1.7699 | 1.6398 | 1.7993 | 2.2796 | 5.199 | 3.5592 | 5.2351 | 6.8749 | 12.0738 | 15.633 | 0
10.4295 | 8.9597 | 2.1476 | 2.2215 | 3.7382 | 3.4429 | 8.1074 | 5.8859 | 19.3892 | 21.6107 | 29.7181 | 35.604 | 10.4295 | 8.9597 | 2.1576 | 2.2215 | 3.7382 | 3.4429 | 8.1074 | 5.8859 | 19.3892 | 21.6107 | 29.7181 | 35.604 | 0
3.5508 | 7.4693 | 1.9184 | 1.8775 | 2.5918 | 2.7551 | 6.3877 | 4.5102 | 11.0202 | 12.8977 | 19.2854 | 23.7956 | 3.5508 | 7.4693 | 1.9284 | 1.8775 | 2.5918 | 2.7551 | 6.3877 | 4.5102 | 11.0202 | 12.8977 | 19.2854 | 23.7956 | 0
8.8773 | 8.6234 | 2.0959 | 2.1439 | 3.4795 | 3.2877 | 7.7193 | 5.5755 | 17.5007 | 19.6445 | 27.3638 | 32.9393 | 8.8773 | 8.6234 | 2.1059 | 2.1439 | 3.4795 | 3.2877 | 7.7193 | 5.5755 | 17.5007 | 19.6445 | 27.3638 | 32.9393 | 0
10.0205 | 8.8711 | 2.134 | 2.201 | 3.6701 | 3.402 | 8.0051 | 5.8041 | 18.8916 | 21.0926 | 29.0977 | 34.9018 | 10.0205 | 8.8711 | 2.144 | 2.201 | 3.6701 | 3.402 | 8.0051 | 5.8041 | 18.8916 | 21.0926 | 29.0977 | 34.9018 | 0
8.7605 | 8.5981 | 2.092 | 2.138 | 3.4601 | 3.276 | 7.6901 | 5.5521 | 17.3586 | 19.4966 | 27.1867 | 32.7388 | 8.7605 | 8.5981 | 2.102 | 2.138 | 3.4601 | 3.276 | 7.6901 | 5.5521 | 17.3586 | 19.4966 | 27.1867 | 32.7388 | 0
13.6101 | 9.6489 | 2.2537 | 2.3805 | 4.2684 | 3.761 | 8.9025 | 6.522 | 23.259 | 25.6395 | 34.542 | 41.064 | 13.6101 | 9.6489 | 2.2637 | 2.3805 | 4.2684 | 3.761 | 8.9025 | 6.522 | 23.259 | 25.6395 | 34.542 | 41.064 | 0
-4.2589 | 5.7772 | 1.658 | 1.4871 | 1.2902 | 1.9741 | 4.4353 | 2.9482 | 1.5183 | 3.0053 | 7.4406 | 10.3888 | -4.2589 | 5.7772 | 1.668 | 1.4871 | 1.2902 | 1.9741 | 4.4353 | 2.9482 | 1.5183 | 3.0053 | 7.4406 | 10.3888 | 0
7.7808 | 8.3858 | 2.0594 | 2.089 | 3.2968 | 3.1781 | 7.4452 | 5.3562 | 16.1666 | 18.2557 | 25.7008 | 31.057 | 7.7808 | 8.3858 | 2.0694 | 2.089 | 3.2968 | 3.1781 | 7.4452 | 5.3562 | 16.1666 | 18.2557 | 25.7008 | 31.057 | 0
9.0241 | 8.6552 | 2.1008 | 2.1512 | 3.504 | 3.3024 | 7.756 | 5.6048 | 17.6794 | 19.8306 | 27.5866 | 33.1914 | 9.0241 | 8.6552 | 2.1108 | 2.1512 | 3.504 | 3.3024 | 7.756 | 5.6048 | 17.6794 | 19.8306 | 27.5866 | 33.1914 | 0
0.87462 | 6.8895 | 1.8292 | 1.7437 | 2.1458 | 2.4875 | 5.7187 | 3.9749 | 7.7641 | 9.5079 | 15.2265 | 19.2014 | 0.87462 | 6.8895 | 1.8392 | 1.7437 | 2.1458 | 2.4875 | 5.7187 | 3.9749 | 7.7641 | 9.5079 | 15.2265 | 19.2014 | 0
4.3537 | 7.6433 | 1.9451 | 1.9177 | 2.7256 | 2.8354 | 6.5884 | 4.6707 | 11.997 | 13.9147 | 20.5031 | 25.1739 | 4.3537 | 7.6433 | 1.9551 | 1.9177 | 2.7256 | 2.8354 | 6.5884 | 4.6707 | 11.997 | 13.9147 | 20.5031 | 25.1739 | 0
7.5191 | 8.3291 | 2.0506 | 2.076 | 3.2532 | 3.1519 | 7.3798 | 5.3038 | 15.8482 | 17.9242 | 25.3039 | 30.6078 | 7.5191 | 8.3291 | 2.0606 | 2.076 | 3.2532 | 3.1519 | 7.3798 | 5.3038 | 15.8482 | 17.9242 | 25.3039 | 30.6078 | 0
-1.0782 | 6.4664 | 1.7641 | 1.6461 | 1.8203 | 2.2922 | 5.2304 | 3.5844 | 5.3882 | 7.0343 | 12.2647 | 15.8491 | -1.0782 | 6.4664 | 1.7741 | 1.6461 | 1.8203 | 2.2922 | 5.2304 | 3.5844 | 5.3882 | 7.0343 | 12.2647 | 15.8491 | 0
-5.1061 | 5.5937 | 1.6298 | 1.4447 | 1.149 | 1.8894 | 4.2235 | 2.7788 | 0.48754 | 1.9322 | 6.1557 | 8.9345 | -5.1061 | 5.5937 | 1.6398 | 1.4447 | 1.149 | 1.8894 | 4.2235 | 2.7788 | 0.48754 | 1.9322 | 6.1557 | 8.9345 | 0
1.3629 | 6.9953 | 1.8454 | 1.7681 | 2.2271 | 2.5363 | 5.8407 | 4.0726 | 8.3582 | 10.1263 | 15.967 | 20.0396 | 1.3629 | 6.9953 | 1.8554 | 1.7681 | 2.2271 | 2.5363 | 5.8407 | 4.0726 | 8.3582 | 10.1263 | 15.967 | 20.0396 | 0
1.8639 | 7.1038 | 1.8621 | 1.7932 | 2.3106 | 2.5864 | 5.966 | 4.1728 | 8.9677 | 10.7609 | 16.7269 | 20.8996 | 1.8639 | 7.1038 | 1.8721 | 1.7932 | 2.3106 | 2.5864 | 5.966 | 4.1728 | 8.9677 | 10.7609 | 16.7269 | 20.8996 | 0
9.9802 | 8.8624 | 2.1327 | 2.199 | 3.6634 | 3.398 | 7.995 | 5.796 | 18.8426 | 21.0416 | 29.0366 | 34.8327 | 9.9802 | 8.8624 | 2.1427 | 2.199 | 3.6634 | 3.398 | 7.995 | 5.796 | 18.8426 | 21.0416 | 29.0366 | 34.8327 | 0
7.6476 | 8.357 | 2.0549 | 2.0824 | 3.2746 | 3.1648 | 7.4119 | 5.3295 | 16.0046 | 18.087 | 25.4989 | 30.8284 | 7.6476 | 8.357 | 2.0649 | 2.0824 | 3.2746 | 3.1648 | 7.4119 | 5.3295 | 16.0046 | 18.087 | 25.4989 | 30.8284 | 0
11.5709 | 9.207 | 2.1857 | 2.2785 | 3.9285 | 3.5571 | 8.3927 | 6.1142 | 20.778 | 23.0565 | 31.4492 | 37.5634 | 11.5709 | 9.207 | 2.1957 | 2.2785 | 3.9285 | 3.5571 | 8.3927 | 6.1142 | 20.778 | 23.0565 | 31.4492 | 37.5634 | 0
2.211 | 7.179 | 1.8737 | 1.8105 | 2.3685 | 2.6211 | 6.0527 | 4.2422 | 9.39 | 11.2006 | 17.2533 | 21.4955 | 2.211 | 7.179 | 1.8837 | 1.8105 | 2.3685 | 2.6211 | 6.0527 | 4.2422 | 9.39 | 11.2006 | 17.2533 | 21.4955 | 0
8.1676 | 8.4696 | 2.0723 | 2.1084 | 3.3613 | 3.2168 | 7.5419 | 5.4335 | 16.6372 | 18.7456 | 26.2875 | 31.721 | 8.1676 | 8.4696 | 2.0823 | 2.1084 | 3.3613 | 3.2168 | 7.5419 | 5.4335 | 16.6372 | 18.7456 | 26.2875 | 31.721 | 0
-1.5632 | 6.3613 | 1.7479 | 1.6218 | 1.7395 | 2.2437 | 5.1092 | 3.4874 | 4.7981 | 6.42 | 11.5292 | 15.0165 | -1.5632 | 6.3613 | 1.7579 | 1.6218 | 1.7395 | 2.2437 | 5.1092 | 3.4874 | 4.7981 | 6.42 | 11.5292 | 15.0165 | 0
6.51 | 8.1105 | 2.017 | 2.0255 | 3.085 | 3.051 | 7.1275 | 5.102 | 14.6205 | 16.646 | 23.7735 | 28.8754 | 6.51 | 8.1105 | 2.027 | 2.0255 | 3.085 | 3.051 | 7.1275 | 5.102 | 14.6205 | 16.646 | 23.7735 | 28.8754 | 0
9.2137 | 8.6963 | 2.1071 | 2.1607 | 3.5356 | 3.3214 | 7.8034 | 5.6427 | 17.91 | 20.0707 | 27.8741 | 33.5169 | 9.2137 | 8.6963 | 2.1171 | 2.1607 | 3.5356 | 3.3214 | 7.8034 | 5.6427 | 17.91 | 20.0707 | 27.8741 | 33.5169 | 0
2.0475 | 7.1436 | 1.8683 | 1.8024 | 2.3413 | 2.6048 | 6.0119 | 4.2095 | 9.1911 | 10.9935 | 17.0054 | 21.2149 | 2.0475 | 7.1436 | 1.8783 | 1.8024 | 2.3413 | 2.6048 | 6.0119 | 4.2095 | 9.1911 | 10.9935 | 17.0054 | 21.2149 | 0
2.251 | 7.1877 | 1.875 | 1.8125 | 2.3752 | 2.6251 | 6.0627 | 4.2502 | 9.4387 | 11.2513 | 17.314 | 21.5642 | 2.251 | 7.1877 | 1.885 | 1.8125 | 2.3752 | 2.6251 | 6.0627 | 4.2502 | 9.4387 | 11.2513 | 17.314 | 21.5642 | 0
3.4527 | 7.4481 | 1.9151 | 1.8726 | 2.5755 | 2.7453 | 6.3632 | 4.4905 | 10.9008 | 12.7734 | 19.1366 | 23.6272 | 3.4527 | 7.4481 | 1.9251 | 1.8726 | 2.5755 | 2.7453 | 6.3632 | 4.4905 | 10.9008 | 12.7734 | 19.1366 | 23.6272 | 0
-0.171 | 6.663 | 1.7943 | 1.6915 | 1.9715 | 2.3829 | 5.4573 | 3.7658 | 6.492 | 8.1834 | 13.6407 | 17.4065 | -0.171 | 6.663 | 1.8043 | 1.6915 | 1.9715 | 2.3829 | 5.4573 | 3.7658 | 6.492 | 8.1834 | 13.6407 | 17.4065 | 0
2.2975 | 7.1978 | 1.8766 | 1.8149 | 2.3829 | 2.6297 | 6.0744 | 4.2595 | 9.4953 | 11.3101 | 17.3845 | 21.644 | 2.2975 | 7.1978 | 1.8866 | 1.8149 | 2.3829 | 2.6297 | 6.0744 | 4.2595 | 9.4953 | 11.3101 | 17.3845 | 21.644 | 0
0.11826 | 6.7256 | 1.8039 | 1.7059 | 2.0197 | 2.4118 | 5.5296 | 3.8237 | 6.8439 | 8.5498 | 14.0794 | 17.903 | 0.11826 | 6.7256 | 1.8139 | 1.7059 | 2.0197 | 2.4118 | 5.5296 | 3.8237 | 6.8439 | 8.5498 | 14.0794 | 17.903 | 0
5.5591 | 7.9045 | 1.9853 | 1.978 | 2.9265 | 2.9559 | 6.8898 | 4.9118 | 13.4636 | 15.4416 | 22.3313 | 27.2432 | 5.5591 | 7.9045 | 1.9953 | 1.978 | 2.9265 | 2.9559 | 6.8898 | 4.9118 | 13.4636 | 15.4416 | 22.3313 | 27.2432 | 0
2.3412 | 7.2073 | 1.878 | 1.8171 | 2.3902 | 2.6341 | 6.0853 | 4.2682 | 9.5484 | 11.3655 | 17.4508 | 21.719 | 2.3412 | 7.2073 | 1.888 | 1.8171 | 2.3902 | 2.6341 | 6.0853 | 4.2682 | 9.5484 | 11.3655 | 17.4508 | 21.719 | 0
8.1691 | 8.47 | 2.0723 | 2.1085 | 3.3615 | 3.2169 | 7.5423 | 5.4338 | 16.639 | 18.7475 | 26.2897 | 31.7235 | 8.1691 | 8.47 | 2.0823 | 2.1085 | 3.3615 | 3.2169 | 7.5423 | 5.4338 | 16.639 | 18.7475 | 26.2897 | 31.7235 | 0
8.3035 | 8.4991 | 2.0768 | 2.1152 | 3.3839 | 3.2303 | 7.5759 | 5.4607 | 16.8026 | 18.9177 | 26.4936 | 31.9543 | 8.3035 | 8.4991 | 2.0868 | 2.1152 | 3.3839 | 3.2303 | 7.5759 | 5.4607 | 16.8026 | 18.9177 | 26.4936 | 31.9543 | 0
10.4961 | 8.9742 | 2.1499 | 2.2248 | 3.7493 | 3.4496 | 8.124 | 5.8992 | 19.4702 | 21.695 | 29.8191 | 35.7183 | 10.4961 | 8.9742 | 2.1599 | 2.2248 | 3.7493 | 3.4496 | 8.124 | 5.8992 | 19.4702 | 21.695 | 29.8191 | 35.7183 | 0
10.5815 | 8.9927 | 2.1527 | 2.2291 | 3.7636 | 3.4582 | 8.1454 | 5.9163 | 19.5742 | 21.8033 | 29.9486 | 35.8649 | 10.5815 | 8.9927 | 2.1627 | 2.2291 | 3.7636 | 3.4582 | 8.1454 | 5.9163 | 19.5742 | 21.8033 | 29.9486 | 35.8649 | 0
5.8599 | 7.9696 | 1.9953 | 1.993 | 2.9766 | 2.986 | 6.965 | 4.972 | 13.8295 | 15.8225 | 22.7875 | 27.7595 | 5.8599 | 7.9696 | 2.0053 | 1.993 | 2.9766 | 2.986 | 6.965 | 4.972 | 13.8295 | 15.8225 | 22.7875 | 27.7595 | 0
14.7012 | 9.8853 | 2.29 | 2.4351 | 4.4502 | 3.8701 | 9.1753 | 6.7402 | 24.5864 | 27.0215 | 36.1968 | 42.937 | 14.7012 | 9.8853 | 2.3 | 2.4351 | 4.4502 | 3.8701 | 9.1753 | 6.7402 | 24.5864 | 27.0215 | 36.1968 | 42.937 | 0
8.3236 | 8.5034 | 2.0775 | 2.1162 | 3.3873 | 3.2324 | 7.5809 | 5.4647 | 16.827 | 18.9432 | 26.5241 | 31.9888 | 8.3236 | 8.5034 | 2.0875 | 2.1162 | 3.3873 | 3.2324 | 7.5809 | 5.4647 | 16.827 | 18.9432 | 26.5241 | 31.9888 | 0
8.3401 | 8.507 | 2.078 | 2.117 | 3.39 | 3.234 | 7.585 | 5.468 | 16.8471 | 18.9641 | 26.5492 | 32.0172 | 8.3401 | 8.507 | 2.088 | 2.117 | 3.39 | 3.234 | 7.585 | 5.468 | 16.8471 | 18.9641 | 26.5492 | 32.0172 | 0
10.3472 | 8.9419 | 2.1449 | 2.2174 | 3.7245 | 3.4347 | 8.0868 | 5.8694 | 19.289 | 21.5064 | 29.5932 | 35.4626 | 10.3472 | 8.9419 | 2.1549 | 2.2174 | 3.7245 | 3.4347 | 8.0868 | 5.8694 | 19.289 | 21.5064 | 29.5932 | 35.4626 | 0
14.4633 | 9.8337 | 2.2821 | 2.4232 | 4.4105 | 3.8463 | 9.1158 | 6.6927 | 24.297 | 26.7201 | 35.836 | 42.5286 | 14.4633 | 9.8337 | 2.2921 | 2.4232 | 4.4105 | 3.8463 | 9.1158 | 6.6927 | 24.297 | 26.7201 | 35.836 | 42.5286 | 0
-3.5127 | 5.9389 | 1.6829 | 1.5244 | 1.4146 | 2.0487 | 4.6218 | 3.0975 | 2.4263 | 3.9506 | 8.5725 | 11.6699 | -3.5127 | 5.9389 | 1.6929 | 1.5244 | 1.4146 | 2.0487 | 4.6218 | 3.0975 | 2.4263 | 3.9506 | 8.5725 | 11.6699 | 0
5.4776 | 7.8868 | 1.9826 | 1.9739 | 2.9129 | 2.9478 | 6.8694 | 4.8955 | 13.3644 | 15.3383 | 22.2077 | 27.1032 | 5.4776 | 7.8868 | 1.9926 | 1.9739 | 2.9129 | 2.9478 | 6.8694 | 4.8955 | 13.3644 | 15.3383 | 22.2077 | 27.1032 | 0
5.2807 | 7.8442 | 1.976 | 1.964 | 2.8801 | 2.9281 | 6.8202 | 4.8561 | 13.1249 | 15.0889 | 21.9091 | 26.7653 | 5.2807 | 7.8442 | 1.986 | 1.964 | 2.8801 | 2.9281 | 6.8202 | 4.8561 | 13.1249 | 15.0889 | 21.9091 | 26.7653 | 0
7.9784 | 8.4286 | 2.0659 | 2.0989 | 3.3297 | 3.1978 | 7.4946 | 5.3957 | 16.407 | 18.5059 | 26.0005 | 31.3962 | 7.9784 | 8.4286 | 2.0759 | 2.0989 | 3.3297 | 3.1978 | 7.4946 | 5.3957 | 16.407 | 18.5059 | 26.0005 | 31.3962 | 0
13.8033 | 9.6907 | 2.2601 | 2.3902 | 4.3006 | 3.7803 | 8.9508 | 6.5607 | 23.494 | 25.8842 | 34.835 | 41.3957 | 13.8033 | 9.6907 | 2.2701 | 2.3902 | 4.3006 | 3.7803 | 8.9508 | 6.5607 | 23.494 | 25.8842 | 34.835 | 41.3957 | 0
8.5439 | 8.5512 | 2.0848 | 2.1272 | 3.424 | 3.2544 | 7.636 | 5.5088 | 17.0951 | 19.2223 | 26.8583 | 32.367 | 8.5439 | 8.5512 | 2.0948 | 2.1272 | 3.424 | 3.2544 | 7.636 | 5.5088 | 17.0951 | 19.2223 | 26.8583 | 32.367 | 0
4.4437 | 7.6628 | 1.9481 | 1.9222 | 2.7406 | 2.8444 | 6.6109 | 4.6887 | 12.1065 | 14.0287 | 20.6396 | 25.3283 | 4.4437 | 7.6628 | 1.9581 | 1.9222 | 2.7406 | 2.8444 | 6.6109 | 4.6887 | 12.1065 | 14.0287 | 20.6396 | 25.3283 | 0
7.7456 | 8.3782 | 2.0582 | 2.0873 | 3.2909 | 3.1746 | 7.4364 | 5.3491 | 16.1238 | 18.2111 | 25.6475 | 30.9967 | 7.7456 | 8.3782 | 2.0682 | 2.0873 | 3.2909 | 3.1746 | 7.4364 | 5.3491 | 16.1238 | 18.2111 | 25.6475 | 30.9967 | 0
-2.7103 | 6.1128 | 1.7097 | 1.5645 | 1.5483 | 2.129 | 4.8224 | 3.2579 | 3.4024 | 4.9669 | 9.7893 | 13.0473 | -2.7103 | 6.1128 | 1.7197 | 1.5645 | 1.5483 | 2.129 | 4.8224 | 3.2579 | 3.4024 | 4.9669 | 9.7893 | 13.0473 | 0
10.561 | 8.9882 | 2.152 | 2.2281 | 3.7602 | 3.4561 | 8.1403 | 5.9122 | 19.5493 | 21.7773 | 29.9176 | 35.8298 | 10.561 | 8.9882 | 2.162 | 2.2281 | 3.7602 | 3.4561 | 8.1403 | 5.9122 | 19.5493 | 21.7773 | 29.9176 | 35.8298 | 0
4.0867 | 7.5855 | 1.9362 | 1.9043 | 2.6811 | 2.8087 | 6.5217 | 4.6173 | 11.6721 | 13.5765 | 20.0982 | 24.7155 | 4.0867 | 7.5855 | 1.9462 | 1.9043 | 2.6811 | 2.8087 | 6.5217 | 4.6173 | 11.6721 | 13.5765 | 20.0982 | 24.7155 | 0
-2.8232 | 6.0883 | 1.7059 | 1.5588 | 1.5295 | 2.1177 | 4.7942 | 3.2354 | 3.2652 | 4.824 | 9.6182 | 12.8536 | -2.8232 | 6.0883 | 1.7159 | 1.5588 | 1.5295 | 2.1177 | 4.7942 | 3.2354 | 3.2652 | 4.824 | 9.6182 | 12.8536 | 0
4.6997 | 7.7183 | 1.9567 | 1.935 | 2.7833 | 2.87 | 6.6749 | 4.7399 | 12.418 | 14.353 | 21.0279 | 25.7678 | 4.6997 | 7.7183 | 1.9667 | 1.935 | 2.7833 | 2.87 | 6.6749 | 4.7399 | 12.418 | 14.353 | 21.0279 | 25.7678 | 0
9.2885 | 8.7125 | 2.1096 | 2.1644 | 3.5481 | 3.3288 | 7.8221 | 5.6577 | 18.0009 | 20.1654 | 27.9875 | 33.6452 | 9.2885 | 8.7125 | 2.1196 | 2.1644 | 3.5481 | 3.3288 | 7.8221 | 5.6577 | 18.0009 | 20.1654 | 27.9875 | 33.6452 | 0
4.1946 | 7.6088 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5486 | 4.6389 | 11.8034 | 13.7131 | 20.2618 | 24.9007 | 4.1946 | 7.6088 | 1.9498 | 1.9097 | 2.6991 | 2.8195 | 6.5486 | 4.6389 | 11.8034 | 13.7131 | 20.2618 | 24.9007 | 0
17.7331 | 10.5422 | 2.3911 | 2.5867 | 4.9555 | 4.1733 | 9.9333 | 7.3466 | 28.2753 | 30.862 | 40.7953 | 48.1419 | 17.7331 | 10.5422 | 2.4011 | 2.5867 | 4.9555 | 4.1733 | 9.9333 | 7.3466 | 28.2753 | 30.862 | 40.7953 | 48.1419 | 0
5.1638 | 7.8188 | 1.9721 | 1.9582 | 2.8606 | 2.9164 | 6.791 | 4.8328 | 12.9827 | 14.9409 | 21.7318 | 26.5646 | 5.1638 | 7.8188 | 1.9821 | 1.9582 | 2.8606 | 2.9164 | 6.791 | 4.8328 | 12.9827 | 14.9409 | 21.7318 | 26.5646 | 0
-1.7584 | 6.319 | 1.7414 | 1.6121 | 1.7069 | 2.2242 | 5.0604 | 3.4483 | 4.5607 | 6.1727 | 11.2331 | 14.6815 | -1.7584 | 6.319 | 1.7514 | 1.6121 | 1.7069 | 2.2242 | 5.0604 | 3.4483 | 4.5607 | 6.1727 | 11.2331 | 14.6815 | 0
-8.3468 | 4.8915 | 1.5218 | 1.2827 | 0.60887 | 1.5653 | 3.4133 | 2.1306 | -3.4553 | -2.1726 | 1.2407 | 3.3713 | -8.3468 | 4.8915 | 1.5318 | 1.2827 | 0.60887 | 1.5653 | 3.4133 | 2.1306 | -3.4553 | -2.1726 | 1.2407 | 3.3713 | 0
-0.18201 | 6.6606 | 1.7939 | 1.6909 | 1.9697 | 2.3818 | 5.4545 | 3.7636 | 6.4786 | 8.1695 | 13.624 | 17.3876 | -0.18201 | 6.6606 | 1.8039 | 1.6909 | 1.9697 | 2.3818 | 5.4545 | 3.7636 | 6.4786 | 8.1695 | 13.624 | 17.3876 | 0
-6.2667 | 5.3422 | 1.5911 | 1.3867 | 0.95556 | 1.7733 | 3.9333 | 2.5467 | -0.92444 | 0.46223 | 4.3956 | 6.9422 | -6.2667 | 5.3422 | 1.6011 | 1.3867 | 0.95556 | 1.7733 | 3.9333 | 2.5467 | -0.92444 | 0.46223 | 4.3956 | 6.9422 | 0
10.6683 | 9.0115 | 2.1556 | 2.2334 | 3.778 | 3.4668 | 8.1671 | 5.9337 | 19.6798 | 21.9132 | 30.0803 | 36.0139 | 10.6683 | 9.0115 | 2.1656 | 2.2334 | 3.778 | 3.4668 | 8.1671 | 5.9337 | 19.6798 | 21.9132 | 30.0803 | 36.0139 | 0
6.5503 | 8.1192 | 2.0183 | 2.0275 | 3.0917 | 3.055 | 7.1376 | 5.1101 | 14.6695 | 16.697 | 23.8346 | 28.9447 | 6.5503 | 8.1192 | 2.0283 | 2.0275 | 3.0917 | 3.055 | 7.1376 | 5.1101 | 14.6695 | 16.697 | 23.8346 | 28.9447 | 0
7.3155 | 8.285 | 2.0438 | 2.0658 | 3.2192 | 3.1315 | 7.3289 | 5.2631 | 15.6005 | 17.6663 | 24.9951 | 30.2582 | 7.3155 | 8.285 | 2.0538 | 2.0658 | 3.2192 | 3.1315 | 7.3289 | 5.2631 | 15.6005 | 17.6663 | 24.9951 | 30.2582 | 0
12.1047 | 9.3227 | 2.2035 | 2.3052 | 4.0174 | 3.6105 | 8.5262 | 6.2209 | 21.4274 | 23.7326 | 32.2588 | 38.4797 | 12.1047 | 9.3227 | 2.2135 | 2.3052 | 4.0174 | 3.6105 | 8.5262 | 6.2209 | 21.4274 | 23.7326 | 32.2588 | 38.4797 | 0
11.6009 | 9.2135 | 2.1867 | 2.28 | 3.9335 | 3.5601 | 8.4002 | 6.1202 | 20.8144 | 23.0944 | 31.4947 | 37.6148 | 11.6009 | 9.2135 | 2.1967 | 2.28 | 3.9335 | 3.5601 | 8.4002 | 6.1202 | 20.8144 | 23.0944 | 31.4947 | 37.6148 | 0
16.131 | 10.195 | 2.3377 | 2.5065 | 4.6885 | 4.0131 | 9.5327 | 7.0262 | 26.326 | 28.8326 | 38.3653 | 45.3915 | 16.131 | 10.195 | 2.3477 | 2.5065 | 4.6885 | 4.0131 | 9.5327 | 7.0262 | 26.326 | 28.8326 | 38.3653 | 45.3915 | 0
7.8716 | 8.4055 | 2.0624 | 2.0936 | 3.3119 | 3.1872 | 7.4679 | 5.3743 | 16.2771 | 18.3706 | 25.8385 | 31.2128 | 7.8716 | 8.4055 | 2.0724 | 2.0936 | 3.3119 | 3.1872 | 7.4679 | 5.3743 | 16.2771 | 18.3706 | 25.8385 | 31.2128 | 0
6.6207 | 8.1345 | 2.0207 | 2.031 | 3.1035 | 3.0621 | 7.1552 | 5.1241 | 14.7552 | 16.7863 | 23.9415 | 29.0656 | 6.6207 | 8.1345 | 2.0307 | 2.031 | 3.1035 | 3.0621 | 7.1552 | 5.1241 | 14.7552 | 16.7863 | 23.9415 | 29.0656 | 0
15.6319 | 10.0869 | 2.3211 | 2.4816 | 4.6053 | 3.9632 | 9.408 | 6.9264 | 25.7188 | 28.2004 | 37.6084 | 44.5348 | 15.6319 | 10.0869 | 2.3311 | 2.4816 | 4.6053 | 3.9632 | 9.408 | 6.9264 | 25.7188 | 28.2004 | 37.6084 | 44.5348 | 0
12.4075 | 9.3883 | 2.2136 | 2.3204 | 4.0679 | 3.6408 | 8.6019 | 6.2815 | 21.7958 | 24.1162 | 32.7181 | 38.9996 | 12.4075 | 9.3883 | 2.2236 | 2.3204 | 4.0679 | 3.6408 | 8.6019 | 6.2815 | 21.7958 | 24.1162 | 32.7181 | 38.9996 | 0
3.1852 | 7.3901 | 1.9062 | 1.8593 | 2.5309 | 2.7185 | 6.2963 | 4.437 | 10.5753 | 12.4346 | 18.7309 | 23.168 | 3.1852 | 7.3901 | 1.9162 | 1.8593 | 2.5309 | 2.7185 | 6.2963 | 4.437 | 10.5753 | 12.4346 | 18.7309 | 23.168 | 0
8.0258 | 8.4389 | 2.0675 | 2.1013 | 3.3376 | 3.2026 | 7.5065 | 5.4052 | 16.4648 | 18.5661 | 26.0725 | 31.4777 | 8.0258 | 8.4389 | 2.0775 | 2.1013 | 3.3376 | 3.2026 | 7.5065 | 5.4052 | 16.4648 | 18.5661 | 26.0725 | 31.4777 | 0
-1.6375 | 6.3452 | 1.7454 | 1.6181 | 1.7271 | 2.2363 | 5.0906 | 3.4725 | 4.7078 | 6.3259 | 11.4165 | 14.889 | -1.6375 | 6.3452 | 1.7554 | 1.6181 | 1.7271 | 2.2363 | 5.0906 | 3.4725 | 4.7078 | 6.3259 | 11.4165 | 14.889 | 0
3.3169 | 7.4187 | 1.9106 | 1.8658 | 2.5528 | 2.7317 | 6.3292 | 4.4634 | 10.7355 | 12.6014 | 18.9306 | 23.394 | 3.3169 | 7.4187 | 1.9206 | 1.8658 | 2.5528 | 2.7317 | 6.3292 | 4.4634 | 10.7355 | 12.6014 | 18.9306 | 23.394 | 0
-1.316 | 6.4149 | 1.7561 | 1.6342 | 1.7807 | 2.2684 | 5.171 | 3.5368 | 5.0988 | 6.733 | 11.904 | 15.4408 | -1.316 | 6.4149 | 1.7661 | 1.6342 | 1.7807 | 2.2684 | 5.171 | 3.5368 | 5.0988 | 6.733 | 11.904 | 15.4408 | 0
7.4915 | 8.3232 | 2.0497 | 2.0746 | 3.2486 | 3.1491 | 7.3729 | 5.2983 | 15.8146 | 17.8892 | 25.2621 | 30.5603 | 7.4915 | 8.3232 | 2.0597 | 2.0746 | 3.2486 | 3.1491 | 7.3729 | 5.2983 | 15.8146 | 17.8892 | 25.2621 | 30.5603 | 0
1.1213 | 6.943 | 1.8374 | 1.7561 | 2.1869 | 2.5121 | 5.7803 | 4.0243 | 8.0643 | 9.8204 | 15.6007 | 19.625 | 1.1213 | 6.943 | 1.8474 | 1.7561 | 2.1869 | 2.5121 | 5.7803 | 4.0243 | 8.0643 | 9.8204 | 15.6007 | 19.625 | 0
-0.19129 | 6.6586 | 1.7936 | 1.6904 | 1.9681 | 2.3809 | 5.4522 | 3.7617 | 6.4673 | 8.1577 | 13.6099 | 17.3716 | -0.19129 | 6.6586 | 1.8036 | 1.6904 | 1.9681 | 2.3809 | 5.4522 | 3.7617 | 6.4673 | 8.1577 | 13.6099 | 17.3716 | 0
14.9327 | 9.9354 | 2.2978 | 2.4466 | 4.4888 | 3.8933 | 9.2332 | 6.7865 | 24.8681 | 27.3147 | 36.5479 | 43.3344 | 14.9327 | 9.9354 | 2.3078 | 2.4466 | 4.4888 | 3.8933 | 9.2332 | 6.7865 | 24.8681 | 27.3147 | 36.5479 | 43.3344 | 0
6.5945 | 8.1288 | 2.0198 | 2.0297 | 3.0991 | 3.0594 | 7.1486 | 5.1189 | 14.7233 | 16.753 | 23.9016 | 29.0205 | 6.5945 | 8.1288 | 2.0298 | 2.0297 | 3.0991 | 3.0594 | 7.1486 | 5.1189 | 14.7233 | 16.753 | 23.9016 | 29.0205 | 0
9.6841 | 8.7982 | 2.1228 | 2.1842 | 3.614 | 3.3684 | 7.921 | 5.7368 | 18.4823 | 20.6665 | 28.5875 | 34.3244 | 9.6841 | 8.7982 | 2.1328 | 2.1842 | 3.614 | 3.3684 | 7.921 | 5.7368 | 18.4823 | 20.6665 | 28.5875 | 34.3244 | 0
10.8748 | 9.0562 | 2.1625 | 2.2437 | 3.8125 | 3.4875 | 8.2187 | 5.975 | 19.931 | 22.1747 | 30.3934 | 36.3684 | 10.8748 | 9.0562 | 2.1725 | 2.2437 | 3.8125 | 3.4875 | 8.2187 | 5.975 | 19.931 | 22.1747 | 30.3934 | 36.3684 | 0
9.5191 | 8.7625 | 2.1173 | 2.176 | 3.5865 | 3.3519 | 7.8798 | 5.7038 | 18.2816 | 20.4576 | 28.3373 | 34.0412 | 9.5191 | 8.7625 | 2.1273 | 2.176 | 3.5865 | 3.3519 | 7.8798 | 5.7038 | 18.2816 | 20.4576 | 28.3373 | 34.0412 | 0
11.791 | 9.2547 | 2.193 | 2.2896 | 3.9652 | 3.5791 | 8.4478 | 6.1582 | 21.0458 | 23.3353 | 31.7831 | 37.9413 | 11.791 | 9.2547 | 2.203 | 2.2896 | 3.9652 | 3.5791 | 8.4478 | 6.1582 | 21.0458 | 23.3353 | 31.7831 | 37.9413 | 0
4.0406 | 7.5755 | 1.9347 | 1.902 | 2.6734 | 2.8041 | 6.5101 | 4.6081 | 11.6161 | 13.5181 | 20.0282 | 24.6364 | 4.0406 | 7.5755 | 1.9447 | 1.902 | 2.6734 | 2.8041 | 6.5101 | 4.6081 | 11.6161 | 13.5181 | 20.0282 | 24.6364 | 0
0.16694 | 6.7362 | 1.8056 | 1.7083 | 2.0278 | 2.4167 | 5.5417 | 3.8334 | 6.9031 | 8.6115 | 14.1532 | 17.9866 | 0.16694 | 6.7362 | 1.8156 | 1.7083 | 2.0278 | 2.4167 | 5.5417 | 3.8334 | 6.9031 | 8.6115 | 14.1532 | 17.9866 | 0
1.7732 | 7.0842 | 1.8591 | 1.7887 | 2.2955 | 2.5773 | 5.9433 | 4.1546 | 8.8574 | 10.6461 | 16.5894 | 20.7441 | 1.7732 | 7.0842 | 1.8691 | 1.7887 | 2.2955 | 2.5773 | 5.9433 | 4.1546 | 8.8574 | 10.6461 | 16.5894 | 20.7441 | 0
2.946 | 7.3383 | 1.8982 | 1.8473 | 2.491 | 2.6946 | 6.2365 | 4.3892 | 10.2843 | 12.1316 | 18.3681 | 22.7573 | 2.946 | 7.3383 | 1.9082 | 1.8473 | 2.491 | 2.6946 | 6.2365 | 4.3892 | 10.2843 | 12.1316 | 18.3681 | 22.7573 | 0
5.1699 | 7.8202 | 1.9723 | 1.9585 | 2.8617 | 2.917 | 6.7925 | 4.834 | 12.9901 | 14.9486 | 21.7411 | 26.5751 | 5.1699 | 7.8202 | 1.9823 | 1.9585 | 2.8617 | 2.917 | 6.7925 | 4.834 | 12.9901 | 14.9486 | 21.7411 | 26.5751 | 0
12.1677 | 9.3363 | 2.2056 | 2.3084 | 4.0279 | 3.6168 | 8.5419 | 6.2335 | 21.504 | 23.8124 | 32.3543 | 38.5878 | 12.1677 | 9.3363 | 2.2156 | 2.3084 | 4.0279 | 3.6168 | 8.5419 | 6.2335 | 21.504 | 23.8124 | 32.3543 | 38.5878 | 0
6.5433 | 8.1177 | 2.0181 | 2.0272 | 3.0906 | 3.0543 | 7.1358 | 5.1087 | 14.661 | 16.6882 | 23.824 | 28.9327 | 6.5433 | 8.1177 | 2.0281 | 2.0272 | 3.0906 | 3.0543 | 7.1358 | 5.1087 | 14.661 | 16.6882 | 23.824 | 28.9327 | 0
11.7076 | 9.2366 | 2.1903 | 2.2854 | 3.9513 | 3.5708 | 8.4269 | 6.1415 | 20.9442 | 23.2296 | 31.6565 | 37.798 | 11.7076 | 9.2366 | 2.2003 | 2.2854 | 3.9513 | 3.5708 | 8.4269 | 6.1415 | 20.9442 | 23.2296 | 31.6565 | 37.798 | 0
5.373 | 7.8641 | 1.9791 | 1.9686 | 2.8955 | 2.9373 | 6.8432 | 4.8746 | 13.2371 | 15.2058 | 22.049 | 26.9236 | 5.373 | 7.8641 | 1.9891 | 1.9686 | 2.8955 | 2.9373 | 6.8432 | 4.8746 | 13.2371 | 15.2058 | 22.049 | 26.9236 | 0
-2.6906 | 6.117 | 1.7103 | 1.5655 | 1.5516 | 2.1309 | 4.8273 | 3.2619 | 3.4264 | 4.9919 | 9.8193 | 13.0811 | -2.6906 | 6.117 | 1.7203 | 1.5655 | 1.5516 | 2.1309 | 4.8273 | 3.2619 | 3.4264 | 4.9919 | 9.8193 | 13.0811 | 0
5.7733 | 7.9509 | 1.9924 | 1.9887 | 2.9622 | 2.9773 | 6.9433 | 4.9547 | 13.7242 | 15.7128 | 22.6561 | 27.6108 | 5.7733 | 7.9509 | 2.0024 | 1.9887 | 2.9622 | 2.9773 | 6.9433 | 4.9547 | 13.7242 | 15.7128 | 22.6561 | 27.6108 | 0
1.0347 | 6.9242 | 1.8345 | 1.7517 | 2.1724 | 2.5035 | 5.7587 | 4.0069 | 7.9588 | 9.7106 | 15.4693 | 19.4762 | 1.0347 | 6.9242 | 1.8445 | 1.7517 | 2.1724 | 2.5035 | 5.7587 | 4.0069 | 7.9588 | 9.7106 | 15.4693 | 19.4762 | 0
17.9452 | 10.5881 | 2.3982 | 2.5973 | 4.9909 | 4.1945 | 9.9863 | 7.389 | 28.5333 | 31.1306 | 41.1169 | 48.5059 | 17.9452 | 10.5881 | 2.4082 | 2.5973 | 4.9909 | 4.1945 | 9.9863 | 7.389 | 28.5333 | 31.1306 | 41.1169 | 48.5059 | 0
2.4162 | 7.2235 | 1.8805 | 1.8208 | 2.4027 | 2.6416 | 6.104 | 4.2832 | 9.6397 | 11.4605 | 17.5645 | 21.8477 | 2.4162 | 7.2235 | 1.8905 | 1.8208 | 2.4027 | 2.6416 | 6.104 | 4.2832 | 9.6397 | 11.4605 | 17.5645 | 21.8477 | 0
5.5634 | 7.9054 | 1.9854 | 1.9782 | 2.9272 | 2.9563 | 6.8909 | 4.9127 | 13.4688 | 15.447 | 22.3378 | 27.2505 | 5.5634 | 7.9054 | 1.9954 | 1.9782 | 2.9272 | 2.9563 | 6.8909 | 4.9127 | 13.4688 | 15.447 | 22.3378 | 27.2505 | 0
-4.3193 | 5.7641 | 1.656 | 1.484 | 1.2801 | 1.9681 | 4.4202 | 2.9361 | 1.4448 | 2.9288 | 7.349 | 10.2851 | -4.3193 | 5.7641 | 1.666 | 1.484 | 1.2801 | 1.9681 | 4.4202 | 2.9361 | 1.4448 | 2.9288 | 7.349 | 10.2851 | 0
-1.7225 | 6.3268 | 1.7426 | 1.6139 | 1.7129 | 2.2278 | 5.0694 | 3.4555 | 4.6043 | 6.2182 | 11.2876 | 14.7431 | -1.7225 | 6.3268 | 1.7526 | 1.6139 | 1.7129 | 2.2278 | 5.0694 | 3.4555 | 4.6043 | 6.2182 | 11.2876 | 14.7431 | 0
5.3795 | 7.8656 | 1.9793 | 1.969 | 2.8966 | 2.9379 | 6.8449 | 4.8759 | 13.245 | 15.214 | 22.0589 | 26.9348 | 5.3795 | 7.8656 | 1.9893 | 1.969 | 2.8966 | 2.9379 | 6.8449 | 4.8759 | 13.245 | 15.214 | 22.0589 | 26.9348 | 0
2.8529 | 7.3181 | 1.8951 | 1.8426 | 2.4755 | 2.6853 | 6.2132 | 4.3706 | 10.171 | 12.0137 | 18.2269 | 22.5975 | 2.8529 | 7.3181 | 1.9051 | 1.8426 | 2.4755 | 2.6853 | 6.2132 | 4.3706 | 10.171 | 12.0137 | 18.2269 | 22.5975 | 0
4.9315 | 7.7685 | 1.9644 | 1.9466 | 2.8219 | 2.8931 | 6.7329 | 4.7863 | 12.6999 | 14.6465 | 21.3794 | 26.1657 | 4.9315 | 7.7685 | 1.9744 | 1.9466 | 2.8219 | 2.8931 | 6.7329 | 4.7863 | 12.6999 | 14.6465 | 21.3794 | 26.1657 | 0
8.9348 | 8.6359 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7337 | 5.587 | 17.5707 | 19.7175 | 27.4512 | 33.0382 | 8.9348 | 8.6359 | 2.1078 | 2.1467 | 3.4891 | 3.2935 | 7.7337 | 5.587 | 17.5707 | 19.7175 | 27.4512 | 33.0382 | 0
18.576 | 10.7248 | 2.4192 | 2.6288 | 5.096 | 4.2576 | 10.144 | 7.5152 | 29.3008 | 31.9296 | 42.0736 | 49.5888 | 18.576 | 10.7248 | 2.4292 | 2.6288 | 5.096 | 4.2576 | 10.144 | 7.5152 | 29.3008 | 31.9296 | 42.0736 | 49.5888 | 0
10.8329 | 9.0471 | 2.1611 | 2.2416 | 3.8055 | 3.4833 | 8.2082 | 5.9666 | 19.88 | 22.1217 | 30.3299 | 36.2965 | 10.8329 | 9.0471 | 2.1711 | 2.2416 | 3.8055 | 3.4833 | 8.2082 | 5.9666 | 19.88 | 22.1217 | 30.3299 | 36.2965 | 0
20.2137 | 11.0796 | 2.4738 | 2.7107 | 5.3689 | 4.4214 | 10.5534 | 7.8427 | 31.2933 | 34.004 | 44.5574 | 52.4001 | 20.2137 | 11.0796 | 2.4838 | 2.7107 | 5.3689 | 4.4214 | 10.5534 | 7.8427 | 31.2933 | 34.004 | 44.5574 | 52.4001 | 0
-2.0597 | 6.2537 | 1.7313 | 1.597 | 1.6567 | 2.194 | 4.9851 | 3.3881 | 4.1941 | 5.7911 | 10.7762 | 14.1642 | -2.0597 | 6.2537 | 1.7413 | 1.597 | 1.6567 | 2.194 | 4.9851 | 3.3881 | 4.1941 | 5.7911 | 10.7762 | 14.1642 | 0
10.1219 | 8.8931 | 2.1374 | 2.2061 | 3.687 | 3.4122 | 8.0305 | 5.8244 | 19.015 | 21.2211 | 29.2516 | 35.0759 | 10.1219 | 8.8931 | 2.1474 | 2.2061 | 3.687 | 3.4122 | 8.0305 | 5.8244 | 19.015 | 21.2211 | 29.2516 | 35.0759 | 0
9.1303 | 8.6782 | 2.1043 | 2.1565 | 3.5217 | 3.313 | 7.7826 | 5.6261 | 17.8085 | 19.965 | 27.7476 | 33.3737 | 9.1303 | 8.6782 | 2.1143 | 2.1565 | 3.5217 | 3.313 | 7.7826 | 5.6261 | 17.8085 | 19.965 | 27.7476 | 33.3737 | 0
1.075 | 6.9329 | 1.8358 | 1.7537 | 2.1792 | 2.5075 | 5.7687 | 4.015 | 8.0079 | 9.7616 | 15.5304 | 19.5454 | 1.075 | 6.9329 | 1.8458 | 1.7537 | 2.1792 | 2.5075 | 5.7687 | 4.015 | 8.0079 | 9.7616 | 15.5304 | 19.5454 | 0
-4.9896 | 5.6189 | 1.6337 | 1.4505 | 1.1684 | 1.901 | 4.2526 | 2.8021 | 0.62936 | 2.0799 | 6.3325 | 9.1346 | -4.9896 | 5.6189 | 1.6437 | 1.4505 | 1.1684 | 1.901 | 4.2526 | 2.8021 | 0.62936 | 2.0799 | 6.3325 | 9.1346 | 0
-0.62885 | 6.5637 | 1.779 | 1.6686 | 1.8952 | 2.3371 | 5.3428 | 3.6742 | 5.9349 | 7.6035 | 12.9462 | 16.6205 | -0.62885 | 6.5637 | 1.789 | 1.6686 | 1.8952 | 2.3371 | 5.3428 | 3.6742 | 5.9349 | 7.6035 | 12.9462 | 16.6205 | 0
7.2339 | 8.2674 | 2.0411 | 2.0617 | 3.2057 | 3.1234 | 7.3085 | 5.2468 | 15.5013 | 17.563 | 24.8715 | 30.1183 | 7.2339 | 8.2674 | 2.0511 | 2.0617 | 3.2057 | 3.1234 | 7.3085 | 5.2468 | 15.5013 | 17.563 | 24.8715 | 30.1183 | 0
10.4833 | 8.9714 | 2.1494 | 2.2242 | 3.7472 | 3.4483 | 8.1208 | 5.8967 | 19.4547 | 21.6788 | 29.7997 | 35.6963 | 10.4833 | 8.9714 | 2.1594 | 2.2242 | 3.7472 | 3.4483 | 8.1208 | 5.8967 | 19.4547 | 21.6788 | 29.7997 | 35.6963 | 0
17.6691 | 10.5283 | 2.389 | 2.5835 | 4.9448 | 4.1669 | 9.9173 | 7.3338 | 28.1974 | 30.7808 | 40.6981 | 48.0319 | 17.6691 | 10.5283 | 2.399 | 2.5835 | 4.9448 | 4.1669 | 9.9173 | 7.3338 | 28.1974 | 30.7808 | 40.6981 | 48.0319 | 0
10.1095 | 8.8904 | 2.137 | 2.2055 | 3.6849 | 3.4109 | 8.0274 | 5.8219 | 18.9999 | 21.2053 | 29.2327 | 35.0546 | 10.1095 | 8.8904 | 2.147 | 2.2055 | 3.6849 | 3.4109 | 8.0274 | 5.8219 | 18.9999 | 21.2053 | 29.2327 | 35.0546 | 0
9.4732 | 8.7525 | 2.1158 | 2.1737 | 3.5789 | 3.3473 | 7.8683 | 5.6946 | 18.2258 | 20.3994 | 28.2677 | 33.9624 | 9.4732 | 8.7525 | 2.1258 | 2.1737 | 3.5789 | 3.3473 | 7.8683 | 5.6946 | 18.2258 | 20.3994 | 28.2677 | 33.9624 | 0
6.8688 | 8.1882 | 2.029 | 2.0434 | 3.1448 | 3.0869 | 7.2172 | 5.1738 | 15.057 | 17.1005 | 24.3177 | 29.4914 | 6.8688 | 8.1882 | 2.039 | 2.0434 | 3.1448 | 3.0869 | 7.2172 | 5.1738 | 15.057 | 17.1005 | 24.3177 | 29.4914 | 0
-7.7712 | 5.0162 | 1.541 | 1.3114 | 0.7048 | 1.6229 | 3.5572 | 2.2458 | -2.755 | -1.4435 | 2.1137 | 4.3594 | -7.7712 | 5.0162 | 1.551 | 1.3114 | 0.7048 | 1.6229 | 3.5572 | 2.2458 | -2.755 | -1.4435 | 2.1137 | 4.3594 | 0
6.6159 | 8.1335 | 2.0205 | 2.0308 | 3.1027 | 3.0616 | 7.154 | 5.1232 | 14.7494 | 16.7802 | 23.9342 | 29.0574 | 6.6159 | 8.1335 | 2.0305 | 2.0308 | 3.1027 | 3.0616 | 7.154 | 5.1232 | 14.7494 | 16.7802 | 23.9342 | 29.0574 | 0
7.7482 | 8.3788 | 2.0583 | 2.0874 | 3.2914 | 3.1748 | 7.437 | 5.3496 | 16.127 | 18.2144 | 25.6514 | 31.0011 | 7.7482 | 8.3788 | 2.0683 | 2.0874 | 3.2914 | 3.1748 | 7.437 | 5.3496 | 16.127 | 18.2144 | 25.6514 | 31.0011 | 0
11.3824 | 9.1662 | 2.1794 | 2.2691 | 3.8971 | 3.5382 | 8.3456 | 6.0765 | 20.5485 | 22.8177 | 31.1632 | 37.2397 | 11.3824 | 9.1662 | 2.1894 | 2.2691 | 3.8971 | 3.5382 | 8.3456 | 6.0765 | 20.5485 | 22.8177 | 31.1632 | 37.2397 | 0
3.369 | 7.4299 | 1.9123 | 1.8684 | 2.5615 | 2.7369 | 6.3422 | 4.4738 | 10.7989 | 12.6674 | 19.0096 | 23.4834 | 3.369 | 7.4299 | 1.9223 | 1.8684 | 2.5615 | 2.7369 | 6.3422 | 4.4738 | 10.7989 | 12.6674 | 19.0096 | 23.4834 | 0
12.951 | 9.506 | 2.2317 | 2.3475 | 4.1585 | 3.6951 | 8.7377 | 6.3902 | 22.457 | 24.8046 | 33.5423 | 39.9325 | 12.951 | 9.506 | 2.2417 | 2.3475 | 4.1585 | 3.6951 | 8.7377 | 6.3902 | 22.457 | 24.8046 | 33.5423 | 39.9325 | 0
0.55287 | 6.8198 | 1.8184 | 1.7276 | 2.0921 | 2.4553 | 5.6382 | 3.9106 | 7.3727 | 9.1003 | 14.7385 | 18.6491 | 0.55287 | 6.8198 | 1.8284 | 1.7276 | 2.0921 | 2.4553 | 5.6382 | 3.9106 | 7.3727 | 9.1003 | 14.7385 | 18.6491 | 0
5.8476 | 7.967 | 1.9949 | 1.9924 | 2.9746 | 2.9848 | 6.9619 | 4.9695 | 13.8146 | 15.807 | 22.7689 | 27.7384 | 5.8476 | 7.967 | 2.0049 | 1.9924 | 2.9746 | 2.9848 | 6.9619 | 4.9695 | 13.8146 | 15.807 | 22.7689 | 27.7384 | 0
1.2162 | 6.9635 | 1.8405 | 1.7608 | 2.2027 | 2.5216 | 5.8041 | 4.0432 | 8.1798 | 9.9406 | 15.7446 | 19.7879 | 1.2162 | 6.9635 | 1.8505 | 1.7608 | 2.2027 | 2.5216 | 5.8041 | 4.0432 | 8.1798 | 9.9406 | 15.7446 | 19.7879 | 0
12.2562 | 9.3555 | 2.2085 | 2.3128 | 4.0427 | 3.6256 | 8.564 | 6.2512 | 21.6117 | 23.9245 | 32.4885 | 38.7398 | 12.2562 | 9.3555 | 2.2185 | 2.3128 | 4.0427 | 3.6256 | 8.564 | 6.2512 | 21.6117 | 23.9245 | 32.4885 | 38.7398 | 0
4.5273 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7055 | 12.2082 | 14.1346 | 20.7664 | 25.4718 | 4.5273 | 7.6809 | 1.9609 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7055 | 12.2082 | 14.1346 | 20.7664 | 25.4718 | 0
-1.3747 | 6.4021 | 1.7542 | 1.6313 | 1.7709 | 2.2625 | 5.1563 | 3.5251 | 5.0275 | 6.6587 | 11.815 | 15.3401 | -1.3747 | 6.4021 | 1.7642 | 1.6313 | 1.7709 | 2.2625 | 5.1563 | 3.5251 | 5.0275 | 6.6587 | 11.815 | 15.3401 | 0
7.568 | 8.3397 | 2.0523 | 2.0784 | 3.2613 | 3.1568 | 7.392 | 5.3136 | 15.9077 | 17.9861 | 25.3781 | 30.6917 | 7.568 | 8.3397 | 2.0623 | 2.0784 | 3.2613 | 3.1568 | 7.392 | 5.3136 | 15.9077 | 17.9861 | 25.3781 | 30.6917 | 0
17.8346 | 10.5642 | 2.3945 | 2.5917 | 4.9724 | 4.1835 | 9.9586 | 7.3669 | 28.3987 | 30.9905 | 40.9491 | 48.316 | 17.8346 | 10.5642 | 2.4045 | 2.5917 | 4.9724 | 4.1835 | 9.9586 | 7.3669 | 28.3987 | 30.9905 | 40.9491 | 48.316 | 0
14.6358 | 9.8711 | 2.2879 | 2.4318 | 4.4393 | 3.8636 | 9.159 | 6.7272 | 24.5069 | 26.9387 | 36.0977 | 42.8248 | 14.6358 | 9.8711 | 2.2979 | 2.4318 | 4.4393 | 3.8636 | 9.159 | 6.7272 | 24.5069 | 26.9387 | 36.0977 | 42.8248 | 0
14.7192 | 9.8892 | 2.2906 | 2.436 | 4.4532 | 3.8719 | 9.1798 | 6.7438 | 24.6084 | 27.0443 | 36.2241 | 42.968 | 14.7192 | 9.8892 | 2.3006 | 2.436 | 4.4532 | 3.8719 | 9.1798 | 6.7438 | 24.6084 | 27.0443 | 36.2241 | 42.968 | 0
8.6596 | 8.5763 | 2.0887 | 2.133 | 3.4433 | 3.266 | 7.6649 | 5.5319 | 17.2359 | 19.3689 | 27.0338 | 32.5657 | 8.6596 | 8.5763 | 2.0987 | 2.133 | 3.4433 | 3.266 | 7.6649 | 5.5319 | 17.2359 | 19.3689 | 27.0338 | 32.5657 | 0
-0.8912 | 6.5069 | 1.7703 | 1.6554 | 1.8515 | 2.3109 | 5.2772 | 3.6218 | 5.6157 | 7.2712 | 12.5484 | 16.1701 | -0.8912 | 6.5069 | 1.7803 | 1.6554 | 1.8515 | 2.3109 | 5.2772 | 3.6218 | 5.6157 | 7.2712 | 12.5484 | 16.1701 | 0
0.11658 | 6.7253 | 1.8039 | 1.7058 | 2.0194 | 2.4117 | 5.5291 | 3.8233 | 6.8418 | 8.5477 | 14.0768 | 17.9001 | 0.11658 | 6.7253 | 1.8139 | 1.7058 | 2.0194 | 2.4117 | 5.5291 | 3.8233 | 6.8418 | 8.5477 | 14.0768 | 17.9001 | 0
2.9789 | 7.3454 | 1.8993 | 1.8489 | 2.4965 | 2.6979 | 6.2447 | 4.3958 | 10.3243 | 12.1733 | 18.418 | 22.8138 | 2.9789 | 7.3454 | 1.9093 | 1.8489 | 2.4965 | 2.6979 | 6.2447 | 4.3958 | 10.3243 | 12.1733 | 18.418 | 22.8138 | 0
10.7182 | 9.0223 | 2.1573 | 2.2359 | 3.7864 | 3.4718 | 8.1796 | 5.9436 | 19.7405 | 21.9764 | 30.156 | 36.0997 | 10.7182 | 9.0223 | 2.1673 | 2.2359 | 3.7864 | 3.4718 | 8.1796 | 5.9436 | 19.7405 | 21.9764 | 30.156 | 36.0997 | 0
8.2018 | 8.4771 | 2.0734 | 2.1101 | 3.367 | 3.2202 | 7.5505 | 5.4404 | 16.6789 | 18.789 | 26.3395 | 31.7798 | 8.2018 | 8.4771 | 2.0834 | 2.1101 | 3.367 | 3.2202 | 7.5505 | 5.4404 | 16.6789 | 18.789 | 26.3395 | 31.7798 | 0
14.9186 | 9.9324 | 2.2973 | 2.4459 | 4.4864 | 3.8919 | 9.2296 | 6.7837 | 24.8509 | 27.2969 | 36.5265 | 43.3102 | 14.9186 | 9.9324 | 2.3073 | 2.4459 | 4.4864 | 3.8919 | 9.2296 | 6.7837 | 24.8509 | 27.2969 | 36.5265 | 43.3102 | 0
3.278 | 7.4102 | 1.9093 | 1.8639 | 2.5463 | 2.7278 | 6.3195 | 4.4556 | 10.6882 | 12.5521 | 18.8716 | 23.3272 | 3.278 | 7.4102 | 1.9193 | 1.8639 | 2.5463 | 2.7278 | 6.3195 | 4.4556 | 10.6882 | 12.5521 | 18.8716 | 23.3272 | 0
11.9059 | 9.2796 | 2.1969 | 2.2953 | 3.9843 | 3.5906 | 8.4765 | 6.1812 | 21.1855 | 23.4808 | 31.9572 | 38.1384 | 11.9059 | 9.2796 | 2.2069 | 2.2953 | 3.9843 | 3.5906 | 8.4765 | 6.1812 | 21.1855 | 23.4808 | 31.9572 | 38.1384 | 0
0.21186 | 6.7459 | 1.8071 | 1.7106 | 2.0353 | 2.4212 | 5.553 | 3.8424 | 6.9578 | 8.6684 | 14.2213 | 18.0637 | 0.21186 | 6.7459 | 1.8171 | 1.7106 | 2.0353 | 2.4212 | 5.553 | 3.8424 | 6.9578 | 8.6684 | 14.2213 | 18.0637 | 0
8.3077 | 8.5 | 2.0769 | 2.1154 | 3.3846 | 3.2308 | 7.5769 | 5.4615 | 16.8077 | 18.9231 | 26.5001 | 31.9616 | 8.3077 | 8.5 | 2.0869 | 2.1154 | 3.3846 | 3.2308 | 7.5769 | 5.4615 | 16.8077 | 18.9231 | 26.5001 | 31.9616 | 0
0.99521 | 6.9156 | 1.8332 | 1.7498 | 2.1659 | 2.4995 | 5.7488 | 3.999 | 7.9108 | 9.6606 | 15.4094 | 19.4084 | 0.99521 | 6.9156 | 1.8432 | 1.7498 | 2.1659 | 2.4995 | 5.7488 | 3.999 | 7.9108 | 9.6606 | 15.4094 | 19.4084 | 0
10.022 | 8.8714 | 2.1341 | 2.2011 | 3.6703 | 3.4022 | 8.0055 | 5.8044 | 18.8934 | 21.0945 | 29.1 | 34.9045 | 10.022 | 8.8714 | 2.1441 | 2.2011 | 3.6703 | 3.4022 | 8.0055 | 5.8044 | 18.8934 | 21.0945 | 29.1 | 34.9045 | 0
-5.1718 | 5.5794 | 1.6276 | 1.4414 | 1.138 | 1.8828 | 4.207 | 2.7656 | 0.4076 | 1.849 | 6.0561 | 8.8217 | -5.1718 | 5.5794 | 1.6376 | 1.4414 | 1.138 | 1.8828 | 4.207 | 2.7656 | 0.4076 | 1.849 | 6.0561 | 8.8217 | 0
-1.0844 | 6.465 | 1.7639 | 1.6458 | 1.8193 | 2.2916 | 5.2289 | 3.5831 | 5.3806 | 7.0264 | 12.2553 | 15.8384 | -1.0844 | 6.465 | 1.7739 | 1.6458 | 1.8193 | 2.2916 | 5.2289 | 3.5831 | 5.3806 | 7.0264 | 12.2553 | 15.8384 | 0
6.9795 | 8.2122 | 2.0326 | 2.049 | 3.1632 | 3.0979 | 7.2449 | 5.1959 | 15.1917 | 17.2407 | 24.4855 | 29.6814 | 6.9795 | 8.2122 | 2.0426 | 2.049 | 3.1632 | 3.0979 | 7.2449 | 5.1959 | 15.1917 | 17.2407 | 24.4855 | 29.6814 | 0
1.3132 | 6.9845 | 1.8438 | 1.7657 | 2.2189 | 2.5313 | 5.8283 | 4.0626 | 8.2978 | 10.0634 | 15.8917 | 19.9544 | 1.3132 | 6.9845 | 1.8538 | 1.7657 | 2.2189 | 2.5313 | 5.8283 | 4.0626 | 8.2978 | 10.0634 | 15.8917 | 19.9544 | 0
1.3639 | 6.9955 | 1.8455 | 1.7682 | 2.2273 | 2.5364 | 5.841 | 4.0728 | 8.3594 | 10.1276 | 15.9686 | 20.0414 | 1.3639 | 6.9955 | 1.8555 | 1.7682 | 2.2273 | 2.5364 | 5.841 | 4.0728 | 8.3594 | 10.1276 | 15.9686 | 20.0414 | 0
-1.4768 | 6.38 | 1.7508 | 1.6262 | 1.7539 | 2.2523 | 5.1308 | 3.5046 | 4.9032 | 6.5293 | 11.6601 | 15.1648 | -1.4768 | 6.38 | 1.7608 | 1.6262 | 1.7539 | 2.2523 | 5.1308 | 3.5046 | 4.9032 | 6.5293 | 11.6601 | 15.1648 | 0
6.5105 | 8.1106 | 2.017 | 2.0255 | 3.0851 | 3.0511 | 7.1276 | 5.1021 | 14.6211 | 16.6466 | 23.7743 | 28.8764 | 6.5105 | 8.1106 | 2.027 | 2.0255 | 3.0851 | 3.0511 | 7.1276 | 5.1021 | 14.6211 | 16.6466 | 23.7743 | 28.8764 | 0
2.9522 | 7.3396 | 1.8984 | 1.8476 | 2.492 | 2.6952 | 6.238 | 4.3904 | 10.2918 | 12.1394 | 18.3775 | 22.7679 | 2.9522 | 7.3396 | 1.9084 | 1.8476 | 2.492 | 2.6952 | 6.238 | 4.3904 | 10.2918 | 12.1394 | 18.3775 | 22.7679 | 0
6.1645 | 8.0356 | 2.0055 | 2.0082 | 3.0274 | 3.0165 | 7.0411 | 5.0329 | 14.2002 | 16.2084 | 23.2495 | 28.2824 | 6.1645 | 8.0356 | 2.0155 | 2.0082 | 3.0274 | 3.0165 | 7.0411 | 5.0329 | 14.2002 | 16.2084 | 23.2495 | 28.2824 | 0
3.115 | 7.3749 | 1.9038 | 1.8557 | 2.5192 | 2.7115 | 6.2787 | 4.423 | 10.4899 | 12.3457 | 18.6244 | 23.0474 | 3.115 | 7.3749 | 1.9138 | 1.8557 | 2.5192 | 2.7115 | 6.2787 | 4.423 | 10.4899 | 12.3457 | 18.6244 | 23.0474 | 0
6.4626 | 8.1002 | 2.0154 | 2.0231 | 3.0771 | 3.0463 | 7.1157 | 5.0925 | 14.5628 | 16.586 | 23.7016 | 28.7941 | 6.4626 | 8.1002 | 2.0254 | 2.0231 | 3.0771 | 3.0463 | 7.1157 | 5.0925 | 14.5628 | 16.586 | 23.7016 | 28.7941 | 0
16.0124 | 10.1694 | 2.3337 | 2.5006 | 4.6687 | 4.0012 | 9.5031 | 7.0025 | 26.1817 | 28.6824 | 38.1855 | 45.1879 | 16.0124 | 10.1694 | 2.3437 | 2.5006 | 4.6687 | 4.0012 | 9.5031 | 7.0025 | 26.1817 | 28.6824 | 38.1855 | 45.1879 | 0
1.5673 | 7.0396 | 1.8522 | 1.7784 | 2.2612 | 2.5567 | 5.8918 | 4.1135 | 8.6068 | 10.3852 | 16.277 | 20.3904 | 1.5673 | 7.0396 | 1.8622 | 1.7784 | 2.2612 | 2.5567 | 5.8918 | 4.1135 | 8.6068 | 10.3852 | 16.277 | 20.3904 | 0
13.5036 | 9.6258 | 2.2501 | 2.3752 | 4.2506 | 3.7504 | 8.8759 | 6.5007 | 23.1293 | 25.5045 | 34.3804 | 40.8811 | 13.5036 | 9.6258 | 2.2601 | 2.3752 | 4.2506 | 3.7504 | 8.8759 | 6.5007 | 23.1293 | 25.5045 | 34.3804 | 40.8811 | 0
0.21402 | 6.7464 | 1.8071 | 1.7107 | 2.0357 | 2.4214 | 5.5535 | 3.8428 | 6.9604 | 8.6711 | 14.2246 | 18.0674 | 0.21402 | 6.7464 | 1.8171 | 1.7107 | 2.0357 | 2.4214 | 5.5535 | 3.8428 | 6.9604 | 8.6711 | 14.2246 | 18.0674 | 0
0.14578 | 6.7316 | 1.8049 | 1.7073 | 2.0243 | 2.4146 | 5.5364 | 3.8292 | 6.8774 | 8.5847 | 14.1211 | 17.9503 | 0.14578 | 6.7316 | 1.8149 | 1.7073 | 2.0243 | 2.4146 | 5.5364 | 3.8292 | 6.8774 | 8.5847 | 14.1211 | 17.9503 | 0
6.3738 | 8.081 | 2.0125 | 2.0187 | 3.0623 | 3.0374 | 7.0935 | 5.0748 | 14.4548 | 16.4735 | 23.5669 | 28.6417 | 6.3738 | 8.081 | 2.0225 | 2.0187 | 3.0623 | 3.0374 | 7.0935 | 5.0748 | 14.4548 | 16.4735 | 23.5669 | 28.6417 | 0
16.4514 | 10.2645 | 2.3484 | 2.5226 | 4.7419 | 4.0451 | 9.6128 | 7.0903 | 26.7158 | 29.2384 | 38.8513 | 45.9415 | 16.4514 | 10.2645 | 2.3584 | 2.5226 | 4.7419 | 4.0451 | 9.6128 | 7.0903 | 26.7158 | 29.2384 | 38.8513 | 45.9415 | 0
13.4295 | 9.6097 | 2.2477 | 2.3715 | 4.2383 | 3.743 | 8.8574 | 6.4859 | 23.0392 | 25.4107 | 34.2681 | 40.754 | 13.4295 | 9.6097 | 2.2577 | 2.3715 | 4.2383 | 3.743 | 8.8574 | 6.4859 | 23.0392 | 25.4107 | 34.2681 | 40.754 | 0
-7.4375 | 5.0886 | 1.5521 | 1.3281 | 0.76042 | 1.6563 | 3.6406 | 2.3125 | -2.3489 | -1.0208 | 2.6199 | 4.9324 | -7.4375 | 5.0886 | 1.5621 | 1.3281 | 0.76042 | 1.6563 | 3.6406 | 2.3125 | -2.3489 | -1.0208 | 2.6199 | 4.9324 | 0
-2.1955 | 6.2243 | 1.7268 | 1.5902 | 1.6341 | 2.1805 | 4.9511 | 3.3609 | 4.0288 | 5.6191 | 10.5702 | 13.9311 | -2.1955 | 6.2243 | 1.7368 | 1.5902 | 1.6341 | 2.1805 | 4.9511 | 3.3609 | 4.0288 | 5.6191 | 10.5702 | 13.9311 | 0
-0.86628 | 6.5123 | 1.7711 | 1.6567 | 1.8556 | 2.3134 | 5.2834 | 3.6267 | 5.646 | 7.3027 | 12.5861 | 16.2129 | -0.86628 | 6.5123 | 1.7811 | 1.6567 | 1.8556 | 2.3134 | 5.2834 | 3.6267 | 5.646 | 7.3027 | 12.5861 | 16.2129 | 0
7.4517 | 8.3145 | 2.0484 | 2.0726 | 3.2419 | 3.1452 | 7.3629 | 5.2903 | 15.7662 | 17.8388 | 25.2017 | 30.492 | 7.4517 | 8.3145 | 2.0584 | 2.0726 | 3.2419 | 3.1452 | 7.3629 | 5.2903 | 15.7662 | 17.8388 | 25.2017 | 30.492 | 0
-4.548 | 5.7146 | 1.6484 | 1.4726 | 1.242 | 1.9452 | 4.363 | 2.8904 | 1.1666 | 2.6392 | 7.0022 | 9.8926 | -4.548 | 5.7146 | 1.6584 | 1.4726 | 1.242 | 1.9452 | 4.363 | 2.8904 | 1.1666 | 2.6392 | 7.0022 | 9.8926 | 0
10.1638 | 8.9022 | 2.1388 | 2.2082 | 3.694 | 3.4164 | 8.0409 | 5.8328 | 19.066 | 21.2741 | 29.3151 | 35.1479 | 10.1638 | 8.9022 | 2.1488 | 2.2082 | 3.694 | 3.4164 | 8.0409 | 5.8328 | 19.066 | 21.2741 | 29.3151 | 35.1479 | 0
7.2783 | 8.277 | 2.0426 | 2.0639 | 3.213 | 3.1278 | 7.3196 | 5.2557 | 15.5552 | 17.6191 | 24.9387 | 30.1943 | 7.2783 | 8.277 | 2.0526 | 2.0639 | 3.213 | 3.1278 | 7.3196 | 5.2557 | 15.5552 | 17.6191 | 24.9387 | 30.1943 | 0
1.4575 | 7.0158 | 1.8486 | 1.7729 | 2.2429 | 2.5457 | 5.8644 | 4.0915 | 8.4732 | 10.2461 | 16.1105 | 20.202 | 1.4575 | 7.0158 | 1.8586 | 1.7729 | 2.2429 | 2.5457 | 5.8644 | 4.0915 | 8.4732 | 10.2461 | 16.1105 | 20.202 | 0
-0.57037 | 6.5764 | 1.781 | 1.6715 | 1.9049 | 2.343 | 5.3574 | 3.6859 | 6.0061 | 7.6775 | 13.0349 | 16.7209 | -0.57037 | 6.5764 | 1.791 | 1.6715 | 1.9049 | 2.343 | 5.3574 | 3.6859 | 6.0061 | 7.6775 | 13.0349 | 16.7209 | 0
2.3931 | 7.2185 | 1.8798 | 1.8197 | 2.3989 | 2.6393 | 6.0983 | 4.2786 | 9.6116 | 11.4313 | 17.5295 | 21.8082 | 2.3931 | 7.2185 | 1.8898 | 1.8197 | 2.3989 | 2.6393 | 6.0983 | 4.2786 | 9.6116 | 11.4313 | 17.5295 | 21.8082 | 0
14.9926 | 9.9484 | 2.2998 | 2.4496 | 4.4988 | 3.8993 | 9.2481 | 6.7985 | 24.941 | 27.3906 | 36.6387 | 43.4372 | 14.9926 | 9.9484 | 2.3098 | 2.4496 | 4.4988 | 3.8993 | 9.2481 | 6.7985 | 24.941 | 27.3906 | 36.6387 | 43.4372 | 0
5.5444 | 7.9013 | 1.9848 | 1.9772 | 2.9241 | 2.9544 | 6.8861 | 4.9089 | 13.4457 | 15.423 | 22.3091 | 27.218 | 5.5444 | 7.9013 | 1.9948 | 1.9772 | 2.9241 | 2.9544 | 6.8861 | 4.9089 | 13.4457 | 15.423 | 22.3091 | 27.218 | 0
13.6245 | 9.652 | 2.2542 | 2.3812 | 4.2708 | 3.7625 | 8.9061 | 6.5249 | 23.2765 | 25.6577 | 34.5638 | 41.0887 | 13.6245 | 9.652 | 2.2642 | 2.3812 | 4.2708 | 3.7625 | 8.9061 | 6.5249 | 23.2765 | 25.6577 | 34.5638 | 41.0887 | 0
1.3803 | 6.9991 | 1.846 | 1.769 | 2.2301 | 2.538 | 5.8451 | 4.0761 | 8.3794 | 10.1484 | 15.9935 | 20.0695 | 1.3803 | 6.9991 | 1.856 | 1.769 | 2.2301 | 2.538 | 5.8451 | 4.0761 | 8.3794 | 10.1484 | 15.9935 | 20.0695 | 0
9.4004 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.8501 | 5.6801 | 18.1371 | 20.3071 | 28.1572 | 33.8373 | 9.4004 | 8.7367 | 2.1233 | 2.17 | 3.5667 | 3.34 | 7.8501 | 5.6801 | 18.1371 | 20.3071 | 28.1572 | 33.8373 | 0
5.1169 | 7.8087 | 1.9706 | 1.9558 | 2.8528 | 2.9117 | 6.7792 | 4.8234 | 12.9255 | 14.8813 | 21.6606 | 26.4839 | 5.1169 | 7.8087 | 1.9806 | 1.9558 | 2.8528 | 2.9117 | 6.7792 | 4.8234 | 12.9255 | 14.8813 | 21.6606 | 26.4839 | 0
-0.84508 | 6.5169 | 1.7718 | 1.6577 | 1.8592 | 2.3155 | 5.2887 | 3.631 | 5.6718 | 7.3296 | 12.6183 | 16.2493 | -0.84508 | 6.5169 | 1.7818 | 1.6577 | 1.8592 | 2.3155 | 5.2887 | 3.631 | 5.6718 | 7.3296 | 12.6183 | 16.2493 | 0
14.9278 | 9.9344 | 2.2976 | 2.4464 | 4.488 | 3.8928 | 9.232 | 6.7856 | 24.8622 | 27.3086 | 36.5405 | 43.3261 | 14.9278 | 9.9344 | 2.3076 | 2.4464 | 4.488 | 3.8928 | 9.232 | 6.7856 | 24.8622 | 27.3086 | 36.5405 | 43.3261 | 0
9.9078 | 8.8467 | 2.1303 | 2.1954 | 3.6513 | 3.3908 | 7.977 | 5.7816 | 18.7545 | 20.9499 | 28.9268 | 34.7084 | 9.9078 | 8.8467 | 2.1403 | 2.1954 | 3.6513 | 3.3908 | 7.977 | 5.7816 | 18.7545 | 20.9499 | 28.9268 | 34.7084 | 0
5.1469 | 7.8152 | 1.9716 | 1.9573 | 2.8578 | 2.9147 | 6.7867 | 4.8294 | 12.962 | 14.9194 | 21.7061 | 26.5355 | 5.1469 | 7.8152 | 1.9816 | 1.9573 | 2.8578 | 2.9147 | 6.7867 | 4.8294 | 12.962 | 14.9194 | 21.7061 | 26.5355 | 0
3.5807 | 7.4758 | 1.9194 | 1.879 | 2.5968 | 2.7581 | 6.3952 | 4.5161 | 11.0565 | 12.9355 | 19.3307 | 23.8468 | 3.5807 | 7.4758 | 1.9294 | 1.879 | 2.5968 | 2.7581 | 6.3952 | 4.5161 | 11.0565 | 12.9355 | 19.3307 | 23.8468 | 0
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2043 | 14.1305 | 20.7616 | 25.4664 | 4.5241 | 7.6802 | 1.9608 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2043 | 14.1305 | 20.7616 | 25.4664 | 0
8.6671 | 8.5779 | 2.0889 | 2.1334 | 3.4445 | 3.2667 | 7.6668 | 5.5334 | 17.2449 | 19.3783 | 27.0451 | 32.5785 | 8.6671 | 8.5779 | 2.0989 | 2.1334 | 3.4445 | 3.2667 | 7.6668 | 5.5334 | 17.2449 | 19.3783 | 27.0451 | 32.5785 | 0
8.4187 | 8.5241 | 2.0806 | 2.1209 | 3.4031 | 3.2419 | 7.6047 | 5.4837 | 16.9428 | 19.0637 | 26.6684 | 32.1522 | 8.4187 | 8.5241 | 2.0906 | 2.1209 | 3.4031 | 3.2419 | 7.6047 | 5.4837 | 16.9428 | 19.0637 | 26.6684 | 32.1522 | 0
-9.9815 | 4.5373 | 1.4673 | 1.2009 | 0.33642 | 1.4019 | 3.0046 | 1.8037 | -5.4442 | -4.2432 | -1.2386 | 0.5651 | -9.9815 | 4.5373 | 1.4773 | 1.2009 | 0.33642 | 1.4019 | 3.0046 | 1.8037 | -5.4442 | -4.2432 | -1.2386 | 0.5651 | 0
17.7361 | 10.5428 | 2.3912 | 2.5868 | 4.956 | 4.1736 | 9.934 | 7.3472 | 28.2789 | 30.8657 | 40.7997 | 48.1469 | 17.7361 | 10.5428 | 2.4012 | 2.5868 | 4.956 | 4.1736 | 9.934 | 7.3472 | 28.2789 | 30.8657 | 40.7997 | 48.1469 | 0
14.6958 | 9.8841 | 2.2899 | 2.4348 | 4.4493 | 3.8696 | 9.174 | 6.7392 | 24.5799 | 27.0147 | 36.1887 | 42.9279 | 14.6958 | 9.8841 | 2.2999 | 2.4348 | 4.4493 | 3.8696 | 9.174 | 6.7392 | 24.5799 | 27.0147 | 36.1887 | 42.9279 | 0
6.9703 | 8.2102 | 2.0323 | 2.0485 | 3.1617 | 3.097 | 7.2426 | 5.1941 | 15.1805 | 17.229 | 24.4716 | 29.6656 | 6.9703 | 8.2102 | 2.0423 | 2.0485 | 3.1617 | 3.097 | 7.2426 | 5.1941 | 15.1805 | 17.229 | 24.4716 | 29.6656 | 0
-2.7649 | 6.1009 | 1.7078 | 1.5618 | 1.5392 | 2.1235 | 4.8088 | 3.247 | 3.336 | 4.8978 | 9.7066 | 12.9536 | -2.7649 | 6.1009 | 1.7178 | 1.5618 | 1.5392 | 2.1235 | 4.8088 | 3.247 | 3.336 | 4.8978 | 9.7066 | 12.9536 | 0
8.3695 | 8.5134 | 2.079 | 2.1185 | 3.3949 | 3.2369 | 7.5924 | 5.4739 | 16.8829 | 19.0014 | 26.5937 | 32.0676 | 8.3695 | 8.5134 | 2.089 | 2.1185 | 3.3949 | 3.2369 | 7.5924 | 5.4739 | 16.8829 | 19.0014 | 26.5937 | 32.0676 | 0
0.31258 | 6.7677 | 1.8104 | 1.7156 | 2.0521 | 2.4313 | 5.5781 | 3.8625 | 7.0803 | 8.7959 | 14.3741 | 18.2366 | 0.31258 | 6.7677 | 1.8204 | 1.7156 | 2.0521 | 2.4313 | 5.5781 | 3.8625 | 7.0803 | 8.7959 | 14.3741 | 18.2366 | 0
14.0166 | 9.7369 | 2.2672 | 2.4008 | 4.3361 | 3.8017 | 9.0041 | 6.6033 | 23.7535 | 26.1543 | 35.1584 | 41.7618 | 14.0166 | 9.7369 | 2.2772 | 2.4008 | 4.3361 | 3.8017 | 9.0041 | 6.6033 | 23.7535 | 26.1543 | 35.1584 | 41.7618 | 0
7.5685 | 8.3398 | 2.0523 | 2.0784 | 3.2614 | 3.1568 | 7.3921 | 5.3137 | 15.9083 | 17.9867 | 25.3788 | 30.6925 | 7.5685 | 8.3398 | 2.0623 | 2.0784 | 3.2614 | 3.1568 | 7.3921 | 5.3137 | 15.9083 | 17.9867 | 25.3788 | 30.6925 | 0
5.9811 | 7.9959 | 1.9994 | 1.9991 | 2.9968 | 2.9981 | 6.9953 | 4.9962 | 13.977 | 15.976 | 22.9713 | 27.9675 | 5.9811 | 7.9959 | 2.0094 | 1.9991 | 2.9968 | 2.9981 | 6.9953 | 4.9962 | 13.977 | 15.976 | 22.9713 | 27.9675 | 0
3.3981 | 7.4363 | 1.9133 | 1.8699 | 2.5664 | 2.7398 | 6.3495 | 4.4796 | 10.8344 | 12.7043 | 19.0538 | 23.5335 | 3.3981 | 7.4363 | 1.9233 | 1.8699 | 2.5664 | 2.7398 | 6.3495 | 4.4796 | 10.8344 | 12.7043 | 19.0538 | 23.5335 | 0
6.2917 | 8.0632 | 2.0097 | 2.0146 | 3.0486 | 3.0292 | 7.0729 | 5.0583 | 14.3549 | 16.3695 | 23.4424 | 28.5007 | 6.2917 | 8.0632 | 2.0197 | 2.0146 | 3.0486 | 3.0292 | 7.0729 | 5.0583 | 14.3549 | 16.3695 | 23.4424 | 28.5007 | 0
3.5617 | 7.4717 | 1.9187 | 1.8781 | 2.5936 | 2.7562 | 6.3904 | 4.5123 | 11.0334 | 12.9115 | 19.3019 | 23.8143 | 3.5617 | 7.4717 | 1.9287 | 1.8781 | 2.5936 | 2.7562 | 6.3904 | 4.5123 | 11.0334 | 12.9115 | 19.3019 | 23.8143 | 0
13.4989 | 9.6248 | 2.25 | 2.3749 | 4.2498 | 3.7499 | 8.8747 | 6.4998 | 23.1236 | 25.4986 | 34.3733 | 40.8731 | 13.4989 | 9.6248 | 2.26 | 2.3749 | 4.2498 | 3.7499 | 8.8747 | 6.4998 | 23.1236 | 25.4986 | 34.3733 | 40.8731 | 0
10.3918 | 8.9516 | 2.1464 | 2.2196 | 3.732 | 3.4392 | 8.098 | 5.8784 | 19.3434 | 21.563 | 29.6609 | 35.5393 | 10.3918 | 8.9516 | 2.1564 | 2.2196 | 3.732 | 3.4392 | 8.098 | 5.8784 | 19.3434 | 21.563 | 29.6609 | 35.5393 | 0
1.0548 | 6.9285 | 1.8352 | 1.7527 | 2.1758 | 2.5055 | 5.7637 | 4.011 | 7.9833 | 9.7361 | 15.4998 | 19.5107 | 1.0548 | 6.9285 | 1.8452 | 1.7527 | 2.1758 | 2.5055 | 5.7637 | 4.011 | 7.9833 | 9.7361 | 15.4998 | 19.5107 | 0
16.2026 | 10.2106 | 2.3401 | 2.5101 | 4.7004 | 4.0203 | 9.5506 | 7.0405 | 26.4131 | 28.9233 | 38.4739 | 45.5144 | 16.2026 | 10.2106 | 2.3501 | 2.5101 | 4.7004 | 4.0203 | 9.5506 | 7.0405 | 26.4131 | 28.9233 | 38.4739 | 45.5144 | 0
8.5304 | 8.5483 | 2.0843 | 2.1265 | 3.4217 | 3.253 | 7.6326 | 5.5061 | 17.0786 | 19.2052 | 26.8378 | 32.3438 | 8.5304 | 8.5483 | 2.0943 | 2.1265 | 3.4217 | 3.253 | 7.6326 | 5.5061 | 17.0786 | 19.2052 | 26.8378 | 32.3438 | 0
7.3385 | 8.29 | 2.0446 | 2.0669 | 3.2231 | 3.1339 | 7.3346 | 5.2677 | 15.6285 | 17.6955 | 25.0301 | 30.2978 | 7.3385 | 8.29 | 2.0546 | 2.0669 | 3.2231 | 3.1339 | 7.3346 | 5.2677 | 15.6285 | 17.6955 | 25.0301 | 30.2978 | 0
-11.3977 | 4.2305 | 1.4201 | 1.1301 | 0.10039 | 1.2602 | 2.6506 | 1.5205 | -7.1672 | -6.0371 | -3.3865 | -1.866 | -11.3977 | 4.2305 | 1.4301 | 1.1301 | 0.10039 | 1.2602 | 2.6506 | 1.5205 | -7.1672 | -6.0371 | -3.3865 | -1.866 | 0
4.3995 | 7.6532 | 1.9466 | 1.92 | 2.7332 | 2.8399 | 6.5999 | 4.6799 | 12.0527 | 13.9727 | 20.5726 | 25.2525 | 4.3995 | 7.6532 | 1.9566 | 1.92 | 2.7332 | 2.8399 | 6.5999 | 4.6799 | 12.0527 | 13.9727 | 20.5726 | 25.2525 | 0
14.4103 | 9.8222 | 2.2803 | 2.4205 | 4.4017 | 3.841 | 9.1026 | 6.6821 | 24.2325 | 26.6531 | 35.7556 | 42.4377 | 14.4103 | 9.8222 | 2.2903 | 2.4205 | 4.4017 | 3.841 | 9.1026 | 6.6821 | 24.2325 | 26.6531 | 35.7556 | 42.4377 | 0
-4.8914 | 5.6402 | 1.637 | 1.4554 | 1.1848 | 1.9109 | 4.2771 | 2.8217 | 0.74876 | 2.2042 | 6.4813 | 9.3031 | -4.8914 | 5.6402 | 1.647 | 1.4554 | 1.1848 | 1.9109 | 4.2771 | 2.8217 | 0.74876 | 2.2042 | 6.4813 | 9.3031 | 0
15.1442 | 9.9812 | 2.3048 | 2.4572 | 4.524 | 3.9144 | 9.2861 | 6.8288 | 25.1255 | 27.5827 | 36.8687 | 43.6976 | 15.1442 | 9.9812 | 2.3148 | 2.4572 | 4.524 | 3.9144 | 9.2861 | 6.8288 | 25.1255 | 27.5827 | 36.8687 | 43.6976 | 0
6.8025 | 8.1739 | 2.0267 | 2.0401 | 3.1337 | 3.0802 | 7.2006 | 5.1605 | 14.9763 | 17.0165 | 24.2171 | 29.3776 | 6.8025 | 8.1739 | 2.0367 | 2.0401 | 3.1337 | 3.0802 | 7.2006 | 5.1605 | 14.9763 | 17.0165 | 24.2171 | 29.3776 | 0
7.5565 | 8.3372 | 2.0519 | 2.0778 | 3.2594 | 3.1556 | 7.3891 | 5.3113 | 15.8937 | 17.9716 | 25.3607 | 30.672 | 7.5565 | 8.3372 | 2.0619 | 2.0778 | 3.2594 | 3.1556 | 7.3891 | 5.3113 | 15.8937 | 17.9716 | 25.3607 | 30.672 | 0
7.1078 | 8.24 | 2.0369 | 2.0554 | 3.1846 | 3.1108 | 7.2769 | 5.2216 | 15.3478 | 17.4032 | 24.6802 | 29.9017 | 7.1078 | 8.24 | 2.0469 | 2.0554 | 3.1846 | 3.1108 | 7.2769 | 5.2216 | 15.3478 | 17.4032 | 24.6802 | 29.9017 | 0
5.4872 | 7.8889 | 1.9829 | 1.9744 | 2.9145 | 2.9487 | 6.8718 | 4.8974 | 13.3761 | 15.3505 | 22.2223 | 27.1197 | 5.4872 | 7.8889 | 1.9929 | 1.9744 | 2.9145 | 2.9487 | 6.8718 | 4.8974 | 13.3761 | 15.3505 | 22.2223 | 27.1197 | 0
-0.20801 | 6.6549 | 1.7931 | 1.6896 | 1.9653 | 2.3792 | 5.448 | 3.7584 | 6.4469 | 8.1365 | 13.5845 | 17.3429 | -0.20801 | 6.6549 | 1.8031 | 1.6896 | 1.9653 | 2.3792 | 5.448 | 3.7584 | 6.4469 | 8.1365 | 13.5845 | 17.3429 | 0
17.5186 | 10.4957 | 2.384 | 2.5759 | 4.9198 | 4.1519 | 9.8796 | 7.3037 | 28.0143 | 30.5902 | 40.4698 | 47.7735 | 17.5186 | 10.4957 | 2.394 | 2.5759 | 4.9198 | 4.1519 | 9.8796 | 7.3037 | 28.0143 | 30.5902 | 40.4698 | 47.7735 | 0
10.1071 | 8.8899 | 2.1369 | 2.2054 | 3.6845 | 3.4107 | 8.0268 | 5.8214 | 18.997 | 21.2024 | 29.2292 | 35.0506 | 10.1071 | 8.8899 | 2.1469 | 2.2054 | 3.6845 | 3.4107 | 8.0268 | 5.8214 | 18.997 | 21.2024 | 29.2292 | 35.0506 | 0
8.5568 | 8.554 | 2.0852 | 2.1278 | 3.4261 | 3.2557 | 7.6392 | 5.5114 | 17.1107 | 19.2386 | 26.8777 | 32.3891 | 8.5568 | 8.554 | 2.0952 | 2.1278 | 3.4261 | 3.2557 | 7.6392 | 5.5114 | 17.1107 | 19.2386 | 26.8777 | 32.3891 | 0
6.2378 | 8.0515 | 2.0079 | 2.0119 | 3.0396 | 3.0238 | 7.0594 | 5.0476 | 14.2893 | 16.3012 | 23.3606 | 28.4082 | 6.2378 | 8.0515 | 2.0179 | 2.0119 | 3.0396 | 3.0238 | 7.0594 | 5.0476 | 14.2893 | 16.3012 | 23.3606 | 28.4082 | 0
-0.17002 | 6.6632 | 1.7943 | 1.6915 | 1.9717 | 2.383 | 5.4575 | 3.766 | 6.4931 | 8.1846 | 13.6421 | 17.4081 | -0.17002 | 6.6632 | 1.8043 | 1.6915 | 1.9717 | 2.383 | 5.4575 | 3.766 | 6.4931 | 8.1846 | 13.6421 | 17.4081 | 0
14.1065 | 9.7564 | 2.2702 | 2.4053 | 4.3511 | 3.8106 | 9.0266 | 6.6213 | 23.8629 | 26.2682 | 35.2948 | 41.9161 | 14.1065 | 9.7564 | 2.2802 | 2.4053 | 4.3511 | 3.8106 | 9.0266 | 6.6213 | 23.8629 | 26.2682 | 35.2948 | 41.9161 | 0
3.8564 | 7.5356 | 1.9285 | 1.8928 | 2.6427 | 2.7856 | 6.4641 | 4.5713 | 11.392 | 13.2848 | 19.7489 | 24.3202 | 3.8564 | 7.5356 | 1.9385 | 1.8928 | 2.6427 | 2.7856 | 6.4641 | 4.5713 | 11.392 | 13.2848 | 19.7489 | 24.3202 | 0
-3.938 | 5.8468 | 1.6687 | 1.5031 | 1.3437 | 2.0062 | 4.5155 | 3.0124 | 1.9088 | 3.4119 | 7.9273 | 10.9397 | -3.938 | 5.8468 | 1.6787 | 1.5031 | 1.3437 | 2.0062 | 4.5155 | 3.0124 | 1.9088 | 3.4119 | 7.9273 | 10.9397 | 0
8.0713 | 8.4488 | 2.069 | 2.1036 | 3.3452 | 3.2071 | 7.5178 | 5.4143 | 16.5201 | 18.6237 | 26.1415 | 31.5558 | 8.0713 | 8.4488 | 2.079 | 2.1036 | 3.3452 | 3.2071 | 7.5178 | 5.4143 | 16.5201 | 18.6237 | 26.1415 | 31.5558 | 0
-3.3537 | 5.9734 | 1.6882 | 1.5323 | 1.4411 | 2.0646 | 4.6616 | 3.1293 | 2.6197 | 4.152 | 8.8136 | 11.9428 | -3.3537 | 5.9734 | 1.6982 | 1.5323 | 1.4411 | 2.0646 | 4.6616 | 3.1293 | 2.6197 | 4.152 | 8.8136 | 11.9428 | 0
-2.1228 | 6.2401 | 1.7292 | 1.5939 | 1.6462 | 2.1877 | 4.9693 | 3.3754 | 4.1173 | 5.7111 | 10.6804 | 14.0558 | -2.1228 | 6.2401 | 1.7392 | 1.5939 | 1.6462 | 2.1877 | 4.9693 | 3.3754 | 4.1173 | 5.7111 | 10.6804 | 14.0558 | 0
3.4464 | 7.4467 | 1.9149 | 1.8723 | 2.5744 | 2.7446 | 6.3616 | 4.4893 | 10.8932 | 12.7655 | 19.1271 | 23.6164 | 3.4464 | 7.4467 | 1.9249 | 1.8723 | 2.5744 | 2.7446 | 6.3616 | 4.4893 | 10.8932 | 12.7655 | 19.1271 | 23.6164 | 0
9.7406 | 8.8105 | 2.1247 | 2.187 | 3.6234 | 3.3741 | 7.9351 | 5.7481 | 18.551 | 20.7381 | 28.6732 | 34.4213 | 9.7406 | 8.8105 | 2.1347 | 2.187 | 3.6234 | 3.3741 | 7.9351 | 5.7481 | 18.551 | 20.7381 | 28.6732 | 34.4213 | 0
14.3409 | 9.8072 | 2.278 | 2.417 | 4.3902 | 3.8341 | 9.0852 | 6.6682 | 24.1481 | 26.5652 | 35.6504 | 42.3186 | 14.3409 | 9.8072 | 2.288 | 2.417 | 4.3902 | 3.8341 | 9.0852 | 6.6682 | 24.1481 | 26.5652 | 35.6504 | 42.3186 | 0
10.4801 | 8.9707 | 2.1493 | 2.224 | 3.7467 | 3.448 | 8.12 | 5.896 | 19.4508 | 21.6748 | 29.7948 | 35.6908 | 10.4801 | 8.9707 | 2.1593 | 2.224 | 3.7467 | 3.448 | 8.12 | 5.896 | 19.4508 | 21.6748 | 29.7948 | 35.6908 | 0
1.9422 | 7.1208 | 1.8647 | 1.7971 | 2.3237 | 2.5942 | 5.9855 | 4.1884 | 9.063 | 10.8601 | 16.8456 | 21.0341 | 1.9422 | 7.1208 | 1.8747 | 1.7971 | 2.3237 | 2.5942 | 5.9855 | 4.1884 | 9.063 | 10.8601 | 16.8456 | 21.0341 | 0
-3.5251 | 5.9362 | 1.6825 | 1.5237 | 1.4125 | 2.0475 | 4.6187 | 3.095 | 2.4111 | 3.9349 | 8.5536 | 11.6486 | -3.5251 | 5.9362 | 1.6925 | 1.5237 | 1.4125 | 2.0475 | 4.6187 | 3.095 | 2.4111 | 3.9349 | 8.5536 | 11.6486 | 0
6.3941 | 8.0854 | 2.0131 | 2.0197 | 3.0657 | 3.0394 | 7.0985 | 5.0788 | 14.4795 | 16.4992 | 23.5978 | 28.6766 | 6.3941 | 8.0854 | 2.0231 | 2.0197 | 3.0657 | 3.0394 | 7.0985 | 5.0788 | 14.4795 | 16.4992 | 23.5978 | 28.6766 | 0
8.1827 | 8.4729 | 2.0728 | 2.1091 | 3.3638 | 3.2183 | 7.5457 | 5.4365 | 16.6556 | 18.7647 | 26.3104 | 31.7469 | 8.1827 | 8.4729 | 2.0828 | 2.1091 | 3.3638 | 3.2183 | 7.5457 | 5.4365 | 16.6556 | 18.7647 | 26.3104 | 31.7469 | 0
13.4254 | 9.6088 | 2.2475 | 2.3713 | 4.2376 | 3.7425 | 8.8563 | 6.4851 | 23.0342 | 25.4055 | 34.2618 | 40.7469 | 13.4254 | 9.6088 | 2.2575 | 2.3713 | 4.2376 | 3.7425 | 8.8563 | 6.4851 | 23.0342 | 25.4055 | 34.2618 | 40.7469 | 0
12.781 | 9.4692 | 2.226 | 2.339 | 4.1302 | 3.6781 | 8.6952 | 6.3562 | 22.2502 | 24.5892 | 33.2844 | 39.6406 | 12.781 | 9.4692 | 2.236 | 2.339 | 4.1302 | 3.6781 | 8.6952 | 6.3562 | 22.2502 | 24.5892 | 33.2844 | 39.6406 | 0
5.32 | 7.8527 | 1.9773 | 1.966 | 2.8867 | 2.932 | 6.83 | 4.864 | 13.1726 | 15.1386 | 21.9686 | 26.8326 | 5.32 | 7.8527 | 1.9873 | 1.966 | 2.8867 | 2.932 | 6.83 | 4.864 | 13.1726 | 15.1386 | 21.9686 | 26.8326 | 0
0.36357 | 6.7788 | 1.8121 | 1.7182 | 2.0606 | 2.4364 | 5.5909 | 3.8727 | 7.1423 | 8.8605 | 14.4514 | 18.3241 | 0.36357 | 6.7788 | 1.8221 | 1.7182 | 2.0606 | 2.4364 | 5.5909 | 3.8727 | 7.1423 | 8.8605 | 14.4514 | 18.3241 | 0
4.4875 | 7.6723 | 1.9496 | 1.9244 | 2.7479 | 2.8487 | 6.6219 | 4.6975 | 12.1597 | 14.0841 | 20.706 | 25.4035 | 4.4875 | 7.6723 | 1.9596 | 1.9244 | 2.7479 | 2.8487 | 6.6219 | 4.6975 | 12.1597 | 14.0841 | 20.706 | 25.4035 | 0
16.3134 | 10.2346 | 2.3438 | 2.5157 | 4.7189 | 4.0313 | 9.5783 | 7.0627 | 26.548 | 29.0636 | 38.642 | 45.7047 | 16.3134 | 10.2346 | 2.3538 | 2.5157 | 4.7189 | 4.0313 | 9.5783 | 7.0627 | 26.548 | 29.0636 | 38.642 | 45.7047 | 0
4.2492 | 7.6207 | 1.9416 | 1.9125 | 2.7082 | 2.8249 | 6.5623 | 4.6498 | 11.8698 | 13.7823 | 20.3446 | 24.9944 | 4.2492 | 7.6207 | 1.9516 | 1.9125 | 2.7082 | 2.8249 | 6.5623 | 4.6498 | 11.8698 | 13.7823 | 20.3446 | 24.9944 | 0
3.7637 | 7.5155 | 1.9255 | 1.8882 | 2.6273 | 2.7764 | 6.4409 | 4.5527 | 11.2792 | 13.1674 | 19.6083 | 24.161 | 3.7637 | 7.5155 | 1.9355 | 1.8882 | 2.6273 | 2.7764 | 6.4409 | 4.5527 | 11.2792 | 13.1674 | 19.6083 | 24.161 | 0
-1.4859 | 6.3781 | 1.7505 | 1.6257 | 1.7524 | 2.2514 | 5.1285 | 3.5028 | 4.8922 | 6.5179 | 11.6464 | 15.1492 | -1.4859 | 6.3781 | 1.7605 | 1.6257 | 1.7524 | 2.2514 | 5.1285 | 3.5028 | 4.8922 | 6.5179 | 11.6464 | 15.1492 | 0
13.1201 | 9.5427 | 2.2373 | 2.356 | 4.1867 | 3.712 | 8.78 | 6.424 | 22.6628 | 25.0188 | 33.7988 | 40.2228 | 13.1201 | 9.5427 | 2.2473 | 2.356 | 4.1867 | 3.712 | 8.78 | 6.424 | 22.6628 | 25.0188 | 33.7988 | 40.2228 | 0
1.2847 | 6.9783 | 1.8428 | 1.7642 | 2.2141 | 2.5285 | 5.8212 | 4.0569 | 8.263 | 10.0273 | 15.8484 | 19.9054 | 1.2847 | 6.9783 | 1.8528 | 1.7642 | 2.2141 | 2.5285 | 5.8212 | 4.0569 | 8.263 | 10.0273 | 15.8484 | 19.9054 | 0
10.1324 | 8.8954 | 2.1377 | 2.2066 | 3.6887 | 3.4132 | 8.0331 | 5.8265 | 19.0278 | 21.2344 | 29.2675 | 35.094 | 10.1324 | 8.8954 | 2.1477 | 2.2066 | 3.6887 | 3.4132 | 8.0331 | 5.8265 | 19.0278 | 21.2344 | 29.2675 | 35.094 | 0
19.078 | 10.8336 | 2.4359 | 2.6539 | 5.1797 | 4.3078 | 10.2695 | 7.6156 | 29.9115 | 32.5654 | 42.8349 | 50.4505 | 19.078 | 10.8336 | 2.4459 | 2.6539 | 5.1797 | 4.3078 | 10.2695 | 7.6156 | 29.9115 | 32.5654 | 42.8349 | 50.4505 | 0
14.4903 | 9.8396 | 2.283 | 2.4245 | 4.4151 | 3.849 | 9.1226 | 6.6981 | 24.3299 | 26.7544 | 35.877 | 42.5751 | 14.4903 | 9.8396 | 2.293 | 2.4245 | 4.4151 | 3.849 | 9.1226 | 6.6981 | 24.3299 | 26.7544 | 35.877 | 42.5751 | 0
1.3037 | 6.9825 | 1.8435 | 1.7652 | 2.2173 | 2.5304 | 5.8259 | 4.0607 | 8.2862 | 10.0514 | 15.8773 | 19.9381 | 1.3037 | 6.9825 | 1.8535 | 1.7652 | 2.2173 | 2.5304 | 5.8259 | 4.0607 | 8.2862 | 10.0514 | 15.8773 | 19.9381 | 0
4.5343 | 7.6824 | 1.9511 | 1.9267 | 2.7557 | 2.8534 | 6.6336 | 4.7069 | 12.2167 | 14.1434 | 20.777 | 25.4838 | 4.5343 | 7.6824 | 1.9611 | 1.9267 | 2.7557 | 2.8534 | 6.6336 | 4.7069 | 12.2167 | 14.1434 | 20.777 | 25.4838 | 0
8.9171 | 8.632 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5834 | 17.5492 | 19.695 | 27.4243 | 33.0077 | 8.9171 | 8.632 | 2.1072 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5834 | 17.5492 | 19.695 | 27.4243 | 33.0077 | 0
4.2696 | 7.6251 | 1.9423 | 1.9135 | 2.7116 | 2.827 | 6.5674 | 4.6539 | 11.8947 | 13.8082 | 20.3756 | 25.0295 | 4.2696 | 7.6251 | 1.9523 | 1.9135 | 2.7116 | 2.827 | 6.5674 | 4.6539 | 11.8947 | 13.8082 | 20.3756 | 25.0295 | 0
1.8769 | 7.1067 | 1.8626 | 1.7938 | 2.3128 | 2.5877 | 5.9692 | 4.1754 | 8.9835 | 10.7774 | 16.7466 | 20.922 | 1.8769 | 7.1067 | 1.8726 | 1.7938 | 2.3128 | 2.5877 | 5.9692 | 4.1754 | 8.9835 | 10.7774 | 16.7466 | 20.922 | 0
1.2769 | 6.9767 | 1.8426 | 1.7638 | 2.2128 | 2.5277 | 5.8192 | 4.0554 | 8.2536 | 10.0174 | 15.8367 | 19.8921 | 1.2769 | 6.9767 | 1.8526 | 1.7638 | 2.2128 | 2.5277 | 5.8192 | 4.0554 | 8.2536 | 10.0174 | 15.8367 | 19.8921 | 0
4.4293 | 7.6597 | 1.9476 | 1.9215 | 2.7382 | 2.8429 | 6.6073 | 4.6859 | 12.089 | 14.0105 | 20.6178 | 25.3037 | 4.4293 | 7.6597 | 1.9576 | 1.9215 | 2.7382 | 2.8429 | 6.6073 | 4.6859 | 12.089 | 14.0105 | 20.6178 | 25.3037 | 0
-0.71252 | 6.5456 | 1.7762 | 1.6644 | 1.8812 | 2.3287 | 5.3219 | 3.6575 | 5.8331 | 7.4975 | 12.8193 | 16.4768 | -0.71252 | 6.5456 | 1.7862 | 1.6644 | 1.8812 | 2.3287 | 5.3219 | 3.6575 | 5.8331 | 7.4975 | 12.8193 | 16.4768 | 0
0.56209 | 6.8218 | 1.8187 | 1.7281 | 2.0937 | 2.4562 | 5.6405 | 3.9124 | 7.3839 | 9.112 | 14.7525 | 18.6649 | 0.56209 | 6.8218 | 1.8287 | 1.7281 | 2.0937 | 2.4562 | 5.6405 | 3.9124 | 7.3839 | 9.112 | 14.7525 | 18.6649 | 0
3.2537 | 7.405 | 1.9085 | 1.8627 | 2.5423 | 2.7254 | 6.3134 | 4.4507 | 10.6587 | 12.5214 | 18.8348 | 23.2856 | 3.2537 | 7.405 | 1.9185 | 1.8627 | 2.5423 | 2.7254 | 6.3134 | 4.4507 | 10.6587 | 12.5214 | 18.8348 | 23.2856 | 0
4.564 | 7.6889 | 1.9521 | 1.9282 | 2.7607 | 2.8564 | 6.641 | 4.7128 | 12.2529 | 14.1811 | 20.8221 | 25.5349 | 4.564 | 7.6889 | 1.9621 | 1.9282 | 2.7607 | 2.8564 | 6.641 | 4.7128 | 12.2529 | 14.1811 | 20.8221 | 25.5349 | 0
17.5236 | 10.4968 | 2.3841 | 2.5762 | 4.9206 | 4.1524 | 9.8809 | 7.3047 | 28.0204 | 30.5966 | 40.4775 | 47.7823 | 17.5236 | 10.4968 | 2.3941 | 2.5762 | 4.9206 | 4.1524 | 9.8809 | 7.3047 | 28.0204 | 30.5966 | 40.4775 | 47.7823 | 0
8.2391 | 8.4851 | 2.0746 | 2.112 | 3.3732 | 3.2239 | 7.5598 | 5.4478 | 16.7242 | 18.8362 | 26.396 | 31.8438 | 8.2391 | 8.4851 | 2.0846 | 2.112 | 3.3732 | 3.2239 | 7.5598 | 5.4478 | 16.7242 | 18.8362 | 26.396 | 31.8438 | 0
11.3647 | 9.1623 | 2.1788 | 2.2682 | 3.8941 | 3.5365 | 8.3412 | 6.0729 | 20.527 | 22.7953 | 31.1364 | 37.2094 | 11.3647 | 9.1623 | 2.1888 | 2.2682 | 3.8941 | 3.5365 | 8.3412 | 6.0729 | 20.527 | 22.7953 | 31.1364 | 37.2094 | 0
-1.6549 | 6.3414 | 1.7448 | 1.6173 | 1.7242 | 2.2345 | 5.0863 | 3.469 | 4.6866 | 6.3038 | 11.3901 | 14.8591 | -1.6549 | 6.3414 | 1.7548 | 1.6173 | 1.7242 | 2.2345 | 5.0863 | 3.469 | 4.6866 | 6.3038 | 11.3901 | 14.8591 | 0
8.9418 | 8.6374 | 2.0981 | 2.1471 | 3.4903 | 3.2942 | 7.7354 | 5.5884 | 17.5791 | 19.7262 | 27.4617 | 33.05 | 8.9418 | 8.6374 | 2.1081 | 2.1471 | 3.4903 | 3.2942 | 7.7354 | 5.5884 | 17.5791 | 19.7262 | 27.4617 | 33.05 | 0
11.8561 | 9.2688 | 2.1952 | 2.2928 | 3.976 | 3.5856 | 8.464 | 6.1712 | 21.1249 | 23.4177 | 31.8817 | 38.053 | 11.8561 | 9.2688 | 2.2052 | 2.2928 | 3.976 | 3.5856 | 8.464 | 6.1712 | 21.1249 | 23.4177 | 31.8817 | 38.053 | 0
10.4949 | 8.9739 | 2.1498 | 2.2247 | 3.7492 | 3.4495 | 8.1237 | 5.899 | 19.4688 | 21.6936 | 29.8173 | 35.7163 | 10.4949 | 8.9739 | 2.1598 | 2.2247 | 3.7492 | 3.4495 | 8.1237 | 5.899 | 19.4688 | 21.6936 | 29.8173 | 35.7163 | 0
10.916 | 9.0651 | 2.1639 | 2.2458 | 3.8193 | 3.4916 | 8.229 | 5.9832 | 19.9811 | 22.2269 | 30.4559 | 36.4391 | 10.916 | 9.0651 | 2.1739 | 2.2458 | 3.8193 | 3.4916 | 8.229 | 5.9832 | 19.9811 | 22.2269 | 30.4559 | 36.4391 | 0
9.4413 | 8.7456 | 2.1147 | 2.1721 | 3.5736 | 3.3441 | 7.8603 | 5.6883 | 18.1869 | 20.359 | 28.2193 | 33.9076 | 9.4413 | 8.7456 | 2.1247 | 2.1721 | 3.5736 | 3.3441 | 7.8603 | 5.6883 | 18.1869 | 20.359 | 28.2193 | 33.9076 | 0
3.8479 | 7.5337 | 1.9283 | 1.8924 | 2.6413 | 2.7848 | 6.462 | 4.5696 | 11.3817 | 13.2741 | 19.7361 | 24.3056 | 3.8479 | 7.5337 | 1.9383 | 1.8924 | 2.6413 | 2.7848 | 6.462 | 4.5696 | 11.3817 | 13.2741 | 19.7361 | 24.3056 | 0
0.12473 | 6.727 | 1.8042 | 1.7062 | 2.0208 | 2.4125 | 5.5312 | 3.8249 | 6.8518 | 8.558 | 14.0892 | 17.9141 | 0.12473 | 6.727 | 1.8142 | 1.7062 | 2.0208 | 2.4125 | 5.5312 | 3.8249 | 6.8518 | 8.558 | 14.0892 | 17.9141 | 0
15.3826 | 10.0329 | 2.3128 | 2.4691 | 4.5638 | 3.9383 | 9.3457 | 6.8765 | 25.4155 | 27.8847 | 37.2303 | 44.1068 | 15.3826 | 10.0329 | 2.3228 | 2.4691 | 4.5638 | 3.9383 | 9.3457 | 6.8765 | 25.4155 | 27.8847 | 37.2303 | 44.1068 | 0
5.5747 | 7.9078 | 1.9858 | 1.9787 | 2.9291 | 2.9575 | 6.8937 | 4.9149 | 13.4825 | 15.4613 | 22.3549 | 27.2699 | 5.5747 | 7.9078 | 1.9958 | 1.9787 | 2.9291 | 2.9575 | 6.8937 | 4.9149 | 13.4825 | 15.4613 | 22.3549 | 27.2699 | 0
7.5314 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8632 | 17.9398 | 25.3227 | 30.629 | 7.5314 | 8.3318 | 2.061 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8632 | 17.9398 | 25.3227 | 30.629 | 0
5.6536 | 7.9249 | 1.9885 | 1.9827 | 2.9423 | 2.9654 | 6.9134 | 4.9307 | 13.5786 | 15.5612 | 22.4746 | 27.4054 | 5.6536 | 7.9249 | 1.9985 | 1.9827 | 2.9423 | 2.9654 | 6.9134 | 4.9307 | 13.5786 | 15.5612 | 22.4746 | 27.4054 | 0
7.9005 | 8.4118 | 2.0633 | 2.095 | 3.3167 | 3.19 | 7.4751 | 5.3801 | 16.3122 | 18.4073 | 25.8824 | 31.2625 | 7.9005 | 8.4118 | 2.0733 | 2.095 | 3.3167 | 3.19 | 7.4751 | 5.3801 | 16.3122 | 18.4073 | 25.8824 | 31.2625 | 0
2.7503 | 7.2959 | 1.8917 | 1.8375 | 2.4584 | 2.675 | 6.1876 | 4.3501 | 10.0462 | 11.8837 | 18.0713 | 22.4213 | 2.7503 | 7.2959 | 1.9017 | 1.8375 | 2.4584 | 2.675 | 6.1876 | 4.3501 | 10.0462 | 11.8837 | 18.0713 | 22.4213 | 0
15.9912 | 10.1648 | 2.333 | 2.4996 | 4.6652 | 3.9991 | 9.4978 | 6.9982 | 26.156 | 28.6556 | 38.1534 | 45.1516 | 15.9912 | 10.1648 | 2.343 | 2.4996 | 4.6652 | 3.9991 | 9.4978 | 6.9982 | 26.156 | 28.6556 | 38.1534 | 45.1516 | 0
3.5741 | 7.4744 | 1.9191 | 1.8787 | 2.5957 | 2.7574 | 6.3935 | 4.5148 | 11.0485 | 12.9272 | 19.3207 | 23.8356 | 3.5741 | 7.4744 | 1.9291 | 1.8787 | 2.5957 | 2.7574 | 6.3935 | 4.5148 | 11.0485 | 12.9272 | 19.3207 | 23.8356 | 0
8.2161 | 8.4802 | 2.0739 | 2.1108 | 3.3693 | 3.2216 | 7.554 | 5.4432 | 16.6962 | 18.8071 | 26.3611 | 31.8043 | 8.2161 | 8.4802 | 2.0839 | 2.1108 | 3.3693 | 3.2216 | 7.554 | 5.4432 | 16.6962 | 18.8071 | 26.3611 | 31.8043 | 0
11.5303 | 9.1982 | 2.1843 | 2.2765 | 3.9217 | 3.553 | 8.3826 | 6.1061 | 20.7286 | 23.0051 | 31.3877 | 37.4937 | 11.5303 | 9.1982 | 2.1943 | 2.2765 | 3.9217 | 3.553 | 8.3826 | 6.1061 | 20.7286 | 23.0051 | 31.3877 | 37.4937 | 0
9.1597 | 8.6846 | 2.1053 | 2.158 | 3.5266 | 3.316 | 7.7899 | 5.6319 | 17.8443 | 20.0023 | 27.7923 | 33.4242 | 9.1597 | 8.6846 | 2.1153 | 2.158 | 3.5266 | 3.316 | 7.7899 | 5.6319 | 17.8443 | 20.0023 | 27.7923 | 33.4242 | 0
12.984 | 9.5132 | 2.2328 | 2.3492 | 4.164 | 3.6984 | 8.746 | 6.3968 | 22.4972 | 24.8464 | 33.5924 | 39.9892 | 12.984 | 9.5132 | 2.2428 | 2.3492 | 4.164 | 3.6984 | 8.746 | 6.3968 | 22.4972 | 24.8464 | 33.5924 | 39.9892 | 0
18.7844 | 10.7699 | 2.4261 | 2.6392 | 5.1307 | 4.2784 | 10.1961 | 7.5569 | 29.5543 | 32.1935 | 42.3896 | 49.9465 | 18.7844 | 10.7699 | 2.4361 | 2.6392 | 5.1307 | 4.2784 | 10.1961 | 7.5569 | 29.5543 | 32.1935 | 42.3896 | 49.9465 | 0
9.9286 | 8.8512 | 2.131 | 2.1964 | 3.6548 | 3.3929 | 7.9822 | 5.7857 | 18.7799 | 20.9763 | 28.9585 | 34.7442 | 9.9286 | 8.8512 | 2.141 | 2.1964 | 3.6548 | 3.3929 | 7.9822 | 5.7857 | 18.7799 | 20.9763 | 28.9585 | 34.7442 | 0
2.0856 | 7.1519 | 1.8695 | 1.8043 | 2.3476 | 2.6086 | 6.0214 | 4.2171 | 9.2375 | 11.0418 | 17.0632 | 21.2803 | 2.0856 | 7.1519 | 1.8795 | 1.8043 | 2.3476 | 2.6086 | 6.0214 | 4.2171 | 9.2375 | 11.0418 | 17.0632 | 21.2803 | 0
7.7123 | 8.371 | 2.0571 | 2.0856 | 3.2854 | 3.1712 | 7.4281 | 5.3425 | 16.0833 | 18.169 | 25.5971 | 30.9395 | 7.7123 | 8.371 | 2.0671 | 2.0856 | 3.2854 | 3.1712 | 7.4281 | 5.3425 | 16.0833 | 18.169 | 25.5971 | 30.9395 | 0
4.3418 | 7.6407 | 1.9447 | 1.9171 | 2.7236 | 2.8342 | 6.5855 | 4.6684 | 11.9825 | 13.8996 | 20.4851 | 25.1535 | 4.3418 | 7.6407 | 1.9547 | 1.9171 | 2.7236 | 2.8342 | 6.5855 | 4.6684 | 11.9825 | 13.8996 | 20.4851 | 25.1535 | 0
11.026 | 9.089 | 2.1675 | 2.2513 | 3.8377 | 3.5026 | 8.2565 | 6.0052 | 20.115 | 22.3663 | 30.6228 | 36.628 | 11.026 | 9.089 | 2.1775 | 2.2513 | 3.8377 | 3.5026 | 8.2565 | 6.0052 | 20.115 | 22.3663 | 30.6228 | 36.628 | 0
17.0012 | 10.3836 | 2.3667 | 2.5501 | 4.8335 | 4.1001 | 9.7503 | 7.2002 | 27.3849 | 29.9349 | 39.6852 | 46.8855 | 17.0012 | 10.3836 | 2.3767 | 2.5501 | 4.8335 | 4.1001 | 9.7503 | 7.2002 | 27.3849 | 29.9349 | 39.6852 | 46.8855 | 0
2.8353 | 7.3143 | 1.8945 | 1.8418 | 2.4726 | 2.6835 | 6.2088 | 4.3671 | 10.1496 | 11.9914 | 18.2002 | 22.5673 | 2.8353 | 7.3143 | 1.9045 | 1.8418 | 2.4726 | 2.6835 | 6.2088 | 4.3671 | 10.1496 | 11.9914 | 18.2002 | 22.5673 | 0
2.9314 | 7.3351 | 1.8977 | 1.8466 | 2.4886 | 2.6931 | 6.2329 | 4.3863 | 10.2666 | 12.1132 | 18.346 | 22.7323 | 2.9314 | 7.3351 | 1.9077 | 1.8466 | 2.4886 | 2.6931 | 6.2329 | 4.3863 | 10.2666 | 12.1132 | 18.346 | 22.7323 | 0
0.2458 | 6.7533 | 1.8082 | 1.7123 | 2.041 | 2.4246 | 5.5615 | 3.8492 | 6.9991 | 8.7114 | 14.2728 | 18.122 | 0.2458 | 6.7533 | 1.8182 | 1.7123 | 2.041 | 2.4246 | 5.5615 | 3.8492 | 6.9991 | 8.7114 | 14.2728 | 18.122 | 0
6.4896 | 8.1061 | 2.0163 | 2.0245 | 3.0816 | 3.049 | 7.1224 | 5.0979 | 14.5957 | 16.6202 | 23.7426 | 28.8405 | 6.4896 | 8.1061 | 2.0263 | 2.0245 | 3.0816 | 3.049 | 7.1224 | 5.0979 | 14.5957 | 16.6202 | 23.7426 | 28.8405 | 0
-6.0201 | 5.3956 | 1.5993 | 1.399 | 0.99665 | 1.798 | 3.995 | 2.596 | -0.62448 | 0.77452 | 4.7695 | 7.3655 | -6.0201 | 5.3956 | 1.6093 | 1.399 | 0.99665 | 1.798 | 3.995 | 2.596 | -0.62448 | 0.77452 | 4.7695 | 7.3655 | 0
3.3036 | 7.4158 | 1.9101 | 1.8652 | 2.5506 | 2.7304 | 6.3259 | 4.4607 | 10.7194 | 12.5846 | 18.9105 | 23.3712 | 3.3036 | 7.4158 | 1.9201 | 1.8652 | 2.5506 | 2.7304 | 6.3259 | 4.4607 | 10.7194 | 12.5846 | 18.9105 | 23.3712 | 0
8.8664 | 8.621 | 2.0955 | 2.1433 | 3.4777 | 3.2866 | 7.7166 | 5.5733 | 17.4874 | 19.6307 | 27.3473 | 32.9206 | 8.8664 | 8.621 | 2.1055 | 2.1433 | 3.4777 | 3.2866 | 7.7166 | 5.5733 | 17.4874 | 19.6307 | 27.3473 | 32.9206 | 0
13.6777 | 9.6635 | 2.2559 | 2.3839 | 4.2796 | 3.7678 | 8.9194 | 6.5355 | 23.3412 | 25.7251 | 34.6446 | 41.1801 | 13.6777 | 9.6635 | 2.2659 | 2.3839 | 4.2796 | 3.7678 | 8.9194 | 6.5355 | 23.3412 | 25.7251 | 34.6446 | 41.1801 | 0
7.5315 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8633 | 17.9399 | 25.3228 | 30.629 | 7.5315 | 8.3318 | 2.061 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8633 | 17.9399 | 25.3228 | 30.629 | 0
6.5002 | 8.1084 | 2.0167 | 2.025 | 3.0834 | 3.05 | 7.1251 | 5.1 | 14.6086 | 16.6336 | 23.7587 | 28.8587 | 6.5002 | 8.1084 | 2.0267 | 2.025 | 3.0834 | 3.05 | 7.1251 | 5.1 | 14.6086 | 16.6336 | 23.7587 | 28.8587 | 0
12.3442 | 9.3746 | 2.2115 | 2.3172 | 4.0574 | 3.6344 | 8.586 | 6.2688 | 21.7187 | 24.036 | 32.622 | 38.8908 | 12.3442 | 9.3746 | 2.2215 | 2.3172 | 4.0574 | 3.6344 | 8.586 | 6.2688 | 21.7187 | 24.036 | 32.622 | 38.8908 | 0
-2.6847 | 6.1183 | 1.7105 | 1.5658 | 1.5526 | 2.1315 | 4.8288 | 3.2631 | 3.4337 | 4.9994 | 9.8283 | 13.0913 | -2.6847 | 6.1183 | 1.7205 | 1.5658 | 1.5526 | 2.1315 | 4.8288 | 3.2631 | 3.4337 | 4.9994 | 9.8283 | 13.0913 | 0
11.3098 | 9.1505 | 2.177 | 2.2655 | 3.885 | 3.531 | 8.3274 | 6.062 | 20.4602 | 22.7257 | 31.0532 | 37.1151 | 11.3098 | 9.1505 | 2.187 | 2.2655 | 3.885 | 3.531 | 8.3274 | 6.062 | 20.4602 | 22.7257 | 31.0532 | 37.1151 | 0
11.2312 | 9.1334 | 2.1744 | 2.2616 | 3.8719 | 3.5231 | 8.3078 | 6.0462 | 20.3646 | 22.6262 | 30.934 | 36.9802 | 11.2312 | 9.1334 | 2.1844 | 2.2616 | 3.8719 | 3.5231 | 8.3078 | 6.0462 | 20.3646 | 22.6262 | 30.934 | 36.9802 | 0
-2.2417 | 6.2143 | 1.7253 | 1.5879 | 1.6264 | 2.1758 | 4.9396 | 3.3517 | 3.9725 | 5.5605 | 10.5 | 13.8517 | -2.2417 | 6.2143 | 1.7353 | 1.5879 | 1.6264 | 2.1758 | 4.9396 | 3.3517 | 3.9725 | 5.5605 | 10.5 | 13.8517 | 0
13.1798 | 9.5556 | 2.2393 | 2.359 | 4.1966 | 3.718 | 8.795 | 6.436 | 22.7354 | 25.0944 | 33.8894 | 40.3253 | 13.1798 | 9.5556 | 2.2493 | 2.359 | 4.1966 | 3.718 | 8.795 | 6.436 | 22.7354 | 25.0944 | 33.8894 | 40.3253 | 0
-6.0136 | 5.397 | 1.5995 | 1.3993 | 0.99773 | 1.7986 | 3.9966 | 2.5973 | -0.61658 | 0.78274 | 4.7793 | 7.3766 | -6.0136 | 5.397 | 1.6095 | 1.3993 | 0.99773 | 1.7986 | 3.9966 | 2.5973 | -0.61658 | 0.78274 | 4.7793 | 7.3766 | 0
2.8839 | 7.3249 | 1.8961 | 1.8442 | 2.4807 | 2.6884 | 6.221 | 4.3768 | 10.2088 | 12.053 | 18.274 | 22.6508 | 2.8839 | 7.3249 | 1.9061 | 1.8442 | 2.4807 | 2.6884 | 6.221 | 4.3768 | 10.2088 | 12.053 | 18.274 | 22.6508 | 0
8.9173 | 8.6321 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5835 | 17.5494 | 19.6953 | 27.4246 | 33.0081 | 8.9173 | 8.6321 | 2.1072 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5835 | 17.5494 | 19.6953 | 27.4246 | 33.0081 | 0
7.3594 | 8.2945 | 2.0453 | 2.068 | 3.2266 | 3.1359 | 7.3399 | 5.2719 | 15.654 | 17.722 | 25.0618 | 30.3337 | 7.3594 | 8.2945 | 2.0553 | 2.068 | 3.2266 | 3.1359 | 7.3399 | 5.2719 | 15.654 | 17.722 | 25.0618 | 30.3337 | 0
10.6967 | 9.0176 | 2.1566 | 2.2348 | 3.7828 | 3.4697 | 8.1742 | 5.9393 | 19.7143 | 21.9491 | 30.1233 | 36.0626 | 10.6967 | 9.0176 | 2.1666 | 2.2348 | 3.7828 | 3.4697 | 8.1742 | 5.9393 | 19.7143 | 21.9491 | 30.1233 | 36.0626 | 0
14.8238 | 9.9118 | 2.2941 | 2.4412 | 4.4706 | 3.8824 | 9.206 | 6.7648 | 24.7356 | 27.1768 | 36.3828 | 43.1475 | 14.8238 | 9.9118 | 2.3041 | 2.4412 | 4.4706 | 3.8824 | 9.206 | 6.7648 | 24.7356 | 27.1768 | 36.3828 | 43.1475 | 0
11.6384 | 9.2216 | 2.1879 | 2.2819 | 3.9397 | 3.5638 | 8.4096 | 6.1277 | 20.86 | 23.1419 | 31.5515 | 37.6792 | 11.6384 | 9.2216 | 2.1979 | 2.2819 | 3.9397 | 3.5638 | 8.4096 | 6.1277 | 20.86 | 23.1419 | 31.5515 | 37.6792 | 0
17.6788 | 10.5304 | 2.3893 | 2.5839 | 4.9465 | 4.1679 | 9.9197 | 7.3358 | 28.2092 | 30.7931 | 40.7128 | 48.0486 | 17.6788 | 10.5304 | 2.3993 | 2.5839 | 4.9465 | 4.1679 | 9.9197 | 7.3358 | 28.2092 | 30.7931 | 40.7128 | 48.0486 | 0
4.3589 | 7.6444 | 1.9453 | 1.9179 | 2.7265 | 2.8359 | 6.5897 | 4.6718 | 12.0033 | 13.9213 | 20.511 | 25.1828 | 4.3589 | 7.6444 | 1.9553 | 1.9179 | 2.7265 | 2.8359 | 6.5897 | 4.6718 | 12.0033 | 13.9213 | 20.511 | 25.1828 | 0
0.47148 | 6.8022 | 1.8157 | 1.7236 | 2.0786 | 2.4471 | 5.6179 | 3.8943 | 7.2736 | 8.9972 | 14.6151 | 18.5094 | 0.47148 | 6.8022 | 1.8257 | 1.7236 | 2.0786 | 2.4471 | 5.6179 | 3.8943 | 7.2736 | 8.9972 | 14.6151 | 18.5094 | 0
7.8912 | 8.4097 | 2.063 | 2.0946 | 3.3152 | 3.1891 | 7.4728 | 5.3782 | 16.3009 | 18.3955 | 25.8682 | 31.2465 | 7.8912 | 8.4097 | 2.073 | 2.0946 | 3.3152 | 3.1891 | 7.4728 | 5.3782 | 16.3009 | 18.3955 | 25.8682 | 31.2465 | 0
4.3809 | 7.6492 | 1.946 | 1.919 | 2.7301 | 2.8381 | 6.5952 | 4.6762 | 12.0301 | 13.9491 | 20.5444 | 25.2205 | 4.3809 | 7.6492 | 1.956 | 1.919 | 2.7301 | 2.8381 | 6.5952 | 4.6762 | 12.0301 | 13.9491 | 20.5444 | 25.2205 | 0
12.5045 | 9.4093 | 2.2168 | 2.3252 | 4.0841 | 3.6505 | 8.6261 | 6.3009 | 21.9138 | 24.2391 | 32.8652 | 39.1661 | 12.5045 | 9.4093 | 2.2268 | 2.3252 | 4.0841 | 3.6505 | 8.6261 | 6.3009 | 21.9138 | 24.2391 | 32.8652 | 39.1661 | 0
-2.5623 | 6.1448 | 1.7146 | 1.5719 | 1.5729 | 2.1438 | 4.8594 | 3.2875 | 3.5825 | 5.1544 | 10.0138 | 13.3013 | -2.5623 | 6.1448 | 1.7246 | 1.5719 | 1.5729 | 2.1438 | 4.8594 | 3.2875 | 3.5825 | 5.1544 | 10.0138 | 13.3013 | 0
5.628 | 7.9194 | 1.9876 | 1.9814 | 2.938 | 2.9628 | 6.907 | 4.9256 | 13.5474 | 15.5288 | 22.4358 | 27.3614 | 5.628 | 7.9194 | 1.9976 | 1.9814 | 2.938 | 2.9628 | 6.907 | 4.9256 | 13.5474 | 15.5288 | 22.4358 | 27.3614 | 0
-2.8667 | 6.0789 | 1.7044 | 1.5567 | 1.5222 | 2.1133 | 4.7833 | 3.2267 | 3.2122 | 4.7689 | 9.5522 | 12.7789 | -2.8667 | 6.0789 | 1.7144 | 1.5567 | 1.5222 | 2.1133 | 4.7833 | 3.2267 | 3.2122 | 4.7689 | 9.5522 | 12.7789 | 0
-6.8201 | 5.2223 | 1.5727 | 1.359 | 0.86332 | 1.718 | 3.795 | 2.436 | -1.5977 | -0.23874 | 3.5562 | 5.9922 | -6.8201 | 5.2223 | 1.5827 | 1.359 | 0.86332 | 1.718 | 3.795 | 2.436 | -1.5977 | -0.23874 | 3.5562 | 5.9922 | 0
-0.06598 | 6.6857 | 1.7978 | 1.6967 | 1.989 | 2.3934 | 5.4835 | 3.7868 | 6.6197 | 8.3164 | 13.7999 | 17.5867 | -0.06598 | 6.6857 | 1.8078 | 1.6967 | 1.989 | 2.3934 | 5.4835 | 3.7868 | 6.6197 | 8.3164 | 13.7999 | 17.5867 | 0
-4.274 | 5.774 | 1.6575 | 1.4863 | 1.2877 | 1.9726 | 4.4315 | 2.9452 | 1.4999 | 2.9862 | 7.4177 | 10.3629 | -4.274 | 5.774 | 1.6675 | 1.4863 | 1.2877 | 1.9726 | 4.4315 | 2.9452 | 1.4999 | 2.9862 | 7.4177 | 10.3629 | 0
9.4 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.85 | 5.68 | 18.1367 | 20.3067 | 28.1567 | 33.8367 | 9.4 | 8.7367 | 2.1233 | 2.17 | 3.5667 | 3.34 | 7.85 | 5.68 | 18.1367 | 20.3067 | 28.1567 | 33.8367 | 0
-0.6032 | 6.5693 | 1.7799 | 1.6698 | 1.8995 | 2.3397 | 5.3492 | 3.6794 | 5.9661 | 7.6359 | 12.9851 | 16.6645 | -0.6032 | 6.5693 | 1.7899 | 1.6698 | 1.8995 | 2.3397 | 5.3492 | 3.6794 | 5.9661 | 7.6359 | 12.9851 | 16.6645 | 0
0.58262 | 6.8262 | 1.8194 | 1.7291 | 2.0971 | 2.4583 | 5.6457 | 3.9165 | 7.4089 | 9.138 | 14.7836 | 18.7002 | 0.58262 | 6.8262 | 1.8294 | 1.7291 | 2.0971 | 2.4583 | 5.6457 | 3.9165 | 7.4089 | 9.138 | 14.7836 | 18.7002 | 0
6.9663 | 8.2094 | 2.0322 | 2.0483 | 3.161 | 3.0966 | 7.2416 | 5.1933 | 15.1756 | 17.2239 | 24.4655 | 29.6587 | 6.9663 | 8.2094 | 2.0422 | 2.0483 | 3.161 | 3.0966 | 7.2416 | 5.1933 | 15.1756 | 17.2239 | 24.4655 | 29.6587 | 0
8.3163 | 8.5019 | 2.0772 | 2.1158 | 3.386 | 3.2316 | 7.5791 | 5.4633 | 16.8181 | 18.9339 | 26.513 | 31.9762 | 8.3163 | 8.5019 | 2.0872 | 2.1158 | 3.386 | 3.2316 | 7.5791 | 5.4633 | 16.8181 | 18.9339 | 26.513 | 31.9762 | 0
-4.5469 | 5.7148 | 1.6484 | 1.4727 | 1.2422 | 1.9453 | 4.3633 | 2.8906 | 1.1679 | 2.6406 | 7.0038 | 9.8944 | -4.5469 | 5.7148 | 1.6584 | 1.4727 | 1.2422 | 1.9453 | 4.3633 | 2.8906 | 1.1679 | 2.6406 | 7.0038 | 9.8944 | 0
-7.9943 | 4.9679 | 1.5335 | 1.3003 | 0.66762 | 1.6006 | 3.5014 | 2.2011 | -3.0264 | -1.7261 | 1.7753 | 3.9765 | -7.9943 | 4.9679 | 1.5435 | 1.3003 | 0.66762 | 1.6006 | 3.5014 | 2.2011 | -3.0264 | -1.7261 | 1.7753 | 3.9765 | 0
4.1948 | 7.6089 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5487 | 4.639 | 11.8036 | 13.7134 | 20.2621 | 24.901 | 4.1948 | 7.6089 | 1.9498 | 1.9097 | 2.6991 | 2.8195 | 6.5487 | 4.639 | 11.8036 | 13.7134 | 20.2621 | 24.901 | 0
0.29908 | 6.7648 | 1.81 | 1.715 | 2.0498 | 2.4299 | 5.5748 | 3.8598 | 7.0639 | 8.7788 | 14.3536 | 18.2134 | 0.29908 | 6.7648 | 1.82 | 1.715 | 2.0498 | 2.4299 | 5.5748 | 3.8598 | 7.0639 | 8.7788 | 14.3536 | 18.2134 | 0
2.5167 | 7.2453 | 1.8839 | 1.8258 | 2.4194 | 2.6517 | 6.1292 | 4.3033 | 9.762 | 11.5878 | 17.717 | 22.0203 | 2.5167 | 7.2453 | 1.8939 | 1.8258 | 2.4194 | 2.6517 | 6.1292 | 4.3033 | 9.762 | 11.5878 | 17.717 | 22.0203 | 0
14.5896 | 9.8611 | 2.2863 | 2.4295 | 4.4316 | 3.859 | 9.1474 | 6.7179 | 24.4507 | 26.8802 | 36.0276 | 42.7455 | 14.5896 | 9.8611 | 2.2963 | 2.4295 | 4.4316 | 3.859 | 9.1474 | 6.7179 | 24.4507 | 26.8802 | 36.0276 | 42.7455 | 0
5.9257 | 7.9839 | 1.9975 | 1.9963 | 2.9876 | 2.9926 | 6.9814 | 4.9851 | 13.9095 | 15.9058 | 22.8872 | 27.8724 | 5.9257 | 7.9839 | 2.0075 | 1.9963 | 2.9876 | 2.9926 | 6.9814 | 4.9851 | 13.9095 | 15.9058 | 22.8872 | 27.8724 | 0
4.8036 | 7.7408 | 1.9601 | 1.9402 | 2.8006 | 2.8804 | 6.7009 | 4.7607 | 12.5443 | 14.4845 | 21.1854 | 25.9461 | 4.8036 | 7.7408 | 1.9701 | 1.9402 | 2.8006 | 2.8804 | 6.7009 | 4.7607 | 12.5443 | 14.4845 | 21.1854 | 25.9461 | 0
2.8171 | 7.3104 | 1.8939 | 1.8409 | 2.4695 | 2.6817 | 6.2043 | 4.3634 | 10.1275 | 11.9683 | 18.1726 | 22.536 | 2.8171 | 7.3104 | 1.9039 | 1.8409 | 2.4695 | 2.6817 | 6.2043 | 4.3634 | 10.1275 | 11.9683 | 18.1726 | 22.536 | 0
7.7332 | 8.3755 | 2.0578 | 2.0867 | 3.2889 | 3.1733 | 7.4333 | 5.3466 | 16.1088 | 18.1954 | 25.6287 | 30.9754 | 7.7332 | 8.3755 | 2.0678 | 2.0867 | 3.2889 | 3.1733 | 7.4333 | 5.3466 | 16.1088 | 18.1954 | 25.6287 | 30.9754 | 0
10.7305 | 9.0249 | 2.1577 | 2.2365 | 3.7884 | 3.473 | 8.1826 | 5.9461 | 19.7554 | 21.9919 | 30.1745 | 36.1206 | 10.7305 | 9.0249 | 2.1677 | 2.2365 | 3.7884 | 3.473 | 8.1826 | 5.9461 | 19.7554 | 21.9919 | 30.1745 | 36.1206 | 0
8.4966 | 8.5409 | 2.0832 | 2.1248 | 3.4161 | 3.2497 | 7.6242 | 5.4993 | 17.0375 | 19.1624 | 26.7865 | 32.2858 | 8.4966 | 8.5409 | 2.0932 | 2.1248 | 3.4161 | 3.2497 | 7.6242 | 5.4993 | 17.0375 | 19.1624 | 26.7865 | 32.2858 | 0
-8.2772 | 4.9066 | 1.5241 | 1.2861 | 0.62047 | 1.5723 | 3.4307 | 2.1446 | -3.3706 | -2.0844 | 1.3463 | 3.4908 | -8.2772 | 4.9066 | 1.5341 | 1.2861 | 0.62047 | 1.5723 | 3.4307 | 2.1446 | -3.3706 | -2.0844 | 1.3463 | 3.4908 | 0
8.6945 | 8.5838 | 2.0898 | 2.1347 | 3.4491 | 3.2695 | 7.6736 | 5.5389 | 17.2783 | 19.413 | 27.0867 | 32.6256 | 8.6945 | 8.5838 | 2.0998 | 2.1347 | 3.4491 | 3.2695 | 7.6736 | 5.5389 | 17.2783 | 19.413 | 27.0867 | 32.6256 | 0
4.4416 | 7.6624 | 1.9481 | 1.9221 | 2.7403 | 2.8442 | 6.6104 | 4.6883 | 12.104 | 14.0261 | 20.6365 | 25.3248 | 4.4416 | 7.6624 | 1.9581 | 1.9221 | 2.7403 | 2.8442 | 6.6104 | 4.6883 | 12.104 | 14.0261 | 20.6365 | 25.3248 | 0
4.5166 | 7.6786 | 1.9506 | 1.9258 | 2.7528 | 2.8517 | 6.6292 | 4.7033 | 12.1953 | 14.1211 | 20.7502 | 25.4536 | 4.5166 | 7.6786 | 1.9606 | 1.9258 | 2.7528 | 2.8517 | 6.6292 | 4.7033 | 12.1953 | 14.1211 | 20.7502 | 25.4536 | 0
7.1372 | 8.2464 | 2.0379 | 2.0569 | 3.1895 | 3.1137 | 7.2843 | 5.2274 | 15.3835 | 17.4404 | 24.7247 | 29.9521 | 7.1372 | 8.2464 | 2.0479 | 2.0569 | 3.1895 | 3.1137 | 7.2843 | 5.2274 | 15.3835 | 17.4404 | 24.7247 | 29.9521 | 0
9.3226 | 8.7199 | 2.1108 | 2.1661 | 3.5538 | 3.3323 | 7.8307 | 5.6645 | 18.0425 | 20.2087 | 28.0393 | 33.7039 | 9.3226 | 8.7199 | 2.1208 | 2.1661 | 3.5538 | 3.3323 | 7.8307 | 5.6645 | 18.0425 | 20.2087 | 28.0393 | 33.7039 | 0
1.1275 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7819 | 4.0255 | 8.0717 | 9.8281 | 15.61 | 19.6355 | 1.1275 | 6.9443 | 1.8476 | 1.7564 | 2.1879 | 2.5127 | 5.7819 | 4.0255 | 8.0717 | 9.8281 | 15.61 | 19.6355 | 0
-2.6418 | 6.1276 | 1.7119 | 1.5679 | 1.5597 | 2.1358 | 4.8395 | 3.2716 | 3.4858 | 5.0537 | 9.8932 | 13.1649 | -2.6418 | 6.1276 | 1.7219 | 1.5679 | 1.5597 | 2.1358 | 4.8395 | 3.2716 | 3.4858 | 5.0537 | 9.8932 | 13.1649 | 0
9.0604 | 8.6631 | 2.102 | 2.153 | 3.5101 | 3.306 | 7.7651 | 5.6121 | 17.7234 | 19.8765 | 27.6415 | 33.2536 | 9.0604 | 8.6631 | 2.112 | 2.153 | 3.5101 | 3.306 | 7.7651 | 5.6121 | 17.7234 | 19.8765 | 27.6415 | 33.2536 | 0
10.6866 | 9.0154 | 2.1562 | 2.2343 | 3.7811 | 3.4687 | 8.1717 | 5.9373 | 19.7021 | 21.9364 | 30.1081 | 36.0454 | 10.6866 | 9.0154 | 2.1662 | 2.2343 | 3.7811 | 3.4687 | 8.1717 | 5.9373 | 19.7021 | 21.9364 | 30.1081 | 36.0454 | 0
8.5379 | 8.5499 | 2.0846 | 2.1269 | 3.423 | 3.2538 | 7.6345 | 5.5076 | 17.0878 | 19.2146 | 26.8491 | 32.3567 | 8.5379 | 8.5499 | 2.0946 | 2.1269 | 3.423 | 3.2538 | 7.6345 | 5.5076 | 17.0878 | 19.2146 | 26.8491 | 32.3567 | 0
1.8028 | 7.0906 | 1.8601 | 1.7901 | 2.3005 | 2.5803 | 5.9507 | 4.1606 | 8.8935 | 10.6836 | 16.6343 | 20.7949 | 1.8028 | 7.0906 | 1.8701 | 1.7901 | 2.3005 | 2.5803 | 5.9507 | 4.1606 | 8.8935 | 10.6836 | 16.6343 | 20.7949 | 0
0.2989 | 6.7648 | 1.81 | 1.7149 | 2.0498 | 2.4299 | 5.5747 | 3.8598 | 7.0637 | 8.7786 | 14.3533 | 18.2131 | 0.2989 | 6.7648 | 1.82 | 1.7149 | 2.0498 | 2.4299 | 5.5747 | 3.8598 | 7.0637 | 8.7786 | 14.3533 | 18.2131 | 0
-0.13421 | 6.6709 | 1.7955 | 1.6933 | 1.9776 | 2.3866 | 5.4664 | 3.7732 | 6.5367 | 8.23 | 13.6965 | 17.4696 | -0.13421 | 6.6709 | 1.8055 | 1.6933 | 1.9776 | 2.3866 | 5.4664 | 3.7732 | 6.5367 | 8.23 | 13.6965 | 17.4696 | 0
7.0264 | 8.2224 | 2.0342 | 2.0513 | 3.1711 | 3.1026 | 7.2566 | 5.2053 | 15.2488 | 17.3001 | 24.5567 | 29.762 | 7.0264 | 8.2224 | 2.0442 | 2.0513 | 3.1711 | 3.1026 | 7.2566 | 5.2053 | 15.2488 | 17.3001 | 24.5567 | 29.762 | 0
15.9381 | 10.1533 | 2.3313 | 2.4969 | 4.6563 | 3.9938 | 9.4845 | 6.9876 | 26.0913 | 28.5883 | 38.0728 | 45.0604 | 15.9381 | 10.1533 | 2.3413 | 2.4969 | 4.6563 | 3.9938 | 9.4845 | 6.9876 | 26.0913 | 28.5883 | 38.0728 | 45.0604 | 0
4.2657 | 7.6242 | 1.9422 | 1.9133 | 2.711 | 2.8266 | 6.5664 | 4.6531 | 11.89 | 13.8033 | 20.3697 | 25.0229 | 4.2657 | 7.6242 | 1.9522 | 1.9133 | 2.711 | 2.8266 | 6.5664 | 4.6531 | 11.89 | 13.8033 | 20.3697 | 25.0229 | 0
-1.1135 | 6.4587 | 1.7629 | 1.6443 | 1.8144 | 2.2886 | 5.2216 | 3.5773 | 5.3452 | 6.9896 | 12.2112 | 15.7885 | -1.1135 | 6.4587 | 1.7729 | 1.6443 | 1.8144 | 2.2886 | 5.2216 | 3.5773 | 5.3452 | 6.9896 | 12.2112 | 15.7885 | 0
4.8713 | 7.7554 | 1.9624 | 1.9436 | 2.8119 | 2.8871 | 6.7178 | 4.7743 | 12.6267 | 14.5703 | 21.2881 | 26.0624 | 4.8713 | 7.7554 | 1.9724 | 1.9436 | 2.8119 | 2.8871 | 6.7178 | 4.7743 | 12.6267 | 14.5703 | 21.2881 | 26.0624 | 0
7.0446 | 8.2263 | 2.0348 | 2.0522 | 3.1741 | 3.1045 | 7.2612 | 5.2089 | 15.2709 | 17.3232 | 24.5843 | 29.7933 | 7.0446 | 8.2263 | 2.0448 | 2.0522 | 3.1741 | 3.1045 | 7.2612 | 5.2089 | 15.2709 | 17.3232 | 24.5843 | 29.7933 | 0
20.3696 | 11.1134 | 2.479 | 2.7185 | 5.3949 | 4.437 | 10.5924 | 7.8739 | 31.483 | 34.2015 | 44.7939 | 52.6678 | 20.3696 | 11.1134 | 2.489 | 2.7185 | 5.3949 | 4.437 | 10.5924 | 7.8739 | 31.483 | 34.2015 | 44.7939 | 52.6678 | 0
2.9926 | 7.3484 | 1.8998 | 1.8496 | 2.4988 | 2.6993 | 6.2482 | 4.3985 | 10.341 | 12.1907 | 18.4388 | 22.8374 | 2.9926 | 7.3484 | 1.9098 | 1.8496 | 2.4988 | 2.6993 | 6.2482 | 4.3985 | 10.341 | 12.1907 | 18.4388 | 22.8374 | 0
3.3625 | 7.4285 | 1.9121 | 1.8681 | 2.5604 | 2.7362 | 6.3406 | 4.4725 | 10.791 | 12.6591 | 18.9998 | 23.4723 | 3.3625 | 7.4285 | 1.9221 | 1.8681 | 2.5604 | 2.7362 | 6.3406 | 4.4725 | 10.791 | 12.6591 | 18.9998 | 23.4723 | 0
2.8398 | 7.3153 | 1.8947 | 1.842 | 2.4733 | 2.684 | 6.21 | 4.368 | 10.1551 | 11.9971 | 18.207 | 22.575 | 2.8398 | 7.3153 | 1.9047 | 1.842 | 2.4733 | 2.684 | 6.21 | 4.368 | 10.1551 | 11.9971 | 18.207 | 22.575 | 0
8.605 | 8.5644 | 2.0868 | 2.1302 | 3.4342 | 3.2605 | 7.6512 | 5.521 | 17.1694 | 19.2996 | 26.9509 | 32.4719 | 8.605 | 8.5644 | 2.0968 | 2.1302 | 3.4342 | 3.2605 | 7.6512 | 5.521 | 17.1694 | 19.2996 | 26.9509 | 32.4719 | 0
8.192 | 8.4749 | 2.0731 | 2.1096 | 3.3653 | 3.2192 | 7.548 | 5.4384 | 16.6669 | 18.7765 | 26.3245 | 31.7629 | 8.192 | 8.4749 | 2.0831 | 2.1096 | 3.3653 | 3.2192 | 7.548 | 5.4384 | 16.6669 | 18.7765 | 26.3245 | 31.7629 | 0
8.0575 | 8.4458 | 2.0686 | 2.1029 | 3.3429 | 3.2057 | 7.5144 | 5.4115 | 16.5033 | 18.6062 | 26.1205 | 31.532 | 8.0575 | 8.4458 | 2.0786 | 2.1029 | 3.3429 | 3.2057 | 7.5144 | 5.4115 | 16.5033 | 18.6062 | 26.1205 | 31.532 | 0
5.6798 | 7.9306 | 1.9893 | 1.984 | 2.9466 | 2.968 | 6.92 | 4.936 | 13.6104 | 15.5944 | 22.5144 | 27.4503 | 5.6798 | 7.9306 | 1.9993 | 1.984 | 2.9466 | 2.968 | 6.92 | 4.936 | 13.6104 | 15.5944 | 22.5144 | 27.4503 | 0
12.1633 | 9.3354 | 2.2054 | 2.3082 | 4.0272 | 3.6163 | 8.5408 | 6.2327 | 21.4987 | 23.8069 | 32.3477 | 38.5804 | 12.1633 | 9.3354 | 2.2154 | 2.3082 | 4.0272 | 3.6163 | 8.5408 | 6.2327 | 21.4987 | 23.8069 | 32.3477 | 38.5804 | 0
8.89 | 8.6262 | 2.0963 | 2.1445 | 3.4817 | 3.289 | 7.7225 | 5.578 | 17.5161 | 19.6606 | 27.3831 | 32.9611 | 8.89 | 8.6262 | 2.1063 | 2.1445 | 3.4817 | 3.289 | 7.7225 | 5.578 | 17.5161 | 19.6606 | 27.3831 | 32.9611 | 0
4.5152 | 7.6783 | 1.9505 | 1.9258 | 2.7525 | 2.8515 | 6.6288 | 4.703 | 12.1935 | 14.1192 | 20.748 | 25.451 | 4.5152 | 7.6783 | 1.9605 | 1.9258 | 2.7525 | 2.8515 | 6.6288 | 4.703 | 12.1935 | 14.1192 | 20.748 | 25.451 | 0
17.5746 | 10.5078 | 2.3858 | 2.5787 | 4.9291 | 4.1575 | 9.8937 | 7.3149 | 28.0824 | 30.6612 | 40.5548 | 47.8697 | 17.5746 | 10.5078 | 2.3958 | 2.5787 | 4.9291 | 4.1575 | 9.8937 | 7.3149 | 28.0824 | 30.6612 | 40.5548 | 47.8697 | 0
7.2511 | 8.2711 | 2.0417 | 2.0626 | 3.2085 | 3.1251 | 7.3128 | 5.2502 | 15.5222 | 17.5848 | 24.8976 | 30.1478 | 7.2511 | 8.2711 | 2.0517 | 2.0626 | 3.2085 | 3.1251 | 7.3128 | 5.2502 | 15.5222 | 17.5848 | 24.8976 | 30.1478 | 0
7.1645 | 8.2523 | 2.0388 | 2.0582 | 3.1941 | 3.1164 | 7.2911 | 5.2329 | 15.4168 | 17.475 | 24.7661 | 29.999 | 7.1645 | 8.2523 | 2.0488 | 2.0582 | 3.1941 | 3.1164 | 7.2911 | 5.2329 | 15.4168 | 17.475 | 24.7661 | 29.999 | 0
8.9096 | 8.6304 | 2.097 | 2.1455 | 3.4849 | 3.291 | 7.7274 | 5.5819 | 17.54 | 19.6855 | 27.4129 | 32.9948 | 8.9096 | 8.6304 | 2.107 | 2.1455 | 3.4849 | 3.291 | 7.7274 | 5.5819 | 17.54 | 19.6855 | 27.4129 | 32.9948 | 0
13.8753 | 9.7063 | 2.2625 | 2.3938 | 4.3126 | 3.7875 | 8.9688 | 6.5751 | 23.5816 | 25.9754 | 34.9442 | 41.5193 | 13.8753 | 9.7063 | 2.2725 | 2.3938 | 4.3126 | 3.7875 | 8.9688 | 6.5751 | 23.5816 | 25.9754 | 34.9442 | 41.5193 | 0
14.9444 | 9.938 | 2.2981 | 2.4472 | 4.4907 | 3.8944 | 9.2361 | 6.7889 | 24.8824 | 27.3296 | 36.5657 | 43.3546 | 14.9444 | 9.938 | 2.3081 | 2.4472 | 4.4907 | 3.8944 | 9.2361 | 6.7889 | 24.8824 | 27.3296 | 36.5657 | 43.3546 | 0
12.6497 | 9.4408 | 2.2217 | 2.3325 | 4.1083 | 3.665 | 8.6624 | 6.3299 | 22.0904 | 24.4229 | 33.0853 | 39.4153 | 12.6497 | 9.4408 | 2.2317 | 2.3325 | 4.1083 | 3.665 | 8.6624 | 6.3299 | 22.0904 | 24.4229 | 33.0853 | 39.4153 | 0
-5.3839 | 5.5335 | 1.6205 | 1.4308 | 1.1027 | 1.8616 | 4.154 | 2.7232 | 0.14953 | 1.5803 | 5.7343 | 8.4576 | -5.3839 | 5.5335 | 1.6305 | 1.4308 | 1.1027 | 1.8616 | 4.154 | 2.7232 | 0.14953 | 1.5803 | 5.7343 | 8.4576 | 0
7.415 | 8.3066 | 2.0472 | 2.0707 | 3.2358 | 3.1415 | 7.3537 | 5.283 | 15.7215 | 17.7923 | 25.146 | 30.429 | 7.415 | 8.3066 | 2.0572 | 2.0707 | 3.2358 | 3.1415 | 7.3537 | 5.283 | 15.7215 | 17.7923 | 25.146 | 30.429 | 0
0.75401 | 6.8634 | 1.8251 | 1.7377 | 2.1257 | 2.4754 | 5.6885 | 3.9508 | 7.6174 | 9.3551 | 15.0436 | 18.9944 | 0.75401 | 6.8634 | 1.8351 | 1.7377 | 2.1257 | 2.4754 | 5.6885 | 3.9508 | 7.6174 | 9.3551 | 15.0436 | 18.9944 | 0
7.6785 | 8.3637 | 2.0559 | 2.0839 | 3.2797 | 3.1678 | 7.4196 | 5.3357 | 16.0421 | 18.1261 | 25.5457 | 30.8814 | 7.6785 | 8.3637 | 2.0659 | 2.0839 | 3.2797 | 3.1678 | 7.4196 | 5.3357 | 16.0421 | 18.1261 | 25.5457 | 30.8814 | 0
-6.7356 | 5.2406 | 1.5755 | 1.3632 | 0.8774 | 1.7264 | 3.8161 | 2.4529 | -1.495 | -0.13174 | 3.6844 | 6.1373 | -6.7356 | 5.2406 | 1.5855 | 1.3632 | 0.8774 | 1.7264 | 3.8161 | 2.4529 | -1.495 | -0.13174 | 3.6844 | 6.1373 | 0
15.0729 | 9.9658 | 2.3024 | 2.4536 | 4.5121 | 3.9073 | 9.2682 | 6.8146 | 25.0387 | 27.4923 | 36.7606 | 43.5751 | 15.0729 | 9.9658 | 2.3124 | 2.4536 | 4.5121 | 3.9073 | 9.2682 | 6.8146 | 25.0387 | 27.4923 | 36.7606 | 43.5751 | 0
4.1628 | 7.6019 | 1.9388 | 1.9081 | 2.6938 | 2.8163 | 6.5407 | 4.6326 | 11.7648 | 13.6729 | 20.2136 | 24.8462 | 4.1628 | 7.6019 | 1.9488 | 1.9081 | 2.6938 | 2.8163 | 6.5407 | 4.6326 | 11.7648 | 13.6729 | 20.2136 | 24.8462 | 0
-1.8279 | 6.304 | 1.7391 | 1.6086 | 1.6954 | 2.2172 | 5.043 | 3.4344 | 4.4761 | 6.0847 | 11.1277 | 14.5622 | -1.8279 | 6.304 | 1.7491 | 1.6086 | 1.6954 | 2.2172 | 5.043 | 3.4344 | 4.4761 | 6.0847 | 11.1277 | 14.5622 | 0
7.3349 | 8.2892 | 2.0445 | 2.0667 | 3.2225 | 3.1335 | 7.3337 | 5.267 | 15.6242 | 17.6909 | 25.0246 | 30.2916 | 7.3349 | 8.2892 | 2.0545 | 2.0667 | 3.2225 | 3.1335 | 7.3337 | 5.267 | 15.6242 | 17.6909 | 25.0246 | 30.2916 | 0
-2.9217 | 6.067 | 1.7026 | 1.5539 | 1.5131 | 2.1078 | 4.7696 | 3.2157 | 3.1453 | 4.6992 | 9.4688 | 12.6845 | -2.9217 | 6.067 | 1.7126 | 1.5539 | 1.5131 | 2.1078 | 4.7696 | 3.2157 | 3.1453 | 4.6992 | 9.4688 | 12.6845 | 0
6.4196 | 8.0909 | 2.014 | 2.021 | 3.0699 | 3.042 | 7.1049 | 5.0839 | 14.5106 | 16.5315 | 23.6364 | 28.7204 | 6.4196 | 8.0909 | 2.024 | 2.021 | 3.0699 | 3.042 | 7.1049 | 5.0839 | 14.5106 | 16.5315 | 23.6364 | 28.7204 | 0
-3.1568 | 6.016 | 1.6948 | 1.5422 | 1.4739 | 2.0843 | 4.7108 | 3.1686 | 2.8592 | 4.4013 | 9.1121 | 12.2807 | -3.1568 | 6.016 | 1.7048 | 1.5422 | 1.4739 | 2.0843 | 4.7108 | 3.1686 | 2.8592 | 4.4013 | 9.1121 | 12.2807 | 0
-5.5235 | 5.5032 | 1.6159 | 1.4238 | 1.0794 | 1.8476 | 4.1191 | 2.6953 | -0.0203 | 1.4035 | 5.5226 | 8.2179 | -5.5235 | 5.5032 | 1.6259 | 1.4238 | 1.0794 | 1.8476 | 4.1191 | 2.6953 | -0.0203 | 1.4035 | 5.5226 | 8.2179 | 0
4.1099 | 7.5905 | 1.937 | 1.9055 | 2.685 | 2.811 | 6.5275 | 4.622 | 11.7004 | 13.6058 | 20.1333 | 24.7553 | 4.1099 | 7.5905 | 1.947 | 1.9055 | 2.685 | 2.811 | 6.5275 | 4.622 | 11.7004 | 13.6058 | 20.1333 | 24.7553 | 0
9.1846 | 8.69 | 2.1062 | 2.1592 | 3.5308 | 3.3185 | 7.7962 | 5.6369 | 17.8746 | 20.0339 | 27.83 | 33.4669 | 9.1846 | 8.69 | 2.1162 | 2.1592 | 3.5308 | 3.3185 | 7.7962 | 5.6369 | 17.8746 | 20.0339 | 27.83 | 33.4669 | 0
-3.3156 | 5.9816 | 1.6895 | 1.5342 | 1.4474 | 2.0684 | 4.6711 | 3.1369 | 2.666 | 4.2003 | 8.8714 | 12.0082 | -3.3156 | 5.9816 | 1.6995 | 1.5342 | 1.4474 | 2.0684 | 4.6711 | 3.1369 | 2.666 | 4.2003 | 8.8714 | 12.0082 | 0
10.6419 | 9.0057 | 2.1547 | 2.2321 | 3.7737 | 3.4642 | 8.1605 | 5.9284 | 19.6477 | 21.8798 | 30.0402 | 35.9686 | 10.6419 | 9.0057 | 2.1647 | 2.2321 | 3.7737 | 3.4642 | 8.1605 | 5.9284 | 19.6477 | 21.8798 | 30.0402 | 35.9686 | 0
9.4293 | 8.743 | 2.1143 | 2.1715 | 3.5716 | 3.3429 | 7.8573 | 5.6859 | 18.1724 | 20.3438 | 28.2012 | 33.8871 | 9.4293 | 8.743 | 2.1243 | 2.1715 | 3.5716 | 3.3429 | 7.8573 | 5.6859 | 18.1724 | 20.3438 | 28.2012 | 33.8871 | 0
24.2891 | 11.9626 | 2.6096 | 2.9145 | 6.0482 | 4.8289 | 11.5723 | 8.6578 | 36.2518 | 39.1662 | 50.7385 | 59.3964 | 24.2891 | 11.9626 | 2.6196 | 2.9145 | 6.0482 | 4.8289 | 11.5723 | 8.6578 | 36.2518 | 39.1662 | 50.7385 | 59.3964 | 0
8.2951 | 8.4973 | 2.0765 | 2.1148 | 3.3825 | 3.2295 | 7.5738 | 5.459 | 16.7923 | 18.9071 | 26.4808 | 31.9398 | 8.2951 | 8.4973 | 2.0865 | 2.1148 | 3.3825 | 3.2295 | 7.5738 | 5.459 | 16.7923 | 18.9071 | 26.4808 | 31.9398 | 0
-5.1847 | 5.5767 | 1.6272 | 1.4408 | 1.1359 | 1.8815 | 4.2038 | 2.7631 | 0.392 | 1.8328 | 6.0366 | 8.7997 | -5.1847 | 5.5767 | 1.6372 | 1.4408 | 1.1359 | 1.8815 | 4.2038 | 2.7631 | 0.392 | 1.8328 | 6.0366 | 8.7997 | 0
7.4308 | 8.31 | 2.0477 | 2.0715 | 3.2385 | 3.1431 | 7.3577 | 5.2862 | 15.7408 | 17.8123 | 25.17 | 30.4562 | 7.4308 | 8.31 | 2.0577 | 2.0715 | 3.2385 | 3.1431 | 7.3577 | 5.2862 | 15.7408 | 17.8123 | 25.17 | 30.4562 | 0
3.9805 | 7.5624 | 1.9327 | 1.899 | 2.6634 | 2.798 | 6.4951 | 4.5961 | 11.5429 | 13.4419 | 19.937 | 24.5331 | 3.9805 | 7.5624 | 1.9427 | 1.899 | 2.6634 | 2.798 | 6.4951 | 4.5961 | 11.5429 | 13.4419 | 19.937 | 24.5331 | 0
6.9627 | 8.2086 | 2.0321 | 2.0481 | 3.1605 | 3.0963 | 7.2407 | 5.1925 | 15.1713 | 17.2195 | 24.4602 | 29.6527 | 6.9627 | 8.2086 | 2.0421 | 2.0481 | 3.1605 | 3.0963 | 7.2407 | 5.1925 | 15.1713 | 17.2195 | 24.4602 | 29.6527 | 0
10.5847 | 8.9933 | 2.1528 | 2.2292 | 3.7641 | 3.4585 | 8.1462 | 5.9169 | 19.578 | 21.8073 | 29.9534 | 35.8704 | 10.5847 | 8.9933 | 2.1628 | 2.2292 | 3.7641 | 3.4585 | 8.1462 | 5.9169 | 19.578 | 21.8073 | 29.9534 | 35.8704 | 0
-1.1576 | 6.4492 | 1.7614 | 1.6421 | 1.8071 | 2.2842 | 5.2106 | 3.5685 | 5.2915 | 6.9337 | 12.1443 | 15.7127 | -1.1576 | 6.4492 | 1.7714 | 1.6421 | 1.8071 | 2.2842 | 5.2106 | 3.5685 | 5.2915 | 6.9337 | 12.1443 | 15.7127 | 0
-1.1256 | 6.4561 | 1.7625 | 1.6437 | 1.8124 | 2.2874 | 5.2186 | 3.5749 | 5.3305 | 6.9742 | 12.1928 | 15.7677 | -1.1256 | 6.4561 | 1.7725 | 1.6437 | 1.8124 | 2.2874 | 5.2186 | 3.5749 | 5.3305 | 6.9742 | 12.1928 | 15.7677 | 0
10.0004 | 8.8667 | 2.1333 | 2.2 | 3.6667 | 3.4 | 8.0001 | 5.8001 | 18.8671 | 21.0671 | 29.0672 | 34.8673 | 10.0004 | 8.8667 | 2.1433 | 2.2 | 3.6667 | 3.4 | 8.0001 | 5.8001 | 18.8671 | 21.0671 | 29.0672 | 34.8673 | 0
8.9462 | 8.6383 | 2.0982 | 2.1473 | 3.491 | 3.2946 | 7.7366 | 5.5892 | 17.5845 | 19.7319 | 27.4684 | 33.0576 | 8.9462 | 8.6383 | 2.1082 | 2.1473 | 3.491 | 3.2946 | 7.7366 | 5.5892 | 17.5845 | 19.7319 | 27.4684 | 33.0576 | 0
1.749 | 7.0789 | 1.8583 | 1.7874 | 2.2915 | 2.5749 | 5.9372 | 4.1498 | 8.8279 | 10.6153 | 16.5526 | 20.7024 | 1.749 | 7.0789 | 1.8683 | 1.7874 | 2.2915 | 2.5749 | 5.9372 | 4.1498 | 8.8279 | 10.6153 | 16.5526 | 20.7024 | 0
0.17321 | 6.7375 | 1.8058 | 1.7087 | 2.0289 | 2.4173 | 5.5433 | 3.8346 | 6.9107 | 8.6194 | 14.1627 | 17.9973 | 0.17321 | 6.7375 | 1.8158 | 1.7087 | 2.0289 | 2.4173 | 5.5433 | 3.8346 | 6.9107 | 8.6194 | 14.1627 | 17.9973 | 0
7.8213 | 8.3946 | 2.0607 | 2.0911 | 3.3035 | 3.1821 | 7.4553 | 5.3643 | 16.2159 | 18.3069 | 25.7622 | 31.1265 | 7.8213 | 8.3946 | 2.0707 | 2.0911 | 3.3035 | 3.1821 | 7.4553 | 5.3643 | 16.2159 | 18.3069 | 25.7622 | 31.1265 | 0
15.1106 | 9.974 | 2.3037 | 2.4555 | 4.5184 | 3.9111 | 9.2777 | 6.8221 | 25.0846 | 27.5401 | 36.8178 | 43.6399 | 15.1106 | 9.974 | 2.3137 | 2.4555 | 4.5184 | 3.9111 | 9.2777 | 6.8221 | 25.0846 | 27.5401 | 36.8178 | 43.6399 | 0
10.1426 | 8.8976 | 2.1381 | 2.2071 | 3.6904 | 3.4143 | 8.0357 | 5.8285 | 19.0402 | 21.2473 | 29.283 | 35.1115 | 10.1426 | 8.8976 | 2.1481 | 2.2071 | 3.6904 | 3.4143 | 8.0357 | 5.8285 | 19.0402 | 21.2473 | 29.283 | 35.1115 | 0
16.8847 | 10.3583 | 2.3628 | 2.5442 | 4.8141 | 4.0885 | 9.7212 | 7.1769 | 27.243 | 29.7873 | 39.5084 | 46.6854 | 16.8847 | 10.3583 | 2.3728 | 2.5442 | 4.8141 | 4.0885 | 9.7212 | 7.1769 | 27.243 | 29.7873 | 39.5084 | 46.6854 | 0
7.7903 | 8.3879 | 2.0597 | 2.0895 | 3.2984 | 3.179 | 7.4476 | 5.3581 | 16.1782 | 18.2677 | 25.7153 | 31.0734 | 7.7903 | 8.3879 | 2.0697 | 2.0895 | 3.2984 | 3.179 | 7.4476 | 5.3581 | 16.1782 | 18.2677 | 25.7153 | 31.0734 | 0
13.5503 | 9.6359 | 2.2517 | 2.3775 | 4.2584 | 3.755 | 8.8876 | 6.5101 | 23.1862 | 25.5637 | 34.4513 | 40.9613 | 13.5503 | 9.6359 | 2.2617 | 2.3775 | 4.2584 | 3.755 | 8.8876 | 6.5101 | 23.1862 | 25.5637 | 34.4513 | 40.9613 | 0
15.0013 | 9.9503 | 2.3 | 2.4501 | 4.5002 | 3.9001 | 9.2503 | 6.8003 | 24.9515 | 27.4016 | 36.6519 | 43.4522 | 15.0013 | 9.9503 | 2.31 | 2.4501 | 4.5002 | 3.9001 | 9.2503 | 6.8003 | 24.9515 | 27.4016 | 36.6519 | 43.4522 | 0
7.9384 | 8.42 | 2.0646 | 2.0969 | 3.3231 | 3.1938 | 7.4846 | 5.3877 | 16.3584 | 18.4553 | 25.9399 | 31.3276 | 7.9384 | 8.42 | 2.0746 | 2.0969 | 3.3231 | 3.1938 | 7.4846 | 5.3877 | 16.3584 | 18.4553 | 25.9399 | 31.3276 | 0
6.8871 | 8.1922 | 2.0296 | 2.0444 | 3.1479 | 3.0887 | 7.2218 | 5.1774 | 15.0793 | 17.1237 | 24.3455 | 29.5229 | 6.8871 | 8.1922 | 2.0396 | 2.0444 | 3.1479 | 3.0887 | 7.2218 | 5.1774 | 15.0793 | 17.1237 | 24.3455 | 29.5229 | 0
1.9661 | 7.126 | 1.8655 | 1.7983 | 2.3277 | 2.5966 | 5.9915 | 4.1932 | 9.0921 | 10.8904 | 16.8819 | 21.0751 | 1.9661 | 7.126 | 1.8755 | 1.7983 | 2.3277 | 2.5966 | 5.9915 | 4.1932 | 9.0921 | 10.8904 | 16.8819 | 21.0751 | 0
3.4524 | 7.448 | 1.9151 | 1.8726 | 2.5754 | 2.7452 | 6.3631 | 4.4905 | 10.9004 | 12.773 | 19.1361 | 23.6266 | 3.4524 | 7.448 | 1.9251 | 1.8726 | 2.5754 | 2.7452 | 6.3631 | 4.4905 | 10.9004 | 12.773 | 19.1361 | 23.6266 | 0
11.6679 | 9.228 | 2.1889 | 2.2834 | 3.9446 | 3.5668 | 8.417 | 6.1336 | 20.8959 | 23.1793 | 31.5963 | 37.7298 | 11.6679 | 9.228 | 2.1989 | 2.2834 | 3.9446 | 3.5668 | 8.417 | 6.1336 | 20.8959 | 23.1793 | 31.5963 | 37.7298 | 0
-0.70544 | 6.5472 | 1.7765 | 1.6647 | 1.8824 | 2.3295 | 5.3236 | 3.6589 | 5.8417 | 7.5064 | 12.8301 | 16.489 | -0.70544 | 6.5472 | 1.7865 | 1.6647 | 1.8824 | 2.3295 | 5.3236 | 3.6589 | 5.8417 | 7.5064 | 12.8301 | 16.489 | 0
4.6741 | 7.7127 | 1.9558 | 1.9337 | 2.779 | 2.8674 | 6.6685 | 4.7348 | 12.3868 | 14.3205 | 20.989 | 25.7238 | 4.6741 | 7.7127 | 1.9658 | 1.9337 | 2.779 | 2.8674 | 6.6685 | 4.7348 | 12.3868 | 14.3205 | 20.989 | 25.7238 | 0
10.26 | 8.923 | 2.142 | 2.213 | 3.71 | 3.426 | 8.065 | 5.852 | 19.183 | 21.396 | 29.461 | 35.313 | 10.26 | 8.923 | 2.152 | 2.213 | 3.71 | 3.426 | 8.065 | 5.852 | 19.183 | 21.396 | 29.461 | 35.313 | 0
7.416 | 8.3068 | 2.0472 | 2.0708 | 3.236 | 3.1416 | 7.354 | 5.2832 | 15.7228 | 17.7936 | 25.1476 | 30.4308 | 7.416 | 8.3068 | 2.0572 | 2.0708 | 3.236 | 3.1416 | 7.354 | 5.2832 | 15.7228 | 17.7936 | 25.1476 | 30.4308 | 0
2.6131 | 7.2662 | 1.8871 | 1.8307 | 2.4355 | 2.6613 | 6.1533 | 4.3226 | 9.8793 | 11.71 | 17.8633 | 22.1859 | 2.6131 | 7.2662 | 1.8971 | 1.8307 | 2.4355 | 2.6613 | 6.1533 | 4.3226 | 9.8793 | 11.71 | 17.8633 | 22.1859 | 0
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2044 | 14.1306 | 20.7616 | 25.4664 | 4.5241 | 7.6802 | 1.9608 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2044 | 14.1306 | 20.7616 | 25.4664 | 0
9.0177 | 8.6538 | 2.1006 | 2.1509 | 3.5029 | 3.3018 | 7.7544 | 5.6035 | 17.6715 | 19.8224 | 27.5768 | 33.1803 | 9.0177 | 8.6538 | 2.1106 | 2.1509 | 3.5029 | 3.3018 | 7.7544 | 5.6035 | 17.6715 | 19.8224 | 27.5768 | 33.1803 | 0
11.271 | 9.1421 | 2.1757 | 2.2636 | 3.8785 | 3.5271 | 8.3178 | 6.0542 | 20.4131 | 22.6766 | 30.9944 | 37.0486 | 11.271 | 9.1421 | 2.1857 | 2.2636 | 3.8785 | 3.5271 | 8.3178 | 6.0542 | 20.4131 | 22.6766 | 30.9944 | 37.0486 | 0
4.8689 | 7.7549 | 1.9623 | 1.9434 | 2.8115 | 2.8869 | 6.7172 | 4.7738 | 12.6238 | 14.5672 | 21.2844 | 26.0582 | 4.8689 | 7.7549 | 1.9723 | 1.9434 | 2.8115 | 2.8869 | 6.7172 | 4.7738 | 12.6238 | 14.5672 | 21.2844 | 26.0582 | 0
13.7381 | 9.6766 | 2.2579 | 2.3869 | 4.2897 | 3.7738 | 8.9345 | 6.5476 | 23.4147 | 25.8016 | 34.7361 | 41.2837 | 13.7381 | 9.6766 | 2.2679 | 2.3869 | 4.2897 | 3.7738 | 8.9345 | 6.5476 | 23.4147 | 25.8016 | 34.7361 | 41.2837 | 0
-0.14801 | 6.6679 | 1.7951 | 1.6926 | 1.9753 | 2.3852 | 5.463 | 3.7704 | 6.5199 | 8.2125 | 13.6755 | 17.4459 | -0.14801 | 6.6679 | 1.8051 | 1.6926 | 1.9753 | 2.3852 | 5.463 | 3.7704 | 6.5199 | 8.2125 | 13.6755 | 17.4459 | 0
4.9965 | 7.7826 | 1.9666 | 1.9498 | 2.8328 | 2.8997 | 6.7491 | 4.7993 | 12.7791 | 14.7289 | 21.478 | 26.2773 | 4.9965 | 7.7826 | 1.9766 | 1.9498 | 2.8328 | 2.8997 | 6.7491 | 4.7993 | 12.7791 | 14.7289 | 21.478 | 26.2773 | 0
2.9362 | 7.3362 | 1.8979 | 1.8468 | 2.4894 | 2.6936 | 6.234 | 4.3872 | 10.2723 | 12.1191 | 18.3532 | 22.7404 | 2.9362 | 7.3362 | 1.9079 | 1.8468 | 2.4894 | 2.6936 | 6.234 | 4.3872 | 10.2723 | 12.1191 | 18.3532 | 22.7404 | 0
10.8682 | 9.0548 | 2.1623 | 2.2434 | 3.8114 | 3.4868 | 8.2171 | 5.9736 | 19.923 | 22.1664 | 30.3835 | 36.3571 | 10.8682 | 9.0548 | 2.1723 | 2.2434 | 3.8114 | 3.4868 | 8.2171 | 5.9736 | 19.923 | 22.1664 | 30.3835 | 36.3571 | 0
5.3766 | 7.8649 | 1.9792 | 1.9688 | 2.8961 | 2.9377 | 6.8441 | 4.8753 | 13.2415 | 15.2103 | 22.0545 | 26.9298 | 5.3766 | 7.8649 | 1.9892 | 1.9688 | 2.8961 | 2.9377 | 6.8441 | 4.8753 | 13.2415 | 15.2103 | 22.0545 | 26.9298 | 0
-3.2425 | 5.9975 | 1.6919 | 1.5379 | 1.4596 | 2.0758 | 4.6894 | 3.1515 | 2.755 | 4.2928 | 8.9822 | 12.1337 | -3.2425 | 5.9975 | 1.7019 | 1.5379 | 1.4596 | 2.0758 | 4.6894 | 3.1515 | 2.755 | 4.2928 | 8.9822 | 12.1337 | 0
5.784 | 7.9532 | 1.9928 | 1.9892 | 2.964 | 2.9784 | 6.946 | 4.9568 | 13.7372 | 15.7264 | 22.6724 | 27.6292 | 5.784 | 7.9532 | 2.0028 | 1.9892 | 2.964 | 2.9784 | 6.946 | 4.9568 | 13.7372 | 15.7264 | 22.6724 | 27.6292 | 0
0.62392 | 6.8352 | 1.8208 | 1.7312 | 2.104 | 2.4624 | 5.656 | 3.9248 | 7.4591 | 9.1903 | 14.8463 | 18.7711 | 0.62392 | 6.8352 | 1.8308 | 1.7312 | 2.104 | 2.4624 | 5.656 | 3.9248 | 7.4591 | 9.1903 | 14.8463 | 18.7711 | 0
3.8817 | 7.541 | 1.9294 | 1.8941 | 2.6469 | 2.7882 | 6.4704 | 4.5763 | 11.4227 | 13.3168 | 19.7872 | 24.3636 | 3.8817 | 7.541 | 1.9394 | 1.8941 | 2.6469 | 2.7882 | 6.4704 | 4.5763 | 11.4227 | 13.3168 | 19.7872 | 24.3636 | 0
6.7592 | 8.1645 | 2.0253 | 2.038 | 3.1265 | 3.0759 | 7.1898 | 5.1518 | 14.9237 | 16.9617 | 24.1515 | 29.3033 | 6.7592 | 8.1645 | 2.0353 | 2.038 | 3.1265 | 3.0759 | 7.1898 | 5.1518 | 14.9237 | 16.9617 | 24.1515 | 29.3033 | 0
8.4274 | 8.5259 | 2.0809 | 2.1214 | 3.4046 | 3.2427 | 7.6069 | 5.4855 | 16.9534 | 19.0748 | 26.6816 | 32.1671 | 8.4274 | 8.5259 | 2.0909 | 2.1214 | 3.4046 | 3.2427 | 7.6069 | 5.4855 | 16.9534 | 19.0748 | 26.6816 | 32.1671 | 0
16.2512 | 10.2211 | 2.3417 | 2.5126 | 4.7085 | 4.0251 | 9.5628 | 7.0502 | 26.4722 | 28.9848 | 38.5476 | 45.5978 | 16.2512 | 10.2211 | 2.3517 | 2.5126 | 4.7085 | 4.0251 | 9.5628 | 7.0502 | 26.4722 | 28.9848 | 38.5476 | 45.5978 | 0
3.9702 | 7.5602 | 1.9323 | 1.8985 | 2.6617 | 2.797 | 6.4925 | 4.594 | 11.5304 | 13.4289 | 19.9214 | 24.5155 | 3.9702 | 7.5602 | 1.9423 | 1.8985 | 2.6617 | 2.797 | 6.4925 | 4.594 | 11.5304 | 13.4289 | 19.9214 | 24.5155 | 0
9.1031 | 8.6723 | 2.1034 | 2.1552 | 3.5172 | 3.3103 | 7.7758 | 5.6206 | 17.7754 | 19.9305 | 27.7063 | 33.3269 | 9.1031 | 8.6723 | 2.1134 | 2.1552 | 3.5172 | 3.3103 | 7.7758 | 5.6206 | 17.7754 | 19.9305 | 27.7063 | 33.3269 | 0
7.6437 | 8.3561 | 2.0548 | 2.0822 | 3.2739 | 3.1644 | 7.4109 | 5.3287 | 15.9998 | 18.082 | 25.4929 | 30.8217 | 7.6437 | 8.3561 | 2.0648 | 2.0822 | 3.2739 | 3.1644 | 7.4109 | 5.3287 | 15.9998 | 18.082 | 25.4929 | 30.8217 | 0
7.4801 | 8.3207 | 2.0493 | 2.074 | 3.2467 | 3.148 | 7.37 | 5.296 | 15.8008 | 17.8748 | 25.2449 | 30.5409 | 7.4801 | 8.3207 | 2.0593 | 2.074 | 3.2467 | 3.148 | 7.37 | 5.296 | 15.8008 | 17.8748 | 25.2449 | 30.5409 | 0
15.1289 | 9.9779 | 2.3043 | 2.4564 | 4.5215 | 3.9129 | 9.2822 | 6.8258 | 25.1068 | 27.5633 | 36.8455 | 43.6713 | 15.1289 | 9.9779 | 2.3143 | 2.4564 | 4.5215 | 3.9129 | 9.2822 | 6.8258 | 25.1068 | 27.5633 | 36.8455 | 43.6713 | 0
0.75091 | 6.8627 | 1.825 | 1.7375 | 2.1252 | 2.4751 | 5.6877 | 3.9502 | 7.6136 | 9.3512 | 15.0389 | 18.9891 | 0.75091 | 6.8627 | 1.835 | 1.7375 | 2.1252 | 2.4751 | 5.6877 | 3.9502 | 7.6136 | 9.3512 | 15.0389 | 18.9891 | 0
1.9654 | 7.1258 | 1.8655 | 1.7983 | 2.3276 | 2.5965 | 5.9914 | 4.1931 | 9.0912 | 10.8895 | 16.8809 | 21.0739 | 1.9654 | 7.1258 | 1.8755 | 1.7983 | 2.3276 | 2.5965 | 5.9914 | 4.1931 | 9.0912 | 10.8895 | 16.8809 | 21.0739 | 0
9.8869 | 8.8422 | 2.1296 | 2.1943 | 3.6478 | 3.3887 | 7.9717 | 5.7774 | 18.7291 | 20.9234 | 28.8951 | 34.6725 | 9.8869 | 8.8422 | 2.1396 | 2.1943 | 3.6478 | 3.3887 | 7.9717 | 5.7774 | 18.7291 | 20.9234 | 28.8951 | 34.6725 | 0
6.4668 | 8.1011 | 2.0156 | 2.0233 | 3.0778 | 3.0467 | 7.1167 | 5.0934 | 14.5679 | 16.5913 | 23.708 | 28.8013 | 6.4668 | 8.1011 | 2.0256 | 2.0233 | 3.0778 | 3.0467 | 7.1167 | 5.0934 | 14.5679 | 16.5913 | 23.708 | 28.8013 | 0
7.8432 | 8.3994 | 2.0614 | 2.0922 | 3.3072 | 3.1843 | 7.4608 | 5.3686 | 16.2426 | 18.3348 | 25.7956 | 31.1642 | 7.8432 | 8.3994 | 2.0714 | 2.0922 | 3.3072 | 3.1843 | 7.4608 | 5.3686 | 16.2426 | 18.3348 | 25.7956 | 31.1642 | 0
3.9091 | 7.547 | 1.9303 | 1.8955 | 2.6515 | 2.7909 | 6.4773 | 4.5818 | 11.456 | 13.3515 | 19.8288 | 24.4106 | 3.9091 | 7.547 | 1.9403 | 1.8955 | 2.6515 | 2.7909 | 6.4773 | 4.5818 | 11.456 | 13.3515 | 19.8288 | 24.4106 | 0
3.4369 | 7.4447 | 1.9146 | 1.8718 | 2.5728 | 2.7437 | 6.3592 | 4.4874 | 10.8815 | 12.7533 | 19.1126 | 23.5999 | 3.4369 | 7.4447 | 1.9246 | 1.8718 | 2.5728 | 2.7437 | 6.3592 | 4.4874 | 10.8815 | 12.7533 | 19.1126 | 23.5999 | 0
16.7592 | 10.3312 | 2.3586 | 2.538 | 4.7932 | 4.0759 | 9.6898 | 7.1518 | 27.0903 | 29.6283 | 39.3181 | 46.4699 | 16.7592 | 10.3312 | 2.3686 | 2.538 | 4.7932 | 4.0759 | 9.6898 | 7.1518 | 27.0903 | 29.6283 | 39.3181 | 46.4699 | 0
-4.8476 | 5.6497 | 1.6384 | 1.4576 | 1.1921 | 1.9152 | 4.2881 | 2.8305 | 0.80204 | 2.2597 | 6.5478 | 9.3782 | -4.8476 | 5.6497 | 1.6484 | 1.4576 | 1.1921 | 1.9152 | 4.2881 | 2.8305 | 0.80204 | 2.2597 | 6.5478 | 9.3782 | 0
4.8571 | 7.7524 | 1.9619 | 1.9429 | 2.8095 | 2.8857 | 6.7143 | 4.7714 | 12.6094 | 14.5523 | 21.2665 | 26.038 | 4.8571 | 7.7524 | 1.9719 | 1.9429 | 2.8095 | 2.8857 | 6.7143 | 4.7714 | 12.6094 | 14.5523 | 21.2665 | 26.038 | 0
15.5217 | 10.063 | 2.3174 | 2.4761 | 4.587 | 3.9522 | 9.3804 | 6.9043 | 25.5847 | 28.0608 | 37.4412 | 44.3456 | 15.5217 | 10.063 | 2.3274 | 2.4761 | 4.587 | 3.9522 | 9.3804 | 6.9043 | 25.5847 | 28.0608 | 37.4412 | 44.3456 | 0
4.5272 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7054 | 12.2081 | 14.1344 | 20.7662 | 25.4717 | 4.5272 | 7.6809 | 1.9609 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7054 | 12.2081 | 14.1344 | 20.7662 | 25.4717 | 0
-6.9383 | 5.1967 | 1.5687 | 1.3531 | 0.84362 | 1.7062 | 3.7654 | 2.4123 | -1.7415 | -0.38845 | 3.377 | 5.7893 | -6.9383 | 5.1967 | 1.5787 | 1.3531 | 0.84362 | 1.7062 | 3.7654 | 2.4123 | -1.7415 | -0.38845 | 3.377 | 5.7893 | 0
16.9328 | 10.3688 | 2.3644 | 2.5466 | 4.8221 | 4.0933 | 9.7332 | 7.1866 | 27.3016 | 29.8482 | 39.5814 | 46.768 | 16.9328 | 10.3688 | 2.3744 | 2.5466 | 4.8221 | 4.0933 | 9.7332 | 7.1866 | 27.3016 | 29.8482 | 39.5814 | 46.768 | 0
14.0968 | 9.7543 | 2.2699 | 2.4048 | 4.3495 | 3.8097 | 9.0242 | 6.6194 | 23.8511 | 26.2559 | 35.2801 | 41.8995 | 14.0968 | 9.7543 | 2.2799 | 2.4048 | 4.3495 | 3.8097 | 9.0242 | 6.6194 | 23.8511 | 26.2559 | 35.2801 | 41.8995 | 0
21.6875 | 11.399 | 2.5229 | 2.7844 | 5.6146 | 4.5687 | 10.9219 | 8.1375 | 33.0864 | 35.8708 | 46.7927 | 54.9302 | 21.6875 | 11.399 | 2.5329 | 2.7844 | 5.6146 | 4.5687 | 10.9219 | 8.1375 | 33.0864 | 35.8708 | 46.7927 | 54.9302 | 0
14.6441 | 9.8729 | 2.2881 | 2.4322 | 4.4407 | 3.8644 | 9.161 | 6.7288 | 24.5169 | 26.9491 | 36.1102 | 42.839 | 14.6441 | 9.8729 | 2.2981 | 2.4322 | 4.4407 | 3.8644 | 9.161 | 6.7288 | 24.5169 | 26.9491 | 36.1102 | 42.839 | 0
0.7403 | 6.8604 | 1.8247 | 1.737 | 2.1234 | 2.474 | 5.6851 | 3.9481 | 7.6007 | 9.3377 | 15.0228 | 18.9709 | 0.7403 | 6.8604 | 1.8347 | 1.737 | 2.1234 | 2.474 | 5.6851 | 3.9481 | 7.6007 | 9.3377 | 15.0228 | 18.9709 | 0
0.19334 | 6.7419 | 1.8064 | 1.7097 | 2.0322 | 2.4193 | 5.5483 | 3.8387 | 6.9352 | 8.6449 | 14.1932 | 18.0319 | 0.19334 | 6.7419 | 1.8164 | 1.7097 | 2.0322 | 2.4193 | 5.5483 | 3.8387 | 6.9352 | 8.6449 | 14.1932 | 18.0319 | 0
8.7563 | 8.5972 | 2.0919 | 2.1378 | 3.4594 | 3.2756 | 7.6891 | 5.5513 | 17.3534 | 19.4913 | 27.1803 | 32.7316 | 8.7563 | 8.5972 | 2.1019 | 2.1378 | 3.4594 | 3.2756 | 7.6891 | 5.5513 | 17.3534 | 19.4913 | 27.1803 | 32.7316 | 0
8.0989 | 8.4548 | 2.07 | 2.1049 | 3.3498 | 3.2099 | 7.5247 | 5.4198 | 16.5537 | 18.6586 | 26.1833 | 31.6031 | 8.0989 | 8.4548 | 2.08 | 2.1049 | 3.3498 | 3.2099 | 7.5247 | 5.4198 | 16.5537 | 18.6586 | 26.1833 | 31.6031 | 0
-3.4729 | 5.9475 | 1.6842 | 1.5264 | 1.4212 | 2.0527 | 4.6318 | 3.1054 | 2.4746 | 4.0009 | 8.6327 | 11.7381 | -3.4729 | 5.9475 | 1.6942 | 1.5264 | 1.4212 | 2.0527 | 4.6318 | 3.1054 | 2.4746 | 4.0009 | 8.6327 | 11.7381 | 0
0.19703 | 6.7427 | 1.8066 | 1.7099 | 2.0328 | 2.4197 | 5.5493 | 3.8394 | 6.9397 | 8.6496 | 14.1988 | 18.0382 | 0.19703 | 6.7427 | 1.8166 | 1.7099 | 2.0328 | 2.4197 | 5.5493 | 3.8394 | 6.9397 | 8.6496 | 14.1988 | 18.0382 | 0
2.1437 | 7.1645 | 1.8715 | 1.8072 | 2.3573 | 2.6144 | 6.0359 | 4.2287 | 9.3082 | 11.1154 | 17.1513 | 21.38 | 2.1437 | 7.1645 | 1.8815 | 1.8072 | 2.3573 | 2.6144 | 6.0359 | 4.2287 | 9.3082 | 11.1154 | 17.1513 | 21.38 | 0
2.1804 | 7.1724 | 1.8727 | 1.809 | 2.3634 | 2.618 | 6.0451 | 4.2361 | 9.3528 | 11.1618 | 17.2069 | 21.443 | 2.1804 | 7.1724 | 1.8827 | 1.809 | 2.3634 | 2.618 | 6.0451 | 4.2361 | 9.3528 | 11.1618 | 17.2069 | 21.443 | 0
8.4919 | 8.5399 | 2.0831 | 2.1246 | 3.4153 | 3.2492 | 7.623 | 5.4984 | 17.0318 | 19.1564 | 26.7793 | 32.2777 | 8.4919 | 8.5399 | 2.0931 | 2.1246 | 3.4153 | 3.2492 | 7.623 | 5.4984 | 17.0318 | 19.1564 | 26.7793 | 32.2777 | 0
-0.30742 | 6.6334 | 1.7898 | 1.6846 | 1.9488 | 2.3693 | 5.4231 | 3.7385 | 6.326 | 8.0106 | 13.4337 | 17.1723 | -0.30742 | 6.6334 | 1.7998 | 1.6846 | 1.9488 | 2.3693 | 5.4231 | 3.7385 | 6.326 | 8.0106 | 13.4337 | 17.1723 | 0
5.7009 | 7.9352 | 1.99 | 1.985 | 2.9501 | 2.9701 | 6.9252 | 4.9402 | 13.6361 | 15.6211 | 22.5463 | 27.4865 | 5.7009 | 7.9352 | 2 | 1.985 | 2.9501 | 2.9701 | 6.9252 | 4.9402 | 13.6361 | 15.6211 | 22.5463 | 27.4865 | 0
3.9954 | 7.5657 | 1.9332 | 1.8998 | 2.6659 | 2.7995 | 6.4988 | 4.5991 | 11.561 | 13.4608 | 19.9596 | 24.5587 | 3.9954 | 7.5657 | 1.9432 | 1.8998 | 2.6659 | 2.7995 | 6.4988 | 4.5991 | 11.561 | 13.4608 | 19.9596 | 24.5587 | 0
2.8736 | 7.3226 | 1.8958 | 1.8437 | 2.4789 | 2.6874 | 6.2184 | 4.3747 | 10.1962 | 12.0399 | 18.2583 | 22.633 | 2.8736 | 7.3226 | 1.9058 | 1.8437 | 2.4789 | 2.6874 | 6.2184 | 4.3747 | 10.1962 | 12.0399 | 18.2583 | 22.633 | 0
7.4078 | 8.305 | 2.0469 | 2.0704 | 3.2346 | 3.1408 | 7.352 | 5.2816 | 15.7128 | 17.7832 | 25.1352 | 30.4167 | 7.4078 | 8.305 | 2.0569 | 2.0704 | 3.2346 | 3.1408 | 7.352 | 5.2816 | 15.7128 | 17.7832 | 25.1352 | 30.4167 | 0
4.6413 | 7.7056 | 1.9547 | 1.9321 | 2.7735 | 2.8641 | 6.6603 | 4.7283 | 12.3469 | 14.2789 | 20.9392 | 25.6675 | 4.6413 | 7.7056 | 1.9647 | 1.9321 | 2.7735 | 2.8641 | 6.6603 | 4.7283 | 12.3469 | 14.2789 | 20.9392 | 25.6675 | 0
17.8399 | 10.5653 | 2.3947 | 2.592 | 4.9733 | 4.184 | 9.96 | 7.368 | 28.4052 | 30.9972 | 40.9571 | 48.3251 | 17.8399 | 10.5653 | 2.4047 | 2.592 | 4.9733 | 4.184 | 9.96 | 7.368 | 28.4052 | 30.9972 | 40.9571 | 48.3251 | 0
10.3126 | 8.9344 | 2.1438 | 2.2156 | 3.7188 | 3.4313 | 8.0782 | 5.8625 | 19.2471 | 21.4627 | 29.5409 | 35.4034 | 10.3126 | 8.9344 | 2.1538 | 2.2156 | 3.7188 | 3.4313 | 8.0782 | 5.8625 | 19.2471 | 21.4627 | 29.5409 | 35.4034 | 0
0.93636 | 6.9029 | 1.8312 | 1.7468 | 2.1561 | 2.4936 | 5.7341 | 3.9873 | 7.8392 | 9.5861 | 15.3201 | 19.3074 | 0.93636 | 6.9029 | 1.8412 | 1.7468 | 2.1561 | 2.4936 | 5.7341 | 3.9873 | 7.8392 | 9.5861 | 15.3201 | 19.3074 | 0
5.9171 | 7.982 | 1.9972 | 1.9959 | 2.9862 | 2.9917 | 6.9793 | 4.9834 | 13.8992 | 15.8951 | 22.8743 | 27.8578 | 5.9171 | 7.982 | 2.0072 | 1.9959 | 2.9862 | 2.9917 | 6.9793 | 4.9834 | 13.8992 | 15.8951 | 22.8743 | 27.8578 | 0
14.2609 | 9.7899 | 2.2754 | 2.413 | 4.3768 | 3.8261 | 9.0652 | 6.6522 | 24.0507 | 26.4638 | 35.529 | 42.1812 | 14.2609 | 9.7899 | 2.2854 | 2.413 | 4.3768 | 3.8261 | 9.0652 | 6.6522 | 24.0507 | 26.4638 | 35.529 | 42.1812 | 0
4.7586 | 7.731 | 1.9586 | 1.9379 | 2.7931 | 2.8759 | 6.6897 | 4.7517 | 12.4897 | 14.4276 | 21.1173 | 25.869 | 4.7586 | 7.731 | 1.9686 | 1.9379 | 2.7931 | 2.8759 | 6.6897 | 4.7517 | 12.4897 | 14.4276 | 21.1173 | 25.869 | 0
-1.5358 | 6.3672 | 1.7488 | 1.6232 | 1.744 | 2.2464 | 5.116 | 3.4928 | 4.8314 | 6.4546 | 11.5707 | 15.0635 | -1.5358 | 6.3672 | 1.7588 | 1.6232 | 1.744 | 2.2464 | 5.116 | 3.4928 | 4.8314 | 6.4546 | 11.5707 | 15.0635 | 0
4.5187 | 7.6791 | 1.9506 | 1.9259 | 2.7531 | 2.8519 | 6.6297 | 4.7037 | 12.1977 | 14.1237 | 20.7534 | 25.4571 | 4.5187 | 7.6791 | 1.9606 | 1.9259 | 2.7531 | 2.8519 | 6.6297 | 4.7037 | 12.1977 | 14.1237 | 20.7534 | 25.4571 | 0
10.9318 | 9.0686 | 2.1644 | 2.2466 | 3.822 | 3.4932 | 8.233 | 5.9864 | 20.0004 | 22.247 | 30.4799 | 36.4663 | 10.9318 | 9.0686 | 2.1744 | 2.2466 | 3.822 | 3.4932 | 8.233 | 5.9864 | 20.0004 | 22.247 | 30.4799 | 36.4663 | 0
3.7619 | 7.5151 | 1.9254 | 1.8881 | 2.627 | 2.7762 | 6.4405 | 4.5524 | 11.2769 | 13.165 | 19.6055 | 24.1579 | 3.7619 | 7.5151 | 1.9354 | 1.8881 | 2.627 | 2.7762 | 6.4405 | 4.5524 | 11.2769 | 13.165 | 19.6055 | 24.1579 | 0
0.66962 | 6.8451 | 1.8223 | 1.7335 | 2.1116 | 2.467 | 5.6674 | 3.9339 | 7.5147 | 9.2482 | 14.9156 | 18.8495 | 0.66962 | 6.8451 | 1.8323 | 1.7335 | 2.1116 | 2.467 | 5.6674 | 3.9339 | 7.5147 | 9.2482 | 14.9156 | 18.8495 | 0
8.4453 | 8.5298 | 2.0815 | 2.1223 | 3.4076 | 3.2445 | 7.6113 | 5.4891 | 16.9752 | 19.0974 | 26.7088 | 32.1978 | 8.4453 | 8.5298 | 2.0915 | 2.1223 | 3.4076 | 3.2445 | 7.6113 | 5.4891 | 16.9752 | 19.0974 | 26.7088 | 32.1978 | 0
4 | 7.5667 | 1.9333 | 1.9 | 2.6667 | 2.8 | 6.5 | 4.6 | 11.5666 | 13.4666 | 19.9666 | 24.5666 | 4 | 7.5667 | 1.9433 | 1.9 | 2.6667 | 2.8 | 6.5 | 4.6 | 11.5666 | 13.4666 | 19.9666 | 24.5666 | 0
0.11313 | 6.7245 | 1.8038 | 1.7057 | 2.0189 | 2.4113 | 5.5283 | 3.8226 | 6.8376 | 8.5433 | 14.0716 | 17.8942 | 0.11313 | 6.7245 | 1.8138 | 1.7057 | 2.0189 | 2.4113 | 5.5283 | 3.8226 | 6.8376 | 8.5433 | 14.0716 | 17.8942 | 0
14.3302 | 9.8049 | 2.2777 | 2.4165 | 4.3884 | 3.833 | 9.0825 | 6.666 | 24.135 | 26.5516 | 35.6341 | 42.3001 | 14.3302 | 9.8049 | 2.2877 | 2.4165 | 4.3884 | 3.833 | 9.0825 | 6.666 | 24.135 | 26.5516 | 35.6341 | 42.3001 | 0
0.82956 | 6.8797 | 1.8277 | 1.7415 | 2.1383 | 2.483 | 5.7074 | 3.9659 | 7.7093 | 9.4508 | 15.1582 | 19.1241 | 0.82956 | 6.8797 | 1.8377 | 1.7415 | 2.1383 | 2.483 | 5.7074 | 3.9659 | 7.7093 | 9.4508 | 15.1582 | 19.1241 | 0
6.5365 | 8.1162 | 2.0179 | 2.0268 | 3.0894 | 3.0537 | 7.1341 | 5.1073 | 14.6528 | 16.6796 | 23.8137 | 28.921 | 6.5365 | 8.1162 | 2.0279 | 2.0268 | 3.0894 | 3.0537 | 7.1341 | 5.1073 | 14.6528 | 16.6796 | 23.8137 | 28.921 | 0
2.4857 | 7.2386 | 1.8829 | 1.8243 | 2.4143 | 2.6486 | 6.1214 | 4.2971 | 9.7243 | 11.5486 | 17.67 | 21.9671 | 2.4857 | 7.2386 | 1.8929 | 1.8243 | 2.4143 | 2.6486 | 6.1214 | 4.2971 | 9.7243 | 11.5486 | 17.67 | 21.9671 | 0
9.4618 | 8.7501 | 2.1154 | 2.1731 | 3.577 | 3.3462 | 7.8655 | 5.6924 | 18.2119 | 20.385 | 28.2504 | 33.9428 | 9.4618 | 8.7501 | 2.1254 | 2.1731 | 3.577 | 3.3462 | 7.8655 | 5.6924 | 18.2119 | 20.385 | 28.2504 | 33.9428 | 0
10.5152 | 8.9783 | 2.1505 | 2.2258 | 3.7525 | 3.4515 | 8.1288 | 5.903 | 19.4935 | 21.7193 | 29.8481 | 35.7511 | 10.5152 | 8.9783 | 2.1605 | 2.2258 | 3.7525 | 3.4515 | 8.1288 | 5.903 | 19.4935 | 21.7193 | 29.8481 | 35.7511 | 0
13.8852 | 9.7085 | 2.2628 | 2.3943 | 4.3142 | 3.7885 | 8.9713 | 6.577 | 23.5937 | 25.9879 | 34.9592 | 41.5363 | 13.8852 | 9.7085 | 2.2728 | 2.3943 | 4.3142 | 3.7885 | 8.9713 | 6.577 | 23.5937 | 25.9879 | 34.9592 | 41.5363 | 0
7.4114 | 8.3058 | 2.047 | 2.0706 | 3.2352 | 3.1411 | 7.3529 | 5.2823 | 15.7172 | 17.7878 | 25.1406 | 30.4229 | 7.4114 | 8.3058 | 2.057 | 2.0706 | 3.2352 | 3.1411 | 7.3529 | 5.2823 | 15.7172 | 17.7878 | 25.1406 | 30.4229 | 0
3.3173 | 7.4187 | 1.9106 | 1.8659 | 2.5529 | 2.7317 | 6.3293 | 4.4635 | 10.736 | 12.6019 | 18.9312 | 23.3947 | 3.3173 | 7.4187 | 1.9206 | 1.8659 | 2.5529 | 2.7317 | 6.3293 | 4.4635 | 10.736 | 12.6019 | 18.9312 | 23.3947 | 0
6.514 | 8.1114 | 2.0171 | 2.0257 | 3.0857 | 3.0514 | 7.1285 | 5.1028 | 14.6253 | 16.651 | 23.7795 | 28.8823 | 6.514 | 8.1114 | 2.0271 | 2.0257 | 3.0857 | 3.0514 | 7.1285 | 5.1028 | 14.6253 | 16.651 | 23.7795 | 28.8823 | 0
-0.5379 | 6.5835 | 1.7821 | 1.6731 | 1.9104 | 2.3462 | 5.3655 | 3.6924 | 6.0456 | 7.7187 | 13.0842 | 16.7766 | -0.5379 | 6.5835 | 1.7921 | 1.6731 | 1.9104 | 2.3462 | 5.3655 | 3.6924 | 6.0456 | 7.7187 | 13.0842 | 16.7766 | 0
1.9903 | 7.1312 | 1.8663 | 1.7995 | 2.3317 | 2.599 | 5.9976 | 4.1981 | 9.1215 | 10.9211 | 16.9186 | 21.1167 | 1.9903 | 7.1312 | 1.8763 | 1.7995 | 2.3317 | 2.599 | 5.9976 | 4.1981 | 9.1215 | 10.9211 | 16.9186 | 21.1167 | 0
17.5171 | 10.4954 | 2.3839 | 2.5759 | 4.9195 | 4.1517 | 9.8793 | 7.3034 | 28.0125 | 30.5883 | 40.4676 | 47.771 | 17.5171 | 10.4954 | 2.3939 | 2.5759 | 4.9195 | 4.1517 | 9.8793 | 7.3034 | 28.0125 | 30.5883 | 40.4676 | 47.771 | 0
5.7762 | 7.9515 | 1.9925 | 1.9888 | 2.9627 | 2.9776 | 6.9441 | 4.9552 | 13.7277 | 15.7166 | 22.6606 | 27.6159 | 5.7762 | 7.9515 | 2.0025 | 1.9888 | 2.9627 | 2.9776 | 6.9441 | 4.9552 | 13.7277 | 15.7166 | 22.6606 | 27.6159 | 0
5.936 | 7.9861 | 1.9979 | 1.9968 | 2.9893 | 2.9936 | 6.984 | 4.9872 | 13.9222 | 15.919 | 22.903 | 27.8902 | 5.936 | 7.9861 | 2.0079 | 1.9968 | 2.9893 | 2.9936 | 6.984 | 4.9872 | 13.9222 | 15.919 | 22.903 | 27.8902 | 0
-4.9884 | 5.6192 | 1.6337 | 1.4506 | 1.1686 | 1.9012 | 4.2529 | 2.8023 | 0.63082 | 2.0814 | 6.3343 | 9.1366 | -4.9884 | 5.6192 | 1.6437 | 1.4506 | 1.1686 | 1.9012 | 4.2529 | 2.8023 | 0.63082 | 2.0814 | 6.3343 | 9.1366 | 0
4.2438 | 7.6195 | 1.9415 | 1.9122 | 2.7073 | 2.8244 | 6.561 | 4.6488 | 11.8633 | 13.7755 | 20.3365 | 24.9852 | 4.2438 | 7.6195 | 1.9515 | 1.9122 | 2.7073 | 2.8244 | 6.561 | 4.6488 | 11.8633 | 13.7755 | 20.3365 | 24.9852 | 0
8.0514 | 8.4445 | 2.0684 | 2.1026 | 3.3419 | 3.2051 | 7.5128 | 5.4103 | 16.4958 | 18.5984 | 26.1112 | 31.5215 | 8.0514 | 8.4445 | 2.0784 | 2.1026 | 3.3419 | 3.2051 | 7.5128 | 5.4103 | 16.4958 | 18.5984 | 26.1112 | 31.5215 | 0
-8.3684 | 4.8868 | 1.5211 | 1.2816 | 0.60526 | 1.5632 | 3.4079 | 2.1263 | -3.4816 | -2.2 | 1.2079 | 3.3342 | -8.3684 | 4.8868 | 1.5311 | 1.2816 | 0.60526 | 1.5632 | 3.4079 | 2.1263 | -3.4816 | -2.2 | 1.2079 | 3.3342 | 0
10.4473 | 8.9636 | 2.1482 | 2.2224 | 3.7412 | 3.4447 | 8.1118 | 5.8895 | 19.4109 | 21.6333 | 29.7451 | 35.6346 | 10.4473 | 8.9636 | 2.1582 | 2.2224 | 3.7412 | 3.4447 | 8.1118 | 5.8895 | 19.4109 | 21.6333 | 29.7451 | 35.6346 | 0
6.2781 | 8.0603 | 2.0093 | 2.0139 | 3.0463 | 3.0278 | 7.0695 | 5.0556 | 14.3383 | 16.3522 | 23.4218 | 28.4774 | 6.2781 | 8.0603 | 2.0193 | 2.0139 | 3.0463 | 3.0278 | 7.0695 | 5.0556 | 14.3383 | 16.3522 | 23.4218 | 28.4774 | 0
-0.026116 | 6.6943 | 1.7991 | 1.6987 | 1.9956 | 2.3974 | 5.4935 | 3.7948 | 6.6682 | 8.3669 | 13.8604 | 17.6552 | -0.026116 | 6.6943 | 1.8091 | 1.6987 | 1.9956 | 2.3974 | 5.4935 | 3.7948 | 6.6682 | 8.3669 | 13.8604 | 17.6552 | 0
12.3808 | 9.3825 | 2.2127 | 2.319 | 4.0635 | 3.6381 | 8.5952 | 6.2762 | 21.7633 | 24.0823 | 32.6775 | 38.9537 | 12.3808 | 9.3825 | 2.2227 | 2.319 | 4.0635 | 3.6381 | 8.5952 | 6.2762 | 21.7633 | 24.0823 | 32.6775 | 38.9537 | 0
4.3092 | 7.6337 | 1.9436 | 1.9155 | 2.7182 | 2.8309 | 6.5773 | 4.6618 | 11.9428 | 13.8583 | 20.4356 | 25.0974 | 4.3092 | 7.6337 | 1.9536 | 1.9155 | 2.7182 | 2.8309 | 6.5773 | 4.6618 | 11.9428 | 13.8583 | 20.4356 | 25.0974 | 0
9.5463 | 8.7684 | 2.1182 | 2.1773 | 3.591 | 3.3546 | 7.8866 | 5.7093 | 18.3146 | 20.492 | 28.3785 | 34.0878 | 9.5463 | 8.7684 | 2.1282 | 2.1773 | 3.591 | 3.3546 | 7.8866 | 5.7093 | 18.3146 | 20.492 | 28.3785 | 34.0878 | 0
3.7633 | 7.5154 | 1.9254 | 1.8882 | 2.6272 | 2.7763 | 6.4408 | 4.5527 | 11.2787 | 13.1668 | 19.6077 | 24.1603 | 3.7633 | 7.5154 | 1.9354 | 1.8882 | 2.6272 | 2.7763 | 6.4408 | 4.5527 | 11.2787 | 13.1668 | 19.6077 | 24.1603 | 0
8.7658 | 8.5992 | 2.0922 | 2.1383 | 3.461 | 3.2766 | 7.6914 | 5.5532 | 17.365 | 19.5033 | 27.1947 | 32.7479 | 8.7658 | 8.5992 | 2.1022 | 2.1383 | 3.461 | 3.2766 | 7.6914 | 5.5532 | 17.365 | 19.5033 | 27.1947 | 32.7479 | 0
0.69767 | 6.8512 | 1.8233 | 1.7349 | 2.1163 | 2.4698 | 5.6744 | 3.9395 | 7.5488 | 9.2837 | 14.9581 | 18.8977 | 0.69767 | 6.8512 | 1.8333 | 1.7349 | 2.1163 | 2.4698 | 5.6744 | 3.9395 | 7.5488 | 9.2837 | 14.9581 | 18.8977 | 0
11.5977 | 9.2128 | 2.1866 | 2.2799 | 3.9329 | 3.5598 | 8.3994 | 6.1195 | 20.8105 | 23.0904 | 31.4898 | 37.6094 | 11.5977 | 9.2128 | 2.1966 | 2.2799 | 3.9329 | 3.5598 | 8.3994 | 6.1195 | 20.8105 | 23.0904 | 31.4898 | 37.6094 | 0
8.4712 | 8.5354 | 2.0824 | 2.1236 | 3.4119 | 3.2471 | 7.6178 | 5.4942 | 17.0067 | 19.1302 | 26.748 | 32.2423 | 8.4712 | 8.5354 | 2.0924 | 2.1236 | 3.4119 | 3.2471 | 7.6178 | 5.4942 | 17.0067 | 19.1302 | 26.748 | 32.2423 | 0
18.2142 | 10.6464 | 2.4071 | 2.6107 | 5.0357 | 4.2214 | 10.0536 | 7.4428 | 28.8606 | 31.4713 | 41.5249 | 48.9677 | 18.2142 | 10.6464 | 2.4171 | 2.6107 | 5.0357 | 4.2214 | 10.0536 | 7.4428 | 28.8606 | 31.4713 | 41.5249 | 48.9677 | 0
13.8999 | 9.7117 | 2.2633 | 2.395 | 4.3167 | 3.79 | 8.975 | 6.58 | 23.6116 | 26.0066 | 34.9816 | 41.5615 | 13.8999 | 9.7117 | 2.2733 | 2.395 | 4.3167 | 3.79 | 8.975 | 6.58 | 23.6116 | 26.0066 | 34.9816 | 41.5615 | 0
6.3636 | 8.0788 | 2.0121 | 2.0182 | 3.0606 | 3.0364 | 7.0909 | 5.0727 | 14.4424 | 16.4605 | 23.5514 | 28.6242 | 6.3636 | 8.0788 | 2.0221 | 2.0182 | 3.0606 | 3.0364 | 7.0909 | 5.0727 | 14.4424 | 16.4605 | 23.5514 | 28.6242 | 0
6.9097 | 8.1971 | 2.0303 | 2.0455 | 3.1516 | 3.091 | 7.2274 | 5.1819 | 15.1068 | 17.1523 | 24.3797 | 29.5616 | 6.9097 | 8.1971 | 2.0403 | 2.0455 | 3.1516 | 3.091 | 7.2274 | 5.1819 | 15.1068 | 17.1523 | 24.3797 | 29.5616 | 0
1.1273 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7818 | 4.0255 | 8.0716 | 9.8279 | 15.6098 | 19.6352 | 1.1273 | 6.9443 | 1.8476 | 1.7564 | 2.1879 | 2.5127 | 5.7818 | 4.0255 | 8.0716 | 9.8279 | 15.6098 | 19.6352 | 0
15.8964 | 10.1442 | 2.3299 | 2.4948 | 4.6494 | 3.9896 | 9.4741 | 6.9793 | 26.0407 | 28.5355 | 38.0096 | 44.9889 | 15.8964 | 10.1442 | 2.3399 | 2.4948 | 4.6494 | 3.9896 | 9.4741 | 6.9793 | 26.0407 | 28.5355 | 38.0096 | 44.9889 | 0
6.1089 | 8.0236 | 2.0036 | 2.0054 | 3.0181 | 3.0109 | 7.0272 | 5.0218 | 14.1325 | 16.1379 | 23.1651 | 28.1869 | 6.1089 | 8.0236 | 2.0136 | 2.0054 | 3.0181 | 3.0109 | 7.0272 | 5.0218 | 14.1325 | 16.1379 | 23.1651 | 28.1869 | 0
0.25643 | 6.7556 | 1.8085 | 1.7128 | 2.0427 | 2.4256 | 5.5641 | 3.8513 | 7.012 | 8.7248 | 14.2889 | 18.1402 | 0.25643 | 6.7556 | 1.8185 | 1.7128 | 2.0427 | 2.4256 | 5.5641 | 3.8513 | 7.012 | 8.7248 | 14.2889 | 18.1402 | 0
-4.2332 | 5.7828 | 1.6589 | 1.4883 | 1.2945 | 1.9767 | 4.4417 | 2.9534 | 1.5496 | 3.038 | 7.4797 | 10.433 | -4.2332 | 5.7828 | 1.6689 | 1.4883 | 1.2945 | 1.9767 | 4.4417 | 2.9534 | 1.5496 | 3.038 | 7.4797 | 10.433 | 0
3.0006 | 7.3501 | 1.9 | 1.85 | 2.5001 | 2.7001 | 6.2501 | 4.4001 | 10.3507 | 12.2007 | 18.4509 | 22.851 | 3.0006 | 7.3501 | 1.91 | 1.85 | 2.5001 | 2.7001 | 6.2501 | 4.4001 | 10.3507 | 12.2007 | 18.4509 | 22.851 | 0
-0.019623 | 6.6957 | 1.7993 | 1.699 | 1.9967 | 2.398 | 5.4951 | 3.7961 | 6.6761 | 8.3751 | 13.8702 | 17.6663 | -0.019623 | 6.6957 | 1.8093 | 1.699 | 1.9967 | 2.398 | 5.4951 | 3.7961 | 6.6761 | 8.3751 | 13.8702 | 17.6663 | 0
1.7234 | 7.0734 | 1.8574 | 1.7862 | 2.2872 | 2.5723 | 5.9308 | 4.1447 | 8.7968 | 10.583 | 16.5138 | 20.6585 | 1.7234 | 7.0734 | 1.8674 | 1.7862 | 2.2872 | 2.5723 | 5.9308 | 4.1447 | 8.7968 | 10.583 | 16.5138 | 20.6585 | 0
17.9337 | 10.5856 | 2.3978 | 2.5967 | 4.9889 | 4.1934 | 9.9834 | 7.3867 | 28.5193 | 31.116 | 41.0994 | 48.4862 | 17.9337 | 10.5856 | 2.4078 | 2.5967 | 4.9889 | 4.1934 | 9.9834 | 7.3867 | 28.5193 | 31.116 | 41.0994 | 48.4862 | 0
5.9536 | 7.9899 | 1.9985 | 1.9977 | 2.9923 | 2.9954 | 6.9884 | 4.9907 | 13.9435 | 15.9412 | 22.9296 | 27.9203 | 5.9536 | 7.9899 | 2.0085 | 1.9977 | 2.9923 | 2.9954 | 6.9884 | 4.9907 | 13.9435 | 15.9412 | 22.9296 | 27.9203 | 0
8.1286 | 8.4612 | 2.071 | 2.1064 | 3.3548 | 3.2129 | 7.5321 | 5.4257 | 16.5897 | 18.6962 | 26.2283 | 31.654 | 8.1286 | 8.4612 | 2.081 | 2.1064 | 3.3548 | 3.2129 | 7.5321 | 5.4257 | 16.5897 | 18.6962 | 26.2283 | 31.654 | 0
0.99013 | 6.9145 | 1.833 | 1.7495 | 2.165 | 2.499 | 5.7475 | 3.998 | 7.9047 | 9.6542 | 15.4017 | 19.3997 | 0.99013 | 6.9145 | 1.843 | 1.7495 | 2.165 | 2.499 | 5.7475 | 3.998 | 7.9047 | 9.6542 | 15.4017 | 19.3997 | 0
9.9327 | 8.8521 | 2.1311 | 2.1966 | 3.6554 | 3.3933 | 7.9832 | 5.7865 | 18.7847 | 20.9814 | 28.9645 | 34.7511 | 9.9327 | 8.8521 | 2.1411 | 2.1966 | 3.6554 | 3.3933 | 7.9832 | 5.7865 | 18.7847 | 20.9814 | 28.9645 | 34.7511 | 0
13.1113 | 9.5408 | 2.237 | 2.3556 | 4.1852 | 3.7111 | 8.7778 | 6.4223 | 22.6521 | 25.0077 | 33.7855 | 40.2078 | 13.1113 | 9.5408 | 2.247 | 2.3556 | 4.1852 | 3.7111 | 8.7778 | 6.4223 | 22.6521 | 25.0077 | 33.7855 | 40.2078 | 0
3.9177 | 7.5488 | 1.9306 | 1.8959 | 2.6529 | 2.7918 | 6.4794 | 4.5835 | 11.4665 | 13.3624 | 19.8418 | 24.4253 | 3.9177 | 7.5488 | 1.9406 | 1.8959 | 2.6529 | 2.7918 | 6.4794 | 4.5835 | 11.4665 | 13.3624 | 19.8418 | 24.4253 | 0
4.0887 | 7.5859 | 1.9363 | 1.9044 | 2.6814 | 2.8089 | 6.5222 | 4.6177 | 11.6745 | 13.579 | 20.1011 | 24.7189 | 4.0887 | 7.5859 | 1.9463 | 1.9044 | 2.6814 | 2.8089 | 6.5222 | 4.6177 | 11.6745 | 13.579 | 20.1011 | 24.7189 | 0
-0.055066 | 6.6881 | 1.7982 | 1.6972 | 1.9908 | 2.3945 | 5.4862 | 3.789 | 6.633 | 8.3303 | 13.8165 | 17.6055 | -0.055066 | 6.6881 | 1.8082 | 1.6972 | 1.9908 | 2.3945 | 5.4862 | 3.789 | 6.633 | 8.3303 | 13.8165 | 17.6055 | 0
3.9499 | 7.5558 | 1.9317 | 1.8975 | 2.6583 | 2.795 | 6.4875 | 4.59 | 11.5057 | 13.4032 | 19.8906 | 24.4806 | 3.9499 | 7.5558 | 1.9417 | 1.8975 | 2.6583 | 2.795 | 6.4875 | 4.59 | 11.5057 | 13.4032 | 19.8906 | 24.4806 | 0
2.5412 | 7.2506 | 1.8847 | 1.8271 | 2.4235 | 2.6541 | 6.1353 | 4.3082 | 9.7918 | 11.6189 | 17.7542 | 22.0624 | 2.5412 | 7.2506 | 1.8947 | 1.8271 | 2.4235 | 2.6541 | 6.1353 | 4.3082 | 9.7918 | 11.6189 | 17.7542 | 22.0624 | 0
-1.6705 | 6.3381 | 1.7443 | 1.6165 | 1.7216 | 2.233 | 5.0824 | 3.4659 | 4.6676 | 6.2841 | 11.3664 | 14.8323 | -1.6705 | 6.3381 | 1.7543 | 1.6165 | 1.7216 | 2.233 | 5.0824 | 3.4659 | 4.6676 | 6.2841 | 11.3664 | 14.8323 | 0
17.8938 | 10.577 | 2.3965 | 2.5947 | 4.9823 | 4.1894 | 9.9734 | 7.3788 | 28.4708 | 31.0655 | 41.0389 | 48.4177 | 17.8938 | 10.577 | 2.4065 | 2.5947 | 4.9823 | 4.1894 | 9.9734 | 7.3788 | 28.4708 | 31.0655 | 41.0389 | 48.4177 | 0
2.6217 | 7.268 | 1.8874 | 1.8311 | 2.4369 | 2.6622 | 6.1554 | 4.3243 | 9.8897 | 11.7208 | 17.8762 | 22.2005 | 2.6217 | 7.268 | 1.8974 | 1.8311 | 2.4369 | 2.6622 | 6.1554 | 4.3243 | 9.8897 | 11.7208 | 17.8762 | 22.2005 | 0
6.531 | 8.1151 | 2.0177 | 2.0266 | 3.0885 | 3.0531 | 7.1328 | 5.1062 | 14.6461 | 16.6726 | 23.8054 | 28.9116 | 6.531 | 8.1151 | 2.0277 | 2.0266 | 3.0885 | 3.0531 | 7.1328 | 5.1062 | 14.6461 | 16.6726 | 23.8054 | 28.9116 | 0
-0.63752 | 6.5619 | 1.7787 | 1.6681 | 1.8937 | 2.3362 | 5.3406 | 3.6725 | 5.9244 | 7.5925 | 12.9331 | 16.6056 | -0.63752 | 6.5619 | 1.7887 | 1.6681 | 1.8937 | 2.3362 | 5.3406 | 3.6725 | 5.9244 | 7.5925 | 12.9331 | 16.6056 | 0
3.242 | 7.4024 | 1.9081 | 1.8621 | 2.5403 | 2.7242 | 6.3105 | 4.4484 | 10.6444 | 12.5065 | 18.817 | 23.2654 | 3.242 | 7.4024 | 1.9181 | 1.8621 | 2.5403 | 2.7242 | 6.3105 | 4.4484 | 10.6444 | 12.5065 | 18.817 | 23.2654 | 0
7.7059 | 8.3696 | 2.0569 | 2.0853 | 3.2843 | 3.1706 | 7.4265 | 5.3412 | 16.0755 | 18.1608 | 25.5873 | 30.9285 | 7.7059 | 8.3696 | 2.0669 | 2.0853 | 3.2843 | 3.1706 | 7.4265 | 5.3412 | 16.0755 | 18.1608 | 25.5873 | 30.9285 | 0
5.5315 | 7.8985 | 1.9844 | 1.9766 | 2.9219 | 2.9532 | 6.8829 | 4.9063 | 13.43 | 15.4066 | 22.2895 | 27.1958 | 5.5315 | 7.8985 | 1.9944 | 1.9766 | 2.9219 | 2.9532 | 6.8829 | 4.9063 | 13.43 | 15.4066 | 22.2895 | 27.1958 | 0
6.2875 | 8.0623 | 2.0096 | 2.0144 | 3.0479 | 3.0288 | 7.0719 | 5.0575 | 14.3498 | 16.3642 | 23.4361 | 28.4936 | 6.2875 | 8.0623 | 2.0196 | 2.0144 | 3.0479 | 3.0288 | 7.0719 | 5.0575 | 14.3498 | 16.3642 | 23.4361 | 28.4936 | 0
8.8478 | 8.617 | 2.0949 | 2.1424 | 3.4746 | 3.2848 | 7.7119 | 5.5696 | 17.4648 | 19.6072 | 27.3191 | 32.8887 | 8.8478 | 8.617 | 2.1049 | 2.1424 | 3.4746 | 3.2848 | 7.7119 | 5.5696 | 17.4648 | 19.6072 | 27.3191 | 32.8887 | 0
3.6485 | 7.4905 | 1.9216 | 1.8824 | 2.6081 | 2.7648 | 6.4121 | 4.5297 | 11.139 | 13.0214 | 19.4335 | 23.9632 | 3.6485 | 7.4905 | 1.9316 | 1.8824 | 2.6081 | 2.7648 | 6.4121 | 4.5297 | 11.139 | 13.0214 | 19.4335 | 23.9632 | 0
4.5406 | 7.6838 | 1.9514 | 1.927 | 2.7568 | 2.8541 | 6.6352 | 4.7081 | 12.2244 | 14.1515 | 20.7866 | 25.4947 | 4.5406 | 7.6838 | 1.9614 | 1.927 | 2.7568 | 2.8541 | 6.6352 | 4.7081 | 12.2244 | 14.1515 | 20.7866 | 25.4947 | 0
7.2969 | 8.281 | 2.0432 | 2.0648 | 3.2162 | 3.1297 | 7.3242 | 5.2594 | 15.5779 | 17.6428 | 24.967 | 30.2264 | 7.2969 | 8.281 | 2.0532 | 2.0648 | 3.2162 | 3.1297 | 7.3242 | 5.2594 | 15.5779 | 17.6428 | 24.967 | 30.2264 | 0
7.5894 | 8.3444 | 2.053 | 2.0795 | 3.2649 | 3.1589 | 7.3974 | 5.3179 | 15.9338 | 18.0133 | 25.4106 | 30.7285 | 7.5894 | 8.3444 | 2.063 | 2.0795 | 3.2649 | 3.1589 | 7.3974 | 5.3179 | 15.9338 | 18.0133 | 25.4106 | 30.7285 | 0
-1.186 | 6.443 | 1.7605 | 1.6407 | 1.8023 | 2.2814 | 5.2035 | 3.5628 | 5.257 | 6.8977 | 12.1012 | 15.664 | -1.186 | 6.443 | 1.7705 | 1.6407 | 1.8023 | 2.2814 | 5.2035 | 3.5628 | 5.257 | 6.8977 | 12.1012 | 15.664 | 0
7.5221 | 8.3298 | 2.0507 | 2.0761 | 3.2537 | 3.1522 | 7.3805 | 5.3044 | 15.8519 | 17.928 | 25.3085 | 30.6129 | 7.5221 | 8.3298 | 2.0607 | 2.0761 | 3.2537 | 3.1522 | 7.3805 | 5.3044 | 15.8519 | 17.928 | 25.3085 | 30.6129 | 0
4.1728 | 7.6041 | 1.9391 | 1.9086 | 2.6955 | 2.8173 | 6.5432 | 4.6346 | 11.7769 | 13.6856 | 20.2288 | 24.8633 | 4.1728 | 7.6041 | 1.9491 | 1.9086 | 2.6955 | 2.8173 | 6.5432 | 4.6346 | 11.7769 | 13.6856 | 20.2288 | 24.8633 | 0
10.0312 | 8.8734 | 2.1344 | 2.2016 | 3.6719 | 3.4031 | 8.0078 | 5.8062 | 18.9047 | 21.1062 | 29.114 | 34.9203 | 10.0312 | 8.8734 | 2.1444 | 2.2016 | 3.6719 | 3.4031 | 8.0078 | 5.8062 | 18.9047 | 21.1062 | 29.114 | 34.9203 | 0
1.8924 | 7.11 | 1.8631 | 1.7946 | 2.3154 | 2.5892 | 5.9731 | 4.1785 | 9.0025 | 10.7971 | 16.7702 | 20.9487 | 1.8924 | 7.11 | 1.8731 | 1.7946 | 2.3154 | 2.5892 | 5.9731 | 4.1785 | 9.0025 | 10.7971 | 16.7702 | 20.9487 | 0
16.936 | 10.3695 | 2.3645 | 2.5468 | 4.8227 | 4.0936 | 9.734 | 7.1872 | 27.3054 | 29.8522 | 39.5862 | 46.7734 | 16.936 | 10.3695 | 2.3745 | 2.5468 | 4.8227 | 4.0936 | 9.734 | 7.1872 | 27.3054 | 29.8522 | 39.5862 | 46.7734 | 0
7.2675 | 8.2746 | 2.0422 | 2.0634 | 3.2112 | 3.1267 | 7.3169 | 5.2535 | 15.5421 | 17.6055 | 24.9223 | 30.1758 | 7.2675 | 8.2746 | 2.0522 | 2.0634 | 3.2112 | 3.1267 | 7.3169 | 5.2535 | 15.5421 | 17.6055 | 24.9223 | 30.1758 | 0
5.0004 | 7.7834 | 1.9667 | 1.95 | 2.8334 | 2.9 | 6.7501 | 4.8001 | 12.7839 | 14.7339 | 21.484 | 26.2841 | 5.0004 | 7.7834 | 1.9767 | 1.95 | 2.8334 | 2.9 | 6.7501 | 4.8001 | 12.7839 | 14.7339 | 21.484 | 26.2841 | 0
8.22 | 8.481 | 2.074 | 2.111 | 3.37 | 3.222 | 7.555 | 5.444 | 16.7011 | 18.8121 | 26.3671 | 31.8111 | 8.22 | 8.481 | 2.084 | 2.111 | 3.37 | 3.222 | 7.555 | 5.444 | 16.7011 | 18.8121 | 26.3671 | 31.8111 | 0
15.5054 | 10.0595 | 2.3168 | 2.4753 | 4.5842 | 3.9505 | 9.3763 | 6.9011 | 25.5649 | 28.0401 | 37.4165 | 44.3175 | 15.5054 | 10.0595 | 2.3268 | 2.4753 | 4.5842 | 3.9505 | 9.3763 | 6.9011 | 25.5649 | 28.0401 | 37.4165 | 44.3175 | 0
1.1288 | 6.9446 | 1.8376 | 1.7564 | 2.1881 | 2.5129 | 5.7822 | 4.0258 | 8.0734 | 9.8299 | 15.6121 | 19.6378 | 1.1288 | 6.9446 | 1.8476 | 1.7564 | 2.1881 | 2.5129 | 5.7822 | 4.0258 | 8.0734 | 9.8299 | 15.6121 | 19.6378 | 0
0.42329 | 6.7917 | 1.8141 | 1.7212 | 2.0705 | 2.4423 | 5.6058 | 3.8847 | 7.215 | 8.9362 | 14.542 | 18.4267 | 0.42329 | 6.7917 | 1.8241 | 1.7212 | 2.0705 | 2.4423 | 5.6058 | 3.8847 | 7.215 | 8.9362 | 14.542 | 18.4267 | 0
6.5131 | 8.1112 | 2.0171 | 2.0257 | 3.0855 | 3.0513 | 7.1283 | 5.1026 | 14.6242 | 16.6499 | 23.7781 | 28.8807 | 6.5131 | 8.1112 | 2.0271 | 2.0257 | 3.0855 | 3.0513 | 7.1283 | 5.1026 | 14.6242 | 16.6499 | 23.7781 | 28.8807 | 0
-0.42709 | 6.6075 | 1.7858 | 1.6786 | 1.9288 | 2.3573 | 5.3932 | 3.7146 | 6.1804 | 7.859 | 13.2522 | 16.9668 | -0.42709 | 6.6075 | 1.7958 | 1.6786 | 1.9288 | 2.3573 | 5.3932 | 3.7146 | 6.1804 | 7.859 | 13.2522 | 16.9668 | 0
3.3855 | 7.4335 | 1.9129 | 1.8693 | 2.5643 | 2.7386 | 6.3464 | 4.4771 | 10.8191 | 12.6883 | 19.0347 | 23.5118 | 3.3855 | 7.4335 | 1.9229 | 1.8693 | 2.5643 | 2.7386 | 6.3464 | 4.4771 | 10.8191 | 12.6883 | 19.0347 | 23.5118 | 0
9.2592 | 8.7062 | 2.1086 | 2.163 | 3.5432 | 3.3259 | 7.8148 | 5.6518 | 17.9653 | 20.1283 | 27.9431 | 33.5949 | 9.2592 | 8.7062 | 2.1186 | 2.163 | 3.5432 | 3.3259 | 7.8148 | 5.6518 | 17.9653 | 20.1283 | 27.9431 | 33.5949 | 0
0.34898 | 6.7756 | 1.8116 | 1.7174 | 2.0582 | 2.4349 | 5.5872 | 3.8698 | 7.1246 | 8.842 | 14.4293 | 18.2991 | 0.34898 | 6.7756 | 1.8216 | 1.7174 | 2.0582 | 2.4349 | 5.5872 | 3.8698 | 7.1246 | 8.842 | 14.4293 | 18.2991 | 0
14.8692 | 9.9217 | 2.2956 | 2.4435 | 4.4782 | 3.8869 | 9.2173 | 6.7738 | 24.7908 | 27.2343 | 36.4516 | 43.2254 | 14.8692 | 9.9217 | 2.3056 | 2.4435 | 4.4782 | 3.8869 | 9.2173 | 6.7738 | 24.7908 | 27.2343 | 36.4516 | 43.2254 | 0
14.2324 | 9.7837 | 2.2744 | 2.4116 | 4.3721 | 3.8232 | 9.0581 | 6.6465 | 24.0161 | 26.4277 | 35.4858 | 42.1323 | 14.2324 | 9.7837 | 2.2844 | 2.4116 | 4.3721 | 3.8232 | 9.0581 | 6.6465 | 24.0161 | 26.4277 | 35.4858 | 42.1323 | 0
-3.7799 | 5.881 | 1.674 | 1.511 | 1.37 | 2.022 | 4.555 | 3.044 | 2.1012 | 3.6122 | 8.1672 | 11.2112 | -3.7799 | 5.881 | 1.684 | 1.511 | 1.37 | 2.022 | 4.555 | 3.044 | 2.1012 | 3.6122 | 8.1672 | 11.2112 | 0
5.3413 | 7.8573 | 1.978 | 1.9671 | 2.8902 | 2.9341 | 6.8353 | 4.8683 | 13.1986 | 15.1657 | 22.001 | 26.8693 | 5.3413 | 7.8573 | 1.988 | 1.9671 | 2.8902 | 2.9341 | 6.8353 | 4.8683 | 13.1986 | 15.1657 | 22.001 | 26.8693 | 0
13.6643 | 9.6606 | 2.2555 | 2.3832 | 4.2774 | 3.7664 | 8.9161 | 6.5329 | 23.3249 | 25.7081 | 34.6242 | 41.157 | 13.6643 | 9.6606 | 2.2655 | 2.3832 | 4.2774 | 3.7664 | 8.9161 | 6.5329 | 23.3249 | 25.7081 | 34.6242 | 41.157 | 0
17.2063 | 10.428 | 2.3735 | 2.5603 | 4.8677 | 4.1206 | 9.8016 | 7.2413 | 27.6343 | 30.1946 | 39.9962 | 47.2374 | 17.2063 | 10.428 | 2.3835 | 2.5603 | 4.8677 | 4.1206 | 9.8016 | 7.2413 | 27.6343 | 30.1946 | 39.9962 | 47.2374 | 0
8.2493 | 8.4874 | 2.075 | 2.1125 | 3.3749 | 3.2249 | 7.5623 | 5.4499 | 16.7367 | 18.8491 | 26.4115 | 31.8613 | 8.2493 | 8.4874 | 2.085 | 2.1125 | 3.3749 | 3.2249 | 7.5623 | 5.4499 | 16.7367 | 18.8491 | 26.4115 | 31.8613 | 0
5.4441 | 7.8796 | 1.9815 | 1.9722 | 2.9074 | 2.9444 | 6.861 | 4.8888 | 13.3237 | 15.2959 | 22.1569 | 27.0457 | 5.4441 | 7.8796 | 1.9915 | 1.9722 | 2.9074 | 2.9444 | 6.861 | 4.8888 | 13.3237 | 15.2959 | 22.1569 | 27.0457 | 0
0.4585 | 6.7993 | 1.8153 | 1.7229 | 2.0764 | 2.4459 | 5.6146 | 3.8917 | 7.2578 | 8.9808 | 14.5954 | 18.4871 | 0.4585 | 6.7993 | 1.8253 | 1.7229 | 2.0764 | 2.4459 | 5.6146 | 3.8917 | 7.2578 | 8.9808 | 14.5954 | 18.4871 | 0
-0.038013 | 6.6918 | 1.7987 | 1.6981 | 1.9937 | 2.3962 | 5.4905 | 3.7924 | 6.6538 | 8.3519 | 13.8423 | 17.6347 | -0.038013 | 6.6918 | 1.8087 | 1.6981 | 1.9937 | 2.3962 | 5.4905 | 3.7924 | 6.6538 | 8.3519 | 13.8423 | 17.6347 | 0
11.8839 | 9.2749 | 2.1961 | 2.2942 | 3.9807 | 3.5884 | 8.471 | 6.1768 | 21.1588 | 23.453 | 31.924 | 38.1008 | 11.8839 | 9.2749 | 2.2061 | 2.2942 | 3.9807 | 3.5884 | 8.471 | 6.1768 | 21.1588 | 23.453 | 31.924 | 38.1008 | 0
-3.1106 | 6.026 | 1.6963 | 1.5445 | 1.4816 | 2.0889 | 4.7224 | 3.1779 | 2.9155 | 4.4599 | 9.1823 | 12.3602 | -3.1106 | 6.026 | 1.7063 | 1.5445 | 1.4816 | 2.0889 | 4.7224 | 3.1779 | 2.9155 | 4.4599 | 9.1823 | 12.3602 | 0
2.154 | 7.1667 | 1.8718 | 1.8077 | 2.359 | 2.6154 | 6.0385 | 4.2308 | 9.3207 | 11.1284 | 17.1669 | 21.3977 | 2.154 | 7.1667 | 1.8818 | 1.8077 | 2.359 | 2.6154 | 6.0385 | 4.2308 | 9.3207 | 11.1284 | 17.1669 | 21.3977 | 0
7.67 | 8.3618 | 2.0557 | 2.0835 | 3.2783 | 3.167 | 7.4175 | 5.334 | 16.0319 | 18.1154 | 25.5329 | 30.8669 | 7.67 | 8.3618 | 2.0657 | 2.0835 | 3.2783 | 3.167 | 7.4175 | 5.334 | 16.0319 | 18.1154 | 25.5329 | 30.8669 | 0
15.8604 | 10.1364 | 2.3287 | 2.493 | 4.6434 | 3.986 | 9.4651 | 6.9721 | 25.9968 | 28.4898 | 37.9549 | 44.927 | 15.8604 | 10.1364 | 2.3387 | 2.493 | 4.6434 | 3.986 | 9.4651 | 6.9721 | 25.9968 | 28.4898 | 37.9549 | 44.927 | 0
-1.0877 | 6.4643 | 1.7637 | 1.6456 | 1.8187 | 2.2912 | 5.2281 | 3.5825 | 5.3766 | 7.0222 | 12.2503 | 15.8327 | -1.0877 | 6.4643 | 1.7737 | 1.6456 | 1.8187 | 2.2912 | 5.2281 | 3.5825 | 5.3766 | 7.0222 | 12.2503 | 15.8327 | 0
9.5656 | 8.7725 | 2.1189 | 2.1783 | 3.5943 | 3.3566 | 7.8914 | 5.7131 | 18.3381 | 20.5164 | 28.4078 | 34.1209 | 9.5656 | 8.7725 | 2.1289 | 2.1783 | 3.5943 | 3.3566 | 7.8914 | 5.7131 | 18.3381 | 20.5164 | 28.4078 | 34.1209 | 0
5.2751 | 7.8429 | 1.9758 | 1.9638 | 2.8792 | 2.9275 | 6.8188 | 4.855 | 13.1181 | 15.0818 | 21.9006 | 26.7557 | 5.2751 | 7.8429 | 1.9858 | 1.9638 | 2.8792 | 2.9275 | 6.8188 | 4.855 | 13.1181 | 15.0818 | 21.9006 | 26.7557 | 0
4.8547 | 7.7519 | 1.9618 | 1.9427 | 2.8091 | 2.8855 | 6.7137 | 4.7709 | 12.6066 | 14.5493 | 21.263 | 26.0339 | 4.8547 | 7.7519 | 1.9718 | 1.9427 | 2.8091 | 2.8855 | 6.7137 | 4.7709 | 12.6066 | 14.5493 | 21.263 | 26.0339 | 0
4.1225 | 7.5932 | 1.9374 | 1.9061 | 2.6871 | 2.8123 | 6.5306 | 4.6245 | 11.7157 | 13.6219 | 20.1525 | 24.777 | 4.1225 | 7.5932 | 1.9474 | 1.9061 | 2.6871 | 2.8123 | 6.5306 | 4.6245 | 11.7157 | 13.6219 | 20.1525 | 24.777 | 0
0.12817 | 6.7278 | 1.8043 | 1.7064 | 2.0214 | 2.4128 | 5.532 | 3.8256 | 6.8559 | 8.5623 | 14.0944 | 17.92 | 0.12817 | 6.7278 | 1.8143 | 1.7064 | 2.0214 | 2.4128 | 5.532 | 3.8256 | 6.8559 | 8.5623 | 14.0944 | 17.92 | 0
3.1497 | 7.3824 | 1.905 | 1.8575 | 2.525 | 2.715 | 6.2874 | 4.4299 | 10.5322 | 12.3897 | 18.6771 | 23.107 | 3.1497 | 7.3824 | 1.915 | 1.8575 | 2.525 | 2.715 | 6.2874 | 4.4299 | 10.5322 | 12.3897 | 18.6771 | 23.107 | 0
0.004088 | 6.7009 | 1.8001 | 1.7002 | 2.0007 | 2.4004 | 5.501 | 3.8008 | 6.705 | 8.4052 | 13.9062 | 17.707 | 0.004088 | 6.7009 | 1.8101 | 1.7002 | 2.0007 | 2.4004 | 5.501 | 3.8008 | 6.705 | 8.4052 | 13.9062 | 17.707 | 0
2.664 | 7.2772 | 1.8888 | 1.8332 | 2.444 | 2.6664 | 6.166 | 4.3328 | 9.9412 | 11.7744 | 17.9403 | 22.2731 | 2.664 | 7.2772 | 1.8988 | 1.8332 | 2.444 | 2.6664 | 6.166 | 4.3328 | 9.9412 | 11.7744 | 17.9403 | 22.2731 | 0
16.3601 | 10.2447 | 2.3453 | 2.518 | 4.7267 | 4.036 | 9.59 | 7.072 | 26.6047 | 29.1227 | 38.7127 | 45.7848 | 16.3601 | 10.2447 | 2.3553 | 2.518 | 4.7267 | 4.036 | 9.59 | 7.072 | 26.6047 | 29.1227 | 38.7127 | 45.7848 | 0
1.1157 | 6.9417 | 1.8372 | 1.7558 | 2.186 | 2.5116 | 5.7789 | 4.0231 | 8.0575 | 9.8133 | 15.5922 | 19.6153 | 1.1157 | 6.9417 | 1.8472 | 1.7558 | 2.186 | 2.5116 | 5.7789 | 4.0231 | 8.0575 | 9.8133 | 15.5922 | 19.6153 | 0
8.3578 | 8.5109 | 2.0786 | 2.1179 | 3.393 | 3.2358 | 7.5894 | 5.4716 | 16.8686 | 18.9865 | 26.576 | 32.0475 | 8.3578 | 8.5109 | 2.0886 | 2.1179 | 3.393 | 3.2358 | 7.5894 | 5.4716 | 16.8686 | 18.9865 | 26.576 | 32.0475 | 0
-3.237 | 5.9986 | 1.6921 | 1.5381 | 1.4605 | 2.0763 | 4.6907 | 3.1526 | 2.7616 | 4.2998 | 8.9905 | 12.1431 | -3.237 | 5.9986 | 1.7021 | 1.5381 | 1.4605 | 2.0763 | 4.6907 | 3.1526 | 2.7616 | 4.2998 | 8.9905 | 12.1431 | 0
3.8189 | 7.5274 | 1.9273 | 1.8909 | 2.6365 | 2.7819 | 6.4547 | 4.5638 | 11.3463 | 13.2373 | 19.692 | 24.2558 | 3.8189 | 7.5274 | 1.9373 | 1.8909 | 2.6365 | 2.7819 | 6.4547 | 4.5638 | 11.3463 | 13.2373 | 19.692 | 24.2558 | 0
9.7219 | 8.8064 | 2.1241 | 2.1861 | 3.6203 | 3.3722 | 7.9305 | 5.7444 | 18.5283 | 20.7144 | 28.6448 | 34.3892 | 9.7219 | 8.8064 | 2.1341 | 2.1861 | 3.6203 | 3.3722 | 7.9305 | 5.7444 | 18.5283 | 20.7144 | 28.6448 | 34.3892 | 0
8.9915 | 8.6482 | 2.0997 | 2.1496 | 3.4986 | 3.2992 | 7.7479 | 5.5983 | 17.6397 | 19.7893 | 27.5372 | 33.1355 | 8.9915 | 8.6482 | 2.1097 | 2.1496 | 3.4986 | 3.2992 | 7.7479 | 5.5983 | 17.6397 | 19.7893 | 27.5372 | 33.1355 | 0
-3.6954 | 5.8993 | 1.6768 | 1.5152 | 1.3841 | 2.0305 | 4.5762 | 3.0609 | 2.2039 | 3.7192 | 8.2953 | 11.3562 | -3.6954 | 5.8993 | 1.6868 | 1.5152 | 1.3841 | 2.0305 | 4.5762 | 3.0609 | 2.2039 | 3.7192 | 8.2953 | 11.3562 | 0
10.0738 | 8.8827 | 2.1358 | 2.2037 | 3.679 | 3.4074 | 8.0185 | 5.8148 | 18.9565 | 21.1602 | 29.1787 | 34.9934 | 10.0738 | 8.8827 | 2.1458 | 2.2037 | 3.679 | 3.4074 | 8.0185 | 5.8148 | 18.9565 | 21.1602 | 29.1787 | 34.9934 | 0
0.046038 | 6.71 | 1.8015 | 1.7023 | 2.0077 | 2.4046 | 5.5115 | 3.8092 | 6.756 | 8.4583 | 13.9698 | 17.779 | 0.046038 | 6.71 | 1.8115 | 1.7023 | 2.0077 | 2.4046 | 5.5115 | 3.8092 | 6.756 | 8.4583 | 13.9698 | 17.779 | 0
11.9431 | 9.2877 | 2.1981 | 2.2972 | 3.9905 | 3.5943 | 8.4858 | 6.1886 | 21.2308 | 23.528 | 32.0138 | 38.2024 | 11.9431 | 9.2877 | 2.2081 | 2.2972 | 3.9905 | 3.5943 | 8.4858 | 6.1886 | 21.2308 | 23.528 | 32.0138 | 38.2024 | 0
10.2351 | 8.9176 | 2.1412 | 2.2118 | 3.7058 | 3.4235 | 8.0588 | 5.847 | 19.1527 | 21.3645 | 29.4232 | 35.2703 | 10.2351 | 8.9176 | 2.1512 | 2.2118 | 3.7058 | 3.4235 | 8.0588 | 5.847 | 19.1527 | 21.3645 | 29.4232 | 35.2703 | 0
16.0073 | 10.1682 | 2.3336 | 2.5004 | 4.6679 | 4.0007 | 9.5018 | 7.0015 | 26.1755 | 28.6759 | 38.1777 | 45.1791 | 16.0073 | 10.1682 | 2.3436 | 2.5004 | 4.6679 | 4.0007 | 9.5018 | 7.0015 | 26.1755 | 28.6759 | 38.1777 | 45.1791 | 0
11.2117 | 9.1292 | 2.1737 | 2.2606 | 3.8686 | 3.5212 | 8.3029 | 6.0423 | 20.3409 | 22.6015 | 30.9044 | 36.9468 | 11.2117 | 9.1292 | 2.1837 | 2.2606 | 3.8686 | 3.5212 | 8.3029 | 6.0423 | 20.3409 | 22.6015 | 30.9044 | 36.9468 | 0
0.7651 | 6.8658 | 1.8255 | 1.7383 | 2.1275 | 2.4765 | 5.6913 | 3.953 | 7.6309 | 9.3691 | 15.0604 | 19.0134 | 0.7651 | 6.8658 | 1.8355 | 1.7383 | 2.1275 | 2.4765 | 5.6913 | 3.953 | 7.6309 | 9.3691 | 15.0604 | 19.0134 | 0
-2.5424 | 6.1491 | 1.7153 | 1.5729 | 1.5763 | 2.1458 | 4.8644 | 3.2915 | 3.6068 | 5.1796 | 10.044 | 13.3356 | -2.5424 | 6.1491 | 1.7253 | 1.5729 | 1.5763 | 2.1458 | 4.8644 | 3.2915 | 3.6068 | 5.1796 | 10.044 | 13.3356 | 0
6.6128 | 8.1328 | 2.0204 | 2.0306 | 3.1021 | 3.0613 | 7.1532 | 5.1226 | 14.7456 | 16.7763 | 23.9295 | 29.052 | 6.6128 | 8.1328 | 2.0304 | 2.0306 | 3.1021 | 3.0613 | 7.1532 | 5.1226 | 14.7456 | 16.7763 | 23.9295 | 29.052 | 0
-0.13011 | 6.6718 | 1.7957 | 1.6935 | 1.9783 | 2.387 | 5.4675 | 3.774 | 6.5417 | 8.2352 | 13.7027 | 17.4766 | -0.13011 | 6.6718 | 1.8057 | 1.6935 | 1.9783 | 2.387 | 5.4675 | 3.774 | 6.5417 | 8.2352 | 13.7027 | 17.4766 | 0
2.5146 | 7.2448 | 1.8838 | 1.8257 | 2.4191 | 2.6515 | 6.1286 | 4.3029 | 9.7594 | 11.5851 | 17.7138 | 22.0167 | 2.5146 | 7.2448 | 1.8938 | 1.8257 | 2.4191 | 2.6515 | 6.1286 | 4.3029 | 9.7594 | 11.5851 | 17.7138 | 22.0167 | 0
14.496 | 9.8408 | 2.2832 | 2.4248 | 4.416 | 3.8496 | 9.124 | 6.6992 | 24.3368 | 26.7616 | 35.8856 | 42.5848 | 14.496 | 9.8408 | 2.2932 | 2.4248 | 4.416 | 3.8496 | 9.124 | 6.6992 | 24.3368 | 26.7616 | 35.8856 | 42.5848 | 0
6.3767 | 8.0816 | 2.0126 | 2.0188 | 3.0628 | 3.0377 | 7.0942 | 5.0753 | 14.4583 | 16.4771 | 23.5713 | 28.6466 | 6.3767 | 8.0816 | 2.0226 | 2.0188 | 3.0628 | 3.0377 | 7.0942 | 5.0753 | 14.4583 | 16.4771 | 23.5713 | 28.6466 | 0
-0.66363 | 6.5562 | 1.7779 | 1.6668 | 1.8894 | 2.3336 | 5.3341 | 3.6673 | 5.8926 | 7.5594 | 12.8935 | 16.5608 | -0.66363 | 6.5562 | 1.7879 | 1.6668 | 1.8894 | 2.3336 | 5.3341 | 3.6673 | 5.8926 | 7.5594 | 12.8935 | 16.5608 | 0
6.6236 | 8.1351 | 2.0208 | 2.0312 | 3.1039 | 3.0624 | 7.1559 | 5.1247 | 14.7587 | 16.7899 | 23.9458 | 29.0705 | 6.6236 | 8.1351 | 2.0308 | 2.0312 | 3.1039 | 3.0624 | 7.1559 | 5.1247 | 14.7587 | 16.7899 | 23.9458 | 29.0705 | 0
-1.4404 | 6.3879 | 1.752 | 1.628 | 1.7599 | 2.256 | 5.1399 | 3.5119 | 4.9476 | 6.5755 | 11.7155 | 15.2274 | -1.4404 | 6.3879 | 1.762 | 1.628 | 1.7599 | 2.256 | 5.1399 | 3.5119 | 4.9476 | 6.5755 | 11.7155 | 15.2274 | 0
3.8707 | 7.5386 | 1.929 | 1.8935 | 2.6451 | 2.7871 | 6.4677 | 4.5741 | 11.4093 | 13.3029 | 19.7705 | 24.3447 | 3.8707 | 7.5386 | 1.939 | 1.8935 | 2.6451 | 2.7871 | 6.4677 | 4.5741 | 11.4093 | 13.3029 | 19.7705 | 24.3447 | 0
-11.3239 | 4.2465 | 1.4225 | 1.1338 | 0.11268 | 1.2676 | 2.669 | 1.5352 | -7.0774 | -5.9436 | -3.2746 | -1.7394 | -11.3239 | 4.2465 | 1.4325 | 1.1338 | 0.11268 | 1.2676 | 2.669 | 1.5352 | -7.0774 | -5.9436 | -3.2746 | -1.7394 | 0
8.374 | 8.5144 | 2.0791 | 2.1187 | 3.3957 | 3.2374 | 7.5935 | 5.4748 | 16.8884 | 19.0071 | 26.6006 | 32.0754 | 8.374 | 8.5144 | 2.0891 | 2.1187 | 3.3957 | 3.2374 | 7.5935 | 5.4748 | 16.8884 | 19.0071 | 26.6006 | 32.0754 | 0
12.9704 | 9.5102 | 2.2323 | 2.3485 | 4.1617 | 3.697 | 8.7426 | 6.3941 | 22.4806 | 24.8291 | 33.5717 | 39.9658 | 12.9704 | 9.5102 | 2.2423 | 2.3485 | 4.1617 | 3.697 | 8.7426 | 6.3941 | 22.4806 | 24.8291 | 33.5717 | 39.9658 | 0
1.7719 | 7.0839 | 1.8591 | 1.7886 | 2.2953 | 2.5772 | 5.943 | 4.1544 | 8.8558 | 10.6444 | 16.5874 | 20.7418 | 1.7719 | 7.0839 | 1.8691 | 1.7886 | 2.2953 | 2.5772 | 5.943 | 4.1544 | 8.8558 | 10.6444 | 16.5874 | 20.7418 | 0
-0.26064 | 6.6435 | 1.7913 | 1.687 | 1.9566 | 2.3739 | 5.4348 | 3.7479 | 6.3829 | 8.0699 | 13.5047 | 17.2526 | -0.26064 | 6.6435 | 1.8013 | 1.687 | 1.9566 | 2.3739 | 5.4348 | 3.7479 | 6.3829 | 8.0699 | 13.5047 | 17.2526 | 0
8.9346 | 8.6358 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7336 | 5.5869 | 17.5704 | 19.7171 | 27.4507 | 33.0376 | 8.9346 | 8.6358 | 2.1078 | 2.1467 | 3.4891 | 3.2935 | 7.7336 | 5.5869 | 17.5704 | 19.7171 | 27.4507 | 33.0376 | 0
8.9889 | 8.6476 | 2.0996 | 2.1494 | 3.4981 | 3.2989 | 7.7472 | 5.5978 | 17.6365 | 19.7859 | 27.5332 | 33.1309 | 8.9889 | 8.6476 | 2.1096 | 2.1494 | 3.4981 | 3.2989 | 7.7472 | 5.5978 | 17.6365 | 19.7859 | 27.5332 | 33.1309 | 0
5.2835 | 7.8448 | 1.9761 | 1.9642 | 2.8806 | 2.9284 | 6.8209 | 4.8567 | 13.1283 | 15.0925 | 21.9133 | 26.77 | 5.2835 | 7.8448 | 1.9861 | 1.9642 | 2.8806 | 2.9284 | 6.8209 | 4.8567 | 13.1283 | 15.0925 | 21.9133 | 26.77 | 0
9.4524 | 8.748 | 2.1151 | 2.1726 | 3.5754 | 3.3452 | 7.8631 | 5.6905 | 18.2004 | 20.373 | 28.2361 | 33.9266 | 9.4524 | 8.748 | 2.1251 | 2.1726 | 3.5754 | 3.3452 | 7.8631 | 5.6905 | 18.2004 | 20.373 | 28.2361 | 33.9266 | 0
12.1174 | 9.3254 | 2.2039 | 2.3059 | 4.0196 | 3.6117 | 8.5294 | 6.2235 | 21.4429 | 23.7487 | 32.2781 | 38.5016 | 12.1174 | 9.3254 | 2.2139 | 2.3059 | 4.0196 | 3.6117 | 8.5294 | 6.2235 | 21.4429 | 23.7487 | 32.2781 | 38.5016 | 0
2.5021 | 7.2421 | 1.8834 | 1.8251 | 2.417 | 2.6502 | 6.1255 | 4.3004 | 9.7443 | 11.5694 | 17.6949 | 21.9953 | 2.5021 | 7.2421 | 1.8934 | 1.8251 | 2.417 | 2.6502 | 6.1255 | 4.3004 | 9.7443 | 11.5694 | 17.6949 | 21.9953 | 0
0.91537 | 6.8983 | 1.8305 | 1.7458 | 2.1526 | 2.4915 | 5.7288 | 3.9831 | 7.8137 | 9.5595 | 15.2883 | 19.2714 | 0.91537 | 6.8983 | 1.8405 | 1.7458 | 2.1526 | 2.4915 | 5.7288 | 3.9831 | 7.8137 | 9.5595 | 15.2883 | 19.2714 | 0
-1.7202 | 6.3273 | 1.7427 | 1.614 | 1.7133 | 2.228 | 5.07 | 3.456 | 4.6071 | 6.2211 | 11.2911 | 14.7471 | -1.7202 | 6.3273 | 1.7527 | 1.614 | 1.7133 | 2.228 | 5.07 | 3.456 | 4.6071 | 6.2211 | 11.2911 | 14.7471 | 0
7.3217 | 8.2864 | 2.0441 | 2.0661 | 3.2203 | 3.1322 | 7.3304 | 5.2643 | 15.608 | 17.6741 | 25.0046 | 30.2689 | 7.3217 | 8.2864 | 2.0541 | 2.0661 | 3.2203 | 3.1322 | 7.3304 | 5.2643 | 15.608 | 17.6741 | 25.0046 | 30.2689 | 0
7.9757 | 8.4281 | 2.0659 | 2.0988 | 3.3293 | 3.1976 | 7.4939 | 5.3951 | 16.4037 | 18.5025 | 25.9965 | 31.3916 | 7.9757 | 8.4281 | 2.0759 | 2.0988 | 3.3293 | 3.1976 | 7.4939 | 5.3951 | 16.4037 | 18.5025 | 25.9965 | 31.3916 | 0
-2.8082 | 6.0916 | 1.7064 | 1.5596 | 1.532 | 2.1192 | 4.798 | 3.2384 | 3.2834 | 4.843 | 9.6409 | 12.8793 | -2.8082 | 6.0916 | 1.7164 | 1.5596 | 1.532 | 2.1192 | 4.798 | 3.2384 | 3.2834 | 4.843 | 9.6409 | 12.8793 | 0
-1.3037 | 6.4175 | 1.7565 | 1.6348 | 1.7827 | 2.2696 | 5.1741 | 3.5393 | 5.1139 | 6.7487 | 11.9228 | 15.462 | -1.3037 | 6.4175 | 1.7665 | 1.6348 | 1.7827 | 2.2696 | 5.1741 | 3.5393 | 5.1139 | 6.7487 | 11.9228 | 15.462 | 0
0.17091 | 6.737 | 1.8057 | 1.7085 | 2.0285 | 2.4171 | 5.5427 | 3.8342 | 6.9079 | 8.6165 | 14.1592 | 17.9934 | 0.17091 | 6.737 | 1.8157 | 1.7085 | 2.0285 | 2.4171 | 5.5427 | 3.8342 | 6.9079 | 8.6165 | 14.1592 | 17.9934 | 0
-7.6486 | 5.0428 | 1.545 | 1.3176 | 0.72523 | 1.6351 | 3.5878 | 2.2703 | -2.6058 | -1.2883 | 2.2996 | 4.5698 | -7.6486 | 5.0428 | 1.555 | 1.3176 | 0.72523 | 1.6351 | 3.5878 | 2.2703 | -2.6058 | -1.2883 | 2.2996 | 4.5698 | 0
7.5446 | 8.3347 | 2.0515 | 2.0772 | 3.2574 | 3.1545 | 7.3862 | 5.3089 | 15.8793 | 17.9565 | 25.3427 | 30.6516 | 7.5446 | 8.3347 | 2.0615 | 2.0772 | 3.2574 | 3.1545 | 7.3862 | 5.3089 | 15.8793 | 17.9565 | 25.3427 | 30.6516 | 0
9.7001 | 8.8017 | 2.1233 | 2.185 | 3.6167 | 3.37 | 7.925 | 5.74 | 18.5018 | 20.6869 | 28.6119 | 34.3519 | 9.7001 | 8.8017 | 2.1333 | 2.185 | 3.6167 | 3.37 | 7.925 | 5.74 | 18.5018 | 20.6869 | 28.6119 | 34.3519 | 0
8.0543 | 8.4451 | 2.0685 | 2.1027 | 3.3424 | 3.2054 | 7.5136 | 5.4109 | 16.4994 | 18.6021 | 26.1157 | 31.5266 | 8.0543 | 8.4451 | 2.0785 | 2.1027 | 3.3424 | 3.2054 | 7.5136 | 5.4109 | 16.4994 | 18.6021 | 26.1157 | 31.5266 | 0
-1.2755 | 6.4236 | 1.7575 | 1.6362 | 1.7874 | 2.2725 | 5.1811 | 3.5449 | 5.1482 | 6.7844 | 11.9655 | 15.5104 | -1.2755 | 6.4236 | 1.7675 | 1.6362 | 1.7874 | 2.2725 | 5.1811 | 3.5449 | 5.1482 | 6.7844 | 11.9655 | 15.5104 | 0
1.6532 | 7.0582 | 1.8551 | 1.7827 | 2.2755 | 2.5653 | 5.9133 | 4.1306 | 8.7114 | 10.494 | 16.4073 | 20.538 | 1.6532 | 7.0582 | 1.8651 | 1.7827 | 2.2755 | 2.5653 | 5.9133 | 4.1306 | 8.7114 | 10.494 | 16.4073 | 20.538 | 0
4.0014 | 7.567 | 1.9334 | 1.9001 | 2.6669 | 2.8001 | 6.5004 | 4.6003 | 11.5684 | 13.4685 | 19.9689 | 24.5692 | 4.0014 | 7.567 | 1.9434 | 1.9001 | 2.6669 | 2.8001 | 6.5004 | 4.6003 | 11.5684 | 13.4685 | 19.9689 | 24.5692 | 0
9.7211 | 8.8062 | 2.124 | 2.1861 | 3.6202 | 3.3721 | 7.9303 | 5.7442 | 18.5273 | 20.7134 | 28.6437 | 34.3879 | 9.7211 | 8.8062 | 2.134 | 2.1861 | 3.6202 | 3.3721 | 7.9303 | 5.7442 | 18.5273 | 20.7134 | 28.6437 | 34.3879 | 0
18.4405 | 10.6954 | 2.4147 | 2.622 | 5.0734 | 4.2441 | 10.1101 | 7.4881 | 29.136 | 31.758 | 41.8681 | 49.3562 | 18.4405 | 10.6954 | 2.4247 | 2.622 | 5.0734 | 4.2441 | 10.1101 | 7.4881 | 29.136 | 31.758 | 41.8681 | 49.3562 | 0
6.7586 | 8.1644 | 2.0253 | 2.0379 | 3.1264 | 3.0759 | 7.1896 | 5.1517 | 14.9229 | 16.9609 | 24.1505 | 29.3022 | 6.7586 | 8.1644 | 2.0353 | 2.0379 | 3.1264 | 3.0759 | 7.1896 | 5.1517 | 14.9229 | 16.9609 | 24.1505 | 29.3022 | 0
17.2651 | 10.4408 | 2.3755 | 2.5633 | 4.8775 | 4.1265 | 9.8163 | 7.253 | 27.7059 | 30.2692 | 40.0855 | 47.3385 | 17.2651 | 10.4408 | 2.3855 | 2.5633 | 4.8775 | 4.1265 | 9.8163 | 7.253 | 27.7059 | 30.2692 | 40.0855 | 47.3385 | 0
-4.1978 | 5.7905 | 1.6601 | 1.4901 | 1.3004 | 1.9802 | 4.4506 | 2.9604 | 1.5927 | 3.0828 | 7.5334 | 10.4938 | -4.1978 | 5.7905 | 1.6701 | 1.4901 | 1.3004 | 1.9802 | 4.4506 | 2.9604 | 1.5927 | 3.0828 | 7.5334 | 10.4938 | 0
7.4729 | 8.3191 | 2.0491 | 2.0736 | 3.2455 | 3.1473 | 7.3682 | 5.2946 | 15.7921 | 17.8657 | 25.2339 | 30.5285 | 7.4729 | 8.3191 | 2.0591 | 2.0736 | 3.2455 | 3.1473 | 7.3682 | 5.2946 | 15.7921 | 17.8657 | 25.2339 | 30.5285 | 0
-0.8847 | 6.5083 | 1.7705 | 1.6558 | 1.8525 | 2.3115 | 5.2788 | 3.6231 | 5.6236 | 7.2794 | 12.5582 | 16.1813 | -0.8847 | 6.5083 | 1.7805 | 1.6558 | 1.8525 | 2.3115 | 5.2788 | 3.6231 | 5.6236 | 7.2794 | 12.5582 | 16.1813 | 0
14.5788 | 9.8587 | 2.286 | 2.4289 | 4.4298 | 3.8579 | 9.1447 | 6.7158 | 24.4376 | 26.8665 | 36.0112 | 42.727 | 14.5788 | 9.8587 | 2.296 | 2.4289 | 4.4298 | 3.8579 | 9.1447 | 6.7158 | 24.4376 | 26.8665 | 36.0112 | 42.727 | 0
0.12537 | 6.7272 | 1.8042 | 1.7063 | 2.0209 | 2.4125 | 5.5313 | 3.8251 | 6.8525 | 8.5588 | 14.0901 | 17.9152 | 0.12537 | 6.7272 | 1.8142 | 1.7063 | 2.0209 | 2.4125 | 5.5313 | 3.8251 | 6.8525 | 8.5588 | 14.0901 | 17.9152 | 0
4.2245 | 7.6153 | 1.9408 | 1.9112 | 2.7041 | 2.8224 | 6.5561 | 4.6449 | 11.8398 | 13.751 | 20.3071 | 24.952 | 4.2245 | 7.6153 | 1.9508 | 1.9112 | 2.7041 | 2.8224 | 6.5561 | 4.6449 | 11.8398 | 13.751 | 20.3071 | 24.952 | 0
15.0219 | 9.9547 | 2.3007 | 2.4511 | 4.5036 | 3.9022 | 9.2555 | 6.8044 | 24.9766 | 27.4277 | 36.6832 | 43.4875 | 15.0219 | 9.9547 | 2.3107 | 2.4511 | 4.5036 | 3.9022 | 9.2555 | 6.8044 | 24.9766 | 27.4277 | 36.6832 | 43.4875 | 0
-2.3623 | 6.1882 | 1.7213 | 1.5819 | 1.6063 | 2.1638 | 4.9094 | 3.3275 | 3.8258 | 5.4077 | 10.3171 | 13.6446 | -2.3623 | 6.1882 | 1.7313 | 1.5819 | 1.6063 | 2.1638 | 4.9094 | 3.3275 | 3.8258 | 5.4077 | 10.3171 | 13.6446 | 0
-0.42982 | 6.6069 | 1.7857 | 1.6785 | 1.9284 | 2.357 | 5.3925 | 3.714 | 6.177 | 7.8556 | 13.2481 | 16.9621 | -0.42982 | 6.6069 | 1.7957 | 1.6785 | 1.9284 | 2.357 | 5.3925 | 3.714 | 6.177 | 7.8556 | 13.2481 | 16.9621 | 0
7.7003 | 8.3684 | 2.0567 | 2.085 | 3.2834 | 3.17 | 7.4251 | 5.3401 | 16.0687 | 18.1537 | 25.5788 | 30.9188 | 7.7003 | 8.3684 | 2.0667 | 2.085 | 3.2834 | 3.17 | 7.4251 | 5.3401 | 16.0687 | 18.1537 | 25.5788 | 30.9188 | 0
5.0337 | 7.7906 | 1.9678 | 1.9517 | 2.839 | 2.9034 | 6.7584 | 4.8067 | 12.8244 | 14.776 | 21.5345 | 26.3412 | 5.0337 | 7.7906 | 1.9778 | 1.9517 | 2.839 | 2.9034 | 6.7584 | 4.8067 | 12.8244 | 14.776 | 21.5345 | 26.3412 | 0
3.2793 | 7.4105 | 1.9093 | 1.864 | 2.5465 | 2.7279 | 6.3198 | 4.4559 | 10.6898 | 12.5538 | 18.8736 | 23.3294 | 3.2793 | 7.4105 | 1.9193 | 1.864 | 2.5465 | 2.7279 | 6.3198 | 4.4559 | 10.6898 | 12.5538 | 18.8736 | 23.3294 | 0
-0.40881 | 6.6114 | 1.7864 | 1.6796 | 1.9319 | 2.3591 | 5.3978 | 3.7182 | 6.2026 | 7.8822 | 13.28 | 16.9982 | -0.40881 | 6.6114 | 1.7964 | 1.6796 | 1.9319 | 2.3591 | 5.3978 | 3.7182 | 6.2026 | 7.8822 | 13.28 | 16.9982 | 0
12.3703 | 9.3802 | 2.2123 | 2.3185 | 4.0617 | 3.637 | 8.5926 | 6.2741 | 21.7505 | 24.069 | 32.6616 | 38.9356 | 12.3703 | 9.3802 | 2.2223 | 2.3185 | 4.0617 | 3.637 | 8.5926 | 6.2741 | 21.7505 | 24.069 | 32.6616 | 38.9356 | 0
9.2318 | 8.7002 | 2.1077 | 2.1616 | 3.5386 | 3.3232 | 7.8079 | 5.6464 | 17.932 | 20.0936 | 27.9015 | 33.5479 | 9.2318 | 8.7002 | 2.1177 | 2.1616 | 3.5386 | 3.3232 | 7.8079 | 5.6464 | 17.932 | 20.0936 | 27.9015 | 33.5479 | 0
9.9205 | 8.8494 | 2.1307 | 2.196 | 3.6534 | 3.392 | 7.9801 | 5.7841 | 18.7699 | 20.9659 | 28.946 | 34.7301 | 9.9205 | 8.8494 | 2.1407 | 2.196 | 3.6534 | 3.392 | 7.9801 | 5.7841 | 18.7699 | 20.9659 | 28.946 | 34.7301 | 0
12.8623 | 9.4868 | 2.2287 | 2.3431 | 4.1437 | 3.6862 | 8.7156 | 6.3725 | 22.3491 | 24.6922 | 33.4078 | 39.7802 | 12.8623 | 9.4868 | 2.2387 | 2.3431 | 4.1437 | 3.6862 | 8.7156 | 6.3725 | 22.3491 | 24.6922 | 33.4078 | 39.7802 | 0
-2.6898 | 6.1172 | 1.7103 | 1.5655 | 1.5517 | 2.131 | 4.8276 | 3.262 | 3.4274 | 4.9929 | 9.8205 | 13.0825 | -2.6898 | 6.1172 | 1.7203 | 1.5655 | 1.5517 | 2.131 | 4.8276 | 3.262 | 3.4274 | 4.9929 | 9.8205 | 13.0825 | 0
10.976 | 9.0781 | 2.1659 | 2.2488 | 3.8293 | 3.4976 | 8.244 | 5.9952 | 20.0542 | 22.303 | 30.547 | 36.5422 | 10.976 | 9.0781 | 2.1759 | 2.2488 | 3.8293 | 3.4976 | 8.244 | 5.9952 | 20.0542 | 22.303 | 30.547 | 36.5422 | 0
6.1885 | 8.0408 | 2.0063 | 2.0094 | 3.0314 | 3.0189 | 7.0471 | 5.0377 | 14.2294 | 16.2388 | 23.2859 | 28.3237 | 6.1885 | 8.0408 | 2.0163 | 2.0094 | 3.0314 | 3.0189 | 7.0471 | 5.0377 | 14.2294 | 16.2388 | 23.2859 | 28.3237 | 0
-0.0097864 | 6.6979 | 1.7997 | 1.6995 | 1.9984 | 2.399 | 5.4976 | 3.798 | 6.6881 | 8.3876 | 13.8852 | 17.6832 | -0.0097864 | 6.6979 | 1.8097 | 1.6995 | 1.9984 | 2.399 | 5.4976 | 3.798 | 6.6881 | 8.3876 | 13.8852 | 17.6832 | 0
13.3212 | 9.5863 | 2.244 | 2.3661 | 4.2202 | 3.7321 | 8.8303 | 6.4642 | 22.9074 | 25.2735 | 34.1038 | 40.568 | 13.3212 | 9.5863 | 2.254 | 2.3661 | 4.2202 | 3.7321 | 8.8303 | 6.4642 | 22.9074 | 25.2735 | 34.1038 | 40.568 | 0
-0.72099 | 6.5438 | 1.776 | 1.664 | 1.8798 | 2.3279 | 5.3198 | 3.6558 | 5.8228 | 7.4867 | 12.8065 | 16.4623 | -0.72099 | 6.5438 | 1.786 | 1.664 | 1.8798 | 2.3279 | 5.3198 | 3.6558 | 5.8228 | 7.4867 | 12.8065 | 16.4623 | 0
-0.99952 | 6.4834 | 1.7667 | 1.65 | 1.8334 | 2.3 | 5.2501 | 3.6001 | 5.4839 | 7.1339 | 12.3841 | 15.9842 | -0.99952 | 6.4834 | 1.7767 | 1.65 | 1.8334 | 2.3 | 5.2501 | 3.6001 | 5.4839 | 7.1339 | 12.3841 | 15.9842 | 0
1.5168 | 7.0286 | 1.8506 | 1.7758 | 2.2528 | 2.5517 | 5.8792 | 4.1034 | 8.5455 | 10.3213 | 16.2005 | 20.3039 | 1.5168 | 7.0286 | 1.8606 | 1.7758 | 2.2528 | 2.5517 | 5.8792 | 4.1034 | 8.5455 | 10.3213 | 16.2005 | 20.3039 | 0
-0.58033 | 6.5743 | 1.7807 | 1.671 | 1.9033 | 2.342 | 5.3549 | 3.6839 | 5.9939 | 7.6649 | 13.0198 | 16.7038 | -0.58033 | 6.5743 | 1.7907 | 1.671 | 1.9033 | 2.342 | 5.3549 | 3.6839 | 5.9939 | 7.6649 | 13.0198 | 16.7038 | 0
0.17113 | 6.7371 | 1.8057 | 1.7086 | 2.0285 | 2.4171 | 5.5428 | 3.8342 | 6.9082 | 8.6168 | 14.1595 | 17.9938 | 0.17113 | 6.7371 | 1.8157 | 1.7086 | 2.0285 | 2.4171 | 5.5428 | 3.8342 | 6.9082 | 8.6168 | 14.1595 | 17.9938 | 0
0.074319 | 6.7161 | 1.8025 | 1.7037 | 2.0124 | 2.4074 | 5.5186 | 3.8149 | 6.7904 | 8.4941 | 14.0127 | 17.8276 | 0.074319 | 6.7161 | 1.8125 | 1.7037 | 2.0124 | 2.4074 | 5.5186 | 3.8149 | 6.7904 | 8.4941 | 14.0127 | 17.8276 | 0
1.085 | 6.9351 | 1.8362 | 1.7543 | 2.1808 | 2.5085 | 5.7713 | 4.017 | 8.0201 | 9.7744 | 15.5456 | 19.5626 | 1.085 | 6.9351 | 1.8462 | 1.7543 | 2.1808 | 2.5085 | 5.7713 | 4.017 | 8.0201 | 9.7744 | 15.5456 | 19.5626 | 0
-3.1212 | 6.0237 | 1.696 | 1.5439 | 1.4798 | 2.0879 | 4.7197 | 3.1758 | 2.9025 | 4.4464 | 9.1661 | 12.3419 | -3.1212 | 6.0237 | 1.706 | 1.5439 | 1.4798 | 2.0879 | 4.7197 | 3.1758 | 2.9025 | 4.4464 | 9.1661 | 12.3419 | 0
6.0895 | 8.0194 | 2.003 | 2.0045 | 3.0149 | 3.009 | 7.0224 | 5.0179 | 14.1089 | 16.1134 | 23.1357 | 28.1536 | 6.0895 | 8.0194 | 2.013 | 2.0045 | 3.0149 | 3.009 | 7.0224 | 5.0179 | 14.1089 | 16.1134 | 23.1357 | 28.1536 | 0
6.2141 | 8.0464 | 2.0071 | 2.0107 | 3.0357 | 3.0214 | 7.0535 | 5.0428 | 14.2605 | 16.2712 | 23.3247 | 28.3676 | 6.2141 | 8.0464 | 2.0171 | 2.0107 | 3.0357 | 3.0214 | 7.0535 | 5.0428 | 14.2605 | 16.2712 | 23.3247 | 28.3676 | 0
9.4624 | 8.7502 | 2.1154 | 2.1731 | 3.5771 | 3.3462 | 7.8656 | 5.6925 | 18.2126 | 20.3857 | 28.2513 | 33.9437 | 9.4624 | 8.7502 | 2.1254 | 2.1731 | 3.5771 | 3.3462 | 7.8656 | 5.6925 | 18.2126 | 20.3857 | 28.2513 | 33.9437 | 0
2.7991 | 7.3065 | 1.8933 | 1.84 | 2.4665 | 2.6799 | 6.1998 | 4.3598 | 10.1056 | 11.9456 | 18.1454 | 22.5052 | 2.7991 | 7.3065 | 1.9033 | 1.84 | 2.4665 | 2.6799 | 6.1998 | 4.3598 | 10.1056 | 11.9456 | 18.1454 | 22.5052 | 0
0.57475 | 6.8245 | 1.8192 | 1.7287 | 2.0958 | 2.4575 | 5.6437 | 3.915 | 7.3993 | 9.128 | 14.7717 | 18.6867 | 0.57475 | 6.8245 | 1.8292 | 1.7287 | 2.0958 | 2.4575 | 5.6437 | 3.915 | 7.3993 | 9.128 | 14.7717 | 18.6867 | 0
9.4411 | 8.7456 | 2.1147 | 2.1721 | 3.5735 | 3.3441 | 7.8603 | 5.6882 | 18.1866 | 20.3587 | 28.219 | 33.9072 | 9.4411 | 8.7456 | 2.1247 | 2.1721 | 3.5735 | 3.3441 | 7.8603 | 5.6882 | 18.1866 | 20.3587 | 28.219 | 33.9072 | 0
-1.3256 | 6.4128 | 1.7558 | 1.6337 | 1.7791 | 2.2674 | 5.1686 | 3.5349 | 5.0872 | 6.7209 | 11.8896 | 15.4244 | -1.3256 | 6.4128 | 1.7658 | 1.6337 | 1.7791 | 2.2674 | 5.1686 | 3.5349 | 5.0872 | 6.7209 | 11.8896 | 15.4244 | 0
6.3785 | 8.082 | 2.0126 | 2.0189 | 3.0631 | 3.0379 | 7.0946 | 5.0757 | 14.4605 | 16.4794 | 23.5741 | 28.6498 | 6.3785 | 8.082 | 2.0226 | 2.0189 | 3.0631 | 3.0379 | 7.0946 | 5.0757 | 14.4605 | 16.4794 | 23.5741 | 28.6498 | 0
1.0149 | 6.9199 | 1.8338 | 1.7507 | 2.1692 | 2.5015 | 5.7537 | 4.003 | 7.9348 | 9.6856 | 15.4393 | 19.4423 | 1.0149 | 6.9199 | 1.8438 | 1.7507 | 2.1692 | 2.5015 | 5.7537 | 4.003 | 7.9348 | 9.6856 | 15.4393 | 19.4423 | 0
3.1071 | 7.3732 | 1.9036 | 1.8554 | 2.5178 | 2.7107 | 6.2768 | 4.4214 | 10.4803 | 12.3356 | 18.6124 | 23.0338 | 3.1071 | 7.3732 | 1.9136 | 1.8554 | 2.5178 | 2.7107 | 6.2768 | 4.4214 | 10.4803 | 12.3356 | 18.6124 | 23.0338 | 0
8.6083 | 8.5651 | 2.0869 | 2.1304 | 3.4347 | 3.2608 | 7.6521 | 5.5217 | 17.1734 | 19.3038 | 26.9559 | 32.4776 | 8.6083 | 8.5651 | 2.0969 | 2.1304 | 3.4347 | 3.2608 | 7.6521 | 5.5217 | 17.1734 | 19.3038 | 26.9559 | 32.4776 | 0
-7.3979 | 5.0971 | 1.5534 | 1.3301 | 0.76701 | 1.6602 | 3.6505 | 2.3204 | -2.3008 | -0.97073 | 2.6798 | 5.0002 | -7.3979 | 5.0971 | 1.5634 | 1.3301 | 0.76701 | 1.6602 | 3.6505 | 2.3204 | -2.3008 | -0.97073 | 2.6798 | 5.0002 | 0
9.1391 | 8.6801 | 2.1046 | 2.157 | 3.5232 | 3.3139 | 7.7848 | 5.6278 | 17.8192 | 19.9762 | 27.7609 | 33.3887 | 9.1391 | 8.6801 | 2.1146 | 2.157 | 3.5232 | 3.3139 | 7.7848 | 5.6278 | 17.8192 | 19.9762 | 27.7609 | 33.3887 | 0
10.1185 | 8.8923 | 2.1373 | 2.2059 | 3.6864 | 3.4118 | 8.0296 | 5.8237 | 19.0108 | 21.2168 | 29.2464 | 35.0701 | 10.1185 | 8.8923 | 2.1473 | 2.2059 | 3.6864 | 3.4118 | 8.0296 | 5.8237 | 19.0108 | 21.2168 | 29.2464 | 35.0701 | 0
8.8895 | 8.6261 | 2.0963 | 2.1445 | 3.4816 | 3.289 | 7.7224 | 5.5779 | 17.5156 | 19.6601 | 27.3825 | 32.9604 | 8.8895 | 8.6261 | 2.1063 | 2.1445 | 3.4816 | 3.289 | 7.7224 | 5.5779 | 17.5156 | 19.6601 | 27.3825 | 32.9604 | 0
18.1174 | 10.6254 | 2.4039 | 2.6059 | 5.0196 | 4.2117 | 10.0293 | 7.4235 | 28.7428 | 31.3487 | 41.378 | 48.8015 | 18.1174 | 10.6254 | 2.4139 | 2.6059 | 5.0196 | 4.2117 | 10.0293 | 7.4235 | 28.7428 | 31.3487 | 41.378 | 48.8015 | 0
-4.172 | 5.7961 | 1.6609 | 1.4914 | 1.3047 | 1.9828 | 4.457 | 2.9656 | 1.6241 | 3.1155 | 7.5725 | 10.5381 | -4.172 | 5.7961 | 1.6709 | 1.4914 | 1.3047 | 1.9828 | 4.457 | 2.9656 | 1.6241 | 3.1155 | 7.5725 | 10.5381 | 0
4.7866 | 7.7371 | 1.9596 | 1.9393 | 2.7978 | 2.8787 | 6.6966 | 4.7573 | 12.5236 | 14.463 | 21.1596 | 25.9169 | 4.7866 | 7.7371 | 1.9696 | 1.9393 | 2.7978 | 2.8787 | 6.6966 | 4.7573 | 12.5236 | 14.463 | 21.1596 | 25.9169 | 0
8.5519 | 8.5529 | 2.0851 | 2.1276 | 3.4253 | 3.2552 | 7.638 | 5.5104 | 17.1048 | 19.2324 | 26.8704 | 32.3807 | 8.5519 | 8.5529 | 2.0951 | 2.1276 | 3.4253 | 3.2552 | 7.638 | 5.5104 | 17.1048 | 19.2324 | 26.8704 | 32.3807 | 0
6.8119 | 8.1759 | 2.0271 | 2.0406 | 3.1353 | 3.0812 | 7.203 | 5.1624 | 14.9878 | 17.0284 | 24.2313 | 29.3937 | 6.8119 | 8.1759 | 2.0371 | 2.0406 | 3.1353 | 3.0812 | 7.203 | 5.1624 | 14.9878 | 17.0284 | 24.2313 | 29.3937 | 0
-7.8754 | 4.9937 | 1.5375 | 1.3062 | 0.68743 | 1.6125 | 3.5311 | 2.2249 | -2.8818 | -1.5755 | 1.9556 | 4.1805 | -7.8754 | 4.9937 | 1.5475 | 1.3062 | 0.68743 | 1.6125 | 3.5311 | 2.2249 | -2.8818 | -1.5755 | 1.9556 | 4.1805 | 0
3.4751 | 7.4529 | 1.9158 | 1.8738 | 2.5792 | 2.7475 | 6.3688 | 4.495 | 10.9281 | 12.8018 | 19.1706 | 23.6656 | 3.4751 | 7.4529 | 1.9258 | 1.8738 | 2.5792 | 2.7475 | 6.3688 | 4.495 | 10.9281 | 12.8018 | 19.1706 | 23.6656 | 0
-3.9303 | 5.8484 | 1.669 | 1.5035 | 1.345 | 2.007 | 4.5174 | 3.0139 | 1.9181 | 3.4216 | 7.9391 | 10.953 | -3.9303 | 5.8484 | 1.679 | 1.5035 | 1.345 | 2.007 | 4.5174 | 3.0139 | 1.9181 | 3.4216 | 7.9391 | 10.953 | 0
11.6169 | 9.217 | 2.1872 | 2.2808 | 3.9362 | 3.5617 | 8.4042 | 6.1234 | 20.8339 | 23.1148 | 31.519 | 37.6424 | 11.6169 | 9.217 | 2.1972 | 2.2808 | 3.9362 | 3.5617 | 8.4042 | 6.1234 | 20.8339 | 23.1148 | 31.519 | 37.6424 | 0
6.6067 | 8.1315 | 2.0202 | 2.0303 | 3.1011 | 3.0607 | 7.1517 | 5.1213 | 14.7382 | 16.7685 | 23.9202 | 29.0415 | 6.6067 | 8.1315 | 2.0302 | 2.0303 | 3.1011 | 3.0607 | 7.1517 | 5.1213 | 14.7382 | 16.7685 | 23.9202 | 29.0415 | 0
3.6787 | 7.4971 | 1.9226 | 1.8839 | 2.6131 | 2.7679 | 6.4197 | 4.5357 | 11.1758 | 13.0597 | 19.4794 | 24.0151 | 3.6787 | 7.4971 | 1.9326 | 1.8839 | 2.6131 | 2.7679 | 6.4197 | 4.5357 | 11.1758 | 13.0597 | 19.4794 | 24.0151 | 0
10.0022 | 8.8671 | 2.1334 | 2.2001 | 3.667 | 3.4002 | 8.0005 | 5.8004 | 18.8693 | 21.0694 | 29.07 | 34.8704 | 10.0022 | 8.8671 | 2.1434 | 2.2001 | 3.667 | 3.4002 | 8.0005 | 5.8004 | 18.8693 | 21.0694 | 29.07 | 34.8704 | 0
2.8576 | 7.3192 | 1.8953 | 1.8429 | 2.4763 | 2.6858 | 6.2144 | 4.3715 | 10.1768 | 12.0197 | 18.2341 | 22.6056 | 2.8576 | 7.3192 | 1.9053 | 1.8429 | 2.4763 | 2.6858 | 6.2144 | 4.3715 | 10.1768 | 12.0197 | 18.2341 | 22.6056 | 0
-5.7356 | 5.4573 | 1.6088 | 1.4132 | 1.0441 | 1.8264 | 4.0661 | 2.6529 | -0.2783 | 1.1349 | 5.201 | 7.8539 | -5.7356 | 5.4573 | 1.6188 | 1.4132 | 1.0441 | 1.8264 | 4.0661 | 2.6529 | -0.2783 | 1.1349 | 5.201 | 7.8539 | 0
-0.24152 | 6.6477 | 1.7919 | 1.6879 | 1.9597 | 2.3758 | 5.4396 | 3.7517 | 6.4062 | 8.0941 | 13.5337 | 17.2854 | -0.24152 | 6.6477 | 1.8019 | 1.6879 | 1.9597 | 2.3758 | 5.4396 | 3.7517 | 6.4062 | 8.0941 | 13.5337 | 17.2854 | 0
-1.1184 | 6.4577 | 1.7627 | 1.6441 | 1.8136 | 2.2882 | 5.2204 | 3.5763 | 5.3393 | 6.9834 | 12.2038 | 15.7801 | -1.1184 | 6.4577 | 1.7727 | 1.6441 | 1.8136 | 2.2882 | 5.2204 | 3.5763 | 5.3393 | 6.9834 | 12.2038 | 15.7801 | 0
9.8841 | 8.8416 | 1.6146 | 2.1942 | 3.6474 | 3.3884 | 7.971 | 5.7768 | 18.7257 | 20.9199 | 28.891 | 34.6678 | 9.8841 | 8.8416 | 1.6246 | 2.1942 | 3.6474 | 3.3884 | 7.971 | 5.7768 | 18.7257 | 20.9199 | 28.891 | 34.6678 | 0
-5.5634 | 5.4946 | 1.9328 | 1.4218 | 1.0728 | 1.8437 | 4.1091 | 2.6873 | -0.068833 | 1.353 | 5.4621 | 8.1495 | -5.5634 | 5.4946 | 1.9428 | 1.4218 | 1.0728 | 1.8437 | 4.1091 | 2.6873 | -0.068833 | 1.353 | 5.4621 | 8.1495 | 0
3.9837 | 7.5631 | 2.3331 | 1.8992 | 2.6639 | 2.7984 | 6.4959 | 4.5967 | 11.5468 | 13.446 | 19.9419 | 24.5386 | 3.9837 | 7.5631 | 2.3431 | 1.8992 | 2.6639 | 2.7984 | 6.4959 | 4.5967 | 11.5468 | 13.446 | 19.9419 | 24.5386 | 0
15.9941 | 10.1654 | 1.7859 | 2.4997 | 4.6657 | 3.9994 | 9.4985 | 6.9988 | 26.1595 | 28.6592 | 38.1577 | 45.1566 | 15.9941 | 10.1654 | 1.7959 | 2.4997 | 4.6657 | 3.9994 | 9.4985 | 6.9988 | 26.1595 | 28.6592 | 38.1577 | 45.1566 | 0
-0.42261 | 6.6084 | 1.794 | 1.6789 | 1.9296 | 2.3577 | 5.3943 | 3.7155 | 6.1858 | 7.8647 | 13.259 | 16.9745 | -0.42261 | 6.6084 | 1.804 | 1.6789 | 1.9296 | 2.3577 | 5.3943 | 3.7155 | 6.1858 | 7.8647 | 13.259 | 16.9745 | 0
-0.18131 | 6.6607 | 1.9908 | 1.6909 | 1.9698 | 2.3819 | 5.4547 | 3.7637 | 6.4794 | 8.1703 | 13.625 | 17.3887 | -0.18131 | 6.6607 | 2.0008 | 1.6909 | 1.9698 | 2.3819 | 5.4547 | 3.7637 | 6.4794 | 8.1703 | 13.625 | 17.3887 | 0
5.7226 | 7.9399 | 2.0474 | 1.9861 | 2.9538 | 2.9723 | 6.9306 | 4.9445 | 13.6625 | 15.6486 | 22.5792 | 27.5238 | 5.7226 | 7.9399 | 2.0574 | 1.9861 | 2.9538 | 2.9723 | 6.9306 | 4.9445 | 13.6625 | 15.6486 | 22.5792 | 27.5238 | 0
7.4208 | 8.3078 | 2.0177 | 2.071 | 3.2368 | 3.1421 | 7.3552 | 5.2842 | 15.7286 | 17.7997 | 25.1549 | 30.439 | 7.4208 | 8.3078 | 2.0277 | 2.071 | 3.2368 | 3.1421 | 7.3552 | 5.2842 | 15.7286 | 17.7997 | 25.1549 | 30.439 | 0
6.5317 | 8.1152 | 2.2316 | 2.0266 | 3.0886 | 3.0532 | 7.1329 | 5.1063 | 14.6469 | 16.6735 | 23.8064 | 28.9127 | 6.5317 | 8.1152 | 2.2416 | 2.0266 | 3.0886 | 3.0532 | 7.1329 | 5.1063 | 14.6469 | 16.6735 | 23.8064 | 28.9127 | 0
12.9487 | 9.5056 | 2.2484 | 2.3474 | 4.1581 | 3.6949 | 8.7372 | 6.3897 | 22.4543 | 24.8017 | 33.5389 | 39.9286 | 12.9487 | 9.5056 | 2.2584 | 2.3474 | 4.1581 | 3.6949 | 8.7372 | 6.3897 | 22.4543 | 24.8017 | 33.5389 | 39.9286 | 0
13.4512 | 9.6144 | 1.8607 | 2.3726 | 4.2419 | 3.7451 | 8.8628 | 6.4902 | 23.0656 | 25.4382 | 34.301 | 40.7912 | 13.4512 | 9.6144 | 1.8707 | 2.3726 | 4.2419 | 3.7451 | 8.8628 | 6.4902 | 23.0656 | 25.4382 | 34.301 | 40.7912 | 0
1.8217 | 7.0947 | 2.0947 | 1.7911 | 2.3036 | 2.5822 | 5.9554 | 4.1643 | 8.9164 | 10.7075 | 16.6629 | 20.8272 | 1.8217 | 7.0947 | 2.1047 | 1.7911 | 2.3036 | 2.5822 | 5.9554 | 4.1643 | 8.9164 | 10.7075 | 16.6629 | 20.8272 | 0
8.8397 | 8.6153 | 1.8922 | 2.142 | 3.4733 | 3.284 | 7.7099 | 5.5679 | 17.455 | 19.597 | 27.3069 | 32.8748 | 8.8397 | 8.6153 | 1.9022 | 2.142 | 3.4733 | 3.284 | 7.7099 | 5.5679 | 17.455 | 19.597 | 27.3069 | 32.8748 | 0
2.7666 | 7.2994 | 2.0757 | 1.8383 | 2.4611 | 2.6767 | 6.1916 | 4.3533 | 10.066 | 11.9043 | 18.0959 | 22.4493 | 2.7666 | 7.2994 | 2.0857 | 1.8383 | 2.4611 | 2.6767 | 6.1916 | 4.3533 | 10.066 | 11.9043 | 18.0959 | 22.4493 | 0
8.2722 | 8.4923 | 1.8633 | 2.1136 | 3.3787 | 3.2272 | 7.568 | 5.4544 | 16.7645 | 18.8781 | 26.4461 | 31.9006 | 8.2722 | 8.4923 | 1.8733 | 2.1136 | 3.3787 | 3.2272 | 7.568 | 5.4544 | 16.7645 | 18.8781 | 26.4461 | 31.9006 | 0
1.8989 | 7.1114 | 2.0766 | 1.7949 | 2.3165 | 2.5899 | 5.9747 | 4.1798 | 9.0103 | 10.8052 | 16.7799 | 20.9597 | 1.8989 | 7.1114 | 2.0866 | 1.7949 | 2.3165 | 2.5899 | 5.9747 | 4.1798 | 9.0103 | 10.8052 | 16.7799 | 20.9597 | 0
8.2977 | 8.4978 | 2.1503 | 2.1149 | 3.3829 | 3.2298 | 7.5744 | 5.4595 | 16.7955 | 18.9104 | 26.4848 | 31.9444 | 8.2977 | 8.4978 | 2.1603 | 2.1149 | 3.3829 | 3.2298 | 7.5744 | 5.4595 | 16.7955 | 18.9104 | 26.4848 | 31.9444 | 0
10.5101 | 8.9772 | 2.0598 | 2.2255 | 3.7517 | 3.451 | 8.1275 | 5.902 | 19.4873 | 21.7128 | 29.8404 | 35.7424 | 10.5101 | 8.9772 | 2.0698 | 2.2255 | 3.7517 | 3.451 | 8.1275 | 5.902 | 19.4873 | 21.7128 | 29.8404 | 35.7424 | 0
7.7932 | 8.3885 | 2.4427 | 2.0897 | 3.2989 | 3.1793 | 7.4483 | 5.3586 | 16.1817 | 18.2714 | 25.7197 | 31.0784 | 7.7932 | 8.3885 | 2.4527 | 2.0897 | 3.2989 | 3.1793 | 7.4483 | 5.3586 | 16.1817 | 18.2714 | 25.7197 | 31.0784 | 0
19.2796 | 10.8773 | 1.7714 | 2.664 | 5.2133 | 4.328 | 10.3199 | 7.6559 | 30.1569 | 32.8209 | 43.1408 | 50.7967 | 19.2796 | 10.8773 | 1.7814 | 2.664 | 5.2133 | 4.328 | 10.3199 | 7.6559 | 30.1569 | 32.8209 | 43.1408 | 50.7967 | 0
-0.85792 | 6.5141 | 1.9787 | 1.6571 | 1.857 | 2.3142 | 5.2855 | 3.6284 | 5.6562 | 7.3133 | 12.5988 | 16.2272 | -0.85792 | 6.5141 | 1.9887 | 1.6571 | 1.857 | 2.3142 | 5.2855 | 3.6284 | 5.6562 | 7.3133 | 12.5988 | 16.2272 | 0
5.3618 | 7.8617 | 2.1086 | 1.9681 | 2.8936 | 2.9362 | 6.8405 | 4.8724 | 13.2236 | 15.1917 | 22.0321 | 26.9045 | 5.3618 | 7.8617 | 2.1186 | 1.9681 | 2.8936 | 2.9362 | 6.8405 | 4.8724 | 13.2236 | 15.1917 | 22.0321 | 26.9045 | 0
9.2577 | 8.7058 | 2.1426 | 2.1629 | 3.543 | 3.3258 | 7.8144 | 5.6515 | 17.9635 | 20.1264 | 27.9408 | 33.5924 | 9.2577 | 8.7058 | 2.1526 | 2.1629 | 3.543 | 3.3258 | 7.8144 | 5.6515 | 17.9635 | 20.1264 | 27.9408 | 33.5924 | 0
10.2787 | 8.9271 | 2.2081 | 2.2139 | 3.7131 | 3.4279 | 8.0697 | 5.8557 | 19.2058 | 21.4197 | 29.4894 | 35.3451 | 10.2787 | 8.9271 | 2.2181 | 2.2139 | 3.7131 | 3.4279 | 8.0697 | 5.8557 | 19.2058 | 21.4197 | 29.4894 | 35.3451 | 0
12.2433 | 9.3527 | 1.7133 | 2.3122 | 4.0406 | 3.6243 | 8.5608 | 6.2487 | 21.5961 | 23.9082 | 32.4691 | 38.7177 | 12.2433 | 9.3527 | 1.7233 | 2.3122 | 4.0406 | 3.6243 | 8.5608 | 6.2487 | 21.5961 | 23.9082 | 32.4691 | 38.7177 | 0
-2.602 | 6.1362 | 2.0305 | 1.5699 | 1.5663 | 2.1398 | 4.8495 | 3.2796 | 3.5343 | 5.1042 | 9.9537 | 13.2333 | -2.602 | 6.1362 | 2.0405 | 1.5699 | 1.5663 | 2.1398 | 4.8495 | 3.2796 | 3.5343 | 5.1042 | 9.9537 | 13.2333 | 0
6.9152 | 8.1983 | 1.9055 | 2.0458 | 3.1525 | 3.0915 | 7.2288 | 5.183 | 15.1135 | 17.1593 | 24.3881 | 29.5711 | 6.9152 | 8.1983 | 1.9155 | 2.0458 | 3.1525 | 3.0915 | 7.2288 | 5.183 | 15.1135 | 17.1593 | 24.3881 | 29.5711 | 0
3.1651 | 7.3858 | 2.0144 | 1.8583 | 2.5275 | 2.7165 | 6.2913 | 4.433 | 10.5509 | 12.4091 | 18.7004 | 23.1334 | 3.1651 | 7.3858 | 2.0244 | 1.8583 | 2.5275 | 2.7165 | 6.2913 | 4.433 | 10.5509 | 12.4091 | 18.7004 | 23.1334 | 0
6.4306 | 8.0933 | 1.864 | 2.0215 | 3.0718 | 3.0431 | 7.1076 | 5.0861 | 14.5239 | 16.5454 | 23.653 | 28.7391 | 6.4306 | 8.0933 | 1.874 | 2.0215 | 3.0718 | 3.0431 | 7.1076 | 5.0861 | 14.5239 | 16.5454 | 23.653 | 28.7391 | 0
1.919 | 7.1158 | 1.9736 | 1.7959 | 2.3198 | 2.5919 | 5.9797 | 4.1838 | 9.0347 | 10.8307 | 16.8104 | 20.9942 | 1.919 | 7.1158 | 1.9836 | 1.7959 | 2.3198 | 2.5919 | 5.9797 | 4.1838 | 9.0347 | 10.8307 | 16.8104 | 20.9942 | 0
5.2075 | 7.8283 | 1.9672 | 1.9604 | 2.8679 | 2.9207 | 6.8019 | 4.8415 | 13.0358 | 14.9962 | 21.798 | 26.6395 | 5.2075 | 7.8283 | 1.9772 | 1.9604 | 2.8679 | 2.9207 | 6.8019 | 4.8415 | 13.0358 | 14.9962 | 21.798 | 26.6395 | 0
5.0148 | 7.7865 | 1.9804 | 1.9507 | 2.8358 | 2.9015 | 6.7537 | 4.803 | 12.8013 | 14.7521 | 21.5058 | 26.3087 | 5.0148 | 7.7865 | 1.9904 | 1.9507 | 2.8358 | 2.9015 | 6.7537 | 4.803 | 12.8013 | 14.7521 | 21.5058 | 26.3087 | 0
5.4118 | 7.8725 | 1.82 | 1.9706 | 2.902 | 2.9412 | 6.8529 | 4.8824 | 13.2843 | 15.2549 | 22.1078 | 26.9902 | 5.4118 | 7.8725 | 1.83 | 1.9706 | 2.902 | 2.9412 | 6.8529 | 4.8824 | 13.2843 | 15.2549 | 22.1078 | 26.9902 | 0
0.60033 | 6.8301 | 2.1284 | 1.73 | 2.1001 | 2.46 | 5.6501 | 3.9201 | 7.4304 | 9.1604 | 14.8105 | 18.7306 | 0.60033 | 6.8301 | 2.1384 | 1.73 | 2.1001 | 2.46 | 5.6501 | 3.9201 | 7.4304 | 9.1604 | 14.8105 | 18.7306 | 0
9.8505 | 8.8343 | 1.9956 | 2.1925 | 3.6418 | 3.3851 | 7.9626 | 5.7701 | 18.6848 | 20.8773 | 28.84 | 34.6101 | 9.8505 | 8.8343 | 2.0056 | 2.1925 | 3.6418 | 3.3851 | 7.9626 | 5.7701 | 18.6848 | 20.8773 | 28.84 | 34.6101 | 0
5.8682 | 7.9714 | 1.8458 | 1.9934 | 2.978 | 2.9868 | 6.9671 | 4.9736 | 13.8396 | 15.8331 | 22.8001 | 27.7737 | 5.8682 | 7.9714 | 1.8558 | 1.9934 | 2.978 | 2.9868 | 6.9671 | 4.9736 | 13.8396 | 15.8331 | 22.8001 | 27.7737 | 0
1.3746 | 6.9978 | 2.3455 | 1.7687 | 2.2291 | 2.5375 | 5.8436 | 4.0749 | 8.3724 | 10.1411 | 15.9848 | 20.0597 | 1.3746 | 6.9978 | 2.3555 | 1.7687 | 2.2291 | 2.5375 | 5.8436 | 4.0749 | 8.3724 | 10.1411 | 15.9848 | 20.0597 | 0
16.3663 | 10.246 | 2.1493 | 2.5183 | 4.7277 | 4.0366 | 9.5916 | 7.0733 | 26.6123 | 29.1306 | 38.7222 | 45.7954 | 16.3663 | 10.246 | 2.1593 | 2.5183 | 4.7277 | 4.0366 | 9.5916 | 7.0733 | 26.6123 | 29.1306 | 38.7222 | 45.7954 | 0
10.4785 | 8.9703 | 2.2881 | 2.2239 | 3.7464 | 3.4479 | 8.1196 | 5.8957 | 19.4488 | 21.6728 | 29.7924 | 35.6881 | 10.4785 | 8.9703 | 2.2981 | 2.2239 | 3.7464 | 3.4479 | 8.1196 | 5.8957 | 19.4488 | 21.6728 | 29.7924 | 35.6881 | 0
14.6431 | 9.8727 | 2.1757 | 2.4322 | 4.4405 | 3.8643 | 9.1608 | 6.7286 | 24.5157 | 26.9479 | 36.1087 | 42.8373 | 14.6431 | 9.8727 | 2.1857 | 2.4322 | 4.4405 | 3.8643 | 9.1608 | 6.7286 | 24.5157 | 26.9479 | 36.1087 | 42.8373 | 0
11.2705 | 9.1419 | 1.6904 | 2.2635 | 3.8784 | 3.5271 | 8.3176 | 6.0541 | 20.4125 | 22.676 | 30.9936 | 37.0477 | 11.2705 | 9.1419 | 1.7004 | 2.2635 | 3.8784 | 3.5271 | 8.3176 | 6.0541 | 20.4125 | 22.676 | 30.9936 | 37.0477 | 0
-3.2871 | 5.9878 | 1.9339 | 1.5356 | 1.4522 | 2.0713 | 4.6782 | 3.1426 | 2.7008 | 4.2364 | 8.9146 | 12.0572 | -3.2871 | 5.9878 | 1.9439 | 1.5356 | 1.4522 | 2.0713 | 4.6782 | 3.1426 | 2.7008 | 4.2364 | 8.9146 | 12.0572 | 0
4.0163 | 7.5702 | 1.9562 | 1.9008 | 2.6694 | 2.8016 | 6.5041 | 4.6033 | 11.5865 | 13.4873 | 19.9914 | 24.5946 | 4.0163 | 7.5702 | 1.9662 | 1.9008 | 2.6694 | 2.8016 | 6.5041 | 4.6033 | 11.5865 | 13.4873 | 19.9914 | 24.5946 | 0
4.6864 | 7.7154 | 1.8488 | 1.9343 | 2.7811 | 2.8686 | 6.6716 | 4.7373 | 12.4018 | 14.3361 | 21.0078 | 25.745 | 4.6864 | 7.7154 | 1.8588 | 1.9343 | 2.7811 | 2.8686 | 6.6716 | 4.7373 | 12.4018 | 14.3361 | 21.0078 | 25.745 | 0
1.4634 | 7.0171 | 1.7742 | 1.7732 | 2.2439 | 3.5791 | 5.8659 | 4.0927 | 8.4805 | 10.2536 | 16.1195 | 20.2122 | 1.4634 | 7.0171 | 1.7842 | 1.7732 | 2.2439 | 3.5791 | 5.8659 | 4.0927 | 8.4805 | 10.2536 | 16.1195 | 20.2122 | 0
-0.77368 | 6.5324 | 2.193 | 1.6613 | 1.8711 | 1.6857 | 5.3066 | 3.6453 | 5.7587 | 7.42 | 12.7266 | 16.3718 | -0.77368 | 6.5324 | 2.203 | 1.6613 | 1.8711 | 1.6857 | 5.3066 | 3.6453 | 5.7587 | 7.42 | 12.7266 | 16.3718 | 0
11.7905 | 9.2546 | 1.5619 | 2.2895 | 3.9651 | 2.9119 | 8.4476 | 6.1581 | 21.0451 | 23.3346 | 31.7823 | 37.9404 | 11.7905 | 9.2546 | 1.5719 | 2.2895 | 3.9651 | 2.9119 | 8.4476 | 6.1581 | 21.0451 | 23.3346 | 31.7823 | 37.9404 | 0
-7.1426 | 5.1524 | 1.9706 | 1.3429 | 0.80957 | 3.4348 | 3.7144 | 2.3715 | -1.9901 | -0.64725 | 3.5972 | 5.9687 | -7.1426 | 5.1524 | 1.9806 | 1.3429 | 0.80957 | 3.4348 | 3.7144 | 2.3715 | -1.9901 | -0.64725 | 3.5972 | 5.9687 | 0
5.1192 | 7.8092 | 2.1449 | 1.956 | 2.8532 | 3.9823 | 6.7798 | 4.8238 | 12.9284 | 14.8844 | 21.7198 | 26.5437 | 5.1192 | 7.8092 | 2.1549 | 1.956 | 2.8532 | 3.9823 | 6.7798 | 4.8238 | 12.9284 | 14.8844 | 21.7198 | 26.5437 | 0
10.3484 | 8.9421 | 2.3274 | 2.2174 | 3.7247 | 2.3004 | 8.0871 | 5.8697 | 19.2905 | 21.5079 | 29.595 | 35.4647 | 10.3484 | 8.9421 | 2.3374 | 2.2174 | 3.7247 | 2.3004 | 8.0871 | 5.8697 | 19.2905 | 21.5079 | 29.595 | 35.4647 | 0
15.8226 | 10.1282 | 1.7668 | 2.4911 | 4.6371 | 1.4393 | 9.4556 | 6.9645 | 25.9508 | 28.442 | 37.8976 | 44.8621 | 15.8226 | 10.1282 | 1.7768 | 2.4911 | 4.6371 | 1.4393 | 9.4556 | 6.9645 | 25.9508 | 28.442 | 37.8976 | 44.8621 | 0
-0.99638 | 6.4841 | 1.4798 | 1.6502 | 1.8339 | 2.1554 | 5.2509 | 3.6007 | 5.4877 | 7.1379 | 12.3888 | 15.9895 | -0.99638 | 6.4841 | 1.4898 | 1.6502 | 1.8339 | 2.1554 | 5.2509 | 3.6007 | 5.4877 | 7.1379 | 12.3888 | 15.9895 | 0
-9.6069 | 4.6185 | 1.7185 | 1.2197 | 0.39885 | 2.5843 | 4.8886 | 1.8786 | -4.9884 | -3.7688 | 1.1198 | 2.9984 | -9.6069 | 4.6185 | 1.7285 | 1.2197 | 0.39885 | 2.5843 | 4.8886 | 1.8786 | -4.9884 | -3.7688 | 1.1198 | 2.9984 | 0
-2.4456 | 6.1701 | 1.8614 | 1.5777 | 1.5924 | 2.3528 | 5.9607 | 3.3109 | 3.7245 | 5.3022 | 11.2629 | 14.5738 | -2.4456 | 6.1701 | 1.8714 | 1.5777 | 1.5924 | 2.3528 | 5.9607 | 3.3109 | 3.7245 | 5.3022 | 11.2629 | 14.5738 | 0
1.8427 | 7.0993 | 1.7843 | 1.7921 | 2.3071 | 2.7307 | 5.3821 | 4.1685 | 8.942 | 10.7341 | 16.1162 | 20.2847 | 1.8427 | 7.0993 | 1.7943 | 1.7921 | 2.3071 | 2.7307 | 5.3821 | 4.1685 | 8.942 | 10.7341 | 16.1162 | 20.2847 | 0
-0.47175 | 6.5978 | 1.9102 | 1.6764 | 1.9214 | 2.5396 | 6.3268 | 3.7057 | 6.126 | 7.8025 | 14.1292 | 17.8349 | -0.47175 | 6.5978 | 1.9202 | 1.6764 | 1.9214 | 2.5396 | 6.3268 | 3.7057 | 6.126 | 7.8025 | 14.1292 | 17.8349 | 0
3.3071 | 7.4165 | 1.8465 | 1.7698 | 2.5512 | 2.4087 | 5.8491 | 4.4614 | 10.7236 | 12.4935 | 18.3426 | 22.804 | 3.3071 | 7.4165 | 1.8565 | 1.7698 | 2.5512 | 2.4087 | 5.8491 | 4.4614 | 10.7236 | 12.4935 | 18.3426 | 22.804 | 0
1.3965 | 7.0026 | 1.8029 | 1.7043 | 2.2327 | 3.3494 | 5.5217 | 4.0793 | 8.399 | 10.1034 | 15.6855 | 19.7648 | 1.3965 | 7.0026 | 1.8129 | 1.7043 | 2.2327 | 3.3494 | 5.5217 | 4.0793 | 8.399 | 10.1034 | 15.6855 | 19.7648 | 0
0.08672 | 6.7188 | 2.1165 | 2.1747 | 2.0145 | 3.9835 | 7.8734 | 3.8173 | 6.8055 | 8.9802 | 16.8536 | 20.671 | 0.08672 | 6.7188 | 2.1265 | 2.1747 | 2.0145 | 3.9835 | 7.8734 | 3.8173 | 6.8055 | 8.9802 | 16.8536 | 20.671 | 0
9.4938 | 8.757 | 2.3278 | 2.4917 | 3.5823 | 3.2911 | 9.4587 | 5.6988 | 18.2508 | 20.7425 | 30.2012 | 35.8999 | 9.4938 | 8.757 | 2.3378 | 2.4917 | 3.5823 | 3.2911 | 9.4587 | 5.6988 | 18.2508 | 20.7425 | 30.2012 | 35.8999 | 0
15.8348 | 10.1309 | 2.097 | 2.1455 | 4.6391 | 3.8318 | 7.7276 | 6.967 | 25.9657 | 28.1112 | 36.5822 | 43.5491 | 15.8348 | 10.1309 | 2.107 | 2.1455 | 4.6391 | 3.8318 | 7.7276 | 6.967 | 25.9657 | 28.1112 | 36.5822 | 43.5491 | 0
8.9106 | 8.6306 | 2.2773 | 2.4159 | 3.4851 | 2.4722 | 9.0796 | 5.5821 | 17.5412 | 19.9571 | 29.0368 | 34.6189 | 8.9106 | 8.6306 | 2.2873 | 2.4159 | 3.4851 | 2.4722 | 9.0796 | 5.5821 | 17.5412 | 19.9571 | 29.0368 | 34.6189 | 0
14.3184 | 9.8023 | 1.8241 | 1.7361 | 4.3864 | 3.1013 | 5.6806 | 6.6637 | 24.1208 | 25.8569 | 33.3446 | 40.0083 | 14.3184 | 9.8023 | 1.8341 | 1.7361 | 4.3864 | 3.1013 | 5.6806 | 6.6637 | 24.1208 | 25.8569 | 33.3446 | 40.0083 | 0
0.7224 | 6.8565 | 2.0338 | 2.0506 | 2.1204 | 4.3384 | 7.2532 | 3.9445 | 7.5789 | 9.6296 | 16.8828 | 20.8273 | 0.7224 | 6.8565 | 2.0438 | 2.0506 | 2.1204 | 4.3384 | 7.2532 | 3.9445 | 7.5789 | 9.6296 | 16.8828 | 20.8273 | 0
7.0128 | 8.2194 | 2.4461 | 2.6692 | 3.1688 | 1.3988 | 10.346 | 5.2026 | 15.2323 | 17.9015 | 28.2475 | 33.45 | 7.0128 | 8.2194 | 2.4561 | 2.6692 | 3.1688 | 1.3988 | 10.346 | 5.2026 | 15.2323 | 17.9015 | 28.2475 | 33.45 | 0
19.384 | 10.8999 | 1.4663 | 1.1994 | 5.2307 | 4.3226 | 2.9969 | 7.6768 | 30.2838 | 31.4832 | 41.0365 | 48.7133 | 19.384 | 10.8999 | 1.4763 | 1.1994 | 5.2307 | 4.3226 | 2.9969 | 7.6768 | 30.2838 | 31.4832 | 41.0365 | 48.7133 | 0
19.2262 | 4.5307 | 2.4409 | 2.6613 | 0.33129 | 3.8214 | 10.3065 | 1.7975 | 23.7568 | 26.4181 | 36.7247 | 38.5222 | 19.2262 | 4.5307 | 2.4509 | 2.6613 | 0.33129 | 3.8214 | 10.3065 | 1.7975 | 23.7568 | 26.4181 | 36.7247 | 38.5222 | 0
14.2142 | 10.8657 | 2.2738 | 2.4107 | 5.2044 | 2.1505 | 9.0535 | 7.6452 | 25.0798 | 27.4905 | 36.5441 | 44.1893 | 14.2142 | 10.8657 | 2.2838 | 2.4107 | 5.2044 | 2.1505 | 9.0535 | 7.6452 | 25.0798 | 27.4905 | 36.5441 | 44.1893 | 0
-2.4952 | 9.7797 | 1.7168 | 1.5752 | 4.369 | 3.5234 | 4.8762 | 6.6428 | 7.2846 | 8.8598 | 16.7522 | 23.395 | -2.4952 | 9.7797 | 1.7268 | 1.5752 | 4.369 | 3.5234 | 4.8762 | 6.6428 | 7.2846 | 8.8598 | 16.7522 | 23.395 | 0
11.2336 | 6.1594 | 2.1745 | 2.2617 | 1.5841 | 4.0163 | 8.3084 | 3.301 | 17.393 | 19.6547 | 27.9631 | 31.2641 | 11.2336 | 6.1594 | 2.1845 | 2.2617 | 1.5841 | 4.0163 | 8.3084 | 3.301 | 17.393 | 19.6547 | 27.9631 | 31.2641 | 0
16.1635 | 9.134 | 2.3388 | 2.5082 | 3.8723 | 2.7069 | 9.5409 | 6.0467 | 25.2974 | 27.8056 | 37.3465 | 43.3932 | 16.1635 | 9.134 | 2.3488 | 2.5082 | 3.8723 | 2.7069 | 9.5409 | 6.0467 | 25.2974 | 27.8056 | 37.3465 | 43.3932 | 0
3.0691 | 10.2021 | 1.9023 | 1.8535 | 4.2369 | 3.7422 | 6.2673 | 7.0327 | 13.2711 | 15.1246 | 23.1037 | 30.1364 | 3.0691 | 10.2021 | 1.9123 | 1.8535 | 4.2369 | 3.7422 | 6.2673 | 7.0327 | 13.2711 | 15.1246 | 23.1037 | 30.1364 | 0
13.4216 | 7.365 | 2.2474 | 2.3711 | 4.3798 | 3.8279 | 8.8554 | 4.4138 | 20.7866 | 23.1577 | 32.0131 | 36.4269 | 13.4216 | 7.365 | 2.2574 | 2.3711 | 4.3798 | 3.8279 | 8.8554 | 4.4138 | 20.7866 | 23.1577 | 32.0131 | 36.4269 | 0
14.2791 | 9.608 | 2.276 | 2.414 | 2.4376 | 2.6625 | 9.0698 | 6.4843 | 23.8871 | 26.301 | 35.3708 | 41.8551 | 14.2791 | 9.608 | 2.286 | 2.414 | 2.4376 | 2.6625 | 9.0698 | 6.4843 | 23.8871 | 26.301 | 35.3708 | 41.8551 | 0
2.6253 | 9.7938 | 1.8875 | 1.8313 | 0.72184 | 1.6331 | 6.1563 | 6.6558 | 12.4191 | 14.2504 | 20.4067 | 27.0625 | 2.6253 | 9.7938 | 1.8975 | 1.8313 | 0.72184 | 1.6331 | 6.1563 | 6.6558 | 12.4191 | 14.2504 | 20.4067 | 27.0625 | 0
-7.6689 | 7.2688 | 1.5444 | 1.3166 | 4.3164 | 3.7899 | 3.5828 | 4.3251 | -0.40013 | 0.91643 | 9.0227 | 13.3478 | -7.6689 | 7.2688 | 1.5544 | 1.3166 | 4.3164 | 3.7899 | 3.5828 | 4.3251 | -0.40013 | 0.91643 | 9.0227 | 13.3478 | 0
13.8987 | 5.0384 | 2.2633 | 2.3949 | 4.5377 | 3.9226 | 8.9747 | 2.2662 | 18.9371 | 21.332 | 30.3067 | 32.5729 | 13.8987 | 5.0384 | 2.2733 | 2.3949 | 4.5377 | 3.9226 | 8.9747 | 2.2662 | 18.9371 | 21.332 | 30.3067 | 32.5729 | 0
15.2263 | 9.7114 | 2.3075 | 2.4613 | 5.1783 | 4.307 | 9.3066 | 6.5797 | 24.9377 | 27.399 | 36.8844 | 43.4641 | 15.2263 | 9.7114 | 2.3175 | 2.4613 | 5.1783 | 4.307 | 9.3066 | 6.5797 | 24.9377 | 27.399 | 36.8844 | 43.4641 | 0
19.0701 | 9.999 | 2.4357 | 2.6535 | 1.7349 | 2.2409 | 10.2675 | 6.8453 | 29.0691 | 31.7226 | 41.9902 | 48.8354 | 19.0701 | 9.999 | 2.4457 | 2.6535 | 1.7349 | 2.2409 | 10.2675 | 6.8453 | 29.0691 | 31.7226 | 41.9902 | 48.8354 | 0
-1.5907 | 10.8319 | 1.747 | 1.6205 | 3.4667 | 3.28 | 5.1023 | 7.614 | 9.2411 | 10.8616 | 17.6083 | 25.2223 | -1.5907 | 10.8319 | 1.757 | 1.6205 | 3.4667 | 3.28 | 5.1023 | 7.614 | 9.2411 | 10.8616 | 17.6083 | 25.2223 | 0
8.8001 | 6.3553 | 2.0933 | 2.14 | 3.3661 | 3.2197 | 7.7 | 3.4819 | 15.1554 | 17.2954 | 24.9955 | 28.4773 | 8.8001 | 6.3553 | 2.1033 | 2.14 | 3.3661 | 3.2197 | 7.7 | 3.4819 | 15.1554 | 17.2954 | 24.9955 | 28.4773 | 0
8.1966 | 8.6067 | 2.0732 | 2.1098 | 2.9229 | 2.9538 | 7.5492 | 5.56 | 16.8033 | 18.9131 | 26.4623 | 32.0223 | 8.1966 | 8.6067 | 2.0832 | 2.1098 | 2.9229 | 2.9538 | 7.5492 | 5.56 | 16.8033 | 18.9131 | 26.4623 | 32.0223 | 0
5.5376 | 8.4759 | 1.9846 | 1.9769 | 2.3602 | 2.6161 | 6.8844 | 5.4393 | 14.0135 | 15.9904 | 22.8748 | 28.3141 | 5.5376 | 8.4759 | 1.9946 | 1.9769 | 2.3602 | 2.6161 | 6.8844 | 5.4393 | 14.0135 | 15.9904 | 22.8748 | 28.3141 | 0
2.1614 | 7.8998 | 1.872 | 1.8081 | 2.489 | 2.6934 | 6.0403 | 4.9075 | 10.0612 | 11.8692 | 17.9096 | 22.8171 | 2.1614 | 7.8998 | 1.882 | 1.8081 | 2.489 | 2.6934 | 6.0403 | 4.9075 | 10.0612 | 11.8692 | 17.9096 | 22.8171 | 0
2.9341 | 7.1683 | 1.8978 | 1.8467 | 3.9122 | 3.5473 | 6.2335 | 4.2323 | 10.1024 | 11.9491 | 19.4087 | 23.641 | 2.9341 | 7.1683 | 1.9078 | 1.8467 | 3.9122 | 3.5473 | 6.2335 | 4.2323 | 10.1024 | 11.9491 | 19.4087 | 23.641 | 0
11.4734 | 7.3357 | 2.1824 | 2.2737 | 4.5221 | 3.9133 | 8.3684 | 4.3868 | 18.8092 | 21.0828 | 29.5182 | 33.9051 | 11.4734 | 7.3357 | 2.1924 | 2.2737 | 4.5221 | 3.9133 | 8.3684 | 4.3868 | 18.8092 | 21.0828 | 29.5182 | 33.9051 | 0
15.1327 | 9.1859 | 2.3044 | 2.4566 | 3.0515 | 3.0309 | 9.2832 | 6.0947 | 24.3186 | 26.7752 | 36.0584 | 42.1531 | 15.1327 | 9.1859 | 2.3144 | 2.4566 | 3.0515 | 3.0309 | 9.2832 | 6.0947 | 24.3186 | 26.7752 | 36.0584 | 42.1531 | 0
6.309 | 9.9788 | 2.0103 | 2.0154 | 3.3918 | 3.2351 | 7.0772 | 6.8265 | 16.2877 | 18.3032 | 25.3804 | 32.207 | 6.309 | 9.9788 | 2.0203 | 2.0154 | 3.3918 | 3.2351 | 7.0772 | 6.8265 | 16.2877 | 18.3032 | 25.3804 | 32.207 | 0
8.3508 | 8.0669 | 2.0784 | 2.1175 | 3.9998 | 3.5999 | 7.5877 | 5.0618 | 16.4178 | 18.5353 | 26.135 | 31.1968 | 8.3508 | 8.0669 | 2.0884 | 2.1175 | 3.9998 | 3.5999 | 7.5877 | 5.0618 | 16.4178 | 18.5353 | 26.135 | 31.1968 | 0
11.9988 | 8.5093 | 2.2 | 2.2999 | 3.3774 | 3.2265 | 8.4997 | 5.4702 | 20.5081 | 22.808 | 31.3077 | 36.7779 | 11.9988 | 8.5093 | 2.21 | 2.2999 | 3.3774 | 3.2265 | 8.4997 | 5.4702 | 20.5081 | 22.808 | 31.3077 | 36.7779 | 0
8.2645 | 9.2997 | 2.0755 | 2.1132 | 2.4958 | 2.6975 | 7.5661 | 6.1998 | 17.5643 | 19.6775 | 27.2436 | 33.4434 | 8.2645 | 9.2997 | 2.0855 | 2.1132 | 2.4958 | 2.6975 | 7.5661 | 6.1998 | 17.5643 | 19.6775 | 27.2436 | 33.4434 | 0
2.9748 | 8.4906 | 1.8992 | 1.8487 | 3.6696 | 3.4018 | 6.2437 | 5.4529 | 11.4654 | 13.3142 | 20.3856 | 25.8385 | 2.9748 | 8.4906 | 1.9092 | 1.8487 | 3.6696 | 3.4018 | 6.2437 | 5.4529 | 11.4654 | 13.3142 | 20.3856 | 25.8385 | 0
10.0178 | 7.3445 | 2.1339 | 2.2009 | 2.3627 | 2.6176 | 8.0044 | 4.395 | 17.3623 | 19.5632 | 27.5677 | 31.9626 | 10.0178 | 7.3445 | 2.1439 | 2.2009 | 2.3627 | 2.6176 | 8.0044 | 4.395 | 17.3623 | 19.5632 | 27.5677 | 31.9626 | 0
2.1761 | 8.8705 | 1.8725 | 1.8088 | 3.6992 | 3.4195 | 6.044 | 5.8036 | 11.0466 | 12.8554 | 19.9742 | 25.7777 | 2.1761 | 8.8705 | 1.8825 | 1.8088 | 3.6992 | 3.4195 | 6.044 | 5.8036 | 11.0466 | 12.8554 | 19.9742 | 25.7777 | 0
10.1953 | 7.1715 | 2.1398 | 2.2098 | 2.0614 | 2.4368 | 8.0488 | 4.2352 | 17.3668 | 19.5765 | 27.6253 | 31.8606 | 10.1953 | 7.1715 | 2.1498 | 2.2098 | 2.0614 | 2.4368 | 8.0488 | 4.2352 | 17.3668 | 19.5765 | 27.6253 | 31.8606 | 0
0.36812 | 8.909 | 1.8123 | 1.7184 | 3.4738 | 3.2843 | 5.592 | 5.8391 | 9.2771 | 10.9955 | 17.7536 | 23.5926 | 0.36812 | 8.909 | 1.8223 | 1.7184 | 3.4738 | 3.2843 | 5.592 | 5.8391 | 9.2771 | 10.9955 | 17.7536 | 23.5926 | 0
8.8428 | 6.7798 | 2.0948 | 2.1421 | 2.5607 | 2.7364 | 7.7107 | 3.8736 | 15.6225 | 17.7647 | 25.4753 | 29.349 | 8.8428 | 6.7798 | 2.1048 | 2.1421 | 2.5607 | 2.7364 | 7.7107 | 3.8736 | 15.6225 | 17.7647 | 25.4753 | 29.349 | 0
3.3639 | 8.6159 | 1.9121 | 1.8682 | 3.7195 | 3.4317 | 6.341 | 5.5686 | 11.9799 | 13.8481 | 20.9992 | 26.5678 | 3.3639 | 8.6159 | 1.9221 | 1.8682 | 3.7195 | 3.4317 | 6.341 | 5.5686 | 11.9799 | 13.8481 | 20.9992 | 26.5678 | 0
10.3169 | 7.4289 | 2.1439 | 2.2158 | 4.0749 | 3.645 | 8.0792 | 4.4728 | 17.7457 | 19.9616 | 28.0408 | 32.5136 | 10.3169 | 7.4289 | 2.1539 | 2.2158 | 4.0749 | 3.645 | 8.0792 | 4.4728 | 17.7457 | 19.9616 | 28.0408 | 32.5136 | 0
12.4496 | 8.9353 | 2.215 | 2.3225 | 3.8485 | 3.5091 | 8.6124 | 5.8634 | 21.3849 | 23.7074 | 32.3198 | 38.1832 | 12.4496 | 8.9353 | 2.225 | 2.3225 | 3.8485 | 3.5091 | 8.6124 | 5.8634 | 21.3849 | 23.7074 | 32.3198 | 38.1832 | 0
11.0913 | 9.3974 | 2.1697 | 2.2546 | 1.6992 | 2.2195 | 8.2728 | 6.2899 | 20.4887 | 22.7433 | 31.0161 | 37.306 | 11.0913 | 9.3974 | 2.1797 | 2.2546 | 1.6992 | 2.2195 | 8.2728 | 6.2899 | 20.4887 | 22.7433 | 31.0161 | 37.306 | 0
-1.8049 | 9.1031 | 1.7398 | 1.6098 | 3.2226 | 3.1336 | 5.0488 | 6.0183 | 7.2982 | 8.908 | 15.2642 | 21.2824 | -1.8049 | 9.1031 | 1.7498 | 1.6098 | 3.2226 | 3.1336 | 5.0488 | 6.0183 | 7.2982 | 8.908 | 15.2642 | 21.2824 | 0
7.3357 | 6.3089 | 2.0445 | 2.0668 | 4.1585 | 3.6951 | 7.3339 | 3.439 | 13.6446 | 15.7114 | 23.565 | 27.004 | 7.3357 | 6.3089 | 2.0545 | 2.0668 | 4.1585 | 3.6951 | 7.3339 | 3.439 | 13.6446 | 15.7114 | 23.565 | 27.004 | 0
12.9509 | 8.2894 | 2.2317 | 2.3475 | 1.8244 | 2.2947 | 8.7377 | 5.2671 | 21.2403 | 23.5878 | 32.3255 | 37.5927 | 12.9509 | 8.2894 | 2.2417 | 2.3475 | 1.8244 | 2.2947 | 8.7377 | 5.2671 | 21.2403 | 23.5878 | 32.3255 | 37.5927 | 0
-1.0534 | 9.506 | 1.7649 | 1.6473 | 4.1219 | 3.6732 | 5.2366 | 6.3902 | 8.4526 | 10.0999 | 17.895 | 24.2852 | -1.0534 | 9.506 | 1.7749 | 1.6473 | 4.1219 | 3.6732 | 5.2366 | 6.3902 | 8.4526 | 10.0999 | 17.895 | 24.2852 | 0
12.7317 | 6.4718 | 2.2244 | 2.3366 | 2.2937 | 2.5762 | 8.6829 | 3.5893 | 19.2034 | 21.54 | 30.2229 | 33.8122 | 12.7317 | 6.4718 | 2.2344 | 2.3366 | 2.2937 | 2.5762 | 8.6829 | 3.5893 | 19.2034 | 21.54 | 30.2229 | 33.8122 | 0
1.7625 | 9.4585 | 1.8587 | 1.7881 | 4.4139 | 3.8484 | 5.9406 | 6.3463 | 11.221 | 13.0091 | 21.2714 | 27.6177 | 1.7625 | 9.4585 | 1.8687 | 1.7881 | 4.4139 | 3.8484 | 5.9406 | 6.3463 | 11.221 | 13.0091 | 21.2714 | 27.6177 | 0
14.4836 | 7.0819 | 2.2828 | 2.4242 | 2.818 | 2.8908 | 9.1209 | 4.1525 | 21.5654 | 23.9896 | 33.1105 | 37.263 | 14.4836 | 7.0819 | 2.2928 | 2.4242 | 2.818 | 2.8908 | 9.1209 | 4.1525 | 21.5654 | 23.9896 | 33.1105 | 37.263 | 0
4.908 | 9.8381 | 1.9636 | 1.9454 | 4.2124 | 3.7275 | 6.727 | 6.6967 | 14.7461 | 16.6915 | 24.6314 | 31.3281 | 4.908 | 9.8381 | 1.9736 | 1.9454 | 4.2124 | 3.7275 | 6.727 | 6.6967 | 14.7461 | 16.6915 | 24.6314 | 31.3281 | 0
13.2747 | 7.7634 | 2.2425 | 2.3637 | 2.6176 | 2.7706 | 8.8187 | 4.7816 | 21.0381 | 23.4018 | 32.2205 | 37.0021 | 13.2747 | 7.7634 | 2.2525 | 2.3637 | 2.6176 | 2.7706 | 8.8187 | 4.7816 | 21.0381 | 23.4018 | 32.2205 | 37.0021 | 0
3.7058 | 9.5762 | 1.9235 | 1.8853 | 4.0942 | 3.6565 | 6.4265 | 6.4549 | 13.282 | 15.1673 | 22.9179 | 29.3729 | 3.7058 | 9.5762 | 1.9335 | 1.8853 | 4.0942 | 3.6565 | 6.4265 | 6.4549 | 13.282 | 15.1673 | 22.9179 | 29.3729 | 0
12.5649 | 7.5029 | 2.2188 | 2.3282 | 2.7136 | 2.8282 | 8.6412 | 4.5412 | 20.0678 | 22.3961 | 31.0373 | 35.5785 | 12.5649 | 7.5029 | 2.2288 | 2.3282 | 2.7136 | 2.8282 | 8.6412 | 4.5412 | 20.0678 | 22.3961 | 31.0373 | 35.5785 | 0
4.2816 | 9.4224 | 1.9427 | 1.9141 | 1.5496 | 2.1298 | 6.5704 | 6.313 | 13.704 | 15.618 | 22.1884 | 28.5014 | 4.2816 | 9.4224 | 1.9527 | 1.9141 | 1.5496 | 2.1298 | 6.5704 | 6.313 | 13.704 | 15.618 | 22.1884 | 28.5014 | 0
-2.7021 | 7.6277 | 1.7099 | 1.5649 | 4.8215 | 4.0929 | 4.8245 | 4.6563 | 4.9255 | 6.4904 | 15.4048 | 20.0611 | -2.7021 | 7.6277 | 1.7199 | 1.5649 | 4.8215 | 4.0929 | 4.8245 | 4.6563 | 4.9255 | 6.4904 | 15.4048 | 20.0611 | 0
16.9289 | 6.1145 | 2.3643 | 2.5464 | 1.5666 | 2.14 | 9.7322 | 3.2596 | 23.0434 | 25.5899 | 35.3221 | 38.5817 | 16.9289 | 6.1145 | 2.3743 | 2.5464 | 1.5666 | 2.14 | 9.7322 | 3.2596 | 23.0434 | 25.5899 | 35.3221 | 38.5817 | 0
-2.6001 | 10.3679 | 1.7133 | 1.57 | 2.43 | 2.658 | 4.85 | 7.1858 | 7.7678 | 9.3378 | 14.4258 | 21.6116 | -2.6001 | 10.3679 | 1.7233 | 1.57 | 2.43 | 2.658 | 4.85 | 7.1858 | 7.7678 | 9.3378 | 14.4258 | 21.6116 | 0
2.5801 | 6.1366 | 1.886 | 1.829 | 0.74844 | 1.6491 | 6.145 | 3.28 | 8.7168 | 10.5458 | 16.6908 | 19.9708 | 2.5801 | 6.1366 | 1.896 | 1.829 | 0.74844 | 1.6491 | 6.145 | 3.28 | 8.7168 | 10.5458 | 16.6908 | 19.9708 | 0
-7.5094 | 7.259 | 1.5497 | 1.3245 | 3.3043 | 3.1826 | 3.6227 | 4.316 | -0.25035 | 1.0742 | 7.5611 | 11.8771 | -7.5094 | 7.259 | 1.5597 | 1.3245 | 3.3043 | 3.1826 | 3.6227 | 4.316 | -0.25035 | 1.0742 | 7.5611 | 11.8771 | 0
7.826 | 5.073 | 2.0609 | 2.0913 | 0.096747 | 1.258 | 7.4565 | 2.2981 | 12.899 | 14.9903 | 22.4468 | 24.7449 | 7.826 | 5.073 | 2.0709 | 2.0913 | 0.096747 | 1.258 | 7.4565 | 2.2981 | 12.899 | 14.9903 | 22.4468 | 24.7449 | 0
-11.4195 | 8.3956 | 1.4193 | 1.129 | 1.1507 | 1.8904 | 2.6451 | 5.3652 | -3.0239 | -1.8949 | 1.1462 | 6.5114 | -11.4195 | 8.3956 | 1.4293 | 1.129 | 1.1507 | 1.8904 | 2.6451 | 5.3652 | -3.0239 | -1.8949 | 1.1462 | 6.5114 | 0
-5.0961 | 4.2258 | 1.6301 | 1.4452 | 2.318 | 2.5908 | 4.226 | 1.5161 | -0.87032 | 0.57488 | 5.4837 | 6.9998 | -5.0961 | 4.2258 | 1.6401 | 1.4452 | 2.318 | 2.5908 | 4.226 | 1.5161 | -0.87032 | 0.57488 | 5.4837 | 6.9998 | 0
1.9081 | 5.5958 | 1.8636 | 1.7954 | 3.9068 | 3.5441 | 5.977 | 2.7808 | 7.5039 | 9.2993 | 16.7502 | 19.531 | 1.9081 | 5.5958 | 1.8736 | 1.7954 | 3.9068 | 3.5441 | 5.977 | 2.7808 | 7.5039 | 9.2993 | 16.7502 | 19.531 | 0
11.4408 | 7.1134 | 2.1814 | 2.272 | 3.9987 | 3.5992 | 8.3602 | 4.1816 | 18.5542 | 20.8263 | 29.1865 | 33.3681 | 11.4408 | 7.1134 | 2.1914 | 2.272 | 3.9987 | 3.5992 | 8.3602 | 4.1816 | 18.5542 | 20.8263 | 29.1865 | 33.3681 | 0
11.9924 | 9.1788 | 2.1997 | 2.2996 | 2.5211 | 2.7127 | 8.4981 | 6.0882 | 21.1712 | 23.4708 | 31.9689 | 38.0571 | 11.9924 | 9.1788 | 2.2097 | 2.2996 | 2.5211 | 2.7127 | 8.4981 | 6.0882 | 21.1712 | 23.4708 | 31.9689 | 38.0571 | 0
3.1269 | 9.2983 | 1.9042 | 1.8563 | 2.6077 | 2.7646 | 6.2817 | 6.1985 | 12.4252 | 14.2815 | 20.5633 | 26.7617 | 3.1269 | 9.2983 | 1.9142 | 1.8563 | 2.6077 | 2.7646 | 6.2817 | 6.1985 | 12.4252 | 14.2815 | 20.5633 | 26.7617 | 0
3.646 | 7.3775 | 1.9215 | 1.8823 | 3.8705 | 3.5223 | 6.4115 | 4.4254 | 11.0234 | 12.9057 | 20.2986 | 24.724 | 3.646 | 7.3775 | 1.9315 | 1.8823 | 3.8705 | 3.5223 | 6.4115 | 4.4254 | 11.0234 | 12.9057 | 20.2986 | 24.724 | 0
11.2232 | 7.49 | 2.1741 | 2.2612 | 4.6272 | 3.9763 | 8.3058 | 4.5292 | 18.7131 | 20.9743 | 29.5778 | 34.107 | 11.2232 | 7.49 | 2.1841 | 2.2612 | 4.6272 | 3.9763 | 8.3058 | 4.5292 | 18.7131 | 20.9743 | 29.5778 | 34.107 | 0
15.7633 | 9.1317 | 2.3254 | 2.4882 | 3.3338 | 3.2003 | 9.4408 | 6.0446 | 24.895 | 27.3831 | 36.8239 | 42.8686 | 15.7633 | 9.1317 | 2.3354 | 2.4882 | 3.3338 | 3.2003 | 9.4408 | 6.0446 | 24.895 | 27.3831 | 36.8239 | 42.8686 | 0
8.0029 | 10.1154 | 2.0668 | 2.1001 | 4.3526 | 3.8116 | 7.5007 | 6.9527 | 18.1183 | 20.2185 | 28.3827 | 35.3354 | 8.0029 | 10.1154 | 2.0768 | 2.1001 | 4.3526 | 3.8116 | 7.5007 | 6.9527 | 18.1183 | 20.2185 | 28.3827 | 35.3354 | 0
14.1159 | 8.434 | 2.2705 | 2.4058 | 3.1711 | 3.1026 | 9.029 | 5.4006 | 22.5498 | 24.9556 | 33.9846 | 39.3852 | 14.1159 | 8.434 | 2.2805 | 2.4058 | 3.1711 | 3.1026 | 9.029 | 5.4006 | 22.5498 | 24.9556 | 33.9846 | 39.3852 | 0
7.0265 | 9.7584 | 2.0342 | 2.0513 | 1.0701 | 1.842 | 7.2566 | 6.6232 | 16.7849 | 18.8362 | 26.0929 | 32.716 | 7.0265 | 9.7584 | 2.0442 | 2.0513 | 1.0701 | 1.842 | 7.2566 | 6.6232 | 16.7849 | 18.8362 | 26.0929 | 32.716 | 0
-5.5795 | 8.2224 | 1.614 | 1.421 | 3.1699 | 3.1019 | 4.1051 | 5.2053 | 2.6429 | 4.0639 | 10.3358 | 15.5411 | -5.5795 | 8.2224 | 1.624 | 1.421 | 3.1699 | 3.1019 | 4.1051 | 5.2053 | 2.6429 | 4.0639 | 10.3358 | 15.5411 | 0
7.0195 | 5.4911 | 2.034 | 2.051 | 2.44 | 2.664 | 7.2549 | 2.6841 | 12.5106 | 14.5615 | 21.8164 | 24.5005 | 7.0195 | 5.4911 | 2.044 | 2.051 | 2.44 | 2.664 | 7.2549 | 2.6841 | 12.5106 | 14.5615 | 21.8164 | 24.5005 | 0
2.6398 | 8.2209 | 1.888 | 1.832 | 3.9164 | 3.5498 | 6.1599 | 5.2039 | 10.8607 | 12.6926 | 20.1589 | 25.3627 | 2.6398 | 8.2209 | 1.898 | 1.832 | 3.9164 | 3.5498 | 6.1599 | 5.2039 | 10.8607 | 12.6926 | 20.1589 | 25.3627 | 0
11.4983 | 7.272 | 2.1833 | 2.2749 | 2.2667 | 2.56 | 8.3746 | 4.328 | 18.7703 | 21.0452 | 29.4197 | 33.7477 | 11.4983 | 7.272 | 2.1933 | 2.2749 | 2.2667 | 2.56 | 8.3746 | 4.328 | 18.7703 | 21.0452 | 29.4197 | 33.7477 | 0
1.6003 | 9.1913 | 1.8533 | 1.78 | 0.78163 | 1.669 | 5.9001 | 6.0997 | 10.7916 | 12.5716 | 18.4716 | 24.5713 | 1.6003 | 9.1913 | 1.8633 | 1.78 | 0.78163 | 1.669 | 5.9001 | 6.0997 | 10.7916 | 12.5716 | 18.4716 | 24.5713 | 0
-7.3102 | 7.0467 | 1.5563 | 1.3345 | 4.619 | 3.9714 | 3.6724 | 4.1201 | -0.26348 | 1.071 | 9.6614 | 13.7815 | -7.3102 | 7.0467 | 1.5663 | 1.3345 | 4.619 | 3.9714 | 3.6724 | 4.1201 | -0.26348 | 1.071 | 9.6614 | 13.7815 | 0
15.714 | 5.1161 | 2.3238 | 2.4857 | 4.1687 | 3.7012 | 9.4285 | 2.338 | 20.8301 | 23.3158 | 32.7443 | 35.0823 | 15.714 | 5.1161 | 2.3338 | 2.4857 | 4.1687 | 3.7012 | 9.4285 | 2.338 | 20.8301 | 23.3158 | 32.7443 | 35.0823 | 0
13.0123 | 10.1047 | 2.2337 | 2.3506 | 0.93932 | 1.7636 | 8.7531 | 6.9428 | 23.117 | 25.4677 | 34.2207 | 41.1635 | 13.0123 | 10.1047 | 2.2437 | 2.3506 | 0.93932 | 1.7636 | 8.7531 | 6.9428 | 23.117 | 25.4677 | 34.2207 | 41.1635 | 0
-6.3641 | 9.5193 | 1.5879 | 1.3818 | 3.1006 | 3.0604 | 3.909 | 6.4025 | 3.1553 | 4.5371 | 10.698 | 17.1005 | -6.3641 | 9.5193 | 1.5979 | 1.3818 | 3.1006 | 3.0604 | 3.909 | 6.4025 | 3.1553 | 4.5371 | 10.698 | 17.1005 | 0
6.6035 | 5.3211 | 2.0201 | 2.0302 | 3.8656 | 3.5194 | 7.1509 | 2.5272 | 11.9246 | 13.9548 | 21.3398 | 23.867 | 6.6035 | 5.3211 | 2.0301 | 2.0302 | 3.8656 | 3.5194 | 7.1509 | 2.5272 | 11.9246 | 13.9548 | 21.3398 | 23.867 | 0
11.1936 | 8.1308 | 2.1731 | 2.2597 | 2.3992 | 2.6395 | 8.2984 | 5.1207 | 19.3244 | 21.584 | 29.8824 | 35.0031 | 11.1936 | 8.1308 | 2.1831 | 2.2597 | 2.3992 | 2.6395 | 8.2984 | 5.1207 | 19.3244 | 21.584 | 29.8824 | 35.0031 | 0
2.3952 | 9.1253 | 1.8798 | 1.8198 | 4.4598 | 3.8759 | 6.0988 | 6.0387 | 11.5205 | 13.3403 | 21.6759 | 27.7146 | 2.3952 | 9.1253 | 1.8898 | 1.8198 | 4.4598 | 3.8759 | 6.0988 | 6.0387 | 11.5205 | 13.3403 | 21.6759 | 27.7146 | 0
14.7587 | 7.219 | 2.292 | 2.4379 | 4.6718 | 4.0031 | 9.1897 | 4.279 | 21.9776 | 24.4156 | 33.6053 | 37.8843 | 14.7587 | 7.219 | 2.302 | 2.4379 | 4.6718 | 4.0031 | 9.1897 | 4.279 | 21.9776 | 24.4156 | 33.6053 | 37.8843 | 0
16.0308 | 9.8977 | 2.3344 | 2.5015 | 2.5827 | 2.7496 | 9.5077 | 6.7517 | 25.9285 | 28.4301 | 37.9378 | 44.6895 | 16.0308 | 9.8977 | 2.3444 | 2.5015 | 2.5827 | 2.7496 | 9.5077 | 6.7517 | 25.9285 | 28.4301 | 37.9378 | 44.6895 | 0
3.496 | 10.1733 | 1.9165 | 1.8748 | 2.8107 | 2.8864 | 6.374 | 7.0062 | 13.6693 | 15.5441 | 21.9181 | 28.9243 | 3.496 | 10.1733 | 1.9265 | 1.8748 | 2.8107 | 2.8864 | 6.374 | 7.0062 | 13.6693 | 15.5441 | 21.9181 | 28.9243 | 0
4.8644 | 7.4575 | 1.9621 | 1.9432 | 4.7599 | 4.0559 | 6.7161 | 4.4992 | 12.3218 | 14.265 | 23.0809 | 27.5801 | 4.8644 | 7.4575 | 1.9721 | 1.9432 | 4.7599 | 4.0559 | 6.7161 | 4.4992 | 12.3218 | 14.265 | 23.0809 | 27.5801 | 0
16.5595 | 7.7539 | 2.352 | 2.528 | 5.0114 | 4.2069 | 9.6399 | 4.7729 | 24.3134 | 26.8414 | 36.4813 | 41.2541 | 16.5595 | 7.7539 | 2.362 | 2.528 | 5.0114 | 4.2069 | 9.6399 | 4.7729 | 24.3134 | 26.8414 | 36.4813 | 41.2541 | 0
18.0686 | 10.2879 | 2.4023 | 2.6034 | 4.3153 | 3.7892 | 10.0172 | 7.1119 | 28.3565 | 30.9599 | 40.9771 | 48.089 | 18.0686 | 10.2879 | 2.4123 | 2.6034 | 4.3153 | 3.7892 | 10.0172 | 7.1119 | 28.3565 | 30.9599 | 40.9771 | 48.089 | 0
13.8917 | 10.6149 | 2.2631 | 2.3946 | 3.384 | 3.2304 | 8.9729 | 7.4137 | 24.5065 | 26.9011 | 35.874 | 43.2878 | 13.8917 | 10.6149 | 2.2731 | 2.3946 | 3.384 | 3.2304 | 8.9729 | 7.4137 | 24.5065 | 26.9011 | 35.874 | 43.2878 | 0
8.3042 | 9.7099 | 2.0768 | 2.1152 | 2.9744 | 2.9846 | 7.576 | 6.5783 | 18.014 | 20.1292 | 27.7053 | 34.2836 | 8.3042 | 9.7099 | 2.0868 | 2.1152 | 2.9744 | 2.9846 | 7.576 | 6.5783 | 18.014 | 20.1292 | 27.7053 | 34.2836 | 0
5.8464 | 8.4992 | 1.9949 | 1.9923 | 4.3016 | 3.781 | 6.9616 | 5.4608 | 14.3457 | 16.338 | 24.4206 | 29.8814 | 5.8464 | 8.4992 | 2.0049 | 1.9923 | 4.3016 | 3.781 | 6.9616 | 5.4608 | 14.3457 | 16.338 | 24.4206 | 29.8814 | 0
13.8097 | 7.9667 | 2.2603 | 2.3905 | 3.6323 | 3.3794 | 8.9524 | 4.9693 | 21.7765 | 24.1669 | 33.1194 | 38.0887 | 13.8097 | 7.9667 | 2.2703 | 2.3905 | 3.6323 | 3.3794 | 8.9524 | 4.9693 | 21.7765 | 24.1669 | 33.1194 | 38.0887 | 0
9.7938 | 9.6921 | 2.1265 | 2.1897 | 3.7296 | 3.4377 | 7.9485 | 6.5619 | 19.4859 | 21.6756 | 29.6241 | 36.186 | 9.7938 | 9.6921 | 2.1365 | 2.1897 | 3.7296 | 3.4377 | 7.9485 | 6.5619 | 19.4859 | 21.6756 | 29.6241 | 36.186 | 0
10.3775 | 8.822 | 2.1459 | 2.2189 | 4.6453 | 3.9872 | 8.0944 | 5.7588 | 19.1995 | 21.4184 | 30.0509 | 35.8096 | 10.3775 | 8.822 | 2.1559 | 2.2189 | 4.6453 | 3.9872 | 8.0944 | 5.7588 | 19.1995 | 21.4184 | 30.0509 | 35.8096 | 0
15.8718 | 8.9485 | 2.3291 | 2.4936 | 2.8253 | 2.8952 | 9.468 | 5.8755 | 24.8203 | 27.3139 | 36.7818 | 42.6573 | 15.8718 | 8.9485 | 2.3391 | 2.4936 | 2.8253 | 2.8952 | 9.468 | 5.8755 | 24.8203 | 27.3139 | 36.7818 | 42.6573 | 0
4.9521 | 10.1389 | 1.9651 | 1.9476 | 2.6385 | 2.7831 | 6.738 | 6.9744 | 15.091 | 17.0386 | 23.7766 | 30.751 | 4.9521 | 10.1389 | 1.9751 | 1.9476 | 2.6385 | 2.7831 | 6.738 | 6.9744 | 15.091 | 17.0386 | 23.7766 | 30.751 | 0
3.8311 | 7.7729 | 1.9277 | 1.8916 | 2.9743 | 2.9846 | 6.4578 | 4.7904 | 11.604 | 13.4956 | 19.9533 | 24.7438 | 3.8311 | 7.7729 | 1.9377 | 1.8916 | 2.9743 | 2.9846 | 6.4578 | 4.7904 | 11.604 | 13.4956 | 19.9533 | 24.7438 | 0
5.8458 | 7.5301 | 1.9949 | 1.9923 | 1.9744 | 2.3846 | 6.9614 | 4.5662 | 13.3758 | 15.3681 | 22.3296 | 26.8958 | 5.8458 | 7.5301 | 2.0049 | 1.9923 | 1.9744 | 2.3846 | 6.9614 | 4.5662 | 13.3758 | 15.3681 | 22.3296 | 26.8958 | 0
-0.15369 | 7.9666 | 1.7949 | 1.6923 | 3.4835 | 3.2901 | 5.4616 | 4.9692 | 7.8129 | 9.5052 | 16.2788 | 21.248 | -0.15369 | 7.9666 | 1.8049 | 1.6923 | 3.4835 | 3.2901 | 5.4616 | 4.9692 | 7.8129 | 9.5052 | 16.2788 | 21.248 | 0
8.9011 | 6.6667 | 2.0967 | 2.1451 | 2.8402 | 2.9041 | 7.7253 | 3.7693 | 15.5678 | 17.7128 | 25.4381 | 29.2073 | 8.9011 | 6.6667 | 2.1067 | 2.1451 | 2.8402 | 2.9041 | 7.7253 | 3.7693 | 15.5678 | 17.7128 | 25.4381 | 29.2073 | 0
5.0411 | 8.6286 | 1.968 | 1.9521 | 2.9244 | 2.9547 | 6.7603 | 5.5802 | 13.6697 | 15.6217 | 22.382 | 27.9622 | 5.0411 | 8.6286 | 1.978 | 1.9521 | 2.9244 | 2.9547 | 6.7603 | 5.5802 | 13.6697 | 15.6217 | 22.382 | 27.9622 | 0
5.5467 | 7.7922 | 1.9849 | 1.9773 | 2.7834 | 2.87 | 6.8867 | 4.8082 | 13.3389 | 15.3163 | 22.2029 | 27.0112 | 5.5467 | 7.7922 | 1.9949 | 1.9773 | 2.7834 | 2.87 | 6.8867 | 4.8082 | 13.3389 | 15.3163 | 22.2029 | 27.0112 | 0
4.7002 | 7.9018 | 1.9567 | 1.935 | 2.2444 | 2.5466 | 6.675 | 4.9093 | 12.602 | 14.537 | 21.212 | 26.1214 | 4.7002 | 7.9018 | 1.9667 | 1.935 | 2.2444 | 2.5466 | 6.675 | 4.9093 | 12.602 | 14.537 | 21.212 | 26.1214 | 0
1.4663 | 7.7184 | 1.8489 | 1.7733 | 3.148 | 3.0888 | 5.8666 | 4.74 | 9.1847 | 10.958 | 17.1947 | 21.9348 | 1.4663 | 7.7184 | 1.8589 | 1.7733 | 3.148 | 3.0888 | 5.8666 | 4.74 | 9.1847 | 10.958 | 17.1947 | 21.9348 | 0
6.8879 | 7.0177 | 2.0296 | 2.0444 | 1.6145 | 2.1687 | 7.222 | 4.0933 | 13.9056 | 15.95 | 23.1719 | 27.2652 | 6.8879 | 7.0177 | 2.0396 | 2.0444 | 1.6145 | 2.1687 | 7.222 | 4.0933 | 13.9056 | 15.95 | 23.1719 | 27.2652 | 0
-2.3129 | 8.1924 | 1.7229 | 1.5844 | 2.1422 | 2.4853 | 4.9218 | 5.1776 | 5.8795 | 7.4639 | 12.3856 | 17.5632 | -2.3129 | 8.1924 | 1.7329 | 1.5844 | 2.1422 | 2.4853 | 4.9218 | 5.1776 | 5.8795 | 7.4639 | 12.3856 | 17.5632 | 0
0.85301 | 6.1989 | 1.8284 | 1.7427 | 3.3938 | 3.2363 | 5.7133 | 3.3374 | 7.0519 | 8.7945 | 15.4247 | 18.7621 | 0.85301 | 6.1989 | 1.8384 | 1.7427 | 3.3938 | 3.2363 | 5.7133 | 3.3374 | 7.0519 | 8.7945 | 15.4247 | 18.7621 | 0
8.363 | 6.8848 | 2.0788 | 2.1181 | 2.8631 | 2.9179 | 7.5907 | 3.9706 | 15.2478 | 17.366 | 24.9567 | 28.9273 | 8.363 | 6.8848 | 2.0888 | 2.1181 | 2.8631 | 2.9179 | 7.5907 | 3.9706 | 15.2478 | 17.366 | 24.9567 | 28.9273 | 0
5.1786 | 8.512 | 1.9726 | 1.9589 | 2.7811 | 2.8686 | 6.7946 | 5.4726 | 13.6906 | 15.6495 | 22.4441 | 27.9167 | 5.1786 | 8.512 | 1.9826 | 1.9589 | 2.7811 | 2.8686 | 6.7946 | 5.4726 | 13.6906 | 15.6495 | 22.4441 | 27.9167 | 0
4.6863 | 7.822 | 1.9562 | 1.9343 | 1.7183 | 2.231 | 6.6716 | 4.8357 | 12.5083 | 14.4427 | 21.1142 | 25.95 | 4.6863 | 7.822 | 1.9662 | 1.9343 | 1.7183 | 2.231 | 6.6716 | 4.8357 | 12.5083 | 14.4427 | 21.1142 | 25.95 | 0
-1.69 | 7.7154 | 1.7437 | 1.6155 | 2.6544 | 2.7926 | 5.0775 | 4.7373 | 6.0254 | 7.6409 | 13.0879 | 17.8252 | -1.69 | 7.7154 | 1.7537 | 1.6155 | 2.6544 | 2.7926 | 5.0775 | 4.7373 | 6.0254 | 7.6409 | 13.0879 | 17.8252 | 0
3.9263 | 6.3338 | 1.9309 | 1.8963 | 2.8467 | 2.908 | 6.4816 | 3.462 | 10.2601 | 12.1564 | 18.638 | 22.1 | 3.9263 | 6.3338 | 1.9409 | 1.8963 | 2.8467 | 2.908 | 6.4816 | 3.462 | 10.2601 | 12.1564 | 18.638 | 22.1 | 0
5.0801 | 7.5507 | 1.9693 | 1.954 | 2.9045 | 2.9427 | 6.77 | 4.5853 | 12.6307 | 14.5847 | 21.3548 | 25.94 | 5.0801 | 7.5507 | 1.9793 | 1.954 | 2.9045 | 2.9427 | 6.77 | 4.5853 | 12.6307 | 14.5847 | 21.3548 | 25.94 | 0
5.4268 | 7.8007 | 1.9809 | 1.9713 | 4.1252 | 3.6751 | 6.8567 | 4.816 | 13.2274 | 15.1988 | 22.9991 | 27.8151 | 5.4268 | 7.8007 | 1.9909 | 1.9713 | 4.1252 | 3.6751 | 6.8567 | 4.816 | 13.2274 | 15.1988 | 22.9991 | 27.8151 | 0
12.7511 | 7.8758 | 2.225 | 2.3376 | 3.8581 | 3.5149 | 8.6878 | 4.8854 | 20.6269 | 22.9645 | 31.6522 | 36.5376 | 12.7511 | 7.8758 | 2.235 | 2.3376 | 3.8581 | 3.5149 | 8.6878 | 4.8854 | 20.6269 | 22.9645 | 31.6522 | 36.5376 | 0
11.1487 | 9.4627 | 2.1716 | 2.2574 | 3.4723 | 3.2834 | 8.2872 | 6.3502 | 20.6114 | 22.8689 | 31.1561 | 37.5063 | 11.1487 | 9.4627 | 2.1816 | 2.2574 | 3.4723 | 3.2834 | 8.2872 | 6.3502 | 20.6114 | 22.8689 | 31.1561 | 37.5063 | 0
8.834 | 9.1156 | 2.0945 | 2.1417 | 3.2206 | 3.1323 | 7.7085 | 6.0297 | 17.9496 | 20.0913 | 27.7998 | 33.8295 | 8.834 | 9.1156 | 2.1045 | 2.1417 | 3.2206 | 3.1323 | 7.7085 | 6.0297 | 17.9496 | 20.0913 | 27.7998 | 33.8295 | 0
7.3235 | 8.614 | 2.0441 | 2.0662 | 3.2162 | 3.1297 | 7.3309 | 5.5668 | 15.9375 | 18.0037 | 25.3346 | 30.9014 | 7.3235 | 8.614 | 2.0541 | 2.0662 | 3.2162 | 3.1297 | 7.3309 | 5.5668 | 15.9375 | 18.0037 | 25.3346 | 30.9014 | 0
7.2969 | 8.2868 | 2.0432 | 2.0648 | 3.2464 | 3.1478 | 7.3242 | 5.2647 | 15.5837 | 17.6485 | 24.9727 | 30.2374 | 7.2969 | 8.2868 | 2.0532 | 2.0648 | 3.2464 | 3.1478 | 7.3242 | 5.2647 | 15.5837 | 17.6485 | 24.9727 | 30.2374 | 0
7.4785 | 8.281 | 2.0493 | 2.0739 | 1.9766 | 2.386 | 7.3696 | 5.2594 | 15.7595 | 17.8334 | 25.203 | 30.4624 | 7.4785 | 8.281 | 2.0593 | 2.0739 | 1.9766 | 2.386 | 7.3696 | 5.2594 | 15.7595 | 17.8334 | 25.203 | 30.4624 | 0
-0.14037 | 8.3203 | 1.7953 | 1.693 | 2.9701 | 2.9821 | 5.4649 | 5.2957 | 8.18 | 9.873 | 15.8251 | 21.1208 | -0.14037 | 8.3203 | 1.8053 | 1.693 | 2.9701 | 2.9821 | 5.4649 | 5.2957 | 8.18 | 9.873 | 15.8251 | 21.1208 | 0
5.8206 | 6.6696 | 1.994 | 1.991 | 1.6681 | 2.2008 | 6.9552 | 3.7719 | 12.4902 | 14.4813 | 21.4364 | 25.2083 | 5.8206 | 6.6696 | 2.004 | 1.991 | 1.6681 | 2.2008 | 6.9552 | 3.7719 | 12.4902 | 14.4813 | 21.4364 | 25.2083 | 0
-1.9916 | 7.9611 | 1.7336 | 1.6004 | 4.1051 | 3.6631 | 5.0021 | 4.9641 | 5.9696 | 7.57 | 15.3382 | 20.3023 | -1.9916 | 7.9611 | 1.7436 | 1.6004 | 4.1051 | 3.6631 | 5.0021 | 4.9641 | 5.9696 | 7.57 | 15.3382 | 20.3023 | 0
12.6307 | 6.2685 | 2.221 | 2.3315 | 3.1409 | 3.0845 | 8.6577 | 3.4017 | 18.8992 | 21.2308 | 29.8884 | 33.2901 | 12.6307 | 6.2685 | 2.231 | 2.3315 | 3.1409 | 3.0845 | 8.6577 | 3.4017 | 18.8992 | 21.2308 | 29.8884 | 33.2901 | 0
6.8453 | 9.4367 | 2.0282 | 2.0423 | 1.4547 | 2.0728 | 7.2113 | 6.3261 | 16.282 | 18.3243 | 25.5356 | 31.8617 | 6.8453 | 9.4367 | 2.0382 | 2.0423 | 1.4547 | 2.0728 | 7.2113 | 6.3261 | 16.282 | 18.3243 | 25.5356 | 31.8617 | 0
-3.272 | 8.1832 | 1.6909 | 1.5364 | 2.8971 | 2.9383 | 4.682 | 5.1691 | 4.9112 | 6.4476 | 12.283 | 17.452 | -3.272 | 8.1832 | 1.7009 | 1.5364 | 2.8971 | 2.9383 | 4.682 | 5.1691 | 4.9112 | 6.4476 | 12.283 | 17.452 | 0
5.3827 | 5.9911 | 1.9794 | 1.9691 | 4.3756 | 3.8253 | 6.8457 | 3.1456 | 11.3738 | 13.3429 | 21.5439 | 24.6895 | 5.3827 | 5.9911 | 1.9894 | 1.9691 | 4.3756 | 3.8253 | 6.8457 | 3.1456 | 11.3738 | 13.3429 | 21.5439 | 24.6895 | 0
14.2535 | 7.8663 | 2.2751 | 2.4127 | 2.174 | 2.5044 | 9.0634 | 4.8765 | 22.1197 | 24.5324 | 33.5958 | 38.4723 | 14.2535 | 7.8663 | 2.2851 | 2.4127 | 2.174 | 2.5044 | 9.0634 | 4.8765 | 22.1197 | 24.5324 | 33.5958 | 38.4723 | 0
1.0437 | 9.7882 | 1.8348 | 1.7522 | 2.1204 | 2.4722 | 5.7609 | 6.6507 | 10.832 | 12.5842 | 18.3451 | 24.9958 | 1.0437 | 9.7882 | 1.8448 | 1.7522 | 2.1204 | 2.4722 | 5.7609 | 6.6507 | 10.832 | 12.5842 | 18.3451 | 24.9958 | 0
0.72232 | 6.9261 | 1.8241 | 1.7361 | 3.0018 | 3.0011 | 5.6806 | 4.0087 | 7.6485 | 9.3846 | 15.3874 | 19.3962 | 0.72232 | 6.9261 | 1.8341 | 1.7361 | 3.0018 | 3.0011 | 5.6806 | 4.0087 | 7.6485 | 9.3846 | 15.3874 | 19.3962 | 0
6.0106 | 6.8565 | 2.0004 | 2.0005 | 2.5764 | 2.7458 | 7.0026 | 3.9445 | 12.8671 | 14.8676 | 21.8703 | 25.8147 | 6.0106 | 6.8565 | 2.0104 | 2.0005 | 2.5764 | 2.7458 | 7.0026 | 3.9445 | 12.8671 | 14.8676 | 21.8703 | 25.8147 | 0
3.4584 | 8.0023 | 1.9153 | 1.8729 | 0.37298 | 1.4238 | 6.3646 | 5.0021 | 11.4607 | 13.3337 | 19.6983 | 24.7004 | 3.4584 | 8.0023 | 1.9253 | 1.8729 | 0.37298 | 1.4238 | 6.3646 | 5.0021 | 11.4607 | 13.3337 | 19.6983 | 24.7004 | 0
-9.7621 | 7.4493 | 1.4746 | 1.2119 | 2.7077 | 2.8246 | 3.0595 | 4.4917 | -2.3128 | -1.1009 | 4.4314 | 8.9231 | -9.7621 | 7.4493 | 1.4846 | 1.2119 | 2.7077 | 2.8246 | 3.0595 | 4.4917 | -2.3128 | -1.1009 | 4.4314 | 8.9231 | 0
4.2463 | 4.5849 | 1.9415 | 1.9123 | 2.3095 | 2.5857 | 6.5616 | 1.8476 | 8.8311 | 10.7435 | 17.305 | 19.1526 | 4.2463 | 4.5849 | 1.9515 | 1.9123 | 2.3095 | 2.5857 | 6.5616 | 1.8476 | 8.8311 | 10.7435 | 17.305 | 19.1526 | 0
1.8569 | 7.62 | 1.8619 | 1.7928 | 3.3009 | 3.1806 | 5.9642 | 4.6493 | 9.4769 | 11.2698 | 17.7513 | 22.4005 | 1.8569 | 7.62 | 1.8719 | 1.7928 | 3.3009 | 3.1806 | 5.9642 | 4.6493 | 9.4769 | 11.2698 | 17.7513 | 22.4005 | 0
7.8055 | 7.1023 | 2.0602 | 2.0903 | 1.9738 | 2.3843 | 7.4514 | 4.1714 | 14.9079 | 16.9981 | 24.4495 | 28.6209 | 7.8055 | 7.1023 | 2.0702 | 2.0903 | 1.9738 | 2.3843 | 7.4514 | 4.1714 | 14.9079 | 16.9981 | 24.4495 | 28.6209 | 0
-0.15737 | 8.3912 | 1.7948 | 1.6921 | 2.3419 | 2.6052 | 5.4607 | 5.3611 | 8.2338 | 9.926 | 15.3866 | 20.7477 | -0.15737 | 8.3912 | 1.8048 | 1.6921 | 2.3419 | 2.6052 | 5.4607 | 5.3611 | 8.2338 | 9.926 | 15.3866 | 20.7477 | 0
2.0516 | 6.6659 | 1.8684 | 1.8026 | 4.6939 | 4.0163 | 6.0129 | 3.7685 | 8.7175 | 10.5201 | 19.2303 | 22.9989 | 2.0516 | 6.6659 | 1.8784 | 1.8026 | 4.6939 | 4.0163 | 6.0129 | 3.7685 | 8.7175 | 10.5201 | 19.2303 | 22.9989 | 0
16.1634 | 7.1445 | 2.3388 | 2.5082 | 2.4881 | 2.6928 | 9.5409 | 4.2103 | 23.308 | 25.8161 | 35.357 | 39.5673 | 16.1634 | 7.1445 | 2.3488 | 2.5082 | 2.4881 | 2.6928 | 9.5409 | 4.2103 | 23.308 | 25.8161 | 35.357 | 39.5673 | 0
2.9283 | 10.2021 | 1.8976 | 1.8464 | 1.8229 | 2.2937 | 6.2321 | 7.0327 | 13.1304 | 14.9768 | 21.2089 | 28.2416 | 2.9283 | 10.2021 | 1.9076 | 1.8464 | 1.8229 | 2.2937 | 6.2321 | 7.0327 | 13.1304 | 14.9768 | 21.2089 | 28.2416 | 0
-1.0626 | 7.3345 | 1.7646 | 1.6469 | 3.6826 | 3.4096 | 5.2344 | 4.3857 | 6.2719 | 7.9188 | 15.0109 | 19.3966 | -1.0626 | 7.3345 | 1.7746 | 1.6469 | 3.6826 | 3.4096 | 5.2344 | 4.3857 | 6.2719 | 7.9188 | 15.0109 | 19.3966 | 0
10.0956 | 6.4698 | 2.1365 | 2.2048 | 2.7751 | 2.865 | 8.0239 | 3.5875 | 16.5653 | 18.7701 | 26.794 | 30.3815 | 10.0956 | 6.4698 | 2.1465 | 2.2048 | 2.7751 | 2.865 | 8.0239 | 3.5875 | 16.5653 | 18.7701 | 26.794 | 30.3815 | 0
4.6504 | 8.8874 | 1.955 | 1.9325 | 4.5711 | 3.9427 | 6.6626 | 5.8191 | 13.5378 | 15.4703 | 23.9841 | 29.8032 | 4.6504 | 8.8874 | 1.965 | 1.9325 | 4.5711 | 3.9427 | 6.6626 | 5.8191 | 13.5378 | 15.4703 | 23.9841 | 29.8032 | 0
15.4267 | 7.7076 | 2.3142 | 2.4713 | 4.305 | 3.783 | 9.3567 | 4.7301 | 23.1343 | 25.6057 | 34.9624 | 39.6924 | 15.4267 | 7.7076 | 2.3242 | 2.4713 | 4.305 | 3.783 | 9.3567 | 4.7301 | 23.1343 | 25.6057 | 34.9624 | 39.6924 | 0
13.8297 | 10.0425 | 2.261 | 2.3915 | 2.4924 | 2.6954 | 8.9574 | 6.8853 | 23.8722 | 26.2637 | 35.2211 | 42.1065 | 13.8297 | 10.0425 | 2.271 | 2.3915 | 2.4924 | 2.6954 | 8.9574 | 6.8853 | 23.8722 | 26.2637 | 35.2211 | 42.1065 | 0
2.9545 | 9.6964 | 1.8985 | 1.8477 | 3.7825 | 3.4695 | 6.2386 | 6.5659 | 12.6509 | 14.4986 | 21.7506 | 28.3166 | 2.9545 | 9.6964 | 1.9085 | 1.8477 | 3.7825 | 3.4695 | 6.2386 | 6.5659 | 12.6509 | 14.4986 | 21.7506 | 28.3166 | 0
10.6949 | 7.3401 | 2.1565 | 2.2347 | 2.8622 | 2.9173 | 8.1737 | 4.3909 | 18.035 | 20.2698 | 28.4435 | 32.8344 | 10.6949 | 7.3401 | 2.1665 | 2.2347 | 2.8622 | 2.9173 | 8.1737 | 4.3909 | 18.035 | 20.2698 | 28.4435 | 32.8344 | 0
5.1733 | 9.0172 | 1.9724 | 1.9587 | 3.1984 | 3.119 | 6.7933 | 5.939 | 14.1905 | 16.1492 | 22.9425 | 28.8815 | 5.1733 | 9.0172 | 1.9824 | 1.9587 | 3.1984 | 3.119 | 6.7933 | 5.939 | 14.1905 | 16.1492 | 22.9425 | 28.8815 | 0
7.1904 | 7.8209 | 2.0397 | 2.0595 | 1.3371 | 2.0022 | 7.2976 | 4.8347 | 15.0112 | 17.0708 | 24.3683 | 29.203 | 7.1904 | 7.8209 | 2.0497 | 2.0595 | 1.3371 | 2.0022 | 7.2976 | 4.8347 | 15.0112 | 17.0708 | 24.3683 | 29.203 | 0
-3.9776 | 8.2579 | 1.6674 | 1.5011 | 2.9624 | 2.9775 | 4.5056 | 5.2381 | 4.2803 | 5.7815 | 11.7213 | 16.9594 | -3.9776 | 8.2579 | 1.6774 | 1.5011 | 2.9624 | 2.9775 | 4.5056 | 5.2381 | 4.2803 | 5.7815 | 11.7213 | 16.9594 | 0
5.7745 | 5.8382 | 1.9925 | 1.9887 | 3.2345 | 3.1407 | 6.9436 | 3.0045 | 11.6127 | 13.6015 | 20.5451 | 23.5496 | 5.7745 | 5.8382 | 2.0025 | 1.9887 | 3.2345 | 3.1407 | 6.9436 | 3.0045 | 11.6127 | 13.6015 | 20.5451 | 23.5496 | 0
7.4073 | 7.9511 | 2.0469 | 2.0704 | 3.9585 | 3.5751 | 7.3518 | 4.9549 | 15.3584 | 17.4288 | 24.9625 | 29.9174 | 7.4073 | 7.9511 | 2.0569 | 2.0704 | 3.9585 | 3.5751 | 7.3518 | 4.9549 | 15.3584 | 17.4288 | 24.9625 | 29.9174 | 0
11.7513 | 8.3049 | 2.1917 | 2.2876 | 2.7908 | 2.8745 | 8.4378 | 5.2815 | 20.0562 | 22.3438 | 30.7816 | 36.063 | 11.7513 | 8.3049 | 2.2017 | 2.2876 | 2.7908 | 2.8745 | 8.4378 | 5.2815 | 20.0562 | 22.3438 | 30.7816 | 36.063 | 0
4.7449 | 9.2461 | 1.9582 | 1.9372 | 1.7315 | 2.2389 | 6.6862 | 6.1503 | 13.991 | 15.9283 | 22.6145 | 28.7648 | 4.7449 | 9.2461 | 1.9682 | 1.9372 | 1.7315 | 2.2389 | 6.6862 | 6.1503 | 13.991 | 15.9283 | 22.6145 | 28.7648 | 0
-1.6111 | 7.7281 | 1.7463 | 1.6194 | 2.8944 | 2.9366 | 5.0972 | 4.749 | 6.1169 | 7.7364 | 13.5674 | 18.3163 | -1.6111 | 7.7281 | 1.7563 | 1.6194 | 2.8944 | 2.9366 | 5.0972 | 4.749 | 6.1169 | 7.7364 | 13.5674 | 18.3163 | 0
5.3662 | 6.3509 | 1.9789 | 1.9683 | 3.0773 | 3.0464 | 6.8415 | 3.4778 | 11.7171 | 13.6854 | 20.527 | 24.0047 | 5.3662 | 6.3509 | 1.9889 | 1.9683 | 3.0773 | 3.0464 | 6.8415 | 3.4778 | 11.7171 | 13.6854 | 20.527 | 24.0047 | 0
6.4638 | 7.8627 | 2.0155 | 2.0232 | 2.5815 | 2.7489 | 7.116 | 4.8732 | 14.3265 | 16.3497 | 23.4657 | 28.3389 | 6.4638 | 7.8627 | 2.0255 | 2.0232 | 2.5815 | 2.7489 | 7.116 | 4.8732 | 14.3265 | 16.3497 | 23.4657 | 28.3389 | 0
3.4889 | 8.1005 | 1.9163 | 1.8744 | 1.8665 | 2.3199 | 6.3722 | 5.0928 | 11.5894 | 13.4638 | 19.836 | 24.9288 | 3.4889 | 8.1005 | 1.9263 | 1.8744 | 1.8665 | 2.3199 | 6.3722 | 5.0928 | 11.5894 | 13.4638 | 19.836 | 24.9288 | 0
-0.80079 | 7.4559 | 1.7733 | 1.66 | 4.0774 | 3.6465 | 5.2998 | 4.4978 | 6.6551 | 8.3151 | 16.039 | 20.5368 | -0.80079 | 7.4559 | 1.7833 | 1.66 | 4.0774 | 3.6465 | 5.2998 | 4.4978 | 6.6551 | 8.3151 | 16.039 | 20.5368 | 0
12.4646 | 6.5265 | 2.2155 | 2.3232 | 2.1699 | 2.5019 | 8.6161 | 3.6398 | 18.9911 | 21.3143 | 29.9305 | 33.5703 | 12.4646 | 6.5265 | 2.2255 | 2.3232 | 2.1699 | 2.5019 | 8.6161 | 3.6398 | 18.9911 | 21.3143 | 29.9305 | 33.5703 | 0
1.0194 | 9.4007 | 1.834 | 1.751 | 4.2351 | 3.7411 | 5.7549 | 6.2929 | 10.4201 | 12.1711 | 20.1472 | 26.4401 | 1.0194 | 9.4007 | 1.844 | 1.751 | 4.2351 | 3.7411 | 5.7549 | 6.2929 | 10.4201 | 12.1711 | 20.1472 | 26.4401 | 0
13.4105 | 6.9209 | 2.247 | 2.3705 | 1.9519 | 2.3711 | 8.8526 | 4.0039 | 20.3314 | 22.7019 | 31.5546 | 35.5585 | 13.4105 | 6.9209 | 2.257 | 2.3705 | 1.9519 | 2.3711 | 8.8526 | 4.0039 | 20.3314 | 22.7019 | 31.5546 | 35.5585 | 0
-0.28881 | 9.6056 | 1.7904 | 1.6856 | 2.9194 | 2.9516 | 5.4278 | 6.4821 | 9.3168 | 11.0024 | 16.8734 | 23.3555 | -0.28881 | 9.6056 | 1.8004 | 1.6856 | 2.9194 | 2.9516 | 5.4278 | 6.4821 | 9.3168 | 11.0024 | 16.8734 | 23.3555 | 0
5.5165 | 6.6374 | 1.9839 | 1.9758 | 3.7465 | 3.4479 | 6.8791 | 3.7422 | 12.1539 | 14.1297 | 21.3241 | 25.0664 | 5.5165 | 6.6374 | 1.9939 | 1.9758 | 3.7465 | 3.4479 | 6.8791 | 3.7422 | 12.1539 | 14.1297 | 21.3241 | 25.0664 | 0
10.479 | 7.8952 | 2.1493 | 2.2239 | 2.4963 | 2.6978 | 8.1197 | 4.9033 | 18.3742 | 20.5982 | 28.7179 | 33.6212 | 10.479 | 7.8952 | 2.1593 | 2.2239 | 2.4963 | 2.6978 | 8.1197 | 4.9033 | 18.3742 | 20.5982 | 28.7179 | 33.6212 | 0
2.978 | 8.9704 | 1.8993 | 1.8489 | 4.1729 | 3.7037 | 6.2445 | 5.8958 | 11.9484 | 13.7973 | 21.6739 | 27.5697 | 2.978 | 8.9704 | 1.9093 | 1.8489 | 4.1729 | 3.7037 | 6.2445 | 5.8958 | 11.9484 | 13.7973 | 21.6739 | 27.5697 | 0
13.0371 | 7.3452 | 2.2346 | 2.3519 | 5.043 | 4.2258 | 8.7593 | 4.3956 | 20.3823 | 22.7342 | 32.0031 | 36.3986 | 13.0371 | 7.3452 | 2.2446 | 2.3519 | 5.043 | 4.2258 | 8.7593 | 4.3956 | 20.3823 | 22.7342 | 32.0031 | 36.3986 | 0
18.2582 | 9.5247 | 2.4086 | 2.6129 | 1.3136 | 1.9881 | 10.0646 | 6.4074 | 27.7829 | 30.3958 | 40.4604 | 46.8678 | 18.2582 | 9.5247 | 2.4186 | 2.6129 | 1.3136 | 1.9881 | 10.0646 | 6.4074 | 27.7829 | 30.3958 | 40.4604 | 46.8678 | 0
-4.1186 | 10.6559 | 1.6627 | 1.4941 | 3.5481 | 3.3289 | 4.4704 | 7.4516 | 6.5374 | 8.0314 | 14.9084 | 22.36 | -4.1186 | 10.6559 | 1.6727 | 1.4941 | 3.5481 | 3.3289 | 4.4704 | 7.4516 | 6.5374 | 8.0314 | 14.9084 | 22.36 | 0
9.2885 | 5.8076 | 2.1096 | 2.1644 | 2.9226 | 2.9536 | 7.8221 | 2.9763 | 15.0962 | 17.2606 | 25.0828 | 28.059 | 9.2885 | 5.8076 | 2.1196 | 2.1644 | 2.9226 | 2.9536 | 7.8221 | 2.9763 | 15.0962 | 17.2606 | 25.0828 | 28.059 | 0
5.5355 | 8.7125 | 1.9845 | 1.9768 | 5.2821 | 4.3692 | 6.8839 | 5.6577 | 14.2481 | 16.2248 | 25.8761 | 31.5339 | 5.5355 | 8.7125 | 1.9945 | 1.9768 | 5.2821 | 4.3692 | 6.8839 | 5.6577 | 14.2481 | 16.2248 | 25.8761 | 31.5339 | 0
19.6924 | 7.8994 | 2.4564 | 2.6846 | 1.3027 | 1.9816 | 10.4231 | 4.9071 | 27.5918 | 30.2764 | 40.6995 | 45.6066 | 19.6924 | 7.8994 | 2.4664 | 2.6846 | 1.3027 | 1.9816 | 10.4231 | 4.9071 | 27.5918 | 30.2764 | 40.6995 | 45.6066 | 0
-4.1837 | 10.9667 | 1.6605 | 1.4908 | 2.4833 | 2.69 | 4.4541 | 7.7385 | 6.7829 | 8.2738 | 13.447 | 21.1855 | -4.1837 | 10.9667 | 1.6705 | 1.4908 | 2.4833 | 2.69 | 4.4541 | 7.7385 | 6.7829 | 8.2738 | 13.447 | 21.1855 | 0
2.8996 | 5.7935 | 1.8967 | 1.845 | 4.6737 | 4.0042 | 6.2249 | 2.9633 | 8.6931 | 10.5381 | 19.216 | 22.1792 | 2.8996 | 5.7935 | 1.9067 | 1.845 | 4.6737 | 4.0042 | 6.2249 | 2.9633 | 8.6931 | 10.5381 | 19.216 | 22.1792 | 0
16.0422 | 7.3282 | 2.3347 | 2.5021 | 2.969 | 2.9814 | 9.5106 | 4.3799 | 23.3705 | 25.8726 | 35.3831 | 39.7631 | 16.0422 | 7.3282 | 2.3447 | 2.5021 | 2.969 | 2.9814 | 9.5106 | 4.3799 | 23.3705 | 25.8726 | 35.3831 | 39.7631 | 0
5.8138 | 10.1758 | 1.9938 | 1.9907 | 2.7846 | 2.8708 | 6.9534 | 7.0084 | 15.9896 | 17.9803 | 24.9337 | 31.9422 | 5.8138 | 10.1758 | 2.0038 | 1.9907 | 2.7846 | 2.8708 | 6.9534 | 7.0084 | 15.9896 | 17.9803 | 24.9337 | 31.9422 | 0
4.7076 | 7.9596 | 1.9569 | 1.9354 | 2.5954 | 2.7572 | 6.6769 | 4.9628 | 12.6673 | 14.6026 | 21.2795 | 26.2423 | 4.7076 | 7.9596 | 1.9669 | 1.9354 | 2.5954 | 2.7572 | 6.6769 | 4.9628 | 12.6673 | 14.6026 | 21.2795 | 26.2423 | 0
3.5724 | 7.72 | 1.9191 | 1.8786 | 4.397 | 3.8382 | 6.3931 | 4.7415 | 11.2924 | 13.171 | 21.4063 | 26.1478 | 3.5724 | 7.72 | 1.9291 | 1.8786 | 4.397 | 3.8382 | 6.3931 | 4.7415 | 11.2924 | 13.171 | 21.4063 | 26.1478 | 0
14.3822 | 7.474 | 2.2794 | 2.4191 | 2.2841 | 2.5705 | 9.0955 | 4.5145 | 21.8562 | 24.2753 | 33.3709 | 37.8854 | 14.3822 | 7.474 | 2.2894 | 2.4191 | 2.2841 | 2.5705 | 9.0955 | 4.5145 | 21.8562 | 24.2753 | 33.3709 | 37.8854 | 0
1.7047 | 9.8161 | 1.8568 | 1.7852 | 3.83 | 3.498 | 5.9262 | 6.6764 | 11.5209 | 13.3061 | 20.6341 | 27.3105 | 1.7047 | 9.8161 | 1.8668 | 1.7852 | 3.83 | 3.498 | 5.9262 | 6.6764 | 11.5209 | 13.3061 | 20.6341 | 27.3105 | 0
10.98 | 7.0694 | 2.166 | 2.249 | 3.431 | 3.2586 | 8.245 | 4.1409 | 18.0494 | 20.2984 | 28.5434 | 32.6843 | 10.98 | 7.0694 | 2.176 | 2.249 | 3.431 | 3.2586 | 8.245 | 4.1409 | 18.0494 | 20.2984 | 28.5434 | 32.6843 | 0
8.5858 | 9.079 | 2.0862 | 2.1293 | 2.0667 | 2.44 | 7.6465 | 5.996 | 17.6648 | 19.7941 | 27.4406 | 33.4366 | 8.5858 | 9.079 | 2.0962 | 2.1293 | 2.0667 | 2.44 | 7.6465 | 5.996 | 17.6648 | 19.7941 | 27.4406 | 33.4366 | 0
0.40007 | 8.5603 | 1.8133 | 1.72 | 3.5941 | 3.3565 | 5.6 | 5.5172 | 8.9603 | 10.6803 | 17.6309 | 23.1481 | 0.40007 | 8.5603 | 1.8233 | 1.72 | 3.5941 | 3.3565 | 5.6 | 5.5172 | 8.9603 | 10.6803 | 17.6309 | 23.1481 | 0
9.5647 | 6.7867 | 2.1188 | 2.1782 | 3.2553 | 3.1532 | 7.8912 | 3.88 | 16.3514 | 18.5296 | 26.4208 | 30.3008 | 9.5647 | 6.7867 | 2.1288 | 2.1782 | 3.2553 | 3.1532 | 7.8912 | 3.88 | 16.3514 | 18.5296 | 26.4208 | 30.3008 | 0
7.5316 | 8.7723 | 2.0511 | 2.0766 | 3.3519 | 3.2111 | 7.3829 | 5.7129 | 16.3039 | 18.3805 | 25.7634 | 31.4763 | 7.5316 | 8.7723 | 2.0611 | 2.0766 | 3.3519 | 3.2111 | 7.3829 | 5.7129 | 16.3039 | 18.3805 | 25.7634 | 31.4763 | 0
8.1115 | 8.3318 | 2.0704 | 2.1056 | 2.3366 | 2.602 | 7.5279 | 5.3063 | 16.4433 | 18.5489 | 26.0767 | 31.3831 | 8.1115 | 8.3318 | 2.0804 | 2.1056 | 2.3366 | 2.602 | 7.5279 | 5.3063 | 16.4433 | 18.5489 | 26.0767 | 31.3831 | 0
2.0197 | 8.4575 | 1.8673 | 1.801 | 2.4549 | 2.6729 | 6.0049 | 5.4223 | 10.4772 | 12.2782 | 18.2831 | 23.7054 | 2.0197 | 8.4575 | 1.8773 | 1.801 | 2.4549 | 2.6729 | 6.0049 | 5.4223 | 10.4772 | 12.2782 | 18.2831 | 23.7054 | 0
2.7292 | 7.1376 | 1.891 | 1.8365 | 3.3007 | 3.1804 | 6.1823 | 4.2039 | 9.8668 | 11.7033 | 18.1844 | 22.3883 | 2.7292 | 7.1376 | 1.901 | 1.8365 | 3.3007 | 3.1804 | 6.1823 | 4.2039 | 9.8668 | 11.7033 | 18.1844 | 22.3883 | 0
7.8041 | 7.2913 | 2.0601 | 2.0902 | 3.2421 | 3.1452 | 7.451 | 4.3458 | 15.0954 | 17.1856 | 24.6366 | 28.9825 | 7.8041 | 7.2913 | 2.0701 | 2.0902 | 3.2421 | 3.1452 | 7.451 | 4.3458 | 15.0954 | 17.1856 | 24.6366 | 28.9825 | 0
7.4524 | 8.3909 | 2.0484 | 2.0726 | 3.8806 | 3.5284 | 7.3631 | 5.3608 | 15.8432 | 17.9159 | 25.3248 | 30.6856 | 7.4524 | 8.3909 | 2.0584 | 2.0726 | 3.8806 | 3.5284 | 7.3631 | 5.3608 | 15.8432 | 17.9159 | 25.3248 | 30.6856 | 0
11.2836 | 8.3147 | 2.1761 | 2.2642 | 5.2907 | 4.3744 | 8.3209 | 5.2905 | 19.5983 | 21.8625 | 31.5276 | 36.8181 | 11.2836 | 8.3147 | 2.1861 | 2.2642 | 5.2907 | 4.3744 | 8.3209 | 5.2905 | 19.5983 | 21.8625 | 31.5276 | 36.8181 | 0
19.7442 | 9.1448 | 2.4581 | 2.6872 | 2.4446 | 2.6667 | 10.4361 | 6.0567 | 28.889 | 31.5762 | 42.0123 | 48.069 | 19.7442 | 9.1448 | 2.4681 | 2.6872 | 2.4446 | 2.6667 | 10.4361 | 6.0567 | 28.889 | 31.5762 | 42.0123 | 48.069 | 0
2.6675 | 10.9779 | 1.8889 | 1.8334 | 2.5403 | 2.7242 | 6.1669 | 7.7488 | 13.6454 | 15.4788 | 21.6456 | 29.3945 | 2.6675 | 10.9779 | 1.8989 | 1.8334 | 2.5403 | 2.7242 | 6.1669 | 7.7488 | 13.6454 | 15.4788 | 21.6456 | 29.3945 | 0
3.2415 | 7.278 | 1.9081 | 1.8621 | 1.9326 | 2.3596 | 6.3104 | 4.3335 | 10.5195 | 12.3816 | 18.692 | 23.0255 | 3.2415 | 7.278 | 1.9181 | 1.8621 | 1.9326 | 2.3596 | 6.3104 | 4.3335 | 10.5195 | 12.3816 | 18.692 | 23.0255 | 0
-0.40435 | 7.4023 | 1.7865 | 1.6798 | 3.4463 | 3.2678 | 5.3989 | 4.4483 | 6.998 | 8.6778 | 15.3919 | 19.8402 | -0.40435 | 7.4023 | 1.7965 | 1.6798 | 3.4463 | 3.2678 | 5.3989 | 4.4483 | 6.998 | 8.6778 | 15.3919 | 19.8402 | 0
0

## test activity D
A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | diff
-12.9745 | 3.8889 | 1.3675 | 1.0513 | -0.16242 | 1.1025 | 2.2564 | 1.2051 | -9.0857 | -8.0344 | -5.778 | -4.5729 | -12.9745 | 3.8889 | 1.3675 | 1.0613 | -0.16242 | 1.1025 | 2.2564 | 1.2051 | -9.0857 | -8.0244 | -5.768 | -4.5629 | 0.01
-0.12216 | 6.6735 | 1.7959 | 1.6939 | 1.9796 | 2.3878 | 5.4695 | 3.7756 | 6.5514 | 8.2453 | 13.7147 | 17.4903 | -0.12216 | 6.6735 | 1.7959 | 1.7039 | 1.9796 | 2.3878 | 5.4695 | 3.7756 | 6.5514 | 8.2553 | 13.7247 | 17.5003 | 0.01
6.9139 | 8.198 | 2.0305 | 2.0457 | 3.1523 | 3.0914 | 7.2285 | 5.1828 | 15.1119 | 17.1576 | 24.3861 | 29.5689 | 6.9139 | 8.198 | 2.0305 | 2.0557 | 3.1523 | 3.0914 | 7.2285 | 5.1828 | 15.1119 | 17.1676 | 24.3961 | 29.5789 | 0.01
12.6187 | 9.4341 | 2.2206 | 2.3309 | 4.1031 | 3.6619 | 8.6547 | 6.3237 | 22.0528 | 24.3837 | 33.0384 | 39.3622 | 12.6187 | 9.4341 | 2.2206 | 2.3409 | 4.1031 | 3.6619 | 8.6547 | 6.3237 | 22.0528 | 24.3937 | 33.0484 | 39.3722 | 0.01
2.4444 | 7.2296 | 1.8815 | 1.8222 | 2.4074 | 2.6444 | 6.1111 | 4.2889 | 9.674 | 11.4962 | 17.6073 | 21.8962 | 2.4444 | 7.2296 | 1.8815 | 1.8322 | 2.4074 | 2.6444 | 6.1111 | 4.2889 | 9.674 | 11.5062 | 17.6173 | 21.9062 | 0.01
13.5518 | 9.6362 | 2.2517 | 2.3776 | 4.2586 | 3.7552 | 8.888 | 6.5104 | 23.188 | 25.5656 | 34.4536 | 40.9639 | 13.5518 | 9.6362 | 2.2517 | 2.3876 | 4.2586 | 3.7552 | 8.888 | 6.5104 | 23.188 | 25.5756 | 34.4636 | 40.9739 | 0.01
9.2237 | 8.6985 | 2.1075 | 2.1612 | 3.5373 | 3.3224 | 7.8059 | 5.6447 | 17.9221 | 20.0833 | 27.8892 | 33.5339 | 9.2237 | 8.6985 | 2.1075 | 2.1712 | 3.5373 | 3.3224 | 7.8059 | 5.6447 | 17.9221 | 20.0933 | 27.8992 | 33.5439 | 0.01
13.2479 | 9.5704 | 2.2416 | 2.3624 | 4.208 | 3.7248 | 8.812 | 6.4496 | 22.8182 | 25.1806 | 33.9926 | 40.4422 | 13.2479 | 9.5704 | 2.2416 | 2.3724 | 4.208 | 3.7248 | 8.812 | 6.4496 | 22.8182 | 25.1906 | 34.0026 | 40.4522 | 0.01
14.8387 | 9.9151 | 2.2946 | 2.4419 | 4.4731 | 3.8839 | 9.2097 | 6.7677 | 24.7538 | 27.1957 | 36.4054 | 43.1731 | 14.8387 | 9.9151 | 2.2946 | 2.4519 | 4.4731 | 3.8839 | 9.2097 | 6.7677 | 24.7538 | 27.2057 | 36.4154 | 43.1831 | 0.01
5.5377 | 7.8998 | 1.9846 | 1.9769 | 2.9229 | 2.9538 | 6.8844 | 4.9075 | 13.4375 | 15.4144 | 22.2988 | 27.2063 | 5.5377 | 7.8998 | 1.9846 | 1.9869 | 2.9229 | 2.9538 | 6.8844 | 4.9075 | 13.4375 | 15.4244 | 22.3088 | 27.2163 | 0.01
3.6914 | 7.4998 | 1.923 | 1.8846 | 2.6152 | 2.7691 | 6.4229 | 4.5383 | 11.1913 | 13.0758 | 19.4987 | 24.037 | 3.6914 | 7.4998 | 1.923 | 1.8946 | 2.6152 | 2.7691 | 6.4229 | 4.5383 | 11.1913 | 13.0858 | 19.5087 | 24.047 | 0.01
15.412 | 10.0393 | 2.3137 | 2.4706 | 4.5687 | 3.9412 | 9.353 | 6.8824 | 25.4513 | 27.9219 | 37.2749 | 44.1573 | 15.412 | 10.0393 | 2.3137 | 2.4806 | 4.5687 | 3.9412 | 9.353 | 6.8824 | 25.4513 | 27.9319 | 37.2849 | 44.1673 | 0.01
-1.8093 | 6.308 | 1.7397 | 1.6095 | 1.6984 | 2.2191 | 5.0477 | 3.4381 | 4.4986 | 6.1082 | 11.1558 | 14.594 | -1.8093 | 6.308 | 1.7397 | 1.6195 | 1.6984 | 2.2191 | 5.0477 | 3.4381 | 4.4986 | 6.1182 | 11.1658 | 14.604 | 0.01
5.3552 | 7.8603 | 1.9785 | 1.9678 | 2.8925 | 2.9355 | 6.8388 | 4.871 | 13.2155 | 15.1833 | 22.0221 | 26.8931 | 5.3552 | 7.8603 | 1.9785 | 1.9778 | 2.8925 | 2.9355 | 6.8388 | 4.871 | 13.2155 | 15.1933 | 22.0321 | 26.9031 | 0.01
3.6258 | 7.4856 | 1.9209 | 1.8813 | 2.6043 | 2.7626 | 6.4065 | 4.5252 | 11.1114 | 12.9927 | 19.3991 | 23.9243 | 3.6258 | 7.4856 | 1.9209 | 1.8913 | 2.6043 | 2.7626 | 6.4065 | 4.5252 | 11.1114 | 13.0027 | 19.4091 | 23.9343 | 0.01
17.2865 | 10.4454 | 2.3762 | 2.5643 | 4.8811 | 4.1286 | 9.8216 | 7.2573 | 27.7319 | 30.2962 | 40.1178 | 47.3751 | 17.2865 | 10.4454 | 2.3762 | 2.5743 | 4.8811 | 4.1286 | 9.8216 | 7.2573 | 27.7319 | 30.3062 | 40.1278 | 47.3851 | 0.01
-1.2041 | 6.4391 | 1.7599 | 1.6398 | 1.7993 | 2.2796 | 5.199 | 3.5592 | 5.2351 | 6.8749 | 12.0738 | 15.633 | -1.2041 | 6.4391 | 1.7599 | 1.6498 | 1.7993 | 2.2796 | 5.199 | 3.5592 | 5.2351 | 6.8849 | 12.0838 | 15.643 | 0.01
10.4295 | 8.9597 | 2.1476 | 2.2215 | 3.7382 | 3.4429 | 8.1074 | 5.8859 | 19.3892 | 21.6107 | 29.7181 | 35.604 | 10.4295 | 8.9597 | 2.1476 | 2.2315 | 3.7382 | 3.4429 | 8.1074 | 5.8859 | 19.3892 | 21.6207 | 29.7281 | 35.614 | 0.01
3.5508 | 7.4693 | 1.9184 | 1.8775 | 2.5918 | 2.7551 | 6.3877 | 4.5102 | 11.0202 | 12.8977 | 19.2854 | 23.7956 | 3.5508 | 7.4693 | 1.9184 | 1.8875 | 2.5918 | 2.7551 | 6.3877 | 4.5102 | 11.0202 | 12.9077 | 19.2954 | 23.8056 | 0.01
8.8773 | 8.6234 | 2.0959 | 2.1439 | 3.4795 | 3.2877 | 7.7193 | 5.5755 | 17.5007 | 19.6445 | 27.3638 | 32.9393 | 8.8773 | 8.6234 | 2.0959 | 2.1539 | 3.4795 | 3.2877 | 7.7193 | 5.5755 | 17.5007 | 19.6545 | 27.3738 | 32.9493 | 0.01
10.0205 | 8.8711 | 2.134 | 2.201 | 3.6701 | 3.402 | 8.0051 | 5.8041 | 18.8916 | 21.0926 | 29.0977 | 34.9018 | 10.0205 | 8.8711 | 2.134 | 2.211 | 3.6701 | 3.402 | 8.0051 | 5.8041 | 18.8916 | 21.1026 | 29.1077 | 34.9118 | 0.01
8.7605 | 8.5981 | 2.092 | 2.138 | 3.4601 | 3.276 | 7.6901 | 5.5521 | 17.3586 | 19.4966 | 27.1867 | 32.7388 | 8.7605 | 8.5981 | 2.092 | 2.148 | 3.4601 | 3.276 | 7.6901 | 5.5521 | 17.3586 | 19.5066 | 27.1967 | 32.7488 | 0.01
13.6101 | 9.6489 | 2.2537 | 2.3805 | 4.2684 | 3.761 | 8.9025 | 6.522 | 23.259 | 25.6395 | 34.542 | 41.064 | 13.6101 | 9.6489 | 2.2537 | 2.3905 | 4.2684 | 3.761 | 8.9025 | 6.522 | 23.259 | 25.6495 | 34.552 | 41.074 | 0.01
-4.2589 | 5.7772 | 1.658 | 1.4871 | 1.2902 | 1.9741 | 4.4353 | 2.9482 | 1.5183 | 3.0053 | 7.4406 | 10.3888 | -4.2589 | 5.7772 | 1.658 | 1.4971 | 1.2902 | 1.9741 | 4.4353 | 2.9482 | 1.5183 | 3.0153 | 7.4506 | 10.3988 | 0.01
7.7808 | 8.3858 | 2.0594 | 2.089 | 3.2968 | 3.1781 | 7.4452 | 5.3562 | 16.1666 | 18.2557 | 25.7008 | 31.057 | 7.7808 | 8.3858 | 2.0594 | 2.099 | 3.2968 | 3.1781 | 7.4452 | 5.3562 | 16.1666 | 18.2657 | 25.7108 | 31.067 | 0.01
9.0241 | 8.6552 | 2.1008 | 2.1512 | 3.504 | 3.3024 | 7.756 | 5.6048 | 17.6794 | 19.8306 | 27.5866 | 33.1914 | 9.0241 | 8.6552 | 2.1008 | 2.1612 | 3.504 | 3.3024 | 7.756 | 5.6048 | 17.6794 | 19.8406 | 27.5966 | 33.2014 | 0.01
0.87462 | 6.8895 | 1.8292 | 1.7437 | 2.1458 | 2.4875 | 5.7187 | 3.9749 | 7.7641 | 9.5079 | 15.2265 | 19.2014 | 0.87462 | 6.8895 | 1.8292 | 1.7537 | 2.1458 | 2.4875 | 5.7187 | 3.9749 | 7.7641 | 9.5179 | 15.2365 | 19.2114 | 0.01
4.3537 | 7.6433 | 1.9451 | 1.9177 | 2.7256 | 2.8354 | 6.5884 | 4.6707 | 11.997 | 13.9147 | 20.5031 | 25.1739 | 4.3537 | 7.6433 | 1.9451 | 1.9277 | 2.7256 | 2.8354 | 6.5884 | 4.6707 | 11.997 | 13.9247 | 20.5131 | 25.1839 | 0.01
7.5191 | 8.3291 | 2.0506 | 2.076 | 3.2532 | 3.1519 | 7.3798 | 5.3038 | 15.8482 | 17.9242 | 25.3039 | 30.6078 | 7.5191 | 8.3291 | 2.0506 | 2.086 | 3.2532 | 3.1519 | 7.3798 | 5.3038 | 15.8482 | 17.9342 | 25.3139 | 30.6178 | 0.01
-1.0782 | 6.4664 | 1.7641 | 1.6461 | 1.8203 | 2.2922 | 5.2304 | 3.5844 | 5.3882 | 7.0343 | 12.2647 | 15.8491 | -1.0782 | 6.4664 | 1.7641 | 1.6561 | 1.8203 | 2.2922 | 5.2304 | 3.5844 | 5.3882 | 7.0443 | 12.2747 | 15.8591 | 0.01
-5.1061 | 5.5937 | 1.6298 | 1.4447 | 1.149 | 1.8894 | 4.2235 | 2.7788 | 0.48754 | 1.9322 | 6.1557 | 8.9345 | -5.1061 | 5.5937 | 1.6298 | 1.4547 | 1.149 | 1.8894 | 4.2235 | 2.7788 | 0.48754 | 1.9422 | 6.1657 | 8.9445 | 0.01
1.3629 | 6.9953 | 1.8454 | 1.7681 | 2.2271 | 2.5363 | 5.8407 | 4.0726 | 8.3582 | 10.1263 | 15.967 | 20.0396 | 1.3629 | 6.9953 | 1.8454 | 1.7781 | 2.2271 | 2.5363 | 5.8407 | 4.0726 | 8.3582 | 10.1363 | 15.977 | 20.0496 | 0.01
1.8639 | 7.1038 | 1.8621 | 1.7932 | 2.3106 | 2.5864 | 5.966 | 4.1728 | 8.9677 | 10.7609 | 16.7269 | 20.8996 | 1.8639 | 7.1038 | 1.8621 | 1.8032 | 2.3106 | 2.5864 | 5.966 | 4.1728 | 8.9677 | 10.7709 | 16.7369 | 20.9096 | 0.01
9.9802 | 8.8624 | 2.1327 | 2.199 | 3.6634 | 3.398 | 7.995 | 5.796 | 18.8426 | 21.0416 | 29.0366 | 34.8327 | 9.9802 | 8.8624 | 2.1327 | 2.209 | 3.6634 | 3.398 | 7.995 | 5.796 | 18.8426 | 21.0516 | 29.0466 | 34.8427 | 0.01
7.6476 | 8.357 | 2.0549 | 2.0824 | 3.2746 | 3.1648 | 7.4119 | 5.3295 | 16.0046 | 18.087 | 25.4989 | 30.8284 | 7.6476 | 8.357 | 2.0549 | 2.0924 | 3.2746 | 3.1648 | 7.4119 | 5.3295 | 16.0046 | 18.097 | 25.5089 | 30.8384 | 0.01
11.5709 | 9.207 | 2.1857 | 2.2785 | 3.9285 | 3.5571 | 8.3927 | 6.1142 | 20.778 | 23.0565 | 31.4492 | 37.5634 | 11.5709 | 9.207 | 2.1857 | 2.2885 | 3.9285 | 3.5571 | 8.3927 | 6.1142 | 20.778 | 23.0665 | 31.4592 | 37.5734 | 0.01
2.211 | 7.179 | 1.8737 | 1.8105 | 2.3685 | 2.6211 | 6.0527 | 4.2422 | 9.39 | 11.2006 | 17.2533 | 21.4955 | 2.211 | 7.179 | 1.8737 | 1.8205 | 2.3685 | 2.6211 | 6.0527 | 4.2422 | 9.39 | 11.2106 | 17.2633 | 21.5055 | 0.01
8.1676 | 8.4696 | 2.0723 | 2.1084 | 3.3613 | 3.2168 | 7.5419 | 5.4335 | 16.6372 | 18.7456 | 26.2875 | 31.721 | 8.1676 | 8.4696 | 2.0723 | 2.1184 | 3.3613 | 3.2168 | 7.5419 | 5.4335 | 16.6372 | 18.7556 | 26.2975 | 31.731 | 0.01
-1.5632 | 6.3613 | 1.7479 | 1.6218 | 1.7395 | 2.2437 | 5.1092 | 3.4874 | 4.7981 | 6.42 | 11.5292 | 15.0165 | -1.5632 | 6.3613 | 1.7479 | 1.6318 | 1.7395 | 2.2437 | 5.1092 | 3.4874 | 4.7981 | 6.43 | 11.5392 | 15.0265 | 0.01
6.51 | 8.1105 | 2.017 | 2.0255 | 3.085 | 3.051 | 7.1275 | 5.102 | 14.6205 | 16.646 | 23.7735 | 28.8754 | 6.51 | 8.1105 | 2.017 | 2.0355 | 3.085 | 3.051 | 7.1275 | 5.102 | 14.6205 | 16.656 | 23.7835 | 28.8854 | 0.01
9.2137 | 8.6963 | 2.1071 | 2.1607 | 3.5356 | 3.3214 | 7.8034 | 5.6427 | 17.91 | 20.0707 | 27.8741 | 33.5169 | 9.2137 | 8.6963 | 2.1071 | 2.1707 | 3.5356 | 3.3214 | 7.8034 | 5.6427 | 17.91 | 20.0807 | 27.8841 | 33.5269 | 0.01
2.0475 | 7.1436 | 1.8683 | 1.8024 | 2.3413 | 2.6048 | 6.0119 | 4.2095 | 9.1911 | 10.9935 | 17.0054 | 21.2149 | 2.0475 | 7.1436 | 1.8683 | 1.8124 | 2.3413 | 2.6048 | 6.0119 | 4.2095 | 9.1911 | 11.0035 | 17.0154 | 21.2249 | 0.01
2.251 | 7.1877 | 1.875 | 1.8125 | 2.3752 | 2.6251 | 6.0627 | 4.2502 | 9.4387 | 11.2513 | 17.314 | 21.5642 | 2.251 | 7.1877 | 1.875 | 1.8225 | 2.3752 | 2.6251 | 6.0627 | 4.2502 | 9.4387 | 11.2613 | 17.324 | 21.5742 | 0.01
3.4527 | 7.4481 | 1.9151 | 1.8726 | 2.5755 | 2.7453 | 6.3632 | 4.4905 | 10.9008 | 12.7734 | 19.1366 | 23.6272 | 3.4527 | 7.4481 | 1.9151 | 1.8826 | 2.5755 | 2.7453 | 6.3632 | 4.4905 | 10.9008 | 12.7834 | 19.1466 | 23.6372 | 0.01
-0.171 | 6.663 | 1.7943 | 1.6915 | 1.9715 | 2.3829 | 5.4573 | 3.7658 | 6.492 | 8.1834 | 13.6407 | 17.4065 | -0.171 | 6.663 | 1.7943 | 1.7015 | 1.9715 | 2.3829 | 5.4573 | 3.7658 | 6.492 | 8.1934 | 13.6507 | 17.4165 | 0.01
2.2975 | 7.1978 | 1.8766 | 1.8149 | 2.3829 | 2.6297 | 6.0744 | 4.2595 | 9.4953 | 11.3101 | 17.3845 | 21.644 | 2.2975 | 7.1978 | 1.8766 | 1.8249 | 2.3829 | 2.6297 | 6.0744 | 4.2595 | 9.4953 | 11.3201 | 17.3945 | 21.654 | 0.01
0.11826 | 6.7256 | 1.8039 | 1.7059 | 2.0197 | 2.4118 | 5.5296 | 3.8237 | 6.8439 | 8.5498 | 14.0794 | 17.903 | 0.11826 | 6.7256 | 1.8039 | 1.7159 | 2.0197 | 2.4118 | 5.5296 | 3.8237 | 6.8439 | 8.5598 | 14.0894 | 17.913 | 0.01
5.5591 | 7.9045 | 1.9853 | 1.978 | 2.9265 | 2.9559 | 6.8898 | 4.9118 | 13.4636 | 15.4416 | 22.3313 | 27.2432 | 5.5591 | 7.9045 | 1.9853 | 1.988 | 2.9265 | 2.9559 | 6.8898 | 4.9118 | 13.4636 | 15.4516 | 22.3413 | 27.2532 | 0.01
2.3412 | 7.2073 | 1.878 | 1.8171 | 2.3902 | 2.6341 | 6.0853 | 4.2682 | 9.5484 | 11.3655 | 17.4508 | 21.719 | 2.3412 | 7.2073 | 1.878 | 1.8271 | 2.3902 | 2.6341 | 6.0853 | 4.2682 | 9.5484 | 11.3755 | 17.4608 | 21.729 | 0.01
8.1691 | 8.47 | 2.0723 | 2.1085 | 3.3615 | 3.2169 | 7.5423 | 5.4338 | 16.639 | 18.7475 | 26.2897 | 31.7235 | 8.1691 | 8.47 | 2.0723 | 2.1185 | 3.3615 | 3.2169 | 7.5423 | 5.4338 | 16.639 | 18.7575 | 26.2997 | 31.7335 | 0.01
8.3035 | 8.4991 | 2.0768 | 2.1152 | 3.3839 | 3.2303 | 7.5759 | 5.4607 | 16.8026 | 18.9177 | 26.4936 | 31.9543 | 8.3035 | 8.4991 | 2.0768 | 2.1252 | 3.3839 | 3.2303 | 7.5759 | 5.4607 | 16.8026 | 18.9277 | 26.5036 | 31.9643 | 0.01
10.4961 | 8.9742 | 2.1499 | 2.2248 | 3.7493 | 3.4496 | 8.124 | 5.8992 | 19.4702 | 21.695 | 29.8191 | 35.7183 | 10.4961 | 8.9742 | 2.1499 | 2.2348 | 3.7493 | 3.4496 | 8.124 | 5.8992 | 19.4702 | 21.705 | 29.8291 | 35.7283 | 0.01
10.5815 | 8.9927 | 2.1527 | 2.2291 | 3.7636 | 3.4582 | 8.1454 | 5.9163 | 19.5742 | 21.8033 | 29.9486 | 35.8649 | 10.5815 | 8.9927 | 2.1527 | 2.2391 | 3.7636 | 3.4582 | 8.1454 | 5.9163 | 19.5742 | 21.8133 | 29.9586 | 35.8749 | 0.01
5.8599 | 7.9696 | 1.9953 | 1.993 | 2.9766 | 2.986 | 6.965 | 4.972 | 13.8295 | 15.8225 | 22.7875 | 27.7595 | 5.8599 | 7.9696 | 1.9953 | 2.003 | 2.9766 | 2.986 | 6.965 | 4.972 | 13.8295 | 15.8325 | 22.7975 | 27.7695 | 0.01
14.7012 | 9.8853 | 2.29 | 2.4351 | 4.4502 | 3.8701 | 9.1753 | 6.7402 | 24.5864 | 27.0215 | 36.1968 | 42.937 | 14.7012 | 9.8853 | 2.29 | 2.4451 | 4.4502 | 3.8701 | 9.1753 | 6.7402 | 24.5864 | 27.0315 | 36.2068 | 42.947 | 0.01
8.3236 | 8.5034 | 2.0775 | 2.1162 | 3.3873 | 3.2324 | 7.5809 | 5.4647 | 16.827 | 18.9432 | 26.5241 | 31.9888 | 8.3236 | 8.5034 | 2.0775 | 2.1262 | 3.3873 | 3.2324 | 7.5809 | 5.4647 | 16.827 | 18.9532 | 26.5341 | 31.9988 | 0.01
8.3401 | 8.507 | 2.078 | 2.117 | 3.39 | 3.234 | 7.585 | 5.468 | 16.8471 | 18.9641 | 26.5492 | 32.0172 | 8.3401 | 8.507 | 2.078 | 2.127 | 3.39 | 3.234 | 7.585 | 5.468 | 16.8471 | 18.9741 | 26.5592 | 32.0272 | 0.01
10.3472 | 8.9419 | 2.1449 | 2.2174 | 3.7245 | 3.4347 | 8.0868 | 5.8694 | 19.289 | 21.5064 | 29.5932 | 35.4626 | 10.3472 | 8.9419 | 2.1449 | 2.2274 | 3.7245 | 3.4347 | 8.0868 | 5.8694 | 19.289 | 21.5164 | 29.6032 | 35.4726 | 0.01
14.4633 | 9.8337 | 2.2821 | 2.4232 | 4.4105 | 3.8463 | 9.1158 | 6.6927 | 24.297 | 26.7201 | 35.836 | 42.5286 | 14.4633 | 9.8337 | 2.2821 | 2.4332 | 4.4105 | 3.8463 | 9.1158 | 6.6927 | 24.297 | 26.7301 | 35.846 | 42.5386 | 0.01
-3.5127 | 5.9389 | 1.6829 | 1.5244 | 1.4146 | 2.0487 | 4.6218 | 3.0975 | 2.4263 | 3.9506 | 8.5725 | 11.6699 | -3.5127 | 5.9389 | 1.6829 | 1.5344 | 1.4146 | 2.0487 | 4.6218 | 3.0975 | 2.4263 | 3.9606 | 8.5825 | 11.6799 | 0.01
5.4776 | 7.8868 | 1.9826 | 1.9739 | 2.9129 | 2.9478 | 6.8694 | 4.8955 | 13.3644 | 15.3383 | 22.2077 | 27.1032 | 5.4776 | 7.8868 | 1.9826 | 1.9839 | 2.9129 | 2.9478 | 6.8694 | 4.8955 | 13.3644 | 15.3483 | 22.2177 | 27.1132 | 0.01
5.2807 | 7.8442 | 1.976 | 1.964 | 2.8801 | 2.9281 | 6.8202 | 4.8561 | 13.1249 | 15.0889 | 21.9091 | 26.7653 | 5.2807 | 7.8442 | 1.976 | 1.974 | 2.8801 | 2.9281 | 6.8202 | 4.8561 | 13.1249 | 15.0989 | 21.9191 | 26.7753 | 0.01
7.9784 | 8.4286 | 2.0659 | 2.0989 | 3.3297 | 3.1978 | 7.4946 | 5.3957 | 16.407 | 18.5059 | 26.0005 | 31.3962 | 7.9784 | 8.4286 | 2.0659 | 2.1089 | 3.3297 | 3.1978 | 7.4946 | 5.3957 | 16.407 | 18.5159 | 26.0105 | 31.4062 | 0.01
13.8033 | 9.6907 | 2.2601 | 2.3902 | 4.3006 | 3.7803 | 8.9508 | 6.5607 | 23.494 | 25.8842 | 34.835 | 41.3957 | 13.8033 | 9.6907 | 2.2601 | 2.4002 | 4.3006 | 3.7803 | 8.9508 | 6.5607 | 23.494 | 25.8942 | 34.845 | 41.4057 | 0.01
8.5439 | 8.5512 | 2.0848 | 2.1272 | 3.424 | 3.2544 | 7.636 | 5.5088 | 17.0951 | 19.2223 | 26.8583 | 32.367 | 8.5439 | 8.5512 | 2.0848 | 2.1372 | 3.424 | 3.2544 | 7.636 | 5.5088 | 17.0951 | 19.2323 | 26.8683 | 32.377 | 0.01
4.4437 | 7.6628 | 1.9481 | 1.9222 | 2.7406 | 2.8444 | 6.6109 | 4.6887 | 12.1065 | 14.0287 | 20.6396 | 25.3283 | 4.4437 | 7.6628 | 1.9481 | 1.9322 | 2.7406 | 2.8444 | 6.6109 | 4.6887 | 12.1065 | 14.0387 | 20.6496 | 25.3383 | 0.01
7.7456 | 8.3782 | 2.0582 | 2.0873 | 3.2909 | 3.1746 | 7.4364 | 5.3491 | 16.1238 | 18.2111 | 25.6475 | 30.9967 | 7.7456 | 8.3782 | 2.0582 | 2.0973 | 3.2909 | 3.1746 | 7.4364 | 5.3491 | 16.1238 | 18.2211 | 25.6575 | 31.0067 | 0.01
-2.7103 | 6.1128 | 1.7097 | 1.5645 | 1.5483 | 2.129 | 4.8224 | 3.2579 | 3.4024 | 4.9669 | 9.7893 | 13.0473 | -2.7103 | 6.1128 | 1.7097 | 1.5745 | 1.5483 | 2.129 | 4.8224 | 3.2579 | 3.4024 | 4.9769 | 9.7993 | 13.0573 | 0.01
10.561 | 8.9882 | 2.152 | 2.2281 | 3.7602 | 3.4561 | 8.1403 | 5.9122 | 19.5493 | 21.7773 | 29.9176 | 35.8298 | 10.561 | 8.9882 | 2.152 | 2.2381 | 3.7602 | 3.4561 | 8.1403 | 5.9122 | 19.5493 | 21.7873 | 29.9276 | 35.8398 | 0.01
4.0867 | 7.5855 | 1.9362 | 1.9043 | 2.6811 | 2.8087 | 6.5217 | 4.6173 | 11.6721 | 13.5765 | 20.0982 | 24.7155 | 4.0867 | 7.5855 | 1.9362 | 1.9143 | 2.6811 | 2.8087 | 6.5217 | 4.6173 | 11.6721 | 13.5865 | 20.1082 | 24.7255 | 0.01
-2.8232 | 6.0883 | 1.7059 | 1.5588 | 1.5295 | 2.1177 | 4.7942 | 3.2354 | 3.2652 | 4.824 | 9.6182 | 12.8536 | -2.8232 | 6.0883 | 1.7059 | 1.5688 | 1.5295 | 2.1177 | 4.7942 | 3.2354 | 3.2652 | 4.834 | 9.6282 | 12.8636 | 0.01
4.6997 | 7.7183 | 1.9567 | 1.935 | 2.7833 | 2.87 | 6.6749 | 4.7399 | 12.418 | 14.353 | 21.0279 | 25.7678 | 4.6997 | 7.7183 | 1.9567 | 1.945 | 2.7833 | 2.87 | 6.6749 | 4.7399 | 12.418 | 14.363 | 21.0379 | 25.7778 | 0.01
9.2885 | 8.7125 | 2.1096 | 2.1644 | 3.5481 | 3.3288 | 7.8221 | 5.6577 | 18.0009 | 20.1654 | 27.9875 | 33.6452 | 9.2885 | 8.7125 | 2.1096 | 2.1744 | 3.5481 | 3.3288 | 7.8221 | 5.6577 | 18.0009 | 20.1754 | 27.9975 | 33.6552 | 0.01
4.1946 | 7.6088 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5486 | 4.6389 | 11.8034 | 13.7131 | 20.2618 | 24.9007 | 4.1946 | 7.6088 | 1.9398 | 1.9197 | 2.6991 | 2.8195 | 6.5486 | 4.6389 | 11.8034 | 13.7231 | 20.2718 | 24.9107 | 0.01
17.7331 | 10.5422 | 2.3911 | 2.5867 | 4.9555 | 4.1733 | 9.9333 | 7.3466 | 28.2753 | 30.862 | 40.7953 | 48.1419 | 17.7331 | 10.5422 | 2.3911 | 2.5967 | 4.9555 | 4.1733 | 9.9333 | 7.3466 | 28.2753 | 30.872 | 40.8053 | 48.1519 | 0.01
5.1638 | 7.8188 | 1.9721 | 1.9582 | 2.8606 | 2.9164 | 6.791 | 4.8328 | 12.9827 | 14.9409 | 21.7318 | 26.5646 | 5.1638 | 7.8188 | 1.9721 | 1.9682 | 2.8606 | 2.9164 | 6.791 | 4.8328 | 12.9827 | 14.9509 | 21.7418 | 26.5746 | 0.01
-1.7584 | 6.319 | 1.7414 | 1.6121 | 1.7069 | 2.2242 | 5.0604 | 3.4483 | 4.5607 | 6.1727 | 11.2331 | 14.6815 | -1.7584 | 6.319 | 1.7414 | 1.6221 | 1.7069 | 2.2242 | 5.0604 | 3.4483 | 4.5607 | 6.1827 | 11.2431 | 14.6915 | 0.01
-8.3468 | 4.8915 | 1.5218 | 1.2827 | 0.60887 | 1.5653 | 3.4133 | 2.1306 | -3.4553 | -2.1726 | 1.2407 | 3.3713 | -8.3468 | 4.8915 | 1.5218 | 1.2927 | 0.60887 | 1.5653 | 3.4133 | 2.1306 | -3.4553 | -2.1626 | 1.2507 | 3.3813 | 0.01
-0.18201 | 6.6606 | 1.7939 | 1.6909 | 1.9697 | 2.3818 | 5.4545 | 3.7636 | 6.4786 | 8.1695 | 13.624 | 17.3876 | -0.18201 | 6.6606 | 1.7939 | 1.7009 | 1.9697 | 2.3818 | 5.4545 | 3.7636 | 6.4786 | 8.1795 | 13.634 | 17.3976 | 0.01
-6.2667 | 5.3422 | 1.5911 | 1.3867 | 0.95556 | 1.7733 | 3.9333 | 2.5467 | -0.92444 | 0.46223 | 4.3956 | 6.9422 | -6.2667 | 5.3422 | 1.5911 | 1.3967 | 0.95556 | 1.7733 | 3.9333 | 2.5467 | -0.92444 | 0.47223 | 4.4056 | 6.9522 | 0.01
10.6683 | 9.0115 | 2.1556 | 2.2334 | 3.778 | 3.4668 | 8.1671 | 5.9337 | 19.6798 | 21.9132 | 30.0803 | 36.0139 | 10.6683 | 9.0115 | 2.1556 | 2.2434 | 3.778 | 3.4668 | 8.1671 | 5.9337 | 19.6798 | 21.9232 | 30.0903 | 36.0239 | 0.01
6.5503 | 8.1192 | 2.0183 | 2.0275 | 3.0917 | 3.055 | 7.1376 | 5.1101 | 14.6695 | 16.697 | 23.8346 | 28.9447 | 6.5503 | 8.1192 | 2.0183 | 2.0375 | 3.0917 | 3.055 | 7.1376 | 5.1101 | 14.6695 | 16.707 | 23.8446 | 28.9547 | 0.01
7.3155 | 8.285 | 2.0438 | 2.0658 | 3.2192 | 3.1315 | 7.3289 | 5.2631 | 15.6005 | 17.6663 | 24.9951 | 30.2582 | 7.3155 | 8.285 | 2.0438 | 2.0758 | 3.2192 | 3.1315 | 7.3289 | 5.2631 | 15.6005 | 17.6763 | 25.0051 | 30.2682 | 0.01
12.1047 | 9.3227 | 2.2035 | 2.3052 | 4.0174 | 3.6105 | 8.5262 | 6.2209 | 21.4274 | 23.7326 | 32.2588 | 38.4797 | 12.1047 | 9.3227 | 2.2035 | 2.3152 | 4.0174 | 3.6105 | 8.5262 | 6.2209 | 21.4274 | 23.7426 | 32.2688 | 38.4897 | 0.01
11.6009 | 9.2135 | 2.1867 | 2.28 | 3.9335 | 3.5601 | 8.4002 | 6.1202 | 20.8144 | 23.0944 | 31.4947 | 37.6148 | 11.6009 | 9.2135 | 2.1867 | 2.29 | 3.9335 | 3.5601 | 8.4002 | 6.1202 | 20.8144 | 23.1044 | 31.5047 | 37.6248 | 0.01
16.131 | 10.195 | 2.3377 | 2.5065 | 4.6885 | 4.0131 | 9.5327 | 7.0262 | 26.326 | 28.8326 | 38.3653 | 45.3915 | 16.131 | 10.195 | 2.3377 | 2.5165 | 4.6885 | 4.0131 | 9.5327 | 7.0262 | 26.326 | 28.8426 | 38.3753 | 45.4015 | 0.01
7.8716 | 8.4055 | 2.0624 | 2.0936 | 3.3119 | 3.1872 | 7.4679 | 5.3743 | 16.2771 | 18.3706 | 25.8385 | 31.2128 | 7.8716 | 8.4055 | 2.0624 | 2.1036 | 3.3119 | 3.1872 | 7.4679 | 5.3743 | 16.2771 | 18.3806 | 25.8485 | 31.2228 | 0.01
6.6207 | 8.1345 | 2.0207 | 2.031 | 3.1035 | 3.0621 | 7.1552 | 5.1241 | 14.7552 | 16.7863 | 23.9415 | 29.0656 | 6.6207 | 8.1345 | 2.0207 | 2.041 | 3.1035 | 3.0621 | 7.1552 | 5.1241 | 14.7552 | 16.7963 | 23.9515 | 29.0756 | 0.01
15.6319 | 10.0869 | 2.3211 | 2.4816 | 4.6053 | 3.9632 | 9.408 | 6.9264 | 25.7188 | 28.2004 | 37.6084 | 44.5348 | 15.6319 | 10.0869 | 2.3211 | 2.4916 | 4.6053 | 3.9632 | 9.408 | 6.9264 | 25.7188 | 28.2104 | 37.6184 | 44.5448 | 0.01
12.4075 | 9.3883 | 2.2136 | 2.3204 | 4.0679 | 3.6408 | 8.6019 | 6.2815 | 21.7958 | 24.1162 | 32.7181 | 38.9996 | 12.4075 | 9.3883 | 2.2136 | 2.3304 | 4.0679 | 3.6408 | 8.6019 | 6.2815 | 21.7958 | 24.1262 | 32.7281 | 39.0096 | 0.01
3.1852 | 7.3901 | 1.9062 | 1.8593 | 2.5309 | 2.7185 | 6.2963 | 4.437 | 10.5753 | 12.4346 | 18.7309 | 23.168 | 3.1852 | 7.3901 | 1.9062 | 1.8693 | 2.5309 | 2.7185 | 6.2963 | 4.437 | 10.5753 | 12.4446 | 18.7409 | 23.178 | 0.01
8.0258 | 8.4389 | 2.0675 | 2.1013 | 3.3376 | 3.2026 | 7.5065 | 5.4052 | 16.4648 | 18.5661 | 26.0725 | 31.4777 | 8.0258 | 8.4389 | 2.0675 | 2.1113 | 3.3376 | 3.2026 | 7.5065 | 5.4052 | 16.4648 | 18.5761 | 26.0825 | 31.4877 | 0.01
-1.6375 | 6.3452 | 1.7454 | 1.6181 | 1.7271 | 2.2363 | 5.0906 | 3.4725 | 4.7078 | 6.3259 | 11.4165 | 14.889 | -1.6375 | 6.3452 | 1.7454 | 1.6281 | 1.7271 | 2.2363 | 5.0906 | 3.4725 | 4.7078 | 6.3359 | 11.4265 | 14.899 | 0.01
3.3169 | 7.4187 | 1.9106 | 1.8658 | 2.5528 | 2.7317 | 6.3292 | 4.4634 | 10.7355 | 12.6014 | 18.9306 | 23.394 | 3.3169 | 7.4187 | 1.9106 | 1.8758 | 2.5528 | 2.7317 | 6.3292 | 4.4634 | 10.7355 | 12.6114 | 18.9406 | 23.404 | 0.01
-1.316 | 6.4149 | 1.7561 | 1.6342 | 1.7807 | 2.2684 | 5.171 | 3.5368 | 5.0988 | 6.733 | 11.904 | 15.4408 | -1.316 | 6.4149 | 1.7561 | 1.6442 | 1.7807 | 2.2684 | 5.171 | 3.5368 | 5.0988 | 6.743 | 11.914 | 15.4508 | 0.01
7.4915 | 8.3232 | 2.0497 | 2.0746 | 3.2486 | 3.1491 | 7.3729 | 5.2983 | 15.8146 | 17.8892 | 25.2621 | 30.5603 | 7.4915 | 8.3232 | 2.0497 | 2.0846 | 3.2486 | 3.1491 | 7.3729 | 5.2983 | 15.8146 | 17.8992 | 25.2721 | 30.5703 | 0.01
1.1213 | 6.943 | 1.8374 | 1.7561 | 2.1869 | 2.5121 | 5.7803 | 4.0243 | 8.0643 | 9.8204 | 15.6007 | 19.625 | 1.1213 | 6.943 | 1.8374 | 1.7661 | 2.1869 | 2.5121 | 5.7803 | 4.0243 | 8.0643 | 9.8304 | 15.6107 | 19.635 | 0.01
-0.19129 | 6.6586 | 1.7936 | 1.6904 | 1.9681 | 2.3809 | 5.4522 | 3.7617 | 6.4673 | 8.1577 | 13.6099 | 17.3716 | -0.19129 | 6.6586 | 1.7936 | 1.7004 | 1.9681 | 2.3809 | 5.4522 | 3.7617 | 6.4673 | 8.1677 | 13.6199 | 17.3816 | 0.01
14.9327 | 9.9354 | 2.2978 | 2.4466 | 4.4888 | 3.8933 | 9.2332 | 6.7865 | 24.8681 | 27.3147 | 36.5479 | 43.3344 | 14.9327 | 9.9354 | 2.2978 | 2.4566 | 4.4888 | 3.8933 | 9.2332 | 6.7865 | 24.8681 | 27.3247 | 36.5579 | 43.3444 | 0.01
6.5945 | 8.1288 | 2.0198 | 2.0297 | 3.0991 | 3.0594 | 7.1486 | 5.1189 | 14.7233 | 16.753 | 23.9016 | 29.0205 | 6.5945 | 8.1288 | 2.0198 | 2.0397 | 3.0991 | 3.0594 | 7.1486 | 5.1189 | 14.7233 | 16.763 | 23.9116 | 29.0305 | 0.01
9.6841 | 8.7982 | 2.1228 | 2.1842 | 3.614 | 3.3684 | 7.921 | 5.7368 | 18.4823 | 20.6665 | 28.5875 | 34.3244 | 9.6841 | 8.7982 | 2.1228 | 2.1942 | 3.614 | 3.3684 | 7.921 | 5.7368 | 18.4823 | 20.6765 | 28.5975 | 34.3344 | 0.01
10.8748 | 9.0562 | 2.1625 | 2.2437 | 3.8125 | 3.4875 | 8.2187 | 5.975 | 19.931 | 22.1747 | 30.3934 | 36.3684 | 10.8748 | 9.0562 | 2.1625 | 2.2537 | 3.8125 | 3.4875 | 8.2187 | 5.975 | 19.931 | 22.1847 | 30.4034 | 36.3784 | 0.01
9.5191 | 8.7625 | 2.1173 | 2.176 | 3.5865 | 3.3519 | 7.8798 | 5.7038 | 18.2816 | 20.4576 | 28.3373 | 34.0412 | 9.5191 | 8.7625 | 2.1173 | 2.186 | 3.5865 | 3.3519 | 7.8798 | 5.7038 | 18.2816 | 20.4676 | 28.3473 | 34.0512 | 0.01
11.791 | 9.2547 | 2.193 | 2.2896 | 3.9652 | 3.5791 | 8.4478 | 6.1582 | 21.0458 | 23.3353 | 31.7831 | 37.9413 | 11.791 | 9.2547 | 2.193 | 2.2996 | 3.9652 | 3.5791 | 8.4478 | 6.1582 | 21.0458 | 23.3453 | 31.7931 | 37.9513 | 0.01
4.0406 | 7.5755 | 1.9347 | 1.902 | 2.6734 | 2.8041 | 6.5101 | 4.6081 | 11.6161 | 13.5181 | 20.0282 | 24.6364 | 4.0406 | 7.5755 | 1.9347 | 1.912 | 2.6734 | 2.8041 | 6.5101 | 4.6081 | 11.6161 | 13.5281 | 20.0382 | 24.6464 | 0.01
0.16694 | 6.7362 | 1.8056 | 1.7083 | 2.0278 | 2.4167 | 5.5417 | 3.8334 | 6.9031 | 8.6115 | 14.1532 | 17.9866 | 0.16694 | 6.7362 | 1.8056 | 1.7183 | 2.0278 | 2.4167 | 5.5417 | 3.8334 | 6.9031 | 8.6215 | 14.1632 | 17.9966 | 0.01
1.7732 | 7.0842 | 1.8591 | 1.7887 | 2.2955 | 2.5773 | 5.9433 | 4.1546 | 8.8574 | 10.6461 | 16.5894 | 20.7441 | 1.7732 | 7.0842 | 1.8591 | 1.7987 | 2.2955 | 2.5773 | 5.9433 | 4.1546 | 8.8574 | 10.6561 | 16.5994 | 20.7541 | 0.01
2.946 | 7.3383 | 1.8982 | 1.8473 | 2.491 | 2.6946 | 6.2365 | 4.3892 | 10.2843 | 12.1316 | 18.3681 | 22.7573 | 2.946 | 7.3383 | 1.8982 | 1.8573 | 2.491 | 2.6946 | 6.2365 | 4.3892 | 10.2843 | 12.1416 | 18.3781 | 22.7673 | 0.01
5.1699 | 7.8202 | 1.9723 | 1.9585 | 2.8617 | 2.917 | 6.7925 | 4.834 | 12.9901 | 14.9486 | 21.7411 | 26.5751 | 5.1699 | 7.8202 | 1.9723 | 1.9685 | 2.8617 | 2.917 | 6.7925 | 4.834 | 12.9901 | 14.9586 | 21.7511 | 26.5851 | 0.01
12.1677 | 9.3363 | 2.2056 | 2.3084 | 4.0279 | 3.6168 | 8.5419 | 6.2335 | 21.504 | 23.8124 | 32.3543 | 38.5878 | 12.1677 | 9.3363 | 2.2056 | 2.3184 | 4.0279 | 3.6168 | 8.5419 | 6.2335 | 21.504 | 23.8224 | 32.3643 | 38.5978 | 0.01
6.5433 | 8.1177 | 2.0181 | 2.0272 | 3.0906 | 3.0543 | 7.1358 | 5.1087 | 14.661 | 16.6882 | 23.824 | 28.9327 | 6.5433 | 8.1177 | 2.0181 | 2.0372 | 3.0906 | 3.0543 | 7.1358 | 5.1087 | 14.661 | 16.6982 | 23.834 | 28.9427 | 0.01
11.7076 | 9.2366 | 2.1903 | 2.2854 | 3.9513 | 3.5708 | 8.4269 | 6.1415 | 20.9442 | 23.2296 | 31.6565 | 37.798 | 11.7076 | 9.2366 | 2.1903 | 2.2954 | 3.9513 | 3.5708 | 8.4269 | 6.1415 | 20.9442 | 23.2396 | 31.6665 | 37.808 | 0.01
5.373 | 7.8641 | 1.9791 | 1.9686 | 2.8955 | 2.9373 | 6.8432 | 4.8746 | 13.2371 | 15.2058 | 22.049 | 26.9236 | 5.373 | 7.8641 | 1.9791 | 1.9786 | 2.8955 | 2.9373 | 6.8432 | 4.8746 | 13.2371 | 15.2158 | 22.059 | 26.9336 | 0.01
-2.6906 | 6.117 | 1.7103 | 1.5655 | 1.5516 | 2.1309 | 4.8273 | 3.2619 | 3.4264 | 4.9919 | 9.8193 | 13.0811 | -2.6906 | 6.117 | 1.7103 | 1.5755 | 1.5516 | 2.1309 | 4.8273 | 3.2619 | 3.4264 | 5.0019 | 9.8293 | 13.0911 | 0.01
5.7733 | 7.9509 | 1.9924 | 1.9887 | 2.9622 | 2.9773 | 6.9433 | 4.9547 | 13.7242 | 15.7128 | 22.6561 | 27.6108 | 5.7733 | 7.9509 | 1.9924 | 1.9987 | 2.9622 | 2.9773 | 6.9433 | 4.9547 | 13.7242 | 15.7228 | 22.6661 | 27.6208 | 0.01
1.0347 | 6.9242 | 1.8345 | 1.7517 | 2.1724 | 2.5035 | 5.7587 | 4.0069 | 7.9588 | 9.7106 | 15.4693 | 19.4762 | 1.0347 | 6.9242 | 1.8345 | 1.7617 | 2.1724 | 2.5035 | 5.7587 | 4.0069 | 7.9588 | 9.7206 | 15.4793 | 19.4862 | 0.01
17.9452 | 10.5881 | 2.3982 | 2.5973 | 4.9909 | 4.1945 | 9.9863 | 7.389 | 28.5333 | 31.1306 | 41.1169 | 48.5059 | 17.9452 | 10.5881 | 2.3982 | 2.6073 | 4.9909 | 4.1945 | 9.9863 | 7.389 | 28.5333 | 31.1406 | 41.1269 | 48.5159 | 0.01
2.4162 | 7.2235 | 1.8805 | 1.8208 | 2.4027 | 2.6416 | 6.104 | 4.2832 | 9.6397 | 11.4605 | 17.5645 | 21.8477 | 2.4162 | 7.2235 | 1.8805 | 1.8308 | 2.4027 | 2.6416 | 6.104 | 4.2832 | 9.6397 | 11.4705 | 17.5745 | 21.8577 | 0.01
5.5634 | 7.9054 | 1.9854 | 1.9782 | 2.9272 | 2.9563 | 6.8909 | 4.9127 | 13.4688 | 15.447 | 22.3378 | 27.2505 | 5.5634 | 7.9054 | 1.9854 | 1.9882 | 2.9272 | 2.9563 | 6.8909 | 4.9127 | 13.4688 | 15.457 | 22.3478 | 27.2605 | 0.01
-4.3193 | 5.7641 | 1.656 | 1.484 | 1.2801 | 1.9681 | 4.4202 | 2.9361 | 1.4448 | 2.9288 | 7.349 | 10.2851 | -4.3193 | 5.7641 | 1.656 | 1.494 | 1.2801 | 1.9681 | 4.4202 | 2.9361 | 1.4448 | 2.9388 | 7.359 | 10.2951 | 0.01
-1.7225 | 6.3268 | 1.7426 | 1.6139 | 1.7129 | 2.2278 | 5.0694 | 3.4555 | 4.6043 | 6.2182 | 11.2876 | 14.7431 | -1.7225 | 6.3268 | 1.7426 | 1.6239 | 1.7129 | 2.2278 | 5.0694 | 3.4555 | 4.6043 | 6.2282 | 11.2976 | 14.7531 | 0.01
5.3795 | 7.8656 | 1.9793 | 1.969 | 2.8966 | 2.9379 | 6.8449 | 4.8759 | 13.245 | 15.214 | 22.0589 | 26.9348 | 5.3795 | 7.8656 | 1.9793 | 1.979 | 2.8966 | 2.9379 | 6.8449 | 4.8759 | 13.245 | 15.224 | 22.0689 | 26.9448 | 0.01
2.8529 | 7.3181 | 1.8951 | 1.8426 | 2.4755 | 2.6853 | 6.2132 | 4.3706 | 10.171 | 12.0137 | 18.2269 | 22.5975 | 2.8529 | 7.3181 | 1.8951 | 1.8526 | 2.4755 | 2.6853 | 6.2132 | 4.3706 | 10.171 | 12.0237 | 18.2369 | 22.6075 | 0.01
4.9315 | 7.7685 | 1.9644 | 1.9466 | 2.8219 | 2.8931 | 6.7329 | 4.7863 | 12.6999 | 14.6465 | 21.3794 | 26.1657 | 4.9315 | 7.7685 | 1.9644 | 1.9566 | 2.8219 | 2.8931 | 6.7329 | 4.7863 | 12.6999 | 14.6565 | 21.3894 | 26.1757 | 0.01
8.9348 | 8.6359 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7337 | 5.587 | 17.5707 | 19.7175 | 27.4512 | 33.0382 | 8.9348 | 8.6359 | 2.0978 | 2.1567 | 3.4891 | 3.2935 | 7.7337 | 5.587 | 17.5707 | 19.7275 | 27.4612 | 33.0482 | 0.01
18.576 | 10.7248 | 2.4192 | 2.6288 | 5.096 | 4.2576 | 10.144 | 7.5152 | 29.3008 | 31.9296 | 42.0736 | 49.5888 | 18.576 | 10.7248 | 2.4192 | 2.6388 | 5.096 | 4.2576 | 10.144 | 7.5152 | 29.3008 | 31.9396 | 42.0836 | 49.5988 | 0.01
10.8329 | 9.0471 | 2.1611 | 2.2416 | 3.8055 | 3.4833 | 8.2082 | 5.9666 | 19.88 | 22.1217 | 30.3299 | 36.2965 | 10.8329 | 9.0471 | 2.1611 | 2.2516 | 3.8055 | 3.4833 | 8.2082 | 5.9666 | 19.88 | 22.1317 | 30.3399 | 36.3065 | 0.01
20.2137 | 11.0796 | 2.4738 | 2.7107 | 5.3689 | 4.4214 | 10.5534 | 7.8427 | 31.2933 | 34.004 | 44.5574 | 52.4001 | 20.2137 | 11.0796 | 2.4738 | 2.7207 | 5.3689 | 4.4214 | 10.5534 | 7.8427 | 31.2933 | 34.014 | 44.5674 | 52.4101 | 0.01
-2.0597 | 6.2537 | 1.7313 | 1.597 | 1.6567 | 2.194 | 4.9851 | 3.3881 | 4.1941 | 5.7911 | 10.7762 | 14.1642 | -2.0597 | 6.2537 | 1.7313 | 1.607 | 1.6567 | 2.194 | 4.9851 | 3.3881 | 4.1941 | 5.8011 | 10.7862 | 14.1742 | 0.01
10.1219 | 8.8931 | 2.1374 | 2.2061 | 3.687 | 3.4122 | 8.0305 | 5.8244 | 19.015 | 21.2211 | 29.2516 | 35.0759 | 10.1219 | 8.8931 | 2.1374 | 2.2161 | 3.687 | 3.4122 | 8.0305 | 5.8244 | 19.015 | 21.2311 | 29.2616 | 35.0859 | 0.01
9.1303 | 8.6782 | 2.1043 | 2.1565 | 3.5217 | 3.313 | 7.7826 | 5.6261 | 17.8085 | 19.965 | 27.7476 | 33.3737 | 9.1303 | 8.6782 | 2.1043 | 2.1665 | 3.5217 | 3.313 | 7.7826 | 5.6261 | 17.8085 | 19.975 | 27.7576 | 33.3837 | 0.01
1.075 | 6.9329 | 1.8358 | 1.7537 | 2.1792 | 2.5075 | 5.7687 | 4.015 | 8.0079 | 9.7616 | 15.5304 | 19.5454 | 1.075 | 6.9329 | 1.8358 | 1.7637 | 2.1792 | 2.5075 | 5.7687 | 4.015 | 8.0079 | 9.7716 | 15.5404 | 19.5554 | 0.01
-4.9896 | 5.6189 | 1.6337 | 1.4505 | 1.1684 | 1.901 | 4.2526 | 2.8021 | 0.62936 | 2.0799 | 6.3325 | 9.1346 | -4.9896 | 5.6189 | 1.6337 | 1.4605 | 1.1684 | 1.901 | 4.2526 | 2.8021 | 0.62936 | 2.0899 | 6.3425 | 9.1446 | 0.01
-0.62885 | 6.5637 | 1.779 | 1.6686 | 1.8952 | 2.3371 | 5.3428 | 3.6742 | 5.9349 | 7.6035 | 12.9462 | 16.6205 | -0.62885 | 6.5637 | 1.779 | 1.6786 | 1.8952 | 2.3371 | 5.3428 | 3.6742 | 5.9349 | 7.6135 | 12.9562 | 16.6305 | 0.01
7.2339 | 8.2674 | 2.0411 | 2.0617 | 3.2057 | 3.1234 | 7.3085 | 5.2468 | 15.5013 | 17.563 | 24.8715 | 30.1183 | 7.2339 | 8.2674 | 2.0411 | 2.0717 | 3.2057 | 3.1234 | 7.3085 | 5.2468 | 15.5013 | 17.573 | 24.8815 | 30.1283 | 0.01
10.4833 | 8.9714 | 2.1494 | 2.2242 | 3.7472 | 3.4483 | 8.1208 | 5.8967 | 19.4547 | 21.6788 | 29.7997 | 35.6963 | 10.4833 | 8.9714 | 2.1494 | 2.2342 | 3.7472 | 3.4483 | 8.1208 | 5.8967 | 19.4547 | 21.6888 | 29.8097 | 35.7063 | 0.01
17.6691 | 10.5283 | 2.389 | 2.5835 | 4.9448 | 4.1669 | 9.9173 | 7.3338 | 28.1974 | 30.7808 | 40.6981 | 48.0319 | 17.6691 | 10.5283 | 2.389 | 2.5935 | 4.9448 | 4.1669 | 9.9173 | 7.3338 | 28.1974 | 30.7908 | 40.7081 | 48.0419 | 0.01
10.1095 | 8.8904 | 2.137 | 2.2055 | 3.6849 | 3.4109 | 8.0274 | 5.8219 | 18.9999 | 21.2053 | 29.2327 | 35.0546 | 10.1095 | 8.8904 | 2.137 | 2.2155 | 3.6849 | 3.4109 | 8.0274 | 5.8219 | 18.9999 | 21.2153 | 29.2427 | 35.0646 | 0.01
9.4732 | 8.7525 | 2.1158 | 2.1737 | 3.5789 | 3.3473 | 7.8683 | 5.6946 | 18.2258 | 20.3994 | 28.2677 | 33.9624 | 9.4732 | 8.7525 | 2.1158 | 2.1837 | 3.5789 | 3.3473 | 7.8683 | 5.6946 | 18.2258 | 20.4094 | 28.2777 | 33.9724 | 0.01
6.8688 | 8.1882 | 2.029 | 2.0434 | 3.1448 | 3.0869 | 7.2172 | 5.1738 | 15.057 | 17.1005 | 24.3177 | 29.4914 | 6.8688 | 8.1882 | 2.029 | 2.0534 | 3.1448 | 3.0869 | 7.2172 | 5.1738 | 15.057 | 17.1105 | 24.3277 | 29.5014 | 0.01
-7.7712 | 5.0162 | 1.541 | 1.3114 | 0.7048 | 1.6229 | 3.5572 | 2.2458 | -2.755 | -1.4435 | 2.1137 | 4.3594 | -7.7712 | 5.0162 | 1.541 | 1.3214 | 0.7048 | 1.6229 | 3.5572 | 2.2458 | -2.755 | -1.4335 | 2.1237 | 4.3694 | 0.01
6.6159 | 8.1335 | 2.0205 | 2.0308 | 3.1027 | 3.0616 | 7.154 | 5.1232 | 14.7494 | 16.7802 | 23.9342 | 29.0574 | 6.6159 | 8.1335 | 2.0205 | 2.0408 | 3.1027 | 3.0616 | 7.154 | 5.1232 | 14.7494 | 16.7902 | 23.9442 | 29.0674 | 0.01
7.7482 | 8.3788 | 2.0583 | 2.0874 | 3.2914 | 3.1748 | 7.437 | 5.3496 | 16.127 | 18.2144 | 25.6514 | 31.0011 | 7.7482 | 8.3788 | 2.0583 | 2.0974 | 3.2914 | 3.1748 | 7.437 | 5.3496 | 16.127 | 18.2244 | 25.6614 | 31.0111 | 0.01
11.3824 | 9.1662 | 2.1794 | 2.2691 | 3.8971 | 3.5382 | 8.3456 | 6.0765 | 20.5485 | 22.8177 | 31.1632 | 37.2397 | 11.3824 | 9.1662 | 2.1794 | 2.2791 | 3.8971 | 3.5382 | 8.3456 | 6.0765 | 20.5485 | 22.8277 | 31.1732 | 37.2497 | 0.01
3.369 | 7.4299 | 1.9123 | 1.8684 | 2.5615 | 2.7369 | 6.3422 | 4.4738 | 10.7989 | 12.6674 | 19.0096 | 23.4834 | 3.369 | 7.4299 | 1.9123 | 1.8784 | 2.5615 | 2.7369 | 6.3422 | 4.4738 | 10.7989 | 12.6774 | 19.0196 | 23.4934 | 0.01
12.951 | 9.506 | 2.2317 | 2.3475 | 4.1585 | 3.6951 | 8.7377 | 6.3902 | 22.457 | 24.8046 | 33.5423 | 39.9325 | 12.951 | 9.506 | 2.2317 | 2.3575 | 4.1585 | 3.6951 | 8.7377 | 6.3902 | 22.457 | 24.8146 | 33.5523 | 39.9425 | 0.01
0.55287 | 6.8198 | 1.8184 | 1.7276 | 2.0921 | 2.4553 | 5.6382 | 3.9106 | 7.3727 | 9.1003 | 14.7385 | 18.6491 | 0.55287 | 6.8198 | 1.8184 | 1.7376 | 2.0921 | 2.4553 | 5.6382 | 3.9106 | 7.3727 | 9.1103 | 14.7485 | 18.6591 | 0.01
5.8476 | 7.967 | 1.9949 | 1.9924 | 2.9746 | 2.9848 | 6.9619 | 4.9695 | 13.8146 | 15.807 | 22.7689 | 27.7384 | 5.8476 | 7.967 | 1.9949 | 2.0024 | 2.9746 | 2.9848 | 6.9619 | 4.9695 | 13.8146 | 15.817 | 22.7789 | 27.7484 | 0.01
1.2162 | 6.9635 | 1.8405 | 1.7608 | 2.2027 | 2.5216 | 5.8041 | 4.0432 | 8.1798 | 9.9406 | 15.7446 | 19.7879 | 1.2162 | 6.9635 | 1.8405 | 1.7708 | 2.2027 | 2.5216 | 5.8041 | 4.0432 | 8.1798 | 9.9506 | 15.7546 | 19.7979 | 0.01
12.2562 | 9.3555 | 2.2085 | 2.3128 | 4.0427 | 3.6256 | 8.564 | 6.2512 | 21.6117 | 23.9245 | 32.4885 | 38.7398 | 12.2562 | 9.3555 | 2.2085 | 2.3228 | 4.0427 | 3.6256 | 8.564 | 6.2512 | 21.6117 | 23.9345 | 32.4985 | 38.7498 | 0.01
4.5273 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7055 | 12.2082 | 14.1346 | 20.7664 | 25.4718 | 4.5273 | 7.6809 | 1.9509 | 1.9364 | 2.7545 | 2.8527 | 6.6318 | 4.7055 | 12.2082 | 14.1446 | 20.7764 | 25.4818 | 0.01
-1.3747 | 6.4021 | 1.7542 | 1.6313 | 1.7709 | 2.2625 | 5.1563 | 3.5251 | 5.0275 | 6.6587 | 11.815 | 15.3401 | -1.3747 | 6.4021 | 1.7542 | 1.6413 | 1.7709 | 2.2625 | 5.1563 | 3.5251 | 5.0275 | 6.6687 | 11.825 | 15.3501 | 0.01
7.568 | 8.3397 | 2.0523 | 2.0784 | 3.2613 | 3.1568 | 7.392 | 5.3136 | 15.9077 | 17.9861 | 25.3781 | 30.6917 | 7.568 | 8.3397 | 2.0523 | 2.0884 | 3.2613 | 3.1568 | 7.392 | 5.3136 | 15.9077 | 17.9961 | 25.3881 | 30.7017 | 0.01
17.8346 | 10.5642 | 2.3945 | 2.5917 | 4.9724 | 4.1835 | 9.9586 | 7.3669 | 28.3987 | 30.9905 | 40.9491 | 48.316 | 17.8346 | 10.5642 | 2.3945 | 2.6017 | 4.9724 | 4.1835 | 9.9586 | 7.3669 | 28.3987 | 31.0005 | 40.9591 | 48.326 | 0.01
14.6358 | 9.8711 | 2.2879 | 2.4318 | 4.4393 | 3.8636 | 9.159 | 6.7272 | 24.5069 | 26.9387 | 36.0977 | 42.8248 | 14.6358 | 9.8711 | 2.2879 | 2.4418 | 4.4393 | 3.8636 | 9.159 | 6.7272 | 24.5069 | 26.9487 | 36.1077 | 42.8348 | 0.01
14.7192 | 9.8892 | 2.2906 | 2.436 | 4.4532 | 3.8719 | 9.1798 | 6.7438 | 24.6084 | 27.0443 | 36.2241 | 42.968 | 14.7192 | 9.8892 | 2.2906 | 2.446 | 4.4532 | 3.8719 | 9.1798 | 6.7438 | 24.6084 | 27.0543 | 36.2341 | 42.978 | 0.01
8.6596 | 8.5763 | 2.0887 | 2.133 | 3.4433 | 3.266 | 7.6649 | 5.5319 | 17.2359 | 19.3689 | 27.0338 | 32.5657 | 8.6596 | 8.5763 | 2.0887 | 2.143 | 3.4433 | 3.266 | 7.6649 | 5.5319 | 17.2359 | 19.3789 | 27.0438 | 32.5757 | 0.01
-0.8912 | 6.5069 | 1.7703 | 1.6554 | 1.8515 | 2.3109 | 5.2772 | 3.6218 | 5.6157 | 7.2712 | 12.5484 | 16.1701 | -0.8912 | 6.5069 | 1.7703 | 1.6654 | 1.8515 | 2.3109 | 5.2772 | 3.6218 | 5.6157 | 7.2812 | 12.5584 | 16.1801 | 0.01
0.11658 | 6.7253 | 1.8039 | 1.7058 | 2.0194 | 2.4117 | 5.5291 | 3.8233 | 6.8418 | 8.5477 | 14.0768 | 17.9001 | 0.11658 | 6.7253 | 1.8039 | 1.7158 | 2.0194 | 2.4117 | 5.5291 | 3.8233 | 6.8418 | 8.5577 | 14.0868 | 17.9101 | 0.01
2.9789 | 7.3454 | 1.8993 | 1.8489 | 2.4965 | 2.6979 | 6.2447 | 4.3958 | 10.3243 | 12.1733 | 18.418 | 22.8138 | 2.9789 | 7.3454 | 1.8993 | 1.8589 | 2.4965 | 2.6979 | 6.2447 | 4.3958 | 10.3243 | 12.1833 | 18.428 | 22.8238 | 0.01
10.7182 | 9.0223 | 2.1573 | 2.2359 | 3.7864 | 3.4718 | 8.1796 | 5.9436 | 19.7405 | 21.9764 | 30.156 | 36.0997 | 10.7182 | 9.0223 | 2.1573 | 2.2459 | 3.7864 | 3.4718 | 8.1796 | 5.9436 | 19.7405 | 21.9864 | 30.166 | 36.1097 | 0.01
8.2018 | 8.4771 | 2.0734 | 2.1101 | 3.367 | 3.2202 | 7.5505 | 5.4404 | 16.6789 | 18.789 | 26.3395 | 31.7798 | 8.2018 | 8.4771 | 2.0734 | 2.1201 | 3.367 | 3.2202 | 7.5505 | 5.4404 | 16.6789 | 18.799 | 26.3495 | 31.7898 | 0.01
14.9186 | 9.9324 | 2.2973 | 2.4459 | 4.4864 | 3.8919 | 9.2296 | 6.7837 | 24.8509 | 27.2969 | 36.5265 | 43.3102 | 14.9186 | 9.9324 | 2.2973 | 2.4559 | 4.4864 | 3.8919 | 9.2296 | 6.7837 | 24.8509 | 27.3069 | 36.5365 | 43.3202 | 0.01
3.278 | 7.4102 | 1.9093 | 1.8639 | 2.5463 | 2.7278 | 6.3195 | 4.4556 | 10.6882 | 12.5521 | 18.8716 | 23.3272 | 3.278 | 7.4102 | 1.9093 | 1.8739 | 2.5463 | 2.7278 | 6.3195 | 4.4556 | 10.6882 | 12.5621 | 18.8816 | 23.3372 | 0.01
11.9059 | 9.2796 | 2.1969 | 2.2953 | 3.9843 | 3.5906 | 8.4765 | 6.1812 | 21.1855 | 23.4808 | 31.9572 | 38.1384 | 11.9059 | 9.2796 | 2.1969 | 2.3053 | 3.9843 | 3.5906 | 8.4765 | 6.1812 | 21.1855 | 23.4908 | 31.9672 | 38.1484 | 0.01
0.21186 | 6.7459 | 1.8071 | 1.7106 | 2.0353 | 2.4212 | 5.553 | 3.8424 | 6.9578 | 8.6684 | 14.2213 | 18.0637 | 0.21186 | 6.7459 | 1.8071 | 1.7206 | 2.0353 | 2.4212 | 5.553 | 3.8424 | 6.9578 | 8.6784 | 14.2313 | 18.0737 | 0.01
8.3077 | 8.5 | 2.0769 | 2.1154 | 3.3846 | 3.2308 | 7.5769 | 5.4615 | 16.8077 | 18.9231 | 26.5001 | 31.9616 | 8.3077 | 8.5 | 2.0769 | 2.1254 | 3.3846 | 3.2308 | 7.5769 | 5.4615 | 16.8077 | 18.9331 | 26.5101 | 31.9716 | 0.01
0.99521 | 6.9156 | 1.8332 | 1.7498 | 2.1659 | 2.4995 | 5.7488 | 3.999 | 7.9108 | 9.6606 | 15.4094 | 19.4084 | 0.99521 | 6.9156 | 1.8332 | 1.7598 | 2.1659 | 2.4995 | 5.7488 | 3.999 | 7.9108 | 9.6706 | 15.4194 | 19.4184 | 0.01
10.022 | 8.8714 | 2.1341 | 2.2011 | 3.6703 | 3.4022 | 8.0055 | 5.8044 | 18.8934 | 21.0945 | 29.1 | 34.9045 | 10.022 | 8.8714 | 2.1341 | 2.2111 | 3.6703 | 3.4022 | 8.0055 | 5.8044 | 18.8934 | 21.1045 | 29.11 | 34.9145 | 0.01
-5.1718 | 5.5794 | 1.6276 | 1.4414 | 1.138 | 1.8828 | 4.207 | 2.7656 | 0.4076 | 1.849 | 6.0561 | 8.8217 | -5.1718 | 5.5794 | 1.6276 | 1.4514 | 1.138 | 1.8828 | 4.207 | 2.7656 | 0.4076 | 1.859 | 6.0661 | 8.8317 | 0.01
-1.0844 | 6.465 | 1.7639 | 1.6458 | 1.8193 | 2.2916 | 5.2289 | 3.5831 | 5.3806 | 7.0264 | 12.2553 | 15.8384 | -1.0844 | 6.465 | 1.7639 | 1.6558 | 1.8193 | 2.2916 | 5.2289 | 3.5831 | 5.3806 | 7.0364 | 12.2653 | 15.8484 | 0.01
6.9795 | 8.2122 | 2.0326 | 2.049 | 3.1632 | 3.0979 | 7.2449 | 5.1959 | 15.1917 | 17.2407 | 24.4855 | 29.6814 | 6.9795 | 8.2122 | 2.0326 | 2.059 | 3.1632 | 3.0979 | 7.2449 | 5.1959 | 15.1917 | 17.2507 | 24.4955 | 29.6914 | 0.01
1.3132 | 6.9845 | 1.8438 | 1.7657 | 2.2189 | 2.5313 | 5.8283 | 4.0626 | 8.2978 | 10.0634 | 15.8917 | 19.9544 | 1.3132 | 6.9845 | 1.8438 | 1.7757 | 2.2189 | 2.5313 | 5.8283 | 4.0626 | 8.2978 | 10.0734 | 15.9017 | 19.9644 | 0.01
1.3639 | 6.9955 | 1.8455 | 1.7682 | 2.2273 | 2.5364 | 5.841 | 4.0728 | 8.3594 | 10.1276 | 15.9686 | 20.0414 | 1.3639 | 6.9955 | 1.8455 | 1.7782 | 2.2273 | 2.5364 | 5.841 | 4.0728 | 8.3594 | 10.1376 | 15.9786 | 20.0514 | 0.01
-1.4768 | 6.38 | 1.7508 | 1.6262 | 1.7539 | 2.2523 | 5.1308 | 3.5046 | 4.9032 | 6.5293 | 11.6601 | 15.1648 | -1.4768 | 6.38 | 1.7508 | 1.6362 | 1.7539 | 2.2523 | 5.1308 | 3.5046 | 4.9032 | 6.5393 | 11.6701 | 15.1748 | 0.01
6.5105 | 8.1106 | 2.017 | 2.0255 | 3.0851 | 3.0511 | 7.1276 | 5.1021 | 14.6211 | 16.6466 | 23.7743 | 28.8764 | 6.5105 | 8.1106 | 2.017 | 2.0355 | 3.0851 | 3.0511 | 7.1276 | 5.1021 | 14.6211 | 16.6566 | 23.7843 | 28.8864 | 0.01
2.9522 | 7.3396 | 1.8984 | 1.8476 | 2.492 | 2.6952 | 6.238 | 4.3904 | 10.2918 | 12.1394 | 18.3775 | 22.7679 | 2.9522 | 7.3396 | 1.8984 | 1.8576 | 2.492 | 2.6952 | 6.238 | 4.3904 | 10.2918 | 12.1494 | 18.3875 | 22.7779 | 0.01
6.1645 | 8.0356 | 2.0055 | 2.0082 | 3.0274 | 3.0165 | 7.0411 | 5.0329 | 14.2002 | 16.2084 | 23.2495 | 28.2824 | 6.1645 | 8.0356 | 2.0055 | 2.0182 | 3.0274 | 3.0165 | 7.0411 | 5.0329 | 14.2002 | 16.2184 | 23.2595 | 28.2924 | 0.01
3.115 | 7.3749 | 1.9038 | 1.8557 | 2.5192 | 2.7115 | 6.2787 | 4.423 | 10.4899 | 12.3457 | 18.6244 | 23.0474 | 3.115 | 7.3749 | 1.9038 | 1.8657 | 2.5192 | 2.7115 | 6.2787 | 4.423 | 10.4899 | 12.3557 | 18.6344 | 23.0574 | 0.01
6.4626 | 8.1002 | 2.0154 | 2.0231 | 3.0771 | 3.0463 | 7.1157 | 5.0925 | 14.5628 | 16.586 | 23.7016 | 28.7941 | 6.4626 | 8.1002 | 2.0154 | 2.0331 | 3.0771 | 3.0463 | 7.1157 | 5.0925 | 14.5628 | 16.596 | 23.7116 | 28.8041 | 0.01
16.0124 | 10.1694 | 2.3337 | 2.5006 | 4.6687 | 4.0012 | 9.5031 | 7.0025 | 26.1817 | 28.6824 | 38.1855 | 45.1879 | 16.0124 | 10.1694 | 2.3337 | 2.5106 | 4.6687 | 4.0012 | 9.5031 | 7.0025 | 26.1817 | 28.6924 | 38.1955 | 45.1979 | 0.01
1.5673 | 7.0396 | 1.8522 | 1.7784 | 2.2612 | 2.5567 | 5.8918 | 4.1135 | 8.6068 | 10.3852 | 16.277 | 20.3904 | 1.5673 | 7.0396 | 1.8522 | 1.7884 | 2.2612 | 2.5567 | 5.8918 | 4.1135 | 8.6068 | 10.3952 | 16.287 | 20.4004 | 0.01
13.5036 | 9.6258 | 2.2501 | 2.3752 | 4.2506 | 3.7504 | 8.8759 | 6.5007 | 23.1293 | 25.5045 | 34.3804 | 40.8811 | 13.5036 | 9.6258 | 2.2501 | 2.3852 | 4.2506 | 3.7504 | 8.8759 | 6.5007 | 23.1293 | 25.5145 | 34.3904 | 40.8911 | 0.01
0.21402 | 6.7464 | 1.8071 | 1.7107 | 2.0357 | 2.4214 | 5.5535 | 3.8428 | 6.9604 | 8.6711 | 14.2246 | 18.0674 | 0.21402 | 6.7464 | 1.8071 | 1.7207 | 2.0357 | 2.4214 | 5.5535 | 3.8428 | 6.9604 | 8.6811 | 14.2346 | 18.0774 | 0.01
0.14578 | 6.7316 | 1.8049 | 1.7073 | 2.0243 | 2.4146 | 5.5364 | 3.8292 | 6.8774 | 8.5847 | 14.1211 | 17.9503 | 0.14578 | 6.7316 | 1.8049 | 1.7173 | 2.0243 | 2.4146 | 5.5364 | 3.8292 | 6.8774 | 8.5947 | 14.1311 | 17.9603 | 0.01
6.3738 | 8.081 | 2.0125 | 2.0187 | 3.0623 | 3.0374 | 7.0935 | 5.0748 | 14.4548 | 16.4735 | 23.5669 | 28.6417 | 6.3738 | 8.081 | 2.0125 | 2.0287 | 3.0623 | 3.0374 | 7.0935 | 5.0748 | 14.4548 | 16.4835 | 23.5769 | 28.6517 | 0.01
16.4514 | 10.2645 | 2.3484 | 2.5226 | 4.7419 | 4.0451 | 9.6128 | 7.0903 | 26.7158 | 29.2384 | 38.8513 | 45.9415 | 16.4514 | 10.2645 | 2.3484 | 2.5326 | 4.7419 | 4.0451 | 9.6128 | 7.0903 | 26.7158 | 29.2484 | 38.8613 | 45.9515 | 0.01
13.4295 | 9.6097 | 2.2477 | 2.3715 | 4.2383 | 3.743 | 8.8574 | 6.4859 | 23.0392 | 25.4107 | 34.2681 | 40.754 | 13.4295 | 9.6097 | 2.2477 | 2.3815 | 4.2383 | 3.743 | 8.8574 | 6.4859 | 23.0392 | 25.4207 | 34.2781 | 40.764 | 0.01
-7.4375 | 5.0886 | 1.5521 | 1.3281 | 0.76042 | 1.6563 | 3.6406 | 2.3125 | -2.3489 | -1.0208 | 2.6199 | 4.9324 | -7.4375 | 5.0886 | 1.5521 | 1.3381 | 0.76042 | 1.6563 | 3.6406 | 2.3125 | -2.3489 | -1.0108 | 2.6299 | 4.9424 | 0.01
-2.1955 | 6.2243 | 1.7268 | 1.5902 | 1.6341 | 2.1805 | 4.9511 | 3.3609 | 4.0288 | 5.6191 | 10.5702 | 13.9311 | -2.1955 | 6.2243 | 1.7268 | 1.6002 | 1.6341 | 2.1805 | 4.9511 | 3.3609 | 4.0288 | 5.6291 | 10.5802 | 13.9411 | 0.01
-0.86628 | 6.5123 | 1.7711 | 1.6567 | 1.8556 | 2.3134 | 5.2834 | 3.6267 | 5.646 | 7.3027 | 12.5861 | 16.2129 | -0.86628 | 6.5123 | 1.7711 | 1.6667 | 1.8556 | 2.3134 | 5.2834 | 3.6267 | 5.646 | 7.3127 | 12.5961 | 16.2229 | 0.01
7.4517 | 8.3145 | 2.0484 | 2.0726 | 3.2419 | 3.1452 | 7.3629 | 5.2903 | 15.7662 | 17.8388 | 25.2017 | 30.492 | 7.4517 | 8.3145 | 2.0484 | 2.0826 | 3.2419 | 3.1452 | 7.3629 | 5.2903 | 15.7662 | 17.8488 | 25.2117 | 30.502 | 0.01
-4.548 | 5.7146 | 1.6484 | 1.4726 | 1.242 | 1.9452 | 4.363 | 2.8904 | 1.1666 | 2.6392 | 7.0022 | 9.8926 | -4.548 | 5.7146 | 1.6484 | 1.4826 | 1.242 | 1.9452 | 4.363 | 2.8904 | 1.1666 | 2.6492 | 7.0122 | 9.9026 | 0.01
10.1638 | 8.9022 | 2.1388 | 2.2082 | 3.694 | 3.4164 | 8.0409 | 5.8328 | 19.066 | 21.2741 | 29.3151 | 35.1479 | 10.1638 | 8.9022 | 2.1388 | 2.2182 | 3.694 | 3.4164 | 8.0409 | 5.8328 | 19.066 | 21.2841 | 29.3251 | 35.1579 | 0.01
7.2783 | 8.277 | 2.0426 | 2.0639 | 3.213 | 3.1278 | 7.3196 | 5.2557 | 15.5552 | 17.6191 | 24.9387 | 30.1943 | 7.2783 | 8.277 | 2.0426 | 2.0739 | 3.213 | 3.1278 | 7.3196 | 5.2557 | 15.5552 | 17.6291 | 24.9487 | 30.2043 | 0.01
1.4575 | 7.0158 | 1.8486 | 1.7729 | 2.2429 | 2.5457 | 5.8644 | 4.0915 | 8.4732 | 10.2461 | 16.1105 | 20.202 | 1.4575 | 7.0158 | 1.8486 | 1.7829 | 2.2429 | 2.5457 | 5.8644 | 4.0915 | 8.4732 | 10.2561 | 16.1205 | 20.212 | 0.01
-0.57037 | 6.5764 | 1.781 | 1.6715 | 1.9049 | 2.343 | 5.3574 | 3.6859 | 6.0061 | 7.6775 | 13.0349 | 16.7209 | -0.57037 | 6.5764 | 1.781 | 1.6815 | 1.9049 | 2.343 | 5.3574 | 3.6859 | 6.0061 | 7.6875 | 13.0449 | 16.7309 | 0.01
2.3931 | 7.2185 | 1.8798 | 1.8197 | 2.3989 | 2.6393 | 6.0983 | 4.2786 | 9.6116 | 11.4313 | 17.5295 | 21.8082 | 2.3931 | 7.2185 | 1.8798 | 1.8297 | 2.3989 | 2.6393 | 6.0983 | 4.2786 | 9.6116 | 11.4413 | 17.5395 | 21.8182 | 0.01
14.9926 | 9.9484 | 2.2998 | 2.4496 | 4.4988 | 3.8993 | 9.2481 | 6.7985 | 24.941 | 27.3906 | 36.6387 | 43.4372 | 14.9926 | 9.9484 | 2.2998 | 2.4596 | 4.4988 | 3.8993 | 9.2481 | 6.7985 | 24.941 | 27.4006 | 36.6487 | 43.4472 | 0.01
5.5444 | 7.9013 | 1.9848 | 1.9772 | 2.9241 | 2.9544 | 6.8861 | 4.9089 | 13.4457 | 15.423 | 22.3091 | 27.218 | 5.5444 | 7.9013 | 1.9848 | 1.9872 | 2.9241 | 2.9544 | 6.8861 | 4.9089 | 13.4457 | 15.433 | 22.3191 | 27.228 | 0.01
13.6245 | 9.652 | 2.2542 | 2.3812 | 4.2708 | 3.7625 | 8.9061 | 6.5249 | 23.2765 | 25.6577 | 34.5638 | 41.0887 | 13.6245 | 9.652 | 2.2542 | 2.3912 | 4.2708 | 3.7625 | 8.9061 | 6.5249 | 23.2765 | 25.6677 | 34.5738 | 41.0987 | 0.01
1.3803 | 6.9991 | 1.846 | 1.769 | 2.2301 | 2.538 | 5.8451 | 4.0761 | 8.3794 | 10.1484 | 15.9935 | 20.0695 | 1.3803 | 6.9991 | 1.846 | 1.779 | 2.2301 | 2.538 | 5.8451 | 4.0761 | 8.3794 | 10.1584 | 16.0035 | 20.0795 | 0.01
9.4004 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.8501 | 5.6801 | 18.1371 | 20.3071 | 28.1572 | 33.8373 | 9.4004 | 8.7367 | 2.1133 | 2.18 | 3.5667 | 3.34 | 7.8501 | 5.6801 | 18.1371 | 20.3171 | 28.1672 | 33.8473 | 0.01
5.1169 | 7.8087 | 1.9706 | 1.9558 | 2.8528 | 2.9117 | 6.7792 | 4.8234 | 12.9255 | 14.8813 | 21.6606 | 26.4839 | 5.1169 | 7.8087 | 1.9706 | 1.9658 | 2.8528 | 2.9117 | 6.7792 | 4.8234 | 12.9255 | 14.8913 | 21.6706 | 26.4939 | 0.01
-0.84508 | 6.5169 | 1.7718 | 1.6577 | 1.8592 | 2.3155 | 5.2887 | 3.631 | 5.6718 | 7.3296 | 12.6183 | 16.2493 | -0.84508 | 6.5169 | 1.7718 | 1.6677 | 1.8592 | 2.3155 | 5.2887 | 3.631 | 5.6718 | 7.3396 | 12.6283 | 16.2593 | 0.01
14.9278 | 9.9344 | 2.2976 | 2.4464 | 4.488 | 3.8928 | 9.232 | 6.7856 | 24.8622 | 27.3086 | 36.5405 | 43.3261 | 14.9278 | 9.9344 | 2.2976 | 2.4564 | 4.488 | 3.8928 | 9.232 | 6.7856 | 24.8622 | 27.3186 | 36.5505 | 43.3361 | 0.01
9.9078 | 8.8467 | 2.1303 | 2.1954 | 3.6513 | 3.3908 | 7.977 | 5.7816 | 18.7545 | 20.9499 | 28.9268 | 34.7084 | 9.9078 | 8.8467 | 2.1303 | 2.2054 | 3.6513 | 3.3908 | 7.977 | 5.7816 | 18.7545 | 20.9599 | 28.9368 | 34.7184 | 0.01
5.1469 | 7.8152 | 1.9716 | 1.9573 | 2.8578 | 2.9147 | 6.7867 | 4.8294 | 12.962 | 14.9194 | 21.7061 | 26.5355 | 5.1469 | 7.8152 | 1.9716 | 1.9673 | 2.8578 | 2.9147 | 6.7867 | 4.8294 | 12.962 | 14.9294 | 21.7161 | 26.5455 | 0.01
3.5807 | 7.4758 | 1.9194 | 1.879 | 2.5968 | 2.7581 | 6.3952 | 4.5161 | 11.0565 | 12.9355 | 19.3307 | 23.8468 | 3.5807 | 7.4758 | 1.9194 | 1.889 | 2.5968 | 2.7581 | 6.3952 | 4.5161 | 11.0565 | 12.9455 | 19.3407 | 23.8568 | 0.01
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2043 | 14.1305 | 20.7616 | 25.4664 | 4.5241 | 7.6802 | 1.9508 | 1.9362 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2043 | 14.1405 | 20.7716 | 25.4764 | 0.01
8.6671 | 8.5779 | 2.0889 | 2.1334 | 3.4445 | 3.2667 | 7.6668 | 5.5334 | 17.2449 | 19.3783 | 27.0451 | 32.5785 | 8.6671 | 8.5779 | 2.0889 | 2.1434 | 3.4445 | 3.2667 | 7.6668 | 5.5334 | 17.2449 | 19.3883 | 27.0551 | 32.5885 | 0.01
8.4187 | 8.5241 | 2.0806 | 2.1209 | 3.4031 | 3.2419 | 7.6047 | 5.4837 | 16.9428 | 19.0637 | 26.6684 | 32.1522 | 8.4187 | 8.5241 | 2.0806 | 2.1309 | 3.4031 | 3.2419 | 7.6047 | 5.4837 | 16.9428 | 19.0737 | 26.6784 | 32.1622 | 0.01
-9.9815 | 4.5373 | 1.4673 | 1.2009 | 0.33642 | 1.4019 | 3.0046 | 1.8037 | -5.4442 | -4.2432 | -1.2386 | 0.5651 | -9.9815 | 4.5373 | 1.4673 | 1.2109 | 0.33642 | 1.4019 | 3.0046 | 1.8037 | -5.4442 | -4.2332 | -1.2286 | 0.5751 | 0.01
17.7361 | 10.5428 | 2.3912 | 2.5868 | 4.956 | 4.1736 | 9.934 | 7.3472 | 28.2789 | 30.8657 | 40.7997 | 48.1469 | 17.7361 | 10.5428 | 2.3912 | 2.5968 | 4.956 | 4.1736 | 9.934 | 7.3472 | 28.2789 | 30.8757 | 40.8097 | 48.1569 | 0.01
14.6958 | 9.8841 | 2.2899 | 2.4348 | 4.4493 | 3.8696 | 9.174 | 6.7392 | 24.5799 | 27.0147 | 36.1887 | 42.9279 | 14.6958 | 9.8841 | 2.2899 | 2.4448 | 4.4493 | 3.8696 | 9.174 | 6.7392 | 24.5799 | 27.0247 | 36.1987 | 42.9379 | 0.01
6.9703 | 8.2102 | 2.0323 | 2.0485 | 3.1617 | 3.097 | 7.2426 | 5.1941 | 15.1805 | 17.229 | 24.4716 | 29.6656 | 6.9703 | 8.2102 | 2.0323 | 2.0585 | 3.1617 | 3.097 | 7.2426 | 5.1941 | 15.1805 | 17.239 | 24.4816 | 29.6756 | 0.01
-2.7649 | 6.1009 | 1.7078 | 1.5618 | 1.5392 | 2.1235 | 4.8088 | 3.247 | 3.336 | 4.8978 | 9.7066 | 12.9536 | -2.7649 | 6.1009 | 1.7078 | 1.5718 | 1.5392 | 2.1235 | 4.8088 | 3.247 | 3.336 | 4.9078 | 9.7166 | 12.9636 | 0.01
8.3695 | 8.5134 | 2.079 | 2.1185 | 3.3949 | 3.2369 | 7.5924 | 5.4739 | 16.8829 | 19.0014 | 26.5937 | 32.0676 | 8.3695 | 8.5134 | 2.079 | 2.1285 | 3.3949 | 3.2369 | 7.5924 | 5.4739 | 16.8829 | 19.0114 | 26.6037 | 32.0776 | 0.01
0.31258 | 6.7677 | 1.8104 | 1.7156 | 2.0521 | 2.4313 | 5.5781 | 3.8625 | 7.0803 | 8.7959 | 14.3741 | 18.2366 | 0.31258 | 6.7677 | 1.8104 | 1.7256 | 2.0521 | 2.4313 | 5.5781 | 3.8625 | 7.0803 | 8.8059 | 14.3841 | 18.2466 | 0.01
14.0166 | 9.7369 | 2.2672 | 2.4008 | 4.3361 | 3.8017 | 9.0041 | 6.6033 | 23.7535 | 26.1543 | 35.1584 | 41.7618 | 14.0166 | 9.7369 | 2.2672 | 2.4108 | 4.3361 | 3.8017 | 9.0041 | 6.6033 | 23.7535 | 26.1643 | 35.1684 | 41.7718 | 0.01
7.5685 | 8.3398 | 2.0523 | 2.0784 | 3.2614 | 3.1568 | 7.3921 | 5.3137 | 15.9083 | 17.9867 | 25.3788 | 30.6925 | 7.5685 | 8.3398 | 2.0523 | 2.0884 | 3.2614 | 3.1568 | 7.3921 | 5.3137 | 15.9083 | 17.9967 | 25.3888 | 30.7025 | 0.01
5.9811 | 7.9959 | 1.9994 | 1.9991 | 2.9968 | 2.9981 | 6.9953 | 4.9962 | 13.977 | 15.976 | 22.9713 | 27.9675 | 5.9811 | 7.9959 | 1.9994 | 2.0091 | 2.9968 | 2.9981 | 6.9953 | 4.9962 | 13.977 | 15.986 | 22.9813 | 27.9775 | 0.01
3.3981 | 7.4363 | 1.9133 | 1.8699 | 2.5664 | 2.7398 | 6.3495 | 4.4796 | 10.8344 | 12.7043 | 19.0538 | 23.5335 | 3.3981 | 7.4363 | 1.9133 | 1.8799 | 2.5664 | 2.7398 | 6.3495 | 4.4796 | 10.8344 | 12.7143 | 19.0638 | 23.5435 | 0.01
6.2917 | 8.0632 | 2.0097 | 2.0146 | 3.0486 | 3.0292 | 7.0729 | 5.0583 | 14.3549 | 16.3695 | 23.4424 | 28.5007 | 6.2917 | 8.0632 | 2.0097 | 2.0246 | 3.0486 | 3.0292 | 7.0729 | 5.0583 | 14.3549 | 16.3795 | 23.4524 | 28.5107 | 0.01
3.5617 | 7.4717 | 1.9187 | 1.8781 | 2.5936 | 2.7562 | 6.3904 | 4.5123 | 11.0334 | 12.9115 | 19.3019 | 23.8143 | 3.5617 | 7.4717 | 1.9187 | 1.8881 | 2.5936 | 2.7562 | 6.3904 | 4.5123 | 11.0334 | 12.9215 | 19.3119 | 23.8243 | 0.01
13.4989 | 9.6248 | 2.25 | 2.3749 | 4.2498 | 3.7499 | 8.8747 | 6.4998 | 23.1236 | 25.4986 | 34.3733 | 40.8731 | 13.4989 | 9.6248 | 2.25 | 2.3849 | 4.2498 | 3.7499 | 8.8747 | 6.4998 | 23.1236 | 25.5086 | 34.3833 | 40.8831 | 0.01
10.3918 | 8.9516 | 2.1464 | 2.2196 | 3.732 | 3.4392 | 8.098 | 5.8784 | 19.3434 | 21.563 | 29.6609 | 35.5393 | 10.3918 | 8.9516 | 2.1464 | 2.2296 | 3.732 | 3.4392 | 8.098 | 5.8784 | 19.3434 | 21.573 | 29.6709 | 35.5493 | 0.01
1.0548 | 6.9285 | 1.8352 | 1.7527 | 2.1758 | 2.5055 | 5.7637 | 4.011 | 7.9833 | 9.7361 | 15.4998 | 19.5107 | 1.0548 | 6.9285 | 1.8352 | 1.7627 | 2.1758 | 2.5055 | 5.7637 | 4.011 | 7.9833 | 9.7461 | 15.5098 | 19.5207 | 0.01
16.2026 | 10.2106 | 2.3401 | 2.5101 | 4.7004 | 4.0203 | 9.5506 | 7.0405 | 26.4131 | 28.9233 | 38.4739 | 45.5144 | 16.2026 | 10.2106 | 2.3401 | 2.5201 | 4.7004 | 4.0203 | 9.5506 | 7.0405 | 26.4131 | 28.9333 | 38.4839 | 45.5244 | 0.01
8.5304 | 8.5483 | 2.0843 | 2.1265 | 3.4217 | 3.253 | 7.6326 | 5.5061 | 17.0786 | 19.2052 | 26.8378 | 32.3438 | 8.5304 | 8.5483 | 2.0843 | 2.1365 | 3.4217 | 3.253 | 7.6326 | 5.5061 | 17.0786 | 19.2152 | 26.8478 | 32.3538 | 0.01
7.3385 | 8.29 | 2.0446 | 2.0669 | 3.2231 | 3.1339 | 7.3346 | 5.2677 | 15.6285 | 17.6955 | 25.0301 | 30.2978 | 7.3385 | 8.29 | 2.0446 | 2.0769 | 3.2231 | 3.1339 | 7.3346 | 5.2677 | 15.6285 | 17.7055 | 25.0401 | 30.3078 | 0.01
-11.3977 | 4.2305 | 1.4201 | 1.1301 | 0.10039 | 1.2602 | 2.6506 | 1.5205 | -7.1672 | -6.0371 | -3.3865 | -1.866 | -11.3977 | 4.2305 | 1.4201 | 1.1401 | 0.10039 | 1.2602 | 2.6506 | 1.5205 | -7.1672 | -6.0271 | -3.3765 | -1.856 | 0.01
4.3995 | 7.6532 | 1.9466 | 1.92 | 2.7332 | 2.8399 | 6.5999 | 4.6799 | 12.0527 | 13.9727 | 20.5726 | 25.2525 | 4.3995 | 7.6532 | 1.9466 | 1.93 | 2.7332 | 2.8399 | 6.5999 | 4.6799 | 12.0527 | 13.9827 | 20.5826 | 25.2625 | 0.01
14.4103 | 9.8222 | 2.2803 | 2.4205 | 4.4017 | 3.841 | 9.1026 | 6.6821 | 24.2325 | 26.6531 | 35.7556 | 42.4377 | 14.4103 | 9.8222 | 2.2803 | 2.4305 | 4.4017 | 3.841 | 9.1026 | 6.6821 | 24.2325 | 26.6631 | 35.7656 | 42.4477 | 0.01
-4.8914 | 5.6402 | 1.637 | 1.4554 | 1.1848 | 1.9109 | 4.2771 | 2.8217 | 0.74876 | 2.2042 | 6.4813 | 9.3031 | -4.8914 | 5.6402 | 1.637 | 1.4654 | 1.1848 | 1.9109 | 4.2771 | 2.8217 | 0.74876 | 2.2142 | 6.4913 | 9.3131 | 0.01
15.1442 | 9.9812 | 2.3048 | 2.4572 | 4.524 | 3.9144 | 9.2861 | 6.8288 | 25.1255 | 27.5827 | 36.8687 | 43.6976 | 15.1442 | 9.9812 | 2.3048 | 2.4672 | 4.524 | 3.9144 | 9.2861 | 6.8288 | 25.1255 | 27.5927 | 36.8787 | 43.7076 | 0.01
6.8025 | 8.1739 | 2.0267 | 2.0401 | 3.1337 | 3.0802 | 7.2006 | 5.1605 | 14.9763 | 17.0165 | 24.2171 | 29.3776 | 6.8025 | 8.1739 | 2.0267 | 2.0501 | 3.1337 | 3.0802 | 7.2006 | 5.1605 | 14.9763 | 17.0265 | 24.2271 | 29.3876 | 0.01
7.5565 | 8.3372 | 2.0519 | 2.0778 | 3.2594 | 3.1556 | 7.3891 | 5.3113 | 15.8937 | 17.9716 | 25.3607 | 30.672 | 7.5565 | 8.3372 | 2.0519 | 2.0878 | 3.2594 | 3.1556 | 7.3891 | 5.3113 | 15.8937 | 17.9816 | 25.3707 | 30.682 | 0.01
7.1078 | 8.24 | 2.0369 | 2.0554 | 3.1846 | 3.1108 | 7.2769 | 5.2216 | 15.3478 | 17.4032 | 24.6802 | 29.9017 | 7.1078 | 8.24 | 2.0369 | 2.0654 | 3.1846 | 3.1108 | 7.2769 | 5.2216 | 15.3478 | 17.4132 | 24.6902 | 29.9117 | 0.01
5.4872 | 7.8889 | 1.9829 | 1.9744 | 2.9145 | 2.9487 | 6.8718 | 4.8974 | 13.3761 | 15.3505 | 22.2223 | 27.1197 | 5.4872 | 7.8889 | 1.9829 | 1.9844 | 2.9145 | 2.9487 | 6.8718 | 4.8974 | 13.3761 | 15.3605 | 22.2323 | 27.1297 | 0.01
-0.20801 | 6.6549 | 1.7931 | 1.6896 | 1.9653 | 2.3792 | 5.448 | 3.7584 | 6.4469 | 8.1365 | 13.5845 | 17.3429 | -0.20801 | 6.6549 | 1.7931 | 1.6996 | 1.9653 | 2.3792 | 5.448 | 3.7584 | 6.4469 | 8.1465 | 13.5945 | 17.3529 | 0.01
17.5186 | 10.4957 | 2.384 | 2.5759 | 4.9198 | 4.1519 | 9.8796 | 7.3037 | 28.0143 | 30.5902 | 40.4698 | 47.7735 | 17.5186 | 10.4957 | 2.384 | 2.5859 | 4.9198 | 4.1519 | 9.8796 | 7.3037 | 28.0143 | 30.6002 | 40.4798 | 47.7835 | 0.01
10.1071 | 8.8899 | 2.1369 | 2.2054 | 3.6845 | 3.4107 | 8.0268 | 5.8214 | 18.997 | 21.2024 | 29.2292 | 35.0506 | 10.1071 | 8.8899 | 2.1369 | 2.2154 | 3.6845 | 3.4107 | 8.0268 | 5.8214 | 18.997 | 21.2124 | 29.2392 | 35.0606 | 0.01
8.5568 | 8.554 | 2.0852 | 2.1278 | 3.4261 | 3.2557 | 7.6392 | 5.5114 | 17.1107 | 19.2386 | 26.8777 | 32.3891 | 8.5568 | 8.554 | 2.0852 | 2.1378 | 3.4261 | 3.2557 | 7.6392 | 5.5114 | 17.1107 | 19.2486 | 26.8877 | 32.3991 | 0.01
6.2378 | 8.0515 | 2.0079 | 2.0119 | 3.0396 | 3.0238 | 7.0594 | 5.0476 | 14.2893 | 16.3012 | 23.3606 | 28.4082 | 6.2378 | 8.0515 | 2.0079 | 2.0219 | 3.0396 | 3.0238 | 7.0594 | 5.0476 | 14.2893 | 16.3112 | 23.3706 | 28.4182 | 0.01
-0.17002 | 6.6632 | 1.7943 | 1.6915 | 1.9717 | 2.383 | 5.4575 | 3.766 | 6.4931 | 8.1846 | 13.6421 | 17.4081 | -0.17002 | 6.6632 | 1.7943 | 1.7015 | 1.9717 | 2.383 | 5.4575 | 3.766 | 6.4931 | 8.1946 | 13.6521 | 17.4181 | 0.01
14.1065 | 9.7564 | 2.2702 | 2.4053 | 4.3511 | 3.8106 | 9.0266 | 6.6213 | 23.8629 | 26.2682 | 35.2948 | 41.9161 | 14.1065 | 9.7564 | 2.2702 | 2.4153 | 4.3511 | 3.8106 | 9.0266 | 6.6213 | 23.8629 | 26.2782 | 35.3048 | 41.9261 | 0.01
3.8564 | 7.5356 | 1.9285 | 1.8928 | 2.6427 | 2.7856 | 6.4641 | 4.5713 | 11.392 | 13.2848 | 19.7489 | 24.3202 | 3.8564 | 7.5356 | 1.9285 | 1.9028 | 2.6427 | 2.7856 | 6.4641 | 4.5713 | 11.392 | 13.2948 | 19.7589 | 24.3302 | 0.01
-3.938 | 5.8468 | 1.6687 | 1.5031 | 1.3437 | 2.0062 | 4.5155 | 3.0124 | 1.9088 | 3.4119 | 7.9273 | 10.9397 | -3.938 | 5.8468 | 1.6687 | 1.5131 | 1.3437 | 2.0062 | 4.5155 | 3.0124 | 1.9088 | 3.4219 | 7.9373 | 10.9497 | 0.01
8.0713 | 8.4488 | 2.069 | 2.1036 | 3.3452 | 3.2071 | 7.5178 | 5.4143 | 16.5201 | 18.6237 | 26.1415 | 31.5558 | 8.0713 | 8.4488 | 2.069 | 2.1136 | 3.3452 | 3.2071 | 7.5178 | 5.4143 | 16.5201 | 18.6337 | 26.1515 | 31.5658 | 0.01
-3.3537 | 5.9734 | 1.6882 | 1.5323 | 1.4411 | 2.0646 | 4.6616 | 3.1293 | 2.6197 | 4.152 | 8.8136 | 11.9428 | -3.3537 | 5.9734 | 1.6882 | 1.5423 | 1.4411 | 2.0646 | 4.6616 | 3.1293 | 2.6197 | 4.162 | 8.8236 | 11.9528 | 0.01
-2.1228 | 6.2401 | 1.7292 | 1.5939 | 1.6462 | 2.1877 | 4.9693 | 3.3754 | 4.1173 | 5.7111 | 10.6804 | 14.0558 | -2.1228 | 6.2401 | 1.7292 | 1.6039 | 1.6462 | 2.1877 | 4.9693 | 3.3754 | 4.1173 | 5.7211 | 10.6904 | 14.0658 | 0.01
3.4464 | 7.4467 | 1.9149 | 1.8723 | 2.5744 | 2.7446 | 6.3616 | 4.4893 | 10.8932 | 12.7655 | 19.1271 | 23.6164 | 3.4464 | 7.4467 | 1.9149 | 1.8823 | 2.5744 | 2.7446 | 6.3616 | 4.4893 | 10.8932 | 12.7755 | 19.1371 | 23.6264 | 0.01
9.7406 | 8.8105 | 2.1247 | 2.187 | 3.6234 | 3.3741 | 7.9351 | 5.7481 | 18.551 | 20.7381 | 28.6732 | 34.4213 | 9.7406 | 8.8105 | 2.1247 | 2.197 | 3.6234 | 3.3741 | 7.9351 | 5.7481 | 18.551 | 20.7481 | 28.6832 | 34.4313 | 0.01
14.3409 | 9.8072 | 2.278 | 2.417 | 4.3902 | 3.8341 | 9.0852 | 6.6682 | 24.1481 | 26.5652 | 35.6504 | 42.3186 | 14.3409 | 9.8072 | 2.278 | 2.427 | 4.3902 | 3.8341 | 9.0852 | 6.6682 | 24.1481 | 26.5752 | 35.6604 | 42.3286 | 0.01
10.4801 | 8.9707 | 2.1493 | 2.224 | 3.7467 | 3.448 | 8.12 | 5.896 | 19.4508 | 21.6748 | 29.7948 | 35.6908 | 10.4801 | 8.9707 | 2.1493 | 2.234 | 3.7467 | 3.448 | 8.12 | 5.896 | 19.4508 | 21.6848 | 29.8048 | 35.7008 | 0.01
1.9422 | 7.1208 | 1.8647 | 1.7971 | 2.3237 | 2.5942 | 5.9855 | 4.1884 | 9.063 | 10.8601 | 16.8456 | 21.0341 | 1.9422 | 7.1208 | 1.8647 | 1.8071 | 2.3237 | 2.5942 | 5.9855 | 4.1884 | 9.063 | 10.8701 | 16.8556 | 21.0441 | 0.01
-3.5251 | 5.9362 | 1.6825 | 1.5237 | 1.4125 | 2.0475 | 4.6187 | 3.095 | 2.4111 | 3.9349 | 8.5536 | 11.6486 | -3.5251 | 5.9362 | 1.6825 | 1.5337 | 1.4125 | 2.0475 | 4.6187 | 3.095 | 2.4111 | 3.9449 | 8.5636 | 11.6586 | 0.01
6.3941 | 8.0854 | 2.0131 | 2.0197 | 3.0657 | 3.0394 | 7.0985 | 5.0788 | 14.4795 | 16.4992 | 23.5978 | 28.6766 | 6.3941 | 8.0854 | 2.0131 | 2.0297 | 3.0657 | 3.0394 | 7.0985 | 5.0788 | 14.4795 | 16.5092 | 23.6078 | 28.6866 | 0.01
8.1827 | 8.4729 | 2.0728 | 2.1091 | 3.3638 | 3.2183 | 7.5457 | 5.4365 | 16.6556 | 18.7647 | 26.3104 | 31.7469 | 8.1827 | 8.4729 | 2.0728 | 2.1191 | 3.3638 | 3.2183 | 7.5457 | 5.4365 | 16.6556 | 18.7747 | 26.3204 | 31.7569 | 0.01
13.4254 | 9.6088 | 2.2475 | 2.3713 | 4.2376 | 3.7425 | 8.8563 | 6.4851 | 23.0342 | 25.4055 | 34.2618 | 40.7469 | 13.4254 | 9.6088 | 2.2475 | 2.3813 | 4.2376 | 3.7425 | 8.8563 | 6.4851 | 23.0342 | 25.4155 | 34.2718 | 40.7569 | 0.01
12.781 | 9.4692 | 2.226 | 2.339 | 4.1302 | 3.6781 | 8.6952 | 6.3562 | 22.2502 | 24.5892 | 33.2844 | 39.6406 | 12.781 | 9.4692 | 2.226 | 2.349 | 4.1302 | 3.6781 | 8.6952 | 6.3562 | 22.2502 | 24.5992 | 33.2944 | 39.6506 | 0.01
5.32 | 7.8527 | 1.9773 | 1.966 | 2.8867 | 2.932 | 6.83 | 4.864 | 13.1726 | 15.1386 | 21.9686 | 26.8326 | 5.32 | 7.8527 | 1.9773 | 1.976 | 2.8867 | 2.932 | 6.83 | 4.864 | 13.1726 | 15.1486 | 21.9786 | 26.8426 | 0.01
0.36357 | 6.7788 | 1.8121 | 1.7182 | 2.0606 | 2.4364 | 5.5909 | 3.8727 | 7.1423 | 8.8605 | 14.4514 | 18.3241 | 0.36357 | 6.7788 | 1.8121 | 1.7282 | 2.0606 | 2.4364 | 5.5909 | 3.8727 | 7.1423 | 8.8705 | 14.4614 | 18.3341 | 0.01
4.4875 | 7.6723 | 1.9496 | 1.9244 | 2.7479 | 2.8487 | 6.6219 | 4.6975 | 12.1597 | 14.0841 | 20.706 | 25.4035 | 4.4875 | 7.6723 | 1.9496 | 1.9344 | 2.7479 | 2.8487 | 6.6219 | 4.6975 | 12.1597 | 14.0941 | 20.716 | 25.4135 | 0.01
16.3134 | 10.2346 | 2.3438 | 2.5157 | 4.7189 | 4.0313 | 9.5783 | 7.0627 | 26.548 | 29.0636 | 38.642 | 45.7047 | 16.3134 | 10.2346 | 2.3438 | 2.5257 | 4.7189 | 4.0313 | 9.5783 | 7.0627 | 26.548 | 29.0736 | 38.652 | 45.7147 | 0.01
4.2492 | 7.6207 | 1.9416 | 1.9125 | 2.7082 | 2.8249 | 6.5623 | 4.6498 | 11.8698 | 13.7823 | 20.3446 | 24.9944 | 4.2492 | 7.6207 | 1.9416 | 1.9225 | 2.7082 | 2.8249 | 6.5623 | 4.6498 | 11.8698 | 13.7923 | 20.3546 | 25.0044 | 0.01
3.7637 | 7.5155 | 1.9255 | 1.8882 | 2.6273 | 2.7764 | 6.4409 | 4.5527 | 11.2792 | 13.1674 | 19.6083 | 24.161 | 3.7637 | 7.5155 | 1.9255 | 1.8982 | 2.6273 | 2.7764 | 6.4409 | 4.5527 | 11.2792 | 13.1774 | 19.6183 | 24.171 | 0.01
-1.4859 | 6.3781 | 1.7505 | 1.6257 | 1.7524 | 2.2514 | 5.1285 | 3.5028 | 4.8922 | 6.5179 | 11.6464 | 15.1492 | -1.4859 | 6.3781 | 1.7505 | 1.6357 | 1.7524 | 2.2514 | 5.1285 | 3.5028 | 4.8922 | 6.5279 | 11.6564 | 15.1592 | 0.01
13.1201 | 9.5427 | 2.2373 | 2.356 | 4.1867 | 3.712 | 8.78 | 6.424 | 22.6628 | 25.0188 | 33.7988 | 40.2228 | 13.1201 | 9.5427 | 2.2373 | 2.366 | 4.1867 | 3.712 | 8.78 | 6.424 | 22.6628 | 25.0288 | 33.8088 | 40.2328 | 0.01
1.2847 | 6.9783 | 1.8428 | 1.7642 | 2.2141 | 2.5285 | 5.8212 | 4.0569 | 8.263 | 10.0273 | 15.8484 | 19.9054 | 1.2847 | 6.9783 | 1.8428 | 1.7742 | 2.2141 | 2.5285 | 5.8212 | 4.0569 | 8.263 | 10.0373 | 15.8584 | 19.9154 | 0.01
10.1324 | 8.8954 | 2.1377 | 2.2066 | 3.6887 | 3.4132 | 8.0331 | 5.8265 | 19.0278 | 21.2344 | 29.2675 | 35.094 | 10.1324 | 8.8954 | 2.1377 | 2.2166 | 3.6887 | 3.4132 | 8.0331 | 5.8265 | 19.0278 | 21.2444 | 29.2775 | 35.104 | 0.01
19.078 | 10.8336 | 2.4359 | 2.6539 | 5.1797 | 4.3078 | 10.2695 | 7.6156 | 29.9115 | 32.5654 | 42.8349 | 50.4505 | 19.078 | 10.8336 | 2.4359 | 2.6639 | 5.1797 | 4.3078 | 10.2695 | 7.6156 | 29.9115 | 32.5754 | 42.8449 | 50.4605 | 0.01
14.4903 | 9.8396 | 2.283 | 2.4245 | 4.4151 | 3.849 | 9.1226 | 6.6981 | 24.3299 | 26.7544 | 35.877 | 42.5751 | 14.4903 | 9.8396 | 2.283 | 2.4345 | 4.4151 | 3.849 | 9.1226 | 6.6981 | 24.3299 | 26.7644 | 35.887 | 42.5851 | 0.01
1.3037 | 6.9825 | 1.8435 | 1.7652 | 2.2173 | 2.5304 | 5.8259 | 4.0607 | 8.2862 | 10.0514 | 15.8773 | 19.9381 | 1.3037 | 6.9825 | 1.8435 | 1.7752 | 2.2173 | 2.5304 | 5.8259 | 4.0607 | 8.2862 | 10.0614 | 15.8873 | 19.9481 | 0.01
4.5343 | 7.6824 | 1.9511 | 1.9267 | 2.7557 | 2.8534 | 6.6336 | 4.7069 | 12.2167 | 14.1434 | 20.777 | 25.4838 | 4.5343 | 7.6824 | 1.9511 | 1.9367 | 2.7557 | 2.8534 | 6.6336 | 4.7069 | 12.2167 | 14.1534 | 20.787 | 25.4938 | 0.01
8.9171 | 8.632 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5834 | 17.5492 | 19.695 | 27.4243 | 33.0077 | 8.9171 | 8.632 | 2.0972 | 2.1559 | 3.4862 | 3.2917 | 7.7293 | 5.5834 | 17.5492 | 19.705 | 27.4343 | 33.0177 | 0.01
4.2696 | 7.6251 | 1.9423 | 1.9135 | 2.7116 | 2.827 | 6.5674 | 4.6539 | 11.8947 | 13.8082 | 20.3756 | 25.0295 | 4.2696 | 7.6251 | 1.9423 | 1.9235 | 2.7116 | 2.827 | 6.5674 | 4.6539 | 11.8947 | 13.8182 | 20.3856 | 25.0395 | 0.01
1.8769 | 7.1067 | 1.8626 | 1.7938 | 2.3128 | 2.5877 | 5.9692 | 4.1754 | 8.9835 | 10.7774 | 16.7466 | 20.922 | 1.8769 | 7.1067 | 1.8626 | 1.8038 | 2.3128 | 2.5877 | 5.9692 | 4.1754 | 8.9835 | 10.7874 | 16.7566 | 20.932 | 0.01
1.2769 | 6.9767 | 1.8426 | 1.7638 | 2.2128 | 2.5277 | 5.8192 | 4.0554 | 8.2536 | 10.0174 | 15.8367 | 19.8921 | 1.2769 | 6.9767 | 1.8426 | 1.7738 | 2.2128 | 2.5277 | 5.8192 | 4.0554 | 8.2536 | 10.0274 | 15.8467 | 19.9021 | 0.01
4.4293 | 7.6597 | 1.9476 | 1.9215 | 2.7382 | 2.8429 | 6.6073 | 4.6859 | 12.089 | 14.0105 | 20.6178 | 25.3037 | 4.4293 | 7.6597 | 1.9476 | 1.9315 | 2.7382 | 2.8429 | 6.6073 | 4.6859 | 12.089 | 14.0205 | 20.6278 | 25.3137 | 0.01
-0.71252 | 6.5456 | 1.7762 | 1.6644 | 1.8812 | 2.3287 | 5.3219 | 3.6575 | 5.8331 | 7.4975 | 12.8193 | 16.4768 | -0.71252 | 6.5456 | 1.7762 | 1.6744 | 1.8812 | 2.3287 | 5.3219 | 3.6575 | 5.8331 | 7.5075 | 12.8293 | 16.4868 | 0.01
0.56209 | 6.8218 | 1.8187 | 1.7281 | 2.0937 | 2.4562 | 5.6405 | 3.9124 | 7.3839 | 9.112 | 14.7525 | 18.6649 | 0.56209 | 6.8218 | 1.8187 | 1.7381 | 2.0937 | 2.4562 | 5.6405 | 3.9124 | 7.3839 | 9.122 | 14.7625 | 18.6749 | 0.01
3.2537 | 7.405 | 1.9085 | 1.8627 | 2.5423 | 2.7254 | 6.3134 | 4.4507 | 10.6587 | 12.5214 | 18.8348 | 23.2856 | 3.2537 | 7.405 | 1.9085 | 1.8727 | 2.5423 | 2.7254 | 6.3134 | 4.4507 | 10.6587 | 12.5314 | 18.8448 | 23.2956 | 0.01
4.564 | 7.6889 | 1.9521 | 1.9282 | 2.7607 | 2.8564 | 6.641 | 4.7128 | 12.2529 | 14.1811 | 20.8221 | 25.5349 | 4.564 | 7.6889 | 1.9521 | 1.9382 | 2.7607 | 2.8564 | 6.641 | 4.7128 | 12.2529 | 14.1911 | 20.8321 | 25.5449 | 0.01
17.5236 | 10.4968 | 2.3841 | 2.5762 | 4.9206 | 4.1524 | 9.8809 | 7.3047 | 28.0204 | 30.5966 | 40.4775 | 47.7823 | 17.5236 | 10.4968 | 2.3841 | 2.5862 | 4.9206 | 4.1524 | 9.8809 | 7.3047 | 28.0204 | 30.6066 | 40.4875 | 47.7923 | 0.01
8.2391 | 8.4851 | 2.0746 | 2.112 | 3.3732 | 3.2239 | 7.5598 | 5.4478 | 16.7242 | 18.8362 | 26.396 | 31.8438 | 8.2391 | 8.4851 | 2.0746 | 2.122 | 3.3732 | 3.2239 | 7.5598 | 5.4478 | 16.7242 | 18.8462 | 26.406 | 31.8538 | 0.01
11.3647 | 9.1623 | 2.1788 | 2.2682 | 3.8941 | 3.5365 | 8.3412 | 6.0729 | 20.527 | 22.7953 | 31.1364 | 37.2094 | 11.3647 | 9.1623 | 2.1788 | 2.2782 | 3.8941 | 3.5365 | 8.3412 | 6.0729 | 20.527 | 22.8053 | 31.1464 | 37.2194 | 0.01
-1.6549 | 6.3414 | 1.7448 | 1.6173 | 1.7242 | 2.2345 | 5.0863 | 3.469 | 4.6866 | 6.3038 | 11.3901 | 14.8591 | -1.6549 | 6.3414 | 1.7448 | 1.6273 | 1.7242 | 2.2345 | 5.0863 | 3.469 | 4.6866 | 6.3138 | 11.4001 | 14.8691 | 0.01
8.9418 | 8.6374 | 2.0981 | 2.1471 | 3.4903 | 3.2942 | 7.7354 | 5.5884 | 17.5791 | 19.7262 | 27.4617 | 33.05 | 8.9418 | 8.6374 | 2.0981 | 2.1571 | 3.4903 | 3.2942 | 7.7354 | 5.5884 | 17.5791 | 19.7362 | 27.4717 | 33.06 | 0.01
11.8561 | 9.2688 | 2.1952 | 2.2928 | 3.976 | 3.5856 | 8.464 | 6.1712 | 21.1249 | 23.4177 | 31.8817 | 38.053 | 11.8561 | 9.2688 | 2.1952 | 2.3028 | 3.976 | 3.5856 | 8.464 | 6.1712 | 21.1249 | 23.4277 | 31.8917 | 38.063 | 0.01
10.4949 | 8.9739 | 2.1498 | 2.2247 | 3.7492 | 3.4495 | 8.1237 | 5.899 | 19.4688 | 21.6936 | 29.8173 | 35.7163 | 10.4949 | 8.9739 | 2.1498 | 2.2347 | 3.7492 | 3.4495 | 8.1237 | 5.899 | 19.4688 | 21.7036 | 29.8273 | 35.7263 | 0.01
10.916 | 9.0651 | 2.1639 | 2.2458 | 3.8193 | 3.4916 | 8.229 | 5.9832 | 19.9811 | 22.2269 | 30.4559 | 36.4391 | 10.916 | 9.0651 | 2.1639 | 2.2558 | 3.8193 | 3.4916 | 8.229 | 5.9832 | 19.9811 | 22.2369 | 30.4659 | 36.4491 | 0.01
9.4413 | 8.7456 | 2.1147 | 2.1721 | 3.5736 | 3.3441 | 7.8603 | 5.6883 | 18.1869 | 20.359 | 28.2193 | 33.9076 | 9.4413 | 8.7456 | 2.1147 | 2.1821 | 3.5736 | 3.3441 | 7.8603 | 5.6883 | 18.1869 | 20.369 | 28.2293 | 33.9176 | 0.01
3.8479 | 7.5337 | 1.9283 | 1.8924 | 2.6413 | 2.7848 | 6.462 | 4.5696 | 11.3817 | 13.2741 | 19.7361 | 24.3056 | 3.8479 | 7.5337 | 1.9283 | 1.9024 | 2.6413 | 2.7848 | 6.462 | 4.5696 | 11.3817 | 13.2841 | 19.7461 | 24.3156 | 0.01
0.12473 | 6.727 | 1.8042 | 1.7062 | 2.0208 | 2.4125 | 5.5312 | 3.8249 | 6.8518 | 8.558 | 14.0892 | 17.9141 | 0.12473 | 6.727 | 1.8042 | 1.7162 | 2.0208 | 2.4125 | 5.5312 | 3.8249 | 6.8518 | 8.568 | 14.0992 | 17.9241 | 0.01
15.3826 | 10.0329 | 2.3128 | 2.4691 | 4.5638 | 3.9383 | 9.3457 | 6.8765 | 25.4155 | 27.8847 | 37.2303 | 44.1068 | 15.3826 | 10.0329 | 2.3128 | 2.4791 | 4.5638 | 3.9383 | 9.3457 | 6.8765 | 25.4155 | 27.8947 | 37.2403 | 44.1168 | 0.01
5.5747 | 7.9078 | 1.9858 | 1.9787 | 2.9291 | 2.9575 | 6.8937 | 4.9149 | 13.4825 | 15.4613 | 22.3549 | 27.2699 | 5.5747 | 7.9078 | 1.9858 | 1.9887 | 2.9291 | 2.9575 | 6.8937 | 4.9149 | 13.4825 | 15.4713 | 22.3649 | 27.2799 | 0.01
7.5314 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8632 | 17.9398 | 25.3227 | 30.629 | 7.5314 | 8.3318 | 2.051 | 2.0866 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8632 | 17.9498 | 25.3327 | 30.639 | 0.01
5.6536 | 7.9249 | 1.9885 | 1.9827 | 2.9423 | 2.9654 | 6.9134 | 4.9307 | 13.5786 | 15.5612 | 22.4746 | 27.4054 | 5.6536 | 7.9249 | 1.9885 | 1.9927 | 2.9423 | 2.9654 | 6.9134 | 4.9307 | 13.5786 | 15.5712 | 22.4846 | 27.4154 | 0.01
7.9005 | 8.4118 | 2.0633 | 2.095 | 3.3167 | 3.19 | 7.4751 | 5.3801 | 16.3122 | 18.4073 | 25.8824 | 31.2625 | 7.9005 | 8.4118 | 2.0633 | 2.105 | 3.3167 | 3.19 | 7.4751 | 5.3801 | 16.3122 | 18.4173 | 25.8924 | 31.2725 | 0.01
2.7503 | 7.2959 | 1.8917 | 1.8375 | 2.4584 | 2.675 | 6.1876 | 4.3501 | 10.0462 | 11.8837 | 18.0713 | 22.4213 | 2.7503 | 7.2959 | 1.8917 | 1.8475 | 2.4584 | 2.675 | 6.1876 | 4.3501 | 10.0462 | 11.8937 | 18.0813 | 22.4313 | 0.01
15.9912 | 10.1648 | 2.333 | 2.4996 | 4.6652 | 3.9991 | 9.4978 | 6.9982 | 26.156 | 28.6556 | 38.1534 | 45.1516 | 15.9912 | 10.1648 | 2.333 | 2.5096 | 4.6652 | 3.9991 | 9.4978 | 6.9982 | 26.156 | 28.6656 | 38.1634 | 45.1616 | 0.01
3.5741 | 7.4744 | 1.9191 | 1.8787 | 2.5957 | 2.7574 | 6.3935 | 4.5148 | 11.0485 | 12.9272 | 19.3207 | 23.8356 | 3.5741 | 7.4744 | 1.9191 | 1.8887 | 2.5957 | 2.7574 | 6.3935 | 4.5148 | 11.0485 | 12.9372 | 19.3307 | 23.8456 | 0.01
8.2161 | 8.4802 | 2.0739 | 2.1108 | 3.3693 | 3.2216 | 7.554 | 5.4432 | 16.6962 | 18.8071 | 26.3611 | 31.8043 | 8.2161 | 8.4802 | 2.0739 | 2.1208 | 3.3693 | 3.2216 | 7.554 | 5.4432 | 16.6962 | 18.8171 | 26.3711 | 31.8143 | 0.01
11.5303 | 9.1982 | 2.1843 | 2.2765 | 3.9217 | 3.553 | 8.3826 | 6.1061 | 20.7286 | 23.0051 | 31.3877 | 37.4937 | 11.5303 | 9.1982 | 2.1843 | 2.2865 | 3.9217 | 3.553 | 8.3826 | 6.1061 | 20.7286 | 23.0151 | 31.3977 | 37.5037 | 0.01
9.1597 | 8.6846 | 2.1053 | 2.158 | 3.5266 | 3.316 | 7.7899 | 5.6319 | 17.8443 | 20.0023 | 27.7923 | 33.4242 | 9.1597 | 8.6846 | 2.1053 | 2.168 | 3.5266 | 3.316 | 7.7899 | 5.6319 | 17.8443 | 20.0123 | 27.8023 | 33.4342 | 0.01
12.984 | 9.5132 | 2.2328 | 2.3492 | 4.164 | 3.6984 | 8.746 | 6.3968 | 22.4972 | 24.8464 | 33.5924 | 39.9892 | 12.984 | 9.5132 | 2.2328 | 2.3592 | 4.164 | 3.6984 | 8.746 | 6.3968 | 22.4972 | 24.8564 | 33.6024 | 39.9992 | 0.01
18.7844 | 10.7699 | 2.4261 | 2.6392 | 5.1307 | 4.2784 | 10.1961 | 7.5569 | 29.5543 | 32.1935 | 42.3896 | 49.9465 | 18.7844 | 10.7699 | 2.4261 | 2.6492 | 5.1307 | 4.2784 | 10.1961 | 7.5569 | 29.5543 | 32.2035 | 42.3996 | 49.9565 | 0.01
9.9286 | 8.8512 | 2.131 | 2.1964 | 3.6548 | 3.3929 | 7.9822 | 5.7857 | 18.7799 | 20.9763 | 28.9585 | 34.7442 | 9.9286 | 8.8512 | 2.131 | 2.2064 | 3.6548 | 3.3929 | 7.9822 | 5.7857 | 18.7799 | 20.9863 | 28.9685 | 34.7542 | 0.01
2.0856 | 7.1519 | 1.8695 | 1.8043 | 2.3476 | 2.6086 | 6.0214 | 4.2171 | 9.2375 | 11.0418 | 17.0632 | 21.2803 | 2.0856 | 7.1519 | 1.8695 | 1.8143 | 2.3476 | 2.6086 | 6.0214 | 4.2171 | 9.2375 | 11.0518 | 17.0732 | 21.2903 | 0.01
7.7123 | 8.371 | 2.0571 | 2.0856 | 3.2854 | 3.1712 | 7.4281 | 5.3425 | 16.0833 | 18.169 | 25.5971 | 30.9395 | 7.7123 | 8.371 | 2.0571 | 2.0956 | 3.2854 | 3.1712 | 7.4281 | 5.3425 | 16.0833 | 18.179 | 25.6071 | 30.9495 | 0.01
4.3418 | 7.6407 | 1.9447 | 1.9171 | 2.7236 | 2.8342 | 6.5855 | 4.6684 | 11.9825 | 13.8996 | 20.4851 | 25.1535 | 4.3418 | 7.6407 | 1.9447 | 1.9271 | 2.7236 | 2.8342 | 6.5855 | 4.6684 | 11.9825 | 13.9096 | 20.4951 | 25.1635 | 0.01
11.026 | 9.089 | 2.1675 | 2.2513 | 3.8377 | 3.5026 | 8.2565 | 6.0052 | 20.115 | 22.3663 | 30.6228 | 36.628 | 11.026 | 9.089 | 2.1675 | 2.2613 | 3.8377 | 3.5026 | 8.2565 | 6.0052 | 20.115 | 22.3763 | 30.6328 | 36.638 | 0.01
17.0012 | 10.3836 | 2.3667 | 2.5501 | 4.8335 | 4.1001 | 9.7503 | 7.2002 | 27.3849 | 29.9349 | 39.6852 | 46.8855 | 17.0012 | 10.3836 | 2.3667 | 2.5601 | 4.8335 | 4.1001 | 9.7503 | 7.2002 | 27.3849 | 29.9449 | 39.6952 | 46.8955 | 0.01
2.8353 | 7.3143 | 1.8945 | 1.8418 | 2.4726 | 2.6835 | 6.2088 | 4.3671 | 10.1496 | 11.9914 | 18.2002 | 22.5673 | 2.8353 | 7.3143 | 1.8945 | 1.8518 | 2.4726 | 2.6835 | 6.2088 | 4.3671 | 10.1496 | 12.0014 | 18.2102 | 22.5773 | 0.01
2.9314 | 7.3351 | 1.8977 | 1.8466 | 2.4886 | 2.6931 | 6.2329 | 4.3863 | 10.2666 | 12.1132 | 18.346 | 22.7323 | 2.9314 | 7.3351 | 1.8977 | 1.8566 | 2.4886 | 2.6931 | 6.2329 | 4.3863 | 10.2666 | 12.1232 | 18.356 | 22.7423 | 0.01
0.2458 | 6.7533 | 1.8082 | 1.7123 | 2.041 | 2.4246 | 5.5615 | 3.8492 | 6.9991 | 8.7114 | 14.2728 | 18.122 | 0.2458 | 6.7533 | 1.8082 | 1.7223 | 2.041 | 2.4246 | 5.5615 | 3.8492 | 6.9991 | 8.7214 | 14.2828 | 18.132 | 0.01
6.4896 | 8.1061 | 2.0163 | 2.0245 | 3.0816 | 3.049 | 7.1224 | 5.0979 | 14.5957 | 16.6202 | 23.7426 | 28.8405 | 6.4896 | 8.1061 | 2.0163 | 2.0345 | 3.0816 | 3.049 | 7.1224 | 5.0979 | 14.5957 | 16.6302 | 23.7526 | 28.8505 | 0.01
-6.0201 | 5.3956 | 1.5993 | 1.399 | 0.99665 | 1.798 | 3.995 | 2.596 | -0.62448 | 0.77452 | 4.7695 | 7.3655 | -6.0201 | 5.3956 | 1.5993 | 1.409 | 0.99665 | 1.798 | 3.995 | 2.596 | -0.62448 | 0.78452 | 4.7795 | 7.3755 | 0.01
3.3036 | 7.4158 | 1.9101 | 1.8652 | 2.5506 | 2.7304 | 6.3259 | 4.4607 | 10.7194 | 12.5846 | 18.9105 | 23.3712 | 3.3036 | 7.4158 | 1.9101 | 1.8752 | 2.5506 | 2.7304 | 6.3259 | 4.4607 | 10.7194 | 12.5946 | 18.9205 | 23.3812 | 0.01
8.8664 | 8.621 | 2.0955 | 2.1433 | 3.4777 | 3.2866 | 7.7166 | 5.5733 | 17.4874 | 19.6307 | 27.3473 | 32.9206 | 8.8664 | 8.621 | 2.0955 | 2.1533 | 3.4777 | 3.2866 | 7.7166 | 5.5733 | 17.4874 | 19.6407 | 27.3573 | 32.9306 | 0.01
13.6777 | 9.6635 | 2.2559 | 2.3839 | 4.2796 | 3.7678 | 8.9194 | 6.5355 | 23.3412 | 25.7251 | 34.6446 | 41.1801 | 13.6777 | 9.6635 | 2.2559 | 2.3939 | 4.2796 | 3.7678 | 8.9194 | 6.5355 | 23.3412 | 25.7351 | 34.6546 | 41.1901 | 0.01
7.5315 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8633 | 17.9399 | 25.3228 | 30.629 | 7.5315 | 8.3318 | 2.051 | 2.0866 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8633 | 17.9499 | 25.3328 | 30.639 | 0.01
6.5002 | 8.1084 | 2.0167 | 2.025 | 3.0834 | 3.05 | 7.1251 | 5.1 | 14.6086 | 16.6336 | 23.7587 | 28.8587 | 6.5002 | 8.1084 | 2.0167 | 2.035 | 3.0834 | 3.05 | 7.1251 | 5.1 | 14.6086 | 16.6436 | 23.7687 | 28.8687 | 0.01
12.3442 | 9.3746 | 2.2115 | 2.3172 | 4.0574 | 3.6344 | 8.586 | 6.2688 | 21.7187 | 24.036 | 32.622 | 38.8908 | 12.3442 | 9.3746 | 2.2115 | 2.3272 | 4.0574 | 3.6344 | 8.586 | 6.2688 | 21.7187 | 24.046 | 32.632 | 38.9008 | 0.01
-2.6847 | 6.1183 | 1.7105 | 1.5658 | 1.5526 | 2.1315 | 4.8288 | 3.2631 | 3.4337 | 4.9994 | 9.8283 | 13.0913 | -2.6847 | 6.1183 | 1.7105 | 1.5758 | 1.5526 | 2.1315 | 4.8288 | 3.2631 | 3.4337 | 5.0094 | 9.8383 | 13.1013 | 0.01
11.3098 | 9.1505 | 2.177 | 2.2655 | 3.885 | 3.531 | 8.3274 | 6.062 | 20.4602 | 22.7257 | 31.0532 | 37.1151 | 11.3098 | 9.1505 | 2.177 | 2.2755 | 3.885 | 3.531 | 8.3274 | 6.062 | 20.4602 | 22.7357 | 31.0632 | 37.1251 | 0.01
11.2312 | 9.1334 | 2.1744 | 2.2616 | 3.8719 | 3.5231 | 8.3078 | 6.0462 | 20.3646 | 22.6262 | 30.934 | 36.9802 | 11.2312 | 9.1334 | 2.1744 | 2.2716 | 3.8719 | 3.5231 | 8.3078 | 6.0462 | 20.3646 | 22.6362 | 30.944 | 36.9902 | 0.01
-2.2417 | 6.2143 | 1.7253 | 1.5879 | 1.6264 | 2.1758 | 4.9396 | 3.3517 | 3.9725 | 5.5605 | 10.5 | 13.8517 | -2.2417 | 6.2143 | 1.7253 | 1.5979 | 1.6264 | 2.1758 | 4.9396 | 3.3517 | 3.9725 | 5.5705 | 10.51 | 13.8617 | 0.01
13.1798 | 9.5556 | 2.2393 | 2.359 | 4.1966 | 3.718 | 8.795 | 6.436 | 22.7354 | 25.0944 | 33.8894 | 40.3253 | 13.1798 | 9.5556 | 2.2393 | 2.369 | 4.1966 | 3.718 | 8.795 | 6.436 | 22.7354 | 25.1044 | 33.8994 | 40.3353 | 0.01
-6.0136 | 5.397 | 1.5995 | 1.3993 | 0.99773 | 1.7986 | 3.9966 | 2.5973 | -0.61658 | 0.78274 | 4.7793 | 7.3766 | -6.0136 | 5.397 | 1.5995 | 1.4093 | 0.99773 | 1.7986 | 3.9966 | 2.5973 | -0.61658 | 0.79274 | 4.7893 | 7.3866 | 0.01
2.8839 | 7.3249 | 1.8961 | 1.8442 | 2.4807 | 2.6884 | 6.221 | 4.3768 | 10.2088 | 12.053 | 18.274 | 22.6508 | 2.8839 | 7.3249 | 1.8961 | 1.8542 | 2.4807 | 2.6884 | 6.221 | 4.3768 | 10.2088 | 12.063 | 18.284 | 22.6608 | 0.01
8.9173 | 8.6321 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5835 | 17.5494 | 19.6953 | 27.4246 | 33.0081 | 8.9173 | 8.6321 | 2.0972 | 2.1559 | 3.4862 | 3.2917 | 7.7293 | 5.5835 | 17.5494 | 19.7053 | 27.4346 | 33.0181 | 0.01
7.3594 | 8.2945 | 2.0453 | 2.068 | 3.2266 | 3.1359 | 7.3399 | 5.2719 | 15.654 | 17.722 | 25.0618 | 30.3337 | 7.3594 | 8.2945 | 2.0453 | 2.078 | 3.2266 | 3.1359 | 7.3399 | 5.2719 | 15.654 | 17.732 | 25.0718 | 30.3437 | 0.01
10.6967 | 9.0176 | 2.1566 | 2.2348 | 3.7828 | 3.4697 | 8.1742 | 5.9393 | 19.7143 | 21.9491 | 30.1233 | 36.0626 | 10.6967 | 9.0176 | 2.1566 | 2.2448 | 3.7828 | 3.4697 | 8.1742 | 5.9393 | 19.7143 | 21.9591 | 30.1333 | 36.0726 | 0.01
14.8238 | 9.9118 | 2.2941 | 2.4412 | 4.4706 | 3.8824 | 9.206 | 6.7648 | 24.7356 | 27.1768 | 36.3828 | 43.1475 | 14.8238 | 9.9118 | 2.2941 | 2.4512 | 4.4706 | 3.8824 | 9.206 | 6.7648 | 24.7356 | 27.1868 | 36.3928 | 43.1575 | 0.01
11.6384 | 9.2216 | 2.1879 | 2.2819 | 3.9397 | 3.5638 | 8.4096 | 6.1277 | 20.86 | 23.1419 | 31.5515 | 37.6792 | 11.6384 | 9.2216 | 2.1879 | 2.2919 | 3.9397 | 3.5638 | 8.4096 | 6.1277 | 20.86 | 23.1519 | 31.5615 | 37.6892 | 0.01
17.6788 | 10.5304 | 2.3893 | 2.5839 | 4.9465 | 4.1679 | 9.9197 | 7.3358 | 28.2092 | 30.7931 | 40.7128 | 48.0486 | 17.6788 | 10.5304 | 2.3893 | 2.5939 | 4.9465 | 4.1679 | 9.9197 | 7.3358 | 28.2092 | 30.8031 | 40.7228 | 48.0586 | 0.01
4.3589 | 7.6444 | 1.9453 | 1.9179 | 2.7265 | 2.8359 | 6.5897 | 4.6718 | 12.0033 | 13.9213 | 20.511 | 25.1828 | 4.3589 | 7.6444 | 1.9453 | 1.9279 | 2.7265 | 2.8359 | 6.5897 | 4.6718 | 12.0033 | 13.9313 | 20.521 | 25.1928 | 0.01
0.47148 | 6.8022 | 1.8157 | 1.7236 | 2.0786 | 2.4471 | 5.6179 | 3.8943 | 7.2736 | 8.9972 | 14.6151 | 18.5094 | 0.47148 | 6.8022 | 1.8157 | 1.7336 | 2.0786 | 2.4471 | 5.6179 | 3.8943 | 7.2736 | 9.0072 | 14.6251 | 18.5194 | 0.01
7.8912 | 8.4097 | 2.063 | 2.0946 | 3.3152 | 3.1891 | 7.4728 | 5.3782 | 16.3009 | 18.3955 | 25.8682 | 31.2465 | 7.8912 | 8.4097 | 2.063 | 2.1046 | 3.3152 | 3.1891 | 7.4728 | 5.3782 | 16.3009 | 18.4055 | 25.8782 | 31.2565 | 0.01
4.3809 | 7.6492 | 1.946 | 1.919 | 2.7301 | 2.8381 | 6.5952 | 4.6762 | 12.0301 | 13.9491 | 20.5444 | 25.2205 | 4.3809 | 7.6492 | 1.946 | 1.929 | 2.7301 | 2.8381 | 6.5952 | 4.6762 | 12.0301 | 13.9591 | 20.5544 | 25.2305 | 0.01
12.5045 | 9.4093 | 2.2168 | 2.3252 | 4.0841 | 3.6505 | 8.6261 | 6.3009 | 21.9138 | 24.2391 | 32.8652 | 39.1661 | 12.5045 | 9.4093 | 2.2168 | 2.3352 | 4.0841 | 3.6505 | 8.6261 | 6.3009 | 21.9138 | 24.2491 | 32.8752 | 39.1761 | 0.01
-2.5623 | 6.1448 | 1.7146 | 1.5719 | 1.5729 | 2.1438 | 4.8594 | 3.2875 | 3.5825 | 5.1544 | 10.0138 | 13.3013 | -2.5623 | 6.1448 | 1.7146 | 1.5819 | 1.5729 | 2.1438 | 4.8594 | 3.2875 | 3.5825 | 5.1644 | 10.0238 | 13.3113 | 0.01
5.628 | 7.9194 | 1.9876 | 1.9814 | 2.938 | 2.9628 | 6.907 | 4.9256 | 13.5474 | 15.5288 | 22.4358 | 27.3614 | 5.628 | 7.9194 | 1.9876 | 1.9914 | 2.938 | 2.9628 | 6.907 | 4.9256 | 13.5474 | 15.5388 | 22.4458 | 27.3714 | 0.01
-2.8667 | 6.0789 | 1.7044 | 1.5567 | 1.5222 | 2.1133 | 4.7833 | 3.2267 | 3.2122 | 4.7689 | 9.5522 | 12.7789 | -2.8667 | 6.0789 | 1.7044 | 1.5667 | 1.5222 | 2.1133 | 4.7833 | 3.2267 | 3.2122 | 4.7789 | 9.5622 | 12.7889 | 0.01
-6.8201 | 5.2223 | 1.5727 | 1.359 | 0.86332 | 1.718 | 3.795 | 2.436 | -1.5977 | -0.23874 | 3.5562 | 5.9922 | -6.8201 | 5.2223 | 1.5727 | 1.369 | 0.86332 | 1.718 | 3.795 | 2.436 | -1.5977 | -0.22874 | 3.5662 | 6.0022 | 0.01
-0.06598 | 6.6857 | 1.7978 | 1.6967 | 1.989 | 2.3934 | 5.4835 | 3.7868 | 6.6197 | 8.3164 | 13.7999 | 17.5867 | -0.06598 | 6.6857 | 1.7978 | 1.7067 | 1.989 | 2.3934 | 5.4835 | 3.7868 | 6.6197 | 8.3264 | 13.8099 | 17.5967 | 0.01
-4.274 | 5.774 | 1.6575 | 1.4863 | 1.2877 | 1.9726 | 4.4315 | 2.9452 | 1.4999 | 2.9862 | 7.4177 | 10.3629 | -4.274 | 5.774 | 1.6575 | 1.4963 | 1.2877 | 1.9726 | 4.4315 | 2.9452 | 1.4999 | 2.9962 | 7.4277 | 10.3729 | 0.01
9.4 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.85 | 5.68 | 18.1367 | 20.3067 | 28.1567 | 33.8367 | 9.4 | 8.7367 | 2.1133 | 2.18 | 3.5667 | 3.34 | 7.85 | 5.68 | 18.1367 | 20.3167 | 28.1667 | 33.8467 | 0.01
-0.6032 | 6.5693 | 1.7799 | 1.6698 | 1.8995 | 2.3397 | 5.3492 | 3.6794 | 5.9661 | 7.6359 | 12.9851 | 16.6645 | -0.6032 | 6.5693 | 1.7799 | 1.6798 | 1.8995 | 2.3397 | 5.3492 | 3.6794 | 5.9661 | 7.6459 | 12.9951 | 16.6745 | 0.01
0.58262 | 6.8262 | 1.8194 | 1.7291 | 2.0971 | 2.4583 | 5.6457 | 3.9165 | 7.4089 | 9.138 | 14.7836 | 18.7002 | 0.58262 | 6.8262 | 1.8194 | 1.7391 | 2.0971 | 2.4583 | 5.6457 | 3.9165 | 7.4089 | 9.148 | 14.7936 | 18.7102 | 0.01
6.9663 | 8.2094 | 2.0322 | 2.0483 | 3.161 | 3.0966 | 7.2416 | 5.1933 | 15.1756 | 17.2239 | 24.4655 | 29.6587 | 6.9663 | 8.2094 | 2.0322 | 2.0583 | 3.161 | 3.0966 | 7.2416 | 5.1933 | 15.1756 | 17.2339 | 24.4755 | 29.6687 | 0.01
8.3163 | 8.5019 | 2.0772 | 2.1158 | 3.386 | 3.2316 | 7.5791 | 5.4633 | 16.8181 | 18.9339 | 26.513 | 31.9762 | 8.3163 | 8.5019 | 2.0772 | 2.1258 | 3.386 | 3.2316 | 7.5791 | 5.4633 | 16.8181 | 18.9439 | 26.523 | 31.9862 | 0.01
-4.5469 | 5.7148 | 1.6484 | 1.4727 | 1.2422 | 1.9453 | 4.3633 | 2.8906 | 1.1679 | 2.6406 | 7.0038 | 9.8944 | -4.5469 | 5.7148 | 1.6484 | 1.4827 | 1.2422 | 1.9453 | 4.3633 | 2.8906 | 1.1679 | 2.6506 | 7.0138 | 9.9044 | 0.01
-7.9943 | 4.9679 | 1.5335 | 1.3003 | 0.66762 | 1.6006 | 3.5014 | 2.2011 | -3.0264 | -1.7261 | 1.7753 | 3.9765 | -7.9943 | 4.9679 | 1.5335 | 1.3103 | 0.66762 | 1.6006 | 3.5014 | 2.2011 | -3.0264 | -1.7161 | 1.7853 | 3.9865 | 0.01
4.1948 | 7.6089 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5487 | 4.639 | 11.8036 | 13.7134 | 20.2621 | 24.901 | 4.1948 | 7.6089 | 1.9398 | 1.9197 | 2.6991 | 2.8195 | 6.5487 | 4.639 | 11.8036 | 13.7234 | 20.2721 | 24.911 | 0.01
0.29908 | 6.7648 | 1.81 | 1.715 | 2.0498 | 2.4299 | 5.5748 | 3.8598 | 7.0639 | 8.7788 | 14.3536 | 18.2134 | 0.29908 | 6.7648 | 1.81 | 1.725 | 2.0498 | 2.4299 | 5.5748 | 3.8598 | 7.0639 | 8.7888 | 14.3636 | 18.2234 | 0.01
2.5167 | 7.2453 | 1.8839 | 1.8258 | 2.4194 | 2.6517 | 6.1292 | 4.3033 | 9.762 | 11.5878 | 17.717 | 22.0203 | 2.5167 | 7.2453 | 1.8839 | 1.8358 | 2.4194 | 2.6517 | 6.1292 | 4.3033 | 9.762 | 11.5978 | 17.727 | 22.0303 | 0.01
14.5896 | 9.8611 | 2.2863 | 2.4295 | 4.4316 | 3.859 | 9.1474 | 6.7179 | 24.4507 | 26.8802 | 36.0276 | 42.7455 | 14.5896 | 9.8611 | 2.2863 | 2.4395 | 4.4316 | 3.859 | 9.1474 | 6.7179 | 24.4507 | 26.8902 | 36.0376 | 42.7555 | 0.01
5.9257 | 7.9839 | 1.9975 | 1.9963 | 2.9876 | 2.9926 | 6.9814 | 4.9851 | 13.9095 | 15.9058 | 22.8872 | 27.8724 | 5.9257 | 7.9839 | 1.9975 | 2.0063 | 2.9876 | 2.9926 | 6.9814 | 4.9851 | 13.9095 | 15.9158 | 22.8972 | 27.8824 | 0.01
4.8036 | 7.7408 | 1.9601 | 1.9402 | 2.8006 | 2.8804 | 6.7009 | 4.7607 | 12.5443 | 14.4845 | 21.1854 | 25.9461 | 4.8036 | 7.7408 | 1.9601 | 1.9502 | 2.8006 | 2.8804 | 6.7009 | 4.7607 | 12.5443 | 14.4945 | 21.1954 | 25.9561 | 0.01
2.8171 | 7.3104 | 1.8939 | 1.8409 | 2.4695 | 2.6817 | 6.2043 | 4.3634 | 10.1275 | 11.9683 | 18.1726 | 22.536 | 2.8171 | 7.3104 | 1.8939 | 1.8509 | 2.4695 | 2.6817 | 6.2043 | 4.3634 | 10.1275 | 11.9783 | 18.1826 | 22.546 | 0.01
7.7332 | 8.3755 | 2.0578 | 2.0867 | 3.2889 | 3.1733 | 7.4333 | 5.3466 | 16.1088 | 18.1954 | 25.6287 | 30.9754 | 7.7332 | 8.3755 | 2.0578 | 2.0967 | 3.2889 | 3.1733 | 7.4333 | 5.3466 | 16.1088 | 18.2054 | 25.6387 | 30.9854 | 0.01
10.7305 | 9.0249 | 2.1577 | 2.2365 | 3.7884 | 3.473 | 8.1826 | 5.9461 | 19.7554 | 21.9919 | 30.1745 | 36.1206 | 10.7305 | 9.0249 | 2.1577 | 2.2465 | 3.7884 | 3.473 | 8.1826 | 5.9461 | 19.7554 | 22.0019 | 30.1845 | 36.1306 | 0.01
8.4966 | 8.5409 | 2.0832 | 2.1248 | 3.4161 | 3.2497 | 7.6242 | 5.4993 | 17.0375 | 19.1624 | 26.7865 | 32.2858 | 8.4966 | 8.5409 | 2.0832 | 2.1348 | 3.4161 | 3.2497 | 7.6242 | 5.4993 | 17.0375 | 19.1724 | 26.7965 | 32.2958 | 0.01
-8.2772 | 4.9066 | 1.5241 | 1.2861 | 0.62047 | 1.5723 | 3.4307 | 2.1446 | -3.3706 | -2.0844 | 1.3463 | 3.4908 | -8.2772 | 4.9066 | 1.5241 | 1.2961 | 0.62047 | 1.5723 | 3.4307 | 2.1446 | -3.3706 | -2.0744 | 1.3563 | 3.5008 | 0.01
8.6945 | 8.5838 | 2.0898 | 2.1347 | 3.4491 | 3.2695 | 7.6736 | 5.5389 | 17.2783 | 19.413 | 27.0867 | 32.6256 | 8.6945 | 8.5838 | 2.0898 | 2.1447 | 3.4491 | 3.2695 | 7.6736 | 5.5389 | 17.2783 | 19.423 | 27.0967 | 32.6356 | 0.01
4.4416 | 7.6624 | 1.9481 | 1.9221 | 2.7403 | 2.8442 | 6.6104 | 4.6883 | 12.104 | 14.0261 | 20.6365 | 25.3248 | 4.4416 | 7.6624 | 1.9481 | 1.9321 | 2.7403 | 2.8442 | 6.6104 | 4.6883 | 12.104 | 14.0361 | 20.6465 | 25.3348 | 0.01
4.5166 | 7.6786 | 1.9506 | 1.9258 | 2.7528 | 2.8517 | 6.6292 | 4.7033 | 12.1953 | 14.1211 | 20.7502 | 25.4536 | 4.5166 | 7.6786 | 1.9506 | 1.9358 | 2.7528 | 2.8517 | 6.6292 | 4.7033 | 12.1953 | 14.1311 | 20.7602 | 25.4636 | 0.01
7.1372 | 8.2464 | 2.0379 | 2.0569 | 3.1895 | 3.1137 | 7.2843 | 5.2274 | 15.3835 | 17.4404 | 24.7247 | 29.9521 | 7.1372 | 8.2464 | 2.0379 | 2.0669 | 3.1895 | 3.1137 | 7.2843 | 5.2274 | 15.3835 | 17.4504 | 24.7347 | 29.9621 | 0.01
9.3226 | 8.7199 | 2.1108 | 2.1661 | 3.5538 | 3.3323 | 7.8307 | 5.6645 | 18.0425 | 20.2087 | 28.0393 | 33.7039 | 9.3226 | 8.7199 | 2.1108 | 2.1761 | 3.5538 | 3.3323 | 7.8307 | 5.6645 | 18.0425 | 20.2187 | 28.0493 | 33.7139 | 0.01
1.1275 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7819 | 4.0255 | 8.0717 | 9.8281 | 15.61 | 19.6355 | 1.1275 | 6.9443 | 1.8376 | 1.7664 | 2.1879 | 2.5127 | 5.7819 | 4.0255 | 8.0717 | 9.8381 | 15.62 | 19.6455 | 0.01
-2.6418 | 6.1276 | 1.7119 | 1.5679 | 1.5597 | 2.1358 | 4.8395 | 3.2716 | 3.4858 | 5.0537 | 9.8932 | 13.1649 | -2.6418 | 6.1276 | 1.7119 | 1.5779 | 1.5597 | 2.1358 | 4.8395 | 3.2716 | 3.4858 | 5.0637 | 9.9032 | 13.1749 | 0.01
9.0604 | 8.6631 | 2.102 | 2.153 | 3.5101 | 3.306 | 7.7651 | 5.6121 | 17.7234 | 19.8765 | 27.6415 | 33.2536 | 9.0604 | 8.6631 | 2.102 | 2.163 | 3.5101 | 3.306 | 7.7651 | 5.6121 | 17.7234 | 19.8865 | 27.6515 | 33.2636 | 0.01
10.6866 | 9.0154 | 2.1562 | 2.2343 | 3.7811 | 3.4687 | 8.1717 | 5.9373 | 19.7021 | 21.9364 | 30.1081 | 36.0454 | 10.6866 | 9.0154 | 2.1562 | 2.2443 | 3.7811 | 3.4687 | 8.1717 | 5.9373 | 19.7021 | 21.9464 | 30.1181 | 36.0554 | 0.01
8.5379 | 8.5499 | 2.0846 | 2.1269 | 3.423 | 3.2538 | 7.6345 | 5.5076 | 17.0878 | 19.2146 | 26.8491 | 32.3567 | 8.5379 | 8.5499 | 2.0846 | 2.1369 | 3.423 | 3.2538 | 7.6345 | 5.5076 | 17.0878 | 19.2246 | 26.8591 | 32.3667 | 0.01
1.8028 | 7.0906 | 1.8601 | 1.7901 | 2.3005 | 2.5803 | 5.9507 | 4.1606 | 8.8935 | 10.6836 | 16.6343 | 20.7949 | 1.8028 | 7.0906 | 1.8601 | 1.8001 | 2.3005 | 2.5803 | 5.9507 | 4.1606 | 8.8935 | 10.6936 | 16.6443 | 20.8049 | 0.01
0.2989 | 6.7648 | 1.81 | 1.7149 | 2.0498 | 2.4299 | 5.5747 | 3.8598 | 7.0637 | 8.7786 | 14.3533 | 18.2131 | 0.2989 | 6.7648 | 1.81 | 1.7249 | 2.0498 | 2.4299 | 5.5747 | 3.8598 | 7.0637 | 8.7886 | 14.3633 | 18.2231 | 0.01
-0.13421 | 6.6709 | 1.7955 | 1.6933 | 1.9776 | 2.3866 | 5.4664 | 3.7732 | 6.5367 | 8.23 | 13.6965 | 17.4696 | -0.13421 | 6.6709 | 1.7955 | 1.7033 | 1.9776 | 2.3866 | 5.4664 | 3.7732 | 6.5367 | 8.24 | 13.7065 | 17.4796 | 0.01
7.0264 | 8.2224 | 2.0342 | 2.0513 | 3.1711 | 3.1026 | 7.2566 | 5.2053 | 15.2488 | 17.3001 | 24.5567 | 29.762 | 7.0264 | 8.2224 | 2.0342 | 2.0613 | 3.1711 | 3.1026 | 7.2566 | 5.2053 | 15.2488 | 17.3101 | 24.5667 | 29.772 | 0.01
15.9381 | 10.1533 | 2.3313 | 2.4969 | 4.6563 | 3.9938 | 9.4845 | 6.9876 | 26.0913 | 28.5883 | 38.0728 | 45.0604 | 15.9381 | 10.1533 | 2.3313 | 2.5069 | 4.6563 | 3.9938 | 9.4845 | 6.9876 | 26.0913 | 28.5983 | 38.0828 | 45.0704 | 0.01
4.2657 | 7.6242 | 1.9422 | 1.9133 | 2.711 | 2.8266 | 6.5664 | 4.6531 | 11.89 | 13.8033 | 20.3697 | 25.0229 | 4.2657 | 7.6242 | 1.9422 | 1.9233 | 2.711 | 2.8266 | 6.5664 | 4.6531 | 11.89 | 13.8133 | 20.3797 | 25.0329 | 0.01
-1.1135 | 6.4587 | 1.7629 | 1.6443 | 1.8144 | 2.2886 | 5.2216 | 3.5773 | 5.3452 | 6.9896 | 12.2112 | 15.7885 | -1.1135 | 6.4587 | 1.7629 | 1.6543 | 1.8144 | 2.2886 | 5.2216 | 3.5773 | 5.3452 | 6.9996 | 12.2212 | 15.7985 | 0.01
4.8713 | 7.7554 | 1.9624 | 1.9436 | 2.8119 | 2.8871 | 6.7178 | 4.7743 | 12.6267 | 14.5703 | 21.2881 | 26.0624 | 4.8713 | 7.7554 | 1.9624 | 1.9536 | 2.8119 | 2.8871 | 6.7178 | 4.7743 | 12.6267 | 14.5803 | 21.2981 | 26.0724 | 0.01
7.0446 | 8.2263 | 2.0348 | 2.0522 | 3.1741 | 3.1045 | 7.2612 | 5.2089 | 15.2709 | 17.3232 | 24.5843 | 29.7933 | 7.0446 | 8.2263 | 2.0348 | 2.0622 | 3.1741 | 3.1045 | 7.2612 | 5.2089 | 15.2709 | 17.3332 | 24.5943 | 29.8033 | 0.01
20.3696 | 11.1134 | 2.479 | 2.7185 | 5.3949 | 4.437 | 10.5924 | 7.8739 | 31.483 | 34.2015 | 44.7939 | 52.6678 | 20.3696 | 11.1134 | 2.479 | 2.7285 | 5.3949 | 4.437 | 10.5924 | 7.8739 | 31.483 | 34.2115 | 44.8039 | 52.6778 | 0.01
2.9926 | 7.3484 | 1.8998 | 1.8496 | 2.4988 | 2.6993 | 6.2482 | 4.3985 | 10.341 | 12.1907 | 18.4388 | 22.8374 | 2.9926 | 7.3484 | 1.8998 | 1.8596 | 2.4988 | 2.6993 | 6.2482 | 4.3985 | 10.341 | 12.2007 | 18.4488 | 22.8474 | 0.01
3.3625 | 7.4285 | 1.9121 | 1.8681 | 2.5604 | 2.7362 | 6.3406 | 4.4725 | 10.791 | 12.6591 | 18.9998 | 23.4723 | 3.3625 | 7.4285 | 1.9121 | 1.8781 | 2.5604 | 2.7362 | 6.3406 | 4.4725 | 10.791 | 12.6691 | 19.0098 | 23.4823 | 0.01
2.8398 | 7.3153 | 1.8947 | 1.842 | 2.4733 | 2.684 | 6.21 | 4.368 | 10.1551 | 11.9971 | 18.207 | 22.575 | 2.8398 | 7.3153 | 1.8947 | 1.852 | 2.4733 | 2.684 | 6.21 | 4.368 | 10.1551 | 12.0071 | 18.217 | 22.585 | 0.01
8.605 | 8.5644 | 2.0868 | 2.1302 | 3.4342 | 3.2605 | 7.6512 | 5.521 | 17.1694 | 19.2996 | 26.9509 | 32.4719 | 8.605 | 8.5644 | 2.0868 | 2.1402 | 3.4342 | 3.2605 | 7.6512 | 5.521 | 17.1694 | 19.3096 | 26.9609 | 32.4819 | 0.01
8.192 | 8.4749 | 2.0731 | 2.1096 | 3.3653 | 3.2192 | 7.548 | 5.4384 | 16.6669 | 18.7765 | 26.3245 | 31.7629 | 8.192 | 8.4749 | 2.0731 | 2.1196 | 3.3653 | 3.2192 | 7.548 | 5.4384 | 16.6669 | 18.7865 | 26.3345 | 31.7729 | 0.01
8.0575 | 8.4458 | 2.0686 | 2.1029 | 3.3429 | 3.2057 | 7.5144 | 5.4115 | 16.5033 | 18.6062 | 26.1205 | 31.532 | 8.0575 | 8.4458 | 2.0686 | 2.1129 | 3.3429 | 3.2057 | 7.5144 | 5.4115 | 16.5033 | 18.6162 | 26.1305 | 31.542 | 0.01
5.6798 | 7.9306 | 1.9893 | 1.984 | 2.9466 | 2.968 | 6.92 | 4.936 | 13.6104 | 15.5944 | 22.5144 | 27.4503 | 5.6798 | 7.9306 | 1.9893 | 1.994 | 2.9466 | 2.968 | 6.92 | 4.936 | 13.6104 | 15.6044 | 22.5244 | 27.4603 | 0.01
12.1633 | 9.3354 | 2.2054 | 2.3082 | 4.0272 | 3.6163 | 8.5408 | 6.2327 | 21.4987 | 23.8069 | 32.3477 | 38.5804 | 12.1633 | 9.3354 | 2.2054 | 2.3182 | 4.0272 | 3.6163 | 8.5408 | 6.2327 | 21.4987 | 23.8169 | 32.3577 | 38.5904 | 0.01
8.89 | 8.6262 | 2.0963 | 2.1445 | 3.4817 | 3.289 | 7.7225 | 5.578 | 17.5161 | 19.6606 | 27.3831 | 32.9611 | 8.89 | 8.6262 | 2.0963 | 2.1545 | 3.4817 | 3.289 | 7.7225 | 5.578 | 17.5161 | 19.6706 | 27.3931 | 32.9711 | 0.01
4.5152 | 7.6783 | 1.9505 | 1.9258 | 2.7525 | 2.8515 | 6.6288 | 4.703 | 12.1935 | 14.1192 | 20.748 | 25.451 | 4.5152 | 7.6783 | 1.9505 | 1.9358 | 2.7525 | 2.8515 | 6.6288 | 4.703 | 12.1935 | 14.1292 | 20.758 | 25.461 | 0.01
17.5746 | 10.5078 | 2.3858 | 2.5787 | 4.9291 | 4.1575 | 9.8937 | 7.3149 | 28.0824 | 30.6612 | 40.5548 | 47.8697 | 17.5746 | 10.5078 | 2.3858 | 2.5887 | 4.9291 | 4.1575 | 9.8937 | 7.3149 | 28.0824 | 30.6712 | 40.5648 | 47.8797 | 0.01
7.2511 | 8.2711 | 2.0417 | 2.0626 | 3.2085 | 3.1251 | 7.3128 | 5.2502 | 15.5222 | 17.5848 | 24.8976 | 30.1478 | 7.2511 | 8.2711 | 2.0417 | 2.0726 | 3.2085 | 3.1251 | 7.3128 | 5.2502 | 15.5222 | 17.5948 | 24.9076 | 30.1578 | 0.01
7.1645 | 8.2523 | 2.0388 | 2.0582 | 3.1941 | 3.1164 | 7.2911 | 5.2329 | 15.4168 | 17.475 | 24.7661 | 29.999 | 7.1645 | 8.2523 | 2.0388 | 2.0682 | 3.1941 | 3.1164 | 7.2911 | 5.2329 | 15.4168 | 17.485 | 24.7761 | 30.009 | 0.01
8.9096 | 8.6304 | 2.097 | 2.1455 | 3.4849 | 3.291 | 7.7274 | 5.5819 | 17.54 | 19.6855 | 27.4129 | 32.9948 | 8.9096 | 8.6304 | 2.097 | 2.1555 | 3.4849 | 3.291 | 7.7274 | 5.5819 | 17.54 | 19.6955 | 27.4229 | 33.0048 | 0.01
13.8753 | 9.7063 | 2.2625 | 2.3938 | 4.3126 | 3.7875 | 8.9688 | 6.5751 | 23.5816 | 25.9754 | 34.9442 | 41.5193 | 13.8753 | 9.7063 | 2.2625 | 2.4038 | 4.3126 | 3.7875 | 8.9688 | 6.5751 | 23.5816 | 25.9854 | 34.9542 | 41.5293 | 0.01
14.9444 | 9.938 | 2.2981 | 2.4472 | 4.4907 | 3.8944 | 9.2361 | 6.7889 | 24.8824 | 27.3296 | 36.5657 | 43.3546 | 14.9444 | 9.938 | 2.2981 | 2.4572 | 4.4907 | 3.8944 | 9.2361 | 6.7889 | 24.8824 | 27.3396 | 36.5757 | 43.3646 | 0.01
12.6497 | 9.4408 | 2.2217 | 2.3325 | 4.1083 | 3.665 | 8.6624 | 6.3299 | 22.0904 | 24.4229 | 33.0853 | 39.4153 | 12.6497 | 9.4408 | 2.2217 | 2.3425 | 4.1083 | 3.665 | 8.6624 | 6.3299 | 22.0904 | 24.4329 | 33.0953 | 39.4253 | 0.01
-5.3839 | 5.5335 | 1.6205 | 1.4308 | 1.1027 | 1.8616 | 4.154 | 2.7232 | 0.14953 | 1.5803 | 5.7343 | 8.4576 | -5.3839 | 5.5335 | 1.6205 | 1.4408 | 1.1027 | 1.8616 | 4.154 | 2.7232 | 0.14953 | 1.5903 | 5.7443 | 8.4676 | 0.01
7.415 | 8.3066 | 2.0472 | 2.0707 | 3.2358 | 3.1415 | 7.3537 | 5.283 | 15.7215 | 17.7923 | 25.146 | 30.429 | 7.415 | 8.3066 | 2.0472 | 2.0807 | 3.2358 | 3.1415 | 7.3537 | 5.283 | 15.7215 | 17.8023 | 25.156 | 30.439 | 0.01
0.75401 | 6.8634 | 1.8251 | 1.7377 | 2.1257 | 2.4754 | 5.6885 | 3.9508 | 7.6174 | 9.3551 | 15.0436 | 18.9944 | 0.75401 | 6.8634 | 1.8251 | 1.7477 | 2.1257 | 2.4754 | 5.6885 | 3.9508 | 7.6174 | 9.3651 | 15.0536 | 19.0044 | 0.01
7.6785 | 8.3637 | 2.0559 | 2.0839 | 3.2797 | 3.1678 | 7.4196 | 5.3357 | 16.0421 | 18.1261 | 25.5457 | 30.8814 | 7.6785 | 8.3637 | 2.0559 | 2.0939 | 3.2797 | 3.1678 | 7.4196 | 5.3357 | 16.0421 | 18.1361 | 25.5557 | 30.8914 | 0.01
-6.7356 | 5.2406 | 1.5755 | 1.3632 | 0.8774 | 1.7264 | 3.8161 | 2.4529 | -1.495 | -0.13174 | 3.6844 | 6.1373 | -6.7356 | 5.2406 | 1.5755 | 1.3732 | 0.8774 | 1.7264 | 3.8161 | 2.4529 | -1.495 | -0.12174 | 3.6944 | 6.1473 | 0.01
15.0729 | 9.9658 | 2.3024 | 2.4536 | 4.5121 | 3.9073 | 9.2682 | 6.8146 | 25.0387 | 27.4923 | 36.7606 | 43.5751 | 15.0729 | 9.9658 | 2.3024 | 2.4636 | 4.5121 | 3.9073 | 9.2682 | 6.8146 | 25.0387 | 27.5023 | 36.7706 | 43.5851 | 0.01
4.1628 | 7.6019 | 1.9388 | 1.9081 | 2.6938 | 2.8163 | 6.5407 | 4.6326 | 11.7648 | 13.6729 | 20.2136 | 24.8462 | 4.1628 | 7.6019 | 1.9388 | 1.9181 | 2.6938 | 2.8163 | 6.5407 | 4.6326 | 11.7648 | 13.6829 | 20.2236 | 24.8562 | 0.01
-1.8279 | 6.304 | 1.7391 | 1.6086 | 1.6954 | 2.2172 | 5.043 | 3.4344 | 4.4761 | 6.0847 | 11.1277 | 14.5622 | -1.8279 | 6.304 | 1.7391 | 1.6186 | 1.6954 | 2.2172 | 5.043 | 3.4344 | 4.4761 | 6.0947 | 11.1377 | 14.5722 | 0.01
7.3349 | 8.2892 | 2.0445 | 2.0667 | 3.2225 | 3.1335 | 7.3337 | 5.267 | 15.6242 | 17.6909 | 25.0246 | 30.2916 | 7.3349 | 8.2892 | 2.0445 | 2.0767 | 3.2225 | 3.1335 | 7.3337 | 5.267 | 15.6242 | 17.7009 | 25.0346 | 30.3016 | 0.01
-2.9217 | 6.067 | 1.7026 | 1.5539 | 1.5131 | 2.1078 | 4.7696 | 3.2157 | 3.1453 | 4.6992 | 9.4688 | 12.6845 | -2.9217 | 6.067 | 1.7026 | 1.5639 | 1.5131 | 2.1078 | 4.7696 | 3.2157 | 3.1453 | 4.7092 | 9.4788 | 12.6945 | 0.01
6.4196 | 8.0909 | 2.014 | 2.021 | 3.0699 | 3.042 | 7.1049 | 5.0839 | 14.5106 | 16.5315 | 23.6364 | 28.7204 | 6.4196 | 8.0909 | 2.014 | 2.031 | 3.0699 | 3.042 | 7.1049 | 5.0839 | 14.5106 | 16.5415 | 23.6464 | 28.7304 | 0.01
-3.1568 | 6.016 | 1.6948 | 1.5422 | 1.4739 | 2.0843 | 4.7108 | 3.1686 | 2.8592 | 4.4013 | 9.1121 | 12.2807 | -3.1568 | 6.016 | 1.6948 | 1.5522 | 1.4739 | 2.0843 | 4.7108 | 3.1686 | 2.8592 | 4.4113 | 9.1221 | 12.2907 | 0.01
-5.5235 | 5.5032 | 1.6159 | 1.4238 | 1.0794 | 1.8476 | 4.1191 | 2.6953 | -0.0203 | 1.4035 | 5.5226 | 8.2179 | -5.5235 | 5.5032 | 1.6159 | 1.4338 | 1.0794 | 1.8476 | 4.1191 | 2.6953 | -0.0203 | 1.4135 | 5.5326 | 8.2279 | 0.01
4.1099 | 7.5905 | 1.937 | 1.9055 | 2.685 | 2.811 | 6.5275 | 4.622 | 11.7004 | 13.6058 | 20.1333 | 24.7553 | 4.1099 | 7.5905 | 1.937 | 1.9155 | 2.685 | 2.811 | 6.5275 | 4.622 | 11.7004 | 13.6158 | 20.1433 | 24.7653 | 0.01
9.1846 | 8.69 | 2.1062 | 2.1592 | 3.5308 | 3.3185 | 7.7962 | 5.6369 | 17.8746 | 20.0339 | 27.83 | 33.4669 | 9.1846 | 8.69 | 2.1062 | 2.1692 | 3.5308 | 3.3185 | 7.7962 | 5.6369 | 17.8746 | 20.0439 | 27.84 | 33.4769 | 0.01
-3.3156 | 5.9816 | 1.6895 | 1.5342 | 1.4474 | 2.0684 | 4.6711 | 3.1369 | 2.666 | 4.2003 | 8.8714 | 12.0082 | -3.3156 | 5.9816 | 1.6895 | 1.5442 | 1.4474 | 2.0684 | 4.6711 | 3.1369 | 2.666 | 4.2103 | 8.8814 | 12.0182 | 0.01
10.6419 | 9.0057 | 2.1547 | 2.2321 | 3.7737 | 3.4642 | 8.1605 | 5.9284 | 19.6477 | 21.8798 | 30.0402 | 35.9686 | 10.6419 | 9.0057 | 2.1547 | 2.2421 | 3.7737 | 3.4642 | 8.1605 | 5.9284 | 19.6477 | 21.8898 | 30.0502 | 35.9786 | 0.01
9.4293 | 8.743 | 2.1143 | 2.1715 | 3.5716 | 3.3429 | 7.8573 | 5.6859 | 18.1724 | 20.3438 | 28.2012 | 33.8871 | 9.4293 | 8.743 | 2.1143 | 2.1815 | 3.5716 | 3.3429 | 7.8573 | 5.6859 | 18.1724 | 20.3538 | 28.2112 | 33.8971 | 0.01
24.2891 | 11.9626 | 2.6096 | 2.9145 | 6.0482 | 4.8289 | 11.5723 | 8.6578 | 36.2518 | 39.1662 | 50.7385 | 59.3964 | 24.2891 | 11.9626 | 2.6096 | 2.9245 | 6.0482 | 4.8289 | 11.5723 | 8.6578 | 36.2518 | 39.1762 | 50.7485 | 59.4064 | 0.01
8.2951 | 8.4973 | 2.0765 | 2.1148 | 3.3825 | 3.2295 | 7.5738 | 5.459 | 16.7923 | 18.9071 | 26.4808 | 31.9398 | 8.2951 | 8.4973 | 2.0765 | 2.1248 | 3.3825 | 3.2295 | 7.5738 | 5.459 | 16.7923 | 18.9171 | 26.4908 | 31.9498 | 0.01
-5.1847 | 5.5767 | 1.6272 | 1.4408 | 1.1359 | 1.8815 | 4.2038 | 2.7631 | 0.392 | 1.8328 | 6.0366 | 8.7997 | -5.1847 | 5.5767 | 1.6272 | 1.4508 | 1.1359 | 1.8815 | 4.2038 | 2.7631 | 0.392 | 1.8428 | 6.0466 | 8.8097 | 0.01
7.4308 | 8.31 | 2.0477 | 2.0715 | 3.2385 | 3.1431 | 7.3577 | 5.2862 | 15.7408 | 17.8123 | 25.17 | 30.4562 | 7.4308 | 8.31 | 2.0477 | 2.0815 | 3.2385 | 3.1431 | 7.3577 | 5.2862 | 15.7408 | 17.8223 | 25.18 | 30.4662 | 0.01
3.9805 | 7.5624 | 1.9327 | 1.899 | 2.6634 | 2.798 | 6.4951 | 4.5961 | 11.5429 | 13.4419 | 19.937 | 24.5331 | 3.9805 | 7.5624 | 1.9327 | 1.909 | 2.6634 | 2.798 | 6.4951 | 4.5961 | 11.5429 | 13.4519 | 19.947 | 24.5431 | 0.01
6.9627 | 8.2086 | 2.0321 | 2.0481 | 3.1605 | 3.0963 | 7.2407 | 5.1925 | 15.1713 | 17.2195 | 24.4602 | 29.6527 | 6.9627 | 8.2086 | 2.0321 | 2.0581 | 3.1605 | 3.0963 | 7.2407 | 5.1925 | 15.1713 | 17.2295 | 24.4702 | 29.6627 | 0.01
10.5847 | 8.9933 | 2.1528 | 2.2292 | 3.7641 | 3.4585 | 8.1462 | 5.9169 | 19.578 | 21.8073 | 29.9534 | 35.8704 | 10.5847 | 8.9933 | 2.1528 | 2.2392 | 3.7641 | 3.4585 | 8.1462 | 5.9169 | 19.578 | 21.8173 | 29.9634 | 35.8804 | 0.01
-1.1576 | 6.4492 | 1.7614 | 1.6421 | 1.8071 | 2.2842 | 5.2106 | 3.5685 | 5.2915 | 6.9337 | 12.1443 | 15.7127 | -1.1576 | 6.4492 | 1.7614 | 1.6521 | 1.8071 | 2.2842 | 5.2106 | 3.5685 | 5.2915 | 6.9437 | 12.1543 | 15.7227 | 0.01
-1.1256 | 6.4561 | 1.7625 | 1.6437 | 1.8124 | 2.2874 | 5.2186 | 3.5749 | 5.3305 | 6.9742 | 12.1928 | 15.7677 | -1.1256 | 6.4561 | 1.7625 | 1.6537 | 1.8124 | 2.2874 | 5.2186 | 3.5749 | 5.3305 | 6.9842 | 12.2028 | 15.7777 | 0.01
10.0004 | 8.8667 | 2.1333 | 2.2 | 3.6667 | 3.4 | 8.0001 | 5.8001 | 18.8671 | 21.0671 | 29.0672 | 34.8673 | 10.0004 | 8.8667 | 2.1333 | 2.21 | 3.6667 | 3.4 | 8.0001 | 5.8001 | 18.8671 | 21.0771 | 29.0772 | 34.8773 | 0.01
8.9462 | 8.6383 | 2.0982 | 2.1473 | 3.491 | 3.2946 | 7.7366 | 5.5892 | 17.5845 | 19.7319 | 27.4684 | 33.0576 | 8.9462 | 8.6383 | 2.0982 | 2.1573 | 3.491 | 3.2946 | 7.7366 | 5.5892 | 17.5845 | 19.7419 | 27.4784 | 33.0676 | 0.01
1.749 | 7.0789 | 1.8583 | 1.7874 | 2.2915 | 2.5749 | 5.9372 | 4.1498 | 8.8279 | 10.6153 | 16.5526 | 20.7024 | 1.749 | 7.0789 | 1.8583 | 1.7974 | 2.2915 | 2.5749 | 5.9372 | 4.1498 | 8.8279 | 10.6253 | 16.5626 | 20.7124 | 0.01
0.17321 | 6.7375 | 1.8058 | 1.7087 | 2.0289 | 2.4173 | 5.5433 | 3.8346 | 6.9107 | 8.6194 | 14.1627 | 17.9973 | 0.17321 | 6.7375 | 1.8058 | 1.7187 | 2.0289 | 2.4173 | 5.5433 | 3.8346 | 6.9107 | 8.6294 | 14.1727 | 18.0073 | 0.01
7.8213 | 8.3946 | 2.0607 | 2.0911 | 3.3035 | 3.1821 | 7.4553 | 5.3643 | 16.2159 | 18.3069 | 25.7622 | 31.1265 | 7.8213 | 8.3946 | 2.0607 | 2.1011 | 3.3035 | 3.1821 | 7.4553 | 5.3643 | 16.2159 | 18.3169 | 25.7722 | 31.1365 | 0.01
15.1106 | 9.974 | 2.3037 | 2.4555 | 4.5184 | 3.9111 | 9.2777 | 6.8221 | 25.0846 | 27.5401 | 36.8178 | 43.6399 | 15.1106 | 9.974 | 2.3037 | 2.4655 | 4.5184 | 3.9111 | 9.2777 | 6.8221 | 25.0846 | 27.5501 | 36.8278 | 43.6499 | 0.01
10.1426 | 8.8976 | 2.1381 | 2.2071 | 3.6904 | 3.4143 | 8.0357 | 5.8285 | 19.0402 | 21.2473 | 29.283 | 35.1115 | 10.1426 | 8.8976 | 2.1381 | 2.2171 | 3.6904 | 3.4143 | 8.0357 | 5.8285 | 19.0402 | 21.2573 | 29.293 | 35.1215 | 0.01
16.8847 | 10.3583 | 2.3628 | 2.5442 | 4.8141 | 4.0885 | 9.7212 | 7.1769 | 27.243 | 29.7873 | 39.5084 | 46.6854 | 16.8847 | 10.3583 | 2.3628 | 2.5542 | 4.8141 | 4.0885 | 9.7212 | 7.1769 | 27.243 | 29.7973 | 39.5184 | 46.6954 | 0.01
7.7903 | 8.3879 | 2.0597 | 2.0895 | 3.2984 | 3.179 | 7.4476 | 5.3581 | 16.1782 | 18.2677 | 25.7153 | 31.0734 | 7.7903 | 8.3879 | 2.0597 | 2.0995 | 3.2984 | 3.179 | 7.4476 | 5.3581 | 16.1782 | 18.2777 | 25.7253 | 31.0834 | 0.01
13.5503 | 9.6359 | 2.2517 | 2.3775 | 4.2584 | 3.755 | 8.8876 | 6.5101 | 23.1862 | 25.5637 | 34.4513 | 40.9613 | 13.5503 | 9.6359 | 2.2517 | 2.3875 | 4.2584 | 3.755 | 8.8876 | 6.5101 | 23.1862 | 25.5737 | 34.4613 | 40.9713 | 0.01
15.0013 | 9.9503 | 2.3 | 2.4501 | 4.5002 | 3.9001 | 9.2503 | 6.8003 | 24.9515 | 27.4016 | 36.6519 | 43.4522 | 15.0013 | 9.9503 | 2.3 | 2.4601 | 4.5002 | 3.9001 | 9.2503 | 6.8003 | 24.9515 | 27.4116 | 36.6619 | 43.4622 | 0.01
7.9384 | 8.42 | 2.0646 | 2.0969 | 3.3231 | 3.1938 | 7.4846 | 5.3877 | 16.3584 | 18.4553 | 25.9399 | 31.3276 | 7.9384 | 8.42 | 2.0646 | 2.1069 | 3.3231 | 3.1938 | 7.4846 | 5.3877 | 16.3584 | 18.4653 | 25.9499 | 31.3376 | 0.01
6.8871 | 8.1922 | 2.0296 | 2.0444 | 3.1479 | 3.0887 | 7.2218 | 5.1774 | 15.0793 | 17.1237 | 24.3455 | 29.5229 | 6.8871 | 8.1922 | 2.0296 | 2.0544 | 3.1479 | 3.0887 | 7.2218 | 5.1774 | 15.0793 | 17.1337 | 24.3555 | 29.5329 | 0.01
1.9661 | 7.126 | 1.8655 | 1.7983 | 2.3277 | 2.5966 | 5.9915 | 4.1932 | 9.0921 | 10.8904 | 16.8819 | 21.0751 | 1.9661 | 7.126 | 1.8655 | 1.8083 | 2.3277 | 2.5966 | 5.9915 | 4.1932 | 9.0921 | 10.9004 | 16.8919 | 21.0851 | 0.01
3.4524 | 7.448 | 1.9151 | 1.8726 | 2.5754 | 2.7452 | 6.3631 | 4.4905 | 10.9004 | 12.773 | 19.1361 | 23.6266 | 3.4524 | 7.448 | 1.9151 | 1.8826 | 2.5754 | 2.7452 | 6.3631 | 4.4905 | 10.9004 | 12.783 | 19.1461 | 23.6366 | 0.01
11.6679 | 9.228 | 2.1889 | 2.2834 | 3.9446 | 3.5668 | 8.417 | 6.1336 | 20.8959 | 23.1793 | 31.5963 | 37.7298 | 11.6679 | 9.228 | 2.1889 | 2.2934 | 3.9446 | 3.5668 | 8.417 | 6.1336 | 20.8959 | 23.1893 | 31.6063 | 37.7398 | 0.01
-0.70544 | 6.5472 | 1.7765 | 1.6647 | 1.8824 | 2.3295 | 5.3236 | 3.6589 | 5.8417 | 7.5064 | 12.8301 | 16.489 | -0.70544 | 6.5472 | 1.7765 | 1.6747 | 1.8824 | 2.3295 | 5.3236 | 3.6589 | 5.8417 | 7.5164 | 12.8401 | 16.499 | 0.01
4.6741 | 7.7127 | 1.9558 | 1.9337 | 2.779 | 2.8674 | 6.6685 | 4.7348 | 12.3868 | 14.3205 | 20.989 | 25.7238 | 4.6741 | 7.7127 | 1.9558 | 1.9437 | 2.779 | 2.8674 | 6.6685 | 4.7348 | 12.3868 | 14.3305 | 20.999 | 25.7338 | 0.01
10.26 | 8.923 | 2.142 | 2.213 | 3.71 | 3.426 | 8.065 | 5.852 | 19.183 | 21.396 | 29.461 | 35.313 | 10.26 | 8.923 | 2.142 | 2.223 | 3.71 | 3.426 | 8.065 | 5.852 | 19.183 | 21.406 | 29.471 | 35.323 | 0.01
7.416 | 8.3068 | 2.0472 | 2.0708 | 3.236 | 3.1416 | 7.354 | 5.2832 | 15.7228 | 17.7936 | 25.1476 | 30.4308 | 7.416 | 8.3068 | 2.0472 | 2.0808 | 3.236 | 3.1416 | 7.354 | 5.2832 | 15.7228 | 17.8036 | 25.1576 | 30.4408 | 0.01
2.6131 | 7.2662 | 1.8871 | 1.8307 | 2.4355 | 2.6613 | 6.1533 | 4.3226 | 9.8793 | 11.71 | 17.8633 | 22.1859 | 2.6131 | 7.2662 | 1.8871 | 1.8407 | 2.4355 | 2.6613 | 6.1533 | 4.3226 | 9.8793 | 11.72 | 17.8733 | 22.1959 | 0.01
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2044 | 14.1306 | 20.7616 | 25.4664 | 4.5241 | 7.6802 | 1.9508 | 1.9362 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2044 | 14.1406 | 20.7716 | 25.4764 | 0.01
9.0177 | 8.6538 | 2.1006 | 2.1509 | 3.5029 | 3.3018 | 7.7544 | 5.6035 | 17.6715 | 19.8224 | 27.5768 | 33.1803 | 9.0177 | 8.6538 | 2.1006 | 2.1609 | 3.5029 | 3.3018 | 7.7544 | 5.6035 | 17.6715 | 19.8324 | 27.5868 | 33.1903 | 0.01
11.271 | 9.1421 | 2.1757 | 2.2636 | 3.8785 | 3.5271 | 8.3178 | 6.0542 | 20.4131 | 22.6766 | 30.9944 | 37.0486 | 11.271 | 9.1421 | 2.1757 | 2.2736 | 3.8785 | 3.5271 | 8.3178 | 6.0542 | 20.4131 | 22.6866 | 31.0044 | 37.0586 | 0.01
4.8689 | 7.7549 | 1.9623 | 1.9434 | 2.8115 | 2.8869 | 6.7172 | 4.7738 | 12.6238 | 14.5672 | 21.2844 | 26.0582 | 4.8689 | 7.7549 | 1.9623 | 1.9534 | 2.8115 | 2.8869 | 6.7172 | 4.7738 | 12.6238 | 14.5772 | 21.2944 | 26.0682 | 0.01
13.7381 | 9.6766 | 2.2579 | 2.3869 | 4.2897 | 3.7738 | 8.9345 | 6.5476 | 23.4147 | 25.8016 | 34.7361 | 41.2837 | 13.7381 | 9.6766 | 2.2579 | 2.3969 | 4.2897 | 3.7738 | 8.9345 | 6.5476 | 23.4147 | 25.8116 | 34.7461 | 41.2937 | 0.01
-0.14801 | 6.6679 | 1.7951 | 1.6926 | 1.9753 | 2.3852 | 5.463 | 3.7704 | 6.5199 | 8.2125 | 13.6755 | 17.4459 | -0.14801 | 6.6679 | 1.7951 | 1.7026 | 1.9753 | 2.3852 | 5.463 | 3.7704 | 6.5199 | 8.2225 | 13.6855 | 17.4559 | 0.01
4.9965 | 7.7826 | 1.9666 | 1.9498 | 2.8328 | 2.8997 | 6.7491 | 4.7993 | 12.7791 | 14.7289 | 21.478 | 26.2773 | 4.9965 | 7.7826 | 1.9666 | 1.9598 | 2.8328 | 2.8997 | 6.7491 | 4.7993 | 12.7791 | 14.7389 | 21.488 | 26.2873 | 0.01
2.9362 | 7.3362 | 1.8979 | 1.8468 | 2.4894 | 2.6936 | 6.234 | 4.3872 | 10.2723 | 12.1191 | 18.3532 | 22.7404 | 2.9362 | 7.3362 | 1.8979 | 1.8568 | 2.4894 | 2.6936 | 6.234 | 4.3872 | 10.2723 | 12.1291 | 18.3632 | 22.7504 | 0.01
10.8682 | 9.0548 | 2.1623 | 2.2434 | 3.8114 | 3.4868 | 8.2171 | 5.9736 | 19.923 | 22.1664 | 30.3835 | 36.3571 | 10.8682 | 9.0548 | 2.1623 | 2.2534 | 3.8114 | 3.4868 | 8.2171 | 5.9736 | 19.923 | 22.1764 | 30.3935 | 36.3671 | 0.01
5.3766 | 7.8649 | 1.9792 | 1.9688 | 2.8961 | 2.9377 | 6.8441 | 4.8753 | 13.2415 | 15.2103 | 22.0545 | 26.9298 | 5.3766 | 7.8649 | 1.9792 | 1.9788 | 2.8961 | 2.9377 | 6.8441 | 4.8753 | 13.2415 | 15.2203 | 22.0645 | 26.9398 | 0.01
-3.2425 | 5.9975 | 1.6919 | 1.5379 | 1.4596 | 2.0758 | 4.6894 | 3.1515 | 2.755 | 4.2928 | 8.9822 | 12.1337 | -3.2425 | 5.9975 | 1.6919 | 1.5479 | 1.4596 | 2.0758 | 4.6894 | 3.1515 | 2.755 | 4.3028 | 8.9922 | 12.1437 | 0.01
5.784 | 7.9532 | 1.9928 | 1.9892 | 2.964 | 2.9784 | 6.946 | 4.9568 | 13.7372 | 15.7264 | 22.6724 | 27.6292 | 5.784 | 7.9532 | 1.9928 | 1.9992 | 2.964 | 2.9784 | 6.946 | 4.9568 | 13.7372 | 15.7364 | 22.6824 | 27.6392 | 0.01
0.62392 | 6.8352 | 1.8208 | 1.7312 | 2.104 | 2.4624 | 5.656 | 3.9248 | 7.4591 | 9.1903 | 14.8463 | 18.7711 | 0.62392 | 6.8352 | 1.8208 | 1.7412 | 2.104 | 2.4624 | 5.656 | 3.9248 | 7.4591 | 9.2003 | 14.8563 | 18.7811 | 0.01
3.8817 | 7.541 | 1.9294 | 1.8941 | 2.6469 | 2.7882 | 6.4704 | 4.5763 | 11.4227 | 13.3168 | 19.7872 | 24.3636 | 3.8817 | 7.541 | 1.9294 | 1.9041 | 2.6469 | 2.7882 | 6.4704 | 4.5763 | 11.4227 | 13.3268 | 19.7972 | 24.3736 | 0.01
6.7592 | 8.1645 | 2.0253 | 2.038 | 3.1265 | 3.0759 | 7.1898 | 5.1518 | 14.9237 | 16.9617 | 24.1515 | 29.3033 | 6.7592 | 8.1645 | 2.0253 | 2.048 | 3.1265 | 3.0759 | 7.1898 | 5.1518 | 14.9237 | 16.9717 | 24.1615 | 29.3133 | 0.01
8.4274 | 8.5259 | 2.0809 | 2.1214 | 3.4046 | 3.2427 | 7.6069 | 5.4855 | 16.9534 | 19.0748 | 26.6816 | 32.1671 | 8.4274 | 8.5259 | 2.0809 | 2.1314 | 3.4046 | 3.2427 | 7.6069 | 5.4855 | 16.9534 | 19.0848 | 26.6916 | 32.1771 | 0.01
16.2512 | 10.2211 | 2.3417 | 2.5126 | 4.7085 | 4.0251 | 9.5628 | 7.0502 | 26.4722 | 28.9848 | 38.5476 | 45.5978 | 16.2512 | 10.2211 | 2.3417 | 2.5226 | 4.7085 | 4.0251 | 9.5628 | 7.0502 | 26.4722 | 28.9948 | 38.5576 | 45.6078 | 0.01
3.9702 | 7.5602 | 1.9323 | 1.8985 | 2.6617 | 2.797 | 6.4925 | 4.594 | 11.5304 | 13.4289 | 19.9214 | 24.5155 | 3.9702 | 7.5602 | 1.9323 | 1.9085 | 2.6617 | 2.797 | 6.4925 | 4.594 | 11.5304 | 13.4389 | 19.9314 | 24.5255 | 0.01
9.1031 | 8.6723 | 2.1034 | 2.1552 | 3.5172 | 3.3103 | 7.7758 | 5.6206 | 17.7754 | 19.9305 | 27.7063 | 33.3269 | 9.1031 | 8.6723 | 2.1034 | 2.1652 | 3.5172 | 3.3103 | 7.7758 | 5.6206 | 17.7754 | 19.9405 | 27.7163 | 33.3369 | 0.01
7.6437 | 8.3561 | 2.0548 | 2.0822 | 3.2739 | 3.1644 | 7.4109 | 5.3287 | 15.9998 | 18.082 | 25.4929 | 30.8217 | 7.6437 | 8.3561 | 2.0548 | 2.0922 | 3.2739 | 3.1644 | 7.4109 | 5.3287 | 15.9998 | 18.092 | 25.5029 | 30.8317 | 0.01
7.4801 | 8.3207 | 2.0493 | 2.074 | 3.2467 | 3.148 | 7.37 | 5.296 | 15.8008 | 17.8748 | 25.2449 | 30.5409 | 7.4801 | 8.3207 | 2.0493 | 2.084 | 3.2467 | 3.148 | 7.37 | 5.296 | 15.8008 | 17.8848 | 25.2549 | 30.5509 | 0.01
15.1289 | 9.9779 | 2.3043 | 2.4564 | 4.5215 | 3.9129 | 9.2822 | 6.8258 | 25.1068 | 27.5633 | 36.8455 | 43.6713 | 15.1289 | 9.9779 | 2.3043 | 2.4664 | 4.5215 | 3.9129 | 9.2822 | 6.8258 | 25.1068 | 27.5733 | 36.8555 | 43.6813 | 0.01
0.75091 | 6.8627 | 1.825 | 1.7375 | 2.1252 | 2.4751 | 5.6877 | 3.9502 | 7.6136 | 9.3512 | 15.0389 | 18.9891 | 0.75091 | 6.8627 | 1.825 | 1.7475 | 2.1252 | 2.4751 | 5.6877 | 3.9502 | 7.6136 | 9.3612 | 15.0489 | 18.9991 | 0.01
1.9654 | 7.1258 | 1.8655 | 1.7983 | 2.3276 | 2.5965 | 5.9914 | 4.1931 | 9.0912 | 10.8895 | 16.8809 | 21.0739 | 1.9654 | 7.1258 | 1.8655 | 1.8083 | 2.3276 | 2.5965 | 5.9914 | 4.1931 | 9.0912 | 10.8995 | 16.8909 | 21.0839 | 0.01
9.8869 | 8.8422 | 2.1296 | 2.1943 | 3.6478 | 3.3887 | 7.9717 | 5.7774 | 18.7291 | 20.9234 | 28.8951 | 34.6725 | 9.8869 | 8.8422 | 2.1296 | 2.2043 | 3.6478 | 3.3887 | 7.9717 | 5.7774 | 18.7291 | 20.9334 | 28.9051 | 34.6825 | 0.01
6.4668 | 8.1011 | 2.0156 | 2.0233 | 3.0778 | 3.0467 | 7.1167 | 5.0934 | 14.5679 | 16.5913 | 23.708 | 28.8013 | 6.4668 | 8.1011 | 2.0156 | 2.0333 | 3.0778 | 3.0467 | 7.1167 | 5.0934 | 14.5679 | 16.6013 | 23.718 | 28.8113 | 0.01
7.8432 | 8.3994 | 2.0614 | 2.0922 | 3.3072 | 3.1843 | 7.4608 | 5.3686 | 16.2426 | 18.3348 | 25.7956 | 31.1642 | 7.8432 | 8.3994 | 2.0614 | 2.1022 | 3.3072 | 3.1843 | 7.4608 | 5.3686 | 16.2426 | 18.3448 | 25.8056 | 31.1742 | 0.01
3.9091 | 7.547 | 1.9303 | 1.8955 | 2.6515 | 2.7909 | 6.4773 | 4.5818 | 11.456 | 13.3515 | 19.8288 | 24.4106 | 3.9091 | 7.547 | 1.9303 | 1.9055 | 2.6515 | 2.7909 | 6.4773 | 4.5818 | 11.456 | 13.3615 | 19.8388 | 24.4206 | 0.01
3.4369 | 7.4447 | 1.9146 | 1.8718 | 2.5728 | 2.7437 | 6.3592 | 4.4874 | 10.8815 | 12.7533 | 19.1126 | 23.5999 | 3.4369 | 7.4447 | 1.9146 | 1.8818 | 2.5728 | 2.7437 | 6.3592 | 4.4874 | 10.8815 | 12.7633 | 19.1226 | 23.6099 | 0.01
16.7592 | 10.3312 | 2.3586 | 2.538 | 4.7932 | 4.0759 | 9.6898 | 7.1518 | 27.0903 | 29.6283 | 39.3181 | 46.4699 | 16.7592 | 10.3312 | 2.3586 | 2.548 | 4.7932 | 4.0759 | 9.6898 | 7.1518 | 27.0903 | 29.6383 | 39.3281 | 46.4799 | 0.01
-4.8476 | 5.6497 | 1.6384 | 1.4576 | 1.1921 | 1.9152 | 4.2881 | 2.8305 | 0.80204 | 2.2597 | 6.5478 | 9.3782 | -4.8476 | 5.6497 | 1.6384 | 1.4676 | 1.1921 | 1.9152 | 4.2881 | 2.8305 | 0.80204 | 2.2697 | 6.5578 | 9.3882 | 0.01
4.8571 | 7.7524 | 1.9619 | 1.9429 | 2.8095 | 2.8857 | 6.7143 | 4.7714 | 12.6094 | 14.5523 | 21.2665 | 26.038 | 4.8571 | 7.7524 | 1.9619 | 1.9529 | 2.8095 | 2.8857 | 6.7143 | 4.7714 | 12.6094 | 14.5623 | 21.2765 | 26.048 | 0.01
15.5217 | 10.063 | 2.3174 | 2.4761 | 4.587 | 3.9522 | 9.3804 | 6.9043 | 25.5847 | 28.0608 | 37.4412 | 44.3456 | 15.5217 | 10.063 | 2.3174 | 2.4861 | 4.587 | 3.9522 | 9.3804 | 6.9043 | 25.5847 | 28.0708 | 37.4512 | 44.3556 | 0.01
4.5272 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7054 | 12.2081 | 14.1344 | 20.7662 | 25.4717 | 4.5272 | 7.6809 | 1.9509 | 1.9364 | 2.7545 | 2.8527 | 6.6318 | 4.7054 | 12.2081 | 14.1444 | 20.7762 | 25.4817 | 0.01
-6.9383 | 5.1967 | 1.5687 | 1.3531 | 0.84362 | 1.7062 | 3.7654 | 2.4123 | -1.7415 | -0.38845 | 3.377 | 5.7893 | -6.9383 | 5.1967 | 1.5687 | 1.3631 | 0.84362 | 1.7062 | 3.7654 | 2.4123 | -1.7415 | -0.37845 | 3.387 | 5.7993 | 0.01
16.9328 | 10.3688 | 2.3644 | 2.5466 | 4.8221 | 4.0933 | 9.7332 | 7.1866 | 27.3016 | 29.8482 | 39.5814 | 46.768 | 16.9328 | 10.3688 | 2.3644 | 2.5566 | 4.8221 | 4.0933 | 9.7332 | 7.1866 | 27.3016 | 29.8582 | 39.5914 | 46.778 | 0.01
14.0968 | 9.7543 | 2.2699 | 2.4048 | 4.3495 | 3.8097 | 9.0242 | 6.6194 | 23.8511 | 26.2559 | 35.2801 | 41.8995 | 14.0968 | 9.7543 | 2.2699 | 2.4148 | 4.3495 | 3.8097 | 9.0242 | 6.6194 | 23.8511 | 26.2659 | 35.2901 | 41.9095 | 0.01
21.6875 | 11.399 | 2.5229 | 2.7844 | 5.6146 | 4.5687 | 10.9219 | 8.1375 | 33.0864 | 35.8708 | 46.7927 | 54.9302 | 21.6875 | 11.399 | 2.5229 | 2.7944 | 5.6146 | 4.5687 | 10.9219 | 8.1375 | 33.0864 | 35.8808 | 46.8027 | 54.9402 | 0.01
14.6441 | 9.8729 | 2.2881 | 2.4322 | 4.4407 | 3.8644 | 9.161 | 6.7288 | 24.5169 | 26.9491 | 36.1102 | 42.839 | 14.6441 | 9.8729 | 2.2881 | 2.4422 | 4.4407 | 3.8644 | 9.161 | 6.7288 | 24.5169 | 26.9591 | 36.1202 | 42.849 | 0.01
0.7403 | 6.8604 | 1.8247 | 1.737 | 2.1234 | 2.474 | 5.6851 | 3.9481 | 7.6007 | 9.3377 | 15.0228 | 18.9709 | 0.7403 | 6.8604 | 1.8247 | 1.747 | 2.1234 | 2.474 | 5.6851 | 3.9481 | 7.6007 | 9.3477 | 15.0328 | 18.9809 | 0.01
0.19334 | 6.7419 | 1.8064 | 1.7097 | 2.0322 | 2.4193 | 5.5483 | 3.8387 | 6.9352 | 8.6449 | 14.1932 | 18.0319 | 0.19334 | 6.7419 | 1.8064 | 1.7197 | 2.0322 | 2.4193 | 5.5483 | 3.8387 | 6.9352 | 8.6549 | 14.2032 | 18.0419 | 0.01
8.7563 | 8.5972 | 2.0919 | 2.1378 | 3.4594 | 3.2756 | 7.6891 | 5.5513 | 17.3534 | 19.4913 | 27.1803 | 32.7316 | 8.7563 | 8.5972 | 2.0919 | 2.1478 | 3.4594 | 3.2756 | 7.6891 | 5.5513 | 17.3534 | 19.5013 | 27.1903 | 32.7416 | 0.01
8.0989 | 8.4548 | 2.07 | 2.1049 | 3.3498 | 3.2099 | 7.5247 | 5.4198 | 16.5537 | 18.6586 | 26.1833 | 31.6031 | 8.0989 | 8.4548 | 2.07 | 2.1149 | 3.3498 | 3.2099 | 7.5247 | 5.4198 | 16.5537 | 18.6686 | 26.1933 | 31.6131 | 0.01
-3.4729 | 5.9475 | 1.6842 | 1.5264 | 1.4212 | 2.0527 | 4.6318 | 3.1054 | 2.4746 | 4.0009 | 8.6327 | 11.7381 | -3.4729 | 5.9475 | 1.6842 | 1.5364 | 1.4212 | 2.0527 | 4.6318 | 3.1054 | 2.4746 | 4.0109 | 8.6427 | 11.7481 | 0.01
0.19703 | 6.7427 | 1.8066 | 1.7099 | 2.0328 | 2.4197 | 5.5493 | 3.8394 | 6.9397 | 8.6496 | 14.1988 | 18.0382 | 0.19703 | 6.7427 | 1.8066 | 1.7199 | 2.0328 | 2.4197 | 5.5493 | 3.8394 | 6.9397 | 8.6596 | 14.2088 | 18.0482 | 0.01
2.1437 | 7.1645 | 1.8715 | 1.8072 | 2.3573 | 2.6144 | 6.0359 | 4.2287 | 9.3082 | 11.1154 | 17.1513 | 21.38 | 2.1437 | 7.1645 | 1.8715 | 1.8172 | 2.3573 | 2.6144 | 6.0359 | 4.2287 | 9.3082 | 11.1254 | 17.1613 | 21.39 | 0.01
2.1804 | 7.1724 | 1.8727 | 1.809 | 2.3634 | 2.618 | 6.0451 | 4.2361 | 9.3528 | 11.1618 | 17.2069 | 21.443 | 2.1804 | 7.1724 | 1.8727 | 1.819 | 2.3634 | 2.618 | 6.0451 | 4.2361 | 9.3528 | 11.1718 | 17.2169 | 21.453 | 0.01
8.4919 | 8.5399 | 2.0831 | 2.1246 | 3.4153 | 3.2492 | 7.623 | 5.4984 | 17.0318 | 19.1564 | 26.7793 | 32.2777 | 8.4919 | 8.5399 | 2.0831 | 2.1346 | 3.4153 | 3.2492 | 7.623 | 5.4984 | 17.0318 | 19.1664 | 26.7893 | 32.2877 | 0.01
-0.30742 | 6.6334 | 1.7898 | 1.6846 | 1.9488 | 2.3693 | 5.4231 | 3.7385 | 6.326 | 8.0106 | 13.4337 | 17.1723 | -0.30742 | 6.6334 | 1.7898 | 1.6946 | 1.9488 | 2.3693 | 5.4231 | 3.7385 | 6.326 | 8.0206 | 13.4437 | 17.1823 | 0.01
5.7009 | 7.9352 | 1.99 | 1.985 | 2.9501 | 2.9701 | 6.9252 | 4.9402 | 13.6361 | 15.6211 | 22.5463 | 27.4865 | 5.7009 | 7.9352 | 1.99 | 1.995 | 2.9501 | 2.9701 | 6.9252 | 4.9402 | 13.6361 | 15.6311 | 22.5563 | 27.4965 | 0.01
3.9954 | 7.5657 | 1.9332 | 1.8998 | 2.6659 | 2.7995 | 6.4988 | 4.5991 | 11.561 | 13.4608 | 19.9596 | 24.5587 | 3.9954 | 7.5657 | 1.9332 | 1.9098 | 2.6659 | 2.7995 | 6.4988 | 4.5991 | 11.561 | 13.4708 | 19.9696 | 24.5687 | 0.01
2.8736 | 7.3226 | 1.8958 | 1.8437 | 2.4789 | 2.6874 | 6.2184 | 4.3747 | 10.1962 | 12.0399 | 18.2583 | 22.633 | 2.8736 | 7.3226 | 1.8958 | 1.8537 | 2.4789 | 2.6874 | 6.2184 | 4.3747 | 10.1962 | 12.0499 | 18.2683 | 22.643 | 0.01
7.4078 | 8.305 | 2.0469 | 2.0704 | 3.2346 | 3.1408 | 7.352 | 5.2816 | 15.7128 | 17.7832 | 25.1352 | 30.4167 | 7.4078 | 8.305 | 2.0469 | 2.0804 | 3.2346 | 3.1408 | 7.352 | 5.2816 | 15.7128 | 17.7932 | 25.1452 | 30.4267 | 0.01
4.6413 | 7.7056 | 1.9547 | 1.9321 | 2.7735 | 2.8641 | 6.6603 | 4.7283 | 12.3469 | 14.2789 | 20.9392 | 25.6675 | 4.6413 | 7.7056 | 1.9547 | 1.9421 | 2.7735 | 2.8641 | 6.6603 | 4.7283 | 12.3469 | 14.2889 | 20.9492 | 25.6775 | 0.01
17.8399 | 10.5653 | 2.3947 | 2.592 | 4.9733 | 4.184 | 9.96 | 7.368 | 28.4052 | 30.9972 | 40.9571 | 48.3251 | 17.8399 | 10.5653 | 2.3947 | 2.602 | 4.9733 | 4.184 | 9.96 | 7.368 | 28.4052 | 31.0072 | 40.9671 | 48.3351 | 0.01
10.3126 | 8.9344 | 2.1438 | 2.2156 | 3.7188 | 3.4313 | 8.0782 | 5.8625 | 19.2471 | 21.4627 | 29.5409 | 35.4034 | 10.3126 | 8.9344 | 2.1438 | 2.2256 | 3.7188 | 3.4313 | 8.0782 | 5.8625 | 19.2471 | 21.4727 | 29.5509 | 35.4134 | 0.01
0.93636 | 6.9029 | 1.8312 | 1.7468 | 2.1561 | 2.4936 | 5.7341 | 3.9873 | 7.8392 | 9.5861 | 15.3201 | 19.3074 | 0.93636 | 6.9029 | 1.8312 | 1.7568 | 2.1561 | 2.4936 | 5.7341 | 3.9873 | 7.8392 | 9.5961 | 15.3301 | 19.3174 | 0.01
5.9171 | 7.982 | 1.9972 | 1.9959 | 2.9862 | 2.9917 | 6.9793 | 4.9834 | 13.8992 | 15.8951 | 22.8743 | 27.8578 | 5.9171 | 7.982 | 1.9972 | 2.0059 | 2.9862 | 2.9917 | 6.9793 | 4.9834 | 13.8992 | 15.9051 | 22.8843 | 27.8678 | 0.01
14.2609 | 9.7899 | 2.2754 | 2.413 | 4.3768 | 3.8261 | 9.0652 | 6.6522 | 24.0507 | 26.4638 | 35.529 | 42.1812 | 14.2609 | 9.7899 | 2.2754 | 2.423 | 4.3768 | 3.8261 | 9.0652 | 6.6522 | 24.0507 | 26.4738 | 35.539 | 42.1912 | 0.01
4.7586 | 7.731 | 1.9586 | 1.9379 | 2.7931 | 2.8759 | 6.6897 | 4.7517 | 12.4897 | 14.4276 | 21.1173 | 25.869 | 4.7586 | 7.731 | 1.9586 | 1.9479 | 2.7931 | 2.8759 | 6.6897 | 4.7517 | 12.4897 | 14.4376 | 21.1273 | 25.879 | 0.01
-1.5358 | 6.3672 | 1.7488 | 1.6232 | 1.744 | 2.2464 | 5.116 | 3.4928 | 4.8314 | 6.4546 | 11.5707 | 15.0635 | -1.5358 | 6.3672 | 1.7488 | 1.6332 | 1.744 | 2.2464 | 5.116 | 3.4928 | 4.8314 | 6.4646 | 11.5807 | 15.0735 | 0.01
4.5187 | 7.6791 | 1.9506 | 1.9259 | 2.7531 | 2.8519 | 6.6297 | 4.7037 | 12.1977 | 14.1237 | 20.7534 | 25.4571 | 4.5187 | 7.6791 | 1.9506 | 1.9359 | 2.7531 | 2.8519 | 6.6297 | 4.7037 | 12.1977 | 14.1337 | 20.7634 | 25.4671 | 0.01
10.9318 | 9.0686 | 2.1644 | 2.2466 | 3.822 | 3.4932 | 8.233 | 5.9864 | 20.0004 | 22.247 | 30.4799 | 36.4663 | 10.9318 | 9.0686 | 2.1644 | 2.2566 | 3.822 | 3.4932 | 8.233 | 5.9864 | 20.0004 | 22.257 | 30.4899 | 36.4763 | 0.01
3.7619 | 7.5151 | 1.9254 | 1.8881 | 2.627 | 2.7762 | 6.4405 | 4.5524 | 11.2769 | 13.165 | 19.6055 | 24.1579 | 3.7619 | 7.5151 | 1.9254 | 1.8981 | 2.627 | 2.7762 | 6.4405 | 4.5524 | 11.2769 | 13.175 | 19.6155 | 24.1679 | 0.01
0.66962 | 6.8451 | 1.8223 | 1.7335 | 2.1116 | 2.467 | 5.6674 | 3.9339 | 7.5147 | 9.2482 | 14.9156 | 18.8495 | 0.66962 | 6.8451 | 1.8223 | 1.7435 | 2.1116 | 2.467 | 5.6674 | 3.9339 | 7.5147 | 9.2582 | 14.9256 | 18.8595 | 0.01
8.4453 | 8.5298 | 2.0815 | 2.1223 | 3.4076 | 3.2445 | 7.6113 | 5.4891 | 16.9752 | 19.0974 | 26.7088 | 32.1978 | 8.4453 | 8.5298 | 2.0815 | 2.1323 | 3.4076 | 3.2445 | 7.6113 | 5.4891 | 16.9752 | 19.1074 | 26.7188 | 32.2078 | 0.01
4 | 7.5667 | 1.9333 | 1.9 | 2.6667 | 2.8 | 6.5 | 4.6 | 11.5666 | 13.4666 | 19.9666 | 24.5666 | 4 | 7.5667 | 1.9333 | 1.91 | 2.6667 | 2.8 | 6.5 | 4.6 | 11.5666 | 13.4766 | 19.9766 | 24.5766 | 0.01
0.11313 | 6.7245 | 1.8038 | 1.7057 | 2.0189 | 2.4113 | 5.5283 | 3.8226 | 6.8376 | 8.5433 | 14.0716 | 17.8942 | 0.11313 | 6.7245 | 1.8038 | 1.7157 | 2.0189 | 2.4113 | 5.5283 | 3.8226 | 6.8376 | 8.5533 | 14.0816 | 17.9042 | 0.01
14.3302 | 9.8049 | 2.2777 | 2.4165 | 4.3884 | 3.833 | 9.0825 | 6.666 | 24.135 | 26.5516 | 35.6341 | 42.3001 | 14.3302 | 9.8049 | 2.2777 | 2.4265 | 4.3884 | 3.833 | 9.0825 | 6.666 | 24.135 | 26.5616 | 35.6441 | 42.3101 | 0.01
0.82956 | 6.8797 | 1.8277 | 1.7415 | 2.1383 | 2.483 | 5.7074 | 3.9659 | 7.7093 | 9.4508 | 15.1582 | 19.1241 | 0.82956 | 6.8797 | 1.8277 | 1.7515 | 2.1383 | 2.483 | 5.7074 | 3.9659 | 7.7093 | 9.4608 | 15.1682 | 19.1341 | 0.01
6.5365 | 8.1162 | 2.0179 | 2.0268 | 3.0894 | 3.0537 | 7.1341 | 5.1073 | 14.6528 | 16.6796 | 23.8137 | 28.921 | 6.5365 | 8.1162 | 2.0179 | 2.0368 | 3.0894 | 3.0537 | 7.1341 | 5.1073 | 14.6528 | 16.6896 | 23.8237 | 28.931 | 0.01
2.4857 | 7.2386 | 1.8829 | 1.8243 | 2.4143 | 2.6486 | 6.1214 | 4.2971 | 9.7243 | 11.5486 | 17.67 | 21.9671 | 2.4857 | 7.2386 | 1.8829 | 1.8343 | 2.4143 | 2.6486 | 6.1214 | 4.2971 | 9.7243 | 11.5586 | 17.68 | 21.9771 | 0.01
9.4618 | 8.7501 | 2.1154 | 2.1731 | 3.577 | 3.3462 | 7.8655 | 5.6924 | 18.2119 | 20.385 | 28.2504 | 33.9428 | 9.4618 | 8.7501 | 2.1154 | 2.1831 | 3.577 | 3.3462 | 7.8655 | 5.6924 | 18.2119 | 20.395 | 28.2604 | 33.9528 | 0.01
10.5152 | 8.9783 | 2.1505 | 2.2258 | 3.7525 | 3.4515 | 8.1288 | 5.903 | 19.4935 | 21.7193 | 29.8481 | 35.7511 | 10.5152 | 8.9783 | 2.1505 | 2.2358 | 3.7525 | 3.4515 | 8.1288 | 5.903 | 19.4935 | 21.7293 | 29.8581 | 35.7611 | 0.01
13.8852 | 9.7085 | 2.2628 | 2.3943 | 4.3142 | 3.7885 | 8.9713 | 6.577 | 23.5937 | 25.9879 | 34.9592 | 41.5363 | 13.8852 | 9.7085 | 2.2628 | 2.4043 | 4.3142 | 3.7885 | 8.9713 | 6.577 | 23.5937 | 25.9979 | 34.9692 | 41.5463 | 0.01
7.4114 | 8.3058 | 2.047 | 2.0706 | 3.2352 | 3.1411 | 7.3529 | 5.2823 | 15.7172 | 17.7878 | 25.1406 | 30.4229 | 7.4114 | 8.3058 | 2.047 | 2.0806 | 3.2352 | 3.1411 | 7.3529 | 5.2823 | 15.7172 | 17.7978 | 25.1506 | 30.4329 | 0.01
3.3173 | 7.4187 | 1.9106 | 1.8659 | 2.5529 | 2.7317 | 6.3293 | 4.4635 | 10.736 | 12.6019 | 18.9312 | 23.3947 | 3.3173 | 7.4187 | 1.9106 | 1.8759 | 2.5529 | 2.7317 | 6.3293 | 4.4635 | 10.736 | 12.6119 | 18.9412 | 23.4047 | 0.01
6.514 | 8.1114 | 2.0171 | 2.0257 | 3.0857 | 3.0514 | 7.1285 | 5.1028 | 14.6253 | 16.651 | 23.7795 | 28.8823 | 6.514 | 8.1114 | 2.0171 | 2.0357 | 3.0857 | 3.0514 | 7.1285 | 5.1028 | 14.6253 | 16.661 | 23.7895 | 28.8923 | 0.01
-0.5379 | 6.5835 | 1.7821 | 1.6731 | 1.9104 | 2.3462 | 5.3655 | 3.6924 | 6.0456 | 7.7187 | 13.0842 | 16.7766 | -0.5379 | 6.5835 | 1.7821 | 1.6831 | 1.9104 | 2.3462 | 5.3655 | 3.6924 | 6.0456 | 7.7287 | 13.0942 | 16.7866 | 0.01
1.9903 | 7.1312 | 1.8663 | 1.7995 | 2.3317 | 2.599 | 5.9976 | 4.1981 | 9.1215 | 10.9211 | 16.9186 | 21.1167 | 1.9903 | 7.1312 | 1.8663 | 1.8095 | 2.3317 | 2.599 | 5.9976 | 4.1981 | 9.1215 | 10.9311 | 16.9286 | 21.1267 | 0.01
17.5171 | 10.4954 | 2.3839 | 2.5759 | 4.9195 | 4.1517 | 9.8793 | 7.3034 | 28.0125 | 30.5883 | 40.4676 | 47.771 | 17.5171 | 10.4954 | 2.3839 | 2.5859 | 4.9195 | 4.1517 | 9.8793 | 7.3034 | 28.0125 | 30.5983 | 40.4776 | 47.781 | 0.01
5.7762 | 7.9515 | 1.9925 | 1.9888 | 2.9627 | 2.9776 | 6.9441 | 4.9552 | 13.7277 | 15.7166 | 22.6606 | 27.6159 | 5.7762 | 7.9515 | 1.9925 | 1.9988 | 2.9627 | 2.9776 | 6.9441 | 4.9552 | 13.7277 | 15.7266 | 22.6706 | 27.6259 | 0.01
5.936 | 7.9861 | 1.9979 | 1.9968 | 2.9893 | 2.9936 | 6.984 | 4.9872 | 13.9222 | 15.919 | 22.903 | 27.8902 | 5.936 | 7.9861 | 1.9979 | 2.0068 | 2.9893 | 2.9936 | 6.984 | 4.9872 | 13.9222 | 15.929 | 22.913 | 27.9002 | 0.01
-4.9884 | 5.6192 | 1.6337 | 1.4506 | 1.1686 | 1.9012 | 4.2529 | 2.8023 | 0.63082 | 2.0814 | 6.3343 | 9.1366 | -4.9884 | 5.6192 | 1.6337 | 1.4606 | 1.1686 | 1.9012 | 4.2529 | 2.8023 | 0.63082 | 2.0914 | 6.3443 | 9.1466 | 0.01
4.2438 | 7.6195 | 1.9415 | 1.9122 | 2.7073 | 2.8244 | 6.561 | 4.6488 | 11.8633 | 13.7755 | 20.3365 | 24.9852 | 4.2438 | 7.6195 | 1.9415 | 1.9222 | 2.7073 | 2.8244 | 6.561 | 4.6488 | 11.8633 | 13.7855 | 20.3465 | 24.9952 | 0.01
8.0514 | 8.4445 | 2.0684 | 2.1026 | 3.3419 | 3.2051 | 7.5128 | 5.4103 | 16.4958 | 18.5984 | 26.1112 | 31.5215 | 8.0514 | 8.4445 | 2.0684 | 2.1126 | 3.3419 | 3.2051 | 7.5128 | 5.4103 | 16.4958 | 18.6084 | 26.1212 | 31.5315 | 0.01
-8.3684 | 4.8868 | 1.5211 | 1.2816 | 0.60526 | 1.5632 | 3.4079 | 2.1263 | -3.4816 | -2.2 | 1.2079 | 3.3342 | -8.3684 | 4.8868 | 1.5211 | 1.2916 | 0.60526 | 1.5632 | 3.4079 | 2.1263 | -3.4816 | -2.19 | 1.2179 | 3.3442 | 0.01
10.4473 | 8.9636 | 2.1482 | 2.2224 | 3.7412 | 3.4447 | 8.1118 | 5.8895 | 19.4109 | 21.6333 | 29.7451 | 35.6346 | 10.4473 | 8.9636 | 2.1482 | 2.2324 | 3.7412 | 3.4447 | 8.1118 | 5.8895 | 19.4109 | 21.6433 | 29.7551 | 35.6446 | 0.01
6.2781 | 8.0603 | 2.0093 | 2.0139 | 3.0463 | 3.0278 | 7.0695 | 5.0556 | 14.3383 | 16.3522 | 23.4218 | 28.4774 | 6.2781 | 8.0603 | 2.0093 | 2.0239 | 3.0463 | 3.0278 | 7.0695 | 5.0556 | 14.3383 | 16.3622 | 23.4318 | 28.4874 | 0.01
-0.026116 | 6.6943 | 1.7991 | 1.6987 | 1.9956 | 2.3974 | 5.4935 | 3.7948 | 6.6682 | 8.3669 | 13.8604 | 17.6552 | -0.026116 | 6.6943 | 1.7991 | 1.7087 | 1.9956 | 2.3974 | 5.4935 | 3.7948 | 6.6682 | 8.3769 | 13.8704 | 17.6652 | 0.01
12.3808 | 9.3825 | 2.2127 | 2.319 | 4.0635 | 3.6381 | 8.5952 | 6.2762 | 21.7633 | 24.0823 | 32.6775 | 38.9537 | 12.3808 | 9.3825 | 2.2127 | 2.329 | 4.0635 | 3.6381 | 8.5952 | 6.2762 | 21.7633 | 24.0923 | 32.6875 | 38.9637 | 0.01
4.3092 | 7.6337 | 1.9436 | 1.9155 | 2.7182 | 2.8309 | 6.5773 | 4.6618 | 11.9428 | 13.8583 | 20.4356 | 25.0974 | 4.3092 | 7.6337 | 1.9436 | 1.9255 | 2.7182 | 2.8309 | 6.5773 | 4.6618 | 11.9428 | 13.8683 | 20.4456 | 25.1074 | 0.01
9.5463 | 8.7684 | 2.1182 | 2.1773 | 3.591 | 3.3546 | 7.8866 | 5.7093 | 18.3146 | 20.492 | 28.3785 | 34.0878 | 9.5463 | 8.7684 | 2.1182 | 2.1873 | 3.591 | 3.3546 | 7.8866 | 5.7093 | 18.3146 | 20.502 | 28.3885 | 34.0978 | 0.01
3.7633 | 7.5154 | 1.9254 | 1.8882 | 2.6272 | 2.7763 | 6.4408 | 4.5527 | 11.2787 | 13.1668 | 19.6077 | 24.1603 | 3.7633 | 7.5154 | 1.9254 | 1.8982 | 2.6272 | 2.7763 | 6.4408 | 4.5527 | 11.2787 | 13.1768 | 19.6177 | 24.1703 | 0.01
8.7658 | 8.5992 | 2.0922 | 2.1383 | 3.461 | 3.2766 | 7.6914 | 5.5532 | 17.365 | 19.5033 | 27.1947 | 32.7479 | 8.7658 | 8.5992 | 2.0922 | 2.1483 | 3.461 | 3.2766 | 7.6914 | 5.5532 | 17.365 | 19.5133 | 27.2047 | 32.7579 | 0.01
0.69767 | 6.8512 | 1.8233 | 1.7349 | 2.1163 | 2.4698 | 5.6744 | 3.9395 | 7.5488 | 9.2837 | 14.9581 | 18.8977 | 0.69767 | 6.8512 | 1.8233 | 1.7449 | 2.1163 | 2.4698 | 5.6744 | 3.9395 | 7.5488 | 9.2937 | 14.9681 | 18.9077 | 0.01
11.5977 | 9.2128 | 2.1866 | 2.2799 | 3.9329 | 3.5598 | 8.3994 | 6.1195 | 20.8105 | 23.0904 | 31.4898 | 37.6094 | 11.5977 | 9.2128 | 2.1866 | 2.2899 | 3.9329 | 3.5598 | 8.3994 | 6.1195 | 20.8105 | 23.1004 | 31.4998 | 37.6194 | 0.01
8.4712 | 8.5354 | 2.0824 | 2.1236 | 3.4119 | 3.2471 | 7.6178 | 5.4942 | 17.0067 | 19.1302 | 26.748 | 32.2423 | 8.4712 | 8.5354 | 2.0824 | 2.1336 | 3.4119 | 3.2471 | 7.6178 | 5.4942 | 17.0067 | 19.1402 | 26.758 | 32.2523 | 0.01
18.2142 | 10.6464 | 2.4071 | 2.6107 | 5.0357 | 4.2214 | 10.0536 | 7.4428 | 28.8606 | 31.4713 | 41.5249 | 48.9677 | 18.2142 | 10.6464 | 2.4071 | 2.6207 | 5.0357 | 4.2214 | 10.0536 | 7.4428 | 28.8606 | 31.4813 | 41.5349 | 48.9777 | 0.01
13.8999 | 9.7117 | 2.2633 | 2.395 | 4.3167 | 3.79 | 8.975 | 6.58 | 23.6116 | 26.0066 | 34.9816 | 41.5615 | 13.8999 | 9.7117 | 2.2633 | 2.405 | 4.3167 | 3.79 | 8.975 | 6.58 | 23.6116 | 26.0166 | 34.9916 | 41.5715 | 0.01
6.3636 | 8.0788 | 2.0121 | 2.0182 | 3.0606 | 3.0364 | 7.0909 | 5.0727 | 14.4424 | 16.4605 | 23.5514 | 28.6242 | 6.3636 | 8.0788 | 2.0121 | 2.0282 | 3.0606 | 3.0364 | 7.0909 | 5.0727 | 14.4424 | 16.4705 | 23.5614 | 28.6342 | 0.01
6.9097 | 8.1971 | 2.0303 | 2.0455 | 3.1516 | 3.091 | 7.2274 | 5.1819 | 15.1068 | 17.1523 | 24.3797 | 29.5616 | 6.9097 | 8.1971 | 2.0303 | 2.0555 | 3.1516 | 3.091 | 7.2274 | 5.1819 | 15.1068 | 17.1623 | 24.3897 | 29.5716 | 0.01
1.1273 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7818 | 4.0255 | 8.0716 | 9.8279 | 15.6098 | 19.6352 | 1.1273 | 6.9443 | 1.8376 | 1.7664 | 2.1879 | 2.5127 | 5.7818 | 4.0255 | 8.0716 | 9.8379 | 15.6198 | 19.6452 | 0.01
15.8964 | 10.1442 | 2.3299 | 2.4948 | 4.6494 | 3.9896 | 9.4741 | 6.9793 | 26.0407 | 28.5355 | 38.0096 | 44.9889 | 15.8964 | 10.1442 | 2.3299 | 2.5048 | 4.6494 | 3.9896 | 9.4741 | 6.9793 | 26.0407 | 28.5455 | 38.0196 | 44.9989 | 0.01
6.1089 | 8.0236 | 2.0036 | 2.0054 | 3.0181 | 3.0109 | 7.0272 | 5.0218 | 14.1325 | 16.1379 | 23.1651 | 28.1869 | 6.1089 | 8.0236 | 2.0036 | 2.0154 | 3.0181 | 3.0109 | 7.0272 | 5.0218 | 14.1325 | 16.1479 | 23.1751 | 28.1969 | 0.01
0.25643 | 6.7556 | 1.8085 | 1.7128 | 2.0427 | 2.4256 | 5.5641 | 3.8513 | 7.012 | 8.7248 | 14.2889 | 18.1402 | 0.25643 | 6.7556 | 1.8085 | 1.7228 | 2.0427 | 2.4256 | 5.5641 | 3.8513 | 7.012 | 8.7348 | 14.2989 | 18.1502 | 0.01
-4.2332 | 5.7828 | 1.6589 | 1.4883 | 1.2945 | 1.9767 | 4.4417 | 2.9534 | 1.5496 | 3.038 | 7.4797 | 10.433 | -4.2332 | 5.7828 | 1.6589 | 1.4983 | 1.2945 | 1.9767 | 4.4417 | 2.9534 | 1.5496 | 3.048 | 7.4897 | 10.443 | 0.01
3.0006 | 7.3501 | 1.9 | 1.85 | 2.5001 | 2.7001 | 6.2501 | 4.4001 | 10.3507 | 12.2007 | 18.4509 | 22.851 | 3.0006 | 7.3501 | 1.9 | 1.86 | 2.5001 | 2.7001 | 6.2501 | 4.4001 | 10.3507 | 12.2107 | 18.4609 | 22.861 | 0.01
-0.019623 | 6.6957 | 1.7993 | 1.699 | 1.9967 | 2.398 | 5.4951 | 3.7961 | 6.6761 | 8.3751 | 13.8702 | 17.6663 | -0.019623 | 6.6957 | 1.7993 | 1.709 | 1.9967 | 2.398 | 5.4951 | 3.7961 | 6.6761 | 8.3851 | 13.8802 | 17.6763 | 0.01
1.7234 | 7.0734 | 1.8574 | 1.7862 | 2.2872 | 2.5723 | 5.9308 | 4.1447 | 8.7968 | 10.583 | 16.5138 | 20.6585 | 1.7234 | 7.0734 | 1.8574 | 1.7962 | 2.2872 | 2.5723 | 5.9308 | 4.1447 | 8.7968 | 10.593 | 16.5238 | 20.6685 | 0.01
17.9337 | 10.5856 | 2.3978 | 2.5967 | 4.9889 | 4.1934 | 9.9834 | 7.3867 | 28.5193 | 31.116 | 41.0994 | 48.4862 | 17.9337 | 10.5856 | 2.3978 | 2.6067 | 4.9889 | 4.1934 | 9.9834 | 7.3867 | 28.5193 | 31.126 | 41.1094 | 48.4962 | 0.01
5.9536 | 7.9899 | 1.9985 | 1.9977 | 2.9923 | 2.9954 | 6.9884 | 4.9907 | 13.9435 | 15.9412 | 22.9296 | 27.9203 | 5.9536 | 7.9899 | 1.9985 | 2.0077 | 2.9923 | 2.9954 | 6.9884 | 4.9907 | 13.9435 | 15.9512 | 22.9396 | 27.9303 | 0.01
8.1286 | 8.4612 | 2.071 | 2.1064 | 3.3548 | 3.2129 | 7.5321 | 5.4257 | 16.5897 | 18.6962 | 26.2283 | 31.654 | 8.1286 | 8.4612 | 2.071 | 2.1164 | 3.3548 | 3.2129 | 7.5321 | 5.4257 | 16.5897 | 18.7062 | 26.2383 | 31.664 | 0.01
0.99013 | 6.9145 | 1.833 | 1.7495 | 2.165 | 2.499 | 5.7475 | 3.998 | 7.9047 | 9.6542 | 15.4017 | 19.3997 | 0.99013 | 6.9145 | 1.833 | 1.7595 | 2.165 | 2.499 | 5.7475 | 3.998 | 7.9047 | 9.6642 | 15.4117 | 19.4097 | 0.01
9.9327 | 8.8521 | 2.1311 | 2.1966 | 3.6554 | 3.3933 | 7.9832 | 5.7865 | 18.7847 | 20.9814 | 28.9645 | 34.7511 | 9.9327 | 8.8521 | 2.1311 | 2.2066 | 3.6554 | 3.3933 | 7.9832 | 5.7865 | 18.7847 | 20.9914 | 28.9745 | 34.7611 | 0.01
13.1113 | 9.5408 | 2.237 | 2.3556 | 4.1852 | 3.7111 | 8.7778 | 6.4223 | 22.6521 | 25.0077 | 33.7855 | 40.2078 | 13.1113 | 9.5408 | 2.237 | 2.3656 | 4.1852 | 3.7111 | 8.7778 | 6.4223 | 22.6521 | 25.0177 | 33.7955 | 40.2178 | 0.01
3.9177 | 7.5488 | 1.9306 | 1.8959 | 2.6529 | 2.7918 | 6.4794 | 4.5835 | 11.4665 | 13.3624 | 19.8418 | 24.4253 | 3.9177 | 7.5488 | 1.9306 | 1.9059 | 2.6529 | 2.7918 | 6.4794 | 4.5835 | 11.4665 | 13.3724 | 19.8518 | 24.4353 | 0.01
4.0887 | 7.5859 | 1.9363 | 1.9044 | 2.6814 | 2.8089 | 6.5222 | 4.6177 | 11.6745 | 13.579 | 20.1011 | 24.7189 | 4.0887 | 7.5859 | 1.9363 | 1.9144 | 2.6814 | 2.8089 | 6.5222 | 4.6177 | 11.6745 | 13.589 | 20.1111 | 24.7289 | 0.01
-0.055066 | 6.6881 | 1.7982 | 1.6972 | 1.9908 | 2.3945 | 5.4862 | 3.789 | 6.633 | 8.3303 | 13.8165 | 17.6055 | -0.055066 | 6.6881 | 1.7982 | 1.7072 | 1.9908 | 2.3945 | 5.4862 | 3.789 | 6.633 | 8.3403 | 13.8265 | 17.6155 | 0.01
3.9499 | 7.5558 | 1.9317 | 1.8975 | 2.6583 | 2.795 | 6.4875 | 4.59 | 11.5057 | 13.4032 | 19.8906 | 24.4806 | 3.9499 | 7.5558 | 1.9317 | 1.9075 | 2.6583 | 2.795 | 6.4875 | 4.59 | 11.5057 | 13.4132 | 19.9006 | 24.4906 | 0.01
2.5412 | 7.2506 | 1.8847 | 1.8271 | 2.4235 | 2.6541 | 6.1353 | 4.3082 | 9.7918 | 11.6189 | 17.7542 | 22.0624 | 2.5412 | 7.2506 | 1.8847 | 1.8371 | 2.4235 | 2.6541 | 6.1353 | 4.3082 | 9.7918 | 11.6289 | 17.7642 | 22.0724 | 0.01
-1.6705 | 6.3381 | 1.7443 | 1.6165 | 1.7216 | 2.233 | 5.0824 | 3.4659 | 4.6676 | 6.2841 | 11.3664 | 14.8323 | -1.6705 | 6.3381 | 1.7443 | 1.6265 | 1.7216 | 2.233 | 5.0824 | 3.4659 | 4.6676 | 6.2941 | 11.3764 | 14.8423 | 0.01
17.8938 | 10.577 | 2.3965 | 2.5947 | 4.9823 | 4.1894 | 9.9734 | 7.3788 | 28.4708 | 31.0655 | 41.0389 | 48.4177 | 17.8938 | 10.577 | 2.3965 | 2.6047 | 4.9823 | 4.1894 | 9.9734 | 7.3788 | 28.4708 | 31.0755 | 41.0489 | 48.4277 | 0.01
2.6217 | 7.268 | 1.8874 | 1.8311 | 2.4369 | 2.6622 | 6.1554 | 4.3243 | 9.8897 | 11.7208 | 17.8762 | 22.2005 | 2.6217 | 7.268 | 1.8874 | 1.8411 | 2.4369 | 2.6622 | 6.1554 | 4.3243 | 9.8897 | 11.7308 | 17.8862 | 22.2105 | 0.01
6.531 | 8.1151 | 2.0177 | 2.0266 | 3.0885 | 3.0531 | 7.1328 | 5.1062 | 14.6461 | 16.6726 | 23.8054 | 28.9116 | 6.531 | 8.1151 | 2.0177 | 2.0366 | 3.0885 | 3.0531 | 7.1328 | 5.1062 | 14.6461 | 16.6826 | 23.8154 | 28.9216 | 0.01
-0.63752 | 6.5619 | 1.7787 | 1.6681 | 1.8937 | 2.3362 | 5.3406 | 3.6725 | 5.9244 | 7.5925 | 12.9331 | 16.6056 | -0.63752 | 6.5619 | 1.7787 | 1.6781 | 1.8937 | 2.3362 | 5.3406 | 3.6725 | 5.9244 | 7.6025 | 12.9431 | 16.6156 | 0.01
3.242 | 7.4024 | 1.9081 | 1.8621 | 2.5403 | 2.7242 | 6.3105 | 4.4484 | 10.6444 | 12.5065 | 18.817 | 23.2654 | 3.242 | 7.4024 | 1.9081 | 1.8721 | 2.5403 | 2.7242 | 6.3105 | 4.4484 | 10.6444 | 12.5165 | 18.827 | 23.2754 | 0.01
7.7059 | 8.3696 | 2.0569 | 2.0853 | 3.2843 | 3.1706 | 7.4265 | 5.3412 | 16.0755 | 18.1608 | 25.5873 | 30.9285 | 7.7059 | 8.3696 | 2.0569 | 2.0953 | 3.2843 | 3.1706 | 7.4265 | 5.3412 | 16.0755 | 18.1708 | 25.5973 | 30.9385 | 0.01
5.5315 | 7.8985 | 1.9844 | 1.9766 | 2.9219 | 2.9532 | 6.8829 | 4.9063 | 13.43 | 15.4066 | 22.2895 | 27.1958 | 5.5315 | 7.8985 | 1.9844 | 1.9866 | 2.9219 | 2.9532 | 6.8829 | 4.9063 | 13.43 | 15.4166 | 22.2995 | 27.2058 | 0.01
6.2875 | 8.0623 | 2.0096 | 2.0144 | 3.0479 | 3.0288 | 7.0719 | 5.0575 | 14.3498 | 16.3642 | 23.4361 | 28.4936 | 6.2875 | 8.0623 | 2.0096 | 2.0244 | 3.0479 | 3.0288 | 7.0719 | 5.0575 | 14.3498 | 16.3742 | 23.4461 | 28.5036 | 0.01
8.8478 | 8.617 | 2.0949 | 2.1424 | 3.4746 | 3.2848 | 7.7119 | 5.5696 | 17.4648 | 19.6072 | 27.3191 | 32.8887 | 8.8478 | 8.617 | 2.0949 | 2.1524 | 3.4746 | 3.2848 | 7.7119 | 5.5696 | 17.4648 | 19.6172 | 27.3291 | 32.8987 | 0.01
3.6485 | 7.4905 | 1.9216 | 1.8824 | 2.6081 | 2.7648 | 6.4121 | 4.5297 | 11.139 | 13.0214 | 19.4335 | 23.9632 | 3.6485 | 7.4905 | 1.9216 | 1.8924 | 2.6081 | 2.7648 | 6.4121 | 4.5297 | 11.139 | 13.0314 | 19.4435 | 23.9732 | 0.01
4.5406 | 7.6838 | 1.9514 | 1.927 | 2.7568 | 2.8541 | 6.6352 | 4.7081 | 12.2244 | 14.1515 | 20.7866 | 25.4947 | 4.5406 | 7.6838 | 1.9514 | 1.937 | 2.7568 | 2.8541 | 6.6352 | 4.7081 | 12.2244 | 14.1615 | 20.7966 | 25.5047 | 0.01
7.2969 | 8.281 | 2.0432 | 2.0648 | 3.2162 | 3.1297 | 7.3242 | 5.2594 | 15.5779 | 17.6428 | 24.967 | 30.2264 | 7.2969 | 8.281 | 2.0432 | 2.0748 | 3.2162 | 3.1297 | 7.3242 | 5.2594 | 15.5779 | 17.6528 | 24.977 | 30.2364 | 0.01
7.5894 | 8.3444 | 2.053 | 2.0795 | 3.2649 | 3.1589 | 7.3974 | 5.3179 | 15.9338 | 18.0133 | 25.4106 | 30.7285 | 7.5894 | 8.3444 | 2.053 | 2.0895 | 3.2649 | 3.1589 | 7.3974 | 5.3179 | 15.9338 | 18.0233 | 25.4206 | 30.7385 | 0.01
-1.186 | 6.443 | 1.7605 | 1.6407 | 1.8023 | 2.2814 | 5.2035 | 3.5628 | 5.257 | 6.8977 | 12.1012 | 15.664 | -1.186 | 6.443 | 1.7605 | 1.6507 | 1.8023 | 2.2814 | 5.2035 | 3.5628 | 5.257 | 6.9077 | 12.1112 | 15.674 | 0.01
7.5221 | 8.3298 | 2.0507 | 2.0761 | 3.2537 | 3.1522 | 7.3805 | 5.3044 | 15.8519 | 17.928 | 25.3085 | 30.6129 | 7.5221 | 8.3298 | 2.0507 | 2.0861 | 3.2537 | 3.1522 | 7.3805 | 5.3044 | 15.8519 | 17.938 | 25.3185 | 30.6229 | 0.01
4.1728 | 7.6041 | 1.9391 | 1.9086 | 2.6955 | 2.8173 | 6.5432 | 4.6346 | 11.7769 | 13.6856 | 20.2288 | 24.8633 | 4.1728 | 7.6041 | 1.9391 | 1.9186 | 2.6955 | 2.8173 | 6.5432 | 4.6346 | 11.7769 | 13.6956 | 20.2388 | 24.8733 | 0.01
10.0312 | 8.8734 | 2.1344 | 2.2016 | 3.6719 | 3.4031 | 8.0078 | 5.8062 | 18.9047 | 21.1062 | 29.114 | 34.9203 | 10.0312 | 8.8734 | 2.1344 | 2.2116 | 3.6719 | 3.4031 | 8.0078 | 5.8062 | 18.9047 | 21.1162 | 29.124 | 34.9303 | 0.01
1.8924 | 7.11 | 1.8631 | 1.7946 | 2.3154 | 2.5892 | 5.9731 | 4.1785 | 9.0025 | 10.7971 | 16.7702 | 20.9487 | 1.8924 | 7.11 | 1.8631 | 1.8046 | 2.3154 | 2.5892 | 5.9731 | 4.1785 | 9.0025 | 10.8071 | 16.7802 | 20.9587 | 0.01
16.936 | 10.3695 | 2.3645 | 2.5468 | 4.8227 | 4.0936 | 9.734 | 7.1872 | 27.3054 | 29.8522 | 39.5862 | 46.7734 | 16.936 | 10.3695 | 2.3645 | 2.5568 | 4.8227 | 4.0936 | 9.734 | 7.1872 | 27.3054 | 29.8622 | 39.5962 | 46.7834 | 0.01
7.2675 | 8.2746 | 2.0422 | 2.0634 | 3.2112 | 3.1267 | 7.3169 | 5.2535 | 15.5421 | 17.6055 | 24.9223 | 30.1758 | 7.2675 | 8.2746 | 2.0422 | 2.0734 | 3.2112 | 3.1267 | 7.3169 | 5.2535 | 15.5421 | 17.6155 | 24.9323 | 30.1858 | 0.01
5.0004 | 7.7834 | 1.9667 | 1.95 | 2.8334 | 2.9 | 6.7501 | 4.8001 | 12.7839 | 14.7339 | 21.484 | 26.2841 | 5.0004 | 7.7834 | 1.9667 | 1.96 | 2.8334 | 2.9 | 6.7501 | 4.8001 | 12.7839 | 14.7439 | 21.494 | 26.2941 | 0.01
8.22 | 8.481 | 2.074 | 2.111 | 3.37 | 3.222 | 7.555 | 5.444 | 16.7011 | 18.8121 | 26.3671 | 31.8111 | 8.22 | 8.481 | 2.074 | 2.121 | 3.37 | 3.222 | 7.555 | 5.444 | 16.7011 | 18.8221 | 26.3771 | 31.8211 | 0.01
15.5054 | 10.0595 | 2.3168 | 2.4753 | 4.5842 | 3.9505 | 9.3763 | 6.9011 | 25.5649 | 28.0401 | 37.4165 | 44.3175 | 15.5054 | 10.0595 | 2.3168 | 2.4853 | 4.5842 | 3.9505 | 9.3763 | 6.9011 | 25.5649 | 28.0501 | 37.4265 | 44.3275 | 0.01
1.1288 | 6.9446 | 1.8376 | 1.7564 | 2.1881 | 2.5129 | 5.7822 | 4.0258 | 8.0734 | 9.8299 | 15.6121 | 19.6378 | 1.1288 | 6.9446 | 1.8376 | 1.7664 | 2.1881 | 2.5129 | 5.7822 | 4.0258 | 8.0734 | 9.8399 | 15.6221 | 19.6478 | 0.01
0.42329 | 6.7917 | 1.8141 | 1.7212 | 2.0705 | 2.4423 | 5.6058 | 3.8847 | 7.215 | 8.9362 | 14.542 | 18.4267 | 0.42329 | 6.7917 | 1.8141 | 1.7312 | 2.0705 | 2.4423 | 5.6058 | 3.8847 | 7.215 | 8.9462 | 14.552 | 18.4367 | 0.01
6.5131 | 8.1112 | 2.0171 | 2.0257 | 3.0855 | 3.0513 | 7.1283 | 5.1026 | 14.6242 | 16.6499 | 23.7781 | 28.8807 | 6.5131 | 8.1112 | 2.0171 | 2.0357 | 3.0855 | 3.0513 | 7.1283 | 5.1026 | 14.6242 | 16.6599 | 23.7881 | 28.8907 | 0.01
-0.42709 | 6.6075 | 1.7858 | 1.6786 | 1.9288 | 2.3573 | 5.3932 | 3.7146 | 6.1804 | 7.859 | 13.2522 | 16.9668 | -0.42709 | 6.6075 | 1.7858 | 1.6886 | 1.9288 | 2.3573 | 5.3932 | 3.7146 | 6.1804 | 7.869 | 13.2622 | 16.9768 | 0.01
3.3855 | 7.4335 | 1.9129 | 1.8693 | 2.5643 | 2.7386 | 6.3464 | 4.4771 | 10.8191 | 12.6883 | 19.0347 | 23.5118 | 3.3855 | 7.4335 | 1.9129 | 1.8793 | 2.5643 | 2.7386 | 6.3464 | 4.4771 | 10.8191 | 12.6983 | 19.0447 | 23.5218 | 0.01
9.2592 | 8.7062 | 2.1086 | 2.163 | 3.5432 | 3.3259 | 7.8148 | 5.6518 | 17.9653 | 20.1283 | 27.9431 | 33.5949 | 9.2592 | 8.7062 | 2.1086 | 2.173 | 3.5432 | 3.3259 | 7.8148 | 5.6518 | 17.9653 | 20.1383 | 27.9531 | 33.6049 | 0.01
0.34898 | 6.7756 | 1.8116 | 1.7174 | 2.0582 | 2.4349 | 5.5872 | 3.8698 | 7.1246 | 8.842 | 14.4293 | 18.2991 | 0.34898 | 6.7756 | 1.8116 | 1.7274 | 2.0582 | 2.4349 | 5.5872 | 3.8698 | 7.1246 | 8.852 | 14.4393 | 18.3091 | 0.01
14.8692 | 9.9217 | 2.2956 | 2.4435 | 4.4782 | 3.8869 | 9.2173 | 6.7738 | 24.7908 | 27.2343 | 36.4516 | 43.2254 | 14.8692 | 9.9217 | 2.2956 | 2.4535 | 4.4782 | 3.8869 | 9.2173 | 6.7738 | 24.7908 | 27.2443 | 36.4616 | 43.2354 | 0.01
14.2324 | 9.7837 | 2.2744 | 2.4116 | 4.3721 | 3.8232 | 9.0581 | 6.6465 | 24.0161 | 26.4277 | 35.4858 | 42.1323 | 14.2324 | 9.7837 | 2.2744 | 2.4216 | 4.3721 | 3.8232 | 9.0581 | 6.6465 | 24.0161 | 26.4377 | 35.4958 | 42.1423 | 0.01
-3.7799 | 5.881 | 1.674 | 1.511 | 1.37 | 2.022 | 4.555 | 3.044 | 2.1012 | 3.6122 | 8.1672 | 11.2112 | -3.7799 | 5.881 | 1.674 | 1.521 | 1.37 | 2.022 | 4.555 | 3.044 | 2.1012 | 3.6222 | 8.1772 | 11.2212 | 0.01
5.3413 | 7.8573 | 1.978 | 1.9671 | 2.8902 | 2.9341 | 6.8353 | 4.8683 | 13.1986 | 15.1657 | 22.001 | 26.8693 | 5.3413 | 7.8573 | 1.978 | 1.9771 | 2.8902 | 2.9341 | 6.8353 | 4.8683 | 13.1986 | 15.1757 | 22.011 | 26.8793 | 0.01
13.6643 | 9.6606 | 2.2555 | 2.3832 | 4.2774 | 3.7664 | 8.9161 | 6.5329 | 23.3249 | 25.7081 | 34.6242 | 41.157 | 13.6643 | 9.6606 | 2.2555 | 2.3932 | 4.2774 | 3.7664 | 8.9161 | 6.5329 | 23.3249 | 25.7181 | 34.6342 | 41.167 | 0.01
17.2063 | 10.428 | 2.3735 | 2.5603 | 4.8677 | 4.1206 | 9.8016 | 7.2413 | 27.6343 | 30.1946 | 39.9962 | 47.2374 | 17.2063 | 10.428 | 2.3735 | 2.5703 | 4.8677 | 4.1206 | 9.8016 | 7.2413 | 27.6343 | 30.2046 | 40.0062 | 47.2474 | 0.01
8.2493 | 8.4874 | 2.075 | 2.1125 | 3.3749 | 3.2249 | 7.5623 | 5.4499 | 16.7367 | 18.8491 | 26.4115 | 31.8613 | 8.2493 | 8.4874 | 2.075 | 2.1225 | 3.3749 | 3.2249 | 7.5623 | 5.4499 | 16.7367 | 18.8591 | 26.4215 | 31.8713 | 0.01
5.4441 | 7.8796 | 1.9815 | 1.9722 | 2.9074 | 2.9444 | 6.861 | 4.8888 | 13.3237 | 15.2959 | 22.1569 | 27.0457 | 5.4441 | 7.8796 | 1.9815 | 1.9822 | 2.9074 | 2.9444 | 6.861 | 4.8888 | 13.3237 | 15.3059 | 22.1669 | 27.0557 | 0.01
0.4585 | 6.7993 | 1.8153 | 1.7229 | 2.0764 | 2.4459 | 5.6146 | 3.8917 | 7.2578 | 8.9808 | 14.5954 | 18.4871 | 0.4585 | 6.7993 | 1.8153 | 1.7329 | 2.0764 | 2.4459 | 5.6146 | 3.8917 | 7.2578 | 8.9908 | 14.6054 | 18.4971 | 0.01
-0.038013 | 6.6918 | 1.7987 | 1.6981 | 1.9937 | 2.3962 | 5.4905 | 3.7924 | 6.6538 | 8.3519 | 13.8423 | 17.6347 | -0.038013 | 6.6918 | 1.7987 | 1.7081 | 1.9937 | 2.3962 | 5.4905 | 3.7924 | 6.6538 | 8.3619 | 13.8523 | 17.6447 | 0.01
11.8839 | 9.2749 | 2.1961 | 2.2942 | 3.9807 | 3.5884 | 8.471 | 6.1768 | 21.1588 | 23.453 | 31.924 | 38.1008 | 11.8839 | 9.2749 | 2.1961 | 2.3042 | 3.9807 | 3.5884 | 8.471 | 6.1768 | 21.1588 | 23.463 | 31.934 | 38.1108 | 0.01
-3.1106 | 6.026 | 1.6963 | 1.5445 | 1.4816 | 2.0889 | 4.7224 | 3.1779 | 2.9155 | 4.4599 | 9.1823 | 12.3602 | -3.1106 | 6.026 | 1.6963 | 1.5545 | 1.4816 | 2.0889 | 4.7224 | 3.1779 | 2.9155 | 4.4699 | 9.1923 | 12.3702 | 0.01
2.154 | 7.1667 | 1.8718 | 1.8077 | 2.359 | 2.6154 | 6.0385 | 4.2308 | 9.3207 | 11.1284 | 17.1669 | 21.3977 | 2.154 | 7.1667 | 1.8718 | 1.8177 | 2.359 | 2.6154 | 6.0385 | 4.2308 | 9.3207 | 11.1384 | 17.1769 | 21.4077 | 0.01
7.67 | 8.3618 | 2.0557 | 2.0835 | 3.2783 | 3.167 | 7.4175 | 5.334 | 16.0319 | 18.1154 | 25.5329 | 30.8669 | 7.67 | 8.3618 | 2.0557 | 2.0935 | 3.2783 | 3.167 | 7.4175 | 5.334 | 16.0319 | 18.1254 | 25.5429 | 30.8769 | 0.01
15.8604 | 10.1364 | 2.3287 | 2.493 | 4.6434 | 3.986 | 9.4651 | 6.9721 | 25.9968 | 28.4898 | 37.9549 | 44.927 | 15.8604 | 10.1364 | 2.3287 | 2.503 | 4.6434 | 3.986 | 9.4651 | 6.9721 | 25.9968 | 28.4998 | 37.9649 | 44.937 | 0.01
-1.0877 | 6.4643 | 1.7637 | 1.6456 | 1.8187 | 2.2912 | 5.2281 | 3.5825 | 5.3766 | 7.0222 | 12.2503 | 15.8327 | -1.0877 | 6.4643 | 1.7637 | 1.6556 | 1.8187 | 2.2912 | 5.2281 | 3.5825 | 5.3766 | 7.0322 | 12.2603 | 15.8427 | 0.01
9.5656 | 8.7725 | 2.1189 | 2.1783 | 3.5943 | 3.3566 | 7.8914 | 5.7131 | 18.3381 | 20.5164 | 28.4078 | 34.1209 | 9.5656 | 8.7725 | 2.1189 | 2.1883 | 3.5943 | 3.3566 | 7.8914 | 5.7131 | 18.3381 | 20.5264 | 28.4178 | 34.1309 | 0.01
5.2751 | 7.8429 | 1.9758 | 1.9638 | 2.8792 | 2.9275 | 6.8188 | 4.855 | 13.1181 | 15.0818 | 21.9006 | 26.7557 | 5.2751 | 7.8429 | 1.9758 | 1.9738 | 2.8792 | 2.9275 | 6.8188 | 4.855 | 13.1181 | 15.0918 | 21.9106 | 26.7657 | 0.01
4.8547 | 7.7519 | 1.9618 | 1.9427 | 2.8091 | 2.8855 | 6.7137 | 4.7709 | 12.6066 | 14.5493 | 21.263 | 26.0339 | 4.8547 | 7.7519 | 1.9618 | 1.9527 | 2.8091 | 2.8855 | 6.7137 | 4.7709 | 12.6066 | 14.5593 | 21.273 | 26.0439 | 0.01
4.1225 | 7.5932 | 1.9374 | 1.9061 | 2.6871 | 2.8123 | 6.5306 | 4.6245 | 11.7157 | 13.6219 | 20.1525 | 24.777 | 4.1225 | 7.5932 | 1.9374 | 1.9161 | 2.6871 | 2.8123 | 6.5306 | 4.6245 | 11.7157 | 13.6319 | 20.1625 | 24.787 | 0.01
0.12817 | 6.7278 | 1.8043 | 1.7064 | 2.0214 | 2.4128 | 5.532 | 3.8256 | 6.8559 | 8.5623 | 14.0944 | 17.92 | 0.12817 | 6.7278 | 1.8043 | 1.7164 | 2.0214 | 2.4128 | 5.532 | 3.8256 | 6.8559 | 8.5723 | 14.1044 | 17.93 | 0.01
3.1497 | 7.3824 | 1.905 | 1.8575 | 2.525 | 2.715 | 6.2874 | 4.4299 | 10.5322 | 12.3897 | 18.6771 | 23.107 | 3.1497 | 7.3824 | 1.905 | 1.8675 | 2.525 | 2.715 | 6.2874 | 4.4299 | 10.5322 | 12.3997 | 18.6871 | 23.117 | 0.01
0.004088 | 6.7009 | 1.8001 | 1.7002 | 2.0007 | 2.4004 | 5.501 | 3.8008 | 6.705 | 8.4052 | 13.9062 | 17.707 | 0.004088 | 6.7009 | 1.8001 | 1.7102 | 2.0007 | 2.4004 | 5.501 | 3.8008 | 6.705 | 8.4152 | 13.9162 | 17.717 | 0.01
2.664 | 7.2772 | 1.8888 | 1.8332 | 2.444 | 2.6664 | 6.166 | 4.3328 | 9.9412 | 11.7744 | 17.9403 | 22.2731 | 2.664 | 7.2772 | 1.8888 | 1.8432 | 2.444 | 2.6664 | 6.166 | 4.3328 | 9.9412 | 11.7844 | 17.9503 | 22.2831 | 0.01
16.3601 | 10.2447 | 2.3453 | 2.518 | 4.7267 | 4.036 | 9.59 | 7.072 | 26.6047 | 29.1227 | 38.7127 | 45.7848 | 16.3601 | 10.2447 | 2.3453 | 2.528 | 4.7267 | 4.036 | 9.59 | 7.072 | 26.6047 | 29.1327 | 38.7227 | 45.7948 | 0.01
1.1157 | 6.9417 | 1.8372 | 1.7558 | 2.186 | 2.5116 | 5.7789 | 4.0231 | 8.0575 | 9.8133 | 15.5922 | 19.6153 | 1.1157 | 6.9417 | 1.8372 | 1.7658 | 2.186 | 2.5116 | 5.7789 | 4.0231 | 8.0575 | 9.8233 | 15.6022 | 19.6253 | 0.01
8.3578 | 8.5109 | 2.0786 | 2.1179 | 3.393 | 3.2358 | 7.5894 | 5.4716 | 16.8686 | 18.9865 | 26.576 | 32.0475 | 8.3578 | 8.5109 | 2.0786 | 2.1279 | 3.393 | 3.2358 | 7.5894 | 5.4716 | 16.8686 | 18.9965 | 26.586 | 32.0575 | 0.01
-3.237 | 5.9986 | 1.6921 | 1.5381 | 1.4605 | 2.0763 | 4.6907 | 3.1526 | 2.7616 | 4.2998 | 8.9905 | 12.1431 | -3.237 | 5.9986 | 1.6921 | 1.5481 | 1.4605 | 2.0763 | 4.6907 | 3.1526 | 2.7616 | 4.3098 | 9.0005 | 12.1531 | 0.01
3.8189 | 7.5274 | 1.9273 | 1.8909 | 2.6365 | 2.7819 | 6.4547 | 4.5638 | 11.3463 | 13.2373 | 19.692 | 24.2558 | 3.8189 | 7.5274 | 1.9273 | 1.9009 | 2.6365 | 2.7819 | 6.4547 | 4.5638 | 11.3463 | 13.2473 | 19.702 | 24.2658 | 0.01
9.7219 | 8.8064 | 2.1241 | 2.1861 | 3.6203 | 3.3722 | 7.9305 | 5.7444 | 18.5283 | 20.7144 | 28.6448 | 34.3892 | 9.7219 | 8.8064 | 2.1241 | 2.1961 | 3.6203 | 3.3722 | 7.9305 | 5.7444 | 18.5283 | 20.7244 | 28.6548 | 34.3992 | 0.01
8.9915 | 8.6482 | 2.0997 | 2.1496 | 3.4986 | 3.2992 | 7.7479 | 5.5983 | 17.6397 | 19.7893 | 27.5372 | 33.1355 | 8.9915 | 8.6482 | 2.0997 | 2.1596 | 3.4986 | 3.2992 | 7.7479 | 5.5983 | 17.6397 | 19.7993 | 27.5472 | 33.1455 | 0.01
-3.6954 | 5.8993 | 1.6768 | 1.5152 | 1.3841 | 2.0305 | 4.5762 | 3.0609 | 2.2039 | 3.7192 | 8.2953 | 11.3562 | -3.6954 | 5.8993 | 1.6768 | 1.5252 | 1.3841 | 2.0305 | 4.5762 | 3.0609 | 2.2039 | 3.7292 | 8.3053 | 11.3662 | 0.01
10.0738 | 8.8827 | 2.1358 | 2.2037 | 3.679 | 3.4074 | 8.0185 | 5.8148 | 18.9565 | 21.1602 | 29.1787 | 34.9934 | 10.0738 | 8.8827 | 2.1358 | 2.2137 | 3.679 | 3.4074 | 8.0185 | 5.8148 | 18.9565 | 21.1702 | 29.1887 | 35.0034 | 0.01
0.046038 | 6.71 | 1.8015 | 1.7023 | 2.0077 | 2.4046 | 5.5115 | 3.8092 | 6.756 | 8.4583 | 13.9698 | 17.779 | 0.046038 | 6.71 | 1.8015 | 1.7123 | 2.0077 | 2.4046 | 5.5115 | 3.8092 | 6.756 | 8.4683 | 13.9798 | 17.789 | 0.01
11.9431 | 9.2877 | 2.1981 | 2.2972 | 3.9905 | 3.5943 | 8.4858 | 6.1886 | 21.2308 | 23.528 | 32.0138 | 38.2024 | 11.9431 | 9.2877 | 2.1981 | 2.3072 | 3.9905 | 3.5943 | 8.4858 | 6.1886 | 21.2308 | 23.538 | 32.0238 | 38.2124 | 0.01
10.2351 | 8.9176 | 2.1412 | 2.2118 | 3.7058 | 3.4235 | 8.0588 | 5.847 | 19.1527 | 21.3645 | 29.4232 | 35.2703 | 10.2351 | 8.9176 | 2.1412 | 2.2218 | 3.7058 | 3.4235 | 8.0588 | 5.847 | 19.1527 | 21.3745 | 29.4332 | 35.2803 | 0.01
16.0073 | 10.1682 | 2.3336 | 2.5004 | 4.6679 | 4.0007 | 9.5018 | 7.0015 | 26.1755 | 28.6759 | 38.1777 | 45.1791 | 16.0073 | 10.1682 | 2.3336 | 2.5104 | 4.6679 | 4.0007 | 9.5018 | 7.0015 | 26.1755 | 28.6859 | 38.1877 | 45.1891 | 0.01
11.2117 | 9.1292 | 2.1737 | 2.2606 | 3.8686 | 3.5212 | 8.3029 | 6.0423 | 20.3409 | 22.6015 | 30.9044 | 36.9468 | 11.2117 | 9.1292 | 2.1737 | 2.2706 | 3.8686 | 3.5212 | 8.3029 | 6.0423 | 20.3409 | 22.6115 | 30.9144 | 36.9568 | 0.01
0.7651 | 6.8658 | 1.8255 | 1.7383 | 2.1275 | 2.4765 | 5.6913 | 3.953 | 7.6309 | 9.3691 | 15.0604 | 19.0134 | 0.7651 | 6.8658 | 1.8255 | 1.7483 | 2.1275 | 2.4765 | 5.6913 | 3.953 | 7.6309 | 9.3791 | 15.0704 | 19.0234 | 0.01
-2.5424 | 6.1491 | 1.7153 | 1.5729 | 1.5763 | 2.1458 | 4.8644 | 3.2915 | 3.6068 | 5.1796 | 10.044 | 13.3356 | -2.5424 | 6.1491 | 1.7153 | 1.5829 | 1.5763 | 2.1458 | 4.8644 | 3.2915 | 3.6068 | 5.1896 | 10.054 | 13.3456 | 0.01
6.6128 | 8.1328 | 2.0204 | 2.0306 | 3.1021 | 3.0613 | 7.1532 | 5.1226 | 14.7456 | 16.7763 | 23.9295 | 29.052 | 6.6128 | 8.1328 | 2.0204 | 2.0406 | 3.1021 | 3.0613 | 7.1532 | 5.1226 | 14.7456 | 16.7863 | 23.9395 | 29.062 | 0.01
-0.13011 | 6.6718 | 1.7957 | 1.6935 | 1.9783 | 2.387 | 5.4675 | 3.774 | 6.5417 | 8.2352 | 13.7027 | 17.4766 | -0.13011 | 6.6718 | 1.7957 | 1.7035 | 1.9783 | 2.387 | 5.4675 | 3.774 | 6.5417 | 8.2452 | 13.7127 | 17.4866 | 0.01
2.5146 | 7.2448 | 1.8838 | 1.8257 | 2.4191 | 2.6515 | 6.1286 | 4.3029 | 9.7594 | 11.5851 | 17.7138 | 22.0167 | 2.5146 | 7.2448 | 1.8838 | 1.8357 | 2.4191 | 2.6515 | 6.1286 | 4.3029 | 9.7594 | 11.5951 | 17.7238 | 22.0267 | 0.01
14.496 | 9.8408 | 2.2832 | 2.4248 | 4.416 | 3.8496 | 9.124 | 6.6992 | 24.3368 | 26.7616 | 35.8856 | 42.5848 | 14.496 | 9.8408 | 2.2832 | 2.4348 | 4.416 | 3.8496 | 9.124 | 6.6992 | 24.3368 | 26.7716 | 35.8956 | 42.5948 | 0.01
6.3767 | 8.0816 | 2.0126 | 2.0188 | 3.0628 | 3.0377 | 7.0942 | 5.0753 | 14.4583 | 16.4771 | 23.5713 | 28.6466 | 6.3767 | 8.0816 | 2.0126 | 2.0288 | 3.0628 | 3.0377 | 7.0942 | 5.0753 | 14.4583 | 16.4871 | 23.5813 | 28.6566 | 0.01
-0.66363 | 6.5562 | 1.7779 | 1.6668 | 1.8894 | 2.3336 | 5.3341 | 3.6673 | 5.8926 | 7.5594 | 12.8935 | 16.5608 | -0.66363 | 6.5562 | 1.7779 | 1.6768 | 1.8894 | 2.3336 | 5.3341 | 3.6673 | 5.8926 | 7.5694 | 12.9035 | 16.5708 | 0.01
6.6236 | 8.1351 | 2.0208 | 2.0312 | 3.1039 | 3.0624 | 7.1559 | 5.1247 | 14.7587 | 16.7899 | 23.9458 | 29.0705 | 6.6236 | 8.1351 | 2.0208 | 2.0412 | 3.1039 | 3.0624 | 7.1559 | 5.1247 | 14.7587 | 16.7999 | 23.9558 | 29.0805 | 0.01
-1.4404 | 6.3879 | 1.752 | 1.628 | 1.7599 | 2.256 | 5.1399 | 3.5119 | 4.9476 | 6.5755 | 11.7155 | 15.2274 | -1.4404 | 6.3879 | 1.752 | 1.638 | 1.7599 | 2.256 | 5.1399 | 3.5119 | 4.9476 | 6.5855 | 11.7255 | 15.2374 | 0.01
3.8707 | 7.5386 | 1.929 | 1.8935 | 2.6451 | 2.7871 | 6.4677 | 4.5741 | 11.4093 | 13.3029 | 19.7705 | 24.3447 | 3.8707 | 7.5386 | 1.929 | 1.9035 | 2.6451 | 2.7871 | 6.4677 | 4.5741 | 11.4093 | 13.3129 | 19.7805 | 24.3547 | 0.01
-11.3239 | 4.2465 | 1.4225 | 1.1338 | 0.11268 | 1.2676 | 2.669 | 1.5352 | -7.0774 | -5.9436 | -3.2746 | -1.7394 | -11.3239 | 4.2465 | 1.4225 | 1.1438 | 0.11268 | 1.2676 | 2.669 | 1.5352 | -7.0774 | -5.9336 | -3.2646 | -1.7294 | 0.01
8.374 | 8.5144 | 2.0791 | 2.1187 | 3.3957 | 3.2374 | 7.5935 | 5.4748 | 16.8884 | 19.0071 | 26.6006 | 32.0754 | 8.374 | 8.5144 | 2.0791 | 2.1287 | 3.3957 | 3.2374 | 7.5935 | 5.4748 | 16.8884 | 19.0171 | 26.6106 | 32.0854 | 0.01
12.9704 | 9.5102 | 2.2323 | 2.3485 | 4.1617 | 3.697 | 8.7426 | 6.3941 | 22.4806 | 24.8291 | 33.5717 | 39.9658 | 12.9704 | 9.5102 | 2.2323 | 2.3585 | 4.1617 | 3.697 | 8.7426 | 6.3941 | 22.4806 | 24.8391 | 33.5817 | 39.9758 | 0.01
1.7719 | 7.0839 | 1.8591 | 1.7886 | 2.2953 | 2.5772 | 5.943 | 4.1544 | 8.8558 | 10.6444 | 16.5874 | 20.7418 | 1.7719 | 7.0839 | 1.8591 | 1.7986 | 2.2953 | 2.5772 | 5.943 | 4.1544 | 8.8558 | 10.6544 | 16.5974 | 20.7518 | 0.01
-0.26064 | 6.6435 | 1.7913 | 1.687 | 1.9566 | 2.3739 | 5.4348 | 3.7479 | 6.3829 | 8.0699 | 13.5047 | 17.2526 | -0.26064 | 6.6435 | 1.7913 | 1.697 | 1.9566 | 2.3739 | 5.4348 | 3.7479 | 6.3829 | 8.0799 | 13.5147 | 17.2626 | 0.01
8.9346 | 8.6358 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7336 | 5.5869 | 17.5704 | 19.7171 | 27.4507 | 33.0376 | 8.9346 | 8.6358 | 2.0978 | 2.1567 | 3.4891 | 3.2935 | 7.7336 | 5.5869 | 17.5704 | 19.7271 | 27.4607 | 33.0476 | 0.01
8.9889 | 8.6476 | 2.0996 | 2.1494 | 3.4981 | 3.2989 | 7.7472 | 5.5978 | 17.6365 | 19.7859 | 27.5332 | 33.1309 | 8.9889 | 8.6476 | 2.0996 | 2.1594 | 3.4981 | 3.2989 | 7.7472 | 5.5978 | 17.6365 | 19.7959 | 27.5432 | 33.1409 | 0.01
5.2835 | 7.8448 | 1.9761 | 1.9642 | 2.8806 | 2.9284 | 6.8209 | 4.8567 | 13.1283 | 15.0925 | 21.9133 | 26.77 | 5.2835 | 7.8448 | 1.9761 | 1.9742 | 2.8806 | 2.9284 | 6.8209 | 4.8567 | 13.1283 | 15.1025 | 21.9233 | 26.78 | 0.01
9.4524 | 8.748 | 2.1151 | 2.1726 | 3.5754 | 3.3452 | 7.8631 | 5.6905 | 18.2004 | 20.373 | 28.2361 | 33.9266 | 9.4524 | 8.748 | 2.1151 | 2.1826 | 3.5754 | 3.3452 | 7.8631 | 5.6905 | 18.2004 | 20.383 | 28.2461 | 33.9366 | 0.01
12.1174 | 9.3254 | 2.2039 | 2.3059 | 4.0196 | 3.6117 | 8.5294 | 6.2235 | 21.4429 | 23.7487 | 32.2781 | 38.5016 | 12.1174 | 9.3254 | 2.2039 | 2.3159 | 4.0196 | 3.6117 | 8.5294 | 6.2235 | 21.4429 | 23.7587 | 32.2881 | 38.5116 | 0.01
2.5021 | 7.2421 | 1.8834 | 1.8251 | 2.417 | 2.6502 | 6.1255 | 4.3004 | 9.7443 | 11.5694 | 17.6949 | 21.9953 | 2.5021 | 7.2421 | 1.8834 | 1.8351 | 2.417 | 2.6502 | 6.1255 | 4.3004 | 9.7443 | 11.5794 | 17.7049 | 22.0053 | 0.01
0.91537 | 6.8983 | 1.8305 | 1.7458 | 2.1526 | 2.4915 | 5.7288 | 3.9831 | 7.8137 | 9.5595 | 15.2883 | 19.2714 | 0.91537 | 6.8983 | 1.8305 | 1.7558 | 2.1526 | 2.4915 | 5.7288 | 3.9831 | 7.8137 | 9.5695 | 15.2983 | 19.2814 | 0.01
-1.7202 | 6.3273 | 1.7427 | 1.614 | 1.7133 | 2.228 | 5.07 | 3.456 | 4.6071 | 6.2211 | 11.2911 | 14.7471 | -1.7202 | 6.3273 | 1.7427 | 1.624 | 1.7133 | 2.228 | 5.07 | 3.456 | 4.6071 | 6.2311 | 11.3011 | 14.7571 | 0.01
7.3217 | 8.2864 | 2.0441 | 2.0661 | 3.2203 | 3.1322 | 7.3304 | 5.2643 | 15.608 | 17.6741 | 25.0046 | 30.2689 | 7.3217 | 8.2864 | 2.0441 | 2.0761 | 3.2203 | 3.1322 | 7.3304 | 5.2643 | 15.608 | 17.6841 | 25.0146 | 30.2789 | 0.01
7.9757 | 8.4281 | 2.0659 | 2.0988 | 3.3293 | 3.1976 | 7.4939 | 5.3951 | 16.4037 | 18.5025 | 25.9965 | 31.3916 | 7.9757 | 8.4281 | 2.0659 | 2.1088 | 3.3293 | 3.1976 | 7.4939 | 5.3951 | 16.4037 | 18.5125 | 26.0065 | 31.4016 | 0.01
-2.8082 | 6.0916 | 1.7064 | 1.5596 | 1.532 | 2.1192 | 4.798 | 3.2384 | 3.2834 | 4.843 | 9.6409 | 12.8793 | -2.8082 | 6.0916 | 1.7064 | 1.5696 | 1.532 | 2.1192 | 4.798 | 3.2384 | 3.2834 | 4.853 | 9.6509 | 12.8893 | 0.01
-1.3037 | 6.4175 | 1.7565 | 1.6348 | 1.7827 | 2.2696 | 5.1741 | 3.5393 | 5.1139 | 6.7487 | 11.9228 | 15.462 | -1.3037 | 6.4175 | 1.7565 | 1.6448 | 1.7827 | 2.2696 | 5.1741 | 3.5393 | 5.1139 | 6.7587 | 11.9328 | 15.472 | 0.01
0.17091 | 6.737 | 1.8057 | 1.7085 | 2.0285 | 2.4171 | 5.5427 | 3.8342 | 6.9079 | 8.6165 | 14.1592 | 17.9934 | 0.17091 | 6.737 | 1.8057 | 1.7185 | 2.0285 | 2.4171 | 5.5427 | 3.8342 | 6.9079 | 8.6265 | 14.1692 | 18.0034 | 0.01
-7.6486 | 5.0428 | 1.545 | 1.3176 | 0.72523 | 1.6351 | 3.5878 | 2.2703 | -2.6058 | -1.2883 | 2.2996 | 4.5698 | -7.6486 | 5.0428 | 1.545 | 1.3276 | 0.72523 | 1.6351 | 3.5878 | 2.2703 | -2.6058 | -1.2783 | 2.3096 | 4.5798 | 0.01
7.5446 | 8.3347 | 2.0515 | 2.0772 | 3.2574 | 3.1545 | 7.3862 | 5.3089 | 15.8793 | 17.9565 | 25.3427 | 30.6516 | 7.5446 | 8.3347 | 2.0515 | 2.0872 | 3.2574 | 3.1545 | 7.3862 | 5.3089 | 15.8793 | 17.9665 | 25.3527 | 30.6616 | 0.01
9.7001 | 8.8017 | 2.1233 | 2.185 | 3.6167 | 3.37 | 7.925 | 5.74 | 18.5018 | 20.6869 | 28.6119 | 34.3519 | 9.7001 | 8.8017 | 2.1233 | 2.195 | 3.6167 | 3.37 | 7.925 | 5.74 | 18.5018 | 20.6969 | 28.6219 | 34.3619 | 0.01
8.0543 | 8.4451 | 2.0685 | 2.1027 | 3.3424 | 3.2054 | 7.5136 | 5.4109 | 16.4994 | 18.6021 | 26.1157 | 31.5266 | 8.0543 | 8.4451 | 2.0685 | 2.1127 | 3.3424 | 3.2054 | 7.5136 | 5.4109 | 16.4994 | 18.6121 | 26.1257 | 31.5366 | 0.01
-1.2755 | 6.4236 | 1.7575 | 1.6362 | 1.7874 | 2.2725 | 5.1811 | 3.5449 | 5.1482 | 6.7844 | 11.9655 | 15.5104 | -1.2755 | 6.4236 | 1.7575 | 1.6462 | 1.7874 | 2.2725 | 5.1811 | 3.5449 | 5.1482 | 6.7944 | 11.9755 | 15.5204 | 0.01
1.6532 | 7.0582 | 1.8551 | 1.7827 | 2.2755 | 2.5653 | 5.9133 | 4.1306 | 8.7114 | 10.494 | 16.4073 | 20.538 | 1.6532 | 7.0582 | 1.8551 | 1.7927 | 2.2755 | 2.5653 | 5.9133 | 4.1306 | 8.7114 | 10.504 | 16.4173 | 20.548 | 0.01
4.0014 | 7.567 | 1.9334 | 1.9001 | 2.6669 | 2.8001 | 6.5004 | 4.6003 | 11.5684 | 13.4685 | 19.9689 | 24.5692 | 4.0014 | 7.567 | 1.9334 | 1.9101 | 2.6669 | 2.8001 | 6.5004 | 4.6003 | 11.5684 | 13.4785 | 19.9789 | 24.5792 | 0.01
9.7211 | 8.8062 | 2.124 | 2.1861 | 3.6202 | 3.3721 | 7.9303 | 5.7442 | 18.5273 | 20.7134 | 28.6437 | 34.3879 | 9.7211 | 8.8062 | 2.124 | 2.1961 | 3.6202 | 3.3721 | 7.9303 | 5.7442 | 18.5273 | 20.7234 | 28.6537 | 34.3979 | 0.01
18.4405 | 10.6954 | 2.4147 | 2.622 | 5.0734 | 4.2441 | 10.1101 | 7.4881 | 29.136 | 31.758 | 41.8681 | 49.3562 | 18.4405 | 10.6954 | 2.4147 | 2.632 | 5.0734 | 4.2441 | 10.1101 | 7.4881 | 29.136 | 31.768 | 41.8781 | 49.3662 | 0.01
6.7586 | 8.1644 | 2.0253 | 2.0379 | 3.1264 | 3.0759 | 7.1896 | 5.1517 | 14.9229 | 16.9609 | 24.1505 | 29.3022 | 6.7586 | 8.1644 | 2.0253 | 2.0479 | 3.1264 | 3.0759 | 7.1896 | 5.1517 | 14.9229 | 16.9709 | 24.1605 | 29.3122 | 0.01
17.2651 | 10.4408 | 2.3755 | 2.5633 | 4.8775 | 4.1265 | 9.8163 | 7.253 | 27.7059 | 30.2692 | 40.0855 | 47.3385 | 17.2651 | 10.4408 | 2.3755 | 2.5733 | 4.8775 | 4.1265 | 9.8163 | 7.253 | 27.7059 | 30.2792 | 40.0955 | 47.3485 | 0.01
-4.1978 | 5.7905 | 1.6601 | 1.4901 | 1.3004 | 1.9802 | 4.4506 | 2.9604 | 1.5927 | 3.0828 | 7.5334 | 10.4938 | -4.1978 | 5.7905 | 1.6601 | 1.5001 | 1.3004 | 1.9802 | 4.4506 | 2.9604 | 1.5927 | 3.0928 | 7.5434 | 10.5038 | 0.01
7.4729 | 8.3191 | 2.0491 | 2.0736 | 3.2455 | 3.1473 | 7.3682 | 5.2946 | 15.7921 | 17.8657 | 25.2339 | 30.5285 | 7.4729 | 8.3191 | 2.0491 | 2.0836 | 3.2455 | 3.1473 | 7.3682 | 5.2946 | 15.7921 | 17.8757 | 25.2439 | 30.5385 | 0.01
-0.8847 | 6.5083 | 1.7705 | 1.6558 | 1.8525 | 2.3115 | 5.2788 | 3.6231 | 5.6236 | 7.2794 | 12.5582 | 16.1813 | -0.8847 | 6.5083 | 1.7705 | 1.6658 | 1.8525 | 2.3115 | 5.2788 | 3.6231 | 5.6236 | 7.2894 | 12.5682 | 16.1913 | 0.01
14.5788 | 9.8587 | 2.286 | 2.4289 | 4.4298 | 3.8579 | 9.1447 | 6.7158 | 24.4376 | 26.8665 | 36.0112 | 42.727 | 14.5788 | 9.8587 | 2.286 | 2.4389 | 4.4298 | 3.8579 | 9.1447 | 6.7158 | 24.4376 | 26.8765 | 36.0212 | 42.737 | 0.01
0.12537 | 6.7272 | 1.8042 | 1.7063 | 2.0209 | 2.4125 | 5.5313 | 3.8251 | 6.8525 | 8.5588 | 14.0901 | 17.9152 | 0.12537 | 6.7272 | 1.8042 | 1.7163 | 2.0209 | 2.4125 | 5.5313 | 3.8251 | 6.8525 | 8.5688 | 14.1001 | 17.9252 | 0.01
4.2245 | 7.6153 | 1.9408 | 1.9112 | 2.7041 | 2.8224 | 6.5561 | 4.6449 | 11.8398 | 13.751 | 20.3071 | 24.952 | 4.2245 | 7.6153 | 1.9408 | 1.9212 | 2.7041 | 2.8224 | 6.5561 | 4.6449 | 11.8398 | 13.761 | 20.3171 | 24.962 | 0.01
15.0219 | 9.9547 | 2.3007 | 2.4511 | 4.5036 | 3.9022 | 9.2555 | 6.8044 | 24.9766 | 27.4277 | 36.6832 | 43.4875 | 15.0219 | 9.9547 | 2.3007 | 2.4611 | 4.5036 | 3.9022 | 9.2555 | 6.8044 | 24.9766 | 27.4377 | 36.6932 | 43.4975 | 0.01
-2.3623 | 6.1882 | 1.7213 | 1.5819 | 1.6063 | 2.1638 | 4.9094 | 3.3275 | 3.8258 | 5.4077 | 10.3171 | 13.6446 | -2.3623 | 6.1882 | 1.7213 | 1.5919 | 1.6063 | 2.1638 | 4.9094 | 3.3275 | 3.8258 | 5.4177 | 10.3271 | 13.6546 | 0.01
-0.42982 | 6.6069 | 1.7857 | 1.6785 | 1.9284 | 2.357 | 5.3925 | 3.714 | 6.177 | 7.8556 | 13.2481 | 16.9621 | -0.42982 | 6.6069 | 1.7857 | 1.6885 | 1.9284 | 2.357 | 5.3925 | 3.714 | 6.177 | 7.8656 | 13.2581 | 16.9721 | 0.01
7.7003 | 8.3684 | 2.0567 | 2.085 | 3.2834 | 3.17 | 7.4251 | 5.3401 | 16.0687 | 18.1537 | 25.5788 | 30.9188 | 7.7003 | 8.3684 | 2.0567 | 2.095 | 3.2834 | 3.17 | 7.4251 | 5.3401 | 16.0687 | 18.1637 | 25.5888 | 30.9288 | 0.01
5.0337 | 7.7906 | 1.9678 | 1.9517 | 2.839 | 2.9034 | 6.7584 | 4.8067 | 12.8244 | 14.776 | 21.5345 | 26.3412 | 5.0337 | 7.7906 | 1.9678 | 1.9617 | 2.839 | 2.9034 | 6.7584 | 4.8067 | 12.8244 | 14.786 | 21.5445 | 26.3512 | 0.01
3.2793 | 7.4105 | 1.9093 | 1.864 | 2.5465 | 2.7279 | 6.3198 | 4.4559 | 10.6898 | 12.5538 | 18.8736 | 23.3294 | 3.2793 | 7.4105 | 1.9093 | 1.874 | 2.5465 | 2.7279 | 6.3198 | 4.4559 | 10.6898 | 12.5638 | 18.8836 | 23.3394 | 0.01
-0.40881 | 6.6114 | 1.7864 | 1.6796 | 1.9319 | 2.3591 | 5.3978 | 3.7182 | 6.2026 | 7.8822 | 13.28 | 16.9982 | -0.40881 | 6.6114 | 1.7864 | 1.6896 | 1.9319 | 2.3591 | 5.3978 | 3.7182 | 6.2026 | 7.8922 | 13.29 | 17.0082 | 0.01
12.3703 | 9.3802 | 2.2123 | 2.3185 | 4.0617 | 3.637 | 8.5926 | 6.2741 | 21.7505 | 24.069 | 32.6616 | 38.9356 | 12.3703 | 9.3802 | 2.2123 | 2.3285 | 4.0617 | 3.637 | 8.5926 | 6.2741 | 21.7505 | 24.079 | 32.6716 | 38.9456 | 0.01
9.2318 | 8.7002 | 2.1077 | 2.1616 | 3.5386 | 3.3232 | 7.8079 | 5.6464 | 17.932 | 20.0936 | 27.9015 | 33.5479 | 9.2318 | 8.7002 | 2.1077 | 2.1716 | 3.5386 | 3.3232 | 7.8079 | 5.6464 | 17.932 | 20.1036 | 27.9115 | 33.5579 | 0.01
9.9205 | 8.8494 | 2.1307 | 2.196 | 3.6534 | 3.392 | 7.9801 | 5.7841 | 18.7699 | 20.9659 | 28.946 | 34.7301 | 9.9205 | 8.8494 | 2.1307 | 2.206 | 3.6534 | 3.392 | 7.9801 | 5.7841 | 18.7699 | 20.9759 | 28.956 | 34.7401 | 0.01
12.8623 | 9.4868 | 2.2287 | 2.3431 | 4.1437 | 3.6862 | 8.7156 | 6.3725 | 22.3491 | 24.6922 | 33.4078 | 39.7802 | 12.8623 | 9.4868 | 2.2287 | 2.3531 | 4.1437 | 3.6862 | 8.7156 | 6.3725 | 22.3491 | 24.7022 | 33.4178 | 39.7902 | 0.01
-2.6898 | 6.1172 | 1.7103 | 1.5655 | 1.5517 | 2.131 | 4.8276 | 3.262 | 3.4274 | 4.9929 | 9.8205 | 13.0825 | -2.6898 | 6.1172 | 1.7103 | 1.5755 | 1.5517 | 2.131 | 4.8276 | 3.262 | 3.4274 | 5.0029 | 9.8305 | 13.0925 | 0.01
10.976 | 9.0781 | 2.1659 | 2.2488 | 3.8293 | 3.4976 | 8.244 | 5.9952 | 20.0542 | 22.303 | 30.547 | 36.5422 | 10.976 | 9.0781 | 2.1659 | 2.2588 | 3.8293 | 3.4976 | 8.244 | 5.9952 | 20.0542 | 22.313 | 30.557 | 36.5522 | 0.01
6.1885 | 8.0408 | 2.0063 | 2.0094 | 3.0314 | 3.0189 | 7.0471 | 5.0377 | 14.2294 | 16.2388 | 23.2859 | 28.3237 | 6.1885 | 8.0408 | 2.0063 | 2.0194 | 3.0314 | 3.0189 | 7.0471 | 5.0377 | 14.2294 | 16.2488 | 23.2959 | 28.3337 | 0.01
-0.0097864 | 6.6979 | 1.7997 | 1.6995 | 1.9984 | 2.399 | 5.4976 | 3.798 | 6.6881 | 8.3876 | 13.8852 | 17.6832 | -0.0097864 | 6.6979 | 1.7997 | 1.7095 | 1.9984 | 2.399 | 5.4976 | 3.798 | 6.6881 | 8.3976 | 13.8952 | 17.6932 | 0.01
13.3212 | 9.5863 | 2.244 | 2.3661 | 4.2202 | 3.7321 | 8.8303 | 6.4642 | 22.9074 | 25.2735 | 34.1038 | 40.568 | 13.3212 | 9.5863 | 2.244 | 2.3761 | 4.2202 | 3.7321 | 8.8303 | 6.4642 | 22.9074 | 25.2835 | 34.1138 | 40.578 | 0.01
-0.72099 | 6.5438 | 1.776 | 1.664 | 1.8798 | 2.3279 | 5.3198 | 3.6558 | 5.8228 | 7.4867 | 12.8065 | 16.4623 | -0.72099 | 6.5438 | 1.776 | 1.674 | 1.8798 | 2.3279 | 5.3198 | 3.6558 | 5.8228 | 7.4967 | 12.8165 | 16.4723 | 0.01
-0.99952 | 6.4834 | 1.7667 | 1.65 | 1.8334 | 2.3 | 5.2501 | 3.6001 | 5.4839 | 7.1339 | 12.3841 | 15.9842 | -0.99952 | 6.4834 | 1.7667 | 1.66 | 1.8334 | 2.3 | 5.2501 | 3.6001 | 5.4839 | 7.1439 | 12.3941 | 15.9942 | 0.01
1.5168 | 7.0286 | 1.8506 | 1.7758 | 2.2528 | 2.5517 | 5.8792 | 4.1034 | 8.5455 | 10.3213 | 16.2005 | 20.3039 | 1.5168 | 7.0286 | 1.8506 | 1.7858 | 2.2528 | 2.5517 | 5.8792 | 4.1034 | 8.5455 | 10.3313 | 16.2105 | 20.3139 | 0.01
-0.58033 | 6.5743 | 1.7807 | 1.671 | 1.9033 | 2.342 | 5.3549 | 3.6839 | 5.9939 | 7.6649 | 13.0198 | 16.7038 | -0.58033 | 6.5743 | 1.7807 | 1.681 | 1.9033 | 2.342 | 5.3549 | 3.6839 | 5.9939 | 7.6749 | 13.0298 | 16.7138 | 0.01
0.17113 | 6.7371 | 1.8057 | 1.7086 | 2.0285 | 2.4171 | 5.5428 | 3.8342 | 6.9082 | 8.6168 | 14.1595 | 17.9938 | 0.17113 | 6.7371 | 1.8057 | 1.7186 | 2.0285 | 2.4171 | 5.5428 | 3.8342 | 6.9082 | 8.6268 | 14.1695 | 18.0038 | 0.01
0.074319 | 6.7161 | 1.8025 | 1.7037 | 2.0124 | 2.4074 | 5.5186 | 3.8149 | 6.7904 | 8.4941 | 14.0127 | 17.8276 | 0.074319 | 6.7161 | 1.8025 | 1.7137 | 2.0124 | 2.4074 | 5.5186 | 3.8149 | 6.7904 | 8.5041 | 14.0227 | 17.8376 | 0.01
1.085 | 6.9351 | 1.8362 | 1.7543 | 2.1808 | 2.5085 | 5.7713 | 4.017 | 8.0201 | 9.7744 | 15.5456 | 19.5626 | 1.085 | 6.9351 | 1.8362 | 1.7643 | 2.1808 | 2.5085 | 5.7713 | 4.017 | 8.0201 | 9.7844 | 15.5556 | 19.5726 | 0.01
-3.1212 | 6.0237 | 1.696 | 1.5439 | 1.4798 | 2.0879 | 4.7197 | 3.1758 | 2.9025 | 4.4464 | 9.1661 | 12.3419 | -3.1212 | 6.0237 | 1.696 | 1.5539 | 1.4798 | 2.0879 | 4.7197 | 3.1758 | 2.9025 | 4.4564 | 9.1761 | 12.3519 | 0.01
6.0895 | 8.0194 | 2.003 | 2.0045 | 3.0149 | 3.009 | 7.0224 | 5.0179 | 14.1089 | 16.1134 | 23.1357 | 28.1536 | 6.0895 | 8.0194 | 2.003 | 2.0145 | 3.0149 | 3.009 | 7.0224 | 5.0179 | 14.1089 | 16.1234 | 23.1457 | 28.1636 | 0.01
6.2141 | 8.0464 | 2.0071 | 2.0107 | 3.0357 | 3.0214 | 7.0535 | 5.0428 | 14.2605 | 16.2712 | 23.3247 | 28.3676 | 6.2141 | 8.0464 | 2.0071 | 2.0207 | 3.0357 | 3.0214 | 7.0535 | 5.0428 | 14.2605 | 16.2812 | 23.3347 | 28.3776 | 0.01
9.4624 | 8.7502 | 2.1154 | 2.1731 | 3.5771 | 3.3462 | 7.8656 | 5.6925 | 18.2126 | 20.3857 | 28.2513 | 33.9437 | 9.4624 | 8.7502 | 2.1154 | 2.1831 | 3.5771 | 3.3462 | 7.8656 | 5.6925 | 18.2126 | 20.3957 | 28.2613 | 33.9537 | 0.01
2.7991 | 7.3065 | 1.8933 | 1.84 | 2.4665 | 2.6799 | 6.1998 | 4.3598 | 10.1056 | 11.9456 | 18.1454 | 22.5052 | 2.7991 | 7.3065 | 1.8933 | 1.85 | 2.4665 | 2.6799 | 6.1998 | 4.3598 | 10.1056 | 11.9556 | 18.1554 | 22.5152 | 0.01
0.57475 | 6.8245 | 1.8192 | 1.7287 | 2.0958 | 2.4575 | 5.6437 | 3.915 | 7.3993 | 9.128 | 14.7717 | 18.6867 | 0.57475 | 6.8245 | 1.8192 | 1.7387 | 2.0958 | 2.4575 | 5.6437 | 3.915 | 7.3993 | 9.138 | 14.7817 | 18.6967 | 0.01
9.4411 | 8.7456 | 2.1147 | 2.1721 | 3.5735 | 3.3441 | 7.8603 | 5.6882 | 18.1866 | 20.3587 | 28.219 | 33.9072 | 9.4411 | 8.7456 | 2.1147 | 2.1821 | 3.5735 | 3.3441 | 7.8603 | 5.6882 | 18.1866 | 20.3687 | 28.229 | 33.9172 | 0.01
-1.3256 | 6.4128 | 1.7558 | 1.6337 | 1.7791 | 2.2674 | 5.1686 | 3.5349 | 5.0872 | 6.7209 | 11.8896 | 15.4244 | -1.3256 | 6.4128 | 1.7558 | 1.6437 | 1.7791 | 2.2674 | 5.1686 | 3.5349 | 5.0872 | 6.7309 | 11.8996 | 15.4344 | 0.01
6.3785 | 8.082 | 2.0126 | 2.0189 | 3.0631 | 3.0379 | 7.0946 | 5.0757 | 14.4605 | 16.4794 | 23.5741 | 28.6498 | 6.3785 | 8.082 | 2.0126 | 2.0289 | 3.0631 | 3.0379 | 7.0946 | 5.0757 | 14.4605 | 16.4894 | 23.5841 | 28.6598 | 0.01
1.0149 | 6.9199 | 1.8338 | 1.7507 | 2.1692 | 2.5015 | 5.7537 | 4.003 | 7.9348 | 9.6856 | 15.4393 | 19.4423 | 1.0149 | 6.9199 | 1.8338 | 1.7607 | 2.1692 | 2.5015 | 5.7537 | 4.003 | 7.9348 | 9.6956 | 15.4493 | 19.4523 | 0.01
3.1071 | 7.3732 | 1.9036 | 1.8554 | 2.5178 | 2.7107 | 6.2768 | 4.4214 | 10.4803 | 12.3356 | 18.6124 | 23.0338 | 3.1071 | 7.3732 | 1.9036 | 1.8654 | 2.5178 | 2.7107 | 6.2768 | 4.4214 | 10.4803 | 12.3456 | 18.6224 | 23.0438 | 0.01
8.6083 | 8.5651 | 2.0869 | 2.1304 | 3.4347 | 3.2608 | 7.6521 | 5.5217 | 17.1734 | 19.3038 | 26.9559 | 32.4776 | 8.6083 | 8.5651 | 2.0869 | 2.1404 | 3.4347 | 3.2608 | 7.6521 | 5.5217 | 17.1734 | 19.3138 | 26.9659 | 32.4876 | 0.01
-7.3979 | 5.0971 | 1.5534 | 1.3301 | 0.76701 | 1.6602 | 3.6505 | 2.3204 | -2.3008 | -0.97073 | 2.6798 | 5.0002 | -7.3979 | 5.0971 | 1.5534 | 1.3401 | 0.76701 | 1.6602 | 3.6505 | 2.3204 | -2.3008 | -0.96073 | 2.6898 | 5.0102 | 0.01
9.1391 | 8.6801 | 2.1046 | 2.157 | 3.5232 | 3.3139 | 7.7848 | 5.6278 | 17.8192 | 19.9762 | 27.7609 | 33.3887 | 9.1391 | 8.6801 | 2.1046 | 2.167 | 3.5232 | 3.3139 | 7.7848 | 5.6278 | 17.8192 | 19.9862 | 27.7709 | 33.3987 | 0.01
10.1185 | 8.8923 | 2.1373 | 2.2059 | 3.6864 | 3.4118 | 8.0296 | 5.8237 | 19.0108 | 21.2168 | 29.2464 | 35.0701 | 10.1185 | 8.8923 | 2.1373 | 2.2159 | 3.6864 | 3.4118 | 8.0296 | 5.8237 | 19.0108 | 21.2268 | 29.2564 | 35.0801 | 0.01
8.8895 | 8.6261 | 2.0963 | 2.1445 | 3.4816 | 3.289 | 7.7224 | 5.5779 | 17.5156 | 19.6601 | 27.3825 | 32.9604 | 8.8895 | 8.6261 | 2.0963 | 2.1545 | 3.4816 | 3.289 | 7.7224 | 5.5779 | 17.5156 | 19.6701 | 27.3925 | 32.9704 | 0.01
18.1174 | 10.6254 | 2.4039 | 2.6059 | 5.0196 | 4.2117 | 10.0293 | 7.4235 | 28.7428 | 31.3487 | 41.378 | 48.8015 | 18.1174 | 10.6254 | 2.4039 | 2.6159 | 5.0196 | 4.2117 | 10.0293 | 7.4235 | 28.7428 | 31.3587 | 41.388 | 48.8115 | 0.01
-4.172 | 5.7961 | 1.6609 | 1.4914 | 1.3047 | 1.9828 | 4.457 | 2.9656 | 1.6241 | 3.1155 | 7.5725 | 10.5381 | -4.172 | 5.7961 | 1.6609 | 1.5014 | 1.3047 | 1.9828 | 4.457 | 2.9656 | 1.6241 | 3.1255 | 7.5825 | 10.5481 | 0.01
4.7866 | 7.7371 | 1.9596 | 1.9393 | 2.7978 | 2.8787 | 6.6966 | 4.7573 | 12.5236 | 14.463 | 21.1596 | 25.9169 | 4.7866 | 7.7371 | 1.9596 | 1.9493 | 2.7978 | 2.8787 | 6.6966 | 4.7573 | 12.5236 | 14.473 | 21.1696 | 25.9269 | 0.01
8.5519 | 8.5529 | 2.0851 | 2.1276 | 3.4253 | 3.2552 | 7.638 | 5.5104 | 17.1048 | 19.2324 | 26.8704 | 32.3807 | 8.5519 | 8.5529 | 2.0851 | 2.1376 | 3.4253 | 3.2552 | 7.638 | 5.5104 | 17.1048 | 19.2424 | 26.8804 | 32.3907 | 0.01
6.8119 | 8.1759 | 2.0271 | 2.0406 | 3.1353 | 3.0812 | 7.203 | 5.1624 | 14.9878 | 17.0284 | 24.2313 | 29.3937 | 6.8119 | 8.1759 | 2.0271 | 2.0506 | 3.1353 | 3.0812 | 7.203 | 5.1624 | 14.9878 | 17.0384 | 24.2413 | 29.4037 | 0.01
-7.8754 | 4.9937 | 1.5375 | 1.3062 | 0.68743 | 1.6125 | 3.5311 | 2.2249 | -2.8818 | -1.5755 | 1.9556 | 4.1805 | -7.8754 | 4.9937 | 1.5375 | 1.3162 | 0.68743 | 1.6125 | 3.5311 | 2.2249 | -2.8818 | -1.5655 | 1.9656 | 4.1905 | 0.01
3.4751 | 7.4529 | 1.9158 | 1.8738 | 2.5792 | 2.7475 | 6.3688 | 4.495 | 10.9281 | 12.8018 | 19.1706 | 23.6656 | 3.4751 | 7.4529 | 1.9158 | 1.8838 | 2.5792 | 2.7475 | 6.3688 | 4.495 | 10.9281 | 12.8118 | 19.1806 | 23.6756 | 0.01
-3.9303 | 5.8484 | 1.669 | 1.5035 | 1.345 | 2.007 | 4.5174 | 3.0139 | 1.9181 | 3.4216 | 7.9391 | 10.953 | -3.9303 | 5.8484 | 1.669 | 1.5135 | 1.345 | 2.007 | 4.5174 | 3.0139 | 1.9181 | 3.4316 | 7.9491 | 10.963 | 0.01
11.6169 | 9.217 | 2.1872 | 2.2808 | 3.9362 | 3.5617 | 8.4042 | 6.1234 | 20.8339 | 23.1148 | 31.519 | 37.6424 | 11.6169 | 9.217 | 2.1872 | 2.2908 | 3.9362 | 3.5617 | 8.4042 | 6.1234 | 20.8339 | 23.1248 | 31.529 | 37.6524 | 0.01
6.6067 | 8.1315 | 2.0202 | 2.0303 | 3.1011 | 3.0607 | 7.1517 | 5.1213 | 14.7382 | 16.7685 | 23.9202 | 29.0415 | 6.6067 | 8.1315 | 2.0202 | 2.0403 | 3.1011 | 3.0607 | 7.1517 | 5.1213 | 14.7382 | 16.7785 | 23.9302 | 29.0515 | 0.01
3.6787 | 7.4971 | 1.9226 | 1.8839 | 2.6131 | 2.7679 | 6.4197 | 4.5357 | 11.1758 | 13.0597 | 19.4794 | 24.0151 | 3.6787 | 7.4971 | 1.9226 | 1.8939 | 2.6131 | 2.7679 | 6.4197 | 4.5357 | 11.1758 | 13.0697 | 19.4894 | 24.0251 | 0.01
10.0022 | 8.8671 | 2.1334 | 2.2001 | 3.667 | 3.4002 | 8.0005 | 5.8004 | 18.8693 | 21.0694 | 29.07 | 34.8704 | 10.0022 | 8.8671 | 2.1334 | 2.2101 | 3.667 | 3.4002 | 8.0005 | 5.8004 | 18.8693 | 21.0794 | 29.08 | 34.8804 | 0.01
2.8576 | 7.3192 | 1.8953 | 1.8429 | 2.4763 | 2.6858 | 6.2144 | 4.3715 | 10.1768 | 12.0197 | 18.2341 | 22.6056 | 2.8576 | 7.3192 | 1.8953 | 1.8529 | 2.4763 | 2.6858 | 6.2144 | 4.3715 | 10.1768 | 12.0297 | 18.2441 | 22.6156 | 0.01
-5.7356 | 5.4573 | 1.6088 | 1.4132 | 1.0441 | 1.8264 | 4.0661 | 2.6529 | -0.2783 | 1.1349 | 5.201 | 7.8539 | -5.7356 | 5.4573 | 1.6088 | 1.4232 | 1.0441 | 1.8264 | 4.0661 | 2.6529 | -0.2783 | 1.1449 | 5.211 | 7.8639 | 0.01
-0.24152 | 6.6477 | 1.7919 | 1.6879 | 1.9597 | 2.3758 | 5.4396 | 3.7517 | 6.4062 | 8.0941 | 13.5337 | 17.2854 | -0.24152 | 6.6477 | 1.7919 | 1.6979 | 1.9597 | 2.3758 | 5.4396 | 3.7517 | 6.4062 | 8.1041 | 13.5437 | 17.2954 | 0.01
-1.1184 | 6.4577 | 1.7627 | 1.6441 | 1.8136 | 2.2882 | 5.2204 | 3.5763 | 5.3393 | 6.9834 | 12.2038 | 15.7801 | -1.1184 | 6.4577 | 1.7627 | 1.6541 | 1.8136 | 2.2882 | 5.2204 | 3.5763 | 5.3393 | 6.9934 | 12.2138 | 15.7901 | 0.01
9.8841 | 8.8416 | 1.6146 | 2.1942 | 3.6474 | 3.3884 | 7.971 | 5.7768 | 18.7257 | 20.9199 | 28.891 | 34.6678 | 9.8841 | 8.8416 | 1.6146 | 2.2042 | 3.6474 | 3.3884 | 7.971 | 5.7768 | 18.7257 | 20.9299 | 28.901 | 34.6778 | 0.01
-5.5634 | 5.4946 | 1.9328 | 1.4218 | 1.0728 | 1.8437 | 4.1091 | 2.6873 | -0.068833 | 1.353 | 5.4621 | 8.1495 | -5.5634 | 5.4946 | 1.9328 | 1.4318 | 1.0728 | 1.8437 | 4.1091 | 2.6873 | -0.068833 | 1.363 | 5.4721 | 8.1595 | 0.01
3.9837 | 7.5631 | 2.3331 | 1.8992 | 2.6639 | 2.7984 | 6.4959 | 4.5967 | 11.5468 | 13.446 | 19.9419 | 24.5386 | 3.9837 | 7.5631 | 2.3331 | 1.9092 | 2.6639 | 2.7984 | 6.4959 | 4.5967 | 11.5468 | 13.456 | 19.9519 | 24.5486 | 0.01
15.9941 | 10.1654 | 1.7859 | 2.4997 | 4.6657 | 3.9994 | 9.4985 | 6.9988 | 26.1595 | 28.6592 | 38.1577 | 45.1566 | 15.9941 | 10.1654 | 1.7859 | 2.5097 | 4.6657 | 3.9994 | 9.4985 | 6.9988 | 26.1595 | 28.6692 | 38.1677 | 45.1666 | 0.01
-0.42261 | 6.6084 | 1.794 | 1.6789 | 1.9296 | 2.3577 | 5.3943 | 3.7155 | 6.1858 | 7.8647 | 13.259 | 16.9745 | -0.42261 | 6.6084 | 1.794 | 1.6889 | 1.9296 | 2.3577 | 5.3943 | 3.7155 | 6.1858 | 7.8747 | 13.269 | 16.9845 | 0.01
-0.18131 | 6.6607 | 1.9908 | 1.6909 | 1.9698 | 2.3819 | 5.4547 | 3.7637 | 6.4794 | 8.1703 | 13.625 | 17.3887 | -0.18131 | 6.6607 | 1.9908 | 1.7009 | 1.9698 | 2.3819 | 5.4547 | 3.7637 | 6.4794 | 8.1803 | 13.635 | 17.3987 | 0.01
5.7226 | 7.9399 | 2.0474 | 1.9861 | 2.9538 | 2.9723 | 6.9306 | 4.9445 | 13.6625 | 15.6486 | 22.5792 | 27.5238 | 5.7226 | 7.9399 | 2.0474 | 1.9961 | 2.9538 | 2.9723 | 6.9306 | 4.9445 | 13.6625 | 15.6586 | 22.5892 | 27.5338 | 0.01
7.4208 | 8.3078 | 2.0177 | 2.071 | 3.2368 | 3.1421 | 7.3552 | 5.2842 | 15.7286 | 17.7997 | 25.1549 | 30.439 | 7.4208 | 8.3078 | 2.0177 | 2.081 | 3.2368 | 3.1421 | 7.3552 | 5.2842 | 15.7286 | 17.8097 | 25.1649 | 30.449 | 0.01
6.5317 | 8.1152 | 2.2316 | 2.0266 | 3.0886 | 3.0532 | 7.1329 | 5.1063 | 14.6469 | 16.6735 | 23.8064 | 28.9127 | 6.5317 | 8.1152 | 2.2316 | 2.0366 | 3.0886 | 3.0532 | 7.1329 | 5.1063 | 14.6469 | 16.6835 | 23.8164 | 28.9227 | 0.01
12.9487 | 9.5056 | 2.2484 | 2.3474 | 4.1581 | 3.6949 | 8.7372 | 6.3897 | 22.4543 | 24.8017 | 33.5389 | 39.9286 | 12.9487 | 9.5056 | 2.2484 | 2.3574 | 4.1581 | 3.6949 | 8.7372 | 6.3897 | 22.4543 | 24.8117 | 33.5489 | 39.9386 | 0.01
13.4512 | 9.6144 | 1.8607 | 2.3726 | 4.2419 | 3.7451 | 8.8628 | 6.4902 | 23.0656 | 25.4382 | 34.301 | 40.7912 | 13.4512 | 9.6144 | 1.8607 | 2.3826 | 4.2419 | 3.7451 | 8.8628 | 6.4902 | 23.0656 | 25.4482 | 34.311 | 40.8012 | 0.01
1.8217 | 7.0947 | 2.0947 | 1.7911 | 2.3036 | 2.5822 | 5.9554 | 4.1643 | 8.9164 | 10.7075 | 16.6629 | 20.8272 | 1.8217 | 7.0947 | 2.0947 | 1.8011 | 2.3036 | 2.5822 | 5.9554 | 4.1643 | 8.9164 | 10.7175 | 16.6729 | 20.8372 | 0.01
8.8397 | 8.6153 | 1.8922 | 2.142 | 3.4733 | 3.284 | 7.7099 | 5.5679 | 17.455 | 19.597 | 27.3069 | 32.8748 | 8.8397 | 8.6153 | 1.8922 | 2.152 | 3.4733 | 3.284 | 7.7099 | 5.5679 | 17.455 | 19.607 | 27.3169 | 32.8848 | 0.01
2.7666 | 7.2994 | 2.0757 | 1.8383 | 2.4611 | 2.6767 | 6.1916 | 4.3533 | 10.066 | 11.9043 | 18.0959 | 22.4493 | 2.7666 | 7.2994 | 2.0757 | 1.8483 | 2.4611 | 2.6767 | 6.1916 | 4.3533 | 10.066 | 11.9143 | 18.1059 | 22.4593 | 0.01
8.2722 | 8.4923 | 1.8633 | 2.1136 | 3.3787 | 3.2272 | 7.568 | 5.4544 | 16.7645 | 18.8781 | 26.4461 | 31.9006 | 8.2722 | 8.4923 | 1.8633 | 2.1236 | 3.3787 | 3.2272 | 7.568 | 5.4544 | 16.7645 | 18.8881 | 26.4561 | 31.9106 | 0.01
1.8989 | 7.1114 | 2.0766 | 1.7949 | 2.3165 | 2.5899 | 5.9747 | 4.1798 | 9.0103 | 10.8052 | 16.7799 | 20.9597 | 1.8989 | 7.1114 | 2.0766 | 1.8049 | 2.3165 | 2.5899 | 5.9747 | 4.1798 | 9.0103 | 10.8152 | 16.7899 | 20.9697 | 0.01
8.2977 | 8.4978 | 2.1503 | 2.1149 | 3.3829 | 3.2298 | 7.5744 | 5.4595 | 16.7955 | 18.9104 | 26.4848 | 31.9444 | 8.2977 | 8.4978 | 2.1503 | 2.1249 | 3.3829 | 3.2298 | 7.5744 | 5.4595 | 16.7955 | 18.9204 | 26.4948 | 31.9544 | 0.01
10.5101 | 8.9772 | 2.0598 | 2.2255 | 3.7517 | 3.451 | 8.1275 | 5.902 | 19.4873 | 21.7128 | 29.8404 | 35.7424 | 10.5101 | 8.9772 | 2.0598 | 2.2355 | 3.7517 | 3.451 | 8.1275 | 5.902 | 19.4873 | 21.7228 | 29.8504 | 35.7524 | 0.01
7.7932 | 8.3885 | 2.4427 | 2.0897 | 3.2989 | 3.1793 | 7.4483 | 5.3586 | 16.1817 | 18.2714 | 25.7197 | 31.0784 | 7.7932 | 8.3885 | 2.4427 | 2.0997 | 3.2989 | 3.1793 | 7.4483 | 5.3586 | 16.1817 | 18.2814 | 25.7297 | 31.0884 | 0.01
19.2796 | 10.8773 | 1.7714 | 2.664 | 5.2133 | 4.328 | 10.3199 | 7.6559 | 30.1569 | 32.8209 | 43.1408 | 50.7967 | 19.2796 | 10.8773 | 1.7714 | 2.674 | 5.2133 | 4.328 | 10.3199 | 7.6559 | 30.1569 | 32.8309 | 43.1508 | 50.8067 | 0.01
-0.85792 | 6.5141 | 1.9787 | 1.6571 | 1.857 | 2.3142 | 5.2855 | 3.6284 | 5.6562 | 7.3133 | 12.5988 | 16.2272 | -0.85792 | 6.5141 | 1.9787 | 1.6671 | 1.857 | 2.3142 | 5.2855 | 3.6284 | 5.6562 | 7.3233 | 12.6088 | 16.2372 | 0.01
5.3618 | 7.8617 | 2.1086 | 1.9681 | 2.8936 | 2.9362 | 6.8405 | 4.8724 | 13.2236 | 15.1917 | 22.0321 | 26.9045 | 5.3618 | 7.8617 | 2.1086 | 1.9781 | 2.8936 | 2.9362 | 6.8405 | 4.8724 | 13.2236 | 15.2017 | 22.0421 | 26.9145 | 0.01
9.2577 | 8.7058 | 2.1426 | 2.1629 | 3.543 | 3.3258 | 7.8144 | 5.6515 | 17.9635 | 20.1264 | 27.9408 | 33.5924 | 9.2577 | 8.7058 | 2.1426 | 2.1729 | 3.543 | 3.3258 | 7.8144 | 5.6515 | 17.9635 | 20.1364 | 27.9508 | 33.6024 | 0.01
10.2787 | 8.9271 | 2.2081 | 2.2139 | 3.7131 | 3.4279 | 8.0697 | 5.8557 | 19.2058 | 21.4197 | 29.4894 | 35.3451 | 10.2787 | 8.9271 | 2.2081 | 2.2239 | 3.7131 | 3.4279 | 8.0697 | 5.8557 | 19.2058 | 21.4297 | 29.4994 | 35.3551 | 0.01
12.2433 | 9.3527 | 1.7133 | 2.3122 | 4.0406 | 3.6243 | 8.5608 | 6.2487 | 21.5961 | 23.9082 | 32.4691 | 38.7177 | 12.2433 | 9.3527 | 1.7133 | 2.3222 | 4.0406 | 3.6243 | 8.5608 | 6.2487 | 21.5961 | 23.9182 | 32.4791 | 38.7277 | 0.01
-2.602 | 6.1362 | 2.0305 | 1.5699 | 1.5663 | 2.1398 | 4.8495 | 3.2796 | 3.5343 | 5.1042 | 9.9537 | 13.2333 | -2.602 | 6.1362 | 2.0305 | 1.5799 | 1.5663 | 2.1398 | 4.8495 | 3.2796 | 3.5343 | 5.1142 | 9.9637 | 13.2433 | 0.01
6.9152 | 8.1983 | 1.9055 | 2.0458 | 3.1525 | 3.0915 | 7.2288 | 5.183 | 15.1135 | 17.1593 | 24.3881 | 29.5711 | 6.9152 | 8.1983 | 1.9055 | 2.0558 | 3.1525 | 3.0915 | 7.2288 | 5.183 | 15.1135 | 17.1693 | 24.3981 | 29.5811 | 0.01
3.1651 | 7.3858 | 2.0144 | 1.8583 | 2.5275 | 2.7165 | 6.2913 | 4.433 | 10.5509 | 12.4091 | 18.7004 | 23.1334 | 3.1651 | 7.3858 | 2.0144 | 1.8683 | 2.5275 | 2.7165 | 6.2913 | 4.433 | 10.5509 | 12.4191 | 18.7104 | 23.1434 | 0.01
6.4306 | 8.0933 | 1.864 | 2.0215 | 3.0718 | 3.0431 | 7.1076 | 5.0861 | 14.5239 | 16.5454 | 23.653 | 28.7391 | 6.4306 | 8.0933 | 1.864 | 2.0315 | 3.0718 | 3.0431 | 7.1076 | 5.0861 | 14.5239 | 16.5554 | 23.663 | 28.7491 | 0.01
1.919 | 7.1158 | 1.9736 | 1.7959 | 2.3198 | 2.5919 | 5.9797 | 4.1838 | 9.0347 | 10.8307 | 16.8104 | 20.9942 | 1.919 | 7.1158 | 1.9736 | 1.8059 | 2.3198 | 2.5919 | 5.9797 | 4.1838 | 9.0347 | 10.8407 | 16.8204 | 21.0042 | 0.01
5.2075 | 7.8283 | 1.9672 | 1.9604 | 2.8679 | 2.9207 | 6.8019 | 4.8415 | 13.0358 | 14.9962 | 21.798 | 26.6395 | 5.2075 | 7.8283 | 1.9672 | 1.9704 | 2.8679 | 2.9207 | 6.8019 | 4.8415 | 13.0358 | 15.0062 | 21.808 | 26.6495 | 0.01
5.0148 | 7.7865 | 1.9804 | 1.9507 | 2.8358 | 2.9015 | 6.7537 | 4.803 | 12.8013 | 14.7521 | 21.5058 | 26.3087 | 5.0148 | 7.7865 | 1.9804 | 1.9607 | 2.8358 | 2.9015 | 6.7537 | 4.803 | 12.8013 | 14.7621 | 21.5158 | 26.3187 | 0.01
5.4118 | 7.8725 | 1.82 | 1.9706 | 2.902 | 2.9412 | 6.8529 | 4.8824 | 13.2843 | 15.2549 | 22.1078 | 26.9902 | 5.4118 | 7.8725 | 1.82 | 1.9806 | 2.902 | 2.9412 | 6.8529 | 4.8824 | 13.2843 | 15.2649 | 22.1178 | 27.0002 | 0.01
0.60033 | 6.8301 | 2.1284 | 1.73 | 2.1001 | 2.46 | 5.6501 | 3.9201 | 7.4304 | 9.1604 | 14.8105 | 18.7306 | 0.60033 | 6.8301 | 2.1284 | 1.74 | 2.1001 | 2.46 | 5.6501 | 3.9201 | 7.4304 | 9.1704 | 14.8205 | 18.7406 | 0.01
9.8505 | 8.8343 | 1.9956 | 2.1925 | 3.6418 | 3.3851 | 7.9626 | 5.7701 | 18.6848 | 20.8773 | 28.84 | 34.6101 | 9.8505 | 8.8343 | 1.9956 | 2.2025 | 3.6418 | 3.3851 | 7.9626 | 5.7701 | 18.6848 | 20.8873 | 28.85 | 34.6201 | 0.01
5.8682 | 7.9714 | 1.8458 | 1.9934 | 2.978 | 2.9868 | 6.9671 | 4.9736 | 13.8396 | 15.8331 | 22.8001 | 27.7737 | 5.8682 | 7.9714 | 1.8458 | 2.0034 | 2.978 | 2.9868 | 6.9671 | 4.9736 | 13.8396 | 15.8431 | 22.8101 | 27.7837 | 0.01
1.3746 | 6.9978 | 2.3455 | 1.7687 | 2.2291 | 2.5375 | 5.8436 | 4.0749 | 8.3724 | 10.1411 | 15.9848 | 20.0597 | 1.3746 | 6.9978 | 2.3455 | 1.7787 | 2.2291 | 2.5375 | 5.8436 | 4.0749 | 8.3724 | 10.1511 | 15.9948 | 20.0697 | 0.01
16.3663 | 10.246 | 2.1493 | 2.5183 | 4.7277 | 4.0366 | 9.5916 | 7.0733 | 26.6123 | 29.1306 | 38.7222 | 45.7954 | 16.3663 | 10.246 | 2.1493 | 2.5283 | 4.7277 | 4.0366 | 9.5916 | 7.0733 | 26.6123 | 29.1406 | 38.7322 | 45.8054 | 0.01
10.4785 | 8.9703 | 2.2881 | 2.2239 | 3.7464 | 3.4479 | 8.1196 | 5.8957 | 19.4488 | 21.6728 | 29.7924 | 35.6881 | 10.4785 | 8.9703 | 2.2881 | 2.2339 | 3.7464 | 3.4479 | 8.1196 | 5.8957 | 19.4488 | 21.6828 | 29.8024 | 35.6981 | 0.01
14.6431 | 9.8727 | 2.1757 | 2.4322 | 4.4405 | 3.8643 | 9.1608 | 6.7286 | 24.5157 | 26.9479 | 36.1087 | 42.8373 | 14.6431 | 9.8727 | 2.1757 | 2.4422 | 4.4405 | 3.8643 | 9.1608 | 6.7286 | 24.5157 | 26.9579 | 36.1187 | 42.8473 | 0.01
11.2705 | 9.1419 | 1.6904 | 2.2635 | 3.8784 | 3.5271 | 8.3176 | 6.0541 | 20.4125 | 22.676 | 30.9936 | 37.0477 | 11.2705 | 9.1419 | 1.6904 | 2.2735 | 3.8784 | 3.5271 | 8.3176 | 6.0541 | 20.4125 | 22.686 | 31.0036 | 37.0577 | 0.01
-3.2871 | 5.9878 | 1.9339 | 1.5356 | 1.4522 | 2.0713 | 4.6782 | 3.1426 | 2.7008 | 4.2364 | 8.9146 | 12.0572 | -3.2871 | 5.9878 | 1.9339 | 1.5456 | 1.4522 | 2.0713 | 4.6782 | 3.1426 | 2.7008 | 4.2464 | 8.9246 | 12.0672 | 0.01
4.0163 | 7.5702 | 1.9562 | 1.9008 | 2.6694 | 2.8016 | 6.5041 | 4.6033 | 11.5865 | 13.4873 | 19.9914 | 24.5946 | 4.0163 | 7.5702 | 1.9562 | 1.9108 | 2.6694 | 2.8016 | 6.5041 | 4.6033 | 11.5865 | 13.4973 | 20.0014 | 24.6046 | 0.01
4.6864 | 7.7154 | 1.8488 | 1.9343 | 2.7811 | 2.8686 | 6.6716 | 4.7373 | 12.4018 | 14.3361 | 21.0078 | 25.745 | 4.6864 | 7.7154 | 1.8488 | 1.9443 | 2.7811 | 2.8686 | 6.6716 | 4.7373 | 12.4018 | 14.3461 | 21.0178 | 25.755 | 0.01
1.4634 | 7.0171 | 1.7742 | 1.7732 | 2.2439 | 3.5791 | 5.8659 | 4.0927 | 8.4805 | 10.2536 | 16.1195 | 20.2122 | 1.4634 | 7.0171 | 1.7742 | 1.7832 | 2.2439 | 3.5791 | 5.8659 | 4.0927 | 8.4805 | 10.2636 | 16.1295 | 20.2222 | 0.01
-0.77368 | 6.5324 | 2.193 | 1.6613 | 1.8711 | 1.6857 | 5.3066 | 3.6453 | 5.7587 | 7.42 | 12.7266 | 16.3718 | -0.77368 | 6.5324 | 2.193 | 1.6713 | 1.8711 | 1.6857 | 5.3066 | 3.6453 | 5.7587 | 7.43 | 12.7366 | 16.3818 | 0.01
11.7905 | 9.2546 | 1.5619 | 2.2895 | 3.9651 | 2.9119 | 8.4476 | 6.1581 | 21.0451 | 23.3346 | 31.7823 | 37.9404 | 11.7905 | 9.2546 | 1.5619 | 2.2995 | 3.9651 | 2.9119 | 8.4476 | 6.1581 | 21.0451 | 23.3446 | 31.7923 | 37.9504 | 0.01
-7.1426 | 5.1524 | 1.9706 | 1.3429 | 0.80957 | 3.4348 | 3.7144 | 2.3715 | -1.9901 | -0.64725 | 3.5972 | 5.9687 | -7.1426 | 5.1524 | 1.9706 | 1.3529 | 0.80957 | 3.4348 | 3.7144 | 2.3715 | -1.9901 | -0.63725 | 3.6072 | 5.9787 | 0.01
5.1192 | 7.8092 | 2.1449 | 1.956 | 2.8532 | 3.9823 | 6.7798 | 4.8238 | 12.9284 | 14.8844 | 21.7198 | 26.5437 | 5.1192 | 7.8092 | 2.1449 | 1.966 | 2.8532 | 3.9823 | 6.7798 | 4.8238 | 12.9284 | 14.8944 | 21.7298 | 26.5537 | 0.01
10.3484 | 8.9421 | 2.3274 | 2.2174 | 3.7247 | 2.3004 | 8.0871 | 5.8697 | 19.2905 | 21.5079 | 29.595 | 35.4647 | 10.3484 | 8.9421 | 2.3274 | 2.2274 | 3.7247 | 2.3004 | 8.0871 | 5.8697 | 19.2905 | 21.5179 | 29.605 | 35.4747 | 0.01
15.8226 | 10.1282 | 1.7668 | 2.4911 | 4.6371 | 1.4393 | 9.4556 | 6.9645 | 25.9508 | 28.442 | 37.8976 | 44.8621 | 15.8226 | 10.1282 | 1.7668 | 2.5011 | 4.6371 | 1.4393 | 9.4556 | 6.9645 | 25.9508 | 28.452 | 37.9076 | 44.8721 | 0.01
-0.99638 | 6.4841 | 1.4798 | 1.6502 | 1.8339 | 2.1554 | 5.2509 | 3.6007 | 5.4877 | 7.1379 | 12.3888 | 15.9895 | -0.99638 | 6.4841 | 1.4798 | 1.6602 | 1.8339 | 2.1554 | 5.2509 | 3.6007 | 5.4877 | 7.1479 | 12.3988 | 15.9995 | 0.01
-9.6069 | 4.6185 | 1.7185 | 1.2197 | 0.39885 | 2.5843 | 4.8886 | 1.8786 | -4.9884 | -3.7688 | 1.1198 | 2.9984 | -9.6069 | 4.6185 | 1.7185 | 1.2297 | 0.39885 | 2.5843 | 4.8886 | 1.8786 | -4.9884 | -3.7588 | 1.1298 | 3.0084 | 0.01
-2.4456 | 6.1701 | 1.8614 | 1.5777 | 1.5924 | 2.3528 | 5.9607 | 3.3109 | 3.7245 | 5.3022 | 11.2629 | 14.5738 | -2.4456 | 6.1701 | 1.8614 | 1.5877 | 1.5924 | 2.3528 | 5.9607 | 3.3109 | 3.7245 | 5.3122 | 11.2729 | 14.5838 | 0.01
1.8427 | 7.0993 | 1.7843 | 1.7921 | 2.3071 | 2.7307 | 5.3821 | 4.1685 | 8.942 | 10.7341 | 16.1162 | 20.2847 | 1.8427 | 7.0993 | 1.7843 | 1.8021 | 2.3071 | 2.7307 | 5.3821 | 4.1685 | 8.942 | 10.7441 | 16.1262 | 20.2947 | 0.01
-0.47175 | 6.5978 | 1.9102 | 1.6764 | 1.9214 | 2.5396 | 6.3268 | 3.7057 | 6.126 | 7.8025 | 14.1292 | 17.8349 | -0.47175 | 6.5978 | 1.9102 | 1.6864 | 1.9214 | 2.5396 | 6.3268 | 3.7057 | 6.126 | 7.8125 | 14.1392 | 17.8449 | 0.01
3.3071 | 7.4165 | 1.8465 | 1.7698 | 2.5512 | 2.4087 | 5.8491 | 4.4614 | 10.7236 | 12.4935 | 18.3426 | 22.804 | 3.3071 | 7.4165 | 1.8465 | 1.7798 | 2.5512 | 2.4087 | 5.8491 | 4.4614 | 10.7236 | 12.5035 | 18.3526 | 22.814 | 0.01
1.3965 | 7.0026 | 1.8029 | 1.7043 | 2.2327 | 3.3494 | 5.5217 | 4.0793 | 8.399 | 10.1034 | 15.6855 | 19.7648 | 1.3965 | 7.0026 | 1.8029 | 1.7143 | 2.2327 | 3.3494 | 5.5217 | 4.0793 | 8.399 | 10.1134 | 15.6955 | 19.7748 | 0.01
0.08672 | 6.7188 | 2.1165 | 2.1747 | 2.0145 | 3.9835 | 7.8734 | 3.8173 | 6.8055 | 8.9802 | 16.8536 | 20.671 | 0.08672 | 6.7188 | 2.1165 | 2.1847 | 2.0145 | 3.9835 | 7.8734 | 3.8173 | 6.8055 | 8.9902 | 16.8636 | 20.681 | 0.01
9.4938 | 8.757 | 2.3278 | 2.4917 | 3.5823 | 3.2911 | 9.4587 | 5.6988 | 18.2508 | 20.7425 | 30.2012 | 35.8999 | 9.4938 | 8.757 | 2.3278 | 2.5017 | 3.5823 | 3.2911 | 9.4587 | 5.6988 | 18.2508 | 20.7525 | 30.2112 | 35.9099 | 0.01
15.8348 | 10.1309 | 2.097 | 2.1455 | 4.6391 | 3.8318 | 7.7276 | 6.967 | 25.9657 | 28.1112 | 36.5822 | 43.5491 | 15.8348 | 10.1309 | 2.097 | 2.1555 | 4.6391 | 3.8318 | 7.7276 | 6.967 | 25.9657 | 28.1212 | 36.5922 | 43.5591 | 0.01
8.9106 | 8.6306 | 2.2773 | 2.4159 | 3.4851 | 2.4722 | 9.0796 | 5.5821 | 17.5412 | 19.9571 | 29.0368 | 34.6189 | 8.9106 | 8.6306 | 2.2773 | 2.4259 | 3.4851 | 2.4722 | 9.0796 | 5.5821 | 17.5412 | 19.9671 | 29.0468 | 34.6289 | 0.01
14.3184 | 9.8023 | 1.8241 | 1.7361 | 4.3864 | 3.1013 | 5.6806 | 6.6637 | 24.1208 | 25.8569 | 33.3446 | 40.0083 | 14.3184 | 9.8023 | 1.8241 | 1.7461 | 4.3864 | 3.1013 | 5.6806 | 6.6637 | 24.1208 | 25.8669 | 33.3546 | 40.0183 | 0.01
0.7224 | 6.8565 | 2.0338 | 2.0506 | 2.1204 | 4.3384 | 7.2532 | 3.9445 | 7.5789 | 9.6296 | 16.8828 | 20.8273 | 0.7224 | 6.8565 | 2.0338 | 2.0606 | 2.1204 | 4.3384 | 7.2532 | 3.9445 | 7.5789 | 9.6396 | 16.8928 | 20.8373 | 0.01
7.0128 | 8.2194 | 2.4461 | 2.6692 | 3.1688 | 1.3988 | 10.346 | 5.2026 | 15.2323 | 17.9015 | 28.2475 | 33.45 | 7.0128 | 8.2194 | 2.4461 | 2.6792 | 3.1688 | 1.3988 | 10.346 | 5.2026 | 15.2323 | 17.9115 | 28.2575 | 33.46 | 0.01
19.384 | 10.8999 | 1.4663 | 1.1994 | 5.2307 | 4.3226 | 2.9969 | 7.6768 | 30.2838 | 31.4832 | 41.0365 | 48.7133 | 19.384 | 10.8999 | 1.4663 | 1.2094 | 5.2307 | 4.3226 | 2.9969 | 7.6768 | 30.2838 | 31.4932 | 41.0465 | 48.7233 | 0.01
19.2262 | 4.5307 | 2.4409 | 2.6613 | 0.33129 | 3.8214 | 10.3065 | 1.7975 | 23.7568 | 26.4181 | 36.7247 | 38.5222 | 19.2262 | 4.5307 | 2.4409 | 2.6713 | 0.33129 | 3.8214 | 10.3065 | 1.7975 | 23.7568 | 26.4281 | 36.7347 | 38.5322 | 0.01
14.2142 | 10.8657 | 2.2738 | 2.4107 | 5.2044 | 2.1505 | 9.0535 | 7.6452 | 25.0798 | 27.4905 | 36.5441 | 44.1893 | 14.2142 | 10.8657 | 2.2738 | 2.4207 | 5.2044 | 2.1505 | 9.0535 | 7.6452 | 25.0798 | 27.5005 | 36.5541 | 44.1993 | 0.01
-2.4952 | 9.7797 | 1.7168 | 1.5752 | 4.369 | 3.5234 | 4.8762 | 6.6428 | 7.2846 | 8.8598 | 16.7522 | 23.395 | -2.4952 | 9.7797 | 1.7168 | 1.5852 | 4.369 | 3.5234 | 4.8762 | 6.6428 | 7.2846 | 8.8698 | 16.7622 | 23.405 | 0.01
11.2336 | 6.1594 | 2.1745 | 2.2617 | 1.5841 | 4.0163 | 8.3084 | 3.301 | 17.393 | 19.6547 | 27.9631 | 31.2641 | 11.2336 | 6.1594 | 2.1745 | 2.2717 | 1.5841 | 4.0163 | 8.3084 | 3.301 | 17.393 | 19.6647 | 27.9731 | 31.2741 | 0.01
16.1635 | 9.134 | 2.3388 | 2.5082 | 3.8723 | 2.7069 | 9.5409 | 6.0467 | 25.2974 | 27.8056 | 37.3465 | 43.3932 | 16.1635 | 9.134 | 2.3388 | 2.5182 | 3.8723 | 2.7069 | 9.5409 | 6.0467 | 25.2974 | 27.8156 | 37.3565 | 43.4032 | 0.01
3.0691 | 10.2021 | 1.9023 | 1.8535 | 4.2369 | 3.7422 | 6.2673 | 7.0327 | 13.2711 | 15.1246 | 23.1037 | 30.1364 | 3.0691 | 10.2021 | 1.9023 | 1.8635 | 4.2369 | 3.7422 | 6.2673 | 7.0327 | 13.2711 | 15.1346 | 23.1137 | 30.1464 | 0.01
13.4216 | 7.365 | 2.2474 | 2.3711 | 4.3798 | 3.8279 | 8.8554 | 4.4138 | 20.7866 | 23.1577 | 32.0131 | 36.4269 | 13.4216 | 7.365 | 2.2474 | 2.3811 | 4.3798 | 3.8279 | 8.8554 | 4.4138 | 20.7866 | 23.1677 | 32.0231 | 36.4369 | 0.01
14.2791 | 9.608 | 2.276 | 2.414 | 2.4376 | 2.6625 | 9.0698 | 6.4843 | 23.8871 | 26.301 | 35.3708 | 41.8551 | 14.2791 | 9.608 | 2.276 | 2.424 | 2.4376 | 2.6625 | 9.0698 | 6.4843 | 23.8871 | 26.311 | 35.3808 | 41.8651 | 0.01
2.6253 | 9.7938 | 1.8875 | 1.8313 | 0.72184 | 1.6331 | 6.1563 | 6.6558 | 12.4191 | 14.2504 | 20.4067 | 27.0625 | 2.6253 | 9.7938 | 1.8875 | 1.8413 | 0.72184 | 1.6331 | 6.1563 | 6.6558 | 12.4191 | 14.2604 | 20.4167 | 27.0725 | 0.01
-7.6689 | 7.2688 | 1.5444 | 1.3166 | 4.3164 | 3.7899 | 3.5828 | 4.3251 | -0.40013 | 0.91643 | 9.0227 | 13.3478 | -7.6689 | 7.2688 | 1.5444 | 1.3266 | 4.3164 | 3.7899 | 3.5828 | 4.3251 | -0.40013 | 0.92643 | 9.0327 | 13.3578 | 0.01
13.8987 | 5.0384 | 2.2633 | 2.3949 | 4.5377 | 3.9226 | 8.9747 | 2.2662 | 18.9371 | 21.332 | 30.3067 | 32.5729 | 13.8987 | 5.0384 | 2.2633 | 2.4049 | 4.5377 | 3.9226 | 8.9747 | 2.2662 | 18.9371 | 21.342 | 30.3167 | 32.5829 | 0.01
15.2263 | 9.7114 | 2.3075 | 2.4613 | 5.1783 | 4.307 | 9.3066 | 6.5797 | 24.9377 | 27.399 | 36.8844 | 43.4641 | 15.2263 | 9.7114 | 2.3075 | 2.4713 | 5.1783 | 4.307 | 9.3066 | 6.5797 | 24.9377 | 27.409 | 36.8944 | 43.4741 | 0.01
19.0701 | 9.999 | 2.4357 | 2.6535 | 1.7349 | 2.2409 | 10.2675 | 6.8453 | 29.0691 | 31.7226 | 41.9902 | 48.8354 | 19.0701 | 9.999 | 2.4357 | 2.6635 | 1.7349 | 2.2409 | 10.2675 | 6.8453 | 29.0691 | 31.7326 | 42.0002 | 48.8454 | 0.01
-1.5907 | 10.8319 | 1.747 | 1.6205 | 3.4667 | 3.28 | 5.1023 | 7.614 | 9.2411 | 10.8616 | 17.6083 | 25.2223 | -1.5907 | 10.8319 | 1.747 | 1.6305 | 3.4667 | 3.28 | 5.1023 | 7.614 | 9.2411 | 10.8716 | 17.6183 | 25.2323 | 0.01
8.8001 | 6.3553 | 2.0933 | 2.14 | 3.3661 | 3.2197 | 7.7 | 3.4819 | 15.1554 | 17.2954 | 24.9955 | 28.4773 | 8.8001 | 6.3553 | 2.0933 | 2.15 | 3.3661 | 3.2197 | 7.7 | 3.4819 | 15.1554 | 17.3054 | 25.0055 | 28.4873 | 0.01
8.1966 | 8.6067 | 2.0732 | 2.1098 | 2.9229 | 2.9538 | 7.5492 | 5.56 | 16.8033 | 18.9131 | 26.4623 | 32.0223 | 8.1966 | 8.6067 | 2.0732 | 2.1198 | 2.9229 | 2.9538 | 7.5492 | 5.56 | 16.8033 | 18.9231 | 26.4723 | 32.0323 | 0.01
5.5376 | 8.4759 | 1.9846 | 1.9769 | 2.3602 | 2.6161 | 6.8844 | 5.4393 | 14.0135 | 15.9904 | 22.8748 | 28.3141 | 5.5376 | 8.4759 | 1.9846 | 1.9869 | 2.3602 | 2.6161 | 6.8844 | 5.4393 | 14.0135 | 16.0004 | 22.8848 | 28.3241 | 0.01
2.1614 | 7.8998 | 1.872 | 1.8081 | 2.489 | 2.6934 | 6.0403 | 4.9075 | 10.0612 | 11.8692 | 17.9096 | 22.8171 | 2.1614 | 7.8998 | 1.872 | 1.8181 | 2.489 | 2.6934 | 6.0403 | 4.9075 | 10.0612 | 11.8792 | 17.9196 | 22.8271 | 0.01
2.9341 | 7.1683 | 1.8978 | 1.8467 | 3.9122 | 3.5473 | 6.2335 | 4.2323 | 10.1024 | 11.9491 | 19.4087 | 23.641 | 2.9341 | 7.1683 | 1.8978 | 1.8567 | 3.9122 | 3.5473 | 6.2335 | 4.2323 | 10.1024 | 11.9591 | 19.4187 | 23.651 | 0.01
11.4734 | 7.3357 | 2.1824 | 2.2737 | 4.5221 | 3.9133 | 8.3684 | 4.3868 | 18.8092 | 21.0828 | 29.5182 | 33.9051 | 11.4734 | 7.3357 | 2.1824 | 2.2837 | 4.5221 | 3.9133 | 8.3684 | 4.3868 | 18.8092 | 21.0928 | 29.5282 | 33.9151 | 0.01
15.1327 | 9.1859 | 2.3044 | 2.4566 | 3.0515 | 3.0309 | 9.2832 | 6.0947 | 24.3186 | 26.7752 | 36.0584 | 42.1531 | 15.1327 | 9.1859 | 2.3044 | 2.4666 | 3.0515 | 3.0309 | 9.2832 | 6.0947 | 24.3186 | 26.7852 | 36.0684 | 42.1631 | 0.01
6.309 | 9.9788 | 2.0103 | 2.0154 | 3.3918 | 3.2351 | 7.0772 | 6.8265 | 16.2877 | 18.3032 | 25.3804 | 32.207 | 6.309 | 9.9788 | 2.0103 | 2.0254 | 3.3918 | 3.2351 | 7.0772 | 6.8265 | 16.2877 | 18.3132 | 25.3904 | 32.217 | 0.01
8.3508 | 8.0669 | 2.0784 | 2.1175 | 3.9998 | 3.5999 | 7.5877 | 5.0618 | 16.4178 | 18.5353 | 26.135 | 31.1968 | 8.3508 | 8.0669 | 2.0784 | 2.1275 | 3.9998 | 3.5999 | 7.5877 | 5.0618 | 16.4178 | 18.5453 | 26.145 | 31.2068 | 0.01
11.9988 | 8.5093 | 2.2 | 2.2999 | 3.3774 | 3.2265 | 8.4997 | 5.4702 | 20.5081 | 22.808 | 31.3077 | 36.7779 | 11.9988 | 8.5093 | 2.2 | 2.3099 | 3.3774 | 3.2265 | 8.4997 | 5.4702 | 20.5081 | 22.818 | 31.3177 | 36.7879 | 0.01
8.2645 | 9.2997 | 2.0755 | 2.1132 | 2.4958 | 2.6975 | 7.5661 | 6.1998 | 17.5643 | 19.6775 | 27.2436 | 33.4434 | 8.2645 | 9.2997 | 2.0755 | 2.1232 | 2.4958 | 2.6975 | 7.5661 | 6.1998 | 17.5643 | 19.6875 | 27.2536 | 33.4534 | 0.01
2.9748 | 8.4906 | 1.8992 | 1.8487 | 3.6696 | 3.4018 | 6.2437 | 5.4529 | 11.4654 | 13.3142 | 20.3856 | 25.8385 | 2.9748 | 8.4906 | 1.8992 | 1.8587 | 3.6696 | 3.4018 | 6.2437 | 5.4529 | 11.4654 | 13.3242 | 20.3956 | 25.8485 | 0.01
10.0178 | 7.3445 | 2.1339 | 2.2009 | 2.3627 | 2.6176 | 8.0044 | 4.395 | 17.3623 | 19.5632 | 27.5677 | 31.9626 | 10.0178 | 7.3445 | 2.1339 | 2.2109 | 2.3627 | 2.6176 | 8.0044 | 4.395 | 17.3623 | 19.5732 | 27.5777 | 31.9726 | 0.01
2.1761 | 8.8705 | 1.8725 | 1.8088 | 3.6992 | 3.4195 | 6.044 | 5.8036 | 11.0466 | 12.8554 | 19.9742 | 25.7777 | 2.1761 | 8.8705 | 1.8725 | 1.8188 | 3.6992 | 3.4195 | 6.044 | 5.8036 | 11.0466 | 12.8654 | 19.9842 | 25.7877 | 0.01
10.1953 | 7.1715 | 2.1398 | 2.2098 | 2.0614 | 2.4368 | 8.0488 | 4.2352 | 17.3668 | 19.5765 | 27.6253 | 31.8606 | 10.1953 | 7.1715 | 2.1398 | 2.2198 | 2.0614 | 2.4368 | 8.0488 | 4.2352 | 17.3668 | 19.5865 | 27.6353 | 31.8706 | 0.01
0.36812 | 8.909 | 1.8123 | 1.7184 | 3.4738 | 3.2843 | 5.592 | 5.8391 | 9.2771 | 10.9955 | 17.7536 | 23.5926 | 0.36812 | 8.909 | 1.8123 | 1.7284 | 3.4738 | 3.2843 | 5.592 | 5.8391 | 9.2771 | 11.0055 | 17.7636 | 23.6026 | 0.01
8.8428 | 6.7798 | 2.0948 | 2.1421 | 2.5607 | 2.7364 | 7.7107 | 3.8736 | 15.6225 | 17.7647 | 25.4753 | 29.349 | 8.8428 | 6.7798 | 2.0948 | 2.1521 | 2.5607 | 2.7364 | 7.7107 | 3.8736 | 15.6225 | 17.7747 | 25.4853 | 29.359 | 0.01
3.3639 | 8.6159 | 1.9121 | 1.8682 | 3.7195 | 3.4317 | 6.341 | 5.5686 | 11.9799 | 13.8481 | 20.9992 | 26.5678 | 3.3639 | 8.6159 | 1.9121 | 1.8782 | 3.7195 | 3.4317 | 6.341 | 5.5686 | 11.9799 | 13.8581 | 21.0092 | 26.5778 | 0.01
10.3169 | 7.4289 | 2.1439 | 2.2158 | 4.0749 | 3.645 | 8.0792 | 4.4728 | 17.7457 | 19.9616 | 28.0408 | 32.5136 | 10.3169 | 7.4289 | 2.1439 | 2.2258 | 4.0749 | 3.645 | 8.0792 | 4.4728 | 17.7457 | 19.9716 | 28.0508 | 32.5236 | 0.01
12.4496 | 8.9353 | 2.215 | 2.3225 | 3.8485 | 3.5091 | 8.6124 | 5.8634 | 21.3849 | 23.7074 | 32.3198 | 38.1832 | 12.4496 | 8.9353 | 2.215 | 2.3325 | 3.8485 | 3.5091 | 8.6124 | 5.8634 | 21.3849 | 23.7174 | 32.3298 | 38.1932 | 0.01
11.0913 | 9.3974 | 2.1697 | 2.2546 | 1.6992 | 2.2195 | 8.2728 | 6.2899 | 20.4887 | 22.7433 | 31.0161 | 37.306 | 11.0913 | 9.3974 | 2.1697 | 2.2646 | 1.6992 | 2.2195 | 8.2728 | 6.2899 | 20.4887 | 22.7533 | 31.0261 | 37.316 | 0.01
-1.8049 | 9.1031 | 1.7398 | 1.6098 | 3.2226 | 3.1336 | 5.0488 | 6.0183 | 7.2982 | 8.908 | 15.2642 | 21.2824 | -1.8049 | 9.1031 | 1.7398 | 1.6198 | 3.2226 | 3.1336 | 5.0488 | 6.0183 | 7.2982 | 8.918 | 15.2742 | 21.2924 | 0.01
7.3357 | 6.3089 | 2.0445 | 2.0668 | 4.1585 | 3.6951 | 7.3339 | 3.439 | 13.6446 | 15.7114 | 23.565 | 27.004 | 7.3357 | 6.3089 | 2.0445 | 2.0768 | 4.1585 | 3.6951 | 7.3339 | 3.439 | 13.6446 | 15.7214 | 23.575 | 27.014 | 0.01
12.9509 | 8.2894 | 2.2317 | 2.3475 | 1.8244 | 2.2947 | 8.7377 | 5.2671 | 21.2403 | 23.5878 | 32.3255 | 37.5927 | 12.9509 | 8.2894 | 2.2317 | 2.3575 | 1.8244 | 2.2947 | 8.7377 | 5.2671 | 21.2403 | 23.5978 | 32.3355 | 37.6027 | 0.01
-1.0534 | 9.506 | 1.7649 | 1.6473 | 4.1219 | 3.6732 | 5.2366 | 6.3902 | 8.4526 | 10.0999 | 17.895 | 24.2852 | -1.0534 | 9.506 | 1.7649 | 1.6573 | 4.1219 | 3.6732 | 5.2366 | 6.3902 | 8.4526 | 10.1099 | 17.905 | 24.2952 | 0.01
12.7317 | 6.4718 | 2.2244 | 2.3366 | 2.2937 | 2.5762 | 8.6829 | 3.5893 | 19.2034 | 21.54 | 30.2229 | 33.8122 | 12.7317 | 6.4718 | 2.2244 | 2.3466 | 2.2937 | 2.5762 | 8.6829 | 3.5893 | 19.2034 | 21.55 | 30.2329 | 33.8222 | 0.01
1.7625 | 9.4585 | 1.8587 | 1.7881 | 4.4139 | 3.8484 | 5.9406 | 6.3463 | 11.221 | 13.0091 | 21.2714 | 27.6177 | 1.7625 | 9.4585 | 1.8587 | 1.7981 | 4.4139 | 3.8484 | 5.9406 | 6.3463 | 11.221 | 13.0191 | 21.2814 | 27.6277 | 0.01
14.4836 | 7.0819 | 2.2828 | 2.4242 | 2.818 | 2.8908 | 9.1209 | 4.1525 | 21.5654 | 23.9896 | 33.1105 | 37.263 | 14.4836 | 7.0819 | 2.2828 | 2.4342 | 2.818 | 2.8908 | 9.1209 | 4.1525 | 21.5654 | 23.9996 | 33.1205 | 37.273 | 0.01
4.908 | 9.8381 | 1.9636 | 1.9454 | 4.2124 | 3.7275 | 6.727 | 6.6967 | 14.7461 | 16.6915 | 24.6314 | 31.3281 | 4.908 | 9.8381 | 1.9636 | 1.9554 | 4.2124 | 3.7275 | 6.727 | 6.6967 | 14.7461 | 16.7015 | 24.6414 | 31.3381 | 0.01
13.2747 | 7.7634 | 2.2425 | 2.3637 | 2.6176 | 2.7706 | 8.8187 | 4.7816 | 21.0381 | 23.4018 | 32.2205 | 37.0021 | 13.2747 | 7.7634 | 2.2425 | 2.3737 | 2.6176 | 2.7706 | 8.8187 | 4.7816 | 21.0381 | 23.4118 | 32.2305 | 37.0121 | 0.01
3.7058 | 9.5762 | 1.9235 | 1.8853 | 4.0942 | 3.6565 | 6.4265 | 6.4549 | 13.282 | 15.1673 | 22.9179 | 29.3729 | 3.7058 | 9.5762 | 1.9235 | 1.8953 | 4.0942 | 3.6565 | 6.4265 | 6.4549 | 13.282 | 15.1773 | 22.9279 | 29.3829 | 0.01
12.5649 | 7.5029 | 2.2188 | 2.3282 | 2.7136 | 2.8282 | 8.6412 | 4.5412 | 20.0678 | 22.3961 | 31.0373 | 35.5785 | 12.5649 | 7.5029 | 2.2188 | 2.3382 | 2.7136 | 2.8282 | 8.6412 | 4.5412 | 20.0678 | 22.4061 | 31.0473 | 35.5885 | 0.01
4.2816 | 9.4224 | 1.9427 | 1.9141 | 1.5496 | 2.1298 | 6.5704 | 6.313 | 13.704 | 15.618 | 22.1884 | 28.5014 | 4.2816 | 9.4224 | 1.9427 | 1.9241 | 1.5496 | 2.1298 | 6.5704 | 6.313 | 13.704 | 15.628 | 22.1984 | 28.5114 | 0.01
-2.7021 | 7.6277 | 1.7099 | 1.5649 | 4.8215 | 4.0929 | 4.8245 | 4.6563 | 4.9255 | 6.4904 | 15.4048 | 20.0611 | -2.7021 | 7.6277 | 1.7099 | 1.5749 | 4.8215 | 4.0929 | 4.8245 | 4.6563 | 4.9255 | 6.5004 | 15.4148 | 20.0711 | 0.01
16.9289 | 6.1145 | 2.3643 | 2.5464 | 1.5666 | 2.14 | 9.7322 | 3.2596 | 23.0434 | 25.5899 | 35.3221 | 38.5817 | 16.9289 | 6.1145 | 2.3643 | 2.5564 | 1.5666 | 2.14 | 9.7322 | 3.2596 | 23.0434 | 25.5999 | 35.3321 | 38.5917 | 0.01
-2.6001 | 10.3679 | 1.7133 | 1.57 | 2.43 | 2.658 | 4.85 | 7.1858 | 7.7678 | 9.3378 | 14.4258 | 21.6116 | -2.6001 | 10.3679 | 1.7133 | 1.58 | 2.43 | 2.658 | 4.85 | 7.1858 | 7.7678 | 9.3478 | 14.4358 | 21.6216 | 0.01
2.5801 | 6.1366 | 1.886 | 1.829 | 0.74844 | 1.6491 | 6.145 | 3.28 | 8.7168 | 10.5458 | 16.6908 | 19.9708 | 2.5801 | 6.1366 | 1.886 | 1.839 | 0.74844 | 1.6491 | 6.145 | 3.28 | 8.7168 | 10.5558 | 16.7008 | 19.9808 | 0.01
-7.5094 | 7.259 | 1.5497 | 1.3245 | 3.3043 | 3.1826 | 3.6227 | 4.316 | -0.25035 | 1.0742 | 7.5611 | 11.8771 | -7.5094 | 7.259 | 1.5497 | 1.3345 | 3.3043 | 3.1826 | 3.6227 | 4.316 | -0.25035 | 1.0842 | 7.5711 | 11.8871 | 0.01
7.826 | 5.073 | 2.0609 | 2.0913 | 0.096747 | 1.258 | 7.4565 | 2.2981 | 12.899 | 14.9903 | 22.4468 | 24.7449 | 7.826 | 5.073 | 2.0609 | 2.1013 | 0.096747 | 1.258 | 7.4565 | 2.2981 | 12.899 | 15.0003 | 22.4568 | 24.7549 | 0.01
-11.4195 | 8.3956 | 1.4193 | 1.129 | 1.1507 | 1.8904 | 2.6451 | 5.3652 | -3.0239 | -1.8949 | 1.1462 | 6.5114 | -11.4195 | 8.3956 | 1.4193 | 1.139 | 1.1507 | 1.8904 | 2.6451 | 5.3652 | -3.0239 | -1.8849 | 1.1562 | 6.5214 | 0.01
-5.0961 | 4.2258 | 1.6301 | 1.4452 | 2.318 | 2.5908 | 4.226 | 1.5161 | -0.87032 | 0.57488 | 5.4837 | 6.9998 | -5.0961 | 4.2258 | 1.6301 | 1.4552 | 2.318 | 2.5908 | 4.226 | 1.5161 | -0.87032 | 0.58488 | 5.4937 | 7.0098 | 0.01
1.9081 | 5.5958 | 1.8636 | 1.7954 | 3.9068 | 3.5441 | 5.977 | 2.7808 | 7.5039 | 9.2993 | 16.7502 | 19.531 | 1.9081 | 5.5958 | 1.8636 | 1.8054 | 3.9068 | 3.5441 | 5.977 | 2.7808 | 7.5039 | 9.3093 | 16.7602 | 19.541 | 0.01
11.4408 | 7.1134 | 2.1814 | 2.272 | 3.9987 | 3.5992 | 8.3602 | 4.1816 | 18.5542 | 20.8263 | 29.1865 | 33.3681 | 11.4408 | 7.1134 | 2.1814 | 2.282 | 3.9987 | 3.5992 | 8.3602 | 4.1816 | 18.5542 | 20.8363 | 29.1965 | 33.3781 | 0.01
11.9924 | 9.1788 | 2.1997 | 2.2996 | 2.5211 | 2.7127 | 8.4981 | 6.0882 | 21.1712 | 23.4708 | 31.9689 | 38.0571 | 11.9924 | 9.1788 | 2.1997 | 2.3096 | 2.5211 | 2.7127 | 8.4981 | 6.0882 | 21.1712 | 23.4808 | 31.9789 | 38.0671 | 0.01
3.1269 | 9.2983 | 1.9042 | 1.8563 | 2.6077 | 2.7646 | 6.2817 | 6.1985 | 12.4252 | 14.2815 | 20.5633 | 26.7617 | 3.1269 | 9.2983 | 1.9042 | 1.8663 | 2.6077 | 2.7646 | 6.2817 | 6.1985 | 12.4252 | 14.2915 | 20.5733 | 26.7717 | 0.01
3.646 | 7.3775 | 1.9215 | 1.8823 | 3.8705 | 3.5223 | 6.4115 | 4.4254 | 11.0234 | 12.9057 | 20.2986 | 24.724 | 3.646 | 7.3775 | 1.9215 | 1.8923 | 3.8705 | 3.5223 | 6.4115 | 4.4254 | 11.0234 | 12.9157 | 20.3086 | 24.734 | 0.01
11.2232 | 7.49 | 2.1741 | 2.2612 | 4.6272 | 3.9763 | 8.3058 | 4.5292 | 18.7131 | 20.9743 | 29.5778 | 34.107 | 11.2232 | 7.49 | 2.1741 | 2.2712 | 4.6272 | 3.9763 | 8.3058 | 4.5292 | 18.7131 | 20.9843 | 29.5878 | 34.117 | 0.01
15.7633 | 9.1317 | 2.3254 | 2.4882 | 3.3338 | 3.2003 | 9.4408 | 6.0446 | 24.895 | 27.3831 | 36.8239 | 42.8686 | 15.7633 | 9.1317 | 2.3254 | 2.4982 | 3.3338 | 3.2003 | 9.4408 | 6.0446 | 24.895 | 27.3931 | 36.8339 | 42.8786 | 0.01
8.0029 | 10.1154 | 2.0668 | 2.1001 | 4.3526 | 3.8116 | 7.5007 | 6.9527 | 18.1183 | 20.2185 | 28.3827 | 35.3354 | 8.0029 | 10.1154 | 2.0668 | 2.1101 | 4.3526 | 3.8116 | 7.5007 | 6.9527 | 18.1183 | 20.2285 | 28.3927 | 35.3454 | 0.01
14.1159 | 8.434 | 2.2705 | 2.4058 | 3.1711 | 3.1026 | 9.029 | 5.4006 | 22.5498 | 24.9556 | 33.9846 | 39.3852 | 14.1159 | 8.434 | 2.2705 | 2.4158 | 3.1711 | 3.1026 | 9.029 | 5.4006 | 22.5498 | 24.9656 | 33.9946 | 39.3952 | 0.01
7.0265 | 9.7584 | 2.0342 | 2.0513 | 1.0701 | 1.842 | 7.2566 | 6.6232 | 16.7849 | 18.8362 | 26.0929 | 32.716 | 7.0265 | 9.7584 | 2.0342 | 2.0613 | 1.0701 | 1.842 | 7.2566 | 6.6232 | 16.7849 | 18.8462 | 26.1029 | 32.726 | 0.01
-5.5795 | 8.2224 | 1.614 | 1.421 | 3.1699 | 3.1019 | 4.1051 | 5.2053 | 2.6429 | 4.0639 | 10.3358 | 15.5411 | -5.5795 | 8.2224 | 1.614 | 1.431 | 3.1699 | 3.1019 | 4.1051 | 5.2053 | 2.6429 | 4.0739 | 10.3458 | 15.5511 | 0.01
7.0195 | 5.4911 | 2.034 | 2.051 | 2.44 | 2.664 | 7.2549 | 2.6841 | 12.5106 | 14.5615 | 21.8164 | 24.5005 | 7.0195 | 5.4911 | 2.034 | 2.061 | 2.44 | 2.664 | 7.2549 | 2.6841 | 12.5106 | 14.5715 | 21.8264 | 24.5105 | 0.01
2.6398 | 8.2209 | 1.888 | 1.832 | 3.9164 | 3.5498 | 6.1599 | 5.2039 | 10.8607 | 12.6926 | 20.1589 | 25.3627 | 2.6398 | 8.2209 | 1.888 | 1.842 | 3.9164 | 3.5498 | 6.1599 | 5.2039 | 10.8607 | 12.7026 | 20.1689 | 25.3727 | 0.01
11.4983 | 7.272 | 2.1833 | 2.2749 | 2.2667 | 2.56 | 8.3746 | 4.328 | 18.7703 | 21.0452 | 29.4197 | 33.7477 | 11.4983 | 7.272 | 2.1833 | 2.2849 | 2.2667 | 2.56 | 8.3746 | 4.328 | 18.7703 | 21.0552 | 29.4297 | 33.7577 | 0.01
1.6003 | 9.1913 | 1.8533 | 1.78 | 0.78163 | 1.669 | 5.9001 | 6.0997 | 10.7916 | 12.5716 | 18.4716 | 24.5713 | 1.6003 | 9.1913 | 1.8533 | 1.79 | 0.78163 | 1.669 | 5.9001 | 6.0997 | 10.7916 | 12.5816 | 18.4816 | 24.5813 | 0.01
-7.3102 | 7.0467 | 1.5563 | 1.3345 | 4.619 | 3.9714 | 3.6724 | 4.1201 | -0.26348 | 1.071 | 9.6614 | 13.7815 | -7.3102 | 7.0467 | 1.5563 | 1.3445 | 4.619 | 3.9714 | 3.6724 | 4.1201 | -0.26348 | 1.081 | 9.6714 | 13.7915 | 0.01
15.714 | 5.1161 | 2.3238 | 2.4857 | 4.1687 | 3.7012 | 9.4285 | 2.338 | 20.8301 | 23.3158 | 32.7443 | 35.0823 | 15.714 | 5.1161 | 2.3238 | 2.4957 | 4.1687 | 3.7012 | 9.4285 | 2.338 | 20.8301 | 23.3258 | 32.7543 | 35.0923 | 0.01
13.0123 | 10.1047 | 2.2337 | 2.3506 | 0.93932 | 1.7636 | 8.7531 | 6.9428 | 23.117 | 25.4677 | 34.2207 | 41.1635 | 13.0123 | 10.1047 | 2.2337 | 2.3606 | 0.93932 | 1.7636 | 8.7531 | 6.9428 | 23.117 | 25.4777 | 34.2307 | 41.1735 | 0.01
-6.3641 | 9.5193 | 1.5879 | 1.3818 | 3.1006 | 3.0604 | 3.909 | 6.4025 | 3.1553 | 4.5371 | 10.698 | 17.1005 | -6.3641 | 9.5193 | 1.5879 | 1.3918 | 3.1006 | 3.0604 | 3.909 | 6.4025 | 3.1553 | 4.5471 | 10.708 | 17.1105 | 0.01
6.6035 | 5.3211 | 2.0201 | 2.0302 | 3.8656 | 3.5194 | 7.1509 | 2.5272 | 11.9246 | 13.9548 | 21.3398 | 23.867 | 6.6035 | 5.3211 | 2.0201 | 2.0402 | 3.8656 | 3.5194 | 7.1509 | 2.5272 | 11.9246 | 13.9648 | 21.3498 | 23.877 | 0.01
11.1936 | 8.1308 | 2.1731 | 2.2597 | 2.3992 | 2.6395 | 8.2984 | 5.1207 | 19.3244 | 21.584 | 29.8824 | 35.0031 | 11.1936 | 8.1308 | 2.1731 | 2.2697 | 2.3992 | 2.6395 | 8.2984 | 5.1207 | 19.3244 | 21.594 | 29.8924 | 35.0131 | 0.01
2.3952 | 9.1253 | 1.8798 | 1.8198 | 4.4598 | 3.8759 | 6.0988 | 6.0387 | 11.5205 | 13.3403 | 21.6759 | 27.7146 | 2.3952 | 9.1253 | 1.8798 | 1.8298 | 4.4598 | 3.8759 | 6.0988 | 6.0387 | 11.5205 | 13.3503 | 21.6859 | 27.7246 | 0.01
14.7587 | 7.219 | 2.292 | 2.4379 | 4.6718 | 4.0031 | 9.1897 | 4.279 | 21.9776 | 24.4156 | 33.6053 | 37.8843 | 14.7587 | 7.219 | 2.292 | 2.4479 | 4.6718 | 4.0031 | 9.1897 | 4.279 | 21.9776 | 24.4256 | 33.6153 | 37.8943 | 0.01
16.0308 | 9.8977 | 2.3344 | 2.5015 | 2.5827 | 2.7496 | 9.5077 | 6.7517 | 25.9285 | 28.4301 | 37.9378 | 44.6895 | 16.0308 | 9.8977 | 2.3344 | 2.5115 | 2.5827 | 2.7496 | 9.5077 | 6.7517 | 25.9285 | 28.4401 | 37.9478 | 44.6995 | 0.01
3.496 | 10.1733 | 1.9165 | 1.8748 | 2.8107 | 2.8864 | 6.374 | 7.0062 | 13.6693 | 15.5441 | 21.9181 | 28.9243 | 3.496 | 10.1733 | 1.9165 | 1.8848 | 2.8107 | 2.8864 | 6.374 | 7.0062 | 13.6693 | 15.5541 | 21.9281 | 28.9343 | 0.01
4.8644 | 7.4575 | 1.9621 | 1.9432 | 4.7599 | 4.0559 | 6.7161 | 4.4992 | 12.3218 | 14.265 | 23.0809 | 27.5801 | 4.8644 | 7.4575 | 1.9621 | 1.9532 | 4.7599 | 4.0559 | 6.7161 | 4.4992 | 12.3218 | 14.275 | 23.0909 | 27.5901 | 0.01
16.5595 | 7.7539 | 2.352 | 2.528 | 5.0114 | 4.2069 | 9.6399 | 4.7729 | 24.3134 | 26.8414 | 36.4813 | 41.2541 | 16.5595 | 7.7539 | 2.352 | 2.538 | 5.0114 | 4.2069 | 9.6399 | 4.7729 | 24.3134 | 26.8514 | 36.4913 | 41.2641 | 0.01
18.0686 | 10.2879 | 2.4023 | 2.6034 | 4.3153 | 3.7892 | 10.0172 | 7.1119 | 28.3565 | 30.9599 | 40.9771 | 48.089 | 18.0686 | 10.2879 | 2.4023 | 2.6134 | 4.3153 | 3.7892 | 10.0172 | 7.1119 | 28.3565 | 30.9699 | 40.9871 | 48.099 | 0.01
13.8917 | 10.6149 | 2.2631 | 2.3946 | 3.384 | 3.2304 | 8.9729 | 7.4137 | 24.5065 | 26.9011 | 35.874 | 43.2878 | 13.8917 | 10.6149 | 2.2631 | 2.4046 | 3.384 | 3.2304 | 8.9729 | 7.4137 | 24.5065 | 26.9111 | 35.884 | 43.2978 | 0.01
8.3042 | 9.7099 | 2.0768 | 2.1152 | 2.9744 | 2.9846 | 7.576 | 6.5783 | 18.014 | 20.1292 | 27.7053 | 34.2836 | 8.3042 | 9.7099 | 2.0768 | 2.1252 | 2.9744 | 2.9846 | 7.576 | 6.5783 | 18.014 | 20.1392 | 27.7153 | 34.2936 | 0.01
5.8464 | 8.4992 | 1.9949 | 1.9923 | 4.3016 | 3.781 | 6.9616 | 5.4608 | 14.3457 | 16.338 | 24.4206 | 29.8814 | 5.8464 | 8.4992 | 1.9949 | 2.0023 | 4.3016 | 3.781 | 6.9616 | 5.4608 | 14.3457 | 16.348 | 24.4306 | 29.8914 | 0.01
13.8097 | 7.9667 | 2.2603 | 2.3905 | 3.6323 | 3.3794 | 8.9524 | 4.9693 | 21.7765 | 24.1669 | 33.1194 | 38.0887 | 13.8097 | 7.9667 | 2.2603 | 2.4005 | 3.6323 | 3.3794 | 8.9524 | 4.9693 | 21.7765 | 24.1769 | 33.1294 | 38.0987 | 0.01
9.7938 | 9.6921 | 2.1265 | 2.1897 | 3.7296 | 3.4377 | 7.9485 | 6.5619 | 19.4859 | 21.6756 | 29.6241 | 36.186 | 9.7938 | 9.6921 | 2.1265 | 2.1997 | 3.7296 | 3.4377 | 7.9485 | 6.5619 | 19.4859 | 21.6856 | 29.6341 | 36.196 | 0.01
10.3775 | 8.822 | 2.1459 | 2.2189 | 4.6453 | 3.9872 | 8.0944 | 5.7588 | 19.1995 | 21.4184 | 30.0509 | 35.8096 | 10.3775 | 8.822 | 2.1459 | 2.2289 | 4.6453 | 3.9872 | 8.0944 | 5.7588 | 19.1995 | 21.4284 | 30.0609 | 35.8196 | 0.01
15.8718 | 8.9485 | 2.3291 | 2.4936 | 2.8253 | 2.8952 | 9.468 | 5.8755 | 24.8203 | 27.3139 | 36.7818 | 42.6573 | 15.8718 | 8.9485 | 2.3291 | 2.5036 | 2.8253 | 2.8952 | 9.468 | 5.8755 | 24.8203 | 27.3239 | 36.7918 | 42.6673 | 0.01
4.9521 | 10.1389 | 1.9651 | 1.9476 | 2.6385 | 2.7831 | 6.738 | 6.9744 | 15.091 | 17.0386 | 23.7766 | 30.751 | 4.9521 | 10.1389 | 1.9651 | 1.9576 | 2.6385 | 2.7831 | 6.738 | 6.9744 | 15.091 | 17.0486 | 23.7866 | 30.761 | 0.01
3.8311 | 7.7729 | 1.9277 | 1.8916 | 2.9743 | 2.9846 | 6.4578 | 4.7904 | 11.604 | 13.4956 | 19.9533 | 24.7438 | 3.8311 | 7.7729 | 1.9277 | 1.9016 | 2.9743 | 2.9846 | 6.4578 | 4.7904 | 11.604 | 13.5056 | 19.9633 | 24.7538 | 0.01
5.8458 | 7.5301 | 1.9949 | 1.9923 | 1.9744 | 2.3846 | 6.9614 | 4.5662 | 13.3758 | 15.3681 | 22.3296 | 26.8958 | 5.8458 | 7.5301 | 1.9949 | 2.0023 | 1.9744 | 2.3846 | 6.9614 | 4.5662 | 13.3758 | 15.3781 | 22.3396 | 26.9058 | 0.01
-0.15369 | 7.9666 | 1.7949 | 1.6923 | 3.4835 | 3.2901 | 5.4616 | 4.9692 | 7.8129 | 9.5052 | 16.2788 | 21.248 | -0.15369 | 7.9666 | 1.7949 | 1.7023 | 3.4835 | 3.2901 | 5.4616 | 4.9692 | 7.8129 | 9.5152 | 16.2888 | 21.258 | 0.01
8.9011 | 6.6667 | 2.0967 | 2.1451 | 2.8402 | 2.9041 | 7.7253 | 3.7693 | 15.5678 | 17.7128 | 25.4381 | 29.2073 | 8.9011 | 6.6667 | 2.0967 | 2.1551 | 2.8402 | 2.9041 | 7.7253 | 3.7693 | 15.5678 | 17.7228 | 25.4481 | 29.2173 | 0.01
5.0411 | 8.6286 | 1.968 | 1.9521 | 2.9244 | 2.9547 | 6.7603 | 5.5802 | 13.6697 | 15.6217 | 22.382 | 27.9622 | 5.0411 | 8.6286 | 1.968 | 1.9621 | 2.9244 | 2.9547 | 6.7603 | 5.5802 | 13.6697 | 15.6317 | 22.392 | 27.9722 | 0.01
5.5467 | 7.7922 | 1.9849 | 1.9773 | 2.7834 | 2.87 | 6.8867 | 4.8082 | 13.3389 | 15.3163 | 22.2029 | 27.0112 | 5.5467 | 7.7922 | 1.9849 | 1.9873 | 2.7834 | 2.87 | 6.8867 | 4.8082 | 13.3389 | 15.3263 | 22.2129 | 27.0212 | 0.01
4.7002 | 7.9018 | 1.9567 | 1.935 | 2.2444 | 2.5466 | 6.675 | 4.9093 | 12.602 | 14.537 | 21.212 | 26.1214 | 4.7002 | 7.9018 | 1.9567 | 1.945 | 2.2444 | 2.5466 | 6.675 | 4.9093 | 12.602 | 14.547 | 21.222 | 26.1314 | 0.01
1.4663 | 7.7184 | 1.8489 | 1.7733 | 3.148 | 3.0888 | 5.8666 | 4.74 | 9.1847 | 10.958 | 17.1947 | 21.9348 | 1.4663 | 7.7184 | 1.8489 | 1.7833 | 3.148 | 3.0888 | 5.8666 | 4.74 | 9.1847 | 10.968 | 17.2047 | 21.9448 | 0.01
6.8879 | 7.0177 | 2.0296 | 2.0444 | 1.6145 | 2.1687 | 7.222 | 4.0933 | 13.9056 | 15.95 | 23.1719 | 27.2652 | 6.8879 | 7.0177 | 2.0296 | 2.0544 | 1.6145 | 2.1687 | 7.222 | 4.0933 | 13.9056 | 15.96 | 23.1819 | 27.2752 | 0.01
-2.3129 | 8.1924 | 1.7229 | 1.5844 | 2.1422 | 2.4853 | 4.9218 | 5.1776 | 5.8795 | 7.4639 | 12.3856 | 17.5632 | -2.3129 | 8.1924 | 1.7229 | 1.5944 | 2.1422 | 2.4853 | 4.9218 | 5.1776 | 5.8795 | 7.4739 | 12.3956 | 17.5732 | 0.01
0.85301 | 6.1989 | 1.8284 | 1.7427 | 3.3938 | 3.2363 | 5.7133 | 3.3374 | 7.0519 | 8.7945 | 15.4247 | 18.7621 | 0.85301 | 6.1989 | 1.8284 | 1.7527 | 3.3938 | 3.2363 | 5.7133 | 3.3374 | 7.0519 | 8.8045 | 15.4347 | 18.7721 | 0.01
8.363 | 6.8848 | 2.0788 | 2.1181 | 2.8631 | 2.9179 | 7.5907 | 3.9706 | 15.2478 | 17.366 | 24.9567 | 28.9273 | 8.363 | 6.8848 | 2.0788 | 2.1281 | 2.8631 | 2.9179 | 7.5907 | 3.9706 | 15.2478 | 17.376 | 24.9667 | 28.9373 | 0.01
5.1786 | 8.512 | 1.9726 | 1.9589 | 2.7811 | 2.8686 | 6.7946 | 5.4726 | 13.6906 | 15.6495 | 22.4441 | 27.9167 | 5.1786 | 8.512 | 1.9726 | 1.9689 | 2.7811 | 2.8686 | 6.7946 | 5.4726 | 13.6906 | 15.6595 | 22.4541 | 27.9267 | 0.01
4.6863 | 7.822 | 1.9562 | 1.9343 | 1.7183 | 2.231 | 6.6716 | 4.8357 | 12.5083 | 14.4427 | 21.1142 | 25.95 | 4.6863 | 7.822 | 1.9562 | 1.9443 | 1.7183 | 2.231 | 6.6716 | 4.8357 | 12.5083 | 14.4527 | 21.1242 | 25.96 | 0.01
-1.69 | 7.7154 | 1.7437 | 1.6155 | 2.6544 | 2.7926 | 5.0775 | 4.7373 | 6.0254 | 7.6409 | 13.0879 | 17.8252 | -1.69 | 7.7154 | 1.7437 | 1.6255 | 2.6544 | 2.7926 | 5.0775 | 4.7373 | 6.0254 | 7.6509 | 13.0979 | 17.8352 | 0.01
3.9263 | 6.3338 | 1.9309 | 1.8963 | 2.8467 | 2.908 | 6.4816 | 3.462 | 10.2601 | 12.1564 | 18.638 | 22.1 | 3.9263 | 6.3338 | 1.9309 | 1.9063 | 2.8467 | 2.908 | 6.4816 | 3.462 | 10.2601 | 12.1664 | 18.648 | 22.11 | 0.01
5.0801 | 7.5507 | 1.9693 | 1.954 | 2.9045 | 2.9427 | 6.77 | 4.5853 | 12.6307 | 14.5847 | 21.3548 | 25.94 | 5.0801 | 7.5507 | 1.9693 | 1.964 | 2.9045 | 2.9427 | 6.77 | 4.5853 | 12.6307 | 14.5947 | 21.3648 | 25.95 | 0.01
5.4268 | 7.8007 | 1.9809 | 1.9713 | 4.1252 | 3.6751 | 6.8567 | 4.816 | 13.2274 | 15.1988 | 22.9991 | 27.8151 | 5.4268 | 7.8007 | 1.9809 | 1.9813 | 4.1252 | 3.6751 | 6.8567 | 4.816 | 13.2274 | 15.2088 | 23.0091 | 27.8251 | 0.01
12.7511 | 7.8758 | 2.225 | 2.3376 | 3.8581 | 3.5149 | 8.6878 | 4.8854 | 20.6269 | 22.9645 | 31.6522 | 36.5376 | 12.7511 | 7.8758 | 2.225 | 2.3476 | 3.8581 | 3.5149 | 8.6878 | 4.8854 | 20.6269 | 22.9745 | 31.6622 | 36.5476 | 0.01
11.1487 | 9.4627 | 2.1716 | 2.2574 | 3.4723 | 3.2834 | 8.2872 | 6.3502 | 20.6114 | 22.8689 | 31.1561 | 37.5063 | 11.1487 | 9.4627 | 2.1716 | 2.2674 | 3.4723 | 3.2834 | 8.2872 | 6.3502 | 20.6114 | 22.8789 | 31.1661 | 37.5163 | 0.01
8.834 | 9.1156 | 2.0945 | 2.1417 | 3.2206 | 3.1323 | 7.7085 | 6.0297 | 17.9496 | 20.0913 | 27.7998 | 33.8295 | 8.834 | 9.1156 | 2.0945 | 2.1517 | 3.2206 | 3.1323 | 7.7085 | 6.0297 | 17.9496 | 20.1013 | 27.8098 | 33.8395 | 0.01
7.3235 | 8.614 | 2.0441 | 2.0662 | 3.2162 | 3.1297 | 7.3309 | 5.5668 | 15.9375 | 18.0037 | 25.3346 | 30.9014 | 7.3235 | 8.614 | 2.0441 | 2.0762 | 3.2162 | 3.1297 | 7.3309 | 5.5668 | 15.9375 | 18.0137 | 25.3446 | 30.9114 | 0.01
7.2969 | 8.2868 | 2.0432 | 2.0648 | 3.2464 | 3.1478 | 7.3242 | 5.2647 | 15.5837 | 17.6485 | 24.9727 | 30.2374 | 7.2969 | 8.2868 | 2.0432 | 2.0748 | 3.2464 | 3.1478 | 7.3242 | 5.2647 | 15.5837 | 17.6585 | 24.9827 | 30.2474 | 0.01
7.4785 | 8.281 | 2.0493 | 2.0739 | 1.9766 | 2.386 | 7.3696 | 5.2594 | 15.7595 | 17.8334 | 25.203 | 30.4624 | 7.4785 | 8.281 | 2.0493 | 2.0839 | 1.9766 | 2.386 | 7.3696 | 5.2594 | 15.7595 | 17.8434 | 25.213 | 30.4724 | 0.01
-0.14037 | 8.3203 | 1.7953 | 1.693 | 2.9701 | 2.9821 | 5.4649 | 5.2957 | 8.18 | 9.873 | 15.8251 | 21.1208 | -0.14037 | 8.3203 | 1.7953 | 1.703 | 2.9701 | 2.9821 | 5.4649 | 5.2957 | 8.18 | 9.883 | 15.8351 | 21.1308 | 0.01
5.8206 | 6.6696 | 1.994 | 1.991 | 1.6681 | 2.2008 | 6.9552 | 3.7719 | 12.4902 | 14.4813 | 21.4364 | 25.2083 | 5.8206 | 6.6696 | 1.994 | 2.001 | 1.6681 | 2.2008 | 6.9552 | 3.7719 | 12.4902 | 14.4913 | 21.4464 | 25.2183 | 0.01
-1.9916 | 7.9611 | 1.7336 | 1.6004 | 4.1051 | 3.6631 | 5.0021 | 4.9641 | 5.9696 | 7.57 | 15.3382 | 20.3023 | -1.9916 | 7.9611 | 1.7336 | 1.6104 | 4.1051 | 3.6631 | 5.0021 | 4.9641 | 5.9696 | 7.58 | 15.3482 | 20.3123 | 0.01
12.6307 | 6.2685 | 2.221 | 2.3315 | 3.1409 | 3.0845 | 8.6577 | 3.4017 | 18.8992 | 21.2308 | 29.8884 | 33.2901 | 12.6307 | 6.2685 | 2.221 | 2.3415 | 3.1409 | 3.0845 | 8.6577 | 3.4017 | 18.8992 | 21.2408 | 29.8984 | 33.3001 | 0.01
6.8453 | 9.4367 | 2.0282 | 2.0423 | 1.4547 | 2.0728 | 7.2113 | 6.3261 | 16.282 | 18.3243 | 25.5356 | 31.8617 | 6.8453 | 9.4367 | 2.0282 | 2.0523 | 1.4547 | 2.0728 | 7.2113 | 6.3261 | 16.282 | 18.3343 | 25.5456 | 31.8717 | 0.01
-3.272 | 8.1832 | 1.6909 | 1.5364 | 2.8971 | 2.9383 | 4.682 | 5.1691 | 4.9112 | 6.4476 | 12.283 | 17.452 | -3.272 | 8.1832 | 1.6909 | 1.5464 | 2.8971 | 2.9383 | 4.682 | 5.1691 | 4.9112 | 6.4576 | 12.293 | 17.462 | 0.01
5.3827 | 5.9911 | 1.9794 | 1.9691 | 4.3756 | 3.8253 | 6.8457 | 3.1456 | 11.3738 | 13.3429 | 21.5439 | 24.6895 | 5.3827 | 5.9911 | 1.9794 | 1.9791 | 4.3756 | 3.8253 | 6.8457 | 3.1456 | 11.3738 | 13.3529 | 21.5539 | 24.6995 | 0.01
14.2535 | 7.8663 | 2.2751 | 2.4127 | 2.174 | 2.5044 | 9.0634 | 4.8765 | 22.1197 | 24.5324 | 33.5958 | 38.4723 | 14.2535 | 7.8663 | 2.2751 | 2.4227 | 2.174 | 2.5044 | 9.0634 | 4.8765 | 22.1197 | 24.5424 | 33.6058 | 38.4823 | 0.01
1.0437 | 9.7882 | 1.8348 | 1.7522 | 2.1204 | 2.4722 | 5.7609 | 6.6507 | 10.832 | 12.5842 | 18.3451 | 24.9958 | 1.0437 | 9.7882 | 1.8348 | 1.7622 | 2.1204 | 2.4722 | 5.7609 | 6.6507 | 10.832 | 12.5942 | 18.3551 | 25.0058 | 0.01
0.72232 | 6.9261 | 1.8241 | 1.7361 | 3.0018 | 3.0011 | 5.6806 | 4.0087 | 7.6485 | 9.3846 | 15.3874 | 19.3962 | 0.72232 | 6.9261 | 1.8241 | 1.7461 | 3.0018 | 3.0011 | 5.6806 | 4.0087 | 7.6485 | 9.3946 | 15.3974 | 19.4062 | 0.01
6.0106 | 6.8565 | 2.0004 | 2.0005 | 2.5764 | 2.7458 | 7.0026 | 3.9445 | 12.8671 | 14.8676 | 21.8703 | 25.8147 | 6.0106 | 6.8565 | 2.0004 | 2.0105 | 2.5764 | 2.7458 | 7.0026 | 3.9445 | 12.8671 | 14.8776 | 21.8803 | 25.8247 | 0.01
3.4584 | 8.0023 | 1.9153 | 1.8729 | 0.37298 | 1.4238 | 6.3646 | 5.0021 | 11.4607 | 13.3337 | 19.6983 | 24.7004 | 3.4584 | 8.0023 | 1.9153 | 1.8829 | 0.37298 | 1.4238 | 6.3646 | 5.0021 | 11.4607 | 13.3437 | 19.7083 | 24.7104 | 0.01
-9.7621 | 7.4493 | 1.4746 | 1.2119 | 2.7077 | 2.8246 | 3.0595 | 4.4917 | -2.3128 | -1.1009 | 4.4314 | 8.9231 | -9.7621 | 7.4493 | 1.4746 | 1.2219 | 2.7077 | 2.8246 | 3.0595 | 4.4917 | -2.3128 | -1.0909 | 4.4414 | 8.9331 | 0.01
4.2463 | 4.5849 | 1.9415 | 1.9123 | 2.3095 | 2.5857 | 6.5616 | 1.8476 | 8.8311 | 10.7435 | 17.305 | 19.1526 | 4.2463 | 4.5849 | 1.9415 | 1.9223 | 2.3095 | 2.5857 | 6.5616 | 1.8476 | 8.8311 | 10.7535 | 17.315 | 19.1626 | 0.01
1.8569 | 7.62 | 1.8619 | 1.7928 | 3.3009 | 3.1806 | 5.9642 | 4.6493 | 9.4769 | 11.2698 | 17.7513 | 22.4005 | 1.8569 | 7.62 | 1.8619 | 1.8028 | 3.3009 | 3.1806 | 5.9642 | 4.6493 | 9.4769 | 11.2798 | 17.7613 | 22.4105 | 0.01
7.8055 | 7.1023 | 2.0602 | 2.0903 | 1.9738 | 2.3843 | 7.4514 | 4.1714 | 14.9079 | 16.9981 | 24.4495 | 28.6209 | 7.8055 | 7.1023 | 2.0602 | 2.1003 | 1.9738 | 2.3843 | 7.4514 | 4.1714 | 14.9079 | 17.0081 | 24.4595 | 28.6309 | 0.01
-0.15737 | 8.3912 | 1.7948 | 1.6921 | 2.3419 | 2.6052 | 5.4607 | 5.3611 | 8.2338 | 9.926 | 15.3866 | 20.7477 | -0.15737 | 8.3912 | 1.7948 | 1.7021 | 2.3419 | 2.6052 | 5.4607 | 5.3611 | 8.2338 | 9.936 | 15.3966 | 20.7577 | 0.01
2.0516 | 6.6659 | 1.8684 | 1.8026 | 4.6939 | 4.0163 | 6.0129 | 3.7685 | 8.7175 | 10.5201 | 19.2303 | 22.9989 | 2.0516 | 6.6659 | 1.8684 | 1.8126 | 4.6939 | 4.0163 | 6.0129 | 3.7685 | 8.7175 | 10.5301 | 19.2403 | 23.0089 | 0.01
16.1634 | 7.1445 | 2.3388 | 2.5082 | 2.4881 | 2.6928 | 9.5409 | 4.2103 | 23.308 | 25.8161 | 35.357 | 39.5673 | 16.1634 | 7.1445 | 2.3388 | 2.5182 | 2.4881 | 2.6928 | 9.5409 | 4.2103 | 23.308 | 25.8261 | 35.367 | 39.5773 | 0.01
2.9283 | 10.2021 | 1.8976 | 1.8464 | 1.8229 | 2.2937 | 6.2321 | 7.0327 | 13.1304 | 14.9768 | 21.2089 | 28.2416 | 2.9283 | 10.2021 | 1.8976 | 1.8564 | 1.8229 | 2.2937 | 6.2321 | 7.0327 | 13.1304 | 14.9868 | 21.2189 | 28.2516 | 0.01
-1.0626 | 7.3345 | 1.7646 | 1.6469 | 3.6826 | 3.4096 | 5.2344 | 4.3857 | 6.2719 | 7.9188 | 15.0109 | 19.3966 | -1.0626 | 7.3345 | 1.7646 | 1.6569 | 3.6826 | 3.4096 | 5.2344 | 4.3857 | 6.2719 | 7.9288 | 15.0209 | 19.4066 | 0.01
10.0956 | 6.4698 | 2.1365 | 2.2048 | 2.7751 | 2.865 | 8.0239 | 3.5875 | 16.5653 | 18.7701 | 26.794 | 30.3815 | 10.0956 | 6.4698 | 2.1365 | 2.2148 | 2.7751 | 2.865 | 8.0239 | 3.5875 | 16.5653 | 18.7801 | 26.804 | 30.3915 | 0.01
4.6504 | 8.8874 | 1.955 | 1.9325 | 4.5711 | 3.9427 | 6.6626 | 5.8191 | 13.5378 | 15.4703 | 23.9841 | 29.8032 | 4.6504 | 8.8874 | 1.955 | 1.9425 | 4.5711 | 3.9427 | 6.6626 | 5.8191 | 13.5378 | 15.4803 | 23.9941 | 29.8132 | 0.01
15.4267 | 7.7076 | 2.3142 | 2.4713 | 4.305 | 3.783 | 9.3567 | 4.7301 | 23.1343 | 25.6057 | 34.9624 | 39.6924 | 15.4267 | 7.7076 | 2.3142 | 2.4813 | 4.305 | 3.783 | 9.3567 | 4.7301 | 23.1343 | 25.6157 | 34.9724 | 39.7024 | 0.01
13.8297 | 10.0425 | 2.261 | 2.3915 | 2.4924 | 2.6954 | 8.9574 | 6.8853 | 23.8722 | 26.2637 | 35.2211 | 42.1065 | 13.8297 | 10.0425 | 2.261 | 2.4015 | 2.4924 | 2.6954 | 8.9574 | 6.8853 | 23.8722 | 26.2737 | 35.2311 | 42.1165 | 0.01
2.9545 | 9.6964 | 1.8985 | 1.8477 | 3.7825 | 3.4695 | 6.2386 | 6.5659 | 12.6509 | 14.4986 | 21.7506 | 28.3166 | 2.9545 | 9.6964 | 1.8985 | 1.8577 | 3.7825 | 3.4695 | 6.2386 | 6.5659 | 12.6509 | 14.5086 | 21.7606 | 28.3266 | 0.01
10.6949 | 7.3401 | 2.1565 | 2.2347 | 2.8622 | 2.9173 | 8.1737 | 4.3909 | 18.035 | 20.2698 | 28.4435 | 32.8344 | 10.6949 | 7.3401 | 2.1565 | 2.2447 | 2.8622 | 2.9173 | 8.1737 | 4.3909 | 18.035 | 20.2798 | 28.4535 | 32.8444 | 0.01
5.1733 | 9.0172 | 1.9724 | 1.9587 | 3.1984 | 3.119 | 6.7933 | 5.939 | 14.1905 | 16.1492 | 22.9425 | 28.8815 | 5.1733 | 9.0172 | 1.9724 | 1.9687 | 3.1984 | 3.119 | 6.7933 | 5.939 | 14.1905 | 16.1592 | 22.9525 | 28.8915 | 0.01
7.1904 | 7.8209 | 2.0397 | 2.0595 | 1.3371 | 2.0022 | 7.2976 | 4.8347 | 15.0112 | 17.0708 | 24.3683 | 29.203 | 7.1904 | 7.8209 | 2.0397 | 2.0695 | 1.3371 | 2.0022 | 7.2976 | 4.8347 | 15.0112 | 17.0808 | 24.3783 | 29.213 | 0.01
-3.9776 | 8.2579 | 1.6674 | 1.5011 | 2.9624 | 2.9775 | 4.5056 | 5.2381 | 4.2803 | 5.7815 | 11.7213 | 16.9594 | -3.9776 | 8.2579 | 1.6674 | 1.5111 | 2.9624 | 2.9775 | 4.5056 | 5.2381 | 4.2803 | 5.7915 | 11.7313 | 16.9694 | 0.01
5.7745 | 5.8382 | 1.9925 | 1.9887 | 3.2345 | 3.1407 | 6.9436 | 3.0045 | 11.6127 | 13.6015 | 20.5451 | 23.5496 | 5.7745 | 5.8382 | 1.9925 | 1.9987 | 3.2345 | 3.1407 | 6.9436 | 3.0045 | 11.6127 | 13.6115 | 20.5551 | 23.5596 | 0.01
7.4073 | 7.9511 | 2.0469 | 2.0704 | 3.9585 | 3.5751 | 7.3518 | 4.9549 | 15.3584 | 17.4288 | 24.9625 | 29.9174 | 7.4073 | 7.9511 | 2.0469 | 2.0804 | 3.9585 | 3.5751 | 7.3518 | 4.9549 | 15.3584 | 17.4388 | 24.9725 | 29.9274 | 0.01
11.7513 | 8.3049 | 2.1917 | 2.2876 | 2.7908 | 2.8745 | 8.4378 | 5.2815 | 20.0562 | 22.3438 | 30.7816 | 36.063 | 11.7513 | 8.3049 | 2.1917 | 2.2976 | 2.7908 | 2.8745 | 8.4378 | 5.2815 | 20.0562 | 22.3538 | 30.7916 | 36.073 | 0.01
4.7449 | 9.2461 | 1.9582 | 1.9372 | 1.7315 | 2.2389 | 6.6862 | 6.1503 | 13.991 | 15.9283 | 22.6145 | 28.7648 | 4.7449 | 9.2461 | 1.9582 | 1.9472 | 1.7315 | 2.2389 | 6.6862 | 6.1503 | 13.991 | 15.9383 | 22.6245 | 28.7748 | 0.01
-1.6111 | 7.7281 | 1.7463 | 1.6194 | 2.8944 | 2.9366 | 5.0972 | 4.749 | 6.1169 | 7.7364 | 13.5674 | 18.3163 | -1.6111 | 7.7281 | 1.7463 | 1.6294 | 2.8944 | 2.9366 | 5.0972 | 4.749 | 6.1169 | 7.7464 | 13.5774 | 18.3263 | 0.01
5.3662 | 6.3509 | 1.9789 | 1.9683 | 3.0773 | 3.0464 | 6.8415 | 3.4778 | 11.7171 | 13.6854 | 20.527 | 24.0047 | 5.3662 | 6.3509 | 1.9789 | 1.9783 | 3.0773 | 3.0464 | 6.8415 | 3.4778 | 11.7171 | 13.6954 | 20.537 | 24.0147 | 0.01
6.4638 | 7.8627 | 2.0155 | 2.0232 | 2.5815 | 2.7489 | 7.116 | 4.8732 | 14.3265 | 16.3497 | 23.4657 | 28.3389 | 6.4638 | 7.8627 | 2.0155 | 2.0332 | 2.5815 | 2.7489 | 7.116 | 4.8732 | 14.3265 | 16.3597 | 23.4757 | 28.3489 | 0.01
3.4889 | 8.1005 | 1.9163 | 1.8744 | 1.8665 | 2.3199 | 6.3722 | 5.0928 | 11.5894 | 13.4638 | 19.836 | 24.9288 | 3.4889 | 8.1005 | 1.9163 | 1.8844 | 1.8665 | 2.3199 | 6.3722 | 5.0928 | 11.5894 | 13.4738 | 19.846 | 24.9388 | 0.01
-0.80079 | 7.4559 | 1.7733 | 1.66 | 4.0774 | 3.6465 | 5.2998 | 4.4978 | 6.6551 | 8.3151 | 16.039 | 20.5368 | -0.80079 | 7.4559 | 1.7733 | 1.67 | 4.0774 | 3.6465 | 5.2998 | 4.4978 | 6.6551 | 8.3251 | 16.049 | 20.5468 | 0.01
12.4646 | 6.5265 | 2.2155 | 2.3232 | 2.1699 | 2.5019 | 8.6161 | 3.6398 | 18.9911 | 21.3143 | 29.9305 | 33.5703 | 12.4646 | 6.5265 | 2.2155 | 2.3332 | 2.1699 | 2.5019 | 8.6161 | 3.6398 | 18.9911 | 21.3243 | 29.9405 | 33.5803 | 0.01
1.0194 | 9.4007 | 1.834 | 1.751 | 4.2351 | 3.7411 | 5.7549 | 6.2929 | 10.4201 | 12.1711 | 20.1472 | 26.4401 | 1.0194 | 9.4007 | 1.834 | 1.761 | 4.2351 | 3.7411 | 5.7549 | 6.2929 | 10.4201 | 12.1811 | 20.1572 | 26.4501 | 0.01
13.4105 | 6.9209 | 2.247 | 2.3705 | 1.9519 | 2.3711 | 8.8526 | 4.0039 | 20.3314 | 22.7019 | 31.5546 | 35.5585 | 13.4105 | 6.9209 | 2.247 | 2.3805 | 1.9519 | 2.3711 | 8.8526 | 4.0039 | 20.3314 | 22.7119 | 31.5646 | 35.5685 | 0.01
-0.28881 | 9.6056 | 1.7904 | 1.6856 | 2.9194 | 2.9516 | 5.4278 | 6.4821 | 9.3168 | 11.0024 | 16.8734 | 23.3555 | -0.28881 | 9.6056 | 1.7904 | 1.6956 | 2.9194 | 2.9516 | 5.4278 | 6.4821 | 9.3168 | 11.0124 | 16.8834 | 23.3655 | 0.01
5.5165 | 6.6374 | 1.9839 | 1.9758 | 3.7465 | 3.4479 | 6.8791 | 3.7422 | 12.1539 | 14.1297 | 21.3241 | 25.0664 | 5.5165 | 6.6374 | 1.9839 | 1.9858 | 3.7465 | 3.4479 | 6.8791 | 3.7422 | 12.1539 | 14.1397 | 21.3341 | 25.0764 | 0.01
10.479 | 7.8952 | 2.1493 | 2.2239 | 2.4963 | 2.6978 | 8.1197 | 4.9033 | 18.3742 | 20.5982 | 28.7179 | 33.6212 | 10.479 | 7.8952 | 2.1493 | 2.2339 | 2.4963 | 2.6978 | 8.1197 | 4.9033 | 18.3742 | 20.6082 | 28.7279 | 33.6312 | 0.01
2.978 | 8.9704 | 1.8993 | 1.8489 | 4.1729 | 3.7037 | 6.2445 | 5.8958 | 11.9484 | 13.7973 | 21.6739 | 27.5697 | 2.978 | 8.9704 | 1.8993 | 1.8589 | 4.1729 | 3.7037 | 6.2445 | 5.8958 | 11.9484 | 13.8073 | 21.6839 | 27.5797 | 0.01
13.0371 | 7.3452 | 2.2346 | 2.3519 | 5.043 | 4.2258 | 8.7593 | 4.3956 | 20.3823 | 22.7342 | 32.0031 | 36.3986 | 13.0371 | 7.3452 | 2.2346 | 2.3619 | 5.043 | 4.2258 | 8.7593 | 4.3956 | 20.3823 | 22.7442 | 32.0131 | 36.4086 | 0.01
18.2582 | 9.5247 | 2.4086 | 2.6129 | 1.3136 | 1.9881 | 10.0646 | 6.4074 | 27.7829 | 30.3958 | 40.4604 | 46.8678 | 18.2582 | 9.5247 | 2.4086 | 2.6229 | 1.3136 | 1.9881 | 10.0646 | 6.4074 | 27.7829 | 30.4058 | 40.4704 | 46.8778 | 0.01
-4.1186 | 10.6559 | 1.6627 | 1.4941 | 3.5481 | 3.3289 | 4.4704 | 7.4516 | 6.5374 | 8.0314 | 14.9084 | 22.36 | -4.1186 | 10.6559 | 1.6627 | 1.5041 | 3.5481 | 3.3289 | 4.4704 | 7.4516 | 6.5374 | 8.0414 | 14.9184 | 22.37 | 0.01
9.2885 | 5.8076 | 2.1096 | 2.1644 | 2.9226 | 2.9536 | 7.8221 | 2.9763 | 15.0962 | 17.2606 | 25.0828 | 28.059 | 9.2885 | 5.8076 | 2.1096 | 2.1744 | 2.9226 | 2.9536 | 7.8221 | 2.9763 | 15.0962 | 17.2706 | 25.0928 | 28.069 | 0.01
5.5355 | 8.7125 | 1.9845 | 1.9768 | 5.2821 | 4.3692 | 6.8839 | 5.6577 | 14.2481 | 16.2248 | 25.8761 | 31.5339 | 5.5355 | 8.7125 | 1.9845 | 1.9868 | 5.2821 | 4.3692 | 6.8839 | 5.6577 | 14.2481 | 16.2348 | 25.8861 | 31.5439 | 0.01
19.6924 | 7.8994 | 2.4564 | 2.6846 | 1.3027 | 1.9816 | 10.4231 | 4.9071 | 27.5918 | 30.2764 | 40.6995 | 45.6066 | 19.6924 | 7.8994 | 2.4564 | 2.6946 | 1.3027 | 1.9816 | 10.4231 | 4.9071 | 27.5918 | 30.2864 | 40.7095 | 45.6166 | 0.01
-4.1837 | 10.9667 | 1.6605 | 1.4908 | 2.4833 | 2.69 | 4.4541 | 7.7385 | 6.7829 | 8.2738 | 13.447 | 21.1855 | -4.1837 | 10.9667 | 1.6605 | 1.5008 | 2.4833 | 2.69 | 4.4541 | 7.7385 | 6.7829 | 8.2838 | 13.457 | 21.1955 | 0.01
2.8996 | 5.7935 | 1.8967 | 1.845 | 4.6737 | 4.0042 | 6.2249 | 2.9633 | 8.6931 | 10.5381 | 19.216 | 22.1792 | 2.8996 | 5.7935 | 1.8967 | 1.855 | 4.6737 | 4.0042 | 6.2249 | 2.9633 | 8.6931 | 10.5481 | 19.226 | 22.1892 | 0.01
16.0422 | 7.3282 | 2.3347 | 2.5021 | 2.969 | 2.9814 | 9.5106 | 4.3799 | 23.3705 | 25.8726 | 35.3831 | 39.7631 | 16.0422 | 7.3282 | 2.3347 | 2.5121 | 2.969 | 2.9814 | 9.5106 | 4.3799 | 23.3705 | 25.8826 | 35.3931 | 39.7731 | 0.01
5.8138 | 10.1758 | 1.9938 | 1.9907 | 2.7846 | 2.8708 | 6.9534 | 7.0084 | 15.9896 | 17.9803 | 24.9337 | 31.9422 | 5.8138 | 10.1758 | 1.9938 | 2.0007 | 2.7846 | 2.8708 | 6.9534 | 7.0084 | 15.9896 | 17.9903 | 24.9437 | 31.9522 | 0.01
4.7076 | 7.9596 | 1.9569 | 1.9354 | 2.5954 | 2.7572 | 6.6769 | 4.9628 | 12.6673 | 14.6026 | 21.2795 | 26.2423 | 4.7076 | 7.9596 | 1.9569 | 1.9454 | 2.5954 | 2.7572 | 6.6769 | 4.9628 | 12.6673 | 14.6126 | 21.2895 | 26.2523 | 0.01
3.5724 | 7.72 | 1.9191 | 1.8786 | 4.397 | 3.8382 | 6.3931 | 4.7415 | 11.2924 | 13.171 | 21.4063 | 26.1478 | 3.5724 | 7.72 | 1.9191 | 1.8886 | 4.397 | 3.8382 | 6.3931 | 4.7415 | 11.2924 | 13.181 | 21.4163 | 26.1578 | 0.01
14.3822 | 7.474 | 2.2794 | 2.4191 | 2.2841 | 2.5705 | 9.0955 | 4.5145 | 21.8562 | 24.2753 | 33.3709 | 37.8854 | 14.3822 | 7.474 | 2.2794 | 2.4291 | 2.2841 | 2.5705 | 9.0955 | 4.5145 | 21.8562 | 24.2853 | 33.3809 | 37.8954 | 0.01
1.7047 | 9.8161 | 1.8568 | 1.7852 | 3.83 | 3.498 | 5.9262 | 6.6764 | 11.5209 | 13.3061 | 20.6341 | 27.3105 | 1.7047 | 9.8161 | 1.8568 | 1.7952 | 3.83 | 3.498 | 5.9262 | 6.6764 | 11.5209 | 13.3161 | 20.6441 | 27.3205 | 0.01
10.98 | 7.0694 | 2.166 | 2.249 | 3.431 | 3.2586 | 8.245 | 4.1409 | 18.0494 | 20.2984 | 28.5434 | 32.6843 | 10.98 | 7.0694 | 2.166 | 2.259 | 3.431 | 3.2586 | 8.245 | 4.1409 | 18.0494 | 20.3084 | 28.5534 | 32.6943 | 0.01
8.5858 | 9.079 | 2.0862 | 2.1293 | 2.0667 | 2.44 | 7.6465 | 5.996 | 17.6648 | 19.7941 | 27.4406 | 33.4366 | 8.5858 | 9.079 | 2.0862 | 2.1393 | 2.0667 | 2.44 | 7.6465 | 5.996 | 17.6648 | 19.8041 | 27.4506 | 33.4466 | 0.01
0.40007 | 8.5603 | 1.8133 | 1.72 | 3.5941 | 3.3565 | 5.6 | 5.5172 | 8.9603 | 10.6803 | 17.6309 | 23.1481 | 0.40007 | 8.5603 | 1.8133 | 1.73 | 3.5941 | 3.3565 | 5.6 | 5.5172 | 8.9603 | 10.6903 | 17.6409 | 23.1581 | 0.01
9.5647 | 6.7867 | 2.1188 | 2.1782 | 3.2553 | 3.1532 | 7.8912 | 3.88 | 16.3514 | 18.5296 | 26.4208 | 30.3008 | 9.5647 | 6.7867 | 2.1188 | 2.1882 | 3.2553 | 3.1532 | 7.8912 | 3.88 | 16.3514 | 18.5396 | 26.4308 | 30.3108 | 0.01
7.5316 | 8.7723 | 2.0511 | 2.0766 | 3.3519 | 3.2111 | 7.3829 | 5.7129 | 16.3039 | 18.3805 | 25.7634 | 31.4763 | 7.5316 | 8.7723 | 2.0511 | 2.0866 | 3.3519 | 3.2111 | 7.3829 | 5.7129 | 16.3039 | 18.3905 | 25.7734 | 31.4863 | 0.01
8.1115 | 8.3318 | 2.0704 | 2.1056 | 2.3366 | 2.602 | 7.5279 | 5.3063 | 16.4433 | 18.5489 | 26.0767 | 31.3831 | 8.1115 | 8.3318 | 2.0704 | 2.1156 | 2.3366 | 2.602 | 7.5279 | 5.3063 | 16.4433 | 18.5589 | 26.0867 | 31.3931 | 0.01
2.0197 | 8.4575 | 1.8673 | 1.801 | 2.4549 | 2.6729 | 6.0049 | 5.4223 | 10.4772 | 12.2782 | 18.2831 | 23.7054 | 2.0197 | 8.4575 | 1.8673 | 1.811 | 2.4549 | 2.6729 | 6.0049 | 5.4223 | 10.4772 | 12.2882 | 18.2931 | 23.7154 | 0.01
2.7292 | 7.1376 | 1.891 | 1.8365 | 3.3007 | 3.1804 | 6.1823 | 4.2039 | 9.8668 | 11.7033 | 18.1844 | 22.3883 | 2.7292 | 7.1376 | 1.891 | 1.8465 | 3.3007 | 3.1804 | 6.1823 | 4.2039 | 9.8668 | 11.7133 | 18.1944 | 22.3983 | 0.01
7.8041 | 7.2913 | 2.0601 | 2.0902 | 3.2421 | 3.1452 | 7.451 | 4.3458 | 15.0954 | 17.1856 | 24.6366 | 28.9825 | 7.8041 | 7.2913 | 2.0601 | 2.1002 | 3.2421 | 3.1452 | 7.451 | 4.3458 | 15.0954 | 17.1956 | 24.6466 | 28.9925 | 0.01
7.4524 | 8.3909 | 2.0484 | 2.0726 | 3.8806 | 3.5284 | 7.3631 | 5.3608 | 15.8432 | 17.9159 | 25.3248 | 30.6856 | 7.4524 | 8.3909 | 2.0484 | 2.0826 | 3.8806 | 3.5284 | 7.3631 | 5.3608 | 15.8432 | 17.9259 | 25.3348 | 30.6956 | 0.01
11.2836 | 8.3147 | 2.1761 | 2.2642 | 5.2907 | 4.3744 | 8.3209 | 5.2905 | 19.5983 | 21.8625 | 31.5276 | 36.8181 | 11.2836 | 8.3147 | 2.1761 | 2.2742 | 5.2907 | 4.3744 | 8.3209 | 5.2905 | 19.5983 | 21.8725 | 31.5376 | 36.8281 | 0.01
19.7442 | 9.1448 | 2.4581 | 2.6872 | 2.4446 | 2.6667 | 10.4361 | 6.0567 | 28.889 | 31.5762 | 42.0123 | 48.069 | 19.7442 | 9.1448 | 2.4581 | 2.6972 | 2.4446 | 2.6667 | 10.4361 | 6.0567 | 28.889 | 31.5862 | 42.0223 | 48.079 | 0.01
2.6675 | 10.9779 | 1.8889 | 1.8334 | 2.5403 | 2.7242 | 6.1669 | 7.7488 | 13.6454 | 15.4788 | 21.6456 | 29.3945 | 2.6675 | 10.9779 | 1.8889 | 1.8434 | 2.5403 | 2.7242 | 6.1669 | 7.7488 | 13.6454 | 15.4888 | 21.6556 | 29.4045 | 0.01
3.2415 | 7.278 | 1.9081 | 1.8621 | 1.9326 | 2.3596 | 6.3104 | 4.3335 | 10.5195 | 12.3816 | 18.692 | 23.0255 | 3.2415 | 7.278 | 1.9081 | 1.8721 | 1.9326 | 2.3596 | 6.3104 | 4.3335 | 10.5195 | 12.3916 | 18.702 | 23.0355 | 0.01
-0.40435 | 7.4023 | 1.7865 | 1.6798 | 3.4463 | 3.2678 | 5.3989 | 4.4483 | 6.998 | 8.6778 | 15.3919 | 19.8402 | -0.40435 | 7.4023 | 1.7865 | 1.6898 | 3.4463 | 3.2678 | 5.3989 | 4.4483 | 6.998 | 8.6878 | 15.4019 | 19.8502 | 0.01
1

## test activity E
A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | diff
-12.9745 | 3.8889 | 1.3675 | 1.0513 | -0.16242 | 1.1025 | 2.2564 | 1.2051 | -9.0857 | -8.0344 | -5.778 | -4.5729 | -12.9745 | 3.8889 | 1.3675 | 1.0513 | -0.15242 | 1.1025 | 2.2564 | 1.2051 | -9.0857 | -8.0344 | -5.778 | -4.5729 | 0
-0.12216 | 6.6735 | 1.7959 | 1.6939 | 1.9796 | 2.3878 | 5.4695 | 3.7756 | 6.5514 | 8.2453 | 13.7147 | 17.4903 | -0.12216 | 6.6735 | 1.7959 | 1.6939 | 1.9896 | 2.3878 | 5.4695 | 3.7756 | 6.5514 | 8.2453 | 13.7147 | 17.4903 | 0
6.9139 | 8.198 | 2.0305 | 2.0457 | 3.1523 | 3.0914 | 7.2285 | 5.1828 | 15.1119 | 17.1576 | 24.3861 | 29.5689 | 6.9139 | 8.198 | 2.0305 | 2.0457 | 3.1623 | 3.0914 | 7.2285 | 5.1828 | 15.1119 | 17.1576 | 24.3861 | 29.5689 | 0
12.6187 | 9.4341 | 2.2206 | 2.3309 | 4.1031 | 3.6619 | 8.6547 | 6.3237 | 22.0528 | 24.3837 | 33.0384 | 39.3622 | 12.6187 | 9.4341 | 2.2206 | 2.3309 | 4.1131 | 3.6619 | 8.6547 | 6.3237 | 22.0528 | 24.3837 | 33.0384 | 39.3622 | 0
2.4444 | 7.2296 | 1.8815 | 1.8222 | 2.4074 | 2.6444 | 6.1111 | 4.2889 | 9.674 | 11.4962 | 17.6073 | 21.8962 | 2.4444 | 7.2296 | 1.8815 | 1.8222 | 2.4174 | 2.6444 | 6.1111 | 4.2889 | 9.674 | 11.4962 | 17.6073 | 21.8962 | 0
13.5518 | 9.6362 | 2.2517 | 2.3776 | 4.2586 | 3.7552 | 8.888 | 6.5104 | 23.188 | 25.5656 | 34.4536 | 40.9639 | 13.5518 | 9.6362 | 2.2517 | 2.3776 | 4.2686 | 3.7552 | 8.888 | 6.5104 | 23.188 | 25.5656 | 34.4536 | 40.9639 | 0
9.2237 | 8.6985 | 2.1075 | 2.1612 | 3.5373 | 3.3224 | 7.8059 | 5.6447 | 17.9221 | 20.0833 | 27.8892 | 33.5339 | 9.2237 | 8.6985 | 2.1075 | 2.1612 | 3.5473 | 3.3224 | 7.8059 | 5.6447 | 17.9221 | 20.0833 | 27.8892 | 33.5339 | 0
13.2479 | 9.5704 | 2.2416 | 2.3624 | 4.208 | 3.7248 | 8.812 | 6.4496 | 22.8182 | 25.1806 | 33.9926 | 40.4422 | 13.2479 | 9.5704 | 2.2416 | 2.3624 | 4.218 | 3.7248 | 8.812 | 6.4496 | 22.8182 | 25.1806 | 33.9926 | 40.4422 | 0
14.8387 | 9.9151 | 2.2946 | 2.4419 | 4.4731 | 3.8839 | 9.2097 | 6.7677 | 24.7538 | 27.1957 | 36.4054 | 43.1731 | 14.8387 | 9.9151 | 2.2946 | 2.4419 | 4.4831 | 3.8839 | 9.2097 | 6.7677 | 24.7538 | 27.1957 | 36.4054 | 43.1731 | 0
5.5377 | 7.8998 | 1.9846 | 1.9769 | 2.9229 | 2.9538 | 6.8844 | 4.9075 | 13.4375 | 15.4144 | 22.2988 | 27.2063 | 5.5377 | 7.8998 | 1.9846 | 1.9769 | 2.9329 | 2.9538 | 6.8844 | 4.9075 | 13.4375 | 15.4144 | 22.2988 | 27.2063 | 0
3.6914 | 7.4998 | 1.923 | 1.8846 | 2.6152 | 2.7691 | 6.4229 | 4.5383 | 11.1913 | 13.0758 | 19.4987 | 24.037 | 3.6914 | 7.4998 | 1.923 | 1.8846 | 2.6252 | 2.7691 | 6.4229 | 4.5383 | 11.1913 | 13.0758 | 19.4987 | 24.037 | 0
15.412 | 10.0393 | 2.3137 | 2.4706 | 4.5687 | 3.9412 | 9.353 | 6.8824 | 25.4513 | 27.9219 | 37.2749 | 44.1573 | 15.412 | 10.0393 | 2.3137 | 2.4706 | 4.5787 | 3.9412 | 9.353 | 6.8824 | 25.4513 | 27.9219 | 37.2749 | 44.1573 | 0
-1.8093 | 6.308 | 1.7397 | 1.6095 | 1.6984 | 2.2191 | 5.0477 | 3.4381 | 4.4986 | 6.1082 | 11.1558 | 14.594 | -1.8093 | 6.308 | 1.7397 | 1.6095 | 1.7084 | 2.2191 | 5.0477 | 3.4381 | 4.4986 | 6.1082 | 11.1558 | 14.594 | 0
5.3552 | 7.8603 | 1.9785 | 1.9678 | 2.8925 | 2.9355 | 6.8388 | 4.871 | 13.2155 | 15.1833 | 22.0221 | 26.8931 | 5.3552 | 7.8603 | 1.9785 | 1.9678 | 2.9025 | 2.9355 | 6.8388 | 4.871 | 13.2155 | 15.1833 | 22.0221 | 26.8931 | 0
3.6258 | 7.4856 | 1.9209 | 1.8813 | 2.6043 | 2.7626 | 6.4065 | 4.5252 | 11.1114 | 12.9927 | 19.3991 | 23.9243 | 3.6258 | 7.4856 | 1.9209 | 1.8813 | 2.6143 | 2.7626 | 6.4065 | 4.5252 | 11.1114 | 12.9927 | 19.3991 | 23.9243 | 0
17.2865 | 10.4454 | 2.3762 | 2.5643 | 4.8811 | 4.1286 | 9.8216 | 7.2573 | 27.7319 | 30.2962 | 40.1178 | 47.3751 | 17.2865 | 10.4454 | 2.3762 | 2.5643 | 4.8911 | 4.1286 | 9.8216 | 7.2573 | 27.7319 | 30.2962 | 40.1178 | 47.3751 | 0
-1.2041 | 6.4391 | 1.7599 | 1.6398 | 1.7993 | 2.2796 | 5.199 | 3.5592 | 5.2351 | 6.8749 | 12.0738 | 15.633 | -1.2041 | 6.4391 | 1.7599 | 1.6398 | 1.8093 | 2.2796 | 5.199 | 3.5592 | 5.2351 | 6.8749 | 12.0738 | 15.633 | 0
10.4295 | 8.9597 | 2.1476 | 2.2215 | 3.7382 | 3.4429 | 8.1074 | 5.8859 | 19.3892 | 21.6107 | 29.7181 | 35.604 | 10.4295 | 8.9597 | 2.1476 | 2.2215 | 3.7482 | 3.4429 | 8.1074 | 5.8859 | 19.3892 | 21.6107 | 29.7181 | 35.604 | 0
3.5508 | 7.4693 | 1.9184 | 1.8775 | 2.5918 | 2.7551 | 6.3877 | 4.5102 | 11.0202 | 12.8977 | 19.2854 | 23.7956 | 3.5508 | 7.4693 | 1.9184 | 1.8775 | 2.6018 | 2.7551 | 6.3877 | 4.5102 | 11.0202 | 12.8977 | 19.2854 | 23.7956 | 0
8.8773 | 8.6234 | 2.0959 | 2.1439 | 3.4795 | 3.2877 | 7.7193 | 5.5755 | 17.5007 | 19.6445 | 27.3638 | 32.9393 | 8.8773 | 8.6234 | 2.0959 | 2.1439 | 3.4895 | 3.2877 | 7.7193 | 5.5755 | 17.5007 | 19.6445 | 27.3638 | 32.9393 | 0
10.0205 | 8.8711 | 2.134 | 2.201 | 3.6701 | 3.402 | 8.0051 | 5.8041 | 18.8916 | 21.0926 | 29.0977 | 34.9018 | 10.0205 | 8.8711 | 2.134 | 2.201 | 3.6801 | 3.402 | 8.0051 | 5.8041 | 18.8916 | 21.0926 | 29.0977 | 34.9018 | 0
8.7605 | 8.5981 | 2.092 | 2.138 | 3.4601 | 3.276 | 7.6901 | 5.5521 | 17.3586 | 19.4966 | 27.1867 | 32.7388 | 8.7605 | 8.5981 | 2.092 | 2.138 | 3.4701 | 3.276 | 7.6901 | 5.5521 | 17.3586 | 19.4966 | 27.1867 | 32.7388 | 0
13.6101 | 9.6489 | 2.2537 | 2.3805 | 4.2684 | 3.761 | 8.9025 | 6.522 | 23.259 | 25.6395 | 34.542 | 41.064 | 13.6101 | 9.6489 | 2.2537 | 2.3805 | 4.2784 | 3.761 | 8.9025 | 6.522 | 23.259 | 25.6395 | 34.542 | 41.064 | 0
-4.2589 | 5.7772 | 1.658 | 1.4871 | 1.2902 | 1.9741 | 4.4353 | 2.9482 | 1.5183 | 3.0053 | 7.4406 | 10.3888 | -4.2589 | 5.7772 | 1.658 | 1.4871 | 1.3002 | 1.9741 | 4.4353 | 2.9482 | 1.5183 | 3.0053 | 7.4406 | 10.3888 | 0
7.7808 | 8.3858 | 2.0594 | 2.089 | 3.2968 | 3.1781 | 7.4452 | 5.3562 | 16.1666 | 18.2557 | 25.7008 | 31.057 | 7.7808 | 8.3858 | 2.0594 | 2.089 | 3.3068 | 3.1781 | 7.4452 | 5.3562 | 16.1666 | 18.2557 | 25.7008 | 31.057 | 0
9.0241 | 8.6552 | 2.1008 | 2.1512 | 3.504 | 3.3024 | 7.756 | 5.6048 | 17.6794 | 19.8306 | 27.5866 | 33.1914 | 9.0241 | 8.6552 | 2.1008 | 2.1512 | 3.514 | 3.3024 | 7.756 | 5.6048 | 17.6794 | 19.8306 | 27.5866 | 33.1914 | 0
0.87462 | 6.8895 | 1.8292 | 1.7437 | 2.1458 | 2.4875 | 5.7187 | 3.9749 | 7.7641 | 9.5079 | 15.2265 | 19.2014 | 0.87462 | 6.8895 | 1.8292 | 1.7437 | 2.1558 | 2.4875 | 5.7187 | 3.9749 | 7.7641 | 9.5079 | 15.2265 | 19.2014 | 0
4.3537 | 7.6433 | 1.9451 | 1.9177 | 2.7256 | 2.8354 | 6.5884 | 4.6707 | 11.997 | 13.9147 | 20.5031 | 25.1739 | 4.3537 | 7.6433 | 1.9451 | 1.9177 | 2.7356 | 2.8354 | 6.5884 | 4.6707 | 11.997 | 13.9147 | 20.5031 | 25.1739 | 0
7.5191 | 8.3291 | 2.0506 | 2.076 | 3.2532 | 3.1519 | 7.3798 | 5.3038 | 15.8482 | 17.9242 | 25.3039 | 30.6078 | 7.5191 | 8.3291 | 2.0506 | 2.076 | 3.2632 | 3.1519 | 7.3798 | 5.3038 | 15.8482 | 17.9242 | 25.3039 | 30.6078 | 0
-1.0782 | 6.4664 | 1.7641 | 1.6461 | 1.8203 | 2.2922 | 5.2304 | 3.5844 | 5.3882 | 7.0343 | 12.2647 | 15.8491 | -1.0782 | 6.4664 | 1.7641 | 1.6461 | 1.8303 | 2.2922 | 5.2304 | 3.5844 | 5.3882 | 7.0343 | 12.2647 | 15.8491 | 0
-5.1061 | 5.5937 | 1.6298 | 1.4447 | 1.149 | 1.8894 | 4.2235 | 2.7788 | 0.48754 | 1.9322 | 6.1557 | 8.9345 | -5.1061 | 5.5937 | 1.6298 | 1.4447 | 1.159 | 1.8894 | 4.2235 | 2.7788 | 0.48754 | 1.9322 | 6.1557 | 8.9345 | 0
1.3629 | 6.9953 | 1.8454 | 1.7681 | 2.2271 | 2.5363 | 5.8407 | 4.0726 | 8.3582 | 10.1263 | 15.967 | 20.0396 | 1.3629 | 6.9953 | 1.8454 | 1.7681 | 2.2371 | 2.5363 | 5.8407 | 4.0726 | 8.3582 | 10.1263 | 15.967 | 20.0396 | 0
1.8639 | 7.1038 | 1.8621 | 1.7932 | 2.3106 | 2.5864 | 5.966 | 4.1728 | 8.9677 | 10.7609 | 16.7269 | 20.8996 | 1.8639 | 7.1038 | 1.8621 | 1.7932 | 2.3206 | 2.5864 | 5.966 | 4.1728 | 8.9677 | 10.7609 | 16.7269 | 20.8996 | 0
9.9802 | 8.8624 | 2.1327 | 2.199 | 3.6634 | 3.398 | 7.995 | 5.796 | 18.8426 | 21.0416 | 29.0366 | 34.8327 | 9.9802 | 8.8624 | 2.1327 | 2.199 | 3.6734 | 3.398 | 7.995 | 5.796 | 18.8426 | 21.0416 | 29.0366 | 34.8327 | 0
7.6476 | 8.357 | 2.0549 | 2.0824 | 3.2746 | 3.1648 | 7.4119 | 5.3295 | 16.0046 | 18.087 | 25.4989 | 30.8284 | 7.6476 | 8.357 | 2.0549 | 2.0824 | 3.2846 | 3.1648 | 7.4119 | 5.3295 | 16.0046 | 18.087 | 25.4989 | 30.8284 | 0
11.5709 | 9.207 | 2.1857 | 2.2785 | 3.9285 | 3.5571 | 8.3927 | 6.1142 | 20.778 | 23.0565 | 31.4492 | 37.5634 | 11.5709 | 9.207 | 2.1857 | 2.2785 | 3.9385 | 3.5571 | 8.3927 | 6.1142 | 20.778 | 23.0565 | 31.4492 | 37.5634 | 0
2.211 | 7.179 | 1.8737 | 1.8105 | 2.3685 | 2.6211 | 6.0527 | 4.2422 | 9.39 | 11.2006 | 17.2533 | 21.4955 | 2.211 | 7.179 | 1.8737 | 1.8105 | 2.3785 | 2.6211 | 6.0527 | 4.2422 | 9.39 | 11.2006 | 17.2533 | 21.4955 | 0
8.1676 | 8.4696 | 2.0723 | 2.1084 | 3.3613 | 3.2168 | 7.5419 | 5.4335 | 16.6372 | 18.7456 | 26.2875 | 31.721 | 8.1676 | 8.4696 | 2.0723 | 2.1084 | 3.3713 | 3.2168 | 7.5419 | 5.4335 | 16.6372 | 18.7456 | 26.2875 | 31.721 | 0
-1.5632 | 6.3613 | 1.7479 | 1.6218 | 1.7395 | 2.2437 | 5.1092 | 3.4874 | 4.7981 | 6.42 | 11.5292 | 15.0165 | -1.5632 | 6.3613 | 1.7479 | 1.6218 | 1.7495 | 2.2437 | 5.1092 | 3.4874 | 4.7981 | 6.42 | 11.5292 | 15.0165 | 0
6.51 | 8.1105 | 2.017 | 2.0255 | 3.085 | 3.051 | 7.1275 | 5.102 | 14.6205 | 16.646 | 23.7735 | 28.8754 | 6.51 | 8.1105 | 2.017 | 2.0255 | 3.095 | 3.051 | 7.1275 | 5.102 | 14.6205 | 16.646 | 23.7735 | 28.8754 | 0
9.2137 | 8.6963 | 2.1071 | 2.1607 | 3.5356 | 3.3214 | 7.8034 | 5.6427 | 17.91 | 20.0707 | 27.8741 | 33.5169 | 9.2137 | 8.6963 | 2.1071 | 2.1607 | 3.5456 | 3.3214 | 7.8034 | 5.6427 | 17.91 | 20.0707 | 27.8741 | 33.5169 | 0
2.0475 | 7.1436 | 1.8683 | 1.8024 | 2.3413 | 2.6048 | 6.0119 | 4.2095 | 9.1911 | 10.9935 | 17.0054 | 21.2149 | 2.0475 | 7.1436 | 1.8683 | 1.8024 | 2.3513 | 2.6048 | 6.0119 | 4.2095 | 9.1911 | 10.9935 | 17.0054 | 21.2149 | 0
2.251 | 7.1877 | 1.875 | 1.8125 | 2.3752 | 2.6251 | 6.0627 | 4.2502 | 9.4387 | 11.2513 | 17.314 | 21.5642 | 2.251 | 7.1877 | 1.875 | 1.8125 | 2.3852 | 2.6251 | 6.0627 | 4.2502 | 9.4387 | 11.2513 | 17.314 | 21.5642 | 0
3.4527 | 7.4481 | 1.9151 | 1.8726 | 2.5755 | 2.7453 | 6.3632 | 4.4905 | 10.9008 | 12.7734 | 19.1366 | 23.6272 | 3.4527 | 7.4481 | 1.9151 | 1.8726 | 2.5855 | 2.7453 | 6.3632 | 4.4905 | 10.9008 | 12.7734 | 19.1366 | 23.6272 | 0
-0.171 | 6.663 | 1.7943 | 1.6915 | 1.9715 | 2.3829 | 5.4573 | 3.7658 | 6.492 | 8.1834 | 13.6407 | 17.4065 | -0.171 | 6.663 | 1.7943 | 1.6915 | 1.9815 | 2.3829 | 5.4573 | 3.7658 | 6.492 | 8.1834 | 13.6407 | 17.4065 | 0
2.2975 | 7.1978 | 1.8766 | 1.8149 | 2.3829 | 2.6297 | 6.0744 | 4.2595 | 9.4953 | 11.3101 | 17.3845 | 21.644 | 2.2975 | 7.1978 | 1.8766 | 1.8149 | 2.3929 | 2.6297 | 6.0744 | 4.2595 | 9.4953 | 11.3101 | 17.3845 | 21.644 | 0
0.11826 | 6.7256 | 1.8039 | 1.7059 | 2.0197 | 2.4118 | 5.5296 | 3.8237 | 6.8439 | 8.5498 | 14.0794 | 17.903 | 0.11826 | 6.7256 | 1.8039 | 1.7059 | 2.0297 | 2.4118 | 5.5296 | 3.8237 | 6.8439 | 8.5498 | 14.0794 | 17.903 | 0
5.5591 | 7.9045 | 1.9853 | 1.978 | 2.9265 | 2.9559 | 6.8898 | 4.9118 | 13.4636 | 15.4416 | 22.3313 | 27.2432 | 5.5591 | 7.9045 | 1.9853 | 1.978 | 2.9365 | 2.9559 | 6.8898 | 4.9118 | 13.4636 | 15.4416 | 22.3313 | 27.2432 | 0
2.3412 | 7.2073 | 1.878 | 1.8171 | 2.3902 | 2.6341 | 6.0853 | 4.2682 | 9.5484 | 11.3655 | 17.4508 | 21.719 | 2.3412 | 7.2073 | 1.878 | 1.8171 | 2.4002 | 2.6341 | 6.0853 | 4.2682 | 9.5484 | 11.3655 | 17.4508 | 21.719 | 0
8.1691 | 8.47 | 2.0723 | 2.1085 | 3.3615 | 3.2169 | 7.5423 | 5.4338 | 16.639 | 18.7475 | 26.2897 | 31.7235 | 8.1691 | 8.47 | 2.0723 | 2.1085 | 3.3715 | 3.2169 | 7.5423 | 5.4338 | 16.639 | 18.7475 | 26.2897 | 31.7235 | 0
8.3035 | 8.4991 | 2.0768 | 2.1152 | 3.3839 | 3.2303 | 7.5759 | 5.4607 | 16.8026 | 18.9177 | 26.4936 | 31.9543 | 8.3035 | 8.4991 | 2.0768 | 2.1152 | 3.3939 | 3.2303 | 7.5759 | 5.4607 | 16.8026 | 18.9177 | 26.4936 | 31.9543 | 0
10.4961 | 8.9742 | 2.1499 | 2.2248 | 3.7493 | 3.4496 | 8.124 | 5.8992 | 19.4702 | 21.695 | 29.8191 | 35.7183 | 10.4961 | 8.9742 | 2.1499 | 2.2248 | 3.7593 | 3.4496 | 8.124 | 5.8992 | 19.4702 | 21.695 | 29.8191 | 35.7183 | 0
10.5815 | 8.9927 | 2.1527 | 2.2291 | 3.7636 | 3.4582 | 8.1454 | 5.9163 | 19.5742 | 21.8033 | 29.9486 | 35.8649 | 10.5815 | 8.9927 | 2.1527 | 2.2291 | 3.7736 | 3.4582 | 8.1454 | 5.9163 | 19.5742 | 21.8033 | 29.9486 | 35.8649 | 0
5.8599 | 7.9696 | 1.9953 | 1.993 | 2.9766 | 2.986 | 6.965 | 4.972 | 13.8295 | 15.8225 | 22.7875 | 27.7595 | 5.8599 | 7.9696 | 1.9953 | 1.993 | 2.9866 | 2.986 | 6.965 | 4.972 | 13.8295 | 15.8225 | 22.7875 | 27.7595 | 0
14.7012 | 9.8853 | 2.29 | 2.4351 | 4.4502 | 3.8701 | 9.1753 | 6.7402 | 24.5864 | 27.0215 | 36.1968 | 42.937 | 14.7012 | 9.8853 | 2.29 | 2.4351 | 4.4602 | 3.8701 | 9.1753 | 6.7402 | 24.5864 | 27.0215 | 36.1968 | 42.937 | 0
8.3236 | 8.5034 | 2.0775 | 2.1162 | 3.3873 | 3.2324 | 7.5809 | 5.4647 | 16.827 | 18.9432 | 26.5241 | 31.9888 | 8.3236 | 8.5034 | 2.0775 | 2.1162 | 3.3973 | 3.2324 | 7.5809 | 5.4647 | 16.827 | 18.9432 | 26.5241 | 31.9888 | 0
8.3401 | 8.507 | 2.078 | 2.117 | 3.39 | 3.234 | 7.585 | 5.468 | 16.8471 | 18.9641 | 26.5492 | 32.0172 | 8.3401 | 8.507 | 2.078 | 2.117 | 3.4 | 3.234 | 7.585 | 5.468 | 16.8471 | 18.9641 | 26.5492 | 32.0172 | 0
10.3472 | 8.9419 | 2.1449 | 2.2174 | 3.7245 | 3.4347 | 8.0868 | 5.8694 | 19.289 | 21.5064 | 29.5932 | 35.4626 | 10.3472 | 8.9419 | 2.1449 | 2.2174 | 3.7345 | 3.4347 | 8.0868 | 5.8694 | 19.289 | 21.5064 | 29.5932 | 35.4626 | 0
14.4633 | 9.8337 | 2.2821 | 2.4232 | 4.4105 | 3.8463 | 9.1158 | 6.6927 | 24.297 | 26.7201 | 35.836 | 42.5286 | 14.4633 | 9.8337 | 2.2821 | 2.4232 | 4.4205 | 3.8463 | 9.1158 | 6.6927 | 24.297 | 26.7201 | 35.836 | 42.5286 | 0
-3.5127 | 5.9389 | 1.6829 | 1.5244 | 1.4146 | 2.0487 | 4.6218 | 3.0975 | 2.4263 | 3.9506 | 8.5725 | 11.6699 | -3.5127 | 5.9389 | 1.6829 | 1.5244 | 1.4246 | 2.0487 | 4.6218 | 3.0975 | 2.4263 | 3.9506 | 8.5725 | 11.6699 | 0
5.4776 | 7.8868 | 1.9826 | 1.9739 | 2.9129 | 2.9478 | 6.8694 | 4.8955 | 13.3644 | 15.3383 | 22.2077 | 27.1032 | 5.4776 | 7.8868 | 1.9826 | 1.9739 | 2.9229 | 2.9478 | 6.8694 | 4.8955 | 13.3644 | 15.3383 | 22.2077 | 27.1032 | 0
5.2807 | 7.8442 | 1.976 | 1.964 | 2.8801 | 2.9281 | 6.8202 | 4.8561 | 13.1249 | 15.0889 | 21.9091 | 26.7653 | 5.2807 | 7.8442 | 1.976 | 1.964 | 2.8901 | 2.9281 | 6.8202 | 4.8561 | 13.1249 | 15.0889 | 21.9091 | 26.7653 | 0
7.9784 | 8.4286 | 2.0659 | 2.0989 | 3.3297 | 3.1978 | 7.4946 | 5.3957 | 16.407 | 18.5059 | 26.0005 | 31.3962 | 7.9784 | 8.4286 | 2.0659 | 2.0989 | 3.3397 | 3.1978 | 7.4946 | 5.3957 | 16.407 | 18.5059 | 26.0005 | 31.3962 | 0
13.8033 | 9.6907 | 2.2601 | 2.3902 | 4.3006 | 3.7803 | 8.9508 | 6.5607 | 23.494 | 25.8842 | 34.835 | 41.3957 | 13.8033 | 9.6907 | 2.2601 | 2.3902 | 4.3106 | 3.7803 | 8.9508 | 6.5607 | 23.494 | 25.8842 | 34.835 | 41.3957 | 0
8.5439 | 8.5512 | 2.0848 | 2.1272 | 3.424 | 3.2544 | 7.636 | 5.5088 | 17.0951 | 19.2223 | 26.8583 | 32.367 | 8.5439 | 8.5512 | 2.0848 | 2.1272 | 3.434 | 3.2544 | 7.636 | 5.5088 | 17.0951 | 19.2223 | 26.8583 | 32.367 | 0
4.4437 | 7.6628 | 1.9481 | 1.9222 | 2.7406 | 2.8444 | 6.6109 | 4.6887 | 12.1065 | 14.0287 | 20.6396 | 25.3283 | 4.4437 | 7.6628 | 1.9481 | 1.9222 | 2.7506 | 2.8444 | 6.6109 | 4.6887 | 12.1065 | 14.0287 | 20.6396 | 25.3283 | 0
7.7456 | 8.3782 | 2.0582 | 2.0873 | 3.2909 | 3.1746 | 7.4364 | 5.3491 | 16.1238 | 18.2111 | 25.6475 | 30.9967 | 7.7456 | 8.3782 | 2.0582 | 2.0873 | 3.3009 | 3.1746 | 7.4364 | 5.3491 | 16.1238 | 18.2111 | 25.6475 | 30.9967 | 0
-2.7103 | 6.1128 | 1.7097 | 1.5645 | 1.5483 | 2.129 | 4.8224 | 3.2579 | 3.4024 | 4.9669 | 9.7893 | 13.0473 | -2.7103 | 6.1128 | 1.7097 | 1.5645 | 1.5583 | 2.129 | 4.8224 | 3.2579 | 3.4024 | 4.9669 | 9.7893 | 13.0473 | 0
10.561 | 8.9882 | 2.152 | 2.2281 | 3.7602 | 3.4561 | 8.1403 | 5.9122 | 19.5493 | 21.7773 | 29.9176 | 35.8298 | 10.561 | 8.9882 | 2.152 | 2.2281 | 3.7702 | 3.4561 | 8.1403 | 5.9122 | 19.5493 | 21.7773 | 29.9176 | 35.8298 | 0
4.0867 | 7.5855 | 1.9362 | 1.9043 | 2.6811 | 2.8087 | 6.5217 | 4.6173 | 11.6721 | 13.5765 | 20.0982 | 24.7155 | 4.0867 | 7.5855 | 1.9362 | 1.9043 | 2.6911 | 2.8087 | 6.5217 | 4.6173 | 11.6721 | 13.5765 | 20.0982 | 24.7155 | 0
-2.8232 | 6.0883 | 1.7059 | 1.5588 | 1.5295 | 2.1177 | 4.7942 | 3.2354 | 3.2652 | 4.824 | 9.6182 | 12.8536 | -2.8232 | 6.0883 | 1.7059 | 1.5588 | 1.5395 | 2.1177 | 4.7942 | 3.2354 | 3.2652 | 4.824 | 9.6182 | 12.8536 | 0
4.6997 | 7.7183 | 1.9567 | 1.935 | 2.7833 | 2.87 | 6.6749 | 4.7399 | 12.418 | 14.353 | 21.0279 | 25.7678 | 4.6997 | 7.7183 | 1.9567 | 1.935 | 2.7933 | 2.87 | 6.6749 | 4.7399 | 12.418 | 14.353 | 21.0279 | 25.7678 | 0
9.2885 | 8.7125 | 2.1096 | 2.1644 | 3.5481 | 3.3288 | 7.8221 | 5.6577 | 18.0009 | 20.1654 | 27.9875 | 33.6452 | 9.2885 | 8.7125 | 2.1096 | 2.1644 | 3.5581 | 3.3288 | 7.8221 | 5.6577 | 18.0009 | 20.1654 | 27.9875 | 33.6452 | 0
4.1946 | 7.6088 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5486 | 4.6389 | 11.8034 | 13.7131 | 20.2618 | 24.9007 | 4.1946 | 7.6088 | 1.9398 | 1.9097 | 2.7091 | 2.8195 | 6.5486 | 4.6389 | 11.8034 | 13.7131 | 20.2618 | 24.9007 | 0
17.7331 | 10.5422 | 2.3911 | 2.5867 | 4.9555 | 4.1733 | 9.9333 | 7.3466 | 28.2753 | 30.862 | 40.7953 | 48.1419 | 17.7331 | 10.5422 | 2.3911 | 2.5867 | 4.9655 | 4.1733 | 9.9333 | 7.3466 | 28.2753 | 30.862 | 40.7953 | 48.1419 | 0
5.1638 | 7.8188 | 1.9721 | 1.9582 | 2.8606 | 2.9164 | 6.791 | 4.8328 | 12.9827 | 14.9409 | 21.7318 | 26.5646 | 5.1638 | 7.8188 | 1.9721 | 1.9582 | 2.8706 | 2.9164 | 6.791 | 4.8328 | 12.9827 | 14.9409 | 21.7318 | 26.5646 | 0
-1.7584 | 6.319 | 1.7414 | 1.6121 | 1.7069 | 2.2242 | 5.0604 | 3.4483 | 4.5607 | 6.1727 | 11.2331 | 14.6815 | -1.7584 | 6.319 | 1.7414 | 1.6121 | 1.7169 | 2.2242 | 5.0604 | 3.4483 | 4.5607 | 6.1727 | 11.2331 | 14.6815 | 0
-8.3468 | 4.8915 | 1.5218 | 1.2827 | 0.60887 | 1.5653 | 3.4133 | 2.1306 | -3.4553 | -2.1726 | 1.2407 | 3.3713 | -8.3468 | 4.8915 | 1.5218 | 1.2827 | 0.61887 | 1.5653 | 3.4133 | 2.1306 | -3.4553 | -2.1726 | 1.2407 | 3.3713 | 0
-0.18201 | 6.6606 | 1.7939 | 1.6909 | 1.9697 | 2.3818 | 5.4545 | 3.7636 | 6.4786 | 8.1695 | 13.624 | 17.3876 | -0.18201 | 6.6606 | 1.7939 | 1.6909 | 1.9797 | 2.3818 | 5.4545 | 3.7636 | 6.4786 | 8.1695 | 13.624 | 17.3876 | 0
-6.2667 | 5.3422 | 1.5911 | 1.3867 | 0.95556 | 1.7733 | 3.9333 | 2.5467 | -0.92444 | 0.46223 | 4.3956 | 6.9422 | -6.2667 | 5.3422 | 1.5911 | 1.3867 | 0.96556 | 1.7733 | 3.9333 | 2.5467 | -0.92444 | 0.46223 | 4.3956 | 6.9422 | 0
10.6683 | 9.0115 | 2.1556 | 2.2334 | 3.778 | 3.4668 | 8.1671 | 5.9337 | 19.6798 | 21.9132 | 30.0803 | 36.0139 | 10.6683 | 9.0115 | 2.1556 | 2.2334 | 3.788 | 3.4668 | 8.1671 | 5.9337 | 19.6798 | 21.9132 | 30.0803 | 36.0139 | 0
6.5503 | 8.1192 | 2.0183 | 2.0275 | 3.0917 | 3.055 | 7.1376 | 5.1101 | 14.6695 | 16.697 | 23.8346 | 28.9447 | 6.5503 | 8.1192 | 2.0183 | 2.0275 | 3.1017 | 3.055 | 7.1376 | 5.1101 | 14.6695 | 16.697 | 23.8346 | 28.9447 | 0
7.3155 | 8.285 | 2.0438 | 2.0658 | 3.2192 | 3.1315 | 7.3289 | 5.2631 | 15.6005 | 17.6663 | 24.9951 | 30.2582 | 7.3155 | 8.285 | 2.0438 | 2.0658 | 3.2292 | 3.1315 | 7.3289 | 5.2631 | 15.6005 | 17.6663 | 24.9951 | 30.2582 | 0
12.1047 | 9.3227 | 2.2035 | 2.3052 | 4.0174 | 3.6105 | 8.5262 | 6.2209 | 21.4274 | 23.7326 | 32.2588 | 38.4797 | 12.1047 | 9.3227 | 2.2035 | 2.3052 | 4.0274 | 3.6105 | 8.5262 | 6.2209 | 21.4274 | 23.7326 | 32.2588 | 38.4797 | 0
11.6009 | 9.2135 | 2.1867 | 2.28 | 3.9335 | 3.5601 | 8.4002 | 6.1202 | 20.8144 | 23.0944 | 31.4947 | 37.6148 | 11.6009 | 9.2135 | 2.1867 | 2.28 | 3.9435 | 3.5601 | 8.4002 | 6.1202 | 20.8144 | 23.0944 | 31.4947 | 37.6148 | 0
16.131 | 10.195 | 2.3377 | 2.5065 | 4.6885 | 4.0131 | 9.5327 | 7.0262 | 26.326 | 28.8326 | 38.3653 | 45.3915 | 16.131 | 10.195 | 2.3377 | 2.5065 | 4.6985 | 4.0131 | 9.5327 | 7.0262 | 26.326 | 28.8326 | 38.3653 | 45.3915 | 0
7.8716 | 8.4055 | 2.0624 | 2.0936 | 3.3119 | 3.1872 | 7.4679 | 5.3743 | 16.2771 | 18.3706 | 25.8385 | 31.2128 | 7.8716 | 8.4055 | 2.0624 | 2.0936 | 3.3219 | 3.1872 | 7.4679 | 5.3743 | 16.2771 | 18.3706 | 25.8385 | 31.2128 | 0
6.6207 | 8.1345 | 2.0207 | 2.031 | 3.1035 | 3.0621 | 7.1552 | 5.1241 | 14.7552 | 16.7863 | 23.9415 | 29.0656 | 6.6207 | 8.1345 | 2.0207 | 2.031 | 3.1135 | 3.0621 | 7.1552 | 5.1241 | 14.7552 | 16.7863 | 23.9415 | 29.0656 | 0
15.6319 | 10.0869 | 2.3211 | 2.4816 | 4.6053 | 3.9632 | 9.408 | 6.9264 | 25.7188 | 28.2004 | 37.6084 | 44.5348 | 15.6319 | 10.0869 | 2.3211 | 2.4816 | 4.6153 | 3.9632 | 9.408 | 6.9264 | 25.7188 | 28.2004 | 37.6084 | 44.5348 | 0
12.4075 | 9.3883 | 2.2136 | 2.3204 | 4.0679 | 3.6408 | 8.6019 | 6.2815 | 21.7958 | 24.1162 | 32.7181 | 38.9996 | 12.4075 | 9.3883 | 2.2136 | 2.3204 | 4.0779 | 3.6408 | 8.6019 | 6.2815 | 21.7958 | 24.1162 | 32.7181 | 38.9996 | 0
3.1852 | 7.3901 | 1.9062 | 1.8593 | 2.5309 | 2.7185 | 6.2963 | 4.437 | 10.5753 | 12.4346 | 18.7309 | 23.168 | 3.1852 | 7.3901 | 1.9062 | 1.8593 | 2.5409 | 2.7185 | 6.2963 | 4.437 | 10.5753 | 12.4346 | 18.7309 | 23.168 | 0
8.0258 | 8.4389 | 2.0675 | 2.1013 | 3.3376 | 3.2026 | 7.5065 | 5.4052 | 16.4648 | 18.5661 | 26.0725 | 31.4777 | 8.0258 | 8.4389 | 2.0675 | 2.1013 | 3.3476 | 3.2026 | 7.5065 | 5.4052 | 16.4648 | 18.5661 | 26.0725 | 31.4777 | 0
-1.6375 | 6.3452 | 1.7454 | 1.6181 | 1.7271 | 2.2363 | 5.0906 | 3.4725 | 4.7078 | 6.3259 | 11.4165 | 14.889 | -1.6375 | 6.3452 | 1.7454 | 1.6181 | 1.7371 | 2.2363 | 5.0906 | 3.4725 | 4.7078 | 6.3259 | 11.4165 | 14.889 | 0
3.3169 | 7.4187 | 1.9106 | 1.8658 | 2.5528 | 2.7317 | 6.3292 | 4.4634 | 10.7355 | 12.6014 | 18.9306 | 23.394 | 3.3169 | 7.4187 | 1.9106 | 1.8658 | 2.5628 | 2.7317 | 6.3292 | 4.4634 | 10.7355 | 12.6014 | 18.9306 | 23.394 | 0
-1.316 | 6.4149 | 1.7561 | 1.6342 | 1.7807 | 2.2684 | 5.171 | 3.5368 | 5.0988 | 6.733 | 11.904 | 15.4408 | -1.316 | 6.4149 | 1.7561 | 1.6342 | 1.7907 | 2.2684 | 5.171 | 3.5368 | 5.0988 | 6.733 | 11.904 | 15.4408 | 0
7.4915 | 8.3232 | 2.0497 | 2.0746 | 3.2486 | 3.1491 | 7.3729 | 5.2983 | 15.8146 | 17.8892 | 25.2621 | 30.5603 | 7.4915 | 8.3232 | 2.0497 | 2.0746 | 3.2586 | 3.1491 | 7.3729 | 5.2983 | 15.8146 | 17.8892 | 25.2621 | 30.5603 | 0
1.1213 | 6.943 | 1.8374 | 1.7561 | 2.1869 | 2.5121 | 5.7803 | 4.0243 | 8.0643 | 9.8204 | 15.6007 | 19.625 | 1.1213 | 6.943 | 1.8374 | 1.7561 | 2.1969 | 2.5121 | 5.7803 | 4.0243 | 8.0643 | 9.8204 | 15.6007 | 19.625 | 0
-0.19129 | 6.6586 | 1.7936 | 1.6904 | 1.9681 | 2.3809 | 5.4522 | 3.7617 | 6.4673 | 8.1577 | 13.6099 | 17.3716 | -0.19129 | 6.6586 | 1.7936 | 1.6904 | 1.9781 | 2.3809 | 5.4522 | 3.7617 | 6.4673 | 8.1577 | 13.6099 | 17.3716 | 0
14.9327 | 9.9354 | 2.2978 | 2.4466 | 4.4888 | 3.8933 | 9.2332 | 6.7865 | 24.8681 | 27.3147 | 36.5479 | 43.3344 | 14.9327 | 9.9354 | 2.2978 | 2.4466 | 4.4988 | 3.8933 | 9.2332 | 6.7865 | 24.8681 | 27.3147 | 36.5479 | 43.3344 | 0
6.5945 | 8.1288 | 2.0198 | 2.0297 | 3.0991 | 3.0594 | 7.1486 | 5.1189 | 14.7233 | 16.753 | 23.9016 | 29.0205 | 6.5945 | 8.1288 | 2.0198 | 2.0297 | 3.1091 | 3.0594 | 7.1486 | 5.1189 | 14.7233 | 16.753 | 23.9016 | 29.0205 | 0
9.6841 | 8.7982 | 2.1228 | 2.1842 | 3.614 | 3.3684 | 7.921 | 5.7368 | 18.4823 | 20.6665 | 28.5875 | 34.3244 | 9.6841 | 8.7982 | 2.1228 | 2.1842 | 3.624 | 3.3684 | 7.921 | 5.7368 | 18.4823 | 20.6665 | 28.5875 | 34.3244 | 0
10.8748 | 9.0562 | 2.1625 | 2.2437 | 3.8125 | 3.4875 | 8.2187 | 5.975 | 19.931 | 22.1747 | 30.3934 | 36.3684 | 10.8748 | 9.0562 | 2.1625 | 2.2437 | 3.8225 | 3.4875 | 8.2187 | 5.975 | 19.931 | 22.1747 | 30.3934 | 36.3684 | 0
9.5191 | 8.7625 | 2.1173 | 2.176 | 3.5865 | 3.3519 | 7.8798 | 5.7038 | 18.2816 | 20.4576 | 28.3373 | 34.0412 | 9.5191 | 8.7625 | 2.1173 | 2.176 | 3.5965 | 3.3519 | 7.8798 | 5.7038 | 18.2816 | 20.4576 | 28.3373 | 34.0412 | 0
11.791 | 9.2547 | 2.193 | 2.2896 | 3.9652 | 3.5791 | 8.4478 | 6.1582 | 21.0458 | 23.3353 | 31.7831 | 37.9413 | 11.791 | 9.2547 | 2.193 | 2.2896 | 3.9752 | 3.5791 | 8.4478 | 6.1582 | 21.0458 | 23.3353 | 31.7831 | 37.9413 | 0
4.0406 | 7.5755 | 1.9347 | 1.902 | 2.6734 | 2.8041 | 6.5101 | 4.6081 | 11.6161 | 13.5181 | 20.0282 | 24.6364 | 4.0406 | 7.5755 | 1.9347 | 1.902 | 2.6834 | 2.8041 | 6.5101 | 4.6081 | 11.6161 | 13.5181 | 20.0282 | 24.6364 | 0
0.16694 | 6.7362 | 1.8056 | 1.7083 | 2.0278 | 2.4167 | 5.5417 | 3.8334 | 6.9031 | 8.6115 | 14.1532 | 17.9866 | 0.16694 | 6.7362 | 1.8056 | 1.7083 | 2.0378 | 2.4167 | 5.5417 | 3.8334 | 6.9031 | 8.6115 | 14.1532 | 17.9866 | 0
1.7732 | 7.0842 | 1.8591 | 1.7887 | 2.2955 | 2.5773 | 5.9433 | 4.1546 | 8.8574 | 10.6461 | 16.5894 | 20.7441 | 1.7732 | 7.0842 | 1.8591 | 1.7887 | 2.3055 | 2.5773 | 5.9433 | 4.1546 | 8.8574 | 10.6461 | 16.5894 | 20.7441 | 0
2.946 | 7.3383 | 1.8982 | 1.8473 | 2.491 | 2.6946 | 6.2365 | 4.3892 | 10.2843 | 12.1316 | 18.3681 | 22.7573 | 2.946 | 7.3383 | 1.8982 | 1.8473 | 2.501 | 2.6946 | 6.2365 | 4.3892 | 10.2843 | 12.1316 | 18.3681 | 22.7573 | 0
5.1699 | 7.8202 | 1.9723 | 1.9585 | 2.8617 | 2.917 | 6.7925 | 4.834 | 12.9901 | 14.9486 | 21.7411 | 26.5751 | 5.1699 | 7.8202 | 1.9723 | 1.9585 | 2.8717 | 2.917 | 6.7925 | 4.834 | 12.9901 | 14.9486 | 21.7411 | 26.5751 | 0
12.1677 | 9.3363 | 2.2056 | 2.3084 | 4.0279 | 3.6168 | 8.5419 | 6.2335 | 21.504 | 23.8124 | 32.3543 | 38.5878 | 12.1677 | 9.3363 | 2.2056 | 2.3084 | 4.0379 | 3.6168 | 8.5419 | 6.2335 | 21.504 | 23.8124 | 32.3543 | 38.5878 | 0
6.5433 | 8.1177 | 2.0181 | 2.0272 | 3.0906 | 3.0543 | 7.1358 | 5.1087 | 14.661 | 16.6882 | 23.824 | 28.9327 | 6.5433 | 8.1177 | 2.0181 | 2.0272 | 3.1006 | 3.0543 | 7.1358 | 5.1087 | 14.661 | 16.6882 | 23.824 | 28.9327 | 0
11.7076 | 9.2366 | 2.1903 | 2.2854 | 3.9513 | 3.5708 | 8.4269 | 6.1415 | 20.9442 | 23.2296 | 31.6565 | 37.798 | 11.7076 | 9.2366 | 2.1903 | 2.2854 | 3.9613 | 3.5708 | 8.4269 | 6.1415 | 20.9442 | 23.2296 | 31.6565 | 37.798 | 0
5.373 | 7.8641 | 1.9791 | 1.9686 | 2.8955 | 2.9373 | 6.8432 | 4.8746 | 13.2371 | 15.2058 | 22.049 | 26.9236 | 5.373 | 7.8641 | 1.9791 | 1.9686 | 2.9055 | 2.9373 | 6.8432 | 4.8746 | 13.2371 | 15.2058 | 22.049 | 26.9236 | 0
-2.6906 | 6.117 | 1.7103 | 1.5655 | 1.5516 | 2.1309 | 4.8273 | 3.2619 | 3.4264 | 4.9919 | 9.8193 | 13.0811 | -2.6906 | 6.117 | 1.7103 | 1.5655 | 1.5616 | 2.1309 | 4.8273 | 3.2619 | 3.4264 | 4.9919 | 9.8193 | 13.0811 | 0
5.7733 | 7.9509 | 1.9924 | 1.9887 | 2.9622 | 2.9773 | 6.9433 | 4.9547 | 13.7242 | 15.7128 | 22.6561 | 27.6108 | 5.7733 | 7.9509 | 1.9924 | 1.9887 | 2.9722 | 2.9773 | 6.9433 | 4.9547 | 13.7242 | 15.7128 | 22.6561 | 27.6108 | 0
1.0347 | 6.9242 | 1.8345 | 1.7517 | 2.1724 | 2.5035 | 5.7587 | 4.0069 | 7.9588 | 9.7106 | 15.4693 | 19.4762 | 1.0347 | 6.9242 | 1.8345 | 1.7517 | 2.1824 | 2.5035 | 5.7587 | 4.0069 | 7.9588 | 9.7106 | 15.4693 | 19.4762 | 0
17.9452 | 10.5881 | 2.3982 | 2.5973 | 4.9909 | 4.1945 | 9.9863 | 7.389 | 28.5333 | 31.1306 | 41.1169 | 48.5059 | 17.9452 | 10.5881 | 2.3982 | 2.5973 | 5.0009 | 4.1945 | 9.9863 | 7.389 | 28.5333 | 31.1306 | 41.1169 | 48.5059 | 0
2.4162 | 7.2235 | 1.8805 | 1.8208 | 2.4027 | 2.6416 | 6.104 | 4.2832 | 9.6397 | 11.4605 | 17.5645 | 21.8477 | 2.4162 | 7.2235 | 1.8805 | 1.8208 | 2.4127 | 2.6416 | 6.104 | 4.2832 | 9.6397 | 11.4605 | 17.5645 | 21.8477 | 0
5.5634 | 7.9054 | 1.9854 | 1.9782 | 2.9272 | 2.9563 | 6.8909 | 4.9127 | 13.4688 | 15.447 | 22.3378 | 27.2505 | 5.5634 | 7.9054 | 1.9854 | 1.9782 | 2.9372 | 2.9563 | 6.8909 | 4.9127 | 13.4688 | 15.447 | 22.3378 | 27.2505 | 0
-4.3193 | 5.7641 | 1.656 | 1.484 | 1.2801 | 1.9681 | 4.4202 | 2.9361 | 1.4448 | 2.9288 | 7.349 | 10.2851 | -4.3193 | 5.7641 | 1.656 | 1.484 | 1.2901 | 1.9681 | 4.4202 | 2.9361 | 1.4448 | 2.9288 | 7.349 | 10.2851 | 0
-1.7225 | 6.3268 | 1.7426 | 1.6139 | 1.7129 | 2.2278 | 5.0694 | 3.4555 | 4.6043 | 6.2182 | 11.2876 | 14.7431 | -1.7225 | 6.3268 | 1.7426 | 1.6139 | 1.7229 | 2.2278 | 5.0694 | 3.4555 | 4.6043 | 6.2182 | 11.2876 | 14.7431 | 0
5.3795 | 7.8656 | 1.9793 | 1.969 | 2.8966 | 2.9379 | 6.8449 | 4.8759 | 13.245 | 15.214 | 22.0589 | 26.9348 | 5.3795 | 7.8656 | 1.9793 | 1.969 | 2.9066 | 2.9379 | 6.8449 | 4.8759 | 13.245 | 15.214 | 22.0589 | 26.9348 | 0
2.8529 | 7.3181 | 1.8951 | 1.8426 | 2.4755 | 2.6853 | 6.2132 | 4.3706 | 10.171 | 12.0137 | 18.2269 | 22.5975 | 2.8529 | 7.3181 | 1.8951 | 1.8426 | 2.4855 | 2.6853 | 6.2132 | 4.3706 | 10.171 | 12.0137 | 18.2269 | 22.5975 | 0
4.9315 | 7.7685 | 1.9644 | 1.9466 | 2.8219 | 2.8931 | 6.7329 | 4.7863 | 12.6999 | 14.6465 | 21.3794 | 26.1657 | 4.9315 | 7.7685 | 1.9644 | 1.9466 | 2.8319 | 2.8931 | 6.7329 | 4.7863 | 12.6999 | 14.6465 | 21.3794 | 26.1657 | 0
8.9348 | 8.6359 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7337 | 5.587 | 17.5707 | 19.7175 | 27.4512 | 33.0382 | 8.9348 | 8.6359 | 2.0978 | 2.1467 | 3.4991 | 3.2935 | 7.7337 | 5.587 | 17.5707 | 19.7175 | 27.4512 | 33.0382 | 0
18.576 | 10.7248 | 2.4192 | 2.6288 | 5.096 | 4.2576 | 10.144 | 7.5152 | 29.3008 | 31.9296 | 42.0736 | 49.5888 | 18.576 | 10.7248 | 2.4192 | 2.6288 | 5.106 | 4.2576 | 10.144 | 7.5152 | 29.3008 | 31.9296 | 42.0736 | 49.5888 | 0
10.8329 | 9.0471 | 2.1611 | 2.2416 | 3.8055 | 3.4833 | 8.2082 | 5.9666 | 19.88 | 22.1217 | 30.3299 | 36.2965 | 10.8329 | 9.0471 | 2.1611 | 2.2416 | 3.8155 | 3.4833 | 8.2082 | 5.9666 | 19.88 | 22.1217 | 30.3299 | 36.2965 | 0
20.2137 | 11.0796 | 2.4738 | 2.7107 | 5.3689 | 4.4214 | 10.5534 | 7.8427 | 31.2933 | 34.004 | 44.5574 | 52.4001 | 20.2137 | 11.0796 | 2.4738 | 2.7107 | 5.3789 | 4.4214 | 10.5534 | 7.8427 | 31.2933 | 34.004 | 44.5574 | 52.4001 | 0
-2.0597 | 6.2537 | 1.7313 | 1.597 | 1.6567 | 2.194 | 4.9851 | 3.3881 | 4.1941 | 5.7911 | 10.7762 | 14.1642 | -2.0597 | 6.2537 | 1.7313 | 1.597 | 1.6667 | 2.194 | 4.9851 | 3.3881 | 4.1941 | 5.7911 | 10.7762 | 14.1642 | 0
10.1219 | 8.8931 | 2.1374 | 2.2061 | 3.687 | 3.4122 | 8.0305 | 5.8244 | 19.015 | 21.2211 | 29.2516 | 35.0759 | 10.1219 | 8.8931 | 2.1374 | 2.2061 | 3.697 | 3.4122 | 8.0305 | 5.8244 | 19.015 | 21.2211 | 29.2516 | 35.0759 | 0
9.1303 | 8.6782 | 2.1043 | 2.1565 | 3.5217 | 3.313 | 7.7826 | 5.6261 | 17.8085 | 19.965 | 27.7476 | 33.3737 | 9.1303 | 8.6782 | 2.1043 | 2.1565 | 3.5317 | 3.313 | 7.7826 | 5.6261 | 17.8085 | 19.965 | 27.7476 | 33.3737 | 0
1.075 | 6.9329 | 1.8358 | 1.7537 | 2.1792 | 2.5075 | 5.7687 | 4.015 | 8.0079 | 9.7616 | 15.5304 | 19.5454 | 1.075 | 6.9329 | 1.8358 | 1.7537 | 2.1892 | 2.5075 | 5.7687 | 4.015 | 8.0079 | 9.7616 | 15.5304 | 19.5454 | 0
-4.9896 | 5.6189 | 1.6337 | 1.4505 | 1.1684 | 1.901 | 4.2526 | 2.8021 | 0.62936 | 2.0799 | 6.3325 | 9.1346 | -4.9896 | 5.6189 | 1.6337 | 1.4505 | 1.1784 | 1.901 | 4.2526 | 2.8021 | 0.62936 | 2.0799 | 6.3325 | 9.1346 | 0
-0.62885 | 6.5637 | 1.779 | 1.6686 | 1.8952 | 2.3371 | 5.3428 | 3.6742 | 5.9349 | 7.6035 | 12.9462 | 16.6205 | -0.62885 | 6.5637 | 1.779 | 1.6686 | 1.9052 | 2.3371 | 5.3428 | 3.6742 | 5.9349 | 7.6035 | 12.9462 | 16.6205 | 0
7.2339 | 8.2674 | 2.0411 | 2.0617 | 3.2057 | 3.1234 | 7.3085 | 5.2468 | 15.5013 | 17.563 | 24.8715 | 30.1183 | 7.2339 | 8.2674 | 2.0411 | 2.0617 | 3.2157 | 3.1234 | 7.3085 | 5.2468 | 15.5013 | 17.563 | 24.8715 | 30.1183 | 0
10.4833 | 8.9714 | 2.1494 | 2.2242 | 3.7472 | 3.4483 | 8.1208 | 5.8967 | 19.4547 | 21.6788 | 29.7997 | 35.6963 | 10.4833 | 8.9714 | 2.1494 | 2.2242 | 3.7572 | 3.4483 | 8.1208 | 5.8967 | 19.4547 | 21.6788 | 29.7997 | 35.6963 | 0
17.6691 | 10.5283 | 2.389 | 2.5835 | 4.9448 | 4.1669 | 9.9173 | 7.3338 | 28.1974 | 30.7808 | 40.6981 | 48.0319 | 17.6691 | 10.5283 | 2.389 | 2.5835 | 4.9548 | 4.1669 | 9.9173 | 7.3338 | 28.1974 | 30.7808 | 40.6981 | 48.0319 | 0
10.1095 | 8.8904 | 2.137 | 2.2055 | 3.6849 | 3.4109 | 8.0274 | 5.8219 | 18.9999 | 21.2053 | 29.2327 | 35.0546 | 10.1095 | 8.8904 | 2.137 | 2.2055 | 3.6949 | 3.4109 | 8.0274 | 5.8219 | 18.9999 | 21.2053 | 29.2327 | 35.0546 | 0
9.4732 | 8.7525 | 2.1158 | 2.1737 | 3.5789 | 3.3473 | 7.8683 | 5.6946 | 18.2258 | 20.3994 | 28.2677 | 33.9624 | 9.4732 | 8.7525 | 2.1158 | 2.1737 | 3.5889 | 3.3473 | 7.8683 | 5.6946 | 18.2258 | 20.3994 | 28.2677 | 33.9624 | 0
6.8688 | 8.1882 | 2.029 | 2.0434 | 3.1448 | 3.0869 | 7.2172 | 5.1738 | 15.057 | 17.1005 | 24.3177 | 29.4914 | 6.8688 | 8.1882 | 2.029 | 2.0434 | 3.1548 | 3.0869 | 7.2172 | 5.1738 | 15.057 | 17.1005 | 24.3177 | 29.4914 | 0
-7.7712 | 5.0162 | 1.541 | 1.3114 | 0.7048 | 1.6229 | 3.5572 | 2.2458 | -2.755 | -1.4435 | 2.1137 | 4.3594 | -7.7712 | 5.0162 | 1.541 | 1.3114 | 0.7148 | 1.6229 | 3.5572 | 2.2458 | -2.755 | -1.4435 | 2.1137 | 4.3594 | 0
6.6159 | 8.1335 | 2.0205 | 2.0308 | 3.1027 | 3.0616 | 7.154 | 5.1232 | 14.7494 | 16.7802 | 23.9342 | 29.0574 | 6.6159 | 8.1335 | 2.0205 | 2.0308 | 3.1127 | 3.0616 | 7.154 | 5.1232 | 14.7494 | 16.7802 | 23.9342 | 29.0574 | 0
7.7482 | 8.3788 | 2.0583 | 2.0874 | 3.2914 | 3.1748 | 7.437 | 5.3496 | 16.127 | 18.2144 | 25.6514 | 31.0011 | 7.7482 | 8.3788 | 2.0583 | 2.0874 | 3.3014 | 3.1748 | 7.437 | 5.3496 | 16.127 | 18.2144 | 25.6514 | 31.0011 | 0
11.3824 | 9.1662 | 2.1794 | 2.2691 | 3.8971 | 3.5382 | 8.3456 | 6.0765 | 20.5485 | 22.8177 | 31.1632 | 37.2397 | 11.3824 | 9.1662 | 2.1794 | 2.2691 | 3.9071 | 3.5382 | 8.3456 | 6.0765 | 20.5485 | 22.8177 | 31.1632 | 37.2397 | 0
3.369 | 7.4299 | 1.9123 | 1.8684 | 2.5615 | 2.7369 | 6.3422 | 4.4738 | 10.7989 | 12.6674 | 19.0096 | 23.4834 | 3.369 | 7.4299 | 1.9123 | 1.8684 | 2.5715 | 2.7369 | 6.3422 | 4.4738 | 10.7989 | 12.6674 | 19.0096 | 23.4834 | 0
12.951 | 9.506 | 2.2317 | 2.3475 | 4.1585 | 3.6951 | 8.7377 | 6.3902 | 22.457 | 24.8046 | 33.5423 | 39.9325 | 12.951 | 9.506 | 2.2317 | 2.3475 | 4.1685 | 3.6951 | 8.7377 | 6.3902 | 22.457 | 24.8046 | 33.5423 | 39.9325 | 0
0.55287 | 6.8198 | 1.8184 | 1.7276 | 2.0921 | 2.4553 | 5.6382 | 3.9106 | 7.3727 | 9.1003 | 14.7385 | 18.6491 | 0.55287 | 6.8198 | 1.8184 | 1.7276 | 2.1021 | 2.4553 | 5.6382 | 3.9106 | 7.3727 | 9.1003 | 14.7385 | 18.6491 | 0
5.8476 | 7.967 | 1.9949 | 1.9924 | 2.9746 | 2.9848 | 6.9619 | 4.9695 | 13.8146 | 15.807 | 22.7689 | 27.7384 | 5.8476 | 7.967 | 1.9949 | 1.9924 | 2.9846 | 2.9848 | 6.9619 | 4.9695 | 13.8146 | 15.807 | 22.7689 | 27.7384 | 0
1.2162 | 6.9635 | 1.8405 | 1.7608 | 2.2027 | 2.5216 | 5.8041 | 4.0432 | 8.1798 | 9.9406 | 15.7446 | 19.7879 | 1.2162 | 6.9635 | 1.8405 | 1.7608 | 2.2127 | 2.5216 | 5.8041 | 4.0432 | 8.1798 | 9.9406 | 15.7446 | 19.7879 | 0
12.2562 | 9.3555 | 2.2085 | 2.3128 | 4.0427 | 3.6256 | 8.564 | 6.2512 | 21.6117 | 23.9245 | 32.4885 | 38.7398 | 12.2562 | 9.3555 | 2.2085 | 2.3128 | 4.0527 | 3.6256 | 8.564 | 6.2512 | 21.6117 | 23.9245 | 32.4885 | 38.7398 | 0
4.5273 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7055 | 12.2082 | 14.1346 | 20.7664 | 25.4718 | 4.5273 | 7.6809 | 1.9509 | 1.9264 | 2.7645 | 2.8527 | 6.6318 | 4.7055 | 12.2082 | 14.1346 | 20.7664 | 25.4718 | 0
-1.3747 | 6.4021 | 1.7542 | 1.6313 | 1.7709 | 2.2625 | 5.1563 | 3.5251 | 5.0275 | 6.6587 | 11.815 | 15.3401 | -1.3747 | 6.4021 | 1.7542 | 1.6313 | 1.7809 | 2.2625 | 5.1563 | 3.5251 | 5.0275 | 6.6587 | 11.815 | 15.3401 | 0
7.568 | 8.3397 | 2.0523 | 2.0784 | 3.2613 | 3.1568 | 7.392 | 5.3136 | 15.9077 | 17.9861 | 25.3781 | 30.6917 | 7.568 | 8.3397 | 2.0523 | 2.0784 | 3.2713 | 3.1568 | 7.392 | 5.3136 | 15.9077 | 17.9861 | 25.3781 | 30.6917 | 0
17.8346 | 10.5642 | 2.3945 | 2.5917 | 4.9724 | 4.1835 | 9.9586 | 7.3669 | 28.3987 | 30.9905 | 40.9491 | 48.316 | 17.8346 | 10.5642 | 2.3945 | 2.5917 | 4.9824 | 4.1835 | 9.9586 | 7.3669 | 28.3987 | 30.9905 | 40.9491 | 48.316 | 0
14.6358 | 9.8711 | 2.2879 | 2.4318 | 4.4393 | 3.8636 | 9.159 | 6.7272 | 24.5069 | 26.9387 | 36.0977 | 42.8248 | 14.6358 | 9.8711 | 2.2879 | 2.4318 | 4.4493 | 3.8636 | 9.159 | 6.7272 | 24.5069 | 26.9387 | 36.0977 | 42.8248 | 0
14.7192 | 9.8892 | 2.2906 | 2.436 | 4.4532 | 3.8719 | 9.1798 | 6.7438 | 24.6084 | 27.0443 | 36.2241 | 42.968 | 14.7192 | 9.8892 | 2.2906 | 2.436 | 4.4632 | 3.8719 | 9.1798 | 6.7438 | 24.6084 | 27.0443 | 36.2241 | 42.968 | 0
8.6596 | 8.5763 | 2.0887 | 2.133 | 3.4433 | 3.266 | 7.6649 | 5.5319 | 17.2359 | 19.3689 | 27.0338 | 32.5657 | 8.6596 | 8.5763 | 2.0887 | 2.133 | 3.4533 | 3.266 | 7.6649 | 5.5319 | 17.2359 | 19.3689 | 27.0338 | 32.5657 | 0
-0.8912 | 6.5069 | 1.7703 | 1.6554 | 1.8515 | 2.3109 | 5.2772 | 3.6218 | 5.6157 | 7.2712 | 12.5484 | 16.1701 | -0.8912 | 6.5069 | 1.7703 | 1.6554 | 1.8615 | 2.3109 | 5.2772 | 3.6218 | 5.6157 | 7.2712 | 12.5484 | 16.1701 | 0
0.11658 | 6.7253 | 1.8039 | 1.7058 | 2.0194 | 2.4117 | 5.5291 | 3.8233 | 6.8418 | 8.5477 | 14.0768 | 17.9001 | 0.11658 | 6.7253 | 1.8039 | 1.7058 | 2.0294 | 2.4117 | 5.5291 | 3.8233 | 6.8418 | 8.5477 | 14.0768 | 17.9001 | 0
2.9789 | 7.3454 | 1.8993 | 1.8489 | 2.4965 | 2.6979 | 6.2447 | 4.3958 | 10.3243 | 12.1733 | 18.418 | 22.8138 | 2.9789 | 7.3454 | 1.8993 | 1.8489 | 2.5065 | 2.6979 | 6.2447 | 4.3958 | 10.3243 | 12.1733 | 18.418 | 22.8138 | 0
10.7182 | 9.0223 | 2.1573 | 2.2359 | 3.7864 | 3.4718 | 8.1796 | 5.9436 | 19.7405 | 21.9764 | 30.156 | 36.0997 | 10.7182 | 9.0223 | 2.1573 | 2.2359 | 3.7964 | 3.4718 | 8.1796 | 5.9436 | 19.7405 | 21.9764 | 30.156 | 36.0997 | 0
8.2018 | 8.4771 | 2.0734 | 2.1101 | 3.367 | 3.2202 | 7.5505 | 5.4404 | 16.6789 | 18.789 | 26.3395 | 31.7798 | 8.2018 | 8.4771 | 2.0734 | 2.1101 | 3.377 | 3.2202 | 7.5505 | 5.4404 | 16.6789 | 18.789 | 26.3395 | 31.7798 | 0
14.9186 | 9.9324 | 2.2973 | 2.4459 | 4.4864 | 3.8919 | 9.2296 | 6.7837 | 24.8509 | 27.2969 | 36.5265 | 43.3102 | 14.9186 | 9.9324 | 2.2973 | 2.4459 | 4.4964 | 3.8919 | 9.2296 | 6.7837 | 24.8509 | 27.2969 | 36.5265 | 43.3102 | 0
3.278 | 7.4102 | 1.9093 | 1.8639 | 2.5463 | 2.7278 | 6.3195 | 4.4556 | 10.6882 | 12.5521 | 18.8716 | 23.3272 | 3.278 | 7.4102 | 1.9093 | 1.8639 | 2.5563 | 2.7278 | 6.3195 | 4.4556 | 10.6882 | 12.5521 | 18.8716 | 23.3272 | 0
11.9059 | 9.2796 | 2.1969 | 2.2953 | 3.9843 | 3.5906 | 8.4765 | 6.1812 | 21.1855 | 23.4808 | 31.9572 | 38.1384 | 11.9059 | 9.2796 | 2.1969 | 2.2953 | 3.9943 | 3.5906 | 8.4765 | 6.1812 | 21.1855 | 23.4808 | 31.9572 | 38.1384 | 0
0.21186 | 6.7459 | 1.8071 | 1.7106 | 2.0353 | 2.4212 | 5.553 | 3.8424 | 6.9578 | 8.6684 | 14.2213 | 18.0637 | 0.21186 | 6.7459 | 1.8071 | 1.7106 | 2.0453 | 2.4212 | 5.553 | 3.8424 | 6.9578 | 8.6684 | 14.2213 | 18.0637 | 0
8.3077 | 8.5 | 2.0769 | 2.1154 | 3.3846 | 3.2308 | 7.5769 | 5.4615 | 16.8077 | 18.9231 | 26.5001 | 31.9616 | 8.3077 | 8.5 | 2.0769 | 2.1154 | 3.3946 | 3.2308 | 7.5769 | 5.4615 | 16.8077 | 18.9231 | 26.5001 | 31.9616 | 0
0.99521 | 6.9156 | 1.8332 | 1.7498 | 2.1659 | 2.4995 | 5.7488 | 3.999 | 7.9108 | 9.6606 | 15.4094 | 19.4084 | 0.99521 | 6.9156 | 1.8332 | 1.7498 | 2.1759 | 2.4995 | 5.7488 | 3.999 | 7.9108 | 9.6606 | 15.4094 | 19.4084 | 0
10.022 | 8.8714 | 2.1341 | 2.2011 | 3.6703 | 3.4022 | 8.0055 | 5.8044 | 18.8934 | 21.0945 | 29.1 | 34.9045 | 10.022 | 8.8714 | 2.1341 | 2.2011 | 3.6803 | 3.4022 | 8.0055 | 5.8044 | 18.8934 | 21.0945 | 29.1 | 34.9045 | 0
-5.1718 | 5.5794 | 1.6276 | 1.4414 | 1.138 | 1.8828 | 4.207 | 2.7656 | 0.4076 | 1.849 | 6.0561 | 8.8217 | -5.1718 | 5.5794 | 1.6276 | 1.4414 | 1.148 | 1.8828 | 4.207 | 2.7656 | 0.4076 | 1.849 | 6.0561 | 8.8217 | 0
-1.0844 | 6.465 | 1.7639 | 1.6458 | 1.8193 | 2.2916 | 5.2289 | 3.5831 | 5.3806 | 7.0264 | 12.2553 | 15.8384 | -1.0844 | 6.465 | 1.7639 | 1.6458 | 1.8293 | 2.2916 | 5.2289 | 3.5831 | 5.3806 | 7.0264 | 12.2553 | 15.8384 | 0
6.9795 | 8.2122 | 2.0326 | 2.049 | 3.1632 | 3.0979 | 7.2449 | 5.1959 | 15.1917 | 17.2407 | 24.4855 | 29.6814 | 6.9795 | 8.2122 | 2.0326 | 2.049 | 3.1732 | 3.0979 | 7.2449 | 5.1959 | 15.1917 | 17.2407 | 24.4855 | 29.6814 | 0
1.3132 | 6.9845 | 1.8438 | 1.7657 | 2.2189 | 2.5313 | 5.8283 | 4.0626 | 8.2978 | 10.0634 | 15.8917 | 19.9544 | 1.3132 | 6.9845 | 1.8438 | 1.7657 | 2.2289 | 2.5313 | 5.8283 | 4.0626 | 8.2978 | 10.0634 | 15.8917 | 19.9544 | 0
1.3639 | 6.9955 | 1.8455 | 1.7682 | 2.2273 | 2.5364 | 5.841 | 4.0728 | 8.3594 | 10.1276 | 15.9686 | 20.0414 | 1.3639 | 6.9955 | 1.8455 | 1.7682 | 2.2373 | 2.5364 | 5.841 | 4.0728 | 8.3594 | 10.1276 | 15.9686 | 20.0414 | 0
-1.4768 | 6.38 | 1.7508 | 1.6262 | 1.7539 | 2.2523 | 5.1308 | 3.5046 | 4.9032 | 6.5293 | 11.6601 | 15.1648 | -1.4768 | 6.38 | 1.7508 | 1.6262 | 1.7639 | 2.2523 | 5.1308 | 3.5046 | 4.9032 | 6.5293 | 11.6601 | 15.1648 | 0
6.5105 | 8.1106 | 2.017 | 2.0255 | 3.0851 | 3.0511 | 7.1276 | 5.1021 | 14.6211 | 16.6466 | 23.7743 | 28.8764 | 6.5105 | 8.1106 | 2.017 | 2.0255 | 3.0951 | 3.0511 | 7.1276 | 5.1021 | 14.6211 | 16.6466 | 23.7743 | 28.8764 | 0
2.9522 | 7.3396 | 1.8984 | 1.8476 | 2.492 | 2.6952 | 6.238 | 4.3904 | 10.2918 | 12.1394 | 18.3775 | 22.7679 | 2.9522 | 7.3396 | 1.8984 | 1.8476 | 2.502 | 2.6952 | 6.238 | 4.3904 | 10.2918 | 12.1394 | 18.3775 | 22.7679 | 0
6.1645 | 8.0356 | 2.0055 | 2.0082 | 3.0274 | 3.0165 | 7.0411 | 5.0329 | 14.2002 | 16.2084 | 23.2495 | 28.2824 | 6.1645 | 8.0356 | 2.0055 | 2.0082 | 3.0374 | 3.0165 | 7.0411 | 5.0329 | 14.2002 | 16.2084 | 23.2495 | 28.2824 | 0
3.115 | 7.3749 | 1.9038 | 1.8557 | 2.5192 | 2.7115 | 6.2787 | 4.423 | 10.4899 | 12.3457 | 18.6244 | 23.0474 | 3.115 | 7.3749 | 1.9038 | 1.8557 | 2.5292 | 2.7115 | 6.2787 | 4.423 | 10.4899 | 12.3457 | 18.6244 | 23.0474 | 0
6.4626 | 8.1002 | 2.0154 | 2.0231 | 3.0771 | 3.0463 | 7.1157 | 5.0925 | 14.5628 | 16.586 | 23.7016 | 28.7941 | 6.4626 | 8.1002 | 2.0154 | 2.0231 | 3.0871 | 3.0463 | 7.1157 | 5.0925 | 14.5628 | 16.586 | 23.7016 | 28.7941 | 0
16.0124 | 10.1694 | 2.3337 | 2.5006 | 4.6687 | 4.0012 | 9.5031 | 7.0025 | 26.1817 | 28.6824 | 38.1855 | 45.1879 | 16.0124 | 10.1694 | 2.3337 | 2.5006 | 4.6787 | 4.0012 | 9.5031 | 7.0025 | 26.1817 | 28.6824 | 38.1855 | 45.1879 | 0
1.5673 | 7.0396 | 1.8522 | 1.7784 | 2.2612 | 2.5567 | 5.8918 | 4.1135 | 8.6068 | 10.3852 | 16.277 | 20.3904 | 1.5673 | 7.0396 | 1.8522 | 1.7784 | 2.2712 | 2.5567 | 5.8918 | 4.1135 | 8.6068 | 10.3852 | 16.277 | 20.3904 | 0
13.5036 | 9.6258 | 2.2501 | 2.3752 | 4.2506 | 3.7504 | 8.8759 | 6.5007 | 23.1293 | 25.5045 | 34.3804 | 40.8811 | 13.5036 | 9.6258 | 2.2501 | 2.3752 | 4.2606 | 3.7504 | 8.8759 | 6.5007 | 23.1293 | 25.5045 | 34.3804 | 40.8811 | 0
0.21402 | 6.7464 | 1.8071 | 1.7107 | 2.0357 | 2.4214 | 5.5535 | 3.8428 | 6.9604 | 8.6711 | 14.2246 | 18.0674 | 0.21402 | 6.7464 | 1.8071 | 1.7107 | 2.0457 | 2.4214 | 5.5535 | 3.8428 | 6.9604 | 8.6711 | 14.2246 | 18.0674 | 0
0.14578 | 6.7316 | 1.8049 | 1.7073 | 2.0243 | 2.4146 | 5.5364 | 3.8292 | 6.8774 | 8.5847 | 14.1211 | 17.9503 | 0.14578 | 6.7316 | 1.8049 | 1.7073 | 2.0343 | 2.4146 | 5.5364 | 3.8292 | 6.8774 | 8.5847 | 14.1211 | 17.9503 | 0
6.3738 | 8.081 | 2.0125 | 2.0187 | 3.0623 | 3.0374 | 7.0935 | 5.0748 | 14.4548 | 16.4735 | 23.5669 | 28.6417 | 6.3738 | 8.081 | 2.0125 | 2.0187 | 3.0723 | 3.0374 | 7.0935 | 5.0748 | 14.4548 | 16.4735 | 23.5669 | 28.6417 | 0
16.4514 | 10.2645 | 2.3484 | 2.5226 | 4.7419 | 4.0451 | 9.6128 | 7.0903 | 26.7158 | 29.2384 | 38.8513 | 45.9415 | 16.4514 | 10.2645 | 2.3484 | 2.5226 | 4.7519 | 4.0451 | 9.6128 | 7.0903 | 26.7158 | 29.2384 | 38.8513 | 45.9415 | 0
13.4295 | 9.6097 | 2.2477 | 2.3715 | 4.2383 | 3.743 | 8.8574 | 6.4859 | 23.0392 | 25.4107 | 34.2681 | 40.754 | 13.4295 | 9.6097 | 2.2477 | 2.3715 | 4.2483 | 3.743 | 8.8574 | 6.4859 | 23.0392 | 25.4107 | 34.2681 | 40.754 | 0
-7.4375 | 5.0886 | 1.5521 | 1.3281 | 0.76042 | 1.6563 | 3.6406 | 2.3125 | -2.3489 | -1.0208 | 2.6199 | 4.9324 | -7.4375 | 5.0886 | 1.5521 | 1.3281 | 0.77042 | 1.6563 | 3.6406 | 2.3125 | -2.3489 | -1.0208 | 2.6199 | 4.9324 | 0
-2.1955 | 6.2243 | 1.7268 | 1.5902 | 1.6341 | 2.1805 | 4.9511 | 3.3609 | 4.0288 | 5.6191 | 10.5702 | 13.9311 | -2.1955 | 6.2243 | 1.7268 | 1.5902 | 1.6441 | 2.1805 | 4.9511 | 3.3609 | 4.0288 | 5.6191 | 10.5702 | 13.9311 | 0
-0.86628 | 6.5123 | 1.7711 | 1.6567 | 1.8556 | 2.3134 | 5.2834 | 3.6267 | 5.646 | 7.3027 | 12.5861 | 16.2129 | -0.86628 | 6.5123 | 1.7711 | 1.6567 | 1.8656 | 2.3134 | 5.2834 | 3.6267 | 5.646 | 7.3027 | 12.5861 | 16.2129 | 0
7.4517 | 8.3145 | 2.0484 | 2.0726 | 3.2419 | 3.1452 | 7.3629 | 5.2903 | 15.7662 | 17.8388 | 25.2017 | 30.492 | 7.4517 | 8.3145 | 2.0484 | 2.0726 | 3.2519 | 3.1452 | 7.3629 | 5.2903 | 15.7662 | 17.8388 | 25.2017 | 30.492 | 0
-4.548 | 5.7146 | 1.6484 | 1.4726 | 1.242 | 1.9452 | 4.363 | 2.8904 | 1.1666 | 2.6392 | 7.0022 | 9.8926 | -4.548 | 5.7146 | 1.6484 | 1.4726 | 1.252 | 1.9452 | 4.363 | 2.8904 | 1.1666 | 2.6392 | 7.0022 | 9.8926 | 0
10.1638 | 8.9022 | 2.1388 | 2.2082 | 3.694 | 3.4164 | 8.0409 | 5.8328 | 19.066 | 21.2741 | 29.3151 | 35.1479 | 10.1638 | 8.9022 | 2.1388 | 2.2082 | 3.704 | 3.4164 | 8.0409 | 5.8328 | 19.066 | 21.2741 | 29.3151 | 35.1479 | 0
7.2783 | 8.277 | 2.0426 | 2.0639 | 3.213 | 3.1278 | 7.3196 | 5.2557 | 15.5552 | 17.6191 | 24.9387 | 30.1943 | 7.2783 | 8.277 | 2.0426 | 2.0639 | 3.223 | 3.1278 | 7.3196 | 5.2557 | 15.5552 | 17.6191 | 24.9387 | 30.1943 | 0
1.4575 | 7.0158 | 1.8486 | 1.7729 | 2.2429 | 2.5457 | 5.8644 | 4.0915 | 8.4732 | 10.2461 | 16.1105 | 20.202 | 1.4575 | 7.0158 | 1.8486 | 1.7729 | 2.2529 | 2.5457 | 5.8644 | 4.0915 | 8.4732 | 10.2461 | 16.1105 | 20.202 | 0
-0.57037 | 6.5764 | 1.781 | 1.6715 | 1.9049 | 2.343 | 5.3574 | 3.6859 | 6.0061 | 7.6775 | 13.0349 | 16.7209 | -0.57037 | 6.5764 | 1.781 | 1.6715 | 1.9149 | 2.343 | 5.3574 | 3.6859 | 6.0061 | 7.6775 | 13.0349 | 16.7209 | 0
2.3931 | 7.2185 | 1.8798 | 1.8197 | 2.3989 | 2.6393 | 6.0983 | 4.2786 | 9.6116 | 11.4313 | 17.5295 | 21.8082 | 2.3931 | 7.2185 | 1.8798 | 1.8197 | 2.4089 | 2.6393 | 6.0983 | 4.2786 | 9.6116 | 11.4313 | 17.5295 | 21.8082 | 0
14.9926 | 9.9484 | 2.2998 | 2.4496 | 4.4988 | 3.8993 | 9.2481 | 6.7985 | 24.941 | 27.3906 | 36.6387 | 43.4372 | 14.9926 | 9.9484 | 2.2998 | 2.4496 | 4.5088 | 3.8993 | 9.2481 | 6.7985 | 24.941 | 27.3906 | 36.6387 | 43.4372 | 0
5.5444 | 7.9013 | 1.9848 | 1.9772 | 2.9241 | 2.9544 | 6.8861 | 4.9089 | 13.4457 | 15.423 | 22.3091 | 27.218 | 5.5444 | 7.9013 | 1.9848 | 1.9772 | 2.9341 | 2.9544 | 6.8861 | 4.9089 | 13.4457 | 15.423 | 22.3091 | 27.218 | 0
13.6245 | 9.652 | 2.2542 | 2.3812 | 4.2708 | 3.7625 | 8.9061 | 6.5249 | 23.2765 | 25.6577 | 34.5638 | 41.0887 | 13.6245 | 9.652 | 2.2542 | 2.3812 | 4.2808 | 3.7625 | 8.9061 | 6.5249 | 23.2765 | 25.6577 | 34.5638 | 41.0887 | 0
1.3803 | 6.9991 | 1.846 | 1.769 | 2.2301 | 2.538 | 5.8451 | 4.0761 | 8.3794 | 10.1484 | 15.9935 | 20.0695 | 1.3803 | 6.9991 | 1.846 | 1.769 | 2.2401 | 2.538 | 5.8451 | 4.0761 | 8.3794 | 10.1484 | 15.9935 | 20.0695 | 0
9.4004 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.8501 | 5.6801 | 18.1371 | 20.3071 | 28.1572 | 33.8373 | 9.4004 | 8.7367 | 2.1133 | 2.17 | 3.5767 | 3.34 | 7.8501 | 5.6801 | 18.1371 | 20.3071 | 28.1572 | 33.8373 | 0
5.1169 | 7.8087 | 1.9706 | 1.9558 | 2.8528 | 2.9117 | 6.7792 | 4.8234 | 12.9255 | 14.8813 | 21.6606 | 26.4839 | 5.1169 | 7.8087 | 1.9706 | 1.9558 | 2.8628 | 2.9117 | 6.7792 | 4.8234 | 12.9255 | 14.8813 | 21.6606 | 26.4839 | 0
-0.84508 | 6.5169 | 1.7718 | 1.6577 | 1.8592 | 2.3155 | 5.2887 | 3.631 | 5.6718 | 7.3296 | 12.6183 | 16.2493 | -0.84508 | 6.5169 | 1.7718 | 1.6577 | 1.8692 | 2.3155 | 5.2887 | 3.631 | 5.6718 | 7.3296 | 12.6183 | 16.2493 | 0
14.9278 | 9.9344 | 2.2976 | 2.4464 | 4.488 | 3.8928 | 9.232 | 6.7856 | 24.8622 | 27.3086 | 36.5405 | 43.3261 | 14.9278 | 9.9344 | 2.2976 | 2.4464 | 4.498 | 3.8928 | 9.232 | 6.7856 | 24.8622 | 27.3086 | 36.5405 | 43.3261 | 0
9.9078 | 8.8467 | 2.1303 | 2.1954 | 3.6513 | 3.3908 | 7.977 | 5.7816 | 18.7545 | 20.9499 | 28.9268 | 34.7084 | 9.9078 | 8.8467 | 2.1303 | 2.1954 | 3.6613 | 3.3908 | 7.977 | 5.7816 | 18.7545 | 20.9499 | 28.9268 | 34.7084 | 0
5.1469 | 7.8152 | 1.9716 | 1.9573 | 2.8578 | 2.9147 | 6.7867 | 4.8294 | 12.962 | 14.9194 | 21.7061 | 26.5355 | 5.1469 | 7.8152 | 1.9716 | 1.9573 | 2.8678 | 2.9147 | 6.7867 | 4.8294 | 12.962 | 14.9194 | 21.7061 | 26.5355 | 0
3.5807 | 7.4758 | 1.9194 | 1.879 | 2.5968 | 2.7581 | 6.3952 | 4.5161 | 11.0565 | 12.9355 | 19.3307 | 23.8468 | 3.5807 | 7.4758 | 1.9194 | 1.879 | 2.6068 | 2.7581 | 6.3952 | 4.5161 | 11.0565 | 12.9355 | 19.3307 | 23.8468 | 0
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2043 | 14.1305 | 20.7616 | 25.4664 | 4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.764 | 2.8524 | 6.631 | 4.7048 | 12.2043 | 14.1305 | 20.7616 | 25.4664 | 0
8.6671 | 8.5779 | 2.0889 | 2.1334 | 3.4445 | 3.2667 | 7.6668 | 5.5334 | 17.2449 | 19.3783 | 27.0451 | 32.5785 | 8.6671 | 8.5779 | 2.0889 | 2.1334 | 3.4545 | 3.2667 | 7.6668 | 5.5334 | 17.2449 | 19.3783 | 27.0451 | 32.5785 | 0
8.4187 | 8.5241 | 2.0806 | 2.1209 | 3.4031 | 3.2419 | 7.6047 | 5.4837 | 16.9428 | 19.0637 | 26.6684 | 32.1522 | 8.4187 | 8.5241 | 2.0806 | 2.1209 | 3.4131 | 3.2419 | 7.6047 | 5.4837 | 16.9428 | 19.0637 | 26.6684 | 32.1522 | 0
-9.9815 | 4.5373 | 1.4673 | 1.2009 | 0.33642 | 1.4019 | 3.0046 | 1.8037 | -5.4442 | -4.2432 | -1.2386 | 0.5651 | -9.9815 | 4.5373 | 1.4673 | 1.2009 | 0.34642 | 1.4019 | 3.0046 | 1.8037 | -5.4442 | -4.2432 | -1.2386 | 0.5651 | 0
17.7361 | 10.5428 | 2.3912 | 2.5868 | 4.956 | 4.1736 | 9.934 | 7.3472 | 28.2789 | 30.8657 | 40.7997 | 48.1469 | 17.7361 | 10.5428 | 2.3912 | 2.5868 | 4.966 | 4.1736 | 9.934 | 7.3472 | 28.2789 | 30.8657 | 40.7997 | 48.1469 | 0
14.6958 | 9.8841 | 2.2899 | 2.4348 | 4.4493 | 3.8696 | 9.174 | 6.7392 | 24.5799 | 27.0147 | 36.1887 | 42.9279 | 14.6958 | 9.8841 | 2.2899 | 2.4348 | 4.4593 | 3.8696 | 9.174 | 6.7392 | 24.5799 | 27.0147 | 36.1887 | 42.9279 | 0
6.9703 | 8.2102 | 2.0323 | 2.0485 | 3.1617 | 3.097 | 7.2426 | 5.1941 | 15.1805 | 17.229 | 24.4716 | 29.6656 | 6.9703 | 8.2102 | 2.0323 | 2.0485 | 3.1717 | 3.097 | 7.2426 | 5.1941 | 15.1805 | 17.229 | 24.4716 | 29.6656 | 0
-2.7649 | 6.1009 | 1.7078 | 1.5618 | 1.5392 | 2.1235 | 4.8088 | 3.247 | 3.336 | 4.8978 | 9.7066 | 12.9536 | -2.7649 | 6.1009 | 1.7078 | 1.5618 | 1.5492 | 2.1235 | 4.8088 | 3.247 | 3.336 | 4.8978 | 9.7066 | 12.9536 | 0
8.3695 | 8.5134 | 2.079 | 2.1185 | 3.3949 | 3.2369 | 7.5924 | 5.4739 | 16.8829 | 19.0014 | 26.5937 | 32.0676 | 8.3695 | 8.5134 | 2.079 | 2.1185 | 3.4049 | 3.2369 | 7.5924 | 5.4739 | 16.8829 | 19.0014 | 26.5937 | 32.0676 | 0
0.31258 | 6.7677 | 1.8104 | 1.7156 | 2.0521 | 2.4313 | 5.5781 | 3.8625 | 7.0803 | 8.7959 | 14.3741 | 18.2366 | 0.31258 | 6.7677 | 1.8104 | 1.7156 | 2.0621 | 2.4313 | 5.5781 | 3.8625 | 7.0803 | 8.7959 | 14.3741 | 18.2366 | 0
14.0166 | 9.7369 | 2.2672 | 2.4008 | 4.3361 | 3.8017 | 9.0041 | 6.6033 | 23.7535 | 26.1543 | 35.1584 | 41.7618 | 14.0166 | 9.7369 | 2.2672 | 2.4008 | 4.3461 | 3.8017 | 9.0041 | 6.6033 | 23.7535 | 26.1543 | 35.1584 | 41.7618 | 0
7.5685 | 8.3398 | 2.0523 | 2.0784 | 3.2614 | 3.1568 | 7.3921 | 5.3137 | 15.9083 | 17.9867 | 25.3788 | 30.6925 | 7.5685 | 8.3398 | 2.0523 | 2.0784 | 3.2714 | 3.1568 | 7.3921 | 5.3137 | 15.9083 | 17.9867 | 25.3788 | 30.6925 | 0
5.9811 | 7.9959 | 1.9994 | 1.9991 | 2.9968 | 2.9981 | 6.9953 | 4.9962 | 13.977 | 15.976 | 22.9713 | 27.9675 | 5.9811 | 7.9959 | 1.9994 | 1.9991 | 3.0068 | 2.9981 | 6.9953 | 4.9962 | 13.977 | 15.976 | 22.9713 | 27.9675 | 0
3.3981 | 7.4363 | 1.9133 | 1.8699 | 2.5664 | 2.7398 | 6.3495 | 4.4796 | 10.8344 | 12.7043 | 19.0538 | 23.5335 | 3.3981 | 7.4363 | 1.9133 | 1.8699 | 2.5764 | 2.7398 | 6.3495 | 4.4796 | 10.8344 | 12.7043 | 19.0538 | 23.5335 | 0
6.2917 | 8.0632 | 2.0097 | 2.0146 | 3.0486 | 3.0292 | 7.0729 | 5.0583 | 14.3549 | 16.3695 | 23.4424 | 28.5007 | 6.2917 | 8.0632 | 2.0097 | 2.0146 | 3.0586 | 3.0292 | 7.0729 | 5.0583 | 14.3549 | 16.3695 | 23.4424 | 28.5007 | 0
3.5617 | 7.4717 | 1.9187 | 1.8781 | 2.5936 | 2.7562 | 6.3904 | 4.5123 | 11.0334 | 12.9115 | 19.3019 | 23.8143 | 3.5617 | 7.4717 | 1.9187 | 1.8781 | 2.6036 | 2.7562 | 6.3904 | 4.5123 | 11.0334 | 12.9115 | 19.3019 | 23.8143 | 0
13.4989 | 9.6248 | 2.25 | 2.3749 | 4.2498 | 3.7499 | 8.8747 | 6.4998 | 23.1236 | 25.4986 | 34.3733 | 40.8731 | 13.4989 | 9.6248 | 2.25 | 2.3749 | 4.2598 | 3.7499 | 8.8747 | 6.4998 | 23.1236 | 25.4986 | 34.3733 | 40.8731 | 0
10.3918 | 8.9516 | 2.1464 | 2.2196 | 3.732 | 3.4392 | 8.098 | 5.8784 | 19.3434 | 21.563 | 29.6609 | 35.5393 | 10.3918 | 8.9516 | 2.1464 | 2.2196 | 3.742 | 3.4392 | 8.098 | 5.8784 | 19.3434 | 21.563 | 29.6609 | 35.5393 | 0
1.0548 | 6.9285 | 1.8352 | 1.7527 | 2.1758 | 2.5055 | 5.7637 | 4.011 | 7.9833 | 9.7361 | 15.4998 | 19.5107 | 1.0548 | 6.9285 | 1.8352 | 1.7527 | 2.1858 | 2.5055 | 5.7637 | 4.011 | 7.9833 | 9.7361 | 15.4998 | 19.5107 | 0
16.2026 | 10.2106 | 2.3401 | 2.5101 | 4.7004 | 4.0203 | 9.5506 | 7.0405 | 26.4131 | 28.9233 | 38.4739 | 45.5144 | 16.2026 | 10.2106 | 2.3401 | 2.5101 | 4.7104 | 4.0203 | 9.5506 | 7.0405 | 26.4131 | 28.9233 | 38.4739 | 45.5144 | 0
8.5304 | 8.5483 | 2.0843 | 2.1265 | 3.4217 | 3.253 | 7.6326 | 5.5061 | 17.0786 | 19.2052 | 26.8378 | 32.3438 | 8.5304 | 8.5483 | 2.0843 | 2.1265 | 3.4317 | 3.253 | 7.6326 | 5.5061 | 17.0786 | 19.2052 | 26.8378 | 32.3438 | 0
7.3385 | 8.29 | 2.0446 | 2.0669 | 3.2231 | 3.1339 | 7.3346 | 5.2677 | 15.6285 | 17.6955 | 25.0301 | 30.2978 | 7.3385 | 8.29 | 2.0446 | 2.0669 | 3.2331 | 3.1339 | 7.3346 | 5.2677 | 15.6285 | 17.6955 | 25.0301 | 30.2978 | 0
-11.3977 | 4.2305 | 1.4201 | 1.1301 | 0.10039 | 1.2602 | 2.6506 | 1.5205 | -7.1672 | -6.0371 | -3.3865 | -1.866 | -11.3977 | 4.2305 | 1.4201 | 1.1301 | 0.11039 | 1.2602 | 2.6506 | 1.5205 | -7.1672 | -6.0371 | -3.3865 | -1.866 | 0
4.3995 | 7.6532 | 1.9466 | 1.92 | 2.7332 | 2.8399 | 6.5999 | 4.6799 | 12.0527 | 13.9727 | 20.5726 | 25.2525 | 4.3995 | 7.6532 | 1.9466 | 1.92 | 2.7432 | 2.8399 | 6.5999 | 4.6799 | 12.0527 | 13.9727 | 20.5726 | 25.2525 | 0
14.4103 | 9.8222 | 2.2803 | 2.4205 | 4.4017 | 3.841 | 9.1026 | 6.6821 | 24.2325 | 26.6531 | 35.7556 | 42.4377 | 14.4103 | 9.8222 | 2.2803 | 2.4205 | 4.4117 | 3.841 | 9.1026 | 6.6821 | 24.2325 | 26.6531 | 35.7556 | 42.4377 | 0
-4.8914 | 5.6402 | 1.637 | 1.4554 | 1.1848 | 1.9109 | 4.2771 | 2.8217 | 0.74876 | 2.2042 | 6.4813 | 9.3031 | -4.8914 | 5.6402 | 1.637 | 1.4554 | 1.1948 | 1.9109 | 4.2771 | 2.8217 | 0.74876 | 2.2042 | 6.4813 | 9.3031 | 0
15.1442 | 9.9812 | 2.3048 | 2.4572 | 4.524 | 3.9144 | 9.2861 | 6.8288 | 25.1255 | 27.5827 | 36.8687 | 43.6976 | 15.1442 | 9.9812 | 2.3048 | 2.4572 | 4.534 | 3.9144 | 9.2861 | 6.8288 | 25.1255 | 27.5827 | 36.8687 | 43.6976 | 0
6.8025 | 8.1739 | 2.0267 | 2.0401 | 3.1337 | 3.0802 | 7.2006 | 5.1605 | 14.9763 | 17.0165 | 24.2171 | 29.3776 | 6.8025 | 8.1739 | 2.0267 | 2.0401 | 3.1437 | 3.0802 | 7.2006 | 5.1605 | 14.9763 | 17.0165 | 24.2171 | 29.3776 | 0
7.5565 | 8.3372 | 2.0519 | 2.0778 | 3.2594 | 3.1556 | 7.3891 | 5.3113 | 15.8937 | 17.9716 | 25.3607 | 30.672 | 7.5565 | 8.3372 | 2.0519 | 2.0778 | 3.2694 | 3.1556 | 7.3891 | 5.3113 | 15.8937 | 17.9716 | 25.3607 | 30.672 | 0
7.1078 | 8.24 | 2.0369 | 2.0554 | 3.1846 | 3.1108 | 7.2769 | 5.2216 | 15.3478 | 17.4032 | 24.6802 | 29.9017 | 7.1078 | 8.24 | 2.0369 | 2.0554 | 3.1946 | 3.1108 | 7.2769 | 5.2216 | 15.3478 | 17.4032 | 24.6802 | 29.9017 | 0
5.4872 | 7.8889 | 1.9829 | 1.9744 | 2.9145 | 2.9487 | 6.8718 | 4.8974 | 13.3761 | 15.3505 | 22.2223 | 27.1197 | 5.4872 | 7.8889 | 1.9829 | 1.9744 | 2.9245 | 2.9487 | 6.8718 | 4.8974 | 13.3761 | 15.3505 | 22.2223 | 27.1197 | 0
-0.20801 | 6.6549 | 1.7931 | 1.6896 | 1.9653 | 2.3792 | 5.448 | 3.7584 | 6.4469 | 8.1365 | 13.5845 | 17.3429 | -0.20801 | 6.6549 | 1.7931 | 1.6896 | 1.9753 | 2.3792 | 5.448 | 3.7584 | 6.4469 | 8.1365 | 13.5845 | 17.3429 | 0
17.5186 | 10.4957 | 2.384 | 2.5759 | 4.9198 | 4.1519 | 9.8796 | 7.3037 | 28.0143 | 30.5902 | 40.4698 | 47.7735 | 17.5186 | 10.4957 | 2.384 | 2.5759 | 4.9298 | 4.1519 | 9.8796 | 7.3037 | 28.0143 | 30.5902 | 40.4698 | 47.7735 | 0
10.1071 | 8.8899 | 2.1369 | 2.2054 | 3.6845 | 3.4107 | 8.0268 | 5.8214 | 18.997 | 21.2024 | 29.2292 | 35.0506 | 10.1071 | 8.8899 | 2.1369 | 2.2054 | 3.6945 | 3.4107 | 8.0268 | 5.8214 | 18.997 | 21.2024 | 29.2292 | 35.0506 | 0
8.5568 | 8.554 | 2.0852 | 2.1278 | 3.4261 | 3.2557 | 7.6392 | 5.5114 | 17.1107 | 19.2386 | 26.8777 | 32.3891 | 8.5568 | 8.554 | 2.0852 | 2.1278 | 3.4361 | 3.2557 | 7.6392 | 5.5114 | 17.1107 | 19.2386 | 26.8777 | 32.3891 | 0
6.2378 | 8.0515 | 2.0079 | 2.0119 | 3.0396 | 3.0238 | 7.0594 | 5.0476 | 14.2893 | 16.3012 | 23.3606 | 28.4082 | 6.2378 | 8.0515 | 2.0079 | 2.0119 | 3.0496 | 3.0238 | 7.0594 | 5.0476 | 14.2893 | 16.3012 | 23.3606 | 28.4082 | 0
-0.17002 | 6.6632 | 1.7943 | 1.6915 | 1.9717 | 2.383 | 5.4575 | 3.766 | 6.4931 | 8.1846 | 13.6421 | 17.4081 | -0.17002 | 6.6632 | 1.7943 | 1.6915 | 1.9817 | 2.383 | 5.4575 | 3.766 | 6.4931 | 8.1846 | 13.6421 | 17.4081 | 0
14.1065 | 9.7564 | 2.2702 | 2.4053 | 4.3511 | 3.8106 | 9.0266 | 6.6213 | 23.8629 | 26.2682 | 35.2948 | 41.9161 | 14.1065 | 9.7564 | 2.2702 | 2.4053 | 4.3611 | 3.8106 | 9.0266 | 6.6213 | 23.8629 | 26.2682 | 35.2948 | 41.9161 | 0
3.8564 | 7.5356 | 1.9285 | 1.8928 | 2.6427 | 2.7856 | 6.4641 | 4.5713 | 11.392 | 13.2848 | 19.7489 | 24.3202 | 3.8564 | 7.5356 | 1.9285 | 1.8928 | 2.6527 | 2.7856 | 6.4641 | 4.5713 | 11.392 | 13.2848 | 19.7489 | 24.3202 | 0
-3.938 | 5.8468 | 1.6687 | 1.5031 | 1.3437 | 2.0062 | 4.5155 | 3.0124 | 1.9088 | 3.4119 | 7.9273 | 10.9397 | -3.938 | 5.8468 | 1.6687 | 1.5031 | 1.3537 | 2.0062 | 4.5155 | 3.0124 | 1.9088 | 3.4119 | 7.9273 | 10.9397 | 0
8.0713 | 8.4488 | 2.069 | 2.1036 | 3.3452 | 3.2071 | 7.5178 | 5.4143 | 16.5201 | 18.6237 | 26.1415 | 31.5558 | 8.0713 | 8.4488 | 2.069 | 2.1036 | 3.3552 | 3.2071 | 7.5178 | 5.4143 | 16.5201 | 18.6237 | 26.1415 | 31.5558 | 0
-3.3537 | 5.9734 | 1.6882 | 1.5323 | 1.4411 | 2.0646 | 4.6616 | 3.1293 | 2.6197 | 4.152 | 8.8136 | 11.9428 | -3.3537 | 5.9734 | 1.6882 | 1.5323 | 1.4511 | 2.0646 | 4.6616 | 3.1293 | 2.6197 | 4.152 | 8.8136 | 11.9428 | 0
-2.1228 | 6.2401 | 1.7292 | 1.5939 | 1.6462 | 2.1877 | 4.9693 | 3.3754 | 4.1173 | 5.7111 | 10.6804 | 14.0558 | -2.1228 | 6.2401 | 1.7292 | 1.5939 | 1.6562 | 2.1877 | 4.9693 | 3.3754 | 4.1173 | 5.7111 | 10.6804 | 14.0558 | 0
3.4464 | 7.4467 | 1.9149 | 1.8723 | 2.5744 | 2.7446 | 6.3616 | 4.4893 | 10.8932 | 12.7655 | 19.1271 | 23.6164 | 3.4464 | 7.4467 | 1.9149 | 1.8723 | 2.5844 | 2.7446 | 6.3616 | 4.4893 | 10.8932 | 12.7655 | 19.1271 | 23.6164 | 0
9.7406 | 8.8105 | 2.1247 | 2.187 | 3.6234 | 3.3741 | 7.9351 | 5.7481 | 18.551 | 20.7381 | 28.6732 | 34.4213 | 9.7406 | 8.8105 | 2.1247 | 2.187 | 3.6334 | 3.3741 | 7.9351 | 5.7481 | 18.551 | 20.7381 | 28.6732 | 34.4213 | 0
14.3409 | 9.8072 | 2.278 | 2.417 | 4.3902 | 3.8341 | 9.0852 | 6.6682 | 24.1481 | 26.5652 | 35.6504 | 42.3186 | 14.3409 | 9.8072 | 2.278 | 2.417 | 4.4002 | 3.8341 | 9.0852 | 6.6682 | 24.1481 | 26.5652 | 35.6504 | 42.3186 | 0
10.4801 | 8.9707 | 2.1493 | 2.224 | 3.7467 | 3.448 | 8.12 | 5.896 | 19.4508 | 21.6748 | 29.7948 | 35.6908 | 10.4801 | 8.9707 | 2.1493 | 2.224 | 3.7567 | 3.448 | 8.12 | 5.896 | 19.4508 | 21.6748 | 29.7948 | 35.6908 | 0
1.9422 | 7.1208 | 1.8647 | 1.7971 | 2.3237 | 2.5942 | 5.9855 | 4.1884 | 9.063 | 10.8601 | 16.8456 | 21.0341 | 1.9422 | 7.1208 | 1.8647 | 1.7971 | 2.3337 | 2.5942 | 5.9855 | 4.1884 | 9.063 | 10.8601 | 16.8456 | 21.0341 | 0
-3.5251 | 5.9362 | 1.6825 | 1.5237 | 1.4125 | 2.0475 | 4.6187 | 3.095 | 2.4111 | 3.9349 | 8.5536 | 11.6486 | -3.5251 | 5.9362 | 1.6825 | 1.5237 | 1.4225 | 2.0475 | 4.6187 | 3.095 | 2.4111 | 3.9349 | 8.5536 | 11.6486 | 0
6.3941 | 8.0854 | 2.0131 | 2.0197 | 3.0657 | 3.0394 | 7.0985 | 5.0788 | 14.4795 | 16.4992 | 23.5978 | 28.6766 | 6.3941 | 8.0854 | 2.0131 | 2.0197 | 3.0757 | 3.0394 | 7.0985 | 5.0788 | 14.4795 | 16.4992 | 23.5978 | 28.6766 | 0
8.1827 | 8.4729 | 2.0728 | 2.1091 | 3.3638 | 3.2183 | 7.5457 | 5.4365 | 16.6556 | 18.7647 | 26.3104 | 31.7469 | 8.1827 | 8.4729 | 2.0728 | 2.1091 | 3.3738 | 3.2183 | 7.5457 | 5.4365 | 16.6556 | 18.7647 | 26.3104 | 31.7469 | 0
13.4254 | 9.6088 | 2.2475 | 2.3713 | 4.2376 | 3.7425 | 8.8563 | 6.4851 | 23.0342 | 25.4055 | 34.2618 | 40.7469 | 13.4254 | 9.6088 | 2.2475 | 2.3713 | 4.2476 | 3.7425 | 8.8563 | 6.4851 | 23.0342 | 25.4055 | 34.2618 | 40.7469 | 0
12.781 | 9.4692 | 2.226 | 2.339 | 4.1302 | 3.6781 | 8.6952 | 6.3562 | 22.2502 | 24.5892 | 33.2844 | 39.6406 | 12.781 | 9.4692 | 2.226 | 2.339 | 4.1402 | 3.6781 | 8.6952 | 6.3562 | 22.2502 | 24.5892 | 33.2844 | 39.6406 | 0
5.32 | 7.8527 | 1.9773 | 1.966 | 2.8867 | 2.932 | 6.83 | 4.864 | 13.1726 | 15.1386 | 21.9686 | 26.8326 | 5.32 | 7.8527 | 1.9773 | 1.966 | 2.8967 | 2.932 | 6.83 | 4.864 | 13.1726 | 15.1386 | 21.9686 | 26.8326 | 0
0.36357 | 6.7788 | 1.8121 | 1.7182 | 2.0606 | 2.4364 | 5.5909 | 3.8727 | 7.1423 | 8.8605 | 14.4514 | 18.3241 | 0.36357 | 6.7788 | 1.8121 | 1.7182 | 2.0706 | 2.4364 | 5.5909 | 3.8727 | 7.1423 | 8.8605 | 14.4514 | 18.3241 | 0
4.4875 | 7.6723 | 1.9496 | 1.9244 | 2.7479 | 2.8487 | 6.6219 | 4.6975 | 12.1597 | 14.0841 | 20.706 | 25.4035 | 4.4875 | 7.6723 | 1.9496 | 1.9244 | 2.7579 | 2.8487 | 6.6219 | 4.6975 | 12.1597 | 14.0841 | 20.706 | 25.4035 | 0
16.3134 | 10.2346 | 2.3438 | 2.5157 | 4.7189 | 4.0313 | 9.5783 | 7.0627 | 26.548 | 29.0636 | 38.642 | 45.7047 | 16.3134 | 10.2346 | 2.3438 | 2.5157 | 4.7289 | 4.0313 | 9.5783 | 7.0627 | 26.548 | 29.0636 | 38.642 | 45.7047 | 0
4.2492 | 7.6207 | 1.9416 | 1.9125 | 2.7082 | 2.8249 | 6.5623 | 4.6498 | 11.8698 | 13.7823 | 20.3446 | 24.9944 | 4.2492 | 7.6207 | 1.9416 | 1.9125 | 2.7182 | 2.8249 | 6.5623 | 4.6498 | 11.8698 | 13.7823 | 20.3446 | 24.9944 | 0
3.7637 | 7.5155 | 1.9255 | 1.8882 | 2.6273 | 2.7764 | 6.4409 | 4.5527 | 11.2792 | 13.1674 | 19.6083 | 24.161 | 3.7637 | 7.5155 | 1.9255 | 1.8882 | 2.6373 | 2.7764 | 6.4409 | 4.5527 | 11.2792 | 13.1674 | 19.6083 | 24.161 | 0
-1.4859 | 6.3781 | 1.7505 | 1.6257 | 1.7524 | 2.2514 | 5.1285 | 3.5028 | 4.8922 | 6.5179 | 11.6464 | 15.1492 | -1.4859 | 6.3781 | 1.7505 | 1.6257 | 1.7624 | 2.2514 | 5.1285 | 3.5028 | 4.8922 | 6.5179 | 11.6464 | 15.1492 | 0
13.1201 | 9.5427 | 2.2373 | 2.356 | 4.1867 | 3.712 | 8.78 | 6.424 | 22.6628 | 25.0188 | 33.7988 | 40.2228 | 13.1201 | 9.5427 | 2.2373 | 2.356 | 4.1967 | 3.712 | 8.78 | 6.424 | 22.6628 | 25.0188 | 33.7988 | 40.2228 | 0
1.2847 | 6.9783 | 1.8428 | 1.7642 | 2.2141 | 2.5285 | 5.8212 | 4.0569 | 8.263 | 10.0273 | 15.8484 | 19.9054 | 1.2847 | 6.9783 | 1.8428 | 1.7642 | 2.2241 | 2.5285 | 5.8212 | 4.0569 | 8.263 | 10.0273 | 15.8484 | 19.9054 | 0
10.1324 | 8.8954 | 2.1377 | 2.2066 | 3.6887 | 3.4132 | 8.0331 | 5.8265 | 19.0278 | 21.2344 | 29.2675 | 35.094 | 10.1324 | 8.8954 | 2.1377 | 2.2066 | 3.6987 | 3.4132 | 8.0331 | 5.8265 | 19.0278 | 21.2344 | 29.2675 | 35.094 | 0
19.078 | 10.8336 | 2.4359 | 2.6539 | 5.1797 | 4.3078 | 10.2695 | 7.6156 | 29.9115 | 32.5654 | 42.8349 | 50.4505 | 19.078 | 10.8336 | 2.4359 | 2.6539 | 5.1897 | 4.3078 | 10.2695 | 7.6156 | 29.9115 | 32.5654 | 42.8349 | 50.4505 | 0
14.4903 | 9.8396 | 2.283 | 2.4245 | 4.4151 | 3.849 | 9.1226 | 6.6981 | 24.3299 | 26.7544 | 35.877 | 42.5751 | 14.4903 | 9.8396 | 2.283 | 2.4245 | 4.4251 | 3.849 | 9.1226 | 6.6981 | 24.3299 | 26.7544 | 35.877 | 42.5751 | 0
1.3037 | 6.9825 | 1.8435 | 1.7652 | 2.2173 | 2.5304 | 5.8259 | 4.0607 | 8.2862 | 10.0514 | 15.8773 | 19.9381 | 1.3037 | 6.9825 | 1.8435 | 1.7652 | 2.2273 | 2.5304 | 5.8259 | 4.0607 | 8.2862 | 10.0514 | 15.8773 | 19.9381 | 0
4.5343 | 7.6824 | 1.9511 | 1.9267 | 2.7557 | 2.8534 | 6.6336 | 4.7069 | 12.2167 | 14.1434 | 20.777 | 25.4838 | 4.5343 | 7.6824 | 1.9511 | 1.9267 | 2.7657 | 2.8534 | 6.6336 | 4.7069 | 12.2167 | 14.1434 | 20.777 | 25.4838 | 0
8.9171 | 8.632 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5834 | 17.5492 | 19.695 | 27.4243 | 33.0077 | 8.9171 | 8.632 | 2.0972 | 2.1459 | 3.4962 | 3.2917 | 7.7293 | 5.5834 | 17.5492 | 19.695 | 27.4243 | 33.0077 | 0
4.2696 | 7.6251 | 1.9423 | 1.9135 | 2.7116 | 2.827 | 6.5674 | 4.6539 | 11.8947 | 13.8082 | 20.3756 | 25.0295 | 4.2696 | 7.6251 | 1.9423 | 1.9135 | 2.7216 | 2.827 | 6.5674 | 4.6539 | 11.8947 | 13.8082 | 20.3756 | 25.0295 | 0
1.8769 | 7.1067 | 1.8626 | 1.7938 | 2.3128 | 2.5877 | 5.9692 | 4.1754 | 8.9835 | 10.7774 | 16.7466 | 20.922 | 1.8769 | 7.1067 | 1.8626 | 1.7938 | 2.3228 | 2.5877 | 5.9692 | 4.1754 | 8.9835 | 10.7774 | 16.7466 | 20.922 | 0
1.2769 | 6.9767 | 1.8426 | 1.7638 | 2.2128 | 2.5277 | 5.8192 | 4.0554 | 8.2536 | 10.0174 | 15.8367 | 19.8921 | 1.2769 | 6.9767 | 1.8426 | 1.7638 | 2.2228 | 2.5277 | 5.8192 | 4.0554 | 8.2536 | 10.0174 | 15.8367 | 19.8921 | 0
4.4293 | 7.6597 | 1.9476 | 1.9215 | 2.7382 | 2.8429 | 6.6073 | 4.6859 | 12.089 | 14.0105 | 20.6178 | 25.3037 | 4.4293 | 7.6597 | 1.9476 | 1.9215 | 2.7482 | 2.8429 | 6.6073 | 4.6859 | 12.089 | 14.0105 | 20.6178 | 25.3037 | 0
-0.71252 | 6.5456 | 1.7762 | 1.6644 | 1.8812 | 2.3287 | 5.3219 | 3.6575 | 5.8331 | 7.4975 | 12.8193 | 16.4768 | -0.71252 | 6.5456 | 1.7762 | 1.6644 | 1.8912 | 2.3287 | 5.3219 | 3.6575 | 5.8331 | 7.4975 | 12.8193 | 16.4768 | 0
0.56209 | 6.8218 | 1.8187 | 1.7281 | 2.0937 | 2.4562 | 5.6405 | 3.9124 | 7.3839 | 9.112 | 14.7525 | 18.6649 | 0.56209 | 6.8218 | 1.8187 | 1.7281 | 2.1037 | 2.4562 | 5.6405 | 3.9124 | 7.3839 | 9.112 | 14.7525 | 18.6649 | 0
3.2537 | 7.405 | 1.9085 | 1.8627 | 2.5423 | 2.7254 | 6.3134 | 4.4507 | 10.6587 | 12.5214 | 18.8348 | 23.2856 | 3.2537 | 7.405 | 1.9085 | 1.8627 | 2.5523 | 2.7254 | 6.3134 | 4.4507 | 10.6587 | 12.5214 | 18.8348 | 23.2856 | 0
4.564 | 7.6889 | 1.9521 | 1.9282 | 2.7607 | 2.8564 | 6.641 | 4.7128 | 12.2529 | 14.1811 | 20.8221 | 25.5349 | 4.564 | 7.6889 | 1.9521 | 1.9282 | 2.7707 | 2.8564 | 6.641 | 4.7128 | 12.2529 | 14.1811 | 20.8221 | 25.5349 | 0
17.5236 | 10.4968 | 2.3841 | 2.5762 | 4.9206 | 4.1524 | 9.8809 | 7.3047 | 28.0204 | 30.5966 | 40.4775 | 47.7823 | 17.5236 | 10.4968 | 2.3841 | 2.5762 | 4.9306 | 4.1524 | 9.8809 | 7.3047 | 28.0204 | 30.5966 | 40.4775 | 47.7823 | 0
8.2391 | 8.4851 | 2.0746 | 2.112 | 3.3732 | 3.2239 | 7.5598 | 5.4478 | 16.7242 | 18.8362 | 26.396 | 31.8438 | 8.2391 | 8.4851 | 2.0746 | 2.112 | 3.3832 | 3.2239 | 7.5598 | 5.4478 | 16.7242 | 18.8362 | 26.396 | 31.8438 | 0
11.3647 | 9.1623 | 2.1788 | 2.2682 | 3.8941 | 3.5365 | 8.3412 | 6.0729 | 20.527 | 22.7953 | 31.1364 | 37.2094 | 11.3647 | 9.1623 | 2.1788 | 2.2682 | 3.9041 | 3.5365 | 8.3412 | 6.0729 | 20.527 | 22.7953 | 31.1364 | 37.2094 | 0
-1.6549 | 6.3414 | 1.7448 | 1.6173 | 1.7242 | 2.2345 | 5.0863 | 3.469 | 4.6866 | 6.3038 | 11.3901 | 14.8591 | -1.6549 | 6.3414 | 1.7448 | 1.6173 | 1.7342 | 2.2345 | 5.0863 | 3.469 | 4.6866 | 6.3038 | 11.3901 | 14.8591 | 0
8.9418 | 8.6374 | 2.0981 | 2.1471 | 3.4903 | 3.2942 | 7.7354 | 5.5884 | 17.5791 | 19.7262 | 27.4617 | 33.05 | 8.9418 | 8.6374 | 2.0981 | 2.1471 | 3.5003 | 3.2942 | 7.7354 | 5.5884 | 17.5791 | 19.7262 | 27.4617 | 33.05 | 0
11.8561 | 9.2688 | 2.1952 | 2.2928 | 3.976 | 3.5856 | 8.464 | 6.1712 | 21.1249 | 23.4177 | 31.8817 | 38.053 | 11.8561 | 9.2688 | 2.1952 | 2.2928 | 3.986 | 3.5856 | 8.464 | 6.1712 | 21.1249 | 23.4177 | 31.8817 | 38.053 | 0
10.4949 | 8.9739 | 2.1498 | 2.2247 | 3.7492 | 3.4495 | 8.1237 | 5.899 | 19.4688 | 21.6936 | 29.8173 | 35.7163 | 10.4949 | 8.9739 | 2.1498 | 2.2247 | 3.7592 | 3.4495 | 8.1237 | 5.899 | 19.4688 | 21.6936 | 29.8173 | 35.7163 | 0
10.916 | 9.0651 | 2.1639 | 2.2458 | 3.8193 | 3.4916 | 8.229 | 5.9832 | 19.9811 | 22.2269 | 30.4559 | 36.4391 | 10.916 | 9.0651 | 2.1639 | 2.2458 | 3.8293 | 3.4916 | 8.229 | 5.9832 | 19.9811 | 22.2269 | 30.4559 | 36.4391 | 0
9.4413 | 8.7456 | 2.1147 | 2.1721 | 3.5736 | 3.3441 | 7.8603 | 5.6883 | 18.1869 | 20.359 | 28.2193 | 33.9076 | 9.4413 | 8.7456 | 2.1147 | 2.1721 | 3.5836 | 3.3441 | 7.8603 | 5.6883 | 18.1869 | 20.359 | 28.2193 | 33.9076 | 0
3.8479 | 7.5337 | 1.9283 | 1.8924 | 2.6413 | 2.7848 | 6.462 | 4.5696 | 11.3817 | 13.2741 | 19.7361 | 24.3056 | 3.8479 | 7.5337 | 1.9283 | 1.8924 | 2.6513 | 2.7848 | 6.462 | 4.5696 | 11.3817 | 13.2741 | 19.7361 | 24.3056 | 0
0.12473 | 6.727 | 1.8042 | 1.7062 | 2.0208 | 2.4125 | 5.5312 | 3.8249 | 6.8518 | 8.558 | 14.0892 | 17.9141 | 0.12473 | 6.727 | 1.8042 | 1.7062 | 2.0308 | 2.4125 | 5.5312 | 3.8249 | 6.8518 | 8.558 | 14.0892 | 17.9141 | 0
15.3826 | 10.0329 | 2.3128 | 2.4691 | 4.5638 | 3.9383 | 9.3457 | 6.8765 | 25.4155 | 27.8847 | 37.2303 | 44.1068 | 15.3826 | 10.0329 | 2.3128 | 2.4691 | 4.5738 | 3.9383 | 9.3457 | 6.8765 | 25.4155 | 27.8847 | 37.2303 | 44.1068 | 0
5.5747 | 7.9078 | 1.9858 | 1.9787 | 2.9291 | 2.9575 | 6.8937 | 4.9149 | 13.4825 | 15.4613 | 22.3549 | 27.2699 | 5.5747 | 7.9078 | 1.9858 | 1.9787 | 2.9391 | 2.9575 | 6.8937 | 4.9149 | 13.4825 | 15.4613 | 22.3549 | 27.2699 | 0
7.5314 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8632 | 17.9398 | 25.3227 | 30.629 | 7.5314 | 8.3318 | 2.051 | 2.0766 | 3.2652 | 3.1531 | 7.3829 | 5.3063 | 15.8632 | 17.9398 | 25.3227 | 30.629 | 0
5.6536 | 7.9249 | 1.9885 | 1.9827 | 2.9423 | 2.9654 | 6.9134 | 4.9307 | 13.5786 | 15.5612 | 22.4746 | 27.4054 | 5.6536 | 7.9249 | 1.9885 | 1.9827 | 2.9523 | 2.9654 | 6.9134 | 4.9307 | 13.5786 | 15.5612 | 22.4746 | 27.4054 | 0
7.9005 | 8.4118 | 2.0633 | 2.095 | 3.3167 | 3.19 | 7.4751 | 5.3801 | 16.3122 | 18.4073 | 25.8824 | 31.2625 | 7.9005 | 8.4118 | 2.0633 | 2.095 | 3.3267 | 3.19 | 7.4751 | 5.3801 | 16.3122 | 18.4073 | 25.8824 | 31.2625 | 0
2.7503 | 7.2959 | 1.8917 | 1.8375 | 2.4584 | 2.675 | 6.1876 | 4.3501 | 10.0462 | 11.8837 | 18.0713 | 22.4213 | 2.7503 | 7.2959 | 1.8917 | 1.8375 | 2.4684 | 2.675 | 6.1876 | 4.3501 | 10.0462 | 11.8837 | 18.0713 | 22.4213 | 0
15.9912 | 10.1648 | 2.333 | 2.4996 | 4.6652 | 3.9991 | 9.4978 | 6.9982 | 26.156 | 28.6556 | 38.1534 | 45.1516 | 15.9912 | 10.1648 | 2.333 | 2.4996 | 4.6752 | 3.9991 | 9.4978 | 6.9982 | 26.156 | 28.6556 | 38.1534 | 45.1516 | 0
3.5741 | 7.4744 | 1.9191 | 1.8787 | 2.5957 | 2.7574 | 6.3935 | 4.5148 | 11.0485 | 12.9272 | 19.3207 | 23.8356 | 3.5741 | 7.4744 | 1.9191 | 1.8787 | 2.6057 | 2.7574 | 6.3935 | 4.5148 | 11.0485 | 12.9272 | 19.3207 | 23.8356 | 0
8.2161 | 8.4802 | 2.0739 | 2.1108 | 3.3693 | 3.2216 | 7.554 | 5.4432 | 16.6962 | 18.8071 | 26.3611 | 31.8043 | 8.2161 | 8.4802 | 2.0739 | 2.1108 | 3.3793 | 3.2216 | 7.554 | 5.4432 | 16.6962 | 18.8071 | 26.3611 | 31.8043 | 0
11.5303 | 9.1982 | 2.1843 | 2.2765 | 3.9217 | 3.553 | 8.3826 | 6.1061 | 20.7286 | 23.0051 | 31.3877 | 37.4937 | 11.5303 | 9.1982 | 2.1843 | 2.2765 | 3.9317 | 3.553 | 8.3826 | 6.1061 | 20.7286 | 23.0051 | 31.3877 | 37.4937 | 0
9.1597 | 8.6846 | 2.1053 | 2.158 | 3.5266 | 3.316 | 7.7899 | 5.6319 | 17.8443 | 20.0023 | 27.7923 | 33.4242 | 9.1597 | 8.6846 | 2.1053 | 2.158 | 3.5366 | 3.316 | 7.7899 | 5.6319 | 17.8443 | 20.0023 | 27.7923 | 33.4242 | 0
12.984 | 9.5132 | 2.2328 | 2.3492 | 4.164 | 3.6984 | 8.746 | 6.3968 | 22.4972 | 24.8464 | 33.5924 | 39.9892 | 12.984 | 9.5132 | 2.2328 | 2.3492 | 4.174 | 3.6984 | 8.746 | 6.3968 | 22.4972 | 24.8464 | 33.5924 | 39.9892 | 0
18.7844 | 10.7699 | 2.4261 | 2.6392 | 5.1307 | 4.2784 | 10.1961 | 7.5569 | 29.5543 | 32.1935 | 42.3896 | 49.9465 | 18.7844 | 10.7699 | 2.4261 | 2.6392 | 5.1407 | 4.2784 | 10.1961 | 7.5569 | 29.5543 | 32.1935 | 42.3896 | 49.9465 | 0
9.9286 | 8.8512 | 2.131 | 2.1964 | 3.6548 | 3.3929 | 7.9822 | 5.7857 | 18.7799 | 20.9763 | 28.9585 | 34.7442 | 9.9286 | 8.8512 | 2.131 | 2.1964 | 3.6648 | 3.3929 | 7.9822 | 5.7857 | 18.7799 | 20.9763 | 28.9585 | 34.7442 | 0
2.0856 | 7.1519 | 1.8695 | 1.8043 | 2.3476 | 2.6086 | 6.0214 | 4.2171 | 9.2375 | 11.0418 | 17.0632 | 21.2803 | 2.0856 | 7.1519 | 1.8695 | 1.8043 | 2.3576 | 2.6086 | 6.0214 | 4.2171 | 9.2375 | 11.0418 | 17.0632 | 21.2803 | 0
7.7123 | 8.371 | 2.0571 | 2.0856 | 3.2854 | 3.1712 | 7.4281 | 5.3425 | 16.0833 | 18.169 | 25.5971 | 30.9395 | 7.7123 | 8.371 | 2.0571 | 2.0856 | 3.2954 | 3.1712 | 7.4281 | 5.3425 | 16.0833 | 18.169 | 25.5971 | 30.9395 | 0
4.3418 | 7.6407 | 1.9447 | 1.9171 | 2.7236 | 2.8342 | 6.5855 | 4.6684 | 11.9825 | 13.8996 | 20.4851 | 25.1535 | 4.3418 | 7.6407 | 1.9447 | 1.9171 | 2.7336 | 2.8342 | 6.5855 | 4.6684 | 11.9825 | 13.8996 | 20.4851 | 25.1535 | 0
11.026 | 9.089 | 2.1675 | 2.2513 | 3.8377 | 3.5026 | 8.2565 | 6.0052 | 20.115 | 22.3663 | 30.6228 | 36.628 | 11.026 | 9.089 | 2.1675 | 2.2513 | 3.8477 | 3.5026 | 8.2565 | 6.0052 | 20.115 | 22.3663 | 30.6228 | 36.628 | 0
17.0012 | 10.3836 | 2.3667 | 2.5501 | 4.8335 | 4.1001 | 9.7503 | 7.2002 | 27.3849 | 29.9349 | 39.6852 | 46.8855 | 17.0012 | 10.3836 | 2.3667 | 2.5501 | 4.8435 | 4.1001 | 9.7503 | 7.2002 | 27.3849 | 29.9349 | 39.6852 | 46.8855 | 0
2.8353 | 7.3143 | 1.8945 | 1.8418 | 2.4726 | 2.6835 | 6.2088 | 4.3671 | 10.1496 | 11.9914 | 18.2002 | 22.5673 | 2.8353 | 7.3143 | 1.8945 | 1.8418 | 2.4826 | 2.6835 | 6.2088 | 4.3671 | 10.1496 | 11.9914 | 18.2002 | 22.5673 | 0
2.9314 | 7.3351 | 1.8977 | 1.8466 | 2.4886 | 2.6931 | 6.2329 | 4.3863 | 10.2666 | 12.1132 | 18.346 | 22.7323 | 2.9314 | 7.3351 | 1.8977 | 1.8466 | 2.4986 | 2.6931 | 6.2329 | 4.3863 | 10.2666 | 12.1132 | 18.346 | 22.7323 | 0
0.2458 | 6.7533 | 1.8082 | 1.7123 | 2.041 | 2.4246 | 5.5615 | 3.8492 | 6.9991 | 8.7114 | 14.2728 | 18.122 | 0.2458 | 6.7533 | 1.8082 | 1.7123 | 2.051 | 2.4246 | 5.5615 | 3.8492 | 6.9991 | 8.7114 | 14.2728 | 18.122 | 0
6.4896 | 8.1061 | 2.0163 | 2.0245 | 3.0816 | 3.049 | 7.1224 | 5.0979 | 14.5957 | 16.6202 | 23.7426 | 28.8405 | 6.4896 | 8.1061 | 2.0163 | 2.0245 | 3.0916 | 3.049 | 7.1224 | 5.0979 | 14.5957 | 16.6202 | 23.7426 | 28.8405 | 0
-6.0201 | 5.3956 | 1.5993 | 1.399 | 0.99665 | 1.798 | 3.995 | 2.596 | -0.62448 | 0.77452 | 4.7695 | 7.3655 | -6.0201 | 5.3956 | 1.5993 | 1.399 | 1.0066 | 1.798 | 3.995 | 2.596 | -0.62448 | 0.77452 | 4.7695 | 7.3655 | 0
3.3036 | 7.4158 | 1.9101 | 1.8652 | 2.5506 | 2.7304 | 6.3259 | 4.4607 | 10.7194 | 12.5846 | 18.9105 | 23.3712 | 3.3036 | 7.4158 | 1.9101 | 1.8652 | 2.5606 | 2.7304 | 6.3259 | 4.4607 | 10.7194 | 12.5846 | 18.9105 | 23.3712 | 0
8.8664 | 8.621 | 2.0955 | 2.1433 | 3.4777 | 3.2866 | 7.7166 | 5.5733 | 17.4874 | 19.6307 | 27.3473 | 32.9206 | 8.8664 | 8.621 | 2.0955 | 2.1433 | 3.4877 | 3.2866 | 7.7166 | 5.5733 | 17.4874 | 19.6307 | 27.3473 | 32.9206 | 0
13.6777 | 9.6635 | 2.2559 | 2.3839 | 4.2796 | 3.7678 | 8.9194 | 6.5355 | 23.3412 | 25.7251 | 34.6446 | 41.1801 | 13.6777 | 9.6635 | 2.2559 | 2.3839 | 4.2896 | 3.7678 | 8.9194 | 6.5355 | 23.3412 | 25.7251 | 34.6446 | 41.1801 | 0
7.5315 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8633 | 17.9399 | 25.3228 | 30.629 | 7.5315 | 8.3318 | 2.051 | 2.0766 | 3.2652 | 3.1531 | 7.3829 | 5.3063 | 15.8633 | 17.9399 | 25.3228 | 30.629 | 0
6.5002 | 8.1084 | 2.0167 | 2.025 | 3.0834 | 3.05 | 7.1251 | 5.1 | 14.6086 | 16.6336 | 23.7587 | 28.8587 | 6.5002 | 8.1084 | 2.0167 | 2.025 | 3.0934 | 3.05 | 7.1251 | 5.1 | 14.6086 | 16.6336 | 23.7587 | 28.8587 | 0
12.3442 | 9.3746 | 2.2115 | 2.3172 | 4.0574 | 3.6344 | 8.586 | 6.2688 | 21.7187 | 24.036 | 32.622 | 38.8908 | 12.3442 | 9.3746 | 2.2115 | 2.3172 | 4.0674 | 3.6344 | 8.586 | 6.2688 | 21.7187 | 24.036 | 32.622 | 38.8908 | 0
-2.6847 | 6.1183 | 1.7105 | 1.5658 | 1.5526 | 2.1315 | 4.8288 | 3.2631 | 3.4337 | 4.9994 | 9.8283 | 13.0913 | -2.6847 | 6.1183 | 1.7105 | 1.5658 | 1.5626 | 2.1315 | 4.8288 | 3.2631 | 3.4337 | 4.9994 | 9.8283 | 13.0913 | 0
11.3098 | 9.1505 | 2.177 | 2.2655 | 3.885 | 3.531 | 8.3274 | 6.062 | 20.4602 | 22.7257 | 31.0532 | 37.1151 | 11.3098 | 9.1505 | 2.177 | 2.2655 | 3.895 | 3.531 | 8.3274 | 6.062 | 20.4602 | 22.7257 | 31.0532 | 37.1151 | 0
11.2312 | 9.1334 | 2.1744 | 2.2616 | 3.8719 | 3.5231 | 8.3078 | 6.0462 | 20.3646 | 22.6262 | 30.934 | 36.9802 | 11.2312 | 9.1334 | 2.1744 | 2.2616 | 3.8819 | 3.5231 | 8.3078 | 6.0462 | 20.3646 | 22.6262 | 30.934 | 36.9802 | 0
-2.2417 | 6.2143 | 1.7253 | 1.5879 | 1.6264 | 2.1758 | 4.9396 | 3.3517 | 3.9725 | 5.5605 | 10.5 | 13.8517 | -2.2417 | 6.2143 | 1.7253 | 1.5879 | 1.6364 | 2.1758 | 4.9396 | 3.3517 | 3.9725 | 5.5605 | 10.5 | 13.8517 | 0
13.1798 | 9.5556 | 2.2393 | 2.359 | 4.1966 | 3.718 | 8.795 | 6.436 | 22.7354 | 25.0944 | 33.8894 | 40.3253 | 13.1798 | 9.5556 | 2.2393 | 2.359 | 4.2066 | 3.718 | 8.795 | 6.436 | 22.7354 | 25.0944 | 33.8894 | 40.3253 | 0
-6.0136 | 5.397 | 1.5995 | 1.3993 | 0.99773 | 1.7986 | 3.9966 | 2.5973 | -0.61658 | 0.78274 | 4.7793 | 7.3766 | -6.0136 | 5.397 | 1.5995 | 1.3993 | 1.0077 | 1.7986 | 3.9966 | 2.5973 | -0.61658 | 0.78274 | 4.7793 | 7.3766 | 0
2.8839 | 7.3249 | 1.8961 | 1.8442 | 2.4807 | 2.6884 | 6.221 | 4.3768 | 10.2088 | 12.053 | 18.274 | 22.6508 | 2.8839 | 7.3249 | 1.8961 | 1.8442 | 2.4907 | 2.6884 | 6.221 | 4.3768 | 10.2088 | 12.053 | 18.274 | 22.6508 | 0
8.9173 | 8.6321 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5835 | 17.5494 | 19.6953 | 27.4246 | 33.0081 | 8.9173 | 8.6321 | 2.0972 | 2.1459 | 3.4962 | 3.2917 | 7.7293 | 5.5835 | 17.5494 | 19.6953 | 27.4246 | 33.0081 | 0
7.3594 | 8.2945 | 2.0453 | 2.068 | 3.2266 | 3.1359 | 7.3399 | 5.2719 | 15.654 | 17.722 | 25.0618 | 30.3337 | 7.3594 | 8.2945 | 2.0453 | 2.068 | 3.2366 | 3.1359 | 7.3399 | 5.2719 | 15.654 | 17.722 | 25.0618 | 30.3337 | 0
10.6967 | 9.0176 | 2.1566 | 2.2348 | 3.7828 | 3.4697 | 8.1742 | 5.9393 | 19.7143 | 21.9491 | 30.1233 | 36.0626 | 10.6967 | 9.0176 | 2.1566 | 2.2348 | 3.7928 | 3.4697 | 8.1742 | 5.9393 | 19.7143 | 21.9491 | 30.1233 | 36.0626 | 0
14.8238 | 9.9118 | 2.2941 | 2.4412 | 4.4706 | 3.8824 | 9.206 | 6.7648 | 24.7356 | 27.1768 | 36.3828 | 43.1475 | 14.8238 | 9.9118 | 2.2941 | 2.4412 | 4.4806 | 3.8824 | 9.206 | 6.7648 | 24.7356 | 27.1768 | 36.3828 | 43.1475 | 0
11.6384 | 9.2216 | 2.1879 | 2.2819 | 3.9397 | 3.5638 | 8.4096 | 6.1277 | 20.86 | 23.1419 | 31.5515 | 37.6792 | 11.6384 | 9.2216 | 2.1879 | 2.2819 | 3.9497 | 3.5638 | 8.4096 | 6.1277 | 20.86 | 23.1419 | 31.5515 | 37.6792 | 0
17.6788 | 10.5304 | 2.3893 | 2.5839 | 4.9465 | 4.1679 | 9.9197 | 7.3358 | 28.2092 | 30.7931 | 40.7128 | 48.0486 | 17.6788 | 10.5304 | 2.3893 | 2.5839 | 4.9565 | 4.1679 | 9.9197 | 7.3358 | 28.2092 | 30.7931 | 40.7128 | 48.0486 | 0
4.3589 | 7.6444 | 1.9453 | 1.9179 | 2.7265 | 2.8359 | 6.5897 | 4.6718 | 12.0033 | 13.9213 | 20.511 | 25.1828 | 4.3589 | 7.6444 | 1.9453 | 1.9179 | 2.7365 | 2.8359 | 6.5897 | 4.6718 | 12.0033 | 13.9213 | 20.511 | 25.1828 | 0
0.47148 | 6.8022 | 1.8157 | 1.7236 | 2.0786 | 2.4471 | 5.6179 | 3.8943 | 7.2736 | 8.9972 | 14.6151 | 18.5094 | 0.47148 | 6.8022 | 1.8157 | 1.7236 | 2.0886 | 2.4471 | 5.6179 | 3.8943 | 7.2736 | 8.9972 | 14.6151 | 18.5094 | 0
7.8912 | 8.4097 | 2.063 | 2.0946 | 3.3152 | 3.1891 | 7.4728 | 5.3782 | 16.3009 | 18.3955 | 25.8682 | 31.2465 | 7.8912 | 8.4097 | 2.063 | 2.0946 | 3.3252 | 3.1891 | 7.4728 | 5.3782 | 16.3009 | 18.3955 | 25.8682 | 31.2465 | 0
4.3809 | 7.6492 | 1.946 | 1.919 | 2.7301 | 2.8381 | 6.5952 | 4.6762 | 12.0301 | 13.9491 | 20.5444 | 25.2205 | 4.3809 | 7.6492 | 1.946 | 1.919 | 2.7401 | 2.8381 | 6.5952 | 4.6762 | 12.0301 | 13.9491 | 20.5444 | 25.2205 | 0
12.5045 | 9.4093 | 2.2168 | 2.3252 | 4.0841 | 3.6505 | 8.6261 | 6.3009 | 21.9138 | 24.2391 | 32.8652 | 39.1661 | 12.5045 | 9.4093 | 2.2168 | 2.3252 | 4.0941 | 3.6505 | 8.6261 | 6.3009 | 21.9138 | 24.2391 | 32.8652 | 39.1661 | 0
-2.5623 | 6.1448 | 1.7146 | 1.5719 | 1.5729 | 2.1438 | 4.8594 | 3.2875 | 3.5825 | 5.1544 | 10.0138 | 13.3013 | -2.5623 | 6.1448 | 1.7146 | 1.5719 | 1.5829 | 2.1438 | 4.8594 | 3.2875 | 3.5825 | 5.1544 | 10.0138 | 13.3013 | 0
5.628 | 7.9194 | 1.9876 | 1.9814 | 2.938 | 2.9628 | 6.907 | 4.9256 | 13.5474 | 15.5288 | 22.4358 | 27.3614 | 5.628 | 7.9194 | 1.9876 | 1.9814 | 2.948 | 2.9628 | 6.907 | 4.9256 | 13.5474 | 15.5288 | 22.4358 | 27.3614 | 0
-2.8667 | 6.0789 | 1.7044 | 1.5567 | 1.5222 | 2.1133 | 4.7833 | 3.2267 | 3.2122 | 4.7689 | 9.5522 | 12.7789 | -2.8667 | 6.0789 | 1.7044 | 1.5567 | 1.5322 | 2.1133 | 4.7833 | 3.2267 | 3.2122 | 4.7689 | 9.5522 | 12.7789 | 0
-6.8201 | 5.2223 | 1.5727 | 1.359 | 0.86332 | 1.718 | 3.795 | 2.436 | -1.5977 | -0.23874 | 3.5562 | 5.9922 | -6.8201 | 5.2223 | 1.5727 | 1.359 | 0.87332 | 1.718 | 3.795 | 2.436 | -1.5977 | -0.23874 | 3.5562 | 5.9922 | 0
-0.06598 | 6.6857 | 1.7978 | 1.6967 | 1.989 | 2.3934 | 5.4835 | 3.7868 | 6.6197 | 8.3164 | 13.7999 | 17.5867 | -0.06598 | 6.6857 | 1.7978 | 1.6967 | 1.999 | 2.3934 | 5.4835 | 3.7868 | 6.6197 | 8.3164 | 13.7999 | 17.5867 | 0
-4.274 | 5.774 | 1.6575 | 1.4863 | 1.2877 | 1.9726 | 4.4315 | 2.9452 | 1.4999 | 2.9862 | 7.4177 | 10.3629 | -4.274 | 5.774 | 1.6575 | 1.4863 | 1.2977 | 1.9726 | 4.4315 | 2.9452 | 1.4999 | 2.9862 | 7.4177 | 10.3629 | 0
9.4 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.85 | 5.68 | 18.1367 | 20.3067 | 28.1567 | 33.8367 | 9.4 | 8.7367 | 2.1133 | 2.17 | 3.5767 | 3.34 | 7.85 | 5.68 | 18.1367 | 20.3067 | 28.1567 | 33.8367 | 0
-0.6032 | 6.5693 | 1.7799 | 1.6698 | 1.8995 | 2.3397 | 5.3492 | 3.6794 | 5.9661 | 7.6359 | 12.9851 | 16.6645 | -0.6032 | 6.5693 | 1.7799 | 1.6698 | 1.9095 | 2.3397 | 5.3492 | 3.6794 | 5.9661 | 7.6359 | 12.9851 | 16.6645 | 0
0.58262 | 6.8262 | 1.8194 | 1.7291 | 2.0971 | 2.4583 | 5.6457 | 3.9165 | 7.4089 | 9.138 | 14.7836 | 18.7002 | 0.58262 | 6.8262 | 1.8194 | 1.7291 | 2.1071 | 2.4583 | 5.6457 | 3.9165 | 7.4089 | 9.138 | 14.7836 | 18.7002 | 0
6.9663 | 8.2094 | 2.0322 | 2.0483 | 3.161 | 3.0966 | 7.2416 | 5.1933 | 15.1756 | 17.2239 | 24.4655 | 29.6587 | 6.9663 | 8.2094 | 2.0322 | 2.0483 | 3.171 | 3.0966 | 7.2416 | 5.1933 | 15.1756 | 17.2239 | 24.4655 | 29.6587 | 0
8.3163 | 8.5019 | 2.0772 | 2.1158 | 3.386 | 3.2316 | 7.5791 | 5.4633 | 16.8181 | 18.9339 | 26.513 | 31.9762 | 8.3163 | 8.5019 | 2.0772 | 2.1158 | 3.396 | 3.2316 | 7.5791 | 5.4633 | 16.8181 | 18.9339 | 26.513 | 31.9762 | 0
-4.5469 | 5.7148 | 1.6484 | 1.4727 | 1.2422 | 1.9453 | 4.3633 | 2.8906 | 1.1679 | 2.6406 | 7.0038 | 9.8944 | -4.5469 | 5.7148 | 1.6484 | 1.4727 | 1.2522 | 1.9453 | 4.3633 | 2.8906 | 1.1679 | 2.6406 | 7.0038 | 9.8944 | 0
-7.9943 | 4.9679 | 1.5335 | 1.3003 | 0.66762 | 1.6006 | 3.5014 | 2.2011 | -3.0264 | -1.7261 | 1.7753 | 3.9765 | -7.9943 | 4.9679 | 1.5335 | 1.3003 | 0.67762 | 1.6006 | 3.5014 | 2.2011 | -3.0264 | -1.7261 | 1.7753 | 3.9765 | 0
4.1948 | 7.6089 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5487 | 4.639 | 11.8036 | 13.7134 | 20.2621 | 24.901 | 4.1948 | 7.6089 | 1.9398 | 1.9097 | 2.7091 | 2.8195 | 6.5487 | 4.639 | 11.8036 | 13.7134 | 20.2621 | 24.901 | 0
0.29908 | 6.7648 | 1.81 | 1.715 | 2.0498 | 2.4299 | 5.5748 | 3.8598 | 7.0639 | 8.7788 | 14.3536 | 18.2134 | 0.29908 | 6.7648 | 1.81 | 1.715 | 2.0598 | 2.4299 | 5.5748 | 3.8598 | 7.0639 | 8.7788 | 14.3536 | 18.2134 | 0
2.5167 | 7.2453 | 1.8839 | 1.8258 | 2.4194 | 2.6517 | 6.1292 | 4.3033 | 9.762 | 11.5878 | 17.717 | 22.0203 | 2.5167 | 7.2453 | 1.8839 | 1.8258 | 2.4294 | 2.6517 | 6.1292 | 4.3033 | 9.762 | 11.5878 | 17.717 | 22.0203 | 0
14.5896 | 9.8611 | 2.2863 | 2.4295 | 4.4316 | 3.859 | 9.1474 | 6.7179 | 24.4507 | 26.8802 | 36.0276 | 42.7455 | 14.5896 | 9.8611 | 2.2863 | 2.4295 | 4.4416 | 3.859 | 9.1474 | 6.7179 | 24.4507 | 26.8802 | 36.0276 | 42.7455 | 0
5.9257 | 7.9839 | 1.9975 | 1.9963 | 2.9876 | 2.9926 | 6.9814 | 4.9851 | 13.9095 | 15.9058 | 22.8872 | 27.8724 | 5.9257 | 7.9839 | 1.9975 | 1.9963 | 2.9976 | 2.9926 | 6.9814 | 4.9851 | 13.9095 | 15.9058 | 22.8872 | 27.8724 | 0
4.8036 | 7.7408 | 1.9601 | 1.9402 | 2.8006 | 2.8804 | 6.7009 | 4.7607 | 12.5443 | 14.4845 | 21.1854 | 25.9461 | 4.8036 | 7.7408 | 1.9601 | 1.9402 | 2.8106 | 2.8804 | 6.7009 | 4.7607 | 12.5443 | 14.4845 | 21.1854 | 25.9461 | 0
2.8171 | 7.3104 | 1.8939 | 1.8409 | 2.4695 | 2.6817 | 6.2043 | 4.3634 | 10.1275 | 11.9683 | 18.1726 | 22.536 | 2.8171 | 7.3104 | 1.8939 | 1.8409 | 2.4795 | 2.6817 | 6.2043 | 4.3634 | 10.1275 | 11.9683 | 18.1726 | 22.536 | 0
7.7332 | 8.3755 | 2.0578 | 2.0867 | 3.2889 | 3.1733 | 7.4333 | 5.3466 | 16.1088 | 18.1954 | 25.6287 | 30.9754 | 7.7332 | 8.3755 | 2.0578 | 2.0867 | 3.2989 | 3.1733 | 7.4333 | 5.3466 | 16.1088 | 18.1954 | 25.6287 | 30.9754 | 0
10.7305 | 9.0249 | 2.1577 | 2.2365 | 3.7884 | 3.473 | 8.1826 | 5.9461 | 19.7554 | 21.9919 | 30.1745 | 36.1206 | 10.7305 | 9.0249 | 2.1577 | 2.2365 | 3.7984 | 3.473 | 8.1826 | 5.9461 | 19.7554 | 21.9919 | 30.1745 | 36.1206 | 0
8.4966 | 8.5409 | 2.0832 | 2.1248 | 3.4161 | 3.2497 | 7.6242 | 5.4993 | 17.0375 | 19.1624 | 26.7865 | 32.2858 | 8.4966 | 8.5409 | 2.0832 | 2.1248 | 3.4261 | 3.2497 | 7.6242 | 5.4993 | 17.0375 | 19.1624 | 26.7865 | 32.2858 | 0
-8.2772 | 4.9066 | 1.5241 | 1.2861 | 0.62047 | 1.5723 | 3.4307 | 2.1446 | -3.3706 | -2.0844 | 1.3463 | 3.4908 | -8.2772 | 4.9066 | 1.5241 | 1.2861 | 0.63047 | 1.5723 | 3.4307 | 2.1446 | -3.3706 | -2.0844 | 1.3463 | 3.4908 | 0
8.6945 | 8.5838 | 2.0898 | 2.1347 | 3.4491 | 3.2695 | 7.6736 | 5.5389 | 17.2783 | 19.413 | 27.0867 | 32.6256 | 8.6945 | 8.5838 | 2.0898 | 2.1347 | 3.4591 | 3.2695 | 7.6736 | 5.5389 | 17.2783 | 19.413 | 27.0867 | 32.6256 | 0
4.4416 | 7.6624 | 1.9481 | 1.9221 | 2.7403 | 2.8442 | 6.6104 | 4.6883 | 12.104 | 14.0261 | 20.6365 | 25.3248 | 4.4416 | 7.6624 | 1.9481 | 1.9221 | 2.7503 | 2.8442 | 6.6104 | 4.6883 | 12.104 | 14.0261 | 20.6365 | 25.3248 | 0
4.5166 | 7.6786 | 1.9506 | 1.9258 | 2.7528 | 2.8517 | 6.6292 | 4.7033 | 12.1953 | 14.1211 | 20.7502 | 25.4536 | 4.5166 | 7.6786 | 1.9506 | 1.9258 | 2.7628 | 2.8517 | 6.6292 | 4.7033 | 12.1953 | 14.1211 | 20.7502 | 25.4536 | 0
7.1372 | 8.2464 | 2.0379 | 2.0569 | 3.1895 | 3.1137 | 7.2843 | 5.2274 | 15.3835 | 17.4404 | 24.7247 | 29.9521 | 7.1372 | 8.2464 | 2.0379 | 2.0569 | 3.1995 | 3.1137 | 7.2843 | 5.2274 | 15.3835 | 17.4404 | 24.7247 | 29.9521 | 0
9.3226 | 8.7199 | 2.1108 | 2.1661 | 3.5538 | 3.3323 | 7.8307 | 5.6645 | 18.0425 | 20.2087 | 28.0393 | 33.7039 | 9.3226 | 8.7199 | 2.1108 | 2.1661 | 3.5638 | 3.3323 | 7.8307 | 5.6645 | 18.0425 | 20.2087 | 28.0393 | 33.7039 | 0
1.1275 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7819 | 4.0255 | 8.0717 | 9.8281 | 15.61 | 19.6355 | 1.1275 | 6.9443 | 1.8376 | 1.7564 | 2.1979 | 2.5127 | 5.7819 | 4.0255 | 8.0717 | 9.8281 | 15.61 | 19.6355 | 0
-2.6418 | 6.1276 | 1.7119 | 1.5679 | 1.5597 | 2.1358 | 4.8395 | 3.2716 | 3.4858 | 5.0537 | 9.8932 | 13.1649 | -2.6418 | 6.1276 | 1.7119 | 1.5679 | 1.5697 | 2.1358 | 4.8395 | 3.2716 | 3.4858 | 5.0537 | 9.8932 | 13.1649 | 0
9.0604 | 8.6631 | 2.102 | 2.153 | 3.5101 | 3.306 | 7.7651 | 5.6121 | 17.7234 | 19.8765 | 27.6415 | 33.2536 | 9.0604 | 8.6631 | 2.102 | 2.153 | 3.5201 | 3.306 | 7.7651 | 5.6121 | 17.7234 | 19.8765 | 27.6415 | 33.2536 | 0
10.6866 | 9.0154 | 2.1562 | 2.2343 | 3.7811 | 3.4687 | 8.1717 | 5.9373 | 19.7021 | 21.9364 | 30.1081 | 36.0454 | 10.6866 | 9.0154 | 2.1562 | 2.2343 | 3.7911 | 3.4687 | 8.1717 | 5.9373 | 19.7021 | 21.9364 | 30.1081 | 36.0454 | 0
8.5379 | 8.5499 | 2.0846 | 2.1269 | 3.423 | 3.2538 | 7.6345 | 5.5076 | 17.0878 | 19.2146 | 26.8491 | 32.3567 | 8.5379 | 8.5499 | 2.0846 | 2.1269 | 3.433 | 3.2538 | 7.6345 | 5.5076 | 17.0878 | 19.2146 | 26.8491 | 32.3567 | 0
1.8028 | 7.0906 | 1.8601 | 1.7901 | 2.3005 | 2.5803 | 5.9507 | 4.1606 | 8.8935 | 10.6836 | 16.6343 | 20.7949 | 1.8028 | 7.0906 | 1.8601 | 1.7901 | 2.3105 | 2.5803 | 5.9507 | 4.1606 | 8.8935 | 10.6836 | 16.6343 | 20.7949 | 0
0.2989 | 6.7648 | 1.81 | 1.7149 | 2.0498 | 2.4299 | 5.5747 | 3.8598 | 7.0637 | 8.7786 | 14.3533 | 18.2131 | 0.2989 | 6.7648 | 1.81 | 1.7149 | 2.0598 | 2.4299 | 5.5747 | 3.8598 | 7.0637 | 8.7786 | 14.3533 | 18.2131 | 0
-0.13421 | 6.6709 | 1.7955 | 1.6933 | 1.9776 | 2.3866 | 5.4664 | 3.7732 | 6.5367 | 8.23 | 13.6965 | 17.4696 | -0.13421 | 6.6709 | 1.7955 | 1.6933 | 1.9876 | 2.3866 | 5.4664 | 3.7732 | 6.5367 | 8.23 | 13.6965 | 17.4696 | 0
7.0264 | 8.2224 | 2.0342 | 2.0513 | 3.1711 | 3.1026 | 7.2566 | 5.2053 | 15.2488 | 17.3001 | 24.5567 | 29.762 | 7.0264 | 8.2224 | 2.0342 | 2.0513 | 3.1811 | 3.1026 | 7.2566 | 5.2053 | 15.2488 | 17.3001 | 24.5567 | 29.762 | 0
15.9381 | 10.1533 | 2.3313 | 2.4969 | 4.6563 | 3.9938 | 9.4845 | 6.9876 | 26.0913 | 28.5883 | 38.0728 | 45.0604 | 15.9381 | 10.1533 | 2.3313 | 2.4969 | 4.6663 | 3.9938 | 9.4845 | 6.9876 | 26.0913 | 28.5883 | 38.0728 | 45.0604 | 0
4.2657 | 7.6242 | 1.9422 | 1.9133 | 2.711 | 2.8266 | 6.5664 | 4.6531 | 11.89 | 13.8033 | 20.3697 | 25.0229 | 4.2657 | 7.6242 | 1.9422 | 1.9133 | 2.721 | 2.8266 | 6.5664 | 4.6531 | 11.89 | 13.8033 | 20.3697 | 25.0229 | 0
-1.1135 | 6.4587 | 1.7629 | 1.6443 | 1.8144 | 2.2886 | 5.2216 | 3.5773 | 5.3452 | 6.9896 | 12.2112 | 15.7885 | -1.1135 | 6.4587 | 1.7629 | 1.6443 | 1.8244 | 2.2886 | 5.2216 | 3.5773 | 5.3452 | 6.9896 | 12.2112 | 15.7885 | 0
4.8713 | 7.7554 | 1.9624 | 1.9436 | 2.8119 | 2.8871 | 6.7178 | 4.7743 | 12.6267 | 14.5703 | 21.2881 | 26.0624 | 4.8713 | 7.7554 | 1.9624 | 1.9436 | 2.8219 | 2.8871 | 6.7178 | 4.7743 | 12.6267 | 14.5703 | 21.2881 | 26.0624 | 0
7.0446 | 8.2263 | 2.0348 | 2.0522 | 3.1741 | 3.1045 | 7.2612 | 5.2089 | 15.2709 | 17.3232 | 24.5843 | 29.7933 | 7.0446 | 8.2263 | 2.0348 | 2.0522 | 3.1841 | 3.1045 | 7.2612 | 5.2089 | 15.2709 | 17.3232 | 24.5843 | 29.7933 | 0
20.3696 | 11.1134 | 2.479 | 2.7185 | 5.3949 | 4.437 | 10.5924 | 7.8739 | 31.483 | 34.2015 | 44.7939 | 52.6678 | 20.3696 | 11.1134 | 2.479 | 2.7185 | 5.4049 | 4.437 | 10.5924 | 7.8739 | 31.483 | 34.2015 | 44.7939 | 52.6678 | 0
2.9926 | 7.3484 | 1.8998 | 1.8496 | 2.4988 | 2.6993 | 6.2482 | 4.3985 | 10.341 | 12.1907 | 18.4388 | 22.8374 | 2.9926 | 7.3484 | 1.8998 | 1.8496 | 2.5088 | 2.6993 | 6.2482 | 4.3985 | 10.341 | 12.1907 | 18.4388 | 22.8374 | 0
3.3625 | 7.4285 | 1.9121 | 1.8681 | 2.5604 | 2.7362 | 6.3406 | 4.4725 | 10.791 | 12.6591 | 18.9998 | 23.4723 | 3.3625 | 7.4285 | 1.9121 | 1.8681 | 2.5704 | 2.7362 | 6.3406 | 4.4725 | 10.791 | 12.6591 | 18.9998 | 23.4723 | 0
2.8398 | 7.3153 | 1.8947 | 1.842 | 2.4733 | 2.684 | 6.21 | 4.368 | 10.1551 | 11.9971 | 18.207 | 22.575 | 2.8398 | 7.3153 | 1.8947 | 1.842 | 2.4833 | 2.684 | 6.21 | 4.368 | 10.1551 | 11.9971 | 18.207 | 22.575 | 0
8.605 | 8.5644 | 2.0868 | 2.1302 | 3.4342 | 3.2605 | 7.6512 | 5.521 | 17.1694 | 19.2996 | 26.9509 | 32.4719 | 8.605 | 8.5644 | 2.0868 | 2.1302 | 3.4442 | 3.2605 | 7.6512 | 5.521 | 17.1694 | 19.2996 | 26.9509 | 32.4719 | 0
8.192 | 8.4749 | 2.0731 | 2.1096 | 3.3653 | 3.2192 | 7.548 | 5.4384 | 16.6669 | 18.7765 | 26.3245 | 31.7629 | 8.192 | 8.4749 | 2.0731 | 2.1096 | 3.3753 | 3.2192 | 7.548 | 5.4384 | 16.6669 | 18.7765 | 26.3245 | 31.7629 | 0
8.0575 | 8.4458 | 2.0686 | 2.1029 | 3.3429 | 3.2057 | 7.5144 | 5.4115 | 16.5033 | 18.6062 | 26.1205 | 31.532 | 8.0575 | 8.4458 | 2.0686 | 2.1029 | 3.3529 | 3.2057 | 7.5144 | 5.4115 | 16.5033 | 18.6062 | 26.1205 | 31.532 | 0
5.6798 | 7.9306 | 1.9893 | 1.984 | 2.9466 | 2.968 | 6.92 | 4.936 | 13.6104 | 15.5944 | 22.5144 | 27.4503 | 5.6798 | 7.9306 | 1.9893 | 1.984 | 2.9566 | 2.968 | 6.92 | 4.936 | 13.6104 | 15.5944 | 22.5144 | 27.4503 | 0
12.1633 | 9.3354 | 2.2054 | 2.3082 | 4.0272 | 3.6163 | 8.5408 | 6.2327 | 21.4987 | 23.8069 | 32.3477 | 38.5804 | 12.1633 | 9.3354 | 2.2054 | 2.3082 | 4.0372 | 3.6163 | 8.5408 | 6.2327 | 21.4987 | 23.8069 | 32.3477 | 38.5804 | 0
8.89 | 8.6262 | 2.0963 | 2.1445 | 3.4817 | 3.289 | 7.7225 | 5.578 | 17.5161 | 19.6606 | 27.3831 | 32.9611 | 8.89 | 8.6262 | 2.0963 | 2.1445 | 3.4917 | 3.289 | 7.7225 | 5.578 | 17.5161 | 19.6606 | 27.3831 | 32.9611 | 0
4.5152 | 7.6783 | 1.9505 | 1.9258 | 2.7525 | 2.8515 | 6.6288 | 4.703 | 12.1935 | 14.1192 | 20.748 | 25.451 | 4.5152 | 7.6783 | 1.9505 | 1.9258 | 2.7625 | 2.8515 | 6.6288 | 4.703 | 12.1935 | 14.1192 | 20.748 | 25.451 | 0
17.5746 | 10.5078 | 2.3858 | 2.5787 | 4.9291 | 4.1575 | 9.8937 | 7.3149 | 28.0824 | 30.6612 | 40.5548 | 47.8697 | 17.5746 | 10.5078 | 2.3858 | 2.5787 | 4.9391 | 4.1575 | 9.8937 | 7.3149 | 28.0824 | 30.6612 | 40.5548 | 47.8697 | 0
7.2511 | 8.2711 | 2.0417 | 2.0626 | 3.2085 | 3.1251 | 7.3128 | 5.2502 | 15.5222 | 17.5848 | 24.8976 | 30.1478 | 7.2511 | 8.2711 | 2.0417 | 2.0626 | 3.2185 | 3.1251 | 7.3128 | 5.2502 | 15.5222 | 17.5848 | 24.8976 | 30.1478 | 0
7.1645 | 8.2523 | 2.0388 | 2.0582 | 3.1941 | 3.1164 | 7.2911 | 5.2329 | 15.4168 | 17.475 | 24.7661 | 29.999 | 7.1645 | 8.2523 | 2.0388 | 2.0582 | 3.2041 | 3.1164 | 7.2911 | 5.2329 | 15.4168 | 17.475 | 24.7661 | 29.999 | 0
8.9096 | 8.6304 | 2.097 | 2.1455 | 3.4849 | 3.291 | 7.7274 | 5.5819 | 17.54 | 19.6855 | 27.4129 | 32.9948 | 8.9096 | 8.6304 | 2.097 | 2.1455 | 3.4949 | 3.291 | 7.7274 | 5.5819 | 17.54 | 19.6855 | 27.4129 | 32.9948 | 0
13.8753 | 9.7063 | 2.2625 | 2.3938 | 4.3126 | 3.7875 | 8.9688 | 6.5751 | 23.5816 | 25.9754 | 34.9442 | 41.5193 | 13.8753 | 9.7063 | 2.2625 | 2.3938 | 4.3226 | 3.7875 | 8.9688 | 6.5751 | 23.5816 | 25.9754 | 34.9442 | 41.5193 | 0
14.9444 | 9.938 | 2.2981 | 2.4472 | 4.4907 | 3.8944 | 9.2361 | 6.7889 | 24.8824 | 27.3296 | 36.5657 | 43.3546 | 14.9444 | 9.938 | 2.2981 | 2.4472 | 4.5007 | 3.8944 | 9.2361 | 6.7889 | 24.8824 | 27.3296 | 36.5657 | 43.3546 | 0
12.6497 | 9.4408 | 2.2217 | 2.3325 | 4.1083 | 3.665 | 8.6624 | 6.3299 | 22.0904 | 24.4229 | 33.0853 | 39.4153 | 12.6497 | 9.4408 | 2.2217 | 2.3325 | 4.1183 | 3.665 | 8.6624 | 6.3299 | 22.0904 | 24.4229 | 33.0853 | 39.4153 | 0
-5.3839 | 5.5335 | 1.6205 | 1.4308 | 1.1027 | 1.8616 | 4.154 | 2.7232 | 0.14953 | 1.5803 | 5.7343 | 8.4576 | -5.3839 | 5.5335 | 1.6205 | 1.4308 | 1.1127 | 1.8616 | 4.154 | 2.7232 | 0.14953 | 1.5803 | 5.7343 | 8.4576 | 0
7.415 | 8.3066 | 2.0472 | 2.0707 | 3.2358 | 3.1415 | 7.3537 | 5.283 | 15.7215 | 17.7923 | 25.146 | 30.429 | 7.415 | 8.3066 | 2.0472 | 2.0707 | 3.2458 | 3.1415 | 7.3537 | 5.283 | 15.7215 | 17.7923 | 25.146 | 30.429 | 0
0.75401 | 6.8634 | 1.8251 | 1.7377 | 2.1257 | 2.4754 | 5.6885 | 3.9508 | 7.6174 | 9.3551 | 15.0436 | 18.9944 | 0.75401 | 6.8634 | 1.8251 | 1.7377 | 2.1357 | 2.4754 | 5.6885 | 3.9508 | 7.6174 | 9.3551 | 15.0436 | 18.9944 | 0
7.6785 | 8.3637 | 2.0559 | 2.0839 | 3.2797 | 3.1678 | 7.4196 | 5.3357 | 16.0421 | 18.1261 | 25.5457 | 30.8814 | 7.6785 | 8.3637 | 2.0559 | 2.0839 | 3.2897 | 3.1678 | 7.4196 | 5.3357 | 16.0421 | 18.1261 | 25.5457 | 30.8814 | 0
-6.7356 | 5.2406 | 1.5755 | 1.3632 | 0.8774 | 1.7264 | 3.8161 | 2.4529 | -1.495 | -0.13174 | 3.6844 | 6.1373 | -6.7356 | 5.2406 | 1.5755 | 1.3632 | 0.8874 | 1.7264 | 3.8161 | 2.4529 | -1.495 | -0.13174 | 3.6844 | 6.1373 | 0
15.0729 | 9.9658 | 2.3024 | 2.4536 | 4.5121 | 3.9073 | 9.2682 | 6.8146 | 25.0387 | 27.4923 | 36.7606 | 43.5751 | 15.0729 | 9.9658 | 2.3024 | 2.4536 | 4.5221 | 3.9073 | 9.2682 | 6.8146 | 25.0387 | 27.4923 | 36.7606 | 43.5751 | 0
4.1628 | 7.6019 | 1.9388 | 1.9081 | 2.6938 | 2.8163 | 6.5407 | 4.6326 | 11.7648 | 13.6729 | 20.2136 | 24.8462 | 4.1628 | 7.6019 | 1.9388 | 1.9081 | 2.7038 | 2.8163 | 6.5407 | 4.6326 | 11.7648 | 13.6729 | 20.2136 | 24.8462 | 0
-1.8279 | 6.304 | 1.7391 | 1.6086 | 1.6954 | 2.2172 | 5.043 | 3.4344 | 4.4761 | 6.0847 | 11.1277 | 14.5622 | -1.8279 | 6.304 | 1.7391 | 1.6086 | 1.7054 | 2.2172 | 5.043 | 3.4344 | 4.4761 | 6.0847 | 11.1277 | 14.5622 | 0
7.3349 | 8.2892 | 2.0445 | 2.0667 | 3.2225 | 3.1335 | 7.3337 | 5.267 | 15.6242 | 17.6909 | 25.0246 | 30.2916 | 7.3349 | 8.2892 | 2.0445 | 2.0667 | 3.2325 | 3.1335 | 7.3337 | 5.267 | 15.6242 | 17.6909 | 25.0246 | 30.2916 | 0
-2.9217 | 6.067 | 1.7026 | 1.5539 | 1.5131 | 2.1078 | 4.7696 | 3.2157 | 3.1453 | 4.6992 | 9.4688 | 12.6845 | -2.9217 | 6.067 | 1.7026 | 1.5539 | 1.5231 | 2.1078 | 4.7696 | 3.2157 | 3.1453 | 4.6992 | 9.4688 | 12.6845 | 0
6.4196 | 8.0909 | 2.014 | 2.021 | 3.0699 | 3.042 | 7.1049 | 5.0839 | 14.5106 | 16.5315 | 23.6364 | 28.7204 | 6.4196 | 8.0909 | 2.014 | 2.021 | 3.0799 | 3.042 | 7.1049 | 5.0839 | 14.5106 | 16.5315 | 23.6364 | 28.7204 | 0
-3.1568 | 6.016 | 1.6948 | 1.5422 | 1.4739 | 2.0843 | 4.7108 | 3.1686 | 2.8592 | 4.4013 | 9.1121 | 12.2807 | -3.1568 | 6.016 | 1.6948 | 1.5422 | 1.4839 | 2.0843 | 4.7108 | 3.1686 | 2.8592 | 4.4013 | 9.1121 | 12.2807 | 0
-5.5235 | 5.5032 | 1.6159 | 1.4238 | 1.0794 | 1.8476 | 4.1191 | 2.6953 | -0.0203 | 1.4035 | 5.5226 | 8.2179 | -5.5235 | 5.5032 | 1.6159 | 1.4238 | 1.0894 | 1.8476 | 4.1191 | 2.6953 | -0.0203 | 1.4035 | 5.5226 | 8.2179 | 0
4.1099 | 7.5905 | 1.937 | 1.9055 | 2.685 | 2.811 | 6.5275 | 4.622 | 11.7004 | 13.6058 | 20.1333 | 24.7553 | 4.1099 | 7.5905 | 1.937 | 1.9055 | 2.695 | 2.811 | 6.5275 | 4.622 | 11.7004 | 13.6058 | 20.1333 | 24.7553 | 0
9.1846 | 8.69 | 2.1062 | 2.1592 | 3.5308 | 3.3185 | 7.7962 | 5.6369 | 17.8746 | 20.0339 | 27.83 | 33.4669 | 9.1846 | 8.69 | 2.1062 | 2.1592 | 3.5408 | 3.3185 | 7.7962 | 5.6369 | 17.8746 | 20.0339 | 27.83 | 33.4669 | 0
-3.3156 | 5.9816 | 1.6895 | 1.5342 | 1.4474 | 2.0684 | 4.6711 | 3.1369 | 2.666 | 4.2003 | 8.8714 | 12.0082 | -3.3156 | 5.9816 | 1.6895 | 1.5342 | 1.4574 | 2.0684 | 4.6711 | 3.1369 | 2.666 | 4.2003 | 8.8714 | 12.0082 | 0
10.6419 | 9.0057 | 2.1547 | 2.2321 | 3.7737 | 3.4642 | 8.1605 | 5.9284 | 19.6477 | 21.8798 | 30.0402 | 35.9686 | 10.6419 | 9.0057 | 2.1547 | 2.2321 | 3.7837 | 3.4642 | 8.1605 | 5.9284 | 19.6477 | 21.8798 | 30.0402 | 35.9686 | 0
9.4293 | 8.743 | 2.1143 | 2.1715 | 3.5716 | 3.3429 | 7.8573 | 5.6859 | 18.1724 | 20.3438 | 28.2012 | 33.8871 | 9.4293 | 8.743 | 2.1143 | 2.1715 | 3.5816 | 3.3429 | 7.8573 | 5.6859 | 18.1724 | 20.3438 | 28.2012 | 33.8871 | 0
24.2891 | 11.9626 | 2.6096 | 2.9145 | 6.0482 | 4.8289 | 11.5723 | 8.6578 | 36.2518 | 39.1662 | 50.7385 | 59.3964 | 24.2891 | 11.9626 | 2.6096 | 2.9145 | 6.0582 | 4.8289 | 11.5723 | 8.6578 | 36.2518 | 39.1662 | 50.7385 | 59.3964 | 0
8.2951 | 8.4973 | 2.0765 | 2.1148 | 3.3825 | 3.2295 | 7.5738 | 5.459 | 16.7923 | 18.9071 | 26.4808 | 31.9398 | 8.2951 | 8.4973 | 2.0765 | 2.1148 | 3.3925 | 3.2295 | 7.5738 | 5.459 | 16.7923 | 18.9071 | 26.4808 | 31.9398 | 0
-5.1847 | 5.5767 | 1.6272 | 1.4408 | 1.1359 | 1.8815 | 4.2038 | 2.7631 | 0.392 | 1.8328 | 6.0366 | 8.7997 | -5.1847 | 5.5767 | 1.6272 | 1.4408 | 1.1459 | 1.8815 | 4.2038 | 2.7631 | 0.392 | 1.8328 | 6.0366 | 8.7997 | 0
7.4308 | 8.31 | 2.0477 | 2.0715 | 3.2385 | 3.1431 | 7.3577 | 5.2862 | 15.7408 | 17.8123 | 25.17 | 30.4562 | 7.4308 | 8.31 | 2.0477 | 2.0715 | 3.2485 | 3.1431 | 7.3577 | 5.2862 | 15.7408 | 17.8123 | 25.17 | 30.4562 | 0
3.9805 | 7.5624 | 1.9327 | 1.899 | 2.6634 | 2.798 | 6.4951 | 4.5961 | 11.5429 | 13.4419 | 19.937 | 24.5331 | 3.9805 | 7.5624 | 1.9327 | 1.899 | 2.6734 | 2.798 | 6.4951 | 4.5961 | 11.5429 | 13.4419 | 19.937 | 24.5331 | 0
6.9627 | 8.2086 | 2.0321 | 2.0481 | 3.1605 | 3.0963 | 7.2407 | 5.1925 | 15.1713 | 17.2195 | 24.4602 | 29.6527 | 6.9627 | 8.2086 | 2.0321 | 2.0481 | 3.1705 | 3.0963 | 7.2407 | 5.1925 | 15.1713 | 17.2195 | 24.4602 | 29.6527 | 0
10.5847 | 8.9933 | 2.1528 | 2.2292 | 3.7641 | 3.4585 | 8.1462 | 5.9169 | 19.578 | 21.8073 | 29.9534 | 35.8704 | 10.5847 | 8.9933 | 2.1528 | 2.2292 | 3.7741 | 3.4585 | 8.1462 | 5.9169 | 19.578 | 21.8073 | 29.9534 | 35.8704 | 0
-1.1576 | 6.4492 | 1.7614 | 1.6421 | 1.8071 | 2.2842 | 5.2106 | 3.5685 | 5.2915 | 6.9337 | 12.1443 | 15.7127 | -1.1576 | 6.4492 | 1.7614 | 1.6421 | 1.8171 | 2.2842 | 5.2106 | 3.5685 | 5.2915 | 6.9337 | 12.1443 | 15.7127 | 0
-1.1256 | 6.4561 | 1.7625 | 1.6437 | 1.8124 | 2.2874 | 5.2186 | 3.5749 | 5.3305 | 6.9742 | 12.1928 | 15.7677 | -1.1256 | 6.4561 | 1.7625 | 1.6437 | 1.8224 | 2.2874 | 5.2186 | 3.5749 | 5.3305 | 6.9742 | 12.1928 | 15.7677 | 0
10.0004 | 8.8667 | 2.1333 | 2.2 | 3.6667 | 3.4 | 8.0001 | 5.8001 | 18.8671 | 21.0671 | 29.0672 | 34.8673 | 10.0004 | 8.8667 | 2.1333 | 2.2 | 3.6767 | 3.4 | 8.0001 | 5.8001 | 18.8671 | 21.0671 | 29.0672 | 34.8673 | 0
8.9462 | 8.6383 | 2.0982 | 2.1473 | 3.491 | 3.2946 | 7.7366 | 5.5892 | 17.5845 | 19.7319 | 27.4684 | 33.0576 | 8.9462 | 8.6383 | 2.0982 | 2.1473 | 3.501 | 3.2946 | 7.7366 | 5.5892 | 17.5845 | 19.7319 | 27.4684 | 33.0576 | 0
1.749 | 7.0789 | 1.8583 | 1.7874 | 2.2915 | 2.5749 | 5.9372 | 4.1498 | 8.8279 | 10.6153 | 16.5526 | 20.7024 | 1.749 | 7.0789 | 1.8583 | 1.7874 | 2.3015 | 2.5749 | 5.9372 | 4.1498 | 8.8279 | 10.6153 | 16.5526 | 20.7024 | 0
0.17321 | 6.7375 | 1.8058 | 1.7087 | 2.0289 | 2.4173 | 5.5433 | 3.8346 | 6.9107 | 8.6194 | 14.1627 | 17.9973 | 0.17321 | 6.7375 | 1.8058 | 1.7087 | 2.0389 | 2.4173 | 5.5433 | 3.8346 | 6.9107 | 8.6194 | 14.1627 | 17.9973 | 0
7.8213 | 8.3946 | 2.0607 | 2.0911 | 3.3035 | 3.1821 | 7.4553 | 5.3643 | 16.2159 | 18.3069 | 25.7622 | 31.1265 | 7.8213 | 8.3946 | 2.0607 | 2.0911 | 3.3135 | 3.1821 | 7.4553 | 5.3643 | 16.2159 | 18.3069 | 25.7622 | 31.1265 | 0
15.1106 | 9.974 | 2.3037 | 2.4555 | 4.5184 | 3.9111 | 9.2777 | 6.8221 | 25.0846 | 27.5401 | 36.8178 | 43.6399 | 15.1106 | 9.974 | 2.3037 | 2.4555 | 4.5284 | 3.9111 | 9.2777 | 6.8221 | 25.0846 | 27.5401 | 36.8178 | 43.6399 | 0
10.1426 | 8.8976 | 2.1381 | 2.2071 | 3.6904 | 3.4143 | 8.0357 | 5.8285 | 19.0402 | 21.2473 | 29.283 | 35.1115 | 10.1426 | 8.8976 | 2.1381 | 2.2071 | 3.7004 | 3.4143 | 8.0357 | 5.8285 | 19.0402 | 21.2473 | 29.283 | 35.1115 | 0
16.8847 | 10.3583 | 2.3628 | 2.5442 | 4.8141 | 4.0885 | 9.7212 | 7.1769 | 27.243 | 29.7873 | 39.5084 | 46.6854 | 16.8847 | 10.3583 | 2.3628 | 2.5442 | 4.8241 | 4.0885 | 9.7212 | 7.1769 | 27.243 | 29.7873 | 39.5084 | 46.6854 | 0
7.7903 | 8.3879 | 2.0597 | 2.0895 | 3.2984 | 3.179 | 7.4476 | 5.3581 | 16.1782 | 18.2677 | 25.7153 | 31.0734 | 7.7903 | 8.3879 | 2.0597 | 2.0895 | 3.3084 | 3.179 | 7.4476 | 5.3581 | 16.1782 | 18.2677 | 25.7153 | 31.0734 | 0
13.5503 | 9.6359 | 2.2517 | 2.3775 | 4.2584 | 3.755 | 8.8876 | 6.5101 | 23.1862 | 25.5637 | 34.4513 | 40.9613 | 13.5503 | 9.6359 | 2.2517 | 2.3775 | 4.2684 | 3.755 | 8.8876 | 6.5101 | 23.1862 | 25.5637 | 34.4513 | 40.9613 | 0
15.0013 | 9.9503 | 2.3 | 2.4501 | 4.5002 | 3.9001 | 9.2503 | 6.8003 | 24.9515 | 27.4016 | 36.6519 | 43.4522 | 15.0013 | 9.9503 | 2.3 | 2.4501 | 4.5102 | 3.9001 | 9.2503 | 6.8003 | 24.9515 | 27.4016 | 36.6519 | 43.4522 | 0
7.9384 | 8.42 | 2.0646 | 2.0969 | 3.3231 | 3.1938 | 7.4846 | 5.3877 | 16.3584 | 18.4553 | 25.9399 | 31.3276 | 7.9384 | 8.42 | 2.0646 | 2.0969 | 3.3331 | 3.1938 | 7.4846 | 5.3877 | 16.3584 | 18.4553 | 25.9399 | 31.3276 | 0
6.8871 | 8.1922 | 2.0296 | 2.0444 | 3.1479 | 3.0887 | 7.2218 | 5.1774 | 15.0793 | 17.1237 | 24.3455 | 29.5229 | 6.8871 | 8.1922 | 2.0296 | 2.0444 | 3.1579 | 3.0887 | 7.2218 | 5.1774 | 15.0793 | 17.1237 | 24.3455 | 29.5229 | 0
1.9661 | 7.126 | 1.8655 | 1.7983 | 2.3277 | 2.5966 | 5.9915 | 4.1932 | 9.0921 | 10.8904 | 16.8819 | 21.0751 | 1.9661 | 7.126 | 1.8655 | 1.7983 | 2.3377 | 2.5966 | 5.9915 | 4.1932 | 9.0921 | 10.8904 | 16.8819 | 21.0751 | 0
3.4524 | 7.448 | 1.9151 | 1.8726 | 2.5754 | 2.7452 | 6.3631 | 4.4905 | 10.9004 | 12.773 | 19.1361 | 23.6266 | 3.4524 | 7.448 | 1.9151 | 1.8726 | 2.5854 | 2.7452 | 6.3631 | 4.4905 | 10.9004 | 12.773 | 19.1361 | 23.6266 | 0
11.6679 | 9.228 | 2.1889 | 2.2834 | 3.9446 | 3.5668 | 8.417 | 6.1336 | 20.8959 | 23.1793 | 31.5963 | 37.7298 | 11.6679 | 9.228 | 2.1889 | 2.2834 | 3.9546 | 3.5668 | 8.417 | 6.1336 | 20.8959 | 23.1793 | 31.5963 | 37.7298 | 0
-0.70544 | 6.5472 | 1.7765 | 1.6647 | 1.8824 | 2.3295 | 5.3236 | 3.6589 | 5.8417 | 7.5064 | 12.8301 | 16.489 | -0.70544 | 6.5472 | 1.7765 | 1.6647 | 1.8924 | 2.3295 | 5.3236 | 3.6589 | 5.8417 | 7.5064 | 12.8301 | 16.489 | 0
4.6741 | 7.7127 | 1.9558 | 1.9337 | 2.779 | 2.8674 | 6.6685 | 4.7348 | 12.3868 | 14.3205 | 20.989 | 25.7238 | 4.6741 | 7.7127 | 1.9558 | 1.9337 | 2.789 | 2.8674 | 6.6685 | 4.7348 | 12.3868 | 14.3205 | 20.989 | 25.7238 | 0
10.26 | 8.923 | 2.142 | 2.213 | 3.71 | 3.426 | 8.065 | 5.852 | 19.183 | 21.396 | 29.461 | 35.313 | 10.26 | 8.923 | 2.142 | 2.213 | 3.72 | 3.426 | 8.065 | 5.852 | 19.183 | 21.396 | 29.461 | 35.313 | 0
7.416 | 8.3068 | 2.0472 | 2.0708 | 3.236 | 3.1416 | 7.354 | 5.2832 | 15.7228 | 17.7936 | 25.1476 | 30.4308 | 7.416 | 8.3068 | 2.0472 | 2.0708 | 3.246 | 3.1416 | 7.354 | 5.2832 | 15.7228 | 17.7936 | 25.1476 | 30.4308 | 0
2.6131 | 7.2662 | 1.8871 | 1.8307 | 2.4355 | 2.6613 | 6.1533 | 4.3226 | 9.8793 | 11.71 | 17.8633 | 22.1859 | 2.6131 | 7.2662 | 1.8871 | 1.8307 | 2.4455 | 2.6613 | 6.1533 | 4.3226 | 9.8793 | 11.71 | 17.8633 | 22.1859 | 0
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2044 | 14.1306 | 20.7616 | 25.4664 | 4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.764 | 2.8524 | 6.631 | 4.7048 | 12.2044 | 14.1306 | 20.7616 | 25.4664 | 0
9.0177 | 8.6538 | 2.1006 | 2.1509 | 3.5029 | 3.3018 | 7.7544 | 5.6035 | 17.6715 | 19.8224 | 27.5768 | 33.1803 | 9.0177 | 8.6538 | 2.1006 | 2.1509 | 3.5129 | 3.3018 | 7.7544 | 5.6035 | 17.6715 | 19.8224 | 27.5768 | 33.1803 | 0
11.271 | 9.1421 | 2.1757 | 2.2636 | 3.8785 | 3.5271 | 8.3178 | 6.0542 | 20.4131 | 22.6766 | 30.9944 | 37.0486 | 11.271 | 9.1421 | 2.1757 | 2.2636 | 3.8885 | 3.5271 | 8.3178 | 6.0542 | 20.4131 | 22.6766 | 30.9944 | 37.0486 | 0
4.8689 | 7.7549 | 1.9623 | 1.9434 | 2.8115 | 2.8869 | 6.7172 | 4.7738 | 12.6238 | 14.5672 | 21.2844 | 26.0582 | 4.8689 | 7.7549 | 1.9623 | 1.9434 | 2.8215 | 2.8869 | 6.7172 | 4.7738 | 12.6238 | 14.5672 | 21.2844 | 26.0582 | 0
13.7381 | 9.6766 | 2.2579 | 2.3869 | 4.2897 | 3.7738 | 8.9345 | 6.5476 | 23.4147 | 25.8016 | 34.7361 | 41.2837 | 13.7381 | 9.6766 | 2.2579 | 2.3869 | 4.2997 | 3.7738 | 8.9345 | 6.5476 | 23.4147 | 25.8016 | 34.7361 | 41.2837 | 0
-0.14801 | 6.6679 | 1.7951 | 1.6926 | 1.9753 | 2.3852 | 5.463 | 3.7704 | 6.5199 | 8.2125 | 13.6755 | 17.4459 | -0.14801 | 6.6679 | 1.7951 | 1.6926 | 1.9853 | 2.3852 | 5.463 | 3.7704 | 6.5199 | 8.2125 | 13.6755 | 17.4459 | 0
4.9965 | 7.7826 | 1.9666 | 1.9498 | 2.8328 | 2.8997 | 6.7491 | 4.7993 | 12.7791 | 14.7289 | 21.478 | 26.2773 | 4.9965 | 7.7826 | 1.9666 | 1.9498 | 2.8428 | 2.8997 | 6.7491 | 4.7993 | 12.7791 | 14.7289 | 21.478 | 26.2773 | 0
2.9362 | 7.3362 | 1.8979 | 1.8468 | 2.4894 | 2.6936 | 6.234 | 4.3872 | 10.2723 | 12.1191 | 18.3532 | 22.7404 | 2.9362 | 7.3362 | 1.8979 | 1.8468 | 2.4994 | 2.6936 | 6.234 | 4.3872 | 10.2723 | 12.1191 | 18.3532 | 22.7404 | 0
10.8682 | 9.0548 | 2.1623 | 2.2434 | 3.8114 | 3.4868 | 8.2171 | 5.9736 | 19.923 | 22.1664 | 30.3835 | 36.3571 | 10.8682 | 9.0548 | 2.1623 | 2.2434 | 3.8214 | 3.4868 | 8.2171 | 5.9736 | 19.923 | 22.1664 | 30.3835 | 36.3571 | 0
5.3766 | 7.8649 | 1.9792 | 1.9688 | 2.8961 | 2.9377 | 6.8441 | 4.8753 | 13.2415 | 15.2103 | 22.0545 | 26.9298 | 5.3766 | 7.8649 | 1.9792 | 1.9688 | 2.9061 | 2.9377 | 6.8441 | 4.8753 | 13.2415 | 15.2103 | 22.0545 | 26.9298 | 0
-3.2425 | 5.9975 | 1.6919 | 1.5379 | 1.4596 | 2.0758 | 4.6894 | 3.1515 | 2.755 | 4.2928 | 8.9822 | 12.1337 | -3.2425 | 5.9975 | 1.6919 | 1.5379 | 1.4696 | 2.0758 | 4.6894 | 3.1515 | 2.755 | 4.2928 | 8.9822 | 12.1337 | 0
5.784 | 7.9532 | 1.9928 | 1.9892 | 2.964 | 2.9784 | 6.946 | 4.9568 | 13.7372 | 15.7264 | 22.6724 | 27.6292 | 5.784 | 7.9532 | 1.9928 | 1.9892 | 2.974 | 2.9784 | 6.946 | 4.9568 | 13.7372 | 15.7264 | 22.6724 | 27.6292 | 0
0.62392 | 6.8352 | 1.8208 | 1.7312 | 2.104 | 2.4624 | 5.656 | 3.9248 | 7.4591 | 9.1903 | 14.8463 | 18.7711 | 0.62392 | 6.8352 | 1.8208 | 1.7312 | 2.114 | 2.4624 | 5.656 | 3.9248 | 7.4591 | 9.1903 | 14.8463 | 18.7711 | 0
3.8817 | 7.541 | 1.9294 | 1.8941 | 2.6469 | 2.7882 | 6.4704 | 4.5763 | 11.4227 | 13.3168 | 19.7872 | 24.3636 | 3.8817 | 7.541 | 1.9294 | 1.8941 | 2.6569 | 2.7882 | 6.4704 | 4.5763 | 11.4227 | 13.3168 | 19.7872 | 24.3636 | 0
6.7592 | 8.1645 | 2.0253 | 2.038 | 3.1265 | 3.0759 | 7.1898 | 5.1518 | 14.9237 | 16.9617 | 24.1515 | 29.3033 | 6.7592 | 8.1645 | 2.0253 | 2.038 | 3.1365 | 3.0759 | 7.1898 | 5.1518 | 14.9237 | 16.9617 | 24.1515 | 29.3033 | 0
8.4274 | 8.5259 | 2.0809 | 2.1214 | 3.4046 | 3.2427 | 7.6069 | 5.4855 | 16.9534 | 19.0748 | 26.6816 | 32.1671 | 8.4274 | 8.5259 | 2.0809 | 2.1214 | 3.4146 | 3.2427 | 7.6069 | 5.4855 | 16.9534 | 19.0748 | 26.6816 | 32.1671 | 0
16.2512 | 10.2211 | 2.3417 | 2.5126 | 4.7085 | 4.0251 | 9.5628 | 7.0502 | 26.4722 | 28.9848 | 38.5476 | 45.5978 | 16.2512 | 10.2211 | 2.3417 | 2.5126 | 4.7185 | 4.0251 | 9.5628 | 7.0502 | 26.4722 | 28.9848 | 38.5476 | 45.5978 | 0
3.9702 | 7.5602 | 1.9323 | 1.8985 | 2.6617 | 2.797 | 6.4925 | 4.594 | 11.5304 | 13.4289 | 19.9214 | 24.5155 | 3.9702 | 7.5602 | 1.9323 | 1.8985 | 2.6717 | 2.797 | 6.4925 | 4.594 | 11.5304 | 13.4289 | 19.9214 | 24.5155 | 0
9.1031 | 8.6723 | 2.1034 | 2.1552 | 3.5172 | 3.3103 | 7.7758 | 5.6206 | 17.7754 | 19.9305 | 27.7063 | 33.3269 | 9.1031 | 8.6723 | 2.1034 | 2.1552 | 3.5272 | 3.3103 | 7.7758 | 5.6206 | 17.7754 | 19.9305 | 27.7063 | 33.3269 | 0
7.6437 | 8.3561 | 2.0548 | 2.0822 | 3.2739 | 3.1644 | 7.4109 | 5.3287 | 15.9998 | 18.082 | 25.4929 | 30.8217 | 7.6437 | 8.3561 | 2.0548 | 2.0822 | 3.2839 | 3.1644 | 7.4109 | 5.3287 | 15.9998 | 18.082 | 25.4929 | 30.8217 | 0
7.4801 | 8.3207 | 2.0493 | 2.074 | 3.2467 | 3.148 | 7.37 | 5.296 | 15.8008 | 17.8748 | 25.2449 | 30.5409 | 7.4801 | 8.3207 | 2.0493 | 2.074 | 3.2567 | 3.148 | 7.37 | 5.296 | 15.8008 | 17.8748 | 25.2449 | 30.5409 | 0
15.1289 | 9.9779 | 2.3043 | 2.4564 | 4.5215 | 3.9129 | 9.2822 | 6.8258 | 25.1068 | 27.5633 | 36.8455 | 43.6713 | 15.1289 | 9.9779 | 2.3043 | 2.4564 | 4.5315 | 3.9129 | 9.2822 | 6.8258 | 25.1068 | 27.5633 | 36.8455 | 43.6713 | 0
0.75091 | 6.8627 | 1.825 | 1.7375 | 2.1252 | 2.4751 | 5.6877 | 3.9502 | 7.6136 | 9.3512 | 15.0389 | 18.9891 | 0.75091 | 6.8627 | 1.825 | 1.7375 | 2.1352 | 2.4751 | 5.6877 | 3.9502 | 7.6136 | 9.3512 | 15.0389 | 18.9891 | 0
1.9654 | 7.1258 | 1.8655 | 1.7983 | 2.3276 | 2.5965 | 5.9914 | 4.1931 | 9.0912 | 10.8895 | 16.8809 | 21.0739 | 1.9654 | 7.1258 | 1.8655 | 1.7983 | 2.3376 | 2.5965 | 5.9914 | 4.1931 | 9.0912 | 10.8895 | 16.8809 | 21.0739 | 0
9.8869 | 8.8422 | 2.1296 | 2.1943 | 3.6478 | 3.3887 | 7.9717 | 5.7774 | 18.7291 | 20.9234 | 28.8951 | 34.6725 | 9.8869 | 8.8422 | 2.1296 | 2.1943 | 3.6578 | 3.3887 | 7.9717 | 5.7774 | 18.7291 | 20.9234 | 28.8951 | 34.6725 | 0
6.4668 | 8.1011 | 2.0156 | 2.0233 | 3.0778 | 3.0467 | 7.1167 | 5.0934 | 14.5679 | 16.5913 | 23.708 | 28.8013 | 6.4668 | 8.1011 | 2.0156 | 2.0233 | 3.0878 | 3.0467 | 7.1167 | 5.0934 | 14.5679 | 16.5913 | 23.708 | 28.8013 | 0
7.8432 | 8.3994 | 2.0614 | 2.0922 | 3.3072 | 3.1843 | 7.4608 | 5.3686 | 16.2426 | 18.3348 | 25.7956 | 31.1642 | 7.8432 | 8.3994 | 2.0614 | 2.0922 | 3.3172 | 3.1843 | 7.4608 | 5.3686 | 16.2426 | 18.3348 | 25.7956 | 31.1642 | 0
3.9091 | 7.547 | 1.9303 | 1.8955 | 2.6515 | 2.7909 | 6.4773 | 4.5818 | 11.456 | 13.3515 | 19.8288 | 24.4106 | 3.9091 | 7.547 | 1.9303 | 1.8955 | 2.6615 | 2.7909 | 6.4773 | 4.5818 | 11.456 | 13.3515 | 19.8288 | 24.4106 | 0
3.4369 | 7.4447 | 1.9146 | 1.8718 | 2.5728 | 2.7437 | 6.3592 | 4.4874 | 10.8815 | 12.7533 | 19.1126 | 23.5999 | 3.4369 | 7.4447 | 1.9146 | 1.8718 | 2.5828 | 2.7437 | 6.3592 | 4.4874 | 10.8815 | 12.7533 | 19.1126 | 23.5999 | 0
16.7592 | 10.3312 | 2.3586 | 2.538 | 4.7932 | 4.0759 | 9.6898 | 7.1518 | 27.0903 | 29.6283 | 39.3181 | 46.4699 | 16.7592 | 10.3312 | 2.3586 | 2.538 | 4.8032 | 4.0759 | 9.6898 | 7.1518 | 27.0903 | 29.6283 | 39.3181 | 46.4699 | 0
-4.8476 | 5.6497 | 1.6384 | 1.4576 | 1.1921 | 1.9152 | 4.2881 | 2.8305 | 0.80204 | 2.2597 | 6.5478 | 9.3782 | -4.8476 | 5.6497 | 1.6384 | 1.4576 | 1.2021 | 1.9152 | 4.2881 | 2.8305 | 0.80204 | 2.2597 | 6.5478 | 9.3782 | 0
4.8571 | 7.7524 | 1.9619 | 1.9429 | 2.8095 | 2.8857 | 6.7143 | 4.7714 | 12.6094 | 14.5523 | 21.2665 | 26.038 | 4.8571 | 7.7524 | 1.9619 | 1.9429 | 2.8195 | 2.8857 | 6.7143 | 4.7714 | 12.6094 | 14.5523 | 21.2665 | 26.038 | 0
15.5217 | 10.063 | 2.3174 | 2.4761 | 4.587 | 3.9522 | 9.3804 | 6.9043 | 25.5847 | 28.0608 | 37.4412 | 44.3456 | 15.5217 | 10.063 | 2.3174 | 2.4761 | 4.597 | 3.9522 | 9.3804 | 6.9043 | 25.5847 | 28.0608 | 37.4412 | 44.3456 | 0
4.5272 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7054 | 12.2081 | 14.1344 | 20.7662 | 25.4717 | 4.5272 | 7.6809 | 1.9509 | 1.9264 | 2.7645 | 2.8527 | 6.6318 | 4.7054 | 12.2081 | 14.1344 | 20.7662 | 25.4717 | 0
-6.9383 | 5.1967 | 1.5687 | 1.3531 | 0.84362 | 1.7062 | 3.7654 | 2.4123 | -1.7415 | -0.38845 | 3.377 | 5.7893 | -6.9383 | 5.1967 | 1.5687 | 1.3531 | 0.85362 | 1.7062 | 3.7654 | 2.4123 | -1.7415 | -0.38845 | 3.377 | 5.7893 | 0
16.9328 | 10.3688 | 2.3644 | 2.5466 | 4.8221 | 4.0933 | 9.7332 | 7.1866 | 27.3016 | 29.8482 | 39.5814 | 46.768 | 16.9328 | 10.3688 | 2.3644 | 2.5466 | 4.8321 | 4.0933 | 9.7332 | 7.1866 | 27.3016 | 29.8482 | 39.5814 | 46.768 | 0
14.0968 | 9.7543 | 2.2699 | 2.4048 | 4.3495 | 3.8097 | 9.0242 | 6.6194 | 23.8511 | 26.2559 | 35.2801 | 41.8995 | 14.0968 | 9.7543 | 2.2699 | 2.4048 | 4.3595 | 3.8097 | 9.0242 | 6.6194 | 23.8511 | 26.2559 | 35.2801 | 41.8995 | 0
21.6875 | 11.399 | 2.5229 | 2.7844 | 5.6146 | 4.5687 | 10.9219 | 8.1375 | 33.0864 | 35.8708 | 46.7927 | 54.9302 | 21.6875 | 11.399 | 2.5229 | 2.7844 | 5.6246 | 4.5687 | 10.9219 | 8.1375 | 33.0864 | 35.8708 | 46.7927 | 54.9302 | 0
14.6441 | 9.8729 | 2.2881 | 2.4322 | 4.4407 | 3.8644 | 9.161 | 6.7288 | 24.5169 | 26.9491 | 36.1102 | 42.839 | 14.6441 | 9.8729 | 2.2881 | 2.4322 | 4.4507 | 3.8644 | 9.161 | 6.7288 | 24.5169 | 26.9491 | 36.1102 | 42.839 | 0
0.7403 | 6.8604 | 1.8247 | 1.737 | 2.1234 | 2.474 | 5.6851 | 3.9481 | 7.6007 | 9.3377 | 15.0228 | 18.9709 | 0.7403 | 6.8604 | 1.8247 | 1.737 | 2.1334 | 2.474 | 5.6851 | 3.9481 | 7.6007 | 9.3377 | 15.0228 | 18.9709 | 0
0.19334 | 6.7419 | 1.8064 | 1.7097 | 2.0322 | 2.4193 | 5.5483 | 3.8387 | 6.9352 | 8.6449 | 14.1932 | 18.0319 | 0.19334 | 6.7419 | 1.8064 | 1.7097 | 2.0422 | 2.4193 | 5.5483 | 3.8387 | 6.9352 | 8.6449 | 14.1932 | 18.0319 | 0
8.7563 | 8.5972 | 2.0919 | 2.1378 | 3.4594 | 3.2756 | 7.6891 | 5.5513 | 17.3534 | 19.4913 | 27.1803 | 32.7316 | 8.7563 | 8.5972 | 2.0919 | 2.1378 | 3.4694 | 3.2756 | 7.6891 | 5.5513 | 17.3534 | 19.4913 | 27.1803 | 32.7316 | 0
8.0989 | 8.4548 | 2.07 | 2.1049 | 3.3498 | 3.2099 | 7.5247 | 5.4198 | 16.5537 | 18.6586 | 26.1833 | 31.6031 | 8.0989 | 8.4548 | 2.07 | 2.1049 | 3.3598 | 3.2099 | 7.5247 | 5.4198 | 16.5537 | 18.6586 | 26.1833 | 31.6031 | 0
-3.4729 | 5.9475 | 1.6842 | 1.5264 | 1.4212 | 2.0527 | 4.6318 | 3.1054 | 2.4746 | 4.0009 | 8.6327 | 11.7381 | -3.4729 | 5.9475 | 1.6842 | 1.5264 | 1.4312 | 2.0527 | 4.6318 | 3.1054 | 2.4746 | 4.0009 | 8.6327 | 11.7381 | 0
0.19703 | 6.7427 | 1.8066 | 1.7099 | 2.0328 | 2.4197 | 5.5493 | 3.8394 | 6.9397 | 8.6496 | 14.1988 | 18.0382 | 0.19703 | 6.7427 | 1.8066 | 1.7099 | 2.0428 | 2.4197 | 5.5493 | 3.8394 | 6.9397 | 8.6496 | 14.1988 | 18.0382 | 0
2.1437 | 7.1645 | 1.8715 | 1.8072 | 2.3573 | 2.6144 | 6.0359 | 4.2287 | 9.3082 | 11.1154 | 17.1513 | 21.38 | 2.1437 | 7.1645 | 1.8715 | 1.8072 | 2.3673 | 2.6144 | 6.0359 | 4.2287 | 9.3082 | 11.1154 | 17.1513 | 21.38 | 0
2.1804 | 7.1724 | 1.8727 | 1.809 | 2.3634 | 2.618 | 6.0451 | 4.2361 | 9.3528 | 11.1618 | 17.2069 | 21.443 | 2.1804 | 7.1724 | 1.8727 | 1.809 | 2.3734 | 2.618 | 6.0451 | 4.2361 | 9.3528 | 11.1618 | 17.2069 | 21.443 | 0
8.4919 | 8.5399 | 2.0831 | 2.1246 | 3.4153 | 3.2492 | 7.623 | 5.4984 | 17.0318 | 19.1564 | 26.7793 | 32.2777 | 8.4919 | 8.5399 | 2.0831 | 2.1246 | 3.4253 | 3.2492 | 7.623 | 5.4984 | 17.0318 | 19.1564 | 26.7793 | 32.2777 | 0
-0.30742 | 6.6334 | 1.7898 | 1.6846 | 1.9488 | 2.3693 | 5.4231 | 3.7385 | 6.326 | 8.0106 | 13.4337 | 17.1723 | -0.30742 | 6.6334 | 1.7898 | 1.6846 | 1.9588 | 2.3693 | 5.4231 | 3.7385 | 6.326 | 8.0106 | 13.4337 | 17.1723 | 0
5.7009 | 7.9352 | 1.99 | 1.985 | 2.9501 | 2.9701 | 6.9252 | 4.9402 | 13.6361 | 15.6211 | 22.5463 | 27.4865 | 5.7009 | 7.9352 | 1.99 | 1.985 | 2.9601 | 2.9701 | 6.9252 | 4.9402 | 13.6361 | 15.6211 | 22.5463 | 27.4865 | 0
3.9954 | 7.5657 | 1.9332 | 1.8998 | 2.6659 | 2.7995 | 6.4988 | 4.5991 | 11.561 | 13.4608 | 19.9596 | 24.5587 | 3.9954 | 7.5657 | 1.9332 | 1.8998 | 2.6759 | 2.7995 | 6.4988 | 4.5991 | 11.561 | 13.4608 | 19.9596 | 24.5587 | 0
2.8736 | 7.3226 | 1.8958 | 1.8437 | 2.4789 | 2.6874 | 6.2184 | 4.3747 | 10.1962 | 12.0399 | 18.2583 | 22.633 | 2.8736 | 7.3226 | 1.8958 | 1.8437 | 2.4889 | 2.6874 | 6.2184 | 4.3747 | 10.1962 | 12.0399 | 18.2583 | 22.633 | 0
7.4078 | 8.305 | 2.0469 | 2.0704 | 3.2346 | 3.1408 | 7.352 | 5.2816 | 15.7128 | 17.7832 | 25.1352 | 30.4167 | 7.4078 | 8.305 | 2.0469 | 2.0704 | 3.2446 | 3.1408 | 7.352 | 5.2816 | 15.7128 | 17.7832 | 25.1352 | 30.4167 | 0
4.6413 | 7.7056 | 1.9547 | 1.9321 | 2.7735 | 2.8641 | 6.6603 | 4.7283 | 12.3469 | 14.2789 | 20.9392 | 25.6675 | 4.6413 | 7.7056 | 1.9547 | 1.9321 | 2.7835 | 2.8641 | 6.6603 | 4.7283 | 12.3469 | 14.2789 | 20.9392 | 25.6675 | 0
17.8399 | 10.5653 | 2.3947 | 2.592 | 4.9733 | 4.184 | 9.96 | 7.368 | 28.4052 | 30.9972 | 40.9571 | 48.3251 | 17.8399 | 10.5653 | 2.3947 | 2.592 | 4.9833 | 4.184 | 9.96 | 7.368 | 28.4052 | 30.9972 | 40.9571 | 48.3251 | 0
10.3126 | 8.9344 | 2.1438 | 2.2156 | 3.7188 | 3.4313 | 8.0782 | 5.8625 | 19.2471 | 21.4627 | 29.5409 | 35.4034 | 10.3126 | 8.9344 | 2.1438 | 2.2156 | 3.7288 | 3.4313 | 8.0782 | 5.8625 | 19.2471 | 21.4627 | 29.5409 | 35.4034 | 0
0.93636 | 6.9029 | 1.8312 | 1.7468 | 2.1561 | 2.4936 | 5.7341 | 3.9873 | 7.8392 | 9.5861 | 15.3201 | 19.3074 | 0.93636 | 6.9029 | 1.8312 | 1.7468 | 2.1661 | 2.4936 | 5.7341 | 3.9873 | 7.8392 | 9.5861 | 15.3201 | 19.3074 | 0
5.9171 | 7.982 | 1.9972 | 1.9959 | 2.9862 | 2.9917 | 6.9793 | 4.9834 | 13.8992 | 15.8951 | 22.8743 | 27.8578 | 5.9171 | 7.982 | 1.9972 | 1.9959 | 2.9962 | 2.9917 | 6.9793 | 4.9834 | 13.8992 | 15.8951 | 22.8743 | 27.8578 | 0
14.2609 | 9.7899 | 2.2754 | 2.413 | 4.3768 | 3.8261 | 9.0652 | 6.6522 | 24.0507 | 26.4638 | 35.529 | 42.1812 | 14.2609 | 9.7899 | 2.2754 | 2.413 | 4.3868 | 3.8261 | 9.0652 | 6.6522 | 24.0507 | 26.4638 | 35.529 | 42.1812 | 0
4.7586 | 7.731 | 1.9586 | 1.9379 | 2.7931 | 2.8759 | 6.6897 | 4.7517 | 12.4897 | 14.4276 | 21.1173 | 25.869 | 4.7586 | 7.731 | 1.9586 | 1.9379 | 2.8031 | 2.8759 | 6.6897 | 4.7517 | 12.4897 | 14.4276 | 21.1173 | 25.869 | 0
-1.5358 | 6.3672 | 1.7488 | 1.6232 | 1.744 | 2.2464 | 5.116 | 3.4928 | 4.8314 | 6.4546 | 11.5707 | 15.0635 | -1.5358 | 6.3672 | 1.7488 | 1.6232 | 1.754 | 2.2464 | 5.116 | 3.4928 | 4.8314 | 6.4546 | 11.5707 | 15.0635 | 0
4.5187 | 7.6791 | 1.9506 | 1.9259 | 2.7531 | 2.8519 | 6.6297 | 4.7037 | 12.1977 | 14.1237 | 20.7534 | 25.4571 | 4.5187 | 7.6791 | 1.9506 | 1.9259 | 2.7631 | 2.8519 | 6.6297 | 4.7037 | 12.1977 | 14.1237 | 20.7534 | 25.4571 | 0
10.9318 | 9.0686 | 2.1644 | 2.2466 | 3.822 | 3.4932 | 8.233 | 5.9864 | 20.0004 | 22.247 | 30.4799 | 36.4663 | 10.9318 | 9.0686 | 2.1644 | 2.2466 | 3.832 | 3.4932 | 8.233 | 5.9864 | 20.0004 | 22.247 | 30.4799 | 36.4663 | 0
3.7619 | 7.5151 | 1.9254 | 1.8881 | 2.627 | 2.7762 | 6.4405 | 4.5524 | 11.2769 | 13.165 | 19.6055 | 24.1579 | 3.7619 | 7.5151 | 1.9254 | 1.8881 | 2.637 | 2.7762 | 6.4405 | 4.5524 | 11.2769 | 13.165 | 19.6055 | 24.1579 | 0
0.66962 | 6.8451 | 1.8223 | 1.7335 | 2.1116 | 2.467 | 5.6674 | 3.9339 | 7.5147 | 9.2482 | 14.9156 | 18.8495 | 0.66962 | 6.8451 | 1.8223 | 1.7335 | 2.1216 | 2.467 | 5.6674 | 3.9339 | 7.5147 | 9.2482 | 14.9156 | 18.8495 | 0
8.4453 | 8.5298 | 2.0815 | 2.1223 | 3.4076 | 3.2445 | 7.6113 | 5.4891 | 16.9752 | 19.0974 | 26.7088 | 32.1978 | 8.4453 | 8.5298 | 2.0815 | 2.1223 | 3.4176 | 3.2445 | 7.6113 | 5.4891 | 16.9752 | 19.0974 | 26.7088 | 32.1978 | 0
4 | 7.5667 | 1.9333 | 1.9 | 2.6667 | 2.8 | 6.5 | 4.6 | 11.5666 | 13.4666 | 19.9666 | 24.5666 | 4 | 7.5667 | 1.9333 | 1.9 | 2.6767 | 2.8 | 6.5 | 4.6 | 11.5666 | 13.4666 | 19.9666 | 24.5666 | 0
0.11313 | 6.7245 | 1.8038 | 1.7057 | 2.0189 | 2.4113 | 5.5283 | 3.8226 | 6.8376 | 8.5433 | 14.0716 | 17.8942 | 0.11313 | 6.7245 | 1.8038 | 1.7057 | 2.0289 | 2.4113 | 5.5283 | 3.8226 | 6.8376 | 8.5433 | 14.0716 | 17.8942 | 0
14.3302 | 9.8049 | 2.2777 | 2.4165 | 4.3884 | 3.833 | 9.0825 | 6.666 | 24.135 | 26.5516 | 35.6341 | 42.3001 | 14.3302 | 9.8049 | 2.2777 | 2.4165 | 4.3984 | 3.833 | 9.0825 | 6.666 | 24.135 | 26.5516 | 35.6341 | 42.3001 | 0
0.82956 | 6.8797 | 1.8277 | 1.7415 | 2.1383 | 2.483 | 5.7074 | 3.9659 | 7.7093 | 9.4508 | 15.1582 | 19.1241 | 0.82956 | 6.8797 | 1.8277 | 1.7415 | 2.1483 | 2.483 | 5.7074 | 3.9659 | 7.7093 | 9.4508 | 15.1582 | 19.1241 | 0
6.5365 | 8.1162 | 2.0179 | 2.0268 | 3.0894 | 3.0537 | 7.1341 | 5.1073 | 14.6528 | 16.6796 | 23.8137 | 28.921 | 6.5365 | 8.1162 | 2.0179 | 2.0268 | 3.0994 | 3.0537 | 7.1341 | 5.1073 | 14.6528 | 16.6796 | 23.8137 | 28.921 | 0
2.4857 | 7.2386 | 1.8829 | 1.8243 | 2.4143 | 2.6486 | 6.1214 | 4.2971 | 9.7243 | 11.5486 | 17.67 | 21.9671 | 2.4857 | 7.2386 | 1.8829 | 1.8243 | 2.4243 | 2.6486 | 6.1214 | 4.2971 | 9.7243 | 11.5486 | 17.67 | 21.9671 | 0
9.4618 | 8.7501 | 2.1154 | 2.1731 | 3.577 | 3.3462 | 7.8655 | 5.6924 | 18.2119 | 20.385 | 28.2504 | 33.9428 | 9.4618 | 8.7501 | 2.1154 | 2.1731 | 3.587 | 3.3462 | 7.8655 | 5.6924 | 18.2119 | 20.385 | 28.2504 | 33.9428 | 0
10.5152 | 8.9783 | 2.1505 | 2.2258 | 3.7525 | 3.4515 | 8.1288 | 5.903 | 19.4935 | 21.7193 | 29.8481 | 35.7511 | 10.5152 | 8.9783 | 2.1505 | 2.2258 | 3.7625 | 3.4515 | 8.1288 | 5.903 | 19.4935 | 21.7193 | 29.8481 | 35.7511 | 0
13.8852 | 9.7085 | 2.2628 | 2.3943 | 4.3142 | 3.7885 | 8.9713 | 6.577 | 23.5937 | 25.9879 | 34.9592 | 41.5363 | 13.8852 | 9.7085 | 2.2628 | 2.3943 | 4.3242 | 3.7885 | 8.9713 | 6.577 | 23.5937 | 25.9879 | 34.9592 | 41.5363 | 0
7.4114 | 8.3058 | 2.047 | 2.0706 | 3.2352 | 3.1411 | 7.3529 | 5.2823 | 15.7172 | 17.7878 | 25.1406 | 30.4229 | 7.4114 | 8.3058 | 2.047 | 2.0706 | 3.2452 | 3.1411 | 7.3529 | 5.2823 | 15.7172 | 17.7878 | 25.1406 | 30.4229 | 0
3.3173 | 7.4187 | 1.9106 | 1.8659 | 2.5529 | 2.7317 | 6.3293 | 4.4635 | 10.736 | 12.6019 | 18.9312 | 23.3947 | 3.3173 | 7.4187 | 1.9106 | 1.8659 | 2.5629 | 2.7317 | 6.3293 | 4.4635 | 10.736 | 12.6019 | 18.9312 | 23.3947 | 0
6.514 | 8.1114 | 2.0171 | 2.0257 | 3.0857 | 3.0514 | 7.1285 | 5.1028 | 14.6253 | 16.651 | 23.7795 | 28.8823 | 6.514 | 8.1114 | 2.0171 | 2.0257 | 3.0957 | 3.0514 | 7.1285 | 5.1028 | 14.6253 | 16.651 | 23.7795 | 28.8823 | 0
-0.5379 | 6.5835 | 1.7821 | 1.6731 | 1.9104 | 2.3462 | 5.3655 | 3.6924 | 6.0456 | 7.7187 | 13.0842 | 16.7766 | -0.5379 | 6.5835 | 1.7821 | 1.6731 | 1.9204 | 2.3462 | 5.3655 | 3.6924 | 6.0456 | 7.7187 | 13.0842 | 16.7766 | 0
1.9903 | 7.1312 | 1.8663 | 1.7995 | 2.3317 | 2.599 | 5.9976 | 4.1981 | 9.1215 | 10.9211 | 16.9186 | 21.1167 | 1.9903 | 7.1312 | 1.8663 | 1.7995 | 2.3417 | 2.599 | 5.9976 | 4.1981 | 9.1215 | 10.9211 | 16.9186 | 21.1167 | 0
17.5171 | 10.4954 | 2.3839 | 2.5759 | 4.9195 | 4.1517 | 9.8793 | 7.3034 | 28.0125 | 30.5883 | 40.4676 | 47.771 | 17.5171 | 10.4954 | 2.3839 | 2.5759 | 4.9295 | 4.1517 | 9.8793 | 7.3034 | 28.0125 | 30.5883 | 40.4676 | 47.771 | 0
5.7762 | 7.9515 | 1.9925 | 1.9888 | 2.9627 | 2.9776 | 6.9441 | 4.9552 | 13.7277 | 15.7166 | 22.6606 | 27.6159 | 5.7762 | 7.9515 | 1.9925 | 1.9888 | 2.9727 | 2.9776 | 6.9441 | 4.9552 | 13.7277 | 15.7166 | 22.6606 | 27.6159 | 0
5.936 | 7.9861 | 1.9979 | 1.9968 | 2.9893 | 2.9936 | 6.984 | 4.9872 | 13.9222 | 15.919 | 22.903 | 27.8902 | 5.936 | 7.9861 | 1.9979 | 1.9968 | 2.9993 | 2.9936 | 6.984 | 4.9872 | 13.9222 | 15.919 | 22.903 | 27.8902 | 0
-4.9884 | 5.6192 | 1.6337 | 1.4506 | 1.1686 | 1.9012 | 4.2529 | 2.8023 | 0.63082 | 2.0814 | 6.3343 | 9.1366 | -4.9884 | 5.6192 | 1.6337 | 1.4506 | 1.1786 | 1.9012 | 4.2529 | 2.8023 | 0.63082 | 2.0814 | 6.3343 | 9.1366 | 0
4.2438 | 7.6195 | 1.9415 | 1.9122 | 2.7073 | 2.8244 | 6.561 | 4.6488 | 11.8633 | 13.7755 | 20.3365 | 24.9852 | 4.2438 | 7.6195 | 1.9415 | 1.9122 | 2.7173 | 2.8244 | 6.561 | 4.6488 | 11.8633 | 13.7755 | 20.3365 | 24.9852 | 0
8.0514 | 8.4445 | 2.0684 | 2.1026 | 3.3419 | 3.2051 | 7.5128 | 5.4103 | 16.4958 | 18.5984 | 26.1112 | 31.5215 | 8.0514 | 8.4445 | 2.0684 | 2.1026 | 3.3519 | 3.2051 | 7.5128 | 5.4103 | 16.4958 | 18.5984 | 26.1112 | 31.5215 | 0
-8.3684 | 4.8868 | 1.5211 | 1.2816 | 0.60526 | 1.5632 | 3.4079 | 2.1263 | -3.4816 | -2.2 | 1.2079 | 3.3342 | -8.3684 | 4.8868 | 1.5211 | 1.2816 | 0.61526 | 1.5632 | 3.4079 | 2.1263 | -3.4816 | -2.2 | 1.2079 | 3.3342 | 0
10.4473 | 8.9636 | 2.1482 | 2.2224 | 3.7412 | 3.4447 | 8.1118 | 5.8895 | 19.4109 | 21.6333 | 29.7451 | 35.6346 | 10.4473 | 8.9636 | 2.1482 | 2.2224 | 3.7512 | 3.4447 | 8.1118 | 5.8895 | 19.4109 | 21.6333 | 29.7451 | 35.6346 | 0
6.2781 | 8.0603 | 2.0093 | 2.0139 | 3.0463 | 3.0278 | 7.0695 | 5.0556 | 14.3383 | 16.3522 | 23.4218 | 28.4774 | 6.2781 | 8.0603 | 2.0093 | 2.0139 | 3.0563 | 3.0278 | 7.0695 | 5.0556 | 14.3383 | 16.3522 | 23.4218 | 28.4774 | 0
-0.026116 | 6.6943 | 1.7991 | 1.6987 | 1.9956 | 2.3974 | 5.4935 | 3.7948 | 6.6682 | 8.3669 | 13.8604 | 17.6552 | -0.026116 | 6.6943 | 1.7991 | 1.6987 | 2.0056 | 2.3974 | 5.4935 | 3.7948 | 6.6682 | 8.3669 | 13.8604 | 17.6552 | 0
12.3808 | 9.3825 | 2.2127 | 2.319 | 4.0635 | 3.6381 | 8.5952 | 6.2762 | 21.7633 | 24.0823 | 32.6775 | 38.9537 | 12.3808 | 9.3825 | 2.2127 | 2.319 | 4.0735 | 3.6381 | 8.5952 | 6.2762 | 21.7633 | 24.0823 | 32.6775 | 38.9537 | 0
4.3092 | 7.6337 | 1.9436 | 1.9155 | 2.7182 | 2.8309 | 6.5773 | 4.6618 | 11.9428 | 13.8583 | 20.4356 | 25.0974 | 4.3092 | 7.6337 | 1.9436 | 1.9155 | 2.7282 | 2.8309 | 6.5773 | 4.6618 | 11.9428 | 13.8583 | 20.4356 | 25.0974 | 0
9.5463 | 8.7684 | 2.1182 | 2.1773 | 3.591 | 3.3546 | 7.8866 | 5.7093 | 18.3146 | 20.492 | 28.3785 | 34.0878 | 9.5463 | 8.7684 | 2.1182 | 2.1773 | 3.601 | 3.3546 | 7.8866 | 5.7093 | 18.3146 | 20.492 | 28.3785 | 34.0878 | 0
3.7633 | 7.5154 | 1.9254 | 1.8882 | 2.6272 | 2.7763 | 6.4408 | 4.5527 | 11.2787 | 13.1668 | 19.6077 | 24.1603 | 3.7633 | 7.5154 | 1.9254 | 1.8882 | 2.6372 | 2.7763 | 6.4408 | 4.5527 | 11.2787 | 13.1668 | 19.6077 | 24.1603 | 0
8.7658 | 8.5992 | 2.0922 | 2.1383 | 3.461 | 3.2766 | 7.6914 | 5.5532 | 17.365 | 19.5033 | 27.1947 | 32.7479 | 8.7658 | 8.5992 | 2.0922 | 2.1383 | 3.471 | 3.2766 | 7.6914 | 5.5532 | 17.365 | 19.5033 | 27.1947 | 32.7479 | 0
0.69767 | 6.8512 | 1.8233 | 1.7349 | 2.1163 | 2.4698 | 5.6744 | 3.9395 | 7.5488 | 9.2837 | 14.9581 | 18.8977 | 0.69767 | 6.8512 | 1.8233 | 1.7349 | 2.1263 | 2.4698 | 5.6744 | 3.9395 | 7.5488 | 9.2837 | 14.9581 | 18.8977 | 0
11.5977 | 9.2128 | 2.1866 | 2.2799 | 3.9329 | 3.5598 | 8.3994 | 6.1195 | 20.8105 | 23.0904 | 31.4898 | 37.6094 | 11.5977 | 9.2128 | 2.1866 | 2.2799 | 3.9429 | 3.5598 | 8.3994 | 6.1195 | 20.8105 | 23.0904 | 31.4898 | 37.6094 | 0
8.4712 | 8.5354 | 2.0824 | 2.1236 | 3.4119 | 3.2471 | 7.6178 | 5.4942 | 17.0067 | 19.1302 | 26.748 | 32.2423 | 8.4712 | 8.5354 | 2.0824 | 2.1236 | 3.4219 | 3.2471 | 7.6178 | 5.4942 | 17.0067 | 19.1302 | 26.748 | 32.2423 | 0
18.2142 | 10.6464 | 2.4071 | 2.6107 | 5.0357 | 4.2214 | 10.0536 | 7.4428 | 28.8606 | 31.4713 | 41.5249 | 48.9677 | 18.2142 | 10.6464 | 2.4071 | 2.6107 | 5.0457 | 4.2214 | 10.0536 | 7.4428 | 28.8606 | 31.4713 | 41.5249 | 48.9677 | 0
13.8999 | 9.7117 | 2.2633 | 2.395 | 4.3167 | 3.79 | 8.975 | 6.58 | 23.6116 | 26.0066 | 34.9816 | 41.5615 | 13.8999 | 9.7117 | 2.2633 | 2.395 | 4.3267 | 3.79 | 8.975 | 6.58 | 23.6116 | 26.0066 | 34.9816 | 41.5615 | 0
6.3636 | 8.0788 | 2.0121 | 2.0182 | 3.0606 | 3.0364 | 7.0909 | 5.0727 | 14.4424 | 16.4605 | 23.5514 | 28.6242 | 6.3636 | 8.0788 | 2.0121 | 2.0182 | 3.0706 | 3.0364 | 7.0909 | 5.0727 | 14.4424 | 16.4605 | 23.5514 | 28.6242 | 0
6.9097 | 8.1971 | 2.0303 | 2.0455 | 3.1516 | 3.091 | 7.2274 | 5.1819 | 15.1068 | 17.1523 | 24.3797 | 29.5616 | 6.9097 | 8.1971 | 2.0303 | 2.0455 | 3.1616 | 3.091 | 7.2274 | 5.1819 | 15.1068 | 17.1523 | 24.3797 | 29.5616 | 0
1.1273 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7818 | 4.0255 | 8.0716 | 9.8279 | 15.6098 | 19.6352 | 1.1273 | 6.9443 | 1.8376 | 1.7564 | 2.1979 | 2.5127 | 5.7818 | 4.0255 | 8.0716 | 9.8279 | 15.6098 | 19.6352 | 0
15.8964 | 10.1442 | 2.3299 | 2.4948 | 4.6494 | 3.9896 | 9.4741 | 6.9793 | 26.0407 | 28.5355 | 38.0096 | 44.9889 | 15.8964 | 10.1442 | 2.3299 | 2.4948 | 4.6594 | 3.9896 | 9.4741 | 6.9793 | 26.0407 | 28.5355 | 38.0096 | 44.9889 | 0
6.1089 | 8.0236 | 2.0036 | 2.0054 | 3.0181 | 3.0109 | 7.0272 | 5.0218 | 14.1325 | 16.1379 | 23.1651 | 28.1869 | 6.1089 | 8.0236 | 2.0036 | 2.0054 | 3.0281 | 3.0109 | 7.0272 | 5.0218 | 14.1325 | 16.1379 | 23.1651 | 28.1869 | 0
0.25643 | 6.7556 | 1.8085 | 1.7128 | 2.0427 | 2.4256 | 5.5641 | 3.8513 | 7.012 | 8.7248 | 14.2889 | 18.1402 | 0.25643 | 6.7556 | 1.8085 | 1.7128 | 2.0527 | 2.4256 | 5.5641 | 3.8513 | 7.012 | 8.7248 | 14.2889 | 18.1402 | 0
-4.2332 | 5.7828 | 1.6589 | 1.4883 | 1.2945 | 1.9767 | 4.4417 | 2.9534 | 1.5496 | 3.038 | 7.4797 | 10.433 | -4.2332 | 5.7828 | 1.6589 | 1.4883 | 1.3045 | 1.9767 | 4.4417 | 2.9534 | 1.5496 | 3.038 | 7.4797 | 10.433 | 0
3.0006 | 7.3501 | 1.9 | 1.85 | 2.5001 | 2.7001 | 6.2501 | 4.4001 | 10.3507 | 12.2007 | 18.4509 | 22.851 | 3.0006 | 7.3501 | 1.9 | 1.85 | 2.5101 | 2.7001 | 6.2501 | 4.4001 | 10.3507 | 12.2007 | 18.4509 | 22.851 | 0
-0.019623 | 6.6957 | 1.7993 | 1.699 | 1.9967 | 2.398 | 5.4951 | 3.7961 | 6.6761 | 8.3751 | 13.8702 | 17.6663 | -0.019623 | 6.6957 | 1.7993 | 1.699 | 2.0067 | 2.398 | 5.4951 | 3.7961 | 6.6761 | 8.3751 | 13.8702 | 17.6663 | 0
1.7234 | 7.0734 | 1.8574 | 1.7862 | 2.2872 | 2.5723 | 5.9308 | 4.1447 | 8.7968 | 10.583 | 16.5138 | 20.6585 | 1.7234 | 7.0734 | 1.8574 | 1.7862 | 2.2972 | 2.5723 | 5.9308 | 4.1447 | 8.7968 | 10.583 | 16.5138 | 20.6585 | 0
17.9337 | 10.5856 | 2.3978 | 2.5967 | 4.9889 | 4.1934 | 9.9834 | 7.3867 | 28.5193 | 31.116 | 41.0994 | 48.4862 | 17.9337 | 10.5856 | 2.3978 | 2.5967 | 4.9989 | 4.1934 | 9.9834 | 7.3867 | 28.5193 | 31.116 | 41.0994 | 48.4862 | 0
5.9536 | 7.9899 | 1.9985 | 1.9977 | 2.9923 | 2.9954 | 6.9884 | 4.9907 | 13.9435 | 15.9412 | 22.9296 | 27.9203 | 5.9536 | 7.9899 | 1.9985 | 1.9977 | 3.0023 | 2.9954 | 6.9884 | 4.9907 | 13.9435 | 15.9412 | 22.9296 | 27.9203 | 0
8.1286 | 8.4612 | 2.071 | 2.1064 | 3.3548 | 3.2129 | 7.5321 | 5.4257 | 16.5897 | 18.6962 | 26.2283 | 31.654 | 8.1286 | 8.4612 | 2.071 | 2.1064 | 3.3648 | 3.2129 | 7.5321 | 5.4257 | 16.5897 | 18.6962 | 26.2283 | 31.654 | 0
0.99013 | 6.9145 | 1.833 | 1.7495 | 2.165 | 2.499 | 5.7475 | 3.998 | 7.9047 | 9.6542 | 15.4017 | 19.3997 | 0.99013 | 6.9145 | 1.833 | 1.7495 | 2.175 | 2.499 | 5.7475 | 3.998 | 7.9047 | 9.6542 | 15.4017 | 19.3997 | 0
9.9327 | 8.8521 | 2.1311 | 2.1966 | 3.6554 | 3.3933 | 7.9832 | 5.7865 | 18.7847 | 20.9814 | 28.9645 | 34.7511 | 9.9327 | 8.8521 | 2.1311 | 2.1966 | 3.6654 | 3.3933 | 7.9832 | 5.7865 | 18.7847 | 20.9814 | 28.9645 | 34.7511 | 0
13.1113 | 9.5408 | 2.237 | 2.3556 | 4.1852 | 3.7111 | 8.7778 | 6.4223 | 22.6521 | 25.0077 | 33.7855 | 40.2078 | 13.1113 | 9.5408 | 2.237 | 2.3556 | 4.1952 | 3.7111 | 8.7778 | 6.4223 | 22.6521 | 25.0077 | 33.7855 | 40.2078 | 0
3.9177 | 7.5488 | 1.9306 | 1.8959 | 2.6529 | 2.7918 | 6.4794 | 4.5835 | 11.4665 | 13.3624 | 19.8418 | 24.4253 | 3.9177 | 7.5488 | 1.9306 | 1.8959 | 2.6629 | 2.7918 | 6.4794 | 4.5835 | 11.4665 | 13.3624 | 19.8418 | 24.4253 | 0
4.0887 | 7.5859 | 1.9363 | 1.9044 | 2.6814 | 2.8089 | 6.5222 | 4.6177 | 11.6745 | 13.579 | 20.1011 | 24.7189 | 4.0887 | 7.5859 | 1.9363 | 1.9044 | 2.6914 | 2.8089 | 6.5222 | 4.6177 | 11.6745 | 13.579 | 20.1011 | 24.7189 | 0
-0.055066 | 6.6881 | 1.7982 | 1.6972 | 1.9908 | 2.3945 | 5.4862 | 3.789 | 6.633 | 8.3303 | 13.8165 | 17.6055 | -0.055066 | 6.6881 | 1.7982 | 1.6972 | 2.0008 | 2.3945 | 5.4862 | 3.789 | 6.633 | 8.3303 | 13.8165 | 17.6055 | 0
3.9499 | 7.5558 | 1.9317 | 1.8975 | 2.6583 | 2.795 | 6.4875 | 4.59 | 11.5057 | 13.4032 | 19.8906 | 24.4806 | 3.9499 | 7.5558 | 1.9317 | 1.8975 | 2.6683 | 2.795 | 6.4875 | 4.59 | 11.5057 | 13.4032 | 19.8906 | 24.4806 | 0
2.5412 | 7.2506 | 1.8847 | 1.8271 | 2.4235 | 2.6541 | 6.1353 | 4.3082 | 9.7918 | 11.6189 | 17.7542 | 22.0624 | 2.5412 | 7.2506 | 1.8847 | 1.8271 | 2.4335 | 2.6541 | 6.1353 | 4.3082 | 9.7918 | 11.6189 | 17.7542 | 22.0624 | 0
-1.6705 | 6.3381 | 1.7443 | 1.6165 | 1.7216 | 2.233 | 5.0824 | 3.4659 | 4.6676 | 6.2841 | 11.3664 | 14.8323 | -1.6705 | 6.3381 | 1.7443 | 1.6165 | 1.7316 | 2.233 | 5.0824 | 3.4659 | 4.6676 | 6.2841 | 11.3664 | 14.8323 | 0
17.8938 | 10.577 | 2.3965 | 2.5947 | 4.9823 | 4.1894 | 9.9734 | 7.3788 | 28.4708 | 31.0655 | 41.0389 | 48.4177 | 17.8938 | 10.577 | 2.3965 | 2.5947 | 4.9923 | 4.1894 | 9.9734 | 7.3788 | 28.4708 | 31.0655 | 41.0389 | 48.4177 | 0
2.6217 | 7.268 | 1.8874 | 1.8311 | 2.4369 | 2.6622 | 6.1554 | 4.3243 | 9.8897 | 11.7208 | 17.8762 | 22.2005 | 2.6217 | 7.268 | 1.8874 | 1.8311 | 2.4469 | 2.6622 | 6.1554 | 4.3243 | 9.8897 | 11.7208 | 17.8762 | 22.2005 | 0
6.531 | 8.1151 | 2.0177 | 2.0266 | 3.0885 | 3.0531 | 7.1328 | 5.1062 | 14.6461 | 16.6726 | 23.8054 | 28.9116 | 6.531 | 8.1151 | 2.0177 | 2.0266 | 3.0985 | 3.0531 | 7.1328 | 5.1062 | 14.6461 | 16.6726 | 23.8054 | 28.9116 | 0
-0.63752 | 6.5619 | 1.7787 | 1.6681 | 1.8937 | 2.3362 | 5.3406 | 3.6725 | 5.9244 | 7.5925 | 12.9331 | 16.6056 | -0.63752 | 6.5619 | 1.7787 | 1.6681 | 1.9037 | 2.3362 | 5.3406 | 3.6725 | 5.9244 | 7.5925 | 12.9331 | 16.6056 | 0
3.242 | 7.4024 | 1.9081 | 1.8621 | 2.5403 | 2.7242 | 6.3105 | 4.4484 | 10.6444 | 12.5065 | 18.817 | 23.2654 | 3.242 | 7.4024 | 1.9081 | 1.8621 | 2.5503 | 2.7242 | 6.3105 | 4.4484 | 10.6444 | 12.5065 | 18.817 | 23.2654 | 0
7.7059 | 8.3696 | 2.0569 | 2.0853 | 3.2843 | 3.1706 | 7.4265 | 5.3412 | 16.0755 | 18.1608 | 25.5873 | 30.9285 | 7.7059 | 8.3696 | 2.0569 | 2.0853 | 3.2943 | 3.1706 | 7.4265 | 5.3412 | 16.0755 | 18.1608 | 25.5873 | 30.9285 | 0
5.5315 | 7.8985 | 1.9844 | 1.9766 | 2.9219 | 2.9532 | 6.8829 | 4.9063 | 13.43 | 15.4066 | 22.2895 | 27.1958 | 5.5315 | 7.8985 | 1.9844 | 1.9766 | 2.9319 | 2.9532 | 6.8829 | 4.9063 | 13.43 | 15.4066 | 22.2895 | 27.1958 | 0
6.2875 | 8.0623 | 2.0096 | 2.0144 | 3.0479 | 3.0288 | 7.0719 | 5.0575 | 14.3498 | 16.3642 | 23.4361 | 28.4936 | 6.2875 | 8.0623 | 2.0096 | 2.0144 | 3.0579 | 3.0288 | 7.0719 | 5.0575 | 14.3498 | 16.3642 | 23.4361 | 28.4936 | 0
8.8478 | 8.617 | 2.0949 | 2.1424 | 3.4746 | 3.2848 | 7.7119 | 5.5696 | 17.4648 | 19.6072 | 27.3191 | 32.8887 | 8.8478 | 8.617 | 2.0949 | 2.1424 | 3.4846 | 3.2848 | 7.7119 | 5.5696 | 17.4648 | 19.6072 | 27.3191 | 32.8887 | 0
3.6485 | 7.4905 | 1.9216 | 1.8824 | 2.6081 | 2.7648 | 6.4121 | 4.5297 | 11.139 | 13.0214 | 19.4335 | 23.9632 | 3.6485 | 7.4905 | 1.9216 | 1.8824 | 2.6181 | 2.7648 | 6.4121 | 4.5297 | 11.139 | 13.0214 | 19.4335 | 23.9632 | 0
4.5406 | 7.6838 | 1.9514 | 1.927 | 2.7568 | 2.8541 | 6.6352 | 4.7081 | 12.2244 | 14.1515 | 20.7866 | 25.4947 | 4.5406 | 7.6838 | 1.9514 | 1.927 | 2.7668 | 2.8541 | 6.6352 | 4.7081 | 12.2244 | 14.1515 | 20.7866 | 25.4947 | 0
7.2969 | 8.281 | 2.0432 | 2.0648 | 3.2162 | 3.1297 | 7.3242 | 5.2594 | 15.5779 | 17.6428 | 24.967 | 30.2264 | 7.2969 | 8.281 | 2.0432 | 2.0648 | 3.2262 | 3.1297 | 7.3242 | 5.2594 | 15.5779 | 17.6428 | 24.967 | 30.2264 | 0
7.5894 | 8.3444 | 2.053 | 2.0795 | 3.2649 | 3.1589 | 7.3974 | 5.3179 | 15.9338 | 18.0133 | 25.4106 | 30.7285 | 7.5894 | 8.3444 | 2.053 | 2.0795 | 3.2749 | 3.1589 | 7.3974 | 5.3179 | 15.9338 | 18.0133 | 25.4106 | 30.7285 | 0
-1.186 | 6.443 | 1.7605 | 1.6407 | 1.8023 | 2.2814 | 5.2035 | 3.5628 | 5.257 | 6.8977 | 12.1012 | 15.664 | -1.186 | 6.443 | 1.7605 | 1.6407 | 1.8123 | 2.2814 | 5.2035 | 3.5628 | 5.257 | 6.8977 | 12.1012 | 15.664 | 0
7.5221 | 8.3298 | 2.0507 | 2.0761 | 3.2537 | 3.1522 | 7.3805 | 5.3044 | 15.8519 | 17.928 | 25.3085 | 30.6129 | 7.5221 | 8.3298 | 2.0507 | 2.0761 | 3.2637 | 3.1522 | 7.3805 | 5.3044 | 15.8519 | 17.928 | 25.3085 | 30.6129 | 0
4.1728 | 7.6041 | 1.9391 | 1.9086 | 2.6955 | 2.8173 | 6.5432 | 4.6346 | 11.7769 | 13.6856 | 20.2288 | 24.8633 | 4.1728 | 7.6041 | 1.9391 | 1.9086 | 2.7055 | 2.8173 | 6.5432 | 4.6346 | 11.7769 | 13.6856 | 20.2288 | 24.8633 | 0
10.0312 | 8.8734 | 2.1344 | 2.2016 | 3.6719 | 3.4031 | 8.0078 | 5.8062 | 18.9047 | 21.1062 | 29.114 | 34.9203 | 10.0312 | 8.8734 | 2.1344 | 2.2016 | 3.6819 | 3.4031 | 8.0078 | 5.8062 | 18.9047 | 21.1062 | 29.114 | 34.9203 | 0
1.8924 | 7.11 | 1.8631 | 1.7946 | 2.3154 | 2.5892 | 5.9731 | 4.1785 | 9.0025 | 10.7971 | 16.7702 | 20.9487 | 1.8924 | 7.11 | 1.8631 | 1.7946 | 2.3254 | 2.5892 | 5.9731 | 4.1785 | 9.0025 | 10.7971 | 16.7702 | 20.9487 | 0
16.936 | 10.3695 | 2.3645 | 2.5468 | 4.8227 | 4.0936 | 9.734 | 7.1872 | 27.3054 | 29.8522 | 39.5862 | 46.7734 | 16.936 | 10.3695 | 2.3645 | 2.5468 | 4.8327 | 4.0936 | 9.734 | 7.1872 | 27.3054 | 29.8522 | 39.5862 | 46.7734 | 0
7.2675 | 8.2746 | 2.0422 | 2.0634 | 3.2112 | 3.1267 | 7.3169 | 5.2535 | 15.5421 | 17.6055 | 24.9223 | 30.1758 | 7.2675 | 8.2746 | 2.0422 | 2.0634 | 3.2212 | 3.1267 | 7.3169 | 5.2535 | 15.5421 | 17.6055 | 24.9223 | 30.1758 | 0
5.0004 | 7.7834 | 1.9667 | 1.95 | 2.8334 | 2.9 | 6.7501 | 4.8001 | 12.7839 | 14.7339 | 21.484 | 26.2841 | 5.0004 | 7.7834 | 1.9667 | 1.95 | 2.8434 | 2.9 | 6.7501 | 4.8001 | 12.7839 | 14.7339 | 21.484 | 26.2841 | 0
8.22 | 8.481 | 2.074 | 2.111 | 3.37 | 3.222 | 7.555 | 5.444 | 16.7011 | 18.8121 | 26.3671 | 31.8111 | 8.22 | 8.481 | 2.074 | 2.111 | 3.38 | 3.222 | 7.555 | 5.444 | 16.7011 | 18.8121 | 26.3671 | 31.8111 | 0
15.5054 | 10.0595 | 2.3168 | 2.4753 | 4.5842 | 3.9505 | 9.3763 | 6.9011 | 25.5649 | 28.0401 | 37.4165 | 44.3175 | 15.5054 | 10.0595 | 2.3168 | 2.4753 | 4.5942 | 3.9505 | 9.3763 | 6.9011 | 25.5649 | 28.0401 | 37.4165 | 44.3175 | 0
1.1288 | 6.9446 | 1.8376 | 1.7564 | 2.1881 | 2.5129 | 5.7822 | 4.0258 | 8.0734 | 9.8299 | 15.6121 | 19.6378 | 1.1288 | 6.9446 | 1.8376 | 1.7564 | 2.1981 | 2.5129 | 5.7822 | 4.0258 | 8.0734 | 9.8299 | 15.6121 | 19.6378 | 0
0.42329 | 6.7917 | 1.8141 | 1.7212 | 2.0705 | 2.4423 | 5.6058 | 3.8847 | 7.215 | 8.9362 | 14.542 | 18.4267 | 0.42329 | 6.7917 | 1.8141 | 1.7212 | 2.0805 | 2.4423 | 5.6058 | 3.8847 | 7.215 | 8.9362 | 14.542 | 18.4267 | 0
6.5131 | 8.1112 | 2.0171 | 2.0257 | 3.0855 | 3.0513 | 7.1283 | 5.1026 | 14.6242 | 16.6499 | 23.7781 | 28.8807 | 6.5131 | 8.1112 | 2.0171 | 2.0257 | 3.0955 | 3.0513 | 7.1283 | 5.1026 | 14.6242 | 16.6499 | 23.7781 | 28.8807 | 0
-0.42709 | 6.6075 | 1.7858 | 1.6786 | 1.9288 | 2.3573 | 5.3932 | 3.7146 | 6.1804 | 7.859 | 13.2522 | 16.9668 | -0.42709 | 6.6075 | 1.7858 | 1.6786 | 1.9388 | 2.3573 | 5.3932 | 3.7146 | 6.1804 | 7.859 | 13.2522 | 16.9668 | 0
3.3855 | 7.4335 | 1.9129 | 1.8693 | 2.5643 | 2.7386 | 6.3464 | 4.4771 | 10.8191 | 12.6883 | 19.0347 | 23.5118 | 3.3855 | 7.4335 | 1.9129 | 1.8693 | 2.5743 | 2.7386 | 6.3464 | 4.4771 | 10.8191 | 12.6883 | 19.0347 | 23.5118 | 0
9.2592 | 8.7062 | 2.1086 | 2.163 | 3.5432 | 3.3259 | 7.8148 | 5.6518 | 17.9653 | 20.1283 | 27.9431 | 33.5949 | 9.2592 | 8.7062 | 2.1086 | 2.163 | 3.5532 | 3.3259 | 7.8148 | 5.6518 | 17.9653 | 20.1283 | 27.9431 | 33.5949 | 0
0.34898 | 6.7756 | 1.8116 | 1.7174 | 2.0582 | 2.4349 | 5.5872 | 3.8698 | 7.1246 | 8.842 | 14.4293 | 18.2991 | 0.34898 | 6.7756 | 1.8116 | 1.7174 | 2.0682 | 2.4349 | 5.5872 | 3.8698 | 7.1246 | 8.842 | 14.4293 | 18.2991 | 0
14.8692 | 9.9217 | 2.2956 | 2.4435 | 4.4782 | 3.8869 | 9.2173 | 6.7738 | 24.7908 | 27.2343 | 36.4516 | 43.2254 | 14.8692 | 9.9217 | 2.2956 | 2.4435 | 4.4882 | 3.8869 | 9.2173 | 6.7738 | 24.7908 | 27.2343 | 36.4516 | 43.2254 | 0
14.2324 | 9.7837 | 2.2744 | 2.4116 | 4.3721 | 3.8232 | 9.0581 | 6.6465 | 24.0161 | 26.4277 | 35.4858 | 42.1323 | 14.2324 | 9.7837 | 2.2744 | 2.4116 | 4.3821 | 3.8232 | 9.0581 | 6.6465 | 24.0161 | 26.4277 | 35.4858 | 42.1323 | 0
-3.7799 | 5.881 | 1.674 | 1.511 | 1.37 | 2.022 | 4.555 | 3.044 | 2.1012 | 3.6122 | 8.1672 | 11.2112 | -3.7799 | 5.881 | 1.674 | 1.511 | 1.38 | 2.022 | 4.555 | 3.044 | 2.1012 | 3.6122 | 8.1672 | 11.2112 | 0
5.3413 | 7.8573 | 1.978 | 1.9671 | 2.8902 | 2.9341 | 6.8353 | 4.8683 | 13.1986 | 15.1657 | 22.001 | 26.8693 | 5.3413 | 7.8573 | 1.978 | 1.9671 | 2.9002 | 2.9341 | 6.8353 | 4.8683 | 13.1986 | 15.1657 | 22.001 | 26.8693 | 0
13.6643 | 9.6606 | 2.2555 | 2.3832 | 4.2774 | 3.7664 | 8.9161 | 6.5329 | 23.3249 | 25.7081 | 34.6242 | 41.157 | 13.6643 | 9.6606 | 2.2555 | 2.3832 | 4.2874 | 3.7664 | 8.9161 | 6.5329 | 23.3249 | 25.7081 | 34.6242 | 41.157 | 0
17.2063 | 10.428 | 2.3735 | 2.5603 | 4.8677 | 4.1206 | 9.8016 | 7.2413 | 27.6343 | 30.1946 | 39.9962 | 47.2374 | 17.2063 | 10.428 | 2.3735 | 2.5603 | 4.8777 | 4.1206 | 9.8016 | 7.2413 | 27.6343 | 30.1946 | 39.9962 | 47.2374 | 0
8.2493 | 8.4874 | 2.075 | 2.1125 | 3.3749 | 3.2249 | 7.5623 | 5.4499 | 16.7367 | 18.8491 | 26.4115 | 31.8613 | 8.2493 | 8.4874 | 2.075 | 2.1125 | 3.3849 | 3.2249 | 7.5623 | 5.4499 | 16.7367 | 18.8491 | 26.4115 | 31.8613 | 0
5.4441 | 7.8796 | 1.9815 | 1.9722 | 2.9074 | 2.9444 | 6.861 | 4.8888 | 13.3237 | 15.2959 | 22.1569 | 27.0457 | 5.4441 | 7.8796 | 1.9815 | 1.9722 | 2.9174 | 2.9444 | 6.861 | 4.8888 | 13.3237 | 15.2959 | 22.1569 | 27.0457 | 0
0.4585 | 6.7993 | 1.8153 | 1.7229 | 2.0764 | 2.4459 | 5.6146 | 3.8917 | 7.2578 | 8.9808 | 14.5954 | 18.4871 | 0.4585 | 6.7993 | 1.8153 | 1.7229 | 2.0864 | 2.4459 | 5.6146 | 3.8917 | 7.2578 | 8.9808 | 14.5954 | 18.4871 | 0
-0.038013 | 6.6918 | 1.7987 | 1.6981 | 1.9937 | 2.3962 | 5.4905 | 3.7924 | 6.6538 | 8.3519 | 13.8423 | 17.6347 | -0.038013 | 6.6918 | 1.7987 | 1.6981 | 2.0037 | 2.3962 | 5.4905 | 3.7924 | 6.6538 | 8.3519 | 13.8423 | 17.6347 | 0
11.8839 | 9.2749 | 2.1961 | 2.2942 | 3.9807 | 3.5884 | 8.471 | 6.1768 | 21.1588 | 23.453 | 31.924 | 38.1008 | 11.8839 | 9.2749 | 2.1961 | 2.2942 | 3.9907 | 3.5884 | 8.471 | 6.1768 | 21.1588 | 23.453 | 31.924 | 38.1008 | 0
-3.1106 | 6.026 | 1.6963 | 1.5445 | 1.4816 | 2.0889 | 4.7224 | 3.1779 | 2.9155 | 4.4599 | 9.1823 | 12.3602 | -3.1106 | 6.026 | 1.6963 | 1.5445 | 1.4916 | 2.0889 | 4.7224 | 3.1779 | 2.9155 | 4.4599 | 9.1823 | 12.3602 | 0
2.154 | 7.1667 | 1.8718 | 1.8077 | 2.359 | 2.6154 | 6.0385 | 4.2308 | 9.3207 | 11.1284 | 17.1669 | 21.3977 | 2.154 | 7.1667 | 1.8718 | 1.8077 | 2.369 | 2.6154 | 6.0385 | 4.2308 | 9.3207 | 11.1284 | 17.1669 | 21.3977 | 0
7.67 | 8.3618 | 2.0557 | 2.0835 | 3.2783 | 3.167 | 7.4175 | 5.334 | 16.0319 | 18.1154 | 25.5329 | 30.8669 | 7.67 | 8.3618 | 2.0557 | 2.0835 | 3.2883 | 3.167 | 7.4175 | 5.334 | 16.0319 | 18.1154 | 25.5329 | 30.8669 | 0
15.8604 | 10.1364 | 2.3287 | 2.493 | 4.6434 | 3.986 | 9.4651 | 6.9721 | 25.9968 | 28.4898 | 37.9549 | 44.927 | 15.8604 | 10.1364 | 2.3287 | 2.493 | 4.6534 | 3.986 | 9.4651 | 6.9721 | 25.9968 | 28.4898 | 37.9549 | 44.927 | 0
-1.0877 | 6.4643 | 1.7637 | 1.6456 | 1.8187 | 2.2912 | 5.2281 | 3.5825 | 5.3766 | 7.0222 | 12.2503 | 15.8327 | -1.0877 | 6.4643 | 1.7637 | 1.6456 | 1.8287 | 2.2912 | 5.2281 | 3.5825 | 5.3766 | 7.0222 | 12.2503 | 15.8327 | 0
9.5656 | 8.7725 | 2.1189 | 2.1783 | 3.5943 | 3.3566 | 7.8914 | 5.7131 | 18.3381 | 20.5164 | 28.4078 | 34.1209 | 9.5656 | 8.7725 | 2.1189 | 2.1783 | 3.6043 | 3.3566 | 7.8914 | 5.7131 | 18.3381 | 20.5164 | 28.4078 | 34.1209 | 0
5.2751 | 7.8429 | 1.9758 | 1.9638 | 2.8792 | 2.9275 | 6.8188 | 4.855 | 13.1181 | 15.0818 | 21.9006 | 26.7557 | 5.2751 | 7.8429 | 1.9758 | 1.9638 | 2.8892 | 2.9275 | 6.8188 | 4.855 | 13.1181 | 15.0818 | 21.9006 | 26.7557 | 0
4.8547 | 7.7519 | 1.9618 | 1.9427 | 2.8091 | 2.8855 | 6.7137 | 4.7709 | 12.6066 | 14.5493 | 21.263 | 26.0339 | 4.8547 | 7.7519 | 1.9618 | 1.9427 | 2.8191 | 2.8855 | 6.7137 | 4.7709 | 12.6066 | 14.5493 | 21.263 | 26.0339 | 0
4.1225 | 7.5932 | 1.9374 | 1.9061 | 2.6871 | 2.8123 | 6.5306 | 4.6245 | 11.7157 | 13.6219 | 20.1525 | 24.777 | 4.1225 | 7.5932 | 1.9374 | 1.9061 | 2.6971 | 2.8123 | 6.5306 | 4.6245 | 11.7157 | 13.6219 | 20.1525 | 24.777 | 0
0.12817 | 6.7278 | 1.8043 | 1.7064 | 2.0214 | 2.4128 | 5.532 | 3.8256 | 6.8559 | 8.5623 | 14.0944 | 17.92 | 0.12817 | 6.7278 | 1.8043 | 1.7064 | 2.0314 | 2.4128 | 5.532 | 3.8256 | 6.8559 | 8.5623 | 14.0944 | 17.92 | 0
3.1497 | 7.3824 | 1.905 | 1.8575 | 2.525 | 2.715 | 6.2874 | 4.4299 | 10.5322 | 12.3897 | 18.6771 | 23.107 | 3.1497 | 7.3824 | 1.905 | 1.8575 | 2.535 | 2.715 | 6.2874 | 4.4299 | 10.5322 | 12.3897 | 18.6771 | 23.107 | 0
0.004088 | 6.7009 | 1.8001 | 1.7002 | 2.0007 | 2.4004 | 5.501 | 3.8008 | 6.705 | 8.4052 | 13.9062 | 17.707 | 0.004088 | 6.7009 | 1.8001 | 1.7002 | 2.0107 | 2.4004 | 5.501 | 3.8008 | 6.705 | 8.4052 | 13.9062 | 17.707 | 0
2.664 | 7.2772 | 1.8888 | 1.8332 | 2.444 | 2.6664 | 6.166 | 4.3328 | 9.9412 | 11.7744 | 17.9403 | 22.2731 | 2.664 | 7.2772 | 1.8888 | 1.8332 | 2.454 | 2.6664 | 6.166 | 4.3328 | 9.9412 | 11.7744 | 17.9403 | 22.2731 | 0
16.3601 | 10.2447 | 2.3453 | 2.518 | 4.7267 | 4.036 | 9.59 | 7.072 | 26.6047 | 29.1227 | 38.7127 | 45.7848 | 16.3601 | 10.2447 | 2.3453 | 2.518 | 4.7367 | 4.036 | 9.59 | 7.072 | 26.6047 | 29.1227 | 38.7127 | 45.7848 | 0
1.1157 | 6.9417 | 1.8372 | 1.7558 | 2.186 | 2.5116 | 5.7789 | 4.0231 | 8.0575 | 9.8133 | 15.5922 | 19.6153 | 1.1157 | 6.9417 | 1.8372 | 1.7558 | 2.196 | 2.5116 | 5.7789 | 4.0231 | 8.0575 | 9.8133 | 15.5922 | 19.6153 | 0
8.3578 | 8.5109 | 2.0786 | 2.1179 | 3.393 | 3.2358 | 7.5894 | 5.4716 | 16.8686 | 18.9865 | 26.576 | 32.0475 | 8.3578 | 8.5109 | 2.0786 | 2.1179 | 3.403 | 3.2358 | 7.5894 | 5.4716 | 16.8686 | 18.9865 | 26.576 | 32.0475 | 0
-3.237 | 5.9986 | 1.6921 | 1.5381 | 1.4605 | 2.0763 | 4.6907 | 3.1526 | 2.7616 | 4.2998 | 8.9905 | 12.1431 | -3.237 | 5.9986 | 1.6921 | 1.5381 | 1.4705 | 2.0763 | 4.6907 | 3.1526 | 2.7616 | 4.2998 | 8.9905 | 12.1431 | 0
3.8189 | 7.5274 | 1.9273 | 1.8909 | 2.6365 | 2.7819 | 6.4547 | 4.5638 | 11.3463 | 13.2373 | 19.692 | 24.2558 | 3.8189 | 7.5274 | 1.9273 | 1.8909 | 2.6465 | 2.7819 | 6.4547 | 4.5638 | 11.3463 | 13.2373 | 19.692 | 24.2558 | 0
9.7219 | 8.8064 | 2.1241 | 2.1861 | 3.6203 | 3.3722 | 7.9305 | 5.7444 | 18.5283 | 20.7144 | 28.6448 | 34.3892 | 9.7219 | 8.8064 | 2.1241 | 2.1861 | 3.6303 | 3.3722 | 7.9305 | 5.7444 | 18.5283 | 20.7144 | 28.6448 | 34.3892 | 0
8.9915 | 8.6482 | 2.0997 | 2.1496 | 3.4986 | 3.2992 | 7.7479 | 5.5983 | 17.6397 | 19.7893 | 27.5372 | 33.1355 | 8.9915 | 8.6482 | 2.0997 | 2.1496 | 3.5086 | 3.2992 | 7.7479 | 5.5983 | 17.6397 | 19.7893 | 27.5372 | 33.1355 | 0
-3.6954 | 5.8993 | 1.6768 | 1.5152 | 1.3841 | 2.0305 | 4.5762 | 3.0609 | 2.2039 | 3.7192 | 8.2953 | 11.3562 | -3.6954 | 5.8993 | 1.6768 | 1.5152 | 1.3941 | 2.0305 | 4.5762 | 3.0609 | 2.2039 | 3.7192 | 8.2953 | 11.3562 | 0
10.0738 | 8.8827 | 2.1358 | 2.2037 | 3.679 | 3.4074 | 8.0185 | 5.8148 | 18.9565 | 21.1602 | 29.1787 | 34.9934 | 10.0738 | 8.8827 | 2.1358 | 2.2037 | 3.689 | 3.4074 | 8.0185 | 5.8148 | 18.9565 | 21.1602 | 29.1787 | 34.9934 | 0
0.046038 | 6.71 | 1.8015 | 1.7023 | 2.0077 | 2.4046 | 5.5115 | 3.8092 | 6.756 | 8.4583 | 13.9698 | 17.779 | 0.046038 | 6.71 | 1.8015 | 1.7023 | 2.0177 | 2.4046 | 5.5115 | 3.8092 | 6.756 | 8.4583 | 13.9698 | 17.779 | 0
11.9431 | 9.2877 | 2.1981 | 2.2972 | 3.9905 | 3.5943 | 8.4858 | 6.1886 | 21.2308 | 23.528 | 32.0138 | 38.2024 | 11.9431 | 9.2877 | 2.1981 | 2.2972 | 4.0005 | 3.5943 | 8.4858 | 6.1886 | 21.2308 | 23.528 | 32.0138 | 38.2024 | 0
10.2351 | 8.9176 | 2.1412 | 2.2118 | 3.7058 | 3.4235 | 8.0588 | 5.847 | 19.1527 | 21.3645 | 29.4232 | 35.2703 | 10.2351 | 8.9176 | 2.1412 | 2.2118 | 3.7158 | 3.4235 | 8.0588 | 5.847 | 19.1527 | 21.3645 | 29.4232 | 35.2703 | 0
16.0073 | 10.1682 | 2.3336 | 2.5004 | 4.6679 | 4.0007 | 9.5018 | 7.0015 | 26.1755 | 28.6759 | 38.1777 | 45.1791 | 16.0073 | 10.1682 | 2.3336 | 2.5004 | 4.6779 | 4.0007 | 9.5018 | 7.0015 | 26.1755 | 28.6759 | 38.1777 | 45.1791 | 0
11.2117 | 9.1292 | 2.1737 | 2.2606 | 3.8686 | 3.5212 | 8.3029 | 6.0423 | 20.3409 | 22.6015 | 30.9044 | 36.9468 | 11.2117 | 9.1292 | 2.1737 | 2.2606 | 3.8786 | 3.5212 | 8.3029 | 6.0423 | 20.3409 | 22.6015 | 30.9044 | 36.9468 | 0
0.7651 | 6.8658 | 1.8255 | 1.7383 | 2.1275 | 2.4765 | 5.6913 | 3.953 | 7.6309 | 9.3691 | 15.0604 | 19.0134 | 0.7651 | 6.8658 | 1.8255 | 1.7383 | 2.1375 | 2.4765 | 5.6913 | 3.953 | 7.6309 | 9.3691 | 15.0604 | 19.0134 | 0
-2.5424 | 6.1491 | 1.7153 | 1.5729 | 1.5763 | 2.1458 | 4.8644 | 3.2915 | 3.6068 | 5.1796 | 10.044 | 13.3356 | -2.5424 | 6.1491 | 1.7153 | 1.5729 | 1.5863 | 2.1458 | 4.8644 | 3.2915 | 3.6068 | 5.1796 | 10.044 | 13.3356 | 0
6.6128 | 8.1328 | 2.0204 | 2.0306 | 3.1021 | 3.0613 | 7.1532 | 5.1226 | 14.7456 | 16.7763 | 23.9295 | 29.052 | 6.6128 | 8.1328 | 2.0204 | 2.0306 | 3.1121 | 3.0613 | 7.1532 | 5.1226 | 14.7456 | 16.7763 | 23.9295 | 29.052 | 0
-0.13011 | 6.6718 | 1.7957 | 1.6935 | 1.9783 | 2.387 | 5.4675 | 3.774 | 6.5417 | 8.2352 | 13.7027 | 17.4766 | -0.13011 | 6.6718 | 1.7957 | 1.6935 | 1.9883 | 2.387 | 5.4675 | 3.774 | 6.5417 | 8.2352 | 13.7027 | 17.4766 | 0
2.5146 | 7.2448 | 1.8838 | 1.8257 | 2.4191 | 2.6515 | 6.1286 | 4.3029 | 9.7594 | 11.5851 | 17.7138 | 22.0167 | 2.5146 | 7.2448 | 1.8838 | 1.8257 | 2.4291 | 2.6515 | 6.1286 | 4.3029 | 9.7594 | 11.5851 | 17.7138 | 22.0167 | 0
14.496 | 9.8408 | 2.2832 | 2.4248 | 4.416 | 3.8496 | 9.124 | 6.6992 | 24.3368 | 26.7616 | 35.8856 | 42.5848 | 14.496 | 9.8408 | 2.2832 | 2.4248 | 4.426 | 3.8496 | 9.124 | 6.6992 | 24.3368 | 26.7616 | 35.8856 | 42.5848 | 0
6.3767 | 8.0816 | 2.0126 | 2.0188 | 3.0628 | 3.0377 | 7.0942 | 5.0753 | 14.4583 | 16.4771 | 23.5713 | 28.6466 | 6.3767 | 8.0816 | 2.0126 | 2.0188 | 3.0728 | 3.0377 | 7.0942 | 5.0753 | 14.4583 | 16.4771 | 23.5713 | 28.6466 | 0
-0.66363 | 6.5562 | 1.7779 | 1.6668 | 1.8894 | 2.3336 | 5.3341 | 3.6673 | 5.8926 | 7.5594 | 12.8935 | 16.5608 | -0.66363 | 6.5562 | 1.7779 | 1.6668 | 1.8994 | 2.3336 | 5.3341 | 3.6673 | 5.8926 | 7.5594 | 12.8935 | 16.5608 | 0
6.6236 | 8.1351 | 2.0208 | 2.0312 | 3.1039 | 3.0624 | 7.1559 | 5.1247 | 14.7587 | 16.7899 | 23.9458 | 29.0705 | 6.6236 | 8.1351 | 2.0208 | 2.0312 | 3.1139 | 3.0624 | 7.1559 | 5.1247 | 14.7587 | 16.7899 | 23.9458 | 29.0705 | 0
-1.4404 | 6.3879 | 1.752 | 1.628 | 1.7599 | 2.256 | 5.1399 | 3.5119 | 4.9476 | 6.5755 | 11.7155 | 15.2274 | -1.4404 | 6.3879 | 1.752 | 1.628 | 1.7699 | 2.256 | 5.1399 | 3.5119 | 4.9476 | 6.5755 | 11.7155 | 15.2274 | 0
3.8707 | 7.5386 | 1.929 | 1.8935 | 2.6451 | 2.7871 | 6.4677 | 4.5741 | 11.4093 | 13.3029 | 19.7705 | 24.3447 | 3.8707 | 7.5386 | 1.929 | 1.8935 | 2.6551 | 2.7871 | 6.4677 | 4.5741 | 11.4093 | 13.3029 | 19.7705 | 24.3447 | 0
-11.3239 | 4.2465 | 1.4225 | 1.1338 | 0.11268 | 1.2676 | 2.669 | 1.5352 | -7.0774 | -5.9436 | -3.2746 | -1.7394 | -11.3239 | 4.2465 | 1.4225 | 1.1338 | 0.12268 | 1.2676 | 2.669 | 1.5352 | -7.0774 | -5.9436 | -3.2746 | -1.7394 | 0
8.374 | 8.5144 | 2.0791 | 2.1187 | 3.3957 | 3.2374 | 7.5935 | 5.4748 | 16.8884 | 19.0071 | 26.6006 | 32.0754 | 8.374 | 8.5144 | 2.0791 | 2.1187 | 3.4057 | 3.2374 | 7.5935 | 5.4748 | 16.8884 | 19.0071 | 26.6006 | 32.0754 | 0
12.9704 | 9.5102 | 2.2323 | 2.3485 | 4.1617 | 3.697 | 8.7426 | 6.3941 | 22.4806 | 24.8291 | 33.5717 | 39.9658 | 12.9704 | 9.5102 | 2.2323 | 2.3485 | 4.1717 | 3.697 | 8.7426 | 6.3941 | 22.4806 | 24.8291 | 33.5717 | 39.9658 | 0
1.7719 | 7.0839 | 1.8591 | 1.7886 | 2.2953 | 2.5772 | 5.943 | 4.1544 | 8.8558 | 10.6444 | 16.5874 | 20.7418 | 1.7719 | 7.0839 | 1.8591 | 1.7886 | 2.3053 | 2.5772 | 5.943 | 4.1544 | 8.8558 | 10.6444 | 16.5874 | 20.7418 | 0
-0.26064 | 6.6435 | 1.7913 | 1.687 | 1.9566 | 2.3739 | 5.4348 | 3.7479 | 6.3829 | 8.0699 | 13.5047 | 17.2526 | -0.26064 | 6.6435 | 1.7913 | 1.687 | 1.9666 | 2.3739 | 5.4348 | 3.7479 | 6.3829 | 8.0699 | 13.5047 | 17.2526 | 0
8.9346 | 8.6358 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7336 | 5.5869 | 17.5704 | 19.7171 | 27.4507 | 33.0376 | 8.9346 | 8.6358 | 2.0978 | 2.1467 | 3.4991 | 3.2935 | 7.7336 | 5.5869 | 17.5704 | 19.7171 | 27.4507 | 33.0376 | 0
8.9889 | 8.6476 | 2.0996 | 2.1494 | 3.4981 | 3.2989 | 7.7472 | 5.5978 | 17.6365 | 19.7859 | 27.5332 | 33.1309 | 8.9889 | 8.6476 | 2.0996 | 2.1494 | 3.5081 | 3.2989 | 7.7472 | 5.5978 | 17.6365 | 19.7859 | 27.5332 | 33.1309 | 0
5.2835 | 7.8448 | 1.9761 | 1.9642 | 2.8806 | 2.9284 | 6.8209 | 4.8567 | 13.1283 | 15.0925 | 21.9133 | 26.77 | 5.2835 | 7.8448 | 1.9761 | 1.9642 | 2.8906 | 2.9284 | 6.8209 | 4.8567 | 13.1283 | 15.0925 | 21.9133 | 26.77 | 0
9.4524 | 8.748 | 2.1151 | 2.1726 | 3.5754 | 3.3452 | 7.8631 | 5.6905 | 18.2004 | 20.373 | 28.2361 | 33.9266 | 9.4524 | 8.748 | 2.1151 | 2.1726 | 3.5854 | 3.3452 | 7.8631 | 5.6905 | 18.2004 | 20.373 | 28.2361 | 33.9266 | 0
12.1174 | 9.3254 | 2.2039 | 2.3059 | 4.0196 | 3.6117 | 8.5294 | 6.2235 | 21.4429 | 23.7487 | 32.2781 | 38.5016 | 12.1174 | 9.3254 | 2.2039 | 2.3059 | 4.0296 | 3.6117 | 8.5294 | 6.2235 | 21.4429 | 23.7487 | 32.2781 | 38.5016 | 0
2.5021 | 7.2421 | 1.8834 | 1.8251 | 2.417 | 2.6502 | 6.1255 | 4.3004 | 9.7443 | 11.5694 | 17.6949 | 21.9953 | 2.5021 | 7.2421 | 1.8834 | 1.8251 | 2.427 | 2.6502 | 6.1255 | 4.3004 | 9.7443 | 11.5694 | 17.6949 | 21.9953 | 0
0.91537 | 6.8983 | 1.8305 | 1.7458 | 2.1526 | 2.4915 | 5.7288 | 3.9831 | 7.8137 | 9.5595 | 15.2883 | 19.2714 | 0.91537 | 6.8983 | 1.8305 | 1.7458 | 2.1626 | 2.4915 | 5.7288 | 3.9831 | 7.8137 | 9.5595 | 15.2883 | 19.2714 | 0
-1.7202 | 6.3273 | 1.7427 | 1.614 | 1.7133 | 2.228 | 5.07 | 3.456 | 4.6071 | 6.2211 | 11.2911 | 14.7471 | -1.7202 | 6.3273 | 1.7427 | 1.614 | 1.7233 | 2.228 | 5.07 | 3.456 | 4.6071 | 6.2211 | 11.2911 | 14.7471 | 0
7.3217 | 8.2864 | 2.0441 | 2.0661 | 3.2203 | 3.1322 | 7.3304 | 5.2643 | 15.608 | 17.6741 | 25.0046 | 30.2689 | 7.3217 | 8.2864 | 2.0441 | 2.0661 | 3.2303 | 3.1322 | 7.3304 | 5.2643 | 15.608 | 17.6741 | 25.0046 | 30.2689 | 0
7.9757 | 8.4281 | 2.0659 | 2.0988 | 3.3293 | 3.1976 | 7.4939 | 5.3951 | 16.4037 | 18.5025 | 25.9965 | 31.3916 | 7.9757 | 8.4281 | 2.0659 | 2.0988 | 3.3393 | 3.1976 | 7.4939 | 5.3951 | 16.4037 | 18.5025 | 25.9965 | 31.3916 | 0
-2.8082 | 6.0916 | 1.7064 | 1.5596 | 1.532 | 2.1192 | 4.798 | 3.2384 | 3.2834 | 4.843 | 9.6409 | 12.8793 | -2.8082 | 6.0916 | 1.7064 | 1.5596 | 1.542 | 2.1192 | 4.798 | 3.2384 | 3.2834 | 4.843 | 9.6409 | 12.8793 | 0
-1.3037 | 6.4175 | 1.7565 | 1.6348 | 1.7827 | 2.2696 | 5.1741 | 3.5393 | 5.1139 | 6.7487 | 11.9228 | 15.462 | -1.3037 | 6.4175 | 1.7565 | 1.6348 | 1.7927 | 2.2696 | 5.1741 | 3.5393 | 5.1139 | 6.7487 | 11.9228 | 15.462 | 0
0.17091 | 6.737 | 1.8057 | 1.7085 | 2.0285 | 2.4171 | 5.5427 | 3.8342 | 6.9079 | 8.6165 | 14.1592 | 17.9934 | 0.17091 | 6.737 | 1.8057 | 1.7085 | 2.0385 | 2.4171 | 5.5427 | 3.8342 | 6.9079 | 8.6165 | 14.1592 | 17.9934 | 0
-7.6486 | 5.0428 | 1.545 | 1.3176 | 0.72523 | 1.6351 | 3.5878 | 2.2703 | -2.6058 | -1.2883 | 2.2996 | 4.5698 | -7.6486 | 5.0428 | 1.545 | 1.3176 | 0.73523 | 1.6351 | 3.5878 | 2.2703 | -2.6058 | -1.2883 | 2.2996 | 4.5698 | 0
7.5446 | 8.3347 | 2.0515 | 2.0772 | 3.2574 | 3.1545 | 7.3862 | 5.3089 | 15.8793 | 17.9565 | 25.3427 | 30.6516 | 7.5446 | 8.3347 | 2.0515 | 2.0772 | 3.2674 | 3.1545 | 7.3862 | 5.3089 | 15.8793 | 17.9565 | 25.3427 | 30.6516 | 0
9.7001 | 8.8017 | 2.1233 | 2.185 | 3.6167 | 3.37 | 7.925 | 5.74 | 18.5018 | 20.6869 | 28.6119 | 34.3519 | 9.7001 | 8.8017 | 2.1233 | 2.185 | 3.6267 | 3.37 | 7.925 | 5.74 | 18.5018 | 20.6869 | 28.6119 | 34.3519 | 0
8.0543 | 8.4451 | 2.0685 | 2.1027 | 3.3424 | 3.2054 | 7.5136 | 5.4109 | 16.4994 | 18.6021 | 26.1157 | 31.5266 | 8.0543 | 8.4451 | 2.0685 | 2.1027 | 3.3524 | 3.2054 | 7.5136 | 5.4109 | 16.4994 | 18.6021 | 26.1157 | 31.5266 | 0
-1.2755 | 6.4236 | 1.7575 | 1.6362 | 1.7874 | 2.2725 | 5.1811 | 3.5449 | 5.1482 | 6.7844 | 11.9655 | 15.5104 | -1.2755 | 6.4236 | 1.7575 | 1.6362 | 1.7974 | 2.2725 | 5.1811 | 3.5449 | 5.1482 | 6.7844 | 11.9655 | 15.5104 | 0
1.6532 | 7.0582 | 1.8551 | 1.7827 | 2.2755 | 2.5653 | 5.9133 | 4.1306 | 8.7114 | 10.494 | 16.4073 | 20.538 | 1.6532 | 7.0582 | 1.8551 | 1.7827 | 2.2855 | 2.5653 | 5.9133 | 4.1306 | 8.7114 | 10.494 | 16.4073 | 20.538 | 0
4.0014 | 7.567 | 1.9334 | 1.9001 | 2.6669 | 2.8001 | 6.5004 | 4.6003 | 11.5684 | 13.4685 | 19.9689 | 24.5692 | 4.0014 | 7.567 | 1.9334 | 1.9001 | 2.6769 | 2.8001 | 6.5004 | 4.6003 | 11.5684 | 13.4685 | 19.9689 | 24.5692 | 0
9.7211 | 8.8062 | 2.124 | 2.1861 | 3.6202 | 3.3721 | 7.9303 | 5.7442 | 18.5273 | 20.7134 | 28.6437 | 34.3879 | 9.7211 | 8.8062 | 2.124 | 2.1861 | 3.6302 | 3.3721 | 7.9303 | 5.7442 | 18.5273 | 20.7134 | 28.6437 | 34.3879 | 0
18.4405 | 10.6954 | 2.4147 | 2.622 | 5.0734 | 4.2441 | 10.1101 | 7.4881 | 29.136 | 31.758 | 41.8681 | 49.3562 | 18.4405 | 10.6954 | 2.4147 | 2.622 | 5.0834 | 4.2441 | 10.1101 | 7.4881 | 29.136 | 31.758 | 41.8681 | 49.3562 | 0
6.7586 | 8.1644 | 2.0253 | 2.0379 | 3.1264 | 3.0759 | 7.1896 | 5.1517 | 14.9229 | 16.9609 | 24.1505 | 29.3022 | 6.7586 | 8.1644 | 2.0253 | 2.0379 | 3.1364 | 3.0759 | 7.1896 | 5.1517 | 14.9229 | 16.9609 | 24.1505 | 29.3022 | 0
17.2651 | 10.4408 | 2.3755 | 2.5633 | 4.8775 | 4.1265 | 9.8163 | 7.253 | 27.7059 | 30.2692 | 40.0855 | 47.3385 | 17.2651 | 10.4408 | 2.3755 | 2.5633 | 4.8875 | 4.1265 | 9.8163 | 7.253 | 27.7059 | 30.2692 | 40.0855 | 47.3385 | 0
-4.1978 | 5.7905 | 1.6601 | 1.4901 | 1.3004 | 1.9802 | 4.4506 | 2.9604 | 1.5927 | 3.0828 | 7.5334 | 10.4938 | -4.1978 | 5.7905 | 1.6601 | 1.4901 | 1.3104 | 1.9802 | 4.4506 | 2.9604 | 1.5927 | 3.0828 | 7.5334 | 10.4938 | 0
7.4729 | 8.3191 | 2.0491 | 2.0736 | 3.2455 | 3.1473 | 7.3682 | 5.2946 | 15.7921 | 17.8657 | 25.2339 | 30.5285 | 7.4729 | 8.3191 | 2.0491 | 2.0736 | 3.2555 | 3.1473 | 7.3682 | 5.2946 | 15.7921 | 17.8657 | 25.2339 | 30.5285 | 0
-0.8847 | 6.5083 | 1.7705 | 1.6558 | 1.8525 | 2.3115 | 5.2788 | 3.6231 | 5.6236 | 7.2794 | 12.5582 | 16.1813 | -0.8847 | 6.5083 | 1.7705 | 1.6558 | 1.8625 | 2.3115 | 5.2788 | 3.6231 | 5.6236 | 7.2794 | 12.5582 | 16.1813 | 0
14.5788 | 9.8587 | 2.286 | 2.4289 | 4.4298 | 3.8579 | 9.1447 | 6.7158 | 24.4376 | 26.8665 | 36.0112 | 42.727 | 14.5788 | 9.8587 | 2.286 | 2.4289 | 4.4398 | 3.8579 | 9.1447 | 6.7158 | 24.4376 | 26.8665 | 36.0112 | 42.727 | 0
0.12537 | 6.7272 | 1.8042 | 1.7063 | 2.0209 | 2.4125 | 5.5313 | 3.8251 | 6.8525 | 8.5588 | 14.0901 | 17.9152 | 0.12537 | 6.7272 | 1.8042 | 1.7063 | 2.0309 | 2.4125 | 5.5313 | 3.8251 | 6.8525 | 8.5588 | 14.0901 | 17.9152 | 0
4.2245 | 7.6153 | 1.9408 | 1.9112 | 2.7041 | 2.8224 | 6.5561 | 4.6449 | 11.8398 | 13.751 | 20.3071 | 24.952 | 4.2245 | 7.6153 | 1.9408 | 1.9112 | 2.7141 | 2.8224 | 6.5561 | 4.6449 | 11.8398 | 13.751 | 20.3071 | 24.952 | 0
15.0219 | 9.9547 | 2.3007 | 2.4511 | 4.5036 | 3.9022 | 9.2555 | 6.8044 | 24.9766 | 27.4277 | 36.6832 | 43.4875 | 15.0219 | 9.9547 | 2.3007 | 2.4511 | 4.5136 | 3.9022 | 9.2555 | 6.8044 | 24.9766 | 27.4277 | 36.6832 | 43.4875 | 0
-2.3623 | 6.1882 | 1.7213 | 1.5819 | 1.6063 | 2.1638 | 4.9094 | 3.3275 | 3.8258 | 5.4077 | 10.3171 | 13.6446 | -2.3623 | 6.1882 | 1.7213 | 1.5819 | 1.6163 | 2.1638 | 4.9094 | 3.3275 | 3.8258 | 5.4077 | 10.3171 | 13.6446 | 0
-0.42982 | 6.6069 | 1.7857 | 1.6785 | 1.9284 | 2.357 | 5.3925 | 3.714 | 6.177 | 7.8556 | 13.2481 | 16.9621 | -0.42982 | 6.6069 | 1.7857 | 1.6785 | 1.9384 | 2.357 | 5.3925 | 3.714 | 6.177 | 7.8556 | 13.2481 | 16.9621 | 0
7.7003 | 8.3684 | 2.0567 | 2.085 | 3.2834 | 3.17 | 7.4251 | 5.3401 | 16.0687 | 18.1537 | 25.5788 | 30.9188 | 7.7003 | 8.3684 | 2.0567 | 2.085 | 3.2934 | 3.17 | 7.4251 | 5.3401 | 16.0687 | 18.1537 | 25.5788 | 30.9188 | 0
5.0337 | 7.7906 | 1.9678 | 1.9517 | 2.839 | 2.9034 | 6.7584 | 4.8067 | 12.8244 | 14.776 | 21.5345 | 26.3412 | 5.0337 | 7.7906 | 1.9678 | 1.9517 | 2.849 | 2.9034 | 6.7584 | 4.8067 | 12.8244 | 14.776 | 21.5345 | 26.3412 | 0
3.2793 | 7.4105 | 1.9093 | 1.864 | 2.5465 | 2.7279 | 6.3198 | 4.4559 | 10.6898 | 12.5538 | 18.8736 | 23.3294 | 3.2793 | 7.4105 | 1.9093 | 1.864 | 2.5565 | 2.7279 | 6.3198 | 4.4559 | 10.6898 | 12.5538 | 18.8736 | 23.3294 | 0
-0.40881 | 6.6114 | 1.7864 | 1.6796 | 1.9319 | 2.3591 | 5.3978 | 3.7182 | 6.2026 | 7.8822 | 13.28 | 16.9982 | -0.40881 | 6.6114 | 1.7864 | 1.6796 | 1.9419 | 2.3591 | 5.3978 | 3.7182 | 6.2026 | 7.8822 | 13.28 | 16.9982 | 0
12.3703 | 9.3802 | 2.2123 | 2.3185 | 4.0617 | 3.637 | 8.5926 | 6.2741 | 21.7505 | 24.069 | 32.6616 | 38.9356 | 12.3703 | 9.3802 | 2.2123 | 2.3185 | 4.0717 | 3.637 | 8.5926 | 6.2741 | 21.7505 | 24.069 | 32.6616 | 38.9356 | 0
9.2318 | 8.7002 | 2.1077 | 2.1616 | 3.5386 | 3.3232 | 7.8079 | 5.6464 | 17.932 | 20.0936 | 27.9015 | 33.5479 | 9.2318 | 8.7002 | 2.1077 | 2.1616 | 3.5486 | 3.3232 | 7.8079 | 5.6464 | 17.932 | 20.0936 | 27.9015 | 33.5479 | 0
9.9205 | 8.8494 | 2.1307 | 2.196 | 3.6534 | 3.392 | 7.9801 | 5.7841 | 18.7699 | 20.9659 | 28.946 | 34.7301 | 9.9205 | 8.8494 | 2.1307 | 2.196 | 3.6634 | 3.392 | 7.9801 | 5.7841 | 18.7699 | 20.9659 | 28.946 | 34.7301 | 0
12.8623 | 9.4868 | 2.2287 | 2.3431 | 4.1437 | 3.6862 | 8.7156 | 6.3725 | 22.3491 | 24.6922 | 33.4078 | 39.7802 | 12.8623 | 9.4868 | 2.2287 | 2.3431 | 4.1537 | 3.6862 | 8.7156 | 6.3725 | 22.3491 | 24.6922 | 33.4078 | 39.7802 | 0
-2.6898 | 6.1172 | 1.7103 | 1.5655 | 1.5517 | 2.131 | 4.8276 | 3.262 | 3.4274 | 4.9929 | 9.8205 | 13.0825 | -2.6898 | 6.1172 | 1.7103 | 1.5655 | 1.5617 | 2.131 | 4.8276 | 3.262 | 3.4274 | 4.9929 | 9.8205 | 13.0825 | 0
10.976 | 9.0781 | 2.1659 | 2.2488 | 3.8293 | 3.4976 | 8.244 | 5.9952 | 20.0542 | 22.303 | 30.547 | 36.5422 | 10.976 | 9.0781 | 2.1659 | 2.2488 | 3.8393 | 3.4976 | 8.244 | 5.9952 | 20.0542 | 22.303 | 30.547 | 36.5422 | 0
6.1885 | 8.0408 | 2.0063 | 2.0094 | 3.0314 | 3.0189 | 7.0471 | 5.0377 | 14.2294 | 16.2388 | 23.2859 | 28.3237 | 6.1885 | 8.0408 | 2.0063 | 2.0094 | 3.0414 | 3.0189 | 7.0471 | 5.0377 | 14.2294 | 16.2388 | 23.2859 | 28.3237 | 0
-0.0097864 | 6.6979 | 1.7997 | 1.6995 | 1.9984 | 2.399 | 5.4976 | 3.798 | 6.6881 | 8.3876 | 13.8852 | 17.6832 | -0.0097864 | 6.6979 | 1.7997 | 1.6995 | 2.0084 | 2.399 | 5.4976 | 3.798 | 6.6881 | 8.3876 | 13.8852 | 17.6832 | 0
13.3212 | 9.5863 | 2.244 | 2.3661 | 4.2202 | 3.7321 | 8.8303 | 6.4642 | 22.9074 | 25.2735 | 34.1038 | 40.568 | 13.3212 | 9.5863 | 2.244 | 2.3661 | 4.2302 | 3.7321 | 8.8303 | 6.4642 | 22.9074 | 25.2735 | 34.1038 | 40.568 | 0
-0.72099 | 6.5438 | 1.776 | 1.664 | 1.8798 | 2.3279 | 5.3198 | 3.6558 | 5.8228 | 7.4867 | 12.8065 | 16.4623 | -0.72099 | 6.5438 | 1.776 | 1.664 | 1.8898 | 2.3279 | 5.3198 | 3.6558 | 5.8228 | 7.4867 | 12.8065 | 16.4623 | 0
-0.99952 | 6.4834 | 1.7667 | 1.65 | 1.8334 | 2.3 | 5.2501 | 3.6001 | 5.4839 | 7.1339 | 12.3841 | 15.9842 | -0.99952 | 6.4834 | 1.7667 | 1.65 | 1.8434 | 2.3 | 5.2501 | 3.6001 | 5.4839 | 7.1339 | 12.3841 | 15.9842 | 0
1.5168 | 7.0286 | 1.8506 | 1.7758 | 2.2528 | 2.5517 | 5.8792 | 4.1034 | 8.5455 | 10.3213 | 16.2005 | 20.3039 | 1.5168 | 7.0286 | 1.8506 | 1.7758 | 2.2628 | 2.5517 | 5.8792 | 4.1034 | 8.5455 | 10.3213 | 16.2005 | 20.3039 | 0
-0.58033 | 6.5743 | 1.7807 | 1.671 | 1.9033 | 2.342 | 5.3549 | 3.6839 | 5.9939 | 7.6649 | 13.0198 | 16.7038 | -0.58033 | 6.5743 | 1.7807 | 1.671 | 1.9133 | 2.342 | 5.3549 | 3.6839 | 5.9939 | 7.6649 | 13.0198 | 16.7038 | 0
0.17113 | 6.7371 | 1.8057 | 1.7086 | 2.0285 | 2.4171 | 5.5428 | 3.8342 | 6.9082 | 8.6168 | 14.1595 | 17.9938 | 0.17113 | 6.7371 | 1.8057 | 1.7086 | 2.0385 | 2.4171 | 5.5428 | 3.8342 | 6.9082 | 8.6168 | 14.1595 | 17.9938 | 0
0.074319 | 6.7161 | 1.8025 | 1.7037 | 2.0124 | 2.4074 | 5.5186 | 3.8149 | 6.7904 | 8.4941 | 14.0127 | 17.8276 | 0.074319 | 6.7161 | 1.8025 | 1.7037 | 2.0224 | 2.4074 | 5.5186 | 3.8149 | 6.7904 | 8.4941 | 14.0127 | 17.8276 | 0
1.085 | 6.9351 | 1.8362 | 1.7543 | 2.1808 | 2.5085 | 5.7713 | 4.017 | 8.0201 | 9.7744 | 15.5456 | 19.5626 | 1.085 | 6.9351 | 1.8362 | 1.7543 | 2.1908 | 2.5085 | 5.7713 | 4.017 | 8.0201 | 9.7744 | 15.5456 | 19.5626 | 0
-3.1212 | 6.0237 | 1.696 | 1.5439 | 1.4798 | 2.0879 | 4.7197 | 3.1758 | 2.9025 | 4.4464 | 9.1661 | 12.3419 | -3.1212 | 6.0237 | 1.696 | 1.5439 | 1.4898 | 2.0879 | 4.7197 | 3.1758 | 2.9025 | 4.4464 | 9.1661 | 12.3419 | 0
6.0895 | 8.0194 | 2.003 | 2.0045 | 3.0149 | 3.009 | 7.0224 | 5.0179 | 14.1089 | 16.1134 | 23.1357 | 28.1536 | 6.0895 | 8.0194 | 2.003 | 2.0045 | 3.0249 | 3.009 | 7.0224 | 5.0179 | 14.1089 | 16.1134 | 23.1357 | 28.1536 | 0
6.2141 | 8.0464 | 2.0071 | 2.0107 | 3.0357 | 3.0214 | 7.0535 | 5.0428 | 14.2605 | 16.2712 | 23.3247 | 28.3676 | 6.2141 | 8.0464 | 2.0071 | 2.0107 | 3.0457 | 3.0214 | 7.0535 | 5.0428 | 14.2605 | 16.2712 | 23.3247 | 28.3676 | 0
9.4624 | 8.7502 | 2.1154 | 2.1731 | 3.5771 | 3.3462 | 7.8656 | 5.6925 | 18.2126 | 20.3857 | 28.2513 | 33.9437 | 9.4624 | 8.7502 | 2.1154 | 2.1731 | 3.5871 | 3.3462 | 7.8656 | 5.6925 | 18.2126 | 20.3857 | 28.2513 | 33.9437 | 0
2.7991 | 7.3065 | 1.8933 | 1.84 | 2.4665 | 2.6799 | 6.1998 | 4.3598 | 10.1056 | 11.9456 | 18.1454 | 22.5052 | 2.7991 | 7.3065 | 1.8933 | 1.84 | 2.4765 | 2.6799 | 6.1998 | 4.3598 | 10.1056 | 11.9456 | 18.1454 | 22.5052 | 0
0.57475 | 6.8245 | 1.8192 | 1.7287 | 2.0958 | 2.4575 | 5.6437 | 3.915 | 7.3993 | 9.128 | 14.7717 | 18.6867 | 0.57475 | 6.8245 | 1.8192 | 1.7287 | 2.1058 | 2.4575 | 5.6437 | 3.915 | 7.3993 | 9.128 | 14.7717 | 18.6867 | 0
9.4411 | 8.7456 | 2.1147 | 2.1721 | 3.5735 | 3.3441 | 7.8603 | 5.6882 | 18.1866 | 20.3587 | 28.219 | 33.9072 | 9.4411 | 8.7456 | 2.1147 | 2.1721 | 3.5835 | 3.3441 | 7.8603 | 5.6882 | 18.1866 | 20.3587 | 28.219 | 33.9072 | 0
-1.3256 | 6.4128 | 1.7558 | 1.6337 | 1.7791 | 2.2674 | 5.1686 | 3.5349 | 5.0872 | 6.7209 | 11.8896 | 15.4244 | -1.3256 | 6.4128 | 1.7558 | 1.6337 | 1.7891 | 2.2674 | 5.1686 | 3.5349 | 5.0872 | 6.7209 | 11.8896 | 15.4244 | 0
6.3785 | 8.082 | 2.0126 | 2.0189 | 3.0631 | 3.0379 | 7.0946 | 5.0757 | 14.4605 | 16.4794 | 23.5741 | 28.6498 | 6.3785 | 8.082 | 2.0126 | 2.0189 | 3.0731 | 3.0379 | 7.0946 | 5.0757 | 14.4605 | 16.4794 | 23.5741 | 28.6498 | 0
1.0149 | 6.9199 | 1.8338 | 1.7507 | 2.1692 | 2.5015 | 5.7537 | 4.003 | 7.9348 | 9.6856 | 15.4393 | 19.4423 | 1.0149 | 6.9199 | 1.8338 | 1.7507 | 2.1792 | 2.5015 | 5.7537 | 4.003 | 7.9348 | 9.6856 | 15.4393 | 19.4423 | 0
3.1071 | 7.3732 | 1.9036 | 1.8554 | 2.5178 | 2.7107 | 6.2768 | 4.4214 | 10.4803 | 12.3356 | 18.6124 | 23.0338 | 3.1071 | 7.3732 | 1.9036 | 1.8554 | 2.5278 | 2.7107 | 6.2768 | 4.4214 | 10.4803 | 12.3356 | 18.6124 | 23.0338 | 0
8.6083 | 8.5651 | 2.0869 | 2.1304 | 3.4347 | 3.2608 | 7.6521 | 5.5217 | 17.1734 | 19.3038 | 26.9559 | 32.4776 | 8.6083 | 8.5651 | 2.0869 | 2.1304 | 3.4447 | 3.2608 | 7.6521 | 5.5217 | 17.1734 | 19.3038 | 26.9559 | 32.4776 | 0
-7.3979 | 5.0971 | 1.5534 | 1.3301 | 0.76701 | 1.6602 | 3.6505 | 2.3204 | -2.3008 | -0.97073 | 2.6798 | 5.0002 | -7.3979 | 5.0971 | 1.5534 | 1.3301 | 0.77701 | 1.6602 | 3.6505 | 2.3204 | -2.3008 | -0.97073 | 2.6798 | 5.0002 | 0
9.1391 | 8.6801 | 2.1046 | 2.157 | 3.5232 | 3.3139 | 7.7848 | 5.6278 | 17.8192 | 19.9762 | 27.7609 | 33.3887 | 9.1391 | 8.6801 | 2.1046 | 2.157 | 3.5332 | 3.3139 | 7.7848 | 5.6278 | 17.8192 | 19.9762 | 27.7609 | 33.3887 | 0
10.1185 | 8.8923 | 2.1373 | 2.2059 | 3.6864 | 3.4118 | 8.0296 | 5.8237 | 19.0108 | 21.2168 | 29.2464 | 35.0701 | 10.1185 | 8.8923 | 2.1373 | 2.2059 | 3.6964 | 3.4118 | 8.0296 | 5.8237 | 19.0108 | 21.2168 | 29.2464 | 35.0701 | 0
8.8895 | 8.6261 | 2.0963 | 2.1445 | 3.4816 | 3.289 | 7.7224 | 5.5779 | 17.5156 | 19.6601 | 27.3825 | 32.9604 | 8.8895 | 8.6261 | 2.0963 | 2.1445 | 3.4916 | 3.289 | 7.7224 | 5.5779 | 17.5156 | 19.6601 | 27.3825 | 32.9604 | 0
18.1174 | 10.6254 | 2.4039 | 2.6059 | 5.0196 | 4.2117 | 10.0293 | 7.4235 | 28.7428 | 31.3487 | 41.378 | 48.8015 | 18.1174 | 10.6254 | 2.4039 | 2.6059 | 5.0296 | 4.2117 | 10.0293 | 7.4235 | 28.7428 | 31.3487 | 41.378 | 48.8015 | 0
-4.172 | 5.7961 | 1.6609 | 1.4914 | 1.3047 | 1.9828 | 4.457 | 2.9656 | 1.6241 | 3.1155 | 7.5725 | 10.5381 | -4.172 | 5.7961 | 1.6609 | 1.4914 | 1.3147 | 1.9828 | 4.457 | 2.9656 | 1.6241 | 3.1155 | 7.5725 | 10.5381 | 0
4.7866 | 7.7371 | 1.9596 | 1.9393 | 2.7978 | 2.8787 | 6.6966 | 4.7573 | 12.5236 | 14.463 | 21.1596 | 25.9169 | 4.7866 | 7.7371 | 1.9596 | 1.9393 | 2.8078 | 2.8787 | 6.6966 | 4.7573 | 12.5236 | 14.463 | 21.1596 | 25.9169 | 0
8.5519 | 8.5529 | 2.0851 | 2.1276 | 3.4253 | 3.2552 | 7.638 | 5.5104 | 17.1048 | 19.2324 | 26.8704 | 32.3807 | 8.5519 | 8.5529 | 2.0851 | 2.1276 | 3.4353 | 3.2552 | 7.638 | 5.5104 | 17.1048 | 19.2324 | 26.8704 | 32.3807 | 0
6.8119 | 8.1759 | 2.0271 | 2.0406 | 3.1353 | 3.0812 | 7.203 | 5.1624 | 14.9878 | 17.0284 | 24.2313 | 29.3937 | 6.8119 | 8.1759 | 2.0271 | 2.0406 | 3.1453 | 3.0812 | 7.203 | 5.1624 | 14.9878 | 17.0284 | 24.2313 | 29.3937 | 0
-7.8754 | 4.9937 | 1.5375 | 1.3062 | 0.68743 | 1.6125 | 3.5311 | 2.2249 | -2.8818 | -1.5755 | 1.9556 | 4.1805 | -7.8754 | 4.9937 | 1.5375 | 1.3062 | 0.69743 | 1.6125 | 3.5311 | 2.2249 | -2.8818 | -1.5755 | 1.9556 | 4.1805 | 0
3.4751 | 7.4529 | 1.9158 | 1.8738 | 2.5792 | 2.7475 | 6.3688 | 4.495 | 10.9281 | 12.8018 | 19.1706 | 23.6656 | 3.4751 | 7.4529 | 1.9158 | 1.8738 | 2.5892 | 2.7475 | 6.3688 | 4.495 | 10.9281 | 12.8018 | 19.1706 | 23.6656 | 0
-3.9303 | 5.8484 | 1.669 | 1.5035 | 1.345 | 2.007 | 4.5174 | 3.0139 | 1.9181 | 3.4216 | 7.9391 | 10.953 | -3.9303 | 5.8484 | 1.669 | 1.5035 | 1.355 | 2.007 | 4.5174 | 3.0139 | 1.9181 | 3.4216 | 7.9391 | 10.953 | 0
11.6169 | 9.217 | 2.1872 | 2.2808 | 3.9362 | 3.5617 | 8.4042 | 6.1234 | 20.8339 | 23.1148 | 31.519 | 37.6424 | 11.6169 | 9.217 | 2.1872 | 2.2808 | 3.9462 | 3.5617 | 8.4042 | 6.1234 | 20.8339 | 23.1148 | 31.519 | 37.6424 | 0
6.6067 | 8.1315 | 2.0202 | 2.0303 | 3.1011 | 3.0607 | 7.1517 | 5.1213 | 14.7382 | 16.7685 | 23.9202 | 29.0415 | 6.6067 | 8.1315 | 2.0202 | 2.0303 | 3.1111 | 3.0607 | 7.1517 | 5.1213 | 14.7382 | 16.7685 | 23.9202 | 29.0415 | 0
3.6787 | 7.4971 | 1.9226 | 1.8839 | 2.6131 | 2.7679 | 6.4197 | 4.5357 | 11.1758 | 13.0597 | 19.4794 | 24.0151 | 3.6787 | 7.4971 | 1.9226 | 1.8839 | 2.6231 | 2.7679 | 6.4197 | 4.5357 | 11.1758 | 13.0597 | 19.4794 | 24.0151 | 0
10.0022 | 8.8671 | 2.1334 | 2.2001 | 3.667 | 3.4002 | 8.0005 | 5.8004 | 18.8693 | 21.0694 | 29.07 | 34.8704 | 10.0022 | 8.8671 | 2.1334 | 2.2001 | 3.677 | 3.4002 | 8.0005 | 5.8004 | 18.8693 | 21.0694 | 29.07 | 34.8704 | 0
2.8576 | 7.3192 | 1.8953 | 1.8429 | 2.4763 | 2.6858 | 6.2144 | 4.3715 | 10.1768 | 12.0197 | 18.2341 | 22.6056 | 2.8576 | 7.3192 | 1.8953 | 1.8429 | 2.4863 | 2.6858 | 6.2144 | 4.3715 | 10.1768 | 12.0197 | 18.2341 | 22.6056 | 0
-5.7356 | 5.4573 | 1.6088 | 1.4132 | 1.0441 | 1.8264 | 4.0661 | 2.6529 | -0.2783 | 1.1349 | 5.201 | 7.8539 | -5.7356 | 5.4573 | 1.6088 | 1.4132 | 1.0541 | 1.8264 | 4.0661 | 2.6529 | -0.2783 | 1.1349 | 5.201 | 7.8539 | 0
-0.24152 | 6.6477 | 1.7919 | 1.6879 | 1.9597 | 2.3758 | 5.4396 | 3.7517 | 6.4062 | 8.0941 | 13.5337 | 17.2854 | -0.24152 | 6.6477 | 1.7919 | 1.6879 | 1.9697 | 2.3758 | 5.4396 | 3.7517 | 6.4062 | 8.0941 | 13.5337 | 17.2854 | 0
-1.1184 | 6.4577 | 1.7627 | 1.6441 | 1.8136 | 2.2882 | 5.2204 | 3.5763 | 5.3393 | 6.9834 | 12.2038 | 15.7801 | -1.1184 | 6.4577 | 1.7627 | 1.6441 | 1.8236 | 2.2882 | 5.2204 | 3.5763 | 5.3393 | 6.9834 | 12.2038 | 15.7801 | 0
9.8841 | 8.8416 | 1.6146 | 2.1942 | 3.6474 | 3.3884 | 7.971 | 5.7768 | 18.7257 | 20.9199 | 28.891 | 34.6678 | 9.8841 | 8.8416 | 1.6146 | 2.1942 | 3.6574 | 3.3884 | 7.971 | 5.7768 | 18.7257 | 20.9199 | 28.891 | 34.6678 | 0
-5.5634 | 5.4946 | 1.9328 | 1.4218 | 1.0728 | 1.8437 | 4.1091 | 2.6873 | -0.068833 | 1.353 | 5.4621 | 8.1495 | -5.5634 | 5.4946 | 1.9328 | 1.4218 | 1.0828 | 1.8437 | 4.1091 | 2.6873 | -0.068833 | 1.353 | 5.4621 | 8.1495 | 0
3.9837 | 7.5631 | 2.3331 | 1.8992 | 2.6639 | 2.7984 | 6.4959 | 4.5967 | 11.5468 | 13.446 | 19.9419 | 24.5386 | 3.9837 | 7.5631 | 2.3331 | 1.8992 | 2.6739 | 2.7984 | 6.4959 | 4.5967 | 11.5468 | 13.446 | 19.9419 | 24.5386 | 0
15.9941 | 10.1654 | 1.7859 | 2.4997 | 4.6657 | 3.9994 | 9.4985 | 6.9988 | 26.1595 | 28.6592 | 38.1577 | 45.1566 | 15.9941 | 10.1654 | 1.7859 | 2.4997 | 4.6757 | 3.9994 | 9.4985 | 6.9988 | 26.1595 | 28.6592 | 38.1577 | 45.1566 | 0
-0.42261 | 6.6084 | 1.794 | 1.6789 | 1.9296 | 2.3577 | 5.3943 | 3.7155 | 6.1858 | 7.8647 | 13.259 | 16.9745 | -0.42261 | 6.6084 | 1.794 | 1.6789 | 1.9396 | 2.3577 | 5.3943 | 3.7155 | 6.1858 | 7.8647 | 13.259 | 16.9745 | 0
-0.18131 | 6.6607 | 1.9908 | 1.6909 | 1.9698 | 2.3819 | 5.4547 | 3.7637 | 6.4794 | 8.1703 | 13.625 | 17.3887 | -0.18131 | 6.6607 | 1.9908 | 1.6909 | 1.9798 | 2.3819 | 5.4547 | 3.7637 | 6.4794 | 8.1703 | 13.625 | 17.3887 | 0
5.7226 | 7.9399 | 2.0474 | 1.9861 | 2.9538 | 2.9723 | 6.9306 | 4.9445 | 13.6625 | 15.6486 | 22.5792 | 27.5238 | 5.7226 | 7.9399 | 2.0474 | 1.9861 | 2.9638 | 2.9723 | 6.9306 | 4.9445 | 13.6625 | 15.6486 | 22.5792 | 27.5238 | 0
7.4208 | 8.3078 | 2.0177 | 2.071 | 3.2368 | 3.1421 | 7.3552 | 5.2842 | 15.7286 | 17.7997 | 25.1549 | 30.439 | 7.4208 | 8.3078 | 2.0177 | 2.071 | 3.2468 | 3.1421 | 7.3552 | 5.2842 | 15.7286 | 17.7997 | 25.1549 | 30.439 | 0
6.5317 | 8.1152 | 2.2316 | 2.0266 | 3.0886 | 3.0532 | 7.1329 | 5.1063 | 14.6469 | 16.6735 | 23.8064 | 28.9127 | 6.5317 | 8.1152 | 2.2316 | 2.0266 | 3.0986 | 3.0532 | 7.1329 | 5.1063 | 14.6469 | 16.6735 | 23.8064 | 28.9127 | 0
12.9487 | 9.5056 | 2.2484 | 2.3474 | 4.1581 | 3.6949 | 8.7372 | 6.3897 | 22.4543 | 24.8017 | 33.5389 | 39.9286 | 12.9487 | 9.5056 | 2.2484 | 2.3474 | 4.1681 | 3.6949 | 8.7372 | 6.3897 | 22.4543 | 24.8017 | 33.5389 | 39.9286 | 0
13.4512 | 9.6144 | 1.8607 | 2.3726 | 4.2419 | 3.7451 | 8.8628 | 6.4902 | 23.0656 | 25.4382 | 34.301 | 40.7912 | 13.4512 | 9.6144 | 1.8607 | 2.3726 | 4.2519 | 3.7451 | 8.8628 | 6.4902 | 23.0656 | 25.4382 | 34.301 | 40.7912 | 0
1.8217 | 7.0947 | 2.0947 | 1.7911 | 2.3036 | 2.5822 | 5.9554 | 4.1643 | 8.9164 | 10.7075 | 16.6629 | 20.8272 | 1.8217 | 7.0947 | 2.0947 | 1.7911 | 2.3136 | 2.5822 | 5.9554 | 4.1643 | 8.9164 | 10.7075 | 16.6629 | 20.8272 | 0
8.8397 | 8.6153 | 1.8922 | 2.142 | 3.4733 | 3.284 | 7.7099 | 5.5679 | 17.455 | 19.597 | 27.3069 | 32.8748 | 8.8397 | 8.6153 | 1.8922 | 2.142 | 3.4833 | 3.284 | 7.7099 | 5.5679 | 17.455 | 19.597 | 27.3069 | 32.8748 | 0
2.7666 | 7.2994 | 2.0757 | 1.8383 | 2.4611 | 2.6767 | 6.1916 | 4.3533 | 10.066 | 11.9043 | 18.0959 | 22.4493 | 2.7666 | 7.2994 | 2.0757 | 1.8383 | 2.4711 | 2.6767 | 6.1916 | 4.3533 | 10.066 | 11.9043 | 18.0959 | 22.4493 | 0
8.2722 | 8.4923 | 1.8633 | 2.1136 | 3.3787 | 3.2272 | 7.568 | 5.4544 | 16.7645 | 18.8781 | 26.4461 | 31.9006 | 8.2722 | 8.4923 | 1.8633 | 2.1136 | 3.3887 | 3.2272 | 7.568 | 5.4544 | 16.7645 | 18.8781 | 26.4461 | 31.9006 | 0
1.8989 | 7.1114 | 2.0766 | 1.7949 | 2.3165 | 2.5899 | 5.9747 | 4.1798 | 9.0103 | 10.8052 | 16.7799 | 20.9597 | 1.8989 | 7.1114 | 2.0766 | 1.7949 | 2.3265 | 2.5899 | 5.9747 | 4.1798 | 9.0103 | 10.8052 | 16.7799 | 20.9597 | 0
8.2977 | 8.4978 | 2.1503 | 2.1149 | 3.3829 | 3.2298 | 7.5744 | 5.4595 | 16.7955 | 18.9104 | 26.4848 | 31.9444 | 8.2977 | 8.4978 | 2.1503 | 2.1149 | 3.3929 | 3.2298 | 7.5744 | 5.4595 | 16.7955 | 18.9104 | 26.4848 | 31.9444 | 0
10.5101 | 8.9772 | 2.0598 | 2.2255 | 3.7517 | 3.451 | 8.1275 | 5.902 | 19.4873 | 21.7128 | 29.8404 | 35.7424 | 10.5101 | 8.9772 | 2.0598 | 2.2255 | 3.7617 | 3.451 | 8.1275 | 5.902 | 19.4873 | 21.7128 | 29.8404 | 35.7424 | 0
7.7932 | 8.3885 | 2.4427 | 2.0897 | 3.2989 | 3.1793 | 7.4483 | 5.3586 | 16.1817 | 18.2714 | 25.7197 | 31.0784 | 7.7932 | 8.3885 | 2.4427 | 2.0897 | 3.3089 | 3.1793 | 7.4483 | 5.3586 | 16.1817 | 18.2714 | 25.7197 | 31.0784 | 0
19.2796 | 10.8773 | 1.7714 | 2.664 | 5.2133 | 4.328 | 10.3199 | 7.6559 | 30.1569 | 32.8209 | 43.1408 | 50.7967 | 19.2796 | 10.8773 | 1.7714 | 2.664 | 5.2233 | 4.328 | 10.3199 | 7.6559 | 30.1569 | 32.8209 | 43.1408 | 50.7967 | 0
-0.85792 | 6.5141 | 1.9787 | 1.6571 | 1.857 | 2.3142 | 5.2855 | 3.6284 | 5.6562 | 7.3133 | 12.5988 | 16.2272 | -0.85792 | 6.5141 | 1.9787 | 1.6571 | 1.867 | 2.3142 | 5.2855 | 3.6284 | 5.6562 | 7.3133 | 12.5988 | 16.2272 | 0
5.3618 | 7.8617 | 2.1086 | 1.9681 | 2.8936 | 2.9362 | 6.8405 | 4.8724 | 13.2236 | 15.1917 | 22.0321 | 26.9045 | 5.3618 | 7.8617 | 2.1086 | 1.9681 | 2.9036 | 2.9362 | 6.8405 | 4.8724 | 13.2236 | 15.1917 | 22.0321 | 26.9045 | 0
9.2577 | 8.7058 | 2.1426 | 2.1629 | 3.543 | 3.3258 | 7.8144 | 5.6515 | 17.9635 | 20.1264 | 27.9408 | 33.5924 | 9.2577 | 8.7058 | 2.1426 | 2.1629 | 3.553 | 3.3258 | 7.8144 | 5.6515 | 17.9635 | 20.1264 | 27.9408 | 33.5924 | 0
10.2787 | 8.9271 | 2.2081 | 2.2139 | 3.7131 | 3.4279 | 8.0697 | 5.8557 | 19.2058 | 21.4197 | 29.4894 | 35.3451 | 10.2787 | 8.9271 | 2.2081 | 2.2139 | 3.7231 | 3.4279 | 8.0697 | 5.8557 | 19.2058 | 21.4197 | 29.4894 | 35.3451 | 0
12.2433 | 9.3527 | 1.7133 | 2.3122 | 4.0406 | 3.6243 | 8.5608 | 6.2487 | 21.5961 | 23.9082 | 32.4691 | 38.7177 | 12.2433 | 9.3527 | 1.7133 | 2.3122 | 4.0506 | 3.6243 | 8.5608 | 6.2487 | 21.5961 | 23.9082 | 32.4691 | 38.7177 | 0
-2.602 | 6.1362 | 2.0305 | 1.5699 | 1.5663 | 2.1398 | 4.8495 | 3.2796 | 3.5343 | 5.1042 | 9.9537 | 13.2333 | -2.602 | 6.1362 | 2.0305 | 1.5699 | 1.5763 | 2.1398 | 4.8495 | 3.2796 | 3.5343 | 5.1042 | 9.9537 | 13.2333 | 0
6.9152 | 8.1983 | 1.9055 | 2.0458 | 3.1525 | 3.0915 | 7.2288 | 5.183 | 15.1135 | 17.1593 | 24.3881 | 29.5711 | 6.9152 | 8.1983 | 1.9055 | 2.0458 | 3.1625 | 3.0915 | 7.2288 | 5.183 | 15.1135 | 17.1593 | 24.3881 | 29.5711 | 0
3.1651 | 7.3858 | 2.0144 | 1.8583 | 2.5275 | 2.7165 | 6.2913 | 4.433 | 10.5509 | 12.4091 | 18.7004 | 23.1334 | 3.1651 | 7.3858 | 2.0144 | 1.8583 | 2.5375 | 2.7165 | 6.2913 | 4.433 | 10.5509 | 12.4091 | 18.7004 | 23.1334 | 0
6.4306 | 8.0933 | 1.864 | 2.0215 | 3.0718 | 3.0431 | 7.1076 | 5.0861 | 14.5239 | 16.5454 | 23.653 | 28.7391 | 6.4306 | 8.0933 | 1.864 | 2.0215 | 3.0818 | 3.0431 | 7.1076 | 5.0861 | 14.5239 | 16.5454 | 23.653 | 28.7391 | 0
1.919 | 7.1158 | 1.9736 | 1.7959 | 2.3198 | 2.5919 | 5.9797 | 4.1838 | 9.0347 | 10.8307 | 16.8104 | 20.9942 | 1.919 | 7.1158 | 1.9736 | 1.7959 | 2.3298 | 2.5919 | 5.9797 | 4.1838 | 9.0347 | 10.8307 | 16.8104 | 20.9942 | 0
5.2075 | 7.8283 | 1.9672 | 1.9604 | 2.8679 | 2.9207 | 6.8019 | 4.8415 | 13.0358 | 14.9962 | 21.798 | 26.6395 | 5.2075 | 7.8283 | 1.9672 | 1.9604 | 2.8779 | 2.9207 | 6.8019 | 4.8415 | 13.0358 | 14.9962 | 21.798 | 26.6395 | 0
5.0148 | 7.7865 | 1.9804 | 1.9507 | 2.8358 | 2.9015 | 6.7537 | 4.803 | 12.8013 | 14.7521 | 21.5058 | 26.3087 | 5.0148 | 7.7865 | 1.9804 | 1.9507 | 2.8458 | 2.9015 | 6.7537 | 4.803 | 12.8013 | 14.7521 | 21.5058 | 26.3087 | 0
5.4118 | 7.8725 | 1.82 | 1.9706 | 2.902 | 2.9412 | 6.8529 | 4.8824 | 13.2843 | 15.2549 | 22.1078 | 26.9902 | 5.4118 | 7.8725 | 1.82 | 1.9706 | 2.912 | 2.9412 | 6.8529 | 4.8824 | 13.2843 | 15.2549 | 22.1078 | 26.9902 | 0
0.60033 | 6.8301 | 2.1284 | 1.73 | 2.1001 | 2.46 | 5.6501 | 3.9201 | 7.4304 | 9.1604 | 14.8105 | 18.7306 | 0.60033 | 6.8301 | 2.1284 | 1.73 | 2.1101 | 2.46 | 5.6501 | 3.9201 | 7.4304 | 9.1604 | 14.8105 | 18.7306 | 0
9.8505 | 8.8343 | 1.9956 | 2.1925 | 3.6418 | 3.3851 | 7.9626 | 5.7701 | 18.6848 | 20.8773 | 28.84 | 34.6101 | 9.8505 | 8.8343 | 1.9956 | 2.1925 | 3.6518 | 3.3851 | 7.9626 | 5.7701 | 18.6848 | 20.8773 | 28.84 | 34.6101 | 0
5.8682 | 7.9714 | 1.8458 | 1.9934 | 2.978 | 2.9868 | 6.9671 | 4.9736 | 13.8396 | 15.8331 | 22.8001 | 27.7737 | 5.8682 | 7.9714 | 1.8458 | 1.9934 | 2.988 | 2.9868 | 6.9671 | 4.9736 | 13.8396 | 15.8331 | 22.8001 | 27.7737 | 0
1.3746 | 6.9978 | 2.3455 | 1.7687 | 2.2291 | 2.5375 | 5.8436 | 4.0749 | 8.3724 | 10.1411 | 15.9848 | 20.0597 | 1.3746 | 6.9978 | 2.3455 | 1.7687 | 2.2391 | 2.5375 | 5.8436 | 4.0749 | 8.3724 | 10.1411 | 15.9848 | 20.0597 | 0
16.3663 | 10.246 | 2.1493 | 2.5183 | 4.7277 | 4.0366 | 9.5916 | 7.0733 | 26.6123 | 29.1306 | 38.7222 | 45.7954 | 16.3663 | 10.246 | 2.1493 | 2.5183 | 4.7377 | 4.0366 | 9.5916 | 7.0733 | 26.6123 | 29.1306 | 38.7222 | 45.7954 | 0
10.4785 | 8.9703 | 2.2881 | 2.2239 | 3.7464 | 3.4479 | 8.1196 | 5.8957 | 19.4488 | 21.6728 | 29.7924 | 35.6881 | 10.4785 | 8.9703 | 2.2881 | 2.2239 | 3.7564 | 3.4479 | 8.1196 | 5.8957 | 19.4488 | 21.6728 | 29.7924 | 35.6881 | 0
14.6431 | 9.8727 | 2.1757 | 2.4322 | 4.4405 | 3.8643 | 9.1608 | 6.7286 | 24.5157 | 26.9479 | 36.1087 | 42.8373 | 14.6431 | 9.8727 | 2.1757 | 2.4322 | 4.4505 | 3.8643 | 9.1608 | 6.7286 | 24.5157 | 26.9479 | 36.1087 | 42.8373 | 0
11.2705 | 9.1419 | 1.6904 | 2.2635 | 3.8784 | 3.5271 | 8.3176 | 6.0541 | 20.4125 | 22.676 | 30.9936 | 37.0477 | 11.2705 | 9.1419 | 1.6904 | 2.2635 | 3.8884 | 3.5271 | 8.3176 | 6.0541 | 20.4125 | 22.676 | 30.9936 | 37.0477 | 0
-3.2871 | 5.9878 | 1.9339 | 1.5356 | 1.4522 | 2.0713 | 4.6782 | 3.1426 | 2.7008 | 4.2364 | 8.9146 | 12.0572 | -3.2871 | 5.9878 | 1.9339 | 1.5356 | 1.4622 | 2.0713 | 4.6782 | 3.1426 | 2.7008 | 4.2364 | 8.9146 | 12.0572 | 0
4.0163 | 7.5702 | 1.9562 | 1.9008 | 2.6694 | 2.8016 | 6.5041 | 4.6033 | 11.5865 | 13.4873 | 19.9914 | 24.5946 | 4.0163 | 7.5702 | 1.9562 | 1.9008 | 2.6794 | 2.8016 | 6.5041 | 4.6033 | 11.5865 | 13.4873 | 19.9914 | 24.5946 | 0
4.6864 | 7.7154 | 1.8488 | 1.9343 | 2.7811 | 2.8686 | 6.6716 | 4.7373 | 12.4018 | 14.3361 | 21.0078 | 25.745 | 4.6864 | 7.7154 | 1.8488 | 1.9343 | 2.7911 | 2.8686 | 6.6716 | 4.7373 | 12.4018 | 14.3361 | 21.0078 | 25.745 | 0
1.4634 | 7.0171 | 1.7742 | 1.7732 | 2.2439 | 3.5791 | 5.8659 | 4.0927 | 8.4805 | 10.2536 | 16.1195 | 20.2122 | 1.4634 | 7.0171 | 1.7742 | 1.7732 | 2.2539 | 3.5791 | 5.8659 | 4.0927 | 8.4805 | 10.2536 | 16.1195 | 20.2122 | 0
-0.77368 | 6.5324 | 2.193 | 1.6613 | 1.8711 | 1.6857 | 5.3066 | 3.6453 | 5.7587 | 7.42 | 12.7266 | 16.3718 | -0.77368 | 6.5324 | 2.193 | 1.6613 | 1.8811 | 1.6857 | 5.3066 | 3.6453 | 5.7587 | 7.42 | 12.7266 | 16.3718 | 0
11.7905 | 9.2546 | 1.5619 | 2.2895 | 3.9651 | 2.9119 | 8.4476 | 6.1581 | 21.0451 | 23.3346 | 31.7823 | 37.9404 | 11.7905 | 9.2546 | 1.5619 | 2.2895 | 3.9751 | 2.9119 | 8.4476 | 6.1581 | 21.0451 | 23.3346 | 31.7823 | 37.9404 | 0
-7.1426 | 5.1524 | 1.9706 | 1.3429 | 0.80957 | 3.4348 | 3.7144 | 2.3715 | -1.9901 | -0.64725 | 3.5972 | 5.9687 | -7.1426 | 5.1524 | 1.9706 | 1.3429 | 0.81957 | 3.4348 | 3.7144 | 2.3715 | -1.9901 | -0.64725 | 3.6072 | 5.9787 | 0.01
5.1192 | 7.8092 | 2.1449 | 1.956 | 2.8532 | 3.9823 | 6.7798 | 4.8238 | 12.9284 | 14.8844 | 21.7198 | 26.5437 | 5.1192 | 7.8092 | 2.1449 | 1.956 | 2.8632 | 3.9823 | 6.7798 | 4.8238 | 12.9284 | 14.8844 | 21.7298 | 26.5537 | 0.01
10.3484 | 8.9421 | 2.3274 | 2.2174 | 3.7247 | 2.3004 | 8.0871 | 5.8697 | 19.2905 | 21.5079 | 29.595 | 35.4647 | 10.3484 | 8.9421 | 2.3274 | 2.2174 | 3.7347 | 2.3004 | 8.0871 | 5.8697 | 19.2905 | 21.5079 | 29.595 | 35.4647 | 0
15.8226 | 10.1282 | 1.7668 | 2.4911 | 4.6371 | 1.4393 | 9.4556 | 6.9645 | 25.9508 | 28.442 | 37.8976 | 44.8621 | 15.8226 | 10.1282 | 1.7668 | 2.4911 | 4.6471 | 1.4393 | 9.4556 | 6.9645 | 25.9508 | 28.442 | 37.8976 | 44.8621 | 0
-0.99638 | 6.4841 | 1.4798 | 1.6502 | 1.8339 | 2.1554 | 5.2509 | 3.6007 | 5.4877 | 7.1379 | 12.3888 | 15.9895 | -0.99638 | 6.4841 | 1.4798 | 1.6502 | 1.8439 | 2.1554 | 5.2509 | 3.6007 | 5.4877 | 7.1379 | 12.3888 | 15.9895 | 0
-9.6069 | 4.6185 | 1.7185 | 1.2197 | 0.39885 | 2.5843 | 4.8886 | 1.8786 | -4.9884 | -3.7688 | 1.1198 | 2.9984 | -9.6069 | 4.6185 | 1.7185 | 1.2197 | 0.40885 | 2.5843 | 4.8886 | 1.8786 | -4.9884 | -3.7688 | 1.1198 | 2.9984 | 0
-2.4456 | 6.1701 | 1.8614 | 1.5777 | 1.5924 | 2.3528 | 5.9607 | 3.3109 | 3.7245 | 5.3022 | 11.2629 | 14.5738 | -2.4456 | 6.1701 | 1.8614 | 1.5777 | 1.6024 | 2.3528 | 5.9607 | 3.3109 | 3.7245 | 5.3022 | 11.2629 | 14.5738 | 0
1.8427 | 7.0993 | 1.7843 | 1.7921 | 2.3071 | 2.7307 | 5.3821 | 4.1685 | 8.942 | 10.7341 | 16.1162 | 20.2847 | 1.8427 | 7.0993 | 1.7843 | 1.7921 | 2.3171 | 2.7307 | 5.3821 | 4.1685 | 8.942 | 10.7341 | 16.1162 | 20.2847 | 0
-0.47175 | 6.5978 | 1.9102 | 1.6764 | 1.9214 | 2.5396 | 6.3268 | 3.7057 | 6.126 | 7.8025 | 14.1292 | 17.8349 | -0.47175 | 6.5978 | 1.9102 | 1.6764 | 1.9314 | 2.5396 | 6.3268 | 3.7057 | 6.126 | 7.8025 | 14.1292 | 17.8349 | 0
3.3071 | 7.4165 | 1.8465 | 1.7698 | 2.5512 | 2.4087 | 5.8491 | 4.4614 | 10.7236 | 12.4935 | 18.3426 | 22.804 | 3.3071 | 7.4165 | 1.8465 | 1.7698 | 2.5612 | 2.4087 | 5.8491 | 4.4614 | 10.7236 | 12.4935 | 18.3426 | 22.804 | 0
1.3965 | 7.0026 | 1.8029 | 1.7043 | 2.2327 | 3.3494 | 5.5217 | 4.0793 | 8.399 | 10.1034 | 15.6855 | 19.7648 | 1.3965 | 7.0026 | 1.8029 | 1.7043 | 2.2427 | 3.3494 | 5.5217 | 4.0793 | 8.399 | 10.1034 | 15.6955 | 19.7748 | 0.01
0.08672 | 6.7188 | 2.1165 | 2.1747 | 2.0145 | 3.9835 | 7.8734 | 3.8173 | 6.8055 | 8.9802 | 16.8536 | 20.671 | 0.08672 | 6.7188 | 2.1165 | 2.1747 | 2.0245 | 3.9835 | 7.8734 | 3.8173 | 6.8055 | 8.9802 | 16.8536 | 20.671 | 0
9.4938 | 8.757 | 2.3278 | 2.4917 | 3.5823 | 3.2911 | 9.4587 | 5.6988 | 18.2508 | 20.7425 | 30.2012 | 35.8999 | 9.4938 | 8.757 | 2.3278 | 2.4917 | 3.5923 | 3.2911 | 9.4587 | 5.6988 | 18.2508 | 20.7425 | 30.2012 | 35.8999 | 0
15.8348 | 10.1309 | 2.097 | 2.1455 | 4.6391 | 3.8318 | 7.7276 | 6.967 | 25.9657 | 28.1112 | 36.5822 | 43.5491 | 15.8348 | 10.1309 | 2.097 | 2.1455 | 4.6491 | 3.8318 | 7.7276 | 6.967 | 25.9657 | 28.1112 | 36.5922 | 43.5591 | 0.01
8.9106 | 8.6306 | 2.2773 | 2.4159 | 3.4851 | 2.4722 | 9.0796 | 5.5821 | 17.5412 | 19.9571 | 29.0368 | 34.6189 | 8.9106 | 8.6306 | 2.2773 | 2.4159 | 3.4951 | 2.4722 | 9.0796 | 5.5821 | 17.5412 | 19.9571 | 29.0368 | 34.6189 | 0
14.3184 | 9.8023 | 1.8241 | 1.7361 | 4.3864 | 3.1013 | 5.6806 | 6.6637 | 24.1208 | 25.8569 | 33.3446 | 40.0083 | 14.3184 | 9.8023 | 1.8241 | 1.7361 | 4.3964 | 3.1013 | 5.6806 | 6.6637 | 24.1208 | 25.8569 | 33.3546 | 40.0183 | 0.01
0.7224 | 6.8565 | 2.0338 | 2.0506 | 2.1204 | 4.3384 | 7.2532 | 3.9445 | 7.5789 | 9.6296 | 16.8828 | 20.8273 | 0.7224 | 6.8565 | 2.0338 | 2.0506 | 2.1304 | 4.3384 | 7.2532 | 3.9445 | 7.5789 | 9.6296 | 16.8828 | 20.8273 | 0
7.0128 | 8.2194 | 2.4461 | 2.6692 | 3.1688 | 1.3988 | 10.346 | 5.2026 | 15.2323 | 17.9015 | 28.2475 | 33.45 | 7.0128 | 8.2194 | 2.4461 | 2.6692 | 3.1788 | 1.3988 | 10.346 | 5.2026 | 15.2323 | 17.9015 | 28.2475 | 33.45 | 0
19.384 | 10.8999 | 1.4663 | 1.1994 | 5.2307 | 4.3226 | 2.9969 | 7.6768 | 30.2838 | 31.4832 | 41.0365 | 48.7133 | 19.384 | 10.8999 | 1.4663 | 1.1994 | 5.2407 | 4.3226 | 2.9969 | 7.6768 | 30.2838 | 31.4832 | 41.0465 | 48.7233 | 0.01
19.2262 | 4.5307 | 2.4409 | 2.6613 | 0.33129 | 3.8214 | 10.3065 | 1.7975 | 23.7568 | 26.4181 | 36.7247 | 38.5222 | 19.2262 | 4.5307 | 2.4409 | 2.6613 | 0.34129 | 3.8214 | 10.3065 | 1.7975 | 23.7568 | 26.4181 | 36.7247 | 38.5222 | 0
14.2142 | 10.8657 | 2.2738 | 2.4107 | 5.2044 | 2.1505 | 9.0535 | 7.6452 | 25.0798 | 27.4905 | 36.5441 | 44.1893 | 14.2142 | 10.8657 | 2.2738 | 2.4107 | 5.2144 | 2.1505 | 9.0535 | 7.6452 | 25.0798 | 27.4905 | 36.5441 | 44.1893 | 0
-2.4952 | 9.7797 | 1.7168 | 1.5752 | 4.369 | 3.5234 | 4.8762 | 6.6428 | 7.2846 | 8.8598 | 16.7522 | 23.395 | -2.4952 | 9.7797 | 1.7168 | 1.5752 | 4.379 | 3.5234 | 4.8762 | 6.6428 | 7.2846 | 8.8598 | 16.7622 | 23.405 | 0.01
11.2336 | 6.1594 | 2.1745 | 2.2617 | 1.5841 | 4.0163 | 8.3084 | 3.301 | 17.393 | 19.6547 | 27.9631 | 31.2641 | 11.2336 | 6.1594 | 2.1745 | 2.2617 | 1.5941 | 4.0163 | 8.3084 | 3.301 | 17.393 | 19.6547 | 27.9631 | 31.2641 | 0
16.1635 | 9.134 | 2.3388 | 2.5082 | 3.8723 | 2.7069 | 9.5409 | 6.0467 | 25.2974 | 27.8056 | 37.3465 | 43.3932 | 16.1635 | 9.134 | 2.3388 | 2.5082 | 3.8823 | 2.7069 | 9.5409 | 6.0467 | 25.2974 | 27.8056 | 37.3465 | 43.3932 | 0
3.0691 | 10.2021 | 1.9023 | 1.8535 | 4.2369 | 3.7422 | 6.2673 | 7.0327 | 13.2711 | 15.1246 | 23.1037 | 30.1364 | 3.0691 | 10.2021 | 1.9023 | 1.8535 | 4.2469 | 3.7422 | 6.2673 | 7.0327 | 13.2711 | 15.1246 | 23.1137 | 30.1464 | 0.01
13.4216 | 7.365 | 2.2474 | 2.3711 | 4.3798 | 3.8279 | 8.8554 | 4.4138 | 20.7866 | 23.1577 | 32.0131 | 36.4269 | 13.4216 | 7.365 | 2.2474 | 2.3711 | 4.3898 | 3.8279 | 8.8554 | 4.4138 | 20.7866 | 23.1577 | 32.0131 | 36.4269 | 0
14.2791 | 9.608 | 2.276 | 2.414 | 2.4376 | 2.6625 | 9.0698 | 6.4843 | 23.8871 | 26.301 | 35.3708 | 41.8551 | 14.2791 | 9.608 | 2.276 | 2.414 | 2.4476 | 2.6625 | 9.0698 | 6.4843 | 23.8871 | 26.301 | 35.3708 | 41.8551 | 0
2.6253 | 9.7938 | 1.8875 | 1.8313 | 0.72184 | 1.6331 | 6.1563 | 6.6558 | 12.4191 | 14.2504 | 20.4067 | 27.0625 | 2.6253 | 9.7938 | 1.8875 | 1.8313 | 0.73184 | 1.6331 | 6.1563 | 6.6558 | 12.4191 | 14.2504 | 20.4067 | 27.0625 | 0
-7.6689 | 7.2688 | 1.5444 | 1.3166 | 4.3164 | 3.7899 | 3.5828 | 4.3251 | -0.40013 | 0.91643 | 9.0227 | 13.3478 | -7.6689 | 7.2688 | 1.5444 | 1.3166 | 4.3264 | 3.7899 | 3.5828 | 4.3251 | -0.40013 | 0.91643 | 9.0327 | 13.3578 | 0.01
13.8987 | 5.0384 | 2.2633 | 2.3949 | 4.5377 | 3.9226 | 8.9747 | 2.2662 | 18.9371 | 21.332 | 30.3067 | 32.5729 | 13.8987 | 5.0384 | 2.2633 | 2.3949 | 4.5477 | 3.9226 | 8.9747 | 2.2662 | 18.9371 | 21.332 | 30.3067 | 32.5729 | 0
15.2263 | 9.7114 | 2.3075 | 2.4613 | 5.1783 | 4.307 | 9.3066 | 6.5797 | 24.9377 | 27.399 | 36.8844 | 43.4641 | 15.2263 | 9.7114 | 2.3075 | 2.4613 | 5.1883 | 4.307 | 9.3066 | 6.5797 | 24.9377 | 27.399 | 36.8944 | 43.4741 | 0.01
19.0701 | 9.999 | 2.4357 | 2.6535 | 1.7349 | 2.2409 | 10.2675 | 6.8453 | 29.0691 | 31.7226 | 41.9902 | 48.8354 | 19.0701 | 9.999 | 2.4357 | 2.6535 | 1.7449 | 2.2409 | 10.2675 | 6.8453 | 29.0691 | 31.7226 | 41.9902 | 48.8354 | 0
-1.5907 | 10.8319 | 1.747 | 1.6205 | 3.4667 | 3.28 | 5.1023 | 7.614 | 9.2411 | 10.8616 | 17.6083 | 25.2223 | -1.5907 | 10.8319 | 1.747 | 1.6205 | 3.4767 | 3.28 | 5.1023 | 7.614 | 9.2411 | 10.8616 | 17.6183 | 25.2323 | 0.01
8.8001 | 6.3553 | 2.0933 | 2.14 | 3.3661 | 3.2197 | 7.7 | 3.4819 | 15.1554 | 17.2954 | 24.9955 | 28.4773 | 8.8001 | 6.3553 | 2.0933 | 2.14 | 3.3761 | 3.2197 | 7.7 | 3.4819 | 15.1554 | 17.2954 | 24.9955 | 28.4773 | 0
8.1966 | 8.6067 | 2.0732 | 2.1098 | 2.9229 | 2.9538 | 7.5492 | 5.56 | 16.8033 | 18.9131 | 26.4623 | 32.0223 | 8.1966 | 8.6067 | 2.0732 | 2.1098 | 2.9329 | 2.9538 | 7.5492 | 5.56 | 16.8033 | 18.9131 | 26.4623 | 32.0223 | 0
5.5376 | 8.4759 | 1.9846 | 1.9769 | 2.3602 | 2.6161 | 6.8844 | 5.4393 | 14.0135 | 15.9904 | 22.8748 | 28.3141 | 5.5376 | 8.4759 | 1.9846 | 1.9769 | 2.3702 | 2.6161 | 6.8844 | 5.4393 | 14.0135 | 15.9904 | 22.8748 | 28.3141 | 0
2.1614 | 7.8998 | 1.872 | 1.8081 | 2.489 | 2.6934 | 6.0403 | 4.9075 | 10.0612 | 11.8692 | 17.9096 | 22.8171 | 2.1614 | 7.8998 | 1.872 | 1.8081 | 2.499 | 2.6934 | 6.0403 | 4.9075 | 10.0612 | 11.8692 | 17.9096 | 22.8171 | 0
2.9341 | 7.1683 | 1.8978 | 1.8467 | 3.9122 | 3.5473 | 6.2335 | 4.2323 | 10.1024 | 11.9491 | 19.4087 | 23.641 | 2.9341 | 7.1683 | 1.8978 | 1.8467 | 3.9222 | 3.5473 | 6.2335 | 4.2323 | 10.1024 | 11.9491 | 19.4187 | 23.651 | 0.01
11.4734 | 7.3357 | 2.1824 | 2.2737 | 4.5221 | 3.9133 | 8.3684 | 4.3868 | 18.8092 | 21.0828 | 29.5182 | 33.9051 | 11.4734 | 7.3357 | 2.1824 | 2.2737 | 4.5321 | 3.9133 | 8.3684 | 4.3868 | 18.8092 | 21.0828 | 29.5282 | 33.9151 | 0.01
15.1327 | 9.1859 | 2.3044 | 2.4566 | 3.0515 | 3.0309 | 9.2832 | 6.0947 | 24.3186 | 26.7752 | 36.0584 | 42.1531 | 15.1327 | 9.1859 | 2.3044 | 2.4566 | 3.0615 | 3.0309 | 9.2832 | 6.0947 | 24.3186 | 26.7752 | 36.0584 | 42.1531 | 0
6.309 | 9.9788 | 2.0103 | 2.0154 | 3.3918 | 3.2351 | 7.0772 | 6.8265 | 16.2877 | 18.3032 | 25.3804 | 32.207 | 6.309 | 9.9788 | 2.0103 | 2.0154 | 3.4018 | 3.2351 | 7.0772 | 6.8265 | 16.2877 | 18.3032 | 25.3804 | 32.207 | 0
8.3508 | 8.0669 | 2.0784 | 2.1175 | 3.9998 | 3.5999 | 7.5877 | 5.0618 | 16.4178 | 18.5353 | 26.135 | 31.1968 | 8.3508 | 8.0669 | 2.0784 | 2.1175 | 4.0098 | 3.5999 | 7.5877 | 5.0618 | 16.4178 | 18.5353 | 26.145 | 31.2068 | 0.01
11.9988 | 8.5093 | 2.2 | 2.2999 | 3.3774 | 3.2265 | 8.4997 | 5.4702 | 20.5081 | 22.808 | 31.3077 | 36.7779 | 11.9988 | 8.5093 | 2.2 | 2.2999 | 3.3874 | 3.2265 | 8.4997 | 5.4702 | 20.5081 | 22.808 | 31.3077 | 36.7779 | 0
8.2645 | 9.2997 | 2.0755 | 2.1132 | 2.4958 | 2.6975 | 7.5661 | 6.1998 | 17.5643 | 19.6775 | 27.2436 | 33.4434 | 8.2645 | 9.2997 | 2.0755 | 2.1132 | 2.5058 | 2.6975 | 7.5661 | 6.1998 | 17.5643 | 19.6775 | 27.2436 | 33.4434 | 0
2.9748 | 8.4906 | 1.8992 | 1.8487 | 3.6696 | 3.4018 | 6.2437 | 5.4529 | 11.4654 | 13.3142 | 20.3856 | 25.8385 | 2.9748 | 8.4906 | 1.8992 | 1.8487 | 3.6796 | 3.4018 | 6.2437 | 5.4529 | 11.4654 | 13.3142 | 20.3956 | 25.8485 | 0.01
10.0178 | 7.3445 | 2.1339 | 2.2009 | 2.3627 | 2.6176 | 8.0044 | 4.395 | 17.3623 | 19.5632 | 27.5677 | 31.9626 | 10.0178 | 7.3445 | 2.1339 | 2.2009 | 2.3727 | 2.6176 | 8.0044 | 4.395 | 17.3623 | 19.5632 | 27.5677 | 31.9626 | 0
2.1761 | 8.8705 | 1.8725 | 1.8088 | 3.6992 | 3.4195 | 6.044 | 5.8036 | 11.0466 | 12.8554 | 19.9742 | 25.7777 | 2.1761 | 8.8705 | 1.8725 | 1.8088 | 3.7092 | 3.4195 | 6.044 | 5.8036 | 11.0466 | 12.8554 | 19.9842 | 25.7877 | 0.01
10.1953 | 7.1715 | 2.1398 | 2.2098 | 2.0614 | 2.4368 | 8.0488 | 4.2352 | 17.3668 | 19.5765 | 27.6253 | 31.8606 | 10.1953 | 7.1715 | 2.1398 | 2.2098 | 2.0714 | 2.4368 | 8.0488 | 4.2352 | 17.3668 | 19.5765 | 27.6253 | 31.8606 | 0
0.36812 | 8.909 | 1.8123 | 1.7184 | 3.4738 | 3.2843 | 5.592 | 5.8391 | 9.2771 | 10.9955 | 17.7536 | 23.5926 | 0.36812 | 8.909 | 1.8123 | 1.7184 | 3.4838 | 3.2843 | 5.592 | 5.8391 | 9.2771 | 10.9955 | 17.7636 | 23.6026 | 0.01
8.8428 | 6.7798 | 2.0948 | 2.1421 | 2.5607 | 2.7364 | 7.7107 | 3.8736 | 15.6225 | 17.7647 | 25.4753 | 29.349 | 8.8428 | 6.7798 | 2.0948 | 2.1421 | 2.5707 | 2.7364 | 7.7107 | 3.8736 | 15.6225 | 17.7647 | 25.4753 | 29.349 | 0
3.3639 | 8.6159 | 1.9121 | 1.8682 | 3.7195 | 3.4317 | 6.341 | 5.5686 | 11.9799 | 13.8481 | 20.9992 | 26.5678 | 3.3639 | 8.6159 | 1.9121 | 1.8682 | 3.7295 | 3.4317 | 6.341 | 5.5686 | 11.9799 | 13.8481 | 21.0092 | 26.5778 | 0.01
10.3169 | 7.4289 | 2.1439 | 2.2158 | 4.0749 | 3.645 | 8.0792 | 4.4728 | 17.7457 | 19.9616 | 28.0408 | 32.5136 | 10.3169 | 7.4289 | 2.1439 | 2.2158 | 4.0849 | 3.645 | 8.0792 | 4.4728 | 17.7457 | 19.9616 | 28.0408 | 32.5136 | 0
12.4496 | 8.9353 | 2.215 | 2.3225 | 3.8485 | 3.5091 | 8.6124 | 5.8634 | 21.3849 | 23.7074 | 32.3198 | 38.1832 | 12.4496 | 8.9353 | 2.215 | 2.3225 | 3.8585 | 3.5091 | 8.6124 | 5.8634 | 21.3849 | 23.7074 | 32.3198 | 38.1832 | 0
11.0913 | 9.3974 | 2.1697 | 2.2546 | 1.6992 | 2.2195 | 8.2728 | 6.2899 | 20.4887 | 22.7433 | 31.0161 | 37.306 | 11.0913 | 9.3974 | 2.1697 | 2.2546 | 1.7092 | 2.2195 | 8.2728 | 6.2899 | 20.4887 | 22.7433 | 31.0161 | 37.306 | 0
-1.8049 | 9.1031 | 1.7398 | 1.6098 | 3.2226 | 3.1336 | 5.0488 | 6.0183 | 7.2982 | 8.908 | 15.2642 | 21.2824 | -1.8049 | 9.1031 | 1.7398 | 1.6098 | 3.2326 | 3.1336 | 5.0488 | 6.0183 | 7.2982 | 8.908 | 15.2742 | 21.2924 | 0.01
7.3357 | 6.3089 | 2.0445 | 2.0668 | 4.1585 | 3.6951 | 7.3339 | 3.439 | 13.6446 | 15.7114 | 23.565 | 27.004 | 7.3357 | 6.3089 | 2.0445 | 2.0668 | 4.1685 | 3.6951 | 7.3339 | 3.439 | 13.6446 | 15.7114 | 23.575 | 27.014 | 0.01
12.9509 | 8.2894 | 2.2317 | 2.3475 | 1.8244 | 2.2947 | 8.7377 | 5.2671 | 21.2403 | 23.5878 | 32.3255 | 37.5927 | 12.9509 | 8.2894 | 2.2317 | 2.3475 | 1.8344 | 2.2947 | 8.7377 | 5.2671 | 21.2403 | 23.5878 | 32.3255 | 37.5927 | 0
-1.0534 | 9.506 | 1.7649 | 1.6473 | 4.1219 | 3.6732 | 5.2366 | 6.3902 | 8.4526 | 10.0999 | 17.895 | 24.2852 | -1.0534 | 9.506 | 1.7649 | 1.6473 | 4.1319 | 3.6732 | 5.2366 | 6.3902 | 8.4526 | 10.0999 | 17.905 | 24.2952 | 0.01
12.7317 | 6.4718 | 2.2244 | 2.3366 | 2.2937 | 2.5762 | 8.6829 | 3.5893 | 19.2034 | 21.54 | 30.2229 | 33.8122 | 12.7317 | 6.4718 | 2.2244 | 2.3366 | 2.3037 | 2.5762 | 8.6829 | 3.5893 | 19.2034 | 21.54 | 30.2229 | 33.8122 | 0
1.7625 | 9.4585 | 1.8587 | 1.7881 | 4.4139 | 3.8484 | 5.9406 | 6.3463 | 11.221 | 13.0091 | 21.2714 | 27.6177 | 1.7625 | 9.4585 | 1.8587 | 1.7881 | 4.4239 | 3.8484 | 5.9406 | 6.3463 | 11.221 | 13.0091 | 21.2814 | 27.6277 | 0.01
14.4836 | 7.0819 | 2.2828 | 2.4242 | 2.818 | 2.8908 | 9.1209 | 4.1525 | 21.5654 | 23.9896 | 33.1105 | 37.263 | 14.4836 | 7.0819 | 2.2828 | 2.4242 | 2.828 | 2.8908 | 9.1209 | 4.1525 | 21.5654 | 23.9896 | 33.1105 | 37.263 | 0
4.908 | 9.8381 | 1.9636 | 1.9454 | 4.2124 | 3.7275 | 6.727 | 6.6967 | 14.7461 | 16.6915 | 24.6314 | 31.3281 | 4.908 | 9.8381 | 1.9636 | 1.9454 | 4.2224 | 3.7275 | 6.727 | 6.6967 | 14.7461 | 16.6915 | 24.6414 | 31.3381 | 0.01
13.2747 | 7.7634 | 2.2425 | 2.3637 | 2.6176 | 2.7706 | 8.8187 | 4.7816 | 21.0381 | 23.4018 | 32.2205 | 37.0021 | 13.2747 | 7.7634 | 2.2425 | 2.3637 | 2.6276 | 2.7706 | 8.8187 | 4.7816 | 21.0381 | 23.4018 | 32.2205 | 37.0021 | 0
3.7058 | 9.5762 | 1.9235 | 1.8853 | 4.0942 | 3.6565 | 6.4265 | 6.4549 | 13.282 | 15.1673 | 22.9179 | 29.3729 | 3.7058 | 9.5762 | 1.9235 | 1.8853 | 4.1042 | 3.6565 | 6.4265 | 6.4549 | 13.282 | 15.1673 | 22.9279 | 29.3829 | 0.01
12.5649 | 7.5029 | 2.2188 | 2.3282 | 2.7136 | 2.8282 | 8.6412 | 4.5412 | 20.0678 | 22.3961 | 31.0373 | 35.5785 | 12.5649 | 7.5029 | 2.2188 | 2.3282 | 2.7236 | 2.8282 | 8.6412 | 4.5412 | 20.0678 | 22.3961 | 31.0373 | 35.5785 | 0
4.2816 | 9.4224 | 1.9427 | 1.9141 | 1.5496 | 2.1298 | 6.5704 | 6.313 | 13.704 | 15.618 | 22.1884 | 28.5014 | 4.2816 | 9.4224 | 1.9427 | 1.9141 | 1.5596 | 2.1298 | 6.5704 | 6.313 | 13.704 | 15.618 | 22.1884 | 28.5014 | 0
-2.7021 | 7.6277 | 1.7099 | 1.5649 | 4.8215 | 4.0929 | 4.8245 | 4.6563 | 4.9255 | 6.4904 | 15.4048 | 20.0611 | -2.7021 | 7.6277 | 1.7099 | 1.5649 | 4.8315 | 4.0929 | 4.8245 | 4.6563 | 4.9255 | 6.4904 | 15.4148 | 20.0711 | 0.01
16.9289 | 6.1145 | 2.3643 | 2.5464 | 1.5666 | 2.14 | 9.7322 | 3.2596 | 23.0434 | 25.5899 | 35.3221 | 38.5817 | 16.9289 | 6.1145 | 2.3643 | 2.5464 | 1.5766 | 2.14 | 9.7322 | 3.2596 | 23.0434 | 25.5899 | 35.3221 | 38.5817 | 0
-2.6001 | 10.3679 | 1.7133 | 1.57 | 2.43 | 2.658 | 4.85 | 7.1858 | 7.7678 | 9.3378 | 14.4258 | 21.6116 | -2.6001 | 10.3679 | 1.7133 | 1.57 | 2.44 | 2.658 | 4.85 | 7.1858 | 7.7678 | 9.3378 | 14.4358 | 21.6216 | 0.01
2.5801 | 6.1366 | 1.886 | 1.829 | 0.74844 | 1.6491 | 6.145 | 3.28 | 8.7168 | 10.5458 | 16.6908 | 19.9708 | 2.5801 | 6.1366 | 1.886 | 1.829 | 0.75844 | 1.6491 | 6.145 | 3.28 | 8.7168 | 10.5458 | 16.6908 | 19.9708 | 0
-7.5094 | 7.259 | 1.5497 | 1.3245 | 3.3043 | 3.1826 | 3.6227 | 4.316 | -0.25035 | 1.0742 | 7.5611 | 11.8771 | -7.5094 | 7.259 | 1.5497 | 1.3245 | 3.3143 | 3.1826 | 3.6227 | 4.316 | -0.25035 | 1.0742 | 7.5711 | 11.8871 | 0.01
7.826 | 5.073 | 2.0609 | 2.0913 | 0.096747 | 1.258 | 7.4565 | 2.2981 | 12.899 | 14.9903 | 22.4468 | 24.7449 | 7.826 | 5.073 | 2.0609 | 2.0913 | 0.10675 | 1.258 | 7.4565 | 2.2981 | 12.899 | 14.9903 | 22.4468 | 24.7449 | 0
-11.4195 | 8.3956 | 1.4193 | 1.129 | 1.1507 | 1.8904 | 2.6451 | 5.3652 | -3.0239 | -1.8949 | 1.1462 | 6.5114 | -11.4195 | 8.3956 | 1.4193 | 1.129 | 1.1607 | 1.8904 | 2.6451 | 5.3652 | -3.0239 | -1.8949 | 1.1562 | 6.5214 | 0.01
-5.0961 | 4.2258 | 1.6301 | 1.4452 | 2.318 | 2.5908 | 4.226 | 1.5161 | -0.87032 | 0.57488 | 5.4837 | 6.9998 | -5.0961 | 4.2258 | 1.6301 | 1.4452 | 2.328 | 2.5908 | 4.226 | 1.5161 | -0.87032 | 0.57488 | 5.4937 | 7.0098 | 0.01
1.9081 | 5.5958 | 1.8636 | 1.7954 | 3.9068 | 3.5441 | 5.977 | 2.7808 | 7.5039 | 9.2993 | 16.7502 | 19.531 | 1.9081 | 5.5958 | 1.8636 | 1.7954 | 3.9168 | 3.5441 | 5.977 | 2.7808 | 7.5039 | 9.2993 | 16.7602 | 19.541 | 0.01
11.4408 | 7.1134 | 2.1814 | 2.272 | 3.9987 | 3.5992 | 8.3602 | 4.1816 | 18.5542 | 20.8263 | 29.1865 | 33.3681 | 11.4408 | 7.1134 | 2.1814 | 2.272 | 4.0087 | 3.5992 | 8.3602 | 4.1816 | 18.5542 | 20.8263 | 29.1865 | 33.3681 | 0
11.9924 | 9.1788 | 2.1997 | 2.2996 | 2.5211 | 2.7127 | 8.4981 | 6.0882 | 21.1712 | 23.4708 | 31.9689 | 38.0571 | 11.9924 | 9.1788 | 2.1997 | 2.2996 | 2.5311 | 2.7127 | 8.4981 | 6.0882 | 21.1712 | 23.4708 | 31.9689 | 38.0571 | 0
3.1269 | 9.2983 | 1.9042 | 1.8563 | 2.6077 | 2.7646 | 6.2817 | 6.1985 | 12.4252 | 14.2815 | 20.5633 | 26.7617 | 3.1269 | 9.2983 | 1.9042 | 1.8563 | 2.6177 | 2.7646 | 6.2817 | 6.1985 | 12.4252 | 14.2815 | 20.5633 | 26.7617 | 0
3.646 | 7.3775 | 1.9215 | 1.8823 | 3.8705 | 3.5223 | 6.4115 | 4.4254 | 11.0234 | 12.9057 | 20.2986 | 24.724 | 3.646 | 7.3775 | 1.9215 | 1.8823 | 3.8805 | 3.5223 | 6.4115 | 4.4254 | 11.0234 | 12.9057 | 20.3086 | 24.734 | 0.01
11.2232 | 7.49 | 2.1741 | 2.2612 | 4.6272 | 3.9763 | 8.3058 | 4.5292 | 18.7131 | 20.9743 | 29.5778 | 34.107 | 11.2232 | 7.49 | 2.1741 | 2.2612 | 4.6372 | 3.9763 | 8.3058 | 4.5292 | 18.7131 | 20.9743 | 29.5878 | 34.117 | 0.01
15.7633 | 9.1317 | 2.3254 | 2.4882 | 3.3338 | 3.2003 | 9.4408 | 6.0446 | 24.895 | 27.3831 | 36.8239 | 42.8686 | 15.7633 | 9.1317 | 2.3254 | 2.4882 | 3.3438 | 3.2003 | 9.4408 | 6.0446 | 24.895 | 27.3831 | 36.8239 | 42.8686 | 0
8.0029 | 10.1154 | 2.0668 | 2.1001 | 4.3526 | 3.8116 | 7.5007 | 6.9527 | 18.1183 | 20.2185 | 28.3827 | 35.3354 | 8.0029 | 10.1154 | 2.0668 | 2.1001 | 4.3626 | 3.8116 | 7.5007 | 6.9527 | 18.1183 | 20.2185 | 28.3927 | 35.3454 | 0.01
14.1159 | 8.434 | 2.2705 | 2.4058 | 3.1711 | 3.1026 | 9.029 | 5.4006 | 22.5498 | 24.9556 | 33.9846 | 39.3852 | 14.1159 | 8.434 | 2.2705 | 2.4058 | 3.1811 | 3.1026 | 9.029 | 5.4006 | 22.5498 | 24.9556 | 33.9846 | 39.3852 | 0
7.0265 | 9.7584 | 2.0342 | 2.0513 | 1.0701 | 1.842 | 7.2566 | 6.6232 | 16.7849 | 18.8362 | 26.0929 | 32.716 | 7.0265 | 9.7584 | 2.0342 | 2.0513 | 1.0801 | 1.842 | 7.2566 | 6.6232 | 16.7849 | 18.8362 | 26.0929 | 32.716 | 0
-5.5795 | 8.2224 | 1.614 | 1.421 | 3.1699 | 3.1019 | 4.1051 | 5.2053 | 2.6429 | 4.0639 | 10.3358 | 15.5411 | -5.5795 | 8.2224 | 1.614 | 1.421 | 3.1799 | 3.1019 | 4.1051 | 5.2053 | 2.6429 | 4.0639 | 10.3458 | 15.5511 | 0.01
7.0195 | 5.4911 | 2.034 | 2.051 | 2.44 | 2.664 | 7.2549 | 2.6841 | 12.5106 | 14.5615 | 21.8164 | 24.5005 | 7.0195 | 5.4911 | 2.034 | 2.051 | 2.45 | 2.664 | 7.2549 | 2.6841 | 12.5106 | 14.5615 | 21.8164 | 24.5005 | 0
2.6398 | 8.2209 | 1.888 | 1.832 | 3.9164 | 3.5498 | 6.1599 | 5.2039 | 10.8607 | 12.6926 | 20.1589 | 25.3627 | 2.6398 | 8.2209 | 1.888 | 1.832 | 3.9264 | 3.5498 | 6.1599 | 5.2039 | 10.8607 | 12.6926 | 20.1689 | 25.3727 | 0.01
11.4983 | 7.272 | 2.1833 | 2.2749 | 2.2667 | 2.56 | 8.3746 | 4.328 | 18.7703 | 21.0452 | 29.4197 | 33.7477 | 11.4983 | 7.272 | 2.1833 | 2.2749 | 2.2767 | 2.56 | 8.3746 | 4.328 | 18.7703 | 21.0452 | 29.4197 | 33.7477 | 0
1.6003 | 9.1913 | 1.8533 | 1.78 | 0.78163 | 1.669 | 5.9001 | 6.0997 | 10.7916 | 12.5716 | 18.4716 | 24.5713 | 1.6003 | 9.1913 | 1.8533 | 1.78 | 0.79163 | 1.669 | 5.9001 | 6.0997 | 10.7916 | 12.5716 | 18.4716 | 24.5713 | 0
-7.3102 | 7.0467 | 1.5563 | 1.3345 | 4.619 | 3.9714 | 3.6724 | 4.1201 | -0.26348 | 1.071 | 9.6614 | 13.7815 | -7.3102 | 7.0467 | 1.5563 | 1.3345 | 4.629 | 3.9714 | 3.6724 | 4.1201 | -0.26348 | 1.071 | 9.6714 | 13.7915 | 0.01
15.714 | 5.1161 | 2.3238 | 2.4857 | 4.1687 | 3.7012 | 9.4285 | 2.338 | 20.8301 | 23.3158 | 32.7443 | 35.0823 | 15.714 | 5.1161 | 2.3238 | 2.4857 | 4.1787 | 3.7012 | 9.4285 | 2.338 | 20.8301 | 23.3158 | 32.7443 | 35.0823 | 0
13.0123 | 10.1047 | 2.2337 | 2.3506 | 0.93932 | 1.7636 | 8.7531 | 6.9428 | 23.117 | 25.4677 | 34.2207 | 41.1635 | 13.0123 | 10.1047 | 2.2337 | 2.3506 | 0.94932 | 1.7636 | 8.7531 | 6.9428 | 23.117 | 25.4677 | 34.2207 | 41.1635 | 0
-6.3641 | 9.5193 | 1.5879 | 1.3818 | 3.1006 | 3.0604 | 3.909 | 6.4025 | 3.1553 | 4.5371 | 10.698 | 17.1005 | -6.3641 | 9.5193 | 1.5879 | 1.3818 | 3.1106 | 3.0604 | 3.909 | 6.4025 | 3.1553 | 4.5371 | 10.708 | 17.1105 | 0.01
6.6035 | 5.3211 | 2.0201 | 2.0302 | 3.8656 | 3.5194 | 7.1509 | 2.5272 | 11.9246 | 13.9548 | 21.3398 | 23.867 | 6.6035 | 5.3211 | 2.0201 | 2.0302 | 3.8756 | 3.5194 | 7.1509 | 2.5272 | 11.9246 | 13.9548 | 21.3498 | 23.877 | 0.01
11.1936 | 8.1308 | 2.1731 | 2.2597 | 2.3992 | 2.6395 | 8.2984 | 5.1207 | 19.3244 | 21.584 | 29.8824 | 35.0031 | 11.1936 | 8.1308 | 2.1731 | 2.2597 | 2.4092 | 2.6395 | 8.2984 | 5.1207 | 19.3244 | 21.584 | 29.8824 | 35.0031 | 0
2.3952 | 9.1253 | 1.8798 | 1.8198 | 4.4598 | 3.8759 | 6.0988 | 6.0387 | 11.5205 | 13.3403 | 21.6759 | 27.7146 | 2.3952 | 9.1253 | 1.8798 | 1.8198 | 4.4698 | 3.8759 | 6.0988 | 6.0387 | 11.5205 | 13.3403 | 21.6859 | 27.7246 | 0.01
14.7587 | 7.219 | 2.292 | 2.4379 | 4.6718 | 4.0031 | 9.1897 | 4.279 | 21.9776 | 24.4156 | 33.6053 | 37.8843 | 14.7587 | 7.219 | 2.292 | 2.4379 | 4.6818 | 4.0031 | 9.1897 | 4.279 | 21.9776 | 24.4156 | 33.6053 | 37.8843 | 0
16.0308 | 9.8977 | 2.3344 | 2.5015 | 2.5827 | 2.7496 | 9.5077 | 6.7517 | 25.9285 | 28.4301 | 37.9378 | 44.6895 | 16.0308 | 9.8977 | 2.3344 | 2.5015 | 2.5927 | 2.7496 | 9.5077 | 6.7517 | 25.9285 | 28.4301 | 37.9378 | 44.6895 | 0
3.496 | 10.1733 | 1.9165 | 1.8748 | 2.8107 | 2.8864 | 6.374 | 7.0062 | 13.6693 | 15.5441 | 21.9181 | 28.9243 | 3.496 | 10.1733 | 1.9165 | 1.8748 | 2.8207 | 2.8864 | 6.374 | 7.0062 | 13.6693 | 15.5441 | 21.9181 | 28.9243 | 0
4.8644 | 7.4575 | 1.9621 | 1.9432 | 4.7599 | 4.0559 | 6.7161 | 4.4992 | 12.3218 | 14.265 | 23.0809 | 27.5801 | 4.8644 | 7.4575 | 1.9621 | 1.9432 | 4.7699 | 4.0559 | 6.7161 | 4.4992 | 12.3218 | 14.265 | 23.0909 | 27.5901 | 0.01
16.5595 | 7.7539 | 2.352 | 2.528 | 5.0114 | 4.2069 | 9.6399 | 4.7729 | 24.3134 | 26.8414 | 36.4813 | 41.2541 | 16.5595 | 7.7539 | 2.352 | 2.528 | 5.0214 | 4.2069 | 9.6399 | 4.7729 | 24.3134 | 26.8414 | 36.4813 | 41.2541 | 0
18.0686 | 10.2879 | 2.4023 | 2.6034 | 4.3153 | 3.7892 | 10.0172 | 7.1119 | 28.3565 | 30.9599 | 40.9771 | 48.089 | 18.0686 | 10.2879 | 2.4023 | 2.6034 | 4.3253 | 3.7892 | 10.0172 | 7.1119 | 28.3565 | 30.9599 | 40.9771 | 48.089 | 0
13.8917 | 10.6149 | 2.2631 | 2.3946 | 3.384 | 3.2304 | 8.9729 | 7.4137 | 24.5065 | 26.9011 | 35.874 | 43.2878 | 13.8917 | 10.6149 | 2.2631 | 2.3946 | 3.394 | 3.2304 | 8.9729 | 7.4137 | 24.5065 | 26.9011 | 35.874 | 43.2878 | 0
8.3042 | 9.7099 | 2.0768 | 2.1152 | 2.9744 | 2.9846 | 7.576 | 6.5783 | 18.014 | 20.1292 | 27.7053 | 34.2836 | 8.3042 | 9.7099 | 2.0768 | 2.1152 | 2.9844 | 2.9846 | 7.576 | 6.5783 | 18.014 | 20.1292 | 27.7053 | 34.2836 | 0
5.8464 | 8.4992 | 1.9949 | 1.9923 | 4.3016 | 3.781 | 6.9616 | 5.4608 | 14.3457 | 16.338 | 24.4206 | 29.8814 | 5.8464 | 8.4992 | 1.9949 | 1.9923 | 4.3116 | 3.781 | 6.9616 | 5.4608 | 14.3457 | 16.338 | 24.4306 | 29.8914 | 0.01
13.8097 | 7.9667 | 2.2603 | 2.3905 | 3.6323 | 3.3794 | 8.9524 | 4.9693 | 21.7765 | 24.1669 | 33.1194 | 38.0887 | 13.8097 | 7.9667 | 2.2603 | 2.3905 | 3.6423 | 3.3794 | 8.9524 | 4.9693 | 21.7765 | 24.1669 | 33.1194 | 38.0887 | 0
9.7938 | 9.6921 | 2.1265 | 2.1897 | 3.7296 | 3.4377 | 7.9485 | 6.5619 | 19.4859 | 21.6756 | 29.6241 | 36.186 | 9.7938 | 9.6921 | 2.1265 | 2.1897 | 3.7396 | 3.4377 | 7.9485 | 6.5619 | 19.4859 | 21.6756 | 29.6241 | 36.186 | 0
10.3775 | 8.822 | 2.1459 | 2.2189 | 4.6453 | 3.9872 | 8.0944 | 5.7588 | 19.1995 | 21.4184 | 30.0509 | 35.8096 | 10.3775 | 8.822 | 2.1459 | 2.2189 | 4.6553 | 3.9872 | 8.0944 | 5.7588 | 19.1995 | 21.4184 | 30.0609 | 35.8196 | 0.01
15.8718 | 8.9485 | 2.3291 | 2.4936 | 2.8253 | 2.8952 | 9.468 | 5.8755 | 24.8203 | 27.3139 | 36.7818 | 42.6573 | 15.8718 | 8.9485 | 2.3291 | 2.4936 | 2.8353 | 2.8952 | 9.468 | 5.8755 | 24.8203 | 27.3139 | 36.7818 | 42.6573 | 0
4.9521 | 10.1389 | 1.9651 | 1.9476 | 2.6385 | 2.7831 | 6.738 | 6.9744 | 15.091 | 17.0386 | 23.7766 | 30.751 | 4.9521 | 10.1389 | 1.9651 | 1.9476 | 2.6485 | 2.7831 | 6.738 | 6.9744 | 15.091 | 17.0386 | 23.7766 | 30.751 | 0
3.8311 | 7.7729 | 1.9277 | 1.8916 | 2.9743 | 2.9846 | 6.4578 | 4.7904 | 11.604 | 13.4956 | 19.9533 | 24.7438 | 3.8311 | 7.7729 | 1.9277 | 1.8916 | 2.9843 | 2.9846 | 6.4578 | 4.7904 | 11.604 | 13.4956 | 19.9533 | 24.7438 | 0
5.8458 | 7.5301 | 1.9949 | 1.9923 | 1.9744 | 2.3846 | 6.9614 | 4.5662 | 13.3758 | 15.3681 | 22.3296 | 26.8958 | 5.8458 | 7.5301 | 1.9949 | 1.9923 | 1.9844 | 2.3846 | 6.9614 | 4.5662 | 13.3758 | 15.3681 | 22.3296 | 26.8958 | 0
-0.15369 | 7.9666 | 1.7949 | 1.6923 | 3.4835 | 3.2901 | 5.4616 | 4.9692 | 7.8129 | 9.5052 | 16.2788 | 21.248 | -0.15369 | 7.9666 | 1.7949 | 1.6923 | 3.4935 | 3.2901 | 5.4616 | 4.9692 | 7.8129 | 9.5052 | 16.2888 | 21.258 | 0.01
8.9011 | 6.6667 | 2.0967 | 2.1451 | 2.8402 | 2.9041 | 7.7253 | 3.7693 | 15.5678 | 17.7128 | 25.4381 | 29.2073 | 8.9011 | 6.6667 | 2.0967 | 2.1451 | 2.8502 | 2.9041 | 7.7253 | 3.7693 | 15.5678 | 17.7128 | 25.4381 | 29.2073 | 0
5.0411 | 8.6286 | 1.968 | 1.9521 | 2.9244 | 2.9547 | 6.7603 | 5.5802 | 13.6697 | 15.6217 | 22.382 | 27.9622 | 5.0411 | 8.6286 | 1.968 | 1.9521 | 2.9344 | 2.9547 | 6.7603 | 5.5802 | 13.6697 | 15.6217 | 22.382 | 27.9622 | 0
5.5467 | 7.7922 | 1.9849 | 1.9773 | 2.7834 | 2.87 | 6.8867 | 4.8082 | 13.3389 | 15.3163 | 22.2029 | 27.0112 | 5.5467 | 7.7922 | 1.9849 | 1.9773 | 2.7934 | 2.87 | 6.8867 | 4.8082 | 13.3389 | 15.3163 | 22.2029 | 27.0112 | 0
4.7002 | 7.9018 | 1.9567 | 1.935 | 2.2444 | 2.5466 | 6.675 | 4.9093 | 12.602 | 14.537 | 21.212 | 26.1214 | 4.7002 | 7.9018 | 1.9567 | 1.935 | 2.2544 | 2.5466 | 6.675 | 4.9093 | 12.602 | 14.537 | 21.212 | 26.1214 | 0
1.4663 | 7.7184 | 1.8489 | 1.7733 | 3.148 | 3.0888 | 5.8666 | 4.74 | 9.1847 | 10.958 | 17.1947 | 21.9348 | 1.4663 | 7.7184 | 1.8489 | 1.7733 | 3.158 | 3.0888 | 5.8666 | 4.74 | 9.1847 | 10.958 | 17.2047 | 21.9448 | 0.01
6.8879 | 7.0177 | 2.0296 | 2.0444 | 1.6145 | 2.1687 | 7.222 | 4.0933 | 13.9056 | 15.95 | 23.1719 | 27.2652 | 6.8879 | 7.0177 | 2.0296 | 2.0444 | 1.6245 | 2.1687 | 7.222 | 4.0933 | 13.9056 | 15.95 | 23.1719 | 27.2652 | 0
-2.3129 | 8.1924 | 1.7229 | 1.5844 | 2.1422 | 2.4853 | 4.9218 | 5.1776 | 5.8795 | 7.4639 | 12.3856 | 17.5632 | -2.3129 | 8.1924 | 1.7229 | 1.5844 | 2.1522 | 2.4853 | 4.9218 | 5.1776 | 5.8795 | 7.4639 | 12.3856 | 17.5632 | 0
0.85301 | 6.1989 | 1.8284 | 1.7427 | 3.3938 | 3.2363 | 5.7133 | 3.3374 | 7.0519 | 8.7945 | 15.4247 | 18.7621 | 0.85301 | 6.1989 | 1.8284 | 1.7427 | 3.4038 | 3.2363 | 5.7133 | 3.3374 | 7.0519 | 8.7945 | 15.4347 | 18.7721 | 0.01
8.363 | 6.8848 | 2.0788 | 2.1181 | 2.8631 | 2.9179 | 7.5907 | 3.9706 | 15.2478 | 17.366 | 24.9567 | 28.9273 | 8.363 | 6.8848 | 2.0788 | 2.1181 | 2.8731 | 2.9179 | 7.5907 | 3.9706 | 15.2478 | 17.366 | 24.9567 | 28.9273 | 0
5.1786 | 8.512 | 1.9726 | 1.9589 | 2.7811 | 2.8686 | 6.7946 | 5.4726 | 13.6906 | 15.6495 | 22.4441 | 27.9167 | 5.1786 | 8.512 | 1.9726 | 1.9589 | 2.7911 | 2.8686 | 6.7946 | 5.4726 | 13.6906 | 15.6495 | 22.4441 | 27.9167 | 0
4.6863 | 7.822 | 1.9562 | 1.9343 | 1.7183 | 2.231 | 6.6716 | 4.8357 | 12.5083 | 14.4427 | 21.1142 | 25.95 | 4.6863 | 7.822 | 1.9562 | 1.9343 | 1.7283 | 2.231 | 6.6716 | 4.8357 | 12.5083 | 14.4427 | 21.1142 | 25.95 | 0
-1.69 | 7.7154 | 1.7437 | 1.6155 | 2.6544 | 2.7926 | 5.0775 | 4.7373 | 6.0254 | 7.6409 | 13.0879 | 17.8252 | -1.69 | 7.7154 | 1.7437 | 1.6155 | 2.6644 | 2.7926 | 5.0775 | 4.7373 | 6.0254 | 7.6409 | 13.0979 | 17.8352 | 0.01
3.9263 | 6.3338 | 1.9309 | 1.8963 | 2.8467 | 2.908 | 6.4816 | 3.462 | 10.2601 | 12.1564 | 18.638 | 22.1 | 3.9263 | 6.3338 | 1.9309 | 1.8963 | 2.8567 | 2.908 | 6.4816 | 3.462 | 10.2601 | 12.1564 | 18.638 | 22.1 | 0
5.0801 | 7.5507 | 1.9693 | 1.954 | 2.9045 | 2.9427 | 6.77 | 4.5853 | 12.6307 | 14.5847 | 21.3548 | 25.94 | 5.0801 | 7.5507 | 1.9693 | 1.954 | 2.9145 | 2.9427 | 6.77 | 4.5853 | 12.6307 | 14.5847 | 21.3548 | 25.94 | 0
5.4268 | 7.8007 | 1.9809 | 1.9713 | 4.1252 | 3.6751 | 6.8567 | 4.816 | 13.2274 | 15.1988 | 22.9991 | 27.8151 | 5.4268 | 7.8007 | 1.9809 | 1.9713 | 4.1352 | 3.6751 | 6.8567 | 4.816 | 13.2274 | 15.1988 | 23.0091 | 27.8251 | 0.01
12.7511 | 7.8758 | 2.225 | 2.3376 | 3.8581 | 3.5149 | 8.6878 | 4.8854 | 20.6269 | 22.9645 | 31.6522 | 36.5376 | 12.7511 | 7.8758 | 2.225 | 2.3376 | 3.8681 | 3.5149 | 8.6878 | 4.8854 | 20.6269 | 22.9645 | 31.6522 | 36.5376 | 0
11.1487 | 9.4627 | 2.1716 | 2.2574 | 3.4723 | 3.2834 | 8.2872 | 6.3502 | 20.6114 | 22.8689 | 31.1561 | 37.5063 | 11.1487 | 9.4627 | 2.1716 | 2.2574 | 3.4823 | 3.2834 | 8.2872 | 6.3502 | 20.6114 | 22.8689 | 31.1561 | 37.5063 | 0
8.834 | 9.1156 | 2.0945 | 2.1417 | 3.2206 | 3.1323 | 7.7085 | 6.0297 | 17.9496 | 20.0913 | 27.7998 | 33.8295 | 8.834 | 9.1156 | 2.0945 | 2.1417 | 3.2306 | 3.1323 | 7.7085 | 6.0297 | 17.9496 | 20.0913 | 27.7998 | 33.8295 | 0
7.3235 | 8.614 | 2.0441 | 2.0662 | 3.2162 | 3.1297 | 7.3309 | 5.5668 | 15.9375 | 18.0037 | 25.3346 | 30.9014 | 7.3235 | 8.614 | 2.0441 | 2.0662 | 3.2262 | 3.1297 | 7.3309 | 5.5668 | 15.9375 | 18.0037 | 25.3346 | 30.9014 | 0
7.2969 | 8.2868 | 2.0432 | 2.0648 | 3.2464 | 3.1478 | 7.3242 | 5.2647 | 15.5837 | 17.6485 | 24.9727 | 30.2374 | 7.2969 | 8.2868 | 2.0432 | 2.0648 | 3.2564 | 3.1478 | 7.3242 | 5.2647 | 15.5837 | 17.6485 | 24.9727 | 30.2374 | 0
7.4785 | 8.281 | 2.0493 | 2.0739 | 1.9766 | 2.386 | 7.3696 | 5.2594 | 15.7595 | 17.8334 | 25.203 | 30.4624 | 7.4785 | 8.281 | 2.0493 | 2.0739 | 1.9866 | 2.386 | 7.3696 | 5.2594 | 15.7595 | 17.8334 | 25.203 | 30.4624 | 0
-0.14037 | 8.3203 | 1.7953 | 1.693 | 2.9701 | 2.9821 | 5.4649 | 5.2957 | 8.18 | 9.873 | 15.8251 | 21.1208 | -0.14037 | 8.3203 | 1.7953 | 1.693 | 2.9801 | 2.9821 | 5.4649 | 5.2957 | 8.18 | 9.873 | 15.8351 | 21.1308 | 0.01
5.8206 | 6.6696 | 1.994 | 1.991 | 1.6681 | 2.2008 | 6.9552 | 3.7719 | 12.4902 | 14.4813 | 21.4364 | 25.2083 | 5.8206 | 6.6696 | 1.994 | 1.991 | 1.6781 | 2.2008 | 6.9552 | 3.7719 | 12.4902 | 14.4813 | 21.4364 | 25.2083 | 0
-1.9916 | 7.9611 | 1.7336 | 1.6004 | 4.1051 | 3.6631 | 5.0021 | 4.9641 | 5.9696 | 7.57 | 15.3382 | 20.3023 | -1.9916 | 7.9611 | 1.7336 | 1.6004 | 4.1151 | 3.6631 | 5.0021 | 4.9641 | 5.9696 | 7.57 | 15.3482 | 20.3123 | 0.01
12.6307 | 6.2685 | 2.221 | 2.3315 | 3.1409 | 3.0845 | 8.6577 | 3.4017 | 18.8992 | 21.2308 | 29.8884 | 33.2901 | 12.6307 | 6.2685 | 2.221 | 2.3315 | 3.1509 | 3.0845 | 8.6577 | 3.4017 | 18.8992 | 21.2308 | 29.8884 | 33.2901 | 0
6.8453 | 9.4367 | 2.0282 | 2.0423 | 1.4547 | 2.0728 | 7.2113 | 6.3261 | 16.282 | 18.3243 | 25.5356 | 31.8617 | 6.8453 | 9.4367 | 2.0282 | 2.0423 | 1.4647 | 2.0728 | 7.2113 | 6.3261 | 16.282 | 18.3243 | 25.5356 | 31.8617 | 0
-3.272 | 8.1832 | 1.6909 | 1.5364 | 2.8971 | 2.9383 | 4.682 | 5.1691 | 4.9112 | 6.4476 | 12.283 | 17.452 | -3.272 | 8.1832 | 1.6909 | 1.5364 | 2.9071 | 2.9383 | 4.682 | 5.1691 | 4.9112 | 6.4476 | 12.293 | 17.462 | 0.01
5.3827 | 5.9911 | 1.9794 | 1.9691 | 4.3756 | 3.8253 | 6.8457 | 3.1456 | 11.3738 | 13.3429 | 21.5439 | 24.6895 | 5.3827 | 5.9911 | 1.9794 | 1.9691 | 4.3856 | 3.8253 | 6.8457 | 3.1456 | 11.3738 | 13.3429 | 21.5539 | 24.6995 | 0.01
14.2535 | 7.8663 | 2.2751 | 2.4127 | 2.174 | 2.5044 | 9.0634 | 4.8765 | 22.1197 | 24.5324 | 33.5958 | 38.4723 | 14.2535 | 7.8663 | 2.2751 | 2.4127 | 2.184 | 2.5044 | 9.0634 | 4.8765 | 22.1197 | 24.5324 | 33.5958 | 38.4723 | 0
1.0437 | 9.7882 | 1.8348 | 1.7522 | 2.1204 | 2.4722 | 5.7609 | 6.6507 | 10.832 | 12.5842 | 18.3451 | 24.9958 | 1.0437 | 9.7882 | 1.8348 | 1.7522 | 2.1304 | 2.4722 | 5.7609 | 6.6507 | 10.832 | 12.5842 | 18.3451 | 24.9958 | 0
0.72232 | 6.9261 | 1.8241 | 1.7361 | 3.0018 | 3.0011 | 5.6806 | 4.0087 | 7.6485 | 9.3846 | 15.3874 | 19.3962 | 0.72232 | 6.9261 | 1.8241 | 1.7361 | 3.0118 | 3.0011 | 5.6806 | 4.0087 | 7.6485 | 9.3846 | 15.3974 | 19.4062 | 0.01
6.0106 | 6.8565 | 2.0004 | 2.0005 | 2.5764 | 2.7458 | 7.0026 | 3.9445 | 12.8671 | 14.8676 | 21.8703 | 25.8147 | 6.0106 | 6.8565 | 2.0004 | 2.0005 | 2.5864 | 2.7458 | 7.0026 | 3.9445 | 12.8671 | 14.8676 | 21.8703 | 25.8147 | 0
3.4584 | 8.0023 | 1.9153 | 1.8729 | 0.37298 | 1.4238 | 6.3646 | 5.0021 | 11.4607 | 13.3337 | 19.6983 | 24.7004 | 3.4584 | 8.0023 | 1.9153 | 1.8729 | 0.38298 | 1.4238 | 6.3646 | 5.0021 | 11.4607 | 13.3337 | 19.6983 | 24.7004 | 0
-9.7621 | 7.4493 | 1.4746 | 1.2119 | 2.7077 | 2.8246 | 3.0595 | 4.4917 | -2.3128 | -1.1009 | 4.4314 | 8.9231 | -9.7621 | 7.4493 | 1.4746 | 1.2119 | 2.7177 | 2.8246 | 3.0595 | 4.4917 | -2.3128 | -1.1009 | 4.4414 | 8.9331 | 0.01
4.2463 | 4.5849 | 1.9415 | 1.9123 | 2.3095 | 2.5857 | 6.5616 | 1.8476 | 8.8311 | 10.7435 | 17.305 | 19.1526 | 4.2463 | 4.5849 | 1.9415 | 1.9123 | 2.3195 | 2.5857 | 6.5616 | 1.8476 | 8.8311 | 10.7435 | 17.305 | 19.1526 | 0
1.8569 | 7.62 | 1.8619 | 1.7928 | 3.3009 | 3.1806 | 5.9642 | 4.6493 | 9.4769 | 11.2698 | 17.7513 | 22.4005 | 1.8569 | 7.62 | 1.8619 | 1.7928 | 3.3109 | 3.1806 | 5.9642 | 4.6493 | 9.4769 | 11.2698 | 17.7613 | 22.4105 | 0.01
7.8055 | 7.1023 | 2.0602 | 2.0903 | 1.9738 | 2.3843 | 7.4514 | 4.1714 | 14.9079 | 16.9981 | 24.4495 | 28.6209 | 7.8055 | 7.1023 | 2.0602 | 2.0903 | 1.9838 | 2.3843 | 7.4514 | 4.1714 | 14.9079 | 16.9981 | 24.4495 | 28.6209 | 0
-0.15737 | 8.3912 | 1.7948 | 1.6921 | 2.3419 | 2.6052 | 5.4607 | 5.3611 | 8.2338 | 9.926 | 15.3866 | 20.7477 | -0.15737 | 8.3912 | 1.7948 | 1.6921 | 2.3519 | 2.6052 | 5.4607 | 5.3611 | 8.2338 | 9.926 | 15.3866 | 20.7477 | 0
2.0516 | 6.6659 | 1.8684 | 1.8026 | 4.6939 | 4.0163 | 6.0129 | 3.7685 | 8.7175 | 10.5201 | 19.2303 | 22.9989 | 2.0516 | 6.6659 | 1.8684 | 1.8026 | 4.7039 | 4.0163 | 6.0129 | 3.7685 | 8.7175 | 10.5201 | 19.2403 | 23.0089 | 0.01
16.1634 | 7.1445 | 2.3388 | 2.5082 | 2.4881 | 2.6928 | 9.5409 | 4.2103 | 23.308 | 25.8161 | 35.357 | 39.5673 | 16.1634 | 7.1445 | 2.3388 | 2.5082 | 2.4981 | 2.6928 | 9.5409 | 4.2103 | 23.308 | 25.8161 | 35.357 | 39.5673 | 0
2.9283 | 10.2021 | 1.8976 | 1.8464 | 1.8229 | 2.2937 | 6.2321 | 7.0327 | 13.1304 | 14.9768 | 21.2089 | 28.2416 | 2.9283 | 10.2021 | 1.8976 | 1.8464 | 1.8329 | 2.2937 | 6.2321 | 7.0327 | 13.1304 | 14.9768 | 21.2089 | 28.2416 | 0
-1.0626 | 7.3345 | 1.7646 | 1.6469 | 3.6826 | 3.4096 | 5.2344 | 4.3857 | 6.2719 | 7.9188 | 15.0109 | 19.3966 | -1.0626 | 7.3345 | 1.7646 | 1.6469 | 3.6926 | 3.4096 | 5.2344 | 4.3857 | 6.2719 | 7.9188 | 15.0209 | 19.4066 | 0.01
10.0956 | 6.4698 | 2.1365 | 2.2048 | 2.7751 | 2.865 | 8.0239 | 3.5875 | 16.5653 | 18.7701 | 26.794 | 30.3815 | 10.0956 | 6.4698 | 2.1365 | 2.2048 | 2.7851 | 2.865 | 8.0239 | 3.5875 | 16.5653 | 18.7701 | 26.794 | 30.3815 | 0
4.6504 | 8.8874 | 1.955 | 1.9325 | 4.5711 | 3.9427 | 6.6626 | 5.8191 | 13.5378 | 15.4703 | 23.9841 | 29.8032 | 4.6504 | 8.8874 | 1.955 | 1.9325 | 4.5811 | 3.9427 | 6.6626 | 5.8191 | 13.5378 | 15.4703 | 23.9941 | 29.8132 | 0.01
15.4267 | 7.7076 | 2.3142 | 2.4713 | 4.305 | 3.783 | 9.3567 | 4.7301 | 23.1343 | 25.6057 | 34.9624 | 39.6924 | 15.4267 | 7.7076 | 2.3142 | 2.4713 | 4.315 | 3.783 | 9.3567 | 4.7301 | 23.1343 | 25.6057 | 34.9624 | 39.6924 | 0
13.8297 | 10.0425 | 2.261 | 2.3915 | 2.4924 | 2.6954 | 8.9574 | 6.8853 | 23.8722 | 26.2637 | 35.2211 | 42.1065 | 13.8297 | 10.0425 | 2.261 | 2.3915 | 2.5024 | 2.6954 | 8.9574 | 6.8853 | 23.8722 | 26.2637 | 35.2211 | 42.1065 | 0
2.9545 | 9.6964 | 1.8985 | 1.8477 | 3.7825 | 3.4695 | 6.2386 | 6.5659 | 12.6509 | 14.4986 | 21.7506 | 28.3166 | 2.9545 | 9.6964 | 1.8985 | 1.8477 | 3.7925 | 3.4695 | 6.2386 | 6.5659 | 12.6509 | 14.4986 | 21.7606 | 28.3266 | 0.01
10.6949 | 7.3401 | 2.1565 | 2.2347 | 2.8622 | 2.9173 | 8.1737 | 4.3909 | 18.035 | 20.2698 | 28.4435 | 32.8344 | 10.6949 | 7.3401 | 2.1565 | 2.2347 | 2.8722 | 2.9173 | 8.1737 | 4.3909 | 18.035 | 20.2698 | 28.4435 | 32.8344 | 0
5.1733 | 9.0172 | 1.9724 | 1.9587 | 3.1984 | 3.119 | 6.7933 | 5.939 | 14.1905 | 16.1492 | 22.9425 | 28.8815 | 5.1733 | 9.0172 | 1.9724 | 1.9587 | 3.2084 | 3.119 | 6.7933 | 5.939 | 14.1905 | 16.1492 | 22.9425 | 28.8815 | 0
7.1904 | 7.8209 | 2.0397 | 2.0595 | 1.3371 | 2.0022 | 7.2976 | 4.8347 | 15.0112 | 17.0708 | 24.3683 | 29.203 | 7.1904 | 7.8209 | 2.0397 | 2.0595 | 1.3471 | 2.0022 | 7.2976 | 4.8347 | 15.0112 | 17.0708 | 24.3683 | 29.203 | 0
-3.9776 | 8.2579 | 1.6674 | 1.5011 | 2.9624 | 2.9775 | 4.5056 | 5.2381 | 4.2803 | 5.7815 | 11.7213 | 16.9594 | -3.9776 | 8.2579 | 1.6674 | 1.5011 | 2.9724 | 2.9775 | 4.5056 | 5.2381 | 4.2803 | 5.7815 | 11.7313 | 16.9694 | 0.01
5.7745 | 5.8382 | 1.9925 | 1.9887 | 3.2345 | 3.1407 | 6.9436 | 3.0045 | 11.6127 | 13.6015 | 20.5451 | 23.5496 | 5.7745 | 5.8382 | 1.9925 | 1.9887 | 3.2445 | 3.1407 | 6.9436 | 3.0045 | 11.6127 | 13.6015 | 20.5451 | 23.5496 | 0
7.4073 | 7.9511 | 2.0469 | 2.0704 | 3.9585 | 3.5751 | 7.3518 | 4.9549 | 15.3584 | 17.4288 | 24.9625 | 29.9174 | 7.4073 | 7.9511 | 2.0469 | 2.0704 | 3.9685 | 3.5751 | 7.3518 | 4.9549 | 15.3584 | 17.4288 | 24.9725 | 29.9274 | 0.01
11.7513 | 8.3049 | 2.1917 | 2.2876 | 2.7908 | 2.8745 | 8.4378 | 5.2815 | 20.0562 | 22.3438 | 30.7816 | 36.063 | 11.7513 | 8.3049 | 2.1917 | 2.2876 | 2.8008 | 2.8745 | 8.4378 | 5.2815 | 20.0562 | 22.3438 | 30.7816 | 36.063 | 0
4.7449 | 9.2461 | 1.9582 | 1.9372 | 1.7315 | 2.2389 | 6.6862 | 6.1503 | 13.991 | 15.9283 | 22.6145 | 28.7648 | 4.7449 | 9.2461 | 1.9582 | 1.9372 | 1.7415 | 2.2389 | 6.6862 | 6.1503 | 13.991 | 15.9283 | 22.6145 | 28.7648 | 0
-1.6111 | 7.7281 | 1.7463 | 1.6194 | 2.8944 | 2.9366 | 5.0972 | 4.749 | 6.1169 | 7.7364 | 13.5674 | 18.3163 | -1.6111 | 7.7281 | 1.7463 | 1.6194 | 2.9044 | 2.9366 | 5.0972 | 4.749 | 6.1169 | 7.7364 | 13.5774 | 18.3263 | 0.01
5.3662 | 6.3509 | 1.9789 | 1.9683 | 3.0773 | 3.0464 | 6.8415 | 3.4778 | 11.7171 | 13.6854 | 20.527 | 24.0047 | 5.3662 | 6.3509 | 1.9789 | 1.9683 | 3.0873 | 3.0464 | 6.8415 | 3.4778 | 11.7171 | 13.6854 | 20.527 | 24.0047 | 0
6.4638 | 7.8627 | 2.0155 | 2.0232 | 2.5815 | 2.7489 | 7.116 | 4.8732 | 14.3265 | 16.3497 | 23.4657 | 28.3389 | 6.4638 | 7.8627 | 2.0155 | 2.0232 | 2.5915 | 2.7489 | 7.116 | 4.8732 | 14.3265 | 16.3497 | 23.4657 | 28.3389 | 0
3.4889 | 8.1005 | 1.9163 | 1.8744 | 1.8665 | 2.3199 | 6.3722 | 5.0928 | 11.5894 | 13.4638 | 19.836 | 24.9288 | 3.4889 | 8.1005 | 1.9163 | 1.8744 | 1.8765 | 2.3199 | 6.3722 | 5.0928 | 11.5894 | 13.4638 | 19.836 | 24.9288 | 0
-0.80079 | 7.4559 | 1.7733 | 1.66 | 4.0774 | 3.6465 | 5.2998 | 4.4978 | 6.6551 | 8.3151 | 16.039 | 20.5368 | -0.80079 | 7.4559 | 1.7733 | 1.66 | 4.0874 | 3.6465 | 5.2998 | 4.4978 | 6.6551 | 8.3151 | 16.049 | 20.5468 | 0.01
12.4646 | 6.5265 | 2.2155 | 2.3232 | 2.1699 | 2.5019 | 8.6161 | 3.6398 | 18.9911 | 21.3143 | 29.9305 | 33.5703 | 12.4646 | 6.5265 | 2.2155 | 2.3232 | 2.1799 | 2.5019 | 8.6161 | 3.6398 | 18.9911 | 21.3143 | 29.9305 | 33.5703 | 0
1.0194 | 9.4007 | 1.834 | 1.751 | 4.2351 | 3.7411 | 5.7549 | 6.2929 | 10.4201 | 12.1711 | 20.1472 | 26.4401 | 1.0194 | 9.4007 | 1.834 | 1.751 | 4.2451 | 3.7411 | 5.7549 | 6.2929 | 10.4201 | 12.1711 | 20.1572 | 26.4501 | 0.01
13.4105 | 6.9209 | 2.247 | 2.3705 | 1.9519 | 2.3711 | 8.8526 | 4.0039 | 20.3314 | 22.7019 | 31.5546 | 35.5585 | 13.4105 | 6.9209 | 2.247 | 2.3705 | 1.9619 | 2.3711 | 8.8526 | 4.0039 | 20.3314 | 22.7019 | 31.5546 | 35.5585 | 0
-0.28881 | 9.6056 | 1.7904 | 1.6856 | 2.9194 | 2.9516 | 5.4278 | 6.4821 | 9.3168 | 11.0024 | 16.8734 | 23.3555 | -0.28881 | 9.6056 | 1.7904 | 1.6856 | 2.9294 | 2.9516 | 5.4278 | 6.4821 | 9.3168 | 11.0024 | 16.8834 | 23.3655 | 0.01
5.5165 | 6.6374 | 1.9839 | 1.9758 | 3.7465 | 3.4479 | 6.8791 | 3.7422 | 12.1539 | 14.1297 | 21.3241 | 25.0664 | 5.5165 | 6.6374 | 1.9839 | 1.9758 | 3.7565 | 3.4479 | 6.8791 | 3.7422 | 12.1539 | 14.1297 | 21.3341 | 25.0764 | 0.01
10.479 | 7.8952 | 2.1493 | 2.2239 | 2.4963 | 2.6978 | 8.1197 | 4.9033 | 18.3742 | 20.5982 | 28.7179 | 33.6212 | 10.479 | 7.8952 | 2.1493 | 2.2239 | 2.5063 | 2.6978 | 8.1197 | 4.9033 | 18.3742 | 20.5982 | 28.7179 | 33.6212 | 0
2.978 | 8.9704 | 1.8993 | 1.8489 | 4.1729 | 3.7037 | 6.2445 | 5.8958 | 11.9484 | 13.7973 | 21.6739 | 27.5697 | 2.978 | 8.9704 | 1.8993 | 1.8489 | 4.1829 | 3.7037 | 6.2445 | 5.8958 | 11.9484 | 13.7973 | 21.6839 | 27.5797 | 0.01
13.0371 | 7.3452 | 2.2346 | 2.3519 | 5.043 | 4.2258 | 8.7593 | 4.3956 | 20.3823 | 22.7342 | 32.0031 | 36.3986 | 13.0371 | 7.3452 | 2.2346 | 2.3519 | 5.053 | 4.2258 | 8.7593 | 4.3956 | 20.3823 | 22.7342 | 32.0131 | 36.4086 | 0.01
18.2582 | 9.5247 | 2.4086 | 2.6129 | 1.3136 | 1.9881 | 10.0646 | 6.4074 | 27.7829 | 30.3958 | 40.4604 | 46.8678 | 18.2582 | 9.5247 | 2.4086 | 2.6129 | 1.3236 | 1.9881 | 10.0646 | 6.4074 | 27.7829 | 30.3958 | 40.4604 | 46.8678 | 0
-4.1186 | 10.6559 | 1.6627 | 1.4941 | 3.5481 | 3.3289 | 4.4704 | 7.4516 | 6.5374 | 8.0314 | 14.9084 | 22.36 | -4.1186 | 10.6559 | 1.6627 | 1.4941 | 3.5581 | 3.3289 | 4.4704 | 7.4516 | 6.5374 | 8.0314 | 14.9184 | 22.37 | 0.01
9.2885 | 5.8076 | 2.1096 | 2.1644 | 2.9226 | 2.9536 | 7.8221 | 2.9763 | 15.0962 | 17.2606 | 25.0828 | 28.059 | 9.2885 | 5.8076 | 2.1096 | 2.1644 | 2.9326 | 2.9536 | 7.8221 | 2.9763 | 15.0962 | 17.2606 | 25.0828 | 28.059 | 0
5.5355 | 8.7125 | 1.9845 | 1.9768 | 5.2821 | 4.3692 | 6.8839 | 5.6577 | 14.2481 | 16.2248 | 25.8761 | 31.5339 | 5.5355 | 8.7125 | 1.9845 | 1.9768 | 5.2921 | 4.3692 | 6.8839 | 5.6577 | 14.2481 | 16.2248 | 25.8861 | 31.5439 | 0.01
19.6924 | 7.8994 | 2.4564 | 2.6846 | 1.3027 | 1.9816 | 10.4231 | 4.9071 | 27.5918 | 30.2764 | 40.6995 | 45.6066 | 19.6924 | 7.8994 | 2.4564 | 2.6846 | 1.3127 | 1.9816 | 10.4231 | 4.9071 | 27.5918 | 30.2764 | 40.6995 | 45.6066 | 0
-4.1837 | 10.9667 | 1.6605 | 1.4908 | 2.4833 | 2.69 | 4.4541 | 7.7385 | 6.7829 | 8.2738 | 13.447 | 21.1855 | -4.1837 | 10.9667 | 1.6605 | 1.4908 | 2.4933 | 2.69 | 4.4541 | 7.7385 | 6.7829 | 8.2738 | 13.457 | 21.1955 | 0.01
2.8996 | 5.7935 | 1.8967 | 1.845 | 4.6737 | 4.0042 | 6.2249 | 2.9633 | 8.6931 | 10.5381 | 19.216 | 22.1792 | 2.8996 | 5.7935 | 1.8967 | 1.845 | 4.6837 | 4.0042 | 6.2249 | 2.9633 | 8.6931 | 10.5381 | 19.226 | 22.1892 | 0.01
16.0422 | 7.3282 | 2.3347 | 2.5021 | 2.969 | 2.9814 | 9.5106 | 4.3799 | 23.3705 | 25.8726 | 35.3831 | 39.7631 | 16.0422 | 7.3282 | 2.3347 | 2.5021 | 2.979 | 2.9814 | 9.5106 | 4.3799 | 23.3705 | 25.8726 | 35.3831 | 39.7631 | 0
5.8138 | 10.1758 | 1.9938 | 1.9907 | 2.7846 | 2.8708 | 6.9534 | 7.0084 | 15.9896 | 17.9803 | 24.9337 | 31.9422 | 5.8138 | 10.1758 | 1.9938 | 1.9907 | 2.7946 | 2.8708 | 6.9534 | 7.0084 | 15.9896 | 17.9803 | 24.9337 | 31.9422 | 0
4.7076 | 7.9596 | 1.9569 | 1.9354 | 2.5954 | 2.7572 | 6.6769 | 4.9628 | 12.6673 | 14.6026 | 21.2795 | 26.2423 | 4.7076 | 7.9596 | 1.9569 | 1.9354 | 2.6054 | 2.7572 | 6.6769 | 4.9628 | 12.6673 | 14.6026 | 21.2795 | 26.2423 | 0
3.5724 | 7.72 | 1.9191 | 1.8786 | 4.397 | 3.8382 | 6.3931 | 4.7415 | 11.2924 | 13.171 | 21.4063 | 26.1478 | 3.5724 | 7.72 | 1.9191 | 1.8786 | 4.407 | 3.8382 | 6.3931 | 4.7415 | 11.2924 | 13.171 | 21.4163 | 26.1578 | 0.01
14.3822 | 7.474 | 2.2794 | 2.4191 | 2.2841 | 2.5705 | 9.0955 | 4.5145 | 21.8562 | 24.2753 | 33.3709 | 37.8854 | 14.3822 | 7.474 | 2.2794 | 2.4191 | 2.2941 | 2.5705 | 9.0955 | 4.5145 | 21.8562 | 24.2753 | 33.3709 | 37.8854 | 0
1.7047 | 9.8161 | 1.8568 | 1.7852 | 3.83 | 3.498 | 5.9262 | 6.6764 | 11.5209 | 13.3061 | 20.6341 | 27.3105 | 1.7047 | 9.8161 | 1.8568 | 1.7852 | 3.84 | 3.498 | 5.9262 | 6.6764 | 11.5209 | 13.3061 | 20.6441 | 27.3205 | 0.01
10.98 | 7.0694 | 2.166 | 2.249 | 3.431 | 3.2586 | 8.245 | 4.1409 | 18.0494 | 20.2984 | 28.5434 | 32.6843 | 10.98 | 7.0694 | 2.166 | 2.249 | 3.441 | 3.2586 | 8.245 | 4.1409 | 18.0494 | 20.2984 | 28.5434 | 32.6843 | 0
8.5858 | 9.079 | 2.0862 | 2.1293 | 2.0667 | 2.44 | 7.6465 | 5.996 | 17.6648 | 19.7941 | 27.4406 | 33.4366 | 8.5858 | 9.079 | 2.0862 | 2.1293 | 2.0767 | 2.44 | 7.6465 | 5.996 | 17.6648 | 19.7941 | 27.4406 | 33.4366 | 0
0.40007 | 8.5603 | 1.8133 | 1.72 | 3.5941 | 3.3565 | 5.6 | 5.5172 | 8.9603 | 10.6803 | 17.6309 | 23.1481 | 0.40007 | 8.5603 | 1.8133 | 1.72 | 3.6041 | 3.3565 | 5.6 | 5.5172 | 8.9603 | 10.6803 | 17.6409 | 23.1581 | 0.01
9.5647 | 6.7867 | 2.1188 | 2.1782 | 3.2553 | 3.1532 | 7.8912 | 3.88 | 16.3514 | 18.5296 | 26.4208 | 30.3008 | 9.5647 | 6.7867 | 2.1188 | 2.1782 | 3.2653 | 3.1532 | 7.8912 | 3.88 | 16.3514 | 18.5296 | 26.4208 | 30.3008 | 0
7.5316 | 8.7723 | 2.0511 | 2.0766 | 3.3519 | 3.2111 | 7.3829 | 5.7129 | 16.3039 | 18.3805 | 25.7634 | 31.4763 | 7.5316 | 8.7723 | 2.0511 | 2.0766 | 3.3619 | 3.2111 | 7.3829 | 5.7129 | 16.3039 | 18.3805 | 25.7634 | 31.4763 | 0
8.1115 | 8.3318 | 2.0704 | 2.1056 | 2.3366 | 2.602 | 7.5279 | 5.3063 | 16.4433 | 18.5489 | 26.0767 | 31.3831 | 8.1115 | 8.3318 | 2.0704 | 2.1056 | 2.3466 | 2.602 | 7.5279 | 5.3063 | 16.4433 | 18.5489 | 26.0767 | 31.3831 | 0
2.0197 | 8.4575 | 1.8673 | 1.801 | 2.4549 | 2.6729 | 6.0049 | 5.4223 | 10.4772 | 12.2782 | 18.2831 | 23.7054 | 2.0197 | 8.4575 | 1.8673 | 1.801 | 2.4649 | 2.6729 | 6.0049 | 5.4223 | 10.4772 | 12.2782 | 18.2831 | 23.7054 | 0
2.7292 | 7.1376 | 1.891 | 1.8365 | 3.3007 | 3.1804 | 6.1823 | 4.2039 | 9.8668 | 11.7033 | 18.1844 | 22.3883 | 2.7292 | 7.1376 | 1.891 | 1.8365 | 3.3107 | 3.1804 | 6.1823 | 4.2039 | 9.8668 | 11.7033 | 18.1944 | 22.3983 | 0.01
7.8041 | 7.2913 | 2.0601 | 2.0902 | 3.2421 | 3.1452 | 7.451 | 4.3458 | 15.0954 | 17.1856 | 24.6366 | 28.9825 | 7.8041 | 7.2913 | 2.0601 | 2.0902 | 3.2521 | 3.1452 | 7.451 | 4.3458 | 15.0954 | 17.1856 | 24.6366 | 28.9825 | 0
7.4524 | 8.3909 | 2.0484 | 2.0726 | 3.8806 | 3.5284 | 7.3631 | 5.3608 | 15.8432 | 17.9159 | 25.3248 | 30.6856 | 7.4524 | 8.3909 | 2.0484 | 2.0726 | 3.8906 | 3.5284 | 7.3631 | 5.3608 | 15.8432 | 17.9159 | 25.3348 | 30.6956 | 0.01
11.2836 | 8.3147 | 2.1761 | 2.2642 | 5.2907 | 4.3744 | 8.3209 | 5.2905 | 19.5983 | 21.8625 | 31.5276 | 36.8181 | 11.2836 | 8.3147 | 2.1761 | 2.2642 | 5.3007 | 4.3744 | 8.3209 | 5.2905 | 19.5983 | 21.8625 | 31.5376 | 36.8281 | 0.01
19.7442 | 9.1448 | 2.4581 | 2.6872 | 2.4446 | 2.6667 | 10.4361 | 6.0567 | 28.889 | 31.5762 | 42.0123 | 48.069 | 19.7442 | 9.1448 | 2.4581 | 2.6872 | 2.4546 | 2.6667 | 10.4361 | 6.0567 | 28.889 | 31.5762 | 42.0123 | 48.069 | 0
2.6675 | 10.9779 | 1.8889 | 1.8334 | 2.5403 | 2.7242 | 6.1669 | 7.7488 | 13.6454 | 15.4788 | 21.6456 | 29.3945 | 2.6675 | 10.9779 | 1.8889 | 1.8334 | 2.5503 | 2.7242 | 6.1669 | 7.7488 | 13.6454 | 15.4788 | 21.6456 | 29.3945 | 0
3.2415 | 7.278 | 1.9081 | 1.8621 | 1.9326 | 2.3596 | 6.3104 | 4.3335 | 10.5195 | 12.3816 | 18.692 | 23.0255 | 3.2415 | 7.278 | 1.9081 | 1.8621 | 1.9426 | 2.3596 | 6.3104 | 4.3335 | 10.5195 | 12.3816 | 18.692 | 23.0255 | 0
-0.40435 | 7.4023 | 1.7865 | 1.6798 | 3.4463 | 3.2678 | 5.3989 | 4.4483 | 6.998 | 8.6778 | 15.3919 | 19.8402 | -0.40435 | 7.4023 | 1.7865 | 1.6798 | 3.4563 | 3.2678 | 5.3989 | 4.4483 | 6.998 | 8.6778 | 15.4019 | 19.8502 | 0.01
0

## test activity F
A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | diff
-12.9745 | 3.8889 | 1.3675 | 1.0513 | -0.16242 | 1.1025 | 2.2564 | 1.2051 | -9.0857 | -8.0344 | -5.778 | -4.5729 | -12.9745 | 3.8889 | 1.3675 | 1.0513 | -0.16242 | 1.1125 | 2.2564 | 1.2051 | -9.0857 | -8.0344 | -5.778 | -4.5729 | 0
-0.12216 | 6.6735 | 1.7959 | 1.6939 | 1.9796 | 2.3878 | 5.4695 | 3.7756 | 6.5514 | 8.2453 | 13.7147 | 17.4903 | -0.12216 | 6.6735 | 1.7959 | 1.6939 | 1.9796 | 2.3978 | 5.4695 | 3.7756 | 6.5514 | 8.2453 | 13.7147 | 17.4903 | 0
6.9139 | 8.198 | 2.0305 | 2.0457 | 3.1523 | 3.0914 | 7.2285 | 5.1828 | 15.1119 | 17.1576 | 24.3861 | 29.5689 | 6.9139 | 8.198 | 2.0305 | 2.0457 | 3.1523 | 3.1014 | 7.2285 | 5.1828 | 15.1119 | 17.1576 | 24.3861 | 29.5689 | 0
12.6187 | 9.4341 | 2.2206 | 2.3309 | 4.1031 | 3.6619 | 8.6547 | 6.3237 | 22.0528 | 24.3837 | 33.0384 | 39.3622 | 12.6187 | 9.4341 | 2.2206 | 2.3309 | 4.1031 | 3.6719 | 8.6547 | 6.3237 | 22.0528 | 24.3837 | 33.0384 | 39.3622 | 0
2.4444 | 7.2296 | 1.8815 | 1.8222 | 2.4074 | 2.6444 | 6.1111 | 4.2889 | 9.674 | 11.4962 | 17.6073 | 21.8962 | 2.4444 | 7.2296 | 1.8815 | 1.8222 | 2.4074 | 2.6544 | 6.1111 | 4.2889 | 9.674 | 11.4962 | 17.6073 | 21.8962 | 0
13.5518 | 9.6362 | 2.2517 | 2.3776 | 4.2586 | 3.7552 | 8.888 | 6.5104 | 23.188 | 25.5656 | 34.4536 | 40.9639 | 13.5518 | 9.6362 | 2.2517 | 2.3776 | 4.2586 | 3.7652 | 8.888 | 6.5104 | 23.188 | 25.5656 | 34.4536 | 40.9639 | 0
9.2237 | 8.6985 | 2.1075 | 2.1612 | 3.5373 | 3.3224 | 7.8059 | 5.6447 | 17.9221 | 20.0833 | 27.8892 | 33.5339 | 9.2237 | 8.6985 | 2.1075 | 2.1612 | 3.5373 | 3.3324 | 7.8059 | 5.6447 | 17.9221 | 20.0833 | 27.8892 | 33.5339 | 0
13.2479 | 9.5704 | 2.2416 | 2.3624 | 4.208 | 3.7248 | 8.812 | 6.4496 | 22.8182 | 25.1806 | 33.9926 | 40.4422 | 13.2479 | 9.5704 | 2.2416 | 2.3624 | 4.208 | 3.7348 | 8.812 | 6.4496 | 22.8182 | 25.1806 | 33.9926 | 40.4422 | 0
14.8387 | 9.9151 | 2.2946 | 2.4419 | 4.4731 | 3.8839 | 9.2097 | 6.7677 | 24.7538 | 27.1957 | 36.4054 | 43.1731 | 14.8387 | 9.9151 | 2.2946 | 2.4419 | 4.4731 | 3.8939 | 9.2097 | 6.7677 | 24.7538 | 27.1957 | 36.4054 | 43.1731 | 0
5.5377 | 7.8998 | 1.9846 | 1.9769 | 2.9229 | 2.9538 | 6.8844 | 4.9075 | 13.4375 | 15.4144 | 22.2988 | 27.2063 | 5.5377 | 7.8998 | 1.9846 | 1.9769 | 2.9229 | 2.9638 | 6.8844 | 4.9075 | 13.4375 | 15.4144 | 22.2988 | 27.2063 | 0
3.6914 | 7.4998 | 1.923 | 1.8846 | 2.6152 | 2.7691 | 6.4229 | 4.5383 | 11.1913 | 13.0758 | 19.4987 | 24.037 | 3.6914 | 7.4998 | 1.923 | 1.8846 | 2.6152 | 2.7791 | 6.4229 | 4.5383 | 11.1913 | 13.0758 | 19.4987 | 24.037 | 0
15.412 | 10.0393 | 2.3137 | 2.4706 | 4.5687 | 3.9412 | 9.353 | 6.8824 | 25.4513 | 27.9219 | 37.2749 | 44.1573 | 15.412 | 10.0393 | 2.3137 | 2.4706 | 4.5687 | 3.9512 | 9.353 | 6.8824 | 25.4513 | 27.9219 | 37.2749 | 44.1573 | 0
-1.8093 | 6.308 | 1.7397 | 1.6095 | 1.6984 | 2.2191 | 5.0477 | 3.4381 | 4.4986 | 6.1082 | 11.1558 | 14.594 | -1.8093 | 6.308 | 1.7397 | 1.6095 | 1.6984 | 2.2291 | 5.0477 | 3.4381 | 4.4986 | 6.1082 | 11.1558 | 14.594 | 0
5.3552 | 7.8603 | 1.9785 | 1.9678 | 2.8925 | 2.9355 | 6.8388 | 4.871 | 13.2155 | 15.1833 | 22.0221 | 26.8931 | 5.3552 | 7.8603 | 1.9785 | 1.9678 | 2.8925 | 2.9455 | 6.8388 | 4.871 | 13.2155 | 15.1833 | 22.0221 | 26.8931 | 0
3.6258 | 7.4856 | 1.9209 | 1.8813 | 2.6043 | 2.7626 | 6.4065 | 4.5252 | 11.1114 | 12.9927 | 19.3991 | 23.9243 | 3.6258 | 7.4856 | 1.9209 | 1.8813 | 2.6043 | 2.7726 | 6.4065 | 4.5252 | 11.1114 | 12.9927 | 19.3991 | 23.9243 | 0
17.2865 | 10.4454 | 2.3762 | 2.5643 | 4.8811 | 4.1286 | 9.8216 | 7.2573 | 27.7319 | 30.2962 | 40.1178 | 47.3751 | 17.2865 | 10.4454 | 2.3762 | 2.5643 | 4.8811 | 4.1386 | 9.8216 | 7.2573 | 27.7319 | 30.2962 | 40.1178 | 47.3751 | 0
-1.2041 | 6.4391 | 1.7599 | 1.6398 | 1.7993 | 2.2796 | 5.199 | 3.5592 | 5.2351 | 6.8749 | 12.0738 | 15.633 | -1.2041 | 6.4391 | 1.7599 | 1.6398 | 1.7993 | 2.2896 | 5.199 | 3.5592 | 5.2351 | 6.8749 | 12.0738 | 15.633 | 0
10.4295 | 8.9597 | 2.1476 | 2.2215 | 3.7382 | 3.4429 | 8.1074 | 5.8859 | 19.3892 | 21.6107 | 29.7181 | 35.604 | 10.4295 | 8.9597 | 2.1476 | 2.2215 | 3.7382 | 3.4529 | 8.1074 | 5.8859 | 19.3892 | 21.6107 | 29.7181 | 35.604 | 0
3.5508 | 7.4693 | 1.9184 | 1.8775 | 2.5918 | 2.7551 | 6.3877 | 4.5102 | 11.0202 | 12.8977 | 19.2854 | 23.7956 | 3.5508 | 7.4693 | 1.9184 | 1.8775 | 2.5918 | 2.7651 | 6.3877 | 4.5102 | 11.0202 | 12.8977 | 19.2854 | 23.7956 | 0
8.8773 | 8.6234 | 2.0959 | 2.1439 | 3.4795 | 3.2877 | 7.7193 | 5.5755 | 17.5007 | 19.6445 | 27.3638 | 32.9393 | 8.8773 | 8.6234 | 2.0959 | 2.1439 | 3.4795 | 3.2977 | 7.7193 | 5.5755 | 17.5007 | 19.6445 | 27.3638 | 32.9393 | 0
10.0205 | 8.8711 | 2.134 | 2.201 | 3.6701 | 3.402 | 8.0051 | 5.8041 | 18.8916 | 21.0926 | 29.0977 | 34.9018 | 10.0205 | 8.8711 | 2.134 | 2.201 | 3.6701 | 3.412 | 8.0051 | 5.8041 | 18.8916 | 21.0926 | 29.0977 | 34.9018 | 0
8.7605 | 8.5981 | 2.092 | 2.138 | 3.4601 | 3.276 | 7.6901 | 5.5521 | 17.3586 | 19.4966 | 27.1867 | 32.7388 | 8.7605 | 8.5981 | 2.092 | 2.138 | 3.4601 | 3.286 | 7.6901 | 5.5521 | 17.3586 | 19.4966 | 27.1867 | 32.7388 | 0
13.6101 | 9.6489 | 2.2537 | 2.3805 | 4.2684 | 3.761 | 8.9025 | 6.522 | 23.259 | 25.6395 | 34.542 | 41.064 | 13.6101 | 9.6489 | 2.2537 | 2.3805 | 4.2684 | 3.771 | 8.9025 | 6.522 | 23.259 | 25.6395 | 34.542 | 41.064 | 0
-4.2589 | 5.7772 | 1.658 | 1.4871 | 1.2902 | 1.9741 | 4.4353 | 2.9482 | 1.5183 | 3.0053 | 7.4406 | 10.3888 | -4.2589 | 5.7772 | 1.658 | 1.4871 | 1.2902 | 1.9841 | 4.4353 | 2.9482 | 1.5183 | 3.0053 | 7.4406 | 10.3888 | 0
7.7808 | 8.3858 | 2.0594 | 2.089 | 3.2968 | 3.1781 | 7.4452 | 5.3562 | 16.1666 | 18.2557 | 25.7008 | 31.057 | 7.7808 | 8.3858 | 2.0594 | 2.089 | 3.2968 | 3.1881 | 7.4452 | 5.3562 | 16.1666 | 18.2557 | 25.7008 | 31.057 | 0
9.0241 | 8.6552 | 2.1008 | 2.1512 | 3.504 | 3.3024 | 7.756 | 5.6048 | 17.6794 | 19.8306 | 27.5866 | 33.1914 | 9.0241 | 8.6552 | 2.1008 | 2.1512 | 3.504 | 3.3124 | 7.756 | 5.6048 | 17.6794 | 19.8306 | 27.5866 | 33.1914 | 0
0.87462 | 6.8895 | 1.8292 | 1.7437 | 2.1458 | 2.4875 | 5.7187 | 3.9749 | 7.7641 | 9.5079 | 15.2265 | 19.2014 | 0.87462 | 6.8895 | 1.8292 | 1.7437 | 2.1458 | 2.4975 | 5.7187 | 3.9749 | 7.7641 | 9.5079 | 15.2265 | 19.2014 | 0
4.3537 | 7.6433 | 1.9451 | 1.9177 | 2.7256 | 2.8354 | 6.5884 | 4.6707 | 11.997 | 13.9147 | 20.5031 | 25.1739 | 4.3537 | 7.6433 | 1.9451 | 1.9177 | 2.7256 | 2.8454 | 6.5884 | 4.6707 | 11.997 | 13.9147 | 20.5031 | 25.1739 | 0
7.5191 | 8.3291 | 2.0506 | 2.076 | 3.2532 | 3.1519 | 7.3798 | 5.3038 | 15.8482 | 17.9242 | 25.3039 | 30.6078 | 7.5191 | 8.3291 | 2.0506 | 2.076 | 3.2532 | 3.1619 | 7.3798 | 5.3038 | 15.8482 | 17.9242 | 25.3039 | 30.6078 | 0
-1.0782 | 6.4664 | 1.7641 | 1.6461 | 1.8203 | 2.2922 | 5.2304 | 3.5844 | 5.3882 | 7.0343 | 12.2647 | 15.8491 | -1.0782 | 6.4664 | 1.7641 | 1.6461 | 1.8203 | 2.3022 | 5.2304 | 3.5844 | 5.3882 | 7.0343 | 12.2647 | 15.8491 | 0
-5.1061 | 5.5937 | 1.6298 | 1.4447 | 1.149 | 1.8894 | 4.2235 | 2.7788 | 0.48754 | 1.9322 | 6.1557 | 8.9345 | -5.1061 | 5.5937 | 1.6298 | 1.4447 | 1.149 | 1.8994 | 4.2235 | 2.7788 | 0.48754 | 1.9322 | 6.1557 | 8.9345 | 0
1.3629 | 6.9953 | 1.8454 | 1.7681 | 2.2271 | 2.5363 | 5.8407 | 4.0726 | 8.3582 | 10.1263 | 15.967 | 20.0396 | 1.3629 | 6.9953 | 1.8454 | 1.7681 | 2.2271 | 2.5463 | 5.8407 | 4.0726 | 8.3582 | 10.1263 | 15.967 | 20.0396 | 0
1.8639 | 7.1038 | 1.8621 | 1.7932 | 2.3106 | 2.5864 | 5.966 | 4.1728 | 8.9677 | 10.7609 | 16.7269 | 20.8996 | 1.8639 | 7.1038 | 1.8621 | 1.7932 | 2.3106 | 2.5964 | 5.966 | 4.1728 | 8.9677 | 10.7609 | 16.7269 | 20.8996 | 0
9.9802 | 8.8624 | 2.1327 | 2.199 | 3.6634 | 3.398 | 7.995 | 5.796 | 18.8426 | 21.0416 | 29.0366 | 34.8327 | 9.9802 | 8.8624 | 2.1327 | 2.199 | 3.6634 | 3.408 | 7.995 | 5.796 | 18.8426 | 21.0416 | 29.0366 | 34.8327 | 0
7.6476 | 8.357 | 2.0549 | 2.0824 | 3.2746 | 3.1648 | 7.4119 | 5.3295 | 16.0046 | 18.087 | 25.4989 | 30.8284 | 7.6476 | 8.357 | 2.0549 | 2.0824 | 3.2746 | 3.1748 | 7.4119 | 5.3295 | 16.0046 | 18.087 | 25.4989 | 30.8284 | 0
11.5709 | 9.207 | 2.1857 | 2.2785 | 3.9285 | 3.5571 | 8.3927 | 6.1142 | 20.778 | 23.0565 | 31.4492 | 37.5634 | 11.5709 | 9.207 | 2.1857 | 2.2785 | 3.9285 | 3.5671 | 8.3927 | 6.1142 | 20.778 | 23.0565 | 31.4492 | 37.5634 | 0
2.211 | 7.179 | 1.8737 | 1.8105 | 2.3685 | 2.6211 | 6.0527 | 4.2422 | 9.39 | 11.2006 | 17.2533 | 21.4955 | 2.211 | 7.179 | 1.8737 | 1.8105 | 2.3685 | 2.6311 | 6.0527 | 4.2422 | 9.39 | 11.2006 | 17.2533 | 21.4955 | 0
8.1676 | 8.4696 | 2.0723 | 2.1084 | 3.3613 | 3.2168 | 7.5419 | 5.4335 | 16.6372 | 18.7456 | 26.2875 | 31.721 | 8.1676 | 8.4696 | 2.0723 | 2.1084 | 3.3613 | 3.2268 | 7.5419 | 5.4335 | 16.6372 | 18.7456 | 26.2875 | 31.721 | 0
-1.5632 | 6.3613 | 1.7479 | 1.6218 | 1.7395 | 2.2437 | 5.1092 | 3.4874 | 4.7981 | 6.42 | 11.5292 | 15.0165 | -1.5632 | 6.3613 | 1.7479 | 1.6218 | 1.7395 | 2.2537 | 5.1092 | 3.4874 | 4.7981 | 6.42 | 11.5292 | 15.0165 | 0
6.51 | 8.1105 | 2.017 | 2.0255 | 3.085 | 3.051 | 7.1275 | 5.102 | 14.6205 | 16.646 | 23.7735 | 28.8754 | 6.51 | 8.1105 | 2.017 | 2.0255 | 3.085 | 3.061 | 7.1275 | 5.102 | 14.6205 | 16.646 | 23.7735 | 28.8754 | 0
9.2137 | 8.6963 | 2.1071 | 2.1607 | 3.5356 | 3.3214 | 7.8034 | 5.6427 | 17.91 | 20.0707 | 27.8741 | 33.5169 | 9.2137 | 8.6963 | 2.1071 | 2.1607 | 3.5356 | 3.3314 | 7.8034 | 5.6427 | 17.91 | 20.0707 | 27.8741 | 33.5169 | 0
2.0475 | 7.1436 | 1.8683 | 1.8024 | 2.3413 | 2.6048 | 6.0119 | 4.2095 | 9.1911 | 10.9935 | 17.0054 | 21.2149 | 2.0475 | 7.1436 | 1.8683 | 1.8024 | 2.3413 | 2.6148 | 6.0119 | 4.2095 | 9.1911 | 10.9935 | 17.0054 | 21.2149 | 0
2.251 | 7.1877 | 1.875 | 1.8125 | 2.3752 | 2.6251 | 6.0627 | 4.2502 | 9.4387 | 11.2513 | 17.314 | 21.5642 | 2.251 | 7.1877 | 1.875 | 1.8125 | 2.3752 | 2.6351 | 6.0627 | 4.2502 | 9.4387 | 11.2513 | 17.314 | 21.5642 | 0
3.4527 | 7.4481 | 1.9151 | 1.8726 | 2.5755 | 2.7453 | 6.3632 | 4.4905 | 10.9008 | 12.7734 | 19.1366 | 23.6272 | 3.4527 | 7.4481 | 1.9151 | 1.8726 | 2.5755 | 2.7553 | 6.3632 | 4.4905 | 10.9008 | 12.7734 | 19.1366 | 23.6272 | 0
-0.171 | 6.663 | 1.7943 | 1.6915 | 1.9715 | 2.3829 | 5.4573 | 3.7658 | 6.492 | 8.1834 | 13.6407 | 17.4065 | -0.171 | 6.663 | 1.7943 | 1.6915 | 1.9715 | 2.3929 | 5.4573 | 3.7658 | 6.492 | 8.1834 | 13.6407 | 17.4065 | 0
2.2975 | 7.1978 | 1.8766 | 1.8149 | 2.3829 | 2.6297 | 6.0744 | 4.2595 | 9.4953 | 11.3101 | 17.3845 | 21.644 | 2.2975 | 7.1978 | 1.8766 | 1.8149 | 2.3829 | 2.6397 | 6.0744 | 4.2595 | 9.4953 | 11.3101 | 17.3845 | 21.644 | 0
0.11826 | 6.7256 | 1.8039 | 1.7059 | 2.0197 | 2.4118 | 5.5296 | 3.8237 | 6.8439 | 8.5498 | 14.0794 | 17.903 | 0.11826 | 6.7256 | 1.8039 | 1.7059 | 2.0197 | 2.4218 | 5.5296 | 3.8237 | 6.8439 | 8.5498 | 14.0794 | 17.903 | 0
5.5591 | 7.9045 | 1.9853 | 1.978 | 2.9265 | 2.9559 | 6.8898 | 4.9118 | 13.4636 | 15.4416 | 22.3313 | 27.2432 | 5.5591 | 7.9045 | 1.9853 | 1.978 | 2.9265 | 2.9659 | 6.8898 | 4.9118 | 13.4636 | 15.4416 | 22.3313 | 27.2432 | 0
2.3412 | 7.2073 | 1.878 | 1.8171 | 2.3902 | 2.6341 | 6.0853 | 4.2682 | 9.5484 | 11.3655 | 17.4508 | 21.719 | 2.3412 | 7.2073 | 1.878 | 1.8171 | 2.3902 | 2.6441 | 6.0853 | 4.2682 | 9.5484 | 11.3655 | 17.4508 | 21.719 | 0
8.1691 | 8.47 | 2.0723 | 2.1085 | 3.3615 | 3.2169 | 7.5423 | 5.4338 | 16.639 | 18.7475 | 26.2897 | 31.7235 | 8.1691 | 8.47 | 2.0723 | 2.1085 | 3.3615 | 3.2269 | 7.5423 | 5.4338 | 16.639 | 18.7475 | 26.2897 | 31.7235 | 0
8.3035 | 8.4991 | 2.0768 | 2.1152 | 3.3839 | 3.2303 | 7.5759 | 5.4607 | 16.8026 | 18.9177 | 26.4936 | 31.9543 | 8.3035 | 8.4991 | 2.0768 | 2.1152 | 3.3839 | 3.2403 | 7.5759 | 5.4607 | 16.8026 | 18.9177 | 26.4936 | 31.9543 | 0
10.4961 | 8.9742 | 2.1499 | 2.2248 | 3.7493 | 3.4496 | 8.124 | 5.8992 | 19.4702 | 21.695 | 29.8191 | 35.7183 | 10.4961 | 8.9742 | 2.1499 | 2.2248 | 3.7493 | 3.4596 | 8.124 | 5.8992 | 19.4702 | 21.695 | 29.8191 | 35.7183 | 0
10.5815 | 8.9927 | 2.1527 | 2.2291 | 3.7636 | 3.4582 | 8.1454 | 5.9163 | 19.5742 | 21.8033 | 29.9486 | 35.8649 | 10.5815 | 8.9927 | 2.1527 | 2.2291 | 3.7636 | 3.4682 | 8.1454 | 5.9163 | 19.5742 | 21.8033 | 29.9486 | 35.8649 | 0
5.8599 | 7.9696 | 1.9953 | 1.993 | 2.9766 | 2.986 | 6.965 | 4.972 | 13.8295 | 15.8225 | 22.7875 | 27.7595 | 5.8599 | 7.9696 | 1.9953 | 1.993 | 2.9766 | 2.996 | 6.965 | 4.972 | 13.8295 | 15.8225 | 22.7875 | 27.7595 | 0
14.7012 | 9.8853 | 2.29 | 2.4351 | 4.4502 | 3.8701 | 9.1753 | 6.7402 | 24.5864 | 27.0215 | 36.1968 | 42.937 | 14.7012 | 9.8853 | 2.29 | 2.4351 | 4.4502 | 3.8801 | 9.1753 | 6.7402 | 24.5864 | 27.0215 | 36.1968 | 42.937 | 0
8.3236 | 8.5034 | 2.0775 | 2.1162 | 3.3873 | 3.2324 | 7.5809 | 5.4647 | 16.827 | 18.9432 | 26.5241 | 31.9888 | 8.3236 | 8.5034 | 2.0775 | 2.1162 | 3.3873 | 3.2424 | 7.5809 | 5.4647 | 16.827 | 18.9432 | 26.5241 | 31.9888 | 0
8.3401 | 8.507 | 2.078 | 2.117 | 3.39 | 3.234 | 7.585 | 5.468 | 16.8471 | 18.9641 | 26.5492 | 32.0172 | 8.3401 | 8.507 | 2.078 | 2.117 | 3.39 | 3.244 | 7.585 | 5.468 | 16.8471 | 18.9641 | 26.5492 | 32.0172 | 0
10.3472 | 8.9419 | 2.1449 | 2.2174 | 3.7245 | 3.4347 | 8.0868 | 5.8694 | 19.289 | 21.5064 | 29.5932 | 35.4626 | 10.3472 | 8.9419 | 2.1449 | 2.2174 | 3.7245 | 3.4447 | 8.0868 | 5.8694 | 19.289 | 21.5064 | 29.5932 | 35.4626 | 0
14.4633 | 9.8337 | 2.2821 | 2.4232 | 4.4105 | 3.8463 | 9.1158 | 6.6927 | 24.297 | 26.7201 | 35.836 | 42.5286 | 14.4633 | 9.8337 | 2.2821 | 2.4232 | 4.4105 | 3.8563 | 9.1158 | 6.6927 | 24.297 | 26.7201 | 35.836 | 42.5286 | 0
-3.5127 | 5.9389 | 1.6829 | 1.5244 | 1.4146 | 2.0487 | 4.6218 | 3.0975 | 2.4263 | 3.9506 | 8.5725 | 11.6699 | -3.5127 | 5.9389 | 1.6829 | 1.5244 | 1.4146 | 2.0587 | 4.6218 | 3.0975 | 2.4263 | 3.9506 | 8.5725 | 11.6699 | 0
5.4776 | 7.8868 | 1.9826 | 1.9739 | 2.9129 | 2.9478 | 6.8694 | 4.8955 | 13.3644 | 15.3383 | 22.2077 | 27.1032 | 5.4776 | 7.8868 | 1.9826 | 1.9739 | 2.9129 | 2.9578 | 6.8694 | 4.8955 | 13.3644 | 15.3383 | 22.2077 | 27.1032 | 0
5.2807 | 7.8442 | 1.976 | 1.964 | 2.8801 | 2.9281 | 6.8202 | 4.8561 | 13.1249 | 15.0889 | 21.9091 | 26.7653 | 5.2807 | 7.8442 | 1.976 | 1.964 | 2.8801 | 2.9381 | 6.8202 | 4.8561 | 13.1249 | 15.0889 | 21.9091 | 26.7653 | 0
7.9784 | 8.4286 | 2.0659 | 2.0989 | 3.3297 | 3.1978 | 7.4946 | 5.3957 | 16.407 | 18.5059 | 26.0005 | 31.3962 | 7.9784 | 8.4286 | 2.0659 | 2.0989 | 3.3297 | 3.2078 | 7.4946 | 5.3957 | 16.407 | 18.5059 | 26.0005 | 31.3962 | 0
13.8033 | 9.6907 | 2.2601 | 2.3902 | 4.3006 | 3.7803 | 8.9508 | 6.5607 | 23.494 | 25.8842 | 34.835 | 41.3957 | 13.8033 | 9.6907 | 2.2601 | 2.3902 | 4.3006 | 3.7903 | 8.9508 | 6.5607 | 23.494 | 25.8842 | 34.835 | 41.3957 | 0
8.5439 | 8.5512 | 2.0848 | 2.1272 | 3.424 | 3.2544 | 7.636 | 5.5088 | 17.0951 | 19.2223 | 26.8583 | 32.367 | 8.5439 | 8.5512 | 2.0848 | 2.1272 | 3.424 | 3.2644 | 7.636 | 5.5088 | 17.0951 | 19.2223 | 26.8583 | 32.367 | 0
4.4437 | 7.6628 | 1.9481 | 1.9222 | 2.7406 | 2.8444 | 6.6109 | 4.6887 | 12.1065 | 14.0287 | 20.6396 | 25.3283 | 4.4437 | 7.6628 | 1.9481 | 1.9222 | 2.7406 | 2.8544 | 6.6109 | 4.6887 | 12.1065 | 14.0287 | 20.6396 | 25.3283 | 0
7.7456 | 8.3782 | 2.0582 | 2.0873 | 3.2909 | 3.1746 | 7.4364 | 5.3491 | 16.1238 | 18.2111 | 25.6475 | 30.9967 | 7.7456 | 8.3782 | 2.0582 | 2.0873 | 3.2909 | 3.1846 | 7.4364 | 5.3491 | 16.1238 | 18.2111 | 25.6475 | 30.9967 | 0
-2.7103 | 6.1128 | 1.7097 | 1.5645 | 1.5483 | 2.129 | 4.8224 | 3.2579 | 3.4024 | 4.9669 | 9.7893 | 13.0473 | -2.7103 | 6.1128 | 1.7097 | 1.5645 | 1.5483 | 2.139 | 4.8224 | 3.2579 | 3.4024 | 4.9669 | 9.7893 | 13.0473 | 0
10.561 | 8.9882 | 2.152 | 2.2281 | 3.7602 | 3.4561 | 8.1403 | 5.9122 | 19.5493 | 21.7773 | 29.9176 | 35.8298 | 10.561 | 8.9882 | 2.152 | 2.2281 | 3.7602 | 3.4661 | 8.1403 | 5.9122 | 19.5493 | 21.7773 | 29.9176 | 35.8298 | 0
4.0867 | 7.5855 | 1.9362 | 1.9043 | 2.6811 | 2.8087 | 6.5217 | 4.6173 | 11.6721 | 13.5765 | 20.0982 | 24.7155 | 4.0867 | 7.5855 | 1.9362 | 1.9043 | 2.6811 | 2.8187 | 6.5217 | 4.6173 | 11.6721 | 13.5765 | 20.0982 | 24.7155 | 0
-2.8232 | 6.0883 | 1.7059 | 1.5588 | 1.5295 | 2.1177 | 4.7942 | 3.2354 | 3.2652 | 4.824 | 9.6182 | 12.8536 | -2.8232 | 6.0883 | 1.7059 | 1.5588 | 1.5295 | 2.1277 | 4.7942 | 3.2354 | 3.2652 | 4.824 | 9.6182 | 12.8536 | 0
4.6997 | 7.7183 | 1.9567 | 1.935 | 2.7833 | 2.87 | 6.6749 | 4.7399 | 12.418 | 14.353 | 21.0279 | 25.7678 | 4.6997 | 7.7183 | 1.9567 | 1.935 | 2.7833 | 2.88 | 6.6749 | 4.7399 | 12.418 | 14.353 | 21.0279 | 25.7678 | 0
9.2885 | 8.7125 | 2.1096 | 2.1644 | 3.5481 | 3.3288 | 7.8221 | 5.6577 | 18.0009 | 20.1654 | 27.9875 | 33.6452 | 9.2885 | 8.7125 | 2.1096 | 2.1644 | 3.5481 | 3.3388 | 7.8221 | 5.6577 | 18.0009 | 20.1654 | 27.9875 | 33.6452 | 0
4.1946 | 7.6088 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5486 | 4.6389 | 11.8034 | 13.7131 | 20.2618 | 24.9007 | 4.1946 | 7.6088 | 1.9398 | 1.9097 | 2.6991 | 2.8295 | 6.5486 | 4.6389 | 11.8034 | 13.7131 | 20.2618 | 24.9007 | 0
17.7331 | 10.5422 | 2.3911 | 2.5867 | 4.9555 | 4.1733 | 9.9333 | 7.3466 | 28.2753 | 30.862 | 40.7953 | 48.1419 | 17.7331 | 10.5422 | 2.3911 | 2.5867 | 4.9555 | 4.1833 | 9.9333 | 7.3466 | 28.2753 | 30.862 | 40.7953 | 48.1419 | 0
5.1638 | 7.8188 | 1.9721 | 1.9582 | 2.8606 | 2.9164 | 6.791 | 4.8328 | 12.9827 | 14.9409 | 21.7318 | 26.5646 | 5.1638 | 7.8188 | 1.9721 | 1.9582 | 2.8606 | 2.9264 | 6.791 | 4.8328 | 12.9827 | 14.9409 | 21.7318 | 26.5646 | 0
-1.7584 | 6.319 | 1.7414 | 1.6121 | 1.7069 | 2.2242 | 5.0604 | 3.4483 | 4.5607 | 6.1727 | 11.2331 | 14.6815 | -1.7584 | 6.319 | 1.7414 | 1.6121 | 1.7069 | 2.2342 | 5.0604 | 3.4483 | 4.5607 | 6.1727 | 11.2331 | 14.6815 | 0
-8.3468 | 4.8915 | 1.5218 | 1.2827 | 0.60887 | 1.5653 | 3.4133 | 2.1306 | -3.4553 | -2.1726 | 1.2407 | 3.3713 | -8.3468 | 4.8915 | 1.5218 | 1.2827 | 0.60887 | 1.5753 | 3.4133 | 2.1306 | -3.4553 | -2.1726 | 1.2407 | 3.3713 | 0
-0.18201 | 6.6606 | 1.7939 | 1.6909 | 1.9697 | 2.3818 | 5.4545 | 3.7636 | 6.4786 | 8.1695 | 13.624 | 17.3876 | -0.18201 | 6.6606 | 1.7939 | 1.6909 | 1.9697 | 2.3918 | 5.4545 | 3.7636 | 6.4786 | 8.1695 | 13.624 | 17.3876 | 0
-6.2667 | 5.3422 | 1.5911 | 1.3867 | 0.95556 | 1.7733 | 3.9333 | 2.5467 | -0.92444 | 0.46223 | 4.3956 | 6.9422 | -6.2667 | 5.3422 | 1.5911 | 1.3867 | 0.95556 | 1.7833 | 3.9333 | 2.5467 | -0.92444 | 0.46223 | 4.3956 | 6.9422 | 0
10.6683 | 9.0115 | 2.1556 | 2.2334 | 3.778 | 3.4668 | 8.1671 | 5.9337 | 19.6798 | 21.9132 | 30.0803 | 36.0139 | 10.6683 | 9.0115 | 2.1556 | 2.2334 | 3.778 | 3.4768 | 8.1671 | 5.9337 | 19.6798 | 21.9132 | 30.0803 | 36.0139 | 0
6.5503 | 8.1192 | 2.0183 | 2.0275 | 3.0917 | 3.055 | 7.1376 | 5.1101 | 14.6695 | 16.697 | 23.8346 | 28.9447 | 6.5503 | 8.1192 | 2.0183 | 2.0275 | 3.0917 | 3.065 | 7.1376 | 5.1101 | 14.6695 | 16.697 | 23.8346 | 28.9447 | 0
7.3155 | 8.285 | 2.0438 | 2.0658 | 3.2192 | 3.1315 | 7.3289 | 5.2631 | 15.6005 | 17.6663 | 24.9951 | 30.2582 | 7.3155 | 8.285 | 2.0438 | 2.0658 | 3.2192 | 3.1415 | 7.3289 | 5.2631 | 15.6005 | 17.6663 | 24.9951 | 30.2582 | 0
12.1047 | 9.3227 | 2.2035 | 2.3052 | 4.0174 | 3.6105 | 8.5262 | 6.2209 | 21.4274 | 23.7326 | 32.2588 | 38.4797 | 12.1047 | 9.3227 | 2.2035 | 2.3052 | 4.0174 | 3.6205 | 8.5262 | 6.2209 | 21.4274 | 23.7326 | 32.2588 | 38.4797 | 0
11.6009 | 9.2135 | 2.1867 | 2.28 | 3.9335 | 3.5601 | 8.4002 | 6.1202 | 20.8144 | 23.0944 | 31.4947 | 37.6148 | 11.6009 | 9.2135 | 2.1867 | 2.28 | 3.9335 | 3.5701 | 8.4002 | 6.1202 | 20.8144 | 23.0944 | 31.4947 | 37.6148 | 0
16.131 | 10.195 | 2.3377 | 2.5065 | 4.6885 | 4.0131 | 9.5327 | 7.0262 | 26.326 | 28.8326 | 38.3653 | 45.3915 | 16.131 | 10.195 | 2.3377 | 2.5065 | 4.6885 | 4.0231 | 9.5327 | 7.0262 | 26.326 | 28.8326 | 38.3653 | 45.3915 | 0
7.8716 | 8.4055 | 2.0624 | 2.0936 | 3.3119 | 3.1872 | 7.4679 | 5.3743 | 16.2771 | 18.3706 | 25.8385 | 31.2128 | 7.8716 | 8.4055 | 2.0624 | 2.0936 | 3.3119 | 3.1972 | 7.4679 | 5.3743 | 16.2771 | 18.3706 | 25.8385 | 31.2128 | 0
6.6207 | 8.1345 | 2.0207 | 2.031 | 3.1035 | 3.0621 | 7.1552 | 5.1241 | 14.7552 | 16.7863 | 23.9415 | 29.0656 | 6.6207 | 8.1345 | 2.0207 | 2.031 | 3.1035 | 3.0721 | 7.1552 | 5.1241 | 14.7552 | 16.7863 | 23.9415 | 29.0656 | 0
15.6319 | 10.0869 | 2.3211 | 2.4816 | 4.6053 | 3.9632 | 9.408 | 6.9264 | 25.7188 | 28.2004 | 37.6084 | 44.5348 | 15.6319 | 10.0869 | 2.3211 | 2.4816 | 4.6053 | 3.9732 | 9.408 | 6.9264 | 25.7188 | 28.2004 | 37.6084 | 44.5348 | 0
12.4075 | 9.3883 | 2.2136 | 2.3204 | 4.0679 | 3.6408 | 8.6019 | 6.2815 | 21.7958 | 24.1162 | 32.7181 | 38.9996 | 12.4075 | 9.3883 | 2.2136 | 2.3204 | 4.0679 | 3.6508 | 8.6019 | 6.2815 | 21.7958 | 24.1162 | 32.7181 | 38.9996 | 0
3.1852 | 7.3901 | 1.9062 | 1.8593 | 2.5309 | 2.7185 | 6.2963 | 4.437 | 10.5753 | 12.4346 | 18.7309 | 23.168 | 3.1852 | 7.3901 | 1.9062 | 1.8593 | 2.5309 | 2.7285 | 6.2963 | 4.437 | 10.5753 | 12.4346 | 18.7309 | 23.168 | 0
8.0258 | 8.4389 | 2.0675 | 2.1013 | 3.3376 | 3.2026 | 7.5065 | 5.4052 | 16.4648 | 18.5661 | 26.0725 | 31.4777 | 8.0258 | 8.4389 | 2.0675 | 2.1013 | 3.3376 | 3.2126 | 7.5065 | 5.4052 | 16.4648 | 18.5661 | 26.0725 | 31.4777 | 0
-1.6375 | 6.3452 | 1.7454 | 1.6181 | 1.7271 | 2.2363 | 5.0906 | 3.4725 | 4.7078 | 6.3259 | 11.4165 | 14.889 | -1.6375 | 6.3452 | 1.7454 | 1.6181 | 1.7271 | 2.2463 | 5.0906 | 3.4725 | 4.7078 | 6.3259 | 11.4165 | 14.889 | 0
3.3169 | 7.4187 | 1.9106 | 1.8658 | 2.5528 | 2.7317 | 6.3292 | 4.4634 | 10.7355 | 12.6014 | 18.9306 | 23.394 | 3.3169 | 7.4187 | 1.9106 | 1.8658 | 2.5528 | 2.7417 | 6.3292 | 4.4634 | 10.7355 | 12.6014 | 18.9306 | 23.394 | 0
-1.316 | 6.4149 | 1.7561 | 1.6342 | 1.7807 | 2.2684 | 5.171 | 3.5368 | 5.0988 | 6.733 | 11.904 | 15.4408 | -1.316 | 6.4149 | 1.7561 | 1.6342 | 1.7807 | 2.2784 | 5.171 | 3.5368 | 5.0988 | 6.733 | 11.904 | 15.4408 | 0
7.4915 | 8.3232 | 2.0497 | 2.0746 | 3.2486 | 3.1491 | 7.3729 | 5.2983 | 15.8146 | 17.8892 | 25.2621 | 30.5603 | 7.4915 | 8.3232 | 2.0497 | 2.0746 | 3.2486 | 3.1591 | 7.3729 | 5.2983 | 15.8146 | 17.8892 | 25.2621 | 30.5603 | 0
1.1213 | 6.943 | 1.8374 | 1.7561 | 2.1869 | 2.5121 | 5.7803 | 4.0243 | 8.0643 | 9.8204 | 15.6007 | 19.625 | 1.1213 | 6.943 | 1.8374 | 1.7561 | 2.1869 | 2.5221 | 5.7803 | 4.0243 | 8.0643 | 9.8204 | 15.6007 | 19.625 | 0
-0.19129 | 6.6586 | 1.7936 | 1.6904 | 1.9681 | 2.3809 | 5.4522 | 3.7617 | 6.4673 | 8.1577 | 13.6099 | 17.3716 | -0.19129 | 6.6586 | 1.7936 | 1.6904 | 1.9681 | 2.3909 | 5.4522 | 3.7617 | 6.4673 | 8.1577 | 13.6099 | 17.3716 | 0
14.9327 | 9.9354 | 2.2978 | 2.4466 | 4.4888 | 3.8933 | 9.2332 | 6.7865 | 24.8681 | 27.3147 | 36.5479 | 43.3344 | 14.9327 | 9.9354 | 2.2978 | 2.4466 | 4.4888 | 3.9033 | 9.2332 | 6.7865 | 24.8681 | 27.3147 | 36.5479 | 43.3344 | 0
6.5945 | 8.1288 | 2.0198 | 2.0297 | 3.0991 | 3.0594 | 7.1486 | 5.1189 | 14.7233 | 16.753 | 23.9016 | 29.0205 | 6.5945 | 8.1288 | 2.0198 | 2.0297 | 3.0991 | 3.0694 | 7.1486 | 5.1189 | 14.7233 | 16.753 | 23.9016 | 29.0205 | 0
9.6841 | 8.7982 | 2.1228 | 2.1842 | 3.614 | 3.3684 | 7.921 | 5.7368 | 18.4823 | 20.6665 | 28.5875 | 34.3244 | 9.6841 | 8.7982 | 2.1228 | 2.1842 | 3.614 | 3.3784 | 7.921 | 5.7368 | 18.4823 | 20.6665 | 28.5875 | 34.3244 | 0
10.8748 | 9.0562 | 2.1625 | 2.2437 | 3.8125 | 3.4875 | 8.2187 | 5.975 | 19.931 | 22.1747 | 30.3934 | 36.3684 | 10.8748 | 9.0562 | 2.1625 | 2.2437 | 3.8125 | 3.4975 | 8.2187 | 5.975 | 19.931 | 22.1747 | 30.3934 | 36.3684 | 0
9.5191 | 8.7625 | 2.1173 | 2.176 | 3.5865 | 3.3519 | 7.8798 | 5.7038 | 18.2816 | 20.4576 | 28.3373 | 34.0412 | 9.5191 | 8.7625 | 2.1173 | 2.176 | 3.5865 | 3.3619 | 7.8798 | 5.7038 | 18.2816 | 20.4576 | 28.3373 | 34.0412 | 0
11.791 | 9.2547 | 2.193 | 2.2896 | 3.9652 | 3.5791 | 8.4478 | 6.1582 | 21.0458 | 23.3353 | 31.7831 | 37.9413 | 11.791 | 9.2547 | 2.193 | 2.2896 | 3.9652 | 3.5891 | 8.4478 | 6.1582 | 21.0458 | 23.3353 | 31.7831 | 37.9413 | 0
4.0406 | 7.5755 | 1.9347 | 1.902 | 2.6734 | 2.8041 | 6.5101 | 4.6081 | 11.6161 | 13.5181 | 20.0282 | 24.6364 | 4.0406 | 7.5755 | 1.9347 | 1.902 | 2.6734 | 2.8141 | 6.5101 | 4.6081 | 11.6161 | 13.5181 | 20.0282 | 24.6364 | 0
0.16694 | 6.7362 | 1.8056 | 1.7083 | 2.0278 | 2.4167 | 5.5417 | 3.8334 | 6.9031 | 8.6115 | 14.1532 | 17.9866 | 0.16694 | 6.7362 | 1.8056 | 1.7083 | 2.0278 | 2.4267 | 5.5417 | 3.8334 | 6.9031 | 8.6115 | 14.1532 | 17.9866 | 0
1.7732 | 7.0842 | 1.8591 | 1.7887 | 2.2955 | 2.5773 | 5.9433 | 4.1546 | 8.8574 | 10.6461 | 16.5894 | 20.7441 | 1.7732 | 7.0842 | 1.8591 | 1.7887 | 2.2955 | 2.5873 | 5.9433 | 4.1546 | 8.8574 | 10.6461 | 16.5894 | 20.7441 | 0
2.946 | 7.3383 | 1.8982 | 1.8473 | 2.491 | 2.6946 | 6.2365 | 4.3892 | 10.2843 | 12.1316 | 18.3681 | 22.7573 | 2.946 | 7.3383 | 1.8982 | 1.8473 | 2.491 | 2.7046 | 6.2365 | 4.3892 | 10.2843 | 12.1316 | 18.3681 | 22.7573 | 0
5.1699 | 7.8202 | 1.9723 | 1.9585 | 2.8617 | 2.917 | 6.7925 | 4.834 | 12.9901 | 14.9486 | 21.7411 | 26.5751 | 5.1699 | 7.8202 | 1.9723 | 1.9585 | 2.8617 | 2.927 | 6.7925 | 4.834 | 12.9901 | 14.9486 | 21.7411 | 26.5751 | 0
12.1677 | 9.3363 | 2.2056 | 2.3084 | 4.0279 | 3.6168 | 8.5419 | 6.2335 | 21.504 | 23.8124 | 32.3543 | 38.5878 | 12.1677 | 9.3363 | 2.2056 | 2.3084 | 4.0279 | 3.6268 | 8.5419 | 6.2335 | 21.504 | 23.8124 | 32.3543 | 38.5878 | 0
6.5433 | 8.1177 | 2.0181 | 2.0272 | 3.0906 | 3.0543 | 7.1358 | 5.1087 | 14.661 | 16.6882 | 23.824 | 28.9327 | 6.5433 | 8.1177 | 2.0181 | 2.0272 | 3.0906 | 3.0643 | 7.1358 | 5.1087 | 14.661 | 16.6882 | 23.824 | 28.9327 | 0
11.7076 | 9.2366 | 2.1903 | 2.2854 | 3.9513 | 3.5708 | 8.4269 | 6.1415 | 20.9442 | 23.2296 | 31.6565 | 37.798 | 11.7076 | 9.2366 | 2.1903 | 2.2854 | 3.9513 | 3.5808 | 8.4269 | 6.1415 | 20.9442 | 23.2296 | 31.6565 | 37.798 | 0
5.373 | 7.8641 | 1.9791 | 1.9686 | 2.8955 | 2.9373 | 6.8432 | 4.8746 | 13.2371 | 15.2058 | 22.049 | 26.9236 | 5.373 | 7.8641 | 1.9791 | 1.9686 | 2.8955 | 2.9473 | 6.8432 | 4.8746 | 13.2371 | 15.2058 | 22.049 | 26.9236 | 0
-2.6906 | 6.117 | 1.7103 | 1.5655 | 1.5516 | 2.1309 | 4.8273 | 3.2619 | 3.4264 | 4.9919 | 9.8193 | 13.0811 | -2.6906 | 6.117 | 1.7103 | 1.5655 | 1.5516 | 2.1409 | 4.8273 | 3.2619 | 3.4264 | 4.9919 | 9.8193 | 13.0811 | 0
5.7733 | 7.9509 | 1.9924 | 1.9887 | 2.9622 | 2.9773 | 6.9433 | 4.9547 | 13.7242 | 15.7128 | 22.6561 | 27.6108 | 5.7733 | 7.9509 | 1.9924 | 1.9887 | 2.9622 | 2.9873 | 6.9433 | 4.9547 | 13.7242 | 15.7128 | 22.6561 | 27.6108 | 0
1.0347 | 6.9242 | 1.8345 | 1.7517 | 2.1724 | 2.5035 | 5.7587 | 4.0069 | 7.9588 | 9.7106 | 15.4693 | 19.4762 | 1.0347 | 6.9242 | 1.8345 | 1.7517 | 2.1724 | 2.5135 | 5.7587 | 4.0069 | 7.9588 | 9.7106 | 15.4693 | 19.4762 | 0
17.9452 | 10.5881 | 2.3982 | 2.5973 | 4.9909 | 4.1945 | 9.9863 | 7.389 | 28.5333 | 31.1306 | 41.1169 | 48.5059 | 17.9452 | 10.5881 | 2.3982 | 2.5973 | 4.9909 | 4.2045 | 9.9863 | 7.389 | 28.5333 | 31.1306 | 41.1169 | 48.5059 | 0
2.4162 | 7.2235 | 1.8805 | 1.8208 | 2.4027 | 2.6416 | 6.104 | 4.2832 | 9.6397 | 11.4605 | 17.5645 | 21.8477 | 2.4162 | 7.2235 | 1.8805 | 1.8208 | 2.4027 | 2.6516 | 6.104 | 4.2832 | 9.6397 | 11.4605 | 17.5645 | 21.8477 | 0
5.5634 | 7.9054 | 1.9854 | 1.9782 | 2.9272 | 2.9563 | 6.8909 | 4.9127 | 13.4688 | 15.447 | 22.3378 | 27.2505 | 5.5634 | 7.9054 | 1.9854 | 1.9782 | 2.9272 | 2.9663 | 6.8909 | 4.9127 | 13.4688 | 15.447 | 22.3378 | 27.2505 | 0
-4.3193 | 5.7641 | 1.656 | 1.484 | 1.2801 | 1.9681 | 4.4202 | 2.9361 | 1.4448 | 2.9288 | 7.349 | 10.2851 | -4.3193 | 5.7641 | 1.656 | 1.484 | 1.2801 | 1.9781 | 4.4202 | 2.9361 | 1.4448 | 2.9288 | 7.349 | 10.2851 | 0
-1.7225 | 6.3268 | 1.7426 | 1.6139 | 1.7129 | 2.2278 | 5.0694 | 3.4555 | 4.6043 | 6.2182 | 11.2876 | 14.7431 | -1.7225 | 6.3268 | 1.7426 | 1.6139 | 1.7129 | 2.2378 | 5.0694 | 3.4555 | 4.6043 | 6.2182 | 11.2876 | 14.7431 | 0
5.3795 | 7.8656 | 1.9793 | 1.969 | 2.8966 | 2.9379 | 6.8449 | 4.8759 | 13.245 | 15.214 | 22.0589 | 26.9348 | 5.3795 | 7.8656 | 1.9793 | 1.969 | 2.8966 | 2.9479 | 6.8449 | 4.8759 | 13.245 | 15.214 | 22.0589 | 26.9348 | 0
2.8529 | 7.3181 | 1.8951 | 1.8426 | 2.4755 | 2.6853 | 6.2132 | 4.3706 | 10.171 | 12.0137 | 18.2269 | 22.5975 | 2.8529 | 7.3181 | 1.8951 | 1.8426 | 2.4755 | 2.6953 | 6.2132 | 4.3706 | 10.171 | 12.0137 | 18.2269 | 22.5975 | 0
4.9315 | 7.7685 | 1.9644 | 1.9466 | 2.8219 | 2.8931 | 6.7329 | 4.7863 | 12.6999 | 14.6465 | 21.3794 | 26.1657 | 4.9315 | 7.7685 | 1.9644 | 1.9466 | 2.8219 | 2.9031 | 6.7329 | 4.7863 | 12.6999 | 14.6465 | 21.3794 | 26.1657 | 0
8.9348 | 8.6359 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7337 | 5.587 | 17.5707 | 19.7175 | 27.4512 | 33.0382 | 8.9348 | 8.6359 | 2.0978 | 2.1467 | 3.4891 | 3.3035 | 7.7337 | 5.587 | 17.5707 | 19.7175 | 27.4512 | 33.0382 | 0
18.576 | 10.7248 | 2.4192 | 2.6288 | 5.096 | 4.2576 | 10.144 | 7.5152 | 29.3008 | 31.9296 | 42.0736 | 49.5888 | 18.576 | 10.7248 | 2.4192 | 2.6288 | 5.096 | 4.2676 | 10.144 | 7.5152 | 29.3008 | 31.9296 | 42.0736 | 49.5888 | 0
10.8329 | 9.0471 | 2.1611 | 2.2416 | 3.8055 | 3.4833 | 8.2082 | 5.9666 | 19.88 | 22.1217 | 30.3299 | 36.2965 | 10.8329 | 9.0471 | 2.1611 | 2.2416 | 3.8055 | 3.4933 | 8.2082 | 5.9666 | 19.88 | 22.1217 | 30.3299 | 36.2965 | 0
20.2137 | 11.0796 | 2.4738 | 2.7107 | 5.3689 | 4.4214 | 10.5534 | 7.8427 | 31.2933 | 34.004 | 44.5574 | 52.4001 | 20.2137 | 11.0796 | 2.4738 | 2.7107 | 5.3689 | 4.4314 | 10.5534 | 7.8427 | 31.2933 | 34.004 | 44.5574 | 52.4001 | 0
-2.0597 | 6.2537 | 1.7313 | 1.597 | 1.6567 | 2.194 | 4.9851 | 3.3881 | 4.1941 | 5.7911 | 10.7762 | 14.1642 | -2.0597 | 6.2537 | 1.7313 | 1.597 | 1.6567 | 2.204 | 4.9851 | 3.3881 | 4.1941 | 5.7911 | 10.7762 | 14.1642 | 0
10.1219 | 8.8931 | 2.1374 | 2.2061 | 3.687 | 3.4122 | 8.0305 | 5.8244 | 19.015 | 21.2211 | 29.2516 | 35.0759 | 10.1219 | 8.8931 | 2.1374 | 2.2061 | 3.687 | 3.4222 | 8.0305 | 5.8244 | 19.015 | 21.2211 | 29.2516 | 35.0759 | 0
9.1303 | 8.6782 | 2.1043 | 2.1565 | 3.5217 | 3.313 | 7.7826 | 5.6261 | 17.8085 | 19.965 | 27.7476 | 33.3737 | 9.1303 | 8.6782 | 2.1043 | 2.1565 | 3.5217 | 3.323 | 7.7826 | 5.6261 | 17.8085 | 19.965 | 27.7476 | 33.3737 | 0
1.075 | 6.9329 | 1.8358 | 1.7537 | 2.1792 | 2.5075 | 5.7687 | 4.015 | 8.0079 | 9.7616 | 15.5304 | 19.5454 | 1.075 | 6.9329 | 1.8358 | 1.7537 | 2.1792 | 2.5175 | 5.7687 | 4.015 | 8.0079 | 9.7616 | 15.5304 | 19.5454 | 0
-4.9896 | 5.6189 | 1.6337 | 1.4505 | 1.1684 | 1.901 | 4.2526 | 2.8021 | 0.62936 | 2.0799 | 6.3325 | 9.1346 | -4.9896 | 5.6189 | 1.6337 | 1.4505 | 1.1684 | 1.911 | 4.2526 | 2.8021 | 0.62936 | 2.0799 | 6.3325 | 9.1346 | 0
-0.62885 | 6.5637 | 1.779 | 1.6686 | 1.8952 | 2.3371 | 5.3428 | 3.6742 | 5.9349 | 7.6035 | 12.9462 | 16.6205 | -0.62885 | 6.5637 | 1.779 | 1.6686 | 1.8952 | 2.3471 | 5.3428 | 3.6742 | 5.9349 | 7.6035 | 12.9462 | 16.6205 | 0
7.2339 | 8.2674 | 2.0411 | 2.0617 | 3.2057 | 3.1234 | 7.3085 | 5.2468 | 15.5013 | 17.563 | 24.8715 | 30.1183 | 7.2339 | 8.2674 | 2.0411 | 2.0617 | 3.2057 | 3.1334 | 7.3085 | 5.2468 | 15.5013 | 17.563 | 24.8715 | 30.1183 | 0
10.4833 | 8.9714 | 2.1494 | 2.2242 | 3.7472 | 3.4483 | 8.1208 | 5.8967 | 19.4547 | 21.6788 | 29.7997 | 35.6963 | 10.4833 | 8.9714 | 2.1494 | 2.2242 | 3.7472 | 3.4583 | 8.1208 | 5.8967 | 19.4547 | 21.6788 | 29.7997 | 35.6963 | 0
17.6691 | 10.5283 | 2.389 | 2.5835 | 4.9448 | 4.1669 | 9.9173 | 7.3338 | 28.1974 | 30.7808 | 40.6981 | 48.0319 | 17.6691 | 10.5283 | 2.389 | 2.5835 | 4.9448 | 4.1769 | 9.9173 | 7.3338 | 28.1974 | 30.7808 | 40.6981 | 48.0319 | 0
10.1095 | 8.8904 | 2.137 | 2.2055 | 3.6849 | 3.4109 | 8.0274 | 5.8219 | 18.9999 | 21.2053 | 29.2327 | 35.0546 | 10.1095 | 8.8904 | 2.137 | 2.2055 | 3.6849 | 3.4209 | 8.0274 | 5.8219 | 18.9999 | 21.2053 | 29.2327 | 35.0546 | 0
9.4732 | 8.7525 | 2.1158 | 2.1737 | 3.5789 | 3.3473 | 7.8683 | 5.6946 | 18.2258 | 20.3994 | 28.2677 | 33.9624 | 9.4732 | 8.7525 | 2.1158 | 2.1737 | 3.5789 | 3.3573 | 7.8683 | 5.6946 | 18.2258 | 20.3994 | 28.2677 | 33.9624 | 0
6.8688 | 8.1882 | 2.029 | 2.0434 | 3.1448 | 3.0869 | 7.2172 | 5.1738 | 15.057 | 17.1005 | 24.3177 | 29.4914 | 6.8688 | 8.1882 | 2.029 | 2.0434 | 3.1448 | 3.0969 | 7.2172 | 5.1738 | 15.057 | 17.1005 | 24.3177 | 29.4914 | 0
-7.7712 | 5.0162 | 1.541 | 1.3114 | 0.7048 | 1.6229 | 3.5572 | 2.2458 | -2.755 | -1.4435 | 2.1137 | 4.3594 | -7.7712 | 5.0162 | 1.541 | 1.3114 | 0.7048 | 1.6329 | 3.5572 | 2.2458 | -2.755 | -1.4435 | 2.1137 | 4.3594 | 0
6.6159 | 8.1335 | 2.0205 | 2.0308 | 3.1027 | 3.0616 | 7.154 | 5.1232 | 14.7494 | 16.7802 | 23.9342 | 29.0574 | 6.6159 | 8.1335 | 2.0205 | 2.0308 | 3.1027 | 3.0716 | 7.154 | 5.1232 | 14.7494 | 16.7802 | 23.9342 | 29.0574 | 0
7.7482 | 8.3788 | 2.0583 | 2.0874 | 3.2914 | 3.1748 | 7.437 | 5.3496 | 16.127 | 18.2144 | 25.6514 | 31.0011 | 7.7482 | 8.3788 | 2.0583 | 2.0874 | 3.2914 | 3.1848 | 7.437 | 5.3496 | 16.127 | 18.2144 | 25.6514 | 31.0011 | 0
11.3824 | 9.1662 | 2.1794 | 2.2691 | 3.8971 | 3.5382 | 8.3456 | 6.0765 | 20.5485 | 22.8177 | 31.1632 | 37.2397 | 11.3824 | 9.1662 | 2.1794 | 2.2691 | 3.8971 | 3.5482 | 8.3456 | 6.0765 | 20.5485 | 22.8177 | 31.1632 | 37.2397 | 0
3.369 | 7.4299 | 1.9123 | 1.8684 | 2.5615 | 2.7369 | 6.3422 | 4.4738 | 10.7989 | 12.6674 | 19.0096 | 23.4834 | 3.369 | 7.4299 | 1.9123 | 1.8684 | 2.5615 | 2.7469 | 6.3422 | 4.4738 | 10.7989 | 12.6674 | 19.0096 | 23.4834 | 0
12.951 | 9.506 | 2.2317 | 2.3475 | 4.1585 | 3.6951 | 8.7377 | 6.3902 | 22.457 | 24.8046 | 33.5423 | 39.9325 | 12.951 | 9.506 | 2.2317 | 2.3475 | 4.1585 | 3.7051 | 8.7377 | 6.3902 | 22.457 | 24.8046 | 33.5423 | 39.9325 | 0
0.55287 | 6.8198 | 1.8184 | 1.7276 | 2.0921 | 2.4553 | 5.6382 | 3.9106 | 7.3727 | 9.1003 | 14.7385 | 18.6491 | 0.55287 | 6.8198 | 1.8184 | 1.7276 | 2.0921 | 2.4653 | 5.6382 | 3.9106 | 7.3727 | 9.1003 | 14.7385 | 18.6491 | 0
5.8476 | 7.967 | 1.9949 | 1.9924 | 2.9746 | 2.9848 | 6.9619 | 4.9695 | 13.8146 | 15.807 | 22.7689 | 27.7384 | 5.8476 | 7.967 | 1.9949 | 1.9924 | 2.9746 | 2.9948 | 6.9619 | 4.9695 | 13.8146 | 15.807 | 22.7689 | 27.7384 | 0
1.2162 | 6.9635 | 1.8405 | 1.7608 | 2.2027 | 2.5216 | 5.8041 | 4.0432 | 8.1798 | 9.9406 | 15.7446 | 19.7879 | 1.2162 | 6.9635 | 1.8405 | 1.7608 | 2.2027 | 2.5316 | 5.8041 | 4.0432 | 8.1798 | 9.9406 | 15.7446 | 19.7879 | 0
12.2562 | 9.3555 | 2.2085 | 2.3128 | 4.0427 | 3.6256 | 8.564 | 6.2512 | 21.6117 | 23.9245 | 32.4885 | 38.7398 | 12.2562 | 9.3555 | 2.2085 | 2.3128 | 4.0427 | 3.6356 | 8.564 | 6.2512 | 21.6117 | 23.9245 | 32.4885 | 38.7398 | 0
4.5273 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7055 | 12.2082 | 14.1346 | 20.7664 | 25.4718 | 4.5273 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8627 | 6.6318 | 4.7055 | 12.2082 | 14.1346 | 20.7664 | 25.4718 | 0
-1.3747 | 6.4021 | 1.7542 | 1.6313 | 1.7709 | 2.2625 | 5.1563 | 3.5251 | 5.0275 | 6.6587 | 11.815 | 15.3401 | -1.3747 | 6.4021 | 1.7542 | 1.6313 | 1.7709 | 2.2725 | 5.1563 | 3.5251 | 5.0275 | 6.6587 | 11.815 | 15.3401 | 0
7.568 | 8.3397 | 2.0523 | 2.0784 | 3.2613 | 3.1568 | 7.392 | 5.3136 | 15.9077 | 17.9861 | 25.3781 | 30.6917 | 7.568 | 8.3397 | 2.0523 | 2.0784 | 3.2613 | 3.1668 | 7.392 | 5.3136 | 15.9077 | 17.9861 | 25.3781 | 30.6917 | 0
17.8346 | 10.5642 | 2.3945 | 2.5917 | 4.9724 | 4.1835 | 9.9586 | 7.3669 | 28.3987 | 30.9905 | 40.9491 | 48.316 | 17.8346 | 10.5642 | 2.3945 | 2.5917 | 4.9724 | 4.1935 | 9.9586 | 7.3669 | 28.3987 | 30.9905 | 40.9491 | 48.316 | 0
14.6358 | 9.8711 | 2.2879 | 2.4318 | 4.4393 | 3.8636 | 9.159 | 6.7272 | 24.5069 | 26.9387 | 36.0977 | 42.8248 | 14.6358 | 9.8711 | 2.2879 | 2.4318 | 4.4393 | 3.8736 | 9.159 | 6.7272 | 24.5069 | 26.9387 | 36.0977 | 42.8248 | 0
14.7192 | 9.8892 | 2.2906 | 2.436 | 4.4532 | 3.8719 | 9.1798 | 6.7438 | 24.6084 | 27.0443 | 36.2241 | 42.968 | 14.7192 | 9.8892 | 2.2906 | 2.436 | 4.4532 | 3.8819 | 9.1798 | 6.7438 | 24.6084 | 27.0443 | 36.2241 | 42.968 | 0
8.6596 | 8.5763 | 2.0887 | 2.133 | 3.4433 | 3.266 | 7.6649 | 5.5319 | 17.2359 | 19.3689 | 27.0338 | 32.5657 | 8.6596 | 8.5763 | 2.0887 | 2.133 | 3.4433 | 3.276 | 7.6649 | 5.5319 | 17.2359 | 19.3689 | 27.0338 | 32.5657 | 0
-0.8912 | 6.5069 | 1.7703 | 1.6554 | 1.8515 | 2.3109 | 5.2772 | 3.6218 | 5.6157 | 7.2712 | 12.5484 | 16.1701 | -0.8912 | 6.5069 | 1.7703 | 1.6554 | 1.8515 | 2.3209 | 5.2772 | 3.6218 | 5.6157 | 7.2712 | 12.5484 | 16.1701 | 0
0.11658 | 6.7253 | 1.8039 | 1.7058 | 2.0194 | 2.4117 | 5.5291 | 3.8233 | 6.8418 | 8.5477 | 14.0768 | 17.9001 | 0.11658 | 6.7253 | 1.8039 | 1.7058 | 2.0194 | 2.4217 | 5.5291 | 3.8233 | 6.8418 | 8.5477 | 14.0768 | 17.9001 | 0
2.9789 | 7.3454 | 1.8993 | 1.8489 | 2.4965 | 2.6979 | 6.2447 | 4.3958 | 10.3243 | 12.1733 | 18.418 | 22.8138 | 2.9789 | 7.3454 | 1.8993 | 1.8489 | 2.4965 | 2.7079 | 6.2447 | 4.3958 | 10.3243 | 12.1733 | 18.418 | 22.8138 | 0
10.7182 | 9.0223 | 2.1573 | 2.2359 | 3.7864 | 3.4718 | 8.1796 | 5.9436 | 19.7405 | 21.9764 | 30.156 | 36.0997 | 10.7182 | 9.0223 | 2.1573 | 2.2359 | 3.7864 | 3.4818 | 8.1796 | 5.9436 | 19.7405 | 21.9764 | 30.156 | 36.0997 | 0
8.2018 | 8.4771 | 2.0734 | 2.1101 | 3.367 | 3.2202 | 7.5505 | 5.4404 | 16.6789 | 18.789 | 26.3395 | 31.7798 | 8.2018 | 8.4771 | 2.0734 | 2.1101 | 3.367 | 3.2302 | 7.5505 | 5.4404 | 16.6789 | 18.789 | 26.3395 | 31.7798 | 0
14.9186 | 9.9324 | 2.2973 | 2.4459 | 4.4864 | 3.8919 | 9.2296 | 6.7837 | 24.8509 | 27.2969 | 36.5265 | 43.3102 | 14.9186 | 9.9324 | 2.2973 | 2.4459 | 4.4864 | 3.9019 | 9.2296 | 6.7837 | 24.8509 | 27.2969 | 36.5265 | 43.3102 | 0
3.278 | 7.4102 | 1.9093 | 1.8639 | 2.5463 | 2.7278 | 6.3195 | 4.4556 | 10.6882 | 12.5521 | 18.8716 | 23.3272 | 3.278 | 7.4102 | 1.9093 | 1.8639 | 2.5463 | 2.7378 | 6.3195 | 4.4556 | 10.6882 | 12.5521 | 18.8716 | 23.3272 | 0
11.9059 | 9.2796 | 2.1969 | 2.2953 | 3.9843 | 3.5906 | 8.4765 | 6.1812 | 21.1855 | 23.4808 | 31.9572 | 38.1384 | 11.9059 | 9.2796 | 2.1969 | 2.2953 | 3.9843 | 3.6006 | 8.4765 | 6.1812 | 21.1855 | 23.4808 | 31.9572 | 38.1384 | 0
0.21186 | 6.7459 | 1.8071 | 1.7106 | 2.0353 | 2.4212 | 5.553 | 3.8424 | 6.9578 | 8.6684 | 14.2213 | 18.0637 | 0.21186 | 6.7459 | 1.8071 | 1.7106 | 2.0353 | 2.4312 | 5.553 | 3.8424 | 6.9578 | 8.6684 | 14.2213 | 18.0637 | 0
8.3077 | 8.5 | 2.0769 | 2.1154 | 3.3846 | 3.2308 | 7.5769 | 5.4615 | 16.8077 | 18.9231 | 26.5001 | 31.9616 | 8.3077 | 8.5 | 2.0769 | 2.1154 | 3.3846 | 3.2408 | 7.5769 | 5.4615 | 16.8077 | 18.9231 | 26.5001 | 31.9616 | 0
0.99521 | 6.9156 | 1.8332 | 1.7498 | 2.1659 | 2.4995 | 5.7488 | 3.999 | 7.9108 | 9.6606 | 15.4094 | 19.4084 | 0.99521 | 6.9156 | 1.8332 | 1.7498 | 2.1659 | 2.5095 | 5.7488 | 3.999 | 7.9108 | 9.6606 | 15.4094 | 19.4084 | 0
10.022 | 8.8714 | 2.1341 | 2.2011 | 3.6703 | 3.4022 | 8.0055 | 5.8044 | 18.8934 | 21.0945 | 29.1 | 34.9045 | 10.022 | 8.8714 | 2.1341 | 2.2011 | 3.6703 | 3.4122 | 8.0055 | 5.8044 | 18.8934 | 21.0945 | 29.1 | 34.9045 | 0
-5.1718 | 5.5794 | 1.6276 | 1.4414 | 1.138 | 1.8828 | 4.207 | 2.7656 | 0.4076 | 1.849 | 6.0561 | 8.8217 | -5.1718 | 5.5794 | 1.6276 | 1.4414 | 1.138 | 1.8928 | 4.207 | 2.7656 | 0.4076 | 1.849 | 6.0561 | 8.8217 | 0
-1.0844 | 6.465 | 1.7639 | 1.6458 | 1.8193 | 2.2916 | 5.2289 | 3.5831 | 5.3806 | 7.0264 | 12.2553 | 15.8384 | -1.0844 | 6.465 | 1.7639 | 1.6458 | 1.8193 | 2.3016 | 5.2289 | 3.5831 | 5.3806 | 7.0264 | 12.2553 | 15.8384 | 0
6.9795 | 8.2122 | 2.0326 | 2.049 | 3.1632 | 3.0979 | 7.2449 | 5.1959 | 15.1917 | 17.2407 | 24.4855 | 29.6814 | 6.9795 | 8.2122 | 2.0326 | 2.049 | 3.1632 | 3.1079 | 7.2449 | 5.1959 | 15.1917 | 17.2407 | 24.4855 | 29.6814 | 0
1.3132 | 6.9845 | 1.8438 | 1.7657 | 2.2189 | 2.5313 | 5.8283 | 4.0626 | 8.2978 | 10.0634 | 15.8917 | 19.9544 | 1.3132 | 6.9845 | 1.8438 | 1.7657 | 2.2189 | 2.5413 | 5.8283 | 4.0626 | 8.2978 | 10.0634 | 15.8917 | 19.9544 | 0
1.3639 | 6.9955 | 1.8455 | 1.7682 | 2.2273 | 2.5364 | 5.841 | 4.0728 | 8.3594 | 10.1276 | 15.9686 | 20.0414 | 1.3639 | 6.9955 | 1.8455 | 1.7682 | 2.2273 | 2.5464 | 5.841 | 4.0728 | 8.3594 | 10.1276 | 15.9686 | 20.0414 | 0
-1.4768 | 6.38 | 1.7508 | 1.6262 | 1.7539 | 2.2523 | 5.1308 | 3.5046 | 4.9032 | 6.5293 | 11.6601 | 15.1648 | -1.4768 | 6.38 | 1.7508 | 1.6262 | 1.7539 | 2.2623 | 5.1308 | 3.5046 | 4.9032 | 6.5293 | 11.6601 | 15.1648 | 0
6.5105 | 8.1106 | 2.017 | 2.0255 | 3.0851 | 3.0511 | 7.1276 | 5.1021 | 14.6211 | 16.6466 | 23.7743 | 28.8764 | 6.5105 | 8.1106 | 2.017 | 2.0255 | 3.0851 | 3.0611 | 7.1276 | 5.1021 | 14.6211 | 16.6466 | 23.7743 | 28.8764 | 0
2.9522 | 7.3396 | 1.8984 | 1.8476 | 2.492 | 2.6952 | 6.238 | 4.3904 | 10.2918 | 12.1394 | 18.3775 | 22.7679 | 2.9522 | 7.3396 | 1.8984 | 1.8476 | 2.492 | 2.7052 | 6.238 | 4.3904 | 10.2918 | 12.1394 | 18.3775 | 22.7679 | 0
6.1645 | 8.0356 | 2.0055 | 2.0082 | 3.0274 | 3.0165 | 7.0411 | 5.0329 | 14.2002 | 16.2084 | 23.2495 | 28.2824 | 6.1645 | 8.0356 | 2.0055 | 2.0082 | 3.0274 | 3.0265 | 7.0411 | 5.0329 | 14.2002 | 16.2084 | 23.2495 | 28.2824 | 0
3.115 | 7.3749 | 1.9038 | 1.8557 | 2.5192 | 2.7115 | 6.2787 | 4.423 | 10.4899 | 12.3457 | 18.6244 | 23.0474 | 3.115 | 7.3749 | 1.9038 | 1.8557 | 2.5192 | 2.7215 | 6.2787 | 4.423 | 10.4899 | 12.3457 | 18.6244 | 23.0474 | 0
6.4626 | 8.1002 | 2.0154 | 2.0231 | 3.0771 | 3.0463 | 7.1157 | 5.0925 | 14.5628 | 16.586 | 23.7016 | 28.7941 | 6.4626 | 8.1002 | 2.0154 | 2.0231 | 3.0771 | 3.0563 | 7.1157 | 5.0925 | 14.5628 | 16.586 | 23.7016 | 28.7941 | 0
16.0124 | 10.1694 | 2.3337 | 2.5006 | 4.6687 | 4.0012 | 9.5031 | 7.0025 | 26.1817 | 28.6824 | 38.1855 | 45.1879 | 16.0124 | 10.1694 | 2.3337 | 2.5006 | 4.6687 | 4.0112 | 9.5031 | 7.0025 | 26.1817 | 28.6824 | 38.1855 | 45.1879 | 0
1.5673 | 7.0396 | 1.8522 | 1.7784 | 2.2612 | 2.5567 | 5.8918 | 4.1135 | 8.6068 | 10.3852 | 16.277 | 20.3904 | 1.5673 | 7.0396 | 1.8522 | 1.7784 | 2.2612 | 2.5667 | 5.8918 | 4.1135 | 8.6068 | 10.3852 | 16.277 | 20.3904 | 0
13.5036 | 9.6258 | 2.2501 | 2.3752 | 4.2506 | 3.7504 | 8.8759 | 6.5007 | 23.1293 | 25.5045 | 34.3804 | 40.8811 | 13.5036 | 9.6258 | 2.2501 | 2.3752 | 4.2506 | 3.7604 | 8.8759 | 6.5007 | 23.1293 | 25.5045 | 34.3804 | 40.8811 | 0
0.21402 | 6.7464 | 1.8071 | 1.7107 | 2.0357 | 2.4214 | 5.5535 | 3.8428 | 6.9604 | 8.6711 | 14.2246 | 18.0674 | 0.21402 | 6.7464 | 1.8071 | 1.7107 | 2.0357 | 2.4314 | 5.5535 | 3.8428 | 6.9604 | 8.6711 | 14.2246 | 18.0674 | 0
0.14578 | 6.7316 | 1.8049 | 1.7073 | 2.0243 | 2.4146 | 5.5364 | 3.8292 | 6.8774 | 8.5847 | 14.1211 | 17.9503 | 0.14578 | 6.7316 | 1.8049 | 1.7073 | 2.0243 | 2.4246 | 5.5364 | 3.8292 | 6.8774 | 8.5847 | 14.1211 | 17.9503 | 0
6.3738 | 8.081 | 2.0125 | 2.0187 | 3.0623 | 3.0374 | 7.0935 | 5.0748 | 14.4548 | 16.4735 | 23.5669 | 28.6417 | 6.3738 | 8.081 | 2.0125 | 2.0187 | 3.0623 | 3.0474 | 7.0935 | 5.0748 | 14.4548 | 16.4735 | 23.5669 | 28.6417 | 0
16.4514 | 10.2645 | 2.3484 | 2.5226 | 4.7419 | 4.0451 | 9.6128 | 7.0903 | 26.7158 | 29.2384 | 38.8513 | 45.9415 | 16.4514 | 10.2645 | 2.3484 | 2.5226 | 4.7419 | 4.0551 | 9.6128 | 7.0903 | 26.7158 | 29.2384 | 38.8513 | 45.9415 | 0
13.4295 | 9.6097 | 2.2477 | 2.3715 | 4.2383 | 3.743 | 8.8574 | 6.4859 | 23.0392 | 25.4107 | 34.2681 | 40.754 | 13.4295 | 9.6097 | 2.2477 | 2.3715 | 4.2383 | 3.753 | 8.8574 | 6.4859 | 23.0392 | 25.4107 | 34.2681 | 40.754 | 0
-7.4375 | 5.0886 | 1.5521 | 1.3281 | 0.76042 | 1.6563 | 3.6406 | 2.3125 | -2.3489 | -1.0208 | 2.6199 | 4.9324 | -7.4375 | 5.0886 | 1.5521 | 1.3281 | 0.76042 | 1.6663 | 3.6406 | 2.3125 | -2.3489 | -1.0208 | 2.6199 | 4.9324 | 0
-2.1955 | 6.2243 | 1.7268 | 1.5902 | 1.6341 | 2.1805 | 4.9511 | 3.3609 | 4.0288 | 5.6191 | 10.5702 | 13.9311 | -2.1955 | 6.2243 | 1.7268 | 1.5902 | 1.6341 | 2.1905 | 4.9511 | 3.3609 | 4.0288 | 5.6191 | 10.5702 | 13.9311 | 0
-0.86628 | 6.5123 | 1.7711 | 1.6567 | 1.8556 | 2.3134 | 5.2834 | 3.6267 | 5.646 | 7.3027 | 12.5861 | 16.2129 | -0.86628 | 6.5123 | 1.7711 | 1.6567 | 1.8556 | 2.3234 | 5.2834 | 3.6267 | 5.646 | 7.3027 | 12.5861 | 16.2129 | 0
7.4517 | 8.3145 | 2.0484 | 2.0726 | 3.2419 | 3.1452 | 7.3629 | 5.2903 | 15.7662 | 17.8388 | 25.2017 | 30.492 | 7.4517 | 8.3145 | 2.0484 | 2.0726 | 3.2419 | 3.1552 | 7.3629 | 5.2903 | 15.7662 | 17.8388 | 25.2017 | 30.492 | 0
-4.548 | 5.7146 | 1.6484 | 1.4726 | 1.242 | 1.9452 | 4.363 | 2.8904 | 1.1666 | 2.6392 | 7.0022 | 9.8926 | -4.548 | 5.7146 | 1.6484 | 1.4726 | 1.242 | 1.9552 | 4.363 | 2.8904 | 1.1666 | 2.6392 | 7.0022 | 9.8926 | 0
10.1638 | 8.9022 | 2.1388 | 2.2082 | 3.694 | 3.4164 | 8.0409 | 5.8328 | 19.066 | 21.2741 | 29.3151 | 35.1479 | 10.1638 | 8.9022 | 2.1388 | 2.2082 | 3.694 | 3.4264 | 8.0409 | 5.8328 | 19.066 | 21.2741 | 29.3151 | 35.1479 | 0
7.2783 | 8.277 | 2.0426 | 2.0639 | 3.213 | 3.1278 | 7.3196 | 5.2557 | 15.5552 | 17.6191 | 24.9387 | 30.1943 | 7.2783 | 8.277 | 2.0426 | 2.0639 | 3.213 | 3.1378 | 7.3196 | 5.2557 | 15.5552 | 17.6191 | 24.9387 | 30.1943 | 0
1.4575 | 7.0158 | 1.8486 | 1.7729 | 2.2429 | 2.5457 | 5.8644 | 4.0915 | 8.4732 | 10.2461 | 16.1105 | 20.202 | 1.4575 | 7.0158 | 1.8486 | 1.7729 | 2.2429 | 2.5557 | 5.8644 | 4.0915 | 8.4732 | 10.2461 | 16.1105 | 20.202 | 0
-0.57037 | 6.5764 | 1.781 | 1.6715 | 1.9049 | 2.343 | 5.3574 | 3.6859 | 6.0061 | 7.6775 | 13.0349 | 16.7209 | -0.57037 | 6.5764 | 1.781 | 1.6715 | 1.9049 | 2.353 | 5.3574 | 3.6859 | 6.0061 | 7.6775 | 13.0349 | 16.7209 | 0
2.3931 | 7.2185 | 1.8798 | 1.8197 | 2.3989 | 2.6393 | 6.0983 | 4.2786 | 9.6116 | 11.4313 | 17.5295 | 21.8082 | 2.3931 | 7.2185 | 1.8798 | 1.8197 | 2.3989 | 2.6493 | 6.0983 | 4.2786 | 9.6116 | 11.4313 | 17.5295 | 21.8082 | 0
14.9926 | 9.9484 | 2.2998 | 2.4496 | 4.4988 | 3.8993 | 9.2481 | 6.7985 | 24.941 | 27.3906 | 36.6387 | 43.4372 | 14.9926 | 9.9484 | 2.2998 | 2.4496 | 4.4988 | 3.9093 | 9.2481 | 6.7985 | 24.941 | 27.3906 | 36.6387 | 43.4372 | 0
5.5444 | 7.9013 | 1.9848 | 1.9772 | 2.9241 | 2.9544 | 6.8861 | 4.9089 | 13.4457 | 15.423 | 22.3091 | 27.218 | 5.5444 | 7.9013 | 1.9848 | 1.9772 | 2.9241 | 2.9644 | 6.8861 | 4.9089 | 13.4457 | 15.423 | 22.3091 | 27.218 | 0
13.6245 | 9.652 | 2.2542 | 2.3812 | 4.2708 | 3.7625 | 8.9061 | 6.5249 | 23.2765 | 25.6577 | 34.5638 | 41.0887 | 13.6245 | 9.652 | 2.2542 | 2.3812 | 4.2708 | 3.7725 | 8.9061 | 6.5249 | 23.2765 | 25.6577 | 34.5638 | 41.0887 | 0
1.3803 | 6.9991 | 1.846 | 1.769 | 2.2301 | 2.538 | 5.8451 | 4.0761 | 8.3794 | 10.1484 | 15.9935 | 20.0695 | 1.3803 | 6.9991 | 1.846 | 1.769 | 2.2301 | 2.548 | 5.8451 | 4.0761 | 8.3794 | 10.1484 | 15.9935 | 20.0695 | 0
9.4004 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.8501 | 5.6801 | 18.1371 | 20.3071 | 28.1572 | 33.8373 | 9.4004 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.35 | 7.8501 | 5.6801 | 18.1371 | 20.3071 | 28.1572 | 33.8373 | 0
5.1169 | 7.8087 | 1.9706 | 1.9558 | 2.8528 | 2.9117 | 6.7792 | 4.8234 | 12.9255 | 14.8813 | 21.6606 | 26.4839 | 5.1169 | 7.8087 | 1.9706 | 1.9558 | 2.8528 | 2.9217 | 6.7792 | 4.8234 | 12.9255 | 14.8813 | 21.6606 | 26.4839 | 0
-0.84508 | 6.5169 | 1.7718 | 1.6577 | 1.8592 | 2.3155 | 5.2887 | 3.631 | 5.6718 | 7.3296 | 12.6183 | 16.2493 | -0.84508 | 6.5169 | 1.7718 | 1.6577 | 1.8592 | 2.3255 | 5.2887 | 3.631 | 5.6718 | 7.3296 | 12.6183 | 16.2493 | 0
14.9278 | 9.9344 | 2.2976 | 2.4464 | 4.488 | 3.8928 | 9.232 | 6.7856 | 24.8622 | 27.3086 | 36.5405 | 43.3261 | 14.9278 | 9.9344 | 2.2976 | 2.4464 | 4.488 | 3.9028 | 9.232 | 6.7856 | 24.8622 | 27.3086 | 36.5405 | 43.3261 | 0
9.9078 | 8.8467 | 2.1303 | 2.1954 | 3.6513 | 3.3908 | 7.977 | 5.7816 | 18.7545 | 20.9499 | 28.9268 | 34.7084 | 9.9078 | 8.8467 | 2.1303 | 2.1954 | 3.6513 | 3.4008 | 7.977 | 5.7816 | 18.7545 | 20.9499 | 28.9268 | 34.7084 | 0
5.1469 | 7.8152 | 1.9716 | 1.9573 | 2.8578 | 2.9147 | 6.7867 | 4.8294 | 12.962 | 14.9194 | 21.7061 | 26.5355 | 5.1469 | 7.8152 | 1.9716 | 1.9573 | 2.8578 | 2.9247 | 6.7867 | 4.8294 | 12.962 | 14.9194 | 21.7061 | 26.5355 | 0
3.5807 | 7.4758 | 1.9194 | 1.879 | 2.5968 | 2.7581 | 6.3952 | 4.5161 | 11.0565 | 12.9355 | 19.3307 | 23.8468 | 3.5807 | 7.4758 | 1.9194 | 1.879 | 2.5968 | 2.7681 | 6.3952 | 4.5161 | 11.0565 | 12.9355 | 19.3307 | 23.8468 | 0
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2043 | 14.1305 | 20.7616 | 25.4664 | 4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8624 | 6.631 | 4.7048 | 12.2043 | 14.1305 | 20.7616 | 25.4664 | 0
8.6671 | 8.5779 | 2.0889 | 2.1334 | 3.4445 | 3.2667 | 7.6668 | 5.5334 | 17.2449 | 19.3783 | 27.0451 | 32.5785 | 8.6671 | 8.5779 | 2.0889 | 2.1334 | 3.4445 | 3.2767 | 7.6668 | 5.5334 | 17.2449 | 19.3783 | 27.0451 | 32.5785 | 0
8.4187 | 8.5241 | 2.0806 | 2.1209 | 3.4031 | 3.2419 | 7.6047 | 5.4837 | 16.9428 | 19.0637 | 26.6684 | 32.1522 | 8.4187 | 8.5241 | 2.0806 | 2.1209 | 3.4031 | 3.2519 | 7.6047 | 5.4837 | 16.9428 | 19.0637 | 26.6684 | 32.1522 | 0
-9.9815 | 4.5373 | 1.4673 | 1.2009 | 0.33642 | 1.4019 | 3.0046 | 1.8037 | -5.4442 | -4.2432 | -1.2386 | 0.5651 | -9.9815 | 4.5373 | 1.4673 | 1.2009 | 0.33642 | 1.4119 | 3.0046 | 1.8037 | -5.4442 | -4.2432 | -1.2386 | 0.5651 | 0
17.7361 | 10.5428 | 2.3912 | 2.5868 | 4.956 | 4.1736 | 9.934 | 7.3472 | 28.2789 | 30.8657 | 40.7997 | 48.1469 | 17.7361 | 10.5428 | 2.3912 | 2.5868 | 4.956 | 4.1836 | 9.934 | 7.3472 | 28.2789 | 30.8657 | 40.7997 | 48.1469 | 0
14.6958 | 9.8841 | 2.2899 | 2.4348 | 4.4493 | 3.8696 | 9.174 | 6.7392 | 24.5799 | 27.0147 | 36.1887 | 42.9279 | 14.6958 | 9.8841 | 2.2899 | 2.4348 | 4.4493 | 3.8796 | 9.174 | 6.7392 | 24.5799 | 27.0147 | 36.1887 | 42.9279 | 0
6.9703 | 8.2102 | 2.0323 | 2.0485 | 3.1617 | 3.097 | 7.2426 | 5.1941 | 15.1805 | 17.229 | 24.4716 | 29.6656 | 6.9703 | 8.2102 | 2.0323 | 2.0485 | 3.1617 | 3.107 | 7.2426 | 5.1941 | 15.1805 | 17.229 | 24.4716 | 29.6656 | 0
-2.7649 | 6.1009 | 1.7078 | 1.5618 | 1.5392 | 2.1235 | 4.8088 | 3.247 | 3.336 | 4.8978 | 9.7066 | 12.9536 | -2.7649 | 6.1009 | 1.7078 | 1.5618 | 1.5392 | 2.1335 | 4.8088 | 3.247 | 3.336 | 4.8978 | 9.7066 | 12.9536 | 0
8.3695 | 8.5134 | 2.079 | 2.1185 | 3.3949 | 3.2369 | 7.5924 | 5.4739 | 16.8829 | 19.0014 | 26.5937 | 32.0676 | 8.3695 | 8.5134 | 2.079 | 2.1185 | 3.3949 | 3.2469 | 7.5924 | 5.4739 | 16.8829 | 19.0014 | 26.5937 | 32.0676 | 0
0.31258 | 6.7677 | 1.8104 | 1.7156 | 2.0521 | 2.4313 | 5.5781 | 3.8625 | 7.0803 | 8.7959 | 14.3741 | 18.2366 | 0.31258 | 6.7677 | 1.8104 | 1.7156 | 2.0521 | 2.4413 | 5.5781 | 3.8625 | 7.0803 | 8.7959 | 14.3741 | 18.2366 | 0
14.0166 | 9.7369 | 2.2672 | 2.4008 | 4.3361 | 3.8017 | 9.0041 | 6.6033 | 23.7535 | 26.1543 | 35.1584 | 41.7618 | 14.0166 | 9.7369 | 2.2672 | 2.4008 | 4.3361 | 3.8117 | 9.0041 | 6.6033 | 23.7535 | 26.1543 | 35.1584 | 41.7618 | 0
7.5685 | 8.3398 | 2.0523 | 2.0784 | 3.2614 | 3.1568 | 7.3921 | 5.3137 | 15.9083 | 17.9867 | 25.3788 | 30.6925 | 7.5685 | 8.3398 | 2.0523 | 2.0784 | 3.2614 | 3.1668 | 7.3921 | 5.3137 | 15.9083 | 17.9867 | 25.3788 | 30.6925 | 0
5.9811 | 7.9959 | 1.9994 | 1.9991 | 2.9968 | 2.9981 | 6.9953 | 4.9962 | 13.977 | 15.976 | 22.9713 | 27.9675 | 5.9811 | 7.9959 | 1.9994 | 1.9991 | 2.9968 | 3.0081 | 6.9953 | 4.9962 | 13.977 | 15.976 | 22.9713 | 27.9675 | 0
3.3981 | 7.4363 | 1.9133 | 1.8699 | 2.5664 | 2.7398 | 6.3495 | 4.4796 | 10.8344 | 12.7043 | 19.0538 | 23.5335 | 3.3981 | 7.4363 | 1.9133 | 1.8699 | 2.5664 | 2.7498 | 6.3495 | 4.4796 | 10.8344 | 12.7043 | 19.0538 | 23.5335 | 0
6.2917 | 8.0632 | 2.0097 | 2.0146 | 3.0486 | 3.0292 | 7.0729 | 5.0583 | 14.3549 | 16.3695 | 23.4424 | 28.5007 | 6.2917 | 8.0632 | 2.0097 | 2.0146 | 3.0486 | 3.0392 | 7.0729 | 5.0583 | 14.3549 | 16.3695 | 23.4424 | 28.5007 | 0
3.5617 | 7.4717 | 1.9187 | 1.8781 | 2.5936 | 2.7562 | 6.3904 | 4.5123 | 11.0334 | 12.9115 | 19.3019 | 23.8143 | 3.5617 | 7.4717 | 1.9187 | 1.8781 | 2.5936 | 2.7662 | 6.3904 | 4.5123 | 11.0334 | 12.9115 | 19.3019 | 23.8143 | 0
13.4989 | 9.6248 | 2.25 | 2.3749 | 4.2498 | 3.7499 | 8.8747 | 6.4998 | 23.1236 | 25.4986 | 34.3733 | 40.8731 | 13.4989 | 9.6248 | 2.25 | 2.3749 | 4.2498 | 3.7599 | 8.8747 | 6.4998 | 23.1236 | 25.4986 | 34.3733 | 40.8731 | 0
10.3918 | 8.9516 | 2.1464 | 2.2196 | 3.732 | 3.4392 | 8.098 | 5.8784 | 19.3434 | 21.563 | 29.6609 | 35.5393 | 10.3918 | 8.9516 | 2.1464 | 2.2196 | 3.732 | 3.4492 | 8.098 | 5.8784 | 19.3434 | 21.563 | 29.6609 | 35.5393 | 0
1.0548 | 6.9285 | 1.8352 | 1.7527 | 2.1758 | 2.5055 | 5.7637 | 4.011 | 7.9833 | 9.7361 | 15.4998 | 19.5107 | 1.0548 | 6.9285 | 1.8352 | 1.7527 | 2.1758 | 2.5155 | 5.7637 | 4.011 | 7.9833 | 9.7361 | 15.4998 | 19.5107 | 0
16.2026 | 10.2106 | 2.3401 | 2.5101 | 4.7004 | 4.0203 | 9.5506 | 7.0405 | 26.4131 | 28.9233 | 38.4739 | 45.5144 | 16.2026 | 10.2106 | 2.3401 | 2.5101 | 4.7004 | 4.0303 | 9.5506 | 7.0405 | 26.4131 | 28.9233 | 38.4739 | 45.5144 | 0
8.5304 | 8.5483 | 2.0843 | 2.1265 | 3.4217 | 3.253 | 7.6326 | 5.5061 | 17.0786 | 19.2052 | 26.8378 | 32.3438 | 8.5304 | 8.5483 | 2.0843 | 2.1265 | 3.4217 | 3.263 | 7.6326 | 5.5061 | 17.0786 | 19.2052 | 26.8378 | 32.3438 | 0
7.3385 | 8.29 | 2.0446 | 2.0669 | 3.2231 | 3.1339 | 7.3346 | 5.2677 | 15.6285 | 17.6955 | 25.0301 | 30.2978 | 7.3385 | 8.29 | 2.0446 | 2.0669 | 3.2231 | 3.1439 | 7.3346 | 5.2677 | 15.6285 | 17.6955 | 25.0301 | 30.2978 | 0
-11.3977 | 4.2305 | 1.4201 | 1.1301 | 0.10039 | 1.2602 | 2.6506 | 1.5205 | -7.1672 | -6.0371 | -3.3865 | -1.866 | -11.3977 | 4.2305 | 1.4201 | 1.1301 | 0.10039 | 1.2702 | 2.6506 | 1.5205 | -7.1672 | -6.0371 | -3.3865 | -1.866 | 0
4.3995 | 7.6532 | 1.9466 | 1.92 | 2.7332 | 2.8399 | 6.5999 | 4.6799 | 12.0527 | 13.9727 | 20.5726 | 25.2525 | 4.3995 | 7.6532 | 1.9466 | 1.92 | 2.7332 | 2.8499 | 6.5999 | 4.6799 | 12.0527 | 13.9727 | 20.5726 | 25.2525 | 0
14.4103 | 9.8222 | 2.2803 | 2.4205 | 4.4017 | 3.841 | 9.1026 | 6.6821 | 24.2325 | 26.6531 | 35.7556 | 42.4377 | 14.4103 | 9.8222 | 2.2803 | 2.4205 | 4.4017 | 3.851 | 9.1026 | 6.6821 | 24.2325 | 26.6531 | 35.7556 | 42.4377 | 0
-4.8914 | 5.6402 | 1.637 | 1.4554 | 1.1848 | 1.9109 | 4.2771 | 2.8217 | 0.74876 | 2.2042 | 6.4813 | 9.3031 | -4.8914 | 5.6402 | 1.637 | 1.4554 | 1.1848 | 1.9209 | 4.2771 | 2.8217 | 0.74876 | 2.2042 | 6.4813 | 9.3031 | 0
15.1442 | 9.9812 | 2.3048 | 2.4572 | 4.524 | 3.9144 | 9.2861 | 6.8288 | 25.1255 | 27.5827 | 36.8687 | 43.6976 | 15.1442 | 9.9812 | 2.3048 | 2.4572 | 4.524 | 3.9244 | 9.2861 | 6.8288 | 25.1255 | 27.5827 | 36.8687 | 43.6976 | 0
6.8025 | 8.1739 | 2.0267 | 2.0401 | 3.1337 | 3.0802 | 7.2006 | 5.1605 | 14.9763 | 17.0165 | 24.2171 | 29.3776 | 6.8025 | 8.1739 | 2.0267 | 2.0401 | 3.1337 | 3.0902 | 7.2006 | 5.1605 | 14.9763 | 17.0165 | 24.2171 | 29.3776 | 0
7.5565 | 8.3372 | 2.0519 | 2.0778 | 3.2594 | 3.1556 | 7.3891 | 5.3113 | 15.8937 | 17.9716 | 25.3607 | 30.672 | 7.5565 | 8.3372 | 2.0519 | 2.0778 | 3.2594 | 3.1656 | 7.3891 | 5.3113 | 15.8937 | 17.9716 | 25.3607 | 30.672 | 0
7.1078 | 8.24 | 2.0369 | 2.0554 | 3.1846 | 3.1108 | 7.2769 | 5.2216 | 15.3478 | 17.4032 | 24.6802 | 29.9017 | 7.1078 | 8.24 | 2.0369 | 2.0554 | 3.1846 | 3.1208 | 7.2769 | 5.2216 | 15.3478 | 17.4032 | 24.6802 | 29.9017 | 0
5.4872 | 7.8889 | 1.9829 | 1.9744 | 2.9145 | 2.9487 | 6.8718 | 4.8974 | 13.3761 | 15.3505 | 22.2223 | 27.1197 | 5.4872 | 7.8889 | 1.9829 | 1.9744 | 2.9145 | 2.9587 | 6.8718 | 4.8974 | 13.3761 | 15.3505 | 22.2223 | 27.1197 | 0
-0.20801 | 6.6549 | 1.7931 | 1.6896 | 1.9653 | 2.3792 | 5.448 | 3.7584 | 6.4469 | 8.1365 | 13.5845 | 17.3429 | -0.20801 | 6.6549 | 1.7931 | 1.6896 | 1.9653 | 2.3892 | 5.448 | 3.7584 | 6.4469 | 8.1365 | 13.5845 | 17.3429 | 0
17.5186 | 10.4957 | 2.384 | 2.5759 | 4.9198 | 4.1519 | 9.8796 | 7.3037 | 28.0143 | 30.5902 | 40.4698 | 47.7735 | 17.5186 | 10.4957 | 2.384 | 2.5759 | 4.9198 | 4.1619 | 9.8796 | 7.3037 | 28.0143 | 30.5902 | 40.4698 | 47.7735 | 0
10.1071 | 8.8899 | 2.1369 | 2.2054 | 3.6845 | 3.4107 | 8.0268 | 5.8214 | 18.997 | 21.2024 | 29.2292 | 35.0506 | 10.1071 | 8.8899 | 2.1369 | 2.2054 | 3.6845 | 3.4207 | 8.0268 | 5.8214 | 18.997 | 21.2024 | 29.2292 | 35.0506 | 0
8.5568 | 8.554 | 2.0852 | 2.1278 | 3.4261 | 3.2557 | 7.6392 | 5.5114 | 17.1107 | 19.2386 | 26.8777 | 32.3891 | 8.5568 | 8.554 | 2.0852 | 2.1278 | 3.4261 | 3.2657 | 7.6392 | 5.5114 | 17.1107 | 19.2386 | 26.8777 | 32.3891 | 0
6.2378 | 8.0515 | 2.0079 | 2.0119 | 3.0396 | 3.0238 | 7.0594 | 5.0476 | 14.2893 | 16.3012 | 23.3606 | 28.4082 | 6.2378 | 8.0515 | 2.0079 | 2.0119 | 3.0396 | 3.0338 | 7.0594 | 5.0476 | 14.2893 | 16.3012 | 23.3606 | 28.4082 | 0
-0.17002 | 6.6632 | 1.7943 | 1.6915 | 1.9717 | 2.383 | 5.4575 | 3.766 | 6.4931 | 8.1846 | 13.6421 | 17.4081 | -0.17002 | 6.6632 | 1.7943 | 1.6915 | 1.9717 | 2.393 | 5.4575 | 3.766 | 6.4931 | 8.1846 | 13.6421 | 17.4081 | 0
14.1065 | 9.7564 | 2.2702 | 2.4053 | 4.3511 | 3.8106 | 9.0266 | 6.6213 | 23.8629 | 26.2682 | 35.2948 | 41.9161 | 14.1065 | 9.7564 | 2.2702 | 2.4053 | 4.3511 | 3.8206 | 9.0266 | 6.6213 | 23.8629 | 26.2682 | 35.2948 | 41.9161 | 0
3.8564 | 7.5356 | 1.9285 | 1.8928 | 2.6427 | 2.7856 | 6.4641 | 4.5713 | 11.392 | 13.2848 | 19.7489 | 24.3202 | 3.8564 | 7.5356 | 1.9285 | 1.8928 | 2.6427 | 2.7956 | 6.4641 | 4.5713 | 11.392 | 13.2848 | 19.7489 | 24.3202 | 0
-3.938 | 5.8468 | 1.6687 | 1.5031 | 1.3437 | 2.0062 | 4.5155 | 3.0124 | 1.9088 | 3.4119 | 7.9273 | 10.9397 | -3.938 | 5.8468 | 1.6687 | 1.5031 | 1.3437 | 2.0162 | 4.5155 | 3.0124 | 1.9088 | 3.4119 | 7.9273 | 10.9397 | 0
8.0713 | 8.4488 | 2.069 | 2.1036 | 3.3452 | 3.2071 | 7.5178 | 5.4143 | 16.5201 | 18.6237 | 26.1415 | 31.5558 | 8.0713 | 8.4488 | 2.069 | 2.1036 | 3.3452 | 3.2171 | 7.5178 | 5.4143 | 16.5201 | 18.6237 | 26.1415 | 31.5558 | 0
-3.3537 | 5.9734 | 1.6882 | 1.5323 | 1.4411 | 2.0646 | 4.6616 | 3.1293 | 2.6197 | 4.152 | 8.8136 | 11.9428 | -3.3537 | 5.9734 | 1.6882 | 1.5323 | 1.4411 | 2.0746 | 4.6616 | 3.1293 | 2.6197 | 4.152 | 8.8136 | 11.9428 | 0
-2.1228 | 6.2401 | 1.7292 | 1.5939 | 1.6462 | 2.1877 | 4.9693 | 3.3754 | 4.1173 | 5.7111 | 10.6804 | 14.0558 | -2.1228 | 6.2401 | 1.7292 | 1.5939 | 1.6462 | 2.1977 | 4.9693 | 3.3754 | 4.1173 | 5.7111 | 10.6804 | 14.0558 | 0
3.4464 | 7.4467 | 1.9149 | 1.8723 | 2.5744 | 2.7446 | 6.3616 | 4.4893 | 10.8932 | 12.7655 | 19.1271 | 23.6164 | 3.4464 | 7.4467 | 1.9149 | 1.8723 | 2.5744 | 2.7546 | 6.3616 | 4.4893 | 10.8932 | 12.7655 | 19.1271 | 23.6164 | 0
9.7406 | 8.8105 | 2.1247 | 2.187 | 3.6234 | 3.3741 | 7.9351 | 5.7481 | 18.551 | 20.7381 | 28.6732 | 34.4213 | 9.7406 | 8.8105 | 2.1247 | 2.187 | 3.6234 | 3.3841 | 7.9351 | 5.7481 | 18.551 | 20.7381 | 28.6732 | 34.4213 | 0
14.3409 | 9.8072 | 2.278 | 2.417 | 4.3902 | 3.8341 | 9.0852 | 6.6682 | 24.1481 | 26.5652 | 35.6504 | 42.3186 | 14.3409 | 9.8072 | 2.278 | 2.417 | 4.3902 | 3.8441 | 9.0852 | 6.6682 | 24.1481 | 26.5652 | 35.6504 | 42.3186 | 0
10.4801 | 8.9707 | 2.1493 | 2.224 | 3.7467 | 3.448 | 8.12 | 5.896 | 19.4508 | 21.6748 | 29.7948 | 35.6908 | 10.4801 | 8.9707 | 2.1493 | 2.224 | 3.7467 | 3.458 | 8.12 | 5.896 | 19.4508 | 21.6748 | 29.7948 | 35.6908 | 0
1.9422 | 7.1208 | 1.8647 | 1.7971 | 2.3237 | 2.5942 | 5.9855 | 4.1884 | 9.063 | 10.8601 | 16.8456 | 21.0341 | 1.9422 | 7.1208 | 1.8647 | 1.7971 | 2.3237 | 2.6042 | 5.9855 | 4.1884 | 9.063 | 10.8601 | 16.8456 | 21.0341 | 0
-3.5251 | 5.9362 | 1.6825 | 1.5237 | 1.4125 | 2.0475 | 4.6187 | 3.095 | 2.4111 | 3.9349 | 8.5536 | 11.6486 | -3.5251 | 5.9362 | 1.6825 | 1.5237 | 1.4125 | 2.0575 | 4.6187 | 3.095 | 2.4111 | 3.9349 | 8.5536 | 11.6486 | 0
6.3941 | 8.0854 | 2.0131 | 2.0197 | 3.0657 | 3.0394 | 7.0985 | 5.0788 | 14.4795 | 16.4992 | 23.5978 | 28.6766 | 6.3941 | 8.0854 | 2.0131 | 2.0197 | 3.0657 | 3.0494 | 7.0985 | 5.0788 | 14.4795 | 16.4992 | 23.5978 | 28.6766 | 0
8.1827 | 8.4729 | 2.0728 | 2.1091 | 3.3638 | 3.2183 | 7.5457 | 5.4365 | 16.6556 | 18.7647 | 26.3104 | 31.7469 | 8.1827 | 8.4729 | 2.0728 | 2.1091 | 3.3638 | 3.2283 | 7.5457 | 5.4365 | 16.6556 | 18.7647 | 26.3104 | 31.7469 | 0
13.4254 | 9.6088 | 2.2475 | 2.3713 | 4.2376 | 3.7425 | 8.8563 | 6.4851 | 23.0342 | 25.4055 | 34.2618 | 40.7469 | 13.4254 | 9.6088 | 2.2475 | 2.3713 | 4.2376 | 3.7525 | 8.8563 | 6.4851 | 23.0342 | 25.4055 | 34.2618 | 40.7469 | 0
12.781 | 9.4692 | 2.226 | 2.339 | 4.1302 | 3.6781 | 8.6952 | 6.3562 | 22.2502 | 24.5892 | 33.2844 | 39.6406 | 12.781 | 9.4692 | 2.226 | 2.339 | 4.1302 | 3.6881 | 8.6952 | 6.3562 | 22.2502 | 24.5892 | 33.2844 | 39.6406 | 0
5.32 | 7.8527 | 1.9773 | 1.966 | 2.8867 | 2.932 | 6.83 | 4.864 | 13.1726 | 15.1386 | 21.9686 | 26.8326 | 5.32 | 7.8527 | 1.9773 | 1.966 | 2.8867 | 2.942 | 6.83 | 4.864 | 13.1726 | 15.1386 | 21.9686 | 26.8326 | 0
0.36357 | 6.7788 | 1.8121 | 1.7182 | 2.0606 | 2.4364 | 5.5909 | 3.8727 | 7.1423 | 8.8605 | 14.4514 | 18.3241 | 0.36357 | 6.7788 | 1.8121 | 1.7182 | 2.0606 | 2.4464 | 5.5909 | 3.8727 | 7.1423 | 8.8605 | 14.4514 | 18.3241 | 0
4.4875 | 7.6723 | 1.9496 | 1.9244 | 2.7479 | 2.8487 | 6.6219 | 4.6975 | 12.1597 | 14.0841 | 20.706 | 25.4035 | 4.4875 | 7.6723 | 1.9496 | 1.9244 | 2.7479 | 2.8587 | 6.6219 | 4.6975 | 12.1597 | 14.0841 | 20.706 | 25.4035 | 0
16.3134 | 10.2346 | 2.3438 | 2.5157 | 4.7189 | 4.0313 | 9.5783 | 7.0627 | 26.548 | 29.0636 | 38.642 | 45.7047 | 16.3134 | 10.2346 | 2.3438 | 2.5157 | 4.7189 | 4.0413 | 9.5783 | 7.0627 | 26.548 | 29.0636 | 38.642 | 45.7047 | 0
4.2492 | 7.6207 | 1.9416 | 1.9125 | 2.7082 | 2.8249 | 6.5623 | 4.6498 | 11.8698 | 13.7823 | 20.3446 | 24.9944 | 4.2492 | 7.6207 | 1.9416 | 1.9125 | 2.7082 | 2.8349 | 6.5623 | 4.6498 | 11.8698 | 13.7823 | 20.3446 | 24.9944 | 0
3.7637 | 7.5155 | 1.9255 | 1.8882 | 2.6273 | 2.7764 | 6.4409 | 4.5527 | 11.2792 | 13.1674 | 19.6083 | 24.161 | 3.7637 | 7.5155 | 1.9255 | 1.8882 | 2.6273 | 2.7864 | 6.4409 | 4.5527 | 11.2792 | 13.1674 | 19.6083 | 24.161 | 0
-1.4859 | 6.3781 | 1.7505 | 1.6257 | 1.7524 | 2.2514 | 5.1285 | 3.5028 | 4.8922 | 6.5179 | 11.6464 | 15.1492 | -1.4859 | 6.3781 | 1.7505 | 1.6257 | 1.7524 | 2.2614 | 5.1285 | 3.5028 | 4.8922 | 6.5179 | 11.6464 | 15.1492 | 0
13.1201 | 9.5427 | 2.2373 | 2.356 | 4.1867 | 3.712 | 8.78 | 6.424 | 22.6628 | 25.0188 | 33.7988 | 40.2228 | 13.1201 | 9.5427 | 2.2373 | 2.356 | 4.1867 | 3.722 | 8.78 | 6.424 | 22.6628 | 25.0188 | 33.7988 | 40.2228 | 0
1.2847 | 6.9783 | 1.8428 | 1.7642 | 2.2141 | 2.5285 | 5.8212 | 4.0569 | 8.263 | 10.0273 | 15.8484 | 19.9054 | 1.2847 | 6.9783 | 1.8428 | 1.7642 | 2.2141 | 2.5385 | 5.8212 | 4.0569 | 8.263 | 10.0273 | 15.8484 | 19.9054 | 0
10.1324 | 8.8954 | 2.1377 | 2.2066 | 3.6887 | 3.4132 | 8.0331 | 5.8265 | 19.0278 | 21.2344 | 29.2675 | 35.094 | 10.1324 | 8.8954 | 2.1377 | 2.2066 | 3.6887 | 3.4232 | 8.0331 | 5.8265 | 19.0278 | 21.2344 | 29.2675 | 35.094 | 0
19.078 | 10.8336 | 2.4359 | 2.6539 | 5.1797 | 4.3078 | 10.2695 | 7.6156 | 29.9115 | 32.5654 | 42.8349 | 50.4505 | 19.078 | 10.8336 | 2.4359 | 2.6539 | 5.1797 | 4.3178 | 10.2695 | 7.6156 | 29.9115 | 32.5654 | 42.8349 | 50.4505 | 0
14.4903 | 9.8396 | 2.283 | 2.4245 | 4.4151 | 3.849 | 9.1226 | 6.6981 | 24.3299 | 26.7544 | 35.877 | 42.5751 | 14.4903 | 9.8396 | 2.283 | 2.4245 | 4.4151 | 3.859 | 9.1226 | 6.6981 | 24.3299 | 26.7544 | 35.877 | 42.5751 | 0
1.3037 | 6.9825 | 1.8435 | 1.7652 | 2.2173 | 2.5304 | 5.8259 | 4.0607 | 8.2862 | 10.0514 | 15.8773 | 19.9381 | 1.3037 | 6.9825 | 1.8435 | 1.7652 | 2.2173 | 2.5404 | 5.8259 | 4.0607 | 8.2862 | 10.0514 | 15.8773 | 19.9381 | 0
4.5343 | 7.6824 | 1.9511 | 1.9267 | 2.7557 | 2.8534 | 6.6336 | 4.7069 | 12.2167 | 14.1434 | 20.777 | 25.4838 | 4.5343 | 7.6824 | 1.9511 | 1.9267 | 2.7557 | 2.8634 | 6.6336 | 4.7069 | 12.2167 | 14.1434 | 20.777 | 25.4838 | 0
8.9171 | 8.632 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5834 | 17.5492 | 19.695 | 27.4243 | 33.0077 | 8.9171 | 8.632 | 2.0972 | 2.1459 | 3.4862 | 3.3017 | 7.7293 | 5.5834 | 17.5492 | 19.695 | 27.4243 | 33.0077 | 0
4.2696 | 7.6251 | 1.9423 | 1.9135 | 2.7116 | 2.827 | 6.5674 | 4.6539 | 11.8947 | 13.8082 | 20.3756 | 25.0295 | 4.2696 | 7.6251 | 1.9423 | 1.9135 | 2.7116 | 2.837 | 6.5674 | 4.6539 | 11.8947 | 13.8082 | 20.3756 | 25.0295 | 0
1.8769 | 7.1067 | 1.8626 | 1.7938 | 2.3128 | 2.5877 | 5.9692 | 4.1754 | 8.9835 | 10.7774 | 16.7466 | 20.922 | 1.8769 | 7.1067 | 1.8626 | 1.7938 | 2.3128 | 2.5977 | 5.9692 | 4.1754 | 8.9835 | 10.7774 | 16.7466 | 20.922 | 0
1.2769 | 6.9767 | 1.8426 | 1.7638 | 2.2128 | 2.5277 | 5.8192 | 4.0554 | 8.2536 | 10.0174 | 15.8367 | 19.8921 | 1.2769 | 6.9767 | 1.8426 | 1.7638 | 2.2128 | 2.5377 | 5.8192 | 4.0554 | 8.2536 | 10.0174 | 15.8367 | 19.8921 | 0
4.4293 | 7.6597 | 1.9476 | 1.9215 | 2.7382 | 2.8429 | 6.6073 | 4.6859 | 12.089 | 14.0105 | 20.6178 | 25.3037 | 4.4293 | 7.6597 | 1.9476 | 1.9215 | 2.7382 | 2.8529 | 6.6073 | 4.6859 | 12.089 | 14.0105 | 20.6178 | 25.3037 | 0
-0.71252 | 6.5456 | 1.7762 | 1.6644 | 1.8812 | 2.3287 | 5.3219 | 3.6575 | 5.8331 | 7.4975 | 12.8193 | 16.4768 | -0.71252 | 6.5456 | 1.7762 | 1.6644 | 1.8812 | 2.3387 | 5.3219 | 3.6575 | 5.8331 | 7.4975 | 12.8193 | 16.4768 | 0
0.56209 | 6.8218 | 1.8187 | 1.7281 | 2.0937 | 2.4562 | 5.6405 | 3.9124 | 7.3839 | 9.112 | 14.7525 | 18.6649 | 0.56209 | 6.8218 | 1.8187 | 1.7281 | 2.0937 | 2.4662 | 5.6405 | 3.9124 | 7.3839 | 9.112 | 14.7525 | 18.6649 | 0
3.2537 | 7.405 | 1.9085 | 1.8627 | 2.5423 | 2.7254 | 6.3134 | 4.4507 | 10.6587 | 12.5214 | 18.8348 | 23.2856 | 3.2537 | 7.405 | 1.9085 | 1.8627 | 2.5423 | 2.7354 | 6.3134 | 4.4507 | 10.6587 | 12.5214 | 18.8348 | 23.2856 | 0
4.564 | 7.6889 | 1.9521 | 1.9282 | 2.7607 | 2.8564 | 6.641 | 4.7128 | 12.2529 | 14.1811 | 20.8221 | 25.5349 | 4.564 | 7.6889 | 1.9521 | 1.9282 | 2.7607 | 2.8664 | 6.641 | 4.7128 | 12.2529 | 14.1811 | 20.8221 | 25.5349 | 0
17.5236 | 10.4968 | 2.3841 | 2.5762 | 4.9206 | 4.1524 | 9.8809 | 7.3047 | 28.0204 | 30.5966 | 40.4775 | 47.7823 | 17.5236 | 10.4968 | 2.3841 | 2.5762 | 4.9206 | 4.1624 | 9.8809 | 7.3047 | 28.0204 | 30.5966 | 40.4775 | 47.7823 | 0
8.2391 | 8.4851 | 2.0746 | 2.112 | 3.3732 | 3.2239 | 7.5598 | 5.4478 | 16.7242 | 18.8362 | 26.396 | 31.8438 | 8.2391 | 8.4851 | 2.0746 | 2.112 | 3.3732 | 3.2339 | 7.5598 | 5.4478 | 16.7242 | 18.8362 | 26.396 | 31.8438 | 0
11.3647 | 9.1623 | 2.1788 | 2.2682 | 3.8941 | 3.5365 | 8.3412 | 6.0729 | 20.527 | 22.7953 | 31.1364 | 37.2094 | 11.3647 | 9.1623 | 2.1788 | 2.2682 | 3.8941 | 3.5465 | 8.3412 | 6.0729 | 20.527 | 22.7953 | 31.1364 | 37.2094 | 0
-1.6549 | 6.3414 | 1.7448 | 1.6173 | 1.7242 | 2.2345 | 5.0863 | 3.469 | 4.6866 | 6.3038 | 11.3901 | 14.8591 | -1.6549 | 6.3414 | 1.7448 | 1.6173 | 1.7242 | 2.2445 | 5.0863 | 3.469 | 4.6866 | 6.3038 | 11.3901 | 14.8591 | 0
8.9418 | 8.6374 | 2.0981 | 2.1471 | 3.4903 | 3.2942 | 7.7354 | 5.5884 | 17.5791 | 19.7262 | 27.4617 | 33.05 | 8.9418 | 8.6374 | 2.0981 | 2.1471 | 3.4903 | 3.3042 | 7.7354 | 5.5884 | 17.5791 | 19.7262 | 27.4617 | 33.05 | 0
11.8561 | 9.2688 | 2.1952 | 2.2928 | 3.976 | 3.5856 | 8.464 | 6.1712 | 21.1249 | 23.4177 | 31.8817 | 38.053 | 11.8561 | 9.2688 | 2.1952 | 2.2928 | 3.976 | 3.5956 | 8.464 | 6.1712 | 21.1249 | 23.4177 | 31.8817 | 38.053 | 0
10.4949 | 8.9739 | 2.1498 | 2.2247 | 3.7492 | 3.4495 | 8.1237 | 5.899 | 19.4688 | 21.6936 | 29.8173 | 35.7163 | 10.4949 | 8.9739 | 2.1498 | 2.2247 | 3.7492 | 3.4595 | 8.1237 | 5.899 | 19.4688 | 21.6936 | 29.8173 | 35.7163 | 0
10.916 | 9.0651 | 2.1639 | 2.2458 | 3.8193 | 3.4916 | 8.229 | 5.9832 | 19.9811 | 22.2269 | 30.4559 | 36.4391 | 10.916 | 9.0651 | 2.1639 | 2.2458 | 3.8193 | 3.5016 | 8.229 | 5.9832 | 19.9811 | 22.2269 | 30.4559 | 36.4391 | 0
9.4413 | 8.7456 | 2.1147 | 2.1721 | 3.5736 | 3.3441 | 7.8603 | 5.6883 | 18.1869 | 20.359 | 28.2193 | 33.9076 | 9.4413 | 8.7456 | 2.1147 | 2.1721 | 3.5736 | 3.3541 | 7.8603 | 5.6883 | 18.1869 | 20.359 | 28.2193 | 33.9076 | 0
3.8479 | 7.5337 | 1.9283 | 1.8924 | 2.6413 | 2.7848 | 6.462 | 4.5696 | 11.3817 | 13.2741 | 19.7361 | 24.3056 | 3.8479 | 7.5337 | 1.9283 | 1.8924 | 2.6413 | 2.7948 | 6.462 | 4.5696 | 11.3817 | 13.2741 | 19.7361 | 24.3056 | 0
0.12473 | 6.727 | 1.8042 | 1.7062 | 2.0208 | 2.4125 | 5.5312 | 3.8249 | 6.8518 | 8.558 | 14.0892 | 17.9141 | 0.12473 | 6.727 | 1.8042 | 1.7062 | 2.0208 | 2.4225 | 5.5312 | 3.8249 | 6.8518 | 8.558 | 14.0892 | 17.9141 | 0
15.3826 | 10.0329 | 2.3128 | 2.4691 | 4.5638 | 3.9383 | 9.3457 | 6.8765 | 25.4155 | 27.8847 | 37.2303 | 44.1068 | 15.3826 | 10.0329 | 2.3128 | 2.4691 | 4.5638 | 3.9483 | 9.3457 | 6.8765 | 25.4155 | 27.8847 | 37.2303 | 44.1068 | 0
5.5747 | 7.9078 | 1.9858 | 1.9787 | 2.9291 | 2.9575 | 6.8937 | 4.9149 | 13.4825 | 15.4613 | 22.3549 | 27.2699 | 5.5747 | 7.9078 | 1.9858 | 1.9787 | 2.9291 | 2.9675 | 6.8937 | 4.9149 | 13.4825 | 15.4613 | 22.3549 | 27.2699 | 0
7.5314 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8632 | 17.9398 | 25.3227 | 30.629 | 7.5314 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1631 | 7.3829 | 5.3063 | 15.8632 | 17.9398 | 25.3227 | 30.629 | 0
5.6536 | 7.9249 | 1.9885 | 1.9827 | 2.9423 | 2.9654 | 6.9134 | 4.9307 | 13.5786 | 15.5612 | 22.4746 | 27.4054 | 5.6536 | 7.9249 | 1.9885 | 1.9827 | 2.9423 | 2.9754 | 6.9134 | 4.9307 | 13.5786 | 15.5612 | 22.4746 | 27.4054 | 0
7.9005 | 8.4118 | 2.0633 | 2.095 | 3.3167 | 3.19 | 7.4751 | 5.3801 | 16.3122 | 18.4073 | 25.8824 | 31.2625 | 7.9005 | 8.4118 | 2.0633 | 2.095 | 3.3167 | 3.2 | 7.4751 | 5.3801 | 16.3122 | 18.4073 | 25.8824 | 31.2625 | 0
2.7503 | 7.2959 | 1.8917 | 1.8375 | 2.4584 | 2.675 | 6.1876 | 4.3501 | 10.0462 | 11.8837 | 18.0713 | 22.4213 | 2.7503 | 7.2959 | 1.8917 | 1.8375 | 2.4584 | 2.685 | 6.1876 | 4.3501 | 10.0462 | 11.8837 | 18.0713 | 22.4213 | 0
15.9912 | 10.1648 | 2.333 | 2.4996 | 4.6652 | 3.9991 | 9.4978 | 6.9982 | 26.156 | 28.6556 | 38.1534 | 45.1516 | 15.9912 | 10.1648 | 2.333 | 2.4996 | 4.6652 | 4.0091 | 9.4978 | 6.9982 | 26.156 | 28.6556 | 38.1534 | 45.1516 | 0
3.5741 | 7.4744 | 1.9191 | 1.8787 | 2.5957 | 2.7574 | 6.3935 | 4.5148 | 11.0485 | 12.9272 | 19.3207 | 23.8356 | 3.5741 | 7.4744 | 1.9191 | 1.8787 | 2.5957 | 2.7674 | 6.3935 | 4.5148 | 11.0485 | 12.9272 | 19.3207 | 23.8356 | 0
8.2161 | 8.4802 | 2.0739 | 2.1108 | 3.3693 | 3.2216 | 7.554 | 5.4432 | 16.6962 | 18.8071 | 26.3611 | 31.8043 | 8.2161 | 8.4802 | 2.0739 | 2.1108 | 3.3693 | 3.2316 | 7.554 | 5.4432 | 16.6962 | 18.8071 | 26.3611 | 31.8043 | 0
11.5303 | 9.1982 | 2.1843 | 2.2765 | 3.9217 | 3.553 | 8.3826 | 6.1061 | 20.7286 | 23.0051 | 31.3877 | 37.4937 | 11.5303 | 9.1982 | 2.1843 | 2.2765 | 3.9217 | 3.563 | 8.3826 | 6.1061 | 20.7286 | 23.0051 | 31.3877 | 37.4937 | 0
9.1597 | 8.6846 | 2.1053 | 2.158 | 3.5266 | 3.316 | 7.7899 | 5.6319 | 17.8443 | 20.0023 | 27.7923 | 33.4242 | 9.1597 | 8.6846 | 2.1053 | 2.158 | 3.5266 | 3.326 | 7.7899 | 5.6319 | 17.8443 | 20.0023 | 27.7923 | 33.4242 | 0
12.984 | 9.5132 | 2.2328 | 2.3492 | 4.164 | 3.6984 | 8.746 | 6.3968 | 22.4972 | 24.8464 | 33.5924 | 39.9892 | 12.984 | 9.5132 | 2.2328 | 2.3492 | 4.164 | 3.7084 | 8.746 | 6.3968 | 22.4972 | 24.8464 | 33.5924 | 39.9892 | 0
18.7844 | 10.7699 | 2.4261 | 2.6392 | 5.1307 | 4.2784 | 10.1961 | 7.5569 | 29.5543 | 32.1935 | 42.3896 | 49.9465 | 18.7844 | 10.7699 | 2.4261 | 2.6392 | 5.1307 | 4.2884 | 10.1961 | 7.5569 | 29.5543 | 32.1935 | 42.3896 | 49.9465 | 0
9.9286 | 8.8512 | 2.131 | 2.1964 | 3.6548 | 3.3929 | 7.9822 | 5.7857 | 18.7799 | 20.9763 | 28.9585 | 34.7442 | 9.9286 | 8.8512 | 2.131 | 2.1964 | 3.6548 | 3.4029 | 7.9822 | 5.7857 | 18.7799 | 20.9763 | 28.9585 | 34.7442 | 0
2.0856 | 7.1519 | 1.8695 | 1.8043 | 2.3476 | 2.6086 | 6.0214 | 4.2171 | 9.2375 | 11.0418 | 17.0632 | 21.2803 | 2.0856 | 7.1519 | 1.8695 | 1.8043 | 2.3476 | 2.6186 | 6.0214 | 4.2171 | 9.2375 | 11.0418 | 17.0632 | 21.2803 | 0
7.7123 | 8.371 | 2.0571 | 2.0856 | 3.2854 | 3.1712 | 7.4281 | 5.3425 | 16.0833 | 18.169 | 25.5971 | 30.9395 | 7.7123 | 8.371 | 2.0571 | 2.0856 | 3.2854 | 3.1812 | 7.4281 | 5.3425 | 16.0833 | 18.169 | 25.5971 | 30.9395 | 0
4.3418 | 7.6407 | 1.9447 | 1.9171 | 2.7236 | 2.8342 | 6.5855 | 4.6684 | 11.9825 | 13.8996 | 20.4851 | 25.1535 | 4.3418 | 7.6407 | 1.9447 | 1.9171 | 2.7236 | 2.8442 | 6.5855 | 4.6684 | 11.9825 | 13.8996 | 20.4851 | 25.1535 | 0
11.026 | 9.089 | 2.1675 | 2.2513 | 3.8377 | 3.5026 | 8.2565 | 6.0052 | 20.115 | 22.3663 | 30.6228 | 36.628 | 11.026 | 9.089 | 2.1675 | 2.2513 | 3.8377 | 3.5126 | 8.2565 | 6.0052 | 20.115 | 22.3663 | 30.6228 | 36.628 | 0
17.0012 | 10.3836 | 2.3667 | 2.5501 | 4.8335 | 4.1001 | 9.7503 | 7.2002 | 27.3849 | 29.9349 | 39.6852 | 46.8855 | 17.0012 | 10.3836 | 2.3667 | 2.5501 | 4.8335 | 4.1101 | 9.7503 | 7.2002 | 27.3849 | 29.9349 | 39.6852 | 46.8855 | 0
2.8353 | 7.3143 | 1.8945 | 1.8418 | 2.4726 | 2.6835 | 6.2088 | 4.3671 | 10.1496 | 11.9914 | 18.2002 | 22.5673 | 2.8353 | 7.3143 | 1.8945 | 1.8418 | 2.4726 | 2.6935 | 6.2088 | 4.3671 | 10.1496 | 11.9914 | 18.2002 | 22.5673 | 0
2.9314 | 7.3351 | 1.8977 | 1.8466 | 2.4886 | 2.6931 | 6.2329 | 4.3863 | 10.2666 | 12.1132 | 18.346 | 22.7323 | 2.9314 | 7.3351 | 1.8977 | 1.8466 | 2.4886 | 2.7031 | 6.2329 | 4.3863 | 10.2666 | 12.1132 | 18.346 | 22.7323 | 0
0.2458 | 6.7533 | 1.8082 | 1.7123 | 2.041 | 2.4246 | 5.5615 | 3.8492 | 6.9991 | 8.7114 | 14.2728 | 18.122 | 0.2458 | 6.7533 | 1.8082 | 1.7123 | 2.041 | 2.4346 | 5.5615 | 3.8492 | 6.9991 | 8.7114 | 14.2728 | 18.122 | 0
6.4896 | 8.1061 | 2.0163 | 2.0245 | 3.0816 | 3.049 | 7.1224 | 5.0979 | 14.5957 | 16.6202 | 23.7426 | 28.8405 | 6.4896 | 8.1061 | 2.0163 | 2.0245 | 3.0816 | 3.059 | 7.1224 | 5.0979 | 14.5957 | 16.6202 | 23.7426 | 28.8405 | 0
-6.0201 | 5.3956 | 1.5993 | 1.399 | 0.99665 | 1.798 | 3.995 | 2.596 | -0.62448 | 0.77452 | 4.7695 | 7.3655 | -6.0201 | 5.3956 | 1.5993 | 1.399 | 0.99665 | 1.808 | 3.995 | 2.596 | -0.62448 | 0.77452 | 4.7695 | 7.3655 | 0
3.3036 | 7.4158 | 1.9101 | 1.8652 | 2.5506 | 2.7304 | 6.3259 | 4.4607 | 10.7194 | 12.5846 | 18.9105 | 23.3712 | 3.3036 | 7.4158 | 1.9101 | 1.8652 | 2.5506 | 2.7404 | 6.3259 | 4.4607 | 10.7194 | 12.5846 | 18.9105 | 23.3712 | 0
8.8664 | 8.621 | 2.0955 | 2.1433 | 3.4777 | 3.2866 | 7.7166 | 5.5733 | 17.4874 | 19.6307 | 27.3473 | 32.9206 | 8.8664 | 8.621 | 2.0955 | 2.1433 | 3.4777 | 3.2966 | 7.7166 | 5.5733 | 17.4874 | 19.6307 | 27.3473 | 32.9206 | 0
13.6777 | 9.6635 | 2.2559 | 2.3839 | 4.2796 | 3.7678 | 8.9194 | 6.5355 | 23.3412 | 25.7251 | 34.6446 | 41.1801 | 13.6777 | 9.6635 | 2.2559 | 2.3839 | 4.2796 | 3.7778 | 8.9194 | 6.5355 | 23.3412 | 25.7251 | 34.6446 | 41.1801 | 0
7.5315 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8633 | 17.9399 | 25.3228 | 30.629 | 7.5315 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1631 | 7.3829 | 5.3063 | 15.8633 | 17.9399 | 25.3228 | 30.629 | 0
6.5002 | 8.1084 | 2.0167 | 2.025 | 3.0834 | 3.05 | 7.1251 | 5.1 | 14.6086 | 16.6336 | 23.7587 | 28.8587 | 6.5002 | 8.1084 | 2.0167 | 2.025 | 3.0834 | 3.06 | 7.1251 | 5.1 | 14.6086 | 16.6336 | 23.7587 | 28.8587 | 0
12.3442 | 9.3746 | 2.2115 | 2.3172 | 4.0574 | 3.6344 | 8.586 | 6.2688 | 21.7187 | 24.036 | 32.622 | 38.8908 | 12.3442 | 9.3746 | 2.2115 | 2.3172 | 4.0574 | 3.6444 | 8.586 | 6.2688 | 21.7187 | 24.036 | 32.622 | 38.8908 | 0
-2.6847 | 6.1183 | 1.7105 | 1.5658 | 1.5526 | 2.1315 | 4.8288 | 3.2631 | 3.4337 | 4.9994 | 9.8283 | 13.0913 | -2.6847 | 6.1183 | 1.7105 | 1.5658 | 1.5526 | 2.1415 | 4.8288 | 3.2631 | 3.4337 | 4.9994 | 9.8283 | 13.0913 | 0
11.3098 | 9.1505 | 2.177 | 2.2655 | 3.885 | 3.531 | 8.3274 | 6.062 | 20.4602 | 22.7257 | 31.0532 | 37.1151 | 11.3098 | 9.1505 | 2.177 | 2.2655 | 3.885 | 3.541 | 8.3274 | 6.062 | 20.4602 | 22.7257 | 31.0532 | 37.1151 | 0
11.2312 | 9.1334 | 2.1744 | 2.2616 | 3.8719 | 3.5231 | 8.3078 | 6.0462 | 20.3646 | 22.6262 | 30.934 | 36.9802 | 11.2312 | 9.1334 | 2.1744 | 2.2616 | 3.8719 | 3.5331 | 8.3078 | 6.0462 | 20.3646 | 22.6262 | 30.934 | 36.9802 | 0
-2.2417 | 6.2143 | 1.7253 | 1.5879 | 1.6264 | 2.1758 | 4.9396 | 3.3517 | 3.9725 | 5.5605 | 10.5 | 13.8517 | -2.2417 | 6.2143 | 1.7253 | 1.5879 | 1.6264 | 2.1858 | 4.9396 | 3.3517 | 3.9725 | 5.5605 | 10.5 | 13.8517 | 0
13.1798 | 9.5556 | 2.2393 | 2.359 | 4.1966 | 3.718 | 8.795 | 6.436 | 22.7354 | 25.0944 | 33.8894 | 40.3253 | 13.1798 | 9.5556 | 2.2393 | 2.359 | 4.1966 | 3.728 | 8.795 | 6.436 | 22.7354 | 25.0944 | 33.8894 | 40.3253 | 0
-6.0136 | 5.397 | 1.5995 | 1.3993 | 0.99773 | 1.7986 | 3.9966 | 2.5973 | -0.61658 | 0.78274 | 4.7793 | 7.3766 | -6.0136 | 5.397 | 1.5995 | 1.3993 | 0.99773 | 1.8086 | 3.9966 | 2.5973 | -0.61658 | 0.78274 | 4.7793 | 7.3766 | 0
2.8839 | 7.3249 | 1.8961 | 1.8442 | 2.4807 | 2.6884 | 6.221 | 4.3768 | 10.2088 | 12.053 | 18.274 | 22.6508 | 2.8839 | 7.3249 | 1.8961 | 1.8442 | 2.4807 | 2.6984 | 6.221 | 4.3768 | 10.2088 | 12.053 | 18.274 | 22.6508 | 0
8.9173 | 8.6321 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5835 | 17.5494 | 19.6953 | 27.4246 | 33.0081 | 8.9173 | 8.6321 | 2.0972 | 2.1459 | 3.4862 | 3.3017 | 7.7293 | 5.5835 | 17.5494 | 19.6953 | 27.4246 | 33.0081 | 0
7.3594 | 8.2945 | 2.0453 | 2.068 | 3.2266 | 3.1359 | 7.3399 | 5.2719 | 15.654 | 17.722 | 25.0618 | 30.3337 | 7.3594 | 8.2945 | 2.0453 | 2.068 | 3.2266 | 3.1459 | 7.3399 | 5.2719 | 15.654 | 17.722 | 25.0618 | 30.3337 | 0
10.6967 | 9.0176 | 2.1566 | 2.2348 | 3.7828 | 3.4697 | 8.1742 | 5.9393 | 19.7143 | 21.9491 | 30.1233 | 36.0626 | 10.6967 | 9.0176 | 2.1566 | 2.2348 | 3.7828 | 3.4797 | 8.1742 | 5.9393 | 19.7143 | 21.9491 | 30.1233 | 36.0626 | 0
14.8238 | 9.9118 | 2.2941 | 2.4412 | 4.4706 | 3.8824 | 9.206 | 6.7648 | 24.7356 | 27.1768 | 36.3828 | 43.1475 | 14.8238 | 9.9118 | 2.2941 | 2.4412 | 4.4706 | 3.8924 | 9.206 | 6.7648 | 24.7356 | 27.1768 | 36.3828 | 43.1475 | 0
11.6384 | 9.2216 | 2.1879 | 2.2819 | 3.9397 | 3.5638 | 8.4096 | 6.1277 | 20.86 | 23.1419 | 31.5515 | 37.6792 | 11.6384 | 9.2216 | 2.1879 | 2.2819 | 3.9397 | 3.5738 | 8.4096 | 6.1277 | 20.86 | 23.1419 | 31.5515 | 37.6792 | 0
17.6788 | 10.5304 | 2.3893 | 2.5839 | 4.9465 | 4.1679 | 9.9197 | 7.3358 | 28.2092 | 30.7931 | 40.7128 | 48.0486 | 17.6788 | 10.5304 | 2.3893 | 2.5839 | 4.9465 | 4.1779 | 9.9197 | 7.3358 | 28.2092 | 30.7931 | 40.7128 | 48.0486 | 0
4.3589 | 7.6444 | 1.9453 | 1.9179 | 2.7265 | 2.8359 | 6.5897 | 4.6718 | 12.0033 | 13.9213 | 20.511 | 25.1828 | 4.3589 | 7.6444 | 1.9453 | 1.9179 | 2.7265 | 2.8459 | 6.5897 | 4.6718 | 12.0033 | 13.9213 | 20.511 | 25.1828 | 0
0.47148 | 6.8022 | 1.8157 | 1.7236 | 2.0786 | 2.4471 | 5.6179 | 3.8943 | 7.2736 | 8.9972 | 14.6151 | 18.5094 | 0.47148 | 6.8022 | 1.8157 | 1.7236 | 2.0786 | 2.4571 | 5.6179 | 3.8943 | 7.2736 | 8.9972 | 14.6151 | 18.5094 | 0
7.8912 | 8.4097 | 2.063 | 2.0946 | 3.3152 | 3.1891 | 7.4728 | 5.3782 | 16.3009 | 18.3955 | 25.8682 | 31.2465 | 7.8912 | 8.4097 | 2.063 | 2.0946 | 3.3152 | 3.1991 | 7.4728 | 5.3782 | 16.3009 | 18.3955 | 25.8682 | 31.2465 | 0
4.3809 | 7.6492 | 1.946 | 1.919 | 2.7301 | 2.8381 | 6.5952 | 4.6762 | 12.0301 | 13.9491 | 20.5444 | 25.2205 | 4.3809 | 7.6492 | 1.946 | 1.919 | 2.7301 | 2.8481 | 6.5952 | 4.6762 | 12.0301 | 13.9491 | 20.5444 | 25.2205 | 0
12.5045 | 9.4093 | 2.2168 | 2.3252 | 4.0841 | 3.6505 | 8.6261 | 6.3009 | 21.9138 | 24.2391 | 32.8652 | 39.1661 | 12.5045 | 9.4093 | 2.2168 | 2.3252 | 4.0841 | 3.6605 | 8.6261 | 6.3009 | 21.9138 | 24.2391 | 32.8652 | 39.1661 | 0
-2.5623 | 6.1448 | 1.7146 | 1.5719 | 1.5729 | 2.1438 | 4.8594 | 3.2875 | 3.5825 | 5.1544 | 10.0138 | 13.3013 | -2.5623 | 6.1448 | 1.7146 | 1.5719 | 1.5729 | 2.1538 | 4.8594 | 3.2875 | 3.5825 | 5.1544 | 10.0138 | 13.3013 | 0
5.628 | 7.9194 | 1.9876 | 1.9814 | 2.938 | 2.9628 | 6.907 | 4.9256 | 13.5474 | 15.5288 | 22.4358 | 27.3614 | 5.628 | 7.9194 | 1.9876 | 1.9814 | 2.938 | 2.9728 | 6.907 | 4.9256 | 13.5474 | 15.5288 | 22.4358 | 27.3614 | 0
-2.8667 | 6.0789 | 1.7044 | 1.5567 | 1.5222 | 2.1133 | 4.7833 | 3.2267 | 3.2122 | 4.7689 | 9.5522 | 12.7789 | -2.8667 | 6.0789 | 1.7044 | 1.5567 | 1.5222 | 2.1233 | 4.7833 | 3.2267 | 3.2122 | 4.7689 | 9.5522 | 12.7789 | 0
-6.8201 | 5.2223 | 1.5727 | 1.359 | 0.86332 | 1.718 | 3.795 | 2.436 | -1.5977 | -0.23874 | 3.5562 | 5.9922 | -6.8201 | 5.2223 | 1.5727 | 1.359 | 0.86332 | 1.728 | 3.795 | 2.436 | -1.5977 | -0.23874 | 3.5562 | 5.9922 | 0
-0.06598 | 6.6857 | 1.7978 | 1.6967 | 1.989 | 2.3934 | 5.4835 | 3.7868 | 6.6197 | 8.3164 | 13.7999 | 17.5867 | -0.06598 | 6.6857 | 1.7978 | 1.6967 | 1.989 | 2.4034 | 5.4835 | 3.7868 | 6.6197 | 8.3164 | 13.7999 | 17.5867 | 0
-4.274 | 5.774 | 1.6575 | 1.4863 | 1.2877 | 1.9726 | 4.4315 | 2.9452 | 1.4999 | 2.9862 | 7.4177 | 10.3629 | -4.274 | 5.774 | 1.6575 | 1.4863 | 1.2877 | 1.9826 | 4.4315 | 2.9452 | 1.4999 | 2.9862 | 7.4177 | 10.3629 | 0
9.4 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.85 | 5.68 | 18.1367 | 20.3067 | 28.1567 | 33.8367 | 9.4 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.35 | 7.85 | 5.68 | 18.1367 | 20.3067 | 28.1567 | 33.8367 | 0
-0.6032 | 6.5693 | 1.7799 | 1.6698 | 1.8995 | 2.3397 | 5.3492 | 3.6794 | 5.9661 | 7.6359 | 12.9851 | 16.6645 | -0.6032 | 6.5693 | 1.7799 | 1.6698 | 1.8995 | 2.3497 | 5.3492 | 3.6794 | 5.9661 | 7.6359 | 12.9851 | 16.6645 | 0
0.58262 | 6.8262 | 1.8194 | 1.7291 | 2.0971 | 2.4583 | 5.6457 | 3.9165 | 7.4089 | 9.138 | 14.7836 | 18.7002 | 0.58262 | 6.8262 | 1.8194 | 1.7291 | 2.0971 | 2.4683 | 5.6457 | 3.9165 | 7.4089 | 9.138 | 14.7836 | 18.7002 | 0
6.9663 | 8.2094 | 2.0322 | 2.0483 | 3.161 | 3.0966 | 7.2416 | 5.1933 | 15.1756 | 17.2239 | 24.4655 | 29.6587 | 6.9663 | 8.2094 | 2.0322 | 2.0483 | 3.161 | 3.1066 | 7.2416 | 5.1933 | 15.1756 | 17.2239 | 24.4655 | 29.6587 | 0
8.3163 | 8.5019 | 2.0772 | 2.1158 | 3.386 | 3.2316 | 7.5791 | 5.4633 | 16.8181 | 18.9339 | 26.513 | 31.9762 | 8.3163 | 8.5019 | 2.0772 | 2.1158 | 3.386 | 3.2416 | 7.5791 | 5.4633 | 16.8181 | 18.9339 | 26.513 | 31.9762 | 0
-4.5469 | 5.7148 | 1.6484 | 1.4727 | 1.2422 | 1.9453 | 4.3633 | 2.8906 | 1.1679 | 2.6406 | 7.0038 | 9.8944 | -4.5469 | 5.7148 | 1.6484 | 1.4727 | 1.2422 | 1.9553 | 4.3633 | 2.8906 | 1.1679 | 2.6406 | 7.0038 | 9.8944 | 0
-7.9943 | 4.9679 | 1.5335 | 1.3003 | 0.66762 | 1.6006 | 3.5014 | 2.2011 | -3.0264 | -1.7261 | 1.7753 | 3.9765 | -7.9943 | 4.9679 | 1.5335 | 1.3003 | 0.66762 | 1.6106 | 3.5014 | 2.2011 | -3.0264 | -1.7261 | 1.7753 | 3.9765 | 0
4.1948 | 7.6089 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5487 | 4.639 | 11.8036 | 13.7134 | 20.2621 | 24.901 | 4.1948 | 7.6089 | 1.9398 | 1.9097 | 2.6991 | 2.8295 | 6.5487 | 4.639 | 11.8036 | 13.7134 | 20.2621 | 24.901 | 0
0.29908 | 6.7648 | 1.81 | 1.715 | 2.0498 | 2.4299 | 5.5748 | 3.8598 | 7.0639 | 8.7788 | 14.3536 | 18.2134 | 0.29908 | 6.7648 | 1.81 | 1.715 | 2.0498 | 2.4399 | 5.5748 | 3.8598 | 7.0639 | 8.7788 | 14.3536 | 18.2134 | 0
2.5167 | 7.2453 | 1.8839 | 1.8258 | 2.4194 | 2.6517 | 6.1292 | 4.3033 | 9.762 | 11.5878 | 17.717 | 22.0203 | 2.5167 | 7.2453 | 1.8839 | 1.8258 | 2.4194 | 2.6617 | 6.1292 | 4.3033 | 9.762 | 11.5878 | 17.717 | 22.0203 | 0
14.5896 | 9.8611 | 2.2863 | 2.4295 | 4.4316 | 3.859 | 9.1474 | 6.7179 | 24.4507 | 26.8802 | 36.0276 | 42.7455 | 14.5896 | 9.8611 | 2.2863 | 2.4295 | 4.4316 | 3.869 | 9.1474 | 6.7179 | 24.4507 | 26.8802 | 36.0276 | 42.7455 | 0
5.9257 | 7.9839 | 1.9975 | 1.9963 | 2.9876 | 2.9926 | 6.9814 | 4.9851 | 13.9095 | 15.9058 | 22.8872 | 27.8724 | 5.9257 | 7.9839 | 1.9975 | 1.9963 | 2.9876 | 3.0026 | 6.9814 | 4.9851 | 13.9095 | 15.9058 | 22.8872 | 27.8724 | 0
4.8036 | 7.7408 | 1.9601 | 1.9402 | 2.8006 | 2.8804 | 6.7009 | 4.7607 | 12.5443 | 14.4845 | 21.1854 | 25.9461 | 4.8036 | 7.7408 | 1.9601 | 1.9402 | 2.8006 | 2.8904 | 6.7009 | 4.7607 | 12.5443 | 14.4845 | 21.1854 | 25.9461 | 0
2.8171 | 7.3104 | 1.8939 | 1.8409 | 2.4695 | 2.6817 | 6.2043 | 4.3634 | 10.1275 | 11.9683 | 18.1726 | 22.536 | 2.8171 | 7.3104 | 1.8939 | 1.8409 | 2.4695 | 2.6917 | 6.2043 | 4.3634 | 10.1275 | 11.9683 | 18.1726 | 22.536 | 0
7.7332 | 8.3755 | 2.0578 | 2.0867 | 3.2889 | 3.1733 | 7.4333 | 5.3466 | 16.1088 | 18.1954 | 25.6287 | 30.9754 | 7.7332 | 8.3755 | 2.0578 | 2.0867 | 3.2889 | 3.1833 | 7.4333 | 5.3466 | 16.1088 | 18.1954 | 25.6287 | 30.9754 | 0
10.7305 | 9.0249 | 2.1577 | 2.2365 | 3.7884 | 3.473 | 8.1826 | 5.9461 | 19.7554 | 21.9919 | 30.1745 | 36.1206 | 10.7305 | 9.0249 | 2.1577 | 2.2365 | 3.7884 | 3.483 | 8.1826 | 5.9461 | 19.7554 | 21.9919 | 30.1745 | 36.1206 | 0
8.4966 | 8.5409 | 2.0832 | 2.1248 | 3.4161 | 3.2497 | 7.6242 | 5.4993 | 17.0375 | 19.1624 | 26.7865 | 32.2858 | 8.4966 | 8.5409 | 2.0832 | 2.1248 | 3.4161 | 3.2597 | 7.6242 | 5.4993 | 17.0375 | 19.1624 | 26.7865 | 32.2858 | 0
-8.2772 | 4.9066 | 1.5241 | 1.2861 | 0.62047 | 1.5723 | 3.4307 | 2.1446 | -3.3706 | -2.0844 | 1.3463 | 3.4908 | -8.2772 | 4.9066 | 1.5241 | 1.2861 | 0.62047 | 1.5823 | 3.4307 | 2.1446 | -3.3706 | -2.0844 | 1.3463 | 3.4908 | 0
8.6945 | 8.5838 | 2.0898 | 2.1347 | 3.4491 | 3.2695 | 7.6736 | 5.5389 | 17.2783 | 19.413 | 27.0867 | 32.6256 | 8.6945 | 8.5838 | 2.0898 | 2.1347 | 3.4491 | 3.2795 | 7.6736 | 5.5389 | 17.2783 | 19.413 | 27.0867 | 32.6256 | 0
4.4416 | 7.6624 | 1.9481 | 1.9221 | 2.7403 | 2.8442 | 6.6104 | 4.6883 | 12.104 | 14.0261 | 20.6365 | 25.3248 | 4.4416 | 7.6624 | 1.9481 | 1.9221 | 2.7403 | 2.8542 | 6.6104 | 4.6883 | 12.104 | 14.0261 | 20.6365 | 25.3248 | 0
4.5166 | 7.6786 | 1.9506 | 1.9258 | 2.7528 | 2.8517 | 6.6292 | 4.7033 | 12.1953 | 14.1211 | 20.7502 | 25.4536 | 4.5166 | 7.6786 | 1.9506 | 1.9258 | 2.7528 | 2.8617 | 6.6292 | 4.7033 | 12.1953 | 14.1211 | 20.7502 | 25.4536 | 0
7.1372 | 8.2464 | 2.0379 | 2.0569 | 3.1895 | 3.1137 | 7.2843 | 5.2274 | 15.3835 | 17.4404 | 24.7247 | 29.9521 | 7.1372 | 8.2464 | 2.0379 | 2.0569 | 3.1895 | 3.1237 | 7.2843 | 5.2274 | 15.3835 | 17.4404 | 24.7247 | 29.9521 | 0
9.3226 | 8.7199 | 2.1108 | 2.1661 | 3.5538 | 3.3323 | 7.8307 | 5.6645 | 18.0425 | 20.2087 | 28.0393 | 33.7039 | 9.3226 | 8.7199 | 2.1108 | 2.1661 | 3.5538 | 3.3423 | 7.8307 | 5.6645 | 18.0425 | 20.2087 | 28.0393 | 33.7039 | 0
1.1275 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7819 | 4.0255 | 8.0717 | 9.8281 | 15.61 | 19.6355 | 1.1275 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5227 | 5.7819 | 4.0255 | 8.0717 | 9.8281 | 15.61 | 19.6355 | 0
-2.6418 | 6.1276 | 1.7119 | 1.5679 | 1.5597 | 2.1358 | 4.8395 | 3.2716 | 3.4858 | 5.0537 | 9.8932 | 13.1649 | -2.6418 | 6.1276 | 1.7119 | 1.5679 | 1.5597 | 2.1458 | 4.8395 | 3.2716 | 3.4858 | 5.0537 | 9.8932 | 13.1649 | 0
9.0604 | 8.6631 | 2.102 | 2.153 | 3.5101 | 3.306 | 7.7651 | 5.6121 | 17.7234 | 19.8765 | 27.6415 | 33.2536 | 9.0604 | 8.6631 | 2.102 | 2.153 | 3.5101 | 3.316 | 7.7651 | 5.6121 | 17.7234 | 19.8765 | 27.6415 | 33.2536 | 0
10.6866 | 9.0154 | 2.1562 | 2.2343 | 3.7811 | 3.4687 | 8.1717 | 5.9373 | 19.7021 | 21.9364 | 30.1081 | 36.0454 | 10.6866 | 9.0154 | 2.1562 | 2.2343 | 3.7811 | 3.4787 | 8.1717 | 5.9373 | 19.7021 | 21.9364 | 30.1081 | 36.0454 | 0
8.5379 | 8.5499 | 2.0846 | 2.1269 | 3.423 | 3.2538 | 7.6345 | 5.5076 | 17.0878 | 19.2146 | 26.8491 | 32.3567 | 8.5379 | 8.5499 | 2.0846 | 2.1269 | 3.423 | 3.2638 | 7.6345 | 5.5076 | 17.0878 | 19.2146 | 26.8491 | 32.3567 | 0
1.8028 | 7.0906 | 1.8601 | 1.7901 | 2.3005 | 2.5803 | 5.9507 | 4.1606 | 8.8935 | 10.6836 | 16.6343 | 20.7949 | 1.8028 | 7.0906 | 1.8601 | 1.7901 | 2.3005 | 2.5903 | 5.9507 | 4.1606 | 8.8935 | 10.6836 | 16.6343 | 20.7949 | 0
0.2989 | 6.7648 | 1.81 | 1.7149 | 2.0498 | 2.4299 | 5.5747 | 3.8598 | 7.0637 | 8.7786 | 14.3533 | 18.2131 | 0.2989 | 6.7648 | 1.81 | 1.7149 | 2.0498 | 2.4399 | 5.5747 | 3.8598 | 7.0637 | 8.7786 | 14.3533 | 18.2131 | 0
-0.13421 | 6.6709 | 1.7955 | 1.6933 | 1.9776 | 2.3866 | 5.4664 | 3.7732 | 6.5367 | 8.23 | 13.6965 | 17.4696 | -0.13421 | 6.6709 | 1.7955 | 1.6933 | 1.9776 | 2.3966 | 5.4664 | 3.7732 | 6.5367 | 8.23 | 13.6965 | 17.4696 | 0
7.0264 | 8.2224 | 2.0342 | 2.0513 | 3.1711 | 3.1026 | 7.2566 | 5.2053 | 15.2488 | 17.3001 | 24.5567 | 29.762 | 7.0264 | 8.2224 | 2.0342 | 2.0513 | 3.1711 | 3.1126 | 7.2566 | 5.2053 | 15.2488 | 17.3001 | 24.5567 | 29.762 | 0
15.9381 | 10.1533 | 2.3313 | 2.4969 | 4.6563 | 3.9938 | 9.4845 | 6.9876 | 26.0913 | 28.5883 | 38.0728 | 45.0604 | 15.9381 | 10.1533 | 2.3313 | 2.4969 | 4.6563 | 4.0038 | 9.4845 | 6.9876 | 26.0913 | 28.5883 | 38.0728 | 45.0604 | 0
4.2657 | 7.6242 | 1.9422 | 1.9133 | 2.711 | 2.8266 | 6.5664 | 4.6531 | 11.89 | 13.8033 | 20.3697 | 25.0229 | 4.2657 | 7.6242 | 1.9422 | 1.9133 | 2.711 | 2.8366 | 6.5664 | 4.6531 | 11.89 | 13.8033 | 20.3697 | 25.0229 | 0
-1.1135 | 6.4587 | 1.7629 | 1.6443 | 1.8144 | 2.2886 | 5.2216 | 3.5773 | 5.3452 | 6.9896 | 12.2112 | 15.7885 | -1.1135 | 6.4587 | 1.7629 | 1.6443 | 1.8144 | 2.2986 | 5.2216 | 3.5773 | 5.3452 | 6.9896 | 12.2112 | 15.7885 | 0
4.8713 | 7.7554 | 1.9624 | 1.9436 | 2.8119 | 2.8871 | 6.7178 | 4.7743 | 12.6267 | 14.5703 | 21.2881 | 26.0624 | 4.8713 | 7.7554 | 1.9624 | 1.9436 | 2.8119 | 2.8971 | 6.7178 | 4.7743 | 12.6267 | 14.5703 | 21.2881 | 26.0624 | 0
7.0446 | 8.2263 | 2.0348 | 2.0522 | 3.1741 | 3.1045 | 7.2612 | 5.2089 | 15.2709 | 17.3232 | 24.5843 | 29.7933 | 7.0446 | 8.2263 | 2.0348 | 2.0522 | 3.1741 | 3.1145 | 7.2612 | 5.2089 | 15.2709 | 17.3232 | 24.5843 | 29.7933 | 0
20.3696 | 11.1134 | 2.479 | 2.7185 | 5.3949 | 4.437 | 10.5924 | 7.8739 | 31.483 | 34.2015 | 44.7939 | 52.6678 | 20.3696 | 11.1134 | 2.479 | 2.7185 | 5.3949 | 4.447 | 10.5924 | 7.8739 | 31.483 | 34.2015 | 44.7939 | 52.6678 | 0
2.9926 | 7.3484 | 1.8998 | 1.8496 | 2.4988 | 2.6993 | 6.2482 | 4.3985 | 10.341 | 12.1907 | 18.4388 | 22.8374 | 2.9926 | 7.3484 | 1.8998 | 1.8496 | 2.4988 | 2.7093 | 6.2482 | 4.3985 | 10.341 | 12.1907 | 18.4388 | 22.8374 | 0
3.3625 | 7.4285 | 1.9121 | 1.8681 | 2.5604 | 2.7362 | 6.3406 | 4.4725 | 10.791 | 12.6591 | 18.9998 | 23.4723 | 3.3625 | 7.4285 | 1.9121 | 1.8681 | 2.5604 | 2.7462 | 6.3406 | 4.4725 | 10.791 | 12.6591 | 18.9998 | 23.4723 | 0
2.8398 | 7.3153 | 1.8947 | 1.842 | 2.4733 | 2.684 | 6.21 | 4.368 | 10.1551 | 11.9971 | 18.207 | 22.575 | 2.8398 | 7.3153 | 1.8947 | 1.842 | 2.4733 | 2.694 | 6.21 | 4.368 | 10.1551 | 11.9971 | 18.207 | 22.575 | 0
8.605 | 8.5644 | 2.0868 | 2.1302 | 3.4342 | 3.2605 | 7.6512 | 5.521 | 17.1694 | 19.2996 | 26.9509 | 32.4719 | 8.605 | 8.5644 | 2.0868 | 2.1302 | 3.4342 | 3.2705 | 7.6512 | 5.521 | 17.1694 | 19.2996 | 26.9509 | 32.4719 | 0
8.192 | 8.4749 | 2.0731 | 2.1096 | 3.3653 | 3.2192 | 7.548 | 5.4384 | 16.6669 | 18.7765 | 26.3245 | 31.7629 | 8.192 | 8.4749 | 2.0731 | 2.1096 | 3.3653 | 3.2292 | 7.548 | 5.4384 | 16.6669 | 18.7765 | 26.3245 | 31.7629 | 0
8.0575 | 8.4458 | 2.0686 | 2.1029 | 3.3429 | 3.2057 | 7.5144 | 5.4115 | 16.5033 | 18.6062 | 26.1205 | 31.532 | 8.0575 | 8.4458 | 2.0686 | 2.1029 | 3.3429 | 3.2157 | 7.5144 | 5.4115 | 16.5033 | 18.6062 | 26.1205 | 31.532 | 0
5.6798 | 7.9306 | 1.9893 | 1.984 | 2.9466 | 2.968 | 6.92 | 4.936 | 13.6104 | 15.5944 | 22.5144 | 27.4503 | 5.6798 | 7.9306 | 1.9893 | 1.984 | 2.9466 | 2.978 | 6.92 | 4.936 | 13.6104 | 15.5944 | 22.5144 | 27.4503 | 0
12.1633 | 9.3354 | 2.2054 | 2.3082 | 4.0272 | 3.6163 | 8.5408 | 6.2327 | 21.4987 | 23.8069 | 32.3477 | 38.5804 | 12.1633 | 9.3354 | 2.2054 | 2.3082 | 4.0272 | 3.6263 | 8.5408 | 6.2327 | 21.4987 | 23.8069 | 32.3477 | 38.5804 | 0
8.89 | 8.6262 | 2.0963 | 2.1445 | 3.4817 | 3.289 | 7.7225 | 5.578 | 17.5161 | 19.6606 | 27.3831 | 32.9611 | 8.89 | 8.6262 | 2.0963 | 2.1445 | 3.4817 | 3.299 | 7.7225 | 5.578 | 17.5161 | 19.6606 | 27.3831 | 32.9611 | 0
4.5152 | 7.6783 | 1.9505 | 1.9258 | 2.7525 | 2.8515 | 6.6288 | 4.703 | 12.1935 | 14.1192 | 20.748 | 25.451 | 4.5152 | 7.6783 | 1.9505 | 1.9258 | 2.7525 | 2.8615 | 6.6288 | 4.703 | 12.1935 | 14.1192 | 20.748 | 25.451 | 0
17.5746 | 10.5078 | 2.3858 | 2.5787 | 4.9291 | 4.1575 | 9.8937 | 7.3149 | 28.0824 | 30.6612 | 40.5548 | 47.8697 | 17.5746 | 10.5078 | 2.3858 | 2.5787 | 4.9291 | 4.1675 | 9.8937 | 7.3149 | 28.0824 | 30.6612 | 40.5548 | 47.8697 | 0
7.2511 | 8.2711 | 2.0417 | 2.0626 | 3.2085 | 3.1251 | 7.3128 | 5.2502 | 15.5222 | 17.5848 | 24.8976 | 30.1478 | 7.2511 | 8.2711 | 2.0417 | 2.0626 | 3.2085 | 3.1351 | 7.3128 | 5.2502 | 15.5222 | 17.5848 | 24.8976 | 30.1478 | 0
7.1645 | 8.2523 | 2.0388 | 2.0582 | 3.1941 | 3.1164 | 7.2911 | 5.2329 | 15.4168 | 17.475 | 24.7661 | 29.999 | 7.1645 | 8.2523 | 2.0388 | 2.0582 | 3.1941 | 3.1264 | 7.2911 | 5.2329 | 15.4168 | 17.475 | 24.7661 | 29.999 | 0
8.9096 | 8.6304 | 2.097 | 2.1455 | 3.4849 | 3.291 | 7.7274 | 5.5819 | 17.54 | 19.6855 | 27.4129 | 32.9948 | 8.9096 | 8.6304 | 2.097 | 2.1455 | 3.4849 | 3.301 | 7.7274 | 5.5819 | 17.54 | 19.6855 | 27.4129 | 32.9948 | 0
13.8753 | 9.7063 | 2.2625 | 2.3938 | 4.3126 | 3.7875 | 8.9688 | 6.5751 | 23.5816 | 25.9754 | 34.9442 | 41.5193 | 13.8753 | 9.7063 | 2.2625 | 2.3938 | 4.3126 | 3.7975 | 8.9688 | 6.5751 | 23.5816 | 25.9754 | 34.9442 | 41.5193 | 0
14.9444 | 9.938 | 2.2981 | 2.4472 | 4.4907 | 3.8944 | 9.2361 | 6.7889 | 24.8824 | 27.3296 | 36.5657 | 43.3546 | 14.9444 | 9.938 | 2.2981 | 2.4472 | 4.4907 | 3.9044 | 9.2361 | 6.7889 | 24.8824 | 27.3296 | 36.5657 | 43.3546 | 0
12.6497 | 9.4408 | 2.2217 | 2.3325 | 4.1083 | 3.665 | 8.6624 | 6.3299 | 22.0904 | 24.4229 | 33.0853 | 39.4153 | 12.6497 | 9.4408 | 2.2217 | 2.3325 | 4.1083 | 3.675 | 8.6624 | 6.3299 | 22.0904 | 24.4229 | 33.0853 | 39.4153 | 0
-5.3839 | 5.5335 | 1.6205 | 1.4308 | 1.1027 | 1.8616 | 4.154 | 2.7232 | 0.14953 | 1.5803 | 5.7343 | 8.4576 | -5.3839 | 5.5335 | 1.6205 | 1.4308 | 1.1027 | 1.8716 | 4.154 | 2.7232 | 0.14953 | 1.5803 | 5.7343 | 8.4576 | 0
7.415 | 8.3066 | 2.0472 | 2.0707 | 3.2358 | 3.1415 | 7.3537 | 5.283 | 15.7215 | 17.7923 | 25.146 | 30.429 | 7.415 | 8.3066 | 2.0472 | 2.0707 | 3.2358 | 3.1515 | 7.3537 | 5.283 | 15.7215 | 17.7923 | 25.146 | 30.429 | 0
0.75401 | 6.8634 | 1.8251 | 1.7377 | 2.1257 | 2.4754 | 5.6885 | 3.9508 | 7.6174 | 9.3551 | 15.0436 | 18.9944 | 0.75401 | 6.8634 | 1.8251 | 1.7377 | 2.1257 | 2.4854 | 5.6885 | 3.9508 | 7.6174 | 9.3551 | 15.0436 | 18.9944 | 0
7.6785 | 8.3637 | 2.0559 | 2.0839 | 3.2797 | 3.1678 | 7.4196 | 5.3357 | 16.0421 | 18.1261 | 25.5457 | 30.8814 | 7.6785 | 8.3637 | 2.0559 | 2.0839 | 3.2797 | 3.1778 | 7.4196 | 5.3357 | 16.0421 | 18.1261 | 25.5457 | 30.8814 | 0
-6.7356 | 5.2406 | 1.5755 | 1.3632 | 0.8774 | 1.7264 | 3.8161 | 2.4529 | -1.495 | -0.13174 | 3.6844 | 6.1373 | -6.7356 | 5.2406 | 1.5755 | 1.3632 | 0.8774 | 1.7364 | 3.8161 | 2.4529 | -1.495 | -0.13174 | 3.6844 | 6.1373 | 0
15.0729 | 9.9658 | 2.3024 | 2.4536 | 4.5121 | 3.9073 | 9.2682 | 6.8146 | 25.0387 | 27.4923 | 36.7606 | 43.5751 | 15.0729 | 9.9658 | 2.3024 | 2.4536 | 4.5121 | 3.9173 | 9.2682 | 6.8146 | 25.0387 | 27.4923 | 36.7606 | 43.5751 | 0
4.1628 | 7.6019 | 1.9388 | 1.9081 | 2.6938 | 2.8163 | 6.5407 | 4.6326 | 11.7648 | 13.6729 | 20.2136 | 24.8462 | 4.1628 | 7.6019 | 1.9388 | 1.9081 | 2.6938 | 2.8263 | 6.5407 | 4.6326 | 11.7648 | 13.6729 | 20.2136 | 24.8462 | 0
-1.8279 | 6.304 | 1.7391 | 1.6086 | 1.6954 | 2.2172 | 5.043 | 3.4344 | 4.4761 | 6.0847 | 11.1277 | 14.5622 | -1.8279 | 6.304 | 1.7391 | 1.6086 | 1.6954 | 2.2272 | 5.043 | 3.4344 | 4.4761 | 6.0847 | 11.1277 | 14.5622 | 0
7.3349 | 8.2892 | 2.0445 | 2.0667 | 3.2225 | 3.1335 | 7.3337 | 5.267 | 15.6242 | 17.6909 | 25.0246 | 30.2916 | 7.3349 | 8.2892 | 2.0445 | 2.0667 | 3.2225 | 3.1435 | 7.3337 | 5.267 | 15.6242 | 17.6909 | 25.0246 | 30.2916 | 0
-2.9217 | 6.067 | 1.7026 | 1.5539 | 1.5131 | 2.1078 | 4.7696 | 3.2157 | 3.1453 | 4.6992 | 9.4688 | 12.6845 | -2.9217 | 6.067 | 1.7026 | 1.5539 | 1.5131 | 2.1178 | 4.7696 | 3.2157 | 3.1453 | 4.6992 | 9.4688 | 12.6845 | 0
6.4196 | 8.0909 | 2.014 | 2.021 | 3.0699 | 3.042 | 7.1049 | 5.0839 | 14.5106 | 16.5315 | 23.6364 | 28.7204 | 6.4196 | 8.0909 | 2.014 | 2.021 | 3.0699 | 3.052 | 7.1049 | 5.0839 | 14.5106 | 16.5315 | 23.6364 | 28.7204 | 0
-3.1568 | 6.016 | 1.6948 | 1.5422 | 1.4739 | 2.0843 | 4.7108 | 3.1686 | 2.8592 | 4.4013 | 9.1121 | 12.2807 | -3.1568 | 6.016 | 1.6948 | 1.5422 | 1.4739 | 2.0943 | 4.7108 | 3.1686 | 2.8592 | 4.4013 | 9.1121 | 12.2807 | 0
-5.5235 | 5.5032 | 1.6159 | 1.4238 | 1.0794 | 1.8476 | 4.1191 | 2.6953 | -0.0203 | 1.4035 | 5.5226 | 8.2179 | -5.5235 | 5.5032 | 1.6159 | 1.4238 | 1.0794 | 1.8576 | 4.1191 | 2.6953 | -0.0203 | 1.4035 | 5.5226 | 8.2179 | 0
4.1099 | 7.5905 | 1.937 | 1.9055 | 2.685 | 2.811 | 6.5275 | 4.622 | 11.7004 | 13.6058 | 20.1333 | 24.7553 | 4.1099 | 7.5905 | 1.937 | 1.9055 | 2.685 | 2.821 | 6.5275 | 4.622 | 11.7004 | 13.6058 | 20.1333 | 24.7553 | 0
9.1846 | 8.69 | 2.1062 | 2.1592 | 3.5308 | 3.3185 | 7.7962 | 5.6369 | 17.8746 | 20.0339 | 27.83 | 33.4669 | 9.1846 | 8.69 | 2.1062 | 2.1592 | 3.5308 | 3.3285 | 7.7962 | 5.6369 | 17.8746 | 20.0339 | 27.83 | 33.4669 | 0
-3.3156 | 5.9816 | 1.6895 | 1.5342 | 1.4474 | 2.0684 | 4.6711 | 3.1369 | 2.666 | 4.2003 | 8.8714 | 12.0082 | -3.3156 | 5.9816 | 1.6895 | 1.5342 | 1.4474 | 2.0784 | 4.6711 | 3.1369 | 2.666 | 4.2003 | 8.8714 | 12.0082 | 0
10.6419 | 9.0057 | 2.1547 | 2.2321 | 3.7737 | 3.4642 | 8.1605 | 5.9284 | 19.6477 | 21.8798 | 30.0402 | 35.9686 | 10.6419 | 9.0057 | 2.1547 | 2.2321 | 3.7737 | 3.4742 | 8.1605 | 5.9284 | 19.6477 | 21.8798 | 30.0402 | 35.9686 | 0
9.4293 | 8.743 | 2.1143 | 2.1715 | 3.5716 | 3.3429 | 7.8573 | 5.6859 | 18.1724 | 20.3438 | 28.2012 | 33.8871 | 9.4293 | 8.743 | 2.1143 | 2.1715 | 3.5716 | 3.3529 | 7.8573 | 5.6859 | 18.1724 | 20.3438 | 28.2012 | 33.8871 | 0
24.2891 | 11.9626 | 2.6096 | 2.9145 | 6.0482 | 4.8289 | 11.5723 | 8.6578 | 36.2518 | 39.1662 | 50.7385 | 59.3964 | 24.2891 | 11.9626 | 2.6096 | 2.9145 | 6.0482 | 4.8389 | 11.5723 | 8.6578 | 36.2518 | 39.1662 | 50.7385 | 59.3964 | 0
8.2951 | 8.4973 | 2.0765 | 2.1148 | 3.3825 | 3.2295 | 7.5738 | 5.459 | 16.7923 | 18.9071 | 26.4808 | 31.9398 | 8.2951 | 8.4973 | 2.0765 | 2.1148 | 3.3825 | 3.2395 | 7.5738 | 5.459 | 16.7923 | 18.9071 | 26.4808 | 31.9398 | 0
-5.1847 | 5.5767 | 1.6272 | 1.4408 | 1.1359 | 1.8815 | 4.2038 | 2.7631 | 0.392 | 1.8328 | 6.0366 | 8.7997 | -5.1847 | 5.5767 | 1.6272 | 1.4408 | 1.1359 | 1.8915 | 4.2038 | 2.7631 | 0.392 | 1.8328 | 6.0366 | 8.7997 | 0
7.4308 | 8.31 | 2.0477 | 2.0715 | 3.2385 | 3.1431 | 7.3577 | 5.2862 | 15.7408 | 17.8123 | 25.17 | 30.4562 | 7.4308 | 8.31 | 2.0477 | 2.0715 | 3.2385 | 3.1531 | 7.3577 | 5.2862 | 15.7408 | 17.8123 | 25.17 | 30.4562 | 0
3.9805 | 7.5624 | 1.9327 | 1.899 | 2.6634 | 2.798 | 6.4951 | 4.5961 | 11.5429 | 13.4419 | 19.937 | 24.5331 | 3.9805 | 7.5624 | 1.9327 | 1.899 | 2.6634 | 2.808 | 6.4951 | 4.5961 | 11.5429 | 13.4419 | 19.937 | 24.5331 | 0
6.9627 | 8.2086 | 2.0321 | 2.0481 | 3.1605 | 3.0963 | 7.2407 | 5.1925 | 15.1713 | 17.2195 | 24.4602 | 29.6527 | 6.9627 | 8.2086 | 2.0321 | 2.0481 | 3.1605 | 3.1063 | 7.2407 | 5.1925 | 15.1713 | 17.2195 | 24.4602 | 29.6527 | 0
10.5847 | 8.9933 | 2.1528 | 2.2292 | 3.7641 | 3.4585 | 8.1462 | 5.9169 | 19.578 | 21.8073 | 29.9534 | 35.8704 | 10.5847 | 8.9933 | 2.1528 | 2.2292 | 3.7641 | 3.4685 | 8.1462 | 5.9169 | 19.578 | 21.8073 | 29.9534 | 35.8704 | 0
-1.1576 | 6.4492 | 1.7614 | 1.6421 | 1.8071 | 2.2842 | 5.2106 | 3.5685 | 5.2915 | 6.9337 | 12.1443 | 15.7127 | -1.1576 | 6.4492 | 1.7614 | 1.6421 | 1.8071 | 2.2942 | 5.2106 | 3.5685 | 5.2915 | 6.9337 | 12.1443 | 15.7127 | 0
-1.1256 | 6.4561 | 1.7625 | 1.6437 | 1.8124 | 2.2874 | 5.2186 | 3.5749 | 5.3305 | 6.9742 | 12.1928 | 15.7677 | -1.1256 | 6.4561 | 1.7625 | 1.6437 | 1.8124 | 2.2974 | 5.2186 | 3.5749 | 5.3305 | 6.9742 | 12.1928 | 15.7677 | 0
10.0004 | 8.8667 | 2.1333 | 2.2 | 3.6667 | 3.4 | 8.0001 | 5.8001 | 18.8671 | 21.0671 | 29.0672 | 34.8673 | 10.0004 | 8.8667 | 2.1333 | 2.2 | 3.6667 | 3.41 | 8.0001 | 5.8001 | 18.8671 | 21.0671 | 29.0672 | 34.8673 | 0
8.9462 | 8.6383 | 2.0982 | 2.1473 | 3.491 | 3.2946 | 7.7366 | 5.5892 | 17.5845 | 19.7319 | 27.4684 | 33.0576 | 8.9462 | 8.6383 | 2.0982 | 2.1473 | 3.491 | 3.3046 | 7.7366 | 5.5892 | 17.5845 | 19.7319 | 27.4684 | 33.0576 | 0
1.749 | 7.0789 | 1.8583 | 1.7874 | 2.2915 | 2.5749 | 5.9372 | 4.1498 | 8.8279 | 10.6153 | 16.5526 | 20.7024 | 1.749 | 7.0789 | 1.8583 | 1.7874 | 2.2915 | 2.5849 | 5.9372 | 4.1498 | 8.8279 | 10.6153 | 16.5526 | 20.7024 | 0
0.17321 | 6.7375 | 1.8058 | 1.7087 | 2.0289 | 2.4173 | 5.5433 | 3.8346 | 6.9107 | 8.6194 | 14.1627 | 17.9973 | 0.17321 | 6.7375 | 1.8058 | 1.7087 | 2.0289 | 2.4273 | 5.5433 | 3.8346 | 6.9107 | 8.6194 | 14.1627 | 17.9973 | 0
7.8213 | 8.3946 | 2.0607 | 2.0911 | 3.3035 | 3.1821 | 7.4553 | 5.3643 | 16.2159 | 18.3069 | 25.7622 | 31.1265 | 7.8213 | 8.3946 | 2.0607 | 2.0911 | 3.3035 | 3.1921 | 7.4553 | 5.3643 | 16.2159 | 18.3069 | 25.7622 | 31.1265 | 0
15.1106 | 9.974 | 2.3037 | 2.4555 | 4.5184 | 3.9111 | 9.2777 | 6.8221 | 25.0846 | 27.5401 | 36.8178 | 43.6399 | 15.1106 | 9.974 | 2.3037 | 2.4555 | 4.5184 | 3.9211 | 9.2777 | 6.8221 | 25.0846 | 27.5401 | 36.8178 | 43.6399 | 0
10.1426 | 8.8976 | 2.1381 | 2.2071 | 3.6904 | 3.4143 | 8.0357 | 5.8285 | 19.0402 | 21.2473 | 29.283 | 35.1115 | 10.1426 | 8.8976 | 2.1381 | 2.2071 | 3.6904 | 3.4243 | 8.0357 | 5.8285 | 19.0402 | 21.2473 | 29.283 | 35.1115 | 0
16.8847 | 10.3583 | 2.3628 | 2.5442 | 4.8141 | 4.0885 | 9.7212 | 7.1769 | 27.243 | 29.7873 | 39.5084 | 46.6854 | 16.8847 | 10.3583 | 2.3628 | 2.5442 | 4.8141 | 4.0985 | 9.7212 | 7.1769 | 27.243 | 29.7873 | 39.5084 | 46.6854 | 0
7.7903 | 8.3879 | 2.0597 | 2.0895 | 3.2984 | 3.179 | 7.4476 | 5.3581 | 16.1782 | 18.2677 | 25.7153 | 31.0734 | 7.7903 | 8.3879 | 2.0597 | 2.0895 | 3.2984 | 3.189 | 7.4476 | 5.3581 | 16.1782 | 18.2677 | 25.7153 | 31.0734 | 0
13.5503 | 9.6359 | 2.2517 | 2.3775 | 4.2584 | 3.755 | 8.8876 | 6.5101 | 23.1862 | 25.5637 | 34.4513 | 40.9613 | 13.5503 | 9.6359 | 2.2517 | 2.3775 | 4.2584 | 3.765 | 8.8876 | 6.5101 | 23.1862 | 25.5637 | 34.4513 | 40.9613 | 0
15.0013 | 9.9503 | 2.3 | 2.4501 | 4.5002 | 3.9001 | 9.2503 | 6.8003 | 24.9515 | 27.4016 | 36.6519 | 43.4522 | 15.0013 | 9.9503 | 2.3 | 2.4501 | 4.5002 | 3.9101 | 9.2503 | 6.8003 | 24.9515 | 27.4016 | 36.6519 | 43.4522 | 0
7.9384 | 8.42 | 2.0646 | 2.0969 | 3.3231 | 3.1938 | 7.4846 | 5.3877 | 16.3584 | 18.4553 | 25.9399 | 31.3276 | 7.9384 | 8.42 | 2.0646 | 2.0969 | 3.3231 | 3.2038 | 7.4846 | 5.3877 | 16.3584 | 18.4553 | 25.9399 | 31.3276 | 0
6.8871 | 8.1922 | 2.0296 | 2.0444 | 3.1479 | 3.0887 | 7.2218 | 5.1774 | 15.0793 | 17.1237 | 24.3455 | 29.5229 | 6.8871 | 8.1922 | 2.0296 | 2.0444 | 3.1479 | 3.0987 | 7.2218 | 5.1774 | 15.0793 | 17.1237 | 24.3455 | 29.5229 | 0
1.9661 | 7.126 | 1.8655 | 1.7983 | 2.3277 | 2.5966 | 5.9915 | 4.1932 | 9.0921 | 10.8904 | 16.8819 | 21.0751 | 1.9661 | 7.126 | 1.8655 | 1.7983 | 2.3277 | 2.6066 | 5.9915 | 4.1932 | 9.0921 | 10.8904 | 16.8819 | 21.0751 | 0
3.4524 | 7.448 | 1.9151 | 1.8726 | 2.5754 | 2.7452 | 6.3631 | 4.4905 | 10.9004 | 12.773 | 19.1361 | 23.6266 | 3.4524 | 7.448 | 1.9151 | 1.8726 | 2.5754 | 2.7552 | 6.3631 | 4.4905 | 10.9004 | 12.773 | 19.1361 | 23.6266 | 0
11.6679 | 9.228 | 2.1889 | 2.2834 | 3.9446 | 3.5668 | 8.417 | 6.1336 | 20.8959 | 23.1793 | 31.5963 | 37.7298 | 11.6679 | 9.228 | 2.1889 | 2.2834 | 3.9446 | 3.5768 | 8.417 | 6.1336 | 20.8959 | 23.1793 | 31.5963 | 37.7298 | 0
-0.70544 | 6.5472 | 1.7765 | 1.6647 | 1.8824 | 2.3295 | 5.3236 | 3.6589 | 5.8417 | 7.5064 | 12.8301 | 16.489 | -0.70544 | 6.5472 | 1.7765 | 1.6647 | 1.8824 | 2.3395 | 5.3236 | 3.6589 | 5.8417 | 7.5064 | 12.8301 | 16.489 | 0
4.6741 | 7.7127 | 1.9558 | 1.9337 | 2.779 | 2.8674 | 6.6685 | 4.7348 | 12.3868 | 14.3205 | 20.989 | 25.7238 | 4.6741 | 7.7127 | 1.9558 | 1.9337 | 2.779 | 2.8774 | 6.6685 | 4.7348 | 12.3868 | 14.3205 | 20.989 | 25.7238 | 0
10.26 | 8.923 | 2.142 | 2.213 | 3.71 | 3.426 | 8.065 | 5.852 | 19.183 | 21.396 | 29.461 | 35.313 | 10.26 | 8.923 | 2.142 | 2.213 | 3.71 | 3.436 | 8.065 | 5.852 | 19.183 | 21.396 | 29.461 | 35.313 | 0
7.416 | 8.3068 | 2.0472 | 2.0708 | 3.236 | 3.1416 | 7.354 | 5.2832 | 15.7228 | 17.7936 | 25.1476 | 30.4308 | 7.416 | 8.3068 | 2.0472 | 2.0708 | 3.236 | 3.1516 | 7.354 | 5.2832 | 15.7228 | 17.7936 | 25.1476 | 30.4308 | 0
2.6131 | 7.2662 | 1.8871 | 1.8307 | 2.4355 | 2.6613 | 6.1533 | 4.3226 | 9.8793 | 11.71 | 17.8633 | 22.1859 | 2.6131 | 7.2662 | 1.8871 | 1.8307 | 2.4355 | 2.6713 | 6.1533 | 4.3226 | 9.8793 | 11.71 | 17.8633 | 22.1859 | 0
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2044 | 14.1306 | 20.7616 | 25.4664 | 4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8624 | 6.631 | 4.7048 | 12.2044 | 14.1306 | 20.7616 | 25.4664 | 0
9.0177 | 8.6538 | 2.1006 | 2.1509 | 3.5029 | 3.3018 | 7.7544 | 5.6035 | 17.6715 | 19.8224 | 27.5768 | 33.1803 | 9.0177 | 8.6538 | 2.1006 | 2.1509 | 3.5029 | 3.3118 | 7.7544 | 5.6035 | 17.6715 | 19.8224 | 27.5768 | 33.1803 | 0
11.271 | 9.1421 | 2.1757 | 2.2636 | 3.8785 | 3.5271 | 8.3178 | 6.0542 | 20.4131 | 22.6766 | 30.9944 | 37.0486 | 11.271 | 9.1421 | 2.1757 | 2.2636 | 3.8785 | 3.5371 | 8.3178 | 6.0542 | 20.4131 | 22.6766 | 30.9944 | 37.0486 | 0
4.8689 | 7.7549 | 1.9623 | 1.9434 | 2.8115 | 2.8869 | 6.7172 | 4.7738 | 12.6238 | 14.5672 | 21.2844 | 26.0582 | 4.8689 | 7.7549 | 1.9623 | 1.9434 | 2.8115 | 2.8969 | 6.7172 | 4.7738 | 12.6238 | 14.5672 | 21.2844 | 26.0582 | 0
13.7381 | 9.6766 | 2.2579 | 2.3869 | 4.2897 | 3.7738 | 8.9345 | 6.5476 | 23.4147 | 25.8016 | 34.7361 | 41.2837 | 13.7381 | 9.6766 | 2.2579 | 2.3869 | 4.2897 | 3.7838 | 8.9345 | 6.5476 | 23.4147 | 25.8016 | 34.7361 | 41.2837 | 0
-0.14801 | 6.6679 | 1.7951 | 1.6926 | 1.9753 | 2.3852 | 5.463 | 3.7704 | 6.5199 | 8.2125 | 13.6755 | 17.4459 | -0.14801 | 6.6679 | 1.7951 | 1.6926 | 1.9753 | 2.3952 | 5.463 | 3.7704 | 6.5199 | 8.2125 | 13.6755 | 17.4459 | 0
4.9965 | 7.7826 | 1.9666 | 1.9498 | 2.8328 | 2.8997 | 6.7491 | 4.7993 | 12.7791 | 14.7289 | 21.478 | 26.2773 | 4.9965 | 7.7826 | 1.9666 | 1.9498 | 2.8328 | 2.9097 | 6.7491 | 4.7993 | 12.7791 | 14.7289 | 21.478 | 26.2773 | 0
2.9362 | 7.3362 | 1.8979 | 1.8468 | 2.4894 | 2.6936 | 6.234 | 4.3872 | 10.2723 | 12.1191 | 18.3532 | 22.7404 | 2.9362 | 7.3362 | 1.8979 | 1.8468 | 2.4894 | 2.7036 | 6.234 | 4.3872 | 10.2723 | 12.1191 | 18.3532 | 22.7404 | 0
10.8682 | 9.0548 | 2.1623 | 2.2434 | 3.8114 | 3.4868 | 8.2171 | 5.9736 | 19.923 | 22.1664 | 30.3835 | 36.3571 | 10.8682 | 9.0548 | 2.1623 | 2.2434 | 3.8114 | 3.4968 | 8.2171 | 5.9736 | 19.923 | 22.1664 | 30.3835 | 36.3571 | 0
5.3766 | 7.8649 | 1.9792 | 1.9688 | 2.8961 | 2.9377 | 6.8441 | 4.8753 | 13.2415 | 15.2103 | 22.0545 | 26.9298 | 5.3766 | 7.8649 | 1.9792 | 1.9688 | 2.8961 | 2.9477 | 6.8441 | 4.8753 | 13.2415 | 15.2103 | 22.0545 | 26.9298 | 0
-3.2425 | 5.9975 | 1.6919 | 1.5379 | 1.4596 | 2.0758 | 4.6894 | 3.1515 | 2.755 | 4.2928 | 8.9822 | 12.1337 | -3.2425 | 5.9975 | 1.6919 | 1.5379 | 1.4596 | 2.0858 | 4.6894 | 3.1515 | 2.755 | 4.2928 | 8.9822 | 12.1337 | 0
5.784 | 7.9532 | 1.9928 | 1.9892 | 2.964 | 2.9784 | 6.946 | 4.9568 | 13.7372 | 15.7264 | 22.6724 | 27.6292 | 5.784 | 7.9532 | 1.9928 | 1.9892 | 2.964 | 2.9884 | 6.946 | 4.9568 | 13.7372 | 15.7264 | 22.6724 | 27.6292 | 0
0.62392 | 6.8352 | 1.8208 | 1.7312 | 2.104 | 2.4624 | 5.656 | 3.9248 | 7.4591 | 9.1903 | 14.8463 | 18.7711 | 0.62392 | 6.8352 | 1.8208 | 1.7312 | 2.104 | 2.4724 | 5.656 | 3.9248 | 7.4591 | 9.1903 | 14.8463 | 18.7711 | 0
3.8817 | 7.541 | 1.9294 | 1.8941 | 2.6469 | 2.7882 | 6.4704 | 4.5763 | 11.4227 | 13.3168 | 19.7872 | 24.3636 | 3.8817 | 7.541 | 1.9294 | 1.8941 | 2.6469 | 2.7982 | 6.4704 | 4.5763 | 11.4227 | 13.3168 | 19.7872 | 24.3636 | 0
6.7592 | 8.1645 | 2.0253 | 2.038 | 3.1265 | 3.0759 | 7.1898 | 5.1518 | 14.9237 | 16.9617 | 24.1515 | 29.3033 | 6.7592 | 8.1645 | 2.0253 | 2.038 | 3.1265 | 3.0859 | 7.1898 | 5.1518 | 14.9237 | 16.9617 | 24.1515 | 29.3033 | 0
8.4274 | 8.5259 | 2.0809 | 2.1214 | 3.4046 | 3.2427 | 7.6069 | 5.4855 | 16.9534 | 19.0748 | 26.6816 | 32.1671 | 8.4274 | 8.5259 | 2.0809 | 2.1214 | 3.4046 | 3.2527 | 7.6069 | 5.4855 | 16.9534 | 19.0748 | 26.6816 | 32.1671 | 0
16.2512 | 10.2211 | 2.3417 | 2.5126 | 4.7085 | 4.0251 | 9.5628 | 7.0502 | 26.4722 | 28.9848 | 38.5476 | 45.5978 | 16.2512 | 10.2211 | 2.3417 | 2.5126 | 4.7085 | 4.0351 | 9.5628 | 7.0502 | 26.4722 | 28.9848 | 38.5476 | 45.5978 | 0
3.9702 | 7.5602 | 1.9323 | 1.8985 | 2.6617 | 2.797 | 6.4925 | 4.594 | 11.5304 | 13.4289 | 19.9214 | 24.5155 | 3.9702 | 7.5602 | 1.9323 | 1.8985 | 2.6617 | 2.807 | 6.4925 | 4.594 | 11.5304 | 13.4289 | 19.9214 | 24.5155 | 0
9.1031 | 8.6723 | 2.1034 | 2.1552 | 3.5172 | 3.3103 | 7.7758 | 5.6206 | 17.7754 | 19.9305 | 27.7063 | 33.3269 | 9.1031 | 8.6723 | 2.1034 | 2.1552 | 3.5172 | 3.3203 | 7.7758 | 5.6206 | 17.7754 | 19.9305 | 27.7063 | 33.3269 | 0
7.6437 | 8.3561 | 2.0548 | 2.0822 | 3.2739 | 3.1644 | 7.4109 | 5.3287 | 15.9998 | 18.082 | 25.4929 | 30.8217 | 7.6437 | 8.3561 | 2.0548 | 2.0822 | 3.2739 | 3.1744 | 7.4109 | 5.3287 | 15.9998 | 18.082 | 25.4929 | 30.8217 | 0
7.4801 | 8.3207 | 2.0493 | 2.074 | 3.2467 | 3.148 | 7.37 | 5.296 | 15.8008 | 17.8748 | 25.2449 | 30.5409 | 7.4801 | 8.3207 | 2.0493 | 2.074 | 3.2467 | 3.158 | 7.37 | 5.296 | 15.8008 | 17.8748 | 25.2449 | 30.5409 | 0
15.1289 | 9.9779 | 2.3043 | 2.4564 | 4.5215 | 3.9129 | 9.2822 | 6.8258 | 25.1068 | 27.5633 | 36.8455 | 43.6713 | 15.1289 | 9.9779 | 2.3043 | 2.4564 | 4.5215 | 3.9229 | 9.2822 | 6.8258 | 25.1068 | 27.5633 | 36.8455 | 43.6713 | 0
0.75091 | 6.8627 | 1.825 | 1.7375 | 2.1252 | 2.4751 | 5.6877 | 3.9502 | 7.6136 | 9.3512 | 15.0389 | 18.9891 | 0.75091 | 6.8627 | 1.825 | 1.7375 | 2.1252 | 2.4851 | 5.6877 | 3.9502 | 7.6136 | 9.3512 | 15.0389 | 18.9891 | 0
1.9654 | 7.1258 | 1.8655 | 1.7983 | 2.3276 | 2.5965 | 5.9914 | 4.1931 | 9.0912 | 10.8895 | 16.8809 | 21.0739 | 1.9654 | 7.1258 | 1.8655 | 1.7983 | 2.3276 | 2.6065 | 5.9914 | 4.1931 | 9.0912 | 10.8895 | 16.8809 | 21.0739 | 0
9.8869 | 8.8422 | 2.1296 | 2.1943 | 3.6478 | 3.3887 | 7.9717 | 5.7774 | 18.7291 | 20.9234 | 28.8951 | 34.6725 | 9.8869 | 8.8422 | 2.1296 | 2.1943 | 3.6478 | 3.3987 | 7.9717 | 5.7774 | 18.7291 | 20.9234 | 28.8951 | 34.6725 | 0
6.4668 | 8.1011 | 2.0156 | 2.0233 | 3.0778 | 3.0467 | 7.1167 | 5.0934 | 14.5679 | 16.5913 | 23.708 | 28.8013 | 6.4668 | 8.1011 | 2.0156 | 2.0233 | 3.0778 | 3.0567 | 7.1167 | 5.0934 | 14.5679 | 16.5913 | 23.708 | 28.8013 | 0
7.8432 | 8.3994 | 2.0614 | 2.0922 | 3.3072 | 3.1843 | 7.4608 | 5.3686 | 16.2426 | 18.3348 | 25.7956 | 31.1642 | 7.8432 | 8.3994 | 2.0614 | 2.0922 | 3.3072 | 3.1943 | 7.4608 | 5.3686 | 16.2426 | 18.3348 | 25.7956 | 31.1642 | 0
3.9091 | 7.547 | 1.9303 | 1.8955 | 2.6515 | 2.7909 | 6.4773 | 4.5818 | 11.456 | 13.3515 | 19.8288 | 24.4106 | 3.9091 | 7.547 | 1.9303 | 1.8955 | 2.6515 | 2.8009 | 6.4773 | 4.5818 | 11.456 | 13.3515 | 19.8288 | 24.4106 | 0
3.4369 | 7.4447 | 1.9146 | 1.8718 | 2.5728 | 2.7437 | 6.3592 | 4.4874 | 10.8815 | 12.7533 | 19.1126 | 23.5999 | 3.4369 | 7.4447 | 1.9146 | 1.8718 | 2.5728 | 2.7537 | 6.3592 | 4.4874 | 10.8815 | 12.7533 | 19.1126 | 23.5999 | 0
16.7592 | 10.3312 | 2.3586 | 2.538 | 4.7932 | 4.0759 | 9.6898 | 7.1518 | 27.0903 | 29.6283 | 39.3181 | 46.4699 | 16.7592 | 10.3312 | 2.3586 | 2.538 | 4.7932 | 4.0859 | 9.6898 | 7.1518 | 27.0903 | 29.6283 | 39.3181 | 46.4699 | 0
-4.8476 | 5.6497 | 1.6384 | 1.4576 | 1.1921 | 1.9152 | 4.2881 | 2.8305 | 0.80204 | 2.2597 | 6.5478 | 9.3782 | -4.8476 | 5.6497 | 1.6384 | 1.4576 | 1.1921 | 1.9252 | 4.2881 | 2.8305 | 0.80204 | 2.2597 | 6.5478 | 9.3782 | 0
4.8571 | 7.7524 | 1.9619 | 1.9429 | 2.8095 | 2.8857 | 6.7143 | 4.7714 | 12.6094 | 14.5523 | 21.2665 | 26.038 | 4.8571 | 7.7524 | 1.9619 | 1.9429 | 2.8095 | 2.8957 | 6.7143 | 4.7714 | 12.6094 | 14.5523 | 21.2665 | 26.038 | 0
15.5217 | 10.063 | 2.3174 | 2.4761 | 4.587 | 3.9522 | 9.3804 | 6.9043 | 25.5847 | 28.0608 | 37.4412 | 44.3456 | 15.5217 | 10.063 | 2.3174 | 2.4761 | 4.587 | 3.9622 | 9.3804 | 6.9043 | 25.5847 | 28.0608 | 37.4412 | 44.3456 | 0
4.5272 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7054 | 12.2081 | 14.1344 | 20.7662 | 25.4717 | 4.5272 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8627 | 6.6318 | 4.7054 | 12.2081 | 14.1344 | 20.7662 | 25.4717 | 0
-6.9383 | 5.1967 | 1.5687 | 1.3531 | 0.84362 | 1.7062 | 3.7654 | 2.4123 | -1.7415 | -0.38845 | 3.377 | 5.7893 | -6.9383 | 5.1967 | 1.5687 | 1.3531 | 0.84362 | 1.7162 | 3.7654 | 2.4123 | -1.7415 | -0.38845 | 3.377 | 5.7893 | 0
16.9328 | 10.3688 | 2.3644 | 2.5466 | 4.8221 | 4.0933 | 9.7332 | 7.1866 | 27.3016 | 29.8482 | 39.5814 | 46.768 | 16.9328 | 10.3688 | 2.3644 | 2.5466 | 4.8221 | 4.1033 | 9.7332 | 7.1866 | 27.3016 | 29.8482 | 39.5814 | 46.768 | 0
14.0968 | 9.7543 | 2.2699 | 2.4048 | 4.3495 | 3.8097 | 9.0242 | 6.6194 | 23.8511 | 26.2559 | 35.2801 | 41.8995 | 14.0968 | 9.7543 | 2.2699 | 2.4048 | 4.3495 | 3.8197 | 9.0242 | 6.6194 | 23.8511 | 26.2559 | 35.2801 | 41.8995 | 0
21.6875 | 11.399 | 2.5229 | 2.7844 | 5.6146 | 4.5687 | 10.9219 | 8.1375 | 33.0864 | 35.8708 | 46.7927 | 54.9302 | 21.6875 | 11.399 | 2.5229 | 2.7844 | 5.6146 | 4.5787 | 10.9219 | 8.1375 | 33.0864 | 35.8708 | 46.7927 | 54.9302 | 0
14.6441 | 9.8729 | 2.2881 | 2.4322 | 4.4407 | 3.8644 | 9.161 | 6.7288 | 24.5169 | 26.9491 | 36.1102 | 42.839 | 14.6441 | 9.8729 | 2.2881 | 2.4322 | 4.4407 | 3.8744 | 9.161 | 6.7288 | 24.5169 | 26.9491 | 36.1102 | 42.839 | 0
0.7403 | 6.8604 | 1.8247 | 1.737 | 2.1234 | 2.474 | 5.6851 | 3.9481 | 7.6007 | 9.3377 | 15.0228 | 18.9709 | 0.7403 | 6.8604 | 1.8247 | 1.737 | 2.1234 | 2.484 | 5.6851 | 3.9481 | 7.6007 | 9.3377 | 15.0228 | 18.9709 | 0
0.19334 | 6.7419 | 1.8064 | 1.7097 | 2.0322 | 2.4193 | 5.5483 | 3.8387 | 6.9352 | 8.6449 | 14.1932 | 18.0319 | 0.19334 | 6.7419 | 1.8064 | 1.7097 | 2.0322 | 2.4293 | 5.5483 | 3.8387 | 6.9352 | 8.6449 | 14.1932 | 18.0319 | 0
8.7563 | 8.5972 | 2.0919 | 2.1378 | 3.4594 | 3.2756 | 7.6891 | 5.5513 | 17.3534 | 19.4913 | 27.1803 | 32.7316 | 8.7563 | 8.5972 | 2.0919 | 2.1378 | 3.4594 | 3.2856 | 7.6891 | 5.5513 | 17.3534 | 19.4913 | 27.1803 | 32.7316 | 0
8.0989 | 8.4548 | 2.07 | 2.1049 | 3.3498 | 3.2099 | 7.5247 | 5.4198 | 16.5537 | 18.6586 | 26.1833 | 31.6031 | 8.0989 | 8.4548 | 2.07 | 2.1049 | 3.3498 | 3.2199 | 7.5247 | 5.4198 | 16.5537 | 18.6586 | 26.1833 | 31.6031 | 0
-3.4729 | 5.9475 | 1.6842 | 1.5264 | 1.4212 | 2.0527 | 4.6318 | 3.1054 | 2.4746 | 4.0009 | 8.6327 | 11.7381 | -3.4729 | 5.9475 | 1.6842 | 1.5264 | 1.4212 | 2.0627 | 4.6318 | 3.1054 | 2.4746 | 4.0009 | 8.6327 | 11.7381 | 0
0.19703 | 6.7427 | 1.8066 | 1.7099 | 2.0328 | 2.4197 | 5.5493 | 3.8394 | 6.9397 | 8.6496 | 14.1988 | 18.0382 | 0.19703 | 6.7427 | 1.8066 | 1.7099 | 2.0328 | 2.4297 | 5.5493 | 3.8394 | 6.9397 | 8.6496 | 14.1988 | 18.0382 | 0
2.1437 | 7.1645 | 1.8715 | 1.8072 | 2.3573 | 2.6144 | 6.0359 | 4.2287 | 9.3082 | 11.1154 | 17.1513 | 21.38 | 2.1437 | 7.1645 | 1.8715 | 1.8072 | 2.3573 | 2.6244 | 6.0359 | 4.2287 | 9.3082 | 11.1154 | 17.1513 | 21.38 | 0
2.1804 | 7.1724 | 1.8727 | 1.809 | 2.3634 | 2.618 | 6.0451 | 4.2361 | 9.3528 | 11.1618 | 17.2069 | 21.443 | 2.1804 | 7.1724 | 1.8727 | 1.809 | 2.3634 | 2.628 | 6.0451 | 4.2361 | 9.3528 | 11.1618 | 17.2069 | 21.443 | 0
8.4919 | 8.5399 | 2.0831 | 2.1246 | 3.4153 | 3.2492 | 7.623 | 5.4984 | 17.0318 | 19.1564 | 26.7793 | 32.2777 | 8.4919 | 8.5399 | 2.0831 | 2.1246 | 3.4153 | 3.2592 | 7.623 | 5.4984 | 17.0318 | 19.1564 | 26.7793 | 32.2777 | 0
-0.30742 | 6.6334 | 1.7898 | 1.6846 | 1.9488 | 2.3693 | 5.4231 | 3.7385 | 6.326 | 8.0106 | 13.4337 | 17.1723 | -0.30742 | 6.6334 | 1.7898 | 1.6846 | 1.9488 | 2.3793 | 5.4231 | 3.7385 | 6.326 | 8.0106 | 13.4337 | 17.1723 | 0
5.7009 | 7.9352 | 1.99 | 1.985 | 2.9501 | 2.9701 | 6.9252 | 4.9402 | 13.6361 | 15.6211 | 22.5463 | 27.4865 | 5.7009 | 7.9352 | 1.99 | 1.985 | 2.9501 | 2.9801 | 6.9252 | 4.9402 | 13.6361 | 15.6211 | 22.5463 | 27.4865 | 0
3.9954 | 7.5657 | 1.9332 | 1.8998 | 2.6659 | 2.7995 | 6.4988 | 4.5991 | 11.561 | 13.4608 | 19.9596 | 24.5587 | 3.9954 | 7.5657 | 1.9332 | 1.8998 | 2.6659 | 2.8095 | 6.4988 | 4.5991 | 11.561 | 13.4608 | 19.9596 | 24.5587 | 0
2.8736 | 7.3226 | 1.8958 | 1.8437 | 2.4789 | 2.6874 | 6.2184 | 4.3747 | 10.1962 | 12.0399 | 18.2583 | 22.633 | 2.8736 | 7.3226 | 1.8958 | 1.8437 | 2.4789 | 2.6974 | 6.2184 | 4.3747 | 10.1962 | 12.0399 | 18.2583 | 22.633 | 0
7.4078 | 8.305 | 2.0469 | 2.0704 | 3.2346 | 3.1408 | 7.352 | 5.2816 | 15.7128 | 17.7832 | 25.1352 | 30.4167 | 7.4078 | 8.305 | 2.0469 | 2.0704 | 3.2346 | 3.1508 | 7.352 | 5.2816 | 15.7128 | 17.7832 | 25.1352 | 30.4167 | 0
4.6413 | 7.7056 | 1.9547 | 1.9321 | 2.7735 | 2.8641 | 6.6603 | 4.7283 | 12.3469 | 14.2789 | 20.9392 | 25.6675 | 4.6413 | 7.7056 | 1.9547 | 1.9321 | 2.7735 | 2.8741 | 6.6603 | 4.7283 | 12.3469 | 14.2789 | 20.9392 | 25.6675 | 0
17.8399 | 10.5653 | 2.3947 | 2.592 | 4.9733 | 4.184 | 9.96 | 7.368 | 28.4052 | 30.9972 | 40.9571 | 48.3251 | 17.8399 | 10.5653 | 2.3947 | 2.592 | 4.9733 | 4.194 | 9.96 | 7.368 | 28.4052 | 30.9972 | 40.9571 | 48.3251 | 0
10.3126 | 8.9344 | 2.1438 | 2.2156 | 3.7188 | 3.4313 | 8.0782 | 5.8625 | 19.2471 | 21.4627 | 29.5409 | 35.4034 | 10.3126 | 8.9344 | 2.1438 | 2.2156 | 3.7188 | 3.4413 | 8.0782 | 5.8625 | 19.2471 | 21.4627 | 29.5409 | 35.4034 | 0
0.93636 | 6.9029 | 1.8312 | 1.7468 | 2.1561 | 2.4936 | 5.7341 | 3.9873 | 7.8392 | 9.5861 | 15.3201 | 19.3074 | 0.93636 | 6.9029 | 1.8312 | 1.7468 | 2.1561 | 2.5036 | 5.7341 | 3.9873 | 7.8392 | 9.5861 | 15.3201 | 19.3074 | 0
5.9171 | 7.982 | 1.9972 | 1.9959 | 2.9862 | 2.9917 | 6.9793 | 4.9834 | 13.8992 | 15.8951 | 22.8743 | 27.8578 | 5.9171 | 7.982 | 1.9972 | 1.9959 | 2.9862 | 3.0017 | 6.9793 | 4.9834 | 13.8992 | 15.8951 | 22.8743 | 27.8578 | 0
14.2609 | 9.7899 | 2.2754 | 2.413 | 4.3768 | 3.8261 | 9.0652 | 6.6522 | 24.0507 | 26.4638 | 35.529 | 42.1812 | 14.2609 | 9.7899 | 2.2754 | 2.413 | 4.3768 | 3.8361 | 9.0652 | 6.6522 | 24.0507 | 26.4638 | 35.529 | 42.1812 | 0
4.7586 | 7.731 | 1.9586 | 1.9379 | 2.7931 | 2.8759 | 6.6897 | 4.7517 | 12.4897 | 14.4276 | 21.1173 | 25.869 | 4.7586 | 7.731 | 1.9586 | 1.9379 | 2.7931 | 2.8859 | 6.6897 | 4.7517 | 12.4897 | 14.4276 | 21.1173 | 25.869 | 0
-1.5358 | 6.3672 | 1.7488 | 1.6232 | 1.744 | 2.2464 | 5.116 | 3.4928 | 4.8314 | 6.4546 | 11.5707 | 15.0635 | -1.5358 | 6.3672 | 1.7488 | 1.6232 | 1.744 | 2.2564 | 5.116 | 3.4928 | 4.8314 | 6.4546 | 11.5707 | 15.0635 | 0
4.5187 | 7.6791 | 1.9506 | 1.9259 | 2.7531 | 2.8519 | 6.6297 | 4.7037 | 12.1977 | 14.1237 | 20.7534 | 25.4571 | 4.5187 | 7.6791 | 1.9506 | 1.9259 | 2.7531 | 2.8619 | 6.6297 | 4.7037 | 12.1977 | 14.1237 | 20.7534 | 25.4571 | 0
10.9318 | 9.0686 | 2.1644 | 2.2466 | 3.822 | 3.4932 | 8.233 | 5.9864 | 20.0004 | 22.247 | 30.4799 | 36.4663 | 10.9318 | 9.0686 | 2.1644 | 2.2466 | 3.822 | 3.5032 | 8.233 | 5.9864 | 20.0004 | 22.247 | 30.4799 | 36.4663 | 0
3.7619 | 7.5151 | 1.9254 | 1.8881 | 2.627 | 2.7762 | 6.4405 | 4.5524 | 11.2769 | 13.165 | 19.6055 | 24.1579 | 3.7619 | 7.5151 | 1.9254 | 1.8881 | 2.627 | 2.7862 | 6.4405 | 4.5524 | 11.2769 | 13.165 | 19.6055 | 24.1579 | 0
0.66962 | 6.8451 | 1.8223 | 1.7335 | 2.1116 | 2.467 | 5.6674 | 3.9339 | 7.5147 | 9.2482 | 14.9156 | 18.8495 | 0.66962 | 6.8451 | 1.8223 | 1.7335 | 2.1116 | 2.477 | 5.6674 | 3.9339 | 7.5147 | 9.2482 | 14.9156 | 18.8495 | 0
8.4453 | 8.5298 | 2.0815 | 2.1223 | 3.4076 | 3.2445 | 7.6113 | 5.4891 | 16.9752 | 19.0974 | 26.7088 | 32.1978 | 8.4453 | 8.5298 | 2.0815 | 2.1223 | 3.4076 | 3.2545 | 7.6113 | 5.4891 | 16.9752 | 19.0974 | 26.7088 | 32.1978 | 0
4 | 7.5667 | 1.9333 | 1.9 | 2.6667 | 2.8 | 6.5 | 4.6 | 11.5666 | 13.4666 | 19.9666 | 24.5666 | 4 | 7.5667 | 1.9333 | 1.9 | 2.6667 | 2.81 | 6.5 | 4.6 | 11.5666 | 13.4666 | 19.9666 | 24.5666 | 0
0.11313 | 6.7245 | 1.8038 | 1.7057 | 2.0189 | 2.4113 | 5.5283 | 3.8226 | 6.8376 | 8.5433 | 14.0716 | 17.8942 | 0.11313 | 6.7245 | 1.8038 | 1.7057 | 2.0189 | 2.4213 | 5.5283 | 3.8226 | 6.8376 | 8.5433 | 14.0716 | 17.8942 | 0
14.3302 | 9.8049 | 2.2777 | 2.4165 | 4.3884 | 3.833 | 9.0825 | 6.666 | 24.135 | 26.5516 | 35.6341 | 42.3001 | 14.3302 | 9.8049 | 2.2777 | 2.4165 | 4.3884 | 3.843 | 9.0825 | 6.666 | 24.135 | 26.5516 | 35.6341 | 42.3001 | 0
0.82956 | 6.8797 | 1.8277 | 1.7415 | 2.1383 | 2.483 | 5.7074 | 3.9659 | 7.7093 | 9.4508 | 15.1582 | 19.1241 | 0.82956 | 6.8797 | 1.8277 | 1.7415 | 2.1383 | 2.493 | 5.7074 | 3.9659 | 7.7093 | 9.4508 | 15.1582 | 19.1241 | 0
6.5365 | 8.1162 | 2.0179 | 2.0268 | 3.0894 | 3.0537 | 7.1341 | 5.1073 | 14.6528 | 16.6796 | 23.8137 | 28.921 | 6.5365 | 8.1162 | 2.0179 | 2.0268 | 3.0894 | 3.0637 | 7.1341 | 5.1073 | 14.6528 | 16.6796 | 23.8137 | 28.921 | 0
2.4857 | 7.2386 | 1.8829 | 1.8243 | 2.4143 | 2.6486 | 6.1214 | 4.2971 | 9.7243 | 11.5486 | 17.67 | 21.9671 | 2.4857 | 7.2386 | 1.8829 | 1.8243 | 2.4143 | 2.6586 | 6.1214 | 4.2971 | 9.7243 | 11.5486 | 17.67 | 21.9671 | 0
9.4618 | 8.7501 | 2.1154 | 2.1731 | 3.577 | 3.3462 | 7.8655 | 5.6924 | 18.2119 | 20.385 | 28.2504 | 33.9428 | 9.4618 | 8.7501 | 2.1154 | 2.1731 | 3.577 | 3.3562 | 7.8655 | 5.6924 | 18.2119 | 20.385 | 28.2504 | 33.9428 | 0
10.5152 | 8.9783 | 2.1505 | 2.2258 | 3.7525 | 3.4515 | 8.1288 | 5.903 | 19.4935 | 21.7193 | 29.8481 | 35.7511 | 10.5152 | 8.9783 | 2.1505 | 2.2258 | 3.7525 | 3.4615 | 8.1288 | 5.903 | 19.4935 | 21.7193 | 29.8481 | 35.7511 | 0
13.8852 | 9.7085 | 2.2628 | 2.3943 | 4.3142 | 3.7885 | 8.9713 | 6.577 | 23.5937 | 25.9879 | 34.9592 | 41.5363 | 13.8852 | 9.7085 | 2.2628 | 2.3943 | 4.3142 | 3.7985 | 8.9713 | 6.577 | 23.5937 | 25.9879 | 34.9592 | 41.5363 | 0
7.4114 | 8.3058 | 2.047 | 2.0706 | 3.2352 | 3.1411 | 7.3529 | 5.2823 | 15.7172 | 17.7878 | 25.1406 | 30.4229 | 7.4114 | 8.3058 | 2.047 | 2.0706 | 3.2352 | 3.1511 | 7.3529 | 5.2823 | 15.7172 | 17.7878 | 25.1406 | 30.4229 | 0
3.3173 | 7.4187 | 1.9106 | 1.8659 | 2.5529 | 2.7317 | 6.3293 | 4.4635 | 10.736 | 12.6019 | 18.9312 | 23.3947 | 3.3173 | 7.4187 | 1.9106 | 1.8659 | 2.5529 | 2.7417 | 6.3293 | 4.4635 | 10.736 | 12.6019 | 18.9312 | 23.3947 | 0
6.514 | 8.1114 | 2.0171 | 2.0257 | 3.0857 | 3.0514 | 7.1285 | 5.1028 | 14.6253 | 16.651 | 23.7795 | 28.8823 | 6.514 | 8.1114 | 2.0171 | 2.0257 | 3.0857 | 3.0614 | 7.1285 | 5.1028 | 14.6253 | 16.651 | 23.7795 | 28.8823 | 0
-0.5379 | 6.5835 | 1.7821 | 1.6731 | 1.9104 | 2.3462 | 5.3655 | 3.6924 | 6.0456 | 7.7187 | 13.0842 | 16.7766 | -0.5379 | 6.5835 | 1.7821 | 1.6731 | 1.9104 | 2.3562 | 5.3655 | 3.6924 | 6.0456 | 7.7187 | 13.0842 | 16.7766 | 0
1.9903 | 7.1312 | 1.8663 | 1.7995 | 2.3317 | 2.599 | 5.9976 | 4.1981 | 9.1215 | 10.9211 | 16.9186 | 21.1167 | 1.9903 | 7.1312 | 1.8663 | 1.7995 | 2.3317 | 2.609 | 5.9976 | 4.1981 | 9.1215 | 10.9211 | 16.9186 | 21.1167 | 0
17.5171 | 10.4954 | 2.3839 | 2.5759 | 4.9195 | 4.1517 | 9.8793 | 7.3034 | 28.0125 | 30.5883 | 40.4676 | 47.771 | 17.5171 | 10.4954 | 2.3839 | 2.5759 | 4.9195 | 4.1617 | 9.8793 | 7.3034 | 28.0125 | 30.5883 | 40.4676 | 47.771 | 0
5.7762 | 7.9515 | 1.9925 | 1.9888 | 2.9627 | 2.9776 | 6.9441 | 4.9552 | 13.7277 | 15.7166 | 22.6606 | 27.6159 | 5.7762 | 7.9515 | 1.9925 | 1.9888 | 2.9627 | 2.9876 | 6.9441 | 4.9552 | 13.7277 | 15.7166 | 22.6606 | 27.6159 | 0
5.936 | 7.9861 | 1.9979 | 1.9968 | 2.9893 | 2.9936 | 6.984 | 4.9872 | 13.9222 | 15.919 | 22.903 | 27.8902 | 5.936 | 7.9861 | 1.9979 | 1.9968 | 2.9893 | 3.0036 | 6.984 | 4.9872 | 13.9222 | 15.919 | 22.903 | 27.8902 | 0
-4.9884 | 5.6192 | 1.6337 | 1.4506 | 1.1686 | 1.9012 | 4.2529 | 2.8023 | 0.63082 | 2.0814 | 6.3343 | 9.1366 | -4.9884 | 5.6192 | 1.6337 | 1.4506 | 1.1686 | 1.9112 | 4.2529 | 2.8023 | 0.63082 | 2.0814 | 6.3343 | 9.1366 | 0
4.2438 | 7.6195 | 1.9415 | 1.9122 | 2.7073 | 2.8244 | 6.561 | 4.6488 | 11.8633 | 13.7755 | 20.3365 | 24.9852 | 4.2438 | 7.6195 | 1.9415 | 1.9122 | 2.7073 | 2.8344 | 6.561 | 4.6488 | 11.8633 | 13.7755 | 20.3365 | 24.9852 | 0
8.0514 | 8.4445 | 2.0684 | 2.1026 | 3.3419 | 3.2051 | 7.5128 | 5.4103 | 16.4958 | 18.5984 | 26.1112 | 31.5215 | 8.0514 | 8.4445 | 2.0684 | 2.1026 | 3.3419 | 3.2151 | 7.5128 | 5.4103 | 16.4958 | 18.5984 | 26.1112 | 31.5215 | 0
-8.3684 | 4.8868 | 1.5211 | 1.2816 | 0.60526 | 1.5632 | 3.4079 | 2.1263 | -3.4816 | -2.2 | 1.2079 | 3.3342 | -8.3684 | 4.8868 | 1.5211 | 1.2816 | 0.60526 | 1.5732 | 3.4079 | 2.1263 | -3.4816 | -2.2 | 1.2079 | 3.3342 | 0
10.4473 | 8.9636 | 2.1482 | 2.2224 | 3.7412 | 3.4447 | 8.1118 | 5.8895 | 19.4109 | 21.6333 | 29.7451 | 35.6346 | 10.4473 | 8.9636 | 2.1482 | 2.2224 | 3.7412 | 3.4547 | 8.1118 | 5.8895 | 19.4109 | 21.6333 | 29.7451 | 35.6346 | 0
6.2781 | 8.0603 | 2.0093 | 2.0139 | 3.0463 | 3.0278 | 7.0695 | 5.0556 | 14.3383 | 16.3522 | 23.4218 | 28.4774 | 6.2781 | 8.0603 | 2.0093 | 2.0139 | 3.0463 | 3.0378 | 7.0695 | 5.0556 | 14.3383 | 16.3522 | 23.4218 | 28.4774 | 0
-0.026116 | 6.6943 | 1.7991 | 1.6987 | 1.9956 | 2.3974 | 5.4935 | 3.7948 | 6.6682 | 8.3669 | 13.8604 | 17.6552 | -0.026116 | 6.6943 | 1.7991 | 1.6987 | 1.9956 | 2.4074 | 5.4935 | 3.7948 | 6.6682 | 8.3669 | 13.8604 | 17.6552 | 0
12.3808 | 9.3825 | 2.2127 | 2.319 | 4.0635 | 3.6381 | 8.5952 | 6.2762 | 21.7633 | 24.0823 | 32.6775 | 38.9537 | 12.3808 | 9.3825 | 2.2127 | 2.319 | 4.0635 | 3.6481 | 8.5952 | 6.2762 | 21.7633 | 24.0823 | 32.6775 | 38.9537 | 0
4.3092 | 7.6337 | 1.9436 | 1.9155 | 2.7182 | 2.8309 | 6.5773 | 4.6618 | 11.9428 | 13.8583 | 20.4356 | 25.0974 | 4.3092 | 7.6337 | 1.9436 | 1.9155 | 2.7182 | 2.8409 | 6.5773 | 4.6618 | 11.9428 | 13.8583 | 20.4356 | 25.0974 | 0
9.5463 | 8.7684 | 2.1182 | 2.1773 | 3.591 | 3.3546 | 7.8866 | 5.7093 | 18.3146 | 20.492 | 28.3785 | 34.0878 | 9.5463 | 8.7684 | 2.1182 | 2.1773 | 3.591 | 3.3646 | 7.8866 | 5.7093 | 18.3146 | 20.492 | 28.3785 | 34.0878 | 0
3.7633 | 7.5154 | 1.9254 | 1.8882 | 2.6272 | 2.7763 | 6.4408 | 4.5527 | 11.2787 | 13.1668 | 19.6077 | 24.1603 | 3.7633 | 7.5154 | 1.9254 | 1.8882 | 2.6272 | 2.7863 | 6.4408 | 4.5527 | 11.2787 | 13.1668 | 19.6077 | 24.1603 | 0
8.7658 | 8.5992 | 2.0922 | 2.1383 | 3.461 | 3.2766 | 7.6914 | 5.5532 | 17.365 | 19.5033 | 27.1947 | 32.7479 | 8.7658 | 8.5992 | 2.0922 | 2.1383 | 3.461 | 3.2866 | 7.6914 | 5.5532 | 17.365 | 19.5033 | 27.1947 | 32.7479 | 0
0.69767 | 6.8512 | 1.8233 | 1.7349 | 2.1163 | 2.4698 | 5.6744 | 3.9395 | 7.5488 | 9.2837 | 14.9581 | 18.8977 | 0.69767 | 6.8512 | 1.8233 | 1.7349 | 2.1163 | 2.4798 | 5.6744 | 3.9395 | 7.5488 | 9.2837 | 14.9581 | 18.8977 | 0
11.5977 | 9.2128 | 2.1866 | 2.2799 | 3.9329 | 3.5598 | 8.3994 | 6.1195 | 20.8105 | 23.0904 | 31.4898 | 37.6094 | 11.5977 | 9.2128 | 2.1866 | 2.2799 | 3.9329 | 3.5698 | 8.3994 | 6.1195 | 20.8105 | 23.0904 | 31.4898 | 37.6094 | 0
8.4712 | 8.5354 | 2.0824 | 2.1236 | 3.4119 | 3.2471 | 7.6178 | 5.4942 | 17.0067 | 19.1302 | 26.748 | 32.2423 | 8.4712 | 8.5354 | 2.0824 | 2.1236 | 3.4119 | 3.2571 | 7.6178 | 5.4942 | 17.0067 | 19.1302 | 26.748 | 32.2423 | 0
18.2142 | 10.6464 | 2.4071 | 2.6107 | 5.0357 | 4.2214 | 10.0536 | 7.4428 | 28.8606 | 31.4713 | 41.5249 | 48.9677 | 18.2142 | 10.6464 | 2.4071 | 2.6107 | 5.0357 | 4.2314 | 10.0536 | 7.4428 | 28.8606 | 31.4713 | 41.5249 | 48.9677 | 0
13.8999 | 9.7117 | 2.2633 | 2.395 | 4.3167 | 3.79 | 8.975 | 6.58 | 23.6116 | 26.0066 | 34.9816 | 41.5615 | 13.8999 | 9.7117 | 2.2633 | 2.395 | 4.3167 | 3.8 | 8.975 | 6.58 | 23.6116 | 26.0066 | 34.9816 | 41.5615 | 0
6.3636 | 8.0788 | 2.0121 | 2.0182 | 3.0606 | 3.0364 | 7.0909 | 5.0727 | 14.4424 | 16.4605 | 23.5514 | 28.6242 | 6.3636 | 8.0788 | 2.0121 | 2.0182 | 3.0606 | 3.0464 | 7.0909 | 5.0727 | 14.4424 | 16.4605 | 23.5514 | 28.6242 | 0
6.9097 | 8.1971 | 2.0303 | 2.0455 | 3.1516 | 3.091 | 7.2274 | 5.1819 | 15.1068 | 17.1523 | 24.3797 | 29.5616 | 6.9097 | 8.1971 | 2.0303 | 2.0455 | 3.1516 | 3.101 | 7.2274 | 5.1819 | 15.1068 | 17.1523 | 24.3797 | 29.5616 | 0
1.1273 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7818 | 4.0255 | 8.0716 | 9.8279 | 15.6098 | 19.6352 | 1.1273 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5227 | 5.7818 | 4.0255 | 8.0716 | 9.8279 | 15.6098 | 19.6352 | 0
15.8964 | 10.1442 | 2.3299 | 2.4948 | 4.6494 | 3.9896 | 9.4741 | 6.9793 | 26.0407 | 28.5355 | 38.0096 | 44.9889 | 15.8964 | 10.1442 | 2.3299 | 2.4948 | 4.6494 | 3.9996 | 9.4741 | 6.9793 | 26.0407 | 28.5355 | 38.0096 | 44.9889 | 0
6.1089 | 8.0236 | 2.0036 | 2.0054 | 3.0181 | 3.0109 | 7.0272 | 5.0218 | 14.1325 | 16.1379 | 23.1651 | 28.1869 | 6.1089 | 8.0236 | 2.0036 | 2.0054 | 3.0181 | 3.0209 | 7.0272 | 5.0218 | 14.1325 | 16.1379 | 23.1651 | 28.1869 | 0
0.25643 | 6.7556 | 1.8085 | 1.7128 | 2.0427 | 2.4256 | 5.5641 | 3.8513 | 7.012 | 8.7248 | 14.2889 | 18.1402 | 0.25643 | 6.7556 | 1.8085 | 1.7128 | 2.0427 | 2.4356 | 5.5641 | 3.8513 | 7.012 | 8.7248 | 14.2889 | 18.1402 | 0
-4.2332 | 5.7828 | 1.6589 | 1.4883 | 1.2945 | 1.9767 | 4.4417 | 2.9534 | 1.5496 | 3.038 | 7.4797 | 10.433 | -4.2332 | 5.7828 | 1.6589 | 1.4883 | 1.2945 | 1.9867 | 4.4417 | 2.9534 | 1.5496 | 3.038 | 7.4797 | 10.433 | 0
3.0006 | 7.3501 | 1.9 | 1.85 | 2.5001 | 2.7001 | 6.2501 | 4.4001 | 10.3507 | 12.2007 | 18.4509 | 22.851 | 3.0006 | 7.3501 | 1.9 | 1.85 | 2.5001 | 2.7101 | 6.2501 | 4.4001 | 10.3507 | 12.2007 | 18.4509 | 22.851 | 0
-0.019623 | 6.6957 | 1.7993 | 1.699 | 1.9967 | 2.398 | 5.4951 | 3.7961 | 6.6761 | 8.3751 | 13.8702 | 17.6663 | -0.019623 | 6.6957 | 1.7993 | 1.699 | 1.9967 | 2.408 | 5.4951 | 3.7961 | 6.6761 | 8.3751 | 13.8702 | 17.6663 | 0
1.7234 | 7.0734 | 1.8574 | 1.7862 | 2.2872 | 2.5723 | 5.9308 | 4.1447 | 8.7968 | 10.583 | 16.5138 | 20.6585 | 1.7234 | 7.0734 | 1.8574 | 1.7862 | 2.2872 | 2.5823 | 5.9308 | 4.1447 | 8.7968 | 10.583 | 16.5138 | 20.6585 | 0
17.9337 | 10.5856 | 2.3978 | 2.5967 | 4.9889 | 4.1934 | 9.9834 | 7.3867 | 28.5193 | 31.116 | 41.0994 | 48.4862 | 17.9337 | 10.5856 | 2.3978 | 2.5967 | 4.9889 | 4.2034 | 9.9834 | 7.3867 | 28.5193 | 31.116 | 41.0994 | 48.4862 | 0
5.9536 | 7.9899 | 1.9985 | 1.9977 | 2.9923 | 2.9954 | 6.9884 | 4.9907 | 13.9435 | 15.9412 | 22.9296 | 27.9203 | 5.9536 | 7.9899 | 1.9985 | 1.9977 | 2.9923 | 3.0054 | 6.9884 | 4.9907 | 13.9435 | 15.9412 | 22.9296 | 27.9203 | 0
8.1286 | 8.4612 | 2.071 | 2.1064 | 3.3548 | 3.2129 | 7.5321 | 5.4257 | 16.5897 | 18.6962 | 26.2283 | 31.654 | 8.1286 | 8.4612 | 2.071 | 2.1064 | 3.3548 | 3.2229 | 7.5321 | 5.4257 | 16.5897 | 18.6962 | 26.2283 | 31.654 | 0
0.99013 | 6.9145 | 1.833 | 1.7495 | 2.165 | 2.499 | 5.7475 | 3.998 | 7.9047 | 9.6542 | 15.4017 | 19.3997 | 0.99013 | 6.9145 | 1.833 | 1.7495 | 2.165 | 2.509 | 5.7475 | 3.998 | 7.9047 | 9.6542 | 15.4017 | 19.3997 | 0
9.9327 | 8.8521 | 2.1311 | 2.1966 | 3.6554 | 3.3933 | 7.9832 | 5.7865 | 18.7847 | 20.9814 | 28.9645 | 34.7511 | 9.9327 | 8.8521 | 2.1311 | 2.1966 | 3.6554 | 3.4033 | 7.9832 | 5.7865 | 18.7847 | 20.9814 | 28.9645 | 34.7511 | 0
13.1113 | 9.5408 | 2.237 | 2.3556 | 4.1852 | 3.7111 | 8.7778 | 6.4223 | 22.6521 | 25.0077 | 33.7855 | 40.2078 | 13.1113 | 9.5408 | 2.237 | 2.3556 | 4.1852 | 3.7211 | 8.7778 | 6.4223 | 22.6521 | 25.0077 | 33.7855 | 40.2078 | 0
3.9177 | 7.5488 | 1.9306 | 1.8959 | 2.6529 | 2.7918 | 6.4794 | 4.5835 | 11.4665 | 13.3624 | 19.8418 | 24.4253 | 3.9177 | 7.5488 | 1.9306 | 1.8959 | 2.6529 | 2.8018 | 6.4794 | 4.5835 | 11.4665 | 13.3624 | 19.8418 | 24.4253 | 0
4.0887 | 7.5859 | 1.9363 | 1.9044 | 2.6814 | 2.8089 | 6.5222 | 4.6177 | 11.6745 | 13.579 | 20.1011 | 24.7189 | 4.0887 | 7.5859 | 1.9363 | 1.9044 | 2.6814 | 2.8189 | 6.5222 | 4.6177 | 11.6745 | 13.579 | 20.1011 | 24.7189 | 0
-0.055066 | 6.6881 | 1.7982 | 1.6972 | 1.9908 | 2.3945 | 5.4862 | 3.789 | 6.633 | 8.3303 | 13.8165 | 17.6055 | -0.055066 | 6.6881 | 1.7982 | 1.6972 | 1.9908 | 2.4045 | 5.4862 | 3.789 | 6.633 | 8.3303 | 13.8165 | 17.6055 | 0
3.9499 | 7.5558 | 1.9317 | 1.8975 | 2.6583 | 2.795 | 6.4875 | 4.59 | 11.5057 | 13.4032 | 19.8906 | 24.4806 | 3.9499 | 7.5558 | 1.9317 | 1.8975 | 2.6583 | 2.805 | 6.4875 | 4.59 | 11.5057 | 13.4032 | 19.8906 | 24.4806 | 0
2.5412 | 7.2506 | 1.8847 | 1.8271 | 2.4235 | 2.6541 | 6.1353 | 4.3082 | 9.7918 | 11.6189 | 17.7542 | 22.0624 | 2.5412 | 7.2506 | 1.8847 | 1.8271 | 2.4235 | 2.6641 | 6.1353 | 4.3082 | 9.7918 | 11.6189 | 17.7542 | 22.0624 | 0
-1.6705 | 6.3381 | 1.7443 | 1.6165 | 1.7216 | 2.233 | 5.0824 | 3.4659 | 4.6676 | 6.2841 | 11.3664 | 14.8323 | -1.6705 | 6.3381 | 1.7443 | 1.6165 | 1.7216 | 2.243 | 5.0824 | 3.4659 | 4.6676 | 6.2841 | 11.3664 | 14.8323 | 0
17.8938 | 10.577 | 2.3965 | 2.5947 | 4.9823 | 4.1894 | 9.9734 | 7.3788 | 28.4708 | 31.0655 | 41.0389 | 48.4177 | 17.8938 | 10.577 | 2.3965 | 2.5947 | 4.9823 | 4.1994 | 9.9734 | 7.3788 | 28.4708 | 31.0655 | 41.0389 | 48.4177 | 0
2.6217 | 7.268 | 1.8874 | 1.8311 | 2.4369 | 2.6622 | 6.1554 | 4.3243 | 9.8897 | 11.7208 | 17.8762 | 22.2005 | 2.6217 | 7.268 | 1.8874 | 1.8311 | 2.4369 | 2.6722 | 6.1554 | 4.3243 | 9.8897 | 11.7208 | 17.8762 | 22.2005 | 0
6.531 | 8.1151 | 2.0177 | 2.0266 | 3.0885 | 3.0531 | 7.1328 | 5.1062 | 14.6461 | 16.6726 | 23.8054 | 28.9116 | 6.531 | 8.1151 | 2.0177 | 2.0266 | 3.0885 | 3.0631 | 7.1328 | 5.1062 | 14.6461 | 16.6726 | 23.8054 | 28.9116 | 0
-0.63752 | 6.5619 | 1.7787 | 1.6681 | 1.8937 | 2.3362 | 5.3406 | 3.6725 | 5.9244 | 7.5925 | 12.9331 | 16.6056 | -0.63752 | 6.5619 | 1.7787 | 1.6681 | 1.8937 | 2.3462 | 5.3406 | 3.6725 | 5.9244 | 7.5925 | 12.9331 | 16.6056 | 0
3.242 | 7.4024 | 1.9081 | 1.8621 | 2.5403 | 2.7242 | 6.3105 | 4.4484 | 10.6444 | 12.5065 | 18.817 | 23.2654 | 3.242 | 7.4024 | 1.9081 | 1.8621 | 2.5403 | 2.7342 | 6.3105 | 4.4484 | 10.6444 | 12.5065 | 18.817 | 23.2654 | 0
7.7059 | 8.3696 | 2.0569 | 2.0853 | 3.2843 | 3.1706 | 7.4265 | 5.3412 | 16.0755 | 18.1608 | 25.5873 | 30.9285 | 7.7059 | 8.3696 | 2.0569 | 2.0853 | 3.2843 | 3.1806 | 7.4265 | 5.3412 | 16.0755 | 18.1608 | 25.5873 | 30.9285 | 0
5.5315 | 7.8985 | 1.9844 | 1.9766 | 2.9219 | 2.9532 | 6.8829 | 4.9063 | 13.43 | 15.4066 | 22.2895 | 27.1958 | 5.5315 | 7.8985 | 1.9844 | 1.9766 | 2.9219 | 2.9632 | 6.8829 | 4.9063 | 13.43 | 15.4066 | 22.2895 | 27.1958 | 0
6.2875 | 8.0623 | 2.0096 | 2.0144 | 3.0479 | 3.0288 | 7.0719 | 5.0575 | 14.3498 | 16.3642 | 23.4361 | 28.4936 | 6.2875 | 8.0623 | 2.0096 | 2.0144 | 3.0479 | 3.0388 | 7.0719 | 5.0575 | 14.3498 | 16.3642 | 23.4361 | 28.4936 | 0
8.8478 | 8.617 | 2.0949 | 2.1424 | 3.4746 | 3.2848 | 7.7119 | 5.5696 | 17.4648 | 19.6072 | 27.3191 | 32.8887 | 8.8478 | 8.617 | 2.0949 | 2.1424 | 3.4746 | 3.2948 | 7.7119 | 5.5696 | 17.4648 | 19.6072 | 27.3191 | 32.8887 | 0
3.6485 | 7.4905 | 1.9216 | 1.8824 | 2.6081 | 2.7648 | 6.4121 | 4.5297 | 11.139 | 13.0214 | 19.4335 | 23.9632 | 3.6485 | 7.4905 | 1.9216 | 1.8824 | 2.6081 | 2.7748 | 6.4121 | 4.5297 | 11.139 | 13.0214 | 19.4335 | 23.9632 | 0
4.5406 | 7.6838 | 1.9514 | 1.927 | 2.7568 | 2.8541 | 6.6352 | 4.7081 | 12.2244 | 14.1515 | 20.7866 | 25.4947 | 4.5406 | 7.6838 | 1.9514 | 1.927 | 2.7568 | 2.8641 | 6.6352 | 4.7081 | 12.2244 | 14.1515 | 20.7866 | 25.4947 | 0
7.2969 | 8.281 | 2.0432 | 2.0648 | 3.2162 | 3.1297 | 7.3242 | 5.2594 | 15.5779 | 17.6428 | 24.967 | 30.2264 | 7.2969 | 8.281 | 2.0432 | 2.0648 | 3.2162 | 3.1397 | 7.3242 | 5.2594 | 15.5779 | 17.6428 | 24.967 | 30.2264 | 0
7.5894 | 8.3444 | 2.053 | 2.0795 | 3.2649 | 3.1589 | 7.3974 | 5.3179 | 15.9338 | 18.0133 | 25.4106 | 30.7285 | 7.5894 | 8.3444 | 2.053 | 2.0795 | 3.2649 | 3.1689 | 7.3974 | 5.3179 | 15.9338 | 18.0133 | 25.4106 | 30.7285 | 0
-1.186 | 6.443 | 1.7605 | 1.6407 | 1.8023 | 2.2814 | 5.2035 | 3.5628 | 5.257 | 6.8977 | 12.1012 | 15.664 | -1.186 | 6.443 | 1.7605 | 1.6407 | 1.8023 | 2.2914 | 5.2035 | 3.5628 | 5.257 | 6.8977 | 12.1012 | 15.664 | 0
7.5221 | 8.3298 | 2.0507 | 2.0761 | 3.2537 | 3.1522 | 7.3805 | 5.3044 | 15.8519 | 17.928 | 25.3085 | 30.6129 | 7.5221 | 8.3298 | 2.0507 | 2.0761 | 3.2537 | 3.1622 | 7.3805 | 5.3044 | 15.8519 | 17.928 | 25.3085 | 30.6129 | 0
4.1728 | 7.6041 | 1.9391 | 1.9086 | 2.6955 | 2.8173 | 6.5432 | 4.6346 | 11.7769 | 13.6856 | 20.2288 | 24.8633 | 4.1728 | 7.6041 | 1.9391 | 1.9086 | 2.6955 | 2.8273 | 6.5432 | 4.6346 | 11.7769 | 13.6856 | 20.2288 | 24.8633 | 0
10.0312 | 8.8734 | 2.1344 | 2.2016 | 3.6719 | 3.4031 | 8.0078 | 5.8062 | 18.9047 | 21.1062 | 29.114 | 34.9203 | 10.0312 | 8.8734 | 2.1344 | 2.2016 | 3.6719 | 3.4131 | 8.0078 | 5.8062 | 18.9047 | 21.1062 | 29.114 | 34.9203 | 0
1.8924 | 7.11 | 1.8631 | 1.7946 | 2.3154 | 2.5892 | 5.9731 | 4.1785 | 9.0025 | 10.7971 | 16.7702 | 20.9487 | 1.8924 | 7.11 | 1.8631 | 1.7946 | 2.3154 | 2.5992 | 5.9731 | 4.1785 | 9.0025 | 10.7971 | 16.7702 | 20.9487 | 0
16.936 | 10.3695 | 2.3645 | 2.5468 | 4.8227 | 4.0936 | 9.734 | 7.1872 | 27.3054 | 29.8522 | 39.5862 | 46.7734 | 16.936 | 10.3695 | 2.3645 | 2.5468 | 4.8227 | 4.1036 | 9.734 | 7.1872 | 27.3054 | 29.8522 | 39.5862 | 46.7734 | 0
7.2675 | 8.2746 | 2.0422 | 2.0634 | 3.2112 | 3.1267 | 7.3169 | 5.2535 | 15.5421 | 17.6055 | 24.9223 | 30.1758 | 7.2675 | 8.2746 | 2.0422 | 2.0634 | 3.2112 | 3.1367 | 7.3169 | 5.2535 | 15.5421 | 17.6055 | 24.9223 | 30.1758 | 0
5.0004 | 7.7834 | 1.9667 | 1.95 | 2.8334 | 2.9 | 6.7501 | 4.8001 | 12.7839 | 14.7339 | 21.484 | 26.2841 | 5.0004 | 7.7834 | 1.9667 | 1.95 | 2.8334 | 2.91 | 6.7501 | 4.8001 | 12.7839 | 14.7339 | 21.484 | 26.2841 | 0
8.22 | 8.481 | 2.074 | 2.111 | 3.37 | 3.222 | 7.555 | 5.444 | 16.7011 | 18.8121 | 26.3671 | 31.8111 | 8.22 | 8.481 | 2.074 | 2.111 | 3.37 | 3.232 | 7.555 | 5.444 | 16.7011 | 18.8121 | 26.3671 | 31.8111 | 0
15.5054 | 10.0595 | 2.3168 | 2.4753 | 4.5842 | 3.9505 | 9.3763 | 6.9011 | 25.5649 | 28.0401 | 37.4165 | 44.3175 | 15.5054 | 10.0595 | 2.3168 | 2.4753 | 4.5842 | 3.9605 | 9.3763 | 6.9011 | 25.5649 | 28.0401 | 37.4165 | 44.3175 | 0
1.1288 | 6.9446 | 1.8376 | 1.7564 | 2.1881 | 2.5129 | 5.7822 | 4.0258 | 8.0734 | 9.8299 | 15.6121 | 19.6378 | 1.1288 | 6.9446 | 1.8376 | 1.7564 | 2.1881 | 2.5229 | 5.7822 | 4.0258 | 8.0734 | 9.8299 | 15.6121 | 19.6378 | 0
0.42329 | 6.7917 | 1.8141 | 1.7212 | 2.0705 | 2.4423 | 5.6058 | 3.8847 | 7.215 | 8.9362 | 14.542 | 18.4267 | 0.42329 | 6.7917 | 1.8141 | 1.7212 | 2.0705 | 2.4523 | 5.6058 | 3.8847 | 7.215 | 8.9362 | 14.542 | 18.4267 | 0
6.5131 | 8.1112 | 2.0171 | 2.0257 | 3.0855 | 3.0513 | 7.1283 | 5.1026 | 14.6242 | 16.6499 | 23.7781 | 28.8807 | 6.5131 | 8.1112 | 2.0171 | 2.0257 | 3.0855 | 3.0613 | 7.1283 | 5.1026 | 14.6242 | 16.6499 | 23.7781 | 28.8807 | 0
-0.42709 | 6.6075 | 1.7858 | 1.6786 | 1.9288 | 2.3573 | 5.3932 | 3.7146 | 6.1804 | 7.859 | 13.2522 | 16.9668 | -0.42709 | 6.6075 | 1.7858 | 1.6786 | 1.9288 | 2.3673 | 5.3932 | 3.7146 | 6.1804 | 7.859 | 13.2522 | 16.9668 | 0
3.3855 | 7.4335 | 1.9129 | 1.8693 | 2.5643 | 2.7386 | 6.3464 | 4.4771 | 10.8191 | 12.6883 | 19.0347 | 23.5118 | 3.3855 | 7.4335 | 1.9129 | 1.8693 | 2.5643 | 2.7486 | 6.3464 | 4.4771 | 10.8191 | 12.6883 | 19.0347 | 23.5118 | 0
9.2592 | 8.7062 | 2.1086 | 2.163 | 3.5432 | 3.3259 | 7.8148 | 5.6518 | 17.9653 | 20.1283 | 27.9431 | 33.5949 | 9.2592 | 8.7062 | 2.1086 | 2.163 | 3.5432 | 3.3359 | 7.8148 | 5.6518 | 17.9653 | 20.1283 | 27.9431 | 33.5949 | 0
0.34898 | 6.7756 | 1.8116 | 1.7174 | 2.0582 | 2.4349 | 5.5872 | 3.8698 | 7.1246 | 8.842 | 14.4293 | 18.2991 | 0.34898 | 6.7756 | 1.8116 | 1.7174 | 2.0582 | 2.4449 | 5.5872 | 3.8698 | 7.1246 | 8.842 | 14.4293 | 18.2991 | 0
14.8692 | 9.9217 | 2.2956 | 2.4435 | 4.4782 | 3.8869 | 9.2173 | 6.7738 | 24.7908 | 27.2343 | 36.4516 | 43.2254 | 14.8692 | 9.9217 | 2.2956 | 2.4435 | 4.4782 | 3.8969 | 9.2173 | 6.7738 | 24.7908 | 27.2343 | 36.4516 | 43.2254 | 0
14.2324 | 9.7837 | 2.2744 | 2.4116 | 4.3721 | 3.8232 | 9.0581 | 6.6465 | 24.0161 | 26.4277 | 35.4858 | 42.1323 | 14.2324 | 9.7837 | 2.2744 | 2.4116 | 4.3721 | 3.8332 | 9.0581 | 6.6465 | 24.0161 | 26.4277 | 35.4858 | 42.1323 | 0
-3.7799 | 5.881 | 1.674 | 1.511 | 1.37 | 2.022 | 4.555 | 3.044 | 2.1012 | 3.6122 | 8.1672 | 11.2112 | -3.7799 | 5.881 | 1.674 | 1.511 | 1.37 | 2.032 | 4.555 | 3.044 | 2.1012 | 3.6122 | 8.1672 | 11.2112 | 0
5.3413 | 7.8573 | 1.978 | 1.9671 | 2.8902 | 2.9341 | 6.8353 | 4.8683 | 13.1986 | 15.1657 | 22.001 | 26.8693 | 5.3413 | 7.8573 | 1.978 | 1.9671 | 2.8902 | 2.9441 | 6.8353 | 4.8683 | 13.1986 | 15.1657 | 22.001 | 26.8693 | 0
13.6643 | 9.6606 | 2.2555 | 2.3832 | 4.2774 | 3.7664 | 8.9161 | 6.5329 | 23.3249 | 25.7081 | 34.6242 | 41.157 | 13.6643 | 9.6606 | 2.2555 | 2.3832 | 4.2774 | 3.7764 | 8.9161 | 6.5329 | 23.3249 | 25.7081 | 34.6242 | 41.157 | 0
17.2063 | 10.428 | 2.3735 | 2.5603 | 4.8677 | 4.1206 | 9.8016 | 7.2413 | 27.6343 | 30.1946 | 39.9962 | 47.2374 | 17.2063 | 10.428 | 2.3735 | 2.5603 | 4.8677 | 4.1306 | 9.8016 | 7.2413 | 27.6343 | 30.1946 | 39.9962 | 47.2374 | 0
8.2493 | 8.4874 | 2.075 | 2.1125 | 3.3749 | 3.2249 | 7.5623 | 5.4499 | 16.7367 | 18.8491 | 26.4115 | 31.8613 | 8.2493 | 8.4874 | 2.075 | 2.1125 | 3.3749 | 3.2349 | 7.5623 | 5.4499 | 16.7367 | 18.8491 | 26.4115 | 31.8613 | 0
5.4441 | 7.8796 | 1.9815 | 1.9722 | 2.9074 | 2.9444 | 6.861 | 4.8888 | 13.3237 | 15.2959 | 22.1569 | 27.0457 | 5.4441 | 7.8796 | 1.9815 | 1.9722 | 2.9074 | 2.9544 | 6.861 | 4.8888 | 13.3237 | 15.2959 | 22.1569 | 27.0457 | 0
0.4585 | 6.7993 | 1.8153 | 1.7229 | 2.0764 | 2.4459 | 5.6146 | 3.8917 | 7.2578 | 8.9808 | 14.5954 | 18.4871 | 0.4585 | 6.7993 | 1.8153 | 1.7229 | 2.0764 | 2.4559 | 5.6146 | 3.8917 | 7.2578 | 8.9808 | 14.5954 | 18.4871 | 0
-0.038013 | 6.6918 | 1.7987 | 1.6981 | 1.9937 | 2.3962 | 5.4905 | 3.7924 | 6.6538 | 8.3519 | 13.8423 | 17.6347 | -0.038013 | 6.6918 | 1.7987 | 1.6981 | 1.9937 | 2.4062 | 5.4905 | 3.7924 | 6.6538 | 8.3519 | 13.8423 | 17.6347 | 0
11.8839 | 9.2749 | 2.1961 | 2.2942 | 3.9807 | 3.5884 | 8.471 | 6.1768 | 21.1588 | 23.453 | 31.924 | 38.1008 | 11.8839 | 9.2749 | 2.1961 | 2.2942 | 3.9807 | 3.5984 | 8.471 | 6.1768 | 21.1588 | 23.453 | 31.924 | 38.1008 | 0
-3.1106 | 6.026 | 1.6963 | 1.5445 | 1.4816 | 2.0889 | 4.7224 | 3.1779 | 2.9155 | 4.4599 | 9.1823 | 12.3602 | -3.1106 | 6.026 | 1.6963 | 1.5445 | 1.4816 | 2.0989 | 4.7224 | 3.1779 | 2.9155 | 4.4599 | 9.1823 | 12.3602 | 0
2.154 | 7.1667 | 1.8718 | 1.8077 | 2.359 | 2.6154 | 6.0385 | 4.2308 | 9.3207 | 11.1284 | 17.1669 | 21.3977 | 2.154 | 7.1667 | 1.8718 | 1.8077 | 2.359 | 2.6254 | 6.0385 | 4.2308 | 9.3207 | 11.1284 | 17.1669 | 21.3977 | 0
7.67 | 8.3618 | 2.0557 | 2.0835 | 3.2783 | 3.167 | 7.4175 | 5.334 | 16.0319 | 18.1154 | 25.5329 | 30.8669 | 7.67 | 8.3618 | 2.0557 | 2.0835 | 3.2783 | 3.177 | 7.4175 | 5.334 | 16.0319 | 18.1154 | 25.5329 | 30.8669 | 0
15.8604 | 10.1364 | 2.3287 | 2.493 | 4.6434 | 3.986 | 9.4651 | 6.9721 | 25.9968 | 28.4898 | 37.9549 | 44.927 | 15.8604 | 10.1364 | 2.3287 | 2.493 | 4.6434 | 3.996 | 9.4651 | 6.9721 | 25.9968 | 28.4898 | 37.9549 | 44.927 | 0
-1.0877 | 6.4643 | 1.7637 | 1.6456 | 1.8187 | 2.2912 | 5.2281 | 3.5825 | 5.3766 | 7.0222 | 12.2503 | 15.8327 | -1.0877 | 6.4643 | 1.7637 | 1.6456 | 1.8187 | 2.3012 | 5.2281 | 3.5825 | 5.3766 | 7.0222 | 12.2503 | 15.8327 | 0
9.5656 | 8.7725 | 2.1189 | 2.1783 | 3.5943 | 3.3566 | 7.8914 | 5.7131 | 18.3381 | 20.5164 | 28.4078 | 34.1209 | 9.5656 | 8.7725 | 2.1189 | 2.1783 | 3.5943 | 3.3666 | 7.8914 | 5.7131 | 18.3381 | 20.5164 | 28.4078 | 34.1209 | 0
5.2751 | 7.8429 | 1.9758 | 1.9638 | 2.8792 | 2.9275 | 6.8188 | 4.855 | 13.1181 | 15.0818 | 21.9006 | 26.7557 | 5.2751 | 7.8429 | 1.9758 | 1.9638 | 2.8792 | 2.9375 | 6.8188 | 4.855 | 13.1181 | 15.0818 | 21.9006 | 26.7557 | 0
4.8547 | 7.7519 | 1.9618 | 1.9427 | 2.8091 | 2.8855 | 6.7137 | 4.7709 | 12.6066 | 14.5493 | 21.263 | 26.0339 | 4.8547 | 7.7519 | 1.9618 | 1.9427 | 2.8091 | 2.8955 | 6.7137 | 4.7709 | 12.6066 | 14.5493 | 21.263 | 26.0339 | 0
4.1225 | 7.5932 | 1.9374 | 1.9061 | 2.6871 | 2.8123 | 6.5306 | 4.6245 | 11.7157 | 13.6219 | 20.1525 | 24.777 | 4.1225 | 7.5932 | 1.9374 | 1.9061 | 2.6871 | 2.8223 | 6.5306 | 4.6245 | 11.7157 | 13.6219 | 20.1525 | 24.777 | 0
0.12817 | 6.7278 | 1.8043 | 1.7064 | 2.0214 | 2.4128 | 5.532 | 3.8256 | 6.8559 | 8.5623 | 14.0944 | 17.92 | 0.12817 | 6.7278 | 1.8043 | 1.7064 | 2.0214 | 2.4228 | 5.532 | 3.8256 | 6.8559 | 8.5623 | 14.0944 | 17.92 | 0
3.1497 | 7.3824 | 1.905 | 1.8575 | 2.525 | 2.715 | 6.2874 | 4.4299 | 10.5322 | 12.3897 | 18.6771 | 23.107 | 3.1497 | 7.3824 | 1.905 | 1.8575 | 2.525 | 2.725 | 6.2874 | 4.4299 | 10.5322 | 12.3897 | 18.6771 | 23.107 | 0
0.004088 | 6.7009 | 1.8001 | 1.7002 | 2.0007 | 2.4004 | 5.501 | 3.8008 | 6.705 | 8.4052 | 13.9062 | 17.707 | 0.004088 | 6.7009 | 1.8001 | 1.7002 | 2.0007 | 2.4104 | 5.501 | 3.8008 | 6.705 | 8.4052 | 13.9062 | 17.707 | 0
2.664 | 7.2772 | 1.8888 | 1.8332 | 2.444 | 2.6664 | 6.166 | 4.3328 | 9.9412 | 11.7744 | 17.9403 | 22.2731 | 2.664 | 7.2772 | 1.8888 | 1.8332 | 2.444 | 2.6764 | 6.166 | 4.3328 | 9.9412 | 11.7744 | 17.9403 | 22.2731 | 0
16.3601 | 10.2447 | 2.3453 | 2.518 | 4.7267 | 4.036 | 9.59 | 7.072 | 26.6047 | 29.1227 | 38.7127 | 45.7848 | 16.3601 | 10.2447 | 2.3453 | 2.518 | 4.7267 | 4.046 | 9.59 | 7.072 | 26.6047 | 29.1227 | 38.7127 | 45.7848 | 0
1.1157 | 6.9417 | 1.8372 | 1.7558 | 2.186 | 2.5116 | 5.7789 | 4.0231 | 8.0575 | 9.8133 | 15.5922 | 19.6153 | 1.1157 | 6.9417 | 1.8372 | 1.7558 | 2.186 | 2.5216 | 5.7789 | 4.0231 | 8.0575 | 9.8133 | 15.5922 | 19.6153 | 0
8.3578 | 8.5109 | 2.0786 | 2.1179 | 3.393 | 3.2358 | 7.5894 | 5.4716 | 16.8686 | 18.9865 | 26.576 | 32.0475 | 8.3578 | 8.5109 | 2.0786 | 2.1179 | 3.393 | 3.2458 | 7.5894 | 5.4716 | 16.8686 | 18.9865 | 26.576 | 32.0475 | 0
-3.237 | 5.9986 | 1.6921 | 1.5381 | 1.4605 | 2.0763 | 4.6907 | 3.1526 | 2.7616 | 4.2998 | 8.9905 | 12.1431 | -3.237 | 5.9986 | 1.6921 | 1.5381 | 1.4605 | 2.0863 | 4.6907 | 3.1526 | 2.7616 | 4.2998 | 8.9905 | 12.1431 | 0
3.8189 | 7.5274 | 1.9273 | 1.8909 | 2.6365 | 2.7819 | 6.4547 | 4.5638 | 11.3463 | 13.2373 | 19.692 | 24.2558 | 3.8189 | 7.5274 | 1.9273 | 1.8909 | 2.6365 | 2.7919 | 6.4547 | 4.5638 | 11.3463 | 13.2373 | 19.692 | 24.2558 | 0
9.7219 | 8.8064 | 2.1241 | 2.1861 | 3.6203 | 3.3722 | 7.9305 | 5.7444 | 18.5283 | 20.7144 | 28.6448 | 34.3892 | 9.7219 | 8.8064 | 2.1241 | 2.1861 | 3.6203 | 3.3822 | 7.9305 | 5.7444 | 18.5283 | 20.7144 | 28.6448 | 34.3892 | 0
8.9915 | 8.6482 | 2.0997 | 2.1496 | 3.4986 | 3.2992 | 7.7479 | 5.5983 | 17.6397 | 19.7893 | 27.5372 | 33.1355 | 8.9915 | 8.6482 | 2.0997 | 2.1496 | 3.4986 | 3.3092 | 7.7479 | 5.5983 | 17.6397 | 19.7893 | 27.5372 | 33.1355 | 0
-3.6954 | 5.8993 | 1.6768 | 1.5152 | 1.3841 | 2.0305 | 4.5762 | 3.0609 | 2.2039 | 3.7192 | 8.2953 | 11.3562 | -3.6954 | 5.8993 | 1.6768 | 1.5152 | 1.3841 | 2.0405 | 4.5762 | 3.0609 | 2.2039 | 3.7192 | 8.2953 | 11.3562 | 0
10.0738 | 8.8827 | 2.1358 | 2.2037 | 3.679 | 3.4074 | 8.0185 | 5.8148 | 18.9565 | 21.1602 | 29.1787 | 34.9934 | 10.0738 | 8.8827 | 2.1358 | 2.2037 | 3.679 | 3.4174 | 8.0185 | 5.8148 | 18.9565 | 21.1602 | 29.1787 | 34.9934 | 0
0.046038 | 6.71 | 1.8015 | 1.7023 | 2.0077 | 2.4046 | 5.5115 | 3.8092 | 6.756 | 8.4583 | 13.9698 | 17.779 | 0.046038 | 6.71 | 1.8015 | 1.7023 | 2.0077 | 2.4146 | 5.5115 | 3.8092 | 6.756 | 8.4583 | 13.9698 | 17.779 | 0
11.9431 | 9.2877 | 2.1981 | 2.2972 | 3.9905 | 3.5943 | 8.4858 | 6.1886 | 21.2308 | 23.528 | 32.0138 | 38.2024 | 11.9431 | 9.2877 | 2.1981 | 2.2972 | 3.9905 | 3.6043 | 8.4858 | 6.1886 | 21.2308 | 23.528 | 32.0138 | 38.2024 | 0
10.2351 | 8.9176 | 2.1412 | 2.2118 | 3.7058 | 3.4235 | 8.0588 | 5.847 | 19.1527 | 21.3645 | 29.4232 | 35.2703 | 10.2351 | 8.9176 | 2.1412 | 2.2118 | 3.7058 | 3.4335 | 8.0588 | 5.847 | 19.1527 | 21.3645 | 29.4232 | 35.2703 | 0
16.0073 | 10.1682 | 2.3336 | 2.5004 | 4.6679 | 4.0007 | 9.5018 | 7.0015 | 26.1755 | 28.6759 | 38.1777 | 45.1791 | 16.0073 | 10.1682 | 2.3336 | 2.5004 | 4.6679 | 4.0107 | 9.5018 | 7.0015 | 26.1755 | 28.6759 | 38.1777 | 45.1791 | 0
11.2117 | 9.1292 | 2.1737 | 2.2606 | 3.8686 | 3.5212 | 8.3029 | 6.0423 | 20.3409 | 22.6015 | 30.9044 | 36.9468 | 11.2117 | 9.1292 | 2.1737 | 2.2606 | 3.8686 | 3.5312 | 8.3029 | 6.0423 | 20.3409 | 22.6015 | 30.9044 | 36.9468 | 0
0.7651 | 6.8658 | 1.8255 | 1.7383 | 2.1275 | 2.4765 | 5.6913 | 3.953 | 7.6309 | 9.3691 | 15.0604 | 19.0134 | 0.7651 | 6.8658 | 1.8255 | 1.7383 | 2.1275 | 2.4865 | 5.6913 | 3.953 | 7.6309 | 9.3691 | 15.0604 | 19.0134 | 0
-2.5424 | 6.1491 | 1.7153 | 1.5729 | 1.5763 | 2.1458 | 4.8644 | 3.2915 | 3.6068 | 5.1796 | 10.044 | 13.3356 | -2.5424 | 6.1491 | 1.7153 | 1.5729 | 1.5763 | 2.1558 | 4.8644 | 3.2915 | 3.6068 | 5.1796 | 10.044 | 13.3356 | 0
6.6128 | 8.1328 | 2.0204 | 2.0306 | 3.1021 | 3.0613 | 7.1532 | 5.1226 | 14.7456 | 16.7763 | 23.9295 | 29.052 | 6.6128 | 8.1328 | 2.0204 | 2.0306 | 3.1021 | 3.0713 | 7.1532 | 5.1226 | 14.7456 | 16.7763 | 23.9295 | 29.052 | 0
-0.13011 | 6.6718 | 1.7957 | 1.6935 | 1.9783 | 2.387 | 5.4675 | 3.774 | 6.5417 | 8.2352 | 13.7027 | 17.4766 | -0.13011 | 6.6718 | 1.7957 | 1.6935 | 1.9783 | 2.397 | 5.4675 | 3.774 | 6.5417 | 8.2352 | 13.7027 | 17.4766 | 0
2.5146 | 7.2448 | 1.8838 | 1.8257 | 2.4191 | 2.6515 | 6.1286 | 4.3029 | 9.7594 | 11.5851 | 17.7138 | 22.0167 | 2.5146 | 7.2448 | 1.8838 | 1.8257 | 2.4191 | 2.6615 | 6.1286 | 4.3029 | 9.7594 | 11.5851 | 17.7138 | 22.0167 | 0
14.496 | 9.8408 | 2.2832 | 2.4248 | 4.416 | 3.8496 | 9.124 | 6.6992 | 24.3368 | 26.7616 | 35.8856 | 42.5848 | 14.496 | 9.8408 | 2.2832 | 2.4248 | 4.416 | 3.8596 | 9.124 | 6.6992 | 24.3368 | 26.7616 | 35.8856 | 42.5848 | 0
6.3767 | 8.0816 | 2.0126 | 2.0188 | 3.0628 | 3.0377 | 7.0942 | 5.0753 | 14.4583 | 16.4771 | 23.5713 | 28.6466 | 6.3767 | 8.0816 | 2.0126 | 2.0188 | 3.0628 | 3.0477 | 7.0942 | 5.0753 | 14.4583 | 16.4771 | 23.5713 | 28.6466 | 0
-0.66363 | 6.5562 | 1.7779 | 1.6668 | 1.8894 | 2.3336 | 5.3341 | 3.6673 | 5.8926 | 7.5594 | 12.8935 | 16.5608 | -0.66363 | 6.5562 | 1.7779 | 1.6668 | 1.8894 | 2.3436 | 5.3341 | 3.6673 | 5.8926 | 7.5594 | 12.8935 | 16.5608 | 0
6.6236 | 8.1351 | 2.0208 | 2.0312 | 3.1039 | 3.0624 | 7.1559 | 5.1247 | 14.7587 | 16.7899 | 23.9458 | 29.0705 | 6.6236 | 8.1351 | 2.0208 | 2.0312 | 3.1039 | 3.0724 | 7.1559 | 5.1247 | 14.7587 | 16.7899 | 23.9458 | 29.0705 | 0
-1.4404 | 6.3879 | 1.752 | 1.628 | 1.7599 | 2.256 | 5.1399 | 3.5119 | 4.9476 | 6.5755 | 11.7155 | 15.2274 | -1.4404 | 6.3879 | 1.752 | 1.628 | 1.7599 | 2.266 | 5.1399 | 3.5119 | 4.9476 | 6.5755 | 11.7155 | 15.2274 | 0
3.8707 | 7.5386 | 1.929 | 1.8935 | 2.6451 | 2.7871 | 6.4677 | 4.5741 | 11.4093 | 13.3029 | 19.7705 | 24.3447 | 3.8707 | 7.5386 | 1.929 | 1.8935 | 2.6451 | 2.7971 | 6.4677 | 4.5741 | 11.4093 | 13.3029 | 19.7705 | 24.3447 | 0
-11.3239 | 4.2465 | 1.4225 | 1.1338 | 0.11268 | 1.2676 | 2.669 | 1.5352 | -7.0774 | -5.9436 | -3.2746 | -1.7394 | -11.3239 | 4.2465 | 1.4225 | 1.1338 | 0.11268 | 1.2776 | 2.669 | 1.5352 | -7.0774 | -5.9436 | -3.2746 | -1.7394 | 0
8.374 | 8.5144 | 2.0791 | 2.1187 | 3.3957 | 3.2374 | 7.5935 | 5.4748 | 16.8884 | 19.0071 | 26.6006 | 32.0754 | 8.374 | 8.5144 | 2.0791 | 2.1187 | 3.3957 | 3.2474 | 7.5935 | 5.4748 | 16.8884 | 19.0071 | 26.6006 | 32.0754 | 0
12.9704 | 9.5102 | 2.2323 | 2.3485 | 4.1617 | 3.697 | 8.7426 | 6.3941 | 22.4806 | 24.8291 | 33.5717 | 39.9658 | 12.9704 | 9.5102 | 2.2323 | 2.3485 | 4.1617 | 3.707 | 8.7426 | 6.3941 | 22.4806 | 24.8291 | 33.5717 | 39.9658 | 0
1.7719 | 7.0839 | 1.8591 | 1.7886 | 2.2953 | 2.5772 | 5.943 | 4.1544 | 8.8558 | 10.6444 | 16.5874 | 20.7418 | 1.7719 | 7.0839 | 1.8591 | 1.7886 | 2.2953 | 2.5872 | 5.943 | 4.1544 | 8.8558 | 10.6444 | 16.5874 | 20.7418 | 0
-0.26064 | 6.6435 | 1.7913 | 1.687 | 1.9566 | 2.3739 | 5.4348 | 3.7479 | 6.3829 | 8.0699 | 13.5047 | 17.2526 | -0.26064 | 6.6435 | 1.7913 | 1.687 | 1.9566 | 2.3839 | 5.4348 | 3.7479 | 6.3829 | 8.0699 | 13.5047 | 17.2526 | 0
8.9346 | 8.6358 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7336 | 5.5869 | 17.5704 | 19.7171 | 27.4507 | 33.0376 | 8.9346 | 8.6358 | 2.0978 | 2.1467 | 3.4891 | 3.3035 | 7.7336 | 5.5869 | 17.5704 | 19.7171 | 27.4507 | 33.0376 | 0
8.9889 | 8.6476 | 2.0996 | 2.1494 | 3.4981 | 3.2989 | 7.7472 | 5.5978 | 17.6365 | 19.7859 | 27.5332 | 33.1309 | 8.9889 | 8.6476 | 2.0996 | 2.1494 | 3.4981 | 3.3089 | 7.7472 | 5.5978 | 17.6365 | 19.7859 | 27.5332 | 33.1309 | 0
5.2835 | 7.8448 | 1.9761 | 1.9642 | 2.8806 | 2.9284 | 6.8209 | 4.8567 | 13.1283 | 15.0925 | 21.9133 | 26.77 | 5.2835 | 7.8448 | 1.9761 | 1.9642 | 2.8806 | 2.9384 | 6.8209 | 4.8567 | 13.1283 | 15.0925 | 21.9133 | 26.77 | 0
9.4524 | 8.748 | 2.1151 | 2.1726 | 3.5754 | 3.3452 | 7.8631 | 5.6905 | 18.2004 | 20.373 | 28.2361 | 33.9266 | 9.4524 | 8.748 | 2.1151 | 2.1726 | 3.5754 | 3.3552 | 7.8631 | 5.6905 | 18.2004 | 20.373 | 28.2361 | 33.9266 | 0
12.1174 | 9.3254 | 2.2039 | 2.3059 | 4.0196 | 3.6117 | 8.5294 | 6.2235 | 21.4429 | 23.7487 | 32.2781 | 38.5016 | 12.1174 | 9.3254 | 2.2039 | 2.3059 | 4.0196 | 3.6217 | 8.5294 | 6.2235 | 21.4429 | 23.7487 | 32.2781 | 38.5016 | 0
2.5021 | 7.2421 | 1.8834 | 1.8251 | 2.417 | 2.6502 | 6.1255 | 4.3004 | 9.7443 | 11.5694 | 17.6949 | 21.9953 | 2.5021 | 7.2421 | 1.8834 | 1.8251 | 2.417 | 2.6602 | 6.1255 | 4.3004 | 9.7443 | 11.5694 | 17.6949 | 21.9953 | 0
0.91537 | 6.8983 | 1.8305 | 1.7458 | 2.1526 | 2.4915 | 5.7288 | 3.9831 | 7.8137 | 9.5595 | 15.2883 | 19.2714 | 0.91537 | 6.8983 | 1.8305 | 1.7458 | 2.1526 | 2.5015 | 5.7288 | 3.9831 | 7.8137 | 9.5595 | 15.2883 | 19.2714 | 0
-1.7202 | 6.3273 | 1.7427 | 1.614 | 1.7133 | 2.228 | 5.07 | 3.456 | 4.6071 | 6.2211 | 11.2911 | 14.7471 | -1.7202 | 6.3273 | 1.7427 | 1.614 | 1.7133 | 2.238 | 5.07 | 3.456 | 4.6071 | 6.2211 | 11.2911 | 14.7471 | 0
7.3217 | 8.2864 | 2.0441 | 2.0661 | 3.2203 | 3.1322 | 7.3304 | 5.2643 | 15.608 | 17.6741 | 25.0046 | 30.2689 | 7.3217 | 8.2864 | 2.0441 | 2.0661 | 3.2203 | 3.1422 | 7.3304 | 5.2643 | 15.608 | 17.6741 | 25.0046 | 30.2689 | 0
7.9757 | 8.4281 | 2.0659 | 2.0988 | 3.3293 | 3.1976 | 7.4939 | 5.3951 | 16.4037 | 18.5025 | 25.9965 | 31.3916 | 7.9757 | 8.4281 | 2.0659 | 2.0988 | 3.3293 | 3.2076 | 7.4939 | 5.3951 | 16.4037 | 18.5025 | 25.9965 | 31.3916 | 0
-2.8082 | 6.0916 | 1.7064 | 1.5596 | 1.532 | 2.1192 | 4.798 | 3.2384 | 3.2834 | 4.843 | 9.6409 | 12.8793 | -2.8082 | 6.0916 | 1.7064 | 1.5596 | 1.532 | 2.1292 | 4.798 | 3.2384 | 3.2834 | 4.843 | 9.6409 | 12.8793 | 0
-1.3037 | 6.4175 | 1.7565 | 1.6348 | 1.7827 | 2.2696 | 5.1741 | 3.5393 | 5.1139 | 6.7487 | 11.9228 | 15.462 | -1.3037 | 6.4175 | 1.7565 | 1.6348 | 1.7827 | 2.2796 | 5.1741 | 3.5393 | 5.1139 | 6.7487 | 11.9228 | 15.462 | 0
0.17091 | 6.737 | 1.8057 | 1.7085 | 2.0285 | 2.4171 | 5.5427 | 3.8342 | 6.9079 | 8.6165 | 14.1592 | 17.9934 | 0.17091 | 6.737 | 1.8057 | 1.7085 | 2.0285 | 2.4271 | 5.5427 | 3.8342 | 6.9079 | 8.6165 | 14.1592 | 17.9934 | 0
-7.6486 | 5.0428 | 1.545 | 1.3176 | 0.72523 | 1.6351 | 3.5878 | 2.2703 | -2.6058 | -1.2883 | 2.2996 | 4.5698 | -7.6486 | 5.0428 | 1.545 | 1.3176 | 0.72523 | 1.6451 | 3.5878 | 2.2703 | -2.6058 | -1.2883 | 2.2996 | 4.5698 | 0
7.5446 | 8.3347 | 2.0515 | 2.0772 | 3.2574 | 3.1545 | 7.3862 | 5.3089 | 15.8793 | 17.9565 | 25.3427 | 30.6516 | 7.5446 | 8.3347 | 2.0515 | 2.0772 | 3.2574 | 3.1645 | 7.3862 | 5.3089 | 15.8793 | 17.9565 | 25.3427 | 30.6516 | 0
9.7001 | 8.8017 | 2.1233 | 2.185 | 3.6167 | 3.37 | 7.925 | 5.74 | 18.5018 | 20.6869 | 28.6119 | 34.3519 | 9.7001 | 8.8017 | 2.1233 | 2.185 | 3.6167 | 3.38 | 7.925 | 5.74 | 18.5018 | 20.6869 | 28.6119 | 34.3519 | 0
8.0543 | 8.4451 | 2.0685 | 2.1027 | 3.3424 | 3.2054 | 7.5136 | 5.4109 | 16.4994 | 18.6021 | 26.1157 | 31.5266 | 8.0543 | 8.4451 | 2.0685 | 2.1027 | 3.3424 | 3.2154 | 7.5136 | 5.4109 | 16.4994 | 18.6021 | 26.1157 | 31.5266 | 0
-1.2755 | 6.4236 | 1.7575 | 1.6362 | 1.7874 | 2.2725 | 5.1811 | 3.5449 | 5.1482 | 6.7844 | 11.9655 | 15.5104 | -1.2755 | 6.4236 | 1.7575 | 1.6362 | 1.7874 | 2.2825 | 5.1811 | 3.5449 | 5.1482 | 6.7844 | 11.9655 | 15.5104 | 0
1.6532 | 7.0582 | 1.8551 | 1.7827 | 2.2755 | 2.5653 | 5.9133 | 4.1306 | 8.7114 | 10.494 | 16.4073 | 20.538 | 1.6532 | 7.0582 | 1.8551 | 1.7827 | 2.2755 | 2.5753 | 5.9133 | 4.1306 | 8.7114 | 10.494 | 16.4073 | 20.538 | 0
4.0014 | 7.567 | 1.9334 | 1.9001 | 2.6669 | 2.8001 | 6.5004 | 4.6003 | 11.5684 | 13.4685 | 19.9689 | 24.5692 | 4.0014 | 7.567 | 1.9334 | 1.9001 | 2.6669 | 2.8101 | 6.5004 | 4.6003 | 11.5684 | 13.4685 | 19.9689 | 24.5692 | 0
9.7211 | 8.8062 | 2.124 | 2.1861 | 3.6202 | 3.3721 | 7.9303 | 5.7442 | 18.5273 | 20.7134 | 28.6437 | 34.3879 | 9.7211 | 8.8062 | 2.124 | 2.1861 | 3.6202 | 3.3821 | 7.9303 | 5.7442 | 18.5273 | 20.7134 | 28.6437 | 34.3879 | 0
18.4405 | 10.6954 | 2.4147 | 2.622 | 5.0734 | 4.2441 | 10.1101 | 7.4881 | 29.136 | 31.758 | 41.8681 | 49.3562 | 18.4405 | 10.6954 | 2.4147 | 2.622 | 5.0734 | 4.2541 | 10.1101 | 7.4881 | 29.136 | 31.758 | 41.8681 | 49.3562 | 0
6.7586 | 8.1644 | 2.0253 | 2.0379 | 3.1264 | 3.0759 | 7.1896 | 5.1517 | 14.9229 | 16.9609 | 24.1505 | 29.3022 | 6.7586 | 8.1644 | 2.0253 | 2.0379 | 3.1264 | 3.0859 | 7.1896 | 5.1517 | 14.9229 | 16.9609 | 24.1505 | 29.3022 | 0
17.2651 | 10.4408 | 2.3755 | 2.5633 | 4.8775 | 4.1265 | 9.8163 | 7.253 | 27.7059 | 30.2692 | 40.0855 | 47.3385 | 17.2651 | 10.4408 | 2.3755 | 2.5633 | 4.8775 | 4.1365 | 9.8163 | 7.253 | 27.7059 | 30.2692 | 40.0855 | 47.3385 | 0
-4.1978 | 5.7905 | 1.6601 | 1.4901 | 1.3004 | 1.9802 | 4.4506 | 2.9604 | 1.5927 | 3.0828 | 7.5334 | 10.4938 | -4.1978 | 5.7905 | 1.6601 | 1.4901 | 1.3004 | 1.9902 | 4.4506 | 2.9604 | 1.5927 | 3.0828 | 7.5334 | 10.4938 | 0
7.4729 | 8.3191 | 2.0491 | 2.0736 | 3.2455 | 3.1473 | 7.3682 | 5.2946 | 15.7921 | 17.8657 | 25.2339 | 30.5285 | 7.4729 | 8.3191 | 2.0491 | 2.0736 | 3.2455 | 3.1573 | 7.3682 | 5.2946 | 15.7921 | 17.8657 | 25.2339 | 30.5285 | 0
-0.8847 | 6.5083 | 1.7705 | 1.6558 | 1.8525 | 2.3115 | 5.2788 | 3.6231 | 5.6236 | 7.2794 | 12.5582 | 16.1813 | -0.8847 | 6.5083 | 1.7705 | 1.6558 | 1.8525 | 2.3215 | 5.2788 | 3.6231 | 5.6236 | 7.2794 | 12.5582 | 16.1813 | 0
14.5788 | 9.8587 | 2.286 | 2.4289 | 4.4298 | 3.8579 | 9.1447 | 6.7158 | 24.4376 | 26.8665 | 36.0112 | 42.727 | 14.5788 | 9.8587 | 2.286 | 2.4289 | 4.4298 | 3.8679 | 9.1447 | 6.7158 | 24.4376 | 26.8665 | 36.0112 | 42.727 | 0
0.12537 | 6.7272 | 1.8042 | 1.7063 | 2.0209 | 2.4125 | 5.5313 | 3.8251 | 6.8525 | 8.5588 | 14.0901 | 17.9152 | 0.12537 | 6.7272 | 1.8042 | 1.7063 | 2.0209 | 2.4225 | 5.5313 | 3.8251 | 6.8525 | 8.5588 | 14.0901 | 17.9152 | 0
4.2245 | 7.6153 | 1.9408 | 1.9112 | 2.7041 | 2.8224 | 6.5561 | 4.6449 | 11.8398 | 13.751 | 20.3071 | 24.952 | 4.2245 | 7.6153 | 1.9408 | 1.9112 | 2.7041 | 2.8324 | 6.5561 | 4.6449 | 11.8398 | 13.751 | 20.3071 | 24.952 | 0
15.0219 | 9.9547 | 2.3007 | 2.4511 | 4.5036 | 3.9022 | 9.2555 | 6.8044 | 24.9766 | 27.4277 | 36.6832 | 43.4875 | 15.0219 | 9.9547 | 2.3007 | 2.4511 | 4.5036 | 3.9122 | 9.2555 | 6.8044 | 24.9766 | 27.4277 | 36.6832 | 43.4875 | 0
-2.3623 | 6.1882 | 1.7213 | 1.5819 | 1.6063 | 2.1638 | 4.9094 | 3.3275 | 3.8258 | 5.4077 | 10.3171 | 13.6446 | -2.3623 | 6.1882 | 1.7213 | 1.5819 | 1.6063 | 2.1738 | 4.9094 | 3.3275 | 3.8258 | 5.4077 | 10.3171 | 13.6446 | 0
-0.42982 | 6.6069 | 1.7857 | 1.6785 | 1.9284 | 2.357 | 5.3925 | 3.714 | 6.177 | 7.8556 | 13.2481 | 16.9621 | -0.42982 | 6.6069 | 1.7857 | 1.6785 | 1.9284 | 2.367 | 5.3925 | 3.714 | 6.177 | 7.8556 | 13.2481 | 16.9621 | 0
7.7003 | 8.3684 | 2.0567 | 2.085 | 3.2834 | 3.17 | 7.4251 | 5.3401 | 16.0687 | 18.1537 | 25.5788 | 30.9188 | 7.7003 | 8.3684 | 2.0567 | 2.085 | 3.2834 | 3.18 | 7.4251 | 5.3401 | 16.0687 | 18.1537 | 25.5788 | 30.9188 | 0
5.0337 | 7.7906 | 1.9678 | 1.9517 | 2.839 | 2.9034 | 6.7584 | 4.8067 | 12.8244 | 14.776 | 21.5345 | 26.3412 | 5.0337 | 7.7906 | 1.9678 | 1.9517 | 2.839 | 2.9134 | 6.7584 | 4.8067 | 12.8244 | 14.776 | 21.5345 | 26.3412 | 0
3.2793 | 7.4105 | 1.9093 | 1.864 | 2.5465 | 2.7279 | 6.3198 | 4.4559 | 10.6898 | 12.5538 | 18.8736 | 23.3294 | 3.2793 | 7.4105 | 1.9093 | 1.864 | 2.5465 | 2.7379 | 6.3198 | 4.4559 | 10.6898 | 12.5538 | 18.8736 | 23.3294 | 0
-0.40881 | 6.6114 | 1.7864 | 1.6796 | 1.9319 | 2.3591 | 5.3978 | 3.7182 | 6.2026 | 7.8822 | 13.28 | 16.9982 | -0.40881 | 6.6114 | 1.7864 | 1.6796 | 1.9319 | 2.3691 | 5.3978 | 3.7182 | 6.2026 | 7.8822 | 13.28 | 16.9982 | 0
12.3703 | 9.3802 | 2.2123 | 2.3185 | 4.0617 | 3.637 | 8.5926 | 6.2741 | 21.7505 | 24.069 | 32.6616 | 38.9356 | 12.3703 | 9.3802 | 2.2123 | 2.3185 | 4.0617 | 3.647 | 8.5926 | 6.2741 | 21.7505 | 24.069 | 32.6616 | 38.9356 | 0
9.2318 | 8.7002 | 2.1077 | 2.1616 | 3.5386 | 3.3232 | 7.8079 | 5.6464 | 17.932 | 20.0936 | 27.9015 | 33.5479 | 9.2318 | 8.7002 | 2.1077 | 2.1616 | 3.5386 | 3.3332 | 7.8079 | 5.6464 | 17.932 | 20.0936 | 27.9015 | 33.5479 | 0
9.9205 | 8.8494 | 2.1307 | 2.196 | 3.6534 | 3.392 | 7.9801 | 5.7841 | 18.7699 | 20.9659 | 28.946 | 34.7301 | 9.9205 | 8.8494 | 2.1307 | 2.196 | 3.6534 | 3.402 | 7.9801 | 5.7841 | 18.7699 | 20.9659 | 28.946 | 34.7301 | 0
12.8623 | 9.4868 | 2.2287 | 2.3431 | 4.1437 | 3.6862 | 8.7156 | 6.3725 | 22.3491 | 24.6922 | 33.4078 | 39.7802 | 12.8623 | 9.4868 | 2.2287 | 2.3431 | 4.1437 | 3.6962 | 8.7156 | 6.3725 | 22.3491 | 24.6922 | 33.4078 | 39.7802 | 0
-2.6898 | 6.1172 | 1.7103 | 1.5655 | 1.5517 | 2.131 | 4.8276 | 3.262 | 3.4274 | 4.9929 | 9.8205 | 13.0825 | -2.6898 | 6.1172 | 1.7103 | 1.5655 | 1.5517 | 2.141 | 4.8276 | 3.262 | 3.4274 | 4.9929 | 9.8205 | 13.0825 | 0
10.976 | 9.0781 | 2.1659 | 2.2488 | 3.8293 | 3.4976 | 8.244 | 5.9952 | 20.0542 | 22.303 | 30.547 | 36.5422 | 10.976 | 9.0781 | 2.1659 | 2.2488 | 3.8293 | 3.5076 | 8.244 | 5.9952 | 20.0542 | 22.303 | 30.547 | 36.5422 | 0
6.1885 | 8.0408 | 2.0063 | 2.0094 | 3.0314 | 3.0189 | 7.0471 | 5.0377 | 14.2294 | 16.2388 | 23.2859 | 28.3237 | 6.1885 | 8.0408 | 2.0063 | 2.0094 | 3.0314 | 3.0289 | 7.0471 | 5.0377 | 14.2294 | 16.2388 | 23.2859 | 28.3237 | 0
-0.0097864 | 6.6979 | 1.7997 | 1.6995 | 1.9984 | 2.399 | 5.4976 | 3.798 | 6.6881 | 8.3876 | 13.8852 | 17.6832 | -0.0097864 | 6.6979 | 1.7997 | 1.6995 | 1.9984 | 2.409 | 5.4976 | 3.798 | 6.6881 | 8.3876 | 13.8852 | 17.6832 | 0
13.3212 | 9.5863 | 2.244 | 2.3661 | 4.2202 | 3.7321 | 8.8303 | 6.4642 | 22.9074 | 25.2735 | 34.1038 | 40.568 | 13.3212 | 9.5863 | 2.244 | 2.3661 | 4.2202 | 3.7421 | 8.8303 | 6.4642 | 22.9074 | 25.2735 | 34.1038 | 40.568 | 0
-0.72099 | 6.5438 | 1.776 | 1.664 | 1.8798 | 2.3279 | 5.3198 | 3.6558 | 5.8228 | 7.4867 | 12.8065 | 16.4623 | -0.72099 | 6.5438 | 1.776 | 1.664 | 1.8798 | 2.3379 | 5.3198 | 3.6558 | 5.8228 | 7.4867 | 12.8065 | 16.4623 | 0
-0.99952 | 6.4834 | 1.7667 | 1.65 | 1.8334 | 2.3 | 5.2501 | 3.6001 | 5.4839 | 7.1339 | 12.3841 | 15.9842 | -0.99952 | 6.4834 | 1.7667 | 1.65 | 1.8334 | 2.31 | 5.2501 | 3.6001 | 5.4839 | 7.1339 | 12.3841 | 15.9842 | 0
1.5168 | 7.0286 | 1.8506 | 1.7758 | 2.2528 | 2.5517 | 5.8792 | 4.1034 | 8.5455 | 10.3213 | 16.2005 | 20.3039 | 1.5168 | 7.0286 | 1.8506 | 1.7758 | 2.2528 | 2.5617 | 5.8792 | 4.1034 | 8.5455 | 10.3213 | 16.2005 | 20.3039 | 0
-0.58033 | 6.5743 | 1.7807 | 1.671 | 1.9033 | 2.342 | 5.3549 | 3.6839 | 5.9939 | 7.6649 | 13.0198 | 16.7038 | -0.58033 | 6.5743 | 1.7807 | 1.671 | 1.9033 | 2.352 | 5.3549 | 3.6839 | 5.9939 | 7.6649 | 13.0198 | 16.7038 | 0
0.17113 | 6.7371 | 1.8057 | 1.7086 | 2.0285 | 2.4171 | 5.5428 | 3.8342 | 6.9082 | 8.6168 | 14.1595 | 17.9938 | 0.17113 | 6.7371 | 1.8057 | 1.7086 | 2.0285 | 2.4271 | 5.5428 | 3.8342 | 6.9082 | 8.6168 | 14.1595 | 17.9938 | 0
0.074319 | 6.7161 | 1.8025 | 1.7037 | 2.0124 | 2.4074 | 5.5186 | 3.8149 | 6.7904 | 8.4941 | 14.0127 | 17.8276 | 0.074319 | 6.7161 | 1.8025 | 1.7037 | 2.0124 | 2.4174 | 5.5186 | 3.8149 | 6.7904 | 8.4941 | 14.0127 | 17.8276 | 0
1.085 | 6.9351 | 1.8362 | 1.7543 | 2.1808 | 2.5085 | 5.7713 | 4.017 | 8.0201 | 9.7744 | 15.5456 | 19.5626 | 1.085 | 6.9351 | 1.8362 | 1.7543 | 2.1808 | 2.5185 | 5.7713 | 4.017 | 8.0201 | 9.7744 | 15.5456 | 19.5626 | 0
-3.1212 | 6.0237 | 1.696 | 1.5439 | 1.4798 | 2.0879 | 4.7197 | 3.1758 | 2.9025 | 4.4464 | 9.1661 | 12.3419 | -3.1212 | 6.0237 | 1.696 | 1.5439 | 1.4798 | 2.0979 | 4.7197 | 3.1758 | 2.9025 | 4.4464 | 9.1661 | 12.3419 | 0
6.0895 | 8.0194 | 2.003 | 2.0045 | 3.0149 | 3.009 | 7.0224 | 5.0179 | 14.1089 | 16.1134 | 23.1357 | 28.1536 | 6.0895 | 8.0194 | 2.003 | 2.0045 | 3.0149 | 3.019 | 7.0224 | 5.0179 | 14.1089 | 16.1134 | 23.1357 | 28.1536 | 0
6.2141 | 8.0464 | 2.0071 | 2.0107 | 3.0357 | 3.0214 | 7.0535 | 5.0428 | 14.2605 | 16.2712 | 23.3247 | 28.3676 | 6.2141 | 8.0464 | 2.0071 | 2.0107 | 3.0357 | 3.0314 | 7.0535 | 5.0428 | 14.2605 | 16.2712 | 23.3247 | 28.3676 | 0
9.4624 | 8.7502 | 2.1154 | 2.1731 | 3.5771 | 3.3462 | 7.8656 | 5.6925 | 18.2126 | 20.3857 | 28.2513 | 33.9437 | 9.4624 | 8.7502 | 2.1154 | 2.1731 | 3.5771 | 3.3562 | 7.8656 | 5.6925 | 18.2126 | 20.3857 | 28.2513 | 33.9437 | 0
2.7991 | 7.3065 | 1.8933 | 1.84 | 2.4665 | 2.6799 | 6.1998 | 4.3598 | 10.1056 | 11.9456 | 18.1454 | 22.5052 | 2.7991 | 7.3065 | 1.8933 | 1.84 | 2.4665 | 2.6899 | 6.1998 | 4.3598 | 10.1056 | 11.9456 | 18.1454 | 22.5052 | 0
0.57475 | 6.8245 | 1.8192 | 1.7287 | 2.0958 | 2.4575 | 5.6437 | 3.915 | 7.3993 | 9.128 | 14.7717 | 18.6867 | 0.57475 | 6.8245 | 1.8192 | 1.7287 | 2.0958 | 2.4675 | 5.6437 | 3.915 | 7.3993 | 9.128 | 14.7717 | 18.6867 | 0
9.4411 | 8.7456 | 2.1147 | 2.1721 | 3.5735 | 3.3441 | 7.8603 | 5.6882 | 18.1866 | 20.3587 | 28.219 | 33.9072 | 9.4411 | 8.7456 | 2.1147 | 2.1721 | 3.5735 | 3.3541 | 7.8603 | 5.6882 | 18.1866 | 20.3587 | 28.219 | 33.9072 | 0
-1.3256 | 6.4128 | 1.7558 | 1.6337 | 1.7791 | 2.2674 | 5.1686 | 3.5349 | 5.0872 | 6.7209 | 11.8896 | 15.4244 | -1.3256 | 6.4128 | 1.7558 | 1.6337 | 1.7791 | 2.2774 | 5.1686 | 3.5349 | 5.0872 | 6.7209 | 11.8896 | 15.4244 | 0
6.3785 | 8.082 | 2.0126 | 2.0189 | 3.0631 | 3.0379 | 7.0946 | 5.0757 | 14.4605 | 16.4794 | 23.5741 | 28.6498 | 6.3785 | 8.082 | 2.0126 | 2.0189 | 3.0631 | 3.0479 | 7.0946 | 5.0757 | 14.4605 | 16.4794 | 23.5741 | 28.6498 | 0
1.0149 | 6.9199 | 1.8338 | 1.7507 | 2.1692 | 2.5015 | 5.7537 | 4.003 | 7.9348 | 9.6856 | 15.4393 | 19.4423 | 1.0149 | 6.9199 | 1.8338 | 1.7507 | 2.1692 | 2.5115 | 5.7537 | 4.003 | 7.9348 | 9.6856 | 15.4393 | 19.4423 | 0
3.1071 | 7.3732 | 1.9036 | 1.8554 | 2.5178 | 2.7107 | 6.2768 | 4.4214 | 10.4803 | 12.3356 | 18.6124 | 23.0338 | 3.1071 | 7.3732 | 1.9036 | 1.8554 | 2.5178 | 2.7207 | 6.2768 | 4.4214 | 10.4803 | 12.3356 | 18.6124 | 23.0338 | 0
8.6083 | 8.5651 | 2.0869 | 2.1304 | 3.4347 | 3.2608 | 7.6521 | 5.5217 | 17.1734 | 19.3038 | 26.9559 | 32.4776 | 8.6083 | 8.5651 | 2.0869 | 2.1304 | 3.4347 | 3.2708 | 7.6521 | 5.5217 | 17.1734 | 19.3038 | 26.9559 | 32.4776 | 0
-7.3979 | 5.0971 | 1.5534 | 1.3301 | 0.76701 | 1.6602 | 3.6505 | 2.3204 | -2.3008 | -0.97073 | 2.6798 | 5.0002 | -7.3979 | 5.0971 | 1.5534 | 1.3301 | 0.76701 | 1.6702 | 3.6505 | 2.3204 | -2.3008 | -0.97073 | 2.6798 | 5.0002 | 0
9.1391 | 8.6801 | 2.1046 | 2.157 | 3.5232 | 3.3139 | 7.7848 | 5.6278 | 17.8192 | 19.9762 | 27.7609 | 33.3887 | 9.1391 | 8.6801 | 2.1046 | 2.157 | 3.5232 | 3.3239 | 7.7848 | 5.6278 | 17.8192 | 19.9762 | 27.7609 | 33.3887 | 0
10.1185 | 8.8923 | 2.1373 | 2.2059 | 3.6864 | 3.4118 | 8.0296 | 5.8237 | 19.0108 | 21.2168 | 29.2464 | 35.0701 | 10.1185 | 8.8923 | 2.1373 | 2.2059 | 3.6864 | 3.4218 | 8.0296 | 5.8237 | 19.0108 | 21.2168 | 29.2464 | 35.0701 | 0
8.8895 | 8.6261 | 2.0963 | 2.1445 | 3.4816 | 3.289 | 7.7224 | 5.5779 | 17.5156 | 19.6601 | 27.3825 | 32.9604 | 8.8895 | 8.6261 | 2.0963 | 2.1445 | 3.4816 | 3.299 | 7.7224 | 5.5779 | 17.5156 | 19.6601 | 27.3825 | 32.9604 | 0
18.1174 | 10.6254 | 2.4039 | 2.6059 | 5.0196 | 4.2117 | 10.0293 | 7.4235 | 28.7428 | 31.3487 | 41.378 | 48.8015 | 18.1174 | 10.6254 | 2.4039 | 2.6059 | 5.0196 | 4.2217 | 10.0293 | 7.4235 | 28.7428 | 31.3487 | 41.378 | 48.8015 | 0
-4.172 | 5.7961 | 1.6609 | 1.4914 | 1.3047 | 1.9828 | 4.457 | 2.9656 | 1.6241 | 3.1155 | 7.5725 | 10.5381 | -4.172 | 5.7961 | 1.6609 | 1.4914 | 1.3047 | 1.9928 | 4.457 | 2.9656 | 1.6241 | 3.1155 | 7.5725 | 10.5381 | 0
4.7866 | 7.7371 | 1.9596 | 1.9393 | 2.7978 | 2.8787 | 6.6966 | 4.7573 | 12.5236 | 14.463 | 21.1596 | 25.9169 | 4.7866 | 7.7371 | 1.9596 | 1.9393 | 2.7978 | 2.8887 | 6.6966 | 4.7573 | 12.5236 | 14.463 | 21.1596 | 25.9169 | 0
8.5519 | 8.5529 | 2.0851 | 2.1276 | 3.4253 | 3.2552 | 7.638 | 5.5104 | 17.1048 | 19.2324 | 26.8704 | 32.3807 | 8.5519 | 8.5529 | 2.0851 | 2.1276 | 3.4253 | 3.2652 | 7.638 | 5.5104 | 17.1048 | 19.2324 | 26.8704 | 32.3807 | 0
6.8119 | 8.1759 | 2.0271 | 2.0406 | 3.1353 | 3.0812 | 7.203 | 5.1624 | 14.9878 | 17.0284 | 24.2313 | 29.3937 | 6.8119 | 8.1759 | 2.0271 | 2.0406 | 3.1353 | 3.0912 | 7.203 | 5.1624 | 14.9878 | 17.0284 | 24.2313 | 29.3937 | 0
-7.8754 | 4.9937 | 1.5375 | 1.3062 | 0.68743 | 1.6125 | 3.5311 | 2.2249 | -2.8818 | -1.5755 | 1.9556 | 4.1805 | -7.8754 | 4.9937 | 1.5375 | 1.3062 | 0.68743 | 1.6225 | 3.5311 | 2.2249 | -2.8818 | -1.5755 | 1.9556 | 4.1805 | 0
3.4751 | 7.4529 | 1.9158 | 1.8738 | 2.5792 | 2.7475 | 6.3688 | 4.495 | 10.9281 | 12.8018 | 19.1706 | 23.6656 | 3.4751 | 7.4529 | 1.9158 | 1.8738 | 2.5792 | 2.7575 | 6.3688 | 4.495 | 10.9281 | 12.8018 | 19.1706 | 23.6656 | 0
-3.9303 | 5.8484 | 1.669 | 1.5035 | 1.345 | 2.007 | 4.5174 | 3.0139 | 1.9181 | 3.4216 | 7.9391 | 10.953 | -3.9303 | 5.8484 | 1.669 | 1.5035 | 1.345 | 2.017 | 4.5174 | 3.0139 | 1.9181 | 3.4216 | 7.9391 | 10.953 | 0
11.6169 | 9.217 | 2.1872 | 2.2808 | 3.9362 | 3.5617 | 8.4042 | 6.1234 | 20.8339 | 23.1148 | 31.519 | 37.6424 | 11.6169 | 9.217 | 2.1872 | 2.2808 | 3.9362 | 3.5717 | 8.4042 | 6.1234 | 20.8339 | 23.1148 | 31.519 | 37.6424 | 0
6.6067 | 8.1315 | 2.0202 | 2.0303 | 3.1011 | 3.0607 | 7.1517 | 5.1213 | 14.7382 | 16.7685 | 23.9202 | 29.0415 | 6.6067 | 8.1315 | 2.0202 | 2.0303 | 3.1011 | 3.0707 | 7.1517 | 5.1213 | 14.7382 | 16.7685 | 23.9202 | 29.0415 | 0
3.6787 | 7.4971 | 1.9226 | 1.8839 | 2.6131 | 2.7679 | 6.4197 | 4.5357 | 11.1758 | 13.0597 | 19.4794 | 24.0151 | 3.6787 | 7.4971 | 1.9226 | 1.8839 | 2.6131 | 2.7779 | 6.4197 | 4.5357 | 11.1758 | 13.0597 | 19.4794 | 24.0151 | 0
10.0022 | 8.8671 | 2.1334 | 2.2001 | 3.667 | 3.4002 | 8.0005 | 5.8004 | 18.8693 | 21.0694 | 29.07 | 34.8704 | 10.0022 | 8.8671 | 2.1334 | 2.2001 | 3.667 | 3.4102 | 8.0005 | 5.8004 | 18.8693 | 21.0694 | 29.07 | 34.8704 | 0
2.8576 | 7.3192 | 1.8953 | 1.8429 | 2.4763 | 2.6858 | 6.2144 | 4.3715 | 10.1768 | 12.0197 | 18.2341 | 22.6056 | 2.8576 | 7.3192 | 1.8953 | 1.8429 | 2.4763 | 2.6958 | 6.2144 | 4.3715 | 10.1768 | 12.0197 | 18.2341 | 22.6056 | 0
-5.7356 | 5.4573 | 1.6088 | 1.4132 | 1.0441 | 1.8264 | 4.0661 | 2.6529 | -0.2783 | 1.1349 | 5.201 | 7.8539 | -5.7356 | 5.4573 | 1.6088 | 1.4132 | 1.0441 | 1.8364 | 4.0661 | 2.6529 | -0.2783 | 1.1349 | 5.201 | 7.8539 | 0
-0.24152 | 6.6477 | 1.7919 | 1.6879 | 1.9597 | 2.3758 | 5.4396 | 3.7517 | 6.4062 | 8.0941 | 13.5337 | 17.2854 | -0.24152 | 6.6477 | 1.7919 | 1.6879 | 1.9597 | 2.3858 | 5.4396 | 3.7517 | 6.4062 | 8.0941 | 13.5337 | 17.2854 | 0
-1.1184 | 6.4577 | 1.7627 | 1.6441 | 1.8136 | 2.2882 | 5.2204 | 3.5763 | 5.3393 | 6.9834 | 12.2038 | 15.7801 | -1.1184 | 6.4577 | 1.7627 | 1.6441 | 1.8136 | 2.2982 | 5.2204 | 3.5763 | 5.3393 | 6.9834 | 12.2038 | 15.7801 | 0
9.8841 | 8.8416 | 1.6146 | 2.1942 | 3.6474 | 3.3884 | 7.971 | 5.7768 | 18.7257 | 20.9199 | 28.891 | 34.6678 | 9.8841 | 8.8416 | 1.6146 | 2.1942 | 3.6474 | 3.3984 | 7.971 | 5.7768 | 18.7257 | 20.9199 | 28.891 | 34.6678 | 0
-5.5634 | 5.4946 | 1.9328 | 1.4218 | 1.0728 | 1.8437 | 4.1091 | 2.6873 | -0.068833 | 1.353 | 5.4621 | 8.1495 | -5.5634 | 5.4946 | 1.9328 | 1.4218 | 1.0728 | 1.8537 | 4.1091 | 2.6873 | -0.068833 | 1.353 | 5.4621 | 8.1495 | 0
3.9837 | 7.5631 | 2.3331 | 1.8992 | 2.6639 | 2.7984 | 6.4959 | 4.5967 | 11.5468 | 13.446 | 19.9419 | 24.5386 | 3.9837 | 7.5631 | 2.3331 | 1.8992 | 2.6639 | 2.8084 | 6.4959 | 4.5967 | 11.5468 | 13.446 | 19.9419 | 24.5386 | 0
15.9941 | 10.1654 | 1.7859 | 2.4997 | 4.6657 | 3.9994 | 9.4985 | 6.9988 | 26.1595 | 28.6592 | 38.1577 | 45.1566 | 15.9941 | 10.1654 | 1.7859 | 2.4997 | 4.6657 | 4.0094 | 9.4985 | 6.9988 | 26.1595 | 28.6592 | 38.1577 | 45.1566 | 0
-0.42261 | 6.6084 | 1.794 | 1.6789 | 1.9296 | 2.3577 | 5.3943 | 3.7155 | 6.1858 | 7.8647 | 13.259 | 16.9745 | -0.42261 | 6.6084 | 1.794 | 1.6789 | 1.9296 | 2.3677 | 5.3943 | 3.7155 | 6.1858 | 7.8647 | 13.259 | 16.9745 | 0
-0.18131 | 6.6607 | 1.9908 | 1.6909 | 1.9698 | 2.3819 | 5.4547 | 3.7637 | 6.4794 | 8.1703 | 13.625 | 17.3887 | -0.18131 | 6.6607 | 1.9908 | 1.6909 | 1.9698 | 2.3919 | 5.4547 | 3.7637 | 6.4794 | 8.1703 | 13.625 | 17.3887 | 0
5.7226 | 7.9399 | 2.0474 | 1.9861 | 2.9538 | 2.9723 | 6.9306 | 4.9445 | 13.6625 | 15.6486 | 22.5792 | 27.5238 | 5.7226 | 7.9399 | 2.0474 | 1.9861 | 2.9538 | 2.9823 | 6.9306 | 4.9445 | 13.6625 | 15.6486 | 22.5792 | 27.5238 | 0
7.4208 | 8.3078 | 2.0177 | 2.071 | 3.2368 | 3.1421 | 7.3552 | 5.2842 | 15.7286 | 17.7997 | 25.1549 | 30.439 | 7.4208 | 8.3078 | 2.0177 | 2.071 | 3.2368 | 3.1521 | 7.3552 | 5.2842 | 15.7286 | 17.7997 | 25.1549 | 30.439 | 0
6.5317 | 8.1152 | 2.2316 | 2.0266 | 3.0886 | 3.0532 | 7.1329 | 5.1063 | 14.6469 | 16.6735 | 23.8064 | 28.9127 | 6.5317 | 8.1152 | 2.2316 | 2.0266 | 3.0886 | 3.0632 | 7.1329 | 5.1063 | 14.6469 | 16.6735 | 23.8064 | 28.9127 | 0
12.9487 | 9.5056 | 2.2484 | 2.3474 | 4.1581 | 3.6949 | 8.7372 | 6.3897 | 22.4543 | 24.8017 | 33.5389 | 39.9286 | 12.9487 | 9.5056 | 2.2484 | 2.3474 | 4.1581 | 3.7049 | 8.7372 | 6.3897 | 22.4543 | 24.8017 | 33.5389 | 39.9286 | 0
13.4512 | 9.6144 | 1.8607 | 2.3726 | 4.2419 | 3.7451 | 8.8628 | 6.4902 | 23.0656 | 25.4382 | 34.301 | 40.7912 | 13.4512 | 9.6144 | 1.8607 | 2.3726 | 4.2419 | 3.7551 | 8.8628 | 6.4902 | 23.0656 | 25.4382 | 34.301 | 40.7912 | 0
1.8217 | 7.0947 | 2.0947 | 1.7911 | 2.3036 | 2.5822 | 5.9554 | 4.1643 | 8.9164 | 10.7075 | 16.6629 | 20.8272 | 1.8217 | 7.0947 | 2.0947 | 1.7911 | 2.3036 | 2.5922 | 5.9554 | 4.1643 | 8.9164 | 10.7075 | 16.6629 | 20.8272 | 0
8.8397 | 8.6153 | 1.8922 | 2.142 | 3.4733 | 3.284 | 7.7099 | 5.5679 | 17.455 | 19.597 | 27.3069 | 32.8748 | 8.8397 | 8.6153 | 1.8922 | 2.142 | 3.4733 | 3.294 | 7.7099 | 5.5679 | 17.455 | 19.597 | 27.3069 | 32.8748 | 0
2.7666 | 7.2994 | 2.0757 | 1.8383 | 2.4611 | 2.6767 | 6.1916 | 4.3533 | 10.066 | 11.9043 | 18.0959 | 22.4493 | 2.7666 | 7.2994 | 2.0757 | 1.8383 | 2.4611 | 2.6867 | 6.1916 | 4.3533 | 10.066 | 11.9043 | 18.0959 | 22.4493 | 0
8.2722 | 8.4923 | 1.8633 | 2.1136 | 3.3787 | 3.2272 | 7.568 | 5.4544 | 16.7645 | 18.8781 | 26.4461 | 31.9006 | 8.2722 | 8.4923 | 1.8633 | 2.1136 | 3.3787 | 3.2372 | 7.568 | 5.4544 | 16.7645 | 18.8781 | 26.4461 | 31.9006 | 0
1.8989 | 7.1114 | 2.0766 | 1.7949 | 2.3165 | 2.5899 | 5.9747 | 4.1798 | 9.0103 | 10.8052 | 16.7799 | 20.9597 | 1.8989 | 7.1114 | 2.0766 | 1.7949 | 2.3165 | 2.5999 | 5.9747 | 4.1798 | 9.0103 | 10.8052 | 16.7799 | 20.9597 | 0
8.2977 | 8.4978 | 2.1503 | 2.1149 | 3.3829 | 3.2298 | 7.5744 | 5.4595 | 16.7955 | 18.9104 | 26.4848 | 31.9444 | 8.2977 | 8.4978 | 2.1503 | 2.1149 | 3.3829 | 3.2398 | 7.5744 | 5.4595 | 16.7955 | 18.9104 | 26.4848 | 31.9444 | 0
10.5101 | 8.9772 | 2.0598 | 2.2255 | 3.7517 | 3.451 | 8.1275 | 5.902 | 19.4873 | 21.7128 | 29.8404 | 35.7424 | 10.5101 | 8.9772 | 2.0598 | 2.2255 | 3.7517 | 3.461 | 8.1275 | 5.902 | 19.4873 | 21.7128 | 29.8404 | 35.7424 | 0
7.7932 | 8.3885 | 2.4427 | 2.0897 | 3.2989 | 3.1793 | 7.4483 | 5.3586 | 16.1817 | 18.2714 | 25.7197 | 31.0784 | 7.7932 | 8.3885 | 2.4427 | 2.0897 | 3.2989 | 3.1893 | 7.4483 | 5.3586 | 16.1817 | 18.2714 | 25.7197 | 31.0784 | 0
19.2796 | 10.8773 | 1.7714 | 2.664 | 5.2133 | 4.328 | 10.3199 | 7.6559 | 30.1569 | 32.8209 | 43.1408 | 50.7967 | 19.2796 | 10.8773 | 1.7714 | 2.664 | 5.2133 | 4.338 | 10.3199 | 7.6559 | 30.1569 | 32.8209 | 43.1408 | 50.7967 | 0
-0.85792 | 6.5141 | 1.9787 | 1.6571 | 1.857 | 2.3142 | 5.2855 | 3.6284 | 5.6562 | 7.3133 | 12.5988 | 16.2272 | -0.85792 | 6.5141 | 1.9787 | 1.6571 | 1.857 | 2.3242 | 5.2855 | 3.6284 | 5.6562 | 7.3133 | 12.5988 | 16.2272 | 0
5.3618 | 7.8617 | 2.1086 | 1.9681 | 2.8936 | 2.9362 | 6.8405 | 4.8724 | 13.2236 | 15.1917 | 22.0321 | 26.9045 | 5.3618 | 7.8617 | 2.1086 | 1.9681 | 2.8936 | 2.9462 | 6.8405 | 4.8724 | 13.2236 | 15.1917 | 22.0321 | 26.9045 | 0
9.2577 | 8.7058 | 2.1426 | 2.1629 | 3.543 | 3.3258 | 7.8144 | 5.6515 | 17.9635 | 20.1264 | 27.9408 | 33.5924 | 9.2577 | 8.7058 | 2.1426 | 2.1629 | 3.543 | 3.3358 | 7.8144 | 5.6515 | 17.9635 | 20.1264 | 27.9408 | 33.5924 | 0
10.2787 | 8.9271 | 2.2081 | 2.2139 | 3.7131 | 3.4279 | 8.0697 | 5.8557 | 19.2058 | 21.4197 | 29.4894 | 35.3451 | 10.2787 | 8.9271 | 2.2081 | 2.2139 | 3.7131 | 3.4379 | 8.0697 | 5.8557 | 19.2058 | 21.4197 | 29.4894 | 35.3451 | 0
12.2433 | 9.3527 | 1.7133 | 2.3122 | 4.0406 | 3.6243 | 8.5608 | 6.2487 | 21.5961 | 23.9082 | 32.4691 | 38.7177 | 12.2433 | 9.3527 | 1.7133 | 2.3122 | 4.0406 | 3.6343 | 8.5608 | 6.2487 | 21.5961 | 23.9082 | 32.4691 | 38.7177 | 0
-2.602 | 6.1362 | 2.0305 | 1.5699 | 1.5663 | 2.1398 | 4.8495 | 3.2796 | 3.5343 | 5.1042 | 9.9537 | 13.2333 | -2.602 | 6.1362 | 2.0305 | 1.5699 | 1.5663 | 2.1498 | 4.8495 | 3.2796 | 3.5343 | 5.1042 | 9.9537 | 13.2333 | 0
6.9152 | 8.1983 | 1.9055 | 2.0458 | 3.1525 | 3.0915 | 7.2288 | 5.183 | 15.1135 | 17.1593 | 24.3881 | 29.5711 | 6.9152 | 8.1983 | 1.9055 | 2.0458 | 3.1525 | 3.1015 | 7.2288 | 5.183 | 15.1135 | 17.1593 | 24.3881 | 29.5711 | 0
3.1651 | 7.3858 | 2.0144 | 1.8583 | 2.5275 | 2.7165 | 6.2913 | 4.433 | 10.5509 | 12.4091 | 18.7004 | 23.1334 | 3.1651 | 7.3858 | 2.0144 | 1.8583 | 2.5275 | 2.7265 | 6.2913 | 4.433 | 10.5509 | 12.4091 | 18.7004 | 23.1334 | 0
6.4306 | 8.0933 | 1.864 | 2.0215 | 3.0718 | 3.0431 | 7.1076 | 5.0861 | 14.5239 | 16.5454 | 23.653 | 28.7391 | 6.4306 | 8.0933 | 1.864 | 2.0215 | 3.0718 | 3.0531 | 7.1076 | 5.0861 | 14.5239 | 16.5454 | 23.653 | 28.7391 | 0
1.919 | 7.1158 | 1.9736 | 1.7959 | 2.3198 | 2.5919 | 5.9797 | 4.1838 | 9.0347 | 10.8307 | 16.8104 | 20.9942 | 1.919 | 7.1158 | 1.9736 | 1.7959 | 2.3198 | 2.6019 | 5.9797 | 4.1838 | 9.0347 | 10.8307 | 16.8104 | 20.9942 | 0
5.2075 | 7.8283 | 1.9672 | 1.9604 | 2.8679 | 2.9207 | 6.8019 | 4.8415 | 13.0358 | 14.9962 | 21.798 | 26.6395 | 5.2075 | 7.8283 | 1.9672 | 1.9604 | 2.8679 | 2.9307 | 6.8019 | 4.8415 | 13.0358 | 14.9962 | 21.798 | 26.6395 | 0
5.0148 | 7.7865 | 1.9804 | 1.9507 | 2.8358 | 2.9015 | 6.7537 | 4.803 | 12.8013 | 14.7521 | 21.5058 | 26.3087 | 5.0148 | 7.7865 | 1.9804 | 1.9507 | 2.8358 | 2.9115 | 6.7537 | 4.803 | 12.8013 | 14.7521 | 21.5058 | 26.3087 | 0
5.4118 | 7.8725 | 1.82 | 1.9706 | 2.902 | 2.9412 | 6.8529 | 4.8824 | 13.2843 | 15.2549 | 22.1078 | 26.9902 | 5.4118 | 7.8725 | 1.82 | 1.9706 | 2.902 | 2.9512 | 6.8529 | 4.8824 | 13.2843 | 15.2549 | 22.1078 | 26.9902 | 0
0.60033 | 6.8301 | 2.1284 | 1.73 | 2.1001 | 2.46 | 5.6501 | 3.9201 | 7.4304 | 9.1604 | 14.8105 | 18.7306 | 0.60033 | 6.8301 | 2.1284 | 1.73 | 2.1001 | 2.47 | 5.6501 | 3.9201 | 7.4304 | 9.1604 | 14.8105 | 18.7306 | 0
9.8505 | 8.8343 | 1.9956 | 2.1925 | 3.6418 | 3.3851 | 7.9626 | 5.7701 | 18.6848 | 20.8773 | 28.84 | 34.6101 | 9.8505 | 8.8343 | 1.9956 | 2.1925 | 3.6418 | 3.3951 | 7.9626 | 5.7701 | 18.6848 | 20.8773 | 28.84 | 34.6101 | 0
5.8682 | 7.9714 | 1.8458 | 1.9934 | 2.978 | 2.9868 | 6.9671 | 4.9736 | 13.8396 | 15.8331 | 22.8001 | 27.7737 | 5.8682 | 7.9714 | 1.8458 | 1.9934 | 2.978 | 2.9968 | 6.9671 | 4.9736 | 13.8396 | 15.8331 | 22.8001 | 27.7737 | 0
1.3746 | 6.9978 | 2.3455 | 1.7687 | 2.2291 | 2.5375 | 5.8436 | 4.0749 | 8.3724 | 10.1411 | 15.9848 | 20.0597 | 1.3746 | 6.9978 | 2.3455 | 1.7687 | 2.2291 | 2.5475 | 5.8436 | 4.0749 | 8.3724 | 10.1411 | 15.9848 | 20.0597 | 0
16.3663 | 10.246 | 2.1493 | 2.5183 | 4.7277 | 4.0366 | 9.5916 | 7.0733 | 26.6123 | 29.1306 | 38.7222 | 45.7954 | 16.3663 | 10.246 | 2.1493 | 2.5183 | 4.7277 | 4.0466 | 9.5916 | 7.0733 | 26.6123 | 29.1306 | 38.7222 | 45.7954 | 0
10.4785 | 8.9703 | 2.2881 | 2.2239 | 3.7464 | 3.4479 | 8.1196 | 5.8957 | 19.4488 | 21.6728 | 29.7924 | 35.6881 | 10.4785 | 8.9703 | 2.2881 | 2.2239 | 3.7464 | 3.4579 | 8.1196 | 5.8957 | 19.4488 | 21.6728 | 29.7924 | 35.6881 | 0
14.6431 | 9.8727 | 2.1757 | 2.4322 | 4.4405 | 3.8643 | 9.1608 | 6.7286 | 24.5157 | 26.9479 | 36.1087 | 42.8373 | 14.6431 | 9.8727 | 2.1757 | 2.4322 | 4.4405 | 3.8743 | 9.1608 | 6.7286 | 24.5157 | 26.9479 | 36.1087 | 42.8373 | 0
11.2705 | 9.1419 | 1.6904 | 2.2635 | 3.8784 | 3.5271 | 8.3176 | 6.0541 | 20.4125 | 22.676 | 30.9936 | 37.0477 | 11.2705 | 9.1419 | 1.6904 | 2.2635 | 3.8784 | 3.5371 | 8.3176 | 6.0541 | 20.4125 | 22.676 | 30.9936 | 37.0477 | 0
-3.2871 | 5.9878 | 1.9339 | 1.5356 | 1.4522 | 2.0713 | 4.6782 | 3.1426 | 2.7008 | 4.2364 | 8.9146 | 12.0572 | -3.2871 | 5.9878 | 1.9339 | 1.5356 | 1.4522 | 2.0813 | 4.6782 | 3.1426 | 2.7008 | 4.2364 | 8.9146 | 12.0572 | 0
4.0163 | 7.5702 | 1.9562 | 1.9008 | 2.6694 | 2.8016 | 6.5041 | 4.6033 | 11.5865 | 13.4873 | 19.9914 | 24.5946 | 4.0163 | 7.5702 | 1.9562 | 1.9008 | 2.6694 | 2.8116 | 6.5041 | 4.6033 | 11.5865 | 13.4873 | 19.9914 | 24.5946 | 0
4.6864 | 7.7154 | 1.8488 | 1.9343 | 2.7811 | 2.8686 | 6.6716 | 4.7373 | 12.4018 | 14.3361 | 21.0078 | 25.745 | 4.6864 | 7.7154 | 1.8488 | 1.9343 | 2.7811 | 2.8786 | 6.6716 | 4.7373 | 12.4018 | 14.3361 | 21.0078 | 25.745 | 0
1.4634 | 7.0171 | 1.7742 | 1.7732 | 2.2439 | 3.5791 | 5.8659 | 4.0927 | 8.4805 | 10.2536 | 16.1195 | 20.2122 | 1.4634 | 7.0171 | 1.7742 | 1.7732 | 2.2439 | 3.5891 | 5.8659 | 4.0927 | 8.4805 | 10.2536 | 16.1195 | 20.2122 | 0
-0.77368 | 6.5324 | 2.193 | 1.6613 | 1.8711 | 1.6857 | 5.3066 | 3.6453 | 5.7587 | 7.42 | 12.7266 | 16.3718 | -0.77368 | 6.5324 | 2.193 | 1.6613 | 1.8711 | 1.6957 | 5.3066 | 3.6453 | 5.7587 | 7.42 | 12.7266 | 16.3718 | 0
11.7905 | 9.2546 | 1.5619 | 2.2895 | 3.9651 | 2.9119 | 8.4476 | 6.1581 | 21.0451 | 23.3346 | 31.7823 | 37.9404 | 11.7905 | 9.2546 | 1.5619 | 2.2895 | 3.9651 | 2.9219 | 8.4476 | 6.1581 | 21.0451 | 23.3346 | 31.7823 | 37.9404 | 0
-7.1426 | 5.1524 | 1.9706 | 1.3429 | 0.80957 | 3.4348 | 3.7144 | 2.3715 | -1.9901 | -0.64725 | 3.5972 | 5.9687 | -7.1426 | 5.1524 | 1.9706 | 1.3429 | 0.80957 | 3.4448 | 3.7144 | 2.3715 | -1.9901 | -0.64725 | 3.6072 | 5.9787 | 0
5.1192 | 7.8092 | 2.1449 | 1.956 | 2.8532 | 3.9823 | 6.7798 | 4.8238 | 12.9284 | 14.8844 | 21.7198 | 26.5437 | 5.1192 | 7.8092 | 2.1449 | 1.956 | 2.8532 | 3.9923 | 6.7798 | 4.8238 | 12.9284 | 14.8844 | 21.7298 | 26.5537 | 0
10.3484 | 8.9421 | 2.3274 | 2.2174 | 3.7247 | 2.3004 | 8.0871 | 5.8697 | 19.2905 | 21.5079 | 29.595 | 35.4647 | 10.3484 | 8.9421 | 2.3274 | 2.2174 | 3.7247 | 2.3104 | 8.0871 | 5.8697 | 19.2905 | 21.5079 | 29.595 | 35.4647 | 0
15.8226 | 10.1282 | 1.7668 | 2.4911 | 4.6371 | 1.4393 | 9.4556 | 6.9645 | 25.9508 | 28.442 | 37.8976 | 44.8621 | 15.8226 | 10.1282 | 1.7668 | 2.4911 | 4.6371 | 1.4493 | 9.4556 | 6.9645 | 25.9508 | 28.442 | 37.8976 | 44.8621 | 0
-0.99638 | 6.4841 | 1.4798 | 1.6502 | 1.8339 | 2.1554 | 5.2509 | 3.6007 | 5.4877 | 7.1379 | 12.3888 | 15.9895 | -0.99638 | 6.4841 | 1.4798 | 1.6502 | 1.8339 | 2.1654 | 5.2509 | 3.6007 | 5.4877 | 7.1379 | 12.3888 | 15.9895 | 0
-9.6069 | 4.6185 | 1.7185 | 1.2197 | 0.39885 | 2.5843 | 4.8886 | 1.8786 | -4.9884 | -3.7688 | 1.1198 | 2.9984 | -9.6069 | 4.6185 | 1.7185 | 1.2197 | 0.39885 | 2.5943 | 4.8886 | 1.8786 | -4.9884 | -3.7688 | 1.1198 | 2.9984 | 0
-2.4456 | 6.1701 | 1.8614 | 1.5777 | 1.5924 | 2.3528 | 5.9607 | 3.3109 | 3.7245 | 5.3022 | 11.2629 | 14.5738 | -2.4456 | 6.1701 | 1.8614 | 1.5777 | 1.5924 | 2.3628 | 5.9607 | 3.3109 | 3.7245 | 5.3022 | 11.2629 | 14.5738 | 0
1.8427 | 7.0993 | 1.7843 | 1.7921 | 2.3071 | 2.7307 | 5.3821 | 4.1685 | 8.942 | 10.7341 | 16.1162 | 20.2847 | 1.8427 | 7.0993 | 1.7843 | 1.7921 | 2.3071 | 2.7407 | 5.3821 | 4.1685 | 8.942 | 10.7341 | 16.1162 | 20.2847 | 0
-0.47175 | 6.5978 | 1.9102 | 1.6764 | 1.9214 | 2.5396 | 6.3268 | 3.7057 | 6.126 | 7.8025 | 14.1292 | 17.8349 | -0.47175 | 6.5978 | 1.9102 | 1.6764 | 1.9214 | 2.5496 | 6.3268 | 3.7057 | 6.126 | 7.8025 | 14.1292 | 17.8349 | 0
3.3071 | 7.4165 | 1.8465 | 1.7698 | 2.5512 | 2.4087 | 5.8491 | 4.4614 | 10.7236 | 12.4935 | 18.3426 | 22.804 | 3.3071 | 7.4165 | 1.8465 | 1.7698 | 2.5512 | 2.4187 | 5.8491 | 4.4614 | 10.7236 | 12.4935 | 18.3426 | 22.804 | 0
1.3965 | 7.0026 | 1.8029 | 1.7043 | 2.2327 | 3.3494 | 5.5217 | 4.0793 | 8.399 | 10.1034 | 15.6855 | 19.7648 | 1.3965 | 7.0026 | 1.8029 | 1.7043 | 2.2327 | 3.3594 | 5.5217 | 4.0793 | 8.399 | 10.1034 | 15.6955 | 19.7748 | 0
0.08672 | 6.7188 | 2.1165 | 2.1747 | 2.0145 | 3.9835 | 7.8734 | 3.8173 | 6.8055 | 8.9802 | 16.8536 | 20.671 | 0.08672 | 6.7188 | 2.1165 | 2.1747 | 2.0145 | 3.9935 | 7.8734 | 3.8173 | 6.8055 | 8.9802 | 16.8536 | 20.671 | 0
9.4938 | 8.757 | 2.3278 | 2.4917 | 3.5823 | 3.2911 | 9.4587 | 5.6988 | 18.2508 | 20.7425 | 30.2012 | 35.8999 | 9.4938 | 8.757 | 2.3278 | 2.4917 | 3.5823 | 3.3011 | 9.4587 | 5.6988 | 18.2508 | 20.7425 | 30.2012 | 35.8999 | 0
15.8348 | 10.1309 | 2.097 | 2.1455 | 4.6391 | 3.8318 | 7.7276 | 6.967 | 25.9657 | 28.1112 | 36.5822 | 43.5491 | 15.8348 | 10.1309 | 2.097 | 2.1455 | 4.6391 | 3.8418 | 7.7276 | 6.967 | 25.9657 | 28.1112 | 36.5922 | 43.5591 | 0
8.9106 | 8.6306 | 2.2773 | 2.4159 | 3.4851 | 2.4722 | 9.0796 | 5.5821 | 17.5412 | 19.9571 | 29.0368 | 34.6189 | 8.9106 | 8.6306 | 2.2773 | 2.4159 | 3.4851 | 2.4822 | 9.0796 | 5.5821 | 17.5412 | 19.9571 | 29.0368 | 34.6189 | 0
14.3184 | 9.8023 | 1.8241 | 1.7361 | 4.3864 | 3.1013 | 5.6806 | 6.6637 | 24.1208 | 25.8569 | 33.3446 | 40.0083 | 14.3184 | 9.8023 | 1.8241 | 1.7361 | 4.3864 | 3.1113 | 5.6806 | 6.6637 | 24.1208 | 25.8569 | 33.3546 | 40.0183 | 0
0.7224 | 6.8565 | 2.0338 | 2.0506 | 2.1204 | 4.3384 | 7.2532 | 3.9445 | 7.5789 | 9.6296 | 16.8828 | 20.8273 | 0.7224 | 6.8565 | 2.0338 | 2.0506 | 2.1204 | 4.3484 | 7.2532 | 3.9445 | 7.5789 | 9.6296 | 16.8828 | 20.8273 | 0
7.0128 | 8.2194 | 2.4461 | 2.6692 | 3.1688 | 1.3988 | 10.346 | 5.2026 | 15.2323 | 17.9015 | 28.2475 | 33.45 | 7.0128 | 8.2194 | 2.4461 | 2.6692 | 3.1688 | 1.4088 | 10.346 | 5.2026 | 15.2323 | 17.9015 | 28.2475 | 33.45 | 0
19.384 | 10.8999 | 1.4663 | 1.1994 | 5.2307 | 4.3226 | 2.9969 | 7.6768 | 30.2838 | 31.4832 | 41.0365 | 48.7133 | 19.384 | 10.8999 | 1.4663 | 1.1994 | 5.2307 | 4.3326 | 2.9969 | 7.6768 | 30.2838 | 31.4832 | 41.0465 | 48.7233 | 0
19.2262 | 4.5307 | 2.4409 | 2.6613 | 0.33129 | 3.8214 | 10.3065 | 1.7975 | 23.7568 | 26.4181 | 36.7247 | 38.5222 | 19.2262 | 4.5307 | 2.4409 | 2.6613 | 0.33129 | 3.8314 | 10.3065 | 1.7975 | 23.7568 | 26.4181 | 36.7247 | 38.5222 | 0
14.2142 | 10.8657 | 2.2738 | 2.4107 | 5.2044 | 2.1505 | 9.0535 | 7.6452 | 25.0798 | 27.4905 | 36.5441 | 44.1893 | 14.2142 | 10.8657 | 2.2738 | 2.4107 | 5.2044 | 2.1605 | 9.0535 | 7.6452 | 25.0798 | 27.4905 | 36.5441 | 44.1893 | 0
-2.4952 | 9.7797 | 1.7168 | 1.5752 | 4.369 | 3.5234 | 4.8762 | 6.6428 | 7.2846 | 8.8598 | 16.7522 | 23.395 | -2.4952 | 9.7797 | 1.7168 | 1.5752 | 4.369 | 3.5334 | 4.8762 | 6.6428 | 7.2846 | 8.8598 | 16.7622 | 23.405 | 0
11.2336 | 6.1594 | 2.1745 | 2.2617 | 1.5841 | 4.0163 | 8.3084 | 3.301 | 17.393 | 19.6547 | 27.9631 | 31.2641 | 11.2336 | 6.1594 | 2.1745 | 2.2617 | 1.5841 | 4.0263 | 8.3084 | 3.301 | 17.393 | 19.6547 | 27.9631 | 31.2641 | 0
16.1635 | 9.134 | 2.3388 | 2.5082 | 3.8723 | 2.7069 | 9.5409 | 6.0467 | 25.2974 | 27.8056 | 37.3465 | 43.3932 | 16.1635 | 9.134 | 2.3388 | 2.5082 | 3.8723 | 2.7169 | 9.5409 | 6.0467 | 25.2974 | 27.8056 | 37.3465 | 43.3932 | 0
3.0691 | 10.2021 | 1.9023 | 1.8535 | 4.2369 | 3.7422 | 6.2673 | 7.0327 | 13.2711 | 15.1246 | 23.1037 | 30.1364 | 3.0691 | 10.2021 | 1.9023 | 1.8535 | 4.2369 | 3.7522 | 6.2673 | 7.0327 | 13.2711 | 15.1246 | 23.1137 | 30.1464 | 0
13.4216 | 7.365 | 2.2474 | 2.3711 | 4.3798 | 3.8279 | 8.8554 | 4.4138 | 20.7866 | 23.1577 | 32.0131 | 36.4269 | 13.4216 | 7.365 | 2.2474 | 2.3711 | 4.3798 | 3.8379 | 8.8554 | 4.4138 | 20.7866 | 23.1577 | 32.0131 | 36.4269 | 0
14.2791 | 9.608 | 2.276 | 2.414 | 2.4376 | 2.6625 | 9.0698 | 6.4843 | 23.8871 | 26.301 | 35.3708 | 41.8551 | 14.2791 | 9.608 | 2.276 | 2.414 | 2.4376 | 2.6725 | 9.0698 | 6.4843 | 23.8871 | 26.301 | 35.3708 | 41.8551 | 0
2.6253 | 9.7938 | 1.8875 | 1.8313 | 0.72184 | 1.6331 | 6.1563 | 6.6558 | 12.4191 | 14.2504 | 20.4067 | 27.0625 | 2.6253 | 9.7938 | 1.8875 | 1.8313 | 0.72184 | 1.6431 | 6.1563 | 6.6558 | 12.4191 | 14.2504 | 20.4067 | 27.0625 | 0
-7.6689 | 7.2688 | 1.5444 | 1.3166 | 4.3164 | 3.7899 | 3.5828 | 4.3251 | -0.40013 | 0.91643 | 9.0227 | 13.3478 | -7.6689 | 7.2688 | 1.5444 | 1.3166 | 4.3164 | 3.7999 | 3.5828 | 4.3251 | -0.40013 | 0.91643 | 9.0327 | 13.3578 | 0
13.8987 | 5.0384 | 2.2633 | 2.3949 | 4.5377 | 3.9226 | 8.9747 | 2.2662 | 18.9371 | 21.332 | 30.3067 | 32.5729 | 13.8987 | 5.0384 | 2.2633 | 2.3949 | 4.5377 | 3.9326 | 8.9747 | 2.2662 | 18.9371 | 21.332 | 30.3067 | 32.5729 | 0
15.2263 | 9.7114 | 2.3075 | 2.4613 | 5.1783 | 4.307 | 9.3066 | 6.5797 | 24.9377 | 27.399 | 36.8844 | 43.4641 | 15.2263 | 9.7114 | 2.3075 | 2.4613 | 5.1783 | 4.317 | 9.3066 | 6.5797 | 24.9377 | 27.399 | 36.8944 | 43.4741 | 0
19.0701 | 9.999 | 2.4357 | 2.6535 | 1.7349 | 2.2409 | 10.2675 | 6.8453 | 29.0691 | 31.7226 | 41.9902 | 48.8354 | 19.0701 | 9.999 | 2.4357 | 2.6535 | 1.7349 | 2.2509 | 10.2675 | 6.8453 | 29.0691 | 31.7226 | 41.9902 | 48.8354 | 0
-1.5907 | 10.8319 | 1.747 | 1.6205 | 3.4667 | 3.28 | 5.1023 | 7.614 | 9.2411 | 10.8616 | 17.6083 | 25.2223 | -1.5907 | 10.8319 | 1.747 | 1.6205 | 3.4667 | 3.29 | 5.1023 | 7.614 | 9.2411 | 10.8616 | 17.6183 | 25.2323 | 0
8.8001 | 6.3553 | 2.0933 | 2.14 | 3.3661 | 3.2197 | 7.7 | 3.4819 | 15.1554 | 17.2954 | 24.9955 | 28.4773 | 8.8001 | 6.3553 | 2.0933 | 2.14 | 3.3661 | 3.2297 | 7.7 | 3.4819 | 15.1554 | 17.2954 | 24.9955 | 28.4773 | 0
8.1966 | 8.6067 | 2.0732 | 2.1098 | 2.9229 | 2.9538 | 7.5492 | 5.56 | 16.8033 | 18.9131 | 26.4623 | 32.0223 | 8.1966 | 8.6067 | 2.0732 | 2.1098 | 2.9229 | 2.9638 | 7.5492 | 5.56 | 16.8033 | 18.9131 | 26.4623 | 32.0223 | 0
5.5376 | 8.4759 | 1.9846 | 1.9769 | 2.3602 | 2.6161 | 6.8844 | 5.4393 | 14.0135 | 15.9904 | 22.8748 | 28.3141 | 5.5376 | 8.4759 | 1.9846 | 1.9769 | 2.3602 | 2.6261 | 6.8844 | 5.4393 | 14.0135 | 15.9904 | 22.8748 | 28.3141 | 0
2.1614 | 7.8998 | 1.872 | 1.8081 | 2.489 | 2.6934 | 6.0403 | 4.9075 | 10.0612 | 11.8692 | 17.9096 | 22.8171 | 2.1614 | 7.8998 | 1.872 | 1.8081 | 2.489 | 2.7034 | 6.0403 | 4.9075 | 10.0612 | 11.8692 | 17.9096 | 22.8171 | 0
2.9341 | 7.1683 | 1.8978 | 1.8467 | 3.9122 | 3.5473 | 6.2335 | 4.2323 | 10.1024 | 11.9491 | 19.4087 | 23.641 | 2.9341 | 7.1683 | 1.8978 | 1.8467 | 3.9122 | 3.5573 | 6.2335 | 4.2323 | 10.1024 | 11.9491 | 19.4187 | 23.651 | 0
11.4734 | 7.3357 | 2.1824 | 2.2737 | 4.5221 | 3.9133 | 8.3684 | 4.3868 | 18.8092 | 21.0828 | 29.5182 | 33.9051 | 11.4734 | 7.3357 | 2.1824 | 2.2737 | 4.5221 | 3.9233 | 8.3684 | 4.3868 | 18.8092 | 21.0828 | 29.5282 | 33.9151 | 0
15.1327 | 9.1859 | 2.3044 | 2.4566 | 3.0515 | 3.0309 | 9.2832 | 6.0947 | 24.3186 | 26.7752 | 36.0584 | 42.1531 | 15.1327 | 9.1859 | 2.3044 | 2.4566 | 3.0515 | 3.0409 | 9.2832 | 6.0947 | 24.3186 | 26.7752 | 36.0584 | 42.1531 | 0
6.309 | 9.9788 | 2.0103 | 2.0154 | 3.3918 | 3.2351 | 7.0772 | 6.8265 | 16.2877 | 18.3032 | 25.3804 | 32.207 | 6.309 | 9.9788 | 2.0103 | 2.0154 | 3.3918 | 3.2451 | 7.0772 | 6.8265 | 16.2877 | 18.3032 | 25.3804 | 32.207 | 0
8.3508 | 8.0669 | 2.0784 | 2.1175 | 3.9998 | 3.5999 | 7.5877 | 5.0618 | 16.4178 | 18.5353 | 26.135 | 31.1968 | 8.3508 | 8.0669 | 2.0784 | 2.1175 | 3.9998 | 3.6099 | 7.5877 | 5.0618 | 16.4178 | 18.5353 | 26.145 | 31.2068 | 0
11.9988 | 8.5093 | 2.2 | 2.2999 | 3.3774 | 3.2265 | 8.4997 | 5.4702 | 20.5081 | 22.808 | 31.3077 | 36.7779 | 11.9988 | 8.5093 | 2.2 | 2.2999 | 3.3774 | 3.2365 | 8.4997 | 5.4702 | 20.5081 | 22.808 | 31.3077 | 36.7779 | 0
8.2645 | 9.2997 | 2.0755 | 2.1132 | 2.4958 | 2.6975 | 7.5661 | 6.1998 | 17.5643 | 19.6775 | 27.2436 | 33.4434 | 8.2645 | 9.2997 | 2.0755 | 2.1132 | 2.4958 | 2.7075 | 7.5661 | 6.1998 | 17.5643 | 19.6775 | 27.2436 | 33.4434 | 0
2.9748 | 8.4906 | 1.8992 | 1.8487 | 3.6696 | 3.4018 | 6.2437 | 5.4529 | 11.4654 | 13.3142 | 20.3856 | 25.8385 | 2.9748 | 8.4906 | 1.8992 | 1.8487 | 3.6696 | 3.4118 | 6.2437 | 5.4529 | 11.4654 | 13.3142 | 20.3956 | 25.8485 | 0
10.0178 | 7.3445 | 2.1339 | 2.2009 | 2.3627 | 2.6176 | 8.0044 | 4.395 | 17.3623 | 19.5632 | 27.5677 | 31.9626 | 10.0178 | 7.3445 | 2.1339 | 2.2009 | 2.3627 | 2.6276 | 8.0044 | 4.395 | 17.3623 | 19.5632 | 27.5677 | 31.9626 | 0
2.1761 | 8.8705 | 1.8725 | 1.8088 | 3.6992 | 3.4195 | 6.044 | 5.8036 | 11.0466 | 12.8554 | 19.9742 | 25.7777 | 2.1761 | 8.8705 | 1.8725 | 1.8088 | 3.6992 | 3.4295 | 6.044 | 5.8036 | 11.0466 | 12.8554 | 19.9842 | 25.7877 | 0
10.1953 | 7.1715 | 2.1398 | 2.2098 | 2.0614 | 2.4368 | 8.0488 | 4.2352 | 17.3668 | 19.5765 | 27.6253 | 31.8606 | 10.1953 | 7.1715 | 2.1398 | 2.2098 | 2.0614 | 2.4468 | 8.0488 | 4.2352 | 17.3668 | 19.5765 | 27.6253 | 31.8606 | 0
0.36812 | 8.909 | 1.8123 | 1.7184 | 3.4738 | 3.2843 | 5.592 | 5.8391 | 9.2771 | 10.9955 | 17.7536 | 23.5926 | 0.36812 | 8.909 | 1.8123 | 1.7184 | 3.4738 | 3.2943 | 5.592 | 5.8391 | 9.2771 | 10.9955 | 17.7636 | 23.6026 | 0
8.8428 | 6.7798 | 2.0948 | 2.1421 | 2.5607 | 2.7364 | 7.7107 | 3.8736 | 15.6225 | 17.7647 | 25.4753 | 29.349 | 8.8428 | 6.7798 | 2.0948 | 2.1421 | 2.5607 | 2.7464 | 7.7107 | 3.8736 | 15.6225 | 17.7647 | 25.4753 | 29.349 | 0
3.3639 | 8.6159 | 1.9121 | 1.8682 | 3.7195 | 3.4317 | 6.341 | 5.5686 | 11.9799 | 13.8481 | 20.9992 | 26.5678 | 3.3639 | 8.6159 | 1.9121 | 1.8682 | 3.7195 | 3.4417 | 6.341 | 5.5686 | 11.9799 | 13.8481 | 21.0092 | 26.5778 | 0
10.3169 | 7.4289 | 2.1439 | 2.2158 | 4.0749 | 3.645 | 8.0792 | 4.4728 | 17.7457 | 19.9616 | 28.0408 | 32.5136 | 10.3169 | 7.4289 | 2.1439 | 2.2158 | 4.0749 | 3.655 | 8.0792 | 4.4728 | 17.7457 | 19.9616 | 28.0408 | 32.5136 | 0
12.4496 | 8.9353 | 2.215 | 2.3225 | 3.8485 | 3.5091 | 8.6124 | 5.8634 | 21.3849 | 23.7074 | 32.3198 | 38.1832 | 12.4496 | 8.9353 | 2.215 | 2.3225 | 3.8485 | 3.5191 | 8.6124 | 5.8634 | 21.3849 | 23.7074 | 32.3198 | 38.1832 | 0
11.0913 | 9.3974 | 2.1697 | 2.2546 | 1.6992 | 2.2195 | 8.2728 | 6.2899 | 20.4887 | 22.7433 | 31.0161 | 37.306 | 11.0913 | 9.3974 | 2.1697 | 2.2546 | 1.6992 | 2.2295 | 8.2728 | 6.2899 | 20.4887 | 22.7433 | 31.0161 | 37.306 | 0
-1.8049 | 9.1031 | 1.7398 | 1.6098 | 3.2226 | 3.1336 | 5.0488 | 6.0183 | 7.2982 | 8.908 | 15.2642 | 21.2824 | -1.8049 | 9.1031 | 1.7398 | 1.6098 | 3.2226 | 3.1436 | 5.0488 | 6.0183 | 7.2982 | 8.908 | 15.2742 | 21.2924 | 0
7.3357 | 6.3089 | 2.0445 | 2.0668 | 4.1585 | 3.6951 | 7.3339 | 3.439 | 13.6446 | 15.7114 | 23.565 | 27.004 | 7.3357 | 6.3089 | 2.0445 | 2.0668 | 4.1585 | 3.7051 | 7.3339 | 3.439 | 13.6446 | 15.7114 | 23.575 | 27.014 | 0
12.9509 | 8.2894 | 2.2317 | 2.3475 | 1.8244 | 2.2947 | 8.7377 | 5.2671 | 21.2403 | 23.5878 | 32.3255 | 37.5927 | 12.9509 | 8.2894 | 2.2317 | 2.3475 | 1.8244 | 2.3047 | 8.7377 | 5.2671 | 21.2403 | 23.5878 | 32.3255 | 37.5927 | 0
-1.0534 | 9.506 | 1.7649 | 1.6473 | 4.1219 | 3.6732 | 5.2366 | 6.3902 | 8.4526 | 10.0999 | 17.895 | 24.2852 | -1.0534 | 9.506 | 1.7649 | 1.6473 | 4.1219 | 3.6832 | 5.2366 | 6.3902 | 8.4526 | 10.0999 | 17.905 | 24.2952 | 0
12.7317 | 6.4718 | 2.2244 | 2.3366 | 2.2937 | 2.5762 | 8.6829 | 3.5893 | 19.2034 | 21.54 | 30.2229 | 33.8122 | 12.7317 | 6.4718 | 2.2244 | 2.3366 | 2.2937 | 2.5862 | 8.6829 | 3.5893 | 19.2034 | 21.54 | 30.2229 | 33.8122 | 0
1.7625 | 9.4585 | 1.8587 | 1.7881 | 4.4139 | 3.8484 | 5.9406 | 6.3463 | 11.221 | 13.0091 | 21.2714 | 27.6177 | 1.7625 | 9.4585 | 1.8587 | 1.7881 | 4.4139 | 3.8584 | 5.9406 | 6.3463 | 11.221 | 13.0091 | 21.2814 | 27.6277 | 0
14.4836 | 7.0819 | 2.2828 | 2.4242 | 2.818 | 2.8908 | 9.1209 | 4.1525 | 21.5654 | 23.9896 | 33.1105 | 37.263 | 14.4836 | 7.0819 | 2.2828 | 2.4242 | 2.818 | 2.9008 | 9.1209 | 4.1525 | 21.5654 | 23.9896 | 33.1105 | 37.263 | 0
4.908 | 9.8381 | 1.9636 | 1.9454 | 4.2124 | 3.7275 | 6.727 | 6.6967 | 14.7461 | 16.6915 | 24.6314 | 31.3281 | 4.908 | 9.8381 | 1.9636 | 1.9454 | 4.2124 | 3.7375 | 6.727 | 6.6967 | 14.7461 | 16.6915 | 24.6414 | 31.3381 | 0
13.2747 | 7.7634 | 2.2425 | 2.3637 | 2.6176 | 2.7706 | 8.8187 | 4.7816 | 21.0381 | 23.4018 | 32.2205 | 37.0021 | 13.2747 | 7.7634 | 2.2425 | 2.3637 | 2.6176 | 2.7806 | 8.8187 | 4.7816 | 21.0381 | 23.4018 | 32.2205 | 37.0021 | 0
3.7058 | 9.5762 | 1.9235 | 1.8853 | 4.0942 | 3.6565 | 6.4265 | 6.4549 | 13.282 | 15.1673 | 22.9179 | 29.3729 | 3.7058 | 9.5762 | 1.9235 | 1.8853 | 4.0942 | 3.6665 | 6.4265 | 6.4549 | 13.282 | 15.1673 | 22.9279 | 29.3829 | 0
12.5649 | 7.5029 | 2.2188 | 2.3282 | 2.7136 | 2.8282 | 8.6412 | 4.5412 | 20.0678 | 22.3961 | 31.0373 | 35.5785 | 12.5649 | 7.5029 | 2.2188 | 2.3282 | 2.7136 | 2.8382 | 8.6412 | 4.5412 | 20.0678 | 22.3961 | 31.0373 | 35.5785 | 0
4.2816 | 9.4224 | 1.9427 | 1.9141 | 1.5496 | 2.1298 | 6.5704 | 6.313 | 13.704 | 15.618 | 22.1884 | 28.5014 | 4.2816 | 9.4224 | 1.9427 | 1.9141 | 1.5496 | 2.1398 | 6.5704 | 6.313 | 13.704 | 15.618 | 22.1884 | 28.5014 | 0
-2.7021 | 7.6277 | 1.7099 | 1.5649 | 4.8215 | 4.0929 | 4.8245 | 4.6563 | 4.9255 | 6.4904 | 15.4048 | 20.0611 | -2.7021 | 7.6277 | 1.7099 | 1.5649 | 4.8215 | 4.1029 | 4.8245 | 4.6563 | 4.9255 | 6.4904 | 15.4148 | 20.0711 | 0
16.9289 | 6.1145 | 2.3643 | 2.5464 | 1.5666 | 2.14 | 9.7322 | 3.2596 | 23.0434 | 25.5899 | 35.3221 | 38.5817 | 16.9289 | 6.1145 | 2.3643 | 2.5464 | 1.5666 | 2.15 | 9.7322 | 3.2596 | 23.0434 | 25.5899 | 35.3221 | 38.5817 | 0
-2.6001 | 10.3679 | 1.7133 | 1.57 | 2.43 | 2.658 | 4.85 | 7.1858 | 7.7678 | 9.3378 | 14.4258 | 21.6116 | -2.6001 | 10.3679 | 1.7133 | 1.57 | 2.43 | 2.668 | 4.85 | 7.1858 | 7.7678 | 9.3378 | 14.4358 | 21.6216 | 0
2.5801 | 6.1366 | 1.886 | 1.829 | 0.74844 | 1.6491 | 6.145 | 3.28 | 8.7168 | 10.5458 | 16.6908 | 19.9708 | 2.5801 | 6.1366 | 1.886 | 1.829 | 0.74844 | 1.6591 | 6.145 | 3.28 | 8.7168 | 10.5458 | 16.6908 | 19.9708 | 0
-7.5094 | 7.259 | 1.5497 | 1.3245 | 3.3043 | 3.1826 | 3.6227 | 4.316 | -0.25035 | 1.0742 | 7.5611 | 11.8771 | -7.5094 | 7.259 | 1.5497 | 1.3245 | 3.3043 | 3.1926 | 3.6227 | 4.316 | -0.25035 | 1.0742 | 7.5711 | 11.8871 | 0
7.826 | 5.073 | 2.0609 | 2.0913 | 0.096747 | 1.258 | 7.4565 | 2.2981 | 12.899 | 14.9903 | 22.4468 | 24.7449 | 7.826 | 5.073 | 2.0609 | 2.0913 | 0.096747 | 1.268 | 7.4565 | 2.2981 | 12.899 | 14.9903 | 22.4468 | 24.7449 | 0
-11.4195 | 8.3956 | 1.4193 | 1.129 | 1.1507 | 1.8904 | 2.6451 | 5.3652 | -3.0239 | -1.8949 | 1.1462 | 6.5114 | -11.4195 | 8.3956 | 1.4193 | 1.129 | 1.1507 | 1.9004 | 2.6451 | 5.3652 | -3.0239 | -1.8949 | 1.1562 | 6.5214 | 0
-5.0961 | 4.2258 | 1.6301 | 1.4452 | 2.318 | 2.5908 | 4.226 | 1.5161 | -0.87032 | 0.57488 | 5.4837 | 6.9998 | -5.0961 | 4.2258 | 1.6301 | 1.4452 | 2.318 | 2.6008 | 4.226 | 1.5161 | -0.87032 | 0.57488 | 5.4937 | 7.0098 | 0
1.9081 | 5.5958 | 1.8636 | 1.7954 | 3.9068 | 3.5441 | 5.977 | 2.7808 | 7.5039 | 9.2993 | 16.7502 | 19.531 | 1.9081 | 5.5958 | 1.8636 | 1.7954 | 3.9068 | 3.5541 | 5.977 | 2.7808 | 7.5039 | 9.2993 | 16.7602 | 19.541 | 0
11.4408 | 7.1134 | 2.1814 | 2.272 | 3.9987 | 3.5992 | 8.3602 | 4.1816 | 18.5542 | 20.8263 | 29.1865 | 33.3681 | 11.4408 | 7.1134 | 2.1814 | 2.272 | 3.9987 | 3.6092 | 8.3602 | 4.1816 | 18.5542 | 20.8263 | 29.1865 | 33.3681 | 0
11.9924 | 9.1788 | 2.1997 | 2.2996 | 2.5211 | 2.7127 | 8.4981 | 6.0882 | 21.1712 | 23.4708 | 31.9689 | 38.0571 | 11.9924 | 9.1788 | 2.1997 | 2.2996 | 2.5211 | 2.7227 | 8.4981 | 6.0882 | 21.1712 | 23.4708 | 31.9689 | 38.0571 | 0
3.1269 | 9.2983 | 1.9042 | 1.8563 | 2.6077 | 2.7646 | 6.2817 | 6.1985 | 12.4252 | 14.2815 | 20.5633 | 26.7617 | 3.1269 | 9.2983 | 1.9042 | 1.8563 | 2.6077 | 2.7746 | 6.2817 | 6.1985 | 12.4252 | 14.2815 | 20.5633 | 26.7617 | 0
3.646 | 7.3775 | 1.9215 | 1.8823 | 3.8705 | 3.5223 | 6.4115 | 4.4254 | 11.0234 | 12.9057 | 20.2986 | 24.724 | 3.646 | 7.3775 | 1.9215 | 1.8823 | 3.8705 | 3.5323 | 6.4115 | 4.4254 | 11.0234 | 12.9057 | 20.3086 | 24.734 | 0
11.2232 | 7.49 | 2.1741 | 2.2612 | 4.6272 | 3.9763 | 8.3058 | 4.5292 | 18.7131 | 20.9743 | 29.5778 | 34.107 | 11.2232 | 7.49 | 2.1741 | 2.2612 | 4.6272 | 3.9863 | 8.3058 | 4.5292 | 18.7131 | 20.9743 | 29.5878 | 34.117 | 0
15.7633 | 9.1317 | 2.3254 | 2.4882 | 3.3338 | 3.2003 | 9.4408 | 6.0446 | 24.895 | 27.3831 | 36.8239 | 42.8686 | 15.7633 | 9.1317 | 2.3254 | 2.4882 | 3.3338 | 3.2103 | 9.4408 | 6.0446 | 24.895 | 27.3831 | 36.8239 | 42.8686 | 0
8.0029 | 10.1154 | 2.0668 | 2.1001 | 4.3526 | 3.8116 | 7.5007 | 6.9527 | 18.1183 | 20.2185 | 28.3827 | 35.3354 | 8.0029 | 10.1154 | 2.0668 | 2.1001 | 4.3526 | 3.8216 | 7.5007 | 6.9527 | 18.1183 | 20.2185 | 28.3927 | 35.3454 | 0
14.1159 | 8.434 | 2.2705 | 2.4058 | 3.1711 | 3.1026 | 9.029 | 5.4006 | 22.5498 | 24.9556 | 33.9846 | 39.3852 | 14.1159 | 8.434 | 2.2705 | 2.4058 | 3.1711 | 3.1126 | 9.029 | 5.4006 | 22.5498 | 24.9556 | 33.9846 | 39.3852 | 0
7.0265 | 9.7584 | 2.0342 | 2.0513 | 1.0701 | 1.842 | 7.2566 | 6.6232 | 16.7849 | 18.8362 | 26.0929 | 32.716 | 7.0265 | 9.7584 | 2.0342 | 2.0513 | 1.0701 | 1.852 | 7.2566 | 6.6232 | 16.7849 | 18.8362 | 26.0929 | 32.716 | 0
-5.5795 | 8.2224 | 1.614 | 1.421 | 3.1699 | 3.1019 | 4.1051 | 5.2053 | 2.6429 | 4.0639 | 10.3358 | 15.5411 | -5.5795 | 8.2224 | 1.614 | 1.421 | 3.1699 | 3.1119 | 4.1051 | 5.2053 | 2.6429 | 4.0639 | 10.3458 | 15.5511 | 0
7.0195 | 5.4911 | 2.034 | 2.051 | 2.44 | 2.664 | 7.2549 | 2.6841 | 12.5106 | 14.5615 | 21.8164 | 24.5005 | 7.0195 | 5.4911 | 2.034 | 2.051 | 2.44 | 2.674 | 7.2549 | 2.6841 | 12.5106 | 14.5615 | 21.8164 | 24.5005 | 0
2.6398 | 8.2209 | 1.888 | 1.832 | 3.9164 | 3.5498 | 6.1599 | 5.2039 | 10.8607 | 12.6926 | 20.1589 | 25.3627 | 2.6398 | 8.2209 | 1.888 | 1.832 | 3.9164 | 3.5598 | 6.1599 | 5.2039 | 10.8607 | 12.6926 | 20.1689 | 25.3727 | 0
11.4983 | 7.272 | 2.1833 | 2.2749 | 2.2667 | 2.56 | 8.3746 | 4.328 | 18.7703 | 21.0452 | 29.4197 | 33.7477 | 11.4983 | 7.272 | 2.1833 | 2.2749 | 2.2667 | 2.57 | 8.3746 | 4.328 | 18.7703 | 21.0452 | 29.4197 | 33.7477 | 0
1.6003 | 9.1913 | 1.8533 | 1.78 | 0.78163 | 1.669 | 5.9001 | 6.0997 | 10.7916 | 12.5716 | 18.4716 | 24.5713 | 1.6003 | 9.1913 | 1.8533 | 1.78 | 0.78163 | 1.679 | 5.9001 | 6.0997 | 10.7916 | 12.5716 | 18.4716 | 24.5713 | 0
-7.3102 | 7.0467 | 1.5563 | 1.3345 | 4.619 | 3.9714 | 3.6724 | 4.1201 | -0.26348 | 1.071 | 9.6614 | 13.7815 | -7.3102 | 7.0467 | 1.5563 | 1.3345 | 4.619 | 3.9814 | 3.6724 | 4.1201 | -0.26348 | 1.071 | 9.6714 | 13.7915 | 0
15.714 | 5.1161 | 2.3238 | 2.4857 | 4.1687 | 3.7012 | 9.4285 | 2.338 | 20.8301 | 23.3158 | 32.7443 | 35.0823 | 15.714 | 5.1161 | 2.3238 | 2.4857 | 4.1687 | 3.7112 | 9.4285 | 2.338 | 20.8301 | 23.3158 | 32.7443 | 35.0823 | 0
13.0123 | 10.1047 | 2.2337 | 2.3506 | 0.93932 | 1.7636 | 8.7531 | 6.9428 | 23.117 | 25.4677 | 34.2207 | 41.1635 | 13.0123 | 10.1047 | 2.2337 | 2.3506 | 0.93932 | 1.7736 | 8.7531 | 6.9428 | 23.117 | 25.4677 | 34.2207 | 41.1635 | 0
-6.3641 | 9.5193 | 1.5879 | 1.3818 | 3.1006 | 3.0604 | 3.909 | 6.4025 | 3.1553 | 4.5371 | 10.698 | 17.1005 | -6.3641 | 9.5193 | 1.5879 | 1.3818 | 3.1006 | 3.0704 | 3.909 | 6.4025 | 3.1553 | 4.5371 | 10.708 | 17.1105 | 0
6.6035 | 5.3211 | 2.0201 | 2.0302 | 3.8656 | 3.5194 | 7.1509 | 2.5272 | 11.9246 | 13.9548 | 21.3398 | 23.867 | 6.6035 | 5.3211 | 2.0201 | 2.0302 | 3.8656 | 3.5294 | 7.1509 | 2.5272 | 11.9246 | 13.9548 | 21.3498 | 23.877 | 0
11.1936 | 8.1308 | 2.1731 | 2.2597 | 2.3992 | 2.6395 | 8.2984 | 5.1207 | 19.3244 | 21.584 | 29.8824 | 35.0031 | 11.1936 | 8.1308 | 2.1731 | 2.2597 | 2.3992 | 2.6495 | 8.2984 | 5.1207 | 19.3244 | 21.584 | 29.8824 | 35.0031 | 0
2.3952 | 9.1253 | 1.8798 | 1.8198 | 4.4598 | 3.8759 | 6.0988 | 6.0387 | 11.5205 | 13.3403 | 21.6759 | 27.7146 | 2.3952 | 9.1253 | 1.8798 | 1.8198 | 4.4598 | 3.8859 | 6.0988 | 6.0387 | 11.5205 | 13.3403 | 21.6859 | 27.7246 | 0
14.7587 | 7.219 | 2.292 | 2.4379 | 4.6718 | 4.0031 | 9.1897 | 4.279 | 21.9776 | 24.4156 | 33.6053 | 37.8843 | 14.7587 | 7.219 | 2.292 | 2.4379 | 4.6718 | 4.0131 | 9.1897 | 4.279 | 21.9776 | 24.4156 | 33.6053 | 37.8843 | 0
16.0308 | 9.8977 | 2.3344 | 2.5015 | 2.5827 | 2.7496 | 9.5077 | 6.7517 | 25.9285 | 28.4301 | 37.9378 | 44.6895 | 16.0308 | 9.8977 | 2.3344 | 2.5015 | 2.5827 | 2.7596 | 9.5077 | 6.7517 | 25.9285 | 28.4301 | 37.9378 | 44.6895 | 0
3.496 | 10.1733 | 1.9165 | 1.8748 | 2.8107 | 2.8864 | 6.374 | 7.0062 | 13.6693 | 15.5441 | 21.9181 | 28.9243 | 3.496 | 10.1733 | 1.9165 | 1.8748 | 2.8107 | 2.8964 | 6.374 | 7.0062 | 13.6693 | 15.5441 | 21.9181 | 28.9243 | 0
4.8644 | 7.4575 | 1.9621 | 1.9432 | 4.7599 | 4.0559 | 6.7161 | 4.4992 | 12.3218 | 14.265 | 23.0809 | 27.5801 | 4.8644 | 7.4575 | 1.9621 | 1.9432 | 4.7599 | 4.0659 | 6.7161 | 4.4992 | 12.3218 | 14.265 | 23.0909 | 27.5901 | 0
16.5595 | 7.7539 | 2.352 | 2.528 | 5.0114 | 4.2069 | 9.6399 | 4.7729 | 24.3134 | 26.8414 | 36.4813 | 41.2541 | 16.5595 | 7.7539 | 2.352 | 2.528 | 5.0114 | 4.2169 | 9.6399 | 4.7729 | 24.3134 | 26.8414 | 36.4813 | 41.2541 | 0
18.0686 | 10.2879 | 2.4023 | 2.6034 | 4.3153 | 3.7892 | 10.0172 | 7.1119 | 28.3565 | 30.9599 | 40.9771 | 48.089 | 18.0686 | 10.2879 | 2.4023 | 2.6034 | 4.3153 | 3.7992 | 10.0172 | 7.1119 | 28.3565 | 30.9599 | 40.9771 | 48.089 | 0
13.8917 | 10.6149 | 2.2631 | 2.3946 | 3.384 | 3.2304 | 8.9729 | 7.4137 | 24.5065 | 26.9011 | 35.874 | 43.2878 | 13.8917 | 10.6149 | 2.2631 | 2.3946 | 3.384 | 3.2404 | 8.9729 | 7.4137 | 24.5065 | 26.9011 | 35.874 | 43.2878 | 0
8.3042 | 9.7099 | 2.0768 | 2.1152 | 2.9744 | 2.9846 | 7.576 | 6.5783 | 18.014 | 20.1292 | 27.7053 | 34.2836 | 8.3042 | 9.7099 | 2.0768 | 2.1152 | 2.9744 | 2.9946 | 7.576 | 6.5783 | 18.014 | 20.1292 | 27.7053 | 34.2836 | 0
5.8464 | 8.4992 | 1.9949 | 1.9923 | 4.3016 | 3.781 | 6.9616 | 5.4608 | 14.3457 | 16.338 | 24.4206 | 29.8814 | 5.8464 | 8.4992 | 1.9949 | 1.9923 | 4.3016 | 3.791 | 6.9616 | 5.4608 | 14.3457 | 16.338 | 24.4306 | 29.8914 | 0
13.8097 | 7.9667 | 2.2603 | 2.3905 | 3.6323 | 3.3794 | 8.9524 | 4.9693 | 21.7765 | 24.1669 | 33.1194 | 38.0887 | 13.8097 | 7.9667 | 2.2603 | 2.3905 | 3.6323 | 3.3894 | 8.9524 | 4.9693 | 21.7765 | 24.1669 | 33.1194 | 38.0887 | 0
9.7938 | 9.6921 | 2.1265 | 2.1897 | 3.7296 | 3.4377 | 7.9485 | 6.5619 | 19.4859 | 21.6756 | 29.6241 | 36.186 | 9.7938 | 9.6921 | 2.1265 | 2.1897 | 3.7296 | 3.4477 | 7.9485 | 6.5619 | 19.4859 | 21.6756 | 29.6241 | 36.186 | 0
10.3775 | 8.822 | 2.1459 | 2.2189 | 4.6453 | 3.9872 | 8.0944 | 5.7588 | 19.1995 | 21.4184 | 30.0509 | 35.8096 | 10.3775 | 8.822 | 2.1459 | 2.2189 | 4.6453 | 3.9972 | 8.0944 | 5.7588 | 19.1995 | 21.4184 | 30.0609 | 35.8196 | 0
15.8718 | 8.9485 | 2.3291 | 2.4936 | 2.8253 | 2.8952 | 9.468 | 5.8755 | 24.8203 | 27.3139 | 36.7818 | 42.6573 | 15.8718 | 8.9485 | 2.3291 | 2.4936 | 2.8253 | 2.9052 | 9.468 | 5.8755 | 24.8203 | 27.3139 | 36.7818 | 42.6573 | 0
4.9521 | 10.1389 | 1.9651 | 1.9476 | 2.6385 | 2.7831 | 6.738 | 6.9744 | 15.091 | 17.0386 | 23.7766 | 30.751 | 4.9521 | 10.1389 | 1.9651 | 1.9476 | 2.6385 | 2.7931 | 6.738 | 6.9744 | 15.091 | 17.0386 | 23.7766 | 30.751 | 0
3.8311 | 7.7729 | 1.9277 | 1.8916 | 2.9743 | 2.9846 | 6.4578 | 4.7904 | 11.604 | 13.4956 | 19.9533 | 24.7438 | 3.8311 | 7.7729 | 1.9277 | 1.8916 | 2.9743 | 2.9946 | 6.4578 | 4.7904 | 11.604 | 13.4956 | 19.9533 | 24.7438 | 0
5.8458 | 7.5301 | 1.9949 | 1.9923 | 1.9744 | 2.3846 | 6.9614 | 4.5662 | 13.3758 | 15.3681 | 22.3296 | 26.8958 | 5.8458 | 7.5301 | 1.9949 | 1.9923 | 1.9744 | 2.3946 | 6.9614 | 4.5662 | 13.3758 | 15.3681 | 22.3296 | 26.8958 | 0
-0.15369 | 7.9666 | 1.7949 | 1.6923 | 3.4835 | 3.2901 | 5.4616 | 4.9692 | 7.8129 | 9.5052 | 16.2788 | 21.248 | -0.15369 | 7.9666 | 1.7949 | 1.6923 | 3.4835 | 3.3001 | 5.4616 | 4.9692 | 7.8129 | 9.5052 | 16.2888 | 21.258 | 0
8.9011 | 6.6667 | 2.0967 | 2.1451 | 2.8402 | 2.9041 | 7.7253 | 3.7693 | 15.5678 | 17.7128 | 25.4381 | 29.2073 | 8.9011 | 6.6667 | 2.0967 | 2.1451 | 2.8402 | 2.9141 | 7.7253 | 3.7693 | 15.5678 | 17.7128 | 25.4381 | 29.2073 | 0
5.0411 | 8.6286 | 1.968 | 1.9521 | 2.9244 | 2.9547 | 6.7603 | 5.5802 | 13.6697 | 15.6217 | 22.382 | 27.9622 | 5.0411 | 8.6286 | 1.968 | 1.9521 | 2.9244 | 2.9647 | 6.7603 | 5.5802 | 13.6697 | 15.6217 | 22.382 | 27.9622 | 0
5.5467 | 7.7922 | 1.9849 | 1.9773 | 2.7834 | 2.87 | 6.8867 | 4.8082 | 13.3389 | 15.3163 | 22.2029 | 27.0112 | 5.5467 | 7.7922 | 1.9849 | 1.9773 | 2.7834 | 2.88 | 6.8867 | 4.8082 | 13.3389 | 15.3163 | 22.2029 | 27.0112 | 0
4.7002 | 7.9018 | 1.9567 | 1.935 | 2.2444 | 2.5466 | 6.675 | 4.9093 | 12.602 | 14.537 | 21.212 | 26.1214 | 4.7002 | 7.9018 | 1.9567 | 1.935 | 2.2444 | 2.5566 | 6.675 | 4.9093 | 12.602 | 14.537 | 21.212 | 26.1214 | 0
1.4663 | 7.7184 | 1.8489 | 1.7733 | 3.148 | 3.0888 | 5.8666 | 4.74 | 9.1847 | 10.958 | 17.1947 | 21.9348 | 1.4663 | 7.7184 | 1.8489 | 1.7733 | 3.148 | 3.0988 | 5.8666 | 4.74 | 9.1847 | 10.958 | 17.2047 | 21.9448 | 0
6.8879 | 7.0177 | 2.0296 | 2.0444 | 1.6145 | 2.1687 | 7.222 | 4.0933 | 13.9056 | 15.95 | 23.1719 | 27.2652 | 6.8879 | 7.0177 | 2.0296 | 2.0444 | 1.6145 | 2.1787 | 7.222 | 4.0933 | 13.9056 | 15.95 | 23.1719 | 27.2652 | 0
-2.3129 | 8.1924 | 1.7229 | 1.5844 | 2.1422 | 2.4853 | 4.9218 | 5.1776 | 5.8795 | 7.4639 | 12.3856 | 17.5632 | -2.3129 | 8.1924 | 1.7229 | 1.5844 | 2.1422 | 2.4953 | 4.9218 | 5.1776 | 5.8795 | 7.4639 | 12.3856 | 17.5632 | 0
0.85301 | 6.1989 | 1.8284 | 1.7427 | 3.3938 | 3.2363 | 5.7133 | 3.3374 | 7.0519 | 8.7945 | 15.4247 | 18.7621 | 0.85301 | 6.1989 | 1.8284 | 1.7427 | 3.3938 | 3.2463 | 5.7133 | 3.3374 | 7.0519 | 8.7945 | 15.4347 | 18.7721 | 0
8.363 | 6.8848 | 2.0788 | 2.1181 | 2.8631 | 2.9179 | 7.5907 | 3.9706 | 15.2478 | 17.366 | 24.9567 | 28.9273 | 8.363 | 6.8848 | 2.0788 | 2.1181 | 2.8631 | 2.9279 | 7.5907 | 3.9706 | 15.2478 | 17.366 | 24.9567 | 28.9273 | 0
5.1786 | 8.512 | 1.9726 | 1.9589 | 2.7811 | 2.8686 | 6.7946 | 5.4726 | 13.6906 | 15.6495 | 22.4441 | 27.9167 | 5.1786 | 8.512 | 1.9726 | 1.9589 | 2.7811 | 2.8786 | 6.7946 | 5.4726 | 13.6906 | 15.6495 | 22.4441 | 27.9167 | 0
4.6863 | 7.822 | 1.9562 | 1.9343 | 1.7183 | 2.231 | 6.6716 | 4.8357 | 12.5083 | 14.4427 | 21.1142 | 25.95 | 4.6863 | 7.822 | 1.9562 | 1.9343 | 1.7183 | 2.241 | 6.6716 | 4.8357 | 12.5083 | 14.4427 | 21.1142 | 25.95 | 0
-1.69 | 7.7154 | 1.7437 | 1.6155 | 2.6544 | 2.7926 | 5.0775 | 4.7373 | 6.0254 | 7.6409 | 13.0879 | 17.8252 | -1.69 | 7.7154 | 1.7437 | 1.6155 | 2.6544 | 2.8026 | 5.0775 | 4.7373 | 6.0254 | 7.6409 | 13.0979 | 17.8352 | 0
3.9263 | 6.3338 | 1.9309 | 1.8963 | 2.8467 | 2.908 | 6.4816 | 3.462 | 10.2601 | 12.1564 | 18.638 | 22.1 | 3.9263 | 6.3338 | 1.9309 | 1.8963 | 2.8467 | 2.918 | 6.4816 | 3.462 | 10.2601 | 12.1564 | 18.638 | 22.1 | 0
5.0801 | 7.5507 | 1.9693 | 1.954 | 2.9045 | 2.9427 | 6.77 | 4.5853 | 12.6307 | 14.5847 | 21.3548 | 25.94 | 5.0801 | 7.5507 | 1.9693 | 1.954 | 2.9045 | 2.9527 | 6.77 | 4.5853 | 12.6307 | 14.5847 | 21.3548 | 25.94 | 0
5.4268 | 7.8007 | 1.9809 | 1.9713 | 4.1252 | 3.6751 | 6.8567 | 4.816 | 13.2274 | 15.1988 | 22.9991 | 27.8151 | 5.4268 | 7.8007 | 1.9809 | 1.9713 | 4.1252 | 3.6851 | 6.8567 | 4.816 | 13.2274 | 15.1988 | 23.0091 | 27.8251 | 0
12.7511 | 7.8758 | 2.225 | 2.3376 | 3.8581 | 3.5149 | 8.6878 | 4.8854 | 20.6269 | 22.9645 | 31.6522 | 36.5376 | 12.7511 | 7.8758 | 2.225 | 2.3376 | 3.8581 | 3.5249 | 8.6878 | 4.8854 | 20.6269 | 22.9645 | 31.6522 | 36.5376 | 0
11.1487 | 9.4627 | 2.1716 | 2.2574 | 3.4723 | 3.2834 | 8.2872 | 6.3502 | 20.6114 | 22.8689 | 31.1561 | 37.5063 | 11.1487 | 9.4627 | 2.1716 | 2.2574 | 3.4723 | 3.2934 | 8.2872 | 6.3502 | 20.6114 | 22.8689 | 31.1561 | 37.5063 | 0
8.834 | 9.1156 | 2.0945 | 2.1417 | 3.2206 | 3.1323 | 7.7085 | 6.0297 | 17.9496 | 20.0913 | 27.7998 | 33.8295 | 8.834 | 9.1156 | 2.0945 | 2.1417 | 3.2206 | 3.1423 | 7.7085 | 6.0297 | 17.9496 | 20.0913 | 27.7998 | 33.8295 | 0
7.3235 | 8.614 | 2.0441 | 2.0662 | 3.2162 | 3.1297 | 7.3309 | 5.5668 | 15.9375 | 18.0037 | 25.3346 | 30.9014 | 7.3235 | 8.614 | 2.0441 | 2.0662 | 3.2162 | 3.1397 | 7.3309 | 5.5668 | 15.9375 | 18.0037 | 25.3346 | 30.9014 | 0
7.2969 | 8.2868 | 2.0432 | 2.0648 | 3.2464 | 3.1478 | 7.3242 | 5.2647 | 15.5837 | 17.6485 | 24.9727 | 30.2374 | 7.2969 | 8.2868 | 2.0432 | 2.0648 | 3.2464 | 3.1578 | 7.3242 | 5.2647 | 15.5837 | 17.6485 | 24.9727 | 30.2374 | 0
7.4785 | 8.281 | 2.0493 | 2.0739 | 1.9766 | 2.386 | 7.3696 | 5.2594 | 15.7595 | 17.8334 | 25.203 | 30.4624 | 7.4785 | 8.281 | 2.0493 | 2.0739 | 1.9766 | 2.396 | 7.3696 | 5.2594 | 15.7595 | 17.8334 | 25.203 | 30.4624 | 0
-0.14037 | 8.3203 | 1.7953 | 1.693 | 2.9701 | 2.9821 | 5.4649 | 5.2957 | 8.18 | 9.873 | 15.8251 | 21.1208 | -0.14037 | 8.3203 | 1.7953 | 1.693 | 2.9701 | 2.9921 | 5.4649 | 5.2957 | 8.18 | 9.873 | 15.8351 | 21.1308 | 0
5.8206 | 6.6696 | 1.994 | 1.991 | 1.6681 | 2.2008 | 6.9552 | 3.7719 | 12.4902 | 14.4813 | 21.4364 | 25.2083 | 5.8206 | 6.6696 | 1.994 | 1.991 | 1.6681 | 2.2108 | 6.9552 | 3.7719 | 12.4902 | 14.4813 | 21.4364 | 25.2083 | 0
-1.9916 | 7.9611 | 1.7336 | 1.6004 | 4.1051 | 3.6631 | 5.0021 | 4.9641 | 5.9696 | 7.57 | 15.3382 | 20.3023 | -1.9916 | 7.9611 | 1.7336 | 1.6004 | 4.1051 | 3.6731 | 5.0021 | 4.9641 | 5.9696 | 7.57 | 15.3482 | 20.3123 | 0
12.6307 | 6.2685 | 2.221 | 2.3315 | 3.1409 | 3.0845 | 8.6577 | 3.4017 | 18.8992 | 21.2308 | 29.8884 | 33.2901 | 12.6307 | 6.2685 | 2.221 | 2.3315 | 3.1409 | 3.0945 | 8.6577 | 3.4017 | 18.8992 | 21.2308 | 29.8884 | 33.2901 | 0
6.8453 | 9.4367 | 2.0282 | 2.0423 | 1.4547 | 2.0728 | 7.2113 | 6.3261 | 16.282 | 18.3243 | 25.5356 | 31.8617 | 6.8453 | 9.4367 | 2.0282 | 2.0423 | 1.4547 | 2.0828 | 7.2113 | 6.3261 | 16.282 | 18.3243 | 25.5356 | 31.8617 | 0
-3.272 | 8.1832 | 1.6909 | 1.5364 | 2.8971 | 2.9383 | 4.682 | 5.1691 | 4.9112 | 6.4476 | 12.283 | 17.452 | -3.272 | 8.1832 | 1.6909 | 1.5364 | 2.8971 | 2.9483 | 4.682 | 5.1691 | 4.9112 | 6.4476 | 12.293 | 17.462 | 0
5.3827 | 5.9911 | 1.9794 | 1.9691 | 4.3756 | 3.8253 | 6.8457 | 3.1456 | 11.3738 | 13.3429 | 21.5439 | 24.6895 | 5.3827 | 5.9911 | 1.9794 | 1.9691 | 4.3756 | 3.8353 | 6.8457 | 3.1456 | 11.3738 | 13.3429 | 21.5539 | 24.6995 | 0
14.2535 | 7.8663 | 2.2751 | 2.4127 | 2.174 | 2.5044 | 9.0634 | 4.8765 | 22.1197 | 24.5324 | 33.5958 | 38.4723 | 14.2535 | 7.8663 | 2.2751 | 2.4127 | 2.174 | 2.5144 | 9.0634 | 4.8765 | 22.1197 | 24.5324 | 33.5958 | 38.4723 | 0
1.0437 | 9.7882 | 1.8348 | 1.7522 | 2.1204 | 2.4722 | 5.7609 | 6.6507 | 10.832 | 12.5842 | 18.3451 | 24.9958 | 1.0437 | 9.7882 | 1.8348 | 1.7522 | 2.1204 | 2.4822 | 5.7609 | 6.6507 | 10.832 | 12.5842 | 18.3451 | 24.9958 | 0
0.72232 | 6.9261 | 1.8241 | 1.7361 | 3.0018 | 3.0011 | 5.6806 | 4.0087 | 7.6485 | 9.3846 | 15.3874 | 19.3962 | 0.72232 | 6.9261 | 1.8241 | 1.7361 | 3.0018 | 3.0111 | 5.6806 | 4.0087 | 7.6485 | 9.3846 | 15.3974 | 19.4062 | 0
6.0106 | 6.8565 | 2.0004 | 2.0005 | 2.5764 | 2.7458 | 7.0026 | 3.9445 | 12.8671 | 14.8676 | 21.8703 | 25.8147 | 6.0106 | 6.8565 | 2.0004 | 2.0005 | 2.5764 | 2.7558 | 7.0026 | 3.9445 | 12.8671 | 14.8676 | 21.8703 | 25.8147 | 0
3.4584 | 8.0023 | 1.9153 | 1.8729 | 0.37298 | 1.4238 | 6.3646 | 5.0021 | 11.4607 | 13.3337 | 19.6983 | 24.7004 | 3.4584 | 8.0023 | 1.9153 | 1.8729 | 0.37298 | 1.4338 | 6.3646 | 5.0021 | 11.4607 | 13.3337 | 19.6983 | 24.7004 | 0
-9.7621 | 7.4493 | 1.4746 | 1.2119 | 2.7077 | 2.8246 | 3.0595 | 4.4917 | -2.3128 | -1.1009 | 4.4314 | 8.9231 | -9.7621 | 7.4493 | 1.4746 | 1.2119 | 2.7077 | 2.8346 | 3.0595 | 4.4917 | -2.3128 | -1.1009 | 4.4414 | 8.9331 | 0
4.2463 | 4.5849 | 1.9415 | 1.9123 | 2.3095 | 2.5857 | 6.5616 | 1.8476 | 8.8311 | 10.7435 | 17.305 | 19.1526 | 4.2463 | 4.5849 | 1.9415 | 1.9123 | 2.3095 | 2.5957 | 6.5616 | 1.8476 | 8.8311 | 10.7435 | 17.305 | 19.1526 | 0
1.8569 | 7.62 | 1.8619 | 1.7928 | 3.3009 | 3.1806 | 5.9642 | 4.6493 | 9.4769 | 11.2698 | 17.7513 | 22.4005 | 1.8569 | 7.62 | 1.8619 | 1.7928 | 3.3009 | 3.1906 | 5.9642 | 4.6493 | 9.4769 | 11.2698 | 17.7613 | 22.4105 | 0
7.8055 | 7.1023 | 2.0602 | 2.0903 | 1.9738 | 2.3843 | 7.4514 | 4.1714 | 14.9079 | 16.9981 | 24.4495 | 28.6209 | 7.8055 | 7.1023 | 2.0602 | 2.0903 | 1.9738 | 2.3943 | 7.4514 | 4.1714 | 14.9079 | 16.9981 | 24.4495 | 28.6209 | 0
-0.15737 | 8.3912 | 1.7948 | 1.6921 | 2.3419 | 2.6052 | 5.4607 | 5.3611 | 8.2338 | 9.926 | 15.3866 | 20.7477 | -0.15737 | 8.3912 | 1.7948 | 1.6921 | 2.3419 | 2.6152 | 5.4607 | 5.3611 | 8.2338 | 9.926 | 15.3866 | 20.7477 | 0
2.0516 | 6.6659 | 1.8684 | 1.8026 | 4.6939 | 4.0163 | 6.0129 | 3.7685 | 8.7175 | 10.5201 | 19.2303 | 22.9989 | 2.0516 | 6.6659 | 1.8684 | 1.8026 | 4.6939 | 4.0263 | 6.0129 | 3.7685 | 8.7175 | 10.5201 | 19.2403 | 23.0089 | 0
16.1634 | 7.1445 | 2.3388 | 2.5082 | 2.4881 | 2.6928 | 9.5409 | 4.2103 | 23.308 | 25.8161 | 35.357 | 39.5673 | 16.1634 | 7.1445 | 2.3388 | 2.5082 | 2.4881 | 2.7028 | 9.5409 | 4.2103 | 23.308 | 25.8161 | 35.357 | 39.5673 | 0
2.9283 | 10.2021 | 1.8976 | 1.8464 | 1.8229 | 2.2937 | 6.2321 | 7.0327 | 13.1304 | 14.9768 | 21.2089 | 28.2416 | 2.9283 | 10.2021 | 1.8976 | 1.8464 | 1.8229 | 2.3037 | 6.2321 | 7.0327 | 13.1304 | 14.9768 | 21.2089 | 28.2416 | 0
-1.0626 | 7.3345 | 1.7646 | 1.6469 | 3.6826 | 3.4096 | 5.2344 | 4.3857 | 6.2719 | 7.9188 | 15.0109 | 19.3966 | -1.0626 | 7.3345 | 1.7646 | 1.6469 | 3.6826 | 3.4196 | 5.2344 | 4.3857 | 6.2719 | 7.9188 | 15.0209 | 19.4066 | 0
10.0956 | 6.4698 | 2.1365 | 2.2048 | 2.7751 | 2.865 | 8.0239 | 3.5875 | 16.5653 | 18.7701 | 26.794 | 30.3815 | 10.0956 | 6.4698 | 2.1365 | 2.2048 | 2.7751 | 2.875 | 8.0239 | 3.5875 | 16.5653 | 18.7701 | 26.794 | 30.3815 | 0
4.6504 | 8.8874 | 1.955 | 1.9325 | 4.5711 | 3.9427 | 6.6626 | 5.8191 | 13.5378 | 15.4703 | 23.9841 | 29.8032 | 4.6504 | 8.8874 | 1.955 | 1.9325 | 4.5711 | 3.9527 | 6.6626 | 5.8191 | 13.5378 | 15.4703 | 23.9941 | 29.8132 | 0
15.4267 | 7.7076 | 2.3142 | 2.4713 | 4.305 | 3.783 | 9.3567 | 4.7301 | 23.1343 | 25.6057 | 34.9624 | 39.6924 | 15.4267 | 7.7076 | 2.3142 | 2.4713 | 4.305 | 3.793 | 9.3567 | 4.7301 | 23.1343 | 25.6057 | 34.9624 | 39.6924 | 0
13.8297 | 10.0425 | 2.261 | 2.3915 | 2.4924 | 2.6954 | 8.9574 | 6.8853 | 23.8722 | 26.2637 | 35.2211 | 42.1065 | 13.8297 | 10.0425 | 2.261 | 2.3915 | 2.4924 | 2.7054 | 8.9574 | 6.8853 | 23.8722 | 26.2637 | 35.2211 | 42.1065 | 0
2.9545 | 9.6964 | 1.8985 | 1.8477 | 3.7825 | 3.4695 | 6.2386 | 6.5659 | 12.6509 | 14.4986 | 21.7506 | 28.3166 | 2.9545 | 9.6964 | 1.8985 | 1.8477 | 3.7825 | 3.4795 | 6.2386 | 6.5659 | 12.6509 | 14.4986 | 21.7606 | 28.3266 | 0
10.6949 | 7.3401 | 2.1565 | 2.2347 | 2.8622 | 2.9173 | 8.1737 | 4.3909 | 18.035 | 20.2698 | 28.4435 | 32.8344 | 10.6949 | 7.3401 | 2.1565 | 2.2347 | 2.8622 | 2.9273 | 8.1737 | 4.3909 | 18.035 | 20.2698 | 28.4435 | 32.8344 | 0
5.1733 | 9.0172 | 1.9724 | 1.9587 | 3.1984 | 3.119 | 6.7933 | 5.939 | 14.1905 | 16.1492 | 22.9425 | 28.8815 | 5.1733 | 9.0172 | 1.9724 | 1.9587 | 3.1984 | 3.129 | 6.7933 | 5.939 | 14.1905 | 16.1492 | 22.9425 | 28.8815 | 0
7.1904 | 7.8209 | 2.0397 | 2.0595 | 1.3371 | 2.0022 | 7.2976 | 4.8347 | 15.0112 | 17.0708 | 24.3683 | 29.203 | 7.1904 | 7.8209 | 2.0397 | 2.0595 | 1.3371 | 2.0122 | 7.2976 | 4.8347 | 15.0112 | 17.0708 | 24.3683 | 29.203 | 0
-3.9776 | 8.2579 | 1.6674 | 1.5011 | 2.9624 | 2.9775 | 4.5056 | 5.2381 | 4.2803 | 5.7815 | 11.7213 | 16.9594 | -3.9776 | 8.2579 | 1.6674 | 1.5011 | 2.9624 | 2.9875 | 4.5056 | 5.2381 | 4.2803 | 5.7815 | 11.7313 | 16.9694 | 0
5.7745 | 5.8382 | 1.9925 | 1.9887 | 3.2345 | 3.1407 | 6.9436 | 3.0045 | 11.6127 | 13.6015 | 20.5451 | 23.5496 | 5.7745 | 5.8382 | 1.9925 | 1.9887 | 3.2345 | 3.1507 | 6.9436 | 3.0045 | 11.6127 | 13.6015 | 20.5451 | 23.5496 | 0
7.4073 | 7.9511 | 2.0469 | 2.0704 | 3.9585 | 3.5751 | 7.3518 | 4.9549 | 15.3584 | 17.4288 | 24.9625 | 29.9174 | 7.4073 | 7.9511 | 2.0469 | 2.0704 | 3.9585 | 3.5851 | 7.3518 | 4.9549 | 15.3584 | 17.4288 | 24.9725 | 29.9274 | 0
11.7513 | 8.3049 | 2.1917 | 2.2876 | 2.7908 | 2.8745 | 8.4378 | 5.2815 | 20.0562 | 22.3438 | 30.7816 | 36.063 | 11.7513 | 8.3049 | 2.1917 | 2.2876 | 2.7908 | 2.8845 | 8.4378 | 5.2815 | 20.0562 | 22.3438 | 30.7816 | 36.063 | 0
4.7449 | 9.2461 | 1.9582 | 1.9372 | 1.7315 | 2.2389 | 6.6862 | 6.1503 | 13.991 | 15.9283 | 22.6145 | 28.7648 | 4.7449 | 9.2461 | 1.9582 | 1.9372 | 1.7315 | 2.2489 | 6.6862 | 6.1503 | 13.991 | 15.9283 | 22.6145 | 28.7648 | 0
-1.6111 | 7.7281 | 1.7463 | 1.6194 | 2.8944 | 2.9366 | 5.0972 | 4.749 | 6.1169 | 7.7364 | 13.5674 | 18.3163 | -1.6111 | 7.7281 | 1.7463 | 1.6194 | 2.8944 | 2.9466 | 5.0972 | 4.749 | 6.1169 | 7.7364 | 13.5774 | 18.3263 | 0
5.3662 | 6.3509 | 1.9789 | 1.9683 | 3.0773 | 3.0464 | 6.8415 | 3.4778 | 11.7171 | 13.6854 | 20.527 | 24.0047 | 5.3662 | 6.3509 | 1.9789 | 1.9683 | 3.0773 | 3.0564 | 6.8415 | 3.4778 | 11.7171 | 13.6854 | 20.527 | 24.0047 | 0
6.4638 | 7.8627 | 2.0155 | 2.0232 | 2.5815 | 2.7489 | 7.116 | 4.8732 | 14.3265 | 16.3497 | 23.4657 | 28.3389 | 6.4638 | 7.8627 | 2.0155 | 2.0232 | 2.5815 | 2.7589 | 7.116 | 4.8732 | 14.3265 | 16.3497 | 23.4657 | 28.3389 | 0
3.4889 | 8.1005 | 1.9163 | 1.8744 | 1.8665 | 2.3199 | 6.3722 | 5.0928 | 11.5894 | 13.4638 | 19.836 | 24.9288 | 3.4889 | 8.1005 | 1.9163 | 1.8744 | 1.8665 | 2.3299 | 6.3722 | 5.0928 | 11.5894 | 13.4638 | 19.836 | 24.9288 | 0
-0.80079 | 7.4559 | 1.7733 | 1.66 | 4.0774 | 3.6465 | 5.2998 | 4.4978 | 6.6551 | 8.3151 | 16.039 | 20.5368 | -0.80079 | 7.4559 | 1.7733 | 1.66 | 4.0774 | 3.6565 | 5.2998 | 4.4978 | 6.6551 | 8.3151 | 16.049 | 20.5468 | 0
12.4646 | 6.5265 | 2.2155 | 2.3232 | 2.1699 | 2.5019 | 8.6161 | 3.6398 | 18.9911 | 21.3143 | 29.9305 | 33.5703 | 12.4646 | 6.5265 | 2.2155 | 2.3232 | 2.1699 | 2.5119 | 8.6161 | 3.6398 | 18.9911 | 21.3143 | 29.9305 | 33.5703 | 0
1.0194 | 9.4007 | 1.834 | 1.751 | 4.2351 | 3.7411 | 5.7549 | 6.2929 | 10.4201 | 12.1711 | 20.1472 | 26.4401 | 1.0194 | 9.4007 | 1.834 | 1.751 | 4.2351 | 3.7511 | 5.7549 | 6.2929 | 10.4201 | 12.1711 | 20.1572 | 26.4501 | 0
13.4105 | 6.9209 | 2.247 | 2.3705 | 1.9519 | 2.3711 | 8.8526 | 4.0039 | 20.3314 | 22.7019 | 31.5546 | 35.5585 | 13.4105 | 6.9209 | 2.247 | 2.3705 | 1.9519 | 2.3811 | 8.8526 | 4.0039 | 20.3314 | 22.7019 | 31.5546 | 35.5585 | 0
-0.28881 | 9.6056 | 1.7904 | 1.6856 | 2.9194 | 2.9516 | 5.4278 | 6.4821 | 9.3168 | 11.0024 | 16.8734 | 23.3555 | -0.28881 | 9.6056 | 1.7904 | 1.6856 | 2.9194 | 2.9616 | 5.4278 | 6.4821 | 9.3168 | 11.0024 | 16.8834 | 23.3655 | 0
5.5165 | 6.6374 | 1.9839 | 1.9758 | 3.7465 | 3.4479 | 6.8791 | 3.7422 | 12.1539 | 14.1297 | 21.3241 | 25.0664 | 5.5165 | 6.6374 | 1.9839 | 1.9758 | 3.7465 | 3.4579 | 6.8791 | 3.7422 | 12.1539 | 14.1297 | 21.3341 | 25.0764 | 0
10.479 | 7.8952 | 2.1493 | 2.2239 | 2.4963 | 2.6978 | 8.1197 | 4.9033 | 18.3742 | 20.5982 | 28.7179 | 33.6212 | 10.479 | 7.8952 | 2.1493 | 2.2239 | 2.4963 | 2.7078 | 8.1197 | 4.9033 | 18.3742 | 20.5982 | 28.7179 | 33.6212 | 0
2.978 | 8.9704 | 1.8993 | 1.8489 | 4.1729 | 3.7037 | 6.2445 | 5.8958 | 11.9484 | 13.7973 | 21.6739 | 27.5697 | 2.978 | 8.9704 | 1.8993 | 1.8489 | 4.1729 | 3.7137 | 6.2445 | 5.8958 | 11.9484 | 13.7973 | 21.6839 | 27.5797 | 0
13.0371 | 7.3452 | 2.2346 | 2.3519 | 5.043 | 4.2258 | 8.7593 | 4.3956 | 20.3823 | 22.7342 | 32.0031 | 36.3986 | 13.0371 | 7.3452 | 2.2346 | 2.3519 | 5.043 | 4.2358 | 8.7593 | 4.3956 | 20.3823 | 22.7342 | 32.0131 | 36.4086 | 0
18.2582 | 9.5247 | 2.4086 | 2.6129 | 1.3136 | 1.9881 | 10.0646 | 6.4074 | 27.7829 | 30.3958 | 40.4604 | 46.8678 | 18.2582 | 9.5247 | 2.4086 | 2.6129 | 1.3136 | 1.9981 | 10.0646 | 6.4074 | 27.7829 | 30.3958 | 40.4604 | 46.8678 | 0
-4.1186 | 10.6559 | 1.6627 | 1.4941 | 3.5481 | 3.3289 | 4.4704 | 7.4516 | 6.5374 | 8.0314 | 14.9084 | 22.36 | -4.1186 | 10.6559 | 1.6627 | 1.4941 | 3.5481 | 3.3389 | 4.4704 | 7.4516 | 6.5374 | 8.0314 | 14.9184 | 22.37 | 0
9.2885 | 5.8076 | 2.1096 | 2.1644 | 2.9226 | 2.9536 | 7.8221 | 2.9763 | 15.0962 | 17.2606 | 25.0828 | 28.059 | 9.2885 | 5.8076 | 2.1096 | 2.1644 | 2.9226 | 2.9636 | 7.8221 | 2.9763 | 15.0962 | 17.2606 | 25.0828 | 28.059 | 0
5.5355 | 8.7125 | 1.9845 | 1.9768 | 5.2821 | 4.3692 | 6.8839 | 5.6577 | 14.2481 | 16.2248 | 25.8761 | 31.5339 | 5.5355 | 8.7125 | 1.9845 | 1.9768 | 5.2821 | 4.3792 | 6.8839 | 5.6577 | 14.2481 | 16.2248 | 25.8861 | 31.5439 | 0
19.6924 | 7.8994 | 2.4564 | 2.6846 | 1.3027 | 1.9816 | 10.4231 | 4.9071 | 27.5918 | 30.2764 | 40.6995 | 45.6066 | 19.6924 | 7.8994 | 2.4564 | 2.6846 | 1.3027 | 1.9916 | 10.4231 | 4.9071 | 27.5918 | 30.2764 | 40.6995 | 45.6066 | 0
-4.1837 | 10.9667 | 1.6605 | 1.4908 | 2.4833 | 2.69 | 4.4541 | 7.7385 | 6.7829 | 8.2738 | 13.447 | 21.1855 | -4.1837 | 10.9667 | 1.6605 | 1.4908 | 2.4833 | 2.7 | 4.4541 | 7.7385 | 6.7829 | 8.2738 | 13.457 | 21.1955 | 0
2.8996 | 5.7935 | 1.8967 | 1.845 | 4.6737 | 4.0042 | 6.2249 | 2.9633 | 8.6931 | 10.5381 | 19.216 | 22.1792 | 2.8996 | 5.7935 | 1.8967 | 1.845 | 4.6737 | 4.0142 | 6.2249 | 2.9633 | 8.6931 | 10.5381 | 19.226 | 22.1892 | 0
16.0422 | 7.3282 | 2.3347 | 2.5021 | 2.969 | 2.9814 | 9.5106 | 4.3799 | 23.3705 | 25.8726 | 35.3831 | 39.7631 | 16.0422 | 7.3282 | 2.3347 | 2.5021 | 2.969 | 2.9914 | 9.5106 | 4.3799 | 23.3705 | 25.8726 | 35.3831 | 39.7631 | 0
5.8138 | 10.1758 | 1.9938 | 1.9907 | 2.7846 | 2.8708 | 6.9534 | 7.0084 | 15.9896 | 17.9803 | 24.9337 | 31.9422 | 5.8138 | 10.1758 | 1.9938 | 1.9907 | 2.7846 | 2.8808 | 6.9534 | 7.0084 | 15.9896 | 17.9803 | 24.9337 | 31.9422 | 0
4.7076 | 7.9596 | 1.9569 | 1.9354 | 2.5954 | 2.7572 | 6.6769 | 4.9628 | 12.6673 | 14.6026 | 21.2795 | 26.2423 | 4.7076 | 7.9596 | 1.9569 | 1.9354 | 2.5954 | 2.7672 | 6.6769 | 4.9628 | 12.6673 | 14.6026 | 21.2795 | 26.2423 | 0
3.5724 | 7.72 | 1.9191 | 1.8786 | 4.397 | 3.8382 | 6.3931 | 4.7415 | 11.2924 | 13.171 | 21.4063 | 26.1478 | 3.5724 | 7.72 | 1.9191 | 1.8786 | 4.397 | 3.8482 | 6.3931 | 4.7415 | 11.2924 | 13.171 | 21.4163 | 26.1578 | 0
14.3822 | 7.474 | 2.2794 | 2.4191 | 2.2841 | 2.5705 | 9.0955 | 4.5145 | 21.8562 | 24.2753 | 33.3709 | 37.8854 | 14.3822 | 7.474 | 2.2794 | 2.4191 | 2.2841 | 2.5805 | 9.0955 | 4.5145 | 21.8562 | 24.2753 | 33.3709 | 37.8854 | 0
1.7047 | 9.8161 | 1.8568 | 1.7852 | 3.83 | 3.498 | 5.9262 | 6.6764 | 11.5209 | 13.3061 | 20.6341 | 27.3105 | 1.7047 | 9.8161 | 1.8568 | 1.7852 | 3.83 | 3.508 | 5.9262 | 6.6764 | 11.5209 | 13.3061 | 20.6441 | 27.3205 | 0
10.98 | 7.0694 | 2.166 | 2.249 | 3.431 | 3.2586 | 8.245 | 4.1409 | 18.0494 | 20.2984 | 28.5434 | 32.6843 | 10.98 | 7.0694 | 2.166 | 2.249 | 3.431 | 3.2686 | 8.245 | 4.1409 | 18.0494 | 20.2984 | 28.5434 | 32.6843 | 0
8.5858 | 9.079 | 2.0862 | 2.1293 | 2.0667 | 2.44 | 7.6465 | 5.996 | 17.6648 | 19.7941 | 27.4406 | 33.4366 | 8.5858 | 9.079 | 2.0862 | 2.1293 | 2.0667 | 2.45 | 7.6465 | 5.996 | 17.6648 | 19.7941 | 27.4406 | 33.4366 | 0
0.40007 | 8.5603 | 1.8133 | 1.72 | 3.5941 | 3.3565 | 5.6 | 5.5172 | 8.9603 | 10.6803 | 17.6309 | 23.1481 | 0.40007 | 8.5603 | 1.8133 | 1.72 | 3.5941 | 3.3665 | 5.6 | 5.5172 | 8.9603 | 10.6803 | 17.6409 | 23.1581 | 0
9.5647 | 6.7867 | 2.1188 | 2.1782 | 3.2553 | 3.1532 | 7.8912 | 3.88 | 16.3514 | 18.5296 | 26.4208 | 30.3008 | 9.5647 | 6.7867 | 2.1188 | 2.1782 | 3.2553 | 3.1632 | 7.8912 | 3.88 | 16.3514 | 18.5296 | 26.4208 | 30.3008 | 0
7.5316 | 8.7723 | 2.0511 | 2.0766 | 3.3519 | 3.2111 | 7.3829 | 5.7129 | 16.3039 | 18.3805 | 25.7634 | 31.4763 | 7.5316 | 8.7723 | 2.0511 | 2.0766 | 3.3519 | 3.2211 | 7.3829 | 5.7129 | 16.3039 | 18.3805 | 25.7634 | 31.4763 | 0
8.1115 | 8.3318 | 2.0704 | 2.1056 | 2.3366 | 2.602 | 7.5279 | 5.3063 | 16.4433 | 18.5489 | 26.0767 | 31.3831 | 8.1115 | 8.3318 | 2.0704 | 2.1056 | 2.3366 | 2.612 | 7.5279 | 5.3063 | 16.4433 | 18.5489 | 26.0767 | 31.3831 | 0
2.0197 | 8.4575 | 1.8673 | 1.801 | 2.4549 | 2.6729 | 6.0049 | 5.4223 | 10.4772 | 12.2782 | 18.2831 | 23.7054 | 2.0197 | 8.4575 | 1.8673 | 1.801 | 2.4549 | 2.6829 | 6.0049 | 5.4223 | 10.4772 | 12.2782 | 18.2831 | 23.7054 | 0
2.7292 | 7.1376 | 1.891 | 1.8365 | 3.3007 | 3.1804 | 6.1823 | 4.2039 | 9.8668 | 11.7033 | 18.1844 | 22.3883 | 2.7292 | 7.1376 | 1.891 | 1.8365 | 3.3007 | 3.1904 | 6.1823 | 4.2039 | 9.8668 | 11.7033 | 18.1944 | 22.3983 | 0
7.8041 | 7.2913 | 2.0601 | 2.0902 | 3.2421 | 3.1452 | 7.451 | 4.3458 | 15.0954 | 17.1856 | 24.6366 | 28.9825 | 7.8041 | 7.2913 | 2.0601 | 2.0902 | 3.2421 | 3.1552 | 7.451 | 4.3458 | 15.0954 | 17.1856 | 24.6366 | 28.9825 | 0
7.4524 | 8.3909 | 2.0484 | 2.0726 | 3.8806 | 3.5284 | 7.3631 | 5.3608 | 15.8432 | 17.9159 | 25.3248 | 30.6856 | 7.4524 | 8.3909 | 2.0484 | 2.0726 | 3.8806 | 3.5384 | 7.3631 | 5.3608 | 15.8432 | 17.9159 | 25.3348 | 30.6956 | 0
11.2836 | 8.3147 | 2.1761 | 2.2642 | 5.2907 | 4.3744 | 8.3209 | 5.2905 | 19.5983 | 21.8625 | 31.5276 | 36.8181 | 11.2836 | 8.3147 | 2.1761 | 2.2642 | 5.2907 | 4.3844 | 8.3209 | 5.2905 | 19.5983 | 21.8625 | 31.5376 | 36.8281 | 0
19.7442 | 9.1448 | 2.4581 | 2.6872 | 2.4446 | 2.6667 | 10.4361 | 6.0567 | 28.889 | 31.5762 | 42.0123 | 48.069 | 19.7442 | 9.1448 | 2.4581 | 2.6872 | 2.4446 | 2.6767 | 10.4361 | 6.0567 | 28.889 | 31.5762 | 42.0123 | 48.069 | 0
2.6675 | 10.9779 | 1.8889 | 1.8334 | 2.5403 | 2.7242 | 6.1669 | 7.7488 | 13.6454 | 15.4788 | 21.6456 | 29.3945 | 2.6675 | 10.9779 | 1.8889 | 1.8334 | 2.5403 | 2.7342 | 6.1669 | 7.7488 | 13.6454 | 15.4788 | 21.6456 | 29.3945 | 0
3.2415 | 7.278 | 1.9081 | 1.8621 | 1.9326 | 2.3596 | 6.3104 | 4.3335 | 10.5195 | 12.3816 | 18.692 | 23.0255 | 3.2415 | 7.278 | 1.9081 | 1.8621 | 1.9326 | 2.3696 | 6.3104 | 4.3335 | 10.5195 | 12.3816 | 18.692 | 23.0255 | 0
-0.40435 | 7.4023 | 1.7865 | 1.6798 | 3.4463 | 3.2678 | 5.3989 | 4.4483 | 6.998 | 8.6778 | 15.3919 | 19.8402 | -0.40435 | 7.4023 | 1.7865 | 1.6798 | 3.4463 | 3.2778 | 5.3989 | 4.4483 | 6.998 | 8.6778 | 15.4019 | 19.8502 | 0
0

## test activity G
A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | diff
5.6668 | 4.8209 | 2.1112 | 1.6188 | 3.9684 | 2.1602 | 8.0072 | 5.3638 | 10.4876 | 12.1064 | 20.1136 | 25.4775 | 5.6668 | 4.8209 | 2.1112 | 1.6188 | 3.9684 | 2.1602 | 8.0172 | 5.3638 | 10.4876 | 12.1064 | 20.1236 | 25.4875 | 0.01
4.2856 | 10.8835 | 1.8169 | 1.9908 | 2.3642 | 3.5081 | 5.759 | 3.9775 | 15.1691 | 17.1599 | 23.0322 | 27.0097 | 4.2856 | 10.8835 | 1.8169 | 1.9908 | 2.3642 | 3.5081 | 5.769 | 3.9775 | 15.1691 | 17.1599 | 23.0322 | 27.0097 | 0.01
5.6033 | 6.1942 | 1.8437 | 1.9592 | 3.2551 | 2.1934 | 7.0654 | 6.0316 | 11.7975 | 13.7567 | 20.822 | 26.8537 | 5.6033 | 6.1942 | 1.8437 | 1.9592 | 3.2551 | 2.1934 | 7.0754 | 6.0316 | 11.7975 | 13.7567 | 20.832 | 26.8637 | 0.01
5.3574 | 7.0043 | 1.8875 | 2.3328 | 2.478 | 2.4376 | 6.6629 | 2.4772 | 12.3618 | 14.6946 | 21.3575 | 23.8347 | 5.3574 | 7.0043 | 1.8875 | 2.3328 | 2.478 | 2.4376 | 6.6729 | 2.4772 | 12.3618 | 14.6946 | 21.3675 | 23.8447 | 0.01
6.1496 | 7.7953 | 1.9943 | 1.8372 | 3.7999 | 3.2774 | 5.257 | 5.2541 | 13.945 | 15.7821 | 22.8594 | 28.1135 | 6.1496 | 7.7953 | 1.9943 | 1.8372 | 3.7999 | 3.2774 | 5.267 | 5.2541 | 13.945 | 15.7821 | 22.8594 | 28.1135 | 0.01
5.5219 | 8.494 | 1.8886 | 2.1791 | 4.1127 | 3.1161 | 7.4896 | 6.1474 | 14.0159 | 16.195 | 23.6847 | 29.8321 | 5.5219 | 8.494 | 1.8886 | 2.1791 | 4.1127 | 3.1161 | 7.4996 | 6.1474 | 14.0159 | 16.195 | 23.6947 | 29.8421 | 0.01
6.7352 | 8.5595 | 1.8737 | 1.967 | 3.2408 | 2.2162 | 5.9339 | 3.329 | 15.2947 | 17.2618 | 23.1957 | 26.5246 | 6.7352 | 8.5595 | 1.8737 | 1.967 | 3.2408 | 2.2162 | 5.9439 | 3.329 | 15.2947 | 17.2618 | 23.2057 | 26.5346 | 0.01
5.83 | 7.9796 | 2.3076 | 1.7437 | 2.3374 | 2.064 | 6.571 | 4.6228 | 13.8096 | 15.5533 | 22.1243 | 26.7471 | 5.83 | 7.9796 | 2.3076 | 1.7437 | 2.3374 | 2.064 | 6.581 | 4.6228 | 13.8096 | 15.5533 | 22.1343 | 26.7571 | 0.01
6.0532 | 7.5455 | 1.9694 | 2.1107 | 1.2006 | 3.1672 | 6.6808 | 5.9132 | 13.5987 | 15.7093 | 22.3902 | 28.3034 | 6.0532 | 7.5455 | 1.9694 | 2.1107 | 1.2006 | 3.1672 | 6.6908 | 5.9132 | 13.5987 | 15.7093 | 22.4002 | 28.3134 | 0.01
7.1293 | 6.9177 | 2.2553 | 1.9092 | 1.402 | 2.3078 | 5.4718 | 6.7733 | 14.047 | 15.9562 | 21.428 | 28.2013 | 7.1293 | 6.9177 | 2.2553 | 1.9092 | 1.402 | 2.3078 | 5.4818 | 6.7733 | 14.047 | 15.9562 | 21.438 | 28.2113 | 0.01
5.3165 | 7.4508 | 2.0122 | 1.7265 | 2.9514 | 2.2788 | 5.8729 | 4.332 | 12.7673 | 14.4939 | 20.3667 | 24.6988 | 5.3165 | 7.4508 | 2.0122 | 1.7265 | 2.9514 | 2.2788 | 5.8829 | 4.332 | 12.7673 | 14.4939 | 20.3767 | 24.7088 | 0.01
6.013 | 7.9794 | 1.9731 | 1.9985 | 3.0427 | 3.9799 | 6.5273 | 5.3465 | 13.9924 | 15.9909 | 23.0135 | 28.36 | 6.013 | 7.9794 | 1.9731 | 1.9985 | 3.0427 | 3.9799 | 6.5373 | 5.3465 | 13.9924 | 15.9909 | 23.0135 | 28.36 | 0.01
6.1398 | 7.3413 | 1.923 | 2.1092 | 3.4813 | 2.6986 | 7.5509 | 4.5727 | 13.4811 | 15.5904 | 23.1413 | 27.714 | 6.1398 | 7.3413 | 1.923 | 2.1092 | 3.4813 | 2.6986 | 7.5609 | 4.5727 | 13.4811 | 15.5904 | 23.1513 | 27.724 | 0.01
6.5041 | 8.4446 | 2.306 | 2.1468 | 2.1629 | 2.7143 | 7.9768 | 5.577 | 14.9487 | 17.0956 | 25.0724 | 30.6494 | 6.5041 | 8.4446 | 2.306 | 2.1468 | 2.1629 | 2.7143 | 7.9868 | 5.577 | 14.9487 | 17.0956 | 25.0824 | 30.6594 | 0.01
6.7143 | 12.2231 | 2.2144 | 1.8661 | 3.0979 | 3.0341 | 4.9646 | 4.4604 | 18.9375 | 20.8036 | 26.9356 | 31.396 | 6.7143 | 12.2231 | 2.2144 | 1.8661 | 3.0979 | 3.0341 | 4.9746 | 4.4604 | 18.9375 | 20.8036 | 26.9356 | 31.396 | 0.01
6.4559 | 7.7546 | 2.1855 | 2.481 | 3.0613 | 2.5562 | 7.3613 | 3.6555 | 14.2105 | 16.6915 | 24.0528 | 27.7083 | 6.4559 | 7.7546 | 2.1855 | 2.481 | 3.0613 | 2.5562 | 7.3713 | 3.6555 | 14.2105 | 16.6915 | 24.0628 | 27.7183 | 0.01
5.8197 | 7.5922 | 2.2865 | 1.9024 | 1.6798 | 3.093 | 7.1288 | 4.4282 | 13.4119 | 15.3143 | 22.4431 | 26.8714 | 5.8197 | 7.5922 | 2.2865 | 1.9024 | 1.6798 | 3.093 | 7.1388 | 4.4282 | 13.4119 | 15.3143 | 22.4531 | 26.8814 | 0.01
5.0677 | 10.0863 | 2.0456 | 1.5542 | 3.6668 | 2.8954 | 7.2348 | 3.382 | 15.1541 | 16.7083 | 23.943 | 27.325 | 5.0677 | 10.0863 | 2.0456 | 1.5542 | 3.6668 | 2.8954 | 7.2448 | 3.382 | 15.1541 | 16.7083 | 23.953 | 27.335 | 0.01
7.3396 | 6.5634 | 1.9043 | 1.6085 | 2.7229 | 2.0482 | 7.9982 | 6.5485 | 13.9029 | 15.5114 | 23.5096 | 30.0581 | 7.3396 | 6.5634 | 1.9043 | 1.6085 | 2.7229 | 2.0482 | 8.0082 | 6.5485 | 13.9029 | 15.5114 | 23.5196 | 30.0681 | 0.01
5.9705 | 9.5233 | 2.0371 | 1.423 | 1.5738 | 2.9958 | 6.8993 | 4.1268 | 15.4938 | 16.9168 | 23.8162 | 27.943 | 5.9705 | 9.5233 | 2.0371 | 1.423 | 1.5738 | 2.9958 | 6.9093 | 4.1268 | 15.4938 | 16.9168 | 23.8262 | 27.953 | 0.01
5.4917 | 6.9881 | 1.8075 | 2.0849 | 2.6716 | 3.2662 | 7.7432 | 7.1028 | 12.4798 | 14.5647 | 22.308 | 29.4108 | 5.4917 | 6.9881 | 1.8075 | 2.0849 | 2.6716 | 3.2662 | 7.7532 | 7.1028 | 12.4798 | 14.5647 | 22.318 | 29.4208 | 0.01
6.7304 | 7.8701 | 2.1443 | 2.5745 | 2.5558 | 3.5329 | 7.5438 | 2.3886 | 14.6005 | 17.175 | 24.7188 | 27.1074 | 6.7304 | 7.8701 | 2.1443 | 2.5745 | 2.5558 | 3.5329 | 7.5538 | 2.3886 | 14.6005 | 17.175 | 24.7288 | 27.1174 | 0.01
5.9637 | 8.0801 | 2.2506 | 1.8486 | 3.65 | 2.9022 | 5.255 | 4.8216 | 14.0438 | 15.8923 | 22.4445 | 27.2661 | 5.9637 | 8.0801 | 2.2506 | 1.8486 | 3.65 | 2.9022 | 5.265 | 4.8216 | 14.0438 | 15.8923 | 22.4445 | 27.2661 | 0.01
6.2726 | 8.9295 | 1.6932 | 1.8247 | 3.6043 | 3.5309 | 8.0208 | 2.1659 | 15.2021 | 17.0268 | 25.0476 | 27.2135 | 6.2726 | 8.9295 | 1.6932 | 1.8247 | 3.6043 | 3.5309 | 8.0308 | 2.1659 | 15.2021 | 17.0268 | 25.0576 | 27.2235 | 0.01
6.7398 | 9.336 | 1.9627 | 1.7956 | 2.6126 | 2.6798 | 8.996 | 4.7416 | 16.0758 | 17.8714 | 26.8674 | 31.609 | 6.7398 | 9.336 | 1.9627 | 1.7956 | 2.6126 | 2.6798 | 9.006 | 4.7416 | 16.0758 | 17.8714 | 26.8774 | 31.619 | 0.01
5.4937 | 7.716 | 2.0587 | 2.1896 | 2.9639 | 2.9342 | 3.9275 | 4.7492 | 13.2097 | 15.3992 | 21.2974 | 26.0466 | 5.4937 | 7.716 | 2.0587 | 2.1896 | 2.9639 | 2.9342 | 3.9375 | 4.7492 | 13.2097 | 15.3992 | 21.2974 | 26.0466 | 0.01
6.3368 | 6.272 | 1.7092 | 1.9503 | 2.6605 | 2.6124 | 6.1776 | 5.3067 | 12.6089 | 14.5591 | 20.7367 | 26.0434 | 6.3368 | 6.272 | 1.7092 | 1.9503 | 2.6605 | 2.6124 | 6.1876 | 5.3067 | 12.6089 | 14.5591 | 20.7467 | 26.0534 | 0.01
5.9099 | 9.7705 | 2.0143 | 1.8608 | 2.8884 | 2.3321 | 5.0959 | 4.7865 | 15.6804 | 17.5412 | 22.7617 | 27.5482 | 5.9099 | 9.7705 | 2.0143 | 1.8608 | 2.8884 | 2.3321 | 5.1059 | 4.7865 | 15.6804 | 17.5412 | 22.7617 | 27.5482 | 0.01
5.5164 | 7.7817 | 1.9795 | 2.2597 | 3.4574 | 3.4756 | 9.5614 | 4.8424 | 13.2981 | 15.5578 | 25.1192 | 29.9617 | 5.5164 | 7.7817 | 1.9795 | 2.2597 | 3.4574 | 3.4756 | 9.5714 | 4.8424 | 13.2981 | 15.5578 | 25.1292 | 29.9717 | 0.01
5.6445 | 8.9087 | 2.2913 | 1.6788 | -0.26399 | 2.3575 | 7.2252 | 4.8622 | 14.5532 | 16.2319 | 23.4572 | 28.3194 | 5.6445 | 8.9087 | 2.2913 | 1.6788 | -0.26399 | 2.3575 | 7.2352 | 4.8622 | 14.5532 | 16.2319 | 23.4672 | 28.3294 | 0.01
6.3989 | 6.4713 | 2.1593 | 2.0496 | 2.2743 | 2.5209 | 7.7424 | 2.7155 | 12.8702 | 14.9198 | 22.6622 | 25.3778 | 6.3989 | 6.4713 | 2.1593 | 2.0496 | 2.2743 | 2.5209 | 7.7524 | 2.7155 | 12.8702 | 14.9198 | 22.6722 | 25.3878 | 0.01
5.8963 | 8.2104 | 2.1549 | 1.6026 | 4.3948 | 3.5717 | 7.6459 | 5.5888 | 14.1067 | 15.7093 | 23.6757 | 29.2644 | 5.8963 | 8.2104 | 2.1549 | 1.6026 | 4.3948 | 3.5717 | 7.6559 | 5.5888 | 14.1067 | 15.7093 | 23.6757 | 29.2644 | 0.01
5.6478 | 8.0927 | 1.9907 | 1.89 | 2.1606 | 2.6199 | 7.2577 | 5.2165 | 13.7405 | 15.6305 | 22.8881 | 28.1046 | 5.6478 | 8.0927 | 1.9907 | 1.89 | 2.1606 | 2.6199 | 7.2677 | 5.2165 | 13.7405 | 15.6305 | 22.8981 | 28.1146 | 0.01
7.2282 | 8.2395 | 2.0691 | 2.2689 | 2.6905 | 2.6829 | 4.7528 | 6.0368 | 15.4677 | 17.7366 | 23.11 | 29.1468 | 7.2282 | 8.2395 | 2.0691 | 2.2689 | 2.6905 | 2.6829 | 4.7628 | 6.0368 | 15.4677 | 17.7366 | 23.11 | 29.1468 | 0.01
6.5351 | 8.463 | 1.4788 | 2.2844 | 2.0828 | 2.2498 | 6.4524 | 5.0942 | 14.9981 | 17.2825 | 23.7349 | 28.8291 | 6.5351 | 8.463 | 1.4788 | 2.2844 | 2.0828 | 2.2498 | 6.4624 | 5.0942 | 14.9981 | 17.2825 | 23.7449 | 28.8391 | 0.01
4.3736 | 7.3447 | 1.752 | 2.1615 | 1.3509 | 3.2823 | 6.739 | 4.4344 | 11.7183 | 13.8798 | 20.6187 | 25.0531 | 4.3736 | 7.3447 | 1.752 | 2.1615 | 1.3509 | 3.2823 | 6.749 | 4.4344 | 11.7183 | 13.8798 | 20.6287 | 25.0631 | 0.01
5.7664 | 9.1213 | 2.0289 | 2.0655 | 2.444 | 2.6102 | 9.5895 | 6.0975 | 14.8877 | 16.9532 | 26.5426 | 32.6401 | 5.7664 | 9.1213 | 2.0289 | 2.0655 | 2.444 | 2.6102 | 9.5995 | 6.0975 | 14.8877 | 16.9532 | 26.5526 | 32.6501 | 0.01
5.2368 | 11.9598 | 1.8686 | 1.6556 | 3.0329 | 2.576 | 8.8494 | 7.2981 | 17.1966 | 18.8522 | 27.7016 | 34.9997 | 5.2368 | 11.9598 | 1.8686 | 1.6556 | 3.0329 | 2.576 | 8.8594 | 7.2981 | 17.1966 | 18.8522 | 27.7116 | 35.0097 | 0.01
5.8233 | 7.1728 | 2.0233 | 1.8494 | 1.2281 | 3.4794 | 8.1719 | 4.4085 | 12.9961 | 14.8455 | 23.0174 | 27.4259 | 5.8233 | 7.1728 | 2.0233 | 1.8494 | 1.2281 | 3.4794 | 8.1819 | 4.4085 | 12.9961 | 14.8455 | 23.0274 | 27.4359 | 0.01
6.293 | 8.7395 | 1.9652 | 2.2617 | 2.4664 | 2.6252 | 8.4431 | 3.5687 | 15.0325 | 17.2943 | 25.7374 | 29.3061 | 6.293 | 8.7395 | 1.9652 | 2.2617 | 2.4664 | 2.6252 | 8.4531 | 3.5687 | 15.0325 | 17.2943 | 25.7474 | 29.3161 | 0.01
5.9928 | 9.1575 | 1.8749 | 1.8623 | 2.3039 | 2.3943 | 7.4493 | 3.4841 | 15.1504 | 17.0126 | 24.4619 | 27.946 | 5.9928 | 9.1575 | 1.8749 | 1.8623 | 2.3039 | 2.3943 | 7.4593 | 3.4841 | 15.1504 | 17.0126 | 24.4719 | 27.956 | 0.01
6.8091 | 6.2315 | 2.0095 | 2.2028 | 1.4867 | 3.9197 | 7.5562 | 6.1335 | 13.0406 | 15.2434 | 22.7996 | 28.9332 | 6.8091 | 6.2315 | 2.0095 | 2.2028 | 1.4867 | 3.9197 | 7.5662 | 6.1335 | 13.0406 | 15.2434 | 22.8096 | 28.9432 | 0.01
6.2628 | 7.1063 | 1.9065 | 2.724 | 3.3411 | 2.9356 | 6.4484 | 4.7534 | 13.3691 | 16.0931 | 22.5415 | 27.295 | 6.2628 | 7.1063 | 1.9065 | 2.724 | 3.3411 | 2.9356 | 6.4584 | 4.7534 | 13.3691 | 16.0931 | 22.5515 | 27.305 | 0.01
5.6885 | 7.2455 | 1.8551 | 2.3603 | 2.401 | 2.3896 | 7.0318 | 4.6963 | 12.934 | 15.2943 | 22.3261 | 27.0224 | 5.6885 | 7.2455 | 1.8551 | 2.3603 | 2.401 | 2.3896 | 7.0418 | 4.6963 | 12.934 | 15.2943 | 22.3361 | 27.0324 | 0.01
5.861 | 9.0397 | 1.6472 | 1.8299 | 2.9158 | 2.6063 | 7.756 | 5.159 | 14.9007 | 16.7306 | 24.4866 | 29.6456 | 5.861 | 9.0397 | 1.6472 | 1.8299 | 2.9158 | 2.6063 | 7.766 | 5.159 | 14.9007 | 16.7306 | 24.4966 | 29.6556 | 0.01
5.8548 | 7.9553 | 2.4039 | 2.0354 | 3.2123 | 4.2256 | 5.7853 | 4.0771 | 13.8101 | 15.8454 | 23.2834 | 27.3605 | 5.8548 | 7.9553 | 2.4039 | 2.0354 | 3.2123 | 4.2256 | 5.7953 | 4.0771 | 13.8101 | 15.8454 | 23.2834 | 27.3605 | 0.01
7.3219 | 6.0143 | 2.0586 | 2.2247 | 3.0902 | 2.8558 | 10.1878 | 3.3578 | 13.3362 | 15.5609 | 25.7487 | 29.1065 | 7.3219 | 6.0143 | 2.0586 | 2.2247 | 3.0902 | 2.8558 | 10.1978 | 3.3578 | 13.3362 | 15.5609 | 25.7587 | 29.1165 | 0.01
5.9699 | 9.2029 | 1.8947 | 1.8993 | 1.7911 | 3.5083 | 7.3809 | 5.4341 | 15.1728 | 17.0722 | 24.4531 | 29.8872 | 5.9699 | 9.2029 | 1.8947 | 1.8993 | 1.7911 | 3.5083 | 7.3909 | 5.4341 | 15.1728 | 17.0722 | 24.4631 | 29.8972 | 0.01
6.9058 | 5.9496 | 1.7202 | 1.8778 | 3.1013 | 3.3229 | 7.8188 | 5.8228 | 12.8555 | 14.7333 | 22.5521 | 28.3749 | 6.9058 | 5.9496 | 1.7202 | 1.8778 | 3.1013 | 3.3229 | 7.8288 | 5.8228 | 12.8555 | 14.7333 | 22.5621 | 28.3849 | 0.01
5.6888 | 7.5466 | 2.2343 | 2.3809 | 4.3165 | 3.7013 | 7.7034 | 6.5024 | 13.2354 | 15.6163 | 23.6341 | 30.1365 | 5.6888 | 7.5466 | 2.2343 | 2.3809 | 4.3165 | 3.7013 | 7.7134 | 6.5024 | 13.2354 | 15.6163 | 23.6341 | 30.1365 | 0.01
6.7398 | 7.1955 | 2.0621 | 1.459 | 5.6178 | 3.352 | 8.6859 | 3.3847 | 13.9353 | 15.3943 | 24.3641 | 27.7489 | 6.7398 | 7.1955 | 2.0621 | 1.459 | 5.6178 | 3.352 | 8.6959 | 3.3847 | 13.9353 | 15.3943 | 24.3641 | 27.7489 | 0.01
6.7526 | 5.3484 | 2.1525 | 1.1859 | 2.4412 | 3.0823 | 7.0112 | 8.1008 | 12.101 | 13.2869 | 20.2981 | 28.3989 | 6.7526 | 5.3484 | 2.1525 | 1.1859 | 2.4412 | 3.0823 | 7.0212 | 8.1008 | 12.101 | 13.2869 | 20.3081 | 28.4089 | 0.01
6.0413 | 5.9771 | 1.8791 | 1.5394 | 4.1015 | 2.2574 | 9.1715 | 4.2991 | 12.0184 | 13.5578 | 22.7293 | 27.0284 | 6.0413 | 5.9771 | 1.8791 | 1.5394 | 4.1015 | 2.2574 | 9.1815 | 4.2991 | 12.0184 | 13.5578 | 22.7393 | 27.0384 | 0.01
5.7237 | 7.8898 | 1.7047 | 1.7304 | 4.0706 | 2.8162 | 6.6571 | 5.0257 | 13.6135 | 15.344 | 22.2307 | 27.2563 | 5.7237 | 7.8898 | 1.7047 | 1.7304 | 4.0706 | 2.8162 | 6.6671 | 5.0257 | 13.6135 | 15.344 | 22.2307 | 27.2563 | 0.01
5.981 | 9.9093 | 2.186 | 2.3319 | 4.6869 | 4.5637 | 4.1324 | 6.0381 | 15.8903 | 18.2222 | 27.4728 | 33.511 | 5.981 | 9.9093 | 2.186 | 2.3319 | 4.6869 | 4.5637 | 4.1424 | 6.0381 | 15.8903 | 18.2222 | 27.4728 | 33.511 | 0.01
7.0721 | 7.0595 | 2.0681 | 1.8805 | 2.1813 | 3.2758 | 6.9392 | 5.8573 | 14.1315 | 16.012 | 22.9512 | 28.8084 | 7.0721 | 7.0595 | 2.0681 | 1.8805 | 2.1813 | 3.2758 | 6.9492 | 5.8573 | 14.1315 | 16.012 | 22.9612 | 28.8184 | 0.01
5.622 | 8.0528 | 2.3749 | 2.2994 | 0.90458 | 2.1556 | 5.3234 | 4.7952 | 13.6747 | 15.9741 | 21.2975 | 26.0927 | 5.622 | 8.0528 | 2.3749 | 2.2994 | 0.90458 | 2.1556 | 5.3334 | 4.7952 | 13.6747 | 15.9741 | 21.3075 | 26.1027 | 0.01
6.4261 | 8.8126 | 1.8543 | 2.0311 | 3.8388 | 3.864 | 8.2339 | 2.9967 | 15.2387 | 17.2697 | 25.5037 | 28.5004 | 6.4261 | 8.8126 | 1.8543 | 2.0311 | 3.8388 | 3.864 | 8.2439 | 2.9967 | 15.2387 | 17.2697 | 25.5137 | 28.5104 | 0.01
6.5307 | 7.7389 | 1.9628 | 1.9304 | 3.1107 | 3.063 | 7.0918 | 3.5573 | 14.2697 | 16.2001 | 23.2919 | 26.8491 | 6.5307 | 7.7389 | 1.9628 | 1.9304 | 3.1107 | 3.063 | 7.1018 | 3.5573 | 14.2697 | 16.2001 | 23.3019 | 26.8591 | 0.01
5.6948 | 7.1674 | 2.4565 | 2.2635 | 2.5802 | 3.4979 | 4.7303 | 4.4205 | 12.8622 | 15.1257 | 21.2038 | 25.6244 | 5.6948 | 7.1674 | 2.4565 | 2.2635 | 2.5802 | 3.4979 | 4.7403 | 4.4205 | 12.8622 | 15.1257 | 21.2038 | 25.6244 | 0.01
6.1224 | 9.0121 | 1.7403 | 1.9023 | 2.9914 | 3.0375 | 5.0785 | 5.2745 | 15.1346 | 17.0369 | 23.0658 | 28.3403 | 6.1224 | 9.0121 | 1.7403 | 1.9023 | 2.9914 | 3.0375 | 5.0885 | 5.2745 | 15.1346 | 17.0369 | 23.0658 | 28.3403 | 0.01
6.7927 | 7.5568 | 1.8479 | 2.0388 | 1.1754 | 3.919 | 10.1483 | 4.6858 | 14.3495 | 16.3883 | 26.5366 | 31.2225 | 6.7927 | 7.5568 | 1.8479 | 2.0388 | 1.1754 | 3.919 | 10.1583 | 4.6858 | 14.3495 | 16.3883 | 26.5466 | 31.2325 | 0.01
6.3303 | 9.3203 | 1.9861 | 1.9305 | 5.0354 | 2.4559 | -7.3051 | 5.9784 | 15.6506 | 17.5811 | 25.0724 | 31.0509 | 6.3303 | 9.3203 | 1.9861 | 1.9305 | 5.0354 | 2.4559 | -7.2951 | 5.9784 | 15.6506 | 17.5811 | 25.0724 | 31.0509 | 0.01
6.413 | 6.8383 | 1.9471 | 1.7251 | 2.0154 | 3.2853 | 7.3079 | 5.0368 | 13.2513 | 14.9765 | 22.2844 | 27.3211 | 6.413 | 6.8383 | 1.9471 | 1.7251 | 2.0154 | 3.2853 | 7.3179 | 5.0368 | 13.2513 | 14.9765 | 22.2944 | 27.3311 | 0.01
5.8237 | 9.7657 | 1.9763 | 2.2163 | 5.1484 | 3.8884 | 7.198 | 3.3032 | 15.5894 | 17.8057 | 26.8426 | 30.1458 | 5.8237 | 9.7657 | 1.9763 | 2.2163 | 5.1484 | 3.8884 | 7.208 | 3.3032 | 15.5894 | 17.8057 | 26.8426 | 30.1458 | 0.01
5.7332 | 8.8832 | 2.159 | 1.4666 | 3.3107 | 2.1105 | 5.3228 | 4.5784 | 14.6164 | 16.083 | 21.5041 | 26.0825 | 5.7332 | 8.8832 | 2.159 | 1.4666 | 3.3107 | 2.1105 | 5.3328 | 4.5784 | 14.6164 | 16.083 | 21.5041 | 26.0825 | 0.01
5.223 | 9.4937 | 2.1729 | 1.9727 | 2.3094 | 2.2833 | 7.0034 | 5.2466 | 14.7167 | 16.6894 | 23.6927 | 28.9393 | 5.223 | 9.4937 | 2.1729 | 1.9727 | 2.3094 | 2.2833 | 7.0134 | 5.2466 | 14.7167 | 16.6894 | 23.7027 | 28.9493 | 0.01
5.4454 | 11.0607 | 2.0375 | 2.5492 | 3.6165 | 3.426 | 8.3531 | 3.7567 | 16.506 | 19.0553 | 27.4084 | 31.1651 | 5.4454 | 11.0607 | 2.0375 | 2.5492 | 3.6165 | 3.426 | 8.3631 | 3.7567 | 16.506 | 19.0553 | 27.4184 | 31.1751 | 0.01
6.3156 | 7.918 | 2.0608 | 1.5452 | 3.8914 | 2.9212 | 8.6874 | 7.0789 | 14.2335 | 15.7787 | 24.4661 | 31.5451 | 6.3156 | 7.918 | 2.0608 | 1.5452 | 3.8914 | 2.9212 | 8.6974 | 7.0789 | 14.2335 | 15.7787 | 24.4761 | 31.5551 | 0.01
6.0928 | 6.7092 | 1.9738 | 2.0792 | 3.3098 | 2.1703 | 6.6322 | 6.7147 | 12.802 | 14.8812 | 21.5134 | 28.2282 | 6.0928 | 6.7092 | 1.9738 | 2.0792 | 3.3098 | 2.1703 | 6.6422 | 6.7147 | 12.802 | 14.8812 | 21.5234 | 28.2382 | 0.01
4.9136 | 7.2695 | 2.0189 | 1.3937 | 2.9853 | 3.8041 | 5.4134 | 5.1781 | 12.1831 | 13.5768 | 20.3662 | 25.5443 | 4.9136 | 7.2695 | 2.0189 | 1.3937 | 2.9853 | 3.8041 | 5.4234 | 5.1781 | 12.1831 | 13.5768 | 20.3662 | 25.5443 | 0.01
6.8023 | 6.037 | 2.074 | 2.0352 | 1.7195 | 2.6336 | 5.2963 | 4.8739 | 12.8393 | 14.8746 | 20.1709 | 25.0448 | 6.8023 | 6.037 | 2.074 | 2.0352 | 1.7195 | 2.6336 | 5.3063 | 4.8739 | 12.8393 | 14.8746 | 20.1809 | 25.0548 | 0.01
6.012 | 8.4282 | 1.9462 | 1.9888 | 3.7486 | 1.9865 | 6.4029 | 5.4619 | 14.4402 | 16.4291 | 22.832 | 28.2939 | 6.012 | 8.4282 | 1.9462 | 1.9888 | 3.7486 | 1.9865 | 6.4129 | 5.4619 | 14.4402 | 16.4291 | 22.842 | 28.3039 | 0.01
5.5508 | 8.3912 | 2.203 | 1.593 | 2.467 | 3.0206 | 6.2898 | 7.739 | 13.942 | 15.5351 | 21.8249 | 29.5638 | 5.5508 | 8.3912 | 2.203 | 1.593 | 2.467 | 3.0206 | 6.2998 | 7.739 | 13.942 | 15.5351 | 21.8349 | 29.5738 | 0.01
5.9817 | 10.7196 | 1.8037 | 2.1174 | 3.1322 | 2.3425 | 7.6139 | 7.6124 | 16.7013 | 18.8187 | 26.4326 | 34.045 | 5.9817 | 10.7196 | 1.8037 | 2.1174 | 3.1322 | 2.3425 | 7.6239 | 7.6124 | 16.7013 | 18.8187 | 26.4426 | 34.055 | 0.01
5.0879 | 7.2662 | 1.94 | 1.9768 | 2.8459 | 2.9535 | 9.6751 | 3.9476 | 12.3542 | 14.3309 | 24.006 | 27.9536 | 5.0879 | 7.2662 | 1.94 | 1.9768 | 2.8459 | 2.9535 | 9.6851 | 3.9476 | 12.3542 | 14.3309 | 24.016 | 27.9636 | 0.01
6.844 | 8.0763 | 1.7866 | 1.625 | 4.3598 | 3.0301 | 6.0462 | 5.9683 | 14.9202 | 16.5452 | 23.9351 | 29.9035 | 6.844 | 8.0763 | 1.7866 | 1.625 | 4.3598 | 3.0301 | 6.0562 | 5.9683 | 14.9202 | 16.5452 | 23.9351 | 29.9035 | 0.01
5.27 | 9.3692 | 1.8899 | 2.055 | 2.5255 | 3.4359 | 7.6042 | 4.8508 | 14.6391 | 16.6941 | 24.2983 | 29.1491 | 5.27 | 9.3692 | 1.8899 | 2.055 | 2.5255 | 3.4359 | 7.6142 | 4.8508 | 14.6391 | 16.6941 | 24.3083 | 29.1591 | 0.01
5.5222 | 8.9 | 1.4918 | 2.0973 | 2.8579 | 3.3103 | 6.2695 | 4.2805 | 14.4222 | 16.5195 | 22.7889 | 27.0694 | 5.5222 | 8.9 | 1.4918 | 2.0973 | 2.8579 | 3.3103 | 6.2795 | 4.2805 | 14.4222 | 16.5195 | 22.7989 | 27.0794 | 0.01
6.0272 | 9.158 | 2.0173 | 2.2995 | 1.6069 | 3.4916 | 5.5802 | 4.4809 | 15.1852 | 17.4846 | 23.0649 | 27.5457 | 6.0272 | 9.158 | 2.0173 | 2.2995 | 1.6069 | 3.4916 | 5.5902 | 4.4809 | 15.1852 | 17.4846 | 23.0749 | 27.5557 | 0.01
5.7989 | 8.0722 | 2.4406 | 1.874 | 3.037 | 3.2084 | 7.277 | 4.1281 | 13.8711 | 15.7451 | 23.0221 | 27.1502 | 5.7989 | 8.0722 | 2.4406 | 1.874 | 3.037 | 3.2084 | 7.287 | 4.1281 | 13.8711 | 15.7451 | 23.0321 | 27.1602 | 0.01
5.5844 | 8.8186 | 2.205 | 1.6595 | 2.9602 | 3.541 | 7.1619 | 6.0375 | 14.403 | 16.0626 | 23.2245 | 29.262 | 5.5844 | 8.8186 | 2.205 | 1.6595 | 2.9602 | 3.541 | 7.1719 | 6.0375 | 14.403 | 16.0626 | 23.2345 | 29.272 | 0.01
6.2425 | 8.3952 | 1.7646 | 1.8736 | 2.5751 | 2.7791 | 6.1796 | 4.1929 | 14.6377 | 16.5113 | 22.6909 | 26.8839 | 6.2425 | 8.3952 | 1.7646 | 1.8736 | 2.5751 | 2.7791 | 6.1896 | 4.1929 | 14.6377 | 16.5113 | 22.7009 | 26.8939 | 0.01
6.5866 | 7.1947 | 2.1164 | 1.7497 | 2.508 | 2.8219 | 4.2175 | 7.1324 | 13.7813 | 15.531 | 20.8609 | 27.9933 | 6.5866 | 7.1947 | 2.1164 | 1.7497 | 2.508 | 2.8219 | 4.2275 | 7.1324 | 13.7813 | 15.531 | 20.8609 | 27.9933 | 0.01
6.9557 | 7.3366 | 1.8436 | 2.4333 | 4.1239 | 2.4637 | 6.8637 | 5.3102 | 14.2922 | 16.7255 | 23.5892 | 28.8993 | 6.9557 | 7.3366 | 1.8436 | 2.4333 | 4.1239 | 2.4637 | 6.8737 | 5.3102 | 14.2922 | 16.7255 | 23.5992 | 28.9093 | 0.01
5.9924 | 6.334 | 2.0972 | 2.4204 | 0.706 | 2.3975 | 8.7414 | 3.6823 | 12.3264 | 14.7468 | 23.4882 | 27.1705 | 5.9924 | 6.334 | 2.0972 | 2.4204 | 0.706 | 2.3975 | 8.7514 | 3.6823 | 12.3264 | 14.7468 | 23.4982 | 27.1805 | 0.01
5.6485 | 9.9844 | 1.9109 | 2.0582 | 3.9165 | 3.0269 | 4.0473 | 4.5144 | 15.6329 | 17.6911 | 24.6345 | 29.149 | 5.6485 | 9.9844 | 1.9109 | 2.0582 | 3.9165 | 3.0269 | 4.0573 | 4.5144 | 15.6329 | 17.6911 | 24.6345 | 29.149 | 0.01
6.8764 | 7.7992 | 2.3267 | 2.2434 | 1.9525 | 3.671 | 6.5202 | 4.3244 | 14.6756 | 16.919 | 23.4391 | 27.7636 | 6.8764 | 7.7992 | 2.3267 | 2.2434 | 1.9525 | 3.671 | 6.5302 | 4.3244 | 14.6756 | 16.919 | 23.4491 | 27.7736 | 0.01
6.0803 | 7.5537 | 2.2218 | 2.2297 | 1.1277 | 2.588 | 7.3192 | 4.3273 | 13.634 | 15.8637 | 23.1828 | 27.5102 | 6.0803 | 7.5537 | 2.2218 | 2.2297 | 1.1277 | 2.588 | 7.3292 | 4.3273 | 13.634 | 15.8637 | 23.1928 | 27.5202 | 0.01
6.3748 | 7.6026 | 1.6182 | 2.3168 | 4.2606 | 2.4003 | 8.0945 | 5.6757 | 13.9774 | 16.2941 | 24.3886 | 30.0643 | 6.3748 | 7.6026 | 1.6182 | 2.3168 | 4.2606 | 2.4003 | 8.1045 | 5.6757 | 13.9774 | 16.2941 | 24.3986 | 30.0743 | 0.01
5.5026 | 6.735 | 2.0198 | 1.7828 | 4.4553 | 3.4662 | 7.0308 | 6.3836 | 12.2376 | 14.0204 | 21.9419 | 28.3255 | 5.5026 | 6.735 | 2.0198 | 1.7828 | 4.4553 | 3.4662 | 7.0408 | 6.3836 | 12.2376 | 14.0204 | 21.9419 | 28.3255 | 0.01
6.3431 | 6.8191 | 1.8928 | 2.0851 | 4.4794 | 3.5813 | 7.9537 | 4.6896 | 13.1621 | 15.2473 | 23.3079 | 27.9975 | 6.3431 | 6.8191 | 1.8928 | 2.0851 | 4.4794 | 3.5813 | 7.9637 | 4.6896 | 13.1621 | 15.2473 | 23.3079 | 27.9975 | 0.01
4.9711 | 10.0608 | 2.1779 | 1.9182 | 2.1308 | 2.8665 | 5.8776 | 4.44 | 15.0318 | 16.95 | 22.8276 | 27.2676 | 4.9711 | 10.0608 | 2.1779 | 1.9182 | 2.1308 | 2.8665 | 5.8876 | 4.44 | 15.0318 | 16.95 | 22.8376 | 27.2776 | 0.01
5.1407 | 9.9847 | 1.9636 | 1.9394 | 2.7764 | 2.9777 | 5.2473 | 2.7882 | 15.1254 | 17.0648 | 22.8189 | 25.6072 | 5.1407 | 9.9847 | 1.9636 | 1.9394 | 2.7764 | 2.9777 | 5.2573 | 2.7882 | 15.1254 | 17.0648 | 22.8189 | 25.6072 | 0.01
6.1673 | 7.9542 | 1.4841 | 1.9295 | 3.7719 | 2.6881 | 5.5183 | 3.5347 | 14.1215 | 16.051 | 22.511 | 26.0457 | 6.1673 | 7.9542 | 1.4841 | 1.9295 | 3.7719 | 2.6881 | 5.5283 | 3.5347 | 14.1215 | 16.051 | 22.511 | 26.0457 | 0.01
6.1389 | 8.5505 | 2.1358 | 1.7472 | 4.9695 | 3.6564 | 9.2871 | 5.882 | 14.6894 | 16.4366 | 25.7237 | 31.6057 | 6.1389 | 8.5505 | 2.1358 | 1.7472 | 4.9695 | 3.6564 | 9.2971 | 5.882 | 14.6894 | 16.4366 | 25.7337 | 31.6157 | 0.01
7.0342 | 9.796 | 1.9245 | 1.717 | 4.0425 | 2.6687 | 5.9092 | 1.305 | 16.8301 | 18.5471 | 25.2583 | 26.5633 | 7.0342 | 9.796 | 1.9245 | 1.717 | 4.0425 | 2.6687 | 5.9192 | 1.305 | 16.8301 | 18.5471 | 25.2583 | 26.5633 | 0.01
5.5869 | 8.0124 | 2.1056 | 2.3272 | 2.2977 | 3.3881 | 4.5839 | 5.1048 | 13.5993 | 15.9265 | 21.6124 | 26.7172 | 5.5869 | 8.0124 | 2.1056 | 2.3272 | 2.2977 | 3.3881 | 4.5939 | 5.1048 | 13.5993 | 15.9265 | 21.6124 | 26.7172 | 0.01
6.4306 | 6.2885 | 2.0894 | 1.9872 | 2.4814 | 2.9799 | 5.8963 | 3.9931 | 12.7191 | 14.7063 | 20.6026 | 24.5957 | 6.4306 | 6.2885 | 2.0894 | 1.9872 | 2.4814 | 2.9799 | 5.9063 | 3.9931 | 12.7191 | 14.7063 | 20.6126 | 24.6057 | 0.01
6.9458 | 8.3558 | 2.1593 | 2.0059 | 1.5973 | 3.1031 | 9.7678 | 2.6658 | 15.3016 | 17.3075 | 27.0754 | 29.7412 | 6.9458 | 8.3558 | 2.1593 | 2.0059 | 1.5973 | 3.1031 | 9.7778 | 2.6658 | 15.3016 | 17.3075 | 27.0854 | 29.7512 | 0.01
5.1227 | 8.6409 | 2.0638 | 1.9308 | 2.7671 | 1.9254 | 9.0036 | 5.6571 | 13.7635 | 15.6943 | 24.6979 | 30.3549 | 5.1227 | 8.6409 | 2.0638 | 1.9308 | 2.7671 | 1.9254 | 9.0136 | 5.6571 | 13.7635 | 15.6943 | 24.7079 | 30.3649 | 0.01
6.1372 | 8.4993 | 1.874 | 1.901 | 2.4878 | 4.3777 | 6.0382 | 6.0511 | 14.6365 | 16.5374 | 23.4028 | 29.454 | 6.1372 | 8.4993 | 1.874 | 1.901 | 2.4878 | 4.3777 | 6.0482 | 6.0511 | 14.6365 | 16.5374 | 23.4028 | 29.454 | 0.01
5.2228 | 7.8052 | 1.8899 | 1.7654 | 4.1659 | 2.0949 | 6.1485 | 5.6294 | 13.028 | 14.7934 | 21.0541 | 26.6835 | 5.2228 | 7.8052 | 1.8899 | 1.7654 | 4.1659 | 2.0949 | 6.1585 | 5.6294 | 13.028 | 14.7934 | 21.0541 | 26.6835 | 0.01
6.059 | 8.6674 | 2.0859 | 2.2557 | 2.038 | 3.018 | 7.5693 | 2.7211 | 14.7264 | 16.9821 | 24.5514 | 27.2725 | 6.059 | 8.6674 | 2.0859 | 2.2557 | 2.038 | 3.018 | 7.5793 | 2.7211 | 14.7264 | 16.9821 | 24.5614 | 27.2825 | 0.01
5.8005 | 8.3484 | 2.1752 | 1.7522 | 2.6489 | 2.5186 | 7.9263 | 5.9465 | 14.1488 | 15.9011 | 23.8274 | 29.7739 | 5.8005 | 8.3484 | 2.1752 | 1.7522 | 2.6489 | 2.5186 | 7.9363 | 5.9465 | 14.1488 | 15.9011 | 23.8374 | 29.7839 | 0.01
6.4614 | 8.5406 | 1.8094 | 1.9385 | 3.7999 | 2.6888 | 4.0615 | 5.1768 | 15.002 | 16.9405 | 23.4292 | 28.606 | 6.4614 | 8.5406 | 1.8094 | 1.9385 | 3.7999 | 2.6888 | 4.0715 | 5.1768 | 15.002 | 16.9405 | 23.4292 | 28.606 | 0.01
5.5917 | 6.908 | 1.9618 | 1.8694 | 2.6832 | 2.0527 | 8.4346 | 6.0292 | 12.4997 | 14.3691 | 22.8037 | 28.8329 | 5.5917 | 6.908 | 1.9618 | 1.8694 | 2.6832 | 2.0527 | 8.4446 | 6.0292 | 12.4997 | 14.3691 | 22.8137 | 28.8429 | 0.01
5.0139 | 9.0503 | 1.6182 | 2.6924 | 4.0182 | 2.8926 | 8.8931 | 5.9557 | 14.0642 | 16.7566 | 25.6497 | 31.6054 | 5.0139 | 9.0503 | 1.6182 | 2.6924 | 4.0182 | 2.8926 | 8.9031 | 5.9557 | 14.0642 | 16.7566 | 25.6597 | 31.6154 | 0.01
6.1757 | 9.8315 | 1.9979 | 1.6681 | 3.726 | 3.3878 | 5.3077 | 6.6408 | 16.0072 | 17.6754 | 24.7891 | 31.43 | 6.1757 | 9.8315 | 1.9979 | 1.6681 | 3.726 | 3.3878 | 5.3177 | 6.6408 | 16.0072 | 17.6754 | 24.7891 | 31.43 | 0.01
6.3309 | 8.9237 | 2.0639 | 2.4224 | 2.8173 | 1.4483 | 2.6862 | 3.4637 | 15.2546 | 17.677 | 21.9427 | 25.4063 | 6.3309 | 8.9237 | 2.0639 | 2.4224 | 2.8173 | 1.4483 | 2.6962 | 3.4637 | 15.2546 | 17.677 | 21.9427 | 25.4063 | 0.01
5.9264 | 7.1327 | 1.618 | 2.1347 | 2.8357 | 3.2603 | 7.2858 | 7.1373 | 13.059 | 15.1937 | 22.4795 | 29.6169 | 5.9264 | 7.1327 | 1.618 | 2.1347 | 2.8357 | 3.2603 | 7.2958 | 7.1373 | 13.059 | 15.1937 | 22.4895 | 29.6269 | 0.01
5.9649 | 6.4703 | 2.1549 | 1.809 | 2.0076 | 3.2355 | 4.7339 | 4.1784 | 12.4352 | 14.2443 | 19.4873 | 23.6657 | 5.9649 | 6.4703 | 2.1549 | 1.809 | 2.0076 | 3.2355 | 4.7439 | 4.1784 | 12.4352 | 14.2443 | 19.4873 | 23.6657 | 0.01
5.4422 | 9.3773 | 1.7776 | 2.4011 | 1.5567 | 2.6235 | 5.2102 | 6.4324 | 14.8195 | 17.2206 | 22.4309 | 28.8633 | 5.4422 | 9.3773 | 1.7776 | 2.4011 | 1.5567 | 2.6235 | 5.2202 | 6.4324 | 14.8195 | 17.2206 | 22.4409 | 28.8733 | 0.01
6.2517 | 5.9657 | 1.8738 | 1.8896 | 3.1466 | 3.4289 | 6.796 | 5.6123 | 12.2174 | 14.107 | 20.903 | 26.5153 | 6.2517 | 5.9657 | 1.8738 | 1.8896 | 3.1466 | 3.4289 | 6.806 | 5.6123 | 12.2174 | 14.107 | 20.913 | 26.5253 | 0.01
5.511 | 7.8265 | 2.1347 | 1.9687 | 2.8271 | 3.2396 | 6.5297 | 2.5811 | 13.3375 | 15.3063 | 21.836 | 24.417 | 5.511 | 7.8265 | 2.1347 | 1.9687 | 2.8271 | 3.2396 | 6.5397 | 2.5811 | 13.3375 | 15.3063 | 21.846 | 24.427 | 0.01
6.4701 | 6.3079 | 2.1902 | 1.9968 | 2.5717 | 2.3845 | 5.8676 | 4.93 | 12.778 | 14.7748 | 20.6423 | 25.5723 | 6.4701 | 6.3079 | 2.1902 | 1.9968 | 2.5717 | 2.3845 | 5.8776 | 4.93 | 12.778 | 14.7748 | 20.6523 | 25.5823 | 0.01
5.6088 | 8.9857 | 2.3678 | 2.2914 | 1.5427 | 3.2266 | 4.6278 | 3.7621 | 14.5945 | 16.8859 | 21.6551 | 25.4172 | 5.6088 | 8.9857 | 2.3678 | 2.2914 | 1.5427 | 3.2266 | 4.6378 | 3.7621 | 14.5945 | 16.8859 | 21.6551 | 25.4172 | 0.01
5.56 | 6.6188 | 2.3664 | 2.0211 | 5.0048 | 2.4263 | 4.2163 | 4.9274 | 12.1788 | 14.1999 | 21.631 | 26.5584 | 5.56 | 6.6188 | 2.3664 | 2.0211 | 5.0048 | 2.4263 | 4.2263 | 4.9274 | 12.1788 | 14.1999 | 21.631 | 26.5584 | 0.01
6.1857 | 7.8356 | 2.0518 | 2.1059 | 0.97363 | 2.4612 | 6.6178 | 5.1962 | 14.0213 | 16.1272 | 22.7449 | 27.9411 | 6.1857 | 7.8356 | 2.0518 | 2.1059 | 0.97363 | 2.4612 | 6.6278 | 5.1962 | 14.0213 | 16.1272 | 22.7549 | 27.9511 | 0.01
6.0117 | 9.798 | 2.0911 | 1.8214 | 3.6976 | 2.1941 | 8.3275 | 4.3259 | 15.8098 | 17.6312 | 25.9587 | 30.2846 | 6.0117 | 9.798 | 2.0911 | 1.8214 | 3.6976 | 2.1941 | 8.3375 | 4.3259 | 15.8098 | 17.6312 | 25.9687 | 30.2946 | 0.01
5.4835 | 5.3208 | 1.9322 | 1.8739 | 0.82789 | 3.9009 | 6.4289 | 3.5573 | 10.8043 | 12.6782 | 19.1071 | 22.6643 | 5.4835 | 5.3208 | 1.9322 | 1.8739 | 0.82789 | 3.9009 | 6.4389 | 3.5573 | 10.8043 | 12.6782 | 19.1171 | 22.6743 | 0.01
5.0524 | 8.8022 | 1.9982 | 1.6036 | 1.9297 | 4.6228 | 9.2068 | 4.2369 | 13.8546 | 15.4582 | 24.665 | 28.9019 | 5.0524 | 8.8022 | 1.9982 | 1.6036 | 1.9297 | 4.6228 | 9.2168 | 4.2369 | 13.8546 | 15.4582 | 24.675 | 28.9119 | 0.01
5.7177 | 7.7906 | 1.8119 | 2.4044 | 3.4403 | 3.3333 | 7.0707 | 5.2725 | 13.5083 | 15.9127 | 22.9834 | 28.2559 | 5.7177 | 7.7906 | 1.8119 | 2.4044 | 3.4403 | 3.3333 | 7.0807 | 5.2725 | 13.5083 | 15.9127 | 22.9934 | 28.2659 | 0.01
6.199 | 8.3202 | 1.9582 | 2.6232 | 1.0283 | 2.6781 | 7.1599 | 6.056 | 14.5192 | 17.1424 | 24.3022 | 30.3582 | 6.199 | 8.3202 | 1.9582 | 2.6232 | 1.0283 | 2.6781 | 7.1699 | 6.056 | 14.5192 | 17.1424 | 24.3122 | 30.3682 | 0.01
7.1811 | 7.687 | 2.3416 | 1.8857 | 3.374 | 3.062 | 6.2899 | 4.9825 | 14.8681 | 16.7538 | 23.1898 | 28.1723 | 7.1811 | 7.687 | 2.3416 | 1.8857 | 3.374 | 3.062 | 6.2999 | 4.9825 | 14.8681 | 16.7538 | 23.1898 | 28.1723 | 0.01
6.7696 | 7.1553 | 2.131 | 2.0329 | 3.6338 | 3.4124 | 6.1495 | 2.926 | 13.9249 | 15.9578 | 23.0041 | 25.93 | 6.7696 | 7.1553 | 2.131 | 2.0329 | 3.6338 | 3.4124 | 6.1595 | 2.926 | 13.9249 | 15.9578 | 23.0041 | 25.93 | 0.01
5.7733 | 9.8401 | 1.6081 | 1.9419 | 1.5616 | 3.8286 | 7.0036 | 3.9644 | 15.6135 | 17.5553 | 24.5589 | 28.5233 | 5.7733 | 9.8401 | 1.6081 | 1.9419 | 1.5616 | 3.8286 | 7.0136 | 3.9644 | 15.6135 | 17.5553 | 24.5689 | 28.5333 | 0.01
5.9731 | 8.3682 | 1.8155 | 2.272 | 2.4512 | 3.1252 | 2.7596 | 3.2921 | 14.3413 | 16.6133 | 22.1897 | 25.4818 | 5.9731 | 8.3682 | 1.8155 | 2.272 | 2.4512 | 3.1252 | 2.7696 | 3.2921 | 14.3413 | 16.6133 | 22.1897 | 25.4818 | 0.01
6.1994 | 10.1607 | 1.97 | 2.2931 | 2.328 | 4.0242 | 4.5182 | 5.7372 | 16.3601 | 18.6532 | 25.0054 | 30.7425 | 6.1994 | 10.1607 | 1.97 | 2.2931 | 2.328 | 4.0242 | 4.5282 | 5.7372 | 16.3601 | 18.6532 | 25.0054 | 30.7425 | 0.01
5.1778 | 9.3077 | 2.2087 | 2.2279 | 1.9239 | 3.3571 | 8.1058 | 4.6866 | 14.4855 | 16.7134 | 24.8192 | 29.5058 | 5.1778 | 9.3077 | 2.2087 | 2.2279 | 1.9239 | 3.3571 | 8.1158 | 4.6866 | 14.4855 | 16.7134 | 24.8292 | 29.5158 | 0.01
9.2187 | 8.0269 | 1.967 | 2.1349 | 4.2118 | 2.5737 | 10.3559 | 4.7449 | 17.2456 | 19.3804 | 29.7363 | 34.4812 | 9.2187 | 8.0269 | 1.967 | 2.1349 | 4.2118 | 2.5737 | 10.3659 | 4.7449 | 17.2456 | 19.3804 | 29.7463 | 34.4912 | 0.01
7.256 | 8.9817 | 2.001 | 1.7653 | 3.6369 | 2.6629 | 8.3433 | 3.5672 | 16.2377 | 18.003 | 26.3464 | 29.9136 | 7.256 | 8.9817 | 2.001 | 1.7653 | 3.6369 | 2.6629 | 8.3533 | 3.5672 | 16.2377 | 18.003 | 26.3564 | 29.9236 | 0.01
6.249 | 9.3413 | 2.0282 | 1.7522 | 2.7448 | 3.3502 | 7.1262 | 6.0448 | 15.5902 | 17.3425 | 24.4687 | 30.5135 | 6.249 | 9.3413 | 2.0282 | 1.7522 | 2.7448 | 3.3502 | 7.1362 | 6.0448 | 15.5902 | 17.3425 | 24.4787 | 30.5235 | 0.01
6.6045 | 8.0468 | 1.5334 | 2.4151 | 3.9494 | 2.2966 | 6.3897 | 5.5004 | 14.6513 | 17.0664 | 23.4561 | 28.9565 | 6.6045 | 8.0468 | 1.5334 | 2.4151 | 3.9494 | 2.2966 | 6.3997 | 5.5004 | 14.6513 | 17.0664 | 23.4661 | 28.9665 | 0.01
6.6431 | 9.2305 | 1.7858 | 2.1318 | 3.35 | 1.703 | 8.3633 | 6.4696 | 15.8736 | 18.0054 | 26.3687 | 32.8383 | 6.6431 | 9.2305 | 1.7858 | 2.1318 | 3.35 | 1.703 | 8.3733 | 6.4696 | 15.8736 | 18.0054 | 26.3787 | 32.8483 | 0.01
7.1079 | 8.1306 | 2.1293 | 2.0002 | 2.7744 | 4.0493 | 8.2362 | 5.3411 | 15.2385 | 17.2388 | 25.475 | 30.8161 | 7.1079 | 8.1306 | 2.1293 | 2.0002 | 2.7744 | 4.0493 | 8.2462 | 5.3411 | 15.2385 | 17.2388 | 25.485 | 30.8261 | 0.01
5.3981 | 6.88 | 1.6214 | 2.5313 | 3.079 | 4.4824 | 8.3492 | 4.7205 | 12.278 | 14.8094 | 23.1585 | 27.879 | 5.3981 | 6.88 | 1.6214 | 2.5313 | 3.079 | 4.4824 | 8.3592 | 4.7205 | 12.278 | 14.8094 | 23.1685 | 27.889 | 0.01
6.1289 | 6.4161 | 1.8278 | 2.0393 | 2.2675 | 3.048 | 8.9054 | 3.3765 | 12.545 | 14.5843 | 23.4897 | 26.8663 | 6.1289 | 6.4161 | 1.8278 | 2.0393 | 2.2675 | 3.048 | 8.9154 | 3.3765 | 12.545 | 14.5843 | 23.4997 | 26.8763 | 0.01
5.3697 | 7.8849 | 1.868 | 2.3197 | 2.3937 | 3.4631 | 7.8988 | 4.9194 | 13.2546 | 15.5744 | 23.4732 | 28.3926 | 5.3697 | 7.8849 | 1.868 | 2.3197 | 2.3937 | 3.4631 | 7.9088 | 4.9194 | 13.2546 | 15.5744 | 23.4832 | 28.4026 | 0.01
6.8428 | 7.5172 | 2.3702 | 1.7653 | 2.2868 | 3.1547 | 11.5024 | 5.4618 | 14.36 | 16.1253 | 27.6278 | 33.0896 | 6.8428 | 7.5172 | 2.3702 | 1.7653 | 2.2868 | 3.1547 | 11.5124 | 5.4618 | 14.36 | 16.1253 | 27.6378 | 33.0996 | 0.01
6.4279 | 8.1445 | 2.3539 | 1.8505 | 1.3376 | 2.9486 | 6.9182 | 5.9981 | 14.5725 | 16.423 | 23.3412 | 29.3393 | 6.4279 | 8.1445 | 2.3539 | 1.8505 | 1.3376 | 2.9486 | 6.9282 | 5.9981 | 14.5725 | 16.423 | 23.3512 | 29.3493 | 0.01
6.2159 | 8.9369 | 2.0705 | 1.4218 | 1.6938 | 2.6921 | 9.3879 | 6.0237 | 15.1528 | 16.5747 | 25.9626 | 31.9863 | 6.2159 | 8.9369 | 2.0705 | 1.4218 | 1.6938 | 2.6921 | 9.3979 | 6.0237 | 15.1528 | 16.5747 | 25.9726 | 31.9963 | 0.01
6.1835 | 6.5701 | 2.3586 | 2.3126 | 2.2075 | 3.386 | 9.1588 | 5.0026 | 12.7536 | 15.0662 | 24.225 | 29.2276 | 6.1835 | 6.5701 | 2.3586 | 2.3126 | 2.2075 | 3.386 | 9.1688 | 5.0026 | 12.7536 | 15.0662 | 24.235 | 29.2376 | 0.01
6.6172 | 7.1001 | 1.9732 | 1.5421 | 2.9659 | 2.7788 | 4.7528 | 5.2458 | 13.7173 | 15.2593 | 21.0041 | 26.2498 | 6.6172 | 7.1001 | 1.9732 | 1.5421 | 2.9659 | 2.7788 | 4.7628 | 5.2458 | 13.7173 | 15.2593 | 21.0041 | 26.2498 | 0.01
5.3235 | 9.082 | 2.0234 | 1.3538 | 1.4331 | 3.8027 | 5.8803 | 4.5727 | 14.4055 | 15.7594 | 21.6397 | 26.2124 | 5.3235 | 9.082 | 2.0234 | 1.3538 | 1.4331 | 3.8027 | 5.8903 | 4.5727 | 14.4055 | 15.7594 | 21.6497 | 26.2224 | 0.01
5.983 | 7.541 | 1.8982 | 2.5283 | 4.0856 | 1.7352 | 9.7504 | 6.1855 | 13.524 | 16.0523 | 25.8027 | 31.9882 | 5.983 | 7.541 | 1.8982 | 2.5283 | 4.0856 | 1.7352 | 9.7604 | 6.1855 | 13.524 | 16.0523 | 25.8127 | 31.9982 | 0.01
7.6771 | 9.7819 | 1.8549 | 2.0122 | 2.5744 | 4.1074 | 7.5437 | 6.0998 | 17.459 | 19.4712 | 27.0149 | 33.1148 | 7.6771 | 9.7819 | 1.8549 | 2.0122 | 2.5744 | 4.1074 | 7.5537 | 6.0998 | 17.459 | 19.4712 | 27.0249 | 33.1248 | 0.01
6.1903 | 7.1794 | 1.8244 | 2.2396 | 2.8762 | 2.08 | 8.1555 | 5.1116 | 13.3698 | 15.6094 | 23.7648 | 28.8764 | 6.1903 | 7.1794 | 1.8244 | 2.2396 | 2.8762 | 2.08 | 8.1655 | 5.1116 | 13.3698 | 15.6094 | 23.7748 | 28.8864 | 0.01
5.0407 | 7.8412 | 2.01 | 1.8661 | 2.8536 | 2.3542 | 8.661 | 3.9116 | 12.882 | 14.7481 | 23.4091 | 27.3207 | 5.0407 | 7.8412 | 2.01 | 1.8661 | 2.8536 | 2.3542 | 8.671 | 3.9116 | 12.882 | 14.7481 | 23.4191 | 27.3307 | 0.01
4.7053 | 9.7595 | 1.8074 | 2.1093 | 1.7381 | 3.3482 | 7.5465 | 2.3074 | 14.4648 | 16.5742 | 24.1207 | 26.4281 | 4.7053 | 9.7595 | 1.8074 | 2.1093 | 1.7381 | 3.3482 | 7.5565 | 2.3074 | 14.4648 | 16.5742 | 24.1307 | 26.4381 | 0.01
5.7142 | 8.9919 | 1.7668 | 1.9261 | 3.7376 | 2.7421 | 5.045 | 4.2602 | 14.7061 | 16.6322 | 23.1118 | 27.372 | 5.7142 | 8.9919 | 1.7668 | 1.9261 | 3.7376 | 2.7421 | 5.055 | 4.2602 | 14.7061 | 16.6322 | 23.1118 | 27.372 | 0.01
6.0701 | 11.1559 | 2.0696 | 2.6698 | 3.384 | 3.1163 | 5.8169 | 5.3834 | 17.226 | 19.8958 | 26.3961 | 31.7795 | 6.0701 | 11.1559 | 2.0696 | 2.6698 | 3.384 | 3.1163 | 5.8269 | 5.3834 | 17.226 | 19.8958 | 26.3961 | 31.7795 | 0.01
6.7926 | 8.9089 | 1.8683 | 1.7495 | 2.6959 | 3.288 | 6.7224 | 5.2388 | 15.7015 | 17.4509 | 24.1733 | 29.4121 | 6.7926 | 8.9089 | 1.8683 | 1.7495 | 2.6959 | 3.288 | 6.7324 | 5.2388 | 15.7015 | 17.4509 | 24.1833 | 29.4221 | 0.01
6.5653 | 6.9048 | 2.0204 | 1.9668 | 3.1483 | 2.0611 | 7.2033 | 6.9634 | 13.4701 | 15.4369 | 22.6402 | 29.6036 | 6.5653 | 6.9048 | 2.0204 | 1.9668 | 3.1483 | 2.0611 | 7.2133 | 6.9634 | 13.4701 | 15.4369 | 22.6502 | 29.6136 | 0.01
5.2956 | 7.1172 | 2.2261 | 1.603 | 4.7249 | 3.3472 | 10.3889 | 5.7909 | 12.4128 | 14.0158 | 24.4047 | 30.1956 | 5.2956 | 7.1172 | 2.2261 | 1.603 | 4.7249 | 3.3472 | 10.3989 | 5.7909 | 12.4128 | 14.0158 | 24.4147 | 30.2056 | 0.01
5.8635 | 8.7178 | 2.395 | 1.7525 | 2.5167 | 2.6256 | 6.7516 | 4.5044 | 14.5813 | 16.3338 | 23.0855 | 27.5898 | 5.8635 | 8.7178 | 2.395 | 1.7525 | 2.5167 | 2.6256 | 6.7616 | 4.5044 | 14.5813 | 16.3338 | 23.0955 | 27.5998 | 0.01
6.0558 | 9.1351 | 2.2637 | 2.1081 | 0.94981 | 3.8144 | 8.057 | 9.3334 | 15.1909 | 17.2989 | 25.3559 | 34.6893 | 6.0558 | 9.1351 | 2.2637 | 2.1081 | 0.94981 | 3.8144 | 8.067 | 9.3334 | 15.1909 | 17.2989 | 25.3659 | 34.6993 | 0.01
5.3803 | 8.5085 | 1.884 | 0.84749 | 3.739 | 4.4814 | 7.2387 | 2.2446 | 13.8887 | 14.7362 | 22.9566 | 25.2012 | 5.3803 | 8.5085 | 1.884 | 0.84749 | 3.739 | 4.4814 | 7.2487 | 2.2446 | 13.8887 | 14.7362 | 22.9566 | 25.2012 | 0.01
6.684 | 7.7947 | 1.9767 | 1.9808 | 3.9737 | 3.043 | 2.149 | 5.0999 | 14.4787 | 16.4596 | 23.4763 | 28.5762 | 6.684 | 7.7947 | 1.9767 | 1.9808 | 3.9737 | 3.043 | 2.159 | 5.0999 | 14.4787 | 16.4596 | 23.4763 | 28.5762 | 0.01
6.6808 | 7.7443 | 1.8029 | 1.7785 | 2.8759 | 3.1287 | 4.907 | 4.0466 | 14.4251 | 16.2036 | 22.2083 | 26.2549 | 6.6808 | 7.7443 | 1.8029 | 1.7785 | 2.8759 | 3.1287 | 4.917 | 4.0466 | 14.4251 | 16.2036 | 22.2083 | 26.2549 | 0.01
5.7119 | 6.2348 | 2.003 | 1.9346 | 2.7781 | 3.9718 | 6.3933 | 3.947 | 11.9466 | 13.8812 | 20.6311 | 24.5781 | 5.7119 | 6.2348 | 2.003 | 1.9346 | 2.7781 | 3.9718 | 6.4033 | 3.947 | 11.9466 | 13.8812 | 20.6311 | 24.5781 | 0.01
5.7808 | 9.1539 | 1.7621 | 1.5018 | 4.1839 | 2.5134 | 6.9897 | 4.7882 | 14.9347 | 16.4365 | 23.4262 | 28.2144 | 5.7808 | 9.1539 | 1.7621 | 1.5018 | 4.1839 | 2.5134 | 6.9997 | 4.7882 | 14.9347 | 16.4365 | 23.4362 | 28.2244 | 0.01
6.0408 | 7.0601 | 2.1076 | 1.9841 | 3.1714 | 2.0152 | 6.4865 | 2.8191 | 13.1009 | 15.085 | 21.5714 | 24.3906 | 6.0408 | 7.0601 | 2.1076 | 1.9841 | 3.1714 | 2.0152 | 6.4965 | 2.8191 | 13.1009 | 15.085 | 21.5814 | 24.4006 | 0.01
5.8255 | 7.6359 | 1.776 | 1.3335 | 2.3285 | 2.335 | 8.3759 | 4.1815 | 13.4615 | 14.795 | 23.1708 | 27.3523 | 5.8255 | 7.6359 | 1.776 | 1.3335 | 2.3285 | 2.335 | 8.3859 | 4.1815 | 13.4615 | 14.795 | 23.1808 | 27.3623 | 0.01
5.9208 | 8.0371 | 1.9624 | 2.4778 | 2.7373 | 2.2325 | 7.4047 | 2.7294 | 13.9579 | 16.4357 | 23.8404 | 26.5699 | 5.9208 | 8.0371 | 1.9624 | 2.4778 | 2.7373 | 2.2325 | 7.4147 | 2.7294 | 13.9579 | 16.4357 | 23.8504 | 26.5799 | 0.01
6.1996 | 7.4433 | 2.2514 | 1.3486 | 3.3037 | 3.8521 | 6.2417 | 4.7512 | 13.6429 | 14.9915 | 22.1473 | 26.8984 | 6.1996 | 7.4433 | 2.2514 | 1.3486 | 3.3037 | 3.8521 | 6.2517 | 4.7512 | 13.6429 | 14.9915 | 22.1473 | 26.8984 | 0.01
6.2059 | 10.3053 | 2.109 | 1.8526 | 3.668 | 3.2722 | 3.791 | 5.1951 | 16.5112 | 18.3638 | 25.304 | 30.4992 | 6.2059 | 10.3053 | 2.109 | 1.8526 | 3.668 | 3.2722 | 3.801 | 5.1951 | 16.5112 | 18.3638 | 25.304 | 30.4992 | 0.01
5.9876 | 7.3599 | 1.877 | 1.6035 | 1.9418 | 2.2815 | 3.0733 | 3.7413 | 13.3475 | 14.9509 | 19.1743 | 22.9155 | 5.9876 | 7.3599 | 1.877 | 1.6035 | 1.9418 | 2.2815 | 3.0833 | 3.7413 | 13.3475 | 14.9509 | 19.1743 | 22.9155 | 0.01
5.5588 | 8.0106 | 1.7449 | 2.1107 | 3.1997 | 2.3467 | 7.164 | 6.9732 | 13.5694 | 15.6801 | 22.8441 | 29.8174 | 5.5588 | 8.0106 | 1.7449 | 2.1107 | 3.1997 | 2.3467 | 7.174 | 6.9732 | 13.5694 | 15.6801 | 22.8541 | 29.8274 | 0.01
6.5473 | 9.6383 | 1.6023 | 1.5716 | 5.0234 | 2.5253 | 6.4225 | 5.1039 | 16.1856 | 17.7572 | 25.3059 | 30.4098 | 6.5473 | 9.6383 | 1.6023 | 1.5716 | 5.0234 | 2.5253 | 6.4325 | 5.1039 | 16.1856 | 17.7572 | 25.3059 | 30.4098 | 0.01
6.81 | 7.0967 | 2.0441 | 2.1661 | 2.8549 | 3.0327 | 6.4366 | 4.6006 | 13.9067 | 16.0728 | 22.5095 | 27.1101 | 6.81 | 7.0967 | 2.0441 | 2.1661 | 2.8549 | 3.0327 | 6.4466 | 4.6006 | 13.9067 | 16.0728 | 22.5195 | 27.1201 | 0.01
6.3864 | 9.2075 | 2.0786 | 2.5046 | 2.3686 | 3.1307 | 6.9587 | 6.4974 | 15.5939 | 18.0985 | 25.0572 | 31.5546 | 6.3864 | 9.2075 | 2.0786 | 2.5046 | 2.3686 | 3.1307 | 6.9687 | 6.4974 | 15.5939 | 18.0985 | 25.0672 | 31.5646 | 0.01
5.8651 | 6.4426 | 1.968 | 1.9805 | 1.4738 | 2.3732 | 8.9093 | 4.5141 | 12.3076 | 14.2881 | 23.1974 | 27.7115 | 5.8651 | 6.4426 | 1.968 | 1.9805 | 1.4738 | 2.3732 | 8.9193 | 4.5141 | 12.3076 | 14.2881 | 23.2074 | 27.7215 | 0.01
4.461 | 10.1442 | 2.2465 | 2.0841 | 3.4135 | 3.0804 | 9.6784 | 3.4526 | 14.6052 | 16.6893 | 26.3677 | 29.8202 | 4.461 | 10.1442 | 2.2465 | 2.0841 | 3.4135 | 3.0804 | 9.6884 | 3.4526 | 14.6052 | 16.6893 | 26.3777 | 29.8302 | 0.01
6.2643 | 7.6512 | 1.9355 | 1.8043 | 0.87846 | 2.9916 | 5.5813 | 5.0644 | 13.9155 | 15.7198 | 21.3011 | 26.3655 | 6.2643 | 7.6512 | 1.9355 | 1.8043 | 0.87846 | 2.9916 | 5.5913 | 5.0644 | 13.9155 | 15.7198 | 21.3111 | 26.3755 | 0.01
4.8826 | 7.9088 | 1.7404 | 1.7547 | 3.2604 | 2.8688 | 10.8118 | 5.5932 | 12.7914 | 14.5461 | 25.3579 | 30.9511 | 4.8826 | 7.9088 | 1.7404 | 1.7547 | 3.2604 | 2.8688 | 10.8218 | 5.5932 | 12.7914 | 14.5461 | 25.3679 | 30.9611 | 0.01
5.6558 | 8.8568 | 2.1559 | 1.3811 | 1.6433 | 2.6709 | 7.8051 | 6.2646 | 14.5126 | 15.8938 | 23.6989 | 29.9635 | 5.6558 | 8.8568 | 2.1559 | 1.3811 | 1.6433 | 2.6709 | 7.8151 | 6.2646 | 14.5126 | 15.8938 | 23.7089 | 29.9735 | 0.01
6.5287 | 8.7002 | 2.0271 | 1.6169 | 3.7779 | 3.2513 | 9.6956 | 6.6879 | 15.2289 | 16.8458 | 26.5414 | 33.2293 | 6.5287 | 8.7002 | 2.0271 | 1.6169 | 3.7779 | 3.2513 | 9.7056 | 6.6879 | 15.2289 | 16.8458 | 26.5514 | 33.2393 | 0.01
4.6462 | 6.2847 | 1.7138 | 1.8268 | 1.8749 | 2.6846 | 8.059 | 6.2144 | 10.9309 | 12.7577 | 20.8167 | 27.0311 | 4.6462 | 6.2847 | 1.7138 | 1.8268 | 1.8749 | 2.6846 | 8.069 | 6.2144 | 10.9309 | 12.7577 | 20.8267 | 27.0411 | 0.01
6.2353 | 9.1336 | 2.0214 | 1.3327 | 3.4156 | 2.7612 | 9.133 | 5.9997 | 15.3689 | 16.7016 | 25.8346 | 31.8343 | 6.2353 | 9.1336 | 2.0214 | 1.3327 | 3.4156 | 2.7612 | 9.143 | 5.9997 | 15.3689 | 16.7016 | 25.8446 | 31.8443 | 0.01
6.3285 | 7.8911 | 2.2611 | 2.3127 | 2.2501 | 2.5405 | 6.8398 | 7.5055 | 14.2197 | 16.5323 | 23.3721 | 30.8776 | 6.3285 | 7.8911 | 2.2611 | 2.3127 | 2.2501 | 2.5405 | 6.8498 | 7.5055 | 14.2197 | 16.5323 | 23.3821 | 30.8876 | 0.01
7.3072 | 7.1187 | 1.9773 | 1.7202 | 4.2326 | 2.8351 | 6.0281 | 3.6856 | 14.4259 | 16.1461 | 23.2138 | 26.8994 | 7.3072 | 7.1187 | 1.9773 | 1.7202 | 4.2326 | 2.8351 | 6.0381 | 3.6856 | 14.4259 | 16.1461 | 23.2138 | 26.8994 | 0.01
5.4917 | 8.4467 | 2.074 | 1.9093 | 3.8719 | 2.9389 | 7.8512 | 5.096 | 13.9383 | 15.8476 | 23.6988 | 28.7948 | 5.4917 | 8.4467 | 2.074 | 1.9093 | 3.8719 | 2.9389 | 7.8612 | 5.096 | 13.9383 | 15.8476 | 23.7088 | 28.8048 | 0.01
6.4931 | 8.9624 | 2.1749 | 2.1119 | 4.011 | 2.2196 | 4.2757 | 4.4357 | 15.4555 | 17.5674 | 23.798 | 28.2337 | 6.4931 | 8.9624 | 2.1749 | 2.1119 | 4.011 | 2.2196 | 4.2857 | 4.4357 | 15.4555 | 17.5674 | 23.798 | 28.2337 | 0.01
6.2951 | 8.0512 | 2.2018 | 1.9716 | 2.5269 | 2.9227 | 7.8199 | 6.3906 | 14.3462 | 16.3179 | 24.1377 | 30.5283 | 6.2951 | 8.0512 | 2.2018 | 1.9716 | 2.5269 | 2.9227 | 7.8299 | 6.3906 | 14.3462 | 16.3179 | 24.1477 | 30.5383 | 0.01
5.6774 | 7.0298 | 1.9847 | 2.4265 | 3.9319 | 3.3994 | 5.7092 | 4.7995 | 12.7072 | 15.1336 | 22.4649 | 27.2645 | 5.6774 | 7.0298 | 1.9847 | 2.4265 | 3.9319 | 3.3994 | 5.7192 | 4.7995 | 12.7072 | 15.1336 | 22.4649 | 27.2645 | 0.01
5.2334 | 8.0816 | 2.339 | 1.5982 | 0.48317 | 3.6224 | 7.0154 | 5.3354 | 13.3149 | 14.9131 | 21.9285 | 27.2639 | 5.2334 | 8.0816 | 2.339 | 1.5982 | 0.48317 | 3.6224 | 7.0254 | 5.3354 | 13.3149 | 14.9131 | 21.9385 | 27.2739 | 0.01
6.5636 | 4.341 | 1.866 | 2.0762 | 2.7535 | 3.6477 | 8.9098 | 4.7859 | 10.9046 | 12.9808 | 21.8906 | 26.6765 | 6.5636 | 4.341 | 1.866 | 2.0762 | 2.7535 | 3.6477 | 8.9198 | 4.7859 | 10.9046 | 12.9808 | 21.9006 | 26.6865 | 0.01
6.2616 | 10.1918 | 1.712 | 2.0427 | 3.7067 | 2.8988 | 6.4014 | 5.8341 | 16.4534 | 18.4961 | 25.1016 | 30.9357 | 6.2616 | 10.1918 | 1.712 | 2.0427 | 3.7067 | 2.8988 | 6.4114 | 5.8341 | 16.4534 | 18.4961 | 25.1016 | 30.9357 | 0.01
5.6066 | 10.4859 | 1.6806 | 1.6861 | 2.8166 | 3.3733 | 8.4039 | 4.7937 | 16.0925 | 17.7786 | 26.1825 | 30.9761 | 5.6066 | 10.4859 | 1.6806 | 1.6861 | 2.8166 | 3.3733 | 8.4139 | 4.7937 | 16.0925 | 17.7786 | 26.1925 | 30.9861 | 0.01
5.3407 | 8.7765 | 1.9967 | 2.1887 | 3.1515 | 3.4983 | 6.2115 | 6.5449 | 14.1172 | 16.3059 | 22.9557 | 29.5006 | 5.3407 | 8.7765 | 1.9967 | 2.1887 | 3.1515 | 3.4983 | 6.2215 | 6.5449 | 14.1172 | 16.3059 | 22.9557 | 29.5006 | 0.01
5.2707 | 7.2062 | 1.9211 | 1.7079 | 2.1551 | 2.3642 | 7.0259 | 3.5218 | 12.4769 | 14.1848 | 21.2107 | 24.7325 | 5.2707 | 7.2062 | 1.9211 | 1.7079 | 2.1551 | 2.3642 | 7.0359 | 3.5218 | 12.4769 | 14.1848 | 21.2207 | 24.7425 | 0.01
5.5124 | 5.8346 | 2.2263 | 2.5805 | 2.6051 | 3.298 | 6.4844 | 6.1653 | 11.347 | 13.9275 | 20.4119 | 26.5772 | 5.5124 | 5.8346 | 2.2263 | 2.5805 | 2.6051 | 3.298 | 6.4944 | 6.1653 | 11.347 | 13.9275 | 20.4219 | 26.5872 | 0.01
6.3646 | 7.9635 | 2.1566 | 2.1828 | 3.47 | 2.42 | 7.9479 | 5.0622 | 14.3281 | 16.5109 | 24.4588 | 29.5211 | 6.3646 | 7.9635 | 2.1566 | 2.1828 | 3.47 | 2.42 | 7.9579 | 5.0622 | 14.3281 | 16.5109 | 24.4688 | 29.5311 | 0.01
6.1458 | 7.3088 | 2.2322 | 2.9349 | 4.5847 | 2.6063 | 5.2318 | 5.4499 | 13.4546 | 16.3895 | 23.5805 | 29.0304 | 6.1458 | 7.3088 | 2.2322 | 2.9349 | 4.5847 | 2.6063 | 5.2418 | 5.4499 | 13.4546 | 16.3895 | 23.5805 | 29.0304 | 0.01
6.2317 | 8.4355 | 2.131 | 2.3068 | 1.5455 | 2.7782 | 10.0245 | 6.5557 | 14.6671 | 16.9739 | 26.9984 | 33.5541 | 6.2317 | 8.4355 | 2.131 | 2.3068 | 1.5455 | 2.7782 | 10.0345 | 6.5557 | 14.6671 | 16.9739 | 27.0084 | 33.5641 | 0.01
5.4787 | 7.6356 | 1.8817 | 1.4227 | 2.444 | 3.2892 | 6.6097 | 3.8723 | 13.1143 | 14.537 | 21.1467 | 25.019 | 5.4787 | 7.6356 | 1.8817 | 1.4227 | 2.444 | 3.2892 | 6.6197 | 3.8723 | 13.1143 | 14.537 | 21.1567 | 25.029 | 0.01
6.8394 | 6.995 | 1.6475 | 2.1743 | 2.3447 | 2.2946 | 7.3608 | 6.7023 | 13.8344 | 16.0087 | 23.3695 | 30.0719 | 6.8394 | 6.995 | 1.6475 | 2.1743 | 2.3447 | 2.2946 | 7.3708 | 6.7023 | 13.8344 | 16.0087 | 23.3795 | 30.0819 | 0.01
6.4529 | 8.919 | 2.2391 | 1.7791 | 3.5845 | 2.286 | 8.3003 | 4.8278 | 15.3719 | 17.1509 | 25.4513 | 30.2791 | 6.4529 | 8.919 | 2.2391 | 1.7791 | 3.5845 | 2.286 | 8.3103 | 4.8278 | 15.3719 | 17.1509 | 25.4613 | 30.2891 | 0.01
5.7109 | 8.0168 | 2.1742 | 2.0506 | 1.6815 | 1.6373 | 7.9747 | 5.737 | 13.7277 | 15.7783 | 23.753 | 29.4901 | 5.7109 | 8.0168 | 2.1742 | 2.0506 | 1.6815 | 1.6373 | 7.9847 | 5.737 | 13.7277 | 15.7783 | 23.763 | 29.5001 | 0.01
5.5551 | 7.3027 | 2.0531 | 2.0334 | 3.2199 | 3.5015 | 8.0918 | 4.6115 | 12.8578 | 14.8912 | 22.983 | 27.5945 | 5.5551 | 7.3027 | 2.0531 | 2.0334 | 3.2199 | 3.5015 | 8.1018 | 4.6115 | 12.8578 | 14.8912 | 22.993 | 27.6045 | 0.01
6.5305 | 10.5137 | 1.8082 | 1.8947 | 1.1709 | 2.3566 | 4.8508 | 4.2331 | 17.0442 | 18.9389 | 23.7897 | 28.0228 | 6.5305 | 10.5137 | 1.8082 | 1.8947 | 1.1709 | 2.3566 | 4.8608 | 4.2331 | 17.0442 | 18.9389 | 23.7997 | 28.0328 | 0.01
6.5079 | 9.761 | 1.7807 | 1.4392 | 1.8146 | 2.3933 | 8.7717 | 5.4728 | 16.2689 | 17.7081 | 26.4798 | 31.9526 | 6.5079 | 9.761 | 1.7807 | 1.4392 | 1.8146 | 2.3933 | 8.7817 | 5.4728 | 16.2689 | 17.7081 | 26.4898 | 31.9626 | 0.01
7.2859 | 7.3906 | 1.8247 | 1.4473 | 2.9468 | 1.6565 | 5.229 | 4.3398 | 14.6765 | 16.1238 | 21.3528 | 25.6926 | 7.2859 | 7.3906 | 1.8247 | 1.4473 | 2.9468 | 1.6565 | 5.239 | 4.3398 | 14.6765 | 16.1238 | 21.3628 | 25.7026 | 0.01
5.8374 | 8.0371 | 2.2048 | 1.9079 | 2.739 | 2.371 | 6.5674 | 4.9569 | 13.8746 | 15.7825 | 22.3499 | 27.3068 | 5.8374 | 8.0371 | 2.2048 | 1.9079 | 2.739 | 2.371 | 6.5774 | 4.9569 | 13.8746 | 15.7825 | 22.3599 | 27.3168 | 0.01
6.0897 | 9.9972 | 2.211 | 2.1318 | 3.2946 | 3.8599 | 6.2938 | 4.7948 | 16.0869 | 18.2187 | 25.3732 | 30.168 | 6.0897 | 9.9972 | 2.211 | 2.1318 | 3.2946 | 3.8599 | 6.3038 | 4.7948 | 16.0869 | 18.2187 | 25.3732 | 30.168 | 0.01
6.126 | 7.7467 | 1.745 | 1.6796 | 3.2803 | 3.2601 | 8.1795 | 6.8415 | 13.8727 | 15.5523 | 23.7319 | 30.5734 | 6.126 | 7.7467 | 1.745 | 1.6796 | 3.2803 | 3.2601 | 8.1895 | 6.8415 | 13.8727 | 15.5523 | 23.7419 | 30.5834 | 0.01
5.7377 | 9.454 | 1.9763 | 1.7316 | 2.8969 | 3.6609 | 7.7715 | 3.328 | 15.1917 | 16.9233 | 24.6948 | 28.0228 | 5.7377 | 9.454 | 1.9763 | 1.7316 | 2.8969 | 3.6609 | 7.7815 | 3.328 | 15.1917 | 16.9233 | 24.7048 | 28.0328 | 0.01
7.1431 | 8.8827 | 2.291 | 2.1496 | 3.1578 | 3.0617 | 5.9859 | 3.3384 | 16.0258 | 18.1753 | 24.3948 | 27.7332 | 7.1431 | 8.8827 | 2.291 | 2.1496 | 3.1578 | 3.0617 | 5.9959 | 3.3384 | 16.0258 | 18.1753 | 24.3948 | 27.7332 | 0.01
6.6859 | 6.803 | 2.5697 | 2.1722 | 2.6549 | 3.09 | 7.2926 | 2.7537 | 13.489 | 15.6612 | 22.9537 | 25.7075 | 6.6859 | 6.803 | 2.5697 | 2.1722 | 2.6549 | 3.09 | 7.3026 | 2.7537 | 13.489 | 15.6612 | 22.9637 | 25.7175 | 0.01
6.44 | 10.2762 | 2.0303 | 1.729 | 4.484 | 2.7086 | 7.236 | 3.2594 | 16.7162 | 18.4452 | 25.6812 | 28.9406 | 6.44 | 10.2762 | 2.0303 | 1.729 | 4.484 | 2.7086 | 7.246 | 3.2594 | 16.7162 | 18.4452 | 25.6912 | 28.9506 | 0.01
6.1011 | 5.8542 | 1.8856 | 1.6729 | 4.1359 | 2.6206 | 6.6714 | 5.2093 | 11.9553 | 13.6282 | 20.3847 | 25.594 | 6.1011 | 5.8542 | 1.8856 | 1.6729 | 4.1359 | 2.6206 | 6.6814 | 5.2093 | 11.9553 | 13.6282 | 20.3847 | 25.594 | 0.01
5.7977 | 6.4243 | 1.8167 | 2.209 | 4.7233 | 2.771 | 8.2865 | 6.3343 | 12.222 | 14.431 | 22.7175 | 29.0518 | 5.7977 | 6.4243 | 1.8167 | 2.209 | 4.7233 | 2.771 | 8.2965 | 6.3343 | 12.222 | 14.431 | 22.7275 | 29.0618 | 0.01
6.9148 | 8.1011 | 2.2541 | 1.8616 | 6.046 | 2.0344 | 5.801 | 3.7344 | 15.0159 | 16.8776 | 24.958 | 28.6924 | 6.9148 | 8.1011 | 2.2541 | 1.8616 | 6.046 | 2.0344 | 5.811 | 3.7344 | 15.0159 | 16.8776 | 24.958 | 28.6924 | 0.01
5.3259 | 6.6099 | 1.8372 | 1.7877 | 2.7785 | 2.5215 | 7.0424 | 5.6739 | 11.9358 | 13.7235 | 20.7659 | 26.4397 | 5.3259 | 6.6099 | 1.8372 | 1.7877 | 2.7785 | 2.5215 | 7.0524 | 5.6739 | 11.9358 | 13.7235 | 20.7759 | 26.4497 | 0.01
6.7971 | 6.577 | 1.9117 | 2.0013 | 3.7279 | 3.9717 | 8.0224 | 5.1282 | 13.3741 | 15.3753 | 23.3977 | 28.5259 | 6.7971 | 6.577 | 1.9117 | 2.0013 | 3.7279 | 3.9717 | 8.0324 | 5.1282 | 13.3741 | 15.3753 | 23.4077 | 28.5359 | 0.01
6.5509 | 9.5642 | 2.4005 | 2.0876 | 3.8398 | 3.1243 | 12.3452 | 5.7572 | 16.1151 | 18.2027 | 30.5479 | 36.3052 | 6.5509 | 9.5642 | 2.4005 | 2.0876 | 3.8398 | 3.1243 | 12.3552 | 5.7572 | 16.1151 | 18.2027 | 30.5579 | 36.3152 | 0.01
6.679 | 7.2773 | 2.5913 | 1.801 | 2.3947 | 2.5847 | 7.7313 | 5.9381 | 13.9563 | 15.7573 | 23.4887 | 29.4268 | 6.679 | 7.2773 | 2.5913 | 1.801 | 2.3947 | 2.5847 | 7.7413 | 5.9381 | 13.9563 | 15.7573 | 23.4987 | 29.4368 | 0.01
5.6592 | 6.2864 | 2.0153 | 2.3386 | 1.4629 | 3.5201 | 8.3246 | 4.1324 | 11.9456 | 14.2842 | 22.6087 | 26.7411 | 5.6592 | 6.2864 | 2.0153 | 2.3386 | 1.4629 | 3.5201 | 8.3346 | 4.1324 | 11.9456 | 14.2842 | 22.6187 | 26.7511 | 0.01
5.0392 | 7.085 | 1.8166 | 2.0124 | 3.8309 | 2.5406 | 9.4981 | 3.8955 | 12.1242 | 14.1366 | 23.6347 | 27.5303 | 5.0392 | 7.085 | 1.8166 | 2.0124 | 3.8309 | 2.5406 | 9.5081 | 3.8955 | 12.1242 | 14.1366 | 23.6447 | 27.5403 | 0.01
5.203 | 9.0775 | 2.2618 | 1.8453 | 3.2312 | 3.8231 | 6.0977 | 5.6803 | 14.2806 | 16.1258 | 23.1801 | 28.8604 | 5.203 | 9.0775 | 2.2618 | 1.8453 | 3.2312 | 3.8231 | 6.1077 | 5.6803 | 14.2806 | 16.1258 | 23.1801 | 28.8604 | 0.01
5.6852 | 8.335 | 2.4559 | 2.0968 | 3.7758 | 3.4744 | 7.889 | 5.6408 | 14.0202 | 16.1171 | 24.006 | 29.6468 | 5.6852 | 8.335 | 2.4559 | 2.0968 | 3.7758 | 3.4744 | 7.899 | 5.6408 | 14.0202 | 16.1171 | 24.016 | 29.6568 | 0.01
5.3503 | 9.5411 | 2.0651 | 2.0269 | 2.4281 | 3.0539 | 7.7566 | 4.5427 | 14.8914 | 16.9182 | 24.6748 | 29.2175 | 5.3503 | 9.5411 | 2.0651 | 2.0269 | 2.4281 | 3.0539 | 7.7666 | 4.5427 | 14.8914 | 16.9182 | 24.6848 | 29.2275 | 0.01
5.9418 | 6.4315 | 2.0152 | 2.3546 | 3.4943 | 2.1039 | 7.5501 | 6.2549 | 12.3733 | 14.7279 | 22.278 | 28.5329 | 5.9418 | 6.4315 | 2.0152 | 2.3546 | 3.4943 | 2.1039 | 7.5601 | 6.2549 | 12.3733 | 14.7279 | 22.288 | 28.5429 | 0.01
6.4717 | 6.9728 | 1.9432 | 2.6766 | 4.0192 | 1.7292 | 6.0955 | 5.4576 | 13.4445 | 16.1212 | 22.2167 | 27.6743 | 6.4717 | 6.9728 | 1.9432 | 2.6766 | 4.0192 | 1.7292 | 6.1055 | 5.4576 | 13.4445 | 16.1212 | 22.2267 | 27.6843 | 0.01
4.7714 | 10.6205 | 2.0207 | 2.1146 | 2.7758 | 2.7716 | 6.0674 | 7.1347 | 15.3919 | 17.5065 | 23.5739 | 30.7086 | 4.7714 | 10.6205 | 2.0207 | 2.1146 | 2.7758 | 2.7716 | 6.0774 | 7.1347 | 15.3919 | 17.5065 | 23.5839 | 30.7186 | 0.01
7.379 | 8.418 | 1.7717 | 2.6992 | 3.368 | 3.6108 | 5.4797 | 5.369 | 15.7969 | 18.4961 | 25.4749 | 30.844 | 7.379 | 8.418 | 1.7717 | 2.6992 | 3.368 | 3.6108 | 5.4897 | 5.369 | 15.7969 | 18.4961 | 25.4749 | 30.844 | 0.01
6.2779 | 10.2684 | 1.6957 | 2.1568 | 3.1594 | 2.5595 | 8.3293 | 4.0739 | 16.5463 | 18.7031 | 27.0324 | 31.1063 | 6.2779 | 10.2684 | 1.6957 | 2.1568 | 3.1594 | 2.5595 | 8.3393 | 4.0739 | 16.5463 | 18.7031 | 27.0424 | 31.1163 | 0.01
5.9066 | 7.5097 | 1.8221 | 2.2097 | 2.3211 | 3.7318 | 7.3129 | 3.2688 | 13.4163 | 15.6261 | 22.939 | 26.2078 | 5.9066 | 7.5097 | 1.8221 | 2.2097 | 2.3211 | 3.7318 | 7.3229 | 3.2688 | 13.4163 | 15.6261 | 22.949 | 26.2178 | 0.01
5.7405 | 9.1544 | 1.9818 | 1.8965 | 2.9394 | 3.351 | 6.7328 | 6.7219 | 14.8949 | 16.7915 | 23.5242 | 30.2461 | 5.7405 | 9.1544 | 1.9818 | 1.8965 | 2.9394 | 3.351 | 6.7428 | 6.7219 | 14.8949 | 16.7915 | 23.5342 | 30.2561 | 0.01
6.2476 | 8.1548 | 2.2087 | 2.1332 | 3.2401 | 3.1066 | 8.132 | 5.072 | 14.4023 | 16.5356 | 24.6676 | 29.7395 | 6.2476 | 8.1548 | 2.2087 | 2.1332 | 3.2401 | 3.1066 | 8.142 | 5.072 | 14.4023 | 16.5356 | 24.6776 | 29.7495 | 0.01
6.0708 | 7.6651 | 1.7055 | 1.9538 | 2.71 | 2.5196 | 7.0198 | 5.3479 | 13.7359 | 15.6897 | 22.7095 | 28.0574 | 6.0708 | 7.6651 | 1.7055 | 1.9538 | 2.71 | 2.5196 | 7.0298 | 5.3479 | 13.7359 | 15.6897 | 22.7195 | 28.0674 | 0.01
5.1294 | 11.1635 | 2.0773 | 1.8943 | 2.7922 | 3.0494 | 5.9556 | 3.8583 | 16.293 | 18.1872 | 24.1429 | 28.0011 | 5.1294 | 11.1635 | 2.0773 | 1.8943 | 2.7922 | 3.0494 | 5.9656 | 3.8583 | 16.293 | 18.1872 | 24.1529 | 28.0111 | 0.01
5.0084 | 7.4379 | 2.0246 | 2.0469 | 1.4455 | 3.728 | 4.5523 | 2.8782 | 12.4463 | 14.4932 | 19.6667 | 22.5449 | 5.0084 | 7.4379 | 2.0246 | 2.0469 | 1.4455 | 3.728 | 4.5623 | 2.8782 | 12.4463 | 14.4932 | 19.6667 | 22.5449 | 0.01
6.1623 | 8.8858 | 1.9479 | 2.0868 | 3.1557 | 2.5206 | 7.5009 | 4.2448 | 15.0481 | 17.135 | 24.6359 | 28.8807 | 6.1623 | 8.8858 | 1.9479 | 2.0868 | 3.1557 | 2.5206 | 7.5109 | 4.2448 | 15.0481 | 17.135 | 24.6459 | 28.8907 | 0.01
6.0454 | 7.1196 | 1.92 | 1.8586 | 2.5974 | 3.0636 | 5.5728 | 4.2624 | 13.165 | 15.0236 | 20.6846 | 24.947 | 6.0454 | 7.1196 | 1.92 | 1.8586 | 2.5974 | 3.0636 | 5.5828 | 4.2624 | 13.165 | 15.0236 | 20.6846 | 24.947 | 0.01
5.7214 | 8.9412 | 1.7943 | 2.1418 | 4.3748 | 3.3663 | 6.402 | 3.9552 | 14.6626 | 16.8044 | 24.5455 | 28.5006 | 5.7214 | 8.9412 | 1.7943 | 2.1418 | 4.3748 | 3.3663 | 6.412 | 3.9552 | 14.6626 | 16.8044 | 24.5455 | 28.5006 | 0.01
6.3419 | 9.502 | 2.2594 | 1.9893 | 3.2864 | 3.6724 | 4.5956 | 3.7842 | 15.8439 | 17.8333 | 24.792 | 28.5762 | 6.3419 | 9.502 | 2.2594 | 1.9893 | 3.2864 | 3.6724 | 4.6056 | 3.7842 | 15.8439 | 17.8333 | 24.792 | 28.5762 | 0.01
5.8039 | 5.3878 | 1.8779 | 2.4155 | 2.4534 | 2.3847 | 8.7952 | 6.9055 | 11.1917 | 13.6072 | 22.4024 | 29.3079 | 5.8039 | 5.3878 | 1.8779 | 2.4155 | 2.4534 | 2.3847 | 8.8052 | 6.9055 | 11.1917 | 13.6072 | 22.4124 | 29.3179 | 0.01
7.0397 | 7.2428 | 1.9447 | 1.4087 | 2.7743 | 2.6526 | 4.5793 | 4.7711 | 14.2825 | 15.6911 | 21.118 | 25.8891 | 7.0397 | 7.2428 | 1.9447 | 1.4087 | 2.7743 | 2.6526 | 4.5893 | 4.7711 | 14.2825 | 15.6911 | 21.118 | 25.8891 | 0.01
6.5304 | 8.0834 | 2.0507 | 1.7536 | 3.4323 | 2.4789 | 6.8983 | 4.3682 | 14.6138 | 16.3674 | 23.2658 | 27.6339 | 6.5304 | 8.0834 | 2.0507 | 1.7536 | 3.4323 | 2.4789 | 6.9083 | 4.3682 | 14.6138 | 16.3674 | 23.2758 | 27.6439 | 0.01
5.1453 | 9.707 | 1.6295 | 2.0236 | 2.5114 | 2.7739 | 5.8834 | 5.5145 | 14.8523 | 16.8759 | 22.7592 | 28.2737 | 5.1453 | 9.707 | 1.6295 | 2.0236 | 2.5114 | 2.7739 | 5.8934 | 5.5145 | 14.8523 | 16.8759 | 22.7692 | 28.2837 | 0.01
5.7099 | 7.6614 | 2.1362 | 1.8465 | 4.1919 | 2.7333 | 4.2992 | 4.2608 | 13.3713 | 15.2178 | 22.143 | 26.4039 | 5.7099 | 7.6614 | 2.1362 | 1.8465 | 4.1919 | 2.7333 | 4.3092 | 4.2608 | 13.3713 | 15.2178 | 22.143 | 26.4039 | 0.01
5.96 | 8.2887 | 1.9829 | 1.7005 | 4.259 | 2.269 | 7.1592 | 6.0938 | 14.2487 | 15.9492 | 23.1084 | 29.2022 | 5.96 | 8.2887 | 1.9829 | 1.7005 | 4.259 | 2.269 | 7.1692 | 6.0938 | 14.2487 | 15.9492 | 23.1184 | 29.2122 | 0.01
7.1097 | 9.2786 | 1.9686 | 1.8451 | 2.8649 | 3.7579 | 6.1526 | 3.9331 | 16.3883 | 18.2334 | 24.8562 | 28.7893 | 7.1097 | 9.2786 | 1.9686 | 1.8451 | 2.8649 | 3.7579 | 6.1626 | 3.9331 | 16.3883 | 18.2334 | 24.8562 | 28.7893 | 0.01
5.7192 | 8.5564 | 1.9871 | 2.0442 | 2.2977 | 3.6297 | 7.4399 | 4.164 | 14.2756 | 16.3198 | 23.7597 | 27.9238 | 5.7192 | 8.5564 | 1.9871 | 2.0442 | 2.2977 | 3.6297 | 7.4499 | 4.164 | 14.2756 | 16.3198 | 23.7697 | 27.9338 | 0.01
4.5859 | 9.2352 | 1.7766 | 2.2529 | 2.7139 | 2.848 | 6.6122 | 4.8535 | 13.8211 | 16.074 | 22.6861 | 27.5397 | 4.5859 | 9.2352 | 1.7766 | 2.2529 | 2.7139 | 2.848 | 6.6222 | 4.8535 | 13.8211 | 16.074 | 22.6961 | 27.5497 | 0.01
5.9244 | 8.9134 | 1.9943 | 1.875 | 2.3249 | 4.0372 | 8.768 | 5.3853 | 14.8378 | 16.7128 | 25.4808 | 30.8661 | 5.9244 | 8.9134 | 1.9943 | 1.875 | 2.3249 | 4.0372 | 8.778 | 5.3853 | 14.8378 | 16.7128 | 25.4908 | 30.8761 | 0.01
6.662 | 6.4434 | 1.632 | 2.047 | 3.1965 | 3.6127 | 3.7133 | 4.7445 | 13.1053 | 15.1523 | 21.9616 | 26.706 | 6.662 | 6.4434 | 1.632 | 2.047 | 3.1965 | 3.6127 | 3.7233 | 4.7445 | 13.1053 | 15.1523 | 21.9616 | 26.706 | 0.01
5.291 | 9.5883 | 1.8641 | 2.719 | 4.2488 | 3.0222 | 5.4282 | 4.9081 | 14.8792 | 17.5982 | 24.8692 | 29.7773 | 5.291 | 9.5883 | 1.8641 | 2.719 | 4.2488 | 3.0222 | 5.4382 | 4.9081 | 14.8792 | 17.5982 | 24.8692 | 29.7773 | 0.01
5.555 | 8.6422 | 1.9917 | 1.5252 | 2.7593 | 3.9676 | 8.3195 | 4.8514 | 14.1972 | 15.7224 | 24.0419 | 28.8933 | 5.555 | 8.6422 | 1.9917 | 1.5252 | 2.7593 | 3.9676 | 8.3295 | 4.8514 | 14.1972 | 15.7224 | 24.0519 | 28.9033 | 0.01
6.2766 | 7.9042 | 1.9242 | 1.871 | 4.3517 | 3.0447 | 5.3999 | 4.5191 | 14.1807 | 16.0517 | 23.4482 | 27.9673 | 6.2766 | 7.9042 | 1.9242 | 1.871 | 4.3517 | 3.0447 | 5.4099 | 4.5191 | 14.1807 | 16.0517 | 23.4482 | 27.9673 | 0.01
5.7035 | 7.8273 | 2.2248 | 2.6908 | 3.0532 | 2.1466 | 5.4563 | 6.2745 | 13.5308 | 16.2216 | 21.6779 | 27.9523 | 5.7035 | 7.8273 | 2.2248 | 2.6908 | 3.0532 | 2.1466 | 5.4663 | 6.2745 | 13.5308 | 16.2216 | 21.6879 | 27.9623 | 0.01
4.8036 | 7.8573 | 2.2679 | 1.8906 | 1.447 | 2.5826 | 7.7435 | 3.6511 | 12.6608 | 14.5514 | 22.2949 | 25.9461 | 4.8036 | 7.8573 | 2.2679 | 1.8906 | 1.447 | 2.5826 | 7.7535 | 3.6511 | 12.6608 | 14.5514 | 22.3049 | 25.9561 | 0.01
6.8117 | 7.7147 | 2.0618 | 1.8943 | 3.174 | 3.3434 | 5.3262 | 4.0735 | 14.5265 | 16.4208 | 22.9381 | 27.0116 | 6.8117 | 7.7147 | 2.0618 | 1.8943 | 3.174 | 3.3434 | 5.3362 | 4.0735 | 14.5265 | 16.4208 | 22.9381 | 27.0116 | 0.01
5.1722 | 8.6405 | 2.0874 | 1.7129 | 2.9514 | 3.2995 | 8.807 | 5.5859 | 13.8127 | 15.5256 | 24.3326 | 29.9185 | 5.1722 | 8.6405 | 2.0874 | 1.7129 | 2.9514 | 3.2995 | 8.817 | 5.5859 | 13.8127 | 15.5256 | 24.3426 | 29.9285 | 0.01
6.5055 | 8.4147 | 1.9707 | 1.8731 | 2.9599 | 2.4189 | 5.3029 | 3.7549 | 14.9202 | 16.7933 | 22.1721 | 25.927 | 6.5055 | 8.4147 | 1.9707 | 1.8731 | 2.9599 | 2.4189 | 5.3129 | 3.7549 | 14.9202 | 16.7933 | 22.1721 | 25.927 | 0.01
5.5209 | 7.7318 | 1.9946 | 1.94 | 3.2607 | 2.6814 | 5.454 | 4.8627 | 13.2527 | 15.1927 | 21.1348 | 25.9975 | 5.5209 | 7.7318 | 1.9946 | 1.94 | 3.2607 | 2.6814 | 5.464 | 4.8627 | 13.2527 | 15.1927 | 21.1348 | 25.9975 | 0.01
4.7729 | 5.9431 | 1.9545 | 2.33 | 2.5594 | 2.9495 | 7.1477 | 3.5293 | 10.7159 | 13.0459 | 20.1937 | 23.7229 | 4.7729 | 5.9431 | 1.9545 | 2.33 | 2.5594 | 2.9495 | 7.1577 | 3.5293 | 10.7159 | 13.0459 | 20.2037 | 23.7329 | 0.01
6.4608 | 6.4468 | 1.9867 | 2.0637 | 5.2622 | 2.1173 | 6.5372 | 8.1274 | 12.9076 | 14.9713 | 22.3508 | 30.4782 | 6.4608 | 6.4468 | 1.9867 | 2.0637 | 5.2622 | 2.1173 | 6.5472 | 8.1274 | 12.9076 | 14.9713 | 22.3508 | 30.4782 | 0.01
6.0121 | 7.7614 | 1.872 | 1.8823 | 3.6046 | 1.886 | 5.9616 | 5.2929 | 13.7736 | 15.6558 | 21.6175 | 26.9104 | 6.0121 | 7.7614 | 1.872 | 1.8823 | 3.6046 | 1.886 | 5.9716 | 5.2929 | 13.7736 | 15.6558 | 21.6275 | 26.9204 | 0.01
5.3798 | 7.2664 | 1.7434 | 2.0519 | 2.0508 | 1.6648 | 8.331 | 3.3251 | 12.6461 | 14.698 | 23.0291 | 26.3541 | 5.3798 | 7.2664 | 1.7434 | 2.0519 | 2.0508 | 1.6648 | 8.341 | 3.3251 | 12.6461 | 14.698 | 23.0391 | 26.3641 | 0.01
6.3169 | 5.9126 | 1.7051 | 1.4548 | 4.5759 | 2.8791 | 5.5086 | 3.3765 | 12.2295 | 13.6842 | 21.1392 | 24.5158 | 6.3169 | 5.9126 | 1.7051 | 1.4548 | 4.5759 | 2.8791 | 5.5186 | 3.3765 | 12.2295 | 13.6842 | 21.1392 | 24.5158 | 0.01
5.5027 | 5.8456 | 2.2891 | 2.2086 | 3.1437 | 3.5283 | 8.388 | 4.0172 | 11.3483 | 13.5569 | 21.9448 | 25.962 | 5.5027 | 5.8456 | 2.2891 | 2.2086 | 3.1437 | 3.5283 | 8.398 | 4.0172 | 11.3483 | 13.5569 | 21.9548 | 25.972 | 0.01
7.0955 | 8.5704 | 2.2351 | 1.7513 | 3.568 | 2.6967 | 7.5271 | 4.594 | 15.6659 | 17.4171 | 24.9442 | 29.5382 | 7.0955 | 8.5704 | 2.2351 | 1.7513 | 3.568 | 2.6967 | 7.5371 | 4.594 | 15.6659 | 17.4171 | 24.9542 | 29.5482 | 0.01
5.4382 | 11.3427 | 1.9941 | 2.0818 | 2.6842 | 3.5185 | 7.126 | 2.9256 | 16.7808 | 18.8626 | 25.9886 | 28.9142 | 5.4382 | 11.3427 | 1.9941 | 2.0818 | 2.6842 | 3.5185 | 7.136 | 2.9256 | 16.7808 | 18.8626 | 25.9986 | 28.9242 | 0.01
6.2294 | 10.1536 | 2.0752 | 2.4037 | 1.5119 | 3.6936 | 4.9033 | 6.7328 | 16.383 | 18.7867 | 23.9922 | 30.7249 | 6.2294 | 10.1536 | 2.0752 | 2.4037 | 1.5119 | 3.6936 | 4.9133 | 6.7328 | 16.383 | 18.7867 | 23.9922 | 30.7249 | 0.01
6.2547 | 7.3136 | 2.0179 | 2.1637 | 2.2477 | 3.6694 | 6.8424 | 6.6313 | 13.5683 | 15.7319 | 22.5744 | 29.2057 | 6.2547 | 7.3136 | 2.0179 | 2.1637 | 2.2477 | 3.6694 | 6.8524 | 6.6313 | 13.5683 | 15.7319 | 22.5844 | 29.2157 | 0.01
6.1348 | 6.0555 | 1.9177 | 2.4758 | 3.7263 | 2.0967 | 7.314 | 4.8764 | 12.1903 | 14.6661 | 21.9801 | 26.8564 | 6.1348 | 6.0555 | 1.9177 | 2.4758 | 3.7263 | 2.0967 | 7.324 | 4.8764 | 12.1903 | 14.6661 | 21.9901 | 26.8664 | 0.01
6.0639 | 7.8239 | 1.9051 | 2.0918 | 2.8943 | 2.2977 | 10.7035 | 5.0807 | 13.8877 | 15.9795 | 26.683 | 31.7637 | 6.0639 | 7.8239 | 1.9051 | 2.0918 | 2.8943 | 2.2977 | 10.7135 | 5.0807 | 13.8877 | 15.9795 | 26.693 | 31.7737 | 0.01
5.1592 | 7.6708 | 1.888 | 1.6816 | 4.2389 | 4.7467 | 5.9982 | 2.4283 | 12.83 | 14.5116 | 23.4971 | 25.9254 | 5.1592 | 7.6708 | 1.888 | 1.6816 | 4.2389 | 4.7467 | 6.0082 | 2.4283 | 12.83 | 14.5116 | 23.4971 | 25.9254 | 0.01
4.8803 | 7.4483 | 2.32 | 1.8245 | 2.2279 | 3.4358 | 9.9729 | 5.1196 | 12.3286 | 14.1531 | 24.126 | 29.2456 | 4.8803 | 7.4483 | 2.32 | 1.8245 | 2.2279 | 3.4358 | 9.9829 | 5.1196 | 12.3286 | 14.1531 | 24.136 | 29.2556 | 0.01
6.3162 | 7.7809 | 2.3299 | 1.6843 | 2.655 | 2.4694 | 8.8445 | 4.3185 | 14.0972 | 15.7814 | 24.6259 | 28.9444 | 6.3162 | 7.7809 | 2.3299 | 1.6843 | 2.655 | 2.4694 | 8.8545 | 4.3185 | 14.0972 | 15.7814 | 24.6359 | 28.9544 | 0.01
7.2173 | 5.7066 | 1.9787 | 1.4974 | 5.0975 | 2.9518 | 7.4549 | 5.731 | 12.9238 | 14.4212 | 22.4705 | 28.2015 | 7.2173 | 5.7066 | 1.9787 | 1.4974 | 5.0975 | 2.9518 | 7.4649 | 5.731 | 12.9238 | 14.4212 | 22.4705 | 28.2015 | 0.01
5.5558 | 6.8807 | 1.9992 | 1.9133 | 2.0222 | 2.7169 | 6.3105 | 7.312 | 12.4364 | 14.3497 | 20.6602 | 27.9723 | 5.5558 | 6.8807 | 1.9992 | 1.9133 | 2.0222 | 2.7169 | 6.3205 | 7.312 | 12.4364 | 14.3497 | 20.6702 | 27.9823 | 0.01
6.7169 | 7.34 | 2.1677 | 1.625 | 2.8797 | 2.5259 | 5.3159 | 3.8555 | 14.0569 | 15.6819 | 21.0876 | 24.9431 | 6.7169 | 7.34 | 2.1677 | 1.625 | 2.8797 | 2.5259 | 5.3259 | 3.8555 | 14.0569 | 15.6819 | 21.0876 | 24.9431 | 0.01
5.5397 | 7.0987 | 2.1685 | 2.1181 | 3.7921 | 2.3286 | 7.7338 | 4.4456 | 12.6384 | 14.7564 | 22.4902 | 26.9358 | 5.5397 | 7.0987 | 2.1685 | 2.1181 | 3.7921 | 2.3286 | 7.7438 | 4.4456 | 12.6384 | 14.7564 | 22.5002 | 26.9458 | 0.01
5.5833 | 6.2701 | 1.6998 | 2.1086 | 3.226 | 2.5332 | 6.4709 | 5.1147 | 11.8534 | 13.962 | 20.4329 | 25.5476 | 5.5833 | 6.2701 | 1.6998 | 2.1086 | 3.226 | 2.5332 | 6.4809 | 5.1147 | 11.8534 | 13.962 | 20.4429 | 25.5576 | 0.01
6.4261 | 8.4238 | 1.5791 | 1.4829 | 1.5297 | 4.2994 | 9.3778 | 5.5246 | 14.85 | 16.3329 | 25.7107 | 31.2353 | 6.4261 | 8.4238 | 1.5791 | 1.4829 | 1.5297 | 4.2994 | 9.3878 | 5.5246 | 14.85 | 16.3329 | 25.7207 | 31.2453 | 0.01
6.7333 | 6.2153 | 2.125 | 1.9771 | 3.0803 | 2.9842 | 9.7048 | 3.0916 | 12.9486 | 14.9257 | 24.6306 | 27.7222 | 6.7333 | 6.2153 | 2.125 | 1.9771 | 3.0803 | 2.9842 | 9.7148 | 3.0916 | 12.9486 | 14.9257 | 24.6406 | 27.7322 | 0.01
6.2548 | 6.4078 | 2.2779 | 2.0861 | 2.1139 | 2.8635 | 6.4957 | 5.6507 | 12.6626 | 14.7487 | 21.2444 | 26.8951 | 6.2548 | 6.4078 | 2.2779 | 2.0861 | 2.1139 | 2.8635 | 6.5057 | 5.6507 | 12.6626 | 14.7487 | 21.2544 | 26.9051 | 0.01
6.422 | 8.2093 | 2.1332 | 1.9701 | 2.576 | 2.6913 | 9.8982 | 4.6103 | 14.6313 | 16.6014 | 26.4995 | 31.1098 | 6.422 | 8.2093 | 2.1332 | 1.9701 | 2.576 | 2.6913 | 9.9082 | 4.6103 | 14.6313 | 16.6014 | 26.5095 | 31.1198 | 0.01
4.7703 | 10.1735 | 1.9904 | 2.4398 | 2.5984 | 2.6555 | 7.2199 | 6.3534 | 14.9437 | 17.3835 | 24.6034 | 30.9568 | 4.7703 | 10.1735 | 1.9904 | 2.4398 | 2.5984 | 2.6555 | 7.2299 | 6.3534 | 14.9437 | 17.3835 | 24.6134 | 30.9668 | 0.01
6.2865 | 5.3158 | 1.5819 | 1.9721 | 1.5054 | 4.4309 | 7.1915 | 4.5001 | 11.6023 | 13.5744 | 20.7659 | 25.2659 | 6.2865 | 5.3158 | 1.5819 | 1.9721 | 1.5054 | 4.4309 | 7.2015 | 4.5001 | 11.6023 | 13.5744 | 20.7759 | 25.2759 | 0.01
6.1655 | 6.781 | 1.9871 | 2.1008 | 3.9852 | 3.069 | 10.5334 | 3.9608 | 12.9464 | 15.0472 | 25.5806 | 29.5414 | 6.1655 | 6.781 | 1.9871 | 2.1008 | 3.9852 | 3.069 | 10.5434 | 3.9608 | 12.9464 | 15.0472 | 25.5906 | 29.5514 | 0.01
6.5542 | 10.7385 | 2.0267 | 2.0328 | 3.3846 | 2.9714 | 9.3245 | 6.7234 | 17.2927 | 19.3255 | 28.6501 | 35.3735 | 6.5542 | 10.7385 | 2.0267 | 2.0328 | 3.3846 | 2.9714 | 9.3345 | 6.7234 | 17.2927 | 19.3255 | 28.6601 | 35.3835 | 0.01
6.0199 | 7.0332 | 2.0104 | 2.3214 | 3.0281 | 2.9486 | 5.8671 | 3.6071 | 13.053 | 15.3744 | 21.3512 | 24.9583 | 6.0199 | 7.0332 | 2.0104 | 2.3214 | 3.0281 | 2.9486 | 5.8771 | 3.6071 | 13.053 | 15.3744 | 21.3512 | 24.9583 | 0.01
5.013 | 8.048 | 2.2288 | 1.8848 | 3.0946 | 3.7156 | 7.6274 | 2.3964 | 13.061 | 14.9458 | 22.5732 | 24.9696 | 5.013 | 8.048 | 2.2288 | 1.8848 | 3.0946 | 3.7156 | 7.6374 | 2.3964 | 13.061 | 14.9458 | 22.5832 | 24.9796 | 0.01
5.6765 | 10.499 | 2.3229 | 1.8458 | 3.2936 | 3.4694 | 8.9356 | 4.6524 | 16.1755 | 18.0213 | 26.9569 | 31.6093 | 5.6765 | 10.499 | 2.3229 | 1.8458 | 3.2936 | 3.4694 | 8.9456 | 4.6524 | 16.1755 | 18.0213 | 26.9669 | 31.6193 | 0.01
5.9083 | 10.6358 | 1.7761 | 1.9537 | 2.8519 | 2.7202 | 7.9292 | 3.4802 | 16.5441 | 18.4978 | 26.427 | 29.9072 | 5.9083 | 10.6358 | 1.7761 | 1.9537 | 2.8519 | 2.7202 | 7.9392 | 3.4802 | 16.5441 | 18.4978 | 26.437 | 29.9172 | 0.01
6.0522 | 7.4358 | 1.9819 | 2.149 | 3.5091 | 2.8809 | 6.9686 | 2.9926 | 13.4879 | 15.637 | 22.6056 | 25.5982 | 6.0522 | 7.4358 | 1.9819 | 2.149 | 3.5091 | 2.8809 | 6.9786 | 2.9926 | 13.4879 | 15.637 | 22.6156 | 25.6082 | 0.01
6.2581 | 6.4964 | 1.5279 | 2.0339 | 3.0487 | 2.5253 | 6.0581 | 5.5607 | 12.7545 | 14.7884 | 20.8465 | 26.4072 | 6.2581 | 6.4964 | 1.5279 | 2.0339 | 3.0487 | 2.5253 | 6.0681 | 5.5607 | 12.7545 | 14.7884 | 20.8565 | 26.4172 | 0.01
6.0104 | 9.0668 | 2.0706 | 2.4086 | 2.8964 | 2.754 | 8.6982 | 5.4141 | 15.0771 | 17.4857 | 26.1839 | 31.5981 | 6.0104 | 9.0668 | 2.0706 | 2.4086 | 2.8964 | 2.754 | 8.7082 | 5.4141 | 15.0771 | 17.4857 | 26.1939 | 31.6081 | 0.01
5.7004 | 7.4806 | 2.1566 | 1.7761 | 2.7245 | 3.1003 | 7.1099 | 7.046 | 13.181 | 14.9571 | 22.0669 | 29.1129 | 5.7004 | 7.4806 | 2.1566 | 1.7761 | 2.7245 | 3.1003 | 7.1199 | 7.046 | 13.181 | 14.9571 | 22.0769 | 29.1229 | 0.01
5.7543 | 7.7294 | 1.8841 | 2.3478 | 4.1085 | 2.5108 | 8.6175 | 5.6193 | 13.4837 | 15.8316 | 24.449 | 30.0683 | 5.7543 | 7.7294 | 1.8841 | 2.3478 | 4.1085 | 2.5108 | 8.6275 | 5.6193 | 13.4837 | 15.8316 | 24.459 | 30.0783 | 0.01
5.5096 | 7.3011 | 1.9492 | 1.615 | 3.1231 | 2.9018 | 6.0062 | 3.2483 | 12.8107 | 14.4257 | 20.4506 | 23.6989 | 5.5096 | 7.3011 | 1.9492 | 1.615 | 3.1231 | 2.9018 | 6.0162 | 3.2483 | 12.8107 | 14.4257 | 20.4506 | 23.6989 | 0.01
5.8337 | 5.9758 | 1.9834 | 2.0607 | 4.3041 | 2.9865 | 7.0746 | 5.0587 | 11.8095 | 13.8701 | 21.1608 | 26.2195 | 5.8337 | 5.9758 | 1.9834 | 2.0607 | 4.3041 | 2.9865 | 7.0846 | 5.0587 | 11.8095 | 13.8701 | 21.1608 | 26.2195 | 0.01
7.3314 | 5.0616 | 2.1151 | 1.7611 | 4.7136 | 1.9055 | 4.6743 | 6.264 | 12.393 | 14.1541 | 20.7731 | 27.0371 | 7.3314 | 5.0616 | 2.1151 | 1.7611 | 4.7136 | 1.9055 | 4.6843 | 6.264 | 12.393 | 14.1541 | 20.7731 | 27.0371 | 0.01
6.465 | 8.3402 | 2.3143 | 1.4319 | 4.7852 | 4.3935 | 8.6698 | 3.7012 | 14.8053 | 16.2372 | 25.416 | 29.1172 | 6.465 | 8.3402 | 2.3143 | 1.4319 | 4.7852 | 4.3935 | 8.6798 | 3.7012 | 14.8053 | 16.2372 | 25.416 | 29.1172 | 0.01
5.1497 | 7.7922 | 2.1989 | 1.6557 | 2.745 | 3.3373 | 6.3248 | 7.1347 | 12.9419 | 14.5976 | 20.9224 | 28.057 | 5.1497 | 7.7922 | 2.1989 | 1.6557 | 2.745 | 3.3373 | 6.3348 | 7.1347 | 12.9419 | 14.5976 | 20.9324 | 28.067 | 0.01
5.8028 | 8.9311 | 1.9664 | 2.1029 | 2.6902 | 2.569 | 6.278 | 4.4228 | 14.7339 | 16.8368 | 23.1148 | 27.5376 | 5.8028 | 8.9311 | 1.9664 | 2.1029 | 2.6902 | 2.569 | 6.288 | 4.4228 | 14.7339 | 16.8368 | 23.1248 | 27.5476 | 0.01
6.4326 | 9.4057 | 1.8875 | 2.4135 | 1.7972 | 3.3069 | 7.9638 | 5.6653 | 15.8383 | 18.2518 | 26.2157 | 31.8809 | 6.4326 | 9.4057 | 1.8875 | 2.4135 | 1.7972 | 3.3069 | 7.9738 | 5.6653 | 15.8383 | 18.2518 | 26.2257 | 31.8909 | 0.01
6.4729 | 6.7576 | 2.1979 | 2.0344 | 3.7412 | 2.8632 | 6.3126 | 6.6193 | 13.2305 | 15.2649 | 21.8693 | 28.4887 | 6.4729 | 6.7576 | 2.1979 | 2.0344 | 3.7412 | 2.8632 | 6.3226 | 6.6193 | 13.2305 | 15.2649 | 21.8693 | 28.4887 | 0.01
6.1096 | 7.8179 | 1.898 | 1.4654 | 1.4031 | 4.0072 | 6.6508 | 4.7162 | 13.9275 | 15.3929 | 22.0437 | 26.76 | 6.1096 | 7.8179 | 1.898 | 1.4654 | 1.4031 | 4.0072 | 6.6608 | 4.7162 | 13.9275 | 15.3929 | 22.0537 | 26.77 | 0.01
6.5456 | 7.9858 | 2.0821 | 2.0008 | 2.7509 | 3.6929 | 9.1537 | 4.5512 | 14.5314 | 16.5323 | 25.6859 | 30.2371 | 6.5456 | 7.9858 | 2.0821 | 2.0008 | 2.7509 | 3.6929 | 9.1637 | 4.5512 | 14.5314 | 16.5323 | 25.6959 | 30.2471 | 0.01
5.6704 | 8.9341 | 1.9908 | 2.0365 | 2.7135 | 2.2656 | 7.9353 | 5.084 | 14.6045 | 16.641 | 24.5763 | 29.6603 | 5.6704 | 8.9341 | 1.9908 | 2.0365 | 2.7135 | 2.2656 | 7.9453 | 5.084 | 14.6045 | 16.641 | 24.5863 | 29.6703 | 0.01
6.1902 | 5.8306 | 1.9634 | 2.2806 | 5.0879 | 3.8245 | 7.8857 | 5.027 | 12.0208 | 14.3014 | 23.2138 | 28.2409 | 6.1902 | 5.8306 | 1.9634 | 2.2806 | 5.0879 | 3.8245 | 7.8957 | 5.027 | 12.0208 | 14.3014 | 23.2138 | 28.2409 | 0.01
6.3438 | 7.5569 | 2.0761 | 1.4649 | 2.0285 | 3.8845 | 7.1194 | 6.5532 | 13.9008 | 15.3656 | 22.485 | 29.0382 | 6.3438 | 7.5569 | 2.0761 | 1.4649 | 2.0285 | 3.8845 | 7.1294 | 6.5532 | 13.9008 | 15.3656 | 22.495 | 29.0482 | 0.01
6.1903 | 6.2807 | 1.9602 | 2.3499 | 2.616 | 2.5683 | 5.7422 | 5.5727 | 12.471 | 14.8209 | 20.5631 | 26.1358 | 6.1903 | 6.2807 | 1.9602 | 2.3499 | 2.616 | 2.5683 | 5.7522 | 5.5727 | 12.471 | 14.8209 | 20.5731 | 26.1458 | 0.01
5.9574 | 8.9994 | 1.9821 | 2.083 | 2.0476 | 3.6481 | 5.2928 | 2.9878 | 14.9568 | 17.0398 | 22.7354 | 25.7232 | 5.9574 | 8.9994 | 1.9821 | 2.083 | 2.0476 | 3.6481 | 5.3028 | 2.9878 | 14.9568 | 17.0398 | 22.7354 | 25.7232 | 0.01
5.7605 | 9.5212 | 2.133 | 1.6166 | 2.5623 | 2.182 | 6.5131 | 5.2049 | 15.2816 | 16.8983 | 23.4114 | 28.6163 | 5.7605 | 9.5212 | 2.133 | 1.6166 | 2.5623 | 2.182 | 6.5231 | 5.2049 | 15.2816 | 16.8983 | 23.4214 | 28.6263 | 0.01
6.1538 | 7.4808 | 2.0876 | 2.1929 | 2.3504 | 2.8995 | 7.297 | 4.9255 | 13.6345 | 15.8274 | 23.1244 | 28.0499 | 6.1538 | 7.4808 | 2.0876 | 2.1929 | 2.3504 | 2.8995 | 7.307 | 4.9255 | 13.6345 | 15.8274 | 23.1344 | 28.0599 | 0.01
5.7579 | 7.7729 | 1.7053 | 1.9868 | 4.5963 | 3.6148 | 7.3254 | 6.7611 | 13.5307 | 15.5175 | 23.7286 | 30.4897 | 5.7579 | 7.7729 | 1.7053 | 1.9868 | 4.5963 | 3.6148 | 7.3354 | 6.7611 | 13.5307 | 15.5175 | 23.7286 | 30.4897 | 0.01
6.263 | 9.5369 | 1.9641 | 2.2158 | 4.2848 | 2.3441 | 8.5159 | 5.9186 | 15.7998 | 18.0157 | 26.5316 | 32.4502 | 6.263 | 9.5369 | 1.9641 | 2.2158 | 4.2848 | 2.3441 | 8.5259 | 5.9186 | 15.7998 | 18.0157 | 26.5416 | 32.4602 | 0.01
5.6443 | 7.774 | 2.3809 | 1.941 | 2.2296 | 2.9792 | 6.0712 | 6.4545 | 13.4182 | 15.3592 | 21.4304 | 27.8849 | 5.6443 | 7.774 | 2.3809 | 1.941 | 2.2296 | 2.9792 | 6.0812 | 6.4545 | 13.4182 | 15.3592 | 21.4404 | 27.8949 | 0.01
5.9506 | 7.9868 | 1.7213 | 1.8821 | 2.9776 | 3.6131 | 8.1883 | 4.1124 | 13.9374 | 15.8195 | 24.0078 | 28.1202 | 5.9506 | 7.9868 | 1.7213 | 1.8821 | 2.9776 | 3.6131 | 8.1983 | 4.1124 | 13.9374 | 15.8195 | 24.0178 | 28.1302 | 0.01
5.0235 | 7.6761 | 1.8687 | 1.6912 | 1.7767 | 3.6257 | 5.7853 | 5.8903 | 12.6996 | 14.3909 | 20.1761 | 26.0664 | 5.0235 | 7.6761 | 1.8687 | 1.6912 | 1.7767 | 3.6257 | 5.7953 | 5.8903 | 12.6996 | 14.3909 | 20.1861 | 26.0764 | 0.01
6.4051 | 6.6956 | 2.0299 | 2.1302 | 1.6647 | 2.3883 | 6.8758 | 4.0016 | 13.1007 | 15.2309 | 22.1066 | 26.1082 | 6.4051 | 6.6956 | 2.0299 | 2.1302 | 1.6647 | 2.3883 | 6.8858 | 4.0016 | 13.1007 | 15.2309 | 22.1166 | 26.1182 | 0.01
4.9074 | 8.4826 | 2.0787 | 2.2767 | 3.6322 | 2.1036 | 5.9177 | 7.0703 | 13.39 | 15.6667 | 21.5844 | 28.6547 | 4.9074 | 8.4826 | 2.0787 | 2.2767 | 3.6322 | 2.1036 | 5.9277 | 7.0703 | 13.39 | 15.6667 | 21.5944 | 28.6647 | 0.01
5.7471 | 9.6039 | 1.9558 | 1.823 | 2.2675 | 1.9786 | 6.7364 | 4.6719 | 15.351 | 17.174 | 23.9104 | 28.5823 | 5.7471 | 9.6039 | 1.9558 | 1.823 | 2.2675 | 1.9786 | 6.7464 | 4.6719 | 15.351 | 17.174 | 23.9204 | 28.5923 | 0.01
6.133 | 8.3538 | 1.9229 | 2.0621 | 2.6848 | 3.8342 | 6.873 | 6.8338 | 14.4869 | 16.5489 | 23.4219 | 30.2558 | 6.133 | 8.3538 | 1.9229 | 2.0621 | 2.6848 | 3.8342 | 6.883 | 6.8338 | 14.4869 | 16.5489 | 23.4319 | 30.2658 | 0.01
7.4583 | 9.4025 | 1.938 | 2.3487 | 3.7335 | 3.0257 | 7.5131 | 4.7547 | 16.8608 | 19.2096 | 26.7226 | 31.4773 | 7.4583 | 9.4025 | 1.938 | 2.3487 | 3.7335 | 3.0257 | 7.5231 | 4.7547 | 16.8608 | 19.2096 | 26.7326 | 31.4873 | 0.01
6.7974 | 6.3395 | 2.1741 | 1.74 | 2.9049 | 3.2629 | 6.5805 | 3.735 | 13.1369 | 14.8768 | 21.4574 | 25.1924 | 6.7974 | 6.3395 | 2.1741 | 1.74 | 2.9049 | 3.2629 | 6.5905 | 3.735 | 13.1369 | 14.8768 | 21.4674 | 25.2024 | 0.01
5.9441 | 7.2666 | 1.9309 | 2.1217 | 2.2793 | 1.9141 | 7.3383 | 4.6367 | 13.2107 | 15.3324 | 22.6707 | 27.3074 | 5.9441 | 7.2666 | 1.9309 | 2.1217 | 2.2793 | 1.9141 | 7.3483 | 4.6367 | 13.2107 | 15.3324 | 22.6807 | 27.3174 | 0.01
5.7204 | 9.0559 | 1.9932 | 1.9846 | 2.8944 | 3.984 | 6.4536 | 3.5734 | 14.7764 | 16.7609 | 23.6393 | 27.2127 | 5.7204 | 9.0559 | 1.9932 | 1.9846 | 2.8944 | 3.984 | 6.4636 | 3.5734 | 14.7764 | 16.7609 | 23.6393 | 27.2127 | 0.01
5.8467 | 7.0123 | 1.8692 | 2.016 | 2.5923 | 2.5599 | 5.4122 | 2.4506 | 12.859 | 14.875 | 20.2871 | 22.7378 | 5.8467 | 7.0123 | 1.8692 | 2.016 | 2.5923 | 2.5599 | 5.4222 | 2.4506 | 12.859 | 14.875 | 20.2971 | 22.7478 | 0.01
5.0324 | 6.8135 | 2.0035 | 2.4049 | 6.8417 | 3.1988 | 6.7212 | 3.9645 | 11.8459 | 14.2508 | 24.2912 | 28.2558 | 5.0324 | 6.8135 | 2.0035 | 2.4049 | 6.8417 | 3.1988 | 6.7312 | 3.9645 | 11.8459 | 14.2508 | 24.2912 | 28.2558 | 0.01
5.825 | 8.9131 | 2.0902 | 2.0596 | 3.5515 | 2.58 | 6.5814 | 6.7924 | 14.7381 | 16.7978 | 23.3791 | 30.1715 | 5.825 | 8.9131 | 2.0902 | 2.0596 | 3.5515 | 2.58 | 6.5914 | 6.7924 | 14.7381 | 16.7978 | 23.3891 | 30.1815 | 0.01
5.2723 | 8.1697 | 1.7603 | 1.9319 | 2.1247 | 3.6584 | 6.4916 | 5.6771 | 13.4419 | 15.3738 | 21.8654 | 27.5425 | 5.2723 | 8.1697 | 1.7603 | 1.9319 | 2.1247 | 3.6584 | 6.5016 | 5.6771 | 13.4419 | 15.3738 | 21.8754 | 27.5525 | 0.01
5.9112 | 7.8924 | 1.9356 | 2.3435 | 2.831 | 2.9822 | 6.8197 | 4.8883 | 13.8036 | 16.1472 | 22.9669 | 27.8551 | 5.9112 | 7.8924 | 1.9356 | 2.3435 | 2.831 | 2.9822 | 6.8297 | 4.8883 | 13.8036 | 16.1472 | 22.9769 | 27.8651 | 0.01
5.8271 | 8.7139 | 1.7678 | 2.1866 | 3.2586 | 2.023 | 8.1596 | 3.9502 | 14.541 | 16.7276 | 24.8872 | 28.8374 | 5.8271 | 8.7139 | 1.7678 | 2.1866 | 3.2586 | 2.023 | 8.1696 | 3.9502 | 14.541 | 16.7276 | 24.8972 | 28.8474 | 0.01
6.6746 | 9.7565 | 2.4673 | 2.0239 | 1.2921 | 3.5801 | 7.5832 | 6.0725 | 16.4311 | 18.455 | 26.0382 | 32.1107 | 6.6746 | 9.7565 | 2.4673 | 2.0239 | 1.2921 | 3.5801 | 7.5932 | 6.0725 | 16.4311 | 18.455 | 26.0482 | 32.1207 | 0.01
6.1904 | 7.5158 | 1.9913 | 1.66 | 2.905 | 2.5455 | 5.5274 | 6.1014 | 13.7063 | 15.3662 | 20.8937 | 26.995 | 6.1904 | 7.5158 | 1.9913 | 1.66 | 2.905 | 2.5455 | 5.5374 | 6.1014 | 13.7063 | 15.3662 | 20.9037 | 27.005 | 0.01
6.4301 | 9.4149 | 2.2617 | 1.998 | 3.5303 | 3.7315 | 7.702 | 5.9133 | 15.8449 | 17.8429 | 25.5449 | 31.4582 | 6.4301 | 9.4149 | 2.2617 | 1.998 | 3.5303 | 3.7315 | 7.712 | 5.9133 | 15.8449 | 17.8429 | 25.5549 | 31.4682 | 0.01
6.1379 | 7.5017 | 2.2476 | 2.8782 | 3.9135 | 3.403 | 5.6839 | 5.5216 | 13.6396 | 16.5178 | 23.8344 | 29.356 | 6.1379 | 7.5017 | 2.2476 | 2.8782 | 3.9135 | 3.403 | 5.6939 | 5.5216 | 13.6396 | 16.5178 | 23.8344 | 29.356 | 0.01
6.0191 | 9.0791 | 2.1804 | 2.4158 | 2.9762 | 1.5579 | 6.3084 | 3.8062 | 15.0982 | 17.514 | 23.8223 | 27.6286 | 6.0191 | 9.0791 | 2.1804 | 2.4158 | 2.9762 | 1.5579 | 6.3184 | 3.8062 | 15.0982 | 17.514 | 23.8323 | 27.6386 | 0.01
6.1901 | 7.6411 | 2.3089 | 2.1278 | 2.4857 | 1.5968 | 8.9478 | 4.5428 | 13.8312 | 15.959 | 24.9069 | 29.4497 | 6.1901 | 7.6411 | 2.3089 | 2.1278 | 2.4857 | 1.5968 | 8.9578 | 4.5428 | 13.8312 | 15.959 | 24.9169 | 29.4597 | 0.01
6.7186 | 7.3043 | 2.1152 | 1.6175 | 2.1529 | 2.6289 | 8.469 | 5.9205 | 14.0229 | 15.6405 | 24.1095 | 30.0301 | 6.7186 | 7.3043 | 2.1152 | 1.6175 | 2.1529 | 2.6289 | 8.479 | 5.9205 | 14.0229 | 15.6405 | 24.1195 | 30.0401 | 0.01
5.3538 | 8.1898 | 2.3266 | 2.1356 | 3.1899 | 2.8573 | 7.7445 | 7.5104 | 13.5436 | 15.6792 | 23.4238 | 30.9341 | 5.3538 | 8.1898 | 2.3266 | 2.1356 | 3.1899 | 2.8573 | 7.7545 | 7.5104 | 13.5436 | 15.6792 | 23.4338 | 30.9441 | 0.01
5.6787 | 6.9733 | 1.6386 | 1.4911 | 3.1715 | 3.2225 | 7.4941 | 6.9865 | 12.6519 | 14.1431 | 21.6372 | 28.6237 | 5.6787 | 6.9733 | 1.6386 | 1.4911 | 3.1715 | 3.2225 | 7.5041 | 6.9865 | 12.6519 | 14.1431 | 21.6472 | 28.6337 | 0.01
5.9295 | 7.3198 | 1.9924 | 2.5095 | 3.8265 | 2.6784 | 6.7111 | 5.677 | 13.2493 | 15.7588 | 22.4699 | 28.1469 | 5.9295 | 7.3198 | 1.9924 | 2.5095 | 3.8265 | 2.6784 | 6.7211 | 5.677 | 13.2493 | 15.7588 | 22.4799 | 28.1569 | 0.01
5.885 | 7.0345 | 1.93 | 2.2326 | 2.3807 | 3.4419 | 6.4935 | 5.5994 | 12.9195 | 15.1521 | 21.6456 | 27.2449 | 5.885 | 7.0345 | 1.93 | 2.2326 | 2.3807 | 3.4419 | 6.5035 | 5.5994 | 12.9195 | 15.1521 | 21.6556 | 27.2549 | 0.01
6.404 | 7.4245 | 1.9915 | 1.8129 | 3.1691 | 4.2377 | 7.2523 | 5.4032 | 13.8285 | 15.6414 | 23.0483 | 28.4514 | 6.404 | 7.4245 | 1.9915 | 1.8129 | 3.1691 | 4.2377 | 7.2623 | 5.4032 | 13.8285 | 15.6414 | 23.0483 | 28.4514 | 0.01
6.6678 | 8.1616 | 1.6798 | 2.0193 | 2.9468 | 2.5227 | 6.3397 | 5.5714 | 14.8294 | 16.8487 | 23.1884 | 28.7599 | 6.6678 | 8.1616 | 1.6798 | 2.0193 | 2.9468 | 2.5227 | 6.3497 | 5.5714 | 14.8294 | 16.8487 | 23.1984 | 28.7699 | 0.01
5.6974 | 7.2938 | 1.9803 | 1.8355 | 4.606 | 2.3486 | 5.049 | 6.8329 | 12.9912 | 14.8268 | 21.7813 | 28.6143 | 5.6974 | 7.2938 | 1.9803 | 1.8355 | 4.606 | 2.3486 | 5.059 | 6.8329 | 12.9912 | 14.8268 | 21.7813 | 28.6143 | 0.01
6.715 | 7.8047 | 2.0679 | 2.2409 | 3.1197 | 2.7257 | 7.8711 | 4.6237 | 14.5197 | 16.7606 | 24.6317 | 29.2554 | 6.715 | 7.8047 | 2.0679 | 2.2409 | 3.1197 | 2.7257 | 7.8811 | 4.6237 | 14.5197 | 16.7606 | 24.6417 | 29.2654 | 0.01
5.373 | 8.2543 | 1.8208 | 1.6604 | 2.7642 | 3.7132 | 6.2511 | 5.5503 | 13.6273 | 15.2877 | 21.7651 | 27.3155 | 5.373 | 8.2543 | 1.8208 | 1.6604 | 2.7642 | 3.7132 | 6.2611 | 5.5503 | 13.6273 | 15.2877 | 21.7651 | 27.3155 | 0.01
6.5719 | 9.0481 | 1.7476 | 1.9699 | 2.5197 | 2.7943 | 10.4976 | 5.7832 | 15.62 | 17.5899 | 28.0875 | 33.8707 | 6.5719 | 9.0481 | 1.7476 | 1.9699 | 2.5197 | 2.7943 | 10.5076 | 5.7832 | 15.62 | 17.5899 | 28.0975 | 33.8807 | 0.01
5.9807 | 8.7184 | 2.1553 | 1.9069 | 2.1247 | 2.8975 | 7.502 | 5.5091 | 14.6991 | 16.606 | 24.108 | 29.617 | 5.9807 | 8.7184 | 2.1553 | 1.9069 | 2.1247 | 2.8975 | 7.512 | 5.5091 | 14.6991 | 16.606 | 24.118 | 29.627 | 0.01
6.0246 | 7.9728 | 1.9879 | 1.9965 | 1.6026 | 2.4929 | 4.5236 | 7.744 | 13.9974 | 15.9939 | 20.5175 | 28.2615 | 6.0246 | 7.9728 | 1.9879 | 1.9965 | 1.6026 | 2.4929 | 4.5336 | 7.744 | 13.9974 | 15.9939 | 20.5275 | 28.2715 | 0.01
6.1483 | 7.6193 | 2.0649 | 1.7571 | 2.752 | 4.06 | 4.9235 | 6.5634 | 13.7676 | 15.5247 | 22.3368 | 28.9002 | 6.1483 | 7.6193 | 2.0649 | 1.7571 | 2.752 | 4.06 | 4.9335 | 6.5634 | 13.7676 | 15.5247 | 22.3368 | 28.9002 | 0.01
6.5655 | 9.6669 | 2.1104 | 1.872 | 2.5903 | 2.2466 | 7.7002 | 5.0967 | 16.2323 | 18.1043 | 25.8045 | 30.9012 | 6.5655 | 9.6669 | 2.1104 | 1.872 | 2.5903 | 2.2466 | 7.7102 | 5.0967 | 16.2323 | 18.1043 | 25.8145 | 30.9112 | 0.01
5.6495 | 8.114 | 2.0658 | 1.8153 | 3.4782 | 1.8544 | 7.398 | 6.6274 | 13.7635 | 15.5788 | 22.9768 | 29.6042 | 5.6495 | 8.114 | 2.0658 | 1.8153 | 3.4782 | 1.8544 | 7.408 | 6.6274 | 13.7635 | 15.5788 | 22.9868 | 29.6142 | 0.01
5.7183 | 7.2918 | 2.0233 | 2.1518 | 1.6127 | 3.4345 | 8.068 | 4.4443 | 13.01 | 15.1618 | 23.2298 | 27.6742 | 5.7183 | 7.2918 | 2.0233 | 2.1518 | 1.6127 | 3.4345 | 8.078 | 4.4443 | 13.01 | 15.1618 | 23.2398 | 27.6842 | 0.01
5.0022 | 9.8056 | 2.1298 | 2.2056 | 2.7135 | 3.5635 | 8.0951 | 6.5498 | 14.8078 | 17.0134 | 25.1085 | 31.6583 | 5.0022 | 9.8056 | 2.1298 | 2.2056 | 2.7135 | 3.5635 | 8.1051 | 6.5498 | 14.8078 | 17.0134 | 25.1185 | 31.6683 | 0.01
6.3071 | 6.8545 | 2.2456 | 1.4285 | 1.8308 | 3.9153 | 2.3812 | 6.3127 | 13.1616 | 14.5901 | 20.3362 | 26.6488 | 6.3071 | 6.8545 | 2.2456 | 1.4285 | 1.8308 | 3.9153 | 2.3912 | 6.3127 | 13.1616 | 14.5901 | 20.3362 | 26.6488 | 0.01
6.1778 | 9.7796 | 1.5097 | 2.5912 | 0.96581 | 3.7576 | 3.1616 | 1.4375 | 15.9574 | 18.5486 | 23.2719 | 24.7094 | 6.1778 | 9.7796 | 1.5097 | 2.5912 | 0.96581 | 3.7576 | 3.1716 | 1.4375 | 15.9574 | 18.5486 | 23.2719 | 24.7094 | 0.01
6.264 | 8.6448 | 1.8081 | 2.4012 | 2.7042 | 2.354 | 3.2844 | 5.4285 | 14.9088 | 17.31 | 22.3681 | 27.7966 | 6.264 | 8.6448 | 1.8081 | 2.4012 | 2.7042 | 2.354 | 3.2944 | 5.4285 | 14.9088 | 17.31 | 22.3681 | 27.7966 | 0.01
5.758 | 7.2925 | 1.6748 | 1.2726 | 3.0228 | 3.0617 | 4.7799 | 5.6407 | 13.0505 | 14.3231 | 20.4076 | 26.0483 | 5.758 | 7.2925 | 1.6748 | 1.2726 | 3.0228 | 3.0617 | 4.7899 | 5.6407 | 13.0505 | 14.3231 | 20.4076 | 26.0483 | 0.01
5.96 | 9.2947 | 1.7281 | 2.293 | 3.8148 | 3.8447 | 8.5784 | 5.5084 | 15.2547 | 17.5477 | 26.1261 | 31.6345 | 5.96 | 9.2947 | 1.7281 | 2.293 | 3.8148 | 3.8447 | 8.5884 | 5.5084 | 15.2547 | 17.5477 | 26.1361 | 31.6445 | 0.01
5.445 | 6.8649 | 1.6904 | 1.3726 | 3.1587 | 3.1653 | 7.2379 | 5.2073 | 12.3099 | 13.6825 | 20.9204 | 26.1276 | 5.445 | 6.8649 | 1.6904 | 1.3726 | 3.1587 | 3.1653 | 7.2479 | 5.2073 | 12.3099 | 13.6825 | 20.9304 | 26.1376 | 0.01
6.2302 | 7.9177 | 2.8019 | 2.3338 | 1.6723 | 3.6676 | 8.3124 | 4.2418 | 14.1478 | 16.4816 | 24.794 | 29.0358 | 6.2302 | 7.9177 | 2.8019 | 2.3338 | 1.6723 | 3.6676 | 8.3224 | 4.2418 | 14.1478 | 16.4816 | 24.804 | 29.0458 | 0.01
5.8189 | 6.7782 | 2.1751 | 1.9565 | 2.6783 | 2.5289 | 8.0978 | 3.7307 | 12.5971 | 14.5536 | 22.6514 | 26.3821 | 5.8189 | 6.7782 | 2.1751 | 1.9565 | 2.6783 | 2.5289 | 8.1078 | 3.7307 | 12.5971 | 14.5536 | 22.6614 | 26.3921 | 0.01
6.0641 | 7.1423 | 1.9364 | 2.4121 | 2.3113 | 1.6913 | 8.4956 | 5.0652 | 13.2065 | 15.6186 | 24.1142 | 29.1794 | 6.0641 | 7.1423 | 1.9364 | 2.4121 | 2.3113 | 1.6913 | 8.5056 | 5.0652 | 13.2065 | 15.6186 | 24.1242 | 29.1894 | 0.01
5.1818 | 8.0029 | 2.0361 | 2.1645 | 0.63575 | 3.8482 | 5.4733 | 3.194 | 13.1847 | 15.3493 | 20.8226 | 24.0166 | 5.1818 | 8.0029 | 2.0361 | 2.1645 | 0.63575 | 3.8482 | 5.4833 | 3.194 | 13.1847 | 15.3493 | 20.8326 | 24.0266 | 0.01
6.1147 | 8.7786 | 1.8099 | 2.2216 | 2.99 | 2.646 | 10.1288 | 5.6383 | 14.8933 | 17.1149 | 27.2437 | 32.882 | 6.1147 | 8.7786 | 1.8099 | 2.2216 | 2.99 | 2.646 | 10.1388 | 5.6383 | 14.8933 | 17.1149 | 27.2537 | 32.892 | 0.01
6.2105 | 7.5669 | 2.1031 | 2.0268 | 2.904 | 3.0508 | 7.3826 | 5.322 | 13.7774 | 15.8042 | 23.1868 | 28.5089 | 6.2105 | 7.5669 | 2.1031 | 2.0268 | 2.904 | 3.0508 | 7.3926 | 5.322 | 13.7774 | 15.8042 | 23.1968 | 28.5189 | 0.01
6.294 | 7.551 | 2.4183 | 1.5528 | 3.0169 | 3.1944 | 7.8946 | 3.3992 | 13.845 | 15.3978 | 23.2924 | 26.6915 | 6.294 | 7.551 | 2.4183 | 1.5528 | 3.0169 | 3.1944 | 7.9046 | 3.3992 | 13.845 | 15.3978 | 23.3024 | 26.7015 | 0.01
6.6485 | 7.8501 | 2.0161 | 1.9538 | 2.691 | 3.4046 | 4.6759 | 5.474 | 14.4986 | 16.4525 | 22.548 | 28.0221 | 6.6485 | 7.8501 | 2.0161 | 1.9538 | 2.691 | 3.4046 | 4.6859 | 5.474 | 14.4986 | 16.4525 | 22.548 | 28.0221 | 0.01
6.4708 | 9.5511 | 1.8213 | 2.0395 | 3.6498 | 3.3316 | 6.9007 | 5.3098 | 16.022 | 18.0614 | 25.0429 | 30.3527 | 6.4708 | 9.5511 | 1.8213 | 2.0395 | 3.6498 | 3.3316 | 6.9107 | 5.3098 | 16.022 | 18.0614 | 25.0429 | 30.3527 | 0.01
6.9974 | 7.0565 | 1.8669 | 2.1099 | 2.2142 | 3.3755 | 8.4755 | 4.2907 | 14.0539 | 16.1638 | 24.6394 | 28.9301 | 6.9974 | 7.0565 | 1.8669 | 2.1099 | 2.2142 | 3.3755 | 8.4855 | 4.2907 | 14.0539 | 16.1638 | 24.6494 | 28.9401 | 0.01
5.7738 | 8.2501 | 2.0708 | 1.7986 | 1.7016 | 3.4602 | 8.4804 | 6.5993 | 14.0239 | 15.8225 | 24.3029 | 30.9022 | 5.7738 | 8.2501 | 2.0708 | 1.7986 | 1.7016 | 3.4602 | 8.4904 | 6.5993 | 14.0239 | 15.8225 | 24.3129 | 30.9122 | 0.01
6.4351 | 10.008 | 1.8373 | 2.2188 | 1.4312 | 2.6924 | 6.4627 | 6.4513 | 16.4431 | 18.6619 | 25.1246 | 31.5759 | 6.4351 | 10.008 | 1.8373 | 2.2188 | 1.4312 | 2.6924 | 6.4727 | 6.4513 | 16.4431 | 18.6619 | 25.1346 | 31.5859 | 0.01
5.444 | 7.9142 | 1.9307 | 2.2101 | 2.536 | 2.535 | 6.3007 | 4.3704 | 13.3582 | 15.5683 | 21.869 | 26.2394 | 5.444 | 7.9142 | 1.9307 | 2.2101 | 2.536 | 2.535 | 6.3107 | 4.3704 | 13.3582 | 15.5683 | 21.879 | 26.2494 | 0.01
7.6107 | 6.5374 | 2.0884 | 2.669 | 3.5556 | 2.2267 | 4.7044 | 5.3827 | 14.1482 | 16.8171 | 22.5994 | 27.9821 | 7.6107 | 6.5374 | 2.0884 | 2.669 | 3.5556 | 2.2267 | 4.7144 | 5.3827 | 14.1482 | 16.8171 | 22.5994 | 27.9821 | 0.01
6.6904 | 7.9712 | 2.1729 | 2.1878 | 3.3899 | 3.4691 | 8.5973 | 5.4128 | 14.6616 | 16.8494 | 25.4467 | 30.8595 | 6.6904 | 7.9712 | 2.1729 | 2.1878 | 3.3899 | 3.4691 | 8.6073 | 5.4128 | 14.6616 | 16.8494 | 25.4567 | 30.8695 | 0.01
5.5809 | 8.2366 | 2.0457 | 2.0519 | 1.5174 | 3.2669 | 5.9259 | 3.5502 | 13.8176 | 15.8695 | 21.7954 | 25.3456 | 5.5809 | 8.2366 | 2.0457 | 2.0519 | 1.5174 | 3.2669 | 5.9359 | 3.5502 | 13.8176 | 15.8695 | 21.8054 | 25.3556 | 0.01
6.137 | 9.4691 | 1.7505 | 1.7499 | 4.2398 | 4.0011 | 8.4977 | 4.2554 | 15.6061 | 17.3561 | 25.8537 | 30.1091 | 6.137 | 9.4691 | 1.7505 | 1.7499 | 4.2398 | 4.0011 | 8.5077 | 4.2554 | 15.6061 | 17.3561 | 25.8637 | 30.1191 | 0.01
5.7116 | 8.8847 | 1.7771 | 1.8404 | 2.4939 | 2.9326 | 5.7722 | 3.9684 | 14.5962 | 16.4367 | 22.2088 | 26.1772 | 5.7116 | 8.8847 | 1.7771 | 1.8404 | 2.4939 | 2.9326 | 5.7822 | 3.9684 | 14.5962 | 16.4367 | 22.2188 | 26.1872 | 0.01
7.2123 | 6.1058 | 1.8955 | 1.8486 | 3.2021 | 3.6253 | 8.4716 | 4.2255 | 13.318 | 15.1666 | 23.6383 | 27.8637 | 7.2123 | 6.1058 | 1.8955 | 1.8486 | 3.2021 | 3.6253 | 8.4816 | 4.2255 | 13.318 | 15.1666 | 23.6483 | 27.8737 | 0.01
6.0644 | 9.2668 | 2.077 | 1.4933 | 2.1938 | 3.2023 | 6.9532 | 7.4663 | 15.3311 | 16.8245 | 23.7777 | 31.244 | 6.0644 | 9.2668 | 2.077 | 1.4933 | 2.1938 | 3.2023 | 6.9632 | 7.4663 | 15.3311 | 16.8245 | 23.7877 | 31.254 | 0.01
5.9792 | 5.4305 | 2.1388 | 1.562 | 2.9355 | 3.5825 | 5.9618 | 4.0441 | 11.4098 | 12.9718 | 19.4898 | 23.5339 | 5.9792 | 5.4305 | 2.1388 | 1.562 | 2.9355 | 3.5825 | 5.9718 | 4.0441 | 11.4098 | 12.9718 | 19.4898 | 23.5339 | 0.01
5.7795 | 8.2552 | 1.9136 | 1.664 | 2.1476 | 3.3916 | 6.4018 | 4.7602 | 14.0346 | 15.6987 | 22.1005 | 26.8607 | 5.7795 | 8.2552 | 1.9136 | 1.664 | 2.1476 | 3.3916 | 6.4118 | 4.7602 | 14.0346 | 15.6987 | 22.1105 | 26.8707 | 0.01
5.7029 | 7.6825 | 1.9203 | 1.9526 | 1.3428 | 3.0399 | 9.227 | 4.3844 | 13.3853 | 15.338 | 24.5649 | 28.9493 | 5.7029 | 7.6825 | 1.9203 | 1.9526 | 1.3428 | 3.0399 | 9.237 | 4.3844 | 13.3853 | 15.338 | 24.5749 | 28.9593 | 0.01
5.5999 | 7.7311 | 1.891 | 2.3367 | 2.2817 | 4.2032 | 3.0698 | 7.0351 | 13.331 | 15.6677 | 22.1526 | 29.1876 | 5.5999 | 7.7311 | 1.891 | 2.3367 | 2.2817 | 4.2032 | 3.0798 | 7.0351 | 13.331 | 15.6677 | 22.1526 | 29.1876 | 0.01
4.8112 | 8.1354 | 1.9275 | 2.0951 | 3.0972 | 3.3593 | 6.2255 | 3.6769 | 12.9466 | 15.0417 | 21.4982 | 25.1751 | 4.8112 | 8.1354 | 1.9275 | 2.0951 | 3.0972 | 3.3593 | 6.2355 | 3.6769 | 12.9466 | 15.0417 | 21.4982 | 25.1751 | 0.01
5.8382 | 7.0973 | 1.9212 | 1.931 | 2.3458 | 2.4116 | 6.2719 | 5.2768 | 12.9355 | 14.8665 | 21.1384 | 26.4152 | 5.8382 | 7.0973 | 1.9212 | 1.931 | 2.3458 | 2.4116 | 6.2819 | 5.2768 | 12.9355 | 14.8665 | 21.1484 | 26.4252 | 0.01
5.6827 | 8.6763 | 2.0464 | 2.2478 | 1.5023 | 2.7736 | 7.7078 | 5.1382 | 14.3589 | 16.6067 | 24.3145 | 29.4527 | 5.6827 | 8.6763 | 2.0464 | 2.2478 | 1.5023 | 2.7736 | 7.7178 | 5.1382 | 14.3589 | 16.6067 | 24.3245 | 29.4627 | 0.01
6.6042 | 9.1561 | 1.9656 | 1.7861 | 3.5985 | 2.3182 | 7.0784 | 4.2906 | 15.7603 | 17.5464 | 24.6248 | 28.9154 | 6.6042 | 9.1561 | 1.9656 | 1.7861 | 3.5985 | 2.3182 | 7.0884 | 4.2906 | 15.7603 | 17.5464 | 24.6348 | 28.9254 | 0.01
4.8335 | 5.7509 | 1.7108 | 1.6673 | 1.1897 | 3.3274 | 5.9527 | 3.4974 | 10.5845 | 12.2517 | 18.2045 | 21.7019 | 4.8335 | 5.7509 | 1.7108 | 1.6673 | 1.1897 | 3.3274 | 5.9627 | 3.4974 | 10.5845 | 12.2517 | 18.2145 | 21.7119 | 0.01
6.3997 | 6.409 | 2.0006 | 1.7381 | 1.6604 | 3.9925 | 7.5965 | 5.399 | 12.8087 | 14.5468 | 22.1432 | 27.5422 | 6.3997 | 6.409 | 2.0006 | 1.7381 | 1.6604 | 3.9925 | 7.6065 | 5.399 | 12.8087 | 14.5468 | 22.1532 | 27.5522 | 0.01
5.2707 | 8.7695 | 1.7775 | 1.486 | 4.7342 | 3.2979 | 6.2052 | 4.3736 | 14.0402 | 15.5262 | 23.5583 | 27.9318 | 5.2707 | 8.7695 | 1.7775 | 1.486 | 4.7342 | 3.2979 | 6.2152 | 4.3736 | 14.0402 | 15.5262 | 23.5583 | 27.9318 | 0.01
6.8154 | 8.6053 | 1.7051 | 1.6691 | 3.8052 | 2.7117 | 6.6047 | 4.1281 | 15.4207 | 17.0898 | 23.6945 | 27.8226 | 6.8154 | 8.6053 | 1.7051 | 1.6691 | 3.8052 | 2.7117 | 6.6147 | 4.1281 | 15.4207 | 17.0898 | 23.7045 | 27.8326 | 0.01
6.7025 | 6.8139 | 2.023 | 1.7978 | 4.1651 | 3.2319 | 7.0515 | 3.1083 | 13.5165 | 15.3143 | 22.7113 | 25.8196 | 6.7025 | 6.8139 | 2.023 | 1.7978 | 4.1651 | 3.2319 | 7.0615 | 3.1083 | 13.5165 | 15.3143 | 22.7113 | 25.8196 | 0.01
5.5199 | 9.1475 | 1.951 | 1.7821 | 3.517 | 2.6751 | 9.2564 | 6.24 | 14.6674 | 16.4495 | 25.7059 | 31.9458 | 5.5199 | 9.1475 | 1.951 | 1.7821 | 3.517 | 2.6751 | 9.2664 | 6.24 | 14.6674 | 16.4495 | 25.7159 | 31.9558 | 0.01
4.5443 | 7.2326 | 1.6507 | 1.84 | 5.7389 | 2.136 | 8.4493 | 5.9834 | 11.7769 | 13.617 | 22.0663 | 28.0497 | 4.5443 | 7.2326 | 1.6507 | 1.84 | 5.7389 | 2.136 | 8.4593 | 5.9834 | 11.7769 | 13.617 | 22.0763 | 28.0597 | 0.01
5.6423 | 5.2179 | 2.179 | 2.0462 | 2.4517 | 2.3069 | 7.887 | 3.8746 | 10.8602 | 12.9064 | 20.7934 | 24.6681 | 5.6423 | 5.2179 | 2.179 | 2.0462 | 2.4517 | 2.3069 | 7.897 | 3.8746 | 10.8602 | 12.9064 | 20.8034 | 24.6781 | 0.01
6.7549 | 7.1515 | 2.4844 | 1.9398 | 4.4638 | 3.3519 | 7.3508 | 4.6056 | 13.9064 | 15.8461 | 23.6618 | 28.2674 | 6.7549 | 7.1515 | 2.4844 | 1.9398 | 4.4638 | 3.3519 | 7.3608 | 4.6056 | 13.9064 | 15.8461 | 23.6618 | 28.2674 | 0.01
5.205 | 5.9579 | 2.157 | 1.8822 | 3.3903 | 2.9063 | 9.6185 | 4.4564 | 11.1629 | 13.0451 | 22.6636 | 27.12 | 5.205 | 5.9579 | 2.157 | 1.8822 | 3.3903 | 2.9063 | 9.6285 | 4.4564 | 11.1629 | 13.0451 | 22.6736 | 27.13 | 0.01
6.5979 | 9.6812 | 1.9795 | 1.7151 | 2.9772 | 1.9333 | 7.5815 | 5.4545 | 16.2791 | 17.9943 | 25.5757 | 31.0303 | 6.5979 | 9.6812 | 1.9795 | 1.7151 | 2.9772 | 1.9333 | 7.5915 | 5.4545 | 16.2791 | 17.9943 | 25.5857 | 31.0403 | 0.01
6.073 | 8.5888 | 2.1131 | 1.436 | 3.5711 | 3.2531 | 7.145 | 3.8432 | 14.6619 | 16.0979 | 23.2429 | 27.086 | 6.073 | 8.5888 | 2.1131 | 1.436 | 3.5711 | 3.2531 | 7.155 | 3.8432 | 14.6619 | 16.0979 | 23.2529 | 27.096 | 0.01
5.4294 | 9.1144 | 1.9019 | 2.0226 | -0.19385 | 4.3092 | 6.898 | 5.0768 | 14.5438 | 16.5665 | 23.4644 | 28.5413 | 5.4294 | 9.1144 | 1.9019 | 2.0226 | -0.19385 | 4.3092 | 6.908 | 5.0768 | 14.5438 | 16.5665 | 23.4744 | 28.5513 | 0.01
6.4272 | 7.9666 | 1.9019 | 1.6093 | 2.1784 | 3 | 9.2356 | 3.1609 | 14.3938 | 16.0032 | 25.2388 | 28.3997 | 6.4272 | 7.9666 | 1.9019 | 1.6093 | 2.1784 | 3 | 9.2456 | 3.1609 | 14.3938 | 16.0032 | 25.2488 | 28.4097 | 0.01
4.8173 | 7.8632 | 2.1622 | 2.2624 | 1.6997 | 3.4668 | 5.1233 | 2.6124 | 12.6805 | 14.9429 | 20.1093 | 22.7218 | 4.8173 | 7.8632 | 2.1622 | 2.2624 | 1.6997 | 3.4668 | 5.1333 | 2.6124 | 12.6805 | 14.9429 | 20.1093 | 22.7218 | 0.01
5.8499 | 7.0686 | 2.1967 | 1.6207 | 2.632 | 2.4009 | 6.6996 | 5.6562 | 12.9185 | 14.5392 | 21.2388 | 26.895 | 5.8499 | 7.0686 | 2.1967 | 1.6207 | 2.632 | 2.4009 | 6.7096 | 5.6562 | 12.9185 | 14.5392 | 21.2488 | 26.905 | 0.01
5.9451 | 6.149 | 2.3987 | 1.9415 | 4.4523 | 3.4304 | 3.0769 | 5.3269 | 12.0941 | 14.0356 | 21.9183 | 27.2452 | 5.9451 | 6.149 | 2.3987 | 1.9415 | 4.4523 | 3.4304 | 3.0869 | 5.3269 | 12.0941 | 14.0356 | 21.9183 | 27.2452 | 0.01
5.3435 | 9.3022 | 1.6392 | 2.3331 | 2.2403 | 1.8666 | 4.601 | 5.2873 | 14.6457 | 16.9789 | 21.5799 | 26.8672 | 5.3435 | 9.3022 | 1.6392 | 2.3331 | 2.2403 | 1.8666 | 4.611 | 5.2873 | 14.6457 | 16.9789 | 21.5899 | 26.8772 | 0.01
6.3476 | 8.85 | 2.5452 | 2.2576 | 3.359 | 3.196 | 8.4167 | 4.8232 | 15.1976 | 17.4552 | 25.8719 | 30.6951 | 6.3476 | 8.85 | 2.5452 | 2.2576 | 3.359 | 3.196 | 8.4267 | 4.8232 | 15.1976 | 17.4552 | 25.8819 | 30.7051 | 0.01
5.2876 | 9.0773 | 1.9958 | 1.7948 | 4.9441 | 2.5748 | 5.9847 | 4.6168 | 14.3649 | 16.1596 | 23.6786 | 28.2954 | 5.2876 | 9.0773 | 1.9958 | 1.7948 | 4.9441 | 2.5748 | 5.9947 | 4.6168 | 14.3649 | 16.1596 | 23.6786 | 28.2954 | 0.01
5.342 | 9.2621 | 1.3824 | 1.9642 | 2.1824 | 3.7466 | 7.9266 | 7.0182 | 14.6041 | 16.5683 | 24.4949 | 31.5131 | 5.342 | 9.2621 | 1.3824 | 1.9642 | 2.1824 | 3.7466 | 7.9366 | 7.0182 | 14.6041 | 16.5683 | 24.5049 | 31.5231 | 0.01
7.4141 | 6.9963 | 2.0538 | 2.289 | 2.6257 | 3.6035 | 7.55 | 3.8997 | 14.4104 | 16.6994 | 24.2493 | 28.1491 | 7.4141 | 6.9963 | 2.0538 | 2.289 | 2.6257 | 3.6035 | 7.56 | 3.8997 | 14.4104 | 16.6994 | 24.2593 | 28.1591 | 0.01
6.0399 | 9.0767 | 2.0233 | 1.9425 | 2.2624 | 3.209 | 7.1125 | 6.0807 | 15.1166 | 17.0591 | 24.1716 | 30.2523 | 6.0399 | 9.0767 | 2.0233 | 1.9425 | 2.2624 | 3.209 | 7.1225 | 6.0807 | 15.1166 | 17.0591 | 24.1816 | 30.2623 | 0.01
6.1959 | 8.5737 | 1.9957 | 2.2471 | 3.2071 | 3.3165 | 6.6798 | 6.2762 | 14.7696 | 17.0167 | 23.6965 | 29.9727 | 6.1959 | 8.5737 | 1.9957 | 2.2471 | 3.2071 | 3.3165 | 6.6898 | 6.2762 | 14.7696 | 17.0167 | 23.7065 | 29.9827 | 0.01
6.2829 | 7.4159 | 2.1409 | 2.1801 | 2.4182 | 3.0886 | 6.5858 | 5.6671 | 13.6989 | 15.8789 | 22.4647 | 28.1318 | 6.2829 | 7.4159 | 2.1409 | 2.1801 | 2.4182 | 3.0886 | 6.5958 | 5.6671 | 13.6989 | 15.8789 | 22.4747 | 28.1418 | 0.01
5.9942 | 8.9148 | 2.313 | 2.3195 | 2.5906 | 2.415 | 6.0051 | 4.1931 | 14.909 | 17.2285 | 23.2335 | 27.4266 | 5.9942 | 8.9148 | 2.313 | 2.3195 | 2.5906 | 2.415 | 6.0151 | 4.1931 | 14.909 | 17.2285 | 23.2435 | 27.4366 | 0.01
5.9727 | 5.8012 | 1.6817 | 1.4426 | 4.5999 | 2.6912 | 7.95 | 5.7482 | 11.7739 | 13.2165 | 21.1665 | 26.9147 | 5.9727 | 5.8012 | 1.6817 | 1.4426 | 4.5999 | 2.6912 | 7.96 | 5.7482 | 11.7739 | 13.2165 | 21.1765 | 26.9247 | 0.01
6.2636 | 8.2469 | 1.94 | 1.8361 | 3.0342 | 1.9185 | 6.0331 | 4.1429 | 14.5105 | 16.3465 | 22.3796 | 26.5225 | 6.2636 | 8.2469 | 1.94 | 1.8361 | 3.0342 | 1.9185 | 6.0431 | 4.1429 | 14.5105 | 16.3465 | 22.3896 | 26.5325 | 0.01
6.6638 | 9.6619 | 2.3176 | 1.7353 | 4.6186 | 3.5897 | 7.8965 | 5.2732 | 16.3257 | 18.061 | 26.2693 | 31.5425 | 6.6638 | 9.6619 | 2.3176 | 1.7353 | 4.6186 | 3.5897 | 7.9065 | 5.2732 | 16.3257 | 18.061 | 26.2693 | 31.5425 | 0.01
6.8217 | 7.8258 | 1.9928 | 2.3153 | 4.2131 | 3.1661 | 8.7255 | 4.2727 | 14.6475 | 16.9628 | 25.6883 | 29.961 | 6.8217 | 7.8258 | 1.9928 | 2.3153 | 4.2131 | 3.1661 | 8.7355 | 4.2727 | 14.6475 | 16.9628 | 25.6983 | 29.971 | 0.01
6.1699 | 10.3111 | 1.7761 | 1.6596 | 4.1291 | 3.4063 | 6.3921 | 5.018 | 16.481 | 18.1406 | 25.676 | 30.694 | 6.1699 | 10.3111 | 1.7761 | 1.6596 | 4.1291 | 3.4063 | 6.4021 | 5.018 | 16.481 | 18.1406 | 25.676 | 30.694 | 0.01
5.5565 | 7.2972 | 1.6011 | 1.2896 | 2.822 | 2.9928 | 3.8558 | 7.1766 | 12.8537 | 14.1433 | 19.958 | 27.1346 | 5.5565 | 7.2972 | 1.6011 | 1.2896 | 2.822 | 2.9928 | 3.8658 | 7.1766 | 12.8537 | 14.1433 | 19.958 | 27.1346 | 0.01
4.8504 | 6.3944 | 1.9669 | 1.7651 | 4.883 | 3.1923 | 8.0694 | 5.3103 | 11.2448 | 13.0099 | 21.0852 | 26.3955 | 4.8504 | 6.3944 | 1.9669 | 1.7651 | 4.883 | 3.1923 | 8.0794 | 5.3103 | 11.2448 | 13.0099 | 21.0893 | 26.3995 | 0.01
6.5794 | 7.6532 | 2.1173 | 2.1109 | 4.8954 | 1.8341 | 7.8007 | 5.5004 | 14.2326 | 16.3435 | 24.1442 | 29.6446 | 6.5794 | 7.6532 | 2.1173 | 2.1109 | 4.8954 | 1.8341 | 7.8107 | 5.5004 | 14.2326 | 16.3435 | 24.1542 | 29.6546 | 0.01
6.618 | 7.572 | 1.9812 | 2.3956 | 3.7534 | 2.6898 | 6.652 | 2.7822 | 14.19 | 16.5856 | 23.2376 | 26.0198 | 6.618 | 7.572 | 1.9812 | 2.3956 | 3.7534 | 2.6898 | 6.662 | 2.7822 | 14.19 | 16.5856 | 23.2476 | 26.0298 | 0.01
6.8747 | 7.5805 | 1.9706 | 2.38 | 2.7996 | 4.2436 | 4.6944 | 4.6653 | 14.4551 | 16.8351 | 23.8783 | 28.5436 | 6.8747 | 7.5805 | 1.9706 | 2.38 | 2.7996 | 4.2436 | 4.7044 | 4.6653 | 14.4551 | 16.8351 | 23.8783 | 28.5436 | 0.01
6.0824 | 8.9274 | 1.932 | 2.3273 | 2.7215 | 2.2287 | 5.8867 | 3.0415 | 15.0099 | 17.3372 | 23.2239 | 26.2654 | 6.0824 | 8.9274 | 1.932 | 2.3273 | 2.7215 | 2.2287 | 5.8967 | 3.0415 | 15.0099 | 17.3372 | 23.2339 | 26.2754 | 0.01
6.6364 | 7.4654 | 1.7283 | 2.2981 | 1.0087 | 3.4092 | 7.1427 | 6.7846 | 14.1019 | 16.4 | 23.5427 | 30.3273 | 6.6364 | 7.4654 | 1.7283 | 2.2981 | 1.0087 | 3.4092 | 7.1527 | 6.7846 | 14.1019 | 16.4 | 23.5527 | 30.3373 | 0.01
6.1233 | 6.1098 | 2.0974 | 2.1828 | 2.1462 | 3.6564 | 5.0641 | 8.1889 | 12.2331 | 14.4158 | 20.2184 | 28.4074 | 6.1233 | 6.1098 | 2.0974 | 2.1828 | 2.1462 | 3.6564 | 5.0741 | 8.1889 | 12.2331 | 14.4158 | 20.2184 | 28.4074 | 0.01
5.9881 | 9.4739 | 1.9271 | 2.2328 | 4.0992 | 3.0543 | 7.8237 | 4.3646 | 15.4619 | 17.6948 | 25.5185 | 29.8831 | 5.9881 | 9.4739 | 1.9271 | 2.2328 | 4.0992 | 3.0543 | 7.8337 | 4.3646 | 15.4619 | 17.6948 | 25.5285 | 29.8931 | 0.01
5.1284 | 9.0652 | 1.8181 | 1.937 | 3.2204 | 2.7837 | 5.9535 | 5.2169 | 14.1936 | 16.1307 | 22.1347 | 27.3517 | 5.1284 | 9.0652 | 1.8181 | 1.937 | 3.2204 | 2.7837 | 5.9635 | 5.2169 | 14.1936 | 16.1307 | 22.1347 | 27.3517 | 0.01
5.3977 | 8.519 | 2.3606 | 2.2311 | 4.152 | 2.6714 | 6.33 | 5.6593 | 13.9167 | 16.1478 | 22.9712 | 28.6305 | 5.3977 | 8.519 | 2.3606 | 2.2311 | 4.152 | 2.6714 | 6.34 | 5.6593 | 13.9167 | 16.1478 | 22.9712 | 28.6305 | 0.01
6.182 | 10.0483 | 1.6951 | 1.9537 | 2.2815 | 4.9491 | 5.5625 | 4.7979 | 16.2303 | 18.1839 | 25.4145 | 30.2124 | 6.182 | 10.0483 | 1.6951 | 1.9537 | 2.2815 | 4.9491 | 5.5725 | 4.7979 | 16.2303 | 18.1839 | 25.4145 | 30.2124 | 0.01
7.4853 | 8.6808 | 1.8898 | 1.5126 | 2.1075 | 3.355 | 6.5558 | 4.4793 | 16.1661 | 17.6787 | 24.2345 | 28.7138 | 7.4853 | 8.6808 | 1.8898 | 1.5126 | 2.1075 | 3.355 | 6.5658 | 4.4793 | 16.1661 | 17.6787 | 24.2445 | 28.7238 | 0.01
5.8231 | 7.5628 | 2.2922 | 1.9575 | 3.2881 | 2.8886 | 9.3674 | 4.9501 | 13.386 | 15.3435 | 24.7109 | 29.6609 | 5.8231 | 7.5628 | 2.2922 | 1.9575 | 3.2881 | 2.8886 | 9.3774 | 4.9501 | 13.386 | 15.3435 | 24.7209 | 29.6709 | 0.01
6.5187 | 8.4865 | 2.2339 | 1.5245 | 4.1632 | 4.0449 | 8.9052 | 5.9537 | 15.0052 | 16.5297 | 25.4349 | 31.3886 | 6.5187 | 8.4865 | 2.2339 | 1.5245 | 4.1632 | 4.0449 | 8.9152 | 5.9537 | 15.0052 | 16.5297 | 25.4449 | 31.3986 | 0.01
6.6304 | 6.6443 | 1.9924 | 2.3914 | 3.9051 | 2.3411 | 9.0002 | 3.9884 | 13.2747 | 15.6661 | 24.6663 | 28.6547 | 6.6304 | 6.6443 | 1.9924 | 2.3914 | 3.9051 | 2.3411 | 9.0102 | 3.9884 | 13.2747 | 15.6661 | 24.6763 | 28.6647 | 0.01
7.2305 | 8.2614 | 2.078 | 2.1227 | 2.1189 | 3.2568 | 6.7046 | 5.6749 | 15.4919 | 17.6146 | 24.3192 | 29.9942 | 7.2305 | 8.2614 | 2.078 | 2.1227 | 2.1189 | 3.2568 | 6.7146 | 5.6749 | 15.4919 | 17.6146 | 24.3292 | 30.0042 | 0.01
6.2678 | 6.563 | 2.0581 | 2.4613 | 3.9799 | 2.571 | 5.8402 | 4.207 | 12.8308 | 15.2921 | 21.8429 | 26.05 | 6.2678 | 6.563 | 2.0581 | 2.4613 | 3.9799 | 2.571 | 5.8502 | 4.207 | 12.8308 | 15.2921 | 21.8429 | 26.05 | 0.01
5.6042 | 7.7657 | 2.0429 | 2.1277 | 1.7159 | 3.0256 | 6.5905 | 6.3373 | 13.3698 | 15.4975 | 22.0881 | 28.4254 | 5.6042 | 7.7657 | 2.0429 | 2.1277 | 1.7159 | 3.0256 | 6.6005 | 6.3373 | 13.3698 | 15.4975 | 22.0981 | 28.4354 | 0.01
5.8459 | 8.5393 | 2.2114 | 2.1631 | 3.5655 | 3.4349 | 9.3754 | 4.6065 | 14.3852 | 16.5484 | 25.9238 | 30.5303 | 5.8459 | 8.5393 | 2.2114 | 2.1631 | 3.5655 | 3.4349 | 9.3854 | 4.6065 | 14.3852 | 16.5484 | 25.9338 | 30.5403 | 0.01
5.4545 | 6.6616 | 2.1213 | 2.1293 | 1.7258 | 1.9549 | 6.135 | 3.8399 | 12.1161 | 14.2454 | 20.3804 | 24.2204 | 5.4545 | 6.6616 | 2.1213 | 2.1293 | 1.7258 | 1.9549 | 6.145 | 3.8399 | 12.1161 | 14.2454 | 20.3904 | 24.2304 | 0.01
4.8115 | 5.4092 | 2.2314 | 2.221 | 2.7946 | 3.5012 | 5.7116 | 4.5249 | 10.2206 | 12.4417 | 18.7374 | 23.2623 | 4.8115 | 5.4092 | 2.2314 | 2.221 | 2.7946 | 3.5012 | 5.7216 | 4.5249 | 10.2206 | 12.4417 | 18.7374 | 23.2623 | 0.01
6.8337 | 6.6749 | 1.8162 | 1.8377 | 0.85462 | 2.7529 | 6.8359 | 3.7528 | 13.5086 | 15.3463 | 22.1821 | 25.935 | 6.8337 | 6.6749 | 1.8162 | 1.8377 | 0.85462 | 2.7529 | 6.8459 | 3.7528 | 13.5086 | 15.3463 | 22.1921 | 25.945 | 0.01
5.9911 | 8.6615 | 1.9339 | 1.9076 | 1.8161 | 2.1768 | 8.2913 | 3.508 | 14.6526 | 16.5602 | 24.8515 | 28.3595 | 5.9911 | 8.6615 | 1.9339 | 1.9076 | 1.8161 | 2.1768 | 8.3013 | 3.508 | 14.6526 | 16.5602 | 24.8615 | 28.3695 | 0.01
6.902 | 7.1838 | 2.3695 | 1.7175 | -0.038149 | 3.4964 | 6.842 | 4.8851 | 14.0858 | 15.8033 | 22.6453 | 27.5304 | 6.902 | 7.1838 | 2.3695 | 1.7175 | -0.038149 | 3.4964 | 6.852 | 4.8851 | 14.0858 | 15.8033 | 22.6553 | 27.5404 | 0.01
6.4632 | 8.007 | 2.136 | 1.5454 | 3.4277 | 2.3859 | 7.4195 | 4.0948 | 14.4702 | 16.0156 | 23.4351 | 27.5299 | 6.4632 | 8.007 | 2.136 | 1.5454 | 3.4277 | 2.3859 | 7.4295 | 4.0948 | 14.4702 | 16.0156 | 23.4451 | 27.5399 | 0.01
5.5612 | 9.4676 | 2.2618 | 2.2619 | 3.2164 | 2.3386 | 7.777 | 4.7451 | 15.0288 | 17.2907 | 25.0677 | 29.8128 | 5.5612 | 9.4676 | 2.2618 | 2.2619 | 3.2164 | 2.3386 | 7.787 | 4.7451 | 15.0288 | 17.2907 | 25.0777 | 29.8228 | 0.01
6.9526 | 7.1263 | 2.1252 | 1.6078 | 1.0684 | 4.0501 | 7.6999 | 1.6366 | 14.0789 | 15.6866 | 23.3866 | 25.0232 | 6.9526 | 7.1263 | 2.1252 | 1.6078 | 1.0684 | 4.0501 | 7.7099 | 1.6366 | 14.0789 | 15.6866 | 23.3966 | 25.0332 | 0.01
7.1872 | 10.7108 | 1.9839 | 2.3184 | 3.7614 | 3.7016 | 8.6923 | 4.8926 | 17.898 | 20.2164 | 28.9087 | 33.8013 | 7.1872 | 10.7108 | 1.9839 | 2.3184 | 3.7614 | 3.7016 | 8.7023 | 4.8926 | 17.898 | 20.2164 | 28.9187 | 33.8113 | 0.01
6.4265 | 8.6528 | 2.1972 | 2.1461 | 3.7563 | 2.7242 | 8.1456 | 6.1142 | 15.0793 | 17.2254 | 25.371 | 31.4851 | 6.4265 | 8.6528 | 2.1972 | 2.1461 | 3.7563 | 2.7242 | 8.1556 | 6.1142 | 15.0793 | 17.2254 | 25.381 | 31.4951 | 0.01
5.2704 | 9.095 | 2.1696 | 1.9518 | 1.8686 | 3.3998 | 6.8242 | 5.9426 | 14.3654 | 16.3173 | 23.1415 | 29.0841 | 5.2704 | 9.095 | 2.1696 | 1.9518 | 1.8686 | 3.3998 | 6.8342 | 5.9426 | 14.3654 | 16.3173 | 23.1515 | 29.0941 | 0.01
5.8184 | 7.7019 | 2.1893 | 1.7752 | 2.2768 | 3.1951 | 5.8814 | 4.9281 | 13.5203 | 15.2955 | 21.1769 | 26.105 | 5.8184 | 7.7019 | 2.1893 | 1.7752 | 2.2768 | 3.1951 | 5.8914 | 4.9281 | 13.5203 | 15.2955 | 21.1869 | 26.115 | 0.01
6.4801 | 7.3975 | 1.7126 | 2.4598 | 2.3971 | 3.417 | 3.8078 | 3.5734 | 13.8775 | 16.3373 | 22.1515 | 25.7249 | 6.4801 | 7.3975 | 1.7126 | 2.4598 | 2.3971 | 3.417 | 3.8178 | 3.5734 | 13.8775 | 16.3373 | 22.1515 | 25.7249 | 0.01
6.7434 | 7.1248 | 2.0593 | 1.9719 | 0.92542 | 3.6808 | 6.0155 | 4.0881 | 13.8682 | 15.8402 | 21.8557 | 25.9437 | 6.7434 | 7.1248 | 2.0593 | 1.9719 | 0.92542 | 3.6808 | 6.0255 | 4.0881 | 13.8682 | 15.8402 | 21.8657 | 25.9537 | 0.01
5.4928 | 7.3711 | 2.2156 | 2.161 | 4.3438 | 2.1908 | 6.5952 | 5.8694 | 12.864 | 15.025 | 21.6202 | 27.4896 | 5.4928 | 7.3711 | 2.2156 | 2.161 | 4.3438 | 2.1908 | 6.6052 | 5.8694 | 12.864 | 15.025 | 21.6302 | 27.4996 | 0.01
5.3407 | 8.0962 | 2.2377 | 2.1238 | 2.2035 | 1.9501 | 8.9241 | 4.009 | 13.4369 | 15.5608 | 24.4848 | 28.4938 | 5.3407 | 8.0962 | 2.2377 | 2.1238 | 2.2035 | 1.9501 | 8.9341 | 4.009 | 13.4369 | 15.5608 | 24.4948 | 28.5038 | 0.01
5.2679 | 7.2724 | 1.4745 | 2.3091 | 3.7965 | 1.5372 | 7.6311 | 4.1903 | 12.5404 | 14.8494 | 22.4805 | 26.6708 | 5.2679 | 7.2724 | 1.4745 | 2.3091 | 3.7965 | 1.5372 | 7.6411 | 4.1903 | 12.5404 | 14.8494 | 22.4905 | 26.6808 | 0.01
5.6067 | 7.7615 | 1.8491 | 1.8631 | 4.2017 | 2.6065 | 8.9196 | 6.2905 | 13.3683 | 15.2314 | 24.151 | 30.4415 | 5.6067 | 7.7615 | 1.8491 | 1.8631 | 4.2017 | 2.6065 | 8.9296 | 6.2905 | 13.3683 | 15.2314 | 24.161 | 30.4515 | 0.01
6.5532 | 7.6247 | 2.1873 | 2.1151 | 3.9661 | 3.3399 | 11.0616 | 6.0155 | 14.1779 | 16.293 | 27.3546 | 33.3701 | 6.5532 | 7.6247 | 2.1873 | 2.1151 | 3.9661 | 3.3399 | 11.0716 | 6.0155 | 14.1779 | 16.293 | 27.3646 | 33.3801 | 0.01
7.3324 | 5.1929 | 2.0893 | 1.8375 | 3.3842 | 2.6122 | 7.53 | 3.7577 | 12.5253 | 14.3629 | 21.8929 | 25.6505 | 7.3324 | 5.1929 | 2.0893 | 1.8375 | 3.3842 | 2.6122 | 7.54 | 3.7577 | 12.5253 | 14.3629 | 21.9029 | 25.6605 | 0.01
6.543 | 6.8785 | 1.9377 | 1.8992 | 3.1547 | 3.4374 | 6.4536 | 5.3765 | 13.4216 | 15.3208 | 21.9129 | 27.2894 | 6.543 | 6.8785 | 1.9377 | 1.8992 | 3.1547 | 3.4374 | 6.4636 | 5.3765 | 13.4216 | 15.3208 | 21.9129 | 27.2894 | 0.01
5.2765 | 6.9243 | 1.9787 | 1.2846 | 2.2173 | 3.1721 | 6.7856 | 9.2762 | 12.2007 | 13.4853 | 20.2709 | 29.547 | 5.2765 | 6.9243 | 1.9787 | 1.2846 | 2.2173 | 3.1721 | 6.7956 | 9.2762 | 12.2007 | 13.4853 | 20.2809 | 29.557 | 0.01
5.0878 | 9.119 | 1.9129 | 1.8714 | 1.9595 | 2.1664 | 6.7037 | 6.6798 | 14.2068 | 16.0782 | 22.7819 | 29.4617 | 5.0878 | 9.119 | 1.9129 | 1.8714 | 1.9595 | 2.1664 | 6.7137 | 6.6798 | 14.2068 | 16.0782 | 22.7919 | 29.4717 | 0.01
6.1194 | 9.1028 | 2.1452 | 2.0868 | 4.573 | 3.5099 | 6.5328 | 4.0227 | 15.2222 | 17.309 | 25.3918 | 29.4146 | 6.1194 | 9.1028 | 2.1452 | 2.0868 | 4.573 | 3.5099 | 6.5428 | 4.0227 | 15.2222 | 17.309 | 25.3918 | 29.4146 | 0.01
6.4632 | 9.2521 | 2.0502 | 2.0187 | 2.8501 | 2.6986 | 7.1855 | 3.5749 | 15.7154 | 17.7341 | 24.9196 | 28.4945 | 6.4632 | 9.2521 | 2.0502 | 2.0187 | 2.8501 | 2.6986 | 7.1955 | 3.5749 | 15.7154 | 17.7341 | 24.9296 | 28.5045 | 0.01
6.8344 | 9.7978 | 1.8791 | 1.9879 | 4.1509 | 2.3656 | 6.0946 | 6.0785 | 16.6322 | 18.6202 | 25.1367 | 31.2152 | 6.8344 | 9.7978 | 1.8791 | 1.9879 | 4.1509 | 2.3656 | 6.1046 | 6.0785 | 16.6322 | 18.6202 | 25.1367 | 31.2152 | 0.01
6.6279 | 9.9108 | 1.9941 | 1.7488 | 3.2437 | 1.8157 | 8.3492 | 5.5568 | 16.5387 | 18.2874 | 26.6366 | 32.1934 | 6.6279 | 9.9108 | 1.9941 | 1.7488 | 3.2437 | 1.8157 | 8.3592 | 5.5568 | 16.5387 | 18.2874 | 26.6466 | 32.2034 | 0.01
6.4823 | 6.9838 | 1.9313 | 2.204 | 2.7857 | 2.7761 | 6.022 | 8.5196 | 13.4661 | 15.67 | 21.6921 | 30.2117 | 6.4823 | 6.9838 | 1.9313 | 2.204 | 2.7857 | 2.7761 | 6.032 | 8.5196 | 13.4661 | 15.67 | 21.7021 | 30.2217 | 0.01
6.7804 | 8.0276 | 2.3521 | 1.4601 | 2.5794 | 3.053 | 7.3294 | 4.9107 | 14.808 | 16.2681 | 23.5975 | 28.5082 | 6.7804 | 8.0276 | 2.3521 | 1.4601 | 2.5794 | 3.053 | 7.3394 | 4.9107 | 14.808 | 16.2681 | 23.6075 | 28.5182 | 0.01
6.6183 | 7.2099 | 2.0493 | 2.2008 | 4.7359 | 3.4186 | 7.1791 | 5.9602 | 13.8283 | 16.029 | 24.1836 | 30.1438 | 6.6183 | 7.2099 | 2.0493 | 2.2008 | 4.7359 | 3.4186 | 7.1891 | 5.9602 | 13.8283 | 16.029 | 24.1836 | 30.1438 | 0.01
5.946 | 7.1708 | 2.0543 | 1.841 | 4.0932 | 2.9428 | 7.3093 | 3.0522 | 13.1168 | 14.9578 | 22.2671 | 25.3193 | 5.946 | 7.1708 | 2.0543 | 1.841 | 4.0932 | 2.9428 | 7.3193 | 3.0522 | 13.1168 | 14.9578 | 22.2771 | 25.3293 | 0.01
6.5518 | 7.6015 | 2.1447 | 2.4703 | 3.1244 | 3.3933 | 9.2794 | 6.2376 | 14.1533 | 16.6236 | 25.903 | 32.1407 | 6.5518 | 7.6015 | 2.1447 | 2.4703 | 3.1244 | 3.3933 | 9.2894 | 6.2376 | 14.1533 | 16.6236 | 25.913 | 32.1507 | 0.01
7.089 | 7.9354 | 1.9466 | 2.0562 | 3.4476 | 3.284 | 6.5829 | 4.9026 | 15.0244 | 17.0806 | 23.8122 | 28.7148 | 7.089 | 7.9354 | 1.9466 | 2.0562 | 3.4476 | 3.284 | 6.5929 | 4.9026 | 15.0244 | 17.0806 | 23.8122 | 28.7148 | 0.01
6.8081 | 6.7155 | 2.1033 | 1.7062 | 1.785 | 2.2308 | 6.2856 | 5.8523 | 13.5236 | 15.2298 | 21.5154 | 27.3677 | 6.8081 | 6.7155 | 2.1033 | 1.7062 | 1.785 | 2.2308 | 6.2956 | 5.8523 | 13.5236 | 15.2298 | 21.5254 | 27.3777 | 0.01
5.802 | 8.4392 | 1.8363 | 2.385 | 3.8043 | 3.7665 | 7.5421 | 4.7093 | 14.2411 | 16.6262 | 24.197 | 28.9062 | 5.802 | 8.4392 | 1.8363 | 2.385 | 3.8043 | 3.7665 | 7.5521 | 4.7093 | 14.2411 | 16.6262 | 24.197 | 28.9062 | 0.01
5.6975 | 9.0148 | 2.3468 | 2.2224 | 0.055493 | 3.142 | 9.2122 | 4.9445 | 14.7123 | 16.9347 | 26.1469 | 31.0914 | 5.6975 | 9.0148 | 2.3468 | 2.2224 | 0.055493 | 3.142 | 9.2222 | 4.9445 | 14.7123 | 16.9347 | 26.1569 | 31.1014 | 0.01
5.8966 | 9.2105 | 2.1484 | 2.1025 | 2.8576 | 4.2253 | 4.7249 | 8.3776 | 15.1071 | 17.2096 | 24.2925 | 32.67 | 5.8966 | 9.2105 | 2.1484 | 2.1025 | 2.8576 | 4.2253 | 4.7349 | 8.3776 | 15.1071 | 17.2096 | 24.2925 | 32.67 | 0.01
5.283 | 6.8327 | 2.2625 | 2.6117 | 4.6691 | 3.2791 | 8.2773 | 4.7113 | 12.1156 | 14.7273 | 23.0046 | 27.716 | 5.283 | 6.8327 | 2.2625 | 2.6117 | 4.6691 | 3.2791 | 8.2873 | 4.7113 | 12.1156 | 14.7273 | 23.0146 | 27.726 | 0.01
6.532 | 7.1627 | 2.3432 | 2.0513 | 2.2042 | 3.3476 | 5.8555 | 4.0753 | 13.6947 | 15.7461 | 21.6016 | 25.6768 | 6.532 | 7.1627 | 2.3432 | 2.0513 | 2.2042 | 3.3476 | 5.8655 | 4.0753 | 13.6947 | 15.7461 | 21.6116 | 25.6868 | 0.01
5.5036 | 7.0221 | 1.9646 | 1.6733 | 3.5126 | 3.0785 | 6.5192 | 4.847 | 12.5257 | 14.199 | 20.7901 | 25.637 | 5.5036 | 7.0221 | 1.9646 | 1.6733 | 3.5126 | 3.0785 | 6.5292 | 4.847 | 12.5257 | 14.199 | 20.7901 | 25.637 | 0.01
6.7593 | 7.194 | 2.0788 | 1.8268 | 1.5089 | 3.1351 | 5.9564 | 6.3575 | 13.9532 | 15.78 | 21.7364 | 28.0939 | 6.7593 | 7.194 | 2.0788 | 1.8268 | 1.5089 | 3.1351 | 5.9664 | 6.3575 | 13.9532 | 15.78 | 21.7464 | 28.1039 | 0.01
6.4701 | 7.229 | 2.4207 | 1.7473 | 1.9465 | 2.4637 | 6.9657 | 4.6285 | 13.6991 | 15.4464 | 22.4121 | 27.0406 | 6.4701 | 7.229 | 2.4207 | 1.7473 | 1.9465 | 2.4637 | 6.9757 | 4.6285 | 13.6991 | 15.4464 | 22.4221 | 27.0506 | 0.01
4.7489 | 7.9481 | 2.1169 | 1.7062 | 4.0857 | 3.5465 | 5.7758 | 5.7967 | 12.697 | 14.4032 | 22.0355 | 27.8322 | 4.7489 | 7.9481 | 2.1169 | 1.7062 | 4.0857 | 3.5465 | 5.7858 | 5.7967 | 12.697 | 14.4032 | 22.0355 | 27.8322 | 0.01
6.4235 | 8.8762 | 2.0805 | 1.8622 | 3.7372 | 3.017 | 5.1761 | 6.219 | 15.2997 | 17.1619 | 23.916 | 30.135 | 6.4235 | 8.8762 | 2.0805 | 1.8622 | 3.7372 | 3.017 | 5.1861 | 6.219 | 15.2997 | 17.1619 | 23.916 | 30.135 | 0.01
5.7025 | 5.1382 | 2.2734 | 2.0589 | 3.4625 | 3.1152 | 6.7839 | 6.0843 | 10.8407 | 12.8997 | 19.6836 | 25.7679 | 5.7025 | 5.1382 | 2.2734 | 2.0589 | 3.4625 | 3.1152 | 6.7939 | 6.0843 | 10.8407 | 12.8997 | 19.6936 | 25.7779 | 0.01
5.9896 | 7.5327 | 2.2504 | 1.9673 | 2.0394 | 3.3191 | 5.715 | 7.2656 | 13.5224 | 15.4897 | 21.2047 | 28.4703 | 5.9896 | 7.5327 | 2.2504 | 1.9673 | 2.0394 | 3.3191 | 5.725 | 7.2656 | 13.5224 | 15.4897 | 21.2147 | 28.4803 | 0.01
5.9634 | 7.8148 | 1.9203 | 2.3326 | 2.1548 | 3.1798 | 7.2259 | 3.9524 | 13.7782 | 16.1108 | 23.3367 | 27.2891 | 5.9634 | 7.8148 | 1.9203 | 2.3326 | 2.1548 | 3.1798 | 7.2359 | 3.9524 | 13.7782 | 16.1108 | 23.3467 | 27.2991 | 0.01
5.7428 | 8.778 | 1.9264 | 1.5607 | 3.3939 | 3.3432 | 7.0797 | 4.437 | 14.5208 | 16.0816 | 23.1613 | 27.5983 | 5.7428 | 8.778 | 1.9264 | 1.5607 | 3.3939 | 3.3432 | 7.0897 | 4.437 | 14.5208 | 16.0816 | 23.1713 | 27.6083 | 0.01
6.2073 | 6.2776 | 1.764 | 2.4617 | 0.094128 | 2.5033 | 5.7731 | 5.1706 | 12.4848 | 14.9466 | 20.7197 | 25.8903 | 6.2073 | 6.2776 | 1.764 | 2.4617 | 0.094128 | 2.5033 | 5.7831 | 5.1706 | 12.4848 | 14.9466 | 20.7297 | 25.9003 | 0.01
6.35 | 7.722 | 1.8888 | 1.4633 | 2.4023 | 3.9526 | 8.0193 | 4.9997 | 14.0719 | 15.5352 | 23.5546 | 28.5543 | 6.35 | 7.722 | 1.8888 | 1.4633 | 2.4023 | 3.9526 | 8.0293 | 4.9997 | 14.0719 | 15.5352 | 23.5646 | 28.5643 | 0.01
5.3796 | 7.9367 | 1.9302 | 2.1641 | 3.3575 | 4.0495 | 8.7805 | 5.4599 | 13.3163 | 15.4804 | 24.2609 | 29.7207 | 5.3796 | 7.9367 | 1.9302 | 2.1641 | 3.3575 | 4.0495 | 8.7905 | 5.4599 | 13.3163 | 15.4804 | 24.2709 | 29.7307 | 0.01
5.7736 | 8.9197 | 1.5412 | 1.6277 | 1.5016 | 2.4375 | 10.2355 | 6.8117 | 14.6933 | 16.321 | 26.5564 | 33.3681 | 5.7736 | 8.9197 | 1.5412 | 1.6277 | 1.5016 | 2.4375 | 10.2455 | 6.8117 | 14.6933 | 16.321 | 26.5664 | 33.3781 | 0.01
5.2758 | 7.1936 | 1.7226 | 1.778 | 3.0006 | 2.7405 | 6.3122 | 4.5858 | 12.4694 | 14.2474 | 20.5595 | 25.1453 | 5.2758 | 7.1936 | 1.7226 | 1.778 | 3.0006 | 2.7405 | 6.3222 | 4.5858 | 12.4694 | 14.2474 | 20.5695 | 25.1553 | 0.01
6.2815 | 9.5774 | 1.9727 | 2.1802 | 3.5773 | 2.461 | 6.948 | 4.2175 | 15.8589 | 18.0391 | 24.987 | 29.2045 | 6.2815 | 9.5774 | 1.9727 | 2.1802 | 3.5773 | 2.461 | 6.958 | 4.2175 | 15.8589 | 18.0391 | 24.997 | 29.2145 | 0.01
5.1363 | 8.1952 | 1.8713 | 2.1317 | 0.96883 | 3.9987 | 7.4398 | 4.7008 | 13.3315 | 15.4633 | 22.9031 | 27.6039 | 5.1363 | 8.1952 | 1.8713 | 2.1317 | 0.96883 | 3.9987 | 7.4498 | 4.7008 | 13.3315 | 15.4633 | 22.9131 | 27.6139 | 0.01
5.4524 | 8.2531 | 2.1011 | 2.5704 | 2.2083 | 2.6285 | 6.6481 | 6.457 | 13.7055 | 16.2759 | 22.9241 | 29.3811 | 5.4524 | 8.2531 | 2.1011 | 2.5704 | 2.2083 | 2.6285 | 6.6581 | 6.457 | 13.7055 | 16.2759 | 22.9341 | 29.3911 | 0.01
6.4528 | 5.5818 | 2.0037 | 2.344 | 4.3525 | 2.5015 | 8.881 | 2.6429 | 12.0346 | 14.3786 | 23.2596 | 25.9025 | 6.4528 | 5.5818 | 2.0037 | 2.344 | 4.3525 | 2.5015 | 8.891 | 2.6429 | 12.0346 | 14.3786 | 23.2696 | 25.9125 | 0.01
5.883 | 9.1977 | 2.4749 | 2.0938 | 3.6354 | 1.9181 | 5.3453 | 4.2586 | 15.0807 | 17.1746 | 22.728 | 26.9867 | 5.883 | 9.1977 | 2.4749 | 2.0938 | 3.6354 | 1.9181 | 5.3553 | 4.2586 | 15.0807 | 17.1746 | 22.728 | 26.9867 | 0.01
5.4903 | 7.9111 | 1.9777 | 2.3305 | 3.6981 | 2.6209 | 9.1273 | 5.8091 | 13.4014 | 15.7319 | 24.8592 | 30.6684 | 5.4903 | 7.9111 | 1.9777 | 2.3305 | 3.6981 | 2.6209 | 9.1373 | 5.8091 | 13.4014 | 15.7319 | 24.8692 | 30.6784 | 0.01
5.4687 | 8.0487 | 2.1267 | 2.0757 | 4.6762 | 4.2479 | 7.7479 | 5.4188 | 13.5174 | 15.5931 | 24.5173 | 29.9361 | 5.4687 | 8.0487 | 2.1267 | 2.0757 | 4.6762 | 4.2479 | 7.7579 | 5.4188 | 13.5174 | 15.5931 | 24.5173 | 29.9361 | 0.01
5.7759 | 8.7607 | 1.7502 | 2.1956 | 4.0889 | 2.8247 | 7.1682 | 5.2375 | 14.5367 | 16.7322 | 23.9004 | 29.1379 | 5.7759 | 8.7607 | 1.7502 | 2.1956 | 4.0889 | 2.8247 | 7.1782 | 5.2375 | 14.5367 | 16.7322 | 23.9104 | 29.1479 | 0.01
6.3041 | 8.4878 | 1.7952 | 2.0604 | 2.637 | 3.3517 | 6.4239 | 5.5019 | 14.7919 | 16.8523 | 23.2762 | 28.7782 | 6.3041 | 8.4878 | 1.7952 | 2.0604 | 2.637 | 3.3517 | 6.4339 | 5.5019 | 14.7919 | 16.8523 | 23.2862 | 28.7882 | 0.01
6.8082 | 6.4677 | 2.0887 | 2.2969 | 3.1751 | 3.8488 | 8.1838 | 2.8851 | 13.2759 | 15.5728 | 23.7566 | 26.6418 | 6.8082 | 6.4677 | 2.0887 | 2.2969 | 3.1751 | 3.8488 | 8.1938 | 2.8851 | 13.2759 | 15.5728 | 23.7666 | 26.6518 | 0.01
6.5026 | 9.1742 | 1.8772 | 2.0314 | 2.2563 | 3.2184 | 7.255 | 4.8603 | 15.6768 | 17.7082 | 24.9632 | 29.8235 | 6.5026 | 9.1742 | 1.8772 | 2.0314 | 2.2563 | 3.2184 | 7.265 | 4.8603 | 15.6768 | 17.7082 | 24.9732 | 29.8335 | 0.01
5.6504 | 7.2432 | 1.7629 | 1.6508 | 3.5007 | 2.4392 | 7.134 | 5.952 | 12.8935 | 14.5443 | 21.6783 | 27.6304 | 5.6504 | 7.2432 | 1.7629 | 1.6508 | 3.5007 | 2.4392 | 7.144 | 5.952 | 12.8935 | 14.5443 | 21.6883 | 27.6404 | 0.01
6.1717 | 4.612 | 2.1949 | 1.9456 | 3.07 | 1.6565 | 6.8617 | 6.7028 | 10.7836 | 12.7292 | 19.5909 | 26.2938 | 6.1717 | 4.612 | 2.1949 | 1.9456 | 3.07 | 1.6565 | 6.8717 | 6.7028 | 10.7836 | 12.7292 | 19.6009 | 26.3038 | 0.01
5.3928 | 8.4637 | 2.1863 | 2.0179 | 2.1683 | 2.3169 | 6.4124 | 2.6622 | 13.8565 | 15.8744 | 22.2868 | 24.949 | 5.3928 | 8.4637 | 2.1863 | 2.0179 | 2.1683 | 2.3169 | 6.4224 | 2.6622 | 13.8565 | 15.8744 | 22.2968 | 24.959 | 0.01
6.5002 | 7.5206 | 1.7949 | 1.7776 | 3.113 | 3.1346 | 7.7932 | 6.9312 | 14.0208 | 15.7985 | 23.5917 | 30.5229 | 6.5002 | 7.5206 | 1.7949 | 1.7776 | 3.113 | 3.1346 | 7.8032 | 6.9312 | 14.0208 | 15.7985 | 23.6017 | 30.5329 | 0.01
6.6901 | 8.7164 | 2.0639 | 2.0272 | 2.0283 | 2.5374 | 4.9995 | 5.6117 | 15.4065 | 17.4338 | 22.4333 | 28.045 | 6.6901 | 8.7164 | 2.0639 | 2.0272 | 2.0283 | 2.5374 | 5.0095 | 5.6117 | 15.4065 | 17.4338 | 22.4433 | 28.055 | 0.01
6.2809 | 8.1285 | 1.8942 | 2.1076 | 3.3048 | 2.9695 | 7.5861 | 6.0299 | 14.4095 | 16.5171 | 24.1032 | 30.1331 | 6.2809 | 8.1285 | 1.8942 | 2.1076 | 3.3048 | 2.9695 | 7.5961 | 6.0299 | 14.4095 | 16.5171 | 24.1132 | 30.1431 | 0.01
6.0224 | 8.6119 | 1.7576 | 2.3395 | 1.2151 | 2.3427 | 4.1754 | 4.189 | 14.6344 | 16.9739 | 21.1493 | 25.3383 | 6.0224 | 8.6119 | 1.7576 | 2.3395 | 1.2151 | 2.3427 | 4.1854 | 4.189 | 14.6344 | 16.9739 | 21.1593 | 25.3483 | 0.01
6.2754 | 10.254 | 1.9216 | 1.7471 | 3.7113 | 3.2588 | 6.874 | 5.2057 | 16.5294 | 18.2765 | 25.2466 | 30.4523 | 6.2754 | 10.254 | 1.9216 | 1.7471 | 3.7113 | 3.2588 | 6.884 | 5.2057 | 16.5294 | 18.2765 | 25.2466 | 30.4523 | 0.01
5.9096 | 8.7623 | 2.0363 | 2.1573 | 2.1961 | 3.2393 | 7.7484 | 4.0912 | 14.6718 | 16.8292 | 24.5776 | 28.6688 | 5.9096 | 8.7623 | 2.0363 | 2.1573 | 2.1961 | 3.2393 | 7.7584 | 4.0912 | 14.6718 | 16.8292 | 24.5876 | 28.6788 | 0.01
5.4042 | 5.7302 | 2.1195 | 2.0684 | 3.9915 | 2.5163 | 5.6094 | 4.0096 | 11.1344 | 13.2028 | 19.7107 | 23.7203 | 5.4042 | 5.7302 | 2.1195 | 2.0684 | 3.9915 | 2.5163 | 5.6194 | 4.0096 | 11.1344 | 13.2028 | 19.7107 | 23.7203 | 0.01
5.4904 | 8.2777 | 1.974 | 2.1559 | 5.6154 | 3.3499 | 6.8167 | 5.1872 | 13.7681 | 15.924 | 24.8893 | 30.0766 | 5.4904 | 8.2777 | 1.974 | 2.1559 | 5.6154 | 3.3499 | 6.8267 | 5.1872 | 13.7681 | 15.924 | 24.8893 | 30.0766 | 0.01
5.6967 | 10.5556 | 1.8635 | 2.1401 | 5.3471 | 4.0662 | 6.2168 | 5.489 | 16.2523 | 18.3924 | 27.8056 | 33.2947 | 5.6967 | 10.5556 | 1.8635 | 2.1401 | 5.3471 | 4.0662 | 6.2268 | 5.489 | 16.2523 | 18.3924 | 27.8056 | 33.2947 | 0.01
5.7992 | 8.4907 | 2.2519 | 1.9177 | 2.6046 | 3.037 | 7.4918 | 3.8946 | 14.2899 | 16.2076 | 23.6994 | 27.594 | 5.7992 | 8.4907 | 2.2519 | 1.9177 | 2.6046 | 3.037 | 7.5018 | 3.8946 | 14.2899 | 16.2076 | 23.7094 | 27.604 | 0.01
5.7843 | 9.3999 | 1.9741 | 1.5458 | 3.1536 | 3.2418 | 8.4622 | 5.8054 | 15.1842 | 16.73 | 25.1922 | 30.9976 | 5.7843 | 9.3999 | 1.9741 | 1.5458 | 3.1536 | 3.2418 | 8.4722 | 5.8054 | 15.1842 | 16.73 | 25.2022 | 31.0076 | 0.01
5.7268 | 8.9296 | 2.2436 | 2.2322 | 3.4073 | 2.5919 | 7.754 | 4.9077 | 14.6564 | 16.8886 | 24.6426 | 29.5503 | 5.7268 | 8.9296 | 2.2436 | 2.2322 | 3.4073 | 2.5919 | 7.764 | 4.9077 | 14.6564 | 16.8886 | 24.6526 | 29.5603 | 0.01
6.3299 | 7.1876 | 1.4529 | 1.9538 | 4.1781 | 3.2746 | 4.5299 | 2.838 | 13.5174 | 15.4712 | 22.9239 | 25.7619 | 6.3299 | 7.1876 | 1.4529 | 1.9538 | 4.1781 | 3.2746 | 4.5399 | 2.838 | 13.5174 | 15.4712 | 22.9239 | 25.7619 | 0.01
6.9965 | 6.4335 | 2.0922 | 2.0163 | 4.7345 | 3.4743 | 7.4096 | 5.2564 | 13.4301 | 15.4463 | 23.6551 | 28.9115 | 6.9965 | 6.4335 | 2.0922 | 2.0163 | 4.7345 | 3.4743 | 7.4196 | 5.2564 | 13.4301 | 15.4463 | 23.6551 | 28.9115 | 0.01
6.5956 | 11.6238 | 1.7773 | 1.7293 | 1.866 | 3.4386 | 6.1777 | 4.697 | 18.2194 | 19.9488 | 26.1265 | 30.8236 | 6.5956 | 11.6238 | 1.7773 | 1.7293 | 1.866 | 3.4386 | 6.1877 | 4.697 | 18.2194 | 19.9488 | 26.1365 | 30.8336 | 0.01
5.8691 | 5.9867 | 1.8508 | 2.1716 | 5.2373 | 3.8608 | 9.1482 | 4.8409 | 11.8559 | 14.0275 | 23.1757 | 28.0166 | 5.8691 | 5.9867 | 1.8508 | 2.1716 | 5.2373 | 3.8608 | 9.1582 | 4.8409 | 11.8559 | 14.0275 | 23.1857 | 28.0266 | 0.01
5.5271 | 7.1007 | 1.935 | 1.8547 | 1.4964 | 3.0776 | 5.7444 | 5.5704 | 12.6278 | 14.4825 | 20.2269 | 25.7973 | 5.5271 | 7.1007 | 1.935 | 1.8547 | 1.4964 | 3.0776 | 5.7544 | 5.5704 | 12.6278 | 14.4825 | 20.2369 | 25.8073 | 0.01
4.8258 | 8.1021 | 2.1122 | 1.7224 | 1.5818 | 3.2397 | 7.6341 | 5.8908 | 12.9279 | 14.6503 | 22.2844 | 28.1751 | 4.8258 | 8.1021 | 2.1122 | 1.7224 | 1.5818 | 3.2397 | 7.6441 | 5.8908 | 12.9279 | 14.6503 | 22.2944 | 28.1851 | 0.01
5.2008 | 8.9826 | 2.0921 | 1.909 | 1.9538 | 2.0559 | 6.7931 | 6.2538 | 14.1835 | 16.0925 | 22.8856 | 29.1394 | 5.2008 | 8.9826 | 2.0921 | 1.909 | 1.9538 | 2.0559 | 6.8031 | 6.2538 | 14.1835 | 16.0925 | 22.8956 | 29.1494 | 0.01
5.9764 | 7.5876 | 1.9518 | 2.0769 | 3.1786 | 2.4948 | 9.3064 | 6.4196 | 13.564 | 15.6408 | 24.9472 | 31.3668 | 5.9764 | 7.5876 | 1.9518 | 2.0769 | 3.1786 | 2.4948 | 9.3164 | 6.4196 | 13.564 | 15.6408 | 24.9572 | 31.3768 | 0.01
6.4884 | 6.6338 | 1.7742 | 1.8573 | 1.4835 | 3.4029 | 6.6933 | 5.1369 | 13.1222 | 14.9796 | 21.6728 | 26.8098 | 6.4884 | 6.6338 | 1.7742 | 1.8573 | 1.4835 | 3.4029 | 6.7033 | 5.1369 | 13.1222 | 14.9796 | 21.6828 | 26.8198 | 0.01
5.3112 | 9.7657 | 1.9574 | 2.4485 | 3.895 | 3.153 | 5.6666 | 3.3638 | 15.077 | 17.5254 | 24.5734 | 27.9373 | 5.3112 | 9.7657 | 1.9574 | 2.4485 | 3.895 | 3.153 | 5.6766 | 3.3638 | 15.077 | 17.5254 | 24.5734 | 27.9373 | 0.01
6.3243 | 7.9564 | 1.7785 | 2.0864 | 3.8702 | 3.449 | 6.9283 | 8.0402 | 14.2807 | 16.3671 | 23.6863 | 31.7266 | 6.3243 | 7.9564 | 1.7785 | 2.0864 | 3.8702 | 3.449 | 6.9383 | 8.0402 | 14.2807 | 16.3671 | 23.6863 | 31.7266 | 0.01
6.2676 | 7.3767 | 2.233 | 1.4658 | 3.7998 | 3.7779 | 7.4161 | 5.9786 | 13.6443 | 15.1101 | 22.6877 | 28.6663 | 6.2676 | 7.3767 | 2.233 | 1.4658 | 3.7998 | 3.7779 | 7.4261 | 5.9786 | 13.6443 | 15.1101 | 22.6877 | 28.6663 | 0.01
6.53 | 6.7791 | 2.0289 | 2.1804 | 2.7472 | 3.139 | 6.1327 | 7.6836 | 13.3092 | 15.4896 | 21.6223 | 29.3059 | 6.53 | 6.7791 | 2.0289 | 2.1804 | 2.7472 | 3.139 | 6.1427 | 7.6836 | 13.3092 | 15.4896 | 21.6323 | 29.3159 | 0.01
5.6807 | 6.0848 | 1.9795 | 1.7403 | 1.7559 | 3.384 | 6.3425 | 5.5195 | 11.7655 | 13.5058 | 19.8484 | 25.3679 | 5.6807 | 6.0848 | 1.9795 | 1.7403 | 1.7559 | 3.384 | 6.3525 | 5.5195 | 11.7655 | 13.5058 | 19.8584 | 25.3779 | 0.01
6.0991 | 10.1005 | 1.9566 | 1.9543 | 2.345 | 3.5215 | 8.12 | 4.1362 | 16.1996 | 18.1539 | 26.2739 | 30.4101 | 6.0991 | 10.1005 | 1.9566 | 1.9543 | 2.345 | 3.5215 | 8.13 | 4.1362 | 16.1996 | 18.1539 | 26.2839 | 30.4201 | 0.01
6.4478 | 6.8334 | 2.0658 | 2.0119 | 3.8659 | 2.2584 | 8.3787 | 8.6367 | 13.2812 | 15.2931 | 23.6718 | 32.3085 | 6.4478 | 6.8334 | 2.0658 | 2.0119 | 3.8659 | 2.2584 | 8.3887 | 8.6367 | 13.2812 | 15.2931 | 23.6818 | 32.3185 | 0.01
5.0188 | 8.5753 | 1.6974 | 1.559 | 2.293 | 2.1171 | 7.5094 | 6.7076 | 13.5941 | 15.1532 | 22.6626 | 29.3702 | 5.0188 | 8.5753 | 1.6974 | 1.559 | 2.293 | 2.1171 | 7.5194 | 6.7076 | 13.5941 | 15.1532 | 22.6726 | 29.3802 | 0.01
5.5349 | 8.7056 | 1.6803 | 2.337 | 4.5759 | 3.9221 | 7.3215 | 3.82 | 14.2405 | 16.5775 | 25.0755 | 28.8955 | 5.5349 | 8.7056 | 1.6803 | 2.337 | 4.5759 | 3.9221 | 7.3315 | 3.82 | 14.2405 | 16.5775 | 25.0755 | 28.8955 | 0.01
5.2296 | 7.4586 | 1.7009 | 1.6699 | 3.1575 | 3.0475 | 6.1343 | 7.0699 | 12.6883 | 14.3582 | 20.5632 | 27.6331 | 5.2296 | 7.4586 | 1.7009 | 1.6699 | 3.1575 | 3.0475 | 6.1443 | 7.0699 | 12.6883 | 14.3582 | 20.5632 | 27.6331 | 0.01
6.1677 | 6.0429 | 2.328 | 2.1524 | 3.9008 | 2.6657 | 8.7853 | 6.3874 | 12.2106 | 14.363 | 23.1484 | 29.5357 | 6.1677 | 6.0429 | 2.328 | 2.1524 | 3.9008 | 2.6657 | 8.7953 | 6.3874 | 12.2106 | 14.363 | 23.1584 | 29.5457 | 0.01
5.5049 | 11.1891 | 1.9754 | 1.9365 | 2.5287 | 3.0434 | 6.8104 | 3.8224 | 16.694 | 18.6305 | 25.4409 | 29.2633 | 5.5049 | 11.1891 | 1.9754 | 1.9365 | 2.5287 | 3.0434 | 6.8204 | 3.8224 | 16.694 | 18.6305 | 25.4509 | 29.2733 | 0.01
6.5012 | 7.7978 | 1.8868 | 1.6845 | 3.5426 | 2.8388 | 8.2592 | 6.0839 | 14.299 | 15.9834 | 24.2427 | 30.3266 | 6.5012 | 7.7978 | 1.8868 | 1.6845 | 3.5426 | 2.8388 | 8.2692 | 6.0839 | 14.299 | 15.9834 | 24.2527 | 30.3366 | 0.01
5.2923 | 7.1753 | 2.2752 | 1.9999 | 2.4827 | 2.4493 | 7.4657 | 6.4439 | 12.4677 | 14.4675 | 21.9333 | 28.3771 | 5.2923 | 7.1753 | 2.2752 | 1.9999 | 2.4827 | 2.4493 | 7.4757 | 6.4439 | 12.4677 | 14.4675 | 21.9433 | 28.3871 | 0.01
6.2308 | 7.2989 | 2.0871 | 2.0845 | 2.7538 | 3.4354 | 9.9903 | 4.6008 | 13.5297 | 15.6142 | 25.6045 | 30.2053 | 6.2308 | 7.2989 | 2.0871 | 2.0845 | 2.7538 | 3.4354 | 10.0003 | 4.6008 | 13.5297 | 15.6142 | 25.6145 | 30.2153 | 0.01
6.2856 | 6.9838 | 2.2065 | 2.3131 | 2.846 | 2.8832 | 7.5112 | 2.1849 | 13.2694 | 15.5824 | 23.0937 | 25.2786 | 6.2856 | 6.9838 | 2.2065 | 2.3131 | 2.846 | 2.8832 | 7.5212 | 2.1849 | 13.2694 | 15.5824 | 23.1037 | 25.2886 | 0.01
6.7467 | 7.2644 | 1.944 | 2.112 | 3.877 | 4.1403 | 6.7459 | 6.1108 | 14.0111 | 16.1231 | 24.1403 | 30.2511 | 6.7467 | 7.2644 | 1.944 | 2.112 | 3.877 | 4.1403 | 6.7559 | 6.1108 | 14.0111 | 16.1231 | 24.1403 | 30.2511 | 0.01
5.6456 | 7.6805 | 2.183 | 2.0014 | 2.4484 | 4.0625 | 6.7304 | 5.4871 | 13.3261 | 15.3276 | 22.058 | 27.5452 | 5.6456 | 7.6805 | 2.183 | 2.0014 | 2.4484 | 4.0625 | 6.7404 | 5.4871 | 13.3261 | 15.3276 | 22.068 | 27.5552 | 0.01
6.3952 | 6.2894 | 2.3836 | 1.8913 | 2.9362 | 1.4207 | 7.6051 | 4.7357 | 12.6847 | 14.576 | 22.181 | 26.9167 | 6.3952 | 6.2894 | 2.3836 | 1.8913 | 2.9362 | 1.4207 | 7.6151 | 4.7357 | 12.6847 | 14.576 | 22.191 | 26.9267 | 0.01
7.325 | 7.5286 | 2.2441 | 2.0692 | 2.5322 | 3.1077 | 7.5036 | 5.3563 | 14.8536 | 16.9228 | 24.4263 | 29.7827 | 7.325 | 7.5286 | 2.2441 | 2.0692 | 2.5322 | 3.1077 | 7.5136 | 5.3563 | 14.8536 | 16.9228 | 24.4363 | 29.7927 | 0.01
5.7188 | 8.5116 | 1.9539 | 2.1994 | 2.3608 | 2.1521 | 6.2669 | 4.5304 | 14.2304 | 16.4298 | 22.6967 | 27.2271 | 5.7188 | 8.5116 | 1.9539 | 2.1994 | 2.3608 | 2.1521 | 6.2769 | 4.5304 | 14.2304 | 16.4298 | 22.7067 | 27.2371 | 0.01
6.2767 | 8.6947 | 1.9306 | 1.9513 | 2.99 | 3.0802 | 5.7814 | 4.6075 | 14.9714 | 16.9226 | 22.9928 | 27.6003 | 6.2767 | 8.6947 | 1.9306 | 1.9513 | 2.99 | 3.0802 | 5.7914 | 4.6075 | 14.9714 | 16.9226 | 22.9928 | 27.6003 | 0.01
5.906 | 8.534 | 1.9903 | 1.8015 | 3.3599 | 3.4458 | 9.3079 | 4.7313 | 14.44 | 16.2415 | 25.5494 | 30.2807 | 5.906 | 8.534 | 1.9903 | 1.8015 | 3.3599 | 3.4458 | 9.3179 | 4.7313 | 14.44 | 16.2415 | 25.5594 | 30.2907 | 0.01
5.8974 | 7.0859 | 1.742 | 2.0691 | 1.6396 | 3.4974 | 6.1957 | 3.8461 | 12.9833 | 15.0525 | 21.2482 | 25.0942 | 5.8974 | 7.0859 | 1.742 | 2.0691 | 1.6396 | 3.4974 | 6.2057 | 3.8461 | 12.9833 | 15.0525 | 21.2582 | 25.1042 | 0.01
6.493 | 7.4461 | 1.747 | 1.8934 | 2.5664 | 2.8059 | 7.7276 | 3.7034 | 13.9391 | 15.8325 | 23.5601 | 27.2635 | 6.493 | 7.4461 | 1.747 | 1.8934 | 2.5664 | 2.8059 | 7.7376 | 3.7034 | 13.9391 | 15.8325 | 23.5701 | 27.2735 | 0.01
6.2531 | 7.919 | 2.1269 | 2.1822 | 3.4403 | 2.2746 | 6.2503 | 4.6727 | 14.1722 | 16.3544 | 22.6047 | 27.2774 | 6.2531 | 7.919 | 2.1269 | 2.1822 | 3.4403 | 2.2746 | 6.2603 | 4.6727 | 14.1722 | 16.3544 | 22.6147 | 27.2874 | 0.01
6.3387 | 7.9052 | 2.1202 | 1.4472 | 2.8783 | 3.3144 | 3.2617 | 6.9574 | 14.2438 | 15.691 | 21.8837 | 28.8412 | 6.3387 | 7.9052 | 2.1202 | 1.4472 | 2.8783 | 3.3144 | 3.2717 | 6.9574 | 14.2438 | 15.691 | 21.8837 | 28.8412 | 0.01
6.0232 | 8.6301 | 1.7241 | 1.6008 | 2.0507 | 2.792 | 8.7893 | 4.651 | 14.6533 | 16.2541 | 25.0434 | 29.6945 | 6.0232 | 8.6301 | 1.7241 | 1.6008 | 2.0507 | 2.792 | 8.7993 | 4.651 | 14.6533 | 16.2541 | 25.0534 | 29.7045 | 0.01
7.1944 | 8.2673 | 2.0189 | 2.4444 | 4.9431 | 2.0821 | 8.5186 | 3.5893 | 15.4618 | 17.9062 | 26.4248 | 30.0141 | 7.1944 | 8.2673 | 2.0189 | 2.4444 | 4.9431 | 2.0821 | 8.5286 | 3.5893 | 15.4618 | 17.9062 | 26.4348 | 30.0241 | 0.01
5.7221 | 7.4246 | 2.0457 | 1.5488 | 3.5796 | 2.9964 | 5.5972 | 3.9832 | 13.1467 | 14.6955 | 21.2715 | 25.2547 | 5.7221 | 7.4246 | 2.0457 | 1.5488 | 3.5796 | 2.9964 | 5.6072 | 3.9832 | 13.1467 | 14.6955 | 21.2715 | 25.2547 | 0.01
6.1793 | 6.4484 | 2.1067 | 1.6139 | 2.7697 | 2.6528 | 4.8434 | 4.5898 | 12.6278 | 14.2417 | 19.6642 | 24.254 | 6.1793 | 6.4484 | 2.1067 | 1.6139 | 2.7697 | 2.6528 | 4.8534 | 4.5898 | 12.6278 | 14.2417 | 19.6642 | 24.254 | 0.01
6.2924 | 6.7575 | 2.0068 | 2.6826 | 4.3508 | 2.3233 | 7.4014 | 4.7262 | 13.0499 | 15.7325 | 23.1339 | 27.8601 | 6.2924 | 6.7575 | 2.0068 | 2.6826 | 4.3508 | 2.3233 | 7.4114 | 4.7262 | 13.0499 | 15.7325 | 23.1439 | 27.8701 | 0.01
5.6159 | 8.8687 | 1.8679 | 2.4622 | 1.9369 | 2.2257 | 5.0532 | 6.3299 | 14.4846 | 16.9468 | 22.0001 | 28.3299 | 5.6159 | 8.8687 | 1.8679 | 2.4622 | 1.9369 | 2.2257 | 5.0632 | 6.3299 | 14.4846 | 16.9468 | 22.0101 | 28.3399 | 0.01
6.367 | 7.4874 | 1.8 | 2.6974 | 2.6162 | 3.5336 | 7.1678 | 5.1579 | 13.8544 | 16.5519 | 23.7197 | 28.8776 | 6.367 | 7.4874 | 1.8 | 2.6974 | 2.6162 | 3.5336 | 7.1778 | 5.1579 | 13.8544 | 16.5519 | 23.7297 | 28.8876 | 0.01
6.2087 | 7.684 | 2.0682 | 1.8975 | 1.9481 | 3.5534 | 6.7233 | 4.6339 | 13.8927 | 15.7902 | 22.5135 | 27.1474 | 6.2087 | 7.684 | 2.0682 | 1.8975 | 1.9481 | 3.5534 | 6.7333 | 4.6339 | 13.8927 | 15.7902 | 22.5235 | 27.1574 | 0.01
6.5676 | 8.3536 | 1.9713 | 1.9558 | 3.3362 | 3.4888 | 7.5053 | 5.2437 | 14.9212 | 16.8769 | 24.3822 | 29.6259 | 6.5676 | 8.3536 | 1.9713 | 1.9558 | 3.3362 | 3.4888 | 7.5153 | 5.2437 | 14.9212 | 16.8769 | 24.3922 | 29.6359 | 0.01
5.966 | 8.2201 | 1.9617 | 2.1647 | 3.5123 | 1.841 | 6.5668 | 4.6923 | 14.1861 | 16.3507 | 22.9175 | 27.6098 | 5.966 | 8.2201 | 1.9617 | 2.1647 | 3.5123 | 1.841 | 6.5768 | 4.6923 | 14.1861 | 16.3507 | 22.9275 | 27.6198 | 0.01
5.9667 | 7.6492 | 1.9597 | 2.0882 | 1.1133 | 4.1981 | 7.9566 | 5.9069 | 13.6158 | 15.704 | 23.6606 | 29.5676 | 5.9667 | 7.6492 | 1.9597 | 2.0882 | 1.1133 | 4.1981 | 7.9666 | 5.9069 | 13.6158 | 15.704 | 23.6706 | 29.5776 | 0.01
5.6069 | 5.8409 | 2.0566 | 2.1697 | 3.504 | 2.8354 | 5.5354 | 4.6458 | 11.4478 | 13.6175 | 19.9568 | 24.6026 | 5.6069 | 5.8409 | 2.0566 | 2.1697 | 3.504 | 2.8354 | 5.5454 | 4.6458 | 11.4478 | 13.6175 | 19.9568 | 24.6026 | 0.01
5.5008 | 7.7435 | 1.4959 | 2.0948 | 2.9449 | 2.431 | 9.5824 | 3.7489 | 13.2443 | 15.3391 | 24.9215 | 28.6703 | 5.5008 | 7.7435 | 1.4959 | 2.0948 | 2.9449 | 2.431 | 9.5924 | 3.7489 | 13.2443 | 15.3391 | 24.9315 | 28.6803 | 0.01
5.3952 | 8.227 | 2.2505 | 2.2325 | 5.3556 | 3.4945 | 6.2645 | 3.8491 | 13.6223 | 15.8548 | 24.7049 | 28.554 | 5.3952 | 8.227 | 2.2505 | 2.2325 | 5.3556 | 3.4945 | 6.2745 | 3.8491 | 13.6223 | 15.8548 | 24.7049 | 28.554 | 0.01
5.9988 | 10.7004 | 2.0394 | 2.1086 | 3.7361 | 2.8994 | 7.7945 | 4.7071 | 16.6992 | 18.8078 | 26.6023 | 31.3094 | 5.9988 | 10.7004 | 2.0394 | 2.1086 | 3.7361 | 2.8994 | 7.8045 | 4.7071 | 16.6992 | 18.8078 | 26.6123 | 31.3194 | 0.01
6.155 | 8.7185 | 1.8839 | 2.0741 | 2.2292 | 2.6908 | 7.8313 | 5.3023 | 14.8736 | 16.9476 | 24.779 | 30.0813 | 6.155 | 8.7185 | 1.8839 | 2.0741 | 2.2292 | 2.6908 | 7.8413 | 5.3023 | 14.8736 | 16.9476 | 24.789 | 30.0913 | 0.01
5.4334 | 8.168 | 1.5209 | 1.4061 | 3.8407 | 3.7807 | 4.2828 | 4.8528 | 13.6014 | 15.0074 | 22.6289 | 27.4817 | 5.4334 | 8.168 | 1.5209 | 1.4061 | 3.8407 | 3.7807 | 4.2928 | 4.8528 | 13.6014 | 15.0074 | 22.6289 | 27.4817 | 0.01
6.0257 | 8.6265 | 2.0194 | 2.1049 | 4.2002 | 2.6541 | 8.6046 | 5.4868 | 14.6523 | 16.7571 | 25.3618 | 30.8486 | 6.0257 | 8.6265 | 2.0194 | 2.1049 | 4.2002 | 2.6541 | 8.6146 | 5.4868 | 14.6523 | 16.7571 | 25.3718 | 30.8586 | 0.01
6.3783 | 8.2725 | 2.0759 | 1.8358 | 3.8131 | 3.2863 | 9.5905 | 2.4012 | 14.6509 | 16.4866 | 26.0771 | 28.4783 | 6.3783 | 8.2725 | 2.0759 | 1.8358 | 3.8131 | 3.2863 | 9.6005 | 2.4012 | 14.6509 | 16.4866 | 26.0871 | 28.4883 | 0.01
6.0875 | 8.5637 | 1.8325 | 2.2939 | 2.108 | 2.3521 | 7.2938 | 5.7301 | 14.6512 | 16.9452 | 24.239 | 29.9691 | 6.0875 | 8.5637 | 1.8325 | 2.2939 | 2.108 | 2.3521 | 7.3038 | 5.7301 | 14.6512 | 16.9452 | 24.249 | 29.9791 | 0.01
5.923 | 8.1703 | 1.9761 | 1.7441 | 2.6118 | 2.9541 | 7.3145 | 5.2439 | 14.0933 | 15.8375 | 23.1519 | 28.3958 | 5.923 | 8.1703 | 1.9761 | 1.7441 | 2.6118 | 2.9541 | 7.3245 | 5.2439 | 14.0933 | 15.8375 | 23.1619 | 28.4058 | 0.01
6.5638 | 8.1999 | 2.1703 | 1.534 | 2.3287 | 3.5945 | 7.3548 | 4.9853 | 14.7638 | 16.2978 | 23.6526 | 28.6379 | 6.5638 | 8.1999 | 2.1703 | 1.534 | 2.3287 | 3.5945 | 7.3648 | 4.9853 | 14.7638 | 16.2978 | 23.6626 | 28.6479 | 0.01
6.2735 | 9.1635 | 1.9635 | 1.8924 | 3.233 | 3.4785 | 5.2403 | 4.9982 | 15.437 | 17.3294 | 24.0409 | 29.0391 | 6.2735 | 9.1635 | 1.9635 | 1.8924 | 3.233 | 3.4785 | 5.2503 | 4.9982 | 15.437 | 17.3294 | 24.0409 | 29.0391 | 0.01
5.6609 | 9.7543 | 1.6919 | 1.6464 | 2.3937 | 3.7064 | 6.8128 | 4.24 | 15.4152 | 17.0615 | 23.8743 | 28.1143 | 5.6609 | 9.7543 | 1.6919 | 1.6464 | 2.3937 | 3.7064 | 6.8228 | 4.24 | 15.4152 | 17.0615 | 23.8843 | 28.1243 | 0.01
5.4288 | 7.8471 | 2.0121 | 1.9106 | 1.6356 | 4.0555 | 6.8961 | 3.3009 | 13.276 | 15.1866 | 22.0827 | 25.3836 | 5.4288 | 7.8471 | 2.0121 | 1.9106 | 1.6356 | 4.0555 | 6.9061 | 3.3009 | 13.276 | 15.1866 | 22.0927 | 25.3936 | 0.01
5.6823 | 8.3965 | 2.2273 | 2.4142 | 3.491 | 3.1861 | 7.5359 | 5.0056 | 14.0788 | 16.493 | 24.0289 | 29.0344 | 5.6823 | 8.3965 | 2.2273 | 2.4142 | 3.491 | 3.1861 | 7.5459 | 5.0056 | 14.0788 | 16.493 | 24.0389 | 29.0444 | 0.01
5.6666 | 7.5959 | 2.0687 | 2.8277 | 2.8202 | 2.9899 | 5.317 | 5.1753 | 13.2625 | 16.0902 | 21.9003 | 27.0756 | 5.6666 | 7.5959 | 2.0687 | 2.8277 | 2.8202 | 2.9899 | 5.327 | 5.1753 | 13.2625 | 16.0902 | 21.9003 | 27.0756 | 0.01
6.0597 | 9.8857 | 1.9465 | 1.7977 | 1.1232 | 2.3367 | 5.0749 | 3.5318 | 15.9454 | 17.7431 | 22.8179 | 26.3497 | 6.0597 | 9.8857 | 1.9465 | 1.7977 | 1.1232 | 2.3367 | 5.0849 | 3.5318 | 15.9454 | 17.7431 | 22.8279 | 26.3597 | 0.01
6.125 | 8.0668 | 1.7114 | 2.3667 | 4.1259 | 2.9758 | 5.0819 | 5.5863 | 14.1918 | 16.5586 | 23.6603 | 29.2466 | 6.125 | 8.0668 | 1.7114 | 2.3667 | 4.1259 | 2.9758 | 5.0919 | 5.5863 | 14.1918 | 16.5586 | 23.6603 | 29.2466 | 0.01
5.4467 | 7.6515 | 1.9227 | 2.0956 | 3.2003 | 4.5453 | 5.5645 | 5.1808 | 13.0982 | 15.1938 | 22.9394 | 28.1202 | 5.4467 | 7.6515 | 1.9227 | 2.0956 | 3.2003 | 4.5453 | 5.5745 | 5.1808 | 13.0982 | 15.1938 | 22.9394 | 28.1202 | 0.01
5.8435 | 6.8204 | 1.9945 | 1.9366 | 3.7767 | 2.3737 | 8.7015 | 5.6817 | 12.6639 | 14.6005 | 23.302 | 28.9837 | 5.8435 | 6.8204 | 1.9945 | 1.9366 | 3.7767 | 2.3737 | 8.7115 | 5.6817 | 12.6639 | 14.6005 | 23.312 | 28.9937 | 0.01
6.2889 | 10.2967 | 2.3247 | 2.1326 | 3.3557 | 1.9117 | 5.5737 | 5.5869 | 16.5856 | 18.7182 | 24.292 | 29.8789 | 6.2889 | 10.2967 | 2.3247 | 2.1326 | 3.3557 | 1.9117 | 5.5837 | 5.5869 | 16.5856 | 18.7182 | 24.302 | 29.8889 | 0.01
6.154 | 8.276 | 1.7722 | 2.1141 | 3.884 | 3.1805 | 5.4921 | 5.5945 | 14.43 | 16.544 | 23.6085 | 29.203 | 6.154 | 8.276 | 1.7722 | 2.1141 | 3.884 | 3.1805 | 5.5021 | 5.5945 | 14.43 | 16.544 | 23.6085 | 29.203 | 0.01
5.4384 | 6.7605 | 2.2164 | 1.6397 | 1.9555 | 3.4853 | 7.9481 | 5.7043 | 12.1988 | 13.8386 | 21.7866 | 27.4909 | 5.4384 | 6.7605 | 2.2164 | 1.6397 | 1.9555 | 3.4853 | 7.9581 | 5.7043 | 12.1988 | 13.8386 | 21.7966 | 27.5009 | 0.01
4.2856 | 8.1391 | 2.0144 | 1.6973 | 3.8453 | 2.0136 | 6.2616 | 5.3575 | 12.4248 | 14.1221 | 20.3837 | 25.7412 | 4.2856 | 8.1391 | 2.0144 | 1.6973 | 3.8453 | 2.0136 | 6.2716 | 5.3575 | 12.4248 | 14.1221 | 20.3937 | 25.7512 | 0.01
6.5756 | 5.8862 | 1.935 | 1.8348 | 3.4596 | 3.5227 | 6.5002 | 3.7247 | 12.4618 | 14.2965 | 21.2789 | 25.0036 | 6.5756 | 5.8862 | 1.935 | 1.8348 | 3.4596 | 3.5227 | 6.5102 | 3.7247 | 12.4618 | 14.2965 | 21.2789 | 25.0036 | 0.01
4.9829 | 6.2308 | 1.9708 | 2.3158 | 3.2005 | 3.5613 | 5.6867 | 6.328 | 11.2136 | 13.5294 | 20.2913 | 26.6192 | 4.9829 | 6.2308 | 1.9708 | 2.3158 | 3.2005 | 3.5613 | 5.6967 | 6.328 | 11.2136 | 13.5294 | 20.2913 | 26.6192 | 0.01
6.7414 | 7.8861 | 1.9931 | 2.0273 | 3.4578 | 3.3156 | 5.7585 | 4.8761 | 14.6276 | 16.6549 | 23.4283 | 28.3044 | 6.7414 | 7.8861 | 1.9931 | 2.0273 | 3.4578 | 3.3156 | 5.7685 | 4.8761 | 14.6276 | 16.6549 | 23.4283 | 28.3044 | 0.01
6.1741 | 9.4512 | 2.2932 | 1.5536 | 2.4334 | 2.8384 | 8.496 | 6.5908 | 15.6253 | 17.1789 | 25.6749 | 32.2657 | 6.1741 | 9.4512 | 2.2932 | 1.5536 | 2.4334 | 2.8384 | 8.506 | 6.5908 | 15.6253 | 17.1789 | 25.6849 | 32.2757 | 0.01
7.2467 | 8.2927 | 1.9398 | 1.6944 | 2.5381 | 3.0888 | 4.892 | 6.3367 | 15.5394 | 17.2338 | 22.8608 | 29.1974 | 7.2467 | 8.2927 | 1.9398 | 1.6944 | 2.5381 | 3.0888 | 4.902 | 6.3367 | 15.5394 | 17.2338 | 22.8608 | 29.1974 | 0.01
6.5306 | 8.0314 | 2.0853 | 1.5906 | 2.8208 | 2.5396 | 8.7317 | 5.3091 | 14.562 | 16.1526 | 24.8843 | 30.1934 | 6.5306 | 8.0314 | 2.0853 | 1.5906 | 2.8208 | 2.5396 | 8.7417 | 5.3091 | 14.562 | 16.1526 | 24.8943 | 30.2034 | 0.01
5.8807 | 7.5946 | 1.9675 | 2.0111 | 3.0869 | 3.1283 | 7.226 | 4.895 | 13.4753 | 15.4864 | 22.7125 | 27.6075 | 5.8807 | 7.5946 | 1.9675 | 2.0111 | 3.0869 | 3.1283 | 7.236 | 4.895 | 13.4753 | 15.4864 | 22.7225 | 27.6175 | 0.01
5.2337 | 8.827 | 1.7614 | 2.1384 | 2.2003 | 2.9562 | 9.5328 | 4.8558 | 14.0607 | 16.1991 | 25.7319 | 30.5876 | 5.2337 | 8.827 | 1.7614 | 2.1384 | 2.2003 | 2.9562 | 9.5428 | 4.8558 | 14.0607 | 16.1991 | 25.7419 | 30.5976 | 0.01
6.1556 | 8.7059 | 1.6315 | 2.5886 | 4.163 | 2.682 | 9.419 | 6.7547 | 14.8615 | 17.4501 | 26.8691 | 33.6238 | 6.1556 | 8.7059 | 1.6315 | 2.5886 | 4.163 | 2.682 | 9.429 | 6.7547 | 14.8615 | 17.4501 | 26.8791 | 33.6338 | 0.01
6.4745 | 7.4294 | 1.7456 | 2.2832 | 2.3076 | 3.1798 | 6.611 | 3.9039 | 13.9039 | 16.1871 | 22.7981 | 26.702 | 6.4745 | 7.4294 | 1.7456 | 2.2832 | 2.3076 | 3.1798 | 6.621 | 3.9039 | 13.9039 | 16.1871 | 22.8081 | 26.712 | 0.01
6.4017 | 7.4503 | 2.2136 | 1.7763 | 2.0977 | 4.2015 | 6.6077 | 6.5882 | 13.852 | 15.6283 | 22.236 | 28.8242 | 6.4017 | 7.4503 | 2.2136 | 1.7763 | 2.0977 | 4.2015 | 6.6177 | 6.5882 | 13.852 | 15.6283 | 22.246 | 28.8342 | 0.01
5.213 | 9.0086 | 2.3436 | 1.5805 | 2.633 | 2.6432 | 9.2504 | 3.9957 | 14.2217 | 15.8022 | 25.0526 | 29.0483 | 5.213 | 9.0086 | 2.3436 | 1.5805 | 2.633 | 2.6432 | 9.2604 | 3.9957 | 14.2217 | 15.8022 | 25.0626 | 29.0583 | 0.01
6.0468 | 7.2173 | 1.8938 | 1.5693 | 1.2245 | 3.3996 | 6.8072 | 5.3685 | 13.2642 | 14.8334 | 21.6406 | 27.0092 | 6.0468 | 7.2173 | 1.8938 | 1.5693 | 1.2245 | 3.3996 | 6.8172 | 5.3685 | 13.2642 | 14.8334 | 21.6506 | 27.0192 | 0.01
6.4092 | 6.7677 | 2.0692 | 2.228 | 2.6709 | 2.5629 | 8.5503 | 5.9469 | 13.1769 | 15.4049 | 23.9553 | 29.9022 | 6.4092 | 6.7677 | 2.0692 | 2.228 | 2.6709 | 2.5629 | 8.5603 | 5.9469 | 13.1769 | 15.4049 | 23.9653 | 29.9122 | 0.01
5.3197 | 7.2432 | 1.8329 | 1.5887 | 3.8505 | 3.1091 | 6.3825 | 5.1281 | 12.5628 | 14.1515 | 21.1112 | 26.2392 | 5.3197 | 7.2432 | 1.8329 | 1.5887 | 3.8505 | 3.1091 | 6.3925 | 5.1281 | 12.5628 | 14.1515 | 21.1112 | 26.2392 | 0.01
5.9842 | 7.1586 | 1.8907 | 1.4429 | 1.1948 | 2.4477 | 7.7291 | 4.9011 | 13.1428 | 14.5857 | 22.3148 | 27.2159 | 5.9842 | 7.1586 | 1.8907 | 1.4429 | 1.1948 | 2.4477 | 7.7391 | 4.9011 | 13.1428 | 14.5857 | 22.3248 | 27.2259 | 0.01
6.1706 | 8.9717 | 2.0352 | 2.2051 | 3.8236 | 3.9803 | 2.7596 | 5.8286 | 15.1423 | 17.3474 | 25.1513 | 30.9798 | 6.1706 | 8.9717 | 2.0352 | 2.2051 | 3.8236 | 3.9803 | 2.7696 | 5.8286 | 15.1423 | 17.3474 | 25.1513 | 30.9798 | 0.01
5.2578 | 7.2976 | 2.192 | 2.3371 | 3.0492 | 4.3544 | 4.6026 | 4.1687 | 12.5554 | 14.8925 | 22.2962 | 26.4649 | 5.2578 | 7.2976 | 2.192 | 2.3371 | 3.0492 | 4.3544 | 4.6126 | 4.1687 | 12.5554 | 14.8925 | 22.2962 | 26.4649 | 0.01
5.1953 | 9.1103 | 1.6475 | 1.8355 | 3.5295 | 4.0921 | 5.7633 | 5.3112 | 14.3056 | 16.1411 | 23.7628 | 29.074 | 5.1953 | 9.1103 | 1.6475 | 1.8355 | 3.5295 | 4.0921 | 5.7733 | 5.3112 | 14.3056 | 16.1411 | 23.7628 | 29.074 | 0.01
5.0297 | 8.906 | 1.7596 | 1.9009 | 2.9802 | 3.5388 | 6.6491 | 6.526 | 13.9357 | 15.8366 | 22.4857 | 29.0117 | 5.0297 | 8.906 | 1.7596 | 1.9009 | 2.9802 | 3.5388 | 6.6591 | 6.526 | 13.9357 | 15.8366 | 22.4957 | 29.0217 | 0.01
7.214 | 9.2998 | 1.8752 | 2.085 | 2.7298 | 2.5248 | 7.4418 | 6.2894 | 16.5138 | 18.5988 | 26.0406 | 32.33 | 7.214 | 9.2998 | 1.8752 | 2.085 | 2.7298 | 2.5248 | 7.4518 | 6.2894 | 16.5138 | 18.5988 | 26.0506 | 32.34 | 0.01
6.2099 | 6.2944 | 2.1367 | 1.9328 | 3.06 | 3.4719 | 7.8888 | 3.1048 | 12.5043 | 14.4371 | 22.3259 | 25.4307 | 6.2099 | 6.2944 | 2.1367 | 1.9328 | 3.06 | 3.4719 | 7.8988 | 3.1048 | 12.5043 | 14.4371 | 22.3359 | 25.4407 | 0.01
5.5403 | 7.2878 | 2.1262 | 1.5789 | 2.0584 | 2.9136 | 5.5119 | 6.2379 | 12.8282 | 14.4071 | 19.919 | 26.1569 | 5.5403 | 7.2878 | 2.1262 | 1.5789 | 2.0584 | 2.9136 | 5.5219 | 6.2379 | 12.8282 | 14.4071 | 19.929 | 26.1669 | 0.01
6.302 | 9.6632 | 1.799 | 1.9699 | 4.8894 | 3.6457 | 5.7372 | 6.798 | 15.9652 | 17.9351 | 26.4701 | 33.2682 | 6.302 | 9.6632 | 1.799 | 1.9699 | 4.8894 | 3.6457 | 5.7472 | 6.798 | 15.9652 | 17.9351 | 26.4701 | 33.2682 | 0.01
5.8248 | 8.9335 | 1.8201 | 2.3644 | 2.3024 | 2.9118 | 7.524 | 6.8769 | 14.7583 | 17.1227 | 24.6467 | 31.5236 | 5.8248 | 8.9335 | 1.8201 | 2.3644 | 2.3024 | 2.9118 | 7.534 | 6.8769 | 14.7583 | 17.1227 | 24.6567 | 31.5336 | 0.01
5.3641 | 8.9021 | 2.0096 | 1.7732 | 2.2735 | 3.2767 | 6.3647 | 5.7025 | 14.2661 | 16.0393 | 22.404 | 28.1065 | 5.3641 | 8.9021 | 2.0096 | 1.7732 | 2.2735 | 3.2767 | 6.3747 | 5.7025 | 14.2661 | 16.0393 | 22.414 | 28.1165 | 0.01
5.8471 | 8.2862 | 2.2599 | 2.3638 | 4.5324 | 2.1749 | 7.7436 | 5.6737 | 14.1333 | 16.4971 | 24.2407 | 29.9144 | 5.8471 | 8.2862 | 2.2599 | 2.3638 | 4.5324 | 2.1749 | 7.7536 | 5.6737 | 14.1333 | 16.4971 | 24.2507 | 29.9244 | 0.01
5.8513 | 7.9435 | 1.8183 | 2.2261 | 6.234 | 3.5513 | 6.3472 | 2.3108 | 13.7949 | 16.021 | 25.8063 | 28.117 | 5.8513 | 7.9435 | 1.8183 | 2.2261 | 6.234 | 3.5513 | 6.3572 | 2.3108 | 13.7949 | 16.021 | 25.8063 | 28.117 | 0.01
5.9885 | 8.6391 | 2.1432 | 1.8434 | 2.1128 | 2.7424 | 7.4384 | 7.4648 | 14.6275 | 16.4709 | 23.9092 | 31.374 | 5.9885 | 8.6391 | 2.1432 | 1.8434 | 2.1128 | 2.7424 | 7.4484 | 7.4648 | 14.6275 | 16.4709 | 23.9192 | 31.384 | 0.01
5.5507 | 8.7545 | 1.7858 | 1.7713 | 2.5427 | 2.7677 | 7.703 | 6.527 | 14.3052 | 16.0765 | 23.7795 | 30.3065 | 5.5507 | 8.7545 | 1.7858 | 1.7713 | 2.5427 | 2.7677 | 7.713 | 6.527 | 14.3052 | 16.0765 | 23.7895 | 30.3165 | 0.01
6.1621 | 6.9331 | 1.5587 | 1.8083 | 4.0029 | 4.2216 | 7.4477 | 6.6583 | 13.0952 | 14.9034 | 23.1279 | 29.7862 | 6.1621 | 6.9331 | 1.5587 | 1.8083 | 4.0029 | 4.2216 | 7.4577 | 6.6583 | 13.0952 | 14.9034 | 23.1279 | 29.7862 | 0.01
5.8794 | 10.0272 | 2.1302 | 1.8487 | 4.4027 | 3.0643 | 6.0881 | 4.4882 | 15.9066 | 17.7553 | 25.2223 | 29.7105 | 5.8794 | 10.0272 | 2.1302 | 1.8487 | 4.4027 | 3.0643 | 6.0981 | 4.4882 | 15.9066 | 17.7553 | 25.2223 | 29.7105 | 0.01
6.0205 | 9.3951 | 2.2717 | 1.9699 | 1.3404 | 3.0722 | 8.3663 | 5.9443 | 15.4156 | 17.3855 | 25.7518 | 31.696 | 6.0205 | 9.3951 | 2.2717 | 1.9699 | 1.3404 | 3.0722 | 8.3763 | 5.9443 | 15.4156 | 17.3855 | 25.7618 | 31.706 | 0.01
7.0017 | 6.4729 | 2.0862 | 1.8533 | 2.4725 | 3.4676 | 6.7341 | 4.8632 | 13.4746 | 15.3279 | 22.0619 | 26.9251 | 7.0017 | 6.4729 | 2.0862 | 1.8533 | 2.4725 | 3.4676 | 6.7441 | 4.8632 | 13.4746 | 15.3279 | 22.0719 | 26.9351 | 0.01
4.5761 | 8.4949 | 1.7483 | 2.2292 | 4.8817 | 3.5433 | 10.6033 | 4.9728 | 13.071 | 15.3002 | 25.9035 | 30.8762 | 4.5761 | 8.4949 | 1.7483 | 2.2292 | 4.8817 | 3.5433 | 10.6133 | 4.9728 | 13.071 | 15.3002 | 25.9135 | 30.8862 | 0.01
6.2069 | 8.1547 | 2.1128 | 2.4812 | 2.1191 | 3.0512 | 5.542 | 4.7918 | 14.3615 | 16.8427 | 22.3848 | 27.1766 | 6.2069 | 8.1547 | 2.1128 | 2.4812 | 2.1191 | 3.0512 | 5.552 | 4.7918 | 14.3615 | 16.8427 | 22.3948 | 27.1866 | 0.01
5.326 | 8.4282 | 2.0317 | 1.8927 | 3.9771 | 2.6978 | 6.7363 | 4.6652 | 13.7542 | 15.6469 | 22.3832 | 27.0484 | 5.326 | 8.4282 | 2.0317 | 1.8927 | 3.9771 | 2.6978 | 6.7463 | 4.6652 | 13.7542 | 15.6469 | 22.3932 | 27.0584 | 0.01
6.393 | 9.3868 | 1.7945 | 1.4479 | 2.9491 | 3.0724 | 7.6966 | 6.491 | 15.7798 | 17.2277 | 24.9243 | 31.4153 | 6.393 | 9.3868 | 1.7945 | 1.4479 | 2.9491 | 3.0724 | 7.7066 | 6.491 | 15.7798 | 17.2277 | 24.9343 | 31.4253 | 0.01
5.9044 | 9.2101 | 2.3494 | 2.198 | 3.8779 | 3.2395 | 5.122 | 5.2739 | 15.1145 | 17.3125 | 24.4298 | 29.7037 | 5.9044 | 9.2101 | 2.3494 | 2.198 | 3.8779 | 3.2395 | 5.132 | 5.2739 | 15.1145 | 17.3125 | 24.4298 | 29.7037 | 0.01
6.4253 | 7.1695 | 1.9257 | 1.9825 | 2.9822 | 3.531 | 8.9955 | 4.5223 | 13.5947 | 15.5772 | 24.5727 | 29.095 | 6.4253 | 7.1695 | 1.9257 | 1.9825 | 2.9822 | 3.531 | 9.0055 | 4.5223 | 13.5947 | 15.5772 | 24.5827 | 29.105 | 0.01
5.1621 | 8.2012 | 2.044 | 2.798 | 3.105 | 3.013 | 9.538 | 5.4506 | 13.3633 | 16.1613 | 25.6994 | 31.1499 | 5.1621 | 8.2012 | 2.044 | 2.798 | 3.105 | 3.013 | 9.548 | 5.4506 | 13.3633 | 16.1613 | 25.7094 | 31.1599 | 0.01
5.5705 | 7.7999 | 2.0094 | 2.2965 | 2.3126 | 3.1736 | 8.5022 | 4.0888 | 13.3704 | 15.6669 | 24.1691 | 28.2579 | 5.5705 | 7.7999 | 2.0094 | 2.2965 | 2.3126 | 3.1736 | 8.5122 | 4.0888 | 13.3704 | 15.6669 | 24.1791 | 28.2679 | 0.01
6.8897 | 6.5372 | 2.1011 | 2.6811 | 3.3821 | 2.3001 | 6.7188 | 2.2865 | 13.4269 | 16.108 | 22.8268 | 25.1133 | 6.8897 | 6.5372 | 2.1011 | 2.6811 | 3.3821 | 2.3001 | 6.7288 | 2.2865 | 13.4269 | 16.108 | 22.8368 | 25.1233 | 0.01
5.7297 | 8.3926 | 1.8323 | 1.9021 | 2.1262 | 2.8457 | 6.8776 | 5.6254 | 14.1223 | 16.0244 | 22.902 | 28.5274 | 5.7297 | 8.3926 | 1.8323 | 1.9021 | 2.1262 | 2.8457 | 6.8876 | 5.6254 | 14.1223 | 16.0244 | 22.912 | 28.5374 | 0.01
5.7335 | 7.559 | 1.8723 | 2.0969 | 4.4205 | 3.6316 | 8.7213 | 3.7354 | 13.2926 | 15.3894 | 24.1107 | 27.8461 | 5.7335 | 7.559 | 1.8723 | 2.0969 | 4.4205 | 3.6316 | 8.7313 | 3.7354 | 13.2926 | 15.3894 | 24.1207 | 27.8561 | 0.01
5.8504 | 7.221 | 2.1675 | 1.9462 | 2.5379 | 2.1147 | 8.3485 | 5.9913 | 13.0714 | 15.0175 | 23.366 | 29.3573 | 5.8504 | 7.221 | 2.1675 | 1.9462 | 2.5379 | 2.1147 | 8.3585 | 5.9913 | 13.0714 | 15.0175 | 23.376 | 29.3673 | 0.01
6.0157 | 6.9526 | 1.7688 | 1.9824 | 3.9982 | 3.6435 | 7.9107 | 6.1374 | 12.9683 | 14.9507 | 22.8614 | 28.9988 | 6.0157 | 6.9526 | 1.7688 | 1.9824 | 3.9982 | 3.6435 | 7.9207 | 6.1374 | 12.9683 | 14.9507 | 22.8714 | 29.0088 | 0.01
7.5764 | 8.2637 | 2.0263 | 1.3471 | 1.9066 | 2.333 | 7.4415 | 4.7621 | 15.8401 | 17.1872 | 24.6287 | 29.3908 | 7.5764 | 8.2637 | 2.0263 | 1.3471 | 1.9066 | 2.333 | 7.4515 | 4.7621 | 15.8401 | 17.1872 | 24.6387 | 29.4008 | 0.01
5.5265 | 10.9605 | 2.2734 | 2.1767 | 2.0362 | 1.9358 | 4.8658 | 3.8037 | 16.487 | 18.6637 | 23.5295 | 27.3332 | 5.5265 | 10.9605 | 2.2734 | 2.1767 | 2.0362 | 1.9358 | 4.8758 | 3.8037 | 16.487 | 18.6637 | 23.5395 | 27.3432 | 0.01
6.3138 | 8.1864 | 2.1805 | 1.4545 | 2.7067 | 3.298 | 8.3734 | 3.5904 | 14.5001 | 15.9546 | 24.328 | 27.9184 | 6.3138 | 8.1864 | 2.1805 | 1.4545 | 2.7067 | 3.298 | 8.3834 | 3.5904 | 14.5001 | 15.9546 | 24.338 | 27.9284 | 0.01
6.5408 | 9.8724 | 2.2137 | 1.606 | 1.7762 | 2.9464 | 5.7619 | 2.8426 | 16.4131 | 18.0191 | 23.781 | 26.6236 | 6.5408 | 9.8724 | 2.2137 | 1.606 | 1.7762 | 2.9464 | 5.7719 | 2.8426 | 16.4131 | 18.0191 | 23.791 | 26.6336 | 0.01
5.6189 | 8.8495 | 2.2109 | 2.0161 | 2.7339 | 4.0183 | 7.9053 | 4.7839 | 14.4684 | 16.4845 | 24.3898 | 29.1737 | 5.6189 | 8.8495 | 2.2109 | 2.0161 | 2.7339 | 4.0183 | 7.9153 | 4.7839 | 14.4684 | 16.4845 | 24.3998 | 29.1837 | 0.01
6.0167 | 8.3127 | 2.2777 | 1.6516 | 4.1502 | 3.041 | 5.0145 | 5.7197 | 14.3295 | 15.9811 | 23.1722 | 28.8919 | 6.0167 | 8.3127 | 2.2777 | 1.6516 | 4.1502 | 3.041 | 5.0245 | 5.7197 | 14.3295 | 15.9811 | 23.1722 | 28.8919 | 0.01
6.104 | 7.6692 | 2.192 | 1.545 | 3.7518 | 3.3613 | 8.3445 | 4.0858 | 13.7732 | 15.3182 | 23.6627 | 27.7486 | 6.104 | 7.6692 | 2.192 | 1.545 | 3.7518 | 3.3613 | 8.3545 | 4.0858 | 13.7732 | 15.3182 | 23.6727 | 27.7586 | 0.01
6.4816 | 8.2289 | 1.9911 | 1.8637 | 3.1093 | 3.3811 | 8.4491 | 5.3931 | 14.7105 | 16.5742 | 25.0234 | 30.4164 | 6.4816 | 8.2289 | 1.9911 | 1.8637 | 3.1093 | 3.3811 | 8.4591 | 5.3931 | 14.7105 | 16.5742 | 25.0334 | 30.4264 | 0.01
4.9656 | 9.1727 | 2.1278 | 2.2697 | 4.2242 | 2.7088 | 8.2282 | 2.7065 | 14.1383 | 16.408 | 24.6362 | 27.3427 | 4.9656 | 9.1727 | 2.1278 | 2.2697 | 4.2242 | 2.7088 | 8.2382 | 2.7065 | 14.1383 | 16.408 | 24.6462 | 27.3527 | 0.01
6.4251 | 8.9882 | 2.0962 | 1.9569 | 2.2423 | 4.0024 | 7.6362 | 5.1765 | 15.4133 | 17.3702 | 25.0064 | 30.1829 | 6.4251 | 8.9882 | 2.0962 | 1.9569 | 2.2423 | 4.0024 | 7.6462 | 5.1765 | 15.4133 | 17.3702 | 25.0164 | 30.1929 | 0.01
4.5852 | 7.6055 | 1.8146 | 1.3903 | 3.2248 | 3.6154 | 8.9732 | 5.1566 | 12.1907 | 13.581 | 22.5542 | 27.7108 | 4.5852 | 7.6055 | 1.8146 | 1.3903 | 3.2248 | 3.6154 | 8.9832 | 5.1566 | 12.1907 | 13.581 | 22.5642 | 27.7208 | 0.01
4.9148 | 9.433 | 2.1546 | 1.6609 | 2.8106 | 2.9729 | 8.1968 | 8.487 | 14.3478 | 16.0086 | 24.2055 | 32.6925 | 4.9148 | 9.433 | 2.1546 | 1.6609 | 2.8106 | 2.9729 | 8.2068 | 8.487 | 14.3478 | 16.0086 | 24.2155 | 32.7025 | 0.01
5.4871 | 8.9718 | 1.5649 | 1.6328 | 3.0447 | 3.6506 | 6.3022 | 4.4922 | 14.4589 | 16.0917 | 22.7871 | 27.2793 | 5.4871 | 8.9718 | 1.5649 | 1.6328 | 3.0447 | 3.6506 | 6.3122 | 4.4922 | 14.4589 | 16.0917 | 22.7871 | 27.2793 | 0.01
6.5788 | 8.739 | 2.1856 | 1.7968 | 3.7269 | 3.2434 | 7.754 | 6.7084 | 15.3178 | 17.1146 | 24.8686 | 31.577 | 6.5788 | 8.739 | 2.1856 | 1.7968 | 3.7269 | 3.2434 | 7.764 | 6.7084 | 15.3178 | 17.1146 | 24.8786 | 31.587 | 0.01
6.0799 | 6.6695 | 1.9612 | 1.5921 | 4.6441 | 3.1918 | 7.5422 | 7.2662 | 12.7494 | 14.3415 | 22.1773 | 29.4435 | 6.0799 | 6.6695 | 1.9612 | 1.5921 | 4.6441 | 3.1918 | 7.5522 | 7.2662 | 12.7494 | 14.3415 | 22.1773 | 29.4435 | 0.01
4.9564 | 8.8907 | 1.9295 | 2.2611 | 3.1976 | 3.2729 | 5.5757 | 3.2944 | 13.8471 | 16.1082 | 22.5787 | 25.8731 | 4.9564 | 8.8907 | 1.9295 | 2.2611 | 3.1976 | 3.2729 | 5.5857 | 3.2944 | 13.8471 | 16.1082 | 22.5787 | 25.8731 | 0.01
6.03 | 8.2582 | 1.9433 | 1.9658 | 3.6957 | 2.1724 | 6.0089 | 4.954 | 14.2882 | 16.254 | 22.2629 | 27.217 | 6.03 | 8.2582 | 1.9433 | 1.9658 | 3.6957 | 2.1724 | 6.0189 | 4.954 | 14.2882 | 16.254 | 22.2729 | 27.227 | 0.01
5.1718 | 8.3899 | 1.7483 | 1.4949 | 3.6053 | 2.886 | 4.8696 | 3.6931 | 13.5617 | 15.0566 | 21.5478 | 25.241 | 5.1718 | 8.3899 | 1.7483 | 1.4949 | 3.6053 | 2.886 | 4.8796 | 3.6931 | 13.5617 | 15.0566 | 21.5478 | 25.241 | 0.01
5.8507 | 7.2137 | 1.7395 | 1.8389 | 3.5447 | 2.9671 | 7.4142 | 6.3737 | 13.0645 | 14.9034 | 22.3176 | 28.6913 | 5.8507 | 7.2137 | 1.7395 | 1.8389 | 3.5447 | 2.9671 | 7.4242 | 6.3737 | 13.0645 | 14.9034 | 22.3276 | 28.7013 | 0.01
6.7209 | 8.124 | 2.0679 | 1.6464 | 2.6518 | 2.6243 | 8.5667 | 3.5887 | 14.8449 | 16.4914 | 25.0581 | 28.6468 | 6.7209 | 8.124 | 2.0679 | 1.6464 | 2.6518 | 2.6243 | 8.5767 | 3.5887 | 14.8449 | 16.4914 | 25.0681 | 28.6568 | 0.01
5.544 | 9.774 | 1.8243 | 1.9998 | 2.4589 | 1.9008 | 7.3663 | 6.5434 | 15.318 | 17.3179 | 24.6841 | 31.2276 | 5.544 | 9.774 | 1.8243 | 1.9998 | 2.4589 | 1.9008 | 7.3763 | 6.5434 | 15.318 | 17.3179 | 24.6941 | 31.2376 | 0.01
4.9419 | 6.851 | 1.9491 | 2.076 | 2.2916 | 3.8307 | 6.983 | 6.328 | 11.7929 | 13.869 | 20.8519 | 27.1799 | 4.9419 | 6.851 | 1.9491 | 2.076 | 2.2916 | 3.8307 | 6.993 | 6.328 | 11.7929 | 13.869 | 20.8619 | 27.1899 | 0.01
4.6217 | 9.7132 | 1.9939 | 2.1446 | 2.6897 | 2.9587 | 5.9274 | 7.0055 | 14.3348 | 16.4794 | 22.4068 | 29.4124 | 4.6217 | 9.7132 | 1.9939 | 2.1446 | 2.6897 | 2.9587 | 5.9374 | 7.0055 | 14.3348 | 16.4794 | 22.4168 | 29.4224 | 0.01
6.1721 | 7.6207 | 1.9969 | 1.9544 | 5.3226 | 2.8274 | 7.7143 | 5.0883 | 13.7928 | 15.7472 | 23.8972 | 28.9854 | 6.1721 | 7.6207 | 1.9969 | 1.9544 | 5.3226 | 2.8274 | 7.7243 | 5.0883 | 13.7928 | 15.7472 | 23.8972 | 28.9854 | 0.01
5.9102 | 8.9983 | 2.2496 | 1.6822 | 3.5782 | 3.5135 | 8.6815 | 4.8163 | 14.9085 | 16.5907 | 25.2722 | 30.0885 | 5.9102 | 8.9983 | 2.2496 | 1.6822 | 3.5782 | 3.5135 | 8.6915 | 4.8163 | 14.9085 | 16.5907 | 25.2822 | 30.0985 | 0.01
7.5556 | 7.7457 | 1.8653 | 2.1003 | 2.7408 | 3.6528 | 7.5071 | 6.1671 | 15.3014 | 17.4016 | 24.9087 | 31.0758 | 7.5556 | 7.7457 | 1.8653 | 2.1003 | 2.7408 | 3.6528 | 7.5171 | 6.1671 | 15.3014 | 17.4016 | 24.9187 | 31.0858 | 0.01
6.7739 | 8.2316 | 2.0403 | 1.8811 | 3.2439 | 3.753 | 5.7829 | 5.4303 | 15.0055 | 16.8867 | 23.8836 | 29.3139 | 6.7739 | 8.2316 | 2.0403 | 1.8811 | 3.2439 | 3.753 | 5.7929 | 5.4303 | 15.0055 | 16.8867 | 23.8836 | 29.3139 | 0.01
6.8524 | 8.8008 | 2.0969 | 1.7937 | 2.4645 | 2.6347 | 8.8467 | 5.4568 | 15.6532 | 17.4469 | 26.2936 | 31.7504 | 6.8524 | 8.8008 | 2.0969 | 1.7937 | 2.4645 | 2.6347 | 8.8567 | 5.4568 | 15.6532 | 17.4469 | 26.3036 | 31.7604 | 0.01
6.4823 | 7.6881 | 2.1119 | 1.761 | 3.8195 | 3.8482 | 4.8658 | 5.4635 | 14.1704 | 15.9314 | 23.5991 | 29.0627 | 6.4823 | 7.6881 | 2.1119 | 1.761 | 3.8195 | 3.8482 | 4.8758 | 5.4635 | 14.1704 | 15.9314 | 23.5991 | 29.0627 | 0.01
5.9339 | 8.0215 | 1.8417 | 1.9281 | 3.1465 | 3.0172 | 9.0955 | 3.8218 | 13.9555 | 15.8836 | 24.9791 | 28.8009 | 5.9339 | 8.0215 | 1.8417 | 1.9281 | 3.1465 | 3.0172 | 9.1055 | 3.8218 | 13.9555 | 15.8836 | 24.9891 | 28.8109 | 0.01
7.2795 | 8.2051 | 2.0625 | 2.2191 | 4.0285 | 4.6793 | 6.5747 | 5.8887 | 15.4846 | 17.7037 | 26.4116 | 32.3003 | 7.2795 | 8.2051 | 2.0625 | 2.2191 | 4.0285 | 4.6793 | 6.5847 | 5.8887 | 15.4846 | 17.7037 | 26.4116 | 32.3003 | 0.01
5.7237 | 8.3899 | 1.8208 | 2.1589 | 3.4222 | 3.2159 | 8.9932 | 6.5598 | 14.1135 | 16.2724 | 25.2656 | 31.8254 | 5.7237 | 8.3899 | 1.8208 | 2.1589 | 3.4222 | 3.2159 | 9.0032 | 6.5598 | 14.1135 | 16.2724 | 25.2756 | 31.8354 | 0.01
6.0392 | 7.5665 | 1.6435 | 2.2733 | 2.6328 | 2.6787 | 6.3589 | 7.1625 | 13.6057 | 15.879 | 22.2379 | 29.4003 | 6.0392 | 7.5665 | 1.6435 | 2.2733 | 2.6328 | 2.6787 | 6.3689 | 7.1625 | 13.6057 | 15.879 | 22.2479 | 29.4103 | 0.01
6.5097 | 6.3426 | 2.08 | 1.8085 | 3.7529 | 2.8635 | 6.1501 | 6.7995 | 12.8523 | 14.6608 | 21.2772 | 28.0767 | 6.5097 | 6.3426 | 2.08 | 1.8085 | 3.7529 | 2.8635 | 6.1601 | 6.7995 | 12.8523 | 14.6608 | 21.2772 | 28.0767 | 0.01
5.4246 | 7.0535 | 1.9464 | 1.9152 | 3.7862 | 3.5488 | 7.7024 | 4.9507 | 12.4781 | 14.3934 | 22.0957 | 27.0465 | 5.4246 | 7.0535 | 1.9464 | 1.9152 | 3.7862 | 3.5488 | 7.7124 | 4.9507 | 12.4781 | 14.3934 | 22.1057 | 27.0565 | 0.01
5.8768 | 7.9824 | 2.0242 | 2.0986 | 2.183 | 3.6355 | 6.7607 | 4.0719 | 13.8592 | 15.9578 | 22.7185 | 26.7905 | 5.8768 | 7.9824 | 2.0242 | 2.0986 | 2.183 | 3.6355 | 6.7707 | 4.0719 | 13.8592 | 15.9578 | 22.7285 | 26.8005 | 0.01
5.7109 | 7.3825 | 1.6082 | 2.0615 | 2.6467 | 3.7599 | 8.244 | 3.2381 | 13.0934 | 15.1549 | 23.3989 | 26.637 | 5.7109 | 7.3825 | 1.6082 | 2.0615 | 2.6467 | 3.7599 | 8.254 | 3.2381 | 13.0934 | 15.1549 | 23.4089 | 26.647 | 0.01
5.2442 | 9.0486 | 1.7726 | 2.0733 | 3.7862 | 4.684 | 10.0021 | 3.8649 | 14.2928 | 16.3661 | 26.3682 | 30.2331 | 5.2442 | 9.0486 | 1.7726 | 2.0733 | 3.7862 | 4.684 | 10.0121 | 3.8649 | 14.2928 | 16.3661 | 26.3782 | 30.2431 | 0.01
6.0856 | 8.9409 | 2.0891 | 2.2138 | 4.1918 | 3.0056 | 7.8285 | 6.5566 | 15.0265 | 17.2403 | 25.0689 | 31.6254 | 6.0856 | 8.9409 | 2.0891 | 2.2138 | 4.1918 | 3.0056 | 7.8385 | 6.5566 | 15.0265 | 17.2403 | 25.0789 | 31.6354 | 0.01
5.9688 | 8.0346 | 2.0631 | 2.1096 | 4.3275 | 3.1635 | 3.9257 | 3.5351 | 14.0034 | 16.113 | 23.604 | 27.1391 | 5.9688 | 8.0346 | 2.0631 | 2.1096 | 4.3275 | 3.1635 | 3.9357 | 3.5351 | 14.0034 | 16.113 | 23.604 | 27.1391 | 0.01
5.3763 | 6.9423 | 1.7303 | 1.8736 | 1.7716 | 3.5091 | 4.7986 | 4.3039 | 12.3186 | 14.1922 | 19.473 | 23.7769 | 5.3763 | 6.9423 | 1.7303 | 1.8736 | 1.7716 | 3.5091 | 4.8086 | 4.3039 | 12.3186 | 14.1922 | 19.473 | 23.7769 | 0.01
5.9757 | 10.5901 | 1.5518 | 1.8822 | 2.8816 | 2.1719 | 9.5342 | 6.5345 | 16.5658 | 18.4481 | 27.9823 | 34.5167 | 5.9757 | 10.5901 | 1.5518 | 1.8822 | 2.8816 | 2.1719 | 9.5442 | 6.5345 | 16.5658 | 18.4481 | 27.9923 | 34.5267 | 0.01
7.1605 | 8.3583 | 2.3258 | 1.7806 | 3.681 | 4.533 | 7.9876 | 5.3675 | 15.5187 | 17.2993 | 25.5133 | 30.8808 | 7.1605 | 8.3583 | 2.3258 | 1.7806 | 3.681 | 4.533 | 7.9976 | 5.3675 | 15.5187 | 17.2993 | 25.5133 | 30.8808 | 0.01
6.9558 | 9.2671 | 2.0147 | 2.1905 | 4.0035 | 2.8997 | 8.9888 | 4.5282 | 16.2229 | 18.4134 | 27.4023 | 31.9304 | 6.9558 | 9.2671 | 2.0147 | 2.1905 | 4.0035 | 2.8997 | 8.9988 | 4.5282 | 16.2229 | 18.4134 | 27.4123 | 31.9404 | 0.01
5.9304 | 7.9313 | 2.0475 | 2.0102 | 2.1096 | 3.4619 | 8.0237 | 3.7199 | 13.8617 | 15.8718 | 23.8955 | 27.6154 | 5.9304 | 7.9313 | 2.0475 | 2.0102 | 2.1096 | 3.4619 | 8.0337 | 3.7199 | 13.8617 | 15.8718 | 23.9055 | 27.6254 | 0.01
6.9019 | 4.9866 | 2.0311 | 1.9988 | 1.567 | 3.355 | 9.0411 | 4.6769 | 11.8884 | 13.8872 | 22.9284 | 27.6053 | 6.9019 | 4.9866 | 2.0311 | 1.9988 | 1.567 | 3.355 | 9.0511 | 4.6769 | 11.8884 | 13.8872 | 22.9384 | 27.6153 | 0.01
5.3674 | 7.0345 | 2.2834 | 2.0318 | 3.99 | 3.0681 | 8.0581 | 5.0652 | 12.4018 | 14.4336 | 22.4917 | 27.5569 | 5.3674 | 7.0345 | 2.2834 | 2.0318 | 3.99 | 3.0681 | 8.0681 | 5.0652 | 12.4018 | 14.4336 | 22.5017 | 27.5669 | 0.01
4.8561 | 5.6185 | 1.896 | 1.613 | 2.0096 | 3.5793 | 6.955 | 5.3299 | 10.4745 | 12.0876 | 19.0425 | 24.3725 | 4.8561 | 5.6185 | 1.896 | 1.613 | 2.0096 | 3.5793 | 6.965 | 5.3299 | 10.4745 | 12.0876 | 19.0525 | 24.3825 | 0.01
6.7709 | 5.7865 | 2.0146 | 2.2716 | 1.965 | 2.0856 | 5.9374 | 3.5022 | 12.5574 | 14.8289 | 20.7664 | 24.2686 | 6.7709 | 5.7865 | 2.0146 | 2.2716 | 1.965 | 2.0856 | 5.9474 | 3.5022 | 12.5574 | 14.8289 | 20.7764 | 24.2786 | 0.01
7.4471 | 9.1849 | 1.5209 | 2.1117 | 2.8734 | 3.0284 | 6.8388 | 4.4965 | 16.632 | 18.7437 | 25.5825 | 30.0789 | 7.4471 | 9.1849 | 1.5209 | 2.1117 | 2.8734 | 3.0284 | 6.8488 | 4.4965 | 16.632 | 18.7437 | 25.5925 | 30.0889 | 0.01
5.6708 | 7.4244 | 2.1651 | 1.8119 | 4.0233 | 3.8529 | 4.4682 | 7.3989 | 13.0952 | 14.907 | 22.7833 | 30.1822 | 5.6708 | 7.4244 | 2.1651 | 1.8119 | 4.0233 | 3.8529 | 4.4782 | 7.3989 | 13.0952 | 14.907 | 22.7833 | 30.1822 | 0.01
5.135 | 5.5739 | 1.7734 | 1.9434 | 5.0181 | 2.6288 | 4.9024 | 2.8114 | 10.709 | 12.6524 | 20.2992 | 23.1106 | 5.135 | 5.5739 | 1.7734 | 1.9434 | 5.0181 | 2.6288 | 4.9124 | 2.8114 | 10.709 | 12.6524 | 20.2992 | 23.1106 | 0.01
7.1166 | 8.088 | 1.9695 | 1.9164 | 2.9739 | 2.9605 | 6.9702 | 5.0011 | 15.2046 | 17.121 | 24.0912 | 29.0923 | 7.1166 | 8.088 | 1.9695 | 1.9164 | 2.9739 | 2.9605 | 6.9802 | 5.0011 | 15.2046 | 17.121 | 24.1012 | 29.1023 | 0.01
5.4766 | 9.2796 | 2.2502 | 1.6829 | 1.806 | 3.7484 | 6.8104 | 7.9346 | 14.7563 | 16.4392 | 23.2496 | 31.1842 | 5.4766 | 9.2796 | 2.2502 | 1.6829 | 1.806 | 3.7484 | 6.8204 | 7.9346 | 14.7563 | 16.4392 | 23.2596 | 31.1942 | 0.01
5.8576 | 6.8862 | 2.272 | 1.9832 | 3.317 | 3.3618 | 6.1214 | 6.8198 | 12.7438 | 14.7269 | 21.4058 | 28.2255 | 5.8576 | 6.8862 | 2.272 | 1.9832 | 3.317 | 3.3618 | 6.1314 | 6.8198 | 12.7438 | 14.7269 | 21.4058 | 28.2255 | 0.01
6.5496 | 8.6678 | 2.0334 | 2.0324 | 3.9292 | 3.5837 | 6.4611 | 3.2173 | 15.2175 | 17.2499 | 24.7628 | 27.9801 | 6.5496 | 8.6678 | 2.0334 | 2.0324 | 3.9292 | 3.5837 | 6.4711 | 3.2173 | 15.2175 | 17.2499 | 24.7628 | 27.9801 | 0.01
6.4611 | 8.4469 | 1.948 | 1.6068 | 4.2305 | 3.0485 | 8.8091 | 5.3812 | 14.9079 | 16.5147 | 25.3238 | 30.705 | 6.4611 | 8.4469 | 1.948 | 1.6068 | 4.2305 | 3.0485 | 8.8191 | 5.3812 | 14.9079 | 16.5147 | 25.3338 | 30.715 | 0.01
6.2762 | 8.0143 | 1.8832 | 2.3672 | 3.4923 | 2.7715 | 4.8867 | 3.2321 | 14.2905 | 16.6576 | 22.9214 | 26.1535 | 6.2762 | 8.0143 | 1.8832 | 2.3672 | 3.4923 | 2.7715 | 4.8967 | 3.2321 | 14.2905 | 16.6576 | 22.9214 | 26.1535 | 0.01
4.8614 | 7.4307 | 2.1435 | 2.0528 | 3.8979 | 3.3656 | 6.807 | 6.9399 | 12.2921 | 14.3449 | 21.6085 | 28.5485 | 4.8614 | 7.4307 | 2.1435 | 2.0528 | 3.8979 | 3.3656 | 6.817 | 6.9399 | 12.2921 | 14.3449 | 21.6085 | 28.5485 | 0.01
5.5402 | 8.2436 | 2.0764 | 2.0686 | 3.9013 | 3.6922 | 5.6893 | 5.0385 | 13.7838 | 15.8524 | 23.4458 | 28.4844 | 5.5402 | 8.2436 | 2.0764 | 2.0686 | 3.9013 | 3.6922 | 5.6993 | 5.0385 | 13.7838 | 15.8524 | 23.4458 | 28.4844 | 0.01
5.5688 | 6.202 | 1.8947 | 1.5847 | 2.5949 | 3.3969 | 8.3554 | 4.0575 | 11.7708 | 13.3555 | 21.7108 | 25.7683 | 5.5688 | 6.202 | 1.8947 | 1.5847 | 2.5949 | 3.3969 | 8.3654 | 4.0575 | 11.7708 | 13.3555 | 21.7208 | 25.7783 | 0.01
6.7957 | 6.4311 | 2.409 | 1.7708 | 3.4177 | 2.6241 | 7.6603 | 4.821 | 13.2268 | 14.9977 | 22.6579 | 27.479 | 6.7957 | 6.4311 | 2.409 | 1.7708 | 3.4177 | 2.6241 | 7.6703 | 4.821 | 13.2268 | 14.9977 | 22.6679 | 27.489 | 0.01
6.4395 | 5.3199 | 2.2409 | 2.0838 | 1.3668 | 3.1987 | 7.2003 | 5.4731 | 11.7595 | 13.8433 | 21.0436 | 26.5167 | 6.4395 | 5.3199 | 2.2409 | 2.0838 | 1.3668 | 3.1987 | 7.2103 | 5.4731 | 11.7595 | 13.8433 | 21.0536 | 26.5267 | 0.01
4.4694 | 9.1045 | 1.8934 | 2.0437 | 2.211 | 2.7287 | 5.5883 | 3.9285 | 13.574 | 15.6177 | 21.2059 | 25.1344 | 4.4694 | 9.1045 | 1.8934 | 2.0437 | 2.211 | 2.7287 | 5.5983 | 3.9285 | 13.574 | 15.6177 | 21.2159 | 25.1444 | 0.01
4.5691 | 10.6351 | 1.8734 | 1.8448 | 1.7762 | 3.3115 | 5.8079 | 3.3752 | 15.2042 | 17.049 | 22.8569 | 26.2321 | 4.5691 | 10.6351 | 1.8734 | 1.8448 | 1.7762 | 3.3115 | 5.8179 | 3.3752 | 15.2042 | 17.049 | 22.8669 | 26.2421 | 0.01
6.5955 | 7.3257 | 1.9979 | 1.4935 | 3.2953 | 2.5429 | 8.0863 | 4.5338 | 13.9212 | 15.4147 | 23.501 | 28.0348 | 6.5955 | 7.3257 | 1.9979 | 1.4935 | 3.2953 | 2.5429 | 8.0963 | 4.5338 | 13.9212 | 15.4147 | 23.511 | 28.0448 | 0.01
5.7975 | 11.8675 | 2.1092 | 1.7015 | 4.8032 | 2.3814 | 6.8821 | 5.8741 | 17.665 | 19.3665 | 26.5511 | 32.4252 | 5.7975 | 11.8675 | 2.1092 | 1.7015 | 4.8032 | 2.3814 | 6.8921 | 5.8741 | 17.665 | 19.3665 | 26.5511 | 32.4252 | 0.01
6.139 | 8.824 | 2.2997 | 1.9708 | 3.0053 | 2.0873 | 7.5831 | 3.5102 | 14.963 | 16.9338 | 24.5169 | 28.0271 | 6.139 | 8.824 | 2.2997 | 1.9708 | 3.0053 | 2.0873 | 7.5931 | 3.5102 | 14.963 | 16.9338 | 24.5269 | 28.0371 | 0.01
5.8107 | 5.9212 | 1.956 | 1.6155 | 1.7711 | 2.276 | 7.4411 | 4.0434 | 11.7319 | 13.3474 | 20.7885 | 24.832 | 5.8107 | 5.9212 | 1.956 | 1.6155 | 1.7711 | 2.276 | 7.4511 | 4.0434 | 11.7319 | 13.3474 | 20.7985 | 24.842 | 0.01
6.0121 | 10.1384 | 2.162 | 2.1017 | 2.2273 | 2.9386 | 7.0806 | 4.3257 | 16.1506 | 18.2523 | 25.333 | 29.6587 | 6.0121 | 10.1384 | 2.162 | 2.1017 | 2.2273 | 2.9386 | 7.0906 | 4.3257 | 16.1506 | 18.2523 | 25.343 | 29.6687 | 0.01
6.1472 | 9.4714 | 2.2018 | 2.5047 | 3.8615 | 3.6566 | 8.9288 | 3.3022 | 15.6186 | 18.1233 | 27.0521 | 30.3542 | 6.1472 | 9.4714 | 2.2018 | 2.5047 | 3.8615 | 3.6566 | 8.9388 | 3.3022 | 15.6186 | 18.1233 | 27.0621 | 30.3642 | 0.01
6.0813 | 7.4182 | 2.1076 | 2.4473 | 3.4017 | 2.0714 | 6.9701 | 5.3012 | 13.4996 | 15.9468 | 22.9169 | 28.2181 | 6.0813 | 7.4182 | 2.1076 | 2.4473 | 3.4017 | 2.0714 | 6.9801 | 5.3012 | 13.4996 | 15.9468 | 22.9269 | 28.2281 | 0.01
5.9706 | 8.6245 | 2.1874 | 2.0586 | 3.5571 | 3.0746 | 9.8989 | 2.8361 | 14.5951 | 16.6537 | 26.5526 | 29.3887 | 5.9706 | 8.6245 | 2.1874 | 2.0586 | 3.5571 | 3.0746 | 9.9089 | 2.8361 | 14.5951 | 16.6537 | 26.5626 | 29.3987 | 0.01
5.8534 | 9.0174 | 2.0329 | 1.7358 | 4.5341 | 2.8599 | 9.2715 | 3.9113 | 14.8708 | 16.6066 | 25.8781 | 29.7894 | 5.8534 | 9.0174 | 2.0329 | 1.7358 | 4.5341 | 2.8599 | 9.2815 | 3.9113 | 14.8708 | 16.6066 | 25.8881 | 29.7994 | 0.01
6.3873 | 7.7867 | 2.2457 | 1.8797 | 4.6074 | 3.234 | 8.3684 | 5.0658 | 14.174 | 16.0537 | 24.422 | 29.4878 | 6.3873 | 7.7867 | 2.2457 | 1.8797 | 4.6074 | 3.234 | 8.3784 | 5.0658 | 14.174 | 16.0537 | 24.432 | 29.4978 | 0.01
5.6265 | 8.9263 | 1.8518 | 2.0038 | 3.7406 | 3.1397 | 6.6269 | 4.0801 | 14.5527 | 16.5565 | 23.4368 | 27.5169 | 5.6265 | 8.9263 | 1.8518 | 2.0038 | 3.7406 | 3.1397 | 6.6369 | 4.0801 | 14.5527 | 16.5565 | 23.4368 | 27.5169 | 0.01
4.447 | 5.9771 | 2.2963 | 2.316 | 3.0296 | 3.6711 | 8.3799 | 4.3598 | 10.4241 | 12.7401 | 21.1199 | 25.4798 | 4.447 | 5.9771 | 2.2963 | 2.316 | 3.0296 | 3.6711 | 8.3899 | 4.3598 | 10.4241 | 12.7401 | 21.1299 | 25.4898 | 0.01
6.0817 | 7.8335 | 1.8263 | 2.1468 | 4.028 | 3.7812 | 9.3794 | 3.0597 | 13.9153 | 16.062 | 25.4414 | 28.5012 | 6.0817 | 7.8335 | 1.8263 | 2.1468 | 4.028 | 3.7812 | 9.3894 | 3.0597 | 13.9153 | 16.062 | 25.4514 | 28.5112 | 0.01
7.2155 | 8.2316 | 1.8625 | 2.4251 | 1.3108 | 2.5742 | 6.1581 | 6.1147 | 15.4471 | 17.8722 | 24.0303 | 30.145 | 7.2155 | 8.2316 | 1.8625 | 2.4251 | 1.3108 | 2.5742 | 6.1681 | 6.1147 | 15.4471 | 17.8722 | 24.0403 | 30.155 | 0.01
6.768 | 7.749 | 1.8707 | 1.9111 | 3.4545 | 2.7044 | 4.7184 | 6.9006 | 14.5169 | 16.428 | 22.5869 | 29.4876 | 6.768 | 7.749 | 1.8707 | 1.9111 | 3.4545 | 2.7044 | 4.7284 | 6.9006 | 14.5169 | 16.428 | 22.5869 | 29.4876 | 0.01
6.5458 | 7.8555 | 1.7781 | 2.375 | 1.6891 | 2.3867 | 10.3629 | 3.7264 | 14.4013 | 16.7763 | 27.1392 | 30.8656 | 6.5458 | 7.8555 | 1.7781 | 2.375 | 1.6891 | 2.3867 | 10.3729 | 3.7264 | 14.4013 | 16.7763 | 27.1492 | 30.8756 | 0.01
6.3501 | 7.5216 | 2.3717 | 1.2944 | 2.9544 | 2.101 | 9.1501 | 5.9909 | 13.8717 | 15.1661 | 24.3162 | 30.3071 | 6.3501 | 7.5216 | 2.3717 | 1.2944 | 2.9544 | 2.101 | 9.1601 | 5.9909 | 13.8717 | 15.1661 | 24.3262 | 30.3171 | 0.01
5.8894 | 9.3737 | 2.4346 | 1.7633 | 2.0383 | 3.2395 | 4.9826 | 5.9052 | 15.2631 | 17.0264 | 22.3042 | 28.2094 | 5.8894 | 9.3737 | 2.4346 | 1.7633 | 2.0383 | 3.2395 | 4.9926 | 5.9052 | 15.2631 | 17.0264 | 22.3042 | 28.2094 | 0.01
5.8675 | 8.6093 | 1.8156 | 2.543 | 3.5672 | 2.9306 | 8.7833 | 4.8608 | 14.4768 | 17.0198 | 25.803 | 30.6639 | 5.8675 | 8.6093 | 1.8156 | 2.543 | 3.5672 | 2.9306 | 8.7933 | 4.8608 | 14.4768 | 17.0198 | 25.813 | 30.6739 | 0.01
6.1741 | 10.619 | 2.3307 | 1.5276 | 2.5333 | 2.5311 | 6.9713 | 6.098 | 16.793 | 18.3207 | 25.2919 | 31.3899 | 6.1741 | 10.619 | 2.3307 | 1.5276 | 2.5333 | 2.5311 | 6.9813 | 6.098 | 16.793 | 18.3207 | 25.3019 | 31.3999 | 0.01
6.1604 | 5.9017 | 2.1926 | 2.4297 | 1.601 | 2.8488 | 7.4714 | 4.1936 | 12.0621 | 14.4918 | 21.9632 | 26.1568 | 6.1604 | 5.9017 | 2.1926 | 2.4297 | 1.601 | 2.8488 | 7.4814 | 4.1936 | 12.0621 | 14.4918 | 21.9732 | 26.1668 | 0.01
5.3224 | 8.1477 | 1.9089 | 2.3473 | 3.3184 | 2.1298 | 4.7063 | 5.4678 | 13.4701 | 15.8175 | 21.2657 | 26.7335 | 5.3224 | 8.1477 | 1.9089 | 2.3473 | 3.3184 | 2.1298 | 4.7163 | 5.4678 | 13.4701 | 15.8175 | 21.2657 | 26.7335 | 0.01
6.3324 | 8.158 | 2.1269 | 2.3973 | 2.592 | 4.0497 | 7.412 | 2.6695 | 14.4903 | 16.8877 | 24.2996 | 26.9691 | 6.3324 | 8.158 | 2.1269 | 2.3973 | 2.592 | 4.0497 | 7.422 | 2.6695 | 14.4903 | 16.8877 | 24.3096 | 26.9791 | 0.01
5.1193 | 8.7002 | 1.9678 | 1.3965 | 2.0388 | 2.7901 | 8.2165 | 5.6251 | 13.8195 | 15.216 | 23.4325 | 29.0575 | 5.1193 | 8.7002 | 1.9678 | 1.3965 | 2.0388 | 2.7901 | 8.2265 | 5.6251 | 13.8195 | 15.216 | 23.4425 | 29.0675 | 0.01
5.9882 | 7.766 | 1.841 | 2.462 | 2.1201 | 2.3217 | 4.5627 | 4.0417 | 13.7542 | 16.2162 | 20.7789 | 24.8205 | 5.9882 | 7.766 | 1.841 | 2.462 | 2.1201 | 2.3217 | 4.5727 | 4.0417 | 13.7542 | 16.2162 | 20.7889 | 24.8305 | 0.01
6.4551 | 6.3694 | 2.1075 | 1.8083 | 3.9504 | 3.8148 | 7.1661 | 6.0929 | 12.8244 | 14.6327 | 22.3979 | 28.4908 | 6.4551 | 6.3694 | 2.1075 | 1.8083 | 3.9504 | 3.8148 | 7.1761 | 6.0929 | 12.8244 | 14.6327 | 22.3979 | 28.4908 | 0.01
6.1673 | 8.8858 | 2.2899 | 1.3748 | 3.4705 | 3.4847 | 7.5032 | 6.1606 | 15.0531 | 16.428 | 23.9312 | 30.0918 | 6.1673 | 8.8858 | 2.2899 | 1.3748 | 3.4705 | 3.4847 | 7.5132 | 6.1606 | 15.0531 | 16.428 | 23.9412 | 30.1018 | 0.01
6.1142 | 8.4208 | 1.8154 | 1.7919 | 3.446 | 3.0832 | 3.9541 | 7.1423 | 14.535 | 16.3269 | 22.8561 | 29.9984 | 6.1142 | 8.4208 | 1.8154 | 1.7919 | 3.446 | 3.0832 | 3.9641 | 7.1423 | 14.535 | 16.3269 | 22.8561 | 29.9984 | 0.01
5.5108 | 8.0558 | 1.8028 | 2.034 | 5.0661 | 2.715 | 6.5133 | 5.0871 | 13.5665 | 15.6005 | 23.3816 | 28.4687 | 5.5108 | 8.0558 | 1.8028 | 2.034 | 5.0661 | 2.715 | 6.5233 | 5.0871 | 13.5665 | 15.6005 | 23.3816 | 28.4687 | 0.01
5.896 | 9.7454 | 1.6055 | 2.2582 | 4.5494 | 3.1719 | 8.4117 | 2.9501 | 15.6415 | 17.8997 | 26.3114 | 29.2615 | 5.896 | 9.7454 | 1.6055 | 2.2582 | 4.5494 | 3.1719 | 8.4217 | 2.9501 | 15.6415 | 17.8997 | 26.3214 | 29.2715 | 0.01
6.4652 | 6.9903 | 1.9503 | 2.2007 | 3.5864 | 2.549 | 5.859 | 3.6327 | 13.4555 | 15.6562 | 21.7916 | 25.4243 | 6.4652 | 6.9903 | 1.9503 | 2.2007 | 3.5864 | 2.549 | 5.869 | 3.6327 | 13.4555 | 15.6562 | 21.7916 | 25.4243 | 0.01
4.8484 | 7.2886 | 2.0785 | 2.0803 | 4.8972 | 3.2327 | 6.6349 | 5.5989 | 12.137 | 14.2173 | 22.3473 | 27.9462 | 4.8484 | 7.2886 | 2.0785 | 2.0803 | 4.8972 | 3.2327 | 6.6449 | 5.5989 | 12.137 | 14.2173 | 22.3473 | 27.9462 | 0.01
6.5591 | 6.8532 | 1.9592 | 2.3925 | 2.2466 | 3.4882 | 6.2674 | 7.1088 | 13.4123 | 15.8047 | 22.0721 | 29.1809 | 6.5591 | 6.8532 | 1.9592 | 2.3925 | 2.2466 | 3.4882 | 6.2774 | 7.1088 | 13.4123 | 15.8047 | 22.0821 | 29.1909 | 0.01
5.0394 | 7.3514 | 1.6808 | 1.627 | 3.1965 | 4.4104 | 4.5321 | 5.1742 | 12.3908 | 14.0178 | 21.6247 | 26.799 | 5.0394 | 7.3514 | 1.6808 | 1.627 | 3.1965 | 4.4104 | 4.5421 | 5.1742 | 12.3908 | 14.0178 | 21.6247 | 26.799 | 0.01
5.7043 | 8.1078 | 1.9307 | 2.0488 | 2.4414 | 2.8841 | 7.0186 | 3.9218 | 13.8121 | 15.8609 | 22.8795 | 26.8013 | 5.7043 | 8.1078 | 1.9307 | 2.0488 | 2.4414 | 2.8841 | 7.0286 | 3.9218 | 13.8121 | 15.8609 | 22.8895 | 26.8113 | 0.01
6.4407 | 8.2046 | 1.8381 | 1.9311 | 0.72164 | 3.6422 | 6.8676 | 5.4518 | 14.6453 | 16.5764 | 23.444 | 28.8957 | 6.4407 | 8.2046 | 1.8381 | 1.9311 | 0.72164 | 3.6422 | 6.8776 | 5.4518 | 14.6453 | 16.5764 | 23.454 | 28.9057 | 0.01
4.4931 | 8.0157 | 2.0415 | 1.9906 | 2.5107 | 2.8525 | 5.3362 | 6.8756 | 12.5088 | 14.4994 | 19.8626 | 26.7383 | 4.4931 | 8.0157 | 2.0415 | 1.9906 | 2.5107 | 2.8525 | 5.3462 | 6.8756 | 12.5088 | 14.4994 | 19.8626 | 26.7383 | 0.01
5.2027 | 8.5972 | 2.0355 | 1.6498 | 2.7468 | 3.1262 | 6.6698 | 4.6639 | 13.7999 | 15.4497 | 22.1195 | 26.7834 | 5.2027 | 8.5972 | 2.0355 | 1.6498 | 2.7468 | 3.1262 | 6.6798 | 4.6639 | 13.7999 | 15.4497 | 22.1295 | 26.7934 | 0.01
5.0412 | 7.6341 | 1.8956 | 2.8749 | 2.8979 | 1.6485 | 6.7146 | 4.7747 | 12.6753 | 15.5502 | 22.2648 | 27.0396 | 5.0412 | 7.6341 | 1.8956 | 2.8749 | 2.8979 | 1.6485 | 6.7246 | 4.7747 | 12.6753 | 15.5502 | 22.2748 | 27.0496 | 0.01
5.401 | 7.6306 | 1.9863 | 1.9025 | 4.4823 | 2.084 | 5.8527 | 5.1283 | 13.0316 | 14.934 | 21.5003 | 26.6287 | 5.401 | 7.6306 | 1.9863 | 1.9025 | 4.4823 | 2.084 | 5.8627 | 5.1283 | 13.0316 | 14.934 | 21.5003 | 26.6287 | 0.01
5.8478 | 5.3191 | 1.5982 | 2.1686 | 2.2222 | 3.2361 | 7.745 | 6.5779 | 11.1669 | 13.3354 | 21.0805 | 27.6584 | 5.8478 | 5.3191 | 1.5982 | 2.1686 | 2.2222 | 3.2361 | 7.755 | 6.5779 | 11.1669 | 13.3354 | 21.0905 | 27.6684 | 0.01
6.8456 | 8.4528 | 1.8429 | 1.9032 | 3.8413 | 3.7121 | 5.2823 | 2.1553 | 15.2983 | 17.2015 | 24.7549 | 26.9103 | 6.8456 | 8.4528 | 1.8429 | 1.9032 | 3.8413 | 3.7121 | 5.2923 | 2.1553 | 15.2983 | 17.2015 | 24.7549 | 26.9103 | 0.01
5.8842 | 8.2141 | 1.9955 | 2.1009 | 3.1826 | 1.7155 | 7.1066 | 5.3518 | 14.0984 | 16.1993 | 23.3059 | 28.6578 | 5.8842 | 8.2141 | 1.9955 | 2.1009 | 3.1826 | 1.7155 | 7.1166 | 5.3518 | 14.0984 | 16.1993 | 23.3159 | 28.6678 | 0.01
6.5869 | 4.6408 | 1.9718 | 2.2349 | 3.4008 | 2.498 | 2.8242 | 3.2045 | 11.2277 | 13.4626 | 19.3614 | 22.5659 | 6.5869 | 4.6408 | 1.9718 | 2.2349 | 3.4008 | 2.498 | 2.8342 | 3.2045 | 11.2277 | 13.4626 | 19.3614 | 22.5659 | 0.01
7.298 | 9.1562 | 2.1111 | 1.6351 | 4.0171 | 2.554 | 7.4042 | 4.5071 | 16.4542 | 18.0893 | 25.4935 | 30.0006 | 7.298 | 9.1562 | 2.1111 | 1.6351 | 4.0171 | 2.554 | 7.4142 | 4.5071 | 16.4542 | 18.0893 | 25.5035 | 30.0106 | 0.01
5.8946 | 6.2094 | 2.0821 | 2.0685 | 3.0785 | 3.6701 | 3.2617 | 6.0279 | 12.104 | 14.1725 | 20.9211 | 26.949 | 5.8946 | 6.2094 | 2.0821 | 2.0685 | 3.0785 | 3.6701 | 3.2717 | 6.0279 | 12.104 | 14.1725 | 20.9211 | 26.949 | 0.01
6.4388 | 7.8588 | 2.1006 | 2.2737 | 2.9688 | 3.6937 | 8.2738 | 5.1473 | 14.2975 | 16.5712 | 24.845 | 29.9923 | 6.4388 | 7.8588 | 2.1006 | 2.2737 | 2.9688 | 3.6937 | 8.2838 | 5.1473 | 14.2975 | 16.5712 | 24.855 | 30.0023 | 0.01
5.4645 | 7.8779 | 1.7151 | 1.9746 | 3.647 | 2.6941 | 4.391 | 4.8531 | 13.3424 | 15.317 | 21.6581 | 26.5112 | 5.4645 | 7.8779 | 1.7151 | 1.9746 | 3.647 | 2.6941 | 4.401 | 4.8531 | 13.3424 | 15.317 | 21.6581 | 26.5112 | 0.01
6.4658 | 8.1021 | 2.0552 | 1.4979 | 3.311 | 2.9427 | 5.093 | 4.0202 | 14.5679 | 16.0657 | 22.3195 | 26.3396 | 6.4658 | 8.1021 | 2.0552 | 1.4979 | 3.311 | 2.9427 | 5.103 | 4.0202 | 14.5679 | 16.0657 | 22.3195 | 26.3396 | 0.01
6.0284 | 6.8903 | 1.6552 | 2.1315 | 3.066 | 3.4006 | 5.2357 | 4.7963 | 12.9187 | 15.0502 | 21.5167 | 26.313 | 6.0284 | 6.8903 | 1.6552 | 2.1315 | 3.066 | 3.4006 | 5.2457 | 4.7963 | 12.9187 | 15.0502 | 21.5167 | 26.313 | 0.01
4.7039 | 8.6637 | 2.2566 | 1.9351 | 2.3451 | 3.6446 | 6.4888 | 3.6498 | 13.3676 | 15.3027 | 21.7915 | 25.4412 | 4.7039 | 8.6637 | 2.2566 | 1.9351 | 2.3451 | 3.6446 | 6.4988 | 3.6498 | 13.3676 | 15.3027 | 21.8015 | 25.4512 | 0.01
5.0713 | 9.5887 | 2.0606 | 2.1785 | 5.2593 | 2.8601 | 7.069 | 6.2738 | 14.6599 | 16.8385 | 24.9578 | 31.2316 | 5.0713 | 9.5887 | 2.0606 | 2.1785 | 5.2593 | 2.8601 | 7.079 | 6.2738 | 14.6599 | 16.8385 | 24.9578 | 31.2316 | 0.01
6.5688 | 6.9904 | 2.1534 | 2.0153 | 3.7691 | 2.6055 | 7.0108 | 6.5443 | 13.5593 | 15.5745 | 22.5854 | 29.1296 | 6.5688 | 6.9904 | 2.1534 | 2.0153 | 3.7691 | 2.6055 | 7.0208 | 6.5443 | 13.5593 | 15.5745 | 22.5954 | 29.1396 | 0.01
6.4756 | 5.9269 | 1.8803 | 1.9076 | 3.503 | 2.6974 | 6.5411 | 5.208 | 12.4025 | 14.3101 | 20.8512 | 26.0592 | 6.4756 | 5.9269 | 1.8803 | 1.9076 | 3.503 | 2.6974 | 6.5511 | 5.208 | 12.4025 | 14.3101 | 20.8612 | 26.0692 | 0.01
6.3422 | 9.588 | 2.0493 | 1.8346 | 4.0615 | 3.1989 | 6.2465 | 4.1916 | 15.9303 | 17.7648 | 25.0252 | 29.2168 | 6.3422 | 9.588 | 2.0493 | 1.8346 | 4.0615 | 3.1989 | 6.2565 | 4.1916 | 15.9303 | 17.7648 | 25.0252 | 29.2168 | 0.01
5.6296 | 7.6621 | 1.9932 | 2.3879 | 4.1062 | 3.9576 | 5.7217 | 4.586 | 13.2918 | 15.6797 | 23.7436 | 28.3295 | 5.6296 | 7.6621 | 1.9932 | 2.3879 | 4.1062 | 3.9576 | 5.7317 | 4.586 | 13.2918 | 15.6797 | 23.7436 | 28.3295 | 0.01
6.5853 | 7.0078 | 2.2262 | 1.6147 | 2.1791 | 3.0015 | 9.6734 | 4.6965 | 13.5931 | 15.2078 | 24.8812 | 29.5777 | 6.5853 | 7.0078 | 2.2262 | 1.6147 | 2.1791 | 3.0015 | 9.6834 | 4.6965 | 13.5931 | 15.2078 | 24.8912 | 29.5877 | 0.01
5.506 | 5.9831 | 1.8278 | 2.1599 | 4.8746 | 3.4559 | 7.0275 | 3.3585 | 11.4891 | 13.649 | 21.9794 | 25.3379 | 5.506 | 5.9831 | 1.8278 | 2.1599 | 4.8746 | 3.4559 | 7.0375 | 3.3585 | 11.4891 | 13.649 | 21.9794 | 25.3379 | 0.01
5.3736 | 5.1012 | 1.9469 | 2.4492 | 1.9353 | 2.6459 | 6.7079 | 4.5977 | 10.4748 | 12.924 | 19.6319 | 24.2296 | 5.3736 | 5.1012 | 1.9469 | 2.4492 | 1.9353 | 2.6459 | 6.7179 | 4.5977 | 10.4748 | 12.924 | 19.6419 | 24.2396 | 0.01
6.6809 | 5.7406 | 2.3738 | 2.1907 | 2.3953 | 3.5341 | 6.2421 | 6.3157 | 12.4215 | 14.6122 | 20.8543 | 27.17 | 6.6809 | 5.7406 | 2.3738 | 2.1907 | 2.3953 | 3.5341 | 6.2521 | 6.3157 | 12.4215 | 14.6122 | 20.8643 | 27.18 | 0.01
5.8659 | 10.1544 | 1.7907 | 1.9973 | 2.4549 | 3.0373 | 6.7257 | 5.8437 | 16.0203 | 18.0176 | 24.7433 | 30.587 | 5.8659 | 10.1544 | 1.7907 | 1.9973 | 2.4549 | 3.0373 | 6.7357 | 5.8437 | 16.0203 | 18.0176 | 24.7533 | 30.597 | 0.01
5.0425 | 9.0076 | 1.7749 | 1.7818 | 2.8156 | 3.1888 | 6.0219 | 3.982 | 14.0501 | 15.8319 | 21.8538 | 25.8358 | 5.0425 | 9.0076 | 1.7749 | 1.7818 | 2.8156 | 3.1888 | 6.0319 | 3.982 | 14.0501 | 15.8319 | 21.8638 | 25.8458 | 0.01
6.235 | 7.9306 | 1.9869 | 2.3562 | 3.4932 | 3.0924 | 5.5328 | 4.0271 | 14.1656 | 16.5218 | 23.1074 | 27.1345 | 6.235 | 7.9306 | 1.9869 | 2.3562 | 3.4932 | 3.0924 | 5.5428 | 4.0271 | 14.1656 | 16.5218 | 23.1074 | 27.1345 | 0.01
6.5568 | 8.7777 | 2.0167 | 1.6881 | 3.4321 | 3.4001 | 8.4843 | 5.2391 | 15.3345 | 17.0226 | 25.5069 | 30.746 | 6.5568 | 8.7777 | 2.0167 | 1.6881 | 3.4321 | 3.4001 | 8.4943 | 5.2391 | 15.3345 | 17.0226 | 25.5169 | 30.756 | 0.01
5.6592 | 8.9435 | 2.0993 | 2.2802 | 3.4303 | 3.1332 | 6.535 | 5.3148 | 14.6027 | 16.883 | 23.4464 | 28.7612 | 5.6592 | 8.9435 | 2.0993 | 2.2802 | 3.4303 | 3.1332 | 6.545 | 5.3148 | 14.6027 | 16.883 | 23.4464 | 28.7612 | 0.01
6.7476 | 7.6776 | 2.2484 | 2.0151 | 3.4781 | 2.439 | 6.2979 | 5.3064 | 14.4252 | 16.4403 | 22.7382 | 28.0446 | 6.7476 | 7.6776 | 2.2484 | 2.0151 | 3.4781 | 2.439 | 6.3079 | 5.3064 | 14.4252 | 16.4403 | 22.7482 | 28.0546 | 0.01
6.5822 | 7.7388 | 2.1207 | 1.8583 | 3.3551 | 3.2664 | 7.2284 | 4.9042 | 14.3211 | 16.1793 | 23.4077 | 28.3119 | 6.5822 | 7.7388 | 2.1207 | 1.8583 | 3.3551 | 3.2664 | 7.2384 | 4.9042 | 14.3211 | 16.1793 | 23.4177 | 28.3219 | 0.01
7.1405 | 7.9286 | 1.5477 | 2.0925 | 1.7002 | 2.4122 | 8.9732 | 5.2195 | 15.0692 | 17.1617 | 26.1348 | 31.3543 | 7.1405 | 7.9286 | 1.5477 | 2.0925 | 1.7002 | 2.4122 | 8.9832 | 5.2195 | 15.0692 | 17.1617 | 26.1448 | 31.3643 | 0.01
5.8659 | 9.0515 | 2.3447 | 1.5639 | 2.2376 | 4.1795 | 6.5368 | 5.9486 | 14.9174 | 16.4813 | 23.0181 | 28.9667 | 5.8659 | 9.0515 | 2.3447 | 1.5639 | 2.2376 | 4.1795 | 6.5468 | 5.9486 | 14.9174 | 16.4813 | 23.0281 | 28.9767 | 0.01
6.6236 | 7.7524 | 2.1251 | 2.2301 | 2.8311 | 2.9608 | 8.2733 | 3.6549 | 14.376 | 16.6062 | 24.8795 | 28.5344 | 6.6236 | 7.7524 | 2.1251 | 2.2301 | 2.8311 | 2.9608 | 8.2833 | 3.6549 | 14.376 | 16.6062 | 24.8895 | 28.5444 | 0.01
6.5182 | 7.0051 | 1.5823 | 2.0394 | 2.3874 | 2.6535 | 6.6196 | 7.0347 | 13.5233 | 15.5628 | 22.1824 | 29.2171 | 6.5182 | 7.0051 | 1.5823 | 2.0394 | 2.3874 | 2.6535 | 6.6296 | 7.0347 | 13.5233 | 15.5628 | 22.1924 | 29.2271 | 0.01
7.0852 | 11.1229 | 1.9799 | 2.2969 | 2.0111 | 2.3301 | 6.3017 | 7.0752 | 18.2081 | 20.505 | 26.8067 | 33.8819 | 7.0852 | 11.1229 | 1.9799 | 2.2969 | 2.0111 | 2.3301 | 6.3117 | 7.0752 | 18.2081 | 20.505 | 26.8167 | 33.8919 | 0.01
5.8233 | 9.8025 | 1.9193 | 2.2735 | 2.6602 | 3.3229 | 9.6392 | 6.2477 | 15.6258 | 17.8993 | 27.5385 | 33.7862 | 5.8233 | 9.8025 | 1.9193 | 2.2735 | 2.6602 | 3.3229 | 9.6492 | 6.2477 | 15.6258 | 17.8993 | 27.5485 | 33.7962 | 0.01
4.8625 | 8.9626 | 1.8922 | 2.3354 | 2.6126 | 2.6529 | 7.7616 | 7.7843 | 13.8252 | 16.1606 | 23.9222 | 31.7065 | 4.8625 | 8.9626 | 1.8922 | 2.3354 | 2.6126 | 2.6529 | 7.7716 | 7.7843 | 13.8252 | 16.1606 | 23.9322 | 31.7165 | 0.01
5.2859 | 9.1998 | 1.9781 | 2.1777 | 2.7251 | 2.4297 | 6.8172 | 3.0563 | 14.4857 | 16.6634 | 23.4806 | 26.5369 | 5.2859 | 9.1998 | 1.9781 | 2.1777 | 2.7251 | 2.4297 | 6.8272 | 3.0563 | 14.4857 | 16.6634 | 23.4906 | 26.5469 | 0.01
5.1961 | 9.2655 | 2.3447 | 2.1878 | 2.8414 | 3.2045 | 4.591 | 3.6506 | 14.4616 | 16.6494 | 22.6953 | 26.3459 | 5.1961 | 9.2655 | 2.3447 | 2.1878 | 2.8414 | 3.2045 | 4.601 | 3.6506 | 14.4616 | 16.6494 | 22.6953 | 26.3459 | 0.01
4.9939 | 9.0486 | 2.2487 | 2.1773 | 4.0915 | 2.8234 | 8.7602 | 4.9361 | 14.0425 | 16.2198 | 24.98 | 29.9161 | 4.9939 | 9.0486 | 2.2487 | 2.1773 | 4.0915 | 2.8234 | 8.7702 | 4.9361 | 14.0425 | 16.2198 | 24.99 | 29.9261 | 0.01
5.6615 | 10.2199 | 1.7219 | 2.4756 | 2.0187 | 3.1911 | 5.895 | 2.9997 | 15.8813 | 18.357 | 24.252 | 27.2516 | 5.6615 | 10.2199 | 1.7219 | 2.4756 | 2.0187 | 3.1911 | 5.905 | 2.9997 | 15.8813 | 18.357 | 24.262 | 27.2616 | 0.01
6.0392 | 9.205 | 1.7339 | 1.9762 | 2.3115 | 2.4951 | 3.5542 | 6.7031 | 15.2443 | 17.2205 | 22.0271 | 28.7302 | 6.0392 | 9.205 | 1.7339 | 1.9762 | 2.3115 | 2.4951 | 3.5642 | 6.7031 | 15.2443 | 17.2205 | 22.0271 | 28.7302 | 0.01
6.1086 | 7.1061 | 1.785 | 2.072 | 2.7358 | 3.4096 | 7.8894 | 5.9476 | 13.2147 | 15.2867 | 23.1761 | 29.1237 | 6.1086 | 7.1061 | 1.785 | 2.072 | 2.7358 | 3.4096 | 7.8994 | 5.9476 | 13.2147 | 15.2867 | 23.1861 | 29.1337 | 0.01
6.3482 | 5.8719 | 2.1946 | 2.2782 | 2.1577 | 2.6006 | 6.0799 | 5.1446 | 12.2201 | 14.4983 | 20.5783 | 25.7229 | 6.3482 | 5.8719 | 2.1946 | 2.2782 | 2.1577 | 2.6006 | 6.0899 | 5.1446 | 12.2201 | 14.4983 | 20.5883 | 25.7329 | 0.01
5.4618 | 7.9451 | 2.0004 | 2.144 | 2.0976 | 3.5121 | 7.1823 | 4.277 | 13.4069 | 15.5509 | 22.7332 | 27.0102 | 5.4618 | 7.9451 | 2.0004 | 2.144 | 2.0976 | 3.5121 | 7.1923 | 4.277 | 13.4069 | 15.5509 | 22.7432 | 27.0202 | 0.01
5.6515 | 10.0316 | 2.3184 | 2.3189 | 1.5009 | 3.8589 | 7.183 | 4.5241 | 15.6831 | 18.002 | 25.1849 | 29.709 | 5.6515 | 10.0316 | 2.3184 | 2.3189 | 1.5009 | 3.8589 | 7.193 | 4.5241 | 15.6831 | 18.002 | 25.1949 | 29.719 | 0.01
5.7939 | 9.7755 | 2.1317 | 1.9182 | 2.6154 | 4.1325 | 8.1209 | 2.2303 | 15.5695 | 17.4877 | 25.6086 | 27.8389 | 5.7939 | 9.7755 | 2.1317 | 1.9182 | 2.6154 | 4.1325 | 8.1309 | 2.2303 | 15.5695 | 17.4877 | 25.6186 | 27.8489 | 0.01
6.9336 | 8.4079 | 1.7189 | 1.7193 | 4.2145 | 3.9016 | 7.9246 | 7.6163 | 15.3416 | 17.0609 | 25.1769 | 32.7933 | 6.9336 | 8.4079 | 1.7189 | 1.7193 | 4.2145 | 3.9016 | 7.9346 | 7.6163 | 15.3416 | 17.0609 | 25.1769 | 32.7933 | 0.01
5.8294 | 6.394 | 2.3871 | 2.0105 | 1.3169 | 2.6005 | 7.1911 | 6.0534 | 12.2234 | 14.2338 | 21.4249 | 27.4783 | 5.8294 | 6.394 | 2.3871 | 2.0105 | 1.3169 | 2.6005 | 7.2011 | 6.0534 | 12.2234 | 14.2338 | 21.4349 | 27.4883 | 0.01
5.019 | 9.2003 | 2.1474 | 1.8903 | 4.7394 | 3.1807 | 7.9819 | 5.371 | 14.2193 | 16.1096 | 24.0916 | 29.4626 | 5.019 | 9.2003 | 2.1474 | 1.8903 | 4.7394 | 3.1807 | 7.9919 | 5.371 | 14.2193 | 16.1096 | 24.1016 | 29.4726 | 0.01
7.2191 | 8.5041 | 2.2983 | 2.7174 | 2.8843 | 2.5069 | 6.9892 | 4.1251 | 15.7231 | 18.4406 | 25.4297 | 29.5548 | 7.2191 | 8.5041 | 2.2983 | 2.7174 | 2.8843 | 2.5069 | 6.9992 | 4.1251 | 15.7231 | 18.4406 | 25.4397 | 29.5648 | 0.01
5.3353 | 7.3937 | 1.9248 | 2.3138 | 3.1891 | 3.8876 | 8.7602 | 3.0847 | 12.729 | 15.0429 | 23.8031 | 26.8878 | 5.3353 | 7.3937 | 1.9248 | 2.3138 | 3.1891 | 3.8876 | 8.7702 | 3.0847 | 12.729 | 15.0429 | 23.8131 | 26.8978 | 0.01
5.6604 | 6.6287 | 1.8178 | 2.1646 | 4.9695 | 2.4511 | 6.5523 | 5.7511 | 12.2892 | 14.4537 | 21.8743 | 27.6254 | 5.6604 | 6.6287 | 1.8178 | 2.1646 | 4.9695 | 2.4511 | 6.5623 | 5.7511 | 12.2892 | 14.4537 | 21.8743 | 27.6254 | 0.01
5.4511 | 8.9224 | 1.9814 | 1.6785 | 2.2882 | 1.4682 | 7.7135 | 4.7253 | 14.3735 | 16.0521 | 23.7656 | 28.4909 | 5.4511 | 8.9224 | 1.9814 | 1.6785 | 2.2882 | 1.4682 | 7.7235 | 4.7253 | 14.3735 | 16.0521 | 23.7756 | 28.5009 | 0.01
5.7623 | 7.5418 | 2.1052 | 1.9141 | 2.4493 | 3.4347 | 7.269 | 4.3611 | 13.3041 | 15.2182 | 22.4871 | 26.8482 | 5.7623 | 7.5418 | 2.1052 | 1.9141 | 2.4493 | 3.4347 | 7.279 | 4.3611 | 13.3041 | 15.2182 | 22.4971 | 26.8582 | 0.01
5.2551 | 8.1867 | 1.7479 | 2.3189 | 2.7686 | 2.8504 | 6.5848 | 4.1658 | 13.4418 | 15.7606 | 22.3454 | 26.5112 | 5.2551 | 8.1867 | 1.7479 | 2.3189 | 2.7686 | 2.8504 | 6.5948 | 4.1658 | 13.4418 | 15.7606 | 22.3554 | 26.5212 | 0.01
5.3205 | 7.865 | 2.3324 | 2.259 | 2.5717 | 2.801 | 6.7125 | 2.7178 | 13.1855 | 15.4445 | 22.157 | 24.8748 | 5.3205 | 7.865 | 2.3324 | 2.259 | 2.5717 | 2.801 | 6.7225 | 2.7178 | 13.1855 | 15.4445 | 22.167 | 24.8848 | 0.01
5.8542 | 7.4998 | 2.009 | 1.9823 | 4.3226 | 2.9336 | 7.0267 | 6.9006 | 13.354 | 15.3363 | 22.5924 | 29.4931 | 5.8542 | 7.4998 | 2.009 | 1.9823 | 4.3226 | 2.9336 | 7.0367 | 6.9006 | 13.354 | 15.3363 | 22.5924 | 29.4931 | 0.01
5.6726 | 7.0144 | 1.7841 | 2.1043 | 1.6195 | 3.6542 | 5.9031 | 4.8869 | 12.6871 | 14.7914 | 20.6944 | 25.5813 | 5.6726 | 7.0144 | 1.7841 | 2.1043 | 1.6195 | 3.6542 | 5.9131 | 4.8869 | 12.6871 | 14.7914 | 20.7044 | 25.5913 | 0.01
6.4665 | 7.8164 | 2.2119 | 2.4917 | 3.0846 | 2.5715 | 4.7874 | 4.6774 | 14.2829 | 16.7746 | 22.4307 | 27.1081 | 6.4665 | 7.8164 | 2.2119 | 2.4917 | 3.0846 | 2.5715 | 4.7974 | 4.6774 | 14.2829 | 16.7746 | 22.4307 | 27.1081 | 0.01
5.9324 | 7.3061 | 2.1924 | 1.7694 | 3.6643 | 2.1259 | 5.7659 | 5.9953 | 13.2385 | 15.0079 | 20.7981 | 26.7934 | 5.9324 | 7.3061 | 2.1924 | 1.7694 | 3.6643 | 2.1259 | 5.7759 | 5.9953 | 13.2385 | 15.0079 | 20.7981 | 26.7934 | 0.01
6.3128 | 8.3043 | 1.9675 | 2.0057 | 2.7684 | 4.0061 | 6.1561 | 5.0196 | 14.6171 | 16.6228 | 23.3973 | 28.4169 | 6.3128 | 8.3043 | 1.9675 | 2.0057 | 2.7684 | 4.0061 | 6.1661 | 5.0196 | 14.6171 | 16.6228 | 23.3973 | 28.4169 | 0.01
6.1819 | 7.9051 | 2.1871 | 2.0994 | 1.3723 | 3.6145 | 8.1663 | 5.2915 | 14.087 | 16.1863 | 24.3526 | 29.6441 | 6.1819 | 7.9051 | 2.1871 | 2.0994 | 1.3723 | 3.6145 | 8.1763 | 5.2915 | 14.087 | 16.1863 | 24.3626 | 29.6541 | 0.01
5.1127 | 5.8623 | 1.7968 | 2.5185 | 1.9385 | 4.2249 | 10.0089 | 4.2026 | 10.975 | 13.4935 | 23.5024 | 27.705 | 5.1127 | 5.8623 | 1.7968 | 2.5185 | 1.9385 | 4.2249 | 10.0189 | 4.2026 | 10.975 | 13.4935 | 23.5124 | 27.715 | 0.01
5.1886 | 8.453 | 2.227 | 1.9764 | 3.1922 | 2.811 | 5.4787 | 4.2074 | 13.6416 | 15.618 | 21.6212 | 25.8286 | 5.1886 | 8.453 | 2.227 | 1.9764 | 3.1922 | 2.811 | 5.4887 | 4.2074 | 13.6416 | 15.618 | 21.6212 | 25.8286 | 0.01
5.8664 | 8.0252 | 1.9978 | 1.7598 | 2.5375 | 3.1467 | 6.6463 | 5.252 | 13.8916 | 15.6515 | 22.2977 | 27.5498 | 5.8664 | 8.0252 | 1.9978 | 1.7598 | 2.5375 | 3.1467 | 6.6563 | 5.252 | 13.8916 | 15.6515 | 22.3077 | 27.5598 | 0.01
5.7414 | 8.6817 | 1.7685 | 1.9035 | 4.6624 | 3.5612 | 7.202 | 4.5212 | 14.4232 | 16.3267 | 24.5503 | 29.0715 | 5.7414 | 8.6817 | 1.7685 | 1.9035 | 4.6624 | 3.5612 | 7.212 | 4.5212 | 14.4232 | 16.3267 | 24.5503 | 29.0715 | 0.01
5.684 | 6.4243 | 2.1478 | 2.0487 | 5.2057 | 3.1586 | 5.4001 | 3.3054 | 12.1082 | 14.157 | 22.5213 | 25.8267 | 5.684 | 6.4243 | 2.1478 | 2.0487 | 5.2057 | 3.1586 | 5.4101 | 3.3054 | 12.1082 | 14.157 | 22.5213 | 25.8267 | 0.01
5.982 | 6.7944 | 2.0784 | 2.3985 | 1.1948 | 4.1801 | 7.3153 | 5.0883 | 12.7764 | 15.1749 | 22.4901 | 27.5785 | 5.982 | 6.7944 | 2.0784 | 2.3985 | 1.1948 | 4.1801 | 7.3253 | 5.0883 | 12.7764 | 15.1749 | 22.5001 | 27.5885 | 0.01
5.7375 | 8.9363 | 2.1673 | 2.2433 | 1.978 | 3.8759 | 5.9494 | 5.272 | 14.6737 | 16.917 | 22.8664 | 28.1384 | 5.7375 | 8.9363 | 2.1673 | 2.2433 | 1.978 | 3.8759 | 5.9594 | 5.272 | 14.6737 | 16.917 | 22.8764 | 28.1484 | 0.01
5.0977 | 6.3457 | 2.1064 | 2.4243 | 2.5613 | 3.5054 | 3.6967 | 5.2071 | 11.4435 | 13.8678 | 19.9345 | 25.1416 | 5.0977 | 6.3457 | 2.1064 | 2.4243 | 2.5613 | 3.5054 | 3.7067 | 5.2071 | 11.4435 | 13.8678 | 19.9345 | 25.1416 | 0.01
5.2068 | 10.5267 | 1.8937 | 1.6587 | 3.5964 | 3.336 | 8.9145 | 4.9115 | 15.7335 | 17.3922 | 26.3066 | 31.2181 | 5.2068 | 10.5267 | 1.8937 | 1.6587 | 3.5964 | 3.336 | 8.9245 | 4.9115 | 15.7335 | 17.3922 | 26.3166 | 31.2281 | 0.01
6.383 | 8.5166 | 1.7331 | 1.9305 | 3.5687 | 3.3744 | 8.2902 | 5.9879 | 14.8997 | 16.8302 | 25.1204 | 31.1083 | 6.383 | 8.5166 | 1.7331 | 1.9305 | 3.5687 | 3.3744 | 8.3002 | 5.9879 | 14.8997 | 16.8302 | 25.1304 | 31.1183 | 0.01
6.6218 | 7.5625 | 2.4003 | 1.8429 | 4.1666 | 3.6512 | 6.6406 | 5.2781 | 14.1843 | 16.0272 | 23.845 | 29.1231 | 6.6218 | 7.5625 | 2.4003 | 1.8429 | 4.1666 | 3.6512 | 6.6506 | 5.2781 | 14.1843 | 16.0272 | 23.845 | 29.1231 | 0.01
5.4963 | 8.0576 | 1.5578 | 2.094 | 3.0555 | 1.621 | 5.3753 | 6.0541 | 13.554 | 15.648 | 21.0233 | 27.0774 | 5.4963 | 8.0576 | 1.5578 | 2.094 | 3.0555 | 1.621 | 5.3853 | 6.0541 | 13.554 | 15.648 | 21.0333 | 27.0874 | 0.01
5.2627 | 5.5264 | 2.1933 | 2.0441 | 1.5644 | 2.3647 | 6.4781 | 3.2737 | 10.7891 | 12.8331 | 19.3112 | 22.5849 | 5.2627 | 5.5264 | 2.1933 | 2.0441 | 1.5644 | 2.3647 | 6.4881 | 3.2737 | 10.7891 | 12.8331 | 19.3212 | 22.5949 | 0.01
6.9791 | 8.4094 | 1.6709 | 2.3072 | 3.8697 | 4.0212 | 8.3604 | 5.9102 | 15.3885 | 17.6956 | 26.056 | 31.9662 | 6.9791 | 8.4094 | 1.6709 | 2.3072 | 3.8697 | 4.0212 | 8.3704 | 5.9102 | 15.3885 | 17.6956 | 26.066 | 31.9762 | 0.01
6.7279 | 10.0152 | 1.9956 | 2.23 | 2.7262 | 2.9961 | 6.4246 | 6.6411 | 16.7432 | 18.9732 | 25.3978 | 32.0388 | 6.7279 | 10.0152 | 1.9956 | 2.23 | 2.7262 | 2.9961 | 6.4346 | 6.6411 | 16.7432 | 18.9732 | 25.4078 | 32.0488 | 0.01
6.3891 | 8.8258 | 1.6393 | 2.3079 | 4.4115 | 3.1699 | 7.958 | 3.4131 | 15.2149 | 17.5229 | 25.4809 | 28.894 | 6.3891 | 8.8258 | 1.6393 | 2.3079 | 4.4115 | 3.1699 | 7.968 | 3.4131 | 15.2149 | 17.5229 | 25.4909 | 28.904 | 0.01
6.077 | 7.8764 | 2.2207 | 2.2358 | 1.8004 | 3.0995 | 5.1385 | 4.464 | 13.9535 | 16.1892 | 21.3277 | 25.7917 | 6.077 | 7.8764 | 2.2207 | 2.2358 | 1.8004 | 3.0995 | 5.1485 | 4.464 | 13.9535 | 16.1892 | 21.3377 | 25.8017 | 0.01
5.775 | 7.5597 | 1.887 | 2.2993 | 3.882 | 3.4382 | 6.7295 | 3.7807 | 13.3346 | 15.6339 | 22.9541 | 26.7348 | 5.775 | 7.5597 | 1.887 | 2.2993 | 3.882 | 3.4382 | 6.7395 | 3.7807 | 13.3346 | 15.6339 | 22.9541 | 26.7348 | 0.01
6.3344 | 8.3545 | 2.264 | 2.1386 | 3.0643 | 3.1601 | 7.4097 | 3.0363 | 14.6889 | 16.8274 | 24.2371 | 27.2734 | 6.3344 | 8.3545 | 2.264 | 2.1386 | 3.0643 | 3.1601 | 7.4197 | 3.0363 | 14.6889 | 16.8274 | 24.2471 | 27.2834 | 0.01
5.9489 | 9.9702 | 1.6921 | 2.2855 | 3.1518 | 2.7785 | 8.6653 | 6.0916 | 15.9191 | 18.2046 | 26.8699 | 32.9615 | 5.9489 | 9.9702 | 1.6921 | 2.2855 | 3.1518 | 2.7785 | 8.6753 | 6.0916 | 15.9191 | 18.2046 | 26.8799 | 32.9715 | 0.01
6.6125 | 8.2032 | 1.6558 | 2.2878 | 3.4272 | 1.9268 | 7.1056 | 6.4093 | 14.8157 | 17.1035 | 24.209 | 30.6183 | 6.6125 | 8.2032 | 1.6558 | 2.2878 | 3.4272 | 1.9268 | 7.1156 | 6.4093 | 14.8157 | 17.1035 | 24.219 | 30.6283 | 0.01
6.7451 | 6.2629 | 2.1464 | 2.0936 | 5.3968 | 3.0241 | 5.9676 | 6.5904 | 13.008 | 15.1016 | 23.5224 | 30.1128 | 6.7451 | 6.2629 | 2.1464 | 2.0936 | 5.3968 | 3.0241 | 5.9776 | 6.5904 | 13.008 | 15.1016 | 23.5224 | 30.1128 | 0.01
5.7355 | 5.9483 | 1.7018 | 2.3257 | 3.7755 | 2.0024 | 6.7551 | 5.9145 | 11.6838 | 14.0095 | 20.7646 | 26.6791 | 5.7355 | 5.9483 | 1.7018 | 2.3257 | 3.7755 | 2.0024 | 6.7651 | 5.9145 | 11.6838 | 14.0095 | 20.7746 | 26.6891 | 0.01
5.8095 | 8.5291 | 2.1727 | 2.2503 | 3.0751 | 2.9075 | 10.7281 | 3.0182 | 14.3387 | 16.589 | 27.3172 | 30.3353 | 5.8095 | 8.5291 | 2.1727 | 2.2503 | 3.0751 | 2.9075 | 10.7381 | 3.0182 | 14.3387 | 16.589 | 27.3272 | 30.3453 | 0.01
5.8677 | 7.6087 | 2.4056 | 1.533 | 2.0403 | 2.2886 | 9.9803 | 6.3877 | 13.4763 | 15.0093 | 24.9896 | 31.3773 | 5.8677 | 7.6087 | 2.4056 | 1.533 | 2.0403 | 2.2886 | 9.9903 | 6.3877 | 13.4763 | 15.0093 | 24.9996 | 31.3873 | 0.01
6.0699 | 5.8903 | 2.2491 | 1.974 | 2.7162 | 3.1399 | 6.7647 | 3.4883 | 11.9602 | 13.9342 | 20.6988 | 24.1872 | 6.0699 | 5.8903 | 2.2491 | 1.974 | 2.7162 | 3.1399 | 6.7747 | 3.4883 | 11.9602 | 13.9342 | 20.7088 | 24.1972 | 0.01
6.1546 | 8.9066 | 2.0356 | 2.5005 | 2.8607 | 3.9427 | 5.5737 | 6.3824 | 15.0612 | 17.5616 | 24.365 | 30.7473 | 6.1546 | 8.9066 | 2.0356 | 2.5005 | 2.8607 | 3.9427 | 5.5837 | 6.3824 | 15.0612 | 17.5616 | 24.365 | 30.7473 | 0.01
7.3682 | 7.1919 | 2.0579 | 1.5043 | 2.363 | 2.3792 | 4.8901 | 7.0885 | 14.5601 | 16.0644 | 20.9545 | 28.043 | 7.3682 | 7.1919 | 2.0579 | 1.5043 | 2.363 | 2.3792 | 4.9001 | 7.0885 | 14.5601 | 16.0644 | 20.9645 | 28.053 | 0.01
6.7864 | 5.7075 | 2.1297 | 2.0584 | 4.68 | 3.0373 | 5.4584 | 5.7351 | 12.4939 | 14.5523 | 22.2696 | 28.0046 | 6.7864 | 5.7075 | 2.1297 | 2.0584 | 4.68 | 3.0373 | 5.4684 | 5.7351 | 12.4939 | 14.5523 | 22.2696 | 28.0046 | 0.01
5.5287 | 9.0623 | 2.0719 | 2.0472 | 3.3543 | 3.1263 | 7.6377 | 3.9986 | 14.5911 | 16.6383 | 24.276 | 28.2746 | 5.5287 | 9.0623 | 2.0719 | 2.0472 | 3.3543 | 3.1263 | 7.6477 | 3.9986 | 14.5911 | 16.6383 | 24.286 | 28.2846 | 0.01
6.359 | 9.6617 | 1.968 | 1.8632 | 2.2718 | 3.5484 | 4.6582 | 4.6296 | 16.0206 | 17.8838 | 23.704 | 28.3337 | 6.359 | 9.6617 | 1.968 | 1.8632 | 2.2718 | 3.5484 | 4.6682 | 4.6296 | 16.0206 | 17.8838 | 23.704 | 28.3337 | 0.01
6.0049 | 7.0873 | 1.6881 | 1.6322 | 2.2218 | 3.0077 | 5.8236 | 5.7313 | 13.0922 | 14.7244 | 20.548 | 26.2792 | 6.0049 | 7.0873 | 1.6881 | 1.6322 | 2.2218 | 3.0077 | 5.8336 | 5.7313 | 13.0922 | 14.7244 | 20.558 | 26.2892 | 0.01
6.6386 | 7.7761 | 1.8263 | 1.8983 | 2.476 | 3.6883 | 8.302 | 5.1766 | 14.4147 | 16.313 | 24.615 | 29.7916 | 6.6386 | 7.7761 | 1.8263 | 1.8983 | 2.476 | 3.6883 | 8.312 | 5.1766 | 14.4147 | 16.313 | 24.625 | 29.8016 | 0.01
5.8877 | 6.4478 | 1.8147 | 2.2192 | 2.7679 | 2.41 | 4.9984 | 4.593 | 12.3355 | 14.5548 | 19.7326 | 24.3256 | 5.8877 | 6.4478 | 1.8147 | 2.2192 | 2.7679 | 2.41 | 5.0084 | 4.593 | 12.3355 | 14.5548 | 19.7326 | 24.3256 | 0.01
5.611 | 6.2107 | 1.9501 | 2.0001 | 1.8721 | 3.1358 | 8.4907 | 5.7615 | 11.8217 | 13.8218 | 22.3125 | 28.074 | 5.611 | 6.2107 | 1.9501 | 2.0001 | 1.8721 | 3.1358 | 8.5007 | 5.7615 | 11.8217 | 13.8218 | 22.3225 | 28.084 | 0.01
5.7795 | 7.1157 | 2.1084 | 2.121 | 0.56354 | 2.99 | 10.3059 | 5.5351 | 12.8952 | 15.0163 | 25.3222 | 30.8573 | 5.7795 | 7.1157 | 2.1084 | 2.121 | 0.56354 | 2.99 | 10.3159 | 5.5351 | 12.8952 | 15.0163 | 25.3322 | 30.8673 | 0.01
5.2912 | 8.4993 | 2.1871 | 1.7047 | 2.1941 | 3.0738 | 6.1711 | 6.8023 | 13.7905 | 15.4952 | 21.6663 | 28.4685 | 5.2912 | 8.4993 | 2.1871 | 1.7047 | 2.1941 | 3.0738 | 6.1811 | 6.8023 | 13.7905 | 15.4952 | 21.6763 | 28.4785 | 0.01
6.1929 | 10.5639 | 2.3784 | 1.6208 | 3.5442 | 3.1857 | 8.7952 | 6.2356 | 16.7568 | 18.3775 | 27.1727 | 33.4083 | 6.1929 | 10.5639 | 2.3784 | 1.6208 | 3.5442 | 3.1857 | 8.8052 | 6.2356 | 16.7568 | 18.3775 | 27.1827 | 33.4183 | 0.01
5.736 | 7.2473 | 2.1175 | 1.8018 | 3.1606 | 3.0972 | 8.734 | 6.0688 | 12.9833 | 14.785 | 23.519 | 29.5878 | 5.736 | 7.2473 | 2.1175 | 1.8018 | 3.1606 | 3.0972 | 8.744 | 6.0688 | 12.9833 | 14.785 | 23.529 | 29.5978 | 0.01
5.5365 | 7.6319 | 1.9042 | 1.876 | 2.9179 | 2.2922 | 5.745 | 6.352 | 13.1684 | 15.0444 | 20.7894 | 27.1414 | 5.5365 | 7.6319 | 1.9042 | 1.876 | 2.9179 | 2.2922 | 5.755 | 6.352 | 13.1684 | 15.0444 | 20.7994 | 27.1514 | 0.01
4.5469 | 9.4348 | 1.8732 | 2.0688 | 2.4416 | 2.5182 | 9.5531 | 3.4653 | 13.9817 | 16.0505 | 25.6035 | 29.0689 | 4.5469 | 9.4348 | 1.8732 | 2.0688 | 2.4416 | 2.5182 | 9.5631 | 3.4653 | 13.9817 | 16.0505 | 25.6135 | 29.0789 | 0.01
5.8236 | 9.9041 | 2.279 | 1.9572 | 4.1132 | 2.9236 | 5.1275 | 6.8863 | 15.7276 | 17.6849 | 24.7216 | 31.6079 | 5.8236 | 9.9041 | 2.279 | 1.9572 | 4.1132 | 2.9236 | 5.1375 | 6.8863 | 15.7276 | 17.6849 | 24.7216 | 31.6079 | 0.01
5.4855 | 6.293 | 2.2579 | 1.7364 | 3.2429 | 2.759 | 5.1355 | 3.5738 | 11.7784 | 13.5148 | 19.5167 | 23.0905 | 5.4855 | 6.293 | 2.2579 | 1.7364 | 3.2429 | 2.759 | 5.1455 | 3.5738 | 11.7784 | 13.5148 | 19.5167 | 23.0905 | 0.01
7.0086 | 8.0699 | 1.8882 | 1.7198 | 3.6416 | 3.6925 | 5.5979 | 3.4402 | 15.0785 | 16.7983 | 24.1324 | 27.5726 | 7.0086 | 8.0699 | 1.8882 | 1.7198 | 3.6416 | 3.6925 | 5.6079 | 3.4402 | 15.0785 | 16.7983 | 24.1324 | 27.5726 | 0.01
6.0893 | 10.797 | 1.7078 | 2.0996 | 3.3619 | 5.0406 | 9.9721 | 4.4622 | 16.8863 | 18.9859 | 28.9579 | 33.4201 | 6.0893 | 10.797 | 1.7078 | 2.0996 | 3.3619 | 5.0406 | 9.9821 | 4.4622 | 16.8863 | 18.9859 | 28.9679 | 33.4301 | 0.01
5.5763 | 7.3501 | 2.018 | 1.8214 | 2.934 | 3.6759 | 6.6272 | 5.2273 | 12.9265 | 14.7479 | 21.3751 | 26.6024 | 5.5763 | 7.3501 | 2.018 | 1.8214 | 2.934 | 3.6759 | 6.6372 | 5.2273 | 12.9265 | 14.7479 | 21.3851 | 26.6124 | 0.01
6.4964 | 9.456 | 1.8673 | 1.5706 | 2.3517 | 3.5808 | 7.3847 | 3.9039 | 15.9524 | 17.5229 | 24.9077 | 28.8116 | 6.4964 | 9.456 | 1.8673 | 1.5706 | 2.3517 | 3.5808 | 7.3947 | 3.9039 | 15.9524 | 17.5229 | 24.9177 | 28.8216 | 0.01
6.0881 | 6.131 | 2.0533 | 2.1196 | 4.1276 | 3.5458 | 5.6334 | 4.4333 | 12.219 | 14.3386 | 22.0121 | 26.4453 | 6.0881 | 6.131 | 2.0533 | 2.1196 | 4.1276 | 3.5458 | 5.6434 | 4.4333 | 12.219 | 14.3386 | 22.0121 | 26.4453 | 0.01
6.5116 | 9.2794 | 1.6569 | 2.3865 | 2.1613 | 3.9319 | 7.3281 | 5.0972 | 15.7911 | 18.1776 | 25.5057 | 30.6028 | 6.5116 | 9.2794 | 1.6569 | 2.3865 | 2.1613 | 3.9319 | 7.3381 | 5.0972 | 15.7911 | 18.1776 | 25.5157 | 30.6128 | 0.01
6.0115 | 8.9917 | 2.125 | 2.4958 | 0.92213 | 3.3839 | 6.609 | 2.8847 | 15.0032 | 17.499 | 24.108 | 26.9927 | 6.0115 | 8.9917 | 2.125 | 2.4958 | 0.92213 | 3.3839 | 6.619 | 2.8847 | 15.0032 | 17.499 | 24.118 | 27.0027 | 0.01
5.9598 | 8.5413 | 2.1014 | 2.1831 | 3.5567 | 2.4429 | 11.2161 | 4.9438 | 14.5011 | 16.6842 | 27.9003 | 32.8441 | 5.9598 | 8.5413 | 2.1014 | 2.1831 | 3.5567 | 2.4429 | 11.2261 | 4.9438 | 14.5011 | 16.6842 | 27.9103 | 32.8541 | 0.01
6.2316 | 7.1293 | 1.7072 | 1.783 | 4.855 | 3.728 | 6.0425 | 5.1318 | 13.3609 | 15.1439 | 23.7269 | 28.8586 | 6.2316 | 7.1293 | 1.7072 | 1.783 | 4.855 | 3.728 | 6.0525 | 5.1318 | 13.3609 | 15.1439 | 23.7269 | 28.8586 | 0.01
5.9426 | 6.8771 | 2.0517 | 2.2839 | 2.6857 | 3.1455 | 6.165 | 6.2842 | 12.8196 | 15.1035 | 21.2686 | 27.5527 | 5.9426 | 6.8771 | 2.0517 | 2.2839 | 2.6857 | 3.1455 | 6.175 | 6.2842 | 12.8196 | 15.1035 | 21.2786 | 27.5627 | 0.01
6.5222 | 7.6918 | 1.8419 | 1.8611 | 3.1741 | 3.3269 | 5.7531 | 6.5673 | 14.214 | 16.0751 | 22.5761 | 29.1434 | 6.5222 | 7.6918 | 1.8419 | 1.8611 | 3.1741 | 3.3269 | 5.7631 | 6.5673 | 14.214 | 16.0751 | 22.5761 | 29.1434 | 0.01
6.0037 | 8.3929 | 2.0938 | 2.1675 | 2.6641 | 3.7259 | 7.4178 | 6.1173 | 14.3966 | 16.5641 | 23.9819 | 30.0992 | 6.0037 | 8.3929 | 2.0938 | 2.1675 | 2.6641 | 3.7259 | 7.4278 | 6.1173 | 14.3966 | 16.5641 | 23.9919 | 30.1092 | 0.01
5.9902 | 5.4997 | 1.7705 | 1.889 | 2.8715 | 3.2159 | 4.2618 | 4.4101 | 11.4899 | 13.3789 | 19.4662 | 23.8763 | 5.9902 | 5.4997 | 1.7705 | 1.889 | 2.8715 | 3.2159 | 4.2718 | 4.4101 | 11.4899 | 13.3789 | 19.4662 | 23.8763 | 0.01
7.2063 | 7.5976 | 2.0012 | 1.7471 | 2.863 | 3.0003 | 4.581 | 4.4795 | 14.8039 | 16.551 | 22.4143 | 26.8938 | 7.2063 | 7.5976 | 2.0012 | 1.7471 | 2.863 | 3.0003 | 4.591 | 4.4795 | 14.8039 | 16.551 | 22.4143 | 26.8938 | 0.01
6.1665 | 10.1615 | 1.5723 | 1.7317 | 2.235 | 2.0696 | 9.3333 | 5.4585 | 16.3279 | 18.0596 | 27.393 | 32.8514 | 6.1665 | 10.1615 | 1.5723 | 1.7317 | 2.235 | 2.0696 | 9.3433 | 5.4585 | 16.3279 | 18.0596 | 27.403 | 32.8614 | 0.01
6.1398 | 9.0042 | 2.1046 | 2.1063 | 3.3925 | 4.0295 | 6.9239 | 5.2423 | 15.1441 | 17.2504 | 24.6724 | 29.9147 | 6.1398 | 9.0042 | 2.1046 | 2.1063 | 3.3925 | 4.0295 | 6.9339 | 5.2423 | 15.1441 | 17.2504 | 24.6724 | 29.9147 | 0.01
5.2965 | 9.4215 | 1.4188 | 2.1189 | 2.7459 | 2.0075 | 7.6098 | 5.2809 | 14.718 | 16.8369 | 24.4467 | 29.7277 | 5.2965 | 9.4215 | 1.4188 | 2.1189 | 2.7459 | 2.0075 | 7.6198 | 5.2809 | 14.718 | 16.8369 | 24.4567 | 29.7377 | 0.01
5.6461 | 8.9788 | 1.9789 | 1.706 | 3.2105 | 2.831 | 4.4445 | 4.3363 | 14.6249 | 16.3309 | 22.3724 | 26.7087 | 5.6461 | 8.9788 | 1.9789 | 1.706 | 3.2105 | 2.831 | 4.4545 | 4.3363 | 14.6249 | 16.3309 | 22.3724 | 26.7087 | 0.01
6.09 | 7.9096 | 1.86 | 1.946 | 3.3487 | 2.3465 | 7.7323 | 2.7473 | 13.9995 | 15.9455 | 23.6779 | 26.4252 | 6.09 | 7.9096 | 1.86 | 1.946 | 3.3487 | 2.3465 | 7.7423 | 2.7473 | 13.9995 | 15.9455 | 23.6879 | 26.4352 | 0.01
4.6766 | 9.3308 | 1.8373 | 1.8972 | 3.0765 | 2.5526 | 5.5033 | 5.6142 | 14.0074 | 15.9046 | 21.5337 | 27.1478 | 4.6766 | 9.3308 | 1.8373 | 1.8972 | 3.0765 | 2.5526 | 5.5133 | 5.6142 | 14.0074 | 15.9046 | 21.5337 | 27.1478 | 0.01
6.1078 | 8.0687 | 2.0157 | 2.0139 | 3.2391 | 3.0238 | 7.4422 | 4.6632 | 14.1765 | 16.1904 | 23.6326 | 28.2958 | 6.1078 | 8.0687 | 2.0157 | 2.0139 | 3.2391 | 3.0238 | 7.4522 | 4.6632 | 14.1765 | 16.1904 | 23.6426 | 28.3058 | 0.01
5.4494 | 11.0373 | 2.2263 | 1.7278 | 4.6054 | 3.4546 | 8.9348 | 5.6177 | 16.4867 | 18.2145 | 27.1493 | 32.767 | 5.4494 | 11.0373 | 2.2263 | 1.7278 | 4.6054 | 3.4546 | 8.9448 | 5.6177 | 16.4867 | 18.2145 | 27.1593 | 32.777 | 0.01
6.7393 | 10.135 | 1.9999 | 1.8267 | 2.7818 | 3.3797 | 8.0549 | 5.7476 | 16.8743 | 18.701 | 26.7559 | 32.5035 | 6.7393 | 10.135 | 1.9999 | 1.8267 | 2.7818 | 3.3797 | 8.0649 | 5.7476 | 16.8743 | 18.701 | 26.7659 | 32.5135 | 0.01
6.0193 | 10.0936 | 1.9681 | 2.3078 | 2.9739 | 3.505 | 7.0005 | 6.3808 | 16.1128 | 18.4206 | 25.4211 | 31.8019 | 6.0193 | 10.0936 | 1.9681 | 2.3078 | 2.9739 | 3.505 | 7.0105 | 6.3808 | 16.1128 | 18.4206 | 25.4311 | 31.8119 | 0.01
6.4698 | 9.6907 | 1.9261 | 2.1135 | 2.1217 | 3.441 | 6.8707 | 6.0758 | 16.1604 | 18.274 | 25.1446 | 31.2204 | 6.4698 | 9.6907 | 1.9261 | 2.1135 | 2.1217 | 3.441 | 6.8807 | 6.0758 | 16.1604 | 18.274 | 25.1546 | 31.2304 | 0.01
6.6166 | 10.5923 | 1.9023 | 2.6313 | 3.5359 | 3.7444 | 5.1725 | 2.876 | 17.2089 | 19.8402 | 27.1206 | 29.9966 | 6.6166 | 10.5923 | 1.9023 | 2.6313 | 3.5359 | 3.7444 | 5.1825 | 2.876 | 17.2089 | 19.8402 | 27.1206 | 29.9966 | 0.01
6.2768 | 6.067 | 1.729 | 2.0726 | 3.2981 | 2.8613 | 7.8731 | 4.4528 | 12.3438 | 14.4164 | 22.2895 | 26.7423 | 6.2768 | 6.067 | 1.729 | 2.0726 | 3.2981 | 2.8613 | 7.8831 | 4.4528 | 12.3438 | 14.4164 | 22.2995 | 26.7523 | 0.01
6.2484 | 9.8103 | 2.3531 | 2.4585 | 1.7758 | 3.4322 | 5.9283 | 6.2053 | 16.0587 | 18.5172 | 24.4455 | 30.6507 | 6.2484 | 9.8103 | 2.3531 | 2.4585 | 1.7758 | 3.4322 | 5.9383 | 6.2053 | 16.0587 | 18.5172 | 24.4555 | 30.6607 | 0.01
5.4091 | 7.3558 | 2.1996 | 2.2177 | 3.3444 | 3.4808 | 5.8297 | 6.7698 | 12.7649 | 14.9826 | 21.8078 | 28.5776 | 5.4091 | 7.3558 | 2.1996 | 2.2177 | 3.3444 | 3.4808 | 5.8397 | 6.7698 | 12.7649 | 14.9826 | 21.8078 | 28.5776 | 0.01
5.5076 | 9.4641 | 2.2682 | 1.4438 | 2.8533 | 3.0528 | 6.988 | 6.8091 | 14.9716 | 16.4154 | 23.4034 | 30.2125 | 5.5076 | 9.4641 | 2.2682 | 1.4438 | 2.8533 | 3.0528 | 6.998 | 6.8091 | 14.9716 | 16.4154 | 23.4134 | 30.2225 | 0.01
5.5535 | 9.1351 | 1.9765 | 2.0283 | 2.1769 | 2.0583 | 4.3857 | 2.9313 | 14.6886 | 16.7169 | 21.1027 | 24.0339 | 5.5535 | 9.1351 | 1.9765 | 2.0283 | 2.1769 | 2.0583 | 4.3957 | 2.9313 | 14.6886 | 16.7169 | 21.1127 | 24.0439 | 0.01
6.5061 | 6.7102 | 1.9734 | 2.4188 | 4.2263 | 1.9462 | 7.5511 | 3.3922 | 13.2163 | 15.6351 | 23.1861 | 26.5784 | 6.5061 | 6.7102 | 1.9734 | 2.4188 | 4.2263 | 1.9462 | 7.5611 | 3.3922 | 13.2163 | 15.6351 | 23.1961 | 26.5884 | 0.01
5.7979 | 5.5885 | 1.9825 | 1.6977 | 3.9282 | 2.8865 | 6.9903 | 3.6022 | 11.3864 | 13.0841 | 20.0744 | 23.6766 | 5.7979 | 5.5885 | 1.9825 | 1.6977 | 3.9282 | 2.8865 | 7.0003 | 3.6022 | 11.3864 | 13.0841 | 20.0844 | 23.6866 | 0.01
6.3246 | 9.3143 | 1.8955 | 2.0541 | 3.9151 | 3.5845 | 6.4419 | 3.6083 | 15.6389 | 17.693 | 25.1926 | 28.801 | 6.3246 | 9.3143 | 1.8955 | 2.0541 | 3.9151 | 3.5845 | 6.4519 | 3.6083 | 15.6389 | 17.693 | 25.1926 | 28.801 | 0.01
5.8408 | 4.9807 | 2.3521 | 2.092 | 3.4179 | 3.3917 | 8.2937 | 4.8863 | 10.8215 | 12.9135 | 21.2072 | 26.0935 | 5.8408 | 4.9807 | 2.3521 | 2.092 | 3.4179 | 3.3917 | 8.3037 | 4.8863 | 10.8215 | 12.9135 | 21.2172 | 26.1035 | 0.01
5.5907 | 8.2054 | 1.987 | 1.5077 | 2.934 | 3.1403 | 4.2816 | 2.5561 | 13.7961 | 15.3037 | 21.378 | 23.9341 | 5.5907 | 8.2054 | 1.987 | 1.5077 | 2.934 | 3.1403 | 4.2916 | 2.5561 | 13.7961 | 15.3037 | 21.378 | 23.9341 | 0.01
5.7545 | 8.5903 | 2.3844 | 1.7032 | 1.0331 | 3.6489 | 5.4234 | 4.3978 | 14.3447 | 16.0479 | 21.4713 | 25.8692 | 5.7545 | 8.5903 | 2.3844 | 1.7032 | 1.0331 | 3.6489 | 5.4334 | 4.3978 | 14.3447 | 16.0479 | 21.4813 | 25.8792 | 0.01
5.7997 | 8.9066 | 1.8979 | 2.1887 | 4.3758 | 2.9984 | 6.1281 | 7.6213 | 14.7063 | 16.8951 | 24.2693 | 31.8906 | 5.7997 | 8.9066 | 1.8979 | 2.1887 | 4.3758 | 2.9984 | 6.1381 | 7.6213 | 14.7063 | 16.8951 | 24.2693 | 31.8906 | 0.01
5.1583 | 8.2078 | 1.9978 | 1.9746 | 3.2719 | 2.1817 | 6.5107 | 5.1648 | 13.366 | 15.3406 | 21.8513 | 27.0161 | 5.1583 | 8.2078 | 1.9978 | 1.9746 | 3.2719 | 2.1817 | 6.5207 | 5.1648 | 13.366 | 15.3406 | 21.8613 | 27.0261 | 0.01
6.7515 | 8.1848 | 2.205 | 2.3748 | 4.6679 | 3.5608 | 6.6877 | 6.4507 | 14.9363 | 17.3111 | 25.5398 | 31.9906 | 6.7515 | 8.1848 | 2.205 | 2.3748 | 4.6679 | 3.5608 | 6.6977 | 6.4507 | 14.9363 | 17.3111 | 25.5398 | 31.9906 | 0.01
5.2569 | 6.5501 | 1.6939 | 1.8501 | 3.2982 | 3.11 | 6.6969 | 5.7609 | 11.807 | 13.6571 | 20.354 | 26.1149 | 5.2569 | 6.5501 | 1.6939 | 1.8501 | 3.2982 | 3.11 | 6.7069 | 5.7609 | 11.807 | 13.6571 | 20.364 | 26.1249 | 0.01
6.002 | 9.4544 | 2.3963 | 2.2417 | 1.9181 | 3.0591 | 5.7349 | 4.2042 | 15.4563 | 17.698 | 23.4329 | 27.6371 | 6.002 | 9.4544 | 2.3963 | 2.2417 | 1.9181 | 3.0591 | 5.7449 | 4.2042 | 15.4563 | 17.698 | 23.4429 | 27.6471 | 0.01
6.3476 | 7.6187 | 2.3075 | 1.7614 | 3.4262 | 2.5112 | 6.5904 | 3.901 | 13.9664 | 15.7278 | 22.3182 | 26.2192 | 6.3476 | 7.6187 | 2.3075 | 1.7614 | 3.4262 | 2.5112 | 6.6004 | 3.901 | 13.9664 | 15.7278 | 22.3282 | 26.2292 | 0.01
6.7208 | 9.1839 | 1.896 | 2.1759 | 2.6918 | 2.8607 | 4.4186 | 4.8031 | 15.9047 | 18.0807 | 23.6332 | 28.4363 | 6.7208 | 9.1839 | 1.896 | 2.1759 | 2.6918 | 2.8607 | 4.4286 | 4.8031 | 15.9047 | 18.0807 | 23.6332 | 28.4363 | 0.01
5.8322 | 8.3296 | 2.2628 | 1.7759 | 2.0188 | 4.0508 | 6.7507 | 5.5669 | 14.1618 | 15.9377 | 22.6884 | 28.2553 | 5.8322 | 8.3296 | 2.2628 | 1.7759 | 2.0188 | 4.0508 | 6.7607 | 5.5669 | 14.1618 | 15.9377 | 22.6984 | 28.2653 | 0.01
7.2764 | 7.6941 | 1.8212 | 1.4059 | 1.9318 | 1.8816 | 7.5674 | 3.2093 | 14.9706 | 16.3765 | 23.9439 | 27.1532 | 7.2764 | 7.6941 | 1.8212 | 1.4059 | 1.9318 | 1.8816 | 7.5774 | 3.2093 | 14.9706 | 16.3765 | 23.9539 | 27.1632 | 0.01
4.8199 | 9.2313 | 1.6427 | 2.5718 | 2.6816 | 3.1166 | 5.1137 | 5.1339 | 14.0511 | 16.6229 | 22.421 | 27.5549 | 4.8199 | 9.2313 | 1.6427 | 2.5718 | 2.6816 | 3.1166 | 5.1237 | 5.1339 | 14.0511 | 16.6229 | 22.421 | 27.5549 | 0.01
6.0056 | 8.5197 | 1.4579 | 2.2212 | 2.0188 | 2.7604 | 5.5361 | 5.5085 | 14.5252 | 16.7464 | 22.2825 | 27.791 | 6.0056 | 8.5197 | 1.4579 | 2.2212 | 2.0188 | 2.7604 | 5.5461 | 5.5085 | 14.5252 | 16.7464 | 22.2925 | 27.801 | 0.01
6.0809 | 8.1694 | 1.8696 | 2.8123 | 4.0381 | 2.6432 | 4.0409 | 5.9793 | 14.2503 | 17.0626 | 23.7439 | 29.7232 | 6.0809 | 8.1694 | 1.8696 | 2.8123 | 4.0381 | 2.6432 | 4.0509 | 5.9793 | 14.2503 | 17.0626 | 23.7439 | 29.7232 | 0.01
6.08 | 7.2381 | 1.9463 | 1.8598 | 3.2844 | 3.8703 | 8.391 | 2.8229 | 13.3181 | 15.1779 | 23.5689 | 26.3918 | 6.08 | 7.2381 | 1.9463 | 1.8598 | 3.2844 | 3.8703 | 8.401 | 2.8229 | 13.3181 | 15.1779 | 23.5789 | 26.4018 | 0.01
6.453 | 8.6702 | 2.1149 | 1.7827 | 2.809 | 3.3127 | 6.1876 | 5.4646 | 15.1233 | 16.906 | 23.0936 | 28.5582 | 6.453 | 8.6702 | 2.1149 | 1.7827 | 2.809 | 3.3127 | 6.1976 | 5.4646 | 15.1233 | 16.906 | 23.1036 | 28.5682 | 0.01
6.9678 | 8.3217 | 2.1405 | 2.1051 | 2.9964 | 3.0629 | 8.1305 | 5.3003 | 15.2895 | 17.3946 | 25.5251 | 30.8254 | 6.9678 | 8.3217 | 2.1405 | 2.1051 | 2.9964 | 3.0629 | 8.1405 | 5.3003 | 15.2895 | 17.3946 | 25.5351 | 30.8354 | 0.01
6.8722 | 6.1109 | 1.9818 | 1.6022 | 3.9747 | 1.94 | 7.6464 | 4.703 | 12.9831 | 14.5852 | 22.2316 | 26.9346 | 6.8722 | 6.1109 | 1.9818 | 1.6022 | 3.9747 | 1.94 | 7.6564 | 4.703 | 12.9831 | 14.5852 | 22.2416 | 26.9446 | 0.01
7.2008 | 8.6343 | 2.1488 | 2.4656 | 2.6616 | 2.9323 | 6.8103 | 4.8318 | 15.8351 | 18.3007 | 25.111 | 29.9428 | 7.2008 | 8.6343 | 2.1488 | 2.4656 | 2.6616 | 2.9323 | 6.8203 | 4.8318 | 15.8351 | 18.3007 | 25.121 | 29.9528 | 0.01
6.8346 | 8.0102 | 1.9209 | 2.1151 | 5.1267 | 1.8951 | 8.4926 | 4.2757 | 14.8447 | 16.9598 | 25.4524 | 29.728 | 6.8346 | 8.0102 | 1.9209 | 2.1151 | 5.1267 | 1.8951 | 8.5026 | 4.2757 | 14.8447 | 16.9598 | 25.4624 | 29.738 | 0.01
5.3057 | 7.0996 | 1.9135 | 2.0683 | 2.9475 | 3.2699 | 7.3605 | 4.9594 | 12.4053 | 14.4735 | 21.834 | 26.7934 | 5.3057 | 7.0996 | 1.9135 | 2.0683 | 2.9475 | 3.2699 | 7.3705 | 4.9594 | 12.4053 | 14.4735 | 21.844 | 26.8034 | 0.01
4.7335 | 7.8804 | 1.773 | 2.0664 | 3.0427 | 3.0979 | 7.4584 | 5.1655 | 12.614 | 14.6804 | 22.1388 | 27.3043 | 4.7335 | 7.8804 | 1.773 | 2.0664 | 3.0427 | 3.0979 | 7.4684 | 5.1655 | 12.614 | 14.6804 | 22.1488 | 27.3143 | 0.01
6.0349 | 10.1473 | 1.9051 | 2.0374 | 3.4241 | 2.3659 | 9.8777 | 4.3683 | 16.1822 | 18.2196 | 28.0973 | 32.4656 | 6.0349 | 10.1473 | 1.9051 | 2.0374 | 3.4241 | 2.3659 | 9.8877 | 4.3683 | 16.1822 | 18.2196 | 28.1073 | 32.4756 | 0.01
6.4712 | 6.5853 | 2.5715 | 1.5297 | 2.816 | 2.0495 | 5.9554 | 4.9704 | 13.0565 | 14.5862 | 20.5415 | 25.5119 | 6.4712 | 6.5853 | 2.5715 | 1.5297 | 2.816 | 2.0495 | 5.9654 | 4.9704 | 13.0565 | 14.5862 | 20.5515 | 25.5219 | 0.01
5.3779 | 9.5032 | 2.1574 | 1.5556 | 1.4632 | 3.1799 | 5.2004 | 4.4594 | 14.8811 | 16.4367 | 21.6371 | 26.0965 | 5.3779 | 9.5032 | 2.1574 | 1.5556 | 1.4632 | 3.1799 | 5.2104 | 4.4594 | 14.8811 | 16.4367 | 21.6471 | 26.1065 | 0.01
6.2501 | 8.0392 | 2.1205 | 2.21 | 2.4065 | 3.4802 | 9.3924 | 3.0135 | 14.2894 | 16.4994 | 25.8918 | 28.9053 | 6.2501 | 8.0392 | 2.1205 | 2.21 | 2.4065 | 3.4802 | 9.4024 | 3.0135 | 14.2894 | 16.4994 | 25.9018 | 28.9153 | 0.01
6.2059 | 7.3227 | 1.7841 | 1.4255 | 1.7404 | 4.553 | 5.2851 | 4.4339 | 13.5286 | 14.9541 | 21.2476 | 25.6815 | 6.2059 | 7.3227 | 1.7841 | 1.4255 | 1.7404 | 4.553 | 5.2951 | 4.4339 | 13.5286 | 14.9541 | 21.2476 | 25.6815 | 0.01
6.2822 | 8.3526 | 1.8593 | 1.7602 | 2.2342 | 3.6994 | 4.5028 | 4.3882 | 14.6348 | 16.395 | 22.3287 | 26.7169 | 6.2822 | 8.3526 | 1.8593 | 1.7602 | 2.2342 | 3.6994 | 4.5128 | 4.3882 | 14.6348 | 16.395 | 22.3287 | 26.7169 | 0.01
6.2866 | 9.5329 | 1.8517 | 1.719 | 3.0828 | 2.5856 | 9.4425 | 3.6627 | 15.8195 | 17.5385 | 26.981 | 30.6436 | 6.2866 | 9.5329 | 1.8517 | 1.719 | 3.0828 | 2.5856 | 9.4525 | 3.6627 | 15.8195 | 17.5385 | 26.991 | 30.6536 | 0.01
6.2115 | 7.5155 | 2.3314 | 2.2067 | 3.5411 | 1.7284 | 7.2081 | 4.2603 | 13.727 | 15.9336 | 23.1417 | 27.402 | 6.2115 | 7.5155 | 2.3314 | 2.2067 | 3.5411 | 1.7284 | 7.2181 | 4.2603 | 13.727 | 15.9336 | 23.1517 | 27.412 | 0.01
5.5339 | 10.0209 | 2.0249 | 1.5631 | 1.4934 | 3.5609 | 6.6379 | 5.1942 | 15.5547 | 17.1179 | 23.7557 | 28.9499 | 5.5339 | 10.0209 | 2.0249 | 1.5631 | 1.4934 | 3.5609 | 6.6479 | 5.1942 | 15.5547 | 17.1179 | 23.7657 | 28.9599 | 0.01
6.2426 | 10.7064 | 1.9915 | 1.5379 | 2.3555 | 2.6897 | 7.2487 | 4.6486 | 16.9491 | 18.487 | 25.7357 | 30.3843 | 6.2426 | 10.7064 | 1.9915 | 1.5379 | 2.3555 | 2.6897 | 7.2587 | 4.6486 | 16.9491 | 18.487 | 25.7457 | 30.3943 | 0.01
6.4336 | 8.0399 | 2.292 | 1.9305 | 3.3239 | 3.5993 | 6.1819 | 6.2068 | 14.4736 | 16.404 | 23.3273 | 29.534 | 6.4336 | 8.0399 | 2.292 | 1.9305 | 3.3239 | 3.5993 | 6.1919 | 6.2068 | 14.4736 | 16.404 | 23.3273 | 29.534 | 0.01
6.4477 | 7.375 | 1.6966 | 1.9962 | 4.1108 | 3.4772 | 9.6678 | 3.3847 | 13.8227 | 15.8189 | 25.4867 | 28.8715 | 6.4477 | 7.375 | 1.6966 | 1.9962 | 4.1108 | 3.4772 | 9.6778 | 3.3847 | 13.8227 | 15.8189 | 25.4967 | 28.8815 | 0.01
5.9306 | 6.5701 | 1.7671 | 1.6918 | 1.4556 | 2.7577 | 6.8382 | 6.2672 | 12.5007 | 14.1925 | 21.0307 | 27.2979 | 5.9306 | 6.5701 | 1.7671 | 1.6918 | 1.4556 | 2.7577 | 6.8482 | 6.2672 | 12.5007 | 14.1925 | 21.0407 | 27.3079 | 0.01
6.33 | 7.0539 | 1.9518 | 1.4771 | 2.7979 | 3.4243 | 8.2618 | 4.8491 | 13.3839 | 14.8611 | 23.1229 | 27.972 | 6.33 | 7.0539 | 1.9518 | 1.4771 | 2.7979 | 3.4243 | 8.2718 | 4.8491 | 13.3839 | 14.8611 | 23.1329 | 27.982 | 0.01
5.7108 | 5.3696 | 1.759 | 1.9716 | 4.8415 | 3.982 | 8.1484 | 4.2715 | 11.0803 | 13.0519 | 21.8754 | 26.1469 | 5.7108 | 5.3696 | 1.759 | 1.9716 | 4.8415 | 3.982 | 8.1584 | 4.2715 | 11.0803 | 13.0519 | 21.8754 | 26.1469 | 0.01
5.1207 | 8.4712 | 1.6589 | 1.9496 | 3.2623 | 2.9483 | 8.6224 | 5.4075 | 13.5919 | 15.5414 | 24.1638 | 29.5714 | 5.1207 | 8.4712 | 1.6589 | 1.9496 | 3.2623 | 2.9483 | 8.6324 | 5.4075 | 13.5919 | 15.5414 | 24.1738 | 29.5814 | 0.01
6.0251 | 8.4814 | 1.9447 | 2.2752 | 4.3827 | 4.0189 | 9.5209 | 5.347 | 14.5066 | 16.7818 | 26.3027 | 31.6498 | 6.0251 | 8.4814 | 1.9447 | 2.2752 | 4.3827 | 4.0189 | 9.5309 | 5.347 | 14.5066 | 16.7818 | 26.3127 | 31.6598 | 0.01
5.5356 | 6.3288 | 2.005 | 1.7842 | 3.3664 | 1.3736 | 10.1922 | 4.5248 | 11.8644 | 13.6487 | 23.8408 | 28.3656 | 5.5356 | 6.3288 | 2.005 | 1.7842 | 3.3664 | 1.3736 | 10.2022 | 4.5248 | 11.8644 | 13.6487 | 23.8508 | 28.3756 | 0.01
6.9637 | 8.633 | 1.9818 | 1.8626 | 4.9103 | 3.7884 | 6.9113 | 2.6365 | 15.5968 | 17.4593 | 26.158 | 28.7946 | 6.9637 | 8.633 | 1.9818 | 1.8626 | 4.9103 | 3.7884 | 6.9213 | 2.6365 | 15.5968 | 17.4593 | 26.158 | 28.7946 | 0.01
6.8063 | 8.1236 | 2.1674 | 1.8941 | 2.8611 | 3.4388 | 5.8228 | 3.8261 | 14.9298 | 16.8239 | 23.1238 | 26.9499 | 6.8063 | 8.1236 | 2.1674 | 1.8941 | 2.8611 | 3.4388 | 5.8328 | 3.8261 | 14.9298 | 16.8239 | 23.1238 | 26.9499 | 0.01
5.3555 | 7.0531 | 1.9069 | 2.4591 | 2.1407 | 3.6211 | 9.3352 | 4.4405 | 12.4087 | 14.8678 | 24.203 | 28.6435 | 5.3555 | 7.0531 | 1.9069 | 2.4591 | 2.1407 | 3.6211 | 9.3452 | 4.4405 | 12.4087 | 14.8678 | 24.213 | 28.6535 | 0.01
6.7898 | 8.445 | 1.9115 | 2.3241 | 2.4542 | 4.176 | 7.5165 | 4.4659 | 15.2348 | 17.5589 | 25.0754 | 29.5413 | 6.7898 | 8.445 | 1.9115 | 2.3241 | 2.4542 | 4.176 | 7.5265 | 4.4659 | 15.2348 | 17.5589 | 25.0854 | 29.5513 | 0.01
5.5872 | 8.9856 | 2.0571 | 1.9896 | 4.2253 | 3.6375 | 6.471 | 5.8695 | 14.5728 | 16.5624 | 24.4251 | 30.2947 | 5.5872 | 8.9856 | 2.0571 | 1.9896 | 4.2253 | 3.6375 | 6.481 | 5.8695 | 14.5728 | 16.5624 | 24.4251 | 30.2947 | 0.01
6.5262 | 7.6889 | 1.8585 | 2.3918 | 1.8454 | 3.574 | 3.863 | 6.5105 | 14.2151 | 16.6069 | 22.0262 | 28.5366 | 6.5262 | 7.6889 | 1.8585 | 2.3918 | 1.8454 | 3.574 | 3.873 | 6.5105 | 14.2151 | 16.6069 | 22.0262 | 28.5366 | 0.01
5.8727 | 8.2903 | 1.8464 | 2.2687 | 3.704 | 2.8312 | 5.8484 | 4.0135 | 14.1631 | 16.4318 | 22.9669 | 26.9804 | 5.8727 | 8.2903 | 1.8464 | 2.2687 | 3.704 | 2.8312 | 5.8584 | 4.0135 | 14.1631 | 16.4318 | 22.9669 | 26.9804 | 0.01
5.0545 | 8.3658 | 1.8967 | 2.4355 | 1.6736 | 3.4223 | 7.1389 | 5.2696 | 13.4203 | 15.8558 | 22.9947 | 28.2643 | 5.0545 | 8.3658 | 1.8967 | 2.4355 | 1.6736 | 3.4223 | 7.1489 | 5.2696 | 13.4203 | 15.8558 | 23.0047 | 28.2743 | 0.01
5.467 | 10.4491 | 2.0661 | 2.036 | 1.811 | 3.0464 | 11.66 | 5.8532 | 15.9161 | 17.9521 | 29.6121 | 35.4654 | 5.467 | 10.4491 | 2.0661 | 2.036 | 1.811 | 3.0464 | 11.67 | 5.8532 | 15.9161 | 17.9521 | 29.6221 | 35.4754 | 0.01
6.5733 | 8.6504 | 1.9929 | 2.3119 | 2.3281 | 1.6858 | 6.3688 | 8.4511 | 15.2237 | 17.5356 | 23.9044 | 32.3555 | 6.5733 | 8.6504 | 1.9929 | 2.3119 | 2.3281 | 1.6858 | 6.3788 | 8.4511 | 15.2237 | 17.5356 | 23.9144 | 32.3655 | 0.01
6.35 | 7.6364 | 1.8692 | 2.2905 | 4.1904 | 2.7535 | 8.2517 | 4.5673 | 13.9863 | 16.2768 | 24.5285 | 29.0958 | 6.35 | 7.6364 | 1.8692 | 2.2905 | 4.1904 | 2.7535 | 8.2617 | 4.5673 | 13.9863 | 16.2768 | 24.5385 | 29.1058 | 0.01
5.7628 | 7.7512 | 2.2335 | 2.0297 | 2.7834 | 1.7335 | 7.1752 | 5.1894 | 13.5141 | 15.5437 | 22.719 | 27.9083 | 5.7628 | 7.7512 | 2.2335 | 2.0297 | 2.7834 | 1.7335 | 7.1852 | 5.1894 | 13.5141 | 15.5437 | 22.729 | 27.9183 | 0.01
6.5506 | 7.2617 | 2.2095 | 2.5645 | 2.8912 | 3.0936 | 7.9551 | 3.4067 | 13.8123 | 16.3768 | 24.3319 | 27.7386 | 6.5506 | 7.2617 | 2.2095 | 2.5645 | 2.8912 | 3.0936 | 7.9651 | 3.4067 | 13.8123 | 16.3768 | 24.3419 | 27.7486 | 0.01
5.2955 | 7.1547 | 2.4298 | 3.1005 | 2.0173 | 2.1403 | 8.6126 | 5.241 | 12.4501 | 15.5506 | 24.1631 | 29.4041 | 5.2955 | 7.1547 | 2.4298 | 3.1005 | 2.0173 | 2.1403 | 8.6226 | 5.241 | 12.4501 | 15.5506 | 24.1731 | 29.4141 | 0.01
5.5204 | 9.2551 | 1.8362 | 2.0349 | 3.9106 | 4.1584 | 8.8775 | 6.5589 | 14.7755 | 16.8104 | 25.6879 | 32.2468 | 5.5204 | 9.2551 | 1.8362 | 2.0349 | 3.9106 | 4.1584 | 8.8875 | 6.5589 | 14.7755 | 16.8104 | 25.6979 | 32.2568 | 0.01
7.434 | 8.4975 | 2.2088 | 2.154 | 2.169 | 3.5418 | 7.5343 | 2.8408 | 15.9316 | 18.0856 | 25.6199 | 28.4606 | 7.434 | 8.4975 | 2.2088 | 2.154 | 2.169 | 3.5418 | 7.5443 | 2.8408 | 15.9316 | 18.0856 | 25.6299 | 28.4706 | 0.01
6.7927 | 5.113 | 2.4586 | 1.833 | 2.9222 | 3.1854 | 5.7625 | 4.8363 | 11.9057 | 13.7386 | 19.8463 | 24.6826 | 6.7927 | 5.113 | 2.4586 | 1.833 | 2.9222 | 3.1854 | 5.7725 | 4.8363 | 11.9057 | 13.7386 | 19.8463 | 24.6826 | 0.01
6.2178 | 8.5768 | 2.1902 | 2.1196 | 2.9807 | 3.7028 | 7.1723 | 6.8128 | 14.7946 | 16.9143 | 24.0866 | 30.8994 | 6.2178 | 8.5768 | 2.1902 | 2.1196 | 2.9807 | 3.7028 | 7.1823 | 6.8128 | 14.7946 | 16.9143 | 24.0966 | 30.9094 | 0.01
6.4443 | 7.5956 | 2.0697 | 2.2645 | 2.2461 | 3.0881 | 7.3978 | 4.639 | 14.0399 | 16.3044 | 23.7022 | 28.3413 | 6.4443 | 7.5956 | 2.0697 | 2.2645 | 2.2461 | 3.0881 | 7.4078 | 4.639 | 14.0399 | 16.3044 | 23.7122 | 28.3513 | 0.01
6.0884 | 9.7929 | 1.9912 | 1.3756 | 2.5205 | 2.61 | 5.0591 | 5.2907 | 15.8813 | 17.2569 | 22.3874 | 27.6781 | 6.0884 | 9.7929 | 1.9912 | 1.3756 | 2.5205 | 2.61 | 5.0691 | 5.2907 | 15.8813 | 17.2569 | 22.3874 | 27.6781 | 0.01
6.2227 | 8.7822 | 2.2486 | 2.0387 | 3.1996 | 2.4117 | 6.4696 | 6.5243 | 15.0049 | 17.0437 | 23.5133 | 30.0376 | 6.2227 | 8.7822 | 2.2486 | 2.0387 | 3.1996 | 2.4117 | 6.4796 | 6.5243 | 15.0049 | 17.0437 | 23.5233 | 30.0476 | 0.01
6.1713 | 7.4182 | 1.6874 | 1.9521 | 2.937 | 2.6712 | 7.2951 | 6.1282 | 13.5895 | 15.5417 | 22.8368 | 28.965 | 6.1713 | 7.4182 | 1.6874 | 1.9521 | 2.937 | 2.6712 | 7.3051 | 6.1282 | 13.5895 | 15.5417 | 22.8468 | 28.975 | 0.01
6.5011 | 5.0108 | 1.7753 | 2.6119 | 2.6546 | 2.6855 | 7.7273 | 2.7882 | 11.5119 | 14.1238 | 21.8511 | 24.6394 | 6.5011 | 5.0108 | 1.7753 | 2.6119 | 2.6546 | 2.6855 | 7.7373 | 2.7882 | 11.5119 | 14.1238 | 21.8611 | 24.6494 | 0.01
5.4361 | 7.15 | 1.9584 | 1.8528 | 3.1504 | 3.5211 | 5.9871 | 4.839 | 12.5861 | 14.4389 | 21.1104 | 25.9494 | 5.4361 | 7.15 | 1.9584 | 1.8528 | 3.1504 | 3.5211 | 5.9971 | 4.839 | 12.5861 | 14.4389 | 21.1104 | 25.9494 | 0.01
5.3842 | 9.4273 | 2.282 | 1.8103 | 1.6517 | 2.0249 | 9.1245 | 5.2569 | 14.8115 | 16.6218 | 25.7463 | 31.0032 | 5.3842 | 9.4273 | 2.282 | 1.8103 | 1.6517 | 2.0249 | 9.1345 | 5.2569 | 14.8115 | 16.6218 | 25.7563 | 31.0132 | 0.01
6.2966 | 9.1218 | 1.8409 | 2.0494 | 3.0887 | 2.8933 | 5.9255 | 3.4345 | 15.4184 | 17.4678 | 23.4498 | 26.8842 | 6.2966 | 9.1218 | 1.8409 | 2.0494 | 3.0887 | 2.8933 | 5.9355 | 3.4345 | 15.4184 | 17.4678 | 23.4498 | 26.8842 | 0.01
6.4895 | 9.064 | 2.1338 | 2.1346 | 2.9278 | 2.5538 | 7.1513 | 3.3738 | 15.5535 | 17.6881 | 24.8395 | 28.2132 | 6.4895 | 9.064 | 2.1338 | 2.1346 | 2.9278 | 2.5538 | 7.1613 | 3.3738 | 15.5535 | 17.6881 | 24.8495 | 28.2232 | 0.01
5.9038 | 8.2467 | 2.3336 | 1.8917 | 2.1849 | 3.3904 | 7.6113 | 3.6458 | 14.1505 | 16.0421 | 23.6534 | 27.2992 | 5.9038 | 8.2467 | 2.3336 | 1.8917 | 2.1849 | 3.3904 | 7.6213 | 3.6458 | 14.1505 | 16.0421 | 23.6634 | 27.3092 | 0.01
6.6322 | 10.0367 | 1.8793 | 2.0987 | 3.6904 | 3.6319 | 6.6033 | 5.5396 | 16.6689 | 18.7676 | 26.09 | 31.6295 | 6.6322 | 10.0367 | 1.8793 | 2.0987 | 3.6904 | 3.6319 | 6.6133 | 5.5396 | 16.6689 | 18.7676 | 26.09 | 31.6295 | 0.01
5.8942 | 7.5817 | 2.294 | 1.8177 | 2.0809 | 3.7741 | 8.7828 | 4.6095 | 13.4759 | 15.2936 | 24.0764 | 28.6859 | 5.8942 | 7.5817 | 2.294 | 1.8177 | 2.0809 | 3.7741 | 8.7928 | 4.6095 | 13.4759 | 15.2936 | 24.0864 | 28.6959 | 0.01
5.2003 | 10.9012 | 1.9248 | 1.7256 | 2.1616 | 2.1888 | 8.9298 | 5.8693 | 16.1014 | 17.8271 | 26.7569 | 32.6262 | 5.2003 | 10.9012 | 1.9248 | 1.7256 | 2.1616 | 2.1888 | 8.9398 | 5.8693 | 16.1014 | 17.8271 | 26.7669 | 32.6362 | 0.01
6.5271 | 7.6874 | 2.0824 | 2.324 | 2.3953 | 3.1692 | 5.6043 | 3.8575 | 14.2144 | 16.5385 | 22.1427 | 26.0003 | 6.5271 | 7.6874 | 2.0824 | 2.324 | 2.3953 | 3.1692 | 5.6143 | 3.8575 | 14.2144 | 16.5385 | 22.1527 | 26.0103 | 0.01
5.9 | 9.7333 | 1.8527 | 1.8913 | 1.6467 | 2.1501 | 7.2255 | 5.119 | 15.6333 | 17.5246 | 24.75 | 29.8691 | 5.9 | 9.7333 | 1.8527 | 1.8913 | 1.6467 | 2.1501 | 7.2355 | 5.119 | 15.6333 | 17.5246 | 24.76 | 29.8791 | 0.01
5.0546 | 5.6147 | 2.2193 | 1.9917 | 3.5873 | 2.5267 | 7.7218 | 3.8493 | 10.6694 | 12.661 | 20.3828 | 24.2321 | 5.0546 | 5.6147 | 2.2193 | 1.9917 | 3.5873 | 2.5267 | 7.7318 | 3.8493 | 10.6694 | 12.661 | 20.3928 | 24.2421 | 0.01
6.3069 | 8.0951 | 2.4164 | 3.6093 | 3.173 | 3.4065 | 6.0813 | 3.5226 | 14.402 | 18.0114 | 24.5909 | 28.1135 | 6.3069 | 8.0951 | 2.4164 | 3.6093 | 3.173 | 3.4065 | 6.0913 | 3.5226 | 14.402 | 18.0114 | 24.5909 | 28.1135 | 0.01
6.4495 | 8.3382 | 2.2839 | 2.4181 | 2.5507 | 2.2917 | 8.0927 | 3.962 | 14.7877 | 17.2058 | 25.2985 | 29.2605 | 6.4495 | 8.3382 | 2.2839 | 2.4181 | 2.5507 | 2.2917 | 8.1027 | 3.962 | 14.7877 | 17.2058 | 25.3085 | 29.2705 | 0.01
6.0135 | 8.6468 | 2.098 | 2.2932 | 1.0679 | 2.3698 | 7.4417 | 5.162 | 14.6603 | 16.9535 | 24.3952 | 29.5572 | 6.0135 | 8.6468 | 2.098 | 2.2932 | 1.0679 | 2.3698 | 7.4517 | 5.162 | 14.6603 | 16.9535 | 24.4052 | 29.5672 | 0.01
5.1003 | 5.4857 | 2.1137 | 1.9891 | 4.2116 | 4.4873 | 6.0356 | 3.7272 | 10.586 | 12.575 | 21.2739 | 25.0011 | 5.1003 | 5.4857 | 2.1137 | 1.9891 | 4.2116 | 4.4873 | 6.0456 | 3.7272 | 10.586 | 12.575 | 21.2739 | 25.0011 | 0.01
6.1251 | 6.6199 | 2.2472 | 2.054 | 2.4068 | 2.4636 | 7.4892 | 4.4551 | 12.745 | 14.799 | 22.2882 | 26.7432 | 6.1251 | 6.6199 | 2.2472 | 2.054 | 2.4068 | 2.4636 | 7.4992 | 4.4551 | 12.745 | 14.799 | 22.2982 | 26.7532 | 0.01
6.0141 | 6.5894 | 1.9448 | 2.6369 | 1.9057 | 2.7587 | 6.9965 | 5.0806 | 12.6035 | 15.2404 | 22.2369 | 27.3175 | 6.0141 | 6.5894 | 1.9448 | 2.6369 | 1.9057 | 2.7587 | 7.0065 | 5.0806 | 12.6035 | 15.2404 | 22.2469 | 27.3275 | 0.01
6.2806 | 7.8012 | 2.2468 | 2.4115 | 1.9529 | 2.8027 | 8.4499 | 4.6584 | 14.0818 | 16.4933 | 24.9432 | 29.6016 | 6.2806 | 7.8012 | 2.2468 | 2.4115 | 1.9529 | 2.8027 | 8.4599 | 4.6584 | 14.0818 | 16.4933 | 24.9532 | 29.6116 | 0.01
6.3105 | 6.9147 | 2.0679 | 2.0709 | 3.8734 | 2.4145 | 8.7317 | 6.0692 | 13.2252 | 15.2961 | 24.0279 | 30.0971 | 6.3105 | 6.9147 | 2.0679 | 2.0709 | 3.8734 | 2.4145 | 8.7417 | 6.0692 | 13.2252 | 15.2961 | 24.0379 | 30.1071 | 0.01
5.8621 | 9.4761 | 1.9848 | 2.1693 | 3.9992 | 3.0247 | 6.8059 | 5.9291 | 15.3382 | 17.5075 | 24.5314 | 30.4605 | 5.8621 | 9.4761 | 1.9848 | 2.1693 | 3.9992 | 3.0247 | 6.8159 | 5.9291 | 15.3382 | 17.5075 | 24.5314 | 30.4605 | 0.01
5.883 | 8.4718 | 2.2748 | 2.1176 | 4.3409 | 3.2937 | 7.4642 | 6.1689 | 14.3549 | 16.4724 | 24.107 | 30.2759 | 5.883 | 8.4718 | 2.2748 | 2.1176 | 4.3409 | 3.2937 | 7.4742 | 6.1689 | 14.3549 | 16.4724 | 24.107 | 30.2759 | 0.01
5.2789 | 8.1038 | 2.1616 | 1.6709 | 1.4644 | 3.3556 | 9.4459 | 4.1681 | 13.3827 | 15.0536 | 24.4995 | 28.6676 | 5.2789 | 8.1038 | 2.1616 | 1.6709 | 1.4644 | 3.3556 | 9.4559 | 4.1681 | 13.3827 | 15.0536 | 24.5095 | 28.6776 | 0.01
6.5233 | 6.6362 | 2.1621 | 2.1472 | 2.894 | 3.4595 | 6.5128 | 4.9492 | 13.1595 | 15.3067 | 21.8195 | 26.7686 | 6.5233 | 6.6362 | 2.1621 | 2.1472 | 2.894 | 3.4595 | 6.5228 | 4.9492 | 13.1595 | 15.3067 | 21.8295 | 26.7786 | 0.01
4.6724 | 7.2862 | 2.0648 | 2.2639 | 2.8147 | 2.4926 | 7.2115 | 4.4305 | 11.9586 | 14.2225 | 21.434 | 25.8646 | 4.6724 | 7.2862 | 2.0648 | 2.2639 | 2.8147 | 2.4926 | 7.2215 | 4.4305 | 11.9586 | 14.2225 | 21.444 | 25.8746 | 0.01
5.6034 | 9.3261 | 2.3419 | 1.7921 | 2.7929 | 2.9571 | 5.2674 | 6.0432 | 14.9295 | 16.7216 | 22.4716 | 28.5148 | 5.6034 | 9.3261 | 2.3419 | 1.7921 | 2.7929 | 2.9571 | 5.2774 | 6.0432 | 14.9295 | 16.7216 | 22.4716 | 28.5148 | 0.01
5.7209 | 9.3092 | 2.2617 | 2.1065 | 2.0148 | 3.2762 | 5.1437 | 6.6334 | 15.0301 | 17.1366 | 22.4276 | 29.061 | 5.7209 | 9.3092 | 2.2617 | 2.1065 | 2.0148 | 3.2762 | 5.1537 | 6.6334 | 15.0301 | 17.1366 | 22.4276 | 29.061 | 0.01
5.4573 | 7.988 | 1.9547 | 2.0584 | 1.23 | 3.1579 | 6.87 | 5.6301 | 13.4453 | 15.5037 | 22.3737 | 28.0038 | 5.4573 | 7.988 | 1.9547 | 2.0584 | 1.23 | 3.1579 | 6.88 | 5.6301 | 13.4453 | 15.5037 | 22.3837 | 28.0138 | 0.01
6.189 | 7.0188 | 2.2182 | 1.8165 | 3.7992 | 3.6168 | 8.5379 | 2.7987 | 13.2079 | 15.0244 | 23.5622 | 26.3609 | 6.189 | 7.0188 | 2.2182 | 1.8165 | 3.7992 | 3.6168 | 8.5479 | 2.7987 | 13.2079 | 15.0244 | 23.5722 | 26.3709 | 0.01
5.1737 | 8.3648 | 1.6395 | 2.0307 | 3.813 | 3.1172 | 7.7502 | 4.8062 | 13.5385 | 15.5692 | 23.3195 | 28.1257 | 5.1737 | 8.3648 | 1.6395 | 2.0307 | 3.813 | 3.1172 | 7.7602 | 4.8062 | 13.5385 | 15.5692 | 23.3295 | 28.1357 | 0.01
5.624 | 7.4073 | 1.7608 | 2.0373 | 2.6505 | 3.7856 | 7.4995 | 3.2405 | 13.0313 | 15.0686 | 22.568 | 25.8085 | 5.624 | 7.4073 | 1.7608 | 2.0373 | 2.6505 | 3.7856 | 7.5095 | 3.2405 | 13.0313 | 15.0686 | 22.578 | 25.8185 | 0.01
6.5009 | 7.3844 | 1.5148 | 2.4998 | 2.6813 | 2.4287 | 7.2908 | 7.8151 | 13.8853 | 16.3851 | 23.6759 | 31.4909 | 6.5009 | 7.3844 | 1.5148 | 2.4998 | 2.6813 | 2.4287 | 7.3008 | 7.8151 | 13.8853 | 16.3851 | 23.6859 | 31.5009 | 0.01
5.4419 | 6.9111 | 2.0699 | 1.8371 | 2.273 | 3.3984 | 6.6833 | 3.9532 | 12.3529 | 14.1901 | 20.8734 | 24.8265 | 5.4419 | 6.9111 | 2.0699 | 1.8371 | 2.273 | 3.3984 | 6.6933 | 3.9532 | 12.3529 | 14.1901 | 20.8834 | 24.8365 | 0.01
3.8619 | 8.507 | 1.8555 | 2.0872 | 2.3624 | 2.0017 | 6.8355 | 6.5922 | 12.3689 | 14.4561 | 21.2916 | 27.8837 | 3.8619 | 8.507 | 1.8555 | 2.0872 | 2.3624 | 2.0017 | 6.8455 | 6.5922 | 12.3689 | 14.4561 | 21.3016 | 27.8937 | 0.01
5.992 | 7.7397 | 1.8892 | 1.6703 | 0.69632 | 2.247 | 6.5222 | 5.689 | 13.7316 | 15.4019 | 21.9241 | 27.6131 | 5.992 | 7.7397 | 1.8892 | 1.6703 | 0.69632 | 2.247 | 6.5322 | 5.689 | 13.7316 | 15.4019 | 21.9341 | 27.6231 | 0.01
5.1857 | 10.9245 | 1.7985 | 1.5414 | 3.9378 | 2.8491 | 8.622 | 3.8481 | 16.1102 | 17.6516 | 26.2736 | 30.1217 | 5.1857 | 10.9245 | 1.7985 | 1.5414 | 3.9378 | 2.8491 | 8.632 | 3.8481 | 16.1102 | 17.6516 | 26.2836 | 30.1317 | 0.01
6.2352 | 7.8605 | 1.8438 | 1.9823 | 0.67289 | 3.1019 | 5.1621 | 4.742 | 14.0956 | 16.0779 | 21.24 | 25.9819 | 6.2352 | 7.8605 | 1.8438 | 1.9823 | 0.67289 | 3.1019 | 5.1721 | 4.742 | 14.0956 | 16.0779 | 21.25 | 25.9919 | 0.01
6.3361 | 8.5312 | 1.8862 | 1.672 | 3.3222 | 1.9861 | 6.8346 | 5.4762 | 14.8673 | 16.5393 | 23.3739 | 28.8501 | 6.3361 | 8.5312 | 1.8862 | 1.672 | 3.3222 | 1.9861 | 6.8446 | 5.4762 | 14.8673 | 16.5393 | 23.3839 | 28.8601 | 0.01
5.8692 | 7.525 | 1.7782 | 1.997 | 3.2439 | 3.4055 | 10.7206 | 3.802 | 13.3942 | 15.3912 | 26.1118 | 29.9138 | 5.8692 | 7.525 | 1.7782 | 1.997 | 3.2439 | 3.4055 | 10.7306 | 3.802 | 13.3942 | 15.3912 | 26.1218 | 29.9238 | 0.01
6.3655 | 7.8551 | 2.0195 | 2.2204 | 3.6821 | 2.9951 | 7.2586 | 1.6366 | 14.2205 | 16.4409 | 23.6995 | 25.3361 | 6.3655 | 7.8551 | 2.0195 | 2.2204 | 3.6821 | 2.9951 | 7.2686 | 1.6366 | 14.2205 | 16.4409 | 23.7095 | 25.3461 | 0.01
6.5956 | 8.9514 | 2.0781 | 1.8296 | 0.88422 | 2.7505 | 4.4963 | 6.0877 | 15.547 | 17.3767 | 21.873 | 27.9607 | 6.5956 | 8.9514 | 2.0781 | 1.8296 | 0.88422 | 2.7505 | 4.5063 | 6.0877 | 15.547 | 17.3767 | 21.883 | 27.9707 | 0.01
6.7598 | 9.9966 | 1.8789 | 1.5907 | 3.6136 | 2.152 | 5.7502 | 5.2344 | 16.7564 | 18.3471 | 24.1126 | 29.3471 | 6.7598 | 9.9966 | 1.8789 | 1.5907 | 3.6136 | 2.152 | 5.7602 | 5.2344 | 16.7564 | 18.3471 | 24.1126 | 29.3471 | 0.01
5.816 | 9.2229 | 1.8299 | 1.5637 | 2.872 | 1.8906 | 8.5387 | 4.8728 | 15.0388 | 16.6025 | 25.1412 | 30.0139 | 5.816 | 9.2229 | 1.8299 | 1.5637 | 2.872 | 1.8906 | 8.5487 | 4.8728 | 15.0388 | 16.6025 | 25.1512 | 30.0239 | 0.01
7.3868 | 7.356 | 2.033 | 1.6463 | 1.578 | 2.5667 | 6.7153 | 5.0385 | 14.7428 | 16.3891 | 23.1044 | 28.1429 | 7.3868 | 7.356 | 2.033 | 1.6463 | 1.578 | 2.5667 | 6.7253 | 5.0385 | 14.7428 | 16.3891 | 23.1144 | 28.1529 | 0.01
5.8793 | 9.4847 | 1.5968 | 2.4421 | 2.3591 | 2.4651 | 5.3206 | 4.1281 | 15.364 | 17.8061 | 23.1267 | 27.2548 | 5.8793 | 9.4847 | 1.5968 | 2.4421 | 2.3591 | 2.4651 | 5.3306 | 4.1281 | 15.364 | 17.8061 | 23.1367 | 27.2648 | 0.01
6.0786 | 7.1197 | 2.0009 | 1.7932 | 3.6283 | 3.7847 | 6.0698 | 7.8151 | 13.1982 | 14.9914 | 22.4045 | 30.2195 | 6.0786 | 7.1197 | 2.0009 | 1.7932 | 3.6283 | 3.7847 | 6.0798 | 7.8151 | 13.1982 | 14.9914 | 22.4045 | 30.2195 | 0.01
6.4339 | 6.3705 | 1.961 | 2.2232 | 1.3545 | 3.4635 | 8.7253 | 5.7311 | 12.8044 | 15.0276 | 23.7529 | 29.4839 | 6.4339 | 6.3705 | 1.961 | 2.2232 | 1.3545 | 3.4635 | 8.7353 | 5.7311 | 12.8044 | 15.0276 | 23.7629 | 29.4939 | 0.01
5.4015 | 8.1606 | 1.926 | 1.6626 | 4.7752 | 2.7295 | 5.4551 | 5.5847 | 13.562 | 15.2246 | 22.7293 | 28.3141 | 5.4015 | 8.1606 | 1.926 | 1.6626 | 4.7752 | 2.7295 | 5.4651 | 5.5847 | 13.562 | 15.2246 | 22.7293 | 28.3141 | 0.01
6.5053 | 9.0682 | 2.0714 | 2.1324 | 4.6096 | 3.7067 | 4.9678 | 3.9765 | 15.5735 | 17.7059 | 26.0222 | 29.9987 | 6.5053 | 9.0682 | 2.0714 | 2.1324 | 4.6096 | 3.7067 | 4.9778 | 3.9765 | 15.5735 | 17.7059 | 26.0222 | 29.9987 | 0.01
5.3474 | 10.9232 | 2.0161 | 1.9338 | 2.901 | 1.5652 | 6.1922 | 4.3793 | 16.2706 | 18.2044 | 24.3966 | 28.776 | 5.3474 | 10.9232 | 2.0161 | 1.9338 | 2.901 | 1.5652 | 6.2022 | 4.3793 | 16.2706 | 18.2044 | 24.4066 | 28.786 | 0.01
6.2327 | 6.5718 | 1.7904 | 2.5299 | 1.8813 | 3.2231 | 5.6453 | 4.0482 | 12.8045 | 15.3344 | 20.9797 | 25.0279 | 6.2327 | 6.5718 | 1.7904 | 2.5299 | 1.8813 | 3.2231 | 5.6553 | 4.0482 | 12.8045 | 15.3344 | 20.9897 | 25.0379 | 0.01
5.2355 | 7.8724 | 1.9212 | 2.3876 | 1.8837 | 4.4691 | 8.3385 | 6.4858 | 13.1078 | 15.4954 | 23.8339 | 30.3198 | 5.2355 | 7.8724 | 1.9212 | 2.3876 | 1.8837 | 4.4691 | 8.3485 | 6.4858 | 13.1078 | 15.4954 | 23.8439 | 30.3298 | 0.01
6.116 | 9.1571 | 1.9155 | 1.5906 | 3.3107 | 3.3551 | 4.6648 | 6.1393 | 15.2731 | 16.8636 | 23.5295 | 29.6688 | 6.116 | 9.1571 | 1.9155 | 1.5906 | 3.3107 | 3.3551 | 4.6748 | 6.1393 | 15.2731 | 16.8636 | 23.5295 | 29.6688 | 0.01
6.5043 | 7.5549 | 2.2974 | 2.1749 | 3.2022 | 2.1248 | 6.3807 | 7.436 | 14.0592 | 16.2341 | 22.6148 | 30.0508 | 6.5043 | 7.5549 | 2.2974 | 2.1749 | 3.2022 | 2.1248 | 6.3907 | 7.436 | 14.0592 | 16.2341 | 22.6248 | 30.0608 | 0.01
5.6822 | 8.3427 | 2.3813 | 1.6809 | 2.2183 | 2.7225 | 7.5903 | 5.0768 | 14.0249 | 15.7058 | 23.2961 | 28.373 | 5.6822 | 8.3427 | 2.3813 | 1.6809 | 2.2183 | 2.7225 | 7.6003 | 5.0768 | 14.0249 | 15.7058 | 23.3061 | 28.383 | 0.01
5.933 | 8.0756 | 1.908 | 2.191 | 4.2175 | 2.8916 | 5.3347 | 5.8699 | 14.0085 | 16.1995 | 23.3086 | 29.1785 | 5.933 | 8.0756 | 1.908 | 2.191 | 4.2175 | 2.8916 | 5.3447 | 5.8699 | 14.0085 | 16.1995 | 23.3086 | 29.1785 | 0.01
5.0545 | 7.6746 | 2.0041 | 1.8734 | 2.4106 | 3.5074 | 6.1745 | 4.3434 | 12.729 | 14.6025 | 20.777 | 25.1204 | 5.0545 | 7.6746 | 2.0041 | 1.8734 | 2.4106 | 3.5074 | 6.1845 | 4.3434 | 12.729 | 14.6025 | 20.787 | 25.1304 | 0.01
5.8966 | 8.9027 | 2.1509 | 2.5616 | 4.6566 | 2.7436 | 9.3974 | 6.0419 | 14.7993 | 17.3608 | 26.7582 | 32.8001 | 5.8966 | 8.9027 | 2.1509 | 2.5616 | 4.6566 | 2.7436 | 9.4074 | 6.0419 | 14.7993 | 17.3608 | 26.7682 | 32.8101 | 0.01

## test activity H
A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6, .6) | B~N(8,1.3) | C~N(2,0.2) | D~N(2,0.3) | E~N(3,1) | F~N(3,0.6) | G~N(7,1.5) | H~N(5,1.2) | Event 1 | Event 2 | Event 3 | Event 4 | diff
-12.9745 | 3.8889 | 1.3675 | 1.0513 | -0.16242 | 1.1025 | 2.2564 | 1.2051 | -9.0857 | -8.0344 | -5.778 | -4.5729 | -12.9745 | 3.8889 | 1.3675 | 1.0513 | -0.16242 | 1.1025 | 2.2564 | 1.2151 | -9.0857 | -8.0344 | -5.778 | -4.5629 | 0.01
-0.12216 | 6.6735 | 1.7959 | 1.6939 | 1.9796 | 2.3878 | 5.4695 | 3.7756 | 6.5514 | 8.2453 | 13.7147 | 17.4903 | -0.12216 | 6.6735 | 1.7959 | 1.6939 | 1.9796 | 2.3878 | 5.4695 | 3.7856 | 6.5514 | 8.2453 | 13.7147 | 17.5003 | 0.01
6.9139 | 8.198 | 2.0305 | 2.0457 | 3.1523 | 3.0914 | 7.2285 | 5.1828 | 15.1119 | 17.1576 | 24.3861 | 29.5689 | 6.9139 | 8.198 | 2.0305 | 2.0457 | 3.1523 | 3.0914 | 7.2285 | 5.1928 | 15.1119 | 17.1576 | 24.3861 | 29.5789 | 0.01
12.6187 | 9.4341 | 2.2206 | 2.3309 | 4.1031 | 3.6619 | 8.6547 | 6.3237 | 22.0528 | 24.3837 | 33.0384 | 39.3622 | 12.6187 | 9.4341 | 2.2206 | 2.3309 | 4.1031 | 3.6619 | 8.6547 | 6.3337 | 22.0528 | 24.3837 | 33.0384 | 39.3722 | 0.01
2.4444 | 7.2296 | 1.8815 | 1.8222 | 2.4074 | 2.6444 | 6.1111 | 4.2889 | 9.674 | 11.4962 | 17.6073 | 21.8962 | 2.4444 | 7.2296 | 1.8815 | 1.8222 | 2.4074 | 2.6444 | 6.1111 | 4.2989 | 9.674 | 11.4962 | 17.6073 | 21.9062 | 0.01
13.5518 | 9.6362 | 2.2517 | 2.3776 | 4.2586 | 3.7552 | 8.888 | 6.5104 | 23.188 | 25.5656 | 34.4536 | 40.9639 | 13.5518 | 9.6362 | 2.2517 | 2.3776 | 4.2586 | 3.7552 | 8.888 | 6.5204 | 23.188 | 25.5656 | 34.4536 | 40.9739 | 0.01
9.2237 | 8.6985 | 2.1075 | 2.1612 | 3.5373 | 3.3224 | 7.8059 | 5.6447 | 17.9221 | 20.0833 | 27.8892 | 33.5339 | 9.2237 | 8.6985 | 2.1075 | 2.1612 | 3.5373 | 3.3224 | 7.8059 | 5.6547 | 17.9221 | 20.0833 | 27.8892 | 33.5439 | 0.01
13.2479 | 9.5704 | 2.2416 | 2.3624 | 4.208 | 3.7248 | 8.812 | 6.4496 | 22.8182 | 25.1806 | 33.9926 | 40.4422 | 13.2479 | 9.5704 | 2.2416 | 2.3624 | 4.208 | 3.7248 | 8.812 | 6.4596 | 22.8182 | 25.1806 | 33.9926 | 40.4522 | 0.01
14.8387 | 9.9151 | 2.2946 | 2.4419 | 4.4731 | 3.8839 | 9.2097 | 6.7677 | 24.7538 | 27.1957 | 36.4054 | 43.1731 | 14.8387 | 9.9151 | 2.2946 | 2.4419 | 4.4731 | 3.8839 | 9.2097 | 6.7777 | 24.7538 | 27.1957 | 36.4054 | 43.1831 | 0.01
5.5377 | 7.8998 | 1.9846 | 1.9769 | 2.9229 | 2.9538 | 6.8844 | 4.9075 | 13.4375 | 15.4144 | 22.2988 | 27.2063 | 5.5377 | 7.8998 | 1.9846 | 1.9769 | 2.9229 | 2.9538 | 6.8844 | 4.9175 | 13.4375 | 15.4144 | 22.2988 | 27.2163 | 0.01
3.6914 | 7.4998 | 1.923 | 1.8846 | 2.6152 | 2.7691 | 6.4229 | 4.5383 | 11.1913 | 13.0758 | 19.4987 | 24.037 | 3.6914 | 7.4998 | 1.923 | 1.8846 | 2.6152 | 2.7691 | 6.4229 | 4.5483 | 11.1913 | 13.0758 | 19.4987 | 24.047 | 0.01
15.412 | 10.0393 | 2.3137 | 2.4706 | 4.5687 | 3.9412 | 9.353 | 6.8824 | 25.4513 | 27.9219 | 37.2749 | 44.1573 | 15.412 | 10.0393 | 2.3137 | 2.4706 | 4.5687 | 3.9412 | 9.353 | 6.8924 | 25.4513 | 27.9219 | 37.2749 | 44.1673 | 0.01
-1.8093 | 6.308 | 1.7397 | 1.6095 | 1.6984 | 2.2191 | 5.0477 | 3.4381 | 4.4986 | 6.1082 | 11.1558 | 14.594 | -1.8093 | 6.308 | 1.7397 | 1.6095 | 1.6984 | 2.2191 | 5.0477 | 3.4481 | 4.4986 | 6.1082 | 11.1558 | 14.604 | 0.01
5.3552 | 7.8603 | 1.9785 | 1.9678 | 2.8925 | 2.9355 | 6.8388 | 4.871 | 13.2155 | 15.1833 | 22.0221 | 26.8931 | 5.3552 | 7.8603 | 1.9785 | 1.9678 | 2.8925 | 2.9355 | 6.8388 | 4.881 | 13.2155 | 15.1833 | 22.0221 | 26.9031 | 0.01
3.6258 | 7.4856 | 1.9209 | 1.8813 | 2.6043 | 2.7626 | 6.4065 | 4.5252 | 11.1114 | 12.9927 | 19.3991 | 23.9243 | 3.6258 | 7.4856 | 1.9209 | 1.8813 | 2.6043 | 2.7626 | 6.4065 | 4.5352 | 11.1114 | 12.9927 | 19.3991 | 23.9343 | 0.01
17.2865 | 10.4454 | 2.3762 | 2.5643 | 4.8811 | 4.1286 | 9.8216 | 7.2573 | 27.7319 | 30.2962 | 40.1178 | 47.3751 | 17.2865 | 10.4454 | 2.3762 | 2.5643 | 4.8811 | 4.1286 | 9.8216 | 7.2673 | 27.7319 | 30.2962 | 40.1178 | 47.3851 | 0.01
-1.2041 | 6.4391 | 1.7599 | 1.6398 | 1.7993 | 2.2796 | 5.199 | 3.5592 | 5.2351 | 6.8749 | 12.0738 | 15.633 | -1.2041 | 6.4391 | 1.7599 | 1.6398 | 1.7993 | 2.2796 | 5.199 | 3.5692 | 5.2351 | 6.8749 | 12.0738 | 15.643 | 0.01
10.4295 | 8.9597 | 2.1476 | 2.2215 | 3.7382 | 3.4429 | 8.1074 | 5.8859 | 19.3892 | 21.6107 | 29.7181 | 35.604 | 10.4295 | 8.9597 | 2.1476 | 2.2215 | 3.7382 | 3.4429 | 8.1074 | 5.8959 | 19.3892 | 21.6107 | 29.7181 | 35.614 | 0.01
3.5508 | 7.4693 | 1.9184 | 1.8775 | 2.5918 | 2.7551 | 6.3877 | 4.5102 | 11.0202 | 12.8977 | 19.2854 | 23.7956 | 3.5508 | 7.4693 | 1.9184 | 1.8775 | 2.5918 | 2.7551 | 6.3877 | 4.5202 | 11.0202 | 12.8977 | 19.2854 | 23.8056 | 0.01
8.8773 | 8.6234 | 2.0959 | 2.1439 | 3.4795 | 3.2877 | 7.7193 | 5.5755 | 17.5007 | 19.6445 | 27.3638 | 32.9393 | 8.8773 | 8.6234 | 2.0959 | 2.1439 | 3.4795 | 3.2877 | 7.7193 | 5.5855 | 17.5007 | 19.6445 | 27.3638 | 32.9493 | 0.01
10.0205 | 8.8711 | 2.134 | 2.201 | 3.6701 | 3.402 | 8.0051 | 5.8041 | 18.8916 | 21.0926 | 29.0977 | 34.9018 | 10.0205 | 8.8711 | 2.134 | 2.201 | 3.6701 | 3.402 | 8.0051 | 5.8141 | 18.8916 | 21.0926 | 29.0977 | 34.9118 | 0.01
8.7605 | 8.5981 | 2.092 | 2.138 | 3.4601 | 3.276 | 7.6901 | 5.5521 | 17.3586 | 19.4966 | 27.1867 | 32.7388 | 8.7605 | 8.5981 | 2.092 | 2.138 | 3.4601 | 3.276 | 7.6901 | 5.5621 | 17.3586 | 19.4966 | 27.1867 | 32.7488 | 0.01
13.6101 | 9.6489 | 2.2537 | 2.3805 | 4.2684 | 3.761 | 8.9025 | 6.522 | 23.259 | 25.6395 | 34.542 | 41.064 | 13.6101 | 9.6489 | 2.2537 | 2.3805 | 4.2684 | 3.761 | 8.9025 | 6.532 | 23.259 | 25.6395 | 34.542 | 41.074 | 0.01
-4.2589 | 5.7772 | 1.658 | 1.4871 | 1.2902 | 1.9741 | 4.4353 | 2.9482 | 1.5183 | 3.0053 | 7.4406 | 10.3888 | -4.2589 | 5.7772 | 1.658 | 1.4871 | 1.2902 | 1.9741 | 4.4353 | 2.9582 | 1.5183 | 3.0053 | 7.4406 | 10.3988 | 0.01
7.7808 | 8.3858 | 2.0594 | 2.089 | 3.2968 | 3.1781 | 7.4452 | 5.3562 | 16.1666 | 18.2557 | 25.7008 | 31.057 | 7.7808 | 8.3858 | 2.0594 | 2.089 | 3.2968 | 3.1781 | 7.4452 | 5.3662 | 16.1666 | 18.2557 | 25.7008 | 31.067 | 0.01
9.0241 | 8.6552 | 2.1008 | 2.1512 | 3.504 | 3.3024 | 7.756 | 5.6048 | 17.6794 | 19.8306 | 27.5866 | 33.1914 | 9.0241 | 8.6552 | 2.1008 | 2.1512 | 3.504 | 3.3024 | 7.756 | 5.6148 | 17.6794 | 19.8306 | 27.5866 | 33.2014 | 0.01
0.87462 | 6.8895 | 1.8292 | 1.7437 | 2.1458 | 2.4875 | 5.7187 | 3.9749 | 7.7641 | 9.5079 | 15.2265 | 19.2014 | 0.87462 | 6.8895 | 1.8292 | 1.7437 | 2.1458 | 2.4875 | 5.7187 | 3.9849 | 7.7641 | 9.5079 | 15.2265 | 19.2114 | 0.01
4.3537 | 7.6433 | 1.9451 | 1.9177 | 2.7256 | 2.8354 | 6.5884 | 4.6707 | 11.997 | 13.9147 | 20.5031 | 25.1739 | 4.3537 | 7.6433 | 1.9451 | 1.9177 | 2.7256 | 2.8354 | 6.5884 | 4.6807 | 11.997 | 13.9147 | 20.5031 | 25.1839 | 0.01
7.5191 | 8.3291 | 2.0506 | 2.076 | 3.2532 | 3.1519 | 7.3798 | 5.3038 | 15.8482 | 17.9242 | 25.3039 | 30.6078 | 7.5191 | 8.3291 | 2.0506 | 2.076 | 3.2532 | 3.1519 | 7.3798 | 5.3138 | 15.8482 | 17.9242 | 25.3039 | 30.6178 | 0.01
-1.0782 | 6.4664 | 1.7641 | 1.6461 | 1.8203 | 2.2922 | 5.2304 | 3.5844 | 5.3882 | 7.0343 | 12.2647 | 15.8491 | -1.0782 | 6.4664 | 1.7641 | 1.6461 | 1.8203 | 2.2922 | 5.2304 | 3.5944 | 5.3882 | 7.0343 | 12.2647 | 15.8591 | 0.01
-5.1061 | 5.5937 | 1.6298 | 1.4447 | 1.149 | 1.8894 | 4.2235 | 2.7788 | 0.48754 | 1.9322 | 6.1557 | 8.9345 | -5.1061 | 5.5937 | 1.6298 | 1.4447 | 1.149 | 1.8894 | 4.2235 | 2.7888 | 0.48754 | 1.9322 | 6.1557 | 8.9445 | 0.01
1.3629 | 6.9953 | 1.8454 | 1.7681 | 2.2271 | 2.5363 | 5.8407 | 4.0726 | 8.3582 | 10.1263 | 15.967 | 20.0396 | 1.3629 | 6.9953 | 1.8454 | 1.7681 | 2.2271 | 2.5363 | 5.8407 | 4.0826 | 8.3582 | 10.1263 | 15.967 | 20.0496 | 0.01
1.8639 | 7.1038 | 1.8621 | 1.7932 | 2.3106 | 2.5864 | 5.966 | 4.1728 | 8.9677 | 10.7609 | 16.7269 | 20.8996 | 1.8639 | 7.1038 | 1.8621 | 1.7932 | 2.3106 | 2.5864 | 5.966 | 4.1828 | 8.9677 | 10.7609 | 16.7269 | 20.9096 | 0.01
9.9802 | 8.8624 | 2.1327 | 2.199 | 3.6634 | 3.398 | 7.995 | 5.796 | 18.8426 | 21.0416 | 29.0366 | 34.8327 | 9.9802 | 8.8624 | 2.1327 | 2.199 | 3.6634 | 3.398 | 7.995 | 5.806 | 18.8426 | 21.0416 | 29.0366 | 34.8427 | 0.01
7.6476 | 8.357 | 2.0549 | 2.0824 | 3.2746 | 3.1648 | 7.4119 | 5.3295 | 16.0046 | 18.087 | 25.4989 | 30.8284 | 7.6476 | 8.357 | 2.0549 | 2.0824 | 3.2746 | 3.1648 | 7.4119 | 5.3395 | 16.0046 | 18.087 | 25.4989 | 30.8384 | 0.01
11.5709 | 9.207 | 2.1857 | 2.2785 | 3.9285 | 3.5571 | 8.3927 | 6.1142 | 20.778 | 23.0565 | 31.4492 | 37.5634 | 11.5709 | 9.207 | 2.1857 | 2.2785 | 3.9285 | 3.5571 | 8.3927 | 6.1242 | 20.778 | 23.0565 | 31.4492 | 37.5734 | 0.01
2.211 | 7.179 | 1.8737 | 1.8105 | 2.3685 | 2.6211 | 6.0527 | 4.2422 | 9.39 | 11.2006 | 17.2533 | 21.4955 | 2.211 | 7.179 | 1.8737 | 1.8105 | 2.3685 | 2.6211 | 6.0527 | 4.2522 | 9.39 | 11.2006 | 17.2533 | 21.5055 | 0.01
8.1676 | 8.4696 | 2.0723 | 2.1084 | 3.3613 | 3.2168 | 7.5419 | 5.4335 | 16.6372 | 18.7456 | 26.2875 | 31.721 | 8.1676 | 8.4696 | 2.0723 | 2.1084 | 3.3613 | 3.2168 | 7.5419 | 5.4435 | 16.6372 | 18.7456 | 26.2875 | 31.731 | 0.01
-1.5632 | 6.3613 | 1.7479 | 1.6218 | 1.7395 | 2.2437 | 5.1092 | 3.4874 | 4.7981 | 6.42 | 11.5292 | 15.0165 | -1.5632 | 6.3613 | 1.7479 | 1.6218 | 1.7395 | 2.2437 | 5.1092 | 3.4974 | 4.7981 | 6.42 | 11.5292 | 15.0265 | 0.01
6.51 | 8.1105 | 2.017 | 2.0255 | 3.085 | 3.051 | 7.1275 | 5.102 | 14.6205 | 16.646 | 23.7735 | 28.8754 | 6.51 | 8.1105 | 2.017 | 2.0255 | 3.085 | 3.051 | 7.1275 | 5.112 | 14.6205 | 16.646 | 23.7735 | 28.8854 | 0.01
9.2137 | 8.6963 | 2.1071 | 2.1607 | 3.5356 | 3.3214 | 7.8034 | 5.6427 | 17.91 | 20.0707 | 27.8741 | 33.5169 | 9.2137 | 8.6963 | 2.1071 | 2.1607 | 3.5356 | 3.3214 | 7.8034 | 5.6527 | 17.91 | 20.0707 | 27.8741 | 33.5269 | 0.01
2.0475 | 7.1436 | 1.8683 | 1.8024 | 2.3413 | 2.6048 | 6.0119 | 4.2095 | 9.1911 | 10.9935 | 17.0054 | 21.2149 | 2.0475 | 7.1436 | 1.8683 | 1.8024 | 2.3413 | 2.6048 | 6.0119 | 4.2195 | 9.1911 | 10.9935 | 17.0054 | 21.2249 | 0.01
2.251 | 7.1877 | 1.875 | 1.8125 | 2.3752 | 2.6251 | 6.0627 | 4.2502 | 9.4387 | 11.2513 | 17.314 | 21.5642 | 2.251 | 7.1877 | 1.875 | 1.8125 | 2.3752 | 2.6251 | 6.0627 | 4.2602 | 9.4387 | 11.2513 | 17.314 | 21.5742 | 0.01
3.4527 | 7.4481 | 1.9151 | 1.8726 | 2.5755 | 2.7453 | 6.3632 | 4.4905 | 10.9008 | 12.7734 | 19.1366 | 23.6272 | 3.4527 | 7.4481 | 1.9151 | 1.8726 | 2.5755 | 2.7453 | 6.3632 | 4.5005 | 10.9008 | 12.7734 | 19.1366 | 23.6372 | 0.01
-0.171 | 6.663 | 1.7943 | 1.6915 | 1.9715 | 2.3829 | 5.4573 | 3.7658 | 6.492 | 8.1834 | 13.6407 | 17.4065 | -0.171 | 6.663 | 1.7943 | 1.6915 | 1.9715 | 2.3829 | 5.4573 | 3.7758 | 6.492 | 8.1834 | 13.6407 | 17.4165 | 0.01
2.2975 | 7.1978 | 1.8766 | 1.8149 | 2.3829 | 2.6297 | 6.0744 | 4.2595 | 9.4953 | 11.3101 | 17.3845 | 21.644 | 2.2975 | 7.1978 | 1.8766 | 1.8149 | 2.3829 | 2.6297 | 6.0744 | 4.2695 | 9.4953 | 11.3101 | 17.3845 | 21.654 | 0.01
0.11826 | 6.7256 | 1.8039 | 1.7059 | 2.0197 | 2.4118 | 5.5296 | 3.8237 | 6.8439 | 8.5498 | 14.0794 | 17.903 | 0.11826 | 6.7256 | 1.8039 | 1.7059 | 2.0197 | 2.4118 | 5.5296 | 3.8337 | 6.8439 | 8.5498 | 14.0794 | 17.913 | 0.01
5.5591 | 7.9045 | 1.9853 | 1.978 | 2.9265 | 2.9559 | 6.8898 | 4.9118 | 13.4636 | 15.4416 | 22.3313 | 27.2432 | 5.5591 | 7.9045 | 1.9853 | 1.978 | 2.9265 | 2.9559 | 6.8898 | 4.9218 | 13.4636 | 15.4416 | 22.3313 | 27.2532 | 0.01
2.3412 | 7.2073 | 1.878 | 1.8171 | 2.3902 | 2.6341 | 6.0853 | 4.2682 | 9.5484 | 11.3655 | 17.4508 | 21.719 | 2.3412 | 7.2073 | 1.878 | 1.8171 | 2.3902 | 2.6341 | 6.0853 | 4.2782 | 9.5484 | 11.3655 | 17.4508 | 21.729 | 0.01
8.1691 | 8.47 | 2.0723 | 2.1085 | 3.3615 | 3.2169 | 7.5423 | 5.4338 | 16.639 | 18.7475 | 26.2897 | 31.7235 | 8.1691 | 8.47 | 2.0723 | 2.1085 | 3.3615 | 3.2169 | 7.5423 | 5.4438 | 16.639 | 18.7475 | 26.2897 | 31.7335 | 0.01
8.3035 | 8.4991 | 2.0768 | 2.1152 | 3.3839 | 3.2303 | 7.5759 | 5.4607 | 16.8026 | 18.9177 | 26.4936 | 31.9543 | 8.3035 | 8.4991 | 2.0768 | 2.1152 | 3.3839 | 3.2303 | 7.5759 | 5.4707 | 16.8026 | 18.9177 | 26.4936 | 31.9643 | 0.01
10.4961 | 8.9742 | 2.1499 | 2.2248 | 3.7493 | 3.4496 | 8.124 | 5.8992 | 19.4702 | 21.695 | 29.8191 | 35.7183 | 10.4961 | 8.9742 | 2.1499 | 2.2248 | 3.7493 | 3.4496 | 8.124 | 5.9092 | 19.4702 | 21.695 | 29.8191 | 35.7283 | 0.01
10.5815 | 8.9927 | 2.1527 | 2.2291 | 3.7636 | 3.4582 | 8.1454 | 5.9163 | 19.5742 | 21.8033 | 29.9486 | 35.8649 | 10.5815 | 8.9927 | 2.1527 | 2.2291 | 3.7636 | 3.4582 | 8.1454 | 5.9263 | 19.5742 | 21.8033 | 29.9486 | 35.8749 | 0.01
5.8599 | 7.9696 | 1.9953 | 1.993 | 2.9766 | 2.986 | 6.965 | 4.972 | 13.8295 | 15.8225 | 22.7875 | 27.7595 | 5.8599 | 7.9696 | 1.9953 | 1.993 | 2.9766 | 2.986 | 6.965 | 4.982 | 13.8295 | 15.8225 | 22.7875 | 27.7695 | 0.01
14.7012 | 9.8853 | 2.29 | 2.4351 | 4.4502 | 3.8701 | 9.1753 | 6.7402 | 24.5864 | 27.0215 | 36.1968 | 42.937 | 14.7012 | 9.8853 | 2.29 | 2.4351 | 4.4502 | 3.8701 | 9.1753 | 6.7502 | 24.5864 | 27.0215 | 36.1968 | 42.947 | 0.01
8.3236 | 8.5034 | 2.0775 | 2.1162 | 3.3873 | 3.2324 | 7.5809 | 5.4647 | 16.827 | 18.9432 | 26.5241 | 31.9888 | 8.3236 | 8.5034 | 2.0775 | 2.1162 | 3.3873 | 3.2324 | 7.5809 | 5.4747 | 16.827 | 18.9432 | 26.5241 | 31.9988 | 0.01
8.3401 | 8.507 | 2.078 | 2.117 | 3.39 | 3.234 | 7.585 | 5.468 | 16.8471 | 18.9641 | 26.5492 | 32.0172 | 8.3401 | 8.507 | 2.078 | 2.117 | 3.39 | 3.234 | 7.585 | 5.478 | 16.8471 | 18.9641 | 26.5492 | 32.0272 | 0.01
10.3472 | 8.9419 | 2.1449 | 2.2174 | 3.7245 | 3.4347 | 8.0868 | 5.8694 | 19.289 | 21.5064 | 29.5932 | 35.4626 | 10.3472 | 8.9419 | 2.1449 | 2.2174 | 3.7245 | 3.4347 | 8.0868 | 5.8794 | 19.289 | 21.5064 | 29.5932 | 35.4726 | 0.01
14.4633 | 9.8337 | 2.2821 | 2.4232 | 4.4105 | 3.8463 | 9.1158 | 6.6927 | 24.297 | 26.7201 | 35.836 | 42.5286 | 14.4633 | 9.8337 | 2.2821 | 2.4232 | 4.4105 | 3.8463 | 9.1158 | 6.7027 | 24.297 | 26.7201 | 35.836 | 42.5386 | 0.01
-3.5127 | 5.9389 | 1.6829 | 1.5244 | 1.4146 | 2.0487 | 4.6218 | 3.0975 | 2.4263 | 3.9506 | 8.5725 | 11.6699 | -3.5127 | 5.9389 | 1.6829 | 1.5244 | 1.4146 | 2.0487 | 4.6218 | 3.1075 | 2.4263 | 3.9506 | 8.5725 | 11.6799 | 0.01
5.4776 | 7.8868 | 1.9826 | 1.9739 | 2.9129 | 2.9478 | 6.8694 | 4.8955 | 13.3644 | 15.3383 | 22.2077 | 27.1032 | 5.4776 | 7.8868 | 1.9826 | 1.9739 | 2.9129 | 2.9478 | 6.8694 | 4.9055 | 13.3644 | 15.3383 | 22.2077 | 27.1132 | 0.01
5.2807 | 7.8442 | 1.976 | 1.964 | 2.8801 | 2.9281 | 6.8202 | 4.8561 | 13.1249 | 15.0889 | 21.9091 | 26.7653 | 5.2807 | 7.8442 | 1.976 | 1.964 | 2.8801 | 2.9281 | 6.8202 | 4.8661 | 13.1249 | 15.0889 | 21.9091 | 26.7753 | 0.01
7.9784 | 8.4286 | 2.0659 | 2.0989 | 3.3297 | 3.1978 | 7.4946 | 5.3957 | 16.407 | 18.5059 | 26.0005 | 31.3962 | 7.9784 | 8.4286 | 2.0659 | 2.0989 | 3.3297 | 3.1978 | 7.4946 | 5.4057 | 16.407 | 18.5059 | 26.0005 | 31.4062 | 0.01
13.8033 | 9.6907 | 2.2601 | 2.3902 | 4.3006 | 3.7803 | 8.9508 | 6.5607 | 23.494 | 25.8842 | 34.835 | 41.3957 | 13.8033 | 9.6907 | 2.2601 | 2.3902 | 4.3006 | 3.7803 | 8.9508 | 6.5707 | 23.494 | 25.8842 | 34.835 | 41.4057 | 0.01
8.5439 | 8.5512 | 2.0848 | 2.1272 | 3.424 | 3.2544 | 7.636 | 5.5088 | 17.0951 | 19.2223 | 26.8583 | 32.367 | 8.5439 | 8.5512 | 2.0848 | 2.1272 | 3.424 | 3.2544 | 7.636 | 5.5188 | 17.0951 | 19.2223 | 26.8583 | 32.377 | 0.01
4.4437 | 7.6628 | 1.9481 | 1.9222 | 2.7406 | 2.8444 | 6.6109 | 4.6887 | 12.1065 | 14.0287 | 20.6396 | 25.3283 | 4.4437 | 7.6628 | 1.9481 | 1.9222 | 2.7406 | 2.8444 | 6.6109 | 4.6987 | 12.1065 | 14.0287 | 20.6396 | 25.3383 | 0.01
7.7456 | 8.3782 | 2.0582 | 2.0873 | 3.2909 | 3.1746 | 7.4364 | 5.3491 | 16.1238 | 18.2111 | 25.6475 | 30.9967 | 7.7456 | 8.3782 | 2.0582 | 2.0873 | 3.2909 | 3.1746 | 7.4364 | 5.3591 | 16.1238 | 18.2111 | 25.6475 | 31.0067 | 0.01
-2.7103 | 6.1128 | 1.7097 | 1.5645 | 1.5483 | 2.129 | 4.8224 | 3.2579 | 3.4024 | 4.9669 | 9.7893 | 13.0473 | -2.7103 | 6.1128 | 1.7097 | 1.5645 | 1.5483 | 2.129 | 4.8224 | 3.2679 | 3.4024 | 4.9669 | 9.7893 | 13.0573 | 0.01
10.561 | 8.9882 | 2.152 | 2.2281 | 3.7602 | 3.4561 | 8.1403 | 5.9122 | 19.5493 | 21.7773 | 29.9176 | 35.8298 | 10.561 | 8.9882 | 2.152 | 2.2281 | 3.7602 | 3.4561 | 8.1403 | 5.9222 | 19.5493 | 21.7773 | 29.9176 | 35.8398 | 0.01
4.0867 | 7.5855 | 1.9362 | 1.9043 | 2.6811 | 2.8087 | 6.5217 | 4.6173 | 11.6721 | 13.5765 | 20.0982 | 24.7155 | 4.0867 | 7.5855 | 1.9362 | 1.9043 | 2.6811 | 2.8087 | 6.5217 | 4.6273 | 11.6721 | 13.5765 | 20.0982 | 24.7255 | 0.01
-2.8232 | 6.0883 | 1.7059 | 1.5588 | 1.5295 | 2.1177 | 4.7942 | 3.2354 | 3.2652 | 4.824 | 9.6182 | 12.8536 | -2.8232 | 6.0883 | 1.7059 | 1.5588 | 1.5295 | 2.1177 | 4.7942 | 3.2454 | 3.2652 | 4.824 | 9.6182 | 12.8636 | 0.01
4.6997 | 7.7183 | 1.9567 | 1.935 | 2.7833 | 2.87 | 6.6749 | 4.7399 | 12.418 | 14.353 | 21.0279 | 25.7678 | 4.6997 | 7.7183 | 1.9567 | 1.935 | 2.7833 | 2.87 | 6.6749 | 4.7499 | 12.418 | 14.353 | 21.0279 | 25.7778 | 0.01
9.2885 | 8.7125 | 2.1096 | 2.1644 | 3.5481 | 3.3288 | 7.8221 | 5.6577 | 18.0009 | 20.1654 | 27.9875 | 33.6452 | 9.2885 | 8.7125 | 2.1096 | 2.1644 | 3.5481 | 3.3288 | 7.8221 | 5.6677 | 18.0009 | 20.1654 | 27.9875 | 33.6552 | 0.01
4.1946 | 7.6088 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5486 | 4.6389 | 11.8034 | 13.7131 | 20.2618 | 24.9007 | 4.1946 | 7.6088 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5486 | 4.6489 | 11.8034 | 13.7131 | 20.2618 | 24.9107 | 0.01
17.7331 | 10.5422 | 2.3911 | 2.5867 | 4.9555 | 4.1733 | 9.9333 | 7.3466 | 28.2753 | 30.862 | 40.7953 | 48.1419 | 17.7331 | 10.5422 | 2.3911 | 2.5867 | 4.9555 | 4.1733 | 9.9333 | 7.3566 | 28.2753 | 30.862 | 40.7953 | 48.1519 | 0.01
5.1638 | 7.8188 | 1.9721 | 1.9582 | 2.8606 | 2.9164 | 6.791 | 4.8328 | 12.9827 | 14.9409 | 21.7318 | 26.5646 | 5.1638 | 7.8188 | 1.9721 | 1.9582 | 2.8606 | 2.9164 | 6.791 | 4.8428 | 12.9827 | 14.9409 | 21.7318 | 26.5746 | 0.01
-1.7584 | 6.319 | 1.7414 | 1.6121 | 1.7069 | 2.2242 | 5.0604 | 3.4483 | 4.5607 | 6.1727 | 11.2331 | 14.6815 | -1.7584 | 6.319 | 1.7414 | 1.6121 | 1.7069 | 2.2242 | 5.0604 | 3.4583 | 4.5607 | 6.1727 | 11.2331 | 14.6915 | 0.01
-8.3468 | 4.8915 | 1.5218 | 1.2827 | 0.60887 | 1.5653 | 3.4133 | 2.1306 | -3.4553 | -2.1726 | 1.2407 | 3.3713 | -8.3468 | 4.8915 | 1.5218 | 1.2827 | 0.60887 | 1.5653 | 3.4133 | 2.1406 | -3.4553 | -2.1726 | 1.2407 | 3.3813 | 0.01
-0.18201 | 6.6606 | 1.7939 | 1.6909 | 1.9697 | 2.3818 | 5.4545 | 3.7636 | 6.4786 | 8.1695 | 13.624 | 17.3876 | -0.18201 | 6.6606 | 1.7939 | 1.6909 | 1.9697 | 2.3818 | 5.4545 | 3.7736 | 6.4786 | 8.1695 | 13.624 | 17.3976 | 0.01
-6.2667 | 5.3422 | 1.5911 | 1.3867 | 0.95556 | 1.7733 | 3.9333 | 2.5467 | -0.92444 | 0.46223 | 4.3956 | 6.9422 | -6.2667 | 5.3422 | 1.5911 | 1.3867 | 0.95556 | 1.7733 | 3.9333 | 2.5567 | -0.92444 | 0.46223 | 4.3956 | 6.9522 | 0.01
10.6683 | 9.0115 | 2.1556 | 2.2334 | 3.778 | 3.4668 | 8.1671 | 5.9337 | 19.6798 | 21.9132 | 30.0803 | 36.0139 | 10.6683 | 9.0115 | 2.1556 | 2.2334 | 3.778 | 3.4668 | 8.1671 | 5.9437 | 19.6798 | 21.9132 | 30.0803 | 36.0239 | 0.01
6.5503 | 8.1192 | 2.0183 | 2.0275 | 3.0917 | 3.055 | 7.1376 | 5.1101 | 14.6695 | 16.697 | 23.8346 | 28.9447 | 6.5503 | 8.1192 | 2.0183 | 2.0275 | 3.0917 | 3.055 | 7.1376 | 5.1201 | 14.6695 | 16.697 | 23.8346 | 28.9547 | 0.01
7.3155 | 8.285 | 2.0438 | 2.0658 | 3.2192 | 3.1315 | 7.3289 | 5.2631 | 15.6005 | 17.6663 | 24.9951 | 30.2582 | 7.3155 | 8.285 | 2.0438 | 2.0658 | 3.2192 | 3.1315 | 7.3289 | 5.2731 | 15.6005 | 17.6663 | 24.9951 | 30.2682 | 0.01
12.1047 | 9.3227 | 2.2035 | 2.3052 | 4.0174 | 3.6105 | 8.5262 | 6.2209 | 21.4274 | 23.7326 | 32.2588 | 38.4797 | 12.1047 | 9.3227 | 2.2035 | 2.3052 | 4.0174 | 3.6105 | 8.5262 | 6.2309 | 21.4274 | 23.7326 | 32.2588 | 38.4897 | 0.01
11.6009 | 9.2135 | 2.1867 | 2.28 | 3.9335 | 3.5601 | 8.4002 | 6.1202 | 20.8144 | 23.0944 | 31.4947 | 37.6148 | 11.6009 | 9.2135 | 2.1867 | 2.28 | 3.9335 | 3.5601 | 8.4002 | 6.1302 | 20.8144 | 23.0944 | 31.4947 | 37.6248 | 0.01
16.131 | 10.195 | 2.3377 | 2.5065 | 4.6885 | 4.0131 | 9.5327 | 7.0262 | 26.326 | 28.8326 | 38.3653 | 45.3915 | 16.131 | 10.195 | 2.3377 | 2.5065 | 4.6885 | 4.0131 | 9.5327 | 7.0362 | 26.326 | 28.8326 | 38.3653 | 45.4015 | 0.01
7.8716 | 8.4055 | 2.0624 | 2.0936 | 3.3119 | 3.1872 | 7.4679 | 5.3743 | 16.2771 | 18.3706 | 25.8385 | 31.2128 | 7.8716 | 8.4055 | 2.0624 | 2.0936 | 3.3119 | 3.1872 | 7.4679 | 5.3843 | 16.2771 | 18.3706 | 25.8385 | 31.2228 | 0.01
6.6207 | 8.1345 | 2.0207 | 2.031 | 3.1035 | 3.0621 | 7.1552 | 5.1241 | 14.7552 | 16.7863 | 23.9415 | 29.0656 | 6.6207 | 8.1345 | 2.0207 | 2.031 | 3.1035 | 3.0621 | 7.1552 | 5.1341 | 14.7552 | 16.7863 | 23.9415 | 29.0756 | 0.01
15.6319 | 10.0869 | 2.3211 | 2.4816 | 4.6053 | 3.9632 | 9.408 | 6.9264 | 25.7188 | 28.2004 | 37.6084 | 44.5348 | 15.6319 | 10.0869 | 2.3211 | 2.4816 | 4.6053 | 3.9632 | 9.408 | 6.9364 | 25.7188 | 28.2004 | 37.6084 | 44.5448 | 0.01
12.4075 | 9.3883 | 2.2136 | 2.3204 | 4.0679 | 3.6408 | 8.6019 | 6.2815 | 21.7958 | 24.1162 | 32.7181 | 38.9996 | 12.4075 | 9.3883 | 2.2136 | 2.3204 | 4.0679 | 3.6408 | 8.6019 | 6.2915 | 21.7958 | 24.1162 | 32.7181 | 39.0096 | 0.01
3.1852 | 7.3901 | 1.9062 | 1.8593 | 2.5309 | 2.7185 | 6.2963 | 4.437 | 10.5753 | 12.4346 | 18.7309 | 23.168 | 3.1852 | 7.3901 | 1.9062 | 1.8593 | 2.5309 | 2.7185 | 6.2963 | 4.447 | 10.5753 | 12.4346 | 18.7309 | 23.178 | 0.01
8.0258 | 8.4389 | 2.0675 | 2.1013 | 3.3376 | 3.2026 | 7.5065 | 5.4052 | 16.4648 | 18.5661 | 26.0725 | 31.4777 | 8.0258 | 8.4389 | 2.0675 | 2.1013 | 3.3376 | 3.2026 | 7.5065 | 5.4152 | 16.4648 | 18.5661 | 26.0725 | 31.4877 | 0.01
-1.6375 | 6.3452 | 1.7454 | 1.6181 | 1.7271 | 2.2363 | 5.0906 | 3.4725 | 4.7078 | 6.3259 | 11.4165 | 14.889 | -1.6375 | 6.3452 | 1.7454 | 1.6181 | 1.7271 | 2.2363 | 5.0906 | 3.4825 | 4.7078 | 6.3259 | 11.4165 | 14.899 | 0.01
3.3169 | 7.4187 | 1.9106 | 1.8658 | 2.5528 | 2.7317 | 6.3292 | 4.4634 | 10.7355 | 12.6014 | 18.9306 | 23.394 | 3.3169 | 7.4187 | 1.9106 | 1.8658 | 2.5528 | 2.7317 | 6.3292 | 4.4734 | 10.7355 | 12.6014 | 18.9306 | 23.404 | 0.01
-1.316 | 6.4149 | 1.7561 | 1.6342 | 1.7807 | 2.2684 | 5.171 | 3.5368 | 5.0988 | 6.733 | 11.904 | 15.4408 | -1.316 | 6.4149 | 1.7561 | 1.6342 | 1.7807 | 2.2684 | 5.171 | 3.5468 | 5.0988 | 6.733 | 11.904 | 15.4508 | 0.01
7.4915 | 8.3232 | 2.0497 | 2.0746 | 3.2486 | 3.1491 | 7.3729 | 5.2983 | 15.8146 | 17.8892 | 25.2621 | 30.5603 | 7.4915 | 8.3232 | 2.0497 | 2.0746 | 3.2486 | 3.1491 | 7.3729 | 5.3083 | 15.8146 | 17.8892 | 25.2621 | 30.5703 | 0.01
1.1213 | 6.943 | 1.8374 | 1.7561 | 2.1869 | 2.5121 | 5.7803 | 4.0243 | 8.0643 | 9.8204 | 15.6007 | 19.625 | 1.1213 | 6.943 | 1.8374 | 1.7561 | 2.1869 | 2.5121 | 5.7803 | 4.0343 | 8.0643 | 9.8204 | 15.6007 | 19.635 | 0.01
-0.19129 | 6.6586 | 1.7936 | 1.6904 | 1.9681 | 2.3809 | 5.4522 | 3.7617 | 6.4673 | 8.1577 | 13.6099 | 17.3716 | -0.19129 | 6.6586 | 1.7936 | 1.6904 | 1.9681 | 2.3809 | 5.4522 | 3.7717 | 6.4673 | 8.1577 | 13.6099 | 17.3816 | 0.01
14.9327 | 9.9354 | 2.2978 | 2.4466 | 4.4888 | 3.8933 | 9.2332 | 6.7865 | 24.8681 | 27.3147 | 36.5479 | 43.3344 | 14.9327 | 9.9354 | 2.2978 | 2.4466 | 4.4888 | 3.8933 | 9.2332 | 6.7965 | 24.8681 | 27.3147 | 36.5479 | 43.3444 | 0.01
6.5945 | 8.1288 | 2.0198 | 2.0297 | 3.0991 | 3.0594 | 7.1486 | 5.1189 | 14.7233 | 16.753 | 23.9016 | 29.0205 | 6.5945 | 8.1288 | 2.0198 | 2.0297 | 3.0991 | 3.0594 | 7.1486 | 5.1289 | 14.7233 | 16.753 | 23.9016 | 29.0305 | 0.01
9.6841 | 8.7982 | 2.1228 | 2.1842 | 3.614 | 3.3684 | 7.921 | 5.7368 | 18.4823 | 20.6665 | 28.5875 | 34.3244 | 9.6841 | 8.7982 | 2.1228 | 2.1842 | 3.614 | 3.3684 | 7.921 | 5.7468 | 18.4823 | 20.6665 | 28.5875 | 34.3344 | 0.01
10.8748 | 9.0562 | 2.1625 | 2.2437 | 3.8125 | 3.4875 | 8.2187 | 5.975 | 19.931 | 22.1747 | 30.3934 | 36.3684 | 10.8748 | 9.0562 | 2.1625 | 2.2437 | 3.8125 | 3.4875 | 8.2187 | 5.985 | 19.931 | 22.1747 | 30.3934 | 36.3784 | 0.01
9.5191 | 8.7625 | 2.1173 | 2.176 | 3.5865 | 3.3519 | 7.8798 | 5.7038 | 18.2816 | 20.4576 | 28.3373 | 34.0412 | 9.5191 | 8.7625 | 2.1173 | 2.176 | 3.5865 | 3.3519 | 7.8798 | 5.7138 | 18.2816 | 20.4576 | 28.3373 | 34.0512 | 0.01
11.791 | 9.2547 | 2.193 | 2.2896 | 3.9652 | 3.5791 | 8.4478 | 6.1582 | 21.0458 | 23.3353 | 31.7831 | 37.9413 | 11.791 | 9.2547 | 2.193 | 2.2896 | 3.9652 | 3.5791 | 8.4478 | 6.1682 | 21.0458 | 23.3353 | 31.7831 | 37.9513 | 0.01
4.0406 | 7.5755 | 1.9347 | 1.902 | 2.6734 | 2.8041 | 6.5101 | 4.6081 | 11.6161 | 13.5181 | 20.0282 | 24.6364 | 4.0406 | 7.5755 | 1.9347 | 1.902 | 2.6734 | 2.8041 | 6.5101 | 4.6181 | 11.6161 | 13.5181 | 20.0282 | 24.6464 | 0.01
0.16694 | 6.7362 | 1.8056 | 1.7083 | 2.0278 | 2.4167 | 5.5417 | 3.8334 | 6.9031 | 8.6115 | 14.1532 | 17.9866 | 0.16694 | 6.7362 | 1.8056 | 1.7083 | 2.0278 | 2.4167 | 5.5417 | 3.8434 | 6.9031 | 8.6115 | 14.1532 | 17.9966 | 0.01
1.7732 | 7.0842 | 1.8591 | 1.7887 | 2.2955 | 2.5773 | 5.9433 | 4.1546 | 8.8574 | 10.6461 | 16.5894 | 20.7441 | 1.7732 | 7.0842 | 1.8591 | 1.7887 | 2.2955 | 2.5773 | 5.9433 | 4.1646 | 8.8574 | 10.6461 | 16.5894 | 20.7541 | 0.01
2.946 | 7.3383 | 1.8982 | 1.8473 | 2.491 | 2.6946 | 6.2365 | 4.3892 | 10.2843 | 12.1316 | 18.3681 | 22.7573 | 2.946 | 7.3383 | 1.8982 | 1.8473 | 2.491 | 2.6946 | 6.2365 | 4.3992 | 10.2843 | 12.1316 | 18.3681 | 22.7673 | 0.01
5.1699 | 7.8202 | 1.9723 | 1.9585 | 2.8617 | 2.917 | 6.7925 | 4.834 | 12.9901 | 14.9486 | 21.7411 | 26.5751 | 5.1699 | 7.8202 | 1.9723 | 1.9585 | 2.8617 | 2.917 | 6.7925 | 4.844 | 12.9901 | 14.9486 | 21.7411 | 26.5851 | 0.01
12.1677 | 9.3363 | 2.2056 | 2.3084 | 4.0279 | 3.6168 | 8.5419 | 6.2335 | 21.504 | 23.8124 | 32.3543 | 38.5878 | 12.1677 | 9.3363 | 2.2056 | 2.3084 | 4.0279 | 3.6168 | 8.5419 | 6.2435 | 21.504 | 23.8124 | 32.3543 | 38.5978 | 0.01
6.5433 | 8.1177 | 2.0181 | 2.0272 | 3.0906 | 3.0543 | 7.1358 | 5.1087 | 14.661 | 16.6882 | 23.824 | 28.9327 | 6.5433 | 8.1177 | 2.0181 | 2.0272 | 3.0906 | 3.0543 | 7.1358 | 5.1187 | 14.661 | 16.6882 | 23.824 | 28.9427 | 0.01
11.7076 | 9.2366 | 2.1903 | 2.2854 | 3.9513 | 3.5708 | 8.4269 | 6.1415 | 20.9442 | 23.2296 | 31.6565 | 37.798 | 11.7076 | 9.2366 | 2.1903 | 2.2854 | 3.9513 | 3.5708 | 8.4269 | 6.1515 | 20.9442 | 23.2296 | 31.6565 | 37.808 | 0.01
5.373 | 7.8641 | 1.9791 | 1.9686 | 2.8955 | 2.9373 | 6.8432 | 4.8746 | 13.2371 | 15.2058 | 22.049 | 26.9236 | 5.373 | 7.8641 | 1.9791 | 1.9686 | 2.8955 | 2.9373 | 6.8432 | 4.8846 | 13.2371 | 15.2058 | 22.049 | 26.9336 | 0.01
-2.6906 | 6.117 | 1.7103 | 1.5655 | 1.5516 | 2.1309 | 4.8273 | 3.2619 | 3.4264 | 4.9919 | 9.8193 | 13.0811 | -2.6906 | 6.117 | 1.7103 | 1.5655 | 1.5516 | 2.1309 | 4.8273 | 3.2719 | 3.4264 | 4.9919 | 9.8193 | 13.0911 | 0.01
5.7733 | 7.9509 | 1.9924 | 1.9887 | 2.9622 | 2.9773 | 6.9433 | 4.9547 | 13.7242 | 15.7128 | 22.6561 | 27.6108 | 5.7733 | 7.9509 | 1.9924 | 1.9887 | 2.9622 | 2.9773 | 6.9433 | 4.9647 | 13.7242 | 15.7128 | 22.6561 | 27.6208 | 0.01
1.0347 | 6.9242 | 1.8345 | 1.7517 | 2.1724 | 2.5035 | 5.7587 | 4.0069 | 7.9588 | 9.7106 | 15.4693 | 19.4762 | 1.0347 | 6.9242 | 1.8345 | 1.7517 | 2.1724 | 2.5035 | 5.7587 | 4.0169 | 7.9588 | 9.7106 | 15.4693 | 19.4862 | 0.01
17.9452 | 10.5881 | 2.3982 | 2.5973 | 4.9909 | 4.1945 | 9.9863 | 7.389 | 28.5333 | 31.1306 | 41.1169 | 48.5059 | 17.9452 | 10.5881 | 2.3982 | 2.5973 | 4.9909 | 4.1945 | 9.9863 | 7.399 | 28.5333 | 31.1306 | 41.1169 | 48.5159 | 0.01
2.4162 | 7.2235 | 1.8805 | 1.8208 | 2.4027 | 2.6416 | 6.104 | 4.2832 | 9.6397 | 11.4605 | 17.5645 | 21.8477 | 2.4162 | 7.2235 | 1.8805 | 1.8208 | 2.4027 | 2.6416 | 6.104 | 4.2932 | 9.6397 | 11.4605 | 17.5645 | 21.8577 | 0.01
5.5634 | 7.9054 | 1.9854 | 1.9782 | 2.9272 | 2.9563 | 6.8909 | 4.9127 | 13.4688 | 15.447 | 22.3378 | 27.2505 | 5.5634 | 7.9054 | 1.9854 | 1.9782 | 2.9272 | 2.9563 | 6.8909 | 4.9227 | 13.4688 | 15.447 | 22.3378 | 27.2605 | 0.01
-4.3193 | 5.7641 | 1.656 | 1.484 | 1.2801 | 1.9681 | 4.4202 | 2.9361 | 1.4448 | 2.9288 | 7.349 | 10.2851 | -4.3193 | 5.7641 | 1.656 | 1.484 | 1.2801 | 1.9681 | 4.4202 | 2.9461 | 1.4448 | 2.9288 | 7.349 | 10.2951 | 0.01
-1.7225 | 6.3268 | 1.7426 | 1.6139 | 1.7129 | 2.2278 | 5.0694 | 3.4555 | 4.6043 | 6.2182 | 11.2876 | 14.7431 | -1.7225 | 6.3268 | 1.7426 | 1.6139 | 1.7129 | 2.2278 | 5.0694 | 3.4655 | 4.6043 | 6.2182 | 11.2876 | 14.7531 | 0.01
5.3795 | 7.8656 | 1.9793 | 1.969 | 2.8966 | 2.9379 | 6.8449 | 4.8759 | 13.245 | 15.214 | 22.0589 | 26.9348 | 5.3795 | 7.8656 | 1.9793 | 1.969 | 2.8966 | 2.9379 | 6.8449 | 4.8859 | 13.245 | 15.214 | 22.0589 | 26.9448 | 0.01
2.8529 | 7.3181 | 1.8951 | 1.8426 | 2.4755 | 2.6853 | 6.2132 | 4.3706 | 10.171 | 12.0137 | 18.2269 | 22.5975 | 2.8529 | 7.3181 | 1.8951 | 1.8426 | 2.4755 | 2.6853 | 6.2132 | 4.3806 | 10.171 | 12.0137 | 18.2269 | 22.6075 | 0.01
4.9315 | 7.7685 | 1.9644 | 1.9466 | 2.8219 | 2.8931 | 6.7329 | 4.7863 | 12.6999 | 14.6465 | 21.3794 | 26.1657 | 4.9315 | 7.7685 | 1.9644 | 1.9466 | 2.8219 | 2.8931 | 6.7329 | 4.7963 | 12.6999 | 14.6465 | 21.3794 | 26.1757 | 0.01
8.9348 | 8.6359 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7337 | 5.587 | 17.5707 | 19.7175 | 27.4512 | 33.0382 | 8.9348 | 8.6359 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7337 | 5.597 | 17.5707 | 19.7175 | 27.4512 | 33.0482 | 0.01
18.576 | 10.7248 | 2.4192 | 2.6288 | 5.096 | 4.2576 | 10.144 | 7.5152 | 29.3008 | 31.9296 | 42.0736 | 49.5888 | 18.576 | 10.7248 | 2.4192 | 2.6288 | 5.096 | 4.2576 | 10.144 | 7.5252 | 29.3008 | 31.9296 | 42.0736 | 49.5988 | 0.01
10.8329 | 9.0471 | 2.1611 | 2.2416 | 3.8055 | 3.4833 | 8.2082 | 5.9666 | 19.88 | 22.1217 | 30.3299 | 36.2965 | 10.8329 | 9.0471 | 2.1611 | 2.2416 | 3.8055 | 3.4833 | 8.2082 | 5.9766 | 19.88 | 22.1217 | 30.3299 | 36.3065 | 0.01
20.2137 | 11.0796 | 2.4738 | 2.7107 | 5.3689 | 4.4214 | 10.5534 | 7.8427 | 31.2933 | 34.004 | 44.5574 | 52.4001 | 20.2137 | 11.0796 | 2.4738 | 2.7107 | 5.3689 | 4.4214 | 10.5534 | 7.8527 | 31.2933 | 34.004 | 44.5574 | 52.4101 | 0.01
-2.0597 | 6.2537 | 1.7313 | 1.597 | 1.6567 | 2.194 | 4.9851 | 3.3881 | 4.1941 | 5.7911 | 10.7762 | 14.1642 | -2.0597 | 6.2537 | 1.7313 | 1.597 | 1.6567 | 2.194 | 4.9851 | 3.3981 | 4.1941 | 5.7911 | 10.7762 | 14.1742 | 0.01
10.1219 | 8.8931 | 2.1374 | 2.2061 | 3.687 | 3.4122 | 8.0305 | 5.8244 | 19.015 | 21.2211 | 29.2516 | 35.0759 | 10.1219 | 8.8931 | 2.1374 | 2.2061 | 3.687 | 3.4122 | 8.0305 | 5.8344 | 19.015 | 21.2211 | 29.2516 | 35.0859 | 0.01
9.1303 | 8.6782 | 2.1043 | 2.1565 | 3.5217 | 3.313 | 7.7826 | 5.6261 | 17.8085 | 19.965 | 27.7476 | 33.3737 | 9.1303 | 8.6782 | 2.1043 | 2.1565 | 3.5217 | 3.313 | 7.7826 | 5.6361 | 17.8085 | 19.965 | 27.7476 | 33.3837 | 0.01
1.075 | 6.9329 | 1.8358 | 1.7537 | 2.1792 | 2.5075 | 5.7687 | 4.015 | 8.0079 | 9.7616 | 15.5304 | 19.5454 | 1.075 | 6.9329 | 1.8358 | 1.7537 | 2.1792 | 2.5075 | 5.7687 | 4.025 | 8.0079 | 9.7616 | 15.5304 | 19.5554 | 0.01
-4.9896 | 5.6189 | 1.6337 | 1.4505 | 1.1684 | 1.901 | 4.2526 | 2.8021 | 0.62936 | 2.0799 | 6.3325 | 9.1346 | -4.9896 | 5.6189 | 1.6337 | 1.4505 | 1.1684 | 1.901 | 4.2526 | 2.8121 | 0.62936 | 2.0799 | 6.3325 | 9.1446 | 0.01
-0.62885 | 6.5637 | 1.779 | 1.6686 | 1.8952 | 2.3371 | 5.3428 | 3.6742 | 5.9349 | 7.6035 | 12.9462 | 16.6205 | -0.62885 | 6.5637 | 1.779 | 1.6686 | 1.8952 | 2.3371 | 5.3428 | 3.6842 | 5.9349 | 7.6035 | 12.9462 | 16.6305 | 0.01
7.2339 | 8.2674 | 2.0411 | 2.0617 | 3.2057 | 3.1234 | 7.3085 | 5.2468 | 15.5013 | 17.563 | 24.8715 | 30.1183 | 7.2339 | 8.2674 | 2.0411 | 2.0617 | 3.2057 | 3.1234 | 7.3085 | 5.2568 | 15.5013 | 17.563 | 24.8715 | 30.1283 | 0.01
10.4833 | 8.9714 | 2.1494 | 2.2242 | 3.7472 | 3.4483 | 8.1208 | 5.8967 | 19.4547 | 21.6788 | 29.7997 | 35.6963 | 10.4833 | 8.9714 | 2.1494 | 2.2242 | 3.7472 | 3.4483 | 8.1208 | 5.9067 | 19.4547 | 21.6788 | 29.7997 | 35.7063 | 0.01
17.6691 | 10.5283 | 2.389 | 2.5835 | 4.9448 | 4.1669 | 9.9173 | 7.3338 | 28.1974 | 30.7808 | 40.6981 | 48.0319 | 17.6691 | 10.5283 | 2.389 | 2.5835 | 4.9448 | 4.1669 | 9.9173 | 7.3438 | 28.1974 | 30.7808 | 40.6981 | 48.0419 | 0.01
10.1095 | 8.8904 | 2.137 | 2.2055 | 3.6849 | 3.4109 | 8.0274 | 5.8219 | 18.9999 | 21.2053 | 29.2327 | 35.0546 | 10.1095 | 8.8904 | 2.137 | 2.2055 | 3.6849 | 3.4109 | 8.0274 | 5.8319 | 18.9999 | 21.2053 | 29.2327 | 35.0646 | 0.01
9.4732 | 8.7525 | 2.1158 | 2.1737 | 3.5789 | 3.3473 | 7.8683 | 5.6946 | 18.2258 | 20.3994 | 28.2677 | 33.9624 | 9.4732 | 8.7525 | 2.1158 | 2.1737 | 3.5789 | 3.3473 | 7.8683 | 5.7046 | 18.2258 | 20.3994 | 28.2677 | 33.9724 | 0.01
6.8688 | 8.1882 | 2.029 | 2.0434 | 3.1448 | 3.0869 | 7.2172 | 5.1738 | 15.057 | 17.1005 | 24.3177 | 29.4914 | 6.8688 | 8.1882 | 2.029 | 2.0434 | 3.1448 | 3.0869 | 7.2172 | 5.1838 | 15.057 | 17.1005 | 24.3177 | 29.5014 | 0.01
-7.7712 | 5.0162 | 1.541 | 1.3114 | 0.7048 | 1.6229 | 3.5572 | 2.2458 | -2.755 | -1.4435 | 2.1137 | 4.3594 | -7.7712 | 5.0162 | 1.541 | 1.3114 | 0.7048 | 1.6229 | 3.5572 | 2.2558 | -2.755 | -1.4435 | 2.1137 | 4.3694 | 0.01
6.6159 | 8.1335 | 2.0205 | 2.0308 | 3.1027 | 3.0616 | 7.154 | 5.1232 | 14.7494 | 16.7802 | 23.9342 | 29.0574 | 6.6159 | 8.1335 | 2.0205 | 2.0308 | 3.1027 | 3.0616 | 7.154 | 5.1332 | 14.7494 | 16.7802 | 23.9342 | 29.0674 | 0.01
7.7482 | 8.3788 | 2.0583 | 2.0874 | 3.2914 | 3.1748 | 7.437 | 5.3496 | 16.127 | 18.2144 | 25.6514 | 31.0011 | 7.7482 | 8.3788 | 2.0583 | 2.0874 | 3.2914 | 3.1748 | 7.437 | 5.3596 | 16.127 | 18.2144 | 25.6514 | 31.0111 | 0.01
11.3824 | 9.1662 | 2.1794 | 2.2691 | 3.8971 | 3.5382 | 8.3456 | 6.0765 | 20.5485 | 22.8177 | 31.1632 | 37.2397 | 11.3824 | 9.1662 | 2.1794 | 2.2691 | 3.8971 | 3.5382 | 8.3456 | 6.0865 | 20.5485 | 22.8177 | 31.1632 | 37.2497 | 0.01
3.369 | 7.4299 | 1.9123 | 1.8684 | 2.5615 | 2.7369 | 6.3422 | 4.4738 | 10.7989 | 12.6674 | 19.0096 | 23.4834 | 3.369 | 7.4299 | 1.9123 | 1.8684 | 2.5615 | 2.7369 | 6.3422 | 4.4838 | 10.7989 | 12.6674 | 19.0096 | 23.4934 | 0.01
12.951 | 9.506 | 2.2317 | 2.3475 | 4.1585 | 3.6951 | 8.7377 | 6.3902 | 22.457 | 24.8046 | 33.5423 | 39.9325 | 12.951 | 9.506 | 2.2317 | 2.3475 | 4.1585 | 3.6951 | 8.7377 | 6.4002 | 22.457 | 24.8046 | 33.5423 | 39.9425 | 0.01
0.55287 | 6.8198 | 1.8184 | 1.7276 | 2.0921 | 2.4553 | 5.6382 | 3.9106 | 7.3727 | 9.1003 | 14.7385 | 18.6491 | 0.55287 | 6.8198 | 1.8184 | 1.7276 | 2.0921 | 2.4553 | 5.6382 | 3.9206 | 7.3727 | 9.1003 | 14.7385 | 18.6591 | 0.01
5.8476 | 7.967 | 1.9949 | 1.9924 | 2.9746 | 2.9848 | 6.9619 | 4.9695 | 13.8146 | 15.807 | 22.7689 | 27.7384 | 5.8476 | 7.967 | 1.9949 | 1.9924 | 2.9746 | 2.9848 | 6.9619 | 4.9795 | 13.8146 | 15.807 | 22.7689 | 27.7484 | 0.01
1.2162 | 6.9635 | 1.8405 | 1.7608 | 2.2027 | 2.5216 | 5.8041 | 4.0432 | 8.1798 | 9.9406 | 15.7446 | 19.7879 | 1.2162 | 6.9635 | 1.8405 | 1.7608 | 2.2027 | 2.5216 | 5.8041 | 4.0532 | 8.1798 | 9.9406 | 15.7446 | 19.7979 | 0.01
12.2562 | 9.3555 | 2.2085 | 2.3128 | 4.0427 | 3.6256 | 8.564 | 6.2512 | 21.6117 | 23.9245 | 32.4885 | 38.7398 | 12.2562 | 9.3555 | 2.2085 | 2.3128 | 4.0427 | 3.6256 | 8.564 | 6.2612 | 21.6117 | 23.9245 | 32.4885 | 38.7498 | 0.01
4.5273 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7055 | 12.2082 | 14.1346 | 20.7664 | 25.4718 | 4.5273 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7155 | 12.2082 | 14.1346 | 20.7664 | 25.4818 | 0.01
-1.3747 | 6.4021 | 1.7542 | 1.6313 | 1.7709 | 2.2625 | 5.1563 | 3.5251 | 5.0275 | 6.6587 | 11.815 | 15.3401 | -1.3747 | 6.4021 | 1.7542 | 1.6313 | 1.7709 | 2.2625 | 5.1563 | 3.5351 | 5.0275 | 6.6587 | 11.815 | 15.3501 | 0.01
7.568 | 8.3397 | 2.0523 | 2.0784 | 3.2613 | 3.1568 | 7.392 | 5.3136 | 15.9077 | 17.9861 | 25.3781 | 30.6917 | 7.568 | 8.3397 | 2.0523 | 2.0784 | 3.2613 | 3.1568 | 7.392 | 5.3236 | 15.9077 | 17.9861 | 25.3781 | 30.7017 | 0.01
17.8346 | 10.5642 | 2.3945 | 2.5917 | 4.9724 | 4.1835 | 9.9586 | 7.3669 | 28.3987 | 30.9905 | 40.9491 | 48.316 | 17.8346 | 10.5642 | 2.3945 | 2.5917 | 4.9724 | 4.1835 | 9.9586 | 7.3769 | 28.3987 | 30.9905 | 40.9491 | 48.326 | 0.01
14.6358 | 9.8711 | 2.2879 | 2.4318 | 4.4393 | 3.8636 | 9.159 | 6.7272 | 24.5069 | 26.9387 | 36.0977 | 42.8248 | 14.6358 | 9.8711 | 2.2879 | 2.4318 | 4.4393 | 3.8636 | 9.159 | 6.7372 | 24.5069 | 26.9387 | 36.0977 | 42.8348 | 0.01
14.7192 | 9.8892 | 2.2906 | 2.436 | 4.4532 | 3.8719 | 9.1798 | 6.7438 | 24.6084 | 27.0443 | 36.2241 | 42.968 | 14.7192 | 9.8892 | 2.2906 | 2.436 | 4.4532 | 3.8719 | 9.1798 | 6.7538 | 24.6084 | 27.0443 | 36.2241 | 42.978 | 0.01
8.6596 | 8.5763 | 2.0887 | 2.133 | 3.4433 | 3.266 | 7.6649 | 5.5319 | 17.2359 | 19.3689 | 27.0338 | 32.5657 | 8.6596 | 8.5763 | 2.0887 | 2.133 | 3.4433 | 3.266 | 7.6649 | 5.5419 | 17.2359 | 19.3689 | 27.0338 | 32.5757 | 0.01
-0.8912 | 6.5069 | 1.7703 | 1.6554 | 1.8515 | 2.3109 | 5.2772 | 3.6218 | 5.6157 | 7.2712 | 12.5484 | 16.1701 | -0.8912 | 6.5069 | 1.7703 | 1.6554 | 1.8515 | 2.3109 | 5.2772 | 3.6318 | 5.6157 | 7.2712 | 12.5484 | 16.1801 | 0.01
0.11658 | 6.7253 | 1.8039 | 1.7058 | 2.0194 | 2.4117 | 5.5291 | 3.8233 | 6.8418 | 8.5477 | 14.0768 | 17.9001 | 0.11658 | 6.7253 | 1.8039 | 1.7058 | 2.0194 | 2.4117 | 5.5291 | 3.8333 | 6.8418 | 8.5477 | 14.0768 | 17.9101 | 0.01
2.9789 | 7.3454 | 1.8993 | 1.8489 | 2.4965 | 2.6979 | 6.2447 | 4.3958 | 10.3243 | 12.1733 | 18.418 | 22.8138 | 2.9789 | 7.3454 | 1.8993 | 1.8489 | 2.4965 | 2.6979 | 6.2447 | 4.4058 | 10.3243 | 12.1733 | 18.418 | 22.8238 | 0.01
10.7182 | 9.0223 | 2.1573 | 2.2359 | 3.7864 | 3.4718 | 8.1796 | 5.9436 | 19.7405 | 21.9764 | 30.156 | 36.0997 | 10.7182 | 9.0223 | 2.1573 | 2.2359 | 3.7864 | 3.4718 | 8.1796 | 5.9536 | 19.7405 | 21.9764 | 30.156 | 36.1097 | 0.01
8.2018 | 8.4771 | 2.0734 | 2.1101 | 3.367 | 3.2202 | 7.5505 | 5.4404 | 16.6789 | 18.789 | 26.3395 | 31.7798 | 8.2018 | 8.4771 | 2.0734 | 2.1101 | 3.367 | 3.2202 | 7.5505 | 5.4504 | 16.6789 | 18.789 | 26.3395 | 31.7898 | 0.01
14.9186 | 9.9324 | 2.2973 | 2.4459 | 4.4864 | 3.8919 | 9.2296 | 6.7837 | 24.8509 | 27.2969 | 36.5265 | 43.3102 | 14.9186 | 9.9324 | 2.2973 | 2.4459 | 4.4864 | 3.8919 | 9.2296 | 6.7937 | 24.8509 | 27.2969 | 36.5265 | 43.3202 | 0.01
3.278 | 7.4102 | 1.9093 | 1.8639 | 2.5463 | 2.7278 | 6.3195 | 4.4556 | 10.6882 | 12.5521 | 18.8716 | 23.3272 | 3.278 | 7.4102 | 1.9093 | 1.8639 | 2.5463 | 2.7278 | 6.3195 | 4.4656 | 10.6882 | 12.5521 | 18.8716 | 23.3372 | 0.01
11.9059 | 9.2796 | 2.1969 | 2.2953 | 3.9843 | 3.5906 | 8.4765 | 6.1812 | 21.1855 | 23.4808 | 31.9572 | 38.1384 | 11.9059 | 9.2796 | 2.1969 | 2.2953 | 3.9843 | 3.5906 | 8.4765 | 6.1912 | 21.1855 | 23.4808 | 31.9572 | 38.1484 | 0.01
0.21186 | 6.7459 | 1.8071 | 1.7106 | 2.0353 | 2.4212 | 5.553 | 3.8424 | 6.9578 | 8.6684 | 14.2213 | 18.0637 | 0.21186 | 6.7459 | 1.8071 | 1.7106 | 2.0353 | 2.4212 | 5.553 | 3.8524 | 6.9578 | 8.6684 | 14.2213 | 18.0737 | 0.01
8.3077 | 8.5 | 2.0769 | 2.1154 | 3.3846 | 3.2308 | 7.5769 | 5.4615 | 16.8077 | 18.9231 | 26.5001 | 31.9616 | 8.3077 | 8.5 | 2.0769 | 2.1154 | 3.3846 | 3.2308 | 7.5769 | 5.4715 | 16.8077 | 18.9231 | 26.5001 | 31.9716 | 0.01
0.99521 | 6.9156 | 1.8332 | 1.7498 | 2.1659 | 2.4995 | 5.7488 | 3.999 | 7.9108 | 9.6606 | 15.4094 | 19.4084 | 0.99521 | 6.9156 | 1.8332 | 1.7498 | 2.1659 | 2.4995 | 5.7488 | 4.009 | 7.9108 | 9.6606 | 15.4094 | 19.4184 | 0.01
10.022 | 8.8714 | 2.1341 | 2.2011 | 3.6703 | 3.4022 | 8.0055 | 5.8044 | 18.8934 | 21.0945 | 29.1 | 34.9045 | 10.022 | 8.8714 | 2.1341 | 2.2011 | 3.6703 | 3.4022 | 8.0055 | 5.8144 | 18.8934 | 21.0945 | 29.1 | 34.9145 | 0.01
-5.1718 | 5.5794 | 1.6276 | 1.4414 | 1.138 | 1.8828 | 4.207 | 2.7656 | 0.4076 | 1.849 | 6.0561 | 8.8217 | -5.1718 | 5.5794 | 1.6276 | 1.4414 | 1.138 | 1.8828 | 4.207 | 2.7756 | 0.4076 | 1.849 | 6.0561 | 8.8317 | 0.01
-1.0844 | 6.465 | 1.7639 | 1.6458 | 1.8193 | 2.2916 | 5.2289 | 3.5831 | 5.3806 | 7.0264 | 12.2553 | 15.8384 | -1.0844 | 6.465 | 1.7639 | 1.6458 | 1.8193 | 2.2916 | 5.2289 | 3.5931 | 5.3806 | 7.0264 | 12.2553 | 15.8484 | 0.01
6.9795 | 8.2122 | 2.0326 | 2.049 | 3.1632 | 3.0979 | 7.2449 | 5.1959 | 15.1917 | 17.2407 | 24.4855 | 29.6814 | 6.9795 | 8.2122 | 2.0326 | 2.049 | 3.1632 | 3.0979 | 7.2449 | 5.2059 | 15.1917 | 17.2407 | 24.4855 | 29.6914 | 0.01
1.3132 | 6.9845 | 1.8438 | 1.7657 | 2.2189 | 2.5313 | 5.8283 | 4.0626 | 8.2978 | 10.0634 | 15.8917 | 19.9544 | 1.3132 | 6.9845 | 1.8438 | 1.7657 | 2.2189 | 2.5313 | 5.8283 | 4.0726 | 8.2978 | 10.0634 | 15.8917 | 19.9644 | 0.01
1.3639 | 6.9955 | 1.8455 | 1.7682 | 2.2273 | 2.5364 | 5.841 | 4.0728 | 8.3594 | 10.1276 | 15.9686 | 20.0414 | 1.3639 | 6.9955 | 1.8455 | 1.7682 | 2.2273 | 2.5364 | 5.841 | 4.0828 | 8.3594 | 10.1276 | 15.9686 | 20.0514 | 0.01
-1.4768 | 6.38 | 1.7508 | 1.6262 | 1.7539 | 2.2523 | 5.1308 | 3.5046 | 4.9032 | 6.5293 | 11.6601 | 15.1648 | -1.4768 | 6.38 | 1.7508 | 1.6262 | 1.7539 | 2.2523 | 5.1308 | 3.5146 | 4.9032 | 6.5293 | 11.6601 | 15.1748 | 0.01
6.5105 | 8.1106 | 2.017 | 2.0255 | 3.0851 | 3.0511 | 7.1276 | 5.1021 | 14.6211 | 16.6466 | 23.7743 | 28.8764 | 6.5105 | 8.1106 | 2.017 | 2.0255 | 3.0851 | 3.0511 | 7.1276 | 5.1121 | 14.6211 | 16.6466 | 23.7743 | 28.8864 | 0.01
2.9522 | 7.3396 | 1.8984 | 1.8476 | 2.492 | 2.6952 | 6.238 | 4.3904 | 10.2918 | 12.1394 | 18.3775 | 22.7679 | 2.9522 | 7.3396 | 1.8984 | 1.8476 | 2.492 | 2.6952 | 6.238 | 4.4004 | 10.2918 | 12.1394 | 18.3775 | 22.7779 | 0.01
6.1645 | 8.0356 | 2.0055 | 2.0082 | 3.0274 | 3.0165 | 7.0411 | 5.0329 | 14.2002 | 16.2084 | 23.2495 | 28.2824 | 6.1645 | 8.0356 | 2.0055 | 2.0082 | 3.0274 | 3.0165 | 7.0411 | 5.0429 | 14.2002 | 16.2084 | 23.2495 | 28.2924 | 0.01
3.115 | 7.3749 | 1.9038 | 1.8557 | 2.5192 | 2.7115 | 6.2787 | 4.423 | 10.4899 | 12.3457 | 18.6244 | 23.0474 | 3.115 | 7.3749 | 1.9038 | 1.8557 | 2.5192 | 2.7115 | 6.2787 | 4.433 | 10.4899 | 12.3457 | 18.6244 | 23.0574 | 0.01
6.4626 | 8.1002 | 2.0154 | 2.0231 | 3.0771 | 3.0463 | 7.1157 | 5.0925 | 14.5628 | 16.586 | 23.7016 | 28.7941 | 6.4626 | 8.1002 | 2.0154 | 2.0231 | 3.0771 | 3.0463 | 7.1157 | 5.1025 | 14.5628 | 16.586 | 23.7016 | 28.8041 | 0.01
16.0124 | 10.1694 | 2.3337 | 2.5006 | 4.6687 | 4.0012 | 9.5031 | 7.0025 | 26.1817 | 28.6824 | 38.1855 | 45.1879 | 16.0124 | 10.1694 | 2.3337 | 2.5006 | 4.6687 | 4.0012 | 9.5031 | 7.0125 | 26.1817 | 28.6824 | 38.1855 | 45.1979 | 0.01
1.5673 | 7.0396 | 1.8522 | 1.7784 | 2.2612 | 2.5567 | 5.8918 | 4.1135 | 8.6068 | 10.3852 | 16.277 | 20.3904 | 1.5673 | 7.0396 | 1.8522 | 1.7784 | 2.2612 | 2.5567 | 5.8918 | 4.1235 | 8.6068 | 10.3852 | 16.277 | 20.4004 | 0.01
13.5036 | 9.6258 | 2.2501 | 2.3752 | 4.2506 | 3.7504 | 8.8759 | 6.5007 | 23.1293 | 25.5045 | 34.3804 | 40.8811 | 13.5036 | 9.6258 | 2.2501 | 2.3752 | 4.2506 | 3.7504 | 8.8759 | 6.5107 | 23.1293 | 25.5045 | 34.3804 | 40.8911 | 0.01
0.21402 | 6.7464 | 1.8071 | 1.7107 | 2.0357 | 2.4214 | 5.5535 | 3.8428 | 6.9604 | 8.6711 | 14.2246 | 18.0674 | 0.21402 | 6.7464 | 1.8071 | 1.7107 | 2.0357 | 2.4214 | 5.5535 | 3.8528 | 6.9604 | 8.6711 | 14.2246 | 18.0774 | 0.01
0.14578 | 6.7316 | 1.8049 | 1.7073 | 2.0243 | 2.4146 | 5.5364 | 3.8292 | 6.8774 | 8.5847 | 14.1211 | 17.9503 | 0.14578 | 6.7316 | 1.8049 | 1.7073 | 2.0243 | 2.4146 | 5.5364 | 3.8392 | 6.8774 | 8.5847 | 14.1211 | 17.9603 | 0.01
6.3738 | 8.081 | 2.0125 | 2.0187 | 3.0623 | 3.0374 | 7.0935 | 5.0748 | 14.4548 | 16.4735 | 23.5669 | 28.6417 | 6.3738 | 8.081 | 2.0125 | 2.0187 | 3.0623 | 3.0374 | 7.0935 | 5.0848 | 14.4548 | 16.4735 | 23.5669 | 28.6517 | 0.01
16.4514 | 10.2645 | 2.3484 | 2.5226 | 4.7419 | 4.0451 | 9.6128 | 7.0903 | 26.7158 | 29.2384 | 38.8513 | 45.9415 | 16.4514 | 10.2645 | 2.3484 | 2.5226 | 4.7419 | 4.0451 | 9.6128 | 7.1003 | 26.7158 | 29.2384 | 38.8513 | 45.9515 | 0.01
13.4295 | 9.6097 | 2.2477 | 2.3715 | 4.2383 | 3.743 | 8.8574 | 6.4859 | 23.0392 | 25.4107 | 34.2681 | 40.754 | 13.4295 | 9.6097 | 2.2477 | 2.3715 | 4.2383 | 3.743 | 8.8574 | 6.4959 | 23.0392 | 25.4107 | 34.2681 | 40.764 | 0.01
-7.4375 | 5.0886 | 1.5521 | 1.3281 | 0.76042 | 1.6563 | 3.6406 | 2.3125 | -2.3489 | -1.0208 | 2.6199 | 4.9324 | -7.4375 | 5.0886 | 1.5521 | 1.3281 | 0.76042 | 1.6563 | 3.6406 | 2.3225 | -2.3489 | -1.0208 | 2.6199 | 4.9424 | 0.01
-2.1955 | 6.2243 | 1.7268 | 1.5902 | 1.6341 | 2.1805 | 4.9511 | 3.3609 | 4.0288 | 5.6191 | 10.5702 | 13.9311 | -2.1955 | 6.2243 | 1.7268 | 1.5902 | 1.6341 | 2.1805 | 4.9511 | 3.3709 | 4.0288 | 5.6191 | 10.5702 | 13.9411 | 0.01
-0.86628 | 6.5123 | 1.7711 | 1.6567 | 1.8556 | 2.3134 | 5.2834 | 3.6267 | 5.646 | 7.3027 | 12.5861 | 16.2129 | -0.86628 | 6.5123 | 1.7711 | 1.6567 | 1.8556 | 2.3134 | 5.2834 | 3.6367 | 5.646 | 7.3027 | 12.5861 | 16.2229 | 0.01
7.4517 | 8.3145 | 2.0484 | 2.0726 | 3.2419 | 3.1452 | 7.3629 | 5.2903 | 15.7662 | 17.8388 | 25.2017 | 30.492 | 7.4517 | 8.3145 | 2.0484 | 2.0726 | 3.2419 | 3.1452 | 7.3629 | 5.3003 | 15.7662 | 17.8388 | 25.2017 | 30.502 | 0.01
-4.548 | 5.7146 | 1.6484 | 1.4726 | 1.242 | 1.9452 | 4.363 | 2.8904 | 1.1666 | 2.6392 | 7.0022 | 9.8926 | -4.548 | 5.7146 | 1.6484 | 1.4726 | 1.242 | 1.9452 | 4.363 | 2.9004 | 1.1666 | 2.6392 | 7.0022 | 9.9026 | 0.01
10.1638 | 8.9022 | 2.1388 | 2.2082 | 3.694 | 3.4164 | 8.0409 | 5.8328 | 19.066 | 21.2741 | 29.3151 | 35.1479 | 10.1638 | 8.9022 | 2.1388 | 2.2082 | 3.694 | 3.4164 | 8.0409 | 5.8428 | 19.066 | 21.2741 | 29.3151 | 35.1579 | 0.01
7.2783 | 8.277 | 2.0426 | 2.0639 | 3.213 | 3.1278 | 7.3196 | 5.2557 | 15.5552 | 17.6191 | 24.9387 | 30.1943 | 7.2783 | 8.277 | 2.0426 | 2.0639 | 3.213 | 3.1278 | 7.3196 | 5.2657 | 15.5552 | 17.6191 | 24.9387 | 30.2043 | 0.01
1.4575 | 7.0158 | 1.8486 | 1.7729 | 2.2429 | 2.5457 | 5.8644 | 4.0915 | 8.4732 | 10.2461 | 16.1105 | 20.202 | 1.4575 | 7.0158 | 1.8486 | 1.7729 | 2.2429 | 2.5457 | 5.8644 | 4.1015 | 8.4732 | 10.2461 | 16.1105 | 20.212 | 0.01
-0.57037 | 6.5764 | 1.781 | 1.6715 | 1.9049 | 2.343 | 5.3574 | 3.6859 | 6.0061 | 7.6775 | 13.0349 | 16.7209 | -0.57037 | 6.5764 | 1.781 | 1.6715 | 1.9049 | 2.343 | 5.3574 | 3.6959 | 6.0061 | 7.6775 | 13.0349 | 16.7309 | 0.01
2.3931 | 7.2185 | 1.8798 | 1.8197 | 2.3989 | 2.6393 | 6.0983 | 4.2786 | 9.6116 | 11.4313 | 17.5295 | 21.8082 | 2.3931 | 7.2185 | 1.8798 | 1.8197 | 2.3989 | 2.6393 | 6.0983 | 4.2886 | 9.6116 | 11.4313 | 17.5295 | 21.8182 | 0.01
14.9926 | 9.9484 | 2.2998 | 2.4496 | 4.4988 | 3.8993 | 9.2481 | 6.7985 | 24.941 | 27.3906 | 36.6387 | 43.4372 | 14.9926 | 9.9484 | 2.2998 | 2.4496 | 4.4988 | 3.8993 | 9.2481 | 6.8085 | 24.941 | 27.3906 | 36.6387 | 43.4472 | 0.01
5.5444 | 7.9013 | 1.9848 | 1.9772 | 2.9241 | 2.9544 | 6.8861 | 4.9089 | 13.4457 | 15.423 | 22.3091 | 27.218 | 5.5444 | 7.9013 | 1.9848 | 1.9772 | 2.9241 | 2.9544 | 6.8861 | 4.9189 | 13.4457 | 15.423 | 22.3091 | 27.228 | 0.01
13.6245 | 9.652 | 2.2542 | 2.3812 | 4.2708 | 3.7625 | 8.9061 | 6.5249 | 23.2765 | 25.6577 | 34.5638 | 41.0887 | 13.6245 | 9.652 | 2.2542 | 2.3812 | 4.2708 | 3.7625 | 8.9061 | 6.5349 | 23.2765 | 25.6577 | 34.5638 | 41.0987 | 0.01
1.3803 | 6.9991 | 1.846 | 1.769 | 2.2301 | 2.538 | 5.8451 | 4.0761 | 8.3794 | 10.1484 | 15.9935 | 20.0695 | 1.3803 | 6.9991 | 1.846 | 1.769 | 2.2301 | 2.538 | 5.8451 | 4.0861 | 8.3794 | 10.1484 | 15.9935 | 20.0795 | 0.01
9.4004 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.8501 | 5.6801 | 18.1371 | 20.3071 | 28.1572 | 33.8373 | 9.4004 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.8501 | 5.6901 | 18.1371 | 20.3071 | 28.1572 | 33.8473 | 0.01
5.1169 | 7.8087 | 1.9706 | 1.9558 | 2.8528 | 2.9117 | 6.7792 | 4.8234 | 12.9255 | 14.8813 | 21.6606 | 26.4839 | 5.1169 | 7.8087 | 1.9706 | 1.9558 | 2.8528 | 2.9117 | 6.7792 | 4.8334 | 12.9255 | 14.8813 | 21.6606 | 26.4939 | 0.01
-0.84508 | 6.5169 | 1.7718 | 1.6577 | 1.8592 | 2.3155 | 5.2887 | 3.631 | 5.6718 | 7.3296 | 12.6183 | 16.2493 | -0.84508 | 6.5169 | 1.7718 | 1.6577 | 1.8592 | 2.3155 | 5.2887 | 3.641 | 5.6718 | 7.3296 | 12.6183 | 16.2593 | 0.01
14.9278 | 9.9344 | 2.2976 | 2.4464 | 4.488 | 3.8928 | 9.232 | 6.7856 | 24.8622 | 27.3086 | 36.5405 | 43.3261 | 14.9278 | 9.9344 | 2.2976 | 2.4464 | 4.488 | 3.8928 | 9.232 | 6.7956 | 24.8622 | 27.3086 | 36.5405 | 43.3361 | 0.01
9.9078 | 8.8467 | 2.1303 | 2.1954 | 3.6513 | 3.3908 | 7.977 | 5.7816 | 18.7545 | 20.9499 | 28.9268 | 34.7084 | 9.9078 | 8.8467 | 2.1303 | 2.1954 | 3.6513 | 3.3908 | 7.977 | 5.7916 | 18.7545 | 20.9499 | 28.9268 | 34.7184 | 0.01
5.1469 | 7.8152 | 1.9716 | 1.9573 | 2.8578 | 2.9147 | 6.7867 | 4.8294 | 12.962 | 14.9194 | 21.7061 | 26.5355 | 5.1469 | 7.8152 | 1.9716 | 1.9573 | 2.8578 | 2.9147 | 6.7867 | 4.8394 | 12.962 | 14.9194 | 21.7061 | 26.5455 | 0.01
3.5807 | 7.4758 | 1.9194 | 1.879 | 2.5968 | 2.7581 | 6.3952 | 4.5161 | 11.0565 | 12.9355 | 19.3307 | 23.8468 | 3.5807 | 7.4758 | 1.9194 | 1.879 | 2.5968 | 2.7581 | 6.3952 | 4.5261 | 11.0565 | 12.9355 | 19.3307 | 23.8568 | 0.01
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2043 | 14.1305 | 20.7616 | 25.4664 | 4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7148 | 12.2043 | 14.1305 | 20.7616 | 25.4764 | 0.01
8.6671 | 8.5779 | 2.0889 | 2.1334 | 3.4445 | 3.2667 | 7.6668 | 5.5334 | 17.2449 | 19.3783 | 27.0451 | 32.5785 | 8.6671 | 8.5779 | 2.0889 | 2.1334 | 3.4445 | 3.2667 | 7.6668 | 5.5434 | 17.2449 | 19.3783 | 27.0451 | 32.5885 | 0.01
8.4187 | 8.5241 | 2.0806 | 2.1209 | 3.4031 | 3.2419 | 7.6047 | 5.4837 | 16.9428 | 19.0637 | 26.6684 | 32.1522 | 8.4187 | 8.5241 | 2.0806 | 2.1209 | 3.4031 | 3.2419 | 7.6047 | 5.4937 | 16.9428 | 19.0637 | 26.6684 | 32.1622 | 0.01
-9.9815 | 4.5373 | 1.4673 | 1.2009 | 0.33642 | 1.4019 | 3.0046 | 1.8037 | -5.4442 | -4.2432 | -1.2386 | 0.5651 | -9.9815 | 4.5373 | 1.4673 | 1.2009 | 0.33642 | 1.4019 | 3.0046 | 1.8137 | -5.4442 | -4.2432 | -1.2386 | 0.5751 | 0.01
17.7361 | 10.5428 | 2.3912 | 2.5868 | 4.956 | 4.1736 | 9.934 | 7.3472 | 28.2789 | 30.8657 | 40.7997 | 48.1469 | 17.7361 | 10.5428 | 2.3912 | 2.5868 | 4.956 | 4.1736 | 9.934 | 7.3572 | 28.2789 | 30.8657 | 40.7997 | 48.1569 | 0.01
14.6958 | 9.8841 | 2.2899 | 2.4348 | 4.4493 | 3.8696 | 9.174 | 6.7392 | 24.5799 | 27.0147 | 36.1887 | 42.9279 | 14.6958 | 9.8841 | 2.2899 | 2.4348 | 4.4493 | 3.8696 | 9.174 | 6.7492 | 24.5799 | 27.0147 | 36.1887 | 42.9379 | 0.01
6.9703 | 8.2102 | 2.0323 | 2.0485 | 3.1617 | 3.097 | 7.2426 | 5.1941 | 15.1805 | 17.229 | 24.4716 | 29.6656 | 6.9703 | 8.2102 | 2.0323 | 2.0485 | 3.1617 | 3.097 | 7.2426 | 5.2041 | 15.1805 | 17.229 | 24.4716 | 29.6756 | 0.01
-2.7649 | 6.1009 | 1.7078 | 1.5618 | 1.5392 | 2.1235 | 4.8088 | 3.247 | 3.336 | 4.8978 | 9.7066 | 12.9536 | -2.7649 | 6.1009 | 1.7078 | 1.5618 | 1.5392 | 2.1235 | 4.8088 | 3.257 | 3.336 | 4.8978 | 9.7066 | 12.9636 | 0.01
8.3695 | 8.5134 | 2.079 | 2.1185 | 3.3949 | 3.2369 | 7.5924 | 5.4739 | 16.8829 | 19.0014 | 26.5937 | 32.0676 | 8.3695 | 8.5134 | 2.079 | 2.1185 | 3.3949 | 3.2369 | 7.5924 | 5.4839 | 16.8829 | 19.0014 | 26.5937 | 32.0776 | 0.01
0.31258 | 6.7677 | 1.8104 | 1.7156 | 2.0521 | 2.4313 | 5.5781 | 3.8625 | 7.0803 | 8.7959 | 14.3741 | 18.2366 | 0.31258 | 6.7677 | 1.8104 | 1.7156 | 2.0521 | 2.4313 | 5.5781 | 3.8725 | 7.0803 | 8.7959 | 14.3741 | 18.2466 | 0.01
14.0166 | 9.7369 | 2.2672 | 2.4008 | 4.3361 | 3.8017 | 9.0041 | 6.6033 | 23.7535 | 26.1543 | 35.1584 | 41.7618 | 14.0166 | 9.7369 | 2.2672 | 2.4008 | 4.3361 | 3.8017 | 9.0041 | 6.6133 | 23.7535 | 26.1543 | 35.1584 | 41.7718 | 0.01
7.5685 | 8.3398 | 2.0523 | 2.0784 | 3.2614 | 3.1568 | 7.3921 | 5.3137 | 15.9083 | 17.9867 | 25.3788 | 30.6925 | 7.5685 | 8.3398 | 2.0523 | 2.0784 | 3.2614 | 3.1568 | 7.3921 | 5.3237 | 15.9083 | 17.9867 | 25.3788 | 30.7025 | 0.01
5.9811 | 7.9959 | 1.9994 | 1.9991 | 2.9968 | 2.9981 | 6.9953 | 4.9962 | 13.977 | 15.976 | 22.9713 | 27.9675 | 5.9811 | 7.9959 | 1.9994 | 1.9991 | 2.9968 | 2.9981 | 6.9953 | 5.0062 | 13.977 | 15.976 | 22.9713 | 27.9775 | 0.01
3.3981 | 7.4363 | 1.9133 | 1.8699 | 2.5664 | 2.7398 | 6.3495 | 4.4796 | 10.8344 | 12.7043 | 19.0538 | 23.5335 | 3.3981 | 7.4363 | 1.9133 | 1.8699 | 2.5664 | 2.7398 | 6.3495 | 4.4896 | 10.8344 | 12.7043 | 19.0538 | 23.5435 | 0.01
6.2917 | 8.0632 | 2.0097 | 2.0146 | 3.0486 | 3.0292 | 7.0729 | 5.0583 | 14.3549 | 16.3695 | 23.4424 | 28.5007 | 6.2917 | 8.0632 | 2.0097 | 2.0146 | 3.0486 | 3.0292 | 7.0729 | 5.0683 | 14.3549 | 16.3695 | 23.4424 | 28.5107 | 0.01
3.5617 | 7.4717 | 1.9187 | 1.8781 | 2.5936 | 2.7562 | 6.3904 | 4.5123 | 11.0334 | 12.9115 | 19.3019 | 23.8143 | 3.5617 | 7.4717 | 1.9187 | 1.8781 | 2.5936 | 2.7562 | 6.3904 | 4.5223 | 11.0334 | 12.9115 | 19.3019 | 23.8243 | 0.01
13.4989 | 9.6248 | 2.25 | 2.3749 | 4.2498 | 3.7499 | 8.8747 | 6.4998 | 23.1236 | 25.4986 | 34.3733 | 40.8731 | 13.4989 | 9.6248 | 2.25 | 2.3749 | 4.2498 | 3.7499 | 8.8747 | 6.5098 | 23.1236 | 25.4986 | 34.3733 | 40.8831 | 0.01
10.3918 | 8.9516 | 2.1464 | 2.2196 | 3.732 | 3.4392 | 8.098 | 5.8784 | 19.3434 | 21.563 | 29.6609 | 35.5393 | 10.3918 | 8.9516 | 2.1464 | 2.2196 | 3.732 | 3.4392 | 8.098 | 5.8884 | 19.3434 | 21.563 | 29.6609 | 35.5493 | 0.01
1.0548 | 6.9285 | 1.8352 | 1.7527 | 2.1758 | 2.5055 | 5.7637 | 4.011 | 7.9833 | 9.7361 | 15.4998 | 19.5107 | 1.0548 | 6.9285 | 1.8352 | 1.7527 | 2.1758 | 2.5055 | 5.7637 | 4.021 | 7.9833 | 9.7361 | 15.4998 | 19.5207 | 0.01
16.2026 | 10.2106 | 2.3401 | 2.5101 | 4.7004 | 4.0203 | 9.5506 | 7.0405 | 26.4131 | 28.9233 | 38.4739 | 45.5144 | 16.2026 | 10.2106 | 2.3401 | 2.5101 | 4.7004 | 4.0203 | 9.5506 | 7.0505 | 26.4131 | 28.9233 | 38.4739 | 45.5244 | 0.01
8.5304 | 8.5483 | 2.0843 | 2.1265 | 3.4217 | 3.253 | 7.6326 | 5.5061 | 17.0786 | 19.2052 | 26.8378 | 32.3438 | 8.5304 | 8.5483 | 2.0843 | 2.1265 | 3.4217 | 3.253 | 7.6326 | 5.5161 | 17.0786 | 19.2052 | 26.8378 | 32.3538 | 0.01
7.3385 | 8.29 | 2.0446 | 2.0669 | 3.2231 | 3.1339 | 7.3346 | 5.2677 | 15.6285 | 17.6955 | 25.0301 | 30.2978 | 7.3385 | 8.29 | 2.0446 | 2.0669 | 3.2231 | 3.1339 | 7.3346 | 5.2777 | 15.6285 | 17.6955 | 25.0301 | 30.3078 | 0.01
-11.3977 | 4.2305 | 1.4201 | 1.1301 | 0.10039 | 1.2602 | 2.6506 | 1.5205 | -7.1672 | -6.0371 | -3.3865 | -1.866 | -11.3977 | 4.2305 | 1.4201 | 1.1301 | 0.10039 | 1.2602 | 2.6506 | 1.5305 | -7.1672 | -6.0371 | -3.3865 | -1.856 | 0.01
4.3995 | 7.6532 | 1.9466 | 1.92 | 2.7332 | 2.8399 | 6.5999 | 4.6799 | 12.0527 | 13.9727 | 20.5726 | 25.2525 | 4.3995 | 7.6532 | 1.9466 | 1.92 | 2.7332 | 2.8399 | 6.5999 | 4.6899 | 12.0527 | 13.9727 | 20.5726 | 25.2625 | 0.01
14.4103 | 9.8222 | 2.2803 | 2.4205 | 4.4017 | 3.841 | 9.1026 | 6.6821 | 24.2325 | 26.6531 | 35.7556 | 42.4377 | 14.4103 | 9.8222 | 2.2803 | 2.4205 | 4.4017 | 3.841 | 9.1026 | 6.6921 | 24.2325 | 26.6531 | 35.7556 | 42.4477 | 0.01
-4.8914 | 5.6402 | 1.637 | 1.4554 | 1.1848 | 1.9109 | 4.2771 | 2.8217 | 0.74876 | 2.2042 | 6.4813 | 9.3031 | -4.8914 | 5.6402 | 1.637 | 1.4554 | 1.1848 | 1.9109 | 4.2771 | 2.8317 | 0.74876 | 2.2042 | 6.4813 | 9.3131 | 0.01
15.1442 | 9.9812 | 2.3048 | 2.4572 | 4.524 | 3.9144 | 9.2861 | 6.8288 | 25.1255 | 27.5827 | 36.8687 | 43.6976 | 15.1442 | 9.9812 | 2.3048 | 2.4572 | 4.524 | 3.9144 | 9.2861 | 6.8388 | 25.1255 | 27.5827 | 36.8687 | 43.7076 | 0.01
6.8025 | 8.1739 | 2.0267 | 2.0401 | 3.1337 | 3.0802 | 7.2006 | 5.1605 | 14.9763 | 17.0165 | 24.2171 | 29.3776 | 6.8025 | 8.1739 | 2.0267 | 2.0401 | 3.1337 | 3.0802 | 7.2006 | 5.1705 | 14.9763 | 17.0165 | 24.2171 | 29.3876 | 0.01
7.5565 | 8.3372 | 2.0519 | 2.0778 | 3.2594 | 3.1556 | 7.3891 | 5.3113 | 15.8937 | 17.9716 | 25.3607 | 30.672 | 7.5565 | 8.3372 | 2.0519 | 2.0778 | 3.2594 | 3.1556 | 7.3891 | 5.3213 | 15.8937 | 17.9716 | 25.3607 | 30.682 | 0.01
7.1078 | 8.24 | 2.0369 | 2.0554 | 3.1846 | 3.1108 | 7.2769 | 5.2216 | 15.3478 | 17.4032 | 24.6802 | 29.9017 | 7.1078 | 8.24 | 2.0369 | 2.0554 | 3.1846 | 3.1108 | 7.2769 | 5.2316 | 15.3478 | 17.4032 | 24.6802 | 29.9117 | 0.01
5.4872 | 7.8889 | 1.9829 | 1.9744 | 2.9145 | 2.9487 | 6.8718 | 4.8974 | 13.3761 | 15.3505 | 22.2223 | 27.1197 | 5.4872 | 7.8889 | 1.9829 | 1.9744 | 2.9145 | 2.9487 | 6.8718 | 4.9074 | 13.3761 | 15.3505 | 22.2223 | 27.1297 | 0.01
-0.20801 | 6.6549 | 1.7931 | 1.6896 | 1.9653 | 2.3792 | 5.448 | 3.7584 | 6.4469 | 8.1365 | 13.5845 | 17.3429 | -0.20801 | 6.6549 | 1.7931 | 1.6896 | 1.9653 | 2.3792 | 5.448 | 3.7684 | 6.4469 | 8.1365 | 13.5845 | 17.3529 | 0.01
17.5186 | 10.4957 | 2.384 | 2.5759 | 4.9198 | 4.1519 | 9.8796 | 7.3037 | 28.0143 | 30.5902 | 40.4698 | 47.7735 | 17.5186 | 10.4957 | 2.384 | 2.5759 | 4.9198 | 4.1519 | 9.8796 | 7.3137 | 28.0143 | 30.5902 | 40.4698 | 47.7835 | 0.01
10.1071 | 8.8899 | 2.1369 | 2.2054 | 3.6845 | 3.4107 | 8.0268 | 5.8214 | 18.997 | 21.2024 | 29.2292 | 35.0506 | 10.1071 | 8.8899 | 2.1369 | 2.2054 | 3.6845 | 3.4107 | 8.0268 | 5.8314 | 18.997 | 21.2024 | 29.2292 | 35.0606 | 0.01
8.5568 | 8.554 | 2.0852 | 2.1278 | 3.4261 | 3.2557 | 7.6392 | 5.5114 | 17.1107 | 19.2386 | 26.8777 | 32.3891 | 8.5568 | 8.554 | 2.0852 | 2.1278 | 3.4261 | 3.2557 | 7.6392 | 5.5214 | 17.1107 | 19.2386 | 26.8777 | 32.3991 | 0.01
6.2378 | 8.0515 | 2.0079 | 2.0119 | 3.0396 | 3.0238 | 7.0594 | 5.0476 | 14.2893 | 16.3012 | 23.3606 | 28.4082 | 6.2378 | 8.0515 | 2.0079 | 2.0119 | 3.0396 | 3.0238 | 7.0594 | 5.0576 | 14.2893 | 16.3012 | 23.3606 | 28.4182 | 0.01
-0.17002 | 6.6632 | 1.7943 | 1.6915 | 1.9717 | 2.383 | 5.4575 | 3.766 | 6.4931 | 8.1846 | 13.6421 | 17.4081 | -0.17002 | 6.6632 | 1.7943 | 1.6915 | 1.9717 | 2.383 | 5.4575 | 3.776 | 6.4931 | 8.1846 | 13.6421 | 17.4181 | 0.01
14.1065 | 9.7564 | 2.2702 | 2.4053 | 4.3511 | 3.8106 | 9.0266 | 6.6213 | 23.8629 | 26.2682 | 35.2948 | 41.9161 | 14.1065 | 9.7564 | 2.2702 | 2.4053 | 4.3511 | 3.8106 | 9.0266 | 6.6313 | 23.8629 | 26.2682 | 35.2948 | 41.9261 | 0.01
3.8564 | 7.5356 | 1.9285 | 1.8928 | 2.6427 | 2.7856 | 6.4641 | 4.5713 | 11.392 | 13.2848 | 19.7489 | 24.3202 | 3.8564 | 7.5356 | 1.9285 | 1.8928 | 2.6427 | 2.7856 | 6.4641 | 4.5813 | 11.392 | 13.2848 | 19.7489 | 24.3302 | 0.01
-3.938 | 5.8468 | 1.6687 | 1.5031 | 1.3437 | 2.0062 | 4.5155 | 3.0124 | 1.9088 | 3.4119 | 7.9273 | 10.9397 | -3.938 | 5.8468 | 1.6687 | 1.5031 | 1.3437 | 2.0062 | 4.5155 | 3.0224 | 1.9088 | 3.4119 | 7.9273 | 10.9497 | 0.01
8.0713 | 8.4488 | 2.069 | 2.1036 | 3.3452 | 3.2071 | 7.5178 | 5.4143 | 16.5201 | 18.6237 | 26.1415 | 31.5558 | 8.0713 | 8.4488 | 2.069 | 2.1036 | 3.3452 | 3.2071 | 7.5178 | 5.4243 | 16.5201 | 18.6237 | 26.1415 | 31.5658 | 0.01
-3.3537 | 5.9734 | 1.6882 | 1.5323 | 1.4411 | 2.0646 | 4.6616 | 3.1293 | 2.6197 | 4.152 | 8.8136 | 11.9428 | -3.3537 | 5.9734 | 1.6882 | 1.5323 | 1.4411 | 2.0646 | 4.6616 | 3.1393 | 2.6197 | 4.152 | 8.8136 | 11.9528 | 0.01
-2.1228 | 6.2401 | 1.7292 | 1.5939 | 1.6462 | 2.1877 | 4.9693 | 3.3754 | 4.1173 | 5.7111 | 10.6804 | 14.0558 | -2.1228 | 6.2401 | 1.7292 | 1.5939 | 1.6462 | 2.1877 | 4.9693 | 3.3854 | 4.1173 | 5.7111 | 10.6804 | 14.0658 | 0.01
3.4464 | 7.4467 | 1.9149 | 1.8723 | 2.5744 | 2.7446 | 6.3616 | 4.4893 | 10.8932 | 12.7655 | 19.1271 | 23.6164 | 3.4464 | 7.4467 | 1.9149 | 1.8723 | 2.5744 | 2.7446 | 6.3616 | 4.4993 | 10.8932 | 12.7655 | 19.1271 | 23.6264 | 0.01
9.7406 | 8.8105 | 2.1247 | 2.187 | 3.6234 | 3.3741 | 7.9351 | 5.7481 | 18.551 | 20.7381 | 28.6732 | 34.4213 | 9.7406 | 8.8105 | 2.1247 | 2.187 | 3.6234 | 3.3741 | 7.9351 | 5.7581 | 18.551 | 20.7381 | 28.6732 | 34.4313 | 0.01
14.3409 | 9.8072 | 2.278 | 2.417 | 4.3902 | 3.8341 | 9.0852 | 6.6682 | 24.1481 | 26.5652 | 35.6504 | 42.3186 | 14.3409 | 9.8072 | 2.278 | 2.417 | 4.3902 | 3.8341 | 9.0852 | 6.6782 | 24.1481 | 26.5652 | 35.6504 | 42.3286 | 0.01
10.4801 | 8.9707 | 2.1493 | 2.224 | 3.7467 | 3.448 | 8.12 | 5.896 | 19.4508 | 21.6748 | 29.7948 | 35.6908 | 10.4801 | 8.9707 | 2.1493 | 2.224 | 3.7467 | 3.448 | 8.12 | 5.906 | 19.4508 | 21.6748 | 29.7948 | 35.7008 | 0.01
1.9422 | 7.1208 | 1.8647 | 1.7971 | 2.3237 | 2.5942 | 5.9855 | 4.1884 | 9.063 | 10.8601 | 16.8456 | 21.0341 | 1.9422 | 7.1208 | 1.8647 | 1.7971 | 2.3237 | 2.5942 | 5.9855 | 4.1984 | 9.063 | 10.8601 | 16.8456 | 21.0441 | 0.01
-3.5251 | 5.9362 | 1.6825 | 1.5237 | 1.4125 | 2.0475 | 4.6187 | 3.095 | 2.4111 | 3.9349 | 8.5536 | 11.6486 | -3.5251 | 5.9362 | 1.6825 | 1.5237 | 1.4125 | 2.0475 | 4.6187 | 3.105 | 2.4111 | 3.9349 | 8.5536 | 11.6586 | 0.01
6.3941 | 8.0854 | 2.0131 | 2.0197 | 3.0657 | 3.0394 | 7.0985 | 5.0788 | 14.4795 | 16.4992 | 23.5978 | 28.6766 | 6.3941 | 8.0854 | 2.0131 | 2.0197 | 3.0657 | 3.0394 | 7.0985 | 5.0888 | 14.4795 | 16.4992 | 23.5978 | 28.6866 | 0.01
8.1827 | 8.4729 | 2.0728 | 2.1091 | 3.3638 | 3.2183 | 7.5457 | 5.4365 | 16.6556 | 18.7647 | 26.3104 | 31.7469 | 8.1827 | 8.4729 | 2.0728 | 2.1091 | 3.3638 | 3.2183 | 7.5457 | 5.4465 | 16.6556 | 18.7647 | 26.3104 | 31.7569 | 0.01
13.4254 | 9.6088 | 2.2475 | 2.3713 | 4.2376 | 3.7425 | 8.8563 | 6.4851 | 23.0342 | 25.4055 | 34.2618 | 40.7469 | 13.4254 | 9.6088 | 2.2475 | 2.3713 | 4.2376 | 3.7425 | 8.8563 | 6.4951 | 23.0342 | 25.4055 | 34.2618 | 40.7569 | 0.01
12.781 | 9.4692 | 2.226 | 2.339 | 4.1302 | 3.6781 | 8.6952 | 6.3562 | 22.2502 | 24.5892 | 33.2844 | 39.6406 | 12.781 | 9.4692 | 2.226 | 2.339 | 4.1302 | 3.6781 | 8.6952 | 6.3662 | 22.2502 | 24.5892 | 33.2844 | 39.6506 | 0.01
5.32 | 7.8527 | 1.9773 | 1.966 | 2.8867 | 2.932 | 6.83 | 4.864 | 13.1726 | 15.1386 | 21.9686 | 26.8326 | 5.32 | 7.8527 | 1.9773 | 1.966 | 2.8867 | 2.932 | 6.83 | 4.874 | 13.1726 | 15.1386 | 21.9686 | 26.8426 | 0.01
0.36357 | 6.7788 | 1.8121 | 1.7182 | 2.0606 | 2.4364 | 5.5909 | 3.8727 | 7.1423 | 8.8605 | 14.4514 | 18.3241 | 0.36357 | 6.7788 | 1.8121 | 1.7182 | 2.0606 | 2.4364 | 5.5909 | 3.8827 | 7.1423 | 8.8605 | 14.4514 | 18.3341 | 0.01
4.4875 | 7.6723 | 1.9496 | 1.9244 | 2.7479 | 2.8487 | 6.6219 | 4.6975 | 12.1597 | 14.0841 | 20.706 | 25.4035 | 4.4875 | 7.6723 | 1.9496 | 1.9244 | 2.7479 | 2.8487 | 6.6219 | 4.7075 | 12.1597 | 14.0841 | 20.706 | 25.4135 | 0.01
16.3134 | 10.2346 | 2.3438 | 2.5157 | 4.7189 | 4.0313 | 9.5783 | 7.0627 | 26.548 | 29.0636 | 38.642 | 45.7047 | 16.3134 | 10.2346 | 2.3438 | 2.5157 | 4.7189 | 4.0313 | 9.5783 | 7.0727 | 26.548 | 29.0636 | 38.642 | 45.7147 | 0.01
4.2492 | 7.6207 | 1.9416 | 1.9125 | 2.7082 | 2.8249 | 6.5623 | 4.6498 | 11.8698 | 13.7823 | 20.3446 | 24.9944 | 4.2492 | 7.6207 | 1.9416 | 1.9125 | 2.7082 | 2.8249 | 6.5623 | 4.6598 | 11.8698 | 13.7823 | 20.3446 | 25.0044 | 0.01
3.7637 | 7.5155 | 1.9255 | 1.8882 | 2.6273 | 2.7764 | 6.4409 | 4.5527 | 11.2792 | 13.1674 | 19.6083 | 24.161 | 3.7637 | 7.5155 | 1.9255 | 1.8882 | 2.6273 | 2.7764 | 6.4409 | 4.5627 | 11.2792 | 13.1674 | 19.6083 | 24.171 | 0.01
-1.4859 | 6.3781 | 1.7505 | 1.6257 | 1.7524 | 2.2514 | 5.1285 | 3.5028 | 4.8922 | 6.5179 | 11.6464 | 15.1492 | -1.4859 | 6.3781 | 1.7505 | 1.6257 | 1.7524 | 2.2514 | 5.1285 | 3.5128 | 4.8922 | 6.5179 | 11.6464 | 15.1592 | 0.01
13.1201 | 9.5427 | 2.2373 | 2.356 | 4.1867 | 3.712 | 8.78 | 6.424 | 22.6628 | 25.0188 | 33.7988 | 40.2228 | 13.1201 | 9.5427 | 2.2373 | 2.356 | 4.1867 | 3.712 | 8.78 | 6.434 | 22.6628 | 25.0188 | 33.7988 | 40.2328 | 0.01
1.2847 | 6.9783 | 1.8428 | 1.7642 | 2.2141 | 2.5285 | 5.8212 | 4.0569 | 8.263 | 10.0273 | 15.8484 | 19.9054 | 1.2847 | 6.9783 | 1.8428 | 1.7642 | 2.2141 | 2.5285 | 5.8212 | 4.0669 | 8.263 | 10.0273 | 15.8484 | 19.9154 | 0.01
10.1324 | 8.8954 | 2.1377 | 2.2066 | 3.6887 | 3.4132 | 8.0331 | 5.8265 | 19.0278 | 21.2344 | 29.2675 | 35.094 | 10.1324 | 8.8954 | 2.1377 | 2.2066 | 3.6887 | 3.4132 | 8.0331 | 5.8365 | 19.0278 | 21.2344 | 29.2675 | 35.104 | 0.01
19.078 | 10.8336 | 2.4359 | 2.6539 | 5.1797 | 4.3078 | 10.2695 | 7.6156 | 29.9115 | 32.5654 | 42.8349 | 50.4505 | 19.078 | 10.8336 | 2.4359 | 2.6539 | 5.1797 | 4.3078 | 10.2695 | 7.6256 | 29.9115 | 32.5654 | 42.8349 | 50.4605 | 0.01
14.4903 | 9.8396 | 2.283 | 2.4245 | 4.4151 | 3.849 | 9.1226 | 6.6981 | 24.3299 | 26.7544 | 35.877 | 42.5751 | 14.4903 | 9.8396 | 2.283 | 2.4245 | 4.4151 | 3.849 | 9.1226 | 6.7081 | 24.3299 | 26.7544 | 35.877 | 42.5851 | 0.01
1.3037 | 6.9825 | 1.8435 | 1.7652 | 2.2173 | 2.5304 | 5.8259 | 4.0607 | 8.2862 | 10.0514 | 15.8773 | 19.9381 | 1.3037 | 6.9825 | 1.8435 | 1.7652 | 2.2173 | 2.5304 | 5.8259 | 4.0707 | 8.2862 | 10.0514 | 15.8773 | 19.9481 | 0.01
4.5343 | 7.6824 | 1.9511 | 1.9267 | 2.7557 | 2.8534 | 6.6336 | 4.7069 | 12.2167 | 14.1434 | 20.777 | 25.4838 | 4.5343 | 7.6824 | 1.9511 | 1.9267 | 2.7557 | 2.8534 | 6.6336 | 4.7169 | 12.2167 | 14.1434 | 20.777 | 25.4938 | 0.01
8.9171 | 8.632 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5834 | 17.5492 | 19.695 | 27.4243 | 33.0077 | 8.9171 | 8.632 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5934 | 17.5492 | 19.695 | 27.4243 | 33.0177 | 0.01
4.2696 | 7.6251 | 1.9423 | 1.9135 | 2.7116 | 2.827 | 6.5674 | 4.6539 | 11.8947 | 13.8082 | 20.3756 | 25.0295 | 4.2696 | 7.6251 | 1.9423 | 1.9135 | 2.7116 | 2.827 | 6.5674 | 4.6639 | 11.8947 | 13.8082 | 20.3756 | 25.0395 | 0.01
1.8769 | 7.1067 | 1.8626 | 1.7938 | 2.3128 | 2.5877 | 5.9692 | 4.1754 | 8.9835 | 10.7774 | 16.7466 | 20.922 | 1.8769 | 7.1067 | 1.8626 | 1.7938 | 2.3128 | 2.5877 | 5.9692 | 4.1854 | 8.9835 | 10.7774 | 16.7466 | 20.932 | 0.01
1.2769 | 6.9767 | 1.8426 | 1.7638 | 2.2128 | 2.5277 | 5.8192 | 4.0554 | 8.2536 | 10.0174 | 15.8367 | 19.8921 | 1.2769 | 6.9767 | 1.8426 | 1.7638 | 2.2128 | 2.5277 | 5.8192 | 4.0654 | 8.2536 | 10.0174 | 15.8367 | 19.9021 | 0.01
4.4293 | 7.6597 | 1.9476 | 1.9215 | 2.7382 | 2.8429 | 6.6073 | 4.6859 | 12.089 | 14.0105 | 20.6178 | 25.3037 | 4.4293 | 7.6597 | 1.9476 | 1.9215 | 2.7382 | 2.8429 | 6.6073 | 4.6959 | 12.089 | 14.0105 | 20.6178 | 25.3137 | 0.01
-0.71252 | 6.5456 | 1.7762 | 1.6644 | 1.8812 | 2.3287 | 5.3219 | 3.6575 | 5.8331 | 7.4975 | 12.8193 | 16.4768 | -0.71252 | 6.5456 | 1.7762 | 1.6644 | 1.8812 | 2.3287 | 5.3219 | 3.6675 | 5.8331 | 7.4975 | 12.8193 | 16.4868 | 0.01
0.56209 | 6.8218 | 1.8187 | 1.7281 | 2.0937 | 2.4562 | 5.6405 | 3.9124 | 7.3839 | 9.112 | 14.7525 | 18.6649 | 0.56209 | 6.8218 | 1.8187 | 1.7281 | 2.0937 | 2.4562 | 5.6405 | 3.9224 | 7.3839 | 9.112 | 14.7525 | 18.6749 | 0.01
3.2537 | 7.405 | 1.9085 | 1.8627 | 2.5423 | 2.7254 | 6.3134 | 4.4507 | 10.6587 | 12.5214 | 18.8348 | 23.2856 | 3.2537 | 7.405 | 1.9085 | 1.8627 | 2.5423 | 2.7254 | 6.3134 | 4.4607 | 10.6587 | 12.5214 | 18.8348 | 23.2956 | 0.01
4.564 | 7.6889 | 1.9521 | 1.9282 | 2.7607 | 2.8564 | 6.641 | 4.7128 | 12.2529 | 14.1811 | 20.8221 | 25.5349 | 4.564 | 7.6889 | 1.9521 | 1.9282 | 2.7607 | 2.8564 | 6.641 | 4.7228 | 12.2529 | 14.1811 | 20.8221 | 25.5449 | 0.01
17.5236 | 10.4968 | 2.3841 | 2.5762 | 4.9206 | 4.1524 | 9.8809 | 7.3047 | 28.0204 | 30.5966 | 40.4775 | 47.7823 | 17.5236 | 10.4968 | 2.3841 | 2.5762 | 4.9206 | 4.1524 | 9.8809 | 7.3147 | 28.0204 | 30.5966 | 40.4775 | 47.7923 | 0.01
8.2391 | 8.4851 | 2.0746 | 2.112 | 3.3732 | 3.2239 | 7.5598 | 5.4478 | 16.7242 | 18.8362 | 26.396 | 31.8438 | 8.2391 | 8.4851 | 2.0746 | 2.112 | 3.3732 | 3.2239 | 7.5598 | 5.4578 | 16.7242 | 18.8362 | 26.396 | 31.8538 | 0.01
11.3647 | 9.1623 | 2.1788 | 2.2682 | 3.8941 | 3.5365 | 8.3412 | 6.0729 | 20.527 | 22.7953 | 31.1364 | 37.2094 | 11.3647 | 9.1623 | 2.1788 | 2.2682 | 3.8941 | 3.5365 | 8.3412 | 6.0829 | 20.527 | 22.7953 | 31.1364 | 37.2194 | 0.01
-1.6549 | 6.3414 | 1.7448 | 1.6173 | 1.7242 | 2.2345 | 5.0863 | 3.469 | 4.6866 | 6.3038 | 11.3901 | 14.8591 | -1.6549 | 6.3414 | 1.7448 | 1.6173 | 1.7242 | 2.2345 | 5.0863 | 3.479 | 4.6866 | 6.3038 | 11.3901 | 14.8691 | 0.01
8.9418 | 8.6374 | 2.0981 | 2.1471 | 3.4903 | 3.2942 | 7.7354 | 5.5884 | 17.5791 | 19.7262 | 27.4617 | 33.05 | 8.9418 | 8.6374 | 2.0981 | 2.1471 | 3.4903 | 3.2942 | 7.7354 | 5.5984 | 17.5791 | 19.7262 | 27.4617 | 33.06 | 0.01
11.8561 | 9.2688 | 2.1952 | 2.2928 | 3.976 | 3.5856 | 8.464 | 6.1712 | 21.1249 | 23.4177 | 31.8817 | 38.053 | 11.8561 | 9.2688 | 2.1952 | 2.2928 | 3.976 | 3.5856 | 8.464 | 6.1812 | 21.1249 | 23.4177 | 31.8817 | 38.063 | 0.01
10.4949 | 8.9739 | 2.1498 | 2.2247 | 3.7492 | 3.4495 | 8.1237 | 5.899 | 19.4688 | 21.6936 | 29.8173 | 35.7163 | 10.4949 | 8.9739 | 2.1498 | 2.2247 | 3.7492 | 3.4495 | 8.1237 | 5.909 | 19.4688 | 21.6936 | 29.8173 | 35.7263 | 0.01
10.916 | 9.0651 | 2.1639 | 2.2458 | 3.8193 | 3.4916 | 8.229 | 5.9832 | 19.9811 | 22.2269 | 30.4559 | 36.4391 | 10.916 | 9.0651 | 2.1639 | 2.2458 | 3.8193 | 3.4916 | 8.229 | 5.9932 | 19.9811 | 22.2269 | 30.4559 | 36.4491 | 0.01
9.4413 | 8.7456 | 2.1147 | 2.1721 | 3.5736 | 3.3441 | 7.8603 | 5.6883 | 18.1869 | 20.359 | 28.2193 | 33.9076 | 9.4413 | 8.7456 | 2.1147 | 2.1721 | 3.5736 | 3.3441 | 7.8603 | 5.6983 | 18.1869 | 20.359 | 28.2193 | 33.9176 | 0.01
3.8479 | 7.5337 | 1.9283 | 1.8924 | 2.6413 | 2.7848 | 6.462 | 4.5696 | 11.3817 | 13.2741 | 19.7361 | 24.3056 | 3.8479 | 7.5337 | 1.9283 | 1.8924 | 2.6413 | 2.7848 | 6.462 | 4.5796 | 11.3817 | 13.2741 | 19.7361 | 24.3156 | 0.01
0.12473 | 6.727 | 1.8042 | 1.7062 | 2.0208 | 2.4125 | 5.5312 | 3.8249 | 6.8518 | 8.558 | 14.0892 | 17.9141 | 0.12473 | 6.727 | 1.8042 | 1.7062 | 2.0208 | 2.4125 | 5.5312 | 3.8349 | 6.8518 | 8.558 | 14.0892 | 17.9241 | 0.01
15.3826 | 10.0329 | 2.3128 | 2.4691 | 4.5638 | 3.9383 | 9.3457 | 6.8765 | 25.4155 | 27.8847 | 37.2303 | 44.1068 | 15.3826 | 10.0329 | 2.3128 | 2.4691 | 4.5638 | 3.9383 | 9.3457 | 6.8865 | 25.4155 | 27.8847 | 37.2303 | 44.1168 | 0.01
5.5747 | 7.9078 | 1.9858 | 1.9787 | 2.9291 | 2.9575 | 6.8937 | 4.9149 | 13.4825 | 15.4613 | 22.3549 | 27.2699 | 5.5747 | 7.9078 | 1.9858 | 1.9787 | 2.9291 | 2.9575 | 6.8937 | 4.9249 | 13.4825 | 15.4613 | 22.3549 | 27.2799 | 0.01
7.5314 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8632 | 17.9398 | 25.3227 | 30.629 | 7.5314 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3163 | 15.8632 | 17.9398 | 25.3227 | 30.639 | 0.01
5.6536 | 7.9249 | 1.9885 | 1.9827 | 2.9423 | 2.9654 | 6.9134 | 4.9307 | 13.5786 | 15.5612 | 22.4746 | 27.4054 | 5.6536 | 7.9249 | 1.9885 | 1.9827 | 2.9423 | 2.9654 | 6.9134 | 4.9407 | 13.5786 | 15.5612 | 22.4746 | 27.4154 | 0.01
7.9005 | 8.4118 | 2.0633 | 2.095 | 3.3167 | 3.19 | 7.4751 | 5.3801 | 16.3122 | 18.4073 | 25.8824 | 31.2625 | 7.9005 | 8.4118 | 2.0633 | 2.095 | 3.3167 | 3.19 | 7.4751 | 5.3901 | 16.3122 | 18.4073 | 25.8824 | 31.2725 | 0.01
2.7503 | 7.2959 | 1.8917 | 1.8375 | 2.4584 | 2.675 | 6.1876 | 4.3501 | 10.0462 | 11.8837 | 18.0713 | 22.4213 | 2.7503 | 7.2959 | 1.8917 | 1.8375 | 2.4584 | 2.675 | 6.1876 | 4.3601 | 10.0462 | 11.8837 | 18.0713 | 22.4313 | 0.01
15.9912 | 10.1648 | 2.333 | 2.4996 | 4.6652 | 3.9991 | 9.4978 | 6.9982 | 26.156 | 28.6556 | 38.1534 | 45.1516 | 15.9912 | 10.1648 | 2.333 | 2.4996 | 4.6652 | 3.9991 | 9.4978 | 7.0082 | 26.156 | 28.6556 | 38.1534 | 45.1616 | 0.01
3.5741 | 7.4744 | 1.9191 | 1.8787 | 2.5957 | 2.7574 | 6.3935 | 4.5148 | 11.0485 | 12.9272 | 19.3207 | 23.8356 | 3.5741 | 7.4744 | 1.9191 | 1.8787 | 2.5957 | 2.7574 | 6.3935 | 4.5248 | 11.0485 | 12.9272 | 19.3207 | 23.8456 | 0.01
8.2161 | 8.4802 | 2.0739 | 2.1108 | 3.3693 | 3.2216 | 7.554 | 5.4432 | 16.6962 | 18.8071 | 26.3611 | 31.8043 | 8.2161 | 8.4802 | 2.0739 | 2.1108 | 3.3693 | 3.2216 | 7.554 | 5.4532 | 16.6962 | 18.8071 | 26.3611 | 31.8143 | 0.01
11.5303 | 9.1982 | 2.1843 | 2.2765 | 3.9217 | 3.553 | 8.3826 | 6.1061 | 20.7286 | 23.0051 | 31.3877 | 37.4937 | 11.5303 | 9.1982 | 2.1843 | 2.2765 | 3.9217 | 3.553 | 8.3826 | 6.1161 | 20.7286 | 23.0051 | 31.3877 | 37.5037 | 0.01
9.1597 | 8.6846 | 2.1053 | 2.158 | 3.5266 | 3.316 | 7.7899 | 5.6319 | 17.8443 | 20.0023 | 27.7923 | 33.4242 | 9.1597 | 8.6846 | 2.1053 | 2.158 | 3.5266 | 3.316 | 7.7899 | 5.6419 | 17.8443 | 20.0023 | 27.7923 | 33.4342 | 0.01
12.984 | 9.5132 | 2.2328 | 2.3492 | 4.164 | 3.6984 | 8.746 | 6.3968 | 22.4972 | 24.8464 | 33.5924 | 39.9892 | 12.984 | 9.5132 | 2.2328 | 2.3492 | 4.164 | 3.6984 | 8.746 | 6.4068 | 22.4972 | 24.8464 | 33.5924 | 39.9992 | 0.01
18.7844 | 10.7699 | 2.4261 | 2.6392 | 5.1307 | 4.2784 | 10.1961 | 7.5569 | 29.5543 | 32.1935 | 42.3896 | 49.9465 | 18.7844 | 10.7699 | 2.4261 | 2.6392 | 5.1307 | 4.2784 | 10.1961 | 7.5669 | 29.5543 | 32.1935 | 42.3896 | 49.9565 | 0.01
9.9286 | 8.8512 | 2.131 | 2.1964 | 3.6548 | 3.3929 | 7.9822 | 5.7857 | 18.7799 | 20.9763 | 28.9585 | 34.7442 | 9.9286 | 8.8512 | 2.131 | 2.1964 | 3.6548 | 3.3929 | 7.9822 | 5.7957 | 18.7799 | 20.9763 | 28.9585 | 34.7542 | 0.01
2.0856 | 7.1519 | 1.8695 | 1.8043 | 2.3476 | 2.6086 | 6.0214 | 4.2171 | 9.2375 | 11.0418 | 17.0632 | 21.2803 | 2.0856 | 7.1519 | 1.8695 | 1.8043 | 2.3476 | 2.6086 | 6.0214 | 4.2271 | 9.2375 | 11.0418 | 17.0632 | 21.2903 | 0.01
7.7123 | 8.371 | 2.0571 | 2.0856 | 3.2854 | 3.1712 | 7.4281 | 5.3425 | 16.0833 | 18.169 | 25.5971 | 30.9395 | 7.7123 | 8.371 | 2.0571 | 2.0856 | 3.2854 | 3.1712 | 7.4281 | 5.3525 | 16.0833 | 18.169 | 25.5971 | 30.9495 | 0.01
4.3418 | 7.6407 | 1.9447 | 1.9171 | 2.7236 | 2.8342 | 6.5855 | 4.6684 | 11.9825 | 13.8996 | 20.4851 | 25.1535 | 4.3418 | 7.6407 | 1.9447 | 1.9171 | 2.7236 | 2.8342 | 6.5855 | 4.6784 | 11.9825 | 13.8996 | 20.4851 | 25.1635 | 0.01
11.026 | 9.089 | 2.1675 | 2.2513 | 3.8377 | 3.5026 | 8.2565 | 6.0052 | 20.115 | 22.3663 | 30.6228 | 36.628 | 11.026 | 9.089 | 2.1675 | 2.2513 | 3.8377 | 3.5026 | 8.2565 | 6.0152 | 20.115 | 22.3663 | 30.6228 | 36.638 | 0.01
17.0012 | 10.3836 | 2.3667 | 2.5501 | 4.8335 | 4.1001 | 9.7503 | 7.2002 | 27.3849 | 29.9349 | 39.6852 | 46.8855 | 17.0012 | 10.3836 | 2.3667 | 2.5501 | 4.8335 | 4.1001 | 9.7503 | 7.2102 | 27.3849 | 29.9349 | 39.6852 | 46.8955 | 0.01
2.8353 | 7.3143 | 1.8945 | 1.8418 | 2.4726 | 2.6835 | 6.2088 | 4.3671 | 10.1496 | 11.9914 | 18.2002 | 22.5673 | 2.8353 | 7.3143 | 1.8945 | 1.8418 | 2.4726 | 2.6835 | 6.2088 | 4.3771 | 10.1496 | 11.9914 | 18.2002 | 22.5773 | 0.01
2.9314 | 7.3351 | 1.8977 | 1.8466 | 2.4886 | 2.6931 | 6.2329 | 4.3863 | 10.2666 | 12.1132 | 18.346 | 22.7323 | 2.9314 | 7.3351 | 1.8977 | 1.8466 | 2.4886 | 2.6931 | 6.2329 | 4.3963 | 10.2666 | 12.1132 | 18.346 | 22.7423 | 0.01
0.2458 | 6.7533 | 1.8082 | 1.7123 | 2.041 | 2.4246 | 5.5615 | 3.8492 | 6.9991 | 8.7114 | 14.2728 | 18.122 | 0.2458 | 6.7533 | 1.8082 | 1.7123 | 2.041 | 2.4246 | 5.5615 | 3.8592 | 6.9991 | 8.7114 | 14.2728 | 18.132 | 0.01
6.4896 | 8.1061 | 2.0163 | 2.0245 | 3.0816 | 3.049 | 7.1224 | 5.0979 | 14.5957 | 16.6202 | 23.7426 | 28.8405 | 6.4896 | 8.1061 | 2.0163 | 2.0245 | 3.0816 | 3.049 | 7.1224 | 5.1079 | 14.5957 | 16.6202 | 23.7426 | 28.8505 | 0.01
-6.0201 | 5.3956 | 1.5993 | 1.399 | 0.99665 | 1.798 | 3.995 | 2.596 | -0.62448 | 0.77452 | 4.7695 | 7.3655 | -6.0201 | 5.3956 | 1.5993 | 1.399 | 0.99665 | 1.798 | 3.995 | 2.606 | -0.62448 | 0.77452 | 4.7695 | 7.3755 | 0.01
3.3036 | 7.4158 | 1.9101 | 1.8652 | 2.5506 | 2.7304 | 6.3259 | 4.4607 | 10.7194 | 12.5846 | 18.9105 | 23.3712 | 3.3036 | 7.4158 | 1.9101 | 1.8652 | 2.5506 | 2.7304 | 6.3259 | 4.4707 | 10.7194 | 12.5846 | 18.9105 | 23.3812 | 0.01
8.8664 | 8.621 | 2.0955 | 2.1433 | 3.4777 | 3.2866 | 7.7166 | 5.5733 | 17.4874 | 19.6307 | 27.3473 | 32.9206 | 8.8664 | 8.621 | 2.0955 | 2.1433 | 3.4777 | 3.2866 | 7.7166 | 5.5833 | 17.4874 | 19.6307 | 27.3473 | 32.9306 | 0.01
13.6777 | 9.6635 | 2.2559 | 2.3839 | 4.2796 | 3.7678 | 8.9194 | 6.5355 | 23.3412 | 25.7251 | 34.6446 | 41.1801 | 13.6777 | 9.6635 | 2.2559 | 2.3839 | 4.2796 | 3.7678 | 8.9194 | 6.5455 | 23.3412 | 25.7251 | 34.6446 | 41.1901 | 0.01
7.5315 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3063 | 15.8633 | 17.9399 | 25.3228 | 30.629 | 7.5315 | 8.3318 | 2.051 | 2.0766 | 3.2552 | 3.1531 | 7.3829 | 5.3163 | 15.8633 | 17.9399 | 25.3228 | 30.639 | 0.01
6.5002 | 8.1084 | 2.0167 | 2.025 | 3.0834 | 3.05 | 7.1251 | 5.1 | 14.6086 | 16.6336 | 23.7587 | 28.8587 | 6.5002 | 8.1084 | 2.0167 | 2.025 | 3.0834 | 3.05 | 7.1251 | 5.11 | 14.6086 | 16.6336 | 23.7587 | 28.8687 | 0.01
12.3442 | 9.3746 | 2.2115 | 2.3172 | 4.0574 | 3.6344 | 8.586 | 6.2688 | 21.7187 | 24.036 | 32.622 | 38.8908 | 12.3442 | 9.3746 | 2.2115 | 2.3172 | 4.0574 | 3.6344 | 8.586 | 6.2788 | 21.7187 | 24.036 | 32.622 | 38.9008 | 0.01
-2.6847 | 6.1183 | 1.7105 | 1.5658 | 1.5526 | 2.1315 | 4.8288 | 3.2631 | 3.4337 | 4.9994 | 9.8283 | 13.0913 | -2.6847 | 6.1183 | 1.7105 | 1.5658 | 1.5526 | 2.1315 | 4.8288 | 3.2731 | 3.4337 | 4.9994 | 9.8283 | 13.1013 | 0.01
11.3098 | 9.1505 | 2.177 | 2.2655 | 3.885 | 3.531 | 8.3274 | 6.062 | 20.4602 | 22.7257 | 31.0532 | 37.1151 | 11.3098 | 9.1505 | 2.177 | 2.2655 | 3.885 | 3.531 | 8.3274 | 6.072 | 20.4602 | 22.7257 | 31.0532 | 37.1251 | 0.01
11.2312 | 9.1334 | 2.1744 | 2.2616 | 3.8719 | 3.5231 | 8.3078 | 6.0462 | 20.3646 | 22.6262 | 30.934 | 36.9802 | 11.2312 | 9.1334 | 2.1744 | 2.2616 | 3.8719 | 3.5231 | 8.3078 | 6.0562 | 20.3646 | 22.6262 | 30.934 | 36.9902 | 0.01
-2.2417 | 6.2143 | 1.7253 | 1.5879 | 1.6264 | 2.1758 | 4.9396 | 3.3517 | 3.9725 | 5.5605 | 10.5 | 13.8517 | -2.2417 | 6.2143 | 1.7253 | 1.5879 | 1.6264 | 2.1758 | 4.9396 | 3.3617 | 3.9725 | 5.5605 | 10.5 | 13.8617 | 0.01
13.1798 | 9.5556 | 2.2393 | 2.359 | 4.1966 | 3.718 | 8.795 | 6.436 | 22.7354 | 25.0944 | 33.8894 | 40.3253 | 13.1798 | 9.5556 | 2.2393 | 2.359 | 4.1966 | 3.718 | 8.795 | 6.446 | 22.7354 | 25.0944 | 33.8894 | 40.3353 | 0.01
-6.0136 | 5.397 | 1.5995 | 1.3993 | 0.99773 | 1.7986 | 3.9966 | 2.5973 | -0.61658 | 0.78274 | 4.7793 | 7.3766 | -6.0136 | 5.397 | 1.5995 | 1.3993 | 0.99773 | 1.7986 | 3.9966 | 2.6073 | -0.61658 | 0.78274 | 4.7793 | 7.3866 | 0.01
2.8839 | 7.3249 | 1.8961 | 1.8442 | 2.4807 | 2.6884 | 6.221 | 4.3768 | 10.2088 | 12.053 | 18.274 | 22.6508 | 2.8839 | 7.3249 | 1.8961 | 1.8442 | 2.4807 | 2.6884 | 6.221 | 4.3868 | 10.2088 | 12.053 | 18.274 | 22.6608 | 0.01
8.9173 | 8.6321 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5835 | 17.5494 | 19.6953 | 27.4246 | 33.0081 | 8.9173 | 8.6321 | 2.0972 | 2.1459 | 3.4862 | 3.2917 | 7.7293 | 5.5935 | 17.5494 | 19.6953 | 27.4246 | 33.0181 | 0.01
7.3594 | 8.2945 | 2.0453 | 2.068 | 3.2266 | 3.1359 | 7.3399 | 5.2719 | 15.654 | 17.722 | 25.0618 | 30.3337 | 7.3594 | 8.2945 | 2.0453 | 2.068 | 3.2266 | 3.1359 | 7.3399 | 5.2819 | 15.654 | 17.722 | 25.0618 | 30.3437 | 0.01
10.6967 | 9.0176 | 2.1566 | 2.2348 | 3.7828 | 3.4697 | 8.1742 | 5.9393 | 19.7143 | 21.9491 | 30.1233 | 36.0626 | 10.6967 | 9.0176 | 2.1566 | 2.2348 | 3.7828 | 3.4697 | 8.1742 | 5.9493 | 19.7143 | 21.9491 | 30.1233 | 36.0726 | 0.01
14.8238 | 9.9118 | 2.2941 | 2.4412 | 4.4706 | 3.8824 | 9.206 | 6.7648 | 24.7356 | 27.1768 | 36.3828 | 43.1475 | 14.8238 | 9.9118 | 2.2941 | 2.4412 | 4.4706 | 3.8824 | 9.206 | 6.7748 | 24.7356 | 27.1768 | 36.3828 | 43.1575 | 0.01
11.6384 | 9.2216 | 2.1879 | 2.2819 | 3.9397 | 3.5638 | 8.4096 | 6.1277 | 20.86 | 23.1419 | 31.5515 | 37.6792 | 11.6384 | 9.2216 | 2.1879 | 2.2819 | 3.9397 | 3.5638 | 8.4096 | 6.1377 | 20.86 | 23.1419 | 31.5515 | 37.6892 | 0.01
17.6788 | 10.5304 | 2.3893 | 2.5839 | 4.9465 | 4.1679 | 9.9197 | 7.3358 | 28.2092 | 30.7931 | 40.7128 | 48.0486 | 17.6788 | 10.5304 | 2.3893 | 2.5839 | 4.9465 | 4.1679 | 9.9197 | 7.3458 | 28.2092 | 30.7931 | 40.7128 | 48.0586 | 0.01
4.3589 | 7.6444 | 1.9453 | 1.9179 | 2.7265 | 2.8359 | 6.5897 | 4.6718 | 12.0033 | 13.9213 | 20.511 | 25.1828 | 4.3589 | 7.6444 | 1.9453 | 1.9179 | 2.7265 | 2.8359 | 6.5897 | 4.6818 | 12.0033 | 13.9213 | 20.511 | 25.1928 | 0.01
0.47148 | 6.8022 | 1.8157 | 1.7236 | 2.0786 | 2.4471 | 5.6179 | 3.8943 | 7.2736 | 8.9972 | 14.6151 | 18.5094 | 0.47148 | 6.8022 | 1.8157 | 1.7236 | 2.0786 | 2.4471 | 5.6179 | 3.9043 | 7.2736 | 8.9972 | 14.6151 | 18.5194 | 0.01
7.8912 | 8.4097 | 2.063 | 2.0946 | 3.3152 | 3.1891 | 7.4728 | 5.3782 | 16.3009 | 18.3955 | 25.8682 | 31.2465 | 7.8912 | 8.4097 | 2.063 | 2.0946 | 3.3152 | 3.1891 | 7.4728 | 5.3882 | 16.3009 | 18.3955 | 25.8682 | 31.2565 | 0.01
4.3809 | 7.6492 | 1.946 | 1.919 | 2.7301 | 2.8381 | 6.5952 | 4.6762 | 12.0301 | 13.9491 | 20.5444 | 25.2205 | 4.3809 | 7.6492 | 1.946 | 1.919 | 2.7301 | 2.8381 | 6.5952 | 4.6862 | 12.0301 | 13.9491 | 20.5444 | 25.2305 | 0.01
12.5045 | 9.4093 | 2.2168 | 2.3252 | 4.0841 | 3.6505 | 8.6261 | 6.3009 | 21.9138 | 24.2391 | 32.8652 | 39.1661 | 12.5045 | 9.4093 | 2.2168 | 2.3252 | 4.0841 | 3.6505 | 8.6261 | 6.3109 | 21.9138 | 24.2391 | 32.8652 | 39.1761 | 0.01
-2.5623 | 6.1448 | 1.7146 | 1.5719 | 1.5729 | 2.1438 | 4.8594 | 3.2875 | 3.5825 | 5.1544 | 10.0138 | 13.3013 | -2.5623 | 6.1448 | 1.7146 | 1.5719 | 1.5729 | 2.1438 | 4.8594 | 3.2975 | 3.5825 | 5.1544 | 10.0138 | 13.3113 | 0.01
5.628 | 7.9194 | 1.9876 | 1.9814 | 2.938 | 2.9628 | 6.907 | 4.9256 | 13.5474 | 15.5288 | 22.4358 | 27.3614 | 5.628 | 7.9194 | 1.9876 | 1.9814 | 2.938 | 2.9628 | 6.907 | 4.9356 | 13.5474 | 15.5288 | 22.4358 | 27.3714 | 0.01
-2.8667 | 6.0789 | 1.7044 | 1.5567 | 1.5222 | 2.1133 | 4.7833 | 3.2267 | 3.2122 | 4.7689 | 9.5522 | 12.7789 | -2.8667 | 6.0789 | 1.7044 | 1.5567 | 1.5222 | 2.1133 | 4.7833 | 3.2367 | 3.2122 | 4.7689 | 9.5522 | 12.7889 | 0.01
-6.8201 | 5.2223 | 1.5727 | 1.359 | 0.86332 | 1.718 | 3.795 | 2.436 | -1.5977 | -0.23874 | 3.5562 | 5.9922 | -6.8201 | 5.2223 | 1.5727 | 1.359 | 0.86332 | 1.718 | 3.795 | 2.446 | -1.5977 | -0.23874 | 3.5562 | 6.0022 | 0.01
-0.06598 | 6.6857 | 1.7978 | 1.6967 | 1.989 | 2.3934 | 5.4835 | 3.7868 | 6.6197 | 8.3164 | 13.7999 | 17.5867 | -0.06598 | 6.6857 | 1.7978 | 1.6967 | 1.989 | 2.3934 | 5.4835 | 3.7968 | 6.6197 | 8.3164 | 13.7999 | 17.5967 | 0.01
-4.274 | 5.774 | 1.6575 | 1.4863 | 1.2877 | 1.9726 | 4.4315 | 2.9452 | 1.4999 | 2.9862 | 7.4177 | 10.3629 | -4.274 | 5.774 | 1.6575 | 1.4863 | 1.2877 | 1.9726 | 4.4315 | 2.9552 | 1.4999 | 2.9862 | 7.4177 | 10.3729 | 0.01
9.4 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.85 | 5.68 | 18.1367 | 20.3067 | 28.1567 | 33.8367 | 9.4 | 8.7367 | 2.1133 | 2.17 | 3.5667 | 3.34 | 7.85 | 5.69 | 18.1367 | 20.3067 | 28.1567 | 33.8467 | 0.01
-0.6032 | 6.5693 | 1.7799 | 1.6698 | 1.8995 | 2.3397 | 5.3492 | 3.6794 | 5.9661 | 7.6359 | 12.9851 | 16.6645 | -0.6032 | 6.5693 | 1.7799 | 1.6698 | 1.8995 | 2.3397 | 5.3492 | 3.6894 | 5.9661 | 7.6359 | 12.9851 | 16.6745 | 0.01
0.58262 | 6.8262 | 1.8194 | 1.7291 | 2.0971 | 2.4583 | 5.6457 | 3.9165 | 7.4089 | 9.138 | 14.7836 | 18.7002 | 0.58262 | 6.8262 | 1.8194 | 1.7291 | 2.0971 | 2.4583 | 5.6457 | 3.9265 | 7.4089 | 9.138 | 14.7836 | 18.7102 | 0.01
6.9663 | 8.2094 | 2.0322 | 2.0483 | 3.161 | 3.0966 | 7.2416 | 5.1933 | 15.1756 | 17.2239 | 24.4655 | 29.6587 | 6.9663 | 8.2094 | 2.0322 | 2.0483 | 3.161 | 3.0966 | 7.2416 | 5.2033 | 15.1756 | 17.2239 | 24.4655 | 29.6687 | 0.01
8.3163 | 8.5019 | 2.0772 | 2.1158 | 3.386 | 3.2316 | 7.5791 | 5.4633 | 16.8181 | 18.9339 | 26.513 | 31.9762 | 8.3163 | 8.5019 | 2.0772 | 2.1158 | 3.386 | 3.2316 | 7.5791 | 5.4733 | 16.8181 | 18.9339 | 26.513 | 31.9862 | 0.01
-4.5469 | 5.7148 | 1.6484 | 1.4727 | 1.2422 | 1.9453 | 4.3633 | 2.8906 | 1.1679 | 2.6406 | 7.0038 | 9.8944 | -4.5469 | 5.7148 | 1.6484 | 1.4727 | 1.2422 | 1.9453 | 4.3633 | 2.9006 | 1.1679 | 2.6406 | 7.0038 | 9.9044 | 0.01
-7.9943 | 4.9679 | 1.5335 | 1.3003 | 0.66762 | 1.6006 | 3.5014 | 2.2011 | -3.0264 | -1.7261 | 1.7753 | 3.9765 | -7.9943 | 4.9679 | 1.5335 | 1.3003 | 0.66762 | 1.6006 | 3.5014 | 2.2111 | -3.0264 | -1.7261 | 1.7753 | 3.9865 | 0.01
4.1948 | 7.6089 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5487 | 4.639 | 11.8036 | 13.7134 | 20.2621 | 24.901 | 4.1948 | 7.6089 | 1.9398 | 1.9097 | 2.6991 | 2.8195 | 6.5487 | 4.649 | 11.8036 | 13.7134 | 20.2621 | 24.911 | 0.01
0.29908 | 6.7648 | 1.81 | 1.715 | 2.0498 | 2.4299 | 5.5748 | 3.8598 | 7.0639 | 8.7788 | 14.3536 | 18.2134 | 0.29908 | 6.7648 | 1.81 | 1.715 | 2.0498 | 2.4299 | 5.5748 | 3.8698 | 7.0639 | 8.7788 | 14.3536 | 18.2234 | 0.01
2.5167 | 7.2453 | 1.8839 | 1.8258 | 2.4194 | 2.6517 | 6.1292 | 4.3033 | 9.762 | 11.5878 | 17.717 | 22.0203 | 2.5167 | 7.2453 | 1.8839 | 1.8258 | 2.4194 | 2.6517 | 6.1292 | 4.3133 | 9.762 | 11.5878 | 17.717 | 22.0303 | 0.01
14.5896 | 9.8611 | 2.2863 | 2.4295 | 4.4316 | 3.859 | 9.1474 | 6.7179 | 24.4507 | 26.8802 | 36.0276 | 42.7455 | 14.5896 | 9.8611 | 2.2863 | 2.4295 | 4.4316 | 3.859 | 9.1474 | 6.7279 | 24.4507 | 26.8802 | 36.0276 | 42.7555 | 0.01
5.9257 | 7.9839 | 1.9975 | 1.9963 | 2.9876 | 2.9926 | 6.9814 | 4.9851 | 13.9095 | 15.9058 | 22.8872 | 27.8724 | 5.9257 | 7.9839 | 1.9975 | 1.9963 | 2.9876 | 2.9926 | 6.9814 | 4.9951 | 13.9095 | 15.9058 | 22.8872 | 27.8824 | 0.01
4.8036 | 7.7408 | 1.9601 | 1.9402 | 2.8006 | 2.8804 | 6.7009 | 4.7607 | 12.5443 | 14.4845 | 21.1854 | 25.9461 | 4.8036 | 7.7408 | 1.9601 | 1.9402 | 2.8006 | 2.8804 | 6.7009 | 4.7707 | 12.5443 | 14.4845 | 21.1854 | 25.9561 | 0.01
2.8171 | 7.3104 | 1.8939 | 1.8409 | 2.4695 | 2.6817 | 6.2043 | 4.3634 | 10.1275 | 11.9683 | 18.1726 | 22.536 | 2.8171 | 7.3104 | 1.8939 | 1.8409 | 2.4695 | 2.6817 | 6.2043 | 4.3734 | 10.1275 | 11.9683 | 18.1726 | 22.546 | 0.01
7.7332 | 8.3755 | 2.0578 | 2.0867 | 3.2889 | 3.1733 | 7.4333 | 5.3466 | 16.1088 | 18.1954 | 25.6287 | 30.9754 | 7.7332 | 8.3755 | 2.0578 | 2.0867 | 3.2889 | 3.1733 | 7.4333 | 5.3566 | 16.1088 | 18.1954 | 25.6287 | 30.9854 | 0.01
10.7305 | 9.0249 | 2.1577 | 2.2365 | 3.7884 | 3.473 | 8.1826 | 5.9461 | 19.7554 | 21.9919 | 30.1745 | 36.1206 | 10.7305 | 9.0249 | 2.1577 | 2.2365 | 3.7884 | 3.473 | 8.1826 | 5.9561 | 19.7554 | 21.9919 | 30.1745 | 36.1306 | 0.01
8.4966 | 8.5409 | 2.0832 | 2.1248 | 3.4161 | 3.2497 | 7.6242 | 5.4993 | 17.0375 | 19.1624 | 26.7865 | 32.2858 | 8.4966 | 8.5409 | 2.0832 | 2.1248 | 3.4161 | 3.2497 | 7.6242 | 5.5093 | 17.0375 | 19.1624 | 26.7865 | 32.2958 | 0.01
-8.2772 | 4.9066 | 1.5241 | 1.2861 | 0.62047 | 1.5723 | 3.4307 | 2.1446 | -3.3706 | -2.0844 | 1.3463 | 3.4908 | -8.2772 | 4.9066 | 1.5241 | 1.2861 | 0.62047 | 1.5723 | 3.4307 | 2.1546 | -3.3706 | -2.0844 | 1.3463 | 3.5008 | 0.01
8.6945 | 8.5838 | 2.0898 | 2.1347 | 3.4491 | 3.2695 | 7.6736 | 5.5389 | 17.2783 | 19.413 | 27.0867 | 32.6256 | 8.6945 | 8.5838 | 2.0898 | 2.1347 | 3.4491 | 3.2695 | 7.6736 | 5.5489 | 17.2783 | 19.413 | 27.0867 | 32.6356 | 0.01
4.4416 | 7.6624 | 1.9481 | 1.9221 | 2.7403 | 2.8442 | 6.6104 | 4.6883 | 12.104 | 14.0261 | 20.6365 | 25.3248 | 4.4416 | 7.6624 | 1.9481 | 1.9221 | 2.7403 | 2.8442 | 6.6104 | 4.6983 | 12.104 | 14.0261 | 20.6365 | 25.3348 | 0.01
4.5166 | 7.6786 | 1.9506 | 1.9258 | 2.7528 | 2.8517 | 6.6292 | 4.7033 | 12.1953 | 14.1211 | 20.7502 | 25.4536 | 4.5166 | 7.6786 | 1.9506 | 1.9258 | 2.7528 | 2.8517 | 6.6292 | 4.7133 | 12.1953 | 14.1211 | 20.7502 | 25.4636 | 0.01
7.1372 | 8.2464 | 2.0379 | 2.0569 | 3.1895 | 3.1137 | 7.2843 | 5.2274 | 15.3835 | 17.4404 | 24.7247 | 29.9521 | 7.1372 | 8.2464 | 2.0379 | 2.0569 | 3.1895 | 3.1137 | 7.2843 | 5.2374 | 15.3835 | 17.4404 | 24.7247 | 29.9621 | 0.01
9.3226 | 8.7199 | 2.1108 | 2.1661 | 3.5538 | 3.3323 | 7.8307 | 5.6645 | 18.0425 | 20.2087 | 28.0393 | 33.7039 | 9.3226 | 8.7199 | 2.1108 | 2.1661 | 3.5538 | 3.3323 | 7.8307 | 5.6745 | 18.0425 | 20.2087 | 28.0393 | 33.7139 | 0.01
1.1275 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7819 | 4.0255 | 8.0717 | 9.8281 | 15.61 | 19.6355 | 1.1275 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7819 | 4.0355 | 8.0717 | 9.8281 | 15.61 | 19.6455 | 0.01
-2.6418 | 6.1276 | 1.7119 | 1.5679 | 1.5597 | 2.1358 | 4.8395 | 3.2716 | 3.4858 | 5.0537 | 9.8932 | 13.1649 | -2.6418 | 6.1276 | 1.7119 | 1.5679 | 1.5597 | 2.1358 | 4.8395 | 3.2816 | 3.4858 | 5.0537 | 9.8932 | 13.1749 | 0.01
9.0604 | 8.6631 | 2.102 | 2.153 | 3.5101 | 3.306 | 7.7651 | 5.6121 | 17.7234 | 19.8765 | 27.6415 | 33.2536 | 9.0604 | 8.6631 | 2.102 | 2.153 | 3.5101 | 3.306 | 7.7651 | 5.6221 | 17.7234 | 19.8765 | 27.6415 | 33.2636 | 0.01
10.6866 | 9.0154 | 2.1562 | 2.2343 | 3.7811 | 3.4687 | 8.1717 | 5.9373 | 19.7021 | 21.9364 | 30.1081 | 36.0454 | 10.6866 | 9.0154 | 2.1562 | 2.2343 | 3.7811 | 3.4687 | 8.1717 | 5.9473 | 19.7021 | 21.9364 | 30.1081 | 36.0554 | 0.01
8.5379 | 8.5499 | 2.0846 | 2.1269 | 3.423 | 3.2538 | 7.6345 | 5.5076 | 17.0878 | 19.2146 | 26.8491 | 32.3567 | 8.5379 | 8.5499 | 2.0846 | 2.1269 | 3.423 | 3.2538 | 7.6345 | 5.5176 | 17.0878 | 19.2146 | 26.8491 | 32.3667 | 0.01
1.8028 | 7.0906 | 1.8601 | 1.7901 | 2.3005 | 2.5803 | 5.9507 | 4.1606 | 8.8935 | 10.6836 | 16.6343 | 20.7949 | 1.8028 | 7.0906 | 1.8601 | 1.7901 | 2.3005 | 2.5803 | 5.9507 | 4.1706 | 8.8935 | 10.6836 | 16.6343 | 20.8049 | 0.01
0.2989 | 6.7648 | 1.81 | 1.7149 | 2.0498 | 2.4299 | 5.5747 | 3.8598 | 7.0637 | 8.7786 | 14.3533 | 18.2131 | 0.2989 | 6.7648 | 1.81 | 1.7149 | 2.0498 | 2.4299 | 5.5747 | 3.8698 | 7.0637 | 8.7786 | 14.3533 | 18.2231 | 0.01
-0.13421 | 6.6709 | 1.7955 | 1.6933 | 1.9776 | 2.3866 | 5.4664 | 3.7732 | 6.5367 | 8.23 | 13.6965 | 17.4696 | -0.13421 | 6.6709 | 1.7955 | 1.6933 | 1.9776 | 2.3866 | 5.4664 | 3.7832 | 6.5367 | 8.23 | 13.6965 | 17.4796 | 0.01
7.0264 | 8.2224 | 2.0342 | 2.0513 | 3.1711 | 3.1026 | 7.2566 | 5.2053 | 15.2488 | 17.3001 | 24.5567 | 29.762 | 7.0264 | 8.2224 | 2.0342 | 2.0513 | 3.1711 | 3.1026 | 7.2566 | 5.2153 | 15.2488 | 17.3001 | 24.5567 | 29.772 | 0.01
15.9381 | 10.1533 | 2.3313 | 2.4969 | 4.6563 | 3.9938 | 9.4845 | 6.9876 | 26.0913 | 28.5883 | 38.0728 | 45.0604 | 15.9381 | 10.1533 | 2.3313 | 2.4969 | 4.6563 | 3.9938 | 9.4845 | 6.9976 | 26.0913 | 28.5883 | 38.0728 | 45.0704 | 0.01
4.2657 | 7.6242 | 1.9422 | 1.9133 | 2.711 | 2.8266 | 6.5664 | 4.6531 | 11.89 | 13.8033 | 20.3697 | 25.0229 | 4.2657 | 7.6242 | 1.9422 | 1.9133 | 2.711 | 2.8266 | 6.5664 | 4.6631 | 11.89 | 13.8033 | 20.3697 | 25.0329 | 0.01
-1.1135 | 6.4587 | 1.7629 | 1.6443 | 1.8144 | 2.2886 | 5.2216 | 3.5773 | 5.3452 | 6.9896 | 12.2112 | 15.7885 | -1.1135 | 6.4587 | 1.7629 | 1.6443 | 1.8144 | 2.2886 | 5.2216 | 3.5873 | 5.3452 | 6.9896 | 12.2112 | 15.7985 | 0.01
4.8713 | 7.7554 | 1.9624 | 1.9436 | 2.8119 | 2.8871 | 6.7178 | 4.7743 | 12.6267 | 14.5703 | 21.2881 | 26.0624 | 4.8713 | 7.7554 | 1.9624 | 1.9436 | 2.8119 | 2.8871 | 6.7178 | 4.7843 | 12.6267 | 14.5703 | 21.2881 | 26.0724 | 0.01
7.0446 | 8.2263 | 2.0348 | 2.0522 | 3.1741 | 3.1045 | 7.2612 | 5.2089 | 15.2709 | 17.3232 | 24.5843 | 29.7933 | 7.0446 | 8.2263 | 2.0348 | 2.0522 | 3.1741 | 3.1045 | 7.2612 | 5.2189 | 15.2709 | 17.3232 | 24.5843 | 29.8033 | 0.01
20.3696 | 11.1134 | 2.479 | 2.7185 | 5.3949 | 4.437 | 10.5924 | 7.8739 | 31.483 | 34.2015 | 44.7939 | 52.6678 | 20.3696 | 11.1134 | 2.479 | 2.7185 | 5.3949 | 4.437 | 10.5924 | 7.8839 | 31.483 | 34.2015 | 44.7939 | 52.6778 | 0.01
2.9926 | 7.3484 | 1.8998 | 1.8496 | 2.4988 | 2.6993 | 6.2482 | 4.3985 | 10.341 | 12.1907 | 18.4388 | 22.8374 | 2.9926 | 7.3484 | 1.8998 | 1.8496 | 2.4988 | 2.6993 | 6.2482 | 4.4085 | 10.341 | 12.1907 | 18.4388 | 22.8474 | 0.01
3.3625 | 7.4285 | 1.9121 | 1.8681 | 2.5604 | 2.7362 | 6.3406 | 4.4725 | 10.791 | 12.6591 | 18.9998 | 23.4723 | 3.3625 | 7.4285 | 1.9121 | 1.8681 | 2.5604 | 2.7362 | 6.3406 | 4.4825 | 10.791 | 12.6591 | 18.9998 | 23.4823 | 0.01
2.8398 | 7.3153 | 1.8947 | 1.842 | 2.4733 | 2.684 | 6.21 | 4.368 | 10.1551 | 11.9971 | 18.207 | 22.575 | 2.8398 | 7.3153 | 1.8947 | 1.842 | 2.4733 | 2.684 | 6.21 | 4.378 | 10.1551 | 11.9971 | 18.207 | 22.585 | 0.01
8.605 | 8.5644 | 2.0868 | 2.1302 | 3.4342 | 3.2605 | 7.6512 | 5.521 | 17.1694 | 19.2996 | 26.9509 | 32.4719 | 8.605 | 8.5644 | 2.0868 | 2.1302 | 3.4342 | 3.2605 | 7.6512 | 5.531 | 17.1694 | 19.2996 | 26.9509 | 32.4819 | 0.01
8.192 | 8.4749 | 2.0731 | 2.1096 | 3.3653 | 3.2192 | 7.548 | 5.4384 | 16.6669 | 18.7765 | 26.3245 | 31.7629 | 8.192 | 8.4749 | 2.0731 | 2.1096 | 3.3653 | 3.2192 | 7.548 | 5.4484 | 16.6669 | 18.7765 | 26.3245 | 31.7729 | 0.01
8.0575 | 8.4458 | 2.0686 | 2.1029 | 3.3429 | 3.2057 | 7.5144 | 5.4115 | 16.5033 | 18.6062 | 26.1205 | 31.532 | 8.0575 | 8.4458 | 2.0686 | 2.1029 | 3.3429 | 3.2057 | 7.5144 | 5.4215 | 16.5033 | 18.6062 | 26.1205 | 31.542 | 0.01
5.6798 | 7.9306 | 1.9893 | 1.984 | 2.9466 | 2.968 | 6.92 | 4.936 | 13.6104 | 15.5944 | 22.5144 | 27.4503 | 5.6798 | 7.9306 | 1.9893 | 1.984 | 2.9466 | 2.968 | 6.92 | 4.946 | 13.6104 | 15.5944 | 22.5144 | 27.4603 | 0.01
12.1633 | 9.3354 | 2.2054 | 2.3082 | 4.0272 | 3.6163 | 8.5408 | 6.2327 | 21.4987 | 23.8069 | 32.3477 | 38.5804 | 12.1633 | 9.3354 | 2.2054 | 2.3082 | 4.0272 | 3.6163 | 8.5408 | 6.2427 | 21.4987 | 23.8069 | 32.3477 | 38.5904 | 0.01
8.89 | 8.6262 | 2.0963 | 2.1445 | 3.4817 | 3.289 | 7.7225 | 5.578 | 17.5161 | 19.6606 | 27.3831 | 32.9611 | 8.89 | 8.6262 | 2.0963 | 2.1445 | 3.4817 | 3.289 | 7.7225 | 5.588 | 17.5161 | 19.6606 | 27.3831 | 32.9711 | 0.01
4.5152 | 7.6783 | 1.9505 | 1.9258 | 2.7525 | 2.8515 | 6.6288 | 4.703 | 12.1935 | 14.1192 | 20.748 | 25.451 | 4.5152 | 7.6783 | 1.9505 | 1.9258 | 2.7525 | 2.8515 | 6.6288 | 4.713 | 12.1935 | 14.1192 | 20.748 | 25.461 | 0.01
17.5746 | 10.5078 | 2.3858 | 2.5787 | 4.9291 | 4.1575 | 9.8937 | 7.3149 | 28.0824 | 30.6612 | 40.5548 | 47.8697 | 17.5746 | 10.5078 | 2.3858 | 2.5787 | 4.9291 | 4.1575 | 9.8937 | 7.3249 | 28.0824 | 30.6612 | 40.5548 | 47.8797 | 0.01
7.2511 | 8.2711 | 2.0417 | 2.0626 | 3.2085 | 3.1251 | 7.3128 | 5.2502 | 15.5222 | 17.5848 | 24.8976 | 30.1478 | 7.2511 | 8.2711 | 2.0417 | 2.0626 | 3.2085 | 3.1251 | 7.3128 | 5.2602 | 15.5222 | 17.5848 | 24.8976 | 30.1578 | 0.01
7.1645 | 8.2523 | 2.0388 | 2.0582 | 3.1941 | 3.1164 | 7.2911 | 5.2329 | 15.4168 | 17.475 | 24.7661 | 29.999 | 7.1645 | 8.2523 | 2.0388 | 2.0582 | 3.1941 | 3.1164 | 7.2911 | 5.2429 | 15.4168 | 17.475 | 24.7661 | 30.009 | 0.01
8.9096 | 8.6304 | 2.097 | 2.1455 | 3.4849 | 3.291 | 7.7274 | 5.5819 | 17.54 | 19.6855 | 27.4129 | 32.9948 | 8.9096 | 8.6304 | 2.097 | 2.1455 | 3.4849 | 3.291 | 7.7274 | 5.5919 | 17.54 | 19.6855 | 27.4129 | 33.0048 | 0.01
13.8753 | 9.7063 | 2.2625 | 2.3938 | 4.3126 | 3.7875 | 8.9688 | 6.5751 | 23.5816 | 25.9754 | 34.9442 | 41.5193 | 13.8753 | 9.7063 | 2.2625 | 2.3938 | 4.3126 | 3.7875 | 8.9688 | 6.5851 | 23.5816 | 25.9754 | 34.9442 | 41.5293 | 0.01
14.9444 | 9.938 | 2.2981 | 2.4472 | 4.4907 | 3.8944 | 9.2361 | 6.7889 | 24.8824 | 27.3296 | 36.5657 | 43.3546 | 14.9444 | 9.938 | 2.2981 | 2.4472 | 4.4907 | 3.8944 | 9.2361 | 6.7989 | 24.8824 | 27.3296 | 36.5657 | 43.3646 | 0.01
12.6497 | 9.4408 | 2.2217 | 2.3325 | 4.1083 | 3.665 | 8.6624 | 6.3299 | 22.0904 | 24.4229 | 33.0853 | 39.4153 | 12.6497 | 9.4408 | 2.2217 | 2.3325 | 4.1083 | 3.665 | 8.6624 | 6.3399 | 22.0904 | 24.4229 | 33.0853 | 39.4253 | 0.01
-5.3839 | 5.5335 | 1.6205 | 1.4308 | 1.1027 | 1.8616 | 4.154 | 2.7232 | 0.14953 | 1.5803 | 5.7343 | 8.4576 | -5.3839 | 5.5335 | 1.6205 | 1.4308 | 1.1027 | 1.8616 | 4.154 | 2.7332 | 0.14953 | 1.5803 | 5.7343 | 8.4676 | 0.01
7.415 | 8.3066 | 2.0472 | 2.0707 | 3.2358 | 3.1415 | 7.3537 | 5.283 | 15.7215 | 17.7923 | 25.146 | 30.429 | 7.415 | 8.3066 | 2.0472 | 2.0707 | 3.2358 | 3.1415 | 7.3537 | 5.293 | 15.7215 | 17.7923 | 25.146 | 30.439 | 0.01
0.75401 | 6.8634 | 1.8251 | 1.7377 | 2.1257 | 2.4754 | 5.6885 | 3.9508 | 7.6174 | 9.3551 | 15.0436 | 18.9944 | 0.75401 | 6.8634 | 1.8251 | 1.7377 | 2.1257 | 2.4754 | 5.6885 | 3.9608 | 7.6174 | 9.3551 | 15.0436 | 19.0044 | 0.01
7.6785 | 8.3637 | 2.0559 | 2.0839 | 3.2797 | 3.1678 | 7.4196 | 5.3357 | 16.0421 | 18.1261 | 25.5457 | 30.8814 | 7.6785 | 8.3637 | 2.0559 | 2.0839 | 3.2797 | 3.1678 | 7.4196 | 5.3457 | 16.0421 | 18.1261 | 25.5457 | 30.8914 | 0.01
-6.7356 | 5.2406 | 1.5755 | 1.3632 | 0.8774 | 1.7264 | 3.8161 | 2.4529 | -1.495 | -0.13174 | 3.6844 | 6.1373 | -6.7356 | 5.2406 | 1.5755 | 1.3632 | 0.8774 | 1.7264 | 3.8161 | 2.4629 | -1.495 | -0.13174 | 3.6844 | 6.1473 | 0.01
15.0729 | 9.9658 | 2.3024 | 2.4536 | 4.5121 | 3.9073 | 9.2682 | 6.8146 | 25.0387 | 27.4923 | 36.7606 | 43.5751 | 15.0729 | 9.9658 | 2.3024 | 2.4536 | 4.5121 | 3.9073 | 9.2682 | 6.8246 | 25.0387 | 27.4923 | 36.7606 | 43.5851 | 0.01
4.1628 | 7.6019 | 1.9388 | 1.9081 | 2.6938 | 2.8163 | 6.5407 | 4.6326 | 11.7648 | 13.6729 | 20.2136 | 24.8462 | 4.1628 | 7.6019 | 1.9388 | 1.9081 | 2.6938 | 2.8163 | 6.5407 | 4.6426 | 11.7648 | 13.6729 | 20.2136 | 24.8562 | 0.01
-1.8279 | 6.304 | 1.7391 | 1.6086 | 1.6954 | 2.2172 | 5.043 | 3.4344 | 4.4761 | 6.0847 | 11.1277 | 14.5622 | -1.8279 | 6.304 | 1.7391 | 1.6086 | 1.6954 | 2.2172 | 5.043 | 3.4444 | 4.4761 | 6.0847 | 11.1277 | 14.5722 | 0.01
7.3349 | 8.2892 | 2.0445 | 2.0667 | 3.2225 | 3.1335 | 7.3337 | 5.267 | 15.6242 | 17.6909 | 25.0246 | 30.2916 | 7.3349 | 8.2892 | 2.0445 | 2.0667 | 3.2225 | 3.1335 | 7.3337 | 5.277 | 15.6242 | 17.6909 | 25.0246 | 30.3016 | 0.01
-2.9217 | 6.067 | 1.7026 | 1.5539 | 1.5131 | 2.1078 | 4.7696 | 3.2157 | 3.1453 | 4.6992 | 9.4688 | 12.6845 | -2.9217 | 6.067 | 1.7026 | 1.5539 | 1.5131 | 2.1078 | 4.7696 | 3.2257 | 3.1453 | 4.6992 | 9.4688 | 12.6945 | 0.01
6.4196 | 8.0909 | 2.014 | 2.021 | 3.0699 | 3.042 | 7.1049 | 5.0839 | 14.5106 | 16.5315 | 23.6364 | 28.7204 | 6.4196 | 8.0909 | 2.014 | 2.021 | 3.0699 | 3.042 | 7.1049 | 5.0939 | 14.5106 | 16.5315 | 23.6364 | 28.7304 | 0.01
-3.1568 | 6.016 | 1.6948 | 1.5422 | 1.4739 | 2.0843 | 4.7108 | 3.1686 | 2.8592 | 4.4013 | 9.1121 | 12.2807 | -3.1568 | 6.016 | 1.6948 | 1.5422 | 1.4739 | 2.0843 | 4.7108 | 3.1786 | 2.8592 | 4.4013 | 9.1121 | 12.2907 | 0.01
-5.5235 | 5.5032 | 1.6159 | 1.4238 | 1.0794 | 1.8476 | 4.1191 | 2.6953 | -0.0203 | 1.4035 | 5.5226 | 8.2179 | -5.5235 | 5.5032 | 1.6159 | 1.4238 | 1.0794 | 1.8476 | 4.1191 | 2.7053 | -0.0203 | 1.4035 | 5.5226 | 8.2279 | 0.01
4.1099 | 7.5905 | 1.937 | 1.9055 | 2.685 | 2.811 | 6.5275 | 4.622 | 11.7004 | 13.6058 | 20.1333 | 24.7553 | 4.1099 | 7.5905 | 1.937 | 1.9055 | 2.685 | 2.811 | 6.5275 | 4.632 | 11.7004 | 13.6058 | 20.1333 | 24.7653 | 0.01
9.1846 | 8.69 | 2.1062 | 2.1592 | 3.5308 | 3.3185 | 7.7962 | 5.6369 | 17.8746 | 20.0339 | 27.83 | 33.4669 | 9.1846 | 8.69 | 2.1062 | 2.1592 | 3.5308 | 3.3185 | 7.7962 | 5.6469 | 17.8746 | 20.0339 | 27.83 | 33.4769 | 0.01
-3.3156 | 5.9816 | 1.6895 | 1.5342 | 1.4474 | 2.0684 | 4.6711 | 3.1369 | 2.666 | 4.2003 | 8.8714 | 12.0082 | -3.3156 | 5.9816 | 1.6895 | 1.5342 | 1.4474 | 2.0684 | 4.6711 | 3.1469 | 2.666 | 4.2003 | 8.8714 | 12.0182 | 0.01
10.6419 | 9.0057 | 2.1547 | 2.2321 | 3.7737 | 3.4642 | 8.1605 | 5.9284 | 19.6477 | 21.8798 | 30.0402 | 35.9686 | 10.6419 | 9.0057 | 2.1547 | 2.2321 | 3.7737 | 3.4642 | 8.1605 | 5.9384 | 19.6477 | 21.8798 | 30.0402 | 35.9786 | 0.01
9.4293 | 8.743 | 2.1143 | 2.1715 | 3.5716 | 3.3429 | 7.8573 | 5.6859 | 18.1724 | 20.3438 | 28.2012 | 33.8871 | 9.4293 | 8.743 | 2.1143 | 2.1715 | 3.5716 | 3.3429 | 7.8573 | 5.6959 | 18.1724 | 20.3438 | 28.2012 | 33.8971 | 0.01
24.2891 | 11.9626 | 2.6096 | 2.9145 | 6.0482 | 4.8289 | 11.5723 | 8.6578 | 36.2518 | 39.1662 | 50.7385 | 59.3964 | 24.2891 | 11.9626 | 2.6096 | 2.9145 | 6.0482 | 4.8289 | 11.5723 | 8.6678 | 36.2518 | 39.1662 | 50.7385 | 59.4064 | 0.01
8.2951 | 8.4973 | 2.0765 | 2.1148 | 3.3825 | 3.2295 | 7.5738 | 5.459 | 16.7923 | 18.9071 | 26.4808 | 31.9398 | 8.2951 | 8.4973 | 2.0765 | 2.1148 | 3.3825 | 3.2295 | 7.5738 | 5.469 | 16.7923 | 18.9071 | 26.4808 | 31.9498 | 0.01
-5.1847 | 5.5767 | 1.6272 | 1.4408 | 1.1359 | 1.8815 | 4.2038 | 2.7631 | 0.392 | 1.8328 | 6.0366 | 8.7997 | -5.1847 | 5.5767 | 1.6272 | 1.4408 | 1.1359 | 1.8815 | 4.2038 | 2.7731 | 0.392 | 1.8328 | 6.0366 | 8.8097 | 0.01
7.4308 | 8.31 | 2.0477 | 2.0715 | 3.2385 | 3.1431 | 7.3577 | 5.2862 | 15.7408 | 17.8123 | 25.17 | 30.4562 | 7.4308 | 8.31 | 2.0477 | 2.0715 | 3.2385 | 3.1431 | 7.3577 | 5.2962 | 15.7408 | 17.8123 | 25.17 | 30.4662 | 0.01
3.9805 | 7.5624 | 1.9327 | 1.899 | 2.6634 | 2.798 | 6.4951 | 4.5961 | 11.5429 | 13.4419 | 19.937 | 24.5331 | 3.9805 | 7.5624 | 1.9327 | 1.899 | 2.6634 | 2.798 | 6.4951 | 4.6061 | 11.5429 | 13.4419 | 19.937 | 24.5431 | 0.01
6.9627 | 8.2086 | 2.0321 | 2.0481 | 3.1605 | 3.0963 | 7.2407 | 5.1925 | 15.1713 | 17.2195 | 24.4602 | 29.6527 | 6.9627 | 8.2086 | 2.0321 | 2.0481 | 3.1605 | 3.0963 | 7.2407 | 5.2025 | 15.1713 | 17.2195 | 24.4602 | 29.6627 | 0.01
10.5847 | 8.9933 | 2.1528 | 2.2292 | 3.7641 | 3.4585 | 8.1462 | 5.9169 | 19.578 | 21.8073 | 29.9534 | 35.8704 | 10.5847 | 8.9933 | 2.1528 | 2.2292 | 3.7641 | 3.4585 | 8.1462 | 5.9269 | 19.578 | 21.8073 | 29.9534 | 35.8804 | 0.01
-1.1576 | 6.4492 | 1.7614 | 1.6421 | 1.8071 | 2.2842 | 5.2106 | 3.5685 | 5.2915 | 6.9337 | 12.1443 | 15.7127 | -1.1576 | 6.4492 | 1.7614 | 1.6421 | 1.8071 | 2.2842 | 5.2106 | 3.5785 | 5.2915 | 6.9337 | 12.1443 | 15.7227 | 0.01
-1.1256 | 6.4561 | 1.7625 | 1.6437 | 1.8124 | 2.2874 | 5.2186 | 3.5749 | 5.3305 | 6.9742 | 12.1928 | 15.7677 | -1.1256 | 6.4561 | 1.7625 | 1.6437 | 1.8124 | 2.2874 | 5.2186 | 3.5849 | 5.3305 | 6.9742 | 12.1928 | 15.7777 | 0.01
10.0004 | 8.8667 | 2.1333 | 2.2 | 3.6667 | 3.4 | 8.0001 | 5.8001 | 18.8671 | 21.0671 | 29.0672 | 34.8673 | 10.0004 | 8.8667 | 2.1333 | 2.2 | 3.6667 | 3.4 | 8.0001 | 5.8101 | 18.8671 | 21.0671 | 29.0672 | 34.8773 | 0.01
8.9462 | 8.6383 | 2.0982 | 2.1473 | 3.491 | 3.2946 | 7.7366 | 5.5892 | 17.5845 | 19.7319 | 27.4684 | 33.0576 | 8.9462 | 8.6383 | 2.0982 | 2.1473 | 3.491 | 3.2946 | 7.7366 | 5.5992 | 17.5845 | 19.7319 | 27.4684 | 33.0676 | 0.01
1.749 | 7.0789 | 1.8583 | 1.7874 | 2.2915 | 2.5749 | 5.9372 | 4.1498 | 8.8279 | 10.6153 | 16.5526 | 20.7024 | 1.749 | 7.0789 | 1.8583 | 1.7874 | 2.2915 | 2.5749 | 5.9372 | 4.1598 | 8.8279 | 10.6153 | 16.5526 | 20.7124 | 0.01
0.17321 | 6.7375 | 1.8058 | 1.7087 | 2.0289 | 2.4173 | 5.5433 | 3.8346 | 6.9107 | 8.6194 | 14.1627 | 17.9973 | 0.17321 | 6.7375 | 1.8058 | 1.7087 | 2.0289 | 2.4173 | 5.5433 | 3.8446 | 6.9107 | 8.6194 | 14.1627 | 18.0073 | 0.01
7.8213 | 8.3946 | 2.0607 | 2.0911 | 3.3035 | 3.1821 | 7.4553 | 5.3643 | 16.2159 | 18.3069 | 25.7622 | 31.1265 | 7.8213 | 8.3946 | 2.0607 | 2.0911 | 3.3035 | 3.1821 | 7.4553 | 5.3743 | 16.2159 | 18.3069 | 25.7622 | 31.1365 | 0.01
15.1106 | 9.974 | 2.3037 | 2.4555 | 4.5184 | 3.9111 | 9.2777 | 6.8221 | 25.0846 | 27.5401 | 36.8178 | 43.6399 | 15.1106 | 9.974 | 2.3037 | 2.4555 | 4.5184 | 3.9111 | 9.2777 | 6.8321 | 25.0846 | 27.5401 | 36.8178 | 43.6499 | 0.01
10.1426 | 8.8976 | 2.1381 | 2.2071 | 3.6904 | 3.4143 | 8.0357 | 5.8285 | 19.0402 | 21.2473 | 29.283 | 35.1115 | 10.1426 | 8.8976 | 2.1381 | 2.2071 | 3.6904 | 3.4143 | 8.0357 | 5.8385 | 19.0402 | 21.2473 | 29.283 | 35.1215 | 0.01
16.8847 | 10.3583 | 2.3628 | 2.5442 | 4.8141 | 4.0885 | 9.7212 | 7.1769 | 27.243 | 29.7873 | 39.5084 | 46.6854 | 16.8847 | 10.3583 | 2.3628 | 2.5442 | 4.8141 | 4.0885 | 9.7212 | 7.1869 | 27.243 | 29.7873 | 39.5084 | 46.6954 | 0.01
7.7903 | 8.3879 | 2.0597 | 2.0895 | 3.2984 | 3.179 | 7.4476 | 5.3581 | 16.1782 | 18.2677 | 25.7153 | 31.0734 | 7.7903 | 8.3879 | 2.0597 | 2.0895 | 3.2984 | 3.179 | 7.4476 | 5.3681 | 16.1782 | 18.2677 | 25.7153 | 31.0834 | 0.01
13.5503 | 9.6359 | 2.2517 | 2.3775 | 4.2584 | 3.755 | 8.8876 | 6.5101 | 23.1862 | 25.5637 | 34.4513 | 40.9613 | 13.5503 | 9.6359 | 2.2517 | 2.3775 | 4.2584 | 3.755 | 8.8876 | 6.5201 | 23.1862 | 25.5637 | 34.4513 | 40.9713 | 0.01
15.0013 | 9.9503 | 2.3 | 2.4501 | 4.5002 | 3.9001 | 9.2503 | 6.8003 | 24.9515 | 27.4016 | 36.6519 | 43.4522 | 15.0013 | 9.9503 | 2.3 | 2.4501 | 4.5002 | 3.9001 | 9.2503 | 6.8103 | 24.9515 | 27.4016 | 36.6519 | 43.4622 | 0.01
7.9384 | 8.42 | 2.0646 | 2.0969 | 3.3231 | 3.1938 | 7.4846 | 5.3877 | 16.3584 | 18.4553 | 25.9399 | 31.3276 | 7.9384 | 8.42 | 2.0646 | 2.0969 | 3.3231 | 3.1938 | 7.4846 | 5.3977 | 16.3584 | 18.4553 | 25.9399 | 31.3376 | 0.01
6.8871 | 8.1922 | 2.0296 | 2.0444 | 3.1479 | 3.0887 | 7.2218 | 5.1774 | 15.0793 | 17.1237 | 24.3455 | 29.5229 | 6.8871 | 8.1922 | 2.0296 | 2.0444 | 3.1479 | 3.0887 | 7.2218 | 5.1874 | 15.0793 | 17.1237 | 24.3455 | 29.5329 | 0.01
1.9661 | 7.126 | 1.8655 | 1.7983 | 2.3277 | 2.5966 | 5.9915 | 4.1932 | 9.0921 | 10.8904 | 16.8819 | 21.0751 | 1.9661 | 7.126 | 1.8655 | 1.7983 | 2.3277 | 2.5966 | 5.9915 | 4.2032 | 9.0921 | 10.8904 | 16.8819 | 21.0851 | 0.01
3.4524 | 7.448 | 1.9151 | 1.8726 | 2.5754 | 2.7452 | 6.3631 | 4.4905 | 10.9004 | 12.773 | 19.1361 | 23.6266 | 3.4524 | 7.448 | 1.9151 | 1.8726 | 2.5754 | 2.7452 | 6.3631 | 4.5005 | 10.9004 | 12.773 | 19.1361 | 23.6366 | 0.01
11.6679 | 9.228 | 2.1889 | 2.2834 | 3.9446 | 3.5668 | 8.417 | 6.1336 | 20.8959 | 23.1793 | 31.5963 | 37.7298 | 11.6679 | 9.228 | 2.1889 | 2.2834 | 3.9446 | 3.5668 | 8.417 | 6.1436 | 20.8959 | 23.1793 | 31.5963 | 37.7398 | 0.01
-0.70544 | 6.5472 | 1.7765 | 1.6647 | 1.8824 | 2.3295 | 5.3236 | 3.6589 | 5.8417 | 7.5064 | 12.8301 | 16.489 | -0.70544 | 6.5472 | 1.7765 | 1.6647 | 1.8824 | 2.3295 | 5.3236 | 3.6689 | 5.8417 | 7.5064 | 12.8301 | 16.499 | 0.01
4.6741 | 7.7127 | 1.9558 | 1.9337 | 2.779 | 2.8674 | 6.6685 | 4.7348 | 12.3868 | 14.3205 | 20.989 | 25.7238 | 4.6741 | 7.7127 | 1.9558 | 1.9337 | 2.779 | 2.8674 | 6.6685 | 4.7448 | 12.3868 | 14.3205 | 20.989 | 25.7338 | 0.01
10.26 | 8.923 | 2.142 | 2.213 | 3.71 | 3.426 | 8.065 | 5.852 | 19.183 | 21.396 | 29.461 | 35.313 | 10.26 | 8.923 | 2.142 | 2.213 | 3.71 | 3.426 | 8.065 | 5.862 | 19.183 | 21.396 | 29.461 | 35.323 | 0.01
7.416 | 8.3068 | 2.0472 | 2.0708 | 3.236 | 3.1416 | 7.354 | 5.2832 | 15.7228 | 17.7936 | 25.1476 | 30.4308 | 7.416 | 8.3068 | 2.0472 | 2.0708 | 3.236 | 3.1416 | 7.354 | 5.2932 | 15.7228 | 17.7936 | 25.1476 | 30.4408 | 0.01
2.6131 | 7.2662 | 1.8871 | 1.8307 | 2.4355 | 2.6613 | 6.1533 | 4.3226 | 9.8793 | 11.71 | 17.8633 | 22.1859 | 2.6131 | 7.2662 | 1.8871 | 1.8307 | 2.4355 | 2.6613 | 6.1533 | 4.3326 | 9.8793 | 11.71 | 17.8633 | 22.1959 | 0.01
4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7048 | 12.2044 | 14.1306 | 20.7616 | 25.4664 | 4.5241 | 7.6802 | 1.9508 | 1.9262 | 2.754 | 2.8524 | 6.631 | 4.7148 | 12.2044 | 14.1306 | 20.7616 | 25.4764 | 0.01
9.0177 | 8.6538 | 2.1006 | 2.1509 | 3.5029 | 3.3018 | 7.7544 | 5.6035 | 17.6715 | 19.8224 | 27.5768 | 33.1803 | 9.0177 | 8.6538 | 2.1006 | 2.1509 | 3.5029 | 3.3018 | 7.7544 | 5.6135 | 17.6715 | 19.8224 | 27.5768 | 33.1903 | 0.01
11.271 | 9.1421 | 2.1757 | 2.2636 | 3.8785 | 3.5271 | 8.3178 | 6.0542 | 20.4131 | 22.6766 | 30.9944 | 37.0486 | 11.271 | 9.1421 | 2.1757 | 2.2636 | 3.8785 | 3.5271 | 8.3178 | 6.0642 | 20.4131 | 22.6766 | 30.9944 | 37.0586 | 0.01
4.8689 | 7.7549 | 1.9623 | 1.9434 | 2.8115 | 2.8869 | 6.7172 | 4.7738 | 12.6238 | 14.5672 | 21.2844 | 26.0582 | 4.8689 | 7.7549 | 1.9623 | 1.9434 | 2.8115 | 2.8869 | 6.7172 | 4.7838 | 12.6238 | 14.5672 | 21.2844 | 26.0682 | 0.01
13.7381 | 9.6766 | 2.2579 | 2.3869 | 4.2897 | 3.7738 | 8.9345 | 6.5476 | 23.4147 | 25.8016 | 34.7361 | 41.2837 | 13.7381 | 9.6766 | 2.2579 | 2.3869 | 4.2897 | 3.7738 | 8.9345 | 6.5576 | 23.4147 | 25.8016 | 34.7361 | 41.2937 | 0.01
-0.14801 | 6.6679 | 1.7951 | 1.6926 | 1.9753 | 2.3852 | 5.463 | 3.7704 | 6.5199 | 8.2125 | 13.6755 | 17.4459 | -0.14801 | 6.6679 | 1.7951 | 1.6926 | 1.9753 | 2.3852 | 5.463 | 3.7804 | 6.5199 | 8.2125 | 13.6755 | 17.4559 | 0.01
4.9965 | 7.7826 | 1.9666 | 1.9498 | 2.8328 | 2.8997 | 6.7491 | 4.7993 | 12.7791 | 14.7289 | 21.478 | 26.2773 | 4.9965 | 7.7826 | 1.9666 | 1.9498 | 2.8328 | 2.8997 | 6.7491 | 4.8093 | 12.7791 | 14.7289 | 21.478 | 26.2873 | 0.01
2.9362 | 7.3362 | 1.8979 | 1.8468 | 2.4894 | 2.6936 | 6.234 | 4.3872 | 10.2723 | 12.1191 | 18.3532 | 22.7404 | 2.9362 | 7.3362 | 1.8979 | 1.8468 | 2.4894 | 2.6936 | 6.234 | 4.3972 | 10.2723 | 12.1191 | 18.3532 | 22.7504 | 0.01
10.8682 | 9.0548 | 2.1623 | 2.2434 | 3.8114 | 3.4868 | 8.2171 | 5.9736 | 19.923 | 22.1664 | 30.3835 | 36.3571 | 10.8682 | 9.0548 | 2.1623 | 2.2434 | 3.8114 | 3.4868 | 8.2171 | 5.9836 | 19.923 | 22.1664 | 30.3835 | 36.3671 | 0.01
5.3766 | 7.8649 | 1.9792 | 1.9688 | 2.8961 | 2.9377 | 6.8441 | 4.8753 | 13.2415 | 15.2103 | 22.0545 | 26.9298 | 5.3766 | 7.8649 | 1.9792 | 1.9688 | 2.8961 | 2.9377 | 6.8441 | 4.8853 | 13.2415 | 15.2103 | 22.0545 | 26.9398 | 0.01
-3.2425 | 5.9975 | 1.6919 | 1.5379 | 1.4596 | 2.0758 | 4.6894 | 3.1515 | 2.755 | 4.2928 | 8.9822 | 12.1337 | -3.2425 | 5.9975 | 1.6919 | 1.5379 | 1.4596 | 2.0758 | 4.6894 | 3.1615 | 2.755 | 4.2928 | 8.9822 | 12.1437 | 0.01
5.784 | 7.9532 | 1.9928 | 1.9892 | 2.964 | 2.9784 | 6.946 | 4.9568 | 13.7372 | 15.7264 | 22.6724 | 27.6292 | 5.784 | 7.9532 | 1.9928 | 1.9892 | 2.964 | 2.9784 | 6.946 | 4.9668 | 13.7372 | 15.7264 | 22.6724 | 27.6392 | 0.01
0.62392 | 6.8352 | 1.8208 | 1.7312 | 2.104 | 2.4624 | 5.656 | 3.9248 | 7.4591 | 9.1903 | 14.8463 | 18.7711 | 0.62392 | 6.8352 | 1.8208 | 1.7312 | 2.104 | 2.4624 | 5.656 | 3.9348 | 7.4591 | 9.1903 | 14.8463 | 18.7811 | 0.01
3.8817 | 7.541 | 1.9294 | 1.8941 | 2.6469 | 2.7882 | 6.4704 | 4.5763 | 11.4227 | 13.3168 | 19.7872 | 24.3636 | 3.8817 | 7.541 | 1.9294 | 1.8941 | 2.6469 | 2.7882 | 6.4704 | 4.5863 | 11.4227 | 13.3168 | 19.7872 | 24.3736 | 0.01
6.7592 | 8.1645 | 2.0253 | 2.038 | 3.1265 | 3.0759 | 7.1898 | 5.1518 | 14.9237 | 16.9617 | 24.1515 | 29.3033 | 6.7592 | 8.1645 | 2.0253 | 2.038 | 3.1265 | 3.0759 | 7.1898 | 5.1618 | 14.9237 | 16.9617 | 24.1515 | 29.3133 | 0.01
8.4274 | 8.5259 | 2.0809 | 2.1214 | 3.4046 | 3.2427 | 7.6069 | 5.4855 | 16.9534 | 19.0748 | 26.6816 | 32.1671 | 8.4274 | 8.5259 | 2.0809 | 2.1214 | 3.4046 | 3.2427 | 7.6069 | 5.4955 | 16.9534 | 19.0748 | 26.6816 | 32.1771 | 0.01
16.2512 | 10.2211 | 2.3417 | 2.5126 | 4.7085 | 4.0251 | 9.5628 | 7.0502 | 26.4722 | 28.9848 | 38.5476 | 45.5978 | 16.2512 | 10.2211 | 2.3417 | 2.5126 | 4.7085 | 4.0251 | 9.5628 | 7.0602 | 26.4722 | 28.9848 | 38.5476 | 45.6078 | 0.01
3.9702 | 7.5602 | 1.9323 | 1.8985 | 2.6617 | 2.797 | 6.4925 | 4.594 | 11.5304 | 13.4289 | 19.9214 | 24.5155 | 3.9702 | 7.5602 | 1.9323 | 1.8985 | 2.6617 | 2.797 | 6.4925 | 4.604 | 11.5304 | 13.4289 | 19.9214 | 24.5255 | 0.01
9.1031 | 8.6723 | 2.1034 | 2.1552 | 3.5172 | 3.3103 | 7.7758 | 5.6206 | 17.7754 | 19.9305 | 27.7063 | 33.3269 | 9.1031 | 8.6723 | 2.1034 | 2.1552 | 3.5172 | 3.3103 | 7.7758 | 5.6306 | 17.7754 | 19.9305 | 27.7063 | 33.3369 | 0.01
7.6437 | 8.3561 | 2.0548 | 2.0822 | 3.2739 | 3.1644 | 7.4109 | 5.3287 | 15.9998 | 18.082 | 25.4929 | 30.8217 | 7.6437 | 8.3561 | 2.0548 | 2.0822 | 3.2739 | 3.1644 | 7.4109 | 5.3387 | 15.9998 | 18.082 | 25.4929 | 30.8317 | 0.01
7.4801 | 8.3207 | 2.0493 | 2.074 | 3.2467 | 3.148 | 7.37 | 5.296 | 15.8008 | 17.8748 | 25.2449 | 30.5409 | 7.4801 | 8.3207 | 2.0493 | 2.074 | 3.2467 | 3.148 | 7.37 | 5.306 | 15.8008 | 17.8748 | 25.2449 | 30.5509 | 0.01
15.1289 | 9.9779 | 2.3043 | 2.4564 | 4.5215 | 3.9129 | 9.2822 | 6.8258 | 25.1068 | 27.5633 | 36.8455 | 43.6713 | 15.1289 | 9.9779 | 2.3043 | 2.4564 | 4.5215 | 3.9129 | 9.2822 | 6.8358 | 25.1068 | 27.5633 | 36.8455 | 43.6813 | 0.01
0.75091 | 6.8627 | 1.825 | 1.7375 | 2.1252 | 2.4751 | 5.6877 | 3.9502 | 7.6136 | 9.3512 | 15.0389 | 18.9891 | 0.75091 | 6.8627 | 1.825 | 1.7375 | 2.1252 | 2.4751 | 5.6877 | 3.9602 | 7.6136 | 9.3512 | 15.0389 | 18.9991 | 0.01
1.9654 | 7.1258 | 1.8655 | 1.7983 | 2.3276 | 2.5965 | 5.9914 | 4.1931 | 9.0912 | 10.8895 | 16.8809 | 21.0739 | 1.9654 | 7.1258 | 1.8655 | 1.7983 | 2.3276 | 2.5965 | 5.9914 | 4.2031 | 9.0912 | 10.8895 | 16.8809 | 21.0839 | 0.01
9.8869 | 8.8422 | 2.1296 | 2.1943 | 3.6478 | 3.3887 | 7.9717 | 5.7774 | 18.7291 | 20.9234 | 28.8951 | 34.6725 | 9.8869 | 8.8422 | 2.1296 | 2.1943 | 3.6478 | 3.3887 | 7.9717 | 5.7874 | 18.7291 | 20.9234 | 28.8951 | 34.6825 | 0.01
6.4668 | 8.1011 | 2.0156 | 2.0233 | 3.0778 | 3.0467 | 7.1167 | 5.0934 | 14.5679 | 16.5913 | 23.708 | 28.8013 | 6.4668 | 8.1011 | 2.0156 | 2.0233 | 3.0778 | 3.0467 | 7.1167 | 5.1034 | 14.5679 | 16.5913 | 23.708 | 28.8113 | 0.01
7.8432 | 8.3994 | 2.0614 | 2.0922 | 3.3072 | 3.1843 | 7.4608 | 5.3686 | 16.2426 | 18.3348 | 25.7956 | 31.1642 | 7.8432 | 8.3994 | 2.0614 | 2.0922 | 3.3072 | 3.1843 | 7.4608 | 5.3786 | 16.2426 | 18.3348 | 25.7956 | 31.1742 | 0.01
3.9091 | 7.547 | 1.9303 | 1.8955 | 2.6515 | 2.7909 | 6.4773 | 4.5818 | 11.456 | 13.3515 | 19.8288 | 24.4106 | 3.9091 | 7.547 | 1.9303 | 1.8955 | 2.6515 | 2.7909 | 6.4773 | 4.5918 | 11.456 | 13.3515 | 19.8288 | 24.4206 | 0.01
3.4369 | 7.4447 | 1.9146 | 1.8718 | 2.5728 | 2.7437 | 6.3592 | 4.4874 | 10.8815 | 12.7533 | 19.1126 | 23.5999 | 3.4369 | 7.4447 | 1.9146 | 1.8718 | 2.5728 | 2.7437 | 6.3592 | 4.4974 | 10.8815 | 12.7533 | 19.1126 | 23.6099 | 0.01
16.7592 | 10.3312 | 2.3586 | 2.538 | 4.7932 | 4.0759 | 9.6898 | 7.1518 | 27.0903 | 29.6283 | 39.3181 | 46.4699 | 16.7592 | 10.3312 | 2.3586 | 2.538 | 4.7932 | 4.0759 | 9.6898 | 7.1618 | 27.0903 | 29.6283 | 39.3181 | 46.4799 | 0.01
-4.8476 | 5.6497 | 1.6384 | 1.4576 | 1.1921 | 1.9152 | 4.2881 | 2.8305 | 0.80204 | 2.2597 | 6.5478 | 9.3782 | -4.8476 | 5.6497 | 1.6384 | 1.4576 | 1.1921 | 1.9152 | 4.2881 | 2.8405 | 0.80204 | 2.2597 | 6.5478 | 9.3882 | 0.01
4.8571 | 7.7524 | 1.9619 | 1.9429 | 2.8095 | 2.8857 | 6.7143 | 4.7714 | 12.6094 | 14.5523 | 21.2665 | 26.038 | 4.8571 | 7.7524 | 1.9619 | 1.9429 | 2.8095 | 2.8857 | 6.7143 | 4.7814 | 12.6094 | 14.5523 | 21.2665 | 26.048 | 0.01
15.5217 | 10.063 | 2.3174 | 2.4761 | 4.587 | 3.9522 | 9.3804 | 6.9043 | 25.5847 | 28.0608 | 37.4412 | 44.3456 | 15.5217 | 10.063 | 2.3174 | 2.4761 | 4.587 | 3.9522 | 9.3804 | 6.9143 | 25.5847 | 28.0608 | 37.4412 | 44.3556 | 0.01
4.5272 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7054 | 12.2081 | 14.1344 | 20.7662 | 25.4717 | 4.5272 | 7.6809 | 1.9509 | 1.9264 | 2.7545 | 2.8527 | 6.6318 | 4.7154 | 12.2081 | 14.1344 | 20.7662 | 25.4817 | 0.01
-6.9383 | 5.1967 | 1.5687 | 1.3531 | 0.84362 | 1.7062 | 3.7654 | 2.4123 | -1.7415 | -0.38845 | 3.377 | 5.7893 | -6.9383 | 5.1967 | 1.5687 | 1.3531 | 0.84362 | 1.7062 | 3.7654 | 2.4223 | -1.7415 | -0.38845 | 3.377 | 5.7993 | 0.01
16.9328 | 10.3688 | 2.3644 | 2.5466 | 4.8221 | 4.0933 | 9.7332 | 7.1866 | 27.3016 | 29.8482 | 39.5814 | 46.768 | 16.9328 | 10.3688 | 2.3644 | 2.5466 | 4.8221 | 4.0933 | 9.7332 | 7.1966 | 27.3016 | 29.8482 | 39.5814 | 46.778 | 0.01
14.0968 | 9.7543 | 2.2699 | 2.4048 | 4.3495 | 3.8097 | 9.0242 | 6.6194 | 23.8511 | 26.2559 | 35.2801 | 41.8995 | 14.0968 | 9.7543 | 2.2699 | 2.4048 | 4.3495 | 3.8097 | 9.0242 | 6.6294 | 23.8511 | 26.2559 | 35.2801 | 41.9095 | 0.01
21.6875 | 11.399 | 2.5229 | 2.7844 | 5.6146 | 4.5687 | 10.9219 | 8.1375 | 33.0864 | 35.8708 | 46.7927 | 54.9302 | 21.6875 | 11.399 | 2.5229 | 2.7844 | 5.6146 | 4.5687 | 10.9219 | 8.1475 | 33.0864 | 35.8708 | 46.7927 | 54.9402 | 0.01
14.6441 | 9.8729 | 2.2881 | 2.4322 | 4.4407 | 3.8644 | 9.161 | 6.7288 | 24.5169 | 26.9491 | 36.1102 | 42.839 | 14.6441 | 9.8729 | 2.2881 | 2.4322 | 4.4407 | 3.8644 | 9.161 | 6.7388 | 24.5169 | 26.9491 | 36.1102 | 42.849 | 0.01
0.7403 | 6.8604 | 1.8247 | 1.737 | 2.1234 | 2.474 | 5.6851 | 3.9481 | 7.6007 | 9.3377 | 15.0228 | 18.9709 | 0.7403 | 6.8604 | 1.8247 | 1.737 | 2.1234 | 2.474 | 5.6851 | 3.9581 | 7.6007 | 9.3377 | 15.0228 | 18.9809 | 0.01
0.19334 | 6.7419 | 1.8064 | 1.7097 | 2.0322 | 2.4193 | 5.5483 | 3.8387 | 6.9352 | 8.6449 | 14.1932 | 18.0319 | 0.19334 | 6.7419 | 1.8064 | 1.7097 | 2.0322 | 2.4193 | 5.5483 | 3.8487 | 6.9352 | 8.6449 | 14.1932 | 18.0419 | 0.01
8.7563 | 8.5972 | 2.0919 | 2.1378 | 3.4594 | 3.2756 | 7.6891 | 5.5513 | 17.3534 | 19.4913 | 27.1803 | 32.7316 | 8.7563 | 8.5972 | 2.0919 | 2.1378 | 3.4594 | 3.2756 | 7.6891 | 5.5613 | 17.3534 | 19.4913 | 27.1803 | 32.7416 | 0.01
8.0989 | 8.4548 | 2.07 | 2.1049 | 3.3498 | 3.2099 | 7.5247 | 5.4198 | 16.5537 | 18.6586 | 26.1833 | 31.6031 | 8.0989 | 8.4548 | 2.07 | 2.1049 | 3.3498 | 3.2099 | 7.5247 | 5.4298 | 16.5537 | 18.6586 | 26.1833 | 31.6131 | 0.01
-3.4729 | 5.9475 | 1.6842 | 1.5264 | 1.4212 | 2.0527 | 4.6318 | 3.1054 | 2.4746 | 4.0009 | 8.6327 | 11.7381 | -3.4729 | 5.9475 | 1.6842 | 1.5264 | 1.4212 | 2.0527 | 4.6318 | 3.1154 | 2.4746 | 4.0009 | 8.6327 | 11.7481 | 0.01
0.19703 | 6.7427 | 1.8066 | 1.7099 | 2.0328 | 2.4197 | 5.5493 | 3.8394 | 6.9397 | 8.6496 | 14.1988 | 18.0382 | 0.19703 | 6.7427 | 1.8066 | 1.7099 | 2.0328 | 2.4197 | 5.5493 | 3.8494 | 6.9397 | 8.6496 | 14.1988 | 18.0482 | 0.01
2.1437 | 7.1645 | 1.8715 | 1.8072 | 2.3573 | 2.6144 | 6.0359 | 4.2287 | 9.3082 | 11.1154 | 17.1513 | 21.38 | 2.1437 | 7.1645 | 1.8715 | 1.8072 | 2.3573 | 2.6144 | 6.0359 | 4.2387 | 9.3082 | 11.1154 | 17.1513 | 21.39 | 0.01
2.1804 | 7.1724 | 1.8727 | 1.809 | 2.3634 | 2.618 | 6.0451 | 4.2361 | 9.3528 | 11.1618 | 17.2069 | 21.443 | 2.1804 | 7.1724 | 1.8727 | 1.809 | 2.3634 | 2.618 | 6.0451 | 4.2461 | 9.3528 | 11.1618 | 17.2069 | 21.453 | 0.01
8.4919 | 8.5399 | 2.0831 | 2.1246 | 3.4153 | 3.2492 | 7.623 | 5.4984 | 17.0318 | 19.1564 | 26.7793 | 32.2777 | 8.4919 | 8.5399 | 2.0831 | 2.1246 | 3.4153 | 3.2492 | 7.623 | 5.5084 | 17.0318 | 19.1564 | 26.7793 | 32.2877 | 0.01
-0.30742 | 6.6334 | 1.7898 | 1.6846 | 1.9488 | 2.3693 | 5.4231 | 3.7385 | 6.326 | 8.0106 | 13.4337 | 17.1723 | -0.30742 | 6.6334 | 1.7898 | 1.6846 | 1.9488 | 2.3693 | 5.4231 | 3.7485 | 6.326 | 8.0106 | 13.4337 | 17.1823 | 0.01
5.7009 | 7.9352 | 1.99 | 1.985 | 2.9501 | 2.9701 | 6.9252 | 4.9402 | 13.6361 | 15.6211 | 22.5463 | 27.4865 | 5.7009 | 7.9352 | 1.99 | 1.985 | 2.9501 | 2.9701 | 6.9252 | 4.9502 | 13.6361 | 15.6211 | 22.5463 | 27.4965 | 0.01
3.9954 | 7.5657 | 1.9332 | 1.8998 | 2.6659 | 2.7995 | 6.4988 | 4.5991 | 11.561 | 13.4608 | 19.9596 | 24.5587 | 3.9954 | 7.5657 | 1.9332 | 1.8998 | 2.6659 | 2.7995 | 6.4988 | 4.6091 | 11.561 | 13.4608 | 19.9596 | 24.5687 | 0.01
2.8736 | 7.3226 | 1.8958 | 1.8437 | 2.4789 | 2.6874 | 6.2184 | 4.3747 | 10.1962 | 12.0399 | 18.2583 | 22.633 | 2.8736 | 7.3226 | 1.8958 | 1.8437 | 2.4789 | 2.6874 | 6.2184 | 4.3847 | 10.1962 | 12.0399 | 18.2583 | 22.643 | 0.01
7.4078 | 8.305 | 2.0469 | 2.0704 | 3.2346 | 3.1408 | 7.352 | 5.2816 | 15.7128 | 17.7832 | 25.1352 | 30.4167 | 7.4078 | 8.305 | 2.0469 | 2.0704 | 3.2346 | 3.1408 | 7.352 | 5.2916 | 15.7128 | 17.7832 | 25.1352 | 30.4267 | 0.01
4.6413 | 7.7056 | 1.9547 | 1.9321 | 2.7735 | 2.8641 | 6.6603 | 4.7283 | 12.3469 | 14.2789 | 20.9392 | 25.6675 | 4.6413 | 7.7056 | 1.9547 | 1.9321 | 2.7735 | 2.8641 | 6.6603 | 4.7383 | 12.3469 | 14.2789 | 20.9392 | 25.6775 | 0.01
17.8399 | 10.5653 | 2.3947 | 2.592 | 4.9733 | 4.184 | 9.96 | 7.368 | 28.4052 | 30.9972 | 40.9571 | 48.3251 | 17.8399 | 10.5653 | 2.3947 | 2.592 | 4.9733 | 4.184 | 9.96 | 7.378 | 28.4052 | 30.9972 | 40.9571 | 48.3351 | 0.01
10.3126 | 8.9344 | 2.1438 | 2.2156 | 3.7188 | 3.4313 | 8.0782 | 5.8625 | 19.2471 | 21.4627 | 29.5409 | 35.4034 | 10.3126 | 8.9344 | 2.1438 | 2.2156 | 3.7188 | 3.4313 | 8.0782 | 5.8725 | 19.2471 | 21.4627 | 29.5409 | 35.4134 | 0.01
0.93636 | 6.9029 | 1.8312 | 1.7468 | 2.1561 | 2.4936 | 5.7341 | 3.9873 | 7.8392 | 9.5861 | 15.3201 | 19.3074 | 0.93636 | 6.9029 | 1.8312 | 1.7468 | 2.1561 | 2.4936 | 5.7341 | 3.9973 | 7.8392 | 9.5861 | 15.3201 | 19.3174 | 0.01
5.9171 | 7.982 | 1.9972 | 1.9959 | 2.9862 | 2.9917 | 6.9793 | 4.9834 | 13.8992 | 15.8951 | 22.8743 | 27.8578 | 5.9171 | 7.982 | 1.9972 | 1.9959 | 2.9862 | 2.9917 | 6.9793 | 4.9934 | 13.8992 | 15.8951 | 22.8743 | 27.8678 | 0.01
14.2609 | 9.7899 | 2.2754 | 2.413 | 4.3768 | 3.8261 | 9.0652 | 6.6522 | 24.0507 | 26.4638 | 35.529 | 42.1812 | 14.2609 | 9.7899 | 2.2754 | 2.413 | 4.3768 | 3.8261 | 9.0652 | 6.6622 | 24.0507 | 26.4638 | 35.529 | 42.1912 | 0.01
4.7586 | 7.731 | 1.9586 | 1.9379 | 2.7931 | 2.8759 | 6.6897 | 4.7517 | 12.4897 | 14.4276 | 21.1173 | 25.869 | 4.7586 | 7.731 | 1.9586 | 1.9379 | 2.7931 | 2.8759 | 6.6897 | 4.7617 | 12.4897 | 14.4276 | 21.1173 | 25.879 | 0.01
-1.5358 | 6.3672 | 1.7488 | 1.6232 | 1.744 | 2.2464 | 5.116 | 3.4928 | 4.8314 | 6.4546 | 11.5707 | 15.0635 | -1.5358 | 6.3672 | 1.7488 | 1.6232 | 1.744 | 2.2464 | 5.116 | 3.5028 | 4.8314 | 6.4546 | 11.5707 | 15.0735 | 0.01
4.5187 | 7.6791 | 1.9506 | 1.9259 | 2.7531 | 2.8519 | 6.6297 | 4.7037 | 12.1977 | 14.1237 | 20.7534 | 25.4571 | 4.5187 | 7.6791 | 1.9506 | 1.9259 | 2.7531 | 2.8519 | 6.6297 | 4.7137 | 12.1977 | 14.1237 | 20.7534 | 25.4671 | 0.01
10.9318 | 9.0686 | 2.1644 | 2.2466 | 3.822 | 3.4932 | 8.233 | 5.9864 | 20.0004 | 22.247 | 30.4799 | 36.4663 | 10.9318 | 9.0686 | 2.1644 | 2.2466 | 3.822 | 3.4932 | 8.233 | 5.9964 | 20.0004 | 22.247 | 30.4799 | 36.4763 | 0.01
3.7619 | 7.5151 | 1.9254 | 1.8881 | 2.627 | 2.7762 | 6.4405 | 4.5524 | 11.2769 | 13.165 | 19.6055 | 24.1579 | 3.7619 | 7.5151 | 1.9254 | 1.8881 | 2.627 | 2.7762 | 6.4405 | 4.5624 | 11.2769 | 13.165 | 19.6055 | 24.1679 | 0.01
0.66962 | 6.8451 | 1.8223 | 1.7335 | 2.1116 | 2.467 | 5.6674 | 3.9339 | 7.5147 | 9.2482 | 14.9156 | 18.8495 | 0.66962 | 6.8451 | 1.8223 | 1.7335 | 2.1116 | 2.467 | 5.6674 | 3.9439 | 7.5147 | 9.2482 | 14.9156 | 18.8595 | 0.01
8.4453 | 8.5298 | 2.0815 | 2.1223 | 3.4076 | 3.2445 | 7.6113 | 5.4891 | 16.9752 | 19.0974 | 26.7088 | 32.1978 | 8.4453 | 8.5298 | 2.0815 | 2.1223 | 3.4076 | 3.2445 | 7.6113 | 5.4991 | 16.9752 | 19.0974 | 26.7088 | 32.2078 | 0.01
4 | 7.5667 | 1.9333 | 1.9 | 2.6667 | 2.8 | 6.5 | 4.6 | 11.5666 | 13.4666 | 19.9666 | 24.5666 | 4 | 7.5667 | 1.9333 | 1.9 | 2.6667 | 2.8 | 6.5 | 4.61 | 11.5666 | 13.4666 | 19.9666 | 24.5766 | 0.01
0.11313 | 6.7245 | 1.8038 | 1.7057 | 2.0189 | 2.4113 | 5.5283 | 3.8226 | 6.8376 | 8.5433 | 14.0716 | 17.8942 | 0.11313 | 6.7245 | 1.8038 | 1.7057 | 2.0189 | 2.4113 | 5.5283 | 3.8326 | 6.8376 | 8.5433 | 14.0716 | 17.9042 | 0.01
14.3302 | 9.8049 | 2.2777 | 2.4165 | 4.3884 | 3.833 | 9.0825 | 6.666 | 24.135 | 26.5516 | 35.6341 | 42.3001 | 14.3302 | 9.8049 | 2.2777 | 2.4165 | 4.3884 | 3.833 | 9.0825 | 6.676 | 24.135 | 26.5516 | 35.6341 | 42.3101 | 0.01
0.82956 | 6.8797 | 1.8277 | 1.7415 | 2.1383 | 2.483 | 5.7074 | 3.9659 | 7.7093 | 9.4508 | 15.1582 | 19.1241 | 0.82956 | 6.8797 | 1.8277 | 1.7415 | 2.1383 | 2.483 | 5.7074 | 3.9759 | 7.7093 | 9.4508 | 15.1582 | 19.1341 | 0.01
6.5365 | 8.1162 | 2.0179 | 2.0268 | 3.0894 | 3.0537 | 7.1341 | 5.1073 | 14.6528 | 16.6796 | 23.8137 | 28.921 | 6.5365 | 8.1162 | 2.0179 | 2.0268 | 3.0894 | 3.0537 | 7.1341 | 5.1173 | 14.6528 | 16.6796 | 23.8137 | 28.931 | 0.01
2.4857 | 7.2386 | 1.8829 | 1.8243 | 2.4143 | 2.6486 | 6.1214 | 4.2971 | 9.7243 | 11.5486 | 17.67 | 21.9671 | 2.4857 | 7.2386 | 1.8829 | 1.8243 | 2.4143 | 2.6486 | 6.1214 | 4.3071 | 9.7243 | 11.5486 | 17.67 | 21.9771 | 0.01
9.4618 | 8.7501 | 2.1154 | 2.1731 | 3.577 | 3.3462 | 7.8655 | 5.6924 | 18.2119 | 20.385 | 28.2504 | 33.9428 | 9.4618 | 8.7501 | 2.1154 | 2.1731 | 3.577 | 3.3462 | 7.8655 | 5.7024 | 18.2119 | 20.385 | 28.2504 | 33.9528 | 0.01
10.5152 | 8.9783 | 2.1505 | 2.2258 | 3.7525 | 3.4515 | 8.1288 | 5.903 | 19.4935 | 21.7193 | 29.8481 | 35.7511 | 10.5152 | 8.9783 | 2.1505 | 2.2258 | 3.7525 | 3.4515 | 8.1288 | 5.913 | 19.4935 | 21.7193 | 29.8481 | 35.7611 | 0.01
13.8852 | 9.7085 | 2.2628 | 2.3943 | 4.3142 | 3.7885 | 8.9713 | 6.577 | 23.5937 | 25.9879 | 34.9592 | 41.5363 | 13.8852 | 9.7085 | 2.2628 | 2.3943 | 4.3142 | 3.7885 | 8.9713 | 6.587 | 23.5937 | 25.9879 | 34.9592 | 41.5463 | 0.01
7.4114 | 8.3058 | 2.047 | 2.0706 | 3.2352 | 3.1411 | 7.3529 | 5.2823 | 15.7172 | 17.7878 | 25.1406 | 30.4229 | 7.4114 | 8.3058 | 2.047 | 2.0706 | 3.2352 | 3.1411 | 7.3529 | 5.2923 | 15.7172 | 17.7878 | 25.1406 | 30.4329 | 0.01
3.3173 | 7.4187 | 1.9106 | 1.8659 | 2.5529 | 2.7317 | 6.3293 | 4.4635 | 10.736 | 12.6019 | 18.9312 | 23.3947 | 3.3173 | 7.4187 | 1.9106 | 1.8659 | 2.5529 | 2.7317 | 6.3293 | 4.4735 | 10.736 | 12.6019 | 18.9312 | 23.4047 | 0.01
6.514 | 8.1114 | 2.0171 | 2.0257 | 3.0857 | 3.0514 | 7.1285 | 5.1028 | 14.6253 | 16.651 | 23.7795 | 28.8823 | 6.514 | 8.1114 | 2.0171 | 2.0257 | 3.0857 | 3.0514 | 7.1285 | 5.1128 | 14.6253 | 16.651 | 23.7795 | 28.8923 | 0.01
-0.5379 | 6.5835 | 1.7821 | 1.6731 | 1.9104 | 2.3462 | 5.3655 | 3.6924 | 6.0456 | 7.7187 | 13.0842 | 16.7766 | -0.5379 | 6.5835 | 1.7821 | 1.6731 | 1.9104 | 2.3462 | 5.3655 | 3.7024 | 6.0456 | 7.7187 | 13.0842 | 16.7866 | 0.01
1.9903 | 7.1312 | 1.8663 | 1.7995 | 2.3317 | 2.599 | 5.9976 | 4.1981 | 9.1215 | 10.9211 | 16.9186 | 21.1167 | 1.9903 | 7.1312 | 1.8663 | 1.7995 | 2.3317 | 2.599 | 5.9976 | 4.2081 | 9.1215 | 10.9211 | 16.9186 | 21.1267 | 0.01
17.5171 | 10.4954 | 2.3839 | 2.5759 | 4.9195 | 4.1517 | 9.8793 | 7.3034 | 28.0125 | 30.5883 | 40.4676 | 47.771 | 17.5171 | 10.4954 | 2.3839 | 2.5759 | 4.9195 | 4.1517 | 9.8793 | 7.3134 | 28.0125 | 30.5883 | 40.4676 | 47.781 | 0.01
5.7762 | 7.9515 | 1.9925 | 1.9888 | 2.9627 | 2.9776 | 6.9441 | 4.9552 | 13.7277 | 15.7166 | 22.6606 | 27.6159 | 5.7762 | 7.9515 | 1.9925 | 1.9888 | 2.9627 | 2.9776 | 6.9441 | 4.9652 | 13.7277 | 15.7166 | 22.6606 | 27.6259 | 0.01
5.936 | 7.9861 | 1.9979 | 1.9968 | 2.9893 | 2.9936 | 6.984 | 4.9872 | 13.9222 | 15.919 | 22.903 | 27.8902 | 5.936 | 7.9861 | 1.9979 | 1.9968 | 2.9893 | 2.9936 | 6.984 | 4.9972 | 13.9222 | 15.919 | 22.903 | 27.9002 | 0.01
-4.9884 | 5.6192 | 1.6337 | 1.4506 | 1.1686 | 1.9012 | 4.2529 | 2.8023 | 0.63082 | 2.0814 | 6.3343 | 9.1366 | -4.9884 | 5.6192 | 1.6337 | 1.4506 | 1.1686 | 1.9012 | 4.2529 | 2.8123 | 0.63082 | 2.0814 | 6.3343 | 9.1466 | 0.01
4.2438 | 7.6195 | 1.9415 | 1.9122 | 2.7073 | 2.8244 | 6.561 | 4.6488 | 11.8633 | 13.7755 | 20.3365 | 24.9852 | 4.2438 | 7.6195 | 1.9415 | 1.9122 | 2.7073 | 2.8244 | 6.561 | 4.6588 | 11.8633 | 13.7755 | 20.3365 | 24.9952 | 0.01
8.0514 | 8.4445 | 2.0684 | 2.1026 | 3.3419 | 3.2051 | 7.5128 | 5.4103 | 16.4958 | 18.5984 | 26.1112 | 31.5215 | 8.0514 | 8.4445 | 2.0684 | 2.1026 | 3.3419 | 3.2051 | 7.5128 | 5.4203 | 16.4958 | 18.5984 | 26.1112 | 31.5315 | 0.01
-8.3684 | 4.8868 | 1.5211 | 1.2816 | 0.60526 | 1.5632 | 3.4079 | 2.1263 | -3.4816 | -2.2 | 1.2079 | 3.3342 | -8.3684 | 4.8868 | 1.5211 | 1.2816 | 0.60526 | 1.5632 | 3.4079 | 2.1363 | -3.4816 | -2.2 | 1.2079 | 3.3442 | 0.01
10.4473 | 8.9636 | 2.1482 | 2.2224 | 3.7412 | 3.4447 | 8.1118 | 5.8895 | 19.4109 | 21.6333 | 29.7451 | 35.6346 | 10.4473 | 8.9636 | 2.1482 | 2.2224 | 3.7412 | 3.4447 | 8.1118 | 5.8995 | 19.4109 | 21.6333 | 29.7451 | 35.6446 | 0.01
6.2781 | 8.0603 | 2.0093 | 2.0139 | 3.0463 | 3.0278 | 7.0695 | 5.0556 | 14.3383 | 16.3522 | 23.4218 | 28.4774 | 6.2781 | 8.0603 | 2.0093 | 2.0139 | 3.0463 | 3.0278 | 7.0695 | 5.0656 | 14.3383 | 16.3522 | 23.4218 | 28.4874 | 0.01
-0.026116 | 6.6943 | 1.7991 | 1.6987 | 1.9956 | 2.3974 | 5.4935 | 3.7948 | 6.6682 | 8.3669 | 13.8604 | 17.6552 | -0.026116 | 6.6943 | 1.7991 | 1.6987 | 1.9956 | 2.3974 | 5.4935 | 3.8048 | 6.6682 | 8.3669 | 13.8604 | 17.6652 | 0.01
12.3808 | 9.3825 | 2.2127 | 2.319 | 4.0635 | 3.6381 | 8.5952 | 6.2762 | 21.7633 | 24.0823 | 32.6775 | 38.9537 | 12.3808 | 9.3825 | 2.2127 | 2.319 | 4.0635 | 3.6381 | 8.5952 | 6.2862 | 21.7633 | 24.0823 | 32.6775 | 38.9637 | 0.01
4.3092 | 7.6337 | 1.9436 | 1.9155 | 2.7182 | 2.8309 | 6.5773 | 4.6618 | 11.9428 | 13.8583 | 20.4356 | 25.0974 | 4.3092 | 7.6337 | 1.9436 | 1.9155 | 2.7182 | 2.8309 | 6.5773 | 4.6718 | 11.9428 | 13.8583 | 20.4356 | 25.1074 | 0.01
9.5463 | 8.7684 | 2.1182 | 2.1773 | 3.591 | 3.3546 | 7.8866 | 5.7093 | 18.3146 | 20.492 | 28.3785 | 34.0878 | 9.5463 | 8.7684 | 2.1182 | 2.1773 | 3.591 | 3.3546 | 7.8866 | 5.7193 | 18.3146 | 20.492 | 28.3785 | 34.0978 | 0.01
3.7633 | 7.5154 | 1.9254 | 1.8882 | 2.6272 | 2.7763 | 6.4408 | 4.5527 | 11.2787 | 13.1668 | 19.6077 | 24.1603 | 3.7633 | 7.5154 | 1.9254 | 1.8882 | 2.6272 | 2.7763 | 6.4408 | 4.5627 | 11.2787 | 13.1668 | 19.6077 | 24.1703 | 0.01
8.7658 | 8.5992 | 2.0922 | 2.1383 | 3.461 | 3.2766 | 7.6914 | 5.5532 | 17.365 | 19.5033 | 27.1947 | 32.7479 | 8.7658 | 8.5992 | 2.0922 | 2.1383 | 3.461 | 3.2766 | 7.6914 | 5.5632 | 17.365 | 19.5033 | 27.1947 | 32.7579 | 0.01
0.69767 | 6.8512 | 1.8233 | 1.7349 | 2.1163 | 2.4698 | 5.6744 | 3.9395 | 7.5488 | 9.2837 | 14.9581 | 18.8977 | 0.69767 | 6.8512 | 1.8233 | 1.7349 | 2.1163 | 2.4698 | 5.6744 | 3.9495 | 7.5488 | 9.2837 | 14.9581 | 18.9077 | 0.01
11.5977 | 9.2128 | 2.1866 | 2.2799 | 3.9329 | 3.5598 | 8.3994 | 6.1195 | 20.8105 | 23.0904 | 31.4898 | 37.6094 | 11.5977 | 9.2128 | 2.1866 | 2.2799 | 3.9329 | 3.5598 | 8.3994 | 6.1295 | 20.8105 | 23.0904 | 31.4898 | 37.6194 | 0.01
8.4712 | 8.5354 | 2.0824 | 2.1236 | 3.4119 | 3.2471 | 7.6178 | 5.4942 | 17.0067 | 19.1302 | 26.748 | 32.2423 | 8.4712 | 8.5354 | 2.0824 | 2.1236 | 3.4119 | 3.2471 | 7.6178 | 5.5042 | 17.0067 | 19.1302 | 26.748 | 32.2523 | 0.01
18.2142 | 10.6464 | 2.4071 | 2.6107 | 5.0357 | 4.2214 | 10.0536 | 7.4428 | 28.8606 | 31.4713 | 41.5249 | 48.9677 | 18.2142 | 10.6464 | 2.4071 | 2.6107 | 5.0357 | 4.2214 | 10.0536 | 7.4528 | 28.8606 | 31.4713 | 41.5249 | 48.9777 | 0.01
13.8999 | 9.7117 | 2.2633 | 2.395 | 4.3167 | 3.79 | 8.975 | 6.58 | 23.6116 | 26.0066 | 34.9816 | 41.5615 | 13.8999 | 9.7117 | 2.2633 | 2.395 | 4.3167 | 3.79 | 8.975 | 6.59 | 23.6116 | 26.0066 | 34.9816 | 41.5715 | 0.01
6.3636 | 8.0788 | 2.0121 | 2.0182 | 3.0606 | 3.0364 | 7.0909 | 5.0727 | 14.4424 | 16.4605 | 23.5514 | 28.6242 | 6.3636 | 8.0788 | 2.0121 | 2.0182 | 3.0606 | 3.0364 | 7.0909 | 5.0827 | 14.4424 | 16.4605 | 23.5514 | 28.6342 | 0.01
6.9097 | 8.1971 | 2.0303 | 2.0455 | 3.1516 | 3.091 | 7.2274 | 5.1819 | 15.1068 | 17.1523 | 24.3797 | 29.5616 | 6.9097 | 8.1971 | 2.0303 | 2.0455 | 3.1516 | 3.091 | 7.2274 | 5.1919 | 15.1068 | 17.1523 | 24.3797 | 29.5716 | 0.01
1.1273 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7818 | 4.0255 | 8.0716 | 9.8279 | 15.6098 | 19.6352 | 1.1273 | 6.9443 | 1.8376 | 1.7564 | 2.1879 | 2.5127 | 5.7818 | 4.0355 | 8.0716 | 9.8279 | 15.6098 | 19.6452 | 0.01
15.8964 | 10.1442 | 2.3299 | 2.4948 | 4.6494 | 3.9896 | 9.4741 | 6.9793 | 26.0407 | 28.5355 | 38.0096 | 44.9889 | 15.8964 | 10.1442 | 2.3299 | 2.4948 | 4.6494 | 3.9896 | 9.4741 | 6.9893 | 26.0407 | 28.5355 | 38.0096 | 44.9989 | 0.01
6.1089 | 8.0236 | 2.0036 | 2.0054 | 3.0181 | 3.0109 | 7.0272 | 5.0218 | 14.1325 | 16.1379 | 23.1651 | 28.1869 | 6.1089 | 8.0236 | 2.0036 | 2.0054 | 3.0181 | 3.0109 | 7.0272 | 5.0318 | 14.1325 | 16.1379 | 23.1651 | 28.1969 | 0.01
0.25643 | 6.7556 | 1.8085 | 1.7128 | 2.0427 | 2.4256 | 5.5641 | 3.8513 | 7.012 | 8.7248 | 14.2889 | 18.1402 | 0.25643 | 6.7556 | 1.8085 | 1.7128 | 2.0427 | 2.4256 | 5.5641 | 3.8613 | 7.012 | 8.7248 | 14.2889 | 18.1502 | 0.01
-4.2332 | 5.7828 | 1.6589 | 1.4883 | 1.2945 | 1.9767 | 4.4417 | 2.9534 | 1.5496 | 3.038 | 7.4797 | 10.433 | -4.2332 | 5.7828 | 1.6589 | 1.4883 | 1.2945 | 1.9767 | 4.4417 | 2.9634 | 1.5496 | 3.038 | 7.4797 | 10.443 | 0.01
3.0006 | 7.3501 | 1.9 | 1.85 | 2.5001 | 2.7001 | 6.2501 | 4.4001 | 10.3507 | 12.2007 | 18.4509 | 22.851 | 3.0006 | 7.3501 | 1.9 | 1.85 | 2.5001 | 2.7001 | 6.2501 | 4.4101 | 10.3507 | 12.2007 | 18.4509 | 22.861 | 0.01
-0.019623 | 6.6957 | 1.7993 | 1.699 | 1.9967 | 2.398 | 5.4951 | 3.7961 | 6.6761 | 8.3751 | 13.8702 | 17.6663 | -0.019623 | 6.6957 | 1.7993 | 1.699 | 1.9967 | 2.398 | 5.4951 | 3.8061 | 6.6761 | 8.3751 | 13.8702 | 17.6763 | 0.01
1.7234 | 7.0734 | 1.8574 | 1.7862 | 2.2872 | 2.5723 | 5.9308 | 4.1447 | 8.7968 | 10.583 | 16.5138 | 20.6585 | 1.7234 | 7.0734 | 1.8574 | 1.7862 | 2.2872 | 2.5723 | 5.9308 | 4.1547 | 8.7968 | 10.583 | 16.5138 | 20.6685 | 0.01
17.9337 | 10.5856 | 2.3978 | 2.5967 | 4.9889 | 4.1934 | 9.9834 | 7.3867 | 28.5193 | 31.116 | 41.0994 | 48.4862 | 17.9337 | 10.5856 | 2.3978 | 2.5967 | 4.9889 | 4.1934 | 9.9834 | 7.3967 | 28.5193 | 31.116 | 41.0994 | 48.4962 | 0.01
5.9536 | 7.9899 | 1.9985 | 1.9977 | 2.9923 | 2.9954 | 6.9884 | 4.9907 | 13.9435 | 15.9412 | 22.9296 | 27.9203 | 5.9536 | 7.9899 | 1.9985 | 1.9977 | 2.9923 | 2.9954 | 6.9884 | 5.0007 | 13.9435 | 15.9412 | 22.9296 | 27.9303 | 0.01
8.1286 | 8.4612 | 2.071 | 2.1064 | 3.3548 | 3.2129 | 7.5321 | 5.4257 | 16.5897 | 18.6962 | 26.2283 | 31.654 | 8.1286 | 8.4612 | 2.071 | 2.1064 | 3.3548 | 3.2129 | 7.5321 | 5.4357 | 16.5897 | 18.6962 | 26.2283 | 31.664 | 0.01
0.99013 | 6.9145 | 1.833 | 1.7495 | 2.165 | 2.499 | 5.7475 | 3.998 | 7.9047 | 9.6542 | 15.4017 | 19.3997 | 0.99013 | 6.9145 | 1.833 | 1.7495 | 2.165 | 2.499 | 5.7475 | 4.008 | 7.9047 | 9.6542 | 15.4017 | 19.4097 | 0.01
9.9327 | 8.8521 | 2.1311 | 2.1966 | 3.6554 | 3.3933 | 7.9832 | 5.7865 | 18.7847 | 20.9814 | 28.9645 | 34.7511 | 9.9327 | 8.8521 | 2.1311 | 2.1966 | 3.6554 | 3.3933 | 7.9832 | 5.7965 | 18.7847 | 20.9814 | 28.9645 | 34.7611 | 0.01
13.1113 | 9.5408 | 2.237 | 2.3556 | 4.1852 | 3.7111 | 8.7778 | 6.4223 | 22.6521 | 25.0077 | 33.7855 | 40.2078 | 13.1113 | 9.5408 | 2.237 | 2.3556 | 4.1852 | 3.7111 | 8.7778 | 6.4323 | 22.6521 | 25.0077 | 33.7855 | 40.2178 | 0.01
3.9177 | 7.5488 | 1.9306 | 1.8959 | 2.6529 | 2.7918 | 6.4794 | 4.5835 | 11.4665 | 13.3624 | 19.8418 | 24.4253 | 3.9177 | 7.5488 | 1.9306 | 1.8959 | 2.6529 | 2.7918 | 6.4794 | 4.5935 | 11.4665 | 13.3624 | 19.8418 | 24.4353 | 0.01
4.0887 | 7.5859 | 1.9363 | 1.9044 | 2.6814 | 2.8089 | 6.5222 | 4.6177 | 11.6745 | 13.579 | 20.1011 | 24.7189 | 4.0887 | 7.5859 | 1.9363 | 1.9044 | 2.6814 | 2.8089 | 6.5222 | 4.6277 | 11.6745 | 13.579 | 20.1011 | 24.7289 | 0.01
-0.055066 | 6.6881 | 1.7982 | 1.6972 | 1.9908 | 2.3945 | 5.4862 | 3.789 | 6.633 | 8.3303 | 13.8165 | 17.6055 | -0.055066 | 6.6881 | 1.7982 | 1.6972 | 1.9908 | 2.3945 | 5.4862 | 3.799 | 6.633 | 8.3303 | 13.8165 | 17.6155 | 0.01
3.9499 | 7.5558 | 1.9317 | 1.8975 | 2.6583 | 2.795 | 6.4875 | 4.59 | 11.5057 | 13.4032 | 19.8906 | 24.4806 | 3.9499 | 7.5558 | 1.9317 | 1.8975 | 2.6583 | 2.795 | 6.4875 | 4.6 | 11.5057 | 13.4032 | 19.8906 | 24.4906 | 0.01
2.5412 | 7.2506 | 1.8847 | 1.8271 | 2.4235 | 2.6541 | 6.1353 | 4.3082 | 9.7918 | 11.6189 | 17.7542 | 22.0624 | 2.5412 | 7.2506 | 1.8847 | 1.8271 | 2.4235 | 2.6541 | 6.1353 | 4.3182 | 9.7918 | 11.6189 | 17.7542 | 22.0724 | 0.01
-1.6705 | 6.3381 | 1.7443 | 1.6165 | 1.7216 | 2.233 | 5.0824 | 3.4659 | 4.6676 | 6.2841 | 11.3664 | 14.8323 | -1.6705 | 6.3381 | 1.7443 | 1.6165 | 1.7216 | 2.233 | 5.0824 | 3.4759 | 4.6676 | 6.2841 | 11.3664 | 14.8423 | 0.01
17.8938 | 10.577 | 2.3965 | 2.5947 | 4.9823 | 4.1894 | 9.9734 | 7.3788 | 28.4708 | 31.0655 | 41.0389 | 48.4177 | 17.8938 | 10.577 | 2.3965 | 2.5947 | 4.9823 | 4.1894 | 9.9734 | 7.3888 | 28.4708 | 31.0655 | 41.0389 | 48.4277 | 0.01
2.6217 | 7.268 | 1.8874 | 1.8311 | 2.4369 | 2.6622 | 6.1554 | 4.3243 | 9.8897 | 11.7208 | 17.8762 | 22.2005 | 2.6217 | 7.268 | 1.8874 | 1.8311 | 2.4369 | 2.6622 | 6.1554 | 4.3343 | 9.8897 | 11.7208 | 17.8762 | 22.2105 | 0.01
6.531 | 8.1151 | 2.0177 | 2.0266 | 3.0885 | 3.0531 | 7.1328 | 5.1062 | 14.6461 | 16.6726 | 23.8054 | 28.9116 | 6.531 | 8.1151 | 2.0177 | 2.0266 | 3.0885 | 3.0531 | 7.1328 | 5.1162 | 14.6461 | 16.6726 | 23.8054 | 28.9216 | 0.01
-0.63752 | 6.5619 | 1.7787 | 1.6681 | 1.8937 | 2.3362 | 5.3406 | 3.6725 | 5.9244 | 7.5925 | 12.9331 | 16.6056 | -0.63752 | 6.5619 | 1.7787 | 1.6681 | 1.8937 | 2.3362 | 5.3406 | 3.6825 | 5.9244 | 7.5925 | 12.9331 | 16.6156 | 0.01
3.242 | 7.4024 | 1.9081 | 1.8621 | 2.5403 | 2.7242 | 6.3105 | 4.4484 | 10.6444 | 12.5065 | 18.817 | 23.2654 | 3.242 | 7.4024 | 1.9081 | 1.8621 | 2.5403 | 2.7242 | 6.3105 | 4.4584 | 10.6444 | 12.5065 | 18.817 | 23.2754 | 0.01
7.7059 | 8.3696 | 2.0569 | 2.0853 | 3.2843 | 3.1706 | 7.4265 | 5.3412 | 16.0755 | 18.1608 | 25.5873 | 30.9285 | 7.7059 | 8.3696 | 2.0569 | 2.0853 | 3.2843 | 3.1706 | 7.4265 | 5.3512 | 16.0755 | 18.1608 | 25.5873 | 30.9385 | 0.01
5.5315 | 7.8985 | 1.9844 | 1.9766 | 2.9219 | 2.9532 | 6.8829 | 4.9063 | 13.43 | 15.4066 | 22.2895 | 27.1958 | 5.5315 | 7.8985 | 1.9844 | 1.9766 | 2.9219 | 2.9532 | 6.8829 | 4.9163 | 13.43 | 15.4066 | 22.2895 | 27.2058 | 0.01
6.2875 | 8.0623 | 2.0096 | 2.0144 | 3.0479 | 3.0288 | 7.0719 | 5.0575 | 14.3498 | 16.3642 | 23.4361 | 28.4936 | 6.2875 | 8.0623 | 2.0096 | 2.0144 | 3.0479 | 3.0288 | 7.0719 | 5.0675 | 14.3498 | 16.3642 | 23.4361 | 28.5036 | 0.01
8.8478 | 8.617 | 2.0949 | 2.1424 | 3.4746 | 3.2848 | 7.7119 | 5.5696 | 17.4648 | 19.6072 | 27.3191 | 32.8887 | 8.8478 | 8.617 | 2.0949 | 2.1424 | 3.4746 | 3.2848 | 7.7119 | 5.5796 | 17.4648 | 19.6072 | 27.3191 | 32.8987 | 0.01
3.6485 | 7.4905 | 1.9216 | 1.8824 | 2.6081 | 2.7648 | 6.4121 | 4.5297 | 11.139 | 13.0214 | 19.4335 | 23.9632 | 3.6485 | 7.4905 | 1.9216 | 1.8824 | 2.6081 | 2.7648 | 6.4121 | 4.5397 | 11.139 | 13.0214 | 19.4335 | 23.9732 | 0.01
4.5406 | 7.6838 | 1.9514 | 1.927 | 2.7568 | 2.8541 | 6.6352 | 4.7081 | 12.2244 | 14.1515 | 20.7866 | 25.4947 | 4.5406 | 7.6838 | 1.9514 | 1.927 | 2.7568 | 2.8541 | 6.6352 | 4.7181 | 12.2244 | 14.1515 | 20.7866 | 25.5047 | 0.01
7.2969 | 8.281 | 2.0432 | 2.0648 | 3.2162 | 3.1297 | 7.3242 | 5.2594 | 15.5779 | 17.6428 | 24.967 | 30.2264 | 7.2969 | 8.281 | 2.0432 | 2.0648 | 3.2162 | 3.1297 | 7.3242 | 5.2694 | 15.5779 | 17.6428 | 24.967 | 30.2364 | 0.01
7.5894 | 8.3444 | 2.053 | 2.0795 | 3.2649 | 3.1589 | 7.3974 | 5.3179 | 15.9338 | 18.0133 | 25.4106 | 30.7285 | 7.5894 | 8.3444 | 2.053 | 2.0795 | 3.2649 | 3.1589 | 7.3974 | 5.3279 | 15.9338 | 18.0133 | 25.4106 | 30.7385 | 0.01
-1.186 | 6.443 | 1.7605 | 1.6407 | 1.8023 | 2.2814 | 5.2035 | 3.5628 | 5.257 | 6.8977 | 12.1012 | 15.664 | -1.186 | 6.443 | 1.7605 | 1.6407 | 1.8023 | 2.2814 | 5.2035 | 3.5728 | 5.257 | 6.8977 | 12.1012 | 15.674 | 0.01
7.5221 | 8.3298 | 2.0507 | 2.0761 | 3.2537 | 3.1522 | 7.3805 | 5.3044 | 15.8519 | 17.928 | 25.3085 | 30.6129 | 7.5221 | 8.3298 | 2.0507 | 2.0761 | 3.2537 | 3.1522 | 7.3805 | 5.3144 | 15.8519 | 17.928 | 25.3085 | 30.6229 | 0.01
4.1728 | 7.6041 | 1.9391 | 1.9086 | 2.6955 | 2.8173 | 6.5432 | 4.6346 | 11.7769 | 13.6856 | 20.2288 | 24.8633 | 4.1728 | 7.6041 | 1.9391 | 1.9086 | 2.6955 | 2.8173 | 6.5432 | 4.6446 | 11.7769 | 13.6856 | 20.2288 | 24.8733 | 0.01
10.0312 | 8.8734 | 2.1344 | 2.2016 | 3.6719 | 3.4031 | 8.0078 | 5.8062 | 18.9047 | 21.1062 | 29.114 | 34.9203 | 10.0312 | 8.8734 | 2.1344 | 2.2016 | 3.6719 | 3.4031 | 8.0078 | 5.8162 | 18.9047 | 21.1062 | 29.114 | 34.9303 | 0.01
1.8924 | 7.11 | 1.8631 | 1.7946 | 2.3154 | 2.5892 | 5.9731 | 4.1785 | 9.0025 | 10.7971 | 16.7702 | 20.9487 | 1.8924 | 7.11 | 1.8631 | 1.7946 | 2.3154 | 2.5892 | 5.9731 | 4.1885 | 9.0025 | 10.7971 | 16.7702 | 20.9587 | 0.01
16.936 | 10.3695 | 2.3645 | 2.5468 | 4.8227 | 4.0936 | 9.734 | 7.1872 | 27.3054 | 29.8522 | 39.5862 | 46.7734 | 16.936 | 10.3695 | 2.3645 | 2.5468 | 4.8227 | 4.0936 | 9.734 | 7.1972 | 27.3054 | 29.8522 | 39.5862 | 46.7834 | 0.01
7.2675 | 8.2746 | 2.0422 | 2.0634 | 3.2112 | 3.1267 | 7.3169 | 5.2535 | 15.5421 | 17.6055 | 24.9223 | 30.1758 | 7.2675 | 8.2746 | 2.0422 | 2.0634 | 3.2112 | 3.1267 | 7.3169 | 5.2635 | 15.5421 | 17.6055 | 24.9223 | 30.1858 | 0.01
5.0004 | 7.7834 | 1.9667 | 1.95 | 2.8334 | 2.9 | 6.7501 | 4.8001 | 12.7839 | 14.7339 | 21.484 | 26.2841 | 5.0004 | 7.7834 | 1.9667 | 1.95 | 2.8334 | 2.9 | 6.7501 | 4.8101 | 12.7839 | 14.7339 | 21.484 | 26.2941 | 0.01
8.22 | 8.481 | 2.074 | 2.111 | 3.37 | 3.222 | 7.555 | 5.444 | 16.7011 | 18.8121 | 26.3671 | 31.8111 | 8.22 | 8.481 | 2.074 | 2.111 | 3.37 | 3.222 | 7.555 | 5.454 | 16.7011 | 18.8121 | 26.3671 | 31.8211 | 0.01
15.5054 | 10.0595 | 2.3168 | 2.4753 | 4.5842 | 3.9505 | 9.3763 | 6.9011 | 25.5649 | 28.0401 | 37.4165 | 44.3175 | 15.5054 | 10.0595 | 2.3168 | 2.4753 | 4.5842 | 3.9505 | 9.3763 | 6.9111 | 25.5649 | 28.0401 | 37.4165 | 44.3275 | 0.01
1.1288 | 6.9446 | 1.8376 | 1.7564 | 2.1881 | 2.5129 | 5.7822 | 4.0258 | 8.0734 | 9.8299 | 15.6121 | 19.6378 | 1.1288 | 6.9446 | 1.8376 | 1.7564 | 2.1881 | 2.5129 | 5.7822 | 4.0358 | 8.0734 | 9.8299 | 15.6121 | 19.6478 | 0.01
0.42329 | 6.7917 | 1.8141 | 1.7212 | 2.0705 | 2.4423 | 5.6058 | 3.8847 | 7.215 | 8.9362 | 14.542 | 18.4267 | 0.42329 | 6.7917 | 1.8141 | 1.7212 | 2.0705 | 2.4423 | 5.6058 | 3.8947 | 7.215 | 8.9362 | 14.542 | 18.4367 | 0.01
6.5131 | 8.1112 | 2.0171 | 2.0257 | 3.0855 | 3.0513 | 7.1283 | 5.1026 | 14.6242 | 16.6499 | 23.7781 | 28.8807 | 6.5131 | 8.1112 | 2.0171 | 2.0257 | 3.0855 | 3.0513 | 7.1283 | 5.1126 | 14.6242 | 16.6499 | 23.7781 | 28.8907 | 0.01
-0.42709 | 6.6075 | 1.7858 | 1.6786 | 1.9288 | 2.3573 | 5.3932 | 3.7146 | 6.1804 | 7.859 | 13.2522 | 16.9668 | -0.42709 | 6.6075 | 1.7858 | 1.6786 | 1.9288 | 2.3573 | 5.3932 | 3.7246 | 6.1804 | 7.859 | 13.2522 | 16.9768 | 0.01
3.3855 | 7.4335 | 1.9129 | 1.8693 | 2.5643 | 2.7386 | 6.3464 | 4.4771 | 10.8191 | 12.6883 | 19.0347 | 23.5118 | 3.3855 | 7.4335 | 1.9129 | 1.8693 | 2.5643 | 2.7386 | 6.3464 | 4.4871 | 10.8191 | 12.6883 | 19.0347 | 23.5218 | 0.01
9.2592 | 8.7062 | 2.1086 | 2.163 | 3.5432 | 3.3259 | 7.8148 | 5.6518 | 17.9653 | 20.1283 | 27.9431 | 33.5949 | 9.2592 | 8.7062 | 2.1086 | 2.163 | 3.5432 | 3.3259 | 7.8148 | 5.6618 | 17.9653 | 20.1283 | 27.9431 | 33.6049 | 0.01
0.34898 | 6.7756 | 1.8116 | 1.7174 | 2.0582 | 2.4349 | 5.5872 | 3.8698 | 7.1246 | 8.842 | 14.4293 | 18.2991 | 0.34898 | 6.7756 | 1.8116 | 1.7174 | 2.0582 | 2.4349 | 5.5872 | 3.8798 | 7.1246 | 8.842 | 14.4293 | 18.3091 | 0.01
14.8692 | 9.9217 | 2.2956 | 2.4435 | 4.4782 | 3.8869 | 9.2173 | 6.7738 | 24.7908 | 27.2343 | 36.4516 | 43.2254 | 14.8692 | 9.9217 | 2.2956 | 2.4435 | 4.4782 | 3.8869 | 9.2173 | 6.7838 | 24.7908 | 27.2343 | 36.4516 | 43.2354 | 0.01
14.2324 | 9.7837 | 2.2744 | 2.4116 | 4.3721 | 3.8232 | 9.0581 | 6.6465 | 24.0161 | 26.4277 | 35.4858 | 42.1323 | 14.2324 | 9.7837 | 2.2744 | 2.4116 | 4.3721 | 3.8232 | 9.0581 | 6.6565 | 24.0161 | 26.4277 | 35.4858 | 42.1423 | 0.01
-3.7799 | 5.881 | 1.674 | 1.511 | 1.37 | 2.022 | 4.555 | 3.044 | 2.1012 | 3.6122 | 8.1672 | 11.2112 | -3.7799 | 5.881 | 1.674 | 1.511 | 1.37 | 2.022 | 4.555 | 3.054 | 2.1012 | 3.6122 | 8.1672 | 11.2212 | 0.01
5.3413 | 7.8573 | 1.978 | 1.9671 | 2.8902 | 2.9341 | 6.8353 | 4.8683 | 13.1986 | 15.1657 | 22.001 | 26.8693 | 5.3413 | 7.8573 | 1.978 | 1.9671 | 2.8902 | 2.9341 | 6.8353 | 4.8783 | 13.1986 | 15.1657 | 22.001 | 26.8793 | 0.01
13.6643 | 9.6606 | 2.2555 | 2.3832 | 4.2774 | 3.7664 | 8.9161 | 6.5329 | 23.3249 | 25.7081 | 34.6242 | 41.157 | 13.6643 | 9.6606 | 2.2555 | 2.3832 | 4.2774 | 3.7664 | 8.9161 | 6.5429 | 23.3249 | 25.7081 | 34.6242 | 41.167 | 0.01
17.2063 | 10.428 | 2.3735 | 2.5603 | 4.8677 | 4.1206 | 9.8016 | 7.2413 | 27.6343 | 30.1946 | 39.9962 | 47.2374 | 17.2063 | 10.428 | 2.3735 | 2.5603 | 4.8677 | 4.1206 | 9.8016 | 7.2513 | 27.6343 | 30.1946 | 39.9962 | 47.2474 | 0.01
8.2493 | 8.4874 | 2.075 | 2.1125 | 3.3749 | 3.2249 | 7.5623 | 5.4499 | 16.7367 | 18.8491 | 26.4115 | 31.8613 | 8.2493 | 8.4874 | 2.075 | 2.1125 | 3.3749 | 3.2249 | 7.5623 | 5.4599 | 16.7367 | 18.8491 | 26.4115 | 31.8713 | 0.01
5.4441 | 7.8796 | 1.9815 | 1.9722 | 2.9074 | 2.9444 | 6.861 | 4.8888 | 13.3237 | 15.2959 | 22.1569 | 27.0457 | 5.4441 | 7.8796 | 1.9815 | 1.9722 | 2.9074 | 2.9444 | 6.861 | 4.8988 | 13.3237 | 15.2959 | 22.1569 | 27.0557 | 0.01
0.4585 | 6.7993 | 1.8153 | 1.7229 | 2.0764 | 2.4459 | 5.6146 | 3.8917 | 7.2578 | 8.9808 | 14.5954 | 18.4871 | 0.4585 | 6.7993 | 1.8153 | 1.7229 | 2.0764 | 2.4459 | 5.6146 | 3.9017 | 7.2578 | 8.9808 | 14.5954 | 18.4971 | 0.01
-0.038013 | 6.6918 | 1.7987 | 1.6981 | 1.9937 | 2.3962 | 5.4905 | 3.7924 | 6.6538 | 8.3519 | 13.8423 | 17.6347 | -0.038013 | 6.6918 | 1.7987 | 1.6981 | 1.9937 | 2.3962 | 5.4905 | 3.8024 | 6.6538 | 8.3519 | 13.8423 | 17.6447 | 0.01
11.8839 | 9.2749 | 2.1961 | 2.2942 | 3.9807 | 3.5884 | 8.471 | 6.1768 | 21.1588 | 23.453 | 31.924 | 38.1008 | 11.8839 | 9.2749 | 2.1961 | 2.2942 | 3.9807 | 3.5884 | 8.471 | 6.1868 | 21.1588 | 23.453 | 31.924 | 38.1108 | 0.01
-3.1106 | 6.026 | 1.6963 | 1.5445 | 1.4816 | 2.0889 | 4.7224 | 3.1779 | 2.9155 | 4.4599 | 9.1823 | 12.3602 | -3.1106 | 6.026 | 1.6963 | 1.5445 | 1.4816 | 2.0889 | 4.7224 | 3.1879 | 2.9155 | 4.4599 | 9.1823 | 12.3702 | 0.01
2.154 | 7.1667 | 1.8718 | 1.8077 | 2.359 | 2.6154 | 6.0385 | 4.2308 | 9.3207 | 11.1284 | 17.1669 | 21.3977 | 2.154 | 7.1667 | 1.8718 | 1.8077 | 2.359 | 2.6154 | 6.0385 | 4.2408 | 9.3207 | 11.1284 | 17.1669 | 21.4077 | 0.01
7.67 | 8.3618 | 2.0557 | 2.0835 | 3.2783 | 3.167 | 7.4175 | 5.334 | 16.0319 | 18.1154 | 25.5329 | 30.8669 | 7.67 | 8.3618 | 2.0557 | 2.0835 | 3.2783 | 3.167 | 7.4175 | 5.344 | 16.0319 | 18.1154 | 25.5329 | 30.8769 | 0.01
15.8604 | 10.1364 | 2.3287 | 2.493 | 4.6434 | 3.986 | 9.4651 | 6.9721 | 25.9968 | 28.4898 | 37.9549 | 44.927 | 15.8604 | 10.1364 | 2.3287 | 2.493 | 4.6434 | 3.986 | 9.4651 | 6.9821 | 25.9968 | 28.4898 | 37.9549 | 44.937 | 0.01
-1.0877 | 6.4643 | 1.7637 | 1.6456 | 1.8187 | 2.2912 | 5.2281 | 3.5825 | 5.3766 | 7.0222 | 12.2503 | 15.8327 | -1.0877 | 6.4643 | 1.7637 | 1.6456 | 1.8187 | 2.2912 | 5.2281 | 3.5925 | 5.3766 | 7.0222 | 12.2503 | 15.8427 | 0.01
9.5656 | 8.7725 | 2.1189 | 2.1783 | 3.5943 | 3.3566 | 7.8914 | 5.7131 | 18.3381 | 20.5164 | 28.4078 | 34.1209 | 9.5656 | 8.7725 | 2.1189 | 2.1783 | 3.5943 | 3.3566 | 7.8914 | 5.7231 | 18.3381 | 20.5164 | 28.4078 | 34.1309 | 0.01
5.2751 | 7.8429 | 1.9758 | 1.9638 | 2.8792 | 2.9275 | 6.8188 | 4.855 | 13.1181 | 15.0818 | 21.9006 | 26.7557 | 5.2751 | 7.8429 | 1.9758 | 1.9638 | 2.8792 | 2.9275 | 6.8188 | 4.865 | 13.1181 | 15.0818 | 21.9006 | 26.7657 | 0.01
4.8547 | 7.7519 | 1.9618 | 1.9427 | 2.8091 | 2.8855 | 6.7137 | 4.7709 | 12.6066 | 14.5493 | 21.263 | 26.0339 | 4.8547 | 7.7519 | 1.9618 | 1.9427 | 2.8091 | 2.8855 | 6.7137 | 4.7809 | 12.6066 | 14.5493 | 21.263 | 26.0439 | 0.01
4.1225 | 7.5932 | 1.9374 | 1.9061 | 2.6871 | 2.8123 | 6.5306 | 4.6245 | 11.7157 | 13.6219 | 20.1525 | 24.777 | 4.1225 | 7.5932 | 1.9374 | 1.9061 | 2.6871 | 2.8123 | 6.5306 | 4.6345 | 11.7157 | 13.6219 | 20.1525 | 24.787 | 0.01
0.12817 | 6.7278 | 1.8043 | 1.7064 | 2.0214 | 2.4128 | 5.532 | 3.8256 | 6.8559 | 8.5623 | 14.0944 | 17.92 | 0.12817 | 6.7278 | 1.8043 | 1.7064 | 2.0214 | 2.4128 | 5.532 | 3.8356 | 6.8559 | 8.5623 | 14.0944 | 17.93 | 0.01
3.1497 | 7.3824 | 1.905 | 1.8575 | 2.525 | 2.715 | 6.2874 | 4.4299 | 10.5322 | 12.3897 | 18.6771 | 23.107 | 3.1497 | 7.3824 | 1.905 | 1.8575 | 2.525 | 2.715 | 6.2874 | 4.4399 | 10.5322 | 12.3897 | 18.6771 | 23.117 | 0.01
0.004088 | 6.7009 | 1.8001 | 1.7002 | 2.0007 | 2.4004 | 5.501 | 3.8008 | 6.705 | 8.4052 | 13.9062 | 17.707 | 0.004088 | 6.7009 | 1.8001 | 1.7002 | 2.0007 | 2.4004 | 5.501 | 3.8108 | 6.705 | 8.4052 | 13.9062 | 17.717 | 0.01
2.664 | 7.2772 | 1.8888 | 1.8332 | 2.444 | 2.6664 | 6.166 | 4.3328 | 9.9412 | 11.7744 | 17.9403 | 22.2731 | 2.664 | 7.2772 | 1.8888 | 1.8332 | 2.444 | 2.6664 | 6.166 | 4.3428 | 9.9412 | 11.7744 | 17.9403 | 22.2831 | 0.01
16.3601 | 10.2447 | 2.3453 | 2.518 | 4.7267 | 4.036 | 9.59 | 7.072 | 26.6047 | 29.1227 | 38.7127 | 45.7848 | 16.3601 | 10.2447 | 2.3453 | 2.518 | 4.7267 | 4.036 | 9.59 | 7.082 | 26.6047 | 29.1227 | 38.7127 | 45.7948 | 0.01
1.1157 | 6.9417 | 1.8372 | 1.7558 | 2.186 | 2.5116 | 5.7789 | 4.0231 | 8.0575 | 9.8133 | 15.5922 | 19.6153 | 1.1157 | 6.9417 | 1.8372 | 1.7558 | 2.186 | 2.5116 | 5.7789 | 4.0331 | 8.0575 | 9.8133 | 15.5922 | 19.6253 | 0.01
8.3578 | 8.5109 | 2.0786 | 2.1179 | 3.393 | 3.2358 | 7.5894 | 5.4716 | 16.8686 | 18.9865 | 26.576 | 32.0475 | 8.3578 | 8.5109 | 2.0786 | 2.1179 | 3.393 | 3.2358 | 7.5894 | 5.4816 | 16.8686 | 18.9865 | 26.576 | 32.0575 | 0.01
-3.237 | 5.9986 | 1.6921 | 1.5381 | 1.4605 | 2.0763 | 4.6907 | 3.1526 | 2.7616 | 4.2998 | 8.9905 | 12.1431 | -3.237 | 5.9986 | 1.6921 | 1.5381 | 1.4605 | 2.0763 | 4.6907 | 3.1626 | 2.7616 | 4.2998 | 8.9905 | 12.1531 | 0.01
3.8189 | 7.5274 | 1.9273 | 1.8909 | 2.6365 | 2.7819 | 6.4547 | 4.5638 | 11.3463 | 13.2373 | 19.692 | 24.2558 | 3.8189 | 7.5274 | 1.9273 | 1.8909 | 2.6365 | 2.7819 | 6.4547 | 4.5738 | 11.3463 | 13.2373 | 19.692 | 24.2658 | 0.01
9.7219 | 8.8064 | 2.1241 | 2.1861 | 3.6203 | 3.3722 | 7.9305 | 5.7444 | 18.5283 | 20.7144 | 28.6448 | 34.3892 | 9.7219 | 8.8064 | 2.1241 | 2.1861 | 3.6203 | 3.3722 | 7.9305 | 5.7544 | 18.5283 | 20.7144 | 28.6448 | 34.3992 | 0.01
8.9915 | 8.6482 | 2.0997 | 2.1496 | 3.4986 | 3.2992 | 7.7479 | 5.5983 | 17.6397 | 19.7893 | 27.5372 | 33.1355 | 8.9915 | 8.6482 | 2.0997 | 2.1496 | 3.4986 | 3.2992 | 7.7479 | 5.6083 | 17.6397 | 19.7893 | 27.5372 | 33.1455 | 0.01
-3.6954 | 5.8993 | 1.6768 | 1.5152 | 1.3841 | 2.0305 | 4.5762 | 3.0609 | 2.2039 | 3.7192 | 8.2953 | 11.3562 | -3.6954 | 5.8993 | 1.6768 | 1.5152 | 1.3841 | 2.0305 | 4.5762 | 3.0709 | 2.2039 | 3.7192 | 8.2953 | 11.3662 | 0.01
10.0738 | 8.8827 | 2.1358 | 2.2037 | 3.679 | 3.4074 | 8.0185 | 5.8148 | 18.9565 | 21.1602 | 29.1787 | 34.9934 | 10.0738 | 8.8827 | 2.1358 | 2.2037 | 3.679 | 3.4074 | 8.0185 | 5.8248 | 18.9565 | 21.1602 | 29.1787 | 35.0034 | 0.01
0.046038 | 6.71 | 1.8015 | 1.7023 | 2.0077 | 2.4046 | 5.5115 | 3.8092 | 6.756 | 8.4583 | 13.9698 | 17.779 | 0.046038 | 6.71 | 1.8015 | 1.7023 | 2.0077 | 2.4046 | 5.5115 | 3.8192 | 6.756 | 8.4583 | 13.9698 | 17.789 | 0.01
11.9431 | 9.2877 | 2.1981 | 2.2972 | 3.9905 | 3.5943 | 8.4858 | 6.1886 | 21.2308 | 23.528 | 32.0138 | 38.2024 | 11.9431 | 9.2877 | 2.1981 | 2.2972 | 3.9905 | 3.5943 | 8.4858 | 6.1986 | 21.2308 | 23.528 | 32.0138 | 38.2124 | 0.01
10.2351 | 8.9176 | 2.1412 | 2.2118 | 3.7058 | 3.4235 | 8.0588 | 5.847 | 19.1527 | 21.3645 | 29.4232 | 35.2703 | 10.2351 | 8.9176 | 2.1412 | 2.2118 | 3.7058 | 3.4235 | 8.0588 | 5.857 | 19.1527 | 21.3645 | 29.4232 | 35.2803 | 0.01
16.0073 | 10.1682 | 2.3336 | 2.5004 | 4.6679 | 4.0007 | 9.5018 | 7.0015 | 26.1755 | 28.6759 | 38.1777 | 45.1791 | 16.0073 | 10.1682 | 2.3336 | 2.5004 | 4.6679 | 4.0007 | 9.5018 | 7.0115 | 26.1755 | 28.6759 | 38.1777 | 45.1891 | 0.01
11.2117 | 9.1292 | 2.1737 | 2.2606 | 3.8686 | 3.5212 | 8.3029 | 6.0423 | 20.3409 | 22.6015 | 30.9044 | 36.9468 | 11.2117 | 9.1292 | 2.1737 | 2.2606 | 3.8686 | 3.5212 | 8.3029 | 6.0523 | 20.3409 | 22.6015 | 30.9044 | 36.9568 | 0.01
0.7651 | 6.8658 | 1.8255 | 1.7383 | 2.1275 | 2.4765 | 5.6913 | 3.953 | 7.6309 | 9.3691 | 15.0604 | 19.0134 | 0.7651 | 6.8658 | 1.8255 | 1.7383 | 2.1275 | 2.4765 | 5.6913 | 3.963 | 7.6309 | 9.3691 | 15.0604 | 19.0234 | 0.01
-2.5424 | 6.1491 | 1.7153 | 1.5729 | 1.5763 | 2.1458 | 4.8644 | 3.2915 | 3.6068 | 5.1796 | 10.044 | 13.3356 | -2.5424 | 6.1491 | 1.7153 | 1.5729 | 1.5763 | 2.1458 | 4.8644 | 3.3015 | 3.6068 | 5.1796 | 10.044 | 13.3456 | 0.01
6.6128 | 8.1328 | 2.0204 | 2.0306 | 3.1021 | 3.0613 | 7.1532 | 5.1226 | 14.7456 | 16.7763 | 23.9295 | 29.052 | 6.6128 | 8.1328 | 2.0204 | 2.0306 | 3.1021 | 3.0613 | 7.1532 | 5.1326 | 14.7456 | 16.7763 | 23.9295 | 29.062 | 0.01
-0.13011 | 6.6718 | 1.7957 | 1.6935 | 1.9783 | 2.387 | 5.4675 | 3.774 | 6.5417 | 8.2352 | 13.7027 | 17.4766 | -0.13011 | 6.6718 | 1.7957 | 1.6935 | 1.9783 | 2.387 | 5.4675 | 3.784 | 6.5417 | 8.2352 | 13.7027 | 17.4866 | 0.01
2.5146 | 7.2448 | 1.8838 | 1.8257 | 2.4191 | 2.6515 | 6.1286 | 4.3029 | 9.7594 | 11.5851 | 17.7138 | 22.0167 | 2.5146 | 7.2448 | 1.8838 | 1.8257 | 2.4191 | 2.6515 | 6.1286 | 4.3129 | 9.7594 | 11.5851 | 17.7138 | 22.0267 | 0.01
14.496 | 9.8408 | 2.2832 | 2.4248 | 4.416 | 3.8496 | 9.124 | 6.6992 | 24.3368 | 26.7616 | 35.8856 | 42.5848 | 14.496 | 9.8408 | 2.2832 | 2.4248 | 4.416 | 3.8496 | 9.124 | 6.7092 | 24.3368 | 26.7616 | 35.8856 | 42.5948 | 0.01
6.3767 | 8.0816 | 2.0126 | 2.0188 | 3.0628 | 3.0377 | 7.0942 | 5.0753 | 14.4583 | 16.4771 | 23.5713 | 28.6466 | 6.3767 | 8.0816 | 2.0126 | 2.0188 | 3.0628 | 3.0377 | 7.0942 | 5.0853 | 14.4583 | 16.4771 | 23.5713 | 28.6566 | 0.01
-0.66363 | 6.5562 | 1.7779 | 1.6668 | 1.8894 | 2.3336 | 5.3341 | 3.6673 | 5.8926 | 7.5594 | 12.8935 | 16.5608 | -0.66363 | 6.5562 | 1.7779 | 1.6668 | 1.8894 | 2.3336 | 5.3341 | 3.6773 | 5.8926 | 7.5594 | 12.8935 | 16.5708 | 0.01
6.6236 | 8.1351 | 2.0208 | 2.0312 | 3.1039 | 3.0624 | 7.1559 | 5.1247 | 14.7587 | 16.7899 | 23.9458 | 29.0705 | 6.6236 | 8.1351 | 2.0208 | 2.0312 | 3.1039 | 3.0624 | 7.1559 | 5.1347 | 14.7587 | 16.7899 | 23.9458 | 29.0805 | 0.01
-1.4404 | 6.3879 | 1.752 | 1.628 | 1.7599 | 2.256 | 5.1399 | 3.5119 | 4.9476 | 6.5755 | 11.7155 | 15.2274 | -1.4404 | 6.3879 | 1.752 | 1.628 | 1.7599 | 2.256 | 5.1399 | 3.5219 | 4.9476 | 6.5755 | 11.7155 | 15.2374 | 0.01
3.8707 | 7.5386 | 1.929 | 1.8935 | 2.6451 | 2.7871 | 6.4677 | 4.5741 | 11.4093 | 13.3029 | 19.7705 | 24.3447 | 3.8707 | 7.5386 | 1.929 | 1.8935 | 2.6451 | 2.7871 | 6.4677 | 4.5841 | 11.4093 | 13.3029 | 19.7705 | 24.3547 | 0.01
-11.3239 | 4.2465 | 1.4225 | 1.1338 | 0.11268 | 1.2676 | 2.669 | 1.5352 | -7.0774 | -5.9436 | -3.2746 | -1.7394 | -11.3239 | 4.2465 | 1.4225 | 1.1338 | 0.11268 | 1.2676 | 2.669 | 1.5452 | -7.0774 | -5.9436 | -3.2746 | -1.7294 | 0.01
8.374 | 8.5144 | 2.0791 | 2.1187 | 3.3957 | 3.2374 | 7.5935 | 5.4748 | 16.8884 | 19.0071 | 26.6006 | 32.0754 | 8.374 | 8.5144 | 2.0791 | 2.1187 | 3.3957 | 3.2374 | 7.5935 | 5.4848 | 16.8884 | 19.0071 | 26.6006 | 32.0854 | 0.01
12.9704 | 9.5102 | 2.2323 | 2.3485 | 4.1617 | 3.697 | 8.7426 | 6.3941 | 22.4806 | 24.8291 | 33.5717 | 39.9658 | 12.9704 | 9.5102 | 2.2323 | 2.3485 | 4.1617 | 3.697 | 8.7426 | 6.4041 | 22.4806 | 24.8291 | 33.5717 | 39.9758 | 0.01
1.7719 | 7.0839 | 1.8591 | 1.7886 | 2.2953 | 2.5772 | 5.943 | 4.1544 | 8.8558 | 10.6444 | 16.5874 | 20.7418 | 1.7719 | 7.0839 | 1.8591 | 1.7886 | 2.2953 | 2.5772 | 5.943 | 4.1644 | 8.8558 | 10.6444 | 16.5874 | 20.7518 | 0.01
-0.26064 | 6.6435 | 1.7913 | 1.687 | 1.9566 | 2.3739 | 5.4348 | 3.7479 | 6.3829 | 8.0699 | 13.5047 | 17.2526 | -0.26064 | 6.6435 | 1.7913 | 1.687 | 1.9566 | 2.3739 | 5.4348 | 3.7579 | 6.3829 | 8.0699 | 13.5047 | 17.2626 | 0.01
8.9346 | 8.6358 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7336 | 5.5869 | 17.5704 | 19.7171 | 27.4507 | 33.0376 | 8.9346 | 8.6358 | 2.0978 | 2.1467 | 3.4891 | 3.2935 | 7.7336 | 5.5969 | 17.5704 | 19.7171 | 27.4507 | 33.0476 | 0.01
8.9889 | 8.6476 | 2.0996 | 2.1494 | 3.4981 | 3.2989 | 7.7472 | 5.5978 | 17.6365 | 19.7859 | 27.5332 | 33.1309 | 8.9889 | 8.6476 | 2.0996 | 2.1494 | 3.4981 | 3.2989 | 7.7472 | 5.6078 | 17.6365 | 19.7859 | 27.5332 | 33.1409 | 0.01
5.2835 | 7.8448 | 1.9761 | 1.9642 | 2.8806 | 2.9284 | 6.8209 | 4.8567 | 13.1283 | 15.0925 | 21.9133 | 26.77 | 5.2835 | 7.8448 | 1.9761 | 1.9642 | 2.8806 | 2.9284 | 6.8209 | 4.8667 | 13.1283 | 15.0925 | 21.9133 | 26.78 | 0.01
9.4524 | 8.748 | 2.1151 | 2.1726 | 3.5754 | 3.3452 | 7.8631 | 5.6905 | 18.2004 | 20.373 | 28.2361 | 33.9266 | 9.4524 | 8.748 | 2.1151 | 2.1726 | 3.5754 | 3.3452 | 7.8631 | 5.7005 | 18.2004 | 20.373 | 28.2361 | 33.9366 | 0.01
12.1174 | 9.3254 | 2.2039 | 2.3059 | 4.0196 | 3.6117 | 8.5294 | 6.2235 | 21.4429 | 23.7487 | 32.2781 | 38.5016 | 12.1174 | 9.3254 | 2.2039 | 2.3059 | 4.0196 | 3.6117 | 8.5294 | 6.2335 | 21.4429 | 23.7487 | 32.2781 | 38.5116 | 0.01
2.5021 | 7.2421 | 1.8834 | 1.8251 | 2.417 | 2.6502 | 6.1255 | 4.3004 | 9.7443 | 11.5694 | 17.6949 | 21.9953 | 2.5021 | 7.2421 | 1.8834 | 1.8251 | 2.417 | 2.6502 | 6.1255 | 4.3104 | 9.7443 | 11.5694 | 17.6949 | 22.0053 | 0.01
0.91537 | 6.8983 | 1.8305 | 1.7458 | 2.1526 | 2.4915 | 5.7288 | 3.9831 | 7.8137 | 9.5595 | 15.2883 | 19.2714 | 0.91537 | 6.8983 | 1.8305 | 1.7458 | 2.1526 | 2.4915 | 5.7288 | 3.9931 | 7.8137 | 9.5595 | 15.2883 | 19.2814 | 0.01
-1.7202 | 6.3273 | 1.7427 | 1.614 | 1.7133 | 2.228 | 5.07 | 3.456 | 4.6071 | 6.2211 | 11.2911 | 14.7471 | -1.7202 | 6.3273 | 1.7427 | 1.614 | 1.7133 | 2.228 | 5.07 | 3.466 | 4.6071 | 6.2211 | 11.2911 | 14.7571 | 0.01
7.3217 | 8.2864 | 2.0441 | 2.0661 | 3.2203 | 3.1322 | 7.3304 | 5.2643 | 15.608 | 17.6741 | 25.0046 | 30.2689 | 7.3217 | 8.2864 | 2.0441 | 2.0661 | 3.2203 | 3.1322 | 7.3304 | 5.2743 | 15.608 | 17.6741 | 25.0046 | 30.2789 | 0.01
7.9757 | 8.4281 | 2.0659 | 2.0988 | 3.3293 | 3.1976 | 7.4939 | 5.3951 | 16.4037 | 18.5025 | 25.9965 | 31.3916 | 7.9757 | 8.4281 | 2.0659 | 2.0988 | 3.3293 | 3.1976 | 7.4939 | 5.4051 | 16.4037 | 18.5025 | 25.9965 | 31.4016 | 0.01
-2.8082 | 6.0916 | 1.7064 | 1.5596 | 1.532 | 2.1192 | 4.798 | 3.2384 | 3.2834 | 4.843 | 9.6409 | 12.8793 | -2.8082 | 6.0916 | 1.7064 | 1.5596 | 1.532 | 2.1192 | 4.798 | 3.2484 | 3.2834 | 4.843 | 9.6409 | 12.8893 | 0.01
-1.3037 | 6.4175 | 1.7565 | 1.6348 | 1.7827 | 2.2696 | 5.1741 | 3.5393 | 5.1139 | 6.7487 | 11.9228 | 15.462 | -1.3037 | 6.4175 | 1.7565 | 1.6348 | 1.7827 | 2.2696 | 5.1741 | 3.5493 | 5.1139 | 6.7487 | 11.9228 | 15.472 | 0.01
0.17091 | 6.737 | 1.8057 | 1.7085 | 2.0285 | 2.4171 | 5.5427 | 3.8342 | 6.9079 | 8.6165 | 14.1592 | 17.9934 | 0.17091 | 6.737 | 1.8057 | 1.7085 | 2.0285 | 2.4171 | 5.5427 | 3.8442 | 6.9079 | 8.6165 | 14.1592 | 18.0034 | 0.01
-7.6486 | 5.0428 | 1.545 | 1.3176 | 0.72523 | 1.6351 | 3.5878 | 2.2703 | -2.6058 | -1.2883 | 2.2996 | 4.5698 | -7.6486 | 5.0428 | 1.545 | 1.3176 | 0.72523 | 1.6351 | 3.5878 | 2.2803 | -2.6058 | -1.2883 | 2.2996 | 4.5798 | 0.01
7.5446 | 8.3347 | 2.0515 | 2.0772 | 3.2574 | 3.1545 | 7.3862 | 5.3089 | 15.8793 | 17.9565 | 25.3427 | 30.6516 | 7.5446 | 8.3347 | 2.0515 | 2.0772 | 3.2574 | 3.1545 | 7.3862 | 5.3189 | 15.8793 | 17.9565 | 25.3427 | 30.6616 | 0.01
9.7001 | 8.8017 | 2.1233 | 2.185 | 3.6167 | 3.37 | 7.925 | 5.74 | 18.5018 | 20.6869 | 28.6119 | 34.3519 | 9.7001 | 8.8017 | 2.1233 | 2.185 | 3.6167 | 3.37 | 7.925 | 5.75 | 18.5018 | 20.6869 | 28.6119 | 34.3619 | 0.01
8.0543 | 8.4451 | 2.0685 | 2.1027 | 3.3424 | 3.2054 | 7.5136 | 5.4109 | 16.4994 | 18.6021 | 26.1157 | 31.5266 | 8.0543 | 8.4451 | 2.0685 | 2.1027 | 3.3424 | 3.2054 | 7.5136 | 5.4209 | 16.4994 | 18.6021 | 26.1157 | 31.5366 | 0.01
-1.2755 | 6.4236 | 1.7575 | 1.6362 | 1.7874 | 2.2725 | 5.1811 | 3.5449 | 5.1482 | 6.7844 | 11.9655 | 15.5104 | -1.2755 | 6.4236 | 1.7575 | 1.6362 | 1.7874 | 2.2725 | 5.1811 | 3.5549 | 5.1482 | 6.7844 | 11.9655 | 15.5204 | 0.01
1.6532 | 7.0582 | 1.8551 | 1.7827 | 2.2755 | 2.5653 | 5.9133 | 4.1306 | 8.7114 | 10.494 | 16.4073 | 20.538 | 1.6532 | 7.0582 | 1.8551 | 1.7827 | 2.2755 | 2.5653 | 5.9133 | 4.1406 | 8.7114 | 10.494 | 16.4073 | 20.548 | 0.01
4.0014 | 7.567 | 1.9334 | 1.9001 | 2.6669 | 2.8001 | 6.5004 | 4.6003 | 11.5684 | 13.4685 | 19.9689 | 24.5692 | 4.0014 | 7.567 | 1.9334 | 1.9001 | 2.6669 | 2.8001 | 6.5004 | 4.6103 | 11.5684 | 13.4685 | 19.9689 | 24.5792 | 0.01
9.7211 | 8.8062 | 2.124 | 2.1861 | 3.6202 | 3.3721 | 7.9303 | 5.7442 | 18.5273 | 20.7134 | 28.6437 | 34.3879 | 9.7211 | 8.8062 | 2.124 | 2.1861 | 3.6202 | 3.3721 | 7.9303 | 5.7542 | 18.5273 | 20.7134 | 28.6437 | 34.3979 | 0.01
18.4405 | 10.6954 | 2.4147 | 2.622 | 5.0734 | 4.2441 | 10.1101 | 7.4881 | 29.136 | 31.758 | 41.8681 | 49.3562 | 18.4405 | 10.6954 | 2.4147 | 2.622 | 5.0734 | 4.2441 | 10.1101 | 7.4981 | 29.136 | 31.758 | 41.8681 | 49.3662 | 0.01
6.7586 | 8.1644 | 2.0253 | 2.0379 | 3.1264 | 3.0759 | 7.1896 | 5.1517 | 14.9229 | 16.9609 | 24.1505 | 29.3022 | 6.7586 | 8.1644 | 2.0253 | 2.0379 | 3.1264 | 3.0759 | 7.1896 | 5.1617 | 14.9229 | 16.9609 | 24.1505 | 29.3122 | 0.01
17.2651 | 10.4408 | 2.3755 | 2.5633 | 4.8775 | 4.1265 | 9.8163 | 7.253 | 27.7059 | 30.2692 | 40.0855 | 47.3385 | 17.2651 | 10.4408 | 2.3755 | 2.5633 | 4.8775 | 4.1265 | 9.8163 | 7.263 | 27.7059 | 30.2692 | 40.0855 | 47.3485 | 0.01
-4.1978 | 5.7905 | 1.6601 | 1.4901 | 1.3004 | 1.9802 | 4.4506 | 2.9604 | 1.5927 | 3.0828 | 7.5334 | 10.4938 | -4.1978 | 5.7905 | 1.6601 | 1.4901 | 1.3004 | 1.9802 | 4.4506 | 2.9704 | 1.5927 | 3.0828 | 7.5334 | 10.5038 | 0.01
7.4729 | 8.3191 | 2.0491 | 2.0736 | 3.2455 | 3.1473 | 7.3682 | 5.2946 | 15.7921 | 17.8657 | 25.2339 | 30.5285 | 7.4729 | 8.3191 | 2.0491 | 2.0736 | 3.2455 | 3.1473 | 7.3682 | 5.3046 | 15.7921 | 17.8657 | 25.2339 | 30.5385 | 0.01
-0.8847 | 6.5083 | 1.7705 | 1.6558 | 1.8525 | 2.3115 | 5.2788 | 3.6231 | 5.6236 | 7.2794 | 12.5582 | 16.1813 | -0.8847 | 6.5083 | 1.7705 | 1.6558 | 1.8525 | 2.3115 | 5.2788 | 3.6331 | 5.6236 | 7.2794 | 12.5582 | 16.1913 | 0.01
14.5788 | 9.8587 | 2.286 | 2.4289 | 4.4298 | 3.8579 | 9.1447 | 6.7158 | 24.4376 | 26.8665 | 36.0112 | 42.727 | 14.5788 | 9.8587 | 2.286 | 2.4289 | 4.4298 | 3.8579 | 9.1447 | 6.7258 | 24.4376 | 26.8665 | 36.0112 | 42.737 | 0.01
0.12537 | 6.7272 | 1.8042 | 1.7063 | 2.0209 | 2.4125 | 5.5313 | 3.8251 | 6.8525 | 8.5588 | 14.0901 | 17.9152 | 0.12537 | 6.7272 | 1.8042 | 1.7063 | 2.0209 | 2.4125 | 5.5313 | 3.8351 | 6.8525 | 8.5588 | 14.0901 | 17.9252 | 0.01
4.2245 | 7.6153 | 1.9408 | 1.9112 | 2.7041 | 2.8224 | 6.5561 | 4.6449 | 11.8398 | 13.751 | 20.3071 | 24.952 | 4.2245 | 7.6153 | 1.9408 | 1.9112 | 2.7041 | 2.8224 | 6.5561 | 4.6549 | 11.8398 | 13.751 | 20.3071 | 24.962 | 0.01
15.0219 | 9.9547 | 2.3007 | 2.4511 | 4.5036 | 3.9022 | 9.2555 | 6.8044 | 24.9766 | 27.4277 | 36.6832 | 43.4875 | 15.0219 | 9.9547 | 2.3007 | 2.4511 | 4.5036 | 3.9022 | 9.2555 | 6.8144 | 24.9766 | 27.4277 | 36.6832 | 43.4975 | 0.01
-2.3623 | 6.1882 | 1.7213 | 1.5819 | 1.6063 | 2.1638 | 4.9094 | 3.3275 | 3.8258 | 5.4077 | 10.3171 | 13.6446 | -2.3623 | 6.1882 | 1.7213 | 1.5819 | 1.6063 | 2.1638 | 4.9094 | 3.3375 | 3.8258 | 5.4077 | 10.3171 | 13.6546 | 0.01
-0.42982 | 6.6069 | 1.7857 | 1.6785 | 1.9284 | 2.357 | 5.3925 | 3.714 | 6.177 | 7.8556 | 13.2481 | 16.9621 | -0.42982 | 6.6069 | 1.7857 | 1.6785 | 1.9284 | 2.357 | 5.3925 | 3.724 | 6.177 | 7.8556 | 13.2481 | 16.9721 | 0.01
7.7003 | 8.3684 | 2.0567 | 2.085 | 3.2834 | 3.17 | 7.4251 | 5.3401 | 16.0687 | 18.1537 | 25.5788 | 30.9188 | 7.7003 | 8.3684 | 2.0567 | 2.085 | 3.2834 | 3.17 | 7.4251 | 5.3501 | 16.0687 | 18.1537 | 25.5788 | 30.9288 | 0.01
5.0337 | 7.7906 | 1.9678 | 1.9517 | 2.839 | 2.9034 | 6.7584 | 4.8067 | 12.8244 | 14.776 | 21.5345 | 26.3412 | 5.0337 | 7.7906 | 1.9678 | 1.9517 | 2.839 | 2.9034 | 6.7584 | 4.8167 | 12.8244 | 14.776 | 21.5345 | 26.3512 | 0.01
3.2793 | 7.4105 | 1.9093 | 1.864 | 2.5465 | 2.7279 | 6.3198 | 4.4559 | 10.6898 | 12.5538 | 18.8736 | 23.3294 | 3.2793 | 7.4105 | 1.9093 | 1.864 | 2.5465 | 2.7279 | 6.3198 | 4.4659 | 10.6898 | 12.5538 | 18.8736 | 23.3394 | 0.01
-0.40881 | 6.6114 | 1.7864 | 1.6796 | 1.9319 | 2.3591 | 5.3978 | 3.7182 | 6.2026 | 7.8822 | 13.28 | 16.9982 | -0.40881 | 6.6114 | 1.7864 | 1.6796 | 1.9319 | 2.3591 | 5.3978 | 3.7282 | 6.2026 | 7.8822 | 13.28 | 17.0082 | 0.01
12.3703 | 9.3802 | 2.2123 | 2.3185 | 4.0617 | 3.637 | 8.5926 | 6.2741 | 21.7505 | 24.069 | 32.6616 | 38.9356 | 12.3703 | 9.3802 | 2.2123 | 2.3185 | 4.0617 | 3.637 | 8.5926 | 6.2841 | 21.7505 | 24.069 | 32.6616 | 38.9456 | 0.01
9.2318 | 8.7002 | 2.1077 | 2.1616 | 3.5386 | 3.3232 | 7.8079 | 5.6464 | 17.932 | 20.0936 | 27.9015 | 33.5479 | 9.2318 | 8.7002 | 2.1077 | 2.1616 | 3.5386 | 3.3232 | 7.8079 | 5.6564 | 17.932 | 20.0936 | 27.9015 | 33.5579 | 0.01
9.9205 | 8.8494 | 2.1307 | 2.196 | 3.6534 | 3.392 | 7.9801 | 5.7841 | 18.7699 | 20.9659 | 28.946 | 34.7301 | 9.9205 | 8.8494 | 2.1307 | 2.196 | 3.6534 | 3.392 | 7.9801 | 5.7941 | 18.7699 | 20.9659 | 28.946 | 34.7401 | 0.01
12.8623 | 9.4868 | 2.2287 | 2.3431 | 4.1437 | 3.6862 | 8.7156 | 6.3725 | 22.3491 | 24.6922 | 33.4078 | 39.7802 | 12.8623 | 9.4868 | 2.2287 | 2.3431 | 4.1437 | 3.6862 | 8.7156 | 6.3825 | 22.3491 | 24.6922 | 33.4078 | 39.7902 | 0.01
-2.6898 | 6.1172 | 1.7103 | 1.5655 | 1.5517 | 2.131 | 4.8276 | 3.262 | 3.4274 | 4.9929 | 9.8205 | 13.0825 | -2.6898 | 6.1172 | 1.7103 | 1.5655 | 1.5517 | 2.131 | 4.8276 | 3.272 | 3.4274 | 4.9929 | 9.8205 | 13.0925 | 0.01
10.976 | 9.0781 | 2.1659 | 2.2488 | 3.8293 | 3.4976 | 8.244 | 5.9952 | 20.0542 | 22.303 | 30.547 | 36.5422 | 10.976 | 9.0781 | 2.1659 | 2.2488 | 3.8293 | 3.4976 | 8.244 | 6.0052 | 20.0542 | 22.303 | 30.547 | 36.5522 | 0.01
6.1885 | 8.0408 | 2.0063 | 2.0094 | 3.0314 | 3.0189 | 7.0471 | 5.0377 | 14.2294 | 16.2388 | 23.2859 | 28.3237 | 6.1885 | 8.0408 | 2.0063 | 2.0094 | 3.0314 | 3.0189 | 7.0471 | 5.0477 | 14.2294 | 16.2388 | 23.2859 | 28.3337 | 0.01
-0.0097864 | 6.6979 | 1.7997 | 1.6995 | 1.9984 | 2.399 | 5.4976 | 3.798 | 6.6881 | 8.3876 | 13.8852 | 17.6832 | -0.0097864 | 6.6979 | 1.7997 | 1.6995 | 1.9984 | 2.399 | 5.4976 | 3.808 | 6.6881 | 8.3876 | 13.8852 | 17.6932 | 0.01
13.3212 | 9.5863 | 2.244 | 2.3661 | 4.2202 | 3.7321 | 8.8303 | 6.4642 | 22.9074 | 25.2735 | 34.1038 | 40.568 | 13.3212 | 9.5863 | 2.244 | 2.3661 | 4.2202 | 3.7321 | 8.8303 | 6.4742 | 22.9074 | 25.2735 | 34.1038 | 40.578 | 0.01
-0.72099 | 6.5438 | 1.776 | 1.664 | 1.8798 | 2.3279 | 5.3198 | 3.6558 | 5.8228 | 7.4867 | 12.8065 | 16.4623 | -0.72099 | 6.5438 | 1.776 | 1.664 | 1.8798 | 2.3279 | 5.3198 | 3.6658 | 5.8228 | 7.4867 | 12.8065 | 16.4723 | 0.01
-0.99952 | 6.4834 | 1.7667 | 1.65 | 1.8334 | 2.3 | 5.2501 | 3.6001 | 5.4839 | 7.1339 | 12.3841 | 15.9842 | -0.99952 | 6.4834 | 1.7667 | 1.65 | 1.8334 | 2.3 | 5.2501 | 3.6101 | 5.4839 | 7.1339 | 12.3841 | 15.9942 | 0.01
1.5168 | 7.0286 | 1.8506 | 1.7758 | 2.2528 | 2.5517 | 5.8792 | 4.1034 | 8.5455 | 10.3213 | 16.2005 | 20.3039 | 1.5168 | 7.0286 | 1.8506 | 1.7758 | 2.2528 | 2.5517 | 5.8792 | 4.1134 | 8.5455 | 10.3213 | 16.2005 | 20.3139 | 0.01
-0.58033 | 6.5743 | 1.7807 | 1.671 | 1.9033 | 2.342 | 5.3549 | 3.6839 | 5.9939 | 7.6649 | 13.0198 | 16.7038 | -0.58033 | 6.5743 | 1.7807 | 1.671 | 1.9033 | 2.342 | 5.3549 | 3.6939 | 5.9939 | 7.6649 | 13.0198 | 16.7138 | 0.01
0.17113 | 6.7371 | 1.8057 | 1.7086 | 2.0285 | 2.4171 | 5.5428 | 3.8342 | 6.9082 | 8.6168 | 14.1595 | 17.9938 | 0.17113 | 6.7371 | 1.8057 | 1.7086 | 2.0285 | 2.4171 | 5.5428 | 3.8442 | 6.9082 | 8.6168 | 14.1595 | 18.0038 | 0.01
0.074319 | 6.7161 | 1.8025 | 1.7037 | 2.0124 | 2.4074 | 5.5186 | 3.8149 | 6.7904 | 8.4941 | 14.0127 | 17.8276 | 0.074319 | 6.7161 | 1.8025 | 1.7037 | 2.0124 | 2.4074 | 5.5186 | 3.8249 | 6.7904 | 8.4941 | 14.0127 | 17.8376 | 0.01
1.085 | 6.9351 | 1.8362 | 1.7543 | 2.1808 | 2.5085 | 5.7713 | 4.017 | 8.0201 | 9.7744 | 15.5456 | 19.5626 | 1.085 | 6.9351 | 1.8362 | 1.7543 | 2.1808 | 2.5085 | 5.7713 | 4.027 | 8.0201 | 9.7744 | 15.5456 | 19.5726 | 0.01
-3.1212 | 6.0237 | 1.696 | 1.5439 | 1.4798 | 2.0879 | 4.7197 | 3.1758 | 2.9025 | 4.4464 | 9.1661 | 12.3419 | -3.1212 | 6.0237 | 1.696 | 1.5439 | 1.4798 | 2.0879 | 4.7197 | 3.1858 | 2.9025 | 4.4464 | 9.1661 | 12.3519 | 0.01
6.0895 | 8.0194 | 2.003 | 2.0045 | 3.0149 | 3.009 | 7.0224 | 5.0179 | 14.1089 | 16.1134 | 23.1357 | 28.1536 | 6.0895 | 8.0194 | 2.003 | 2.0045 | 3.0149 | 3.009 | 7.0224 | 5.0279 | 14.1089 | 16.1134 | 23.1357 | 28.1636 | 0.01
6.2141 | 8.0464 | 2.0071 | 2.0107 | 3.0357 | 3.0214 | 7.0535 | 5.0428 | 14.2605 | 16.2712 | 23.3247 | 28.3676 | 6.2141 | 8.0464 | 2.0071 | 2.0107 | 3.0357 | 3.0214 | 7.0535 | 5.0528 | 14.2605 | 16.2712 | 23.3247 | 28.3776 | 0.01
9.4624 | 8.7502 | 2.1154 | 2.1731 | 3.5771 | 3.3462 | 7.8656 | 5.6925 | 18.2126 | 20.3857 | 28.2513 | 33.9437 | 9.4624 | 8.7502 | 2.1154 | 2.1731 | 3.5771 | 3.3462 | 7.8656 | 5.7025 | 18.2126 | 20.3857 | 28.2513 | 33.9537 | 0.01
2.7991 | 7.3065 | 1.8933 | 1.84 | 2.4665 | 2.6799 | 6.1998 | 4.3598 | 10.1056 | 11.9456 | 18.1454 | 22.5052 | 2.7991 | 7.3065 | 1.8933 | 1.84 | 2.4665 | 2.6799 | 6.1998 | 4.3698 | 10.1056 | 11.9456 | 18.1454 | 22.5152 | 0.01
0.57475 | 6.8245 | 1.8192 | 1.7287 | 2.0958 | 2.4575 | 5.6437 | 3.915 | 7.3993 | 9.128 | 14.7717 | 18.6867 | 0.57475 | 6.8245 | 1.8192 | 1.7287 | 2.0958 | 2.4575 | 5.6437 | 3.925 | 7.3993 | 9.128 | 14.7717 | 18.6967 | 0.01
9.4411 | 8.7456 | 2.1147 | 2.1721 | 3.5735 | 3.3441 | 7.8603 | 5.6882 | 18.1866 | 20.3587 | 28.219 | 33.9072 | 9.4411 | 8.7456 | 2.1147 | 2.1721 | 3.5735 | 3.3441 | 7.8603 | 5.6982 | 18.1866 | 20.3587 | 28.219 | 33.9172 | 0.01
-1.3256 | 6.4128 | 1.7558 | 1.6337 | 1.7791 | 2.2674 | 5.1686 | 3.5349 | 5.0872 | 6.7209 | 11.8896 | 15.4244 | -1.3256 | 6.4128 | 1.7558 | 1.6337 | 1.7791 | 2.2674 | 5.1686 | 3.5449 | 5.0872 | 6.7209 | 11.8896 | 15.4344 | 0.01
6.3785 | 8.082 | 2.0126 | 2.0189 | 3.0631 | 3.0379 | 7.0946 | 5.0757 | 14.4605 | 16.4794 | 23.5741 | 28.6498 | 6.3785 | 8.082 | 2.0126 | 2.0189 | 3.0631 | 3.0379 | 7.0946 | 5.0857 | 14.4605 | 16.4794 | 23.5741 | 28.6598 | 0.01
1.0149 | 6.9199 | 1.8338 | 1.7507 | 2.1692 | 2.5015 | 5.7537 | 4.003 | 7.9348 | 9.6856 | 15.4393 | 19.4423 | 1.0149 | 6.9199 | 1.8338 | 1.7507 | 2.1692 | 2.5015 | 5.7537 | 4.013 | 7.9348 | 9.6856 | 15.4393 | 19.4523 | 0.01
3.1071 | 7.3732 | 1.9036 | 1.8554 | 2.5178 | 2.7107 | 6.2768 | 4.4214 | 10.4803 | 12.3356 | 18.6124 | 23.0338 | 3.1071 | 7.3732 | 1.9036 | 1.8554 | 2.5178 | 2.7107 | 6.2768 | 4.4314 | 10.4803 | 12.3356 | 18.6124 | 23.0438 | 0.01
8.6083 | 8.5651 | 2.0869 | 2.1304 | 3.4347 | 3.2608 | 7.6521 | 5.5217 | 17.1734 | 19.3038 | 26.9559 | 32.4776 | 8.6083 | 8.5651 | 2.0869 | 2.1304 | 3.4347 | 3.2608 | 7.6521 | 5.5317 | 17.1734 | 19.3038 | 26.9559 | 32.4876 | 0.01
-7.3979 | 5.0971 | 1.5534 | 1.3301 | 0.76701 | 1.6602 | 3.6505 | 2.3204 | -2.3008 | -0.97073 | 2.6798 | 5.0002 | -7.3979 | 5.0971 | 1.5534 | 1.3301 | 0.76701 | 1.6602 | 3.6505 | 2.3304 | -2.3008 | -0.97073 | 2.6798 | 5.0102 | 0.01
9.1391 | 8.6801 | 2.1046 | 2.157 | 3.5232 | 3.3139 | 7.7848 | 5.6278 | 17.8192 | 19.9762 | 27.7609 | 33.3887 | 9.1391 | 8.6801 | 2.1046 | 2.157 | 3.5232 | 3.3139 | 7.7848 | 5.6378 | 17.8192 | 19.9762 | 27.7609 | 33.3987 | 0.01
10.1185 | 8.8923 | 2.1373 | 2.2059 | 3.6864 | 3.4118 | 8.0296 | 5.8237 | 19.0108 | 21.2168 | 29.2464 | 35.0701 | 10.1185 | 8.8923 | 2.1373 | 2.2059 | 3.6864 | 3.4118 | 8.0296 | 5.8337 | 19.0108 | 21.2168 | 29.2464 | 35.0801 | 0.01
8.8895 | 8.6261 | 2.0963 | 2.1445 | 3.4816 | 3.289 | 7.7224 | 5.5779 | 17.5156 | 19.6601 | 27.3825 | 32.9604 | 8.8895 | 8.6261 | 2.0963 | 2.1445 | 3.4816 | 3.289 | 7.7224 | 5.5879 | 17.5156 | 19.6601 | 27.3825 | 32.9704 | 0.01
18.1174 | 10.6254 | 2.4039 | 2.6059 | 5.0196 | 4.2117 | 10.0293 | 7.4235 | 28.7428 | 31.3487 | 41.378 | 48.8015 | 18.1174 | 10.6254 | 2.4039 | 2.6059 | 5.0196 | 4.2117 | 10.0293 | 7.4335 | 28.7428 | 31.3487 | 41.378 | 48.8115 | 0.01
-4.172 | 5.7961 | 1.6609 | 1.4914 | 1.3047 | 1.9828 | 4.457 | 2.9656 | 1.6241 | 3.1155 | 7.5725 | 10.5381 | -4.172 | 5.7961 | 1.6609 | 1.4914 | 1.3047 | 1.9828 | 4.457 | 2.9756 | 1.6241 | 3.1155 | 7.5725 | 10.5481 | 0.01
4.7866 | 7.7371 | 1.9596 | 1.9393 | 2.7978 | 2.8787 | 6.6966 | 4.7573 | 12.5236 | 14.463 | 21.1596 | 25.9169 | 4.7866 | 7.7371 | 1.9596 | 1.9393 | 2.7978 | 2.8787 | 6.6966 | 4.7673 | 12.5236 | 14.463 | 21.1596 | 25.9269 | 0.01
8.5519 | 8.5529 | 2.0851 | 2.1276 | 3.4253 | 3.2552 | 7.638 | 5.5104 | 17.1048 | 19.2324 | 26.8704 | 32.3807 | 8.5519 | 8.5529 | 2.0851 | 2.1276 | 3.4253 | 3.2552 | 7.638 | 5.5204 | 17.1048 | 19.2324 | 26.8704 | 32.3907 | 0.01
6.8119 | 8.1759 | 2.0271 | 2.0406 | 3.1353 | 3.0812 | 7.203 | 5.1624 | 14.9878 | 17.0284 | 24.2313 | 29.3937 | 6.8119 | 8.1759 | 2.0271 | 2.0406 | 3.1353 | 3.0812 | 7.203 | 5.1724 | 14.9878 | 17.0284 | 24.2313 | 29.4037 | 0.01
-7.8754 | 4.9937 | 1.5375 | 1.3062 | 0.68743 | 1.6125 | 3.5311 | 2.2249 | -2.8818 | -1.5755 | 1.9556 | 4.1805 | -7.8754 | 4.9937 | 1.5375 | 1.3062 | 0.68743 | 1.6125 | 3.5311 | 2.2349 | -2.8818 | -1.5755 | 1.9556 | 4.1905 | 0.01
3.4751 | 7.4529 | 1.9158 | 1.8738 | 2.5792 | 2.7475 | 6.3688 | 4.495 | 10.9281 | 12.8018 | 19.1706 | 23.6656 | 3.4751 | 7.4529 | 1.9158 | 1.8738 | 2.5792 | 2.7475 | 6.3688 | 4.505 | 10.9281 | 12.8018 | 19.1706 | 23.6756 | 0.01
-3.9303 | 5.8484 | 1.669 | 1.5035 | 1.345 | 2.007 | 4.5174 | 3.0139 | 1.9181 | 3.4216 | 7.9391 | 10.953 | -3.9303 | 5.8484 | 1.669 | 1.5035 | 1.345 | 2.007 | 4.5174 | 3.0239 | 1.9181 | 3.4216 | 7.9391 | 10.963 | 0.01
11.6169 | 9.217 | 2.1872 | 2.2808 | 3.9362 | 3.5617 | 8.4042 | 6.1234 | 20.8339 | 23.1148 | 31.519 | 37.6424 | 11.6169 | 9.217 | 2.1872 | 2.2808 | 3.9362 | 3.5617 | 8.4042 | 6.1334 | 20.8339 | 23.1148 | 31.519 | 37.6524 | 0.01
6.6067 | 8.1315 | 2.0202 | 2.0303 | 3.1011 | 3.0607 | 7.1517 | 5.1213 | 14.7382 | 16.7685 | 23.9202 | 29.0415 | 6.6067 | 8.1315 | 2.0202 | 2.0303 | 3.1011 | 3.0607 | 7.1517 | 5.1313 | 14.7382 | 16.7685 | 23.9202 | 29.0515 | 0.01
3.6787 | 7.4971 | 1.9226 | 1.8839 | 2.6131 | 2.7679 | 6.4197 | 4.5357 | 11.1758 | 13.0597 | 19.4794 | 24.0151 | 3.6787 | 7.4971 | 1.9226 | 1.8839 | 2.6131 | 2.7679 | 6.4197 | 4.5457 | 11.1758 | 13.0597 | 19.4794 | 24.0251 | 0.01
10.0022 | 8.8671 | 2.1334 | 2.2001 | 3.667 | 3.4002 | 8.0005 | 5.8004 | 18.8693 | 21.0694 | 29.07 | 34.8704 | 10.0022 | 8.8671 | 2.1334 | 2.2001 | 3.667 | 3.4002 | 8.0005 | 5.8104 | 18.8693 | 21.0694 | 29.07 | 34.8804 | 0.01
2.8576 | 7.3192 | 1.8953 | 1.8429 | 2.4763 | 2.6858 | 6.2144 | 4.3715 | 10.1768 | 12.0197 | 18.2341 | 22.6056 | 2.8576 | 7.3192 | 1.8953 | 1.8429 | 2.4763 | 2.6858 | 6.2144 | 4.3815 | 10.1768 | 12.0197 | 18.2341 | 22.6156 | 0.01
-5.7356 | 5.4573 | 1.6088 | 1.4132 | 1.0441 | 1.8264 | 4.0661 | 2.6529 | -0.2783 | 1.1349 | 5.201 | 7.8539 | -5.7356 | 5.4573 | 1.6088 | 1.4132 | 1.0441 | 1.8264 | 4.0661 | 2.6629 | -0.2783 | 1.1349 | 5.201 | 7.8639 | 0.01
-0.24152 | 6.6477 | 1.7919 | 1.6879 | 1.9597 | 2.3758 | 5.4396 | 3.7517 | 6.4062 | 8.0941 | 13.5337 | 17.2854 | -0.24152 | 6.6477 | 1.7919 | 1.6879 | 1.9597 | 2.3758 | 5.4396 | 3.7617 | 6.4062 | 8.0941 | 13.5337 | 17.2954 | 0.01
-1.1184 | 6.4577 | 1.7627 | 1.6441 | 1.8136 | 2.2882 | 5.2204 | 3.5763 | 5.3393 | 6.9834 | 12.2038 | 15.7801 | -1.1184 | 6.4577 | 1.7627 | 1.6441 | 1.8136 | 2.2882 | 5.2204 | 3.5863 | 5.3393 | 6.9834 | 12.2038 | 15.7901 | 0.01
9.8841 | 8.8416 | 1.6146 | 2.1942 | 3.6474 | 3.3884 | 7.971 | 5.7768 | 18.7257 | 20.9199 | 28.891 | 34.6678 | 9.8841 | 8.8416 | 1.6146 | 2.1942 | 3.6474 | 3.3884 | 7.971 | 5.7868 | 18.7257 | 20.9199 | 28.891 | 34.6778 | 0.01
-5.5634 | 5.4946 | 1.9328 | 1.4218 | 1.0728 | 1.8437 | 4.1091 | 2.6873 | -0.068833 | 1.353 | 5.4621 | 8.1495 | -5.5634 | 5.4946 | 1.9328 | 1.4218 | 1.0728 | 1.8437 | 4.1091 | 2.6973 | -0.068833 | 1.353 | 5.4621 | 8.1595 | 0.01
3.9837 | 7.5631 | 2.3331 | 1.8992 | 2.6639 | 2.7984 | 6.4959 | 4.5967 | 11.5468 | 13.446 | 19.9419 | 24.5386 | 3.9837 | 7.5631 | 2.3331 | 1.8992 | 2.6639 | 2.7984 | 6.4959 | 4.6067 | 11.5468 | 13.446 | 19.9419 | 24.5486 | 0.01
15.9941 | 10.1654 | 1.7859 | 2.4997 | 4.6657 | 3.9994 | 9.4985 | 6.9988 | 26.1595 | 28.6592 | 38.1577 | 45.1566 | 15.9941 | 10.1654 | 1.7859 | 2.4997 | 4.6657 | 3.9994 | 9.4985 | 7.0088 | 26.1595 | 28.6592 | 38.1577 | 45.1666 | 0.01
-0.42261 | 6.6084 | 1.794 | 1.6789 | 1.9296 | 2.3577 | 5.3943 | 3.7155 | 6.1858 | 7.8647 | 13.259 | 16.9745 | -0.42261 | 6.6084 | 1.794 | 1.6789 | 1.9296 | 2.3577 | 5.3943 | 3.7255 | 6.1858 | 7.8647 | 13.259 | 16.9845 | 0.01
-0.18131 | 6.6607 | 1.9908 | 1.6909 | 1.9698 | 2.3819 | 5.4547 | 3.7637 | 6.4794 | 8.1703 | 13.625 | 17.3887 | -0.18131 | 6.6607 | 1.9908 | 1.6909 | 1.9698 | 2.3819 | 5.4547 | 3.7737 | 6.4794 | 8.1703 | 13.625 | 17.3987 | 0.01
5.7226 | 7.9399 | 2.0474 | 1.9861 | 2.9538 | 2.9723 | 6.9306 | 4.9445 | 13.6625 | 15.6486 | 22.5792 | 27.5238 | 5.7226 | 7.9399 | 2.0474 | 1.9861 | 2.9538 | 2.9723 | 6.9306 | 4.9545 | 13.6625 | 15.6486 | 22.5792 | 27.5338 | 0.01
7.4208 | 8.3078 | 2.0177 | 2.071 | 3.2368 | 3.1421 | 7.3552 | 5.2842 | 15.7286 | 17.7997 | 25.1549 | 30.439 | 7.4208 | 8.3078 | 2.0177 | 2.071 | 3.2368 | 3.1421 | 7.3552 | 5.2942 | 15.7286 | 17.7997 | 25.1549 | 30.449 | 0.01
6.5317 | 8.1152 | 2.2316 | 2.0266 | 3.0886 | 3.0532 | 7.1329 | 5.1063 | 14.6469 | 16.6735 | 23.8064 | 28.9127 | 6.5317 | 8.1152 | 2.2316 | 2.0266 | 3.0886 | 3.0532 | 7.1329 | 5.1163 | 14.6469 | 16.6735 | 23.8064 | 28.9227 | 0.01
12.9487 | 9.5056 | 2.2484 | 2.3474 | 4.1581 | 3.6949 | 8.7372 | 6.3897 | 22.4543 | 24.8017 | 33.5389 | 39.9286 | 12.9487 | 9.5056 | 2.2484 | 2.3474 | 4.1581 | 3.6949 | 8.7372 | 6.3997 | 22.4543 | 24.8017 | 33.5389 | 39.9386 | 0.01
13.4512 | 9.6144 | 1.8607 | 2.3726 | 4.2419 | 3.7451 | 8.8628 | 6.4902 | 23.0656 | 25.4382 | 34.301 | 40.7912 | 13.4512 | 9.6144 | 1.8607 | 2.3726 | 4.2419 | 3.7451 | 8.8628 | 6.5002 | 23.0656 | 25.4382 | 34.301 | 40.8012 | 0.01
1.8217 | 7.0947 | 2.0947 | 1.7911 | 2.3036 | 2.5822 | 5.9554 | 4.1643 | 8.9164 | 10.7075 | 16.6629 | 20.8272 | 1.8217 | 7.0947 | 2.0947 | 1.7911 | 2.3036 | 2.5822 | 5.9554 | 4.1743 | 8.9164 | 10.7075 | 16.6629 | 20.8372 | 0.01
8.8397 | 8.6153 | 1.8922 | 2.142 | 3.4733 | 3.284 | 7.7099 | 5.5679 | 17.455 | 19.597 | 27.3069 | 32.8748 | 8.8397 | 8.6153 | 1.8922 | 2.142 | 3.4733 | 3.284 | 7.7099 | 5.5779 | 17.455 | 19.597 | 27.3069 | 32.8848 | 0.01
2.7666 | 7.2994 | 2.0757 | 1.8383 | 2.4611 | 2.6767 | 6.1916 | 4.3533 | 10.066 | 11.9043 | 18.0959 | 22.4493 | 2.7666 | 7.2994 | 2.0757 | 1.8383 | 2.4611 | 2.6767 | 6.1916 | 4.3633 | 10.066 | 11.9043 | 18.0959 | 22.4593 | 0.01
8.2722 | 8.4923 | 1.8633 | 2.1136 | 3.3787 | 3.2272 | 7.568 | 5.4544 | 16.7645 | 18.8781 | 26.4461 | 31.9006 | 8.2722 | 8.4923 | 1.8633 | 2.1136 | 3.3787 | 3.2272 | 7.568 | 5.4644 | 16.7645 | 18.8781 | 26.4461 | 31.9106 | 0.01
1.8989 | 7.1114 | 2.0766 | 1.7949 | 2.3165 | 2.5899 | 5.9747 | 4.1798 | 9.0103 | 10.8052 | 16.7799 | 20.9597 | 1.8989 | 7.1114 | 2.0766 | 1.7949 | 2.3165 | 2.5899 | 5.9747 | 4.1898 | 9.0103 | 10.8052 | 16.7799 | 20.9697 | 0.01
8.2977 | 8.4978 | 2.1503 | 2.1149 | 3.3829 | 3.2298 | 7.5744 | 5.4595 | 16.7955 | 18.9104 | 26.4848 | 31.9444 | 8.2977 | 8.4978 | 2.1503 | 2.1149 | 3.3829 | 3.2298 | 7.5744 | 5.4695 | 16.7955 | 18.9104 | 26.4848 | 31.9544 | 0.01
10.5101 | 8.9772 | 2.0598 | 2.2255 | 3.7517 | 3.451 | 8.1275 | 5.902 | 19.4873 | 21.7128 | 29.8404 | 35.7424 | 10.5101 | 8.9772 | 2.0598 | 2.2255 | 3.7517 | 3.451 | 8.1275 | 5.912 | 19.4873 | 21.7128 | 29.8404 | 35.7524 | 0.01
7.7932 | 8.3885 | 2.4427 | 2.0897 | 3.2989 | 3.1793 | 7.4483 | 5.3586 | 16.1817 | 18.2714 | 25.7197 | 31.0784 | 7.7932 | 8.3885 | 2.4427 | 2.0897 | 3.2989 | 3.1793 | 7.4483 | 5.3686 | 16.1817 | 18.2714 | 25.7197 | 31.0884 | 0.01
19.2796 | 10.8773 | 1.7714 | 2.664 | 5.2133 | 4.328 | 10.3199 | 7.6559 | 30.1569 | 32.8209 | 43.1408 | 50.7967 | 19.2796 | 10.8773 | 1.7714 | 2.664 | 5.2133 | 4.328 | 10.3199 | 7.6659 | 30.1569 | 32.8209 | 43.1408 | 50.8067 | 0.01
-0.85792 | 6.5141 | 1.9787 | 1.6571 | 1.857 | 2.3142 | 5.2855 | 3.6284 | 5.6562 | 7.3133 | 12.5988 | 16.2272 | -0.85792 | 6.5141 | 1.9787 | 1.6571 | 1.857 | 2.3142 | 5.2855 | 3.6384 | 5.6562 | 7.3133 | 12.5988 | 16.2372 | 0.01
5.3618 | 7.8617 | 2.1086 | 1.9681 | 2.8936 | 2.9362 | 6.8405 | 4.8724 | 13.2236 | 15.1917 | 22.0321 | 26.9045 | 5.3618 | 7.8617 | 2.1086 | 1.9681 | 2.8936 | 2.9362 | 6.8405 | 4.8824 | 13.2236 | 15.1917 | 22.0321 | 26.9145 | 0.01
9.2577 | 8.7058 | 2.1426 | 2.1629 | 3.543 | 3.3258 | 7.8144 | 5.6515 | 17.9635 | 20.1264 | 27.9408 | 33.5924 | 9.2577 | 8.7058 | 2.1426 | 2.1629 | 3.543 | 3.3258 | 7.8144 | 5.6615 | 17.9635 | 20.1264 | 27.9408 | 33.6024 | 0.01
10.2787 | 8.9271 | 2.2081 | 2.2139 | 3.7131 | 3.4279 | 8.0697 | 5.8557 | 19.2058 | 21.4197 | 29.4894 | 35.3451 | 10.2787 | 8.9271 | 2.2081 | 2.2139 | 3.7131 | 3.4279 | 8.0697 | 5.8657 | 19.2058 | 21.4197 | 29.4894 | 35.3551 | 0.01
12.2433 | 9.3527 | 1.7133 | 2.3122 | 4.0406 | 3.6243 | 8.5608 | 6.2487 | 21.5961 | 23.9082 | 32.4691 | 38.7177 | 12.2433 | 9.3527 | 1.7133 | 2.3122 | 4.0406 | 3.6243 | 8.5608 | 6.2587 | 21.5961 | 23.9082 | 32.4691 | 38.7277 | 0.01
-2.602 | 6.1362 | 2.0305 | 1.5699 | 1.5663 | 2.1398 | 4.8495 | 3.2796 | 3.5343 | 5.1042 | 9.9537 | 13.2333 | -2.602 | 6.1362 | 2.0305 | 1.5699 | 1.5663 | 2.1398 | 4.8495 | 3.2896 | 3.5343 | 5.1042 | 9.9537 | 13.2433 | 0.01
6.9152 | 8.1983 | 1.9055 | 2.0458 | 3.1525 | 3.0915 | 7.2288 | 5.183 | 15.1135 | 17.1593 | 24.3881 | 29.5711 | 6.9152 | 8.1983 | 1.9055 | 2.0458 | 3.1525 | 3.0915 | 7.2288 | 5.193 | 15.1135 | 17.1593 | 24.3881 | 29.5811 | 0.01
3.1651 | 7.3858 | 2.0144 | 1.8583 | 2.5275 | 2.7165 | 6.2913 | 4.433 | 10.5509 | 12.4091 | 18.7004 | 23.1334 | 3.1651 | 7.3858 | 2.0144 | 1.8583 | 2.5275 | 2.7165 | 6.2913 | 4.443 | 10.5509 | 12.4091 | 18.7004 | 23.1434 | 0.01
6.4306 | 8.0933 | 1.864 | 2.0215 | 3.0718 | 3.0431 | 7.1076 | 5.0861 | 14.5239 | 16.5454 | 23.653 | 28.7391 | 6.4306 | 8.0933 | 1.864 | 2.0215 | 3.0718 | 3.0431 | 7.1076 | 5.0961 | 14.5239 | 16.5454 | 23.653 | 28.7491 | 0.01
1.919 | 7.1158 | 1.9736 | 1.7959 | 2.3198 | 2.5919 | 5.9797 | 4.1838 | 9.0347 | 10.8307 | 16.8104 | 20.9942 | 1.919 | 7.1158 | 1.9736 | 1.7959 | 2.3198 | 2.5919 | 5.9797 | 4.1938 | 9.0347 | 10.8307 | 16.8104 | 21.0042 | 0.01
5.2075 | 7.8283 | 1.9672 | 1.9604 | 2.8679 | 2.9207 | 6.8019 | 4.8415 | 13.0358 | 14.9962 | 21.798 | 26.6395 | 5.2075 | 7.8283 | 1.9672 | 1.9604 | 2.8679 | 2.9207 | 6.8019 | 4.8515 | 13.0358 | 14.9962 | 21.798 | 26.6495 | 0.01
5.0148 | 7.7865 | 1.9804 | 1.9507 | 2.8358 | 2.9015 | 6.7537 | 4.803 | 12.8013 | 14.7521 | 21.5058 | 26.3087 | 5.0148 | 7.7865 | 1.9804 | 1.9507 | 2.8358 | 2.9015 | 6.7537 | 4.813 | 12.8013 | 14.7521 | 21.5058 | 26.3187 | 0.01
5.4118 | 7.8725 | 1.82 | 1.9706 | 2.902 | 2.9412 | 6.8529 | 4.8824 | 13.2843 | 15.2549 | 22.1078 | 26.9902 | 5.4118 | 7.8725 | 1.82 | 1.9706 | 2.902 | 2.9412 | 6.8529 | 4.8924 | 13.2843 | 15.2549 | 22.1078 | 27.0002 | 0.01
0.60033 | 6.8301 | 2.1284 | 1.73 | 2.1001 | 2.46 | 5.6501 | 3.9201 | 7.4304 | 9.1604 | 14.8105 | 18.7306 | 0.60033 | 6.8301 | 2.1284 | 1.73 | 2.1001 | 2.46 | 5.6501 | 3.9301 | 7.4304 | 9.1604 | 14.8105 | 18.7406 | 0.01
9.8505 | 8.8343 | 1.9956 | 2.1925 | 3.6418 | 3.3851 | 7.9626 | 5.7701 | 18.6848 | 20.8773 | 28.84 | 34.6101 | 9.8505 | 8.8343 | 1.9956 | 2.1925 | 3.6418 | 3.3851 | 7.9626 | 5.7801 | 18.6848 | 20.8773 | 28.84 | 34.6201 | 0.01
5.8682 | 7.9714 | 1.8458 | 1.9934 | 2.978 | 2.9868 | 6.9671 | 4.9736 | 13.8396 | 15.8331 | 22.8001 | 27.7737 | 5.8682 | 7.9714 | 1.8458 | 1.9934 | 2.978 | 2.9868 | 6.9671 | 4.9836 | 13.8396 | 15.8331 | 22.8001 | 27.7837 | 0.01
1.3746 | 6.9978 | 2.3455 | 1.7687 | 2.2291 | 2.5375 | 5.8436 | 4.0749 | 8.3724 | 10.1411 | 15.9848 | 20.0597 | 1.3746 | 6.9978 | 2.3455 | 1.7687 | 2.2291 | 2.5375 | 5.8436 | 4.0849 | 8.3724 | 10.1411 | 15.9848 | 20.0697 | 0.01
16.3663 | 10.246 | 2.1493 | 2.5183 | 4.7277 | 4.0366 | 9.5916 | 7.0733 | 26.6123 | 29.1306 | 38.7222 | 45.7954 | 16.3663 | 10.246 | 2.1493 | 2.5183 | 4.7277 | 4.0366 | 9.5916 | 7.0833 | 26.6123 | 29.1306 | 38.7222 | 45.8054 | 0.01
10.4785 | 8.9703 | 2.2881 | 2.2239 | 3.7464 | 3.4479 | 8.1196 | 5.8957 | 19.4488 | 21.6728 | 29.7924 | 35.6881 | 10.4785 | 8.9703 | 2.2881 | 2.2239 | 3.7464 | 3.4479 | 8.1196 | 5.9057 | 19.4488 | 21.6728 | 29.7924 | 35.6981 | 0.01
14.6431 | 9.8727 | 2.1757 | 2.4322 | 4.4405 | 3.8643 | 9.1608 | 6.7286 | 24.5157 | 26.9479 | 36.1087 | 42.8373 | 14.6431 | 9.8727 | 2.1757 | 2.4322 | 4.4405 | 3.8643 | 9.1608 | 6.7386 | 24.5157 | 26.9479 | 36.1087 | 42.8473 | 0.01
11.2705 | 9.1419 | 1.6904 | 2.2635 | 3.8784 | 3.5271 | 8.3176 | 6.0541 | 20.4125 | 22.676 | 30.9936 | 37.0477 | 11.2705 | 9.1419 | 1.6904 | 2.2635 | 3.8784 | 3.5271 | 8.3176 | 6.0641 | 20.4125 | 22.676 | 30.9936 | 37.0577 | 0.01
-3.2871 | 5.9878 | 1.9339 | 1.5356 | 1.4522 | 2.0713 | 4.6782 | 3.1426 | 2.7008 | 4.2364 | 8.9146 | 12.0572 | -3.2871 | 5.9878 | 1.9339 | 1.5356 | 1.4522 | 2.0713 | 4.6782 | 3.1526 | 2.7008 | 4.2364 | 8.9146 | 12.0672 | 0.01
4.0163 | 7.5702 | 1.9562 | 1.9008 | 2.6694 | 2.8016 | 6.5041 | 4.6033 | 11.5865 | 13.4873 | 19.9914 | 24.5946 | 4.0163 | 7.5702 | 1.9562 | 1.9008 | 2.6694 | 2.8016 | 6.5041 | 4.6133 | 11.5865 | 13.4873 | 19.9914 | 24.6046 | 0.01
4.6864 | 7.7154 | 1.8488 | 1.9343 | 2.7811 | 2.8686 | 6.6716 | 4.7373 | 12.4018 | 14.3361 | 21.0078 | 25.745 | 4.6864 | 7.7154 | 1.8488 | 1.9343 | 2.7811 | 2.8686 | 6.6716 | 4.7473 | 12.4018 | 14.3361 | 21.0078 | 25.755 | 0.01
1.4634 | 7.0171 | 1.7742 | 1.7732 | 2.2439 | 3.5791 | 5.8659 | 4.0927 | 8.4805 | 10.2536 | 16.1195 | 20.2122 | 1.4634 | 7.0171 | 1.7742 | 1.7732 | 2.2439 | 3.5791 | 5.8659 | 4.1027 | 8.4805 | 10.2536 | 16.1195 | 20.2222 | 0.01
-0.77368 | 6.5324 | 2.193 | 1.6613 | 1.8711 | 1.6857 | 5.3066 | 3.6453 | 5.7587 | 7.42 | 12.7266 | 16.3718 | -0.77368 | 6.5324 | 2.193 | 1.6613 | 1.8711 | 1.6857 | 5.3066 | 3.6553 | 5.7587 | 7.42 | 12.7266 | 16.3818 | 0.01
11.7905 | 9.2546 | 1.5619 | 2.2895 | 3.9651 | 2.9119 | 8.4476 | 6.1581 | 21.0451 | 23.3346 | 31.7823 | 37.9404 | 11.7905 | 9.2546 | 1.5619 | 2.2895 | 3.9651 | 2.9119 | 8.4476 | 6.1681 | 21.0451 | 23.3346 | 31.7823 | 37.9504 | 0.01
-7.1426 | 5.1524 | 1.9706 | 1.3429 | 0.80957 | 3.4348 | 3.7144 | 2.3715 | -1.9901 | -0.64725 | 3.5972 | 5.9687 | -7.1426 | 5.1524 | 1.9706 | 1.3429 | 0.80957 | 3.4348 | 3.7144 | 2.3815 | -1.9901 | -0.64725 | 3.5972 | 5.9787 | 0.01
5.1192 | 7.8092 | 2.1449 | 1.956 | 2.8532 | 3.9823 | 6.7798 | 4.8238 | 12.9284 | 14.8844 | 21.7198 | 26.5437 | 5.1192 | 7.8092 | 2.1449 | 1.956 | 2.8532 | 3.9823 | 6.7798 | 4.8338 | 12.9284 | 14.8844 | 21.7198 | 26.5537 | 0.01
10.3484 | 8.9421 | 2.3274 | 2.2174 | 3.7247 | 2.3004 | 8.0871 | 5.8697 | 19.2905 | 21.5079 | 29.595 | 35.4647 | 10.3484 | 8.9421 | 2.3274 | 2.2174 | 3.7247 | 2.3004 | 8.0871 | 5.8797 | 19.2905 | 21.5079 | 29.595 | 35.4747 | 0.01
15.8226 | 10.1282 | 1.7668 | 2.4911 | 4.6371 | 1.4393 | 9.4556 | 6.9645 | 25.9508 | 28.442 | 37.8976 | 44.8621 | 15.8226 | 10.1282 | 1.7668 | 2.4911 | 4.6371 | 1.4393 | 9.4556 | 6.9745 | 25.9508 | 28.442 | 37.8976 | 44.8721 | 0.01
-0.99638 | 6.4841 | 1.4798 | 1.6502 | 1.8339 | 2.1554 | 5.2509 | 3.6007 | 5.4877 | 7.1379 | 12.3888 | 15.9895 | -0.99638 | 6.4841 | 1.4798 | 1.6502 | 1.8339 | 2.1554 | 5.2509 | 3.6107 | 5.4877 | 7.1379 | 12.3888 | 15.9995 | 0.01
-9.6069 | 4.6185 | 1.7185 | 1.2197 | 0.39885 | 2.5843 | 4.8886 | 1.8786 | -4.9884 | -3.7688 | 1.1198 | 2.9984 | -9.6069 | 4.6185 | 1.7185 | 1.2197 | 0.39885 | 2.5843 | 4.8886 | 1.8886 | -4.9884 | -3.7688 | 1.1198 | 3.0084 | 0.01
-2.4456 | 6.1701 | 1.8614 | 1.5777 | 1.5924 | 2.3528 | 5.9607 | 3.3109 | 3.7245 | 5.3022 | 11.2629 | 14.5738 | -2.4456 | 6.1701 | 1.8614 | 1.5777 | 1.5924 | 2.3528 | 5.9607 | 3.3209 | 3.7245 | 5.3022 | 11.2629 | 14.5838 | 0.01
1.8427 | 7.0993 | 1.7843 | 1.7921 | 2.3071 | 2.7307 | 5.3821 | 4.1685 | 8.942 | 10.7341 | 16.1162 | 20.2847 | 1.8427 | 7.0993 | 1.7843 | 1.7921 | 2.3071 | 2.7307 | 5.3821 | 4.1785 | 8.942 | 10.7341 | 16.1162 | 20.2947 | 0.01
-0.47175 | 6.5978 | 1.9102 | 1.6764 | 1.9214 | 2.5396 | 6.3268 | 3.7057 | 6.126 | 7.8025 | 14.1292 | 17.8349 | -0.47175 | 6.5978 | 1.9102 | 1.6764 | 1.9214 | 2.5396 | 6.3268 | 3.7157 | 6.126 | 7.8025 | 14.1292 | 17.8449 | 0.01
3.3071 | 7.4165 | 1.8465 | 1.7698 | 2.5512 | 2.4087 | 5.8491 | 4.4614 | 10.7236 | 12.4935 | 18.3426 | 22.804 | 3.3071 | 7.4165 | 1.8465 | 1.7698 | 2.5512 | 2.4087 | 5.8491 | 4.4714 | 10.7236 | 12.4935 | 18.3426 | 22.814 | 0.01
1.3965 | 7.0026 | 1.8029 | 1.7043 | 2.2327 | 3.3494 | 5.5217 | 4.0793 | 8.399 | 10.1034 | 15.6855 | 19.7648 | 1.3965 | 7.0026 | 1.8029 | 1.7043 | 2.2327 | 3.3494 | 5.5217 | 4.0893 | 8.399 | 10.1034 | 15.6855 | 19.7748 | 0.01
0.08672 | 6.7188 | 2.1165 | 2.1747 | 2.0145 | 3.9835 | 7.8734 | 3.8173 | 6.8055 | 8.9802 | 16.8536 | 20.671 | 0.08672 | 6.7188 | 2.1165 | 2.1747 | 2.0145 | 3.9835 | 7.8734 | 3.8273 | 6.8055 | 8.9802 | 16.8536 | 20.681 | 0.01
9.4938 | 8.757 | 2.3278 | 2.4917 | 3.5823 | 3.2911 | 9.4587 | 5.6988 | 18.2508 | 20.7425 | 30.2012 | 35.8999 | 9.4938 | 8.757 | 2.3278 | 2.4917 | 3.5823 | 3.2911 | 9.4587 | 5.7088 | 18.2508 | 20.7425 | 30.2012 | 35.9099 | 0.01
15.8348 | 10.1309 | 2.097 | 2.1455 | 4.6391 | 3.8318 | 7.7276 | 6.967 | 25.9657 | 28.1112 | 36.5822 | 43.5491 | 15.8348 | 10.1309 | 2.097 | 2.1455 | 4.6391 | 3.8318 | 7.7276 | 6.977 | 25.9657 | 28.1112 | 36.5822 | 43.5591 | 0.01
8.9106 | 8.6306 | 2.2773 | 2.4159 | 3.4851 | 2.4722 | 9.0796 | 5.5821 | 17.5412 | 19.9571 | 29.0368 | 34.6189 | 8.9106 | 8.6306 | 2.2773 | 2.4159 | 3.4851 | 2.4722 | 9.0796 | 5.5921 | 17.5412 | 19.9571 | 29.0368 | 34.6289 | 0.01
14.3184 | 9.8023 | 1.8241 | 1.7361 | 4.3864 | 3.1013 | 5.6806 | 6.6637 | 24.1208 | 25.8569 | 33.3446 | 40.0083 | 14.3184 | 9.8023 | 1.8241 | 1.7361 | 4.3864 | 3.1013 | 5.6806 | 6.6737 | 24.1208 | 25.8569 | 33.3446 | 40.0183 | 0.01
0.7224 | 6.8565 | 2.0338 | 2.0506 | 2.1204 | 4.3384 | 7.2532 | 3.9445 | 7.5789 | 9.6296 | 16.8828 | 20.8273 | 0.7224 | 6.8565 | 2.0338 | 2.0506 | 2.1204 | 4.3384 | 7.2532 | 3.9545 | 7.5789 | 9.6296 | 16.8828 | 20.8373 | 0.01
7.0128 | 8.2194 | 2.4461 | 2.6692 | 3.1688 | 1.3988 | 10.346 | 5.2026 | 15.2323 | 17.9015 | 28.2475 | 33.45 | 7.0128 | 8.2194 | 2.4461 | 2.6692 | 3.1688 | 1.3988 | 10.346 | 5.2126 | 15.2323 | 17.9015 | 28.2475 | 33.46 | 0.01
19.384 | 10.8999 | 1.4663 | 1.1994 | 5.2307 | 4.3226 | 2.9969 | 7.6768 | 30.2838 | 31.4832 | 41.0365 | 48.7133 | 19.384 | 10.8999 | 1.4663 | 1.1994 | 5.2307 | 4.3226 | 2.9969 | 7.6868 | 30.2838 | 31.4832 | 41.0365 | 48.7233 | 0.01
19.2262 | 4.5307 | 2.4409 | 2.6613 | 0.33129 | 3.8214 | 10.3065 | 1.7975 | 23.7568 | 26.4181 | 36.7247 | 38.5222 | 19.2262 | 4.5307 | 2.4409 | 2.6613 | 0.33129 | 3.8214 | 10.3065 | 1.8075 | 23.7568 | 26.4181 | 36.7247 | 38.5322 | 0.01
14.2142 | 10.8657 | 2.2738 | 2.4107 | 5.2044 | 2.1505 | 9.0535 | 7.6452 | 25.0798 | 27.4905 | 36.5441 | 44.1893 | 14.2142 | 10.8657 | 2.2738 | 2.4107 | 5.2044 | 2.1505 | 9.0535 | 7.6552 | 25.0798 | 27.4905 | 36.5441 | 44.1993 | 0.01
-2.4952 | 9.7797 | 1.7168 | 1.5752 | 4.369 | 3.5234 | 4.8762 | 6.6428 | 7.2846 | 8.8598 | 16.7522 | 23.395 | -2.4952 | 9.7797 | 1.7168 | 1.5752 | 4.369 | 3.5234 | 4.8762 | 6.6528 | 7.2846 | 8.8598 | 16.7522 | 23.405 | 0.01
11.2336 | 6.1594 | 2.1745 | 2.2617 | 1.5841 | 4.0163 | 8.3084 | 3.301 | 17.393 | 19.6547 | 27.9631 | 31.2641 | 11.2336 | 6.1594 | 2.1745 | 2.2617 | 1.5841 | 4.0163 | 8.3084 | 3.311 | 17.393 | 19.6547 | 27.9631 | 31.2741 | 0.01
16.1635 | 9.134 | 2.3388 | 2.5082 | 3.8723 | 2.7069 | 9.5409 | 6.0467 | 25.2974 | 27.8056 | 37.3465 | 43.3932 | 16.1635 | 9.134 | 2.3388 | 2.5082 | 3.8723 | 2.7069 | 9.5409 | 6.0567 | 25.2974 | 27.8056 | 37.3465 | 43.4032 | 0.01
3.0691 | 10.2021 | 1.9023 | 1.8535 | 4.2369 | 3.7422 | 6.2673 | 7.0327 | 13.2711 | 15.1246 | 23.1037 | 30.1364 | 3.0691 | 10.2021 | 1.9023 | 1.8535 | 4.2369 | 3.7422 | 6.2673 | 7.0427 | 13.2711 | 15.1246 | 23.1037 | 30.1464 | 0.01
13.4216 | 7.365 | 2.2474 | 2.3711 | 4.3798 | 3.8279 | 8.8554 | 4.4138 | 20.7866 | 23.1577 | 32.0131 | 36.4269 | 13.4216 | 7.365 | 2.2474 | 2.3711 | 4.3798 | 3.8279 | 8.8554 | 4.4238 | 20.7866 | 23.1577 | 32.0131 | 36.4369 | 0.01
14.2791 | 9.608 | 2.276 | 2.414 | 2.4376 | 2.6625 | 9.0698 | 6.4843 | 23.8871 | 26.301 | 35.3708 | 41.8551 | 14.2791 | 9.608 | 2.276 | 2.414 | 2.4376 | 2.6625 | 9.0698 | 6.4943 | 23.8871 | 26.301 | 35.3708 | 41.8651 | 0.01
2.6253 | 9.7938 | 1.8875 | 1.8313 | 0.72184 | 1.6331 | 6.1563 | 6.6558 | 12.4191 | 14.2504 | 20.4067 | 27.0625 | 2.6253 | 9.7938 | 1.8875 | 1.8313 | 0.72184 | 1.6331 | 6.1563 | 6.6658 | 12.4191 | 14.2504 | 20.4067 | 27.0725 | 0.01
-7.6689 | 7.2688 | 1.5444 | 1.3166 | 4.3164 | 3.7899 | 3.5828 | 4.3251 | -0.40013 | 0.91643 | 9.0227 | 13.3478 | -7.6689 | 7.2688 | 1.5444 | 1.3166 | 4.3164 | 3.7899 | 3.5828 | 4.3351 | -0.40013 | 0.91643 | 9.0227 | 13.3578 | 0.01
13.8987 | 5.0384 | 2.2633 | 2.3949 | 4.5377 | 3.9226 | 8.9747 | 2.2662 | 18.9371 | 21.332 | 30.3067 | 32.5729 | 13.8987 | 5.0384 | 2.2633 | 2.3949 | 4.5377 | 3.9226 | 8.9747 | 2.2762 | 18.9371 | 21.332 | 30.3067 | 32.5829 | 0.01
15.2263 | 9.7114 | 2.3075 | 2.4613 | 5.1783 | 4.307 | 9.3066 | 6.5797 | 24.9377 | 27.399 | 36.8844 | 43.4641 | 15.2263 | 9.7114 | 2.3075 | 2.4613 | 5.1783 | 4.307 | 9.3066 | 6.5897 | 24.9377 | 27.399 | 36.8844 | 43.4741 | 0.01
19.0701 | 9.999 | 2.4357 | 2.6535 | 1.7349 | 2.2409 | 10.2675 | 6.8453 | 29.0691 | 31.7226 | 41.9902 | 48.8354 | 19.0701 | 9.999 | 2.4357 | 2.6535 | 1.7349 | 2.2409 | 10.2675 | 6.8553 | 29.0691 | 31.7226 | 41.9902 | 48.8454 | 0.01
-1.5907 | 10.8319 | 1.747 | 1.6205 | 3.4667 | 3.28 | 5.1023 | 7.614 | 9.2411 | 10.8616 | 17.6083 | 25.2223 | -1.5907 | 10.8319 | 1.747 | 1.6205 | 3.4667 | 3.28 | 5.1023 | 7.624 | 9.2411 | 10.8616 | 17.6083 | 25.2323 | 0.01
8.8001 | 6.3553 | 2.0933 | 2.14 | 3.3661 | 3.2197 | 7.7 | 3.4819 | 15.1554 | 17.2954 | 24.9955 | 28.4773 | 8.8001 | 6.3553 | 2.0933 | 2.14 | 3.3661 | 3.2197 | 7.7 | 3.4919 | 15.1554 | 17.2954 | 24.9955 | 28.4873 | 0.01
8.1966 | 8.6067 | 2.0732 | 2.1098 | 2.9229 | 2.9538 | 7.5492 | 5.56 | 16.8033 | 18.9131 | 26.4623 | 32.0223 | 8.1966 | 8.6067 | 2.0732 | 2.1098 | 2.9229 | 2.9538 | 7.5492 | 5.57 | 16.8033 | 18.9131 | 26.4623 | 32.0323 | 0.01
5.5376 | 8.4759 | 1.9846 | 1.9769 | 2.3602 | 2.6161 | 6.8844 | 5.4393 | 14.0135 | 15.9904 | 22.8748 | 28.3141 | 5.5376 | 8.4759 | 1.9846 | 1.9769 | 2.3602 | 2.6161 | 6.8844 | 5.4493 | 14.0135 | 15.9904 | 22.8748 | 28.3241 | 0.01
2.1614 | 7.8998 | 1.872 | 1.8081 | 2.489 | 2.6934 | 6.0403 | 4.9075 | 10.0612 | 11.8692 | 17.9096 | 22.8171 | 2.1614 | 7.8998 | 1.872 | 1.8081 | 2.489 | 2.6934 | 6.0403 | 4.9175 | 10.0612 | 11.8692 | 17.9096 | 22.8271 | 0.01
2.9341 | 7.1683 | 1.8978 | 1.8467 | 3.9122 | 3.5473 | 6.2335 | 4.2323 | 10.1024 | 11.9491 | 19.4087 | 23.641 | 2.9341 | 7.1683 | 1.8978 | 1.8467 | 3.9122 | 3.5473 | 6.2335 | 4.2423 | 10.1024 | 11.9491 | 19.4087 | 23.651 | 0.01
11.4734 | 7.3357 | 2.1824 | 2.2737 | 4.5221 | 3.9133 | 8.3684 | 4.3868 | 18.8092 | 21.0828 | 29.5182 | 33.9051 | 11.4734 | 7.3357 | 2.1824 | 2.2737 | 4.5221 | 3.9133 | 8.3684 | 4.3968 | 18.8092 | 21.0828 | 29.5182 | 33.9151 | 0.01
15.1327 | 9.1859 | 2.3044 | 2.4566 | 3.0515 | 3.0309 | 9.2832 | 6.0947 | 24.3186 | 26.7752 | 36.0584 | 42.1531 | 15.1327 | 9.1859 | 2.3044 | 2.4566 | 3.0515 | 3.0309 | 9.2832 | 6.1047 | 24.3186 | 26.7752 | 36.0584 | 42.1631 | 0.01
6.309 | 9.9788 | 2.0103 | 2.0154 | 3.3918 | 3.2351 | 7.0772 | 6.8265 | 16.2877 | 18.3032 | 25.3804 | 32.207 | 6.309 | 9.9788 | 2.0103 | 2.0154 | 3.3918 | 3.2351 | 7.0772 | 6.8365 | 16.2877 | 18.3032 | 25.3804 | 32.217 | 0.01
8.3508 | 8.0669 | 2.0784 | 2.1175 | 3.9998 | 3.5999 | 7.5877 | 5.0618 | 16.4178 | 18.5353 | 26.135 | 31.1968 | 8.3508 | 8.0669 | 2.0784 | 2.1175 | 3.9998 | 3.5999 | 7.5877 | 5.0718 | 16.4178 | 18.5353 | 26.135 | 31.2068 | 0.01
11.9988 | 8.5093 | 2.2 | 2.2999 | 3.3774 | 3.2265 | 8.4997 | 5.4702 | 20.5081 | 22.808 | 31.3077 | 36.7779 | 11.9988 | 8.5093 | 2.2 | 2.2999 | 3.3774 | 3.2265 | 8.4997 | 5.4802 | 20.5081 | 22.808 | 31.3077 | 36.7879 | 0.01
8.2645 | 9.2997 | 2.0755 | 2.1132 | 2.4958 | 2.6975 | 7.5661 | 6.1998 | 17.5643 | 19.6775 | 27.2436 | 33.4434 | 8.2645 | 9.2997 | 2.0755 | 2.1132 | 2.4958 | 2.6975 | 7.5661 | 6.2098 | 17.5643 | 19.6775 | 27.2436 | 33.4534 | 0.01
2.9748 | 8.4906 | 1.8992 | 1.8487 | 3.6696 | 3.4018 | 6.2437 | 5.4529 | 11.4654 | 13.3142 | 20.3856 | 25.8385 | 2.9748 | 8.4906 | 1.8992 | 1.8487 | 3.6696 | 3.4018 | 6.2437 | 5.4629 | 11.4654 | 13.3142 | 20.3856 | 25.8485 | 0.01
10.0178 | 7.3445 | 2.1339 | 2.2009 | 2.3627 | 2.6176 | 8.0044 | 4.395 | 17.3623 | 19.5632 | 27.5677 | 31.9626 | 10.0178 | 7.3445 | 2.1339 | 2.2009 | 2.3627 | 2.6176 | 8.0044 | 4.405 | 17.3623 | 19.5632 | 27.5677 | 31.9726 | 0.01
2.1761 | 8.8705 | 1.8725 | 1.8088 | 3.6992 | 3.4195 | 6.044 | 5.8036 | 11.0466 | 12.8554 | 19.9742 | 25.7777 | 2.1761 | 8.8705 | 1.8725 | 1.8088 | 3.6992 | 3.4195 | 6.044 | 5.8136 | 11.0466 | 12.8554 | 19.9742 | 25.7877 | 0.01
10.1953 | 7.1715 | 2.1398 | 2.2098 | 2.0614 | 2.4368 | 8.0488 | 4.2352 | 17.3668 | 19.5765 | 27.6253 | 31.8606 | 10.1953 | 7.1715 | 2.1398 | 2.2098 | 2.0614 | 2.4368 | 8.0488 | 4.2452 | 17.3668 | 19.5765 | 27.6253 | 31.8706 | 0.01
0.36812 | 8.909 | 1.8123 | 1.7184 | 3.4738 | 3.2843 | 5.592 | 5.8391 | 9.2771 | 10.9955 | 17.7536 | 23.5926 | 0.36812 | 8.909 | 1.8123 | 1.7184 | 3.4738 | 3.2843 | 5.592 | 5.8491 | 9.2771 | 10.9955 | 17.7536 | 23.6026 | 0.01
8.8428 | 6.7798 | 2.0948 | 2.1421 | 2.5607 | 2.7364 | 7.7107 | 3.8736 | 15.6225 | 17.7647 | 25.4753 | 29.349 | 8.8428 | 6.7798 | 2.0948 | 2.1421 | 2.5607 | 2.7364 | 7.7107 | 3.8836 | 15.6225 | 17.7647 | 25.4753 | 29.359 | 0.01
3.3639 | 8.6159 | 1.9121 | 1.8682 | 3.7195 | 3.4317 | 6.341 | 5.5686 | 11.9799 | 13.8481 | 20.9992 | 26.5678 | 3.3639 | 8.6159 | 1.9121 | 1.8682 | 3.7195 | 3.4317 | 6.341 | 5.5786 | 11.9799 | 13.8481 | 20.9992 | 26.5778 | 0.01
10.3169 | 7.4289 | 2.1439 | 2.2158 | 4.0749 | 3.645 | 8.0792 | 4.4728 | 17.7457 | 19.9616 | 28.0408 | 32.5136 | 10.3169 | 7.4289 | 2.1439 | 2.2158 | 4.0749 | 3.645 | 8.0792 | 4.4828 | 17.7457 | 19.9616 | 28.0408 | 32.5236 | 0.01
12.4496 | 8.9353 | 2.215 | 2.3225 | 3.8485 | 3.5091 | 8.6124 | 5.8634 | 21.3849 | 23.7074 | 32.3198 | 38.1832 | 12.4496 | 8.9353 | 2.215 | 2.3225 | 3.8485 | 3.5091 | 8.6124 | 5.8734 | 21.3849 | 23.7074 | 32.3198 | 38.1932 | 0.01
11.0913 | 9.3974 | 2.1697 | 2.2546 | 1.6992 | 2.2195 | 8.2728 | 6.2899 | 20.4887 | 22.7433 | 31.0161 | 37.306 | 11.0913 | 9.3974 | 2.1697 | 2.2546 | 1.6992 | 2.2195 | 8.2728 | 6.2999 | 20.4887 | 22.7433 | 31.0161 | 37.316 | 0.01
-1.8049 | 9.1031 | 1.7398 | 1.6098 | 3.2226 | 3.1336 | 5.0488 | 6.0183 | 7.2982 | 8.908 | 15.2642 | 21.2824 | -1.8049 | 9.1031 | 1.7398 | 1.6098 | 3.2226 | 3.1336 | 5.0488 | 6.0283 | 7.2982 | 8.908 | 15.2642 | 21.2924 | 0.01
7.3357 | 6.3089 | 2.0445 | 2.0668 | 4.1585 | 3.6951 | 7.3339 | 3.439 | 13.6446 | 15.7114 | 23.565 | 27.004 | 7.3357 | 6.3089 | 2.0445 | 2.0668 | 4.1585 | 3.6951 | 7.3339 | 3.449 | 13.6446 | 15.7114 | 23.565 | 27.014 | 0.01
12.9509 | 8.2894 | 2.2317 | 2.3475 | 1.8244 | 2.2947 | 8.7377 | 5.2671 | 21.2403 | 23.5878 | 32.3255 | 37.5927 | 12.9509 | 8.2894 | 2.2317 | 2.3475 | 1.8244 | 2.2947 | 8.7377 | 5.2771 | 21.2403 | 23.5878 | 32.3255 | 37.6027 | 0.01
-1.0534 | 9.506 | 1.7649 | 1.6473 | 4.1219 | 3.6732 | 5.2366 | 6.3902 | 8.4526 | 10.0999 | 17.895 | 24.2852 | -1.0534 | 9.506 | 1.7649 | 1.6473 | 4.1219 | 3.6732 | 5.2366 | 6.4002 | 8.4526 | 10.0999 | 17.895 | 24.2952 | 0.01
12.7317 | 6.4718 | 2.2244 | 2.3366 | 2.2937 | 2.5762 | 8.6829 | 3.5893 | 19.2034 | 21.54 | 30.2229 | 33.8122 | 12.7317 | 6.4718 | 2.2244 | 2.3366 | 2.2937 | 2.5762 | 8.6829 | 3.5993 | 19.2034 | 21.54 | 30.2229 | 33.8222 | 0.01
1.7625 | 9.4585 | 1.8587 | 1.7881 | 4.4139 | 3.8484 | 5.9406 | 6.3463 | 11.221 | 13.0091 | 21.2714 | 27.6177 | 1.7625 | 9.4585 | 1.8587 | 1.7881 | 4.4139 | 3.8484 | 5.9406 | 6.3563 | 11.221 | 13.0091 | 21.2714 | 27.6277 | 0.01
14.4836 | 7.0819 | 2.2828 | 2.4242 | 2.818 | 2.8908 | 9.1209 | 4.1525 | 21.5654 | 23.9896 | 33.1105 | 37.263 | 14.4836 | 7.0819 | 2.2828 | 2.4242 | 2.818 | 2.8908 | 9.1209 | 4.1625 | 21.5654 | 23.9896 | 33.1105 | 37.273 | 0.01
4.908 | 9.8381 | 1.9636 | 1.9454 | 4.2124 | 3.7275 | 6.727 | 6.6967 | 14.7461 | 16.6915 | 24.6314 | 31.3281 | 4.908 | 9.8381 | 1.9636 | 1.9454 | 4.2124 | 3.7275 | 6.727 | 6.7067 | 14.7461 | 16.6915 | 24.6314 | 31.3381 | 0.01
13.2747 | 7.7634 | 2.2425 | 2.3637 | 2.6176 | 2.7706 | 8.8187 | 4.7816 | 21.0381 | 23.4018 | 32.2205 | 37.0021 | 13.2747 | 7.7634 | 2.2425 | 2.3637 | 2.6176 | 2.7706 | 8.8187 | 4.7916 | 21.0381 | 23.4018 | 32.2205 | 37.0121 | 0.01
3.7058 | 9.5762 | 1.9235 | 1.8853 | 4.0942 | 3.6565 | 6.4265 | 6.4549 | 13.282 | 15.1673 | 22.9179 | 29.3729 | 3.7058 | 9.5762 | 1.9235 | 1.8853 | 4.0942 | 3.6565 | 6.4265 | 6.4649 | 13.282 | 15.1673 | 22.9179 | 29.3829 | 0.01
12.5649 | 7.5029 | 2.2188 | 2.3282 | 2.7136 | 2.8282 | 8.6412 | 4.5412 | 20.0678 | 22.3961 | 31.0373 | 35.5785 | 12.5649 | 7.5029 | 2.2188 | 2.3282 | 2.7136 | 2.8282 | 8.6412 | 4.5512 | 20.0678 | 22.3961 | 31.0373 | 35.5885 | 0.01
4.2816 | 9.4224 | 1.9427 | 1.9141 | 1.5496 | 2.1298 | 6.5704 | 6.313 | 13.704 | 15.618 | 22.1884 | 28.5014 | 4.2816 | 9.4224 | 1.9427 | 1.9141 | 1.5496 | 2.1298 | 6.5704 | 6.323 | 13.704 | 15.618 | 22.1884 | 28.5114 | 0.01
-2.7021 | 7.6277 | 1.7099 | 1.5649 | 4.8215 | 4.0929 | 4.8245 | 4.6563 | 4.9255 | 6.4904 | 15.4048 | 20.0611 | -2.7021 | 7.6277 | 1.7099 | 1.5649 | 4.8215 | 4.0929 | 4.8245 | 4.6663 | 4.9255 | 6.4904 | 15.4048 | 20.0711 | 0.01
16.9289 | 6.1145 | 2.3643 | 2.5464 | 1.5666 | 2.14 | 9.7322 | 3.2596 | 23.0434 | 25.5899 | 35.3221 | 38.5817 | 16.9289 | 6.1145 | 2.3643 | 2.5464 | 1.5666 | 2.14 | 9.7322 | 3.2696 | 23.0434 | 25.5899 | 35.3221 | 38.5917 | 0.01
-2.6001 | 10.3679 | 1.7133 | 1.57 | 2.43 | 2.658 | 4.85 | 7.1858 | 7.7678 | 9.3378 | 14.4258 | 21.6116 | -2.6001 | 10.3679 | 1.7133 | 1.57 | 2.43 | 2.658 | 4.85 | 7.1958 | 7.7678 | 9.3378 | 14.4258 | 21.6216 | 0.01
2.5801 | 6.1366 | 1.886 | 1.829 | 0.74844 | 1.6491 | 6.145 | 3.28 | 8.7168 | 10.5458 | 16.6908 | 19.9708 | 2.5801 | 6.1366 | 1.886 | 1.829 | 0.74844 | 1.6491 | 6.145 | 3.29 | 8.7168 | 10.5458 | 16.6908 | 19.9808 | 0.01
-7.5094 | 7.259 | 1.5497 | 1.3245 | 3.3043 | 3.1826 | 3.6227 | 4.316 | -0.25035 | 1.0742 | 7.5611 | 11.8771 | -7.5094 | 7.259 | 1.5497 | 1.3245 | 3.3043 | 3.1826 | 3.6227 | 4.326 | -0.25035 | 1.0742 | 7.5611 | 11.8871 | 0.01
7.826 | 5.073 | 2.0609 | 2.0913 | 0.096747 | 1.258 | 7.4565 | 2.2981 | 12.899 | 14.9903 | 22.4468 | 24.7449 | 7.826 | 5.073 | 2.0609 | 2.0913 | 0.096747 | 1.258 | 7.4565 | 2.3081 | 12.899 | 14.9903 | 22.4468 | 24.7549 | 0.01
-11.4195 | 8.3956 | 1.4193 | 1.129 | 1.1507 | 1.8904 | 2.6451 | 5.3652 | -3.0239 | -1.8949 | 1.1462 | 6.5114 | -11.4195 | 8.3956 | 1.4193 | 1.129 | 1.1507 | 1.8904 | 2.6451 | 5.3752 | -3.0239 | -1.8949 | 1.1462 | 6.5214 | 0.01
-5.0961 | 4.2258 | 1.6301 | 1.4452 | 2.318 | 2.5908 | 4.226 | 1.5161 | -0.87032 | 0.57488 | 5.4837 | 6.9998 | -5.0961 | 4.2258 | 1.6301 | 1.4452 | 2.318 | 2.5908 | 4.226 | 1.5261 | -0.87032 | 0.57488 | 5.4837 | 7.0098 | 0.01
1.9081 | 5.5958 | 1.8636 | 1.7954 | 3.9068 | 3.5441 | 5.977 | 2.7808 | 7.5039 | 9.2993 | 16.7502 | 19.531 | 1.9081 | 5.5958 | 1.8636 | 1.7954 | 3.9068 | 3.5441 | 5.977 | 2.7908 | 7.5039 | 9.2993 | 16.7502 | 19.541 | 0.01
11.4408 | 7.1134 | 2.1814 | 2.272 | 3.9987 | 3.5992 | 8.3602 | 4.1816 | 18.5542 | 20.8263 | 29.1865 | 33.3681 | 11.4408 | 7.1134 | 2.1814 | 2.272 | 3.9987 | 3.5992 | 8.3602 | 4.1916 | 18.5542 | 20.8263 | 29.1865 | 33.3781 | 0.01
11.9924 | 9.1788 | 2.1997 | 2.2996 | 2.5211 | 2.7127 | 8.4981 | 6.0882 | 21.1712 | 23.4708 | 31.9689 | 38.0571 | 11.9924 | 9.1788 | 2.1997 | 2.2996 | 2.5211 | 2.7127 | 8.4981 | 6.0982 | 21.1712 | 23.4708 | 31.9689 | 38.0671 | 0.01
3.1269 | 9.2983 | 1.9042 | 1.8563 | 2.6077 | 2.7646 | 6.2817 | 6.1985 | 12.4252 | 14.2815 | 20.5633 | 26.7617 | 3.1269 | 9.2983 | 1.9042 | 1.8563 | 2.6077 | 2.7646 | 6.2817 | 6.2085 | 12.4252 | 14.2815 | 20.5633 | 26.7717 | 0.01
3.646 | 7.3775 | 1.9215 | 1.8823 | 3.8705 | 3.5223 | 6.4115 | 4.4254 | 11.0234 | 12.9057 | 20.2986 | 24.724 | 3.646 | 7.3775 | 1.9215 | 1.8823 | 3.8705 | 3.5223 | 6.4115 | 4.4354 | 11.0234 | 12.9057 | 20.2986 | 24.734 | 0.01
11.2232 | 7.49 | 2.1741 | 2.2612 | 4.6272 | 3.9763 | 8.3058 | 4.5292 | 18.7131 | 20.9743 | 29.5778 | 34.107 | 11.2232 | 7.49 | 2.1741 | 2.2612 | 4.6272 | 3.9763 | 8.3058 | 4.5392 | 18.7131 | 20.9743 | 29.5778 | 34.117 | 0.01
15.7633 | 9.1317 | 2.3254 | 2.4882 | 3.3338 | 3.2003 | 9.4408 | 6.0446 | 24.895 | 27.3831 | 36.8239 | 42.8686 | 15.7633 | 9.1317 | 2.3254 | 2.4882 | 3.3338 | 3.2003 | 9.4408 | 6.0546 | 24.895 | 27.3831 | 36.8239 | 42.8786 | 0.01
8.0029 | 10.1154 | 2.0668 | 2.1001 | 4.3526 | 3.8116 | 7.5007 | 6.9527 | 18.1183 | 20.2185 | 28.3827 | 35.3354 | 8.0029 | 10.1154 | 2.0668 | 2.1001 | 4.3526 | 3.8116 | 7.5007 | 6.9627 | 18.1183 | 20.2185 | 28.3827 | 35.3454 | 0.01
14.1159 | 8.434 | 2.2705 | 2.4058 | 3.1711 | 3.1026 | 9.029 | 5.4006 | 22.5498 | 24.9556 | 33.9846 | 39.3852 | 14.1159 | 8.434 | 2.2705 | 2.4058 | 3.1711 | 3.1026 | 9.029 | 5.4106 | 22.5498 | 24.9556 | 33.9846 | 39.3952 | 0.01
7.0265 | 9.7584 | 2.0342 | 2.0513 | 1.0701 | 1.842 | 7.2566 | 6.6232 | 16.7849 | 18.8362 | 26.0929 | 32.716 | 7.0265 | 9.7584 | 2.0342 | 2.0513 | 1.0701 | 1.842 | 7.2566 | 6.6332 | 16.7849 | 18.8362 | 26.0929 | 32.726 | 0.01
-5.5795 | 8.2224 | 1.614 | 1.421 | 3.1699 | 3.1019 | 4.1051 | 5.2053 | 2.6429 | 4.0639 | 10.3358 | 15.5411 | -5.5795 | 8.2224 | 1.614 | 1.421 | 3.1699 | 3.1019 | 4.1051 | 5.2153 | 2.6429 | 4.0639 | 10.3358 | 15.5511 | 0.01
7.0195 | 5.4911 | 2.034 | 2.051 | 2.44 | 2.664 | 7.2549 | 2.6841 | 12.5106 | 14.5615 | 21.8164 | 24.5005 | 7.0195 | 5.4911 | 2.034 | 2.051 | 2.44 | 2.664 | 7.2549 | 2.6941 | 12.5106 | 14.5615 | 21.8164 | 24.5105 | 0.01
2.6398 | 8.2209 | 1.888 | 1.832 | 3.9164 | 3.5498 | 6.1599 | 5.2039 | 10.8607 | 12.6926 | 20.1589 | 25.3627 | 2.6398 | 8.2209 | 1.888 | 1.832 | 3.9164 | 3.5498 | 6.1599 | 5.2139 | 10.8607 | 12.6926 | 20.1589 | 25.3727 | 0.01
11.4983 | 7.272 | 2.1833 | 2.2749 | 2.2667 | 2.56 | 8.3746 | 4.328 | 18.7703 | 21.0452 | 29.4197 | 33.7477 | 11.4983 | 7.272 | 2.1833 | 2.2749 | 2.2667 | 2.56 | 8.3746 | 4.338 | 18.7703 | 21.0452 | 29.4197 | 33.7577 | 0.01
1.6003 | 9.1913 | 1.8533 | 1.78 | 0.78163 | 1.669 | 5.9001 | 6.0997 | 10.7916 | 12.5716 | 18.4716 | 24.5713 | 1.6003 | 9.1913 | 1.8533 | 1.78 | 0.78163 | 1.669 | 5.9001 | 6.1097 | 10.7916 | 12.5716 | 18.4716 | 24.5813 | 0.01
-7.3102 | 7.0467 | 1.5563 | 1.3345 | 4.619 | 3.9714 | 3.6724 | 4.1201 | -0.26348 | 1.071 | 9.6614 | 13.7815 | -7.3102 | 7.0467 | 1.5563 | 1.3345 | 4.619 | 3.9714 | 3.6724 | 4.1301 | -0.26348 | 1.071 | 9.6614 | 13.7915 | 0.01
15.714 | 5.1161 | 2.3238 | 2.4857 | 4.1687 | 3.7012 | 9.4285 | 2.338 | 20.8301 | 23.3158 | 32.7443 | 35.0823 | 15.714 | 5.1161 | 2.3238 | 2.4857 | 4.1687 | 3.7012 | 9.4285 | 2.348 | 20.8301 | 23.3158 | 32.7443 | 35.0923 | 0.01
13.0123 | 10.1047 | 2.2337 | 2.3506 | 0.93932 | 1.7636 | 8.7531 | 6.9428 | 23.117 | 25.4677 | 34.2207 | 41.1635 | 13.0123 | 10.1047 | 2.2337 | 2.3506 | 0.93932 | 1.7636 | 8.7531 | 6.9528 | 23.117 | 25.4677 | 34.2207 | 41.1735 | 0.01
-6.3641 | 9.5193 | 1.5879 | 1.3818 | 3.1006 | 3.0604 | 3.909 | 6.4025 | 3.1553 | 4.5371 | 10.698 | 17.1005 | -6.3641 | 9.5193 | 1.5879 | 1.3818 | 3.1006 | 3.0604 | 3.909 | 6.4125 | 3.1553 | 4.5371 | 10.698 | 17.1105 | 0.01
6.6035 | 5.3211 | 2.0201 | 2.0302 | 3.8656 | 3.5194 | 7.1509 | 2.5272 | 11.9246 | 13.9548 | 21.3398 | 23.867 | 6.6035 | 5.3211 | 2.0201 | 2.0302 | 3.8656 | 3.5194 | 7.1509 | 2.5372 | 11.9246 | 13.9548 | 21.3398 | 23.877 | 0.01
11.1936 | 8.1308 | 2.1731 | 2.2597 | 2.3992 | 2.6395 | 8.2984 | 5.1207 | 19.3244 | 21.584 | 29.8824 | 35.0031 | 11.1936 | 8.1308 | 2.1731 | 2.2597 | 2.3992 | 2.6395 | 8.2984 | 5.1307 | 19.3244 | 21.584 | 29.8824 | 35.0131 | 0.01
2.3952 | 9.1253 | 1.8798 | 1.8198 | 4.4598 | 3.8759 | 6.0988 | 6.0387 | 11.5205 | 13.3403 | 21.6759 | 27.7146 | 2.3952 | 9.1253 | 1.8798 | 1.8198 | 4.4598 | 3.8759 | 6.0988 | 6.0487 | 11.5205 | 13.3403 | 21.6759 | 27.7246 | 0.01
14.7587 | 7.219 | 2.292 | 2.4379 | 4.6718 | 4.0031 | 9.1897 | 4.279 | 21.9776 | 24.4156 | 33.6053 | 37.8843 | 14.7587 | 7.219 | 2.292 | 2.4379 | 4.6718 | 4.0031 | 9.1897 | 4.289 | 21.9776 | 24.4156 | 33.6053 | 37.8943 | 0.01
16.0308 | 9.8977 | 2.3344 | 2.5015 | 2.5827 | 2.7496 | 9.5077 | 6.7517 | 25.9285 | 28.4301 | 37.9378 | 44.6895 | 16.0308 | 9.8977 | 2.3344 | 2.5015 | 2.5827 | 2.7496 | 9.5077 | 6.7617 | 25.9285 | 28.4301 | 37.9378 | 44.6995 | 0.01
3.496 | 10.1733 | 1.9165 | 1.8748 | 2.8107 | 2.8864 | 6.374 | 7.0062 | 13.6693 | 15.5441 | 21.9181 | 28.9243 | 3.496 | 10.1733 | 1.9165 | 1.8748 | 2.8107 | 2.8864 | 6.374 | 7.0162 | 13.6693 | 15.5441 | 21.9181 | 28.9343 | 0.01
4.8644 | 7.4575 | 1.9621 | 1.9432 | 4.7599 | 4.0559 | 6.7161 | 4.4992 | 12.3218 | 14.265 | 23.0809 | 27.5801 | 4.8644 | 7.4575 | 1.9621 | 1.9432 | 4.7599 | 4.0559 | 6.7161 | 4.5092 | 12.3218 | 14.265 | 23.0809 | 27.5901 | 0.01
16.5595 | 7.7539 | 2.352 | 2.528 | 5.0114 | 4.2069 | 9.6399 | 4.7729 | 24.3134 | 26.8414 | 36.4813 | 41.2541 | 16.5595 | 7.7539 | 2.352 | 2.528 | 5.0114 | 4.2069 | 9.6399 | 4.7829 | 24.3134 | 26.8414 | 36.4813 | 41.2641 | 0.01
18.0686 | 10.2879 | 2.4023 | 2.6034 | 4.3153 | 3.7892 | 10.0172 | 7.1119 | 28.3565 | 30.9599 | 40.9771 | 48.089 | 18.0686 | 10.2879 | 2.4023 | 2.6034 | 4.3153 | 3.7892 | 10.0172 | 7.1219 | 28.3565 | 30.9599 | 40.9771 | 48.099 | 0.01
13.8917 | 10.6149 | 2.2631 | 2.3946 | 3.384 | 3.2304 | 8.9729 | 7.4137 | 24.5065 | 26.9011 | 35.874 | 43.2878 | 13.8917 | 10.6149 | 2.2631 | 2.3946 | 3.384 | 3.2304 | 8.9729 | 7.4237 | 24.5065 | 26.9011 | 35.874 | 43.2978 | 0.01
8.3042 | 9.7099 | 2.0768 | 2.1152 | 2.9744 | 2.9846 | 7.576 | 6.5783 | 18.014 | 20.1292 | 27.7053 | 34.2836 | 8.3042 | 9.7099 | 2.0768 | 2.1152 | 2.9744 | 2.9846 | 7.576 | 6.5883 | 18.014 | 20.1292 | 27.7053 | 34.2936 | 0.01
5.8464 | 8.4992 | 1.9949 | 1.9923 | 4.3016 | 3.781 | 6.9616 | 5.4608 | 14.3457 | 16.338 | 24.4206 | 29.8814 | 5.8464 | 8.4992 | 1.9949 | 1.9923 | 4.3016 | 3.781 | 6.9616 | 5.4708 | 14.3457 | 16.338 | 24.4206 | 29.8914 | 0.01
13.8097 | 7.9667 | 2.2603 | 2.3905 | 3.6323 | 3.3794 | 8.9524 | 4.9693 | 21.7765 | 24.1669 | 33.1194 | 38.0887 | 13.8097 | 7.9667 | 2.2603 | 2.3905 | 3.6323 | 3.3794 | 8.9524 | 4.9793 | 21.7765 | 24.1669 | 33.1194 | 38.0987 | 0.01
9.7938 | 9.6921 | 2.1265 | 2.1897 | 3.7296 | 3.4377 | 7.9485 | 6.5619 | 19.4859 | 21.6756 | 29.6241 | 36.186 | 9.7938 | 9.6921 | 2.1265 | 2.1897 | 3.7296 | 3.4377 | 7.9485 | 6.5719 | 19.4859 | 21.6756 | 29.6241 | 36.196 | 0.01
10.3775 | 8.822 | 2.1459 | 2.2189 | 4.6453 | 3.9872 | 8.0944 | 5.7588 | 19.1995 | 21.4184 | 30.0509 | 35.8096 | 10.3775 | 8.822 | 2.1459 | 2.2189 | 4.6453 | 3.9872 | 8.0944 | 5.7688 | 19.1995 | 21.4184 | 30.0509 | 35.8196 | 0.01
15.8718 | 8.9485 | 2.3291 | 2.4936 | 2.8253 | 2.8952 | 9.468 | 5.8755 | 24.8203 | 27.3139 | 36.7818 | 42.6573 | 15.8718 | 8.9485 | 2.3291 | 2.4936 | 2.8253 | 2.8952 | 9.468 | 5.8855 | 24.8203 | 27.3139 | 36.7818 | 42.6673 | 0.01
4.9521 | 10.1389 | 1.9651 | 1.9476 | 2.6385 | 2.7831 | 6.738 | 6.9744 | 15.091 | 17.0386 | 23.7766 | 30.751 | 4.9521 | 10.1389 | 1.9651 | 1.9476 | 2.6385 | 2.7831 | 6.738 | 6.9844 | 15.091 | 17.0386 | 23.7766 | 30.761 | 0.01
3.8311 | 7.7729 | 1.9277 | 1.8916 | 2.9743 | 2.9846 | 6.4578 | 4.7904 | 11.604 | 13.4956 | 19.9533 | 24.7438 | 3.8311 | 7.7729 | 1.9277 | 1.8916 | 2.9743 | 2.9846 | 6.4578 | 4.8004 | 11.604 | 13.4956 | 19.9533 | 24.7538 | 0.01
5.8458 | 7.5301 | 1.9949 | 1.9923 | 1.9744 | 2.3846 | 6.9614 | 4.5662 | 13.3758 | 15.3681 | 22.3296 | 26.8958 | 5.8458 | 7.5301 | 1.9949 | 1.9923 | 1.9744 | 2.3846 | 6.9614 | 4.5762 | 13.3758 | 15.3681 | 22.3296 | 26.9058 | 0.01
-0.15369 | 7.9666 | 1.7949 | 1.6923 | 3.4835 | 3.2901 | 5.4616 | 4.9692 | 7.8129 | 9.5052 | 16.2788 | 21.248 | -0.15369 | 7.9666 | 1.7949 | 1.6923 | 3.4835 | 3.2901 | 5.4616 | 4.9792 | 7.8129 | 9.5052 | 16.2788 | 21.258 | 0.01
8.9011 | 6.6667 | 2.0967 | 2.1451 | 2.8402 | 2.9041 | 7.7253 | 3.7693 | 15.5678 | 17.7128 | 25.4381 | 29.2073 | 8.9011 | 6.6667 | 2.0967 | 2.1451 | 2.8402 | 2.9041 | 7.7253 | 3.7793 | 15.5678 | 17.7128 | 25.4381 | 29.2173 | 0.01
5.0411 | 8.6286 | 1.968 | 1.9521 | 2.9244 | 2.9547 | 6.7603 | 5.5802 | 13.6697 | 15.6217 | 22.382 | 27.9622 | 5.0411 | 8.6286 | 1.968 | 1.9521 | 2.9244 | 2.9547 | 6.7603 | 5.5902 | 13.6697 | 15.6217 | 22.382 | 27.9722 | 0.01
5.5467 | 7.7922 | 1.9849 | 1.9773 | 2.7834 | 2.87 | 6.8867 | 4.8082 | 13.3389 | 15.3163 | 22.2029 | 27.0112 | 5.5467 | 7.7922 | 1.9849 | 1.9773 | 2.7834 | 2.87 | 6.8867 | 4.8182 | 13.3389 | 15.3163 | 22.2029 | 27.0212 | 0.01
4.7002 | 7.9018 | 1.9567 | 1.935 | 2.2444 | 2.5466 | 6.675 | 4.9093 | 12.602 | 14.537 | 21.212 | 26.1214 | 4.7002 | 7.9018 | 1.9567 | 1.935 | 2.2444 | 2.5466 | 6.675 | 4.9193 | 12.602 | 14.537 | 21.212 | 26.1314 | 0.01
1.4663 | 7.7184 | 1.8489 | 1.7733 | 3.148 | 3.0888 | 5.8666 | 4.74 | 9.1847 | 10.958 | 17.1947 | 21.9348 | 1.4663 | 7.7184 | 1.8489 | 1.7733 | 3.148 | 3.0888 | 5.8666 | 4.75 | 9.1847 | 10.958 | 17.1947 | 21.9448 | 0.01
6.8879 | 7.0177 | 2.0296 | 2.0444 | 1.6145 | 2.1687 | 7.222 | 4.0933 | 13.9056 | 15.95 | 23.1719 | 27.2652 | 6.8879 | 7.0177 | 2.0296 | 2.0444 | 1.6145 | 2.1687 | 7.222 | 4.1033 | 13.9056 | 15.95 | 23.1719 | 27.2752 | 0.01
-2.3129 | 8.1924 | 1.7229 | 1.5844 | 2.1422 | 2.4853 | 4.9218 | 5.1776 | 5.8795 | 7.4639 | 12.3856 | 17.5632 | -2.3129 | 8.1924 | 1.7229 | 1.5844 | 2.1422 | 2.4853 | 4.9218 | 5.1876 | 5.8795 | 7.4639 | 12.3856 | 17.5732 | 0.01
0.85301 | 6.1989 | 1.8284 | 1.7427 | 3.3938 | 3.2363 | 5.7133 | 3.3374 | 7.0519 | 8.7945 | 15.4247 | 18.7621 | 0.85301 | 6.1989 | 1.8284 | 1.7427 | 3.3938 | 3.2363 | 5.7133 | 3.3474 | 7.0519 | 8.7945 | 15.4247 | 18.7721 | 0.01
8.363 | 6.8848 | 2.0788 | 2.1181 | 2.8631 | 2.9179 | 7.5907 | 3.9706 | 15.2478 | 17.366 | 24.9567 | 28.9273 | 8.363 | 6.8848 | 2.0788 | 2.1181 | 2.8631 | 2.9179 | 7.5907 | 3.9806 | 15.2478 | 17.366 | 24.9567 | 28.9373 | 0.01
5.1786 | 8.512 | 1.9726 | 1.9589 | 2.7811 | 2.8686 | 6.7946 | 5.4726 | 13.6906 | 15.6495 | 22.4441 | 27.9167 | 5.1786 | 8.512 | 1.9726 | 1.9589 | 2.7811 | 2.8686 | 6.7946 | 5.4826 | 13.6906 | 15.6495 | 22.4441 | 27.9267 | 0.01
4.6863 | 7.822 | 1.9562 | 1.9343 | 1.7183 | 2.231 | 6.6716 | 4.8357 | 12.5083 | 14.4427 | 21.1142 | 25.95 | 4.6863 | 7.822 | 1.9562 | 1.9343 | 1.7183 | 2.231 | 6.6716 | 4.8457 | 12.5083 | 14.4427 | 21.1142 | 25.96 | 0.01
-1.69 | 7.7154 | 1.7437 | 1.6155 | 2.6544 | 2.7926 | 5.0775 | 4.7373 | 6.0254 | 7.6409 | 13.0879 | 17.8252 | -1.69 | 7.7154 | 1.7437 | 1.6155 | 2.6544 | 2.7926 | 5.0775 | 4.7473 | 6.0254 | 7.6409 | 13.0879 | 17.8352 | 0.01
3.9263 | 6.3338 | 1.9309 | 1.8963 | 2.8467 | 2.908 | 6.4816 | 3.462 | 10.2601 | 12.1564 | 18.638 | 22.1 | 3.9263 | 6.3338 | 1.9309 | 1.8963 | 2.8467 | 2.908 | 6.4816 | 3.472 | 10.2601 | 12.1564 | 18.638 | 22.11 | 0.01
5.0801 | 7.5507 | 1.9693 | 1.954 | 2.9045 | 2.9427 | 6.77 | 4.5853 | 12.6307 | 14.5847 | 21.3548 | 25.94 | 5.0801 | 7.5507 | 1.9693 | 1.954 | 2.9045 | 2.9427 | 6.77 | 4.5953 | 12.6307 | 14.5847 | 21.3548 | 25.95 | 0.01
5.4268 | 7.8007 | 1.9809 | 1.9713 | 4.1252 | 3.6751 | 6.8567 | 4.816 | 13.2274 | 15.1988 | 22.9991 | 27.8151 | 5.4268 | 7.8007 | 1.9809 | 1.9713 | 4.1252 | 3.6751 | 6.8567 | 4.826 | 13.2274 | 15.1988 | 22.9991 | 27.8251 | 0.01
12.7511 | 7.8758 | 2.225 | 2.3376 | 3.8581 | 3.5149 | 8.6878 | 4.8854 | 20.6269 | 22.9645 | 31.6522 | 36.5376 | 12.7511 | 7.8758 | 2.225 | 2.3376 | 3.8581 | 3.5149 | 8.6878 | 4.8954 | 20.6269 | 22.9645 | 31.6522 | 36.5476 | 0.01
11.1487 | 9.4627 | 2.1716 | 2.2574 | 3.4723 | 3.2834 | 8.2872 | 6.3502 | 20.6114 | 22.8689 | 31.1561 | 37.5063 | 11.1487 | 9.4627 | 2.1716 | 2.2574 | 3.4723 | 3.2834 | 8.2872 | 6.3602 | 20.6114 | 22.8689 | 31.1561 | 37.5163 | 0.01
8.834 | 9.1156 | 2.0945 | 2.1417 | 3.2206 | 3.1323 | 7.7085 | 6.0297 | 17.9496 | 20.0913 | 27.7998 | 33.8295 | 8.834 | 9.1156 | 2.0945 | 2.1417 | 3.2206 | 3.1323 | 7.7085 | 6.0397 | 17.9496 | 20.0913 | 27.7998 | 33.8395 | 0.01
7.3235 | 8.614 | 2.0441 | 2.0662 | 3.2162 | 3.1297 | 7.3309 | 5.5668 | 15.9375 | 18.0037 | 25.3346 | 30.9014 | 7.3235 | 8.614 | 2.0441 | 2.0662 | 3.2162 | 3.1297 | 7.3309 | 5.5768 | 15.9375 | 18.0037 | 25.3346 | 30.9114 | 0.01
7.2969 | 8.2868 | 2.0432 | 2.0648 | 3.2464 | 3.1478 | 7.3242 | 5.2647 | 15.5837 | 17.6485 | 24.9727 | 30.2374 | 7.2969 | 8.2868 | 2.0432 | 2.0648 | 3.2464 | 3.1478 | 7.3242 | 5.2747 | 15.5837 | 17.6485 | 24.9727 | 30.2474 | 0.01
7.4785 | 8.281 | 2.0493 | 2.0739 | 1.9766 | 2.386 | 7.3696 | 5.2594 | 15.7595 | 17.8334 | 25.203 | 30.4624 | 7.4785 | 8.281 | 2.0493 | 2.0739 | 1.9766 | 2.386 | 7.3696 | 5.2694 | 15.7595 | 17.8334 | 25.203 | 30.4724 | 0.01
-0.14037 | 8.3203 | 1.7953 | 1.693 | 2.9701 | 2.9821 | 5.4649 | 5.2957 | 8.18 | 9.873 | 15.8251 | 21.1208 | -0.14037 | 8.3203 | 1.7953 | 1.693 | 2.9701 | 2.9821 | 5.4649 | 5.3057 | 8.18 | 9.873 | 15.8251 | 21.1308 | 0.01
5.8206 | 6.6696 | 1.994 | 1.991 | 1.6681 | 2.2008 | 6.9552 | 3.7719 | 12.4902 | 14.4813 | 21.4364 | 25.2083 | 5.8206 | 6.6696 | 1.994 | 1.991 | 1.6681 | 2.2008 | 6.9552 | 3.7819 | 12.4902 | 14.4813 | 21.4364 | 25.2183 | 0.01
-1.9916 | 7.9611 | 1.7336 | 1.6004 | 4.1051 | 3.6631 | 5.0021 | 4.9641 | 5.9696 | 7.57 | 15.3382 | 20.3023 | -1.9916 | 7.9611 | 1.7336 | 1.6004 | 4.1051 | 3.6631 | 5.0021 | 4.9741 | 5.9696 | 7.57 | 15.3382 | 20.3123 | 0.01
12.6307 | 6.2685 | 2.221 | 2.3315 | 3.1409 | 3.0845 | 8.6577 | 3.4017 | 18.8992 | 21.2308 | 29.8884 | 33.2901 | 12.6307 | 6.2685 | 2.221 | 2.3315 | 3.1409 | 3.0845 | 8.6577 | 3.4117 | 18.8992 | 21.2308 | 29.8884 | 33.3001 | 0.01
6.8453 | 9.4367 | 2.0282 | 2.0423 | 1.4547 | 2.0728 | 7.2113 | 6.3261 | 16.282 | 18.3243 | 25.5356 | 31.8617 | 6.8453 | 9.4367 | 2.0282 | 2.0423 | 1.4547 | 2.0728 | 7.2113 | 6.3361 | 16.282 | 18.3243 | 25.5356 | 31.8717 | 0.01
-3.272 | 8.1832 | 1.6909 | 1.5364 | 2.8971 | 2.9383 | 4.682 | 5.1691 | 4.9112 | 6.4476 | 12.283 | 17.452 | -3.272 | 8.1832 | 1.6909 | 1.5364 | 2.8971 | 2.9383 | 4.682 | 5.1791 | 4.9112 | 6.4476 | 12.283 | 17.462 | 0.01
5.3827 | 5.9911 | 1.9794 | 1.9691 | 4.3756 | 3.8253 | 6.8457 | 3.1456 | 11.3738 | 13.3429 | 21.5439 | 24.6895 | 5.3827 | 5.9911 | 1.9794 | 1.9691 | 4.3756 | 3.8253 | 6.8457 | 3.1556 | 11.3738 | 13.3429 | 21.5439 | 24.6995 | 0.01
14.2535 | 7.8663 | 2.2751 | 2.4127 | 2.174 | 2.5044 | 9.0634 | 4.8765 | 22.1197 | 24.5324 | 33.5958 | 38.4723 | 14.2535 | 7.8663 | 2.2751 | 2.4127 | 2.174 | 2.5044 | 9.0634 | 4.8865 | 22.1197 | 24.5324 | 33.5958 | 38.4823 | 0.01
1.0437 | 9.7882 | 1.8348 | 1.7522 | 2.1204 | 2.4722 | 5.7609 | 6.6507 | 10.832 | 12.5842 | 18.3451 | 24.9958 | 1.0437 | 9.7882 | 1.8348 | 1.7522 | 2.1204 | 2.4722 | 5.7609 | 6.6607 | 10.832 | 12.5842 | 18.3451 | 25.0058 | 0.01
0.72232 | 6.9261 | 1.8241 | 1.7361 | 3.0018 | 3.0011 | 5.6806 | 4.0087 | 7.6485 | 9.3846 | 15.3874 | 19.3962 | 0.72232 | 6.9261 | 1.8241 | 1.7361 | 3.0018 | 3.0011 | 5.6806 | 4.0187 | 7.6485 | 9.3846 | 15.3874 | 19.4062 | 0.01
6.0106 | 6.8565 | 2.0004 | 2.0005 | 2.5764 | 2.7458 | 7.0026 | 3.9445 | 12.8671 | 14.8676 | 21.8703 | 25.8147 | 6.0106 | 6.8565 | 2.0004 | 2.0005 | 2.5764 | 2.7458 | 7.0026 | 3.9545 | 12.8671 | 14.8676 | 21.8703 | 25.8247 | 0.01
3.4584 | 8.0023 | 1.9153 | 1.8729 | 0.37298 | 1.4238 | 6.3646 | 5.0021 | 11.4607 | 13.3337 | 19.6983 | 24.7004 | 3.4584 | 8.0023 | 1.9153 | 1.8729 | 0.37298 | 1.4238 | 6.3646 | 5.0121 | 11.4607 | 13.3337 | 19.6983 | 24.7104 | 0.01
-9.7621 | 7.4493 | 1.4746 | 1.2119 | 2.7077 | 2.8246 | 3.0595 | 4.4917 | -2.3128 | -1.1009 | 4.4314 | 8.9231 | -9.7621 | 7.4493 | 1.4746 | 1.2119 | 2.7077 | 2.8246 | 3.0595 | 4.5017 | -2.3128 | -1.1009 | 4.4314 | 8.9331 | 0.01
4.2463 | 4.5849 | 1.9415 | 1.9123 | 2.3095 | 2.5857 | 6.5616 | 1.8476 | 8.8311 | 10.7435 | 17.305 | 19.1526 | 4.2463 | 4.5849 | 1.9415 | 1.9123 | 2.3095 | 2.5857 | 6.5616 | 1.8576 | 8.8311 | 10.7435 | 17.305 | 19.1626 | 0.01
1.8569 | 7.62 | 1.8619 | 1.7928 | 3.3009 | 3.1806 | 5.9642 | 4.6493 | 9.4769 | 11.2698 | 17.7513 | 22.4005 | 1.8569 | 7.62 | 1.8619 | 1.7928 | 3.3009 | 3.1806 | 5.9642 | 4.6593 | 9.4769 | 11.2698 | 17.7513 | 22.4105 | 0.01
7.8055 | 7.1023 | 2.0602 | 2.0903 | 1.9738 | 2.3843 | 7.4514 | 4.1714 | 14.9079 | 16.9981 | 24.4495 | 28.6209 | 7.8055 | 7.1023 | 2.0602 | 2.0903 | 1.9738 | 2.3843 | 7.4514 | 4.1814 | 14.9079 | 16.9981 | 24.4495 | 28.6309 | 0.01
-0.15737 | 8.3912 | 1.7948 | 1.6921 | 2.3419 | 2.6052 | 5.4607 | 5.3611 | 8.2338 | 9.926 | 15.3866 | 20.7477 | -0.15737 | 8.3912 | 1.7948 | 1.6921 | 2.3419 | 2.6052 | 5.4607 | 5.3711 | 8.2338 | 9.926 | 15.3866 | 20.7577 | 0.01
2.0516 | 6.6659 | 1.8684 | 1.8026 | 4.6939 | 4.0163 | 6.0129 | 3.7685 | 8.7175 | 10.5201 | 19.2303 | 22.9989 | 2.0516 | 6.6659 | 1.8684 | 1.8026 | 4.6939 | 4.0163 | 6.0129 | 3.7785 | 8.7175 | 10.5201 | 19.2303 | 23.0089 | 0.01
16.1634 | 7.1445 | 2.3388 | 2.5082 | 2.4881 | 2.6928 | 9.5409 | 4.2103 | 23.308 | 25.8161 | 35.357 | 39.5673 | 16.1634 | 7.1445 | 2.3388 | 2.5082 | 2.4881 | 2.6928 | 9.5409 | 4.2203 | 23.308 | 25.8161 | 35.357 | 39.5773 | 0.01
2.9283 | 10.2021 | 1.8976 | 1.8464 | 1.8229 | 2.2937 | 6.2321 | 7.0327 | 13.1304 | 14.9768 | 21.2089 | 28.2416 | 2.9283 | 10.2021 | 1.8976 | 1.8464 | 1.8229 | 2.2937 | 6.2321 | 7.0427 | 13.1304 | 14.9768 | 21.2089 | 28.2516 | 0.01
-1.0626 | 7.3345 | 1.7646 | 1.6469 | 3.6826 | 3.4096 | 5.2344 | 4.3857 | 6.2719 | 7.9188 | 15.0109 | 19.3966 | -1.0626 | 7.3345 | 1.7646 | 1.6469 | 3.6826 | 3.4096 | 5.2344 | 4.3957 | 6.2719 | 7.9188 | 15.0109 | 19.4066 | 0.01
10.0956 | 6.4698 | 2.1365 | 2.2048 | 2.7751 | 2.865 | 8.0239 | 3.5875 | 16.5653 | 18.7701 | 26.794 | 30.3815 | 10.0956 | 6.4698 | 2.1365 | 2.2048 | 2.7751 | 2.865 | 8.0239 | 3.5975 | 16.5653 | 18.7701 | 26.794 | 30.3915 | 0.01
4.6504 | 8.8874 | 1.955 | 1.9325 | 4.5711 | 3.9427 | 6.6626 | 5.8191 | 13.5378 | 15.4703 | 23.9841 | 29.8032 | 4.6504 | 8.8874 | 1.955 | 1.9325 | 4.5711 | 3.9427 | 6.6626 | 5.8291 | 13.5378 | 15.4703 | 23.9841 | 29.8132 | 0.01
15.4267 | 7.7076 | 2.3142 | 2.4713 | 4.305 | 3.783 | 9.3567 | 4.7301 | 23.1343 | 25.6057 | 34.9624 | 39.6924 | 15.4267 | 7.7076 | 2.3142 | 2.4713 | 4.305 | 3.783 | 9.3567 | 4.7401 | 23.1343 | 25.6057 | 34.9624 | 39.7024 | 0.01
13.8297 | 10.0425 | 2.261 | 2.3915 | 2.4924 | 2.6954 | 8.9574 | 6.8853 | 23.8722 | 26.2637 | 35.2211 | 42.1065 | 13.8297 | 10.0425 | 2.261 | 2.3915 | 2.4924 | 2.6954 | 8.9574 | 6.8953 | 23.8722 | 26.2637 | 35.2211 | 42.1165 | 0.01
2.9545 | 9.6964 | 1.8985 | 1.8477 | 3.7825 | 3.4695 | 6.2386 | 6.5659 | 12.6509 | 14.4986 | 21.7506 | 28.3166 | 2.9545 | 9.6964 | 1.8985 | 1.8477 | 3.7825 | 3.4695 | 6.2386 | 6.5759 | 12.6509 | 14.4986 | 21.7506 | 28.3266 | 0.01
10.6949 | 7.3401 | 2.1565 | 2.2347 | 2.8622 | 2.9173 | 8.1737 | 4.3909 | 18.035 | 20.2698 | 28.4435 | 32.8344 | 10.6949 | 7.3401 | 2.1565 | 2.2347 | 2.8622 | 2.9173 | 8.1737 | 4.4009 | 18.035 | 20.2698 | 28.4435 | 32.8444 | 0.01
5.1733 | 9.0172 | 1.9724 | 1.9587 | 3.1984 | 3.119 | 6.7933 | 5.939 | 14.1905 | 16.1492 | 22.9425 | 28.8815 | 5.1733 | 9.0172 | 1.9724 | 1.9587 | 3.1984 | 3.119 | 6.7933 | 5.949 | 14.1905 | 16.1492 | 22.9425 | 28.8915 | 0.01
7.1904 | 7.8209 | 2.0397 | 2.0595 | 1.3371 | 2.0022 | 7.2976 | 4.8347 | 15.0112 | 17.0708 | 24.3683 | 29.203 | 7.1904 | 7.8209 | 2.0397 | 2.0595 | 1.3371 | 2.0022 | 7.2976 | 4.8447 | 15.0112 | 17.0708 | 24.3683 | 29.213 | 0.01
-3.9776 | 8.2579 | 1.6674 | 1.5011 | 2.9624 | 2.9775 | 4.5056 | 5.2381 | 4.2803 | 5.7815 | 11.7213 | 16.9594 | -3.9776 | 8.2579 | 1.6674 | 1.5011 | 2.9624 | 2.9775 | 4.5056 | 5.2481 | 4.2803 | 5.7815 | 11.7213 | 16.9694 | 0.01
5.7745 | 5.8382 | 1.9925 | 1.9887 | 3.2345 | 3.1407 | 6.9436 | 3.0045 | 11.6127 | 13.6015 | 20.5451 | 23.5496 | 5.7745 | 5.8382 | 1.9925 | 1.9887 | 3.2345 | 3.1407 | 6.9436 | 3.0145 | 11.6127 | 13.6015 | 20.5451 | 23.5596 | 0.01
7.4073 | 7.9511 | 2.0469 | 2.0704 | 3.9585 | 3.5751 | 7.3518 | 4.9549 | 15.3584 | 17.4288 | 24.9625 | 29.9174 | 7.4073 | 7.9511 | 2.0469 | 2.0704 | 3.9585 | 3.5751 | 7.3518 | 4.9649 | 15.3584 | 17.4288 | 24.9625 | 29.9274 | 0.01
11.7513 | 8.3049 | 2.1917 | 2.2876 | 2.7908 | 2.8745 | 8.4378 | 5.2815 | 20.0562 | 22.3438 | 30.7816 | 36.063 | 11.7513 | 8.3049 | 2.1917 | 2.2876 | 2.7908 | 2.8745 | 8.4378 | 5.2915 | 20.0562 | 22.3438 | 30.7816 | 36.073 | 0.01
4.7449 | 9.2461 | 1.9582 | 1.9372 | 1.7315 | 2.2389 | 6.6862 | 6.1503 | 13.991 | 15.9283 | 22.6145 | 28.7648 | 4.7449 | 9.2461 | 1.9582 | 1.9372 | 1.7315 | 2.2389 | 6.6862 | 6.1603 | 13.991 | 15.9283 | 22.6145 | 28.7748 | 0.01
-1.6111 | 7.7281 | 1.7463 | 1.6194 | 2.8944 | 2.9366 | 5.0972 | 4.749 | 6.1169 | 7.7364 | 13.5674 | 18.3163 | -1.6111 | 7.7281 | 1.7463 | 1.6194 | 2.8944 | 2.9366 | 5.0972 | 4.759 | 6.1169 | 7.7364 | 13.5674 | 18.3263 | 0.01
5.3662 | 6.3509 | 1.9789 | 1.9683 | 3.0773 | 3.0464 | 6.8415 | 3.4778 | 11.7171 | 13.6854 | 20.527 | 24.0047 | 5.3662 | 6.3509 | 1.9789 | 1.9683 | 3.0773 | 3.0464 | 6.8415 | 3.4878 | 11.7171 | 13.6854 | 20.527 | 24.0147 | 0.01
6.4638 | 7.8627 | 2.0155 | 2.0232 | 2.5815 | 2.7489 | 7.116 | 4.8732 | 14.3265 | 16.3497 | 23.4657 | 28.3389 | 6.4638 | 7.8627 | 2.0155 | 2.0232 | 2.5815 | 2.7489 | 7.116 | 4.8832 | 14.3265 | 16.3497 | 23.4657 | 28.3489 | 0.01
3.4889 | 8.1005 | 1.9163 | 1.8744 | 1.8665 | 2.3199 | 6.3722 | 5.0928 | 11.5894 | 13.4638 | 19.836 | 24.9288 | 3.4889 | 8.1005 | 1.9163 | 1.8744 | 1.8665 | 2.3199 | 6.3722 | 5.1028 | 11.5894 | 13.4638 | 19.836 | 24.9388 | 0.01
-0.80079 | 7.4559 | 1.7733 | 1.66 | 4.0774 | 3.6465 | 5.2998 | 4.4978 | 6.6551 | 8.3151 | 16.039 | 20.5368 | -0.80079 | 7.4559 | 1.7733 | 1.66 | 4.0774 | 3.6465 | 5.2998 | 4.5078 | 6.6551 | 8.3151 | 16.039 | 20.5468 | 0.01
12.4646 | 6.5265 | 2.2155 | 2.3232 | 2.1699 | 2.5019 | 8.6161 | 3.6398 | 18.9911 | 21.3143 | 29.9305 | 33.5703 | 12.4646 | 6.5265 | 2.2155 | 2.3232 | 2.1699 | 2.5019 | 8.6161 | 3.6498 | 18.9911 | 21.3143 | 29.9305 | 33.5803 | 0.01
1.0194 | 9.4007 | 1.834 | 1.751 | 4.2351 | 3.7411 | 5.7549 | 6.2929 | 10.4201 | 12.1711 | 20.1472 | 26.4401 | 1.0194 | 9.4007 | 1.834 | 1.751 | 4.2351 | 3.7411 | 5.7549 | 6.3029 | 10.4201 | 12.1711 | 20.1472 | 26.4501 | 0.01
13.4105 | 6.9209 | 2.247 | 2.3705 | 1.9519 | 2.3711 | 8.8526 | 4.0039 | 20.3314 | 22.7019 | 31.5546 | 35.5585 | 13.4105 | 6.9209 | 2.247 | 2.3705 | 1.9519 | 2.3711 | 8.8526 | 4.0139 | 20.3314 | 22.7019 | 31.5546 | 35.5685 | 0.01
-0.28881 | 9.6056 | 1.7904 | 1.6856 | 2.9194 | 2.9516 | 5.4278 | 6.4821 | 9.3168 | 11.0024 | 16.8734 | 23.3555 | -0.28881 | 9.6056 | 1.7904 | 1.6856 | 2.9194 | 2.9516 | 5.4278 | 6.4921 | 9.3168 | 11.0024 | 16.8734 | 23.3655 | 0.01
5.5165 | 6.6374 | 1.9839 | 1.9758 | 3.7465 | 3.4479 | 6.8791 | 3.7422 | 12.1539 | 14.1297 | 21.3241 | 25.0664 | 5.5165 | 6.6374 | 1.9839 | 1.9758 | 3.7465 | 3.4479 | 6.8791 | 3.7522 | 12.1539 | 14.1297 | 21.3241 | 25.0764 | 0.01
10.479 | 7.8952 | 2.1493 | 2.2239 | 2.4963 | 2.6978 | 8.1197 | 4.9033 | 18.3742 | 20.5982 | 28.7179 | 33.6212 | 10.479 | 7.8952 | 2.1493 | 2.2239 | 2.4963 | 2.6978 | 8.1197 | 4.9133 | 18.3742 | 20.5982 | 28.7179 | 33.6312 | 0.01
2.978 | 8.9704 | 1.8993 | 1.8489 | 4.1729 | 3.7037 | 6.2445 | 5.8958 | 11.9484 | 13.7973 | 21.6739 | 27.5697 | 2.978 | 8.9704 | 1.8993 | 1.8489 | 4.1729 | 3.7037 | 6.2445 | 5.9058 | 11.9484 | 13.7973 | 21.6739 | 27.5797 | 0.01
13.0371 | 7.3452 | 2.2346 | 2.3519 | 5.043 | 4.2258 | 8.7593 | 4.3956 | 20.3823 | 22.7342 | 32.0031 | 36.3986 | 13.0371 | 7.3452 | 2.2346 | 2.3519 | 5.043 | 4.2258 | 8.7593 | 4.4056 | 20.3823 | 22.7342 | 32.0031 | 36.4086 | 0.01
18.2582 | 9.5247 | 2.4086 | 2.6129 | 1.3136 | 1.9881 | 10.0646 | 6.4074 | 27.7829 | 30.3958 | 40.4604 | 46.8678 | 18.2582 | 9.5247 | 2.4086 | 2.6129 | 1.3136 | 1.9881 | 10.0646 | 6.4174 | 27.7829 | 30.3958 | 40.4604 | 46.8778 | 0.01
-4.1186 | 10.6559 | 1.6627 | 1.4941 | 3.5481 | 3.3289 | 4.4704 | 7.4516 | 6.5374 | 8.0314 | 14.9084 | 22.36 | -4.1186 | 10.6559 | 1.6627 | 1.4941 | 3.5481 | 3.3289 | 4.4704 | 7.4616 | 6.5374 | 8.0314 | 14.9084 | 22.37 | 0.01
9.2885 | 5.8076 | 2.1096 | 2.1644 | 2.9226 | 2.9536 | 7.8221 | 2.9763 | 15.0962 | 17.2606 | 25.0828 | 28.059 | 9.2885 | 5.8076 | 2.1096 | 2.1644 | 2.9226 | 2.9536 | 7.8221 | 2.9863 | 15.0962 | 17.2606 | 25.0828 | 28.069 | 0.01
5.5355 | 8.7125 | 1.9845 | 1.9768 | 5.2821 | 4.3692 | 6.8839 | 5.6577 | 14.2481 | 16.2248 | 25.8761 | 31.5339 | 5.5355 | 8.7125 | 1.9845 | 1.9768 | 5.2821 | 4.3692 | 6.8839 | 5.6677 | 14.2481 | 16.2248 | 25.8761 | 31.5439 | 0.01
19.6924 | 7.8994 | 2.4564 | 2.6846 | 1.3027 | 1.9816 | 10.4231 | 4.9071 | 27.5918 | 30.2764 | 40.6995 | 45.6066 | 19.6924 | 7.8994 | 2.4564 | 2.6846 | 1.3027 | 1.9816 | 10.4231 | 4.9171 | 27.5918 | 30.2764 | 40.6995 | 45.6166 | 0.01
-4.1837 | 10.9667 | 1.6605 | 1.4908 | 2.4833 | 2.69 | 4.4541 | 7.7385 | 6.7829 | 8.2738 | 13.447 | 21.1855 | -4.1837 | 10.9667 | 1.6605 | 1.4908 | 2.4833 | 2.69 | 4.4541 | 7.7485 | 6.7829 | 8.2738 | 13.447 | 21.1955 | 0.01
2.8996 | 5.7935 | 1.8967 | 1.845 | 4.6737 | 4.0042 | 6.2249 | 2.9633 | 8.6931 | 10.5381 | 19.216 | 22.1792 | 2.8996 | 5.7935 | 1.8967 | 1.845 | 4.6737 | 4.0042 | 6.2249 | 2.9733 | 8.6931 | 10.5381 | 19.216 | 22.1892 | 0.01
16.0422 | 7.3282 | 2.3347 | 2.5021 | 2.969 | 2.9814 | 9.5106 | 4.3799 | 23.3705 | 25.8726 | 35.3831 | 39.7631 | 16.0422 | 7.3282 | 2.3347 | 2.5021 | 2.969 | 2.9814 | 9.5106 | 4.3899 | 23.3705 | 25.8726 | 35.3831 | 39.7731 | 0.01
5.8138 | 10.1758 | 1.9938 | 1.9907 | 2.7846 | 2.8708 | 6.9534 | 7.0084 | 15.9896 | 17.9803 | 24.9337 | 31.9422 | 5.8138 | 10.1758 | 1.9938 | 1.9907 | 2.7846 | 2.8708 | 6.9534 | 7.0184 | 15.9896 | 17.9803 | 24.9337 | 31.9522 | 0.01
4.7076 | 7.9596 | 1.9569 | 1.9354 | 2.5954 | 2.7572 | 6.6769 | 4.9628 | 12.6673 | 14.6026 | 21.2795 | 26.2423 | 4.7076 | 7.9596 | 1.9569 | 1.9354 | 2.5954 | 2.7572 | 6.6769 | 4.9728 | 12.6673 | 14.6026 | 21.2795 | 26.2523 | 0.01
3.5724 | 7.72 | 1.9191 | 1.8786 | 4.397 | 3.8382 | 6.3931 | 4.7415 | 11.2924 | 13.171 | 21.4063 | 26.1478 | 3.5724 | 7.72 | 1.9191 | 1.8786 | 4.397 | 3.8382 | 6.3931 | 4.7515 | 11.2924 | 13.171 | 21.4063 | 26.1578 | 0.01
14.3822 | 7.474 | 2.2794 | 2.4191 | 2.2841 | 2.5705 | 9.0955 | 4.5145 | 21.8562 | 24.2753 | 33.3709 | 37.8854 | 14.3822 | 7.474 | 2.2794 | 2.4191 | 2.2841 | 2.5705 | 9.0955 | 4.5245 | 21.8562 | 24.2753 | 33.3709 | 37.8954 | 0.01
1.7047 | 9.8161 | 1.8568 | 1.7852 | 3.83 | 3.498 | 5.9262 | 6.6764 | 11.5209 | 13.3061 | 20.6341 | 27.3105 | 1.7047 | 9.8161 | 1.8568 | 1.7852 | 3.83 | 3.498 | 5.9262 | 6.6864 | 11.5209 | 13.3061 | 20.6341 | 27.3205 | 0.01
10.98 | 7.0694 | 2.166 | 2.249 | 3.431 | 3.2586 | 8.245 | 4.1409 | 18.0494 | 20.2984 | 28.5434 | 32.6843 | 10.98 | 7.0694 | 2.166 | 2.249 | 3.431 | 3.2586 | 8.245 | 4.1509 | 18.0494 | 20.2984 | 28.5434 | 32.6943 | 0.01
8.5858 | 9.079 | 2.0862 | 2.1293 | 2.0667 | 2.44 | 7.6465 | 5.996 | 17.6648 | 19.7941 | 27.4406 | 33.4366 | 8.5858 | 9.079 | 2.0862 | 2.1293 | 2.0667 | 2.44 | 7.6465 | 6.006 | 17.6648 | 19.7941 | 27.4406 | 33.4466 | 0.01
0.40007 | 8.5603 | 1.8133 | 1.72 | 3.5941 | 3.3565 | 5.6 | 5.5172 | 8.9603 | 10.6803 | 17.6309 | 23.1481 | 0.40007 | 8.5603 | 1.8133 | 1.72 | 3.5941 | 3.3565 | 5.6 | 5.5272 | 8.9603 | 10.6803 | 17.6309 | 23.1581 | 0.01
9.5647 | 6.7867 | 2.1188 | 2.1782 | 3.2553 | 3.1532 | 7.8912 | 3.88 | 16.3514 | 18.5296 | 26.4208 | 30.3008 | 9.5647 | 6.7867 | 2.1188 | 2.1782 | 3.2553 | 3.1532 | 7.8912 | 3.89 | 16.3514 | 18.5296 | 26.4208 | 30.3108 | 0.01
7.5316 | 8.7723 | 2.0511 | 2.0766 | 3.3519 | 3.2111 | 7.3829 | 5.7129 | 16.3039 | 18.3805 | 25.7634 | 31.4763 | 7.5316 | 8.7723 | 2.0511 | 2.0766 | 3.3519 | 3.2111 | 7.3829 | 5.7229 | 16.3039 | 18.3805 | 25.7634 | 31.4863 | 0.01
8.1115 | 8.3318 | 2.0704 | 2.1056 | 2.3366 | 2.602 | 7.5279 | 5.3063 | 16.4433 | 18.5489 | 26.0767 | 31.3831 | 8.1115 | 8.3318 | 2.0704 | 2.1056 | 2.3366 | 2.602 | 7.5279 | 5.3163 | 16.4433 | 18.5489 | 26.0767 | 31.3931 | 0.01
2.0197 | 8.4575 | 1.8673 | 1.801 | 2.4549 | 2.6729 | 6.0049 | 5.4223 | 10.4772 | 12.2782 | 18.2831 | 23.7054 | 2.0197 | 8.4575 | 1.8673 | 1.801 | 2.4549 | 2.6729 | 6.0049 | 5.4323 | 10.4772 | 12.2782 | 18.2831 | 23.7154 | 0.01
2.7292 | 7.1376 | 1.891 | 1.8365 | 3.3007 | 3.1804 | 6.1823 | 4.2039 | 9.8668 | 11.7033 | 18.1844 | 22.3883 | 2.7292 | 7.1376 | 1.891 | 1.8365 | 3.3007 | 3.1804 | 6.1823 | 4.2139 | 9.8668 | 11.7033 | 18.1844 | 22.3983 | 0.01
7.8041 | 7.2913 | 2.0601 | 2.0902 | 3.2421 | 3.1452 | 7.451 | 4.3458 | 15.0954 | 17.1856 | 24.6366 | 28.9825 | 7.8041 | 7.2913 | 2.0601 | 2.0902 | 3.2421 | 3.1452 | 7.451 | 4.3558 | 15.0954 | 17.1856 | 24.6366 | 28.9925 | 0.01
7.4524 | 8.3909 | 2.0484 | 2.0726 | 3.8806 | 3.5284 | 7.3631 | 5.3608 | 15.8432 | 17.9159 | 25.3248 | 30.6856 | 7.4524 | 8.3909 | 2.0484 | 2.0726 | 3.8806 | 3.5284 | 7.3631 | 5.3708 | 15.8432 | 17.9159 | 25.3248 | 30.6956 | 0.01
11.2836 | 8.3147 | 2.1761 | 2.2642 | 5.2907 | 4.3744 | 8.3209 | 5.2905 | 19.5983 | 21.8625 | 31.5276 | 36.8181 | 11.2836 | 8.3147 | 2.1761 | 2.2642 | 5.2907 | 4.3744 | 8.3209 | 5.3005 | 19.5983 | 21.8625 | 31.5276 | 36.8281 | 0.01
19.7442 | 9.1448 | 2.4581 | 2.6872 | 2.4446 | 2.6667 | 10.4361 | 6.0567 | 28.889 | 31.5762 | 42.0123 | 48.069 | 19.7442 | 9.1448 | 2.4581 | 2.6872 | 2.4446 | 2.6667 | 10.4361 | 6.0667 | 28.889 | 31.5762 | 42.0123 | 48.079 | 0.01
2.6675 | 10.9779 | 1.8889 | 1.8334 | 2.5403 | 2.7242 | 6.1669 | 7.7488 | 13.6454 | 15.4788 | 21.6456 | 29.3945 | 2.6675 | 10.9779 | 1.8889 | 1.8334 | 2.5403 | 2.7242 | 6.1669 | 7.7588 | 13.6454 | 15.4788 | 21.6456 | 29.4045 | 0.01
3.2415 | 7.278 | 1.9081 | 1.8621 | 1.9326 | 2.3596 | 6.3104 | 4.3335 | 10.5195 | 12.3816 | 18.692 | 23.0255 | 3.2415 | 7.278 | 1.9081 | 1.8621 | 1.9326 | 2.3596 | 6.3104 | 4.3435 | 10.5195 | 12.3816 | 18.692 | 23.0355 | 0.01
-0.40435 | 7.4023 | 1.7865 | 1.6798 | 3.4463 | 3.2678 | 5.3989 | 4.4483 | 6.998 | 8.6778 | 15.3919 | 19.8402 | -0.40435 | 7.4023 | 1.7865 | 1.6798 | 3.4463 | 3.2678 | 5.3989 | 4.4583 | 6.998 | 8.6778 | 15.3919 | 19.8502 | 0.01
1