## Project Management
Activity | Mean | Standard Deviation | Variance
A | 6 | 2
B | 9 | 1 | 1
C | 8 | 2
D | 7 | 2 | 4
E | 10 | 3 | 9
F | 12 | 3 | 9
Prove that Activities B, D, E and F are critical; but A and C not critical!
| Variance of the Project= |  | 23
| STD of the project (stdp) = |  | 4.7958
| Project Expected Time = |  | 38
check three different ways
P(T<40days) = P( (T-meanp)/std < (40-38)/4.80 ) = P(Z <.42)
40 |  |  |  | 0.41703 | 66.17% | 66.17% | 66.17%
P(T>45 days)=1-P(T<=45days)
| = | 1-P(Z<=(45-38)/4.80 ) = 1- P(Z<=1.46)
45 |  |  |  | 1.4596 | 7.22% | 7.22% | 7.22%
Reference: Wayne W.L., 2001, Simulation Modeling, pg 111-119
Note on F18: Ozdogru, Unsal: Z value
Note on F22: Ozdogru, Unsal: Z value
by the property of Normal distribution

## critical path
A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4
1.4288 | 6.7144 | 3.4288 | 2.4288 | 3.1433 | 5.1433 | 6.7144 | 9.1433 | 12.2865 | 17.4298
2.4295 | 7.2148 | 4.4295 | 3.4295 | 4.6443 | 6.6443 | 7.2148 | 10.6443 | 15.2885 | 21.9328
4.0538 | 8.0269 | 6.0538 | 5.0538 | 7.0808 | 9.0808 | 8.0269 | 13.0808 | 20.1615 | 29.2423
6.049 | 9.0245 | 8.049 | 7.049 | 10.0736 | 12.0736 | 9.0245 | 16.0736 | 26.1471 | 38.2207
7.3353 | 9.6677 | 9.3353 | 8.3353 | 12.003 | 14.003 | 9.6677 | 18.003 | 30.006 | 44.009
5.1939 | 8.5969 | 7.1939 | 6.1939 | 8.7908 | 10.7908 | 8.5969 | 14.7908 | 23.5817 | 34.3725
7.3727 | 9.6863 | 9.3727 | 8.3727 | 12.059 | 14.059 | 9.6863 | 18.059 | 30.118 | 44.1769
2.7474 | 7.3737 | 4.7474 | 3.7474 | 5.1211 | 7.1211 | 7.3737 | 11.1211 | 16.2422 | 23.3633
7.0969 | 9.5484 | 9.0969 | 8.0969 | 11.6453 | 13.6453 | 9.5484 | 17.6453 | 29.2906 | 42.9359
4.1058 | 8.0529 | 6.1058 | 5.1058 | 7.1586 | 9.1586 | 8.0529 | 13.1586 | 20.3173 | 29.4759
7.2091 | 9.6045 | 9.2091 | 8.2091 | 11.8136 | 13.8136 | 9.6045 | 17.8136 | 29.6272 | 43.4408
10.8182 | 11.4091 | 12.8182 | 11.8182 | 17.2273 | 19.2273 | 11.4091 | 23.2273 | 40.4546 | 59.682
6.4931 | 9.2465 | 8.4931 | 7.4931 | 10.7396 | 12.7396 | 9.2465 | 16.7396 | 27.4793 | 40.2189
6.0198 | 9.0099 | 8.0198 | 7.0198 | 10.0297 | 12.0297 | 9.0099 | 16.0297 | 26.0594 | 38.0892
5.2393 | 8.6197 | 7.2393 | 6.2393 | 8.859 | 10.859 | 8.6197 | 14.859 | 23.718 | 34.577
5.4805 | 8.7403 | 7.4805 | 6.4805 | 9.2208 | 11.2208 | 8.7403 | 15.2208 | 24.4416 | 35.6624
3.5992 | 7.7996 | 5.5992 | 4.5992 | 6.3988 | 8.3988 | 7.7996 | 12.3988 | 18.7976 | 27.1965
2.2806 | 7.1403 | 4.2806 | 3.2806 | 4.4209 | 6.4209 | 7.1403 | 10.4209 | 14.8419 | 21.2628
6.9264 | 9.4632 | 8.9264 | 7.9264 | 11.3897 | 13.3897 | 9.4632 | 17.3897 | 28.7793 | 42.169
4.5848 | 8.2924 | 6.5848 | 5.5848 | 7.8772 | 9.8772 | 8.2924 | 13.8772 | 21.7545 | 31.6317
5.8871 | 8.9436 | 7.8871 | 6.8871 | 9.8307 | 11.8307 | 8.9436 | 15.8307 | 25.6613 | 37.492
4.4375 | 8.2187 | 6.4375 | 5.4375 | 7.6562 | 9.6562 | 8.2187 | 13.6562 | 21.3124 | 30.9686
5.9122 | 8.9561 | 7.9122 | 6.9122 | 9.8683 | 11.8683 | 8.9561 | 15.8683 | 25.7367 | 37.605
4.2985 | 8.1493 | 6.2985 | 5.2985 | 7.4478 | 9.4478 | 8.1493 | 13.4478 | 20.8955 | 30.3433
3.7284 | 7.8642 | 5.7284 | 4.7284 | 6.5927 | 8.5927 | 7.8642 | 12.5927 | 19.1853 | 27.778
7.6067 | 9.8034 | 9.6067 | 8.6067 | 12.4101 | 14.4101 | 9.8034 | 18.4101 | 30.8202 | 45.2303
8.6808 | 10.3404 | 10.6808 | 9.6808 | 14.0212 | 16.0212 | 10.3404 | 20.0212 | 34.0423 | 50.0635
5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488
7.6331 | 9.8165 | 9.6331 | 8.6331 | 12.4496 | 14.4496 | 9.8165 | 18.4496 | 30.8992 | 45.3488
4.2833 | 8.1416 | 6.2833 | 5.2833 | 7.4249 | 9.4249 | 8.1416 | 13.4249 | 20.8499 | 30.2748
4.5407 | 8.2703 | 6.5407 | 5.5407 | 7.811 | 9.811 | 8.2703 | 13.811 | 21.622 | 31.433
6.1115 | 9.0558 | 8.1115 | 7.1115 | 10.1673 | 12.1673 | 9.0558 | 16.1673 | 26.3345 | 38.5018
6.1999 | 9.1 | 8.1999 | 7.1999 | 10.2999 | 12.2999 | 9.1 | 16.2999 | 26.5997 | 38.8996
2.8161 | 7.408 | 4.8161 | 3.8161 | 5.2241 | 7.2241 | 7.408 | 11.2241 | 16.4482 | 23.6723
6.6314 | 9.3157 | 8.6314 | 7.6314 | 10.9471 | 12.9471 | 9.3157 | 16.9471 | 27.8943 | 40.8414
6.5394 | 9.2697 | 8.5394 | 7.5394 | 10.8092 | 12.8092 | 9.2697 | 16.8092 | 27.6183 | 40.4275
11.0521 | 11.526 | 13.0521 | 12.0521 | 17.5781 | 19.5781 | 11.526 | 23.5781 | 41.1562 | 60.7343
3.8102 | 7.9051 | 5.8102 | 4.8102 | 6.7153 | 8.7153 | 7.9051 | 12.7153 | 19.4307 | 28.146
5.2518 | 8.6259 | 7.2518 | 6.2518 | 8.8777 | 10.8777 | 8.6259 | 14.8777 | 23.7554 | 34.6332
6.3771 | 9.1886 | 8.3771 | 7.3771 | 10.5657 | 12.5657 | 9.1886 | 16.5657 | 27.1314 | 39.6971
5.3383 | 8.6691 | 7.3383 | 6.3383 | 9.0074 | 11.0074 | 8.6691 | 15.0074 | 24.0148 | 35.0222
8.3948 | 10.1974 | 10.3948 | 9.3948 | 13.5922 | 15.5922 | 10.1974 | 19.5922 | 33.1845 | 48.7767
5.0712 | 8.5356 | 7.0712 | 6.0712 | 8.6068 | 10.6068 | 8.5356 | 14.6068 | 23.2135 | 33.8203
6.1543 | 9.0771 | 8.1543 | 7.1543 | 10.2314 | 12.2314 | 9.0771 | 16.2314 | 26.4629 | 38.6943
5.863 | 8.9315 | 7.863 | 6.863 | 9.7946 | 11.7946 | 8.9315 | 15.7946 | 25.5891 | 37.3837
2.5835 | 7.2917 | 4.5835 | 3.5835 | 4.8752 | 6.8752 | 7.2917 | 10.8752 | 15.7504 | 22.6257
5.0249 | 8.5125 | 7.0249 | 6.0249 | 8.5374 | 10.5374 | 8.5125 | 14.5374 | 23.0747 | 33.6121
6.1918 | 9.0959 | 8.1918 | 7.1918 | 10.2877 | 12.2877 | 9.0959 | 16.2877 | 26.5753 | 38.863
5.0897 | 8.5449 | 7.0897 | 6.0897 | 8.6346 | 10.6346 | 8.5449 | 14.6346 | 23.2691 | 33.9037
5.4889 | 8.7445 | 7.4889 | 6.4889 | 9.2334 | 11.2334 | 8.7445 | 15.2334 | 24.4667 | 35.7001
8.7445 | 10.3722 | 10.7445 | 9.7445 | 14.1167 | 16.1167 | 10.3722 | 20.1167 | 34.2334 | 50.3502
6.1328 | 9.0664 | 8.1328 | 7.1328 | 10.1992 | 12.1992 | 9.0664 | 16.1992 | 26.3985 | 38.5977
6.4019 | 9.201 | 8.4019 | 7.4019 | 10.6029 | 12.6029 | 9.201 | 16.6029 | 27.2058 | 39.8087
4.0371 | 8.0185 | 6.0371 | 5.0371 | 7.0556 | 9.0556 | 8.0185 | 13.0556 | 20.1112 | 29.1668
5.83 | 8.915 | 7.83 | 6.83 | 9.7451 | 11.7451 | 8.915 | 15.7451 | 25.4901 | 37.2352
2.6753 | 7.3376 | 4.6753 | 3.6753 | 5.0129 | 7.0129 | 7.3376 | 11.0129 | 16.0258 | 23.0387
5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013
2.6862 | 7.3431 | 4.6862 | 3.6862 | 5.0293 | 7.0293 | 7.3431 | 11.0293 | 16.0585 | 23.0878
9.7341 | 10.8671 | 11.7341 | 10.7341 | 15.6012 | 17.6012 | 10.8671 | 21.6012 | 37.2024 | 54.8037
4.1077 | 8.0538 | 6.1077 | 5.1077 | 7.1615 | 9.1615 | 8.0538 | 13.1615 | 20.323 | 29.4845
7.484 | 9.742 | 9.484 | 8.484 | 12.226 | 14.226 | 9.742 | 18.226 | 30.452 | 44.6781
6.2666 | 9.1333 | 8.2666 | 7.2666 | 10.3999 | 12.3999 | 9.1333 | 16.3999 | 26.7999 | 39.1998
5.2959 | 8.648 | 7.2959 | 6.2959 | 8.9439 | 10.9439 | 8.648 | 14.9439 | 23.8878 | 34.8317
4.8999 | 8.45 | 6.8999 | 5.8999 | 8.3499 | 10.3499 | 8.45 | 14.3499 | 22.6998 | 33.0497
5.8151 | 8.9076 | 7.8151 | 6.8151 | 9.7227 | 11.7227 | 8.9076 | 15.7227 | 25.4454 | 37.1682
5.9292 | 8.9646 | 7.9292 | 6.9292 | 9.8938 | 11.8938 | 8.9646 | 15.8938 | 25.7877 | 37.6815
2.9022 | 7.4511 | 4.9022 | 3.9022 | 5.3533 | 7.3533 | 7.4511 | 11.3533 | 16.7065 | 24.0598
3.7424 | 7.8712 | 5.7424 | 4.7424 | 6.6136 | 8.6136 | 7.8712 | 12.6136 | 19.2272 | 27.8407
8.3173 | 10.1587 | 10.3173 | 9.3173 | 13.476 | 15.476 | 10.1587 | 19.476 | 32.952 | 48.4281
4.7975 | 8.3988 | 6.7975 | 5.7975 | 8.1963 | 10.1963 | 8.3988 | 14.1963 | 22.3926 | 32.5889
4.0727 | 8.0363 | 6.0727 | 5.0727 | 7.109 | 9.109 | 8.0363 | 13.109 | 20.218 | 29.327
7.2028 | 9.6014 | 9.2028 | 8.2028 | 11.8042 | 13.8042 | 9.6014 | 17.8042 | 29.6085 | 43.4127
5.1967 | 8.5984 | 7.1967 | 6.1967 | 8.7951 | 10.7951 | 8.5984 | 14.7951 | 23.5902 | 34.3852
3.0576 | 7.5288 | 5.0576 | 4.0576 | 5.5864 | 7.5864 | 7.5288 | 11.5864 | 17.1729 | 24.7593
4.772 | 8.386 | 6.772 | 5.772 | 8.1579 | 10.1579 | 8.386 | 14.1579 | 22.3159 | 32.4738
6.9343 | 9.4671 | 8.9343 | 7.9343 | 11.4014 | 13.4014 | 9.4671 | 17.4014 | 28.8028 | 42.2043
5.9782 | 8.9891 | 7.9782 | 6.9782 | 9.9673 | 11.9673 | 8.9891 | 15.9673 | 25.9346 | 37.9019
4.3539 | 8.1769 | 6.3539 | 5.3539 | 7.5308 | 9.5308 | 8.1769 | 13.5308 | 21.0616 | 30.5925
4.4273 | 8.2136 | 6.4273 | 5.4273 | 7.6409 | 9.6409 | 8.2136 | 13.6409 | 21.2818 | 30.9227
5.6648 | 8.8324 | 7.6648 | 6.6648 | 9.4972 | 11.4972 | 8.8324 | 15.4972 | 24.9945 | 36.4917
6.1502 | 9.0751 | 8.1502 | 7.1502 | 10.2252 | 12.2252 | 9.0751 | 16.2252 | 26.4505 | 38.6757
13.0455 | 12.5227 | 15.0455 | 14.0455 | 20.5682 | 22.5682 | 13.0455 | 27.0909 | 47.6591 | 70.2273
7.6173 | 9.8087 | 9.6173 | 8.6173 | 12.426 | 14.426 | 9.8087 | 18.426 | 30.8519 | 45.2779
8.3774 | 10.1887 | 10.3774 | 9.3774 | 13.566 | 15.566 | 10.1887 | 19.566 | 33.1321 | 48.6981
6.074 | 9.037 | 8.074 | 7.074 | 10.111 | 12.111 | 9.037 | 16.111 | 26.222 | 38.333
5.9353 | 8.9677 | 7.9353 | 6.9353 | 9.903 | 11.903 | 8.9677 | 15.903 | 25.806 | 37.7091
6.9629 | 9.4814 | 8.9629 | 7.9629 | 11.4443 | 13.4443 | 9.4814 | 17.4443 | 28.8886 | 42.3329
3.2723 | 7.6361 | 5.2723 | 4.2723 | 5.9084 | 7.9084 | 7.6361 | 11.9084 | 17.8169 | 25.7253
5.3875 | 8.6938 | 7.3875 | 6.3875 | 9.0813 | 11.0813 | 8.6938 | 15.0813 | 24.1626 | 35.2438
2.8991 | 7.4496 | 4.8991 | 3.8991 | 5.3487 | 7.3487 | 7.4496 | 11.3487 | 16.6974 | 24.0461
6.8927 | 9.4463 | 8.8927 | 7.8927 | 11.339 | 13.339 | 9.4463 | 17.339 | 28.678 | 42.017
5.2946 | 8.6473 | 7.2946 | 6.2946 | 8.942 | 10.942 | 8.6473 | 14.942 | 23.8839 | 34.8259
7.3723 | 9.6861 | 9.3723 | 8.3723 | 12.0584 | 14.0584 | 9.6861 | 18.0584 | 30.1168 | 44.1752
6.4354 | 9.2177 | 8.4354 | 7.4354 | 10.6531 | 12.6531 | 9.2177 | 16.6531 | 27.3062 | 39.9593
5.4793 | 8.7396 | 7.4793 | 6.4793 | 9.2189 | 11.2189 | 8.7396 | 15.2189 | 24.4378 | 35.6567
6.2472 | 9.1236 | 8.2472 | 7.2472 | 10.3708 | 12.3708 | 9.1236 | 16.3708 | 26.7415 | 39.1123
4.9739 | 8.487 | 6.9739 | 5.9739 | 8.4609 | 10.4609 | 8.487 | 14.4609 | 22.9218 | 33.3827
1.3058 | 6.6529 | 3.3058 | 2.3058 | 2.9588 | 4.9588 | 6.6529 | 8.9588 | 11.9175 | 16.8763
6.9362 | 9.4681 | 8.9362 | 7.9362 | 11.4042 | 13.4042 | 9.4681 | 17.4042 | 28.8085 | 42.2127
7.1438 | 9.5719 | 9.1438 | 8.1438 | 11.7157 | 13.7157 | 9.5719 | 17.7157 | 29.4313 | 43.147
7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355
10.4708 | 11.2354 | 12.4708 | 11.4708 | 16.7062 | 18.7062 | 11.2354 | 22.7062 | 39.4124 | 58.1185
7.3244 | 9.6622 | 9.3244 | 8.3244 | 11.9867 | 13.9867 | 9.6622 | 17.9867 | 29.9733 | 43.96
3.4391 | 7.7195 | 5.4391 | 4.4391 | 6.1586 | 8.1586 | 7.7195 | 12.1586 | 18.3173 | 26.4759
3.4033 | 7.7016 | 5.4033 | 4.4033 | 6.1049 | 8.1049 | 7.7016 | 12.1049 | 18.2098 | 26.3146
6.3856 | 9.1928 | 8.3856 | 7.3856 | 10.5783 | 12.5783 | 9.1928 | 16.5783 | 27.1567 | 39.735
4.8622 | 8.4311 | 6.8622 | 5.8622 | 8.2933 | 10.2933 | 8.4311 | 14.2933 | 22.5865 | 32.8798
6.2649 | 9.1325 | 8.2649 | 7.2649 | 10.3974 | 12.3974 | 9.1325 | 16.3974 | 26.7948 | 39.1921
6.3815 | 9.1908 | 8.3815 | 7.3815 | 10.5723 | 12.5723 | 9.1908 | 16.5723 | 27.1445 | 39.7168
6.0503 | 9.0251 | 8.0503 | 7.0503 | 10.0754 | 12.0754 | 9.0251 | 16.0754 | 26.1508 | 38.2262
7.3199 | 9.6599 | 9.3199 | 8.3199 | 11.9798 | 13.9798 | 9.6599 | 17.9798 | 29.9596 | 43.9394
4.8278 | 8.4139 | 6.8278 | 5.8278 | 8.2417 | 10.2417 | 8.4139 | 14.2417 | 22.4835 | 32.7252
5.4652 | 8.7326 | 7.4652 | 6.4652 | 9.1977 | 11.1977 | 8.7326 | 15.1977 | 24.3955 | 35.5932
3.3593 | 7.6796 | 5.3593 | 4.3593 | 6.0389 | 8.0389 | 7.6796 | 12.0389 | 18.0778 | 26.1167
7.5124 | 9.7562 | 9.5124 | 8.5124 | 12.2686 | 14.2686 | 9.7562 | 18.2686 | 30.5371 | 44.8057
3.9132 | 7.9566 | 5.9132 | 4.9132 | 6.8698 | 8.8698 | 7.9566 | 12.8698 | 19.7396 | 28.6094
1.5199 | 6.7599 | 3.5199 | 2.5199 | 3.2798 | 5.2798 | 6.7599 | 9.2798 | 12.5596 | 17.8394
4.6499 | 8.325 | 6.6499 | 5.6499 | 7.9749 | 9.9749 | 8.325 | 13.9749 | 21.9497 | 31.9246
4.3616 | 8.1808 | 6.3616 | 5.3616 | 7.5424 | 9.5424 | 8.1808 | 13.5424 | 21.0848 | 30.6272
5.2767 | 8.6383 | 7.2767 | 6.2767 | 8.915 | 10.915 | 8.6383 | 14.915 | 23.8301 | 34.7451
4.6809 | 8.3404 | 6.6809 | 5.6809 | 8.0213 | 10.0213 | 8.3404 | 14.0213 | 22.0426 | 32.064
7.3392 | 9.6696 | 9.3392 | 8.3392 | 12.0087 | 14.0087 | 9.6696 | 18.0087 | 30.0175 | 44.0262
5.9878 | 8.9939 | 7.9878 | 6.9878 | 9.9818 | 11.9818 | 8.9939 | 15.9818 | 25.9635 | 37.9453
7.2575 | 9.6288 | 9.2575 | 8.2575 | 11.8863 | 13.8863 | 9.6288 | 17.8863 | 29.7726 | 43.659
6.2064 | 9.1032 | 8.2064 | 7.2064 | 10.3096 | 12.3096 | 9.1032 | 16.3096 | 26.6191 | 38.9287
3.8799 | 7.94 | 5.8799 | 4.8799 | 6.8199 | 8.8199 | 7.94 | 12.8199 | 19.6398 | 28.4598
2.4504 | 7.2252 | 4.4504 | 3.4504 | 4.6756 | 6.6756 | 7.2252 | 10.6756 | 15.3512 | 22.0267
5.7233 | 8.8617 | 7.7233 | 6.7233 | 9.585 | 11.585 | 8.8617 | 15.585 | 25.17 | 36.755
8.2167 | 10.1084 | 10.2167 | 9.2167 | 13.3251 | 15.3251 | 10.1084 | 19.3251 | 32.6501 | 47.9752
5.8225 | 8.9113 | 7.8225 | 6.8225 | 9.7338 | 11.7338 | 8.9113 | 15.7338 | 25.4676 | 37.2013
4.44 | 8.22 | 6.44 | 5.44 | 7.6599 | 9.6599 | 8.22 | 13.6599 | 21.3199 | 30.9798
5.5445 | 8.7723 | 7.5445 | 6.5445 | 9.3168 | 11.3168 | 8.7723 | 15.3168 | 24.6336 | 35.9503
6.9782 | 9.4891 | 8.9782 | 7.9782 | 11.4673 | 13.4673 | 9.4891 | 17.4673 | 28.9346 | 42.4018
4.06 | 8.03 | 6.06 | 5.06 | 7.09 | 9.09 | 8.03 | 13.09 | 20.1799 | 29.2699
6.8952 | 9.4476 | 8.8952 | 7.8952 | 11.3428 | 13.3428 | 9.4476 | 17.3428 | 28.6856 | 42.0284
4.2954 | 8.1477 | 6.2954 | 5.2954 | 7.4431 | 9.4431 | 8.1477 | 13.4431 | 20.8863 | 30.3294
5.384 | 8.692 | 7.384 | 6.384 | 9.076 | 11.076 | 8.692 | 15.076 | 24.152 | 35.228
5.5138 | 8.7569 | 7.5138 | 6.5138 | 9.2708 | 11.2708 | 8.7569 | 15.2708 | 24.5415 | 35.8123
6.558 | 9.279 | 8.558 | 7.558 | 10.837 | 12.837 | 9.279 | 16.837 | 27.6741 | 40.5111
6.8751 | 9.4376 | 8.8751 | 7.8751 | 11.3127 | 13.3127 | 9.4376 | 17.3127 | 28.6254 | 41.9381
5.5105 | 8.7553 | 7.5105 | 6.5105 | 9.2658 | 11.2658 | 8.7553 | 15.2658 | 24.5316 | 35.7974
3.8041 | 7.902 | 5.8041 | 4.8041 | 6.7061 | 8.7061 | 7.902 | 12.7061 | 19.4123 | 28.1184
6.5984 | 9.2992 | 8.5984 | 7.5984 | 10.8976 | 12.8976 | 9.2992 | 16.8976 | 27.7952 | 40.6927
4.1412 | 8.0706 | 6.1412 | 5.1412 | 7.2117 | 9.2117 | 8.0706 | 13.2117 | 20.4235 | 29.6352
8.1884 | 10.0942 | 10.1884 | 9.1884 | 13.2826 | 15.2826 | 10.0942 | 19.2826 | 32.5651 | 47.8477
3.3929 | 7.6965 | 5.3929 | 4.3929 | 6.0894 | 8.0894 | 7.6965 | 12.0894 | 18.1787 | 26.2681
8.253 | 10.1265 | 10.253 | 9.253 | 13.3795 | 15.3795 | 10.1265 | 19.3795 | 32.759 | 48.1384
6.3518 | 9.1759 | 8.3518 | 7.3518 | 10.5277 | 12.5277 | 9.1759 | 16.5277 | 27.0554 | 39.583
6.4248 | 9.2124 | 8.4248 | 7.4248 | 10.6371 | 12.6371 | 9.2124 | 16.6371 | 27.2743 | 39.9114
4.0788 | 8.0394 | 6.0788 | 5.0788 | 7.1181 | 9.1181 | 8.0394 | 13.1181 | 20.2363 | 29.3544
3.7415 | 7.8708 | 5.7415 | 4.7415 | 6.6123 | 8.6123 | 7.8708 | 12.6123 | 19.2246 | 27.8368
7.8238 | 9.9119 | 9.8238 | 8.8238 | 12.7357 | 14.7357 | 9.9119 | 18.7357 | 31.4713 | 46.207
5.4348 | 8.7174 | 7.4348 | 6.4348 | 9.1522 | 11.1522 | 8.7174 | 15.1522 | 24.3044 | 35.4567
4.2646 | 8.1323 | 6.2646 | 5.2646 | 7.397 | 9.397 | 8.1323 | 13.397 | 20.7939 | 30.1909
5.7679 | 8.884 | 7.7679 | 6.7679 | 9.6519 | 11.6519 | 8.884 | 15.6519 | 25.3038 | 36.9556
6.0709 | 9.0355 | 8.0709 | 7.0709 | 10.1064 | 12.1064 | 9.0355 | 16.1064 | 26.2128 | 38.3192
7.1335 | 9.5668 | 9.1335 | 8.1335 | 11.7003 | 13.7003 | 9.5668 | 17.7003 | 29.4005 | 43.1008
7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355
1.7153 | 6.8577 | 3.7153 | 2.7153 | 3.573 | 5.573 | 6.8577 | 9.573 | 13.146 | 18.719
2.3377 | 7.1689 | 4.3377 | 3.3377 | 4.5066 | 6.5066 | 7.1689 | 10.5066 | 15.0132 | 21.5197
4.5542 | 8.2771 | 6.5542 | 5.5542 | 7.8313 | 9.8313 | 8.2771 | 13.8313 | 21.6626 | 31.4939
8.0371 | 10.0185 | 10.0371 | 9.0371 | 13.0556 | 15.0556 | 10.0185 | 19.0556 | 32.1113 | 47.1669
9.1147 | 10.5573 | 11.1147 | 10.1147 | 14.672 | 16.672 | 10.5573 | 20.672 | 35.3441 | 52.0161
6.8241 | 9.412 | 8.8241 | 7.8241 | 11.2361 | 13.2361 | 9.412 | 17.2361 | 28.4722 | 41.7083
6.7062 | 9.3531 | 8.7062 | 7.7062 | 11.0593 | 13.0593 | 9.3531 | 17.0593 | 28.1185 | 41.1778
5.2576 | 8.6288 | 7.2576 | 6.2576 | 8.8863 | 10.8863 | 8.6288 | 14.8863 | 23.7727 | 34.659
6.3132 | 9.1566 | 8.3132 | 7.3132 | 10.4697 | 12.4697 | 9.1566 | 16.4697 | 26.9395 | 39.4092
5.6124 | 8.8062 | 7.6124 | 6.6124 | 9.4186 | 11.4186 | 8.8062 | 15.4186 | 24.8373 | 36.2559
4.4577 | 8.2289 | 6.4577 | 5.4577 | 7.6866 | 9.6866 | 8.2289 | 13.6866 | 21.3732 | 31.0598
7.1172 | 9.5586 | 9.1172 | 8.1172 | 11.6758 | 13.6758 | 9.5586 | 17.6758 | 29.3516 | 43.0274
1.8832 | 6.9416 | 3.8832 | 2.8832 | 3.8248 | 5.8248 | 6.9416 | 9.8248 | 13.6496 | 19.4744
9.3963 | 10.6981 | 11.3963 | 10.3963 | 15.0944 | 17.0944 | 10.6981 | 21.0944 | 36.1889 | 53.2833
5.7522 | 8.8761 | 7.7522 | 6.7522 | 9.6283 | 11.6283 | 8.8761 | 15.6283 | 25.2566 | 36.8849
8.7802 | 10.3901 | 10.7802 | 9.7802 | 14.1703 | 16.1703 | 10.3901 | 20.1703 | 34.3407 | 50.511
6.4029 | 9.2014 | 8.4029 | 7.4029 | 10.6043 | 12.6043 | 9.2014 | 16.6043 | 27.2086 | 39.8129
3.783 | 7.8915 | 5.783 | 4.783 | 6.6745 | 8.6745 | 7.8915 | 12.6745 | 19.349 | 28.0235
4.0209 | 8.0105 | 6.0209 | 5.0209 | 7.0314 | 9.0314 | 8.0105 | 13.0314 | 20.0627 | 29.0941
6.4079 | 9.2039 | 8.4079 | 7.4079 | 10.6118 | 12.6118 | 9.2039 | 16.6118 | 27.2236 | 39.8354
6.5453 | 9.2727 | 8.5453 | 7.5453 | 10.818 | 12.818 | 9.2727 | 16.818 | 27.6359 | 40.4539
7.6805 | 9.8402 | 9.6805 | 8.6805 | 12.5207 | 14.5207 | 9.8402 | 18.5207 | 31.0415 | 45.5622
6.1081 | 9.0541 | 8.1081 | 7.1081 | 10.1622 | 12.1622 | 9.0541 | 16.1622 | 26.3244 | 38.4866
6.5904 | 9.2952 | 8.5904 | 7.5904 | 10.8856 | 12.8856 | 9.2952 | 16.8856 | 27.7712 | 40.6568
6.4252 | 9.2126 | 8.4252 | 7.4252 | 10.6378 | 12.6378 | 9.2126 | 16.6378 | 27.2757 | 39.9135
5.1021 | 8.551 | 7.1021 | 6.1021 | 8.6531 | 10.6531 | 8.551 | 14.6531 | 23.3063 | 33.9594
5.7627 | 8.8813 | 7.7627 | 6.7627 | 9.644 | 11.644 | 8.8813 | 15.644 | 25.288 | 36.9321
6.6646 | 9.3323 | 8.6646 | 7.6646 | 10.997 | 12.997 | 9.3323 | 16.997 | 27.9939 | 40.9909
3.2081 | 7.604 | 5.2081 | 4.2081 | 5.8121 | 7.8121 | 7.604 | 11.8121 | 17.6242 | 25.4363
5.1092 | 8.5546 | 7.1092 | 6.1092 | 8.6638 | 10.6638 | 8.5546 | 14.6638 | 23.3276 | 33.9913
6.6987 | 9.3493 | 8.6987 | 7.6987 | 11.048 | 13.048 | 9.3493 | 17.048 | 28.0961 | 41.1441
6.0901 | 9.045 | 8.0901 | 7.0901 | 10.1351 | 12.1351 | 9.045 | 16.1351 | 26.2702 | 38.4053
3.3738 | 7.6869 | 5.3738 | 4.3738 | 6.0607 | 8.0607 | 7.6869 | 12.0607 | 18.1215 | 26.1822
4.8105 | 8.4053 | 6.8105 | 5.8105 | 8.2158 | 10.2158 | 8.4053 | 14.2158 | 22.4316 | 32.6474
7.522 | 9.761 | 9.522 | 8.522 | 12.2829 | 14.2829 | 9.761 | 18.2829 | 30.5659 | 44.8488
4.9713 | 8.4857 | 6.9713 | 5.9713 | 8.457 | 10.457 | 8.4857 | 14.457 | 22.9139 | 33.3709
6.749 | 9.3745 | 8.749 | 7.749 | 11.1235 | 13.1235 | 9.3745 | 17.1235 | 28.247 | 41.3705
5.0742 | 8.5371 | 7.0742 | 6.0742 | 8.6114 | 10.6114 | 8.5371 | 14.6114 | 23.2227 | 33.8341
4.7646 | 8.3823 | 6.7646 | 5.7646 | 8.1468 | 10.1468 | 8.3823 | 14.1468 | 22.2937 | 32.4405
7.389 | 9.6945 | 9.389 | 8.389 | 12.0834 | 14.0834 | 9.6945 | 18.0834 | 30.1669 | 44.2503
2.893 | 7.4465 | 4.893 | 3.893 | 5.3395 | 7.3395 | 7.4465 | 11.3395 | 16.679 | 24.0185
3.3349 | 7.6675 | 5.3349 | 4.3349 | 6.0024 | 8.0024 | 7.6675 | 12.0024 | 18.0048 | 26.0072
8.9925 | 10.4963 | 10.9925 | 9.9925 | 14.4888 | 16.4888 | 10.4963 | 20.4888 | 34.9775 | 51.4663
7.789 | 9.8945 | 9.789 | 8.789 | 12.6836 | 14.6836 | 9.8945 | 18.6836 | 31.3671 | 46.0507
7.8333 | 9.9167 | 9.8333 | 8.8333 | 12.75 | 14.75 | 9.9167 | 18.75 | 31.4999 | 46.2499
7.307 | 9.6535 | 9.307 | 8.307 | 11.9605 | 13.9605 | 9.6535 | 17.9605 | 29.9209 | 43.8814
9.787 | 10.8935 | 11.787 | 10.787 | 15.6805 | 17.6805 | 10.8935 | 21.6805 | 37.361 | 55.0415
5.2045 | 8.6023 | 7.2045 | 6.2045 | 8.8068 | 10.8068 | 8.6023 | 14.8068 | 23.6135 | 34.4203
5.5481 | 8.7741 | 7.5481 | 6.5481 | 9.3222 | 11.3222 | 8.7741 | 15.3222 | 24.6444 | 35.9666
2.9819 | 7.491 | 4.9819 | 3.9819 | 5.4729 | 7.4729 | 7.491 | 11.4729 | 16.9458 | 24.4187
7.6554 | 9.8277 | 9.6554 | 8.6554 | 12.4831 | 14.4831 | 9.8277 | 18.4831 | 30.9661 | 45.4492
4.8098 | 8.4049 | 6.8098 | 5.8098 | 8.2147 | 10.2147 | 8.4049 | 14.2147 | 22.4294 | 32.6441
2.7341 | 7.3671 | 4.7341 | 3.7341 | 5.1012 | 7.1012 | 7.3671 | 11.1012 | 16.2023 | 23.3035
8.5249 | 10.2624 | 10.5249 | 9.5249 | 13.7873 | 15.7873 | 10.2624 | 19.7873 | 33.5746 | 49.3619
8.5457 | 10.2729 | 10.5457 | 9.5457 | 13.8186 | 15.8186 | 10.2729 | 19.8186 | 33.6371 | 49.4557
6.6239 | 9.3119 | 8.6239 | 7.6239 | 10.9358 | 12.9358 | 9.3119 | 16.9358 | 27.8716 | 40.8074
7.2382 | 9.6191 | 9.2382 | 8.2382 | 11.8573 | 13.8573 | 9.6191 | 17.8573 | 29.7147 | 43.572
6.7582 | 9.3791 | 8.7582 | 7.7582 | 11.1373 | 13.1373 | 9.3791 | 17.1373 | 28.2746 | 41.4119
5.4894 | 8.7447 | 7.4894 | 6.4894 | 9.2341 | 11.2341 | 8.7447 | 15.2341 | 24.4682 | 35.7022
5.7659 | 8.883 | 7.7659 | 6.7659 | 9.6489 | 11.6489 | 8.883 | 15.6489 | 25.2977 | 36.9466
5.7573 | 8.8786 | 7.7573 | 6.7573 | 9.6359 | 11.6359 | 8.8786 | 15.6359 | 25.2719 | 36.9078
4.4028 | 8.2014 | 6.4028 | 5.4028 | 7.6042 | 9.6042 | 8.2014 | 13.6042 | 21.2083 | 30.8125
5.7536 | 8.8768 | 7.7536 | 6.7536 | 9.6304 | 11.6304 | 8.8768 | 15.6304 | 25.2608 | 36.8911
5.0303 | 8.5151 | 7.0303 | 6.0303 | 8.5454 | 10.5454 | 8.5151 | 14.5454 | 23.0908 | 33.6361
3.0131 | 7.5066 | 5.0131 | 4.0131 | 5.5197 | 7.5197 | 7.5066 | 11.5197 | 17.0393 | 24.559
2.4946 | 7.2473 | 4.4946 | 3.4946 | 4.7419 | 6.7419 | 7.2473 | 10.7419 | 15.4838 | 22.2257
3.8321 | 7.9161 | 5.8321 | 4.8321 | 6.7482 | 8.7482 | 7.9161 | 12.7482 | 19.4963 | 28.2445
3.881 | 7.9405 | 5.881 | 4.881 | 6.8215 | 8.8215 | 7.9405 | 12.8215 | 19.6431 | 28.4646
6.8478 | 9.4239 | 8.8478 | 7.8478 | 11.2716 | 13.2716 | 9.4239 | 17.2716 | 28.5433 | 41.8149
6.8117 | 9.4059 | 8.8117 | 7.8117 | 11.2176 | 13.2176 | 9.4059 | 17.2176 | 28.4352 | 41.6529
2.5649 | 7.2825 | 4.5649 | 3.5649 | 4.8474 | 6.8474 | 7.2825 | 10.8474 | 15.6947 | 22.5421
4.502 | 8.251 | 6.502 | 5.502 | 7.7531 | 9.7531 | 8.251 | 13.7531 | 21.5061 | 31.2592
8.0192 | 10.0096 | 10.0192 | 9.0192 | 13.0288 | 15.0288 | 10.0096 | 19.0288 | 32.0575 | 47.0863
5.5992 | 8.7996 | 7.5992 | 6.5992 | 9.3987 | 11.3987 | 8.7996 | 15.3987 | 24.7975 | 36.1962
3.538 | 7.769 | 5.538 | 4.538 | 6.3071 | 8.3071 | 7.769 | 12.3071 | 18.6141 | 26.9212
4.1922 | 8.0961 | 6.1922 | 5.1922 | 7.2882 | 9.2882 | 8.0961 | 13.2882 | 20.5765 | 29.8647
8.0617 | 10.0308 | 10.0617 | 9.0617 | 13.0925 | 15.0925 | 10.0308 | 19.0925 | 32.185 | 47.2775
7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998
11.8438 | 11.9219 | 13.8438 | 12.8438 | 18.7656 | 20.7656 | 11.9219 | 24.7656 | 43.5313 | 64.2969
6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915
8.8082 | 10.4041 | 10.8082 | 9.8082 | 14.2124 | 16.2124 | 10.4041 | 20.2124 | 34.4247 | 50.6371
7.6294 | 9.8147 | 9.6294 | 8.6294 | 12.4441 | 14.4441 | 9.8147 | 18.4441 | 30.8883 | 45.3324
6.2816 | 9.1408 | 8.2816 | 7.2816 | 10.4224 | 12.4224 | 9.1408 | 16.4224 | 26.8448 | 39.2672
2.9948 | 7.4974 | 4.9948 | 3.9948 | 5.4922 | 7.4922 | 7.4974 | 11.4922 | 16.9843 | 24.4765
7.6577 | 9.8289 | 9.6577 | 8.6577 | 12.4866 | 14.4866 | 9.8289 | 18.4866 | 30.9732 | 45.4598
5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381
6.3502 | 9.1751 | 8.3502 | 7.3502 | 10.5253 | 12.5253 | 9.1751 | 16.5253 | 27.0507 | 39.576
8.2841 | 10.1421 | 10.2841 | 9.2841 | 13.4262 | 15.4262 | 10.1421 | 19.4262 | 32.8524 | 48.2786
7.4494 | 9.7247 | 9.4494 | 8.4494 | 12.1741 | 14.1741 | 9.7247 | 18.1741 | 30.3481 | 44.5222
5.769 | 8.8845 | 7.769 | 6.769 | 9.6535 | 11.6535 | 8.8845 | 15.6535 | 25.307 | 36.9605
5.8084 | 8.9042 | 7.8084 | 6.8084 | 9.7126 | 11.7126 | 8.9042 | 15.7126 | 25.4252 | 37.1377
4.3983 | 8.1992 | 6.3983 | 5.3983 | 7.5975 | 9.5975 | 8.1992 | 13.5975 | 21.195 | 30.7925
4.0729 | 8.0365 | 6.0729 | 5.0729 | 7.1094 | 9.1094 | 8.0365 | 13.1094 | 20.2188 | 29.3281
6.5512 | 9.2756 | 8.5512 | 7.5512 | 10.8268 | 12.8268 | 9.2756 | 16.8268 | 27.6536 | 40.4803
3.2266 | 7.6133 | 5.2266 | 4.2266 | 5.8399 | 7.8399 | 7.6133 | 11.8399 | 17.6798 | 25.5197
6.4914 | 9.2457 | 8.4914 | 7.4914 | 10.737 | 12.737 | 9.2457 | 16.737 | 27.4741 | 40.2111
7.4177 | 9.7089 | 9.4177 | 8.4177 | 12.1266 | 14.1266 | 9.7089 | 18.1266 | 30.2532 | 44.3798
3.4213 | 7.7106 | 5.4213 | 4.4213 | 6.1319 | 8.1319 | 7.7106 | 12.1319 | 18.2638 | 26.3957
4.6599 | 8.3299 | 6.6599 | 5.6599 | 7.9898 | 9.9898 | 8.3299 | 13.9898 | 21.9797 | 31.9695
7.9283 | 9.9641 | 9.9283 | 8.9283 | 12.8924 | 14.8924 | 9.9641 | 18.8924 | 31.7849 | 46.6773
8.1195 | 10.0598 | 10.1195 | 9.1195 | 13.1793 | 15.1793 | 10.0598 | 19.1793 | 32.3586 | 47.5378
5.1511 | 8.5755 | 7.1511 | 6.1511 | 8.7266 | 10.7266 | 8.5755 | 14.7266 | 23.4532 | 34.1798
4.3661 | 8.183 | 6.3661 | 5.3661 | 7.5491 | 9.5491 | 8.183 | 13.5491 | 21.0983 | 30.6474
4.8403 | 8.4202 | 6.8403 | 5.8403 | 8.2605 | 10.2605 | 8.4202 | 14.2605 | 22.521 | 32.7815
6.6155 | 9.3078 | 8.6155 | 7.6155 | 10.9233 | 12.9233 | 9.3078 | 16.9233 | 27.8466 | 40.7699
6.1813 | 9.0907 | 8.1813 | 7.1813 | 10.272 | 12.272 | 9.0907 | 16.272 | 26.544 | 38.8159
6.6324 | 9.3162 | 8.6324 | 7.6324 | 10.9486 | 12.9486 | 9.3162 | 16.9486 | 27.8972 | 40.8458
5.7216 | 8.8608 | 7.7216 | 6.7216 | 9.5825 | 11.5825 | 8.8608 | 15.5825 | 25.1649 | 36.7474
5.8658 | 8.9329 | 7.8658 | 6.8658 | 9.7987 | 11.7987 | 8.9329 | 15.7987 | 25.5974 | 37.3961
4.2094 | 8.1047 | 6.2094 | 5.2094 | 7.314 | 9.314 | 8.1047 | 13.314 | 20.6281 | 29.9421
5.2214 | 8.6107 | 7.2214 | 6.2214 | 8.8321 | 10.8321 | 8.6107 | 14.8321 | 23.6641 | 34.4962
5.3992 | 8.6996 | 7.3992 | 6.3992 | 9.0988 | 11.0988 | 8.6996 | 15.0988 | 24.1976 | 35.2965
9.2618 | 10.6309 | 11.2618 | 10.2618 | 14.8927 | 16.8927 | 10.6309 | 20.8927 | 35.7855 | 52.6782
2.5164 | 7.2582 | 4.5164 | 3.5164 | 4.7746 | 6.7746 | 7.2582 | 10.7746 | 15.5493 | 22.3239
6.053 | 9.0265 | 8.053 | 7.053 | 10.0795 | 12.0795 | 9.0265 | 16.0795 | 26.1591 | 38.2386
11.0086 | 11.5043 | 13.0086 | 12.0086 | 17.5129 | 19.5129 | 11.5043 | 23.5129 | 41.0259 | 60.5388
9.7368 | 10.8684 | 11.7368 | 10.7368 | 15.6052 | 17.6052 | 10.8684 | 21.6052 | 37.2103 | 54.8155
9.4739 | 10.7369 | 11.4739 | 10.4739 | 15.2108 | 17.2108 | 10.7369 | 21.2108 | 36.4216 | 53.6323
4.0971 | 8.0486 | 6.0971 | 5.0971 | 7.1457 | 9.1457 | 8.0486 | 13.1457 | 20.2913 | 29.437
7.1106 | 9.5553 | 9.1106 | 8.1106 | 11.6659 | 13.6659 | 9.5553 | 17.6659 | 29.3318 | 42.9977
8.668 | 10.334 | 10.668 | 9.668 | 14.0021 | 16.0021 | 10.334 | 20.0021 | 34.0041 | 50.0062
5.0877 | 8.5438 | 7.0877 | 6.0877 | 8.6315 | 10.6315 | 8.5438 | 14.6315 | 23.263 | 33.8945
3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769
6.5588 | 9.2794 | 8.5588 | 7.5588 | 10.8382 | 12.8382 | 9.2794 | 16.8382 | 27.6765 | 40.5147
5.3003 | 8.6502 | 7.3003 | 6.3003 | 8.9505 | 10.9505 | 8.6502 | 14.9505 | 23.901 | 34.8515
5.3086 | 8.6543 | 7.3086 | 6.3086 | 8.9629 | 10.9629 | 8.6543 | 14.9629 | 23.9259 | 34.8888
4.5764 | 8.2882 | 6.5764 | 5.5764 | 7.8645 | 9.8645 | 8.2882 | 13.8645 | 21.7291 | 31.5936
5.9923 | 8.9961 | 7.9923 | 6.9923 | 9.9884 | 11.9884 | 8.9961 | 15.9884 | 25.9768 | 37.9652
2.2553 | 7.1277 | 4.2553 | 3.2553 | 4.383 | 6.383 | 7.1277 | 10.383 | 14.766 | 21.1489
3.77 | 7.885 | 5.77 | 4.77 | 6.6549 | 8.6549 | 7.885 | 12.6549 | 19.3099 | 27.9648
5.0845 | 8.5422 | 7.0845 | 6.0845 | 8.6267 | 10.6267 | 8.5422 | 14.6267 | 23.2534 | 33.88
10.4131 | 11.2066 | 12.4131 | 11.4131 | 16.6197 | 18.6197 | 11.2066 | 22.6197 | 39.2394 | 57.8591
6.5663 | 9.2831 | 8.5663 | 7.5663 | 10.8494 | 12.8494 | 9.2831 | 16.8494 | 27.6989 | 40.5483
5.6487 | 8.8243 | 7.6487 | 6.6487 | 9.473 | 11.473 | 8.8243 | 15.473 | 24.946 | 36.4191
7.5932 | 9.7966 | 9.5932 | 8.5932 | 12.3899 | 14.3899 | 9.7966 | 18.3899 | 30.7797 | 45.1696
3.3026 | 7.6513 | 5.3026 | 4.3026 | 5.9539 | 7.9539 | 7.6513 | 11.9539 | 17.9078 | 25.8617
3.76 | 7.88 | 5.76 | 4.76 | 6.6399 | 8.6399 | 7.88 | 12.6399 | 19.2799 | 27.9198
5.8466 | 8.9233 | 7.8466 | 6.8466 | 9.7699 | 11.7699 | 8.9233 | 15.7699 | 25.5399 | 37.3098
6.6787 | 9.3394 | 8.6787 | 7.6787 | 11.0181 | 13.0181 | 9.3394 | 17.0181 | 28.0362 | 41.0543
5.4037 | 8.7018 | 7.4037 | 6.4037 | 9.1055 | 11.1055 | 8.7018 | 15.1055 | 24.2111 | 35.3166
6.474 | 9.237 | 8.474 | 7.474 | 10.711 | 12.711 | 9.237 | 16.711 | 27.4221 | 40.1331
6.1767 | 9.0884 | 8.1767 | 7.1767 | 10.2651 | 12.2651 | 9.0884 | 16.2651 | 26.5301 | 38.7952
6.604 | 9.302 | 8.604 | 7.604 | 10.906 | 12.906 | 9.302 | 16.906 | 27.812 | 40.7179
4.67 | 8.335 | 6.67 | 5.67 | 8.005 | 10.005 | 8.335 | 14.005 | 22.0101 | 32.0151
5.3308 | 8.6654 | 7.3308 | 6.3308 | 8.9962 | 10.9962 | 8.6654 | 14.9962 | 23.9925 | 34.9887
5.7182 | 8.8591 | 7.7182 | 6.7182 | 9.5774 | 11.5774 | 8.8591 | 15.5774 | 25.1547 | 36.7321
1.3905 | 6.6952 | 3.3905 | 2.3905 | 3.0857 | 5.0857 | 6.6952 | 9.0857 | 12.1714 | 17.2571
4.6854 | 8.3427 | 6.6854 | 5.6854 | 8.0282 | 10.0282 | 8.3427 | 14.0282 | 22.0563 | 32.0845
4.5016 | 8.2508 | 6.5016 | 5.5016 | 7.7525 | 9.7525 | 8.2508 | 13.7525 | 21.5049 | 31.2574
3.0906 | 7.5453 | 5.0906 | 4.0906 | 5.6359 | 7.6359 | 7.5453 | 11.6359 | 17.2719 | 24.9078
3.6427 | 7.8213 | 5.6427 | 4.6427 | 6.464 | 8.464 | 7.8213 | 12.464 | 18.928 | 27.392
3.7734 | 7.8867 | 5.7734 | 4.7734 | 6.66 | 8.66 | 7.8867 | 12.66 | 19.3201 | 27.9801
5.5801 | 8.79 | 7.5801 | 6.5801 | 9.3701 | 11.3701 | 8.79 | 15.3701 | 24.7403 | 36.1104
7.3028 | 9.6514 | 9.3028 | 8.3028 | 11.9542 | 13.9542 | 9.6514 | 17.9542 | 29.9084 | 43.8626
4.8107 | 8.4054 | 6.8107 | 5.8107 | 8.2161 | 10.2161 | 8.4054 | 14.2161 | 22.4321 | 32.6482
6.0516 | 9.0258 | 8.0516 | 7.0516 | 10.0775 | 12.0775 | 9.0258 | 16.0775 | 26.1549 | 38.2324
7.0705 | 9.5352 | 9.0705 | 8.0705 | 11.6057 | 13.6057 | 9.5352 | 17.6057 | 29.2114 | 42.8171
7.2568 | 9.6284 | 9.2568 | 8.2568 | 11.8852 | 13.8852 | 9.6284 | 17.8852 | 29.7704 | 43.6556
5.5195 | 8.7598 | 7.5195 | 6.5195 | 9.2793 | 11.2793 | 8.7598 | 15.2793 | 24.5586 | 35.8378
7.7236 | 9.8618 | 9.7236 | 8.7236 | 12.5854 | 14.5854 | 9.8618 | 18.5854 | 31.1707 | 45.7561
7.4454 | 9.7227 | 9.4454 | 8.4454 | 12.1681 | 14.1681 | 9.7227 | 18.1681 | 30.3362 | 44.5043
7.2098 | 9.6049 | 9.2098 | 8.2098 | 11.8147 | 13.8147 | 9.6049 | 17.8147 | 29.6294 | 43.4441
8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144
5.3983 | 8.6991 | 7.3983 | 6.3983 | 9.0974 | 11.0974 | 8.6991 | 15.0974 | 24.1948 | 35.2922
8.1214 | 10.0607 | 10.1214 | 9.1214 | 13.1821 | 15.1821 | 10.0607 | 19.1821 | 32.3642 | 47.5463
5.6079 | 8.8039 | 7.6079 | 6.6079 | 9.4118 | 11.4118 | 8.8039 | 15.4118 | 24.8237 | 36.2355
6.4616 | 9.2308 | 8.4616 | 7.4616 | 10.6924 | 12.6924 | 9.2308 | 16.6924 | 27.3848 | 40.0772
5.8819 | 8.9409 | 7.8819 | 6.8819 | 9.8228 | 11.8228 | 8.9409 | 15.8228 | 25.6457 | 37.4685
3.8915 | 7.9457 | 5.8915 | 4.8915 | 6.8372 | 8.8372 | 7.9457 | 12.8372 | 19.6744 | 28.5115
3.9971 | 7.9985 | 5.9971 | 4.9971 | 6.9956 | 8.9956 | 7.9985 | 12.9956 | 19.9912 | 28.9868
6.3642 | 9.1821 | 8.3642 | 7.3642 | 10.5463 | 12.5463 | 9.1821 | 16.5463 | 27.0927 | 39.639
9.0628 | 10.5314 | 11.0628 | 10.0628 | 14.5941 | 16.5941 | 10.5314 | 20.5941 | 35.1883 | 51.7824
6.7215 | 9.3608 | 8.7215 | 7.7215 | 11.0823 | 13.0823 | 9.3608 | 17.0823 | 28.1645 | 41.2468
7.5347 | 9.7673 | 9.5347 | 8.5347 | 12.302 | 14.302 | 9.7673 | 18.302 | 30.604 | 44.906
4.2203 | 8.1102 | 6.2203 | 5.2203 | 7.3305 | 9.3305 | 8.1102 | 13.3305 | 20.6609 | 29.9914
4.9198 | 8.4599 | 6.9198 | 5.9198 | 8.3797 | 10.3797 | 8.4599 | 14.3797 | 22.7594 | 33.1391
3.252 | 7.626 | 5.252 | 4.252 | 5.878 | 7.878 | 7.626 | 11.878 | 17.7559 | 25.6339
6.2071 | 9.1036 | 8.2071 | 7.2071 | 10.3107 | 12.3107 | 9.1036 | 16.3107 | 26.6214 | 38.9322
6.9816 | 9.4908 | 8.9816 | 7.9816 | 11.4725 | 13.4725 | 9.4908 | 17.4725 | 28.9449 | 42.4174
4.3537 | 8.1768 | 6.3537 | 5.3537 | 7.5305 | 9.5305 | 8.1768 | 13.5305 | 21.061 | 30.5915
7.4024 | 9.7012 | 9.4024 | 8.4024 | 12.1036 | 14.1036 | 9.7012 | 18.1036 | 30.2073 | 44.3109
5.2403 | 8.6202 | 7.2403 | 6.2403 | 8.8605 | 10.8605 | 8.6202 | 14.8605 | 23.7209 | 34.5814
6.5781 | 9.289 | 8.5781 | 7.5781 | 10.8671 | 12.8671 | 9.289 | 16.8671 | 27.7343 | 40.6014
7.6429 | 9.8215 | 9.6429 | 8.6429 | 12.4644 | 14.4644 | 9.8215 | 18.4644 | 30.9287 | 45.3931
6.3829 | 9.1915 | 8.3829 | 7.3829 | 10.5744 | 12.5744 | 9.1915 | 16.5744 | 27.1487 | 39.7231
3.4405 | 7.7202 | 5.4405 | 4.4405 | 6.1607 | 8.1607 | 7.7202 | 12.1607 | 18.3214 | 26.4821
8.5773 | 10.2887 | 10.5773 | 9.5773 | 13.866 | 15.866 | 10.2887 | 19.866 | 33.732 | 49.598
8.9551 | 10.4775 | 10.9551 | 9.9551 | 14.4326 | 16.4326 | 10.4775 | 20.4326 | 34.8653 | 51.2979
5.4187 | 8.7094 | 7.4187 | 6.4187 | 9.1281 | 11.1281 | 8.7094 | 15.1281 | 24.2561 | 35.3842
5.3886 | 8.6943 | 7.3886 | 6.3886 | 9.083 | 11.083 | 8.6943 | 15.083 | 24.1659 | 35.2489
8.0894 | 10.0447 | 10.0894 | 9.0894 | 13.1342 | 15.1342 | 10.0447 | 19.1342 | 32.2683 | 47.4025
9.5481 | 10.7741 | 11.5481 | 10.5481 | 15.3222 | 17.3222 | 10.7741 | 21.3222 | 36.6444 | 53.9666
8.3839 | 10.1919 | 10.3839 | 9.3839 | 13.5758 | 15.5758 | 10.1919 | 19.5758 | 33.1517 | 48.7275
5.3671 | 8.6836 | 7.3671 | 6.3671 | 9.0507 | 11.0507 | 8.6836 | 15.0507 | 24.1014 | 35.1521
6.4787 | 9.2394 | 8.4787 | 7.4787 | 10.7181 | 12.7181 | 9.2394 | 16.7181 | 27.4362 | 40.1544
9.3042 | 10.6521 | 11.3042 | 10.3042 | 14.9563 | 16.9563 | 10.6521 | 20.9563 | 35.9126 | 52.8689
2.544 | 7.272 | 4.544 | 3.544 | 4.816 | 6.816 | 7.272 | 10.816 | 15.632 | 22.448
4.3068 | 8.1534 | 6.3068 | 5.3068 | 7.4603 | 9.4603 | 8.1534 | 13.4603 | 20.9205 | 30.3808
4.3765 | 8.1883 | 6.3765 | 5.3765 | 7.5648 | 9.5648 | 8.1883 | 13.5648 | 21.1296 | 30.6944
8.9067 | 10.4534 | 10.9067 | 9.9067 | 14.3601 | 16.3601 | 10.4534 | 20.3601 | 34.7202 | 51.0803
5.8313 | 8.9156 | 7.8313 | 6.8313 | 9.7469 | 11.7469 | 8.9156 | 15.7469 | 25.4938 | 37.2407
5.7318 | 8.8659 | 7.7318 | 6.7318 | 9.5978 | 11.5978 | 8.8659 | 15.5978 | 25.1955 | 36.7933
4.0139 | 8.007 | 6.0139 | 5.0139 | 7.0209 | 9.0209 | 8.007 | 13.0209 | 20.0417 | 29.0626
4.3425 | 8.1712 | 6.3425 | 5.3425 | 7.5137 | 9.5137 | 8.1712 | 13.5137 | 21.0274 | 30.5411
6.3885 | 9.1943 | 8.3885 | 7.3885 | 10.5828 | 12.5828 | 9.1943 | 16.5828 | 27.1656 | 39.7483
4.828 | 8.414 | 6.828 | 5.828 | 8.242 | 10.242 | 8.414 | 14.242 | 22.484 | 32.726
4.4034 | 8.2017 | 6.4034 | 5.4034 | 7.6051 | 9.6051 | 8.2017 | 13.6051 | 21.2102 | 30.8153
4.8238 | 8.4119 | 6.8238 | 5.8238 | 8.2357 | 10.2357 | 8.4119 | 14.2357 | 22.4715 | 32.7072
2.2571 | 7.1285 | 4.2571 | 3.2571 | 4.3856 | 6.3856 | 7.1285 | 10.3856 | 14.7713 | 21.1569
7.5318 | 9.7659 | 9.5318 | 8.5318 | 12.2977 | 14.2977 | 9.7659 | 18.2977 | 30.5954 | 44.8931
5.7824 | 8.8912 | 7.7824 | 6.7824 | 9.6736 | 11.6736 | 8.8912 | 15.6736 | 25.3472 | 37.0208
5.2454 | 8.6227 | 7.2454 | 6.2454 | 8.8681 | 10.8681 | 8.6227 | 14.8681 | 23.7362 | 34.6043
4.8561 | 8.428 | 6.8561 | 5.8561 | 8.2841 | 10.2841 | 8.428 | 14.2841 | 22.5682 | 32.8522
8.4147 | 10.2073 | 10.4147 | 9.4147 | 13.622 | 15.622 | 10.2073 | 19.622 | 33.244 | 48.866
6.6838 | 9.3419 | 8.6838 | 7.6838 | 11.0256 | 13.0256 | 9.3419 | 17.0256 | 28.0513 | 41.0769
0.96635 | 6.4832 | 2.9663 | 1.9663 | 2.4495 | 4.4495 | 6.4832 | 8.4495 | 10.899 | 15.3486
7.0703 | 9.5351 | 9.0703 | 8.0703 | 11.6054 | 13.6054 | 9.5351 | 17.6054 | 29.2109 | 42.8163
7.017 | 9.5085 | 9.017 | 8.017 | 11.5255 | 13.5255 | 9.5085 | 17.5255 | 29.051 | 42.5765
5.4393 | 8.7196 | 7.4393 | 6.4393 | 9.1589 | 11.1589 | 8.7196 | 15.1589 | 24.3178 | 35.4767 | #REF! | chance that the project will take less than 40 days
2.5841 | 7.2921 | 4.5841 | 3.5841 | 4.8762 | 6.8762 | 7.2921 | 10.8762 | 15.7524 | 22.6286
3.8108 | 7.9054 | 5.8108 | 4.8108 | 6.7162 | 8.7162 | 7.9054 | 12.7162 | 19.4324 | 28.1486
5.3143 | 8.6572 | 7.3143 | 6.3143 | 8.9715 | 10.9715 | 8.6572 | 14.9715 | 23.9429 | 34.9144
6.6577 | 9.3288 | 8.6577 | 7.6577 | 10.9865 | 12.9865 | 9.3288 | 16.9865 | 27.9731 | 40.9596
3.0098 | 7.5049 | 5.0098 | 4.0098 | 5.5147 | 7.5147 | 7.5049 | 11.5147 | 17.0295 | 24.5442
5.1527 | 8.5764 | 7.1527 | 6.1527 | 8.7291 | 10.7291 | 8.5764 | 14.7291 | 23.4582 | 34.1873
5.8825 | 8.9413 | 7.8825 | 6.8825 | 9.8238 | 11.8238 | 8.9413 | 15.8238 | 25.6475 | 37.4713
6.6117 | 9.3058 | 8.6117 | 7.6117 | 10.9175 | 12.9175 | 9.3058 | 16.9175 | 27.835 | 40.7525
7.5536 | 9.7768 | 9.5536 | 8.5536 | 12.3304 | 14.3304 | 9.7768 | 18.3304 | 30.6609 | 44.9913
3.9811 | 7.9905 | 5.9811 | 4.9811 | 6.9716 | 8.9716 | 7.9905 | 12.9716 | 19.9432 | 28.9148
2.7565 | 7.3783 | 4.7565 | 3.7565 | 5.1348 | 7.1348 | 7.3783 | 11.1348 | 16.2696 | 23.4044
1.279 | 6.6395 | 3.279 | 2.279 | 2.9185 | 4.9185 | 6.6395 | 8.9185 | 11.837 | 16.7555
6.3987 | 9.1993 | 8.3987 | 7.3987 | 10.598 | 12.598 | 9.1993 | 16.598 | 27.196 | 39.794
8.8962 | 10.4481 | 10.8962 | 9.8962 | 14.3443 | 16.3443 | 10.4481 | 20.3443 | 34.6886 | 51.033
3.2532 | 7.6266 | 5.2532 | 4.2532 | 5.8797 | 7.8797 | 7.6266 | 11.8797 | 17.7595 | 25.6392
5.4748 | 8.7374 | 7.4748 | 6.4748 | 9.2122 | 11.2122 | 8.7374 | 15.2122 | 24.4245 | 35.6367
5.6701 | 8.8351 | 7.6701 | 6.6701 | 9.5052 | 11.5052 | 8.8351 | 15.5052 | 25.0103 | 36.5155
8.5124 | 10.2562 | 10.5124 | 9.5124 | 13.7685 | 15.7685 | 10.2562 | 19.7685 | 33.5371 | 49.3056
7.7278 | 9.8639 | 9.7278 | 8.7278 | 12.5917 | 14.5917 | 9.8639 | 18.5917 | 31.1834 | 45.7751
6.6958 | 9.3479 | 8.6958 | 7.6958 | 11.0437 | 13.0437 | 9.3479 | 17.0437 | 28.0873 | 41.131
6.6747 | 9.3373 | 8.6747 | 7.6747 | 11.012 | 13.012 | 9.3373 | 17.012 | 28.024 | 41.036
4.1136 | 8.0568 | 6.1136 | 5.1136 | 7.1705 | 9.1705 | 8.0568 | 13.1705 | 20.3409 | 29.5114
6.0322 | 9.0161 | 8.0322 | 7.0322 | 10.0483 | 12.0483 | 9.0161 | 16.0483 | 26.0966 | 38.1449
6.0533 | 9.0267 | 8.0533 | 7.0533 | 10.08 | 12.08 | 9.0267 | 16.08 | 26.16 | 38.24
5.3099 | 8.655 | 7.3099 | 6.3099 | 8.9649 | 10.9649 | 8.655 | 14.9649 | 23.9298 | 34.8946
2.783 | 7.3915 | 4.783 | 3.783 | 5.1746 | 7.1746 | 7.3915 | 11.1746 | 16.3491 | 23.5237
4.1082 | 8.0541 | 6.1082 | 5.1082 | 7.1622 | 9.1622 | 8.0541 | 13.1622 | 20.3245 | 29.4867
9.1167 | 10.5584 | 11.1167 | 10.1167 | 14.6751 | 16.6751 | 10.5584 | 20.6751 | 35.3502 | 52.0254
7.2546 | 9.6273 | 9.2546 | 8.2546 | 11.8819 | 13.8819 | 9.6273 | 17.8819 | 29.7637 | 43.6456
3.9195 | 7.9598 | 5.9195 | 4.9195 | 6.8793 | 8.8793 | 7.9598 | 12.8793 | 19.7585 | 28.6378
7.2151 | 9.6076 | 9.2151 | 8.2151 | 11.8227 | 13.8227 | 9.6076 | 17.8227 | 29.6454 | 43.4681
5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741
4.1806 | 8.0903 | 6.1806 | 5.1806 | 7.2709 | 9.2709 | 8.0903 | 13.2709 | 20.5419 | 29.8128
4.4304 | 8.2152 | 6.4304 | 5.4304 | 7.6456 | 9.6456 | 8.2152 | 13.6456 | 21.2912 | 30.9368
4.0583 | 8.0291 | 6.0583 | 5.0583 | 7.0874 | 9.0874 | 8.0291 | 13.0874 | 20.1748 | 29.2622
6.3386 | 9.1693 | 8.3386 | 7.3386 | 10.5079 | 12.5079 | 9.1693 | 16.5079 | 27.0158 | 39.5236
8.3318 | 10.1659 | 10.3318 | 9.3318 | 13.4977 | 15.4977 | 10.1659 | 19.4977 | 32.9953 | 48.493
3.4866 | 7.7433 | 5.4866 | 4.4866 | 6.23 | 8.23 | 7.7433 | 12.23 | 18.4599 | 26.6899
5.145 | 8.5725 | 7.145 | 6.145 | 8.7175 | 10.7175 | 8.5725 | 14.7175 | 23.4351 | 34.1526
4.7066 | 8.3533 | 6.7066 | 5.7066 | 8.06 | 10.06 | 8.3533 | 14.06 | 22.1199 | 32.1799
3.6298 | 7.8149 | 5.6298 | 4.6298 | 6.4446 | 8.4446 | 7.8149 | 12.4446 | 18.8893 | 27.3339
7.1394 | 9.5697 | 9.1394 | 8.1394 | 11.7092 | 13.7092 | 9.5697 | 17.7092 | 29.4183 | 43.1275
6.9539 | 9.477 | 8.9539 | 7.9539 | 11.4309 | 13.4309 | 9.477 | 17.4309 | 28.8618 | 42.2928
3.8824 | 7.9412 | 5.8824 | 4.8824 | 6.8235 | 8.8235 | 7.9412 | 12.8235 | 19.6471 | 28.4706
4.5081 | 8.2541 | 6.5081 | 5.5081 | 7.7622 | 9.7622 | 8.2541 | 13.7622 | 21.5243 | 31.2865
5.4401 | 8.72 | 7.4401 | 6.4401 | 9.1601 | 11.1601 | 8.72 | 15.1601 | 24.3202 | 35.4803
7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955
6.3068 | 9.1534 | 8.3068 | 7.3068 | 10.4602 | 12.4602 | 9.1534 | 16.4602 | 26.9204 | 39.3807
2.4541 | 7.227 | 4.4541 | 3.4541 | 4.6811 | 6.6811 | 7.227 | 10.6811 | 15.3622 | 22.0434
6.616 | 9.308 | 8.616 | 7.616 | 10.924 | 12.924 | 9.308 | 16.924 | 27.848 | 40.772
6.1816 | 9.0908 | 8.1816 | 7.1816 | 10.2724 | 12.2724 | 9.0908 | 16.2724 | 26.5449 | 38.8173
4.1669 | 8.0835 | 6.1669 | 5.1669 | 7.2504 | 9.2504 | 8.0835 | 13.2504 | 20.5008 | 29.7512
5.6994 | 8.8497 | 7.6994 | 6.6994 | 9.5491 | 11.5491 | 8.8497 | 15.5491 | 25.0981 | 36.6472
6.0425 | 9.0212 | 8.0425 | 7.0425 | 10.0637 | 12.0637 | 9.0212 | 16.0637 | 26.1274 | 38.1911
10.3015 | 11.1508 | 12.3015 | 11.3015 | 16.4523 | 18.4523 | 11.1508 | 22.4523 | 38.9045 | 57.3568
5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381
2.9544 | 7.4772 | 4.9544 | 3.9544 | 5.4316 | 7.4316 | 7.4772 | 11.4316 | 16.8633 | 24.2949
8.086 | 10.043 | 10.086 | 9.086 | 13.129 | 15.129 | 10.043 | 19.129 | 32.258 | 47.3871
3.5671 | 7.7836 | 5.5671 | 4.5671 | 6.3507 | 8.3507 | 7.7836 | 12.3507 | 18.7014 | 27.0522
3.1336 | 7.5668 | 5.1336 | 4.1336 | 5.7004 | 7.7004 | 7.5668 | 11.7004 | 17.4008 | 25.1012
6.5277 | 9.2639 | 8.5277 | 7.5277 | 10.7916 | 12.7916 | 9.2639 | 16.7916 | 27.5831 | 40.3747
4.9065 | 8.4533 | 6.9065 | 5.9065 | 8.3598 | 10.3598 | 8.4533 | 14.3598 | 22.7195 | 33.0793
5.0165 | 8.5082 | 7.0165 | 6.0165 | 8.5247 | 10.5247 | 8.5082 | 14.5247 | 23.0494 | 33.5741
7.6593 | 9.8296 | 9.6593 | 8.6593 | 12.4889 | 14.4889 | 9.8296 | 18.4889 | 30.9778 | 45.4666
7.9067 | 9.9534 | 9.9067 | 8.9067 | 12.8601 | 14.8601 | 9.9534 | 18.8601 | 31.7202 | 46.5803
5.5669 | 8.7835 | 7.5669 | 6.5669 | 9.3504 | 11.3504 | 8.7835 | 15.3504 | 24.7008 | 36.0513
6.8194 | 9.4097 | 8.8194 | 7.8194 | 11.2291 | 13.2291 | 9.4097 | 17.2291 | 28.4582 | 41.6873
4.8316 | 8.4158 | 6.8316 | 5.8316 | 8.2475 | 10.2475 | 8.4158 | 14.2475 | 22.4949 | 32.7424
7.73 | 9.865 | 9.73 | 8.73 | 12.595 | 14.595 | 9.865 | 18.595 | 31.19 | 45.785
4.3301 | 8.1651 | 6.3301 | 5.3301 | 7.4952 | 9.4952 | 8.1651 | 13.4952 | 20.9904 | 30.4857
4.0174 | 8.0087 | 6.0174 | 5.0174 | 7.0261 | 9.0261 | 8.0087 | 13.0261 | 20.0522 | 29.0784
3.7223 | 7.8612 | 5.7223 | 4.7223 | 6.5835 | 8.5835 | 7.8612 | 12.5835 | 19.1669 | 27.7504
5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053
7.4619 | 9.731 | 9.4619 | 8.4619 | 12.1929 | 14.1929 | 9.731 | 18.1929 | 30.3858 | 44.5787
4.2939 | 8.1469 | 6.2939 | 5.2939 | 7.4408 | 9.4408 | 8.1469 | 13.4408 | 20.8817 | 30.3225
6.2435 | 9.1217 | 8.2435 | 7.2435 | 10.3652 | 12.3652 | 9.1217 | 16.3652 | 26.7304 | 39.0957
5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144
7.367 | 9.6835 | 9.367 | 8.367 | 12.0506 | 14.0506 | 9.6835 | 18.0506 | 30.1011 | 44.1517
9.1555 | 10.5777 | 11.1555 | 10.1555 | 14.7332 | 16.7332 | 10.5777 | 20.7332 | 35.4664 | 52.1996
4.4266 | 8.2133 | 6.4266 | 5.4266 | 7.64 | 9.64 | 8.2133 | 13.64 | 21.2799 | 30.9199
6.4001 | 9.2 | 8.4001 | 7.4001 | 10.6001 | 12.6001 | 9.2 | 16.6001 | 27.2002 | 39.8003
5.0045 | 8.5023 | 7.0045 | 6.0045 | 8.5068 | 10.5068 | 8.5023 | 14.5068 | 23.0136 | 33.5204
2.7353 | 7.3676 | 4.7353 | 3.7353 | 5.1029 | 7.1029 | 7.3676 | 11.1029 | 16.2058 | 23.3088
5.211 | 8.6055 | 7.211 | 6.211 | 8.8164 | 10.8164 | 8.6055 | 14.8164 | 23.6329 | 34.4493
5.7148 | 8.8574 | 7.7148 | 6.7148 | 9.5723 | 11.5723 | 8.8574 | 15.5723 | 25.1445 | 36.7168
2.991 | 7.4955 | 4.991 | 3.991 | 5.4865 | 7.4865 | 7.4955 | 11.4865 | 16.9729 | 24.4594
5.3673 | 8.6836 | 7.3673 | 6.3673 | 9.0509 | 11.0509 | 8.6836 | 15.0509 | 24.1019 | 35.1528
6.8222 | 9.4111 | 8.8222 | 7.8222 | 11.2333 | 13.2333 | 9.4111 | 17.2333 | 28.4667 | 41.7
5.639 | 8.8195 | 7.639 | 6.639 | 9.4586 | 11.4586 | 8.8195 | 15.4586 | 24.9171 | 36.3757
10.6751 | 11.3376 | 12.6751 | 11.6751 | 17.0127 | 19.0127 | 11.3376 | 23.0127 | 40.0254 | 59.0381
1.6411 | 6.8205 | 3.6411 | 2.6411 | 3.4616 | 5.4616 | 6.8205 | 9.4616 | 12.9232 | 18.3849
5.3028 | 8.6514 | 7.3028 | 6.3028 | 8.9542 | 10.9542 | 8.6514 | 14.9542 | 23.9083 | 34.8625
8.489 | 10.2445 | 10.489 | 9.489 | 13.7334 | 15.7334 | 10.2445 | 19.7334 | 33.4669 | 49.2003
6.2238 | 9.1119 | 8.2238 | 7.2238 | 10.3356 | 12.3356 | 9.1119 | 16.3356 | 26.6713 | 39.0069
5.7985 | 8.8993 | 7.7985 | 6.7985 | 9.6978 | 11.6978 | 8.8993 | 15.6978 | 25.3956 | 37.0935
7.9791 | 9.9895 | 9.9791 | 8.9791 | 12.9686 | 14.9686 | 9.9895 | 18.9686 | 31.9373 | 46.9059
6.6718 | 9.3359 | 8.6718 | 7.6718 | 11.0076 | 13.0076 | 9.3359 | 17.0076 | 28.0153 | 41.0229
2.7548 | 7.3774 | 4.7548 | 3.7548 | 5.1322 | 7.1322 | 7.3774 | 11.1322 | 16.2645 | 23.3967
3.7539 | 7.877 | 5.7539 | 4.7539 | 6.6309 | 8.6309 | 7.877 | 12.6309 | 19.2618 | 27.8927
4.0079 | 8.0039 | 6.0079 | 5.0079 | 7.0118 | 9.0118 | 8.0039 | 13.0118 | 20.0237 | 29.0355
8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039
6.8933 | 9.4467 | 8.8933 | 7.8933 | 11.34 | 13.34 | 9.4467 | 17.34 | 28.68 | 42.0201
3.0902 | 7.5451 | 5.0902 | 4.0902 | 5.6353 | 7.6353 | 7.5451 | 11.6353 | 17.2706 | 24.9059
3.6821 | 7.841 | 5.6821 | 4.6821 | 6.5231 | 8.5231 | 7.841 | 12.5231 | 19.0462 | 27.5692
3.021 | 7.5105 | 5.021 | 4.021 | 5.5315 | 7.5315 | 7.5105 | 11.5315 | 17.063 | 24.5945
8.4728 | 10.2364 | 10.4728 | 9.4728 | 13.7092 | 15.7092 | 10.2364 | 19.7092 | 33.4183 | 49.1275
3.493 | 7.7465 | 5.493 | 4.493 | 6.2395 | 8.2395 | 7.7465 | 12.2395 | 18.4791 | 26.7186
9.0142 | 10.5071 | 11.0142 | 10.0142 | 14.5214 | 16.5214 | 10.5071 | 20.5214 | 35.0427 | 51.5641
10.0246 | 11.0123 | 12.0246 | 11.0246 | 16.0368 | 18.0368 | 11.0123 | 22.0368 | 38.0737 | 56.1105
9.1517 | 10.5759 | 11.1517 | 10.1517 | 14.7276 | 16.7276 | 10.5759 | 20.7276 | 35.4552 | 52.1829
4.2742 | 8.1371 | 6.2742 | 5.2742 | 7.4113 | 9.4113 | 8.1371 | 13.4113 | 20.8226 | 30.2339
4.3436 | 8.1718 | 6.3436 | 5.3436 | 7.5153 | 9.5153 | 8.1718 | 13.5153 | 21.0307 | 30.546 | #REF!
7.5365 | 9.7683 | 9.5365 | 8.5365 | 12.3048 | 14.3048 | 9.7683 | 18.3048 | 30.6095 | 44.9143
2.6661 | 7.333 | 4.6661 | 3.6661 | 4.9991 | 6.9991 | 7.333 | 10.9991 | 15.9983 | 22.9974
5.1754 | 8.5877 | 7.1754 | 6.1754 | 8.7632 | 10.7632 | 8.5877 | 14.7632 | 23.5263 | 34.2895
5.602 | 8.801 | 7.602 | 6.602 | 9.4029 | 11.4029 | 8.801 | 15.4029 | 24.8059 | 36.2088
2.4497 | 7.2248 | 4.4497 | 3.4497 | 4.6745 | 6.6745 | 7.2248 | 10.6745 | 15.349 | 22.0234
8.632 | 10.316 | 10.632 | 9.632 | 13.948 | 15.948 | 10.316 | 19.948 | 33.8959 | 49.8439
7.3605 | 9.6802 | 9.3605 | 8.3605 | 12.0407 | 14.0407 | 9.6802 | 18.0407 | 30.0814 | 44.1221
6.2503 | 9.1251 | 8.2503 | 7.2503 | 10.3754 | 12.3754 | 9.1251 | 16.3754 | 26.7508 | 39.1262
6.4729 | 9.2365 | 8.4729 | 7.4729 | 10.7094 | 12.7094 | 9.2365 | 16.7094 | 27.4188 | 40.1282
5.0375 | 8.5187 | 7.0375 | 6.0375 | 8.5562 | 10.5562 | 8.5187 | 14.5562 | 23.1124 | 33.6686
6.4828 | 9.2414 | 8.4828 | 7.4828 | 10.7243 | 12.7243 | 9.2414 | 16.7243 | 27.4485 | 40.1728
8.6636 | 10.3318 | 10.6636 | 9.6636 | 13.9954 | 15.9954 | 10.3318 | 19.9954 | 33.9908 | 49.9862
6.1928 | 9.0964 | 8.1928 | 7.1928 | 10.2893 | 12.2893 | 9.0964 | 16.2893 | 26.5785 | 38.8678
5.2215 | 8.6108 | 7.2215 | 6.2215 | 8.8323 | 10.8323 | 8.6108 | 14.8323 | 23.6646 | 34.4969
3.3861 | 7.693 | 5.3861 | 4.3861 | 6.0791 | 8.0791 | 7.693 | 12.0791 | 18.1583 | 26.2374
10.7513 | 11.3757 | 12.7513 | 11.7513 | 17.127 | 19.127 | 11.3757 | 23.127 | 40.2539 | 59.3809
5.4192 | 8.7096 | 7.4192 | 6.4192 | 9.1288 | 11.1288 | 8.7096 | 15.1288 | 24.2576 | 35.3864
10.2533 | 11.1267 | 12.2533 | 11.2533 | 16.38 | 18.38 | 11.1267 | 22.38 | 38.7599 | 57.1399
4.7906 | 8.3953 | 6.7906 | 5.7906 | 8.1858 | 10.1858 | 8.3953 | 14.1858 | 22.3717 | 32.5575
5.4023 | 8.7011 | 7.4023 | 6.4023 | 9.1034 | 11.1034 | 8.7011 | 15.1034 | 24.2068 | 35.3102
9.2231 | 10.6116 | 11.2231 | 10.2231 | 14.8347 | 16.8347 | 10.6116 | 20.8347 | 35.6693 | 52.504
6.4629 | 9.2314 | 8.4629 | 7.4629 | 10.6943 | 12.6943 | 9.2314 | 16.6943 | 27.3886 | 40.0829
3.3717 | 7.6858 | 5.3717 | 4.3717 | 6.0575 | 8.0575 | 7.6858 | 12.0575 | 18.115 | 26.1724
5.6239 | 8.812 | 7.6239 | 6.6239 | 9.4359 | 11.4359 | 8.812 | 15.4359 | 24.8718 | 36.3078
9.3247 | 10.6624 | 11.3247 | 10.3247 | 14.9871 | 16.9871 | 10.6624 | 20.9871 | 35.9742 | 52.9613
4.3088 | 8.1544 | 6.3088 | 5.3088 | 7.4632 | 9.4632 | 8.1544 | 13.4632 | 20.9264 | 30.3896
5.0985 | 8.5493 | 7.0985 | 6.0985 | 8.6478 | 10.6478 | 8.5493 | 14.6478 | 23.2956 | 33.9434
7.6629 | 9.8315 | 9.6629 | 8.6629 | 12.4944 | 14.4944 | 9.8315 | 18.4944 | 30.9888 | 45.4832
9.3024 | 10.6512 | 11.3024 | 10.3024 | 14.9536 | 16.9536 | 10.6512 | 20.9536 | 35.9072 | 52.8609
8.7686 | 10.3843 | 10.7686 | 9.7686 | 14.1529 | 16.1529 | 10.3843 | 20.1529 | 34.3058 | 50.4587
8.1501 | 10.075 | 10.1501 | 9.1501 | 13.2251 | 15.2251 | 10.075 | 19.2251 | 32.4502 | 47.6753
6.7669 | 9.3835 | 8.7669 | 7.7669 | 11.1504 | 13.1504 | 9.3835 | 17.1504 | 28.3008 | 41.4512
6.0705 | 9.0352 | 8.0705 | 7.0705 | 10.1057 | 12.1057 | 9.0352 | 16.1057 | 26.2114 | 38.3171
5.7724 | 8.8862 | 7.7724 | 6.7724 | 9.6586 | 11.6586 | 8.8862 | 15.6586 | 25.3172 | 36.9757
7.6638 | 9.8319 | 9.6638 | 8.6638 | 12.4957 | 14.4957 | 9.8319 | 18.4957 | 30.9914 | 45.487
5.8442 | 8.9221 | 7.8442 | 6.8442 | 9.7663 | 11.7663 | 8.9221 | 15.7663 | 25.5325 | 37.2988
4.8173 | 8.4086 | 6.8173 | 5.8173 | 8.2259 | 10.2259 | 8.4086 | 14.2259 | 22.4518 | 32.6777
3.6353 | 7.8177 | 5.6353 | 4.6353 | 6.453 | 8.453 | 7.8177 | 12.453 | 18.9059 | 27.3589
3.3053 | 7.6526 | 5.3053 | 4.3053 | 5.9579 | 7.9579 | 7.6526 | 11.9579 | 17.9158 | 25.8737
5.0443 | 8.5222 | 7.0443 | 6.0443 | 8.5665 | 10.5665 | 8.5222 | 14.5665 | 23.133 | 33.6995
8.0763 | 10.0381 | 10.0763 | 9.0763 | 13.1144 | 15.1144 | 10.0381 | 19.1144 | 32.2289 | 47.3433
4.3336 | 8.1668 | 6.3336 | 5.3336 | 7.5004 | 9.5004 | 8.1668 | 13.5004 | 21.0008 | 30.5013
9.9359 | 10.9679 | 11.9359 | 10.9359 | 15.9038 | 17.9038 | 10.9679 | 21.9038 | 37.8077 | 55.7115
6.4882 | 9.2441 | 8.4882 | 7.4882 | 10.7323 | 12.7323 | 9.2441 | 16.7323 | 27.4646 | 40.1969
3.7597 | 7.8798 | 5.7597 | 4.7597 | 6.6395 | 8.6395 | 7.8798 | 12.6395 | 19.279 | 27.9185
4.1555 | 8.0777 | 6.1555 | 5.1555 | 7.2332 | 9.2332 | 8.0777 | 13.2332 | 20.4665 | 29.6997
2.6525 | 7.3263 | 4.6525 | 3.6525 | 4.9788 | 6.9788 | 7.3263 | 10.9788 | 15.9575 | 22.9363
1.8403 | 6.9201 | 3.8403 | 2.8403 | 3.7604 | 5.7604 | 6.9201 | 9.7604 | 13.5208 | 19.2812
2.6667 | 7.3334 | 4.6667 | 3.6667 | 5.0001 | 7.0001 | 7.3334 | 11.0001 | 16.0001 | 23.0002
6.4608 | 9.2304 | 8.4608 | 7.4608 | 10.6912 | 12.6912 | 9.2304 | 16.6912 | 27.3825 | 40.0737
4.1906 | 8.0953 | 6.1906 | 5.1906 | 7.2858 | 9.2858 | 8.0953 | 13.2858 | 20.5717 | 29.8575
8.6153 | 10.3077 | 10.6153 | 9.6153 | 13.923 | 15.923 | 10.3077 | 19.923 | 33.846 | 49.769
4.7385 | 8.3693 | 6.7385 | 5.7385 | 8.1078 | 10.1078 | 8.3693 | 14.1078 | 22.2156 | 32.3234
2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273
3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769
5.9707 | 8.9854 | 7.9707 | 6.9707 | 9.9561 | 11.9561 | 8.9854 | 15.9561 | 25.9121 | 37.8682
8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397
5.1237 | 8.5618 | 7.1237 | 6.1237 | 8.6855 | 10.6855 | 8.5618 | 14.6855 | 23.3711 | 34.0566
4.2034 | 8.1017 | 6.2034 | 5.2034 | 7.3051 | 9.3051 | 8.1017 | 13.3051 | 20.6102 | 29.9154
5.5663 | 8.7832 | 7.5663 | 6.5663 | 9.3495 | 11.3495 | 8.7832 | 15.3495 | 24.699 | 36.0484
6.8431 | 9.4215 | 8.8431 | 7.8431 | 11.2646 | 13.2646 | 9.4215 | 17.2646 | 28.5292 | 41.7939
6.8551 | 9.4276 | 8.8551 | 7.8551 | 11.2827 | 13.2827 | 9.4276 | 17.2827 | 28.5654 | 41.8481
4.4435 | 8.2217 | 6.4435 | 5.4435 | 7.6652 | 9.6652 | 8.2217 | 13.6652 | 21.3304 | 30.9956
9.454 | 10.727 | 11.454 | 10.454 | 15.181 | 17.181 | 10.727 | 21.181 | 36.3619 | 53.5429
7.8182 | 9.9091 | 9.8182 | 8.8182 | 12.7273 | 14.7273 | 9.9091 | 18.7273 | 31.4547 | 46.182
6.9341 | 9.4671 | 8.9341 | 7.9341 | 11.4012 | 13.4012 | 9.4671 | 17.4012 | 28.8023 | 42.2035
4.4815 | 8.2408 | 6.4815 | 5.4815 | 7.7223 | 9.7223 | 8.2408 | 13.7223 | 21.4445 | 31.1668
5.1586 | 8.5793 | 7.1586 | 6.1586 | 8.7379 | 10.7379 | 8.5793 | 14.7379 | 23.4758 | 34.2137
8.2539 | 10.1269 | 10.2539 | 9.2539 | 13.3808 | 15.3808 | 10.1269 | 19.3808 | 32.7616 | 48.1423
7.8806 | 9.9403 | 9.8806 | 8.8806 | 12.8209 | 14.8209 | 9.9403 | 18.8209 | 31.6419 | 46.4628
4.776 | 8.388 | 6.776 | 5.776 | 8.164 | 10.164 | 8.388 | 14.164 | 22.3281 | 32.4921
6.3025 | 9.1512 | 8.3025 | 7.3025 | 10.4537 | 12.4537 | 9.1512 | 16.4537 | 26.9074 | 39.3611
6.7528 | 9.3764 | 8.7528 | 7.7528 | 11.1292 | 13.1292 | 9.3764 | 17.1292 | 28.2584 | 41.3875
6.2989 | 9.1495 | 8.2989 | 7.2989 | 10.4484 | 12.4484 | 9.1495 | 16.4484 | 26.8968 | 39.3451
6.9488 | 9.4744 | 8.9488 | 7.9488 | 11.4232 | 13.4232 | 9.4744 | 17.4232 | 28.8464 | 42.2696
3.3735 | 7.6867 | 5.3735 | 4.3735 | 6.0602 | 8.0602 | 7.6867 | 12.0602 | 18.1204 | 26.1806
8.8156 | 10.4078 | 10.8156 | 9.8156 | 14.2235 | 16.2235 | 10.4078 | 20.2235 | 34.4469 | 50.6704
6.1938 | 9.0969 | 8.1938 | 7.1938 | 10.2907 | 12.2907 | 9.0969 | 16.2907 | 26.5813 | 38.872
2.6892 | 7.3446 | 4.6892 | 3.6892 | 5.0338 | 7.0338 | 7.3446 | 11.0338 | 16.0676 | 23.1013
9.693 | 10.8465 | 11.693 | 10.693 | 15.5395 | 17.5395 | 10.8465 | 21.5395 | 37.0789 | 54.6184
7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955
7.6207 | 9.8104 | 9.6207 | 8.6207 | 12.4311 | 14.4311 | 9.8104 | 18.4311 | 30.8621 | 45.2932
5.3109 | 8.6554 | 7.3109 | 6.3109 | 8.9663 | 10.9663 | 8.6554 | 14.9663 | 23.9327 | 34.899
5.815 | 8.9075 | 7.815 | 6.815 | 9.7225 | 11.7225 | 8.9075 | 15.7225 | 25.445 | 37.1675
8.6974 | 10.3487 | 10.6974 | 9.6974 | 14.0461 | 16.0461 | 10.3487 | 20.0461 | 34.0922 | 50.1383
4.5436 | 8.2718 | 6.5436 | 5.5436 | 7.8155 | 9.8155 | 8.2718 | 13.8155 | 21.6309 | 31.4464
3.342 | 7.671 | 5.342 | 4.342 | 6.013 | 8.013 | 7.671 | 12.013 | 18.0259 | 26.0389
3.0612 | 7.5306 | 5.0612 | 4.0612 | 5.5918 | 7.5918 | 7.5306 | 11.5918 | 17.1837 | 24.7755
8.378 | 10.189 | 10.378 | 9.378 | 13.567 | 15.567 | 10.189 | 19.567 | 33.1339 | 48.7009
5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099
5.55 | 8.775 | 7.55 | 6.55 | 9.325 | 11.325 | 8.775 | 15.325 | 24.65 | 35.9751
8.0143 | 10.0072 | 10.0143 | 9.0143 | 13.0215 | 15.0215 | 10.0072 | 19.0215 | 32.043 | 47.0645
4.2615 | 8.1308 | 6.2615 | 5.2615 | 7.3923 | 9.3923 | 8.1308 | 13.3923 | 20.7846 | 30.1769
4.3816 | 8.1908 | 6.3816 | 5.3816 | 7.5724 | 9.5724 | 8.1908 | 13.5724 | 21.1449 | 30.7173
5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099
7.8028 | 9.9014 | 9.8028 | 8.8028 | 12.7042 | 14.7042 | 9.9014 | 18.7042 | 31.4083 | 46.1125
8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397
5.5132 | 8.7566 | 7.5132 | 6.5132 | 9.2698 | 11.2698 | 8.7566 | 15.2698 | 24.5397 | 35.8095
7.8861 | 9.9431 | 9.8861 | 8.8861 | 12.8292 | 14.8292 | 9.9431 | 18.8292 | 31.6583 | 46.4875
6.7892 | 9.3946 | 8.7892 | 7.7892 | 11.1838 | 13.1838 | 9.3946 | 17.1838 | 28.3676 | 41.5514
4.1869 | 8.0934 | 6.1869 | 5.1869 | 7.2803 | 9.2803 | 8.0934 | 13.2803 | 20.5606 | 29.8409
4.1938 | 8.0969 | 6.1938 | 5.1938 | 7.2907 | 9.2907 | 8.0969 | 13.2907 | 20.5813 | 29.872
3.2575 | 7.6287 | 5.2575 | 4.2575 | 5.8862 | 7.8862 | 7.6287 | 11.8862 | 17.7724 | 25.6586
4.0356 | 8.0178 | 6.0356 | 5.0356 | 7.0534 | 9.0534 | 8.0178 | 13.0534 | 20.1068 | 29.1602
6.4349 | 9.2175 | 8.4349 | 7.4349 | 10.6524 | 12.6524 | 9.2175 | 16.6524 | 27.3048 | 39.9572
7.869 | 9.9345 | 9.869 | 8.869 | 12.8035 | 14.8035 | 9.9345 | 18.8035 | 31.607 | 46.4105
6.7712 | 9.3856 | 8.7712 | 7.7712 | 11.1568 | 13.1568 | 9.3856 | 17.1568 | 28.3136 | 41.4704
8.0857 | 10.0429 | 10.0857 | 9.0857 | 13.1286 | 15.1286 | 10.0429 | 19.1286 | 32.2572 | 47.3859
7.7566 | 9.8783 | 9.7566 | 8.7566 | 12.6349 | 14.6349 | 9.8783 | 18.6349 | 31.2699 | 45.9048
9.6525 | 10.8263 | 11.6525 | 10.6525 | 15.4788 | 17.4788 | 10.8263 | 21.4788 | 36.9575 | 54.4363
7.2986 | 9.6493 | 9.2986 | 8.2986 | 11.948 | 13.948 | 9.6493 | 17.948 | 29.8959 | 43.8439
4.0521 | 8.0261 | 6.0521 | 5.0521 | 7.0782 | 9.0782 | 8.0261 | 13.0782 | 20.1564 | 29.2346
7.0371 | 9.5185 | 9.0371 | 8.0371 | 11.5556 | 13.5556 | 9.5185 | 17.5556 | 29.1112 | 42.6668
2.233 | 7.1165 | 4.233 | 3.233 | 4.3495 | 6.3495 | 7.1165 | 10.3495 | 14.6991 | 21.0486
7.2275 | 9.6137 | 9.2275 | 8.2275 | 11.8412 | 13.8412 | 9.6137 | 17.8412 | 29.6825 | 43.5237
6.3896 | 9.1948 | 8.3896 | 7.3896 | 10.5844 | 12.5844 | 9.1948 | 16.5844 | 27.1688 | 39.7532
6.4116 | 9.2058 | 8.4116 | 7.4116 | 10.6174 | 12.6174 | 9.2058 | 16.6174 | 27.2349 | 39.8523
4.7322 | 8.3661 | 6.7322 | 5.7322 | 8.0983 | 10.0983 | 8.3661 | 14.0983 | 22.1965 | 32.2948
6.7518 | 9.3759 | 8.7518 | 7.7518 | 11.1277 | 13.1277 | 9.3759 | 17.1277 | 28.2554 | 41.3831
4.1562 | 8.0781 | 6.1562 | 5.1562 | 7.2343 | 9.2343 | 8.0781 | 13.2343 | 20.4686 | 29.7029
3.8186 | 7.9093 | 5.8186 | 4.8186 | 6.7279 | 8.7279 | 7.9093 | 12.7279 | 19.4557 | 28.1836
4.9033 | 8.4517 | 6.9033 | 5.9033 | 8.355 | 10.355 | 8.4517 | 14.355 | 22.7099 | 33.0649
3.8613 | 7.9307 | 5.8613 | 4.8613 | 6.792 | 8.792 | 7.9307 | 12.792 | 19.584 | 28.376
8.8507 | 10.4253 | 10.8507 | 9.8507 | 14.276 | 16.276 | 10.4253 | 20.276 | 34.5521 | 50.8281
4.7771 | 8.3886 | 6.7771 | 5.7771 | 8.1657 | 10.1657 | 8.3886 | 14.1657 | 22.3314 | 32.4971
6.5063 | 9.2532 | 8.5063 | 7.5063 | 10.7595 | 12.7595 | 9.2532 | 16.7595 | 27.519 | 40.2786
6.9271 | 9.4636 | 8.9271 | 7.9271 | 11.3907 | 13.3907 | 9.4636 | 17.3907 | 28.7813 | 42.172
4.2626 | 8.1313 | 6.2626 | 5.2626 | 7.394 | 9.394 | 8.1313 | 13.394 | 20.7879 | 30.1819
2.6952 | 7.3476 | 4.6952 | 3.6952 | 5.0428 | 7.0428 | 7.3476 | 11.0428 | 16.0856 | 23.1284
7.9818 | 9.9909 | 9.9818 | 8.9818 | 12.9728 | 14.9728 | 9.9909 | 18.9728 | 31.9455 | 46.9183
4.4602 | 8.2301 | 6.4602 | 5.4602 | 7.6903 | 9.6903 | 8.2301 | 13.6903 | 21.3806 | 31.0709
7.8904 | 9.9452 | 9.8904 | 8.8904 | 12.8356 | 14.8356 | 9.9452 | 18.8356 | 31.6712 | 46.5069
4.5586 | 8.2793 | 6.5586 | 5.5586 | 7.8379 | 9.8379 | 8.2793 | 13.8379 | 21.6757 | 31.5136
5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013
4.5162 | 8.2581 | 6.5162 | 5.5162 | 7.7743 | 9.7743 | 8.2581 | 13.7743 | 21.5486 | 31.3228
4.8841 | 8.442 | 6.8841 | 5.8841 | 8.3261 | 10.3261 | 8.442 | 14.3261 | 22.6522 | 32.9782
5.6401 | 8.8201 | 7.6401 | 6.6401 | 9.4602 | 11.4602 | 8.8201 | 15.4602 | 24.9204 | 36.3806
9.7333 | 10.8666 | 11.7333 | 10.7333 | 15.5999 | 17.5999 | 10.8666 | 21.5999 | 37.1998 | 54.7997
4.4464 | 8.2232 | 6.4464 | 5.4464 | 7.6696 | 9.6696 | 8.2232 | 13.6696 | 21.3391 | 31.0087
3.4011 | 7.7006 | 5.4011 | 4.4011 | 6.1017 | 8.1017 | 7.7006 | 12.1017 | 18.2034 | 26.305
5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053
2.1888 | 7.0944 | 4.1888 | 3.1888 | 4.2832 | 6.2832 | 7.0944 | 10.2832 | 14.5665 | 20.8497
6.8979 | 9.449 | 8.8979 | 7.8979 | 11.3469 | 13.3469 | 9.449 | 17.3469 | 28.6937 | 42.0406
4.4544 | 8.2272 | 6.4544 | 5.4544 | 7.6816 | 9.6816 | 8.2272 | 13.6816 | 21.3633 | 31.0449
5.3782 | 8.6891 | 7.3782 | 6.3782 | 9.0673 | 11.0673 | 8.6891 | 15.0673 | 24.1346 | 35.202
4.8642 | 8.4321 | 6.8642 | 5.8642 | 8.2962 | 10.2962 | 8.4321 | 14.2962 | 22.5925 | 32.8887
6.4795 | 9.2398 | 8.4795 | 7.4795 | 10.7193 | 12.7193 | 9.2398 | 16.7193 | 27.4386 | 40.1579
6.2353 | 9.1177 | 8.2353 | 7.2353 | 10.353 | 12.353 | 9.1177 | 16.353 | 26.7059 | 39.0589
6.6358 | 9.3179 | 8.6358 | 7.6358 | 10.9537 | 12.9537 | 9.3179 | 16.9537 | 27.9073 | 40.861
5.2598 | 8.6299 | 7.2598 | 6.2598 | 8.8898 | 10.8898 | 8.6299 | 14.8898 | 23.7795 | 34.6693
5.8382 | 8.9191 | 7.8382 | 6.8382 | 9.7573 | 11.7573 | 8.9191 | 15.7573 | 25.5145 | 37.2718
3.6537 | 7.8268 | 5.6537 | 4.6537 | 6.4805 | 8.4805 | 7.8268 | 12.4805 | 18.961 | 27.4415
10.3093 | 11.1546 | 12.3093 | 11.3093 | 16.4639 | 18.4639 | 11.1546 | 22.4639 | 38.9278 | 57.3917
2.9072 | 7.4536 | 4.9072 | 3.9072 | 5.3609 | 7.3609 | 7.4536 | 11.3609 | 16.7217 | 24.0826
8.8398 | 10.4199 | 10.8398 | 9.8398 | 14.2596 | 16.2596 | 10.4199 | 20.2596 | 34.5193 | 50.7789
4.7994 | 8.3997 | 6.7994 | 5.7994 | 8.1991 | 10.1991 | 8.3997 | 14.1991 | 22.3981 | 32.5972
4.8728 | 8.4364 | 6.8728 | 5.8728 | 8.3092 | 10.3092 | 8.4364 | 14.3092 | 22.6183 | 32.9275
8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039
8.2877 | 10.1438 | 10.2877 | 9.2877 | 13.4315 | 15.4315 | 10.1438 | 19.4315 | 32.863 | 48.2945
5.1521 | 8.576 | 7.1521 | 6.1521 | 8.7281 | 10.7281 | 8.576 | 14.7281 | 23.4562 | 34.1843
7.8614 | 9.9307 | 9.8614 | 8.8614 | 12.7921 | 14.7921 | 9.9307 | 18.7921 | 31.5843 | 46.3764
7.2199 | 9.61 | 9.2199 | 8.2199 | 11.8299 | 13.8299 | 9.61 | 17.8299 | 29.6598 | 43.4897
5.6179 | 8.8089 | 7.6179 | 6.6179 | 9.4268 | 11.4268 | 8.8089 | 15.4268 | 24.8536 | 36.2804
2.7189 | 7.3595 | 4.7189 | 3.7189 | 5.0784 | 7.0784 | 7.3595 | 11.0784 | 16.1568 | 23.2352
7.0937 | 9.5468 | 9.0937 | 8.0937 | 11.6405 | 13.6405 | 9.5468 | 17.6405 | 29.281 | 42.9215
6.5789 | 9.2894 | 8.5789 | 7.5789 | 10.8683 | 12.8683 | 9.2894 | 16.8683 | 27.7367 | 40.605
4.9738 | 8.4869 | 6.9738 | 5.9738 | 8.4606 | 10.4606 | 8.4869 | 14.4606 | 22.9213 | 33.3819
5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741
3.3249 | 7.6624 | 5.3249 | 4.3249 | 5.9873 | 7.9873 | 7.6624 | 11.9873 | 17.9746 | 25.9618
5.9637 | 8.9818 | 7.9637 | 6.9637 | 9.9455 | 11.9455 | 8.9818 | 15.9455 | 25.891 | 37.8365
3.7881 | 7.894 | 5.7881 | 4.7881 | 6.6821 | 8.6821 | 7.894 | 12.6821 | 19.3643 | 28.0464
8.004 | 10.002 | 10.004 | 9.004 | 13.0059 | 15.0059 | 10.002 | 19.0059 | 32.0119 | 47.0178
7.6199 | 9.8099 | 9.6199 | 8.6199 | 12.4298 | 14.4298 | 9.8099 | 18.4298 | 30.8596 | 45.2893
5.0882 | 8.5441 | 7.0882 | 6.0882 | 8.6323 | 10.6323 | 8.5441 | 14.6323 | 23.2646 | 33.8968
4.9297 | 8.4649 | 6.9297 | 5.9297 | 8.3946 | 10.3946 | 8.4649 | 14.3946 | 22.7891 | 33.1837
1.9638 | 6.9819 | 3.9638 | 2.9638 | 3.9457 | 5.9457 | 6.9819 | 9.9457 | 13.8914 | 19.8371
5.227 | 8.6135 | 7.227 | 6.227 | 8.8405 | 10.8405 | 8.6135 | 14.8405 | 23.6809 | 34.5214
2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273
6.9433 | 9.4717 | 8.9433 | 7.9433 | 11.415 | 13.415 | 9.4717 | 17.415 | 28.83 | 42.245
5.765 | 8.8825 | 7.765 | 6.765 | 9.6475 | 11.6475 | 8.8825 | 15.6475 | 25.295 | 36.9425
2.6494 | 7.3247 | 4.6494 | 3.6494 | 4.9741 | 6.9741 | 7.3247 | 10.9741 | 15.9482 | 22.9223
7.3038 | 9.6519 | 9.3038 | 8.3038 | 11.9556 | 13.9556 | 9.6519 | 17.9556 | 29.9113 | 43.8669
3.554 | 7.777 | 5.554 | 4.554 | 6.3309 | 8.3309 | 7.777 | 12.3309 | 18.6619 | 26.9928
5.9113 | 8.9557 | 7.9113 | 6.9113 | 9.867 | 11.867 | 8.9557 | 15.867 | 25.7339 | 37.6009
8.773 | 10.3865 | 10.773 | 9.773 | 14.1595 | 16.1595 | 10.3865 | 20.1595 | 34.319 | 50.4785
6.175 | 9.0875 | 8.175 | 7.175 | 10.2625 | 12.2625 | 9.0875 | 16.2625 | 26.5251 | 38.7876
7.0464 | 9.5232 | 9.0464 | 8.0464 | 11.5695 | 13.5695 | 9.5232 | 17.5695 | 29.1391 | 42.7086
4.9413 | 8.4707 | 6.9413 | 5.9413 | 8.412 | 10.412 | 8.4707 | 14.412 | 22.824 | 33.236
4.8679 | 8.434 | 6.8679 | 5.8679 | 8.3019 | 10.3019 | 8.434 | 14.3019 | 22.6038 | 32.9057
4.8742 | 8.4371 | 6.8742 | 5.8742 | 8.3113 | 10.3113 | 8.4371 | 14.3113 | 22.6226 | 32.9339
9.329 | 10.6645 | 11.329 | 10.329 | 14.9935 | 16.9935 | 10.6645 | 20.9935 | 35.987 | 52.9806
7.5224 | 9.7612 | 9.5224 | 8.5224 | 12.2836 | 14.2836 | 9.7612 | 18.2836 | 30.5671 | 44.8507
8.1979 | 10.0989 | 10.1979 | 9.1979 | 13.2968 | 15.2968 | 10.0989 | 19.2968 | 32.5936 | 47.8904
5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488
8.1953 | 10.0977 | 10.1953 | 9.1953 | 13.293 | 15.293 | 10.0977 | 19.293 | 32.586 | 47.8791
4.9143 | 8.4572 | 6.9143 | 5.9143 | 8.3715 | 10.3715 | 8.4572 | 14.3715 | 22.7429 | 33.1144
8.9991 | 10.4995 | 10.9991 | 9.9991 | 14.4986 | 16.4986 | 10.4995 | 20.4986 | 34.9973 | 51.4959
3.9365 | 7.9683 | 5.9365 | 4.9365 | 6.9048 | 8.9048 | 7.9683 | 12.9048 | 19.8096 | 28.7143
7.8134 | 9.9067 | 9.8134 | 8.8134 | 12.7201 | 14.7201 | 9.9067 | 18.7201 | 31.4401 | 46.1602
4.0634 | 8.0317 | 6.0634 | 5.0634 | 7.0951 | 9.0951 | 8.0317 | 13.0951 | 20.1902 | 29.2853
6.7403 | 9.3702 | 8.7403 | 7.7403 | 11.1105 | 13.1105 | 9.3702 | 17.1105 | 28.221 | 41.3314
5.6408 | 8.8204 | 7.6408 | 6.6408 | 9.4611 | 11.4611 | 8.8204 | 15.4611 | 24.9223 | 36.3834
6.2507 | 9.1254 | 8.2507 | 7.2507 | 10.3761 | 12.3761 | 9.1254 | 16.3761 | 26.7522 | 39.1283
8.3342 | 10.1671 | 10.3342 | 9.3342 | 13.5013 | 15.5013 | 10.1671 | 19.5013 | 33.0026 | 48.5039
9.8378 | 10.9189 | 11.8378 | 10.8378 | 15.7567 | 17.7567 | 10.9189 | 21.7567 | 37.5135 | 55.2702
5.9193 | 8.9596 | 7.9193 | 6.9193 | 9.8789 | 11.8789 | 8.9596 | 15.8789 | 25.7578 | 37.6367
9.7806 | 10.8903 | 11.7806 | 10.7806 | 15.6709 | 17.6709 | 10.8903 | 21.6709 | 37.3418 | 55.0127
7.2998 | 9.6499 | 9.2998 | 8.2998 | 11.9497 | 13.9497 | 9.6499 | 17.9497 | 29.8993 | 43.849
5.2258 | 8.6129 | 7.2258 | 6.2258 | 8.8387 | 10.8387 | 8.6129 | 14.8387 | 23.6775 | 34.5162
5.5571 | 8.7785 | 7.5571 | 6.5571 | 9.3356 | 11.3356 | 8.7785 | 15.3356 | 24.6712 | 36.0068
3.6445 | 7.8223 | 5.6445 | 4.6445 | 6.4668 | 8.4668 | 7.8223 | 12.4668 | 18.9335 | 27.4003
4.0026 | 8.0013 | 6.0026 | 5.0026 | 7.0039 | 9.0039 | 8.0013 | 13.0039 | 20.0078 | 29.0117
6.0532 | 9.0266 | 8.0532 | 7.0532 | 10.0798 | 12.0798 | 9.0266 | 16.0798 | 26.1595 | 38.2393
6.9761 | 9.4881 | 8.9761 | 7.9761 | 11.4642 | 13.4642 | 9.4881 | 17.4642 | 28.9284 | 42.3925
2.4113 | 7.2056 | 4.4113 | 3.4113 | 4.6169 | 6.6169 | 7.2056 | 10.6169 | 15.2338 | 21.8508
3.7525 | 7.8762 | 5.7525 | 4.7525 | 6.6287 | 8.6287 | 7.8762 | 12.6287 | 19.2575 | 27.8862
6.4384 | 9.2192 | 8.4384 | 7.4384 | 10.6576 | 12.6576 | 9.2192 | 16.6576 | 27.3151 | 39.9727
1.4433 | 6.7216 | 3.4433 | 2.4433 | 3.1649 | 5.1649 | 6.7216 | 9.1649 | 12.3299 | 17.4948
7.9113 | 9.9557 | 9.9113 | 8.9113 | 12.867 | 14.867 | 9.9557 | 18.867 | 31.734 | 46.6009
4.1557 | 8.0779 | 6.1557 | 5.1557 | 7.2336 | 9.2336 | 8.0779 | 13.2336 | 20.4672 | 29.7007
9.7438 | 10.8719 | 11.7438 | 10.7438 | 15.6157 | 17.6157 | 10.8719 | 21.6157 | 37.2314 | 54.8471
8.0146 | 10.0073 | 10.0146 | 9.0146 | 13.0219 | 15.0219 | 10.0073 | 19.0219 | 32.0438 | 47.0657
7.2032 | 9.6016 | 9.2032 | 8.2032 | 11.8048 | 13.8048 | 9.6016 | 17.8048 | 29.6096 | 43.4144
5.1038 | 8.5519 | 7.1038 | 6.1038 | 8.6557 | 10.6557 | 8.5519 | 14.6557 | 23.3113 | 33.967
10.3046 | 11.1523 | 12.3046 | 11.3046 | 16.4569 | 18.4569 | 11.1523 | 22.4569 | 38.9138 | 57.3707
6.0128 | 9.0064 | 8.0128 | 7.0128 | 10.0192 | 12.0192 | 9.0064 | 16.0192 | 26.0383 | 38.0575
5.3452 | 8.6726 | 7.3452 | 6.3452 | 9.0178 | 11.0178 | 8.6726 | 15.0178 | 24.0356 | 35.0535
5.0104 | 8.5052 | 7.0104 | 6.0104 | 8.5156 | 10.5156 | 8.5052 | 14.5156 | 23.0312 | 33.5469
8.5886 | 10.2943 | 10.5886 | 9.5886 | 13.8829 | 15.8829 | 10.2943 | 19.8829 | 33.7658 | 49.6487
4.7374 | 8.3687 | 6.7374 | 5.7374 | 8.1061 | 10.1061 | 8.3687 | 14.1061 | 22.2122 | 32.3184
4.205 | 8.1025 | 6.205 | 5.205 | 7.3075 | 9.3075 | 8.1025 | 13.3075 | 20.6151 | 29.9226
6.7811 | 9.3906 | 8.7811 | 7.7811 | 11.1717 | 13.1717 | 9.3906 | 17.1717 | 28.3433 | 41.515
5.058 | 8.529 | 7.058 | 6.058 | 8.5871 | 10.5871 | 8.529 | 14.5871 | 23.1741 | 33.7612
5.1781 | 8.5891 | 7.1781 | 6.1781 | 8.7672 | 10.7672 | 8.5891 | 14.7672 | 23.5343 | 34.3015
2.0437 | 7.0219 | 4.0437 | 3.0437 | 4.0656 | 6.0656 | 7.0219 | 10.0656 | 14.1312 | 20.1968
7.546 | 9.773 | 9.546 | 8.546 | 12.319 | 14.319 | 9.773 | 18.319 | 30.6379 | 44.9569
5.6743 | 8.8371 | 7.6743 | 6.6743 | 9.5114 | 11.5114 | 8.8371 | 15.5114 | 25.0229 | 36.5343
4.0812 | 8.0406 | 6.0812 | 5.0812 | 7.1218 | 9.1218 | 8.0406 | 13.1218 | 20.2435 | 29.3653
9.5518 | 10.7759 | 11.5518 | 10.5518 | 15.3277 | 17.3277 | 10.7759 | 21.3277 | 36.6555 | 53.9832
7.9334 | 9.9667 | 9.9334 | 8.9334 | 12.9001 | 14.9001 | 9.9667 | 18.9001 | 31.8003 | 46.7004
4.7753 | 8.3876 | 6.7753 | 5.7753 | 8.1629 | 10.1629 | 8.3876 | 14.1629 | 22.3258 | 32.4888
8.5211 | 10.2606 | 10.5211 | 9.5211 | 13.7817 | 15.7817 | 10.2606 | 19.7817 | 33.5634 | 49.3451
5.7198 | 8.8599 | 7.7198 | 6.7198 | 9.5797 | 11.5797 | 8.8599 | 15.5797 | 25.1594 | 36.7391
4.9962 | 8.4981 | 6.9962 | 5.9962 | 8.4943 | 10.4943 | 8.4981 | 14.4943 | 22.9886 | 33.4829
5.1437 | 8.5718 | 7.1437 | 6.1437 | 8.7155 | 10.7155 | 8.5718 | 14.7155 | 23.4311 | 34.1466
5.9165 | 8.9583 | 7.9165 | 6.9165 | 9.8748 | 11.8748 | 8.9583 | 15.8748 | 25.7496 | 37.6243
6.5709 | 9.2855 | 8.5709 | 7.5709 | 10.8564 | 12.8564 | 9.2855 | 16.8564 | 27.7128 | 40.5691
4.407 | 8.2035 | 6.407 | 5.407 | 7.6105 | 9.6105 | 8.2035 | 13.6105 | 21.2209 | 30.8314
7.6827 | 9.8413 | 9.6827 | 8.6827 | 12.524 | 14.524 | 9.8413 | 18.524 | 31.048 | 45.572
5.0637 | 8.5318 | 7.0637 | 6.0637 | 8.5955 | 10.5955 | 8.5318 | 14.5955 | 23.191 | 33.7865
3.1421 | 7.5711 | 5.1421 | 4.1421 | 5.7132 | 7.7132 | 7.5711 | 11.7132 | 17.4263 | 25.1395
8.3315 | 10.1657 | 10.3315 | 9.3315 | 13.4972 | 15.4972 | 10.1657 | 19.4972 | 32.9944 | 48.4916
7.0219 | 9.5109 | 9.0219 | 8.0219 | 11.5328 | 13.5328 | 9.5109 | 17.5328 | 29.0656 | 42.5985
7.4577 | 9.7289 | 9.4577 | 8.4577 | 12.1866 | 14.1866 | 9.7289 | 18.1866 | 30.3732 | 44.5599
8.7512 | 10.3756 | 10.7512 | 9.7512 | 14.1268 | 16.1268 | 10.3756 | 20.1268 | 34.2535 | 50.3803
3.186 | 7.593 | 5.186 | 4.186 | 5.779 | 7.779 | 7.593 | 11.779 | 17.558 | 25.337
3.9737 | 7.9868 | 5.9737 | 4.9737 | 6.9605 | 8.9605 | 7.9868 | 12.9605 | 19.921 | 28.8815
6.1466 | 9.0733 | 8.1466 | 7.1466 | 10.2199 | 12.2199 | 9.0733 | 16.2199 | 26.4399 | 38.6598
4.2176 | 8.1088 | 6.2176 | 5.2176 | 7.3264 | 9.3264 | 8.1088 | 13.3264 | 20.6527 | 29.9791
6.6912 | 9.3456 | 8.6912 | 7.6912 | 11.0368 | 13.0368 | 9.3456 | 17.0368 | 28.0737 | 41.1105
4.7236 | 8.3618 | 6.7236 | 5.7236 | 8.0853 | 10.0853 | 8.3618 | 14.0853 | 22.1707 | 32.256
4.7267 | 8.3634 | 6.7267 | 5.7267 | 8.0901 | 10.0901 | 8.3634 | 14.0901 | 22.1802 | 32.2704
7.199 | 9.5995 | 9.199 | 8.199 | 11.7985 | 13.7985 | 9.5995 | 17.7985 | 29.5969 | 43.3954
3.7067 | 7.8534 | 5.7067 | 4.7067 | 6.5601 | 8.5601 | 7.8534 | 12.5601 | 19.1202 | 27.6803
5.995 | 8.9975 | 7.995 | 6.995 | 9.9925 | 11.9925 | 8.9975 | 15.9925 | 25.9851 | 37.9776
5.0831 | 8.5415 | 7.0831 | 6.0831 | 8.6246 | 10.6246 | 8.5415 | 14.6246 | 23.2493 | 33.8739
6.1092 | 9.0546 | 8.1092 | 7.1092 | 10.1638 | 12.1638 | 9.0546 | 16.1638 | 26.3277 | 38.4915
8.5861 | 10.2931 | 10.5861 | 9.5861 | 13.8792 | 15.8792 | 10.2931 | 19.8792 | 33.7584 | 49.6375
5.3112 | 8.6556 | 7.3112 | 6.3112 | 8.9668 | 10.9668 | 8.6556 | 14.9668 | 23.9337 | 34.9005
3.0662 | 7.5331 | 5.0662 | 4.0662 | 5.5993 | 7.5993 | 7.5331 | 11.5993 | 17.1985 | 24.7978
5.713 | 8.8565 | 7.713 | 6.713 | 9.5695 | 11.5695 | 8.8565 | 15.5695 | 25.139 | 36.7085
2.1945 | 7.0972 | 4.1945 | 3.1945 | 4.2917 | 6.2917 | 7.0972 | 10.2917 | 14.5834 | 20.8751
4.0199 | 8.01 | 6.0199 | 5.0199 | 7.0299 | 9.0299 | 8.01 | 13.0299 | 20.0597 | 29.0896
6.6125 | 9.3062 | 8.6125 | 7.6125 | 10.9187 | 12.9187 | 9.3062 | 16.9187 | 27.8374 | 40.7562
6.4942 | 9.2471 | 8.4942 | 7.4942 | 10.7413 | 12.7413 | 9.2471 | 16.7413 | 27.4826 | 40.2239
5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144
5.964 | 8.982 | 7.964 | 6.964 | 9.946 | 11.946 | 8.982 | 15.946 | 25.8919 | 37.8379
5.7816 | 8.8908 | 7.7816 | 6.7816 | 9.6724 | 11.6724 | 8.8908 | 15.6724 | 25.3449 | 37.0173
3.5707 | 7.7853 | 5.5707 | 4.5707 | 6.356 | 8.356 | 7.7853 | 12.356 | 18.712 | 27.068
3.9955 | 7.9978 | 5.9955 | 4.9955 | 6.9933 | 8.9933 | 7.9978 | 12.9933 | 19.9866 | 28.9799
6.0997 | 9.0499 | 8.0997 | 7.0997 | 10.1496 | 12.1496 | 9.0499 | 16.1496 | 26.2992 | 38.4487
7.8375 | 9.9188 | 9.8375 | 8.8375 | 12.7563 | 14.7563 | 9.9188 | 18.7563 | 31.5125 | 46.2688
6.5393 | 9.2696 | 8.5393 | 7.5393 | 10.8089 | 12.8089 | 9.2696 | 16.8089 | 27.6178 | 40.4267
3.8684 | 7.9342 | 5.8684 | 4.8684 | 6.8026 | 8.8026 | 7.9342 | 12.8026 | 19.6051 | 28.4077
5.8862 | 8.9431 | 7.8862 | 6.8862 | 9.8293 | 11.8293 | 8.9431 | 15.8293 | 25.6586 | 37.4878
4.754 | 8.377 | 6.754 | 5.754 | 8.131 | 10.131 | 8.377 | 14.131 | 22.262 | 32.3929
3.8834 | 7.9417 | 5.8834 | 4.8834 | 6.8251 | 8.8251 | 7.9417 | 12.8251 | 19.6503 | 28.4754
5.5401 | 8.7701 | 7.5401 | 6.5401 | 9.3102 | 11.3102 | 8.7701 | 15.3102 | 24.6204 | 35.9306
6.0247 | 9.0124 | 8.0247 | 7.0247 | 10.0371 | 12.0371 | 9.0124 | 16.0371 | 26.0741 | 38.1112
4.9316 | 8.4658 | 6.9316 | 5.9316 | 8.3975 | 10.3975 | 8.4658 | 14.3975 | 22.7949 | 33.1924
9.3444 | 10.6722 | 11.3444 | 10.3444 | 15.0166 | 17.0166 | 10.6722 | 21.0166 | 36.0332 | 53.0498
6.4224 | 9.2112 | 8.4224 | 7.4224 | 10.6336 | 12.6336 | 9.2112 | 16.6336 | 27.2672 | 39.9008
5.0339 | 8.5169 | 7.0339 | 6.0339 | 8.5508 | 10.5508 | 8.5169 | 14.5508 | 23.1016 | 33.6524
5.9344 | 8.9672 | 7.9344 | 6.9344 | 9.9016 | 11.9016 | 8.9672 | 15.9016 | 25.8033 | 37.7049
6.8634 | 9.4317 | 8.8634 | 7.8634 | 11.295 | 13.295 | 9.4317 | 17.295 | 28.5901 | 41.8851
3.9905 | 7.9952 | 5.9905 | 4.9905 | 6.9857 | 8.9857 | 7.9952 | 12.9857 | 19.9714 | 28.9572
7.2021 | 9.601 | 9.2021 | 8.2021 | 11.8031 | 13.8031 | 9.601 | 17.8031 | 29.6063 | 43.4094
0.53517 | 6.2676 | 2.5352 | 1.5352 | 1.8028 | 3.8028 | 6.2676 | 7.8028 | 9.6055 | 13.4083
5.5684 | 8.7842 | 7.5684 | 6.5684 | 9.3525 | 11.3525 | 8.7842 | 15.3525 | 24.7051 | 36.0576
5.3874 | 8.6937 | 7.3874 | 6.3874 | 9.081 | 11.081 | 8.6937 | 15.081 | 24.1621 | 35.2431
6.5294 | 9.2647 | 8.5294 | 7.5294 | 10.7942 | 12.7942 | 9.2647 | 16.7942 | 27.5883 | 40.3825
8.7496 | 10.3748 | 10.7496 | 9.7496 | 14.1244 | 16.1244 | 10.3748 | 20.1244 | 34.2488 | 50.3732
5.9569 | 8.9785 | 7.9569 | 6.9569 | 9.9354 | 11.9354 | 8.9785 | 15.9354 | 25.8708 | 37.8062
5.1926 | 8.5963 | 7.1926 | 6.1926 | 8.7889 | 10.7889 | 8.5963 | 14.7889 | 23.5777 | 34.3666
4.5049 | 8.2524 | 6.5049 | 5.5049 | 7.7573 | 9.7573 | 8.2524 | 13.7573 | 21.5146 | 31.272
4.4453 | 8.2227 | 6.4453 | 5.4453 | 7.668 | 9.668 | 8.2227 | 13.668 | 21.336 | 31.004
8.9107 | 10.4553 | 10.9107 | 9.9107 | 14.366 | 16.366 | 10.4553 | 20.366 | 34.7321 | 51.0981
5.5784 | 8.7892 | 7.5784 | 6.5784 | 9.3676 | 11.3676 | 8.7892 | 15.3676 | 24.7351 | 36.1027
6.5968 | 9.2984 | 8.5968 | 7.5968 | 10.8952 | 12.8952 | 9.2984 | 16.8952 | 27.7903 | 40.6855
9.5841 | 10.7921 | 11.5841 | 10.5841 | 15.3762 | 17.3762 | 10.7921 | 21.3762 | 36.7524 | 54.1286
7.1421 | 9.5711 | 9.1421 | 8.1421 | 11.7132 | 13.7132 | 9.5711 | 17.7132 | 29.4264 | 43.1397
6.9164 | 9.4582 | 8.9164 | 7.9164 | 11.3746 | 13.3746 | 9.4582 | 17.3746 | 28.7492 | 42.1238 | 20% chance that the project will take 30 days or less
8.2153 | 10.1076 | 10.2153 | 9.2153 | 13.3229 | 15.3229 | 10.1076 | 19.3229 | 32.6459 | 47.9688
5.5263 | 8.7631 | 7.5263 | 6.5263 | 9.2894 | 11.2894 | 8.7631 | 15.2894 | 24.5789 | 35.8683
11.0337 | 11.5168 | 13.0337 | 12.0337 | 17.5505 | 19.5505 | 11.5168 | 23.5505 | 41.101 | 60.6514
6.0016 | 9.0008 | 8.0016 | 7.0016 | 10.0024 | 12.0024 | 9.0008 | 16.0024 | 26.0048 | 38.0072
10.3738 | 11.1869 | 12.3738 | 11.3738 | 16.5607 | 18.5607 | 11.1869 | 22.5607 | 39.1215 | 57.6822
6.4121 | 9.206 | 8.4121 | 7.4121 | 10.6181 | 12.6181 | 9.206 | 16.6181 | 27.2363 | 39.8544
9.217 | 10.6085 | 11.217 | 10.217 | 14.8254 | 16.8254 | 10.6085 | 20.8254 | 35.6509 | 52.4763
9.7797 | 10.8898 | 11.7797 | 10.7797 | 15.6695 | 17.6695 | 10.8898 | 21.6695 | 37.3391 | 55.0086
5.0423 | 8.5211 | 7.0423 | 6.0423 | 8.5634 | 10.5634 | 8.5211 | 14.5634 | 23.1268 | 33.6903
4.3481 | 8.174 | 6.3481 | 5.3481 | 7.5221 | 9.5221 | 8.174 | 13.5221 | 21.0442 | 30.5663
7.1758 | 9.5879 | 9.1758 | 8.1758 | 11.7637 | 13.7637 | 9.5879 | 17.7637 | 29.5274 | 43.2911
4.6681 | 8.3341 | 6.6681 | 5.6681 | 8.0022 | 10.0022 | 8.3341 | 14.0022 | 22.0043 | 32.0065
1.8921 | 6.946 | 3.8921 | 2.8921 | 3.8381 | 5.8381 | 6.946 | 9.8381 | 13.6762 | 19.5143
5.0109 | 8.5055 | 7.0109 | 6.0109 | 8.5164 | 10.5164 | 8.5055 | 14.5164 | 23.0328 | 33.5492
3.8584 | 7.9292 | 5.8584 | 4.8584 | 6.7875 | 8.7875 | 7.9292 | 12.7875 | 19.5751 | 28.3626
6.4966 | 9.2483 | 8.4966 | 7.4966 | 10.7448 | 12.7448 | 9.2483 | 16.7448 | 27.4897 | 40.2345
7.0352 | 9.5176 | 9.0352 | 8.0352 | 11.5527 | 13.5527 | 9.5176 | 17.5527 | 29.1055 | 42.6582
6.1885 | 9.0943 | 8.1885 | 7.1885 | 10.2828 | 12.2828 | 9.0943 | 16.2828 | 26.5656 | 38.8484
5.8998 | 8.9499 | 7.8998 | 6.8998 | 9.8497 | 11.8497 | 8.9499 | 15.8497 | 25.6995 | 37.5492
3.7522 | 7.8761 | 5.7522 | 4.7522 | 6.6283 | 8.6283 | 7.8761 | 12.6283 | 19.2566 | 27.8849
6.776 | 9.388 | 8.776 | 7.776 | 11.164 | 13.164 | 9.388 | 17.164 | 28.328 | 41.492
5.7807 | 8.8903 | 7.7807 | 6.7807 | 9.671 | 11.671 | 8.8903 | 15.671 | 25.3421 | 37.0131
3.3449 | 7.6725 | 5.3449 | 4.3449 | 6.0174 | 8.0174 | 7.6725 | 12.0174 | 18.0348 | 26.0522
3.0968 | 7.5484 | 5.0968 | 4.0968 | 5.6452 | 7.6452 | 7.5484 | 11.6452 | 17.2904 | 24.9355
7.9137 | 9.9569 | 9.9137 | 8.9137 | 12.8706 | 14.8706 | 9.9569 | 18.8706 | 31.7412 | 46.6118
8.1265 | 10.0633 | 10.1265 | 9.1265 | 13.1898 | 15.1898 | 10.0633 | 19.1898 | 32.3795 | 47.5693
4.2244 | 8.1122 | 6.2244 | 5.2244 | 7.3366 | 9.3366 | 8.1122 | 13.3366 | 20.6732 | 30.0098
6.3537 | 9.1768 | 8.3537 | 7.3537 | 10.5305 | 12.5305 | 9.1768 | 16.5305 | 27.061 | 39.5914
11.168 | 11.584 | 13.168 | 12.168 | 17.7521 | 19.7521 | 11.584 | 23.7521 | 41.5041 | 61.2562
5.4518 | 8.7259 | 7.4518 | 6.4518 | 9.1778 | 11.1778 | 8.7259 | 15.1778 | 24.3555 | 35.5333
6.0492 | 9.0246 | 8.0492 | 7.0492 | 10.0738 | 12.0738 | 9.0246 | 16.0738 | 26.1476 | 38.2214
7.4105 | 9.7052 | 9.4105 | 8.4105 | 12.1157 | 14.1157 | 9.7052 | 18.1157 | 30.2314 | 44.3471
3.5875 | 7.7938 | 5.5875 | 4.5875 | 6.3813 | 8.3813 | 7.7938 | 12.3813 | 18.7626 | 27.1439
5.9969 | 8.9984 | 7.9969 | 6.9969 | 9.9953 | 11.9953 | 8.9984 | 15.9953 | 25.9906 | 37.9859
4.4596 | 8.2298 | 6.4596 | 5.4596 | 7.6894 | 9.6894 | 8.2298 | 13.6894 | 21.3787 | 31.0681
4.6953 | 8.3477 | 6.6953 | 5.6953 | 8.043 | 10.043 | 8.3477 | 14.043 | 22.0859 | 32.1289
6.2341 | 9.117 | 8.2341 | 7.2341 | 10.3511 | 12.3511 | 9.117 | 16.3511 | 26.7023 | 39.0534
10.223 | 11.1115 | 12.223 | 11.223 | 16.3345 | 18.3345 | 11.1115 | 22.3345 | 38.669 | 57.0034
7.3917 | 9.6958 | 9.3917 | 8.3917 | 12.0875 | 14.0875 | 9.6958 | 18.0875 | 30.1751 | 44.2626
7.055 | 9.5275 | 9.055 | 8.055 | 11.5825 | 13.5825 | 9.5275 | 17.5825 | 29.1649 | 42.7474
2.1916 | 7.0958 | 4.1916 | 3.1916 | 4.2875 | 6.2875 | 7.0958 | 10.2875 | 14.5749 | 20.8624
4.1961 | 8.098 | 6.1961 | 5.1961 | 7.2941 | 9.2941 | 8.098 | 13.2941 | 20.5882 | 29.8823
9.3012 | 10.6506 | 11.3012 | 10.3012 | 14.9518 | 16.9518 | 10.6506 | 20.9518 | 35.9036 | 52.8554
6.1032 | 9.0516 | 8.1032 | 7.1032 | 10.1549 | 12.1549 | 9.0516 | 16.1549 | 26.3097 | 38.4646
10.9776 | 11.4888 | 12.9776 | 11.9776 | 17.4663 | 19.4663 | 11.4888 | 23.4663 | 40.9327 | 60.399
3.8066 | 7.9033 | 5.8066 | 4.8066 | 6.7099 | 8.7099 | 7.9033 | 12.7099 | 19.4198 | 28.1297
4.2458 | 8.1229 | 6.2458 | 5.2458 | 7.3688 | 9.3688 | 8.1229 | 13.3688 | 20.7375 | 30.1063
6.4005 | 9.2003 | 8.4005 | 7.4005 | 10.6008 | 12.6008 | 9.2003 | 16.6008 | 27.2016 | 39.8024
4.7583 | 8.3791 | 6.7583 | 5.7583 | 8.1374 | 10.1374 | 8.3791 | 14.1374 | 22.2748 | 32.4122
6.5861 | 9.293 | 8.5861 | 7.5861 | 10.8791 | 12.8791 | 9.293 | 16.8791 | 27.7582 | 40.6373
8.5851 | 10.2925 | 10.5851 | 9.5851 | 13.8776 | 15.8776 | 10.2925 | 19.8776 | 33.7552 | 49.6328
8.0992 | 10.0496 | 10.0992 | 9.0992 | 13.1489 | 15.1489 | 10.0496 | 19.1489 | 32.2977 | 47.4466
6.8226 | 9.4113 | 8.8226 | 7.8226 | 11.2338 | 13.2338 | 9.4113 | 17.2338 | 28.4677 | 41.7015
5.9018 | 8.9509 | 7.9018 | 6.9018 | 9.8527 | 11.8527 | 8.9509 | 15.8527 | 25.7054 | 37.5582
3.8038 | 7.9019 | 5.8038 | 4.8038 | 6.7057 | 8.7057 | 7.9019 | 12.7057 | 19.4114 | 28.1172
7.6562 | 9.8281 | 9.6562 | 8.6562 | 12.4843 | 14.4843 | 9.8281 | 18.4843 | 30.9687 | 45.453
5.9438 | 8.9719 | 7.9438 | 6.9438 | 9.9156 | 11.9156 | 8.9719 | 15.9156 | 25.8313 | 37.7469
4.5206 | 8.2603 | 6.5206 | 5.5206 | 7.7809 | 9.7809 | 8.2603 | 13.7809 | 21.5618 | 31.3428
6.1925 | 9.0963 | 8.1925 | 7.1925 | 10.2888 | 12.2888 | 9.0963 | 16.2888 | 26.5776 | 38.8664
6.2748 | 9.1374 | 8.2748 | 7.2748 | 10.4122 | 12.4122 | 9.1374 | 16.4122 | 26.8244 | 39.2366
6.3519 | 9.176 | 8.3519 | 7.3519 | 10.5279 | 12.5279 | 9.176 | 16.5279 | 27.0558 | 39.5837
4.0229 | 8.0115 | 6.0229 | 5.0229 | 7.0344 | 9.0344 | 8.0115 | 13.0344 | 20.0687 | 29.1031
5.9303 | 8.9651 | 7.9303 | 6.9303 | 9.8954 | 11.8954 | 8.9651 | 15.8954 | 25.7909 | 37.6863
6.936 | 9.468 | 8.936 | 7.936 | 11.404 | 13.404 | 9.468 | 17.404 | 28.808 | 42.2119
7.0226 | 9.5113 | 9.0226 | 8.0226 | 11.5339 | 13.5339 | 9.5113 | 17.5339 | 29.0677 | 42.6016
2.7903 | 7.3951 | 4.7903 | 3.7903 | 5.1854 | 7.1854 | 7.3951 | 11.1854 | 16.3708 | 23.5562
6.8957 | 9.4479 | 8.8957 | 7.8957 | 11.3436 | 13.3436 | 9.4479 | 17.3436 | 28.6871 | 42.0307
6.0138 | 9.0069 | 8.0138 | 7.0138 | 10.0208 | 12.0208 | 9.0069 | 16.0208 | 26.0415 | 38.0623
3.8657 | 7.9328 | 5.8657 | 4.8657 | 6.7985 | 8.7985 | 7.9328 | 12.7985 | 19.597 | 28.3955
7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998
8.8202 | 10.4101 | 10.8202 | 9.8202 | 14.2303 | 16.2303 | 10.4101 | 20.2303 | 34.4605 | 50.6908
7.8196 | 9.9098 | 9.8196 | 8.8196 | 12.7294 | 14.7294 | 9.9098 | 18.7294 | 31.4588 | 46.1882
4.576 | 8.288 | 6.576 | 5.576 | 7.864 | 9.864 | 8.288 | 13.864 | 21.7279 | 31.5919
7.0266 | 9.5133 | 9.0266 | 8.0266 | 11.5399 | 13.5399 | 9.5133 | 17.5399 | 29.0798 | 42.6196
6.0145 | 9.0072 | 8.0145 | 7.0145 | 10.0217 | 12.0217 | 9.0072 | 16.0217 | 26.0434 | 38.0651
2.6438 | 7.3219 | 4.6438 | 3.6438 | 4.9657 | 6.9657 | 7.3219 | 10.9657 | 15.9313 | 22.897
6.0348 | 9.0174 | 8.0348 | 7.0348 | 10.0522 | 12.0522 | 9.0174 | 16.0522 | 26.1044 | 38.1566
5.4907 | 8.7453 | 7.4907 | 6.4907 | 9.236 | 11.236 | 8.7453 | 15.236 | 24.472 | 35.7079
7.3925 | 9.6962 | 9.3925 | 8.3925 | 12.0887 | 14.0887 | 9.6962 | 18.0887 | 30.1774 | 44.2661
6.0746 | 9.0373 | 8.0746 | 7.0746 | 10.1119 | 12.1119 | 9.0373 | 16.1119 | 26.2238 | 38.3357
5.7247 | 8.8624 | 7.7247 | 6.7247 | 9.5871 | 11.5871 | 8.8624 | 15.5871 | 25.1742 | 36.7613
5.7801 | 8.89 | 7.7801 | 6.7801 | 9.6701 | 11.6701 | 8.89 | 15.6701 | 25.3403 | 37.0104
4.7764 | 8.3882 | 6.7764 | 5.7764 | 8.1646 | 10.1646 | 8.3882 | 14.1646 | 22.3292 | 32.4937
2.1447 | 7.0723 | 4.1447 | 3.1447 | 4.217 | 6.217 | 7.0723 | 10.217 | 14.434 | 20.6509
5.7028 | 8.8514 | 7.7028 | 6.7028 | 9.5542 | 11.5542 | 8.8514 | 15.5542 | 25.1084 | 36.6625
7.7214 | 9.8607 | 9.7214 | 8.7214 | 12.582 | 14.582 | 9.8607 | 18.582 | 31.1641 | 45.7461
5.5976 | 8.7988 | 7.5976 | 6.5976 | 9.3964 | 11.3964 | 8.7988 | 15.3964 | 24.7928 | 36.1892
5.3389 | 8.6695 | 7.3389 | 6.3389 | 9.0084 | 11.0084 | 8.6695 | 15.0084 | 24.0167 | 35.0251
8.3081 | 10.154 | 10.3081 | 9.3081 | 13.4621 | 15.4621 | 10.154 | 19.4621 | 32.9243 | 48.3864
6.3383 | 9.1691 | 8.3383 | 7.3383 | 10.5074 | 12.5074 | 9.1691 | 16.5074 | 27.0148 | 39.5222
6.2356 | 9.1178 | 8.2356 | 7.2356 | 10.3534 | 12.3534 | 9.1178 | 16.3534 | 26.7069 | 39.0603
8.8103 | 10.4051 | 10.8103 | 9.8103 | 14.2154 | 16.2154 | 10.4051 | 20.2154 | 34.4309 | 50.6463
9.1328 | 10.5664 | 11.1328 | 10.1328 | 14.6992 | 16.6992 | 10.5664 | 20.6992 | 35.3985 | 52.0977
7.1789 | 9.5895 | 9.1789 | 8.1789 | 11.7684 | 13.7684 | 9.5895 | 17.7684 | 29.5367 | 43.3051
6.2187 | 9.1093 | 8.2187 | 7.2187 | 10.328 | 12.328 | 9.1093 | 16.328 | 26.6561 | 38.9841
10.8017 | 11.4008 | 12.8017 | 11.8017 | 17.2025 | 19.2025 | 11.4008 | 23.2025 | 40.405 | 59.6075
4.3082 | 8.1541 | 6.3082 | 5.3082 | 7.4622 | 9.4622 | 8.1541 | 13.4622 | 20.9245 | 30.3867
6.2847 | 9.1423 | 8.2847 | 7.2847 | 10.427 | 12.427 | 9.1423 | 16.427 | 26.8541 | 39.2811
3.8754 | 7.9377 | 5.8754 | 4.8754 | 6.8131 | 8.8131 | 7.9377 | 12.8131 | 19.6261 | 28.4392
3.5216 | 7.7608 | 5.5216 | 4.5216 | 6.2824 | 8.2824 | 7.7608 | 12.2824 | 18.5649 | 26.8473
5.5633 | 8.7817 | 7.5633 | 6.5633 | 9.345 | 11.345 | 8.7817 | 15.345 | 24.69 | 36.0351
4.8463 | 8.4232 | 6.8463 | 5.8463 | 8.2695 | 10.2695 | 8.4232 | 14.2695 | 22.5389 | 32.8084
6.9828 | 9.4914 | 8.9828 | 7.9828 | 11.4743 | 13.4743 | 9.4914 | 17.4743 | 28.9485 | 42.4228
7.8476 | 9.9238 | 9.8476 | 8.8476 | 12.7713 | 14.7713 | 9.9238 | 18.7713 | 31.5427 | 46.314
7.0345 | 9.5172 | 9.0345 | 8.0345 | 11.5517 | 13.5517 | 9.5172 | 17.5517 | 29.1034 | 42.655
7.2596 | 9.6298 | 9.2596 | 8.2596 | 11.8894 | 13.8894 | 9.6298 | 17.8894 | 29.7788 | 43.6682
6.762 | 9.381 | 8.762 | 7.762 | 11.143 | 13.143 | 9.381 | 17.143 | 28.286 | 41.4289
4.7843 | 8.3922 | 6.7843 | 5.7843 | 8.1765 | 10.1765 | 8.3922 | 14.1765 | 22.3529 | 32.5294
5.9404 | 8.9702 | 7.9404 | 6.9404 | 9.9106 | 11.9106 | 8.9702 | 15.9106 | 25.8212 | 37.7318
6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915
7.0135 | 9.5068 | 9.0135 | 8.0135 | 11.5203 | 13.5203 | 9.5068 | 17.5203 | 29.0406 | 42.5608
3.4265 | 7.7133 | 5.4265 | 4.4265 | 6.1398 | 8.1398 | 7.7133 | 12.1398 | 18.2796 | 26.4194
5.4813 | 8.7407 | 7.4813 | 6.4813 | 9.222 | 11.222 | 8.7407 | 15.222 | 24.444 | 35.6659
7.7681 | 9.8841 | 9.7681 | 8.7681 | 12.6522 | 14.6522 | 9.8841 | 18.6522 | 31.3044 | 45.9566
6.4122 | 9.2061 | 8.4122 | 7.4122 | 10.6184 | 12.6184 | 9.2061 | 16.6184 | 27.2367 | 39.8551
8.7219 | 10.361 | 10.7219 | 9.7219 | 14.0829 | 16.0829 | 10.361 | 20.0829 | 34.1657 | 50.2486
5.8098 | 8.9049 | 7.8098 | 6.8098 | 9.7147 | 11.7147 | 8.9049 | 15.7147 | 25.4293 | 37.144
4.8329 | 8.4165 | 6.8329 | 5.8329 | 8.2494 | 10.2494 | 8.4165 | 14.2494 | 22.4987 | 32.7481
6.7605 | 9.3803 | 8.7605 | 7.7605 | 11.1408 | 13.1408 | 9.3803 | 17.1408 | 28.2815 | 41.4223
9.047 | 10.5235 | 11.047 | 10.047 | 14.5706 | 16.5706 | 10.5235 | 20.5706 | 35.1411 | 51.7117
7.8454 | 9.9227 | 9.8454 | 8.8454 | 12.7682 | 14.7682 | 9.9227 | 18.7682 | 31.5363 | 46.3045
6.6496 | 9.3248 | 8.6496 | 7.6496 | 10.9744 | 12.9744 | 9.3248 | 16.9744 | 27.9489 | 40.9233
4.2135 | 8.1067 | 6.2135 | 5.2135 | 7.3202 | 9.3202 | 8.1067 | 13.3202 | 20.6404 | 29.9606
11.6293 | 11.8146 | 13.6293 | 12.6293 | 18.4439 | 20.4439 | 11.8146 | 24.4439 | 42.8878 | 63.3317
5.3138 | 8.6569 | 7.3138 | 6.3138 | 8.9707 | 10.9707 | 8.6569 | 14.9707 | 23.9414 | 34.9122
6.2814 | 9.1407 | 8.2814 | 7.2814 | 10.4222 | 12.4222 | 9.1407 | 16.4222 | 26.8443 | 39.2665
5.935 | 8.9675 | 7.935 | 6.935 | 9.9026 | 11.9026 | 8.9675 | 15.9026 | 25.8051 | 37.7077
6.1508 | 9.0754 | 8.1508 | 7.1508 | 10.2262 | 12.2262 | 9.0754 | 16.2262 | 26.4523 | 38.6785
5.3276 | 8.6638 | 7.3276 | 6.3276 | 8.9914 | 10.9914 | 8.6638 | 14.9914 | 23.9828 | 34.9742
2.0185 | 7.0093 | 4.0185 | 3.0185 | 4.0278 | 6.0278 | 7.0093 | 10.0278 | 14.0556 | 20.0834
7.9373 | 9.9687 | 9.9373 | 8.9373 | 12.906 | 14.906 | 9.9687 | 18.906 | 31.812 | 46.718
7.1858 | 9.5929 | 9.1858 | 8.1858 | 11.7787 | 13.7787 | 9.5929 | 17.7787 | 29.5575 | 43.3362
6.7905 | 9.3953 | 8.7905 | 7.7905 | 11.1858 | 13.1858 | 9.3953 | 17.1858 | 28.3716 | 41.5574
8.3321 | 10.166 | 10.3321 | 9.3321 | 13.4981 | 15.4981 | 10.166 | 19.4981 | 32.9962 | 48.4944
4.4306 | 8.2153 | 6.4306 | 5.4306 | 7.6459 | 9.6459 | 8.2153 | 13.6459 | 21.2918 | 30.9377
5.963 | 8.9815 | 7.963 | 6.963 | 9.9446 | 11.9446 | 8.9815 | 15.9446 | 25.8891 | 37.8337
5.0349 | 8.5174 | 7.0349 | 6.0349 | 8.5523 | 10.5523 | 8.5174 | 14.5523 | 23.1047 | 33.657
7.8813 | 9.9407 | 9.8813 | 8.8813 | 12.822 | 14.822 | 9.9407 | 18.822 | 31.644 | 46.466
2.9422 | 7.4711 | 4.9422 | 3.9422 | 5.4133 | 7.4133 | 7.4711 | 11.4133 | 16.8265 | 24.2398
5.5831 | 8.7915 | 7.5831 | 6.5831 | 9.3746 | 11.3746 | 8.7915 | 15.3746 | 24.7492 | 36.1238
6.1071 | 9.0535 | 8.1071 | 7.1071 | 10.1606 | 12.1606 | 9.0535 | 16.1606 | 26.3212 | 38.4818
3.7728 | 7.8864 | 5.7728 | 4.7728 | 6.6592 | 8.6592 | 7.8864 | 12.6592 | 19.3184 | 27.9776
7.4075 | 9.7038 | 9.4075 | 8.4075 | 12.1113 | 14.1113 | 9.7038 | 18.1113 | 30.2226 | 44.3338
4.9966 | 8.4983 | 6.9966 | 5.9966 | 8.4948 | 10.4948 | 8.4983 | 14.4948 | 22.9897 | 33.4845
5.7338 | 8.8669 | 7.7338 | 6.7338 | 9.6008 | 11.6008 | 8.8669 | 15.6008 | 25.2015 | 36.8023
9.5995 | 10.7997 | 11.5995 | 10.5995 | 15.3992 | 17.3992 | 10.7997 | 21.3992 | 36.7984 | 54.1977
4.5772 | 8.2886 | 6.5772 | 5.5772 | 7.8657 | 9.8657 | 8.2886 | 13.8657 | 21.7315 | 31.5972
6.272 | 9.136 | 8.272 | 7.272 | 10.408 | 12.408 | 9.136 | 16.408 | 26.8161 | 39.2241
8.0427 | 10.0214 | 10.0427 | 9.0427 | 13.0641 | 15.0641 | 10.0214 | 19.0641 | 32.1282 | 47.1924
7.5719 | 9.7859 | 9.5719 | 8.5719 | 12.3578 | 14.3578 | 9.7859 | 18.3578 | 30.7157 | 45.0735
5.6432 | 8.8216 | 7.6432 | 6.6432 | 9.4649 | 11.4649 | 8.8216 | 15.4649 | 24.9297 | 36.3946
8.7355 | 10.3677 | 10.7355 | 9.7355 | 14.1032 | 16.1032 | 10.3677 | 20.1032 | 34.2065 | 50.3097
5.0301 | 8.515 | 7.0301 | 6.0301 | 8.5451 | 10.5451 | 8.515 | 14.5451 | 23.0902 | 33.6354
7.0523 | 9.5262 | 9.0523 | 8.0523 | 11.5785 | 13.5785 | 9.5262 | 17.5785 | 29.157 | 42.7355
7.9439 | 9.972 | 9.9439 | 8.9439 | 12.9159 | 14.9159 | 9.972 | 18.9159 | 31.8318 | 46.7478
8.5616 | 10.2808 | 10.5616 | 9.5616 | 13.8424 | 15.8424 | 10.2808 | 19.8424 | 33.6848 | 49.5272
7.3831 | 9.6916 | 9.3831 | 8.3831 | 12.0747 | 14.0747 | 9.6916 | 18.0747 | 30.1494 | 44.2241
4.1357 | 8.0679 | 6.1357 | 5.1357 | 7.2036 | 9.2036 | 8.0679 | 13.2036 | 20.4072 | 29.6108
2.1727 | 7.0864 | 4.1727 | 3.1727 | 4.2591 | 6.2591 | 7.0864 | 10.2591 | 14.5182 | 20.7772
5.5513 | 8.7756 | 7.5513 | 6.5513 | 9.3269 | 11.3269 | 8.7756 | 15.3269 | 24.6538 | 35.9807
3.49 | 7.745 | 5.49 | 4.49 | 6.235 | 8.235 | 7.745 | 12.235 | 18.47 | 26.705
0.33785 | 6.1689 | 2.3378 | 1.3378 | 1.5068 | 3.5068 | 6.1689 | 7.5068 | 9.0135 | 12.5203
5.2149 | 8.6075 | 7.2149 | 6.2149 | 8.8224 | 10.8224 | 8.6075 | 14.8224 | 23.6448 | 34.4672
7.5632 | 9.7816 | 9.5632 | 8.5632 | 12.3447 | 14.3447 | 9.7816 | 18.3447 | 30.6895 | 45.0342
7.7902 | 9.8951 | 9.7902 | 8.7902 | 12.6853 | 14.6853 | 9.8951 | 18.6853 | 31.3705 | 46.0558
9.4106 | 10.7053 | 11.4106 | 10.4106 | 15.1159 | 17.1159 | 10.7053 | 21.1159 | 36.2318 | 53.3477
6.338 | 9.169 | 8.338 | 7.338 | 10.5069 | 12.5069 | 9.169 | 16.5069 | 27.0139 | 39.5208
8.4698 | 10.2349 | 10.4698 | 9.4698 | 13.7047 | 15.7047 | 10.2349 | 19.7047 | 33.4094 | 49.1142
3.966 | 7.983 | 5.966 | 4.966 | 6.949 | 8.949 | 7.983 | 12.949 | 19.898 | 28.847
2.0788 | 7.0394 | 4.0788 | 3.0788 | 4.1183 | 6.1183 | 7.0394 | 10.1183 | 14.2365 | 20.3548
7.9038 | 9.9519 | 9.9038 | 8.9038 | 12.8558 | 14.8558 | 9.9519 | 18.8558 | 31.7115 | 46.5673
5.9358 | 8.9679 | 7.9358 | 6.9358 | 9.9037 | 11.9037 | 8.9679 | 15.9037 | 25.8074 | 37.7111
8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144
6.657 | 9.3285 | 8.657 | 7.657 | 10.9856 | 12.9856 | 9.3285 | 16.9856 | 27.9711 | 40.9567
6.5966 | 9.2983 | 8.5966 | 7.5966 | 10.8949 | 12.8949 | 9.2983 | 16.8949 | 27.7899 | 40.6848
5.4851 | 8.7426 | 7.4851 | 6.4851 | 9.2277 | 11.2277 | 8.7426 | 15.2277 | 24.4554 | 35.683
3.0805 | 7.5402 | 5.0805 | 4.0805 | 5.6207 | 7.6207 | 7.5402 | 11.6207 | 17.2414 | 24.8621
7.2083 | 9.6042 | 9.2083 | 8.2083 | 11.8125 | 13.8125 | 9.6042 | 17.8125 | 29.625 | 43.4375
2.7006 | 7.3503 | 4.7006 | 3.7006 | 5.0509 | 7.0509 | 7.3503 | 11.0509 | 16.1017 | 23.1526
7.4982 | 9.7491 | 9.4982 | 8.4982 | 12.2472 | 14.2472 | 9.7491 | 18.2472 | 30.4945 | 44.7417
5.3544 | 8.6772 | 7.3544 | 6.3544 | 9.0316 | 11.0316 | 8.6772 | 15.0316 | 24.0632 | 35.0948
4.5186 | 8.2593 | 6.5186 | 5.5186 | 7.7779 | 9.7779 | 8.2593 | 13.7779 | 21.5558 | 31.3337
4.8309 | 8.4155 | 6.8309 | 5.8309 | 8.2464 | 10.2464 | 8.4155 | 14.2464 | 22.4927 | 32.7391
1.1151 | 6.5575 | 3.1151 | 2.1151 | 2.6726 | 4.6726 | 6.5575 | 8.6726 | 11.3452 | 16.0178
5.9719 | 8.986 | 7.9719 | 6.9719 | 9.9579 | 11.9579 | 8.986 | 15.9579 | 25.9158 | 37.8737
6.5507 | 9.2754 | 8.5507 | 7.5507 | 10.8261 | 12.8261 | 9.2754 | 16.8261 | 27.6521 | 40.4782
4.8226 | 8.4113 | 6.8226 | 5.8226 | 8.2338 | 10.2338 | 8.4113 | 14.2338 | 22.4677 | 32.7015
6.1037 | 9.0519 | 8.1037 | 7.1037 | 10.1556 | 12.1556 | 9.0519 | 16.1556 | 26.3111 | 38.4667
6.9292 | 9.4646 | 8.9292 | 7.9292 | 11.3937 | 13.3937 | 9.4646 | 17.3937 | 28.7875 | 42.1812
3.7038 | 7.8519 | 5.7038 | 4.7038 | 6.5557 | 8.5557 | 7.8519 | 12.5557 | 19.1113 | 27.667
7.5671 | 9.7836 | 9.5671 | 8.5671 | 12.3507 | 14.3507 | 9.7836 | 18.3507 | 30.7013 | 45.052
2.3254 | 7.1627 | 4.3254 | 3.3254 | 4.4881 | 6.4881 | 7.1627 | 10.4881 | 14.9762 | 21.4642
5.8236 | 8.9118 | 7.8236 | 6.8236 | 9.7354 | 11.7354 | 8.9118 | 15.7354 | 25.4708 | 37.2062
6.3687 | 9.1844 | 8.3687 | 7.3687 | 10.5531 | 12.5531 | 9.1844 | 16.5531 | 27.1062 | 39.6593
7.032 | 9.516 | 9.032 | 8.032 | 11.548 | 13.548 | 9.516 | 17.548 | 29.096 | 42.644
5.9999 | 9 | 7.9999 | 6.9999 | 9.9999 | 11.9999 | 9 | 15.9999 | 25.9998 | 37.9997
6.0206 | 9.0103 | 8.0206 | 7.0206 | 10.0309 | 12.0309 | 9.0103 | 16.0309 | 26.0617 | 38.0926
9.147 | 10.5735 | 11.147 | 10.147 | 14.7205 | 16.7205 | 10.5735 | 20.7205 | 35.441 | 52.1614
7.1056 | 9.5528 | 9.1056 | 8.1056 | 11.6584 | 13.6584 | 9.5528 | 17.6584 | 29.3168 | 42.9752
[6 empty] | 0 |  | Average

## test activity A
A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | diff
1.4288 | 6.7144 | 3.4288 | 2.4288 | 3.1433 | 5.1433 | 6.7144 | 9.1433 | 12.2865 | 17.4298 | 1.4388 | 6.7144 | 3.4288 | 2.4288 | 3.1433 | 5.1433 | 6.7144 | 9.1433 | 12.2865 | 17.4298 | 0
2.4295 | 7.2148 | 4.4295 | 3.4295 | 4.6443 | 6.6443 | 7.2148 | 10.6443 | 15.2885 | 21.9328 | 2.4395 | 7.2148 | 4.4295 | 3.4295 | 4.6443 | 6.6443 | 7.2148 | 10.6443 | 15.2885 | 21.9328 | 0
4.0538 | 8.0269 | 6.0538 | 5.0538 | 7.0808 | 9.0808 | 8.0269 | 13.0808 | 20.1615 | 29.2423 | 4.0638 | 8.0269 | 6.0538 | 5.0538 | 7.0808 | 9.0808 | 8.0269 | 13.0808 | 20.1615 | 29.2423 | 0
6.049 | 9.0245 | 8.049 | 7.049 | 10.0736 | 12.0736 | 9.0245 | 16.0736 | 26.1471 | 38.2207 | 6.059 | 9.0245 | 8.049 | 7.049 | 10.0736 | 12.0736 | 9.0245 | 16.0736 | 26.1471 | 38.2207 | 0
7.3353 | 9.6677 | 9.3353 | 8.3353 | 12.003 | 14.003 | 9.6677 | 18.003 | 30.006 | 44.009 | 7.3453 | 9.6677 | 9.3353 | 8.3353 | 12.003 | 14.003 | 9.6677 | 18.003 | 30.006 | 44.009 | 0
5.1939 | 8.5969 | 7.1939 | 6.1939 | 8.7908 | 10.7908 | 8.5969 | 14.7908 | 23.5817 | 34.3725 | 5.2039 | 8.5969 | 7.1939 | 6.1939 | 8.7908 | 10.7908 | 8.5969 | 14.7908 | 23.5817 | 34.3725 | 0
7.3727 | 9.6863 | 9.3727 | 8.3727 | 12.059 | 14.059 | 9.6863 | 18.059 | 30.118 | 44.1769 | 7.3827 | 9.6863 | 9.3727 | 8.3727 | 12.059 | 14.059 | 9.6863 | 18.059 | 30.118 | 44.1769 | 0
2.7474 | 7.3737 | 4.7474 | 3.7474 | 5.1211 | 7.1211 | 7.3737 | 11.1211 | 16.2422 | 23.3633 | 2.7574 | 7.3737 | 4.7474 | 3.7474 | 5.1211 | 7.1211 | 7.3737 | 11.1211 | 16.2422 | 23.3633 | 0
7.0969 | 9.5484 | 9.0969 | 8.0969 | 11.6453 | 13.6453 | 9.5484 | 17.6453 | 29.2906 | 42.9359 | 7.1069 | 9.5484 | 9.0969 | 8.0969 | 11.6453 | 13.6453 | 9.5484 | 17.6453 | 29.2906 | 42.9359 | 0
4.1058 | 8.0529 | 6.1058 | 5.1058 | 7.1586 | 9.1586 | 8.0529 | 13.1586 | 20.3173 | 29.4759 | 4.1158 | 8.0529 | 6.1058 | 5.1058 | 7.1586 | 9.1586 | 8.0529 | 13.1586 | 20.3173 | 29.4759 | 0
7.2091 | 9.6045 | 9.2091 | 8.2091 | 11.8136 | 13.8136 | 9.6045 | 17.8136 | 29.6272 | 43.4408 | 7.2191 | 9.6045 | 9.2091 | 8.2091 | 11.8136 | 13.8136 | 9.6045 | 17.8136 | 29.6272 | 43.4408 | 0
10.8182 | 11.4091 | 12.8182 | 11.8182 | 17.2273 | 19.2273 | 11.4091 | 23.2273 | 40.4546 | 59.682 | 10.8282 | 11.4091 | 12.8182 | 11.8182 | 17.2273 | 19.2273 | 11.4091 | 23.2273 | 40.4546 | 59.682 | 0
6.4931 | 9.2465 | 8.4931 | 7.4931 | 10.7396 | 12.7396 | 9.2465 | 16.7396 | 27.4793 | 40.2189 | 6.5031 | 9.2465 | 8.4931 | 7.4931 | 10.7396 | 12.7396 | 9.2465 | 16.7396 | 27.4793 | 40.2189 | 0
6.0198 | 9.0099 | 8.0198 | 7.0198 | 10.0297 | 12.0297 | 9.0099 | 16.0297 | 26.0594 | 38.0892 | 6.0298 | 9.0099 | 8.0198 | 7.0198 | 10.0297 | 12.0297 | 9.0099 | 16.0297 | 26.0594 | 38.0892 | 0
5.2393 | 8.6197 | 7.2393 | 6.2393 | 8.859 | 10.859 | 8.6197 | 14.859 | 23.718 | 34.577 | 5.2493 | 8.6197 | 7.2393 | 6.2393 | 8.859 | 10.859 | 8.6197 | 14.859 | 23.718 | 34.577 | 0
5.4805 | 8.7403 | 7.4805 | 6.4805 | 9.2208 | 11.2208 | 8.7403 | 15.2208 | 24.4416 | 35.6624 | 5.4905 | 8.7403 | 7.4805 | 6.4805 | 9.2208 | 11.2208 | 8.7403 | 15.2208 | 24.4416 | 35.6624 | 0
3.5992 | 7.7996 | 5.5992 | 4.5992 | 6.3988 | 8.3988 | 7.7996 | 12.3988 | 18.7976 | 27.1965 | 3.6092 | 7.7996 | 5.5992 | 4.5992 | 6.3988 | 8.3988 | 7.7996 | 12.3988 | 18.7976 | 27.1965 | 0
2.2806 | 7.1403 | 4.2806 | 3.2806 | 4.4209 | 6.4209 | 7.1403 | 10.4209 | 14.8419 | 21.2628 | 2.2906 | 7.1403 | 4.2806 | 3.2806 | 4.4209 | 6.4209 | 7.1403 | 10.4209 | 14.8419 | 21.2628 | 0
6.9264 | 9.4632 | 8.9264 | 7.9264 | 11.3897 | 13.3897 | 9.4632 | 17.3897 | 28.7793 | 42.169 | 6.9364 | 9.4632 | 8.9264 | 7.9264 | 11.3897 | 13.3897 | 9.4632 | 17.3897 | 28.7793 | 42.169 | 0
4.5848 | 8.2924 | 6.5848 | 5.5848 | 7.8772 | 9.8772 | 8.2924 | 13.8772 | 21.7545 | 31.6317 | 4.5948 | 8.2924 | 6.5848 | 5.5848 | 7.8772 | 9.8772 | 8.2924 | 13.8772 | 21.7545 | 31.6317 | 0
5.8871 | 8.9436 | 7.8871 | 6.8871 | 9.8307 | 11.8307 | 8.9436 | 15.8307 | 25.6613 | 37.492 | 5.8971 | 8.9436 | 7.8871 | 6.8871 | 9.8307 | 11.8307 | 8.9436 | 15.8307 | 25.6613 | 37.492 | 0
4.4375 | 8.2187 | 6.4375 | 5.4375 | 7.6562 | 9.6562 | 8.2187 | 13.6562 | 21.3124 | 30.9686 | 4.4475 | 8.2187 | 6.4375 | 5.4375 | 7.6562 | 9.6562 | 8.2187 | 13.6562 | 21.3124 | 30.9686 | 0
5.9122 | 8.9561 | 7.9122 | 6.9122 | 9.8683 | 11.8683 | 8.9561 | 15.8683 | 25.7367 | 37.605 | 5.9222 | 8.9561 | 7.9122 | 6.9122 | 9.8683 | 11.8683 | 8.9561 | 15.8683 | 25.7367 | 37.605 | 0
4.2985 | 8.1493 | 6.2985 | 5.2985 | 7.4478 | 9.4478 | 8.1493 | 13.4478 | 20.8955 | 30.3433 | 4.3085 | 8.1493 | 6.2985 | 5.2985 | 7.4478 | 9.4478 | 8.1493 | 13.4478 | 20.8955 | 30.3433 | 0
3.7284 | 7.8642 | 5.7284 | 4.7284 | 6.5927 | 8.5927 | 7.8642 | 12.5927 | 19.1853 | 27.778 | 3.7384 | 7.8642 | 5.7284 | 4.7284 | 6.5927 | 8.5927 | 7.8642 | 12.5927 | 19.1853 | 27.778 | 0
7.6067 | 9.8034 | 9.6067 | 8.6067 | 12.4101 | 14.4101 | 9.8034 | 18.4101 | 30.8202 | 45.2303 | 7.6167 | 9.8034 | 9.6067 | 8.6067 | 12.4101 | 14.4101 | 9.8034 | 18.4101 | 30.8202 | 45.2303 | 0
8.6808 | 10.3404 | 10.6808 | 9.6808 | 14.0212 | 16.0212 | 10.3404 | 20.0212 | 34.0423 | 50.0635 | 8.6908 | 10.3404 | 10.6808 | 9.6808 | 14.0212 | 16.0212 | 10.3404 | 20.0212 | 34.0423 | 50.0635 | 0
5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 5.2296 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 0
7.6331 | 9.8165 | 9.6331 | 8.6331 | 12.4496 | 14.4496 | 9.8165 | 18.4496 | 30.8992 | 45.3488 | 7.6431 | 9.8165 | 9.6331 | 8.6331 | 12.4496 | 14.4496 | 9.8165 | 18.4496 | 30.8992 | 45.3488 | 0
4.2833 | 8.1416 | 6.2833 | 5.2833 | 7.4249 | 9.4249 | 8.1416 | 13.4249 | 20.8499 | 30.2748 | 4.2933 | 8.1416 | 6.2833 | 5.2833 | 7.4249 | 9.4249 | 8.1416 | 13.4249 | 20.8499 | 30.2748 | 0
4.5407 | 8.2703 | 6.5407 | 5.5407 | 7.811 | 9.811 | 8.2703 | 13.811 | 21.622 | 31.433 | 4.5507 | 8.2703 | 6.5407 | 5.5407 | 7.811 | 9.811 | 8.2703 | 13.811 | 21.622 | 31.433 | 0
6.1115 | 9.0558 | 8.1115 | 7.1115 | 10.1673 | 12.1673 | 9.0558 | 16.1673 | 26.3345 | 38.5018 | 6.1215 | 9.0558 | 8.1115 | 7.1115 | 10.1673 | 12.1673 | 9.0558 | 16.1673 | 26.3345 | 38.5018 | 0
6.1999 | 9.1 | 8.1999 | 7.1999 | 10.2999 | 12.2999 | 9.1 | 16.2999 | 26.5997 | 38.8996 | 6.2099 | 9.1 | 8.1999 | 7.1999 | 10.2999 | 12.2999 | 9.1 | 16.2999 | 26.5997 | 38.8996 | 0
2.8161 | 7.408 | 4.8161 | 3.8161 | 5.2241 | 7.2241 | 7.408 | 11.2241 | 16.4482 | 23.6723 | 2.8261 | 7.408 | 4.8161 | 3.8161 | 5.2241 | 7.2241 | 7.408 | 11.2241 | 16.4482 | 23.6723 | 0
6.6314 | 9.3157 | 8.6314 | 7.6314 | 10.9471 | 12.9471 | 9.3157 | 16.9471 | 27.8943 | 40.8414 | 6.6414 | 9.3157 | 8.6314 | 7.6314 | 10.9471 | 12.9471 | 9.3157 | 16.9471 | 27.8943 | 40.8414 | 0
6.5394 | 9.2697 | 8.5394 | 7.5394 | 10.8092 | 12.8092 | 9.2697 | 16.8092 | 27.6183 | 40.4275 | 6.5494 | 9.2697 | 8.5394 | 7.5394 | 10.8092 | 12.8092 | 9.2697 | 16.8092 | 27.6183 | 40.4275 | 0
11.0521 | 11.526 | 13.0521 | 12.0521 | 17.5781 | 19.5781 | 11.526 | 23.5781 | 41.1562 | 60.7343 | 11.0621 | 11.526 | 13.0521 | 12.0521 | 17.5781 | 19.5781 | 11.526 | 23.5781 | 41.1562 | 60.7343 | 0
3.8102 | 7.9051 | 5.8102 | 4.8102 | 6.7153 | 8.7153 | 7.9051 | 12.7153 | 19.4307 | 28.146 | 3.8202 | 7.9051 | 5.8102 | 4.8102 | 6.7153 | 8.7153 | 7.9051 | 12.7153 | 19.4307 | 28.146 | 0
5.2518 | 8.6259 | 7.2518 | 6.2518 | 8.8777 | 10.8777 | 8.6259 | 14.8777 | 23.7554 | 34.6332 | 5.2618 | 8.6259 | 7.2518 | 6.2518 | 8.8777 | 10.8777 | 8.6259 | 14.8777 | 23.7554 | 34.6332 | 0
6.3771 | 9.1886 | 8.3771 | 7.3771 | 10.5657 | 12.5657 | 9.1886 | 16.5657 | 27.1314 | 39.6971 | 6.3871 | 9.1886 | 8.3771 | 7.3771 | 10.5657 | 12.5657 | 9.1886 | 16.5657 | 27.1314 | 39.6971 | 0
5.3383 | 8.6691 | 7.3383 | 6.3383 | 9.0074 | 11.0074 | 8.6691 | 15.0074 | 24.0148 | 35.0222 | 5.3483 | 8.6691 | 7.3383 | 6.3383 | 9.0074 | 11.0074 | 8.6691 | 15.0074 | 24.0148 | 35.0222 | 0
8.3948 | 10.1974 | 10.3948 | 9.3948 | 13.5922 | 15.5922 | 10.1974 | 19.5922 | 33.1845 | 48.7767 | 8.4048 | 10.1974 | 10.3948 | 9.3948 | 13.5922 | 15.5922 | 10.1974 | 19.5922 | 33.1845 | 48.7767 | 0
5.0712 | 8.5356 | 7.0712 | 6.0712 | 8.6068 | 10.6068 | 8.5356 | 14.6068 | 23.2135 | 33.8203 | 5.0812 | 8.5356 | 7.0712 | 6.0712 | 8.6068 | 10.6068 | 8.5356 | 14.6068 | 23.2135 | 33.8203 | 0
6.1543 | 9.0771 | 8.1543 | 7.1543 | 10.2314 | 12.2314 | 9.0771 | 16.2314 | 26.4629 | 38.6943 | 6.1643 | 9.0771 | 8.1543 | 7.1543 | 10.2314 | 12.2314 | 9.0771 | 16.2314 | 26.4629 | 38.6943 | 0
5.863 | 8.9315 | 7.863 | 6.863 | 9.7946 | 11.7946 | 8.9315 | 15.7946 | 25.5891 | 37.3837 | 5.873 | 8.9315 | 7.863 | 6.863 | 9.7946 | 11.7946 | 8.9315 | 15.7946 | 25.5891 | 37.3837 | 0
2.5835 | 7.2917 | 4.5835 | 3.5835 | 4.8752 | 6.8752 | 7.2917 | 10.8752 | 15.7504 | 22.6257 | 2.5935 | 7.2917 | 4.5835 | 3.5835 | 4.8752 | 6.8752 | 7.2917 | 10.8752 | 15.7504 | 22.6257 | 0
5.0249 | 8.5125 | 7.0249 | 6.0249 | 8.5374 | 10.5374 | 8.5125 | 14.5374 | 23.0747 | 33.6121 | 5.0349 | 8.5125 | 7.0249 | 6.0249 | 8.5374 | 10.5374 | 8.5125 | 14.5374 | 23.0747 | 33.6121 | 0
6.1918 | 9.0959 | 8.1918 | 7.1918 | 10.2877 | 12.2877 | 9.0959 | 16.2877 | 26.5753 | 38.863 | 6.2018 | 9.0959 | 8.1918 | 7.1918 | 10.2877 | 12.2877 | 9.0959 | 16.2877 | 26.5753 | 38.863 | 0
5.0897 | 8.5449 | 7.0897 | 6.0897 | 8.6346 | 10.6346 | 8.5449 | 14.6346 | 23.2691 | 33.9037 | 5.0997 | 8.5449 | 7.0897 | 6.0897 | 8.6346 | 10.6346 | 8.5449 | 14.6346 | 23.2691 | 33.9037 | 0
5.4889 | 8.7445 | 7.4889 | 6.4889 | 9.2334 | 11.2334 | 8.7445 | 15.2334 | 24.4667 | 35.7001 | 5.4989 | 8.7445 | 7.4889 | 6.4889 | 9.2334 | 11.2334 | 8.7445 | 15.2334 | 24.4667 | 35.7001 | 0
8.7445 | 10.3722 | 10.7445 | 9.7445 | 14.1167 | 16.1167 | 10.3722 | 20.1167 | 34.2334 | 50.3502 | 8.7545 | 10.3722 | 10.7445 | 9.7445 | 14.1167 | 16.1167 | 10.3722 | 20.1167 | 34.2334 | 50.3502 | 0
6.1328 | 9.0664 | 8.1328 | 7.1328 | 10.1992 | 12.1992 | 9.0664 | 16.1992 | 26.3985 | 38.5977 | 6.1428 | 9.0664 | 8.1328 | 7.1328 | 10.1992 | 12.1992 | 9.0664 | 16.1992 | 26.3985 | 38.5977 | 0
6.4019 | 9.201 | 8.4019 | 7.4019 | 10.6029 | 12.6029 | 9.201 | 16.6029 | 27.2058 | 39.8087 | 6.4119 | 9.201 | 8.4019 | 7.4019 | 10.6029 | 12.6029 | 9.201 | 16.6029 | 27.2058 | 39.8087 | 0
4.0371 | 8.0185 | 6.0371 | 5.0371 | 7.0556 | 9.0556 | 8.0185 | 13.0556 | 20.1112 | 29.1668 | 4.0471 | 8.0185 | 6.0371 | 5.0371 | 7.0556 | 9.0556 | 8.0185 | 13.0556 | 20.1112 | 29.1668 | 0
5.83 | 8.915 | 7.83 | 6.83 | 9.7451 | 11.7451 | 8.915 | 15.7451 | 25.4901 | 37.2352 | 5.84 | 8.915 | 7.83 | 6.83 | 9.7451 | 11.7451 | 8.915 | 15.7451 | 25.4901 | 37.2352 | 0
2.6753 | 7.3376 | 4.6753 | 3.6753 | 5.0129 | 7.0129 | 7.3376 | 11.0129 | 16.0258 | 23.0387 | 2.6853 | 7.3376 | 4.6753 | 3.6753 | 5.0129 | 7.0129 | 7.3376 | 11.0129 | 16.0258 | 23.0387 | 0
5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 5.3659 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 0
2.6862 | 7.3431 | 4.6862 | 3.6862 | 5.0293 | 7.0293 | 7.3431 | 11.0293 | 16.0585 | 23.0878 | 2.6962 | 7.3431 | 4.6862 | 3.6862 | 5.0293 | 7.0293 | 7.3431 | 11.0293 | 16.0585 | 23.0878 | 0
9.7341 | 10.8671 | 11.7341 | 10.7341 | 15.6012 | 17.6012 | 10.8671 | 21.6012 | 37.2024 | 54.8037 | 9.7441 | 10.8671 | 11.7341 | 10.7341 | 15.6012 | 17.6012 | 10.8671 | 21.6012 | 37.2024 | 54.8037 | 0
4.1077 | 8.0538 | 6.1077 | 5.1077 | 7.1615 | 9.1615 | 8.0538 | 13.1615 | 20.323 | 29.4845 | 4.1177 | 8.0538 | 6.1077 | 5.1077 | 7.1615 | 9.1615 | 8.0538 | 13.1615 | 20.323 | 29.4845 | 0
7.484 | 9.742 | 9.484 | 8.484 | 12.226 | 14.226 | 9.742 | 18.226 | 30.452 | 44.6781 | 7.494 | 9.742 | 9.484 | 8.484 | 12.226 | 14.226 | 9.742 | 18.226 | 30.452 | 44.6781 | 0
6.2666 | 9.1333 | 8.2666 | 7.2666 | 10.3999 | 12.3999 | 9.1333 | 16.3999 | 26.7999 | 39.1998 | 6.2766 | 9.1333 | 8.2666 | 7.2666 | 10.3999 | 12.3999 | 9.1333 | 16.3999 | 26.7999 | 39.1998 | 0
5.2959 | 8.648 | 7.2959 | 6.2959 | 8.9439 | 10.9439 | 8.648 | 14.9439 | 23.8878 | 34.8317 | 5.3059 | 8.648 | 7.2959 | 6.2959 | 8.9439 | 10.9439 | 8.648 | 14.9439 | 23.8878 | 34.8317 | 0
4.8999 | 8.45 | 6.8999 | 5.8999 | 8.3499 | 10.3499 | 8.45 | 14.3499 | 22.6998 | 33.0497 | 4.9099 | 8.45 | 6.8999 | 5.8999 | 8.3499 | 10.3499 | 8.45 | 14.3499 | 22.6998 | 33.0497 | 0
5.8151 | 8.9076 | 7.8151 | 6.8151 | 9.7227 | 11.7227 | 8.9076 | 15.7227 | 25.4454 | 37.1682 | 5.8251 | 8.9076 | 7.8151 | 6.8151 | 9.7227 | 11.7227 | 8.9076 | 15.7227 | 25.4454 | 37.1682 | 0
5.9292 | 8.9646 | 7.9292 | 6.9292 | 9.8938 | 11.8938 | 8.9646 | 15.8938 | 25.7877 | 37.6815 | 5.9392 | 8.9646 | 7.9292 | 6.9292 | 9.8938 | 11.8938 | 8.9646 | 15.8938 | 25.7877 | 37.6815 | 0
2.9022 | 7.4511 | 4.9022 | 3.9022 | 5.3533 | 7.3533 | 7.4511 | 11.3533 | 16.7065 | 24.0598 | 2.9122 | 7.4511 | 4.9022 | 3.9022 | 5.3533 | 7.3533 | 7.4511 | 11.3533 | 16.7065 | 24.0598 | 0
3.7424 | 7.8712 | 5.7424 | 4.7424 | 6.6136 | 8.6136 | 7.8712 | 12.6136 | 19.2272 | 27.8407 | 3.7524 | 7.8712 | 5.7424 | 4.7424 | 6.6136 | 8.6136 | 7.8712 | 12.6136 | 19.2272 | 27.8407 | 0
8.3173 | 10.1587 | 10.3173 | 9.3173 | 13.476 | 15.476 | 10.1587 | 19.476 | 32.952 | 48.4281 | 8.3273 | 10.1587 | 10.3173 | 9.3173 | 13.476 | 15.476 | 10.1587 | 19.476 | 32.952 | 48.4281 | 0
4.7975 | 8.3988 | 6.7975 | 5.7975 | 8.1963 | 10.1963 | 8.3988 | 14.1963 | 22.3926 | 32.5889 | 4.8075 | 8.3988 | 6.7975 | 5.7975 | 8.1963 | 10.1963 | 8.3988 | 14.1963 | 22.3926 | 32.5889 | 0
4.0727 | 8.0363 | 6.0727 | 5.0727 | 7.109 | 9.109 | 8.0363 | 13.109 | 20.218 | 29.327 | 4.0827 | 8.0363 | 6.0727 | 5.0727 | 7.109 | 9.109 | 8.0363 | 13.109 | 20.218 | 29.327 | 0
7.2028 | 9.6014 | 9.2028 | 8.2028 | 11.8042 | 13.8042 | 9.6014 | 17.8042 | 29.6085 | 43.4127 | 7.2128 | 9.6014 | 9.2028 | 8.2028 | 11.8042 | 13.8042 | 9.6014 | 17.8042 | 29.6085 | 43.4127 | 0
5.1967 | 8.5984 | 7.1967 | 6.1967 | 8.7951 | 10.7951 | 8.5984 | 14.7951 | 23.5902 | 34.3852 | 5.2067 | 8.5984 | 7.1967 | 6.1967 | 8.7951 | 10.7951 | 8.5984 | 14.7951 | 23.5902 | 34.3852 | 0
3.0576 | 7.5288 | 5.0576 | 4.0576 | 5.5864 | 7.5864 | 7.5288 | 11.5864 | 17.1729 | 24.7593 | 3.0676 | 7.5288 | 5.0576 | 4.0576 | 5.5864 | 7.5864 | 7.5288 | 11.5864 | 17.1729 | 24.7593 | 0
4.772 | 8.386 | 6.772 | 5.772 | 8.1579 | 10.1579 | 8.386 | 14.1579 | 22.3159 | 32.4738 | 4.782 | 8.386 | 6.772 | 5.772 | 8.1579 | 10.1579 | 8.386 | 14.1579 | 22.3159 | 32.4738 | 0
6.9343 | 9.4671 | 8.9343 | 7.9343 | 11.4014 | 13.4014 | 9.4671 | 17.4014 | 28.8028 | 42.2043 | 6.9443 | 9.4671 | 8.9343 | 7.9343 | 11.4014 | 13.4014 | 9.4671 | 17.4014 | 28.8028 | 42.2043 | 0
5.9782 | 8.9891 | 7.9782 | 6.9782 | 9.9673 | 11.9673 | 8.9891 | 15.9673 | 25.9346 | 37.9019 | 5.9882 | 8.9891 | 7.9782 | 6.9782 | 9.9673 | 11.9673 | 8.9891 | 15.9673 | 25.9346 | 37.9019 | 0
4.3539 | 8.1769 | 6.3539 | 5.3539 | 7.5308 | 9.5308 | 8.1769 | 13.5308 | 21.0616 | 30.5925 | 4.3639 | 8.1769 | 6.3539 | 5.3539 | 7.5308 | 9.5308 | 8.1769 | 13.5308 | 21.0616 | 30.5925 | 0
4.4273 | 8.2136 | 6.4273 | 5.4273 | 7.6409 | 9.6409 | 8.2136 | 13.6409 | 21.2818 | 30.9227 | 4.4373 | 8.2136 | 6.4273 | 5.4273 | 7.6409 | 9.6409 | 8.2136 | 13.6409 | 21.2818 | 30.9227 | 0
5.6648 | 8.8324 | 7.6648 | 6.6648 | 9.4972 | 11.4972 | 8.8324 | 15.4972 | 24.9945 | 36.4917 | 5.6748 | 8.8324 | 7.6648 | 6.6648 | 9.4972 | 11.4972 | 8.8324 | 15.4972 | 24.9945 | 36.4917 | 0
6.1502 | 9.0751 | 8.1502 | 7.1502 | 10.2252 | 12.2252 | 9.0751 | 16.2252 | 26.4505 | 38.6757 | 6.1602 | 9.0751 | 8.1502 | 7.1502 | 10.2252 | 12.2252 | 9.0751 | 16.2252 | 26.4505 | 38.6757 | 0
13.0455 | 12.5227 | 15.0455 | 14.0455 | 20.5682 | 22.5682 | 13.0455 | 27.0909 | 47.6591 | 70.2273 | 13.0555 | 12.5227 | 15.0455 | 14.0455 | 20.5682 | 22.5682 | 13.0555 | 27.1009 | 47.6691 | 70.2373 | 0.01
7.6173 | 9.8087 | 9.6173 | 8.6173 | 12.426 | 14.426 | 9.8087 | 18.426 | 30.8519 | 45.2779 | 7.6273 | 9.8087 | 9.6173 | 8.6173 | 12.426 | 14.426 | 9.8087 | 18.426 | 30.8519 | 45.2779 | 0
8.3774 | 10.1887 | 10.3774 | 9.3774 | 13.566 | 15.566 | 10.1887 | 19.566 | 33.1321 | 48.6981 | 8.3874 | 10.1887 | 10.3774 | 9.3774 | 13.566 | 15.566 | 10.1887 | 19.566 | 33.1321 | 48.6981 | 0
6.074 | 9.037 | 8.074 | 7.074 | 10.111 | 12.111 | 9.037 | 16.111 | 26.222 | 38.333 | 6.084 | 9.037 | 8.074 | 7.074 | 10.111 | 12.111 | 9.037 | 16.111 | 26.222 | 38.333 | 0
5.9353 | 8.9677 | 7.9353 | 6.9353 | 9.903 | 11.903 | 8.9677 | 15.903 | 25.806 | 37.7091 | 5.9453 | 8.9677 | 7.9353 | 6.9353 | 9.903 | 11.903 | 8.9677 | 15.903 | 25.806 | 37.7091 | 0
6.9629 | 9.4814 | 8.9629 | 7.9629 | 11.4443 | 13.4443 | 9.4814 | 17.4443 | 28.8886 | 42.3329 | 6.9729 | 9.4814 | 8.9629 | 7.9629 | 11.4443 | 13.4443 | 9.4814 | 17.4443 | 28.8886 | 42.3329 | 0
3.2723 | 7.6361 | 5.2723 | 4.2723 | 5.9084 | 7.9084 | 7.6361 | 11.9084 | 17.8169 | 25.7253 | 3.2823 | 7.6361 | 5.2723 | 4.2723 | 5.9084 | 7.9084 | 7.6361 | 11.9084 | 17.8169 | 25.7253 | 0
5.3875 | 8.6938 | 7.3875 | 6.3875 | 9.0813 | 11.0813 | 8.6938 | 15.0813 | 24.1626 | 35.2438 | 5.3975 | 8.6938 | 7.3875 | 6.3875 | 9.0813 | 11.0813 | 8.6938 | 15.0813 | 24.1626 | 35.2438 | 0
2.8991 | 7.4496 | 4.8991 | 3.8991 | 5.3487 | 7.3487 | 7.4496 | 11.3487 | 16.6974 | 24.0461 | 2.9091 | 7.4496 | 4.8991 | 3.8991 | 5.3487 | 7.3487 | 7.4496 | 11.3487 | 16.6974 | 24.0461 | 0
6.8927 | 9.4463 | 8.8927 | 7.8927 | 11.339 | 13.339 | 9.4463 | 17.339 | 28.678 | 42.017 | 6.9027 | 9.4463 | 8.8927 | 7.8927 | 11.339 | 13.339 | 9.4463 | 17.339 | 28.678 | 42.017 | 0
5.2946 | 8.6473 | 7.2946 | 6.2946 | 8.942 | 10.942 | 8.6473 | 14.942 | 23.8839 | 34.8259 | 5.3046 | 8.6473 | 7.2946 | 6.2946 | 8.942 | 10.942 | 8.6473 | 14.942 | 23.8839 | 34.8259 | 0
7.3723 | 9.6861 | 9.3723 | 8.3723 | 12.0584 | 14.0584 | 9.6861 | 18.0584 | 30.1168 | 44.1752 | 7.3823 | 9.6861 | 9.3723 | 8.3723 | 12.0584 | 14.0584 | 9.6861 | 18.0584 | 30.1168 | 44.1752 | 0
6.4354 | 9.2177 | 8.4354 | 7.4354 | 10.6531 | 12.6531 | 9.2177 | 16.6531 | 27.3062 | 39.9593 | 6.4454 | 9.2177 | 8.4354 | 7.4354 | 10.6531 | 12.6531 | 9.2177 | 16.6531 | 27.3062 | 39.9593 | 0
5.4793 | 8.7396 | 7.4793 | 6.4793 | 9.2189 | 11.2189 | 8.7396 | 15.2189 | 24.4378 | 35.6567 | 5.4893 | 8.7396 | 7.4793 | 6.4793 | 9.2189 | 11.2189 | 8.7396 | 15.2189 | 24.4378 | 35.6567 | 0
6.2472 | 9.1236 | 8.2472 | 7.2472 | 10.3708 | 12.3708 | 9.1236 | 16.3708 | 26.7415 | 39.1123 | 6.2572 | 9.1236 | 8.2472 | 7.2472 | 10.3708 | 12.3708 | 9.1236 | 16.3708 | 26.7415 | 39.1123 | 0
4.9739 | 8.487 | 6.9739 | 5.9739 | 8.4609 | 10.4609 | 8.487 | 14.4609 | 22.9218 | 33.3827 | 4.9839 | 8.487 | 6.9739 | 5.9739 | 8.4609 | 10.4609 | 8.487 | 14.4609 | 22.9218 | 33.3827 | 0
1.3058 | 6.6529 | 3.3058 | 2.3058 | 2.9588 | 4.9588 | 6.6529 | 8.9588 | 11.9175 | 16.8763 | 1.3158 | 6.6529 | 3.3058 | 2.3058 | 2.9588 | 4.9588 | 6.6529 | 8.9588 | 11.9175 | 16.8763 | 0
6.9362 | 9.4681 | 8.9362 | 7.9362 | 11.4042 | 13.4042 | 9.4681 | 17.4042 | 28.8085 | 42.2127 | 6.9462 | 9.4681 | 8.9362 | 7.9362 | 11.4042 | 13.4042 | 9.4681 | 17.4042 | 28.8085 | 42.2127 | 0
7.1438 | 9.5719 | 9.1438 | 8.1438 | 11.7157 | 13.7157 | 9.5719 | 17.7157 | 29.4313 | 43.147 | 7.1538 | 9.5719 | 9.1438 | 8.1438 | 11.7157 | 13.7157 | 9.5719 | 17.7157 | 29.4313 | 43.147 | 0
7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 7.2623 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 0
10.4708 | 11.2354 | 12.4708 | 11.4708 | 16.7062 | 18.7062 | 11.2354 | 22.7062 | 39.4124 | 58.1185 | 10.4808 | 11.2354 | 12.4708 | 11.4708 | 16.7062 | 18.7062 | 11.2354 | 22.7062 | 39.4124 | 58.1185 | 0
7.3244 | 9.6622 | 9.3244 | 8.3244 | 11.9867 | 13.9867 | 9.6622 | 17.9867 | 29.9733 | 43.96 | 7.3344 | 9.6622 | 9.3244 | 8.3244 | 11.9867 | 13.9867 | 9.6622 | 17.9867 | 29.9733 | 43.96 | 0
3.4391 | 7.7195 | 5.4391 | 4.4391 | 6.1586 | 8.1586 | 7.7195 | 12.1586 | 18.3173 | 26.4759 | 3.4491 | 7.7195 | 5.4391 | 4.4391 | 6.1586 | 8.1586 | 7.7195 | 12.1586 | 18.3173 | 26.4759 | 0
3.4033 | 7.7016 | 5.4033 | 4.4033 | 6.1049 | 8.1049 | 7.7016 | 12.1049 | 18.2098 | 26.3146 | 3.4133 | 7.7016 | 5.4033 | 4.4033 | 6.1049 | 8.1049 | 7.7016 | 12.1049 | 18.2098 | 26.3146 | 0
6.3856 | 9.1928 | 8.3856 | 7.3856 | 10.5783 | 12.5783 | 9.1928 | 16.5783 | 27.1567 | 39.735 | 6.3956 | 9.1928 | 8.3856 | 7.3856 | 10.5783 | 12.5783 | 9.1928 | 16.5783 | 27.1567 | 39.735 | 0
4.8622 | 8.4311 | 6.8622 | 5.8622 | 8.2933 | 10.2933 | 8.4311 | 14.2933 | 22.5865 | 32.8798 | 4.8722 | 8.4311 | 6.8622 | 5.8622 | 8.2933 | 10.2933 | 8.4311 | 14.2933 | 22.5865 | 32.8798 | 0
6.2649 | 9.1325 | 8.2649 | 7.2649 | 10.3974 | 12.3974 | 9.1325 | 16.3974 | 26.7948 | 39.1921 | 6.2749 | 9.1325 | 8.2649 | 7.2649 | 10.3974 | 12.3974 | 9.1325 | 16.3974 | 26.7948 | 39.1921 | 0
6.3815 | 9.1908 | 8.3815 | 7.3815 | 10.5723 | 12.5723 | 9.1908 | 16.5723 | 27.1445 | 39.7168 | 6.3915 | 9.1908 | 8.3815 | 7.3815 | 10.5723 | 12.5723 | 9.1908 | 16.5723 | 27.1445 | 39.7168 | 0
6.0503 | 9.0251 | 8.0503 | 7.0503 | 10.0754 | 12.0754 | 9.0251 | 16.0754 | 26.1508 | 38.2262 | 6.0603 | 9.0251 | 8.0503 | 7.0503 | 10.0754 | 12.0754 | 9.0251 | 16.0754 | 26.1508 | 38.2262 | 0
7.3199 | 9.6599 | 9.3199 | 8.3199 | 11.9798 | 13.9798 | 9.6599 | 17.9798 | 29.9596 | 43.9394 | 7.3299 | 9.6599 | 9.3199 | 8.3199 | 11.9798 | 13.9798 | 9.6599 | 17.9798 | 29.9596 | 43.9394 | 0
4.8278 | 8.4139 | 6.8278 | 5.8278 | 8.2417 | 10.2417 | 8.4139 | 14.2417 | 22.4835 | 32.7252 | 4.8378 | 8.4139 | 6.8278 | 5.8278 | 8.2417 | 10.2417 | 8.4139 | 14.2417 | 22.4835 | 32.7252 | 0
5.4652 | 8.7326 | 7.4652 | 6.4652 | 9.1977 | 11.1977 | 8.7326 | 15.1977 | 24.3955 | 35.5932 | 5.4752 | 8.7326 | 7.4652 | 6.4652 | 9.1977 | 11.1977 | 8.7326 | 15.1977 | 24.3955 | 35.5932 | 0
3.3593 | 7.6796 | 5.3593 | 4.3593 | 6.0389 | 8.0389 | 7.6796 | 12.0389 | 18.0778 | 26.1167 | 3.3693 | 7.6796 | 5.3593 | 4.3593 | 6.0389 | 8.0389 | 7.6796 | 12.0389 | 18.0778 | 26.1167 | 0
7.5124 | 9.7562 | 9.5124 | 8.5124 | 12.2686 | 14.2686 | 9.7562 | 18.2686 | 30.5371 | 44.8057 | 7.5224 | 9.7562 | 9.5124 | 8.5124 | 12.2686 | 14.2686 | 9.7562 | 18.2686 | 30.5371 | 44.8057 | 0
3.9132 | 7.9566 | 5.9132 | 4.9132 | 6.8698 | 8.8698 | 7.9566 | 12.8698 | 19.7396 | 28.6094 | 3.9232 | 7.9566 | 5.9132 | 4.9132 | 6.8698 | 8.8698 | 7.9566 | 12.8698 | 19.7396 | 28.6094 | 0
1.5199 | 6.7599 | 3.5199 | 2.5199 | 3.2798 | 5.2798 | 6.7599 | 9.2798 | 12.5596 | 17.8394 | 1.5299 | 6.7599 | 3.5199 | 2.5199 | 3.2798 | 5.2798 | 6.7599 | 9.2798 | 12.5596 | 17.8394 | 0
4.6499 | 8.325 | 6.6499 | 5.6499 | 7.9749 | 9.9749 | 8.325 | 13.9749 | 21.9497 | 31.9246 | 4.6599 | 8.325 | 6.6499 | 5.6499 | 7.9749 | 9.9749 | 8.325 | 13.9749 | 21.9497 | 31.9246 | 0
4.3616 | 8.1808 | 6.3616 | 5.3616 | 7.5424 | 9.5424 | 8.1808 | 13.5424 | 21.0848 | 30.6272 | 4.3716 | 8.1808 | 6.3616 | 5.3616 | 7.5424 | 9.5424 | 8.1808 | 13.5424 | 21.0848 | 30.6272 | 0
5.2767 | 8.6383 | 7.2767 | 6.2767 | 8.915 | 10.915 | 8.6383 | 14.915 | 23.8301 | 34.7451 | 5.2867 | 8.6383 | 7.2767 | 6.2767 | 8.915 | 10.915 | 8.6383 | 14.915 | 23.8301 | 34.7451 | 0
4.6809 | 8.3404 | 6.6809 | 5.6809 | 8.0213 | 10.0213 | 8.3404 | 14.0213 | 22.0426 | 32.064 | 4.6909 | 8.3404 | 6.6809 | 5.6809 | 8.0213 | 10.0213 | 8.3404 | 14.0213 | 22.0426 | 32.064 | 0
7.3392 | 9.6696 | 9.3392 | 8.3392 | 12.0087 | 14.0087 | 9.6696 | 18.0087 | 30.0175 | 44.0262 | 7.3492 | 9.6696 | 9.3392 | 8.3392 | 12.0087 | 14.0087 | 9.6696 | 18.0087 | 30.0175 | 44.0262 | 0
5.9878 | 8.9939 | 7.9878 | 6.9878 | 9.9818 | 11.9818 | 8.9939 | 15.9818 | 25.9635 | 37.9453 | 5.9978 | 8.9939 | 7.9878 | 6.9878 | 9.9818 | 11.9818 | 8.9939 | 15.9818 | 25.9635 | 37.9453 | 0
7.2575 | 9.6288 | 9.2575 | 8.2575 | 11.8863 | 13.8863 | 9.6288 | 17.8863 | 29.7726 | 43.659 | 7.2675 | 9.6288 | 9.2575 | 8.2575 | 11.8863 | 13.8863 | 9.6288 | 17.8863 | 29.7726 | 43.659 | 0
6.2064 | 9.1032 | 8.2064 | 7.2064 | 10.3096 | 12.3096 | 9.1032 | 16.3096 | 26.6191 | 38.9287 | 6.2164 | 9.1032 | 8.2064 | 7.2064 | 10.3096 | 12.3096 | 9.1032 | 16.3096 | 26.6191 | 38.9287 | 0
3.8799 | 7.94 | 5.8799 | 4.8799 | 6.8199 | 8.8199 | 7.94 | 12.8199 | 19.6398 | 28.4598 | 3.8899 | 7.94 | 5.8799 | 4.8799 | 6.8199 | 8.8199 | 7.94 | 12.8199 | 19.6398 | 28.4598 | 0
2.4504 | 7.2252 | 4.4504 | 3.4504 | 4.6756 | 6.6756 | 7.2252 | 10.6756 | 15.3512 | 22.0267 | 2.4604 | 7.2252 | 4.4504 | 3.4504 | 4.6756 | 6.6756 | 7.2252 | 10.6756 | 15.3512 | 22.0267 | 0
5.7233 | 8.8617 | 7.7233 | 6.7233 | 9.585 | 11.585 | 8.8617 | 15.585 | 25.17 | 36.755 | 5.7333 | 8.8617 | 7.7233 | 6.7233 | 9.585 | 11.585 | 8.8617 | 15.585 | 25.17 | 36.755 | 0
8.2167 | 10.1084 | 10.2167 | 9.2167 | 13.3251 | 15.3251 | 10.1084 | 19.3251 | 32.6501 | 47.9752 | 8.2267 | 10.1084 | 10.2167 | 9.2167 | 13.3251 | 15.3251 | 10.1084 | 19.3251 | 32.6501 | 47.9752 | 0
5.8225 | 8.9113 | 7.8225 | 6.8225 | 9.7338 | 11.7338 | 8.9113 | 15.7338 | 25.4676 | 37.2013 | 5.8325 | 8.9113 | 7.8225 | 6.8225 | 9.7338 | 11.7338 | 8.9113 | 15.7338 | 25.4676 | 37.2013 | 0
4.44 | 8.22 | 6.44 | 5.44 | 7.6599 | 9.6599 | 8.22 | 13.6599 | 21.3199 | 30.9798 | 4.45 | 8.22 | 6.44 | 5.44 | 7.6599 | 9.6599 | 8.22 | 13.6599 | 21.3199 | 30.9798 | 0
5.5445 | 8.7723 | 7.5445 | 6.5445 | 9.3168 | 11.3168 | 8.7723 | 15.3168 | 24.6336 | 35.9503 | 5.5545 | 8.7723 | 7.5445 | 6.5445 | 9.3168 | 11.3168 | 8.7723 | 15.3168 | 24.6336 | 35.9503 | 0
6.9782 | 9.4891 | 8.9782 | 7.9782 | 11.4673 | 13.4673 | 9.4891 | 17.4673 | 28.9346 | 42.4018 | 6.9882 | 9.4891 | 8.9782 | 7.9782 | 11.4673 | 13.4673 | 9.4891 | 17.4673 | 28.9346 | 42.4018 | 0
4.06 | 8.03 | 6.06 | 5.06 | 7.09 | 9.09 | 8.03 | 13.09 | 20.1799 | 29.2699 | 4.07 | 8.03 | 6.06 | 5.06 | 7.09 | 9.09 | 8.03 | 13.09 | 20.1799 | 29.2699 | 0
6.8952 | 9.4476 | 8.8952 | 7.8952 | 11.3428 | 13.3428 | 9.4476 | 17.3428 | 28.6856 | 42.0284 | 6.9052 | 9.4476 | 8.8952 | 7.8952 | 11.3428 | 13.3428 | 9.4476 | 17.3428 | 28.6856 | 42.0284 | 0
4.2954 | 8.1477 | 6.2954 | 5.2954 | 7.4431 | 9.4431 | 8.1477 | 13.4431 | 20.8863 | 30.3294 | 4.3054 | 8.1477 | 6.2954 | 5.2954 | 7.4431 | 9.4431 | 8.1477 | 13.4431 | 20.8863 | 30.3294 | 0
5.384 | 8.692 | 7.384 | 6.384 | 9.076 | 11.076 | 8.692 | 15.076 | 24.152 | 35.228 | 5.394 | 8.692 | 7.384 | 6.384 | 9.076 | 11.076 | 8.692 | 15.076 | 24.152 | 35.228 | 0
5.5138 | 8.7569 | 7.5138 | 6.5138 | 9.2708 | 11.2708 | 8.7569 | 15.2708 | 24.5415 | 35.8123 | 5.5238 | 8.7569 | 7.5138 | 6.5138 | 9.2708 | 11.2708 | 8.7569 | 15.2708 | 24.5415 | 35.8123 | 0
6.558 | 9.279 | 8.558 | 7.558 | 10.837 | 12.837 | 9.279 | 16.837 | 27.6741 | 40.5111 | 6.568 | 9.279 | 8.558 | 7.558 | 10.837 | 12.837 | 9.279 | 16.837 | 27.6741 | 40.5111 | 0
6.8751 | 9.4376 | 8.8751 | 7.8751 | 11.3127 | 13.3127 | 9.4376 | 17.3127 | 28.6254 | 41.9381 | 6.8851 | 9.4376 | 8.8751 | 7.8751 | 11.3127 | 13.3127 | 9.4376 | 17.3127 | 28.6254 | 41.9381 | 0
5.5105 | 8.7553 | 7.5105 | 6.5105 | 9.2658 | 11.2658 | 8.7553 | 15.2658 | 24.5316 | 35.7974 | 5.5205 | 8.7553 | 7.5105 | 6.5105 | 9.2658 | 11.2658 | 8.7553 | 15.2658 | 24.5316 | 35.7974 | 0
3.8041 | 7.902 | 5.8041 | 4.8041 | 6.7061 | 8.7061 | 7.902 | 12.7061 | 19.4123 | 28.1184 | 3.8141 | 7.902 | 5.8041 | 4.8041 | 6.7061 | 8.7061 | 7.902 | 12.7061 | 19.4123 | 28.1184 | 0
6.5984 | 9.2992 | 8.5984 | 7.5984 | 10.8976 | 12.8976 | 9.2992 | 16.8976 | 27.7952 | 40.6927 | 6.6084 | 9.2992 | 8.5984 | 7.5984 | 10.8976 | 12.8976 | 9.2992 | 16.8976 | 27.7952 | 40.6927 | 0
4.1412 | 8.0706 | 6.1412 | 5.1412 | 7.2117 | 9.2117 | 8.0706 | 13.2117 | 20.4235 | 29.6352 | 4.1512 | 8.0706 | 6.1412 | 5.1412 | 7.2117 | 9.2117 | 8.0706 | 13.2117 | 20.4235 | 29.6352 | 0
8.1884 | 10.0942 | 10.1884 | 9.1884 | 13.2826 | 15.2826 | 10.0942 | 19.2826 | 32.5651 | 47.8477 | 8.1984 | 10.0942 | 10.1884 | 9.1884 | 13.2826 | 15.2826 | 10.0942 | 19.2826 | 32.5651 | 47.8477 | 0
3.3929 | 7.6965 | 5.3929 | 4.3929 | 6.0894 | 8.0894 | 7.6965 | 12.0894 | 18.1787 | 26.2681 | 3.4029 | 7.6965 | 5.3929 | 4.3929 | 6.0894 | 8.0894 | 7.6965 | 12.0894 | 18.1787 | 26.2681 | 0
8.253 | 10.1265 | 10.253 | 9.253 | 13.3795 | 15.3795 | 10.1265 | 19.3795 | 32.759 | 48.1384 | 8.263 | 10.1265 | 10.253 | 9.253 | 13.3795 | 15.3795 | 10.1265 | 19.3795 | 32.759 | 48.1384 | 0
6.3518 | 9.1759 | 8.3518 | 7.3518 | 10.5277 | 12.5277 | 9.1759 | 16.5277 | 27.0554 | 39.583 | 6.3618 | 9.1759 | 8.3518 | 7.3518 | 10.5277 | 12.5277 | 9.1759 | 16.5277 | 27.0554 | 39.583 | 0
6.4248 | 9.2124 | 8.4248 | 7.4248 | 10.6371 | 12.6371 | 9.2124 | 16.6371 | 27.2743 | 39.9114 | 6.4348 | 9.2124 | 8.4248 | 7.4248 | 10.6371 | 12.6371 | 9.2124 | 16.6371 | 27.2743 | 39.9114 | 0
4.0788 | 8.0394 | 6.0788 | 5.0788 | 7.1181 | 9.1181 | 8.0394 | 13.1181 | 20.2363 | 29.3544 | 4.0888 | 8.0394 | 6.0788 | 5.0788 | 7.1181 | 9.1181 | 8.0394 | 13.1181 | 20.2363 | 29.3544 | 0
3.7415 | 7.8708 | 5.7415 | 4.7415 | 6.6123 | 8.6123 | 7.8708 | 12.6123 | 19.2246 | 27.8368 | 3.7515 | 7.8708 | 5.7415 | 4.7415 | 6.6123 | 8.6123 | 7.8708 | 12.6123 | 19.2246 | 27.8368 | 0
7.8238 | 9.9119 | 9.8238 | 8.8238 | 12.7357 | 14.7357 | 9.9119 | 18.7357 | 31.4713 | 46.207 | 7.8338 | 9.9119 | 9.8238 | 8.8238 | 12.7357 | 14.7357 | 9.9119 | 18.7357 | 31.4713 | 46.207 | 0
5.4348 | 8.7174 | 7.4348 | 6.4348 | 9.1522 | 11.1522 | 8.7174 | 15.1522 | 24.3044 | 35.4567 | 5.4448 | 8.7174 | 7.4348 | 6.4348 | 9.1522 | 11.1522 | 8.7174 | 15.1522 | 24.3044 | 35.4567 | 0
4.2646 | 8.1323 | 6.2646 | 5.2646 | 7.397 | 9.397 | 8.1323 | 13.397 | 20.7939 | 30.1909 | 4.2746 | 8.1323 | 6.2646 | 5.2646 | 7.397 | 9.397 | 8.1323 | 13.397 | 20.7939 | 30.1909 | 0
5.7679 | 8.884 | 7.7679 | 6.7679 | 9.6519 | 11.6519 | 8.884 | 15.6519 | 25.3038 | 36.9556 | 5.7779 | 8.884 | 7.7679 | 6.7679 | 9.6519 | 11.6519 | 8.884 | 15.6519 | 25.3038 | 36.9556 | 0
6.0709 | 9.0355 | 8.0709 | 7.0709 | 10.1064 | 12.1064 | 9.0355 | 16.1064 | 26.2128 | 38.3192 | 6.0809 | 9.0355 | 8.0709 | 7.0709 | 10.1064 | 12.1064 | 9.0355 | 16.1064 | 26.2128 | 38.3192 | 0
7.1335 | 9.5668 | 9.1335 | 8.1335 | 11.7003 | 13.7003 | 9.5668 | 17.7003 | 29.4005 | 43.1008 | 7.1435 | 9.5668 | 9.1335 | 8.1335 | 11.7003 | 13.7003 | 9.5668 | 17.7003 | 29.4005 | 43.1008 | 0
7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 7.2623 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 0
1.7153 | 6.8577 | 3.7153 | 2.7153 | 3.573 | 5.573 | 6.8577 | 9.573 | 13.146 | 18.719 | 1.7253 | 6.8577 | 3.7153 | 2.7153 | 3.573 | 5.573 | 6.8577 | 9.573 | 13.146 | 18.719 | 0
2.3377 | 7.1689 | 4.3377 | 3.3377 | 4.5066 | 6.5066 | 7.1689 | 10.5066 | 15.0132 | 21.5197 | 2.3477 | 7.1689 | 4.3377 | 3.3377 | 4.5066 | 6.5066 | 7.1689 | 10.5066 | 15.0132 | 21.5197 | 0
4.5542 | 8.2771 | 6.5542 | 5.5542 | 7.8313 | 9.8313 | 8.2771 | 13.8313 | 21.6626 | 31.4939 | 4.5642 | 8.2771 | 6.5542 | 5.5542 | 7.8313 | 9.8313 | 8.2771 | 13.8313 | 21.6626 | 31.4939 | 0
8.0371 | 10.0185 | 10.0371 | 9.0371 | 13.0556 | 15.0556 | 10.0185 | 19.0556 | 32.1113 | 47.1669 | 8.0471 | 10.0185 | 10.0371 | 9.0371 | 13.0556 | 15.0556 | 10.0185 | 19.0556 | 32.1113 | 47.1669 | 0
9.1147 | 10.5573 | 11.1147 | 10.1147 | 14.672 | 16.672 | 10.5573 | 20.672 | 35.3441 | 52.0161 | 9.1247 | 10.5573 | 11.1147 | 10.1147 | 14.672 | 16.672 | 10.5573 | 20.672 | 35.3441 | 52.0161 | 0
6.8241 | 9.412 | 8.8241 | 7.8241 | 11.2361 | 13.2361 | 9.412 | 17.2361 | 28.4722 | 41.7083 | 6.8341 | 9.412 | 8.8241 | 7.8241 | 11.2361 | 13.2361 | 9.412 | 17.2361 | 28.4722 | 41.7083 | 0
6.7062 | 9.3531 | 8.7062 | 7.7062 | 11.0593 | 13.0593 | 9.3531 | 17.0593 | 28.1185 | 41.1778 | 6.7162 | 9.3531 | 8.7062 | 7.7062 | 11.0593 | 13.0593 | 9.3531 | 17.0593 | 28.1185 | 41.1778 | 0
5.2576 | 8.6288 | 7.2576 | 6.2576 | 8.8863 | 10.8863 | 8.6288 | 14.8863 | 23.7727 | 34.659 | 5.2676 | 8.6288 | 7.2576 | 6.2576 | 8.8863 | 10.8863 | 8.6288 | 14.8863 | 23.7727 | 34.659 | 0
6.3132 | 9.1566 | 8.3132 | 7.3132 | 10.4697 | 12.4697 | 9.1566 | 16.4697 | 26.9395 | 39.4092 | 6.3232 | 9.1566 | 8.3132 | 7.3132 | 10.4697 | 12.4697 | 9.1566 | 16.4697 | 26.9395 | 39.4092 | 0
5.6124 | 8.8062 | 7.6124 | 6.6124 | 9.4186 | 11.4186 | 8.8062 | 15.4186 | 24.8373 | 36.2559 | 5.6224 | 8.8062 | 7.6124 | 6.6124 | 9.4186 | 11.4186 | 8.8062 | 15.4186 | 24.8373 | 36.2559 | 0
4.4577 | 8.2289 | 6.4577 | 5.4577 | 7.6866 | 9.6866 | 8.2289 | 13.6866 | 21.3732 | 31.0598 | 4.4677 | 8.2289 | 6.4577 | 5.4577 | 7.6866 | 9.6866 | 8.2289 | 13.6866 | 21.3732 | 31.0598 | 0
7.1172 | 9.5586 | 9.1172 | 8.1172 | 11.6758 | 13.6758 | 9.5586 | 17.6758 | 29.3516 | 43.0274 | 7.1272 | 9.5586 | 9.1172 | 8.1172 | 11.6758 | 13.6758 | 9.5586 | 17.6758 | 29.3516 | 43.0274 | 0
1.8832 | 6.9416 | 3.8832 | 2.8832 | 3.8248 | 5.8248 | 6.9416 | 9.8248 | 13.6496 | 19.4744 | 1.8932 | 6.9416 | 3.8832 | 2.8832 | 3.8248 | 5.8248 | 6.9416 | 9.8248 | 13.6496 | 19.4744 | 0
9.3963 | 10.6981 | 11.3963 | 10.3963 | 15.0944 | 17.0944 | 10.6981 | 21.0944 | 36.1889 | 53.2833 | 9.4063 | 10.6981 | 11.3963 | 10.3963 | 15.0944 | 17.0944 | 10.6981 | 21.0944 | 36.1889 | 53.2833 | 0
5.7522 | 8.8761 | 7.7522 | 6.7522 | 9.6283 | 11.6283 | 8.8761 | 15.6283 | 25.2566 | 36.8849 | 5.7622 | 8.8761 | 7.7522 | 6.7522 | 9.6283 | 11.6283 | 8.8761 | 15.6283 | 25.2566 | 36.8849 | 0
8.7802 | 10.3901 | 10.7802 | 9.7802 | 14.1703 | 16.1703 | 10.3901 | 20.1703 | 34.3407 | 50.511 | 8.7902 | 10.3901 | 10.7802 | 9.7802 | 14.1703 | 16.1703 | 10.3901 | 20.1703 | 34.3407 | 50.511 | 0
6.4029 | 9.2014 | 8.4029 | 7.4029 | 10.6043 | 12.6043 | 9.2014 | 16.6043 | 27.2086 | 39.8129 | 6.4129 | 9.2014 | 8.4029 | 7.4029 | 10.6043 | 12.6043 | 9.2014 | 16.6043 | 27.2086 | 39.8129 | 0
3.783 | 7.8915 | 5.783 | 4.783 | 6.6745 | 8.6745 | 7.8915 | 12.6745 | 19.349 | 28.0235 | 3.793 | 7.8915 | 5.783 | 4.783 | 6.6745 | 8.6745 | 7.8915 | 12.6745 | 19.349 | 28.0235 | 0
4.0209 | 8.0105 | 6.0209 | 5.0209 | 7.0314 | 9.0314 | 8.0105 | 13.0314 | 20.0627 | 29.0941 | 4.0309 | 8.0105 | 6.0209 | 5.0209 | 7.0314 | 9.0314 | 8.0105 | 13.0314 | 20.0627 | 29.0941 | 0
6.4079 | 9.2039 | 8.4079 | 7.4079 | 10.6118 | 12.6118 | 9.2039 | 16.6118 | 27.2236 | 39.8354 | 6.4179 | 9.2039 | 8.4079 | 7.4079 | 10.6118 | 12.6118 | 9.2039 | 16.6118 | 27.2236 | 39.8354 | 0
6.5453 | 9.2727 | 8.5453 | 7.5453 | 10.818 | 12.818 | 9.2727 | 16.818 | 27.6359 | 40.4539 | 6.5553 | 9.2727 | 8.5453 | 7.5453 | 10.818 | 12.818 | 9.2727 | 16.818 | 27.6359 | 40.4539 | 0
7.6805 | 9.8402 | 9.6805 | 8.6805 | 12.5207 | 14.5207 | 9.8402 | 18.5207 | 31.0415 | 45.5622 | 7.6905 | 9.8402 | 9.6805 | 8.6805 | 12.5207 | 14.5207 | 9.8402 | 18.5207 | 31.0415 | 45.5622 | 0
6.1081 | 9.0541 | 8.1081 | 7.1081 | 10.1622 | 12.1622 | 9.0541 | 16.1622 | 26.3244 | 38.4866 | 6.1181 | 9.0541 | 8.1081 | 7.1081 | 10.1622 | 12.1622 | 9.0541 | 16.1622 | 26.3244 | 38.4866 | 0
6.5904 | 9.2952 | 8.5904 | 7.5904 | 10.8856 | 12.8856 | 9.2952 | 16.8856 | 27.7712 | 40.6568 | 6.6004 | 9.2952 | 8.5904 | 7.5904 | 10.8856 | 12.8856 | 9.2952 | 16.8856 | 27.7712 | 40.6568 | 0
6.4252 | 9.2126 | 8.4252 | 7.4252 | 10.6378 | 12.6378 | 9.2126 | 16.6378 | 27.2757 | 39.9135 | 6.4352 | 9.2126 | 8.4252 | 7.4252 | 10.6378 | 12.6378 | 9.2126 | 16.6378 | 27.2757 | 39.9135 | 0
5.1021 | 8.551 | 7.1021 | 6.1021 | 8.6531 | 10.6531 | 8.551 | 14.6531 | 23.3063 | 33.9594 | 5.1121 | 8.551 | 7.1021 | 6.1021 | 8.6531 | 10.6531 | 8.551 | 14.6531 | 23.3063 | 33.9594 | 0
5.7627 | 8.8813 | 7.7627 | 6.7627 | 9.644 | 11.644 | 8.8813 | 15.644 | 25.288 | 36.9321 | 5.7727 | 8.8813 | 7.7627 | 6.7627 | 9.644 | 11.644 | 8.8813 | 15.644 | 25.288 | 36.9321 | 0
6.6646 | 9.3323 | 8.6646 | 7.6646 | 10.997 | 12.997 | 9.3323 | 16.997 | 27.9939 | 40.9909 | 6.6746 | 9.3323 | 8.6646 | 7.6646 | 10.997 | 12.997 | 9.3323 | 16.997 | 27.9939 | 40.9909 | 0
3.2081 | 7.604 | 5.2081 | 4.2081 | 5.8121 | 7.8121 | 7.604 | 11.8121 | 17.6242 | 25.4363 | 3.2181 | 7.604 | 5.2081 | 4.2081 | 5.8121 | 7.8121 | 7.604 | 11.8121 | 17.6242 | 25.4363 | 0
5.1092 | 8.5546 | 7.1092 | 6.1092 | 8.6638 | 10.6638 | 8.5546 | 14.6638 | 23.3276 | 33.9913 | 5.1192 | 8.5546 | 7.1092 | 6.1092 | 8.6638 | 10.6638 | 8.5546 | 14.6638 | 23.3276 | 33.9913 | 0
6.6987 | 9.3493 | 8.6987 | 7.6987 | 11.048 | 13.048 | 9.3493 | 17.048 | 28.0961 | 41.1441 | 6.7087 | 9.3493 | 8.6987 | 7.6987 | 11.048 | 13.048 | 9.3493 | 17.048 | 28.0961 | 41.1441 | 0
6.0901 | 9.045 | 8.0901 | 7.0901 | 10.1351 | 12.1351 | 9.045 | 16.1351 | 26.2702 | 38.4053 | 6.1001 | 9.045 | 8.0901 | 7.0901 | 10.1351 | 12.1351 | 9.045 | 16.1351 | 26.2702 | 38.4053 | 0
3.3738 | 7.6869 | 5.3738 | 4.3738 | 6.0607 | 8.0607 | 7.6869 | 12.0607 | 18.1215 | 26.1822 | 3.3838 | 7.6869 | 5.3738 | 4.3738 | 6.0607 | 8.0607 | 7.6869 | 12.0607 | 18.1215 | 26.1822 | 0
4.8105 | 8.4053 | 6.8105 | 5.8105 | 8.2158 | 10.2158 | 8.4053 | 14.2158 | 22.4316 | 32.6474 | 4.8205 | 8.4053 | 6.8105 | 5.8105 | 8.2158 | 10.2158 | 8.4053 | 14.2158 | 22.4316 | 32.6474 | 0
7.522 | 9.761 | 9.522 | 8.522 | 12.2829 | 14.2829 | 9.761 | 18.2829 | 30.5659 | 44.8488 | 7.532 | 9.761 | 9.522 | 8.522 | 12.2829 | 14.2829 | 9.761 | 18.2829 | 30.5659 | 44.8488 | 0
4.9713 | 8.4857 | 6.9713 | 5.9713 | 8.457 | 10.457 | 8.4857 | 14.457 | 22.9139 | 33.3709 | 4.9813 | 8.4857 | 6.9713 | 5.9713 | 8.457 | 10.457 | 8.4857 | 14.457 | 22.9139 | 33.3709 | 0
6.749 | 9.3745 | 8.749 | 7.749 | 11.1235 | 13.1235 | 9.3745 | 17.1235 | 28.247 | 41.3705 | 6.759 | 9.3745 | 8.749 | 7.749 | 11.1235 | 13.1235 | 9.3745 | 17.1235 | 28.247 | 41.3705 | 0
5.0742 | 8.5371 | 7.0742 | 6.0742 | 8.6114 | 10.6114 | 8.5371 | 14.6114 | 23.2227 | 33.8341 | 5.0842 | 8.5371 | 7.0742 | 6.0742 | 8.6114 | 10.6114 | 8.5371 | 14.6114 | 23.2227 | 33.8341 | 0
4.7646 | 8.3823 | 6.7646 | 5.7646 | 8.1468 | 10.1468 | 8.3823 | 14.1468 | 22.2937 | 32.4405 | 4.7746 | 8.3823 | 6.7646 | 5.7646 | 8.1468 | 10.1468 | 8.3823 | 14.1468 | 22.2937 | 32.4405 | 0
7.389 | 9.6945 | 9.389 | 8.389 | 12.0834 | 14.0834 | 9.6945 | 18.0834 | 30.1669 | 44.2503 | 7.399 | 9.6945 | 9.389 | 8.389 | 12.0834 | 14.0834 | 9.6945 | 18.0834 | 30.1669 | 44.2503 | 0
2.893 | 7.4465 | 4.893 | 3.893 | 5.3395 | 7.3395 | 7.4465 | 11.3395 | 16.679 | 24.0185 | 2.903 | 7.4465 | 4.893 | 3.893 | 5.3395 | 7.3395 | 7.4465 | 11.3395 | 16.679 | 24.0185 | 0
3.3349 | 7.6675 | 5.3349 | 4.3349 | 6.0024 | 8.0024 | 7.6675 | 12.0024 | 18.0048 | 26.0072 | 3.3449 | 7.6675 | 5.3349 | 4.3349 | 6.0024 | 8.0024 | 7.6675 | 12.0024 | 18.0048 | 26.0072 | 0
8.9925 | 10.4963 | 10.9925 | 9.9925 | 14.4888 | 16.4888 | 10.4963 | 20.4888 | 34.9775 | 51.4663 | 9.0025 | 10.4963 | 10.9925 | 9.9925 | 14.4888 | 16.4888 | 10.4963 | 20.4888 | 34.9775 | 51.4663 | 0
7.789 | 9.8945 | 9.789 | 8.789 | 12.6836 | 14.6836 | 9.8945 | 18.6836 | 31.3671 | 46.0507 | 7.799 | 9.8945 | 9.789 | 8.789 | 12.6836 | 14.6836 | 9.8945 | 18.6836 | 31.3671 | 46.0507 | 0
7.8333 | 9.9167 | 9.8333 | 8.8333 | 12.75 | 14.75 | 9.9167 | 18.75 | 31.4999 | 46.2499 | 7.8433 | 9.9167 | 9.8333 | 8.8333 | 12.75 | 14.75 | 9.9167 | 18.75 | 31.4999 | 46.2499 | 0
7.307 | 9.6535 | 9.307 | 8.307 | 11.9605 | 13.9605 | 9.6535 | 17.9605 | 29.9209 | 43.8814 | 7.317 | 9.6535 | 9.307 | 8.307 | 11.9605 | 13.9605 | 9.6535 | 17.9605 | 29.9209 | 43.8814 | 0
9.787 | 10.8935 | 11.787 | 10.787 | 15.6805 | 17.6805 | 10.8935 | 21.6805 | 37.361 | 55.0415 | 9.797 | 10.8935 | 11.787 | 10.787 | 15.6805 | 17.6805 | 10.8935 | 21.6805 | 37.361 | 55.0415 | 0
5.2045 | 8.6023 | 7.2045 | 6.2045 | 8.8068 | 10.8068 | 8.6023 | 14.8068 | 23.6135 | 34.4203 | 5.2145 | 8.6023 | 7.2045 | 6.2045 | 8.8068 | 10.8068 | 8.6023 | 14.8068 | 23.6135 | 34.4203 | 0
5.5481 | 8.7741 | 7.5481 | 6.5481 | 9.3222 | 11.3222 | 8.7741 | 15.3222 | 24.6444 | 35.9666 | 5.5581 | 8.7741 | 7.5481 | 6.5481 | 9.3222 | 11.3222 | 8.7741 | 15.3222 | 24.6444 | 35.9666 | 0
2.9819 | 7.491 | 4.9819 | 3.9819 | 5.4729 | 7.4729 | 7.491 | 11.4729 | 16.9458 | 24.4187 | 2.9919 | 7.491 | 4.9819 | 3.9819 | 5.4729 | 7.4729 | 7.491 | 11.4729 | 16.9458 | 24.4187 | 0
7.6554 | 9.8277 | 9.6554 | 8.6554 | 12.4831 | 14.4831 | 9.8277 | 18.4831 | 30.9661 | 45.4492 | 7.6654 | 9.8277 | 9.6554 | 8.6554 | 12.4831 | 14.4831 | 9.8277 | 18.4831 | 30.9661 | 45.4492 | 0
4.8098 | 8.4049 | 6.8098 | 5.8098 | 8.2147 | 10.2147 | 8.4049 | 14.2147 | 22.4294 | 32.6441 | 4.8198 | 8.4049 | 6.8098 | 5.8098 | 8.2147 | 10.2147 | 8.4049 | 14.2147 | 22.4294 | 32.6441 | 0
2.7341 | 7.3671 | 4.7341 | 3.7341 | 5.1012 | 7.1012 | 7.3671 | 11.1012 | 16.2023 | 23.3035 | 2.7441 | 7.3671 | 4.7341 | 3.7341 | 5.1012 | 7.1012 | 7.3671 | 11.1012 | 16.2023 | 23.3035 | 0
8.5249 | 10.2624 | 10.5249 | 9.5249 | 13.7873 | 15.7873 | 10.2624 | 19.7873 | 33.5746 | 49.3619 | 8.5349 | 10.2624 | 10.5249 | 9.5249 | 13.7873 | 15.7873 | 10.2624 | 19.7873 | 33.5746 | 49.3619 | 0
8.5457 | 10.2729 | 10.5457 | 9.5457 | 13.8186 | 15.8186 | 10.2729 | 19.8186 | 33.6371 | 49.4557 | 8.5557 | 10.2729 | 10.5457 | 9.5457 | 13.8186 | 15.8186 | 10.2729 | 19.8186 | 33.6371 | 49.4557 | 0
6.6239 | 9.3119 | 8.6239 | 7.6239 | 10.9358 | 12.9358 | 9.3119 | 16.9358 | 27.8716 | 40.8074 | 6.6339 | 9.3119 | 8.6239 | 7.6239 | 10.9358 | 12.9358 | 9.3119 | 16.9358 | 27.8716 | 40.8074 | 0
7.2382 | 9.6191 | 9.2382 | 8.2382 | 11.8573 | 13.8573 | 9.6191 | 17.8573 | 29.7147 | 43.572 | 7.2482 | 9.6191 | 9.2382 | 8.2382 | 11.8573 | 13.8573 | 9.6191 | 17.8573 | 29.7147 | 43.572 | 0
6.7582 | 9.3791 | 8.7582 | 7.7582 | 11.1373 | 13.1373 | 9.3791 | 17.1373 | 28.2746 | 41.4119 | 6.7682 | 9.3791 | 8.7582 | 7.7582 | 11.1373 | 13.1373 | 9.3791 | 17.1373 | 28.2746 | 41.4119 | 0
5.4894 | 8.7447 | 7.4894 | 6.4894 | 9.2341 | 11.2341 | 8.7447 | 15.2341 | 24.4682 | 35.7022 | 5.4994 | 8.7447 | 7.4894 | 6.4894 | 9.2341 | 11.2341 | 8.7447 | 15.2341 | 24.4682 | 35.7022 | 0
5.7659 | 8.883 | 7.7659 | 6.7659 | 9.6489 | 11.6489 | 8.883 | 15.6489 | 25.2977 | 36.9466 | 5.7759 | 8.883 | 7.7659 | 6.7659 | 9.6489 | 11.6489 | 8.883 | 15.6489 | 25.2977 | 36.9466 | 0
5.7573 | 8.8786 | 7.7573 | 6.7573 | 9.6359 | 11.6359 | 8.8786 | 15.6359 | 25.2719 | 36.9078 | 5.7673 | 8.8786 | 7.7573 | 6.7573 | 9.6359 | 11.6359 | 8.8786 | 15.6359 | 25.2719 | 36.9078 | 0
4.4028 | 8.2014 | 6.4028 | 5.4028 | 7.6042 | 9.6042 | 8.2014 | 13.6042 | 21.2083 | 30.8125 | 4.4128 | 8.2014 | 6.4028 | 5.4028 | 7.6042 | 9.6042 | 8.2014 | 13.6042 | 21.2083 | 30.8125 | 0
5.7536 | 8.8768 | 7.7536 | 6.7536 | 9.6304 | 11.6304 | 8.8768 | 15.6304 | 25.2608 | 36.8911 | 5.7636 | 8.8768 | 7.7536 | 6.7536 | 9.6304 | 11.6304 | 8.8768 | 15.6304 | 25.2608 | 36.8911 | 0
5.0303 | 8.5151 | 7.0303 | 6.0303 | 8.5454 | 10.5454 | 8.5151 | 14.5454 | 23.0908 | 33.6361 | 5.0403 | 8.5151 | 7.0303 | 6.0303 | 8.5454 | 10.5454 | 8.5151 | 14.5454 | 23.0908 | 33.6361 | 0
3.0131 | 7.5066 | 5.0131 | 4.0131 | 5.5197 | 7.5197 | 7.5066 | 11.5197 | 17.0393 | 24.559 | 3.0231 | 7.5066 | 5.0131 | 4.0131 | 5.5197 | 7.5197 | 7.5066 | 11.5197 | 17.0393 | 24.559 | 0
2.4946 | 7.2473 | 4.4946 | 3.4946 | 4.7419 | 6.7419 | 7.2473 | 10.7419 | 15.4838 | 22.2257 | 2.5046 | 7.2473 | 4.4946 | 3.4946 | 4.7419 | 6.7419 | 7.2473 | 10.7419 | 15.4838 | 22.2257 | 0
3.8321 | 7.9161 | 5.8321 | 4.8321 | 6.7482 | 8.7482 | 7.9161 | 12.7482 | 19.4963 | 28.2445 | 3.8421 | 7.9161 | 5.8321 | 4.8321 | 6.7482 | 8.7482 | 7.9161 | 12.7482 | 19.4963 | 28.2445 | 0
3.881 | 7.9405 | 5.881 | 4.881 | 6.8215 | 8.8215 | 7.9405 | 12.8215 | 19.6431 | 28.4646 | 3.891 | 7.9405 | 5.881 | 4.881 | 6.8215 | 8.8215 | 7.9405 | 12.8215 | 19.6431 | 28.4646 | 0
6.8478 | 9.4239 | 8.8478 | 7.8478 | 11.2716 | 13.2716 | 9.4239 | 17.2716 | 28.5433 | 41.8149 | 6.8578 | 9.4239 | 8.8478 | 7.8478 | 11.2716 | 13.2716 | 9.4239 | 17.2716 | 28.5433 | 41.8149 | 0
6.8117 | 9.4059 | 8.8117 | 7.8117 | 11.2176 | 13.2176 | 9.4059 | 17.2176 | 28.4352 | 41.6529 | 6.8217 | 9.4059 | 8.8117 | 7.8117 | 11.2176 | 13.2176 | 9.4059 | 17.2176 | 28.4352 | 41.6529 | 0
2.5649 | 7.2825 | 4.5649 | 3.5649 | 4.8474 | 6.8474 | 7.2825 | 10.8474 | 15.6947 | 22.5421 | 2.5749 | 7.2825 | 4.5649 | 3.5649 | 4.8474 | 6.8474 | 7.2825 | 10.8474 | 15.6947 | 22.5421 | 0
4.502 | 8.251 | 6.502 | 5.502 | 7.7531 | 9.7531 | 8.251 | 13.7531 | 21.5061 | 31.2592 | 4.512 | 8.251 | 6.502 | 5.502 | 7.7531 | 9.7531 | 8.251 | 13.7531 | 21.5061 | 31.2592 | 0
8.0192 | 10.0096 | 10.0192 | 9.0192 | 13.0288 | 15.0288 | 10.0096 | 19.0288 | 32.0575 | 47.0863 | 8.0292 | 10.0096 | 10.0192 | 9.0192 | 13.0288 | 15.0288 | 10.0096 | 19.0288 | 32.0575 | 47.0863 | 0
5.5992 | 8.7996 | 7.5992 | 6.5992 | 9.3987 | 11.3987 | 8.7996 | 15.3987 | 24.7975 | 36.1962 | 5.6092 | 8.7996 | 7.5992 | 6.5992 | 9.3987 | 11.3987 | 8.7996 | 15.3987 | 24.7975 | 36.1962 | 0
3.538 | 7.769 | 5.538 | 4.538 | 6.3071 | 8.3071 | 7.769 | 12.3071 | 18.6141 | 26.9212 | 3.548 | 7.769 | 5.538 | 4.538 | 6.3071 | 8.3071 | 7.769 | 12.3071 | 18.6141 | 26.9212 | 0
4.1922 | 8.0961 | 6.1922 | 5.1922 | 7.2882 | 9.2882 | 8.0961 | 13.2882 | 20.5765 | 29.8647 | 4.2022 | 8.0961 | 6.1922 | 5.1922 | 7.2882 | 9.2882 | 8.0961 | 13.2882 | 20.5765 | 29.8647 | 0
8.0617 | 10.0308 | 10.0617 | 9.0617 | 13.0925 | 15.0925 | 10.0308 | 19.0925 | 32.185 | 47.2775 | 8.0717 | 10.0308 | 10.0617 | 9.0617 | 13.0925 | 15.0925 | 10.0308 | 19.0925 | 32.185 | 47.2775 | 0
7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 7.4989 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 0
11.8438 | 11.9219 | 13.8438 | 12.8438 | 18.7656 | 20.7656 | 11.9219 | 24.7656 | 43.5313 | 64.2969 | 11.8538 | 11.9219 | 13.8438 | 12.8438 | 18.7656 | 20.7656 | 11.9219 | 24.7656 | 43.5313 | 64.2969 | 0
6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 6.3414 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 0
8.8082 | 10.4041 | 10.8082 | 9.8082 | 14.2124 | 16.2124 | 10.4041 | 20.2124 | 34.4247 | 50.6371 | 8.8182 | 10.4041 | 10.8082 | 9.8082 | 14.2124 | 16.2124 | 10.4041 | 20.2124 | 34.4247 | 50.6371 | 0
7.6294 | 9.8147 | 9.6294 | 8.6294 | 12.4441 | 14.4441 | 9.8147 | 18.4441 | 30.8883 | 45.3324 | 7.6394 | 9.8147 | 9.6294 | 8.6294 | 12.4441 | 14.4441 | 9.8147 | 18.4441 | 30.8883 | 45.3324 | 0
6.2816 | 9.1408 | 8.2816 | 7.2816 | 10.4224 | 12.4224 | 9.1408 | 16.4224 | 26.8448 | 39.2672 | 6.2916 | 9.1408 | 8.2816 | 7.2816 | 10.4224 | 12.4224 | 9.1408 | 16.4224 | 26.8448 | 39.2672 | 0
2.9948 | 7.4974 | 4.9948 | 3.9948 | 5.4922 | 7.4922 | 7.4974 | 11.4922 | 16.9843 | 24.4765 | 3.0048 | 7.4974 | 4.9948 | 3.9948 | 5.4922 | 7.4922 | 7.4974 | 11.4922 | 16.9843 | 24.4765 | 0
7.6577 | 9.8289 | 9.6577 | 8.6577 | 12.4866 | 14.4866 | 9.8289 | 18.4866 | 30.9732 | 45.4598 | 7.6677 | 9.8289 | 9.6577 | 8.6577 | 12.4866 | 14.4866 | 9.8289 | 18.4866 | 30.9732 | 45.4598 | 0
5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 5.1073 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 0
6.3502 | 9.1751 | 8.3502 | 7.3502 | 10.5253 | 12.5253 | 9.1751 | 16.5253 | 27.0507 | 39.576 | 6.3602 | 9.1751 | 8.3502 | 7.3502 | 10.5253 | 12.5253 | 9.1751 | 16.5253 | 27.0507 | 39.576 | 0
8.2841 | 10.1421 | 10.2841 | 9.2841 | 13.4262 | 15.4262 | 10.1421 | 19.4262 | 32.8524 | 48.2786 | 8.2941 | 10.1421 | 10.2841 | 9.2841 | 13.4262 | 15.4262 | 10.1421 | 19.4262 | 32.8524 | 48.2786 | 0
7.4494 | 9.7247 | 9.4494 | 8.4494 | 12.1741 | 14.1741 | 9.7247 | 18.1741 | 30.3481 | 44.5222 | 7.4594 | 9.7247 | 9.4494 | 8.4494 | 12.1741 | 14.1741 | 9.7247 | 18.1741 | 30.3481 | 44.5222 | 0
5.769 | 8.8845 | 7.769 | 6.769 | 9.6535 | 11.6535 | 8.8845 | 15.6535 | 25.307 | 36.9605 | 5.779 | 8.8845 | 7.769 | 6.769 | 9.6535 | 11.6535 | 8.8845 | 15.6535 | 25.307 | 36.9605 | 0
5.8084 | 8.9042 | 7.8084 | 6.8084 | 9.7126 | 11.7126 | 8.9042 | 15.7126 | 25.4252 | 37.1377 | 5.8184 | 8.9042 | 7.8084 | 6.8084 | 9.7126 | 11.7126 | 8.9042 | 15.7126 | 25.4252 | 37.1377 | 0
4.3983 | 8.1992 | 6.3983 | 5.3983 | 7.5975 | 9.5975 | 8.1992 | 13.5975 | 21.195 | 30.7925 | 4.4083 | 8.1992 | 6.3983 | 5.3983 | 7.5975 | 9.5975 | 8.1992 | 13.5975 | 21.195 | 30.7925 | 0
4.0729 | 8.0365 | 6.0729 | 5.0729 | 7.1094 | 9.1094 | 8.0365 | 13.1094 | 20.2188 | 29.3281 | 4.0829 | 8.0365 | 6.0729 | 5.0729 | 7.1094 | 9.1094 | 8.0365 | 13.1094 | 20.2188 | 29.3281 | 0
6.5512 | 9.2756 | 8.5512 | 7.5512 | 10.8268 | 12.8268 | 9.2756 | 16.8268 | 27.6536 | 40.4803 | 6.5612 | 9.2756 | 8.5512 | 7.5512 | 10.8268 | 12.8268 | 9.2756 | 16.8268 | 27.6536 | 40.4803 | 0
3.2266 | 7.6133 | 5.2266 | 4.2266 | 5.8399 | 7.8399 | 7.6133 | 11.8399 | 17.6798 | 25.5197 | 3.2366 | 7.6133 | 5.2266 | 4.2266 | 5.8399 | 7.8399 | 7.6133 | 11.8399 | 17.6798 | 25.5197 | 0
6.4914 | 9.2457 | 8.4914 | 7.4914 | 10.737 | 12.737 | 9.2457 | 16.737 | 27.4741 | 40.2111 | 6.5014 | 9.2457 | 8.4914 | 7.4914 | 10.737 | 12.737 | 9.2457 | 16.737 | 27.4741 | 40.2111 | 0
7.4177 | 9.7089 | 9.4177 | 8.4177 | 12.1266 | 14.1266 | 9.7089 | 18.1266 | 30.2532 | 44.3798 | 7.4277 | 9.7089 | 9.4177 | 8.4177 | 12.1266 | 14.1266 | 9.7089 | 18.1266 | 30.2532 | 44.3798 | 0
3.4213 | 7.7106 | 5.4213 | 4.4213 | 6.1319 | 8.1319 | 7.7106 | 12.1319 | 18.2638 | 26.3957 | 3.4313 | 7.7106 | 5.4213 | 4.4213 | 6.1319 | 8.1319 | 7.7106 | 12.1319 | 18.2638 | 26.3957 | 0
4.6599 | 8.3299 | 6.6599 | 5.6599 | 7.9898 | 9.9898 | 8.3299 | 13.9898 | 21.9797 | 31.9695 | 4.6699 | 8.3299 | 6.6599 | 5.6599 | 7.9898 | 9.9898 | 8.3299 | 13.9898 | 21.9797 | 31.9695 | 0
7.9283 | 9.9641 | 9.9283 | 8.9283 | 12.8924 | 14.8924 | 9.9641 | 18.8924 | 31.7849 | 46.6773 | 7.9383 | 9.9641 | 9.9283 | 8.9283 | 12.8924 | 14.8924 | 9.9641 | 18.8924 | 31.7849 | 46.6773 | 0
8.1195 | 10.0598 | 10.1195 | 9.1195 | 13.1793 | 15.1793 | 10.0598 | 19.1793 | 32.3586 | 47.5378 | 8.1295 | 10.0598 | 10.1195 | 9.1195 | 13.1793 | 15.1793 | 10.0598 | 19.1793 | 32.3586 | 47.5378 | 0
5.1511 | 8.5755 | 7.1511 | 6.1511 | 8.7266 | 10.7266 | 8.5755 | 14.7266 | 23.4532 | 34.1798 | 5.1611 | 8.5755 | 7.1511 | 6.1511 | 8.7266 | 10.7266 | 8.5755 | 14.7266 | 23.4532 | 34.1798 | 0
4.3661 | 8.183 | 6.3661 | 5.3661 | 7.5491 | 9.5491 | 8.183 | 13.5491 | 21.0983 | 30.6474 | 4.3761 | 8.183 | 6.3661 | 5.3661 | 7.5491 | 9.5491 | 8.183 | 13.5491 | 21.0983 | 30.6474 | 0
4.8403 | 8.4202 | 6.8403 | 5.8403 | 8.2605 | 10.2605 | 8.4202 | 14.2605 | 22.521 | 32.7815 | 4.8503 | 8.4202 | 6.8403 | 5.8403 | 8.2605 | 10.2605 | 8.4202 | 14.2605 | 22.521 | 32.7815 | 0
6.6155 | 9.3078 | 8.6155 | 7.6155 | 10.9233 | 12.9233 | 9.3078 | 16.9233 | 27.8466 | 40.7699 | 6.6255 | 9.3078 | 8.6155 | 7.6155 | 10.9233 | 12.9233 | 9.3078 | 16.9233 | 27.8466 | 40.7699 | 0
6.1813 | 9.0907 | 8.1813 | 7.1813 | 10.272 | 12.272 | 9.0907 | 16.272 | 26.544 | 38.8159 | 6.1913 | 9.0907 | 8.1813 | 7.1813 | 10.272 | 12.272 | 9.0907 | 16.272 | 26.544 | 38.8159 | 0
6.6324 | 9.3162 | 8.6324 | 7.6324 | 10.9486 | 12.9486 | 9.3162 | 16.9486 | 27.8972 | 40.8458 | 6.6424 | 9.3162 | 8.6324 | 7.6324 | 10.9486 | 12.9486 | 9.3162 | 16.9486 | 27.8972 | 40.8458 | 0
5.7216 | 8.8608 | 7.7216 | 6.7216 | 9.5825 | 11.5825 | 8.8608 | 15.5825 | 25.1649 | 36.7474 | 5.7316 | 8.8608 | 7.7216 | 6.7216 | 9.5825 | 11.5825 | 8.8608 | 15.5825 | 25.1649 | 36.7474 | 0
5.8658 | 8.9329 | 7.8658 | 6.8658 | 9.7987 | 11.7987 | 8.9329 | 15.7987 | 25.5974 | 37.3961 | 5.8758 | 8.9329 | 7.8658 | 6.8658 | 9.7987 | 11.7987 | 8.9329 | 15.7987 | 25.5974 | 37.3961 | 0
4.2094 | 8.1047 | 6.2094 | 5.2094 | 7.314 | 9.314 | 8.1047 | 13.314 | 20.6281 | 29.9421 | 4.2194 | 8.1047 | 6.2094 | 5.2094 | 7.314 | 9.314 | 8.1047 | 13.314 | 20.6281 | 29.9421 | 0
5.2214 | 8.6107 | 7.2214 | 6.2214 | 8.8321 | 10.8321 | 8.6107 | 14.8321 | 23.6641 | 34.4962 | 5.2314 | 8.6107 | 7.2214 | 6.2214 | 8.8321 | 10.8321 | 8.6107 | 14.8321 | 23.6641 | 34.4962 | 0
5.3992 | 8.6996 | 7.3992 | 6.3992 | 9.0988 | 11.0988 | 8.6996 | 15.0988 | 24.1976 | 35.2965 | 5.4092 | 8.6996 | 7.3992 | 6.3992 | 9.0988 | 11.0988 | 8.6996 | 15.0988 | 24.1976 | 35.2965 | 0
9.2618 | 10.6309 | 11.2618 | 10.2618 | 14.8927 | 16.8927 | 10.6309 | 20.8927 | 35.7855 | 52.6782 | 9.2718 | 10.6309 | 11.2618 | 10.2618 | 14.8927 | 16.8927 | 10.6309 | 20.8927 | 35.7855 | 52.6782 | 0
2.5164 | 7.2582 | 4.5164 | 3.5164 | 4.7746 | 6.7746 | 7.2582 | 10.7746 | 15.5493 | 22.3239 | 2.5264 | 7.2582 | 4.5164 | 3.5164 | 4.7746 | 6.7746 | 7.2582 | 10.7746 | 15.5493 | 22.3239 | 0
6.053 | 9.0265 | 8.053 | 7.053 | 10.0795 | 12.0795 | 9.0265 | 16.0795 | 26.1591 | 38.2386 | 6.063 | 9.0265 | 8.053 | 7.053 | 10.0795 | 12.0795 | 9.0265 | 16.0795 | 26.1591 | 38.2386 | 0
11.0086 | 11.5043 | 13.0086 | 12.0086 | 17.5129 | 19.5129 | 11.5043 | 23.5129 | 41.0259 | 60.5388 | 11.0186 | 11.5043 | 13.0086 | 12.0086 | 17.5129 | 19.5129 | 11.5043 | 23.5129 | 41.0259 | 60.5388 | 0
9.7368 | 10.8684 | 11.7368 | 10.7368 | 15.6052 | 17.6052 | 10.8684 | 21.6052 | 37.2103 | 54.8155 | 9.7468 | 10.8684 | 11.7368 | 10.7368 | 15.6052 | 17.6052 | 10.8684 | 21.6052 | 37.2103 | 54.8155 | 0
9.4739 | 10.7369 | 11.4739 | 10.4739 | 15.2108 | 17.2108 | 10.7369 | 21.2108 | 36.4216 | 53.6323 | 9.4839 | 10.7369 | 11.4739 | 10.4739 | 15.2108 | 17.2108 | 10.7369 | 21.2108 | 36.4216 | 53.6323 | 0
4.0971 | 8.0486 | 6.0971 | 5.0971 | 7.1457 | 9.1457 | 8.0486 | 13.1457 | 20.2913 | 29.437 | 4.1071 | 8.0486 | 6.0971 | 5.0971 | 7.1457 | 9.1457 | 8.0486 | 13.1457 | 20.2913 | 29.437 | 0
7.1106 | 9.5553 | 9.1106 | 8.1106 | 11.6659 | 13.6659 | 9.5553 | 17.6659 | 29.3318 | 42.9977 | 7.1206 | 9.5553 | 9.1106 | 8.1106 | 11.6659 | 13.6659 | 9.5553 | 17.6659 | 29.3318 | 42.9977 | 0
8.668 | 10.334 | 10.668 | 9.668 | 14.0021 | 16.0021 | 10.334 | 20.0021 | 34.0041 | 50.0062 | 8.678 | 10.334 | 10.668 | 9.668 | 14.0021 | 16.0021 | 10.334 | 20.0021 | 34.0041 | 50.0062 | 0
5.0877 | 8.5438 | 7.0877 | 6.0877 | 8.6315 | 10.6315 | 8.5438 | 14.6315 | 23.263 | 33.8945 | 5.0977 | 8.5438 | 7.0877 | 6.0877 | 8.6315 | 10.6315 | 8.5438 | 14.6315 | 23.263 | 33.8945 | 0
3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 3.9827 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 0
6.5588 | 9.2794 | 8.5588 | 7.5588 | 10.8382 | 12.8382 | 9.2794 | 16.8382 | 27.6765 | 40.5147 | 6.5688 | 9.2794 | 8.5588 | 7.5588 | 10.8382 | 12.8382 | 9.2794 | 16.8382 | 27.6765 | 40.5147 | 0
5.3003 | 8.6502 | 7.3003 | 6.3003 | 8.9505 | 10.9505 | 8.6502 | 14.9505 | 23.901 | 34.8515 | 5.3103 | 8.6502 | 7.3003 | 6.3003 | 8.9505 | 10.9505 | 8.6502 | 14.9505 | 23.901 | 34.8515 | 0
5.3086 | 8.6543 | 7.3086 | 6.3086 | 8.9629 | 10.9629 | 8.6543 | 14.9629 | 23.9259 | 34.8888 | 5.3186 | 8.6543 | 7.3086 | 6.3086 | 8.9629 | 10.9629 | 8.6543 | 14.9629 | 23.9259 | 34.8888 | 0
4.5764 | 8.2882 | 6.5764 | 5.5764 | 7.8645 | 9.8645 | 8.2882 | 13.8645 | 21.7291 | 31.5936 | 4.5864 | 8.2882 | 6.5764 | 5.5764 | 7.8645 | 9.8645 | 8.2882 | 13.8645 | 21.7291 | 31.5936 | 0
5.9923 | 8.9961 | 7.9923 | 6.9923 | 9.9884 | 11.9884 | 8.9961 | 15.9884 | 25.9768 | 37.9652 | 6.0023 | 8.9961 | 7.9923 | 6.9923 | 9.9884 | 11.9884 | 8.9961 | 15.9884 | 25.9768 | 37.9652 | 0
2.2553 | 7.1277 | 4.2553 | 3.2553 | 4.383 | 6.383 | 7.1277 | 10.383 | 14.766 | 21.1489 | 2.2653 | 7.1277 | 4.2553 | 3.2553 | 4.383 | 6.383 | 7.1277 | 10.383 | 14.766 | 21.1489 | 0
3.77 | 7.885 | 5.77 | 4.77 | 6.6549 | 8.6549 | 7.885 | 12.6549 | 19.3099 | 27.9648 | 3.78 | 7.885 | 5.77 | 4.77 | 6.6549 | 8.6549 | 7.885 | 12.6549 | 19.3099 | 27.9648 | 0
5.0845 | 8.5422 | 7.0845 | 6.0845 | 8.6267 | 10.6267 | 8.5422 | 14.6267 | 23.2534 | 33.88 | 5.0945 | 8.5422 | 7.0845 | 6.0845 | 8.6267 | 10.6267 | 8.5422 | 14.6267 | 23.2534 | 33.88 | 0
10.4131 | 11.2066 | 12.4131 | 11.4131 | 16.6197 | 18.6197 | 11.2066 | 22.6197 | 39.2394 | 57.8591 | 10.4231 | 11.2066 | 12.4131 | 11.4131 | 16.6197 | 18.6197 | 11.2066 | 22.6197 | 39.2394 | 57.8591 | 0
6.5663 | 9.2831 | 8.5663 | 7.5663 | 10.8494 | 12.8494 | 9.2831 | 16.8494 | 27.6989 | 40.5483 | 6.5763 | 9.2831 | 8.5663 | 7.5663 | 10.8494 | 12.8494 | 9.2831 | 16.8494 | 27.6989 | 40.5483 | 0
5.6487 | 8.8243 | 7.6487 | 6.6487 | 9.473 | 11.473 | 8.8243 | 15.473 | 24.946 | 36.4191 | 5.6587 | 8.8243 | 7.6487 | 6.6487 | 9.473 | 11.473 | 8.8243 | 15.473 | 24.946 | 36.4191 | 0
7.5932 | 9.7966 | 9.5932 | 8.5932 | 12.3899 | 14.3899 | 9.7966 | 18.3899 | 30.7797 | 45.1696 | 7.6032 | 9.7966 | 9.5932 | 8.5932 | 12.3899 | 14.3899 | 9.7966 | 18.3899 | 30.7797 | 45.1696 | 0
3.3026 | 7.6513 | 5.3026 | 4.3026 | 5.9539 | 7.9539 | 7.6513 | 11.9539 | 17.9078 | 25.8617 | 3.3126 | 7.6513 | 5.3026 | 4.3026 | 5.9539 | 7.9539 | 7.6513 | 11.9539 | 17.9078 | 25.8617 | 0
3.76 | 7.88 | 5.76 | 4.76 | 6.6399 | 8.6399 | 7.88 | 12.6399 | 19.2799 | 27.9198 | 3.77 | 7.88 | 5.76 | 4.76 | 6.6399 | 8.6399 | 7.88 | 12.6399 | 19.2799 | 27.9198 | 0
5.8466 | 8.9233 | 7.8466 | 6.8466 | 9.7699 | 11.7699 | 8.9233 | 15.7699 | 25.5399 | 37.3098 | 5.8566 | 8.9233 | 7.8466 | 6.8466 | 9.7699 | 11.7699 | 8.9233 | 15.7699 | 25.5399 | 37.3098 | 0
6.6787 | 9.3394 | 8.6787 | 7.6787 | 11.0181 | 13.0181 | 9.3394 | 17.0181 | 28.0362 | 41.0543 | 6.6887 | 9.3394 | 8.6787 | 7.6787 | 11.0181 | 13.0181 | 9.3394 | 17.0181 | 28.0362 | 41.0543 | 0
5.4037 | 8.7018 | 7.4037 | 6.4037 | 9.1055 | 11.1055 | 8.7018 | 15.1055 | 24.2111 | 35.3166 | 5.4137 | 8.7018 | 7.4037 | 6.4037 | 9.1055 | 11.1055 | 8.7018 | 15.1055 | 24.2111 | 35.3166 | 0
6.474 | 9.237 | 8.474 | 7.474 | 10.711 | 12.711 | 9.237 | 16.711 | 27.4221 | 40.1331 | 6.484 | 9.237 | 8.474 | 7.474 | 10.711 | 12.711 | 9.237 | 16.711 | 27.4221 | 40.1331 | 0
6.1767 | 9.0884 | 8.1767 | 7.1767 | 10.2651 | 12.2651 | 9.0884 | 16.2651 | 26.5301 | 38.7952 | 6.1867 | 9.0884 | 8.1767 | 7.1767 | 10.2651 | 12.2651 | 9.0884 | 16.2651 | 26.5301 | 38.7952 | 0
6.604 | 9.302 | 8.604 | 7.604 | 10.906 | 12.906 | 9.302 | 16.906 | 27.812 | 40.7179 | 6.614 | 9.302 | 8.604 | 7.604 | 10.906 | 12.906 | 9.302 | 16.906 | 27.812 | 40.7179 | 0
4.67 | 8.335 | 6.67 | 5.67 | 8.005 | 10.005 | 8.335 | 14.005 | 22.0101 | 32.0151 | 4.68 | 8.335 | 6.67 | 5.67 | 8.005 | 10.005 | 8.335 | 14.005 | 22.0101 | 32.0151 | 0
5.3308 | 8.6654 | 7.3308 | 6.3308 | 8.9962 | 10.9962 | 8.6654 | 14.9962 | 23.9925 | 34.9887 | 5.3408 | 8.6654 | 7.3308 | 6.3308 | 8.9962 | 10.9962 | 8.6654 | 14.9962 | 23.9925 | 34.9887 | 0
5.7182 | 8.8591 | 7.7182 | 6.7182 | 9.5774 | 11.5774 | 8.8591 | 15.5774 | 25.1547 | 36.7321 | 5.7282 | 8.8591 | 7.7182 | 6.7182 | 9.5774 | 11.5774 | 8.8591 | 15.5774 | 25.1547 | 36.7321 | 0
1.3905 | 6.6952 | 3.3905 | 2.3905 | 3.0857 | 5.0857 | 6.6952 | 9.0857 | 12.1714 | 17.2571 | 1.4005 | 6.6952 | 3.3905 | 2.3905 | 3.0857 | 5.0857 | 6.6952 | 9.0857 | 12.1714 | 17.2571 | 0
4.6854 | 8.3427 | 6.6854 | 5.6854 | 8.0282 | 10.0282 | 8.3427 | 14.0282 | 22.0563 | 32.0845 | 4.6954 | 8.3427 | 6.6854 | 5.6854 | 8.0282 | 10.0282 | 8.3427 | 14.0282 | 22.0563 | 32.0845 | 0
4.5016 | 8.2508 | 6.5016 | 5.5016 | 7.7525 | 9.7525 | 8.2508 | 13.7525 | 21.5049 | 31.2574 | 4.5116 | 8.2508 | 6.5016 | 5.5016 | 7.7525 | 9.7525 | 8.2508 | 13.7525 | 21.5049 | 31.2574 | 0
3.0906 | 7.5453 | 5.0906 | 4.0906 | 5.6359 | 7.6359 | 7.5453 | 11.6359 | 17.2719 | 24.9078 | 3.1006 | 7.5453 | 5.0906 | 4.0906 | 5.6359 | 7.6359 | 7.5453 | 11.6359 | 17.2719 | 24.9078 | 0
3.6427 | 7.8213 | 5.6427 | 4.6427 | 6.464 | 8.464 | 7.8213 | 12.464 | 18.928 | 27.392 | 3.6527 | 7.8213 | 5.6427 | 4.6427 | 6.464 | 8.464 | 7.8213 | 12.464 | 18.928 | 27.392 | 0
3.7734 | 7.8867 | 5.7734 | 4.7734 | 6.66 | 8.66 | 7.8867 | 12.66 | 19.3201 | 27.9801 | 3.7834 | 7.8867 | 5.7734 | 4.7734 | 6.66 | 8.66 | 7.8867 | 12.66 | 19.3201 | 27.9801 | 0
5.5801 | 8.79 | 7.5801 | 6.5801 | 9.3701 | 11.3701 | 8.79 | 15.3701 | 24.7403 | 36.1104 | 5.5901 | 8.79 | 7.5801 | 6.5801 | 9.3701 | 11.3701 | 8.79 | 15.3701 | 24.7403 | 36.1104 | 0
7.3028 | 9.6514 | 9.3028 | 8.3028 | 11.9542 | 13.9542 | 9.6514 | 17.9542 | 29.9084 | 43.8626 | 7.3128 | 9.6514 | 9.3028 | 8.3028 | 11.9542 | 13.9542 | 9.6514 | 17.9542 | 29.9084 | 43.8626 | 0
4.8107 | 8.4054 | 6.8107 | 5.8107 | 8.2161 | 10.2161 | 8.4054 | 14.2161 | 22.4321 | 32.6482 | 4.8207 | 8.4054 | 6.8107 | 5.8107 | 8.2161 | 10.2161 | 8.4054 | 14.2161 | 22.4321 | 32.6482 | 0
6.0516 | 9.0258 | 8.0516 | 7.0516 | 10.0775 | 12.0775 | 9.0258 | 16.0775 | 26.1549 | 38.2324 | 6.0616 | 9.0258 | 8.0516 | 7.0516 | 10.0775 | 12.0775 | 9.0258 | 16.0775 | 26.1549 | 38.2324 | 0
7.0705 | 9.5352 | 9.0705 | 8.0705 | 11.6057 | 13.6057 | 9.5352 | 17.6057 | 29.2114 | 42.8171 | 7.0805 | 9.5352 | 9.0705 | 8.0705 | 11.6057 | 13.6057 | 9.5352 | 17.6057 | 29.2114 | 42.8171 | 0
7.2568 | 9.6284 | 9.2568 | 8.2568 | 11.8852 | 13.8852 | 9.6284 | 17.8852 | 29.7704 | 43.6556 | 7.2668 | 9.6284 | 9.2568 | 8.2568 | 11.8852 | 13.8852 | 9.6284 | 17.8852 | 29.7704 | 43.6556 | 0
5.5195 | 8.7598 | 7.5195 | 6.5195 | 9.2793 | 11.2793 | 8.7598 | 15.2793 | 24.5586 | 35.8378 | 5.5295 | 8.7598 | 7.5195 | 6.5195 | 9.2793 | 11.2793 | 8.7598 | 15.2793 | 24.5586 | 35.8378 | 0
7.7236 | 9.8618 | 9.7236 | 8.7236 | 12.5854 | 14.5854 | 9.8618 | 18.5854 | 31.1707 | 45.7561 | 7.7336 | 9.8618 | 9.7236 | 8.7236 | 12.5854 | 14.5854 | 9.8618 | 18.5854 | 31.1707 | 45.7561 | 0
7.4454 | 9.7227 | 9.4454 | 8.4454 | 12.1681 | 14.1681 | 9.7227 | 18.1681 | 30.3362 | 44.5043 | 7.4554 | 9.7227 | 9.4454 | 8.4454 | 12.1681 | 14.1681 | 9.7227 | 18.1681 | 30.3362 | 44.5043 | 0
7.2098 | 9.6049 | 9.2098 | 8.2098 | 11.8147 | 13.8147 | 9.6049 | 17.8147 | 29.6294 | 43.4441 | 7.2198 | 9.6049 | 9.2098 | 8.2098 | 11.8147 | 13.8147 | 9.6049 | 17.8147 | 29.6294 | 43.4441 | 0
8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 8.0577 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 0
5.3983 | 8.6991 | 7.3983 | 6.3983 | 9.0974 | 11.0974 | 8.6991 | 15.0974 | 24.1948 | 35.2922 | 5.4083 | 8.6991 | 7.3983 | 6.3983 | 9.0974 | 11.0974 | 8.6991 | 15.0974 | 24.1948 | 35.2922 | 0
8.1214 | 10.0607 | 10.1214 | 9.1214 | 13.1821 | 15.1821 | 10.0607 | 19.1821 | 32.3642 | 47.5463 | 8.1314 | 10.0607 | 10.1214 | 9.1214 | 13.1821 | 15.1821 | 10.0607 | 19.1821 | 32.3642 | 47.5463 | 0
5.6079 | 8.8039 | 7.6079 | 6.6079 | 9.4118 | 11.4118 | 8.8039 | 15.4118 | 24.8237 | 36.2355 | 5.6179 | 8.8039 | 7.6079 | 6.6079 | 9.4118 | 11.4118 | 8.8039 | 15.4118 | 24.8237 | 36.2355 | 0
6.4616 | 9.2308 | 8.4616 | 7.4616 | 10.6924 | 12.6924 | 9.2308 | 16.6924 | 27.3848 | 40.0772 | 6.4716 | 9.2308 | 8.4616 | 7.4616 | 10.6924 | 12.6924 | 9.2308 | 16.6924 | 27.3848 | 40.0772 | 0
5.8819 | 8.9409 | 7.8819 | 6.8819 | 9.8228 | 11.8228 | 8.9409 | 15.8228 | 25.6457 | 37.4685 | 5.8919 | 8.9409 | 7.8819 | 6.8819 | 9.8228 | 11.8228 | 8.9409 | 15.8228 | 25.6457 | 37.4685 | 0
3.8915 | 7.9457 | 5.8915 | 4.8915 | 6.8372 | 8.8372 | 7.9457 | 12.8372 | 19.6744 | 28.5115 | 3.9015 | 7.9457 | 5.8915 | 4.8915 | 6.8372 | 8.8372 | 7.9457 | 12.8372 | 19.6744 | 28.5115 | 0
3.9971 | 7.9985 | 5.9971 | 4.9971 | 6.9956 | 8.9956 | 7.9985 | 12.9956 | 19.9912 | 28.9868 | 4.0071 | 7.9985 | 5.9971 | 4.9971 | 6.9956 | 8.9956 | 7.9985 | 12.9956 | 19.9912 | 28.9868 | 0
6.3642 | 9.1821 | 8.3642 | 7.3642 | 10.5463 | 12.5463 | 9.1821 | 16.5463 | 27.0927 | 39.639 | 6.3742 | 9.1821 | 8.3642 | 7.3642 | 10.5463 | 12.5463 | 9.1821 | 16.5463 | 27.0927 | 39.639 | 0
9.0628 | 10.5314 | 11.0628 | 10.0628 | 14.5941 | 16.5941 | 10.5314 | 20.5941 | 35.1883 | 51.7824 | 9.0728 | 10.5314 | 11.0628 | 10.0628 | 14.5941 | 16.5941 | 10.5314 | 20.5941 | 35.1883 | 51.7824 | 0
6.7215 | 9.3608 | 8.7215 | 7.7215 | 11.0823 | 13.0823 | 9.3608 | 17.0823 | 28.1645 | 41.2468 | 6.7315 | 9.3608 | 8.7215 | 7.7215 | 11.0823 | 13.0823 | 9.3608 | 17.0823 | 28.1645 | 41.2468 | 0
7.5347 | 9.7673 | 9.5347 | 8.5347 | 12.302 | 14.302 | 9.7673 | 18.302 | 30.604 | 44.906 | 7.5447 | 9.7673 | 9.5347 | 8.5347 | 12.302 | 14.302 | 9.7673 | 18.302 | 30.604 | 44.906 | 0
4.2203 | 8.1102 | 6.2203 | 5.2203 | 7.3305 | 9.3305 | 8.1102 | 13.3305 | 20.6609 | 29.9914 | 4.2303 | 8.1102 | 6.2203 | 5.2203 | 7.3305 | 9.3305 | 8.1102 | 13.3305 | 20.6609 | 29.9914 | 0
4.9198 | 8.4599 | 6.9198 | 5.9198 | 8.3797 | 10.3797 | 8.4599 | 14.3797 | 22.7594 | 33.1391 | 4.9298 | 8.4599 | 6.9198 | 5.9198 | 8.3797 | 10.3797 | 8.4599 | 14.3797 | 22.7594 | 33.1391 | 0
3.252 | 7.626 | 5.252 | 4.252 | 5.878 | 7.878 | 7.626 | 11.878 | 17.7559 | 25.6339 | 3.262 | 7.626 | 5.252 | 4.252 | 5.878 | 7.878 | 7.626 | 11.878 | 17.7559 | 25.6339 | 0
6.2071 | 9.1036 | 8.2071 | 7.2071 | 10.3107 | 12.3107 | 9.1036 | 16.3107 | 26.6214 | 38.9322 | 6.2171 | 9.1036 | 8.2071 | 7.2071 | 10.3107 | 12.3107 | 9.1036 | 16.3107 | 26.6214 | 38.9322 | 0
6.9816 | 9.4908 | 8.9816 | 7.9816 | 11.4725 | 13.4725 | 9.4908 | 17.4725 | 28.9449 | 42.4174 | 6.9916 | 9.4908 | 8.9816 | 7.9816 | 11.4725 | 13.4725 | 9.4908 | 17.4725 | 28.9449 | 42.4174 | 0
4.3537 | 8.1768 | 6.3537 | 5.3537 | 7.5305 | 9.5305 | 8.1768 | 13.5305 | 21.061 | 30.5915 | 4.3637 | 8.1768 | 6.3537 | 5.3537 | 7.5305 | 9.5305 | 8.1768 | 13.5305 | 21.061 | 30.5915 | 0
7.4024 | 9.7012 | 9.4024 | 8.4024 | 12.1036 | 14.1036 | 9.7012 | 18.1036 | 30.2073 | 44.3109 | 7.4124 | 9.7012 | 9.4024 | 8.4024 | 12.1036 | 14.1036 | 9.7012 | 18.1036 | 30.2073 | 44.3109 | 0
5.2403 | 8.6202 | 7.2403 | 6.2403 | 8.8605 | 10.8605 | 8.6202 | 14.8605 | 23.7209 | 34.5814 | 5.2503 | 8.6202 | 7.2403 | 6.2403 | 8.8605 | 10.8605 | 8.6202 | 14.8605 | 23.7209 | 34.5814 | 0
6.5781 | 9.289 | 8.5781 | 7.5781 | 10.8671 | 12.8671 | 9.289 | 16.8671 | 27.7343 | 40.6014 | 6.5881 | 9.289 | 8.5781 | 7.5781 | 10.8671 | 12.8671 | 9.289 | 16.8671 | 27.7343 | 40.6014 | 0
7.6429 | 9.8215 | 9.6429 | 8.6429 | 12.4644 | 14.4644 | 9.8215 | 18.4644 | 30.9287 | 45.3931 | 7.6529 | 9.8215 | 9.6429 | 8.6429 | 12.4644 | 14.4644 | 9.8215 | 18.4644 | 30.9287 | 45.3931 | 0
6.3829 | 9.1915 | 8.3829 | 7.3829 | 10.5744 | 12.5744 | 9.1915 | 16.5744 | 27.1487 | 39.7231 | 6.3929 | 9.1915 | 8.3829 | 7.3829 | 10.5744 | 12.5744 | 9.1915 | 16.5744 | 27.1487 | 39.7231 | 0
3.4405 | 7.7202 | 5.4405 | 4.4405 | 6.1607 | 8.1607 | 7.7202 | 12.1607 | 18.3214 | 26.4821 | 3.4505 | 7.7202 | 5.4405 | 4.4405 | 6.1607 | 8.1607 | 7.7202 | 12.1607 | 18.3214 | 26.4821 | 0
8.5773 | 10.2887 | 10.5773 | 9.5773 | 13.866 | 15.866 | 10.2887 | 19.866 | 33.732 | 49.598 | 8.5873 | 10.2887 | 10.5773 | 9.5773 | 13.866 | 15.866 | 10.2887 | 19.866 | 33.732 | 49.598 | 0
8.9551 | 10.4775 | 10.9551 | 9.9551 | 14.4326 | 16.4326 | 10.4775 | 20.4326 | 34.8653 | 51.2979 | 8.9651 | 10.4775 | 10.9551 | 9.9551 | 14.4326 | 16.4326 | 10.4775 | 20.4326 | 34.8653 | 51.2979 | 0
5.4187 | 8.7094 | 7.4187 | 6.4187 | 9.1281 | 11.1281 | 8.7094 | 15.1281 | 24.2561 | 35.3842 | 5.4287 | 8.7094 | 7.4187 | 6.4187 | 9.1281 | 11.1281 | 8.7094 | 15.1281 | 24.2561 | 35.3842 | 0
5.3886 | 8.6943 | 7.3886 | 6.3886 | 9.083 | 11.083 | 8.6943 | 15.083 | 24.1659 | 35.2489 | 5.3986 | 8.6943 | 7.3886 | 6.3886 | 9.083 | 11.083 | 8.6943 | 15.083 | 24.1659 | 35.2489 | 0
8.0894 | 10.0447 | 10.0894 | 9.0894 | 13.1342 | 15.1342 | 10.0447 | 19.1342 | 32.2683 | 47.4025 | 8.0994 | 10.0447 | 10.0894 | 9.0894 | 13.1342 | 15.1342 | 10.0447 | 19.1342 | 32.2683 | 47.4025 | 0
9.5481 | 10.7741 | 11.5481 | 10.5481 | 15.3222 | 17.3222 | 10.7741 | 21.3222 | 36.6444 | 53.9666 | 9.5581 | 10.7741 | 11.5481 | 10.5481 | 15.3222 | 17.3222 | 10.7741 | 21.3222 | 36.6444 | 53.9666 | 0
8.3839 | 10.1919 | 10.3839 | 9.3839 | 13.5758 | 15.5758 | 10.1919 | 19.5758 | 33.1517 | 48.7275 | 8.3939 | 10.1919 | 10.3839 | 9.3839 | 13.5758 | 15.5758 | 10.1919 | 19.5758 | 33.1517 | 48.7275 | 0
5.3671 | 8.6836 | 7.3671 | 6.3671 | 9.0507 | 11.0507 | 8.6836 | 15.0507 | 24.1014 | 35.1521 | 5.3771 | 8.6836 | 7.3671 | 6.3671 | 9.0507 | 11.0507 | 8.6836 | 15.0507 | 24.1014 | 35.1521 | 0
6.4787 | 9.2394 | 8.4787 | 7.4787 | 10.7181 | 12.7181 | 9.2394 | 16.7181 | 27.4362 | 40.1544 | 6.4887 | 9.2394 | 8.4787 | 7.4787 | 10.7181 | 12.7181 | 9.2394 | 16.7181 | 27.4362 | 40.1544 | 0
9.3042 | 10.6521 | 11.3042 | 10.3042 | 14.9563 | 16.9563 | 10.6521 | 20.9563 | 35.9126 | 52.8689 | 9.3142 | 10.6521 | 11.3042 | 10.3042 | 14.9563 | 16.9563 | 10.6521 | 20.9563 | 35.9126 | 52.8689 | 0
2.544 | 7.272 | 4.544 | 3.544 | 4.816 | 6.816 | 7.272 | 10.816 | 15.632 | 22.448 | 2.554 | 7.272 | 4.544 | 3.544 | 4.816 | 6.816 | 7.272 | 10.816 | 15.632 | 22.448 | 0
4.3068 | 8.1534 | 6.3068 | 5.3068 | 7.4603 | 9.4603 | 8.1534 | 13.4603 | 20.9205 | 30.3808 | 4.3168 | 8.1534 | 6.3068 | 5.3068 | 7.4603 | 9.4603 | 8.1534 | 13.4603 | 20.9205 | 30.3808 | 0
4.3765 | 8.1883 | 6.3765 | 5.3765 | 7.5648 | 9.5648 | 8.1883 | 13.5648 | 21.1296 | 30.6944 | 4.3865 | 8.1883 | 6.3765 | 5.3765 | 7.5648 | 9.5648 | 8.1883 | 13.5648 | 21.1296 | 30.6944 | 0
8.9067 | 10.4534 | 10.9067 | 9.9067 | 14.3601 | 16.3601 | 10.4534 | 20.3601 | 34.7202 | 51.0803 | 8.9167 | 10.4534 | 10.9067 | 9.9067 | 14.3601 | 16.3601 | 10.4534 | 20.3601 | 34.7202 | 51.0803 | 0
5.8313 | 8.9156 | 7.8313 | 6.8313 | 9.7469 | 11.7469 | 8.9156 | 15.7469 | 25.4938 | 37.2407 | 5.8413 | 8.9156 | 7.8313 | 6.8313 | 9.7469 | 11.7469 | 8.9156 | 15.7469 | 25.4938 | 37.2407 | 0
5.7318 | 8.8659 | 7.7318 | 6.7318 | 9.5978 | 11.5978 | 8.8659 | 15.5978 | 25.1955 | 36.7933 | 5.7418 | 8.8659 | 7.7318 | 6.7318 | 9.5978 | 11.5978 | 8.8659 | 15.5978 | 25.1955 | 36.7933 | 0
4.0139 | 8.007 | 6.0139 | 5.0139 | 7.0209 | 9.0209 | 8.007 | 13.0209 | 20.0417 | 29.0626 | 4.0239 | 8.007 | 6.0139 | 5.0139 | 7.0209 | 9.0209 | 8.007 | 13.0209 | 20.0417 | 29.0626 | 0
4.3425 | 8.1712 | 6.3425 | 5.3425 | 7.5137 | 9.5137 | 8.1712 | 13.5137 | 21.0274 | 30.5411 | 4.3525 | 8.1712 | 6.3425 | 5.3425 | 7.5137 | 9.5137 | 8.1712 | 13.5137 | 21.0274 | 30.5411 | 0
6.3885 | 9.1943 | 8.3885 | 7.3885 | 10.5828 | 12.5828 | 9.1943 | 16.5828 | 27.1656 | 39.7483 | 6.3985 | 9.1943 | 8.3885 | 7.3885 | 10.5828 | 12.5828 | 9.1943 | 16.5828 | 27.1656 | 39.7483 | 0
4.828 | 8.414 | 6.828 | 5.828 | 8.242 | 10.242 | 8.414 | 14.242 | 22.484 | 32.726 | 4.838 | 8.414 | 6.828 | 5.828 | 8.242 | 10.242 | 8.414 | 14.242 | 22.484 | 32.726 | 0
4.4034 | 8.2017 | 6.4034 | 5.4034 | 7.6051 | 9.6051 | 8.2017 | 13.6051 | 21.2102 | 30.8153 | 4.4134 | 8.2017 | 6.4034 | 5.4034 | 7.6051 | 9.6051 | 8.2017 | 13.6051 | 21.2102 | 30.8153 | 0
4.8238 | 8.4119 | 6.8238 | 5.8238 | 8.2357 | 10.2357 | 8.4119 | 14.2357 | 22.4715 | 32.7072 | 4.8338 | 8.4119 | 6.8238 | 5.8238 | 8.2357 | 10.2357 | 8.4119 | 14.2357 | 22.4715 | 32.7072 | 0
2.2571 | 7.1285 | 4.2571 | 3.2571 | 4.3856 | 6.3856 | 7.1285 | 10.3856 | 14.7713 | 21.1569 | 2.2671 | 7.1285 | 4.2571 | 3.2571 | 4.3856 | 6.3856 | 7.1285 | 10.3856 | 14.7713 | 21.1569 | 0
7.5318 | 9.7659 | 9.5318 | 8.5318 | 12.2977 | 14.2977 | 9.7659 | 18.2977 | 30.5954 | 44.8931 | 7.5418 | 9.7659 | 9.5318 | 8.5318 | 12.2977 | 14.2977 | 9.7659 | 18.2977 | 30.5954 | 44.8931 | 0
5.7824 | 8.8912 | 7.7824 | 6.7824 | 9.6736 | 11.6736 | 8.8912 | 15.6736 | 25.3472 | 37.0208 | 5.7924 | 8.8912 | 7.7824 | 6.7824 | 9.6736 | 11.6736 | 8.8912 | 15.6736 | 25.3472 | 37.0208 | 0
5.2454 | 8.6227 | 7.2454 | 6.2454 | 8.8681 | 10.8681 | 8.6227 | 14.8681 | 23.7362 | 34.6043 | 5.2554 | 8.6227 | 7.2454 | 6.2454 | 8.8681 | 10.8681 | 8.6227 | 14.8681 | 23.7362 | 34.6043 | 0
4.8561 | 8.428 | 6.8561 | 5.8561 | 8.2841 | 10.2841 | 8.428 | 14.2841 | 22.5682 | 32.8522 | 4.8661 | 8.428 | 6.8561 | 5.8561 | 8.2841 | 10.2841 | 8.428 | 14.2841 | 22.5682 | 32.8522 | 0
8.4147 | 10.2073 | 10.4147 | 9.4147 | 13.622 | 15.622 | 10.2073 | 19.622 | 33.244 | 48.866 | 8.4247 | 10.2073 | 10.4147 | 9.4147 | 13.622 | 15.622 | 10.2073 | 19.622 | 33.244 | 48.866 | 0
6.6838 | 9.3419 | 8.6838 | 7.6838 | 11.0256 | 13.0256 | 9.3419 | 17.0256 | 28.0513 | 41.0769 | 6.6938 | 9.3419 | 8.6838 | 7.6838 | 11.0256 | 13.0256 | 9.3419 | 17.0256 | 28.0513 | 41.0769 | 0
0.96635 | 6.4832 | 2.9663 | 1.9663 | 2.4495 | 4.4495 | 6.4832 | 8.4495 | 10.899 | 15.3486 | 0.97635 | 6.4832 | 2.9663 | 1.9663 | 2.4495 | 4.4495 | 6.4832 | 8.4495 | 10.899 | 15.3486 | 0
7.0703 | 9.5351 | 9.0703 | 8.0703 | 11.6054 | 13.6054 | 9.5351 | 17.6054 | 29.2109 | 42.8163 | 7.0803 | 9.5351 | 9.0703 | 8.0703 | 11.6054 | 13.6054 | 9.5351 | 17.6054 | 29.2109 | 42.8163 | 0
7.017 | 9.5085 | 9.017 | 8.017 | 11.5255 | 13.5255 | 9.5085 | 17.5255 | 29.051 | 42.5765 | 7.027 | 9.5085 | 9.017 | 8.017 | 11.5255 | 13.5255 | 9.5085 | 17.5255 | 29.051 | 42.5765 | 0
5.4393 | 8.7196 | 7.4393 | 6.4393 | 9.1589 | 11.1589 | 8.7196 | 15.1589 | 24.3178 | 35.4767 | 5.4493 | 8.7196 | 7.4393 | 6.4393 | 9.1589 | 11.1589 | 8.7196 | 15.1589 | 24.3178 | 35.4767 | 0
2.5841 | 7.2921 | 4.5841 | 3.5841 | 4.8762 | 6.8762 | 7.2921 | 10.8762 | 15.7524 | 22.6286 | 2.5941 | 7.2921 | 4.5841 | 3.5841 | 4.8762 | 6.8762 | 7.2921 | 10.8762 | 15.7524 | 22.6286 | 0
3.8108 | 7.9054 | 5.8108 | 4.8108 | 6.7162 | 8.7162 | 7.9054 | 12.7162 | 19.4324 | 28.1486 | 3.8208 | 7.9054 | 5.8108 | 4.8108 | 6.7162 | 8.7162 | 7.9054 | 12.7162 | 19.4324 | 28.1486 | 0
5.3143 | 8.6572 | 7.3143 | 6.3143 | 8.9715 | 10.9715 | 8.6572 | 14.9715 | 23.9429 | 34.9144 | 5.3243 | 8.6572 | 7.3143 | 6.3143 | 8.9715 | 10.9715 | 8.6572 | 14.9715 | 23.9429 | 34.9144 | 0
6.6577 | 9.3288 | 8.6577 | 7.6577 | 10.9865 | 12.9865 | 9.3288 | 16.9865 | 27.9731 | 40.9596 | 6.6677 | 9.3288 | 8.6577 | 7.6577 | 10.9865 | 12.9865 | 9.3288 | 16.9865 | 27.9731 | 40.9596 | 0
3.0098 | 7.5049 | 5.0098 | 4.0098 | 5.5147 | 7.5147 | 7.5049 | 11.5147 | 17.0295 | 24.5442 | 3.0198 | 7.5049 | 5.0098 | 4.0098 | 5.5147 | 7.5147 | 7.5049 | 11.5147 | 17.0295 | 24.5442 | 0
5.1527 | 8.5764 | 7.1527 | 6.1527 | 8.7291 | 10.7291 | 8.5764 | 14.7291 | 23.4582 | 34.1873 | 5.1627 | 8.5764 | 7.1527 | 6.1527 | 8.7291 | 10.7291 | 8.5764 | 14.7291 | 23.4582 | 34.1873 | 0
5.8825 | 8.9413 | 7.8825 | 6.8825 | 9.8238 | 11.8238 | 8.9413 | 15.8238 | 25.6475 | 37.4713 | 5.8925 | 8.9413 | 7.8825 | 6.8825 | 9.8238 | 11.8238 | 8.9413 | 15.8238 | 25.6475 | 37.4713 | 0
6.6117 | 9.3058 | 8.6117 | 7.6117 | 10.9175 | 12.9175 | 9.3058 | 16.9175 | 27.835 | 40.7525 | 6.6217 | 9.3058 | 8.6117 | 7.6117 | 10.9175 | 12.9175 | 9.3058 | 16.9175 | 27.835 | 40.7525 | 0
7.5536 | 9.7768 | 9.5536 | 8.5536 | 12.3304 | 14.3304 | 9.7768 | 18.3304 | 30.6609 | 44.9913 | 7.5636 | 9.7768 | 9.5536 | 8.5536 | 12.3304 | 14.3304 | 9.7768 | 18.3304 | 30.6609 | 44.9913 | 0
3.9811 | 7.9905 | 5.9811 | 4.9811 | 6.9716 | 8.9716 | 7.9905 | 12.9716 | 19.9432 | 28.9148 | 3.9911 | 7.9905 | 5.9811 | 4.9811 | 6.9716 | 8.9716 | 7.9905 | 12.9716 | 19.9432 | 28.9148 | 0
2.7565 | 7.3783 | 4.7565 | 3.7565 | 5.1348 | 7.1348 | 7.3783 | 11.1348 | 16.2696 | 23.4044 | 2.7665 | 7.3783 | 4.7565 | 3.7565 | 5.1348 | 7.1348 | 7.3783 | 11.1348 | 16.2696 | 23.4044 | 0
1.279 | 6.6395 | 3.279 | 2.279 | 2.9185 | 4.9185 | 6.6395 | 8.9185 | 11.837 | 16.7555 | 1.289 | 6.6395 | 3.279 | 2.279 | 2.9185 | 4.9185 | 6.6395 | 8.9185 | 11.837 | 16.7555 | 0
6.3987 | 9.1993 | 8.3987 | 7.3987 | 10.598 | 12.598 | 9.1993 | 16.598 | 27.196 | 39.794 | 6.4087 | 9.1993 | 8.3987 | 7.3987 | 10.598 | 12.598 | 9.1993 | 16.598 | 27.196 | 39.794 | 0
8.8962 | 10.4481 | 10.8962 | 9.8962 | 14.3443 | 16.3443 | 10.4481 | 20.3443 | 34.6886 | 51.033 | 8.9062 | 10.4481 | 10.8962 | 9.8962 | 14.3443 | 16.3443 | 10.4481 | 20.3443 | 34.6886 | 51.033 | 0
3.2532 | 7.6266 | 5.2532 | 4.2532 | 5.8797 | 7.8797 | 7.6266 | 11.8797 | 17.7595 | 25.6392 | 3.2632 | 7.6266 | 5.2532 | 4.2532 | 5.8797 | 7.8797 | 7.6266 | 11.8797 | 17.7595 | 25.6392 | 0
5.4748 | 8.7374 | 7.4748 | 6.4748 | 9.2122 | 11.2122 | 8.7374 | 15.2122 | 24.4245 | 35.6367 | 5.4848 | 8.7374 | 7.4748 | 6.4748 | 9.2122 | 11.2122 | 8.7374 | 15.2122 | 24.4245 | 35.6367 | 0
5.6701 | 8.8351 | 7.6701 | 6.6701 | 9.5052 | 11.5052 | 8.8351 | 15.5052 | 25.0103 | 36.5155 | 5.6801 | 8.8351 | 7.6701 | 6.6701 | 9.5052 | 11.5052 | 8.8351 | 15.5052 | 25.0103 | 36.5155 | 0
8.5124 | 10.2562 | 10.5124 | 9.5124 | 13.7685 | 15.7685 | 10.2562 | 19.7685 | 33.5371 | 49.3056 | 8.5224 | 10.2562 | 10.5124 | 9.5124 | 13.7685 | 15.7685 | 10.2562 | 19.7685 | 33.5371 | 49.3056 | 0
7.7278 | 9.8639 | 9.7278 | 8.7278 | 12.5917 | 14.5917 | 9.8639 | 18.5917 | 31.1834 | 45.7751 | 7.7378 | 9.8639 | 9.7278 | 8.7278 | 12.5917 | 14.5917 | 9.8639 | 18.5917 | 31.1834 | 45.7751 | 0
6.6958 | 9.3479 | 8.6958 | 7.6958 | 11.0437 | 13.0437 | 9.3479 | 17.0437 | 28.0873 | 41.131 | 6.7058 | 9.3479 | 8.6958 | 7.6958 | 11.0437 | 13.0437 | 9.3479 | 17.0437 | 28.0873 | 41.131 | 0
6.6747 | 9.3373 | 8.6747 | 7.6747 | 11.012 | 13.012 | 9.3373 | 17.012 | 28.024 | 41.036 | 6.6847 | 9.3373 | 8.6747 | 7.6747 | 11.012 | 13.012 | 9.3373 | 17.012 | 28.024 | 41.036 | 0
4.1136 | 8.0568 | 6.1136 | 5.1136 | 7.1705 | 9.1705 | 8.0568 | 13.1705 | 20.3409 | 29.5114 | 4.1236 | 8.0568 | 6.1136 | 5.1136 | 7.1705 | 9.1705 | 8.0568 | 13.1705 | 20.3409 | 29.5114 | 0
6.0322 | 9.0161 | 8.0322 | 7.0322 | 10.0483 | 12.0483 | 9.0161 | 16.0483 | 26.0966 | 38.1449 | 6.0422 | 9.0161 | 8.0322 | 7.0322 | 10.0483 | 12.0483 | 9.0161 | 16.0483 | 26.0966 | 38.1449 | 0
6.0533 | 9.0267 | 8.0533 | 7.0533 | 10.08 | 12.08 | 9.0267 | 16.08 | 26.16 | 38.24 | 6.0633 | 9.0267 | 8.0533 | 7.0533 | 10.08 | 12.08 | 9.0267 | 16.08 | 26.16 | 38.24 | 0
5.3099 | 8.655 | 7.3099 | 6.3099 | 8.9649 | 10.9649 | 8.655 | 14.9649 | 23.9298 | 34.8946 | 5.3199 | 8.655 | 7.3099 | 6.3099 | 8.9649 | 10.9649 | 8.655 | 14.9649 | 23.9298 | 34.8946 | 0
2.783 | 7.3915 | 4.783 | 3.783 | 5.1746 | 7.1746 | 7.3915 | 11.1746 | 16.3491 | 23.5237 | 2.793 | 7.3915 | 4.783 | 3.783 | 5.1746 | 7.1746 | 7.3915 | 11.1746 | 16.3491 | 23.5237 | 0
4.1082 | 8.0541 | 6.1082 | 5.1082 | 7.1622 | 9.1622 | 8.0541 | 13.1622 | 20.3245 | 29.4867 | 4.1182 | 8.0541 | 6.1082 | 5.1082 | 7.1622 | 9.1622 | 8.0541 | 13.1622 | 20.3245 | 29.4867 | 0
9.1167 | 10.5584 | 11.1167 | 10.1167 | 14.6751 | 16.6751 | 10.5584 | 20.6751 | 35.3502 | 52.0254 | 9.1267 | 10.5584 | 11.1167 | 10.1167 | 14.6751 | 16.6751 | 10.5584 | 20.6751 | 35.3502 | 52.0254 | 0
7.2546 | 9.6273 | 9.2546 | 8.2546 | 11.8819 | 13.8819 | 9.6273 | 17.8819 | 29.7637 | 43.6456 | 7.2646 | 9.6273 | 9.2546 | 8.2546 | 11.8819 | 13.8819 | 9.6273 | 17.8819 | 29.7637 | 43.6456 | 0
3.9195 | 7.9598 | 5.9195 | 4.9195 | 6.8793 | 8.8793 | 7.9598 | 12.8793 | 19.7585 | 28.6378 | 3.9295 | 7.9598 | 5.9195 | 4.9195 | 6.8793 | 8.8793 | 7.9598 | 12.8793 | 19.7585 | 28.6378 | 0
7.2151 | 9.6076 | 9.2151 | 8.2151 | 11.8227 | 13.8227 | 9.6076 | 17.8227 | 29.6454 | 43.4681 | 7.2251 | 9.6076 | 9.2151 | 8.2151 | 11.8227 | 13.8227 | 9.6076 | 17.8227 | 29.6454 | 43.4681 | 0
5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 5.4043 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 0
4.1806 | 8.0903 | 6.1806 | 5.1806 | 7.2709 | 9.2709 | 8.0903 | 13.2709 | 20.5419 | 29.8128 | 4.1906 | 8.0903 | 6.1806 | 5.1806 | 7.2709 | 9.2709 | 8.0903 | 13.2709 | 20.5419 | 29.8128 | 0
4.4304 | 8.2152 | 6.4304 | 5.4304 | 7.6456 | 9.6456 | 8.2152 | 13.6456 | 21.2912 | 30.9368 | 4.4404 | 8.2152 | 6.4304 | 5.4304 | 7.6456 | 9.6456 | 8.2152 | 13.6456 | 21.2912 | 30.9368 | 0
4.0583 | 8.0291 | 6.0583 | 5.0583 | 7.0874 | 9.0874 | 8.0291 | 13.0874 | 20.1748 | 29.2622 | 4.0683 | 8.0291 | 6.0583 | 5.0583 | 7.0874 | 9.0874 | 8.0291 | 13.0874 | 20.1748 | 29.2622 | 0
6.3386 | 9.1693 | 8.3386 | 7.3386 | 10.5079 | 12.5079 | 9.1693 | 16.5079 | 27.0158 | 39.5236 | 6.3486 | 9.1693 | 8.3386 | 7.3386 | 10.5079 | 12.5079 | 9.1693 | 16.5079 | 27.0158 | 39.5236 | 0
8.3318 | 10.1659 | 10.3318 | 9.3318 | 13.4977 | 15.4977 | 10.1659 | 19.4977 | 32.9953 | 48.493 | 8.3418 | 10.1659 | 10.3318 | 9.3318 | 13.4977 | 15.4977 | 10.1659 | 19.4977 | 32.9953 | 48.493 | 0
3.4866 | 7.7433 | 5.4866 | 4.4866 | 6.23 | 8.23 | 7.7433 | 12.23 | 18.4599 | 26.6899 | 3.4966 | 7.7433 | 5.4866 | 4.4866 | 6.23 | 8.23 | 7.7433 | 12.23 | 18.4599 | 26.6899 | 0
5.145 | 8.5725 | 7.145 | 6.145 | 8.7175 | 10.7175 | 8.5725 | 14.7175 | 23.4351 | 34.1526 | 5.155 | 8.5725 | 7.145 | 6.145 | 8.7175 | 10.7175 | 8.5725 | 14.7175 | 23.4351 | 34.1526 | 0
4.7066 | 8.3533 | 6.7066 | 5.7066 | 8.06 | 10.06 | 8.3533 | 14.06 | 22.1199 | 32.1799 | 4.7166 | 8.3533 | 6.7066 | 5.7066 | 8.06 | 10.06 | 8.3533 | 14.06 | 22.1199 | 32.1799 | 0
3.6298 | 7.8149 | 5.6298 | 4.6298 | 6.4446 | 8.4446 | 7.8149 | 12.4446 | 18.8893 | 27.3339 | 3.6398 | 7.8149 | 5.6298 | 4.6298 | 6.4446 | 8.4446 | 7.8149 | 12.4446 | 18.8893 | 27.3339 | 0
7.1394 | 9.5697 | 9.1394 | 8.1394 | 11.7092 | 13.7092 | 9.5697 | 17.7092 | 29.4183 | 43.1275 | 7.1494 | 9.5697 | 9.1394 | 8.1394 | 11.7092 | 13.7092 | 9.5697 | 17.7092 | 29.4183 | 43.1275 | 0
6.9539 | 9.477 | 8.9539 | 7.9539 | 11.4309 | 13.4309 | 9.477 | 17.4309 | 28.8618 | 42.2928 | 6.9639 | 9.477 | 8.9539 | 7.9539 | 11.4309 | 13.4309 | 9.477 | 17.4309 | 28.8618 | 42.2928 | 0
3.8824 | 7.9412 | 5.8824 | 4.8824 | 6.8235 | 8.8235 | 7.9412 | 12.8235 | 19.6471 | 28.4706 | 3.8924 | 7.9412 | 5.8824 | 4.8824 | 6.8235 | 8.8235 | 7.9412 | 12.8235 | 19.6471 | 28.4706 | 0
4.5081 | 8.2541 | 6.5081 | 5.5081 | 7.7622 | 9.7622 | 8.2541 | 13.7622 | 21.5243 | 31.2865 | 4.5181 | 8.2541 | 6.5081 | 5.5081 | 7.7622 | 9.7622 | 8.2541 | 13.7622 | 21.5243 | 31.2865 | 0
5.4401 | 8.72 | 7.4401 | 6.4401 | 9.1601 | 11.1601 | 8.72 | 15.1601 | 24.3202 | 35.4803 | 5.4501 | 8.72 | 7.4401 | 6.4401 | 9.1601 | 11.1601 | 8.72 | 15.1601 | 24.3202 | 35.4803 | 0
7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 7.2312 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 0
6.3068 | 9.1534 | 8.3068 | 7.3068 | 10.4602 | 12.4602 | 9.1534 | 16.4602 | 26.9204 | 39.3807 | 6.3168 | 9.1534 | 8.3068 | 7.3068 | 10.4602 | 12.4602 | 9.1534 | 16.4602 | 26.9204 | 39.3807 | 0
2.4541 | 7.227 | 4.4541 | 3.4541 | 4.6811 | 6.6811 | 7.227 | 10.6811 | 15.3622 | 22.0434 | 2.4641 | 7.227 | 4.4541 | 3.4541 | 4.6811 | 6.6811 | 7.227 | 10.6811 | 15.3622 | 22.0434 | 0
6.616 | 9.308 | 8.616 | 7.616 | 10.924 | 12.924 | 9.308 | 16.924 | 27.848 | 40.772 | 6.626 | 9.308 | 8.616 | 7.616 | 10.924 | 12.924 | 9.308 | 16.924 | 27.848 | 40.772 | 0
6.1816 | 9.0908 | 8.1816 | 7.1816 | 10.2724 | 12.2724 | 9.0908 | 16.2724 | 26.5449 | 38.8173 | 6.1916 | 9.0908 | 8.1816 | 7.1816 | 10.2724 | 12.2724 | 9.0908 | 16.2724 | 26.5449 | 38.8173 | 0
4.1669 | 8.0835 | 6.1669 | 5.1669 | 7.2504 | 9.2504 | 8.0835 | 13.2504 | 20.5008 | 29.7512 | 4.1769 | 8.0835 | 6.1669 | 5.1669 | 7.2504 | 9.2504 | 8.0835 | 13.2504 | 20.5008 | 29.7512 | 0
5.6994 | 8.8497 | 7.6994 | 6.6994 | 9.5491 | 11.5491 | 8.8497 | 15.5491 | 25.0981 | 36.6472 | 5.7094 | 8.8497 | 7.6994 | 6.6994 | 9.5491 | 11.5491 | 8.8497 | 15.5491 | 25.0981 | 36.6472 | 0
6.0425 | 9.0212 | 8.0425 | 7.0425 | 10.0637 | 12.0637 | 9.0212 | 16.0637 | 26.1274 | 38.1911 | 6.0525 | 9.0212 | 8.0425 | 7.0425 | 10.0637 | 12.0637 | 9.0212 | 16.0637 | 26.1274 | 38.1911 | 0
10.3015 | 11.1508 | 12.3015 | 11.3015 | 16.4523 | 18.4523 | 11.1508 | 22.4523 | 38.9045 | 57.3568 | 10.3115 | 11.1508 | 12.3015 | 11.3015 | 16.4523 | 18.4523 | 11.1508 | 22.4523 | 38.9045 | 57.3568 | 0
5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 5.1073 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 0
2.9544 | 7.4772 | 4.9544 | 3.9544 | 5.4316 | 7.4316 | 7.4772 | 11.4316 | 16.8633 | 24.2949 | 2.9644 | 7.4772 | 4.9544 | 3.9544 | 5.4316 | 7.4316 | 7.4772 | 11.4316 | 16.8633 | 24.2949 | 0
8.086 | 10.043 | 10.086 | 9.086 | 13.129 | 15.129 | 10.043 | 19.129 | 32.258 | 47.3871 | 8.096 | 10.043 | 10.086 | 9.086 | 13.129 | 15.129 | 10.043 | 19.129 | 32.258 | 47.3871 | 0
3.5671 | 7.7836 | 5.5671 | 4.5671 | 6.3507 | 8.3507 | 7.7836 | 12.3507 | 18.7014 | 27.0522 | 3.5771 | 7.7836 | 5.5671 | 4.5671 | 6.3507 | 8.3507 | 7.7836 | 12.3507 | 18.7014 | 27.0522 | 0
3.1336 | 7.5668 | 5.1336 | 4.1336 | 5.7004 | 7.7004 | 7.5668 | 11.7004 | 17.4008 | 25.1012 | 3.1436 | 7.5668 | 5.1336 | 4.1336 | 5.7004 | 7.7004 | 7.5668 | 11.7004 | 17.4008 | 25.1012 | 0
6.5277 | 9.2639 | 8.5277 | 7.5277 | 10.7916 | 12.7916 | 9.2639 | 16.7916 | 27.5831 | 40.3747 | 6.5377 | 9.2639 | 8.5277 | 7.5277 | 10.7916 | 12.7916 | 9.2639 | 16.7916 | 27.5831 | 40.3747 | 0
4.9065 | 8.4533 | 6.9065 | 5.9065 | 8.3598 | 10.3598 | 8.4533 | 14.3598 | 22.7195 | 33.0793 | 4.9165 | 8.4533 | 6.9065 | 5.9065 | 8.3598 | 10.3598 | 8.4533 | 14.3598 | 22.7195 | 33.0793 | 0
5.0165 | 8.5082 | 7.0165 | 6.0165 | 8.5247 | 10.5247 | 8.5082 | 14.5247 | 23.0494 | 33.5741 | 5.0265 | 8.5082 | 7.0165 | 6.0165 | 8.5247 | 10.5247 | 8.5082 | 14.5247 | 23.0494 | 33.5741 | 0
7.6593 | 9.8296 | 9.6593 | 8.6593 | 12.4889 | 14.4889 | 9.8296 | 18.4889 | 30.9778 | 45.4666 | 7.6693 | 9.8296 | 9.6593 | 8.6593 | 12.4889 | 14.4889 | 9.8296 | 18.4889 | 30.9778 | 45.4666 | 0
7.9067 | 9.9534 | 9.9067 | 8.9067 | 12.8601 | 14.8601 | 9.9534 | 18.8601 | 31.7202 | 46.5803 | 7.9167 | 9.9534 | 9.9067 | 8.9067 | 12.8601 | 14.8601 | 9.9534 | 18.8601 | 31.7202 | 46.5803 | 0
5.5669 | 8.7835 | 7.5669 | 6.5669 | 9.3504 | 11.3504 | 8.7835 | 15.3504 | 24.7008 | 36.0513 | 5.5769 | 8.7835 | 7.5669 | 6.5669 | 9.3504 | 11.3504 | 8.7835 | 15.3504 | 24.7008 | 36.0513 | 0
6.8194 | 9.4097 | 8.8194 | 7.8194 | 11.2291 | 13.2291 | 9.4097 | 17.2291 | 28.4582 | 41.6873 | 6.8294 | 9.4097 | 8.8194 | 7.8194 | 11.2291 | 13.2291 | 9.4097 | 17.2291 | 28.4582 | 41.6873 | 0
4.8316 | 8.4158 | 6.8316 | 5.8316 | 8.2475 | 10.2475 | 8.4158 | 14.2475 | 22.4949 | 32.7424 | 4.8416 | 8.4158 | 6.8316 | 5.8316 | 8.2475 | 10.2475 | 8.4158 | 14.2475 | 22.4949 | 32.7424 | 0
7.73 | 9.865 | 9.73 | 8.73 | 12.595 | 14.595 | 9.865 | 18.595 | 31.19 | 45.785 | 7.74 | 9.865 | 9.73 | 8.73 | 12.595 | 14.595 | 9.865 | 18.595 | 31.19 | 45.785 | 0
4.3301 | 8.1651 | 6.3301 | 5.3301 | 7.4952 | 9.4952 | 8.1651 | 13.4952 | 20.9904 | 30.4857 | 4.3401 | 8.1651 | 6.3301 | 5.3301 | 7.4952 | 9.4952 | 8.1651 | 13.4952 | 20.9904 | 30.4857 | 0
4.0174 | 8.0087 | 6.0174 | 5.0174 | 7.0261 | 9.0261 | 8.0087 | 13.0261 | 20.0522 | 29.0784 | 4.0274 | 8.0087 | 6.0174 | 5.0174 | 7.0261 | 9.0261 | 8.0087 | 13.0261 | 20.0522 | 29.0784 | 0
3.7223 | 7.8612 | 5.7223 | 4.7223 | 6.5835 | 8.5835 | 7.8612 | 12.5835 | 19.1669 | 27.7504 | 3.7323 | 7.8612 | 5.7223 | 4.7223 | 6.5835 | 8.5835 | 7.8612 | 12.5835 | 19.1669 | 27.7504 | 0
5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 5.3001 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 0
7.4619 | 9.731 | 9.4619 | 8.4619 | 12.1929 | 14.1929 | 9.731 | 18.1929 | 30.3858 | 44.5787 | 7.4719 | 9.731 | 9.4619 | 8.4619 | 12.1929 | 14.1929 | 9.731 | 18.1929 | 30.3858 | 44.5787 | 0
4.2939 | 8.1469 | 6.2939 | 5.2939 | 7.4408 | 9.4408 | 8.1469 | 13.4408 | 20.8817 | 30.3225 | 4.3039 | 8.1469 | 6.2939 | 5.2939 | 7.4408 | 9.4408 | 8.1469 | 13.4408 | 20.8817 | 30.3225 | 0
6.2435 | 9.1217 | 8.2435 | 7.2435 | 10.3652 | 12.3652 | 9.1217 | 16.3652 | 26.7304 | 39.0957 | 6.2535 | 9.1217 | 8.2435 | 7.2435 | 10.3652 | 12.3652 | 9.1217 | 16.3652 | 26.7304 | 39.0957 | 0
5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 5.1021 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 0
7.367 | 9.6835 | 9.367 | 8.367 | 12.0506 | 14.0506 | 9.6835 | 18.0506 | 30.1011 | 44.1517 | 7.377 | 9.6835 | 9.367 | 8.367 | 12.0506 | 14.0506 | 9.6835 | 18.0506 | 30.1011 | 44.1517 | 0
9.1555 | 10.5777 | 11.1555 | 10.1555 | 14.7332 | 16.7332 | 10.5777 | 20.7332 | 35.4664 | 52.1996 | 9.1655 | 10.5777 | 11.1555 | 10.1555 | 14.7332 | 16.7332 | 10.5777 | 20.7332 | 35.4664 | 52.1996 | 0
4.4266 | 8.2133 | 6.4266 | 5.4266 | 7.64 | 9.64 | 8.2133 | 13.64 | 21.2799 | 30.9199 | 4.4366 | 8.2133 | 6.4266 | 5.4266 | 7.64 | 9.64 | 8.2133 | 13.64 | 21.2799 | 30.9199 | 0
6.4001 | 9.2 | 8.4001 | 7.4001 | 10.6001 | 12.6001 | 9.2 | 16.6001 | 27.2002 | 39.8003 | 6.4101 | 9.2 | 8.4001 | 7.4001 | 10.6001 | 12.6001 | 9.2 | 16.6001 | 27.2002 | 39.8003 | 0
5.0045 | 8.5023 | 7.0045 | 6.0045 | 8.5068 | 10.5068 | 8.5023 | 14.5068 | 23.0136 | 33.5204 | 5.0145 | 8.5023 | 7.0045 | 6.0045 | 8.5068 | 10.5068 | 8.5023 | 14.5068 | 23.0136 | 33.5204 | 0
2.7353 | 7.3676 | 4.7353 | 3.7353 | 5.1029 | 7.1029 | 7.3676 | 11.1029 | 16.2058 | 23.3088 | 2.7453 | 7.3676 | 4.7353 | 3.7353 | 5.1029 | 7.1029 | 7.3676 | 11.1029 | 16.2058 | 23.3088 | 0
5.211 | 8.6055 | 7.211 | 6.211 | 8.8164 | 10.8164 | 8.6055 | 14.8164 | 23.6329 | 34.4493 | 5.221 | 8.6055 | 7.211 | 6.211 | 8.8164 | 10.8164 | 8.6055 | 14.8164 | 23.6329 | 34.4493 | 0
5.7148 | 8.8574 | 7.7148 | 6.7148 | 9.5723 | 11.5723 | 8.8574 | 15.5723 | 25.1445 | 36.7168 | 5.7248 | 8.8574 | 7.7148 | 6.7148 | 9.5723 | 11.5723 | 8.8574 | 15.5723 | 25.1445 | 36.7168 | 0
2.991 | 7.4955 | 4.991 | 3.991 | 5.4865 | 7.4865 | 7.4955 | 11.4865 | 16.9729 | 24.4594 | 3.001 | 7.4955 | 4.991 | 3.991 | 5.4865 | 7.4865 | 7.4955 | 11.4865 | 16.9729 | 24.4594 | 0
5.3673 | 8.6836 | 7.3673 | 6.3673 | 9.0509 | 11.0509 | 8.6836 | 15.0509 | 24.1019 | 35.1528 | 5.3773 | 8.6836 | 7.3673 | 6.3673 | 9.0509 | 11.0509 | 8.6836 | 15.0509 | 24.1019 | 35.1528 | 0
6.8222 | 9.4111 | 8.8222 | 7.8222 | 11.2333 | 13.2333 | 9.4111 | 17.2333 | 28.4667 | 41.7 | 6.8322 | 9.4111 | 8.8222 | 7.8222 | 11.2333 | 13.2333 | 9.4111 | 17.2333 | 28.4667 | 41.7 | 0
5.639 | 8.8195 | 7.639 | 6.639 | 9.4586 | 11.4586 | 8.8195 | 15.4586 | 24.9171 | 36.3757 | 5.649 | 8.8195 | 7.639 | 6.639 | 9.4586 | 11.4586 | 8.8195 | 15.4586 | 24.9171 | 36.3757 | 0
10.6751 | 11.3376 | 12.6751 | 11.6751 | 17.0127 | 19.0127 | 11.3376 | 23.0127 | 40.0254 | 59.0381 | 10.6851 | 11.3376 | 12.6751 | 11.6751 | 17.0127 | 19.0127 | 11.3376 | 23.0127 | 40.0254 | 59.0381 | 0
1.6411 | 6.8205 | 3.6411 | 2.6411 | 3.4616 | 5.4616 | 6.8205 | 9.4616 | 12.9232 | 18.3849 | 1.6511 | 6.8205 | 3.6411 | 2.6411 | 3.4616 | 5.4616 | 6.8205 | 9.4616 | 12.9232 | 18.3849 | 0
5.3028 | 8.6514 | 7.3028 | 6.3028 | 8.9542 | 10.9542 | 8.6514 | 14.9542 | 23.9083 | 34.8625 | 5.3128 | 8.6514 | 7.3028 | 6.3028 | 8.9542 | 10.9542 | 8.6514 | 14.9542 | 23.9083 | 34.8625 | 0
8.489 | 10.2445 | 10.489 | 9.489 | 13.7334 | 15.7334 | 10.2445 | 19.7334 | 33.4669 | 49.2003 | 8.499 | 10.2445 | 10.489 | 9.489 | 13.7334 | 15.7334 | 10.2445 | 19.7334 | 33.4669 | 49.2003 | 0
6.2238 | 9.1119 | 8.2238 | 7.2238 | 10.3356 | 12.3356 | 9.1119 | 16.3356 | 26.6713 | 39.0069 | 6.2338 | 9.1119 | 8.2238 | 7.2238 | 10.3356 | 12.3356 | 9.1119 | 16.3356 | 26.6713 | 39.0069 | 0
5.7985 | 8.8993 | 7.7985 | 6.7985 | 9.6978 | 11.6978 | 8.8993 | 15.6978 | 25.3956 | 37.0935 | 5.8085 | 8.8993 | 7.7985 | 6.7985 | 9.6978 | 11.6978 | 8.8993 | 15.6978 | 25.3956 | 37.0935 | 0
7.9791 | 9.9895 | 9.9791 | 8.9791 | 12.9686 | 14.9686 | 9.9895 | 18.9686 | 31.9373 | 46.9059 | 7.9891 | 9.9895 | 9.9791 | 8.9791 | 12.9686 | 14.9686 | 9.9895 | 18.9686 | 31.9373 | 46.9059 | 0
6.6718 | 9.3359 | 8.6718 | 7.6718 | 11.0076 | 13.0076 | 9.3359 | 17.0076 | 28.0153 | 41.0229 | 6.6818 | 9.3359 | 8.6718 | 7.6718 | 11.0076 | 13.0076 | 9.3359 | 17.0076 | 28.0153 | 41.0229 | 0
2.7548 | 7.3774 | 4.7548 | 3.7548 | 5.1322 | 7.1322 | 7.3774 | 11.1322 | 16.2645 | 23.3967 | 2.7648 | 7.3774 | 4.7548 | 3.7548 | 5.1322 | 7.1322 | 7.3774 | 11.1322 | 16.2645 | 23.3967 | 0
3.7539 | 7.877 | 5.7539 | 4.7539 | 6.6309 | 8.6309 | 7.877 | 12.6309 | 19.2618 | 27.8927 | 3.7639 | 7.877 | 5.7539 | 4.7539 | 6.6309 | 8.6309 | 7.877 | 12.6309 | 19.2618 | 27.8927 | 0
4.0079 | 8.0039 | 6.0079 | 5.0079 | 7.0118 | 9.0118 | 8.0039 | 13.0118 | 20.0237 | 29.0355 | 4.0179 | 8.0039 | 6.0079 | 5.0079 | 7.0118 | 9.0118 | 8.0039 | 13.0118 | 20.0237 | 29.0355 | 0
8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 8.8331 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 0
6.8933 | 9.4467 | 8.8933 | 7.8933 | 11.34 | 13.34 | 9.4467 | 17.34 | 28.68 | 42.0201 | 6.9033 | 9.4467 | 8.8933 | 7.8933 | 11.34 | 13.34 | 9.4467 | 17.34 | 28.68 | 42.0201 | 0
3.0902 | 7.5451 | 5.0902 | 4.0902 | 5.6353 | 7.6353 | 7.5451 | 11.6353 | 17.2706 | 24.9059 | 3.1002 | 7.5451 | 5.0902 | 4.0902 | 5.6353 | 7.6353 | 7.5451 | 11.6353 | 17.2706 | 24.9059 | 0
3.6821 | 7.841 | 5.6821 | 4.6821 | 6.5231 | 8.5231 | 7.841 | 12.5231 | 19.0462 | 27.5692 | 3.6921 | 7.841 | 5.6821 | 4.6821 | 6.5231 | 8.5231 | 7.841 | 12.5231 | 19.0462 | 27.5692 | 0
3.021 | 7.5105 | 5.021 | 4.021 | 5.5315 | 7.5315 | 7.5105 | 11.5315 | 17.063 | 24.5945 | 3.031 | 7.5105 | 5.021 | 4.021 | 5.5315 | 7.5315 | 7.5105 | 11.5315 | 17.063 | 24.5945 | 0
8.4728 | 10.2364 | 10.4728 | 9.4728 | 13.7092 | 15.7092 | 10.2364 | 19.7092 | 33.4183 | 49.1275 | 8.4828 | 10.2364 | 10.4728 | 9.4728 | 13.7092 | 15.7092 | 10.2364 | 19.7092 | 33.4183 | 49.1275 | 0
3.493 | 7.7465 | 5.493 | 4.493 | 6.2395 | 8.2395 | 7.7465 | 12.2395 | 18.4791 | 26.7186 | 3.503 | 7.7465 | 5.493 | 4.493 | 6.2395 | 8.2395 | 7.7465 | 12.2395 | 18.4791 | 26.7186 | 0
9.0142 | 10.5071 | 11.0142 | 10.0142 | 14.5214 | 16.5214 | 10.5071 | 20.5214 | 35.0427 | 51.5641 | 9.0242 | 10.5071 | 11.0142 | 10.0142 | 14.5214 | 16.5214 | 10.5071 | 20.5214 | 35.0427 | 51.5641 | 0
10.0246 | 11.0123 | 12.0246 | 11.0246 | 16.0368 | 18.0368 | 11.0123 | 22.0368 | 38.0737 | 56.1105 | 10.0346 | 11.0123 | 12.0246 | 11.0246 | 16.0368 | 18.0368 | 11.0123 | 22.0368 | 38.0737 | 56.1105 | 0
9.1517 | 10.5759 | 11.1517 | 10.1517 | 14.7276 | 16.7276 | 10.5759 | 20.7276 | 35.4552 | 52.1829 | 9.1617 | 10.5759 | 11.1517 | 10.1517 | 14.7276 | 16.7276 | 10.5759 | 20.7276 | 35.4552 | 52.1829 | 0
4.2742 | 8.1371 | 6.2742 | 5.2742 | 7.4113 | 9.4113 | 8.1371 | 13.4113 | 20.8226 | 30.2339 | 4.2842 | 8.1371 | 6.2742 | 5.2742 | 7.4113 | 9.4113 | 8.1371 | 13.4113 | 20.8226 | 30.2339 | 0
4.3436 | 8.1718 | 6.3436 | 5.3436 | 7.5153 | 9.5153 | 8.1718 | 13.5153 | 21.0307 | 30.546 | 4.3536 | 8.1718 | 6.3436 | 5.3436 | 7.5153 | 9.5153 | 8.1718 | 13.5153 | 21.0307 | 30.546 | 0
7.5365 | 9.7683 | 9.5365 | 8.5365 | 12.3048 | 14.3048 | 9.7683 | 18.3048 | 30.6095 | 44.9143 | 7.5465 | 9.7683 | 9.5365 | 8.5365 | 12.3048 | 14.3048 | 9.7683 | 18.3048 | 30.6095 | 44.9143 | 0
2.6661 | 7.333 | 4.6661 | 3.6661 | 4.9991 | 6.9991 | 7.333 | 10.9991 | 15.9983 | 22.9974 | 2.6761 | 7.333 | 4.6661 | 3.6661 | 4.9991 | 6.9991 | 7.333 | 10.9991 | 15.9983 | 22.9974 | 0
5.1754 | 8.5877 | 7.1754 | 6.1754 | 8.7632 | 10.7632 | 8.5877 | 14.7632 | 23.5263 | 34.2895 | 5.1854 | 8.5877 | 7.1754 | 6.1754 | 8.7632 | 10.7632 | 8.5877 | 14.7632 | 23.5263 | 34.2895 | 0
5.602 | 8.801 | 7.602 | 6.602 | 9.4029 | 11.4029 | 8.801 | 15.4029 | 24.8059 | 36.2088 | 5.612 | 8.801 | 7.602 | 6.602 | 9.4029 | 11.4029 | 8.801 | 15.4029 | 24.8059 | 36.2088 | 0
2.4497 | 7.2248 | 4.4497 | 3.4497 | 4.6745 | 6.6745 | 7.2248 | 10.6745 | 15.349 | 22.0234 | 2.4597 | 7.2248 | 4.4497 | 3.4497 | 4.6745 | 6.6745 | 7.2248 | 10.6745 | 15.349 | 22.0234 | 0
8.632 | 10.316 | 10.632 | 9.632 | 13.948 | 15.948 | 10.316 | 19.948 | 33.8959 | 49.8439 | 8.642 | 10.316 | 10.632 | 9.632 | 13.948 | 15.948 | 10.316 | 19.948 | 33.8959 | 49.8439 | 0
7.3605 | 9.6802 | 9.3605 | 8.3605 | 12.0407 | 14.0407 | 9.6802 | 18.0407 | 30.0814 | 44.1221 | 7.3705 | 9.6802 | 9.3605 | 8.3605 | 12.0407 | 14.0407 | 9.6802 | 18.0407 | 30.0814 | 44.1221 | 0
6.2503 | 9.1251 | 8.2503 | 7.2503 | 10.3754 | 12.3754 | 9.1251 | 16.3754 | 26.7508 | 39.1262 | 6.2603 | 9.1251 | 8.2503 | 7.2503 | 10.3754 | 12.3754 | 9.1251 | 16.3754 | 26.7508 | 39.1262 | 0
6.4729 | 9.2365 | 8.4729 | 7.4729 | 10.7094 | 12.7094 | 9.2365 | 16.7094 | 27.4188 | 40.1282 | 6.4829 | 9.2365 | 8.4729 | 7.4729 | 10.7094 | 12.7094 | 9.2365 | 16.7094 | 27.4188 | 40.1282 | 0
5.0375 | 8.5187 | 7.0375 | 6.0375 | 8.5562 | 10.5562 | 8.5187 | 14.5562 | 23.1124 | 33.6686 | 5.0475 | 8.5187 | 7.0375 | 6.0375 | 8.5562 | 10.5562 | 8.5187 | 14.5562 | 23.1124 | 33.6686 | 0
6.4828 | 9.2414 | 8.4828 | 7.4828 | 10.7243 | 12.7243 | 9.2414 | 16.7243 | 27.4485 | 40.1728 | 6.4928 | 9.2414 | 8.4828 | 7.4828 | 10.7243 | 12.7243 | 9.2414 | 16.7243 | 27.4485 | 40.1728 | 0
8.6636 | 10.3318 | 10.6636 | 9.6636 | 13.9954 | 15.9954 | 10.3318 | 19.9954 | 33.9908 | 49.9862 | 8.6736 | 10.3318 | 10.6636 | 9.6636 | 13.9954 | 15.9954 | 10.3318 | 19.9954 | 33.9908 | 49.9862 | 0
6.1928 | 9.0964 | 8.1928 | 7.1928 | 10.2893 | 12.2893 | 9.0964 | 16.2893 | 26.5785 | 38.8678 | 6.2028 | 9.0964 | 8.1928 | 7.1928 | 10.2893 | 12.2893 | 9.0964 | 16.2893 | 26.5785 | 38.8678 | 0
5.2215 | 8.6108 | 7.2215 | 6.2215 | 8.8323 | 10.8323 | 8.6108 | 14.8323 | 23.6646 | 34.4969 | 5.2315 | 8.6108 | 7.2215 | 6.2215 | 8.8323 | 10.8323 | 8.6108 | 14.8323 | 23.6646 | 34.4969 | 0
3.3861 | 7.693 | 5.3861 | 4.3861 | 6.0791 | 8.0791 | 7.693 | 12.0791 | 18.1583 | 26.2374 | 3.3961 | 7.693 | 5.3861 | 4.3861 | 6.0791 | 8.0791 | 7.693 | 12.0791 | 18.1583 | 26.2374 | 0
10.7513 | 11.3757 | 12.7513 | 11.7513 | 17.127 | 19.127 | 11.3757 | 23.127 | 40.2539 | 59.3809 | 10.7613 | 11.3757 | 12.7513 | 11.7513 | 17.127 | 19.127 | 11.3757 | 23.127 | 40.2539 | 59.3809 | 0
5.4192 | 8.7096 | 7.4192 | 6.4192 | 9.1288 | 11.1288 | 8.7096 | 15.1288 | 24.2576 | 35.3864 | 5.4292 | 8.7096 | 7.4192 | 6.4192 | 9.1288 | 11.1288 | 8.7096 | 15.1288 | 24.2576 | 35.3864 | 0
10.2533 | 11.1267 | 12.2533 | 11.2533 | 16.38 | 18.38 | 11.1267 | 22.38 | 38.7599 | 57.1399 | 10.2633 | 11.1267 | 12.2533 | 11.2533 | 16.38 | 18.38 | 11.1267 | 22.38 | 38.7599 | 57.1399 | 0
4.7906 | 8.3953 | 6.7906 | 5.7906 | 8.1858 | 10.1858 | 8.3953 | 14.1858 | 22.3717 | 32.5575 | 4.8006 | 8.3953 | 6.7906 | 5.7906 | 8.1858 | 10.1858 | 8.3953 | 14.1858 | 22.3717 | 32.5575 | 0
5.4023 | 8.7011 | 7.4023 | 6.4023 | 9.1034 | 11.1034 | 8.7011 | 15.1034 | 24.2068 | 35.3102 | 5.4123 | 8.7011 | 7.4023 | 6.4023 | 9.1034 | 11.1034 | 8.7011 | 15.1034 | 24.2068 | 35.3102 | 0
9.2231 | 10.6116 | 11.2231 | 10.2231 | 14.8347 | 16.8347 | 10.6116 | 20.8347 | 35.6693 | 52.504 | 9.2331 | 10.6116 | 11.2231 | 10.2231 | 14.8347 | 16.8347 | 10.6116 | 20.8347 | 35.6693 | 52.504 | 0
6.4629 | 9.2314 | 8.4629 | 7.4629 | 10.6943 | 12.6943 | 9.2314 | 16.6943 | 27.3886 | 40.0829 | 6.4729 | 9.2314 | 8.4629 | 7.4629 | 10.6943 | 12.6943 | 9.2314 | 16.6943 | 27.3886 | 40.0829 | 0
3.3717 | 7.6858 | 5.3717 | 4.3717 | 6.0575 | 8.0575 | 7.6858 | 12.0575 | 18.115 | 26.1724 | 3.3817 | 7.6858 | 5.3717 | 4.3717 | 6.0575 | 8.0575 | 7.6858 | 12.0575 | 18.115 | 26.1724 | 0
5.6239 | 8.812 | 7.6239 | 6.6239 | 9.4359 | 11.4359 | 8.812 | 15.4359 | 24.8718 | 36.3078 | 5.6339 | 8.812 | 7.6239 | 6.6239 | 9.4359 | 11.4359 | 8.812 | 15.4359 | 24.8718 | 36.3078 | 0
9.3247 | 10.6624 | 11.3247 | 10.3247 | 14.9871 | 16.9871 | 10.6624 | 20.9871 | 35.9742 | 52.9613 | 9.3347 | 10.6624 | 11.3247 | 10.3247 | 14.9871 | 16.9871 | 10.6624 | 20.9871 | 35.9742 | 52.9613 | 0
4.3088 | 8.1544 | 6.3088 | 5.3088 | 7.4632 | 9.4632 | 8.1544 | 13.4632 | 20.9264 | 30.3896 | 4.3188 | 8.1544 | 6.3088 | 5.3088 | 7.4632 | 9.4632 | 8.1544 | 13.4632 | 20.9264 | 30.3896 | 0
5.0985 | 8.5493 | 7.0985 | 6.0985 | 8.6478 | 10.6478 | 8.5493 | 14.6478 | 23.2956 | 33.9434 | 5.1085 | 8.5493 | 7.0985 | 6.0985 | 8.6478 | 10.6478 | 8.5493 | 14.6478 | 23.2956 | 33.9434 | 0
7.6629 | 9.8315 | 9.6629 | 8.6629 | 12.4944 | 14.4944 | 9.8315 | 18.4944 | 30.9888 | 45.4832 | 7.6729 | 9.8315 | 9.6629 | 8.6629 | 12.4944 | 14.4944 | 9.8315 | 18.4944 | 30.9888 | 45.4832 | 0
9.3024 | 10.6512 | 11.3024 | 10.3024 | 14.9536 | 16.9536 | 10.6512 | 20.9536 | 35.9072 | 52.8609 | 9.3124 | 10.6512 | 11.3024 | 10.3024 | 14.9536 | 16.9536 | 10.6512 | 20.9536 | 35.9072 | 52.8609 | 0
8.7686 | 10.3843 | 10.7686 | 9.7686 | 14.1529 | 16.1529 | 10.3843 | 20.1529 | 34.3058 | 50.4587 | 8.7786 | 10.3843 | 10.7686 | 9.7686 | 14.1529 | 16.1529 | 10.3843 | 20.1529 | 34.3058 | 50.4587 | 0
8.1501 | 10.075 | 10.1501 | 9.1501 | 13.2251 | 15.2251 | 10.075 | 19.2251 | 32.4502 | 47.6753 | 8.1601 | 10.075 | 10.1501 | 9.1501 | 13.2251 | 15.2251 | 10.075 | 19.2251 | 32.4502 | 47.6753 | 0
6.7669 | 9.3835 | 8.7669 | 7.7669 | 11.1504 | 13.1504 | 9.3835 | 17.1504 | 28.3008 | 41.4512 | 6.7769 | 9.3835 | 8.7669 | 7.7669 | 11.1504 | 13.1504 | 9.3835 | 17.1504 | 28.3008 | 41.4512 | 0
6.0705 | 9.0352 | 8.0705 | 7.0705 | 10.1057 | 12.1057 | 9.0352 | 16.1057 | 26.2114 | 38.3171 | 6.0805 | 9.0352 | 8.0705 | 7.0705 | 10.1057 | 12.1057 | 9.0352 | 16.1057 | 26.2114 | 38.3171 | 0
5.7724 | 8.8862 | 7.7724 | 6.7724 | 9.6586 | 11.6586 | 8.8862 | 15.6586 | 25.3172 | 36.9757 | 5.7824 | 8.8862 | 7.7724 | 6.7724 | 9.6586 | 11.6586 | 8.8862 | 15.6586 | 25.3172 | 36.9757 | 0
7.6638 | 9.8319 | 9.6638 | 8.6638 | 12.4957 | 14.4957 | 9.8319 | 18.4957 | 30.9914 | 45.487 | 7.6738 | 9.8319 | 9.6638 | 8.6638 | 12.4957 | 14.4957 | 9.8319 | 18.4957 | 30.9914 | 45.487 | 0
5.8442 | 8.9221 | 7.8442 | 6.8442 | 9.7663 | 11.7663 | 8.9221 | 15.7663 | 25.5325 | 37.2988 | 5.8542 | 8.9221 | 7.8442 | 6.8442 | 9.7663 | 11.7663 | 8.9221 | 15.7663 | 25.5325 | 37.2988 | 0
4.8173 | 8.4086 | 6.8173 | 5.8173 | 8.2259 | 10.2259 | 8.4086 | 14.2259 | 22.4518 | 32.6777 | 4.8273 | 8.4086 | 6.8173 | 5.8173 | 8.2259 | 10.2259 | 8.4086 | 14.2259 | 22.4518 | 32.6777 | 0
3.6353 | 7.8177 | 5.6353 | 4.6353 | 6.453 | 8.453 | 7.8177 | 12.453 | 18.9059 | 27.3589 | 3.6453 | 7.8177 | 5.6353 | 4.6353 | 6.453 | 8.453 | 7.8177 | 12.453 | 18.9059 | 27.3589 | 0
3.3053 | 7.6526 | 5.3053 | 4.3053 | 5.9579 | 7.9579 | 7.6526 | 11.9579 | 17.9158 | 25.8737 | 3.3153 | 7.6526 | 5.3053 | 4.3053 | 5.9579 | 7.9579 | 7.6526 | 11.9579 | 17.9158 | 25.8737 | 0
5.0443 | 8.5222 | 7.0443 | 6.0443 | 8.5665 | 10.5665 | 8.5222 | 14.5665 | 23.133 | 33.6995 | 5.0543 | 8.5222 | 7.0443 | 6.0443 | 8.5665 | 10.5665 | 8.5222 | 14.5665 | 23.133 | 33.6995 | 0
8.0763 | 10.0381 | 10.0763 | 9.0763 | 13.1144 | 15.1144 | 10.0381 | 19.1144 | 32.2289 | 47.3433 | 8.0863 | 10.0381 | 10.0763 | 9.0763 | 13.1144 | 15.1144 | 10.0381 | 19.1144 | 32.2289 | 47.3433 | 0
4.3336 | 8.1668 | 6.3336 | 5.3336 | 7.5004 | 9.5004 | 8.1668 | 13.5004 | 21.0008 | 30.5013 | 4.3436 | 8.1668 | 6.3336 | 5.3336 | 7.5004 | 9.5004 | 8.1668 | 13.5004 | 21.0008 | 30.5013 | 0
9.9359 | 10.9679 | 11.9359 | 10.9359 | 15.9038 | 17.9038 | 10.9679 | 21.9038 | 37.8077 | 55.7115 | 9.9459 | 10.9679 | 11.9359 | 10.9359 | 15.9038 | 17.9038 | 10.9679 | 21.9038 | 37.8077 | 55.7115 | 0
6.4882 | 9.2441 | 8.4882 | 7.4882 | 10.7323 | 12.7323 | 9.2441 | 16.7323 | 27.4646 | 40.1969 | 6.4982 | 9.2441 | 8.4882 | 7.4882 | 10.7323 | 12.7323 | 9.2441 | 16.7323 | 27.4646 | 40.1969 | 0
3.7597 | 7.8798 | 5.7597 | 4.7597 | 6.6395 | 8.6395 | 7.8798 | 12.6395 | 19.279 | 27.9185 | 3.7697 | 7.8798 | 5.7597 | 4.7597 | 6.6395 | 8.6395 | 7.8798 | 12.6395 | 19.279 | 27.9185 | 0
4.1555 | 8.0777 | 6.1555 | 5.1555 | 7.2332 | 9.2332 | 8.0777 | 13.2332 | 20.4665 | 29.6997 | 4.1655 | 8.0777 | 6.1555 | 5.1555 | 7.2332 | 9.2332 | 8.0777 | 13.2332 | 20.4665 | 29.6997 | 0
2.6525 | 7.3263 | 4.6525 | 3.6525 | 4.9788 | 6.9788 | 7.3263 | 10.9788 | 15.9575 | 22.9363 | 2.6625 | 7.3263 | 4.6525 | 3.6525 | 4.9788 | 6.9788 | 7.3263 | 10.9788 | 15.9575 | 22.9363 | 0
1.8403 | 6.9201 | 3.8403 | 2.8403 | 3.7604 | 5.7604 | 6.9201 | 9.7604 | 13.5208 | 19.2812 | 1.8503 | 6.9201 | 3.8403 | 2.8403 | 3.7604 | 5.7604 | 6.9201 | 9.7604 | 13.5208 | 19.2812 | 0
2.6667 | 7.3334 | 4.6667 | 3.6667 | 5.0001 | 7.0001 | 7.3334 | 11.0001 | 16.0001 | 23.0002 | 2.6767 | 7.3334 | 4.6667 | 3.6667 | 5.0001 | 7.0001 | 7.3334 | 11.0001 | 16.0001 | 23.0002 | 0
6.4608 | 9.2304 | 8.4608 | 7.4608 | 10.6912 | 12.6912 | 9.2304 | 16.6912 | 27.3825 | 40.0737 | 6.4708 | 9.2304 | 8.4608 | 7.4608 | 10.6912 | 12.6912 | 9.2304 | 16.6912 | 27.3825 | 40.0737 | 0
4.1906 | 8.0953 | 6.1906 | 5.1906 | 7.2858 | 9.2858 | 8.0953 | 13.2858 | 20.5717 | 29.8575 | 4.2006 | 8.0953 | 6.1906 | 5.1906 | 7.2858 | 9.2858 | 8.0953 | 13.2858 | 20.5717 | 29.8575 | 0
8.6153 | 10.3077 | 10.6153 | 9.6153 | 13.923 | 15.923 | 10.3077 | 19.923 | 33.846 | 49.769 | 8.6253 | 10.3077 | 10.6153 | 9.6153 | 13.923 | 15.923 | 10.3077 | 19.923 | 33.846 | 49.769 | 0
4.7385 | 8.3693 | 6.7385 | 5.7385 | 8.1078 | 10.1078 | 8.3693 | 14.1078 | 22.2156 | 32.3234 | 4.7485 | 8.3693 | 6.7385 | 5.7385 | 8.1078 | 10.1078 | 8.3693 | 14.1078 | 22.2156 | 32.3234 | 0
2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 2.9938 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 0
3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 3.9827 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 0
5.9707 | 8.9854 | 7.9707 | 6.9707 | 9.9561 | 11.9561 | 8.9854 | 15.9561 | 25.9121 | 37.8682 | 5.9807 | 8.9854 | 7.9707 | 6.9707 | 9.9561 | 11.9561 | 8.9854 | 15.9561 | 25.9121 | 37.8682 | 0
8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 8.3744 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 0
5.1237 | 8.5618 | 7.1237 | 6.1237 | 8.6855 | 10.6855 | 8.5618 | 14.6855 | 23.3711 | 34.0566 | 5.1337 | 8.5618 | 7.1237 | 6.1237 | 8.6855 | 10.6855 | 8.5618 | 14.6855 | 23.3711 | 34.0566 | 0
4.2034 | 8.1017 | 6.2034 | 5.2034 | 7.3051 | 9.3051 | 8.1017 | 13.3051 | 20.6102 | 29.9154 | 4.2134 | 8.1017 | 6.2034 | 5.2034 | 7.3051 | 9.3051 | 8.1017 | 13.3051 | 20.6102 | 29.9154 | 0
5.5663 | 8.7832 | 7.5663 | 6.5663 | 9.3495 | 11.3495 | 8.7832 | 15.3495 | 24.699 | 36.0484 | 5.5763 | 8.7832 | 7.5663 | 6.5663 | 9.3495 | 11.3495 | 8.7832 | 15.3495 | 24.699 | 36.0484 | 0
6.8431 | 9.4215 | 8.8431 | 7.8431 | 11.2646 | 13.2646 | 9.4215 | 17.2646 | 28.5292 | 41.7939 | 6.8531 | 9.4215 | 8.8431 | 7.8431 | 11.2646 | 13.2646 | 9.4215 | 17.2646 | 28.5292 | 41.7939 | 0
6.8551 | 9.4276 | 8.8551 | 7.8551 | 11.2827 | 13.2827 | 9.4276 | 17.2827 | 28.5654 | 41.8481 | 6.8651 | 9.4276 | 8.8551 | 7.8551 | 11.2827 | 13.2827 | 9.4276 | 17.2827 | 28.5654 | 41.8481 | 0
4.4435 | 8.2217 | 6.4435 | 5.4435 | 7.6652 | 9.6652 | 8.2217 | 13.6652 | 21.3304 | 30.9956 | 4.4535 | 8.2217 | 6.4435 | 5.4435 | 7.6652 | 9.6652 | 8.2217 | 13.6652 | 21.3304 | 30.9956 | 0
9.454 | 10.727 | 11.454 | 10.454 | 15.181 | 17.181 | 10.727 | 21.181 | 36.3619 | 53.5429 | 9.464 | 10.727 | 11.454 | 10.454 | 15.181 | 17.181 | 10.727 | 21.181 | 36.3619 | 53.5429 | 0
7.8182 | 9.9091 | 9.8182 | 8.8182 | 12.7273 | 14.7273 | 9.9091 | 18.7273 | 31.4547 | 46.182 | 7.8282 | 9.9091 | 9.8182 | 8.8182 | 12.7273 | 14.7273 | 9.9091 | 18.7273 | 31.4547 | 46.182 | 0
6.9341 | 9.4671 | 8.9341 | 7.9341 | 11.4012 | 13.4012 | 9.4671 | 17.4012 | 28.8023 | 42.2035 | 6.9441 | 9.4671 | 8.9341 | 7.9341 | 11.4012 | 13.4012 | 9.4671 | 17.4012 | 28.8023 | 42.2035 | 0
4.4815 | 8.2408 | 6.4815 | 5.4815 | 7.7223 | 9.7223 | 8.2408 | 13.7223 | 21.4445 | 31.1668 | 4.4915 | 8.2408 | 6.4815 | 5.4815 | 7.7223 | 9.7223 | 8.2408 | 13.7223 | 21.4445 | 31.1668 | 0
5.1586 | 8.5793 | 7.1586 | 6.1586 | 8.7379 | 10.7379 | 8.5793 | 14.7379 | 23.4758 | 34.2137 | 5.1686 | 8.5793 | 7.1586 | 6.1586 | 8.7379 | 10.7379 | 8.5793 | 14.7379 | 23.4758 | 34.2137 | 0
8.2539 | 10.1269 | 10.2539 | 9.2539 | 13.3808 | 15.3808 | 10.1269 | 19.3808 | 32.7616 | 48.1423 | 8.2639 | 10.1269 | 10.2539 | 9.2539 | 13.3808 | 15.3808 | 10.1269 | 19.3808 | 32.7616 | 48.1423 | 0
7.8806 | 9.9403 | 9.8806 | 8.8806 | 12.8209 | 14.8209 | 9.9403 | 18.8209 | 31.6419 | 46.4628 | 7.8906 | 9.9403 | 9.8806 | 8.8806 | 12.8209 | 14.8209 | 9.9403 | 18.8209 | 31.6419 | 46.4628 | 0
4.776 | 8.388 | 6.776 | 5.776 | 8.164 | 10.164 | 8.388 | 14.164 | 22.3281 | 32.4921 | 4.786 | 8.388 | 6.776 | 5.776 | 8.164 | 10.164 | 8.388 | 14.164 | 22.3281 | 32.4921 | 0
6.3025 | 9.1512 | 8.3025 | 7.3025 | 10.4537 | 12.4537 | 9.1512 | 16.4537 | 26.9074 | 39.3611 | 6.3125 | 9.1512 | 8.3025 | 7.3025 | 10.4537 | 12.4537 | 9.1512 | 16.4537 | 26.9074 | 39.3611 | 0
6.7528 | 9.3764 | 8.7528 | 7.7528 | 11.1292 | 13.1292 | 9.3764 | 17.1292 | 28.2584 | 41.3875 | 6.7628 | 9.3764 | 8.7528 | 7.7528 | 11.1292 | 13.1292 | 9.3764 | 17.1292 | 28.2584 | 41.3875 | 0
6.2989 | 9.1495 | 8.2989 | 7.2989 | 10.4484 | 12.4484 | 9.1495 | 16.4484 | 26.8968 | 39.3451 | 6.3089 | 9.1495 | 8.2989 | 7.2989 | 10.4484 | 12.4484 | 9.1495 | 16.4484 | 26.8968 | 39.3451 | 0
6.9488 | 9.4744 | 8.9488 | 7.9488 | 11.4232 | 13.4232 | 9.4744 | 17.4232 | 28.8464 | 42.2696 | 6.9588 | 9.4744 | 8.9488 | 7.9488 | 11.4232 | 13.4232 | 9.4744 | 17.4232 | 28.8464 | 42.2696 | 0
3.3735 | 7.6867 | 5.3735 | 4.3735 | 6.0602 | 8.0602 | 7.6867 | 12.0602 | 18.1204 | 26.1806 | 3.3835 | 7.6867 | 5.3735 | 4.3735 | 6.0602 | 8.0602 | 7.6867 | 12.0602 | 18.1204 | 26.1806 | 0
8.8156 | 10.4078 | 10.8156 | 9.8156 | 14.2235 | 16.2235 | 10.4078 | 20.2235 | 34.4469 | 50.6704 | 8.8256 | 10.4078 | 10.8156 | 9.8156 | 14.2235 | 16.2235 | 10.4078 | 20.2235 | 34.4469 | 50.6704 | 0
6.1938 | 9.0969 | 8.1938 | 7.1938 | 10.2907 | 12.2907 | 9.0969 | 16.2907 | 26.5813 | 38.872 | 6.2038 | 9.0969 | 8.1938 | 7.1938 | 10.2907 | 12.2907 | 9.0969 | 16.2907 | 26.5813 | 38.872 | 0
2.6892 | 7.3446 | 4.6892 | 3.6892 | 5.0338 | 7.0338 | 7.3446 | 11.0338 | 16.0676 | 23.1013 | 2.6992 | 7.3446 | 4.6892 | 3.6892 | 5.0338 | 7.0338 | 7.3446 | 11.0338 | 16.0676 | 23.1013 | 0
9.693 | 10.8465 | 11.693 | 10.693 | 15.5395 | 17.5395 | 10.8465 | 21.5395 | 37.0789 | 54.6184 | 9.703 | 10.8465 | 11.693 | 10.693 | 15.5395 | 17.5395 | 10.8465 | 21.5395 | 37.0789 | 54.6184 | 0
7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 7.2312 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 0
7.6207 | 9.8104 | 9.6207 | 8.6207 | 12.4311 | 14.4311 | 9.8104 | 18.4311 | 30.8621 | 45.2932 | 7.6307 | 9.8104 | 9.6207 | 8.6207 | 12.4311 | 14.4311 | 9.8104 | 18.4311 | 30.8621 | 45.2932 | 0
5.3109 | 8.6554 | 7.3109 | 6.3109 | 8.9663 | 10.9663 | 8.6554 | 14.9663 | 23.9327 | 34.899 | 5.3209 | 8.6554 | 7.3109 | 6.3109 | 8.9663 | 10.9663 | 8.6554 | 14.9663 | 23.9327 | 34.899 | 0
5.815 | 8.9075 | 7.815 | 6.815 | 9.7225 | 11.7225 | 8.9075 | 15.7225 | 25.445 | 37.1675 | 5.825 | 8.9075 | 7.815 | 6.815 | 9.7225 | 11.7225 | 8.9075 | 15.7225 | 25.445 | 37.1675 | 0
8.6974 | 10.3487 | 10.6974 | 9.6974 | 14.0461 | 16.0461 | 10.3487 | 20.0461 | 34.0922 | 50.1383 | 8.7074 | 10.3487 | 10.6974 | 9.6974 | 14.0461 | 16.0461 | 10.3487 | 20.0461 | 34.0922 | 50.1383 | 0
4.5436 | 8.2718 | 6.5436 | 5.5436 | 7.8155 | 9.8155 | 8.2718 | 13.8155 | 21.6309 | 31.4464 | 4.5536 | 8.2718 | 6.5436 | 5.5436 | 7.8155 | 9.8155 | 8.2718 | 13.8155 | 21.6309 | 31.4464 | 0
3.342 | 7.671 | 5.342 | 4.342 | 6.013 | 8.013 | 7.671 | 12.013 | 18.0259 | 26.0389 | 3.352 | 7.671 | 5.342 | 4.342 | 6.013 | 8.013 | 7.671 | 12.013 | 18.0259 | 26.0389 | 0
3.0612 | 7.5306 | 5.0612 | 4.0612 | 5.5918 | 7.5918 | 7.5306 | 11.5918 | 17.1837 | 24.7755 | 3.0712 | 7.5306 | 5.0612 | 4.0612 | 5.5918 | 7.5918 | 7.5306 | 11.5918 | 17.1837 | 24.7755 | 0
8.378 | 10.189 | 10.378 | 9.378 | 13.567 | 15.567 | 10.189 | 19.567 | 33.1339 | 48.7009 | 8.388 | 10.189 | 10.378 | 9.378 | 13.567 | 15.567 | 10.189 | 19.567 | 33.1339 | 48.7009 | 0
5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 5.8098 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 0
5.55 | 8.775 | 7.55 | 6.55 | 9.325 | 11.325 | 8.775 | 15.325 | 24.65 | 35.9751 | 5.56 | 8.775 | 7.55 | 6.55 | 9.325 | 11.325 | 8.775 | 15.325 | 24.65 | 35.9751 | 0
8.0143 | 10.0072 | 10.0143 | 9.0143 | 13.0215 | 15.0215 | 10.0072 | 19.0215 | 32.043 | 47.0645 | 8.0243 | 10.0072 | 10.0143 | 9.0143 | 13.0215 | 15.0215 | 10.0072 | 19.0215 | 32.043 | 47.0645 | 0
4.2615 | 8.1308 | 6.2615 | 5.2615 | 7.3923 | 9.3923 | 8.1308 | 13.3923 | 20.7846 | 30.1769 | 4.2715 | 8.1308 | 6.2615 | 5.2615 | 7.3923 | 9.3923 | 8.1308 | 13.3923 | 20.7846 | 30.1769 | 0
4.3816 | 8.1908 | 6.3816 | 5.3816 | 7.5724 | 9.5724 | 8.1908 | 13.5724 | 21.1449 | 30.7173 | 4.3916 | 8.1908 | 6.3816 | 5.3816 | 7.5724 | 9.5724 | 8.1908 | 13.5724 | 21.1449 | 30.7173 | 0
5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 5.8098 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 0
7.8028 | 9.9014 | 9.8028 | 8.8028 | 12.7042 | 14.7042 | 9.9014 | 18.7042 | 31.4083 | 46.1125 | 7.8128 | 9.9014 | 9.8028 | 8.8028 | 12.7042 | 14.7042 | 9.9014 | 18.7042 | 31.4083 | 46.1125 | 0
8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 8.3744 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 0
5.5132 | 8.7566 | 7.5132 | 6.5132 | 9.2698 | 11.2698 | 8.7566 | 15.2698 | 24.5397 | 35.8095 | 5.5232 | 8.7566 | 7.5132 | 6.5132 | 9.2698 | 11.2698 | 8.7566 | 15.2698 | 24.5397 | 35.8095 | 0
7.8861 | 9.9431 | 9.8861 | 8.8861 | 12.8292 | 14.8292 | 9.9431 | 18.8292 | 31.6583 | 46.4875 | 7.8961 | 9.9431 | 9.8861 | 8.8861 | 12.8292 | 14.8292 | 9.9431 | 18.8292 | 31.6583 | 46.4875 | 0
6.7892 | 9.3946 | 8.7892 | 7.7892 | 11.1838 | 13.1838 | 9.3946 | 17.1838 | 28.3676 | 41.5514 | 6.7992 | 9.3946 | 8.7892 | 7.7892 | 11.1838 | 13.1838 | 9.3946 | 17.1838 | 28.3676 | 41.5514 | 0
4.1869 | 8.0934 | 6.1869 | 5.1869 | 7.2803 | 9.2803 | 8.0934 | 13.2803 | 20.5606 | 29.8409 | 4.1969 | 8.0934 | 6.1869 | 5.1869 | 7.2803 | 9.2803 | 8.0934 | 13.2803 | 20.5606 | 29.8409 | 0
4.1938 | 8.0969 | 6.1938 | 5.1938 | 7.2907 | 9.2907 | 8.0969 | 13.2907 | 20.5813 | 29.872 | 4.2038 | 8.0969 | 6.1938 | 5.1938 | 7.2907 | 9.2907 | 8.0969 | 13.2907 | 20.5813 | 29.872 | 0
3.2575 | 7.6287 | 5.2575 | 4.2575 | 5.8862 | 7.8862 | 7.6287 | 11.8862 | 17.7724 | 25.6586 | 3.2675 | 7.6287 | 5.2575 | 4.2575 | 5.8862 | 7.8862 | 7.6287 | 11.8862 | 17.7724 | 25.6586 | 0
4.0356 | 8.0178 | 6.0356 | 5.0356 | 7.0534 | 9.0534 | 8.0178 | 13.0534 | 20.1068 | 29.1602 | 4.0456 | 8.0178 | 6.0356 | 5.0356 | 7.0534 | 9.0534 | 8.0178 | 13.0534 | 20.1068 | 29.1602 | 0
6.4349 | 9.2175 | 8.4349 | 7.4349 | 10.6524 | 12.6524 | 9.2175 | 16.6524 | 27.3048 | 39.9572 | 6.4449 | 9.2175 | 8.4349 | 7.4349 | 10.6524 | 12.6524 | 9.2175 | 16.6524 | 27.3048 | 39.9572 | 0
7.869 | 9.9345 | 9.869 | 8.869 | 12.8035 | 14.8035 | 9.9345 | 18.8035 | 31.607 | 46.4105 | 7.879 | 9.9345 | 9.869 | 8.869 | 12.8035 | 14.8035 | 9.9345 | 18.8035 | 31.607 | 46.4105 | 0
6.7712 | 9.3856 | 8.7712 | 7.7712 | 11.1568 | 13.1568 | 9.3856 | 17.1568 | 28.3136 | 41.4704 | 6.7812 | 9.3856 | 8.7712 | 7.7712 | 11.1568 | 13.1568 | 9.3856 | 17.1568 | 28.3136 | 41.4704 | 0
8.0857 | 10.0429 | 10.0857 | 9.0857 | 13.1286 | 15.1286 | 10.0429 | 19.1286 | 32.2572 | 47.3859 | 8.0957 | 10.0429 | 10.0857 | 9.0857 | 13.1286 | 15.1286 | 10.0429 | 19.1286 | 32.2572 | 47.3859 | 0
7.7566 | 9.8783 | 9.7566 | 8.7566 | 12.6349 | 14.6349 | 9.8783 | 18.6349 | 31.2699 | 45.9048 | 7.7666 | 9.8783 | 9.7566 | 8.7566 | 12.6349 | 14.6349 | 9.8783 | 18.6349 | 31.2699 | 45.9048 | 0
9.6525 | 10.8263 | 11.6525 | 10.6525 | 15.4788 | 17.4788 | 10.8263 | 21.4788 | 36.9575 | 54.4363 | 9.6625 | 10.8263 | 11.6525 | 10.6525 | 15.4788 | 17.4788 | 10.8263 | 21.4788 | 36.9575 | 54.4363 | 0
7.2986 | 9.6493 | 9.2986 | 8.2986 | 11.948 | 13.948 | 9.6493 | 17.948 | 29.8959 | 43.8439 | 7.3086 | 9.6493 | 9.2986 | 8.2986 | 11.948 | 13.948 | 9.6493 | 17.948 | 29.8959 | 43.8439 | 0
4.0521 | 8.0261 | 6.0521 | 5.0521 | 7.0782 | 9.0782 | 8.0261 | 13.0782 | 20.1564 | 29.2346 | 4.0621 | 8.0261 | 6.0521 | 5.0521 | 7.0782 | 9.0782 | 8.0261 | 13.0782 | 20.1564 | 29.2346 | 0
7.0371 | 9.5185 | 9.0371 | 8.0371 | 11.5556 | 13.5556 | 9.5185 | 17.5556 | 29.1112 | 42.6668 | 7.0471 | 9.5185 | 9.0371 | 8.0371 | 11.5556 | 13.5556 | 9.5185 | 17.5556 | 29.1112 | 42.6668 | 0
2.233 | 7.1165 | 4.233 | 3.233 | 4.3495 | 6.3495 | 7.1165 | 10.3495 | 14.6991 | 21.0486 | 2.243 | 7.1165 | 4.233 | 3.233 | 4.3495 | 6.3495 | 7.1165 | 10.3495 | 14.6991 | 21.0486 | 0
7.2275 | 9.6137 | 9.2275 | 8.2275 | 11.8412 | 13.8412 | 9.6137 | 17.8412 | 29.6825 | 43.5237 | 7.2375 | 9.6137 | 9.2275 | 8.2275 | 11.8412 | 13.8412 | 9.6137 | 17.8412 | 29.6825 | 43.5237 | 0
6.3896 | 9.1948 | 8.3896 | 7.3896 | 10.5844 | 12.5844 | 9.1948 | 16.5844 | 27.1688 | 39.7532 | 6.3996 | 9.1948 | 8.3896 | 7.3896 | 10.5844 | 12.5844 | 9.1948 | 16.5844 | 27.1688 | 39.7532 | 0
6.4116 | 9.2058 | 8.4116 | 7.4116 | 10.6174 | 12.6174 | 9.2058 | 16.6174 | 27.2349 | 39.8523 | 6.4216 | 9.2058 | 8.4116 | 7.4116 | 10.6174 | 12.6174 | 9.2058 | 16.6174 | 27.2349 | 39.8523 | 0
4.7322 | 8.3661 | 6.7322 | 5.7322 | 8.0983 | 10.0983 | 8.3661 | 14.0983 | 22.1965 | 32.2948 | 4.7422 | 8.3661 | 6.7322 | 5.7322 | 8.0983 | 10.0983 | 8.3661 | 14.0983 | 22.1965 | 32.2948 | 0
6.7518 | 9.3759 | 8.7518 | 7.7518 | 11.1277 | 13.1277 | 9.3759 | 17.1277 | 28.2554 | 41.3831 | 6.7618 | 9.3759 | 8.7518 | 7.7518 | 11.1277 | 13.1277 | 9.3759 | 17.1277 | 28.2554 | 41.3831 | 0
4.1562 | 8.0781 | 6.1562 | 5.1562 | 7.2343 | 9.2343 | 8.0781 | 13.2343 | 20.4686 | 29.7029 | 4.1662 | 8.0781 | 6.1562 | 5.1562 | 7.2343 | 9.2343 | 8.0781 | 13.2343 | 20.4686 | 29.7029 | 0
3.8186 | 7.9093 | 5.8186 | 4.8186 | 6.7279 | 8.7279 | 7.9093 | 12.7279 | 19.4557 | 28.1836 | 3.8286 | 7.9093 | 5.8186 | 4.8186 | 6.7279 | 8.7279 | 7.9093 | 12.7279 | 19.4557 | 28.1836 | 0
4.9033 | 8.4517 | 6.9033 | 5.9033 | 8.355 | 10.355 | 8.4517 | 14.355 | 22.7099 | 33.0649 | 4.9133 | 8.4517 | 6.9033 | 5.9033 | 8.355 | 10.355 | 8.4517 | 14.355 | 22.7099 | 33.0649 | 0
3.8613 | 7.9307 | 5.8613 | 4.8613 | 6.792 | 8.792 | 7.9307 | 12.792 | 19.584 | 28.376 | 3.8713 | 7.9307 | 5.8613 | 4.8613 | 6.792 | 8.792 | 7.9307 | 12.792 | 19.584 | 28.376 | 0
8.8507 | 10.4253 | 10.8507 | 9.8507 | 14.276 | 16.276 | 10.4253 | 20.276 | 34.5521 | 50.8281 | 8.8607 | 10.4253 | 10.8507 | 9.8507 | 14.276 | 16.276 | 10.4253 | 20.276 | 34.5521 | 50.8281 | 0
4.7771 | 8.3886 | 6.7771 | 5.7771 | 8.1657 | 10.1657 | 8.3886 | 14.1657 | 22.3314 | 32.4971 | 4.7871 | 8.3886 | 6.7771 | 5.7771 | 8.1657 | 10.1657 | 8.3886 | 14.1657 | 22.3314 | 32.4971 | 0
6.5063 | 9.2532 | 8.5063 | 7.5063 | 10.7595 | 12.7595 | 9.2532 | 16.7595 | 27.519 | 40.2786 | 6.5163 | 9.2532 | 8.5063 | 7.5063 | 10.7595 | 12.7595 | 9.2532 | 16.7595 | 27.519 | 40.2786 | 0
6.9271 | 9.4636 | 8.9271 | 7.9271 | 11.3907 | 13.3907 | 9.4636 | 17.3907 | 28.7813 | 42.172 | 6.9371 | 9.4636 | 8.9271 | 7.9271 | 11.3907 | 13.3907 | 9.4636 | 17.3907 | 28.7813 | 42.172 | 0
4.2626 | 8.1313 | 6.2626 | 5.2626 | 7.394 | 9.394 | 8.1313 | 13.394 | 20.7879 | 30.1819 | 4.2726 | 8.1313 | 6.2626 | 5.2626 | 7.394 | 9.394 | 8.1313 | 13.394 | 20.7879 | 30.1819 | 0
2.6952 | 7.3476 | 4.6952 | 3.6952 | 5.0428 | 7.0428 | 7.3476 | 11.0428 | 16.0856 | 23.1284 | 2.7052 | 7.3476 | 4.6952 | 3.6952 | 5.0428 | 7.0428 | 7.3476 | 11.0428 | 16.0856 | 23.1284 | 0
7.9818 | 9.9909 | 9.9818 | 8.9818 | 12.9728 | 14.9728 | 9.9909 | 18.9728 | 31.9455 | 46.9183 | 7.9918 | 9.9909 | 9.9818 | 8.9818 | 12.9728 | 14.9728 | 9.9909 | 18.9728 | 31.9455 | 46.9183 | 0
4.4602 | 8.2301 | 6.4602 | 5.4602 | 7.6903 | 9.6903 | 8.2301 | 13.6903 | 21.3806 | 31.0709 | 4.4702 | 8.2301 | 6.4602 | 5.4602 | 7.6903 | 9.6903 | 8.2301 | 13.6903 | 21.3806 | 31.0709 | 0
7.8904 | 9.9452 | 9.8904 | 8.8904 | 12.8356 | 14.8356 | 9.9452 | 18.8356 | 31.6712 | 46.5069 | 7.9004 | 9.9452 | 9.8904 | 8.8904 | 12.8356 | 14.8356 | 9.9452 | 18.8356 | 31.6712 | 46.5069 | 0
4.5586 | 8.2793 | 6.5586 | 5.5586 | 7.8379 | 9.8379 | 8.2793 | 13.8379 | 21.6757 | 31.5136 | 4.5686 | 8.2793 | 6.5586 | 5.5586 | 7.8379 | 9.8379 | 8.2793 | 13.8379 | 21.6757 | 31.5136 | 0
5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 5.3659 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 0
4.5162 | 8.2581 | 6.5162 | 5.5162 | 7.7743 | 9.7743 | 8.2581 | 13.7743 | 21.5486 | 31.3228 | 4.5262 | 8.2581 | 6.5162 | 5.5162 | 7.7743 | 9.7743 | 8.2581 | 13.7743 | 21.5486 | 31.3228 | 0
4.8841 | 8.442 | 6.8841 | 5.8841 | 8.3261 | 10.3261 | 8.442 | 14.3261 | 22.6522 | 32.9782 | 4.8941 | 8.442 | 6.8841 | 5.8841 | 8.3261 | 10.3261 | 8.442 | 14.3261 | 22.6522 | 32.9782 | 0
5.6401 | 8.8201 | 7.6401 | 6.6401 | 9.4602 | 11.4602 | 8.8201 | 15.4602 | 24.9204 | 36.3806 | 5.6501 | 8.8201 | 7.6401 | 6.6401 | 9.4602 | 11.4602 | 8.8201 | 15.4602 | 24.9204 | 36.3806 | 0
9.7333 | 10.8666 | 11.7333 | 10.7333 | 15.5999 | 17.5999 | 10.8666 | 21.5999 | 37.1998 | 54.7997 | 9.7433 | 10.8666 | 11.7333 | 10.7333 | 15.5999 | 17.5999 | 10.8666 | 21.5999 | 37.1998 | 54.7997 | 0
4.4464 | 8.2232 | 6.4464 | 5.4464 | 7.6696 | 9.6696 | 8.2232 | 13.6696 | 21.3391 | 31.0087 | 4.4564 | 8.2232 | 6.4464 | 5.4464 | 7.6696 | 9.6696 | 8.2232 | 13.6696 | 21.3391 | 31.0087 | 0
3.4011 | 7.7006 | 5.4011 | 4.4011 | 6.1017 | 8.1017 | 7.7006 | 12.1017 | 18.2034 | 26.305 | 3.4111 | 7.7006 | 5.4011 | 4.4011 | 6.1017 | 8.1017 | 7.7006 | 12.1017 | 18.2034 | 26.305 | 0
5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 5.3001 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 0
2.1888 | 7.0944 | 4.1888 | 3.1888 | 4.2832 | 6.2832 | 7.0944 | 10.2832 | 14.5665 | 20.8497 | 2.1988 | 7.0944 | 4.1888 | 3.1888 | 4.2832 | 6.2832 | 7.0944 | 10.2832 | 14.5665 | 20.8497 | 0
6.8979 | 9.449 | 8.8979 | 7.8979 | 11.3469 | 13.3469 | 9.449 | 17.3469 | 28.6937 | 42.0406 | 6.9079 | 9.449 | 8.8979 | 7.8979 | 11.3469 | 13.3469 | 9.449 | 17.3469 | 28.6937 | 42.0406 | 0
4.4544 | 8.2272 | 6.4544 | 5.4544 | 7.6816 | 9.6816 | 8.2272 | 13.6816 | 21.3633 | 31.0449 | 4.4644 | 8.2272 | 6.4544 | 5.4544 | 7.6816 | 9.6816 | 8.2272 | 13.6816 | 21.3633 | 31.0449 | 0
5.3782 | 8.6891 | 7.3782 | 6.3782 | 9.0673 | 11.0673 | 8.6891 | 15.0673 | 24.1346 | 35.202 | 5.3882 | 8.6891 | 7.3782 | 6.3782 | 9.0673 | 11.0673 | 8.6891 | 15.0673 | 24.1346 | 35.202 | 0
4.8642 | 8.4321 | 6.8642 | 5.8642 | 8.2962 | 10.2962 | 8.4321 | 14.2962 | 22.5925 | 32.8887 | 4.8742 | 8.4321 | 6.8642 | 5.8642 | 8.2962 | 10.2962 | 8.4321 | 14.2962 | 22.5925 | 32.8887 | 0
6.4795 | 9.2398 | 8.4795 | 7.4795 | 10.7193 | 12.7193 | 9.2398 | 16.7193 | 27.4386 | 40.1579 | 6.4895 | 9.2398 | 8.4795 | 7.4795 | 10.7193 | 12.7193 | 9.2398 | 16.7193 | 27.4386 | 40.1579 | 0
6.2353 | 9.1177 | 8.2353 | 7.2353 | 10.353 | 12.353 | 9.1177 | 16.353 | 26.7059 | 39.0589 | 6.2453 | 9.1177 | 8.2353 | 7.2353 | 10.353 | 12.353 | 9.1177 | 16.353 | 26.7059 | 39.0589 | 0
6.6358 | 9.3179 | 8.6358 | 7.6358 | 10.9537 | 12.9537 | 9.3179 | 16.9537 | 27.9073 | 40.861 | 6.6458 | 9.3179 | 8.6358 | 7.6358 | 10.9537 | 12.9537 | 9.3179 | 16.9537 | 27.9073 | 40.861 | 0
5.2598 | 8.6299 | 7.2598 | 6.2598 | 8.8898 | 10.8898 | 8.6299 | 14.8898 | 23.7795 | 34.6693 | 5.2698 | 8.6299 | 7.2598 | 6.2598 | 8.8898 | 10.8898 | 8.6299 | 14.8898 | 23.7795 | 34.6693 | 0
5.8382 | 8.9191 | 7.8382 | 6.8382 | 9.7573 | 11.7573 | 8.9191 | 15.7573 | 25.5145 | 37.2718 | 5.8482 | 8.9191 | 7.8382 | 6.8382 | 9.7573 | 11.7573 | 8.9191 | 15.7573 | 25.5145 | 37.2718 | 0
3.6537 | 7.8268 | 5.6537 | 4.6537 | 6.4805 | 8.4805 | 7.8268 | 12.4805 | 18.961 | 27.4415 | 3.6637 | 7.8268 | 5.6537 | 4.6537 | 6.4805 | 8.4805 | 7.8268 | 12.4805 | 18.961 | 27.4415 | 0
10.3093 | 11.1546 | 12.3093 | 11.3093 | 16.4639 | 18.4639 | 11.1546 | 22.4639 | 38.9278 | 57.3917 | 10.3193 | 11.1546 | 12.3093 | 11.3093 | 16.4639 | 18.4639 | 11.1546 | 22.4639 | 38.9278 | 57.3917 | 0
2.9072 | 7.4536 | 4.9072 | 3.9072 | 5.3609 | 7.3609 | 7.4536 | 11.3609 | 16.7217 | 24.0826 | 2.9172 | 7.4536 | 4.9072 | 3.9072 | 5.3609 | 7.3609 | 7.4536 | 11.3609 | 16.7217 | 24.0826 | 0
8.8398 | 10.4199 | 10.8398 | 9.8398 | 14.2596 | 16.2596 | 10.4199 | 20.2596 | 34.5193 | 50.7789 | 8.8498 | 10.4199 | 10.8398 | 9.8398 | 14.2596 | 16.2596 | 10.4199 | 20.2596 | 34.5193 | 50.7789 | 0
4.7994 | 8.3997 | 6.7994 | 5.7994 | 8.1991 | 10.1991 | 8.3997 | 14.1991 | 22.3981 | 32.5972 | 4.8094 | 8.3997 | 6.7994 | 5.7994 | 8.1991 | 10.1991 | 8.3997 | 14.1991 | 22.3981 | 32.5972 | 0
4.8728 | 8.4364 | 6.8728 | 5.8728 | 8.3092 | 10.3092 | 8.4364 | 14.3092 | 22.6183 | 32.9275 | 4.8828 | 8.4364 | 6.8728 | 5.8728 | 8.3092 | 10.3092 | 8.4364 | 14.3092 | 22.6183 | 32.9275 | 0
8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 8.8331 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 0
8.2877 | 10.1438 | 10.2877 | 9.2877 | 13.4315 | 15.4315 | 10.1438 | 19.4315 | 32.863 | 48.2945 | 8.2977 | 10.1438 | 10.2877 | 9.2877 | 13.4315 | 15.4315 | 10.1438 | 19.4315 | 32.863 | 48.2945 | 0
5.1521 | 8.576 | 7.1521 | 6.1521 | 8.7281 | 10.7281 | 8.576 | 14.7281 | 23.4562 | 34.1843 | 5.1621 | 8.576 | 7.1521 | 6.1521 | 8.7281 | 10.7281 | 8.576 | 14.7281 | 23.4562 | 34.1843 | 0
7.8614 | 9.9307 | 9.8614 | 8.8614 | 12.7921 | 14.7921 | 9.9307 | 18.7921 | 31.5843 | 46.3764 | 7.8714 | 9.9307 | 9.8614 | 8.8614 | 12.7921 | 14.7921 | 9.9307 | 18.7921 | 31.5843 | 46.3764 | 0
7.2199 | 9.61 | 9.2199 | 8.2199 | 11.8299 | 13.8299 | 9.61 | 17.8299 | 29.6598 | 43.4897 | 7.2299 | 9.61 | 9.2199 | 8.2199 | 11.8299 | 13.8299 | 9.61 | 17.8299 | 29.6598 | 43.4897 | 0
5.6179 | 8.8089 | 7.6179 | 6.6179 | 9.4268 | 11.4268 | 8.8089 | 15.4268 | 24.8536 | 36.2804 | 5.6279 | 8.8089 | 7.6179 | 6.6179 | 9.4268 | 11.4268 | 8.8089 | 15.4268 | 24.8536 | 36.2804 | 0
2.7189 | 7.3595 | 4.7189 | 3.7189 | 5.0784 | 7.0784 | 7.3595 | 11.0784 | 16.1568 | 23.2352 | 2.7289 | 7.3595 | 4.7189 | 3.7189 | 5.0784 | 7.0784 | 7.3595 | 11.0784 | 16.1568 | 23.2352 | 0
7.0937 | 9.5468 | 9.0937 | 8.0937 | 11.6405 | 13.6405 | 9.5468 | 17.6405 | 29.281 | 42.9215 | 7.1037 | 9.5468 | 9.0937 | 8.0937 | 11.6405 | 13.6405 | 9.5468 | 17.6405 | 29.281 | 42.9215 | 0
6.5789 | 9.2894 | 8.5789 | 7.5789 | 10.8683 | 12.8683 | 9.2894 | 16.8683 | 27.7367 | 40.605 | 6.5889 | 9.2894 | 8.5789 | 7.5789 | 10.8683 | 12.8683 | 9.2894 | 16.8683 | 27.7367 | 40.605 | 0
4.9738 | 8.4869 | 6.9738 | 5.9738 | 8.4606 | 10.4606 | 8.4869 | 14.4606 | 22.9213 | 33.3819 | 4.9838 | 8.4869 | 6.9738 | 5.9738 | 8.4606 | 10.4606 | 8.4869 | 14.4606 | 22.9213 | 33.3819 | 0
5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 5.4043 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 0
3.3249 | 7.6624 | 5.3249 | 4.3249 | 5.9873 | 7.9873 | 7.6624 | 11.9873 | 17.9746 | 25.9618 | 3.3349 | 7.6624 | 5.3249 | 4.3249 | 5.9873 | 7.9873 | 7.6624 | 11.9873 | 17.9746 | 25.9618 | 0
5.9637 | 8.9818 | 7.9637 | 6.9637 | 9.9455 | 11.9455 | 8.9818 | 15.9455 | 25.891 | 37.8365 | 5.9737 | 8.9818 | 7.9637 | 6.9637 | 9.9455 | 11.9455 | 8.9818 | 15.9455 | 25.891 | 37.8365 | 0
3.7881 | 7.894 | 5.7881 | 4.7881 | 6.6821 | 8.6821 | 7.894 | 12.6821 | 19.3643 | 28.0464 | 3.7981 | 7.894 | 5.7881 | 4.7881 | 6.6821 | 8.6821 | 7.894 | 12.6821 | 19.3643 | 28.0464 | 0
8.004 | 10.002 | 10.004 | 9.004 | 13.0059 | 15.0059 | 10.002 | 19.0059 | 32.0119 | 47.0178 | 8.014 | 10.002 | 10.004 | 9.004 | 13.0059 | 15.0059 | 10.002 | 19.0059 | 32.0119 | 47.0178 | 0
7.6199 | 9.8099 | 9.6199 | 8.6199 | 12.4298 | 14.4298 | 9.8099 | 18.4298 | 30.8596 | 45.2893 | 7.6299 | 9.8099 | 9.6199 | 8.6199 | 12.4298 | 14.4298 | 9.8099 | 18.4298 | 30.8596 | 45.2893 | 0
5.0882 | 8.5441 | 7.0882 | 6.0882 | 8.6323 | 10.6323 | 8.5441 | 14.6323 | 23.2646 | 33.8968 | 5.0982 | 8.5441 | 7.0882 | 6.0882 | 8.6323 | 10.6323 | 8.5441 | 14.6323 | 23.2646 | 33.8968 | 0
4.9297 | 8.4649 | 6.9297 | 5.9297 | 8.3946 | 10.3946 | 8.4649 | 14.3946 | 22.7891 | 33.1837 | 4.9397 | 8.4649 | 6.9297 | 5.9297 | 8.3946 | 10.3946 | 8.4649 | 14.3946 | 22.7891 | 33.1837 | 0
1.9638 | 6.9819 | 3.9638 | 2.9638 | 3.9457 | 5.9457 | 6.9819 | 9.9457 | 13.8914 | 19.8371 | 1.9738 | 6.9819 | 3.9638 | 2.9638 | 3.9457 | 5.9457 | 6.9819 | 9.9457 | 13.8914 | 19.8371 | 0
5.227 | 8.6135 | 7.227 | 6.227 | 8.8405 | 10.8405 | 8.6135 | 14.8405 | 23.6809 | 34.5214 | 5.237 | 8.6135 | 7.227 | 6.227 | 8.8405 | 10.8405 | 8.6135 | 14.8405 | 23.6809 | 34.5214 | 0
2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 2.9938 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 0
6.9433 | 9.4717 | 8.9433 | 7.9433 | 11.415 | 13.415 | 9.4717 | 17.415 | 28.83 | 42.245 | 6.9533 | 9.4717 | 8.9433 | 7.9433 | 11.415 | 13.415 | 9.4717 | 17.415 | 28.83 | 42.245 | 0
5.765 | 8.8825 | 7.765 | 6.765 | 9.6475 | 11.6475 | 8.8825 | 15.6475 | 25.295 | 36.9425 | 5.775 | 8.8825 | 7.765 | 6.765 | 9.6475 | 11.6475 | 8.8825 | 15.6475 | 25.295 | 36.9425 | 0
2.6494 | 7.3247 | 4.6494 | 3.6494 | 4.9741 | 6.9741 | 7.3247 | 10.9741 | 15.9482 | 22.9223 | 2.6594 | 7.3247 | 4.6494 | 3.6494 | 4.9741 | 6.9741 | 7.3247 | 10.9741 | 15.9482 | 22.9223 | 0
7.3038 | 9.6519 | 9.3038 | 8.3038 | 11.9556 | 13.9556 | 9.6519 | 17.9556 | 29.9113 | 43.8669 | 7.3138 | 9.6519 | 9.3038 | 8.3038 | 11.9556 | 13.9556 | 9.6519 | 17.9556 | 29.9113 | 43.8669 | 0
3.554 | 7.777 | 5.554 | 4.554 | 6.3309 | 8.3309 | 7.777 | 12.3309 | 18.6619 | 26.9928 | 3.564 | 7.777 | 5.554 | 4.554 | 6.3309 | 8.3309 | 7.777 | 12.3309 | 18.6619 | 26.9928 | 0
5.9113 | 8.9557 | 7.9113 | 6.9113 | 9.867 | 11.867 | 8.9557 | 15.867 | 25.7339 | 37.6009 | 5.9213 | 8.9557 | 7.9113 | 6.9113 | 9.867 | 11.867 | 8.9557 | 15.867 | 25.7339 | 37.6009 | 0
8.773 | 10.3865 | 10.773 | 9.773 | 14.1595 | 16.1595 | 10.3865 | 20.1595 | 34.319 | 50.4785 | 8.783 | 10.3865 | 10.773 | 9.773 | 14.1595 | 16.1595 | 10.3865 | 20.1595 | 34.319 | 50.4785 | 0
6.175 | 9.0875 | 8.175 | 7.175 | 10.2625 | 12.2625 | 9.0875 | 16.2625 | 26.5251 | 38.7876 | 6.185 | 9.0875 | 8.175 | 7.175 | 10.2625 | 12.2625 | 9.0875 | 16.2625 | 26.5251 | 38.7876 | 0
7.0464 | 9.5232 | 9.0464 | 8.0464 | 11.5695 | 13.5695 | 9.5232 | 17.5695 | 29.1391 | 42.7086 | 7.0564 | 9.5232 | 9.0464 | 8.0464 | 11.5695 | 13.5695 | 9.5232 | 17.5695 | 29.1391 | 42.7086 | 0
4.9413 | 8.4707 | 6.9413 | 5.9413 | 8.412 | 10.412 | 8.4707 | 14.412 | 22.824 | 33.236 | 4.9513 | 8.4707 | 6.9413 | 5.9413 | 8.412 | 10.412 | 8.4707 | 14.412 | 22.824 | 33.236 | 0
4.8679 | 8.434 | 6.8679 | 5.8679 | 8.3019 | 10.3019 | 8.434 | 14.3019 | 22.6038 | 32.9057 | 4.8779 | 8.434 | 6.8679 | 5.8679 | 8.3019 | 10.3019 | 8.434 | 14.3019 | 22.6038 | 32.9057 | 0
4.8742 | 8.4371 | 6.8742 | 5.8742 | 8.3113 | 10.3113 | 8.4371 | 14.3113 | 22.6226 | 32.9339 | 4.8842 | 8.4371 | 6.8742 | 5.8742 | 8.3113 | 10.3113 | 8.4371 | 14.3113 | 22.6226 | 32.9339 | 0
9.329 | 10.6645 | 11.329 | 10.329 | 14.9935 | 16.9935 | 10.6645 | 20.9935 | 35.987 | 52.9806 | 9.339 | 10.6645 | 11.329 | 10.329 | 14.9935 | 16.9935 | 10.6645 | 20.9935 | 35.987 | 52.9806 | 0
7.5224 | 9.7612 | 9.5224 | 8.5224 | 12.2836 | 14.2836 | 9.7612 | 18.2836 | 30.5671 | 44.8507 | 7.5324 | 9.7612 | 9.5224 | 8.5224 | 12.2836 | 14.2836 | 9.7612 | 18.2836 | 30.5671 | 44.8507 | 0
8.1979 | 10.0989 | 10.1979 | 9.1979 | 13.2968 | 15.2968 | 10.0989 | 19.2968 | 32.5936 | 47.8904 | 8.2079 | 10.0989 | 10.1979 | 9.1979 | 13.2968 | 15.2968 | 10.0989 | 19.2968 | 32.5936 | 47.8904 | 0
5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 5.2296 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 0
8.1953 | 10.0977 | 10.1953 | 9.1953 | 13.293 | 15.293 | 10.0977 | 19.293 | 32.586 | 47.8791 | 8.2053 | 10.0977 | 10.1953 | 9.1953 | 13.293 | 15.293 | 10.0977 | 19.293 | 32.586 | 47.8791 | 0
4.9143 | 8.4572 | 6.9143 | 5.9143 | 8.3715 | 10.3715 | 8.4572 | 14.3715 | 22.7429 | 33.1144 | 4.9243 | 8.4572 | 6.9143 | 5.9143 | 8.3715 | 10.3715 | 8.4572 | 14.3715 | 22.7429 | 33.1144 | 0
8.9991 | 10.4995 | 10.9991 | 9.9991 | 14.4986 | 16.4986 | 10.4995 | 20.4986 | 34.9973 | 51.4959 | 9.0091 | 10.4995 | 10.9991 | 9.9991 | 14.4986 | 16.4986 | 10.4995 | 20.4986 | 34.9973 | 51.4959 | 0
3.9365 | 7.9683 | 5.9365 | 4.9365 | 6.9048 | 8.9048 | 7.9683 | 12.9048 | 19.8096 | 28.7143 | 3.9465 | 7.9683 | 5.9365 | 4.9365 | 6.9048 | 8.9048 | 7.9683 | 12.9048 | 19.8096 | 28.7143 | 0
7.8134 | 9.9067 | 9.8134 | 8.8134 | 12.7201 | 14.7201 | 9.9067 | 18.7201 | 31.4401 | 46.1602 | 7.8234 | 9.9067 | 9.8134 | 8.8134 | 12.7201 | 14.7201 | 9.9067 | 18.7201 | 31.4401 | 46.1602 | 0
4.0634 | 8.0317 | 6.0634 | 5.0634 | 7.0951 | 9.0951 | 8.0317 | 13.0951 | 20.1902 | 29.2853 | 4.0734 | 8.0317 | 6.0634 | 5.0634 | 7.0951 | 9.0951 | 8.0317 | 13.0951 | 20.1902 | 29.2853 | 0
6.7403 | 9.3702 | 8.7403 | 7.7403 | 11.1105 | 13.1105 | 9.3702 | 17.1105 | 28.221 | 41.3314 | 6.7503 | 9.3702 | 8.7403 | 7.7403 | 11.1105 | 13.1105 | 9.3702 | 17.1105 | 28.221 | 41.3314 | 0
5.6408 | 8.8204 | 7.6408 | 6.6408 | 9.4611 | 11.4611 | 8.8204 | 15.4611 | 24.9223 | 36.3834 | 5.6508 | 8.8204 | 7.6408 | 6.6408 | 9.4611 | 11.4611 | 8.8204 | 15.4611 | 24.9223 | 36.3834 | 0
6.2507 | 9.1254 | 8.2507 | 7.2507 | 10.3761 | 12.3761 | 9.1254 | 16.3761 | 26.7522 | 39.1283 | 6.2607 | 9.1254 | 8.2507 | 7.2507 | 10.3761 | 12.3761 | 9.1254 | 16.3761 | 26.7522 | 39.1283 | 0
8.3342 | 10.1671 | 10.3342 | 9.3342 | 13.5013 | 15.5013 | 10.1671 | 19.5013 | 33.0026 | 48.5039 | 8.3442 | 10.1671 | 10.3342 | 9.3342 | 13.5013 | 15.5013 | 10.1671 | 19.5013 | 33.0026 | 48.5039 | 0
9.8378 | 10.9189 | 11.8378 | 10.8378 | 15.7567 | 17.7567 | 10.9189 | 21.7567 | 37.5135 | 55.2702 | 9.8478 | 10.9189 | 11.8378 | 10.8378 | 15.7567 | 17.7567 | 10.9189 | 21.7567 | 37.5135 | 55.2702 | 0
5.9193 | 8.9596 | 7.9193 | 6.9193 | 9.8789 | 11.8789 | 8.9596 | 15.8789 | 25.7578 | 37.6367 | 5.9293 | 8.9596 | 7.9193 | 6.9193 | 9.8789 | 11.8789 | 8.9596 | 15.8789 | 25.7578 | 37.6367 | 0
9.7806 | 10.8903 | 11.7806 | 10.7806 | 15.6709 | 17.6709 | 10.8903 | 21.6709 | 37.3418 | 55.0127 | 9.7906 | 10.8903 | 11.7806 | 10.7806 | 15.6709 | 17.6709 | 10.8903 | 21.6709 | 37.3418 | 55.0127 | 0
7.2998 | 9.6499 | 9.2998 | 8.2998 | 11.9497 | 13.9497 | 9.6499 | 17.9497 | 29.8993 | 43.849 | 7.3098 | 9.6499 | 9.2998 | 8.2998 | 11.9497 | 13.9497 | 9.6499 | 17.9497 | 29.8993 | 43.849 | 0
5.2258 | 8.6129 | 7.2258 | 6.2258 | 8.8387 | 10.8387 | 8.6129 | 14.8387 | 23.6775 | 34.5162 | 5.2358 | 8.6129 | 7.2258 | 6.2258 | 8.8387 | 10.8387 | 8.6129 | 14.8387 | 23.6775 | 34.5162 | 0
5.5571 | 8.7785 | 7.5571 | 6.5571 | 9.3356 | 11.3356 | 8.7785 | 15.3356 | 24.6712 | 36.0068 | 5.5671 | 8.7785 | 7.5571 | 6.5571 | 9.3356 | 11.3356 | 8.7785 | 15.3356 | 24.6712 | 36.0068 | 0
3.6445 | 7.8223 | 5.6445 | 4.6445 | 6.4668 | 8.4668 | 7.8223 | 12.4668 | 18.9335 | 27.4003 | 3.6545 | 7.8223 | 5.6445 | 4.6445 | 6.4668 | 8.4668 | 7.8223 | 12.4668 | 18.9335 | 27.4003 | 0
4.0026 | 8.0013 | 6.0026 | 5.0026 | 7.0039 | 9.0039 | 8.0013 | 13.0039 | 20.0078 | 29.0117 | 4.0126 | 8.0013 | 6.0026 | 5.0026 | 7.0039 | 9.0039 | 8.0013 | 13.0039 | 20.0078 | 29.0117 | 0
6.0532 | 9.0266 | 8.0532 | 7.0532 | 10.0798 | 12.0798 | 9.0266 | 16.0798 | 26.1595 | 38.2393 | 6.0632 | 9.0266 | 8.0532 | 7.0532 | 10.0798 | 12.0798 | 9.0266 | 16.0798 | 26.1595 | 38.2393 | 0
6.9761 | 9.4881 | 8.9761 | 7.9761 | 11.4642 | 13.4642 | 9.4881 | 17.4642 | 28.9284 | 42.3925 | 6.9861 | 9.4881 | 8.9761 | 7.9761 | 11.4642 | 13.4642 | 9.4881 | 17.4642 | 28.9284 | 42.3925 | 0
2.4113 | 7.2056 | 4.4113 | 3.4113 | 4.6169 | 6.6169 | 7.2056 | 10.6169 | 15.2338 | 21.8508 | 2.4213 | 7.2056 | 4.4113 | 3.4113 | 4.6169 | 6.6169 | 7.2056 | 10.6169 | 15.2338 | 21.8508 | 0
3.7525 | 7.8762 | 5.7525 | 4.7525 | 6.6287 | 8.6287 | 7.8762 | 12.6287 | 19.2575 | 27.8862 | 3.7625 | 7.8762 | 5.7525 | 4.7525 | 6.6287 | 8.6287 | 7.8762 | 12.6287 | 19.2575 | 27.8862 | 0
6.4384 | 9.2192 | 8.4384 | 7.4384 | 10.6576 | 12.6576 | 9.2192 | 16.6576 | 27.3151 | 39.9727 | 6.4484 | 9.2192 | 8.4384 | 7.4384 | 10.6576 | 12.6576 | 9.2192 | 16.6576 | 27.3151 | 39.9727 | 0
1.4433 | 6.7216 | 3.4433 | 2.4433 | 3.1649 | 5.1649 | 6.7216 | 9.1649 | 12.3299 | 17.4948 | 1.4533 | 6.7216 | 3.4433 | 2.4433 | 3.1649 | 5.1649 | 6.7216 | 9.1649 | 12.3299 | 17.4948 | 0
7.9113 | 9.9557 | 9.9113 | 8.9113 | 12.867 | 14.867 | 9.9557 | 18.867 | 31.734 | 46.6009 | 7.9213 | 9.9557 | 9.9113 | 8.9113 | 12.867 | 14.867 | 9.9557 | 18.867 | 31.734 | 46.6009 | 0
4.1557 | 8.0779 | 6.1557 | 5.1557 | 7.2336 | 9.2336 | 8.0779 | 13.2336 | 20.4672 | 29.7007 | 4.1657 | 8.0779 | 6.1557 | 5.1557 | 7.2336 | 9.2336 | 8.0779 | 13.2336 | 20.4672 | 29.7007 | 0
9.7438 | 10.8719 | 11.7438 | 10.7438 | 15.6157 | 17.6157 | 10.8719 | 21.6157 | 37.2314 | 54.8471 | 9.7538 | 10.8719 | 11.7438 | 10.7438 | 15.6157 | 17.6157 | 10.8719 | 21.6157 | 37.2314 | 54.8471 | 0
8.0146 | 10.0073 | 10.0146 | 9.0146 | 13.0219 | 15.0219 | 10.0073 | 19.0219 | 32.0438 | 47.0657 | 8.0246 | 10.0073 | 10.0146 | 9.0146 | 13.0219 | 15.0219 | 10.0073 | 19.0219 | 32.0438 | 47.0657 | 0
7.2032 | 9.6016 | 9.2032 | 8.2032 | 11.8048 | 13.8048 | 9.6016 | 17.8048 | 29.6096 | 43.4144 | 7.2132 | 9.6016 | 9.2032 | 8.2032 | 11.8048 | 13.8048 | 9.6016 | 17.8048 | 29.6096 | 43.4144 | 0
5.1038 | 8.5519 | 7.1038 | 6.1038 | 8.6557 | 10.6557 | 8.5519 | 14.6557 | 23.3113 | 33.967 | 5.1138 | 8.5519 | 7.1038 | 6.1038 | 8.6557 | 10.6557 | 8.5519 | 14.6557 | 23.3113 | 33.967 | 0
10.3046 | 11.1523 | 12.3046 | 11.3046 | 16.4569 | 18.4569 | 11.1523 | 22.4569 | 38.9138 | 57.3707 | 10.3146 | 11.1523 | 12.3046 | 11.3046 | 16.4569 | 18.4569 | 11.1523 | 22.4569 | 38.9138 | 57.3707 | 0
6.0128 | 9.0064 | 8.0128 | 7.0128 | 10.0192 | 12.0192 | 9.0064 | 16.0192 | 26.0383 | 38.0575 | 6.0228 | 9.0064 | 8.0128 | 7.0128 | 10.0192 | 12.0192 | 9.0064 | 16.0192 | 26.0383 | 38.0575 | 0
5.3452 | 8.6726 | 7.3452 | 6.3452 | 9.0178 | 11.0178 | 8.6726 | 15.0178 | 24.0356 | 35.0535 | 5.3552 | 8.6726 | 7.3452 | 6.3452 | 9.0178 | 11.0178 | 8.6726 | 15.0178 | 24.0356 | 35.0535 | 0
5.0104 | 8.5052 | 7.0104 | 6.0104 | 8.5156 | 10.5156 | 8.5052 | 14.5156 | 23.0312 | 33.5469 | 5.0204 | 8.5052 | 7.0104 | 6.0104 | 8.5156 | 10.5156 | 8.5052 | 14.5156 | 23.0312 | 33.5469 | 0
8.5886 | 10.2943 | 10.5886 | 9.5886 | 13.8829 | 15.8829 | 10.2943 | 19.8829 | 33.7658 | 49.6487 | 8.5986 | 10.2943 | 10.5886 | 9.5886 | 13.8829 | 15.8829 | 10.2943 | 19.8829 | 33.7658 | 49.6487 | 0
4.7374 | 8.3687 | 6.7374 | 5.7374 | 8.1061 | 10.1061 | 8.3687 | 14.1061 | 22.2122 | 32.3184 | 4.7474 | 8.3687 | 6.7374 | 5.7374 | 8.1061 | 10.1061 | 8.3687 | 14.1061 | 22.2122 | 32.3184 | 0
4.205 | 8.1025 | 6.205 | 5.205 | 7.3075 | 9.3075 | 8.1025 | 13.3075 | 20.6151 | 29.9226 | 4.215 | 8.1025 | 6.205 | 5.205 | 7.3075 | 9.3075 | 8.1025 | 13.3075 | 20.6151 | 29.9226 | 0
6.7811 | 9.3906 | 8.7811 | 7.7811 | 11.1717 | 13.1717 | 9.3906 | 17.1717 | 28.3433 | 41.515 | 6.7911 | 9.3906 | 8.7811 | 7.7811 | 11.1717 | 13.1717 | 9.3906 | 17.1717 | 28.3433 | 41.515 | 0
5.058 | 8.529 | 7.058 | 6.058 | 8.5871 | 10.5871 | 8.529 | 14.5871 | 23.1741 | 33.7612 | 5.068 | 8.529 | 7.058 | 6.058 | 8.5871 | 10.5871 | 8.529 | 14.5871 | 23.1741 | 33.7612 | 0
5.1781 | 8.5891 | 7.1781 | 6.1781 | 8.7672 | 10.7672 | 8.5891 | 14.7672 | 23.5343 | 34.3015 | 5.1881 | 8.5891 | 7.1781 | 6.1781 | 8.7672 | 10.7672 | 8.5891 | 14.7672 | 23.5343 | 34.3015 | 0
2.0437 | 7.0219 | 4.0437 | 3.0437 | 4.0656 | 6.0656 | 7.0219 | 10.0656 | 14.1312 | 20.1968 | 2.0537 | 7.0219 | 4.0437 | 3.0437 | 4.0656 | 6.0656 | 7.0219 | 10.0656 | 14.1312 | 20.1968 | 0
7.546 | 9.773 | 9.546 | 8.546 | 12.319 | 14.319 | 9.773 | 18.319 | 30.6379 | 44.9569 | 7.556 | 9.773 | 9.546 | 8.546 | 12.319 | 14.319 | 9.773 | 18.319 | 30.6379 | 44.9569 | 0
5.6743 | 8.8371 | 7.6743 | 6.6743 | 9.5114 | 11.5114 | 8.8371 | 15.5114 | 25.0229 | 36.5343 | 5.6843 | 8.8371 | 7.6743 | 6.6743 | 9.5114 | 11.5114 | 8.8371 | 15.5114 | 25.0229 | 36.5343 | 0
4.0812 | 8.0406 | 6.0812 | 5.0812 | 7.1218 | 9.1218 | 8.0406 | 13.1218 | 20.2435 | 29.3653 | 4.0912 | 8.0406 | 6.0812 | 5.0812 | 7.1218 | 9.1218 | 8.0406 | 13.1218 | 20.2435 | 29.3653 | 0
9.5518 | 10.7759 | 11.5518 | 10.5518 | 15.3277 | 17.3277 | 10.7759 | 21.3277 | 36.6555 | 53.9832 | 9.5618 | 10.7759 | 11.5518 | 10.5518 | 15.3277 | 17.3277 | 10.7759 | 21.3277 | 36.6555 | 53.9832 | 0
7.9334 | 9.9667 | 9.9334 | 8.9334 | 12.9001 | 14.9001 | 9.9667 | 18.9001 | 31.8003 | 46.7004 | 7.9434 | 9.9667 | 9.9334 | 8.9334 | 12.9001 | 14.9001 | 9.9667 | 18.9001 | 31.8003 | 46.7004 | 0
4.7753 | 8.3876 | 6.7753 | 5.7753 | 8.1629 | 10.1629 | 8.3876 | 14.1629 | 22.3258 | 32.4888 | 4.7853 | 8.3876 | 6.7753 | 5.7753 | 8.1629 | 10.1629 | 8.3876 | 14.1629 | 22.3258 | 32.4888 | 0
8.5211 | 10.2606 | 10.5211 | 9.5211 | 13.7817 | 15.7817 | 10.2606 | 19.7817 | 33.5634 | 49.3451 | 8.5311 | 10.2606 | 10.5211 | 9.5211 | 13.7817 | 15.7817 | 10.2606 | 19.7817 | 33.5634 | 49.3451 | 0
5.7198 | 8.8599 | 7.7198 | 6.7198 | 9.5797 | 11.5797 | 8.8599 | 15.5797 | 25.1594 | 36.7391 | 5.7298 | 8.8599 | 7.7198 | 6.7198 | 9.5797 | 11.5797 | 8.8599 | 15.5797 | 25.1594 | 36.7391 | 0
4.9962 | 8.4981 | 6.9962 | 5.9962 | 8.4943 | 10.4943 | 8.4981 | 14.4943 | 22.9886 | 33.4829 | 5.0062 | 8.4981 | 6.9962 | 5.9962 | 8.4943 | 10.4943 | 8.4981 | 14.4943 | 22.9886 | 33.4829 | 0
5.1437 | 8.5718 | 7.1437 | 6.1437 | 8.7155 | 10.7155 | 8.5718 | 14.7155 | 23.4311 | 34.1466 | 5.1537 | 8.5718 | 7.1437 | 6.1437 | 8.7155 | 10.7155 | 8.5718 | 14.7155 | 23.4311 | 34.1466 | 0
5.9165 | 8.9583 | 7.9165 | 6.9165 | 9.8748 | 11.8748 | 8.9583 | 15.8748 | 25.7496 | 37.6243 | 5.9265 | 8.9583 | 7.9165 | 6.9165 | 9.8748 | 11.8748 | 8.9583 | 15.8748 | 25.7496 | 37.6243 | 0
6.5709 | 9.2855 | 8.5709 | 7.5709 | 10.8564 | 12.8564 | 9.2855 | 16.8564 | 27.7128 | 40.5691 | 6.5809 | 9.2855 | 8.5709 | 7.5709 | 10.8564 | 12.8564 | 9.2855 | 16.8564 | 27.7128 | 40.5691 | 0
4.407 | 8.2035 | 6.407 | 5.407 | 7.6105 | 9.6105 | 8.2035 | 13.6105 | 21.2209 | 30.8314 | 4.417 | 8.2035 | 6.407 | 5.407 | 7.6105 | 9.6105 | 8.2035 | 13.6105 | 21.2209 | 30.8314 | 0
7.6827 | 9.8413 | 9.6827 | 8.6827 | 12.524 | 14.524 | 9.8413 | 18.524 | 31.048 | 45.572 | 7.6927 | 9.8413 | 9.6827 | 8.6827 | 12.524 | 14.524 | 9.8413 | 18.524 | 31.048 | 45.572 | 0
5.0637 | 8.5318 | 7.0637 | 6.0637 | 8.5955 | 10.5955 | 8.5318 | 14.5955 | 23.191 | 33.7865 | 5.0737 | 8.5318 | 7.0637 | 6.0637 | 8.5955 | 10.5955 | 8.5318 | 14.5955 | 23.191 | 33.7865 | 0
3.1421 | 7.5711 | 5.1421 | 4.1421 | 5.7132 | 7.7132 | 7.5711 | 11.7132 | 17.4263 | 25.1395 | 3.1521 | 7.5711 | 5.1421 | 4.1421 | 5.7132 | 7.7132 | 7.5711 | 11.7132 | 17.4263 | 25.1395 | 0
8.3315 | 10.1657 | 10.3315 | 9.3315 | 13.4972 | 15.4972 | 10.1657 | 19.4972 | 32.9944 | 48.4916 | 8.3415 | 10.1657 | 10.3315 | 9.3315 | 13.4972 | 15.4972 | 10.1657 | 19.4972 | 32.9944 | 48.4916 | 0
7.0219 | 9.5109 | 9.0219 | 8.0219 | 11.5328 | 13.5328 | 9.5109 | 17.5328 | 29.0656 | 42.5985 | 7.0319 | 9.5109 | 9.0219 | 8.0219 | 11.5328 | 13.5328 | 9.5109 | 17.5328 | 29.0656 | 42.5985 | 0
7.4577 | 9.7289 | 9.4577 | 8.4577 | 12.1866 | 14.1866 | 9.7289 | 18.1866 | 30.3732 | 44.5599 | 7.4677 | 9.7289 | 9.4577 | 8.4577 | 12.1866 | 14.1866 | 9.7289 | 18.1866 | 30.3732 | 44.5599 | 0
8.7512 | 10.3756 | 10.7512 | 9.7512 | 14.1268 | 16.1268 | 10.3756 | 20.1268 | 34.2535 | 50.3803 | 8.7612 | 10.3756 | 10.7512 | 9.7512 | 14.1268 | 16.1268 | 10.3756 | 20.1268 | 34.2535 | 50.3803 | 0
3.186 | 7.593 | 5.186 | 4.186 | 5.779 | 7.779 | 7.593 | 11.779 | 17.558 | 25.337 | 3.196 | 7.593 | 5.186 | 4.186 | 5.779 | 7.779 | 7.593 | 11.779 | 17.558 | 25.337 | 0
3.9737 | 7.9868 | 5.9737 | 4.9737 | 6.9605 | 8.9605 | 7.9868 | 12.9605 | 19.921 | 28.8815 | 3.9837 | 7.9868 | 5.9737 | 4.9737 | 6.9605 | 8.9605 | 7.9868 | 12.9605 | 19.921 | 28.8815 | 0
6.1466 | 9.0733 | 8.1466 | 7.1466 | 10.2199 | 12.2199 | 9.0733 | 16.2199 | 26.4399 | 38.6598 | 6.1566 | 9.0733 | 8.1466 | 7.1466 | 10.2199 | 12.2199 | 9.0733 | 16.2199 | 26.4399 | 38.6598 | 0
4.2176 | 8.1088 | 6.2176 | 5.2176 | 7.3264 | 9.3264 | 8.1088 | 13.3264 | 20.6527 | 29.9791 | 4.2276 | 8.1088 | 6.2176 | 5.2176 | 7.3264 | 9.3264 | 8.1088 | 13.3264 | 20.6527 | 29.9791 | 0
6.6912 | 9.3456 | 8.6912 | 7.6912 | 11.0368 | 13.0368 | 9.3456 | 17.0368 | 28.0737 | 41.1105 | 6.7012 | 9.3456 | 8.6912 | 7.6912 | 11.0368 | 13.0368 | 9.3456 | 17.0368 | 28.0737 | 41.1105 | 0
4.7236 | 8.3618 | 6.7236 | 5.7236 | 8.0853 | 10.0853 | 8.3618 | 14.0853 | 22.1707 | 32.256 | 4.7336 | 8.3618 | 6.7236 | 5.7236 | 8.0853 | 10.0853 | 8.3618 | 14.0853 | 22.1707 | 32.256 | 0
4.7267 | 8.3634 | 6.7267 | 5.7267 | 8.0901 | 10.0901 | 8.3634 | 14.0901 | 22.1802 | 32.2704 | 4.7367 | 8.3634 | 6.7267 | 5.7267 | 8.0901 | 10.0901 | 8.3634 | 14.0901 | 22.1802 | 32.2704 | 0
7.199 | 9.5995 | 9.199 | 8.199 | 11.7985 | 13.7985 | 9.5995 | 17.7985 | 29.5969 | 43.3954 | 7.209 | 9.5995 | 9.199 | 8.199 | 11.7985 | 13.7985 | 9.5995 | 17.7985 | 29.5969 | 43.3954 | 0
3.7067 | 7.8534 | 5.7067 | 4.7067 | 6.5601 | 8.5601 | 7.8534 | 12.5601 | 19.1202 | 27.6803 | 3.7167 | 7.8534 | 5.7067 | 4.7067 | 6.5601 | 8.5601 | 7.8534 | 12.5601 | 19.1202 | 27.6803 | 0
5.995 | 8.9975 | 7.995 | 6.995 | 9.9925 | 11.9925 | 8.9975 | 15.9925 | 25.9851 | 37.9776 | 6.005 | 8.9975 | 7.995 | 6.995 | 9.9925 | 11.9925 | 8.9975 | 15.9925 | 25.9851 | 37.9776 | 0
5.0831 | 8.5415 | 7.0831 | 6.0831 | 8.6246 | 10.6246 | 8.5415 | 14.6246 | 23.2493 | 33.8739 | 5.0931 | 8.5415 | 7.0831 | 6.0831 | 8.6246 | 10.6246 | 8.5415 | 14.6246 | 23.2493 | 33.8739 | 0
6.1092 | 9.0546 | 8.1092 | 7.1092 | 10.1638 | 12.1638 | 9.0546 | 16.1638 | 26.3277 | 38.4915 | 6.1192 | 9.0546 | 8.1092 | 7.1092 | 10.1638 | 12.1638 | 9.0546 | 16.1638 | 26.3277 | 38.4915 | 0
8.5861 | 10.2931 | 10.5861 | 9.5861 | 13.8792 | 15.8792 | 10.2931 | 19.8792 | 33.7584 | 49.6375 | 8.5961 | 10.2931 | 10.5861 | 9.5861 | 13.8792 | 15.8792 | 10.2931 | 19.8792 | 33.7584 | 49.6375 | 0
5.3112 | 8.6556 | 7.3112 | 6.3112 | 8.9668 | 10.9668 | 8.6556 | 14.9668 | 23.9337 | 34.9005 | 5.3212 | 8.6556 | 7.3112 | 6.3112 | 8.9668 | 10.9668 | 8.6556 | 14.9668 | 23.9337 | 34.9005 | 0
3.0662 | 7.5331 | 5.0662 | 4.0662 | 5.5993 | 7.5993 | 7.5331 | 11.5993 | 17.1985 | 24.7978 | 3.0762 | 7.5331 | 5.0662 | 4.0662 | 5.5993 | 7.5993 | 7.5331 | 11.5993 | 17.1985 | 24.7978 | 0
5.713 | 8.8565 | 7.713 | 6.713 | 9.5695 | 11.5695 | 8.8565 | 15.5695 | 25.139 | 36.7085 | 5.723 | 8.8565 | 7.713 | 6.713 | 9.5695 | 11.5695 | 8.8565 | 15.5695 | 25.139 | 36.7085 | 0
2.1945 | 7.0972 | 4.1945 | 3.1945 | 4.2917 | 6.2917 | 7.0972 | 10.2917 | 14.5834 | 20.8751 | 2.2045 | 7.0972 | 4.1945 | 3.1945 | 4.2917 | 6.2917 | 7.0972 | 10.2917 | 14.5834 | 20.8751 | 0
4.0199 | 8.01 | 6.0199 | 5.0199 | 7.0299 | 9.0299 | 8.01 | 13.0299 | 20.0597 | 29.0896 | 4.0299 | 8.01 | 6.0199 | 5.0199 | 7.0299 | 9.0299 | 8.01 | 13.0299 | 20.0597 | 29.0896 | 0
6.6125 | 9.3062 | 8.6125 | 7.6125 | 10.9187 | 12.9187 | 9.3062 | 16.9187 | 27.8374 | 40.7562 | 6.6225 | 9.3062 | 8.6125 | 7.6125 | 10.9187 | 12.9187 | 9.3062 | 16.9187 | 27.8374 | 40.7562 | 0
6.4942 | 9.2471 | 8.4942 | 7.4942 | 10.7413 | 12.7413 | 9.2471 | 16.7413 | 27.4826 | 40.2239 | 6.5042 | 9.2471 | 8.4942 | 7.4942 | 10.7413 | 12.7413 | 9.2471 | 16.7413 | 27.4826 | 40.2239 | 0
5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 5.1021 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 0
5.964 | 8.982 | 7.964 | 6.964 | 9.946 | 11.946 | 8.982 | 15.946 | 25.8919 | 37.8379 | 5.974 | 8.982 | 7.964 | 6.964 | 9.946 | 11.946 | 8.982 | 15.946 | 25.8919 | 37.8379 | 0
5.7816 | 8.8908 | 7.7816 | 6.7816 | 9.6724 | 11.6724 | 8.8908 | 15.6724 | 25.3449 | 37.0173 | 5.7916 | 8.8908 | 7.7816 | 6.7816 | 9.6724 | 11.6724 | 8.8908 | 15.6724 | 25.3449 | 37.0173 | 0
3.5707 | 7.7853 | 5.5707 | 4.5707 | 6.356 | 8.356 | 7.7853 | 12.356 | 18.712 | 27.068 | 3.5807 | 7.7853 | 5.5707 | 4.5707 | 6.356 | 8.356 | 7.7853 | 12.356 | 18.712 | 27.068 | 0
3.9955 | 7.9978 | 5.9955 | 4.9955 | 6.9933 | 8.9933 | 7.9978 | 12.9933 | 19.9866 | 28.9799 | 4.0055 | 7.9978 | 5.9955 | 4.9955 | 6.9933 | 8.9933 | 7.9978 | 12.9933 | 19.9866 | 28.9799 | 0
6.0997 | 9.0499 | 8.0997 | 7.0997 | 10.1496 | 12.1496 | 9.0499 | 16.1496 | 26.2992 | 38.4487 | 6.1097 | 9.0499 | 8.0997 | 7.0997 | 10.1496 | 12.1496 | 9.0499 | 16.1496 | 26.2992 | 38.4487 | 0
7.8375 | 9.9188 | 9.8375 | 8.8375 | 12.7563 | 14.7563 | 9.9188 | 18.7563 | 31.5125 | 46.2688 | 7.8475 | 9.9188 | 9.8375 | 8.8375 | 12.7563 | 14.7563 | 9.9188 | 18.7563 | 31.5125 | 46.2688 | 0
6.5393 | 9.2696 | 8.5393 | 7.5393 | 10.8089 | 12.8089 | 9.2696 | 16.8089 | 27.6178 | 40.4267 | 6.5493 | 9.2696 | 8.5393 | 7.5393 | 10.8089 | 12.8089 | 9.2696 | 16.8089 | 27.6178 | 40.4267 | 0
3.8684 | 7.9342 | 5.8684 | 4.8684 | 6.8026 | 8.8026 | 7.9342 | 12.8026 | 19.6051 | 28.4077 | 3.8784 | 7.9342 | 5.8684 | 4.8684 | 6.8026 | 8.8026 | 7.9342 | 12.8026 | 19.6051 | 28.4077 | 0
5.8862 | 8.9431 | 7.8862 | 6.8862 | 9.8293 | 11.8293 | 8.9431 | 15.8293 | 25.6586 | 37.4878 | 5.8962 | 8.9431 | 7.8862 | 6.8862 | 9.8293 | 11.8293 | 8.9431 | 15.8293 | 25.6586 | 37.4878 | 0
4.754 | 8.377 | 6.754 | 5.754 | 8.131 | 10.131 | 8.377 | 14.131 | 22.262 | 32.3929 | 4.764 | 8.377 | 6.754 | 5.754 | 8.131 | 10.131 | 8.377 | 14.131 | 22.262 | 32.3929 | 0
3.8834 | 7.9417 | 5.8834 | 4.8834 | 6.8251 | 8.8251 | 7.9417 | 12.8251 | 19.6503 | 28.4754 | 3.8934 | 7.9417 | 5.8834 | 4.8834 | 6.8251 | 8.8251 | 7.9417 | 12.8251 | 19.6503 | 28.4754 | 0
5.5401 | 8.7701 | 7.5401 | 6.5401 | 9.3102 | 11.3102 | 8.7701 | 15.3102 | 24.6204 | 35.9306 | 5.5501 | 8.7701 | 7.5401 | 6.5401 | 9.3102 | 11.3102 | 8.7701 | 15.3102 | 24.6204 | 35.9306 | 0
6.0247 | 9.0124 | 8.0247 | 7.0247 | 10.0371 | 12.0371 | 9.0124 | 16.0371 | 26.0741 | 38.1112 | 6.0347 | 9.0124 | 8.0247 | 7.0247 | 10.0371 | 12.0371 | 9.0124 | 16.0371 | 26.0741 | 38.1112 | 0
4.9316 | 8.4658 | 6.9316 | 5.9316 | 8.3975 | 10.3975 | 8.4658 | 14.3975 | 22.7949 | 33.1924 | 4.9416 | 8.4658 | 6.9316 | 5.9316 | 8.3975 | 10.3975 | 8.4658 | 14.3975 | 22.7949 | 33.1924 | 0
9.3444 | 10.6722 | 11.3444 | 10.3444 | 15.0166 | 17.0166 | 10.6722 | 21.0166 | 36.0332 | 53.0498 | 9.3544 | 10.6722 | 11.3444 | 10.3444 | 15.0166 | 17.0166 | 10.6722 | 21.0166 | 36.0332 | 53.0498 | 0
6.4224 | 9.2112 | 8.4224 | 7.4224 | 10.6336 | 12.6336 | 9.2112 | 16.6336 | 27.2672 | 39.9008 | 6.4324 | 9.2112 | 8.4224 | 7.4224 | 10.6336 | 12.6336 | 9.2112 | 16.6336 | 27.2672 | 39.9008 | 0
5.0339 | 8.5169 | 7.0339 | 6.0339 | 8.5508 | 10.5508 | 8.5169 | 14.5508 | 23.1016 | 33.6524 | 5.0439 | 8.5169 | 7.0339 | 6.0339 | 8.5508 | 10.5508 | 8.5169 | 14.5508 | 23.1016 | 33.6524 | 0
5.9344 | 8.9672 | 7.9344 | 6.9344 | 9.9016 | 11.9016 | 8.9672 | 15.9016 | 25.8033 | 37.7049 | 5.9444 | 8.9672 | 7.9344 | 6.9344 | 9.9016 | 11.9016 | 8.9672 | 15.9016 | 25.8033 | 37.7049 | 0
6.8634 | 9.4317 | 8.8634 | 7.8634 | 11.295 | 13.295 | 9.4317 | 17.295 | 28.5901 | 41.8851 | 6.8734 | 9.4317 | 8.8634 | 7.8634 | 11.295 | 13.295 | 9.4317 | 17.295 | 28.5901 | 41.8851 | 0
3.9905 | 7.9952 | 5.9905 | 4.9905 | 6.9857 | 8.9857 | 7.9952 | 12.9857 | 19.9714 | 28.9572 | 4.0005 | 7.9952 | 5.9905 | 4.9905 | 6.9857 | 8.9857 | 7.9952 | 12.9857 | 19.9714 | 28.9572 | 0
7.2021 | 9.601 | 9.2021 | 8.2021 | 11.8031 | 13.8031 | 9.601 | 17.8031 | 29.6063 | 43.4094 | 7.2121 | 9.601 | 9.2021 | 8.2021 | 11.8031 | 13.8031 | 9.601 | 17.8031 | 29.6063 | 43.4094 | 0
0.53517 | 6.2676 | 2.5352 | 1.5352 | 1.8028 | 3.8028 | 6.2676 | 7.8028 | 9.6055 | 13.4083 | 0.54517 | 6.2676 | 2.5352 | 1.5352 | 1.8028 | 3.8028 | 6.2676 | 7.8028 | 9.6055 | 13.4083 | 0
5.5684 | 8.7842 | 7.5684 | 6.5684 | 9.3525 | 11.3525 | 8.7842 | 15.3525 | 24.7051 | 36.0576 | 5.5784 | 8.7842 | 7.5684 | 6.5684 | 9.3525 | 11.3525 | 8.7842 | 15.3525 | 24.7051 | 36.0576 | 0
5.3874 | 8.6937 | 7.3874 | 6.3874 | 9.081 | 11.081 | 8.6937 | 15.081 | 24.1621 | 35.2431 | 5.3974 | 8.6937 | 7.3874 | 6.3874 | 9.081 | 11.081 | 8.6937 | 15.081 | 24.1621 | 35.2431 | 0
6.5294 | 9.2647 | 8.5294 | 7.5294 | 10.7942 | 12.7942 | 9.2647 | 16.7942 | 27.5883 | 40.3825 | 6.5394 | 9.2647 | 8.5294 | 7.5294 | 10.7942 | 12.7942 | 9.2647 | 16.7942 | 27.5883 | 40.3825 | 0
8.7496 | 10.3748 | 10.7496 | 9.7496 | 14.1244 | 16.1244 | 10.3748 | 20.1244 | 34.2488 | 50.3732 | 8.7596 | 10.3748 | 10.7496 | 9.7496 | 14.1244 | 16.1244 | 10.3748 | 20.1244 | 34.2488 | 50.3732 | 0
5.9569 | 8.9785 | 7.9569 | 6.9569 | 9.9354 | 11.9354 | 8.9785 | 15.9354 | 25.8708 | 37.8062 | 5.9669 | 8.9785 | 7.9569 | 6.9569 | 9.9354 | 11.9354 | 8.9785 | 15.9354 | 25.8708 | 37.8062 | 0
5.1926 | 8.5963 | 7.1926 | 6.1926 | 8.7889 | 10.7889 | 8.5963 | 14.7889 | 23.5777 | 34.3666 | 5.2026 | 8.5963 | 7.1926 | 6.1926 | 8.7889 | 10.7889 | 8.5963 | 14.7889 | 23.5777 | 34.3666 | 0
4.5049 | 8.2524 | 6.5049 | 5.5049 | 7.7573 | 9.7573 | 8.2524 | 13.7573 | 21.5146 | 31.272 | 4.5149 | 8.2524 | 6.5049 | 5.5049 | 7.7573 | 9.7573 | 8.2524 | 13.7573 | 21.5146 | 31.272 | 0
4.4453 | 8.2227 | 6.4453 | 5.4453 | 7.668 | 9.668 | 8.2227 | 13.668 | 21.336 | 31.004 | 4.4553 | 8.2227 | 6.4453 | 5.4453 | 7.668 | 9.668 | 8.2227 | 13.668 | 21.336 | 31.004 | 0
8.9107 | 10.4553 | 10.9107 | 9.9107 | 14.366 | 16.366 | 10.4553 | 20.366 | 34.7321 | 51.0981 | 8.9207 | 10.4553 | 10.9107 | 9.9107 | 14.366 | 16.366 | 10.4553 | 20.366 | 34.7321 | 51.0981 | 0
5.5784 | 8.7892 | 7.5784 | 6.5784 | 9.3676 | 11.3676 | 8.7892 | 15.3676 | 24.7351 | 36.1027 | 5.5884 | 8.7892 | 7.5784 | 6.5784 | 9.3676 | 11.3676 | 8.7892 | 15.3676 | 24.7351 | 36.1027 | 0
6.5968 | 9.2984 | 8.5968 | 7.5968 | 10.8952 | 12.8952 | 9.2984 | 16.8952 | 27.7903 | 40.6855 | 6.6068 | 9.2984 | 8.5968 | 7.5968 | 10.8952 | 12.8952 | 9.2984 | 16.8952 | 27.7903 | 40.6855 | 0
9.5841 | 10.7921 | 11.5841 | 10.5841 | 15.3762 | 17.3762 | 10.7921 | 21.3762 | 36.7524 | 54.1286 | 9.5941 | 10.7921 | 11.5841 | 10.5841 | 15.3762 | 17.3762 | 10.7921 | 21.3762 | 36.7524 | 54.1286 | 0
7.1421 | 9.5711 | 9.1421 | 8.1421 | 11.7132 | 13.7132 | 9.5711 | 17.7132 | 29.4264 | 43.1397 | 7.1521 | 9.5711 | 9.1421 | 8.1421 | 11.7132 | 13.7132 | 9.5711 | 17.7132 | 29.4264 | 43.1397 | 0
6.9164 | 9.4582 | 8.9164 | 7.9164 | 11.3746 | 13.3746 | 9.4582 | 17.3746 | 28.7492 | 42.1238 | 6.9264 | 9.4582 | 8.9164 | 7.9164 | 11.3746 | 13.3746 | 9.4582 | 17.3746 | 28.7492 | 42.1238 | 0
8.2153 | 10.1076 | 10.2153 | 9.2153 | 13.3229 | 15.3229 | 10.1076 | 19.3229 | 32.6459 | 47.9688 | 8.2253 | 10.1076 | 10.2153 | 9.2153 | 13.3229 | 15.3229 | 10.1076 | 19.3229 | 32.6459 | 47.9688 | 0
5.5263 | 8.7631 | 7.5263 | 6.5263 | 9.2894 | 11.2894 | 8.7631 | 15.2894 | 24.5789 | 35.8683 | 5.5363 | 8.7631 | 7.5263 | 6.5263 | 9.2894 | 11.2894 | 8.7631 | 15.2894 | 24.5789 | 35.8683 | 0
11.0337 | 11.5168 | 13.0337 | 12.0337 | 17.5505 | 19.5505 | 11.5168 | 23.5505 | 41.101 | 60.6514 | 11.0437 | 11.5168 | 13.0337 | 12.0337 | 17.5505 | 19.5505 | 11.5168 | 23.5505 | 41.101 | 60.6514 | 0
6.0016 | 9.0008 | 8.0016 | 7.0016 | 10.0024 | 12.0024 | 9.0008 | 16.0024 | 26.0048 | 38.0072 | 6.0116 | 9.0008 | 8.0016 | 7.0016 | 10.0024 | 12.0024 | 9.0008 | 16.0024 | 26.0048 | 38.0072 | 0
10.3738 | 11.1869 | 12.3738 | 11.3738 | 16.5607 | 18.5607 | 11.1869 | 22.5607 | 39.1215 | 57.6822 | 10.3838 | 11.1869 | 12.3738 | 11.3738 | 16.5607 | 18.5607 | 11.1869 | 22.5607 | 39.1215 | 57.6822 | 0
6.4121 | 9.206 | 8.4121 | 7.4121 | 10.6181 | 12.6181 | 9.206 | 16.6181 | 27.2363 | 39.8544 | 6.4221 | 9.206 | 8.4121 | 7.4121 | 10.6181 | 12.6181 | 9.206 | 16.6181 | 27.2363 | 39.8544 | 0
9.217 | 10.6085 | 11.217 | 10.217 | 14.8254 | 16.8254 | 10.6085 | 20.8254 | 35.6509 | 52.4763 | 9.227 | 10.6085 | 11.217 | 10.217 | 14.8254 | 16.8254 | 10.6085 | 20.8254 | 35.6509 | 52.4763 | 0
9.7797 | 10.8898 | 11.7797 | 10.7797 | 15.6695 | 17.6695 | 10.8898 | 21.6695 | 37.3391 | 55.0086 | 9.7897 | 10.8898 | 11.7797 | 10.7797 | 15.6695 | 17.6695 | 10.8898 | 21.6695 | 37.3391 | 55.0086 | 0
5.0423 | 8.5211 | 7.0423 | 6.0423 | 8.5634 | 10.5634 | 8.5211 | 14.5634 | 23.1268 | 33.6903 | 5.0523 | 8.5211 | 7.0423 | 6.0423 | 8.5634 | 10.5634 | 8.5211 | 14.5634 | 23.1268 | 33.6903 | 0
4.3481 | 8.174 | 6.3481 | 5.3481 | 7.5221 | 9.5221 | 8.174 | 13.5221 | 21.0442 | 30.5663 | 4.3581 | 8.174 | 6.3481 | 5.3481 | 7.5221 | 9.5221 | 8.174 | 13.5221 | 21.0442 | 30.5663 | 0
7.1758 | 9.5879 | 9.1758 | 8.1758 | 11.7637 | 13.7637 | 9.5879 | 17.7637 | 29.5274 | 43.2911 | 7.1858 | 9.5879 | 9.1758 | 8.1758 | 11.7637 | 13.7637 | 9.5879 | 17.7637 | 29.5274 | 43.2911 | 0
4.6681 | 8.3341 | 6.6681 | 5.6681 | 8.0022 | 10.0022 | 8.3341 | 14.0022 | 22.0043 | 32.0065 | 4.6781 | 8.3341 | 6.6681 | 5.6681 | 8.0022 | 10.0022 | 8.3341 | 14.0022 | 22.0043 | 32.0065 | 0
1.8921 | 6.946 | 3.8921 | 2.8921 | 3.8381 | 5.8381 | 6.946 | 9.8381 | 13.6762 | 19.5143 | 1.9021 | 6.946 | 3.8921 | 2.8921 | 3.8381 | 5.8381 | 6.946 | 9.8381 | 13.6762 | 19.5143 | 0
5.0109 | 8.5055 | 7.0109 | 6.0109 | 8.5164 | 10.5164 | 8.5055 | 14.5164 | 23.0328 | 33.5492 | 5.0209 | 8.5055 | 7.0109 | 6.0109 | 8.5164 | 10.5164 | 8.5055 | 14.5164 | 23.0328 | 33.5492 | 0
3.8584 | 7.9292 | 5.8584 | 4.8584 | 6.7875 | 8.7875 | 7.9292 | 12.7875 | 19.5751 | 28.3626 | 3.8684 | 7.9292 | 5.8584 | 4.8584 | 6.7875 | 8.7875 | 7.9292 | 12.7875 | 19.5751 | 28.3626 | 0
6.4966 | 9.2483 | 8.4966 | 7.4966 | 10.7448 | 12.7448 | 9.2483 | 16.7448 | 27.4897 | 40.2345 | 6.5066 | 9.2483 | 8.4966 | 7.4966 | 10.7448 | 12.7448 | 9.2483 | 16.7448 | 27.4897 | 40.2345 | 0
7.0352 | 9.5176 | 9.0352 | 8.0352 | 11.5527 | 13.5527 | 9.5176 | 17.5527 | 29.1055 | 42.6582 | 7.0452 | 9.5176 | 9.0352 | 8.0352 | 11.5527 | 13.5527 | 9.5176 | 17.5527 | 29.1055 | 42.6582 | 0
6.1885 | 9.0943 | 8.1885 | 7.1885 | 10.2828 | 12.2828 | 9.0943 | 16.2828 | 26.5656 | 38.8484 | 6.1985 | 9.0943 | 8.1885 | 7.1885 | 10.2828 | 12.2828 | 9.0943 | 16.2828 | 26.5656 | 38.8484 | 0
5.8998 | 8.9499 | 7.8998 | 6.8998 | 9.8497 | 11.8497 | 8.9499 | 15.8497 | 25.6995 | 37.5492 | 5.9098 | 8.9499 | 7.8998 | 6.8998 | 9.8497 | 11.8497 | 8.9499 | 15.8497 | 25.6995 | 37.5492 | 0
3.7522 | 7.8761 | 5.7522 | 4.7522 | 6.6283 | 8.6283 | 7.8761 | 12.6283 | 19.2566 | 27.8849 | 3.7622 | 7.8761 | 5.7522 | 4.7522 | 6.6283 | 8.6283 | 7.8761 | 12.6283 | 19.2566 | 27.8849 | 0
6.776 | 9.388 | 8.776 | 7.776 | 11.164 | 13.164 | 9.388 | 17.164 | 28.328 | 41.492 | 6.786 | 9.388 | 8.776 | 7.776 | 11.164 | 13.164 | 9.388 | 17.164 | 28.328 | 41.492 | 0
5.7807 | 8.8903 | 7.7807 | 6.7807 | 9.671 | 11.671 | 8.8903 | 15.671 | 25.3421 | 37.0131 | 5.7907 | 8.8903 | 7.7807 | 6.7807 | 9.671 | 11.671 | 8.8903 | 15.671 | 25.3421 | 37.0131 | 0
3.3449 | 7.6725 | 5.3449 | 4.3449 | 6.0174 | 8.0174 | 7.6725 | 12.0174 | 18.0348 | 26.0522 | 3.3549 | 7.6725 | 5.3449 | 4.3449 | 6.0174 | 8.0174 | 7.6725 | 12.0174 | 18.0348 | 26.0522 | 0
3.0968 | 7.5484 | 5.0968 | 4.0968 | 5.6452 | 7.6452 | 7.5484 | 11.6452 | 17.2904 | 24.9355 | 3.1068 | 7.5484 | 5.0968 | 4.0968 | 5.6452 | 7.6452 | 7.5484 | 11.6452 | 17.2904 | 24.9355 | 0
7.9137 | 9.9569 | 9.9137 | 8.9137 | 12.8706 | 14.8706 | 9.9569 | 18.8706 | 31.7412 | 46.6118 | 7.9237 | 9.9569 | 9.9137 | 8.9137 | 12.8706 | 14.8706 | 9.9569 | 18.8706 | 31.7412 | 46.6118 | 0
8.1265 | 10.0633 | 10.1265 | 9.1265 | 13.1898 | 15.1898 | 10.0633 | 19.1898 | 32.3795 | 47.5693 | 8.1365 | 10.0633 | 10.1265 | 9.1265 | 13.1898 | 15.1898 | 10.0633 | 19.1898 | 32.3795 | 47.5693 | 0
4.2244 | 8.1122 | 6.2244 | 5.2244 | 7.3366 | 9.3366 | 8.1122 | 13.3366 | 20.6732 | 30.0098 | 4.2344 | 8.1122 | 6.2244 | 5.2244 | 7.3366 | 9.3366 | 8.1122 | 13.3366 | 20.6732 | 30.0098 | 0
6.3537 | 9.1768 | 8.3537 | 7.3537 | 10.5305 | 12.5305 | 9.1768 | 16.5305 | 27.061 | 39.5914 | 6.3637 | 9.1768 | 8.3537 | 7.3537 | 10.5305 | 12.5305 | 9.1768 | 16.5305 | 27.061 | 39.5914 | 0
11.168 | 11.584 | 13.168 | 12.168 | 17.7521 | 19.7521 | 11.584 | 23.7521 | 41.5041 | 61.2562 | 11.178 | 11.584 | 13.168 | 12.168 | 17.7521 | 19.7521 | 11.584 | 23.7521 | 41.5041 | 61.2562 | 0
5.4518 | 8.7259 | 7.4518 | 6.4518 | 9.1778 | 11.1778 | 8.7259 | 15.1778 | 24.3555 | 35.5333 | 5.4618 | 8.7259 | 7.4518 | 6.4518 | 9.1778 | 11.1778 | 8.7259 | 15.1778 | 24.3555 | 35.5333 | 0
6.0492 | 9.0246 | 8.0492 | 7.0492 | 10.0738 | 12.0738 | 9.0246 | 16.0738 | 26.1476 | 38.2214 | 6.0592 | 9.0246 | 8.0492 | 7.0492 | 10.0738 | 12.0738 | 9.0246 | 16.0738 | 26.1476 | 38.2214 | 0
7.4105 | 9.7052 | 9.4105 | 8.4105 | 12.1157 | 14.1157 | 9.7052 | 18.1157 | 30.2314 | 44.3471 | 7.4205 | 9.7052 | 9.4105 | 8.4105 | 12.1157 | 14.1157 | 9.7052 | 18.1157 | 30.2314 | 44.3471 | 0
3.5875 | 7.7938 | 5.5875 | 4.5875 | 6.3813 | 8.3813 | 7.7938 | 12.3813 | 18.7626 | 27.1439 | 3.5975 | 7.7938 | 5.5875 | 4.5875 | 6.3813 | 8.3813 | 7.7938 | 12.3813 | 18.7626 | 27.1439 | 0
5.9969 | 8.9984 | 7.9969 | 6.9969 | 9.9953 | 11.9953 | 8.9984 | 15.9953 | 25.9906 | 37.9859 | 6.0069 | 8.9984 | 7.9969 | 6.9969 | 9.9953 | 11.9953 | 8.9984 | 15.9953 | 25.9906 | 37.9859 | 0
4.4596 | 8.2298 | 6.4596 | 5.4596 | 7.6894 | 9.6894 | 8.2298 | 13.6894 | 21.3787 | 31.0681 | 4.4696 | 8.2298 | 6.4596 | 5.4596 | 7.6894 | 9.6894 | 8.2298 | 13.6894 | 21.3787 | 31.0681 | 0
4.6953 | 8.3477 | 6.6953 | 5.6953 | 8.043 | 10.043 | 8.3477 | 14.043 | 22.0859 | 32.1289 | 4.7053 | 8.3477 | 6.6953 | 5.6953 | 8.043 | 10.043 | 8.3477 | 14.043 | 22.0859 | 32.1289 | 0
6.2341 | 9.117 | 8.2341 | 7.2341 | 10.3511 | 12.3511 | 9.117 | 16.3511 | 26.7023 | 39.0534 | 6.2441 | 9.117 | 8.2341 | 7.2341 | 10.3511 | 12.3511 | 9.117 | 16.3511 | 26.7023 | 39.0534 | 0
10.223 | 11.1115 | 12.223 | 11.223 | 16.3345 | 18.3345 | 11.1115 | 22.3345 | 38.669 | 57.0034 | 10.233 | 11.1115 | 12.223 | 11.223 | 16.3345 | 18.3345 | 11.1115 | 22.3345 | 38.669 | 57.0034 | 0
7.3917 | 9.6958 | 9.3917 | 8.3917 | 12.0875 | 14.0875 | 9.6958 | 18.0875 | 30.1751 | 44.2626 | 7.4017 | 9.6958 | 9.3917 | 8.3917 | 12.0875 | 14.0875 | 9.6958 | 18.0875 | 30.1751 | 44.2626 | 0
7.055 | 9.5275 | 9.055 | 8.055 | 11.5825 | 13.5825 | 9.5275 | 17.5825 | 29.1649 | 42.7474 | 7.065 | 9.5275 | 9.055 | 8.055 | 11.5825 | 13.5825 | 9.5275 | 17.5825 | 29.1649 | 42.7474 | 0
2.1916 | 7.0958 | 4.1916 | 3.1916 | 4.2875 | 6.2875 | 7.0958 | 10.2875 | 14.5749 | 20.8624 | 2.2016 | 7.0958 | 4.1916 | 3.1916 | 4.2875 | 6.2875 | 7.0958 | 10.2875 | 14.5749 | 20.8624 | 0
4.1961 | 8.098 | 6.1961 | 5.1961 | 7.2941 | 9.2941 | 8.098 | 13.2941 | 20.5882 | 29.8823 | 4.2061 | 8.098 | 6.1961 | 5.1961 | 7.2941 | 9.2941 | 8.098 | 13.2941 | 20.5882 | 29.8823 | 0
9.3012 | 10.6506 | 11.3012 | 10.3012 | 14.9518 | 16.9518 | 10.6506 | 20.9518 | 35.9036 | 52.8554 | 9.3112 | 10.6506 | 11.3012 | 10.3012 | 14.9518 | 16.9518 | 10.6506 | 20.9518 | 35.9036 | 52.8554 | 0
6.1032 | 9.0516 | 8.1032 | 7.1032 | 10.1549 | 12.1549 | 9.0516 | 16.1549 | 26.3097 | 38.4646 | 6.1132 | 9.0516 | 8.1032 | 7.1032 | 10.1549 | 12.1549 | 9.0516 | 16.1549 | 26.3097 | 38.4646 | 0
10.9776 | 11.4888 | 12.9776 | 11.9776 | 17.4663 | 19.4663 | 11.4888 | 23.4663 | 40.9327 | 60.399 | 10.9876 | 11.4888 | 12.9776 | 11.9776 | 17.4663 | 19.4663 | 11.4888 | 23.4663 | 40.9327 | 60.399 | 0
3.8066 | 7.9033 | 5.8066 | 4.8066 | 6.7099 | 8.7099 | 7.9033 | 12.7099 | 19.4198 | 28.1297 | 3.8166 | 7.9033 | 5.8066 | 4.8066 | 6.7099 | 8.7099 | 7.9033 | 12.7099 | 19.4198 | 28.1297 | 0
4.2458 | 8.1229 | 6.2458 | 5.2458 | 7.3688 | 9.3688 | 8.1229 | 13.3688 | 20.7375 | 30.1063 | 4.2558 | 8.1229 | 6.2458 | 5.2458 | 7.3688 | 9.3688 | 8.1229 | 13.3688 | 20.7375 | 30.1063 | 0
6.4005 | 9.2003 | 8.4005 | 7.4005 | 10.6008 | 12.6008 | 9.2003 | 16.6008 | 27.2016 | 39.8024 | 6.4105 | 9.2003 | 8.4005 | 7.4005 | 10.6008 | 12.6008 | 9.2003 | 16.6008 | 27.2016 | 39.8024 | 0
4.7583 | 8.3791 | 6.7583 | 5.7583 | 8.1374 | 10.1374 | 8.3791 | 14.1374 | 22.2748 | 32.4122 | 4.7683 | 8.3791 | 6.7583 | 5.7583 | 8.1374 | 10.1374 | 8.3791 | 14.1374 | 22.2748 | 32.4122 | 0
6.5861 | 9.293 | 8.5861 | 7.5861 | 10.8791 | 12.8791 | 9.293 | 16.8791 | 27.7582 | 40.6373 | 6.5961 | 9.293 | 8.5861 | 7.5861 | 10.8791 | 12.8791 | 9.293 | 16.8791 | 27.7582 | 40.6373 | 0
8.5851 | 10.2925 | 10.5851 | 9.5851 | 13.8776 | 15.8776 | 10.2925 | 19.8776 | 33.7552 | 49.6328 | 8.5951 | 10.2925 | 10.5851 | 9.5851 | 13.8776 | 15.8776 | 10.2925 | 19.8776 | 33.7552 | 49.6328 | 0
8.0992 | 10.0496 | 10.0992 | 9.0992 | 13.1489 | 15.1489 | 10.0496 | 19.1489 | 32.2977 | 47.4466 | 8.1092 | 10.0496 | 10.0992 | 9.0992 | 13.1489 | 15.1489 | 10.0496 | 19.1489 | 32.2977 | 47.4466 | 0
6.8226 | 9.4113 | 8.8226 | 7.8226 | 11.2338 | 13.2338 | 9.4113 | 17.2338 | 28.4677 | 41.7015 | 6.8326 | 9.4113 | 8.8226 | 7.8226 | 11.2338 | 13.2338 | 9.4113 | 17.2338 | 28.4677 | 41.7015 | 0
5.9018 | 8.9509 | 7.9018 | 6.9018 | 9.8527 | 11.8527 | 8.9509 | 15.8527 | 25.7054 | 37.5582 | 5.9118 | 8.9509 | 7.9018 | 6.9018 | 9.8527 | 11.8527 | 8.9509 | 15.8527 | 25.7054 | 37.5582 | 0
3.8038 | 7.9019 | 5.8038 | 4.8038 | 6.7057 | 8.7057 | 7.9019 | 12.7057 | 19.4114 | 28.1172 | 3.8138 | 7.9019 | 5.8038 | 4.8038 | 6.7057 | 8.7057 | 7.9019 | 12.7057 | 19.4114 | 28.1172 | 0
7.6562 | 9.8281 | 9.6562 | 8.6562 | 12.4843 | 14.4843 | 9.8281 | 18.4843 | 30.9687 | 45.453 | 7.6662 | 9.8281 | 9.6562 | 8.6562 | 12.4843 | 14.4843 | 9.8281 | 18.4843 | 30.9687 | 45.453 | 0
5.9438 | 8.9719 | 7.9438 | 6.9438 | 9.9156 | 11.9156 | 8.9719 | 15.9156 | 25.8313 | 37.7469 | 5.9538 | 8.9719 | 7.9438 | 6.9438 | 9.9156 | 11.9156 | 8.9719 | 15.9156 | 25.8313 | 37.7469 | 0
4.5206 | 8.2603 | 6.5206 | 5.5206 | 7.7809 | 9.7809 | 8.2603 | 13.7809 | 21.5618 | 31.3428 | 4.5306 | 8.2603 | 6.5206 | 5.5206 | 7.7809 | 9.7809 | 8.2603 | 13.7809 | 21.5618 | 31.3428 | 0
6.1925 | 9.0963 | 8.1925 | 7.1925 | 10.2888 | 12.2888 | 9.0963 | 16.2888 | 26.5776 | 38.8664 | 6.2025 | 9.0963 | 8.1925 | 7.1925 | 10.2888 | 12.2888 | 9.0963 | 16.2888 | 26.5776 | 38.8664 | 0
6.2748 | 9.1374 | 8.2748 | 7.2748 | 10.4122 | 12.4122 | 9.1374 | 16.4122 | 26.8244 | 39.2366 | 6.2848 | 9.1374 | 8.2748 | 7.2748 | 10.4122 | 12.4122 | 9.1374 | 16.4122 | 26.8244 | 39.2366 | 0
6.3519 | 9.176 | 8.3519 | 7.3519 | 10.5279 | 12.5279 | 9.176 | 16.5279 | 27.0558 | 39.5837 | 6.3619 | 9.176 | 8.3519 | 7.3519 | 10.5279 | 12.5279 | 9.176 | 16.5279 | 27.0558 | 39.5837 | 0
4.0229 | 8.0115 | 6.0229 | 5.0229 | 7.0344 | 9.0344 | 8.0115 | 13.0344 | 20.0687 | 29.1031 | 4.0329 | 8.0115 | 6.0229 | 5.0229 | 7.0344 | 9.0344 | 8.0115 | 13.0344 | 20.0687 | 29.1031 | 0
5.9303 | 8.9651 | 7.9303 | 6.9303 | 9.8954 | 11.8954 | 8.9651 | 15.8954 | 25.7909 | 37.6863 | 5.9403 | 8.9651 | 7.9303 | 6.9303 | 9.8954 | 11.8954 | 8.9651 | 15.8954 | 25.7909 | 37.6863 | 0
6.936 | 9.468 | 8.936 | 7.936 | 11.404 | 13.404 | 9.468 | 17.404 | 28.808 | 42.2119 | 6.946 | 9.468 | 8.936 | 7.936 | 11.404 | 13.404 | 9.468 | 17.404 | 28.808 | 42.2119 | 0
7.0226 | 9.5113 | 9.0226 | 8.0226 | 11.5339 | 13.5339 | 9.5113 | 17.5339 | 29.0677 | 42.6016 | 7.0326 | 9.5113 | 9.0226 | 8.0226 | 11.5339 | 13.5339 | 9.5113 | 17.5339 | 29.0677 | 42.6016 | 0
2.7903 | 7.3951 | 4.7903 | 3.7903 | 5.1854 | 7.1854 | 7.3951 | 11.1854 | 16.3708 | 23.5562 | 2.8003 | 7.3951 | 4.7903 | 3.7903 | 5.1854 | 7.1854 | 7.3951 | 11.1854 | 16.3708 | 23.5562 | 0
6.8957 | 9.4479 | 8.8957 | 7.8957 | 11.3436 | 13.3436 | 9.4479 | 17.3436 | 28.6871 | 42.0307 | 6.9057 | 9.4479 | 8.8957 | 7.8957 | 11.3436 | 13.3436 | 9.4479 | 17.3436 | 28.6871 | 42.0307 | 0
6.0138 | 9.0069 | 8.0138 | 7.0138 | 10.0208 | 12.0208 | 9.0069 | 16.0208 | 26.0415 | 38.0623 | 6.0238 | 9.0069 | 8.0138 | 7.0138 | 10.0208 | 12.0208 | 9.0069 | 16.0208 | 26.0415 | 38.0623 | 0
3.8657 | 7.9328 | 5.8657 | 4.8657 | 6.7985 | 8.7985 | 7.9328 | 12.7985 | 19.597 | 28.3955 | 3.8757 | 7.9328 | 5.8657 | 4.8657 | 6.7985 | 8.7985 | 7.9328 | 12.7985 | 19.597 | 28.3955 | 0
7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 7.4989 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 0
8.8202 | 10.4101 | 10.8202 | 9.8202 | 14.2303 | 16.2303 | 10.4101 | 20.2303 | 34.4605 | 50.6908 | 8.8302 | 10.4101 | 10.8202 | 9.8202 | 14.2303 | 16.2303 | 10.4101 | 20.2303 | 34.4605 | 50.6908 | 0
7.8196 | 9.9098 | 9.8196 | 8.8196 | 12.7294 | 14.7294 | 9.9098 | 18.7294 | 31.4588 | 46.1882 | 7.8296 | 9.9098 | 9.8196 | 8.8196 | 12.7294 | 14.7294 | 9.9098 | 18.7294 | 31.4588 | 46.1882 | 0
4.576 | 8.288 | 6.576 | 5.576 | 7.864 | 9.864 | 8.288 | 13.864 | 21.7279 | 31.5919 | 4.586 | 8.288 | 6.576 | 5.576 | 7.864 | 9.864 | 8.288 | 13.864 | 21.7279 | 31.5919 | 0
7.0266 | 9.5133 | 9.0266 | 8.0266 | 11.5399 | 13.5399 | 9.5133 | 17.5399 | 29.0798 | 42.6196 | 7.0366 | 9.5133 | 9.0266 | 8.0266 | 11.5399 | 13.5399 | 9.5133 | 17.5399 | 29.0798 | 42.6196 | 0
6.0145 | 9.0072 | 8.0145 | 7.0145 | 10.0217 | 12.0217 | 9.0072 | 16.0217 | 26.0434 | 38.0651 | 6.0245 | 9.0072 | 8.0145 | 7.0145 | 10.0217 | 12.0217 | 9.0072 | 16.0217 | 26.0434 | 38.0651 | 0
2.6438 | 7.3219 | 4.6438 | 3.6438 | 4.9657 | 6.9657 | 7.3219 | 10.9657 | 15.9313 | 22.897 | 2.6538 | 7.3219 | 4.6438 | 3.6438 | 4.9657 | 6.9657 | 7.3219 | 10.9657 | 15.9313 | 22.897 | 0
6.0348 | 9.0174 | 8.0348 | 7.0348 | 10.0522 | 12.0522 | 9.0174 | 16.0522 | 26.1044 | 38.1566 | 6.0448 | 9.0174 | 8.0348 | 7.0348 | 10.0522 | 12.0522 | 9.0174 | 16.0522 | 26.1044 | 38.1566 | 0
5.4907 | 8.7453 | 7.4907 | 6.4907 | 9.236 | 11.236 | 8.7453 | 15.236 | 24.472 | 35.7079 | 5.5007 | 8.7453 | 7.4907 | 6.4907 | 9.236 | 11.236 | 8.7453 | 15.236 | 24.472 | 35.7079 | 0
7.3925 | 9.6962 | 9.3925 | 8.3925 | 12.0887 | 14.0887 | 9.6962 | 18.0887 | 30.1774 | 44.2661 | 7.4025 | 9.6962 | 9.3925 | 8.3925 | 12.0887 | 14.0887 | 9.6962 | 18.0887 | 30.1774 | 44.2661 | 0
6.0746 | 9.0373 | 8.0746 | 7.0746 | 10.1119 | 12.1119 | 9.0373 | 16.1119 | 26.2238 | 38.3357 | 6.0846 | 9.0373 | 8.0746 | 7.0746 | 10.1119 | 12.1119 | 9.0373 | 16.1119 | 26.2238 | 38.3357 | 0
5.7247 | 8.8624 | 7.7247 | 6.7247 | 9.5871 | 11.5871 | 8.8624 | 15.5871 | 25.1742 | 36.7613 | 5.7347 | 8.8624 | 7.7247 | 6.7247 | 9.5871 | 11.5871 | 8.8624 | 15.5871 | 25.1742 | 36.7613 | 0
5.7801 | 8.89 | 7.7801 | 6.7801 | 9.6701 | 11.6701 | 8.89 | 15.6701 | 25.3403 | 37.0104 | 5.7901 | 8.89 | 7.7801 | 6.7801 | 9.6701 | 11.6701 | 8.89 | 15.6701 | 25.3403 | 37.0104 | 0
4.7764 | 8.3882 | 6.7764 | 5.7764 | 8.1646 | 10.1646 | 8.3882 | 14.1646 | 22.3292 | 32.4937 | 4.7864 | 8.3882 | 6.7764 | 5.7764 | 8.1646 | 10.1646 | 8.3882 | 14.1646 | 22.3292 | 32.4937 | 0
2.1447 | 7.0723 | 4.1447 | 3.1447 | 4.217 | 6.217 | 7.0723 | 10.217 | 14.434 | 20.6509 | 2.1547 | 7.0723 | 4.1447 | 3.1447 | 4.217 | 6.217 | 7.0723 | 10.217 | 14.434 | 20.6509 | 0
5.7028 | 8.8514 | 7.7028 | 6.7028 | 9.5542 | 11.5542 | 8.8514 | 15.5542 | 25.1084 | 36.6625 | 5.7128 | 8.8514 | 7.7028 | 6.7028 | 9.5542 | 11.5542 | 8.8514 | 15.5542 | 25.1084 | 36.6625 | 0
7.7214 | 9.8607 | 9.7214 | 8.7214 | 12.582 | 14.582 | 9.8607 | 18.582 | 31.1641 | 45.7461 | 7.7314 | 9.8607 | 9.7214 | 8.7214 | 12.582 | 14.582 | 9.8607 | 18.582 | 31.1641 | 45.7461 | 0
5.5976 | 8.7988 | 7.5976 | 6.5976 | 9.3964 | 11.3964 | 8.7988 | 15.3964 | 24.7928 | 36.1892 | 5.6076 | 8.7988 | 7.5976 | 6.5976 | 9.3964 | 11.3964 | 8.7988 | 15.3964 | 24.7928 | 36.1892 | 0
5.3389 | 8.6695 | 7.3389 | 6.3389 | 9.0084 | 11.0084 | 8.6695 | 15.0084 | 24.0167 | 35.0251 | 5.3489 | 8.6695 | 7.3389 | 6.3389 | 9.0084 | 11.0084 | 8.6695 | 15.0084 | 24.0167 | 35.0251 | 0
8.3081 | 10.154 | 10.3081 | 9.3081 | 13.4621 | 15.4621 | 10.154 | 19.4621 | 32.9243 | 48.3864 | 8.3181 | 10.154 | 10.3081 | 9.3081 | 13.4621 | 15.4621 | 10.154 | 19.4621 | 32.9243 | 48.3864 | 0
6.3383 | 9.1691 | 8.3383 | 7.3383 | 10.5074 | 12.5074 | 9.1691 | 16.5074 | 27.0148 | 39.5222 | 6.3483 | 9.1691 | 8.3383 | 7.3383 | 10.5074 | 12.5074 | 9.1691 | 16.5074 | 27.0148 | 39.5222 | 0
6.2356 | 9.1178 | 8.2356 | 7.2356 | 10.3534 | 12.3534 | 9.1178 | 16.3534 | 26.7069 | 39.0603 | 6.2456 | 9.1178 | 8.2356 | 7.2356 | 10.3534 | 12.3534 | 9.1178 | 16.3534 | 26.7069 | 39.0603 | 0
8.8103 | 10.4051 | 10.8103 | 9.8103 | 14.2154 | 16.2154 | 10.4051 | 20.2154 | 34.4309 | 50.6463 | 8.8203 | 10.4051 | 10.8103 | 9.8103 | 14.2154 | 16.2154 | 10.4051 | 20.2154 | 34.4309 | 50.6463 | 0
9.1328 | 10.5664 | 11.1328 | 10.1328 | 14.6992 | 16.6992 | 10.5664 | 20.6992 | 35.3985 | 52.0977 | 9.1428 | 10.5664 | 11.1328 | 10.1328 | 14.6992 | 16.6992 | 10.5664 | 20.6992 | 35.3985 | 52.0977 | 0
7.1789 | 9.5895 | 9.1789 | 8.1789 | 11.7684 | 13.7684 | 9.5895 | 17.7684 | 29.5367 | 43.3051 | 7.1889 | 9.5895 | 9.1789 | 8.1789 | 11.7684 | 13.7684 | 9.5895 | 17.7684 | 29.5367 | 43.3051 | 0
6.2187 | 9.1093 | 8.2187 | 7.2187 | 10.328 | 12.328 | 9.1093 | 16.328 | 26.6561 | 38.9841 | 6.2287 | 9.1093 | 8.2187 | 7.2187 | 10.328 | 12.328 | 9.1093 | 16.328 | 26.6561 | 38.9841 | 0
10.8017 | 11.4008 | 12.8017 | 11.8017 | 17.2025 | 19.2025 | 11.4008 | 23.2025 | 40.405 | 59.6075 | 10.8117 | 11.4008 | 12.8017 | 11.8017 | 17.2025 | 19.2025 | 11.4008 | 23.2025 | 40.405 | 59.6075 | 0
4.3082 | 8.1541 | 6.3082 | 5.3082 | 7.4622 | 9.4622 | 8.1541 | 13.4622 | 20.9245 | 30.3867 | 4.3182 | 8.1541 | 6.3082 | 5.3082 | 7.4622 | 9.4622 | 8.1541 | 13.4622 | 20.9245 | 30.3867 | 0
6.2847 | 9.1423 | 8.2847 | 7.2847 | 10.427 | 12.427 | 9.1423 | 16.427 | 26.8541 | 39.2811 | 6.2947 | 9.1423 | 8.2847 | 7.2847 | 10.427 | 12.427 | 9.1423 | 16.427 | 26.8541 | 39.2811 | 0
3.8754 | 7.9377 | 5.8754 | 4.8754 | 6.8131 | 8.8131 | 7.9377 | 12.8131 | 19.6261 | 28.4392 | 3.8854 | 7.9377 | 5.8754 | 4.8754 | 6.8131 | 8.8131 | 7.9377 | 12.8131 | 19.6261 | 28.4392 | 0
3.5216 | 7.7608 | 5.5216 | 4.5216 | 6.2824 | 8.2824 | 7.7608 | 12.2824 | 18.5649 | 26.8473 | 3.5316 | 7.7608 | 5.5216 | 4.5216 | 6.2824 | 8.2824 | 7.7608 | 12.2824 | 18.5649 | 26.8473 | 0
5.5633 | 8.7817 | 7.5633 | 6.5633 | 9.345 | 11.345 | 8.7817 | 15.345 | 24.69 | 36.0351 | 5.5733 | 8.7817 | 7.5633 | 6.5633 | 9.345 | 11.345 | 8.7817 | 15.345 | 24.69 | 36.0351 | 0
4.8463 | 8.4232 | 6.8463 | 5.8463 | 8.2695 | 10.2695 | 8.4232 | 14.2695 | 22.5389 | 32.8084 | 4.8563 | 8.4232 | 6.8463 | 5.8463 | 8.2695 | 10.2695 | 8.4232 | 14.2695 | 22.5389 | 32.8084 | 0
6.9828 | 9.4914 | 8.9828 | 7.9828 | 11.4743 | 13.4743 | 9.4914 | 17.4743 | 28.9485 | 42.4228 | 6.9928 | 9.4914 | 8.9828 | 7.9828 | 11.4743 | 13.4743 | 9.4914 | 17.4743 | 28.9485 | 42.4228 | 0
7.8476 | 9.9238 | 9.8476 | 8.8476 | 12.7713 | 14.7713 | 9.9238 | 18.7713 | 31.5427 | 46.314 | 7.8576 | 9.9238 | 9.8476 | 8.8476 | 12.7713 | 14.7713 | 9.9238 | 18.7713 | 31.5427 | 46.314 | 0
7.0345 | 9.5172 | 9.0345 | 8.0345 | 11.5517 | 13.5517 | 9.5172 | 17.5517 | 29.1034 | 42.655 | 7.0445 | 9.5172 | 9.0345 | 8.0345 | 11.5517 | 13.5517 | 9.5172 | 17.5517 | 29.1034 | 42.655 | 0
7.2596 | 9.6298 | 9.2596 | 8.2596 | 11.8894 | 13.8894 | 9.6298 | 17.8894 | 29.7788 | 43.6682 | 7.2696 | 9.6298 | 9.2596 | 8.2596 | 11.8894 | 13.8894 | 9.6298 | 17.8894 | 29.7788 | 43.6682 | 0
6.762 | 9.381 | 8.762 | 7.762 | 11.143 | 13.143 | 9.381 | 17.143 | 28.286 | 41.4289 | 6.772 | 9.381 | 8.762 | 7.762 | 11.143 | 13.143 | 9.381 | 17.143 | 28.286 | 41.4289 | 0
4.7843 | 8.3922 | 6.7843 | 5.7843 | 8.1765 | 10.1765 | 8.3922 | 14.1765 | 22.3529 | 32.5294 | 4.7943 | 8.3922 | 6.7843 | 5.7843 | 8.1765 | 10.1765 | 8.3922 | 14.1765 | 22.3529 | 32.5294 | 0
5.9404 | 8.9702 | 7.9404 | 6.9404 | 9.9106 | 11.9106 | 8.9702 | 15.9106 | 25.8212 | 37.7318 | 5.9504 | 8.9702 | 7.9404 | 6.9404 | 9.9106 | 11.9106 | 8.9702 | 15.9106 | 25.8212 | 37.7318 | 0
6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 6.3414 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 0
7.0135 | 9.5068 | 9.0135 | 8.0135 | 11.5203 | 13.5203 | 9.5068 | 17.5203 | 29.0406 | 42.5608 | 7.0235 | 9.5068 | 9.0135 | 8.0135 | 11.5203 | 13.5203 | 9.5068 | 17.5203 | 29.0406 | 42.5608 | 0
3.4265 | 7.7133 | 5.4265 | 4.4265 | 6.1398 | 8.1398 | 7.7133 | 12.1398 | 18.2796 | 26.4194 | 3.4365 | 7.7133 | 5.4265 | 4.4265 | 6.1398 | 8.1398 | 7.7133 | 12.1398 | 18.2796 | 26.4194 | 0
5.4813 | 8.7407 | 7.4813 | 6.4813 | 9.222 | 11.222 | 8.7407 | 15.222 | 24.444 | 35.6659 | 5.4913 | 8.7407 | 7.4813 | 6.4813 | 9.222 | 11.222 | 8.7407 | 15.222 | 24.444 | 35.6659 | 0
7.7681 | 9.8841 | 9.7681 | 8.7681 | 12.6522 | 14.6522 | 9.8841 | 18.6522 | 31.3044 | 45.9566 | 7.7781 | 9.8841 | 9.7681 | 8.7681 | 12.6522 | 14.6522 | 9.8841 | 18.6522 | 31.3044 | 45.9566 | 0
6.4122 | 9.2061 | 8.4122 | 7.4122 | 10.6184 | 12.6184 | 9.2061 | 16.6184 | 27.2367 | 39.8551 | 6.4222 | 9.2061 | 8.4122 | 7.4122 | 10.6184 | 12.6184 | 9.2061 | 16.6184 | 27.2367 | 39.8551 | 0
8.7219 | 10.361 | 10.7219 | 9.7219 | 14.0829 | 16.0829 | 10.361 | 20.0829 | 34.1657 | 50.2486 | 8.7319 | 10.361 | 10.7219 | 9.7219 | 14.0829 | 16.0829 | 10.361 | 20.0829 | 34.1657 | 50.2486 | 0
5.8098 | 8.9049 | 7.8098 | 6.8098 | 9.7147 | 11.7147 | 8.9049 | 15.7147 | 25.4293 | 37.144 | 5.8198 | 8.9049 | 7.8098 | 6.8098 | 9.7147 | 11.7147 | 8.9049 | 15.7147 | 25.4293 | 37.144 | 0
4.8329 | 8.4165 | 6.8329 | 5.8329 | 8.2494 | 10.2494 | 8.4165 | 14.2494 | 22.4987 | 32.7481 | 4.8429 | 8.4165 | 6.8329 | 5.8329 | 8.2494 | 10.2494 | 8.4165 | 14.2494 | 22.4987 | 32.7481 | 0
6.7605 | 9.3803 | 8.7605 | 7.7605 | 11.1408 | 13.1408 | 9.3803 | 17.1408 | 28.2815 | 41.4223 | 6.7705 | 9.3803 | 8.7605 | 7.7605 | 11.1408 | 13.1408 | 9.3803 | 17.1408 | 28.2815 | 41.4223 | 0
9.047 | 10.5235 | 11.047 | 10.047 | 14.5706 | 16.5706 | 10.5235 | 20.5706 | 35.1411 | 51.7117 | 9.057 | 10.5235 | 11.047 | 10.047 | 14.5706 | 16.5706 | 10.5235 | 20.5706 | 35.1411 | 51.7117 | 0
7.8454 | 9.9227 | 9.8454 | 8.8454 | 12.7682 | 14.7682 | 9.9227 | 18.7682 | 31.5363 | 46.3045 | 7.8554 | 9.9227 | 9.8454 | 8.8454 | 12.7682 | 14.7682 | 9.9227 | 18.7682 | 31.5363 | 46.3045 | 0
6.6496 | 9.3248 | 8.6496 | 7.6496 | 10.9744 | 12.9744 | 9.3248 | 16.9744 | 27.9489 | 40.9233 | 6.6596 | 9.3248 | 8.6496 | 7.6496 | 10.9744 | 12.9744 | 9.3248 | 16.9744 | 27.9489 | 40.9233 | 0
4.2135 | 8.1067 | 6.2135 | 5.2135 | 7.3202 | 9.3202 | 8.1067 | 13.3202 | 20.6404 | 29.9606 | 4.2235 | 8.1067 | 6.2135 | 5.2135 | 7.3202 | 9.3202 | 8.1067 | 13.3202 | 20.6404 | 29.9606 | 0
11.6293 | 11.8146 | 13.6293 | 12.6293 | 18.4439 | 20.4439 | 11.8146 | 24.4439 | 42.8878 | 63.3317 | 11.6393 | 11.8146 | 13.6293 | 12.6293 | 18.4439 | 20.4439 | 11.8146 | 24.4439 | 42.8878 | 63.3317 | 0
5.3138 | 8.6569 | 7.3138 | 6.3138 | 8.9707 | 10.9707 | 8.6569 | 14.9707 | 23.9414 | 34.9122 | 5.3238 | 8.6569 | 7.3138 | 6.3138 | 8.9707 | 10.9707 | 8.6569 | 14.9707 | 23.9414 | 34.9122 | 0
6.2814 | 9.1407 | 8.2814 | 7.2814 | 10.4222 | 12.4222 | 9.1407 | 16.4222 | 26.8443 | 39.2665 | 6.2914 | 9.1407 | 8.2814 | 7.2814 | 10.4222 | 12.4222 | 9.1407 | 16.4222 | 26.8443 | 39.2665 | 0
5.935 | 8.9675 | 7.935 | 6.935 | 9.9026 | 11.9026 | 8.9675 | 15.9026 | 25.8051 | 37.7077 | 5.945 | 8.9675 | 7.935 | 6.935 | 9.9026 | 11.9026 | 8.9675 | 15.9026 | 25.8051 | 37.7077 | 0
6.1508 | 9.0754 | 8.1508 | 7.1508 | 10.2262 | 12.2262 | 9.0754 | 16.2262 | 26.4523 | 38.6785 | 6.1608 | 9.0754 | 8.1508 | 7.1508 | 10.2262 | 12.2262 | 9.0754 | 16.2262 | 26.4523 | 38.6785 | 0
5.3276 | 8.6638 | 7.3276 | 6.3276 | 8.9914 | 10.9914 | 8.6638 | 14.9914 | 23.9828 | 34.9742 | 5.3376 | 8.6638 | 7.3276 | 6.3276 | 8.9914 | 10.9914 | 8.6638 | 14.9914 | 23.9828 | 34.9742 | 0
2.0185 | 7.0093 | 4.0185 | 3.0185 | 4.0278 | 6.0278 | 7.0093 | 10.0278 | 14.0556 | 20.0834 | 2.0285 | 7.0093 | 4.0185 | 3.0185 | 4.0278 | 6.0278 | 7.0093 | 10.0278 | 14.0556 | 20.0834 | 0
7.9373 | 9.9687 | 9.9373 | 8.9373 | 12.906 | 14.906 | 9.9687 | 18.906 | 31.812 | 46.718 | 7.9473 | 9.9687 | 9.9373 | 8.9373 | 12.906 | 14.906 | 9.9687 | 18.906 | 31.812 | 46.718 | 0
7.1858 | 9.5929 | 9.1858 | 8.1858 | 11.7787 | 13.7787 | 9.5929 | 17.7787 | 29.5575 | 43.3362 | 7.1958 | 9.5929 | 9.1858 | 8.1858 | 11.7787 | 13.7787 | 9.5929 | 17.7787 | 29.5575 | 43.3362 | 0
6.7905 | 9.3953 | 8.7905 | 7.7905 | 11.1858 | 13.1858 | 9.3953 | 17.1858 | 28.3716 | 41.5574 | 6.8005 | 9.3953 | 8.7905 | 7.7905 | 11.1858 | 13.1858 | 9.3953 | 17.1858 | 28.3716 | 41.5574 | 0
8.3321 | 10.166 | 10.3321 | 9.3321 | 13.4981 | 15.4981 | 10.166 | 19.4981 | 32.9962 | 48.4944 | 8.3421 | 10.166 | 10.3321 | 9.3321 | 13.4981 | 15.4981 | 10.166 | 19.4981 | 32.9962 | 48.4944 | 0
4.4306 | 8.2153 | 6.4306 | 5.4306 | 7.6459 | 9.6459 | 8.2153 | 13.6459 | 21.2918 | 30.9377 | 4.4406 | 8.2153 | 6.4306 | 5.4306 | 7.6459 | 9.6459 | 8.2153 | 13.6459 | 21.2918 | 30.9377 | 0
5.963 | 8.9815 | 7.963 | 6.963 | 9.9446 | 11.9446 | 8.9815 | 15.9446 | 25.8891 | 37.8337 | 5.973 | 8.9815 | 7.963 | 6.963 | 9.9446 | 11.9446 | 8.9815 | 15.9446 | 25.8891 | 37.8337 | 0
5.0349 | 8.5174 | 7.0349 | 6.0349 | 8.5523 | 10.5523 | 8.5174 | 14.5523 | 23.1047 | 33.657 | 5.0449 | 8.5174 | 7.0349 | 6.0349 | 8.5523 | 10.5523 | 8.5174 | 14.5523 | 23.1047 | 33.657 | 0
7.8813 | 9.9407 | 9.8813 | 8.8813 | 12.822 | 14.822 | 9.9407 | 18.822 | 31.644 | 46.466 | 7.8913 | 9.9407 | 9.8813 | 8.8813 | 12.822 | 14.822 | 9.9407 | 18.822 | 31.644 | 46.466 | 0
2.9422 | 7.4711 | 4.9422 | 3.9422 | 5.4133 | 7.4133 | 7.4711 | 11.4133 | 16.8265 | 24.2398 | 2.9522 | 7.4711 | 4.9422 | 3.9422 | 5.4133 | 7.4133 | 7.4711 | 11.4133 | 16.8265 | 24.2398 | 0
5.5831 | 8.7915 | 7.5831 | 6.5831 | 9.3746 | 11.3746 | 8.7915 | 15.3746 | 24.7492 | 36.1238 | 5.5931 | 8.7915 | 7.5831 | 6.5831 | 9.3746 | 11.3746 | 8.7915 | 15.3746 | 24.7492 | 36.1238 | 0
6.1071 | 9.0535 | 8.1071 | 7.1071 | 10.1606 | 12.1606 | 9.0535 | 16.1606 | 26.3212 | 38.4818 | 6.1171 | 9.0535 | 8.1071 | 7.1071 | 10.1606 | 12.1606 | 9.0535 | 16.1606 | 26.3212 | 38.4818 | 0
3.7728 | 7.8864 | 5.7728 | 4.7728 | 6.6592 | 8.6592 | 7.8864 | 12.6592 | 19.3184 | 27.9776 | 3.7828 | 7.8864 | 5.7728 | 4.7728 | 6.6592 | 8.6592 | 7.8864 | 12.6592 | 19.3184 | 27.9776 | 0
7.4075 | 9.7038 | 9.4075 | 8.4075 | 12.1113 | 14.1113 | 9.7038 | 18.1113 | 30.2226 | 44.3338 | 7.4175 | 9.7038 | 9.4075 | 8.4075 | 12.1113 | 14.1113 | 9.7038 | 18.1113 | 30.2226 | 44.3338 | 0
4.9966 | 8.4983 | 6.9966 | 5.9966 | 8.4948 | 10.4948 | 8.4983 | 14.4948 | 22.9897 | 33.4845 | 5.0066 | 8.4983 | 6.9966 | 5.9966 | 8.4948 | 10.4948 | 8.4983 | 14.4948 | 22.9897 | 33.4845 | 0
5.7338 | 8.8669 | 7.7338 | 6.7338 | 9.6008 | 11.6008 | 8.8669 | 15.6008 | 25.2015 | 36.8023 | 5.7438 | 8.8669 | 7.7338 | 6.7338 | 9.6008 | 11.6008 | 8.8669 | 15.6008 | 25.2015 | 36.8023 | 0
9.5995 | 10.7997 | 11.5995 | 10.5995 | 15.3992 | 17.3992 | 10.7997 | 21.3992 | 36.7984 | 54.1977 | 9.6095 | 10.7997 | 11.5995 | 10.5995 | 15.3992 | 17.3992 | 10.7997 | 21.3992 | 36.7984 | 54.1977 | 0
4.5772 | 8.2886 | 6.5772 | 5.5772 | 7.8657 | 9.8657 | 8.2886 | 13.8657 | 21.7315 | 31.5972 | 4.5872 | 8.2886 | 6.5772 | 5.5772 | 7.8657 | 9.8657 | 8.2886 | 13.8657 | 21.7315 | 31.5972 | 0
6.272 | 9.136 | 8.272 | 7.272 | 10.408 | 12.408 | 9.136 | 16.408 | 26.8161 | 39.2241 | 6.282 | 9.136 | 8.272 | 7.272 | 10.408 | 12.408 | 9.136 | 16.408 | 26.8161 | 39.2241 | 0
8.0427 | 10.0214 | 10.0427 | 9.0427 | 13.0641 | 15.0641 | 10.0214 | 19.0641 | 32.1282 | 47.1924 | 8.0527 | 10.0214 | 10.0427 | 9.0427 | 13.0641 | 15.0641 | 10.0214 | 19.0641 | 32.1282 | 47.1924 | 0
7.5719 | 9.7859 | 9.5719 | 8.5719 | 12.3578 | 14.3578 | 9.7859 | 18.3578 | 30.7157 | 45.0735 | 7.5819 | 9.7859 | 9.5719 | 8.5719 | 12.3578 | 14.3578 | 9.7859 | 18.3578 | 30.7157 | 45.0735 | 0
5.6432 | 8.8216 | 7.6432 | 6.6432 | 9.4649 | 11.4649 | 8.8216 | 15.4649 | 24.9297 | 36.3946 | 5.6532 | 8.8216 | 7.6432 | 6.6432 | 9.4649 | 11.4649 | 8.8216 | 15.4649 | 24.9297 | 36.3946 | 0
8.7355 | 10.3677 | 10.7355 | 9.7355 | 14.1032 | 16.1032 | 10.3677 | 20.1032 | 34.2065 | 50.3097 | 8.7455 | 10.3677 | 10.7355 | 9.7355 | 14.1032 | 16.1032 | 10.3677 | 20.1032 | 34.2065 | 50.3097 | 0
5.0301 | 8.515 | 7.0301 | 6.0301 | 8.5451 | 10.5451 | 8.515 | 14.5451 | 23.0902 | 33.6354 | 5.0401 | 8.515 | 7.0301 | 6.0301 | 8.5451 | 10.5451 | 8.515 | 14.5451 | 23.0902 | 33.6354 | 0
7.0523 | 9.5262 | 9.0523 | 8.0523 | 11.5785 | 13.5785 | 9.5262 | 17.5785 | 29.157 | 42.7355 | 7.0623 | 9.5262 | 9.0523 | 8.0523 | 11.5785 | 13.5785 | 9.5262 | 17.5785 | 29.157 | 42.7355 | 0
7.9439 | 9.972 | 9.9439 | 8.9439 | 12.9159 | 14.9159 | 9.972 | 18.9159 | 31.8318 | 46.7478 | 7.9539 | 9.972 | 9.9439 | 8.9439 | 12.9159 | 14.9159 | 9.972 | 18.9159 | 31.8318 | 46.7478 | 0
8.5616 | 10.2808 | 10.5616 | 9.5616 | 13.8424 | 15.8424 | 10.2808 | 19.8424 | 33.6848 | 49.5272 | 8.5716 | 10.2808 | 10.5616 | 9.5616 | 13.8424 | 15.8424 | 10.2808 | 19.8424 | 33.6848 | 49.5272 | 0
7.3831 | 9.6916 | 9.3831 | 8.3831 | 12.0747 | 14.0747 | 9.6916 | 18.0747 | 30.1494 | 44.2241 | 7.3931 | 9.6916 | 9.3831 | 8.3831 | 12.0747 | 14.0747 | 9.6916 | 18.0747 | 30.1494 | 44.2241 | 0
4.1357 | 8.0679 | 6.1357 | 5.1357 | 7.2036 | 9.2036 | 8.0679 | 13.2036 | 20.4072 | 29.6108 | 4.1457 | 8.0679 | 6.1357 | 5.1357 | 7.2036 | 9.2036 | 8.0679 | 13.2036 | 20.4072 | 29.6108 | 0
2.1727 | 7.0864 | 4.1727 | 3.1727 | 4.2591 | 6.2591 | 7.0864 | 10.2591 | 14.5182 | 20.7772 | 2.1827 | 7.0864 | 4.1727 | 3.1727 | 4.2591 | 6.2591 | 7.0864 | 10.2591 | 14.5182 | 20.7772 | 0
5.5513 | 8.7756 | 7.5513 | 6.5513 | 9.3269 | 11.3269 | 8.7756 | 15.3269 | 24.6538 | 35.9807 | 5.5613 | 8.7756 | 7.5513 | 6.5513 | 9.3269 | 11.3269 | 8.7756 | 15.3269 | 24.6538 | 35.9807 | 0
3.49 | 7.745 | 5.49 | 4.49 | 6.235 | 8.235 | 7.745 | 12.235 | 18.47 | 26.705 | 3.5 | 7.745 | 5.49 | 4.49 | 6.235 | 8.235 | 7.745 | 12.235 | 18.47 | 26.705 | 0
0.33785 | 6.1689 | 2.3378 | 1.3378 | 1.5068 | 3.5068 | 6.1689 | 7.5068 | 9.0135 | 12.5203 | 0.34785 | 6.1689 | 2.3378 | 1.3378 | 1.5068 | 3.5068 | 6.1689 | 7.5068 | 9.0135 | 12.5203 | 0
5.2149 | 8.6075 | 7.2149 | 6.2149 | 8.8224 | 10.8224 | 8.6075 | 14.8224 | 23.6448 | 34.4672 | 5.2249 | 8.6075 | 7.2149 | 6.2149 | 8.8224 | 10.8224 | 8.6075 | 14.8224 | 23.6448 | 34.4672 | 0
7.5632 | 9.7816 | 9.5632 | 8.5632 | 12.3447 | 14.3447 | 9.7816 | 18.3447 | 30.6895 | 45.0342 | 7.5732 | 9.7816 | 9.5632 | 8.5632 | 12.3447 | 14.3447 | 9.7816 | 18.3447 | 30.6895 | 45.0342 | 0
7.7902 | 9.8951 | 9.7902 | 8.7902 | 12.6853 | 14.6853 | 9.8951 | 18.6853 | 31.3705 | 46.0558 | 7.8002 | 9.8951 | 9.7902 | 8.7902 | 12.6853 | 14.6853 | 9.8951 | 18.6853 | 31.3705 | 46.0558 | 0
9.4106 | 10.7053 | 11.4106 | 10.4106 | 15.1159 | 17.1159 | 10.7053 | 21.1159 | 36.2318 | 53.3477 | 9.4206 | 10.7053 | 11.4106 | 10.4106 | 15.1159 | 17.1159 | 10.7053 | 21.1159 | 36.2318 | 53.3477 | 0
6.338 | 9.169 | 8.338 | 7.338 | 10.5069 | 12.5069 | 9.169 | 16.5069 | 27.0139 | 39.5208 | 6.348 | 9.169 | 8.338 | 7.338 | 10.5069 | 12.5069 | 9.169 | 16.5069 | 27.0139 | 39.5208 | 0
8.4698 | 10.2349 | 10.4698 | 9.4698 | 13.7047 | 15.7047 | 10.2349 | 19.7047 | 33.4094 | 49.1142 | 8.4798 | 10.2349 | 10.4698 | 9.4698 | 13.7047 | 15.7047 | 10.2349 | 19.7047 | 33.4094 | 49.1142 | 0
3.966 | 7.983 | 5.966 | 4.966 | 6.949 | 8.949 | 7.983 | 12.949 | 19.898 | 28.847 | 3.976 | 7.983 | 5.966 | 4.966 | 6.949 | 8.949 | 7.983 | 12.949 | 19.898 | 28.847 | 0
2.0788 | 7.0394 | 4.0788 | 3.0788 | 4.1183 | 6.1183 | 7.0394 | 10.1183 | 14.2365 | 20.3548 | 2.0888 | 7.0394 | 4.0788 | 3.0788 | 4.1183 | 6.1183 | 7.0394 | 10.1183 | 14.2365 | 20.3548 | 0
7.9038 | 9.9519 | 9.9038 | 8.9038 | 12.8558 | 14.8558 | 9.9519 | 18.8558 | 31.7115 | 46.5673 | 7.9138 | 9.9519 | 9.9038 | 8.9038 | 12.8558 | 14.8558 | 9.9519 | 18.8558 | 31.7115 | 46.5673 | 0
5.9358 | 8.9679 | 7.9358 | 6.9358 | 9.9037 | 11.9037 | 8.9679 | 15.9037 | 25.8074 | 37.7111 | 5.9458 | 8.9679 | 7.9358 | 6.9358 | 9.9037 | 11.9037 | 8.9679 | 15.9037 | 25.8074 | 37.7111 | 0
8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 8.0577 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 0
6.657 | 9.3285 | 8.657 | 7.657 | 10.9856 | 12.9856 | 9.3285 | 16.9856 | 27.9711 | 40.9567 | 6.667 | 9.3285 | 8.657 | 7.657 | 10.9856 | 12.9856 | 9.3285 | 16.9856 | 27.9711 | 40.9567 | 0
6.5966 | 9.2983 | 8.5966 | 7.5966 | 10.8949 | 12.8949 | 9.2983 | 16.8949 | 27.7899 | 40.6848 | 6.6066 | 9.2983 | 8.5966 | 7.5966 | 10.8949 | 12.8949 | 9.2983 | 16.8949 | 27.7899 | 40.6848 | 0
5.4851 | 8.7426 | 7.4851 | 6.4851 | 9.2277 | 11.2277 | 8.7426 | 15.2277 | 24.4554 | 35.683 | 5.4951 | 8.7426 | 7.4851 | 6.4851 | 9.2277 | 11.2277 | 8.7426 | 15.2277 | 24.4554 | 35.683 | 0
3.0805 | 7.5402 | 5.0805 | 4.0805 | 5.6207 | 7.6207 | 7.5402 | 11.6207 | 17.2414 | 24.8621 | 3.0905 | 7.5402 | 5.0805 | 4.0805 | 5.6207 | 7.6207 | 7.5402 | 11.6207 | 17.2414 | 24.8621 | 0
7.2083 | 9.6042 | 9.2083 | 8.2083 | 11.8125 | 13.8125 | 9.6042 | 17.8125 | 29.625 | 43.4375 | 7.2183 | 9.6042 | 9.2083 | 8.2083 | 11.8125 | 13.8125 | 9.6042 | 17.8125 | 29.625 | 43.4375 | 0
2.7006 | 7.3503 | 4.7006 | 3.7006 | 5.0509 | 7.0509 | 7.3503 | 11.0509 | 16.1017 | 23.1526 | 2.7106 | 7.3503 | 4.7006 | 3.7006 | 5.0509 | 7.0509 | 7.3503 | 11.0509 | 16.1017 | 23.1526 | 0
7.4982 | 9.7491 | 9.4982 | 8.4982 | 12.2472 | 14.2472 | 9.7491 | 18.2472 | 30.4945 | 44.7417 | 7.5082 | 9.7491 | 9.4982 | 8.4982 | 12.2472 | 14.2472 | 9.7491 | 18.2472 | 30.4945 | 44.7417 | 0
5.3544 | 8.6772 | 7.3544 | 6.3544 | 9.0316 | 11.0316 | 8.6772 | 15.0316 | 24.0632 | 35.0948 | 5.3644 | 8.6772 | 7.3544 | 6.3544 | 9.0316 | 11.0316 | 8.6772 | 15.0316 | 24.0632 | 35.0948 | 0
4.5186 | 8.2593 | 6.5186 | 5.5186 | 7.7779 | 9.7779 | 8.2593 | 13.7779 | 21.5558 | 31.3337 | 4.5286 | 8.2593 | 6.5186 | 5.5186 | 7.7779 | 9.7779 | 8.2593 | 13.7779 | 21.5558 | 31.3337 | 0
4.8309 | 8.4155 | 6.8309 | 5.8309 | 8.2464 | 10.2464 | 8.4155 | 14.2464 | 22.4927 | 32.7391 | 4.8409 | 8.4155 | 6.8309 | 5.8309 | 8.2464 | 10.2464 | 8.4155 | 14.2464 | 22.4927 | 32.7391 | 0
1.1151 | 6.5575 | 3.1151 | 2.1151 | 2.6726 | 4.6726 | 6.5575 | 8.6726 | 11.3452 | 16.0178 | 1.1251 | 6.5575 | 3.1151 | 2.1151 | 2.6726 | 4.6726 | 6.5575 | 8.6726 | 11.3452 | 16.0178 | 0
5.9719 | 8.986 | 7.9719 | 6.9719 | 9.9579 | 11.9579 | 8.986 | 15.9579 | 25.9158 | 37.8737 | 5.9819 | 8.986 | 7.9719 | 6.9719 | 9.9579 | 11.9579 | 8.986 | 15.9579 | 25.9158 | 37.8737 | 0
6.5507 | 9.2754 | 8.5507 | 7.5507 | 10.8261 | 12.8261 | 9.2754 | 16.8261 | 27.6521 | 40.4782 | 6.5607 | 9.2754 | 8.5507 | 7.5507 | 10.8261 | 12.8261 | 9.2754 | 16.8261 | 27.6521 | 40.4782 | 0
4.8226 | 8.4113 | 6.8226 | 5.8226 | 8.2338 | 10.2338 | 8.4113 | 14.2338 | 22.4677 | 32.7015 | 4.8326 | 8.4113 | 6.8226 | 5.8226 | 8.2338 | 10.2338 | 8.4113 | 14.2338 | 22.4677 | 32.7015 | 0
6.1037 | 9.0519 | 8.1037 | 7.1037 | 10.1556 | 12.1556 | 9.0519 | 16.1556 | 26.3111 | 38.4667 | 6.1137 | 9.0519 | 8.1037 | 7.1037 | 10.1556 | 12.1556 | 9.0519 | 16.1556 | 26.3111 | 38.4667 | 0
6.9292 | 9.4646 | 8.9292 | 7.9292 | 11.3937 | 13.3937 | 9.4646 | 17.3937 | 28.7875 | 42.1812 | 6.9392 | 9.4646 | 8.9292 | 7.9292 | 11.3937 | 13.3937 | 9.4646 | 17.3937 | 28.7875 | 42.1812 | 0
3.7038 | 7.8519 | 5.7038 | 4.7038 | 6.5557 | 8.5557 | 7.8519 | 12.5557 | 19.1113 | 27.667 | 3.7138 | 7.8519 | 5.7038 | 4.7038 | 6.5557 | 8.5557 | 7.8519 | 12.5557 | 19.1113 | 27.667 | 0
7.5671 | 9.7836 | 9.5671 | 8.5671 | 12.3507 | 14.3507 | 9.7836 | 18.3507 | 30.7013 | 45.052 | 7.5771 | 9.7836 | 9.5671 | 8.5671 | 12.3507 | 14.3507 | 9.7836 | 18.3507 | 30.7013 | 45.052 | 0
2.3254 | 7.1627 | 4.3254 | 3.3254 | 4.4881 | 6.4881 | 7.1627 | 10.4881 | 14.9762 | 21.4642 | 2.3354 | 7.1627 | 4.3254 | 3.3254 | 4.4881 | 6.4881 | 7.1627 | 10.4881 | 14.9762 | 21.4642 | 0
5.8236 | 8.9118 | 7.8236 | 6.8236 | 9.7354 | 11.7354 | 8.9118 | 15.7354 | 25.4708 | 37.2062 | 5.8336 | 8.9118 | 7.8236 | 6.8236 | 9.7354 | 11.7354 | 8.9118 | 15.7354 | 25.4708 | 37.2062 | 0
6.3687 | 9.1844 | 8.3687 | 7.3687 | 10.5531 | 12.5531 | 9.1844 | 16.5531 | 27.1062 | 39.6593 | 6.3787 | 9.1844 | 8.3687 | 7.3687 | 10.5531 | 12.5531 | 9.1844 | 16.5531 | 27.1062 | 39.6593 | 0
7.032 | 9.516 | 9.032 | 8.032 | 11.548 | 13.548 | 9.516 | 17.548 | 29.096 | 42.644 | 7.042 | 9.516 | 9.032 | 8.032 | 11.548 | 13.548 | 9.516 | 17.548 | 29.096 | 42.644 | 0
5.9999 | 9 | 7.9999 | 6.9999 | 9.9999 | 11.9999 | 9 | 15.9999 | 25.9998 | 37.9997 | 6.0099 | 9 | 7.9999 | 6.9999 | 9.9999 | 11.9999 | 9 | 15.9999 | 25.9998 | 37.9997 | 0
6.0206 | 9.0103 | 8.0206 | 7.0206 | 10.0309 | 12.0309 | 9.0103 | 16.0309 | 26.0617 | 38.0926 | 6.0306 | 9.0103 | 8.0206 | 7.0206 | 10.0309 | 12.0309 | 9.0103 | 16.0309 | 26.0617 | 38.0926 | 0
9.147 | 10.5735 | 11.147 | 10.147 | 14.7205 | 16.7205 | 10.5735 | 20.7205 | 35.441 | 52.1614 | 9.157 | 10.5735 | 11.147 | 10.147 | 14.7205 | 16.7205 | 10.5735 | 20.7205 | 35.441 | 52.1614 | 0
7.1056 | 9.5528 | 9.1056 | 8.1056 | 11.6584 | 13.6584 | 9.5528 | 17.6584 | 29.3168 | 42.9752 | 7.1156 | 9.5528 | 9.1056 | 8.1056 | 11.6584 | 13.6584 | 9.5528 | 17.6584 | 29.3168 | 42.9752 | 0
[8 empty] | Average | 37.4427 | [8 empty] | Average |  | 0.1%

## test activity B
A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | diff
1.4288 | 6.7144 | 3.4288 | 2.4288 | 3.1433 | 5.1433 | 6.7144 | 9.1433 | 12.2865 | 17.4298 | 1.4288 | 6.7244 | 3.4288 | 2.4288 | 3.1433 | 5.1433 | 6.7244 | 9.1533 | 12.2965 | 17.4398 | 0.01
2.4295 | 7.2148 | 4.4295 | 3.4295 | 4.6443 | 6.6443 | 7.2148 | 10.6443 | 15.2885 | 21.9328 | 2.4295 | 7.2248 | 4.4295 | 3.4295 | 4.6443 | 6.6443 | 7.2248 | 10.6543 | 15.2985 | 21.9428 | 0.01
4.0538 | 8.0269 | 6.0538 | 5.0538 | 7.0808 | 9.0808 | 8.0269 | 13.0808 | 20.1615 | 29.2423 | 4.0538 | 8.0369 | 6.0538 | 5.0538 | 7.0808 | 9.0808 | 8.0369 | 13.0908 | 20.1715 | 29.2523 | 0.01
6.049 | 9.0245 | 8.049 | 7.049 | 10.0736 | 12.0736 | 9.0245 | 16.0736 | 26.1471 | 38.2207 | 6.049 | 9.0345 | 8.049 | 7.049 | 10.0736 | 12.0736 | 9.0345 | 16.0836 | 26.1571 | 38.2307 | 0.01
7.3353 | 9.6677 | 9.3353 | 8.3353 | 12.003 | 14.003 | 9.6677 | 18.003 | 30.006 | 44.009 | 7.3353 | 9.6777 | 9.3353 | 8.3353 | 12.003 | 14.003 | 9.6777 | 18.013 | 30.016 | 44.019 | 0.01
5.1939 | 8.5969 | 7.1939 | 6.1939 | 8.7908 | 10.7908 | 8.5969 | 14.7908 | 23.5817 | 34.3725 | 5.1939 | 8.6069 | 7.1939 | 6.1939 | 8.7908 | 10.7908 | 8.6069 | 14.8008 | 23.5917 | 34.3825 | 0.01
7.3727 | 9.6863 | 9.3727 | 8.3727 | 12.059 | 14.059 | 9.6863 | 18.059 | 30.118 | 44.1769 | 7.3727 | 9.6963 | 9.3727 | 8.3727 | 12.059 | 14.059 | 9.6963 | 18.069 | 30.128 | 44.1869 | 0.01
2.7474 | 7.3737 | 4.7474 | 3.7474 | 5.1211 | 7.1211 | 7.3737 | 11.1211 | 16.2422 | 23.3633 | 2.7474 | 7.3837 | 4.7474 | 3.7474 | 5.1211 | 7.1211 | 7.3837 | 11.1311 | 16.2522 | 23.3733 | 0.01
7.0969 | 9.5484 | 9.0969 | 8.0969 | 11.6453 | 13.6453 | 9.5484 | 17.6453 | 29.2906 | 42.9359 | 7.0969 | 9.5584 | 9.0969 | 8.0969 | 11.6453 | 13.6453 | 9.5584 | 17.6553 | 29.3006 | 42.9459 | 0.01
4.1058 | 8.0529 | 6.1058 | 5.1058 | 7.1586 | 9.1586 | 8.0529 | 13.1586 | 20.3173 | 29.4759 | 4.1058 | 8.0629 | 6.1058 | 5.1058 | 7.1586 | 9.1586 | 8.0629 | 13.1686 | 20.3273 | 29.4859 | 0.01
7.2091 | 9.6045 | 9.2091 | 8.2091 | 11.8136 | 13.8136 | 9.6045 | 17.8136 | 29.6272 | 43.4408 | 7.2091 | 9.6145 | 9.2091 | 8.2091 | 11.8136 | 13.8136 | 9.6145 | 17.8236 | 29.6372 | 43.4508 | 0.01
10.8182 | 11.4091 | 12.8182 | 11.8182 | 17.2273 | 19.2273 | 11.4091 | 23.2273 | 40.4546 | 59.682 | 10.8182 | 11.4191 | 12.8182 | 11.8182 | 17.2273 | 19.2273 | 11.4191 | 23.2373 | 40.4646 | 59.692 | 0.01
6.4931 | 9.2465 | 8.4931 | 7.4931 | 10.7396 | 12.7396 | 9.2465 | 16.7396 | 27.4793 | 40.2189 | 6.4931 | 9.2565 | 8.4931 | 7.4931 | 10.7396 | 12.7396 | 9.2565 | 16.7496 | 27.4893 | 40.2289 | 0.01
6.0198 | 9.0099 | 8.0198 | 7.0198 | 10.0297 | 12.0297 | 9.0099 | 16.0297 | 26.0594 | 38.0892 | 6.0198 | 9.0199 | 8.0198 | 7.0198 | 10.0297 | 12.0297 | 9.0199 | 16.0397 | 26.0694 | 38.0992 | 0.01
5.2393 | 8.6197 | 7.2393 | 6.2393 | 8.859 | 10.859 | 8.6197 | 14.859 | 23.718 | 34.577 | 5.2393 | 8.6297 | 7.2393 | 6.2393 | 8.859 | 10.859 | 8.6297 | 14.869 | 23.728 | 34.587 | 0.01
5.4805 | 8.7403 | 7.4805 | 6.4805 | 9.2208 | 11.2208 | 8.7403 | 15.2208 | 24.4416 | 35.6624 | 5.4805 | 8.7503 | 7.4805 | 6.4805 | 9.2208 | 11.2208 | 8.7503 | 15.2308 | 24.4516 | 35.6724 | 0.01
3.5992 | 7.7996 | 5.5992 | 4.5992 | 6.3988 | 8.3988 | 7.7996 | 12.3988 | 18.7976 | 27.1965 | 3.5992 | 7.8096 | 5.5992 | 4.5992 | 6.3988 | 8.3988 | 7.8096 | 12.4088 | 18.8076 | 27.2065 | 0.01
2.2806 | 7.1403 | 4.2806 | 3.2806 | 4.4209 | 6.4209 | 7.1403 | 10.4209 | 14.8419 | 21.2628 | 2.2806 | 7.1503 | 4.2806 | 3.2806 | 4.4209 | 6.4209 | 7.1503 | 10.4309 | 14.8519 | 21.2728 | 0.01
6.9264 | 9.4632 | 8.9264 | 7.9264 | 11.3897 | 13.3897 | 9.4632 | 17.3897 | 28.7793 | 42.169 | 6.9264 | 9.4732 | 8.9264 | 7.9264 | 11.3897 | 13.3897 | 9.4732 | 17.3997 | 28.7893 | 42.179 | 0.01
4.5848 | 8.2924 | 6.5848 | 5.5848 | 7.8772 | 9.8772 | 8.2924 | 13.8772 | 21.7545 | 31.6317 | 4.5848 | 8.3024 | 6.5848 | 5.5848 | 7.8772 | 9.8772 | 8.3024 | 13.8872 | 21.7645 | 31.6417 | 0.01
5.8871 | 8.9436 | 7.8871 | 6.8871 | 9.8307 | 11.8307 | 8.9436 | 15.8307 | 25.6613 | 37.492 | 5.8871 | 8.9536 | 7.8871 | 6.8871 | 9.8307 | 11.8307 | 8.9536 | 15.8407 | 25.6713 | 37.502 | 0.01
4.4375 | 8.2187 | 6.4375 | 5.4375 | 7.6562 | 9.6562 | 8.2187 | 13.6562 | 21.3124 | 30.9686 | 4.4375 | 8.2287 | 6.4375 | 5.4375 | 7.6562 | 9.6562 | 8.2287 | 13.6662 | 21.3224 | 30.9786 | 0.01
5.9122 | 8.9561 | 7.9122 | 6.9122 | 9.8683 | 11.8683 | 8.9561 | 15.8683 | 25.7367 | 37.605 | 5.9122 | 8.9661 | 7.9122 | 6.9122 | 9.8683 | 11.8683 | 8.9661 | 15.8783 | 25.7467 | 37.615 | 0.01
4.2985 | 8.1493 | 6.2985 | 5.2985 | 7.4478 | 9.4478 | 8.1493 | 13.4478 | 20.8955 | 30.3433 | 4.2985 | 8.1593 | 6.2985 | 5.2985 | 7.4478 | 9.4478 | 8.1593 | 13.4578 | 20.9055 | 30.3533 | 0.01
3.7284 | 7.8642 | 5.7284 | 4.7284 | 6.5927 | 8.5927 | 7.8642 | 12.5927 | 19.1853 | 27.778 | 3.7284 | 7.8742 | 5.7284 | 4.7284 | 6.5927 | 8.5927 | 7.8742 | 12.6027 | 19.1953 | 27.788 | 0.01
7.6067 | 9.8034 | 9.6067 | 8.6067 | 12.4101 | 14.4101 | 9.8034 | 18.4101 | 30.8202 | 45.2303 | 7.6067 | 9.8134 | 9.6067 | 8.6067 | 12.4101 | 14.4101 | 9.8134 | 18.4201 | 30.8302 | 45.2403 | 0.01
8.6808 | 10.3404 | 10.6808 | 9.6808 | 14.0212 | 16.0212 | 10.3404 | 20.0212 | 34.0423 | 50.0635 | 8.6808 | 10.3504 | 10.6808 | 9.6808 | 14.0212 | 16.0212 | 10.3504 | 20.0312 | 34.0523 | 50.0735 | 0.01
5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 5.2196 | 8.6198 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6198 | 14.8393 | 23.6687 | 34.498 | 0.01
7.6331 | 9.8165 | 9.6331 | 8.6331 | 12.4496 | 14.4496 | 9.8165 | 18.4496 | 30.8992 | 45.3488 | 7.6331 | 9.8265 | 9.6331 | 8.6331 | 12.4496 | 14.4496 | 9.8265 | 18.4596 | 30.9092 | 45.3588 | 0.01
4.2833 | 8.1416 | 6.2833 | 5.2833 | 7.4249 | 9.4249 | 8.1416 | 13.4249 | 20.8499 | 30.2748 | 4.2833 | 8.1516 | 6.2833 | 5.2833 | 7.4249 | 9.4249 | 8.1516 | 13.4349 | 20.8599 | 30.2848 | 0.01
4.5407 | 8.2703 | 6.5407 | 5.5407 | 7.811 | 9.811 | 8.2703 | 13.811 | 21.622 | 31.433 | 4.5407 | 8.2803 | 6.5407 | 5.5407 | 7.811 | 9.811 | 8.2803 | 13.821 | 21.632 | 31.443 | 0.01
6.1115 | 9.0558 | 8.1115 | 7.1115 | 10.1673 | 12.1673 | 9.0558 | 16.1673 | 26.3345 | 38.5018 | 6.1115 | 9.0658 | 8.1115 | 7.1115 | 10.1673 | 12.1673 | 9.0658 | 16.1773 | 26.3445 | 38.5118 | 0.01
6.1999 | 9.1 | 8.1999 | 7.1999 | 10.2999 | 12.2999 | 9.1 | 16.2999 | 26.5997 | 38.8996 | 6.1999 | 9.11 | 8.1999 | 7.1999 | 10.2999 | 12.2999 | 9.11 | 16.3099 | 26.6097 | 38.9096 | 0.01
2.8161 | 7.408 | 4.8161 | 3.8161 | 5.2241 | 7.2241 | 7.408 | 11.2241 | 16.4482 | 23.6723 | 2.8161 | 7.418 | 4.8161 | 3.8161 | 5.2241 | 7.2241 | 7.418 | 11.2341 | 16.4582 | 23.6823 | 0.01
6.6314 | 9.3157 | 8.6314 | 7.6314 | 10.9471 | 12.9471 | 9.3157 | 16.9471 | 27.8943 | 40.8414 | 6.6314 | 9.3257 | 8.6314 | 7.6314 | 10.9471 | 12.9471 | 9.3257 | 16.9571 | 27.9043 | 40.8514 | 0.01
6.5394 | 9.2697 | 8.5394 | 7.5394 | 10.8092 | 12.8092 | 9.2697 | 16.8092 | 27.6183 | 40.4275 | 6.5394 | 9.2797 | 8.5394 | 7.5394 | 10.8092 | 12.8092 | 9.2797 | 16.8192 | 27.6283 | 40.4375 | 0.01
11.0521 | 11.526 | 13.0521 | 12.0521 | 17.5781 | 19.5781 | 11.526 | 23.5781 | 41.1562 | 60.7343 | 11.0521 | 11.536 | 13.0521 | 12.0521 | 17.5781 | 19.5781 | 11.536 | 23.5881 | 41.1662 | 60.7443 | 0.01
3.8102 | 7.9051 | 5.8102 | 4.8102 | 6.7153 | 8.7153 | 7.9051 | 12.7153 | 19.4307 | 28.146 | 3.8102 | 7.9151 | 5.8102 | 4.8102 | 6.7153 | 8.7153 | 7.9151 | 12.7253 | 19.4407 | 28.156 | 0.01
5.2518 | 8.6259 | 7.2518 | 6.2518 | 8.8777 | 10.8777 | 8.6259 | 14.8777 | 23.7554 | 34.6332 | 5.2518 | 8.6359 | 7.2518 | 6.2518 | 8.8777 | 10.8777 | 8.6359 | 14.8877 | 23.7654 | 34.6432 | 0.01
6.3771 | 9.1886 | 8.3771 | 7.3771 | 10.5657 | 12.5657 | 9.1886 | 16.5657 | 27.1314 | 39.6971 | 6.3771 | 9.1986 | 8.3771 | 7.3771 | 10.5657 | 12.5657 | 9.1986 | 16.5757 | 27.1414 | 39.7071 | 0.01
5.3383 | 8.6691 | 7.3383 | 6.3383 | 9.0074 | 11.0074 | 8.6691 | 15.0074 | 24.0148 | 35.0222 | 5.3383 | 8.6791 | 7.3383 | 6.3383 | 9.0074 | 11.0074 | 8.6791 | 15.0174 | 24.0248 | 35.0322 | 0.01
8.3948 | 10.1974 | 10.3948 | 9.3948 | 13.5922 | 15.5922 | 10.1974 | 19.5922 | 33.1845 | 48.7767 | 8.3948 | 10.2074 | 10.3948 | 9.3948 | 13.5922 | 15.5922 | 10.2074 | 19.6022 | 33.1945 | 48.7867 | 0.01
5.0712 | 8.5356 | 7.0712 | 6.0712 | 8.6068 | 10.6068 | 8.5356 | 14.6068 | 23.2135 | 33.8203 | 5.0712 | 8.5456 | 7.0712 | 6.0712 | 8.6068 | 10.6068 | 8.5456 | 14.6168 | 23.2235 | 33.8303 | 0.01
6.1543 | 9.0771 | 8.1543 | 7.1543 | 10.2314 | 12.2314 | 9.0771 | 16.2314 | 26.4629 | 38.6943 | 6.1543 | 9.0871 | 8.1543 | 7.1543 | 10.2314 | 12.2314 | 9.0871 | 16.2414 | 26.4729 | 38.7043 | 0.01
5.863 | 8.9315 | 7.863 | 6.863 | 9.7946 | 11.7946 | 8.9315 | 15.7946 | 25.5891 | 37.3837 | 5.863 | 8.9415 | 7.863 | 6.863 | 9.7946 | 11.7946 | 8.9415 | 15.8046 | 25.5991 | 37.3937 | 0.01
2.5835 | 7.2917 | 4.5835 | 3.5835 | 4.8752 | 6.8752 | 7.2917 | 10.8752 | 15.7504 | 22.6257 | 2.5835 | 7.3017 | 4.5835 | 3.5835 | 4.8752 | 6.8752 | 7.3017 | 10.8852 | 15.7604 | 22.6357 | 0.01
5.0249 | 8.5125 | 7.0249 | 6.0249 | 8.5374 | 10.5374 | 8.5125 | 14.5374 | 23.0747 | 33.6121 | 5.0249 | 8.5225 | 7.0249 | 6.0249 | 8.5374 | 10.5374 | 8.5225 | 14.5474 | 23.0847 | 33.6221 | 0.01
6.1918 | 9.0959 | 8.1918 | 7.1918 | 10.2877 | 12.2877 | 9.0959 | 16.2877 | 26.5753 | 38.863 | 6.1918 | 9.1059 | 8.1918 | 7.1918 | 10.2877 | 12.2877 | 9.1059 | 16.2977 | 26.5853 | 38.873 | 0.01
5.0897 | 8.5449 | 7.0897 | 6.0897 | 8.6346 | 10.6346 | 8.5449 | 14.6346 | 23.2691 | 33.9037 | 5.0897 | 8.5549 | 7.0897 | 6.0897 | 8.6346 | 10.6346 | 8.5549 | 14.6446 | 23.2791 | 33.9137 | 0.01
5.4889 | 8.7445 | 7.4889 | 6.4889 | 9.2334 | 11.2334 | 8.7445 | 15.2334 | 24.4667 | 35.7001 | 5.4889 | 8.7545 | 7.4889 | 6.4889 | 9.2334 | 11.2334 | 8.7545 | 15.2434 | 24.4767 | 35.7101 | 0.01
8.7445 | 10.3722 | 10.7445 | 9.7445 | 14.1167 | 16.1167 | 10.3722 | 20.1167 | 34.2334 | 50.3502 | 8.7445 | 10.3822 | 10.7445 | 9.7445 | 14.1167 | 16.1167 | 10.3822 | 20.1267 | 34.2434 | 50.3602 | 0.01
6.1328 | 9.0664 | 8.1328 | 7.1328 | 10.1992 | 12.1992 | 9.0664 | 16.1992 | 26.3985 | 38.5977 | 6.1328 | 9.0764 | 8.1328 | 7.1328 | 10.1992 | 12.1992 | 9.0764 | 16.2092 | 26.4085 | 38.6077 | 0.01
6.4019 | 9.201 | 8.4019 | 7.4019 | 10.6029 | 12.6029 | 9.201 | 16.6029 | 27.2058 | 39.8087 | 6.4019 | 9.211 | 8.4019 | 7.4019 | 10.6029 | 12.6029 | 9.211 | 16.6129 | 27.2158 | 39.8187 | 0.01
4.0371 | 8.0185 | 6.0371 | 5.0371 | 7.0556 | 9.0556 | 8.0185 | 13.0556 | 20.1112 | 29.1668 | 4.0371 | 8.0285 | 6.0371 | 5.0371 | 7.0556 | 9.0556 | 8.0285 | 13.0656 | 20.1212 | 29.1768 | 0.01
5.83 | 8.915 | 7.83 | 6.83 | 9.7451 | 11.7451 | 8.915 | 15.7451 | 25.4901 | 37.2352 | 5.83 | 8.925 | 7.83 | 6.83 | 9.7451 | 11.7451 | 8.925 | 15.7551 | 25.5001 | 37.2452 | 0.01
2.6753 | 7.3376 | 4.6753 | 3.6753 | 5.0129 | 7.0129 | 7.3376 | 11.0129 | 16.0258 | 23.0387 | 2.6753 | 7.3476 | 4.6753 | 3.6753 | 5.0129 | 7.0129 | 7.3476 | 11.0229 | 16.0358 | 23.0487 | 0.01
5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 5.3559 | 8.6879 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6879 | 15.0438 | 24.0776 | 35.1113 | 0.01
2.6862 | 7.3431 | 4.6862 | 3.6862 | 5.0293 | 7.0293 | 7.3431 | 11.0293 | 16.0585 | 23.0878 | 2.6862 | 7.3531 | 4.6862 | 3.6862 | 5.0293 | 7.0293 | 7.3531 | 11.0393 | 16.0685 | 23.0978 | 0.01
9.7341 | 10.8671 | 11.7341 | 10.7341 | 15.6012 | 17.6012 | 10.8671 | 21.6012 | 37.2024 | 54.8037 | 9.7341 | 10.8771 | 11.7341 | 10.7341 | 15.6012 | 17.6012 | 10.8771 | 21.6112 | 37.2124 | 54.8137 | 0.01
4.1077 | 8.0538 | 6.1077 | 5.1077 | 7.1615 | 9.1615 | 8.0538 | 13.1615 | 20.323 | 29.4845 | 4.1077 | 8.0638 | 6.1077 | 5.1077 | 7.1615 | 9.1615 | 8.0638 | 13.1715 | 20.333 | 29.4945 | 0.01
7.484 | 9.742 | 9.484 | 8.484 | 12.226 | 14.226 | 9.742 | 18.226 | 30.452 | 44.6781 | 7.484 | 9.752 | 9.484 | 8.484 | 12.226 | 14.226 | 9.752 | 18.236 | 30.462 | 44.6881 | 0.01
6.2666 | 9.1333 | 8.2666 | 7.2666 | 10.3999 | 12.3999 | 9.1333 | 16.3999 | 26.7999 | 39.1998 | 6.2666 | 9.1433 | 8.2666 | 7.2666 | 10.3999 | 12.3999 | 9.1433 | 16.4099 | 26.8099 | 39.2098 | 0.01
5.2959 | 8.648 | 7.2959 | 6.2959 | 8.9439 | 10.9439 | 8.648 | 14.9439 | 23.8878 | 34.8317 | 5.2959 | 8.658 | 7.2959 | 6.2959 | 8.9439 | 10.9439 | 8.658 | 14.9539 | 23.8978 | 34.8417 | 0.01
4.8999 | 8.45 | 6.8999 | 5.8999 | 8.3499 | 10.3499 | 8.45 | 14.3499 | 22.6998 | 33.0497 | 4.8999 | 8.46 | 6.8999 | 5.8999 | 8.3499 | 10.3499 | 8.46 | 14.3599 | 22.7098 | 33.0597 | 0.01
5.8151 | 8.9076 | 7.8151 | 6.8151 | 9.7227 | 11.7227 | 8.9076 | 15.7227 | 25.4454 | 37.1682 | 5.8151 | 8.9176 | 7.8151 | 6.8151 | 9.7227 | 11.7227 | 8.9176 | 15.7327 | 25.4554 | 37.1782 | 0.01
5.9292 | 8.9646 | 7.9292 | 6.9292 | 9.8938 | 11.8938 | 8.9646 | 15.8938 | 25.7877 | 37.6815 | 5.9292 | 8.9746 | 7.9292 | 6.9292 | 9.8938 | 11.8938 | 8.9746 | 15.9038 | 25.7977 | 37.6915 | 0.01
2.9022 | 7.4511 | 4.9022 | 3.9022 | 5.3533 | 7.3533 | 7.4511 | 11.3533 | 16.7065 | 24.0598 | 2.9022 | 7.4611 | 4.9022 | 3.9022 | 5.3533 | 7.3533 | 7.4611 | 11.3633 | 16.7165 | 24.0698 | 0.01
3.7424 | 7.8712 | 5.7424 | 4.7424 | 6.6136 | 8.6136 | 7.8712 | 12.6136 | 19.2272 | 27.8407 | 3.7424 | 7.8812 | 5.7424 | 4.7424 | 6.6136 | 8.6136 | 7.8812 | 12.6236 | 19.2372 | 27.8507 | 0.01
8.3173 | 10.1587 | 10.3173 | 9.3173 | 13.476 | 15.476 | 10.1587 | 19.476 | 32.952 | 48.4281 | 8.3173 | 10.1687 | 10.3173 | 9.3173 | 13.476 | 15.476 | 10.1687 | 19.486 | 32.962 | 48.4381 | 0.01
4.7975 | 8.3988 | 6.7975 | 5.7975 | 8.1963 | 10.1963 | 8.3988 | 14.1963 | 22.3926 | 32.5889 | 4.7975 | 8.4088 | 6.7975 | 5.7975 | 8.1963 | 10.1963 | 8.4088 | 14.2063 | 22.4026 | 32.5989 | 0.01
4.0727 | 8.0363 | 6.0727 | 5.0727 | 7.109 | 9.109 | 8.0363 | 13.109 | 20.218 | 29.327 | 4.0727 | 8.0463 | 6.0727 | 5.0727 | 7.109 | 9.109 | 8.0463 | 13.119 | 20.228 | 29.337 | 0.01
7.2028 | 9.6014 | 9.2028 | 8.2028 | 11.8042 | 13.8042 | 9.6014 | 17.8042 | 29.6085 | 43.4127 | 7.2028 | 9.6114 | 9.2028 | 8.2028 | 11.8042 | 13.8042 | 9.6114 | 17.8142 | 29.6185 | 43.4227 | 0.01
5.1967 | 8.5984 | 7.1967 | 6.1967 | 8.7951 | 10.7951 | 8.5984 | 14.7951 | 23.5902 | 34.3852 | 5.1967 | 8.6084 | 7.1967 | 6.1967 | 8.7951 | 10.7951 | 8.6084 | 14.8051 | 23.6002 | 34.3952 | 0.01
3.0576 | 7.5288 | 5.0576 | 4.0576 | 5.5864 | 7.5864 | 7.5288 | 11.5864 | 17.1729 | 24.7593 | 3.0576 | 7.5388 | 5.0576 | 4.0576 | 5.5864 | 7.5864 | 7.5388 | 11.5964 | 17.1829 | 24.7693 | 0.01
4.772 | 8.386 | 6.772 | 5.772 | 8.1579 | 10.1579 | 8.386 | 14.1579 | 22.3159 | 32.4738 | 4.772 | 8.396 | 6.772 | 5.772 | 8.1579 | 10.1579 | 8.396 | 14.1679 | 22.3259 | 32.4838 | 0.01
6.9343 | 9.4671 | 8.9343 | 7.9343 | 11.4014 | 13.4014 | 9.4671 | 17.4014 | 28.8028 | 42.2043 | 6.9343 | 9.4771 | 8.9343 | 7.9343 | 11.4014 | 13.4014 | 9.4771 | 17.4114 | 28.8128 | 42.2143 | 0.01
5.9782 | 8.9891 | 7.9782 | 6.9782 | 9.9673 | 11.9673 | 8.9891 | 15.9673 | 25.9346 | 37.9019 | 5.9782 | 8.9991 | 7.9782 | 6.9782 | 9.9673 | 11.9673 | 8.9991 | 15.9773 | 25.9446 | 37.9119 | 0.01
4.3539 | 8.1769 | 6.3539 | 5.3539 | 7.5308 | 9.5308 | 8.1769 | 13.5308 | 21.0616 | 30.5925 | 4.3539 | 8.1869 | 6.3539 | 5.3539 | 7.5308 | 9.5308 | 8.1869 | 13.5408 | 21.0716 | 30.6025 | 0.01
4.4273 | 8.2136 | 6.4273 | 5.4273 | 7.6409 | 9.6409 | 8.2136 | 13.6409 | 21.2818 | 30.9227 | 4.4273 | 8.2236 | 6.4273 | 5.4273 | 7.6409 | 9.6409 | 8.2236 | 13.6509 | 21.2918 | 30.9327 | 0.01
5.6648 | 8.8324 | 7.6648 | 6.6648 | 9.4972 | 11.4972 | 8.8324 | 15.4972 | 24.9945 | 36.4917 | 5.6648 | 8.8424 | 7.6648 | 6.6648 | 9.4972 | 11.4972 | 8.8424 | 15.5072 | 25.0045 | 36.5017 | 0.01
6.1502 | 9.0751 | 8.1502 | 7.1502 | 10.2252 | 12.2252 | 9.0751 | 16.2252 | 26.4505 | 38.6757 | 6.1502 | 9.0851 | 8.1502 | 7.1502 | 10.2252 | 12.2252 | 9.0851 | 16.2352 | 26.4605 | 38.6857 | 0.01
13.0455 | 12.5227 | 15.0455 | 14.0455 | 20.5682 | 22.5682 | 13.0455 | 27.0909 | 47.6591 | 70.2273 | 13.0455 | 12.5327 | 15.0455 | 14.0455 | 20.5682 | 22.5682 | 13.0455 | 27.0909 | 47.6591 | 70.2273 | 0
7.6173 | 9.8087 | 9.6173 | 8.6173 | 12.426 | 14.426 | 9.8087 | 18.426 | 30.8519 | 45.2779 | 7.6173 | 9.8187 | 9.6173 | 8.6173 | 12.426 | 14.426 | 9.8187 | 18.436 | 30.8619 | 45.2879 | 0.01
8.3774 | 10.1887 | 10.3774 | 9.3774 | 13.566 | 15.566 | 10.1887 | 19.566 | 33.1321 | 48.6981 | 8.3774 | 10.1987 | 10.3774 | 9.3774 | 13.566 | 15.566 | 10.1987 | 19.576 | 33.1421 | 48.7081 | 0.01
6.074 | 9.037 | 8.074 | 7.074 | 10.111 | 12.111 | 9.037 | 16.111 | 26.222 | 38.333 | 6.074 | 9.047 | 8.074 | 7.074 | 10.111 | 12.111 | 9.047 | 16.121 | 26.232 | 38.343 | 0.01
5.9353 | 8.9677 | 7.9353 | 6.9353 | 9.903 | 11.903 | 8.9677 | 15.903 | 25.806 | 37.7091 | 5.9353 | 8.9777 | 7.9353 | 6.9353 | 9.903 | 11.903 | 8.9777 | 15.913 | 25.816 | 37.7191 | 0.01
6.9629 | 9.4814 | 8.9629 | 7.9629 | 11.4443 | 13.4443 | 9.4814 | 17.4443 | 28.8886 | 42.3329 | 6.9629 | 9.4914 | 8.9629 | 7.9629 | 11.4443 | 13.4443 | 9.4914 | 17.4543 | 28.8986 | 42.3429 | 0.01
3.2723 | 7.6361 | 5.2723 | 4.2723 | 5.9084 | 7.9084 | 7.6361 | 11.9084 | 17.8169 | 25.7253 | 3.2723 | 7.6461 | 5.2723 | 4.2723 | 5.9084 | 7.9084 | 7.6461 | 11.9184 | 17.8269 | 25.7353 | 0.01
5.3875 | 8.6938 | 7.3875 | 6.3875 | 9.0813 | 11.0813 | 8.6938 | 15.0813 | 24.1626 | 35.2438 | 5.3875 | 8.7038 | 7.3875 | 6.3875 | 9.0813 | 11.0813 | 8.7038 | 15.0913 | 24.1726 | 35.2538 | 0.01
2.8991 | 7.4496 | 4.8991 | 3.8991 | 5.3487 | 7.3487 | 7.4496 | 11.3487 | 16.6974 | 24.0461 | 2.8991 | 7.4596 | 4.8991 | 3.8991 | 5.3487 | 7.3487 | 7.4596 | 11.3587 | 16.7074 | 24.0561 | 0.01
6.8927 | 9.4463 | 8.8927 | 7.8927 | 11.339 | 13.339 | 9.4463 | 17.339 | 28.678 | 42.017 | 6.8927 | 9.4563 | 8.8927 | 7.8927 | 11.339 | 13.339 | 9.4563 | 17.349 | 28.688 | 42.027 | 0.01
5.2946 | 8.6473 | 7.2946 | 6.2946 | 8.942 | 10.942 | 8.6473 | 14.942 | 23.8839 | 34.8259 | 5.2946 | 8.6573 | 7.2946 | 6.2946 | 8.942 | 10.942 | 8.6573 | 14.952 | 23.8939 | 34.8359 | 0.01
7.3723 | 9.6861 | 9.3723 | 8.3723 | 12.0584 | 14.0584 | 9.6861 | 18.0584 | 30.1168 | 44.1752 | 7.3723 | 9.6961 | 9.3723 | 8.3723 | 12.0584 | 14.0584 | 9.6961 | 18.0684 | 30.1268 | 44.1852 | 0.01
6.4354 | 9.2177 | 8.4354 | 7.4354 | 10.6531 | 12.6531 | 9.2177 | 16.6531 | 27.3062 | 39.9593 | 6.4354 | 9.2277 | 8.4354 | 7.4354 | 10.6531 | 12.6531 | 9.2277 | 16.6631 | 27.3162 | 39.9693 | 0.01
5.4793 | 8.7396 | 7.4793 | 6.4793 | 9.2189 | 11.2189 | 8.7396 | 15.2189 | 24.4378 | 35.6567 | 5.4793 | 8.7496 | 7.4793 | 6.4793 | 9.2189 | 11.2189 | 8.7496 | 15.2289 | 24.4478 | 35.6667 | 0.01
6.2472 | 9.1236 | 8.2472 | 7.2472 | 10.3708 | 12.3708 | 9.1236 | 16.3708 | 26.7415 | 39.1123 | 6.2472 | 9.1336 | 8.2472 | 7.2472 | 10.3708 | 12.3708 | 9.1336 | 16.3808 | 26.7515 | 39.1223 | 0.01
4.9739 | 8.487 | 6.9739 | 5.9739 | 8.4609 | 10.4609 | 8.487 | 14.4609 | 22.9218 | 33.3827 | 4.9739 | 8.497 | 6.9739 | 5.9739 | 8.4609 | 10.4609 | 8.497 | 14.4709 | 22.9318 | 33.3927 | 0.01
1.3058 | 6.6529 | 3.3058 | 2.3058 | 2.9588 | 4.9588 | 6.6529 | 8.9588 | 11.9175 | 16.8763 | 1.3058 | 6.6629 | 3.3058 | 2.3058 | 2.9588 | 4.9588 | 6.6629 | 8.9688 | 11.9275 | 16.8863 | 0.01
6.9362 | 9.4681 | 8.9362 | 7.9362 | 11.4042 | 13.4042 | 9.4681 | 17.4042 | 28.8085 | 42.2127 | 6.9362 | 9.4781 | 8.9362 | 7.9362 | 11.4042 | 13.4042 | 9.4781 | 17.4142 | 28.8185 | 42.2227 | 0.01
7.1438 | 9.5719 | 9.1438 | 8.1438 | 11.7157 | 13.7157 | 9.5719 | 17.7157 | 29.4313 | 43.147 | 7.1438 | 9.5819 | 9.1438 | 8.1438 | 11.7157 | 13.7157 | 9.5819 | 17.7257 | 29.4413 | 43.157 | 0.01
7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 7.2523 | 9.6362 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6362 | 17.8885 | 29.767 | 43.6455 | 0.01
10.4708 | 11.2354 | 12.4708 | 11.4708 | 16.7062 | 18.7062 | 11.2354 | 22.7062 | 39.4124 | 58.1185 | 10.4708 | 11.2454 | 12.4708 | 11.4708 | 16.7062 | 18.7062 | 11.2454 | 22.7162 | 39.4224 | 58.1285 | 0.01
7.3244 | 9.6622 | 9.3244 | 8.3244 | 11.9867 | 13.9867 | 9.6622 | 17.9867 | 29.9733 | 43.96 | 7.3244 | 9.6722 | 9.3244 | 8.3244 | 11.9867 | 13.9867 | 9.6722 | 17.9967 | 29.9833 | 43.97 | 0.01
3.4391 | 7.7195 | 5.4391 | 4.4391 | 6.1586 | 8.1586 | 7.7195 | 12.1586 | 18.3173 | 26.4759 | 3.4391 | 7.7295 | 5.4391 | 4.4391 | 6.1586 | 8.1586 | 7.7295 | 12.1686 | 18.3273 | 26.4859 | 0.01
3.4033 | 7.7016 | 5.4033 | 4.4033 | 6.1049 | 8.1049 | 7.7016 | 12.1049 | 18.2098 | 26.3146 | 3.4033 | 7.7116 | 5.4033 | 4.4033 | 6.1049 | 8.1049 | 7.7116 | 12.1149 | 18.2198 | 26.3246 | 0.01
6.3856 | 9.1928 | 8.3856 | 7.3856 | 10.5783 | 12.5783 | 9.1928 | 16.5783 | 27.1567 | 39.735 | 6.3856 | 9.2028 | 8.3856 | 7.3856 | 10.5783 | 12.5783 | 9.2028 | 16.5883 | 27.1667 | 39.745 | 0.01
4.8622 | 8.4311 | 6.8622 | 5.8622 | 8.2933 | 10.2933 | 8.4311 | 14.2933 | 22.5865 | 32.8798 | 4.8622 | 8.4411 | 6.8622 | 5.8622 | 8.2933 | 10.2933 | 8.4411 | 14.3033 | 22.5965 | 32.8898 | 0.01
6.2649 | 9.1325 | 8.2649 | 7.2649 | 10.3974 | 12.3974 | 9.1325 | 16.3974 | 26.7948 | 39.1921 | 6.2649 | 9.1425 | 8.2649 | 7.2649 | 10.3974 | 12.3974 | 9.1425 | 16.4074 | 26.8048 | 39.2021 | 0.01
6.3815 | 9.1908 | 8.3815 | 7.3815 | 10.5723 | 12.5723 | 9.1908 | 16.5723 | 27.1445 | 39.7168 | 6.3815 | 9.2008 | 8.3815 | 7.3815 | 10.5723 | 12.5723 | 9.2008 | 16.5823 | 27.1545 | 39.7268 | 0.01
6.0503 | 9.0251 | 8.0503 | 7.0503 | 10.0754 | 12.0754 | 9.0251 | 16.0754 | 26.1508 | 38.2262 | 6.0503 | 9.0351 | 8.0503 | 7.0503 | 10.0754 | 12.0754 | 9.0351 | 16.0854 | 26.1608 | 38.2362 | 0.01
7.3199 | 9.6599 | 9.3199 | 8.3199 | 11.9798 | 13.9798 | 9.6599 | 17.9798 | 29.9596 | 43.9394 | 7.3199 | 9.6699 | 9.3199 | 8.3199 | 11.9798 | 13.9798 | 9.6699 | 17.9898 | 29.9696 | 43.9494 | 0.01
4.8278 | 8.4139 | 6.8278 | 5.8278 | 8.2417 | 10.2417 | 8.4139 | 14.2417 | 22.4835 | 32.7252 | 4.8278 | 8.4239 | 6.8278 | 5.8278 | 8.2417 | 10.2417 | 8.4239 | 14.2517 | 22.4935 | 32.7352 | 0.01
5.4652 | 8.7326 | 7.4652 | 6.4652 | 9.1977 | 11.1977 | 8.7326 | 15.1977 | 24.3955 | 35.5932 | 5.4652 | 8.7426 | 7.4652 | 6.4652 | 9.1977 | 11.1977 | 8.7426 | 15.2077 | 24.4055 | 35.6032 | 0.01
3.3593 | 7.6796 | 5.3593 | 4.3593 | 6.0389 | 8.0389 | 7.6796 | 12.0389 | 18.0778 | 26.1167 | 3.3593 | 7.6896 | 5.3593 | 4.3593 | 6.0389 | 8.0389 | 7.6896 | 12.0489 | 18.0878 | 26.1267 | 0.01
7.5124 | 9.7562 | 9.5124 | 8.5124 | 12.2686 | 14.2686 | 9.7562 | 18.2686 | 30.5371 | 44.8057 | 7.5124 | 9.7662 | 9.5124 | 8.5124 | 12.2686 | 14.2686 | 9.7662 | 18.2786 | 30.5471 | 44.8157 | 0.01
3.9132 | 7.9566 | 5.9132 | 4.9132 | 6.8698 | 8.8698 | 7.9566 | 12.8698 | 19.7396 | 28.6094 | 3.9132 | 7.9666 | 5.9132 | 4.9132 | 6.8698 | 8.8698 | 7.9666 | 12.8798 | 19.7496 | 28.6194 | 0.01
1.5199 | 6.7599 | 3.5199 | 2.5199 | 3.2798 | 5.2798 | 6.7599 | 9.2798 | 12.5596 | 17.8394 | 1.5199 | 6.7699 | 3.5199 | 2.5199 | 3.2798 | 5.2798 | 6.7699 | 9.2898 | 12.5696 | 17.8494 | 0.01
4.6499 | 8.325 | 6.6499 | 5.6499 | 7.9749 | 9.9749 | 8.325 | 13.9749 | 21.9497 | 31.9246 | 4.6499 | 8.335 | 6.6499 | 5.6499 | 7.9749 | 9.9749 | 8.335 | 13.9849 | 21.9597 | 31.9346 | 0.01
4.3616 | 8.1808 | 6.3616 | 5.3616 | 7.5424 | 9.5424 | 8.1808 | 13.5424 | 21.0848 | 30.6272 | 4.3616 | 8.1908 | 6.3616 | 5.3616 | 7.5424 | 9.5424 | 8.1908 | 13.5524 | 21.0948 | 30.6372 | 0.01
5.2767 | 8.6383 | 7.2767 | 6.2767 | 8.915 | 10.915 | 8.6383 | 14.915 | 23.8301 | 34.7451 | 5.2767 | 8.6483 | 7.2767 | 6.2767 | 8.915 | 10.915 | 8.6483 | 14.925 | 23.8401 | 34.7551 | 0.01
4.6809 | 8.3404 | 6.6809 | 5.6809 | 8.0213 | 10.0213 | 8.3404 | 14.0213 | 22.0426 | 32.064 | 4.6809 | 8.3504 | 6.6809 | 5.6809 | 8.0213 | 10.0213 | 8.3504 | 14.0313 | 22.0526 | 32.074 | 0.01
7.3392 | 9.6696 | 9.3392 | 8.3392 | 12.0087 | 14.0087 | 9.6696 | 18.0087 | 30.0175 | 44.0262 | 7.3392 | 9.6796 | 9.3392 | 8.3392 | 12.0087 | 14.0087 | 9.6796 | 18.0187 | 30.0275 | 44.0362 | 0.01
5.9878 | 8.9939 | 7.9878 | 6.9878 | 9.9818 | 11.9818 | 8.9939 | 15.9818 | 25.9635 | 37.9453 | 5.9878 | 9.0039 | 7.9878 | 6.9878 | 9.9818 | 11.9818 | 9.0039 | 15.9918 | 25.9735 | 37.9553 | 0.01
7.2575 | 9.6288 | 9.2575 | 8.2575 | 11.8863 | 13.8863 | 9.6288 | 17.8863 | 29.7726 | 43.659 | 7.2575 | 9.6388 | 9.2575 | 8.2575 | 11.8863 | 13.8863 | 9.6388 | 17.8963 | 29.7826 | 43.669 | 0.01
6.2064 | 9.1032 | 8.2064 | 7.2064 | 10.3096 | 12.3096 | 9.1032 | 16.3096 | 26.6191 | 38.9287 | 6.2064 | 9.1132 | 8.2064 | 7.2064 | 10.3096 | 12.3096 | 9.1132 | 16.3196 | 26.6291 | 38.9387 | 0.01
3.8799 | 7.94 | 5.8799 | 4.8799 | 6.8199 | 8.8199 | 7.94 | 12.8199 | 19.6398 | 28.4598 | 3.8799 | 7.95 | 5.8799 | 4.8799 | 6.8199 | 8.8199 | 7.95 | 12.8299 | 19.6498 | 28.4698 | 0.01
2.4504 | 7.2252 | 4.4504 | 3.4504 | 4.6756 | 6.6756 | 7.2252 | 10.6756 | 15.3512 | 22.0267 | 2.4504 | 7.2352 | 4.4504 | 3.4504 | 4.6756 | 6.6756 | 7.2352 | 10.6856 | 15.3612 | 22.0367 | 0.01
5.7233 | 8.8617 | 7.7233 | 6.7233 | 9.585 | 11.585 | 8.8617 | 15.585 | 25.17 | 36.755 | 5.7233 | 8.8717 | 7.7233 | 6.7233 | 9.585 | 11.585 | 8.8717 | 15.595 | 25.18 | 36.765 | 0.01
8.2167 | 10.1084 | 10.2167 | 9.2167 | 13.3251 | 15.3251 | 10.1084 | 19.3251 | 32.6501 | 47.9752 | 8.2167 | 10.1184 | 10.2167 | 9.2167 | 13.3251 | 15.3251 | 10.1184 | 19.3351 | 32.6601 | 47.9852 | 0.01
5.8225 | 8.9113 | 7.8225 | 6.8225 | 9.7338 | 11.7338 | 8.9113 | 15.7338 | 25.4676 | 37.2013 | 5.8225 | 8.9213 | 7.8225 | 6.8225 | 9.7338 | 11.7338 | 8.9213 | 15.7438 | 25.4776 | 37.2113 | 0.01
4.44 | 8.22 | 6.44 | 5.44 | 7.6599 | 9.6599 | 8.22 | 13.6599 | 21.3199 | 30.9798 | 4.44 | 8.23 | 6.44 | 5.44 | 7.6599 | 9.6599 | 8.23 | 13.6699 | 21.3299 | 30.9898 | 0.01
5.5445 | 8.7723 | 7.5445 | 6.5445 | 9.3168 | 11.3168 | 8.7723 | 15.3168 | 24.6336 | 35.9503 | 5.5445 | 8.7823 | 7.5445 | 6.5445 | 9.3168 | 11.3168 | 8.7823 | 15.3268 | 24.6436 | 35.9603 | 0.01
6.9782 | 9.4891 | 8.9782 | 7.9782 | 11.4673 | 13.4673 | 9.4891 | 17.4673 | 28.9346 | 42.4018 | 6.9782 | 9.4991 | 8.9782 | 7.9782 | 11.4673 | 13.4673 | 9.4991 | 17.4773 | 28.9446 | 42.4118 | 0.01
4.06 | 8.03 | 6.06 | 5.06 | 7.09 | 9.09 | 8.03 | 13.09 | 20.1799 | 29.2699 | 4.06 | 8.04 | 6.06 | 5.06 | 7.09 | 9.09 | 8.04 | 13.1 | 20.1899 | 29.2799 | 0.01
6.8952 | 9.4476 | 8.8952 | 7.8952 | 11.3428 | 13.3428 | 9.4476 | 17.3428 | 28.6856 | 42.0284 | 6.8952 | 9.4576 | 8.8952 | 7.8952 | 11.3428 | 13.3428 | 9.4576 | 17.3528 | 28.6956 | 42.0384 | 0.01
4.2954 | 8.1477 | 6.2954 | 5.2954 | 7.4431 | 9.4431 | 8.1477 | 13.4431 | 20.8863 | 30.3294 | 4.2954 | 8.1577 | 6.2954 | 5.2954 | 7.4431 | 9.4431 | 8.1577 | 13.4531 | 20.8963 | 30.3394 | 0.01
5.384 | 8.692 | 7.384 | 6.384 | 9.076 | 11.076 | 8.692 | 15.076 | 24.152 | 35.228 | 5.384 | 8.702 | 7.384 | 6.384 | 9.076 | 11.076 | 8.702 | 15.086 | 24.162 | 35.238 | 0.01
5.5138 | 8.7569 | 7.5138 | 6.5138 | 9.2708 | 11.2708 | 8.7569 | 15.2708 | 24.5415 | 35.8123 | 5.5138 | 8.7669 | 7.5138 | 6.5138 | 9.2708 | 11.2708 | 8.7669 | 15.2808 | 24.5515 | 35.8223 | 0.01
6.558 | 9.279 | 8.558 | 7.558 | 10.837 | 12.837 | 9.279 | 16.837 | 27.6741 | 40.5111 | 6.558 | 9.289 | 8.558 | 7.558 | 10.837 | 12.837 | 9.289 | 16.847 | 27.6841 | 40.5211 | 0.01
6.8751 | 9.4376 | 8.8751 | 7.8751 | 11.3127 | 13.3127 | 9.4376 | 17.3127 | 28.6254 | 41.9381 | 6.8751 | 9.4476 | 8.8751 | 7.8751 | 11.3127 | 13.3127 | 9.4476 | 17.3227 | 28.6354 | 41.9481 | 0.01
5.5105 | 8.7553 | 7.5105 | 6.5105 | 9.2658 | 11.2658 | 8.7553 | 15.2658 | 24.5316 | 35.7974 | 5.5105 | 8.7653 | 7.5105 | 6.5105 | 9.2658 | 11.2658 | 8.7653 | 15.2758 | 24.5416 | 35.8074 | 0.01
3.8041 | 7.902 | 5.8041 | 4.8041 | 6.7061 | 8.7061 | 7.902 | 12.7061 | 19.4123 | 28.1184 | 3.8041 | 7.912 | 5.8041 | 4.8041 | 6.7061 | 8.7061 | 7.912 | 12.7161 | 19.4223 | 28.1284 | 0.01
6.5984 | 9.2992 | 8.5984 | 7.5984 | 10.8976 | 12.8976 | 9.2992 | 16.8976 | 27.7952 | 40.6927 | 6.5984 | 9.3092 | 8.5984 | 7.5984 | 10.8976 | 12.8976 | 9.3092 | 16.9076 | 27.8052 | 40.7027 | 0.01
4.1412 | 8.0706 | 6.1412 | 5.1412 | 7.2117 | 9.2117 | 8.0706 | 13.2117 | 20.4235 | 29.6352 | 4.1412 | 8.0806 | 6.1412 | 5.1412 | 7.2117 | 9.2117 | 8.0806 | 13.2217 | 20.4335 | 29.6452 | 0.01
8.1884 | 10.0942 | 10.1884 | 9.1884 | 13.2826 | 15.2826 | 10.0942 | 19.2826 | 32.5651 | 47.8477 | 8.1884 | 10.1042 | 10.1884 | 9.1884 | 13.2826 | 15.2826 | 10.1042 | 19.2926 | 32.5751 | 47.8577 | 0.01
3.3929 | 7.6965 | 5.3929 | 4.3929 | 6.0894 | 8.0894 | 7.6965 | 12.0894 | 18.1787 | 26.2681 | 3.3929 | 7.7065 | 5.3929 | 4.3929 | 6.0894 | 8.0894 | 7.7065 | 12.0994 | 18.1887 | 26.2781 | 0.01
8.253 | 10.1265 | 10.253 | 9.253 | 13.3795 | 15.3795 | 10.1265 | 19.3795 | 32.759 | 48.1384 | 8.253 | 10.1365 | 10.253 | 9.253 | 13.3795 | 15.3795 | 10.1365 | 19.3895 | 32.769 | 48.1484 | 0.01
6.3518 | 9.1759 | 8.3518 | 7.3518 | 10.5277 | 12.5277 | 9.1759 | 16.5277 | 27.0554 | 39.583 | 6.3518 | 9.1859 | 8.3518 | 7.3518 | 10.5277 | 12.5277 | 9.1859 | 16.5377 | 27.0654 | 39.593 | 0.01
6.4248 | 9.2124 | 8.4248 | 7.4248 | 10.6371 | 12.6371 | 9.2124 | 16.6371 | 27.2743 | 39.9114 | 6.4248 | 9.2224 | 8.4248 | 7.4248 | 10.6371 | 12.6371 | 9.2224 | 16.6471 | 27.2843 | 39.9214 | 0.01
4.0788 | 8.0394 | 6.0788 | 5.0788 | 7.1181 | 9.1181 | 8.0394 | 13.1181 | 20.2363 | 29.3544 | 4.0788 | 8.0494 | 6.0788 | 5.0788 | 7.1181 | 9.1181 | 8.0494 | 13.1281 | 20.2463 | 29.3644 | 0.01
3.7415 | 7.8708 | 5.7415 | 4.7415 | 6.6123 | 8.6123 | 7.8708 | 12.6123 | 19.2246 | 27.8368 | 3.7415 | 7.8808 | 5.7415 | 4.7415 | 6.6123 | 8.6123 | 7.8808 | 12.6223 | 19.2346 | 27.8468 | 0.01
7.8238 | 9.9119 | 9.8238 | 8.8238 | 12.7357 | 14.7357 | 9.9119 | 18.7357 | 31.4713 | 46.207 | 7.8238 | 9.9219 | 9.8238 | 8.8238 | 12.7357 | 14.7357 | 9.9219 | 18.7457 | 31.4813 | 46.217 | 0.01
5.4348 | 8.7174 | 7.4348 | 6.4348 | 9.1522 | 11.1522 | 8.7174 | 15.1522 | 24.3044 | 35.4567 | 5.4348 | 8.7274 | 7.4348 | 6.4348 | 9.1522 | 11.1522 | 8.7274 | 15.1622 | 24.3144 | 35.4667 | 0.01
4.2646 | 8.1323 | 6.2646 | 5.2646 | 7.397 | 9.397 | 8.1323 | 13.397 | 20.7939 | 30.1909 | 4.2646 | 8.1423 | 6.2646 | 5.2646 | 7.397 | 9.397 | 8.1423 | 13.407 | 20.8039 | 30.2009 | 0.01
5.7679 | 8.884 | 7.7679 | 6.7679 | 9.6519 | 11.6519 | 8.884 | 15.6519 | 25.3038 | 36.9556 | 5.7679 | 8.894 | 7.7679 | 6.7679 | 9.6519 | 11.6519 | 8.894 | 15.6619 | 25.3138 | 36.9656 | 0.01
6.0709 | 9.0355 | 8.0709 | 7.0709 | 10.1064 | 12.1064 | 9.0355 | 16.1064 | 26.2128 | 38.3192 | 6.0709 | 9.0455 | 8.0709 | 7.0709 | 10.1064 | 12.1064 | 9.0455 | 16.1164 | 26.2228 | 38.3292 | 0.01
7.1335 | 9.5668 | 9.1335 | 8.1335 | 11.7003 | 13.7003 | 9.5668 | 17.7003 | 29.4005 | 43.1008 | 7.1335 | 9.5768 | 9.1335 | 8.1335 | 11.7003 | 13.7003 | 9.5768 | 17.7103 | 29.4105 | 43.1108 | 0.01
7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 7.2523 | 9.6362 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6362 | 17.8885 | 29.767 | 43.6455 | 0.01
1.7153 | 6.8577 | 3.7153 | 2.7153 | 3.573 | 5.573 | 6.8577 | 9.573 | 13.146 | 18.719 | 1.7153 | 6.8677 | 3.7153 | 2.7153 | 3.573 | 5.573 | 6.8677 | 9.583 | 13.156 | 18.729 | 0.01
2.3377 | 7.1689 | 4.3377 | 3.3377 | 4.5066 | 6.5066 | 7.1689 | 10.5066 | 15.0132 | 21.5197 | 2.3377 | 7.1789 | 4.3377 | 3.3377 | 4.5066 | 6.5066 | 7.1789 | 10.5166 | 15.0232 | 21.5297 | 0.01
4.5542 | 8.2771 | 6.5542 | 5.5542 | 7.8313 | 9.8313 | 8.2771 | 13.8313 | 21.6626 | 31.4939 | 4.5542 | 8.2871 | 6.5542 | 5.5542 | 7.8313 | 9.8313 | 8.2871 | 13.8413 | 21.6726 | 31.5039 | 0.01
8.0371 | 10.0185 | 10.0371 | 9.0371 | 13.0556 | 15.0556 | 10.0185 | 19.0556 | 32.1113 | 47.1669 | 8.0371 | 10.0285 | 10.0371 | 9.0371 | 13.0556 | 15.0556 | 10.0285 | 19.0656 | 32.1213 | 47.1769 | 0.01
9.1147 | 10.5573 | 11.1147 | 10.1147 | 14.672 | 16.672 | 10.5573 | 20.672 | 35.3441 | 52.0161 | 9.1147 | 10.5673 | 11.1147 | 10.1147 | 14.672 | 16.672 | 10.5673 | 20.682 | 35.3541 | 52.0261 | 0.01
6.8241 | 9.412 | 8.8241 | 7.8241 | 11.2361 | 13.2361 | 9.412 | 17.2361 | 28.4722 | 41.7083 | 6.8241 | 9.422 | 8.8241 | 7.8241 | 11.2361 | 13.2361 | 9.422 | 17.2461 | 28.4822 | 41.7183 | 0.01
6.7062 | 9.3531 | 8.7062 | 7.7062 | 11.0593 | 13.0593 | 9.3531 | 17.0593 | 28.1185 | 41.1778 | 6.7062 | 9.3631 | 8.7062 | 7.7062 | 11.0593 | 13.0593 | 9.3631 | 17.0693 | 28.1285 | 41.1878 | 0.01
5.2576 | 8.6288 | 7.2576 | 6.2576 | 8.8863 | 10.8863 | 8.6288 | 14.8863 | 23.7727 | 34.659 | 5.2576 | 8.6388 | 7.2576 | 6.2576 | 8.8863 | 10.8863 | 8.6388 | 14.8963 | 23.7827 | 34.669 | 0.01
6.3132 | 9.1566 | 8.3132 | 7.3132 | 10.4697 | 12.4697 | 9.1566 | 16.4697 | 26.9395 | 39.4092 | 6.3132 | 9.1666 | 8.3132 | 7.3132 | 10.4697 | 12.4697 | 9.1666 | 16.4797 | 26.9495 | 39.4192 | 0.01
5.6124 | 8.8062 | 7.6124 | 6.6124 | 9.4186 | 11.4186 | 8.8062 | 15.4186 | 24.8373 | 36.2559 | 5.6124 | 8.8162 | 7.6124 | 6.6124 | 9.4186 | 11.4186 | 8.8162 | 15.4286 | 24.8473 | 36.2659 | 0.01
4.4577 | 8.2289 | 6.4577 | 5.4577 | 7.6866 | 9.6866 | 8.2289 | 13.6866 | 21.3732 | 31.0598 | 4.4577 | 8.2389 | 6.4577 | 5.4577 | 7.6866 | 9.6866 | 8.2389 | 13.6966 | 21.3832 | 31.0698 | 0.01
7.1172 | 9.5586 | 9.1172 | 8.1172 | 11.6758 | 13.6758 | 9.5586 | 17.6758 | 29.3516 | 43.0274 | 7.1172 | 9.5686 | 9.1172 | 8.1172 | 11.6758 | 13.6758 | 9.5686 | 17.6858 | 29.3616 | 43.0374 | 0.01
1.8832 | 6.9416 | 3.8832 | 2.8832 | 3.8248 | 5.8248 | 6.9416 | 9.8248 | 13.6496 | 19.4744 | 1.8832 | 6.9516 | 3.8832 | 2.8832 | 3.8248 | 5.8248 | 6.9516 | 9.8348 | 13.6596 | 19.4844 | 0.01
9.3963 | 10.6981 | 11.3963 | 10.3963 | 15.0944 | 17.0944 | 10.6981 | 21.0944 | 36.1889 | 53.2833 | 9.3963 | 10.7081 | 11.3963 | 10.3963 | 15.0944 | 17.0944 | 10.7081 | 21.1044 | 36.1989 | 53.2933 | 0.01
5.7522 | 8.8761 | 7.7522 | 6.7522 | 9.6283 | 11.6283 | 8.8761 | 15.6283 | 25.2566 | 36.8849 | 5.7522 | 8.8861 | 7.7522 | 6.7522 | 9.6283 | 11.6283 | 8.8861 | 15.6383 | 25.2666 | 36.8949 | 0.01
8.7802 | 10.3901 | 10.7802 | 9.7802 | 14.1703 | 16.1703 | 10.3901 | 20.1703 | 34.3407 | 50.511 | 8.7802 | 10.4001 | 10.7802 | 9.7802 | 14.1703 | 16.1703 | 10.4001 | 20.1803 | 34.3507 | 50.521 | 0.01
6.4029 | 9.2014 | 8.4029 | 7.4029 | 10.6043 | 12.6043 | 9.2014 | 16.6043 | 27.2086 | 39.8129 | 6.4029 | 9.2114 | 8.4029 | 7.4029 | 10.6043 | 12.6043 | 9.2114 | 16.6143 | 27.2186 | 39.8229 | 0.01
3.783 | 7.8915 | 5.783 | 4.783 | 6.6745 | 8.6745 | 7.8915 | 12.6745 | 19.349 | 28.0235 | 3.783 | 7.9015 | 5.783 | 4.783 | 6.6745 | 8.6745 | 7.9015 | 12.6845 | 19.359 | 28.0335 | 0.01
4.0209 | 8.0105 | 6.0209 | 5.0209 | 7.0314 | 9.0314 | 8.0105 | 13.0314 | 20.0627 | 29.0941 | 4.0209 | 8.0205 | 6.0209 | 5.0209 | 7.0314 | 9.0314 | 8.0205 | 13.0414 | 20.0727 | 29.1041 | 0.01
6.4079 | 9.2039 | 8.4079 | 7.4079 | 10.6118 | 12.6118 | 9.2039 | 16.6118 | 27.2236 | 39.8354 | 6.4079 | 9.2139 | 8.4079 | 7.4079 | 10.6118 | 12.6118 | 9.2139 | 16.6218 | 27.2336 | 39.8454 | 0.01
6.5453 | 9.2727 | 8.5453 | 7.5453 | 10.818 | 12.818 | 9.2727 | 16.818 | 27.6359 | 40.4539 | 6.5453 | 9.2827 | 8.5453 | 7.5453 | 10.818 | 12.818 | 9.2827 | 16.828 | 27.6459 | 40.4639 | 0.01
7.6805 | 9.8402 | 9.6805 | 8.6805 | 12.5207 | 14.5207 | 9.8402 | 18.5207 | 31.0415 | 45.5622 | 7.6805 | 9.8502 | 9.6805 | 8.6805 | 12.5207 | 14.5207 | 9.8502 | 18.5307 | 31.0515 | 45.5722 | 0.01
6.1081 | 9.0541 | 8.1081 | 7.1081 | 10.1622 | 12.1622 | 9.0541 | 16.1622 | 26.3244 | 38.4866 | 6.1081 | 9.0641 | 8.1081 | 7.1081 | 10.1622 | 12.1622 | 9.0641 | 16.1722 | 26.3344 | 38.4966 | 0.01
6.5904 | 9.2952 | 8.5904 | 7.5904 | 10.8856 | 12.8856 | 9.2952 | 16.8856 | 27.7712 | 40.6568 | 6.5904 | 9.3052 | 8.5904 | 7.5904 | 10.8856 | 12.8856 | 9.3052 | 16.8956 | 27.7812 | 40.6668 | 0.01
6.4252 | 9.2126 | 8.4252 | 7.4252 | 10.6378 | 12.6378 | 9.2126 | 16.6378 | 27.2757 | 39.9135 | 6.4252 | 9.2226 | 8.4252 | 7.4252 | 10.6378 | 12.6378 | 9.2226 | 16.6478 | 27.2857 | 39.9235 | 0.01
5.1021 | 8.551 | 7.1021 | 6.1021 | 8.6531 | 10.6531 | 8.551 | 14.6531 | 23.3063 | 33.9594 | 5.1021 | 8.561 | 7.1021 | 6.1021 | 8.6531 | 10.6531 | 8.561 | 14.6631 | 23.3163 | 33.9694 | 0.01
5.7627 | 8.8813 | 7.7627 | 6.7627 | 9.644 | 11.644 | 8.8813 | 15.644 | 25.288 | 36.9321 | 5.7627 | 8.8913 | 7.7627 | 6.7627 | 9.644 | 11.644 | 8.8913 | 15.654 | 25.298 | 36.9421 | 0.01
6.6646 | 9.3323 | 8.6646 | 7.6646 | 10.997 | 12.997 | 9.3323 | 16.997 | 27.9939 | 40.9909 | 6.6646 | 9.3423 | 8.6646 | 7.6646 | 10.997 | 12.997 | 9.3423 | 17.007 | 28.0039 | 41.0009 | 0.01
3.2081 | 7.604 | 5.2081 | 4.2081 | 5.8121 | 7.8121 | 7.604 | 11.8121 | 17.6242 | 25.4363 | 3.2081 | 7.614 | 5.2081 | 4.2081 | 5.8121 | 7.8121 | 7.614 | 11.8221 | 17.6342 | 25.4463 | 0.01
5.1092 | 8.5546 | 7.1092 | 6.1092 | 8.6638 | 10.6638 | 8.5546 | 14.6638 | 23.3276 | 33.9913 | 5.1092 | 8.5646 | 7.1092 | 6.1092 | 8.6638 | 10.6638 | 8.5646 | 14.6738 | 23.3376 | 34.0013 | 0.01
6.6987 | 9.3493 | 8.6987 | 7.6987 | 11.048 | 13.048 | 9.3493 | 17.048 | 28.0961 | 41.1441 | 6.6987 | 9.3593 | 8.6987 | 7.6987 | 11.048 | 13.048 | 9.3593 | 17.058 | 28.1061 | 41.1541 | 0.01
6.0901 | 9.045 | 8.0901 | 7.0901 | 10.1351 | 12.1351 | 9.045 | 16.1351 | 26.2702 | 38.4053 | 6.0901 | 9.055 | 8.0901 | 7.0901 | 10.1351 | 12.1351 | 9.055 | 16.1451 | 26.2802 | 38.4153 | 0.01
3.3738 | 7.6869 | 5.3738 | 4.3738 | 6.0607 | 8.0607 | 7.6869 | 12.0607 | 18.1215 | 26.1822 | 3.3738 | 7.6969 | 5.3738 | 4.3738 | 6.0607 | 8.0607 | 7.6969 | 12.0707 | 18.1315 | 26.1922 | 0.01
4.8105 | 8.4053 | 6.8105 | 5.8105 | 8.2158 | 10.2158 | 8.4053 | 14.2158 | 22.4316 | 32.6474 | 4.8105 | 8.4153 | 6.8105 | 5.8105 | 8.2158 | 10.2158 | 8.4153 | 14.2258 | 22.4416 | 32.6574 | 0.01
7.522 | 9.761 | 9.522 | 8.522 | 12.2829 | 14.2829 | 9.761 | 18.2829 | 30.5659 | 44.8488 | 7.522 | 9.771 | 9.522 | 8.522 | 12.2829 | 14.2829 | 9.771 | 18.2929 | 30.5759 | 44.8588 | 0.01
4.9713 | 8.4857 | 6.9713 | 5.9713 | 8.457 | 10.457 | 8.4857 | 14.457 | 22.9139 | 33.3709 | 4.9713 | 8.4957 | 6.9713 | 5.9713 | 8.457 | 10.457 | 8.4957 | 14.467 | 22.9239 | 33.3809 | 0.01
6.749 | 9.3745 | 8.749 | 7.749 | 11.1235 | 13.1235 | 9.3745 | 17.1235 | 28.247 | 41.3705 | 6.749 | 9.3845 | 8.749 | 7.749 | 11.1235 | 13.1235 | 9.3845 | 17.1335 | 28.257 | 41.3805 | 0.01
5.0742 | 8.5371 | 7.0742 | 6.0742 | 8.6114 | 10.6114 | 8.5371 | 14.6114 | 23.2227 | 33.8341 | 5.0742 | 8.5471 | 7.0742 | 6.0742 | 8.6114 | 10.6114 | 8.5471 | 14.6214 | 23.2327 | 33.8441 | 0.01
4.7646 | 8.3823 | 6.7646 | 5.7646 | 8.1468 | 10.1468 | 8.3823 | 14.1468 | 22.2937 | 32.4405 | 4.7646 | 8.3923 | 6.7646 | 5.7646 | 8.1468 | 10.1468 | 8.3923 | 14.1568 | 22.3037 | 32.4505 | 0.01
7.389 | 9.6945 | 9.389 | 8.389 | 12.0834 | 14.0834 | 9.6945 | 18.0834 | 30.1669 | 44.2503 | 7.389 | 9.7045 | 9.389 | 8.389 | 12.0834 | 14.0834 | 9.7045 | 18.0934 | 30.1769 | 44.2603 | 0.01
2.893 | 7.4465 | 4.893 | 3.893 | 5.3395 | 7.3395 | 7.4465 | 11.3395 | 16.679 | 24.0185 | 2.893 | 7.4565 | 4.893 | 3.893 | 5.3395 | 7.3395 | 7.4565 | 11.3495 | 16.689 | 24.0285 | 0.01
3.3349 | 7.6675 | 5.3349 | 4.3349 | 6.0024 | 8.0024 | 7.6675 | 12.0024 | 18.0048 | 26.0072 | 3.3349 | 7.6775 | 5.3349 | 4.3349 | 6.0024 | 8.0024 | 7.6775 | 12.0124 | 18.0148 | 26.0172 | 0.01
8.9925 | 10.4963 | 10.9925 | 9.9925 | 14.4888 | 16.4888 | 10.4963 | 20.4888 | 34.9775 | 51.4663 | 8.9925 | 10.5063 | 10.9925 | 9.9925 | 14.4888 | 16.4888 | 10.5063 | 20.4988 | 34.9875 | 51.4763 | 0.01
7.789 | 9.8945 | 9.789 | 8.789 | 12.6836 | 14.6836 | 9.8945 | 18.6836 | 31.3671 | 46.0507 | 7.789 | 9.9045 | 9.789 | 8.789 | 12.6836 | 14.6836 | 9.9045 | 18.6936 | 31.3771 | 46.0607 | 0.01
7.8333 | 9.9167 | 9.8333 | 8.8333 | 12.75 | 14.75 | 9.9167 | 18.75 | 31.4999 | 46.2499 | 7.8333 | 9.9267 | 9.8333 | 8.8333 | 12.75 | 14.75 | 9.9267 | 18.76 | 31.5099 | 46.2599 | 0.01
7.307 | 9.6535 | 9.307 | 8.307 | 11.9605 | 13.9605 | 9.6535 | 17.9605 | 29.9209 | 43.8814 | 7.307 | 9.6635 | 9.307 | 8.307 | 11.9605 | 13.9605 | 9.6635 | 17.9705 | 29.9309 | 43.8914 | 0.01
9.787 | 10.8935 | 11.787 | 10.787 | 15.6805 | 17.6805 | 10.8935 | 21.6805 | 37.361 | 55.0415 | 9.787 | 10.9035 | 11.787 | 10.787 | 15.6805 | 17.6805 | 10.9035 | 21.6905 | 37.371 | 55.0515 | 0.01
5.2045 | 8.6023 | 7.2045 | 6.2045 | 8.8068 | 10.8068 | 8.6023 | 14.8068 | 23.6135 | 34.4203 | 5.2045 | 8.6123 | 7.2045 | 6.2045 | 8.8068 | 10.8068 | 8.6123 | 14.8168 | 23.6235 | 34.4303 | 0.01
5.5481 | 8.7741 | 7.5481 | 6.5481 | 9.3222 | 11.3222 | 8.7741 | 15.3222 | 24.6444 | 35.9666 | 5.5481 | 8.7841 | 7.5481 | 6.5481 | 9.3222 | 11.3222 | 8.7841 | 15.3322 | 24.6544 | 35.9766 | 0.01
2.9819 | 7.491 | 4.9819 | 3.9819 | 5.4729 | 7.4729 | 7.491 | 11.4729 | 16.9458 | 24.4187 | 2.9819 | 7.501 | 4.9819 | 3.9819 | 5.4729 | 7.4729 | 7.501 | 11.4829 | 16.9558 | 24.4287 | 0.01
7.6554 | 9.8277 | 9.6554 | 8.6554 | 12.4831 | 14.4831 | 9.8277 | 18.4831 | 30.9661 | 45.4492 | 7.6554 | 9.8377 | 9.6554 | 8.6554 | 12.4831 | 14.4831 | 9.8377 | 18.4931 | 30.9761 | 45.4592 | 0.01
4.8098 | 8.4049 | 6.8098 | 5.8098 | 8.2147 | 10.2147 | 8.4049 | 14.2147 | 22.4294 | 32.6441 | 4.8098 | 8.4149 | 6.8098 | 5.8098 | 8.2147 | 10.2147 | 8.4149 | 14.2247 | 22.4394 | 32.6541 | 0.01
2.7341 | 7.3671 | 4.7341 | 3.7341 | 5.1012 | 7.1012 | 7.3671 | 11.1012 | 16.2023 | 23.3035 | 2.7341 | 7.3771 | 4.7341 | 3.7341 | 5.1012 | 7.1012 | 7.3771 | 11.1112 | 16.2123 | 23.3135 | 0.01
8.5249 | 10.2624 | 10.5249 | 9.5249 | 13.7873 | 15.7873 | 10.2624 | 19.7873 | 33.5746 | 49.3619 | 8.5249 | 10.2724 | 10.5249 | 9.5249 | 13.7873 | 15.7873 | 10.2724 | 19.7973 | 33.5846 | 49.3719 | 0.01
8.5457 | 10.2729 | 10.5457 | 9.5457 | 13.8186 | 15.8186 | 10.2729 | 19.8186 | 33.6371 | 49.4557 | 8.5457 | 10.2829 | 10.5457 | 9.5457 | 13.8186 | 15.8186 | 10.2829 | 19.8286 | 33.6471 | 49.4657 | 0.01
6.6239 | 9.3119 | 8.6239 | 7.6239 | 10.9358 | 12.9358 | 9.3119 | 16.9358 | 27.8716 | 40.8074 | 6.6239 | 9.3219 | 8.6239 | 7.6239 | 10.9358 | 12.9358 | 9.3219 | 16.9458 | 27.8816 | 40.8174 | 0.01
7.2382 | 9.6191 | 9.2382 | 8.2382 | 11.8573 | 13.8573 | 9.6191 | 17.8573 | 29.7147 | 43.572 | 7.2382 | 9.6291 | 9.2382 | 8.2382 | 11.8573 | 13.8573 | 9.6291 | 17.8673 | 29.7247 | 43.582 | 0.01
6.7582 | 9.3791 | 8.7582 | 7.7582 | 11.1373 | 13.1373 | 9.3791 | 17.1373 | 28.2746 | 41.4119 | 6.7582 | 9.3891 | 8.7582 | 7.7582 | 11.1373 | 13.1373 | 9.3891 | 17.1473 | 28.2846 | 41.4219 | 0.01
5.4894 | 8.7447 | 7.4894 | 6.4894 | 9.2341 | 11.2341 | 8.7447 | 15.2341 | 24.4682 | 35.7022 | 5.4894 | 8.7547 | 7.4894 | 6.4894 | 9.2341 | 11.2341 | 8.7547 | 15.2441 | 24.4782 | 35.7122 | 0.01
5.7659 | 8.883 | 7.7659 | 6.7659 | 9.6489 | 11.6489 | 8.883 | 15.6489 | 25.2977 | 36.9466 | 5.7659 | 8.893 | 7.7659 | 6.7659 | 9.6489 | 11.6489 | 8.893 | 15.6589 | 25.3077 | 36.9566 | 0.01
5.7573 | 8.8786 | 7.7573 | 6.7573 | 9.6359 | 11.6359 | 8.8786 | 15.6359 | 25.2719 | 36.9078 | 5.7573 | 8.8886 | 7.7573 | 6.7573 | 9.6359 | 11.6359 | 8.8886 | 15.6459 | 25.2819 | 36.9178 | 0.01
4.4028 | 8.2014 | 6.4028 | 5.4028 | 7.6042 | 9.6042 | 8.2014 | 13.6042 | 21.2083 | 30.8125 | 4.4028 | 8.2114 | 6.4028 | 5.4028 | 7.6042 | 9.6042 | 8.2114 | 13.6142 | 21.2183 | 30.8225 | 0.01
5.7536 | 8.8768 | 7.7536 | 6.7536 | 9.6304 | 11.6304 | 8.8768 | 15.6304 | 25.2608 | 36.8911 | 5.7536 | 8.8868 | 7.7536 | 6.7536 | 9.6304 | 11.6304 | 8.8868 | 15.6404 | 25.2708 | 36.9011 | 0.01
5.0303 | 8.5151 | 7.0303 | 6.0303 | 8.5454 | 10.5454 | 8.5151 | 14.5454 | 23.0908 | 33.6361 | 5.0303 | 8.5251 | 7.0303 | 6.0303 | 8.5454 | 10.5454 | 8.5251 | 14.5554 | 23.1008 | 33.6461 | 0.01
3.0131 | 7.5066 | 5.0131 | 4.0131 | 5.5197 | 7.5197 | 7.5066 | 11.5197 | 17.0393 | 24.559 | 3.0131 | 7.5166 | 5.0131 | 4.0131 | 5.5197 | 7.5197 | 7.5166 | 11.5297 | 17.0493 | 24.569 | 0.01
2.4946 | 7.2473 | 4.4946 | 3.4946 | 4.7419 | 6.7419 | 7.2473 | 10.7419 | 15.4838 | 22.2257 | 2.4946 | 7.2573 | 4.4946 | 3.4946 | 4.7419 | 6.7419 | 7.2573 | 10.7519 | 15.4938 | 22.2357 | 0.01
3.8321 | 7.9161 | 5.8321 | 4.8321 | 6.7482 | 8.7482 | 7.9161 | 12.7482 | 19.4963 | 28.2445 | 3.8321 | 7.9261 | 5.8321 | 4.8321 | 6.7482 | 8.7482 | 7.9261 | 12.7582 | 19.5063 | 28.2545 | 0.01
3.881 | 7.9405 | 5.881 | 4.881 | 6.8215 | 8.8215 | 7.9405 | 12.8215 | 19.6431 | 28.4646 | 3.881 | 7.9505 | 5.881 | 4.881 | 6.8215 | 8.8215 | 7.9505 | 12.8315 | 19.6531 | 28.4746 | 0.01
6.8478 | 9.4239 | 8.8478 | 7.8478 | 11.2716 | 13.2716 | 9.4239 | 17.2716 | 28.5433 | 41.8149 | 6.8478 | 9.4339 | 8.8478 | 7.8478 | 11.2716 | 13.2716 | 9.4339 | 17.2816 | 28.5533 | 41.8249 | 0.01
6.8117 | 9.4059 | 8.8117 | 7.8117 | 11.2176 | 13.2176 | 9.4059 | 17.2176 | 28.4352 | 41.6529 | 6.8117 | 9.4159 | 8.8117 | 7.8117 | 11.2176 | 13.2176 | 9.4159 | 17.2276 | 28.4452 | 41.6629 | 0.01
2.5649 | 7.2825 | 4.5649 | 3.5649 | 4.8474 | 6.8474 | 7.2825 | 10.8474 | 15.6947 | 22.5421 | 2.5649 | 7.2925 | 4.5649 | 3.5649 | 4.8474 | 6.8474 | 7.2925 | 10.8574 | 15.7047 | 22.5521 | 0.01
4.502 | 8.251 | 6.502 | 5.502 | 7.7531 | 9.7531 | 8.251 | 13.7531 | 21.5061 | 31.2592 | 4.502 | 8.261 | 6.502 | 5.502 | 7.7531 | 9.7531 | 8.261 | 13.7631 | 21.5161 | 31.2692 | 0.01
8.0192 | 10.0096 | 10.0192 | 9.0192 | 13.0288 | 15.0288 | 10.0096 | 19.0288 | 32.0575 | 47.0863 | 8.0192 | 10.0196 | 10.0192 | 9.0192 | 13.0288 | 15.0288 | 10.0196 | 19.0388 | 32.0675 | 47.0963 | 0.01
5.5992 | 8.7996 | 7.5992 | 6.5992 | 9.3987 | 11.3987 | 8.7996 | 15.3987 | 24.7975 | 36.1962 | 5.5992 | 8.8096 | 7.5992 | 6.5992 | 9.3987 | 11.3987 | 8.8096 | 15.4087 | 24.8075 | 36.2062 | 0.01
3.538 | 7.769 | 5.538 | 4.538 | 6.3071 | 8.3071 | 7.769 | 12.3071 | 18.6141 | 26.9212 | 3.538 | 7.779 | 5.538 | 4.538 | 6.3071 | 8.3071 | 7.779 | 12.3171 | 18.6241 | 26.9312 | 0.01
4.1922 | 8.0961 | 6.1922 | 5.1922 | 7.2882 | 9.2882 | 8.0961 | 13.2882 | 20.5765 | 29.8647 | 4.1922 | 8.1061 | 6.1922 | 5.1922 | 7.2882 | 9.2882 | 8.1061 | 13.2982 | 20.5865 | 29.8747 | 0.01
8.0617 | 10.0308 | 10.0617 | 9.0617 | 13.0925 | 15.0925 | 10.0308 | 19.0925 | 32.185 | 47.2775 | 8.0617 | 10.0408 | 10.0617 | 9.0617 | 13.0925 | 15.0925 | 10.0408 | 19.1025 | 32.195 | 47.2875 | 0.01
7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 7.4889 | 9.7544 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7544 | 18.2433 | 30.4766 | 44.7098 | 0.01
11.8438 | 11.9219 | 13.8438 | 12.8438 | 18.7656 | 20.7656 | 11.9219 | 24.7656 | 43.5313 | 64.2969 | 11.8438 | 11.9319 | 13.8438 | 12.8438 | 18.7656 | 20.7656 | 11.9319 | 24.7756 | 43.5413 | 64.3069 | 0.01
6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 6.3314 | 9.1757 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1757 | 16.5072 | 27.0043 | 39.5015 | 0.01
8.8082 | 10.4041 | 10.8082 | 9.8082 | 14.2124 | 16.2124 | 10.4041 | 20.2124 | 34.4247 | 50.6371 | 8.8082 | 10.4141 | 10.8082 | 9.8082 | 14.2124 | 16.2124 | 10.4141 | 20.2224 | 34.4347 | 50.6471 | 0.01
7.6294 | 9.8147 | 9.6294 | 8.6294 | 12.4441 | 14.4441 | 9.8147 | 18.4441 | 30.8883 | 45.3324 | 7.6294 | 9.8247 | 9.6294 | 8.6294 | 12.4441 | 14.4441 | 9.8247 | 18.4541 | 30.8983 | 45.3424 | 0.01
6.2816 | 9.1408 | 8.2816 | 7.2816 | 10.4224 | 12.4224 | 9.1408 | 16.4224 | 26.8448 | 39.2672 | 6.2816 | 9.1508 | 8.2816 | 7.2816 | 10.4224 | 12.4224 | 9.1508 | 16.4324 | 26.8548 | 39.2772 | 0.01
2.9948 | 7.4974 | 4.9948 | 3.9948 | 5.4922 | 7.4922 | 7.4974 | 11.4922 | 16.9843 | 24.4765 | 2.9948 | 7.5074 | 4.9948 | 3.9948 | 5.4922 | 7.4922 | 7.5074 | 11.5022 | 16.9943 | 24.4865 | 0.01
7.6577 | 9.8289 | 9.6577 | 8.6577 | 12.4866 | 14.4866 | 9.8289 | 18.4866 | 30.9732 | 45.4598 | 7.6577 | 9.8389 | 9.6577 | 8.6577 | 12.4866 | 14.4866 | 9.8389 | 18.4966 | 30.9832 | 45.4698 | 0.01
5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 5.0973 | 8.5587 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5587 | 14.656 | 23.302 | 33.9481 | 0.01
6.3502 | 9.1751 | 8.3502 | 7.3502 | 10.5253 | 12.5253 | 9.1751 | 16.5253 | 27.0507 | 39.576 | 6.3502 | 9.1851 | 8.3502 | 7.3502 | 10.5253 | 12.5253 | 9.1851 | 16.5353 | 27.0607 | 39.586 | 0.01
8.2841 | 10.1421 | 10.2841 | 9.2841 | 13.4262 | 15.4262 | 10.1421 | 19.4262 | 32.8524 | 48.2786 | 8.2841 | 10.1521 | 10.2841 | 9.2841 | 13.4262 | 15.4262 | 10.1521 | 19.4362 | 32.8624 | 48.2886 | 0.01
7.4494 | 9.7247 | 9.4494 | 8.4494 | 12.1741 | 14.1741 | 9.7247 | 18.1741 | 30.3481 | 44.5222 | 7.4494 | 9.7347 | 9.4494 | 8.4494 | 12.1741 | 14.1741 | 9.7347 | 18.1841 | 30.3581 | 44.5322 | 0.01
5.769 | 8.8845 | 7.769 | 6.769 | 9.6535 | 11.6535 | 8.8845 | 15.6535 | 25.307 | 36.9605 | 5.769 | 8.8945 | 7.769 | 6.769 | 9.6535 | 11.6535 | 8.8945 | 15.6635 | 25.317 | 36.9705 | 0.01
5.8084 | 8.9042 | 7.8084 | 6.8084 | 9.7126 | 11.7126 | 8.9042 | 15.7126 | 25.4252 | 37.1377 | 5.8084 | 8.9142 | 7.8084 | 6.8084 | 9.7126 | 11.7126 | 8.9142 | 15.7226 | 25.4352 | 37.1477 | 0.01
4.3983 | 8.1992 | 6.3983 | 5.3983 | 7.5975 | 9.5975 | 8.1992 | 13.5975 | 21.195 | 30.7925 | 4.3983 | 8.2092 | 6.3983 | 5.3983 | 7.5975 | 9.5975 | 8.2092 | 13.6075 | 21.205 | 30.8025 | 0.01
4.0729 | 8.0365 | 6.0729 | 5.0729 | 7.1094 | 9.1094 | 8.0365 | 13.1094 | 20.2188 | 29.3281 | 4.0729 | 8.0465 | 6.0729 | 5.0729 | 7.1094 | 9.1094 | 8.0465 | 13.1194 | 20.2288 | 29.3381 | 0.01
6.5512 | 9.2756 | 8.5512 | 7.5512 | 10.8268 | 12.8268 | 9.2756 | 16.8268 | 27.6536 | 40.4803 | 6.5512 | 9.2856 | 8.5512 | 7.5512 | 10.8268 | 12.8268 | 9.2856 | 16.8368 | 27.6636 | 40.4903 | 0.01
3.2266 | 7.6133 | 5.2266 | 4.2266 | 5.8399 | 7.8399 | 7.6133 | 11.8399 | 17.6798 | 25.5197 | 3.2266 | 7.6233 | 5.2266 | 4.2266 | 5.8399 | 7.8399 | 7.6233 | 11.8499 | 17.6898 | 25.5297 | 0.01
6.4914 | 9.2457 | 8.4914 | 7.4914 | 10.737 | 12.737 | 9.2457 | 16.737 | 27.4741 | 40.2111 | 6.4914 | 9.2557 | 8.4914 | 7.4914 | 10.737 | 12.737 | 9.2557 | 16.747 | 27.4841 | 40.2211 | 0.01
7.4177 | 9.7089 | 9.4177 | 8.4177 | 12.1266 | 14.1266 | 9.7089 | 18.1266 | 30.2532 | 44.3798 | 7.4177 | 9.7189 | 9.4177 | 8.4177 | 12.1266 | 14.1266 | 9.7189 | 18.1366 | 30.2632 | 44.3898 | 0.01
3.4213 | 7.7106 | 5.4213 | 4.4213 | 6.1319 | 8.1319 | 7.7106 | 12.1319 | 18.2638 | 26.3957 | 3.4213 | 7.7206 | 5.4213 | 4.4213 | 6.1319 | 8.1319 | 7.7206 | 12.1419 | 18.2738 | 26.4057 | 0.01
4.6599 | 8.3299 | 6.6599 | 5.6599 | 7.9898 | 9.9898 | 8.3299 | 13.9898 | 21.9797 | 31.9695 | 4.6599 | 8.3399 | 6.6599 | 5.6599 | 7.9898 | 9.9898 | 8.3399 | 13.9998 | 21.9897 | 31.9795 | 0.01
7.9283 | 9.9641 | 9.9283 | 8.9283 | 12.8924 | 14.8924 | 9.9641 | 18.8924 | 31.7849 | 46.6773 | 7.9283 | 9.9741 | 9.9283 | 8.9283 | 12.8924 | 14.8924 | 9.9741 | 18.9024 | 31.7949 | 46.6873 | 0.01
8.1195 | 10.0598 | 10.1195 | 9.1195 | 13.1793 | 15.1793 | 10.0598 | 19.1793 | 32.3586 | 47.5378 | 8.1195 | 10.0698 | 10.1195 | 9.1195 | 13.1793 | 15.1793 | 10.0698 | 19.1893 | 32.3686 | 47.5478 | 0.01
5.1511 | 8.5755 | 7.1511 | 6.1511 | 8.7266 | 10.7266 | 8.5755 | 14.7266 | 23.4532 | 34.1798 | 5.1511 | 8.5855 | 7.1511 | 6.1511 | 8.7266 | 10.7266 | 8.5855 | 14.7366 | 23.4632 | 34.1898 | 0.01
4.3661 | 8.183 | 6.3661 | 5.3661 | 7.5491 | 9.5491 | 8.183 | 13.5491 | 21.0983 | 30.6474 | 4.3661 | 8.193 | 6.3661 | 5.3661 | 7.5491 | 9.5491 | 8.193 | 13.5591 | 21.1083 | 30.6574 | 0.01
4.8403 | 8.4202 | 6.8403 | 5.8403 | 8.2605 | 10.2605 | 8.4202 | 14.2605 | 22.521 | 32.7815 | 4.8403 | 8.4302 | 6.8403 | 5.8403 | 8.2605 | 10.2605 | 8.4302 | 14.2705 | 22.531 | 32.7915 | 0.01
6.6155 | 9.3078 | 8.6155 | 7.6155 | 10.9233 | 12.9233 | 9.3078 | 16.9233 | 27.8466 | 40.7699 | 6.6155 | 9.3178 | 8.6155 | 7.6155 | 10.9233 | 12.9233 | 9.3178 | 16.9333 | 27.8566 | 40.7799 | 0.01
6.1813 | 9.0907 | 8.1813 | 7.1813 | 10.272 | 12.272 | 9.0907 | 16.272 | 26.544 | 38.8159 | 6.1813 | 9.1007 | 8.1813 | 7.1813 | 10.272 | 12.272 | 9.1007 | 16.282 | 26.554 | 38.8259 | 0.01
6.6324 | 9.3162 | 8.6324 | 7.6324 | 10.9486 | 12.9486 | 9.3162 | 16.9486 | 27.8972 | 40.8458 | 6.6324 | 9.3262 | 8.6324 | 7.6324 | 10.9486 | 12.9486 | 9.3262 | 16.9586 | 27.9072 | 40.8558 | 0.01
5.7216 | 8.8608 | 7.7216 | 6.7216 | 9.5825 | 11.5825 | 8.8608 | 15.5825 | 25.1649 | 36.7474 | 5.7216 | 8.8708 | 7.7216 | 6.7216 | 9.5825 | 11.5825 | 8.8708 | 15.5925 | 25.1749 | 36.7574 | 0.01
5.8658 | 8.9329 | 7.8658 | 6.8658 | 9.7987 | 11.7987 | 8.9329 | 15.7987 | 25.5974 | 37.3961 | 5.8658 | 8.9429 | 7.8658 | 6.8658 | 9.7987 | 11.7987 | 8.9429 | 15.8087 | 25.6074 | 37.4061 | 0.01
4.2094 | 8.1047 | 6.2094 | 5.2094 | 7.314 | 9.314 | 8.1047 | 13.314 | 20.6281 | 29.9421 | 4.2094 | 8.1147 | 6.2094 | 5.2094 | 7.314 | 9.314 | 8.1147 | 13.324 | 20.6381 | 29.9521 | 0.01
5.2214 | 8.6107 | 7.2214 | 6.2214 | 8.8321 | 10.8321 | 8.6107 | 14.8321 | 23.6641 | 34.4962 | 5.2214 | 8.6207 | 7.2214 | 6.2214 | 8.8321 | 10.8321 | 8.6207 | 14.8421 | 23.6741 | 34.5062 | 0.01
5.3992 | 8.6996 | 7.3992 | 6.3992 | 9.0988 | 11.0988 | 8.6996 | 15.0988 | 24.1976 | 35.2965 | 5.3992 | 8.7096 | 7.3992 | 6.3992 | 9.0988 | 11.0988 | 8.7096 | 15.1088 | 24.2076 | 35.3065 | 0.01
9.2618 | 10.6309 | 11.2618 | 10.2618 | 14.8927 | 16.8927 | 10.6309 | 20.8927 | 35.7855 | 52.6782 | 9.2618 | 10.6409 | 11.2618 | 10.2618 | 14.8927 | 16.8927 | 10.6409 | 20.9027 | 35.7955 | 52.6882 | 0.01
2.5164 | 7.2582 | 4.5164 | 3.5164 | 4.7746 | 6.7746 | 7.2582 | 10.7746 | 15.5493 | 22.3239 | 2.5164 | 7.2682 | 4.5164 | 3.5164 | 4.7746 | 6.7746 | 7.2682 | 10.7846 | 15.5593 | 22.3339 | 0.01
6.053 | 9.0265 | 8.053 | 7.053 | 10.0795 | 12.0795 | 9.0265 | 16.0795 | 26.1591 | 38.2386 | 6.053 | 9.0365 | 8.053 | 7.053 | 10.0795 | 12.0795 | 9.0365 | 16.0895 | 26.1691 | 38.2486 | 0.01
11.0086 | 11.5043 | 13.0086 | 12.0086 | 17.5129 | 19.5129 | 11.5043 | 23.5129 | 41.0259 | 60.5388 | 11.0086 | 11.5143 | 13.0086 | 12.0086 | 17.5129 | 19.5129 | 11.5143 | 23.5229 | 41.0359 | 60.5488 | 0.01
9.7368 | 10.8684 | 11.7368 | 10.7368 | 15.6052 | 17.6052 | 10.8684 | 21.6052 | 37.2103 | 54.8155 | 9.7368 | 10.8784 | 11.7368 | 10.7368 | 15.6052 | 17.6052 | 10.8784 | 21.6152 | 37.2203 | 54.8255 | 0.01
9.4739 | 10.7369 | 11.4739 | 10.4739 | 15.2108 | 17.2108 | 10.7369 | 21.2108 | 36.4216 | 53.6323 | 9.4739 | 10.7469 | 11.4739 | 10.4739 | 15.2108 | 17.2108 | 10.7469 | 21.2208 | 36.4316 | 53.6423 | 0.01
4.0971 | 8.0486 | 6.0971 | 5.0971 | 7.1457 | 9.1457 | 8.0486 | 13.1457 | 20.2913 | 29.437 | 4.0971 | 8.0586 | 6.0971 | 5.0971 | 7.1457 | 9.1457 | 8.0586 | 13.1557 | 20.3013 | 29.447 | 0.01
7.1106 | 9.5553 | 9.1106 | 8.1106 | 11.6659 | 13.6659 | 9.5553 | 17.6659 | 29.3318 | 42.9977 | 7.1106 | 9.5653 | 9.1106 | 8.1106 | 11.6659 | 13.6659 | 9.5653 | 17.6759 | 29.3418 | 43.0077 | 0.01
8.668 | 10.334 | 10.668 | 9.668 | 14.0021 | 16.0021 | 10.334 | 20.0021 | 34.0041 | 50.0062 | 8.668 | 10.344 | 10.668 | 9.668 | 14.0021 | 16.0021 | 10.344 | 20.0121 | 34.0141 | 50.0162 | 0.01
5.0877 | 8.5438 | 7.0877 | 6.0877 | 8.6315 | 10.6315 | 8.5438 | 14.6315 | 23.263 | 33.8945 | 5.0877 | 8.5538 | 7.0877 | 6.0877 | 8.6315 | 10.6315 | 8.5538 | 14.6415 | 23.273 | 33.9045 | 0.01
3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 3.9727 | 7.9963 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9963 | 12.969 | 19.928 | 28.8869 | 0.01
6.5588 | 9.2794 | 8.5588 | 7.5588 | 10.8382 | 12.8382 | 9.2794 | 16.8382 | 27.6765 | 40.5147 | 6.5588 | 9.2894 | 8.5588 | 7.5588 | 10.8382 | 12.8382 | 9.2894 | 16.8482 | 27.6865 | 40.5247 | 0.01
5.3003 | 8.6502 | 7.3003 | 6.3003 | 8.9505 | 10.9505 | 8.6502 | 14.9505 | 23.901 | 34.8515 | 5.3003 | 8.6602 | 7.3003 | 6.3003 | 8.9505 | 10.9505 | 8.6602 | 14.9605 | 23.911 | 34.8615 | 0.01
5.3086 | 8.6543 | 7.3086 | 6.3086 | 8.9629 | 10.9629 | 8.6543 | 14.9629 | 23.9259 | 34.8888 | 5.3086 | 8.6643 | 7.3086 | 6.3086 | 8.9629 | 10.9629 | 8.6643 | 14.9729 | 23.9359 | 34.8988 | 0.01
4.5764 | 8.2882 | 6.5764 | 5.5764 | 7.8645 | 9.8645 | 8.2882 | 13.8645 | 21.7291 | 31.5936 | 4.5764 | 8.2982 | 6.5764 | 5.5764 | 7.8645 | 9.8645 | 8.2982 | 13.8745 | 21.7391 | 31.6036 | 0.01
5.9923 | 8.9961 | 7.9923 | 6.9923 | 9.9884 | 11.9884 | 8.9961 | 15.9884 | 25.9768 | 37.9652 | 5.9923 | 9.0061 | 7.9923 | 6.9923 | 9.9884 | 11.9884 | 9.0061 | 15.9984 | 25.9868 | 37.9752 | 0.01
2.2553 | 7.1277 | 4.2553 | 3.2553 | 4.383 | 6.383 | 7.1277 | 10.383 | 14.766 | 21.1489 | 2.2553 | 7.1377 | 4.2553 | 3.2553 | 4.383 | 6.383 | 7.1377 | 10.393 | 14.776 | 21.1589 | 0.01
3.77 | 7.885 | 5.77 | 4.77 | 6.6549 | 8.6549 | 7.885 | 12.6549 | 19.3099 | 27.9648 | 3.77 | 7.895 | 5.77 | 4.77 | 6.6549 | 8.6549 | 7.895 | 12.6649 | 19.3199 | 27.9748 | 0.01
5.0845 | 8.5422 | 7.0845 | 6.0845 | 8.6267 | 10.6267 | 8.5422 | 14.6267 | 23.2534 | 33.88 | 5.0845 | 8.5522 | 7.0845 | 6.0845 | 8.6267 | 10.6267 | 8.5522 | 14.6367 | 23.2634 | 33.89 | 0.01
10.4131 | 11.2066 | 12.4131 | 11.4131 | 16.6197 | 18.6197 | 11.2066 | 22.6197 | 39.2394 | 57.8591 | 10.4131 | 11.2166 | 12.4131 | 11.4131 | 16.6197 | 18.6197 | 11.2166 | 22.6297 | 39.2494 | 57.8691 | 0.01
6.5663 | 9.2831 | 8.5663 | 7.5663 | 10.8494 | 12.8494 | 9.2831 | 16.8494 | 27.6989 | 40.5483 | 6.5663 | 9.2931 | 8.5663 | 7.5663 | 10.8494 | 12.8494 | 9.2931 | 16.8594 | 27.7089 | 40.5583 | 0.01
5.6487 | 8.8243 | 7.6487 | 6.6487 | 9.473 | 11.473 | 8.8243 | 15.473 | 24.946 | 36.4191 | 5.6487 | 8.8343 | 7.6487 | 6.6487 | 9.473 | 11.473 | 8.8343 | 15.483 | 24.956 | 36.4291 | 0.01
7.5932 | 9.7966 | 9.5932 | 8.5932 | 12.3899 | 14.3899 | 9.7966 | 18.3899 | 30.7797 | 45.1696 | 7.5932 | 9.8066 | 9.5932 | 8.5932 | 12.3899 | 14.3899 | 9.8066 | 18.3999 | 30.7897 | 45.1796 | 0.01
3.3026 | 7.6513 | 5.3026 | 4.3026 | 5.9539 | 7.9539 | 7.6513 | 11.9539 | 17.9078 | 25.8617 | 3.3026 | 7.6613 | 5.3026 | 4.3026 | 5.9539 | 7.9539 | 7.6613 | 11.9639 | 17.9178 | 25.8717 | 0.01
3.76 | 7.88 | 5.76 | 4.76 | 6.6399 | 8.6399 | 7.88 | 12.6399 | 19.2799 | 27.9198 | 3.76 | 7.89 | 5.76 | 4.76 | 6.6399 | 8.6399 | 7.89 | 12.6499 | 19.2899 | 27.9298 | 0.01
5.8466 | 8.9233 | 7.8466 | 6.8466 | 9.7699 | 11.7699 | 8.9233 | 15.7699 | 25.5399 | 37.3098 | 5.8466 | 8.9333 | 7.8466 | 6.8466 | 9.7699 | 11.7699 | 8.9333 | 15.7799 | 25.5499 | 37.3198 | 0.01
6.6787 | 9.3394 | 8.6787 | 7.6787 | 11.0181 | 13.0181 | 9.3394 | 17.0181 | 28.0362 | 41.0543 | 6.6787 | 9.3494 | 8.6787 | 7.6787 | 11.0181 | 13.0181 | 9.3494 | 17.0281 | 28.0462 | 41.0643 | 0.01
5.4037 | 8.7018 | 7.4037 | 6.4037 | 9.1055 | 11.1055 | 8.7018 | 15.1055 | 24.2111 | 35.3166 | 5.4037 | 8.7118 | 7.4037 | 6.4037 | 9.1055 | 11.1055 | 8.7118 | 15.1155 | 24.2211 | 35.3266 | 0.01
6.474 | 9.237 | 8.474 | 7.474 | 10.711 | 12.711 | 9.237 | 16.711 | 27.4221 | 40.1331 | 6.474 | 9.247 | 8.474 | 7.474 | 10.711 | 12.711 | 9.247 | 16.721 | 27.4321 | 40.1431 | 0.01
6.1767 | 9.0884 | 8.1767 | 7.1767 | 10.2651 | 12.2651 | 9.0884 | 16.2651 | 26.5301 | 38.7952 | 6.1767 | 9.0984 | 8.1767 | 7.1767 | 10.2651 | 12.2651 | 9.0984 | 16.2751 | 26.5401 | 38.8052 | 0.01
6.604 | 9.302 | 8.604 | 7.604 | 10.906 | 12.906 | 9.302 | 16.906 | 27.812 | 40.7179 | 6.604 | 9.312 | 8.604 | 7.604 | 10.906 | 12.906 | 9.312 | 16.916 | 27.822 | 40.7279 | 0.01
4.67 | 8.335 | 6.67 | 5.67 | 8.005 | 10.005 | 8.335 | 14.005 | 22.0101 | 32.0151 | 4.67 | 8.345 | 6.67 | 5.67 | 8.005 | 10.005 | 8.345 | 14.015 | 22.0201 | 32.0251 | 0.01
5.3308 | 8.6654 | 7.3308 | 6.3308 | 8.9962 | 10.9962 | 8.6654 | 14.9962 | 23.9925 | 34.9887 | 5.3308 | 8.6754 | 7.3308 | 6.3308 | 8.9962 | 10.9962 | 8.6754 | 15.0062 | 24.0025 | 34.9987 | 0.01
5.7182 | 8.8591 | 7.7182 | 6.7182 | 9.5774 | 11.5774 | 8.8591 | 15.5774 | 25.1547 | 36.7321 | 5.7182 | 8.8691 | 7.7182 | 6.7182 | 9.5774 | 11.5774 | 8.8691 | 15.5874 | 25.1647 | 36.7421 | 0.01
1.3905 | 6.6952 | 3.3905 | 2.3905 | 3.0857 | 5.0857 | 6.6952 | 9.0857 | 12.1714 | 17.2571 | 1.3905 | 6.7052 | 3.3905 | 2.3905 | 3.0857 | 5.0857 | 6.7052 | 9.0957 | 12.1814 | 17.2671 | 0.01
4.6854 | 8.3427 | 6.6854 | 5.6854 | 8.0282 | 10.0282 | 8.3427 | 14.0282 | 22.0563 | 32.0845 | 4.6854 | 8.3527 | 6.6854 | 5.6854 | 8.0282 | 10.0282 | 8.3527 | 14.0382 | 22.0663 | 32.0945 | 0.01
4.5016 | 8.2508 | 6.5016 | 5.5016 | 7.7525 | 9.7525 | 8.2508 | 13.7525 | 21.5049 | 31.2574 | 4.5016 | 8.2608 | 6.5016 | 5.5016 | 7.7525 | 9.7525 | 8.2608 | 13.7625 | 21.5149 | 31.2674 | 0.01
3.0906 | 7.5453 | 5.0906 | 4.0906 | 5.6359 | 7.6359 | 7.5453 | 11.6359 | 17.2719 | 24.9078 | 3.0906 | 7.5553 | 5.0906 | 4.0906 | 5.6359 | 7.6359 | 7.5553 | 11.6459 | 17.2819 | 24.9178 | 0.01
3.6427 | 7.8213 | 5.6427 | 4.6427 | 6.464 | 8.464 | 7.8213 | 12.464 | 18.928 | 27.392 | 3.6427 | 7.8313 | 5.6427 | 4.6427 | 6.464 | 8.464 | 7.8313 | 12.474 | 18.938 | 27.402 | 0.01
3.7734 | 7.8867 | 5.7734 | 4.7734 | 6.66 | 8.66 | 7.8867 | 12.66 | 19.3201 | 27.9801 | 3.7734 | 7.8967 | 5.7734 | 4.7734 | 6.66 | 8.66 | 7.8967 | 12.67 | 19.3301 | 27.9901 | 0.01
5.5801 | 8.79 | 7.5801 | 6.5801 | 9.3701 | 11.3701 | 8.79 | 15.3701 | 24.7403 | 36.1104 | 5.5801 | 8.8 | 7.5801 | 6.5801 | 9.3701 | 11.3701 | 8.8 | 15.3801 | 24.7503 | 36.1204 | 0.01
7.3028 | 9.6514 | 9.3028 | 8.3028 | 11.9542 | 13.9542 | 9.6514 | 17.9542 | 29.9084 | 43.8626 | 7.3028 | 9.6614 | 9.3028 | 8.3028 | 11.9542 | 13.9542 | 9.6614 | 17.9642 | 29.9184 | 43.8726 | 0.01
4.8107 | 8.4054 | 6.8107 | 5.8107 | 8.2161 | 10.2161 | 8.4054 | 14.2161 | 22.4321 | 32.6482 | 4.8107 | 8.4154 | 6.8107 | 5.8107 | 8.2161 | 10.2161 | 8.4154 | 14.2261 | 22.4421 | 32.6582 | 0.01
6.0516 | 9.0258 | 8.0516 | 7.0516 | 10.0775 | 12.0775 | 9.0258 | 16.0775 | 26.1549 | 38.2324 | 6.0516 | 9.0358 | 8.0516 | 7.0516 | 10.0775 | 12.0775 | 9.0358 | 16.0875 | 26.1649 | 38.2424 | 0.01
7.0705 | 9.5352 | 9.0705 | 8.0705 | 11.6057 | 13.6057 | 9.5352 | 17.6057 | 29.2114 | 42.8171 | 7.0705 | 9.5452 | 9.0705 | 8.0705 | 11.6057 | 13.6057 | 9.5452 | 17.6157 | 29.2214 | 42.8271 | 0.01
7.2568 | 9.6284 | 9.2568 | 8.2568 | 11.8852 | 13.8852 | 9.6284 | 17.8852 | 29.7704 | 43.6556 | 7.2568 | 9.6384 | 9.2568 | 8.2568 | 11.8852 | 13.8852 | 9.6384 | 17.8952 | 29.7804 | 43.6656 | 0.01
5.5195 | 8.7598 | 7.5195 | 6.5195 | 9.2793 | 11.2793 | 8.7598 | 15.2793 | 24.5586 | 35.8378 | 5.5195 | 8.7698 | 7.5195 | 6.5195 | 9.2793 | 11.2793 | 8.7698 | 15.2893 | 24.5686 | 35.8478 | 0.01
7.7236 | 9.8618 | 9.7236 | 8.7236 | 12.5854 | 14.5854 | 9.8618 | 18.5854 | 31.1707 | 45.7561 | 7.7236 | 9.8718 | 9.7236 | 8.7236 | 12.5854 | 14.5854 | 9.8718 | 18.5954 | 31.1807 | 45.7661 | 0.01
7.4454 | 9.7227 | 9.4454 | 8.4454 | 12.1681 | 14.1681 | 9.7227 | 18.1681 | 30.3362 | 44.5043 | 7.4454 | 9.7327 | 9.4454 | 8.4454 | 12.1681 | 14.1681 | 9.7327 | 18.1781 | 30.3462 | 44.5143 | 0.01
7.2098 | 9.6049 | 9.2098 | 8.2098 | 11.8147 | 13.8147 | 9.6049 | 17.8147 | 29.6294 | 43.4441 | 7.2098 | 9.6149 | 9.2098 | 8.2098 | 11.8147 | 13.8147 | 9.6149 | 17.8247 | 29.6394 | 43.4541 | 0.01
8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 8.0477 | 10.0338 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0338 | 19.0815 | 32.153 | 47.2244 | 0.01
5.3983 | 8.6991 | 7.3983 | 6.3983 | 9.0974 | 11.0974 | 8.6991 | 15.0974 | 24.1948 | 35.2922 | 5.3983 | 8.7091 | 7.3983 | 6.3983 | 9.0974 | 11.0974 | 8.7091 | 15.1074 | 24.2048 | 35.3022 | 0.01
8.1214 | 10.0607 | 10.1214 | 9.1214 | 13.1821 | 15.1821 | 10.0607 | 19.1821 | 32.3642 | 47.5463 | 8.1214 | 10.0707 | 10.1214 | 9.1214 | 13.1821 | 15.1821 | 10.0707 | 19.1921 | 32.3742 | 47.5563 | 0.01
5.6079 | 8.8039 | 7.6079 | 6.6079 | 9.4118 | 11.4118 | 8.8039 | 15.4118 | 24.8237 | 36.2355 | 5.6079 | 8.8139 | 7.6079 | 6.6079 | 9.4118 | 11.4118 | 8.8139 | 15.4218 | 24.8337 | 36.2455 | 0.01
6.4616 | 9.2308 | 8.4616 | 7.4616 | 10.6924 | 12.6924 | 9.2308 | 16.6924 | 27.3848 | 40.0772 | 6.4616 | 9.2408 | 8.4616 | 7.4616 | 10.6924 | 12.6924 | 9.2408 | 16.7024 | 27.3948 | 40.0872 | 0.01
5.8819 | 8.9409 | 7.8819 | 6.8819 | 9.8228 | 11.8228 | 8.9409 | 15.8228 | 25.6457 | 37.4685 | 5.8819 | 8.9509 | 7.8819 | 6.8819 | 9.8228 | 11.8228 | 8.9509 | 15.8328 | 25.6557 | 37.4785 | 0.01
3.8915 | 7.9457 | 5.8915 | 4.8915 | 6.8372 | 8.8372 | 7.9457 | 12.8372 | 19.6744 | 28.5115 | 3.8915 | 7.9557 | 5.8915 | 4.8915 | 6.8372 | 8.8372 | 7.9557 | 12.8472 | 19.6844 | 28.5215 | 0.01
3.9971 | 7.9985 | 5.9971 | 4.9971 | 6.9956 | 8.9956 | 7.9985 | 12.9956 | 19.9912 | 28.9868 | 3.9971 | 8.0085 | 5.9971 | 4.9971 | 6.9956 | 8.9956 | 8.0085 | 13.0056 | 20.0012 | 28.9968 | 0.01
6.3642 | 9.1821 | 8.3642 | 7.3642 | 10.5463 | 12.5463 | 9.1821 | 16.5463 | 27.0927 | 39.639 | 6.3642 | 9.1921 | 8.3642 | 7.3642 | 10.5463 | 12.5463 | 9.1921 | 16.5563 | 27.1027 | 39.649 | 0.01
9.0628 | 10.5314 | 11.0628 | 10.0628 | 14.5941 | 16.5941 | 10.5314 | 20.5941 | 35.1883 | 51.7824 | 9.0628 | 10.5414 | 11.0628 | 10.0628 | 14.5941 | 16.5941 | 10.5414 | 20.6041 | 35.1983 | 51.7924 | 0.01
6.7215 | 9.3608 | 8.7215 | 7.7215 | 11.0823 | 13.0823 | 9.3608 | 17.0823 | 28.1645 | 41.2468 | 6.7215 | 9.3708 | 8.7215 | 7.7215 | 11.0823 | 13.0823 | 9.3708 | 17.0923 | 28.1745 | 41.2568 | 0.01
7.5347 | 9.7673 | 9.5347 | 8.5347 | 12.302 | 14.302 | 9.7673 | 18.302 | 30.604 | 44.906 | 7.5347 | 9.7773 | 9.5347 | 8.5347 | 12.302 | 14.302 | 9.7773 | 18.312 | 30.614 | 44.916 | 0.01
4.2203 | 8.1102 | 6.2203 | 5.2203 | 7.3305 | 9.3305 | 8.1102 | 13.3305 | 20.6609 | 29.9914 | 4.2203 | 8.1202 | 6.2203 | 5.2203 | 7.3305 | 9.3305 | 8.1202 | 13.3405 | 20.6709 | 30.0014 | 0.01
4.9198 | 8.4599 | 6.9198 | 5.9198 | 8.3797 | 10.3797 | 8.4599 | 14.3797 | 22.7594 | 33.1391 | 4.9198 | 8.4699 | 6.9198 | 5.9198 | 8.3797 | 10.3797 | 8.4699 | 14.3897 | 22.7694 | 33.1491 | 0.01
3.252 | 7.626 | 5.252 | 4.252 | 5.878 | 7.878 | 7.626 | 11.878 | 17.7559 | 25.6339 | 3.252 | 7.636 | 5.252 | 4.252 | 5.878 | 7.878 | 7.636 | 11.888 | 17.7659 | 25.6439 | 0.01
6.2071 | 9.1036 | 8.2071 | 7.2071 | 10.3107 | 12.3107 | 9.1036 | 16.3107 | 26.6214 | 38.9322 | 6.2071 | 9.1136 | 8.2071 | 7.2071 | 10.3107 | 12.3107 | 9.1136 | 16.3207 | 26.6314 | 38.9422 | 0.01
6.9816 | 9.4908 | 8.9816 | 7.9816 | 11.4725 | 13.4725 | 9.4908 | 17.4725 | 28.9449 | 42.4174 | 6.9816 | 9.5008 | 8.9816 | 7.9816 | 11.4725 | 13.4725 | 9.5008 | 17.4825 | 28.9549 | 42.4274 | 0.01
4.3537 | 8.1768 | 6.3537 | 5.3537 | 7.5305 | 9.5305 | 8.1768 | 13.5305 | 21.061 | 30.5915 | 4.3537 | 8.1868 | 6.3537 | 5.3537 | 7.5305 | 9.5305 | 8.1868 | 13.5405 | 21.071 | 30.6015 | 0.01
7.4024 | 9.7012 | 9.4024 | 8.4024 | 12.1036 | 14.1036 | 9.7012 | 18.1036 | 30.2073 | 44.3109 | 7.4024 | 9.7112 | 9.4024 | 8.4024 | 12.1036 | 14.1036 | 9.7112 | 18.1136 | 30.2173 | 44.3209 | 0.01
5.2403 | 8.6202 | 7.2403 | 6.2403 | 8.8605 | 10.8605 | 8.6202 | 14.8605 | 23.7209 | 34.5814 | 5.2403 | 8.6302 | 7.2403 | 6.2403 | 8.8605 | 10.8605 | 8.6302 | 14.8705 | 23.7309 | 34.5914 | 0.01
6.5781 | 9.289 | 8.5781 | 7.5781 | 10.8671 | 12.8671 | 9.289 | 16.8671 | 27.7343 | 40.6014 | 6.5781 | 9.299 | 8.5781 | 7.5781 | 10.8671 | 12.8671 | 9.299 | 16.8771 | 27.7443 | 40.6114 | 0.01
7.6429 | 9.8215 | 9.6429 | 8.6429 | 12.4644 | 14.4644 | 9.8215 | 18.4644 | 30.9287 | 45.3931 | 7.6429 | 9.8315 | 9.6429 | 8.6429 | 12.4644 | 14.4644 | 9.8315 | 18.4744 | 30.9387 | 45.4031 | 0.01
6.3829 | 9.1915 | 8.3829 | 7.3829 | 10.5744 | 12.5744 | 9.1915 | 16.5744 | 27.1487 | 39.7231 | 6.3829 | 9.2015 | 8.3829 | 7.3829 | 10.5744 | 12.5744 | 9.2015 | 16.5844 | 27.1587 | 39.7331 | 0.01
3.4405 | 7.7202 | 5.4405 | 4.4405 | 6.1607 | 8.1607 | 7.7202 | 12.1607 | 18.3214 | 26.4821 | 3.4405 | 7.7302 | 5.4405 | 4.4405 | 6.1607 | 8.1607 | 7.7302 | 12.1707 | 18.3314 | 26.4921 | 0.01
8.5773 | 10.2887 | 10.5773 | 9.5773 | 13.866 | 15.866 | 10.2887 | 19.866 | 33.732 | 49.598 | 8.5773 | 10.2987 | 10.5773 | 9.5773 | 13.866 | 15.866 | 10.2987 | 19.876 | 33.742 | 49.608 | 0.01
8.9551 | 10.4775 | 10.9551 | 9.9551 | 14.4326 | 16.4326 | 10.4775 | 20.4326 | 34.8653 | 51.2979 | 8.9551 | 10.4875 | 10.9551 | 9.9551 | 14.4326 | 16.4326 | 10.4875 | 20.4426 | 34.8753 | 51.3079 | 0.01
5.4187 | 8.7094 | 7.4187 | 6.4187 | 9.1281 | 11.1281 | 8.7094 | 15.1281 | 24.2561 | 35.3842 | 5.4187 | 8.7194 | 7.4187 | 6.4187 | 9.1281 | 11.1281 | 8.7194 | 15.1381 | 24.2661 | 35.3942 | 0.01
5.3886 | 8.6943 | 7.3886 | 6.3886 | 9.083 | 11.083 | 8.6943 | 15.083 | 24.1659 | 35.2489 | 5.3886 | 8.7043 | 7.3886 | 6.3886 | 9.083 | 11.083 | 8.7043 | 15.093 | 24.1759 | 35.2589 | 0.01
8.0894 | 10.0447 | 10.0894 | 9.0894 | 13.1342 | 15.1342 | 10.0447 | 19.1342 | 32.2683 | 47.4025 | 8.0894 | 10.0547 | 10.0894 | 9.0894 | 13.1342 | 15.1342 | 10.0547 | 19.1442 | 32.2783 | 47.4125 | 0.01
9.5481 | 10.7741 | 11.5481 | 10.5481 | 15.3222 | 17.3222 | 10.7741 | 21.3222 | 36.6444 | 53.9666 | 9.5481 | 10.7841 | 11.5481 | 10.5481 | 15.3222 | 17.3222 | 10.7841 | 21.3322 | 36.6544 | 53.9766 | 0.01
8.3839 | 10.1919 | 10.3839 | 9.3839 | 13.5758 | 15.5758 | 10.1919 | 19.5758 | 33.1517 | 48.7275 | 8.3839 | 10.2019 | 10.3839 | 9.3839 | 13.5758 | 15.5758 | 10.2019 | 19.5858 | 33.1617 | 48.7375 | 0.01
5.3671 | 8.6836 | 7.3671 | 6.3671 | 9.0507 | 11.0507 | 8.6836 | 15.0507 | 24.1014 | 35.1521 | 5.3671 | 8.6936 | 7.3671 | 6.3671 | 9.0507 | 11.0507 | 8.6936 | 15.0607 | 24.1114 | 35.1621 | 0.01
6.4787 | 9.2394 | 8.4787 | 7.4787 | 10.7181 | 12.7181 | 9.2394 | 16.7181 | 27.4362 | 40.1544 | 6.4787 | 9.2494 | 8.4787 | 7.4787 | 10.7181 | 12.7181 | 9.2494 | 16.7281 | 27.4462 | 40.1644 | 0.01
9.3042 | 10.6521 | 11.3042 | 10.3042 | 14.9563 | 16.9563 | 10.6521 | 20.9563 | 35.9126 | 52.8689 | 9.3042 | 10.6621 | 11.3042 | 10.3042 | 14.9563 | 16.9563 | 10.6621 | 20.9663 | 35.9226 | 52.8789 | 0.01
2.544 | 7.272 | 4.544 | 3.544 | 4.816 | 6.816 | 7.272 | 10.816 | 15.632 | 22.448 | 2.544 | 7.282 | 4.544 | 3.544 | 4.816 | 6.816 | 7.282 | 10.826 | 15.642 | 22.458 | 0.01
4.3068 | 8.1534 | 6.3068 | 5.3068 | 7.4603 | 9.4603 | 8.1534 | 13.4603 | 20.9205 | 30.3808 | 4.3068 | 8.1634 | 6.3068 | 5.3068 | 7.4603 | 9.4603 | 8.1634 | 13.4703 | 20.9305 | 30.3908 | 0.01
4.3765 | 8.1883 | 6.3765 | 5.3765 | 7.5648 | 9.5648 | 8.1883 | 13.5648 | 21.1296 | 30.6944 | 4.3765 | 8.1983 | 6.3765 | 5.3765 | 7.5648 | 9.5648 | 8.1983 | 13.5748 | 21.1396 | 30.7044 | 0.01
8.9067 | 10.4534 | 10.9067 | 9.9067 | 14.3601 | 16.3601 | 10.4534 | 20.3601 | 34.7202 | 51.0803 | 8.9067 | 10.4634 | 10.9067 | 9.9067 | 14.3601 | 16.3601 | 10.4634 | 20.3701 | 34.7302 | 51.0903 | 0.01
5.8313 | 8.9156 | 7.8313 | 6.8313 | 9.7469 | 11.7469 | 8.9156 | 15.7469 | 25.4938 | 37.2407 | 5.8313 | 8.9256 | 7.8313 | 6.8313 | 9.7469 | 11.7469 | 8.9256 | 15.7569 | 25.5038 | 37.2507 | 0.01
5.7318 | 8.8659 | 7.7318 | 6.7318 | 9.5978 | 11.5978 | 8.8659 | 15.5978 | 25.1955 | 36.7933 | 5.7318 | 8.8759 | 7.7318 | 6.7318 | 9.5978 | 11.5978 | 8.8759 | 15.6078 | 25.2055 | 36.8033 | 0.01
4.0139 | 8.007 | 6.0139 | 5.0139 | 7.0209 | 9.0209 | 8.007 | 13.0209 | 20.0417 | 29.0626 | 4.0139 | 8.017 | 6.0139 | 5.0139 | 7.0209 | 9.0209 | 8.017 | 13.0309 | 20.0517 | 29.0726 | 0.01
4.3425 | 8.1712 | 6.3425 | 5.3425 | 7.5137 | 9.5137 | 8.1712 | 13.5137 | 21.0274 | 30.5411 | 4.3425 | 8.1812 | 6.3425 | 5.3425 | 7.5137 | 9.5137 | 8.1812 | 13.5237 | 21.0374 | 30.5511 | 0.01
6.3885 | 9.1943 | 8.3885 | 7.3885 | 10.5828 | 12.5828 | 9.1943 | 16.5828 | 27.1656 | 39.7483 | 6.3885 | 9.2043 | 8.3885 | 7.3885 | 10.5828 | 12.5828 | 9.2043 | 16.5928 | 27.1756 | 39.7583 | 0.01
4.828 | 8.414 | 6.828 | 5.828 | 8.242 | 10.242 | 8.414 | 14.242 | 22.484 | 32.726 | 4.828 | 8.424 | 6.828 | 5.828 | 8.242 | 10.242 | 8.424 | 14.252 | 22.494 | 32.736 | 0.01
4.4034 | 8.2017 | 6.4034 | 5.4034 | 7.6051 | 9.6051 | 8.2017 | 13.6051 | 21.2102 | 30.8153 | 4.4034 | 8.2117 | 6.4034 | 5.4034 | 7.6051 | 9.6051 | 8.2117 | 13.6151 | 21.2202 | 30.8253 | 0.01
4.8238 | 8.4119 | 6.8238 | 5.8238 | 8.2357 | 10.2357 | 8.4119 | 14.2357 | 22.4715 | 32.7072 | 4.8238 | 8.4219 | 6.8238 | 5.8238 | 8.2357 | 10.2357 | 8.4219 | 14.2457 | 22.4815 | 32.7172 | 0.01
2.2571 | 7.1285 | 4.2571 | 3.2571 | 4.3856 | 6.3856 | 7.1285 | 10.3856 | 14.7713 | 21.1569 | 2.2571 | 7.1385 | 4.2571 | 3.2571 | 4.3856 | 6.3856 | 7.1385 | 10.3956 | 14.7813 | 21.1669 | 0.01
7.5318 | 9.7659 | 9.5318 | 8.5318 | 12.2977 | 14.2977 | 9.7659 | 18.2977 | 30.5954 | 44.8931 | 7.5318 | 9.7759 | 9.5318 | 8.5318 | 12.2977 | 14.2977 | 9.7759 | 18.3077 | 30.6054 | 44.9031 | 0.01
5.7824 | 8.8912 | 7.7824 | 6.7824 | 9.6736 | 11.6736 | 8.8912 | 15.6736 | 25.3472 | 37.0208 | 5.7824 | 8.9012 | 7.7824 | 6.7824 | 9.6736 | 11.6736 | 8.9012 | 15.6836 | 25.3572 | 37.0308 | 0.01
5.2454 | 8.6227 | 7.2454 | 6.2454 | 8.8681 | 10.8681 | 8.6227 | 14.8681 | 23.7362 | 34.6043 | 5.2454 | 8.6327 | 7.2454 | 6.2454 | 8.8681 | 10.8681 | 8.6327 | 14.8781 | 23.7462 | 34.6143 | 0.01
4.8561 | 8.428 | 6.8561 | 5.8561 | 8.2841 | 10.2841 | 8.428 | 14.2841 | 22.5682 | 32.8522 | 4.8561 | 8.438 | 6.8561 | 5.8561 | 8.2841 | 10.2841 | 8.438 | 14.2941 | 22.5782 | 32.8622 | 0.01
8.4147 | 10.2073 | 10.4147 | 9.4147 | 13.622 | 15.622 | 10.2073 | 19.622 | 33.244 | 48.866 | 8.4147 | 10.2173 | 10.4147 | 9.4147 | 13.622 | 15.622 | 10.2173 | 19.632 | 33.254 | 48.876 | 0.01
6.6838 | 9.3419 | 8.6838 | 7.6838 | 11.0256 | 13.0256 | 9.3419 | 17.0256 | 28.0513 | 41.0769 | 6.6838 | 9.3519 | 8.6838 | 7.6838 | 11.0256 | 13.0256 | 9.3519 | 17.0356 | 28.0613 | 41.0869 | 0.01
0.96635 | 6.4832 | 2.9663 | 1.9663 | 2.4495 | 4.4495 | 6.4832 | 8.4495 | 10.899 | 15.3486 | 0.96635 | 6.4932 | 2.9663 | 1.9663 | 2.4495 | 4.4495 | 6.4932 | 8.4595 | 10.909 | 15.3586 | 0.01
7.0703 | 9.5351 | 9.0703 | 8.0703 | 11.6054 | 13.6054 | 9.5351 | 17.6054 | 29.2109 | 42.8163 | 7.0703 | 9.5451 | 9.0703 | 8.0703 | 11.6054 | 13.6054 | 9.5451 | 17.6154 | 29.2209 | 42.8263 | 0.01
7.017 | 9.5085 | 9.017 | 8.017 | 11.5255 | 13.5255 | 9.5085 | 17.5255 | 29.051 | 42.5765 | 7.017 | 9.5185 | 9.017 | 8.017 | 11.5255 | 13.5255 | 9.5185 | 17.5355 | 29.061 | 42.5865 | 0.01
5.4393 | 8.7196 | 7.4393 | 6.4393 | 9.1589 | 11.1589 | 8.7196 | 15.1589 | 24.3178 | 35.4767 | 5.4393 | 8.7296 | 7.4393 | 6.4393 | 9.1589 | 11.1589 | 8.7296 | 15.1689 | 24.3278 | 35.4867 | 0.01
2.5841 | 7.2921 | 4.5841 | 3.5841 | 4.8762 | 6.8762 | 7.2921 | 10.8762 | 15.7524 | 22.6286 | 2.5841 | 7.3021 | 4.5841 | 3.5841 | 4.8762 | 6.8762 | 7.3021 | 10.8862 | 15.7624 | 22.6386 | 0.01
3.8108 | 7.9054 | 5.8108 | 4.8108 | 6.7162 | 8.7162 | 7.9054 | 12.7162 | 19.4324 | 28.1486 | 3.8108 | 7.9154 | 5.8108 | 4.8108 | 6.7162 | 8.7162 | 7.9154 | 12.7262 | 19.4424 | 28.1586 | 0.01
5.3143 | 8.6572 | 7.3143 | 6.3143 | 8.9715 | 10.9715 | 8.6572 | 14.9715 | 23.9429 | 34.9144 | 5.3143 | 8.6672 | 7.3143 | 6.3143 | 8.9715 | 10.9715 | 8.6672 | 14.9815 | 23.9529 | 34.9244 | 0.01
6.6577 | 9.3288 | 8.6577 | 7.6577 | 10.9865 | 12.9865 | 9.3288 | 16.9865 | 27.9731 | 40.9596 | 6.6577 | 9.3388 | 8.6577 | 7.6577 | 10.9865 | 12.9865 | 9.3388 | 16.9965 | 27.9831 | 40.9696 | 0.01
3.0098 | 7.5049 | 5.0098 | 4.0098 | 5.5147 | 7.5147 | 7.5049 | 11.5147 | 17.0295 | 24.5442 | 3.0098 | 7.5149 | 5.0098 | 4.0098 | 5.5147 | 7.5147 | 7.5149 | 11.5247 | 17.0395 | 24.5542 | 0.01
5.1527 | 8.5764 | 7.1527 | 6.1527 | 8.7291 | 10.7291 | 8.5764 | 14.7291 | 23.4582 | 34.1873 | 5.1527 | 8.5864 | 7.1527 | 6.1527 | 8.7291 | 10.7291 | 8.5864 | 14.7391 | 23.4682 | 34.1973 | 0.01
5.8825 | 8.9413 | 7.8825 | 6.8825 | 9.8238 | 11.8238 | 8.9413 | 15.8238 | 25.6475 | 37.4713 | 5.8825 | 8.9513 | 7.8825 | 6.8825 | 9.8238 | 11.8238 | 8.9513 | 15.8338 | 25.6575 | 37.4813 | 0.01
6.6117 | 9.3058 | 8.6117 | 7.6117 | 10.9175 | 12.9175 | 9.3058 | 16.9175 | 27.835 | 40.7525 | 6.6117 | 9.3158 | 8.6117 | 7.6117 | 10.9175 | 12.9175 | 9.3158 | 16.9275 | 27.845 | 40.7625 | 0.01
7.5536 | 9.7768 | 9.5536 | 8.5536 | 12.3304 | 14.3304 | 9.7768 | 18.3304 | 30.6609 | 44.9913 | 7.5536 | 9.7868 | 9.5536 | 8.5536 | 12.3304 | 14.3304 | 9.7868 | 18.3404 | 30.6709 | 45.0013 | 0.01
3.9811 | 7.9905 | 5.9811 | 4.9811 | 6.9716 | 8.9716 | 7.9905 | 12.9716 | 19.9432 | 28.9148 | 3.9811 | 8.0005 | 5.9811 | 4.9811 | 6.9716 | 8.9716 | 8.0005 | 12.9816 | 19.9532 | 28.9248 | 0.01
2.7565 | 7.3783 | 4.7565 | 3.7565 | 5.1348 | 7.1348 | 7.3783 | 11.1348 | 16.2696 | 23.4044 | 2.7565 | 7.3883 | 4.7565 | 3.7565 | 5.1348 | 7.1348 | 7.3883 | 11.1448 | 16.2796 | 23.4144 | 0.01
1.279 | 6.6395 | 3.279 | 2.279 | 2.9185 | 4.9185 | 6.6395 | 8.9185 | 11.837 | 16.7555 | 1.279 | 6.6495 | 3.279 | 2.279 | 2.9185 | 4.9185 | 6.6495 | 8.9285 | 11.847 | 16.7655 | 0.01
6.3987 | 9.1993 | 8.3987 | 7.3987 | 10.598 | 12.598 | 9.1993 | 16.598 | 27.196 | 39.794 | 6.3987 | 9.2093 | 8.3987 | 7.3987 | 10.598 | 12.598 | 9.2093 | 16.608 | 27.206 | 39.804 | 0.01
8.8962 | 10.4481 | 10.8962 | 9.8962 | 14.3443 | 16.3443 | 10.4481 | 20.3443 | 34.6886 | 51.033 | 8.8962 | 10.4581 | 10.8962 | 9.8962 | 14.3443 | 16.3443 | 10.4581 | 20.3543 | 34.6986 | 51.043 | 0.01
3.2532 | 7.6266 | 5.2532 | 4.2532 | 5.8797 | 7.8797 | 7.6266 | 11.8797 | 17.7595 | 25.6392 | 3.2532 | 7.6366 | 5.2532 | 4.2532 | 5.8797 | 7.8797 | 7.6366 | 11.8897 | 17.7695 | 25.6492 | 0.01
5.4748 | 8.7374 | 7.4748 | 6.4748 | 9.2122 | 11.2122 | 8.7374 | 15.2122 | 24.4245 | 35.6367 | 5.4748 | 8.7474 | 7.4748 | 6.4748 | 9.2122 | 11.2122 | 8.7474 | 15.2222 | 24.4345 | 35.6467 | 0.01
5.6701 | 8.8351 | 7.6701 | 6.6701 | 9.5052 | 11.5052 | 8.8351 | 15.5052 | 25.0103 | 36.5155 | 5.6701 | 8.8451 | 7.6701 | 6.6701 | 9.5052 | 11.5052 | 8.8451 | 15.5152 | 25.0203 | 36.5255 | 0.01
8.5124 | 10.2562 | 10.5124 | 9.5124 | 13.7685 | 15.7685 | 10.2562 | 19.7685 | 33.5371 | 49.3056 | 8.5124 | 10.2662 | 10.5124 | 9.5124 | 13.7685 | 15.7685 | 10.2662 | 19.7785 | 33.5471 | 49.3156 | 0.01
7.7278 | 9.8639 | 9.7278 | 8.7278 | 12.5917 | 14.5917 | 9.8639 | 18.5917 | 31.1834 | 45.7751 | 7.7278 | 9.8739 | 9.7278 | 8.7278 | 12.5917 | 14.5917 | 9.8739 | 18.6017 | 31.1934 | 45.7851 | 0.01
6.6958 | 9.3479 | 8.6958 | 7.6958 | 11.0437 | 13.0437 | 9.3479 | 17.0437 | 28.0873 | 41.131 | 6.6958 | 9.3579 | 8.6958 | 7.6958 | 11.0437 | 13.0437 | 9.3579 | 17.0537 | 28.0973 | 41.141 | 0.01
6.6747 | 9.3373 | 8.6747 | 7.6747 | 11.012 | 13.012 | 9.3373 | 17.012 | 28.024 | 41.036 | 6.6747 | 9.3473 | 8.6747 | 7.6747 | 11.012 | 13.012 | 9.3473 | 17.022 | 28.034 | 41.046 | 0.01
4.1136 | 8.0568 | 6.1136 | 5.1136 | 7.1705 | 9.1705 | 8.0568 | 13.1705 | 20.3409 | 29.5114 | 4.1136 | 8.0668 | 6.1136 | 5.1136 | 7.1705 | 9.1705 | 8.0668 | 13.1805 | 20.3509 | 29.5214 | 0.01
6.0322 | 9.0161 | 8.0322 | 7.0322 | 10.0483 | 12.0483 | 9.0161 | 16.0483 | 26.0966 | 38.1449 | 6.0322 | 9.0261 | 8.0322 | 7.0322 | 10.0483 | 12.0483 | 9.0261 | 16.0583 | 26.1066 | 38.1549 | 0.01
6.0533 | 9.0267 | 8.0533 | 7.0533 | 10.08 | 12.08 | 9.0267 | 16.08 | 26.16 | 38.24 | 6.0533 | 9.0367 | 8.0533 | 7.0533 | 10.08 | 12.08 | 9.0367 | 16.09 | 26.17 | 38.25 | 0.01
5.3099 | 8.655 | 7.3099 | 6.3099 | 8.9649 | 10.9649 | 8.655 | 14.9649 | 23.9298 | 34.8946 | 5.3099 | 8.665 | 7.3099 | 6.3099 | 8.9649 | 10.9649 | 8.665 | 14.9749 | 23.9398 | 34.9046 | 0.01
2.783 | 7.3915 | 4.783 | 3.783 | 5.1746 | 7.1746 | 7.3915 | 11.1746 | 16.3491 | 23.5237 | 2.783 | 7.4015 | 4.783 | 3.783 | 5.1746 | 7.1746 | 7.4015 | 11.1846 | 16.3591 | 23.5337 | 0.01
4.1082 | 8.0541 | 6.1082 | 5.1082 | 7.1622 | 9.1622 | 8.0541 | 13.1622 | 20.3245 | 29.4867 | 4.1082 | 8.0641 | 6.1082 | 5.1082 | 7.1622 | 9.1622 | 8.0641 | 13.1722 | 20.3345 | 29.4967 | 0.01
9.1167 | 10.5584 | 11.1167 | 10.1167 | 14.6751 | 16.6751 | 10.5584 | 20.6751 | 35.3502 | 52.0254 | 9.1167 | 10.5684 | 11.1167 | 10.1167 | 14.6751 | 16.6751 | 10.5684 | 20.6851 | 35.3602 | 52.0354 | 0.01
7.2546 | 9.6273 | 9.2546 | 8.2546 | 11.8819 | 13.8819 | 9.6273 | 17.8819 | 29.7637 | 43.6456 | 7.2546 | 9.6373 | 9.2546 | 8.2546 | 11.8819 | 13.8819 | 9.6373 | 17.8919 | 29.7737 | 43.6556 | 0.01
3.9195 | 7.9598 | 5.9195 | 4.9195 | 6.8793 | 8.8793 | 7.9598 | 12.8793 | 19.7585 | 28.6378 | 3.9195 | 7.9698 | 5.9195 | 4.9195 | 6.8793 | 8.8793 | 7.9698 | 12.8893 | 19.7685 | 28.6478 | 0.01
7.2151 | 9.6076 | 9.2151 | 8.2151 | 11.8227 | 13.8227 | 9.6076 | 17.8227 | 29.6454 | 43.4681 | 7.2151 | 9.6176 | 9.2151 | 8.2151 | 11.8227 | 13.8227 | 9.6176 | 17.8327 | 29.6554 | 43.4781 | 0.01
5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 5.3943 | 8.7071 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.7071 | 15.1014 | 24.1928 | 35.2841 | 0.01
4.1806 | 8.0903 | 6.1806 | 5.1806 | 7.2709 | 9.2709 | 8.0903 | 13.2709 | 20.5419 | 29.8128 | 4.1806 | 8.1003 | 6.1806 | 5.1806 | 7.2709 | 9.2709 | 8.1003 | 13.2809 | 20.5519 | 29.8228 | 0.01
4.4304 | 8.2152 | 6.4304 | 5.4304 | 7.6456 | 9.6456 | 8.2152 | 13.6456 | 21.2912 | 30.9368 | 4.4304 | 8.2252 | 6.4304 | 5.4304 | 7.6456 | 9.6456 | 8.2252 | 13.6556 | 21.3012 | 30.9468 | 0.01
4.0583 | 8.0291 | 6.0583 | 5.0583 | 7.0874 | 9.0874 | 8.0291 | 13.0874 | 20.1748 | 29.2622 | 4.0583 | 8.0391 | 6.0583 | 5.0583 | 7.0874 | 9.0874 | 8.0391 | 13.0974 | 20.1848 | 29.2722 | 0.01
6.3386 | 9.1693 | 8.3386 | 7.3386 | 10.5079 | 12.5079 | 9.1693 | 16.5079 | 27.0158 | 39.5236 | 6.3386 | 9.1793 | 8.3386 | 7.3386 | 10.5079 | 12.5079 | 9.1793 | 16.5179 | 27.0258 | 39.5336 | 0.01
8.3318 | 10.1659 | 10.3318 | 9.3318 | 13.4977 | 15.4977 | 10.1659 | 19.4977 | 32.9953 | 48.493 | 8.3318 | 10.1759 | 10.3318 | 9.3318 | 13.4977 | 15.4977 | 10.1759 | 19.5077 | 33.0053 | 48.503 | 0.01
3.4866 | 7.7433 | 5.4866 | 4.4866 | 6.23 | 8.23 | 7.7433 | 12.23 | 18.4599 | 26.6899 | 3.4866 | 7.7533 | 5.4866 | 4.4866 | 6.23 | 8.23 | 7.7533 | 12.24 | 18.4699 | 26.6999 | 0.01
5.145 | 8.5725 | 7.145 | 6.145 | 8.7175 | 10.7175 | 8.5725 | 14.7175 | 23.4351 | 34.1526 | 5.145 | 8.5825 | 7.145 | 6.145 | 8.7175 | 10.7175 | 8.5825 | 14.7275 | 23.4451 | 34.1626 | 0.01
4.7066 | 8.3533 | 6.7066 | 5.7066 | 8.06 | 10.06 | 8.3533 | 14.06 | 22.1199 | 32.1799 | 4.7066 | 8.3633 | 6.7066 | 5.7066 | 8.06 | 10.06 | 8.3633 | 14.07 | 22.1299 | 32.1899 | 0.01
3.6298 | 7.8149 | 5.6298 | 4.6298 | 6.4446 | 8.4446 | 7.8149 | 12.4446 | 18.8893 | 27.3339 | 3.6298 | 7.8249 | 5.6298 | 4.6298 | 6.4446 | 8.4446 | 7.8249 | 12.4546 | 18.8993 | 27.3439 | 0.01
7.1394 | 9.5697 | 9.1394 | 8.1394 | 11.7092 | 13.7092 | 9.5697 | 17.7092 | 29.4183 | 43.1275 | 7.1394 | 9.5797 | 9.1394 | 8.1394 | 11.7092 | 13.7092 | 9.5797 | 17.7192 | 29.4283 | 43.1375 | 0.01
6.9539 | 9.477 | 8.9539 | 7.9539 | 11.4309 | 13.4309 | 9.477 | 17.4309 | 28.8618 | 42.2928 | 6.9539 | 9.487 | 8.9539 | 7.9539 | 11.4309 | 13.4309 | 9.487 | 17.4409 | 28.8718 | 42.3028 | 0.01
3.8824 | 7.9412 | 5.8824 | 4.8824 | 6.8235 | 8.8235 | 7.9412 | 12.8235 | 19.6471 | 28.4706 | 3.8824 | 7.9512 | 5.8824 | 4.8824 | 6.8235 | 8.8235 | 7.9512 | 12.8335 | 19.6571 | 28.4806 | 0.01
4.5081 | 8.2541 | 6.5081 | 5.5081 | 7.7622 | 9.7622 | 8.2541 | 13.7622 | 21.5243 | 31.2865 | 4.5081 | 8.2641 | 6.5081 | 5.5081 | 7.7622 | 9.7622 | 8.2641 | 13.7722 | 21.5343 | 31.2965 | 0.01
5.4401 | 8.72 | 7.4401 | 6.4401 | 9.1601 | 11.1601 | 8.72 | 15.1601 | 24.3202 | 35.4803 | 5.4401 | 8.73 | 7.4401 | 6.4401 | 9.1601 | 11.1601 | 8.73 | 15.1701 | 24.3302 | 35.4903 | 0.01
7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 7.2212 | 9.6206 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6206 | 17.8418 | 29.6736 | 43.5055 | 0.01
6.3068 | 9.1534 | 8.3068 | 7.3068 | 10.4602 | 12.4602 | 9.1534 | 16.4602 | 26.9204 | 39.3807 | 6.3068 | 9.1634 | 8.3068 | 7.3068 | 10.4602 | 12.4602 | 9.1634 | 16.4702 | 26.9304 | 39.3907 | 0.01
2.4541 | 7.227 | 4.4541 | 3.4541 | 4.6811 | 6.6811 | 7.227 | 10.6811 | 15.3622 | 22.0434 | 2.4541 | 7.237 | 4.4541 | 3.4541 | 4.6811 | 6.6811 | 7.237 | 10.6911 | 15.3722 | 22.0534 | 0.01
6.616 | 9.308 | 8.616 | 7.616 | 10.924 | 12.924 | 9.308 | 16.924 | 27.848 | 40.772 | 6.616 | 9.318 | 8.616 | 7.616 | 10.924 | 12.924 | 9.318 | 16.934 | 27.858 | 40.782 | 0.01
6.1816 | 9.0908 | 8.1816 | 7.1816 | 10.2724 | 12.2724 | 9.0908 | 16.2724 | 26.5449 | 38.8173 | 6.1816 | 9.1008 | 8.1816 | 7.1816 | 10.2724 | 12.2724 | 9.1008 | 16.2824 | 26.5549 | 38.8273 | 0.01
4.1669 | 8.0835 | 6.1669 | 5.1669 | 7.2504 | 9.2504 | 8.0835 | 13.2504 | 20.5008 | 29.7512 | 4.1669 | 8.0935 | 6.1669 | 5.1669 | 7.2504 | 9.2504 | 8.0935 | 13.2604 | 20.5108 | 29.7612 | 0.01
5.6994 | 8.8497 | 7.6994 | 6.6994 | 9.5491 | 11.5491 | 8.8497 | 15.5491 | 25.0981 | 36.6472 | 5.6994 | 8.8597 | 7.6994 | 6.6994 | 9.5491 | 11.5491 | 8.8597 | 15.5591 | 25.1081 | 36.6572 | 0.01
6.0425 | 9.0212 | 8.0425 | 7.0425 | 10.0637 | 12.0637 | 9.0212 | 16.0637 | 26.1274 | 38.1911 | 6.0425 | 9.0312 | 8.0425 | 7.0425 | 10.0637 | 12.0637 | 9.0312 | 16.0737 | 26.1374 | 38.2011 | 0.01
10.3015 | 11.1508 | 12.3015 | 11.3015 | 16.4523 | 18.4523 | 11.1508 | 22.4523 | 38.9045 | 57.3568 | 10.3015 | 11.1608 | 12.3015 | 11.3015 | 16.4523 | 18.4523 | 11.1608 | 22.4623 | 38.9145 | 57.3668 | 0.01
5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 5.0973 | 8.5587 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5587 | 14.656 | 23.302 | 33.9481 | 0.01
2.9544 | 7.4772 | 4.9544 | 3.9544 | 5.4316 | 7.4316 | 7.4772 | 11.4316 | 16.8633 | 24.2949 | 2.9544 | 7.4872 | 4.9544 | 3.9544 | 5.4316 | 7.4316 | 7.4872 | 11.4416 | 16.8733 | 24.3049 | 0.01
8.086 | 10.043 | 10.086 | 9.086 | 13.129 | 15.129 | 10.043 | 19.129 | 32.258 | 47.3871 | 8.086 | 10.053 | 10.086 | 9.086 | 13.129 | 15.129 | 10.053 | 19.139 | 32.268 | 47.3971 | 0.01
3.5671 | 7.7836 | 5.5671 | 4.5671 | 6.3507 | 8.3507 | 7.7836 | 12.3507 | 18.7014 | 27.0522 | 3.5671 | 7.7936 | 5.5671 | 4.5671 | 6.3507 | 8.3507 | 7.7936 | 12.3607 | 18.7114 | 27.0622 | 0.01
3.1336 | 7.5668 | 5.1336 | 4.1336 | 5.7004 | 7.7004 | 7.5668 | 11.7004 | 17.4008 | 25.1012 | 3.1336 | 7.5768 | 5.1336 | 4.1336 | 5.7004 | 7.7004 | 7.5768 | 11.7104 | 17.4108 | 25.1112 | 0.01
6.5277 | 9.2639 | 8.5277 | 7.5277 | 10.7916 | 12.7916 | 9.2639 | 16.7916 | 27.5831 | 40.3747 | 6.5277 | 9.2739 | 8.5277 | 7.5277 | 10.7916 | 12.7916 | 9.2739 | 16.8016 | 27.5931 | 40.3847 | 0.01
4.9065 | 8.4533 | 6.9065 | 5.9065 | 8.3598 | 10.3598 | 8.4533 | 14.3598 | 22.7195 | 33.0793 | 4.9065 | 8.4633 | 6.9065 | 5.9065 | 8.3598 | 10.3598 | 8.4633 | 14.3698 | 22.7295 | 33.0893 | 0.01
5.0165 | 8.5082 | 7.0165 | 6.0165 | 8.5247 | 10.5247 | 8.5082 | 14.5247 | 23.0494 | 33.5741 | 5.0165 | 8.5182 | 7.0165 | 6.0165 | 8.5247 | 10.5247 | 8.5182 | 14.5347 | 23.0594 | 33.5841 | 0.01
7.6593 | 9.8296 | 9.6593 | 8.6593 | 12.4889 | 14.4889 | 9.8296 | 18.4889 | 30.9778 | 45.4666 | 7.6593 | 9.8396 | 9.6593 | 8.6593 | 12.4889 | 14.4889 | 9.8396 | 18.4989 | 30.9878 | 45.4766 | 0.01
7.9067 | 9.9534 | 9.9067 | 8.9067 | 12.8601 | 14.8601 | 9.9534 | 18.8601 | 31.7202 | 46.5803 | 7.9067 | 9.9634 | 9.9067 | 8.9067 | 12.8601 | 14.8601 | 9.9634 | 18.8701 | 31.7302 | 46.5903 | 0.01
5.5669 | 8.7835 | 7.5669 | 6.5669 | 9.3504 | 11.3504 | 8.7835 | 15.3504 | 24.7008 | 36.0513 | 5.5669 | 8.7935 | 7.5669 | 6.5669 | 9.3504 | 11.3504 | 8.7935 | 15.3604 | 24.7108 | 36.0613 | 0.01
6.8194 | 9.4097 | 8.8194 | 7.8194 | 11.2291 | 13.2291 | 9.4097 | 17.2291 | 28.4582 | 41.6873 | 6.8194 | 9.4197 | 8.8194 | 7.8194 | 11.2291 | 13.2291 | 9.4197 | 17.2391 | 28.4682 | 41.6973 | 0.01
4.8316 | 8.4158 | 6.8316 | 5.8316 | 8.2475 | 10.2475 | 8.4158 | 14.2475 | 22.4949 | 32.7424 | 4.8316 | 8.4258 | 6.8316 | 5.8316 | 8.2475 | 10.2475 | 8.4258 | 14.2575 | 22.5049 | 32.7524 | 0.01
7.73 | 9.865 | 9.73 | 8.73 | 12.595 | 14.595 | 9.865 | 18.595 | 31.19 | 45.785 | 7.73 | 9.875 | 9.73 | 8.73 | 12.595 | 14.595 | 9.875 | 18.605 | 31.2 | 45.795 | 0.01
4.3301 | 8.1651 | 6.3301 | 5.3301 | 7.4952 | 9.4952 | 8.1651 | 13.4952 | 20.9904 | 30.4857 | 4.3301 | 8.1751 | 6.3301 | 5.3301 | 7.4952 | 9.4952 | 8.1751 | 13.5052 | 21.0004 | 30.4957 | 0.01
4.0174 | 8.0087 | 6.0174 | 5.0174 | 7.0261 | 9.0261 | 8.0087 | 13.0261 | 20.0522 | 29.0784 | 4.0174 | 8.0187 | 6.0174 | 5.0174 | 7.0261 | 9.0261 | 8.0187 | 13.0361 | 20.0622 | 29.0884 | 0.01
3.7223 | 7.8612 | 5.7223 | 4.7223 | 6.5835 | 8.5835 | 7.8612 | 12.5835 | 19.1669 | 27.7504 | 3.7223 | 7.8712 | 5.7223 | 4.7223 | 6.5835 | 8.5835 | 7.8712 | 12.5935 | 19.1769 | 27.7604 | 0.01
5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 5.2901 | 8.655 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.655 | 14.9451 | 23.8802 | 34.8153 | 0.01
7.4619 | 9.731 | 9.4619 | 8.4619 | 12.1929 | 14.1929 | 9.731 | 18.1929 | 30.3858 | 44.5787 | 7.4619 | 9.741 | 9.4619 | 8.4619 | 12.1929 | 14.1929 | 9.741 | 18.2029 | 30.3958 | 44.5887 | 0.01
4.2939 | 8.1469 | 6.2939 | 5.2939 | 7.4408 | 9.4408 | 8.1469 | 13.4408 | 20.8817 | 30.3225 | 4.2939 | 8.1569 | 6.2939 | 5.2939 | 7.4408 | 9.4408 | 8.1569 | 13.4508 | 20.8917 | 30.3325 | 0.01
6.2435 | 9.1217 | 8.2435 | 7.2435 | 10.3652 | 12.3652 | 9.1217 | 16.3652 | 26.7304 | 39.0957 | 6.2435 | 9.1317 | 8.2435 | 7.2435 | 10.3652 | 12.3652 | 9.1317 | 16.3752 | 26.7404 | 39.1057 | 0.01
5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 5.0921 | 8.556 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.556 | 14.6481 | 23.2863 | 33.9244 | 0.01
7.367 | 9.6835 | 9.367 | 8.367 | 12.0506 | 14.0506 | 9.6835 | 18.0506 | 30.1011 | 44.1517 | 7.367 | 9.6935 | 9.367 | 8.367 | 12.0506 | 14.0506 | 9.6935 | 18.0606 | 30.1111 | 44.1617 | 0.01
9.1555 | 10.5777 | 11.1555 | 10.1555 | 14.7332 | 16.7332 | 10.5777 | 20.7332 | 35.4664 | 52.1996 | 9.1555 | 10.5877 | 11.1555 | 10.1555 | 14.7332 | 16.7332 | 10.5877 | 20.7432 | 35.4764 | 52.2096 | 0.01
4.4266 | 8.2133 | 6.4266 | 5.4266 | 7.64 | 9.64 | 8.2133 | 13.64 | 21.2799 | 30.9199 | 4.4266 | 8.2233 | 6.4266 | 5.4266 | 7.64 | 9.64 | 8.2233 | 13.65 | 21.2899 | 30.9299 | 0.01
6.4001 | 9.2 | 8.4001 | 7.4001 | 10.6001 | 12.6001 | 9.2 | 16.6001 | 27.2002 | 39.8003 | 6.4001 | 9.21 | 8.4001 | 7.4001 | 10.6001 | 12.6001 | 9.21 | 16.6101 | 27.2102 | 39.8103 | 0.01
5.0045 | 8.5023 | 7.0045 | 6.0045 | 8.5068 | 10.5068 | 8.5023 | 14.5068 | 23.0136 | 33.5204 | 5.0045 | 8.5123 | 7.0045 | 6.0045 | 8.5068 | 10.5068 | 8.5123 | 14.5168 | 23.0236 | 33.5304 | 0.01
2.7353 | 7.3676 | 4.7353 | 3.7353 | 5.1029 | 7.1029 | 7.3676 | 11.1029 | 16.2058 | 23.3088 | 2.7353 | 7.3776 | 4.7353 | 3.7353 | 5.1029 | 7.1029 | 7.3776 | 11.1129 | 16.2158 | 23.3188 | 0.01
5.211 | 8.6055 | 7.211 | 6.211 | 8.8164 | 10.8164 | 8.6055 | 14.8164 | 23.6329 | 34.4493 | 5.211 | 8.6155 | 7.211 | 6.211 | 8.8164 | 10.8164 | 8.6155 | 14.8264 | 23.6429 | 34.4593 | 0.01
5.7148 | 8.8574 | 7.7148 | 6.7148 | 9.5723 | 11.5723 | 8.8574 | 15.5723 | 25.1445 | 36.7168 | 5.7148 | 8.8674 | 7.7148 | 6.7148 | 9.5723 | 11.5723 | 8.8674 | 15.5823 | 25.1545 | 36.7268 | 0.01
2.991 | 7.4955 | 4.991 | 3.991 | 5.4865 | 7.4865 | 7.4955 | 11.4865 | 16.9729 | 24.4594 | 2.991 | 7.5055 | 4.991 | 3.991 | 5.4865 | 7.4865 | 7.5055 | 11.4965 | 16.9829 | 24.4694 | 0.01
5.3673 | 8.6836 | 7.3673 | 6.3673 | 9.0509 | 11.0509 | 8.6836 | 15.0509 | 24.1019 | 35.1528 | 5.3673 | 8.6936 | 7.3673 | 6.3673 | 9.0509 | 11.0509 | 8.6936 | 15.0609 | 24.1119 | 35.1628 | 0.01
6.8222 | 9.4111 | 8.8222 | 7.8222 | 11.2333 | 13.2333 | 9.4111 | 17.2333 | 28.4667 | 41.7 | 6.8222 | 9.4211 | 8.8222 | 7.8222 | 11.2333 | 13.2333 | 9.4211 | 17.2433 | 28.4767 | 41.71 | 0.01
5.639 | 8.8195 | 7.639 | 6.639 | 9.4586 | 11.4586 | 8.8195 | 15.4586 | 24.9171 | 36.3757 | 5.639 | 8.8295 | 7.639 | 6.639 | 9.4586 | 11.4586 | 8.8295 | 15.4686 | 24.9271 | 36.3857 | 0.01
10.6751 | 11.3376 | 12.6751 | 11.6751 | 17.0127 | 19.0127 | 11.3376 | 23.0127 | 40.0254 | 59.0381 | 10.6751 | 11.3476 | 12.6751 | 11.6751 | 17.0127 | 19.0127 | 11.3476 | 23.0227 | 40.0354 | 59.0481 | 0.01
1.6411 | 6.8205 | 3.6411 | 2.6411 | 3.4616 | 5.4616 | 6.8205 | 9.4616 | 12.9232 | 18.3849 | 1.6411 | 6.8305 | 3.6411 | 2.6411 | 3.4616 | 5.4616 | 6.8305 | 9.4716 | 12.9332 | 18.3949 | 0.01
5.3028 | 8.6514 | 7.3028 | 6.3028 | 8.9542 | 10.9542 | 8.6514 | 14.9542 | 23.9083 | 34.8625 | 5.3028 | 8.6614 | 7.3028 | 6.3028 | 8.9542 | 10.9542 | 8.6614 | 14.9642 | 23.9183 | 34.8725 | 0.01
8.489 | 10.2445 | 10.489 | 9.489 | 13.7334 | 15.7334 | 10.2445 | 19.7334 | 33.4669 | 49.2003 | 8.489 | 10.2545 | 10.489 | 9.489 | 13.7334 | 15.7334 | 10.2545 | 19.7434 | 33.4769 | 49.2103 | 0.01
6.2238 | 9.1119 | 8.2238 | 7.2238 | 10.3356 | 12.3356 | 9.1119 | 16.3356 | 26.6713 | 39.0069 | 6.2238 | 9.1219 | 8.2238 | 7.2238 | 10.3356 | 12.3356 | 9.1219 | 16.3456 | 26.6813 | 39.0169 | 0.01
5.7985 | 8.8993 | 7.7985 | 6.7985 | 9.6978 | 11.6978 | 8.8993 | 15.6978 | 25.3956 | 37.0935 | 5.7985 | 8.9093 | 7.7985 | 6.7985 | 9.6978 | 11.6978 | 8.9093 | 15.7078 | 25.4056 | 37.1035 | 0.01
7.9791 | 9.9895 | 9.9791 | 8.9791 | 12.9686 | 14.9686 | 9.9895 | 18.9686 | 31.9373 | 46.9059 | 7.9791 | 9.9995 | 9.9791 | 8.9791 | 12.9686 | 14.9686 | 9.9995 | 18.9786 | 31.9473 | 46.9159 | 0.01
6.6718 | 9.3359 | 8.6718 | 7.6718 | 11.0076 | 13.0076 | 9.3359 | 17.0076 | 28.0153 | 41.0229 | 6.6718 | 9.3459 | 8.6718 | 7.6718 | 11.0076 | 13.0076 | 9.3459 | 17.0176 | 28.0253 | 41.0329 | 0.01
2.7548 | 7.3774 | 4.7548 | 3.7548 | 5.1322 | 7.1322 | 7.3774 | 11.1322 | 16.2645 | 23.3967 | 2.7548 | 7.3874 | 4.7548 | 3.7548 | 5.1322 | 7.1322 | 7.3874 | 11.1422 | 16.2745 | 23.4067 | 0.01
3.7539 | 7.877 | 5.7539 | 4.7539 | 6.6309 | 8.6309 | 7.877 | 12.6309 | 19.2618 | 27.8927 | 3.7539 | 7.887 | 5.7539 | 4.7539 | 6.6309 | 8.6309 | 7.887 | 12.6409 | 19.2718 | 27.9027 | 0.01
4.0079 | 8.0039 | 6.0079 | 5.0079 | 7.0118 | 9.0118 | 8.0039 | 13.0118 | 20.0237 | 29.0355 | 4.0079 | 8.0139 | 6.0079 | 5.0079 | 7.0118 | 9.0118 | 8.0139 | 13.0218 | 20.0337 | 29.0455 | 0.01
8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 8.8231 | 10.4215 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4215 | 20.2446 | 34.4792 | 50.7139 | 0.01
6.8933 | 9.4467 | 8.8933 | 7.8933 | 11.34 | 13.34 | 9.4467 | 17.34 | 28.68 | 42.0201 | 6.8933 | 9.4567 | 8.8933 | 7.8933 | 11.34 | 13.34 | 9.4567 | 17.35 | 28.69 | 42.0301 | 0.01
3.0902 | 7.5451 | 5.0902 | 4.0902 | 5.6353 | 7.6353 | 7.5451 | 11.6353 | 17.2706 | 24.9059 | 3.0902 | 7.5551 | 5.0902 | 4.0902 | 5.6353 | 7.6353 | 7.5551 | 11.6453 | 17.2806 | 24.9159 | 0.01
3.6821 | 7.841 | 5.6821 | 4.6821 | 6.5231 | 8.5231 | 7.841 | 12.5231 | 19.0462 | 27.5692 | 3.6821 | 7.851 | 5.6821 | 4.6821 | 6.5231 | 8.5231 | 7.851 | 12.5331 | 19.0562 | 27.5792 | 0.01
3.021 | 7.5105 | 5.021 | 4.021 | 5.5315 | 7.5315 | 7.5105 | 11.5315 | 17.063 | 24.5945 | 3.021 | 7.5205 | 5.021 | 4.021 | 5.5315 | 7.5315 | 7.5205 | 11.5415 | 17.073 | 24.6045 | 0.01
8.4728 | 10.2364 | 10.4728 | 9.4728 | 13.7092 | 15.7092 | 10.2364 | 19.7092 | 33.4183 | 49.1275 | 8.4728 | 10.2464 | 10.4728 | 9.4728 | 13.7092 | 15.7092 | 10.2464 | 19.7192 | 33.4283 | 49.1375 | 0.01
3.493 | 7.7465 | 5.493 | 4.493 | 6.2395 | 8.2395 | 7.7465 | 12.2395 | 18.4791 | 26.7186 | 3.493 | 7.7565 | 5.493 | 4.493 | 6.2395 | 8.2395 | 7.7565 | 12.2495 | 18.4891 | 26.7286 | 0.01
9.0142 | 10.5071 | 11.0142 | 10.0142 | 14.5214 | 16.5214 | 10.5071 | 20.5214 | 35.0427 | 51.5641 | 9.0142 | 10.5171 | 11.0142 | 10.0142 | 14.5214 | 16.5214 | 10.5171 | 20.5314 | 35.0527 | 51.5741 | 0.01
10.0246 | 11.0123 | 12.0246 | 11.0246 | 16.0368 | 18.0368 | 11.0123 | 22.0368 | 38.0737 | 56.1105 | 10.0246 | 11.0223 | 12.0246 | 11.0246 | 16.0368 | 18.0368 | 11.0223 | 22.0468 | 38.0837 | 56.1205 | 0.01
9.1517 | 10.5759 | 11.1517 | 10.1517 | 14.7276 | 16.7276 | 10.5759 | 20.7276 | 35.4552 | 52.1829 | 9.1517 | 10.5859 | 11.1517 | 10.1517 | 14.7276 | 16.7276 | 10.5859 | 20.7376 | 35.4652 | 52.1929 | 0.01
4.2742 | 8.1371 | 6.2742 | 5.2742 | 7.4113 | 9.4113 | 8.1371 | 13.4113 | 20.8226 | 30.2339 | 4.2742 | 8.1471 | 6.2742 | 5.2742 | 7.4113 | 9.4113 | 8.1471 | 13.4213 | 20.8326 | 30.2439 | 0.01
4.3436 | 8.1718 | 6.3436 | 5.3436 | 7.5153 | 9.5153 | 8.1718 | 13.5153 | 21.0307 | 30.546 | 4.3436 | 8.1818 | 6.3436 | 5.3436 | 7.5153 | 9.5153 | 8.1818 | 13.5253 | 21.0407 | 30.556 | 0.01
7.5365 | 9.7683 | 9.5365 | 8.5365 | 12.3048 | 14.3048 | 9.7683 | 18.3048 | 30.6095 | 44.9143 | 7.5365 | 9.7783 | 9.5365 | 8.5365 | 12.3048 | 14.3048 | 9.7783 | 18.3148 | 30.6195 | 44.9243 | 0.01
2.6661 | 7.333 | 4.6661 | 3.6661 | 4.9991 | 6.9991 | 7.333 | 10.9991 | 15.9983 | 22.9974 | 2.6661 | 7.343 | 4.6661 | 3.6661 | 4.9991 | 6.9991 | 7.343 | 11.0091 | 16.0083 | 23.0074 | 0.01
5.1754 | 8.5877 | 7.1754 | 6.1754 | 8.7632 | 10.7632 | 8.5877 | 14.7632 | 23.5263 | 34.2895 | 5.1754 | 8.5977 | 7.1754 | 6.1754 | 8.7632 | 10.7632 | 8.5977 | 14.7732 | 23.5363 | 34.2995 | 0.01
5.602 | 8.801 | 7.602 | 6.602 | 9.4029 | 11.4029 | 8.801 | 15.4029 | 24.8059 | 36.2088 | 5.602 | 8.811 | 7.602 | 6.602 | 9.4029 | 11.4029 | 8.811 | 15.4129 | 24.8159 | 36.2188 | 0.01
2.4497 | 7.2248 | 4.4497 | 3.4497 | 4.6745 | 6.6745 | 7.2248 | 10.6745 | 15.349 | 22.0234 | 2.4497 | 7.2348 | 4.4497 | 3.4497 | 4.6745 | 6.6745 | 7.2348 | 10.6845 | 15.359 | 22.0334 | 0.01
8.632 | 10.316 | 10.632 | 9.632 | 13.948 | 15.948 | 10.316 | 19.948 | 33.8959 | 49.8439 | 8.632 | 10.326 | 10.632 | 9.632 | 13.948 | 15.948 | 10.326 | 19.958 | 33.9059 | 49.8539 | 0.01
7.3605 | 9.6802 | 9.3605 | 8.3605 | 12.0407 | 14.0407 | 9.6802 | 18.0407 | 30.0814 | 44.1221 | 7.3605 | 9.6902 | 9.3605 | 8.3605 | 12.0407 | 14.0407 | 9.6902 | 18.0507 | 30.0914 | 44.1321 | 0.01
6.2503 | 9.1251 | 8.2503 | 7.2503 | 10.3754 | 12.3754 | 9.1251 | 16.3754 | 26.7508 | 39.1262 | 6.2503 | 9.1351 | 8.2503 | 7.2503 | 10.3754 | 12.3754 | 9.1351 | 16.3854 | 26.7608 | 39.1362 | 0.01
6.4729 | 9.2365 | 8.4729 | 7.4729 | 10.7094 | 12.7094 | 9.2365 | 16.7094 | 27.4188 | 40.1282 | 6.4729 | 9.2465 | 8.4729 | 7.4729 | 10.7094 | 12.7094 | 9.2465 | 16.7194 | 27.4288 | 40.1382 | 0.01
5.0375 | 8.5187 | 7.0375 | 6.0375 | 8.5562 | 10.5562 | 8.5187 | 14.5562 | 23.1124 | 33.6686 | 5.0375 | 8.5287 | 7.0375 | 6.0375 | 8.5562 | 10.5562 | 8.5287 | 14.5662 | 23.1224 | 33.6786 | 0.01
6.4828 | 9.2414 | 8.4828 | 7.4828 | 10.7243 | 12.7243 | 9.2414 | 16.7243 | 27.4485 | 40.1728 | 6.4828 | 9.2514 | 8.4828 | 7.4828 | 10.7243 | 12.7243 | 9.2514 | 16.7343 | 27.4585 | 40.1828 | 0.01
8.6636 | 10.3318 | 10.6636 | 9.6636 | 13.9954 | 15.9954 | 10.3318 | 19.9954 | 33.9908 | 49.9862 | 8.6636 | 10.3418 | 10.6636 | 9.6636 | 13.9954 | 15.9954 | 10.3418 | 20.0054 | 34.0008 | 49.9962 | 0.01
6.1928 | 9.0964 | 8.1928 | 7.1928 | 10.2893 | 12.2893 | 9.0964 | 16.2893 | 26.5785 | 38.8678 | 6.1928 | 9.1064 | 8.1928 | 7.1928 | 10.2893 | 12.2893 | 9.1064 | 16.2993 | 26.5885 | 38.8778 | 0.01
5.2215 | 8.6108 | 7.2215 | 6.2215 | 8.8323 | 10.8323 | 8.6108 | 14.8323 | 23.6646 | 34.4969 | 5.2215 | 8.6208 | 7.2215 | 6.2215 | 8.8323 | 10.8323 | 8.6208 | 14.8423 | 23.6746 | 34.5069 | 0.01
3.3861 | 7.693 | 5.3861 | 4.3861 | 6.0791 | 8.0791 | 7.693 | 12.0791 | 18.1583 | 26.2374 | 3.3861 | 7.703 | 5.3861 | 4.3861 | 6.0791 | 8.0791 | 7.703 | 12.0891 | 18.1683 | 26.2474 | 0.01
10.7513 | 11.3757 | 12.7513 | 11.7513 | 17.127 | 19.127 | 11.3757 | 23.127 | 40.2539 | 59.3809 | 10.7513 | 11.3857 | 12.7513 | 11.7513 | 17.127 | 19.127 | 11.3857 | 23.137 | 40.2639 | 59.3909 | 0.01
5.4192 | 8.7096 | 7.4192 | 6.4192 | 9.1288 | 11.1288 | 8.7096 | 15.1288 | 24.2576 | 35.3864 | 5.4192 | 8.7196 | 7.4192 | 6.4192 | 9.1288 | 11.1288 | 8.7196 | 15.1388 | 24.2676 | 35.3964 | 0.01
10.2533 | 11.1267 | 12.2533 | 11.2533 | 16.38 | 18.38 | 11.1267 | 22.38 | 38.7599 | 57.1399 | 10.2533 | 11.1367 | 12.2533 | 11.2533 | 16.38 | 18.38 | 11.1367 | 22.39 | 38.7699 | 57.1499 | 0.01
4.7906 | 8.3953 | 6.7906 | 5.7906 | 8.1858 | 10.1858 | 8.3953 | 14.1858 | 22.3717 | 32.5575 | 4.7906 | 8.4053 | 6.7906 | 5.7906 | 8.1858 | 10.1858 | 8.4053 | 14.1958 | 22.3817 | 32.5675 | 0.01
5.4023 | 8.7011 | 7.4023 | 6.4023 | 9.1034 | 11.1034 | 8.7011 | 15.1034 | 24.2068 | 35.3102 | 5.4023 | 8.7111 | 7.4023 | 6.4023 | 9.1034 | 11.1034 | 8.7111 | 15.1134 | 24.2168 | 35.3202 | 0.01
9.2231 | 10.6116 | 11.2231 | 10.2231 | 14.8347 | 16.8347 | 10.6116 | 20.8347 | 35.6693 | 52.504 | 9.2231 | 10.6216 | 11.2231 | 10.2231 | 14.8347 | 16.8347 | 10.6216 | 20.8447 | 35.6793 | 52.514 | 0.01
6.4629 | 9.2314 | 8.4629 | 7.4629 | 10.6943 | 12.6943 | 9.2314 | 16.6943 | 27.3886 | 40.0829 | 6.4629 | 9.2414 | 8.4629 | 7.4629 | 10.6943 | 12.6943 | 9.2414 | 16.7043 | 27.3986 | 40.0929 | 0.01
3.3717 | 7.6858 | 5.3717 | 4.3717 | 6.0575 | 8.0575 | 7.6858 | 12.0575 | 18.115 | 26.1724 | 3.3717 | 7.6958 | 5.3717 | 4.3717 | 6.0575 | 8.0575 | 7.6958 | 12.0675 | 18.125 | 26.1824 | 0.01
5.6239 | 8.812 | 7.6239 | 6.6239 | 9.4359 | 11.4359 | 8.812 | 15.4359 | 24.8718 | 36.3078 | 5.6239 | 8.822 | 7.6239 | 6.6239 | 9.4359 | 11.4359 | 8.822 | 15.4459 | 24.8818 | 36.3178 | 0.01
9.3247 | 10.6624 | 11.3247 | 10.3247 | 14.9871 | 16.9871 | 10.6624 | 20.9871 | 35.9742 | 52.9613 | 9.3247 | 10.6724 | 11.3247 | 10.3247 | 14.9871 | 16.9871 | 10.6724 | 20.9971 | 35.9842 | 52.9713 | 0.01
4.3088 | 8.1544 | 6.3088 | 5.3088 | 7.4632 | 9.4632 | 8.1544 | 13.4632 | 20.9264 | 30.3896 | 4.3088 | 8.1644 | 6.3088 | 5.3088 | 7.4632 | 9.4632 | 8.1644 | 13.4732 | 20.9364 | 30.3996 | 0.01
5.0985 | 8.5493 | 7.0985 | 6.0985 | 8.6478 | 10.6478 | 8.5493 | 14.6478 | 23.2956 | 33.9434 | 5.0985 | 8.5593 | 7.0985 | 6.0985 | 8.6478 | 10.6478 | 8.5593 | 14.6578 | 23.3056 | 33.9534 | 0.01
7.6629 | 9.8315 | 9.6629 | 8.6629 | 12.4944 | 14.4944 | 9.8315 | 18.4944 | 30.9888 | 45.4832 | 7.6629 | 9.8415 | 9.6629 | 8.6629 | 12.4944 | 14.4944 | 9.8415 | 18.5044 | 30.9988 | 45.4932 | 0.01
9.3024 | 10.6512 | 11.3024 | 10.3024 | 14.9536 | 16.9536 | 10.6512 | 20.9536 | 35.9072 | 52.8609 | 9.3024 | 10.6612 | 11.3024 | 10.3024 | 14.9536 | 16.9536 | 10.6612 | 20.9636 | 35.9172 | 52.8709 | 0.01
8.7686 | 10.3843 | 10.7686 | 9.7686 | 14.1529 | 16.1529 | 10.3843 | 20.1529 | 34.3058 | 50.4587 | 8.7686 | 10.3943 | 10.7686 | 9.7686 | 14.1529 | 16.1529 | 10.3943 | 20.1629 | 34.3158 | 50.4687 | 0.01
8.1501 | 10.075 | 10.1501 | 9.1501 | 13.2251 | 15.2251 | 10.075 | 19.2251 | 32.4502 | 47.6753 | 8.1501 | 10.085 | 10.1501 | 9.1501 | 13.2251 | 15.2251 | 10.085 | 19.2351 | 32.4602 | 47.6853 | 0.01
6.7669 | 9.3835 | 8.7669 | 7.7669 | 11.1504 | 13.1504 | 9.3835 | 17.1504 | 28.3008 | 41.4512 | 6.7669 | 9.3935 | 8.7669 | 7.7669 | 11.1504 | 13.1504 | 9.3935 | 17.1604 | 28.3108 | 41.4612 | 0.01
6.0705 | 9.0352 | 8.0705 | 7.0705 | 10.1057 | 12.1057 | 9.0352 | 16.1057 | 26.2114 | 38.3171 | 6.0705 | 9.0452 | 8.0705 | 7.0705 | 10.1057 | 12.1057 | 9.0452 | 16.1157 | 26.2214 | 38.3271 | 0.01
5.7724 | 8.8862 | 7.7724 | 6.7724 | 9.6586 | 11.6586 | 8.8862 | 15.6586 | 25.3172 | 36.9757 | 5.7724 | 8.8962 | 7.7724 | 6.7724 | 9.6586 | 11.6586 | 8.8962 | 15.6686 | 25.3272 | 36.9857 | 0.01
7.6638 | 9.8319 | 9.6638 | 8.6638 | 12.4957 | 14.4957 | 9.8319 | 18.4957 | 30.9914 | 45.487 | 7.6638 | 9.8419 | 9.6638 | 8.6638 | 12.4957 | 14.4957 | 9.8419 | 18.5057 | 31.0014 | 45.497 | 0.01
5.8442 | 8.9221 | 7.8442 | 6.8442 | 9.7663 | 11.7663 | 8.9221 | 15.7663 | 25.5325 | 37.2988 | 5.8442 | 8.9321 | 7.8442 | 6.8442 | 9.7663 | 11.7663 | 8.9321 | 15.7763 | 25.5425 | 37.3088 | 0.01
4.8173 | 8.4086 | 6.8173 | 5.8173 | 8.2259 | 10.2259 | 8.4086 | 14.2259 | 22.4518 | 32.6777 | 4.8173 | 8.4186 | 6.8173 | 5.8173 | 8.2259 | 10.2259 | 8.4186 | 14.2359 | 22.4618 | 32.6877 | 0.01
3.6353 | 7.8177 | 5.6353 | 4.6353 | 6.453 | 8.453 | 7.8177 | 12.453 | 18.9059 | 27.3589 | 3.6353 | 7.8277 | 5.6353 | 4.6353 | 6.453 | 8.453 | 7.8277 | 12.463 | 18.9159 | 27.3689 | 0.01
3.3053 | 7.6526 | 5.3053 | 4.3053 | 5.9579 | 7.9579 | 7.6526 | 11.9579 | 17.9158 | 25.8737 | 3.3053 | 7.6626 | 5.3053 | 4.3053 | 5.9579 | 7.9579 | 7.6626 | 11.9679 | 17.9258 | 25.8837 | 0.01
5.0443 | 8.5222 | 7.0443 | 6.0443 | 8.5665 | 10.5665 | 8.5222 | 14.5665 | 23.133 | 33.6995 | 5.0443 | 8.5322 | 7.0443 | 6.0443 | 8.5665 | 10.5665 | 8.5322 | 14.5765 | 23.143 | 33.7095 | 0.01
8.0763 | 10.0381 | 10.0763 | 9.0763 | 13.1144 | 15.1144 | 10.0381 | 19.1144 | 32.2289 | 47.3433 | 8.0763 | 10.0481 | 10.0763 | 9.0763 | 13.1144 | 15.1144 | 10.0481 | 19.1244 | 32.2389 | 47.3533 | 0.01
4.3336 | 8.1668 | 6.3336 | 5.3336 | 7.5004 | 9.5004 | 8.1668 | 13.5004 | 21.0008 | 30.5013 | 4.3336 | 8.1768 | 6.3336 | 5.3336 | 7.5004 | 9.5004 | 8.1768 | 13.5104 | 21.0108 | 30.5113 | 0.01
9.9359 | 10.9679 | 11.9359 | 10.9359 | 15.9038 | 17.9038 | 10.9679 | 21.9038 | 37.8077 | 55.7115 | 9.9359 | 10.9779 | 11.9359 | 10.9359 | 15.9038 | 17.9038 | 10.9779 | 21.9138 | 37.8177 | 55.7215 | 0.01
6.4882 | 9.2441 | 8.4882 | 7.4882 | 10.7323 | 12.7323 | 9.2441 | 16.7323 | 27.4646 | 40.1969 | 6.4882 | 9.2541 | 8.4882 | 7.4882 | 10.7323 | 12.7323 | 9.2541 | 16.7423 | 27.4746 | 40.2069 | 0.01
3.7597 | 7.8798 | 5.7597 | 4.7597 | 6.6395 | 8.6395 | 7.8798 | 12.6395 | 19.279 | 27.9185 | 3.7597 | 7.8898 | 5.7597 | 4.7597 | 6.6395 | 8.6395 | 7.8898 | 12.6495 | 19.289 | 27.9285 | 0.01
4.1555 | 8.0777 | 6.1555 | 5.1555 | 7.2332 | 9.2332 | 8.0777 | 13.2332 | 20.4665 | 29.6997 | 4.1555 | 8.0877 | 6.1555 | 5.1555 | 7.2332 | 9.2332 | 8.0877 | 13.2432 | 20.4765 | 29.7097 | 0.01
2.6525 | 7.3263 | 4.6525 | 3.6525 | 4.9788 | 6.9788 | 7.3263 | 10.9788 | 15.9575 | 22.9363 | 2.6525 | 7.3363 | 4.6525 | 3.6525 | 4.9788 | 6.9788 | 7.3363 | 10.9888 | 15.9675 | 22.9463 | 0.01
1.8403 | 6.9201 | 3.8403 | 2.8403 | 3.7604 | 5.7604 | 6.9201 | 9.7604 | 13.5208 | 19.2812 | 1.8403 | 6.9301 | 3.8403 | 2.8403 | 3.7604 | 5.7604 | 6.9301 | 9.7704 | 13.5308 | 19.2912 | 0.01
2.6667 | 7.3334 | 4.6667 | 3.6667 | 5.0001 | 7.0001 | 7.3334 | 11.0001 | 16.0001 | 23.0002 | 2.6667 | 7.3434 | 4.6667 | 3.6667 | 5.0001 | 7.0001 | 7.3434 | 11.0101 | 16.0101 | 23.0102 | 0.01
6.4608 | 9.2304 | 8.4608 | 7.4608 | 10.6912 | 12.6912 | 9.2304 | 16.6912 | 27.3825 | 40.0737 | 6.4608 | 9.2404 | 8.4608 | 7.4608 | 10.6912 | 12.6912 | 9.2404 | 16.7012 | 27.3925 | 40.0837 | 0.01
4.1906 | 8.0953 | 6.1906 | 5.1906 | 7.2858 | 9.2858 | 8.0953 | 13.2858 | 20.5717 | 29.8575 | 4.1906 | 8.1053 | 6.1906 | 5.1906 | 7.2858 | 9.2858 | 8.1053 | 13.2958 | 20.5817 | 29.8675 | 0.01
8.6153 | 10.3077 | 10.6153 | 9.6153 | 13.923 | 15.923 | 10.3077 | 19.923 | 33.846 | 49.769 | 8.6153 | 10.3177 | 10.6153 | 9.6153 | 13.923 | 15.923 | 10.3177 | 19.933 | 33.856 | 49.779 | 0.01
4.7385 | 8.3693 | 6.7385 | 5.7385 | 8.1078 | 10.1078 | 8.3693 | 14.1078 | 22.2156 | 32.3234 | 4.7385 | 8.3793 | 6.7385 | 5.7385 | 8.1078 | 10.1078 | 8.3793 | 14.1178 | 22.2256 | 32.3334 | 0.01
2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 2.9838 | 7.5019 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.5019 | 11.4858 | 16.9615 | 24.4373 | 0.01
3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 3.9727 | 7.9963 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9963 | 12.969 | 19.928 | 28.8869 | 0.01
5.9707 | 8.9854 | 7.9707 | 6.9707 | 9.9561 | 11.9561 | 8.9854 | 15.9561 | 25.9121 | 37.8682 | 5.9707 | 8.9954 | 7.9707 | 6.9707 | 9.9561 | 11.9561 | 8.9954 | 15.9661 | 25.9221 | 37.8782 | 0.01
8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 8.3644 | 10.1922 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1922 | 19.5566 | 33.1032 | 48.6497 | 0.01
5.1237 | 8.5618 | 7.1237 | 6.1237 | 8.6855 | 10.6855 | 8.5618 | 14.6855 | 23.3711 | 34.0566 | 5.1237 | 8.5718 | 7.1237 | 6.1237 | 8.6855 | 10.6855 | 8.5718 | 14.6955 | 23.3811 | 34.0666 | 0.01
4.2034 | 8.1017 | 6.2034 | 5.2034 | 7.3051 | 9.3051 | 8.1017 | 13.3051 | 20.6102 | 29.9154 | 4.2034 | 8.1117 | 6.2034 | 5.2034 | 7.3051 | 9.3051 | 8.1117 | 13.3151 | 20.6202 | 29.9254 | 0.01
5.5663 | 8.7832 | 7.5663 | 6.5663 | 9.3495 | 11.3495 | 8.7832 | 15.3495 | 24.699 | 36.0484 | 5.5663 | 8.7932 | 7.5663 | 6.5663 | 9.3495 | 11.3495 | 8.7932 | 15.3595 | 24.709 | 36.0584 | 0.01
6.8431 | 9.4215 | 8.8431 | 7.8431 | 11.2646 | 13.2646 | 9.4215 | 17.2646 | 28.5292 | 41.7939 | 6.8431 | 9.4315 | 8.8431 | 7.8431 | 11.2646 | 13.2646 | 9.4315 | 17.2746 | 28.5392 | 41.8039 | 0.01
6.8551 | 9.4276 | 8.8551 | 7.8551 | 11.2827 | 13.2827 | 9.4276 | 17.2827 | 28.5654 | 41.8481 | 6.8551 | 9.4376 | 8.8551 | 7.8551 | 11.2827 | 13.2827 | 9.4376 | 17.2927 | 28.5754 | 41.8581 | 0.01
4.4435 | 8.2217 | 6.4435 | 5.4435 | 7.6652 | 9.6652 | 8.2217 | 13.6652 | 21.3304 | 30.9956 | 4.4435 | 8.2317 | 6.4435 | 5.4435 | 7.6652 | 9.6652 | 8.2317 | 13.6752 | 21.3404 | 31.0056 | 0.01
9.454 | 10.727 | 11.454 | 10.454 | 15.181 | 17.181 | 10.727 | 21.181 | 36.3619 | 53.5429 | 9.454 | 10.737 | 11.454 | 10.454 | 15.181 | 17.181 | 10.737 | 21.191 | 36.3719 | 53.5529 | 0.01
7.8182 | 9.9091 | 9.8182 | 8.8182 | 12.7273 | 14.7273 | 9.9091 | 18.7273 | 31.4547 | 46.182 | 7.8182 | 9.9191 | 9.8182 | 8.8182 | 12.7273 | 14.7273 | 9.9191 | 18.7373 | 31.4647 | 46.192 | 0.01
6.9341 | 9.4671 | 8.9341 | 7.9341 | 11.4012 | 13.4012 | 9.4671 | 17.4012 | 28.8023 | 42.2035 | 6.9341 | 9.4771 | 8.9341 | 7.9341 | 11.4012 | 13.4012 | 9.4771 | 17.4112 | 28.8123 | 42.2135 | 0.01
4.4815 | 8.2408 | 6.4815 | 5.4815 | 7.7223 | 9.7223 | 8.2408 | 13.7223 | 21.4445 | 31.1668 | 4.4815 | 8.2508 | 6.4815 | 5.4815 | 7.7223 | 9.7223 | 8.2508 | 13.7323 | 21.4545 | 31.1768 | 0.01
5.1586 | 8.5793 | 7.1586 | 6.1586 | 8.7379 | 10.7379 | 8.5793 | 14.7379 | 23.4758 | 34.2137 | 5.1586 | 8.5893 | 7.1586 | 6.1586 | 8.7379 | 10.7379 | 8.5893 | 14.7479 | 23.4858 | 34.2237 | 0.01
8.2539 | 10.1269 | 10.2539 | 9.2539 | 13.3808 | 15.3808 | 10.1269 | 19.3808 | 32.7616 | 48.1423 | 8.2539 | 10.1369 | 10.2539 | 9.2539 | 13.3808 | 15.3808 | 10.1369 | 19.3908 | 32.7716 | 48.1523 | 0.01
7.8806 | 9.9403 | 9.8806 | 8.8806 | 12.8209 | 14.8209 | 9.9403 | 18.8209 | 31.6419 | 46.4628 | 7.8806 | 9.9503 | 9.8806 | 8.8806 | 12.8209 | 14.8209 | 9.9503 | 18.8309 | 31.6519 | 46.4728 | 0.01
4.776 | 8.388 | 6.776 | 5.776 | 8.164 | 10.164 | 8.388 | 14.164 | 22.3281 | 32.4921 | 4.776 | 8.398 | 6.776 | 5.776 | 8.164 | 10.164 | 8.398 | 14.174 | 22.3381 | 32.5021 | 0.01
6.3025 | 9.1512 | 8.3025 | 7.3025 | 10.4537 | 12.4537 | 9.1512 | 16.4537 | 26.9074 | 39.3611 | 6.3025 | 9.1612 | 8.3025 | 7.3025 | 10.4537 | 12.4537 | 9.1612 | 16.4637 | 26.9174 | 39.3711 | 0.01
6.7528 | 9.3764 | 8.7528 | 7.7528 | 11.1292 | 13.1292 | 9.3764 | 17.1292 | 28.2584 | 41.3875 | 6.7528 | 9.3864 | 8.7528 | 7.7528 | 11.1292 | 13.1292 | 9.3864 | 17.1392 | 28.2684 | 41.3975 | 0.01
6.2989 | 9.1495 | 8.2989 | 7.2989 | 10.4484 | 12.4484 | 9.1495 | 16.4484 | 26.8968 | 39.3451 | 6.2989 | 9.1595 | 8.2989 | 7.2989 | 10.4484 | 12.4484 | 9.1595 | 16.4584 | 26.9068 | 39.3551 | 0.01
6.9488 | 9.4744 | 8.9488 | 7.9488 | 11.4232 | 13.4232 | 9.4744 | 17.4232 | 28.8464 | 42.2696 | 6.9488 | 9.4844 | 8.9488 | 7.9488 | 11.4232 | 13.4232 | 9.4844 | 17.4332 | 28.8564 | 42.2796 | 0.01
3.3735 | 7.6867 | 5.3735 | 4.3735 | 6.0602 | 8.0602 | 7.6867 | 12.0602 | 18.1204 | 26.1806 | 3.3735 | 7.6967 | 5.3735 | 4.3735 | 6.0602 | 8.0602 | 7.6967 | 12.0702 | 18.1304 | 26.1906 | 0.01
8.8156 | 10.4078 | 10.8156 | 9.8156 | 14.2235 | 16.2235 | 10.4078 | 20.2235 | 34.4469 | 50.6704 | 8.8156 | 10.4178 | 10.8156 | 9.8156 | 14.2235 | 16.2235 | 10.4178 | 20.2335 | 34.4569 | 50.6804 | 0.01
6.1938 | 9.0969 | 8.1938 | 7.1938 | 10.2907 | 12.2907 | 9.0969 | 16.2907 | 26.5813 | 38.872 | 6.1938 | 9.1069 | 8.1938 | 7.1938 | 10.2907 | 12.2907 | 9.1069 | 16.3007 | 26.5913 | 38.882 | 0.01
2.6892 | 7.3446 | 4.6892 | 3.6892 | 5.0338 | 7.0338 | 7.3446 | 11.0338 | 16.0676 | 23.1013 | 2.6892 | 7.3546 | 4.6892 | 3.6892 | 5.0338 | 7.0338 | 7.3546 | 11.0438 | 16.0776 | 23.1113 | 0.01
9.693 | 10.8465 | 11.693 | 10.693 | 15.5395 | 17.5395 | 10.8465 | 21.5395 | 37.0789 | 54.6184 | 9.693 | 10.8565 | 11.693 | 10.693 | 15.5395 | 17.5395 | 10.8565 | 21.5495 | 37.0889 | 54.6284 | 0.01
7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 7.2212 | 9.6206 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6206 | 17.8418 | 29.6736 | 43.5055 | 0.01
7.6207 | 9.8104 | 9.6207 | 8.6207 | 12.4311 | 14.4311 | 9.8104 | 18.4311 | 30.8621 | 45.2932 | 7.6207 | 9.8204 | 9.6207 | 8.6207 | 12.4311 | 14.4311 | 9.8204 | 18.4411 | 30.8721 | 45.3032 | 0.01
5.3109 | 8.6554 | 7.3109 | 6.3109 | 8.9663 | 10.9663 | 8.6554 | 14.9663 | 23.9327 | 34.899 | 5.3109 | 8.6654 | 7.3109 | 6.3109 | 8.9663 | 10.9663 | 8.6654 | 14.9763 | 23.9427 | 34.909 | 0.01
5.815 | 8.9075 | 7.815 | 6.815 | 9.7225 | 11.7225 | 8.9075 | 15.7225 | 25.445 | 37.1675 | 5.815 | 8.9175 | 7.815 | 6.815 | 9.7225 | 11.7225 | 8.9175 | 15.7325 | 25.455 | 37.1775 | 0.01
8.6974 | 10.3487 | 10.6974 | 9.6974 | 14.0461 | 16.0461 | 10.3487 | 20.0461 | 34.0922 | 50.1383 | 8.6974 | 10.3587 | 10.6974 | 9.6974 | 14.0461 | 16.0461 | 10.3587 | 20.0561 | 34.1022 | 50.1483 | 0.01
4.5436 | 8.2718 | 6.5436 | 5.5436 | 7.8155 | 9.8155 | 8.2718 | 13.8155 | 21.6309 | 31.4464 | 4.5436 | 8.2818 | 6.5436 | 5.5436 | 7.8155 | 9.8155 | 8.2818 | 13.8255 | 21.6409 | 31.4564 | 0.01
3.342 | 7.671 | 5.342 | 4.342 | 6.013 | 8.013 | 7.671 | 12.013 | 18.0259 | 26.0389 | 3.342 | 7.681 | 5.342 | 4.342 | 6.013 | 8.013 | 7.681 | 12.023 | 18.0359 | 26.0489 | 0.01
3.0612 | 7.5306 | 5.0612 | 4.0612 | 5.5918 | 7.5918 | 7.5306 | 11.5918 | 17.1837 | 24.7755 | 3.0612 | 7.5406 | 5.0612 | 4.0612 | 5.5918 | 7.5918 | 7.5406 | 11.6018 | 17.1937 | 24.7855 | 0.01
8.378 | 10.189 | 10.378 | 9.378 | 13.567 | 15.567 | 10.189 | 19.567 | 33.1339 | 48.7009 | 8.378 | 10.199 | 10.378 | 9.378 | 13.567 | 15.567 | 10.199 | 19.577 | 33.1439 | 48.7109 | 0.01
5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 5.7998 | 8.9099 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.9099 | 15.7097 | 25.4093 | 37.109 | 0.01
5.55 | 8.775 | 7.55 | 6.55 | 9.325 | 11.325 | 8.775 | 15.325 | 24.65 | 35.9751 | 5.55 | 8.785 | 7.55 | 6.55 | 9.325 | 11.325 | 8.785 | 15.335 | 24.66 | 35.9851 | 0.01
8.0143 | 10.0072 | 10.0143 | 9.0143 | 13.0215 | 15.0215 | 10.0072 | 19.0215 | 32.043 | 47.0645 | 8.0143 | 10.0172 | 10.0143 | 9.0143 | 13.0215 | 15.0215 | 10.0172 | 19.0315 | 32.053 | 47.0745 | 0.01
4.2615 | 8.1308 | 6.2615 | 5.2615 | 7.3923 | 9.3923 | 8.1308 | 13.3923 | 20.7846 | 30.1769 | 4.2615 | 8.1408 | 6.2615 | 5.2615 | 7.3923 | 9.3923 | 8.1408 | 13.4023 | 20.7946 | 30.1869 | 0.01
4.3816 | 8.1908 | 6.3816 | 5.3816 | 7.5724 | 9.5724 | 8.1908 | 13.5724 | 21.1449 | 30.7173 | 4.3816 | 8.2008 | 6.3816 | 5.3816 | 7.5724 | 9.5724 | 8.2008 | 13.5824 | 21.1549 | 30.7273 | 0.01
5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 5.7998 | 8.9099 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.9099 | 15.7097 | 25.4093 | 37.109 | 0.01
7.8028 | 9.9014 | 9.8028 | 8.8028 | 12.7042 | 14.7042 | 9.9014 | 18.7042 | 31.4083 | 46.1125 | 7.8028 | 9.9114 | 9.8028 | 8.8028 | 12.7042 | 14.7042 | 9.9114 | 18.7142 | 31.4183 | 46.1225 | 0.01
8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 8.3644 | 10.1922 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1922 | 19.5566 | 33.1032 | 48.6497 | 0.01
5.5132 | 8.7566 | 7.5132 | 6.5132 | 9.2698 | 11.2698 | 8.7566 | 15.2698 | 24.5397 | 35.8095 | 5.5132 | 8.7666 | 7.5132 | 6.5132 | 9.2698 | 11.2698 | 8.7666 | 15.2798 | 24.5497 | 35.8195 | 0.01
7.8861 | 9.9431 | 9.8861 | 8.8861 | 12.8292 | 14.8292 | 9.9431 | 18.8292 | 31.6583 | 46.4875 | 7.8861 | 9.9531 | 9.8861 | 8.8861 | 12.8292 | 14.8292 | 9.9531 | 18.8392 | 31.6683 | 46.4975 | 0.01
6.7892 | 9.3946 | 8.7892 | 7.7892 | 11.1838 | 13.1838 | 9.3946 | 17.1838 | 28.3676 | 41.5514 | 6.7892 | 9.4046 | 8.7892 | 7.7892 | 11.1838 | 13.1838 | 9.4046 | 17.1938 | 28.3776 | 41.5614 | 0.01
4.1869 | 8.0934 | 6.1869 | 5.1869 | 7.2803 | 9.2803 | 8.0934 | 13.2803 | 20.5606 | 29.8409 | 4.1869 | 8.1034 | 6.1869 | 5.1869 | 7.2803 | 9.2803 | 8.1034 | 13.2903 | 20.5706 | 29.8509 | 0.01
4.1938 | 8.0969 | 6.1938 | 5.1938 | 7.2907 | 9.2907 | 8.0969 | 13.2907 | 20.5813 | 29.872 | 4.1938 | 8.1069 | 6.1938 | 5.1938 | 7.2907 | 9.2907 | 8.1069 | 13.3007 | 20.5913 | 29.882 | 0.01
3.2575 | 7.6287 | 5.2575 | 4.2575 | 5.8862 | 7.8862 | 7.6287 | 11.8862 | 17.7724 | 25.6586 | 3.2575 | 7.6387 | 5.2575 | 4.2575 | 5.8862 | 7.8862 | 7.6387 | 11.8962 | 17.7824 | 25.6686 | 0.01
4.0356 | 8.0178 | 6.0356 | 5.0356 | 7.0534 | 9.0534 | 8.0178 | 13.0534 | 20.1068 | 29.1602 | 4.0356 | 8.0278 | 6.0356 | 5.0356 | 7.0534 | 9.0534 | 8.0278 | 13.0634 | 20.1168 | 29.1702 | 0.01
6.4349 | 9.2175 | 8.4349 | 7.4349 | 10.6524 | 12.6524 | 9.2175 | 16.6524 | 27.3048 | 39.9572 | 6.4349 | 9.2275 | 8.4349 | 7.4349 | 10.6524 | 12.6524 | 9.2275 | 16.6624 | 27.3148 | 39.9672 | 0.01
7.869 | 9.9345 | 9.869 | 8.869 | 12.8035 | 14.8035 | 9.9345 | 18.8035 | 31.607 | 46.4105 | 7.869 | 9.9445 | 9.869 | 8.869 | 12.8035 | 14.8035 | 9.9445 | 18.8135 | 31.617 | 46.4205 | 0.01
6.7712 | 9.3856 | 8.7712 | 7.7712 | 11.1568 | 13.1568 | 9.3856 | 17.1568 | 28.3136 | 41.4704 | 6.7712 | 9.3956 | 8.7712 | 7.7712 | 11.1568 | 13.1568 | 9.3956 | 17.1668 | 28.3236 | 41.4804 | 0.01
8.0857 | 10.0429 | 10.0857 | 9.0857 | 13.1286 | 15.1286 | 10.0429 | 19.1286 | 32.2572 | 47.3859 | 8.0857 | 10.0529 | 10.0857 | 9.0857 | 13.1286 | 15.1286 | 10.0529 | 19.1386 | 32.2672 | 47.3959 | 0.01
7.7566 | 9.8783 | 9.7566 | 8.7566 | 12.6349 | 14.6349 | 9.8783 | 18.6349 | 31.2699 | 45.9048 | 7.7566 | 9.8883 | 9.7566 | 8.7566 | 12.6349 | 14.6349 | 9.8883 | 18.6449 | 31.2799 | 45.9148 | 0.01
9.6525 | 10.8263 | 11.6525 | 10.6525 | 15.4788 | 17.4788 | 10.8263 | 21.4788 | 36.9575 | 54.4363 | 9.6525 | 10.8363 | 11.6525 | 10.6525 | 15.4788 | 17.4788 | 10.8363 | 21.4888 | 36.9675 | 54.4463 | 0.01
7.2986 | 9.6493 | 9.2986 | 8.2986 | 11.948 | 13.948 | 9.6493 | 17.948 | 29.8959 | 43.8439 | 7.2986 | 9.6593 | 9.2986 | 8.2986 | 11.948 | 13.948 | 9.6593 | 17.958 | 29.9059 | 43.8539 | 0.01
4.0521 | 8.0261 | 6.0521 | 5.0521 | 7.0782 | 9.0782 | 8.0261 | 13.0782 | 20.1564 | 29.2346 | 4.0521 | 8.0361 | 6.0521 | 5.0521 | 7.0782 | 9.0782 | 8.0361 | 13.0882 | 20.1664 | 29.2446 | 0.01
7.0371 | 9.5185 | 9.0371 | 8.0371 | 11.5556 | 13.5556 | 9.5185 | 17.5556 | 29.1112 | 42.6668 | 7.0371 | 9.5285 | 9.0371 | 8.0371 | 11.5556 | 13.5556 | 9.5285 | 17.5656 | 29.1212 | 42.6768 | 0.01
2.233 | 7.1165 | 4.233 | 3.233 | 4.3495 | 6.3495 | 7.1165 | 10.3495 | 14.6991 | 21.0486 | 2.233 | 7.1265 | 4.233 | 3.233 | 4.3495 | 6.3495 | 7.1265 | 10.3595 | 14.7091 | 21.0586 | 0.01
7.2275 | 9.6137 | 9.2275 | 8.2275 | 11.8412 | 13.8412 | 9.6137 | 17.8412 | 29.6825 | 43.5237 | 7.2275 | 9.6237 | 9.2275 | 8.2275 | 11.8412 | 13.8412 | 9.6237 | 17.8512 | 29.6925 | 43.5337 | 0.01
6.3896 | 9.1948 | 8.3896 | 7.3896 | 10.5844 | 12.5844 | 9.1948 | 16.5844 | 27.1688 | 39.7532 | 6.3896 | 9.2048 | 8.3896 | 7.3896 | 10.5844 | 12.5844 | 9.2048 | 16.5944 | 27.1788 | 39.7632 | 0.01
6.4116 | 9.2058 | 8.4116 | 7.4116 | 10.6174 | 12.6174 | 9.2058 | 16.6174 | 27.2349 | 39.8523 | 6.4116 | 9.2158 | 8.4116 | 7.4116 | 10.6174 | 12.6174 | 9.2158 | 16.6274 | 27.2449 | 39.8623 | 0.01
4.7322 | 8.3661 | 6.7322 | 5.7322 | 8.0983 | 10.0983 | 8.3661 | 14.0983 | 22.1965 | 32.2948 | 4.7322 | 8.3761 | 6.7322 | 5.7322 | 8.0983 | 10.0983 | 8.3761 | 14.1083 | 22.2065 | 32.3048 | 0.01
6.7518 | 9.3759 | 8.7518 | 7.7518 | 11.1277 | 13.1277 | 9.3759 | 17.1277 | 28.2554 | 41.3831 | 6.7518 | 9.3859 | 8.7518 | 7.7518 | 11.1277 | 13.1277 | 9.3859 | 17.1377 | 28.2654 | 41.3931 | 0.01
4.1562 | 8.0781 | 6.1562 | 5.1562 | 7.2343 | 9.2343 | 8.0781 | 13.2343 | 20.4686 | 29.7029 | 4.1562 | 8.0881 | 6.1562 | 5.1562 | 7.2343 | 9.2343 | 8.0881 | 13.2443 | 20.4786 | 29.7129 | 0.01
3.8186 | 7.9093 | 5.8186 | 4.8186 | 6.7279 | 8.7279 | 7.9093 | 12.7279 | 19.4557 | 28.1836 | 3.8186 | 7.9193 | 5.8186 | 4.8186 | 6.7279 | 8.7279 | 7.9193 | 12.7379 | 19.4657 | 28.1936 | 0.01
4.9033 | 8.4517 | 6.9033 | 5.9033 | 8.355 | 10.355 | 8.4517 | 14.355 | 22.7099 | 33.0649 | 4.9033 | 8.4617 | 6.9033 | 5.9033 | 8.355 | 10.355 | 8.4617 | 14.365 | 22.7199 | 33.0749 | 0.01
3.8613 | 7.9307 | 5.8613 | 4.8613 | 6.792 | 8.792 | 7.9307 | 12.792 | 19.584 | 28.376 | 3.8613 | 7.9407 | 5.8613 | 4.8613 | 6.792 | 8.792 | 7.9407 | 12.802 | 19.594 | 28.386 | 0.01
8.8507 | 10.4253 | 10.8507 | 9.8507 | 14.276 | 16.276 | 10.4253 | 20.276 | 34.5521 | 50.8281 | 8.8507 | 10.4353 | 10.8507 | 9.8507 | 14.276 | 16.276 | 10.4353 | 20.286 | 34.5621 | 50.8381 | 0.01
4.7771 | 8.3886 | 6.7771 | 5.7771 | 8.1657 | 10.1657 | 8.3886 | 14.1657 | 22.3314 | 32.4971 | 4.7771 | 8.3986 | 6.7771 | 5.7771 | 8.1657 | 10.1657 | 8.3986 | 14.1757 | 22.3414 | 32.5071 | 0.01
6.5063 | 9.2532 | 8.5063 | 7.5063 | 10.7595 | 12.7595 | 9.2532 | 16.7595 | 27.519 | 40.2786 | 6.5063 | 9.2632 | 8.5063 | 7.5063 | 10.7595 | 12.7595 | 9.2632 | 16.7695 | 27.529 | 40.2886 | 0.01
6.9271 | 9.4636 | 8.9271 | 7.9271 | 11.3907 | 13.3907 | 9.4636 | 17.3907 | 28.7813 | 42.172 | 6.9271 | 9.4736 | 8.9271 | 7.9271 | 11.3907 | 13.3907 | 9.4736 | 17.4007 | 28.7913 | 42.182 | 0.01
4.2626 | 8.1313 | 6.2626 | 5.2626 | 7.394 | 9.394 | 8.1313 | 13.394 | 20.7879 | 30.1819 | 4.2626 | 8.1413 | 6.2626 | 5.2626 | 7.394 | 9.394 | 8.1413 | 13.404 | 20.7979 | 30.1919 | 0.01
2.6952 | 7.3476 | 4.6952 | 3.6952 | 5.0428 | 7.0428 | 7.3476 | 11.0428 | 16.0856 | 23.1284 | 2.6952 | 7.3576 | 4.6952 | 3.6952 | 5.0428 | 7.0428 | 7.3576 | 11.0528 | 16.0956 | 23.1384 | 0.01
7.9818 | 9.9909 | 9.9818 | 8.9818 | 12.9728 | 14.9728 | 9.9909 | 18.9728 | 31.9455 | 46.9183 | 7.9818 | 10.0009 | 9.9818 | 8.9818 | 12.9728 | 14.9728 | 10.0009 | 18.9828 | 31.9555 | 46.9283 | 0.01
4.4602 | 8.2301 | 6.4602 | 5.4602 | 7.6903 | 9.6903 | 8.2301 | 13.6903 | 21.3806 | 31.0709 | 4.4602 | 8.2401 | 6.4602 | 5.4602 | 7.6903 | 9.6903 | 8.2401 | 13.7003 | 21.3906 | 31.0809 | 0.01
7.8904 | 9.9452 | 9.8904 | 8.8904 | 12.8356 | 14.8356 | 9.9452 | 18.8356 | 31.6712 | 46.5069 | 7.8904 | 9.9552 | 9.8904 | 8.8904 | 12.8356 | 14.8356 | 9.9552 | 18.8456 | 31.6812 | 46.5169 | 0.01
4.5586 | 8.2793 | 6.5586 | 5.5586 | 7.8379 | 9.8379 | 8.2793 | 13.8379 | 21.6757 | 31.5136 | 4.5586 | 8.2893 | 6.5586 | 5.5586 | 7.8379 | 9.8379 | 8.2893 | 13.8479 | 21.6857 | 31.5236 | 0.01
5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 5.3559 | 8.6879 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6879 | 15.0438 | 24.0776 | 35.1113 | 0.01
4.5162 | 8.2581 | 6.5162 | 5.5162 | 7.7743 | 9.7743 | 8.2581 | 13.7743 | 21.5486 | 31.3228 | 4.5162 | 8.2681 | 6.5162 | 5.5162 | 7.7743 | 9.7743 | 8.2681 | 13.7843 | 21.5586 | 31.3328 | 0.01
4.8841 | 8.442 | 6.8841 | 5.8841 | 8.3261 | 10.3261 | 8.442 | 14.3261 | 22.6522 | 32.9782 | 4.8841 | 8.452 | 6.8841 | 5.8841 | 8.3261 | 10.3261 | 8.452 | 14.3361 | 22.6622 | 32.9882 | 0.01
5.6401 | 8.8201 | 7.6401 | 6.6401 | 9.4602 | 11.4602 | 8.8201 | 15.4602 | 24.9204 | 36.3806 | 5.6401 | 8.8301 | 7.6401 | 6.6401 | 9.4602 | 11.4602 | 8.8301 | 15.4702 | 24.9304 | 36.3906 | 0.01
9.7333 | 10.8666 | 11.7333 | 10.7333 | 15.5999 | 17.5999 | 10.8666 | 21.5999 | 37.1998 | 54.7997 | 9.7333 | 10.8766 | 11.7333 | 10.7333 | 15.5999 | 17.5999 | 10.8766 | 21.6099 | 37.2098 | 54.8097 | 0.01
4.4464 | 8.2232 | 6.4464 | 5.4464 | 7.6696 | 9.6696 | 8.2232 | 13.6696 | 21.3391 | 31.0087 | 4.4464 | 8.2332 | 6.4464 | 5.4464 | 7.6696 | 9.6696 | 8.2332 | 13.6796 | 21.3491 | 31.0187 | 0.01
3.4011 | 7.7006 | 5.4011 | 4.4011 | 6.1017 | 8.1017 | 7.7006 | 12.1017 | 18.2034 | 26.305 | 3.4011 | 7.7106 | 5.4011 | 4.4011 | 6.1017 | 8.1017 | 7.7106 | 12.1117 | 18.2134 | 26.315 | 0.01
5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 5.2901 | 8.655 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.655 | 14.9451 | 23.8802 | 34.8153 | 0.01
2.1888 | 7.0944 | 4.1888 | 3.1888 | 4.2832 | 6.2832 | 7.0944 | 10.2832 | 14.5665 | 20.8497 | 2.1888 | 7.1044 | 4.1888 | 3.1888 | 4.2832 | 6.2832 | 7.1044 | 10.2932 | 14.5765 | 20.8597 | 0.01
6.8979 | 9.449 | 8.8979 | 7.8979 | 11.3469 | 13.3469 | 9.449 | 17.3469 | 28.6937 | 42.0406 | 6.8979 | 9.459 | 8.8979 | 7.8979 | 11.3469 | 13.3469 | 9.459 | 17.3569 | 28.7037 | 42.0506 | 0.01
4.4544 | 8.2272 | 6.4544 | 5.4544 | 7.6816 | 9.6816 | 8.2272 | 13.6816 | 21.3633 | 31.0449 | 4.4544 | 8.2372 | 6.4544 | 5.4544 | 7.6816 | 9.6816 | 8.2372 | 13.6916 | 21.3733 | 31.0549 | 0.01
5.3782 | 8.6891 | 7.3782 | 6.3782 | 9.0673 | 11.0673 | 8.6891 | 15.0673 | 24.1346 | 35.202 | 5.3782 | 8.6991 | 7.3782 | 6.3782 | 9.0673 | 11.0673 | 8.6991 | 15.0773 | 24.1446 | 35.212 | 0.01
4.8642 | 8.4321 | 6.8642 | 5.8642 | 8.2962 | 10.2962 | 8.4321 | 14.2962 | 22.5925 | 32.8887 | 4.8642 | 8.4421 | 6.8642 | 5.8642 | 8.2962 | 10.2962 | 8.4421 | 14.3062 | 22.6025 | 32.8987 | 0.01
6.4795 | 9.2398 | 8.4795 | 7.4795 | 10.7193 | 12.7193 | 9.2398 | 16.7193 | 27.4386 | 40.1579 | 6.4795 | 9.2498 | 8.4795 | 7.4795 | 10.7193 | 12.7193 | 9.2498 | 16.7293 | 27.4486 | 40.1679 | 0.01
6.2353 | 9.1177 | 8.2353 | 7.2353 | 10.353 | 12.353 | 9.1177 | 16.353 | 26.7059 | 39.0589 | 6.2353 | 9.1277 | 8.2353 | 7.2353 | 10.353 | 12.353 | 9.1277 | 16.363 | 26.7159 | 39.0689 | 0.01
6.6358 | 9.3179 | 8.6358 | 7.6358 | 10.9537 | 12.9537 | 9.3179 | 16.9537 | 27.9073 | 40.861 | 6.6358 | 9.3279 | 8.6358 | 7.6358 | 10.9537 | 12.9537 | 9.3279 | 16.9637 | 27.9173 | 40.871 | 0.01
5.2598 | 8.6299 | 7.2598 | 6.2598 | 8.8898 | 10.8898 | 8.6299 | 14.8898 | 23.7795 | 34.6693 | 5.2598 | 8.6399 | 7.2598 | 6.2598 | 8.8898 | 10.8898 | 8.6399 | 14.8998 | 23.7895 | 34.6793 | 0.01
5.8382 | 8.9191 | 7.8382 | 6.8382 | 9.7573 | 11.7573 | 8.9191 | 15.7573 | 25.5145 | 37.2718 | 5.8382 | 8.9291 | 7.8382 | 6.8382 | 9.7573 | 11.7573 | 8.9291 | 15.7673 | 25.5245 | 37.2818 | 0.01
3.6537 | 7.8268 | 5.6537 | 4.6537 | 6.4805 | 8.4805 | 7.8268 | 12.4805 | 18.961 | 27.4415 | 3.6537 | 7.8368 | 5.6537 | 4.6537 | 6.4805 | 8.4805 | 7.8368 | 12.4905 | 18.971 | 27.4515 | 0.01
10.3093 | 11.1546 | 12.3093 | 11.3093 | 16.4639 | 18.4639 | 11.1546 | 22.4639 | 38.9278 | 57.3917 | 10.3093 | 11.1646 | 12.3093 | 11.3093 | 16.4639 | 18.4639 | 11.1646 | 22.4739 | 38.9378 | 57.4017 | 0.01
2.9072 | 7.4536 | 4.9072 | 3.9072 | 5.3609 | 7.3609 | 7.4536 | 11.3609 | 16.7217 | 24.0826 | 2.9072 | 7.4636 | 4.9072 | 3.9072 | 5.3609 | 7.3609 | 7.4636 | 11.3709 | 16.7317 | 24.0926 | 0.01
8.8398 | 10.4199 | 10.8398 | 9.8398 | 14.2596 | 16.2596 | 10.4199 | 20.2596 | 34.5193 | 50.7789 | 8.8398 | 10.4299 | 10.8398 | 9.8398 | 14.2596 | 16.2596 | 10.4299 | 20.2696 | 34.5293 | 50.7889 | 0.01
4.7994 | 8.3997 | 6.7994 | 5.7994 | 8.1991 | 10.1991 | 8.3997 | 14.1991 | 22.3981 | 32.5972 | 4.7994 | 8.4097 | 6.7994 | 5.7994 | 8.1991 | 10.1991 | 8.4097 | 14.2091 | 22.4081 | 32.6072 | 0.01
4.8728 | 8.4364 | 6.8728 | 5.8728 | 8.3092 | 10.3092 | 8.4364 | 14.3092 | 22.6183 | 32.9275 | 4.8728 | 8.4464 | 6.8728 | 5.8728 | 8.3092 | 10.3092 | 8.4464 | 14.3192 | 22.6283 | 32.9375 | 0.01
8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 8.8231 | 10.4215 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4215 | 20.2446 | 34.4792 | 50.7139 | 0.01
8.2877 | 10.1438 | 10.2877 | 9.2877 | 13.4315 | 15.4315 | 10.1438 | 19.4315 | 32.863 | 48.2945 | 8.2877 | 10.1538 | 10.2877 | 9.2877 | 13.4315 | 15.4315 | 10.1538 | 19.4415 | 32.873 | 48.3045 | 0.01
5.1521 | 8.576 | 7.1521 | 6.1521 | 8.7281 | 10.7281 | 8.576 | 14.7281 | 23.4562 | 34.1843 | 5.1521 | 8.586 | 7.1521 | 6.1521 | 8.7281 | 10.7281 | 8.586 | 14.7381 | 23.4662 | 34.1943 | 0.01
7.8614 | 9.9307 | 9.8614 | 8.8614 | 12.7921 | 14.7921 | 9.9307 | 18.7921 | 31.5843 | 46.3764 | 7.8614 | 9.9407 | 9.8614 | 8.8614 | 12.7921 | 14.7921 | 9.9407 | 18.8021 | 31.5943 | 46.3864 | 0.01
7.2199 | 9.61 | 9.2199 | 8.2199 | 11.8299 | 13.8299 | 9.61 | 17.8299 | 29.6598 | 43.4897 | 7.2199 | 9.62 | 9.2199 | 8.2199 | 11.8299 | 13.8299 | 9.62 | 17.8399 | 29.6698 | 43.4997 | 0.01
5.6179 | 8.8089 | 7.6179 | 6.6179 | 9.4268 | 11.4268 | 8.8089 | 15.4268 | 24.8536 | 36.2804 | 5.6179 | 8.8189 | 7.6179 | 6.6179 | 9.4268 | 11.4268 | 8.8189 | 15.4368 | 24.8636 | 36.2904 | 0.01
2.7189 | 7.3595 | 4.7189 | 3.7189 | 5.0784 | 7.0784 | 7.3595 | 11.0784 | 16.1568 | 23.2352 | 2.7189 | 7.3695 | 4.7189 | 3.7189 | 5.0784 | 7.0784 | 7.3695 | 11.0884 | 16.1668 | 23.2452 | 0.01
7.0937 | 9.5468 | 9.0937 | 8.0937 | 11.6405 | 13.6405 | 9.5468 | 17.6405 | 29.281 | 42.9215 | 7.0937 | 9.5568 | 9.0937 | 8.0937 | 11.6405 | 13.6405 | 9.5568 | 17.6505 | 29.291 | 42.9315 | 0.01
6.5789 | 9.2894 | 8.5789 | 7.5789 | 10.8683 | 12.8683 | 9.2894 | 16.8683 | 27.7367 | 40.605 | 6.5789 | 9.2994 | 8.5789 | 7.5789 | 10.8683 | 12.8683 | 9.2994 | 16.8783 | 27.7467 | 40.615 | 0.01
4.9738 | 8.4869 | 6.9738 | 5.9738 | 8.4606 | 10.4606 | 8.4869 | 14.4606 | 22.9213 | 33.3819 | 4.9738 | 8.4969 | 6.9738 | 5.9738 | 8.4606 | 10.4606 | 8.4969 | 14.4706 | 22.9313 | 33.3919 | 0.01
5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 5.3943 | 8.7071 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.7071 | 15.1014 | 24.1928 | 35.2841 | 0.01
3.3249 | 7.6624 | 5.3249 | 4.3249 | 5.9873 | 7.9873 | 7.6624 | 11.9873 | 17.9746 | 25.9618 | 3.3249 | 7.6724 | 5.3249 | 4.3249 | 5.9873 | 7.9873 | 7.6724 | 11.9973 | 17.9846 | 25.9718 | 0.01
5.9637 | 8.9818 | 7.9637 | 6.9637 | 9.9455 | 11.9455 | 8.9818 | 15.9455 | 25.891 | 37.8365 | 5.9637 | 8.9918 | 7.9637 | 6.9637 | 9.9455 | 11.9455 | 8.9918 | 15.9555 | 25.901 | 37.8465 | 0.01
3.7881 | 7.894 | 5.7881 | 4.7881 | 6.6821 | 8.6821 | 7.894 | 12.6821 | 19.3643 | 28.0464 | 3.7881 | 7.904 | 5.7881 | 4.7881 | 6.6821 | 8.6821 | 7.904 | 12.6921 | 19.3743 | 28.0564 | 0.01
8.004 | 10.002 | 10.004 | 9.004 | 13.0059 | 15.0059 | 10.002 | 19.0059 | 32.0119 | 47.0178 | 8.004 | 10.012 | 10.004 | 9.004 | 13.0059 | 15.0059 | 10.012 | 19.0159 | 32.0219 | 47.0278 | 0.01
7.6199 | 9.8099 | 9.6199 | 8.6199 | 12.4298 | 14.4298 | 9.8099 | 18.4298 | 30.8596 | 45.2893 | 7.6199 | 9.8199 | 9.6199 | 8.6199 | 12.4298 | 14.4298 | 9.8199 | 18.4398 | 30.8696 | 45.2993 | 0.01
5.0882 | 8.5441 | 7.0882 | 6.0882 | 8.6323 | 10.6323 | 8.5441 | 14.6323 | 23.2646 | 33.8968 | 5.0882 | 8.5541 | 7.0882 | 6.0882 | 8.6323 | 10.6323 | 8.5541 | 14.6423 | 23.2746 | 33.9068 | 0.01
4.9297 | 8.4649 | 6.9297 | 5.9297 | 8.3946 | 10.3946 | 8.4649 | 14.3946 | 22.7891 | 33.1837 | 4.9297 | 8.4749 | 6.9297 | 5.9297 | 8.3946 | 10.3946 | 8.4749 | 14.4046 | 22.7991 | 33.1937 | 0.01
1.9638 | 6.9819 | 3.9638 | 2.9638 | 3.9457 | 5.9457 | 6.9819 | 9.9457 | 13.8914 | 19.8371 | 1.9638 | 6.9919 | 3.9638 | 2.9638 | 3.9457 | 5.9457 | 6.9919 | 9.9557 | 13.9014 | 19.8471 | 0.01
5.227 | 8.6135 | 7.227 | 6.227 | 8.8405 | 10.8405 | 8.6135 | 14.8405 | 23.6809 | 34.5214 | 5.227 | 8.6235 | 7.227 | 6.227 | 8.8405 | 10.8405 | 8.6235 | 14.8505 | 23.6909 | 34.5314 | 0.01
2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 2.9838 | 7.5019 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.5019 | 11.4858 | 16.9615 | 24.4373 | 0.01
6.9433 | 9.4717 | 8.9433 | 7.9433 | 11.415 | 13.415 | 9.4717 | 17.415 | 28.83 | 42.245 | 6.9433 | 9.4817 | 8.9433 | 7.9433 | 11.415 | 13.415 | 9.4817 | 17.425 | 28.84 | 42.255 | 0.01
5.765 | 8.8825 | 7.765 | 6.765 | 9.6475 | 11.6475 | 8.8825 | 15.6475 | 25.295 | 36.9425 | 5.765 | 8.8925 | 7.765 | 6.765 | 9.6475 | 11.6475 | 8.8925 | 15.6575 | 25.305 | 36.9525 | 0.01
2.6494 | 7.3247 | 4.6494 | 3.6494 | 4.9741 | 6.9741 | 7.3247 | 10.9741 | 15.9482 | 22.9223 | 2.6494 | 7.3347 | 4.6494 | 3.6494 | 4.9741 | 6.9741 | 7.3347 | 10.9841 | 15.9582 | 22.9323 | 0.01
7.3038 | 9.6519 | 9.3038 | 8.3038 | 11.9556 | 13.9556 | 9.6519 | 17.9556 | 29.9113 | 43.8669 | 7.3038 | 9.6619 | 9.3038 | 8.3038 | 11.9556 | 13.9556 | 9.6619 | 17.9656 | 29.9213 | 43.8769 | 0.01
3.554 | 7.777 | 5.554 | 4.554 | 6.3309 | 8.3309 | 7.777 | 12.3309 | 18.6619 | 26.9928 | 3.554 | 7.787 | 5.554 | 4.554 | 6.3309 | 8.3309 | 7.787 | 12.3409 | 18.6719 | 27.0028 | 0.01
5.9113 | 8.9557 | 7.9113 | 6.9113 | 9.867 | 11.867 | 8.9557 | 15.867 | 25.7339 | 37.6009 | 5.9113 | 8.9657 | 7.9113 | 6.9113 | 9.867 | 11.867 | 8.9657 | 15.877 | 25.7439 | 37.6109 | 0.01
8.773 | 10.3865 | 10.773 | 9.773 | 14.1595 | 16.1595 | 10.3865 | 20.1595 | 34.319 | 50.4785 | 8.773 | 10.3965 | 10.773 | 9.773 | 14.1595 | 16.1595 | 10.3965 | 20.1695 | 34.329 | 50.4885 | 0.01
6.175 | 9.0875 | 8.175 | 7.175 | 10.2625 | 12.2625 | 9.0875 | 16.2625 | 26.5251 | 38.7876 | 6.175 | 9.0975 | 8.175 | 7.175 | 10.2625 | 12.2625 | 9.0975 | 16.2725 | 26.5351 | 38.7976 | 0.01
7.0464 | 9.5232 | 9.0464 | 8.0464 | 11.5695 | 13.5695 | 9.5232 | 17.5695 | 29.1391 | 42.7086 | 7.0464 | 9.5332 | 9.0464 | 8.0464 | 11.5695 | 13.5695 | 9.5332 | 17.5795 | 29.1491 | 42.7186 | 0.01
4.9413 | 8.4707 | 6.9413 | 5.9413 | 8.412 | 10.412 | 8.4707 | 14.412 | 22.824 | 33.236 | 4.9413 | 8.4807 | 6.9413 | 5.9413 | 8.412 | 10.412 | 8.4807 | 14.422 | 22.834 | 33.246 | 0.01
4.8679 | 8.434 | 6.8679 | 5.8679 | 8.3019 | 10.3019 | 8.434 | 14.3019 | 22.6038 | 32.9057 | 4.8679 | 8.444 | 6.8679 | 5.8679 | 8.3019 | 10.3019 | 8.444 | 14.3119 | 22.6138 | 32.9157 | 0.01
4.8742 | 8.4371 | 6.8742 | 5.8742 | 8.3113 | 10.3113 | 8.4371 | 14.3113 | 22.6226 | 32.9339 | 4.8742 | 8.4471 | 6.8742 | 5.8742 | 8.3113 | 10.3113 | 8.4471 | 14.3213 | 22.6326 | 32.9439 | 0.01
9.329 | 10.6645 | 11.329 | 10.329 | 14.9935 | 16.9935 | 10.6645 | 20.9935 | 35.987 | 52.9806 | 9.329 | 10.6745 | 11.329 | 10.329 | 14.9935 | 16.9935 | 10.6745 | 21.0035 | 35.997 | 52.9906 | 0.01
7.5224 | 9.7612 | 9.5224 | 8.5224 | 12.2836 | 14.2836 | 9.7612 | 18.2836 | 30.5671 | 44.8507 | 7.5224 | 9.7712 | 9.5224 | 8.5224 | 12.2836 | 14.2836 | 9.7712 | 18.2936 | 30.5771 | 44.8607 | 0.01
8.1979 | 10.0989 | 10.1979 | 9.1979 | 13.2968 | 15.2968 | 10.0989 | 19.2968 | 32.5936 | 47.8904 | 8.1979 | 10.1089 | 10.1979 | 9.1979 | 13.2968 | 15.2968 | 10.1089 | 19.3068 | 32.6036 | 47.9004 | 0.01
5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 5.2196 | 8.6198 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6198 | 14.8393 | 23.6687 | 34.498 | 0.01
8.1953 | 10.0977 | 10.1953 | 9.1953 | 13.293 | 15.293 | 10.0977 | 19.293 | 32.586 | 47.8791 | 8.1953 | 10.1077 | 10.1953 | 9.1953 | 13.293 | 15.293 | 10.1077 | 19.303 | 32.596 | 47.8891 | 0.01
4.9143 | 8.4572 | 6.9143 | 5.9143 | 8.3715 | 10.3715 | 8.4572 | 14.3715 | 22.7429 | 33.1144 | 4.9143 | 8.4672 | 6.9143 | 5.9143 | 8.3715 | 10.3715 | 8.4672 | 14.3815 | 22.7529 | 33.1244 | 0.01
8.9991 | 10.4995 | 10.9991 | 9.9991 | 14.4986 | 16.4986 | 10.4995 | 20.4986 | 34.9973 | 51.4959 | 8.9991 | 10.5095 | 10.9991 | 9.9991 | 14.4986 | 16.4986 | 10.5095 | 20.5086 | 35.0073 | 51.5059 | 0.01
3.9365 | 7.9683 | 5.9365 | 4.9365 | 6.9048 | 8.9048 | 7.9683 | 12.9048 | 19.8096 | 28.7143 | 3.9365 | 7.9783 | 5.9365 | 4.9365 | 6.9048 | 8.9048 | 7.9783 | 12.9148 | 19.8196 | 28.7243 | 0.01
7.8134 | 9.9067 | 9.8134 | 8.8134 | 12.7201 | 14.7201 | 9.9067 | 18.7201 | 31.4401 | 46.1602 | 7.8134 | 9.9167 | 9.8134 | 8.8134 | 12.7201 | 14.7201 | 9.9167 | 18.7301 | 31.4501 | 46.1702 | 0.01
4.0634 | 8.0317 | 6.0634 | 5.0634 | 7.0951 | 9.0951 | 8.0317 | 13.0951 | 20.1902 | 29.2853 | 4.0634 | 8.0417 | 6.0634 | 5.0634 | 7.0951 | 9.0951 | 8.0417 | 13.1051 | 20.2002 | 29.2953 | 0.01
6.7403 | 9.3702 | 8.7403 | 7.7403 | 11.1105 | 13.1105 | 9.3702 | 17.1105 | 28.221 | 41.3314 | 6.7403 | 9.3802 | 8.7403 | 7.7403 | 11.1105 | 13.1105 | 9.3802 | 17.1205 | 28.231 | 41.3414 | 0.01
5.6408 | 8.8204 | 7.6408 | 6.6408 | 9.4611 | 11.4611 | 8.8204 | 15.4611 | 24.9223 | 36.3834 | 5.6408 | 8.8304 | 7.6408 | 6.6408 | 9.4611 | 11.4611 | 8.8304 | 15.4711 | 24.9323 | 36.3934 | 0.01
6.2507 | 9.1254 | 8.2507 | 7.2507 | 10.3761 | 12.3761 | 9.1254 | 16.3761 | 26.7522 | 39.1283 | 6.2507 | 9.1354 | 8.2507 | 7.2507 | 10.3761 | 12.3761 | 9.1354 | 16.3861 | 26.7622 | 39.1383 | 0.01
8.3342 | 10.1671 | 10.3342 | 9.3342 | 13.5013 | 15.5013 | 10.1671 | 19.5013 | 33.0026 | 48.5039 | 8.3342 | 10.1771 | 10.3342 | 9.3342 | 13.5013 | 15.5013 | 10.1771 | 19.5113 | 33.0126 | 48.5139 | 0.01
9.8378 | 10.9189 | 11.8378 | 10.8378 | 15.7567 | 17.7567 | 10.9189 | 21.7567 | 37.5135 | 55.2702 | 9.8378 | 10.9289 | 11.8378 | 10.8378 | 15.7567 | 17.7567 | 10.9289 | 21.7667 | 37.5235 | 55.2802 | 0.01
5.9193 | 8.9596 | 7.9193 | 6.9193 | 9.8789 | 11.8789 | 8.9596 | 15.8789 | 25.7578 | 37.6367 | 5.9193 | 8.9696 | 7.9193 | 6.9193 | 9.8789 | 11.8789 | 8.9696 | 15.8889 | 25.7678 | 37.6467 | 0.01
9.7806 | 10.8903 | 11.7806 | 10.7806 | 15.6709 | 17.6709 | 10.8903 | 21.6709 | 37.3418 | 55.0127 | 9.7806 | 10.9003 | 11.7806 | 10.7806 | 15.6709 | 17.6709 | 10.9003 | 21.6809 | 37.3518 | 55.0227 | 0.01
7.2998 | 9.6499 | 9.2998 | 8.2998 | 11.9497 | 13.9497 | 9.6499 | 17.9497 | 29.8993 | 43.849 | 7.2998 | 9.6599 | 9.2998 | 8.2998 | 11.9497 | 13.9497 | 9.6599 | 17.9597 | 29.9093 | 43.859 | 0.01
5.2258 | 8.6129 | 7.2258 | 6.2258 | 8.8387 | 10.8387 | 8.6129 | 14.8387 | 23.6775 | 34.5162 | 5.2258 | 8.6229 | 7.2258 | 6.2258 | 8.8387 | 10.8387 | 8.6229 | 14.8487 | 23.6875 | 34.5262 | 0.01
5.5571 | 8.7785 | 7.5571 | 6.5571 | 9.3356 | 11.3356 | 8.7785 | 15.3356 | 24.6712 | 36.0068 | 5.5571 | 8.7885 | 7.5571 | 6.5571 | 9.3356 | 11.3356 | 8.7885 | 15.3456 | 24.6812 | 36.0168 | 0.01
3.6445 | 7.8223 | 5.6445 | 4.6445 | 6.4668 | 8.4668 | 7.8223 | 12.4668 | 18.9335 | 27.4003 | 3.6445 | 7.8323 | 5.6445 | 4.6445 | 6.4668 | 8.4668 | 7.8323 | 12.4768 | 18.9435 | 27.4103 | 0.01
4.0026 | 8.0013 | 6.0026 | 5.0026 | 7.0039 | 9.0039 | 8.0013 | 13.0039 | 20.0078 | 29.0117 | 4.0026 | 8.0113 | 6.0026 | 5.0026 | 7.0039 | 9.0039 | 8.0113 | 13.0139 | 20.0178 | 29.0217 | 0.01
6.0532 | 9.0266 | 8.0532 | 7.0532 | 10.0798 | 12.0798 | 9.0266 | 16.0798 | 26.1595 | 38.2393 | 6.0532 | 9.0366 | 8.0532 | 7.0532 | 10.0798 | 12.0798 | 9.0366 | 16.0898 | 26.1695 | 38.2493 | 0.01
6.9761 | 9.4881 | 8.9761 | 7.9761 | 11.4642 | 13.4642 | 9.4881 | 17.4642 | 28.9284 | 42.3925 | 6.9761 | 9.4981 | 8.9761 | 7.9761 | 11.4642 | 13.4642 | 9.4981 | 17.4742 | 28.9384 | 42.4025 | 0.01
2.4113 | 7.2056 | 4.4113 | 3.4113 | 4.6169 | 6.6169 | 7.2056 | 10.6169 | 15.2338 | 21.8508 | 2.4113 | 7.2156 | 4.4113 | 3.4113 | 4.6169 | 6.6169 | 7.2156 | 10.6269 | 15.2438 | 21.8608 | 0.01
3.7525 | 7.8762 | 5.7525 | 4.7525 | 6.6287 | 8.6287 | 7.8762 | 12.6287 | 19.2575 | 27.8862 | 3.7525 | 7.8862 | 5.7525 | 4.7525 | 6.6287 | 8.6287 | 7.8862 | 12.6387 | 19.2675 | 27.8962 | 0.01
6.4384 | 9.2192 | 8.4384 | 7.4384 | 10.6576 | 12.6576 | 9.2192 | 16.6576 | 27.3151 | 39.9727 | 6.4384 | 9.2292 | 8.4384 | 7.4384 | 10.6576 | 12.6576 | 9.2292 | 16.6676 | 27.3251 | 39.9827 | 0.01
1.4433 | 6.7216 | 3.4433 | 2.4433 | 3.1649 | 5.1649 | 6.7216 | 9.1649 | 12.3299 | 17.4948 | 1.4433 | 6.7316 | 3.4433 | 2.4433 | 3.1649 | 5.1649 | 6.7316 | 9.1749 | 12.3399 | 17.5048 | 0.01
7.9113 | 9.9557 | 9.9113 | 8.9113 | 12.867 | 14.867 | 9.9557 | 18.867 | 31.734 | 46.6009 | 7.9113 | 9.9657 | 9.9113 | 8.9113 | 12.867 | 14.867 | 9.9657 | 18.877 | 31.744 | 46.6109 | 0.01
4.1557 | 8.0779 | 6.1557 | 5.1557 | 7.2336 | 9.2336 | 8.0779 | 13.2336 | 20.4672 | 29.7007 | 4.1557 | 8.0879 | 6.1557 | 5.1557 | 7.2336 | 9.2336 | 8.0879 | 13.2436 | 20.4772 | 29.7107 | 0.01
9.7438 | 10.8719 | 11.7438 | 10.7438 | 15.6157 | 17.6157 | 10.8719 | 21.6157 | 37.2314 | 54.8471 | 9.7438 | 10.8819 | 11.7438 | 10.7438 | 15.6157 | 17.6157 | 10.8819 | 21.6257 | 37.2414 | 54.8571 | 0.01
8.0146 | 10.0073 | 10.0146 | 9.0146 | 13.0219 | 15.0219 | 10.0073 | 19.0219 | 32.0438 | 47.0657 | 8.0146 | 10.0173 | 10.0146 | 9.0146 | 13.0219 | 15.0219 | 10.0173 | 19.0319 | 32.0538 | 47.0757 | 0.01
7.2032 | 9.6016 | 9.2032 | 8.2032 | 11.8048 | 13.8048 | 9.6016 | 17.8048 | 29.6096 | 43.4144 | 7.2032 | 9.6116 | 9.2032 | 8.2032 | 11.8048 | 13.8048 | 9.6116 | 17.8148 | 29.6196 | 43.4244 | 0.01
5.1038 | 8.5519 | 7.1038 | 6.1038 | 8.6557 | 10.6557 | 8.5519 | 14.6557 | 23.3113 | 33.967 | 5.1038 | 8.5619 | 7.1038 | 6.1038 | 8.6557 | 10.6557 | 8.5619 | 14.6657 | 23.3213 | 33.977 | 0.01
10.3046 | 11.1523 | 12.3046 | 11.3046 | 16.4569 | 18.4569 | 11.1523 | 22.4569 | 38.9138 | 57.3707 | 10.3046 | 11.1623 | 12.3046 | 11.3046 | 16.4569 | 18.4569 | 11.1623 | 22.4669 | 38.9238 | 57.3807 | 0.01
6.0128 | 9.0064 | 8.0128 | 7.0128 | 10.0192 | 12.0192 | 9.0064 | 16.0192 | 26.0383 | 38.0575 | 6.0128 | 9.0164 | 8.0128 | 7.0128 | 10.0192 | 12.0192 | 9.0164 | 16.0292 | 26.0483 | 38.0675 | 0.01
5.3452 | 8.6726 | 7.3452 | 6.3452 | 9.0178 | 11.0178 | 8.6726 | 15.0178 | 24.0356 | 35.0535 | 5.3452 | 8.6826 | 7.3452 | 6.3452 | 9.0178 | 11.0178 | 8.6826 | 15.0278 | 24.0456 | 35.0635 | 0.01
5.0104 | 8.5052 | 7.0104 | 6.0104 | 8.5156 | 10.5156 | 8.5052 | 14.5156 | 23.0312 | 33.5469 | 5.0104 | 8.5152 | 7.0104 | 6.0104 | 8.5156 | 10.5156 | 8.5152 | 14.5256 | 23.0412 | 33.5569 | 0.01
8.5886 | 10.2943 | 10.5886 | 9.5886 | 13.8829 | 15.8829 | 10.2943 | 19.8829 | 33.7658 | 49.6487 | 8.5886 | 10.3043 | 10.5886 | 9.5886 | 13.8829 | 15.8829 | 10.3043 | 19.8929 | 33.7758 | 49.6587 | 0.01
4.7374 | 8.3687 | 6.7374 | 5.7374 | 8.1061 | 10.1061 | 8.3687 | 14.1061 | 22.2122 | 32.3184 | 4.7374 | 8.3787 | 6.7374 | 5.7374 | 8.1061 | 10.1061 | 8.3787 | 14.1161 | 22.2222 | 32.3284 | 0.01
4.205 | 8.1025 | 6.205 | 5.205 | 7.3075 | 9.3075 | 8.1025 | 13.3075 | 20.6151 | 29.9226 | 4.205 | 8.1125 | 6.205 | 5.205 | 7.3075 | 9.3075 | 8.1125 | 13.3175 | 20.6251 | 29.9326 | 0.01
6.7811 | 9.3906 | 8.7811 | 7.7811 | 11.1717 | 13.1717 | 9.3906 | 17.1717 | 28.3433 | 41.515 | 6.7811 | 9.4006 | 8.7811 | 7.7811 | 11.1717 | 13.1717 | 9.4006 | 17.1817 | 28.3533 | 41.525 | 0.01
5.058 | 8.529 | 7.058 | 6.058 | 8.5871 | 10.5871 | 8.529 | 14.5871 | 23.1741 | 33.7612 | 5.058 | 8.539 | 7.058 | 6.058 | 8.5871 | 10.5871 | 8.539 | 14.5971 | 23.1841 | 33.7712 | 0.01
5.1781 | 8.5891 | 7.1781 | 6.1781 | 8.7672 | 10.7672 | 8.5891 | 14.7672 | 23.5343 | 34.3015 | 5.1781 | 8.5991 | 7.1781 | 6.1781 | 8.7672 | 10.7672 | 8.5991 | 14.7772 | 23.5443 | 34.3115 | 0.01
2.0437 | 7.0219 | 4.0437 | 3.0437 | 4.0656 | 6.0656 | 7.0219 | 10.0656 | 14.1312 | 20.1968 | 2.0437 | 7.0319 | 4.0437 | 3.0437 | 4.0656 | 6.0656 | 7.0319 | 10.0756 | 14.1412 | 20.2068 | 0.01
7.546 | 9.773 | 9.546 | 8.546 | 12.319 | 14.319 | 9.773 | 18.319 | 30.6379 | 44.9569 | 7.546 | 9.783 | 9.546 | 8.546 | 12.319 | 14.319 | 9.783 | 18.329 | 30.6479 | 44.9669 | 0.01
5.6743 | 8.8371 | 7.6743 | 6.6743 | 9.5114 | 11.5114 | 8.8371 | 15.5114 | 25.0229 | 36.5343 | 5.6743 | 8.8471 | 7.6743 | 6.6743 | 9.5114 | 11.5114 | 8.8471 | 15.5214 | 25.0329 | 36.5443 | 0.01
4.0812 | 8.0406 | 6.0812 | 5.0812 | 7.1218 | 9.1218 | 8.0406 | 13.1218 | 20.2435 | 29.3653 | 4.0812 | 8.0506 | 6.0812 | 5.0812 | 7.1218 | 9.1218 | 8.0506 | 13.1318 | 20.2535 | 29.3753 | 0.01
9.5518 | 10.7759 | 11.5518 | 10.5518 | 15.3277 | 17.3277 | 10.7759 | 21.3277 | 36.6555 | 53.9832 | 9.5518 | 10.7859 | 11.5518 | 10.5518 | 15.3277 | 17.3277 | 10.7859 | 21.3377 | 36.6655 | 53.9932 | 0.01
7.9334 | 9.9667 | 9.9334 | 8.9334 | 12.9001 | 14.9001 | 9.9667 | 18.9001 | 31.8003 | 46.7004 | 7.9334 | 9.9767 | 9.9334 | 8.9334 | 12.9001 | 14.9001 | 9.9767 | 18.9101 | 31.8103 | 46.7104 | 0.01
4.7753 | 8.3876 | 6.7753 | 5.7753 | 8.1629 | 10.1629 | 8.3876 | 14.1629 | 22.3258 | 32.4888 | 4.7753 | 8.3976 | 6.7753 | 5.7753 | 8.1629 | 10.1629 | 8.3976 | 14.1729 | 22.3358 | 32.4988 | 0.01
8.5211 | 10.2606 | 10.5211 | 9.5211 | 13.7817 | 15.7817 | 10.2606 | 19.7817 | 33.5634 | 49.3451 | 8.5211 | 10.2706 | 10.5211 | 9.5211 | 13.7817 | 15.7817 | 10.2706 | 19.7917 | 33.5734 | 49.3551 | 0.01
5.7198 | 8.8599 | 7.7198 | 6.7198 | 9.5797 | 11.5797 | 8.8599 | 15.5797 | 25.1594 | 36.7391 | 5.7198 | 8.8699 | 7.7198 | 6.7198 | 9.5797 | 11.5797 | 8.8699 | 15.5897 | 25.1694 | 36.7491 | 0.01
4.9962 | 8.4981 | 6.9962 | 5.9962 | 8.4943 | 10.4943 | 8.4981 | 14.4943 | 22.9886 | 33.4829 | 4.9962 | 8.5081 | 6.9962 | 5.9962 | 8.4943 | 10.4943 | 8.5081 | 14.5043 | 22.9986 | 33.4929 | 0.01
5.1437 | 8.5718 | 7.1437 | 6.1437 | 8.7155 | 10.7155 | 8.5718 | 14.7155 | 23.4311 | 34.1466 | 5.1437 | 8.5818 | 7.1437 | 6.1437 | 8.7155 | 10.7155 | 8.5818 | 14.7255 | 23.4411 | 34.1566 | 0.01
5.9165 | 8.9583 | 7.9165 | 6.9165 | 9.8748 | 11.8748 | 8.9583 | 15.8748 | 25.7496 | 37.6243 | 5.9165 | 8.9683 | 7.9165 | 6.9165 | 9.8748 | 11.8748 | 8.9683 | 15.8848 | 25.7596 | 37.6343 | 0.01
6.5709 | 9.2855 | 8.5709 | 7.5709 | 10.8564 | 12.8564 | 9.2855 | 16.8564 | 27.7128 | 40.5691 | 6.5709 | 9.2955 | 8.5709 | 7.5709 | 10.8564 | 12.8564 | 9.2955 | 16.8664 | 27.7228 | 40.5791 | 0.01
4.407 | 8.2035 | 6.407 | 5.407 | 7.6105 | 9.6105 | 8.2035 | 13.6105 | 21.2209 | 30.8314 | 4.407 | 8.2135 | 6.407 | 5.407 | 7.6105 | 9.6105 | 8.2135 | 13.6205 | 21.2309 | 30.8414 | 0.01
7.6827 | 9.8413 | 9.6827 | 8.6827 | 12.524 | 14.524 | 9.8413 | 18.524 | 31.048 | 45.572 | 7.6827 | 9.8513 | 9.6827 | 8.6827 | 12.524 | 14.524 | 9.8513 | 18.534 | 31.058 | 45.582 | 0.01
5.0637 | 8.5318 | 7.0637 | 6.0637 | 8.5955 | 10.5955 | 8.5318 | 14.5955 | 23.191 | 33.7865 | 5.0637 | 8.5418 | 7.0637 | 6.0637 | 8.5955 | 10.5955 | 8.5418 | 14.6055 | 23.201 | 33.7965 | 0.01
3.1421 | 7.5711 | 5.1421 | 4.1421 | 5.7132 | 7.7132 | 7.5711 | 11.7132 | 17.4263 | 25.1395 | 3.1421 | 7.5811 | 5.1421 | 4.1421 | 5.7132 | 7.7132 | 7.5811 | 11.7232 | 17.4363 | 25.1495 | 0.01
8.3315 | 10.1657 | 10.3315 | 9.3315 | 13.4972 | 15.4972 | 10.1657 | 19.4972 | 32.9944 | 48.4916 | 8.3315 | 10.1757 | 10.3315 | 9.3315 | 13.4972 | 15.4972 | 10.1757 | 19.5072 | 33.0044 | 48.5016 | 0.01
7.0219 | 9.5109 | 9.0219 | 8.0219 | 11.5328 | 13.5328 | 9.5109 | 17.5328 | 29.0656 | 42.5985 | 7.0219 | 9.5209 | 9.0219 | 8.0219 | 11.5328 | 13.5328 | 9.5209 | 17.5428 | 29.0756 | 42.6085 | 0.01
7.4577 | 9.7289 | 9.4577 | 8.4577 | 12.1866 | 14.1866 | 9.7289 | 18.1866 | 30.3732 | 44.5599 | 7.4577 | 9.7389 | 9.4577 | 8.4577 | 12.1866 | 14.1866 | 9.7389 | 18.1966 | 30.3832 | 44.5699 | 0.01
8.7512 | 10.3756 | 10.7512 | 9.7512 | 14.1268 | 16.1268 | 10.3756 | 20.1268 | 34.2535 | 50.3803 | 8.7512 | 10.3856 | 10.7512 | 9.7512 | 14.1268 | 16.1268 | 10.3856 | 20.1368 | 34.2635 | 50.3903 | 0.01
3.186 | 7.593 | 5.186 | 4.186 | 5.779 | 7.779 | 7.593 | 11.779 | 17.558 | 25.337 | 3.186 | 7.603 | 5.186 | 4.186 | 5.779 | 7.779 | 7.603 | 11.789 | 17.568 | 25.347 | 0.01
3.9737 | 7.9868 | 5.9737 | 4.9737 | 6.9605 | 8.9605 | 7.9868 | 12.9605 | 19.921 | 28.8815 | 3.9737 | 7.9968 | 5.9737 | 4.9737 | 6.9605 | 8.9605 | 7.9968 | 12.9705 | 19.931 | 28.8915 | 0.01
6.1466 | 9.0733 | 8.1466 | 7.1466 | 10.2199 | 12.2199 | 9.0733 | 16.2199 | 26.4399 | 38.6598 | 6.1466 | 9.0833 | 8.1466 | 7.1466 | 10.2199 | 12.2199 | 9.0833 | 16.2299 | 26.4499 | 38.6698 | 0.01
4.2176 | 8.1088 | 6.2176 | 5.2176 | 7.3264 | 9.3264 | 8.1088 | 13.3264 | 20.6527 | 29.9791 | 4.2176 | 8.1188 | 6.2176 | 5.2176 | 7.3264 | 9.3264 | 8.1188 | 13.3364 | 20.6627 | 29.9891 | 0.01
6.6912 | 9.3456 | 8.6912 | 7.6912 | 11.0368 | 13.0368 | 9.3456 | 17.0368 | 28.0737 | 41.1105 | 6.6912 | 9.3556 | 8.6912 | 7.6912 | 11.0368 | 13.0368 | 9.3556 | 17.0468 | 28.0837 | 41.1205 | 0.01
4.7236 | 8.3618 | 6.7236 | 5.7236 | 8.0853 | 10.0853 | 8.3618 | 14.0853 | 22.1707 | 32.256 | 4.7236 | 8.3718 | 6.7236 | 5.7236 | 8.0853 | 10.0853 | 8.3718 | 14.0953 | 22.1807 | 32.266 | 0.01
4.7267 | 8.3634 | 6.7267 | 5.7267 | 8.0901 | 10.0901 | 8.3634 | 14.0901 | 22.1802 | 32.2704 | 4.7267 | 8.3734 | 6.7267 | 5.7267 | 8.0901 | 10.0901 | 8.3734 | 14.1001 | 22.1902 | 32.2804 | 0.01
7.199 | 9.5995 | 9.199 | 8.199 | 11.7985 | 13.7985 | 9.5995 | 17.7985 | 29.5969 | 43.3954 | 7.199 | 9.6095 | 9.199 | 8.199 | 11.7985 | 13.7985 | 9.6095 | 17.8085 | 29.6069 | 43.4054 | 0.01
3.7067 | 7.8534 | 5.7067 | 4.7067 | 6.5601 | 8.5601 | 7.8534 | 12.5601 | 19.1202 | 27.6803 | 3.7067 | 7.8634 | 5.7067 | 4.7067 | 6.5601 | 8.5601 | 7.8634 | 12.5701 | 19.1302 | 27.6903 | 0.01
5.995 | 8.9975 | 7.995 | 6.995 | 9.9925 | 11.9925 | 8.9975 | 15.9925 | 25.9851 | 37.9776 | 5.995 | 9.0075 | 7.995 | 6.995 | 9.9925 | 11.9925 | 9.0075 | 16.0025 | 25.9951 | 37.9876 | 0.01
5.0831 | 8.5415 | 7.0831 | 6.0831 | 8.6246 | 10.6246 | 8.5415 | 14.6246 | 23.2493 | 33.8739 | 5.0831 | 8.5515 | 7.0831 | 6.0831 | 8.6246 | 10.6246 | 8.5515 | 14.6346 | 23.2593 | 33.8839 | 0.01
6.1092 | 9.0546 | 8.1092 | 7.1092 | 10.1638 | 12.1638 | 9.0546 | 16.1638 | 26.3277 | 38.4915 | 6.1092 | 9.0646 | 8.1092 | 7.1092 | 10.1638 | 12.1638 | 9.0646 | 16.1738 | 26.3377 | 38.5015 | 0.01
8.5861 | 10.2931 | 10.5861 | 9.5861 | 13.8792 | 15.8792 | 10.2931 | 19.8792 | 33.7584 | 49.6375 | 8.5861 | 10.3031 | 10.5861 | 9.5861 | 13.8792 | 15.8792 | 10.3031 | 19.8892 | 33.7684 | 49.6475 | 0.01
5.3112 | 8.6556 | 7.3112 | 6.3112 | 8.9668 | 10.9668 | 8.6556 | 14.9668 | 23.9337 | 34.9005 | 5.3112 | 8.6656 | 7.3112 | 6.3112 | 8.9668 | 10.9668 | 8.6656 | 14.9768 | 23.9437 | 34.9105 | 0.01
3.0662 | 7.5331 | 5.0662 | 4.0662 | 5.5993 | 7.5993 | 7.5331 | 11.5993 | 17.1985 | 24.7978 | 3.0662 | 7.5431 | 5.0662 | 4.0662 | 5.5993 | 7.5993 | 7.5431 | 11.6093 | 17.2085 | 24.8078 | 0.01
5.713 | 8.8565 | 7.713 | 6.713 | 9.5695 | 11.5695 | 8.8565 | 15.5695 | 25.139 | 36.7085 | 5.713 | 8.8665 | 7.713 | 6.713 | 9.5695 | 11.5695 | 8.8665 | 15.5795 | 25.149 | 36.7185 | 0.01
2.1945 | 7.0972 | 4.1945 | 3.1945 | 4.2917 | 6.2917 | 7.0972 | 10.2917 | 14.5834 | 20.8751 | 2.1945 | 7.1072 | 4.1945 | 3.1945 | 4.2917 | 6.2917 | 7.1072 | 10.3017 | 14.5934 | 20.8851 | 0.01
4.0199 | 8.01 | 6.0199 | 5.0199 | 7.0299 | 9.0299 | 8.01 | 13.0299 | 20.0597 | 29.0896 | 4.0199 | 8.02 | 6.0199 | 5.0199 | 7.0299 | 9.0299 | 8.02 | 13.0399 | 20.0697 | 29.0996 | 0.01
6.6125 | 9.3062 | 8.6125 | 7.6125 | 10.9187 | 12.9187 | 9.3062 | 16.9187 | 27.8374 | 40.7562 | 6.6125 | 9.3162 | 8.6125 | 7.6125 | 10.9187 | 12.9187 | 9.3162 | 16.9287 | 27.8474 | 40.7662 | 0.01
6.4942 | 9.2471 | 8.4942 | 7.4942 | 10.7413 | 12.7413 | 9.2471 | 16.7413 | 27.4826 | 40.2239 | 6.4942 | 9.2571 | 8.4942 | 7.4942 | 10.7413 | 12.7413 | 9.2571 | 16.7513 | 27.4926 | 40.2339 | 0.01
5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 5.0921 | 8.556 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.556 | 14.6481 | 23.2863 | 33.9244 | 0.01
5.964 | 8.982 | 7.964 | 6.964 | 9.946 | 11.946 | 8.982 | 15.946 | 25.8919 | 37.8379 | 5.964 | 8.992 | 7.964 | 6.964 | 9.946 | 11.946 | 8.992 | 15.956 | 25.9019 | 37.8479 | 0.01
5.7816 | 8.8908 | 7.7816 | 6.7816 | 9.6724 | 11.6724 | 8.8908 | 15.6724 | 25.3449 | 37.0173 | 5.7816 | 8.9008 | 7.7816 | 6.7816 | 9.6724 | 11.6724 | 8.9008 | 15.6824 | 25.3549 | 37.0273 | 0.01
3.5707 | 7.7853 | 5.5707 | 4.5707 | 6.356 | 8.356 | 7.7853 | 12.356 | 18.712 | 27.068 | 3.5707 | 7.7953 | 5.5707 | 4.5707 | 6.356 | 8.356 | 7.7953 | 12.366 | 18.722 | 27.078 | 0.01
3.9955 | 7.9978 | 5.9955 | 4.9955 | 6.9933 | 8.9933 | 7.9978 | 12.9933 | 19.9866 | 28.9799 | 3.9955 | 8.0078 | 5.9955 | 4.9955 | 6.9933 | 8.9933 | 8.0078 | 13.0033 | 19.9966 | 28.9899 | 0.01
6.0997 | 9.0499 | 8.0997 | 7.0997 | 10.1496 | 12.1496 | 9.0499 | 16.1496 | 26.2992 | 38.4487 | 6.0997 | 9.0599 | 8.0997 | 7.0997 | 10.1496 | 12.1496 | 9.0599 | 16.1596 | 26.3092 | 38.4587 | 0.01
7.8375 | 9.9188 | 9.8375 | 8.8375 | 12.7563 | 14.7563 | 9.9188 | 18.7563 | 31.5125 | 46.2688 | 7.8375 | 9.9288 | 9.8375 | 8.8375 | 12.7563 | 14.7563 | 9.9288 | 18.7663 | 31.5225 | 46.2788 | 0.01
6.5393 | 9.2696 | 8.5393 | 7.5393 | 10.8089 | 12.8089 | 9.2696 | 16.8089 | 27.6178 | 40.4267 | 6.5393 | 9.2796 | 8.5393 | 7.5393 | 10.8089 | 12.8089 | 9.2796 | 16.8189 | 27.6278 | 40.4367 | 0.01
3.8684 | 7.9342 | 5.8684 | 4.8684 | 6.8026 | 8.8026 | 7.9342 | 12.8026 | 19.6051 | 28.4077 | 3.8684 | 7.9442 | 5.8684 | 4.8684 | 6.8026 | 8.8026 | 7.9442 | 12.8126 | 19.6151 | 28.4177 | 0.01
5.8862 | 8.9431 | 7.8862 | 6.8862 | 9.8293 | 11.8293 | 8.9431 | 15.8293 | 25.6586 | 37.4878 | 5.8862 | 8.9531 | 7.8862 | 6.8862 | 9.8293 | 11.8293 | 8.9531 | 15.8393 | 25.6686 | 37.4978 | 0.01
4.754 | 8.377 | 6.754 | 5.754 | 8.131 | 10.131 | 8.377 | 14.131 | 22.262 | 32.3929 | 4.754 | 8.387 | 6.754 | 5.754 | 8.131 | 10.131 | 8.387 | 14.141 | 22.272 | 32.4029 | 0.01
3.8834 | 7.9417 | 5.8834 | 4.8834 | 6.8251 | 8.8251 | 7.9417 | 12.8251 | 19.6503 | 28.4754 | 3.8834 | 7.9517 | 5.8834 | 4.8834 | 6.8251 | 8.8251 | 7.9517 | 12.8351 | 19.6603 | 28.4854 | 0.01
5.5401 | 8.7701 | 7.5401 | 6.5401 | 9.3102 | 11.3102 | 8.7701 | 15.3102 | 24.6204 | 35.9306 | 5.5401 | 8.7801 | 7.5401 | 6.5401 | 9.3102 | 11.3102 | 8.7801 | 15.3202 | 24.6304 | 35.9406 | 0.01
6.0247 | 9.0124 | 8.0247 | 7.0247 | 10.0371 | 12.0371 | 9.0124 | 16.0371 | 26.0741 | 38.1112 | 6.0247 | 9.0224 | 8.0247 | 7.0247 | 10.0371 | 12.0371 | 9.0224 | 16.0471 | 26.0841 | 38.1212 | 0.01
4.9316 | 8.4658 | 6.9316 | 5.9316 | 8.3975 | 10.3975 | 8.4658 | 14.3975 | 22.7949 | 33.1924 | 4.9316 | 8.4758 | 6.9316 | 5.9316 | 8.3975 | 10.3975 | 8.4758 | 14.4075 | 22.8049 | 33.2024 | 0.01
9.3444 | 10.6722 | 11.3444 | 10.3444 | 15.0166 | 17.0166 | 10.6722 | 21.0166 | 36.0332 | 53.0498 | 9.3444 | 10.6822 | 11.3444 | 10.3444 | 15.0166 | 17.0166 | 10.6822 | 21.0266 | 36.0432 | 53.0598 | 0.01
6.4224 | 9.2112 | 8.4224 | 7.4224 | 10.6336 | 12.6336 | 9.2112 | 16.6336 | 27.2672 | 39.9008 | 6.4224 | 9.2212 | 8.4224 | 7.4224 | 10.6336 | 12.6336 | 9.2212 | 16.6436 | 27.2772 | 39.9108 | 0.01
5.0339 | 8.5169 | 7.0339 | 6.0339 | 8.5508 | 10.5508 | 8.5169 | 14.5508 | 23.1016 | 33.6524 | 5.0339 | 8.5269 | 7.0339 | 6.0339 | 8.5508 | 10.5508 | 8.5269 | 14.5608 | 23.1116 | 33.6624 | 0.01
5.9344 | 8.9672 | 7.9344 | 6.9344 | 9.9016 | 11.9016 | 8.9672 | 15.9016 | 25.8033 | 37.7049 | 5.9344 | 8.9772 | 7.9344 | 6.9344 | 9.9016 | 11.9016 | 8.9772 | 15.9116 | 25.8133 | 37.7149 | 0.01
6.8634 | 9.4317 | 8.8634 | 7.8634 | 11.295 | 13.295 | 9.4317 | 17.295 | 28.5901 | 41.8851 | 6.8634 | 9.4417 | 8.8634 | 7.8634 | 11.295 | 13.295 | 9.4417 | 17.305 | 28.6001 | 41.8951 | 0.01
3.9905 | 7.9952 | 5.9905 | 4.9905 | 6.9857 | 8.9857 | 7.9952 | 12.9857 | 19.9714 | 28.9572 | 3.9905 | 8.0052 | 5.9905 | 4.9905 | 6.9857 | 8.9857 | 8.0052 | 12.9957 | 19.9814 | 28.9672 | 0.01
7.2021 | 9.601 | 9.2021 | 8.2021 | 11.8031 | 13.8031 | 9.601 | 17.8031 | 29.6063 | 43.4094 | 7.2021 | 9.611 | 9.2021 | 8.2021 | 11.8031 | 13.8031 | 9.611 | 17.8131 | 29.6163 | 43.4194 | 0.01
0.53517 | 6.2676 | 2.5352 | 1.5352 | 1.8028 | 3.8028 | 6.2676 | 7.8028 | 9.6055 | 13.4083 | 0.53517 | 6.2776 | 2.5352 | 1.5352 | 1.8028 | 3.8028 | 6.2776 | 7.8128 | 9.6155 | 13.4183 | 0.01
5.5684 | 8.7842 | 7.5684 | 6.5684 | 9.3525 | 11.3525 | 8.7842 | 15.3525 | 24.7051 | 36.0576 | 5.5684 | 8.7942 | 7.5684 | 6.5684 | 9.3525 | 11.3525 | 8.7942 | 15.3625 | 24.7151 | 36.0676 | 0.01
5.3874 | 8.6937 | 7.3874 | 6.3874 | 9.081 | 11.081 | 8.6937 | 15.081 | 24.1621 | 35.2431 | 5.3874 | 8.7037 | 7.3874 | 6.3874 | 9.081 | 11.081 | 8.7037 | 15.091 | 24.1721 | 35.2531 | 0.01
6.5294 | 9.2647 | 8.5294 | 7.5294 | 10.7942 | 12.7942 | 9.2647 | 16.7942 | 27.5883 | 40.3825 | 6.5294 | 9.2747 | 8.5294 | 7.5294 | 10.7942 | 12.7942 | 9.2747 | 16.8042 | 27.5983 | 40.3925 | 0.01
8.7496 | 10.3748 | 10.7496 | 9.7496 | 14.1244 | 16.1244 | 10.3748 | 20.1244 | 34.2488 | 50.3732 | 8.7496 | 10.3848 | 10.7496 | 9.7496 | 14.1244 | 16.1244 | 10.3848 | 20.1344 | 34.2588 | 50.3832 | 0.01
5.9569 | 8.9785 | 7.9569 | 6.9569 | 9.9354 | 11.9354 | 8.9785 | 15.9354 | 25.8708 | 37.8062 | 5.9569 | 8.9885 | 7.9569 | 6.9569 | 9.9354 | 11.9354 | 8.9885 | 15.9454 | 25.8808 | 37.8162 | 0.01
5.1926 | 8.5963 | 7.1926 | 6.1926 | 8.7889 | 10.7889 | 8.5963 | 14.7889 | 23.5777 | 34.3666 | 5.1926 | 8.6063 | 7.1926 | 6.1926 | 8.7889 | 10.7889 | 8.6063 | 14.7989 | 23.5877 | 34.3766 | 0.01
4.5049 | 8.2524 | 6.5049 | 5.5049 | 7.7573 | 9.7573 | 8.2524 | 13.7573 | 21.5146 | 31.272 | 4.5049 | 8.2624 | 6.5049 | 5.5049 | 7.7573 | 9.7573 | 8.2624 | 13.7673 | 21.5246 | 31.282 | 0.01
4.4453 | 8.2227 | 6.4453 | 5.4453 | 7.668 | 9.668 | 8.2227 | 13.668 | 21.336 | 31.004 | 4.4453 | 8.2327 | 6.4453 | 5.4453 | 7.668 | 9.668 | 8.2327 | 13.678 | 21.346 | 31.014 | 0.01
8.9107 | 10.4553 | 10.9107 | 9.9107 | 14.366 | 16.366 | 10.4553 | 20.366 | 34.7321 | 51.0981 | 8.9107 | 10.4653 | 10.9107 | 9.9107 | 14.366 | 16.366 | 10.4653 | 20.376 | 34.7421 | 51.1081 | 0.01
5.5784 | 8.7892 | 7.5784 | 6.5784 | 9.3676 | 11.3676 | 8.7892 | 15.3676 | 24.7351 | 36.1027 | 5.5784 | 8.7992 | 7.5784 | 6.5784 | 9.3676 | 11.3676 | 8.7992 | 15.3776 | 24.7451 | 36.1127 | 0.01
6.5968 | 9.2984 | 8.5968 | 7.5968 | 10.8952 | 12.8952 | 9.2984 | 16.8952 | 27.7903 | 40.6855 | 6.5968 | 9.3084 | 8.5968 | 7.5968 | 10.8952 | 12.8952 | 9.3084 | 16.9052 | 27.8003 | 40.6955 | 0.01
9.5841 | 10.7921 | 11.5841 | 10.5841 | 15.3762 | 17.3762 | 10.7921 | 21.3762 | 36.7524 | 54.1286 | 9.5841 | 10.8021 | 11.5841 | 10.5841 | 15.3762 | 17.3762 | 10.8021 | 21.3862 | 36.7624 | 54.1386 | 0.01
7.1421 | 9.5711 | 9.1421 | 8.1421 | 11.7132 | 13.7132 | 9.5711 | 17.7132 | 29.4264 | 43.1397 | 7.1421 | 9.5811 | 9.1421 | 8.1421 | 11.7132 | 13.7132 | 9.5811 | 17.7232 | 29.4364 | 43.1497 | 0.01
6.9164 | 9.4582 | 8.9164 | 7.9164 | 11.3746 | 13.3746 | 9.4582 | 17.3746 | 28.7492 | 42.1238 | 6.9164 | 9.4682 | 8.9164 | 7.9164 | 11.3746 | 13.3746 | 9.4682 | 17.3846 | 28.7592 | 42.1338 | 0.01
8.2153 | 10.1076 | 10.2153 | 9.2153 | 13.3229 | 15.3229 | 10.1076 | 19.3229 | 32.6459 | 47.9688 | 8.2153 | 10.1176 | 10.2153 | 9.2153 | 13.3229 | 15.3229 | 10.1176 | 19.3329 | 32.6559 | 47.9788 | 0.01
5.5263 | 8.7631 | 7.5263 | 6.5263 | 9.2894 | 11.2894 | 8.7631 | 15.2894 | 24.5789 | 35.8683 | 5.5263 | 8.7731 | 7.5263 | 6.5263 | 9.2894 | 11.2894 | 8.7731 | 15.2994 | 24.5889 | 35.8783 | 0.01
11.0337 | 11.5168 | 13.0337 | 12.0337 | 17.5505 | 19.5505 | 11.5168 | 23.5505 | 41.101 | 60.6514 | 11.0337 | 11.5268 | 13.0337 | 12.0337 | 17.5505 | 19.5505 | 11.5268 | 23.5605 | 41.111 | 60.6614 | 0.01
6.0016 | 9.0008 | 8.0016 | 7.0016 | 10.0024 | 12.0024 | 9.0008 | 16.0024 | 26.0048 | 38.0072 | 6.0016 | 9.0108 | 8.0016 | 7.0016 | 10.0024 | 12.0024 | 9.0108 | 16.0124 | 26.0148 | 38.0172 | 0.01
10.3738 | 11.1869 | 12.3738 | 11.3738 | 16.5607 | 18.5607 | 11.1869 | 22.5607 | 39.1215 | 57.6822 | 10.3738 | 11.1969 | 12.3738 | 11.3738 | 16.5607 | 18.5607 | 11.1969 | 22.5707 | 39.1315 | 57.6922 | 0.01
6.4121 | 9.206 | 8.4121 | 7.4121 | 10.6181 | 12.6181 | 9.206 | 16.6181 | 27.2363 | 39.8544 | 6.4121 | 9.216 | 8.4121 | 7.4121 | 10.6181 | 12.6181 | 9.216 | 16.6281 | 27.2463 | 39.8644 | 0.01
9.217 | 10.6085 | 11.217 | 10.217 | 14.8254 | 16.8254 | 10.6085 | 20.8254 | 35.6509 | 52.4763 | 9.217 | 10.6185 | 11.217 | 10.217 | 14.8254 | 16.8254 | 10.6185 | 20.8354 | 35.6609 | 52.4863 | 0.01
9.7797 | 10.8898 | 11.7797 | 10.7797 | 15.6695 | 17.6695 | 10.8898 | 21.6695 | 37.3391 | 55.0086 | 9.7797 | 10.8998 | 11.7797 | 10.7797 | 15.6695 | 17.6695 | 10.8998 | 21.6795 | 37.3491 | 55.0186 | 0.01
5.0423 | 8.5211 | 7.0423 | 6.0423 | 8.5634 | 10.5634 | 8.5211 | 14.5634 | 23.1268 | 33.6903 | 5.0423 | 8.5311 | 7.0423 | 6.0423 | 8.5634 | 10.5634 | 8.5311 | 14.5734 | 23.1368 | 33.7003 | 0.01
4.3481 | 8.174 | 6.3481 | 5.3481 | 7.5221 | 9.5221 | 8.174 | 13.5221 | 21.0442 | 30.5663 | 4.3481 | 8.184 | 6.3481 | 5.3481 | 7.5221 | 9.5221 | 8.184 | 13.5321 | 21.0542 | 30.5763 | 0.01
7.1758 | 9.5879 | 9.1758 | 8.1758 | 11.7637 | 13.7637 | 9.5879 | 17.7637 | 29.5274 | 43.2911 | 7.1758 | 9.5979 | 9.1758 | 8.1758 | 11.7637 | 13.7637 | 9.5979 | 17.7737 | 29.5374 | 43.3011 | 0.01
4.6681 | 8.3341 | 6.6681 | 5.6681 | 8.0022 | 10.0022 | 8.3341 | 14.0022 | 22.0043 | 32.0065 | 4.6681 | 8.3441 | 6.6681 | 5.6681 | 8.0022 | 10.0022 | 8.3441 | 14.0122 | 22.0143 | 32.0165 | 0.01
1.8921 | 6.946 | 3.8921 | 2.8921 | 3.8381 | 5.8381 | 6.946 | 9.8381 | 13.6762 | 19.5143 | 1.8921 | 6.956 | 3.8921 | 2.8921 | 3.8381 | 5.8381 | 6.956 | 9.8481 | 13.6862 | 19.5243 | 0.01
5.0109 | 8.5055 | 7.0109 | 6.0109 | 8.5164 | 10.5164 | 8.5055 | 14.5164 | 23.0328 | 33.5492 | 5.0109 | 8.5155 | 7.0109 | 6.0109 | 8.5164 | 10.5164 | 8.5155 | 14.5264 | 23.0428 | 33.5592 | 0.01
3.8584 | 7.9292 | 5.8584 | 4.8584 | 6.7875 | 8.7875 | 7.9292 | 12.7875 | 19.5751 | 28.3626 | 3.8584 | 7.9392 | 5.8584 | 4.8584 | 6.7875 | 8.7875 | 7.9392 | 12.7975 | 19.5851 | 28.3726 | 0.01
6.4966 | 9.2483 | 8.4966 | 7.4966 | 10.7448 | 12.7448 | 9.2483 | 16.7448 | 27.4897 | 40.2345 | 6.4966 | 9.2583 | 8.4966 | 7.4966 | 10.7448 | 12.7448 | 9.2583 | 16.7548 | 27.4997 | 40.2445 | 0.01
7.0352 | 9.5176 | 9.0352 | 8.0352 | 11.5527 | 13.5527 | 9.5176 | 17.5527 | 29.1055 | 42.6582 | 7.0352 | 9.5276 | 9.0352 | 8.0352 | 11.5527 | 13.5527 | 9.5276 | 17.5627 | 29.1155 | 42.6682 | 0.01
6.1885 | 9.0943 | 8.1885 | 7.1885 | 10.2828 | 12.2828 | 9.0943 | 16.2828 | 26.5656 | 38.8484 | 6.1885 | 9.1043 | 8.1885 | 7.1885 | 10.2828 | 12.2828 | 9.1043 | 16.2928 | 26.5756 | 38.8584 | 0.01
5.8998 | 8.9499 | 7.8998 | 6.8998 | 9.8497 | 11.8497 | 8.9499 | 15.8497 | 25.6995 | 37.5492 | 5.8998 | 8.9599 | 7.8998 | 6.8998 | 9.8497 | 11.8497 | 8.9599 | 15.8597 | 25.7095 | 37.5592 | 0.01
3.7522 | 7.8761 | 5.7522 | 4.7522 | 6.6283 | 8.6283 | 7.8761 | 12.6283 | 19.2566 | 27.8849 | 3.7522 | 7.8861 | 5.7522 | 4.7522 | 6.6283 | 8.6283 | 7.8861 | 12.6383 | 19.2666 | 27.8949 | 0.01
6.776 | 9.388 | 8.776 | 7.776 | 11.164 | 13.164 | 9.388 | 17.164 | 28.328 | 41.492 | 6.776 | 9.398 | 8.776 | 7.776 | 11.164 | 13.164 | 9.398 | 17.174 | 28.338 | 41.502 | 0.01
5.7807 | 8.8903 | 7.7807 | 6.7807 | 9.671 | 11.671 | 8.8903 | 15.671 | 25.3421 | 37.0131 | 5.7807 | 8.9003 | 7.7807 | 6.7807 | 9.671 | 11.671 | 8.9003 | 15.681 | 25.3521 | 37.0231 | 0.01
3.3449 | 7.6725 | 5.3449 | 4.3449 | 6.0174 | 8.0174 | 7.6725 | 12.0174 | 18.0348 | 26.0522 | 3.3449 | 7.6825 | 5.3449 | 4.3449 | 6.0174 | 8.0174 | 7.6825 | 12.0274 | 18.0448 | 26.0622 | 0.01
3.0968 | 7.5484 | 5.0968 | 4.0968 | 5.6452 | 7.6452 | 7.5484 | 11.6452 | 17.2904 | 24.9355 | 3.0968 | 7.5584 | 5.0968 | 4.0968 | 5.6452 | 7.6452 | 7.5584 | 11.6552 | 17.3004 | 24.9455 | 0.01
7.9137 | 9.9569 | 9.9137 | 8.9137 | 12.8706 | 14.8706 | 9.9569 | 18.8706 | 31.7412 | 46.6118 | 7.9137 | 9.9669 | 9.9137 | 8.9137 | 12.8706 | 14.8706 | 9.9669 | 18.8806 | 31.7512 | 46.6218 | 0.01
8.1265 | 10.0633 | 10.1265 | 9.1265 | 13.1898 | 15.1898 | 10.0633 | 19.1898 | 32.3795 | 47.5693 | 8.1265 | 10.0733 | 10.1265 | 9.1265 | 13.1898 | 15.1898 | 10.0733 | 19.1998 | 32.3895 | 47.5793 | 0.01
4.2244 | 8.1122 | 6.2244 | 5.2244 | 7.3366 | 9.3366 | 8.1122 | 13.3366 | 20.6732 | 30.0098 | 4.2244 | 8.1222 | 6.2244 | 5.2244 | 7.3366 | 9.3366 | 8.1222 | 13.3466 | 20.6832 | 30.0198 | 0.01
6.3537 | 9.1768 | 8.3537 | 7.3537 | 10.5305 | 12.5305 | 9.1768 | 16.5305 | 27.061 | 39.5914 | 6.3537 | 9.1868 | 8.3537 | 7.3537 | 10.5305 | 12.5305 | 9.1868 | 16.5405 | 27.071 | 39.6014 | 0.01
11.168 | 11.584 | 13.168 | 12.168 | 17.7521 | 19.7521 | 11.584 | 23.7521 | 41.5041 | 61.2562 | 11.168 | 11.594 | 13.168 | 12.168 | 17.7521 | 19.7521 | 11.594 | 23.7621 | 41.5141 | 61.2662 | 0.01
5.4518 | 8.7259 | 7.4518 | 6.4518 | 9.1778 | 11.1778 | 8.7259 | 15.1778 | 24.3555 | 35.5333 | 5.4518 | 8.7359 | 7.4518 | 6.4518 | 9.1778 | 11.1778 | 8.7359 | 15.1878 | 24.3655 | 35.5433 | 0.01
6.0492 | 9.0246 | 8.0492 | 7.0492 | 10.0738 | 12.0738 | 9.0246 | 16.0738 | 26.1476 | 38.2214 | 6.0492 | 9.0346 | 8.0492 | 7.0492 | 10.0738 | 12.0738 | 9.0346 | 16.0838 | 26.1576 | 38.2314 | 0.01
7.4105 | 9.7052 | 9.4105 | 8.4105 | 12.1157 | 14.1157 | 9.7052 | 18.1157 | 30.2314 | 44.3471 | 7.4105 | 9.7152 | 9.4105 | 8.4105 | 12.1157 | 14.1157 | 9.7152 | 18.1257 | 30.2414 | 44.3571 | 0.01
3.5875 | 7.7938 | 5.5875 | 4.5875 | 6.3813 | 8.3813 | 7.7938 | 12.3813 | 18.7626 | 27.1439 | 3.5875 | 7.8038 | 5.5875 | 4.5875 | 6.3813 | 8.3813 | 7.8038 | 12.3913 | 18.7726 | 27.1539 | 0.01
5.9969 | 8.9984 | 7.9969 | 6.9969 | 9.9953 | 11.9953 | 8.9984 | 15.9953 | 25.9906 | 37.9859 | 5.9969 | 9.0084 | 7.9969 | 6.9969 | 9.9953 | 11.9953 | 9.0084 | 16.0053 | 26.0006 | 37.9959 | 0.01
4.4596 | 8.2298 | 6.4596 | 5.4596 | 7.6894 | 9.6894 | 8.2298 | 13.6894 | 21.3787 | 31.0681 | 4.4596 | 8.2398 | 6.4596 | 5.4596 | 7.6894 | 9.6894 | 8.2398 | 13.6994 | 21.3887 | 31.0781 | 0.01
4.6953 | 8.3477 | 6.6953 | 5.6953 | 8.043 | 10.043 | 8.3477 | 14.043 | 22.0859 | 32.1289 | 4.6953 | 8.3577 | 6.6953 | 5.6953 | 8.043 | 10.043 | 8.3577 | 14.053 | 22.0959 | 32.1389 | 0.01
6.2341 | 9.117 | 8.2341 | 7.2341 | 10.3511 | 12.3511 | 9.117 | 16.3511 | 26.7023 | 39.0534 | 6.2341 | 9.127 | 8.2341 | 7.2341 | 10.3511 | 12.3511 | 9.127 | 16.3611 | 26.7123 | 39.0634 | 0.01
10.223 | 11.1115 | 12.223 | 11.223 | 16.3345 | 18.3345 | 11.1115 | 22.3345 | 38.669 | 57.0034 | 10.223 | 11.1215 | 12.223 | 11.223 | 16.3345 | 18.3345 | 11.1215 | 22.3445 | 38.679 | 57.0134 | 0.01
7.3917 | 9.6958 | 9.3917 | 8.3917 | 12.0875 | 14.0875 | 9.6958 | 18.0875 | 30.1751 | 44.2626 | 7.3917 | 9.7058 | 9.3917 | 8.3917 | 12.0875 | 14.0875 | 9.7058 | 18.0975 | 30.1851 | 44.2726 | 0.01
7.055 | 9.5275 | 9.055 | 8.055 | 11.5825 | 13.5825 | 9.5275 | 17.5825 | 29.1649 | 42.7474 | 7.055 | 9.5375 | 9.055 | 8.055 | 11.5825 | 13.5825 | 9.5375 | 17.5925 | 29.1749 | 42.7574 | 0.01
2.1916 | 7.0958 | 4.1916 | 3.1916 | 4.2875 | 6.2875 | 7.0958 | 10.2875 | 14.5749 | 20.8624 | 2.1916 | 7.1058 | 4.1916 | 3.1916 | 4.2875 | 6.2875 | 7.1058 | 10.2975 | 14.5849 | 20.8724 | 0.01
4.1961 | 8.098 | 6.1961 | 5.1961 | 7.2941 | 9.2941 | 8.098 | 13.2941 | 20.5882 | 29.8823 | 4.1961 | 8.108 | 6.1961 | 5.1961 | 7.2941 | 9.2941 | 8.108 | 13.3041 | 20.5982 | 29.8923 | 0.01
9.3012 | 10.6506 | 11.3012 | 10.3012 | 14.9518 | 16.9518 | 10.6506 | 20.9518 | 35.9036 | 52.8554 | 9.3012 | 10.6606 | 11.3012 | 10.3012 | 14.9518 | 16.9518 | 10.6606 | 20.9618 | 35.9136 | 52.8654 | 0.01
6.1032 | 9.0516 | 8.1032 | 7.1032 | 10.1549 | 12.1549 | 9.0516 | 16.1549 | 26.3097 | 38.4646 | 6.1032 | 9.0616 | 8.1032 | 7.1032 | 10.1549 | 12.1549 | 9.0616 | 16.1649 | 26.3197 | 38.4746 | 0.01
10.9776 | 11.4888 | 12.9776 | 11.9776 | 17.4663 | 19.4663 | 11.4888 | 23.4663 | 40.9327 | 60.399 | 10.9776 | 11.4988 | 12.9776 | 11.9776 | 17.4663 | 19.4663 | 11.4988 | 23.4763 | 40.9427 | 60.409 | 0.01
3.8066 | 7.9033 | 5.8066 | 4.8066 | 6.7099 | 8.7099 | 7.9033 | 12.7099 | 19.4198 | 28.1297 | 3.8066 | 7.9133 | 5.8066 | 4.8066 | 6.7099 | 8.7099 | 7.9133 | 12.7199 | 19.4298 | 28.1397 | 0.01
4.2458 | 8.1229 | 6.2458 | 5.2458 | 7.3688 | 9.3688 | 8.1229 | 13.3688 | 20.7375 | 30.1063 | 4.2458 | 8.1329 | 6.2458 | 5.2458 | 7.3688 | 9.3688 | 8.1329 | 13.3788 | 20.7475 | 30.1163 | 0.01
6.4005 | 9.2003 | 8.4005 | 7.4005 | 10.6008 | 12.6008 | 9.2003 | 16.6008 | 27.2016 | 39.8024 | 6.4005 | 9.2103 | 8.4005 | 7.4005 | 10.6008 | 12.6008 | 9.2103 | 16.6108 | 27.2116 | 39.8124 | 0.01
4.7583 | 8.3791 | 6.7583 | 5.7583 | 8.1374 | 10.1374 | 8.3791 | 14.1374 | 22.2748 | 32.4122 | 4.7583 | 8.3891 | 6.7583 | 5.7583 | 8.1374 | 10.1374 | 8.3891 | 14.1474 | 22.2848 | 32.4222 | 0.01
6.5861 | 9.293 | 8.5861 | 7.5861 | 10.8791 | 12.8791 | 9.293 | 16.8791 | 27.7582 | 40.6373 | 6.5861 | 9.303 | 8.5861 | 7.5861 | 10.8791 | 12.8791 | 9.303 | 16.8891 | 27.7682 | 40.6473 | 0.01
8.5851 | 10.2925 | 10.5851 | 9.5851 | 13.8776 | 15.8776 | 10.2925 | 19.8776 | 33.7552 | 49.6328 | 8.5851 | 10.3025 | 10.5851 | 9.5851 | 13.8776 | 15.8776 | 10.3025 | 19.8876 | 33.7652 | 49.6428 | 0.01
8.0992 | 10.0496 | 10.0992 | 9.0992 | 13.1489 | 15.1489 | 10.0496 | 19.1489 | 32.2977 | 47.4466 | 8.0992 | 10.0596 | 10.0992 | 9.0992 | 13.1489 | 15.1489 | 10.0596 | 19.1589 | 32.3077 | 47.4566 | 0.01
6.8226 | 9.4113 | 8.8226 | 7.8226 | 11.2338 | 13.2338 | 9.4113 | 17.2338 | 28.4677 | 41.7015 | 6.8226 | 9.4213 | 8.8226 | 7.8226 | 11.2338 | 13.2338 | 9.4213 | 17.2438 | 28.4777 | 41.7115 | 0.01
5.9018 | 8.9509 | 7.9018 | 6.9018 | 9.8527 | 11.8527 | 8.9509 | 15.8527 | 25.7054 | 37.5582 | 5.9018 | 8.9609 | 7.9018 | 6.9018 | 9.8527 | 11.8527 | 8.9609 | 15.8627 | 25.7154 | 37.5682 | 0.01
3.8038 | 7.9019 | 5.8038 | 4.8038 | 6.7057 | 8.7057 | 7.9019 | 12.7057 | 19.4114 | 28.1172 | 3.8038 | 7.9119 | 5.8038 | 4.8038 | 6.7057 | 8.7057 | 7.9119 | 12.7157 | 19.4214 | 28.1272 | 0.01
7.6562 | 9.8281 | 9.6562 | 8.6562 | 12.4843 | 14.4843 | 9.8281 | 18.4843 | 30.9687 | 45.453 | 7.6562 | 9.8381 | 9.6562 | 8.6562 | 12.4843 | 14.4843 | 9.8381 | 18.4943 | 30.9787 | 45.463 | 0.01
5.9438 | 8.9719 | 7.9438 | 6.9438 | 9.9156 | 11.9156 | 8.9719 | 15.9156 | 25.8313 | 37.7469 | 5.9438 | 8.9819 | 7.9438 | 6.9438 | 9.9156 | 11.9156 | 8.9819 | 15.9256 | 25.8413 | 37.7569 | 0.01
4.5206 | 8.2603 | 6.5206 | 5.5206 | 7.7809 | 9.7809 | 8.2603 | 13.7809 | 21.5618 | 31.3428 | 4.5206 | 8.2703 | 6.5206 | 5.5206 | 7.7809 | 9.7809 | 8.2703 | 13.7909 | 21.5718 | 31.3528 | 0.01
6.1925 | 9.0963 | 8.1925 | 7.1925 | 10.2888 | 12.2888 | 9.0963 | 16.2888 | 26.5776 | 38.8664 | 6.1925 | 9.1063 | 8.1925 | 7.1925 | 10.2888 | 12.2888 | 9.1063 | 16.2988 | 26.5876 | 38.8764 | 0.01
6.2748 | 9.1374 | 8.2748 | 7.2748 | 10.4122 | 12.4122 | 9.1374 | 16.4122 | 26.8244 | 39.2366 | 6.2748 | 9.1474 | 8.2748 | 7.2748 | 10.4122 | 12.4122 | 9.1474 | 16.4222 | 26.8344 | 39.2466 | 0.01
6.3519 | 9.176 | 8.3519 | 7.3519 | 10.5279 | 12.5279 | 9.176 | 16.5279 | 27.0558 | 39.5837 | 6.3519 | 9.186 | 8.3519 | 7.3519 | 10.5279 | 12.5279 | 9.186 | 16.5379 | 27.0658 | 39.5937 | 0.01
4.0229 | 8.0115 | 6.0229 | 5.0229 | 7.0344 | 9.0344 | 8.0115 | 13.0344 | 20.0687 | 29.1031 | 4.0229 | 8.0215 | 6.0229 | 5.0229 | 7.0344 | 9.0344 | 8.0215 | 13.0444 | 20.0787 | 29.1131 | 0.01
5.9303 | 8.9651 | 7.9303 | 6.9303 | 9.8954 | 11.8954 | 8.9651 | 15.8954 | 25.7909 | 37.6863 | 5.9303 | 8.9751 | 7.9303 | 6.9303 | 9.8954 | 11.8954 | 8.9751 | 15.9054 | 25.8009 | 37.6963 | 0.01
6.936 | 9.468 | 8.936 | 7.936 | 11.404 | 13.404 | 9.468 | 17.404 | 28.808 | 42.2119 | 6.936 | 9.478 | 8.936 | 7.936 | 11.404 | 13.404 | 9.478 | 17.414 | 28.818 | 42.2219 | 0.01
7.0226 | 9.5113 | 9.0226 | 8.0226 | 11.5339 | 13.5339 | 9.5113 | 17.5339 | 29.0677 | 42.6016 | 7.0226 | 9.5213 | 9.0226 | 8.0226 | 11.5339 | 13.5339 | 9.5213 | 17.5439 | 29.0777 | 42.6116 | 0.01
2.7903 | 7.3951 | 4.7903 | 3.7903 | 5.1854 | 7.1854 | 7.3951 | 11.1854 | 16.3708 | 23.5562 | 2.7903 | 7.4051 | 4.7903 | 3.7903 | 5.1854 | 7.1854 | 7.4051 | 11.1954 | 16.3808 | 23.5662 | 0.01
6.8957 | 9.4479 | 8.8957 | 7.8957 | 11.3436 | 13.3436 | 9.4479 | 17.3436 | 28.6871 | 42.0307 | 6.8957 | 9.4579 | 8.8957 | 7.8957 | 11.3436 | 13.3436 | 9.4579 | 17.3536 | 28.6971 | 42.0407 | 0.01
6.0138 | 9.0069 | 8.0138 | 7.0138 | 10.0208 | 12.0208 | 9.0069 | 16.0208 | 26.0415 | 38.0623 | 6.0138 | 9.0169 | 8.0138 | 7.0138 | 10.0208 | 12.0208 | 9.0169 | 16.0308 | 26.0515 | 38.0723 | 0.01
3.8657 | 7.9328 | 5.8657 | 4.8657 | 6.7985 | 8.7985 | 7.9328 | 12.7985 | 19.597 | 28.3955 | 3.8657 | 7.9428 | 5.8657 | 4.8657 | 6.7985 | 8.7985 | 7.9428 | 12.8085 | 19.607 | 28.4055 | 0.01
7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 7.4889 | 9.7544 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7544 | 18.2433 | 30.4766 | 44.7098 | 0.01
8.8202 | 10.4101 | 10.8202 | 9.8202 | 14.2303 | 16.2303 | 10.4101 | 20.2303 | 34.4605 | 50.6908 | 8.8202 | 10.4201 | 10.8202 | 9.8202 | 14.2303 | 16.2303 | 10.4201 | 20.2403 | 34.4705 | 50.7008 | 0.01
7.8196 | 9.9098 | 9.8196 | 8.8196 | 12.7294 | 14.7294 | 9.9098 | 18.7294 | 31.4588 | 46.1882 | 7.8196 | 9.9198 | 9.8196 | 8.8196 | 12.7294 | 14.7294 | 9.9198 | 18.7394 | 31.4688 | 46.1982 | 0.01
4.576 | 8.288 | 6.576 | 5.576 | 7.864 | 9.864 | 8.288 | 13.864 | 21.7279 | 31.5919 | 4.576 | 8.298 | 6.576 | 5.576 | 7.864 | 9.864 | 8.298 | 13.874 | 21.7379 | 31.6019 | 0.01
7.0266 | 9.5133 | 9.0266 | 8.0266 | 11.5399 | 13.5399 | 9.5133 | 17.5399 | 29.0798 | 42.6196 | 7.0266 | 9.5233 | 9.0266 | 8.0266 | 11.5399 | 13.5399 | 9.5233 | 17.5499 | 29.0898 | 42.6296 | 0.01
6.0145 | 9.0072 | 8.0145 | 7.0145 | 10.0217 | 12.0217 | 9.0072 | 16.0217 | 26.0434 | 38.0651 | 6.0145 | 9.0172 | 8.0145 | 7.0145 | 10.0217 | 12.0217 | 9.0172 | 16.0317 | 26.0534 | 38.0751 | 0.01
2.6438 | 7.3219 | 4.6438 | 3.6438 | 4.9657 | 6.9657 | 7.3219 | 10.9657 | 15.9313 | 22.897 | 2.6438 | 7.3319 | 4.6438 | 3.6438 | 4.9657 | 6.9657 | 7.3319 | 10.9757 | 15.9413 | 22.907 | 0.01
6.0348 | 9.0174 | 8.0348 | 7.0348 | 10.0522 | 12.0522 | 9.0174 | 16.0522 | 26.1044 | 38.1566 | 6.0348 | 9.0274 | 8.0348 | 7.0348 | 10.0522 | 12.0522 | 9.0274 | 16.0622 | 26.1144 | 38.1666 | 0.01
5.4907 | 8.7453 | 7.4907 | 6.4907 | 9.236 | 11.236 | 8.7453 | 15.236 | 24.472 | 35.7079 | 5.4907 | 8.7553 | 7.4907 | 6.4907 | 9.236 | 11.236 | 8.7553 | 15.246 | 24.482 | 35.7179 | 0.01
7.3925 | 9.6962 | 9.3925 | 8.3925 | 12.0887 | 14.0887 | 9.6962 | 18.0887 | 30.1774 | 44.2661 | 7.3925 | 9.7062 | 9.3925 | 8.3925 | 12.0887 | 14.0887 | 9.7062 | 18.0987 | 30.1874 | 44.2761 | 0.01
6.0746 | 9.0373 | 8.0746 | 7.0746 | 10.1119 | 12.1119 | 9.0373 | 16.1119 | 26.2238 | 38.3357 | 6.0746 | 9.0473 | 8.0746 | 7.0746 | 10.1119 | 12.1119 | 9.0473 | 16.1219 | 26.2338 | 38.3457 | 0.01
5.7247 | 8.8624 | 7.7247 | 6.7247 | 9.5871 | 11.5871 | 8.8624 | 15.5871 | 25.1742 | 36.7613 | 5.7247 | 8.8724 | 7.7247 | 6.7247 | 9.5871 | 11.5871 | 8.8724 | 15.5971 | 25.1842 | 36.7713 | 0.01
5.7801 | 8.89 | 7.7801 | 6.7801 | 9.6701 | 11.6701 | 8.89 | 15.6701 | 25.3403 | 37.0104 | 5.7801 | 8.9 | 7.7801 | 6.7801 | 9.6701 | 11.6701 | 8.9 | 15.6801 | 25.3503 | 37.0204 | 0.01
4.7764 | 8.3882 | 6.7764 | 5.7764 | 8.1646 | 10.1646 | 8.3882 | 14.1646 | 22.3292 | 32.4937 | 4.7764 | 8.3982 | 6.7764 | 5.7764 | 8.1646 | 10.1646 | 8.3982 | 14.1746 | 22.3392 | 32.5037 | 0.01
2.1447 | 7.0723 | 4.1447 | 3.1447 | 4.217 | 6.217 | 7.0723 | 10.217 | 14.434 | 20.6509 | 2.1447 | 7.0823 | 4.1447 | 3.1447 | 4.217 | 6.217 | 7.0823 | 10.227 | 14.444 | 20.6609 | 0.01
5.7028 | 8.8514 | 7.7028 | 6.7028 | 9.5542 | 11.5542 | 8.8514 | 15.5542 | 25.1084 | 36.6625 | 5.7028 | 8.8614 | 7.7028 | 6.7028 | 9.5542 | 11.5542 | 8.8614 | 15.5642 | 25.1184 | 36.6725 | 0.01
7.7214 | 9.8607 | 9.7214 | 8.7214 | 12.582 | 14.582 | 9.8607 | 18.582 | 31.1641 | 45.7461 | 7.7214 | 9.8707 | 9.7214 | 8.7214 | 12.582 | 14.582 | 9.8707 | 18.592 | 31.1741 | 45.7561 | 0.01
5.5976 | 8.7988 | 7.5976 | 6.5976 | 9.3964 | 11.3964 | 8.7988 | 15.3964 | 24.7928 | 36.1892 | 5.5976 | 8.8088 | 7.5976 | 6.5976 | 9.3964 | 11.3964 | 8.8088 | 15.4064 | 24.8028 | 36.1992 | 0.01
5.3389 | 8.6695 | 7.3389 | 6.3389 | 9.0084 | 11.0084 | 8.6695 | 15.0084 | 24.0167 | 35.0251 | 5.3389 | 8.6795 | 7.3389 | 6.3389 | 9.0084 | 11.0084 | 8.6795 | 15.0184 | 24.0267 | 35.0351 | 0.01
8.3081 | 10.154 | 10.3081 | 9.3081 | 13.4621 | 15.4621 | 10.154 | 19.4621 | 32.9243 | 48.3864 | 8.3081 | 10.164 | 10.3081 | 9.3081 | 13.4621 | 15.4621 | 10.164 | 19.4721 | 32.9343 | 48.3964 | 0.01
6.3383 | 9.1691 | 8.3383 | 7.3383 | 10.5074 | 12.5074 | 9.1691 | 16.5074 | 27.0148 | 39.5222 | 6.3383 | 9.1791 | 8.3383 | 7.3383 | 10.5074 | 12.5074 | 9.1791 | 16.5174 | 27.0248 | 39.5322 | 0.01
6.2356 | 9.1178 | 8.2356 | 7.2356 | 10.3534 | 12.3534 | 9.1178 | 16.3534 | 26.7069 | 39.0603 | 6.2356 | 9.1278 | 8.2356 | 7.2356 | 10.3534 | 12.3534 | 9.1278 | 16.3634 | 26.7169 | 39.0703 | 0.01
8.8103 | 10.4051 | 10.8103 | 9.8103 | 14.2154 | 16.2154 | 10.4051 | 20.2154 | 34.4309 | 50.6463 | 8.8103 | 10.4151 | 10.8103 | 9.8103 | 14.2154 | 16.2154 | 10.4151 | 20.2254 | 34.4409 | 50.6563 | 0.01
9.1328 | 10.5664 | 11.1328 | 10.1328 | 14.6992 | 16.6992 | 10.5664 | 20.6992 | 35.3985 | 52.0977 | 9.1328 | 10.5764 | 11.1328 | 10.1328 | 14.6992 | 16.6992 | 10.5764 | 20.7092 | 35.4085 | 52.1077 | 0.01
7.1789 | 9.5895 | 9.1789 | 8.1789 | 11.7684 | 13.7684 | 9.5895 | 17.7684 | 29.5367 | 43.3051 | 7.1789 | 9.5995 | 9.1789 | 8.1789 | 11.7684 | 13.7684 | 9.5995 | 17.7784 | 29.5467 | 43.3151 | 0.01
6.2187 | 9.1093 | 8.2187 | 7.2187 | 10.328 | 12.328 | 9.1093 | 16.328 | 26.6561 | 38.9841 | 6.2187 | 9.1193 | 8.2187 | 7.2187 | 10.328 | 12.328 | 9.1193 | 16.338 | 26.6661 | 38.9941 | 0.01
10.8017 | 11.4008 | 12.8017 | 11.8017 | 17.2025 | 19.2025 | 11.4008 | 23.2025 | 40.405 | 59.6075 | 10.8017 | 11.4108 | 12.8017 | 11.8017 | 17.2025 | 19.2025 | 11.4108 | 23.2125 | 40.415 | 59.6175 | 0.01
4.3082 | 8.1541 | 6.3082 | 5.3082 | 7.4622 | 9.4622 | 8.1541 | 13.4622 | 20.9245 | 30.3867 | 4.3082 | 8.1641 | 6.3082 | 5.3082 | 7.4622 | 9.4622 | 8.1641 | 13.4722 | 20.9345 | 30.3967 | 0.01
6.2847 | 9.1423 | 8.2847 | 7.2847 | 10.427 | 12.427 | 9.1423 | 16.427 | 26.8541 | 39.2811 | 6.2847 | 9.1523 | 8.2847 | 7.2847 | 10.427 | 12.427 | 9.1523 | 16.437 | 26.8641 | 39.2911 | 0.01
3.8754 | 7.9377 | 5.8754 | 4.8754 | 6.8131 | 8.8131 | 7.9377 | 12.8131 | 19.6261 | 28.4392 | 3.8754 | 7.9477 | 5.8754 | 4.8754 | 6.8131 | 8.8131 | 7.9477 | 12.8231 | 19.6361 | 28.4492 | 0.01
3.5216 | 7.7608 | 5.5216 | 4.5216 | 6.2824 | 8.2824 | 7.7608 | 12.2824 | 18.5649 | 26.8473 | 3.5216 | 7.7708 | 5.5216 | 4.5216 | 6.2824 | 8.2824 | 7.7708 | 12.2924 | 18.5749 | 26.8573 | 0.01
5.5633 | 8.7817 | 7.5633 | 6.5633 | 9.345 | 11.345 | 8.7817 | 15.345 | 24.69 | 36.0351 | 5.5633 | 8.7917 | 7.5633 | 6.5633 | 9.345 | 11.345 | 8.7917 | 15.355 | 24.7 | 36.0451 | 0.01
4.8463 | 8.4232 | 6.8463 | 5.8463 | 8.2695 | 10.2695 | 8.4232 | 14.2695 | 22.5389 | 32.8084 | 4.8463 | 8.4332 | 6.8463 | 5.8463 | 8.2695 | 10.2695 | 8.4332 | 14.2795 | 22.5489 | 32.8184 | 0.01
6.9828 | 9.4914 | 8.9828 | 7.9828 | 11.4743 | 13.4743 | 9.4914 | 17.4743 | 28.9485 | 42.4228 | 6.9828 | 9.5014 | 8.9828 | 7.9828 | 11.4743 | 13.4743 | 9.5014 | 17.4843 | 28.9585 | 42.4328 | 0.01
7.8476 | 9.9238 | 9.8476 | 8.8476 | 12.7713 | 14.7713 | 9.9238 | 18.7713 | 31.5427 | 46.314 | 7.8476 | 9.9338 | 9.8476 | 8.8476 | 12.7713 | 14.7713 | 9.9338 | 18.7813 | 31.5527 | 46.324 | 0.01
7.0345 | 9.5172 | 9.0345 | 8.0345 | 11.5517 | 13.5517 | 9.5172 | 17.5517 | 29.1034 | 42.655 | 7.0345 | 9.5272 | 9.0345 | 8.0345 | 11.5517 | 13.5517 | 9.5272 | 17.5617 | 29.1134 | 42.665 | 0.01
7.2596 | 9.6298 | 9.2596 | 8.2596 | 11.8894 | 13.8894 | 9.6298 | 17.8894 | 29.7788 | 43.6682 | 7.2596 | 9.6398 | 9.2596 | 8.2596 | 11.8894 | 13.8894 | 9.6398 | 17.8994 | 29.7888 | 43.6782 | 0.01
6.762 | 9.381 | 8.762 | 7.762 | 11.143 | 13.143 | 9.381 | 17.143 | 28.286 | 41.4289 | 6.762 | 9.391 | 8.762 | 7.762 | 11.143 | 13.143 | 9.391 | 17.153 | 28.296 | 41.4389 | 0.01
4.7843 | 8.3922 | 6.7843 | 5.7843 | 8.1765 | 10.1765 | 8.3922 | 14.1765 | 22.3529 | 32.5294 | 4.7843 | 8.4022 | 6.7843 | 5.7843 | 8.1765 | 10.1765 | 8.4022 | 14.1865 | 22.3629 | 32.5394 | 0.01
5.9404 | 8.9702 | 7.9404 | 6.9404 | 9.9106 | 11.9106 | 8.9702 | 15.9106 | 25.8212 | 37.7318 | 5.9404 | 8.9802 | 7.9404 | 6.9404 | 9.9106 | 11.9106 | 8.9802 | 15.9206 | 25.8312 | 37.7418 | 0.01
6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 6.3314 | 9.1757 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1757 | 16.5072 | 27.0043 | 39.5015 | 0.01
7.0135 | 9.5068 | 9.0135 | 8.0135 | 11.5203 | 13.5203 | 9.5068 | 17.5203 | 29.0406 | 42.5608 | 7.0135 | 9.5168 | 9.0135 | 8.0135 | 11.5203 | 13.5203 | 9.5168 | 17.5303 | 29.0506 | 42.5708 | 0.01
3.4265 | 7.7133 | 5.4265 | 4.4265 | 6.1398 | 8.1398 | 7.7133 | 12.1398 | 18.2796 | 26.4194 | 3.4265 | 7.7233 | 5.4265 | 4.4265 | 6.1398 | 8.1398 | 7.7233 | 12.1498 | 18.2896 | 26.4294 | 0.01
5.4813 | 8.7407 | 7.4813 | 6.4813 | 9.222 | 11.222 | 8.7407 | 15.222 | 24.444 | 35.6659 | 5.4813 | 8.7507 | 7.4813 | 6.4813 | 9.222 | 11.222 | 8.7507 | 15.232 | 24.454 | 35.6759 | 0.01
7.7681 | 9.8841 | 9.7681 | 8.7681 | 12.6522 | 14.6522 | 9.8841 | 18.6522 | 31.3044 | 45.9566 | 7.7681 | 9.8941 | 9.7681 | 8.7681 | 12.6522 | 14.6522 | 9.8941 | 18.6622 | 31.3144 | 45.9666 | 0.01
6.4122 | 9.2061 | 8.4122 | 7.4122 | 10.6184 | 12.6184 | 9.2061 | 16.6184 | 27.2367 | 39.8551 | 6.4122 | 9.2161 | 8.4122 | 7.4122 | 10.6184 | 12.6184 | 9.2161 | 16.6284 | 27.2467 | 39.8651 | 0.01
8.7219 | 10.361 | 10.7219 | 9.7219 | 14.0829 | 16.0829 | 10.361 | 20.0829 | 34.1657 | 50.2486 | 8.7219 | 10.371 | 10.7219 | 9.7219 | 14.0829 | 16.0829 | 10.371 | 20.0929 | 34.1757 | 50.2586 | 0.01
5.8098 | 8.9049 | 7.8098 | 6.8098 | 9.7147 | 11.7147 | 8.9049 | 15.7147 | 25.4293 | 37.144 | 5.8098 | 8.9149 | 7.8098 | 6.8098 | 9.7147 | 11.7147 | 8.9149 | 15.7247 | 25.4393 | 37.154 | 0.01
4.8329 | 8.4165 | 6.8329 | 5.8329 | 8.2494 | 10.2494 | 8.4165 | 14.2494 | 22.4987 | 32.7481 | 4.8329 | 8.4265 | 6.8329 | 5.8329 | 8.2494 | 10.2494 | 8.4265 | 14.2594 | 22.5087 | 32.7581 | 0.01
6.7605 | 9.3803 | 8.7605 | 7.7605 | 11.1408 | 13.1408 | 9.3803 | 17.1408 | 28.2815 | 41.4223 | 6.7605 | 9.3903 | 8.7605 | 7.7605 | 11.1408 | 13.1408 | 9.3903 | 17.1508 | 28.2915 | 41.4323 | 0.01
9.047 | 10.5235 | 11.047 | 10.047 | 14.5706 | 16.5706 | 10.5235 | 20.5706 | 35.1411 | 51.7117 | 9.047 | 10.5335 | 11.047 | 10.047 | 14.5706 | 16.5706 | 10.5335 | 20.5806 | 35.1511 | 51.7217 | 0.01
7.8454 | 9.9227 | 9.8454 | 8.8454 | 12.7682 | 14.7682 | 9.9227 | 18.7682 | 31.5363 | 46.3045 | 7.8454 | 9.9327 | 9.8454 | 8.8454 | 12.7682 | 14.7682 | 9.9327 | 18.7782 | 31.5463 | 46.3145 | 0.01
6.6496 | 9.3248 | 8.6496 | 7.6496 | 10.9744 | 12.9744 | 9.3248 | 16.9744 | 27.9489 | 40.9233 | 6.6496 | 9.3348 | 8.6496 | 7.6496 | 10.9744 | 12.9744 | 9.3348 | 16.9844 | 27.9589 | 40.9333 | 0.01
4.2135 | 8.1067 | 6.2135 | 5.2135 | 7.3202 | 9.3202 | 8.1067 | 13.3202 | 20.6404 | 29.9606 | 4.2135 | 8.1167 | 6.2135 | 5.2135 | 7.3202 | 9.3202 | 8.1167 | 13.3302 | 20.6504 | 29.9706 | 0.01
11.6293 | 11.8146 | 13.6293 | 12.6293 | 18.4439 | 20.4439 | 11.8146 | 24.4439 | 42.8878 | 63.3317 | 11.6293 | 11.8246 | 13.6293 | 12.6293 | 18.4439 | 20.4439 | 11.8246 | 24.4539 | 42.8978 | 63.3417 | 0.01
5.3138 | 8.6569 | 7.3138 | 6.3138 | 8.9707 | 10.9707 | 8.6569 | 14.9707 | 23.9414 | 34.9122 | 5.3138 | 8.6669 | 7.3138 | 6.3138 | 8.9707 | 10.9707 | 8.6669 | 14.9807 | 23.9514 | 34.9222 | 0.01
6.2814 | 9.1407 | 8.2814 | 7.2814 | 10.4222 | 12.4222 | 9.1407 | 16.4222 | 26.8443 | 39.2665 | 6.2814 | 9.1507 | 8.2814 | 7.2814 | 10.4222 | 12.4222 | 9.1507 | 16.4322 | 26.8543 | 39.2765 | 0.01
5.935 | 8.9675 | 7.935 | 6.935 | 9.9026 | 11.9026 | 8.9675 | 15.9026 | 25.8051 | 37.7077 | 5.935 | 8.9775 | 7.935 | 6.935 | 9.9026 | 11.9026 | 8.9775 | 15.9126 | 25.8151 | 37.7177 | 0.01
6.1508 | 9.0754 | 8.1508 | 7.1508 | 10.2262 | 12.2262 | 9.0754 | 16.2262 | 26.4523 | 38.6785 | 6.1508 | 9.0854 | 8.1508 | 7.1508 | 10.2262 | 12.2262 | 9.0854 | 16.2362 | 26.4623 | 38.6885 | 0.01
5.3276 | 8.6638 | 7.3276 | 6.3276 | 8.9914 | 10.9914 | 8.6638 | 14.9914 | 23.9828 | 34.9742 | 5.3276 | 8.6738 | 7.3276 | 6.3276 | 8.9914 | 10.9914 | 8.6738 | 15.0014 | 23.9928 | 34.9842 | 0.01
2.0185 | 7.0093 | 4.0185 | 3.0185 | 4.0278 | 6.0278 | 7.0093 | 10.0278 | 14.0556 | 20.0834 | 2.0185 | 7.0193 | 4.0185 | 3.0185 | 4.0278 | 6.0278 | 7.0193 | 10.0378 | 14.0656 | 20.0934 | 0.01
7.9373 | 9.9687 | 9.9373 | 8.9373 | 12.906 | 14.906 | 9.9687 | 18.906 | 31.812 | 46.718 | 7.9373 | 9.9787 | 9.9373 | 8.9373 | 12.906 | 14.906 | 9.9787 | 18.916 | 31.822 | 46.728 | 0.01
7.1858 | 9.5929 | 9.1858 | 8.1858 | 11.7787 | 13.7787 | 9.5929 | 17.7787 | 29.5575 | 43.3362 | 7.1858 | 9.6029 | 9.1858 | 8.1858 | 11.7787 | 13.7787 | 9.6029 | 17.7887 | 29.5675 | 43.3462 | 0.01
6.7905 | 9.3953 | 8.7905 | 7.7905 | 11.1858 | 13.1858 | 9.3953 | 17.1858 | 28.3716 | 41.5574 | 6.7905 | 9.4053 | 8.7905 | 7.7905 | 11.1858 | 13.1858 | 9.4053 | 17.1958 | 28.3816 | 41.5674 | 0.01
8.3321 | 10.166 | 10.3321 | 9.3321 | 13.4981 | 15.4981 | 10.166 | 19.4981 | 32.9962 | 48.4944 | 8.3321 | 10.176 | 10.3321 | 9.3321 | 13.4981 | 15.4981 | 10.176 | 19.5081 | 33.0062 | 48.5044 | 0.01
4.4306 | 8.2153 | 6.4306 | 5.4306 | 7.6459 | 9.6459 | 8.2153 | 13.6459 | 21.2918 | 30.9377 | 4.4306 | 8.2253 | 6.4306 | 5.4306 | 7.6459 | 9.6459 | 8.2253 | 13.6559 | 21.3018 | 30.9477 | 0.01
5.963 | 8.9815 | 7.963 | 6.963 | 9.9446 | 11.9446 | 8.9815 | 15.9446 | 25.8891 | 37.8337 | 5.963 | 8.9915 | 7.963 | 6.963 | 9.9446 | 11.9446 | 8.9915 | 15.9546 | 25.8991 | 37.8437 | 0.01
5.0349 | 8.5174 | 7.0349 | 6.0349 | 8.5523 | 10.5523 | 8.5174 | 14.5523 | 23.1047 | 33.657 | 5.0349 | 8.5274 | 7.0349 | 6.0349 | 8.5523 | 10.5523 | 8.5274 | 14.5623 | 23.1147 | 33.667 | 0.01
7.8813 | 9.9407 | 9.8813 | 8.8813 | 12.822 | 14.822 | 9.9407 | 18.822 | 31.644 | 46.466 | 7.8813 | 9.9507 | 9.8813 | 8.8813 | 12.822 | 14.822 | 9.9507 | 18.832 | 31.654 | 46.476 | 0.01
2.9422 | 7.4711 | 4.9422 | 3.9422 | 5.4133 | 7.4133 | 7.4711 | 11.4133 | 16.8265 | 24.2398 | 2.9422 | 7.4811 | 4.9422 | 3.9422 | 5.4133 | 7.4133 | 7.4811 | 11.4233 | 16.8365 | 24.2498 | 0.01
5.5831 | 8.7915 | 7.5831 | 6.5831 | 9.3746 | 11.3746 | 8.7915 | 15.3746 | 24.7492 | 36.1238 | 5.5831 | 8.8015 | 7.5831 | 6.5831 | 9.3746 | 11.3746 | 8.8015 | 15.3846 | 24.7592 | 36.1338 | 0.01
6.1071 | 9.0535 | 8.1071 | 7.1071 | 10.1606 | 12.1606 | 9.0535 | 16.1606 | 26.3212 | 38.4818 | 6.1071 | 9.0635 | 8.1071 | 7.1071 | 10.1606 | 12.1606 | 9.0635 | 16.1706 | 26.3312 | 38.4918 | 0.01
3.7728 | 7.8864 | 5.7728 | 4.7728 | 6.6592 | 8.6592 | 7.8864 | 12.6592 | 19.3184 | 27.9776 | 3.7728 | 7.8964 | 5.7728 | 4.7728 | 6.6592 | 8.6592 | 7.8964 | 12.6692 | 19.3284 | 27.9876 | 0.01
7.4075 | 9.7038 | 9.4075 | 8.4075 | 12.1113 | 14.1113 | 9.7038 | 18.1113 | 30.2226 | 44.3338 | 7.4075 | 9.7138 | 9.4075 | 8.4075 | 12.1113 | 14.1113 | 9.7138 | 18.1213 | 30.2326 | 44.3438 | 0.01
4.9966 | 8.4983 | 6.9966 | 5.9966 | 8.4948 | 10.4948 | 8.4983 | 14.4948 | 22.9897 | 33.4845 | 4.9966 | 8.5083 | 6.9966 | 5.9966 | 8.4948 | 10.4948 | 8.5083 | 14.5048 | 22.9997 | 33.4945 | 0.01
5.7338 | 8.8669 | 7.7338 | 6.7338 | 9.6008 | 11.6008 | 8.8669 | 15.6008 | 25.2015 | 36.8023 | 5.7338 | 8.8769 | 7.7338 | 6.7338 | 9.6008 | 11.6008 | 8.8769 | 15.6108 | 25.2115 | 36.8123 | 0.01
9.5995 | 10.7997 | 11.5995 | 10.5995 | 15.3992 | 17.3992 | 10.7997 | 21.3992 | 36.7984 | 54.1977 | 9.5995 | 10.8097 | 11.5995 | 10.5995 | 15.3992 | 17.3992 | 10.8097 | 21.4092 | 36.8084 | 54.2077 | 0.01
4.5772 | 8.2886 | 6.5772 | 5.5772 | 7.8657 | 9.8657 | 8.2886 | 13.8657 | 21.7315 | 31.5972 | 4.5772 | 8.2986 | 6.5772 | 5.5772 | 7.8657 | 9.8657 | 8.2986 | 13.8757 | 21.7415 | 31.6072 | 0.01
6.272 | 9.136 | 8.272 | 7.272 | 10.408 | 12.408 | 9.136 | 16.408 | 26.8161 | 39.2241 | 6.272 | 9.146 | 8.272 | 7.272 | 10.408 | 12.408 | 9.146 | 16.418 | 26.8261 | 39.2341 | 0.01
8.0427 | 10.0214 | 10.0427 | 9.0427 | 13.0641 | 15.0641 | 10.0214 | 19.0641 | 32.1282 | 47.1924 | 8.0427 | 10.0314 | 10.0427 | 9.0427 | 13.0641 | 15.0641 | 10.0314 | 19.0741 | 32.1382 | 47.2024 | 0.01
7.5719 | 9.7859 | 9.5719 | 8.5719 | 12.3578 | 14.3578 | 9.7859 | 18.3578 | 30.7157 | 45.0735 | 7.5719 | 9.7959 | 9.5719 | 8.5719 | 12.3578 | 14.3578 | 9.7959 | 18.3678 | 30.7257 | 45.0835 | 0.01
5.6432 | 8.8216 | 7.6432 | 6.6432 | 9.4649 | 11.4649 | 8.8216 | 15.4649 | 24.9297 | 36.3946 | 5.6432 | 8.8316 | 7.6432 | 6.6432 | 9.4649 | 11.4649 | 8.8316 | 15.4749 | 24.9397 | 36.4046 | 0.01
8.7355 | 10.3677 | 10.7355 | 9.7355 | 14.1032 | 16.1032 | 10.3677 | 20.1032 | 34.2065 | 50.3097 | 8.7355 | 10.3777 | 10.7355 | 9.7355 | 14.1032 | 16.1032 | 10.3777 | 20.1132 | 34.2165 | 50.3197 | 0.01
5.0301 | 8.515 | 7.0301 | 6.0301 | 8.5451 | 10.5451 | 8.515 | 14.5451 | 23.0902 | 33.6354 | 5.0301 | 8.525 | 7.0301 | 6.0301 | 8.5451 | 10.5451 | 8.525 | 14.5551 | 23.1002 | 33.6454 | 0.01
7.0523 | 9.5262 | 9.0523 | 8.0523 | 11.5785 | 13.5785 | 9.5262 | 17.5785 | 29.157 | 42.7355 | 7.0523 | 9.5362 | 9.0523 | 8.0523 | 11.5785 | 13.5785 | 9.5362 | 17.5885 | 29.167 | 42.7455 | 0.01
7.9439 | 9.972 | 9.9439 | 8.9439 | 12.9159 | 14.9159 | 9.972 | 18.9159 | 31.8318 | 46.7478 | 7.9439 | 9.982 | 9.9439 | 8.9439 | 12.9159 | 14.9159 | 9.982 | 18.9259 | 31.8418 | 46.7578 | 0.01
8.5616 | 10.2808 | 10.5616 | 9.5616 | 13.8424 | 15.8424 | 10.2808 | 19.8424 | 33.6848 | 49.5272 | 8.5616 | 10.2908 | 10.5616 | 9.5616 | 13.8424 | 15.8424 | 10.2908 | 19.8524 | 33.6948 | 49.5372 | 0.01
7.3831 | 9.6916 | 9.3831 | 8.3831 | 12.0747 | 14.0747 | 9.6916 | 18.0747 | 30.1494 | 44.2241 | 7.3831 | 9.7016 | 9.3831 | 8.3831 | 12.0747 | 14.0747 | 9.7016 | 18.0847 | 30.1594 | 44.2341 | 0.01
4.1357 | 8.0679 | 6.1357 | 5.1357 | 7.2036 | 9.2036 | 8.0679 | 13.2036 | 20.4072 | 29.6108 | 4.1357 | 8.0779 | 6.1357 | 5.1357 | 7.2036 | 9.2036 | 8.0779 | 13.2136 | 20.4172 | 29.6208 | 0.01
2.1727 | 7.0864 | 4.1727 | 3.1727 | 4.2591 | 6.2591 | 7.0864 | 10.2591 | 14.5182 | 20.7772 | 2.1727 | 7.0964 | 4.1727 | 3.1727 | 4.2591 | 6.2591 | 7.0964 | 10.2691 | 14.5282 | 20.7872 | 0.01
5.5513 | 8.7756 | 7.5513 | 6.5513 | 9.3269 | 11.3269 | 8.7756 | 15.3269 | 24.6538 | 35.9807 | 5.5513 | 8.7856 | 7.5513 | 6.5513 | 9.3269 | 11.3269 | 8.7856 | 15.3369 | 24.6638 | 35.9907 | 0.01
3.49 | 7.745 | 5.49 | 4.49 | 6.235 | 8.235 | 7.745 | 12.235 | 18.47 | 26.705 | 3.49 | 7.755 | 5.49 | 4.49 | 6.235 | 8.235 | 7.755 | 12.245 | 18.48 | 26.715 | 0.01
0.33785 | 6.1689 | 2.3378 | 1.3378 | 1.5068 | 3.5068 | 6.1689 | 7.5068 | 9.0135 | 12.5203 | 0.33785 | 6.1789 | 2.3378 | 1.3378 | 1.5068 | 3.5068 | 6.1789 | 7.5168 | 9.0235 | 12.5303 | 0.01
5.2149 | 8.6075 | 7.2149 | 6.2149 | 8.8224 | 10.8224 | 8.6075 | 14.8224 | 23.6448 | 34.4672 | 5.2149 | 8.6175 | 7.2149 | 6.2149 | 8.8224 | 10.8224 | 8.6175 | 14.8324 | 23.6548 | 34.4772 | 0.01
7.5632 | 9.7816 | 9.5632 | 8.5632 | 12.3447 | 14.3447 | 9.7816 | 18.3447 | 30.6895 | 45.0342 | 7.5632 | 9.7916 | 9.5632 | 8.5632 | 12.3447 | 14.3447 | 9.7916 | 18.3547 | 30.6995 | 45.0442 | 0.01
7.7902 | 9.8951 | 9.7902 | 8.7902 | 12.6853 | 14.6853 | 9.8951 | 18.6853 | 31.3705 | 46.0558 | 7.7902 | 9.9051 | 9.7902 | 8.7902 | 12.6853 | 14.6853 | 9.9051 | 18.6953 | 31.3805 | 46.0658 | 0.01
9.4106 | 10.7053 | 11.4106 | 10.4106 | 15.1159 | 17.1159 | 10.7053 | 21.1159 | 36.2318 | 53.3477 | 9.4106 | 10.7153 | 11.4106 | 10.4106 | 15.1159 | 17.1159 | 10.7153 | 21.1259 | 36.2418 | 53.3577 | 0.01
6.338 | 9.169 | 8.338 | 7.338 | 10.5069 | 12.5069 | 9.169 | 16.5069 | 27.0139 | 39.5208 | 6.338 | 9.179 | 8.338 | 7.338 | 10.5069 | 12.5069 | 9.179 | 16.5169 | 27.0239 | 39.5308 | 0.01
8.4698 | 10.2349 | 10.4698 | 9.4698 | 13.7047 | 15.7047 | 10.2349 | 19.7047 | 33.4094 | 49.1142 | 8.4698 | 10.2449 | 10.4698 | 9.4698 | 13.7047 | 15.7047 | 10.2449 | 19.7147 | 33.4194 | 49.1242 | 0.01
3.966 | 7.983 | 5.966 | 4.966 | 6.949 | 8.949 | 7.983 | 12.949 | 19.898 | 28.847 | 3.966 | 7.993 | 5.966 | 4.966 | 6.949 | 8.949 | 7.993 | 12.959 | 19.908 | 28.857 | 0.01
2.0788 | 7.0394 | 4.0788 | 3.0788 | 4.1183 | 6.1183 | 7.0394 | 10.1183 | 14.2365 | 20.3548 | 2.0788 | 7.0494 | 4.0788 | 3.0788 | 4.1183 | 6.1183 | 7.0494 | 10.1283 | 14.2465 | 20.3648 | 0.01
7.9038 | 9.9519 | 9.9038 | 8.9038 | 12.8558 | 14.8558 | 9.9519 | 18.8558 | 31.7115 | 46.5673 | 7.9038 | 9.9619 | 9.9038 | 8.9038 | 12.8558 | 14.8558 | 9.9619 | 18.8658 | 31.7215 | 46.5773 | 0.01
5.9358 | 8.9679 | 7.9358 | 6.9358 | 9.9037 | 11.9037 | 8.9679 | 15.9037 | 25.8074 | 37.7111 | 5.9358 | 8.9779 | 7.9358 | 6.9358 | 9.9037 | 11.9037 | 8.9779 | 15.9137 | 25.8174 | 37.7211 | 0.01
8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 8.0477 | 10.0338 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0338 | 19.0815 | 32.153 | 47.2244 | 0.01
6.657 | 9.3285 | 8.657 | 7.657 | 10.9856 | 12.9856 | 9.3285 | 16.9856 | 27.9711 | 40.9567 | 6.657 | 9.3385 | 8.657 | 7.657 | 10.9856 | 12.9856 | 9.3385 | 16.9956 | 27.9811 | 40.9667 | 0.01
6.5966 | 9.2983 | 8.5966 | 7.5966 | 10.8949 | 12.8949 | 9.2983 | 16.8949 | 27.7899 | 40.6848 | 6.5966 | 9.3083 | 8.5966 | 7.5966 | 10.8949 | 12.8949 | 9.3083 | 16.9049 | 27.7999 | 40.6948 | 0.01
5.4851 | 8.7426 | 7.4851 | 6.4851 | 9.2277 | 11.2277 | 8.7426 | 15.2277 | 24.4554 | 35.683 | 5.4851 | 8.7526 | 7.4851 | 6.4851 | 9.2277 | 11.2277 | 8.7526 | 15.2377 | 24.4654 | 35.693 | 0.01
3.0805 | 7.5402 | 5.0805 | 4.0805 | 5.6207 | 7.6207 | 7.5402 | 11.6207 | 17.2414 | 24.8621 | 3.0805 | 7.5502 | 5.0805 | 4.0805 | 5.6207 | 7.6207 | 7.5502 | 11.6307 | 17.2514 | 24.8721 | 0.01
7.2083 | 9.6042 | 9.2083 | 8.2083 | 11.8125 | 13.8125 | 9.6042 | 17.8125 | 29.625 | 43.4375 | 7.2083 | 9.6142 | 9.2083 | 8.2083 | 11.8125 | 13.8125 | 9.6142 | 17.8225 | 29.635 | 43.4475 | 0.01
2.7006 | 7.3503 | 4.7006 | 3.7006 | 5.0509 | 7.0509 | 7.3503 | 11.0509 | 16.1017 | 23.1526 | 2.7006 | 7.3603 | 4.7006 | 3.7006 | 5.0509 | 7.0509 | 7.3603 | 11.0609 | 16.1117 | 23.1626 | 0.01
7.4982 | 9.7491 | 9.4982 | 8.4982 | 12.2472 | 14.2472 | 9.7491 | 18.2472 | 30.4945 | 44.7417 | 7.4982 | 9.7591 | 9.4982 | 8.4982 | 12.2472 | 14.2472 | 9.7591 | 18.2572 | 30.5045 | 44.7517 | 0.01
5.3544 | 8.6772 | 7.3544 | 6.3544 | 9.0316 | 11.0316 | 8.6772 | 15.0316 | 24.0632 | 35.0948 | 5.3544 | 8.6872 | 7.3544 | 6.3544 | 9.0316 | 11.0316 | 8.6872 | 15.0416 | 24.0732 | 35.1048 | 0.01
4.5186 | 8.2593 | 6.5186 | 5.5186 | 7.7779 | 9.7779 | 8.2593 | 13.7779 | 21.5558 | 31.3337 | 4.5186 | 8.2693 | 6.5186 | 5.5186 | 7.7779 | 9.7779 | 8.2693 | 13.7879 | 21.5658 | 31.3437 | 0.01
4.8309 | 8.4155 | 6.8309 | 5.8309 | 8.2464 | 10.2464 | 8.4155 | 14.2464 | 22.4927 | 32.7391 | 4.8309 | 8.4255 | 6.8309 | 5.8309 | 8.2464 | 10.2464 | 8.4255 | 14.2564 | 22.5027 | 32.7491 | 0.01
1.1151 | 6.5575 | 3.1151 | 2.1151 | 2.6726 | 4.6726 | 6.5575 | 8.6726 | 11.3452 | 16.0178 | 1.1151 | 6.5675 | 3.1151 | 2.1151 | 2.6726 | 4.6726 | 6.5675 | 8.6826 | 11.3552 | 16.0278 | 0.01
5.9719 | 8.986 | 7.9719 | 6.9719 | 9.9579 | 11.9579 | 8.986 | 15.9579 | 25.9158 | 37.8737 | 5.9719 | 8.996 | 7.9719 | 6.9719 | 9.9579 | 11.9579 | 8.996 | 15.9679 | 25.9258 | 37.8837 | 0.01
6.5507 | 9.2754 | 8.5507 | 7.5507 | 10.8261 | 12.8261 | 9.2754 | 16.8261 | 27.6521 | 40.4782 | 6.5507 | 9.2854 | 8.5507 | 7.5507 | 10.8261 | 12.8261 | 9.2854 | 16.8361 | 27.6621 | 40.4882 | 0.01
4.8226 | 8.4113 | 6.8226 | 5.8226 | 8.2338 | 10.2338 | 8.4113 | 14.2338 | 22.4677 | 32.7015 | 4.8226 | 8.4213 | 6.8226 | 5.8226 | 8.2338 | 10.2338 | 8.4213 | 14.2438 | 22.4777 | 32.7115 | 0.01
6.1037 | 9.0519 | 8.1037 | 7.1037 | 10.1556 | 12.1556 | 9.0519 | 16.1556 | 26.3111 | 38.4667 | 6.1037 | 9.0619 | 8.1037 | 7.1037 | 10.1556 | 12.1556 | 9.0619 | 16.1656 | 26.3211 | 38.4767 | 0.01
6.9292 | 9.4646 | 8.9292 | 7.9292 | 11.3937 | 13.3937 | 9.4646 | 17.3937 | 28.7875 | 42.1812 | 6.9292 | 9.4746 | 8.9292 | 7.9292 | 11.3937 | 13.3937 | 9.4746 | 17.4037 | 28.7975 | 42.1912 | 0.01
3.7038 | 7.8519 | 5.7038 | 4.7038 | 6.5557 | 8.5557 | 7.8519 | 12.5557 | 19.1113 | 27.667 | 3.7038 | 7.8619 | 5.7038 | 4.7038 | 6.5557 | 8.5557 | 7.8619 | 12.5657 | 19.1213 | 27.677 | 0.01
7.5671 | 9.7836 | 9.5671 | 8.5671 | 12.3507 | 14.3507 | 9.7836 | 18.3507 | 30.7013 | 45.052 | 7.5671 | 9.7936 | 9.5671 | 8.5671 | 12.3507 | 14.3507 | 9.7936 | 18.3607 | 30.7113 | 45.062 | 0.01
2.3254 | 7.1627 | 4.3254 | 3.3254 | 4.4881 | 6.4881 | 7.1627 | 10.4881 | 14.9762 | 21.4642 | 2.3254 | 7.1727 | 4.3254 | 3.3254 | 4.4881 | 6.4881 | 7.1727 | 10.4981 | 14.9862 | 21.4742 | 0.01
5.8236 | 8.9118 | 7.8236 | 6.8236 | 9.7354 | 11.7354 | 8.9118 | 15.7354 | 25.4708 | 37.2062 | 5.8236 | 8.9218 | 7.8236 | 6.8236 | 9.7354 | 11.7354 | 8.9218 | 15.7454 | 25.4808 | 37.2162 | 0.01
6.3687 | 9.1844 | 8.3687 | 7.3687 | 10.5531 | 12.5531 | 9.1844 | 16.5531 | 27.1062 | 39.6593 | 6.3687 | 9.1944 | 8.3687 | 7.3687 | 10.5531 | 12.5531 | 9.1944 | 16.5631 | 27.1162 | 39.6693 | 0.01
7.032 | 9.516 | 9.032 | 8.032 | 11.548 | 13.548 | 9.516 | 17.548 | 29.096 | 42.644 | 7.032 | 9.526 | 9.032 | 8.032 | 11.548 | 13.548 | 9.526 | 17.558 | 29.106 | 42.654 | 0.01
5.9999 | 9 | 7.9999 | 6.9999 | 9.9999 | 11.9999 | 9 | 15.9999 | 25.9998 | 37.9997 | 5.9999 | 9.01 | 7.9999 | 6.9999 | 9.9999 | 11.9999 | 9.01 | 16.0099 | 26.0098 | 38.0097 | 0.01
6.0206 | 9.0103 | 8.0206 | 7.0206 | 10.0309 | 12.0309 | 9.0103 | 16.0309 | 26.0617 | 38.0926 | 6.0206 | 9.0203 | 8.0206 | 7.0206 | 10.0309 | 12.0309 | 9.0203 | 16.0409 | 26.0717 | 38.1026 | 0.01
9.147 | 10.5735 | 11.147 | 10.147 | 14.7205 | 16.7205 | 10.5735 | 20.7205 | 35.441 | 52.1614 | 9.147 | 10.5835 | 11.147 | 10.147 | 14.7205 | 16.7205 | 10.5835 | 20.7305 | 35.451 | 52.1714 | 0.01
7.1056 | 9.5528 | 9.1056 | 8.1056 | 11.6584 | 13.6584 | 9.5528 | 17.6584 | 29.3168 | 42.9752 | 7.1056 | 9.5628 | 9.1056 | 8.1056 | 11.6584 | 13.6584 | 9.5628 | 17.6684 | 29.3268 | 42.9852 | 0.01
[8 empty] | Average | 37.4427 | [8 empty] | Average |  | 99.9%

## test activity C
A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | diff
1.4288 | 6.7144 | 3.4288 | 2.4288 | 3.1433 | 5.1433 | 6.7144 | 9.1433 | 12.2865 | 17.4298 | 1.4288 | 6.7144 | 3.4388 | 2.4288 | 3.1433 | 5.1433 | 6.7144 | 9.1433 | 12.2865 | 17.4298 | 0
2.4295 | 7.2148 | 4.4295 | 3.4295 | 4.6443 | 6.6443 | 7.2148 | 10.6443 | 15.2885 | 21.9328 | 2.4295 | 7.2148 | 4.4395 | 3.4295 | 4.6443 | 6.6443 | 7.2148 | 10.6443 | 15.2885 | 21.9328 | 0
4.0538 | 8.0269 | 6.0538 | 5.0538 | 7.0808 | 9.0808 | 8.0269 | 13.0808 | 20.1615 | 29.2423 | 4.0538 | 8.0269 | 6.0638 | 5.0538 | 7.0808 | 9.0808 | 8.0269 | 13.0808 | 20.1615 | 29.2423 | 0
6.049 | 9.0245 | 8.049 | 7.049 | 10.0736 | 12.0736 | 9.0245 | 16.0736 | 26.1471 | 38.2207 | 6.049 | 9.0245 | 8.059 | 7.049 | 10.0736 | 12.0736 | 9.0245 | 16.0736 | 26.1471 | 38.2207 | 0
7.3353 | 9.6677 | 9.3353 | 8.3353 | 12.003 | 14.003 | 9.6677 | 18.003 | 30.006 | 44.009 | 7.3353 | 9.6677 | 9.3453 | 8.3353 | 12.003 | 14.003 | 9.6677 | 18.003 | 30.006 | 44.009 | 0
5.1939 | 8.5969 | 7.1939 | 6.1939 | 8.7908 | 10.7908 | 8.5969 | 14.7908 | 23.5817 | 34.3725 | 5.1939 | 8.5969 | 7.2039 | 6.1939 | 8.7908 | 10.7908 | 8.5969 | 14.7908 | 23.5817 | 34.3725 | 0
7.3727 | 9.6863 | 9.3727 | 8.3727 | 12.059 | 14.059 | 9.6863 | 18.059 | 30.118 | 44.1769 | 7.3727 | 9.6863 | 9.3827 | 8.3727 | 12.059 | 14.059 | 9.6863 | 18.059 | 30.118 | 44.1769 | 0
2.7474 | 7.3737 | 4.7474 | 3.7474 | 5.1211 | 7.1211 | 7.3737 | 11.1211 | 16.2422 | 23.3633 | 2.7474 | 7.3737 | 4.7574 | 3.7474 | 5.1211 | 7.1211 | 7.3737 | 11.1211 | 16.2422 | 23.3633 | 0
7.0969 | 9.5484 | 9.0969 | 8.0969 | 11.6453 | 13.6453 | 9.5484 | 17.6453 | 29.2906 | 42.9359 | 7.0969 | 9.5484 | 9.1069 | 8.0969 | 11.6453 | 13.6453 | 9.5484 | 17.6453 | 29.2906 | 42.9359 | 0
4.1058 | 8.0529 | 6.1058 | 5.1058 | 7.1586 | 9.1586 | 8.0529 | 13.1586 | 20.3173 | 29.4759 | 4.1058 | 8.0529 | 6.1158 | 5.1058 | 7.1586 | 9.1586 | 8.0529 | 13.1586 | 20.3173 | 29.4759 | 0
7.2091 | 9.6045 | 9.2091 | 8.2091 | 11.8136 | 13.8136 | 9.6045 | 17.8136 | 29.6272 | 43.4408 | 7.2091 | 9.6045 | 9.2191 | 8.2091 | 11.8136 | 13.8136 | 9.6045 | 17.8136 | 29.6272 | 43.4408 | 0
10.8182 | 11.4091 | 12.8182 | 11.8182 | 17.2273 | 19.2273 | 11.4091 | 23.2273 | 40.4546 | 59.682 | 10.8182 | 11.4091 | 12.8282 | 11.8182 | 17.2273 | 19.2273 | 11.4091 | 23.2273 | 40.4546 | 59.682 | 0
6.4931 | 9.2465 | 8.4931 | 7.4931 | 10.7396 | 12.7396 | 9.2465 | 16.7396 | 27.4793 | 40.2189 | 6.4931 | 9.2465 | 8.5031 | 7.4931 | 10.7396 | 12.7396 | 9.2465 | 16.7396 | 27.4793 | 40.2189 | 0
6.0198 | 9.0099 | 8.0198 | 7.0198 | 10.0297 | 12.0297 | 9.0099 | 16.0297 | 26.0594 | 38.0892 | 6.0198 | 9.0099 | 8.0298 | 7.0198 | 10.0297 | 12.0297 | 9.0099 | 16.0297 | 26.0594 | 38.0892 | 0
5.2393 | 8.6197 | 7.2393 | 6.2393 | 8.859 | 10.859 | 8.6197 | 14.859 | 23.718 | 34.577 | 5.2393 | 8.6197 | 7.2493 | 6.2393 | 8.859 | 10.859 | 8.6197 | 14.859 | 23.718 | 34.577 | 0
5.4805 | 8.7403 | 7.4805 | 6.4805 | 9.2208 | 11.2208 | 8.7403 | 15.2208 | 24.4416 | 35.6624 | 5.4805 | 8.7403 | 7.4905 | 6.4805 | 9.2208 | 11.2208 | 8.7403 | 15.2208 | 24.4416 | 35.6624 | 0
3.5992 | 7.7996 | 5.5992 | 4.5992 | 6.3988 | 8.3988 | 7.7996 | 12.3988 | 18.7976 | 27.1965 | 3.5992 | 7.7996 | 5.6092 | 4.5992 | 6.3988 | 8.3988 | 7.7996 | 12.3988 | 18.7976 | 27.1965 | 0
2.2806 | 7.1403 | 4.2806 | 3.2806 | 4.4209 | 6.4209 | 7.1403 | 10.4209 | 14.8419 | 21.2628 | 2.2806 | 7.1403 | 4.2906 | 3.2806 | 4.4209 | 6.4209 | 7.1403 | 10.4209 | 14.8419 | 21.2628 | 0
6.9264 | 9.4632 | 8.9264 | 7.9264 | 11.3897 | 13.3897 | 9.4632 | 17.3897 | 28.7793 | 42.169 | 6.9264 | 9.4632 | 8.9364 | 7.9264 | 11.3897 | 13.3897 | 9.4632 | 17.3897 | 28.7793 | 42.169 | 0
4.5848 | 8.2924 | 6.5848 | 5.5848 | 7.8772 | 9.8772 | 8.2924 | 13.8772 | 21.7545 | 31.6317 | 4.5848 | 8.2924 | 6.5948 | 5.5848 | 7.8772 | 9.8772 | 8.2924 | 13.8772 | 21.7545 | 31.6317 | 0
5.8871 | 8.9436 | 7.8871 | 6.8871 | 9.8307 | 11.8307 | 8.9436 | 15.8307 | 25.6613 | 37.492 | 5.8871 | 8.9436 | 7.8971 | 6.8871 | 9.8307 | 11.8307 | 8.9436 | 15.8307 | 25.6613 | 37.492 | 0
4.4375 | 8.2187 | 6.4375 | 5.4375 | 7.6562 | 9.6562 | 8.2187 | 13.6562 | 21.3124 | 30.9686 | 4.4375 | 8.2187 | 6.4475 | 5.4375 | 7.6562 | 9.6562 | 8.2187 | 13.6562 | 21.3124 | 30.9686 | 0
5.9122 | 8.9561 | 7.9122 | 6.9122 | 9.8683 | 11.8683 | 8.9561 | 15.8683 | 25.7367 | 37.605 | 5.9122 | 8.9561 | 7.9222 | 6.9122 | 9.8683 | 11.8683 | 8.9561 | 15.8683 | 25.7367 | 37.605 | 0
4.2985 | 8.1493 | 6.2985 | 5.2985 | 7.4478 | 9.4478 | 8.1493 | 13.4478 | 20.8955 | 30.3433 | 4.2985 | 8.1493 | 6.3085 | 5.2985 | 7.4478 | 9.4478 | 8.1493 | 13.4478 | 20.8955 | 30.3433 | 0
3.7284 | 7.8642 | 5.7284 | 4.7284 | 6.5927 | 8.5927 | 7.8642 | 12.5927 | 19.1853 | 27.778 | 3.7284 | 7.8642 | 5.7384 | 4.7284 | 6.5927 | 8.5927 | 7.8642 | 12.5927 | 19.1853 | 27.778 | 0
7.6067 | 9.8034 | 9.6067 | 8.6067 | 12.4101 | 14.4101 | 9.8034 | 18.4101 | 30.8202 | 45.2303 | 7.6067 | 9.8034 | 9.6167 | 8.6067 | 12.4101 | 14.4101 | 9.8034 | 18.4101 | 30.8202 | 45.2303 | 0
8.6808 | 10.3404 | 10.6808 | 9.6808 | 14.0212 | 16.0212 | 10.3404 | 20.0212 | 34.0423 | 50.0635 | 8.6808 | 10.3404 | 10.6908 | 9.6808 | 14.0212 | 16.0212 | 10.3404 | 20.0212 | 34.0423 | 50.0635 | 0
5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 5.2196 | 8.6098 | 7.2296 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 0
7.6331 | 9.8165 | 9.6331 | 8.6331 | 12.4496 | 14.4496 | 9.8165 | 18.4496 | 30.8992 | 45.3488 | 7.6331 | 9.8165 | 9.6431 | 8.6331 | 12.4496 | 14.4496 | 9.8165 | 18.4496 | 30.8992 | 45.3488 | 0
4.2833 | 8.1416 | 6.2833 | 5.2833 | 7.4249 | 9.4249 | 8.1416 | 13.4249 | 20.8499 | 30.2748 | 4.2833 | 8.1416 | 6.2933 | 5.2833 | 7.4249 | 9.4249 | 8.1416 | 13.4249 | 20.8499 | 30.2748 | 0
4.5407 | 8.2703 | 6.5407 | 5.5407 | 7.811 | 9.811 | 8.2703 | 13.811 | 21.622 | 31.433 | 4.5407 | 8.2703 | 6.5507 | 5.5407 | 7.811 | 9.811 | 8.2703 | 13.811 | 21.622 | 31.433 | 0
6.1115 | 9.0558 | 8.1115 | 7.1115 | 10.1673 | 12.1673 | 9.0558 | 16.1673 | 26.3345 | 38.5018 | 6.1115 | 9.0558 | 8.1215 | 7.1115 | 10.1673 | 12.1673 | 9.0558 | 16.1673 | 26.3345 | 38.5018 | 0
6.1999 | 9.1 | 8.1999 | 7.1999 | 10.2999 | 12.2999 | 9.1 | 16.2999 | 26.5997 | 38.8996 | 6.1999 | 9.1 | 8.2099 | 7.1999 | 10.2999 | 12.2999 | 9.1 | 16.2999 | 26.5997 | 38.8996 | 0
2.8161 | 7.408 | 4.8161 | 3.8161 | 5.2241 | 7.2241 | 7.408 | 11.2241 | 16.4482 | 23.6723 | 2.8161 | 7.408 | 4.8261 | 3.8161 | 5.2241 | 7.2241 | 7.408 | 11.2241 | 16.4482 | 23.6723 | 0
6.6314 | 9.3157 | 8.6314 | 7.6314 | 10.9471 | 12.9471 | 9.3157 | 16.9471 | 27.8943 | 40.8414 | 6.6314 | 9.3157 | 8.6414 | 7.6314 | 10.9471 | 12.9471 | 9.3157 | 16.9471 | 27.8943 | 40.8414 | 0
6.5394 | 9.2697 | 8.5394 | 7.5394 | 10.8092 | 12.8092 | 9.2697 | 16.8092 | 27.6183 | 40.4275 | 6.5394 | 9.2697 | 8.5494 | 7.5394 | 10.8092 | 12.8092 | 9.2697 | 16.8092 | 27.6183 | 40.4275 | 0
11.0521 | 11.526 | 13.0521 | 12.0521 | 17.5781 | 19.5781 | 11.526 | 23.5781 | 41.1562 | 60.7343 | 11.0521 | 11.526 | 13.0621 | 12.0521 | 17.5781 | 19.5781 | 11.526 | 23.5781 | 41.1562 | 60.7343 | 0
3.8102 | 7.9051 | 5.8102 | 4.8102 | 6.7153 | 8.7153 | 7.9051 | 12.7153 | 19.4307 | 28.146 | 3.8102 | 7.9051 | 5.8202 | 4.8102 | 6.7153 | 8.7153 | 7.9051 | 12.7153 | 19.4307 | 28.146 | 0
5.2518 | 8.6259 | 7.2518 | 6.2518 | 8.8777 | 10.8777 | 8.6259 | 14.8777 | 23.7554 | 34.6332 | 5.2518 | 8.6259 | 7.2618 | 6.2518 | 8.8777 | 10.8777 | 8.6259 | 14.8777 | 23.7554 | 34.6332 | 0
6.3771 | 9.1886 | 8.3771 | 7.3771 | 10.5657 | 12.5657 | 9.1886 | 16.5657 | 27.1314 | 39.6971 | 6.3771 | 9.1886 | 8.3871 | 7.3771 | 10.5657 | 12.5657 | 9.1886 | 16.5657 | 27.1314 | 39.6971 | 0
5.3383 | 8.6691 | 7.3383 | 6.3383 | 9.0074 | 11.0074 | 8.6691 | 15.0074 | 24.0148 | 35.0222 | 5.3383 | 8.6691 | 7.3483 | 6.3383 | 9.0074 | 11.0074 | 8.6691 | 15.0074 | 24.0148 | 35.0222 | 0
8.3948 | 10.1974 | 10.3948 | 9.3948 | 13.5922 | 15.5922 | 10.1974 | 19.5922 | 33.1845 | 48.7767 | 8.3948 | 10.1974 | 10.4048 | 9.3948 | 13.5922 | 15.5922 | 10.1974 | 19.5922 | 33.1845 | 48.7767 | 0
5.0712 | 8.5356 | 7.0712 | 6.0712 | 8.6068 | 10.6068 | 8.5356 | 14.6068 | 23.2135 | 33.8203 | 5.0712 | 8.5356 | 7.0812 | 6.0712 | 8.6068 | 10.6068 | 8.5356 | 14.6068 | 23.2135 | 33.8203 | 0
6.1543 | 9.0771 | 8.1543 | 7.1543 | 10.2314 | 12.2314 | 9.0771 | 16.2314 | 26.4629 | 38.6943 | 6.1543 | 9.0771 | 8.1643 | 7.1543 | 10.2314 | 12.2314 | 9.0771 | 16.2314 | 26.4629 | 38.6943 | 0
5.863 | 8.9315 | 7.863 | 6.863 | 9.7946 | 11.7946 | 8.9315 | 15.7946 | 25.5891 | 37.3837 | 5.863 | 8.9315 | 7.873 | 6.863 | 9.7946 | 11.7946 | 8.9315 | 15.7946 | 25.5891 | 37.3837 | 0
2.5835 | 7.2917 | 4.5835 | 3.5835 | 4.8752 | 6.8752 | 7.2917 | 10.8752 | 15.7504 | 22.6257 | 2.5835 | 7.2917 | 4.5935 | 3.5835 | 4.8752 | 6.8752 | 7.2917 | 10.8752 | 15.7504 | 22.6257 | 0
5.0249 | 8.5125 | 7.0249 | 6.0249 | 8.5374 | 10.5374 | 8.5125 | 14.5374 | 23.0747 | 33.6121 | 5.0249 | 8.5125 | 7.0349 | 6.0249 | 8.5374 | 10.5374 | 8.5125 | 14.5374 | 23.0747 | 33.6121 | 0
6.1918 | 9.0959 | 8.1918 | 7.1918 | 10.2877 | 12.2877 | 9.0959 | 16.2877 | 26.5753 | 38.863 | 6.1918 | 9.0959 | 8.2018 | 7.1918 | 10.2877 | 12.2877 | 9.0959 | 16.2877 | 26.5753 | 38.863 | 0
5.0897 | 8.5449 | 7.0897 | 6.0897 | 8.6346 | 10.6346 | 8.5449 | 14.6346 | 23.2691 | 33.9037 | 5.0897 | 8.5449 | 7.0997 | 6.0897 | 8.6346 | 10.6346 | 8.5449 | 14.6346 | 23.2691 | 33.9037 | 0
5.4889 | 8.7445 | 7.4889 | 6.4889 | 9.2334 | 11.2334 | 8.7445 | 15.2334 | 24.4667 | 35.7001 | 5.4889 | 8.7445 | 7.4989 | 6.4889 | 9.2334 | 11.2334 | 8.7445 | 15.2334 | 24.4667 | 35.7001 | 0
8.7445 | 10.3722 | 10.7445 | 9.7445 | 14.1167 | 16.1167 | 10.3722 | 20.1167 | 34.2334 | 50.3502 | 8.7445 | 10.3722 | 10.7545 | 9.7445 | 14.1167 | 16.1167 | 10.3722 | 20.1167 | 34.2334 | 50.3502 | 0
6.1328 | 9.0664 | 8.1328 | 7.1328 | 10.1992 | 12.1992 | 9.0664 | 16.1992 | 26.3985 | 38.5977 | 6.1328 | 9.0664 | 8.1428 | 7.1328 | 10.1992 | 12.1992 | 9.0664 | 16.1992 | 26.3985 | 38.5977 | 0
6.4019 | 9.201 | 8.4019 | 7.4019 | 10.6029 | 12.6029 | 9.201 | 16.6029 | 27.2058 | 39.8087 | 6.4019 | 9.201 | 8.4119 | 7.4019 | 10.6029 | 12.6029 | 9.201 | 16.6029 | 27.2058 | 39.8087 | 0
4.0371 | 8.0185 | 6.0371 | 5.0371 | 7.0556 | 9.0556 | 8.0185 | 13.0556 | 20.1112 | 29.1668 | 4.0371 | 8.0185 | 6.0471 | 5.0371 | 7.0556 | 9.0556 | 8.0185 | 13.0556 | 20.1112 | 29.1668 | 0
5.83 | 8.915 | 7.83 | 6.83 | 9.7451 | 11.7451 | 8.915 | 15.7451 | 25.4901 | 37.2352 | 5.83 | 8.915 | 7.84 | 6.83 | 9.7451 | 11.7451 | 8.915 | 15.7451 | 25.4901 | 37.2352 | 0
2.6753 | 7.3376 | 4.6753 | 3.6753 | 5.0129 | 7.0129 | 7.3376 | 11.0129 | 16.0258 | 23.0387 | 2.6753 | 7.3376 | 4.6853 | 3.6753 | 5.0129 | 7.0129 | 7.3376 | 11.0129 | 16.0258 | 23.0387 | 0
5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 5.3559 | 8.6779 | 7.3659 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 0
2.6862 | 7.3431 | 4.6862 | 3.6862 | 5.0293 | 7.0293 | 7.3431 | 11.0293 | 16.0585 | 23.0878 | 2.6862 | 7.3431 | 4.6962 | 3.6862 | 5.0293 | 7.0293 | 7.3431 | 11.0293 | 16.0585 | 23.0878 | 0
9.7341 | 10.8671 | 11.7341 | 10.7341 | 15.6012 | 17.6012 | 10.8671 | 21.6012 | 37.2024 | 54.8037 | 9.7341 | 10.8671 | 11.7441 | 10.7341 | 15.6012 | 17.6012 | 10.8671 | 21.6012 | 37.2024 | 54.8037 | 0
4.1077 | 8.0538 | 6.1077 | 5.1077 | 7.1615 | 9.1615 | 8.0538 | 13.1615 | 20.323 | 29.4845 | 4.1077 | 8.0538 | 6.1177 | 5.1077 | 7.1615 | 9.1615 | 8.0538 | 13.1615 | 20.323 | 29.4845 | 0
7.484 | 9.742 | 9.484 | 8.484 | 12.226 | 14.226 | 9.742 | 18.226 | 30.452 | 44.6781 | 7.484 | 9.742 | 9.494 | 8.484 | 12.226 | 14.226 | 9.742 | 18.226 | 30.452 | 44.6781 | 0
6.2666 | 9.1333 | 8.2666 | 7.2666 | 10.3999 | 12.3999 | 9.1333 | 16.3999 | 26.7999 | 39.1998 | 6.2666 | 9.1333 | 8.2766 | 7.2666 | 10.3999 | 12.3999 | 9.1333 | 16.3999 | 26.7999 | 39.1998 | 0
5.2959 | 8.648 | 7.2959 | 6.2959 | 8.9439 | 10.9439 | 8.648 | 14.9439 | 23.8878 | 34.8317 | 5.2959 | 8.648 | 7.3059 | 6.2959 | 8.9439 | 10.9439 | 8.648 | 14.9439 | 23.8878 | 34.8317 | 0
4.8999 | 8.45 | 6.8999 | 5.8999 | 8.3499 | 10.3499 | 8.45 | 14.3499 | 22.6998 | 33.0497 | 4.8999 | 8.45 | 6.9099 | 5.8999 | 8.3499 | 10.3499 | 8.45 | 14.3499 | 22.6998 | 33.0497 | 0
5.8151 | 8.9076 | 7.8151 | 6.8151 | 9.7227 | 11.7227 | 8.9076 | 15.7227 | 25.4454 | 37.1682 | 5.8151 | 8.9076 | 7.8251 | 6.8151 | 9.7227 | 11.7227 | 8.9076 | 15.7227 | 25.4454 | 37.1682 | 0
5.9292 | 8.9646 | 7.9292 | 6.9292 | 9.8938 | 11.8938 | 8.9646 | 15.8938 | 25.7877 | 37.6815 | 5.9292 | 8.9646 | 7.9392 | 6.9292 | 9.8938 | 11.8938 | 8.9646 | 15.8938 | 25.7877 | 37.6815 | 0
2.9022 | 7.4511 | 4.9022 | 3.9022 | 5.3533 | 7.3533 | 7.4511 | 11.3533 | 16.7065 | 24.0598 | 2.9022 | 7.4511 | 4.9122 | 3.9022 | 5.3533 | 7.3533 | 7.4511 | 11.3533 | 16.7065 | 24.0598 | 0
3.7424 | 7.8712 | 5.7424 | 4.7424 | 6.6136 | 8.6136 | 7.8712 | 12.6136 | 19.2272 | 27.8407 | 3.7424 | 7.8712 | 5.7524 | 4.7424 | 6.6136 | 8.6136 | 7.8712 | 12.6136 | 19.2272 | 27.8407 | 0
8.3173 | 10.1587 | 10.3173 | 9.3173 | 13.476 | 15.476 | 10.1587 | 19.476 | 32.952 | 48.4281 | 8.3173 | 10.1587 | 10.3273 | 9.3173 | 13.476 | 15.476 | 10.1587 | 19.476 | 32.952 | 48.4281 | 0
4.7975 | 8.3988 | 6.7975 | 5.7975 | 8.1963 | 10.1963 | 8.3988 | 14.1963 | 22.3926 | 32.5889 | 4.7975 | 8.3988 | 6.8075 | 5.7975 | 8.1963 | 10.1963 | 8.3988 | 14.1963 | 22.3926 | 32.5889 | 0
4.0727 | 8.0363 | 6.0727 | 5.0727 | 7.109 | 9.109 | 8.0363 | 13.109 | 20.218 | 29.327 | 4.0727 | 8.0363 | 6.0827 | 5.0727 | 7.109 | 9.109 | 8.0363 | 13.109 | 20.218 | 29.327 | 0
7.2028 | 9.6014 | 9.2028 | 8.2028 | 11.8042 | 13.8042 | 9.6014 | 17.8042 | 29.6085 | 43.4127 | 7.2028 | 9.6014 | 9.2128 | 8.2028 | 11.8042 | 13.8042 | 9.6014 | 17.8042 | 29.6085 | 43.4127 | 0
5.1967 | 8.5984 | 7.1967 | 6.1967 | 8.7951 | 10.7951 | 8.5984 | 14.7951 | 23.5902 | 34.3852 | 5.1967 | 8.5984 | 7.2067 | 6.1967 | 8.7951 | 10.7951 | 8.5984 | 14.7951 | 23.5902 | 34.3852 | 0
3.0576 | 7.5288 | 5.0576 | 4.0576 | 5.5864 | 7.5864 | 7.5288 | 11.5864 | 17.1729 | 24.7593 | 3.0576 | 7.5288 | 5.0676 | 4.0576 | 5.5864 | 7.5864 | 7.5288 | 11.5864 | 17.1729 | 24.7593 | 0
4.772 | 8.386 | 6.772 | 5.772 | 8.1579 | 10.1579 | 8.386 | 14.1579 | 22.3159 | 32.4738 | 4.772 | 8.386 | 6.782 | 5.772 | 8.1579 | 10.1579 | 8.386 | 14.1579 | 22.3159 | 32.4738 | 0
6.9343 | 9.4671 | 8.9343 | 7.9343 | 11.4014 | 13.4014 | 9.4671 | 17.4014 | 28.8028 | 42.2043 | 6.9343 | 9.4671 | 8.9443 | 7.9343 | 11.4014 | 13.4014 | 9.4671 | 17.4014 | 28.8028 | 42.2043 | 0
5.9782 | 8.9891 | 7.9782 | 6.9782 | 9.9673 | 11.9673 | 8.9891 | 15.9673 | 25.9346 | 37.9019 | 5.9782 | 8.9891 | 7.9882 | 6.9782 | 9.9673 | 11.9673 | 8.9891 | 15.9673 | 25.9346 | 37.9019 | 0
4.3539 | 8.1769 | 6.3539 | 5.3539 | 7.5308 | 9.5308 | 8.1769 | 13.5308 | 21.0616 | 30.5925 | 4.3539 | 8.1769 | 6.3639 | 5.3539 | 7.5308 | 9.5308 | 8.1769 | 13.5308 | 21.0616 | 30.5925 | 0
4.4273 | 8.2136 | 6.4273 | 5.4273 | 7.6409 | 9.6409 | 8.2136 | 13.6409 | 21.2818 | 30.9227 | 4.4273 | 8.2136 | 6.4373 | 5.4273 | 7.6409 | 9.6409 | 8.2136 | 13.6409 | 21.2818 | 30.9227 | 0
5.6648 | 8.8324 | 7.6648 | 6.6648 | 9.4972 | 11.4972 | 8.8324 | 15.4972 | 24.9945 | 36.4917 | 5.6648 | 8.8324 | 7.6748 | 6.6648 | 9.4972 | 11.4972 | 8.8324 | 15.4972 | 24.9945 | 36.4917 | 0
6.1502 | 9.0751 | 8.1502 | 7.1502 | 10.2252 | 12.2252 | 9.0751 | 16.2252 | 26.4505 | 38.6757 | 6.1502 | 9.0751 | 8.1602 | 7.1502 | 10.2252 | 12.2252 | 9.0751 | 16.2252 | 26.4505 | 38.6757 | 0
13.0455 | 12.5227 | 15.0455 | 14.0455 | 20.5682 | 22.5682 | 13.0455 | 27.0909 | 47.6591 | 70.2273 | 13.0455 | 12.5227 | 15.0555 | 14.0455 | 20.5682 | 22.5682 | 13.0455 | 27.0909 | 47.6591 | 70.2273 | 0
7.6173 | 9.8087 | 9.6173 | 8.6173 | 12.426 | 14.426 | 9.8087 | 18.426 | 30.8519 | 45.2779 | 7.6173 | 9.8087 | 9.6273 | 8.6173 | 12.426 | 14.426 | 9.8087 | 18.426 | 30.8519 | 45.2779 | 0
8.3774 | 10.1887 | 10.3774 | 9.3774 | 13.566 | 15.566 | 10.1887 | 19.566 | 33.1321 | 48.6981 | 8.3774 | 10.1887 | 10.3874 | 9.3774 | 13.566 | 15.566 | 10.1887 | 19.566 | 33.1321 | 48.6981 | 0
6.074 | 9.037 | 8.074 | 7.074 | 10.111 | 12.111 | 9.037 | 16.111 | 26.222 | 38.333 | 6.074 | 9.037 | 8.084 | 7.074 | 10.111 | 12.111 | 9.037 | 16.111 | 26.222 | 38.333 | 0
5.9353 | 8.9677 | 7.9353 | 6.9353 | 9.903 | 11.903 | 8.9677 | 15.903 | 25.806 | 37.7091 | 5.9353 | 8.9677 | 7.9453 | 6.9353 | 9.903 | 11.903 | 8.9677 | 15.903 | 25.806 | 37.7091 | 0
6.9629 | 9.4814 | 8.9629 | 7.9629 | 11.4443 | 13.4443 | 9.4814 | 17.4443 | 28.8886 | 42.3329 | 6.9629 | 9.4814 | 8.9729 | 7.9629 | 11.4443 | 13.4443 | 9.4814 | 17.4443 | 28.8886 | 42.3329 | 0
3.2723 | 7.6361 | 5.2723 | 4.2723 | 5.9084 | 7.9084 | 7.6361 | 11.9084 | 17.8169 | 25.7253 | 3.2723 | 7.6361 | 5.2823 | 4.2723 | 5.9084 | 7.9084 | 7.6361 | 11.9084 | 17.8169 | 25.7253 | 0
5.3875 | 8.6938 | 7.3875 | 6.3875 | 9.0813 | 11.0813 | 8.6938 | 15.0813 | 24.1626 | 35.2438 | 5.3875 | 8.6938 | 7.3975 | 6.3875 | 9.0813 | 11.0813 | 8.6938 | 15.0813 | 24.1626 | 35.2438 | 0
2.8991 | 7.4496 | 4.8991 | 3.8991 | 5.3487 | 7.3487 | 7.4496 | 11.3487 | 16.6974 | 24.0461 | 2.8991 | 7.4496 | 4.9091 | 3.8991 | 5.3487 | 7.3487 | 7.4496 | 11.3487 | 16.6974 | 24.0461 | 0
6.8927 | 9.4463 | 8.8927 | 7.8927 | 11.339 | 13.339 | 9.4463 | 17.339 | 28.678 | 42.017 | 6.8927 | 9.4463 | 8.9027 | 7.8927 | 11.339 | 13.339 | 9.4463 | 17.339 | 28.678 | 42.017 | 0
5.2946 | 8.6473 | 7.2946 | 6.2946 | 8.942 | 10.942 | 8.6473 | 14.942 | 23.8839 | 34.8259 | 5.2946 | 8.6473 | 7.3046 | 6.2946 | 8.942 | 10.942 | 8.6473 | 14.942 | 23.8839 | 34.8259 | 0
7.3723 | 9.6861 | 9.3723 | 8.3723 | 12.0584 | 14.0584 | 9.6861 | 18.0584 | 30.1168 | 44.1752 | 7.3723 | 9.6861 | 9.3823 | 8.3723 | 12.0584 | 14.0584 | 9.6861 | 18.0584 | 30.1168 | 44.1752 | 0
6.4354 | 9.2177 | 8.4354 | 7.4354 | 10.6531 | 12.6531 | 9.2177 | 16.6531 | 27.3062 | 39.9593 | 6.4354 | 9.2177 | 8.4454 | 7.4354 | 10.6531 | 12.6531 | 9.2177 | 16.6531 | 27.3062 | 39.9593 | 0
5.4793 | 8.7396 | 7.4793 | 6.4793 | 9.2189 | 11.2189 | 8.7396 | 15.2189 | 24.4378 | 35.6567 | 5.4793 | 8.7396 | 7.4893 | 6.4793 | 9.2189 | 11.2189 | 8.7396 | 15.2189 | 24.4378 | 35.6567 | 0
6.2472 | 9.1236 | 8.2472 | 7.2472 | 10.3708 | 12.3708 | 9.1236 | 16.3708 | 26.7415 | 39.1123 | 6.2472 | 9.1236 | 8.2572 | 7.2472 | 10.3708 | 12.3708 | 9.1236 | 16.3708 | 26.7415 | 39.1123 | 0
4.9739 | 8.487 | 6.9739 | 5.9739 | 8.4609 | 10.4609 | 8.487 | 14.4609 | 22.9218 | 33.3827 | 4.9739 | 8.487 | 6.9839 | 5.9739 | 8.4609 | 10.4609 | 8.487 | 14.4609 | 22.9218 | 33.3827 | 0
1.3058 | 6.6529 | 3.3058 | 2.3058 | 2.9588 | 4.9588 | 6.6529 | 8.9588 | 11.9175 | 16.8763 | 1.3058 | 6.6529 | 3.3158 | 2.3058 | 2.9588 | 4.9588 | 6.6529 | 8.9588 | 11.9175 | 16.8763 | 0
6.9362 | 9.4681 | 8.9362 | 7.9362 | 11.4042 | 13.4042 | 9.4681 | 17.4042 | 28.8085 | 42.2127 | 6.9362 | 9.4681 | 8.9462 | 7.9362 | 11.4042 | 13.4042 | 9.4681 | 17.4042 | 28.8085 | 42.2127 | 0
7.1438 | 9.5719 | 9.1438 | 8.1438 | 11.7157 | 13.7157 | 9.5719 | 17.7157 | 29.4313 | 43.147 | 7.1438 | 9.5719 | 9.1538 | 8.1438 | 11.7157 | 13.7157 | 9.5719 | 17.7157 | 29.4313 | 43.147 | 0
7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 7.2523 | 9.6262 | 9.2623 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 0
10.4708 | 11.2354 | 12.4708 | 11.4708 | 16.7062 | 18.7062 | 11.2354 | 22.7062 | 39.4124 | 58.1185 | 10.4708 | 11.2354 | 12.4808 | 11.4708 | 16.7062 | 18.7062 | 11.2354 | 22.7062 | 39.4124 | 58.1185 | 0
7.3244 | 9.6622 | 9.3244 | 8.3244 | 11.9867 | 13.9867 | 9.6622 | 17.9867 | 29.9733 | 43.96 | 7.3244 | 9.6622 | 9.3344 | 8.3244 | 11.9867 | 13.9867 | 9.6622 | 17.9867 | 29.9733 | 43.96 | 0
3.4391 | 7.7195 | 5.4391 | 4.4391 | 6.1586 | 8.1586 | 7.7195 | 12.1586 | 18.3173 | 26.4759 | 3.4391 | 7.7195 | 5.4491 | 4.4391 | 6.1586 | 8.1586 | 7.7195 | 12.1586 | 18.3173 | 26.4759 | 0
3.4033 | 7.7016 | 5.4033 | 4.4033 | 6.1049 | 8.1049 | 7.7016 | 12.1049 | 18.2098 | 26.3146 | 3.4033 | 7.7016 | 5.4133 | 4.4033 | 6.1049 | 8.1049 | 7.7016 | 12.1049 | 18.2098 | 26.3146 | 0
6.3856 | 9.1928 | 8.3856 | 7.3856 | 10.5783 | 12.5783 | 9.1928 | 16.5783 | 27.1567 | 39.735 | 6.3856 | 9.1928 | 8.3956 | 7.3856 | 10.5783 | 12.5783 | 9.1928 | 16.5783 | 27.1567 | 39.735 | 0
4.8622 | 8.4311 | 6.8622 | 5.8622 | 8.2933 | 10.2933 | 8.4311 | 14.2933 | 22.5865 | 32.8798 | 4.8622 | 8.4311 | 6.8722 | 5.8622 | 8.2933 | 10.2933 | 8.4311 | 14.2933 | 22.5865 | 32.8798 | 0
6.2649 | 9.1325 | 8.2649 | 7.2649 | 10.3974 | 12.3974 | 9.1325 | 16.3974 | 26.7948 | 39.1921 | 6.2649 | 9.1325 | 8.2749 | 7.2649 | 10.3974 | 12.3974 | 9.1325 | 16.3974 | 26.7948 | 39.1921 | 0
6.3815 | 9.1908 | 8.3815 | 7.3815 | 10.5723 | 12.5723 | 9.1908 | 16.5723 | 27.1445 | 39.7168 | 6.3815 | 9.1908 | 8.3915 | 7.3815 | 10.5723 | 12.5723 | 9.1908 | 16.5723 | 27.1445 | 39.7168 | 0
6.0503 | 9.0251 | 8.0503 | 7.0503 | 10.0754 | 12.0754 | 9.0251 | 16.0754 | 26.1508 | 38.2262 | 6.0503 | 9.0251 | 8.0603 | 7.0503 | 10.0754 | 12.0754 | 9.0251 | 16.0754 | 26.1508 | 38.2262 | 0
7.3199 | 9.6599 | 9.3199 | 8.3199 | 11.9798 | 13.9798 | 9.6599 | 17.9798 | 29.9596 | 43.9394 | 7.3199 | 9.6599 | 9.3299 | 8.3199 | 11.9798 | 13.9798 | 9.6599 | 17.9798 | 29.9596 | 43.9394 | 0
4.8278 | 8.4139 | 6.8278 | 5.8278 | 8.2417 | 10.2417 | 8.4139 | 14.2417 | 22.4835 | 32.7252 | 4.8278 | 8.4139 | 6.8378 | 5.8278 | 8.2417 | 10.2417 | 8.4139 | 14.2417 | 22.4835 | 32.7252 | 0
5.4652 | 8.7326 | 7.4652 | 6.4652 | 9.1977 | 11.1977 | 8.7326 | 15.1977 | 24.3955 | 35.5932 | 5.4652 | 8.7326 | 7.4752 | 6.4652 | 9.1977 | 11.1977 | 8.7326 | 15.1977 | 24.3955 | 35.5932 | 0
3.3593 | 7.6796 | 5.3593 | 4.3593 | 6.0389 | 8.0389 | 7.6796 | 12.0389 | 18.0778 | 26.1167 | 3.3593 | 7.6796 | 5.3693 | 4.3593 | 6.0389 | 8.0389 | 7.6796 | 12.0389 | 18.0778 | 26.1167 | 0
7.5124 | 9.7562 | 9.5124 | 8.5124 | 12.2686 | 14.2686 | 9.7562 | 18.2686 | 30.5371 | 44.8057 | 7.5124 | 9.7562 | 9.5224 | 8.5124 | 12.2686 | 14.2686 | 9.7562 | 18.2686 | 30.5371 | 44.8057 | 0
3.9132 | 7.9566 | 5.9132 | 4.9132 | 6.8698 | 8.8698 | 7.9566 | 12.8698 | 19.7396 | 28.6094 | 3.9132 | 7.9566 | 5.9232 | 4.9132 | 6.8698 | 8.8698 | 7.9566 | 12.8698 | 19.7396 | 28.6094 | 0
1.5199 | 6.7599 | 3.5199 | 2.5199 | 3.2798 | 5.2798 | 6.7599 | 9.2798 | 12.5596 | 17.8394 | 1.5199 | 6.7599 | 3.5299 | 2.5199 | 3.2798 | 5.2798 | 6.7599 | 9.2798 | 12.5596 | 17.8394 | 0
4.6499 | 8.325 | 6.6499 | 5.6499 | 7.9749 | 9.9749 | 8.325 | 13.9749 | 21.9497 | 31.9246 | 4.6499 | 8.325 | 6.6599 | 5.6499 | 7.9749 | 9.9749 | 8.325 | 13.9749 | 21.9497 | 31.9246 | 0
4.3616 | 8.1808 | 6.3616 | 5.3616 | 7.5424 | 9.5424 | 8.1808 | 13.5424 | 21.0848 | 30.6272 | 4.3616 | 8.1808 | 6.3716 | 5.3616 | 7.5424 | 9.5424 | 8.1808 | 13.5424 | 21.0848 | 30.6272 | 0
5.2767 | 8.6383 | 7.2767 | 6.2767 | 8.915 | 10.915 | 8.6383 | 14.915 | 23.8301 | 34.7451 | 5.2767 | 8.6383 | 7.2867 | 6.2767 | 8.915 | 10.915 | 8.6383 | 14.915 | 23.8301 | 34.7451 | 0
4.6809 | 8.3404 | 6.6809 | 5.6809 | 8.0213 | 10.0213 | 8.3404 | 14.0213 | 22.0426 | 32.064 | 4.6809 | 8.3404 | 6.6909 | 5.6809 | 8.0213 | 10.0213 | 8.3404 | 14.0213 | 22.0426 | 32.064 | 0
7.3392 | 9.6696 | 9.3392 | 8.3392 | 12.0087 | 14.0087 | 9.6696 | 18.0087 | 30.0175 | 44.0262 | 7.3392 | 9.6696 | 9.3492 | 8.3392 | 12.0087 | 14.0087 | 9.6696 | 18.0087 | 30.0175 | 44.0262 | 0
5.9878 | 8.9939 | 7.9878 | 6.9878 | 9.9818 | 11.9818 | 8.9939 | 15.9818 | 25.9635 | 37.9453 | 5.9878 | 8.9939 | 7.9978 | 6.9878 | 9.9818 | 11.9818 | 8.9939 | 15.9818 | 25.9635 | 37.9453 | 0
7.2575 | 9.6288 | 9.2575 | 8.2575 | 11.8863 | 13.8863 | 9.6288 | 17.8863 | 29.7726 | 43.659 | 7.2575 | 9.6288 | 9.2675 | 8.2575 | 11.8863 | 13.8863 | 9.6288 | 17.8863 | 29.7726 | 43.659 | 0
6.2064 | 9.1032 | 8.2064 | 7.2064 | 10.3096 | 12.3096 | 9.1032 | 16.3096 | 26.6191 | 38.9287 | 6.2064 | 9.1032 | 8.2164 | 7.2064 | 10.3096 | 12.3096 | 9.1032 | 16.3096 | 26.6191 | 38.9287 | 0
3.8799 | 7.94 | 5.8799 | 4.8799 | 6.8199 | 8.8199 | 7.94 | 12.8199 | 19.6398 | 28.4598 | 3.8799 | 7.94 | 5.8899 | 4.8799 | 6.8199 | 8.8199 | 7.94 | 12.8199 | 19.6398 | 28.4598 | 0
2.4504 | 7.2252 | 4.4504 | 3.4504 | 4.6756 | 6.6756 | 7.2252 | 10.6756 | 15.3512 | 22.0267 | 2.4504 | 7.2252 | 4.4604 | 3.4504 | 4.6756 | 6.6756 | 7.2252 | 10.6756 | 15.3512 | 22.0267 | 0
5.7233 | 8.8617 | 7.7233 | 6.7233 | 9.585 | 11.585 | 8.8617 | 15.585 | 25.17 | 36.755 | 5.7233 | 8.8617 | 7.7333 | 6.7233 | 9.585 | 11.585 | 8.8617 | 15.585 | 25.17 | 36.755 | 0
8.2167 | 10.1084 | 10.2167 | 9.2167 | 13.3251 | 15.3251 | 10.1084 | 19.3251 | 32.6501 | 47.9752 | 8.2167 | 10.1084 | 10.2267 | 9.2167 | 13.3251 | 15.3251 | 10.1084 | 19.3251 | 32.6501 | 47.9752 | 0
5.8225 | 8.9113 | 7.8225 | 6.8225 | 9.7338 | 11.7338 | 8.9113 | 15.7338 | 25.4676 | 37.2013 | 5.8225 | 8.9113 | 7.8325 | 6.8225 | 9.7338 | 11.7338 | 8.9113 | 15.7338 | 25.4676 | 37.2013 | 0
4.44 | 8.22 | 6.44 | 5.44 | 7.6599 | 9.6599 | 8.22 | 13.6599 | 21.3199 | 30.9798 | 4.44 | 8.22 | 6.45 | 5.44 | 7.6599 | 9.6599 | 8.22 | 13.6599 | 21.3199 | 30.9798 | 0
5.5445 | 8.7723 | 7.5445 | 6.5445 | 9.3168 | 11.3168 | 8.7723 | 15.3168 | 24.6336 | 35.9503 | 5.5445 | 8.7723 | 7.5545 | 6.5445 | 9.3168 | 11.3168 | 8.7723 | 15.3168 | 24.6336 | 35.9503 | 0
6.9782 | 9.4891 | 8.9782 | 7.9782 | 11.4673 | 13.4673 | 9.4891 | 17.4673 | 28.9346 | 42.4018 | 6.9782 | 9.4891 | 8.9882 | 7.9782 | 11.4673 | 13.4673 | 9.4891 | 17.4673 | 28.9346 | 42.4018 | 0
4.06 | 8.03 | 6.06 | 5.06 | 7.09 | 9.09 | 8.03 | 13.09 | 20.1799 | 29.2699 | 4.06 | 8.03 | 6.07 | 5.06 | 7.09 | 9.09 | 8.03 | 13.09 | 20.1799 | 29.2699 | 0
6.8952 | 9.4476 | 8.8952 | 7.8952 | 11.3428 | 13.3428 | 9.4476 | 17.3428 | 28.6856 | 42.0284 | 6.8952 | 9.4476 | 8.9052 | 7.8952 | 11.3428 | 13.3428 | 9.4476 | 17.3428 | 28.6856 | 42.0284 | 0
4.2954 | 8.1477 | 6.2954 | 5.2954 | 7.4431 | 9.4431 | 8.1477 | 13.4431 | 20.8863 | 30.3294 | 4.2954 | 8.1477 | 6.3054 | 5.2954 | 7.4431 | 9.4431 | 8.1477 | 13.4431 | 20.8863 | 30.3294 | 0
5.384 | 8.692 | 7.384 | 6.384 | 9.076 | 11.076 | 8.692 | 15.076 | 24.152 | 35.228 | 5.384 | 8.692 | 7.394 | 6.384 | 9.076 | 11.076 | 8.692 | 15.076 | 24.152 | 35.228 | 0
5.5138 | 8.7569 | 7.5138 | 6.5138 | 9.2708 | 11.2708 | 8.7569 | 15.2708 | 24.5415 | 35.8123 | 5.5138 | 8.7569 | 7.5238 | 6.5138 | 9.2708 | 11.2708 | 8.7569 | 15.2708 | 24.5415 | 35.8123 | 0
6.558 | 9.279 | 8.558 | 7.558 | 10.837 | 12.837 | 9.279 | 16.837 | 27.6741 | 40.5111 | 6.558 | 9.279 | 8.568 | 7.558 | 10.837 | 12.837 | 9.279 | 16.837 | 27.6741 | 40.5111 | 0
6.8751 | 9.4376 | 8.8751 | 7.8751 | 11.3127 | 13.3127 | 9.4376 | 17.3127 | 28.6254 | 41.9381 | 6.8751 | 9.4376 | 8.8851 | 7.8751 | 11.3127 | 13.3127 | 9.4376 | 17.3127 | 28.6254 | 41.9381 | 0
5.5105 | 8.7553 | 7.5105 | 6.5105 | 9.2658 | 11.2658 | 8.7553 | 15.2658 | 24.5316 | 35.7974 | 5.5105 | 8.7553 | 7.5205 | 6.5105 | 9.2658 | 11.2658 | 8.7553 | 15.2658 | 24.5316 | 35.7974 | 0
3.8041 | 7.902 | 5.8041 | 4.8041 | 6.7061 | 8.7061 | 7.902 | 12.7061 | 19.4123 | 28.1184 | 3.8041 | 7.902 | 5.8141 | 4.8041 | 6.7061 | 8.7061 | 7.902 | 12.7061 | 19.4123 | 28.1184 | 0
6.5984 | 9.2992 | 8.5984 | 7.5984 | 10.8976 | 12.8976 | 9.2992 | 16.8976 | 27.7952 | 40.6927 | 6.5984 | 9.2992 | 8.6084 | 7.5984 | 10.8976 | 12.8976 | 9.2992 | 16.8976 | 27.7952 | 40.6927 | 0
4.1412 | 8.0706 | 6.1412 | 5.1412 | 7.2117 | 9.2117 | 8.0706 | 13.2117 | 20.4235 | 29.6352 | 4.1412 | 8.0706 | 6.1512 | 5.1412 | 7.2117 | 9.2117 | 8.0706 | 13.2117 | 20.4235 | 29.6352 | 0
8.1884 | 10.0942 | 10.1884 | 9.1884 | 13.2826 | 15.2826 | 10.0942 | 19.2826 | 32.5651 | 47.8477 | 8.1884 | 10.0942 | 10.1984 | 9.1884 | 13.2826 | 15.2826 | 10.0942 | 19.2826 | 32.5651 | 47.8477 | 0
3.3929 | 7.6965 | 5.3929 | 4.3929 | 6.0894 | 8.0894 | 7.6965 | 12.0894 | 18.1787 | 26.2681 | 3.3929 | 7.6965 | 5.4029 | 4.3929 | 6.0894 | 8.0894 | 7.6965 | 12.0894 | 18.1787 | 26.2681 | 0
8.253 | 10.1265 | 10.253 | 9.253 | 13.3795 | 15.3795 | 10.1265 | 19.3795 | 32.759 | 48.1384 | 8.253 | 10.1265 | 10.263 | 9.253 | 13.3795 | 15.3795 | 10.1265 | 19.3795 | 32.759 | 48.1384 | 0
6.3518 | 9.1759 | 8.3518 | 7.3518 | 10.5277 | 12.5277 | 9.1759 | 16.5277 | 27.0554 | 39.583 | 6.3518 | 9.1759 | 8.3618 | 7.3518 | 10.5277 | 12.5277 | 9.1759 | 16.5277 | 27.0554 | 39.583 | 0
6.4248 | 9.2124 | 8.4248 | 7.4248 | 10.6371 | 12.6371 | 9.2124 | 16.6371 | 27.2743 | 39.9114 | 6.4248 | 9.2124 | 8.4348 | 7.4248 | 10.6371 | 12.6371 | 9.2124 | 16.6371 | 27.2743 | 39.9114 | 0
4.0788 | 8.0394 | 6.0788 | 5.0788 | 7.1181 | 9.1181 | 8.0394 | 13.1181 | 20.2363 | 29.3544 | 4.0788 | 8.0394 | 6.0888 | 5.0788 | 7.1181 | 9.1181 | 8.0394 | 13.1181 | 20.2363 | 29.3544 | 0
3.7415 | 7.8708 | 5.7415 | 4.7415 | 6.6123 | 8.6123 | 7.8708 | 12.6123 | 19.2246 | 27.8368 | 3.7415 | 7.8708 | 5.7515 | 4.7415 | 6.6123 | 8.6123 | 7.8708 | 12.6123 | 19.2246 | 27.8368 | 0
7.8238 | 9.9119 | 9.8238 | 8.8238 | 12.7357 | 14.7357 | 9.9119 | 18.7357 | 31.4713 | 46.207 | 7.8238 | 9.9119 | 9.8338 | 8.8238 | 12.7357 | 14.7357 | 9.9119 | 18.7357 | 31.4713 | 46.207 | 0
5.4348 | 8.7174 | 7.4348 | 6.4348 | 9.1522 | 11.1522 | 8.7174 | 15.1522 | 24.3044 | 35.4567 | 5.4348 | 8.7174 | 7.4448 | 6.4348 | 9.1522 | 11.1522 | 8.7174 | 15.1522 | 24.3044 | 35.4567 | 0
4.2646 | 8.1323 | 6.2646 | 5.2646 | 7.397 | 9.397 | 8.1323 | 13.397 | 20.7939 | 30.1909 | 4.2646 | 8.1323 | 6.2746 | 5.2646 | 7.397 | 9.397 | 8.1323 | 13.397 | 20.7939 | 30.1909 | 0
5.7679 | 8.884 | 7.7679 | 6.7679 | 9.6519 | 11.6519 | 8.884 | 15.6519 | 25.3038 | 36.9556 | 5.7679 | 8.884 | 7.7779 | 6.7679 | 9.6519 | 11.6519 | 8.884 | 15.6519 | 25.3038 | 36.9556 | 0
6.0709 | 9.0355 | 8.0709 | 7.0709 | 10.1064 | 12.1064 | 9.0355 | 16.1064 | 26.2128 | 38.3192 | 6.0709 | 9.0355 | 8.0809 | 7.0709 | 10.1064 | 12.1064 | 9.0355 | 16.1064 | 26.2128 | 38.3192 | 0
7.1335 | 9.5668 | 9.1335 | 8.1335 | 11.7003 | 13.7003 | 9.5668 | 17.7003 | 29.4005 | 43.1008 | 7.1335 | 9.5668 | 9.1435 | 8.1335 | 11.7003 | 13.7003 | 9.5668 | 17.7003 | 29.4005 | 43.1008 | 0
7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 7.2523 | 9.6262 | 9.2623 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 0
1.7153 | 6.8577 | 3.7153 | 2.7153 | 3.573 | 5.573 | 6.8577 | 9.573 | 13.146 | 18.719 | 1.7153 | 6.8577 | 3.7253 | 2.7153 | 3.573 | 5.573 | 6.8577 | 9.573 | 13.146 | 18.719 | 0
2.3377 | 7.1689 | 4.3377 | 3.3377 | 4.5066 | 6.5066 | 7.1689 | 10.5066 | 15.0132 | 21.5197 | 2.3377 | 7.1689 | 4.3477 | 3.3377 | 4.5066 | 6.5066 | 7.1689 | 10.5066 | 15.0132 | 21.5197 | 0
4.5542 | 8.2771 | 6.5542 | 5.5542 | 7.8313 | 9.8313 | 8.2771 | 13.8313 | 21.6626 | 31.4939 | 4.5542 | 8.2771 | 6.5642 | 5.5542 | 7.8313 | 9.8313 | 8.2771 | 13.8313 | 21.6626 | 31.4939 | 0
8.0371 | 10.0185 | 10.0371 | 9.0371 | 13.0556 | 15.0556 | 10.0185 | 19.0556 | 32.1113 | 47.1669 | 8.0371 | 10.0185 | 10.0471 | 9.0371 | 13.0556 | 15.0556 | 10.0185 | 19.0556 | 32.1113 | 47.1669 | 0
9.1147 | 10.5573 | 11.1147 | 10.1147 | 14.672 | 16.672 | 10.5573 | 20.672 | 35.3441 | 52.0161 | 9.1147 | 10.5573 | 11.1247 | 10.1147 | 14.672 | 16.672 | 10.5573 | 20.672 | 35.3441 | 52.0161 | 0
6.8241 | 9.412 | 8.8241 | 7.8241 | 11.2361 | 13.2361 | 9.412 | 17.2361 | 28.4722 | 41.7083 | 6.8241 | 9.412 | 8.8341 | 7.8241 | 11.2361 | 13.2361 | 9.412 | 17.2361 | 28.4722 | 41.7083 | 0
6.7062 | 9.3531 | 8.7062 | 7.7062 | 11.0593 | 13.0593 | 9.3531 | 17.0593 | 28.1185 | 41.1778 | 6.7062 | 9.3531 | 8.7162 | 7.7062 | 11.0593 | 13.0593 | 9.3531 | 17.0593 | 28.1185 | 41.1778 | 0
5.2576 | 8.6288 | 7.2576 | 6.2576 | 8.8863 | 10.8863 | 8.6288 | 14.8863 | 23.7727 | 34.659 | 5.2576 | 8.6288 | 7.2676 | 6.2576 | 8.8863 | 10.8863 | 8.6288 | 14.8863 | 23.7727 | 34.659 | 0
6.3132 | 9.1566 | 8.3132 | 7.3132 | 10.4697 | 12.4697 | 9.1566 | 16.4697 | 26.9395 | 39.4092 | 6.3132 | 9.1566 | 8.3232 | 7.3132 | 10.4697 | 12.4697 | 9.1566 | 16.4697 | 26.9395 | 39.4092 | 0
5.6124 | 8.8062 | 7.6124 | 6.6124 | 9.4186 | 11.4186 | 8.8062 | 15.4186 | 24.8373 | 36.2559 | 5.6124 | 8.8062 | 7.6224 | 6.6124 | 9.4186 | 11.4186 | 8.8062 | 15.4186 | 24.8373 | 36.2559 | 0
4.4577 | 8.2289 | 6.4577 | 5.4577 | 7.6866 | 9.6866 | 8.2289 | 13.6866 | 21.3732 | 31.0598 | 4.4577 | 8.2289 | 6.4677 | 5.4577 | 7.6866 | 9.6866 | 8.2289 | 13.6866 | 21.3732 | 31.0598 | 0
7.1172 | 9.5586 | 9.1172 | 8.1172 | 11.6758 | 13.6758 | 9.5586 | 17.6758 | 29.3516 | 43.0274 | 7.1172 | 9.5586 | 9.1272 | 8.1172 | 11.6758 | 13.6758 | 9.5586 | 17.6758 | 29.3516 | 43.0274 | 0
1.8832 | 6.9416 | 3.8832 | 2.8832 | 3.8248 | 5.8248 | 6.9416 | 9.8248 | 13.6496 | 19.4744 | 1.8832 | 6.9416 | 3.8932 | 2.8832 | 3.8248 | 5.8248 | 6.9416 | 9.8248 | 13.6496 | 19.4744 | 0
9.3963 | 10.6981 | 11.3963 | 10.3963 | 15.0944 | 17.0944 | 10.6981 | 21.0944 | 36.1889 | 53.2833 | 9.3963 | 10.6981 | 11.4063 | 10.3963 | 15.0944 | 17.0944 | 10.6981 | 21.0944 | 36.1889 | 53.2833 | 0
5.7522 | 8.8761 | 7.7522 | 6.7522 | 9.6283 | 11.6283 | 8.8761 | 15.6283 | 25.2566 | 36.8849 | 5.7522 | 8.8761 | 7.7622 | 6.7522 | 9.6283 | 11.6283 | 8.8761 | 15.6283 | 25.2566 | 36.8849 | 0
8.7802 | 10.3901 | 10.7802 | 9.7802 | 14.1703 | 16.1703 | 10.3901 | 20.1703 | 34.3407 | 50.511 | 8.7802 | 10.3901 | 10.7902 | 9.7802 | 14.1703 | 16.1703 | 10.3901 | 20.1703 | 34.3407 | 50.511 | 0
6.4029 | 9.2014 | 8.4029 | 7.4029 | 10.6043 | 12.6043 | 9.2014 | 16.6043 | 27.2086 | 39.8129 | 6.4029 | 9.2014 | 8.4129 | 7.4029 | 10.6043 | 12.6043 | 9.2014 | 16.6043 | 27.2086 | 39.8129 | 0
3.783 | 7.8915 | 5.783 | 4.783 | 6.6745 | 8.6745 | 7.8915 | 12.6745 | 19.349 | 28.0235 | 3.783 | 7.8915 | 5.793 | 4.783 | 6.6745 | 8.6745 | 7.8915 | 12.6745 | 19.349 | 28.0235 | 0
4.0209 | 8.0105 | 6.0209 | 5.0209 | 7.0314 | 9.0314 | 8.0105 | 13.0314 | 20.0627 | 29.0941 | 4.0209 | 8.0105 | 6.0309 | 5.0209 | 7.0314 | 9.0314 | 8.0105 | 13.0314 | 20.0627 | 29.0941 | 0
6.4079 | 9.2039 | 8.4079 | 7.4079 | 10.6118 | 12.6118 | 9.2039 | 16.6118 | 27.2236 | 39.8354 | 6.4079 | 9.2039 | 8.4179 | 7.4079 | 10.6118 | 12.6118 | 9.2039 | 16.6118 | 27.2236 | 39.8354 | 0
6.5453 | 9.2727 | 8.5453 | 7.5453 | 10.818 | 12.818 | 9.2727 | 16.818 | 27.6359 | 40.4539 | 6.5453 | 9.2727 | 8.5553 | 7.5453 | 10.818 | 12.818 | 9.2727 | 16.818 | 27.6359 | 40.4539 | 0
7.6805 | 9.8402 | 9.6805 | 8.6805 | 12.5207 | 14.5207 | 9.8402 | 18.5207 | 31.0415 | 45.5622 | 7.6805 | 9.8402 | 9.6905 | 8.6805 | 12.5207 | 14.5207 | 9.8402 | 18.5207 | 31.0415 | 45.5622 | 0
6.1081 | 9.0541 | 8.1081 | 7.1081 | 10.1622 | 12.1622 | 9.0541 | 16.1622 | 26.3244 | 38.4866 | 6.1081 | 9.0541 | 8.1181 | 7.1081 | 10.1622 | 12.1622 | 9.0541 | 16.1622 | 26.3244 | 38.4866 | 0
6.5904 | 9.2952 | 8.5904 | 7.5904 | 10.8856 | 12.8856 | 9.2952 | 16.8856 | 27.7712 | 40.6568 | 6.5904 | 9.2952 | 8.6004 | 7.5904 | 10.8856 | 12.8856 | 9.2952 | 16.8856 | 27.7712 | 40.6568 | 0
6.4252 | 9.2126 | 8.4252 | 7.4252 | 10.6378 | 12.6378 | 9.2126 | 16.6378 | 27.2757 | 39.9135 | 6.4252 | 9.2126 | 8.4352 | 7.4252 | 10.6378 | 12.6378 | 9.2126 | 16.6378 | 27.2757 | 39.9135 | 0
5.1021 | 8.551 | 7.1021 | 6.1021 | 8.6531 | 10.6531 | 8.551 | 14.6531 | 23.3063 | 33.9594 | 5.1021 | 8.551 | 7.1121 | 6.1021 | 8.6531 | 10.6531 | 8.551 | 14.6531 | 23.3063 | 33.9594 | 0
5.7627 | 8.8813 | 7.7627 | 6.7627 | 9.644 | 11.644 | 8.8813 | 15.644 | 25.288 | 36.9321 | 5.7627 | 8.8813 | 7.7727 | 6.7627 | 9.644 | 11.644 | 8.8813 | 15.644 | 25.288 | 36.9321 | 0
6.6646 | 9.3323 | 8.6646 | 7.6646 | 10.997 | 12.997 | 9.3323 | 16.997 | 27.9939 | 40.9909 | 6.6646 | 9.3323 | 8.6746 | 7.6646 | 10.997 | 12.997 | 9.3323 | 16.997 | 27.9939 | 40.9909 | 0
3.2081 | 7.604 | 5.2081 | 4.2081 | 5.8121 | 7.8121 | 7.604 | 11.8121 | 17.6242 | 25.4363 | 3.2081 | 7.604 | 5.2181 | 4.2081 | 5.8121 | 7.8121 | 7.604 | 11.8121 | 17.6242 | 25.4363 | 0
5.1092 | 8.5546 | 7.1092 | 6.1092 | 8.6638 | 10.6638 | 8.5546 | 14.6638 | 23.3276 | 33.9913 | 5.1092 | 8.5546 | 7.1192 | 6.1092 | 8.6638 | 10.6638 | 8.5546 | 14.6638 | 23.3276 | 33.9913 | 0
6.6987 | 9.3493 | 8.6987 | 7.6987 | 11.048 | 13.048 | 9.3493 | 17.048 | 28.0961 | 41.1441 | 6.6987 | 9.3493 | 8.7087 | 7.6987 | 11.048 | 13.048 | 9.3493 | 17.048 | 28.0961 | 41.1441 | 0
6.0901 | 9.045 | 8.0901 | 7.0901 | 10.1351 | 12.1351 | 9.045 | 16.1351 | 26.2702 | 38.4053 | 6.0901 | 9.045 | 8.1001 | 7.0901 | 10.1351 | 12.1351 | 9.045 | 16.1351 | 26.2702 | 38.4053 | 0
3.3738 | 7.6869 | 5.3738 | 4.3738 | 6.0607 | 8.0607 | 7.6869 | 12.0607 | 18.1215 | 26.1822 | 3.3738 | 7.6869 | 5.3838 | 4.3738 | 6.0607 | 8.0607 | 7.6869 | 12.0607 | 18.1215 | 26.1822 | 0
4.8105 | 8.4053 | 6.8105 | 5.8105 | 8.2158 | 10.2158 | 8.4053 | 14.2158 | 22.4316 | 32.6474 | 4.8105 | 8.4053 | 6.8205 | 5.8105 | 8.2158 | 10.2158 | 8.4053 | 14.2158 | 22.4316 | 32.6474 | 0
7.522 | 9.761 | 9.522 | 8.522 | 12.2829 | 14.2829 | 9.761 | 18.2829 | 30.5659 | 44.8488 | 7.522 | 9.761 | 9.532 | 8.522 | 12.2829 | 14.2829 | 9.761 | 18.2829 | 30.5659 | 44.8488 | 0
4.9713 | 8.4857 | 6.9713 | 5.9713 | 8.457 | 10.457 | 8.4857 | 14.457 | 22.9139 | 33.3709 | 4.9713 | 8.4857 | 6.9813 | 5.9713 | 8.457 | 10.457 | 8.4857 | 14.457 | 22.9139 | 33.3709 | 0
6.749 | 9.3745 | 8.749 | 7.749 | 11.1235 | 13.1235 | 9.3745 | 17.1235 | 28.247 | 41.3705 | 6.749 | 9.3745 | 8.759 | 7.749 | 11.1235 | 13.1235 | 9.3745 | 17.1235 | 28.247 | 41.3705 | 0
5.0742 | 8.5371 | 7.0742 | 6.0742 | 8.6114 | 10.6114 | 8.5371 | 14.6114 | 23.2227 | 33.8341 | 5.0742 | 8.5371 | 7.0842 | 6.0742 | 8.6114 | 10.6114 | 8.5371 | 14.6114 | 23.2227 | 33.8341 | 0
4.7646 | 8.3823 | 6.7646 | 5.7646 | 8.1468 | 10.1468 | 8.3823 | 14.1468 | 22.2937 | 32.4405 | 4.7646 | 8.3823 | 6.7746 | 5.7646 | 8.1468 | 10.1468 | 8.3823 | 14.1468 | 22.2937 | 32.4405 | 0
7.389 | 9.6945 | 9.389 | 8.389 | 12.0834 | 14.0834 | 9.6945 | 18.0834 | 30.1669 | 44.2503 | 7.389 | 9.6945 | 9.399 | 8.389 | 12.0834 | 14.0834 | 9.6945 | 18.0834 | 30.1669 | 44.2503 | 0
2.893 | 7.4465 | 4.893 | 3.893 | 5.3395 | 7.3395 | 7.4465 | 11.3395 | 16.679 | 24.0185 | 2.893 | 7.4465 | 4.903 | 3.893 | 5.3395 | 7.3395 | 7.4465 | 11.3395 | 16.679 | 24.0185 | 0
3.3349 | 7.6675 | 5.3349 | 4.3349 | 6.0024 | 8.0024 | 7.6675 | 12.0024 | 18.0048 | 26.0072 | 3.3349 | 7.6675 | 5.3449 | 4.3349 | 6.0024 | 8.0024 | 7.6675 | 12.0024 | 18.0048 | 26.0072 | 0
8.9925 | 10.4963 | 10.9925 | 9.9925 | 14.4888 | 16.4888 | 10.4963 | 20.4888 | 34.9775 | 51.4663 | 8.9925 | 10.4963 | 11.0025 | 9.9925 | 14.4888 | 16.4888 | 10.4963 | 20.4888 | 34.9775 | 51.4663 | 0
7.789 | 9.8945 | 9.789 | 8.789 | 12.6836 | 14.6836 | 9.8945 | 18.6836 | 31.3671 | 46.0507 | 7.789 | 9.8945 | 9.799 | 8.789 | 12.6836 | 14.6836 | 9.8945 | 18.6836 | 31.3671 | 46.0507 | 0
7.8333 | 9.9167 | 9.8333 | 8.8333 | 12.75 | 14.75 | 9.9167 | 18.75 | 31.4999 | 46.2499 | 7.8333 | 9.9167 | 9.8433 | 8.8333 | 12.75 | 14.75 | 9.9167 | 18.75 | 31.4999 | 46.2499 | 0
7.307 | 9.6535 | 9.307 | 8.307 | 11.9605 | 13.9605 | 9.6535 | 17.9605 | 29.9209 | 43.8814 | 7.307 | 9.6535 | 9.317 | 8.307 | 11.9605 | 13.9605 | 9.6535 | 17.9605 | 29.9209 | 43.8814 | 0
9.787 | 10.8935 | 11.787 | 10.787 | 15.6805 | 17.6805 | 10.8935 | 21.6805 | 37.361 | 55.0415 | 9.787 | 10.8935 | 11.797 | 10.787 | 15.6805 | 17.6805 | 10.8935 | 21.6805 | 37.361 | 55.0415 | 0
5.2045 | 8.6023 | 7.2045 | 6.2045 | 8.8068 | 10.8068 | 8.6023 | 14.8068 | 23.6135 | 34.4203 | 5.2045 | 8.6023 | 7.2145 | 6.2045 | 8.8068 | 10.8068 | 8.6023 | 14.8068 | 23.6135 | 34.4203 | 0
5.5481 | 8.7741 | 7.5481 | 6.5481 | 9.3222 | 11.3222 | 8.7741 | 15.3222 | 24.6444 | 35.9666 | 5.5481 | 8.7741 | 7.5581 | 6.5481 | 9.3222 | 11.3222 | 8.7741 | 15.3222 | 24.6444 | 35.9666 | 0
2.9819 | 7.491 | 4.9819 | 3.9819 | 5.4729 | 7.4729 | 7.491 | 11.4729 | 16.9458 | 24.4187 | 2.9819 | 7.491 | 4.9919 | 3.9819 | 5.4729 | 7.4729 | 7.491 | 11.4729 | 16.9458 | 24.4187 | 0
7.6554 | 9.8277 | 9.6554 | 8.6554 | 12.4831 | 14.4831 | 9.8277 | 18.4831 | 30.9661 | 45.4492 | 7.6554 | 9.8277 | 9.6654 | 8.6554 | 12.4831 | 14.4831 | 9.8277 | 18.4831 | 30.9661 | 45.4492 | 0
4.8098 | 8.4049 | 6.8098 | 5.8098 | 8.2147 | 10.2147 | 8.4049 | 14.2147 | 22.4294 | 32.6441 | 4.8098 | 8.4049 | 6.8198 | 5.8098 | 8.2147 | 10.2147 | 8.4049 | 14.2147 | 22.4294 | 32.6441 | 0
2.7341 | 7.3671 | 4.7341 | 3.7341 | 5.1012 | 7.1012 | 7.3671 | 11.1012 | 16.2023 | 23.3035 | 2.7341 | 7.3671 | 4.7441 | 3.7341 | 5.1012 | 7.1012 | 7.3671 | 11.1012 | 16.2023 | 23.3035 | 0
8.5249 | 10.2624 | 10.5249 | 9.5249 | 13.7873 | 15.7873 | 10.2624 | 19.7873 | 33.5746 | 49.3619 | 8.5249 | 10.2624 | 10.5349 | 9.5249 | 13.7873 | 15.7873 | 10.2624 | 19.7873 | 33.5746 | 49.3619 | 0
8.5457 | 10.2729 | 10.5457 | 9.5457 | 13.8186 | 15.8186 | 10.2729 | 19.8186 | 33.6371 | 49.4557 | 8.5457 | 10.2729 | 10.5557 | 9.5457 | 13.8186 | 15.8186 | 10.2729 | 19.8186 | 33.6371 | 49.4557 | 0
6.6239 | 9.3119 | 8.6239 | 7.6239 | 10.9358 | 12.9358 | 9.3119 | 16.9358 | 27.8716 | 40.8074 | 6.6239 | 9.3119 | 8.6339 | 7.6239 | 10.9358 | 12.9358 | 9.3119 | 16.9358 | 27.8716 | 40.8074 | 0
7.2382 | 9.6191 | 9.2382 | 8.2382 | 11.8573 | 13.8573 | 9.6191 | 17.8573 | 29.7147 | 43.572 | 7.2382 | 9.6191 | 9.2482 | 8.2382 | 11.8573 | 13.8573 | 9.6191 | 17.8573 | 29.7147 | 43.572 | 0
6.7582 | 9.3791 | 8.7582 | 7.7582 | 11.1373 | 13.1373 | 9.3791 | 17.1373 | 28.2746 | 41.4119 | 6.7582 | 9.3791 | 8.7682 | 7.7582 | 11.1373 | 13.1373 | 9.3791 | 17.1373 | 28.2746 | 41.4119 | 0
5.4894 | 8.7447 | 7.4894 | 6.4894 | 9.2341 | 11.2341 | 8.7447 | 15.2341 | 24.4682 | 35.7022 | 5.4894 | 8.7447 | 7.4994 | 6.4894 | 9.2341 | 11.2341 | 8.7447 | 15.2341 | 24.4682 | 35.7022 | 0
5.7659 | 8.883 | 7.7659 | 6.7659 | 9.6489 | 11.6489 | 8.883 | 15.6489 | 25.2977 | 36.9466 | 5.7659 | 8.883 | 7.7759 | 6.7659 | 9.6489 | 11.6489 | 8.883 | 15.6489 | 25.2977 | 36.9466 | 0
5.7573 | 8.8786 | 7.7573 | 6.7573 | 9.6359 | 11.6359 | 8.8786 | 15.6359 | 25.2719 | 36.9078 | 5.7573 | 8.8786 | 7.7673 | 6.7573 | 9.6359 | 11.6359 | 8.8786 | 15.6359 | 25.2719 | 36.9078 | 0
4.4028 | 8.2014 | 6.4028 | 5.4028 | 7.6042 | 9.6042 | 8.2014 | 13.6042 | 21.2083 | 30.8125 | 4.4028 | 8.2014 | 6.4128 | 5.4028 | 7.6042 | 9.6042 | 8.2014 | 13.6042 | 21.2083 | 30.8125 | 0
5.7536 | 8.8768 | 7.7536 | 6.7536 | 9.6304 | 11.6304 | 8.8768 | 15.6304 | 25.2608 | 36.8911 | 5.7536 | 8.8768 | 7.7636 | 6.7536 | 9.6304 | 11.6304 | 8.8768 | 15.6304 | 25.2608 | 36.8911 | 0
5.0303 | 8.5151 | 7.0303 | 6.0303 | 8.5454 | 10.5454 | 8.5151 | 14.5454 | 23.0908 | 33.6361 | 5.0303 | 8.5151 | 7.0403 | 6.0303 | 8.5454 | 10.5454 | 8.5151 | 14.5454 | 23.0908 | 33.6361 | 0
3.0131 | 7.5066 | 5.0131 | 4.0131 | 5.5197 | 7.5197 | 7.5066 | 11.5197 | 17.0393 | 24.559 | 3.0131 | 7.5066 | 5.0231 | 4.0131 | 5.5197 | 7.5197 | 7.5066 | 11.5197 | 17.0393 | 24.559 | 0
2.4946 | 7.2473 | 4.4946 | 3.4946 | 4.7419 | 6.7419 | 7.2473 | 10.7419 | 15.4838 | 22.2257 | 2.4946 | 7.2473 | 4.5046 | 3.4946 | 4.7419 | 6.7419 | 7.2473 | 10.7419 | 15.4838 | 22.2257 | 0
3.8321 | 7.9161 | 5.8321 | 4.8321 | 6.7482 | 8.7482 | 7.9161 | 12.7482 | 19.4963 | 28.2445 | 3.8321 | 7.9161 | 5.8421 | 4.8321 | 6.7482 | 8.7482 | 7.9161 | 12.7482 | 19.4963 | 28.2445 | 0
3.881 | 7.9405 | 5.881 | 4.881 | 6.8215 | 8.8215 | 7.9405 | 12.8215 | 19.6431 | 28.4646 | 3.881 | 7.9405 | 5.891 | 4.881 | 6.8215 | 8.8215 | 7.9405 | 12.8215 | 19.6431 | 28.4646 | 0
6.8478 | 9.4239 | 8.8478 | 7.8478 | 11.2716 | 13.2716 | 9.4239 | 17.2716 | 28.5433 | 41.8149 | 6.8478 | 9.4239 | 8.8578 | 7.8478 | 11.2716 | 13.2716 | 9.4239 | 17.2716 | 28.5433 | 41.8149 | 0
6.8117 | 9.4059 | 8.8117 | 7.8117 | 11.2176 | 13.2176 | 9.4059 | 17.2176 | 28.4352 | 41.6529 | 6.8117 | 9.4059 | 8.8217 | 7.8117 | 11.2176 | 13.2176 | 9.4059 | 17.2176 | 28.4352 | 41.6529 | 0
2.5649 | 7.2825 | 4.5649 | 3.5649 | 4.8474 | 6.8474 | 7.2825 | 10.8474 | 15.6947 | 22.5421 | 2.5649 | 7.2825 | 4.5749 | 3.5649 | 4.8474 | 6.8474 | 7.2825 | 10.8474 | 15.6947 | 22.5421 | 0
4.502 | 8.251 | 6.502 | 5.502 | 7.7531 | 9.7531 | 8.251 | 13.7531 | 21.5061 | 31.2592 | 4.502 | 8.251 | 6.512 | 5.502 | 7.7531 | 9.7531 | 8.251 | 13.7531 | 21.5061 | 31.2592 | 0
8.0192 | 10.0096 | 10.0192 | 9.0192 | 13.0288 | 15.0288 | 10.0096 | 19.0288 | 32.0575 | 47.0863 | 8.0192 | 10.0096 | 10.0292 | 9.0192 | 13.0288 | 15.0288 | 10.0096 | 19.0288 | 32.0575 | 47.0863 | 0
5.5992 | 8.7996 | 7.5992 | 6.5992 | 9.3987 | 11.3987 | 8.7996 | 15.3987 | 24.7975 | 36.1962 | 5.5992 | 8.7996 | 7.6092 | 6.5992 | 9.3987 | 11.3987 | 8.7996 | 15.3987 | 24.7975 | 36.1962 | 0
3.538 | 7.769 | 5.538 | 4.538 | 6.3071 | 8.3071 | 7.769 | 12.3071 | 18.6141 | 26.9212 | 3.538 | 7.769 | 5.548 | 4.538 | 6.3071 | 8.3071 | 7.769 | 12.3071 | 18.6141 | 26.9212 | 0
4.1922 | 8.0961 | 6.1922 | 5.1922 | 7.2882 | 9.2882 | 8.0961 | 13.2882 | 20.5765 | 29.8647 | 4.1922 | 8.0961 | 6.2022 | 5.1922 | 7.2882 | 9.2882 | 8.0961 | 13.2882 | 20.5765 | 29.8647 | 0
8.0617 | 10.0308 | 10.0617 | 9.0617 | 13.0925 | 15.0925 | 10.0308 | 19.0925 | 32.185 | 47.2775 | 8.0617 | 10.0308 | 10.0717 | 9.0617 | 13.0925 | 15.0925 | 10.0308 | 19.0925 | 32.185 | 47.2775 | 0
7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 7.4889 | 9.7444 | 9.4989 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 0
11.8438 | 11.9219 | 13.8438 | 12.8438 | 18.7656 | 20.7656 | 11.9219 | 24.7656 | 43.5313 | 64.2969 | 11.8438 | 11.9219 | 13.8538 | 12.8438 | 18.7656 | 20.7656 | 11.9219 | 24.7656 | 43.5313 | 64.2969 | 0
6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 6.3314 | 9.1657 | 8.3414 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 0
8.8082 | 10.4041 | 10.8082 | 9.8082 | 14.2124 | 16.2124 | 10.4041 | 20.2124 | 34.4247 | 50.6371 | 8.8082 | 10.4041 | 10.8182 | 9.8082 | 14.2124 | 16.2124 | 10.4041 | 20.2124 | 34.4247 | 50.6371 | 0
7.6294 | 9.8147 | 9.6294 | 8.6294 | 12.4441 | 14.4441 | 9.8147 | 18.4441 | 30.8883 | 45.3324 | 7.6294 | 9.8147 | 9.6394 | 8.6294 | 12.4441 | 14.4441 | 9.8147 | 18.4441 | 30.8883 | 45.3324 | 0
6.2816 | 9.1408 | 8.2816 | 7.2816 | 10.4224 | 12.4224 | 9.1408 | 16.4224 | 26.8448 | 39.2672 | 6.2816 | 9.1408 | 8.2916 | 7.2816 | 10.4224 | 12.4224 | 9.1408 | 16.4224 | 26.8448 | 39.2672 | 0
2.9948 | 7.4974 | 4.9948 | 3.9948 | 5.4922 | 7.4922 | 7.4974 | 11.4922 | 16.9843 | 24.4765 | 2.9948 | 7.4974 | 5.0048 | 3.9948 | 5.4922 | 7.4922 | 7.4974 | 11.4922 | 16.9843 | 24.4765 | 0
7.6577 | 9.8289 | 9.6577 | 8.6577 | 12.4866 | 14.4866 | 9.8289 | 18.4866 | 30.9732 | 45.4598 | 7.6577 | 9.8289 | 9.6677 | 8.6577 | 12.4866 | 14.4866 | 9.8289 | 18.4866 | 30.9732 | 45.4598 | 0
5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 5.0973 | 8.5487 | 7.1073 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 0
6.3502 | 9.1751 | 8.3502 | 7.3502 | 10.5253 | 12.5253 | 9.1751 | 16.5253 | 27.0507 | 39.576 | 6.3502 | 9.1751 | 8.3602 | 7.3502 | 10.5253 | 12.5253 | 9.1751 | 16.5253 | 27.0507 | 39.576 | 0
8.2841 | 10.1421 | 10.2841 | 9.2841 | 13.4262 | 15.4262 | 10.1421 | 19.4262 | 32.8524 | 48.2786 | 8.2841 | 10.1421 | 10.2941 | 9.2841 | 13.4262 | 15.4262 | 10.1421 | 19.4262 | 32.8524 | 48.2786 | 0
7.4494 | 9.7247 | 9.4494 | 8.4494 | 12.1741 | 14.1741 | 9.7247 | 18.1741 | 30.3481 | 44.5222 | 7.4494 | 9.7247 | 9.4594 | 8.4494 | 12.1741 | 14.1741 | 9.7247 | 18.1741 | 30.3481 | 44.5222 | 0
5.769 | 8.8845 | 7.769 | 6.769 | 9.6535 | 11.6535 | 8.8845 | 15.6535 | 25.307 | 36.9605 | 5.769 | 8.8845 | 7.779 | 6.769 | 9.6535 | 11.6535 | 8.8845 | 15.6535 | 25.307 | 36.9605 | 0
5.8084 | 8.9042 | 7.8084 | 6.8084 | 9.7126 | 11.7126 | 8.9042 | 15.7126 | 25.4252 | 37.1377 | 5.8084 | 8.9042 | 7.8184 | 6.8084 | 9.7126 | 11.7126 | 8.9042 | 15.7126 | 25.4252 | 37.1377 | 0
4.3983 | 8.1992 | 6.3983 | 5.3983 | 7.5975 | 9.5975 | 8.1992 | 13.5975 | 21.195 | 30.7925 | 4.3983 | 8.1992 | 6.4083 | 5.3983 | 7.5975 | 9.5975 | 8.1992 | 13.5975 | 21.195 | 30.7925 | 0
4.0729 | 8.0365 | 6.0729 | 5.0729 | 7.1094 | 9.1094 | 8.0365 | 13.1094 | 20.2188 | 29.3281 | 4.0729 | 8.0365 | 6.0829 | 5.0729 | 7.1094 | 9.1094 | 8.0365 | 13.1094 | 20.2188 | 29.3281 | 0
6.5512 | 9.2756 | 8.5512 | 7.5512 | 10.8268 | 12.8268 | 9.2756 | 16.8268 | 27.6536 | 40.4803 | 6.5512 | 9.2756 | 8.5612 | 7.5512 | 10.8268 | 12.8268 | 9.2756 | 16.8268 | 27.6536 | 40.4803 | 0
3.2266 | 7.6133 | 5.2266 | 4.2266 | 5.8399 | 7.8399 | 7.6133 | 11.8399 | 17.6798 | 25.5197 | 3.2266 | 7.6133 | 5.2366 | 4.2266 | 5.8399 | 7.8399 | 7.6133 | 11.8399 | 17.6798 | 25.5197 | 0
6.4914 | 9.2457 | 8.4914 | 7.4914 | 10.737 | 12.737 | 9.2457 | 16.737 | 27.4741 | 40.2111 | 6.4914 | 9.2457 | 8.5014 | 7.4914 | 10.737 | 12.737 | 9.2457 | 16.737 | 27.4741 | 40.2111 | 0
7.4177 | 9.7089 | 9.4177 | 8.4177 | 12.1266 | 14.1266 | 9.7089 | 18.1266 | 30.2532 | 44.3798 | 7.4177 | 9.7089 | 9.4277 | 8.4177 | 12.1266 | 14.1266 | 9.7089 | 18.1266 | 30.2532 | 44.3798 | 0
3.4213 | 7.7106 | 5.4213 | 4.4213 | 6.1319 | 8.1319 | 7.7106 | 12.1319 | 18.2638 | 26.3957 | 3.4213 | 7.7106 | 5.4313 | 4.4213 | 6.1319 | 8.1319 | 7.7106 | 12.1319 | 18.2638 | 26.3957 | 0
4.6599 | 8.3299 | 6.6599 | 5.6599 | 7.9898 | 9.9898 | 8.3299 | 13.9898 | 21.9797 | 31.9695 | 4.6599 | 8.3299 | 6.6699 | 5.6599 | 7.9898 | 9.9898 | 8.3299 | 13.9898 | 21.9797 | 31.9695 | 0
7.9283 | 9.9641 | 9.9283 | 8.9283 | 12.8924 | 14.8924 | 9.9641 | 18.8924 | 31.7849 | 46.6773 | 7.9283 | 9.9641 | 9.9383 | 8.9283 | 12.8924 | 14.8924 | 9.9641 | 18.8924 | 31.7849 | 46.6773 | 0
8.1195 | 10.0598 | 10.1195 | 9.1195 | 13.1793 | 15.1793 | 10.0598 | 19.1793 | 32.3586 | 47.5378 | 8.1195 | 10.0598 | 10.1295 | 9.1195 | 13.1793 | 15.1793 | 10.0598 | 19.1793 | 32.3586 | 47.5378 | 0
5.1511 | 8.5755 | 7.1511 | 6.1511 | 8.7266 | 10.7266 | 8.5755 | 14.7266 | 23.4532 | 34.1798 | 5.1511 | 8.5755 | 7.1611 | 6.1511 | 8.7266 | 10.7266 | 8.5755 | 14.7266 | 23.4532 | 34.1798 | 0
4.3661 | 8.183 | 6.3661 | 5.3661 | 7.5491 | 9.5491 | 8.183 | 13.5491 | 21.0983 | 30.6474 | 4.3661 | 8.183 | 6.3761 | 5.3661 | 7.5491 | 9.5491 | 8.183 | 13.5491 | 21.0983 | 30.6474 | 0
4.8403 | 8.4202 | 6.8403 | 5.8403 | 8.2605 | 10.2605 | 8.4202 | 14.2605 | 22.521 | 32.7815 | 4.8403 | 8.4202 | 6.8503 | 5.8403 | 8.2605 | 10.2605 | 8.4202 | 14.2605 | 22.521 | 32.7815 | 0
6.6155 | 9.3078 | 8.6155 | 7.6155 | 10.9233 | 12.9233 | 9.3078 | 16.9233 | 27.8466 | 40.7699 | 6.6155 | 9.3078 | 8.6255 | 7.6155 | 10.9233 | 12.9233 | 9.3078 | 16.9233 | 27.8466 | 40.7699 | 0
6.1813 | 9.0907 | 8.1813 | 7.1813 | 10.272 | 12.272 | 9.0907 | 16.272 | 26.544 | 38.8159 | 6.1813 | 9.0907 | 8.1913 | 7.1813 | 10.272 | 12.272 | 9.0907 | 16.272 | 26.544 | 38.8159 | 0
6.6324 | 9.3162 | 8.6324 | 7.6324 | 10.9486 | 12.9486 | 9.3162 | 16.9486 | 27.8972 | 40.8458 | 6.6324 | 9.3162 | 8.6424 | 7.6324 | 10.9486 | 12.9486 | 9.3162 | 16.9486 | 27.8972 | 40.8458 | 0
5.7216 | 8.8608 | 7.7216 | 6.7216 | 9.5825 | 11.5825 | 8.8608 | 15.5825 | 25.1649 | 36.7474 | 5.7216 | 8.8608 | 7.7316 | 6.7216 | 9.5825 | 11.5825 | 8.8608 | 15.5825 | 25.1649 | 36.7474 | 0
5.8658 | 8.9329 | 7.8658 | 6.8658 | 9.7987 | 11.7987 | 8.9329 | 15.7987 | 25.5974 | 37.3961 | 5.8658 | 8.9329 | 7.8758 | 6.8658 | 9.7987 | 11.7987 | 8.9329 | 15.7987 | 25.5974 | 37.3961 | 0
4.2094 | 8.1047 | 6.2094 | 5.2094 | 7.314 | 9.314 | 8.1047 | 13.314 | 20.6281 | 29.9421 | 4.2094 | 8.1047 | 6.2194 | 5.2094 | 7.314 | 9.314 | 8.1047 | 13.314 | 20.6281 | 29.9421 | 0
5.2214 | 8.6107 | 7.2214 | 6.2214 | 8.8321 | 10.8321 | 8.6107 | 14.8321 | 23.6641 | 34.4962 | 5.2214 | 8.6107 | 7.2314 | 6.2214 | 8.8321 | 10.8321 | 8.6107 | 14.8321 | 23.6641 | 34.4962 | 0
5.3992 | 8.6996 | 7.3992 | 6.3992 | 9.0988 | 11.0988 | 8.6996 | 15.0988 | 24.1976 | 35.2965 | 5.3992 | 8.6996 | 7.4092 | 6.3992 | 9.0988 | 11.0988 | 8.6996 | 15.0988 | 24.1976 | 35.2965 | 0
9.2618 | 10.6309 | 11.2618 | 10.2618 | 14.8927 | 16.8927 | 10.6309 | 20.8927 | 35.7855 | 52.6782 | 9.2618 | 10.6309 | 11.2718 | 10.2618 | 14.8927 | 16.8927 | 10.6309 | 20.8927 | 35.7855 | 52.6782 | 0
2.5164 | 7.2582 | 4.5164 | 3.5164 | 4.7746 | 6.7746 | 7.2582 | 10.7746 | 15.5493 | 22.3239 | 2.5164 | 7.2582 | 4.5264 | 3.5164 | 4.7746 | 6.7746 | 7.2582 | 10.7746 | 15.5493 | 22.3239 | 0
6.053 | 9.0265 | 8.053 | 7.053 | 10.0795 | 12.0795 | 9.0265 | 16.0795 | 26.1591 | 38.2386 | 6.053 | 9.0265 | 8.063 | 7.053 | 10.0795 | 12.0795 | 9.0265 | 16.0795 | 26.1591 | 38.2386 | 0
11.0086 | 11.5043 | 13.0086 | 12.0086 | 17.5129 | 19.5129 | 11.5043 | 23.5129 | 41.0259 | 60.5388 | 11.0086 | 11.5043 | 13.0186 | 12.0086 | 17.5129 | 19.5129 | 11.5043 | 23.5129 | 41.0259 | 60.5388 | 0
9.7368 | 10.8684 | 11.7368 | 10.7368 | 15.6052 | 17.6052 | 10.8684 | 21.6052 | 37.2103 | 54.8155 | 9.7368 | 10.8684 | 11.7468 | 10.7368 | 15.6052 | 17.6052 | 10.8684 | 21.6052 | 37.2103 | 54.8155 | 0
9.4739 | 10.7369 | 11.4739 | 10.4739 | 15.2108 | 17.2108 | 10.7369 | 21.2108 | 36.4216 | 53.6323 | 9.4739 | 10.7369 | 11.4839 | 10.4739 | 15.2108 | 17.2108 | 10.7369 | 21.2108 | 36.4216 | 53.6323 | 0
4.0971 | 8.0486 | 6.0971 | 5.0971 | 7.1457 | 9.1457 | 8.0486 | 13.1457 | 20.2913 | 29.437 | 4.0971 | 8.0486 | 6.1071 | 5.0971 | 7.1457 | 9.1457 | 8.0486 | 13.1457 | 20.2913 | 29.437 | 0
7.1106 | 9.5553 | 9.1106 | 8.1106 | 11.6659 | 13.6659 | 9.5553 | 17.6659 | 29.3318 | 42.9977 | 7.1106 | 9.5553 | 9.1206 | 8.1106 | 11.6659 | 13.6659 | 9.5553 | 17.6659 | 29.3318 | 42.9977 | 0
8.668 | 10.334 | 10.668 | 9.668 | 14.0021 | 16.0021 | 10.334 | 20.0021 | 34.0041 | 50.0062 | 8.668 | 10.334 | 10.678 | 9.668 | 14.0021 | 16.0021 | 10.334 | 20.0021 | 34.0041 | 50.0062 | 0
5.0877 | 8.5438 | 7.0877 | 6.0877 | 8.6315 | 10.6315 | 8.5438 | 14.6315 | 23.263 | 33.8945 | 5.0877 | 8.5438 | 7.0977 | 6.0877 | 8.6315 | 10.6315 | 8.5438 | 14.6315 | 23.263 | 33.8945 | 0
3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 3.9727 | 7.9863 | 5.9827 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 0
6.5588 | 9.2794 | 8.5588 | 7.5588 | 10.8382 | 12.8382 | 9.2794 | 16.8382 | 27.6765 | 40.5147 | 6.5588 | 9.2794 | 8.5688 | 7.5588 | 10.8382 | 12.8382 | 9.2794 | 16.8382 | 27.6765 | 40.5147 | 0
5.3003 | 8.6502 | 7.3003 | 6.3003 | 8.9505 | 10.9505 | 8.6502 | 14.9505 | 23.901 | 34.8515 | 5.3003 | 8.6502 | 7.3103 | 6.3003 | 8.9505 | 10.9505 | 8.6502 | 14.9505 | 23.901 | 34.8515 | 0
5.3086 | 8.6543 | 7.3086 | 6.3086 | 8.9629 | 10.9629 | 8.6543 | 14.9629 | 23.9259 | 34.8888 | 5.3086 | 8.6543 | 7.3186 | 6.3086 | 8.9629 | 10.9629 | 8.6543 | 14.9629 | 23.9259 | 34.8888 | 0
4.5764 | 8.2882 | 6.5764 | 5.5764 | 7.8645 | 9.8645 | 8.2882 | 13.8645 | 21.7291 | 31.5936 | 4.5764 | 8.2882 | 6.5864 | 5.5764 | 7.8645 | 9.8645 | 8.2882 | 13.8645 | 21.7291 | 31.5936 | 0
5.9923 | 8.9961 | 7.9923 | 6.9923 | 9.9884 | 11.9884 | 8.9961 | 15.9884 | 25.9768 | 37.9652 | 5.9923 | 8.9961 | 8.0023 | 6.9923 | 9.9884 | 11.9884 | 8.9961 | 15.9884 | 25.9768 | 37.9652 | 0
2.2553 | 7.1277 | 4.2553 | 3.2553 | 4.383 | 6.383 | 7.1277 | 10.383 | 14.766 | 21.1489 | 2.2553 | 7.1277 | 4.2653 | 3.2553 | 4.383 | 6.383 | 7.1277 | 10.383 | 14.766 | 21.1489 | 0
3.77 | 7.885 | 5.77 | 4.77 | 6.6549 | 8.6549 | 7.885 | 12.6549 | 19.3099 | 27.9648 | 3.77 | 7.885 | 5.78 | 4.77 | 6.6549 | 8.6549 | 7.885 | 12.6549 | 19.3099 | 27.9648 | 0
5.0845 | 8.5422 | 7.0845 | 6.0845 | 8.6267 | 10.6267 | 8.5422 | 14.6267 | 23.2534 | 33.88 | 5.0845 | 8.5422 | 7.0945 | 6.0845 | 8.6267 | 10.6267 | 8.5422 | 14.6267 | 23.2534 | 33.88 | 0
10.4131 | 11.2066 | 12.4131 | 11.4131 | 16.6197 | 18.6197 | 11.2066 | 22.6197 | 39.2394 | 57.8591 | 10.4131 | 11.2066 | 12.4231 | 11.4131 | 16.6197 | 18.6197 | 11.2066 | 22.6197 | 39.2394 | 57.8591 | 0
6.5663 | 9.2831 | 8.5663 | 7.5663 | 10.8494 | 12.8494 | 9.2831 | 16.8494 | 27.6989 | 40.5483 | 6.5663 | 9.2831 | 8.5763 | 7.5663 | 10.8494 | 12.8494 | 9.2831 | 16.8494 | 27.6989 | 40.5483 | 0
5.6487 | 8.8243 | 7.6487 | 6.6487 | 9.473 | 11.473 | 8.8243 | 15.473 | 24.946 | 36.4191 | 5.6487 | 8.8243 | 7.6587 | 6.6487 | 9.473 | 11.473 | 8.8243 | 15.473 | 24.946 | 36.4191 | 0
7.5932 | 9.7966 | 9.5932 | 8.5932 | 12.3899 | 14.3899 | 9.7966 | 18.3899 | 30.7797 | 45.1696 | 7.5932 | 9.7966 | 9.6032 | 8.5932 | 12.3899 | 14.3899 | 9.7966 | 18.3899 | 30.7797 | 45.1696 | 0
3.3026 | 7.6513 | 5.3026 | 4.3026 | 5.9539 | 7.9539 | 7.6513 | 11.9539 | 17.9078 | 25.8617 | 3.3026 | 7.6513 | 5.3126 | 4.3026 | 5.9539 | 7.9539 | 7.6513 | 11.9539 | 17.9078 | 25.8617 | 0
3.76 | 7.88 | 5.76 | 4.76 | 6.6399 | 8.6399 | 7.88 | 12.6399 | 19.2799 | 27.9198 | 3.76 | 7.88 | 5.77 | 4.76 | 6.6399 | 8.6399 | 7.88 | 12.6399 | 19.2799 | 27.9198 | 0
5.8466 | 8.9233 | 7.8466 | 6.8466 | 9.7699 | 11.7699 | 8.9233 | 15.7699 | 25.5399 | 37.3098 | 5.8466 | 8.9233 | 7.8566 | 6.8466 | 9.7699 | 11.7699 | 8.9233 | 15.7699 | 25.5399 | 37.3098 | 0
6.6787 | 9.3394 | 8.6787 | 7.6787 | 11.0181 | 13.0181 | 9.3394 | 17.0181 | 28.0362 | 41.0543 | 6.6787 | 9.3394 | 8.6887 | 7.6787 | 11.0181 | 13.0181 | 9.3394 | 17.0181 | 28.0362 | 41.0543 | 0
5.4037 | 8.7018 | 7.4037 | 6.4037 | 9.1055 | 11.1055 | 8.7018 | 15.1055 | 24.2111 | 35.3166 | 5.4037 | 8.7018 | 7.4137 | 6.4037 | 9.1055 | 11.1055 | 8.7018 | 15.1055 | 24.2111 | 35.3166 | 0
6.474 | 9.237 | 8.474 | 7.474 | 10.711 | 12.711 | 9.237 | 16.711 | 27.4221 | 40.1331 | 6.474 | 9.237 | 8.484 | 7.474 | 10.711 | 12.711 | 9.237 | 16.711 | 27.4221 | 40.1331 | 0
6.1767 | 9.0884 | 8.1767 | 7.1767 | 10.2651 | 12.2651 | 9.0884 | 16.2651 | 26.5301 | 38.7952 | 6.1767 | 9.0884 | 8.1867 | 7.1767 | 10.2651 | 12.2651 | 9.0884 | 16.2651 | 26.5301 | 38.7952 | 0
6.604 | 9.302 | 8.604 | 7.604 | 10.906 | 12.906 | 9.302 | 16.906 | 27.812 | 40.7179 | 6.604 | 9.302 | 8.614 | 7.604 | 10.906 | 12.906 | 9.302 | 16.906 | 27.812 | 40.7179 | 0
4.67 | 8.335 | 6.67 | 5.67 | 8.005 | 10.005 | 8.335 | 14.005 | 22.0101 | 32.0151 | 4.67 | 8.335 | 6.68 | 5.67 | 8.005 | 10.005 | 8.335 | 14.005 | 22.0101 | 32.0151 | 0
5.3308 | 8.6654 | 7.3308 | 6.3308 | 8.9962 | 10.9962 | 8.6654 | 14.9962 | 23.9925 | 34.9887 | 5.3308 | 8.6654 | 7.3408 | 6.3308 | 8.9962 | 10.9962 | 8.6654 | 14.9962 | 23.9925 | 34.9887 | 0
5.7182 | 8.8591 | 7.7182 | 6.7182 | 9.5774 | 11.5774 | 8.8591 | 15.5774 | 25.1547 | 36.7321 | 5.7182 | 8.8591 | 7.7282 | 6.7182 | 9.5774 | 11.5774 | 8.8591 | 15.5774 | 25.1547 | 36.7321 | 0
1.3905 | 6.6952 | 3.3905 | 2.3905 | 3.0857 | 5.0857 | 6.6952 | 9.0857 | 12.1714 | 17.2571 | 1.3905 | 6.6952 | 3.4005 | 2.3905 | 3.0857 | 5.0857 | 6.6952 | 9.0857 | 12.1714 | 17.2571 | 0
4.6854 | 8.3427 | 6.6854 | 5.6854 | 8.0282 | 10.0282 | 8.3427 | 14.0282 | 22.0563 | 32.0845 | 4.6854 | 8.3427 | 6.6954 | 5.6854 | 8.0282 | 10.0282 | 8.3427 | 14.0282 | 22.0563 | 32.0845 | 0
4.5016 | 8.2508 | 6.5016 | 5.5016 | 7.7525 | 9.7525 | 8.2508 | 13.7525 | 21.5049 | 31.2574 | 4.5016 | 8.2508 | 6.5116 | 5.5016 | 7.7525 | 9.7525 | 8.2508 | 13.7525 | 21.5049 | 31.2574 | 0
3.0906 | 7.5453 | 5.0906 | 4.0906 | 5.6359 | 7.6359 | 7.5453 | 11.6359 | 17.2719 | 24.9078 | 3.0906 | 7.5453 | 5.1006 | 4.0906 | 5.6359 | 7.6359 | 7.5453 | 11.6359 | 17.2719 | 24.9078 | 0
3.6427 | 7.8213 | 5.6427 | 4.6427 | 6.464 | 8.464 | 7.8213 | 12.464 | 18.928 | 27.392 | 3.6427 | 7.8213 | 5.6527 | 4.6427 | 6.464 | 8.464 | 7.8213 | 12.464 | 18.928 | 27.392 | 0
3.7734 | 7.8867 | 5.7734 | 4.7734 | 6.66 | 8.66 | 7.8867 | 12.66 | 19.3201 | 27.9801 | 3.7734 | 7.8867 | 5.7834 | 4.7734 | 6.66 | 8.66 | 7.8867 | 12.66 | 19.3201 | 27.9801 | 0
5.5801 | 8.79 | 7.5801 | 6.5801 | 9.3701 | 11.3701 | 8.79 | 15.3701 | 24.7403 | 36.1104 | 5.5801 | 8.79 | 7.5901 | 6.5801 | 9.3701 | 11.3701 | 8.79 | 15.3701 | 24.7403 | 36.1104 | 0
7.3028 | 9.6514 | 9.3028 | 8.3028 | 11.9542 | 13.9542 | 9.6514 | 17.9542 | 29.9084 | 43.8626 | 7.3028 | 9.6514 | 9.3128 | 8.3028 | 11.9542 | 13.9542 | 9.6514 | 17.9542 | 29.9084 | 43.8626 | 0
4.8107 | 8.4054 | 6.8107 | 5.8107 | 8.2161 | 10.2161 | 8.4054 | 14.2161 | 22.4321 | 32.6482 | 4.8107 | 8.4054 | 6.8207 | 5.8107 | 8.2161 | 10.2161 | 8.4054 | 14.2161 | 22.4321 | 32.6482 | 0
6.0516 | 9.0258 | 8.0516 | 7.0516 | 10.0775 | 12.0775 | 9.0258 | 16.0775 | 26.1549 | 38.2324 | 6.0516 | 9.0258 | 8.0616 | 7.0516 | 10.0775 | 12.0775 | 9.0258 | 16.0775 | 26.1549 | 38.2324 | 0
7.0705 | 9.5352 | 9.0705 | 8.0705 | 11.6057 | 13.6057 | 9.5352 | 17.6057 | 29.2114 | 42.8171 | 7.0705 | 9.5352 | 9.0805 | 8.0705 | 11.6057 | 13.6057 | 9.5352 | 17.6057 | 29.2114 | 42.8171 | 0
7.2568 | 9.6284 | 9.2568 | 8.2568 | 11.8852 | 13.8852 | 9.6284 | 17.8852 | 29.7704 | 43.6556 | 7.2568 | 9.6284 | 9.2668 | 8.2568 | 11.8852 | 13.8852 | 9.6284 | 17.8852 | 29.7704 | 43.6556 | 0
5.5195 | 8.7598 | 7.5195 | 6.5195 | 9.2793 | 11.2793 | 8.7598 | 15.2793 | 24.5586 | 35.8378 | 5.5195 | 8.7598 | 7.5295 | 6.5195 | 9.2793 | 11.2793 | 8.7598 | 15.2793 | 24.5586 | 35.8378 | 0
7.7236 | 9.8618 | 9.7236 | 8.7236 | 12.5854 | 14.5854 | 9.8618 | 18.5854 | 31.1707 | 45.7561 | 7.7236 | 9.8618 | 9.7336 | 8.7236 | 12.5854 | 14.5854 | 9.8618 | 18.5854 | 31.1707 | 45.7561 | 0
7.4454 | 9.7227 | 9.4454 | 8.4454 | 12.1681 | 14.1681 | 9.7227 | 18.1681 | 30.3362 | 44.5043 | 7.4454 | 9.7227 | 9.4554 | 8.4454 | 12.1681 | 14.1681 | 9.7227 | 18.1681 | 30.3362 | 44.5043 | 0
7.2098 | 9.6049 | 9.2098 | 8.2098 | 11.8147 | 13.8147 | 9.6049 | 17.8147 | 29.6294 | 43.4441 | 7.2098 | 9.6049 | 9.2198 | 8.2098 | 11.8147 | 13.8147 | 9.6049 | 17.8147 | 29.6294 | 43.4441 | 0
8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 8.0477 | 10.0238 | 10.0577 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 0
5.3983 | 8.6991 | 7.3983 | 6.3983 | 9.0974 | 11.0974 | 8.6991 | 15.0974 | 24.1948 | 35.2922 | 5.3983 | 8.6991 | 7.4083 | 6.3983 | 9.0974 | 11.0974 | 8.6991 | 15.0974 | 24.1948 | 35.2922 | 0
8.1214 | 10.0607 | 10.1214 | 9.1214 | 13.1821 | 15.1821 | 10.0607 | 19.1821 | 32.3642 | 47.5463 | 8.1214 | 10.0607 | 10.1314 | 9.1214 | 13.1821 | 15.1821 | 10.0607 | 19.1821 | 32.3642 | 47.5463 | 0
5.6079 | 8.8039 | 7.6079 | 6.6079 | 9.4118 | 11.4118 | 8.8039 | 15.4118 | 24.8237 | 36.2355 | 5.6079 | 8.8039 | 7.6179 | 6.6079 | 9.4118 | 11.4118 | 8.8039 | 15.4118 | 24.8237 | 36.2355 | 0
6.4616 | 9.2308 | 8.4616 | 7.4616 | 10.6924 | 12.6924 | 9.2308 | 16.6924 | 27.3848 | 40.0772 | 6.4616 | 9.2308 | 8.4716 | 7.4616 | 10.6924 | 12.6924 | 9.2308 | 16.6924 | 27.3848 | 40.0772 | 0
5.8819 | 8.9409 | 7.8819 | 6.8819 | 9.8228 | 11.8228 | 8.9409 | 15.8228 | 25.6457 | 37.4685 | 5.8819 | 8.9409 | 7.8919 | 6.8819 | 9.8228 | 11.8228 | 8.9409 | 15.8228 | 25.6457 | 37.4685 | 0
3.8915 | 7.9457 | 5.8915 | 4.8915 | 6.8372 | 8.8372 | 7.9457 | 12.8372 | 19.6744 | 28.5115 | 3.8915 | 7.9457 | 5.9015 | 4.8915 | 6.8372 | 8.8372 | 7.9457 | 12.8372 | 19.6744 | 28.5115 | 0
3.9971 | 7.9985 | 5.9971 | 4.9971 | 6.9956 | 8.9956 | 7.9985 | 12.9956 | 19.9912 | 28.9868 | 3.9971 | 7.9985 | 6.0071 | 4.9971 | 6.9956 | 8.9956 | 7.9985 | 12.9956 | 19.9912 | 28.9868 | 0
6.3642 | 9.1821 | 8.3642 | 7.3642 | 10.5463 | 12.5463 | 9.1821 | 16.5463 | 27.0927 | 39.639 | 6.3642 | 9.1821 | 8.3742 | 7.3642 | 10.5463 | 12.5463 | 9.1821 | 16.5463 | 27.0927 | 39.639 | 0
9.0628 | 10.5314 | 11.0628 | 10.0628 | 14.5941 | 16.5941 | 10.5314 | 20.5941 | 35.1883 | 51.7824 | 9.0628 | 10.5314 | 11.0728 | 10.0628 | 14.5941 | 16.5941 | 10.5314 | 20.5941 | 35.1883 | 51.7824 | 0
6.7215 | 9.3608 | 8.7215 | 7.7215 | 11.0823 | 13.0823 | 9.3608 | 17.0823 | 28.1645 | 41.2468 | 6.7215 | 9.3608 | 8.7315 | 7.7215 | 11.0823 | 13.0823 | 9.3608 | 17.0823 | 28.1645 | 41.2468 | 0
7.5347 | 9.7673 | 9.5347 | 8.5347 | 12.302 | 14.302 | 9.7673 | 18.302 | 30.604 | 44.906 | 7.5347 | 9.7673 | 9.5447 | 8.5347 | 12.302 | 14.302 | 9.7673 | 18.302 | 30.604 | 44.906 | 0
4.2203 | 8.1102 | 6.2203 | 5.2203 | 7.3305 | 9.3305 | 8.1102 | 13.3305 | 20.6609 | 29.9914 | 4.2203 | 8.1102 | 6.2303 | 5.2203 | 7.3305 | 9.3305 | 8.1102 | 13.3305 | 20.6609 | 29.9914 | 0
4.9198 | 8.4599 | 6.9198 | 5.9198 | 8.3797 | 10.3797 | 8.4599 | 14.3797 | 22.7594 | 33.1391 | 4.9198 | 8.4599 | 6.9298 | 5.9198 | 8.3797 | 10.3797 | 8.4599 | 14.3797 | 22.7594 | 33.1391 | 0
3.252 | 7.626 | 5.252 | 4.252 | 5.878 | 7.878 | 7.626 | 11.878 | 17.7559 | 25.6339 | 3.252 | 7.626 | 5.262 | 4.252 | 5.878 | 7.878 | 7.626 | 11.878 | 17.7559 | 25.6339 | 0
6.2071 | 9.1036 | 8.2071 | 7.2071 | 10.3107 | 12.3107 | 9.1036 | 16.3107 | 26.6214 | 38.9322 | 6.2071 | 9.1036 | 8.2171 | 7.2071 | 10.3107 | 12.3107 | 9.1036 | 16.3107 | 26.6214 | 38.9322 | 0
6.9816 | 9.4908 | 8.9816 | 7.9816 | 11.4725 | 13.4725 | 9.4908 | 17.4725 | 28.9449 | 42.4174 | 6.9816 | 9.4908 | 8.9916 | 7.9816 | 11.4725 | 13.4725 | 9.4908 | 17.4725 | 28.9449 | 42.4174 | 0
4.3537 | 8.1768 | 6.3537 | 5.3537 | 7.5305 | 9.5305 | 8.1768 | 13.5305 | 21.061 | 30.5915 | 4.3537 | 8.1768 | 6.3637 | 5.3537 | 7.5305 | 9.5305 | 8.1768 | 13.5305 | 21.061 | 30.5915 | 0
7.4024 | 9.7012 | 9.4024 | 8.4024 | 12.1036 | 14.1036 | 9.7012 | 18.1036 | 30.2073 | 44.3109 | 7.4024 | 9.7012 | 9.4124 | 8.4024 | 12.1036 | 14.1036 | 9.7012 | 18.1036 | 30.2073 | 44.3109 | 0
5.2403 | 8.6202 | 7.2403 | 6.2403 | 8.8605 | 10.8605 | 8.6202 | 14.8605 | 23.7209 | 34.5814 | 5.2403 | 8.6202 | 7.2503 | 6.2403 | 8.8605 | 10.8605 | 8.6202 | 14.8605 | 23.7209 | 34.5814 | 0
6.5781 | 9.289 | 8.5781 | 7.5781 | 10.8671 | 12.8671 | 9.289 | 16.8671 | 27.7343 | 40.6014 | 6.5781 | 9.289 | 8.5881 | 7.5781 | 10.8671 | 12.8671 | 9.289 | 16.8671 | 27.7343 | 40.6014 | 0
7.6429 | 9.8215 | 9.6429 | 8.6429 | 12.4644 | 14.4644 | 9.8215 | 18.4644 | 30.9287 | 45.3931 | 7.6429 | 9.8215 | 9.6529 | 8.6429 | 12.4644 | 14.4644 | 9.8215 | 18.4644 | 30.9287 | 45.3931 | 0
6.3829 | 9.1915 | 8.3829 | 7.3829 | 10.5744 | 12.5744 | 9.1915 | 16.5744 | 27.1487 | 39.7231 | 6.3829 | 9.1915 | 8.3929 | 7.3829 | 10.5744 | 12.5744 | 9.1915 | 16.5744 | 27.1487 | 39.7231 | 0
3.4405 | 7.7202 | 5.4405 | 4.4405 | 6.1607 | 8.1607 | 7.7202 | 12.1607 | 18.3214 | 26.4821 | 3.4405 | 7.7202 | 5.4505 | 4.4405 | 6.1607 | 8.1607 | 7.7202 | 12.1607 | 18.3214 | 26.4821 | 0
8.5773 | 10.2887 | 10.5773 | 9.5773 | 13.866 | 15.866 | 10.2887 | 19.866 | 33.732 | 49.598 | 8.5773 | 10.2887 | 10.5873 | 9.5773 | 13.866 | 15.866 | 10.2887 | 19.866 | 33.732 | 49.598 | 0
8.9551 | 10.4775 | 10.9551 | 9.9551 | 14.4326 | 16.4326 | 10.4775 | 20.4326 | 34.8653 | 51.2979 | 8.9551 | 10.4775 | 10.9651 | 9.9551 | 14.4326 | 16.4326 | 10.4775 | 20.4326 | 34.8653 | 51.2979 | 0
5.4187 | 8.7094 | 7.4187 | 6.4187 | 9.1281 | 11.1281 | 8.7094 | 15.1281 | 24.2561 | 35.3842 | 5.4187 | 8.7094 | 7.4287 | 6.4187 | 9.1281 | 11.1281 | 8.7094 | 15.1281 | 24.2561 | 35.3842 | 0
5.3886 | 8.6943 | 7.3886 | 6.3886 | 9.083 | 11.083 | 8.6943 | 15.083 | 24.1659 | 35.2489 | 5.3886 | 8.6943 | 7.3986 | 6.3886 | 9.083 | 11.083 | 8.6943 | 15.083 | 24.1659 | 35.2489 | 0
8.0894 | 10.0447 | 10.0894 | 9.0894 | 13.1342 | 15.1342 | 10.0447 | 19.1342 | 32.2683 | 47.4025 | 8.0894 | 10.0447 | 10.0994 | 9.0894 | 13.1342 | 15.1342 | 10.0447 | 19.1342 | 32.2683 | 47.4025 | 0
9.5481 | 10.7741 | 11.5481 | 10.5481 | 15.3222 | 17.3222 | 10.7741 | 21.3222 | 36.6444 | 53.9666 | 9.5481 | 10.7741 | 11.5581 | 10.5481 | 15.3222 | 17.3222 | 10.7741 | 21.3222 | 36.6444 | 53.9666 | 0
8.3839 | 10.1919 | 10.3839 | 9.3839 | 13.5758 | 15.5758 | 10.1919 | 19.5758 | 33.1517 | 48.7275 | 8.3839 | 10.1919 | 10.3939 | 9.3839 | 13.5758 | 15.5758 | 10.1919 | 19.5758 | 33.1517 | 48.7275 | 0
5.3671 | 8.6836 | 7.3671 | 6.3671 | 9.0507 | 11.0507 | 8.6836 | 15.0507 | 24.1014 | 35.1521 | 5.3671 | 8.6836 | 7.3771 | 6.3671 | 9.0507 | 11.0507 | 8.6836 | 15.0507 | 24.1014 | 35.1521 | 0
6.4787 | 9.2394 | 8.4787 | 7.4787 | 10.7181 | 12.7181 | 9.2394 | 16.7181 | 27.4362 | 40.1544 | 6.4787 | 9.2394 | 8.4887 | 7.4787 | 10.7181 | 12.7181 | 9.2394 | 16.7181 | 27.4362 | 40.1544 | 0
9.3042 | 10.6521 | 11.3042 | 10.3042 | 14.9563 | 16.9563 | 10.6521 | 20.9563 | 35.9126 | 52.8689 | 9.3042 | 10.6521 | 11.3142 | 10.3042 | 14.9563 | 16.9563 | 10.6521 | 20.9563 | 35.9126 | 52.8689 | 0
2.544 | 7.272 | 4.544 | 3.544 | 4.816 | 6.816 | 7.272 | 10.816 | 15.632 | 22.448 | 2.544 | 7.272 | 4.554 | 3.544 | 4.816 | 6.816 | 7.272 | 10.816 | 15.632 | 22.448 | 0
4.3068 | 8.1534 | 6.3068 | 5.3068 | 7.4603 | 9.4603 | 8.1534 | 13.4603 | 20.9205 | 30.3808 | 4.3068 | 8.1534 | 6.3168 | 5.3068 | 7.4603 | 9.4603 | 8.1534 | 13.4603 | 20.9205 | 30.3808 | 0
4.3765 | 8.1883 | 6.3765 | 5.3765 | 7.5648 | 9.5648 | 8.1883 | 13.5648 | 21.1296 | 30.6944 | 4.3765 | 8.1883 | 6.3865 | 5.3765 | 7.5648 | 9.5648 | 8.1883 | 13.5648 | 21.1296 | 30.6944 | 0
8.9067 | 10.4534 | 10.9067 | 9.9067 | 14.3601 | 16.3601 | 10.4534 | 20.3601 | 34.7202 | 51.0803 | 8.9067 | 10.4534 | 10.9167 | 9.9067 | 14.3601 | 16.3601 | 10.4534 | 20.3601 | 34.7202 | 51.0803 | 0
5.8313 | 8.9156 | 7.8313 | 6.8313 | 9.7469 | 11.7469 | 8.9156 | 15.7469 | 25.4938 | 37.2407 | 5.8313 | 8.9156 | 7.8413 | 6.8313 | 9.7469 | 11.7469 | 8.9156 | 15.7469 | 25.4938 | 37.2407 | 0
5.7318 | 8.8659 | 7.7318 | 6.7318 | 9.5978 | 11.5978 | 8.8659 | 15.5978 | 25.1955 | 36.7933 | 5.7318 | 8.8659 | 7.7418 | 6.7318 | 9.5978 | 11.5978 | 8.8659 | 15.5978 | 25.1955 | 36.7933 | 0
4.0139 | 8.007 | 6.0139 | 5.0139 | 7.0209 | 9.0209 | 8.007 | 13.0209 | 20.0417 | 29.0626 | 4.0139 | 8.007 | 6.0239 | 5.0139 | 7.0209 | 9.0209 | 8.007 | 13.0209 | 20.0417 | 29.0626 | 0
4.3425 | 8.1712 | 6.3425 | 5.3425 | 7.5137 | 9.5137 | 8.1712 | 13.5137 | 21.0274 | 30.5411 | 4.3425 | 8.1712 | 6.3525 | 5.3425 | 7.5137 | 9.5137 | 8.1712 | 13.5137 | 21.0274 | 30.5411 | 0
6.3885 | 9.1943 | 8.3885 | 7.3885 | 10.5828 | 12.5828 | 9.1943 | 16.5828 | 27.1656 | 39.7483 | 6.3885 | 9.1943 | 8.3985 | 7.3885 | 10.5828 | 12.5828 | 9.1943 | 16.5828 | 27.1656 | 39.7483 | 0
4.828 | 8.414 | 6.828 | 5.828 | 8.242 | 10.242 | 8.414 | 14.242 | 22.484 | 32.726 | 4.828 | 8.414 | 6.838 | 5.828 | 8.242 | 10.242 | 8.414 | 14.242 | 22.484 | 32.726 | 0
4.4034 | 8.2017 | 6.4034 | 5.4034 | 7.6051 | 9.6051 | 8.2017 | 13.6051 | 21.2102 | 30.8153 | 4.4034 | 8.2017 | 6.4134 | 5.4034 | 7.6051 | 9.6051 | 8.2017 | 13.6051 | 21.2102 | 30.8153 | 0
4.8238 | 8.4119 | 6.8238 | 5.8238 | 8.2357 | 10.2357 | 8.4119 | 14.2357 | 22.4715 | 32.7072 | 4.8238 | 8.4119 | 6.8338 | 5.8238 | 8.2357 | 10.2357 | 8.4119 | 14.2357 | 22.4715 | 32.7072 | 0
2.2571 | 7.1285 | 4.2571 | 3.2571 | 4.3856 | 6.3856 | 7.1285 | 10.3856 | 14.7713 | 21.1569 | 2.2571 | 7.1285 | 4.2671 | 3.2571 | 4.3856 | 6.3856 | 7.1285 | 10.3856 | 14.7713 | 21.1569 | 0
7.5318 | 9.7659 | 9.5318 | 8.5318 | 12.2977 | 14.2977 | 9.7659 | 18.2977 | 30.5954 | 44.8931 | 7.5318 | 9.7659 | 9.5418 | 8.5318 | 12.2977 | 14.2977 | 9.7659 | 18.2977 | 30.5954 | 44.8931 | 0
5.7824 | 8.8912 | 7.7824 | 6.7824 | 9.6736 | 11.6736 | 8.8912 | 15.6736 | 25.3472 | 37.0208 | 5.7824 | 8.8912 | 7.7924 | 6.7824 | 9.6736 | 11.6736 | 8.8912 | 15.6736 | 25.3472 | 37.0208 | 0
5.2454 | 8.6227 | 7.2454 | 6.2454 | 8.8681 | 10.8681 | 8.6227 | 14.8681 | 23.7362 | 34.6043 | 5.2454 | 8.6227 | 7.2554 | 6.2454 | 8.8681 | 10.8681 | 8.6227 | 14.8681 | 23.7362 | 34.6043 | 0
4.8561 | 8.428 | 6.8561 | 5.8561 | 8.2841 | 10.2841 | 8.428 | 14.2841 | 22.5682 | 32.8522 | 4.8561 | 8.428 | 6.8661 | 5.8561 | 8.2841 | 10.2841 | 8.428 | 14.2841 | 22.5682 | 32.8522 | 0
8.4147 | 10.2073 | 10.4147 | 9.4147 | 13.622 | 15.622 | 10.2073 | 19.622 | 33.244 | 48.866 | 8.4147 | 10.2073 | 10.4247 | 9.4147 | 13.622 | 15.622 | 10.2073 | 19.622 | 33.244 | 48.866 | 0
6.6838 | 9.3419 | 8.6838 | 7.6838 | 11.0256 | 13.0256 | 9.3419 | 17.0256 | 28.0513 | 41.0769 | 6.6838 | 9.3419 | 8.6938 | 7.6838 | 11.0256 | 13.0256 | 9.3419 | 17.0256 | 28.0513 | 41.0769 | 0
0.96635 | 6.4832 | 2.9663 | 1.9663 | 2.4495 | 4.4495 | 6.4832 | 8.4495 | 10.899 | 15.3486 | 0.96635 | 6.4832 | 2.9763 | 1.9663 | 2.4495 | 4.4495 | 6.4832 | 8.4495 | 10.899 | 15.3486 | 0
7.0703 | 9.5351 | 9.0703 | 8.0703 | 11.6054 | 13.6054 | 9.5351 | 17.6054 | 29.2109 | 42.8163 | 7.0703 | 9.5351 | 9.0803 | 8.0703 | 11.6054 | 13.6054 | 9.5351 | 17.6054 | 29.2109 | 42.8163 | 0
7.017 | 9.5085 | 9.017 | 8.017 | 11.5255 | 13.5255 | 9.5085 | 17.5255 | 29.051 | 42.5765 | 7.017 | 9.5085 | 9.027 | 8.017 | 11.5255 | 13.5255 | 9.5085 | 17.5255 | 29.051 | 42.5765 | 0
5.4393 | 8.7196 | 7.4393 | 6.4393 | 9.1589 | 11.1589 | 8.7196 | 15.1589 | 24.3178 | 35.4767 | 5.4393 | 8.7196 | 7.4493 | 6.4393 | 9.1589 | 11.1589 | 8.7196 | 15.1589 | 24.3178 | 35.4767 | 0
2.5841 | 7.2921 | 4.5841 | 3.5841 | 4.8762 | 6.8762 | 7.2921 | 10.8762 | 15.7524 | 22.6286 | 2.5841 | 7.2921 | 4.5941 | 3.5841 | 4.8762 | 6.8762 | 7.2921 | 10.8762 | 15.7524 | 22.6286 | 0
3.8108 | 7.9054 | 5.8108 | 4.8108 | 6.7162 | 8.7162 | 7.9054 | 12.7162 | 19.4324 | 28.1486 | 3.8108 | 7.9054 | 5.8208 | 4.8108 | 6.7162 | 8.7162 | 7.9054 | 12.7162 | 19.4324 | 28.1486 | 0
5.3143 | 8.6572 | 7.3143 | 6.3143 | 8.9715 | 10.9715 | 8.6572 | 14.9715 | 23.9429 | 34.9144 | 5.3143 | 8.6572 | 7.3243 | 6.3143 | 8.9715 | 10.9715 | 8.6572 | 14.9715 | 23.9429 | 34.9144 | 0
6.6577 | 9.3288 | 8.6577 | 7.6577 | 10.9865 | 12.9865 | 9.3288 | 16.9865 | 27.9731 | 40.9596 | 6.6577 | 9.3288 | 8.6677 | 7.6577 | 10.9865 | 12.9865 | 9.3288 | 16.9865 | 27.9731 | 40.9596 | 0
3.0098 | 7.5049 | 5.0098 | 4.0098 | 5.5147 | 7.5147 | 7.5049 | 11.5147 | 17.0295 | 24.5442 | 3.0098 | 7.5049 | 5.0198 | 4.0098 | 5.5147 | 7.5147 | 7.5049 | 11.5147 | 17.0295 | 24.5442 | 0
5.1527 | 8.5764 | 7.1527 | 6.1527 | 8.7291 | 10.7291 | 8.5764 | 14.7291 | 23.4582 | 34.1873 | 5.1527 | 8.5764 | 7.1627 | 6.1527 | 8.7291 | 10.7291 | 8.5764 | 14.7291 | 23.4582 | 34.1873 | 0
5.8825 | 8.9413 | 7.8825 | 6.8825 | 9.8238 | 11.8238 | 8.9413 | 15.8238 | 25.6475 | 37.4713 | 5.8825 | 8.9413 | 7.8925 | 6.8825 | 9.8238 | 11.8238 | 8.9413 | 15.8238 | 25.6475 | 37.4713 | 0
6.6117 | 9.3058 | 8.6117 | 7.6117 | 10.9175 | 12.9175 | 9.3058 | 16.9175 | 27.835 | 40.7525 | 6.6117 | 9.3058 | 8.6217 | 7.6117 | 10.9175 | 12.9175 | 9.3058 | 16.9175 | 27.835 | 40.7525 | 0
7.5536 | 9.7768 | 9.5536 | 8.5536 | 12.3304 | 14.3304 | 9.7768 | 18.3304 | 30.6609 | 44.9913 | 7.5536 | 9.7768 | 9.5636 | 8.5536 | 12.3304 | 14.3304 | 9.7768 | 18.3304 | 30.6609 | 44.9913 | 0
3.9811 | 7.9905 | 5.9811 | 4.9811 | 6.9716 | 8.9716 | 7.9905 | 12.9716 | 19.9432 | 28.9148 | 3.9811 | 7.9905 | 5.9911 | 4.9811 | 6.9716 | 8.9716 | 7.9905 | 12.9716 | 19.9432 | 28.9148 | 0
2.7565 | 7.3783 | 4.7565 | 3.7565 | 5.1348 | 7.1348 | 7.3783 | 11.1348 | 16.2696 | 23.4044 | 2.7565 | 7.3783 | 4.7665 | 3.7565 | 5.1348 | 7.1348 | 7.3783 | 11.1348 | 16.2696 | 23.4044 | 0
1.279 | 6.6395 | 3.279 | 2.279 | 2.9185 | 4.9185 | 6.6395 | 8.9185 | 11.837 | 16.7555 | 1.279 | 6.6395 | 3.289 | 2.279 | 2.9185 | 4.9185 | 6.6395 | 8.9185 | 11.837 | 16.7555 | 0
6.3987 | 9.1993 | 8.3987 | 7.3987 | 10.598 | 12.598 | 9.1993 | 16.598 | 27.196 | 39.794 | 6.3987 | 9.1993 | 8.4087 | 7.3987 | 10.598 | 12.598 | 9.1993 | 16.598 | 27.196 | 39.794 | 0
8.8962 | 10.4481 | 10.8962 | 9.8962 | 14.3443 | 16.3443 | 10.4481 | 20.3443 | 34.6886 | 51.033 | 8.8962 | 10.4481 | 10.9062 | 9.8962 | 14.3443 | 16.3443 | 10.4481 | 20.3443 | 34.6886 | 51.033 | 0
3.2532 | 7.6266 | 5.2532 | 4.2532 | 5.8797 | 7.8797 | 7.6266 | 11.8797 | 17.7595 | 25.6392 | 3.2532 | 7.6266 | 5.2632 | 4.2532 | 5.8797 | 7.8797 | 7.6266 | 11.8797 | 17.7595 | 25.6392 | 0
5.4748 | 8.7374 | 7.4748 | 6.4748 | 9.2122 | 11.2122 | 8.7374 | 15.2122 | 24.4245 | 35.6367 | 5.4748 | 8.7374 | 7.4848 | 6.4748 | 9.2122 | 11.2122 | 8.7374 | 15.2122 | 24.4245 | 35.6367 | 0
5.6701 | 8.8351 | 7.6701 | 6.6701 | 9.5052 | 11.5052 | 8.8351 | 15.5052 | 25.0103 | 36.5155 | 5.6701 | 8.8351 | 7.6801 | 6.6701 | 9.5052 | 11.5052 | 8.8351 | 15.5052 | 25.0103 | 36.5155 | 0
8.5124 | 10.2562 | 10.5124 | 9.5124 | 13.7685 | 15.7685 | 10.2562 | 19.7685 | 33.5371 | 49.3056 | 8.5124 | 10.2562 | 10.5224 | 9.5124 | 13.7685 | 15.7685 | 10.2562 | 19.7685 | 33.5371 | 49.3056 | 0
7.7278 | 9.8639 | 9.7278 | 8.7278 | 12.5917 | 14.5917 | 9.8639 | 18.5917 | 31.1834 | 45.7751 | 7.7278 | 9.8639 | 9.7378 | 8.7278 | 12.5917 | 14.5917 | 9.8639 | 18.5917 | 31.1834 | 45.7751 | 0
6.6958 | 9.3479 | 8.6958 | 7.6958 | 11.0437 | 13.0437 | 9.3479 | 17.0437 | 28.0873 | 41.131 | 6.6958 | 9.3479 | 8.7058 | 7.6958 | 11.0437 | 13.0437 | 9.3479 | 17.0437 | 28.0873 | 41.131 | 0
6.6747 | 9.3373 | 8.6747 | 7.6747 | 11.012 | 13.012 | 9.3373 | 17.012 | 28.024 | 41.036 | 6.6747 | 9.3373 | 8.6847 | 7.6747 | 11.012 | 13.012 | 9.3373 | 17.012 | 28.024 | 41.036 | 0
4.1136 | 8.0568 | 6.1136 | 5.1136 | 7.1705 | 9.1705 | 8.0568 | 13.1705 | 20.3409 | 29.5114 | 4.1136 | 8.0568 | 6.1236 | 5.1136 | 7.1705 | 9.1705 | 8.0568 | 13.1705 | 20.3409 | 29.5114 | 0
6.0322 | 9.0161 | 8.0322 | 7.0322 | 10.0483 | 12.0483 | 9.0161 | 16.0483 | 26.0966 | 38.1449 | 6.0322 | 9.0161 | 8.0422 | 7.0322 | 10.0483 | 12.0483 | 9.0161 | 16.0483 | 26.0966 | 38.1449 | 0
6.0533 | 9.0267 | 8.0533 | 7.0533 | 10.08 | 12.08 | 9.0267 | 16.08 | 26.16 | 38.24 | 6.0533 | 9.0267 | 8.0633 | 7.0533 | 10.08 | 12.08 | 9.0267 | 16.08 | 26.16 | 38.24 | 0
5.3099 | 8.655 | 7.3099 | 6.3099 | 8.9649 | 10.9649 | 8.655 | 14.9649 | 23.9298 | 34.8946 | 5.3099 | 8.655 | 7.3199 | 6.3099 | 8.9649 | 10.9649 | 8.655 | 14.9649 | 23.9298 | 34.8946 | 0
2.783 | 7.3915 | 4.783 | 3.783 | 5.1746 | 7.1746 | 7.3915 | 11.1746 | 16.3491 | 23.5237 | 2.783 | 7.3915 | 4.793 | 3.783 | 5.1746 | 7.1746 | 7.3915 | 11.1746 | 16.3491 | 23.5237 | 0
4.1082 | 8.0541 | 6.1082 | 5.1082 | 7.1622 | 9.1622 | 8.0541 | 13.1622 | 20.3245 | 29.4867 | 4.1082 | 8.0541 | 6.1182 | 5.1082 | 7.1622 | 9.1622 | 8.0541 | 13.1622 | 20.3245 | 29.4867 | 0
9.1167 | 10.5584 | 11.1167 | 10.1167 | 14.6751 | 16.6751 | 10.5584 | 20.6751 | 35.3502 | 52.0254 | 9.1167 | 10.5584 | 11.1267 | 10.1167 | 14.6751 | 16.6751 | 10.5584 | 20.6751 | 35.3502 | 52.0254 | 0
7.2546 | 9.6273 | 9.2546 | 8.2546 | 11.8819 | 13.8819 | 9.6273 | 17.8819 | 29.7637 | 43.6456 | 7.2546 | 9.6273 | 9.2646 | 8.2546 | 11.8819 | 13.8819 | 9.6273 | 17.8819 | 29.7637 | 43.6456 | 0
3.9195 | 7.9598 | 5.9195 | 4.9195 | 6.8793 | 8.8793 | 7.9598 | 12.8793 | 19.7585 | 28.6378 | 3.9195 | 7.9598 | 5.9295 | 4.9195 | 6.8793 | 8.8793 | 7.9598 | 12.8793 | 19.7585 | 28.6378 | 0
7.2151 | 9.6076 | 9.2151 | 8.2151 | 11.8227 | 13.8227 | 9.6076 | 17.8227 | 29.6454 | 43.4681 | 7.2151 | 9.6076 | 9.2251 | 8.2151 | 11.8227 | 13.8227 | 9.6076 | 17.8227 | 29.6454 | 43.4681 | 0
5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 5.3943 | 8.6971 | 7.4043 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 0
4.1806 | 8.0903 | 6.1806 | 5.1806 | 7.2709 | 9.2709 | 8.0903 | 13.2709 | 20.5419 | 29.8128 | 4.1806 | 8.0903 | 6.1906 | 5.1806 | 7.2709 | 9.2709 | 8.0903 | 13.2709 | 20.5419 | 29.8128 | 0
4.4304 | 8.2152 | 6.4304 | 5.4304 | 7.6456 | 9.6456 | 8.2152 | 13.6456 | 21.2912 | 30.9368 | 4.4304 | 8.2152 | 6.4404 | 5.4304 | 7.6456 | 9.6456 | 8.2152 | 13.6456 | 21.2912 | 30.9368 | 0
4.0583 | 8.0291 | 6.0583 | 5.0583 | 7.0874 | 9.0874 | 8.0291 | 13.0874 | 20.1748 | 29.2622 | 4.0583 | 8.0291 | 6.0683 | 5.0583 | 7.0874 | 9.0874 | 8.0291 | 13.0874 | 20.1748 | 29.2622 | 0
6.3386 | 9.1693 | 8.3386 | 7.3386 | 10.5079 | 12.5079 | 9.1693 | 16.5079 | 27.0158 | 39.5236 | 6.3386 | 9.1693 | 8.3486 | 7.3386 | 10.5079 | 12.5079 | 9.1693 | 16.5079 | 27.0158 | 39.5236 | 0
8.3318 | 10.1659 | 10.3318 | 9.3318 | 13.4977 | 15.4977 | 10.1659 | 19.4977 | 32.9953 | 48.493 | 8.3318 | 10.1659 | 10.3418 | 9.3318 | 13.4977 | 15.4977 | 10.1659 | 19.4977 | 32.9953 | 48.493 | 0
3.4866 | 7.7433 | 5.4866 | 4.4866 | 6.23 | 8.23 | 7.7433 | 12.23 | 18.4599 | 26.6899 | 3.4866 | 7.7433 | 5.4966 | 4.4866 | 6.23 | 8.23 | 7.7433 | 12.23 | 18.4599 | 26.6899 | 0
5.145 | 8.5725 | 7.145 | 6.145 | 8.7175 | 10.7175 | 8.5725 | 14.7175 | 23.4351 | 34.1526 | 5.145 | 8.5725 | 7.155 | 6.145 | 8.7175 | 10.7175 | 8.5725 | 14.7175 | 23.4351 | 34.1526 | 0
4.7066 | 8.3533 | 6.7066 | 5.7066 | 8.06 | 10.06 | 8.3533 | 14.06 | 22.1199 | 32.1799 | 4.7066 | 8.3533 | 6.7166 | 5.7066 | 8.06 | 10.06 | 8.3533 | 14.06 | 22.1199 | 32.1799 | 0
3.6298 | 7.8149 | 5.6298 | 4.6298 | 6.4446 | 8.4446 | 7.8149 | 12.4446 | 18.8893 | 27.3339 | 3.6298 | 7.8149 | 5.6398 | 4.6298 | 6.4446 | 8.4446 | 7.8149 | 12.4446 | 18.8893 | 27.3339 | 0
7.1394 | 9.5697 | 9.1394 | 8.1394 | 11.7092 | 13.7092 | 9.5697 | 17.7092 | 29.4183 | 43.1275 | 7.1394 | 9.5697 | 9.1494 | 8.1394 | 11.7092 | 13.7092 | 9.5697 | 17.7092 | 29.4183 | 43.1275 | 0
6.9539 | 9.477 | 8.9539 | 7.9539 | 11.4309 | 13.4309 | 9.477 | 17.4309 | 28.8618 | 42.2928 | 6.9539 | 9.477 | 8.9639 | 7.9539 | 11.4309 | 13.4309 | 9.477 | 17.4309 | 28.8618 | 42.2928 | 0
3.8824 | 7.9412 | 5.8824 | 4.8824 | 6.8235 | 8.8235 | 7.9412 | 12.8235 | 19.6471 | 28.4706 | 3.8824 | 7.9412 | 5.8924 | 4.8824 | 6.8235 | 8.8235 | 7.9412 | 12.8235 | 19.6471 | 28.4706 | 0
4.5081 | 8.2541 | 6.5081 | 5.5081 | 7.7622 | 9.7622 | 8.2541 | 13.7622 | 21.5243 | 31.2865 | 4.5081 | 8.2541 | 6.5181 | 5.5081 | 7.7622 | 9.7622 | 8.2541 | 13.7622 | 21.5243 | 31.2865 | 0
5.4401 | 8.72 | 7.4401 | 6.4401 | 9.1601 | 11.1601 | 8.72 | 15.1601 | 24.3202 | 35.4803 | 5.4401 | 8.72 | 7.4501 | 6.4401 | 9.1601 | 11.1601 | 8.72 | 15.1601 | 24.3202 | 35.4803 | 0
7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 7.2212 | 9.6106 | 9.2312 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 0
6.3068 | 9.1534 | 8.3068 | 7.3068 | 10.4602 | 12.4602 | 9.1534 | 16.4602 | 26.9204 | 39.3807 | 6.3068 | 9.1534 | 8.3168 | 7.3068 | 10.4602 | 12.4602 | 9.1534 | 16.4602 | 26.9204 | 39.3807 | 0
2.4541 | 7.227 | 4.4541 | 3.4541 | 4.6811 | 6.6811 | 7.227 | 10.6811 | 15.3622 | 22.0434 | 2.4541 | 7.227 | 4.4641 | 3.4541 | 4.6811 | 6.6811 | 7.227 | 10.6811 | 15.3622 | 22.0434 | 0
6.616 | 9.308 | 8.616 | 7.616 | 10.924 | 12.924 | 9.308 | 16.924 | 27.848 | 40.772 | 6.616 | 9.308 | 8.626 | 7.616 | 10.924 | 12.924 | 9.308 | 16.924 | 27.848 | 40.772 | 0
6.1816 | 9.0908 | 8.1816 | 7.1816 | 10.2724 | 12.2724 | 9.0908 | 16.2724 | 26.5449 | 38.8173 | 6.1816 | 9.0908 | 8.1916 | 7.1816 | 10.2724 | 12.2724 | 9.0908 | 16.2724 | 26.5449 | 38.8173 | 0
4.1669 | 8.0835 | 6.1669 | 5.1669 | 7.2504 | 9.2504 | 8.0835 | 13.2504 | 20.5008 | 29.7512 | 4.1669 | 8.0835 | 6.1769 | 5.1669 | 7.2504 | 9.2504 | 8.0835 | 13.2504 | 20.5008 | 29.7512 | 0
5.6994 | 8.8497 | 7.6994 | 6.6994 | 9.5491 | 11.5491 | 8.8497 | 15.5491 | 25.0981 | 36.6472 | 5.6994 | 8.8497 | 7.7094 | 6.6994 | 9.5491 | 11.5491 | 8.8497 | 15.5491 | 25.0981 | 36.6472 | 0
6.0425 | 9.0212 | 8.0425 | 7.0425 | 10.0637 | 12.0637 | 9.0212 | 16.0637 | 26.1274 | 38.1911 | 6.0425 | 9.0212 | 8.0525 | 7.0425 | 10.0637 | 12.0637 | 9.0212 | 16.0637 | 26.1274 | 38.1911 | 0
10.3015 | 11.1508 | 12.3015 | 11.3015 | 16.4523 | 18.4523 | 11.1508 | 22.4523 | 38.9045 | 57.3568 | 10.3015 | 11.1508 | 12.3115 | 11.3015 | 16.4523 | 18.4523 | 11.1508 | 22.4523 | 38.9045 | 57.3568 | 0
5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 5.0973 | 8.5487 | 7.1073 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 0
2.9544 | 7.4772 | 4.9544 | 3.9544 | 5.4316 | 7.4316 | 7.4772 | 11.4316 | 16.8633 | 24.2949 | 2.9544 | 7.4772 | 4.9644 | 3.9544 | 5.4316 | 7.4316 | 7.4772 | 11.4316 | 16.8633 | 24.2949 | 0
8.086 | 10.043 | 10.086 | 9.086 | 13.129 | 15.129 | 10.043 | 19.129 | 32.258 | 47.3871 | 8.086 | 10.043 | 10.096 | 9.086 | 13.129 | 15.129 | 10.043 | 19.129 | 32.258 | 47.3871 | 0
3.5671 | 7.7836 | 5.5671 | 4.5671 | 6.3507 | 8.3507 | 7.7836 | 12.3507 | 18.7014 | 27.0522 | 3.5671 | 7.7836 | 5.5771 | 4.5671 | 6.3507 | 8.3507 | 7.7836 | 12.3507 | 18.7014 | 27.0522 | 0
3.1336 | 7.5668 | 5.1336 | 4.1336 | 5.7004 | 7.7004 | 7.5668 | 11.7004 | 17.4008 | 25.1012 | 3.1336 | 7.5668 | 5.1436 | 4.1336 | 5.7004 | 7.7004 | 7.5668 | 11.7004 | 17.4008 | 25.1012 | 0
6.5277 | 9.2639 | 8.5277 | 7.5277 | 10.7916 | 12.7916 | 9.2639 | 16.7916 | 27.5831 | 40.3747 | 6.5277 | 9.2639 | 8.5377 | 7.5277 | 10.7916 | 12.7916 | 9.2639 | 16.7916 | 27.5831 | 40.3747 | 0
4.9065 | 8.4533 | 6.9065 | 5.9065 | 8.3598 | 10.3598 | 8.4533 | 14.3598 | 22.7195 | 33.0793 | 4.9065 | 8.4533 | 6.9165 | 5.9065 | 8.3598 | 10.3598 | 8.4533 | 14.3598 | 22.7195 | 33.0793 | 0
5.0165 | 8.5082 | 7.0165 | 6.0165 | 8.5247 | 10.5247 | 8.5082 | 14.5247 | 23.0494 | 33.5741 | 5.0165 | 8.5082 | 7.0265 | 6.0165 | 8.5247 | 10.5247 | 8.5082 | 14.5247 | 23.0494 | 33.5741 | 0
7.6593 | 9.8296 | 9.6593 | 8.6593 | 12.4889 | 14.4889 | 9.8296 | 18.4889 | 30.9778 | 45.4666 | 7.6593 | 9.8296 | 9.6693 | 8.6593 | 12.4889 | 14.4889 | 9.8296 | 18.4889 | 30.9778 | 45.4666 | 0
7.9067 | 9.9534 | 9.9067 | 8.9067 | 12.8601 | 14.8601 | 9.9534 | 18.8601 | 31.7202 | 46.5803 | 7.9067 | 9.9534 | 9.9167 | 8.9067 | 12.8601 | 14.8601 | 9.9534 | 18.8601 | 31.7202 | 46.5803 | 0
5.5669 | 8.7835 | 7.5669 | 6.5669 | 9.3504 | 11.3504 | 8.7835 | 15.3504 | 24.7008 | 36.0513 | 5.5669 | 8.7835 | 7.5769 | 6.5669 | 9.3504 | 11.3504 | 8.7835 | 15.3504 | 24.7008 | 36.0513 | 0
6.8194 | 9.4097 | 8.8194 | 7.8194 | 11.2291 | 13.2291 | 9.4097 | 17.2291 | 28.4582 | 41.6873 | 6.8194 | 9.4097 | 8.8294 | 7.8194 | 11.2291 | 13.2291 | 9.4097 | 17.2291 | 28.4582 | 41.6873 | 0
4.8316 | 8.4158 | 6.8316 | 5.8316 | 8.2475 | 10.2475 | 8.4158 | 14.2475 | 22.4949 | 32.7424 | 4.8316 | 8.4158 | 6.8416 | 5.8316 | 8.2475 | 10.2475 | 8.4158 | 14.2475 | 22.4949 | 32.7424 | 0
7.73 | 9.865 | 9.73 | 8.73 | 12.595 | 14.595 | 9.865 | 18.595 | 31.19 | 45.785 | 7.73 | 9.865 | 9.74 | 8.73 | 12.595 | 14.595 | 9.865 | 18.595 | 31.19 | 45.785 | 0
4.3301 | 8.1651 | 6.3301 | 5.3301 | 7.4952 | 9.4952 | 8.1651 | 13.4952 | 20.9904 | 30.4857 | 4.3301 | 8.1651 | 6.3401 | 5.3301 | 7.4952 | 9.4952 | 8.1651 | 13.4952 | 20.9904 | 30.4857 | 0
4.0174 | 8.0087 | 6.0174 | 5.0174 | 7.0261 | 9.0261 | 8.0087 | 13.0261 | 20.0522 | 29.0784 | 4.0174 | 8.0087 | 6.0274 | 5.0174 | 7.0261 | 9.0261 | 8.0087 | 13.0261 | 20.0522 | 29.0784 | 0
3.7223 | 7.8612 | 5.7223 | 4.7223 | 6.5835 | 8.5835 | 7.8612 | 12.5835 | 19.1669 | 27.7504 | 3.7223 | 7.8612 | 5.7323 | 4.7223 | 6.5835 | 8.5835 | 7.8612 | 12.5835 | 19.1669 | 27.7504 | 0
5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 5.2901 | 8.645 | 7.3001 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 0
7.4619 | 9.731 | 9.4619 | 8.4619 | 12.1929 | 14.1929 | 9.731 | 18.1929 | 30.3858 | 44.5787 | 7.4619 | 9.731 | 9.4719 | 8.4619 | 12.1929 | 14.1929 | 9.731 | 18.1929 | 30.3858 | 44.5787 | 0
4.2939 | 8.1469 | 6.2939 | 5.2939 | 7.4408 | 9.4408 | 8.1469 | 13.4408 | 20.8817 | 30.3225 | 4.2939 | 8.1469 | 6.3039 | 5.2939 | 7.4408 | 9.4408 | 8.1469 | 13.4408 | 20.8817 | 30.3225 | 0
6.2435 | 9.1217 | 8.2435 | 7.2435 | 10.3652 | 12.3652 | 9.1217 | 16.3652 | 26.7304 | 39.0957 | 6.2435 | 9.1217 | 8.2535 | 7.2435 | 10.3652 | 12.3652 | 9.1217 | 16.3652 | 26.7304 | 39.0957 | 0
5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 5.0921 | 8.546 | 7.1021 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 0
7.367 | 9.6835 | 9.367 | 8.367 | 12.0506 | 14.0506 | 9.6835 | 18.0506 | 30.1011 | 44.1517 | 7.367 | 9.6835 | 9.377 | 8.367 | 12.0506 | 14.0506 | 9.6835 | 18.0506 | 30.1011 | 44.1517 | 0
9.1555 | 10.5777 | 11.1555 | 10.1555 | 14.7332 | 16.7332 | 10.5777 | 20.7332 | 35.4664 | 52.1996 | 9.1555 | 10.5777 | 11.1655 | 10.1555 | 14.7332 | 16.7332 | 10.5777 | 20.7332 | 35.4664 | 52.1996 | 0
4.4266 | 8.2133 | 6.4266 | 5.4266 | 7.64 | 9.64 | 8.2133 | 13.64 | 21.2799 | 30.9199 | 4.4266 | 8.2133 | 6.4366 | 5.4266 | 7.64 | 9.64 | 8.2133 | 13.64 | 21.2799 | 30.9199 | 0
6.4001 | 9.2 | 8.4001 | 7.4001 | 10.6001 | 12.6001 | 9.2 | 16.6001 | 27.2002 | 39.8003 | 6.4001 | 9.2 | 8.4101 | 7.4001 | 10.6001 | 12.6001 | 9.2 | 16.6001 | 27.2002 | 39.8003 | 0
5.0045 | 8.5023 | 7.0045 | 6.0045 | 8.5068 | 10.5068 | 8.5023 | 14.5068 | 23.0136 | 33.5204 | 5.0045 | 8.5023 | 7.0145 | 6.0045 | 8.5068 | 10.5068 | 8.5023 | 14.5068 | 23.0136 | 33.5204 | 0
2.7353 | 7.3676 | 4.7353 | 3.7353 | 5.1029 | 7.1029 | 7.3676 | 11.1029 | 16.2058 | 23.3088 | 2.7353 | 7.3676 | 4.7453 | 3.7353 | 5.1029 | 7.1029 | 7.3676 | 11.1029 | 16.2058 | 23.3088 | 0
5.211 | 8.6055 | 7.211 | 6.211 | 8.8164 | 10.8164 | 8.6055 | 14.8164 | 23.6329 | 34.4493 | 5.211 | 8.6055 | 7.221 | 6.211 | 8.8164 | 10.8164 | 8.6055 | 14.8164 | 23.6329 | 34.4493 | 0
5.7148 | 8.8574 | 7.7148 | 6.7148 | 9.5723 | 11.5723 | 8.8574 | 15.5723 | 25.1445 | 36.7168 | 5.7148 | 8.8574 | 7.7248 | 6.7148 | 9.5723 | 11.5723 | 8.8574 | 15.5723 | 25.1445 | 36.7168 | 0
2.991 | 7.4955 | 4.991 | 3.991 | 5.4865 | 7.4865 | 7.4955 | 11.4865 | 16.9729 | 24.4594 | 2.991 | 7.4955 | 5.001 | 3.991 | 5.4865 | 7.4865 | 7.4955 | 11.4865 | 16.9729 | 24.4594 | 0
5.3673 | 8.6836 | 7.3673 | 6.3673 | 9.0509 | 11.0509 | 8.6836 | 15.0509 | 24.1019 | 35.1528 | 5.3673 | 8.6836 | 7.3773 | 6.3673 | 9.0509 | 11.0509 | 8.6836 | 15.0509 | 24.1019 | 35.1528 | 0
6.8222 | 9.4111 | 8.8222 | 7.8222 | 11.2333 | 13.2333 | 9.4111 | 17.2333 | 28.4667 | 41.7 | 6.8222 | 9.4111 | 8.8322 | 7.8222 | 11.2333 | 13.2333 | 9.4111 | 17.2333 | 28.4667 | 41.7 | 0
5.639 | 8.8195 | 7.639 | 6.639 | 9.4586 | 11.4586 | 8.8195 | 15.4586 | 24.9171 | 36.3757 | 5.639 | 8.8195 | 7.649 | 6.639 | 9.4586 | 11.4586 | 8.8195 | 15.4586 | 24.9171 | 36.3757 | 0
10.6751 | 11.3376 | 12.6751 | 11.6751 | 17.0127 | 19.0127 | 11.3376 | 23.0127 | 40.0254 | 59.0381 | 10.6751 | 11.3376 | 12.6851 | 11.6751 | 17.0127 | 19.0127 | 11.3376 | 23.0127 | 40.0254 | 59.0381 | 0
1.6411 | 6.8205 | 3.6411 | 2.6411 | 3.4616 | 5.4616 | 6.8205 | 9.4616 | 12.9232 | 18.3849 | 1.6411 | 6.8205 | 3.6511 | 2.6411 | 3.4616 | 5.4616 | 6.8205 | 9.4616 | 12.9232 | 18.3849 | 0
5.3028 | 8.6514 | 7.3028 | 6.3028 | 8.9542 | 10.9542 | 8.6514 | 14.9542 | 23.9083 | 34.8625 | 5.3028 | 8.6514 | 7.3128 | 6.3028 | 8.9542 | 10.9542 | 8.6514 | 14.9542 | 23.9083 | 34.8625 | 0
8.489 | 10.2445 | 10.489 | 9.489 | 13.7334 | 15.7334 | 10.2445 | 19.7334 | 33.4669 | 49.2003 | 8.489 | 10.2445 | 10.499 | 9.489 | 13.7334 | 15.7334 | 10.2445 | 19.7334 | 33.4669 | 49.2003 | 0
6.2238 | 9.1119 | 8.2238 | 7.2238 | 10.3356 | 12.3356 | 9.1119 | 16.3356 | 26.6713 | 39.0069 | 6.2238 | 9.1119 | 8.2338 | 7.2238 | 10.3356 | 12.3356 | 9.1119 | 16.3356 | 26.6713 | 39.0069 | 0
5.7985 | 8.8993 | 7.7985 | 6.7985 | 9.6978 | 11.6978 | 8.8993 | 15.6978 | 25.3956 | 37.0935 | 5.7985 | 8.8993 | 7.8085 | 6.7985 | 9.6978 | 11.6978 | 8.8993 | 15.6978 | 25.3956 | 37.0935 | 0
7.9791 | 9.9895 | 9.9791 | 8.9791 | 12.9686 | 14.9686 | 9.9895 | 18.9686 | 31.9373 | 46.9059 | 7.9791 | 9.9895 | 9.9891 | 8.9791 | 12.9686 | 14.9686 | 9.9895 | 18.9686 | 31.9373 | 46.9059 | 0
6.6718 | 9.3359 | 8.6718 | 7.6718 | 11.0076 | 13.0076 | 9.3359 | 17.0076 | 28.0153 | 41.0229 | 6.6718 | 9.3359 | 8.6818 | 7.6718 | 11.0076 | 13.0076 | 9.3359 | 17.0076 | 28.0153 | 41.0229 | 0
2.7548 | 7.3774 | 4.7548 | 3.7548 | 5.1322 | 7.1322 | 7.3774 | 11.1322 | 16.2645 | 23.3967 | 2.7548 | 7.3774 | 4.7648 | 3.7548 | 5.1322 | 7.1322 | 7.3774 | 11.1322 | 16.2645 | 23.3967 | 0
3.7539 | 7.877 | 5.7539 | 4.7539 | 6.6309 | 8.6309 | 7.877 | 12.6309 | 19.2618 | 27.8927 | 3.7539 | 7.877 | 5.7639 | 4.7539 | 6.6309 | 8.6309 | 7.877 | 12.6309 | 19.2618 | 27.8927 | 0
4.0079 | 8.0039 | 6.0079 | 5.0079 | 7.0118 | 9.0118 | 8.0039 | 13.0118 | 20.0237 | 29.0355 | 4.0079 | 8.0039 | 6.0179 | 5.0079 | 7.0118 | 9.0118 | 8.0039 | 13.0118 | 20.0237 | 29.0355 | 0
8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 8.8231 | 10.4115 | 10.8331 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 0
6.8933 | 9.4467 | 8.8933 | 7.8933 | 11.34 | 13.34 | 9.4467 | 17.34 | 28.68 | 42.0201 | 6.8933 | 9.4467 | 8.9033 | 7.8933 | 11.34 | 13.34 | 9.4467 | 17.34 | 28.68 | 42.0201 | 0
3.0902 | 7.5451 | 5.0902 | 4.0902 | 5.6353 | 7.6353 | 7.5451 | 11.6353 | 17.2706 | 24.9059 | 3.0902 | 7.5451 | 5.1002 | 4.0902 | 5.6353 | 7.6353 | 7.5451 | 11.6353 | 17.2706 | 24.9059 | 0
3.6821 | 7.841 | 5.6821 | 4.6821 | 6.5231 | 8.5231 | 7.841 | 12.5231 | 19.0462 | 27.5692 | 3.6821 | 7.841 | 5.6921 | 4.6821 | 6.5231 | 8.5231 | 7.841 | 12.5231 | 19.0462 | 27.5692 | 0
3.021 | 7.5105 | 5.021 | 4.021 | 5.5315 | 7.5315 | 7.5105 | 11.5315 | 17.063 | 24.5945 | 3.021 | 7.5105 | 5.031 | 4.021 | 5.5315 | 7.5315 | 7.5105 | 11.5315 | 17.063 | 24.5945 | 0
8.4728 | 10.2364 | 10.4728 | 9.4728 | 13.7092 | 15.7092 | 10.2364 | 19.7092 | 33.4183 | 49.1275 | 8.4728 | 10.2364 | 10.4828 | 9.4728 | 13.7092 | 15.7092 | 10.2364 | 19.7092 | 33.4183 | 49.1275 | 0
3.493 | 7.7465 | 5.493 | 4.493 | 6.2395 | 8.2395 | 7.7465 | 12.2395 | 18.4791 | 26.7186 | 3.493 | 7.7465 | 5.503 | 4.493 | 6.2395 | 8.2395 | 7.7465 | 12.2395 | 18.4791 | 26.7186 | 0
9.0142 | 10.5071 | 11.0142 | 10.0142 | 14.5214 | 16.5214 | 10.5071 | 20.5214 | 35.0427 | 51.5641 | 9.0142 | 10.5071 | 11.0242 | 10.0142 | 14.5214 | 16.5214 | 10.5071 | 20.5214 | 35.0427 | 51.5641 | 0
10.0246 | 11.0123 | 12.0246 | 11.0246 | 16.0368 | 18.0368 | 11.0123 | 22.0368 | 38.0737 | 56.1105 | 10.0246 | 11.0123 | 12.0346 | 11.0246 | 16.0368 | 18.0368 | 11.0123 | 22.0368 | 38.0737 | 56.1105 | 0
9.1517 | 10.5759 | 11.1517 | 10.1517 | 14.7276 | 16.7276 | 10.5759 | 20.7276 | 35.4552 | 52.1829 | 9.1517 | 10.5759 | 11.1617 | 10.1517 | 14.7276 | 16.7276 | 10.5759 | 20.7276 | 35.4552 | 52.1829 | 0
4.2742 | 8.1371 | 6.2742 | 5.2742 | 7.4113 | 9.4113 | 8.1371 | 13.4113 | 20.8226 | 30.2339 | 4.2742 | 8.1371 | 6.2842 | 5.2742 | 7.4113 | 9.4113 | 8.1371 | 13.4113 | 20.8226 | 30.2339 | 0
4.3436 | 8.1718 | 6.3436 | 5.3436 | 7.5153 | 9.5153 | 8.1718 | 13.5153 | 21.0307 | 30.546 | 4.3436 | 8.1718 | 6.3536 | 5.3436 | 7.5153 | 9.5153 | 8.1718 | 13.5153 | 21.0307 | 30.546 | 0
7.5365 | 9.7683 | 9.5365 | 8.5365 | 12.3048 | 14.3048 | 9.7683 | 18.3048 | 30.6095 | 44.9143 | 7.5365 | 9.7683 | 9.5465 | 8.5365 | 12.3048 | 14.3048 | 9.7683 | 18.3048 | 30.6095 | 44.9143 | 0
2.6661 | 7.333 | 4.6661 | 3.6661 | 4.9991 | 6.9991 | 7.333 | 10.9991 | 15.9983 | 22.9974 | 2.6661 | 7.333 | 4.6761 | 3.6661 | 4.9991 | 6.9991 | 7.333 | 10.9991 | 15.9983 | 22.9974 | 0
5.1754 | 8.5877 | 7.1754 | 6.1754 | 8.7632 | 10.7632 | 8.5877 | 14.7632 | 23.5263 | 34.2895 | 5.1754 | 8.5877 | 7.1854 | 6.1754 | 8.7632 | 10.7632 | 8.5877 | 14.7632 | 23.5263 | 34.2895 | 0
5.602 | 8.801 | 7.602 | 6.602 | 9.4029 | 11.4029 | 8.801 | 15.4029 | 24.8059 | 36.2088 | 5.602 | 8.801 | 7.612 | 6.602 | 9.4029 | 11.4029 | 8.801 | 15.4029 | 24.8059 | 36.2088 | 0
2.4497 | 7.2248 | 4.4497 | 3.4497 | 4.6745 | 6.6745 | 7.2248 | 10.6745 | 15.349 | 22.0234 | 2.4497 | 7.2248 | 4.4597 | 3.4497 | 4.6745 | 6.6745 | 7.2248 | 10.6745 | 15.349 | 22.0234 | 0
8.632 | 10.316 | 10.632 | 9.632 | 13.948 | 15.948 | 10.316 | 19.948 | 33.8959 | 49.8439 | 8.632 | 10.316 | 10.642 | 9.632 | 13.948 | 15.948 | 10.316 | 19.948 | 33.8959 | 49.8439 | 0
7.3605 | 9.6802 | 9.3605 | 8.3605 | 12.0407 | 14.0407 | 9.6802 | 18.0407 | 30.0814 | 44.1221 | 7.3605 | 9.6802 | 9.3705 | 8.3605 | 12.0407 | 14.0407 | 9.6802 | 18.0407 | 30.0814 | 44.1221 | 0
6.2503 | 9.1251 | 8.2503 | 7.2503 | 10.3754 | 12.3754 | 9.1251 | 16.3754 | 26.7508 | 39.1262 | 6.2503 | 9.1251 | 8.2603 | 7.2503 | 10.3754 | 12.3754 | 9.1251 | 16.3754 | 26.7508 | 39.1262 | 0
6.4729 | 9.2365 | 8.4729 | 7.4729 | 10.7094 | 12.7094 | 9.2365 | 16.7094 | 27.4188 | 40.1282 | 6.4729 | 9.2365 | 8.4829 | 7.4729 | 10.7094 | 12.7094 | 9.2365 | 16.7094 | 27.4188 | 40.1282 | 0
5.0375 | 8.5187 | 7.0375 | 6.0375 | 8.5562 | 10.5562 | 8.5187 | 14.5562 | 23.1124 | 33.6686 | 5.0375 | 8.5187 | 7.0475 | 6.0375 | 8.5562 | 10.5562 | 8.5187 | 14.5562 | 23.1124 | 33.6686 | 0
6.4828 | 9.2414 | 8.4828 | 7.4828 | 10.7243 | 12.7243 | 9.2414 | 16.7243 | 27.4485 | 40.1728 | 6.4828 | 9.2414 | 8.4928 | 7.4828 | 10.7243 | 12.7243 | 9.2414 | 16.7243 | 27.4485 | 40.1728 | 0
8.6636 | 10.3318 | 10.6636 | 9.6636 | 13.9954 | 15.9954 | 10.3318 | 19.9954 | 33.9908 | 49.9862 | 8.6636 | 10.3318 | 10.6736 | 9.6636 | 13.9954 | 15.9954 | 10.3318 | 19.9954 | 33.9908 | 49.9862 | 0
6.1928 | 9.0964 | 8.1928 | 7.1928 | 10.2893 | 12.2893 | 9.0964 | 16.2893 | 26.5785 | 38.8678 | 6.1928 | 9.0964 | 8.2028 | 7.1928 | 10.2893 | 12.2893 | 9.0964 | 16.2893 | 26.5785 | 38.8678 | 0
5.2215 | 8.6108 | 7.2215 | 6.2215 | 8.8323 | 10.8323 | 8.6108 | 14.8323 | 23.6646 | 34.4969 | 5.2215 | 8.6108 | 7.2315 | 6.2215 | 8.8323 | 10.8323 | 8.6108 | 14.8323 | 23.6646 | 34.4969 | 0
3.3861 | 7.693 | 5.3861 | 4.3861 | 6.0791 | 8.0791 | 7.693 | 12.0791 | 18.1583 | 26.2374 | 3.3861 | 7.693 | 5.3961 | 4.3861 | 6.0791 | 8.0791 | 7.693 | 12.0791 | 18.1583 | 26.2374 | 0
10.7513 | 11.3757 | 12.7513 | 11.7513 | 17.127 | 19.127 | 11.3757 | 23.127 | 40.2539 | 59.3809 | 10.7513 | 11.3757 | 12.7613 | 11.7513 | 17.127 | 19.127 | 11.3757 | 23.127 | 40.2539 | 59.3809 | 0
5.4192 | 8.7096 | 7.4192 | 6.4192 | 9.1288 | 11.1288 | 8.7096 | 15.1288 | 24.2576 | 35.3864 | 5.4192 | 8.7096 | 7.4292 | 6.4192 | 9.1288 | 11.1288 | 8.7096 | 15.1288 | 24.2576 | 35.3864 | 0
10.2533 | 11.1267 | 12.2533 | 11.2533 | 16.38 | 18.38 | 11.1267 | 22.38 | 38.7599 | 57.1399 | 10.2533 | 11.1267 | 12.2633 | 11.2533 | 16.38 | 18.38 | 11.1267 | 22.38 | 38.7599 | 57.1399 | 0
4.7906 | 8.3953 | 6.7906 | 5.7906 | 8.1858 | 10.1858 | 8.3953 | 14.1858 | 22.3717 | 32.5575 | 4.7906 | 8.3953 | 6.8006 | 5.7906 | 8.1858 | 10.1858 | 8.3953 | 14.1858 | 22.3717 | 32.5575 | 0
5.4023 | 8.7011 | 7.4023 | 6.4023 | 9.1034 | 11.1034 | 8.7011 | 15.1034 | 24.2068 | 35.3102 | 5.4023 | 8.7011 | 7.4123 | 6.4023 | 9.1034 | 11.1034 | 8.7011 | 15.1034 | 24.2068 | 35.3102 | 0
9.2231 | 10.6116 | 11.2231 | 10.2231 | 14.8347 | 16.8347 | 10.6116 | 20.8347 | 35.6693 | 52.504 | 9.2231 | 10.6116 | 11.2331 | 10.2231 | 14.8347 | 16.8347 | 10.6116 | 20.8347 | 35.6693 | 52.504 | 0
6.4629 | 9.2314 | 8.4629 | 7.4629 | 10.6943 | 12.6943 | 9.2314 | 16.6943 | 27.3886 | 40.0829 | 6.4629 | 9.2314 | 8.4729 | 7.4629 | 10.6943 | 12.6943 | 9.2314 | 16.6943 | 27.3886 | 40.0829 | 0
3.3717 | 7.6858 | 5.3717 | 4.3717 | 6.0575 | 8.0575 | 7.6858 | 12.0575 | 18.115 | 26.1724 | 3.3717 | 7.6858 | 5.3817 | 4.3717 | 6.0575 | 8.0575 | 7.6858 | 12.0575 | 18.115 | 26.1724 | 0
5.6239 | 8.812 | 7.6239 | 6.6239 | 9.4359 | 11.4359 | 8.812 | 15.4359 | 24.8718 | 36.3078 | 5.6239 | 8.812 | 7.6339 | 6.6239 | 9.4359 | 11.4359 | 8.812 | 15.4359 | 24.8718 | 36.3078 | 0
9.3247 | 10.6624 | 11.3247 | 10.3247 | 14.9871 | 16.9871 | 10.6624 | 20.9871 | 35.9742 | 52.9613 | 9.3247 | 10.6624 | 11.3347 | 10.3247 | 14.9871 | 16.9871 | 10.6624 | 20.9871 | 35.9742 | 52.9613 | 0
4.3088 | 8.1544 | 6.3088 | 5.3088 | 7.4632 | 9.4632 | 8.1544 | 13.4632 | 20.9264 | 30.3896 | 4.3088 | 8.1544 | 6.3188 | 5.3088 | 7.4632 | 9.4632 | 8.1544 | 13.4632 | 20.9264 | 30.3896 | 0
5.0985 | 8.5493 | 7.0985 | 6.0985 | 8.6478 | 10.6478 | 8.5493 | 14.6478 | 23.2956 | 33.9434 | 5.0985 | 8.5493 | 7.1085 | 6.0985 | 8.6478 | 10.6478 | 8.5493 | 14.6478 | 23.2956 | 33.9434 | 0
7.6629 | 9.8315 | 9.6629 | 8.6629 | 12.4944 | 14.4944 | 9.8315 | 18.4944 | 30.9888 | 45.4832 | 7.6629 | 9.8315 | 9.6729 | 8.6629 | 12.4944 | 14.4944 | 9.8315 | 18.4944 | 30.9888 | 45.4832 | 0
9.3024 | 10.6512 | 11.3024 | 10.3024 | 14.9536 | 16.9536 | 10.6512 | 20.9536 | 35.9072 | 52.8609 | 9.3024 | 10.6512 | 11.3124 | 10.3024 | 14.9536 | 16.9536 | 10.6512 | 20.9536 | 35.9072 | 52.8609 | 0
8.7686 | 10.3843 | 10.7686 | 9.7686 | 14.1529 | 16.1529 | 10.3843 | 20.1529 | 34.3058 | 50.4587 | 8.7686 | 10.3843 | 10.7786 | 9.7686 | 14.1529 | 16.1529 | 10.3843 | 20.1529 | 34.3058 | 50.4587 | 0
8.1501 | 10.075 | 10.1501 | 9.1501 | 13.2251 | 15.2251 | 10.075 | 19.2251 | 32.4502 | 47.6753 | 8.1501 | 10.075 | 10.1601 | 9.1501 | 13.2251 | 15.2251 | 10.075 | 19.2251 | 32.4502 | 47.6753 | 0
6.7669 | 9.3835 | 8.7669 | 7.7669 | 11.1504 | 13.1504 | 9.3835 | 17.1504 | 28.3008 | 41.4512 | 6.7669 | 9.3835 | 8.7769 | 7.7669 | 11.1504 | 13.1504 | 9.3835 | 17.1504 | 28.3008 | 41.4512 | 0
6.0705 | 9.0352 | 8.0705 | 7.0705 | 10.1057 | 12.1057 | 9.0352 | 16.1057 | 26.2114 | 38.3171 | 6.0705 | 9.0352 | 8.0805 | 7.0705 | 10.1057 | 12.1057 | 9.0352 | 16.1057 | 26.2114 | 38.3171 | 0
5.7724 | 8.8862 | 7.7724 | 6.7724 | 9.6586 | 11.6586 | 8.8862 | 15.6586 | 25.3172 | 36.9757 | 5.7724 | 8.8862 | 7.7824 | 6.7724 | 9.6586 | 11.6586 | 8.8862 | 15.6586 | 25.3172 | 36.9757 | 0
7.6638 | 9.8319 | 9.6638 | 8.6638 | 12.4957 | 14.4957 | 9.8319 | 18.4957 | 30.9914 | 45.487 | 7.6638 | 9.8319 | 9.6738 | 8.6638 | 12.4957 | 14.4957 | 9.8319 | 18.4957 | 30.9914 | 45.487 | 0
5.8442 | 8.9221 | 7.8442 | 6.8442 | 9.7663 | 11.7663 | 8.9221 | 15.7663 | 25.5325 | 37.2988 | 5.8442 | 8.9221 | 7.8542 | 6.8442 | 9.7663 | 11.7663 | 8.9221 | 15.7663 | 25.5325 | 37.2988 | 0
4.8173 | 8.4086 | 6.8173 | 5.8173 | 8.2259 | 10.2259 | 8.4086 | 14.2259 | 22.4518 | 32.6777 | 4.8173 | 8.4086 | 6.8273 | 5.8173 | 8.2259 | 10.2259 | 8.4086 | 14.2259 | 22.4518 | 32.6777 | 0
3.6353 | 7.8177 | 5.6353 | 4.6353 | 6.453 | 8.453 | 7.8177 | 12.453 | 18.9059 | 27.3589 | 3.6353 | 7.8177 | 5.6453 | 4.6353 | 6.453 | 8.453 | 7.8177 | 12.453 | 18.9059 | 27.3589 | 0
3.3053 | 7.6526 | 5.3053 | 4.3053 | 5.9579 | 7.9579 | 7.6526 | 11.9579 | 17.9158 | 25.8737 | 3.3053 | 7.6526 | 5.3153 | 4.3053 | 5.9579 | 7.9579 | 7.6526 | 11.9579 | 17.9158 | 25.8737 | 0
5.0443 | 8.5222 | 7.0443 | 6.0443 | 8.5665 | 10.5665 | 8.5222 | 14.5665 | 23.133 | 33.6995 | 5.0443 | 8.5222 | 7.0543 | 6.0443 | 8.5665 | 10.5665 | 8.5222 | 14.5665 | 23.133 | 33.6995 | 0
8.0763 | 10.0381 | 10.0763 | 9.0763 | 13.1144 | 15.1144 | 10.0381 | 19.1144 | 32.2289 | 47.3433 | 8.0763 | 10.0381 | 10.0863 | 9.0763 | 13.1144 | 15.1144 | 10.0381 | 19.1144 | 32.2289 | 47.3433 | 0
4.3336 | 8.1668 | 6.3336 | 5.3336 | 7.5004 | 9.5004 | 8.1668 | 13.5004 | 21.0008 | 30.5013 | 4.3336 | 8.1668 | 6.3436 | 5.3336 | 7.5004 | 9.5004 | 8.1668 | 13.5004 | 21.0008 | 30.5013 | 0
9.9359 | 10.9679 | 11.9359 | 10.9359 | 15.9038 | 17.9038 | 10.9679 | 21.9038 | 37.8077 | 55.7115 | 9.9359 | 10.9679 | 11.9459 | 10.9359 | 15.9038 | 17.9038 | 10.9679 | 21.9038 | 37.8077 | 55.7115 | 0
6.4882 | 9.2441 | 8.4882 | 7.4882 | 10.7323 | 12.7323 | 9.2441 | 16.7323 | 27.4646 | 40.1969 | 6.4882 | 9.2441 | 8.4982 | 7.4882 | 10.7323 | 12.7323 | 9.2441 | 16.7323 | 27.4646 | 40.1969 | 0
3.7597 | 7.8798 | 5.7597 | 4.7597 | 6.6395 | 8.6395 | 7.8798 | 12.6395 | 19.279 | 27.9185 | 3.7597 | 7.8798 | 5.7697 | 4.7597 | 6.6395 | 8.6395 | 7.8798 | 12.6395 | 19.279 | 27.9185 | 0
4.1555 | 8.0777 | 6.1555 | 5.1555 | 7.2332 | 9.2332 | 8.0777 | 13.2332 | 20.4665 | 29.6997 | 4.1555 | 8.0777 | 6.1655 | 5.1555 | 7.2332 | 9.2332 | 8.0777 | 13.2332 | 20.4665 | 29.6997 | 0
2.6525 | 7.3263 | 4.6525 | 3.6525 | 4.9788 | 6.9788 | 7.3263 | 10.9788 | 15.9575 | 22.9363 | 2.6525 | 7.3263 | 4.6625 | 3.6525 | 4.9788 | 6.9788 | 7.3263 | 10.9788 | 15.9575 | 22.9363 | 0
1.8403 | 6.9201 | 3.8403 | 2.8403 | 3.7604 | 5.7604 | 6.9201 | 9.7604 | 13.5208 | 19.2812 | 1.8403 | 6.9201 | 3.8503 | 2.8403 | 3.7604 | 5.7604 | 6.9201 | 9.7604 | 13.5208 | 19.2812 | 0
2.6667 | 7.3334 | 4.6667 | 3.6667 | 5.0001 | 7.0001 | 7.3334 | 11.0001 | 16.0001 | 23.0002 | 2.6667 | 7.3334 | 4.6767 | 3.6667 | 5.0001 | 7.0001 | 7.3334 | 11.0001 | 16.0001 | 23.0002 | 0
6.4608 | 9.2304 | 8.4608 | 7.4608 | 10.6912 | 12.6912 | 9.2304 | 16.6912 | 27.3825 | 40.0737 | 6.4608 | 9.2304 | 8.4708 | 7.4608 | 10.6912 | 12.6912 | 9.2304 | 16.6912 | 27.3825 | 40.0737 | 0
4.1906 | 8.0953 | 6.1906 | 5.1906 | 7.2858 | 9.2858 | 8.0953 | 13.2858 | 20.5717 | 29.8575 | 4.1906 | 8.0953 | 6.2006 | 5.1906 | 7.2858 | 9.2858 | 8.0953 | 13.2858 | 20.5717 | 29.8575 | 0
8.6153 | 10.3077 | 10.6153 | 9.6153 | 13.923 | 15.923 | 10.3077 | 19.923 | 33.846 | 49.769 | 8.6153 | 10.3077 | 10.6253 | 9.6153 | 13.923 | 15.923 | 10.3077 | 19.923 | 33.846 | 49.769 | 0
4.7385 | 8.3693 | 6.7385 | 5.7385 | 8.1078 | 10.1078 | 8.3693 | 14.1078 | 22.2156 | 32.3234 | 4.7385 | 8.3693 | 6.7485 | 5.7385 | 8.1078 | 10.1078 | 8.3693 | 14.1078 | 22.2156 | 32.3234 | 0
2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 2.9838 | 7.4919 | 4.9938 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 0
3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 3.9727 | 7.9863 | 5.9827 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 0
5.9707 | 8.9854 | 7.9707 | 6.9707 | 9.9561 | 11.9561 | 8.9854 | 15.9561 | 25.9121 | 37.8682 | 5.9707 | 8.9854 | 7.9807 | 6.9707 | 9.9561 | 11.9561 | 8.9854 | 15.9561 | 25.9121 | 37.8682 | 0
8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 8.3644 | 10.1822 | 10.3744 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 0
5.1237 | 8.5618 | 7.1237 | 6.1237 | 8.6855 | 10.6855 | 8.5618 | 14.6855 | 23.3711 | 34.0566 | 5.1237 | 8.5618 | 7.1337 | 6.1237 | 8.6855 | 10.6855 | 8.5618 | 14.6855 | 23.3711 | 34.0566 | 0
4.2034 | 8.1017 | 6.2034 | 5.2034 | 7.3051 | 9.3051 | 8.1017 | 13.3051 | 20.6102 | 29.9154 | 4.2034 | 8.1017 | 6.2134 | 5.2034 | 7.3051 | 9.3051 | 8.1017 | 13.3051 | 20.6102 | 29.9154 | 0
5.5663 | 8.7832 | 7.5663 | 6.5663 | 9.3495 | 11.3495 | 8.7832 | 15.3495 | 24.699 | 36.0484 | 5.5663 | 8.7832 | 7.5763 | 6.5663 | 9.3495 | 11.3495 | 8.7832 | 15.3495 | 24.699 | 36.0484 | 0
6.8431 | 9.4215 | 8.8431 | 7.8431 | 11.2646 | 13.2646 | 9.4215 | 17.2646 | 28.5292 | 41.7939 | 6.8431 | 9.4215 | 8.8531 | 7.8431 | 11.2646 | 13.2646 | 9.4215 | 17.2646 | 28.5292 | 41.7939 | 0
6.8551 | 9.4276 | 8.8551 | 7.8551 | 11.2827 | 13.2827 | 9.4276 | 17.2827 | 28.5654 | 41.8481 | 6.8551 | 9.4276 | 8.8651 | 7.8551 | 11.2827 | 13.2827 | 9.4276 | 17.2827 | 28.5654 | 41.8481 | 0
4.4435 | 8.2217 | 6.4435 | 5.4435 | 7.6652 | 9.6652 | 8.2217 | 13.6652 | 21.3304 | 30.9956 | 4.4435 | 8.2217 | 6.4535 | 5.4435 | 7.6652 | 9.6652 | 8.2217 | 13.6652 | 21.3304 | 30.9956 | 0
9.454 | 10.727 | 11.454 | 10.454 | 15.181 | 17.181 | 10.727 | 21.181 | 36.3619 | 53.5429 | 9.454 | 10.727 | 11.464 | 10.454 | 15.181 | 17.181 | 10.727 | 21.181 | 36.3619 | 53.5429 | 0
7.8182 | 9.9091 | 9.8182 | 8.8182 | 12.7273 | 14.7273 | 9.9091 | 18.7273 | 31.4547 | 46.182 | 7.8182 | 9.9091 | 9.8282 | 8.8182 | 12.7273 | 14.7273 | 9.9091 | 18.7273 | 31.4547 | 46.182 | 0
6.9341 | 9.4671 | 8.9341 | 7.9341 | 11.4012 | 13.4012 | 9.4671 | 17.4012 | 28.8023 | 42.2035 | 6.9341 | 9.4671 | 8.9441 | 7.9341 | 11.4012 | 13.4012 | 9.4671 | 17.4012 | 28.8023 | 42.2035 | 0
4.4815 | 8.2408 | 6.4815 | 5.4815 | 7.7223 | 9.7223 | 8.2408 | 13.7223 | 21.4445 | 31.1668 | 4.4815 | 8.2408 | 6.4915 | 5.4815 | 7.7223 | 9.7223 | 8.2408 | 13.7223 | 21.4445 | 31.1668 | 0
5.1586 | 8.5793 | 7.1586 | 6.1586 | 8.7379 | 10.7379 | 8.5793 | 14.7379 | 23.4758 | 34.2137 | 5.1586 | 8.5793 | 7.1686 | 6.1586 | 8.7379 | 10.7379 | 8.5793 | 14.7379 | 23.4758 | 34.2137 | 0
8.2539 | 10.1269 | 10.2539 | 9.2539 | 13.3808 | 15.3808 | 10.1269 | 19.3808 | 32.7616 | 48.1423 | 8.2539 | 10.1269 | 10.2639 | 9.2539 | 13.3808 | 15.3808 | 10.1269 | 19.3808 | 32.7616 | 48.1423 | 0
7.8806 | 9.9403 | 9.8806 | 8.8806 | 12.8209 | 14.8209 | 9.9403 | 18.8209 | 31.6419 | 46.4628 | 7.8806 | 9.9403 | 9.8906 | 8.8806 | 12.8209 | 14.8209 | 9.9403 | 18.8209 | 31.6419 | 46.4628 | 0
4.776 | 8.388 | 6.776 | 5.776 | 8.164 | 10.164 | 8.388 | 14.164 | 22.3281 | 32.4921 | 4.776 | 8.388 | 6.786 | 5.776 | 8.164 | 10.164 | 8.388 | 14.164 | 22.3281 | 32.4921 | 0
6.3025 | 9.1512 | 8.3025 | 7.3025 | 10.4537 | 12.4537 | 9.1512 | 16.4537 | 26.9074 | 39.3611 | 6.3025 | 9.1512 | 8.3125 | 7.3025 | 10.4537 | 12.4537 | 9.1512 | 16.4537 | 26.9074 | 39.3611 | 0
6.7528 | 9.3764 | 8.7528 | 7.7528 | 11.1292 | 13.1292 | 9.3764 | 17.1292 | 28.2584 | 41.3875 | 6.7528 | 9.3764 | 8.7628 | 7.7528 | 11.1292 | 13.1292 | 9.3764 | 17.1292 | 28.2584 | 41.3875 | 0
6.2989 | 9.1495 | 8.2989 | 7.2989 | 10.4484 | 12.4484 | 9.1495 | 16.4484 | 26.8968 | 39.3451 | 6.2989 | 9.1495 | 8.3089 | 7.2989 | 10.4484 | 12.4484 | 9.1495 | 16.4484 | 26.8968 | 39.3451 | 0
6.9488 | 9.4744 | 8.9488 | 7.9488 | 11.4232 | 13.4232 | 9.4744 | 17.4232 | 28.8464 | 42.2696 | 6.9488 | 9.4744 | 8.9588 | 7.9488 | 11.4232 | 13.4232 | 9.4744 | 17.4232 | 28.8464 | 42.2696 | 0
3.3735 | 7.6867 | 5.3735 | 4.3735 | 6.0602 | 8.0602 | 7.6867 | 12.0602 | 18.1204 | 26.1806 | 3.3735 | 7.6867 | 5.3835 | 4.3735 | 6.0602 | 8.0602 | 7.6867 | 12.0602 | 18.1204 | 26.1806 | 0
8.8156 | 10.4078 | 10.8156 | 9.8156 | 14.2235 | 16.2235 | 10.4078 | 20.2235 | 34.4469 | 50.6704 | 8.8156 | 10.4078 | 10.8256 | 9.8156 | 14.2235 | 16.2235 | 10.4078 | 20.2235 | 34.4469 | 50.6704 | 0
6.1938 | 9.0969 | 8.1938 | 7.1938 | 10.2907 | 12.2907 | 9.0969 | 16.2907 | 26.5813 | 38.872 | 6.1938 | 9.0969 | 8.2038 | 7.1938 | 10.2907 | 12.2907 | 9.0969 | 16.2907 | 26.5813 | 38.872 | 0
2.6892 | 7.3446 | 4.6892 | 3.6892 | 5.0338 | 7.0338 | 7.3446 | 11.0338 | 16.0676 | 23.1013 | 2.6892 | 7.3446 | 4.6992 | 3.6892 | 5.0338 | 7.0338 | 7.3446 | 11.0338 | 16.0676 | 23.1013 | 0
9.693 | 10.8465 | 11.693 | 10.693 | 15.5395 | 17.5395 | 10.8465 | 21.5395 | 37.0789 | 54.6184 | 9.693 | 10.8465 | 11.703 | 10.693 | 15.5395 | 17.5395 | 10.8465 | 21.5395 | 37.0789 | 54.6184 | 0
7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 7.2212 | 9.6106 | 9.2312 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 0
7.6207 | 9.8104 | 9.6207 | 8.6207 | 12.4311 | 14.4311 | 9.8104 | 18.4311 | 30.8621 | 45.2932 | 7.6207 | 9.8104 | 9.6307 | 8.6207 | 12.4311 | 14.4311 | 9.8104 | 18.4311 | 30.8621 | 45.2932 | 0
5.3109 | 8.6554 | 7.3109 | 6.3109 | 8.9663 | 10.9663 | 8.6554 | 14.9663 | 23.9327 | 34.899 | 5.3109 | 8.6554 | 7.3209 | 6.3109 | 8.9663 | 10.9663 | 8.6554 | 14.9663 | 23.9327 | 34.899 | 0
5.815 | 8.9075 | 7.815 | 6.815 | 9.7225 | 11.7225 | 8.9075 | 15.7225 | 25.445 | 37.1675 | 5.815 | 8.9075 | 7.825 | 6.815 | 9.7225 | 11.7225 | 8.9075 | 15.7225 | 25.445 | 37.1675 | 0
8.6974 | 10.3487 | 10.6974 | 9.6974 | 14.0461 | 16.0461 | 10.3487 | 20.0461 | 34.0922 | 50.1383 | 8.6974 | 10.3487 | 10.7074 | 9.6974 | 14.0461 | 16.0461 | 10.3487 | 20.0461 | 34.0922 | 50.1383 | 0
4.5436 | 8.2718 | 6.5436 | 5.5436 | 7.8155 | 9.8155 | 8.2718 | 13.8155 | 21.6309 | 31.4464 | 4.5436 | 8.2718 | 6.5536 | 5.5436 | 7.8155 | 9.8155 | 8.2718 | 13.8155 | 21.6309 | 31.4464 | 0
3.342 | 7.671 | 5.342 | 4.342 | 6.013 | 8.013 | 7.671 | 12.013 | 18.0259 | 26.0389 | 3.342 | 7.671 | 5.352 | 4.342 | 6.013 | 8.013 | 7.671 | 12.013 | 18.0259 | 26.0389 | 0
3.0612 | 7.5306 | 5.0612 | 4.0612 | 5.5918 | 7.5918 | 7.5306 | 11.5918 | 17.1837 | 24.7755 | 3.0612 | 7.5306 | 5.0712 | 4.0612 | 5.5918 | 7.5918 | 7.5306 | 11.5918 | 17.1837 | 24.7755 | 0
8.378 | 10.189 | 10.378 | 9.378 | 13.567 | 15.567 | 10.189 | 19.567 | 33.1339 | 48.7009 | 8.378 | 10.189 | 10.388 | 9.378 | 13.567 | 15.567 | 10.189 | 19.567 | 33.1339 | 48.7009 | 0
5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 5.7998 | 8.8999 | 7.8098 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 0
5.55 | 8.775 | 7.55 | 6.55 | 9.325 | 11.325 | 8.775 | 15.325 | 24.65 | 35.9751 | 5.55 | 8.775 | 7.56 | 6.55 | 9.325 | 11.325 | 8.775 | 15.325 | 24.65 | 35.9751 | 0
8.0143 | 10.0072 | 10.0143 | 9.0143 | 13.0215 | 15.0215 | 10.0072 | 19.0215 | 32.043 | 47.0645 | 8.0143 | 10.0072 | 10.0243 | 9.0143 | 13.0215 | 15.0215 | 10.0072 | 19.0215 | 32.043 | 47.0645 | 0
4.2615 | 8.1308 | 6.2615 | 5.2615 | 7.3923 | 9.3923 | 8.1308 | 13.3923 | 20.7846 | 30.1769 | 4.2615 | 8.1308 | 6.2715 | 5.2615 | 7.3923 | 9.3923 | 8.1308 | 13.3923 | 20.7846 | 30.1769 | 0
4.3816 | 8.1908 | 6.3816 | 5.3816 | 7.5724 | 9.5724 | 8.1908 | 13.5724 | 21.1449 | 30.7173 | 4.3816 | 8.1908 | 6.3916 | 5.3816 | 7.5724 | 9.5724 | 8.1908 | 13.5724 | 21.1449 | 30.7173 | 0
5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 5.7998 | 8.8999 | 7.8098 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 0
7.8028 | 9.9014 | 9.8028 | 8.8028 | 12.7042 | 14.7042 | 9.9014 | 18.7042 | 31.4083 | 46.1125 | 7.8028 | 9.9014 | 9.8128 | 8.8028 | 12.7042 | 14.7042 | 9.9014 | 18.7042 | 31.4083 | 46.1125 | 0
8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 8.3644 | 10.1822 | 10.3744 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 0
5.5132 | 8.7566 | 7.5132 | 6.5132 | 9.2698 | 11.2698 | 8.7566 | 15.2698 | 24.5397 | 35.8095 | 5.5132 | 8.7566 | 7.5232 | 6.5132 | 9.2698 | 11.2698 | 8.7566 | 15.2698 | 24.5397 | 35.8095 | 0
7.8861 | 9.9431 | 9.8861 | 8.8861 | 12.8292 | 14.8292 | 9.9431 | 18.8292 | 31.6583 | 46.4875 | 7.8861 | 9.9431 | 9.8961 | 8.8861 | 12.8292 | 14.8292 | 9.9431 | 18.8292 | 31.6583 | 46.4875 | 0
6.7892 | 9.3946 | 8.7892 | 7.7892 | 11.1838 | 13.1838 | 9.3946 | 17.1838 | 28.3676 | 41.5514 | 6.7892 | 9.3946 | 8.7992 | 7.7892 | 11.1838 | 13.1838 | 9.3946 | 17.1838 | 28.3676 | 41.5514 | 0
4.1869 | 8.0934 | 6.1869 | 5.1869 | 7.2803 | 9.2803 | 8.0934 | 13.2803 | 20.5606 | 29.8409 | 4.1869 | 8.0934 | 6.1969 | 5.1869 | 7.2803 | 9.2803 | 8.0934 | 13.2803 | 20.5606 | 29.8409 | 0
4.1938 | 8.0969 | 6.1938 | 5.1938 | 7.2907 | 9.2907 | 8.0969 | 13.2907 | 20.5813 | 29.872 | 4.1938 | 8.0969 | 6.2038 | 5.1938 | 7.2907 | 9.2907 | 8.0969 | 13.2907 | 20.5813 | 29.872 | 0
3.2575 | 7.6287 | 5.2575 | 4.2575 | 5.8862 | 7.8862 | 7.6287 | 11.8862 | 17.7724 | 25.6586 | 3.2575 | 7.6287 | 5.2675 | 4.2575 | 5.8862 | 7.8862 | 7.6287 | 11.8862 | 17.7724 | 25.6586 | 0
4.0356 | 8.0178 | 6.0356 | 5.0356 | 7.0534 | 9.0534 | 8.0178 | 13.0534 | 20.1068 | 29.1602 | 4.0356 | 8.0178 | 6.0456 | 5.0356 | 7.0534 | 9.0534 | 8.0178 | 13.0534 | 20.1068 | 29.1602 | 0
6.4349 | 9.2175 | 8.4349 | 7.4349 | 10.6524 | 12.6524 | 9.2175 | 16.6524 | 27.3048 | 39.9572 | 6.4349 | 9.2175 | 8.4449 | 7.4349 | 10.6524 | 12.6524 | 9.2175 | 16.6524 | 27.3048 | 39.9572 | 0
7.869 | 9.9345 | 9.869 | 8.869 | 12.8035 | 14.8035 | 9.9345 | 18.8035 | 31.607 | 46.4105 | 7.869 | 9.9345 | 9.879 | 8.869 | 12.8035 | 14.8035 | 9.9345 | 18.8035 | 31.607 | 46.4105 | 0
6.7712 | 9.3856 | 8.7712 | 7.7712 | 11.1568 | 13.1568 | 9.3856 | 17.1568 | 28.3136 | 41.4704 | 6.7712 | 9.3856 | 8.7812 | 7.7712 | 11.1568 | 13.1568 | 9.3856 | 17.1568 | 28.3136 | 41.4704 | 0
8.0857 | 10.0429 | 10.0857 | 9.0857 | 13.1286 | 15.1286 | 10.0429 | 19.1286 | 32.2572 | 47.3859 | 8.0857 | 10.0429 | 10.0957 | 9.0857 | 13.1286 | 15.1286 | 10.0429 | 19.1286 | 32.2572 | 47.3859 | 0
7.7566 | 9.8783 | 9.7566 | 8.7566 | 12.6349 | 14.6349 | 9.8783 | 18.6349 | 31.2699 | 45.9048 | 7.7566 | 9.8783 | 9.7666 | 8.7566 | 12.6349 | 14.6349 | 9.8783 | 18.6349 | 31.2699 | 45.9048 | 0
9.6525 | 10.8263 | 11.6525 | 10.6525 | 15.4788 | 17.4788 | 10.8263 | 21.4788 | 36.9575 | 54.4363 | 9.6525 | 10.8263 | 11.6625 | 10.6525 | 15.4788 | 17.4788 | 10.8263 | 21.4788 | 36.9575 | 54.4363 | 0
7.2986 | 9.6493 | 9.2986 | 8.2986 | 11.948 | 13.948 | 9.6493 | 17.948 | 29.8959 | 43.8439 | 7.2986 | 9.6493 | 9.3086 | 8.2986 | 11.948 | 13.948 | 9.6493 | 17.948 | 29.8959 | 43.8439 | 0
4.0521 | 8.0261 | 6.0521 | 5.0521 | 7.0782 | 9.0782 | 8.0261 | 13.0782 | 20.1564 | 29.2346 | 4.0521 | 8.0261 | 6.0621 | 5.0521 | 7.0782 | 9.0782 | 8.0261 | 13.0782 | 20.1564 | 29.2346 | 0
7.0371 | 9.5185 | 9.0371 | 8.0371 | 11.5556 | 13.5556 | 9.5185 | 17.5556 | 29.1112 | 42.6668 | 7.0371 | 9.5185 | 9.0471 | 8.0371 | 11.5556 | 13.5556 | 9.5185 | 17.5556 | 29.1112 | 42.6668 | 0
2.233 | 7.1165 | 4.233 | 3.233 | 4.3495 | 6.3495 | 7.1165 | 10.3495 | 14.6991 | 21.0486 | 2.233 | 7.1165 | 4.243 | 3.233 | 4.3495 | 6.3495 | 7.1165 | 10.3495 | 14.6991 | 21.0486 | 0
7.2275 | 9.6137 | 9.2275 | 8.2275 | 11.8412 | 13.8412 | 9.6137 | 17.8412 | 29.6825 | 43.5237 | 7.2275 | 9.6137 | 9.2375 | 8.2275 | 11.8412 | 13.8412 | 9.6137 | 17.8412 | 29.6825 | 43.5237 | 0
6.3896 | 9.1948 | 8.3896 | 7.3896 | 10.5844 | 12.5844 | 9.1948 | 16.5844 | 27.1688 | 39.7532 | 6.3896 | 9.1948 | 8.3996 | 7.3896 | 10.5844 | 12.5844 | 9.1948 | 16.5844 | 27.1688 | 39.7532 | 0
6.4116 | 9.2058 | 8.4116 | 7.4116 | 10.6174 | 12.6174 | 9.2058 | 16.6174 | 27.2349 | 39.8523 | 6.4116 | 9.2058 | 8.4216 | 7.4116 | 10.6174 | 12.6174 | 9.2058 | 16.6174 | 27.2349 | 39.8523 | 0
4.7322 | 8.3661 | 6.7322 | 5.7322 | 8.0983 | 10.0983 | 8.3661 | 14.0983 | 22.1965 | 32.2948 | 4.7322 | 8.3661 | 6.7422 | 5.7322 | 8.0983 | 10.0983 | 8.3661 | 14.0983 | 22.1965 | 32.2948 | 0
6.7518 | 9.3759 | 8.7518 | 7.7518 | 11.1277 | 13.1277 | 9.3759 | 17.1277 | 28.2554 | 41.3831 | 6.7518 | 9.3759 | 8.7618 | 7.7518 | 11.1277 | 13.1277 | 9.3759 | 17.1277 | 28.2554 | 41.3831 | 0
4.1562 | 8.0781 | 6.1562 | 5.1562 | 7.2343 | 9.2343 | 8.0781 | 13.2343 | 20.4686 | 29.7029 | 4.1562 | 8.0781 | 6.1662 | 5.1562 | 7.2343 | 9.2343 | 8.0781 | 13.2343 | 20.4686 | 29.7029 | 0
3.8186 | 7.9093 | 5.8186 | 4.8186 | 6.7279 | 8.7279 | 7.9093 | 12.7279 | 19.4557 | 28.1836 | 3.8186 | 7.9093 | 5.8286 | 4.8186 | 6.7279 | 8.7279 | 7.9093 | 12.7279 | 19.4557 | 28.1836 | 0
4.9033 | 8.4517 | 6.9033 | 5.9033 | 8.355 | 10.355 | 8.4517 | 14.355 | 22.7099 | 33.0649 | 4.9033 | 8.4517 | 6.9133 | 5.9033 | 8.355 | 10.355 | 8.4517 | 14.355 | 22.7099 | 33.0649 | 0
3.8613 | 7.9307 | 5.8613 | 4.8613 | 6.792 | 8.792 | 7.9307 | 12.792 | 19.584 | 28.376 | 3.8613 | 7.9307 | 5.8713 | 4.8613 | 6.792 | 8.792 | 7.9307 | 12.792 | 19.584 | 28.376 | 0
8.8507 | 10.4253 | 10.8507 | 9.8507 | 14.276 | 16.276 | 10.4253 | 20.276 | 34.5521 | 50.8281 | 8.8507 | 10.4253 | 10.8607 | 9.8507 | 14.276 | 16.276 | 10.4253 | 20.276 | 34.5521 | 50.8281 | 0
4.7771 | 8.3886 | 6.7771 | 5.7771 | 8.1657 | 10.1657 | 8.3886 | 14.1657 | 22.3314 | 32.4971 | 4.7771 | 8.3886 | 6.7871 | 5.7771 | 8.1657 | 10.1657 | 8.3886 | 14.1657 | 22.3314 | 32.4971 | 0
6.5063 | 9.2532 | 8.5063 | 7.5063 | 10.7595 | 12.7595 | 9.2532 | 16.7595 | 27.519 | 40.2786 | 6.5063 | 9.2532 | 8.5163 | 7.5063 | 10.7595 | 12.7595 | 9.2532 | 16.7595 | 27.519 | 40.2786 | 0
6.9271 | 9.4636 | 8.9271 | 7.9271 | 11.3907 | 13.3907 | 9.4636 | 17.3907 | 28.7813 | 42.172 | 6.9271 | 9.4636 | 8.9371 | 7.9271 | 11.3907 | 13.3907 | 9.4636 | 17.3907 | 28.7813 | 42.172 | 0
4.2626 | 8.1313 | 6.2626 | 5.2626 | 7.394 | 9.394 | 8.1313 | 13.394 | 20.7879 | 30.1819 | 4.2626 | 8.1313 | 6.2726 | 5.2626 | 7.394 | 9.394 | 8.1313 | 13.394 | 20.7879 | 30.1819 | 0
2.6952 | 7.3476 | 4.6952 | 3.6952 | 5.0428 | 7.0428 | 7.3476 | 11.0428 | 16.0856 | 23.1284 | 2.6952 | 7.3476 | 4.7052 | 3.6952 | 5.0428 | 7.0428 | 7.3476 | 11.0428 | 16.0856 | 23.1284 | 0
7.9818 | 9.9909 | 9.9818 | 8.9818 | 12.9728 | 14.9728 | 9.9909 | 18.9728 | 31.9455 | 46.9183 | 7.9818 | 9.9909 | 9.9918 | 8.9818 | 12.9728 | 14.9728 | 9.9909 | 18.9728 | 31.9455 | 46.9183 | 0
4.4602 | 8.2301 | 6.4602 | 5.4602 | 7.6903 | 9.6903 | 8.2301 | 13.6903 | 21.3806 | 31.0709 | 4.4602 | 8.2301 | 6.4702 | 5.4602 | 7.6903 | 9.6903 | 8.2301 | 13.6903 | 21.3806 | 31.0709 | 0
7.8904 | 9.9452 | 9.8904 | 8.8904 | 12.8356 | 14.8356 | 9.9452 | 18.8356 | 31.6712 | 46.5069 | 7.8904 | 9.9452 | 9.9004 | 8.8904 | 12.8356 | 14.8356 | 9.9452 | 18.8356 | 31.6712 | 46.5069 | 0
4.5586 | 8.2793 | 6.5586 | 5.5586 | 7.8379 | 9.8379 | 8.2793 | 13.8379 | 21.6757 | 31.5136 | 4.5586 | 8.2793 | 6.5686 | 5.5586 | 7.8379 | 9.8379 | 8.2793 | 13.8379 | 21.6757 | 31.5136 | 0
5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 5.3559 | 8.6779 | 7.3659 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 0
4.5162 | 8.2581 | 6.5162 | 5.5162 | 7.7743 | 9.7743 | 8.2581 | 13.7743 | 21.5486 | 31.3228 | 4.5162 | 8.2581 | 6.5262 | 5.5162 | 7.7743 | 9.7743 | 8.2581 | 13.7743 | 21.5486 | 31.3228 | 0
4.8841 | 8.442 | 6.8841 | 5.8841 | 8.3261 | 10.3261 | 8.442 | 14.3261 | 22.6522 | 32.9782 | 4.8841 | 8.442 | 6.8941 | 5.8841 | 8.3261 | 10.3261 | 8.442 | 14.3261 | 22.6522 | 32.9782 | 0
5.6401 | 8.8201 | 7.6401 | 6.6401 | 9.4602 | 11.4602 | 8.8201 | 15.4602 | 24.9204 | 36.3806 | 5.6401 | 8.8201 | 7.6501 | 6.6401 | 9.4602 | 11.4602 | 8.8201 | 15.4602 | 24.9204 | 36.3806 | 0
9.7333 | 10.8666 | 11.7333 | 10.7333 | 15.5999 | 17.5999 | 10.8666 | 21.5999 | 37.1998 | 54.7997 | 9.7333 | 10.8666 | 11.7433 | 10.7333 | 15.5999 | 17.5999 | 10.8666 | 21.5999 | 37.1998 | 54.7997 | 0
4.4464 | 8.2232 | 6.4464 | 5.4464 | 7.6696 | 9.6696 | 8.2232 | 13.6696 | 21.3391 | 31.0087 | 4.4464 | 8.2232 | 6.4564 | 5.4464 | 7.6696 | 9.6696 | 8.2232 | 13.6696 | 21.3391 | 31.0087 | 0
3.4011 | 7.7006 | 5.4011 | 4.4011 | 6.1017 | 8.1017 | 7.7006 | 12.1017 | 18.2034 | 26.305 | 3.4011 | 7.7006 | 5.4111 | 4.4011 | 6.1017 | 8.1017 | 7.7006 | 12.1017 | 18.2034 | 26.305 | 0
5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 5.2901 | 8.645 | 7.3001 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 0
2.1888 | 7.0944 | 4.1888 | 3.1888 | 4.2832 | 6.2832 | 7.0944 | 10.2832 | 14.5665 | 20.8497 | 2.1888 | 7.0944 | 4.1988 | 3.1888 | 4.2832 | 6.2832 | 7.0944 | 10.2832 | 14.5665 | 20.8497 | 0
6.8979 | 9.449 | 8.8979 | 7.8979 | 11.3469 | 13.3469 | 9.449 | 17.3469 | 28.6937 | 42.0406 | 6.8979 | 9.449 | 8.9079 | 7.8979 | 11.3469 | 13.3469 | 9.449 | 17.3469 | 28.6937 | 42.0406 | 0
4.4544 | 8.2272 | 6.4544 | 5.4544 | 7.6816 | 9.6816 | 8.2272 | 13.6816 | 21.3633 | 31.0449 | 4.4544 | 8.2272 | 6.4644 | 5.4544 | 7.6816 | 9.6816 | 8.2272 | 13.6816 | 21.3633 | 31.0449 | 0
5.3782 | 8.6891 | 7.3782 | 6.3782 | 9.0673 | 11.0673 | 8.6891 | 15.0673 | 24.1346 | 35.202 | 5.3782 | 8.6891 | 7.3882 | 6.3782 | 9.0673 | 11.0673 | 8.6891 | 15.0673 | 24.1346 | 35.202 | 0
4.8642 | 8.4321 | 6.8642 | 5.8642 | 8.2962 | 10.2962 | 8.4321 | 14.2962 | 22.5925 | 32.8887 | 4.8642 | 8.4321 | 6.8742 | 5.8642 | 8.2962 | 10.2962 | 8.4321 | 14.2962 | 22.5925 | 32.8887 | 0
6.4795 | 9.2398 | 8.4795 | 7.4795 | 10.7193 | 12.7193 | 9.2398 | 16.7193 | 27.4386 | 40.1579 | 6.4795 | 9.2398 | 8.4895 | 7.4795 | 10.7193 | 12.7193 | 9.2398 | 16.7193 | 27.4386 | 40.1579 | 0
6.2353 | 9.1177 | 8.2353 | 7.2353 | 10.353 | 12.353 | 9.1177 | 16.353 | 26.7059 | 39.0589 | 6.2353 | 9.1177 | 8.2453 | 7.2353 | 10.353 | 12.353 | 9.1177 | 16.353 | 26.7059 | 39.0589 | 0
6.6358 | 9.3179 | 8.6358 | 7.6358 | 10.9537 | 12.9537 | 9.3179 | 16.9537 | 27.9073 | 40.861 | 6.6358 | 9.3179 | 8.6458 | 7.6358 | 10.9537 | 12.9537 | 9.3179 | 16.9537 | 27.9073 | 40.861 | 0
5.2598 | 8.6299 | 7.2598 | 6.2598 | 8.8898 | 10.8898 | 8.6299 | 14.8898 | 23.7795 | 34.6693 | 5.2598 | 8.6299 | 7.2698 | 6.2598 | 8.8898 | 10.8898 | 8.6299 | 14.8898 | 23.7795 | 34.6693 | 0
5.8382 | 8.9191 | 7.8382 | 6.8382 | 9.7573 | 11.7573 | 8.9191 | 15.7573 | 25.5145 | 37.2718 | 5.8382 | 8.9191 | 7.8482 | 6.8382 | 9.7573 | 11.7573 | 8.9191 | 15.7573 | 25.5145 | 37.2718 | 0
3.6537 | 7.8268 | 5.6537 | 4.6537 | 6.4805 | 8.4805 | 7.8268 | 12.4805 | 18.961 | 27.4415 | 3.6537 | 7.8268 | 5.6637 | 4.6537 | 6.4805 | 8.4805 | 7.8268 | 12.4805 | 18.961 | 27.4415 | 0
10.3093 | 11.1546 | 12.3093 | 11.3093 | 16.4639 | 18.4639 | 11.1546 | 22.4639 | 38.9278 | 57.3917 | 10.3093 | 11.1546 | 12.3193 | 11.3093 | 16.4639 | 18.4639 | 11.1546 | 22.4639 | 38.9278 | 57.3917 | 0
2.9072 | 7.4536 | 4.9072 | 3.9072 | 5.3609 | 7.3609 | 7.4536 | 11.3609 | 16.7217 | 24.0826 | 2.9072 | 7.4536 | 4.9172 | 3.9072 | 5.3609 | 7.3609 | 7.4536 | 11.3609 | 16.7217 | 24.0826 | 0
8.8398 | 10.4199 | 10.8398 | 9.8398 | 14.2596 | 16.2596 | 10.4199 | 20.2596 | 34.5193 | 50.7789 | 8.8398 | 10.4199 | 10.8498 | 9.8398 | 14.2596 | 16.2596 | 10.4199 | 20.2596 | 34.5193 | 50.7789 | 0
4.7994 | 8.3997 | 6.7994 | 5.7994 | 8.1991 | 10.1991 | 8.3997 | 14.1991 | 22.3981 | 32.5972 | 4.7994 | 8.3997 | 6.8094 | 5.7994 | 8.1991 | 10.1991 | 8.3997 | 14.1991 | 22.3981 | 32.5972 | 0
4.8728 | 8.4364 | 6.8728 | 5.8728 | 8.3092 | 10.3092 | 8.4364 | 14.3092 | 22.6183 | 32.9275 | 4.8728 | 8.4364 | 6.8828 | 5.8728 | 8.3092 | 10.3092 | 8.4364 | 14.3092 | 22.6183 | 32.9275 | 0
8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 8.8231 | 10.4115 | 10.8331 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 0
8.2877 | 10.1438 | 10.2877 | 9.2877 | 13.4315 | 15.4315 | 10.1438 | 19.4315 | 32.863 | 48.2945 | 8.2877 | 10.1438 | 10.2977 | 9.2877 | 13.4315 | 15.4315 | 10.1438 | 19.4315 | 32.863 | 48.2945 | 0
5.1521 | 8.576 | 7.1521 | 6.1521 | 8.7281 | 10.7281 | 8.576 | 14.7281 | 23.4562 | 34.1843 | 5.1521 | 8.576 | 7.1621 | 6.1521 | 8.7281 | 10.7281 | 8.576 | 14.7281 | 23.4562 | 34.1843 | 0
7.8614 | 9.9307 | 9.8614 | 8.8614 | 12.7921 | 14.7921 | 9.9307 | 18.7921 | 31.5843 | 46.3764 | 7.8614 | 9.9307 | 9.8714 | 8.8614 | 12.7921 | 14.7921 | 9.9307 | 18.7921 | 31.5843 | 46.3764 | 0
7.2199 | 9.61 | 9.2199 | 8.2199 | 11.8299 | 13.8299 | 9.61 | 17.8299 | 29.6598 | 43.4897 | 7.2199 | 9.61 | 9.2299 | 8.2199 | 11.8299 | 13.8299 | 9.61 | 17.8299 | 29.6598 | 43.4897 | 0
5.6179 | 8.8089 | 7.6179 | 6.6179 | 9.4268 | 11.4268 | 8.8089 | 15.4268 | 24.8536 | 36.2804 | 5.6179 | 8.8089 | 7.6279 | 6.6179 | 9.4268 | 11.4268 | 8.8089 | 15.4268 | 24.8536 | 36.2804 | 0
2.7189 | 7.3595 | 4.7189 | 3.7189 | 5.0784 | 7.0784 | 7.3595 | 11.0784 | 16.1568 | 23.2352 | 2.7189 | 7.3595 | 4.7289 | 3.7189 | 5.0784 | 7.0784 | 7.3595 | 11.0784 | 16.1568 | 23.2352 | 0
7.0937 | 9.5468 | 9.0937 | 8.0937 | 11.6405 | 13.6405 | 9.5468 | 17.6405 | 29.281 | 42.9215 | 7.0937 | 9.5468 | 9.1037 | 8.0937 | 11.6405 | 13.6405 | 9.5468 | 17.6405 | 29.281 | 42.9215 | 0
6.5789 | 9.2894 | 8.5789 | 7.5789 | 10.8683 | 12.8683 | 9.2894 | 16.8683 | 27.7367 | 40.605 | 6.5789 | 9.2894 | 8.5889 | 7.5789 | 10.8683 | 12.8683 | 9.2894 | 16.8683 | 27.7367 | 40.605 | 0
4.9738 | 8.4869 | 6.9738 | 5.9738 | 8.4606 | 10.4606 | 8.4869 | 14.4606 | 22.9213 | 33.3819 | 4.9738 | 8.4869 | 6.9838 | 5.9738 | 8.4606 | 10.4606 | 8.4869 | 14.4606 | 22.9213 | 33.3819 | 0
5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 5.3943 | 8.6971 | 7.4043 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 0
3.3249 | 7.6624 | 5.3249 | 4.3249 | 5.9873 | 7.9873 | 7.6624 | 11.9873 | 17.9746 | 25.9618 | 3.3249 | 7.6624 | 5.3349 | 4.3249 | 5.9873 | 7.9873 | 7.6624 | 11.9873 | 17.9746 | 25.9618 | 0
5.9637 | 8.9818 | 7.9637 | 6.9637 | 9.9455 | 11.9455 | 8.9818 | 15.9455 | 25.891 | 37.8365 | 5.9637 | 8.9818 | 7.9737 | 6.9637 | 9.9455 | 11.9455 | 8.9818 | 15.9455 | 25.891 | 37.8365 | 0
3.7881 | 7.894 | 5.7881 | 4.7881 | 6.6821 | 8.6821 | 7.894 | 12.6821 | 19.3643 | 28.0464 | 3.7881 | 7.894 | 5.7981 | 4.7881 | 6.6821 | 8.6821 | 7.894 | 12.6821 | 19.3643 | 28.0464 | 0
8.004 | 10.002 | 10.004 | 9.004 | 13.0059 | 15.0059 | 10.002 | 19.0059 | 32.0119 | 47.0178 | 8.004 | 10.002 | 10.014 | 9.004 | 13.0059 | 15.0059 | 10.002 | 19.0059 | 32.0119 | 47.0178 | 0
7.6199 | 9.8099 | 9.6199 | 8.6199 | 12.4298 | 14.4298 | 9.8099 | 18.4298 | 30.8596 | 45.2893 | 7.6199 | 9.8099 | 9.6299 | 8.6199 | 12.4298 | 14.4298 | 9.8099 | 18.4298 | 30.8596 | 45.2893 | 0
5.0882 | 8.5441 | 7.0882 | 6.0882 | 8.6323 | 10.6323 | 8.5441 | 14.6323 | 23.2646 | 33.8968 | 5.0882 | 8.5441 | 7.0982 | 6.0882 | 8.6323 | 10.6323 | 8.5441 | 14.6323 | 23.2646 | 33.8968 | 0
4.9297 | 8.4649 | 6.9297 | 5.9297 | 8.3946 | 10.3946 | 8.4649 | 14.3946 | 22.7891 | 33.1837 | 4.9297 | 8.4649 | 6.9397 | 5.9297 | 8.3946 | 10.3946 | 8.4649 | 14.3946 | 22.7891 | 33.1837 | 0
1.9638 | 6.9819 | 3.9638 | 2.9638 | 3.9457 | 5.9457 | 6.9819 | 9.9457 | 13.8914 | 19.8371 | 1.9638 | 6.9819 | 3.9738 | 2.9638 | 3.9457 | 5.9457 | 6.9819 | 9.9457 | 13.8914 | 19.8371 | 0
5.227 | 8.6135 | 7.227 | 6.227 | 8.8405 | 10.8405 | 8.6135 | 14.8405 | 23.6809 | 34.5214 | 5.227 | 8.6135 | 7.237 | 6.227 | 8.8405 | 10.8405 | 8.6135 | 14.8405 | 23.6809 | 34.5214 | 0
2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 2.9838 | 7.4919 | 4.9938 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 0
6.9433 | 9.4717 | 8.9433 | 7.9433 | 11.415 | 13.415 | 9.4717 | 17.415 | 28.83 | 42.245 | 6.9433 | 9.4717 | 8.9533 | 7.9433 | 11.415 | 13.415 | 9.4717 | 17.415 | 28.83 | 42.245 | 0
5.765 | 8.8825 | 7.765 | 6.765 | 9.6475 | 11.6475 | 8.8825 | 15.6475 | 25.295 | 36.9425 | 5.765 | 8.8825 | 7.775 | 6.765 | 9.6475 | 11.6475 | 8.8825 | 15.6475 | 25.295 | 36.9425 | 0
2.6494 | 7.3247 | 4.6494 | 3.6494 | 4.9741 | 6.9741 | 7.3247 | 10.9741 | 15.9482 | 22.9223 | 2.6494 | 7.3247 | 4.6594 | 3.6494 | 4.9741 | 6.9741 | 7.3247 | 10.9741 | 15.9482 | 22.9223 | 0
7.3038 | 9.6519 | 9.3038 | 8.3038 | 11.9556 | 13.9556 | 9.6519 | 17.9556 | 29.9113 | 43.8669 | 7.3038 | 9.6519 | 9.3138 | 8.3038 | 11.9556 | 13.9556 | 9.6519 | 17.9556 | 29.9113 | 43.8669 | 0
3.554 | 7.777 | 5.554 | 4.554 | 6.3309 | 8.3309 | 7.777 | 12.3309 | 18.6619 | 26.9928 | 3.554 | 7.777 | 5.564 | 4.554 | 6.3309 | 8.3309 | 7.777 | 12.3309 | 18.6619 | 26.9928 | 0
5.9113 | 8.9557 | 7.9113 | 6.9113 | 9.867 | 11.867 | 8.9557 | 15.867 | 25.7339 | 37.6009 | 5.9113 | 8.9557 | 7.9213 | 6.9113 | 9.867 | 11.867 | 8.9557 | 15.867 | 25.7339 | 37.6009 | 0
8.773 | 10.3865 | 10.773 | 9.773 | 14.1595 | 16.1595 | 10.3865 | 20.1595 | 34.319 | 50.4785 | 8.773 | 10.3865 | 10.783 | 9.773 | 14.1595 | 16.1595 | 10.3865 | 20.1595 | 34.319 | 50.4785 | 0
6.175 | 9.0875 | 8.175 | 7.175 | 10.2625 | 12.2625 | 9.0875 | 16.2625 | 26.5251 | 38.7876 | 6.175 | 9.0875 | 8.185 | 7.175 | 10.2625 | 12.2625 | 9.0875 | 16.2625 | 26.5251 | 38.7876 | 0
7.0464 | 9.5232 | 9.0464 | 8.0464 | 11.5695 | 13.5695 | 9.5232 | 17.5695 | 29.1391 | 42.7086 | 7.0464 | 9.5232 | 9.0564 | 8.0464 | 11.5695 | 13.5695 | 9.5232 | 17.5695 | 29.1391 | 42.7086 | 0
4.9413 | 8.4707 | 6.9413 | 5.9413 | 8.412 | 10.412 | 8.4707 | 14.412 | 22.824 | 33.236 | 4.9413 | 8.4707 | 6.9513 | 5.9413 | 8.412 | 10.412 | 8.4707 | 14.412 | 22.824 | 33.236 | 0
4.8679 | 8.434 | 6.8679 | 5.8679 | 8.3019 | 10.3019 | 8.434 | 14.3019 | 22.6038 | 32.9057 | 4.8679 | 8.434 | 6.8779 | 5.8679 | 8.3019 | 10.3019 | 8.434 | 14.3019 | 22.6038 | 32.9057 | 0
4.8742 | 8.4371 | 6.8742 | 5.8742 | 8.3113 | 10.3113 | 8.4371 | 14.3113 | 22.6226 | 32.9339 | 4.8742 | 8.4371 | 6.8842 | 5.8742 | 8.3113 | 10.3113 | 8.4371 | 14.3113 | 22.6226 | 32.9339 | 0
9.329 | 10.6645 | 11.329 | 10.329 | 14.9935 | 16.9935 | 10.6645 | 20.9935 | 35.987 | 52.9806 | 9.329 | 10.6645 | 11.339 | 10.329 | 14.9935 | 16.9935 | 10.6645 | 20.9935 | 35.987 | 52.9806 | 0
7.5224 | 9.7612 | 9.5224 | 8.5224 | 12.2836 | 14.2836 | 9.7612 | 18.2836 | 30.5671 | 44.8507 | 7.5224 | 9.7612 | 9.5324 | 8.5224 | 12.2836 | 14.2836 | 9.7612 | 18.2836 | 30.5671 | 44.8507 | 0
8.1979 | 10.0989 | 10.1979 | 9.1979 | 13.2968 | 15.2968 | 10.0989 | 19.2968 | 32.5936 | 47.8904 | 8.1979 | 10.0989 | 10.2079 | 9.1979 | 13.2968 | 15.2968 | 10.0989 | 19.2968 | 32.5936 | 47.8904 | 0
5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 5.2196 | 8.6098 | 7.2296 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 0
8.1953 | 10.0977 | 10.1953 | 9.1953 | 13.293 | 15.293 | 10.0977 | 19.293 | 32.586 | 47.8791 | 8.1953 | 10.0977 | 10.2053 | 9.1953 | 13.293 | 15.293 | 10.0977 | 19.293 | 32.586 | 47.8791 | 0
4.9143 | 8.4572 | 6.9143 | 5.9143 | 8.3715 | 10.3715 | 8.4572 | 14.3715 | 22.7429 | 33.1144 | 4.9143 | 8.4572 | 6.9243 | 5.9143 | 8.3715 | 10.3715 | 8.4572 | 14.3715 | 22.7429 | 33.1144 | 0
8.9991 | 10.4995 | 10.9991 | 9.9991 | 14.4986 | 16.4986 | 10.4995 | 20.4986 | 34.9973 | 51.4959 | 8.9991 | 10.4995 | 11.0091 | 9.9991 | 14.4986 | 16.4986 | 10.4995 | 20.4986 | 34.9973 | 51.4959 | 0
3.9365 | 7.9683 | 5.9365 | 4.9365 | 6.9048 | 8.9048 | 7.9683 | 12.9048 | 19.8096 | 28.7143 | 3.9365 | 7.9683 | 5.9465 | 4.9365 | 6.9048 | 8.9048 | 7.9683 | 12.9048 | 19.8096 | 28.7143 | 0
7.8134 | 9.9067 | 9.8134 | 8.8134 | 12.7201 | 14.7201 | 9.9067 | 18.7201 | 31.4401 | 46.1602 | 7.8134 | 9.9067 | 9.8234 | 8.8134 | 12.7201 | 14.7201 | 9.9067 | 18.7201 | 31.4401 | 46.1602 | 0
4.0634 | 8.0317 | 6.0634 | 5.0634 | 7.0951 | 9.0951 | 8.0317 | 13.0951 | 20.1902 | 29.2853 | 4.0634 | 8.0317 | 6.0734 | 5.0634 | 7.0951 | 9.0951 | 8.0317 | 13.0951 | 20.1902 | 29.2853 | 0
6.7403 | 9.3702 | 8.7403 | 7.7403 | 11.1105 | 13.1105 | 9.3702 | 17.1105 | 28.221 | 41.3314 | 6.7403 | 9.3702 | 8.7503 | 7.7403 | 11.1105 | 13.1105 | 9.3702 | 17.1105 | 28.221 | 41.3314 | 0
5.6408 | 8.8204 | 7.6408 | 6.6408 | 9.4611 | 11.4611 | 8.8204 | 15.4611 | 24.9223 | 36.3834 | 5.6408 | 8.8204 | 7.6508 | 6.6408 | 9.4611 | 11.4611 | 8.8204 | 15.4611 | 24.9223 | 36.3834 | 0
6.2507 | 9.1254 | 8.2507 | 7.2507 | 10.3761 | 12.3761 | 9.1254 | 16.3761 | 26.7522 | 39.1283 | 6.2507 | 9.1254 | 8.2607 | 7.2507 | 10.3761 | 12.3761 | 9.1254 | 16.3761 | 26.7522 | 39.1283 | 0
8.3342 | 10.1671 | 10.3342 | 9.3342 | 13.5013 | 15.5013 | 10.1671 | 19.5013 | 33.0026 | 48.5039 | 8.3342 | 10.1671 | 10.3442 | 9.3342 | 13.5013 | 15.5013 | 10.1671 | 19.5013 | 33.0026 | 48.5039 | 0
9.8378 | 10.9189 | 11.8378 | 10.8378 | 15.7567 | 17.7567 | 10.9189 | 21.7567 | 37.5135 | 55.2702 | 9.8378 | 10.9189 | 11.8478 | 10.8378 | 15.7567 | 17.7567 | 10.9189 | 21.7567 | 37.5135 | 55.2702 | 0
5.9193 | 8.9596 | 7.9193 | 6.9193 | 9.8789 | 11.8789 | 8.9596 | 15.8789 | 25.7578 | 37.6367 | 5.9193 | 8.9596 | 7.9293 | 6.9193 | 9.8789 | 11.8789 | 8.9596 | 15.8789 | 25.7578 | 37.6367 | 0
9.7806 | 10.8903 | 11.7806 | 10.7806 | 15.6709 | 17.6709 | 10.8903 | 21.6709 | 37.3418 | 55.0127 | 9.7806 | 10.8903 | 11.7906 | 10.7806 | 15.6709 | 17.6709 | 10.8903 | 21.6709 | 37.3418 | 55.0127 | 0
7.2998 | 9.6499 | 9.2998 | 8.2998 | 11.9497 | 13.9497 | 9.6499 | 17.9497 | 29.8993 | 43.849 | 7.2998 | 9.6499 | 9.3098 | 8.2998 | 11.9497 | 13.9497 | 9.6499 | 17.9497 | 29.8993 | 43.849 | 0
5.2258 | 8.6129 | 7.2258 | 6.2258 | 8.8387 | 10.8387 | 8.6129 | 14.8387 | 23.6775 | 34.5162 | 5.2258 | 8.6129 | 7.2358 | 6.2258 | 8.8387 | 10.8387 | 8.6129 | 14.8387 | 23.6775 | 34.5162 | 0
5.5571 | 8.7785 | 7.5571 | 6.5571 | 9.3356 | 11.3356 | 8.7785 | 15.3356 | 24.6712 | 36.0068 | 5.5571 | 8.7785 | 7.5671 | 6.5571 | 9.3356 | 11.3356 | 8.7785 | 15.3356 | 24.6712 | 36.0068 | 0
3.6445 | 7.8223 | 5.6445 | 4.6445 | 6.4668 | 8.4668 | 7.8223 | 12.4668 | 18.9335 | 27.4003 | 3.6445 | 7.8223 | 5.6545 | 4.6445 | 6.4668 | 8.4668 | 7.8223 | 12.4668 | 18.9335 | 27.4003 | 0
4.0026 | 8.0013 | 6.0026 | 5.0026 | 7.0039 | 9.0039 | 8.0013 | 13.0039 | 20.0078 | 29.0117 | 4.0026 | 8.0013 | 6.0126 | 5.0026 | 7.0039 | 9.0039 | 8.0013 | 13.0039 | 20.0078 | 29.0117 | 0
6.0532 | 9.0266 | 8.0532 | 7.0532 | 10.0798 | 12.0798 | 9.0266 | 16.0798 | 26.1595 | 38.2393 | 6.0532 | 9.0266 | 8.0632 | 7.0532 | 10.0798 | 12.0798 | 9.0266 | 16.0798 | 26.1595 | 38.2393 | 0
6.9761 | 9.4881 | 8.9761 | 7.9761 | 11.4642 | 13.4642 | 9.4881 | 17.4642 | 28.9284 | 42.3925 | 6.9761 | 9.4881 | 8.9861 | 7.9761 | 11.4642 | 13.4642 | 9.4881 | 17.4642 | 28.9284 | 42.3925 | 0
2.4113 | 7.2056 | 4.4113 | 3.4113 | 4.6169 | 6.6169 | 7.2056 | 10.6169 | 15.2338 | 21.8508 | 2.4113 | 7.2056 | 4.4213 | 3.4113 | 4.6169 | 6.6169 | 7.2056 | 10.6169 | 15.2338 | 21.8508 | 0
3.7525 | 7.8762 | 5.7525 | 4.7525 | 6.6287 | 8.6287 | 7.8762 | 12.6287 | 19.2575 | 27.8862 | 3.7525 | 7.8762 | 5.7625 | 4.7525 | 6.6287 | 8.6287 | 7.8762 | 12.6287 | 19.2575 | 27.8862 | 0
6.4384 | 9.2192 | 8.4384 | 7.4384 | 10.6576 | 12.6576 | 9.2192 | 16.6576 | 27.3151 | 39.9727 | 6.4384 | 9.2192 | 8.4484 | 7.4384 | 10.6576 | 12.6576 | 9.2192 | 16.6576 | 27.3151 | 39.9727 | 0
1.4433 | 6.7216 | 3.4433 | 2.4433 | 3.1649 | 5.1649 | 6.7216 | 9.1649 | 12.3299 | 17.4948 | 1.4433 | 6.7216 | 3.4533 | 2.4433 | 3.1649 | 5.1649 | 6.7216 | 9.1649 | 12.3299 | 17.4948 | 0
7.9113 | 9.9557 | 9.9113 | 8.9113 | 12.867 | 14.867 | 9.9557 | 18.867 | 31.734 | 46.6009 | 7.9113 | 9.9557 | 9.9213 | 8.9113 | 12.867 | 14.867 | 9.9557 | 18.867 | 31.734 | 46.6009 | 0
4.1557 | 8.0779 | 6.1557 | 5.1557 | 7.2336 | 9.2336 | 8.0779 | 13.2336 | 20.4672 | 29.7007 | 4.1557 | 8.0779 | 6.1657 | 5.1557 | 7.2336 | 9.2336 | 8.0779 | 13.2336 | 20.4672 | 29.7007 | 0
9.7438 | 10.8719 | 11.7438 | 10.7438 | 15.6157 | 17.6157 | 10.8719 | 21.6157 | 37.2314 | 54.8471 | 9.7438 | 10.8719 | 11.7538 | 10.7438 | 15.6157 | 17.6157 | 10.8719 | 21.6157 | 37.2314 | 54.8471 | 0
8.0146 | 10.0073 | 10.0146 | 9.0146 | 13.0219 | 15.0219 | 10.0073 | 19.0219 | 32.0438 | 47.0657 | 8.0146 | 10.0073 | 10.0246 | 9.0146 | 13.0219 | 15.0219 | 10.0073 | 19.0219 | 32.0438 | 47.0657 | 0
7.2032 | 9.6016 | 9.2032 | 8.2032 | 11.8048 | 13.8048 | 9.6016 | 17.8048 | 29.6096 | 43.4144 | 7.2032 | 9.6016 | 9.2132 | 8.2032 | 11.8048 | 13.8048 | 9.6016 | 17.8048 | 29.6096 | 43.4144 | 0
5.1038 | 8.5519 | 7.1038 | 6.1038 | 8.6557 | 10.6557 | 8.5519 | 14.6557 | 23.3113 | 33.967 | 5.1038 | 8.5519 | 7.1138 | 6.1038 | 8.6557 | 10.6557 | 8.5519 | 14.6557 | 23.3113 | 33.967 | 0
10.3046 | 11.1523 | 12.3046 | 11.3046 | 16.4569 | 18.4569 | 11.1523 | 22.4569 | 38.9138 | 57.3707 | 10.3046 | 11.1523 | 12.3146 | 11.3046 | 16.4569 | 18.4569 | 11.1523 | 22.4569 | 38.9138 | 57.3707 | 0
6.0128 | 9.0064 | 8.0128 | 7.0128 | 10.0192 | 12.0192 | 9.0064 | 16.0192 | 26.0383 | 38.0575 | 6.0128 | 9.0064 | 8.0228 | 7.0128 | 10.0192 | 12.0192 | 9.0064 | 16.0192 | 26.0383 | 38.0575 | 0
5.3452 | 8.6726 | 7.3452 | 6.3452 | 9.0178 | 11.0178 | 8.6726 | 15.0178 | 24.0356 | 35.0535 | 5.3452 | 8.6726 | 7.3552 | 6.3452 | 9.0178 | 11.0178 | 8.6726 | 15.0178 | 24.0356 | 35.0535 | 0
5.0104 | 8.5052 | 7.0104 | 6.0104 | 8.5156 | 10.5156 | 8.5052 | 14.5156 | 23.0312 | 33.5469 | 5.0104 | 8.5052 | 7.0204 | 6.0104 | 8.5156 | 10.5156 | 8.5052 | 14.5156 | 23.0312 | 33.5469 | 0
8.5886 | 10.2943 | 10.5886 | 9.5886 | 13.8829 | 15.8829 | 10.2943 | 19.8829 | 33.7658 | 49.6487 | 8.5886 | 10.2943 | 10.5986 | 9.5886 | 13.8829 | 15.8829 | 10.2943 | 19.8829 | 33.7658 | 49.6487 | 0
4.7374 | 8.3687 | 6.7374 | 5.7374 | 8.1061 | 10.1061 | 8.3687 | 14.1061 | 22.2122 | 32.3184 | 4.7374 | 8.3687 | 6.7474 | 5.7374 | 8.1061 | 10.1061 | 8.3687 | 14.1061 | 22.2122 | 32.3184 | 0
4.205 | 8.1025 | 6.205 | 5.205 | 7.3075 | 9.3075 | 8.1025 | 13.3075 | 20.6151 | 29.9226 | 4.205 | 8.1025 | 6.215 | 5.205 | 7.3075 | 9.3075 | 8.1025 | 13.3075 | 20.6151 | 29.9226 | 0
6.7811 | 9.3906 | 8.7811 | 7.7811 | 11.1717 | 13.1717 | 9.3906 | 17.1717 | 28.3433 | 41.515 | 6.7811 | 9.3906 | 8.7911 | 7.7811 | 11.1717 | 13.1717 | 9.3906 | 17.1717 | 28.3433 | 41.515 | 0
5.058 | 8.529 | 7.058 | 6.058 | 8.5871 | 10.5871 | 8.529 | 14.5871 | 23.1741 | 33.7612 | 5.058 | 8.529 | 7.068 | 6.058 | 8.5871 | 10.5871 | 8.529 | 14.5871 | 23.1741 | 33.7612 | 0
5.1781 | 8.5891 | 7.1781 | 6.1781 | 8.7672 | 10.7672 | 8.5891 | 14.7672 | 23.5343 | 34.3015 | 5.1781 | 8.5891 | 7.1881 | 6.1781 | 8.7672 | 10.7672 | 8.5891 | 14.7672 | 23.5343 | 34.3015 | 0
2.0437 | 7.0219 | 4.0437 | 3.0437 | 4.0656 | 6.0656 | 7.0219 | 10.0656 | 14.1312 | 20.1968 | 2.0437 | 7.0219 | 4.0537 | 3.0437 | 4.0656 | 6.0656 | 7.0219 | 10.0656 | 14.1312 | 20.1968 | 0
7.546 | 9.773 | 9.546 | 8.546 | 12.319 | 14.319 | 9.773 | 18.319 | 30.6379 | 44.9569 | 7.546 | 9.773 | 9.556 | 8.546 | 12.319 | 14.319 | 9.773 | 18.319 | 30.6379 | 44.9569 | 0
5.6743 | 8.8371 | 7.6743 | 6.6743 | 9.5114 | 11.5114 | 8.8371 | 15.5114 | 25.0229 | 36.5343 | 5.6743 | 8.8371 | 7.6843 | 6.6743 | 9.5114 | 11.5114 | 8.8371 | 15.5114 | 25.0229 | 36.5343 | 0
4.0812 | 8.0406 | 6.0812 | 5.0812 | 7.1218 | 9.1218 | 8.0406 | 13.1218 | 20.2435 | 29.3653 | 4.0812 | 8.0406 | 6.0912 | 5.0812 | 7.1218 | 9.1218 | 8.0406 | 13.1218 | 20.2435 | 29.3653 | 0
9.5518 | 10.7759 | 11.5518 | 10.5518 | 15.3277 | 17.3277 | 10.7759 | 21.3277 | 36.6555 | 53.9832 | 9.5518 | 10.7759 | 11.5618 | 10.5518 | 15.3277 | 17.3277 | 10.7759 | 21.3277 | 36.6555 | 53.9832 | 0
7.9334 | 9.9667 | 9.9334 | 8.9334 | 12.9001 | 14.9001 | 9.9667 | 18.9001 | 31.8003 | 46.7004 | 7.9334 | 9.9667 | 9.9434 | 8.9334 | 12.9001 | 14.9001 | 9.9667 | 18.9001 | 31.8003 | 46.7004 | 0
4.7753 | 8.3876 | 6.7753 | 5.7753 | 8.1629 | 10.1629 | 8.3876 | 14.1629 | 22.3258 | 32.4888 | 4.7753 | 8.3876 | 6.7853 | 5.7753 | 8.1629 | 10.1629 | 8.3876 | 14.1629 | 22.3258 | 32.4888 | 0
8.5211 | 10.2606 | 10.5211 | 9.5211 | 13.7817 | 15.7817 | 10.2606 | 19.7817 | 33.5634 | 49.3451 | 8.5211 | 10.2606 | 10.5311 | 9.5211 | 13.7817 | 15.7817 | 10.2606 | 19.7817 | 33.5634 | 49.3451 | 0
5.7198 | 8.8599 | 7.7198 | 6.7198 | 9.5797 | 11.5797 | 8.8599 | 15.5797 | 25.1594 | 36.7391 | 5.7198 | 8.8599 | 7.7298 | 6.7198 | 9.5797 | 11.5797 | 8.8599 | 15.5797 | 25.1594 | 36.7391 | 0
4.9962 | 8.4981 | 6.9962 | 5.9962 | 8.4943 | 10.4943 | 8.4981 | 14.4943 | 22.9886 | 33.4829 | 4.9962 | 8.4981 | 7.0062 | 5.9962 | 8.4943 | 10.4943 | 8.4981 | 14.4943 | 22.9886 | 33.4829 | 0
5.1437 | 8.5718 | 7.1437 | 6.1437 | 8.7155 | 10.7155 | 8.5718 | 14.7155 | 23.4311 | 34.1466 | 5.1437 | 8.5718 | 7.1537 | 6.1437 | 8.7155 | 10.7155 | 8.5718 | 14.7155 | 23.4311 | 34.1466 | 0
5.9165 | 8.9583 | 7.9165 | 6.9165 | 9.8748 | 11.8748 | 8.9583 | 15.8748 | 25.7496 | 37.6243 | 5.9165 | 8.9583 | 7.9265 | 6.9165 | 9.8748 | 11.8748 | 8.9583 | 15.8748 | 25.7496 | 37.6243 | 0
6.5709 | 9.2855 | 8.5709 | 7.5709 | 10.8564 | 12.8564 | 9.2855 | 16.8564 | 27.7128 | 40.5691 | 6.5709 | 9.2855 | 8.5809 | 7.5709 | 10.8564 | 12.8564 | 9.2855 | 16.8564 | 27.7128 | 40.5691 | 0
4.407 | 8.2035 | 6.407 | 5.407 | 7.6105 | 9.6105 | 8.2035 | 13.6105 | 21.2209 | 30.8314 | 4.407 | 8.2035 | 6.417 | 5.407 | 7.6105 | 9.6105 | 8.2035 | 13.6105 | 21.2209 | 30.8314 | 0
7.6827 | 9.8413 | 9.6827 | 8.6827 | 12.524 | 14.524 | 9.8413 | 18.524 | 31.048 | 45.572 | 7.6827 | 9.8413 | 9.6927 | 8.6827 | 12.524 | 14.524 | 9.8413 | 18.524 | 31.048 | 45.572 | 0
5.0637 | 8.5318 | 7.0637 | 6.0637 | 8.5955 | 10.5955 | 8.5318 | 14.5955 | 23.191 | 33.7865 | 5.0637 | 8.5318 | 7.0737 | 6.0637 | 8.5955 | 10.5955 | 8.5318 | 14.5955 | 23.191 | 33.7865 | 0
3.1421 | 7.5711 | 5.1421 | 4.1421 | 5.7132 | 7.7132 | 7.5711 | 11.7132 | 17.4263 | 25.1395 | 3.1421 | 7.5711 | 5.1521 | 4.1421 | 5.7132 | 7.7132 | 7.5711 | 11.7132 | 17.4263 | 25.1395 | 0
8.3315 | 10.1657 | 10.3315 | 9.3315 | 13.4972 | 15.4972 | 10.1657 | 19.4972 | 32.9944 | 48.4916 | 8.3315 | 10.1657 | 10.3415 | 9.3315 | 13.4972 | 15.4972 | 10.1657 | 19.4972 | 32.9944 | 48.4916 | 0
7.0219 | 9.5109 | 9.0219 | 8.0219 | 11.5328 | 13.5328 | 9.5109 | 17.5328 | 29.0656 | 42.5985 | 7.0219 | 9.5109 | 9.0319 | 8.0219 | 11.5328 | 13.5328 | 9.5109 | 17.5328 | 29.0656 | 42.5985 | 0
7.4577 | 9.7289 | 9.4577 | 8.4577 | 12.1866 | 14.1866 | 9.7289 | 18.1866 | 30.3732 | 44.5599 | 7.4577 | 9.7289 | 9.4677 | 8.4577 | 12.1866 | 14.1866 | 9.7289 | 18.1866 | 30.3732 | 44.5599 | 0
8.7512 | 10.3756 | 10.7512 | 9.7512 | 14.1268 | 16.1268 | 10.3756 | 20.1268 | 34.2535 | 50.3803 | 8.7512 | 10.3756 | 10.7612 | 9.7512 | 14.1268 | 16.1268 | 10.3756 | 20.1268 | 34.2535 | 50.3803 | 0
3.186 | 7.593 | 5.186 | 4.186 | 5.779 | 7.779 | 7.593 | 11.779 | 17.558 | 25.337 | 3.186 | 7.593 | 5.196 | 4.186 | 5.779 | 7.779 | 7.593 | 11.779 | 17.558 | 25.337 | 0
3.9737 | 7.9868 | 5.9737 | 4.9737 | 6.9605 | 8.9605 | 7.9868 | 12.9605 | 19.921 | 28.8815 | 3.9737 | 7.9868 | 5.9837 | 4.9737 | 6.9605 | 8.9605 | 7.9868 | 12.9605 | 19.921 | 28.8815 | 0
6.1466 | 9.0733 | 8.1466 | 7.1466 | 10.2199 | 12.2199 | 9.0733 | 16.2199 | 26.4399 | 38.6598 | 6.1466 | 9.0733 | 8.1566 | 7.1466 | 10.2199 | 12.2199 | 9.0733 | 16.2199 | 26.4399 | 38.6598 | 0
4.2176 | 8.1088 | 6.2176 | 5.2176 | 7.3264 | 9.3264 | 8.1088 | 13.3264 | 20.6527 | 29.9791 | 4.2176 | 8.1088 | 6.2276 | 5.2176 | 7.3264 | 9.3264 | 8.1088 | 13.3264 | 20.6527 | 29.9791 | 0
6.6912 | 9.3456 | 8.6912 | 7.6912 | 11.0368 | 13.0368 | 9.3456 | 17.0368 | 28.0737 | 41.1105 | 6.6912 | 9.3456 | 8.7012 | 7.6912 | 11.0368 | 13.0368 | 9.3456 | 17.0368 | 28.0737 | 41.1105 | 0
4.7236 | 8.3618 | 6.7236 | 5.7236 | 8.0853 | 10.0853 | 8.3618 | 14.0853 | 22.1707 | 32.256 | 4.7236 | 8.3618 | 6.7336 | 5.7236 | 8.0853 | 10.0853 | 8.3618 | 14.0853 | 22.1707 | 32.256 | 0
4.7267 | 8.3634 | 6.7267 | 5.7267 | 8.0901 | 10.0901 | 8.3634 | 14.0901 | 22.1802 | 32.2704 | 4.7267 | 8.3634 | 6.7367 | 5.7267 | 8.0901 | 10.0901 | 8.3634 | 14.0901 | 22.1802 | 32.2704 | 0
7.199 | 9.5995 | 9.199 | 8.199 | 11.7985 | 13.7985 | 9.5995 | 17.7985 | 29.5969 | 43.3954 | 7.199 | 9.5995 | 9.209 | 8.199 | 11.7985 | 13.7985 | 9.5995 | 17.7985 | 29.5969 | 43.3954 | 0
3.7067 | 7.8534 | 5.7067 | 4.7067 | 6.5601 | 8.5601 | 7.8534 | 12.5601 | 19.1202 | 27.6803 | 3.7067 | 7.8534 | 5.7167 | 4.7067 | 6.5601 | 8.5601 | 7.8534 | 12.5601 | 19.1202 | 27.6803 | 0
5.995 | 8.9975 | 7.995 | 6.995 | 9.9925 | 11.9925 | 8.9975 | 15.9925 | 25.9851 | 37.9776 | 5.995 | 8.9975 | 8.005 | 6.995 | 9.9925 | 11.9925 | 8.9975 | 15.9925 | 25.9851 | 37.9776 | 0
5.0831 | 8.5415 | 7.0831 | 6.0831 | 8.6246 | 10.6246 | 8.5415 | 14.6246 | 23.2493 | 33.8739 | 5.0831 | 8.5415 | 7.0931 | 6.0831 | 8.6246 | 10.6246 | 8.5415 | 14.6246 | 23.2493 | 33.8739 | 0
6.1092 | 9.0546 | 8.1092 | 7.1092 | 10.1638 | 12.1638 | 9.0546 | 16.1638 | 26.3277 | 38.4915 | 6.1092 | 9.0546 | 8.1192 | 7.1092 | 10.1638 | 12.1638 | 9.0546 | 16.1638 | 26.3277 | 38.4915 | 0
8.5861 | 10.2931 | 10.5861 | 9.5861 | 13.8792 | 15.8792 | 10.2931 | 19.8792 | 33.7584 | 49.6375 | 8.5861 | 10.2931 | 10.5961 | 9.5861 | 13.8792 | 15.8792 | 10.2931 | 19.8792 | 33.7584 | 49.6375 | 0
5.3112 | 8.6556 | 7.3112 | 6.3112 | 8.9668 | 10.9668 | 8.6556 | 14.9668 | 23.9337 | 34.9005 | 5.3112 | 8.6556 | 7.3212 | 6.3112 | 8.9668 | 10.9668 | 8.6556 | 14.9668 | 23.9337 | 34.9005 | 0
3.0662 | 7.5331 | 5.0662 | 4.0662 | 5.5993 | 7.5993 | 7.5331 | 11.5993 | 17.1985 | 24.7978 | 3.0662 | 7.5331 | 5.0762 | 4.0662 | 5.5993 | 7.5993 | 7.5331 | 11.5993 | 17.1985 | 24.7978 | 0
5.713 | 8.8565 | 7.713 | 6.713 | 9.5695 | 11.5695 | 8.8565 | 15.5695 | 25.139 | 36.7085 | 5.713 | 8.8565 | 7.723 | 6.713 | 9.5695 | 11.5695 | 8.8565 | 15.5695 | 25.139 | 36.7085 | 0
2.1945 | 7.0972 | 4.1945 | 3.1945 | 4.2917 | 6.2917 | 7.0972 | 10.2917 | 14.5834 | 20.8751 | 2.1945 | 7.0972 | 4.2045 | 3.1945 | 4.2917 | 6.2917 | 7.0972 | 10.2917 | 14.5834 | 20.8751 | 0
4.0199 | 8.01 | 6.0199 | 5.0199 | 7.0299 | 9.0299 | 8.01 | 13.0299 | 20.0597 | 29.0896 | 4.0199 | 8.01 | 6.0299 | 5.0199 | 7.0299 | 9.0299 | 8.01 | 13.0299 | 20.0597 | 29.0896 | 0
6.6125 | 9.3062 | 8.6125 | 7.6125 | 10.9187 | 12.9187 | 9.3062 | 16.9187 | 27.8374 | 40.7562 | 6.6125 | 9.3062 | 8.6225 | 7.6125 | 10.9187 | 12.9187 | 9.3062 | 16.9187 | 27.8374 | 40.7562 | 0
6.4942 | 9.2471 | 8.4942 | 7.4942 | 10.7413 | 12.7413 | 9.2471 | 16.7413 | 27.4826 | 40.2239 | 6.4942 | 9.2471 | 8.5042 | 7.4942 | 10.7413 | 12.7413 | 9.2471 | 16.7413 | 27.4826 | 40.2239 | 0
5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 5.0921 | 8.546 | 7.1021 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 0
5.964 | 8.982 | 7.964 | 6.964 | 9.946 | 11.946 | 8.982 | 15.946 | 25.8919 | 37.8379 | 5.964 | 8.982 | 7.974 | 6.964 | 9.946 | 11.946 | 8.982 | 15.946 | 25.8919 | 37.8379 | 0
5.7816 | 8.8908 | 7.7816 | 6.7816 | 9.6724 | 11.6724 | 8.8908 | 15.6724 | 25.3449 | 37.0173 | 5.7816 | 8.8908 | 7.7916 | 6.7816 | 9.6724 | 11.6724 | 8.8908 | 15.6724 | 25.3449 | 37.0173 | 0
3.5707 | 7.7853 | 5.5707 | 4.5707 | 6.356 | 8.356 | 7.7853 | 12.356 | 18.712 | 27.068 | 3.5707 | 7.7853 | 5.5807 | 4.5707 | 6.356 | 8.356 | 7.7853 | 12.356 | 18.712 | 27.068 | 0
3.9955 | 7.9978 | 5.9955 | 4.9955 | 6.9933 | 8.9933 | 7.9978 | 12.9933 | 19.9866 | 28.9799 | 3.9955 | 7.9978 | 6.0055 | 4.9955 | 6.9933 | 8.9933 | 7.9978 | 12.9933 | 19.9866 | 28.9799 | 0
6.0997 | 9.0499 | 8.0997 | 7.0997 | 10.1496 | 12.1496 | 9.0499 | 16.1496 | 26.2992 | 38.4487 | 6.0997 | 9.0499 | 8.1097 | 7.0997 | 10.1496 | 12.1496 | 9.0499 | 16.1496 | 26.2992 | 38.4487 | 0
7.8375 | 9.9188 | 9.8375 | 8.8375 | 12.7563 | 14.7563 | 9.9188 | 18.7563 | 31.5125 | 46.2688 | 7.8375 | 9.9188 | 9.8475 | 8.8375 | 12.7563 | 14.7563 | 9.9188 | 18.7563 | 31.5125 | 46.2688 | 0
6.5393 | 9.2696 | 8.5393 | 7.5393 | 10.8089 | 12.8089 | 9.2696 | 16.8089 | 27.6178 | 40.4267 | 6.5393 | 9.2696 | 8.5493 | 7.5393 | 10.8089 | 12.8089 | 9.2696 | 16.8089 | 27.6178 | 40.4267 | 0
3.8684 | 7.9342 | 5.8684 | 4.8684 | 6.8026 | 8.8026 | 7.9342 | 12.8026 | 19.6051 | 28.4077 | 3.8684 | 7.9342 | 5.8784 | 4.8684 | 6.8026 | 8.8026 | 7.9342 | 12.8026 | 19.6051 | 28.4077 | 0
5.8862 | 8.9431 | 7.8862 | 6.8862 | 9.8293 | 11.8293 | 8.9431 | 15.8293 | 25.6586 | 37.4878 | 5.8862 | 8.9431 | 7.8962 | 6.8862 | 9.8293 | 11.8293 | 8.9431 | 15.8293 | 25.6586 | 37.4878 | 0
4.754 | 8.377 | 6.754 | 5.754 | 8.131 | 10.131 | 8.377 | 14.131 | 22.262 | 32.3929 | 4.754 | 8.377 | 6.764 | 5.754 | 8.131 | 10.131 | 8.377 | 14.131 | 22.262 | 32.3929 | 0
3.8834 | 7.9417 | 5.8834 | 4.8834 | 6.8251 | 8.8251 | 7.9417 | 12.8251 | 19.6503 | 28.4754 | 3.8834 | 7.9417 | 5.8934 | 4.8834 | 6.8251 | 8.8251 | 7.9417 | 12.8251 | 19.6503 | 28.4754 | 0
5.5401 | 8.7701 | 7.5401 | 6.5401 | 9.3102 | 11.3102 | 8.7701 | 15.3102 | 24.6204 | 35.9306 | 5.5401 | 8.7701 | 7.5501 | 6.5401 | 9.3102 | 11.3102 | 8.7701 | 15.3102 | 24.6204 | 35.9306 | 0
6.0247 | 9.0124 | 8.0247 | 7.0247 | 10.0371 | 12.0371 | 9.0124 | 16.0371 | 26.0741 | 38.1112 | 6.0247 | 9.0124 | 8.0347 | 7.0247 | 10.0371 | 12.0371 | 9.0124 | 16.0371 | 26.0741 | 38.1112 | 0
4.9316 | 8.4658 | 6.9316 | 5.9316 | 8.3975 | 10.3975 | 8.4658 | 14.3975 | 22.7949 | 33.1924 | 4.9316 | 8.4658 | 6.9416 | 5.9316 | 8.3975 | 10.3975 | 8.4658 | 14.3975 | 22.7949 | 33.1924 | 0
9.3444 | 10.6722 | 11.3444 | 10.3444 | 15.0166 | 17.0166 | 10.6722 | 21.0166 | 36.0332 | 53.0498 | 9.3444 | 10.6722 | 11.3544 | 10.3444 | 15.0166 | 17.0166 | 10.6722 | 21.0166 | 36.0332 | 53.0498 | 0
6.4224 | 9.2112 | 8.4224 | 7.4224 | 10.6336 | 12.6336 | 9.2112 | 16.6336 | 27.2672 | 39.9008 | 6.4224 | 9.2112 | 8.4324 | 7.4224 | 10.6336 | 12.6336 | 9.2112 | 16.6336 | 27.2672 | 39.9008 | 0
5.0339 | 8.5169 | 7.0339 | 6.0339 | 8.5508 | 10.5508 | 8.5169 | 14.5508 | 23.1016 | 33.6524 | 5.0339 | 8.5169 | 7.0439 | 6.0339 | 8.5508 | 10.5508 | 8.5169 | 14.5508 | 23.1016 | 33.6524 | 0
5.9344 | 8.9672 | 7.9344 | 6.9344 | 9.9016 | 11.9016 | 8.9672 | 15.9016 | 25.8033 | 37.7049 | 5.9344 | 8.9672 | 7.9444 | 6.9344 | 9.9016 | 11.9016 | 8.9672 | 15.9016 | 25.8033 | 37.7049 | 0
6.8634 | 9.4317 | 8.8634 | 7.8634 | 11.295 | 13.295 | 9.4317 | 17.295 | 28.5901 | 41.8851 | 6.8634 | 9.4317 | 8.8734 | 7.8634 | 11.295 | 13.295 | 9.4317 | 17.295 | 28.5901 | 41.8851 | 0
3.9905 | 7.9952 | 5.9905 | 4.9905 | 6.9857 | 8.9857 | 7.9952 | 12.9857 | 19.9714 | 28.9572 | 3.9905 | 7.9952 | 6.0005 | 4.9905 | 6.9857 | 8.9857 | 7.9952 | 12.9857 | 19.9714 | 28.9572 | 0
7.2021 | 9.601 | 9.2021 | 8.2021 | 11.8031 | 13.8031 | 9.601 | 17.8031 | 29.6063 | 43.4094 | 7.2021 | 9.601 | 9.2121 | 8.2021 | 11.8031 | 13.8031 | 9.601 | 17.8031 | 29.6063 | 43.4094 | 0
0.53517 | 6.2676 | 2.5352 | 1.5352 | 1.8028 | 3.8028 | 6.2676 | 7.8028 | 9.6055 | 13.4083 | 0.53517 | 6.2676 | 2.5452 | 1.5352 | 1.8028 | 3.8028 | 6.2676 | 7.8028 | 9.6055 | 13.4083 | 0
5.5684 | 8.7842 | 7.5684 | 6.5684 | 9.3525 | 11.3525 | 8.7842 | 15.3525 | 24.7051 | 36.0576 | 5.5684 | 8.7842 | 7.5784 | 6.5684 | 9.3525 | 11.3525 | 8.7842 | 15.3525 | 24.7051 | 36.0576 | 0
5.3874 | 8.6937 | 7.3874 | 6.3874 | 9.081 | 11.081 | 8.6937 | 15.081 | 24.1621 | 35.2431 | 5.3874 | 8.6937 | 7.3974 | 6.3874 | 9.081 | 11.081 | 8.6937 | 15.081 | 24.1621 | 35.2431 | 0
6.5294 | 9.2647 | 8.5294 | 7.5294 | 10.7942 | 12.7942 | 9.2647 | 16.7942 | 27.5883 | 40.3825 | 6.5294 | 9.2647 | 8.5394 | 7.5294 | 10.7942 | 12.7942 | 9.2647 | 16.7942 | 27.5883 | 40.3825 | 0
8.7496 | 10.3748 | 10.7496 | 9.7496 | 14.1244 | 16.1244 | 10.3748 | 20.1244 | 34.2488 | 50.3732 | 8.7496 | 10.3748 | 10.7596 | 9.7496 | 14.1244 | 16.1244 | 10.3748 | 20.1244 | 34.2488 | 50.3732 | 0
5.9569 | 8.9785 | 7.9569 | 6.9569 | 9.9354 | 11.9354 | 8.9785 | 15.9354 | 25.8708 | 37.8062 | 5.9569 | 8.9785 | 7.9669 | 6.9569 | 9.9354 | 11.9354 | 8.9785 | 15.9354 | 25.8708 | 37.8062 | 0
5.1926 | 8.5963 | 7.1926 | 6.1926 | 8.7889 | 10.7889 | 8.5963 | 14.7889 | 23.5777 | 34.3666 | 5.1926 | 8.5963 | 7.2026 | 6.1926 | 8.7889 | 10.7889 | 8.5963 | 14.7889 | 23.5777 | 34.3666 | 0
4.5049 | 8.2524 | 6.5049 | 5.5049 | 7.7573 | 9.7573 | 8.2524 | 13.7573 | 21.5146 | 31.272 | 4.5049 | 8.2524 | 6.5149 | 5.5049 | 7.7573 | 9.7573 | 8.2524 | 13.7573 | 21.5146 | 31.272 | 0
4.4453 | 8.2227 | 6.4453 | 5.4453 | 7.668 | 9.668 | 8.2227 | 13.668 | 21.336 | 31.004 | 4.4453 | 8.2227 | 6.4553 | 5.4453 | 7.668 | 9.668 | 8.2227 | 13.668 | 21.336 | 31.004 | 0
8.9107 | 10.4553 | 10.9107 | 9.9107 | 14.366 | 16.366 | 10.4553 | 20.366 | 34.7321 | 51.0981 | 8.9107 | 10.4553 | 10.9207 | 9.9107 | 14.366 | 16.366 | 10.4553 | 20.366 | 34.7321 | 51.0981 | 0
5.5784 | 8.7892 | 7.5784 | 6.5784 | 9.3676 | 11.3676 | 8.7892 | 15.3676 | 24.7351 | 36.1027 | 5.5784 | 8.7892 | 7.5884 | 6.5784 | 9.3676 | 11.3676 | 8.7892 | 15.3676 | 24.7351 | 36.1027 | 0
6.5968 | 9.2984 | 8.5968 | 7.5968 | 10.8952 | 12.8952 | 9.2984 | 16.8952 | 27.7903 | 40.6855 | 6.5968 | 9.2984 | 8.6068 | 7.5968 | 10.8952 | 12.8952 | 9.2984 | 16.8952 | 27.7903 | 40.6855 | 0
9.5841 | 10.7921 | 11.5841 | 10.5841 | 15.3762 | 17.3762 | 10.7921 | 21.3762 | 36.7524 | 54.1286 | 9.5841 | 10.7921 | 11.5941 | 10.5841 | 15.3762 | 17.3762 | 10.7921 | 21.3762 | 36.7524 | 54.1286 | 0
7.1421 | 9.5711 | 9.1421 | 8.1421 | 11.7132 | 13.7132 | 9.5711 | 17.7132 | 29.4264 | 43.1397 | 7.1421 | 9.5711 | 9.1521 | 8.1421 | 11.7132 | 13.7132 | 9.5711 | 17.7132 | 29.4264 | 43.1397 | 0
6.9164 | 9.4582 | 8.9164 | 7.9164 | 11.3746 | 13.3746 | 9.4582 | 17.3746 | 28.7492 | 42.1238 | 6.9164 | 9.4582 | 8.9264 | 7.9164 | 11.3746 | 13.3746 | 9.4582 | 17.3746 | 28.7492 | 42.1238 | 0
8.2153 | 10.1076 | 10.2153 | 9.2153 | 13.3229 | 15.3229 | 10.1076 | 19.3229 | 32.6459 | 47.9688 | 8.2153 | 10.1076 | 10.2253 | 9.2153 | 13.3229 | 15.3229 | 10.1076 | 19.3229 | 32.6459 | 47.9688 | 0
5.5263 | 8.7631 | 7.5263 | 6.5263 | 9.2894 | 11.2894 | 8.7631 | 15.2894 | 24.5789 | 35.8683 | 5.5263 | 8.7631 | 7.5363 | 6.5263 | 9.2894 | 11.2894 | 8.7631 | 15.2894 | 24.5789 | 35.8683 | 0
11.0337 | 11.5168 | 13.0337 | 12.0337 | 17.5505 | 19.5505 | 11.5168 | 23.5505 | 41.101 | 60.6514 | 11.0337 | 11.5168 | 13.0437 | 12.0337 | 17.5505 | 19.5505 | 11.5168 | 23.5505 | 41.101 | 60.6514 | 0
6.0016 | 9.0008 | 8.0016 | 7.0016 | 10.0024 | 12.0024 | 9.0008 | 16.0024 | 26.0048 | 38.0072 | 6.0016 | 9.0008 | 8.0116 | 7.0016 | 10.0024 | 12.0024 | 9.0008 | 16.0024 | 26.0048 | 38.0072 | 0
10.3738 | 11.1869 | 12.3738 | 11.3738 | 16.5607 | 18.5607 | 11.1869 | 22.5607 | 39.1215 | 57.6822 | 10.3738 | 11.1869 | 12.3838 | 11.3738 | 16.5607 | 18.5607 | 11.1869 | 22.5607 | 39.1215 | 57.6822 | 0
6.4121 | 9.206 | 8.4121 | 7.4121 | 10.6181 | 12.6181 | 9.206 | 16.6181 | 27.2363 | 39.8544 | 6.4121 | 9.206 | 8.4221 | 7.4121 | 10.6181 | 12.6181 | 9.206 | 16.6181 | 27.2363 | 39.8544 | 0
9.217 | 10.6085 | 11.217 | 10.217 | 14.8254 | 16.8254 | 10.6085 | 20.8254 | 35.6509 | 52.4763 | 9.217 | 10.6085 | 11.227 | 10.217 | 14.8254 | 16.8254 | 10.6085 | 20.8254 | 35.6509 | 52.4763 | 0
9.7797 | 10.8898 | 11.7797 | 10.7797 | 15.6695 | 17.6695 | 10.8898 | 21.6695 | 37.3391 | 55.0086 | 9.7797 | 10.8898 | 11.7897 | 10.7797 | 15.6695 | 17.6695 | 10.8898 | 21.6695 | 37.3391 | 55.0086 | 0
5.0423 | 8.5211 | 7.0423 | 6.0423 | 8.5634 | 10.5634 | 8.5211 | 14.5634 | 23.1268 | 33.6903 | 5.0423 | 8.5211 | 7.0523 | 6.0423 | 8.5634 | 10.5634 | 8.5211 | 14.5634 | 23.1268 | 33.6903 | 0
4.3481 | 8.174 | 6.3481 | 5.3481 | 7.5221 | 9.5221 | 8.174 | 13.5221 | 21.0442 | 30.5663 | 4.3481 | 8.174 | 6.3581 | 5.3481 | 7.5221 | 9.5221 | 8.174 | 13.5221 | 21.0442 | 30.5663 | 0
7.1758 | 9.5879 | 9.1758 | 8.1758 | 11.7637 | 13.7637 | 9.5879 | 17.7637 | 29.5274 | 43.2911 | 7.1758 | 9.5879 | 9.1858 | 8.1758 | 11.7637 | 13.7637 | 9.5879 | 17.7637 | 29.5274 | 43.2911 | 0
4.6681 | 8.3341 | 6.6681 | 5.6681 | 8.0022 | 10.0022 | 8.3341 | 14.0022 | 22.0043 | 32.0065 | 4.6681 | 8.3341 | 6.6781 | 5.6681 | 8.0022 | 10.0022 | 8.3341 | 14.0022 | 22.0043 | 32.0065 | 0
1.8921 | 6.946 | 3.8921 | 2.8921 | 3.8381 | 5.8381 | 6.946 | 9.8381 | 13.6762 | 19.5143 | 1.8921 | 6.946 | 3.9021 | 2.8921 | 3.8381 | 5.8381 | 6.946 | 9.8381 | 13.6762 | 19.5143 | 0
5.0109 | 8.5055 | 7.0109 | 6.0109 | 8.5164 | 10.5164 | 8.5055 | 14.5164 | 23.0328 | 33.5492 | 5.0109 | 8.5055 | 7.0209 | 6.0109 | 8.5164 | 10.5164 | 8.5055 | 14.5164 | 23.0328 | 33.5492 | 0
3.8584 | 7.9292 | 5.8584 | 4.8584 | 6.7875 | 8.7875 | 7.9292 | 12.7875 | 19.5751 | 28.3626 | 3.8584 | 7.9292 | 5.8684 | 4.8584 | 6.7875 | 8.7875 | 7.9292 | 12.7875 | 19.5751 | 28.3626 | 0
6.4966 | 9.2483 | 8.4966 | 7.4966 | 10.7448 | 12.7448 | 9.2483 | 16.7448 | 27.4897 | 40.2345 | 6.4966 | 9.2483 | 8.5066 | 7.4966 | 10.7448 | 12.7448 | 9.2483 | 16.7448 | 27.4897 | 40.2345 | 0
7.0352 | 9.5176 | 9.0352 | 8.0352 | 11.5527 | 13.5527 | 9.5176 | 17.5527 | 29.1055 | 42.6582 | 7.0352 | 9.5176 | 9.0452 | 8.0352 | 11.5527 | 13.5527 | 9.5176 | 17.5527 | 29.1055 | 42.6582 | 0
6.1885 | 9.0943 | 8.1885 | 7.1885 | 10.2828 | 12.2828 | 9.0943 | 16.2828 | 26.5656 | 38.8484 | 6.1885 | 9.0943 | 8.1985 | 7.1885 | 10.2828 | 12.2828 | 9.0943 | 16.2828 | 26.5656 | 38.8484 | 0
5.8998 | 8.9499 | 7.8998 | 6.8998 | 9.8497 | 11.8497 | 8.9499 | 15.8497 | 25.6995 | 37.5492 | 5.8998 | 8.9499 | 7.9098 | 6.8998 | 9.8497 | 11.8497 | 8.9499 | 15.8497 | 25.6995 | 37.5492 | 0
3.7522 | 7.8761 | 5.7522 | 4.7522 | 6.6283 | 8.6283 | 7.8761 | 12.6283 | 19.2566 | 27.8849 | 3.7522 | 7.8761 | 5.7622 | 4.7522 | 6.6283 | 8.6283 | 7.8761 | 12.6283 | 19.2566 | 27.8849 | 0
6.776 | 9.388 | 8.776 | 7.776 | 11.164 | 13.164 | 9.388 | 17.164 | 28.328 | 41.492 | 6.776 | 9.388 | 8.786 | 7.776 | 11.164 | 13.164 | 9.388 | 17.164 | 28.328 | 41.492 | 0
5.7807 | 8.8903 | 7.7807 | 6.7807 | 9.671 | 11.671 | 8.8903 | 15.671 | 25.3421 | 37.0131 | 5.7807 | 8.8903 | 7.7907 | 6.7807 | 9.671 | 11.671 | 8.8903 | 15.671 | 25.3421 | 37.0131 | 0
3.3449 | 7.6725 | 5.3449 | 4.3449 | 6.0174 | 8.0174 | 7.6725 | 12.0174 | 18.0348 | 26.0522 | 3.3449 | 7.6725 | 5.3549 | 4.3449 | 6.0174 | 8.0174 | 7.6725 | 12.0174 | 18.0348 | 26.0522 | 0
3.0968 | 7.5484 | 5.0968 | 4.0968 | 5.6452 | 7.6452 | 7.5484 | 11.6452 | 17.2904 | 24.9355 | 3.0968 | 7.5484 | 5.1068 | 4.0968 | 5.6452 | 7.6452 | 7.5484 | 11.6452 | 17.2904 | 24.9355 | 0
7.9137 | 9.9569 | 9.9137 | 8.9137 | 12.8706 | 14.8706 | 9.9569 | 18.8706 | 31.7412 | 46.6118 | 7.9137 | 9.9569 | 9.9237 | 8.9137 | 12.8706 | 14.8706 | 9.9569 | 18.8706 | 31.7412 | 46.6118 | 0
8.1265 | 10.0633 | 10.1265 | 9.1265 | 13.1898 | 15.1898 | 10.0633 | 19.1898 | 32.3795 | 47.5693 | 8.1265 | 10.0633 | 10.1365 | 9.1265 | 13.1898 | 15.1898 | 10.0633 | 19.1898 | 32.3795 | 47.5693 | 0
4.2244 | 8.1122 | 6.2244 | 5.2244 | 7.3366 | 9.3366 | 8.1122 | 13.3366 | 20.6732 | 30.0098 | 4.2244 | 8.1122 | 6.2344 | 5.2244 | 7.3366 | 9.3366 | 8.1122 | 13.3366 | 20.6732 | 30.0098 | 0
6.3537 | 9.1768 | 8.3537 | 7.3537 | 10.5305 | 12.5305 | 9.1768 | 16.5305 | 27.061 | 39.5914 | 6.3537 | 9.1768 | 8.3637 | 7.3537 | 10.5305 | 12.5305 | 9.1768 | 16.5305 | 27.061 | 39.5914 | 0
11.168 | 11.584 | 13.168 | 12.168 | 17.7521 | 19.7521 | 11.584 | 23.7521 | 41.5041 | 61.2562 | 11.168 | 11.584 | 13.178 | 12.168 | 17.7521 | 19.7521 | 11.584 | 23.7521 | 41.5041 | 61.2562 | 0
5.4518 | 8.7259 | 7.4518 | 6.4518 | 9.1778 | 11.1778 | 8.7259 | 15.1778 | 24.3555 | 35.5333 | 5.4518 | 8.7259 | 7.4618 | 6.4518 | 9.1778 | 11.1778 | 8.7259 | 15.1778 | 24.3555 | 35.5333 | 0
6.0492 | 9.0246 | 8.0492 | 7.0492 | 10.0738 | 12.0738 | 9.0246 | 16.0738 | 26.1476 | 38.2214 | 6.0492 | 9.0246 | 8.0592 | 7.0492 | 10.0738 | 12.0738 | 9.0246 | 16.0738 | 26.1476 | 38.2214 | 0
7.4105 | 9.7052 | 9.4105 | 8.4105 | 12.1157 | 14.1157 | 9.7052 | 18.1157 | 30.2314 | 44.3471 | 7.4105 | 9.7052 | 9.4205 | 8.4105 | 12.1157 | 14.1157 | 9.7052 | 18.1157 | 30.2314 | 44.3471 | 0
3.5875 | 7.7938 | 5.5875 | 4.5875 | 6.3813 | 8.3813 | 7.7938 | 12.3813 | 18.7626 | 27.1439 | 3.5875 | 7.7938 | 5.5975 | 4.5875 | 6.3813 | 8.3813 | 7.7938 | 12.3813 | 18.7626 | 27.1439 | 0
5.9969 | 8.9984 | 7.9969 | 6.9969 | 9.9953 | 11.9953 | 8.9984 | 15.9953 | 25.9906 | 37.9859 | 5.9969 | 8.9984 | 8.0069 | 6.9969 | 9.9953 | 11.9953 | 8.9984 | 15.9953 | 25.9906 | 37.9859 | 0
4.4596 | 8.2298 | 6.4596 | 5.4596 | 7.6894 | 9.6894 | 8.2298 | 13.6894 | 21.3787 | 31.0681 | 4.4596 | 8.2298 | 6.4696 | 5.4596 | 7.6894 | 9.6894 | 8.2298 | 13.6894 | 21.3787 | 31.0681 | 0
4.6953 | 8.3477 | 6.6953 | 5.6953 | 8.043 | 10.043 | 8.3477 | 14.043 | 22.0859 | 32.1289 | 4.6953 | 8.3477 | 6.7053 | 5.6953 | 8.043 | 10.043 | 8.3477 | 14.043 | 22.0859 | 32.1289 | 0
6.2341 | 9.117 | 8.2341 | 7.2341 | 10.3511 | 12.3511 | 9.117 | 16.3511 | 26.7023 | 39.0534 | 6.2341 | 9.117 | 8.2441 | 7.2341 | 10.3511 | 12.3511 | 9.117 | 16.3511 | 26.7023 | 39.0534 | 0
10.223 | 11.1115 | 12.223 | 11.223 | 16.3345 | 18.3345 | 11.1115 | 22.3345 | 38.669 | 57.0034 | 10.223 | 11.1115 | 12.233 | 11.223 | 16.3345 | 18.3345 | 11.1115 | 22.3345 | 38.669 | 57.0034 | 0
7.3917 | 9.6958 | 9.3917 | 8.3917 | 12.0875 | 14.0875 | 9.6958 | 18.0875 | 30.1751 | 44.2626 | 7.3917 | 9.6958 | 9.4017 | 8.3917 | 12.0875 | 14.0875 | 9.6958 | 18.0875 | 30.1751 | 44.2626 | 0
7.055 | 9.5275 | 9.055 | 8.055 | 11.5825 | 13.5825 | 9.5275 | 17.5825 | 29.1649 | 42.7474 | 7.055 | 9.5275 | 9.065 | 8.055 | 11.5825 | 13.5825 | 9.5275 | 17.5825 | 29.1649 | 42.7474 | 0
2.1916 | 7.0958 | 4.1916 | 3.1916 | 4.2875 | 6.2875 | 7.0958 | 10.2875 | 14.5749 | 20.8624 | 2.1916 | 7.0958 | 4.2016 | 3.1916 | 4.2875 | 6.2875 | 7.0958 | 10.2875 | 14.5749 | 20.8624 | 0
4.1961 | 8.098 | 6.1961 | 5.1961 | 7.2941 | 9.2941 | 8.098 | 13.2941 | 20.5882 | 29.8823 | 4.1961 | 8.098 | 6.2061 | 5.1961 | 7.2941 | 9.2941 | 8.098 | 13.2941 | 20.5882 | 29.8823 | 0
9.3012 | 10.6506 | 11.3012 | 10.3012 | 14.9518 | 16.9518 | 10.6506 | 20.9518 | 35.9036 | 52.8554 | 9.3012 | 10.6506 | 11.3112 | 10.3012 | 14.9518 | 16.9518 | 10.6506 | 20.9518 | 35.9036 | 52.8554 | 0
6.1032 | 9.0516 | 8.1032 | 7.1032 | 10.1549 | 12.1549 | 9.0516 | 16.1549 | 26.3097 | 38.4646 | 6.1032 | 9.0516 | 8.1132 | 7.1032 | 10.1549 | 12.1549 | 9.0516 | 16.1549 | 26.3097 | 38.4646 | 0
10.9776 | 11.4888 | 12.9776 | 11.9776 | 17.4663 | 19.4663 | 11.4888 | 23.4663 | 40.9327 | 60.399 | 10.9776 | 11.4888 | 12.9876 | 11.9776 | 17.4663 | 19.4663 | 11.4888 | 23.4663 | 40.9327 | 60.399 | 0
3.8066 | 7.9033 | 5.8066 | 4.8066 | 6.7099 | 8.7099 | 7.9033 | 12.7099 | 19.4198 | 28.1297 | 3.8066 | 7.9033 | 5.8166 | 4.8066 | 6.7099 | 8.7099 | 7.9033 | 12.7099 | 19.4198 | 28.1297 | 0
4.2458 | 8.1229 | 6.2458 | 5.2458 | 7.3688 | 9.3688 | 8.1229 | 13.3688 | 20.7375 | 30.1063 | 4.2458 | 8.1229 | 6.2558 | 5.2458 | 7.3688 | 9.3688 | 8.1229 | 13.3688 | 20.7375 | 30.1063 | 0
6.4005 | 9.2003 | 8.4005 | 7.4005 | 10.6008 | 12.6008 | 9.2003 | 16.6008 | 27.2016 | 39.8024 | 6.4005 | 9.2003 | 8.4105 | 7.4005 | 10.6008 | 12.6008 | 9.2003 | 16.6008 | 27.2016 | 39.8024 | 0
4.7583 | 8.3791 | 6.7583 | 5.7583 | 8.1374 | 10.1374 | 8.3791 | 14.1374 | 22.2748 | 32.4122 | 4.7583 | 8.3791 | 6.7683 | 5.7583 | 8.1374 | 10.1374 | 8.3791 | 14.1374 | 22.2748 | 32.4122 | 0
6.5861 | 9.293 | 8.5861 | 7.5861 | 10.8791 | 12.8791 | 9.293 | 16.8791 | 27.7582 | 40.6373 | 6.5861 | 9.293 | 8.5961 | 7.5861 | 10.8791 | 12.8791 | 9.293 | 16.8791 | 27.7582 | 40.6373 | 0
8.5851 | 10.2925 | 10.5851 | 9.5851 | 13.8776 | 15.8776 | 10.2925 | 19.8776 | 33.7552 | 49.6328 | 8.5851 | 10.2925 | 10.5951 | 9.5851 | 13.8776 | 15.8776 | 10.2925 | 19.8776 | 33.7552 | 49.6328 | 0
8.0992 | 10.0496 | 10.0992 | 9.0992 | 13.1489 | 15.1489 | 10.0496 | 19.1489 | 32.2977 | 47.4466 | 8.0992 | 10.0496 | 10.1092 | 9.0992 | 13.1489 | 15.1489 | 10.0496 | 19.1489 | 32.2977 | 47.4466 | 0
6.8226 | 9.4113 | 8.8226 | 7.8226 | 11.2338 | 13.2338 | 9.4113 | 17.2338 | 28.4677 | 41.7015 | 6.8226 | 9.4113 | 8.8326 | 7.8226 | 11.2338 | 13.2338 | 9.4113 | 17.2338 | 28.4677 | 41.7015 | 0
5.9018 | 8.9509 | 7.9018 | 6.9018 | 9.8527 | 11.8527 | 8.9509 | 15.8527 | 25.7054 | 37.5582 | 5.9018 | 8.9509 | 7.9118 | 6.9018 | 9.8527 | 11.8527 | 8.9509 | 15.8527 | 25.7054 | 37.5582 | 0
3.8038 | 7.9019 | 5.8038 | 4.8038 | 6.7057 | 8.7057 | 7.9019 | 12.7057 | 19.4114 | 28.1172 | 3.8038 | 7.9019 | 5.8138 | 4.8038 | 6.7057 | 8.7057 | 7.9019 | 12.7057 | 19.4114 | 28.1172 | 0
7.6562 | 9.8281 | 9.6562 | 8.6562 | 12.4843 | 14.4843 | 9.8281 | 18.4843 | 30.9687 | 45.453 | 7.6562 | 9.8281 | 9.6662 | 8.6562 | 12.4843 | 14.4843 | 9.8281 | 18.4843 | 30.9687 | 45.453 | 0
5.9438 | 8.9719 | 7.9438 | 6.9438 | 9.9156 | 11.9156 | 8.9719 | 15.9156 | 25.8313 | 37.7469 | 5.9438 | 8.9719 | 7.9538 | 6.9438 | 9.9156 | 11.9156 | 8.9719 | 15.9156 | 25.8313 | 37.7469 | 0
4.5206 | 8.2603 | 6.5206 | 5.5206 | 7.7809 | 9.7809 | 8.2603 | 13.7809 | 21.5618 | 31.3428 | 4.5206 | 8.2603 | 6.5306 | 5.5206 | 7.7809 | 9.7809 | 8.2603 | 13.7809 | 21.5618 | 31.3428 | 0
6.1925 | 9.0963 | 8.1925 | 7.1925 | 10.2888 | 12.2888 | 9.0963 | 16.2888 | 26.5776 | 38.8664 | 6.1925 | 9.0963 | 8.2025 | 7.1925 | 10.2888 | 12.2888 | 9.0963 | 16.2888 | 26.5776 | 38.8664 | 0
6.2748 | 9.1374 | 8.2748 | 7.2748 | 10.4122 | 12.4122 | 9.1374 | 16.4122 | 26.8244 | 39.2366 | 6.2748 | 9.1374 | 8.2848 | 7.2748 | 10.4122 | 12.4122 | 9.1374 | 16.4122 | 26.8244 | 39.2366 | 0
6.3519 | 9.176 | 8.3519 | 7.3519 | 10.5279 | 12.5279 | 9.176 | 16.5279 | 27.0558 | 39.5837 | 6.3519 | 9.176 | 8.3619 | 7.3519 | 10.5279 | 12.5279 | 9.176 | 16.5279 | 27.0558 | 39.5837 | 0
4.0229 | 8.0115 | 6.0229 | 5.0229 | 7.0344 | 9.0344 | 8.0115 | 13.0344 | 20.0687 | 29.1031 | 4.0229 | 8.0115 | 6.0329 | 5.0229 | 7.0344 | 9.0344 | 8.0115 | 13.0344 | 20.0687 | 29.1031 | 0
5.9303 | 8.9651 | 7.9303 | 6.9303 | 9.8954 | 11.8954 | 8.9651 | 15.8954 | 25.7909 | 37.6863 | 5.9303 | 8.9651 | 7.9403 | 6.9303 | 9.8954 | 11.8954 | 8.9651 | 15.8954 | 25.7909 | 37.6863 | 0
6.936 | 9.468 | 8.936 | 7.936 | 11.404 | 13.404 | 9.468 | 17.404 | 28.808 | 42.2119 | 6.936 | 9.468 | 8.946 | 7.936 | 11.404 | 13.404 | 9.468 | 17.404 | 28.808 | 42.2119 | 0
7.0226 | 9.5113 | 9.0226 | 8.0226 | 11.5339 | 13.5339 | 9.5113 | 17.5339 | 29.0677 | 42.6016 | 7.0226 | 9.5113 | 9.0326 | 8.0226 | 11.5339 | 13.5339 | 9.5113 | 17.5339 | 29.0677 | 42.6016 | 0
2.7903 | 7.3951 | 4.7903 | 3.7903 | 5.1854 | 7.1854 | 7.3951 | 11.1854 | 16.3708 | 23.5562 | 2.7903 | 7.3951 | 4.8003 | 3.7903 | 5.1854 | 7.1854 | 7.3951 | 11.1854 | 16.3708 | 23.5562 | 0
6.8957 | 9.4479 | 8.8957 | 7.8957 | 11.3436 | 13.3436 | 9.4479 | 17.3436 | 28.6871 | 42.0307 | 6.8957 | 9.4479 | 8.9057 | 7.8957 | 11.3436 | 13.3436 | 9.4479 | 17.3436 | 28.6871 | 42.0307 | 0
6.0138 | 9.0069 | 8.0138 | 7.0138 | 10.0208 | 12.0208 | 9.0069 | 16.0208 | 26.0415 | 38.0623 | 6.0138 | 9.0069 | 8.0238 | 7.0138 | 10.0208 | 12.0208 | 9.0069 | 16.0208 | 26.0415 | 38.0623 | 0
3.8657 | 7.9328 | 5.8657 | 4.8657 | 6.7985 | 8.7985 | 7.9328 | 12.7985 | 19.597 | 28.3955 | 3.8657 | 7.9328 | 5.8757 | 4.8657 | 6.7985 | 8.7985 | 7.9328 | 12.7985 | 19.597 | 28.3955 | 0
7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 7.4889 | 9.7444 | 9.4989 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 0
8.8202 | 10.4101 | 10.8202 | 9.8202 | 14.2303 | 16.2303 | 10.4101 | 20.2303 | 34.4605 | 50.6908 | 8.8202 | 10.4101 | 10.8302 | 9.8202 | 14.2303 | 16.2303 | 10.4101 | 20.2303 | 34.4605 | 50.6908 | 0
7.8196 | 9.9098 | 9.8196 | 8.8196 | 12.7294 | 14.7294 | 9.9098 | 18.7294 | 31.4588 | 46.1882 | 7.8196 | 9.9098 | 9.8296 | 8.8196 | 12.7294 | 14.7294 | 9.9098 | 18.7294 | 31.4588 | 46.1882 | 0
4.576 | 8.288 | 6.576 | 5.576 | 7.864 | 9.864 | 8.288 | 13.864 | 21.7279 | 31.5919 | 4.576 | 8.288 | 6.586 | 5.576 | 7.864 | 9.864 | 8.288 | 13.864 | 21.7279 | 31.5919 | 0
7.0266 | 9.5133 | 9.0266 | 8.0266 | 11.5399 | 13.5399 | 9.5133 | 17.5399 | 29.0798 | 42.6196 | 7.0266 | 9.5133 | 9.0366 | 8.0266 | 11.5399 | 13.5399 | 9.5133 | 17.5399 | 29.0798 | 42.6196 | 0
6.0145 | 9.0072 | 8.0145 | 7.0145 | 10.0217 | 12.0217 | 9.0072 | 16.0217 | 26.0434 | 38.0651 | 6.0145 | 9.0072 | 8.0245 | 7.0145 | 10.0217 | 12.0217 | 9.0072 | 16.0217 | 26.0434 | 38.0651 | 0
2.6438 | 7.3219 | 4.6438 | 3.6438 | 4.9657 | 6.9657 | 7.3219 | 10.9657 | 15.9313 | 22.897 | 2.6438 | 7.3219 | 4.6538 | 3.6438 | 4.9657 | 6.9657 | 7.3219 | 10.9657 | 15.9313 | 22.897 | 0
6.0348 | 9.0174 | 8.0348 | 7.0348 | 10.0522 | 12.0522 | 9.0174 | 16.0522 | 26.1044 | 38.1566 | 6.0348 | 9.0174 | 8.0448 | 7.0348 | 10.0522 | 12.0522 | 9.0174 | 16.0522 | 26.1044 | 38.1566 | 0
5.4907 | 8.7453 | 7.4907 | 6.4907 | 9.236 | 11.236 | 8.7453 | 15.236 | 24.472 | 35.7079 | 5.4907 | 8.7453 | 7.5007 | 6.4907 | 9.236 | 11.236 | 8.7453 | 15.236 | 24.472 | 35.7079 | 0
7.3925 | 9.6962 | 9.3925 | 8.3925 | 12.0887 | 14.0887 | 9.6962 | 18.0887 | 30.1774 | 44.2661 | 7.3925 | 9.6962 | 9.4025 | 8.3925 | 12.0887 | 14.0887 | 9.6962 | 18.0887 | 30.1774 | 44.2661 | 0
6.0746 | 9.0373 | 8.0746 | 7.0746 | 10.1119 | 12.1119 | 9.0373 | 16.1119 | 26.2238 | 38.3357 | 6.0746 | 9.0373 | 8.0846 | 7.0746 | 10.1119 | 12.1119 | 9.0373 | 16.1119 | 26.2238 | 38.3357 | 0
5.7247 | 8.8624 | 7.7247 | 6.7247 | 9.5871 | 11.5871 | 8.8624 | 15.5871 | 25.1742 | 36.7613 | 5.7247 | 8.8624 | 7.7347 | 6.7247 | 9.5871 | 11.5871 | 8.8624 | 15.5871 | 25.1742 | 36.7613 | 0
5.7801 | 8.89 | 7.7801 | 6.7801 | 9.6701 | 11.6701 | 8.89 | 15.6701 | 25.3403 | 37.0104 | 5.7801 | 8.89 | 7.7901 | 6.7801 | 9.6701 | 11.6701 | 8.89 | 15.6701 | 25.3403 | 37.0104 | 0
4.7764 | 8.3882 | 6.7764 | 5.7764 | 8.1646 | 10.1646 | 8.3882 | 14.1646 | 22.3292 | 32.4937 | 4.7764 | 8.3882 | 6.7864 | 5.7764 | 8.1646 | 10.1646 | 8.3882 | 14.1646 | 22.3292 | 32.4937 | 0
2.1447 | 7.0723 | 4.1447 | 3.1447 | 4.217 | 6.217 | 7.0723 | 10.217 | 14.434 | 20.6509 | 2.1447 | 7.0723 | 4.1547 | 3.1447 | 4.217 | 6.217 | 7.0723 | 10.217 | 14.434 | 20.6509 | 0
5.7028 | 8.8514 | 7.7028 | 6.7028 | 9.5542 | 11.5542 | 8.8514 | 15.5542 | 25.1084 | 36.6625 | 5.7028 | 8.8514 | 7.7128 | 6.7028 | 9.5542 | 11.5542 | 8.8514 | 15.5542 | 25.1084 | 36.6625 | 0
7.7214 | 9.8607 | 9.7214 | 8.7214 | 12.582 | 14.582 | 9.8607 | 18.582 | 31.1641 | 45.7461 | 7.7214 | 9.8607 | 9.7314 | 8.7214 | 12.582 | 14.582 | 9.8607 | 18.582 | 31.1641 | 45.7461 | 0
5.5976 | 8.7988 | 7.5976 | 6.5976 | 9.3964 | 11.3964 | 8.7988 | 15.3964 | 24.7928 | 36.1892 | 5.5976 | 8.7988 | 7.6076 | 6.5976 | 9.3964 | 11.3964 | 8.7988 | 15.3964 | 24.7928 | 36.1892 | 0
5.3389 | 8.6695 | 7.3389 | 6.3389 | 9.0084 | 11.0084 | 8.6695 | 15.0084 | 24.0167 | 35.0251 | 5.3389 | 8.6695 | 7.3489 | 6.3389 | 9.0084 | 11.0084 | 8.6695 | 15.0084 | 24.0167 | 35.0251 | 0
8.3081 | 10.154 | 10.3081 | 9.3081 | 13.4621 | 15.4621 | 10.154 | 19.4621 | 32.9243 | 48.3864 | 8.3081 | 10.154 | 10.3181 | 9.3081 | 13.4621 | 15.4621 | 10.154 | 19.4621 | 32.9243 | 48.3864 | 0
6.3383 | 9.1691 | 8.3383 | 7.3383 | 10.5074 | 12.5074 | 9.1691 | 16.5074 | 27.0148 | 39.5222 | 6.3383 | 9.1691 | 8.3483 | 7.3383 | 10.5074 | 12.5074 | 9.1691 | 16.5074 | 27.0148 | 39.5222 | 0
6.2356 | 9.1178 | 8.2356 | 7.2356 | 10.3534 | 12.3534 | 9.1178 | 16.3534 | 26.7069 | 39.0603 | 6.2356 | 9.1178 | 8.2456 | 7.2356 | 10.3534 | 12.3534 | 9.1178 | 16.3534 | 26.7069 | 39.0603 | 0
8.8103 | 10.4051 | 10.8103 | 9.8103 | 14.2154 | 16.2154 | 10.4051 | 20.2154 | 34.4309 | 50.6463 | 8.8103 | 10.4051 | 10.8203 | 9.8103 | 14.2154 | 16.2154 | 10.4051 | 20.2154 | 34.4309 | 50.6463 | 0
9.1328 | 10.5664 | 11.1328 | 10.1328 | 14.6992 | 16.6992 | 10.5664 | 20.6992 | 35.3985 | 52.0977 | 9.1328 | 10.5664 | 11.1428 | 10.1328 | 14.6992 | 16.6992 | 10.5664 | 20.6992 | 35.3985 | 52.0977 | 0
7.1789 | 9.5895 | 9.1789 | 8.1789 | 11.7684 | 13.7684 | 9.5895 | 17.7684 | 29.5367 | 43.3051 | 7.1789 | 9.5895 | 9.1889 | 8.1789 | 11.7684 | 13.7684 | 9.5895 | 17.7684 | 29.5367 | 43.3051 | 0
6.2187 | 9.1093 | 8.2187 | 7.2187 | 10.328 | 12.328 | 9.1093 | 16.328 | 26.6561 | 38.9841 | 6.2187 | 9.1093 | 8.2287 | 7.2187 | 10.328 | 12.328 | 9.1093 | 16.328 | 26.6561 | 38.9841 | 0
10.8017 | 11.4008 | 12.8017 | 11.8017 | 17.2025 | 19.2025 | 11.4008 | 23.2025 | 40.405 | 59.6075 | 10.8017 | 11.4008 | 12.8117 | 11.8017 | 17.2025 | 19.2025 | 11.4008 | 23.2025 | 40.405 | 59.6075 | 0
4.3082 | 8.1541 | 6.3082 | 5.3082 | 7.4622 | 9.4622 | 8.1541 | 13.4622 | 20.9245 | 30.3867 | 4.3082 | 8.1541 | 6.3182 | 5.3082 | 7.4622 | 9.4622 | 8.1541 | 13.4622 | 20.9245 | 30.3867 | 0
6.2847 | 9.1423 | 8.2847 | 7.2847 | 10.427 | 12.427 | 9.1423 | 16.427 | 26.8541 | 39.2811 | 6.2847 | 9.1423 | 8.2947 | 7.2847 | 10.427 | 12.427 | 9.1423 | 16.427 | 26.8541 | 39.2811 | 0
3.8754 | 7.9377 | 5.8754 | 4.8754 | 6.8131 | 8.8131 | 7.9377 | 12.8131 | 19.6261 | 28.4392 | 3.8754 | 7.9377 | 5.8854 | 4.8754 | 6.8131 | 8.8131 | 7.9377 | 12.8131 | 19.6261 | 28.4392 | 0
3.5216 | 7.7608 | 5.5216 | 4.5216 | 6.2824 | 8.2824 | 7.7608 | 12.2824 | 18.5649 | 26.8473 | 3.5216 | 7.7608 | 5.5316 | 4.5216 | 6.2824 | 8.2824 | 7.7608 | 12.2824 | 18.5649 | 26.8473 | 0
5.5633 | 8.7817 | 7.5633 | 6.5633 | 9.345 | 11.345 | 8.7817 | 15.345 | 24.69 | 36.0351 | 5.5633 | 8.7817 | 7.5733 | 6.5633 | 9.345 | 11.345 | 8.7817 | 15.345 | 24.69 | 36.0351 | 0
4.8463 | 8.4232 | 6.8463 | 5.8463 | 8.2695 | 10.2695 | 8.4232 | 14.2695 | 22.5389 | 32.8084 | 4.8463 | 8.4232 | 6.8563 | 5.8463 | 8.2695 | 10.2695 | 8.4232 | 14.2695 | 22.5389 | 32.8084 | 0
6.9828 | 9.4914 | 8.9828 | 7.9828 | 11.4743 | 13.4743 | 9.4914 | 17.4743 | 28.9485 | 42.4228 | 6.9828 | 9.4914 | 8.9928 | 7.9828 | 11.4743 | 13.4743 | 9.4914 | 17.4743 | 28.9485 | 42.4228 | 0
7.8476 | 9.9238 | 9.8476 | 8.8476 | 12.7713 | 14.7713 | 9.9238 | 18.7713 | 31.5427 | 46.314 | 7.8476 | 9.9238 | 9.8576 | 8.8476 | 12.7713 | 14.7713 | 9.9238 | 18.7713 | 31.5427 | 46.314 | 0
7.0345 | 9.5172 | 9.0345 | 8.0345 | 11.5517 | 13.5517 | 9.5172 | 17.5517 | 29.1034 | 42.655 | 7.0345 | 9.5172 | 9.0445 | 8.0345 | 11.5517 | 13.5517 | 9.5172 | 17.5517 | 29.1034 | 42.655 | 0
7.2596 | 9.6298 | 9.2596 | 8.2596 | 11.8894 | 13.8894 | 9.6298 | 17.8894 | 29.7788 | 43.6682 | 7.2596 | 9.6298 | 9.2696 | 8.2596 | 11.8894 | 13.8894 | 9.6298 | 17.8894 | 29.7788 | 43.6682 | 0
6.762 | 9.381 | 8.762 | 7.762 | 11.143 | 13.143 | 9.381 | 17.143 | 28.286 | 41.4289 | 6.762 | 9.381 | 8.772 | 7.762 | 11.143 | 13.143 | 9.381 | 17.143 | 28.286 | 41.4289 | 0
4.7843 | 8.3922 | 6.7843 | 5.7843 | 8.1765 | 10.1765 | 8.3922 | 14.1765 | 22.3529 | 32.5294 | 4.7843 | 8.3922 | 6.7943 | 5.7843 | 8.1765 | 10.1765 | 8.3922 | 14.1765 | 22.3529 | 32.5294 | 0
5.9404 | 8.9702 | 7.9404 | 6.9404 | 9.9106 | 11.9106 | 8.9702 | 15.9106 | 25.8212 | 37.7318 | 5.9404 | 8.9702 | 7.9504 | 6.9404 | 9.9106 | 11.9106 | 8.9702 | 15.9106 | 25.8212 | 37.7318 | 0
6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 6.3314 | 9.1657 | 8.3414 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 0
7.0135 | 9.5068 | 9.0135 | 8.0135 | 11.5203 | 13.5203 | 9.5068 | 17.5203 | 29.0406 | 42.5608 | 7.0135 | 9.5068 | 9.0235 | 8.0135 | 11.5203 | 13.5203 | 9.5068 | 17.5203 | 29.0406 | 42.5608 | 0
3.4265 | 7.7133 | 5.4265 | 4.4265 | 6.1398 | 8.1398 | 7.7133 | 12.1398 | 18.2796 | 26.4194 | 3.4265 | 7.7133 | 5.4365 | 4.4265 | 6.1398 | 8.1398 | 7.7133 | 12.1398 | 18.2796 | 26.4194 | 0
5.4813 | 8.7407 | 7.4813 | 6.4813 | 9.222 | 11.222 | 8.7407 | 15.222 | 24.444 | 35.6659 | 5.4813 | 8.7407 | 7.4913 | 6.4813 | 9.222 | 11.222 | 8.7407 | 15.222 | 24.444 | 35.6659 | 0
7.7681 | 9.8841 | 9.7681 | 8.7681 | 12.6522 | 14.6522 | 9.8841 | 18.6522 | 31.3044 | 45.9566 | 7.7681 | 9.8841 | 9.7781 | 8.7681 | 12.6522 | 14.6522 | 9.8841 | 18.6522 | 31.3044 | 45.9566 | 0
6.4122 | 9.2061 | 8.4122 | 7.4122 | 10.6184 | 12.6184 | 9.2061 | 16.6184 | 27.2367 | 39.8551 | 6.4122 | 9.2061 | 8.4222 | 7.4122 | 10.6184 | 12.6184 | 9.2061 | 16.6184 | 27.2367 | 39.8551 | 0
8.7219 | 10.361 | 10.7219 | 9.7219 | 14.0829 | 16.0829 | 10.361 | 20.0829 | 34.1657 | 50.2486 | 8.7219 | 10.361 | 10.7319 | 9.7219 | 14.0829 | 16.0829 | 10.361 | 20.0829 | 34.1657 | 50.2486 | 0
5.8098 | 8.9049 | 7.8098 | 6.8098 | 9.7147 | 11.7147 | 8.9049 | 15.7147 | 25.4293 | 37.144 | 5.8098 | 8.9049 | 7.8198 | 6.8098 | 9.7147 | 11.7147 | 8.9049 | 15.7147 | 25.4293 | 37.144 | 0
4.8329 | 8.4165 | 6.8329 | 5.8329 | 8.2494 | 10.2494 | 8.4165 | 14.2494 | 22.4987 | 32.7481 | 4.8329 | 8.4165 | 6.8429 | 5.8329 | 8.2494 | 10.2494 | 8.4165 | 14.2494 | 22.4987 | 32.7481 | 0
6.7605 | 9.3803 | 8.7605 | 7.7605 | 11.1408 | 13.1408 | 9.3803 | 17.1408 | 28.2815 | 41.4223 | 6.7605 | 9.3803 | 8.7705 | 7.7605 | 11.1408 | 13.1408 | 9.3803 | 17.1408 | 28.2815 | 41.4223 | 0
9.047 | 10.5235 | 11.047 | 10.047 | 14.5706 | 16.5706 | 10.5235 | 20.5706 | 35.1411 | 51.7117 | 9.047 | 10.5235 | 11.057 | 10.047 | 14.5706 | 16.5706 | 10.5235 | 20.5706 | 35.1411 | 51.7117 | 0
7.8454 | 9.9227 | 9.8454 | 8.8454 | 12.7682 | 14.7682 | 9.9227 | 18.7682 | 31.5363 | 46.3045 | 7.8454 | 9.9227 | 9.8554 | 8.8454 | 12.7682 | 14.7682 | 9.9227 | 18.7682 | 31.5363 | 46.3045 | 0
6.6496 | 9.3248 | 8.6496 | 7.6496 | 10.9744 | 12.9744 | 9.3248 | 16.9744 | 27.9489 | 40.9233 | 6.6496 | 9.3248 | 8.6596 | 7.6496 | 10.9744 | 12.9744 | 9.3248 | 16.9744 | 27.9489 | 40.9233 | 0
4.2135 | 8.1067 | 6.2135 | 5.2135 | 7.3202 | 9.3202 | 8.1067 | 13.3202 | 20.6404 | 29.9606 | 4.2135 | 8.1067 | 6.2235 | 5.2135 | 7.3202 | 9.3202 | 8.1067 | 13.3202 | 20.6404 | 29.9606 | 0
11.6293 | 11.8146 | 13.6293 | 12.6293 | 18.4439 | 20.4439 | 11.8146 | 24.4439 | 42.8878 | 63.3317 | 11.6293 | 11.8146 | 13.6393 | 12.6293 | 18.4439 | 20.4439 | 11.8146 | 24.4439 | 42.8878 | 63.3317 | 0
5.3138 | 8.6569 | 7.3138 | 6.3138 | 8.9707 | 10.9707 | 8.6569 | 14.9707 | 23.9414 | 34.9122 | 5.3138 | 8.6569 | 7.3238 | 6.3138 | 8.9707 | 10.9707 | 8.6569 | 14.9707 | 23.9414 | 34.9122 | 0
6.2814 | 9.1407 | 8.2814 | 7.2814 | 10.4222 | 12.4222 | 9.1407 | 16.4222 | 26.8443 | 39.2665 | 6.2814 | 9.1407 | 8.2914 | 7.2814 | 10.4222 | 12.4222 | 9.1407 | 16.4222 | 26.8443 | 39.2665 | 0
5.935 | 8.9675 | 7.935 | 6.935 | 9.9026 | 11.9026 | 8.9675 | 15.9026 | 25.8051 | 37.7077 | 5.935 | 8.9675 | 7.945 | 6.935 | 9.9026 | 11.9026 | 8.9675 | 15.9026 | 25.8051 | 37.7077 | 0
6.1508 | 9.0754 | 8.1508 | 7.1508 | 10.2262 | 12.2262 | 9.0754 | 16.2262 | 26.4523 | 38.6785 | 6.1508 | 9.0754 | 8.1608 | 7.1508 | 10.2262 | 12.2262 | 9.0754 | 16.2262 | 26.4523 | 38.6785 | 0
5.3276 | 8.6638 | 7.3276 | 6.3276 | 8.9914 | 10.9914 | 8.6638 | 14.9914 | 23.9828 | 34.9742 | 5.3276 | 8.6638 | 7.3376 | 6.3276 | 8.9914 | 10.9914 | 8.6638 | 14.9914 | 23.9828 | 34.9742 | 0
2.0185 | 7.0093 | 4.0185 | 3.0185 | 4.0278 | 6.0278 | 7.0093 | 10.0278 | 14.0556 | 20.0834 | 2.0185 | 7.0093 | 4.0285 | 3.0185 | 4.0278 | 6.0278 | 7.0093 | 10.0278 | 14.0556 | 20.0834 | 0
7.9373 | 9.9687 | 9.9373 | 8.9373 | 12.906 | 14.906 | 9.9687 | 18.906 | 31.812 | 46.718 | 7.9373 | 9.9687 | 9.9473 | 8.9373 | 12.906 | 14.906 | 9.9687 | 18.906 | 31.812 | 46.718 | 0
7.1858 | 9.5929 | 9.1858 | 8.1858 | 11.7787 | 13.7787 | 9.5929 | 17.7787 | 29.5575 | 43.3362 | 7.1858 | 9.5929 | 9.1958 | 8.1858 | 11.7787 | 13.7787 | 9.5929 | 17.7787 | 29.5575 | 43.3362 | 0
6.7905 | 9.3953 | 8.7905 | 7.7905 | 11.1858 | 13.1858 | 9.3953 | 17.1858 | 28.3716 | 41.5574 | 6.7905 | 9.3953 | 8.8005 | 7.7905 | 11.1858 | 13.1858 | 9.3953 | 17.1858 | 28.3716 | 41.5574 | 0
8.3321 | 10.166 | 10.3321 | 9.3321 | 13.4981 | 15.4981 | 10.166 | 19.4981 | 32.9962 | 48.4944 | 8.3321 | 10.166 | 10.3421 | 9.3321 | 13.4981 | 15.4981 | 10.166 | 19.4981 | 32.9962 | 48.4944 | 0
4.4306 | 8.2153 | 6.4306 | 5.4306 | 7.6459 | 9.6459 | 8.2153 | 13.6459 | 21.2918 | 30.9377 | 4.4306 | 8.2153 | 6.4406 | 5.4306 | 7.6459 | 9.6459 | 8.2153 | 13.6459 | 21.2918 | 30.9377 | 0
5.963 | 8.9815 | 7.963 | 6.963 | 9.9446 | 11.9446 | 8.9815 | 15.9446 | 25.8891 | 37.8337 | 5.963 | 8.9815 | 7.973 | 6.963 | 9.9446 | 11.9446 | 8.9815 | 15.9446 | 25.8891 | 37.8337 | 0
5.0349 | 8.5174 | 7.0349 | 6.0349 | 8.5523 | 10.5523 | 8.5174 | 14.5523 | 23.1047 | 33.657 | 5.0349 | 8.5174 | 7.0449 | 6.0349 | 8.5523 | 10.5523 | 8.5174 | 14.5523 | 23.1047 | 33.657 | 0
7.8813 | 9.9407 | 9.8813 | 8.8813 | 12.822 | 14.822 | 9.9407 | 18.822 | 31.644 | 46.466 | 7.8813 | 9.9407 | 9.8913 | 8.8813 | 12.822 | 14.822 | 9.9407 | 18.822 | 31.644 | 46.466 | 0
2.9422 | 7.4711 | 4.9422 | 3.9422 | 5.4133 | 7.4133 | 7.4711 | 11.4133 | 16.8265 | 24.2398 | 2.9422 | 7.4711 | 4.9522 | 3.9422 | 5.4133 | 7.4133 | 7.4711 | 11.4133 | 16.8265 | 24.2398 | 0
5.5831 | 8.7915 | 7.5831 | 6.5831 | 9.3746 | 11.3746 | 8.7915 | 15.3746 | 24.7492 | 36.1238 | 5.5831 | 8.7915 | 7.5931 | 6.5831 | 9.3746 | 11.3746 | 8.7915 | 15.3746 | 24.7492 | 36.1238 | 0
6.1071 | 9.0535 | 8.1071 | 7.1071 | 10.1606 | 12.1606 | 9.0535 | 16.1606 | 26.3212 | 38.4818 | 6.1071 | 9.0535 | 8.1171 | 7.1071 | 10.1606 | 12.1606 | 9.0535 | 16.1606 | 26.3212 | 38.4818 | 0
3.7728 | 7.8864 | 5.7728 | 4.7728 | 6.6592 | 8.6592 | 7.8864 | 12.6592 | 19.3184 | 27.9776 | 3.7728 | 7.8864 | 5.7828 | 4.7728 | 6.6592 | 8.6592 | 7.8864 | 12.6592 | 19.3184 | 27.9776 | 0
7.4075 | 9.7038 | 9.4075 | 8.4075 | 12.1113 | 14.1113 | 9.7038 | 18.1113 | 30.2226 | 44.3338 | 7.4075 | 9.7038 | 9.4175 | 8.4075 | 12.1113 | 14.1113 | 9.7038 | 18.1113 | 30.2226 | 44.3338 | 0
4.9966 | 8.4983 | 6.9966 | 5.9966 | 8.4948 | 10.4948 | 8.4983 | 14.4948 | 22.9897 | 33.4845 | 4.9966 | 8.4983 | 7.0066 | 5.9966 | 8.4948 | 10.4948 | 8.4983 | 14.4948 | 22.9897 | 33.4845 | 0
5.7338 | 8.8669 | 7.7338 | 6.7338 | 9.6008 | 11.6008 | 8.8669 | 15.6008 | 25.2015 | 36.8023 | 5.7338 | 8.8669 | 7.7438 | 6.7338 | 9.6008 | 11.6008 | 8.8669 | 15.6008 | 25.2015 | 36.8023 | 0
9.5995 | 10.7997 | 11.5995 | 10.5995 | 15.3992 | 17.3992 | 10.7997 | 21.3992 | 36.7984 | 54.1977 | 9.5995 | 10.7997 | 11.6095 | 10.5995 | 15.3992 | 17.3992 | 10.7997 | 21.3992 | 36.7984 | 54.1977 | 0
4.5772 | 8.2886 | 6.5772 | 5.5772 | 7.8657 | 9.8657 | 8.2886 | 13.8657 | 21.7315 | 31.5972 | 4.5772 | 8.2886 | 6.5872 | 5.5772 | 7.8657 | 9.8657 | 8.2886 | 13.8657 | 21.7315 | 31.5972 | 0
6.272 | 9.136 | 8.272 | 7.272 | 10.408 | 12.408 | 9.136 | 16.408 | 26.8161 | 39.2241 | 6.272 | 9.136 | 8.282 | 7.272 | 10.408 | 12.408 | 9.136 | 16.408 | 26.8161 | 39.2241 | 0
8.0427 | 10.0214 | 10.0427 | 9.0427 | 13.0641 | 15.0641 | 10.0214 | 19.0641 | 32.1282 | 47.1924 | 8.0427 | 10.0214 | 10.0527 | 9.0427 | 13.0641 | 15.0641 | 10.0214 | 19.0641 | 32.1282 | 47.1924 | 0
7.5719 | 9.7859 | 9.5719 | 8.5719 | 12.3578 | 14.3578 | 9.7859 | 18.3578 | 30.7157 | 45.0735 | 7.5719 | 9.7859 | 9.5819 | 8.5719 | 12.3578 | 14.3578 | 9.7859 | 18.3578 | 30.7157 | 45.0735 | 0
5.6432 | 8.8216 | 7.6432 | 6.6432 | 9.4649 | 11.4649 | 8.8216 | 15.4649 | 24.9297 | 36.3946 | 5.6432 | 8.8216 | 7.6532 | 6.6432 | 9.4649 | 11.4649 | 8.8216 | 15.4649 | 24.9297 | 36.3946 | 0
8.7355 | 10.3677 | 10.7355 | 9.7355 | 14.1032 | 16.1032 | 10.3677 | 20.1032 | 34.2065 | 50.3097 | 8.7355 | 10.3677 | 10.7455 | 9.7355 | 14.1032 | 16.1032 | 10.3677 | 20.1032 | 34.2065 | 50.3097 | 0
5.0301 | 8.515 | 7.0301 | 6.0301 | 8.5451 | 10.5451 | 8.515 | 14.5451 | 23.0902 | 33.6354 | 5.0301 | 8.515 | 7.0401 | 6.0301 | 8.5451 | 10.5451 | 8.515 | 14.5451 | 23.0902 | 33.6354 | 0
7.0523 | 9.5262 | 9.0523 | 8.0523 | 11.5785 | 13.5785 | 9.5262 | 17.5785 | 29.157 | 42.7355 | 7.0523 | 9.5262 | 9.0623 | 8.0523 | 11.5785 | 13.5785 | 9.5262 | 17.5785 | 29.157 | 42.7355 | 0
7.9439 | 9.972 | 9.9439 | 8.9439 | 12.9159 | 14.9159 | 9.972 | 18.9159 | 31.8318 | 46.7478 | 7.9439 | 9.972 | 9.9539 | 8.9439 | 12.9159 | 14.9159 | 9.972 | 18.9159 | 31.8318 | 46.7478 | 0
8.5616 | 10.2808 | 10.5616 | 9.5616 | 13.8424 | 15.8424 | 10.2808 | 19.8424 | 33.6848 | 49.5272 | 8.5616 | 10.2808 | 10.5716 | 9.5616 | 13.8424 | 15.8424 | 10.2808 | 19.8424 | 33.6848 | 49.5272 | 0
7.3831 | 9.6916 | 9.3831 | 8.3831 | 12.0747 | 14.0747 | 9.6916 | 18.0747 | 30.1494 | 44.2241 | 7.3831 | 9.6916 | 9.3931 | 8.3831 | 12.0747 | 14.0747 | 9.6916 | 18.0747 | 30.1494 | 44.2241 | 0
4.1357 | 8.0679 | 6.1357 | 5.1357 | 7.2036 | 9.2036 | 8.0679 | 13.2036 | 20.4072 | 29.6108 | 4.1357 | 8.0679 | 6.1457 | 5.1357 | 7.2036 | 9.2036 | 8.0679 | 13.2036 | 20.4072 | 29.6108 | 0
2.1727 | 7.0864 | 4.1727 | 3.1727 | 4.2591 | 6.2591 | 7.0864 | 10.2591 | 14.5182 | 20.7772 | 2.1727 | 7.0864 | 4.1827 | 3.1727 | 4.2591 | 6.2591 | 7.0864 | 10.2591 | 14.5182 | 20.7772 | 0
5.5513 | 8.7756 | 7.5513 | 6.5513 | 9.3269 | 11.3269 | 8.7756 | 15.3269 | 24.6538 | 35.9807 | 5.5513 | 8.7756 | 7.5613 | 6.5513 | 9.3269 | 11.3269 | 8.7756 | 15.3269 | 24.6538 | 35.9807 | 0
3.49 | 7.745 | 5.49 | 4.49 | 6.235 | 8.235 | 7.745 | 12.235 | 18.47 | 26.705 | 3.49 | 7.745 | 5.5 | 4.49 | 6.235 | 8.235 | 7.745 | 12.235 | 18.47 | 26.705 | 0
0.33785 | 6.1689 | 2.3378 | 1.3378 | 1.5068 | 3.5068 | 6.1689 | 7.5068 | 9.0135 | 12.5203 | 0.33785 | 6.1689 | 2.3478 | 1.3378 | 1.5068 | 3.5068 | 6.1689 | 7.5068 | 9.0135 | 12.5203 | 0
5.2149 | 8.6075 | 7.2149 | 6.2149 | 8.8224 | 10.8224 | 8.6075 | 14.8224 | 23.6448 | 34.4672 | 5.2149 | 8.6075 | 7.2249 | 6.2149 | 8.8224 | 10.8224 | 8.6075 | 14.8224 | 23.6448 | 34.4672 | 0
7.5632 | 9.7816 | 9.5632 | 8.5632 | 12.3447 | 14.3447 | 9.7816 | 18.3447 | 30.6895 | 45.0342 | 7.5632 | 9.7816 | 9.5732 | 8.5632 | 12.3447 | 14.3447 | 9.7816 | 18.3447 | 30.6895 | 45.0342 | 0
7.7902 | 9.8951 | 9.7902 | 8.7902 | 12.6853 | 14.6853 | 9.8951 | 18.6853 | 31.3705 | 46.0558 | 7.7902 | 9.8951 | 9.8002 | 8.7902 | 12.6853 | 14.6853 | 9.8951 | 18.6853 | 31.3705 | 46.0558 | 0
9.4106 | 10.7053 | 11.4106 | 10.4106 | 15.1159 | 17.1159 | 10.7053 | 21.1159 | 36.2318 | 53.3477 | 9.4106 | 10.7053 | 11.4206 | 10.4106 | 15.1159 | 17.1159 | 10.7053 | 21.1159 | 36.2318 | 53.3477 | 0
6.338 | 9.169 | 8.338 | 7.338 | 10.5069 | 12.5069 | 9.169 | 16.5069 | 27.0139 | 39.5208 | 6.338 | 9.169 | 8.348 | 7.338 | 10.5069 | 12.5069 | 9.169 | 16.5069 | 27.0139 | 39.5208 | 0
8.4698 | 10.2349 | 10.4698 | 9.4698 | 13.7047 | 15.7047 | 10.2349 | 19.7047 | 33.4094 | 49.1142 | 8.4698 | 10.2349 | 10.4798 | 9.4698 | 13.7047 | 15.7047 | 10.2349 | 19.7047 | 33.4094 | 49.1142 | 0
3.966 | 7.983 | 5.966 | 4.966 | 6.949 | 8.949 | 7.983 | 12.949 | 19.898 | 28.847 | 3.966 | 7.983 | 5.976 | 4.966 | 6.949 | 8.949 | 7.983 | 12.949 | 19.898 | 28.847 | 0
2.0788 | 7.0394 | 4.0788 | 3.0788 | 4.1183 | 6.1183 | 7.0394 | 10.1183 | 14.2365 | 20.3548 | 2.0788 | 7.0394 | 4.0888 | 3.0788 | 4.1183 | 6.1183 | 7.0394 | 10.1183 | 14.2365 | 20.3548 | 0
7.9038 | 9.9519 | 9.9038 | 8.9038 | 12.8558 | 14.8558 | 9.9519 | 18.8558 | 31.7115 | 46.5673 | 7.9038 | 9.9519 | 9.9138 | 8.9038 | 12.8558 | 14.8558 | 9.9519 | 18.8558 | 31.7115 | 46.5673 | 0
5.9358 | 8.9679 | 7.9358 | 6.9358 | 9.9037 | 11.9037 | 8.9679 | 15.9037 | 25.8074 | 37.7111 | 5.9358 | 8.9679 | 7.9458 | 6.9358 | 9.9037 | 11.9037 | 8.9679 | 15.9037 | 25.8074 | 37.7111 | 0
8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 8.0477 | 10.0238 | 10.0577 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 0
6.657 | 9.3285 | 8.657 | 7.657 | 10.9856 | 12.9856 | 9.3285 | 16.9856 | 27.9711 | 40.9567 | 6.657 | 9.3285 | 8.667 | 7.657 | 10.9856 | 12.9856 | 9.3285 | 16.9856 | 27.9711 | 40.9567 | 0
6.5966 | 9.2983 | 8.5966 | 7.5966 | 10.8949 | 12.8949 | 9.2983 | 16.8949 | 27.7899 | 40.6848 | 6.5966 | 9.2983 | 8.6066 | 7.5966 | 10.8949 | 12.8949 | 9.2983 | 16.8949 | 27.7899 | 40.6848 | 0
5.4851 | 8.7426 | 7.4851 | 6.4851 | 9.2277 | 11.2277 | 8.7426 | 15.2277 | 24.4554 | 35.683 | 5.4851 | 8.7426 | 7.4951 | 6.4851 | 9.2277 | 11.2277 | 8.7426 | 15.2277 | 24.4554 | 35.683 | 0
3.0805 | 7.5402 | 5.0805 | 4.0805 | 5.6207 | 7.6207 | 7.5402 | 11.6207 | 17.2414 | 24.8621 | 3.0805 | 7.5402 | 5.0905 | 4.0805 | 5.6207 | 7.6207 | 7.5402 | 11.6207 | 17.2414 | 24.8621 | 0
7.2083 | 9.6042 | 9.2083 | 8.2083 | 11.8125 | 13.8125 | 9.6042 | 17.8125 | 29.625 | 43.4375 | 7.2083 | 9.6042 | 9.2183 | 8.2083 | 11.8125 | 13.8125 | 9.6042 | 17.8125 | 29.625 | 43.4375 | 0
2.7006 | 7.3503 | 4.7006 | 3.7006 | 5.0509 | 7.0509 | 7.3503 | 11.0509 | 16.1017 | 23.1526 | 2.7006 | 7.3503 | 4.7106 | 3.7006 | 5.0509 | 7.0509 | 7.3503 | 11.0509 | 16.1017 | 23.1526 | 0
7.4982 | 9.7491 | 9.4982 | 8.4982 | 12.2472 | 14.2472 | 9.7491 | 18.2472 | 30.4945 | 44.7417 | 7.4982 | 9.7491 | 9.5082 | 8.4982 | 12.2472 | 14.2472 | 9.7491 | 18.2472 | 30.4945 | 44.7417 | 0
5.3544 | 8.6772 | 7.3544 | 6.3544 | 9.0316 | 11.0316 | 8.6772 | 15.0316 | 24.0632 | 35.0948 | 5.3544 | 8.6772 | 7.3644 | 6.3544 | 9.0316 | 11.0316 | 8.6772 | 15.0316 | 24.0632 | 35.0948 | 0
4.5186 | 8.2593 | 6.5186 | 5.5186 | 7.7779 | 9.7779 | 8.2593 | 13.7779 | 21.5558 | 31.3337 | 4.5186 | 8.2593 | 6.5286 | 5.5186 | 7.7779 | 9.7779 | 8.2593 | 13.7779 | 21.5558 | 31.3337 | 0
4.8309 | 8.4155 | 6.8309 | 5.8309 | 8.2464 | 10.2464 | 8.4155 | 14.2464 | 22.4927 | 32.7391 | 4.8309 | 8.4155 | 6.8409 | 5.8309 | 8.2464 | 10.2464 | 8.4155 | 14.2464 | 22.4927 | 32.7391 | 0
1.1151 | 6.5575 | 3.1151 | 2.1151 | 2.6726 | 4.6726 | 6.5575 | 8.6726 | 11.3452 | 16.0178 | 1.1151 | 6.5575 | 3.1251 | 2.1151 | 2.6726 | 4.6726 | 6.5575 | 8.6726 | 11.3452 | 16.0178 | 0
5.9719 | 8.986 | 7.9719 | 6.9719 | 9.9579 | 11.9579 | 8.986 | 15.9579 | 25.9158 | 37.8737 | 5.9719 | 8.986 | 7.9819 | 6.9719 | 9.9579 | 11.9579 | 8.986 | 15.9579 | 25.9158 | 37.8737 | 0
6.5507 | 9.2754 | 8.5507 | 7.5507 | 10.8261 | 12.8261 | 9.2754 | 16.8261 | 27.6521 | 40.4782 | 6.5507 | 9.2754 | 8.5607 | 7.5507 | 10.8261 | 12.8261 | 9.2754 | 16.8261 | 27.6521 | 40.4782 | 0
4.8226 | 8.4113 | 6.8226 | 5.8226 | 8.2338 | 10.2338 | 8.4113 | 14.2338 | 22.4677 | 32.7015 | 4.8226 | 8.4113 | 6.8326 | 5.8226 | 8.2338 | 10.2338 | 8.4113 | 14.2338 | 22.4677 | 32.7015 | 0
6.1037 | 9.0519 | 8.1037 | 7.1037 | 10.1556 | 12.1556 | 9.0519 | 16.1556 | 26.3111 | 38.4667 | 6.1037 | 9.0519 | 8.1137 | 7.1037 | 10.1556 | 12.1556 | 9.0519 | 16.1556 | 26.3111 | 38.4667 | 0
6.9292 | 9.4646 | 8.9292 | 7.9292 | 11.3937 | 13.3937 | 9.4646 | 17.3937 | 28.7875 | 42.1812 | 6.9292 | 9.4646 | 8.9392 | 7.9292 | 11.3937 | 13.3937 | 9.4646 | 17.3937 | 28.7875 | 42.1812 | 0
3.7038 | 7.8519 | 5.7038 | 4.7038 | 6.5557 | 8.5557 | 7.8519 | 12.5557 | 19.1113 | 27.667 | 3.7038 | 7.8519 | 5.7138 | 4.7038 | 6.5557 | 8.5557 | 7.8519 | 12.5557 | 19.1113 | 27.667 | 0
7.5671 | 9.7836 | 9.5671 | 8.5671 | 12.3507 | 14.3507 | 9.7836 | 18.3507 | 30.7013 | 45.052 | 7.5671 | 9.7836 | 9.5771 | 8.5671 | 12.3507 | 14.3507 | 9.7836 | 18.3507 | 30.7013 | 45.052 | 0
2.3254 | 7.1627 | 4.3254 | 3.3254 | 4.4881 | 6.4881 | 7.1627 | 10.4881 | 14.9762 | 21.4642 | 2.3254 | 7.1627 | 4.3354 | 3.3254 | 4.4881 | 6.4881 | 7.1627 | 10.4881 | 14.9762 | 21.4642 | 0
5.8236 | 8.9118 | 7.8236 | 6.8236 | 9.7354 | 11.7354 | 8.9118 | 15.7354 | 25.4708 | 37.2062 | 5.8236 | 8.9118 | 7.8336 | 6.8236 | 9.7354 | 11.7354 | 8.9118 | 15.7354 | 25.4708 | 37.2062 | 0
6.3687 | 9.1844 | 8.3687 | 7.3687 | 10.5531 | 12.5531 | 9.1844 | 16.5531 | 27.1062 | 39.6593 | 6.3687 | 9.1844 | 8.3787 | 7.3687 | 10.5531 | 12.5531 | 9.1844 | 16.5531 | 27.1062 | 39.6593 | 0
7.032 | 9.516 | 9.032 | 8.032 | 11.548 | 13.548 | 9.516 | 17.548 | 29.096 | 42.644 | 7.032 | 9.516 | 9.042 | 8.032 | 11.548 | 13.548 | 9.516 | 17.548 | 29.096 | 42.644 | 0
5.9999 | 9 | 7.9999 | 6.9999 | 9.9999 | 11.9999 | 9 | 15.9999 | 25.9998 | 37.9997 | 5.9999 | 9 | 8.0099 | 6.9999 | 9.9999 | 11.9999 | 9 | 15.9999 | 25.9998 | 37.9997 | 0
6.0206 | 9.0103 | 8.0206 | 7.0206 | 10.0309 | 12.0309 | 9.0103 | 16.0309 | 26.0617 | 38.0926 | 6.0206 | 9.0103 | 8.0306 | 7.0206 | 10.0309 | 12.0309 | 9.0103 | 16.0309 | 26.0617 | 38.0926 | 0
9.147 | 10.5735 | 11.147 | 10.147 | 14.7205 | 16.7205 | 10.5735 | 20.7205 | 35.441 | 52.1614 | 9.147 | 10.5735 | 11.157 | 10.147 | 14.7205 | 16.7205 | 10.5735 | 20.7205 | 35.441 | 52.1614 | 0
7.1056 | 9.5528 | 9.1056 | 8.1056 | 11.6584 | 13.6584 | 9.5528 | 17.6584 | 29.3168 | 42.9752 | 7.1056 | 9.5528 | 9.1156 | 8.1056 | 11.6584 | 13.6584 | 9.5528 | 17.6584 | 29.3168 | 42.9752 | 0
[8 empty] | Average | 37.4427 | [8 empty] | Average |  | 0%

## test activity D
A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | diff
1.4288 | 6.7144 | 3.4288 | 2.4288 | 3.1433 | 5.1433 | 6.7144 | 9.1433 | 12.2865 | 17.4298 | 1.4288 | 6.7144 | 3.4288 | 2.4388 | 3.1433 | 5.1433 | 6.7144 | 9.1533 | 12.2965 | 17.4398 | 0.01
2.4295 | 7.2148 | 4.4295 | 3.4295 | 4.6443 | 6.6443 | 7.2148 | 10.6443 | 15.2885 | 21.9328 | 2.4295 | 7.2148 | 4.4295 | 3.4395 | 4.6443 | 6.6443 | 7.2148 | 10.6543 | 15.2985 | 21.9428 | 0.01
4.0538 | 8.0269 | 6.0538 | 5.0538 | 7.0808 | 9.0808 | 8.0269 | 13.0808 | 20.1615 | 29.2423 | 4.0538 | 8.0269 | 6.0538 | 5.0638 | 7.0808 | 9.0808 | 8.0269 | 13.0908 | 20.1715 | 29.2523 | 0.01
6.049 | 9.0245 | 8.049 | 7.049 | 10.0736 | 12.0736 | 9.0245 | 16.0736 | 26.1471 | 38.2207 | 6.049 | 9.0245 | 8.049 | 7.059 | 10.0736 | 12.0736 | 9.0245 | 16.0836 | 26.1571 | 38.2307 | 0.01
7.3353 | 9.6677 | 9.3353 | 8.3353 | 12.003 | 14.003 | 9.6677 | 18.003 | 30.006 | 44.009 | 7.3353 | 9.6677 | 9.3353 | 8.3453 | 12.003 | 14.003 | 9.6677 | 18.013 | 30.016 | 44.019 | 0.01
5.1939 | 8.5969 | 7.1939 | 6.1939 | 8.7908 | 10.7908 | 8.5969 | 14.7908 | 23.5817 | 34.3725 | 5.1939 | 8.5969 | 7.1939 | 6.2039 | 8.7908 | 10.7908 | 8.5969 | 14.8008 | 23.5917 | 34.3825 | 0.01
7.3727 | 9.6863 | 9.3727 | 8.3727 | 12.059 | 14.059 | 9.6863 | 18.059 | 30.118 | 44.1769 | 7.3727 | 9.6863 | 9.3727 | 8.3827 | 12.059 | 14.059 | 9.6863 | 18.069 | 30.128 | 44.1869 | 0.01
2.7474 | 7.3737 | 4.7474 | 3.7474 | 5.1211 | 7.1211 | 7.3737 | 11.1211 | 16.2422 | 23.3633 | 2.7474 | 7.3737 | 4.7474 | 3.7574 | 5.1211 | 7.1211 | 7.3737 | 11.1311 | 16.2522 | 23.3733 | 0.01
7.0969 | 9.5484 | 9.0969 | 8.0969 | 11.6453 | 13.6453 | 9.5484 | 17.6453 | 29.2906 | 42.9359 | 7.0969 | 9.5484 | 9.0969 | 8.1069 | 11.6453 | 13.6453 | 9.5484 | 17.6553 | 29.3006 | 42.9459 | 0.01
4.1058 | 8.0529 | 6.1058 | 5.1058 | 7.1586 | 9.1586 | 8.0529 | 13.1586 | 20.3173 | 29.4759 | 4.1058 | 8.0529 | 6.1058 | 5.1158 | 7.1586 | 9.1586 | 8.0529 | 13.1686 | 20.3273 | 29.4859 | 0.01
7.2091 | 9.6045 | 9.2091 | 8.2091 | 11.8136 | 13.8136 | 9.6045 | 17.8136 | 29.6272 | 43.4408 | 7.2091 | 9.6045 | 9.2091 | 8.2191 | 11.8136 | 13.8136 | 9.6045 | 17.8236 | 29.6372 | 43.4508 | 0.01
10.8182 | 11.4091 | 12.8182 | 11.8182 | 17.2273 | 19.2273 | 11.4091 | 23.2273 | 40.4546 | 59.682 | 10.8182 | 11.4091 | 12.8182 | 11.8282 | 17.2273 | 19.2273 | 11.4091 | 23.2373 | 40.4646 | 59.692 | 0.01
6.4931 | 9.2465 | 8.4931 | 7.4931 | 10.7396 | 12.7396 | 9.2465 | 16.7396 | 27.4793 | 40.2189 | 6.4931 | 9.2465 | 8.4931 | 7.5031 | 10.7396 | 12.7396 | 9.2465 | 16.7496 | 27.4893 | 40.2289 | 0.01
6.0198 | 9.0099 | 8.0198 | 7.0198 | 10.0297 | 12.0297 | 9.0099 | 16.0297 | 26.0594 | 38.0892 | 6.0198 | 9.0099 | 8.0198 | 7.0298 | 10.0297 | 12.0297 | 9.0099 | 16.0397 | 26.0694 | 38.0992 | 0.01
5.2393 | 8.6197 | 7.2393 | 6.2393 | 8.859 | 10.859 | 8.6197 | 14.859 | 23.718 | 34.577 | 5.2393 | 8.6197 | 7.2393 | 6.2493 | 8.859 | 10.859 | 8.6197 | 14.869 | 23.728 | 34.587 | 0.01
5.4805 | 8.7403 | 7.4805 | 6.4805 | 9.2208 | 11.2208 | 8.7403 | 15.2208 | 24.4416 | 35.6624 | 5.4805 | 8.7403 | 7.4805 | 6.4905 | 9.2208 | 11.2208 | 8.7403 | 15.2308 | 24.4516 | 35.6724 | 0.01
3.5992 | 7.7996 | 5.5992 | 4.5992 | 6.3988 | 8.3988 | 7.7996 | 12.3988 | 18.7976 | 27.1965 | 3.5992 | 7.7996 | 5.5992 | 4.6092 | 6.3988 | 8.3988 | 7.7996 | 12.4088 | 18.8076 | 27.2065 | 0.01
2.2806 | 7.1403 | 4.2806 | 3.2806 | 4.4209 | 6.4209 | 7.1403 | 10.4209 | 14.8419 | 21.2628 | 2.2806 | 7.1403 | 4.2806 | 3.2906 | 4.4209 | 6.4209 | 7.1403 | 10.4309 | 14.8519 | 21.2728 | 0.01
6.9264 | 9.4632 | 8.9264 | 7.9264 | 11.3897 | 13.3897 | 9.4632 | 17.3897 | 28.7793 | 42.169 | 6.9264 | 9.4632 | 8.9264 | 7.9364 | 11.3897 | 13.3897 | 9.4632 | 17.3997 | 28.7893 | 42.179 | 0.01
4.5848 | 8.2924 | 6.5848 | 5.5848 | 7.8772 | 9.8772 | 8.2924 | 13.8772 | 21.7545 | 31.6317 | 4.5848 | 8.2924 | 6.5848 | 5.5948 | 7.8772 | 9.8772 | 8.2924 | 13.8872 | 21.7645 | 31.6417 | 0.01
5.8871 | 8.9436 | 7.8871 | 6.8871 | 9.8307 | 11.8307 | 8.9436 | 15.8307 | 25.6613 | 37.492 | 5.8871 | 8.9436 | 7.8871 | 6.8971 | 9.8307 | 11.8307 | 8.9436 | 15.8407 | 25.6713 | 37.502 | 0.01
4.4375 | 8.2187 | 6.4375 | 5.4375 | 7.6562 | 9.6562 | 8.2187 | 13.6562 | 21.3124 | 30.9686 | 4.4375 | 8.2187 | 6.4375 | 5.4475 | 7.6562 | 9.6562 | 8.2187 | 13.6662 | 21.3224 | 30.9786 | 0.01
5.9122 | 8.9561 | 7.9122 | 6.9122 | 9.8683 | 11.8683 | 8.9561 | 15.8683 | 25.7367 | 37.605 | 5.9122 | 8.9561 | 7.9122 | 6.9222 | 9.8683 | 11.8683 | 8.9561 | 15.8783 | 25.7467 | 37.615 | 0.01
4.2985 | 8.1493 | 6.2985 | 5.2985 | 7.4478 | 9.4478 | 8.1493 | 13.4478 | 20.8955 | 30.3433 | 4.2985 | 8.1493 | 6.2985 | 5.3085 | 7.4478 | 9.4478 | 8.1493 | 13.4578 | 20.9055 | 30.3533 | 0.01
3.7284 | 7.8642 | 5.7284 | 4.7284 | 6.5927 | 8.5927 | 7.8642 | 12.5927 | 19.1853 | 27.778 | 3.7284 | 7.8642 | 5.7284 | 4.7384 | 6.5927 | 8.5927 | 7.8642 | 12.6027 | 19.1953 | 27.788 | 0.01
7.6067 | 9.8034 | 9.6067 | 8.6067 | 12.4101 | 14.4101 | 9.8034 | 18.4101 | 30.8202 | 45.2303 | 7.6067 | 9.8034 | 9.6067 | 8.6167 | 12.4101 | 14.4101 | 9.8034 | 18.4201 | 30.8302 | 45.2403 | 0.01
8.6808 | 10.3404 | 10.6808 | 9.6808 | 14.0212 | 16.0212 | 10.3404 | 20.0212 | 34.0423 | 50.0635 | 8.6808 | 10.3404 | 10.6808 | 9.6908 | 14.0212 | 16.0212 | 10.3404 | 20.0312 | 34.0523 | 50.0735 | 0.01
5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 5.2196 | 8.6098 | 7.2196 | 6.2296 | 8.8293 | 10.8293 | 8.6098 | 14.8393 | 23.6687 | 34.498 | 0.01
7.6331 | 9.8165 | 9.6331 | 8.6331 | 12.4496 | 14.4496 | 9.8165 | 18.4496 | 30.8992 | 45.3488 | 7.6331 | 9.8165 | 9.6331 | 8.6431 | 12.4496 | 14.4496 | 9.8165 | 18.4596 | 30.9092 | 45.3588 | 0.01
4.2833 | 8.1416 | 6.2833 | 5.2833 | 7.4249 | 9.4249 | 8.1416 | 13.4249 | 20.8499 | 30.2748 | 4.2833 | 8.1416 | 6.2833 | 5.2933 | 7.4249 | 9.4249 | 8.1416 | 13.4349 | 20.8599 | 30.2848 | 0.01
4.5407 | 8.2703 | 6.5407 | 5.5407 | 7.811 | 9.811 | 8.2703 | 13.811 | 21.622 | 31.433 | 4.5407 | 8.2703 | 6.5407 | 5.5507 | 7.811 | 9.811 | 8.2703 | 13.821 | 21.632 | 31.443 | 0.01
6.1115 | 9.0558 | 8.1115 | 7.1115 | 10.1673 | 12.1673 | 9.0558 | 16.1673 | 26.3345 | 38.5018 | 6.1115 | 9.0558 | 8.1115 | 7.1215 | 10.1673 | 12.1673 | 9.0558 | 16.1773 | 26.3445 | 38.5118 | 0.01
6.1999 | 9.1 | 8.1999 | 7.1999 | 10.2999 | 12.2999 | 9.1 | 16.2999 | 26.5997 | 38.8996 | 6.1999 | 9.1 | 8.1999 | 7.2099 | 10.2999 | 12.2999 | 9.1 | 16.3099 | 26.6097 | 38.9096 | 0.01
2.8161 | 7.408 | 4.8161 | 3.8161 | 5.2241 | 7.2241 | 7.408 | 11.2241 | 16.4482 | 23.6723 | 2.8161 | 7.408 | 4.8161 | 3.8261 | 5.2241 | 7.2241 | 7.408 | 11.2341 | 16.4582 | 23.6823 | 0.01
6.6314 | 9.3157 | 8.6314 | 7.6314 | 10.9471 | 12.9471 | 9.3157 | 16.9471 | 27.8943 | 40.8414 | 6.6314 | 9.3157 | 8.6314 | 7.6414 | 10.9471 | 12.9471 | 9.3157 | 16.9571 | 27.9043 | 40.8514 | 0.01
6.5394 | 9.2697 | 8.5394 | 7.5394 | 10.8092 | 12.8092 | 9.2697 | 16.8092 | 27.6183 | 40.4275 | 6.5394 | 9.2697 | 8.5394 | 7.5494 | 10.8092 | 12.8092 | 9.2697 | 16.8192 | 27.6283 | 40.4375 | 0.01
11.0521 | 11.526 | 13.0521 | 12.0521 | 17.5781 | 19.5781 | 11.526 | 23.5781 | 41.1562 | 60.7343 | 11.0521 | 11.526 | 13.0521 | 12.0621 | 17.5781 | 19.5781 | 11.526 | 23.5881 | 41.1662 | 60.7443 | 0.01
3.8102 | 7.9051 | 5.8102 | 4.8102 | 6.7153 | 8.7153 | 7.9051 | 12.7153 | 19.4307 | 28.146 | 3.8102 | 7.9051 | 5.8102 | 4.8202 | 6.7153 | 8.7153 | 7.9051 | 12.7253 | 19.4407 | 28.156 | 0.01
5.2518 | 8.6259 | 7.2518 | 6.2518 | 8.8777 | 10.8777 | 8.6259 | 14.8777 | 23.7554 | 34.6332 | 5.2518 | 8.6259 | 7.2518 | 6.2618 | 8.8777 | 10.8777 | 8.6259 | 14.8877 | 23.7654 | 34.6432 | 0.01
6.3771 | 9.1886 | 8.3771 | 7.3771 | 10.5657 | 12.5657 | 9.1886 | 16.5657 | 27.1314 | 39.6971 | 6.3771 | 9.1886 | 8.3771 | 7.3871 | 10.5657 | 12.5657 | 9.1886 | 16.5757 | 27.1414 | 39.7071 | 0.01
5.3383 | 8.6691 | 7.3383 | 6.3383 | 9.0074 | 11.0074 | 8.6691 | 15.0074 | 24.0148 | 35.0222 | 5.3383 | 8.6691 | 7.3383 | 6.3483 | 9.0074 | 11.0074 | 8.6691 | 15.0174 | 24.0248 | 35.0322 | 0.01
8.3948 | 10.1974 | 10.3948 | 9.3948 | 13.5922 | 15.5922 | 10.1974 | 19.5922 | 33.1845 | 48.7767 | 8.3948 | 10.1974 | 10.3948 | 9.4048 | 13.5922 | 15.5922 | 10.1974 | 19.6022 | 33.1945 | 48.7867 | 0.01
5.0712 | 8.5356 | 7.0712 | 6.0712 | 8.6068 | 10.6068 | 8.5356 | 14.6068 | 23.2135 | 33.8203 | 5.0712 | 8.5356 | 7.0712 | 6.0812 | 8.6068 | 10.6068 | 8.5356 | 14.6168 | 23.2235 | 33.8303 | 0.01
6.1543 | 9.0771 | 8.1543 | 7.1543 | 10.2314 | 12.2314 | 9.0771 | 16.2314 | 26.4629 | 38.6943 | 6.1543 | 9.0771 | 8.1543 | 7.1643 | 10.2314 | 12.2314 | 9.0771 | 16.2414 | 26.4729 | 38.7043 | 0.01
5.863 | 8.9315 | 7.863 | 6.863 | 9.7946 | 11.7946 | 8.9315 | 15.7946 | 25.5891 | 37.3837 | 5.863 | 8.9315 | 7.863 | 6.873 | 9.7946 | 11.7946 | 8.9315 | 15.8046 | 25.5991 | 37.3937 | 0.01
2.5835 | 7.2917 | 4.5835 | 3.5835 | 4.8752 | 6.8752 | 7.2917 | 10.8752 | 15.7504 | 22.6257 | 2.5835 | 7.2917 | 4.5835 | 3.5935 | 4.8752 | 6.8752 | 7.2917 | 10.8852 | 15.7604 | 22.6357 | 0.01
5.0249 | 8.5125 | 7.0249 | 6.0249 | 8.5374 | 10.5374 | 8.5125 | 14.5374 | 23.0747 | 33.6121 | 5.0249 | 8.5125 | 7.0249 | 6.0349 | 8.5374 | 10.5374 | 8.5125 | 14.5474 | 23.0847 | 33.6221 | 0.01
6.1918 | 9.0959 | 8.1918 | 7.1918 | 10.2877 | 12.2877 | 9.0959 | 16.2877 | 26.5753 | 38.863 | 6.1918 | 9.0959 | 8.1918 | 7.2018 | 10.2877 | 12.2877 | 9.0959 | 16.2977 | 26.5853 | 38.873 | 0.01
5.0897 | 8.5449 | 7.0897 | 6.0897 | 8.6346 | 10.6346 | 8.5449 | 14.6346 | 23.2691 | 33.9037 | 5.0897 | 8.5449 | 7.0897 | 6.0997 | 8.6346 | 10.6346 | 8.5449 | 14.6446 | 23.2791 | 33.9137 | 0.01
5.4889 | 8.7445 | 7.4889 | 6.4889 | 9.2334 | 11.2334 | 8.7445 | 15.2334 | 24.4667 | 35.7001 | 5.4889 | 8.7445 | 7.4889 | 6.4989 | 9.2334 | 11.2334 | 8.7445 | 15.2434 | 24.4767 | 35.7101 | 0.01
8.7445 | 10.3722 | 10.7445 | 9.7445 | 14.1167 | 16.1167 | 10.3722 | 20.1167 | 34.2334 | 50.3502 | 8.7445 | 10.3722 | 10.7445 | 9.7545 | 14.1167 | 16.1167 | 10.3722 | 20.1267 | 34.2434 | 50.3602 | 0.01
6.1328 | 9.0664 | 8.1328 | 7.1328 | 10.1992 | 12.1992 | 9.0664 | 16.1992 | 26.3985 | 38.5977 | 6.1328 | 9.0664 | 8.1328 | 7.1428 | 10.1992 | 12.1992 | 9.0664 | 16.2092 | 26.4085 | 38.6077 | 0.01
6.4019 | 9.201 | 8.4019 | 7.4019 | 10.6029 | 12.6029 | 9.201 | 16.6029 | 27.2058 | 39.8087 | 6.4019 | 9.201 | 8.4019 | 7.4119 | 10.6029 | 12.6029 | 9.201 | 16.6129 | 27.2158 | 39.8187 | 0.01
4.0371 | 8.0185 | 6.0371 | 5.0371 | 7.0556 | 9.0556 | 8.0185 | 13.0556 | 20.1112 | 29.1668 | 4.0371 | 8.0185 | 6.0371 | 5.0471 | 7.0556 | 9.0556 | 8.0185 | 13.0656 | 20.1212 | 29.1768 | 0.01
5.83 | 8.915 | 7.83 | 6.83 | 9.7451 | 11.7451 | 8.915 | 15.7451 | 25.4901 | 37.2352 | 5.83 | 8.915 | 7.83 | 6.84 | 9.7451 | 11.7451 | 8.915 | 15.7551 | 25.5001 | 37.2452 | 0.01
2.6753 | 7.3376 | 4.6753 | 3.6753 | 5.0129 | 7.0129 | 7.3376 | 11.0129 | 16.0258 | 23.0387 | 2.6753 | 7.3376 | 4.6753 | 3.6853 | 5.0129 | 7.0129 | 7.3376 | 11.0229 | 16.0358 | 23.0487 | 0.01
5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 5.3559 | 8.6779 | 7.3559 | 6.3659 | 9.0338 | 11.0338 | 8.6779 | 15.0438 | 24.0776 | 35.1113 | 0.01
2.6862 | 7.3431 | 4.6862 | 3.6862 | 5.0293 | 7.0293 | 7.3431 | 11.0293 | 16.0585 | 23.0878 | 2.6862 | 7.3431 | 4.6862 | 3.6962 | 5.0293 | 7.0293 | 7.3431 | 11.0393 | 16.0685 | 23.0978 | 0.01
9.7341 | 10.8671 | 11.7341 | 10.7341 | 15.6012 | 17.6012 | 10.8671 | 21.6012 | 37.2024 | 54.8037 | 9.7341 | 10.8671 | 11.7341 | 10.7441 | 15.6012 | 17.6012 | 10.8671 | 21.6112 | 37.2124 | 54.8137 | 0.01
4.1077 | 8.0538 | 6.1077 | 5.1077 | 7.1615 | 9.1615 | 8.0538 | 13.1615 | 20.323 | 29.4845 | 4.1077 | 8.0538 | 6.1077 | 5.1177 | 7.1615 | 9.1615 | 8.0538 | 13.1715 | 20.333 | 29.4945 | 0.01
7.484 | 9.742 | 9.484 | 8.484 | 12.226 | 14.226 | 9.742 | 18.226 | 30.452 | 44.6781 | 7.484 | 9.742 | 9.484 | 8.494 | 12.226 | 14.226 | 9.742 | 18.236 | 30.462 | 44.6881 | 0.01
6.2666 | 9.1333 | 8.2666 | 7.2666 | 10.3999 | 12.3999 | 9.1333 | 16.3999 | 26.7999 | 39.1998 | 6.2666 | 9.1333 | 8.2666 | 7.2766 | 10.3999 | 12.3999 | 9.1333 | 16.4099 | 26.8099 | 39.2098 | 0.01
5.2959 | 8.648 | 7.2959 | 6.2959 | 8.9439 | 10.9439 | 8.648 | 14.9439 | 23.8878 | 34.8317 | 5.2959 | 8.648 | 7.2959 | 6.3059 | 8.9439 | 10.9439 | 8.648 | 14.9539 | 23.8978 | 34.8417 | 0.01
4.8999 | 8.45 | 6.8999 | 5.8999 | 8.3499 | 10.3499 | 8.45 | 14.3499 | 22.6998 | 33.0497 | 4.8999 | 8.45 | 6.8999 | 5.9099 | 8.3499 | 10.3499 | 8.45 | 14.3599 | 22.7098 | 33.0597 | 0.01
5.8151 | 8.9076 | 7.8151 | 6.8151 | 9.7227 | 11.7227 | 8.9076 | 15.7227 | 25.4454 | 37.1682 | 5.8151 | 8.9076 | 7.8151 | 6.8251 | 9.7227 | 11.7227 | 8.9076 | 15.7327 | 25.4554 | 37.1782 | 0.01
5.9292 | 8.9646 | 7.9292 | 6.9292 | 9.8938 | 11.8938 | 8.9646 | 15.8938 | 25.7877 | 37.6815 | 5.9292 | 8.9646 | 7.9292 | 6.9392 | 9.8938 | 11.8938 | 8.9646 | 15.9038 | 25.7977 | 37.6915 | 0.01
2.9022 | 7.4511 | 4.9022 | 3.9022 | 5.3533 | 7.3533 | 7.4511 | 11.3533 | 16.7065 | 24.0598 | 2.9022 | 7.4511 | 4.9022 | 3.9122 | 5.3533 | 7.3533 | 7.4511 | 11.3633 | 16.7165 | 24.0698 | 0.01
3.7424 | 7.8712 | 5.7424 | 4.7424 | 6.6136 | 8.6136 | 7.8712 | 12.6136 | 19.2272 | 27.8407 | 3.7424 | 7.8712 | 5.7424 | 4.7524 | 6.6136 | 8.6136 | 7.8712 | 12.6236 | 19.2372 | 27.8507 | 0.01
8.3173 | 10.1587 | 10.3173 | 9.3173 | 13.476 | 15.476 | 10.1587 | 19.476 | 32.952 | 48.4281 | 8.3173 | 10.1587 | 10.3173 | 9.3273 | 13.476 | 15.476 | 10.1587 | 19.486 | 32.962 | 48.4381 | 0.01
4.7975 | 8.3988 | 6.7975 | 5.7975 | 8.1963 | 10.1963 | 8.3988 | 14.1963 | 22.3926 | 32.5889 | 4.7975 | 8.3988 | 6.7975 | 5.8075 | 8.1963 | 10.1963 | 8.3988 | 14.2063 | 22.4026 | 32.5989 | 0.01
4.0727 | 8.0363 | 6.0727 | 5.0727 | 7.109 | 9.109 | 8.0363 | 13.109 | 20.218 | 29.327 | 4.0727 | 8.0363 | 6.0727 | 5.0827 | 7.109 | 9.109 | 8.0363 | 13.119 | 20.228 | 29.337 | 0.01
7.2028 | 9.6014 | 9.2028 | 8.2028 | 11.8042 | 13.8042 | 9.6014 | 17.8042 | 29.6085 | 43.4127 | 7.2028 | 9.6014 | 9.2028 | 8.2128 | 11.8042 | 13.8042 | 9.6014 | 17.8142 | 29.6185 | 43.4227 | 0.01
5.1967 | 8.5984 | 7.1967 | 6.1967 | 8.7951 | 10.7951 | 8.5984 | 14.7951 | 23.5902 | 34.3852 | 5.1967 | 8.5984 | 7.1967 | 6.2067 | 8.7951 | 10.7951 | 8.5984 | 14.8051 | 23.6002 | 34.3952 | 0.01
3.0576 | 7.5288 | 5.0576 | 4.0576 | 5.5864 | 7.5864 | 7.5288 | 11.5864 | 17.1729 | 24.7593 | 3.0576 | 7.5288 | 5.0576 | 4.0676 | 5.5864 | 7.5864 | 7.5288 | 11.5964 | 17.1829 | 24.7693 | 0.01
4.772 | 8.386 | 6.772 | 5.772 | 8.1579 | 10.1579 | 8.386 | 14.1579 | 22.3159 | 32.4738 | 4.772 | 8.386 | 6.772 | 5.782 | 8.1579 | 10.1579 | 8.386 | 14.1679 | 22.3259 | 32.4838 | 0.01
6.9343 | 9.4671 | 8.9343 | 7.9343 | 11.4014 | 13.4014 | 9.4671 | 17.4014 | 28.8028 | 42.2043 | 6.9343 | 9.4671 | 8.9343 | 7.9443 | 11.4014 | 13.4014 | 9.4671 | 17.4114 | 28.8128 | 42.2143 | 0.01
5.9782 | 8.9891 | 7.9782 | 6.9782 | 9.9673 | 11.9673 | 8.9891 | 15.9673 | 25.9346 | 37.9019 | 5.9782 | 8.9891 | 7.9782 | 6.9882 | 9.9673 | 11.9673 | 8.9891 | 15.9773 | 25.9446 | 37.9119 | 0.01
4.3539 | 8.1769 | 6.3539 | 5.3539 | 7.5308 | 9.5308 | 8.1769 | 13.5308 | 21.0616 | 30.5925 | 4.3539 | 8.1769 | 6.3539 | 5.3639 | 7.5308 | 9.5308 | 8.1769 | 13.5408 | 21.0716 | 30.6025 | 0.01
4.4273 | 8.2136 | 6.4273 | 5.4273 | 7.6409 | 9.6409 | 8.2136 | 13.6409 | 21.2818 | 30.9227 | 4.4273 | 8.2136 | 6.4273 | 5.4373 | 7.6409 | 9.6409 | 8.2136 | 13.6509 | 21.2918 | 30.9327 | 0.01
5.6648 | 8.8324 | 7.6648 | 6.6648 | 9.4972 | 11.4972 | 8.8324 | 15.4972 | 24.9945 | 36.4917 | 5.6648 | 8.8324 | 7.6648 | 6.6748 | 9.4972 | 11.4972 | 8.8324 | 15.5072 | 25.0045 | 36.5017 | 0.01
6.1502 | 9.0751 | 8.1502 | 7.1502 | 10.2252 | 12.2252 | 9.0751 | 16.2252 | 26.4505 | 38.6757 | 6.1502 | 9.0751 | 8.1502 | 7.1602 | 10.2252 | 12.2252 | 9.0751 | 16.2352 | 26.4605 | 38.6857 | 0.01
13.0455 | 12.5227 | 15.0455 | 14.0455 | 20.5682 | 22.5682 | 13.0455 | 27.0909 | 47.6591 | 70.2273 | 13.0455 | 12.5227 | 15.0455 | 14.0555 | 20.5682 | 22.5682 | 13.0455 | 27.1009 | 47.6691 | 70.2373 | 0.01
7.6173 | 9.8087 | 9.6173 | 8.6173 | 12.426 | 14.426 | 9.8087 | 18.426 | 30.8519 | 45.2779 | 7.6173 | 9.8087 | 9.6173 | 8.6273 | 12.426 | 14.426 | 9.8087 | 18.436 | 30.8619 | 45.2879 | 0.01
8.3774 | 10.1887 | 10.3774 | 9.3774 | 13.566 | 15.566 | 10.1887 | 19.566 | 33.1321 | 48.6981 | 8.3774 | 10.1887 | 10.3774 | 9.3874 | 13.566 | 15.566 | 10.1887 | 19.576 | 33.1421 | 48.7081 | 0.01
6.074 | 9.037 | 8.074 | 7.074 | 10.111 | 12.111 | 9.037 | 16.111 | 26.222 | 38.333 | 6.074 | 9.037 | 8.074 | 7.084 | 10.111 | 12.111 | 9.037 | 16.121 | 26.232 | 38.343 | 0.01
5.9353 | 8.9677 | 7.9353 | 6.9353 | 9.903 | 11.903 | 8.9677 | 15.903 | 25.806 | 37.7091 | 5.9353 | 8.9677 | 7.9353 | 6.9453 | 9.903 | 11.903 | 8.9677 | 15.913 | 25.816 | 37.7191 | 0.01
6.9629 | 9.4814 | 8.9629 | 7.9629 | 11.4443 | 13.4443 | 9.4814 | 17.4443 | 28.8886 | 42.3329 | 6.9629 | 9.4814 | 8.9629 | 7.9729 | 11.4443 | 13.4443 | 9.4814 | 17.4543 | 28.8986 | 42.3429 | 0.01
3.2723 | 7.6361 | 5.2723 | 4.2723 | 5.9084 | 7.9084 | 7.6361 | 11.9084 | 17.8169 | 25.7253 | 3.2723 | 7.6361 | 5.2723 | 4.2823 | 5.9084 | 7.9084 | 7.6361 | 11.9184 | 17.8269 | 25.7353 | 0.01
5.3875 | 8.6938 | 7.3875 | 6.3875 | 9.0813 | 11.0813 | 8.6938 | 15.0813 | 24.1626 | 35.2438 | 5.3875 | 8.6938 | 7.3875 | 6.3975 | 9.0813 | 11.0813 | 8.6938 | 15.0913 | 24.1726 | 35.2538 | 0.01
2.8991 | 7.4496 | 4.8991 | 3.8991 | 5.3487 | 7.3487 | 7.4496 | 11.3487 | 16.6974 | 24.0461 | 2.8991 | 7.4496 | 4.8991 | 3.9091 | 5.3487 | 7.3487 | 7.4496 | 11.3587 | 16.7074 | 24.0561 | 0.01
6.8927 | 9.4463 | 8.8927 | 7.8927 | 11.339 | 13.339 | 9.4463 | 17.339 | 28.678 | 42.017 | 6.8927 | 9.4463 | 8.8927 | 7.9027 | 11.339 | 13.339 | 9.4463 | 17.349 | 28.688 | 42.027 | 0.01
5.2946 | 8.6473 | 7.2946 | 6.2946 | 8.942 | 10.942 | 8.6473 | 14.942 | 23.8839 | 34.8259 | 5.2946 | 8.6473 | 7.2946 | 6.3046 | 8.942 | 10.942 | 8.6473 | 14.952 | 23.8939 | 34.8359 | 0.01
7.3723 | 9.6861 | 9.3723 | 8.3723 | 12.0584 | 14.0584 | 9.6861 | 18.0584 | 30.1168 | 44.1752 | 7.3723 | 9.6861 | 9.3723 | 8.3823 | 12.0584 | 14.0584 | 9.6861 | 18.0684 | 30.1268 | 44.1852 | 0.01
6.4354 | 9.2177 | 8.4354 | 7.4354 | 10.6531 | 12.6531 | 9.2177 | 16.6531 | 27.3062 | 39.9593 | 6.4354 | 9.2177 | 8.4354 | 7.4454 | 10.6531 | 12.6531 | 9.2177 | 16.6631 | 27.3162 | 39.9693 | 0.01
5.4793 | 8.7396 | 7.4793 | 6.4793 | 9.2189 | 11.2189 | 8.7396 | 15.2189 | 24.4378 | 35.6567 | 5.4793 | 8.7396 | 7.4793 | 6.4893 | 9.2189 | 11.2189 | 8.7396 | 15.2289 | 24.4478 | 35.6667 | 0.01
6.2472 | 9.1236 | 8.2472 | 7.2472 | 10.3708 | 12.3708 | 9.1236 | 16.3708 | 26.7415 | 39.1123 | 6.2472 | 9.1236 | 8.2472 | 7.2572 | 10.3708 | 12.3708 | 9.1236 | 16.3808 | 26.7515 | 39.1223 | 0.01
4.9739 | 8.487 | 6.9739 | 5.9739 | 8.4609 | 10.4609 | 8.487 | 14.4609 | 22.9218 | 33.3827 | 4.9739 | 8.487 | 6.9739 | 5.9839 | 8.4609 | 10.4609 | 8.487 | 14.4709 | 22.9318 | 33.3927 | 0.01
1.3058 | 6.6529 | 3.3058 | 2.3058 | 2.9588 | 4.9588 | 6.6529 | 8.9588 | 11.9175 | 16.8763 | 1.3058 | 6.6529 | 3.3058 | 2.3158 | 2.9588 | 4.9588 | 6.6529 | 8.9688 | 11.9275 | 16.8863 | 0.01
6.9362 | 9.4681 | 8.9362 | 7.9362 | 11.4042 | 13.4042 | 9.4681 | 17.4042 | 28.8085 | 42.2127 | 6.9362 | 9.4681 | 8.9362 | 7.9462 | 11.4042 | 13.4042 | 9.4681 | 17.4142 | 28.8185 | 42.2227 | 0.01
7.1438 | 9.5719 | 9.1438 | 8.1438 | 11.7157 | 13.7157 | 9.5719 | 17.7157 | 29.4313 | 43.147 | 7.1438 | 9.5719 | 9.1438 | 8.1538 | 11.7157 | 13.7157 | 9.5719 | 17.7257 | 29.4413 | 43.157 | 0.01
7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 7.2523 | 9.6262 | 9.2523 | 8.2623 | 11.8785 | 13.8785 | 9.6262 | 17.8885 | 29.767 | 43.6455 | 0.01
10.4708 | 11.2354 | 12.4708 | 11.4708 | 16.7062 | 18.7062 | 11.2354 | 22.7062 | 39.4124 | 58.1185 | 10.4708 | 11.2354 | 12.4708 | 11.4808 | 16.7062 | 18.7062 | 11.2354 | 22.7162 | 39.4224 | 58.1285 | 0.01
7.3244 | 9.6622 | 9.3244 | 8.3244 | 11.9867 | 13.9867 | 9.6622 | 17.9867 | 29.9733 | 43.96 | 7.3244 | 9.6622 | 9.3244 | 8.3344 | 11.9867 | 13.9867 | 9.6622 | 17.9967 | 29.9833 | 43.97 | 0.01
3.4391 | 7.7195 | 5.4391 | 4.4391 | 6.1586 | 8.1586 | 7.7195 | 12.1586 | 18.3173 | 26.4759 | 3.4391 | 7.7195 | 5.4391 | 4.4491 | 6.1586 | 8.1586 | 7.7195 | 12.1686 | 18.3273 | 26.4859 | 0.01
3.4033 | 7.7016 | 5.4033 | 4.4033 | 6.1049 | 8.1049 | 7.7016 | 12.1049 | 18.2098 | 26.3146 | 3.4033 | 7.7016 | 5.4033 | 4.4133 | 6.1049 | 8.1049 | 7.7016 | 12.1149 | 18.2198 | 26.3246 | 0.01
6.3856 | 9.1928 | 8.3856 | 7.3856 | 10.5783 | 12.5783 | 9.1928 | 16.5783 | 27.1567 | 39.735 | 6.3856 | 9.1928 | 8.3856 | 7.3956 | 10.5783 | 12.5783 | 9.1928 | 16.5883 | 27.1667 | 39.745 | 0.01
4.8622 | 8.4311 | 6.8622 | 5.8622 | 8.2933 | 10.2933 | 8.4311 | 14.2933 | 22.5865 | 32.8798 | 4.8622 | 8.4311 | 6.8622 | 5.8722 | 8.2933 | 10.2933 | 8.4311 | 14.3033 | 22.5965 | 32.8898 | 0.01
6.2649 | 9.1325 | 8.2649 | 7.2649 | 10.3974 | 12.3974 | 9.1325 | 16.3974 | 26.7948 | 39.1921 | 6.2649 | 9.1325 | 8.2649 | 7.2749 | 10.3974 | 12.3974 | 9.1325 | 16.4074 | 26.8048 | 39.2021 | 0.01
6.3815 | 9.1908 | 8.3815 | 7.3815 | 10.5723 | 12.5723 | 9.1908 | 16.5723 | 27.1445 | 39.7168 | 6.3815 | 9.1908 | 8.3815 | 7.3915 | 10.5723 | 12.5723 | 9.1908 | 16.5823 | 27.1545 | 39.7268 | 0.01
6.0503 | 9.0251 | 8.0503 | 7.0503 | 10.0754 | 12.0754 | 9.0251 | 16.0754 | 26.1508 | 38.2262 | 6.0503 | 9.0251 | 8.0503 | 7.0603 | 10.0754 | 12.0754 | 9.0251 | 16.0854 | 26.1608 | 38.2362 | 0.01
7.3199 | 9.6599 | 9.3199 | 8.3199 | 11.9798 | 13.9798 | 9.6599 | 17.9798 | 29.9596 | 43.9394 | 7.3199 | 9.6599 | 9.3199 | 8.3299 | 11.9798 | 13.9798 | 9.6599 | 17.9898 | 29.9696 | 43.9494 | 0.01
4.8278 | 8.4139 | 6.8278 | 5.8278 | 8.2417 | 10.2417 | 8.4139 | 14.2417 | 22.4835 | 32.7252 | 4.8278 | 8.4139 | 6.8278 | 5.8378 | 8.2417 | 10.2417 | 8.4139 | 14.2517 | 22.4935 | 32.7352 | 0.01
5.4652 | 8.7326 | 7.4652 | 6.4652 | 9.1977 | 11.1977 | 8.7326 | 15.1977 | 24.3955 | 35.5932 | 5.4652 | 8.7326 | 7.4652 | 6.4752 | 9.1977 | 11.1977 | 8.7326 | 15.2077 | 24.4055 | 35.6032 | 0.01
3.3593 | 7.6796 | 5.3593 | 4.3593 | 6.0389 | 8.0389 | 7.6796 | 12.0389 | 18.0778 | 26.1167 | 3.3593 | 7.6796 | 5.3593 | 4.3693 | 6.0389 | 8.0389 | 7.6796 | 12.0489 | 18.0878 | 26.1267 | 0.01
7.5124 | 9.7562 | 9.5124 | 8.5124 | 12.2686 | 14.2686 | 9.7562 | 18.2686 | 30.5371 | 44.8057 | 7.5124 | 9.7562 | 9.5124 | 8.5224 | 12.2686 | 14.2686 | 9.7562 | 18.2786 | 30.5471 | 44.8157 | 0.01
3.9132 | 7.9566 | 5.9132 | 4.9132 | 6.8698 | 8.8698 | 7.9566 | 12.8698 | 19.7396 | 28.6094 | 3.9132 | 7.9566 | 5.9132 | 4.9232 | 6.8698 | 8.8698 | 7.9566 | 12.8798 | 19.7496 | 28.6194 | 0.01
1.5199 | 6.7599 | 3.5199 | 2.5199 | 3.2798 | 5.2798 | 6.7599 | 9.2798 | 12.5596 | 17.8394 | 1.5199 | 6.7599 | 3.5199 | 2.5299 | 3.2798 | 5.2798 | 6.7599 | 9.2898 | 12.5696 | 17.8494 | 0.01
4.6499 | 8.325 | 6.6499 | 5.6499 | 7.9749 | 9.9749 | 8.325 | 13.9749 | 21.9497 | 31.9246 | 4.6499 | 8.325 | 6.6499 | 5.6599 | 7.9749 | 9.9749 | 8.325 | 13.9849 | 21.9597 | 31.9346 | 0.01
4.3616 | 8.1808 | 6.3616 | 5.3616 | 7.5424 | 9.5424 | 8.1808 | 13.5424 | 21.0848 | 30.6272 | 4.3616 | 8.1808 | 6.3616 | 5.3716 | 7.5424 | 9.5424 | 8.1808 | 13.5524 | 21.0948 | 30.6372 | 0.01
5.2767 | 8.6383 | 7.2767 | 6.2767 | 8.915 | 10.915 | 8.6383 | 14.915 | 23.8301 | 34.7451 | 5.2767 | 8.6383 | 7.2767 | 6.2867 | 8.915 | 10.915 | 8.6383 | 14.925 | 23.8401 | 34.7551 | 0.01
4.6809 | 8.3404 | 6.6809 | 5.6809 | 8.0213 | 10.0213 | 8.3404 | 14.0213 | 22.0426 | 32.064 | 4.6809 | 8.3404 | 6.6809 | 5.6909 | 8.0213 | 10.0213 | 8.3404 | 14.0313 | 22.0526 | 32.074 | 0.01
7.3392 | 9.6696 | 9.3392 | 8.3392 | 12.0087 | 14.0087 | 9.6696 | 18.0087 | 30.0175 | 44.0262 | 7.3392 | 9.6696 | 9.3392 | 8.3492 | 12.0087 | 14.0087 | 9.6696 | 18.0187 | 30.0275 | 44.0362 | 0.01
5.9878 | 8.9939 | 7.9878 | 6.9878 | 9.9818 | 11.9818 | 8.9939 | 15.9818 | 25.9635 | 37.9453 | 5.9878 | 8.9939 | 7.9878 | 6.9978 | 9.9818 | 11.9818 | 8.9939 | 15.9918 | 25.9735 | 37.9553 | 0.01
7.2575 | 9.6288 | 9.2575 | 8.2575 | 11.8863 | 13.8863 | 9.6288 | 17.8863 | 29.7726 | 43.659 | 7.2575 | 9.6288 | 9.2575 | 8.2675 | 11.8863 | 13.8863 | 9.6288 | 17.8963 | 29.7826 | 43.669 | 0.01
6.2064 | 9.1032 | 8.2064 | 7.2064 | 10.3096 | 12.3096 | 9.1032 | 16.3096 | 26.6191 | 38.9287 | 6.2064 | 9.1032 | 8.2064 | 7.2164 | 10.3096 | 12.3096 | 9.1032 | 16.3196 | 26.6291 | 38.9387 | 0.01
3.8799 | 7.94 | 5.8799 | 4.8799 | 6.8199 | 8.8199 | 7.94 | 12.8199 | 19.6398 | 28.4598 | 3.8799 | 7.94 | 5.8799 | 4.8899 | 6.8199 | 8.8199 | 7.94 | 12.8299 | 19.6498 | 28.4698 | 0.01
2.4504 | 7.2252 | 4.4504 | 3.4504 | 4.6756 | 6.6756 | 7.2252 | 10.6756 | 15.3512 | 22.0267 | 2.4504 | 7.2252 | 4.4504 | 3.4604 | 4.6756 | 6.6756 | 7.2252 | 10.6856 | 15.3612 | 22.0367 | 0.01
5.7233 | 8.8617 | 7.7233 | 6.7233 | 9.585 | 11.585 | 8.8617 | 15.585 | 25.17 | 36.755 | 5.7233 | 8.8617 | 7.7233 | 6.7333 | 9.585 | 11.585 | 8.8617 | 15.595 | 25.18 | 36.765 | 0.01
8.2167 | 10.1084 | 10.2167 | 9.2167 | 13.3251 | 15.3251 | 10.1084 | 19.3251 | 32.6501 | 47.9752 | 8.2167 | 10.1084 | 10.2167 | 9.2267 | 13.3251 | 15.3251 | 10.1084 | 19.3351 | 32.6601 | 47.9852 | 0.01
5.8225 | 8.9113 | 7.8225 | 6.8225 | 9.7338 | 11.7338 | 8.9113 | 15.7338 | 25.4676 | 37.2013 | 5.8225 | 8.9113 | 7.8225 | 6.8325 | 9.7338 | 11.7338 | 8.9113 | 15.7438 | 25.4776 | 37.2113 | 0.01
4.44 | 8.22 | 6.44 | 5.44 | 7.6599 | 9.6599 | 8.22 | 13.6599 | 21.3199 | 30.9798 | 4.44 | 8.22 | 6.44 | 5.45 | 7.6599 | 9.6599 | 8.22 | 13.6699 | 21.3299 | 30.9898 | 0.01
5.5445 | 8.7723 | 7.5445 | 6.5445 | 9.3168 | 11.3168 | 8.7723 | 15.3168 | 24.6336 | 35.9503 | 5.5445 | 8.7723 | 7.5445 | 6.5545 | 9.3168 | 11.3168 | 8.7723 | 15.3268 | 24.6436 | 35.9603 | 0.01
6.9782 | 9.4891 | 8.9782 | 7.9782 | 11.4673 | 13.4673 | 9.4891 | 17.4673 | 28.9346 | 42.4018 | 6.9782 | 9.4891 | 8.9782 | 7.9882 | 11.4673 | 13.4673 | 9.4891 | 17.4773 | 28.9446 | 42.4118 | 0.01
4.06 | 8.03 | 6.06 | 5.06 | 7.09 | 9.09 | 8.03 | 13.09 | 20.1799 | 29.2699 | 4.06 | 8.03 | 6.06 | 5.07 | 7.09 | 9.09 | 8.03 | 13.1 | 20.1899 | 29.2799 | 0.01
6.8952 | 9.4476 | 8.8952 | 7.8952 | 11.3428 | 13.3428 | 9.4476 | 17.3428 | 28.6856 | 42.0284 | 6.8952 | 9.4476 | 8.8952 | 7.9052 | 11.3428 | 13.3428 | 9.4476 | 17.3528 | 28.6956 | 42.0384 | 0.01
4.2954 | 8.1477 | 6.2954 | 5.2954 | 7.4431 | 9.4431 | 8.1477 | 13.4431 | 20.8863 | 30.3294 | 4.2954 | 8.1477 | 6.2954 | 5.3054 | 7.4431 | 9.4431 | 8.1477 | 13.4531 | 20.8963 | 30.3394 | 0.01
5.384 | 8.692 | 7.384 | 6.384 | 9.076 | 11.076 | 8.692 | 15.076 | 24.152 | 35.228 | 5.384 | 8.692 | 7.384 | 6.394 | 9.076 | 11.076 | 8.692 | 15.086 | 24.162 | 35.238 | 0.01
5.5138 | 8.7569 | 7.5138 | 6.5138 | 9.2708 | 11.2708 | 8.7569 | 15.2708 | 24.5415 | 35.8123 | 5.5138 | 8.7569 | 7.5138 | 6.5238 | 9.2708 | 11.2708 | 8.7569 | 15.2808 | 24.5515 | 35.8223 | 0.01
6.558 | 9.279 | 8.558 | 7.558 | 10.837 | 12.837 | 9.279 | 16.837 | 27.6741 | 40.5111 | 6.558 | 9.279 | 8.558 | 7.568 | 10.837 | 12.837 | 9.279 | 16.847 | 27.6841 | 40.5211 | 0.01
6.8751 | 9.4376 | 8.8751 | 7.8751 | 11.3127 | 13.3127 | 9.4376 | 17.3127 | 28.6254 | 41.9381 | 6.8751 | 9.4376 | 8.8751 | 7.8851 | 11.3127 | 13.3127 | 9.4376 | 17.3227 | 28.6354 | 41.9481 | 0.01
5.5105 | 8.7553 | 7.5105 | 6.5105 | 9.2658 | 11.2658 | 8.7553 | 15.2658 | 24.5316 | 35.7974 | 5.5105 | 8.7553 | 7.5105 | 6.5205 | 9.2658 | 11.2658 | 8.7553 | 15.2758 | 24.5416 | 35.8074 | 0.01
3.8041 | 7.902 | 5.8041 | 4.8041 | 6.7061 | 8.7061 | 7.902 | 12.7061 | 19.4123 | 28.1184 | 3.8041 | 7.902 | 5.8041 | 4.8141 | 6.7061 | 8.7061 | 7.902 | 12.7161 | 19.4223 | 28.1284 | 0.01
6.5984 | 9.2992 | 8.5984 | 7.5984 | 10.8976 | 12.8976 | 9.2992 | 16.8976 | 27.7952 | 40.6927 | 6.5984 | 9.2992 | 8.5984 | 7.6084 | 10.8976 | 12.8976 | 9.2992 | 16.9076 | 27.8052 | 40.7027 | 0.01
4.1412 | 8.0706 | 6.1412 | 5.1412 | 7.2117 | 9.2117 | 8.0706 | 13.2117 | 20.4235 | 29.6352 | 4.1412 | 8.0706 | 6.1412 | 5.1512 | 7.2117 | 9.2117 | 8.0706 | 13.2217 | 20.4335 | 29.6452 | 0.01
8.1884 | 10.0942 | 10.1884 | 9.1884 | 13.2826 | 15.2826 | 10.0942 | 19.2826 | 32.5651 | 47.8477 | 8.1884 | 10.0942 | 10.1884 | 9.1984 | 13.2826 | 15.2826 | 10.0942 | 19.2926 | 32.5751 | 47.8577 | 0.01
3.3929 | 7.6965 | 5.3929 | 4.3929 | 6.0894 | 8.0894 | 7.6965 | 12.0894 | 18.1787 | 26.2681 | 3.3929 | 7.6965 | 5.3929 | 4.4029 | 6.0894 | 8.0894 | 7.6965 | 12.0994 | 18.1887 | 26.2781 | 0.01
8.253 | 10.1265 | 10.253 | 9.253 | 13.3795 | 15.3795 | 10.1265 | 19.3795 | 32.759 | 48.1384 | 8.253 | 10.1265 | 10.253 | 9.263 | 13.3795 | 15.3795 | 10.1265 | 19.3895 | 32.769 | 48.1484 | 0.01
6.3518 | 9.1759 | 8.3518 | 7.3518 | 10.5277 | 12.5277 | 9.1759 | 16.5277 | 27.0554 | 39.583 | 6.3518 | 9.1759 | 8.3518 | 7.3618 | 10.5277 | 12.5277 | 9.1759 | 16.5377 | 27.0654 | 39.593 | 0.01
6.4248 | 9.2124 | 8.4248 | 7.4248 | 10.6371 | 12.6371 | 9.2124 | 16.6371 | 27.2743 | 39.9114 | 6.4248 | 9.2124 | 8.4248 | 7.4348 | 10.6371 | 12.6371 | 9.2124 | 16.6471 | 27.2843 | 39.9214 | 0.01
4.0788 | 8.0394 | 6.0788 | 5.0788 | 7.1181 | 9.1181 | 8.0394 | 13.1181 | 20.2363 | 29.3544 | 4.0788 | 8.0394 | 6.0788 | 5.0888 | 7.1181 | 9.1181 | 8.0394 | 13.1281 | 20.2463 | 29.3644 | 0.01
3.7415 | 7.8708 | 5.7415 | 4.7415 | 6.6123 | 8.6123 | 7.8708 | 12.6123 | 19.2246 | 27.8368 | 3.7415 | 7.8708 | 5.7415 | 4.7515 | 6.6123 | 8.6123 | 7.8708 | 12.6223 | 19.2346 | 27.8468 | 0.01
7.8238 | 9.9119 | 9.8238 | 8.8238 | 12.7357 | 14.7357 | 9.9119 | 18.7357 | 31.4713 | 46.207 | 7.8238 | 9.9119 | 9.8238 | 8.8338 | 12.7357 | 14.7357 | 9.9119 | 18.7457 | 31.4813 | 46.217 | 0.01
5.4348 | 8.7174 | 7.4348 | 6.4348 | 9.1522 | 11.1522 | 8.7174 | 15.1522 | 24.3044 | 35.4567 | 5.4348 | 8.7174 | 7.4348 | 6.4448 | 9.1522 | 11.1522 | 8.7174 | 15.1622 | 24.3144 | 35.4667 | 0.01
4.2646 | 8.1323 | 6.2646 | 5.2646 | 7.397 | 9.397 | 8.1323 | 13.397 | 20.7939 | 30.1909 | 4.2646 | 8.1323 | 6.2646 | 5.2746 | 7.397 | 9.397 | 8.1323 | 13.407 | 20.8039 | 30.2009 | 0.01
5.7679 | 8.884 | 7.7679 | 6.7679 | 9.6519 | 11.6519 | 8.884 | 15.6519 | 25.3038 | 36.9556 | 5.7679 | 8.884 | 7.7679 | 6.7779 | 9.6519 | 11.6519 | 8.884 | 15.6619 | 25.3138 | 36.9656 | 0.01
6.0709 | 9.0355 | 8.0709 | 7.0709 | 10.1064 | 12.1064 | 9.0355 | 16.1064 | 26.2128 | 38.3192 | 6.0709 | 9.0355 | 8.0709 | 7.0809 | 10.1064 | 12.1064 | 9.0355 | 16.1164 | 26.2228 | 38.3292 | 0.01
7.1335 | 9.5668 | 9.1335 | 8.1335 | 11.7003 | 13.7003 | 9.5668 | 17.7003 | 29.4005 | 43.1008 | 7.1335 | 9.5668 | 9.1335 | 8.1435 | 11.7003 | 13.7003 | 9.5668 | 17.7103 | 29.4105 | 43.1108 | 0.01
7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 7.2523 | 9.6262 | 9.2523 | 8.2623 | 11.8785 | 13.8785 | 9.6262 | 17.8885 | 29.767 | 43.6455 | 0.01
1.7153 | 6.8577 | 3.7153 | 2.7153 | 3.573 | 5.573 | 6.8577 | 9.573 | 13.146 | 18.719 | 1.7153 | 6.8577 | 3.7153 | 2.7253 | 3.573 | 5.573 | 6.8577 | 9.583 | 13.156 | 18.729 | 0.01
2.3377 | 7.1689 | 4.3377 | 3.3377 | 4.5066 | 6.5066 | 7.1689 | 10.5066 | 15.0132 | 21.5197 | 2.3377 | 7.1689 | 4.3377 | 3.3477 | 4.5066 | 6.5066 | 7.1689 | 10.5166 | 15.0232 | 21.5297 | 0.01
4.5542 | 8.2771 | 6.5542 | 5.5542 | 7.8313 | 9.8313 | 8.2771 | 13.8313 | 21.6626 | 31.4939 | 4.5542 | 8.2771 | 6.5542 | 5.5642 | 7.8313 | 9.8313 | 8.2771 | 13.8413 | 21.6726 | 31.5039 | 0.01
8.0371 | 10.0185 | 10.0371 | 9.0371 | 13.0556 | 15.0556 | 10.0185 | 19.0556 | 32.1113 | 47.1669 | 8.0371 | 10.0185 | 10.0371 | 9.0471 | 13.0556 | 15.0556 | 10.0185 | 19.0656 | 32.1213 | 47.1769 | 0.01
9.1147 | 10.5573 | 11.1147 | 10.1147 | 14.672 | 16.672 | 10.5573 | 20.672 | 35.3441 | 52.0161 | 9.1147 | 10.5573 | 11.1147 | 10.1247 | 14.672 | 16.672 | 10.5573 | 20.682 | 35.3541 | 52.0261 | 0.01
6.8241 | 9.412 | 8.8241 | 7.8241 | 11.2361 | 13.2361 | 9.412 | 17.2361 | 28.4722 | 41.7083 | 6.8241 | 9.412 | 8.8241 | 7.8341 | 11.2361 | 13.2361 | 9.412 | 17.2461 | 28.4822 | 41.7183 | 0.01
6.7062 | 9.3531 | 8.7062 | 7.7062 | 11.0593 | 13.0593 | 9.3531 | 17.0593 | 28.1185 | 41.1778 | 6.7062 | 9.3531 | 8.7062 | 7.7162 | 11.0593 | 13.0593 | 9.3531 | 17.0693 | 28.1285 | 41.1878 | 0.01
5.2576 | 8.6288 | 7.2576 | 6.2576 | 8.8863 | 10.8863 | 8.6288 | 14.8863 | 23.7727 | 34.659 | 5.2576 | 8.6288 | 7.2576 | 6.2676 | 8.8863 | 10.8863 | 8.6288 | 14.8963 | 23.7827 | 34.669 | 0.01
6.3132 | 9.1566 | 8.3132 | 7.3132 | 10.4697 | 12.4697 | 9.1566 | 16.4697 | 26.9395 | 39.4092 | 6.3132 | 9.1566 | 8.3132 | 7.3232 | 10.4697 | 12.4697 | 9.1566 | 16.4797 | 26.9495 | 39.4192 | 0.01
5.6124 | 8.8062 | 7.6124 | 6.6124 | 9.4186 | 11.4186 | 8.8062 | 15.4186 | 24.8373 | 36.2559 | 5.6124 | 8.8062 | 7.6124 | 6.6224 | 9.4186 | 11.4186 | 8.8062 | 15.4286 | 24.8473 | 36.2659 | 0.01
4.4577 | 8.2289 | 6.4577 | 5.4577 | 7.6866 | 9.6866 | 8.2289 | 13.6866 | 21.3732 | 31.0598 | 4.4577 | 8.2289 | 6.4577 | 5.4677 | 7.6866 | 9.6866 | 8.2289 | 13.6966 | 21.3832 | 31.0698 | 0.01
7.1172 | 9.5586 | 9.1172 | 8.1172 | 11.6758 | 13.6758 | 9.5586 | 17.6758 | 29.3516 | 43.0274 | 7.1172 | 9.5586 | 9.1172 | 8.1272 | 11.6758 | 13.6758 | 9.5586 | 17.6858 | 29.3616 | 43.0374 | 0.01
1.8832 | 6.9416 | 3.8832 | 2.8832 | 3.8248 | 5.8248 | 6.9416 | 9.8248 | 13.6496 | 19.4744 | 1.8832 | 6.9416 | 3.8832 | 2.8932 | 3.8248 | 5.8248 | 6.9416 | 9.8348 | 13.6596 | 19.4844 | 0.01
9.3963 | 10.6981 | 11.3963 | 10.3963 | 15.0944 | 17.0944 | 10.6981 | 21.0944 | 36.1889 | 53.2833 | 9.3963 | 10.6981 | 11.3963 | 10.4063 | 15.0944 | 17.0944 | 10.6981 | 21.1044 | 36.1989 | 53.2933 | 0.01
5.7522 | 8.8761 | 7.7522 | 6.7522 | 9.6283 | 11.6283 | 8.8761 | 15.6283 | 25.2566 | 36.8849 | 5.7522 | 8.8761 | 7.7522 | 6.7622 | 9.6283 | 11.6283 | 8.8761 | 15.6383 | 25.2666 | 36.8949 | 0.01
8.7802 | 10.3901 | 10.7802 | 9.7802 | 14.1703 | 16.1703 | 10.3901 | 20.1703 | 34.3407 | 50.511 | 8.7802 | 10.3901 | 10.7802 | 9.7902 | 14.1703 | 16.1703 | 10.3901 | 20.1803 | 34.3507 | 50.521 | 0.01
6.4029 | 9.2014 | 8.4029 | 7.4029 | 10.6043 | 12.6043 | 9.2014 | 16.6043 | 27.2086 | 39.8129 | 6.4029 | 9.2014 | 8.4029 | 7.4129 | 10.6043 | 12.6043 | 9.2014 | 16.6143 | 27.2186 | 39.8229 | 0.01
3.783 | 7.8915 | 5.783 | 4.783 | 6.6745 | 8.6745 | 7.8915 | 12.6745 | 19.349 | 28.0235 | 3.783 | 7.8915 | 5.783 | 4.793 | 6.6745 | 8.6745 | 7.8915 | 12.6845 | 19.359 | 28.0335 | 0.01
4.0209 | 8.0105 | 6.0209 | 5.0209 | 7.0314 | 9.0314 | 8.0105 | 13.0314 | 20.0627 | 29.0941 | 4.0209 | 8.0105 | 6.0209 | 5.0309 | 7.0314 | 9.0314 | 8.0105 | 13.0414 | 20.0727 | 29.1041 | 0.01
6.4079 | 9.2039 | 8.4079 | 7.4079 | 10.6118 | 12.6118 | 9.2039 | 16.6118 | 27.2236 | 39.8354 | 6.4079 | 9.2039 | 8.4079 | 7.4179 | 10.6118 | 12.6118 | 9.2039 | 16.6218 | 27.2336 | 39.8454 | 0.01
6.5453 | 9.2727 | 8.5453 | 7.5453 | 10.818 | 12.818 | 9.2727 | 16.818 | 27.6359 | 40.4539 | 6.5453 | 9.2727 | 8.5453 | 7.5553 | 10.818 | 12.818 | 9.2727 | 16.828 | 27.6459 | 40.4639 | 0.01
7.6805 | 9.8402 | 9.6805 | 8.6805 | 12.5207 | 14.5207 | 9.8402 | 18.5207 | 31.0415 | 45.5622 | 7.6805 | 9.8402 | 9.6805 | 8.6905 | 12.5207 | 14.5207 | 9.8402 | 18.5307 | 31.0515 | 45.5722 | 0.01
6.1081 | 9.0541 | 8.1081 | 7.1081 | 10.1622 | 12.1622 | 9.0541 | 16.1622 | 26.3244 | 38.4866 | 6.1081 | 9.0541 | 8.1081 | 7.1181 | 10.1622 | 12.1622 | 9.0541 | 16.1722 | 26.3344 | 38.4966 | 0.01
6.5904 | 9.2952 | 8.5904 | 7.5904 | 10.8856 | 12.8856 | 9.2952 | 16.8856 | 27.7712 | 40.6568 | 6.5904 | 9.2952 | 8.5904 | 7.6004 | 10.8856 | 12.8856 | 9.2952 | 16.8956 | 27.7812 | 40.6668 | 0.01
6.4252 | 9.2126 | 8.4252 | 7.4252 | 10.6378 | 12.6378 | 9.2126 | 16.6378 | 27.2757 | 39.9135 | 6.4252 | 9.2126 | 8.4252 | 7.4352 | 10.6378 | 12.6378 | 9.2126 | 16.6478 | 27.2857 | 39.9235 | 0.01
5.1021 | 8.551 | 7.1021 | 6.1021 | 8.6531 | 10.6531 | 8.551 | 14.6531 | 23.3063 | 33.9594 | 5.1021 | 8.551 | 7.1021 | 6.1121 | 8.6531 | 10.6531 | 8.551 | 14.6631 | 23.3163 | 33.9694 | 0.01
5.7627 | 8.8813 | 7.7627 | 6.7627 | 9.644 | 11.644 | 8.8813 | 15.644 | 25.288 | 36.9321 | 5.7627 | 8.8813 | 7.7627 | 6.7727 | 9.644 | 11.644 | 8.8813 | 15.654 | 25.298 | 36.9421 | 0.01
6.6646 | 9.3323 | 8.6646 | 7.6646 | 10.997 | 12.997 | 9.3323 | 16.997 | 27.9939 | 40.9909 | 6.6646 | 9.3323 | 8.6646 | 7.6746 | 10.997 | 12.997 | 9.3323 | 17.007 | 28.0039 | 41.0009 | 0.01
3.2081 | 7.604 | 5.2081 | 4.2081 | 5.8121 | 7.8121 | 7.604 | 11.8121 | 17.6242 | 25.4363 | 3.2081 | 7.604 | 5.2081 | 4.2181 | 5.8121 | 7.8121 | 7.604 | 11.8221 | 17.6342 | 25.4463 | 0.01
5.1092 | 8.5546 | 7.1092 | 6.1092 | 8.6638 | 10.6638 | 8.5546 | 14.6638 | 23.3276 | 33.9913 | 5.1092 | 8.5546 | 7.1092 | 6.1192 | 8.6638 | 10.6638 | 8.5546 | 14.6738 | 23.3376 | 34.0013 | 0.01
6.6987 | 9.3493 | 8.6987 | 7.6987 | 11.048 | 13.048 | 9.3493 | 17.048 | 28.0961 | 41.1441 | 6.6987 | 9.3493 | 8.6987 | 7.7087 | 11.048 | 13.048 | 9.3493 | 17.058 | 28.1061 | 41.1541 | 0.01
6.0901 | 9.045 | 8.0901 | 7.0901 | 10.1351 | 12.1351 | 9.045 | 16.1351 | 26.2702 | 38.4053 | 6.0901 | 9.045 | 8.0901 | 7.1001 | 10.1351 | 12.1351 | 9.045 | 16.1451 | 26.2802 | 38.4153 | 0.01
3.3738 | 7.6869 | 5.3738 | 4.3738 | 6.0607 | 8.0607 | 7.6869 | 12.0607 | 18.1215 | 26.1822 | 3.3738 | 7.6869 | 5.3738 | 4.3838 | 6.0607 | 8.0607 | 7.6869 | 12.0707 | 18.1315 | 26.1922 | 0.01
4.8105 | 8.4053 | 6.8105 | 5.8105 | 8.2158 | 10.2158 | 8.4053 | 14.2158 | 22.4316 | 32.6474 | 4.8105 | 8.4053 | 6.8105 | 5.8205 | 8.2158 | 10.2158 | 8.4053 | 14.2258 | 22.4416 | 32.6574 | 0.01
7.522 | 9.761 | 9.522 | 8.522 | 12.2829 | 14.2829 | 9.761 | 18.2829 | 30.5659 | 44.8488 | 7.522 | 9.761 | 9.522 | 8.532 | 12.2829 | 14.2829 | 9.761 | 18.2929 | 30.5759 | 44.8588 | 0.01
4.9713 | 8.4857 | 6.9713 | 5.9713 | 8.457 | 10.457 | 8.4857 | 14.457 | 22.9139 | 33.3709 | 4.9713 | 8.4857 | 6.9713 | 5.9813 | 8.457 | 10.457 | 8.4857 | 14.467 | 22.9239 | 33.3809 | 0.01
6.749 | 9.3745 | 8.749 | 7.749 | 11.1235 | 13.1235 | 9.3745 | 17.1235 | 28.247 | 41.3705 | 6.749 | 9.3745 | 8.749 | 7.759 | 11.1235 | 13.1235 | 9.3745 | 17.1335 | 28.257 | 41.3805 | 0.01
5.0742 | 8.5371 | 7.0742 | 6.0742 | 8.6114 | 10.6114 | 8.5371 | 14.6114 | 23.2227 | 33.8341 | 5.0742 | 8.5371 | 7.0742 | 6.0842 | 8.6114 | 10.6114 | 8.5371 | 14.6214 | 23.2327 | 33.8441 | 0.01
4.7646 | 8.3823 | 6.7646 | 5.7646 | 8.1468 | 10.1468 | 8.3823 | 14.1468 | 22.2937 | 32.4405 | 4.7646 | 8.3823 | 6.7646 | 5.7746 | 8.1468 | 10.1468 | 8.3823 | 14.1568 | 22.3037 | 32.4505 | 0.01
7.389 | 9.6945 | 9.389 | 8.389 | 12.0834 | 14.0834 | 9.6945 | 18.0834 | 30.1669 | 44.2503 | 7.389 | 9.6945 | 9.389 | 8.399 | 12.0834 | 14.0834 | 9.6945 | 18.0934 | 30.1769 | 44.2603 | 0.01
2.893 | 7.4465 | 4.893 | 3.893 | 5.3395 | 7.3395 | 7.4465 | 11.3395 | 16.679 | 24.0185 | 2.893 | 7.4465 | 4.893 | 3.903 | 5.3395 | 7.3395 | 7.4465 | 11.3495 | 16.689 | 24.0285 | 0.01
3.3349 | 7.6675 | 5.3349 | 4.3349 | 6.0024 | 8.0024 | 7.6675 | 12.0024 | 18.0048 | 26.0072 | 3.3349 | 7.6675 | 5.3349 | 4.3449 | 6.0024 | 8.0024 | 7.6675 | 12.0124 | 18.0148 | 26.0172 | 0.01
8.9925 | 10.4963 | 10.9925 | 9.9925 | 14.4888 | 16.4888 | 10.4963 | 20.4888 | 34.9775 | 51.4663 | 8.9925 | 10.4963 | 10.9925 | 10.0025 | 14.4888 | 16.4888 | 10.4963 | 20.4988 | 34.9875 | 51.4763 | 0.01
7.789 | 9.8945 | 9.789 | 8.789 | 12.6836 | 14.6836 | 9.8945 | 18.6836 | 31.3671 | 46.0507 | 7.789 | 9.8945 | 9.789 | 8.799 | 12.6836 | 14.6836 | 9.8945 | 18.6936 | 31.3771 | 46.0607 | 0.01
7.8333 | 9.9167 | 9.8333 | 8.8333 | 12.75 | 14.75 | 9.9167 | 18.75 | 31.4999 | 46.2499 | 7.8333 | 9.9167 | 9.8333 | 8.8433 | 12.75 | 14.75 | 9.9167 | 18.76 | 31.5099 | 46.2599 | 0.01
7.307 | 9.6535 | 9.307 | 8.307 | 11.9605 | 13.9605 | 9.6535 | 17.9605 | 29.9209 | 43.8814 | 7.307 | 9.6535 | 9.307 | 8.317 | 11.9605 | 13.9605 | 9.6535 | 17.9705 | 29.9309 | 43.8914 | 0.01
9.787 | 10.8935 | 11.787 | 10.787 | 15.6805 | 17.6805 | 10.8935 | 21.6805 | 37.361 | 55.0415 | 9.787 | 10.8935 | 11.787 | 10.797 | 15.6805 | 17.6805 | 10.8935 | 21.6905 | 37.371 | 55.0515 | 0.01
5.2045 | 8.6023 | 7.2045 | 6.2045 | 8.8068 | 10.8068 | 8.6023 | 14.8068 | 23.6135 | 34.4203 | 5.2045 | 8.6023 | 7.2045 | 6.2145 | 8.8068 | 10.8068 | 8.6023 | 14.8168 | 23.6235 | 34.4303 | 0.01
5.5481 | 8.7741 | 7.5481 | 6.5481 | 9.3222 | 11.3222 | 8.7741 | 15.3222 | 24.6444 | 35.9666 | 5.5481 | 8.7741 | 7.5481 | 6.5581 | 9.3222 | 11.3222 | 8.7741 | 15.3322 | 24.6544 | 35.9766 | 0.01
2.9819 | 7.491 | 4.9819 | 3.9819 | 5.4729 | 7.4729 | 7.491 | 11.4729 | 16.9458 | 24.4187 | 2.9819 | 7.491 | 4.9819 | 3.9919 | 5.4729 | 7.4729 | 7.491 | 11.4829 | 16.9558 | 24.4287 | 0.01
7.6554 | 9.8277 | 9.6554 | 8.6554 | 12.4831 | 14.4831 | 9.8277 | 18.4831 | 30.9661 | 45.4492 | 7.6554 | 9.8277 | 9.6554 | 8.6654 | 12.4831 | 14.4831 | 9.8277 | 18.4931 | 30.9761 | 45.4592 | 0.01
4.8098 | 8.4049 | 6.8098 | 5.8098 | 8.2147 | 10.2147 | 8.4049 | 14.2147 | 22.4294 | 32.6441 | 4.8098 | 8.4049 | 6.8098 | 5.8198 | 8.2147 | 10.2147 | 8.4049 | 14.2247 | 22.4394 | 32.6541 | 0.01
2.7341 | 7.3671 | 4.7341 | 3.7341 | 5.1012 | 7.1012 | 7.3671 | 11.1012 | 16.2023 | 23.3035 | 2.7341 | 7.3671 | 4.7341 | 3.7441 | 5.1012 | 7.1012 | 7.3671 | 11.1112 | 16.2123 | 23.3135 | 0.01
8.5249 | 10.2624 | 10.5249 | 9.5249 | 13.7873 | 15.7873 | 10.2624 | 19.7873 | 33.5746 | 49.3619 | 8.5249 | 10.2624 | 10.5249 | 9.5349 | 13.7873 | 15.7873 | 10.2624 | 19.7973 | 33.5846 | 49.3719 | 0.01
8.5457 | 10.2729 | 10.5457 | 9.5457 | 13.8186 | 15.8186 | 10.2729 | 19.8186 | 33.6371 | 49.4557 | 8.5457 | 10.2729 | 10.5457 | 9.5557 | 13.8186 | 15.8186 | 10.2729 | 19.8286 | 33.6471 | 49.4657 | 0.01
6.6239 | 9.3119 | 8.6239 | 7.6239 | 10.9358 | 12.9358 | 9.3119 | 16.9358 | 27.8716 | 40.8074 | 6.6239 | 9.3119 | 8.6239 | 7.6339 | 10.9358 | 12.9358 | 9.3119 | 16.9458 | 27.8816 | 40.8174 | 0.01
7.2382 | 9.6191 | 9.2382 | 8.2382 | 11.8573 | 13.8573 | 9.6191 | 17.8573 | 29.7147 | 43.572 | 7.2382 | 9.6191 | 9.2382 | 8.2482 | 11.8573 | 13.8573 | 9.6191 | 17.8673 | 29.7247 | 43.582 | 0.01
6.7582 | 9.3791 | 8.7582 | 7.7582 | 11.1373 | 13.1373 | 9.3791 | 17.1373 | 28.2746 | 41.4119 | 6.7582 | 9.3791 | 8.7582 | 7.7682 | 11.1373 | 13.1373 | 9.3791 | 17.1473 | 28.2846 | 41.4219 | 0.01
5.4894 | 8.7447 | 7.4894 | 6.4894 | 9.2341 | 11.2341 | 8.7447 | 15.2341 | 24.4682 | 35.7022 | 5.4894 | 8.7447 | 7.4894 | 6.4994 | 9.2341 | 11.2341 | 8.7447 | 15.2441 | 24.4782 | 35.7122 | 0.01
5.7659 | 8.883 | 7.7659 | 6.7659 | 9.6489 | 11.6489 | 8.883 | 15.6489 | 25.2977 | 36.9466 | 5.7659 | 8.883 | 7.7659 | 6.7759 | 9.6489 | 11.6489 | 8.883 | 15.6589 | 25.3077 | 36.9566 | 0.01
5.7573 | 8.8786 | 7.7573 | 6.7573 | 9.6359 | 11.6359 | 8.8786 | 15.6359 | 25.2719 | 36.9078 | 5.7573 | 8.8786 | 7.7573 | 6.7673 | 9.6359 | 11.6359 | 8.8786 | 15.6459 | 25.2819 | 36.9178 | 0.01
4.4028 | 8.2014 | 6.4028 | 5.4028 | 7.6042 | 9.6042 | 8.2014 | 13.6042 | 21.2083 | 30.8125 | 4.4028 | 8.2014 | 6.4028 | 5.4128 | 7.6042 | 9.6042 | 8.2014 | 13.6142 | 21.2183 | 30.8225 | 0.01
5.7536 | 8.8768 | 7.7536 | 6.7536 | 9.6304 | 11.6304 | 8.8768 | 15.6304 | 25.2608 | 36.8911 | 5.7536 | 8.8768 | 7.7536 | 6.7636 | 9.6304 | 11.6304 | 8.8768 | 15.6404 | 25.2708 | 36.9011 | 0.01
5.0303 | 8.5151 | 7.0303 | 6.0303 | 8.5454 | 10.5454 | 8.5151 | 14.5454 | 23.0908 | 33.6361 | 5.0303 | 8.5151 | 7.0303 | 6.0403 | 8.5454 | 10.5454 | 8.5151 | 14.5554 | 23.1008 | 33.6461 | 0.01
3.0131 | 7.5066 | 5.0131 | 4.0131 | 5.5197 | 7.5197 | 7.5066 | 11.5197 | 17.0393 | 24.559 | 3.0131 | 7.5066 | 5.0131 | 4.0231 | 5.5197 | 7.5197 | 7.5066 | 11.5297 | 17.0493 | 24.569 | 0.01
2.4946 | 7.2473 | 4.4946 | 3.4946 | 4.7419 | 6.7419 | 7.2473 | 10.7419 | 15.4838 | 22.2257 | 2.4946 | 7.2473 | 4.4946 | 3.5046 | 4.7419 | 6.7419 | 7.2473 | 10.7519 | 15.4938 | 22.2357 | 0.01
3.8321 | 7.9161 | 5.8321 | 4.8321 | 6.7482 | 8.7482 | 7.9161 | 12.7482 | 19.4963 | 28.2445 | 3.8321 | 7.9161 | 5.8321 | 4.8421 | 6.7482 | 8.7482 | 7.9161 | 12.7582 | 19.5063 | 28.2545 | 0.01
3.881 | 7.9405 | 5.881 | 4.881 | 6.8215 | 8.8215 | 7.9405 | 12.8215 | 19.6431 | 28.4646 | 3.881 | 7.9405 | 5.881 | 4.891 | 6.8215 | 8.8215 | 7.9405 | 12.8315 | 19.6531 | 28.4746 | 0.01
6.8478 | 9.4239 | 8.8478 | 7.8478 | 11.2716 | 13.2716 | 9.4239 | 17.2716 | 28.5433 | 41.8149 | 6.8478 | 9.4239 | 8.8478 | 7.8578 | 11.2716 | 13.2716 | 9.4239 | 17.2816 | 28.5533 | 41.8249 | 0.01
6.8117 | 9.4059 | 8.8117 | 7.8117 | 11.2176 | 13.2176 | 9.4059 | 17.2176 | 28.4352 | 41.6529 | 6.8117 | 9.4059 | 8.8117 | 7.8217 | 11.2176 | 13.2176 | 9.4059 | 17.2276 | 28.4452 | 41.6629 | 0.01
2.5649 | 7.2825 | 4.5649 | 3.5649 | 4.8474 | 6.8474 | 7.2825 | 10.8474 | 15.6947 | 22.5421 | 2.5649 | 7.2825 | 4.5649 | 3.5749 | 4.8474 | 6.8474 | 7.2825 | 10.8574 | 15.7047 | 22.5521 | 0.01
4.502 | 8.251 | 6.502 | 5.502 | 7.7531 | 9.7531 | 8.251 | 13.7531 | 21.5061 | 31.2592 | 4.502 | 8.251 | 6.502 | 5.512 | 7.7531 | 9.7531 | 8.251 | 13.7631 | 21.5161 | 31.2692 | 0.01
8.0192 | 10.0096 | 10.0192 | 9.0192 | 13.0288 | 15.0288 | 10.0096 | 19.0288 | 32.0575 | 47.0863 | 8.0192 | 10.0096 | 10.0192 | 9.0292 | 13.0288 | 15.0288 | 10.0096 | 19.0388 | 32.0675 | 47.0963 | 0.01
5.5992 | 8.7996 | 7.5992 | 6.5992 | 9.3987 | 11.3987 | 8.7996 | 15.3987 | 24.7975 | 36.1962 | 5.5992 | 8.7996 | 7.5992 | 6.6092 | 9.3987 | 11.3987 | 8.7996 | 15.4087 | 24.8075 | 36.2062 | 0.01
3.538 | 7.769 | 5.538 | 4.538 | 6.3071 | 8.3071 | 7.769 | 12.3071 | 18.6141 | 26.9212 | 3.538 | 7.769 | 5.538 | 4.548 | 6.3071 | 8.3071 | 7.769 | 12.3171 | 18.6241 | 26.9312 | 0.01
4.1922 | 8.0961 | 6.1922 | 5.1922 | 7.2882 | 9.2882 | 8.0961 | 13.2882 | 20.5765 | 29.8647 | 4.1922 | 8.0961 | 6.1922 | 5.2022 | 7.2882 | 9.2882 | 8.0961 | 13.2982 | 20.5865 | 29.8747 | 0.01
8.0617 | 10.0308 | 10.0617 | 9.0617 | 13.0925 | 15.0925 | 10.0308 | 19.0925 | 32.185 | 47.2775 | 8.0617 | 10.0308 | 10.0617 | 9.0717 | 13.0925 | 15.0925 | 10.0308 | 19.1025 | 32.195 | 47.2875 | 0.01
7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 7.4889 | 9.7444 | 9.4889 | 8.4989 | 12.2333 | 14.2333 | 9.7444 | 18.2433 | 30.4766 | 44.7098 | 0.01
11.8438 | 11.9219 | 13.8438 | 12.8438 | 18.7656 | 20.7656 | 11.9219 | 24.7656 | 43.5313 | 64.2969 | 11.8438 | 11.9219 | 13.8438 | 12.8538 | 18.7656 | 20.7656 | 11.9219 | 24.7756 | 43.5413 | 64.3069 | 0.01
6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 6.3314 | 9.1657 | 8.3314 | 7.3414 | 10.4972 | 12.4972 | 9.1657 | 16.5072 | 27.0043 | 39.5015 | 0.01
8.8082 | 10.4041 | 10.8082 | 9.8082 | 14.2124 | 16.2124 | 10.4041 | 20.2124 | 34.4247 | 50.6371 | 8.8082 | 10.4041 | 10.8082 | 9.8182 | 14.2124 | 16.2124 | 10.4041 | 20.2224 | 34.4347 | 50.6471 | 0.01
7.6294 | 9.8147 | 9.6294 | 8.6294 | 12.4441 | 14.4441 | 9.8147 | 18.4441 | 30.8883 | 45.3324 | 7.6294 | 9.8147 | 9.6294 | 8.6394 | 12.4441 | 14.4441 | 9.8147 | 18.4541 | 30.8983 | 45.3424 | 0.01
6.2816 | 9.1408 | 8.2816 | 7.2816 | 10.4224 | 12.4224 | 9.1408 | 16.4224 | 26.8448 | 39.2672 | 6.2816 | 9.1408 | 8.2816 | 7.2916 | 10.4224 | 12.4224 | 9.1408 | 16.4324 | 26.8548 | 39.2772 | 0.01
2.9948 | 7.4974 | 4.9948 | 3.9948 | 5.4922 | 7.4922 | 7.4974 | 11.4922 | 16.9843 | 24.4765 | 2.9948 | 7.4974 | 4.9948 | 4.0048 | 5.4922 | 7.4922 | 7.4974 | 11.5022 | 16.9943 | 24.4865 | 0.01
7.6577 | 9.8289 | 9.6577 | 8.6577 | 12.4866 | 14.4866 | 9.8289 | 18.4866 | 30.9732 | 45.4598 | 7.6577 | 9.8289 | 9.6577 | 8.6677 | 12.4866 | 14.4866 | 9.8289 | 18.4966 | 30.9832 | 45.4698 | 0.01
5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 5.0973 | 8.5487 | 7.0973 | 6.1073 | 8.646 | 10.646 | 8.5487 | 14.656 | 23.302 | 33.9481 | 0.01
6.3502 | 9.1751 | 8.3502 | 7.3502 | 10.5253 | 12.5253 | 9.1751 | 16.5253 | 27.0507 | 39.576 | 6.3502 | 9.1751 | 8.3502 | 7.3602 | 10.5253 | 12.5253 | 9.1751 | 16.5353 | 27.0607 | 39.586 | 0.01
8.2841 | 10.1421 | 10.2841 | 9.2841 | 13.4262 | 15.4262 | 10.1421 | 19.4262 | 32.8524 | 48.2786 | 8.2841 | 10.1421 | 10.2841 | 9.2941 | 13.4262 | 15.4262 | 10.1421 | 19.4362 | 32.8624 | 48.2886 | 0.01
7.4494 | 9.7247 | 9.4494 | 8.4494 | 12.1741 | 14.1741 | 9.7247 | 18.1741 | 30.3481 | 44.5222 | 7.4494 | 9.7247 | 9.4494 | 8.4594 | 12.1741 | 14.1741 | 9.7247 | 18.1841 | 30.3581 | 44.5322 | 0.01
5.769 | 8.8845 | 7.769 | 6.769 | 9.6535 | 11.6535 | 8.8845 | 15.6535 | 25.307 | 36.9605 | 5.769 | 8.8845 | 7.769 | 6.779 | 9.6535 | 11.6535 | 8.8845 | 15.6635 | 25.317 | 36.9705 | 0.01
5.8084 | 8.9042 | 7.8084 | 6.8084 | 9.7126 | 11.7126 | 8.9042 | 15.7126 | 25.4252 | 37.1377 | 5.8084 | 8.9042 | 7.8084 | 6.8184 | 9.7126 | 11.7126 | 8.9042 | 15.7226 | 25.4352 | 37.1477 | 0.01
4.3983 | 8.1992 | 6.3983 | 5.3983 | 7.5975 | 9.5975 | 8.1992 | 13.5975 | 21.195 | 30.7925 | 4.3983 | 8.1992 | 6.3983 | 5.4083 | 7.5975 | 9.5975 | 8.1992 | 13.6075 | 21.205 | 30.8025 | 0.01
4.0729 | 8.0365 | 6.0729 | 5.0729 | 7.1094 | 9.1094 | 8.0365 | 13.1094 | 20.2188 | 29.3281 | 4.0729 | 8.0365 | 6.0729 | 5.0829 | 7.1094 | 9.1094 | 8.0365 | 13.1194 | 20.2288 | 29.3381 | 0.01
6.5512 | 9.2756 | 8.5512 | 7.5512 | 10.8268 | 12.8268 | 9.2756 | 16.8268 | 27.6536 | 40.4803 | 6.5512 | 9.2756 | 8.5512 | 7.5612 | 10.8268 | 12.8268 | 9.2756 | 16.8368 | 27.6636 | 40.4903 | 0.01
3.2266 | 7.6133 | 5.2266 | 4.2266 | 5.8399 | 7.8399 | 7.6133 | 11.8399 | 17.6798 | 25.5197 | 3.2266 | 7.6133 | 5.2266 | 4.2366 | 5.8399 | 7.8399 | 7.6133 | 11.8499 | 17.6898 | 25.5297 | 0.01
6.4914 | 9.2457 | 8.4914 | 7.4914 | 10.737 | 12.737 | 9.2457 | 16.737 | 27.4741 | 40.2111 | 6.4914 | 9.2457 | 8.4914 | 7.5014 | 10.737 | 12.737 | 9.2457 | 16.747 | 27.4841 | 40.2211 | 0.01
7.4177 | 9.7089 | 9.4177 | 8.4177 | 12.1266 | 14.1266 | 9.7089 | 18.1266 | 30.2532 | 44.3798 | 7.4177 | 9.7089 | 9.4177 | 8.4277 | 12.1266 | 14.1266 | 9.7089 | 18.1366 | 30.2632 | 44.3898 | 0.01
3.4213 | 7.7106 | 5.4213 | 4.4213 | 6.1319 | 8.1319 | 7.7106 | 12.1319 | 18.2638 | 26.3957 | 3.4213 | 7.7106 | 5.4213 | 4.4313 | 6.1319 | 8.1319 | 7.7106 | 12.1419 | 18.2738 | 26.4057 | 0.01
4.6599 | 8.3299 | 6.6599 | 5.6599 | 7.9898 | 9.9898 | 8.3299 | 13.9898 | 21.9797 | 31.9695 | 4.6599 | 8.3299 | 6.6599 | 5.6699 | 7.9898 | 9.9898 | 8.3299 | 13.9998 | 21.9897 | 31.9795 | 0.01
7.9283 | 9.9641 | 9.9283 | 8.9283 | 12.8924 | 14.8924 | 9.9641 | 18.8924 | 31.7849 | 46.6773 | 7.9283 | 9.9641 | 9.9283 | 8.9383 | 12.8924 | 14.8924 | 9.9641 | 18.9024 | 31.7949 | 46.6873 | 0.01
8.1195 | 10.0598 | 10.1195 | 9.1195 | 13.1793 | 15.1793 | 10.0598 | 19.1793 | 32.3586 | 47.5378 | 8.1195 | 10.0598 | 10.1195 | 9.1295 | 13.1793 | 15.1793 | 10.0598 | 19.1893 | 32.3686 | 47.5478 | 0.01
5.1511 | 8.5755 | 7.1511 | 6.1511 | 8.7266 | 10.7266 | 8.5755 | 14.7266 | 23.4532 | 34.1798 | 5.1511 | 8.5755 | 7.1511 | 6.1611 | 8.7266 | 10.7266 | 8.5755 | 14.7366 | 23.4632 | 34.1898 | 0.01
4.3661 | 8.183 | 6.3661 | 5.3661 | 7.5491 | 9.5491 | 8.183 | 13.5491 | 21.0983 | 30.6474 | 4.3661 | 8.183 | 6.3661 | 5.3761 | 7.5491 | 9.5491 | 8.183 | 13.5591 | 21.1083 | 30.6574 | 0.01
4.8403 | 8.4202 | 6.8403 | 5.8403 | 8.2605 | 10.2605 | 8.4202 | 14.2605 | 22.521 | 32.7815 | 4.8403 | 8.4202 | 6.8403 | 5.8503 | 8.2605 | 10.2605 | 8.4202 | 14.2705 | 22.531 | 32.7915 | 0.01
6.6155 | 9.3078 | 8.6155 | 7.6155 | 10.9233 | 12.9233 | 9.3078 | 16.9233 | 27.8466 | 40.7699 | 6.6155 | 9.3078 | 8.6155 | 7.6255 | 10.9233 | 12.9233 | 9.3078 | 16.9333 | 27.8566 | 40.7799 | 0.01
6.1813 | 9.0907 | 8.1813 | 7.1813 | 10.272 | 12.272 | 9.0907 | 16.272 | 26.544 | 38.8159 | 6.1813 | 9.0907 | 8.1813 | 7.1913 | 10.272 | 12.272 | 9.0907 | 16.282 | 26.554 | 38.8259 | 0.01
6.6324 | 9.3162 | 8.6324 | 7.6324 | 10.9486 | 12.9486 | 9.3162 | 16.9486 | 27.8972 | 40.8458 | 6.6324 | 9.3162 | 8.6324 | 7.6424 | 10.9486 | 12.9486 | 9.3162 | 16.9586 | 27.9072 | 40.8558 | 0.01
5.7216 | 8.8608 | 7.7216 | 6.7216 | 9.5825 | 11.5825 | 8.8608 | 15.5825 | 25.1649 | 36.7474 | 5.7216 | 8.8608 | 7.7216 | 6.7316 | 9.5825 | 11.5825 | 8.8608 | 15.5925 | 25.1749 | 36.7574 | 0.01
5.8658 | 8.9329 | 7.8658 | 6.8658 | 9.7987 | 11.7987 | 8.9329 | 15.7987 | 25.5974 | 37.3961 | 5.8658 | 8.9329 | 7.8658 | 6.8758 | 9.7987 | 11.7987 | 8.9329 | 15.8087 | 25.6074 | 37.4061 | 0.01
4.2094 | 8.1047 | 6.2094 | 5.2094 | 7.314 | 9.314 | 8.1047 | 13.314 | 20.6281 | 29.9421 | 4.2094 | 8.1047 | 6.2094 | 5.2194 | 7.314 | 9.314 | 8.1047 | 13.324 | 20.6381 | 29.9521 | 0.01
5.2214 | 8.6107 | 7.2214 | 6.2214 | 8.8321 | 10.8321 | 8.6107 | 14.8321 | 23.6641 | 34.4962 | 5.2214 | 8.6107 | 7.2214 | 6.2314 | 8.8321 | 10.8321 | 8.6107 | 14.8421 | 23.6741 | 34.5062 | 0.01
5.3992 | 8.6996 | 7.3992 | 6.3992 | 9.0988 | 11.0988 | 8.6996 | 15.0988 | 24.1976 | 35.2965 | 5.3992 | 8.6996 | 7.3992 | 6.4092 | 9.0988 | 11.0988 | 8.6996 | 15.1088 | 24.2076 | 35.3065 | 0.01
9.2618 | 10.6309 | 11.2618 | 10.2618 | 14.8927 | 16.8927 | 10.6309 | 20.8927 | 35.7855 | 52.6782 | 9.2618 | 10.6309 | 11.2618 | 10.2718 | 14.8927 | 16.8927 | 10.6309 | 20.9027 | 35.7955 | 52.6882 | 0.01
2.5164 | 7.2582 | 4.5164 | 3.5164 | 4.7746 | 6.7746 | 7.2582 | 10.7746 | 15.5493 | 22.3239 | 2.5164 | 7.2582 | 4.5164 | 3.5264 | 4.7746 | 6.7746 | 7.2582 | 10.7846 | 15.5593 | 22.3339 | 0.01
6.053 | 9.0265 | 8.053 | 7.053 | 10.0795 | 12.0795 | 9.0265 | 16.0795 | 26.1591 | 38.2386 | 6.053 | 9.0265 | 8.053 | 7.063 | 10.0795 | 12.0795 | 9.0265 | 16.0895 | 26.1691 | 38.2486 | 0.01
11.0086 | 11.5043 | 13.0086 | 12.0086 | 17.5129 | 19.5129 | 11.5043 | 23.5129 | 41.0259 | 60.5388 | 11.0086 | 11.5043 | 13.0086 | 12.0186 | 17.5129 | 19.5129 | 11.5043 | 23.5229 | 41.0359 | 60.5488 | 0.01
9.7368 | 10.8684 | 11.7368 | 10.7368 | 15.6052 | 17.6052 | 10.8684 | 21.6052 | 37.2103 | 54.8155 | 9.7368 | 10.8684 | 11.7368 | 10.7468 | 15.6052 | 17.6052 | 10.8684 | 21.6152 | 37.2203 | 54.8255 | 0.01
9.4739 | 10.7369 | 11.4739 | 10.4739 | 15.2108 | 17.2108 | 10.7369 | 21.2108 | 36.4216 | 53.6323 | 9.4739 | 10.7369 | 11.4739 | 10.4839 | 15.2108 | 17.2108 | 10.7369 | 21.2208 | 36.4316 | 53.6423 | 0.01
4.0971 | 8.0486 | 6.0971 | 5.0971 | 7.1457 | 9.1457 | 8.0486 | 13.1457 | 20.2913 | 29.437 | 4.0971 | 8.0486 | 6.0971 | 5.1071 | 7.1457 | 9.1457 | 8.0486 | 13.1557 | 20.3013 | 29.447 | 0.01
7.1106 | 9.5553 | 9.1106 | 8.1106 | 11.6659 | 13.6659 | 9.5553 | 17.6659 | 29.3318 | 42.9977 | 7.1106 | 9.5553 | 9.1106 | 8.1206 | 11.6659 | 13.6659 | 9.5553 | 17.6759 | 29.3418 | 43.0077 | 0.01
8.668 | 10.334 | 10.668 | 9.668 | 14.0021 | 16.0021 | 10.334 | 20.0021 | 34.0041 | 50.0062 | 8.668 | 10.334 | 10.668 | 9.678 | 14.0021 | 16.0021 | 10.334 | 20.0121 | 34.0141 | 50.0162 | 0.01
5.0877 | 8.5438 | 7.0877 | 6.0877 | 8.6315 | 10.6315 | 8.5438 | 14.6315 | 23.263 | 33.8945 | 5.0877 | 8.5438 | 7.0877 | 6.0977 | 8.6315 | 10.6315 | 8.5438 | 14.6415 | 23.273 | 33.9045 | 0.01
3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 3.9727 | 7.9863 | 5.9727 | 4.9827 | 6.959 | 8.959 | 7.9863 | 12.969 | 19.928 | 28.8869 | 0.01
6.5588 | 9.2794 | 8.5588 | 7.5588 | 10.8382 | 12.8382 | 9.2794 | 16.8382 | 27.6765 | 40.5147 | 6.5588 | 9.2794 | 8.5588 | 7.5688 | 10.8382 | 12.8382 | 9.2794 | 16.8482 | 27.6865 | 40.5247 | 0.01
5.3003 | 8.6502 | 7.3003 | 6.3003 | 8.9505 | 10.9505 | 8.6502 | 14.9505 | 23.901 | 34.8515 | 5.3003 | 8.6502 | 7.3003 | 6.3103 | 8.9505 | 10.9505 | 8.6502 | 14.9605 | 23.911 | 34.8615 | 0.01
5.3086 | 8.6543 | 7.3086 | 6.3086 | 8.9629 | 10.9629 | 8.6543 | 14.9629 | 23.9259 | 34.8888 | 5.3086 | 8.6543 | 7.3086 | 6.3186 | 8.9629 | 10.9629 | 8.6543 | 14.9729 | 23.9359 | 34.8988 | 0.01
4.5764 | 8.2882 | 6.5764 | 5.5764 | 7.8645 | 9.8645 | 8.2882 | 13.8645 | 21.7291 | 31.5936 | 4.5764 | 8.2882 | 6.5764 | 5.5864 | 7.8645 | 9.8645 | 8.2882 | 13.8745 | 21.7391 | 31.6036 | 0.01
5.9923 | 8.9961 | 7.9923 | 6.9923 | 9.9884 | 11.9884 | 8.9961 | 15.9884 | 25.9768 | 37.9652 | 5.9923 | 8.9961 | 7.9923 | 7.0023 | 9.9884 | 11.9884 | 8.9961 | 15.9984 | 25.9868 | 37.9752 | 0.01
2.2553 | 7.1277 | 4.2553 | 3.2553 | 4.383 | 6.383 | 7.1277 | 10.383 | 14.766 | 21.1489 | 2.2553 | 7.1277 | 4.2553 | 3.2653 | 4.383 | 6.383 | 7.1277 | 10.393 | 14.776 | 21.1589 | 0.01
3.77 | 7.885 | 5.77 | 4.77 | 6.6549 | 8.6549 | 7.885 | 12.6549 | 19.3099 | 27.9648 | 3.77 | 7.885 | 5.77 | 4.78 | 6.6549 | 8.6549 | 7.885 | 12.6649 | 19.3199 | 27.9748 | 0.01
5.0845 | 8.5422 | 7.0845 | 6.0845 | 8.6267 | 10.6267 | 8.5422 | 14.6267 | 23.2534 | 33.88 | 5.0845 | 8.5422 | 7.0845 | 6.0945 | 8.6267 | 10.6267 | 8.5422 | 14.6367 | 23.2634 | 33.89 | 0.01
10.4131 | 11.2066 | 12.4131 | 11.4131 | 16.6197 | 18.6197 | 11.2066 | 22.6197 | 39.2394 | 57.8591 | 10.4131 | 11.2066 | 12.4131 | 11.4231 | 16.6197 | 18.6197 | 11.2066 | 22.6297 | 39.2494 | 57.8691 | 0.01
6.5663 | 9.2831 | 8.5663 | 7.5663 | 10.8494 | 12.8494 | 9.2831 | 16.8494 | 27.6989 | 40.5483 | 6.5663 | 9.2831 | 8.5663 | 7.5763 | 10.8494 | 12.8494 | 9.2831 | 16.8594 | 27.7089 | 40.5583 | 0.01
5.6487 | 8.8243 | 7.6487 | 6.6487 | 9.473 | 11.473 | 8.8243 | 15.473 | 24.946 | 36.4191 | 5.6487 | 8.8243 | 7.6487 | 6.6587 | 9.473 | 11.473 | 8.8243 | 15.483 | 24.956 | 36.4291 | 0.01
7.5932 | 9.7966 | 9.5932 | 8.5932 | 12.3899 | 14.3899 | 9.7966 | 18.3899 | 30.7797 | 45.1696 | 7.5932 | 9.7966 | 9.5932 | 8.6032 | 12.3899 | 14.3899 | 9.7966 | 18.3999 | 30.7897 | 45.1796 | 0.01
3.3026 | 7.6513 | 5.3026 | 4.3026 | 5.9539 | 7.9539 | 7.6513 | 11.9539 | 17.9078 | 25.8617 | 3.3026 | 7.6513 | 5.3026 | 4.3126 | 5.9539 | 7.9539 | 7.6513 | 11.9639 | 17.9178 | 25.8717 | 0.01
3.76 | 7.88 | 5.76 | 4.76 | 6.6399 | 8.6399 | 7.88 | 12.6399 | 19.2799 | 27.9198 | 3.76 | 7.88 | 5.76 | 4.77 | 6.6399 | 8.6399 | 7.88 | 12.6499 | 19.2899 | 27.9298 | 0.01
5.8466 | 8.9233 | 7.8466 | 6.8466 | 9.7699 | 11.7699 | 8.9233 | 15.7699 | 25.5399 | 37.3098 | 5.8466 | 8.9233 | 7.8466 | 6.8566 | 9.7699 | 11.7699 | 8.9233 | 15.7799 | 25.5499 | 37.3198 | 0.01
6.6787 | 9.3394 | 8.6787 | 7.6787 | 11.0181 | 13.0181 | 9.3394 | 17.0181 | 28.0362 | 41.0543 | 6.6787 | 9.3394 | 8.6787 | 7.6887 | 11.0181 | 13.0181 | 9.3394 | 17.0281 | 28.0462 | 41.0643 | 0.01
5.4037 | 8.7018 | 7.4037 | 6.4037 | 9.1055 | 11.1055 | 8.7018 | 15.1055 | 24.2111 | 35.3166 | 5.4037 | 8.7018 | 7.4037 | 6.4137 | 9.1055 | 11.1055 | 8.7018 | 15.1155 | 24.2211 | 35.3266 | 0.01
6.474 | 9.237 | 8.474 | 7.474 | 10.711 | 12.711 | 9.237 | 16.711 | 27.4221 | 40.1331 | 6.474 | 9.237 | 8.474 | 7.484 | 10.711 | 12.711 | 9.237 | 16.721 | 27.4321 | 40.1431 | 0.01
6.1767 | 9.0884 | 8.1767 | 7.1767 | 10.2651 | 12.2651 | 9.0884 | 16.2651 | 26.5301 | 38.7952 | 6.1767 | 9.0884 | 8.1767 | 7.1867 | 10.2651 | 12.2651 | 9.0884 | 16.2751 | 26.5401 | 38.8052 | 0.01
6.604 | 9.302 | 8.604 | 7.604 | 10.906 | 12.906 | 9.302 | 16.906 | 27.812 | 40.7179 | 6.604 | 9.302 | 8.604 | 7.614 | 10.906 | 12.906 | 9.302 | 16.916 | 27.822 | 40.7279 | 0.01
4.67 | 8.335 | 6.67 | 5.67 | 8.005 | 10.005 | 8.335 | 14.005 | 22.0101 | 32.0151 | 4.67 | 8.335 | 6.67 | 5.68 | 8.005 | 10.005 | 8.335 | 14.015 | 22.0201 | 32.0251 | 0.01
5.3308 | 8.6654 | 7.3308 | 6.3308 | 8.9962 | 10.9962 | 8.6654 | 14.9962 | 23.9925 | 34.9887 | 5.3308 | 8.6654 | 7.3308 | 6.3408 | 8.9962 | 10.9962 | 8.6654 | 15.0062 | 24.0025 | 34.9987 | 0.01
5.7182 | 8.8591 | 7.7182 | 6.7182 | 9.5774 | 11.5774 | 8.8591 | 15.5774 | 25.1547 | 36.7321 | 5.7182 | 8.8591 | 7.7182 | 6.7282 | 9.5774 | 11.5774 | 8.8591 | 15.5874 | 25.1647 | 36.7421 | 0.01
1.3905 | 6.6952 | 3.3905 | 2.3905 | 3.0857 | 5.0857 | 6.6952 | 9.0857 | 12.1714 | 17.2571 | 1.3905 | 6.6952 | 3.3905 | 2.4005 | 3.0857 | 5.0857 | 6.6952 | 9.0957 | 12.1814 | 17.2671 | 0.01
4.6854 | 8.3427 | 6.6854 | 5.6854 | 8.0282 | 10.0282 | 8.3427 | 14.0282 | 22.0563 | 32.0845 | 4.6854 | 8.3427 | 6.6854 | 5.6954 | 8.0282 | 10.0282 | 8.3427 | 14.0382 | 22.0663 | 32.0945 | 0.01
4.5016 | 8.2508 | 6.5016 | 5.5016 | 7.7525 | 9.7525 | 8.2508 | 13.7525 | 21.5049 | 31.2574 | 4.5016 | 8.2508 | 6.5016 | 5.5116 | 7.7525 | 9.7525 | 8.2508 | 13.7625 | 21.5149 | 31.2674 | 0.01
3.0906 | 7.5453 | 5.0906 | 4.0906 | 5.6359 | 7.6359 | 7.5453 | 11.6359 | 17.2719 | 24.9078 | 3.0906 | 7.5453 | 5.0906 | 4.1006 | 5.6359 | 7.6359 | 7.5453 | 11.6459 | 17.2819 | 24.9178 | 0.01
3.6427 | 7.8213 | 5.6427 | 4.6427 | 6.464 | 8.464 | 7.8213 | 12.464 | 18.928 | 27.392 | 3.6427 | 7.8213 | 5.6427 | 4.6527 | 6.464 | 8.464 | 7.8213 | 12.474 | 18.938 | 27.402 | 0.01
3.7734 | 7.8867 | 5.7734 | 4.7734 | 6.66 | 8.66 | 7.8867 | 12.66 | 19.3201 | 27.9801 | 3.7734 | 7.8867 | 5.7734 | 4.7834 | 6.66 | 8.66 | 7.8867 | 12.67 | 19.3301 | 27.9901 | 0.01
5.5801 | 8.79 | 7.5801 | 6.5801 | 9.3701 | 11.3701 | 8.79 | 15.3701 | 24.7403 | 36.1104 | 5.5801 | 8.79 | 7.5801 | 6.5901 | 9.3701 | 11.3701 | 8.79 | 15.3801 | 24.7503 | 36.1204 | 0.01
7.3028 | 9.6514 | 9.3028 | 8.3028 | 11.9542 | 13.9542 | 9.6514 | 17.9542 | 29.9084 | 43.8626 | 7.3028 | 9.6514 | 9.3028 | 8.3128 | 11.9542 | 13.9542 | 9.6514 | 17.9642 | 29.9184 | 43.8726 | 0.01
4.8107 | 8.4054 | 6.8107 | 5.8107 | 8.2161 | 10.2161 | 8.4054 | 14.2161 | 22.4321 | 32.6482 | 4.8107 | 8.4054 | 6.8107 | 5.8207 | 8.2161 | 10.2161 | 8.4054 | 14.2261 | 22.4421 | 32.6582 | 0.01
6.0516 | 9.0258 | 8.0516 | 7.0516 | 10.0775 | 12.0775 | 9.0258 | 16.0775 | 26.1549 | 38.2324 | 6.0516 | 9.0258 | 8.0516 | 7.0616 | 10.0775 | 12.0775 | 9.0258 | 16.0875 | 26.1649 | 38.2424 | 0.01
7.0705 | 9.5352 | 9.0705 | 8.0705 | 11.6057 | 13.6057 | 9.5352 | 17.6057 | 29.2114 | 42.8171 | 7.0705 | 9.5352 | 9.0705 | 8.0805 | 11.6057 | 13.6057 | 9.5352 | 17.6157 | 29.2214 | 42.8271 | 0.01
7.2568 | 9.6284 | 9.2568 | 8.2568 | 11.8852 | 13.8852 | 9.6284 | 17.8852 | 29.7704 | 43.6556 | 7.2568 | 9.6284 | 9.2568 | 8.2668 | 11.8852 | 13.8852 | 9.6284 | 17.8952 | 29.7804 | 43.6656 | 0.01
5.5195 | 8.7598 | 7.5195 | 6.5195 | 9.2793 | 11.2793 | 8.7598 | 15.2793 | 24.5586 | 35.8378 | 5.5195 | 8.7598 | 7.5195 | 6.5295 | 9.2793 | 11.2793 | 8.7598 | 15.2893 | 24.5686 | 35.8478 | 0.01
7.7236 | 9.8618 | 9.7236 | 8.7236 | 12.5854 | 14.5854 | 9.8618 | 18.5854 | 31.1707 | 45.7561 | 7.7236 | 9.8618 | 9.7236 | 8.7336 | 12.5854 | 14.5854 | 9.8618 | 18.5954 | 31.1807 | 45.7661 | 0.01
7.4454 | 9.7227 | 9.4454 | 8.4454 | 12.1681 | 14.1681 | 9.7227 | 18.1681 | 30.3362 | 44.5043 | 7.4454 | 9.7227 | 9.4454 | 8.4554 | 12.1681 | 14.1681 | 9.7227 | 18.1781 | 30.3462 | 44.5143 | 0.01
7.2098 | 9.6049 | 9.2098 | 8.2098 | 11.8147 | 13.8147 | 9.6049 | 17.8147 | 29.6294 | 43.4441 | 7.2098 | 9.6049 | 9.2098 | 8.2198 | 11.8147 | 13.8147 | 9.6049 | 17.8247 | 29.6394 | 43.4541 | 0.01
8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 8.0477 | 10.0238 | 10.0477 | 9.0577 | 13.0715 | 15.0715 | 10.0238 | 19.0815 | 32.153 | 47.2244 | 0.01
5.3983 | 8.6991 | 7.3983 | 6.3983 | 9.0974 | 11.0974 | 8.6991 | 15.0974 | 24.1948 | 35.2922 | 5.3983 | 8.6991 | 7.3983 | 6.4083 | 9.0974 | 11.0974 | 8.6991 | 15.1074 | 24.2048 | 35.3022 | 0.01
8.1214 | 10.0607 | 10.1214 | 9.1214 | 13.1821 | 15.1821 | 10.0607 | 19.1821 | 32.3642 | 47.5463 | 8.1214 | 10.0607 | 10.1214 | 9.1314 | 13.1821 | 15.1821 | 10.0607 | 19.1921 | 32.3742 | 47.5563 | 0.01
5.6079 | 8.8039 | 7.6079 | 6.6079 | 9.4118 | 11.4118 | 8.8039 | 15.4118 | 24.8237 | 36.2355 | 5.6079 | 8.8039 | 7.6079 | 6.6179 | 9.4118 | 11.4118 | 8.8039 | 15.4218 | 24.8337 | 36.2455 | 0.01
6.4616 | 9.2308 | 8.4616 | 7.4616 | 10.6924 | 12.6924 | 9.2308 | 16.6924 | 27.3848 | 40.0772 | 6.4616 | 9.2308 | 8.4616 | 7.4716 | 10.6924 | 12.6924 | 9.2308 | 16.7024 | 27.3948 | 40.0872 | 0.01
5.8819 | 8.9409 | 7.8819 | 6.8819 | 9.8228 | 11.8228 | 8.9409 | 15.8228 | 25.6457 | 37.4685 | 5.8819 | 8.9409 | 7.8819 | 6.8919 | 9.8228 | 11.8228 | 8.9409 | 15.8328 | 25.6557 | 37.4785 | 0.01
3.8915 | 7.9457 | 5.8915 | 4.8915 | 6.8372 | 8.8372 | 7.9457 | 12.8372 | 19.6744 | 28.5115 | 3.8915 | 7.9457 | 5.8915 | 4.9015 | 6.8372 | 8.8372 | 7.9457 | 12.8472 | 19.6844 | 28.5215 | 0.01
3.9971 | 7.9985 | 5.9971 | 4.9971 | 6.9956 | 8.9956 | 7.9985 | 12.9956 | 19.9912 | 28.9868 | 3.9971 | 7.9985 | 5.9971 | 5.0071 | 6.9956 | 8.9956 | 7.9985 | 13.0056 | 20.0012 | 28.9968 | 0.01
6.3642 | 9.1821 | 8.3642 | 7.3642 | 10.5463 | 12.5463 | 9.1821 | 16.5463 | 27.0927 | 39.639 | 6.3642 | 9.1821 | 8.3642 | 7.3742 | 10.5463 | 12.5463 | 9.1821 | 16.5563 | 27.1027 | 39.649 | 0.01
9.0628 | 10.5314 | 11.0628 | 10.0628 | 14.5941 | 16.5941 | 10.5314 | 20.5941 | 35.1883 | 51.7824 | 9.0628 | 10.5314 | 11.0628 | 10.0728 | 14.5941 | 16.5941 | 10.5314 | 20.6041 | 35.1983 | 51.7924 | 0.01
6.7215 | 9.3608 | 8.7215 | 7.7215 | 11.0823 | 13.0823 | 9.3608 | 17.0823 | 28.1645 | 41.2468 | 6.7215 | 9.3608 | 8.7215 | 7.7315 | 11.0823 | 13.0823 | 9.3608 | 17.0923 | 28.1745 | 41.2568 | 0.01
7.5347 | 9.7673 | 9.5347 | 8.5347 | 12.302 | 14.302 | 9.7673 | 18.302 | 30.604 | 44.906 | 7.5347 | 9.7673 | 9.5347 | 8.5447 | 12.302 | 14.302 | 9.7673 | 18.312 | 30.614 | 44.916 | 0.01
4.2203 | 8.1102 | 6.2203 | 5.2203 | 7.3305 | 9.3305 | 8.1102 | 13.3305 | 20.6609 | 29.9914 | 4.2203 | 8.1102 | 6.2203 | 5.2303 | 7.3305 | 9.3305 | 8.1102 | 13.3405 | 20.6709 | 30.0014 | 0.01
4.9198 | 8.4599 | 6.9198 | 5.9198 | 8.3797 | 10.3797 | 8.4599 | 14.3797 | 22.7594 | 33.1391 | 4.9198 | 8.4599 | 6.9198 | 5.9298 | 8.3797 | 10.3797 | 8.4599 | 14.3897 | 22.7694 | 33.1491 | 0.01
3.252 | 7.626 | 5.252 | 4.252 | 5.878 | 7.878 | 7.626 | 11.878 | 17.7559 | 25.6339 | 3.252 | 7.626 | 5.252 | 4.262 | 5.878 | 7.878 | 7.626 | 11.888 | 17.7659 | 25.6439 | 0.01
6.2071 | 9.1036 | 8.2071 | 7.2071 | 10.3107 | 12.3107 | 9.1036 | 16.3107 | 26.6214 | 38.9322 | 6.2071 | 9.1036 | 8.2071 | 7.2171 | 10.3107 | 12.3107 | 9.1036 | 16.3207 | 26.6314 | 38.9422 | 0.01
6.9816 | 9.4908 | 8.9816 | 7.9816 | 11.4725 | 13.4725 | 9.4908 | 17.4725 | 28.9449 | 42.4174 | 6.9816 | 9.4908 | 8.9816 | 7.9916 | 11.4725 | 13.4725 | 9.4908 | 17.4825 | 28.9549 | 42.4274 | 0.01
4.3537 | 8.1768 | 6.3537 | 5.3537 | 7.5305 | 9.5305 | 8.1768 | 13.5305 | 21.061 | 30.5915 | 4.3537 | 8.1768 | 6.3537 | 5.3637 | 7.5305 | 9.5305 | 8.1768 | 13.5405 | 21.071 | 30.6015 | 0.01
7.4024 | 9.7012 | 9.4024 | 8.4024 | 12.1036 | 14.1036 | 9.7012 | 18.1036 | 30.2073 | 44.3109 | 7.4024 | 9.7012 | 9.4024 | 8.4124 | 12.1036 | 14.1036 | 9.7012 | 18.1136 | 30.2173 | 44.3209 | 0.01
5.2403 | 8.6202 | 7.2403 | 6.2403 | 8.8605 | 10.8605 | 8.6202 | 14.8605 | 23.7209 | 34.5814 | 5.2403 | 8.6202 | 7.2403 | 6.2503 | 8.8605 | 10.8605 | 8.6202 | 14.8705 | 23.7309 | 34.5914 | 0.01
6.5781 | 9.289 | 8.5781 | 7.5781 | 10.8671 | 12.8671 | 9.289 | 16.8671 | 27.7343 | 40.6014 | 6.5781 | 9.289 | 8.5781 | 7.5881 | 10.8671 | 12.8671 | 9.289 | 16.8771 | 27.7443 | 40.6114 | 0.01
7.6429 | 9.8215 | 9.6429 | 8.6429 | 12.4644 | 14.4644 | 9.8215 | 18.4644 | 30.9287 | 45.3931 | 7.6429 | 9.8215 | 9.6429 | 8.6529 | 12.4644 | 14.4644 | 9.8215 | 18.4744 | 30.9387 | 45.4031 | 0.01
6.3829 | 9.1915 | 8.3829 | 7.3829 | 10.5744 | 12.5744 | 9.1915 | 16.5744 | 27.1487 | 39.7231 | 6.3829 | 9.1915 | 8.3829 | 7.3929 | 10.5744 | 12.5744 | 9.1915 | 16.5844 | 27.1587 | 39.7331 | 0.01
3.4405 | 7.7202 | 5.4405 | 4.4405 | 6.1607 | 8.1607 | 7.7202 | 12.1607 | 18.3214 | 26.4821 | 3.4405 | 7.7202 | 5.4405 | 4.4505 | 6.1607 | 8.1607 | 7.7202 | 12.1707 | 18.3314 | 26.4921 | 0.01
8.5773 | 10.2887 | 10.5773 | 9.5773 | 13.866 | 15.866 | 10.2887 | 19.866 | 33.732 | 49.598 | 8.5773 | 10.2887 | 10.5773 | 9.5873 | 13.866 | 15.866 | 10.2887 | 19.876 | 33.742 | 49.608 | 0.01
8.9551 | 10.4775 | 10.9551 | 9.9551 | 14.4326 | 16.4326 | 10.4775 | 20.4326 | 34.8653 | 51.2979 | 8.9551 | 10.4775 | 10.9551 | 9.9651 | 14.4326 | 16.4326 | 10.4775 | 20.4426 | 34.8753 | 51.3079 | 0.01
5.4187 | 8.7094 | 7.4187 | 6.4187 | 9.1281 | 11.1281 | 8.7094 | 15.1281 | 24.2561 | 35.3842 | 5.4187 | 8.7094 | 7.4187 | 6.4287 | 9.1281 | 11.1281 | 8.7094 | 15.1381 | 24.2661 | 35.3942 | 0.01
5.3886 | 8.6943 | 7.3886 | 6.3886 | 9.083 | 11.083 | 8.6943 | 15.083 | 24.1659 | 35.2489 | 5.3886 | 8.6943 | 7.3886 | 6.3986 | 9.083 | 11.083 | 8.6943 | 15.093 | 24.1759 | 35.2589 | 0.01
8.0894 | 10.0447 | 10.0894 | 9.0894 | 13.1342 | 15.1342 | 10.0447 | 19.1342 | 32.2683 | 47.4025 | 8.0894 | 10.0447 | 10.0894 | 9.0994 | 13.1342 | 15.1342 | 10.0447 | 19.1442 | 32.2783 | 47.4125 | 0.01
9.5481 | 10.7741 | 11.5481 | 10.5481 | 15.3222 | 17.3222 | 10.7741 | 21.3222 | 36.6444 | 53.9666 | 9.5481 | 10.7741 | 11.5481 | 10.5581 | 15.3222 | 17.3222 | 10.7741 | 21.3322 | 36.6544 | 53.9766 | 0.01
8.3839 | 10.1919 | 10.3839 | 9.3839 | 13.5758 | 15.5758 | 10.1919 | 19.5758 | 33.1517 | 48.7275 | 8.3839 | 10.1919 | 10.3839 | 9.3939 | 13.5758 | 15.5758 | 10.1919 | 19.5858 | 33.1617 | 48.7375 | 0.01
5.3671 | 8.6836 | 7.3671 | 6.3671 | 9.0507 | 11.0507 | 8.6836 | 15.0507 | 24.1014 | 35.1521 | 5.3671 | 8.6836 | 7.3671 | 6.3771 | 9.0507 | 11.0507 | 8.6836 | 15.0607 | 24.1114 | 35.1621 | 0.01
6.4787 | 9.2394 | 8.4787 | 7.4787 | 10.7181 | 12.7181 | 9.2394 | 16.7181 | 27.4362 | 40.1544 | 6.4787 | 9.2394 | 8.4787 | 7.4887 | 10.7181 | 12.7181 | 9.2394 | 16.7281 | 27.4462 | 40.1644 | 0.01
9.3042 | 10.6521 | 11.3042 | 10.3042 | 14.9563 | 16.9563 | 10.6521 | 20.9563 | 35.9126 | 52.8689 | 9.3042 | 10.6521 | 11.3042 | 10.3142 | 14.9563 | 16.9563 | 10.6521 | 20.9663 | 35.9226 | 52.8789 | 0.01
2.544 | 7.272 | 4.544 | 3.544 | 4.816 | 6.816 | 7.272 | 10.816 | 15.632 | 22.448 | 2.544 | 7.272 | 4.544 | 3.554 | 4.816 | 6.816 | 7.272 | 10.826 | 15.642 | 22.458 | 0.01
4.3068 | 8.1534 | 6.3068 | 5.3068 | 7.4603 | 9.4603 | 8.1534 | 13.4603 | 20.9205 | 30.3808 | 4.3068 | 8.1534 | 6.3068 | 5.3168 | 7.4603 | 9.4603 | 8.1534 | 13.4703 | 20.9305 | 30.3908 | 0.01
4.3765 | 8.1883 | 6.3765 | 5.3765 | 7.5648 | 9.5648 | 8.1883 | 13.5648 | 21.1296 | 30.6944 | 4.3765 | 8.1883 | 6.3765 | 5.3865 | 7.5648 | 9.5648 | 8.1883 | 13.5748 | 21.1396 | 30.7044 | 0.01
8.9067 | 10.4534 | 10.9067 | 9.9067 | 14.3601 | 16.3601 | 10.4534 | 20.3601 | 34.7202 | 51.0803 | 8.9067 | 10.4534 | 10.9067 | 9.9167 | 14.3601 | 16.3601 | 10.4534 | 20.3701 | 34.7302 | 51.0903 | 0.01
5.8313 | 8.9156 | 7.8313 | 6.8313 | 9.7469 | 11.7469 | 8.9156 | 15.7469 | 25.4938 | 37.2407 | 5.8313 | 8.9156 | 7.8313 | 6.8413 | 9.7469 | 11.7469 | 8.9156 | 15.7569 | 25.5038 | 37.2507 | 0.01
5.7318 | 8.8659 | 7.7318 | 6.7318 | 9.5978 | 11.5978 | 8.8659 | 15.5978 | 25.1955 | 36.7933 | 5.7318 | 8.8659 | 7.7318 | 6.7418 | 9.5978 | 11.5978 | 8.8659 | 15.6078 | 25.2055 | 36.8033 | 0.01
4.0139 | 8.007 | 6.0139 | 5.0139 | 7.0209 | 9.0209 | 8.007 | 13.0209 | 20.0417 | 29.0626 | 4.0139 | 8.007 | 6.0139 | 5.0239 | 7.0209 | 9.0209 | 8.007 | 13.0309 | 20.0517 | 29.0726 | 0.01
4.3425 | 8.1712 | 6.3425 | 5.3425 | 7.5137 | 9.5137 | 8.1712 | 13.5137 | 21.0274 | 30.5411 | 4.3425 | 8.1712 | 6.3425 | 5.3525 | 7.5137 | 9.5137 | 8.1712 | 13.5237 | 21.0374 | 30.5511 | 0.01
6.3885 | 9.1943 | 8.3885 | 7.3885 | 10.5828 | 12.5828 | 9.1943 | 16.5828 | 27.1656 | 39.7483 | 6.3885 | 9.1943 | 8.3885 | 7.3985 | 10.5828 | 12.5828 | 9.1943 | 16.5928 | 27.1756 | 39.7583 | 0.01
4.828 | 8.414 | 6.828 | 5.828 | 8.242 | 10.242 | 8.414 | 14.242 | 22.484 | 32.726 | 4.828 | 8.414 | 6.828 | 5.838 | 8.242 | 10.242 | 8.414 | 14.252 | 22.494 | 32.736 | 0.01
4.4034 | 8.2017 | 6.4034 | 5.4034 | 7.6051 | 9.6051 | 8.2017 | 13.6051 | 21.2102 | 30.8153 | 4.4034 | 8.2017 | 6.4034 | 5.4134 | 7.6051 | 9.6051 | 8.2017 | 13.6151 | 21.2202 | 30.8253 | 0.01
4.8238 | 8.4119 | 6.8238 | 5.8238 | 8.2357 | 10.2357 | 8.4119 | 14.2357 | 22.4715 | 32.7072 | 4.8238 | 8.4119 | 6.8238 | 5.8338 | 8.2357 | 10.2357 | 8.4119 | 14.2457 | 22.4815 | 32.7172 | 0.01
2.2571 | 7.1285 | 4.2571 | 3.2571 | 4.3856 | 6.3856 | 7.1285 | 10.3856 | 14.7713 | 21.1569 | 2.2571 | 7.1285 | 4.2571 | 3.2671 | 4.3856 | 6.3856 | 7.1285 | 10.3956 | 14.7813 | 21.1669 | 0.01
7.5318 | 9.7659 | 9.5318 | 8.5318 | 12.2977 | 14.2977 | 9.7659 | 18.2977 | 30.5954 | 44.8931 | 7.5318 | 9.7659 | 9.5318 | 8.5418 | 12.2977 | 14.2977 | 9.7659 | 18.3077 | 30.6054 | 44.9031 | 0.01
5.7824 | 8.8912 | 7.7824 | 6.7824 | 9.6736 | 11.6736 | 8.8912 | 15.6736 | 25.3472 | 37.0208 | 5.7824 | 8.8912 | 7.7824 | 6.7924 | 9.6736 | 11.6736 | 8.8912 | 15.6836 | 25.3572 | 37.0308 | 0.01
5.2454 | 8.6227 | 7.2454 | 6.2454 | 8.8681 | 10.8681 | 8.6227 | 14.8681 | 23.7362 | 34.6043 | 5.2454 | 8.6227 | 7.2454 | 6.2554 | 8.8681 | 10.8681 | 8.6227 | 14.8781 | 23.7462 | 34.6143 | 0.01
4.8561 | 8.428 | 6.8561 | 5.8561 | 8.2841 | 10.2841 | 8.428 | 14.2841 | 22.5682 | 32.8522 | 4.8561 | 8.428 | 6.8561 | 5.8661 | 8.2841 | 10.2841 | 8.428 | 14.2941 | 22.5782 | 32.8622 | 0.01
8.4147 | 10.2073 | 10.4147 | 9.4147 | 13.622 | 15.622 | 10.2073 | 19.622 | 33.244 | 48.866 | 8.4147 | 10.2073 | 10.4147 | 9.4247 | 13.622 | 15.622 | 10.2073 | 19.632 | 33.254 | 48.876 | 0.01
6.6838 | 9.3419 | 8.6838 | 7.6838 | 11.0256 | 13.0256 | 9.3419 | 17.0256 | 28.0513 | 41.0769 | 6.6838 | 9.3419 | 8.6838 | 7.6938 | 11.0256 | 13.0256 | 9.3419 | 17.0356 | 28.0613 | 41.0869 | 0.01
0.96635 | 6.4832 | 2.9663 | 1.9663 | 2.4495 | 4.4495 | 6.4832 | 8.4495 | 10.899 | 15.3486 | 0.96635 | 6.4832 | 2.9663 | 1.9763 | 2.4495 | 4.4495 | 6.4832 | 8.4595 | 10.909 | 15.3586 | 0.01
7.0703 | 9.5351 | 9.0703 | 8.0703 | 11.6054 | 13.6054 | 9.5351 | 17.6054 | 29.2109 | 42.8163 | 7.0703 | 9.5351 | 9.0703 | 8.0803 | 11.6054 | 13.6054 | 9.5351 | 17.6154 | 29.2209 | 42.8263 | 0.01
7.017 | 9.5085 | 9.017 | 8.017 | 11.5255 | 13.5255 | 9.5085 | 17.5255 | 29.051 | 42.5765 | 7.017 | 9.5085 | 9.017 | 8.027 | 11.5255 | 13.5255 | 9.5085 | 17.5355 | 29.061 | 42.5865 | 0.01
5.4393 | 8.7196 | 7.4393 | 6.4393 | 9.1589 | 11.1589 | 8.7196 | 15.1589 | 24.3178 | 35.4767 | 5.4393 | 8.7196 | 7.4393 | 6.4493 | 9.1589 | 11.1589 | 8.7196 | 15.1689 | 24.3278 | 35.4867 | 0.01
2.5841 | 7.2921 | 4.5841 | 3.5841 | 4.8762 | 6.8762 | 7.2921 | 10.8762 | 15.7524 | 22.6286 | 2.5841 | 7.2921 | 4.5841 | 3.5941 | 4.8762 | 6.8762 | 7.2921 | 10.8862 | 15.7624 | 22.6386 | 0.01
3.8108 | 7.9054 | 5.8108 | 4.8108 | 6.7162 | 8.7162 | 7.9054 | 12.7162 | 19.4324 | 28.1486 | 3.8108 | 7.9054 | 5.8108 | 4.8208 | 6.7162 | 8.7162 | 7.9054 | 12.7262 | 19.4424 | 28.1586 | 0.01
5.3143 | 8.6572 | 7.3143 | 6.3143 | 8.9715 | 10.9715 | 8.6572 | 14.9715 | 23.9429 | 34.9144 | 5.3143 | 8.6572 | 7.3143 | 6.3243 | 8.9715 | 10.9715 | 8.6572 | 14.9815 | 23.9529 | 34.9244 | 0.01
6.6577 | 9.3288 | 8.6577 | 7.6577 | 10.9865 | 12.9865 | 9.3288 | 16.9865 | 27.9731 | 40.9596 | 6.6577 | 9.3288 | 8.6577 | 7.6677 | 10.9865 | 12.9865 | 9.3288 | 16.9965 | 27.9831 | 40.9696 | 0.01
3.0098 | 7.5049 | 5.0098 | 4.0098 | 5.5147 | 7.5147 | 7.5049 | 11.5147 | 17.0295 | 24.5442 | 3.0098 | 7.5049 | 5.0098 | 4.0198 | 5.5147 | 7.5147 | 7.5049 | 11.5247 | 17.0395 | 24.5542 | 0.01
5.1527 | 8.5764 | 7.1527 | 6.1527 | 8.7291 | 10.7291 | 8.5764 | 14.7291 | 23.4582 | 34.1873 | 5.1527 | 8.5764 | 7.1527 | 6.1627 | 8.7291 | 10.7291 | 8.5764 | 14.7391 | 23.4682 | 34.1973 | 0.01
5.8825 | 8.9413 | 7.8825 | 6.8825 | 9.8238 | 11.8238 | 8.9413 | 15.8238 | 25.6475 | 37.4713 | 5.8825 | 8.9413 | 7.8825 | 6.8925 | 9.8238 | 11.8238 | 8.9413 | 15.8338 | 25.6575 | 37.4813 | 0.01
6.6117 | 9.3058 | 8.6117 | 7.6117 | 10.9175 | 12.9175 | 9.3058 | 16.9175 | 27.835 | 40.7525 | 6.6117 | 9.3058 | 8.6117 | 7.6217 | 10.9175 | 12.9175 | 9.3058 | 16.9275 | 27.845 | 40.7625 | 0.01
7.5536 | 9.7768 | 9.5536 | 8.5536 | 12.3304 | 14.3304 | 9.7768 | 18.3304 | 30.6609 | 44.9913 | 7.5536 | 9.7768 | 9.5536 | 8.5636 | 12.3304 | 14.3304 | 9.7768 | 18.3404 | 30.6709 | 45.0013 | 0.01
3.9811 | 7.9905 | 5.9811 | 4.9811 | 6.9716 | 8.9716 | 7.9905 | 12.9716 | 19.9432 | 28.9148 | 3.9811 | 7.9905 | 5.9811 | 4.9911 | 6.9716 | 8.9716 | 7.9905 | 12.9816 | 19.9532 | 28.9248 | 0.01
2.7565 | 7.3783 | 4.7565 | 3.7565 | 5.1348 | 7.1348 | 7.3783 | 11.1348 | 16.2696 | 23.4044 | 2.7565 | 7.3783 | 4.7565 | 3.7665 | 5.1348 | 7.1348 | 7.3783 | 11.1448 | 16.2796 | 23.4144 | 0.01
1.279 | 6.6395 | 3.279 | 2.279 | 2.9185 | 4.9185 | 6.6395 | 8.9185 | 11.837 | 16.7555 | 1.279 | 6.6395 | 3.279 | 2.289 | 2.9185 | 4.9185 | 6.6395 | 8.9285 | 11.847 | 16.7655 | 0.01
6.3987 | 9.1993 | 8.3987 | 7.3987 | 10.598 | 12.598 | 9.1993 | 16.598 | 27.196 | 39.794 | 6.3987 | 9.1993 | 8.3987 | 7.4087 | 10.598 | 12.598 | 9.1993 | 16.608 | 27.206 | 39.804 | 0.01
8.8962 | 10.4481 | 10.8962 | 9.8962 | 14.3443 | 16.3443 | 10.4481 | 20.3443 | 34.6886 | 51.033 | 8.8962 | 10.4481 | 10.8962 | 9.9062 | 14.3443 | 16.3443 | 10.4481 | 20.3543 | 34.6986 | 51.043 | 0.01
3.2532 | 7.6266 | 5.2532 | 4.2532 | 5.8797 | 7.8797 | 7.6266 | 11.8797 | 17.7595 | 25.6392 | 3.2532 | 7.6266 | 5.2532 | 4.2632 | 5.8797 | 7.8797 | 7.6266 | 11.8897 | 17.7695 | 25.6492 | 0.01
5.4748 | 8.7374 | 7.4748 | 6.4748 | 9.2122 | 11.2122 | 8.7374 | 15.2122 | 24.4245 | 35.6367 | 5.4748 | 8.7374 | 7.4748 | 6.4848 | 9.2122 | 11.2122 | 8.7374 | 15.2222 | 24.4345 | 35.6467 | 0.01
5.6701 | 8.8351 | 7.6701 | 6.6701 | 9.5052 | 11.5052 | 8.8351 | 15.5052 | 25.0103 | 36.5155 | 5.6701 | 8.8351 | 7.6701 | 6.6801 | 9.5052 | 11.5052 | 8.8351 | 15.5152 | 25.0203 | 36.5255 | 0.01
8.5124 | 10.2562 | 10.5124 | 9.5124 | 13.7685 | 15.7685 | 10.2562 | 19.7685 | 33.5371 | 49.3056 | 8.5124 | 10.2562 | 10.5124 | 9.5224 | 13.7685 | 15.7685 | 10.2562 | 19.7785 | 33.5471 | 49.3156 | 0.01
7.7278 | 9.8639 | 9.7278 | 8.7278 | 12.5917 | 14.5917 | 9.8639 | 18.5917 | 31.1834 | 45.7751 | 7.7278 | 9.8639 | 9.7278 | 8.7378 | 12.5917 | 14.5917 | 9.8639 | 18.6017 | 31.1934 | 45.7851 | 0.01
6.6958 | 9.3479 | 8.6958 | 7.6958 | 11.0437 | 13.0437 | 9.3479 | 17.0437 | 28.0873 | 41.131 | 6.6958 | 9.3479 | 8.6958 | 7.7058 | 11.0437 | 13.0437 | 9.3479 | 17.0537 | 28.0973 | 41.141 | 0.01
6.6747 | 9.3373 | 8.6747 | 7.6747 | 11.012 | 13.012 | 9.3373 | 17.012 | 28.024 | 41.036 | 6.6747 | 9.3373 | 8.6747 | 7.6847 | 11.012 | 13.012 | 9.3373 | 17.022 | 28.034 | 41.046 | 0.01
4.1136 | 8.0568 | 6.1136 | 5.1136 | 7.1705 | 9.1705 | 8.0568 | 13.1705 | 20.3409 | 29.5114 | 4.1136 | 8.0568 | 6.1136 | 5.1236 | 7.1705 | 9.1705 | 8.0568 | 13.1805 | 20.3509 | 29.5214 | 0.01
6.0322 | 9.0161 | 8.0322 | 7.0322 | 10.0483 | 12.0483 | 9.0161 | 16.0483 | 26.0966 | 38.1449 | 6.0322 | 9.0161 | 8.0322 | 7.0422 | 10.0483 | 12.0483 | 9.0161 | 16.0583 | 26.1066 | 38.1549 | 0.01
6.0533 | 9.0267 | 8.0533 | 7.0533 | 10.08 | 12.08 | 9.0267 | 16.08 | 26.16 | 38.24 | 6.0533 | 9.0267 | 8.0533 | 7.0633 | 10.08 | 12.08 | 9.0267 | 16.09 | 26.17 | 38.25 | 0.01
5.3099 | 8.655 | 7.3099 | 6.3099 | 8.9649 | 10.9649 | 8.655 | 14.9649 | 23.9298 | 34.8946 | 5.3099 | 8.655 | 7.3099 | 6.3199 | 8.9649 | 10.9649 | 8.655 | 14.9749 | 23.9398 | 34.9046 | 0.01
2.783 | 7.3915 | 4.783 | 3.783 | 5.1746 | 7.1746 | 7.3915 | 11.1746 | 16.3491 | 23.5237 | 2.783 | 7.3915 | 4.783 | 3.793 | 5.1746 | 7.1746 | 7.3915 | 11.1846 | 16.3591 | 23.5337 | 0.01
4.1082 | 8.0541 | 6.1082 | 5.1082 | 7.1622 | 9.1622 | 8.0541 | 13.1622 | 20.3245 | 29.4867 | 4.1082 | 8.0541 | 6.1082 | 5.1182 | 7.1622 | 9.1622 | 8.0541 | 13.1722 | 20.3345 | 29.4967 | 0.01
9.1167 | 10.5584 | 11.1167 | 10.1167 | 14.6751 | 16.6751 | 10.5584 | 20.6751 | 35.3502 | 52.0254 | 9.1167 | 10.5584 | 11.1167 | 10.1267 | 14.6751 | 16.6751 | 10.5584 | 20.6851 | 35.3602 | 52.0354 | 0.01
7.2546 | 9.6273 | 9.2546 | 8.2546 | 11.8819 | 13.8819 | 9.6273 | 17.8819 | 29.7637 | 43.6456 | 7.2546 | 9.6273 | 9.2546 | 8.2646 | 11.8819 | 13.8819 | 9.6273 | 17.8919 | 29.7737 | 43.6556 | 0.01
3.9195 | 7.9598 | 5.9195 | 4.9195 | 6.8793 | 8.8793 | 7.9598 | 12.8793 | 19.7585 | 28.6378 | 3.9195 | 7.9598 | 5.9195 | 4.9295 | 6.8793 | 8.8793 | 7.9598 | 12.8893 | 19.7685 | 28.6478 | 0.01
7.2151 | 9.6076 | 9.2151 | 8.2151 | 11.8227 | 13.8227 | 9.6076 | 17.8227 | 29.6454 | 43.4681 | 7.2151 | 9.6076 | 9.2151 | 8.2251 | 11.8227 | 13.8227 | 9.6076 | 17.8327 | 29.6554 | 43.4781 | 0.01
5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 5.3943 | 8.6971 | 7.3943 | 6.4043 | 9.0914 | 11.0914 | 8.6971 | 15.1014 | 24.1928 | 35.2841 | 0.01
4.1806 | 8.0903 | 6.1806 | 5.1806 | 7.2709 | 9.2709 | 8.0903 | 13.2709 | 20.5419 | 29.8128 | 4.1806 | 8.0903 | 6.1806 | 5.1906 | 7.2709 | 9.2709 | 8.0903 | 13.2809 | 20.5519 | 29.8228 | 0.01
4.4304 | 8.2152 | 6.4304 | 5.4304 | 7.6456 | 9.6456 | 8.2152 | 13.6456 | 21.2912 | 30.9368 | 4.4304 | 8.2152 | 6.4304 | 5.4404 | 7.6456 | 9.6456 | 8.2152 | 13.6556 | 21.3012 | 30.9468 | 0.01
4.0583 | 8.0291 | 6.0583 | 5.0583 | 7.0874 | 9.0874 | 8.0291 | 13.0874 | 20.1748 | 29.2622 | 4.0583 | 8.0291 | 6.0583 | 5.0683 | 7.0874 | 9.0874 | 8.0291 | 13.0974 | 20.1848 | 29.2722 | 0.01
6.3386 | 9.1693 | 8.3386 | 7.3386 | 10.5079 | 12.5079 | 9.1693 | 16.5079 | 27.0158 | 39.5236 | 6.3386 | 9.1693 | 8.3386 | 7.3486 | 10.5079 | 12.5079 | 9.1693 | 16.5179 | 27.0258 | 39.5336 | 0.01
8.3318 | 10.1659 | 10.3318 | 9.3318 | 13.4977 | 15.4977 | 10.1659 | 19.4977 | 32.9953 | 48.493 | 8.3318 | 10.1659 | 10.3318 | 9.3418 | 13.4977 | 15.4977 | 10.1659 | 19.5077 | 33.0053 | 48.503 | 0.01
3.4866 | 7.7433 | 5.4866 | 4.4866 | 6.23 | 8.23 | 7.7433 | 12.23 | 18.4599 | 26.6899 | 3.4866 | 7.7433 | 5.4866 | 4.4966 | 6.23 | 8.23 | 7.7433 | 12.24 | 18.4699 | 26.6999 | 0.01
5.145 | 8.5725 | 7.145 | 6.145 | 8.7175 | 10.7175 | 8.5725 | 14.7175 | 23.4351 | 34.1526 | 5.145 | 8.5725 | 7.145 | 6.155 | 8.7175 | 10.7175 | 8.5725 | 14.7275 | 23.4451 | 34.1626 | 0.01
4.7066 | 8.3533 | 6.7066 | 5.7066 | 8.06 | 10.06 | 8.3533 | 14.06 | 22.1199 | 32.1799 | 4.7066 | 8.3533 | 6.7066 | 5.7166 | 8.06 | 10.06 | 8.3533 | 14.07 | 22.1299 | 32.1899 | 0.01
3.6298 | 7.8149 | 5.6298 | 4.6298 | 6.4446 | 8.4446 | 7.8149 | 12.4446 | 18.8893 | 27.3339 | 3.6298 | 7.8149 | 5.6298 | 4.6398 | 6.4446 | 8.4446 | 7.8149 | 12.4546 | 18.8993 | 27.3439 | 0.01
7.1394 | 9.5697 | 9.1394 | 8.1394 | 11.7092 | 13.7092 | 9.5697 | 17.7092 | 29.4183 | 43.1275 | 7.1394 | 9.5697 | 9.1394 | 8.1494 | 11.7092 | 13.7092 | 9.5697 | 17.7192 | 29.4283 | 43.1375 | 0.01
6.9539 | 9.477 | 8.9539 | 7.9539 | 11.4309 | 13.4309 | 9.477 | 17.4309 | 28.8618 | 42.2928 | 6.9539 | 9.477 | 8.9539 | 7.9639 | 11.4309 | 13.4309 | 9.477 | 17.4409 | 28.8718 | 42.3028 | 0.01
3.8824 | 7.9412 | 5.8824 | 4.8824 | 6.8235 | 8.8235 | 7.9412 | 12.8235 | 19.6471 | 28.4706 | 3.8824 | 7.9412 | 5.8824 | 4.8924 | 6.8235 | 8.8235 | 7.9412 | 12.8335 | 19.6571 | 28.4806 | 0.01
4.5081 | 8.2541 | 6.5081 | 5.5081 | 7.7622 | 9.7622 | 8.2541 | 13.7622 | 21.5243 | 31.2865 | 4.5081 | 8.2541 | 6.5081 | 5.5181 | 7.7622 | 9.7622 | 8.2541 | 13.7722 | 21.5343 | 31.2965 | 0.01
5.4401 | 8.72 | 7.4401 | 6.4401 | 9.1601 | 11.1601 | 8.72 | 15.1601 | 24.3202 | 35.4803 | 5.4401 | 8.72 | 7.4401 | 6.4501 | 9.1601 | 11.1601 | 8.72 | 15.1701 | 24.3302 | 35.4903 | 0.01
7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 7.2212 | 9.6106 | 9.2212 | 8.2312 | 11.8318 | 13.8318 | 9.6106 | 17.8418 | 29.6736 | 43.5055 | 0.01
6.3068 | 9.1534 | 8.3068 | 7.3068 | 10.4602 | 12.4602 | 9.1534 | 16.4602 | 26.9204 | 39.3807 | 6.3068 | 9.1534 | 8.3068 | 7.3168 | 10.4602 | 12.4602 | 9.1534 | 16.4702 | 26.9304 | 39.3907 | 0.01
2.4541 | 7.227 | 4.4541 | 3.4541 | 4.6811 | 6.6811 | 7.227 | 10.6811 | 15.3622 | 22.0434 | 2.4541 | 7.227 | 4.4541 | 3.4641 | 4.6811 | 6.6811 | 7.227 | 10.6911 | 15.3722 | 22.0534 | 0.01
6.616 | 9.308 | 8.616 | 7.616 | 10.924 | 12.924 | 9.308 | 16.924 | 27.848 | 40.772 | 6.616 | 9.308 | 8.616 | 7.626 | 10.924 | 12.924 | 9.308 | 16.934 | 27.858 | 40.782 | 0.01
6.1816 | 9.0908 | 8.1816 | 7.1816 | 10.2724 | 12.2724 | 9.0908 | 16.2724 | 26.5449 | 38.8173 | 6.1816 | 9.0908 | 8.1816 | 7.1916 | 10.2724 | 12.2724 | 9.0908 | 16.2824 | 26.5549 | 38.8273 | 0.01
4.1669 | 8.0835 | 6.1669 | 5.1669 | 7.2504 | 9.2504 | 8.0835 | 13.2504 | 20.5008 | 29.7512 | 4.1669 | 8.0835 | 6.1669 | 5.1769 | 7.2504 | 9.2504 | 8.0835 | 13.2604 | 20.5108 | 29.7612 | 0.01
5.6994 | 8.8497 | 7.6994 | 6.6994 | 9.5491 | 11.5491 | 8.8497 | 15.5491 | 25.0981 | 36.6472 | 5.6994 | 8.8497 | 7.6994 | 6.7094 | 9.5491 | 11.5491 | 8.8497 | 15.5591 | 25.1081 | 36.6572 | 0.01
6.0425 | 9.0212 | 8.0425 | 7.0425 | 10.0637 | 12.0637 | 9.0212 | 16.0637 | 26.1274 | 38.1911 | 6.0425 | 9.0212 | 8.0425 | 7.0525 | 10.0637 | 12.0637 | 9.0212 | 16.0737 | 26.1374 | 38.2011 | 0.01
10.3015 | 11.1508 | 12.3015 | 11.3015 | 16.4523 | 18.4523 | 11.1508 | 22.4523 | 38.9045 | 57.3568 | 10.3015 | 11.1508 | 12.3015 | 11.3115 | 16.4523 | 18.4523 | 11.1508 | 22.4623 | 38.9145 | 57.3668 | 0.01
5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 5.0973 | 8.5487 | 7.0973 | 6.1073 | 8.646 | 10.646 | 8.5487 | 14.656 | 23.302 | 33.9481 | 0.01
2.9544 | 7.4772 | 4.9544 | 3.9544 | 5.4316 | 7.4316 | 7.4772 | 11.4316 | 16.8633 | 24.2949 | 2.9544 | 7.4772 | 4.9544 | 3.9644 | 5.4316 | 7.4316 | 7.4772 | 11.4416 | 16.8733 | 24.3049 | 0.01
8.086 | 10.043 | 10.086 | 9.086 | 13.129 | 15.129 | 10.043 | 19.129 | 32.258 | 47.3871 | 8.086 | 10.043 | 10.086 | 9.096 | 13.129 | 15.129 | 10.043 | 19.139 | 32.268 | 47.3971 | 0.01
3.5671 | 7.7836 | 5.5671 | 4.5671 | 6.3507 | 8.3507 | 7.7836 | 12.3507 | 18.7014 | 27.0522 | 3.5671 | 7.7836 | 5.5671 | 4.5771 | 6.3507 | 8.3507 | 7.7836 | 12.3607 | 18.7114 | 27.0622 | 0.01
3.1336 | 7.5668 | 5.1336 | 4.1336 | 5.7004 | 7.7004 | 7.5668 | 11.7004 | 17.4008 | 25.1012 | 3.1336 | 7.5668 | 5.1336 | 4.1436 | 5.7004 | 7.7004 | 7.5668 | 11.7104 | 17.4108 | 25.1112 | 0.01
6.5277 | 9.2639 | 8.5277 | 7.5277 | 10.7916 | 12.7916 | 9.2639 | 16.7916 | 27.5831 | 40.3747 | 6.5277 | 9.2639 | 8.5277 | 7.5377 | 10.7916 | 12.7916 | 9.2639 | 16.8016 | 27.5931 | 40.3847 | 0.01
4.9065 | 8.4533 | 6.9065 | 5.9065 | 8.3598 | 10.3598 | 8.4533 | 14.3598 | 22.7195 | 33.0793 | 4.9065 | 8.4533 | 6.9065 | 5.9165 | 8.3598 | 10.3598 | 8.4533 | 14.3698 | 22.7295 | 33.0893 | 0.01
5.0165 | 8.5082 | 7.0165 | 6.0165 | 8.5247 | 10.5247 | 8.5082 | 14.5247 | 23.0494 | 33.5741 | 5.0165 | 8.5082 | 7.0165 | 6.0265 | 8.5247 | 10.5247 | 8.5082 | 14.5347 | 23.0594 | 33.5841 | 0.01
7.6593 | 9.8296 | 9.6593 | 8.6593 | 12.4889 | 14.4889 | 9.8296 | 18.4889 | 30.9778 | 45.4666 | 7.6593 | 9.8296 | 9.6593 | 8.6693 | 12.4889 | 14.4889 | 9.8296 | 18.4989 | 30.9878 | 45.4766 | 0.01
7.9067 | 9.9534 | 9.9067 | 8.9067 | 12.8601 | 14.8601 | 9.9534 | 18.8601 | 31.7202 | 46.5803 | 7.9067 | 9.9534 | 9.9067 | 8.9167 | 12.8601 | 14.8601 | 9.9534 | 18.8701 | 31.7302 | 46.5903 | 0.01
5.5669 | 8.7835 | 7.5669 | 6.5669 | 9.3504 | 11.3504 | 8.7835 | 15.3504 | 24.7008 | 36.0513 | 5.5669 | 8.7835 | 7.5669 | 6.5769 | 9.3504 | 11.3504 | 8.7835 | 15.3604 | 24.7108 | 36.0613 | 0.01
6.8194 | 9.4097 | 8.8194 | 7.8194 | 11.2291 | 13.2291 | 9.4097 | 17.2291 | 28.4582 | 41.6873 | 6.8194 | 9.4097 | 8.8194 | 7.8294 | 11.2291 | 13.2291 | 9.4097 | 17.2391 | 28.4682 | 41.6973 | 0.01
4.8316 | 8.4158 | 6.8316 | 5.8316 | 8.2475 | 10.2475 | 8.4158 | 14.2475 | 22.4949 | 32.7424 | 4.8316 | 8.4158 | 6.8316 | 5.8416 | 8.2475 | 10.2475 | 8.4158 | 14.2575 | 22.5049 | 32.7524 | 0.01
7.73 | 9.865 | 9.73 | 8.73 | 12.595 | 14.595 | 9.865 | 18.595 | 31.19 | 45.785 | 7.73 | 9.865 | 9.73 | 8.74 | 12.595 | 14.595 | 9.865 | 18.605 | 31.2 | 45.795 | 0.01
4.3301 | 8.1651 | 6.3301 | 5.3301 | 7.4952 | 9.4952 | 8.1651 | 13.4952 | 20.9904 | 30.4857 | 4.3301 | 8.1651 | 6.3301 | 5.3401 | 7.4952 | 9.4952 | 8.1651 | 13.5052 | 21.0004 | 30.4957 | 0.01
4.0174 | 8.0087 | 6.0174 | 5.0174 | 7.0261 | 9.0261 | 8.0087 | 13.0261 | 20.0522 | 29.0784 | 4.0174 | 8.0087 | 6.0174 | 5.0274 | 7.0261 | 9.0261 | 8.0087 | 13.0361 | 20.0622 | 29.0884 | 0.01
3.7223 | 7.8612 | 5.7223 | 4.7223 | 6.5835 | 8.5835 | 7.8612 | 12.5835 | 19.1669 | 27.7504 | 3.7223 | 7.8612 | 5.7223 | 4.7323 | 6.5835 | 8.5835 | 7.8612 | 12.5935 | 19.1769 | 27.7604 | 0.01
5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 5.2901 | 8.645 | 7.2901 | 6.3001 | 8.9351 | 10.9351 | 8.645 | 14.9451 | 23.8802 | 34.8153 | 0.01
7.4619 | 9.731 | 9.4619 | 8.4619 | 12.1929 | 14.1929 | 9.731 | 18.1929 | 30.3858 | 44.5787 | 7.4619 | 9.731 | 9.4619 | 8.4719 | 12.1929 | 14.1929 | 9.731 | 18.2029 | 30.3958 | 44.5887 | 0.01
4.2939 | 8.1469 | 6.2939 | 5.2939 | 7.4408 | 9.4408 | 8.1469 | 13.4408 | 20.8817 | 30.3225 | 4.2939 | 8.1469 | 6.2939 | 5.3039 | 7.4408 | 9.4408 | 8.1469 | 13.4508 | 20.8917 | 30.3325 | 0.01
6.2435 | 9.1217 | 8.2435 | 7.2435 | 10.3652 | 12.3652 | 9.1217 | 16.3652 | 26.7304 | 39.0957 | 6.2435 | 9.1217 | 8.2435 | 7.2535 | 10.3652 | 12.3652 | 9.1217 | 16.3752 | 26.7404 | 39.1057 | 0.01
5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 5.0921 | 8.546 | 7.0921 | 6.1021 | 8.6381 | 10.6381 | 8.546 | 14.6481 | 23.2863 | 33.9244 | 0.01
7.367 | 9.6835 | 9.367 | 8.367 | 12.0506 | 14.0506 | 9.6835 | 18.0506 | 30.1011 | 44.1517 | 7.367 | 9.6835 | 9.367 | 8.377 | 12.0506 | 14.0506 | 9.6835 | 18.0606 | 30.1111 | 44.1617 | 0.01
9.1555 | 10.5777 | 11.1555 | 10.1555 | 14.7332 | 16.7332 | 10.5777 | 20.7332 | 35.4664 | 52.1996 | 9.1555 | 10.5777 | 11.1555 | 10.1655 | 14.7332 | 16.7332 | 10.5777 | 20.7432 | 35.4764 | 52.2096 | 0.01
4.4266 | 8.2133 | 6.4266 | 5.4266 | 7.64 | 9.64 | 8.2133 | 13.64 | 21.2799 | 30.9199 | 4.4266 | 8.2133 | 6.4266 | 5.4366 | 7.64 | 9.64 | 8.2133 | 13.65 | 21.2899 | 30.9299 | 0.01
6.4001 | 9.2 | 8.4001 | 7.4001 | 10.6001 | 12.6001 | 9.2 | 16.6001 | 27.2002 | 39.8003 | 6.4001 | 9.2 | 8.4001 | 7.4101 | 10.6001 | 12.6001 | 9.2 | 16.6101 | 27.2102 | 39.8103 | 0.01
5.0045 | 8.5023 | 7.0045 | 6.0045 | 8.5068 | 10.5068 | 8.5023 | 14.5068 | 23.0136 | 33.5204 | 5.0045 | 8.5023 | 7.0045 | 6.0145 | 8.5068 | 10.5068 | 8.5023 | 14.5168 | 23.0236 | 33.5304 | 0.01
2.7353 | 7.3676 | 4.7353 | 3.7353 | 5.1029 | 7.1029 | 7.3676 | 11.1029 | 16.2058 | 23.3088 | 2.7353 | 7.3676 | 4.7353 | 3.7453 | 5.1029 | 7.1029 | 7.3676 | 11.1129 | 16.2158 | 23.3188 | 0.01
5.211 | 8.6055 | 7.211 | 6.211 | 8.8164 | 10.8164 | 8.6055 | 14.8164 | 23.6329 | 34.4493 | 5.211 | 8.6055 | 7.211 | 6.221 | 8.8164 | 10.8164 | 8.6055 | 14.8264 | 23.6429 | 34.4593 | 0.01
5.7148 | 8.8574 | 7.7148 | 6.7148 | 9.5723 | 11.5723 | 8.8574 | 15.5723 | 25.1445 | 36.7168 | 5.7148 | 8.8574 | 7.7148 | 6.7248 | 9.5723 | 11.5723 | 8.8574 | 15.5823 | 25.1545 | 36.7268 | 0.01
2.991 | 7.4955 | 4.991 | 3.991 | 5.4865 | 7.4865 | 7.4955 | 11.4865 | 16.9729 | 24.4594 | 2.991 | 7.4955 | 4.991 | 4.001 | 5.4865 | 7.4865 | 7.4955 | 11.4965 | 16.9829 | 24.4694 | 0.01
5.3673 | 8.6836 | 7.3673 | 6.3673 | 9.0509 | 11.0509 | 8.6836 | 15.0509 | 24.1019 | 35.1528 | 5.3673 | 8.6836 | 7.3673 | 6.3773 | 9.0509 | 11.0509 | 8.6836 | 15.0609 | 24.1119 | 35.1628 | 0.01
6.8222 | 9.4111 | 8.8222 | 7.8222 | 11.2333 | 13.2333 | 9.4111 | 17.2333 | 28.4667 | 41.7 | 6.8222 | 9.4111 | 8.8222 | 7.8322 | 11.2333 | 13.2333 | 9.4111 | 17.2433 | 28.4767 | 41.71 | 0.01
5.639 | 8.8195 | 7.639 | 6.639 | 9.4586 | 11.4586 | 8.8195 | 15.4586 | 24.9171 | 36.3757 | 5.639 | 8.8195 | 7.639 | 6.649 | 9.4586 | 11.4586 | 8.8195 | 15.4686 | 24.9271 | 36.3857 | 0.01
10.6751 | 11.3376 | 12.6751 | 11.6751 | 17.0127 | 19.0127 | 11.3376 | 23.0127 | 40.0254 | 59.0381 | 10.6751 | 11.3376 | 12.6751 | 11.6851 | 17.0127 | 19.0127 | 11.3376 | 23.0227 | 40.0354 | 59.0481 | 0.01
1.6411 | 6.8205 | 3.6411 | 2.6411 | 3.4616 | 5.4616 | 6.8205 | 9.4616 | 12.9232 | 18.3849 | 1.6411 | 6.8205 | 3.6411 | 2.6511 | 3.4616 | 5.4616 | 6.8205 | 9.4716 | 12.9332 | 18.3949 | 0.01
5.3028 | 8.6514 | 7.3028 | 6.3028 | 8.9542 | 10.9542 | 8.6514 | 14.9542 | 23.9083 | 34.8625 | 5.3028 | 8.6514 | 7.3028 | 6.3128 | 8.9542 | 10.9542 | 8.6514 | 14.9642 | 23.9183 | 34.8725 | 0.01
8.489 | 10.2445 | 10.489 | 9.489 | 13.7334 | 15.7334 | 10.2445 | 19.7334 | 33.4669 | 49.2003 | 8.489 | 10.2445 | 10.489 | 9.499 | 13.7334 | 15.7334 | 10.2445 | 19.7434 | 33.4769 | 49.2103 | 0.01
6.2238 | 9.1119 | 8.2238 | 7.2238 | 10.3356 | 12.3356 | 9.1119 | 16.3356 | 26.6713 | 39.0069 | 6.2238 | 9.1119 | 8.2238 | 7.2338 | 10.3356 | 12.3356 | 9.1119 | 16.3456 | 26.6813 | 39.0169 | 0.01
5.7985 | 8.8993 | 7.7985 | 6.7985 | 9.6978 | 11.6978 | 8.8993 | 15.6978 | 25.3956 | 37.0935 | 5.7985 | 8.8993 | 7.7985 | 6.8085 | 9.6978 | 11.6978 | 8.8993 | 15.7078 | 25.4056 | 37.1035 | 0.01
7.9791 | 9.9895 | 9.9791 | 8.9791 | 12.9686 | 14.9686 | 9.9895 | 18.9686 | 31.9373 | 46.9059 | 7.9791 | 9.9895 | 9.9791 | 8.9891 | 12.9686 | 14.9686 | 9.9895 | 18.9786 | 31.9473 | 46.9159 | 0.01
6.6718 | 9.3359 | 8.6718 | 7.6718 | 11.0076 | 13.0076 | 9.3359 | 17.0076 | 28.0153 | 41.0229 | 6.6718 | 9.3359 | 8.6718 | 7.6818 | 11.0076 | 13.0076 | 9.3359 | 17.0176 | 28.0253 | 41.0329 | 0.01
2.7548 | 7.3774 | 4.7548 | 3.7548 | 5.1322 | 7.1322 | 7.3774 | 11.1322 | 16.2645 | 23.3967 | 2.7548 | 7.3774 | 4.7548 | 3.7648 | 5.1322 | 7.1322 | 7.3774 | 11.1422 | 16.2745 | 23.4067 | 0.01
3.7539 | 7.877 | 5.7539 | 4.7539 | 6.6309 | 8.6309 | 7.877 | 12.6309 | 19.2618 | 27.8927 | 3.7539 | 7.877 | 5.7539 | 4.7639 | 6.6309 | 8.6309 | 7.877 | 12.6409 | 19.2718 | 27.9027 | 0.01
4.0079 | 8.0039 | 6.0079 | 5.0079 | 7.0118 | 9.0118 | 8.0039 | 13.0118 | 20.0237 | 29.0355 | 4.0079 | 8.0039 | 6.0079 | 5.0179 | 7.0118 | 9.0118 | 8.0039 | 13.0218 | 20.0337 | 29.0455 | 0.01
8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 8.8231 | 10.4115 | 10.8231 | 9.8331 | 14.2346 | 16.2346 | 10.4115 | 20.2446 | 34.4792 | 50.7139 | 0.01
6.8933 | 9.4467 | 8.8933 | 7.8933 | 11.34 | 13.34 | 9.4467 | 17.34 | 28.68 | 42.0201 | 6.8933 | 9.4467 | 8.8933 | 7.9033 | 11.34 | 13.34 | 9.4467 | 17.35 | 28.69 | 42.0301 | 0.01
3.0902 | 7.5451 | 5.0902 | 4.0902 | 5.6353 | 7.6353 | 7.5451 | 11.6353 | 17.2706 | 24.9059 | 3.0902 | 7.5451 | 5.0902 | 4.1002 | 5.6353 | 7.6353 | 7.5451 | 11.6453 | 17.2806 | 24.9159 | 0.01
3.6821 | 7.841 | 5.6821 | 4.6821 | 6.5231 | 8.5231 | 7.841 | 12.5231 | 19.0462 | 27.5692 | 3.6821 | 7.841 | 5.6821 | 4.6921 | 6.5231 | 8.5231 | 7.841 | 12.5331 | 19.0562 | 27.5792 | 0.01
3.021 | 7.5105 | 5.021 | 4.021 | 5.5315 | 7.5315 | 7.5105 | 11.5315 | 17.063 | 24.5945 | 3.021 | 7.5105 | 5.021 | 4.031 | 5.5315 | 7.5315 | 7.5105 | 11.5415 | 17.073 | 24.6045 | 0.01
8.4728 | 10.2364 | 10.4728 | 9.4728 | 13.7092 | 15.7092 | 10.2364 | 19.7092 | 33.4183 | 49.1275 | 8.4728 | 10.2364 | 10.4728 | 9.4828 | 13.7092 | 15.7092 | 10.2364 | 19.7192 | 33.4283 | 49.1375 | 0.01
3.493 | 7.7465 | 5.493 | 4.493 | 6.2395 | 8.2395 | 7.7465 | 12.2395 | 18.4791 | 26.7186 | 3.493 | 7.7465 | 5.493 | 4.503 | 6.2395 | 8.2395 | 7.7465 | 12.2495 | 18.4891 | 26.7286 | 0.01
9.0142 | 10.5071 | 11.0142 | 10.0142 | 14.5214 | 16.5214 | 10.5071 | 20.5214 | 35.0427 | 51.5641 | 9.0142 | 10.5071 | 11.0142 | 10.0242 | 14.5214 | 16.5214 | 10.5071 | 20.5314 | 35.0527 | 51.5741 | 0.01
10.0246 | 11.0123 | 12.0246 | 11.0246 | 16.0368 | 18.0368 | 11.0123 | 22.0368 | 38.0737 | 56.1105 | 10.0246 | 11.0123 | 12.0246 | 11.0346 | 16.0368 | 18.0368 | 11.0123 | 22.0468 | 38.0837 | 56.1205 | 0.01
9.1517 | 10.5759 | 11.1517 | 10.1517 | 14.7276 | 16.7276 | 10.5759 | 20.7276 | 35.4552 | 52.1829 | 9.1517 | 10.5759 | 11.1517 | 10.1617 | 14.7276 | 16.7276 | 10.5759 | 20.7376 | 35.4652 | 52.1929 | 0.01
4.2742 | 8.1371 | 6.2742 | 5.2742 | 7.4113 | 9.4113 | 8.1371 | 13.4113 | 20.8226 | 30.2339 | 4.2742 | 8.1371 | 6.2742 | 5.2842 | 7.4113 | 9.4113 | 8.1371 | 13.4213 | 20.8326 | 30.2439 | 0.01
4.3436 | 8.1718 | 6.3436 | 5.3436 | 7.5153 | 9.5153 | 8.1718 | 13.5153 | 21.0307 | 30.546 | 4.3436 | 8.1718 | 6.3436 | 5.3536 | 7.5153 | 9.5153 | 8.1718 | 13.5253 | 21.0407 | 30.556 | 0.01
7.5365 | 9.7683 | 9.5365 | 8.5365 | 12.3048 | 14.3048 | 9.7683 | 18.3048 | 30.6095 | 44.9143 | 7.5365 | 9.7683 | 9.5365 | 8.5465 | 12.3048 | 14.3048 | 9.7683 | 18.3148 | 30.6195 | 44.9243 | 0.01
2.6661 | 7.333 | 4.6661 | 3.6661 | 4.9991 | 6.9991 | 7.333 | 10.9991 | 15.9983 | 22.9974 | 2.6661 | 7.333 | 4.6661 | 3.6761 | 4.9991 | 6.9991 | 7.333 | 11.0091 | 16.0083 | 23.0074 | 0.01
5.1754 | 8.5877 | 7.1754 | 6.1754 | 8.7632 | 10.7632 | 8.5877 | 14.7632 | 23.5263 | 34.2895 | 5.1754 | 8.5877 | 7.1754 | 6.1854 | 8.7632 | 10.7632 | 8.5877 | 14.7732 | 23.5363 | 34.2995 | 0.01
5.602 | 8.801 | 7.602 | 6.602 | 9.4029 | 11.4029 | 8.801 | 15.4029 | 24.8059 | 36.2088 | 5.602 | 8.801 | 7.602 | 6.612 | 9.4029 | 11.4029 | 8.801 | 15.4129 | 24.8159 | 36.2188 | 0.01
2.4497 | 7.2248 | 4.4497 | 3.4497 | 4.6745 | 6.6745 | 7.2248 | 10.6745 | 15.349 | 22.0234 | 2.4497 | 7.2248 | 4.4497 | 3.4597 | 4.6745 | 6.6745 | 7.2248 | 10.6845 | 15.359 | 22.0334 | 0.01
8.632 | 10.316 | 10.632 | 9.632 | 13.948 | 15.948 | 10.316 | 19.948 | 33.8959 | 49.8439 | 8.632 | 10.316 | 10.632 | 9.642 | 13.948 | 15.948 | 10.316 | 19.958 | 33.9059 | 49.8539 | 0.01
7.3605 | 9.6802 | 9.3605 | 8.3605 | 12.0407 | 14.0407 | 9.6802 | 18.0407 | 30.0814 | 44.1221 | 7.3605 | 9.6802 | 9.3605 | 8.3705 | 12.0407 | 14.0407 | 9.6802 | 18.0507 | 30.0914 | 44.1321 | 0.01
6.2503 | 9.1251 | 8.2503 | 7.2503 | 10.3754 | 12.3754 | 9.1251 | 16.3754 | 26.7508 | 39.1262 | 6.2503 | 9.1251 | 8.2503 | 7.2603 | 10.3754 | 12.3754 | 9.1251 | 16.3854 | 26.7608 | 39.1362 | 0.01
6.4729 | 9.2365 | 8.4729 | 7.4729 | 10.7094 | 12.7094 | 9.2365 | 16.7094 | 27.4188 | 40.1282 | 6.4729 | 9.2365 | 8.4729 | 7.4829 | 10.7094 | 12.7094 | 9.2365 | 16.7194 | 27.4288 | 40.1382 | 0.01
5.0375 | 8.5187 | 7.0375 | 6.0375 | 8.5562 | 10.5562 | 8.5187 | 14.5562 | 23.1124 | 33.6686 | 5.0375 | 8.5187 | 7.0375 | 6.0475 | 8.5562 | 10.5562 | 8.5187 | 14.5662 | 23.1224 | 33.6786 | 0.01
6.4828 | 9.2414 | 8.4828 | 7.4828 | 10.7243 | 12.7243 | 9.2414 | 16.7243 | 27.4485 | 40.1728 | 6.4828 | 9.2414 | 8.4828 | 7.4928 | 10.7243 | 12.7243 | 9.2414 | 16.7343 | 27.4585 | 40.1828 | 0.01
8.6636 | 10.3318 | 10.6636 | 9.6636 | 13.9954 | 15.9954 | 10.3318 | 19.9954 | 33.9908 | 49.9862 | 8.6636 | 10.3318 | 10.6636 | 9.6736 | 13.9954 | 15.9954 | 10.3318 | 20.0054 | 34.0008 | 49.9962 | 0.01
6.1928 | 9.0964 | 8.1928 | 7.1928 | 10.2893 | 12.2893 | 9.0964 | 16.2893 | 26.5785 | 38.8678 | 6.1928 | 9.0964 | 8.1928 | 7.2028 | 10.2893 | 12.2893 | 9.0964 | 16.2993 | 26.5885 | 38.8778 | 0.01
5.2215 | 8.6108 | 7.2215 | 6.2215 | 8.8323 | 10.8323 | 8.6108 | 14.8323 | 23.6646 | 34.4969 | 5.2215 | 8.6108 | 7.2215 | 6.2315 | 8.8323 | 10.8323 | 8.6108 | 14.8423 | 23.6746 | 34.5069 | 0.01
3.3861 | 7.693 | 5.3861 | 4.3861 | 6.0791 | 8.0791 | 7.693 | 12.0791 | 18.1583 | 26.2374 | 3.3861 | 7.693 | 5.3861 | 4.3961 | 6.0791 | 8.0791 | 7.693 | 12.0891 | 18.1683 | 26.2474 | 0.01
10.7513 | 11.3757 | 12.7513 | 11.7513 | 17.127 | 19.127 | 11.3757 | 23.127 | 40.2539 | 59.3809 | 10.7513 | 11.3757 | 12.7513 | 11.7613 | 17.127 | 19.127 | 11.3757 | 23.137 | 40.2639 | 59.3909 | 0.01
5.4192 | 8.7096 | 7.4192 | 6.4192 | 9.1288 | 11.1288 | 8.7096 | 15.1288 | 24.2576 | 35.3864 | 5.4192 | 8.7096 | 7.4192 | 6.4292 | 9.1288 | 11.1288 | 8.7096 | 15.1388 | 24.2676 | 35.3964 | 0.01
10.2533 | 11.1267 | 12.2533 | 11.2533 | 16.38 | 18.38 | 11.1267 | 22.38 | 38.7599 | 57.1399 | 10.2533 | 11.1267 | 12.2533 | 11.2633 | 16.38 | 18.38 | 11.1267 | 22.39 | 38.7699 | 57.1499 | 0.01
4.7906 | 8.3953 | 6.7906 | 5.7906 | 8.1858 | 10.1858 | 8.3953 | 14.1858 | 22.3717 | 32.5575 | 4.7906 | 8.3953 | 6.7906 | 5.8006 | 8.1858 | 10.1858 | 8.3953 | 14.1958 | 22.3817 | 32.5675 | 0.01
5.4023 | 8.7011 | 7.4023 | 6.4023 | 9.1034 | 11.1034 | 8.7011 | 15.1034 | 24.2068 | 35.3102 | 5.4023 | 8.7011 | 7.4023 | 6.4123 | 9.1034 | 11.1034 | 8.7011 | 15.1134 | 24.2168 | 35.3202 | 0.01
9.2231 | 10.6116 | 11.2231 | 10.2231 | 14.8347 | 16.8347 | 10.6116 | 20.8347 | 35.6693 | 52.504 | 9.2231 | 10.6116 | 11.2231 | 10.2331 | 14.8347 | 16.8347 | 10.6116 | 20.8447 | 35.6793 | 52.514 | 0.01
6.4629 | 9.2314 | 8.4629 | 7.4629 | 10.6943 | 12.6943 | 9.2314 | 16.6943 | 27.3886 | 40.0829 | 6.4629 | 9.2314 | 8.4629 | 7.4729 | 10.6943 | 12.6943 | 9.2314 | 16.7043 | 27.3986 | 40.0929 | 0.01
3.3717 | 7.6858 | 5.3717 | 4.3717 | 6.0575 | 8.0575 | 7.6858 | 12.0575 | 18.115 | 26.1724 | 3.3717 | 7.6858 | 5.3717 | 4.3817 | 6.0575 | 8.0575 | 7.6858 | 12.0675 | 18.125 | 26.1824 | 0.01
5.6239 | 8.812 | 7.6239 | 6.6239 | 9.4359 | 11.4359 | 8.812 | 15.4359 | 24.8718 | 36.3078 | 5.6239 | 8.812 | 7.6239 | 6.6339 | 9.4359 | 11.4359 | 8.812 | 15.4459 | 24.8818 | 36.3178 | 0.01
9.3247 | 10.6624 | 11.3247 | 10.3247 | 14.9871 | 16.9871 | 10.6624 | 20.9871 | 35.9742 | 52.9613 | 9.3247 | 10.6624 | 11.3247 | 10.3347 | 14.9871 | 16.9871 | 10.6624 | 20.9971 | 35.9842 | 52.9713 | 0.01
4.3088 | 8.1544 | 6.3088 | 5.3088 | 7.4632 | 9.4632 | 8.1544 | 13.4632 | 20.9264 | 30.3896 | 4.3088 | 8.1544 | 6.3088 | 5.3188 | 7.4632 | 9.4632 | 8.1544 | 13.4732 | 20.9364 | 30.3996 | 0.01
5.0985 | 8.5493 | 7.0985 | 6.0985 | 8.6478 | 10.6478 | 8.5493 | 14.6478 | 23.2956 | 33.9434 | 5.0985 | 8.5493 | 7.0985 | 6.1085 | 8.6478 | 10.6478 | 8.5493 | 14.6578 | 23.3056 | 33.9534 | 0.01
7.6629 | 9.8315 | 9.6629 | 8.6629 | 12.4944 | 14.4944 | 9.8315 | 18.4944 | 30.9888 | 45.4832 | 7.6629 | 9.8315 | 9.6629 | 8.6729 | 12.4944 | 14.4944 | 9.8315 | 18.5044 | 30.9988 | 45.4932 | 0.01
9.3024 | 10.6512 | 11.3024 | 10.3024 | 14.9536 | 16.9536 | 10.6512 | 20.9536 | 35.9072 | 52.8609 | 9.3024 | 10.6512 | 11.3024 | 10.3124 | 14.9536 | 16.9536 | 10.6512 | 20.9636 | 35.9172 | 52.8709 | 0.01
8.7686 | 10.3843 | 10.7686 | 9.7686 | 14.1529 | 16.1529 | 10.3843 | 20.1529 | 34.3058 | 50.4587 | 8.7686 | 10.3843 | 10.7686 | 9.7786 | 14.1529 | 16.1529 | 10.3843 | 20.1629 | 34.3158 | 50.4687 | 0.01
8.1501 | 10.075 | 10.1501 | 9.1501 | 13.2251 | 15.2251 | 10.075 | 19.2251 | 32.4502 | 47.6753 | 8.1501 | 10.075 | 10.1501 | 9.1601 | 13.2251 | 15.2251 | 10.075 | 19.2351 | 32.4602 | 47.6853 | 0.01
6.7669 | 9.3835 | 8.7669 | 7.7669 | 11.1504 | 13.1504 | 9.3835 | 17.1504 | 28.3008 | 41.4512 | 6.7669 | 9.3835 | 8.7669 | 7.7769 | 11.1504 | 13.1504 | 9.3835 | 17.1604 | 28.3108 | 41.4612 | 0.01
6.0705 | 9.0352 | 8.0705 | 7.0705 | 10.1057 | 12.1057 | 9.0352 | 16.1057 | 26.2114 | 38.3171 | 6.0705 | 9.0352 | 8.0705 | 7.0805 | 10.1057 | 12.1057 | 9.0352 | 16.1157 | 26.2214 | 38.3271 | 0.01
5.7724 | 8.8862 | 7.7724 | 6.7724 | 9.6586 | 11.6586 | 8.8862 | 15.6586 | 25.3172 | 36.9757 | 5.7724 | 8.8862 | 7.7724 | 6.7824 | 9.6586 | 11.6586 | 8.8862 | 15.6686 | 25.3272 | 36.9857 | 0.01
7.6638 | 9.8319 | 9.6638 | 8.6638 | 12.4957 | 14.4957 | 9.8319 | 18.4957 | 30.9914 | 45.487 | 7.6638 | 9.8319 | 9.6638 | 8.6738 | 12.4957 | 14.4957 | 9.8319 | 18.5057 | 31.0014 | 45.497 | 0.01
5.8442 | 8.9221 | 7.8442 | 6.8442 | 9.7663 | 11.7663 | 8.9221 | 15.7663 | 25.5325 | 37.2988 | 5.8442 | 8.9221 | 7.8442 | 6.8542 | 9.7663 | 11.7663 | 8.9221 | 15.7763 | 25.5425 | 37.3088 | 0.01
4.8173 | 8.4086 | 6.8173 | 5.8173 | 8.2259 | 10.2259 | 8.4086 | 14.2259 | 22.4518 | 32.6777 | 4.8173 | 8.4086 | 6.8173 | 5.8273 | 8.2259 | 10.2259 | 8.4086 | 14.2359 | 22.4618 | 32.6877 | 0.01
3.6353 | 7.8177 | 5.6353 | 4.6353 | 6.453 | 8.453 | 7.8177 | 12.453 | 18.9059 | 27.3589 | 3.6353 | 7.8177 | 5.6353 | 4.6453 | 6.453 | 8.453 | 7.8177 | 12.463 | 18.9159 | 27.3689 | 0.01
3.3053 | 7.6526 | 5.3053 | 4.3053 | 5.9579 | 7.9579 | 7.6526 | 11.9579 | 17.9158 | 25.8737 | 3.3053 | 7.6526 | 5.3053 | 4.3153 | 5.9579 | 7.9579 | 7.6526 | 11.9679 | 17.9258 | 25.8837 | 0.01
5.0443 | 8.5222 | 7.0443 | 6.0443 | 8.5665 | 10.5665 | 8.5222 | 14.5665 | 23.133 | 33.6995 | 5.0443 | 8.5222 | 7.0443 | 6.0543 | 8.5665 | 10.5665 | 8.5222 | 14.5765 | 23.143 | 33.7095 | 0.01
8.0763 | 10.0381 | 10.0763 | 9.0763 | 13.1144 | 15.1144 | 10.0381 | 19.1144 | 32.2289 | 47.3433 | 8.0763 | 10.0381 | 10.0763 | 9.0863 | 13.1144 | 15.1144 | 10.0381 | 19.1244 | 32.2389 | 47.3533 | 0.01
4.3336 | 8.1668 | 6.3336 | 5.3336 | 7.5004 | 9.5004 | 8.1668 | 13.5004 | 21.0008 | 30.5013 | 4.3336 | 8.1668 | 6.3336 | 5.3436 | 7.5004 | 9.5004 | 8.1668 | 13.5104 | 21.0108 | 30.5113 | 0.01
9.9359 | 10.9679 | 11.9359 | 10.9359 | 15.9038 | 17.9038 | 10.9679 | 21.9038 | 37.8077 | 55.7115 | 9.9359 | 10.9679 | 11.9359 | 10.9459 | 15.9038 | 17.9038 | 10.9679 | 21.9138 | 37.8177 | 55.7215 | 0.01
6.4882 | 9.2441 | 8.4882 | 7.4882 | 10.7323 | 12.7323 | 9.2441 | 16.7323 | 27.4646 | 40.1969 | 6.4882 | 9.2441 | 8.4882 | 7.4982 | 10.7323 | 12.7323 | 9.2441 | 16.7423 | 27.4746 | 40.2069 | 0.01
3.7597 | 7.8798 | 5.7597 | 4.7597 | 6.6395 | 8.6395 | 7.8798 | 12.6395 | 19.279 | 27.9185 | 3.7597 | 7.8798 | 5.7597 | 4.7697 | 6.6395 | 8.6395 | 7.8798 | 12.6495 | 19.289 | 27.9285 | 0.01
4.1555 | 8.0777 | 6.1555 | 5.1555 | 7.2332 | 9.2332 | 8.0777 | 13.2332 | 20.4665 | 29.6997 | 4.1555 | 8.0777 | 6.1555 | 5.1655 | 7.2332 | 9.2332 | 8.0777 | 13.2432 | 20.4765 | 29.7097 | 0.01
2.6525 | 7.3263 | 4.6525 | 3.6525 | 4.9788 | 6.9788 | 7.3263 | 10.9788 | 15.9575 | 22.9363 | 2.6525 | 7.3263 | 4.6525 | 3.6625 | 4.9788 | 6.9788 | 7.3263 | 10.9888 | 15.9675 | 22.9463 | 0.01
1.8403 | 6.9201 | 3.8403 | 2.8403 | 3.7604 | 5.7604 | 6.9201 | 9.7604 | 13.5208 | 19.2812 | 1.8403 | 6.9201 | 3.8403 | 2.8503 | 3.7604 | 5.7604 | 6.9201 | 9.7704 | 13.5308 | 19.2912 | 0.01
2.6667 | 7.3334 | 4.6667 | 3.6667 | 5.0001 | 7.0001 | 7.3334 | 11.0001 | 16.0001 | 23.0002 | 2.6667 | 7.3334 | 4.6667 | 3.6767 | 5.0001 | 7.0001 | 7.3334 | 11.0101 | 16.0101 | 23.0102 | 0.01
6.4608 | 9.2304 | 8.4608 | 7.4608 | 10.6912 | 12.6912 | 9.2304 | 16.6912 | 27.3825 | 40.0737 | 6.4608 | 9.2304 | 8.4608 | 7.4708 | 10.6912 | 12.6912 | 9.2304 | 16.7012 | 27.3925 | 40.0837 | 0.01
4.1906 | 8.0953 | 6.1906 | 5.1906 | 7.2858 | 9.2858 | 8.0953 | 13.2858 | 20.5717 | 29.8575 | 4.1906 | 8.0953 | 6.1906 | 5.2006 | 7.2858 | 9.2858 | 8.0953 | 13.2958 | 20.5817 | 29.8675 | 0.01
8.6153 | 10.3077 | 10.6153 | 9.6153 | 13.923 | 15.923 | 10.3077 | 19.923 | 33.846 | 49.769 | 8.6153 | 10.3077 | 10.6153 | 9.6253 | 13.923 | 15.923 | 10.3077 | 19.933 | 33.856 | 49.779 | 0.01
4.7385 | 8.3693 | 6.7385 | 5.7385 | 8.1078 | 10.1078 | 8.3693 | 14.1078 | 22.2156 | 32.3234 | 4.7385 | 8.3693 | 6.7385 | 5.7485 | 8.1078 | 10.1078 | 8.3693 | 14.1178 | 22.2256 | 32.3334 | 0.01
2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 2.9838 | 7.4919 | 4.9838 | 3.9938 | 5.4758 | 7.4758 | 7.4919 | 11.4858 | 16.9615 | 24.4373 | 0.01
3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 3.9727 | 7.9863 | 5.9727 | 4.9827 | 6.959 | 8.959 | 7.9863 | 12.969 | 19.928 | 28.8869 | 0.01
5.9707 | 8.9854 | 7.9707 | 6.9707 | 9.9561 | 11.9561 | 8.9854 | 15.9561 | 25.9121 | 37.8682 | 5.9707 | 8.9854 | 7.9707 | 6.9807 | 9.9561 | 11.9561 | 8.9854 | 15.9661 | 25.9221 | 37.8782 | 0.01
8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 8.3644 | 10.1822 | 10.3644 | 9.3744 | 13.5466 | 15.5466 | 10.1822 | 19.5566 | 33.1032 | 48.6497 | 0.01
5.1237 | 8.5618 | 7.1237 | 6.1237 | 8.6855 | 10.6855 | 8.5618 | 14.6855 | 23.3711 | 34.0566 | 5.1237 | 8.5618 | 7.1237 | 6.1337 | 8.6855 | 10.6855 | 8.5618 | 14.6955 | 23.3811 | 34.0666 | 0.01
4.2034 | 8.1017 | 6.2034 | 5.2034 | 7.3051 | 9.3051 | 8.1017 | 13.3051 | 20.6102 | 29.9154 | 4.2034 | 8.1017 | 6.2034 | 5.2134 | 7.3051 | 9.3051 | 8.1017 | 13.3151 | 20.6202 | 29.9254 | 0.01
5.5663 | 8.7832 | 7.5663 | 6.5663 | 9.3495 | 11.3495 | 8.7832 | 15.3495 | 24.699 | 36.0484 | 5.5663 | 8.7832 | 7.5663 | 6.5763 | 9.3495 | 11.3495 | 8.7832 | 15.3595 | 24.709 | 36.0584 | 0.01
6.8431 | 9.4215 | 8.8431 | 7.8431 | 11.2646 | 13.2646 | 9.4215 | 17.2646 | 28.5292 | 41.7939 | 6.8431 | 9.4215 | 8.8431 | 7.8531 | 11.2646 | 13.2646 | 9.4215 | 17.2746 | 28.5392 | 41.8039 | 0.01
6.8551 | 9.4276 | 8.8551 | 7.8551 | 11.2827 | 13.2827 | 9.4276 | 17.2827 | 28.5654 | 41.8481 | 6.8551 | 9.4276 | 8.8551 | 7.8651 | 11.2827 | 13.2827 | 9.4276 | 17.2927 | 28.5754 | 41.8581 | 0.01
4.4435 | 8.2217 | 6.4435 | 5.4435 | 7.6652 | 9.6652 | 8.2217 | 13.6652 | 21.3304 | 30.9956 | 4.4435 | 8.2217 | 6.4435 | 5.4535 | 7.6652 | 9.6652 | 8.2217 | 13.6752 | 21.3404 | 31.0056 | 0.01
9.454 | 10.727 | 11.454 | 10.454 | 15.181 | 17.181 | 10.727 | 21.181 | 36.3619 | 53.5429 | 9.454 | 10.727 | 11.454 | 10.464 | 15.181 | 17.181 | 10.727 | 21.191 | 36.3719 | 53.5529 | 0.01
7.8182 | 9.9091 | 9.8182 | 8.8182 | 12.7273 | 14.7273 | 9.9091 | 18.7273 | 31.4547 | 46.182 | 7.8182 | 9.9091 | 9.8182 | 8.8282 | 12.7273 | 14.7273 | 9.9091 | 18.7373 | 31.4647 | 46.192 | 0.01
6.9341 | 9.4671 | 8.9341 | 7.9341 | 11.4012 | 13.4012 | 9.4671 | 17.4012 | 28.8023 | 42.2035 | 6.9341 | 9.4671 | 8.9341 | 7.9441 | 11.4012 | 13.4012 | 9.4671 | 17.4112 | 28.8123 | 42.2135 | 0.01
4.4815 | 8.2408 | 6.4815 | 5.4815 | 7.7223 | 9.7223 | 8.2408 | 13.7223 | 21.4445 | 31.1668 | 4.4815 | 8.2408 | 6.4815 | 5.4915 | 7.7223 | 9.7223 | 8.2408 | 13.7323 | 21.4545 | 31.1768 | 0.01
5.1586 | 8.5793 | 7.1586 | 6.1586 | 8.7379 | 10.7379 | 8.5793 | 14.7379 | 23.4758 | 34.2137 | 5.1586 | 8.5793 | 7.1586 | 6.1686 | 8.7379 | 10.7379 | 8.5793 | 14.7479 | 23.4858 | 34.2237 | 0.01
8.2539 | 10.1269 | 10.2539 | 9.2539 | 13.3808 | 15.3808 | 10.1269 | 19.3808 | 32.7616 | 48.1423 | 8.2539 | 10.1269 | 10.2539 | 9.2639 | 13.3808 | 15.3808 | 10.1269 | 19.3908 | 32.7716 | 48.1523 | 0.01
7.8806 | 9.9403 | 9.8806 | 8.8806 | 12.8209 | 14.8209 | 9.9403 | 18.8209 | 31.6419 | 46.4628 | 7.8806 | 9.9403 | 9.8806 | 8.8906 | 12.8209 | 14.8209 | 9.9403 | 18.8309 | 31.6519 | 46.4728 | 0.01
4.776 | 8.388 | 6.776 | 5.776 | 8.164 | 10.164 | 8.388 | 14.164 | 22.3281 | 32.4921 | 4.776 | 8.388 | 6.776 | 5.786 | 8.164 | 10.164 | 8.388 | 14.174 | 22.3381 | 32.5021 | 0.01
6.3025 | 9.1512 | 8.3025 | 7.3025 | 10.4537 | 12.4537 | 9.1512 | 16.4537 | 26.9074 | 39.3611 | 6.3025 | 9.1512 | 8.3025 | 7.3125 | 10.4537 | 12.4537 | 9.1512 | 16.4637 | 26.9174 | 39.3711 | 0.01
6.7528 | 9.3764 | 8.7528 | 7.7528 | 11.1292 | 13.1292 | 9.3764 | 17.1292 | 28.2584 | 41.3875 | 6.7528 | 9.3764 | 8.7528 | 7.7628 | 11.1292 | 13.1292 | 9.3764 | 17.1392 | 28.2684 | 41.3975 | 0.01
6.2989 | 9.1495 | 8.2989 | 7.2989 | 10.4484 | 12.4484 | 9.1495 | 16.4484 | 26.8968 | 39.3451 | 6.2989 | 9.1495 | 8.2989 | 7.3089 | 10.4484 | 12.4484 | 9.1495 | 16.4584 | 26.9068 | 39.3551 | 0.01
6.9488 | 9.4744 | 8.9488 | 7.9488 | 11.4232 | 13.4232 | 9.4744 | 17.4232 | 28.8464 | 42.2696 | 6.9488 | 9.4744 | 8.9488 | 7.9588 | 11.4232 | 13.4232 | 9.4744 | 17.4332 | 28.8564 | 42.2796 | 0.01
3.3735 | 7.6867 | 5.3735 | 4.3735 | 6.0602 | 8.0602 | 7.6867 | 12.0602 | 18.1204 | 26.1806 | 3.3735 | 7.6867 | 5.3735 | 4.3835 | 6.0602 | 8.0602 | 7.6867 | 12.0702 | 18.1304 | 26.1906 | 0.01
8.8156 | 10.4078 | 10.8156 | 9.8156 | 14.2235 | 16.2235 | 10.4078 | 20.2235 | 34.4469 | 50.6704 | 8.8156 | 10.4078 | 10.8156 | 9.8256 | 14.2235 | 16.2235 | 10.4078 | 20.2335 | 34.4569 | 50.6804 | 0.01
6.1938 | 9.0969 | 8.1938 | 7.1938 | 10.2907 | 12.2907 | 9.0969 | 16.2907 | 26.5813 | 38.872 | 6.1938 | 9.0969 | 8.1938 | 7.2038 | 10.2907 | 12.2907 | 9.0969 | 16.3007 | 26.5913 | 38.882 | 0.01
2.6892 | 7.3446 | 4.6892 | 3.6892 | 5.0338 | 7.0338 | 7.3446 | 11.0338 | 16.0676 | 23.1013 | 2.6892 | 7.3446 | 4.6892 | 3.6992 | 5.0338 | 7.0338 | 7.3446 | 11.0438 | 16.0776 | 23.1113 | 0.01
9.693 | 10.8465 | 11.693 | 10.693 | 15.5395 | 17.5395 | 10.8465 | 21.5395 | 37.0789 | 54.6184 | 9.693 | 10.8465 | 11.693 | 10.703 | 15.5395 | 17.5395 | 10.8465 | 21.5495 | 37.0889 | 54.6284 | 0.01
7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 7.2212 | 9.6106 | 9.2212 | 8.2312 | 11.8318 | 13.8318 | 9.6106 | 17.8418 | 29.6736 | 43.5055 | 0.01
7.6207 | 9.8104 | 9.6207 | 8.6207 | 12.4311 | 14.4311 | 9.8104 | 18.4311 | 30.8621 | 45.2932 | 7.6207 | 9.8104 | 9.6207 | 8.6307 | 12.4311 | 14.4311 | 9.8104 | 18.4411 | 30.8721 | 45.3032 | 0.01
5.3109 | 8.6554 | 7.3109 | 6.3109 | 8.9663 | 10.9663 | 8.6554 | 14.9663 | 23.9327 | 34.899 | 5.3109 | 8.6554 | 7.3109 | 6.3209 | 8.9663 | 10.9663 | 8.6554 | 14.9763 | 23.9427 | 34.909 | 0.01
5.815 | 8.9075 | 7.815 | 6.815 | 9.7225 | 11.7225 | 8.9075 | 15.7225 | 25.445 | 37.1675 | 5.815 | 8.9075 | 7.815 | 6.825 | 9.7225 | 11.7225 | 8.9075 | 15.7325 | 25.455 | 37.1775 | 0.01
8.6974 | 10.3487 | 10.6974 | 9.6974 | 14.0461 | 16.0461 | 10.3487 | 20.0461 | 34.0922 | 50.1383 | 8.6974 | 10.3487 | 10.6974 | 9.7074 | 14.0461 | 16.0461 | 10.3487 | 20.0561 | 34.1022 | 50.1483 | 0.01
4.5436 | 8.2718 | 6.5436 | 5.5436 | 7.8155 | 9.8155 | 8.2718 | 13.8155 | 21.6309 | 31.4464 | 4.5436 | 8.2718 | 6.5436 | 5.5536 | 7.8155 | 9.8155 | 8.2718 | 13.8255 | 21.6409 | 31.4564 | 0.01
3.342 | 7.671 | 5.342 | 4.342 | 6.013 | 8.013 | 7.671 | 12.013 | 18.0259 | 26.0389 | 3.342 | 7.671 | 5.342 | 4.352 | 6.013 | 8.013 | 7.671 | 12.023 | 18.0359 | 26.0489 | 0.01
3.0612 | 7.5306 | 5.0612 | 4.0612 | 5.5918 | 7.5918 | 7.5306 | 11.5918 | 17.1837 | 24.7755 | 3.0612 | 7.5306 | 5.0612 | 4.0712 | 5.5918 | 7.5918 | 7.5306 | 11.6018 | 17.1937 | 24.7855 | 0.01
8.378 | 10.189 | 10.378 | 9.378 | 13.567 | 15.567 | 10.189 | 19.567 | 33.1339 | 48.7009 | 8.378 | 10.189 | 10.378 | 9.388 | 13.567 | 15.567 | 10.189 | 19.577 | 33.1439 | 48.7109 | 0.01
5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 5.7998 | 8.8999 | 7.7998 | 6.8098 | 9.6997 | 11.6997 | 8.8999 | 15.7097 | 25.4093 | 37.109 | 0.01
5.55 | 8.775 | 7.55 | 6.55 | 9.325 | 11.325 | 8.775 | 15.325 | 24.65 | 35.9751 | 5.55 | 8.775 | 7.55 | 6.56 | 9.325 | 11.325 | 8.775 | 15.335 | 24.66 | 35.9851 | 0.01
8.0143 | 10.0072 | 10.0143 | 9.0143 | 13.0215 | 15.0215 | 10.0072 | 19.0215 | 32.043 | 47.0645 | 8.0143 | 10.0072 | 10.0143 | 9.0243 | 13.0215 | 15.0215 | 10.0072 | 19.0315 | 32.053 | 47.0745 | 0.01
4.2615 | 8.1308 | 6.2615 | 5.2615 | 7.3923 | 9.3923 | 8.1308 | 13.3923 | 20.7846 | 30.1769 | 4.2615 | 8.1308 | 6.2615 | 5.2715 | 7.3923 | 9.3923 | 8.1308 | 13.4023 | 20.7946 | 30.1869 | 0.01
4.3816 | 8.1908 | 6.3816 | 5.3816 | 7.5724 | 9.5724 | 8.1908 | 13.5724 | 21.1449 | 30.7173 | 4.3816 | 8.1908 | 6.3816 | 5.3916 | 7.5724 | 9.5724 | 8.1908 | 13.5824 | 21.1549 | 30.7273 | 0.01
5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 5.7998 | 8.8999 | 7.7998 | 6.8098 | 9.6997 | 11.6997 | 8.8999 | 15.7097 | 25.4093 | 37.109 | 0.01
7.8028 | 9.9014 | 9.8028 | 8.8028 | 12.7042 | 14.7042 | 9.9014 | 18.7042 | 31.4083 | 46.1125 | 7.8028 | 9.9014 | 9.8028 | 8.8128 | 12.7042 | 14.7042 | 9.9014 | 18.7142 | 31.4183 | 46.1225 | 0.01
8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 8.3644 | 10.1822 | 10.3644 | 9.3744 | 13.5466 | 15.5466 | 10.1822 | 19.5566 | 33.1032 | 48.6497 | 0.01
5.5132 | 8.7566 | 7.5132 | 6.5132 | 9.2698 | 11.2698 | 8.7566 | 15.2698 | 24.5397 | 35.8095 | 5.5132 | 8.7566 | 7.5132 | 6.5232 | 9.2698 | 11.2698 | 8.7566 | 15.2798 | 24.5497 | 35.8195 | 0.01
7.8861 | 9.9431 | 9.8861 | 8.8861 | 12.8292 | 14.8292 | 9.9431 | 18.8292 | 31.6583 | 46.4875 | 7.8861 | 9.9431 | 9.8861 | 8.8961 | 12.8292 | 14.8292 | 9.9431 | 18.8392 | 31.6683 | 46.4975 | 0.01
6.7892 | 9.3946 | 8.7892 | 7.7892 | 11.1838 | 13.1838 | 9.3946 | 17.1838 | 28.3676 | 41.5514 | 6.7892 | 9.3946 | 8.7892 | 7.7992 | 11.1838 | 13.1838 | 9.3946 | 17.1938 | 28.3776 | 41.5614 | 0.01
4.1869 | 8.0934 | 6.1869 | 5.1869 | 7.2803 | 9.2803 | 8.0934 | 13.2803 | 20.5606 | 29.8409 | 4.1869 | 8.0934 | 6.1869 | 5.1969 | 7.2803 | 9.2803 | 8.0934 | 13.2903 | 20.5706 | 29.8509 | 0.01
4.1938 | 8.0969 | 6.1938 | 5.1938 | 7.2907 | 9.2907 | 8.0969 | 13.2907 | 20.5813 | 29.872 | 4.1938 | 8.0969 | 6.1938 | 5.2038 | 7.2907 | 9.2907 | 8.0969 | 13.3007 | 20.5913 | 29.882 | 0.01
3.2575 | 7.6287 | 5.2575 | 4.2575 | 5.8862 | 7.8862 | 7.6287 | 11.8862 | 17.7724 | 25.6586 | 3.2575 | 7.6287 | 5.2575 | 4.2675 | 5.8862 | 7.8862 | 7.6287 | 11.8962 | 17.7824 | 25.6686 | 0.01
4.0356 | 8.0178 | 6.0356 | 5.0356 | 7.0534 | 9.0534 | 8.0178 | 13.0534 | 20.1068 | 29.1602 | 4.0356 | 8.0178 | 6.0356 | 5.0456 | 7.0534 | 9.0534 | 8.0178 | 13.0634 | 20.1168 | 29.1702 | 0.01
6.4349 | 9.2175 | 8.4349 | 7.4349 | 10.6524 | 12.6524 | 9.2175 | 16.6524 | 27.3048 | 39.9572 | 6.4349 | 9.2175 | 8.4349 | 7.4449 | 10.6524 | 12.6524 | 9.2175 | 16.6624 | 27.3148 | 39.9672 | 0.01
7.869 | 9.9345 | 9.869 | 8.869 | 12.8035 | 14.8035 | 9.9345 | 18.8035 | 31.607 | 46.4105 | 7.869 | 9.9345 | 9.869 | 8.879 | 12.8035 | 14.8035 | 9.9345 | 18.8135 | 31.617 | 46.4205 | 0.01
6.7712 | 9.3856 | 8.7712 | 7.7712 | 11.1568 | 13.1568 | 9.3856 | 17.1568 | 28.3136 | 41.4704 | 6.7712 | 9.3856 | 8.7712 | 7.7812 | 11.1568 | 13.1568 | 9.3856 | 17.1668 | 28.3236 | 41.4804 | 0.01
8.0857 | 10.0429 | 10.0857 | 9.0857 | 13.1286 | 15.1286 | 10.0429 | 19.1286 | 32.2572 | 47.3859 | 8.0857 | 10.0429 | 10.0857 | 9.0957 | 13.1286 | 15.1286 | 10.0429 | 19.1386 | 32.2672 | 47.3959 | 0.01
7.7566 | 9.8783 | 9.7566 | 8.7566 | 12.6349 | 14.6349 | 9.8783 | 18.6349 | 31.2699 | 45.9048 | 7.7566 | 9.8783 | 9.7566 | 8.7666 | 12.6349 | 14.6349 | 9.8783 | 18.6449 | 31.2799 | 45.9148 | 0.01
9.6525 | 10.8263 | 11.6525 | 10.6525 | 15.4788 | 17.4788 | 10.8263 | 21.4788 | 36.9575 | 54.4363 | 9.6525 | 10.8263 | 11.6525 | 10.6625 | 15.4788 | 17.4788 | 10.8263 | 21.4888 | 36.9675 | 54.4463 | 0.01
7.2986 | 9.6493 | 9.2986 | 8.2986 | 11.948 | 13.948 | 9.6493 | 17.948 | 29.8959 | 43.8439 | 7.2986 | 9.6493 | 9.2986 | 8.3086 | 11.948 | 13.948 | 9.6493 | 17.958 | 29.9059 | 43.8539 | 0.01
4.0521 | 8.0261 | 6.0521 | 5.0521 | 7.0782 | 9.0782 | 8.0261 | 13.0782 | 20.1564 | 29.2346 | 4.0521 | 8.0261 | 6.0521 | 5.0621 | 7.0782 | 9.0782 | 8.0261 | 13.0882 | 20.1664 | 29.2446 | 0.01
7.0371 | 9.5185 | 9.0371 | 8.0371 | 11.5556 | 13.5556 | 9.5185 | 17.5556 | 29.1112 | 42.6668 | 7.0371 | 9.5185 | 9.0371 | 8.0471 | 11.5556 | 13.5556 | 9.5185 | 17.5656 | 29.1212 | 42.6768 | 0.01
2.233 | 7.1165 | 4.233 | 3.233 | 4.3495 | 6.3495 | 7.1165 | 10.3495 | 14.6991 | 21.0486 | 2.233 | 7.1165 | 4.233 | 3.243 | 4.3495 | 6.3495 | 7.1165 | 10.3595 | 14.7091 | 21.0586 | 0.01
7.2275 | 9.6137 | 9.2275 | 8.2275 | 11.8412 | 13.8412 | 9.6137 | 17.8412 | 29.6825 | 43.5237 | 7.2275 | 9.6137 | 9.2275 | 8.2375 | 11.8412 | 13.8412 | 9.6137 | 17.8512 | 29.6925 | 43.5337 | 0.01
6.3896 | 9.1948 | 8.3896 | 7.3896 | 10.5844 | 12.5844 | 9.1948 | 16.5844 | 27.1688 | 39.7532 | 6.3896 | 9.1948 | 8.3896 | 7.3996 | 10.5844 | 12.5844 | 9.1948 | 16.5944 | 27.1788 | 39.7632 | 0.01
6.4116 | 9.2058 | 8.4116 | 7.4116 | 10.6174 | 12.6174 | 9.2058 | 16.6174 | 27.2349 | 39.8523 | 6.4116 | 9.2058 | 8.4116 | 7.4216 | 10.6174 | 12.6174 | 9.2058 | 16.6274 | 27.2449 | 39.8623 | 0.01
4.7322 | 8.3661 | 6.7322 | 5.7322 | 8.0983 | 10.0983 | 8.3661 | 14.0983 | 22.1965 | 32.2948 | 4.7322 | 8.3661 | 6.7322 | 5.7422 | 8.0983 | 10.0983 | 8.3661 | 14.1083 | 22.2065 | 32.3048 | 0.01
6.7518 | 9.3759 | 8.7518 | 7.7518 | 11.1277 | 13.1277 | 9.3759 | 17.1277 | 28.2554 | 41.3831 | 6.7518 | 9.3759 | 8.7518 | 7.7618 | 11.1277 | 13.1277 | 9.3759 | 17.1377 | 28.2654 | 41.3931 | 0.01
4.1562 | 8.0781 | 6.1562 | 5.1562 | 7.2343 | 9.2343 | 8.0781 | 13.2343 | 20.4686 | 29.7029 | 4.1562 | 8.0781 | 6.1562 | 5.1662 | 7.2343 | 9.2343 | 8.0781 | 13.2443 | 20.4786 | 29.7129 | 0.01
3.8186 | 7.9093 | 5.8186 | 4.8186 | 6.7279 | 8.7279 | 7.9093 | 12.7279 | 19.4557 | 28.1836 | 3.8186 | 7.9093 | 5.8186 | 4.8286 | 6.7279 | 8.7279 | 7.9093 | 12.7379 | 19.4657 | 28.1936 | 0.01
4.9033 | 8.4517 | 6.9033 | 5.9033 | 8.355 | 10.355 | 8.4517 | 14.355 | 22.7099 | 33.0649 | 4.9033 | 8.4517 | 6.9033 | 5.9133 | 8.355 | 10.355 | 8.4517 | 14.365 | 22.7199 | 33.0749 | 0.01
3.8613 | 7.9307 | 5.8613 | 4.8613 | 6.792 | 8.792 | 7.9307 | 12.792 | 19.584 | 28.376 | 3.8613 | 7.9307 | 5.8613 | 4.8713 | 6.792 | 8.792 | 7.9307 | 12.802 | 19.594 | 28.386 | 0.01
8.8507 | 10.4253 | 10.8507 | 9.8507 | 14.276 | 16.276 | 10.4253 | 20.276 | 34.5521 | 50.8281 | 8.8507 | 10.4253 | 10.8507 | 9.8607 | 14.276 | 16.276 | 10.4253 | 20.286 | 34.5621 | 50.8381 | 0.01
4.7771 | 8.3886 | 6.7771 | 5.7771 | 8.1657 | 10.1657 | 8.3886 | 14.1657 | 22.3314 | 32.4971 | 4.7771 | 8.3886 | 6.7771 | 5.7871 | 8.1657 | 10.1657 | 8.3886 | 14.1757 | 22.3414 | 32.5071 | 0.01
6.5063 | 9.2532 | 8.5063 | 7.5063 | 10.7595 | 12.7595 | 9.2532 | 16.7595 | 27.519 | 40.2786 | 6.5063 | 9.2532 | 8.5063 | 7.5163 | 10.7595 | 12.7595 | 9.2532 | 16.7695 | 27.529 | 40.2886 | 0.01
6.9271 | 9.4636 | 8.9271 | 7.9271 | 11.3907 | 13.3907 | 9.4636 | 17.3907 | 28.7813 | 42.172 | 6.9271 | 9.4636 | 8.9271 | 7.9371 | 11.3907 | 13.3907 | 9.4636 | 17.4007 | 28.7913 | 42.182 | 0.01
4.2626 | 8.1313 | 6.2626 | 5.2626 | 7.394 | 9.394 | 8.1313 | 13.394 | 20.7879 | 30.1819 | 4.2626 | 8.1313 | 6.2626 | 5.2726 | 7.394 | 9.394 | 8.1313 | 13.404 | 20.7979 | 30.1919 | 0.01
2.6952 | 7.3476 | 4.6952 | 3.6952 | 5.0428 | 7.0428 | 7.3476 | 11.0428 | 16.0856 | 23.1284 | 2.6952 | 7.3476 | 4.6952 | 3.7052 | 5.0428 | 7.0428 | 7.3476 | 11.0528 | 16.0956 | 23.1384 | 0.01
7.9818 | 9.9909 | 9.9818 | 8.9818 | 12.9728 | 14.9728 | 9.9909 | 18.9728 | 31.9455 | 46.9183 | 7.9818 | 9.9909 | 9.9818 | 8.9918 | 12.9728 | 14.9728 | 9.9909 | 18.9828 | 31.9555 | 46.9283 | 0.01
4.4602 | 8.2301 | 6.4602 | 5.4602 | 7.6903 | 9.6903 | 8.2301 | 13.6903 | 21.3806 | 31.0709 | 4.4602 | 8.2301 | 6.4602 | 5.4702 | 7.6903 | 9.6903 | 8.2301 | 13.7003 | 21.3906 | 31.0809 | 0.01
7.8904 | 9.9452 | 9.8904 | 8.8904 | 12.8356 | 14.8356 | 9.9452 | 18.8356 | 31.6712 | 46.5069 | 7.8904 | 9.9452 | 9.8904 | 8.9004 | 12.8356 | 14.8356 | 9.9452 | 18.8456 | 31.6812 | 46.5169 | 0.01
4.5586 | 8.2793 | 6.5586 | 5.5586 | 7.8379 | 9.8379 | 8.2793 | 13.8379 | 21.6757 | 31.5136 | 4.5586 | 8.2793 | 6.5586 | 5.5686 | 7.8379 | 9.8379 | 8.2793 | 13.8479 | 21.6857 | 31.5236 | 0.01
5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 5.3559 | 8.6779 | 7.3559 | 6.3659 | 9.0338 | 11.0338 | 8.6779 | 15.0438 | 24.0776 | 35.1113 | 0.01
4.5162 | 8.2581 | 6.5162 | 5.5162 | 7.7743 | 9.7743 | 8.2581 | 13.7743 | 21.5486 | 31.3228 | 4.5162 | 8.2581 | 6.5162 | 5.5262 | 7.7743 | 9.7743 | 8.2581 | 13.7843 | 21.5586 | 31.3328 | 0.01
4.8841 | 8.442 | 6.8841 | 5.8841 | 8.3261 | 10.3261 | 8.442 | 14.3261 | 22.6522 | 32.9782 | 4.8841 | 8.442 | 6.8841 | 5.8941 | 8.3261 | 10.3261 | 8.442 | 14.3361 | 22.6622 | 32.9882 | 0.01
5.6401 | 8.8201 | 7.6401 | 6.6401 | 9.4602 | 11.4602 | 8.8201 | 15.4602 | 24.9204 | 36.3806 | 5.6401 | 8.8201 | 7.6401 | 6.6501 | 9.4602 | 11.4602 | 8.8201 | 15.4702 | 24.9304 | 36.3906 | 0.01
9.7333 | 10.8666 | 11.7333 | 10.7333 | 15.5999 | 17.5999 | 10.8666 | 21.5999 | 37.1998 | 54.7997 | 9.7333 | 10.8666 | 11.7333 | 10.7433 | 15.5999 | 17.5999 | 10.8666 | 21.6099 | 37.2098 | 54.8097 | 0.01
4.4464 | 8.2232 | 6.4464 | 5.4464 | 7.6696 | 9.6696 | 8.2232 | 13.6696 | 21.3391 | 31.0087 | 4.4464 | 8.2232 | 6.4464 | 5.4564 | 7.6696 | 9.6696 | 8.2232 | 13.6796 | 21.3491 | 31.0187 | 0.01
3.4011 | 7.7006 | 5.4011 | 4.4011 | 6.1017 | 8.1017 | 7.7006 | 12.1017 | 18.2034 | 26.305 | 3.4011 | 7.7006 | 5.4011 | 4.4111 | 6.1017 | 8.1017 | 7.7006 | 12.1117 | 18.2134 | 26.315 | 0.01
5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 5.2901 | 8.645 | 7.2901 | 6.3001 | 8.9351 | 10.9351 | 8.645 | 14.9451 | 23.8802 | 34.8153 | 0.01
2.1888 | 7.0944 | 4.1888 | 3.1888 | 4.2832 | 6.2832 | 7.0944 | 10.2832 | 14.5665 | 20.8497 | 2.1888 | 7.0944 | 4.1888 | 3.1988 | 4.2832 | 6.2832 | 7.0944 | 10.2932 | 14.5765 | 20.8597 | 0.01
6.8979 | 9.449 | 8.8979 | 7.8979 | 11.3469 | 13.3469 | 9.449 | 17.3469 | 28.6937 | 42.0406 | 6.8979 | 9.449 | 8.8979 | 7.9079 | 11.3469 | 13.3469 | 9.449 | 17.3569 | 28.7037 | 42.0506 | 0.01
4.4544 | 8.2272 | 6.4544 | 5.4544 | 7.6816 | 9.6816 | 8.2272 | 13.6816 | 21.3633 | 31.0449 | 4.4544 | 8.2272 | 6.4544 | 5.4644 | 7.6816 | 9.6816 | 8.2272 | 13.6916 | 21.3733 | 31.0549 | 0.01
5.3782 | 8.6891 | 7.3782 | 6.3782 | 9.0673 | 11.0673 | 8.6891 | 15.0673 | 24.1346 | 35.202 | 5.3782 | 8.6891 | 7.3782 | 6.3882 | 9.0673 | 11.0673 | 8.6891 | 15.0773 | 24.1446 | 35.212 | 0.01
4.8642 | 8.4321 | 6.8642 | 5.8642 | 8.2962 | 10.2962 | 8.4321 | 14.2962 | 22.5925 | 32.8887 | 4.8642 | 8.4321 | 6.8642 | 5.8742 | 8.2962 | 10.2962 | 8.4321 | 14.3062 | 22.6025 | 32.8987 | 0.01
6.4795 | 9.2398 | 8.4795 | 7.4795 | 10.7193 | 12.7193 | 9.2398 | 16.7193 | 27.4386 | 40.1579 | 6.4795 | 9.2398 | 8.4795 | 7.4895 | 10.7193 | 12.7193 | 9.2398 | 16.7293 | 27.4486 | 40.1679 | 0.01
6.2353 | 9.1177 | 8.2353 | 7.2353 | 10.353 | 12.353 | 9.1177 | 16.353 | 26.7059 | 39.0589 | 6.2353 | 9.1177 | 8.2353 | 7.2453 | 10.353 | 12.353 | 9.1177 | 16.363 | 26.7159 | 39.0689 | 0.01
6.6358 | 9.3179 | 8.6358 | 7.6358 | 10.9537 | 12.9537 | 9.3179 | 16.9537 | 27.9073 | 40.861 | 6.6358 | 9.3179 | 8.6358 | 7.6458 | 10.9537 | 12.9537 | 9.3179 | 16.9637 | 27.9173 | 40.871 | 0.01
5.2598 | 8.6299 | 7.2598 | 6.2598 | 8.8898 | 10.8898 | 8.6299 | 14.8898 | 23.7795 | 34.6693 | 5.2598 | 8.6299 | 7.2598 | 6.2698 | 8.8898 | 10.8898 | 8.6299 | 14.8998 | 23.7895 | 34.6793 | 0.01
5.8382 | 8.9191 | 7.8382 | 6.8382 | 9.7573 | 11.7573 | 8.9191 | 15.7573 | 25.5145 | 37.2718 | 5.8382 | 8.9191 | 7.8382 | 6.8482 | 9.7573 | 11.7573 | 8.9191 | 15.7673 | 25.5245 | 37.2818 | 0.01
3.6537 | 7.8268 | 5.6537 | 4.6537 | 6.4805 | 8.4805 | 7.8268 | 12.4805 | 18.961 | 27.4415 | 3.6537 | 7.8268 | 5.6537 | 4.6637 | 6.4805 | 8.4805 | 7.8268 | 12.4905 | 18.971 | 27.4515 | 0.01
10.3093 | 11.1546 | 12.3093 | 11.3093 | 16.4639 | 18.4639 | 11.1546 | 22.4639 | 38.9278 | 57.3917 | 10.3093 | 11.1546 | 12.3093 | 11.3193 | 16.4639 | 18.4639 | 11.1546 | 22.4739 | 38.9378 | 57.4017 | 0.01
2.9072 | 7.4536 | 4.9072 | 3.9072 | 5.3609 | 7.3609 | 7.4536 | 11.3609 | 16.7217 | 24.0826 | 2.9072 | 7.4536 | 4.9072 | 3.9172 | 5.3609 | 7.3609 | 7.4536 | 11.3709 | 16.7317 | 24.0926 | 0.01
8.8398 | 10.4199 | 10.8398 | 9.8398 | 14.2596 | 16.2596 | 10.4199 | 20.2596 | 34.5193 | 50.7789 | 8.8398 | 10.4199 | 10.8398 | 9.8498 | 14.2596 | 16.2596 | 10.4199 | 20.2696 | 34.5293 | 50.7889 | 0.01
4.7994 | 8.3997 | 6.7994 | 5.7994 | 8.1991 | 10.1991 | 8.3997 | 14.1991 | 22.3981 | 32.5972 | 4.7994 | 8.3997 | 6.7994 | 5.8094 | 8.1991 | 10.1991 | 8.3997 | 14.2091 | 22.4081 | 32.6072 | 0.01
4.8728 | 8.4364 | 6.8728 | 5.8728 | 8.3092 | 10.3092 | 8.4364 | 14.3092 | 22.6183 | 32.9275 | 4.8728 | 8.4364 | 6.8728 | 5.8828 | 8.3092 | 10.3092 | 8.4364 | 14.3192 | 22.6283 | 32.9375 | 0.01
8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 8.8231 | 10.4115 | 10.8231 | 9.8331 | 14.2346 | 16.2346 | 10.4115 | 20.2446 | 34.4792 | 50.7139 | 0.01
8.2877 | 10.1438 | 10.2877 | 9.2877 | 13.4315 | 15.4315 | 10.1438 | 19.4315 | 32.863 | 48.2945 | 8.2877 | 10.1438 | 10.2877 | 9.2977 | 13.4315 | 15.4315 | 10.1438 | 19.4415 | 32.873 | 48.3045 | 0.01
5.1521 | 8.576 | 7.1521 | 6.1521 | 8.7281 | 10.7281 | 8.576 | 14.7281 | 23.4562 | 34.1843 | 5.1521 | 8.576 | 7.1521 | 6.1621 | 8.7281 | 10.7281 | 8.576 | 14.7381 | 23.4662 | 34.1943 | 0.01
7.8614 | 9.9307 | 9.8614 | 8.8614 | 12.7921 | 14.7921 | 9.9307 | 18.7921 | 31.5843 | 46.3764 | 7.8614 | 9.9307 | 9.8614 | 8.8714 | 12.7921 | 14.7921 | 9.9307 | 18.8021 | 31.5943 | 46.3864 | 0.01
7.2199 | 9.61 | 9.2199 | 8.2199 | 11.8299 | 13.8299 | 9.61 | 17.8299 | 29.6598 | 43.4897 | 7.2199 | 9.61 | 9.2199 | 8.2299 | 11.8299 | 13.8299 | 9.61 | 17.8399 | 29.6698 | 43.4997 | 0.01
5.6179 | 8.8089 | 7.6179 | 6.6179 | 9.4268 | 11.4268 | 8.8089 | 15.4268 | 24.8536 | 36.2804 | 5.6179 | 8.8089 | 7.6179 | 6.6279 | 9.4268 | 11.4268 | 8.8089 | 15.4368 | 24.8636 | 36.2904 | 0.01
2.7189 | 7.3595 | 4.7189 | 3.7189 | 5.0784 | 7.0784 | 7.3595 | 11.0784 | 16.1568 | 23.2352 | 2.7189 | 7.3595 | 4.7189 | 3.7289 | 5.0784 | 7.0784 | 7.3595 | 11.0884 | 16.1668 | 23.2452 | 0.01
7.0937 | 9.5468 | 9.0937 | 8.0937 | 11.6405 | 13.6405 | 9.5468 | 17.6405 | 29.281 | 42.9215 | 7.0937 | 9.5468 | 9.0937 | 8.1037 | 11.6405 | 13.6405 | 9.5468 | 17.6505 | 29.291 | 42.9315 | 0.01
6.5789 | 9.2894 | 8.5789 | 7.5789 | 10.8683 | 12.8683 | 9.2894 | 16.8683 | 27.7367 | 40.605 | 6.5789 | 9.2894 | 8.5789 | 7.5889 | 10.8683 | 12.8683 | 9.2894 | 16.8783 | 27.7467 | 40.615 | 0.01
4.9738 | 8.4869 | 6.9738 | 5.9738 | 8.4606 | 10.4606 | 8.4869 | 14.4606 | 22.9213 | 33.3819 | 4.9738 | 8.4869 | 6.9738 | 5.9838 | 8.4606 | 10.4606 | 8.4869 | 14.4706 | 22.9313 | 33.3919 | 0.01
5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 5.3943 | 8.6971 | 7.3943 | 6.4043 | 9.0914 | 11.0914 | 8.6971 | 15.1014 | 24.1928 | 35.2841 | 0.01
3.3249 | 7.6624 | 5.3249 | 4.3249 | 5.9873 | 7.9873 | 7.6624 | 11.9873 | 17.9746 | 25.9618 | 3.3249 | 7.6624 | 5.3249 | 4.3349 | 5.9873 | 7.9873 | 7.6624 | 11.9973 | 17.9846 | 25.9718 | 0.01
5.9637 | 8.9818 | 7.9637 | 6.9637 | 9.9455 | 11.9455 | 8.9818 | 15.9455 | 25.891 | 37.8365 | 5.9637 | 8.9818 | 7.9637 | 6.9737 | 9.9455 | 11.9455 | 8.9818 | 15.9555 | 25.901 | 37.8465 | 0.01
3.7881 | 7.894 | 5.7881 | 4.7881 | 6.6821 | 8.6821 | 7.894 | 12.6821 | 19.3643 | 28.0464 | 3.7881 | 7.894 | 5.7881 | 4.7981 | 6.6821 | 8.6821 | 7.894 | 12.6921 | 19.3743 | 28.0564 | 0.01
8.004 | 10.002 | 10.004 | 9.004 | 13.0059 | 15.0059 | 10.002 | 19.0059 | 32.0119 | 47.0178 | 8.004 | 10.002 | 10.004 | 9.014 | 13.0059 | 15.0059 | 10.002 | 19.0159 | 32.0219 | 47.0278 | 0.01
7.6199 | 9.8099 | 9.6199 | 8.6199 | 12.4298 | 14.4298 | 9.8099 | 18.4298 | 30.8596 | 45.2893 | 7.6199 | 9.8099 | 9.6199 | 8.6299 | 12.4298 | 14.4298 | 9.8099 | 18.4398 | 30.8696 | 45.2993 | 0.01
5.0882 | 8.5441 | 7.0882 | 6.0882 | 8.6323 | 10.6323 | 8.5441 | 14.6323 | 23.2646 | 33.8968 | 5.0882 | 8.5441 | 7.0882 | 6.0982 | 8.6323 | 10.6323 | 8.5441 | 14.6423 | 23.2746 | 33.9068 | 0.01
4.9297 | 8.4649 | 6.9297 | 5.9297 | 8.3946 | 10.3946 | 8.4649 | 14.3946 | 22.7891 | 33.1837 | 4.9297 | 8.4649 | 6.9297 | 5.9397 | 8.3946 | 10.3946 | 8.4649 | 14.4046 | 22.7991 | 33.1937 | 0.01
1.9638 | 6.9819 | 3.9638 | 2.9638 | 3.9457 | 5.9457 | 6.9819 | 9.9457 | 13.8914 | 19.8371 | 1.9638 | 6.9819 | 3.9638 | 2.9738 | 3.9457 | 5.9457 | 6.9819 | 9.9557 | 13.9014 | 19.8471 | 0.01
5.227 | 8.6135 | 7.227 | 6.227 | 8.8405 | 10.8405 | 8.6135 | 14.8405 | 23.6809 | 34.5214 | 5.227 | 8.6135 | 7.227 | 6.237 | 8.8405 | 10.8405 | 8.6135 | 14.8505 | 23.6909 | 34.5314 | 0.01
2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 2.9838 | 7.4919 | 4.9838 | 3.9938 | 5.4758 | 7.4758 | 7.4919 | 11.4858 | 16.9615 | 24.4373 | 0.01
6.9433 | 9.4717 | 8.9433 | 7.9433 | 11.415 | 13.415 | 9.4717 | 17.415 | 28.83 | 42.245 | 6.9433 | 9.4717 | 8.9433 | 7.9533 | 11.415 | 13.415 | 9.4717 | 17.425 | 28.84 | 42.255 | 0.01
5.765 | 8.8825 | 7.765 | 6.765 | 9.6475 | 11.6475 | 8.8825 | 15.6475 | 25.295 | 36.9425 | 5.765 | 8.8825 | 7.765 | 6.775 | 9.6475 | 11.6475 | 8.8825 | 15.6575 | 25.305 | 36.9525 | 0.01
2.6494 | 7.3247 | 4.6494 | 3.6494 | 4.9741 | 6.9741 | 7.3247 | 10.9741 | 15.9482 | 22.9223 | 2.6494 | 7.3247 | 4.6494 | 3.6594 | 4.9741 | 6.9741 | 7.3247 | 10.9841 | 15.9582 | 22.9323 | 0.01
7.3038 | 9.6519 | 9.3038 | 8.3038 | 11.9556 | 13.9556 | 9.6519 | 17.9556 | 29.9113 | 43.8669 | 7.3038 | 9.6519 | 9.3038 | 8.3138 | 11.9556 | 13.9556 | 9.6519 | 17.9656 | 29.9213 | 43.8769 | 0.01
3.554 | 7.777 | 5.554 | 4.554 | 6.3309 | 8.3309 | 7.777 | 12.3309 | 18.6619 | 26.9928 | 3.554 | 7.777 | 5.554 | 4.564 | 6.3309 | 8.3309 | 7.777 | 12.3409 | 18.6719 | 27.0028 | 0.01
5.9113 | 8.9557 | 7.9113 | 6.9113 | 9.867 | 11.867 | 8.9557 | 15.867 | 25.7339 | 37.6009 | 5.9113 | 8.9557 | 7.9113 | 6.9213 | 9.867 | 11.867 | 8.9557 | 15.877 | 25.7439 | 37.6109 | 0.01
8.773 | 10.3865 | 10.773 | 9.773 | 14.1595 | 16.1595 | 10.3865 | 20.1595 | 34.319 | 50.4785 | 8.773 | 10.3865 | 10.773 | 9.783 | 14.1595 | 16.1595 | 10.3865 | 20.1695 | 34.329 | 50.4885 | 0.01
6.175 | 9.0875 | 8.175 | 7.175 | 10.2625 | 12.2625 | 9.0875 | 16.2625 | 26.5251 | 38.7876 | 6.175 | 9.0875 | 8.175 | 7.185 | 10.2625 | 12.2625 | 9.0875 | 16.2725 | 26.5351 | 38.7976 | 0.01
7.0464 | 9.5232 | 9.0464 | 8.0464 | 11.5695 | 13.5695 | 9.5232 | 17.5695 | 29.1391 | 42.7086 | 7.0464 | 9.5232 | 9.0464 | 8.0564 | 11.5695 | 13.5695 | 9.5232 | 17.5795 | 29.1491 | 42.7186 | 0.01
4.9413 | 8.4707 | 6.9413 | 5.9413 | 8.412 | 10.412 | 8.4707 | 14.412 | 22.824 | 33.236 | 4.9413 | 8.4707 | 6.9413 | 5.9513 | 8.412 | 10.412 | 8.4707 | 14.422 | 22.834 | 33.246 | 0.01
4.8679 | 8.434 | 6.8679 | 5.8679 | 8.3019 | 10.3019 | 8.434 | 14.3019 | 22.6038 | 32.9057 | 4.8679 | 8.434 | 6.8679 | 5.8779 | 8.3019 | 10.3019 | 8.434 | 14.3119 | 22.6138 | 32.9157 | 0.01
4.8742 | 8.4371 | 6.8742 | 5.8742 | 8.3113 | 10.3113 | 8.4371 | 14.3113 | 22.6226 | 32.9339 | 4.8742 | 8.4371 | 6.8742 | 5.8842 | 8.3113 | 10.3113 | 8.4371 | 14.3213 | 22.6326 | 32.9439 | 0.01
9.329 | 10.6645 | 11.329 | 10.329 | 14.9935 | 16.9935 | 10.6645 | 20.9935 | 35.987 | 52.9806 | 9.329 | 10.6645 | 11.329 | 10.339 | 14.9935 | 16.9935 | 10.6645 | 21.0035 | 35.997 | 52.9906 | 0.01
7.5224 | 9.7612 | 9.5224 | 8.5224 | 12.2836 | 14.2836 | 9.7612 | 18.2836 | 30.5671 | 44.8507 | 7.5224 | 9.7612 | 9.5224 | 8.5324 | 12.2836 | 14.2836 | 9.7612 | 18.2936 | 30.5771 | 44.8607 | 0.01
8.1979 | 10.0989 | 10.1979 | 9.1979 | 13.2968 | 15.2968 | 10.0989 | 19.2968 | 32.5936 | 47.8904 | 8.1979 | 10.0989 | 10.1979 | 9.2079 | 13.2968 | 15.2968 | 10.0989 | 19.3068 | 32.6036 | 47.9004 | 0.01
5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 5.2196 | 8.6098 | 7.2196 | 6.2296 | 8.8293 | 10.8293 | 8.6098 | 14.8393 | 23.6687 | 34.498 | 0.01
8.1953 | 10.0977 | 10.1953 | 9.1953 | 13.293 | 15.293 | 10.0977 | 19.293 | 32.586 | 47.8791 | 8.1953 | 10.0977 | 10.1953 | 9.2053 | 13.293 | 15.293 | 10.0977 | 19.303 | 32.596 | 47.8891 | 0.01
4.9143 | 8.4572 | 6.9143 | 5.9143 | 8.3715 | 10.3715 | 8.4572 | 14.3715 | 22.7429 | 33.1144 | 4.9143 | 8.4572 | 6.9143 | 5.9243 | 8.3715 | 10.3715 | 8.4572 | 14.3815 | 22.7529 | 33.1244 | 0.01
8.9991 | 10.4995 | 10.9991 | 9.9991 | 14.4986 | 16.4986 | 10.4995 | 20.4986 | 34.9973 | 51.4959 | 8.9991 | 10.4995 | 10.9991 | 10.0091 | 14.4986 | 16.4986 | 10.4995 | 20.5086 | 35.0073 | 51.5059 | 0.01
3.9365 | 7.9683 | 5.9365 | 4.9365 | 6.9048 | 8.9048 | 7.9683 | 12.9048 | 19.8096 | 28.7143 | 3.9365 | 7.9683 | 5.9365 | 4.9465 | 6.9048 | 8.9048 | 7.9683 | 12.9148 | 19.8196 | 28.7243 | 0.01
7.8134 | 9.9067 | 9.8134 | 8.8134 | 12.7201 | 14.7201 | 9.9067 | 18.7201 | 31.4401 | 46.1602 | 7.8134 | 9.9067 | 9.8134 | 8.8234 | 12.7201 | 14.7201 | 9.9067 | 18.7301 | 31.4501 | 46.1702 | 0.01
4.0634 | 8.0317 | 6.0634 | 5.0634 | 7.0951 | 9.0951 | 8.0317 | 13.0951 | 20.1902 | 29.2853 | 4.0634 | 8.0317 | 6.0634 | 5.0734 | 7.0951 | 9.0951 | 8.0317 | 13.1051 | 20.2002 | 29.2953 | 0.01
6.7403 | 9.3702 | 8.7403 | 7.7403 | 11.1105 | 13.1105 | 9.3702 | 17.1105 | 28.221 | 41.3314 | 6.7403 | 9.3702 | 8.7403 | 7.7503 | 11.1105 | 13.1105 | 9.3702 | 17.1205 | 28.231 | 41.3414 | 0.01
5.6408 | 8.8204 | 7.6408 | 6.6408 | 9.4611 | 11.4611 | 8.8204 | 15.4611 | 24.9223 | 36.3834 | 5.6408 | 8.8204 | 7.6408 | 6.6508 | 9.4611 | 11.4611 | 8.8204 | 15.4711 | 24.9323 | 36.3934 | 0.01
6.2507 | 9.1254 | 8.2507 | 7.2507 | 10.3761 | 12.3761 | 9.1254 | 16.3761 | 26.7522 | 39.1283 | 6.2507 | 9.1254 | 8.2507 | 7.2607 | 10.3761 | 12.3761 | 9.1254 | 16.3861 | 26.7622 | 39.1383 | 0.01
8.3342 | 10.1671 | 10.3342 | 9.3342 | 13.5013 | 15.5013 | 10.1671 | 19.5013 | 33.0026 | 48.5039 | 8.3342 | 10.1671 | 10.3342 | 9.3442 | 13.5013 | 15.5013 | 10.1671 | 19.5113 | 33.0126 | 48.5139 | 0.01
9.8378 | 10.9189 | 11.8378 | 10.8378 | 15.7567 | 17.7567 | 10.9189 | 21.7567 | 37.5135 | 55.2702 | 9.8378 | 10.9189 | 11.8378 | 10.8478 | 15.7567 | 17.7567 | 10.9189 | 21.7667 | 37.5235 | 55.2802 | 0.01
5.9193 | 8.9596 | 7.9193 | 6.9193 | 9.8789 | 11.8789 | 8.9596 | 15.8789 | 25.7578 | 37.6367 | 5.9193 | 8.9596 | 7.9193 | 6.9293 | 9.8789 | 11.8789 | 8.9596 | 15.8889 | 25.7678 | 37.6467 | 0.01
9.7806 | 10.8903 | 11.7806 | 10.7806 | 15.6709 | 17.6709 | 10.8903 | 21.6709 | 37.3418 | 55.0127 | 9.7806 | 10.8903 | 11.7806 | 10.7906 | 15.6709 | 17.6709 | 10.8903 | 21.6809 | 37.3518 | 55.0227 | 0.01
7.2998 | 9.6499 | 9.2998 | 8.2998 | 11.9497 | 13.9497 | 9.6499 | 17.9497 | 29.8993 | 43.849 | 7.2998 | 9.6499 | 9.2998 | 8.3098 | 11.9497 | 13.9497 | 9.6499 | 17.9597 | 29.9093 | 43.859 | 0.01
5.2258 | 8.6129 | 7.2258 | 6.2258 | 8.8387 | 10.8387 | 8.6129 | 14.8387 | 23.6775 | 34.5162 | 5.2258 | 8.6129 | 7.2258 | 6.2358 | 8.8387 | 10.8387 | 8.6129 | 14.8487 | 23.6875 | 34.5262 | 0.01
5.5571 | 8.7785 | 7.5571 | 6.5571 | 9.3356 | 11.3356 | 8.7785 | 15.3356 | 24.6712 | 36.0068 | 5.5571 | 8.7785 | 7.5571 | 6.5671 | 9.3356 | 11.3356 | 8.7785 | 15.3456 | 24.6812 | 36.0168 | 0.01
3.6445 | 7.8223 | 5.6445 | 4.6445 | 6.4668 | 8.4668 | 7.8223 | 12.4668 | 18.9335 | 27.4003 | 3.6445 | 7.8223 | 5.6445 | 4.6545 | 6.4668 | 8.4668 | 7.8223 | 12.4768 | 18.9435 | 27.4103 | 0.01
4.0026 | 8.0013 | 6.0026 | 5.0026 | 7.0039 | 9.0039 | 8.0013 | 13.0039 | 20.0078 | 29.0117 | 4.0026 | 8.0013 | 6.0026 | 5.0126 | 7.0039 | 9.0039 | 8.0013 | 13.0139 | 20.0178 | 29.0217 | 0.01
6.0532 | 9.0266 | 8.0532 | 7.0532 | 10.0798 | 12.0798 | 9.0266 | 16.0798 | 26.1595 | 38.2393 | 6.0532 | 9.0266 | 8.0532 | 7.0632 | 10.0798 | 12.0798 | 9.0266 | 16.0898 | 26.1695 | 38.2493 | 0.01
6.9761 | 9.4881 | 8.9761 | 7.9761 | 11.4642 | 13.4642 | 9.4881 | 17.4642 | 28.9284 | 42.3925 | 6.9761 | 9.4881 | 8.9761 | 7.9861 | 11.4642 | 13.4642 | 9.4881 | 17.4742 | 28.9384 | 42.4025 | 0.01
2.4113 | 7.2056 | 4.4113 | 3.4113 | 4.6169 | 6.6169 | 7.2056 | 10.6169 | 15.2338 | 21.8508 | 2.4113 | 7.2056 | 4.4113 | 3.4213 | 4.6169 | 6.6169 | 7.2056 | 10.6269 | 15.2438 | 21.8608 | 0.01
3.7525 | 7.8762 | 5.7525 | 4.7525 | 6.6287 | 8.6287 | 7.8762 | 12.6287 | 19.2575 | 27.8862 | 3.7525 | 7.8762 | 5.7525 | 4.7625 | 6.6287 | 8.6287 | 7.8762 | 12.6387 | 19.2675 | 27.8962 | 0.01
6.4384 | 9.2192 | 8.4384 | 7.4384 | 10.6576 | 12.6576 | 9.2192 | 16.6576 | 27.3151 | 39.9727 | 6.4384 | 9.2192 | 8.4384 | 7.4484 | 10.6576 | 12.6576 | 9.2192 | 16.6676 | 27.3251 | 39.9827 | 0.01
1.4433 | 6.7216 | 3.4433 | 2.4433 | 3.1649 | 5.1649 | 6.7216 | 9.1649 | 12.3299 | 17.4948 | 1.4433 | 6.7216 | 3.4433 | 2.4533 | 3.1649 | 5.1649 | 6.7216 | 9.1749 | 12.3399 | 17.5048 | 0.01
7.9113 | 9.9557 | 9.9113 | 8.9113 | 12.867 | 14.867 | 9.9557 | 18.867 | 31.734 | 46.6009 | 7.9113 | 9.9557 | 9.9113 | 8.9213 | 12.867 | 14.867 | 9.9557 | 18.877 | 31.744 | 46.6109 | 0.01
4.1557 | 8.0779 | 6.1557 | 5.1557 | 7.2336 | 9.2336 | 8.0779 | 13.2336 | 20.4672 | 29.7007 | 4.1557 | 8.0779 | 6.1557 | 5.1657 | 7.2336 | 9.2336 | 8.0779 | 13.2436 | 20.4772 | 29.7107 | 0.01
9.7438 | 10.8719 | 11.7438 | 10.7438 | 15.6157 | 17.6157 | 10.8719 | 21.6157 | 37.2314 | 54.8471 | 9.7438 | 10.8719 | 11.7438 | 10.7538 | 15.6157 | 17.6157 | 10.8719 | 21.6257 | 37.2414 | 54.8571 | 0.01
8.0146 | 10.0073 | 10.0146 | 9.0146 | 13.0219 | 15.0219 | 10.0073 | 19.0219 | 32.0438 | 47.0657 | 8.0146 | 10.0073 | 10.0146 | 9.0246 | 13.0219 | 15.0219 | 10.0073 | 19.0319 | 32.0538 | 47.0757 | 0.01
7.2032 | 9.6016 | 9.2032 | 8.2032 | 11.8048 | 13.8048 | 9.6016 | 17.8048 | 29.6096 | 43.4144 | 7.2032 | 9.6016 | 9.2032 | 8.2132 | 11.8048 | 13.8048 | 9.6016 | 17.8148 | 29.6196 | 43.4244 | 0.01
5.1038 | 8.5519 | 7.1038 | 6.1038 | 8.6557 | 10.6557 | 8.5519 | 14.6557 | 23.3113 | 33.967 | 5.1038 | 8.5519 | 7.1038 | 6.1138 | 8.6557 | 10.6557 | 8.5519 | 14.6657 | 23.3213 | 33.977 | 0.01
10.3046 | 11.1523 | 12.3046 | 11.3046 | 16.4569 | 18.4569 | 11.1523 | 22.4569 | 38.9138 | 57.3707 | 10.3046 | 11.1523 | 12.3046 | 11.3146 | 16.4569 | 18.4569 | 11.1523 | 22.4669 | 38.9238 | 57.3807 | 0.01
6.0128 | 9.0064 | 8.0128 | 7.0128 | 10.0192 | 12.0192 | 9.0064 | 16.0192 | 26.0383 | 38.0575 | 6.0128 | 9.0064 | 8.0128 | 7.0228 | 10.0192 | 12.0192 | 9.0064 | 16.0292 | 26.0483 | 38.0675 | 0.01
5.3452 | 8.6726 | 7.3452 | 6.3452 | 9.0178 | 11.0178 | 8.6726 | 15.0178 | 24.0356 | 35.0535 | 5.3452 | 8.6726 | 7.3452 | 6.3552 | 9.0178 | 11.0178 | 8.6726 | 15.0278 | 24.0456 | 35.0635 | 0.01
5.0104 | 8.5052 | 7.0104 | 6.0104 | 8.5156 | 10.5156 | 8.5052 | 14.5156 | 23.0312 | 33.5469 | 5.0104 | 8.5052 | 7.0104 | 6.0204 | 8.5156 | 10.5156 | 8.5052 | 14.5256 | 23.0412 | 33.5569 | 0.01
8.5886 | 10.2943 | 10.5886 | 9.5886 | 13.8829 | 15.8829 | 10.2943 | 19.8829 | 33.7658 | 49.6487 | 8.5886 | 10.2943 | 10.5886 | 9.5986 | 13.8829 | 15.8829 | 10.2943 | 19.8929 | 33.7758 | 49.6587 | 0.01
4.7374 | 8.3687 | 6.7374 | 5.7374 | 8.1061 | 10.1061 | 8.3687 | 14.1061 | 22.2122 | 32.3184 | 4.7374 | 8.3687 | 6.7374 | 5.7474 | 8.1061 | 10.1061 | 8.3687 | 14.1161 | 22.2222 | 32.3284 | 0.01
4.205 | 8.1025 | 6.205 | 5.205 | 7.3075 | 9.3075 | 8.1025 | 13.3075 | 20.6151 | 29.9226 | 4.205 | 8.1025 | 6.205 | 5.215 | 7.3075 | 9.3075 | 8.1025 | 13.3175 | 20.6251 | 29.9326 | 0.01
6.7811 | 9.3906 | 8.7811 | 7.7811 | 11.1717 | 13.1717 | 9.3906 | 17.1717 | 28.3433 | 41.515 | 6.7811 | 9.3906 | 8.7811 | 7.7911 | 11.1717 | 13.1717 | 9.3906 | 17.1817 | 28.3533 | 41.525 | 0.01
5.058 | 8.529 | 7.058 | 6.058 | 8.5871 | 10.5871 | 8.529 | 14.5871 | 23.1741 | 33.7612 | 5.058 | 8.529 | 7.058 | 6.068 | 8.5871 | 10.5871 | 8.529 | 14.5971 | 23.1841 | 33.7712 | 0.01
5.1781 | 8.5891 | 7.1781 | 6.1781 | 8.7672 | 10.7672 | 8.5891 | 14.7672 | 23.5343 | 34.3015 | 5.1781 | 8.5891 | 7.1781 | 6.1881 | 8.7672 | 10.7672 | 8.5891 | 14.7772 | 23.5443 | 34.3115 | 0.01
2.0437 | 7.0219 | 4.0437 | 3.0437 | 4.0656 | 6.0656 | 7.0219 | 10.0656 | 14.1312 | 20.1968 | 2.0437 | 7.0219 | 4.0437 | 3.0537 | 4.0656 | 6.0656 | 7.0219 | 10.0756 | 14.1412 | 20.2068 | 0.01
7.546 | 9.773 | 9.546 | 8.546 | 12.319 | 14.319 | 9.773 | 18.319 | 30.6379 | 44.9569 | 7.546 | 9.773 | 9.546 | 8.556 | 12.319 | 14.319 | 9.773 | 18.329 | 30.6479 | 44.9669 | 0.01
5.6743 | 8.8371 | 7.6743 | 6.6743 | 9.5114 | 11.5114 | 8.8371 | 15.5114 | 25.0229 | 36.5343 | 5.6743 | 8.8371 | 7.6743 | 6.6843 | 9.5114 | 11.5114 | 8.8371 | 15.5214 | 25.0329 | 36.5443 | 0.01
4.0812 | 8.0406 | 6.0812 | 5.0812 | 7.1218 | 9.1218 | 8.0406 | 13.1218 | 20.2435 | 29.3653 | 4.0812 | 8.0406 | 6.0812 | 5.0912 | 7.1218 | 9.1218 | 8.0406 | 13.1318 | 20.2535 | 29.3753 | 0.01
9.5518 | 10.7759 | 11.5518 | 10.5518 | 15.3277 | 17.3277 | 10.7759 | 21.3277 | 36.6555 | 53.9832 | 9.5518 | 10.7759 | 11.5518 | 10.5618 | 15.3277 | 17.3277 | 10.7759 | 21.3377 | 36.6655 | 53.9932 | 0.01
7.9334 | 9.9667 | 9.9334 | 8.9334 | 12.9001 | 14.9001 | 9.9667 | 18.9001 | 31.8003 | 46.7004 | 7.9334 | 9.9667 | 9.9334 | 8.9434 | 12.9001 | 14.9001 | 9.9667 | 18.9101 | 31.8103 | 46.7104 | 0.01
4.7753 | 8.3876 | 6.7753 | 5.7753 | 8.1629 | 10.1629 | 8.3876 | 14.1629 | 22.3258 | 32.4888 | 4.7753 | 8.3876 | 6.7753 | 5.7853 | 8.1629 | 10.1629 | 8.3876 | 14.1729 | 22.3358 | 32.4988 | 0.01
8.5211 | 10.2606 | 10.5211 | 9.5211 | 13.7817 | 15.7817 | 10.2606 | 19.7817 | 33.5634 | 49.3451 | 8.5211 | 10.2606 | 10.5211 | 9.5311 | 13.7817 | 15.7817 | 10.2606 | 19.7917 | 33.5734 | 49.3551 | 0.01
5.7198 | 8.8599 | 7.7198 | 6.7198 | 9.5797 | 11.5797 | 8.8599 | 15.5797 | 25.1594 | 36.7391 | 5.7198 | 8.8599 | 7.7198 | 6.7298 | 9.5797 | 11.5797 | 8.8599 | 15.5897 | 25.1694 | 36.7491 | 0.01
4.9962 | 8.4981 | 6.9962 | 5.9962 | 8.4943 | 10.4943 | 8.4981 | 14.4943 | 22.9886 | 33.4829 | 4.9962 | 8.4981 | 6.9962 | 6.0062 | 8.4943 | 10.4943 | 8.4981 | 14.5043 | 22.9986 | 33.4929 | 0.01
5.1437 | 8.5718 | 7.1437 | 6.1437 | 8.7155 | 10.7155 | 8.5718 | 14.7155 | 23.4311 | 34.1466 | 5.1437 | 8.5718 | 7.1437 | 6.1537 | 8.7155 | 10.7155 | 8.5718 | 14.7255 | 23.4411 | 34.1566 | 0.01
5.9165 | 8.9583 | 7.9165 | 6.9165 | 9.8748 | 11.8748 | 8.9583 | 15.8748 | 25.7496 | 37.6243 | 5.9165 | 8.9583 | 7.9165 | 6.9265 | 9.8748 | 11.8748 | 8.9583 | 15.8848 | 25.7596 | 37.6343 | 0.01
6.5709 | 9.2855 | 8.5709 | 7.5709 | 10.8564 | 12.8564 | 9.2855 | 16.8564 | 27.7128 | 40.5691 | 6.5709 | 9.2855 | 8.5709 | 7.5809 | 10.8564 | 12.8564 | 9.2855 | 16.8664 | 27.7228 | 40.5791 | 0.01
4.407 | 8.2035 | 6.407 | 5.407 | 7.6105 | 9.6105 | 8.2035 | 13.6105 | 21.2209 | 30.8314 | 4.407 | 8.2035 | 6.407 | 5.417 | 7.6105 | 9.6105 | 8.2035 | 13.6205 | 21.2309 | 30.8414 | 0.01
7.6827 | 9.8413 | 9.6827 | 8.6827 | 12.524 | 14.524 | 9.8413 | 18.524 | 31.048 | 45.572 | 7.6827 | 9.8413 | 9.6827 | 8.6927 | 12.524 | 14.524 | 9.8413 | 18.534 | 31.058 | 45.582 | 0.01
5.0637 | 8.5318 | 7.0637 | 6.0637 | 8.5955 | 10.5955 | 8.5318 | 14.5955 | 23.191 | 33.7865 | 5.0637 | 8.5318 | 7.0637 | 6.0737 | 8.5955 | 10.5955 | 8.5318 | 14.6055 | 23.201 | 33.7965 | 0.01
3.1421 | 7.5711 | 5.1421 | 4.1421 | 5.7132 | 7.7132 | 7.5711 | 11.7132 | 17.4263 | 25.1395 | 3.1421 | 7.5711 | 5.1421 | 4.1521 | 5.7132 | 7.7132 | 7.5711 | 11.7232 | 17.4363 | 25.1495 | 0.01
8.3315 | 10.1657 | 10.3315 | 9.3315 | 13.4972 | 15.4972 | 10.1657 | 19.4972 | 32.9944 | 48.4916 | 8.3315 | 10.1657 | 10.3315 | 9.3415 | 13.4972 | 15.4972 | 10.1657 | 19.5072 | 33.0044 | 48.5016 | 0.01
7.0219 | 9.5109 | 9.0219 | 8.0219 | 11.5328 | 13.5328 | 9.5109 | 17.5328 | 29.0656 | 42.5985 | 7.0219 | 9.5109 | 9.0219 | 8.0319 | 11.5328 | 13.5328 | 9.5109 | 17.5428 | 29.0756 | 42.6085 | 0.01
7.4577 | 9.7289 | 9.4577 | 8.4577 | 12.1866 | 14.1866 | 9.7289 | 18.1866 | 30.3732 | 44.5599 | 7.4577 | 9.7289 | 9.4577 | 8.4677 | 12.1866 | 14.1866 | 9.7289 | 18.1966 | 30.3832 | 44.5699 | 0.01
8.7512 | 10.3756 | 10.7512 | 9.7512 | 14.1268 | 16.1268 | 10.3756 | 20.1268 | 34.2535 | 50.3803 | 8.7512 | 10.3756 | 10.7512 | 9.7612 | 14.1268 | 16.1268 | 10.3756 | 20.1368 | 34.2635 | 50.3903 | 0.01
3.186 | 7.593 | 5.186 | 4.186 | 5.779 | 7.779 | 7.593 | 11.779 | 17.558 | 25.337 | 3.186 | 7.593 | 5.186 | 4.196 | 5.779 | 7.779 | 7.593 | 11.789 | 17.568 | 25.347 | 0.01
3.9737 | 7.9868 | 5.9737 | 4.9737 | 6.9605 | 8.9605 | 7.9868 | 12.9605 | 19.921 | 28.8815 | 3.9737 | 7.9868 | 5.9737 | 4.9837 | 6.9605 | 8.9605 | 7.9868 | 12.9705 | 19.931 | 28.8915 | 0.01
6.1466 | 9.0733 | 8.1466 | 7.1466 | 10.2199 | 12.2199 | 9.0733 | 16.2199 | 26.4399 | 38.6598 | 6.1466 | 9.0733 | 8.1466 | 7.1566 | 10.2199 | 12.2199 | 9.0733 | 16.2299 | 26.4499 | 38.6698 | 0.01
4.2176 | 8.1088 | 6.2176 | 5.2176 | 7.3264 | 9.3264 | 8.1088 | 13.3264 | 20.6527 | 29.9791 | 4.2176 | 8.1088 | 6.2176 | 5.2276 | 7.3264 | 9.3264 | 8.1088 | 13.3364 | 20.6627 | 29.9891 | 0.01
6.6912 | 9.3456 | 8.6912 | 7.6912 | 11.0368 | 13.0368 | 9.3456 | 17.0368 | 28.0737 | 41.1105 | 6.6912 | 9.3456 | 8.6912 | 7.7012 | 11.0368 | 13.0368 | 9.3456 | 17.0468 | 28.0837 | 41.1205 | 0.01
4.7236 | 8.3618 | 6.7236 | 5.7236 | 8.0853 | 10.0853 | 8.3618 | 14.0853 | 22.1707 | 32.256 | 4.7236 | 8.3618 | 6.7236 | 5.7336 | 8.0853 | 10.0853 | 8.3618 | 14.0953 | 22.1807 | 32.266 | 0.01
4.7267 | 8.3634 | 6.7267 | 5.7267 | 8.0901 | 10.0901 | 8.3634 | 14.0901 | 22.1802 | 32.2704 | 4.7267 | 8.3634 | 6.7267 | 5.7367 | 8.0901 | 10.0901 | 8.3634 | 14.1001 | 22.1902 | 32.2804 | 0.01
7.199 | 9.5995 | 9.199 | 8.199 | 11.7985 | 13.7985 | 9.5995 | 17.7985 | 29.5969 | 43.3954 | 7.199 | 9.5995 | 9.199 | 8.209 | 11.7985 | 13.7985 | 9.5995 | 17.8085 | 29.6069 | 43.4054 | 0.01
3.7067 | 7.8534 | 5.7067 | 4.7067 | 6.5601 | 8.5601 | 7.8534 | 12.5601 | 19.1202 | 27.6803 | 3.7067 | 7.8534 | 5.7067 | 4.7167 | 6.5601 | 8.5601 | 7.8534 | 12.5701 | 19.1302 | 27.6903 | 0.01
5.995 | 8.9975 | 7.995 | 6.995 | 9.9925 | 11.9925 | 8.9975 | 15.9925 | 25.9851 | 37.9776 | 5.995 | 8.9975 | 7.995 | 7.005 | 9.9925 | 11.9925 | 8.9975 | 16.0025 | 25.9951 | 37.9876 | 0.01
5.0831 | 8.5415 | 7.0831 | 6.0831 | 8.6246 | 10.6246 | 8.5415 | 14.6246 | 23.2493 | 33.8739 | 5.0831 | 8.5415 | 7.0831 | 6.0931 | 8.6246 | 10.6246 | 8.5415 | 14.6346 | 23.2593 | 33.8839 | 0.01
6.1092 | 9.0546 | 8.1092 | 7.1092 | 10.1638 | 12.1638 | 9.0546 | 16.1638 | 26.3277 | 38.4915 | 6.1092 | 9.0546 | 8.1092 | 7.1192 | 10.1638 | 12.1638 | 9.0546 | 16.1738 | 26.3377 | 38.5015 | 0.01
8.5861 | 10.2931 | 10.5861 | 9.5861 | 13.8792 | 15.8792 | 10.2931 | 19.8792 | 33.7584 | 49.6375 | 8.5861 | 10.2931 | 10.5861 | 9.5961 | 13.8792 | 15.8792 | 10.2931 | 19.8892 | 33.7684 | 49.6475 | 0.01
5.3112 | 8.6556 | 7.3112 | 6.3112 | 8.9668 | 10.9668 | 8.6556 | 14.9668 | 23.9337 | 34.9005 | 5.3112 | 8.6556 | 7.3112 | 6.3212 | 8.9668 | 10.9668 | 8.6556 | 14.9768 | 23.9437 | 34.9105 | 0.01
3.0662 | 7.5331 | 5.0662 | 4.0662 | 5.5993 | 7.5993 | 7.5331 | 11.5993 | 17.1985 | 24.7978 | 3.0662 | 7.5331 | 5.0662 | 4.0762 | 5.5993 | 7.5993 | 7.5331 | 11.6093 | 17.2085 | 24.8078 | 0.01
5.713 | 8.8565 | 7.713 | 6.713 | 9.5695 | 11.5695 | 8.8565 | 15.5695 | 25.139 | 36.7085 | 5.713 | 8.8565 | 7.713 | 6.723 | 9.5695 | 11.5695 | 8.8565 | 15.5795 | 25.149 | 36.7185 | 0.01
2.1945 | 7.0972 | 4.1945 | 3.1945 | 4.2917 | 6.2917 | 7.0972 | 10.2917 | 14.5834 | 20.8751 | 2.1945 | 7.0972 | 4.1945 | 3.2045 | 4.2917 | 6.2917 | 7.0972 | 10.3017 | 14.5934 | 20.8851 | 0.01
4.0199 | 8.01 | 6.0199 | 5.0199 | 7.0299 | 9.0299 | 8.01 | 13.0299 | 20.0597 | 29.0896 | 4.0199 | 8.01 | 6.0199 | 5.0299 | 7.0299 | 9.0299 | 8.01 | 13.0399 | 20.0697 | 29.0996 | 0.01
6.6125 | 9.3062 | 8.6125 | 7.6125 | 10.9187 | 12.9187 | 9.3062 | 16.9187 | 27.8374 | 40.7562 | 6.6125 | 9.3062 | 8.6125 | 7.6225 | 10.9187 | 12.9187 | 9.3062 | 16.9287 | 27.8474 | 40.7662 | 0.01
6.4942 | 9.2471 | 8.4942 | 7.4942 | 10.7413 | 12.7413 | 9.2471 | 16.7413 | 27.4826 | 40.2239 | 6.4942 | 9.2471 | 8.4942 | 7.5042 | 10.7413 | 12.7413 | 9.2471 | 16.7513 | 27.4926 | 40.2339 | 0.01
5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 5.0921 | 8.546 | 7.0921 | 6.1021 | 8.6381 | 10.6381 | 8.546 | 14.6481 | 23.2863 | 33.9244 | 0.01
5.964 | 8.982 | 7.964 | 6.964 | 9.946 | 11.946 | 8.982 | 15.946 | 25.8919 | 37.8379 | 5.964 | 8.982 | 7.964 | 6.974 | 9.946 | 11.946 | 8.982 | 15.956 | 25.9019 | 37.8479 | 0.01
5.7816 | 8.8908 | 7.7816 | 6.7816 | 9.6724 | 11.6724 | 8.8908 | 15.6724 | 25.3449 | 37.0173 | 5.7816 | 8.8908 | 7.7816 | 6.7916 | 9.6724 | 11.6724 | 8.8908 | 15.6824 | 25.3549 | 37.0273 | 0.01
3.5707 | 7.7853 | 5.5707 | 4.5707 | 6.356 | 8.356 | 7.7853 | 12.356 | 18.712 | 27.068 | 3.5707 | 7.7853 | 5.5707 | 4.5807 | 6.356 | 8.356 | 7.7853 | 12.366 | 18.722 | 27.078 | 0.01
3.9955 | 7.9978 | 5.9955 | 4.9955 | 6.9933 | 8.9933 | 7.9978 | 12.9933 | 19.9866 | 28.9799 | 3.9955 | 7.9978 | 5.9955 | 5.0055 | 6.9933 | 8.9933 | 7.9978 | 13.0033 | 19.9966 | 28.9899 | 0.01
6.0997 | 9.0499 | 8.0997 | 7.0997 | 10.1496 | 12.1496 | 9.0499 | 16.1496 | 26.2992 | 38.4487 | 6.0997 | 9.0499 | 8.0997 | 7.1097 | 10.1496 | 12.1496 | 9.0499 | 16.1596 | 26.3092 | 38.4587 | 0.01
7.8375 | 9.9188 | 9.8375 | 8.8375 | 12.7563 | 14.7563 | 9.9188 | 18.7563 | 31.5125 | 46.2688 | 7.8375 | 9.9188 | 9.8375 | 8.8475 | 12.7563 | 14.7563 | 9.9188 | 18.7663 | 31.5225 | 46.2788 | 0.01
6.5393 | 9.2696 | 8.5393 | 7.5393 | 10.8089 | 12.8089 | 9.2696 | 16.8089 | 27.6178 | 40.4267 | 6.5393 | 9.2696 | 8.5393 | 7.5493 | 10.8089 | 12.8089 | 9.2696 | 16.8189 | 27.6278 | 40.4367 | 0.01
3.8684 | 7.9342 | 5.8684 | 4.8684 | 6.8026 | 8.8026 | 7.9342 | 12.8026 | 19.6051 | 28.4077 | 3.8684 | 7.9342 | 5.8684 | 4.8784 | 6.8026 | 8.8026 | 7.9342 | 12.8126 | 19.6151 | 28.4177 | 0.01
5.8862 | 8.9431 | 7.8862 | 6.8862 | 9.8293 | 11.8293 | 8.9431 | 15.8293 | 25.6586 | 37.4878 | 5.8862 | 8.9431 | 7.8862 | 6.8962 | 9.8293 | 11.8293 | 8.9431 | 15.8393 | 25.6686 | 37.4978 | 0.01
4.754 | 8.377 | 6.754 | 5.754 | 8.131 | 10.131 | 8.377 | 14.131 | 22.262 | 32.3929 | 4.754 | 8.377 | 6.754 | 5.764 | 8.131 | 10.131 | 8.377 | 14.141 | 22.272 | 32.4029 | 0.01
3.8834 | 7.9417 | 5.8834 | 4.8834 | 6.8251 | 8.8251 | 7.9417 | 12.8251 | 19.6503 | 28.4754 | 3.8834 | 7.9417 | 5.8834 | 4.8934 | 6.8251 | 8.8251 | 7.9417 | 12.8351 | 19.6603 | 28.4854 | 0.01
5.5401 | 8.7701 | 7.5401 | 6.5401 | 9.3102 | 11.3102 | 8.7701 | 15.3102 | 24.6204 | 35.9306 | 5.5401 | 8.7701 | 7.5401 | 6.5501 | 9.3102 | 11.3102 | 8.7701 | 15.3202 | 24.6304 | 35.9406 | 0.01
6.0247 | 9.0124 | 8.0247 | 7.0247 | 10.0371 | 12.0371 | 9.0124 | 16.0371 | 26.0741 | 38.1112 | 6.0247 | 9.0124 | 8.0247 | 7.0347 | 10.0371 | 12.0371 | 9.0124 | 16.0471 | 26.0841 | 38.1212 | 0.01
4.9316 | 8.4658 | 6.9316 | 5.9316 | 8.3975 | 10.3975 | 8.4658 | 14.3975 | 22.7949 | 33.1924 | 4.9316 | 8.4658 | 6.9316 | 5.9416 | 8.3975 | 10.3975 | 8.4658 | 14.4075 | 22.8049 | 33.2024 | 0.01
9.3444 | 10.6722 | 11.3444 | 10.3444 | 15.0166 | 17.0166 | 10.6722 | 21.0166 | 36.0332 | 53.0498 | 9.3444 | 10.6722 | 11.3444 | 10.3544 | 15.0166 | 17.0166 | 10.6722 | 21.0266 | 36.0432 | 53.0598 | 0.01
6.4224 | 9.2112 | 8.4224 | 7.4224 | 10.6336 | 12.6336 | 9.2112 | 16.6336 | 27.2672 | 39.9008 | 6.4224 | 9.2112 | 8.4224 | 7.4324 | 10.6336 | 12.6336 | 9.2112 | 16.6436 | 27.2772 | 39.9108 | 0.01
5.0339 | 8.5169 | 7.0339 | 6.0339 | 8.5508 | 10.5508 | 8.5169 | 14.5508 | 23.1016 | 33.6524 | 5.0339 | 8.5169 | 7.0339 | 6.0439 | 8.5508 | 10.5508 | 8.5169 | 14.5608 | 23.1116 | 33.6624 | 0.01
5.9344 | 8.9672 | 7.9344 | 6.9344 | 9.9016 | 11.9016 | 8.9672 | 15.9016 | 25.8033 | 37.7049 | 5.9344 | 8.9672 | 7.9344 | 6.9444 | 9.9016 | 11.9016 | 8.9672 | 15.9116 | 25.8133 | 37.7149 | 0.01
6.8634 | 9.4317 | 8.8634 | 7.8634 | 11.295 | 13.295 | 9.4317 | 17.295 | 28.5901 | 41.8851 | 6.8634 | 9.4317 | 8.8634 | 7.8734 | 11.295 | 13.295 | 9.4317 | 17.305 | 28.6001 | 41.8951 | 0.01
3.9905 | 7.9952 | 5.9905 | 4.9905 | 6.9857 | 8.9857 | 7.9952 | 12.9857 | 19.9714 | 28.9572 | 3.9905 | 7.9952 | 5.9905 | 5.0005 | 6.9857 | 8.9857 | 7.9952 | 12.9957 | 19.9814 | 28.9672 | 0.01
7.2021 | 9.601 | 9.2021 | 8.2021 | 11.8031 | 13.8031 | 9.601 | 17.8031 | 29.6063 | 43.4094 | 7.2021 | 9.601 | 9.2021 | 8.2121 | 11.8031 | 13.8031 | 9.601 | 17.8131 | 29.6163 | 43.4194 | 0.01
0.53517 | 6.2676 | 2.5352 | 1.5352 | 1.8028 | 3.8028 | 6.2676 | 7.8028 | 9.6055 | 13.4083 | 0.53517 | 6.2676 | 2.5352 | 1.5452 | 1.8028 | 3.8028 | 6.2676 | 7.8128 | 9.6155 | 13.4183 | 0.01
5.5684 | 8.7842 | 7.5684 | 6.5684 | 9.3525 | 11.3525 | 8.7842 | 15.3525 | 24.7051 | 36.0576 | 5.5684 | 8.7842 | 7.5684 | 6.5784 | 9.3525 | 11.3525 | 8.7842 | 15.3625 | 24.7151 | 36.0676 | 0.01
5.3874 | 8.6937 | 7.3874 | 6.3874 | 9.081 | 11.081 | 8.6937 | 15.081 | 24.1621 | 35.2431 | 5.3874 | 8.6937 | 7.3874 | 6.3974 | 9.081 | 11.081 | 8.6937 | 15.091 | 24.1721 | 35.2531 | 0.01
6.5294 | 9.2647 | 8.5294 | 7.5294 | 10.7942 | 12.7942 | 9.2647 | 16.7942 | 27.5883 | 40.3825 | 6.5294 | 9.2647 | 8.5294 | 7.5394 | 10.7942 | 12.7942 | 9.2647 | 16.8042 | 27.5983 | 40.3925 | 0.01
8.7496 | 10.3748 | 10.7496 | 9.7496 | 14.1244 | 16.1244 | 10.3748 | 20.1244 | 34.2488 | 50.3732 | 8.7496 | 10.3748 | 10.7496 | 9.7596 | 14.1244 | 16.1244 | 10.3748 | 20.1344 | 34.2588 | 50.3832 | 0.01
5.9569 | 8.9785 | 7.9569 | 6.9569 | 9.9354 | 11.9354 | 8.9785 | 15.9354 | 25.8708 | 37.8062 | 5.9569 | 8.9785 | 7.9569 | 6.9669 | 9.9354 | 11.9354 | 8.9785 | 15.9454 | 25.8808 | 37.8162 | 0.01
5.1926 | 8.5963 | 7.1926 | 6.1926 | 8.7889 | 10.7889 | 8.5963 | 14.7889 | 23.5777 | 34.3666 | 5.1926 | 8.5963 | 7.1926 | 6.2026 | 8.7889 | 10.7889 | 8.5963 | 14.7989 | 23.5877 | 34.3766 | 0.01
4.5049 | 8.2524 | 6.5049 | 5.5049 | 7.7573 | 9.7573 | 8.2524 | 13.7573 | 21.5146 | 31.272 | 4.5049 | 8.2524 | 6.5049 | 5.5149 | 7.7573 | 9.7573 | 8.2524 | 13.7673 | 21.5246 | 31.282 | 0.01
4.4453 | 8.2227 | 6.4453 | 5.4453 | 7.668 | 9.668 | 8.2227 | 13.668 | 21.336 | 31.004 | 4.4453 | 8.2227 | 6.4453 | 5.4553 | 7.668 | 9.668 | 8.2227 | 13.678 | 21.346 | 31.014 | 0.01
8.9107 | 10.4553 | 10.9107 | 9.9107 | 14.366 | 16.366 | 10.4553 | 20.366 | 34.7321 | 51.0981 | 8.9107 | 10.4553 | 10.9107 | 9.9207 | 14.366 | 16.366 | 10.4553 | 20.376 | 34.7421 | 51.1081 | 0.01
5.5784 | 8.7892 | 7.5784 | 6.5784 | 9.3676 | 11.3676 | 8.7892 | 15.3676 | 24.7351 | 36.1027 | 5.5784 | 8.7892 | 7.5784 | 6.5884 | 9.3676 | 11.3676 | 8.7892 | 15.3776 | 24.7451 | 36.1127 | 0.01
6.5968 | 9.2984 | 8.5968 | 7.5968 | 10.8952 | 12.8952 | 9.2984 | 16.8952 | 27.7903 | 40.6855 | 6.5968 | 9.2984 | 8.5968 | 7.6068 | 10.8952 | 12.8952 | 9.2984 | 16.9052 | 27.8003 | 40.6955 | 0.01
9.5841 | 10.7921 | 11.5841 | 10.5841 | 15.3762 | 17.3762 | 10.7921 | 21.3762 | 36.7524 | 54.1286 | 9.5841 | 10.7921 | 11.5841 | 10.5941 | 15.3762 | 17.3762 | 10.7921 | 21.3862 | 36.7624 | 54.1386 | 0.01
7.1421 | 9.5711 | 9.1421 | 8.1421 | 11.7132 | 13.7132 | 9.5711 | 17.7132 | 29.4264 | 43.1397 | 7.1421 | 9.5711 | 9.1421 | 8.1521 | 11.7132 | 13.7132 | 9.5711 | 17.7232 | 29.4364 | 43.1497 | 0.01
6.9164 | 9.4582 | 8.9164 | 7.9164 | 11.3746 | 13.3746 | 9.4582 | 17.3746 | 28.7492 | 42.1238 | 6.9164 | 9.4582 | 8.9164 | 7.9264 | 11.3746 | 13.3746 | 9.4582 | 17.3846 | 28.7592 | 42.1338 | 0.01
8.2153 | 10.1076 | 10.2153 | 9.2153 | 13.3229 | 15.3229 | 10.1076 | 19.3229 | 32.6459 | 47.9688 | 8.2153 | 10.1076 | 10.2153 | 9.2253 | 13.3229 | 15.3229 | 10.1076 | 19.3329 | 32.6559 | 47.9788 | 0.01
5.5263 | 8.7631 | 7.5263 | 6.5263 | 9.2894 | 11.2894 | 8.7631 | 15.2894 | 24.5789 | 35.8683 | 5.5263 | 8.7631 | 7.5263 | 6.5363 | 9.2894 | 11.2894 | 8.7631 | 15.2994 | 24.5889 | 35.8783 | 0.01
11.0337 | 11.5168 | 13.0337 | 12.0337 | 17.5505 | 19.5505 | 11.5168 | 23.5505 | 41.101 | 60.6514 | 11.0337 | 11.5168 | 13.0337 | 12.0437 | 17.5505 | 19.5505 | 11.5168 | 23.5605 | 41.111 | 60.6614 | 0.01
6.0016 | 9.0008 | 8.0016 | 7.0016 | 10.0024 | 12.0024 | 9.0008 | 16.0024 | 26.0048 | 38.0072 | 6.0016 | 9.0008 | 8.0016 | 7.0116 | 10.0024 | 12.0024 | 9.0008 | 16.0124 | 26.0148 | 38.0172 | 0.01
10.3738 | 11.1869 | 12.3738 | 11.3738 | 16.5607 | 18.5607 | 11.1869 | 22.5607 | 39.1215 | 57.6822 | 10.3738 | 11.1869 | 12.3738 | 11.3838 | 16.5607 | 18.5607 | 11.1869 | 22.5707 | 39.1315 | 57.6922 | 0.01
6.4121 | 9.206 | 8.4121 | 7.4121 | 10.6181 | 12.6181 | 9.206 | 16.6181 | 27.2363 | 39.8544 | 6.4121 | 9.206 | 8.4121 | 7.4221 | 10.6181 | 12.6181 | 9.206 | 16.6281 | 27.2463 | 39.8644 | 0.01
9.217 | 10.6085 | 11.217 | 10.217 | 14.8254 | 16.8254 | 10.6085 | 20.8254 | 35.6509 | 52.4763 | 9.217 | 10.6085 | 11.217 | 10.227 | 14.8254 | 16.8254 | 10.6085 | 20.8354 | 35.6609 | 52.4863 | 0.01
9.7797 | 10.8898 | 11.7797 | 10.7797 | 15.6695 | 17.6695 | 10.8898 | 21.6695 | 37.3391 | 55.0086 | 9.7797 | 10.8898 | 11.7797 | 10.7897 | 15.6695 | 17.6695 | 10.8898 | 21.6795 | 37.3491 | 55.0186 | 0.01
5.0423 | 8.5211 | 7.0423 | 6.0423 | 8.5634 | 10.5634 | 8.5211 | 14.5634 | 23.1268 | 33.6903 | 5.0423 | 8.5211 | 7.0423 | 6.0523 | 8.5634 | 10.5634 | 8.5211 | 14.5734 | 23.1368 | 33.7003 | 0.01
4.3481 | 8.174 | 6.3481 | 5.3481 | 7.5221 | 9.5221 | 8.174 | 13.5221 | 21.0442 | 30.5663 | 4.3481 | 8.174 | 6.3481 | 5.3581 | 7.5221 | 9.5221 | 8.174 | 13.5321 | 21.0542 | 30.5763 | 0.01
7.1758 | 9.5879 | 9.1758 | 8.1758 | 11.7637 | 13.7637 | 9.5879 | 17.7637 | 29.5274 | 43.2911 | 7.1758 | 9.5879 | 9.1758 | 8.1858 | 11.7637 | 13.7637 | 9.5879 | 17.7737 | 29.5374 | 43.3011 | 0.01
4.6681 | 8.3341 | 6.6681 | 5.6681 | 8.0022 | 10.0022 | 8.3341 | 14.0022 | 22.0043 | 32.0065 | 4.6681 | 8.3341 | 6.6681 | 5.6781 | 8.0022 | 10.0022 | 8.3341 | 14.0122 | 22.0143 | 32.0165 | 0.01
1.8921 | 6.946 | 3.8921 | 2.8921 | 3.8381 | 5.8381 | 6.946 | 9.8381 | 13.6762 | 19.5143 | 1.8921 | 6.946 | 3.8921 | 2.9021 | 3.8381 | 5.8381 | 6.946 | 9.8481 | 13.6862 | 19.5243 | 0.01
5.0109 | 8.5055 | 7.0109 | 6.0109 | 8.5164 | 10.5164 | 8.5055 | 14.5164 | 23.0328 | 33.5492 | 5.0109 | 8.5055 | 7.0109 | 6.0209 | 8.5164 | 10.5164 | 8.5055 | 14.5264 | 23.0428 | 33.5592 | 0.01
3.8584 | 7.9292 | 5.8584 | 4.8584 | 6.7875 | 8.7875 | 7.9292 | 12.7875 | 19.5751 | 28.3626 | 3.8584 | 7.9292 | 5.8584 | 4.8684 | 6.7875 | 8.7875 | 7.9292 | 12.7975 | 19.5851 | 28.3726 | 0.01
6.4966 | 9.2483 | 8.4966 | 7.4966 | 10.7448 | 12.7448 | 9.2483 | 16.7448 | 27.4897 | 40.2345 | 6.4966 | 9.2483 | 8.4966 | 7.5066 | 10.7448 | 12.7448 | 9.2483 | 16.7548 | 27.4997 | 40.2445 | 0.01
7.0352 | 9.5176 | 9.0352 | 8.0352 | 11.5527 | 13.5527 | 9.5176 | 17.5527 | 29.1055 | 42.6582 | 7.0352 | 9.5176 | 9.0352 | 8.0452 | 11.5527 | 13.5527 | 9.5176 | 17.5627 | 29.1155 | 42.6682 | 0.01
6.1885 | 9.0943 | 8.1885 | 7.1885 | 10.2828 | 12.2828 | 9.0943 | 16.2828 | 26.5656 | 38.8484 | 6.1885 | 9.0943 | 8.1885 | 7.1985 | 10.2828 | 12.2828 | 9.0943 | 16.2928 | 26.5756 | 38.8584 | 0.01
5.8998 | 8.9499 | 7.8998 | 6.8998 | 9.8497 | 11.8497 | 8.9499 | 15.8497 | 25.6995 | 37.5492 | 5.8998 | 8.9499 | 7.8998 | 6.9098 | 9.8497 | 11.8497 | 8.9499 | 15.8597 | 25.7095 | 37.5592 | 0.01
3.7522 | 7.8761 | 5.7522 | 4.7522 | 6.6283 | 8.6283 | 7.8761 | 12.6283 | 19.2566 | 27.8849 | 3.7522 | 7.8761 | 5.7522 | 4.7622 | 6.6283 | 8.6283 | 7.8761 | 12.6383 | 19.2666 | 27.8949 | 0.01
6.776 | 9.388 | 8.776 | 7.776 | 11.164 | 13.164 | 9.388 | 17.164 | 28.328 | 41.492 | 6.776 | 9.388 | 8.776 | 7.786 | 11.164 | 13.164 | 9.388 | 17.174 | 28.338 | 41.502 | 0.01
5.7807 | 8.8903 | 7.7807 | 6.7807 | 9.671 | 11.671 | 8.8903 | 15.671 | 25.3421 | 37.0131 | 5.7807 | 8.8903 | 7.7807 | 6.7907 | 9.671 | 11.671 | 8.8903 | 15.681 | 25.3521 | 37.0231 | 0.01
3.3449 | 7.6725 | 5.3449 | 4.3449 | 6.0174 | 8.0174 | 7.6725 | 12.0174 | 18.0348 | 26.0522 | 3.3449 | 7.6725 | 5.3449 | 4.3549 | 6.0174 | 8.0174 | 7.6725 | 12.0274 | 18.0448 | 26.0622 | 0.01
3.0968 | 7.5484 | 5.0968 | 4.0968 | 5.6452 | 7.6452 | 7.5484 | 11.6452 | 17.2904 | 24.9355 | 3.0968 | 7.5484 | 5.0968 | 4.1068 | 5.6452 | 7.6452 | 7.5484 | 11.6552 | 17.3004 | 24.9455 | 0.01
7.9137 | 9.9569 | 9.9137 | 8.9137 | 12.8706 | 14.8706 | 9.9569 | 18.8706 | 31.7412 | 46.6118 | 7.9137 | 9.9569 | 9.9137 | 8.9237 | 12.8706 | 14.8706 | 9.9569 | 18.8806 | 31.7512 | 46.6218 | 0.01
8.1265 | 10.0633 | 10.1265 | 9.1265 | 13.1898 | 15.1898 | 10.0633 | 19.1898 | 32.3795 | 47.5693 | 8.1265 | 10.0633 | 10.1265 | 9.1365 | 13.1898 | 15.1898 | 10.0633 | 19.1998 | 32.3895 | 47.5793 | 0.01
4.2244 | 8.1122 | 6.2244 | 5.2244 | 7.3366 | 9.3366 | 8.1122 | 13.3366 | 20.6732 | 30.0098 | 4.2244 | 8.1122 | 6.2244 | 5.2344 | 7.3366 | 9.3366 | 8.1122 | 13.3466 | 20.6832 | 30.0198 | 0.01
6.3537 | 9.1768 | 8.3537 | 7.3537 | 10.5305 | 12.5305 | 9.1768 | 16.5305 | 27.061 | 39.5914 | 6.3537 | 9.1768 | 8.3537 | 7.3637 | 10.5305 | 12.5305 | 9.1768 | 16.5405 | 27.071 | 39.6014 | 0.01
11.168 | 11.584 | 13.168 | 12.168 | 17.7521 | 19.7521 | 11.584 | 23.7521 | 41.5041 | 61.2562 | 11.168 | 11.584 | 13.168 | 12.178 | 17.7521 | 19.7521 | 11.584 | 23.7621 | 41.5141 | 61.2662 | 0.01
5.4518 | 8.7259 | 7.4518 | 6.4518 | 9.1778 | 11.1778 | 8.7259 | 15.1778 | 24.3555 | 35.5333 | 5.4518 | 8.7259 | 7.4518 | 6.4618 | 9.1778 | 11.1778 | 8.7259 | 15.1878 | 24.3655 | 35.5433 | 0.01
6.0492 | 9.0246 | 8.0492 | 7.0492 | 10.0738 | 12.0738 | 9.0246 | 16.0738 | 26.1476 | 38.2214 | 6.0492 | 9.0246 | 8.0492 | 7.0592 | 10.0738 | 12.0738 | 9.0246 | 16.0838 | 26.1576 | 38.2314 | 0.01
7.4105 | 9.7052 | 9.4105 | 8.4105 | 12.1157 | 14.1157 | 9.7052 | 18.1157 | 30.2314 | 44.3471 | 7.4105 | 9.7052 | 9.4105 | 8.4205 | 12.1157 | 14.1157 | 9.7052 | 18.1257 | 30.2414 | 44.3571 | 0.01
3.5875 | 7.7938 | 5.5875 | 4.5875 | 6.3813 | 8.3813 | 7.7938 | 12.3813 | 18.7626 | 27.1439 | 3.5875 | 7.7938 | 5.5875 | 4.5975 | 6.3813 | 8.3813 | 7.7938 | 12.3913 | 18.7726 | 27.1539 | 0.01
5.9969 | 8.9984 | 7.9969 | 6.9969 | 9.9953 | 11.9953 | 8.9984 | 15.9953 | 25.9906 | 37.9859 | 5.9969 | 8.9984 | 7.9969 | 7.0069 | 9.9953 | 11.9953 | 8.9984 | 16.0053 | 26.0006 | 37.9959 | 0.01
4.4596 | 8.2298 | 6.4596 | 5.4596 | 7.6894 | 9.6894 | 8.2298 | 13.6894 | 21.3787 | 31.0681 | 4.4596 | 8.2298 | 6.4596 | 5.4696 | 7.6894 | 9.6894 | 8.2298 | 13.6994 | 21.3887 | 31.0781 | 0.01
4.6953 | 8.3477 | 6.6953 | 5.6953 | 8.043 | 10.043 | 8.3477 | 14.043 | 22.0859 | 32.1289 | 4.6953 | 8.3477 | 6.6953 | 5.7053 | 8.043 | 10.043 | 8.3477 | 14.053 | 22.0959 | 32.1389 | 0.01
6.2341 | 9.117 | 8.2341 | 7.2341 | 10.3511 | 12.3511 | 9.117 | 16.3511 | 26.7023 | 39.0534 | 6.2341 | 9.117 | 8.2341 | 7.2441 | 10.3511 | 12.3511 | 9.117 | 16.3611 | 26.7123 | 39.0634 | 0.01
10.223 | 11.1115 | 12.223 | 11.223 | 16.3345 | 18.3345 | 11.1115 | 22.3345 | 38.669 | 57.0034 | 10.223 | 11.1115 | 12.223 | 11.233 | 16.3345 | 18.3345 | 11.1115 | 22.3445 | 38.679 | 57.0134 | 0.01
7.3917 | 9.6958 | 9.3917 | 8.3917 | 12.0875 | 14.0875 | 9.6958 | 18.0875 | 30.1751 | 44.2626 | 7.3917 | 9.6958 | 9.3917 | 8.4017 | 12.0875 | 14.0875 | 9.6958 | 18.0975 | 30.1851 | 44.2726 | 0.01
7.055 | 9.5275 | 9.055 | 8.055 | 11.5825 | 13.5825 | 9.5275 | 17.5825 | 29.1649 | 42.7474 | 7.055 | 9.5275 | 9.055 | 8.065 | 11.5825 | 13.5825 | 9.5275 | 17.5925 | 29.1749 | 42.7574 | 0.01
2.1916 | 7.0958 | 4.1916 | 3.1916 | 4.2875 | 6.2875 | 7.0958 | 10.2875 | 14.5749 | 20.8624 | 2.1916 | 7.0958 | 4.1916 | 3.2016 | 4.2875 | 6.2875 | 7.0958 | 10.2975 | 14.5849 | 20.8724 | 0.01
4.1961 | 8.098 | 6.1961 | 5.1961 | 7.2941 | 9.2941 | 8.098 | 13.2941 | 20.5882 | 29.8823 | 4.1961 | 8.098 | 6.1961 | 5.2061 | 7.2941 | 9.2941 | 8.098 | 13.3041 | 20.5982 | 29.8923 | 0.01
9.3012 | 10.6506 | 11.3012 | 10.3012 | 14.9518 | 16.9518 | 10.6506 | 20.9518 | 35.9036 | 52.8554 | 9.3012 | 10.6506 | 11.3012 | 10.3112 | 14.9518 | 16.9518 | 10.6506 | 20.9618 | 35.9136 | 52.8654 | 0.01
6.1032 | 9.0516 | 8.1032 | 7.1032 | 10.1549 | 12.1549 | 9.0516 | 16.1549 | 26.3097 | 38.4646 | 6.1032 | 9.0516 | 8.1032 | 7.1132 | 10.1549 | 12.1549 | 9.0516 | 16.1649 | 26.3197 | 38.4746 | 0.01
10.9776 | 11.4888 | 12.9776 | 11.9776 | 17.4663 | 19.4663 | 11.4888 | 23.4663 | 40.9327 | 60.399 | 10.9776 | 11.4888 | 12.9776 | 11.9876 | 17.4663 | 19.4663 | 11.4888 | 23.4763 | 40.9427 | 60.409 | 0.01
3.8066 | 7.9033 | 5.8066 | 4.8066 | 6.7099 | 8.7099 | 7.9033 | 12.7099 | 19.4198 | 28.1297 | 3.8066 | 7.9033 | 5.8066 | 4.8166 | 6.7099 | 8.7099 | 7.9033 | 12.7199 | 19.4298 | 28.1397 | 0.01
4.2458 | 8.1229 | 6.2458 | 5.2458 | 7.3688 | 9.3688 | 8.1229 | 13.3688 | 20.7375 | 30.1063 | 4.2458 | 8.1229 | 6.2458 | 5.2558 | 7.3688 | 9.3688 | 8.1229 | 13.3788 | 20.7475 | 30.1163 | 0.01
6.4005 | 9.2003 | 8.4005 | 7.4005 | 10.6008 | 12.6008 | 9.2003 | 16.6008 | 27.2016 | 39.8024 | 6.4005 | 9.2003 | 8.4005 | 7.4105 | 10.6008 | 12.6008 | 9.2003 | 16.6108 | 27.2116 | 39.8124 | 0.01
4.7583 | 8.3791 | 6.7583 | 5.7583 | 8.1374 | 10.1374 | 8.3791 | 14.1374 | 22.2748 | 32.4122 | 4.7583 | 8.3791 | 6.7583 | 5.7683 | 8.1374 | 10.1374 | 8.3791 | 14.1474 | 22.2848 | 32.4222 | 0.01
6.5861 | 9.293 | 8.5861 | 7.5861 | 10.8791 | 12.8791 | 9.293 | 16.8791 | 27.7582 | 40.6373 | 6.5861 | 9.293 | 8.5861 | 7.5961 | 10.8791 | 12.8791 | 9.293 | 16.8891 | 27.7682 | 40.6473 | 0.01
8.5851 | 10.2925 | 10.5851 | 9.5851 | 13.8776 | 15.8776 | 10.2925 | 19.8776 | 33.7552 | 49.6328 | 8.5851 | 10.2925 | 10.5851 | 9.5951 | 13.8776 | 15.8776 | 10.2925 | 19.8876 | 33.7652 | 49.6428 | 0.01
8.0992 | 10.0496 | 10.0992 | 9.0992 | 13.1489 | 15.1489 | 10.0496 | 19.1489 | 32.2977 | 47.4466 | 8.0992 | 10.0496 | 10.0992 | 9.1092 | 13.1489 | 15.1489 | 10.0496 | 19.1589 | 32.3077 | 47.4566 | 0.01
6.8226 | 9.4113 | 8.8226 | 7.8226 | 11.2338 | 13.2338 | 9.4113 | 17.2338 | 28.4677 | 41.7015 | 6.8226 | 9.4113 | 8.8226 | 7.8326 | 11.2338 | 13.2338 | 9.4113 | 17.2438 | 28.4777 | 41.7115 | 0.01
5.9018 | 8.9509 | 7.9018 | 6.9018 | 9.8527 | 11.8527 | 8.9509 | 15.8527 | 25.7054 | 37.5582 | 5.9018 | 8.9509 | 7.9018 | 6.9118 | 9.8527 | 11.8527 | 8.9509 | 15.8627 | 25.7154 | 37.5682 | 0.01
3.8038 | 7.9019 | 5.8038 | 4.8038 | 6.7057 | 8.7057 | 7.9019 | 12.7057 | 19.4114 | 28.1172 | 3.8038 | 7.9019 | 5.8038 | 4.8138 | 6.7057 | 8.7057 | 7.9019 | 12.7157 | 19.4214 | 28.1272 | 0.01
7.6562 | 9.8281 | 9.6562 | 8.6562 | 12.4843 | 14.4843 | 9.8281 | 18.4843 | 30.9687 | 45.453 | 7.6562 | 9.8281 | 9.6562 | 8.6662 | 12.4843 | 14.4843 | 9.8281 | 18.4943 | 30.9787 | 45.463 | 0.01
5.9438 | 8.9719 | 7.9438 | 6.9438 | 9.9156 | 11.9156 | 8.9719 | 15.9156 | 25.8313 | 37.7469 | 5.9438 | 8.9719 | 7.9438 | 6.9538 | 9.9156 | 11.9156 | 8.9719 | 15.9256 | 25.8413 | 37.7569 | 0.01
4.5206 | 8.2603 | 6.5206 | 5.5206 | 7.7809 | 9.7809 | 8.2603 | 13.7809 | 21.5618 | 31.3428 | 4.5206 | 8.2603 | 6.5206 | 5.5306 | 7.7809 | 9.7809 | 8.2603 | 13.7909 | 21.5718 | 31.3528 | 0.01
6.1925 | 9.0963 | 8.1925 | 7.1925 | 10.2888 | 12.2888 | 9.0963 | 16.2888 | 26.5776 | 38.8664 | 6.1925 | 9.0963 | 8.1925 | 7.2025 | 10.2888 | 12.2888 | 9.0963 | 16.2988 | 26.5876 | 38.8764 | 0.01
6.2748 | 9.1374 | 8.2748 | 7.2748 | 10.4122 | 12.4122 | 9.1374 | 16.4122 | 26.8244 | 39.2366 | 6.2748 | 9.1374 | 8.2748 | 7.2848 | 10.4122 | 12.4122 | 9.1374 | 16.4222 | 26.8344 | 39.2466 | 0.01
6.3519 | 9.176 | 8.3519 | 7.3519 | 10.5279 | 12.5279 | 9.176 | 16.5279 | 27.0558 | 39.5837 | 6.3519 | 9.176 | 8.3519 | 7.3619 | 10.5279 | 12.5279 | 9.176 | 16.5379 | 27.0658 | 39.5937 | 0.01
4.0229 | 8.0115 | 6.0229 | 5.0229 | 7.0344 | 9.0344 | 8.0115 | 13.0344 | 20.0687 | 29.1031 | 4.0229 | 8.0115 | 6.0229 | 5.0329 | 7.0344 | 9.0344 | 8.0115 | 13.0444 | 20.0787 | 29.1131 | 0.01
5.9303 | 8.9651 | 7.9303 | 6.9303 | 9.8954 | 11.8954 | 8.9651 | 15.8954 | 25.7909 | 37.6863 | 5.9303 | 8.9651 | 7.9303 | 6.9403 | 9.8954 | 11.8954 | 8.9651 | 15.9054 | 25.8009 | 37.6963 | 0.01
6.936 | 9.468 | 8.936 | 7.936 | 11.404 | 13.404 | 9.468 | 17.404 | 28.808 | 42.2119 | 6.936 | 9.468 | 8.936 | 7.946 | 11.404 | 13.404 | 9.468 | 17.414 | 28.818 | 42.2219 | 0.01
7.0226 | 9.5113 | 9.0226 | 8.0226 | 11.5339 | 13.5339 | 9.5113 | 17.5339 | 29.0677 | 42.6016 | 7.0226 | 9.5113 | 9.0226 | 8.0326 | 11.5339 | 13.5339 | 9.5113 | 17.5439 | 29.0777 | 42.6116 | 0.01
2.7903 | 7.3951 | 4.7903 | 3.7903 | 5.1854 | 7.1854 | 7.3951 | 11.1854 | 16.3708 | 23.5562 | 2.7903 | 7.3951 | 4.7903 | 3.8003 | 5.1854 | 7.1854 | 7.3951 | 11.1954 | 16.3808 | 23.5662 | 0.01
6.8957 | 9.4479 | 8.8957 | 7.8957 | 11.3436 | 13.3436 | 9.4479 | 17.3436 | 28.6871 | 42.0307 | 6.8957 | 9.4479 | 8.8957 | 7.9057 | 11.3436 | 13.3436 | 9.4479 | 17.3536 | 28.6971 | 42.0407 | 0.01
6.0138 | 9.0069 | 8.0138 | 7.0138 | 10.0208 | 12.0208 | 9.0069 | 16.0208 | 26.0415 | 38.0623 | 6.0138 | 9.0069 | 8.0138 | 7.0238 | 10.0208 | 12.0208 | 9.0069 | 16.0308 | 26.0515 | 38.0723 | 0.01
3.8657 | 7.9328 | 5.8657 | 4.8657 | 6.7985 | 8.7985 | 7.9328 | 12.7985 | 19.597 | 28.3955 | 3.8657 | 7.9328 | 5.8657 | 4.8757 | 6.7985 | 8.7985 | 7.9328 | 12.8085 | 19.607 | 28.4055 | 0.01
7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 7.4889 | 9.7444 | 9.4889 | 8.4989 | 12.2333 | 14.2333 | 9.7444 | 18.2433 | 30.4766 | 44.7098 | 0.01
8.8202 | 10.4101 | 10.8202 | 9.8202 | 14.2303 | 16.2303 | 10.4101 | 20.2303 | 34.4605 | 50.6908 | 8.8202 | 10.4101 | 10.8202 | 9.8302 | 14.2303 | 16.2303 | 10.4101 | 20.2403 | 34.4705 | 50.7008 | 0.01
7.8196 | 9.9098 | 9.8196 | 8.8196 | 12.7294 | 14.7294 | 9.9098 | 18.7294 | 31.4588 | 46.1882 | 7.8196 | 9.9098 | 9.8196 | 8.8296 | 12.7294 | 14.7294 | 9.9098 | 18.7394 | 31.4688 | 46.1982 | 0.01
4.576 | 8.288 | 6.576 | 5.576 | 7.864 | 9.864 | 8.288 | 13.864 | 21.7279 | 31.5919 | 4.576 | 8.288 | 6.576 | 5.586 | 7.864 | 9.864 | 8.288 | 13.874 | 21.7379 | 31.6019 | 0.01
7.0266 | 9.5133 | 9.0266 | 8.0266 | 11.5399 | 13.5399 | 9.5133 | 17.5399 | 29.0798 | 42.6196 | 7.0266 | 9.5133 | 9.0266 | 8.0366 | 11.5399 | 13.5399 | 9.5133 | 17.5499 | 29.0898 | 42.6296 | 0.01
6.0145 | 9.0072 | 8.0145 | 7.0145 | 10.0217 | 12.0217 | 9.0072 | 16.0217 | 26.0434 | 38.0651 | 6.0145 | 9.0072 | 8.0145 | 7.0245 | 10.0217 | 12.0217 | 9.0072 | 16.0317 | 26.0534 | 38.0751 | 0.01
2.6438 | 7.3219 | 4.6438 | 3.6438 | 4.9657 | 6.9657 | 7.3219 | 10.9657 | 15.9313 | 22.897 | 2.6438 | 7.3219 | 4.6438 | 3.6538 | 4.9657 | 6.9657 | 7.3219 | 10.9757 | 15.9413 | 22.907 | 0.01
6.0348 | 9.0174 | 8.0348 | 7.0348 | 10.0522 | 12.0522 | 9.0174 | 16.0522 | 26.1044 | 38.1566 | 6.0348 | 9.0174 | 8.0348 | 7.0448 | 10.0522 | 12.0522 | 9.0174 | 16.0622 | 26.1144 | 38.1666 | 0.01
5.4907 | 8.7453 | 7.4907 | 6.4907 | 9.236 | 11.236 | 8.7453 | 15.236 | 24.472 | 35.7079 | 5.4907 | 8.7453 | 7.4907 | 6.5007 | 9.236 | 11.236 | 8.7453 | 15.246 | 24.482 | 35.7179 | 0.01
7.3925 | 9.6962 | 9.3925 | 8.3925 | 12.0887 | 14.0887 | 9.6962 | 18.0887 | 30.1774 | 44.2661 | 7.3925 | 9.6962 | 9.3925 | 8.4025 | 12.0887 | 14.0887 | 9.6962 | 18.0987 | 30.1874 | 44.2761 | 0.01
6.0746 | 9.0373 | 8.0746 | 7.0746 | 10.1119 | 12.1119 | 9.0373 | 16.1119 | 26.2238 | 38.3357 | 6.0746 | 9.0373 | 8.0746 | 7.0846 | 10.1119 | 12.1119 | 9.0373 | 16.1219 | 26.2338 | 38.3457 | 0.01
5.7247 | 8.8624 | 7.7247 | 6.7247 | 9.5871 | 11.5871 | 8.8624 | 15.5871 | 25.1742 | 36.7613 | 5.7247 | 8.8624 | 7.7247 | 6.7347 | 9.5871 | 11.5871 | 8.8624 | 15.5971 | 25.1842 | 36.7713 | 0.01
5.7801 | 8.89 | 7.7801 | 6.7801 | 9.6701 | 11.6701 | 8.89 | 15.6701 | 25.3403 | 37.0104 | 5.7801 | 8.89 | 7.7801 | 6.7901 | 9.6701 | 11.6701 | 8.89 | 15.6801 | 25.3503 | 37.0204 | 0.01
4.7764 | 8.3882 | 6.7764 | 5.7764 | 8.1646 | 10.1646 | 8.3882 | 14.1646 | 22.3292 | 32.4937 | 4.7764 | 8.3882 | 6.7764 | 5.7864 | 8.1646 | 10.1646 | 8.3882 | 14.1746 | 22.3392 | 32.5037 | 0.01
2.1447 | 7.0723 | 4.1447 | 3.1447 | 4.217 | 6.217 | 7.0723 | 10.217 | 14.434 | 20.6509 | 2.1447 | 7.0723 | 4.1447 | 3.1547 | 4.217 | 6.217 | 7.0723 | 10.227 | 14.444 | 20.6609 | 0.01
5.7028 | 8.8514 | 7.7028 | 6.7028 | 9.5542 | 11.5542 | 8.8514 | 15.5542 | 25.1084 | 36.6625 | 5.7028 | 8.8514 | 7.7028 | 6.7128 | 9.5542 | 11.5542 | 8.8514 | 15.5642 | 25.1184 | 36.6725 | 0.01
7.7214 | 9.8607 | 9.7214 | 8.7214 | 12.582 | 14.582 | 9.8607 | 18.582 | 31.1641 | 45.7461 | 7.7214 | 9.8607 | 9.7214 | 8.7314 | 12.582 | 14.582 | 9.8607 | 18.592 | 31.1741 | 45.7561 | 0.01
5.5976 | 8.7988 | 7.5976 | 6.5976 | 9.3964 | 11.3964 | 8.7988 | 15.3964 | 24.7928 | 36.1892 | 5.5976 | 8.7988 | 7.5976 | 6.6076 | 9.3964 | 11.3964 | 8.7988 | 15.4064 | 24.8028 | 36.1992 | 0.01
5.3389 | 8.6695 | 7.3389 | 6.3389 | 9.0084 | 11.0084 | 8.6695 | 15.0084 | 24.0167 | 35.0251 | 5.3389 | 8.6695 | 7.3389 | 6.3489 | 9.0084 | 11.0084 | 8.6695 | 15.0184 | 24.0267 | 35.0351 | 0.01
8.3081 | 10.154 | 10.3081 | 9.3081 | 13.4621 | 15.4621 | 10.154 | 19.4621 | 32.9243 | 48.3864 | 8.3081 | 10.154 | 10.3081 | 9.3181 | 13.4621 | 15.4621 | 10.154 | 19.4721 | 32.9343 | 48.3964 | 0.01
6.3383 | 9.1691 | 8.3383 | 7.3383 | 10.5074 | 12.5074 | 9.1691 | 16.5074 | 27.0148 | 39.5222 | 6.3383 | 9.1691 | 8.3383 | 7.3483 | 10.5074 | 12.5074 | 9.1691 | 16.5174 | 27.0248 | 39.5322 | 0.01
6.2356 | 9.1178 | 8.2356 | 7.2356 | 10.3534 | 12.3534 | 9.1178 | 16.3534 | 26.7069 | 39.0603 | 6.2356 | 9.1178 | 8.2356 | 7.2456 | 10.3534 | 12.3534 | 9.1178 | 16.3634 | 26.7169 | 39.0703 | 0.01
8.8103 | 10.4051 | 10.8103 | 9.8103 | 14.2154 | 16.2154 | 10.4051 | 20.2154 | 34.4309 | 50.6463 | 8.8103 | 10.4051 | 10.8103 | 9.8203 | 14.2154 | 16.2154 | 10.4051 | 20.2254 | 34.4409 | 50.6563 | 0.01
9.1328 | 10.5664 | 11.1328 | 10.1328 | 14.6992 | 16.6992 | 10.5664 | 20.6992 | 35.3985 | 52.0977 | 9.1328 | 10.5664 | 11.1328 | 10.1428 | 14.6992 | 16.6992 | 10.5664 | 20.7092 | 35.4085 | 52.1077 | 0.01
7.1789 | 9.5895 | 9.1789 | 8.1789 | 11.7684 | 13.7684 | 9.5895 | 17.7684 | 29.5367 | 43.3051 | 7.1789 | 9.5895 | 9.1789 | 8.1889 | 11.7684 | 13.7684 | 9.5895 | 17.7784 | 29.5467 | 43.3151 | 0.01
6.2187 | 9.1093 | 8.2187 | 7.2187 | 10.328 | 12.328 | 9.1093 | 16.328 | 26.6561 | 38.9841 | 6.2187 | 9.1093 | 8.2187 | 7.2287 | 10.328 | 12.328 | 9.1093 | 16.338 | 26.6661 | 38.9941 | 0.01
10.8017 | 11.4008 | 12.8017 | 11.8017 | 17.2025 | 19.2025 | 11.4008 | 23.2025 | 40.405 | 59.6075 | 10.8017 | 11.4008 | 12.8017 | 11.8117 | 17.2025 | 19.2025 | 11.4008 | 23.2125 | 40.415 | 59.6175 | 0.01
4.3082 | 8.1541 | 6.3082 | 5.3082 | 7.4622 | 9.4622 | 8.1541 | 13.4622 | 20.9245 | 30.3867 | 4.3082 | 8.1541 | 6.3082 | 5.3182 | 7.4622 | 9.4622 | 8.1541 | 13.4722 | 20.9345 | 30.3967 | 0.01
6.2847 | 9.1423 | 8.2847 | 7.2847 | 10.427 | 12.427 | 9.1423 | 16.427 | 26.8541 | 39.2811 | 6.2847 | 9.1423 | 8.2847 | 7.2947 | 10.427 | 12.427 | 9.1423 | 16.437 | 26.8641 | 39.2911 | 0.01
3.8754 | 7.9377 | 5.8754 | 4.8754 | 6.8131 | 8.8131 | 7.9377 | 12.8131 | 19.6261 | 28.4392 | 3.8754 | 7.9377 | 5.8754 | 4.8854 | 6.8131 | 8.8131 | 7.9377 | 12.8231 | 19.6361 | 28.4492 | 0.01
3.5216 | 7.7608 | 5.5216 | 4.5216 | 6.2824 | 8.2824 | 7.7608 | 12.2824 | 18.5649 | 26.8473 | 3.5216 | 7.7608 | 5.5216 | 4.5316 | 6.2824 | 8.2824 | 7.7608 | 12.2924 | 18.5749 | 26.8573 | 0.01
5.5633 | 8.7817 | 7.5633 | 6.5633 | 9.345 | 11.345 | 8.7817 | 15.345 | 24.69 | 36.0351 | 5.5633 | 8.7817 | 7.5633 | 6.5733 | 9.345 | 11.345 | 8.7817 | 15.355 | 24.7 | 36.0451 | 0.01
4.8463 | 8.4232 | 6.8463 | 5.8463 | 8.2695 | 10.2695 | 8.4232 | 14.2695 | 22.5389 | 32.8084 | 4.8463 | 8.4232 | 6.8463 | 5.8563 | 8.2695 | 10.2695 | 8.4232 | 14.2795 | 22.5489 | 32.8184 | 0.01
6.9828 | 9.4914 | 8.9828 | 7.9828 | 11.4743 | 13.4743 | 9.4914 | 17.4743 | 28.9485 | 42.4228 | 6.9828 | 9.4914 | 8.9828 | 7.9928 | 11.4743 | 13.4743 | 9.4914 | 17.4843 | 28.9585 | 42.4328 | 0.01
7.8476 | 9.9238 | 9.8476 | 8.8476 | 12.7713 | 14.7713 | 9.9238 | 18.7713 | 31.5427 | 46.314 | 7.8476 | 9.9238 | 9.8476 | 8.8576 | 12.7713 | 14.7713 | 9.9238 | 18.7813 | 31.5527 | 46.324 | 0.01
7.0345 | 9.5172 | 9.0345 | 8.0345 | 11.5517 | 13.5517 | 9.5172 | 17.5517 | 29.1034 | 42.655 | 7.0345 | 9.5172 | 9.0345 | 8.0445 | 11.5517 | 13.5517 | 9.5172 | 17.5617 | 29.1134 | 42.665 | 0.01
7.2596 | 9.6298 | 9.2596 | 8.2596 | 11.8894 | 13.8894 | 9.6298 | 17.8894 | 29.7788 | 43.6682 | 7.2596 | 9.6298 | 9.2596 | 8.2696 | 11.8894 | 13.8894 | 9.6298 | 17.8994 | 29.7888 | 43.6782 | 0.01
6.762 | 9.381 | 8.762 | 7.762 | 11.143 | 13.143 | 9.381 | 17.143 | 28.286 | 41.4289 | 6.762 | 9.381 | 8.762 | 7.772 | 11.143 | 13.143 | 9.381 | 17.153 | 28.296 | 41.4389 | 0.01
4.7843 | 8.3922 | 6.7843 | 5.7843 | 8.1765 | 10.1765 | 8.3922 | 14.1765 | 22.3529 | 32.5294 | 4.7843 | 8.3922 | 6.7843 | 5.7943 | 8.1765 | 10.1765 | 8.3922 | 14.1865 | 22.3629 | 32.5394 | 0.01
5.9404 | 8.9702 | 7.9404 | 6.9404 | 9.9106 | 11.9106 | 8.9702 | 15.9106 | 25.8212 | 37.7318 | 5.9404 | 8.9702 | 7.9404 | 6.9504 | 9.9106 | 11.9106 | 8.9702 | 15.9206 | 25.8312 | 37.7418 | 0.01
6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 6.3314 | 9.1657 | 8.3314 | 7.3414 | 10.4972 | 12.4972 | 9.1657 | 16.5072 | 27.0043 | 39.5015 | 0.01
7.0135 | 9.5068 | 9.0135 | 8.0135 | 11.5203 | 13.5203 | 9.5068 | 17.5203 | 29.0406 | 42.5608 | 7.0135 | 9.5068 | 9.0135 | 8.0235 | 11.5203 | 13.5203 | 9.5068 | 17.5303 | 29.0506 | 42.5708 | 0.01
3.4265 | 7.7133 | 5.4265 | 4.4265 | 6.1398 | 8.1398 | 7.7133 | 12.1398 | 18.2796 | 26.4194 | 3.4265 | 7.7133 | 5.4265 | 4.4365 | 6.1398 | 8.1398 | 7.7133 | 12.1498 | 18.2896 | 26.4294 | 0.01
5.4813 | 8.7407 | 7.4813 | 6.4813 | 9.222 | 11.222 | 8.7407 | 15.222 | 24.444 | 35.6659 | 5.4813 | 8.7407 | 7.4813 | 6.4913 | 9.222 | 11.222 | 8.7407 | 15.232 | 24.454 | 35.6759 | 0.01
7.7681 | 9.8841 | 9.7681 | 8.7681 | 12.6522 | 14.6522 | 9.8841 | 18.6522 | 31.3044 | 45.9566 | 7.7681 | 9.8841 | 9.7681 | 8.7781 | 12.6522 | 14.6522 | 9.8841 | 18.6622 | 31.3144 | 45.9666 | 0.01
6.4122 | 9.2061 | 8.4122 | 7.4122 | 10.6184 | 12.6184 | 9.2061 | 16.6184 | 27.2367 | 39.8551 | 6.4122 | 9.2061 | 8.4122 | 7.4222 | 10.6184 | 12.6184 | 9.2061 | 16.6284 | 27.2467 | 39.8651 | 0.01
8.7219 | 10.361 | 10.7219 | 9.7219 | 14.0829 | 16.0829 | 10.361 | 20.0829 | 34.1657 | 50.2486 | 8.7219 | 10.361 | 10.7219 | 9.7319 | 14.0829 | 16.0829 | 10.361 | 20.0929 | 34.1757 | 50.2586 | 0.01
5.8098 | 8.9049 | 7.8098 | 6.8098 | 9.7147 | 11.7147 | 8.9049 | 15.7147 | 25.4293 | 37.144 | 5.8098 | 8.9049 | 7.8098 | 6.8198 | 9.7147 | 11.7147 | 8.9049 | 15.7247 | 25.4393 | 37.154 | 0.01
4.8329 | 8.4165 | 6.8329 | 5.8329 | 8.2494 | 10.2494 | 8.4165 | 14.2494 | 22.4987 | 32.7481 | 4.8329 | 8.4165 | 6.8329 | 5.8429 | 8.2494 | 10.2494 | 8.4165 | 14.2594 | 22.5087 | 32.7581 | 0.01
6.7605 | 9.3803 | 8.7605 | 7.7605 | 11.1408 | 13.1408 | 9.3803 | 17.1408 | 28.2815 | 41.4223 | 6.7605 | 9.3803 | 8.7605 | 7.7705 | 11.1408 | 13.1408 | 9.3803 | 17.1508 | 28.2915 | 41.4323 | 0.01
9.047 | 10.5235 | 11.047 | 10.047 | 14.5706 | 16.5706 | 10.5235 | 20.5706 | 35.1411 | 51.7117 | 9.047 | 10.5235 | 11.047 | 10.057 | 14.5706 | 16.5706 | 10.5235 | 20.5806 | 35.1511 | 51.7217 | 0.01
7.8454 | 9.9227 | 9.8454 | 8.8454 | 12.7682 | 14.7682 | 9.9227 | 18.7682 | 31.5363 | 46.3045 | 7.8454 | 9.9227 | 9.8454 | 8.8554 | 12.7682 | 14.7682 | 9.9227 | 18.7782 | 31.5463 | 46.3145 | 0.01
6.6496 | 9.3248 | 8.6496 | 7.6496 | 10.9744 | 12.9744 | 9.3248 | 16.9744 | 27.9489 | 40.9233 | 6.6496 | 9.3248 | 8.6496 | 7.6596 | 10.9744 | 12.9744 | 9.3248 | 16.9844 | 27.9589 | 40.9333 | 0.01
4.2135 | 8.1067 | 6.2135 | 5.2135 | 7.3202 | 9.3202 | 8.1067 | 13.3202 | 20.6404 | 29.9606 | 4.2135 | 8.1067 | 6.2135 | 5.2235 | 7.3202 | 9.3202 | 8.1067 | 13.3302 | 20.6504 | 29.9706 | 0.01
11.6293 | 11.8146 | 13.6293 | 12.6293 | 18.4439 | 20.4439 | 11.8146 | 24.4439 | 42.8878 | 63.3317 | 11.6293 | 11.8146 | 13.6293 | 12.6393 | 18.4439 | 20.4439 | 11.8146 | 24.4539 | 42.8978 | 63.3417 | 0.01
5.3138 | 8.6569 | 7.3138 | 6.3138 | 8.9707 | 10.9707 | 8.6569 | 14.9707 | 23.9414 | 34.9122 | 5.3138 | 8.6569 | 7.3138 | 6.3238 | 8.9707 | 10.9707 | 8.6569 | 14.9807 | 23.9514 | 34.9222 | 0.01
6.2814 | 9.1407 | 8.2814 | 7.2814 | 10.4222 | 12.4222 | 9.1407 | 16.4222 | 26.8443 | 39.2665 | 6.2814 | 9.1407 | 8.2814 | 7.2914 | 10.4222 | 12.4222 | 9.1407 | 16.4322 | 26.8543 | 39.2765 | 0.01
5.935 | 8.9675 | 7.935 | 6.935 | 9.9026 | 11.9026 | 8.9675 | 15.9026 | 25.8051 | 37.7077 | 5.935 | 8.9675 | 7.935 | 6.945 | 9.9026 | 11.9026 | 8.9675 | 15.9126 | 25.8151 | 37.7177 | 0.01
6.1508 | 9.0754 | 8.1508 | 7.1508 | 10.2262 | 12.2262 | 9.0754 | 16.2262 | 26.4523 | 38.6785 | 6.1508 | 9.0754 | 8.1508 | 7.1608 | 10.2262 | 12.2262 | 9.0754 | 16.2362 | 26.4623 | 38.6885 | 0.01
5.3276 | 8.6638 | 7.3276 | 6.3276 | 8.9914 | 10.9914 | 8.6638 | 14.9914 | 23.9828 | 34.9742 | 5.3276 | 8.6638 | 7.3276 | 6.3376 | 8.9914 | 10.9914 | 8.6638 | 15.0014 | 23.9928 | 34.9842 | 0.01
2.0185 | 7.0093 | 4.0185 | 3.0185 | 4.0278 | 6.0278 | 7.0093 | 10.0278 | 14.0556 | 20.0834 | 2.0185 | 7.0093 | 4.0185 | 3.0285 | 4.0278 | 6.0278 | 7.0093 | 10.0378 | 14.0656 | 20.0934 | 0.01
7.9373 | 9.9687 | 9.9373 | 8.9373 | 12.906 | 14.906 | 9.9687 | 18.906 | 31.812 | 46.718 | 7.9373 | 9.9687 | 9.9373 | 8.9473 | 12.906 | 14.906 | 9.9687 | 18.916 | 31.822 | 46.728 | 0.01
7.1858 | 9.5929 | 9.1858 | 8.1858 | 11.7787 | 13.7787 | 9.5929 | 17.7787 | 29.5575 | 43.3362 | 7.1858 | 9.5929 | 9.1858 | 8.1958 | 11.7787 | 13.7787 | 9.5929 | 17.7887 | 29.5675 | 43.3462 | 0.01
6.7905 | 9.3953 | 8.7905 | 7.7905 | 11.1858 | 13.1858 | 9.3953 | 17.1858 | 28.3716 | 41.5574 | 6.7905 | 9.3953 | 8.7905 | 7.8005 | 11.1858 | 13.1858 | 9.3953 | 17.1958 | 28.3816 | 41.5674 | 0.01
8.3321 | 10.166 | 10.3321 | 9.3321 | 13.4981 | 15.4981 | 10.166 | 19.4981 | 32.9962 | 48.4944 | 8.3321 | 10.166 | 10.3321 | 9.3421 | 13.4981 | 15.4981 | 10.166 | 19.5081 | 33.0062 | 48.5044 | 0.01
4.4306 | 8.2153 | 6.4306 | 5.4306 | 7.6459 | 9.6459 | 8.2153 | 13.6459 | 21.2918 | 30.9377 | 4.4306 | 8.2153 | 6.4306 | 5.4406 | 7.6459 | 9.6459 | 8.2153 | 13.6559 | 21.3018 | 30.9477 | 0.01
5.963 | 8.9815 | 7.963 | 6.963 | 9.9446 | 11.9446 | 8.9815 | 15.9446 | 25.8891 | 37.8337 | 5.963 | 8.9815 | 7.963 | 6.973 | 9.9446 | 11.9446 | 8.9815 | 15.9546 | 25.8991 | 37.8437 | 0.01
5.0349 | 8.5174 | 7.0349 | 6.0349 | 8.5523 | 10.5523 | 8.5174 | 14.5523 | 23.1047 | 33.657 | 5.0349 | 8.5174 | 7.0349 | 6.0449 | 8.5523 | 10.5523 | 8.5174 | 14.5623 | 23.1147 | 33.667 | 0.01
7.8813 | 9.9407 | 9.8813 | 8.8813 | 12.822 | 14.822 | 9.9407 | 18.822 | 31.644 | 46.466 | 7.8813 | 9.9407 | 9.8813 | 8.8913 | 12.822 | 14.822 | 9.9407 | 18.832 | 31.654 | 46.476 | 0.01
2.9422 | 7.4711 | 4.9422 | 3.9422 | 5.4133 | 7.4133 | 7.4711 | 11.4133 | 16.8265 | 24.2398 | 2.9422 | 7.4711 | 4.9422 | 3.9522 | 5.4133 | 7.4133 | 7.4711 | 11.4233 | 16.8365 | 24.2498 | 0.01
5.5831 | 8.7915 | 7.5831 | 6.5831 | 9.3746 | 11.3746 | 8.7915 | 15.3746 | 24.7492 | 36.1238 | 5.5831 | 8.7915 | 7.5831 | 6.5931 | 9.3746 | 11.3746 | 8.7915 | 15.3846 | 24.7592 | 36.1338 | 0.01
6.1071 | 9.0535 | 8.1071 | 7.1071 | 10.1606 | 12.1606 | 9.0535 | 16.1606 | 26.3212 | 38.4818 | 6.1071 | 9.0535 | 8.1071 | 7.1171 | 10.1606 | 12.1606 | 9.0535 | 16.1706 | 26.3312 | 38.4918 | 0.01
3.7728 | 7.8864 | 5.7728 | 4.7728 | 6.6592 | 8.6592 | 7.8864 | 12.6592 | 19.3184 | 27.9776 | 3.7728 | 7.8864 | 5.7728 | 4.7828 | 6.6592 | 8.6592 | 7.8864 | 12.6692 | 19.3284 | 27.9876 | 0.01
7.4075 | 9.7038 | 9.4075 | 8.4075 | 12.1113 | 14.1113 | 9.7038 | 18.1113 | 30.2226 | 44.3338 | 7.4075 | 9.7038 | 9.4075 | 8.4175 | 12.1113 | 14.1113 | 9.7038 | 18.1213 | 30.2326 | 44.3438 | 0.01
4.9966 | 8.4983 | 6.9966 | 5.9966 | 8.4948 | 10.4948 | 8.4983 | 14.4948 | 22.9897 | 33.4845 | 4.9966 | 8.4983 | 6.9966 | 6.0066 | 8.4948 | 10.4948 | 8.4983 | 14.5048 | 22.9997 | 33.4945 | 0.01
5.7338 | 8.8669 | 7.7338 | 6.7338 | 9.6008 | 11.6008 | 8.8669 | 15.6008 | 25.2015 | 36.8023 | 5.7338 | 8.8669 | 7.7338 | 6.7438 | 9.6008 | 11.6008 | 8.8669 | 15.6108 | 25.2115 | 36.8123 | 0.01
9.5995 | 10.7997 | 11.5995 | 10.5995 | 15.3992 | 17.3992 | 10.7997 | 21.3992 | 36.7984 | 54.1977 | 9.5995 | 10.7997 | 11.5995 | 10.6095 | 15.3992 | 17.3992 | 10.7997 | 21.4092 | 36.8084 | 54.2077 | 0.01
4.5772 | 8.2886 | 6.5772 | 5.5772 | 7.8657 | 9.8657 | 8.2886 | 13.8657 | 21.7315 | 31.5972 | 4.5772 | 8.2886 | 6.5772 | 5.5872 | 7.8657 | 9.8657 | 8.2886 | 13.8757 | 21.7415 | 31.6072 | 0.01
6.272 | 9.136 | 8.272 | 7.272 | 10.408 | 12.408 | 9.136 | 16.408 | 26.8161 | 39.2241 | 6.272 | 9.136 | 8.272 | 7.282 | 10.408 | 12.408 | 9.136 | 16.418 | 26.8261 | 39.2341 | 0.01
8.0427 | 10.0214 | 10.0427 | 9.0427 | 13.0641 | 15.0641 | 10.0214 | 19.0641 | 32.1282 | 47.1924 | 8.0427 | 10.0214 | 10.0427 | 9.0527 | 13.0641 | 15.0641 | 10.0214 | 19.0741 | 32.1382 | 47.2024 | 0.01
7.5719 | 9.7859 | 9.5719 | 8.5719 | 12.3578 | 14.3578 | 9.7859 | 18.3578 | 30.7157 | 45.0735 | 7.5719 | 9.7859 | 9.5719 | 8.5819 | 12.3578 | 14.3578 | 9.7859 | 18.3678 | 30.7257 | 45.0835 | 0.01
5.6432 | 8.8216 | 7.6432 | 6.6432 | 9.4649 | 11.4649 | 8.8216 | 15.4649 | 24.9297 | 36.3946 | 5.6432 | 8.8216 | 7.6432 | 6.6532 | 9.4649 | 11.4649 | 8.8216 | 15.4749 | 24.9397 | 36.4046 | 0.01
8.7355 | 10.3677 | 10.7355 | 9.7355 | 14.1032 | 16.1032 | 10.3677 | 20.1032 | 34.2065 | 50.3097 | 8.7355 | 10.3677 | 10.7355 | 9.7455 | 14.1032 | 16.1032 | 10.3677 | 20.1132 | 34.2165 | 50.3197 | 0.01
5.0301 | 8.515 | 7.0301 | 6.0301 | 8.5451 | 10.5451 | 8.515 | 14.5451 | 23.0902 | 33.6354 | 5.0301 | 8.515 | 7.0301 | 6.0401 | 8.5451 | 10.5451 | 8.515 | 14.5551 | 23.1002 | 33.6454 | 0.01
7.0523 | 9.5262 | 9.0523 | 8.0523 | 11.5785 | 13.5785 | 9.5262 | 17.5785 | 29.157 | 42.7355 | 7.0523 | 9.5262 | 9.0523 | 8.0623 | 11.5785 | 13.5785 | 9.5262 | 17.5885 | 29.167 | 42.7455 | 0.01
7.9439 | 9.972 | 9.9439 | 8.9439 | 12.9159 | 14.9159 | 9.972 | 18.9159 | 31.8318 | 46.7478 | 7.9439 | 9.972 | 9.9439 | 8.9539 | 12.9159 | 14.9159 | 9.972 | 18.9259 | 31.8418 | 46.7578 | 0.01
8.5616 | 10.2808 | 10.5616 | 9.5616 | 13.8424 | 15.8424 | 10.2808 | 19.8424 | 33.6848 | 49.5272 | 8.5616 | 10.2808 | 10.5616 | 9.5716 | 13.8424 | 15.8424 | 10.2808 | 19.8524 | 33.6948 | 49.5372 | 0.01
7.3831 | 9.6916 | 9.3831 | 8.3831 | 12.0747 | 14.0747 | 9.6916 | 18.0747 | 30.1494 | 44.2241 | 7.3831 | 9.6916 | 9.3831 | 8.3931 | 12.0747 | 14.0747 | 9.6916 | 18.0847 | 30.1594 | 44.2341 | 0.01
4.1357 | 8.0679 | 6.1357 | 5.1357 | 7.2036 | 9.2036 | 8.0679 | 13.2036 | 20.4072 | 29.6108 | 4.1357 | 8.0679 | 6.1357 | 5.1457 | 7.2036 | 9.2036 | 8.0679 | 13.2136 | 20.4172 | 29.6208 | 0.01
2.1727 | 7.0864 | 4.1727 | 3.1727 | 4.2591 | 6.2591 | 7.0864 | 10.2591 | 14.5182 | 20.7772 | 2.1727 | 7.0864 | 4.1727 | 3.1827 | 4.2591 | 6.2591 | 7.0864 | 10.2691 | 14.5282 | 20.7872 | 0.01
5.5513 | 8.7756 | 7.5513 | 6.5513 | 9.3269 | 11.3269 | 8.7756 | 15.3269 | 24.6538 | 35.9807 | 5.5513 | 8.7756 | 7.5513 | 6.5613 | 9.3269 | 11.3269 | 8.7756 | 15.3369 | 24.6638 | 35.9907 | 0.01
3.49 | 7.745 | 5.49 | 4.49 | 6.235 | 8.235 | 7.745 | 12.235 | 18.47 | 26.705 | 3.49 | 7.745 | 5.49 | 4.5 | 6.235 | 8.235 | 7.745 | 12.245 | 18.48 | 26.715 | 0.01
0.33785 | 6.1689 | 2.3378 | 1.3378 | 1.5068 | 3.5068 | 6.1689 | 7.5068 | 9.0135 | 12.5203 | 0.33785 | 6.1689 | 2.3378 | 1.3478 | 1.5068 | 3.5068 | 6.1689 | 7.5168 | 9.0235 | 12.5303 | 0.01
5.2149 | 8.6075 | 7.2149 | 6.2149 | 8.8224 | 10.8224 | 8.6075 | 14.8224 | 23.6448 | 34.4672 | 5.2149 | 8.6075 | 7.2149 | 6.2249 | 8.8224 | 10.8224 | 8.6075 | 14.8324 | 23.6548 | 34.4772 | 0.01
7.5632 | 9.7816 | 9.5632 | 8.5632 | 12.3447 | 14.3447 | 9.7816 | 18.3447 | 30.6895 | 45.0342 | 7.5632 | 9.7816 | 9.5632 | 8.5732 | 12.3447 | 14.3447 | 9.7816 | 18.3547 | 30.6995 | 45.0442 | 0.01
7.7902 | 9.8951 | 9.7902 | 8.7902 | 12.6853 | 14.6853 | 9.8951 | 18.6853 | 31.3705 | 46.0558 | 7.7902 | 9.8951 | 9.7902 | 8.8002 | 12.6853 | 14.6853 | 9.8951 | 18.6953 | 31.3805 | 46.0658 | 0.01
9.4106 | 10.7053 | 11.4106 | 10.4106 | 15.1159 | 17.1159 | 10.7053 | 21.1159 | 36.2318 | 53.3477 | 9.4106 | 10.7053 | 11.4106 | 10.4206 | 15.1159 | 17.1159 | 10.7053 | 21.1259 | 36.2418 | 53.3577 | 0.01
6.338 | 9.169 | 8.338 | 7.338 | 10.5069 | 12.5069 | 9.169 | 16.5069 | 27.0139 | 39.5208 | 6.338 | 9.169 | 8.338 | 7.348 | 10.5069 | 12.5069 | 9.169 | 16.5169 | 27.0239 | 39.5308 | 0.01
8.4698 | 10.2349 | 10.4698 | 9.4698 | 13.7047 | 15.7047 | 10.2349 | 19.7047 | 33.4094 | 49.1142 | 8.4698 | 10.2349 | 10.4698 | 9.4798 | 13.7047 | 15.7047 | 10.2349 | 19.7147 | 33.4194 | 49.1242 | 0.01
3.966 | 7.983 | 5.966 | 4.966 | 6.949 | 8.949 | 7.983 | 12.949 | 19.898 | 28.847 | 3.966 | 7.983 | 5.966 | 4.976 | 6.949 | 8.949 | 7.983 | 12.959 | 19.908 | 28.857 | 0.01
2.0788 | 7.0394 | 4.0788 | 3.0788 | 4.1183 | 6.1183 | 7.0394 | 10.1183 | 14.2365 | 20.3548 | 2.0788 | 7.0394 | 4.0788 | 3.0888 | 4.1183 | 6.1183 | 7.0394 | 10.1283 | 14.2465 | 20.3648 | 0.01
7.9038 | 9.9519 | 9.9038 | 8.9038 | 12.8558 | 14.8558 | 9.9519 | 18.8558 | 31.7115 | 46.5673 | 7.9038 | 9.9519 | 9.9038 | 8.9138 | 12.8558 | 14.8558 | 9.9519 | 18.8658 | 31.7215 | 46.5773 | 0.01
5.9358 | 8.9679 | 7.9358 | 6.9358 | 9.9037 | 11.9037 | 8.9679 | 15.9037 | 25.8074 | 37.7111 | 5.9358 | 8.9679 | 7.9358 | 6.9458 | 9.9037 | 11.9037 | 8.9679 | 15.9137 | 25.8174 | 37.7211 | 0.01
8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 8.0477 | 10.0238 | 10.0477 | 9.0577 | 13.0715 | 15.0715 | 10.0238 | 19.0815 | 32.153 | 47.2244 | 0.01
6.657 | 9.3285 | 8.657 | 7.657 | 10.9856 | 12.9856 | 9.3285 | 16.9856 | 27.9711 | 40.9567 | 6.657 | 9.3285 | 8.657 | 7.667 | 10.9856 | 12.9856 | 9.3285 | 16.9956 | 27.9811 | 40.9667 | 0.01
6.5966 | 9.2983 | 8.5966 | 7.5966 | 10.8949 | 12.8949 | 9.2983 | 16.8949 | 27.7899 | 40.6848 | 6.5966 | 9.2983 | 8.5966 | 7.6066 | 10.8949 | 12.8949 | 9.2983 | 16.9049 | 27.7999 | 40.6948 | 0.01
5.4851 | 8.7426 | 7.4851 | 6.4851 | 9.2277 | 11.2277 | 8.7426 | 15.2277 | 24.4554 | 35.683 | 5.4851 | 8.7426 | 7.4851 | 6.4951 | 9.2277 | 11.2277 | 8.7426 | 15.2377 | 24.4654 | 35.693 | 0.01
3.0805 | 7.5402 | 5.0805 | 4.0805 | 5.6207 | 7.6207 | 7.5402 | 11.6207 | 17.2414 | 24.8621 | 3.0805 | 7.5402 | 5.0805 | 4.0905 | 5.6207 | 7.6207 | 7.5402 | 11.6307 | 17.2514 | 24.8721 | 0.01
7.2083 | 9.6042 | 9.2083 | 8.2083 | 11.8125 | 13.8125 | 9.6042 | 17.8125 | 29.625 | 43.4375 | 7.2083 | 9.6042 | 9.2083 | 8.2183 | 11.8125 | 13.8125 | 9.6042 | 17.8225 | 29.635 | 43.4475 | 0.01
2.7006 | 7.3503 | 4.7006 | 3.7006 | 5.0509 | 7.0509 | 7.3503 | 11.0509 | 16.1017 | 23.1526 | 2.7006 | 7.3503 | 4.7006 | 3.7106 | 5.0509 | 7.0509 | 7.3503 | 11.0609 | 16.1117 | 23.1626 | 0.01
7.4982 | 9.7491 | 9.4982 | 8.4982 | 12.2472 | 14.2472 | 9.7491 | 18.2472 | 30.4945 | 44.7417 | 7.4982 | 9.7491 | 9.4982 | 8.5082 | 12.2472 | 14.2472 | 9.7491 | 18.2572 | 30.5045 | 44.7517 | 0.01
5.3544 | 8.6772 | 7.3544 | 6.3544 | 9.0316 | 11.0316 | 8.6772 | 15.0316 | 24.0632 | 35.0948 | 5.3544 | 8.6772 | 7.3544 | 6.3644 | 9.0316 | 11.0316 | 8.6772 | 15.0416 | 24.0732 | 35.1048 | 0.01
4.5186 | 8.2593 | 6.5186 | 5.5186 | 7.7779 | 9.7779 | 8.2593 | 13.7779 | 21.5558 | 31.3337 | 4.5186 | 8.2593 | 6.5186 | 5.5286 | 7.7779 | 9.7779 | 8.2593 | 13.7879 | 21.5658 | 31.3437 | 0.01
4.8309 | 8.4155 | 6.8309 | 5.8309 | 8.2464 | 10.2464 | 8.4155 | 14.2464 | 22.4927 | 32.7391 | 4.8309 | 8.4155 | 6.8309 | 5.8409 | 8.2464 | 10.2464 | 8.4155 | 14.2564 | 22.5027 | 32.7491 | 0.01
1.1151 | 6.5575 | 3.1151 | 2.1151 | 2.6726 | 4.6726 | 6.5575 | 8.6726 | 11.3452 | 16.0178 | 1.1151 | 6.5575 | 3.1151 | 2.1251 | 2.6726 | 4.6726 | 6.5575 | 8.6826 | 11.3552 | 16.0278 | 0.01
5.9719 | 8.986 | 7.9719 | 6.9719 | 9.9579 | 11.9579 | 8.986 | 15.9579 | 25.9158 | 37.8737 | 5.9719 | 8.986 | 7.9719 | 6.9819 | 9.9579 | 11.9579 | 8.986 | 15.9679 | 25.9258 | 37.8837 | 0.01
6.5507 | 9.2754 | 8.5507 | 7.5507 | 10.8261 | 12.8261 | 9.2754 | 16.8261 | 27.6521 | 40.4782 | 6.5507 | 9.2754 | 8.5507 | 7.5607 | 10.8261 | 12.8261 | 9.2754 | 16.8361 | 27.6621 | 40.4882 | 0.01
4.8226 | 8.4113 | 6.8226 | 5.8226 | 8.2338 | 10.2338 | 8.4113 | 14.2338 | 22.4677 | 32.7015 | 4.8226 | 8.4113 | 6.8226 | 5.8326 | 8.2338 | 10.2338 | 8.4113 | 14.2438 | 22.4777 | 32.7115 | 0.01
6.1037 | 9.0519 | 8.1037 | 7.1037 | 10.1556 | 12.1556 | 9.0519 | 16.1556 | 26.3111 | 38.4667 | 6.1037 | 9.0519 | 8.1037 | 7.1137 | 10.1556 | 12.1556 | 9.0519 | 16.1656 | 26.3211 | 38.4767 | 0.01
6.9292 | 9.4646 | 8.9292 | 7.9292 | 11.3937 | 13.3937 | 9.4646 | 17.3937 | 28.7875 | 42.1812 | 6.9292 | 9.4646 | 8.9292 | 7.9392 | 11.3937 | 13.3937 | 9.4646 | 17.4037 | 28.7975 | 42.1912 | 0.01
3.7038 | 7.8519 | 5.7038 | 4.7038 | 6.5557 | 8.5557 | 7.8519 | 12.5557 | 19.1113 | 27.667 | 3.7038 | 7.8519 | 5.7038 | 4.7138 | 6.5557 | 8.5557 | 7.8519 | 12.5657 | 19.1213 | 27.677 | 0.01
7.5671 | 9.7836 | 9.5671 | 8.5671 | 12.3507 | 14.3507 | 9.7836 | 18.3507 | 30.7013 | 45.052 | 7.5671 | 9.7836 | 9.5671 | 8.5771 | 12.3507 | 14.3507 | 9.7836 | 18.3607 | 30.7113 | 45.062 | 0.01
2.3254 | 7.1627 | 4.3254 | 3.3254 | 4.4881 | 6.4881 | 7.1627 | 10.4881 | 14.9762 | 21.4642 | 2.3254 | 7.1627 | 4.3254 | 3.3354 | 4.4881 | 6.4881 | 7.1627 | 10.4981 | 14.9862 | 21.4742 | 0.01
5.8236 | 8.9118 | 7.8236 | 6.8236 | 9.7354 | 11.7354 | 8.9118 | 15.7354 | 25.4708 | 37.2062 | 5.8236 | 8.9118 | 7.8236 | 6.8336 | 9.7354 | 11.7354 | 8.9118 | 15.7454 | 25.4808 | 37.2162 | 0.01
6.3687 | 9.1844 | 8.3687 | 7.3687 | 10.5531 | 12.5531 | 9.1844 | 16.5531 | 27.1062 | 39.6593 | 6.3687 | 9.1844 | 8.3687 | 7.3787 | 10.5531 | 12.5531 | 9.1844 | 16.5631 | 27.1162 | 39.6693 | 0.01
7.032 | 9.516 | 9.032 | 8.032 | 11.548 | 13.548 | 9.516 | 17.548 | 29.096 | 42.644 | 7.032 | 9.516 | 9.032 | 8.042 | 11.548 | 13.548 | 9.516 | 17.558 | 29.106 | 42.654 | 0.01
5.9999 | 9 | 7.9999 | 6.9999 | 9.9999 | 11.9999 | 9 | 15.9999 | 25.9998 | 37.9997 | 5.9999 | 9 | 7.9999 | 7.0099 | 9.9999 | 11.9999 | 9 | 16.0099 | 26.0098 | 38.0097 | 0.01
6.0206 | 9.0103 | 8.0206 | 7.0206 | 10.0309 | 12.0309 | 9.0103 | 16.0309 | 26.0617 | 38.0926 | 6.0206 | 9.0103 | 8.0206 | 7.0306 | 10.0309 | 12.0309 | 9.0103 | 16.0409 | 26.0717 | 38.1026 | 0.01
9.147 | 10.5735 | 11.147 | 10.147 | 14.7205 | 16.7205 | 10.5735 | 20.7205 | 35.441 | 52.1614 | 9.147 | 10.5735 | 11.147 | 10.157 | 14.7205 | 16.7205 | 10.5735 | 20.7305 | 35.451 | 52.1714 | 0.01
7.1056 | 9.5528 | 9.1056 | 8.1056 | 11.6584 | 13.6584 | 9.5528 | 17.6584 | 29.3168 | 42.9752 | 7.1056 | 9.5528 | 9.1056 | 8.1156 | 11.6584 | 13.6584 | 9.5528 | 17.6684 | 29.3268 | 42.9852 | 0.01
[8 empty] | Average | 37.4427 | [8 empty] | Average |  | 100%

## test activity E
A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | diff
1.4288 | 6.7144 | 3.4288 | 2.4288 | 3.1433 | 5.1433 | 6.7144 | 9.1433 | 12.2865 | 17.4298 | 1.4288 | 6.7144 | 3.4288 | 2.4288 | 3.1533 | 5.1433 | 6.7144 | 9.1433 | 12.2965 | 17.4398 | 0.01
2.4295 | 7.2148 | 4.4295 | 3.4295 | 4.6443 | 6.6443 | 7.2148 | 10.6443 | 15.2885 | 21.9328 | 2.4295 | 7.2148 | 4.4295 | 3.4295 | 4.6543 | 6.6443 | 7.2148 | 10.6443 | 15.2985 | 21.9428 | 0.01
4.0538 | 8.0269 | 6.0538 | 5.0538 | 7.0808 | 9.0808 | 8.0269 | 13.0808 | 20.1615 | 29.2423 | 4.0538 | 8.0269 | 6.0538 | 5.0538 | 7.0908 | 9.0808 | 8.0269 | 13.0808 | 20.1715 | 29.2523 | 0.01
6.049 | 9.0245 | 8.049 | 7.049 | 10.0736 | 12.0736 | 9.0245 | 16.0736 | 26.1471 | 38.2207 | 6.049 | 9.0245 | 8.049 | 7.049 | 10.0836 | 12.0736 | 9.0245 | 16.0736 | 26.1571 | 38.2307 | 0.01
7.3353 | 9.6677 | 9.3353 | 8.3353 | 12.003 | 14.003 | 9.6677 | 18.003 | 30.006 | 44.009 | 7.3353 | 9.6677 | 9.3353 | 8.3353 | 12.013 | 14.003 | 9.6677 | 18.003 | 30.016 | 44.019 | 0.01
5.1939 | 8.5969 | 7.1939 | 6.1939 | 8.7908 | 10.7908 | 8.5969 | 14.7908 | 23.5817 | 34.3725 | 5.1939 | 8.5969 | 7.1939 | 6.1939 | 8.8008 | 10.7908 | 8.5969 | 14.7908 | 23.5917 | 34.3825 | 0.01
7.3727 | 9.6863 | 9.3727 | 8.3727 | 12.059 | 14.059 | 9.6863 | 18.059 | 30.118 | 44.1769 | 7.3727 | 9.6863 | 9.3727 | 8.3727 | 12.069 | 14.059 | 9.6863 | 18.059 | 30.128 | 44.1869 | 0.01
2.7474 | 7.3737 | 4.7474 | 3.7474 | 5.1211 | 7.1211 | 7.3737 | 11.1211 | 16.2422 | 23.3633 | 2.7474 | 7.3737 | 4.7474 | 3.7474 | 5.1311 | 7.1211 | 7.3737 | 11.1211 | 16.2522 | 23.3733 | 0.01
7.0969 | 9.5484 | 9.0969 | 8.0969 | 11.6453 | 13.6453 | 9.5484 | 17.6453 | 29.2906 | 42.9359 | 7.0969 | 9.5484 | 9.0969 | 8.0969 | 11.6553 | 13.6453 | 9.5484 | 17.6453 | 29.3006 | 42.9459 | 0.01
4.1058 | 8.0529 | 6.1058 | 5.1058 | 7.1586 | 9.1586 | 8.0529 | 13.1586 | 20.3173 | 29.4759 | 4.1058 | 8.0529 | 6.1058 | 5.1058 | 7.1686 | 9.1586 | 8.0529 | 13.1586 | 20.3273 | 29.4859 | 0.01
7.2091 | 9.6045 | 9.2091 | 8.2091 | 11.8136 | 13.8136 | 9.6045 | 17.8136 | 29.6272 | 43.4408 | 7.2091 | 9.6045 | 9.2091 | 8.2091 | 11.8236 | 13.8136 | 9.6045 | 17.8136 | 29.6372 | 43.4508 | 0.01
10.8182 | 11.4091 | 12.8182 | 11.8182 | 17.2273 | 19.2273 | 11.4091 | 23.2273 | 40.4546 | 59.682 | 10.8182 | 11.4091 | 12.8182 | 11.8182 | 17.2373 | 19.2273 | 11.4091 | 23.2273 | 40.4646 | 59.692 | 0.01
6.4931 | 9.2465 | 8.4931 | 7.4931 | 10.7396 | 12.7396 | 9.2465 | 16.7396 | 27.4793 | 40.2189 | 6.4931 | 9.2465 | 8.4931 | 7.4931 | 10.7496 | 12.7396 | 9.2465 | 16.7396 | 27.4893 | 40.2289 | 0.01
6.0198 | 9.0099 | 8.0198 | 7.0198 | 10.0297 | 12.0297 | 9.0099 | 16.0297 | 26.0594 | 38.0892 | 6.0198 | 9.0099 | 8.0198 | 7.0198 | 10.0397 | 12.0297 | 9.0099 | 16.0297 | 26.0694 | 38.0992 | 0.01
5.2393 | 8.6197 | 7.2393 | 6.2393 | 8.859 | 10.859 | 8.6197 | 14.859 | 23.718 | 34.577 | 5.2393 | 8.6197 | 7.2393 | 6.2393 | 8.869 | 10.859 | 8.6197 | 14.859 | 23.728 | 34.587 | 0.01
5.4805 | 8.7403 | 7.4805 | 6.4805 | 9.2208 | 11.2208 | 8.7403 | 15.2208 | 24.4416 | 35.6624 | 5.4805 | 8.7403 | 7.4805 | 6.4805 | 9.2308 | 11.2208 | 8.7403 | 15.2208 | 24.4516 | 35.6724 | 0.01
3.5992 | 7.7996 | 5.5992 | 4.5992 | 6.3988 | 8.3988 | 7.7996 | 12.3988 | 18.7976 | 27.1965 | 3.5992 | 7.7996 | 5.5992 | 4.5992 | 6.4088 | 8.3988 | 7.7996 | 12.3988 | 18.8076 | 27.2065 | 0.01
2.2806 | 7.1403 | 4.2806 | 3.2806 | 4.4209 | 6.4209 | 7.1403 | 10.4209 | 14.8419 | 21.2628 | 2.2806 | 7.1403 | 4.2806 | 3.2806 | 4.4309 | 6.4209 | 7.1403 | 10.4209 | 14.8519 | 21.2728 | 0.01
6.9264 | 9.4632 | 8.9264 | 7.9264 | 11.3897 | 13.3897 | 9.4632 | 17.3897 | 28.7793 | 42.169 | 6.9264 | 9.4632 | 8.9264 | 7.9264 | 11.3997 | 13.3897 | 9.4632 | 17.3897 | 28.7893 | 42.179 | 0.01
4.5848 | 8.2924 | 6.5848 | 5.5848 | 7.8772 | 9.8772 | 8.2924 | 13.8772 | 21.7545 | 31.6317 | 4.5848 | 8.2924 | 6.5848 | 5.5848 | 7.8872 | 9.8772 | 8.2924 | 13.8772 | 21.7645 | 31.6417 | 0.01
5.8871 | 8.9436 | 7.8871 | 6.8871 | 9.8307 | 11.8307 | 8.9436 | 15.8307 | 25.6613 | 37.492 | 5.8871 | 8.9436 | 7.8871 | 6.8871 | 9.8407 | 11.8307 | 8.9436 | 15.8307 | 25.6713 | 37.502 | 0.01
4.4375 | 8.2187 | 6.4375 | 5.4375 | 7.6562 | 9.6562 | 8.2187 | 13.6562 | 21.3124 | 30.9686 | 4.4375 | 8.2187 | 6.4375 | 5.4375 | 7.6662 | 9.6562 | 8.2187 | 13.6562 | 21.3224 | 30.9786 | 0.01
5.9122 | 8.9561 | 7.9122 | 6.9122 | 9.8683 | 11.8683 | 8.9561 | 15.8683 | 25.7367 | 37.605 | 5.9122 | 8.9561 | 7.9122 | 6.9122 | 9.8783 | 11.8683 | 8.9561 | 15.8683 | 25.7467 | 37.615 | 0.01
4.2985 | 8.1493 | 6.2985 | 5.2985 | 7.4478 | 9.4478 | 8.1493 | 13.4478 | 20.8955 | 30.3433 | 4.2985 | 8.1493 | 6.2985 | 5.2985 | 7.4578 | 9.4478 | 8.1493 | 13.4478 | 20.9055 | 30.3533 | 0.01
3.7284 | 7.8642 | 5.7284 | 4.7284 | 6.5927 | 8.5927 | 7.8642 | 12.5927 | 19.1853 | 27.778 | 3.7284 | 7.8642 | 5.7284 | 4.7284 | 6.6027 | 8.5927 | 7.8642 | 12.5927 | 19.1953 | 27.788 | 0.01
7.6067 | 9.8034 | 9.6067 | 8.6067 | 12.4101 | 14.4101 | 9.8034 | 18.4101 | 30.8202 | 45.2303 | 7.6067 | 9.8034 | 9.6067 | 8.6067 | 12.4201 | 14.4101 | 9.8034 | 18.4101 | 30.8302 | 45.2403 | 0.01
8.6808 | 10.3404 | 10.6808 | 9.6808 | 14.0212 | 16.0212 | 10.3404 | 20.0212 | 34.0423 | 50.0635 | 8.6808 | 10.3404 | 10.6808 | 9.6808 | 14.0312 | 16.0212 | 10.3404 | 20.0212 | 34.0523 | 50.0735 | 0.01
5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8393 | 10.8293 | 8.6098 | 14.8293 | 23.6687 | 34.498 | 0.01
7.6331 | 9.8165 | 9.6331 | 8.6331 | 12.4496 | 14.4496 | 9.8165 | 18.4496 | 30.8992 | 45.3488 | 7.6331 | 9.8165 | 9.6331 | 8.6331 | 12.4596 | 14.4496 | 9.8165 | 18.4496 | 30.9092 | 45.3588 | 0.01
4.2833 | 8.1416 | 6.2833 | 5.2833 | 7.4249 | 9.4249 | 8.1416 | 13.4249 | 20.8499 | 30.2748 | 4.2833 | 8.1416 | 6.2833 | 5.2833 | 7.4349 | 9.4249 | 8.1416 | 13.4249 | 20.8599 | 30.2848 | 0.01
4.5407 | 8.2703 | 6.5407 | 5.5407 | 7.811 | 9.811 | 8.2703 | 13.811 | 21.622 | 31.433 | 4.5407 | 8.2703 | 6.5407 | 5.5407 | 7.821 | 9.811 | 8.2703 | 13.811 | 21.632 | 31.443 | 0.01
6.1115 | 9.0558 | 8.1115 | 7.1115 | 10.1673 | 12.1673 | 9.0558 | 16.1673 | 26.3345 | 38.5018 | 6.1115 | 9.0558 | 8.1115 | 7.1115 | 10.1773 | 12.1673 | 9.0558 | 16.1673 | 26.3445 | 38.5118 | 0.01
6.1999 | 9.1 | 8.1999 | 7.1999 | 10.2999 | 12.2999 | 9.1 | 16.2999 | 26.5997 | 38.8996 | 6.1999 | 9.1 | 8.1999 | 7.1999 | 10.3099 | 12.2999 | 9.1 | 16.2999 | 26.6097 | 38.9096 | 0.01
2.8161 | 7.408 | 4.8161 | 3.8161 | 5.2241 | 7.2241 | 7.408 | 11.2241 | 16.4482 | 23.6723 | 2.8161 | 7.408 | 4.8161 | 3.8161 | 5.2341 | 7.2241 | 7.408 | 11.2241 | 16.4582 | 23.6823 | 0.01
6.6314 | 9.3157 | 8.6314 | 7.6314 | 10.9471 | 12.9471 | 9.3157 | 16.9471 | 27.8943 | 40.8414 | 6.6314 | 9.3157 | 8.6314 | 7.6314 | 10.9571 | 12.9471 | 9.3157 | 16.9471 | 27.9043 | 40.8514 | 0.01
6.5394 | 9.2697 | 8.5394 | 7.5394 | 10.8092 | 12.8092 | 9.2697 | 16.8092 | 27.6183 | 40.4275 | 6.5394 | 9.2697 | 8.5394 | 7.5394 | 10.8192 | 12.8092 | 9.2697 | 16.8092 | 27.6283 | 40.4375 | 0.01
11.0521 | 11.526 | 13.0521 | 12.0521 | 17.5781 | 19.5781 | 11.526 | 23.5781 | 41.1562 | 60.7343 | 11.0521 | 11.526 | 13.0521 | 12.0521 | 17.5881 | 19.5781 | 11.526 | 23.5781 | 41.1662 | 60.7443 | 0.01
3.8102 | 7.9051 | 5.8102 | 4.8102 | 6.7153 | 8.7153 | 7.9051 | 12.7153 | 19.4307 | 28.146 | 3.8102 | 7.9051 | 5.8102 | 4.8102 | 6.7253 | 8.7153 | 7.9051 | 12.7153 | 19.4407 | 28.156 | 0.01
5.2518 | 8.6259 | 7.2518 | 6.2518 | 8.8777 | 10.8777 | 8.6259 | 14.8777 | 23.7554 | 34.6332 | 5.2518 | 8.6259 | 7.2518 | 6.2518 | 8.8877 | 10.8777 | 8.6259 | 14.8777 | 23.7654 | 34.6432 | 0.01
6.3771 | 9.1886 | 8.3771 | 7.3771 | 10.5657 | 12.5657 | 9.1886 | 16.5657 | 27.1314 | 39.6971 | 6.3771 | 9.1886 | 8.3771 | 7.3771 | 10.5757 | 12.5657 | 9.1886 | 16.5657 | 27.1414 | 39.7071 | 0.01
5.3383 | 8.6691 | 7.3383 | 6.3383 | 9.0074 | 11.0074 | 8.6691 | 15.0074 | 24.0148 | 35.0222 | 5.3383 | 8.6691 | 7.3383 | 6.3383 | 9.0174 | 11.0074 | 8.6691 | 15.0074 | 24.0248 | 35.0322 | 0.01
8.3948 | 10.1974 | 10.3948 | 9.3948 | 13.5922 | 15.5922 | 10.1974 | 19.5922 | 33.1845 | 48.7767 | 8.3948 | 10.1974 | 10.3948 | 9.3948 | 13.6022 | 15.5922 | 10.1974 | 19.5922 | 33.1945 | 48.7867 | 0.01
5.0712 | 8.5356 | 7.0712 | 6.0712 | 8.6068 | 10.6068 | 8.5356 | 14.6068 | 23.2135 | 33.8203 | 5.0712 | 8.5356 | 7.0712 | 6.0712 | 8.6168 | 10.6068 | 8.5356 | 14.6068 | 23.2235 | 33.8303 | 0.01
6.1543 | 9.0771 | 8.1543 | 7.1543 | 10.2314 | 12.2314 | 9.0771 | 16.2314 | 26.4629 | 38.6943 | 6.1543 | 9.0771 | 8.1543 | 7.1543 | 10.2414 | 12.2314 | 9.0771 | 16.2314 | 26.4729 | 38.7043 | 0.01
5.863 | 8.9315 | 7.863 | 6.863 | 9.7946 | 11.7946 | 8.9315 | 15.7946 | 25.5891 | 37.3837 | 5.863 | 8.9315 | 7.863 | 6.863 | 9.8046 | 11.7946 | 8.9315 | 15.7946 | 25.5991 | 37.3937 | 0.01
2.5835 | 7.2917 | 4.5835 | 3.5835 | 4.8752 | 6.8752 | 7.2917 | 10.8752 | 15.7504 | 22.6257 | 2.5835 | 7.2917 | 4.5835 | 3.5835 | 4.8852 | 6.8752 | 7.2917 | 10.8752 | 15.7604 | 22.6357 | 0.01
5.0249 | 8.5125 | 7.0249 | 6.0249 | 8.5374 | 10.5374 | 8.5125 | 14.5374 | 23.0747 | 33.6121 | 5.0249 | 8.5125 | 7.0249 | 6.0249 | 8.5474 | 10.5374 | 8.5125 | 14.5374 | 23.0847 | 33.6221 | 0.01
6.1918 | 9.0959 | 8.1918 | 7.1918 | 10.2877 | 12.2877 | 9.0959 | 16.2877 | 26.5753 | 38.863 | 6.1918 | 9.0959 | 8.1918 | 7.1918 | 10.2977 | 12.2877 | 9.0959 | 16.2877 | 26.5853 | 38.873 | 0.01
5.0897 | 8.5449 | 7.0897 | 6.0897 | 8.6346 | 10.6346 | 8.5449 | 14.6346 | 23.2691 | 33.9037 | 5.0897 | 8.5449 | 7.0897 | 6.0897 | 8.6446 | 10.6346 | 8.5449 | 14.6346 | 23.2791 | 33.9137 | 0.01
5.4889 | 8.7445 | 7.4889 | 6.4889 | 9.2334 | 11.2334 | 8.7445 | 15.2334 | 24.4667 | 35.7001 | 5.4889 | 8.7445 | 7.4889 | 6.4889 | 9.2434 | 11.2334 | 8.7445 | 15.2334 | 24.4767 | 35.7101 | 0.01
8.7445 | 10.3722 | 10.7445 | 9.7445 | 14.1167 | 16.1167 | 10.3722 | 20.1167 | 34.2334 | 50.3502 | 8.7445 | 10.3722 | 10.7445 | 9.7445 | 14.1267 | 16.1167 | 10.3722 | 20.1167 | 34.2434 | 50.3602 | 0.01
6.1328 | 9.0664 | 8.1328 | 7.1328 | 10.1992 | 12.1992 | 9.0664 | 16.1992 | 26.3985 | 38.5977 | 6.1328 | 9.0664 | 8.1328 | 7.1328 | 10.2092 | 12.1992 | 9.0664 | 16.1992 | 26.4085 | 38.6077 | 0.01
6.4019 | 9.201 | 8.4019 | 7.4019 | 10.6029 | 12.6029 | 9.201 | 16.6029 | 27.2058 | 39.8087 | 6.4019 | 9.201 | 8.4019 | 7.4019 | 10.6129 | 12.6029 | 9.201 | 16.6029 | 27.2158 | 39.8187 | 0.01
4.0371 | 8.0185 | 6.0371 | 5.0371 | 7.0556 | 9.0556 | 8.0185 | 13.0556 | 20.1112 | 29.1668 | 4.0371 | 8.0185 | 6.0371 | 5.0371 | 7.0656 | 9.0556 | 8.0185 | 13.0556 | 20.1212 | 29.1768 | 0.01
5.83 | 8.915 | 7.83 | 6.83 | 9.7451 | 11.7451 | 8.915 | 15.7451 | 25.4901 | 37.2352 | 5.83 | 8.915 | 7.83 | 6.83 | 9.7551 | 11.7451 | 8.915 | 15.7451 | 25.5001 | 37.2452 | 0.01
2.6753 | 7.3376 | 4.6753 | 3.6753 | 5.0129 | 7.0129 | 7.3376 | 11.0129 | 16.0258 | 23.0387 | 2.6753 | 7.3376 | 4.6753 | 3.6753 | 5.0229 | 7.0129 | 7.3376 | 11.0129 | 16.0358 | 23.0487 | 0.01
5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0438 | 11.0338 | 8.6779 | 15.0338 | 24.0776 | 35.1113 | 0.01
2.6862 | 7.3431 | 4.6862 | 3.6862 | 5.0293 | 7.0293 | 7.3431 | 11.0293 | 16.0585 | 23.0878 | 2.6862 | 7.3431 | 4.6862 | 3.6862 | 5.0393 | 7.0293 | 7.3431 | 11.0293 | 16.0685 | 23.0978 | 0.01
9.7341 | 10.8671 | 11.7341 | 10.7341 | 15.6012 | 17.6012 | 10.8671 | 21.6012 | 37.2024 | 54.8037 | 9.7341 | 10.8671 | 11.7341 | 10.7341 | 15.6112 | 17.6012 | 10.8671 | 21.6012 | 37.2124 | 54.8137 | 0.01
4.1077 | 8.0538 | 6.1077 | 5.1077 | 7.1615 | 9.1615 | 8.0538 | 13.1615 | 20.323 | 29.4845 | 4.1077 | 8.0538 | 6.1077 | 5.1077 | 7.1715 | 9.1615 | 8.0538 | 13.1615 | 20.333 | 29.4945 | 0.01
7.484 | 9.742 | 9.484 | 8.484 | 12.226 | 14.226 | 9.742 | 18.226 | 30.452 | 44.6781 | 7.484 | 9.742 | 9.484 | 8.484 | 12.236 | 14.226 | 9.742 | 18.226 | 30.462 | 44.6881 | 0.01
6.2666 | 9.1333 | 8.2666 | 7.2666 | 10.3999 | 12.3999 | 9.1333 | 16.3999 | 26.7999 | 39.1998 | 6.2666 | 9.1333 | 8.2666 | 7.2666 | 10.4099 | 12.3999 | 9.1333 | 16.3999 | 26.8099 | 39.2098 | 0.01
5.2959 | 8.648 | 7.2959 | 6.2959 | 8.9439 | 10.9439 | 8.648 | 14.9439 | 23.8878 | 34.8317 | 5.2959 | 8.648 | 7.2959 | 6.2959 | 8.9539 | 10.9439 | 8.648 | 14.9439 | 23.8978 | 34.8417 | 0.01
4.8999 | 8.45 | 6.8999 | 5.8999 | 8.3499 | 10.3499 | 8.45 | 14.3499 | 22.6998 | 33.0497 | 4.8999 | 8.45 | 6.8999 | 5.8999 | 8.3599 | 10.3499 | 8.45 | 14.3499 | 22.7098 | 33.0597 | 0.01
5.8151 | 8.9076 | 7.8151 | 6.8151 | 9.7227 | 11.7227 | 8.9076 | 15.7227 | 25.4454 | 37.1682 | 5.8151 | 8.9076 | 7.8151 | 6.8151 | 9.7327 | 11.7227 | 8.9076 | 15.7227 | 25.4554 | 37.1782 | 0.01
5.9292 | 8.9646 | 7.9292 | 6.9292 | 9.8938 | 11.8938 | 8.9646 | 15.8938 | 25.7877 | 37.6815 | 5.9292 | 8.9646 | 7.9292 | 6.9292 | 9.9038 | 11.8938 | 8.9646 | 15.8938 | 25.7977 | 37.6915 | 0.01
2.9022 | 7.4511 | 4.9022 | 3.9022 | 5.3533 | 7.3533 | 7.4511 | 11.3533 | 16.7065 | 24.0598 | 2.9022 | 7.4511 | 4.9022 | 3.9022 | 5.3633 | 7.3533 | 7.4511 | 11.3533 | 16.7165 | 24.0698 | 0.01
3.7424 | 7.8712 | 5.7424 | 4.7424 | 6.6136 | 8.6136 | 7.8712 | 12.6136 | 19.2272 | 27.8407 | 3.7424 | 7.8712 | 5.7424 | 4.7424 | 6.6236 | 8.6136 | 7.8712 | 12.6136 | 19.2372 | 27.8507 | 0.01
8.3173 | 10.1587 | 10.3173 | 9.3173 | 13.476 | 15.476 | 10.1587 | 19.476 | 32.952 | 48.4281 | 8.3173 | 10.1587 | 10.3173 | 9.3173 | 13.486 | 15.476 | 10.1587 | 19.476 | 32.962 | 48.4381 | 0.01
4.7975 | 8.3988 | 6.7975 | 5.7975 | 8.1963 | 10.1963 | 8.3988 | 14.1963 | 22.3926 | 32.5889 | 4.7975 | 8.3988 | 6.7975 | 5.7975 | 8.2063 | 10.1963 | 8.3988 | 14.1963 | 22.4026 | 32.5989 | 0.01
4.0727 | 8.0363 | 6.0727 | 5.0727 | 7.109 | 9.109 | 8.0363 | 13.109 | 20.218 | 29.327 | 4.0727 | 8.0363 | 6.0727 | 5.0727 | 7.119 | 9.109 | 8.0363 | 13.109 | 20.228 | 29.337 | 0.01
7.2028 | 9.6014 | 9.2028 | 8.2028 | 11.8042 | 13.8042 | 9.6014 | 17.8042 | 29.6085 | 43.4127 | 7.2028 | 9.6014 | 9.2028 | 8.2028 | 11.8142 | 13.8042 | 9.6014 | 17.8042 | 29.6185 | 43.4227 | 0.01
5.1967 | 8.5984 | 7.1967 | 6.1967 | 8.7951 | 10.7951 | 8.5984 | 14.7951 | 23.5902 | 34.3852 | 5.1967 | 8.5984 | 7.1967 | 6.1967 | 8.8051 | 10.7951 | 8.5984 | 14.7951 | 23.6002 | 34.3952 | 0.01
3.0576 | 7.5288 | 5.0576 | 4.0576 | 5.5864 | 7.5864 | 7.5288 | 11.5864 | 17.1729 | 24.7593 | 3.0576 | 7.5288 | 5.0576 | 4.0576 | 5.5964 | 7.5864 | 7.5288 | 11.5864 | 17.1829 | 24.7693 | 0.01
4.772 | 8.386 | 6.772 | 5.772 | 8.1579 | 10.1579 | 8.386 | 14.1579 | 22.3159 | 32.4738 | 4.772 | 8.386 | 6.772 | 5.772 | 8.1679 | 10.1579 | 8.386 | 14.1579 | 22.3259 | 32.4838 | 0.01
6.9343 | 9.4671 | 8.9343 | 7.9343 | 11.4014 | 13.4014 | 9.4671 | 17.4014 | 28.8028 | 42.2043 | 6.9343 | 9.4671 | 8.9343 | 7.9343 | 11.4114 | 13.4014 | 9.4671 | 17.4014 | 28.8128 | 42.2143 | 0.01
5.9782 | 8.9891 | 7.9782 | 6.9782 | 9.9673 | 11.9673 | 8.9891 | 15.9673 | 25.9346 | 37.9019 | 5.9782 | 8.9891 | 7.9782 | 6.9782 | 9.9773 | 11.9673 | 8.9891 | 15.9673 | 25.9446 | 37.9119 | 0.01
4.3539 | 8.1769 | 6.3539 | 5.3539 | 7.5308 | 9.5308 | 8.1769 | 13.5308 | 21.0616 | 30.5925 | 4.3539 | 8.1769 | 6.3539 | 5.3539 | 7.5408 | 9.5308 | 8.1769 | 13.5308 | 21.0716 | 30.6025 | 0.01
4.4273 | 8.2136 | 6.4273 | 5.4273 | 7.6409 | 9.6409 | 8.2136 | 13.6409 | 21.2818 | 30.9227 | 4.4273 | 8.2136 | 6.4273 | 5.4273 | 7.6509 | 9.6409 | 8.2136 | 13.6409 | 21.2918 | 30.9327 | 0.01
5.6648 | 8.8324 | 7.6648 | 6.6648 | 9.4972 | 11.4972 | 8.8324 | 15.4972 | 24.9945 | 36.4917 | 5.6648 | 8.8324 | 7.6648 | 6.6648 | 9.5072 | 11.4972 | 8.8324 | 15.4972 | 25.0045 | 36.5017 | 0.01
6.1502 | 9.0751 | 8.1502 | 7.1502 | 10.2252 | 12.2252 | 9.0751 | 16.2252 | 26.4505 | 38.6757 | 6.1502 | 9.0751 | 8.1502 | 7.1502 | 10.2352 | 12.2252 | 9.0751 | 16.2252 | 26.4605 | 38.6857 | 0.01
13.0455 | 12.5227 | 15.0455 | 14.0455 | 20.5682 | 22.5682 | 13.0455 | 27.0909 | 47.6591 | 70.2273 | 13.0455 | 12.5227 | 15.0455 | 14.0455 | 20.5782 | 22.5682 | 13.0455 | 27.0909 | 47.6691 | 70.2373 | 0.01
7.6173 | 9.8087 | 9.6173 | 8.6173 | 12.426 | 14.426 | 9.8087 | 18.426 | 30.8519 | 45.2779 | 7.6173 | 9.8087 | 9.6173 | 8.6173 | 12.436 | 14.426 | 9.8087 | 18.426 | 30.8619 | 45.2879 | 0.01
8.3774 | 10.1887 | 10.3774 | 9.3774 | 13.566 | 15.566 | 10.1887 | 19.566 | 33.1321 | 48.6981 | 8.3774 | 10.1887 | 10.3774 | 9.3774 | 13.576 | 15.566 | 10.1887 | 19.566 | 33.1421 | 48.7081 | 0.01
6.074 | 9.037 | 8.074 | 7.074 | 10.111 | 12.111 | 9.037 | 16.111 | 26.222 | 38.333 | 6.074 | 9.037 | 8.074 | 7.074 | 10.121 | 12.111 | 9.037 | 16.111 | 26.232 | 38.343 | 0.01
5.9353 | 8.9677 | 7.9353 | 6.9353 | 9.903 | 11.903 | 8.9677 | 15.903 | 25.806 | 37.7091 | 5.9353 | 8.9677 | 7.9353 | 6.9353 | 9.913 | 11.903 | 8.9677 | 15.903 | 25.816 | 37.7191 | 0.01
6.9629 | 9.4814 | 8.9629 | 7.9629 | 11.4443 | 13.4443 | 9.4814 | 17.4443 | 28.8886 | 42.3329 | 6.9629 | 9.4814 | 8.9629 | 7.9629 | 11.4543 | 13.4443 | 9.4814 | 17.4443 | 28.8986 | 42.3429 | 0.01
3.2723 | 7.6361 | 5.2723 | 4.2723 | 5.9084 | 7.9084 | 7.6361 | 11.9084 | 17.8169 | 25.7253 | 3.2723 | 7.6361 | 5.2723 | 4.2723 | 5.9184 | 7.9084 | 7.6361 | 11.9084 | 17.8269 | 25.7353 | 0.01
5.3875 | 8.6938 | 7.3875 | 6.3875 | 9.0813 | 11.0813 | 8.6938 | 15.0813 | 24.1626 | 35.2438 | 5.3875 | 8.6938 | 7.3875 | 6.3875 | 9.0913 | 11.0813 | 8.6938 | 15.0813 | 24.1726 | 35.2538 | 0.01
2.8991 | 7.4496 | 4.8991 | 3.8991 | 5.3487 | 7.3487 | 7.4496 | 11.3487 | 16.6974 | 24.0461 | 2.8991 | 7.4496 | 4.8991 | 3.8991 | 5.3587 | 7.3487 | 7.4496 | 11.3487 | 16.7074 | 24.0561 | 0.01
6.8927 | 9.4463 | 8.8927 | 7.8927 | 11.339 | 13.339 | 9.4463 | 17.339 | 28.678 | 42.017 | 6.8927 | 9.4463 | 8.8927 | 7.8927 | 11.349 | 13.339 | 9.4463 | 17.339 | 28.688 | 42.027 | 0.01
5.2946 | 8.6473 | 7.2946 | 6.2946 | 8.942 | 10.942 | 8.6473 | 14.942 | 23.8839 | 34.8259 | 5.2946 | 8.6473 | 7.2946 | 6.2946 | 8.952 | 10.942 | 8.6473 | 14.942 | 23.8939 | 34.8359 | 0.01
7.3723 | 9.6861 | 9.3723 | 8.3723 | 12.0584 | 14.0584 | 9.6861 | 18.0584 | 30.1168 | 44.1752 | 7.3723 | 9.6861 | 9.3723 | 8.3723 | 12.0684 | 14.0584 | 9.6861 | 18.0584 | 30.1268 | 44.1852 | 0.01
6.4354 | 9.2177 | 8.4354 | 7.4354 | 10.6531 | 12.6531 | 9.2177 | 16.6531 | 27.3062 | 39.9593 | 6.4354 | 9.2177 | 8.4354 | 7.4354 | 10.6631 | 12.6531 | 9.2177 | 16.6531 | 27.3162 | 39.9693 | 0.01
5.4793 | 8.7396 | 7.4793 | 6.4793 | 9.2189 | 11.2189 | 8.7396 | 15.2189 | 24.4378 | 35.6567 | 5.4793 | 8.7396 | 7.4793 | 6.4793 | 9.2289 | 11.2189 | 8.7396 | 15.2189 | 24.4478 | 35.6667 | 0.01
6.2472 | 9.1236 | 8.2472 | 7.2472 | 10.3708 | 12.3708 | 9.1236 | 16.3708 | 26.7415 | 39.1123 | 6.2472 | 9.1236 | 8.2472 | 7.2472 | 10.3808 | 12.3708 | 9.1236 | 16.3708 | 26.7515 | 39.1223 | 0.01
4.9739 | 8.487 | 6.9739 | 5.9739 | 8.4609 | 10.4609 | 8.487 | 14.4609 | 22.9218 | 33.3827 | 4.9739 | 8.487 | 6.9739 | 5.9739 | 8.4709 | 10.4609 | 8.487 | 14.4609 | 22.9318 | 33.3927 | 0.01
1.3058 | 6.6529 | 3.3058 | 2.3058 | 2.9588 | 4.9588 | 6.6529 | 8.9588 | 11.9175 | 16.8763 | 1.3058 | 6.6529 | 3.3058 | 2.3058 | 2.9688 | 4.9588 | 6.6529 | 8.9588 | 11.9275 | 16.8863 | 0.01
6.9362 | 9.4681 | 8.9362 | 7.9362 | 11.4042 | 13.4042 | 9.4681 | 17.4042 | 28.8085 | 42.2127 | 6.9362 | 9.4681 | 8.9362 | 7.9362 | 11.4142 | 13.4042 | 9.4681 | 17.4042 | 28.8185 | 42.2227 | 0.01
7.1438 | 9.5719 | 9.1438 | 8.1438 | 11.7157 | 13.7157 | 9.5719 | 17.7157 | 29.4313 | 43.147 | 7.1438 | 9.5719 | 9.1438 | 8.1438 | 11.7257 | 13.7157 | 9.5719 | 17.7157 | 29.4413 | 43.157 | 0.01
7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8885 | 13.8785 | 9.6262 | 17.8785 | 29.767 | 43.6455 | 0.01
10.4708 | 11.2354 | 12.4708 | 11.4708 | 16.7062 | 18.7062 | 11.2354 | 22.7062 | 39.4124 | 58.1185 | 10.4708 | 11.2354 | 12.4708 | 11.4708 | 16.7162 | 18.7062 | 11.2354 | 22.7062 | 39.4224 | 58.1285 | 0.01
7.3244 | 9.6622 | 9.3244 | 8.3244 | 11.9867 | 13.9867 | 9.6622 | 17.9867 | 29.9733 | 43.96 | 7.3244 | 9.6622 | 9.3244 | 8.3244 | 11.9967 | 13.9867 | 9.6622 | 17.9867 | 29.9833 | 43.97 | 0.01
3.4391 | 7.7195 | 5.4391 | 4.4391 | 6.1586 | 8.1586 | 7.7195 | 12.1586 | 18.3173 | 26.4759 | 3.4391 | 7.7195 | 5.4391 | 4.4391 | 6.1686 | 8.1586 | 7.7195 | 12.1586 | 18.3273 | 26.4859 | 0.01
3.4033 | 7.7016 | 5.4033 | 4.4033 | 6.1049 | 8.1049 | 7.7016 | 12.1049 | 18.2098 | 26.3146 | 3.4033 | 7.7016 | 5.4033 | 4.4033 | 6.1149 | 8.1049 | 7.7016 | 12.1049 | 18.2198 | 26.3246 | 0.01
6.3856 | 9.1928 | 8.3856 | 7.3856 | 10.5783 | 12.5783 | 9.1928 | 16.5783 | 27.1567 | 39.735 | 6.3856 | 9.1928 | 8.3856 | 7.3856 | 10.5883 | 12.5783 | 9.1928 | 16.5783 | 27.1667 | 39.745 | 0.01
4.8622 | 8.4311 | 6.8622 | 5.8622 | 8.2933 | 10.2933 | 8.4311 | 14.2933 | 22.5865 | 32.8798 | 4.8622 | 8.4311 | 6.8622 | 5.8622 | 8.3033 | 10.2933 | 8.4311 | 14.2933 | 22.5965 | 32.8898 | 0.01
6.2649 | 9.1325 | 8.2649 | 7.2649 | 10.3974 | 12.3974 | 9.1325 | 16.3974 | 26.7948 | 39.1921 | 6.2649 | 9.1325 | 8.2649 | 7.2649 | 10.4074 | 12.3974 | 9.1325 | 16.3974 | 26.8048 | 39.2021 | 0.01
6.3815 | 9.1908 | 8.3815 | 7.3815 | 10.5723 | 12.5723 | 9.1908 | 16.5723 | 27.1445 | 39.7168 | 6.3815 | 9.1908 | 8.3815 | 7.3815 | 10.5823 | 12.5723 | 9.1908 | 16.5723 | 27.1545 | 39.7268 | 0.01
6.0503 | 9.0251 | 8.0503 | 7.0503 | 10.0754 | 12.0754 | 9.0251 | 16.0754 | 26.1508 | 38.2262 | 6.0503 | 9.0251 | 8.0503 | 7.0503 | 10.0854 | 12.0754 | 9.0251 | 16.0754 | 26.1608 | 38.2362 | 0.01
7.3199 | 9.6599 | 9.3199 | 8.3199 | 11.9798 | 13.9798 | 9.6599 | 17.9798 | 29.9596 | 43.9394 | 7.3199 | 9.6599 | 9.3199 | 8.3199 | 11.9898 | 13.9798 | 9.6599 | 17.9798 | 29.9696 | 43.9494 | 0.01
4.8278 | 8.4139 | 6.8278 | 5.8278 | 8.2417 | 10.2417 | 8.4139 | 14.2417 | 22.4835 | 32.7252 | 4.8278 | 8.4139 | 6.8278 | 5.8278 | 8.2517 | 10.2417 | 8.4139 | 14.2417 | 22.4935 | 32.7352 | 0.01
5.4652 | 8.7326 | 7.4652 | 6.4652 | 9.1977 | 11.1977 | 8.7326 | 15.1977 | 24.3955 | 35.5932 | 5.4652 | 8.7326 | 7.4652 | 6.4652 | 9.2077 | 11.1977 | 8.7326 | 15.1977 | 24.4055 | 35.6032 | 0.01
3.3593 | 7.6796 | 5.3593 | 4.3593 | 6.0389 | 8.0389 | 7.6796 | 12.0389 | 18.0778 | 26.1167 | 3.3593 | 7.6796 | 5.3593 | 4.3593 | 6.0489 | 8.0389 | 7.6796 | 12.0389 | 18.0878 | 26.1267 | 0.01
7.5124 | 9.7562 | 9.5124 | 8.5124 | 12.2686 | 14.2686 | 9.7562 | 18.2686 | 30.5371 | 44.8057 | 7.5124 | 9.7562 | 9.5124 | 8.5124 | 12.2786 | 14.2686 | 9.7562 | 18.2686 | 30.5471 | 44.8157 | 0.01
3.9132 | 7.9566 | 5.9132 | 4.9132 | 6.8698 | 8.8698 | 7.9566 | 12.8698 | 19.7396 | 28.6094 | 3.9132 | 7.9566 | 5.9132 | 4.9132 | 6.8798 | 8.8698 | 7.9566 | 12.8698 | 19.7496 | 28.6194 | 0.01
1.5199 | 6.7599 | 3.5199 | 2.5199 | 3.2798 | 5.2798 | 6.7599 | 9.2798 | 12.5596 | 17.8394 | 1.5199 | 6.7599 | 3.5199 | 2.5199 | 3.2898 | 5.2798 | 6.7599 | 9.2798 | 12.5696 | 17.8494 | 0.01
4.6499 | 8.325 | 6.6499 | 5.6499 | 7.9749 | 9.9749 | 8.325 | 13.9749 | 21.9497 | 31.9246 | 4.6499 | 8.325 | 6.6499 | 5.6499 | 7.9849 | 9.9749 | 8.325 | 13.9749 | 21.9597 | 31.9346 | 0.01
4.3616 | 8.1808 | 6.3616 | 5.3616 | 7.5424 | 9.5424 | 8.1808 | 13.5424 | 21.0848 | 30.6272 | 4.3616 | 8.1808 | 6.3616 | 5.3616 | 7.5524 | 9.5424 | 8.1808 | 13.5424 | 21.0948 | 30.6372 | 0.01
5.2767 | 8.6383 | 7.2767 | 6.2767 | 8.915 | 10.915 | 8.6383 | 14.915 | 23.8301 | 34.7451 | 5.2767 | 8.6383 | 7.2767 | 6.2767 | 8.925 | 10.915 | 8.6383 | 14.915 | 23.8401 | 34.7551 | 0.01
4.6809 | 8.3404 | 6.6809 | 5.6809 | 8.0213 | 10.0213 | 8.3404 | 14.0213 | 22.0426 | 32.064 | 4.6809 | 8.3404 | 6.6809 | 5.6809 | 8.0313 | 10.0213 | 8.3404 | 14.0213 | 22.0526 | 32.074 | 0.01
7.3392 | 9.6696 | 9.3392 | 8.3392 | 12.0087 | 14.0087 | 9.6696 | 18.0087 | 30.0175 | 44.0262 | 7.3392 | 9.6696 | 9.3392 | 8.3392 | 12.0187 | 14.0087 | 9.6696 | 18.0087 | 30.0275 | 44.0362 | 0.01
5.9878 | 8.9939 | 7.9878 | 6.9878 | 9.9818 | 11.9818 | 8.9939 | 15.9818 | 25.9635 | 37.9453 | 5.9878 | 8.9939 | 7.9878 | 6.9878 | 9.9918 | 11.9818 | 8.9939 | 15.9818 | 25.9735 | 37.9553 | 0.01
7.2575 | 9.6288 | 9.2575 | 8.2575 | 11.8863 | 13.8863 | 9.6288 | 17.8863 | 29.7726 | 43.659 | 7.2575 | 9.6288 | 9.2575 | 8.2575 | 11.8963 | 13.8863 | 9.6288 | 17.8863 | 29.7826 | 43.669 | 0.01
6.2064 | 9.1032 | 8.2064 | 7.2064 | 10.3096 | 12.3096 | 9.1032 | 16.3096 | 26.6191 | 38.9287 | 6.2064 | 9.1032 | 8.2064 | 7.2064 | 10.3196 | 12.3096 | 9.1032 | 16.3096 | 26.6291 | 38.9387 | 0.01
3.8799 | 7.94 | 5.8799 | 4.8799 | 6.8199 | 8.8199 | 7.94 | 12.8199 | 19.6398 | 28.4598 | 3.8799 | 7.94 | 5.8799 | 4.8799 | 6.8299 | 8.8199 | 7.94 | 12.8199 | 19.6498 | 28.4698 | 0.01
2.4504 | 7.2252 | 4.4504 | 3.4504 | 4.6756 | 6.6756 | 7.2252 | 10.6756 | 15.3512 | 22.0267 | 2.4504 | 7.2252 | 4.4504 | 3.4504 | 4.6856 | 6.6756 | 7.2252 | 10.6756 | 15.3612 | 22.0367 | 0.01
5.7233 | 8.8617 | 7.7233 | 6.7233 | 9.585 | 11.585 | 8.8617 | 15.585 | 25.17 | 36.755 | 5.7233 | 8.8617 | 7.7233 | 6.7233 | 9.595 | 11.585 | 8.8617 | 15.585 | 25.18 | 36.765 | 0.01
8.2167 | 10.1084 | 10.2167 | 9.2167 | 13.3251 | 15.3251 | 10.1084 | 19.3251 | 32.6501 | 47.9752 | 8.2167 | 10.1084 | 10.2167 | 9.2167 | 13.3351 | 15.3251 | 10.1084 | 19.3251 | 32.6601 | 47.9852 | 0.01
5.8225 | 8.9113 | 7.8225 | 6.8225 | 9.7338 | 11.7338 | 8.9113 | 15.7338 | 25.4676 | 37.2013 | 5.8225 | 8.9113 | 7.8225 | 6.8225 | 9.7438 | 11.7338 | 8.9113 | 15.7338 | 25.4776 | 37.2113 | 0.01
4.44 | 8.22 | 6.44 | 5.44 | 7.6599 | 9.6599 | 8.22 | 13.6599 | 21.3199 | 30.9798 | 4.44 | 8.22 | 6.44 | 5.44 | 7.6699 | 9.6599 | 8.22 | 13.6599 | 21.3299 | 30.9898 | 0.01
5.5445 | 8.7723 | 7.5445 | 6.5445 | 9.3168 | 11.3168 | 8.7723 | 15.3168 | 24.6336 | 35.9503 | 5.5445 | 8.7723 | 7.5445 | 6.5445 | 9.3268 | 11.3168 | 8.7723 | 15.3168 | 24.6436 | 35.9603 | 0.01
6.9782 | 9.4891 | 8.9782 | 7.9782 | 11.4673 | 13.4673 | 9.4891 | 17.4673 | 28.9346 | 42.4018 | 6.9782 | 9.4891 | 8.9782 | 7.9782 | 11.4773 | 13.4673 | 9.4891 | 17.4673 | 28.9446 | 42.4118 | 0.01
4.06 | 8.03 | 6.06 | 5.06 | 7.09 | 9.09 | 8.03 | 13.09 | 20.1799 | 29.2699 | 4.06 | 8.03 | 6.06 | 5.06 | 7.1 | 9.09 | 8.03 | 13.09 | 20.1899 | 29.2799 | 0.01
6.8952 | 9.4476 | 8.8952 | 7.8952 | 11.3428 | 13.3428 | 9.4476 | 17.3428 | 28.6856 | 42.0284 | 6.8952 | 9.4476 | 8.8952 | 7.8952 | 11.3528 | 13.3428 | 9.4476 | 17.3428 | 28.6956 | 42.0384 | 0.01
4.2954 | 8.1477 | 6.2954 | 5.2954 | 7.4431 | 9.4431 | 8.1477 | 13.4431 | 20.8863 | 30.3294 | 4.2954 | 8.1477 | 6.2954 | 5.2954 | 7.4531 | 9.4431 | 8.1477 | 13.4431 | 20.8963 | 30.3394 | 0.01
5.384 | 8.692 | 7.384 | 6.384 | 9.076 | 11.076 | 8.692 | 15.076 | 24.152 | 35.228 | 5.384 | 8.692 | 7.384 | 6.384 | 9.086 | 11.076 | 8.692 | 15.076 | 24.162 | 35.238 | 0.01
5.5138 | 8.7569 | 7.5138 | 6.5138 | 9.2708 | 11.2708 | 8.7569 | 15.2708 | 24.5415 | 35.8123 | 5.5138 | 8.7569 | 7.5138 | 6.5138 | 9.2808 | 11.2708 | 8.7569 | 15.2708 | 24.5515 | 35.8223 | 0.01
6.558 | 9.279 | 8.558 | 7.558 | 10.837 | 12.837 | 9.279 | 16.837 | 27.6741 | 40.5111 | 6.558 | 9.279 | 8.558 | 7.558 | 10.847 | 12.837 | 9.279 | 16.837 | 27.6841 | 40.5211 | 0.01
6.8751 | 9.4376 | 8.8751 | 7.8751 | 11.3127 | 13.3127 | 9.4376 | 17.3127 | 28.6254 | 41.9381 | 6.8751 | 9.4376 | 8.8751 | 7.8751 | 11.3227 | 13.3127 | 9.4376 | 17.3127 | 28.6354 | 41.9481 | 0.01
5.5105 | 8.7553 | 7.5105 | 6.5105 | 9.2658 | 11.2658 | 8.7553 | 15.2658 | 24.5316 | 35.7974 | 5.5105 | 8.7553 | 7.5105 | 6.5105 | 9.2758 | 11.2658 | 8.7553 | 15.2658 | 24.5416 | 35.8074 | 0.01
3.8041 | 7.902 | 5.8041 | 4.8041 | 6.7061 | 8.7061 | 7.902 | 12.7061 | 19.4123 | 28.1184 | 3.8041 | 7.902 | 5.8041 | 4.8041 | 6.7161 | 8.7061 | 7.902 | 12.7061 | 19.4223 | 28.1284 | 0.01
6.5984 | 9.2992 | 8.5984 | 7.5984 | 10.8976 | 12.8976 | 9.2992 | 16.8976 | 27.7952 | 40.6927 | 6.5984 | 9.2992 | 8.5984 | 7.5984 | 10.9076 | 12.8976 | 9.2992 | 16.8976 | 27.8052 | 40.7027 | 0.01
4.1412 | 8.0706 | 6.1412 | 5.1412 | 7.2117 | 9.2117 | 8.0706 | 13.2117 | 20.4235 | 29.6352 | 4.1412 | 8.0706 | 6.1412 | 5.1412 | 7.2217 | 9.2117 | 8.0706 | 13.2117 | 20.4335 | 29.6452 | 0.01
8.1884 | 10.0942 | 10.1884 | 9.1884 | 13.2826 | 15.2826 | 10.0942 | 19.2826 | 32.5651 | 47.8477 | 8.1884 | 10.0942 | 10.1884 | 9.1884 | 13.2926 | 15.2826 | 10.0942 | 19.2826 | 32.5751 | 47.8577 | 0.01
3.3929 | 7.6965 | 5.3929 | 4.3929 | 6.0894 | 8.0894 | 7.6965 | 12.0894 | 18.1787 | 26.2681 | 3.3929 | 7.6965 | 5.3929 | 4.3929 | 6.0994 | 8.0894 | 7.6965 | 12.0894 | 18.1887 | 26.2781 | 0.01
8.253 | 10.1265 | 10.253 | 9.253 | 13.3795 | 15.3795 | 10.1265 | 19.3795 | 32.759 | 48.1384 | 8.253 | 10.1265 | 10.253 | 9.253 | 13.3895 | 15.3795 | 10.1265 | 19.3795 | 32.769 | 48.1484 | 0.01
6.3518 | 9.1759 | 8.3518 | 7.3518 | 10.5277 | 12.5277 | 9.1759 | 16.5277 | 27.0554 | 39.583 | 6.3518 | 9.1759 | 8.3518 | 7.3518 | 10.5377 | 12.5277 | 9.1759 | 16.5277 | 27.0654 | 39.593 | 0.01
6.4248 | 9.2124 | 8.4248 | 7.4248 | 10.6371 | 12.6371 | 9.2124 | 16.6371 | 27.2743 | 39.9114 | 6.4248 | 9.2124 | 8.4248 | 7.4248 | 10.6471 | 12.6371 | 9.2124 | 16.6371 | 27.2843 | 39.9214 | 0.01
4.0788 | 8.0394 | 6.0788 | 5.0788 | 7.1181 | 9.1181 | 8.0394 | 13.1181 | 20.2363 | 29.3544 | 4.0788 | 8.0394 | 6.0788 | 5.0788 | 7.1281 | 9.1181 | 8.0394 | 13.1181 | 20.2463 | 29.3644 | 0.01
3.7415 | 7.8708 | 5.7415 | 4.7415 | 6.6123 | 8.6123 | 7.8708 | 12.6123 | 19.2246 | 27.8368 | 3.7415 | 7.8708 | 5.7415 | 4.7415 | 6.6223 | 8.6123 | 7.8708 | 12.6123 | 19.2346 | 27.8468 | 0.01
7.8238 | 9.9119 | 9.8238 | 8.8238 | 12.7357 | 14.7357 | 9.9119 | 18.7357 | 31.4713 | 46.207 | 7.8238 | 9.9119 | 9.8238 | 8.8238 | 12.7457 | 14.7357 | 9.9119 | 18.7357 | 31.4813 | 46.217 | 0.01
5.4348 | 8.7174 | 7.4348 | 6.4348 | 9.1522 | 11.1522 | 8.7174 | 15.1522 | 24.3044 | 35.4567 | 5.4348 | 8.7174 | 7.4348 | 6.4348 | 9.1622 | 11.1522 | 8.7174 | 15.1522 | 24.3144 | 35.4667 | 0.01
4.2646 | 8.1323 | 6.2646 | 5.2646 | 7.397 | 9.397 | 8.1323 | 13.397 | 20.7939 | 30.1909 | 4.2646 | 8.1323 | 6.2646 | 5.2646 | 7.407 | 9.397 | 8.1323 | 13.397 | 20.8039 | 30.2009 | 0.01
5.7679 | 8.884 | 7.7679 | 6.7679 | 9.6519 | 11.6519 | 8.884 | 15.6519 | 25.3038 | 36.9556 | 5.7679 | 8.884 | 7.7679 | 6.7679 | 9.6619 | 11.6519 | 8.884 | 15.6519 | 25.3138 | 36.9656 | 0.01
6.0709 | 9.0355 | 8.0709 | 7.0709 | 10.1064 | 12.1064 | 9.0355 | 16.1064 | 26.2128 | 38.3192 | 6.0709 | 9.0355 | 8.0709 | 7.0709 | 10.1164 | 12.1064 | 9.0355 | 16.1064 | 26.2228 | 38.3292 | 0.01
7.1335 | 9.5668 | 9.1335 | 8.1335 | 11.7003 | 13.7003 | 9.5668 | 17.7003 | 29.4005 | 43.1008 | 7.1335 | 9.5668 | 9.1335 | 8.1335 | 11.7103 | 13.7003 | 9.5668 | 17.7003 | 29.4105 | 43.1108 | 0.01
7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8885 | 13.8785 | 9.6262 | 17.8785 | 29.767 | 43.6455 | 0.01
1.7153 | 6.8577 | 3.7153 | 2.7153 | 3.573 | 5.573 | 6.8577 | 9.573 | 13.146 | 18.719 | 1.7153 | 6.8577 | 3.7153 | 2.7153 | 3.583 | 5.573 | 6.8577 | 9.573 | 13.156 | 18.729 | 0.01
2.3377 | 7.1689 | 4.3377 | 3.3377 | 4.5066 | 6.5066 | 7.1689 | 10.5066 | 15.0132 | 21.5197 | 2.3377 | 7.1689 | 4.3377 | 3.3377 | 4.5166 | 6.5066 | 7.1689 | 10.5066 | 15.0232 | 21.5297 | 0.01
4.5542 | 8.2771 | 6.5542 | 5.5542 | 7.8313 | 9.8313 | 8.2771 | 13.8313 | 21.6626 | 31.4939 | 4.5542 | 8.2771 | 6.5542 | 5.5542 | 7.8413 | 9.8313 | 8.2771 | 13.8313 | 21.6726 | 31.5039 | 0.01
8.0371 | 10.0185 | 10.0371 | 9.0371 | 13.0556 | 15.0556 | 10.0185 | 19.0556 | 32.1113 | 47.1669 | 8.0371 | 10.0185 | 10.0371 | 9.0371 | 13.0656 | 15.0556 | 10.0185 | 19.0556 | 32.1213 | 47.1769 | 0.01
9.1147 | 10.5573 | 11.1147 | 10.1147 | 14.672 | 16.672 | 10.5573 | 20.672 | 35.3441 | 52.0161 | 9.1147 | 10.5573 | 11.1147 | 10.1147 | 14.682 | 16.672 | 10.5573 | 20.672 | 35.3541 | 52.0261 | 0.01
6.8241 | 9.412 | 8.8241 | 7.8241 | 11.2361 | 13.2361 | 9.412 | 17.2361 | 28.4722 | 41.7083 | 6.8241 | 9.412 | 8.8241 | 7.8241 | 11.2461 | 13.2361 | 9.412 | 17.2361 | 28.4822 | 41.7183 | 0.01
6.7062 | 9.3531 | 8.7062 | 7.7062 | 11.0593 | 13.0593 | 9.3531 | 17.0593 | 28.1185 | 41.1778 | 6.7062 | 9.3531 | 8.7062 | 7.7062 | 11.0693 | 13.0593 | 9.3531 | 17.0593 | 28.1285 | 41.1878 | 0.01
5.2576 | 8.6288 | 7.2576 | 6.2576 | 8.8863 | 10.8863 | 8.6288 | 14.8863 | 23.7727 | 34.659 | 5.2576 | 8.6288 | 7.2576 | 6.2576 | 8.8963 | 10.8863 | 8.6288 | 14.8863 | 23.7827 | 34.669 | 0.01
6.3132 | 9.1566 | 8.3132 | 7.3132 | 10.4697 | 12.4697 | 9.1566 | 16.4697 | 26.9395 | 39.4092 | 6.3132 | 9.1566 | 8.3132 | 7.3132 | 10.4797 | 12.4697 | 9.1566 | 16.4697 | 26.9495 | 39.4192 | 0.01
5.6124 | 8.8062 | 7.6124 | 6.6124 | 9.4186 | 11.4186 | 8.8062 | 15.4186 | 24.8373 | 36.2559 | 5.6124 | 8.8062 | 7.6124 | 6.6124 | 9.4286 | 11.4186 | 8.8062 | 15.4186 | 24.8473 | 36.2659 | 0.01
4.4577 | 8.2289 | 6.4577 | 5.4577 | 7.6866 | 9.6866 | 8.2289 | 13.6866 | 21.3732 | 31.0598 | 4.4577 | 8.2289 | 6.4577 | 5.4577 | 7.6966 | 9.6866 | 8.2289 | 13.6866 | 21.3832 | 31.0698 | 0.01
7.1172 | 9.5586 | 9.1172 | 8.1172 | 11.6758 | 13.6758 | 9.5586 | 17.6758 | 29.3516 | 43.0274 | 7.1172 | 9.5586 | 9.1172 | 8.1172 | 11.6858 | 13.6758 | 9.5586 | 17.6758 | 29.3616 | 43.0374 | 0.01
1.8832 | 6.9416 | 3.8832 | 2.8832 | 3.8248 | 5.8248 | 6.9416 | 9.8248 | 13.6496 | 19.4744 | 1.8832 | 6.9416 | 3.8832 | 2.8832 | 3.8348 | 5.8248 | 6.9416 | 9.8248 | 13.6596 | 19.4844 | 0.01
9.3963 | 10.6981 | 11.3963 | 10.3963 | 15.0944 | 17.0944 | 10.6981 | 21.0944 | 36.1889 | 53.2833 | 9.3963 | 10.6981 | 11.3963 | 10.3963 | 15.1044 | 17.0944 | 10.6981 | 21.0944 | 36.1989 | 53.2933 | 0.01
5.7522 | 8.8761 | 7.7522 | 6.7522 | 9.6283 | 11.6283 | 8.8761 | 15.6283 | 25.2566 | 36.8849 | 5.7522 | 8.8761 | 7.7522 | 6.7522 | 9.6383 | 11.6283 | 8.8761 | 15.6283 | 25.2666 | 36.8949 | 0.01
8.7802 | 10.3901 | 10.7802 | 9.7802 | 14.1703 | 16.1703 | 10.3901 | 20.1703 | 34.3407 | 50.511 | 8.7802 | 10.3901 | 10.7802 | 9.7802 | 14.1803 | 16.1703 | 10.3901 | 20.1703 | 34.3507 | 50.521 | 0.01
6.4029 | 9.2014 | 8.4029 | 7.4029 | 10.6043 | 12.6043 | 9.2014 | 16.6043 | 27.2086 | 39.8129 | 6.4029 | 9.2014 | 8.4029 | 7.4029 | 10.6143 | 12.6043 | 9.2014 | 16.6043 | 27.2186 | 39.8229 | 0.01
3.783 | 7.8915 | 5.783 | 4.783 | 6.6745 | 8.6745 | 7.8915 | 12.6745 | 19.349 | 28.0235 | 3.783 | 7.8915 | 5.783 | 4.783 | 6.6845 | 8.6745 | 7.8915 | 12.6745 | 19.359 | 28.0335 | 0.01
4.0209 | 8.0105 | 6.0209 | 5.0209 | 7.0314 | 9.0314 | 8.0105 | 13.0314 | 20.0627 | 29.0941 | 4.0209 | 8.0105 | 6.0209 | 5.0209 | 7.0414 | 9.0314 | 8.0105 | 13.0314 | 20.0727 | 29.1041 | 0.01
6.4079 | 9.2039 | 8.4079 | 7.4079 | 10.6118 | 12.6118 | 9.2039 | 16.6118 | 27.2236 | 39.8354 | 6.4079 | 9.2039 | 8.4079 | 7.4079 | 10.6218 | 12.6118 | 9.2039 | 16.6118 | 27.2336 | 39.8454 | 0.01
6.5453 | 9.2727 | 8.5453 | 7.5453 | 10.818 | 12.818 | 9.2727 | 16.818 | 27.6359 | 40.4539 | 6.5453 | 9.2727 | 8.5453 | 7.5453 | 10.828 | 12.818 | 9.2727 | 16.818 | 27.6459 | 40.4639 | 0.01
7.6805 | 9.8402 | 9.6805 | 8.6805 | 12.5207 | 14.5207 | 9.8402 | 18.5207 | 31.0415 | 45.5622 | 7.6805 | 9.8402 | 9.6805 | 8.6805 | 12.5307 | 14.5207 | 9.8402 | 18.5207 | 31.0515 | 45.5722 | 0.01
6.1081 | 9.0541 | 8.1081 | 7.1081 | 10.1622 | 12.1622 | 9.0541 | 16.1622 | 26.3244 | 38.4866 | 6.1081 | 9.0541 | 8.1081 | 7.1081 | 10.1722 | 12.1622 | 9.0541 | 16.1622 | 26.3344 | 38.4966 | 0.01
6.5904 | 9.2952 | 8.5904 | 7.5904 | 10.8856 | 12.8856 | 9.2952 | 16.8856 | 27.7712 | 40.6568 | 6.5904 | 9.2952 | 8.5904 | 7.5904 | 10.8956 | 12.8856 | 9.2952 | 16.8856 | 27.7812 | 40.6668 | 0.01
6.4252 | 9.2126 | 8.4252 | 7.4252 | 10.6378 | 12.6378 | 9.2126 | 16.6378 | 27.2757 | 39.9135 | 6.4252 | 9.2126 | 8.4252 | 7.4252 | 10.6478 | 12.6378 | 9.2126 | 16.6378 | 27.2857 | 39.9235 | 0.01
5.1021 | 8.551 | 7.1021 | 6.1021 | 8.6531 | 10.6531 | 8.551 | 14.6531 | 23.3063 | 33.9594 | 5.1021 | 8.551 | 7.1021 | 6.1021 | 8.6631 | 10.6531 | 8.551 | 14.6531 | 23.3163 | 33.9694 | 0.01
5.7627 | 8.8813 | 7.7627 | 6.7627 | 9.644 | 11.644 | 8.8813 | 15.644 | 25.288 | 36.9321 | 5.7627 | 8.8813 | 7.7627 | 6.7627 | 9.654 | 11.644 | 8.8813 | 15.644 | 25.298 | 36.9421 | 0.01
6.6646 | 9.3323 | 8.6646 | 7.6646 | 10.997 | 12.997 | 9.3323 | 16.997 | 27.9939 | 40.9909 | 6.6646 | 9.3323 | 8.6646 | 7.6646 | 11.007 | 12.997 | 9.3323 | 16.997 | 28.0039 | 41.0009 | 0.01
3.2081 | 7.604 | 5.2081 | 4.2081 | 5.8121 | 7.8121 | 7.604 | 11.8121 | 17.6242 | 25.4363 | 3.2081 | 7.604 | 5.2081 | 4.2081 | 5.8221 | 7.8121 | 7.604 | 11.8121 | 17.6342 | 25.4463 | 0.01
5.1092 | 8.5546 | 7.1092 | 6.1092 | 8.6638 | 10.6638 | 8.5546 | 14.6638 | 23.3276 | 33.9913 | 5.1092 | 8.5546 | 7.1092 | 6.1092 | 8.6738 | 10.6638 | 8.5546 | 14.6638 | 23.3376 | 34.0013 | 0.01
6.6987 | 9.3493 | 8.6987 | 7.6987 | 11.048 | 13.048 | 9.3493 | 17.048 | 28.0961 | 41.1441 | 6.6987 | 9.3493 | 8.6987 | 7.6987 | 11.058 | 13.048 | 9.3493 | 17.048 | 28.1061 | 41.1541 | 0.01
6.0901 | 9.045 | 8.0901 | 7.0901 | 10.1351 | 12.1351 | 9.045 | 16.1351 | 26.2702 | 38.4053 | 6.0901 | 9.045 | 8.0901 | 7.0901 | 10.1451 | 12.1351 | 9.045 | 16.1351 | 26.2802 | 38.4153 | 0.01
3.3738 | 7.6869 | 5.3738 | 4.3738 | 6.0607 | 8.0607 | 7.6869 | 12.0607 | 18.1215 | 26.1822 | 3.3738 | 7.6869 | 5.3738 | 4.3738 | 6.0707 | 8.0607 | 7.6869 | 12.0607 | 18.1315 | 26.1922 | 0.01
4.8105 | 8.4053 | 6.8105 | 5.8105 | 8.2158 | 10.2158 | 8.4053 | 14.2158 | 22.4316 | 32.6474 | 4.8105 | 8.4053 | 6.8105 | 5.8105 | 8.2258 | 10.2158 | 8.4053 | 14.2158 | 22.4416 | 32.6574 | 0.01
7.522 | 9.761 | 9.522 | 8.522 | 12.2829 | 14.2829 | 9.761 | 18.2829 | 30.5659 | 44.8488 | 7.522 | 9.761 | 9.522 | 8.522 | 12.2929 | 14.2829 | 9.761 | 18.2829 | 30.5759 | 44.8588 | 0.01
4.9713 | 8.4857 | 6.9713 | 5.9713 | 8.457 | 10.457 | 8.4857 | 14.457 | 22.9139 | 33.3709 | 4.9713 | 8.4857 | 6.9713 | 5.9713 | 8.467 | 10.457 | 8.4857 | 14.457 | 22.9239 | 33.3809 | 0.01
6.749 | 9.3745 | 8.749 | 7.749 | 11.1235 | 13.1235 | 9.3745 | 17.1235 | 28.247 | 41.3705 | 6.749 | 9.3745 | 8.749 | 7.749 | 11.1335 | 13.1235 | 9.3745 | 17.1235 | 28.257 | 41.3805 | 0.01
5.0742 | 8.5371 | 7.0742 | 6.0742 | 8.6114 | 10.6114 | 8.5371 | 14.6114 | 23.2227 | 33.8341 | 5.0742 | 8.5371 | 7.0742 | 6.0742 | 8.6214 | 10.6114 | 8.5371 | 14.6114 | 23.2327 | 33.8441 | 0.01
4.7646 | 8.3823 | 6.7646 | 5.7646 | 8.1468 | 10.1468 | 8.3823 | 14.1468 | 22.2937 | 32.4405 | 4.7646 | 8.3823 | 6.7646 | 5.7646 | 8.1568 | 10.1468 | 8.3823 | 14.1468 | 22.3037 | 32.4505 | 0.01
7.389 | 9.6945 | 9.389 | 8.389 | 12.0834 | 14.0834 | 9.6945 | 18.0834 | 30.1669 | 44.2503 | 7.389 | 9.6945 | 9.389 | 8.389 | 12.0934 | 14.0834 | 9.6945 | 18.0834 | 30.1769 | 44.2603 | 0.01
2.893 | 7.4465 | 4.893 | 3.893 | 5.3395 | 7.3395 | 7.4465 | 11.3395 | 16.679 | 24.0185 | 2.893 | 7.4465 | 4.893 | 3.893 | 5.3495 | 7.3395 | 7.4465 | 11.3395 | 16.689 | 24.0285 | 0.01
3.3349 | 7.6675 | 5.3349 | 4.3349 | 6.0024 | 8.0024 | 7.6675 | 12.0024 | 18.0048 | 26.0072 | 3.3349 | 7.6675 | 5.3349 | 4.3349 | 6.0124 | 8.0024 | 7.6675 | 12.0024 | 18.0148 | 26.0172 | 0.01
8.9925 | 10.4963 | 10.9925 | 9.9925 | 14.4888 | 16.4888 | 10.4963 | 20.4888 | 34.9775 | 51.4663 | 8.9925 | 10.4963 | 10.9925 | 9.9925 | 14.4988 | 16.4888 | 10.4963 | 20.4888 | 34.9875 | 51.4763 | 0.01
7.789 | 9.8945 | 9.789 | 8.789 | 12.6836 | 14.6836 | 9.8945 | 18.6836 | 31.3671 | 46.0507 | 7.789 | 9.8945 | 9.789 | 8.789 | 12.6936 | 14.6836 | 9.8945 | 18.6836 | 31.3771 | 46.0607 | 0.01
7.8333 | 9.9167 | 9.8333 | 8.8333 | 12.75 | 14.75 | 9.9167 | 18.75 | 31.4999 | 46.2499 | 7.8333 | 9.9167 | 9.8333 | 8.8333 | 12.76 | 14.75 | 9.9167 | 18.75 | 31.5099 | 46.2599 | 0.01
7.307 | 9.6535 | 9.307 | 8.307 | 11.9605 | 13.9605 | 9.6535 | 17.9605 | 29.9209 | 43.8814 | 7.307 | 9.6535 | 9.307 | 8.307 | 11.9705 | 13.9605 | 9.6535 | 17.9605 | 29.9309 | 43.8914 | 0.01
9.787 | 10.8935 | 11.787 | 10.787 | 15.6805 | 17.6805 | 10.8935 | 21.6805 | 37.361 | 55.0415 | 9.787 | 10.8935 | 11.787 | 10.787 | 15.6905 | 17.6805 | 10.8935 | 21.6805 | 37.371 | 55.0515 | 0.01
5.2045 | 8.6023 | 7.2045 | 6.2045 | 8.8068 | 10.8068 | 8.6023 | 14.8068 | 23.6135 | 34.4203 | 5.2045 | 8.6023 | 7.2045 | 6.2045 | 8.8168 | 10.8068 | 8.6023 | 14.8068 | 23.6235 | 34.4303 | 0.01
5.5481 | 8.7741 | 7.5481 | 6.5481 | 9.3222 | 11.3222 | 8.7741 | 15.3222 | 24.6444 | 35.9666 | 5.5481 | 8.7741 | 7.5481 | 6.5481 | 9.3322 | 11.3222 | 8.7741 | 15.3222 | 24.6544 | 35.9766 | 0.01
2.9819 | 7.491 | 4.9819 | 3.9819 | 5.4729 | 7.4729 | 7.491 | 11.4729 | 16.9458 | 24.4187 | 2.9819 | 7.491 | 4.9819 | 3.9819 | 5.4829 | 7.4729 | 7.491 | 11.4729 | 16.9558 | 24.4287 | 0.01
7.6554 | 9.8277 | 9.6554 | 8.6554 | 12.4831 | 14.4831 | 9.8277 | 18.4831 | 30.9661 | 45.4492 | 7.6554 | 9.8277 | 9.6554 | 8.6554 | 12.4931 | 14.4831 | 9.8277 | 18.4831 | 30.9761 | 45.4592 | 0.01
4.8098 | 8.4049 | 6.8098 | 5.8098 | 8.2147 | 10.2147 | 8.4049 | 14.2147 | 22.4294 | 32.6441 | 4.8098 | 8.4049 | 6.8098 | 5.8098 | 8.2247 | 10.2147 | 8.4049 | 14.2147 | 22.4394 | 32.6541 | 0.01
2.7341 | 7.3671 | 4.7341 | 3.7341 | 5.1012 | 7.1012 | 7.3671 | 11.1012 | 16.2023 | 23.3035 | 2.7341 | 7.3671 | 4.7341 | 3.7341 | 5.1112 | 7.1012 | 7.3671 | 11.1012 | 16.2123 | 23.3135 | 0.01
8.5249 | 10.2624 | 10.5249 | 9.5249 | 13.7873 | 15.7873 | 10.2624 | 19.7873 | 33.5746 | 49.3619 | 8.5249 | 10.2624 | 10.5249 | 9.5249 | 13.7973 | 15.7873 | 10.2624 | 19.7873 | 33.5846 | 49.3719 | 0.01
8.5457 | 10.2729 | 10.5457 | 9.5457 | 13.8186 | 15.8186 | 10.2729 | 19.8186 | 33.6371 | 49.4557 | 8.5457 | 10.2729 | 10.5457 | 9.5457 | 13.8286 | 15.8186 | 10.2729 | 19.8186 | 33.6471 | 49.4657 | 0.01
6.6239 | 9.3119 | 8.6239 | 7.6239 | 10.9358 | 12.9358 | 9.3119 | 16.9358 | 27.8716 | 40.8074 | 6.6239 | 9.3119 | 8.6239 | 7.6239 | 10.9458 | 12.9358 | 9.3119 | 16.9358 | 27.8816 | 40.8174 | 0.01
7.2382 | 9.6191 | 9.2382 | 8.2382 | 11.8573 | 13.8573 | 9.6191 | 17.8573 | 29.7147 | 43.572 | 7.2382 | 9.6191 | 9.2382 | 8.2382 | 11.8673 | 13.8573 | 9.6191 | 17.8573 | 29.7247 | 43.582 | 0.01
6.7582 | 9.3791 | 8.7582 | 7.7582 | 11.1373 | 13.1373 | 9.3791 | 17.1373 | 28.2746 | 41.4119 | 6.7582 | 9.3791 | 8.7582 | 7.7582 | 11.1473 | 13.1373 | 9.3791 | 17.1373 | 28.2846 | 41.4219 | 0.01
5.4894 | 8.7447 | 7.4894 | 6.4894 | 9.2341 | 11.2341 | 8.7447 | 15.2341 | 24.4682 | 35.7022 | 5.4894 | 8.7447 | 7.4894 | 6.4894 | 9.2441 | 11.2341 | 8.7447 | 15.2341 | 24.4782 | 35.7122 | 0.01
5.7659 | 8.883 | 7.7659 | 6.7659 | 9.6489 | 11.6489 | 8.883 | 15.6489 | 25.2977 | 36.9466 | 5.7659 | 8.883 | 7.7659 | 6.7659 | 9.6589 | 11.6489 | 8.883 | 15.6489 | 25.3077 | 36.9566 | 0.01
5.7573 | 8.8786 | 7.7573 | 6.7573 | 9.6359 | 11.6359 | 8.8786 | 15.6359 | 25.2719 | 36.9078 | 5.7573 | 8.8786 | 7.7573 | 6.7573 | 9.6459 | 11.6359 | 8.8786 | 15.6359 | 25.2819 | 36.9178 | 0.01
4.4028 | 8.2014 | 6.4028 | 5.4028 | 7.6042 | 9.6042 | 8.2014 | 13.6042 | 21.2083 | 30.8125 | 4.4028 | 8.2014 | 6.4028 | 5.4028 | 7.6142 | 9.6042 | 8.2014 | 13.6042 | 21.2183 | 30.8225 | 0.01
5.7536 | 8.8768 | 7.7536 | 6.7536 | 9.6304 | 11.6304 | 8.8768 | 15.6304 | 25.2608 | 36.8911 | 5.7536 | 8.8768 | 7.7536 | 6.7536 | 9.6404 | 11.6304 | 8.8768 | 15.6304 | 25.2708 | 36.9011 | 0.01
5.0303 | 8.5151 | 7.0303 | 6.0303 | 8.5454 | 10.5454 | 8.5151 | 14.5454 | 23.0908 | 33.6361 | 5.0303 | 8.5151 | 7.0303 | 6.0303 | 8.5554 | 10.5454 | 8.5151 | 14.5454 | 23.1008 | 33.6461 | 0.01
3.0131 | 7.5066 | 5.0131 | 4.0131 | 5.5197 | 7.5197 | 7.5066 | 11.5197 | 17.0393 | 24.559 | 3.0131 | 7.5066 | 5.0131 | 4.0131 | 5.5297 | 7.5197 | 7.5066 | 11.5197 | 17.0493 | 24.569 | 0.01
2.4946 | 7.2473 | 4.4946 | 3.4946 | 4.7419 | 6.7419 | 7.2473 | 10.7419 | 15.4838 | 22.2257 | 2.4946 | 7.2473 | 4.4946 | 3.4946 | 4.7519 | 6.7419 | 7.2473 | 10.7419 | 15.4938 | 22.2357 | 0.01
3.8321 | 7.9161 | 5.8321 | 4.8321 | 6.7482 | 8.7482 | 7.9161 | 12.7482 | 19.4963 | 28.2445 | 3.8321 | 7.9161 | 5.8321 | 4.8321 | 6.7582 | 8.7482 | 7.9161 | 12.7482 | 19.5063 | 28.2545 | 0.01
3.881 | 7.9405 | 5.881 | 4.881 | 6.8215 | 8.8215 | 7.9405 | 12.8215 | 19.6431 | 28.4646 | 3.881 | 7.9405 | 5.881 | 4.881 | 6.8315 | 8.8215 | 7.9405 | 12.8215 | 19.6531 | 28.4746 | 0.01
6.8478 | 9.4239 | 8.8478 | 7.8478 | 11.2716 | 13.2716 | 9.4239 | 17.2716 | 28.5433 | 41.8149 | 6.8478 | 9.4239 | 8.8478 | 7.8478 | 11.2816 | 13.2716 | 9.4239 | 17.2716 | 28.5533 | 41.8249 | 0.01
6.8117 | 9.4059 | 8.8117 | 7.8117 | 11.2176 | 13.2176 | 9.4059 | 17.2176 | 28.4352 | 41.6529 | 6.8117 | 9.4059 | 8.8117 | 7.8117 | 11.2276 | 13.2176 | 9.4059 | 17.2176 | 28.4452 | 41.6629 | 0.01
2.5649 | 7.2825 | 4.5649 | 3.5649 | 4.8474 | 6.8474 | 7.2825 | 10.8474 | 15.6947 | 22.5421 | 2.5649 | 7.2825 | 4.5649 | 3.5649 | 4.8574 | 6.8474 | 7.2825 | 10.8474 | 15.7047 | 22.5521 | 0.01
4.502 | 8.251 | 6.502 | 5.502 | 7.7531 | 9.7531 | 8.251 | 13.7531 | 21.5061 | 31.2592 | 4.502 | 8.251 | 6.502 | 5.502 | 7.7631 | 9.7531 | 8.251 | 13.7531 | 21.5161 | 31.2692 | 0.01
8.0192 | 10.0096 | 10.0192 | 9.0192 | 13.0288 | 15.0288 | 10.0096 | 19.0288 | 32.0575 | 47.0863 | 8.0192 | 10.0096 | 10.0192 | 9.0192 | 13.0388 | 15.0288 | 10.0096 | 19.0288 | 32.0675 | 47.0963 | 0.01
5.5992 | 8.7996 | 7.5992 | 6.5992 | 9.3987 | 11.3987 | 8.7996 | 15.3987 | 24.7975 | 36.1962 | 5.5992 | 8.7996 | 7.5992 | 6.5992 | 9.4087 | 11.3987 | 8.7996 | 15.3987 | 24.8075 | 36.2062 | 0.01
3.538 | 7.769 | 5.538 | 4.538 | 6.3071 | 8.3071 | 7.769 | 12.3071 | 18.6141 | 26.9212 | 3.538 | 7.769 | 5.538 | 4.538 | 6.3171 | 8.3071 | 7.769 | 12.3071 | 18.6241 | 26.9312 | 0.01
4.1922 | 8.0961 | 6.1922 | 5.1922 | 7.2882 | 9.2882 | 8.0961 | 13.2882 | 20.5765 | 29.8647 | 4.1922 | 8.0961 | 6.1922 | 5.1922 | 7.2982 | 9.2882 | 8.0961 | 13.2882 | 20.5865 | 29.8747 | 0.01
8.0617 | 10.0308 | 10.0617 | 9.0617 | 13.0925 | 15.0925 | 10.0308 | 19.0925 | 32.185 | 47.2775 | 8.0617 | 10.0308 | 10.0617 | 9.0617 | 13.1025 | 15.0925 | 10.0308 | 19.0925 | 32.195 | 47.2875 | 0.01
7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2433 | 14.2333 | 9.7444 | 18.2333 | 30.4766 | 44.7098 | 0.01
11.8438 | 11.9219 | 13.8438 | 12.8438 | 18.7656 | 20.7656 | 11.9219 | 24.7656 | 43.5313 | 64.2969 | 11.8438 | 11.9219 | 13.8438 | 12.8438 | 18.7756 | 20.7656 | 11.9219 | 24.7656 | 43.5413 | 64.3069 | 0.01
6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.5072 | 12.4972 | 9.1657 | 16.4972 | 27.0043 | 39.5015 | 0.01
8.8082 | 10.4041 | 10.8082 | 9.8082 | 14.2124 | 16.2124 | 10.4041 | 20.2124 | 34.4247 | 50.6371 | 8.8082 | 10.4041 | 10.8082 | 9.8082 | 14.2224 | 16.2124 | 10.4041 | 20.2124 | 34.4347 | 50.6471 | 0.01
7.6294 | 9.8147 | 9.6294 | 8.6294 | 12.4441 | 14.4441 | 9.8147 | 18.4441 | 30.8883 | 45.3324 | 7.6294 | 9.8147 | 9.6294 | 8.6294 | 12.4541 | 14.4441 | 9.8147 | 18.4441 | 30.8983 | 45.3424 | 0.01
6.2816 | 9.1408 | 8.2816 | 7.2816 | 10.4224 | 12.4224 | 9.1408 | 16.4224 | 26.8448 | 39.2672 | 6.2816 | 9.1408 | 8.2816 | 7.2816 | 10.4324 | 12.4224 | 9.1408 | 16.4224 | 26.8548 | 39.2772 | 0.01
2.9948 | 7.4974 | 4.9948 | 3.9948 | 5.4922 | 7.4922 | 7.4974 | 11.4922 | 16.9843 | 24.4765 | 2.9948 | 7.4974 | 4.9948 | 3.9948 | 5.5022 | 7.4922 | 7.4974 | 11.4922 | 16.9943 | 24.4865 | 0.01
7.6577 | 9.8289 | 9.6577 | 8.6577 | 12.4866 | 14.4866 | 9.8289 | 18.4866 | 30.9732 | 45.4598 | 7.6577 | 9.8289 | 9.6577 | 8.6577 | 12.4966 | 14.4866 | 9.8289 | 18.4866 | 30.9832 | 45.4698 | 0.01
5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.656 | 10.646 | 8.5487 | 14.646 | 23.302 | 33.9481 | 0.01
6.3502 | 9.1751 | 8.3502 | 7.3502 | 10.5253 | 12.5253 | 9.1751 | 16.5253 | 27.0507 | 39.576 | 6.3502 | 9.1751 | 8.3502 | 7.3502 | 10.5353 | 12.5253 | 9.1751 | 16.5253 | 27.0607 | 39.586 | 0.01
8.2841 | 10.1421 | 10.2841 | 9.2841 | 13.4262 | 15.4262 | 10.1421 | 19.4262 | 32.8524 | 48.2786 | 8.2841 | 10.1421 | 10.2841 | 9.2841 | 13.4362 | 15.4262 | 10.1421 | 19.4262 | 32.8624 | 48.2886 | 0.01
7.4494 | 9.7247 | 9.4494 | 8.4494 | 12.1741 | 14.1741 | 9.7247 | 18.1741 | 30.3481 | 44.5222 | 7.4494 | 9.7247 | 9.4494 | 8.4494 | 12.1841 | 14.1741 | 9.7247 | 18.1741 | 30.3581 | 44.5322 | 0.01
5.769 | 8.8845 | 7.769 | 6.769 | 9.6535 | 11.6535 | 8.8845 | 15.6535 | 25.307 | 36.9605 | 5.769 | 8.8845 | 7.769 | 6.769 | 9.6635 | 11.6535 | 8.8845 | 15.6535 | 25.317 | 36.9705 | 0.01
5.8084 | 8.9042 | 7.8084 | 6.8084 | 9.7126 | 11.7126 | 8.9042 | 15.7126 | 25.4252 | 37.1377 | 5.8084 | 8.9042 | 7.8084 | 6.8084 | 9.7226 | 11.7126 | 8.9042 | 15.7126 | 25.4352 | 37.1477 | 0.01
4.3983 | 8.1992 | 6.3983 | 5.3983 | 7.5975 | 9.5975 | 8.1992 | 13.5975 | 21.195 | 30.7925 | 4.3983 | 8.1992 | 6.3983 | 5.3983 | 7.6075 | 9.5975 | 8.1992 | 13.5975 | 21.205 | 30.8025 | 0.01
4.0729 | 8.0365 | 6.0729 | 5.0729 | 7.1094 | 9.1094 | 8.0365 | 13.1094 | 20.2188 | 29.3281 | 4.0729 | 8.0365 | 6.0729 | 5.0729 | 7.1194 | 9.1094 | 8.0365 | 13.1094 | 20.2288 | 29.3381 | 0.01
6.5512 | 9.2756 | 8.5512 | 7.5512 | 10.8268 | 12.8268 | 9.2756 | 16.8268 | 27.6536 | 40.4803 | 6.5512 | 9.2756 | 8.5512 | 7.5512 | 10.8368 | 12.8268 | 9.2756 | 16.8268 | 27.6636 | 40.4903 | 0.01
3.2266 | 7.6133 | 5.2266 | 4.2266 | 5.8399 | 7.8399 | 7.6133 | 11.8399 | 17.6798 | 25.5197 | 3.2266 | 7.6133 | 5.2266 | 4.2266 | 5.8499 | 7.8399 | 7.6133 | 11.8399 | 17.6898 | 25.5297 | 0.01
6.4914 | 9.2457 | 8.4914 | 7.4914 | 10.737 | 12.737 | 9.2457 | 16.737 | 27.4741 | 40.2111 | 6.4914 | 9.2457 | 8.4914 | 7.4914 | 10.747 | 12.737 | 9.2457 | 16.737 | 27.4841 | 40.2211 | 0.01
7.4177 | 9.7089 | 9.4177 | 8.4177 | 12.1266 | 14.1266 | 9.7089 | 18.1266 | 30.2532 | 44.3798 | 7.4177 | 9.7089 | 9.4177 | 8.4177 | 12.1366 | 14.1266 | 9.7089 | 18.1266 | 30.2632 | 44.3898 | 0.01
3.4213 | 7.7106 | 5.4213 | 4.4213 | 6.1319 | 8.1319 | 7.7106 | 12.1319 | 18.2638 | 26.3957 | 3.4213 | 7.7106 | 5.4213 | 4.4213 | 6.1419 | 8.1319 | 7.7106 | 12.1319 | 18.2738 | 26.4057 | 0.01
4.6599 | 8.3299 | 6.6599 | 5.6599 | 7.9898 | 9.9898 | 8.3299 | 13.9898 | 21.9797 | 31.9695 | 4.6599 | 8.3299 | 6.6599 | 5.6599 | 7.9998 | 9.9898 | 8.3299 | 13.9898 | 21.9897 | 31.9795 | 0.01
7.9283 | 9.9641 | 9.9283 | 8.9283 | 12.8924 | 14.8924 | 9.9641 | 18.8924 | 31.7849 | 46.6773 | 7.9283 | 9.9641 | 9.9283 | 8.9283 | 12.9024 | 14.8924 | 9.9641 | 18.8924 | 31.7949 | 46.6873 | 0.01
8.1195 | 10.0598 | 10.1195 | 9.1195 | 13.1793 | 15.1793 | 10.0598 | 19.1793 | 32.3586 | 47.5378 | 8.1195 | 10.0598 | 10.1195 | 9.1195 | 13.1893 | 15.1793 | 10.0598 | 19.1793 | 32.3686 | 47.5478 | 0.01
5.1511 | 8.5755 | 7.1511 | 6.1511 | 8.7266 | 10.7266 | 8.5755 | 14.7266 | 23.4532 | 34.1798 | 5.1511 | 8.5755 | 7.1511 | 6.1511 | 8.7366 | 10.7266 | 8.5755 | 14.7266 | 23.4632 | 34.1898 | 0.01
4.3661 | 8.183 | 6.3661 | 5.3661 | 7.5491 | 9.5491 | 8.183 | 13.5491 | 21.0983 | 30.6474 | 4.3661 | 8.183 | 6.3661 | 5.3661 | 7.5591 | 9.5491 | 8.183 | 13.5491 | 21.1083 | 30.6574 | 0.01
4.8403 | 8.4202 | 6.8403 | 5.8403 | 8.2605 | 10.2605 | 8.4202 | 14.2605 | 22.521 | 32.7815 | 4.8403 | 8.4202 | 6.8403 | 5.8403 | 8.2705 | 10.2605 | 8.4202 | 14.2605 | 22.531 | 32.7915 | 0.01
6.6155 | 9.3078 | 8.6155 | 7.6155 | 10.9233 | 12.9233 | 9.3078 | 16.9233 | 27.8466 | 40.7699 | 6.6155 | 9.3078 | 8.6155 | 7.6155 | 10.9333 | 12.9233 | 9.3078 | 16.9233 | 27.8566 | 40.7799 | 0.01
6.1813 | 9.0907 | 8.1813 | 7.1813 | 10.272 | 12.272 | 9.0907 | 16.272 | 26.544 | 38.8159 | 6.1813 | 9.0907 | 8.1813 | 7.1813 | 10.282 | 12.272 | 9.0907 | 16.272 | 26.554 | 38.8259 | 0.01
6.6324 | 9.3162 | 8.6324 | 7.6324 | 10.9486 | 12.9486 | 9.3162 | 16.9486 | 27.8972 | 40.8458 | 6.6324 | 9.3162 | 8.6324 | 7.6324 | 10.9586 | 12.9486 | 9.3162 | 16.9486 | 27.9072 | 40.8558 | 0.01
5.7216 | 8.8608 | 7.7216 | 6.7216 | 9.5825 | 11.5825 | 8.8608 | 15.5825 | 25.1649 | 36.7474 | 5.7216 | 8.8608 | 7.7216 | 6.7216 | 9.5925 | 11.5825 | 8.8608 | 15.5825 | 25.1749 | 36.7574 | 0.01
5.8658 | 8.9329 | 7.8658 | 6.8658 | 9.7987 | 11.7987 | 8.9329 | 15.7987 | 25.5974 | 37.3961 | 5.8658 | 8.9329 | 7.8658 | 6.8658 | 9.8087 | 11.7987 | 8.9329 | 15.7987 | 25.6074 | 37.4061 | 0.01
4.2094 | 8.1047 | 6.2094 | 5.2094 | 7.314 | 9.314 | 8.1047 | 13.314 | 20.6281 | 29.9421 | 4.2094 | 8.1047 | 6.2094 | 5.2094 | 7.324 | 9.314 | 8.1047 | 13.314 | 20.6381 | 29.9521 | 0.01
5.2214 | 8.6107 | 7.2214 | 6.2214 | 8.8321 | 10.8321 | 8.6107 | 14.8321 | 23.6641 | 34.4962 | 5.2214 | 8.6107 | 7.2214 | 6.2214 | 8.8421 | 10.8321 | 8.6107 | 14.8321 | 23.6741 | 34.5062 | 0.01
5.3992 | 8.6996 | 7.3992 | 6.3992 | 9.0988 | 11.0988 | 8.6996 | 15.0988 | 24.1976 | 35.2965 | 5.3992 | 8.6996 | 7.3992 | 6.3992 | 9.1088 | 11.0988 | 8.6996 | 15.0988 | 24.2076 | 35.3065 | 0.01
9.2618 | 10.6309 | 11.2618 | 10.2618 | 14.8927 | 16.8927 | 10.6309 | 20.8927 | 35.7855 | 52.6782 | 9.2618 | 10.6309 | 11.2618 | 10.2618 | 14.9027 | 16.8927 | 10.6309 | 20.8927 | 35.7955 | 52.6882 | 0.01
2.5164 | 7.2582 | 4.5164 | 3.5164 | 4.7746 | 6.7746 | 7.2582 | 10.7746 | 15.5493 | 22.3239 | 2.5164 | 7.2582 | 4.5164 | 3.5164 | 4.7846 | 6.7746 | 7.2582 | 10.7746 | 15.5593 | 22.3339 | 0.01
6.053 | 9.0265 | 8.053 | 7.053 | 10.0795 | 12.0795 | 9.0265 | 16.0795 | 26.1591 | 38.2386 | 6.053 | 9.0265 | 8.053 | 7.053 | 10.0895 | 12.0795 | 9.0265 | 16.0795 | 26.1691 | 38.2486 | 0.01
11.0086 | 11.5043 | 13.0086 | 12.0086 | 17.5129 | 19.5129 | 11.5043 | 23.5129 | 41.0259 | 60.5388 | 11.0086 | 11.5043 | 13.0086 | 12.0086 | 17.5229 | 19.5129 | 11.5043 | 23.5129 | 41.0359 | 60.5488 | 0.01
9.7368 | 10.8684 | 11.7368 | 10.7368 | 15.6052 | 17.6052 | 10.8684 | 21.6052 | 37.2103 | 54.8155 | 9.7368 | 10.8684 | 11.7368 | 10.7368 | 15.6152 | 17.6052 | 10.8684 | 21.6052 | 37.2203 | 54.8255 | 0.01
9.4739 | 10.7369 | 11.4739 | 10.4739 | 15.2108 | 17.2108 | 10.7369 | 21.2108 | 36.4216 | 53.6323 | 9.4739 | 10.7369 | 11.4739 | 10.4739 | 15.2208 | 17.2108 | 10.7369 | 21.2108 | 36.4316 | 53.6423 | 0.01
4.0971 | 8.0486 | 6.0971 | 5.0971 | 7.1457 | 9.1457 | 8.0486 | 13.1457 | 20.2913 | 29.437 | 4.0971 | 8.0486 | 6.0971 | 5.0971 | 7.1557 | 9.1457 | 8.0486 | 13.1457 | 20.3013 | 29.447 | 0.01
7.1106 | 9.5553 | 9.1106 | 8.1106 | 11.6659 | 13.6659 | 9.5553 | 17.6659 | 29.3318 | 42.9977 | 7.1106 | 9.5553 | 9.1106 | 8.1106 | 11.6759 | 13.6659 | 9.5553 | 17.6659 | 29.3418 | 43.0077 | 0.01
8.668 | 10.334 | 10.668 | 9.668 | 14.0021 | 16.0021 | 10.334 | 20.0021 | 34.0041 | 50.0062 | 8.668 | 10.334 | 10.668 | 9.668 | 14.0121 | 16.0021 | 10.334 | 20.0021 | 34.0141 | 50.0162 | 0.01
5.0877 | 8.5438 | 7.0877 | 6.0877 | 8.6315 | 10.6315 | 8.5438 | 14.6315 | 23.263 | 33.8945 | 5.0877 | 8.5438 | 7.0877 | 6.0877 | 8.6415 | 10.6315 | 8.5438 | 14.6315 | 23.273 | 33.9045 | 0.01
3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.969 | 8.959 | 7.9863 | 12.959 | 19.928 | 28.8869 | 0.01
6.5588 | 9.2794 | 8.5588 | 7.5588 | 10.8382 | 12.8382 | 9.2794 | 16.8382 | 27.6765 | 40.5147 | 6.5588 | 9.2794 | 8.5588 | 7.5588 | 10.8482 | 12.8382 | 9.2794 | 16.8382 | 27.6865 | 40.5247 | 0.01
5.3003 | 8.6502 | 7.3003 | 6.3003 | 8.9505 | 10.9505 | 8.6502 | 14.9505 | 23.901 | 34.8515 | 5.3003 | 8.6502 | 7.3003 | 6.3003 | 8.9605 | 10.9505 | 8.6502 | 14.9505 | 23.911 | 34.8615 | 0.01
5.3086 | 8.6543 | 7.3086 | 6.3086 | 8.9629 | 10.9629 | 8.6543 | 14.9629 | 23.9259 | 34.8888 | 5.3086 | 8.6543 | 7.3086 | 6.3086 | 8.9729 | 10.9629 | 8.6543 | 14.9629 | 23.9359 | 34.8988 | 0.01
4.5764 | 8.2882 | 6.5764 | 5.5764 | 7.8645 | 9.8645 | 8.2882 | 13.8645 | 21.7291 | 31.5936 | 4.5764 | 8.2882 | 6.5764 | 5.5764 | 7.8745 | 9.8645 | 8.2882 | 13.8645 | 21.7391 | 31.6036 | 0.01
5.9923 | 8.9961 | 7.9923 | 6.9923 | 9.9884 | 11.9884 | 8.9961 | 15.9884 | 25.9768 | 37.9652 | 5.9923 | 8.9961 | 7.9923 | 6.9923 | 9.9984 | 11.9884 | 8.9961 | 15.9884 | 25.9868 | 37.9752 | 0.01
2.2553 | 7.1277 | 4.2553 | 3.2553 | 4.383 | 6.383 | 7.1277 | 10.383 | 14.766 | 21.1489 | 2.2553 | 7.1277 | 4.2553 | 3.2553 | 4.393 | 6.383 | 7.1277 | 10.383 | 14.776 | 21.1589 | 0.01
3.77 | 7.885 | 5.77 | 4.77 | 6.6549 | 8.6549 | 7.885 | 12.6549 | 19.3099 | 27.9648 | 3.77 | 7.885 | 5.77 | 4.77 | 6.6649 | 8.6549 | 7.885 | 12.6549 | 19.3199 | 27.9748 | 0.01
5.0845 | 8.5422 | 7.0845 | 6.0845 | 8.6267 | 10.6267 | 8.5422 | 14.6267 | 23.2534 | 33.88 | 5.0845 | 8.5422 | 7.0845 | 6.0845 | 8.6367 | 10.6267 | 8.5422 | 14.6267 | 23.2634 | 33.89 | 0.01
10.4131 | 11.2066 | 12.4131 | 11.4131 | 16.6197 | 18.6197 | 11.2066 | 22.6197 | 39.2394 | 57.8591 | 10.4131 | 11.2066 | 12.4131 | 11.4131 | 16.6297 | 18.6197 | 11.2066 | 22.6197 | 39.2494 | 57.8691 | 0.01
6.5663 | 9.2831 | 8.5663 | 7.5663 | 10.8494 | 12.8494 | 9.2831 | 16.8494 | 27.6989 | 40.5483 | 6.5663 | 9.2831 | 8.5663 | 7.5663 | 10.8594 | 12.8494 | 9.2831 | 16.8494 | 27.7089 | 40.5583 | 0.01
5.6487 | 8.8243 | 7.6487 | 6.6487 | 9.473 | 11.473 | 8.8243 | 15.473 | 24.946 | 36.4191 | 5.6487 | 8.8243 | 7.6487 | 6.6487 | 9.483 | 11.473 | 8.8243 | 15.473 | 24.956 | 36.4291 | 0.01
7.5932 | 9.7966 | 9.5932 | 8.5932 | 12.3899 | 14.3899 | 9.7966 | 18.3899 | 30.7797 | 45.1696 | 7.5932 | 9.7966 | 9.5932 | 8.5932 | 12.3999 | 14.3899 | 9.7966 | 18.3899 | 30.7897 | 45.1796 | 0.01
3.3026 | 7.6513 | 5.3026 | 4.3026 | 5.9539 | 7.9539 | 7.6513 | 11.9539 | 17.9078 | 25.8617 | 3.3026 | 7.6513 | 5.3026 | 4.3026 | 5.9639 | 7.9539 | 7.6513 | 11.9539 | 17.9178 | 25.8717 | 0.01
3.76 | 7.88 | 5.76 | 4.76 | 6.6399 | 8.6399 | 7.88 | 12.6399 | 19.2799 | 27.9198 | 3.76 | 7.88 | 5.76 | 4.76 | 6.6499 | 8.6399 | 7.88 | 12.6399 | 19.2899 | 27.9298 | 0.01
5.8466 | 8.9233 | 7.8466 | 6.8466 | 9.7699 | 11.7699 | 8.9233 | 15.7699 | 25.5399 | 37.3098 | 5.8466 | 8.9233 | 7.8466 | 6.8466 | 9.7799 | 11.7699 | 8.9233 | 15.7699 | 25.5499 | 37.3198 | 0.01
6.6787 | 9.3394 | 8.6787 | 7.6787 | 11.0181 | 13.0181 | 9.3394 | 17.0181 | 28.0362 | 41.0543 | 6.6787 | 9.3394 | 8.6787 | 7.6787 | 11.0281 | 13.0181 | 9.3394 | 17.0181 | 28.0462 | 41.0643 | 0.01
5.4037 | 8.7018 | 7.4037 | 6.4037 | 9.1055 | 11.1055 | 8.7018 | 15.1055 | 24.2111 | 35.3166 | 5.4037 | 8.7018 | 7.4037 | 6.4037 | 9.1155 | 11.1055 | 8.7018 | 15.1055 | 24.2211 | 35.3266 | 0.01
6.474 | 9.237 | 8.474 | 7.474 | 10.711 | 12.711 | 9.237 | 16.711 | 27.4221 | 40.1331 | 6.474 | 9.237 | 8.474 | 7.474 | 10.721 | 12.711 | 9.237 | 16.711 | 27.4321 | 40.1431 | 0.01
6.1767 | 9.0884 | 8.1767 | 7.1767 | 10.2651 | 12.2651 | 9.0884 | 16.2651 | 26.5301 | 38.7952 | 6.1767 | 9.0884 | 8.1767 | 7.1767 | 10.2751 | 12.2651 | 9.0884 | 16.2651 | 26.5401 | 38.8052 | 0.01
6.604 | 9.302 | 8.604 | 7.604 | 10.906 | 12.906 | 9.302 | 16.906 | 27.812 | 40.7179 | 6.604 | 9.302 | 8.604 | 7.604 | 10.916 | 12.906 | 9.302 | 16.906 | 27.822 | 40.7279 | 0.01
4.67 | 8.335 | 6.67 | 5.67 | 8.005 | 10.005 | 8.335 | 14.005 | 22.0101 | 32.0151 | 4.67 | 8.335 | 6.67 | 5.67 | 8.015 | 10.005 | 8.335 | 14.005 | 22.0201 | 32.0251 | 0.01
5.3308 | 8.6654 | 7.3308 | 6.3308 | 8.9962 | 10.9962 | 8.6654 | 14.9962 | 23.9925 | 34.9887 | 5.3308 | 8.6654 | 7.3308 | 6.3308 | 9.0062 | 10.9962 | 8.6654 | 14.9962 | 24.0025 | 34.9987 | 0.01
5.7182 | 8.8591 | 7.7182 | 6.7182 | 9.5774 | 11.5774 | 8.8591 | 15.5774 | 25.1547 | 36.7321 | 5.7182 | 8.8591 | 7.7182 | 6.7182 | 9.5874 | 11.5774 | 8.8591 | 15.5774 | 25.1647 | 36.7421 | 0.01
1.3905 | 6.6952 | 3.3905 | 2.3905 | 3.0857 | 5.0857 | 6.6952 | 9.0857 | 12.1714 | 17.2571 | 1.3905 | 6.6952 | 3.3905 | 2.3905 | 3.0957 | 5.0857 | 6.6952 | 9.0857 | 12.1814 | 17.2671 | 0.01
4.6854 | 8.3427 | 6.6854 | 5.6854 | 8.0282 | 10.0282 | 8.3427 | 14.0282 | 22.0563 | 32.0845 | 4.6854 | 8.3427 | 6.6854 | 5.6854 | 8.0382 | 10.0282 | 8.3427 | 14.0282 | 22.0663 | 32.0945 | 0.01
4.5016 | 8.2508 | 6.5016 | 5.5016 | 7.7525 | 9.7525 | 8.2508 | 13.7525 | 21.5049 | 31.2574 | 4.5016 | 8.2508 | 6.5016 | 5.5016 | 7.7625 | 9.7525 | 8.2508 | 13.7525 | 21.5149 | 31.2674 | 0.01
3.0906 | 7.5453 | 5.0906 | 4.0906 | 5.6359 | 7.6359 | 7.5453 | 11.6359 | 17.2719 | 24.9078 | 3.0906 | 7.5453 | 5.0906 | 4.0906 | 5.6459 | 7.6359 | 7.5453 | 11.6359 | 17.2819 | 24.9178 | 0.01
3.6427 | 7.8213 | 5.6427 | 4.6427 | 6.464 | 8.464 | 7.8213 | 12.464 | 18.928 | 27.392 | 3.6427 | 7.8213 | 5.6427 | 4.6427 | 6.474 | 8.464 | 7.8213 | 12.464 | 18.938 | 27.402 | 0.01
3.7734 | 7.8867 | 5.7734 | 4.7734 | 6.66 | 8.66 | 7.8867 | 12.66 | 19.3201 | 27.9801 | 3.7734 | 7.8867 | 5.7734 | 4.7734 | 6.67 | 8.66 | 7.8867 | 12.66 | 19.3301 | 27.9901 | 0.01
5.5801 | 8.79 | 7.5801 | 6.5801 | 9.3701 | 11.3701 | 8.79 | 15.3701 | 24.7403 | 36.1104 | 5.5801 | 8.79 | 7.5801 | 6.5801 | 9.3801 | 11.3701 | 8.79 | 15.3701 | 24.7503 | 36.1204 | 0.01
7.3028 | 9.6514 | 9.3028 | 8.3028 | 11.9542 | 13.9542 | 9.6514 | 17.9542 | 29.9084 | 43.8626 | 7.3028 | 9.6514 | 9.3028 | 8.3028 | 11.9642 | 13.9542 | 9.6514 | 17.9542 | 29.9184 | 43.8726 | 0.01
4.8107 | 8.4054 | 6.8107 | 5.8107 | 8.2161 | 10.2161 | 8.4054 | 14.2161 | 22.4321 | 32.6482 | 4.8107 | 8.4054 | 6.8107 | 5.8107 | 8.2261 | 10.2161 | 8.4054 | 14.2161 | 22.4421 | 32.6582 | 0.01
6.0516 | 9.0258 | 8.0516 | 7.0516 | 10.0775 | 12.0775 | 9.0258 | 16.0775 | 26.1549 | 38.2324 | 6.0516 | 9.0258 | 8.0516 | 7.0516 | 10.0875 | 12.0775 | 9.0258 | 16.0775 | 26.1649 | 38.2424 | 0.01
7.0705 | 9.5352 | 9.0705 | 8.0705 | 11.6057 | 13.6057 | 9.5352 | 17.6057 | 29.2114 | 42.8171 | 7.0705 | 9.5352 | 9.0705 | 8.0705 | 11.6157 | 13.6057 | 9.5352 | 17.6057 | 29.2214 | 42.8271 | 0.01
7.2568 | 9.6284 | 9.2568 | 8.2568 | 11.8852 | 13.8852 | 9.6284 | 17.8852 | 29.7704 | 43.6556 | 7.2568 | 9.6284 | 9.2568 | 8.2568 | 11.8952 | 13.8852 | 9.6284 | 17.8852 | 29.7804 | 43.6656 | 0.01
5.5195 | 8.7598 | 7.5195 | 6.5195 | 9.2793 | 11.2793 | 8.7598 | 15.2793 | 24.5586 | 35.8378 | 5.5195 | 8.7598 | 7.5195 | 6.5195 | 9.2893 | 11.2793 | 8.7598 | 15.2793 | 24.5686 | 35.8478 | 0.01
7.7236 | 9.8618 | 9.7236 | 8.7236 | 12.5854 | 14.5854 | 9.8618 | 18.5854 | 31.1707 | 45.7561 | 7.7236 | 9.8618 | 9.7236 | 8.7236 | 12.5954 | 14.5854 | 9.8618 | 18.5854 | 31.1807 | 45.7661 | 0.01
7.4454 | 9.7227 | 9.4454 | 8.4454 | 12.1681 | 14.1681 | 9.7227 | 18.1681 | 30.3362 | 44.5043 | 7.4454 | 9.7227 | 9.4454 | 8.4454 | 12.1781 | 14.1681 | 9.7227 | 18.1681 | 30.3462 | 44.5143 | 0.01
7.2098 | 9.6049 | 9.2098 | 8.2098 | 11.8147 | 13.8147 | 9.6049 | 17.8147 | 29.6294 | 43.4441 | 7.2098 | 9.6049 | 9.2098 | 8.2098 | 11.8247 | 13.8147 | 9.6049 | 17.8147 | 29.6394 | 43.4541 | 0.01
8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0815 | 15.0715 | 10.0238 | 19.0715 | 32.153 | 47.2244 | 0.01
5.3983 | 8.6991 | 7.3983 | 6.3983 | 9.0974 | 11.0974 | 8.6991 | 15.0974 | 24.1948 | 35.2922 | 5.3983 | 8.6991 | 7.3983 | 6.3983 | 9.1074 | 11.0974 | 8.6991 | 15.0974 | 24.2048 | 35.3022 | 0.01
8.1214 | 10.0607 | 10.1214 | 9.1214 | 13.1821 | 15.1821 | 10.0607 | 19.1821 | 32.3642 | 47.5463 | 8.1214 | 10.0607 | 10.1214 | 9.1214 | 13.1921 | 15.1821 | 10.0607 | 19.1821 | 32.3742 | 47.5563 | 0.01
5.6079 | 8.8039 | 7.6079 | 6.6079 | 9.4118 | 11.4118 | 8.8039 | 15.4118 | 24.8237 | 36.2355 | 5.6079 | 8.8039 | 7.6079 | 6.6079 | 9.4218 | 11.4118 | 8.8039 | 15.4118 | 24.8337 | 36.2455 | 0.01
6.4616 | 9.2308 | 8.4616 | 7.4616 | 10.6924 | 12.6924 | 9.2308 | 16.6924 | 27.3848 | 40.0772 | 6.4616 | 9.2308 | 8.4616 | 7.4616 | 10.7024 | 12.6924 | 9.2308 | 16.6924 | 27.3948 | 40.0872 | 0.01
5.8819 | 8.9409 | 7.8819 | 6.8819 | 9.8228 | 11.8228 | 8.9409 | 15.8228 | 25.6457 | 37.4685 | 5.8819 | 8.9409 | 7.8819 | 6.8819 | 9.8328 | 11.8228 | 8.9409 | 15.8228 | 25.6557 | 37.4785 | 0.01
3.8915 | 7.9457 | 5.8915 | 4.8915 | 6.8372 | 8.8372 | 7.9457 | 12.8372 | 19.6744 | 28.5115 | 3.8915 | 7.9457 | 5.8915 | 4.8915 | 6.8472 | 8.8372 | 7.9457 | 12.8372 | 19.6844 | 28.5215 | 0.01
3.9971 | 7.9985 | 5.9971 | 4.9971 | 6.9956 | 8.9956 | 7.9985 | 12.9956 | 19.9912 | 28.9868 | 3.9971 | 7.9985 | 5.9971 | 4.9971 | 7.0056 | 8.9956 | 7.9985 | 12.9956 | 20.0012 | 28.9968 | 0.01
6.3642 | 9.1821 | 8.3642 | 7.3642 | 10.5463 | 12.5463 | 9.1821 | 16.5463 | 27.0927 | 39.639 | 6.3642 | 9.1821 | 8.3642 | 7.3642 | 10.5563 | 12.5463 | 9.1821 | 16.5463 | 27.1027 | 39.649 | 0.01
9.0628 | 10.5314 | 11.0628 | 10.0628 | 14.5941 | 16.5941 | 10.5314 | 20.5941 | 35.1883 | 51.7824 | 9.0628 | 10.5314 | 11.0628 | 10.0628 | 14.6041 | 16.5941 | 10.5314 | 20.5941 | 35.1983 | 51.7924 | 0.01
6.7215 | 9.3608 | 8.7215 | 7.7215 | 11.0823 | 13.0823 | 9.3608 | 17.0823 | 28.1645 | 41.2468 | 6.7215 | 9.3608 | 8.7215 | 7.7215 | 11.0923 | 13.0823 | 9.3608 | 17.0823 | 28.1745 | 41.2568 | 0.01
7.5347 | 9.7673 | 9.5347 | 8.5347 | 12.302 | 14.302 | 9.7673 | 18.302 | 30.604 | 44.906 | 7.5347 | 9.7673 | 9.5347 | 8.5347 | 12.312 | 14.302 | 9.7673 | 18.302 | 30.614 | 44.916 | 0.01
4.2203 | 8.1102 | 6.2203 | 5.2203 | 7.3305 | 9.3305 | 8.1102 | 13.3305 | 20.6609 | 29.9914 | 4.2203 | 8.1102 | 6.2203 | 5.2203 | 7.3405 | 9.3305 | 8.1102 | 13.3305 | 20.6709 | 30.0014 | 0.01
4.9198 | 8.4599 | 6.9198 | 5.9198 | 8.3797 | 10.3797 | 8.4599 | 14.3797 | 22.7594 | 33.1391 | 4.9198 | 8.4599 | 6.9198 | 5.9198 | 8.3897 | 10.3797 | 8.4599 | 14.3797 | 22.7694 | 33.1491 | 0.01
3.252 | 7.626 | 5.252 | 4.252 | 5.878 | 7.878 | 7.626 | 11.878 | 17.7559 | 25.6339 | 3.252 | 7.626 | 5.252 | 4.252 | 5.888 | 7.878 | 7.626 | 11.878 | 17.7659 | 25.6439 | 0.01
6.2071 | 9.1036 | 8.2071 | 7.2071 | 10.3107 | 12.3107 | 9.1036 | 16.3107 | 26.6214 | 38.9322 | 6.2071 | 9.1036 | 8.2071 | 7.2071 | 10.3207 | 12.3107 | 9.1036 | 16.3107 | 26.6314 | 38.9422 | 0.01
6.9816 | 9.4908 | 8.9816 | 7.9816 | 11.4725 | 13.4725 | 9.4908 | 17.4725 | 28.9449 | 42.4174 | 6.9816 | 9.4908 | 8.9816 | 7.9816 | 11.4825 | 13.4725 | 9.4908 | 17.4725 | 28.9549 | 42.4274 | 0.01
4.3537 | 8.1768 | 6.3537 | 5.3537 | 7.5305 | 9.5305 | 8.1768 | 13.5305 | 21.061 | 30.5915 | 4.3537 | 8.1768 | 6.3537 | 5.3537 | 7.5405 | 9.5305 | 8.1768 | 13.5305 | 21.071 | 30.6015 | 0.01
7.4024 | 9.7012 | 9.4024 | 8.4024 | 12.1036 | 14.1036 | 9.7012 | 18.1036 | 30.2073 | 44.3109 | 7.4024 | 9.7012 | 9.4024 | 8.4024 | 12.1136 | 14.1036 | 9.7012 | 18.1036 | 30.2173 | 44.3209 | 0.01
5.2403 | 8.6202 | 7.2403 | 6.2403 | 8.8605 | 10.8605 | 8.6202 | 14.8605 | 23.7209 | 34.5814 | 5.2403 | 8.6202 | 7.2403 | 6.2403 | 8.8705 | 10.8605 | 8.6202 | 14.8605 | 23.7309 | 34.5914 | 0.01
6.5781 | 9.289 | 8.5781 | 7.5781 | 10.8671 | 12.8671 | 9.289 | 16.8671 | 27.7343 | 40.6014 | 6.5781 | 9.289 | 8.5781 | 7.5781 | 10.8771 | 12.8671 | 9.289 | 16.8671 | 27.7443 | 40.6114 | 0.01
7.6429 | 9.8215 | 9.6429 | 8.6429 | 12.4644 | 14.4644 | 9.8215 | 18.4644 | 30.9287 | 45.3931 | 7.6429 | 9.8215 | 9.6429 | 8.6429 | 12.4744 | 14.4644 | 9.8215 | 18.4644 | 30.9387 | 45.4031 | 0.01
6.3829 | 9.1915 | 8.3829 | 7.3829 | 10.5744 | 12.5744 | 9.1915 | 16.5744 | 27.1487 | 39.7231 | 6.3829 | 9.1915 | 8.3829 | 7.3829 | 10.5844 | 12.5744 | 9.1915 | 16.5744 | 27.1587 | 39.7331 | 0.01
3.4405 | 7.7202 | 5.4405 | 4.4405 | 6.1607 | 8.1607 | 7.7202 | 12.1607 | 18.3214 | 26.4821 | 3.4405 | 7.7202 | 5.4405 | 4.4405 | 6.1707 | 8.1607 | 7.7202 | 12.1607 | 18.3314 | 26.4921 | 0.01
8.5773 | 10.2887 | 10.5773 | 9.5773 | 13.866 | 15.866 | 10.2887 | 19.866 | 33.732 | 49.598 | 8.5773 | 10.2887 | 10.5773 | 9.5773 | 13.876 | 15.866 | 10.2887 | 19.866 | 33.742 | 49.608 | 0.01
8.9551 | 10.4775 | 10.9551 | 9.9551 | 14.4326 | 16.4326 | 10.4775 | 20.4326 | 34.8653 | 51.2979 | 8.9551 | 10.4775 | 10.9551 | 9.9551 | 14.4426 | 16.4326 | 10.4775 | 20.4326 | 34.8753 | 51.3079 | 0.01
5.4187 | 8.7094 | 7.4187 | 6.4187 | 9.1281 | 11.1281 | 8.7094 | 15.1281 | 24.2561 | 35.3842 | 5.4187 | 8.7094 | 7.4187 | 6.4187 | 9.1381 | 11.1281 | 8.7094 | 15.1281 | 24.2661 | 35.3942 | 0.01
5.3886 | 8.6943 | 7.3886 | 6.3886 | 9.083 | 11.083 | 8.6943 | 15.083 | 24.1659 | 35.2489 | 5.3886 | 8.6943 | 7.3886 | 6.3886 | 9.093 | 11.083 | 8.6943 | 15.083 | 24.1759 | 35.2589 | 0.01
8.0894 | 10.0447 | 10.0894 | 9.0894 | 13.1342 | 15.1342 | 10.0447 | 19.1342 | 32.2683 | 47.4025 | 8.0894 | 10.0447 | 10.0894 | 9.0894 | 13.1442 | 15.1342 | 10.0447 | 19.1342 | 32.2783 | 47.4125 | 0.01
9.5481 | 10.7741 | 11.5481 | 10.5481 | 15.3222 | 17.3222 | 10.7741 | 21.3222 | 36.6444 | 53.9666 | 9.5481 | 10.7741 | 11.5481 | 10.5481 | 15.3322 | 17.3222 | 10.7741 | 21.3222 | 36.6544 | 53.9766 | 0.01
8.3839 | 10.1919 | 10.3839 | 9.3839 | 13.5758 | 15.5758 | 10.1919 | 19.5758 | 33.1517 | 48.7275 | 8.3839 | 10.1919 | 10.3839 | 9.3839 | 13.5858 | 15.5758 | 10.1919 | 19.5758 | 33.1617 | 48.7375 | 0.01
5.3671 | 8.6836 | 7.3671 | 6.3671 | 9.0507 | 11.0507 | 8.6836 | 15.0507 | 24.1014 | 35.1521 | 5.3671 | 8.6836 | 7.3671 | 6.3671 | 9.0607 | 11.0507 | 8.6836 | 15.0507 | 24.1114 | 35.1621 | 0.01
6.4787 | 9.2394 | 8.4787 | 7.4787 | 10.7181 | 12.7181 | 9.2394 | 16.7181 | 27.4362 | 40.1544 | 6.4787 | 9.2394 | 8.4787 | 7.4787 | 10.7281 | 12.7181 | 9.2394 | 16.7181 | 27.4462 | 40.1644 | 0.01
9.3042 | 10.6521 | 11.3042 | 10.3042 | 14.9563 | 16.9563 | 10.6521 | 20.9563 | 35.9126 | 52.8689 | 9.3042 | 10.6521 | 11.3042 | 10.3042 | 14.9663 | 16.9563 | 10.6521 | 20.9563 | 35.9226 | 52.8789 | 0.01
2.544 | 7.272 | 4.544 | 3.544 | 4.816 | 6.816 | 7.272 | 10.816 | 15.632 | 22.448 | 2.544 | 7.272 | 4.544 | 3.544 | 4.826 | 6.816 | 7.272 | 10.816 | 15.642 | 22.458 | 0.01
4.3068 | 8.1534 | 6.3068 | 5.3068 | 7.4603 | 9.4603 | 8.1534 | 13.4603 | 20.9205 | 30.3808 | 4.3068 | 8.1534 | 6.3068 | 5.3068 | 7.4703 | 9.4603 | 8.1534 | 13.4603 | 20.9305 | 30.3908 | 0.01
4.3765 | 8.1883 | 6.3765 | 5.3765 | 7.5648 | 9.5648 | 8.1883 | 13.5648 | 21.1296 | 30.6944 | 4.3765 | 8.1883 | 6.3765 | 5.3765 | 7.5748 | 9.5648 | 8.1883 | 13.5648 | 21.1396 | 30.7044 | 0.01
8.9067 | 10.4534 | 10.9067 | 9.9067 | 14.3601 | 16.3601 | 10.4534 | 20.3601 | 34.7202 | 51.0803 | 8.9067 | 10.4534 | 10.9067 | 9.9067 | 14.3701 | 16.3601 | 10.4534 | 20.3601 | 34.7302 | 51.0903 | 0.01
5.8313 | 8.9156 | 7.8313 | 6.8313 | 9.7469 | 11.7469 | 8.9156 | 15.7469 | 25.4938 | 37.2407 | 5.8313 | 8.9156 | 7.8313 | 6.8313 | 9.7569 | 11.7469 | 8.9156 | 15.7469 | 25.5038 | 37.2507 | 0.01
5.7318 | 8.8659 | 7.7318 | 6.7318 | 9.5978 | 11.5978 | 8.8659 | 15.5978 | 25.1955 | 36.7933 | 5.7318 | 8.8659 | 7.7318 | 6.7318 | 9.6078 | 11.5978 | 8.8659 | 15.5978 | 25.2055 | 36.8033 | 0.01
4.0139 | 8.007 | 6.0139 | 5.0139 | 7.0209 | 9.0209 | 8.007 | 13.0209 | 20.0417 | 29.0626 | 4.0139 | 8.007 | 6.0139 | 5.0139 | 7.0309 | 9.0209 | 8.007 | 13.0209 | 20.0517 | 29.0726 | 0.01
4.3425 | 8.1712 | 6.3425 | 5.3425 | 7.5137 | 9.5137 | 8.1712 | 13.5137 | 21.0274 | 30.5411 | 4.3425 | 8.1712 | 6.3425 | 5.3425 | 7.5237 | 9.5137 | 8.1712 | 13.5137 | 21.0374 | 30.5511 | 0.01
6.3885 | 9.1943 | 8.3885 | 7.3885 | 10.5828 | 12.5828 | 9.1943 | 16.5828 | 27.1656 | 39.7483 | 6.3885 | 9.1943 | 8.3885 | 7.3885 | 10.5928 | 12.5828 | 9.1943 | 16.5828 | 27.1756 | 39.7583 | 0.01
4.828 | 8.414 | 6.828 | 5.828 | 8.242 | 10.242 | 8.414 | 14.242 | 22.484 | 32.726 | 4.828 | 8.414 | 6.828 | 5.828 | 8.252 | 10.242 | 8.414 | 14.242 | 22.494 | 32.736 | 0.01
4.4034 | 8.2017 | 6.4034 | 5.4034 | 7.6051 | 9.6051 | 8.2017 | 13.6051 | 21.2102 | 30.8153 | 4.4034 | 8.2017 | 6.4034 | 5.4034 | 7.6151 | 9.6051 | 8.2017 | 13.6051 | 21.2202 | 30.8253 | 0.01
4.8238 | 8.4119 | 6.8238 | 5.8238 | 8.2357 | 10.2357 | 8.4119 | 14.2357 | 22.4715 | 32.7072 | 4.8238 | 8.4119 | 6.8238 | 5.8238 | 8.2457 | 10.2357 | 8.4119 | 14.2357 | 22.4815 | 32.7172 | 0.01
2.2571 | 7.1285 | 4.2571 | 3.2571 | 4.3856 | 6.3856 | 7.1285 | 10.3856 | 14.7713 | 21.1569 | 2.2571 | 7.1285 | 4.2571 | 3.2571 | 4.3956 | 6.3856 | 7.1285 | 10.3856 | 14.7813 | 21.1669 | 0.01
7.5318 | 9.7659 | 9.5318 | 8.5318 | 12.2977 | 14.2977 | 9.7659 | 18.2977 | 30.5954 | 44.8931 | 7.5318 | 9.7659 | 9.5318 | 8.5318 | 12.3077 | 14.2977 | 9.7659 | 18.2977 | 30.6054 | 44.9031 | 0.01
5.7824 | 8.8912 | 7.7824 | 6.7824 | 9.6736 | 11.6736 | 8.8912 | 15.6736 | 25.3472 | 37.0208 | 5.7824 | 8.8912 | 7.7824 | 6.7824 | 9.6836 | 11.6736 | 8.8912 | 15.6736 | 25.3572 | 37.0308 | 0.01
5.2454 | 8.6227 | 7.2454 | 6.2454 | 8.8681 | 10.8681 | 8.6227 | 14.8681 | 23.7362 | 34.6043 | 5.2454 | 8.6227 | 7.2454 | 6.2454 | 8.8781 | 10.8681 | 8.6227 | 14.8681 | 23.7462 | 34.6143 | 0.01
4.8561 | 8.428 | 6.8561 | 5.8561 | 8.2841 | 10.2841 | 8.428 | 14.2841 | 22.5682 | 32.8522 | 4.8561 | 8.428 | 6.8561 | 5.8561 | 8.2941 | 10.2841 | 8.428 | 14.2841 | 22.5782 | 32.8622 | 0.01
8.4147 | 10.2073 | 10.4147 | 9.4147 | 13.622 | 15.622 | 10.2073 | 19.622 | 33.244 | 48.866 | 8.4147 | 10.2073 | 10.4147 | 9.4147 | 13.632 | 15.622 | 10.2073 | 19.622 | 33.254 | 48.876 | 0.01
6.6838 | 9.3419 | 8.6838 | 7.6838 | 11.0256 | 13.0256 | 9.3419 | 17.0256 | 28.0513 | 41.0769 | 6.6838 | 9.3419 | 8.6838 | 7.6838 | 11.0356 | 13.0256 | 9.3419 | 17.0256 | 28.0613 | 41.0869 | 0.01
0.96635 | 6.4832 | 2.9663 | 1.9663 | 2.4495 | 4.4495 | 6.4832 | 8.4495 | 10.899 | 15.3486 | 0.96635 | 6.4832 | 2.9663 | 1.9663 | 2.4595 | 4.4495 | 6.4832 | 8.4495 | 10.909 | 15.3586 | 0.01
7.0703 | 9.5351 | 9.0703 | 8.0703 | 11.6054 | 13.6054 | 9.5351 | 17.6054 | 29.2109 | 42.8163 | 7.0703 | 9.5351 | 9.0703 | 8.0703 | 11.6154 | 13.6054 | 9.5351 | 17.6054 | 29.2209 | 42.8263 | 0.01
7.017 | 9.5085 | 9.017 | 8.017 | 11.5255 | 13.5255 | 9.5085 | 17.5255 | 29.051 | 42.5765 | 7.017 | 9.5085 | 9.017 | 8.017 | 11.5355 | 13.5255 | 9.5085 | 17.5255 | 29.061 | 42.5865 | 0.01
5.4393 | 8.7196 | 7.4393 | 6.4393 | 9.1589 | 11.1589 | 8.7196 | 15.1589 | 24.3178 | 35.4767 | 5.4393 | 8.7196 | 7.4393 | 6.4393 | 9.1689 | 11.1589 | 8.7196 | 15.1589 | 24.3278 | 35.4867 | 0.01
2.5841 | 7.2921 | 4.5841 | 3.5841 | 4.8762 | 6.8762 | 7.2921 | 10.8762 | 15.7524 | 22.6286 | 2.5841 | 7.2921 | 4.5841 | 3.5841 | 4.8862 | 6.8762 | 7.2921 | 10.8762 | 15.7624 | 22.6386 | 0.01
3.8108 | 7.9054 | 5.8108 | 4.8108 | 6.7162 | 8.7162 | 7.9054 | 12.7162 | 19.4324 | 28.1486 | 3.8108 | 7.9054 | 5.8108 | 4.8108 | 6.7262 | 8.7162 | 7.9054 | 12.7162 | 19.4424 | 28.1586 | 0.01
5.3143 | 8.6572 | 7.3143 | 6.3143 | 8.9715 | 10.9715 | 8.6572 | 14.9715 | 23.9429 | 34.9144 | 5.3143 | 8.6572 | 7.3143 | 6.3143 | 8.9815 | 10.9715 | 8.6572 | 14.9715 | 23.9529 | 34.9244 | 0.01
6.6577 | 9.3288 | 8.6577 | 7.6577 | 10.9865 | 12.9865 | 9.3288 | 16.9865 | 27.9731 | 40.9596 | 6.6577 | 9.3288 | 8.6577 | 7.6577 | 10.9965 | 12.9865 | 9.3288 | 16.9865 | 27.9831 | 40.9696 | 0.01
3.0098 | 7.5049 | 5.0098 | 4.0098 | 5.5147 | 7.5147 | 7.5049 | 11.5147 | 17.0295 | 24.5442 | 3.0098 | 7.5049 | 5.0098 | 4.0098 | 5.5247 | 7.5147 | 7.5049 | 11.5147 | 17.0395 | 24.5542 | 0.01
5.1527 | 8.5764 | 7.1527 | 6.1527 | 8.7291 | 10.7291 | 8.5764 | 14.7291 | 23.4582 | 34.1873 | 5.1527 | 8.5764 | 7.1527 | 6.1527 | 8.7391 | 10.7291 | 8.5764 | 14.7291 | 23.4682 | 34.1973 | 0.01
5.8825 | 8.9413 | 7.8825 | 6.8825 | 9.8238 | 11.8238 | 8.9413 | 15.8238 | 25.6475 | 37.4713 | 5.8825 | 8.9413 | 7.8825 | 6.8825 | 9.8338 | 11.8238 | 8.9413 | 15.8238 | 25.6575 | 37.4813 | 0.01
6.6117 | 9.3058 | 8.6117 | 7.6117 | 10.9175 | 12.9175 | 9.3058 | 16.9175 | 27.835 | 40.7525 | 6.6117 | 9.3058 | 8.6117 | 7.6117 | 10.9275 | 12.9175 | 9.3058 | 16.9175 | 27.845 | 40.7625 | 0.01
7.5536 | 9.7768 | 9.5536 | 8.5536 | 12.3304 | 14.3304 | 9.7768 | 18.3304 | 30.6609 | 44.9913 | 7.5536 | 9.7768 | 9.5536 | 8.5536 | 12.3404 | 14.3304 | 9.7768 | 18.3304 | 30.6709 | 45.0013 | 0.01
3.9811 | 7.9905 | 5.9811 | 4.9811 | 6.9716 | 8.9716 | 7.9905 | 12.9716 | 19.9432 | 28.9148 | 3.9811 | 7.9905 | 5.9811 | 4.9811 | 6.9816 | 8.9716 | 7.9905 | 12.9716 | 19.9532 | 28.9248 | 0.01
2.7565 | 7.3783 | 4.7565 | 3.7565 | 5.1348 | 7.1348 | 7.3783 | 11.1348 | 16.2696 | 23.4044 | 2.7565 | 7.3783 | 4.7565 | 3.7565 | 5.1448 | 7.1348 | 7.3783 | 11.1348 | 16.2796 | 23.4144 | 0.01
1.279 | 6.6395 | 3.279 | 2.279 | 2.9185 | 4.9185 | 6.6395 | 8.9185 | 11.837 | 16.7555 | 1.279 | 6.6395 | 3.279 | 2.279 | 2.9285 | 4.9185 | 6.6395 | 8.9185 | 11.847 | 16.7655 | 0.01
6.3987 | 9.1993 | 8.3987 | 7.3987 | 10.598 | 12.598 | 9.1993 | 16.598 | 27.196 | 39.794 | 6.3987 | 9.1993 | 8.3987 | 7.3987 | 10.608 | 12.598 | 9.1993 | 16.598 | 27.206 | 39.804 | 0.01
8.8962 | 10.4481 | 10.8962 | 9.8962 | 14.3443 | 16.3443 | 10.4481 | 20.3443 | 34.6886 | 51.033 | 8.8962 | 10.4481 | 10.8962 | 9.8962 | 14.3543 | 16.3443 | 10.4481 | 20.3443 | 34.6986 | 51.043 | 0.01
3.2532 | 7.6266 | 5.2532 | 4.2532 | 5.8797 | 7.8797 | 7.6266 | 11.8797 | 17.7595 | 25.6392 | 3.2532 | 7.6266 | 5.2532 | 4.2532 | 5.8897 | 7.8797 | 7.6266 | 11.8797 | 17.7695 | 25.6492 | 0.01
5.4748 | 8.7374 | 7.4748 | 6.4748 | 9.2122 | 11.2122 | 8.7374 | 15.2122 | 24.4245 | 35.6367 | 5.4748 | 8.7374 | 7.4748 | 6.4748 | 9.2222 | 11.2122 | 8.7374 | 15.2122 | 24.4345 | 35.6467 | 0.01
5.6701 | 8.8351 | 7.6701 | 6.6701 | 9.5052 | 11.5052 | 8.8351 | 15.5052 | 25.0103 | 36.5155 | 5.6701 | 8.8351 | 7.6701 | 6.6701 | 9.5152 | 11.5052 | 8.8351 | 15.5052 | 25.0203 | 36.5255 | 0.01
8.5124 | 10.2562 | 10.5124 | 9.5124 | 13.7685 | 15.7685 | 10.2562 | 19.7685 | 33.5371 | 49.3056 | 8.5124 | 10.2562 | 10.5124 | 9.5124 | 13.7785 | 15.7685 | 10.2562 | 19.7685 | 33.5471 | 49.3156 | 0.01
7.7278 | 9.8639 | 9.7278 | 8.7278 | 12.5917 | 14.5917 | 9.8639 | 18.5917 | 31.1834 | 45.7751 | 7.7278 | 9.8639 | 9.7278 | 8.7278 | 12.6017 | 14.5917 | 9.8639 | 18.5917 | 31.1934 | 45.7851 | 0.01
6.6958 | 9.3479 | 8.6958 | 7.6958 | 11.0437 | 13.0437 | 9.3479 | 17.0437 | 28.0873 | 41.131 | 6.6958 | 9.3479 | 8.6958 | 7.6958 | 11.0537 | 13.0437 | 9.3479 | 17.0437 | 28.0973 | 41.141 | 0.01
6.6747 | 9.3373 | 8.6747 | 7.6747 | 11.012 | 13.012 | 9.3373 | 17.012 | 28.024 | 41.036 | 6.6747 | 9.3373 | 8.6747 | 7.6747 | 11.022 | 13.012 | 9.3373 | 17.012 | 28.034 | 41.046 | 0.01
4.1136 | 8.0568 | 6.1136 | 5.1136 | 7.1705 | 9.1705 | 8.0568 | 13.1705 | 20.3409 | 29.5114 | 4.1136 | 8.0568 | 6.1136 | 5.1136 | 7.1805 | 9.1705 | 8.0568 | 13.1705 | 20.3509 | 29.5214 | 0.01
6.0322 | 9.0161 | 8.0322 | 7.0322 | 10.0483 | 12.0483 | 9.0161 | 16.0483 | 26.0966 | 38.1449 | 6.0322 | 9.0161 | 8.0322 | 7.0322 | 10.0583 | 12.0483 | 9.0161 | 16.0483 | 26.1066 | 38.1549 | 0.01
6.0533 | 9.0267 | 8.0533 | 7.0533 | 10.08 | 12.08 | 9.0267 | 16.08 | 26.16 | 38.24 | 6.0533 | 9.0267 | 8.0533 | 7.0533 | 10.09 | 12.08 | 9.0267 | 16.08 | 26.17 | 38.25 | 0.01
5.3099 | 8.655 | 7.3099 | 6.3099 | 8.9649 | 10.9649 | 8.655 | 14.9649 | 23.9298 | 34.8946 | 5.3099 | 8.655 | 7.3099 | 6.3099 | 8.9749 | 10.9649 | 8.655 | 14.9649 | 23.9398 | 34.9046 | 0.01
2.783 | 7.3915 | 4.783 | 3.783 | 5.1746 | 7.1746 | 7.3915 | 11.1746 | 16.3491 | 23.5237 | 2.783 | 7.3915 | 4.783 | 3.783 | 5.1846 | 7.1746 | 7.3915 | 11.1746 | 16.3591 | 23.5337 | 0.01
4.1082 | 8.0541 | 6.1082 | 5.1082 | 7.1622 | 9.1622 | 8.0541 | 13.1622 | 20.3245 | 29.4867 | 4.1082 | 8.0541 | 6.1082 | 5.1082 | 7.1722 | 9.1622 | 8.0541 | 13.1622 | 20.3345 | 29.4967 | 0.01
9.1167 | 10.5584 | 11.1167 | 10.1167 | 14.6751 | 16.6751 | 10.5584 | 20.6751 | 35.3502 | 52.0254 | 9.1167 | 10.5584 | 11.1167 | 10.1167 | 14.6851 | 16.6751 | 10.5584 | 20.6751 | 35.3602 | 52.0354 | 0.01
7.2546 | 9.6273 | 9.2546 | 8.2546 | 11.8819 | 13.8819 | 9.6273 | 17.8819 | 29.7637 | 43.6456 | 7.2546 | 9.6273 | 9.2546 | 8.2546 | 11.8919 | 13.8819 | 9.6273 | 17.8819 | 29.7737 | 43.6556 | 0.01
3.9195 | 7.9598 | 5.9195 | 4.9195 | 6.8793 | 8.8793 | 7.9598 | 12.8793 | 19.7585 | 28.6378 | 3.9195 | 7.9598 | 5.9195 | 4.9195 | 6.8893 | 8.8793 | 7.9598 | 12.8793 | 19.7685 | 28.6478 | 0.01
7.2151 | 9.6076 | 9.2151 | 8.2151 | 11.8227 | 13.8227 | 9.6076 | 17.8227 | 29.6454 | 43.4681 | 7.2151 | 9.6076 | 9.2151 | 8.2151 | 11.8327 | 13.8227 | 9.6076 | 17.8227 | 29.6554 | 43.4781 | 0.01
5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.1014 | 11.0914 | 8.6971 | 15.0914 | 24.1928 | 35.2841 | 0.01
4.1806 | 8.0903 | 6.1806 | 5.1806 | 7.2709 | 9.2709 | 8.0903 | 13.2709 | 20.5419 | 29.8128 | 4.1806 | 8.0903 | 6.1806 | 5.1806 | 7.2809 | 9.2709 | 8.0903 | 13.2709 | 20.5519 | 29.8228 | 0.01
4.4304 | 8.2152 | 6.4304 | 5.4304 | 7.6456 | 9.6456 | 8.2152 | 13.6456 | 21.2912 | 30.9368 | 4.4304 | 8.2152 | 6.4304 | 5.4304 | 7.6556 | 9.6456 | 8.2152 | 13.6456 | 21.3012 | 30.9468 | 0.01
4.0583 | 8.0291 | 6.0583 | 5.0583 | 7.0874 | 9.0874 | 8.0291 | 13.0874 | 20.1748 | 29.2622 | 4.0583 | 8.0291 | 6.0583 | 5.0583 | 7.0974 | 9.0874 | 8.0291 | 13.0874 | 20.1848 | 29.2722 | 0.01
6.3386 | 9.1693 | 8.3386 | 7.3386 | 10.5079 | 12.5079 | 9.1693 | 16.5079 | 27.0158 | 39.5236 | 6.3386 | 9.1693 | 8.3386 | 7.3386 | 10.5179 | 12.5079 | 9.1693 | 16.5079 | 27.0258 | 39.5336 | 0.01
8.3318 | 10.1659 | 10.3318 | 9.3318 | 13.4977 | 15.4977 | 10.1659 | 19.4977 | 32.9953 | 48.493 | 8.3318 | 10.1659 | 10.3318 | 9.3318 | 13.5077 | 15.4977 | 10.1659 | 19.4977 | 33.0053 | 48.503 | 0.01
3.4866 | 7.7433 | 5.4866 | 4.4866 | 6.23 | 8.23 | 7.7433 | 12.23 | 18.4599 | 26.6899 | 3.4866 | 7.7433 | 5.4866 | 4.4866 | 6.24 | 8.23 | 7.7433 | 12.23 | 18.4699 | 26.6999 | 0.01
5.145 | 8.5725 | 7.145 | 6.145 | 8.7175 | 10.7175 | 8.5725 | 14.7175 | 23.4351 | 34.1526 | 5.145 | 8.5725 | 7.145 | 6.145 | 8.7275 | 10.7175 | 8.5725 | 14.7175 | 23.4451 | 34.1626 | 0.01
4.7066 | 8.3533 | 6.7066 | 5.7066 | 8.06 | 10.06 | 8.3533 | 14.06 | 22.1199 | 32.1799 | 4.7066 | 8.3533 | 6.7066 | 5.7066 | 8.07 | 10.06 | 8.3533 | 14.06 | 22.1299 | 32.1899 | 0.01
3.6298 | 7.8149 | 5.6298 | 4.6298 | 6.4446 | 8.4446 | 7.8149 | 12.4446 | 18.8893 | 27.3339 | 3.6298 | 7.8149 | 5.6298 | 4.6298 | 6.4546 | 8.4446 | 7.8149 | 12.4446 | 18.8993 | 27.3439 | 0.01
7.1394 | 9.5697 | 9.1394 | 8.1394 | 11.7092 | 13.7092 | 9.5697 | 17.7092 | 29.4183 | 43.1275 | 7.1394 | 9.5697 | 9.1394 | 8.1394 | 11.7192 | 13.7092 | 9.5697 | 17.7092 | 29.4283 | 43.1375 | 0.01
6.9539 | 9.477 | 8.9539 | 7.9539 | 11.4309 | 13.4309 | 9.477 | 17.4309 | 28.8618 | 42.2928 | 6.9539 | 9.477 | 8.9539 | 7.9539 | 11.4409 | 13.4309 | 9.477 | 17.4309 | 28.8718 | 42.3028 | 0.01
3.8824 | 7.9412 | 5.8824 | 4.8824 | 6.8235 | 8.8235 | 7.9412 | 12.8235 | 19.6471 | 28.4706 | 3.8824 | 7.9412 | 5.8824 | 4.8824 | 6.8335 | 8.8235 | 7.9412 | 12.8235 | 19.6571 | 28.4806 | 0.01
4.5081 | 8.2541 | 6.5081 | 5.5081 | 7.7622 | 9.7622 | 8.2541 | 13.7622 | 21.5243 | 31.2865 | 4.5081 | 8.2541 | 6.5081 | 5.5081 | 7.7722 | 9.7622 | 8.2541 | 13.7622 | 21.5343 | 31.2965 | 0.01
5.4401 | 8.72 | 7.4401 | 6.4401 | 9.1601 | 11.1601 | 8.72 | 15.1601 | 24.3202 | 35.4803 | 5.4401 | 8.72 | 7.4401 | 6.4401 | 9.1701 | 11.1601 | 8.72 | 15.1601 | 24.3302 | 35.4903 | 0.01
7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8418 | 13.8318 | 9.6106 | 17.8318 | 29.6736 | 43.5055 | 0.01
6.3068 | 9.1534 | 8.3068 | 7.3068 | 10.4602 | 12.4602 | 9.1534 | 16.4602 | 26.9204 | 39.3807 | 6.3068 | 9.1534 | 8.3068 | 7.3068 | 10.4702 | 12.4602 | 9.1534 | 16.4602 | 26.9304 | 39.3907 | 0.01
2.4541 | 7.227 | 4.4541 | 3.4541 | 4.6811 | 6.6811 | 7.227 | 10.6811 | 15.3622 | 22.0434 | 2.4541 | 7.227 | 4.4541 | 3.4541 | 4.6911 | 6.6811 | 7.227 | 10.6811 | 15.3722 | 22.0534 | 0.01
6.616 | 9.308 | 8.616 | 7.616 | 10.924 | 12.924 | 9.308 | 16.924 | 27.848 | 40.772 | 6.616 | 9.308 | 8.616 | 7.616 | 10.934 | 12.924 | 9.308 | 16.924 | 27.858 | 40.782 | 0.01
6.1816 | 9.0908 | 8.1816 | 7.1816 | 10.2724 | 12.2724 | 9.0908 | 16.2724 | 26.5449 | 38.8173 | 6.1816 | 9.0908 | 8.1816 | 7.1816 | 10.2824 | 12.2724 | 9.0908 | 16.2724 | 26.5549 | 38.8273 | 0.01
4.1669 | 8.0835 | 6.1669 | 5.1669 | 7.2504 | 9.2504 | 8.0835 | 13.2504 | 20.5008 | 29.7512 | 4.1669 | 8.0835 | 6.1669 | 5.1669 | 7.2604 | 9.2504 | 8.0835 | 13.2504 | 20.5108 | 29.7612 | 0.01
5.6994 | 8.8497 | 7.6994 | 6.6994 | 9.5491 | 11.5491 | 8.8497 | 15.5491 | 25.0981 | 36.6472 | 5.6994 | 8.8497 | 7.6994 | 6.6994 | 9.5591 | 11.5491 | 8.8497 | 15.5491 | 25.1081 | 36.6572 | 0.01
6.0425 | 9.0212 | 8.0425 | 7.0425 | 10.0637 | 12.0637 | 9.0212 | 16.0637 | 26.1274 | 38.1911 | 6.0425 | 9.0212 | 8.0425 | 7.0425 | 10.0737 | 12.0637 | 9.0212 | 16.0637 | 26.1374 | 38.2011 | 0.01
10.3015 | 11.1508 | 12.3015 | 11.3015 | 16.4523 | 18.4523 | 11.1508 | 22.4523 | 38.9045 | 57.3568 | 10.3015 | 11.1508 | 12.3015 | 11.3015 | 16.4623 | 18.4523 | 11.1508 | 22.4523 | 38.9145 | 57.3668 | 0.01
5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.656 | 10.646 | 8.5487 | 14.646 | 23.302 | 33.9481 | 0.01
2.9544 | 7.4772 | 4.9544 | 3.9544 | 5.4316 | 7.4316 | 7.4772 | 11.4316 | 16.8633 | 24.2949 | 2.9544 | 7.4772 | 4.9544 | 3.9544 | 5.4416 | 7.4316 | 7.4772 | 11.4316 | 16.8733 | 24.3049 | 0.01
8.086 | 10.043 | 10.086 | 9.086 | 13.129 | 15.129 | 10.043 | 19.129 | 32.258 | 47.3871 | 8.086 | 10.043 | 10.086 | 9.086 | 13.139 | 15.129 | 10.043 | 19.129 | 32.268 | 47.3971 | 0.01
3.5671 | 7.7836 | 5.5671 | 4.5671 | 6.3507 | 8.3507 | 7.7836 | 12.3507 | 18.7014 | 27.0522 | 3.5671 | 7.7836 | 5.5671 | 4.5671 | 6.3607 | 8.3507 | 7.7836 | 12.3507 | 18.7114 | 27.0622 | 0.01
3.1336 | 7.5668 | 5.1336 | 4.1336 | 5.7004 | 7.7004 | 7.5668 | 11.7004 | 17.4008 | 25.1012 | 3.1336 | 7.5668 | 5.1336 | 4.1336 | 5.7104 | 7.7004 | 7.5668 | 11.7004 | 17.4108 | 25.1112 | 0.01
6.5277 | 9.2639 | 8.5277 | 7.5277 | 10.7916 | 12.7916 | 9.2639 | 16.7916 | 27.5831 | 40.3747 | 6.5277 | 9.2639 | 8.5277 | 7.5277 | 10.8016 | 12.7916 | 9.2639 | 16.7916 | 27.5931 | 40.3847 | 0.01
4.9065 | 8.4533 | 6.9065 | 5.9065 | 8.3598 | 10.3598 | 8.4533 | 14.3598 | 22.7195 | 33.0793 | 4.9065 | 8.4533 | 6.9065 | 5.9065 | 8.3698 | 10.3598 | 8.4533 | 14.3598 | 22.7295 | 33.0893 | 0.01
5.0165 | 8.5082 | 7.0165 | 6.0165 | 8.5247 | 10.5247 | 8.5082 | 14.5247 | 23.0494 | 33.5741 | 5.0165 | 8.5082 | 7.0165 | 6.0165 | 8.5347 | 10.5247 | 8.5082 | 14.5247 | 23.0594 | 33.5841 | 0.01
7.6593 | 9.8296 | 9.6593 | 8.6593 | 12.4889 | 14.4889 | 9.8296 | 18.4889 | 30.9778 | 45.4666 | 7.6593 | 9.8296 | 9.6593 | 8.6593 | 12.4989 | 14.4889 | 9.8296 | 18.4889 | 30.9878 | 45.4766 | 0.01
7.9067 | 9.9534 | 9.9067 | 8.9067 | 12.8601 | 14.8601 | 9.9534 | 18.8601 | 31.7202 | 46.5803 | 7.9067 | 9.9534 | 9.9067 | 8.9067 | 12.8701 | 14.8601 | 9.9534 | 18.8601 | 31.7302 | 46.5903 | 0.01
5.5669 | 8.7835 | 7.5669 | 6.5669 | 9.3504 | 11.3504 | 8.7835 | 15.3504 | 24.7008 | 36.0513 | 5.5669 | 8.7835 | 7.5669 | 6.5669 | 9.3604 | 11.3504 | 8.7835 | 15.3504 | 24.7108 | 36.0613 | 0.01
6.8194 | 9.4097 | 8.8194 | 7.8194 | 11.2291 | 13.2291 | 9.4097 | 17.2291 | 28.4582 | 41.6873 | 6.8194 | 9.4097 | 8.8194 | 7.8194 | 11.2391 | 13.2291 | 9.4097 | 17.2291 | 28.4682 | 41.6973 | 0.01
4.8316 | 8.4158 | 6.8316 | 5.8316 | 8.2475 | 10.2475 | 8.4158 | 14.2475 | 22.4949 | 32.7424 | 4.8316 | 8.4158 | 6.8316 | 5.8316 | 8.2575 | 10.2475 | 8.4158 | 14.2475 | 22.5049 | 32.7524 | 0.01
7.73 | 9.865 | 9.73 | 8.73 | 12.595 | 14.595 | 9.865 | 18.595 | 31.19 | 45.785 | 7.73 | 9.865 | 9.73 | 8.73 | 12.605 | 14.595 | 9.865 | 18.595 | 31.2 | 45.795 | 0.01
4.3301 | 8.1651 | 6.3301 | 5.3301 | 7.4952 | 9.4952 | 8.1651 | 13.4952 | 20.9904 | 30.4857 | 4.3301 | 8.1651 | 6.3301 | 5.3301 | 7.5052 | 9.4952 | 8.1651 | 13.4952 | 21.0004 | 30.4957 | 0.01
4.0174 | 8.0087 | 6.0174 | 5.0174 | 7.0261 | 9.0261 | 8.0087 | 13.0261 | 20.0522 | 29.0784 | 4.0174 | 8.0087 | 6.0174 | 5.0174 | 7.0361 | 9.0261 | 8.0087 | 13.0261 | 20.0622 | 29.0884 | 0.01
3.7223 | 7.8612 | 5.7223 | 4.7223 | 6.5835 | 8.5835 | 7.8612 | 12.5835 | 19.1669 | 27.7504 | 3.7223 | 7.8612 | 5.7223 | 4.7223 | 6.5935 | 8.5835 | 7.8612 | 12.5835 | 19.1769 | 27.7604 | 0.01
5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9451 | 10.9351 | 8.645 | 14.9351 | 23.8802 | 34.8153 | 0.01
7.4619 | 9.731 | 9.4619 | 8.4619 | 12.1929 | 14.1929 | 9.731 | 18.1929 | 30.3858 | 44.5787 | 7.4619 | 9.731 | 9.4619 | 8.4619 | 12.2029 | 14.1929 | 9.731 | 18.1929 | 30.3958 | 44.5887 | 0.01
4.2939 | 8.1469 | 6.2939 | 5.2939 | 7.4408 | 9.4408 | 8.1469 | 13.4408 | 20.8817 | 30.3225 | 4.2939 | 8.1469 | 6.2939 | 5.2939 | 7.4508 | 9.4408 | 8.1469 | 13.4408 | 20.8917 | 30.3325 | 0.01
6.2435 | 9.1217 | 8.2435 | 7.2435 | 10.3652 | 12.3652 | 9.1217 | 16.3652 | 26.7304 | 39.0957 | 6.2435 | 9.1217 | 8.2435 | 7.2435 | 10.3752 | 12.3652 | 9.1217 | 16.3652 | 26.7404 | 39.1057 | 0.01
5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6481 | 10.6381 | 8.546 | 14.6381 | 23.2863 | 33.9244 | 0.01
7.367 | 9.6835 | 9.367 | 8.367 | 12.0506 | 14.0506 | 9.6835 | 18.0506 | 30.1011 | 44.1517 | 7.367 | 9.6835 | 9.367 | 8.367 | 12.0606 | 14.0506 | 9.6835 | 18.0506 | 30.1111 | 44.1617 | 0.01
9.1555 | 10.5777 | 11.1555 | 10.1555 | 14.7332 | 16.7332 | 10.5777 | 20.7332 | 35.4664 | 52.1996 | 9.1555 | 10.5777 | 11.1555 | 10.1555 | 14.7432 | 16.7332 | 10.5777 | 20.7332 | 35.4764 | 52.2096 | 0.01
4.4266 | 8.2133 | 6.4266 | 5.4266 | 7.64 | 9.64 | 8.2133 | 13.64 | 21.2799 | 30.9199 | 4.4266 | 8.2133 | 6.4266 | 5.4266 | 7.65 | 9.64 | 8.2133 | 13.64 | 21.2899 | 30.9299 | 0.01
6.4001 | 9.2 | 8.4001 | 7.4001 | 10.6001 | 12.6001 | 9.2 | 16.6001 | 27.2002 | 39.8003 | 6.4001 | 9.2 | 8.4001 | 7.4001 | 10.6101 | 12.6001 | 9.2 | 16.6001 | 27.2102 | 39.8103 | 0.01
5.0045 | 8.5023 | 7.0045 | 6.0045 | 8.5068 | 10.5068 | 8.5023 | 14.5068 | 23.0136 | 33.5204 | 5.0045 | 8.5023 | 7.0045 | 6.0045 | 8.5168 | 10.5068 | 8.5023 | 14.5068 | 23.0236 | 33.5304 | 0.01
2.7353 | 7.3676 | 4.7353 | 3.7353 | 5.1029 | 7.1029 | 7.3676 | 11.1029 | 16.2058 | 23.3088 | 2.7353 | 7.3676 | 4.7353 | 3.7353 | 5.1129 | 7.1029 | 7.3676 | 11.1029 | 16.2158 | 23.3188 | 0.01
5.211 | 8.6055 | 7.211 | 6.211 | 8.8164 | 10.8164 | 8.6055 | 14.8164 | 23.6329 | 34.4493 | 5.211 | 8.6055 | 7.211 | 6.211 | 8.8264 | 10.8164 | 8.6055 | 14.8164 | 23.6429 | 34.4593 | 0.01
5.7148 | 8.8574 | 7.7148 | 6.7148 | 9.5723 | 11.5723 | 8.8574 | 15.5723 | 25.1445 | 36.7168 | 5.7148 | 8.8574 | 7.7148 | 6.7148 | 9.5823 | 11.5723 | 8.8574 | 15.5723 | 25.1545 | 36.7268 | 0.01
2.991 | 7.4955 | 4.991 | 3.991 | 5.4865 | 7.4865 | 7.4955 | 11.4865 | 16.9729 | 24.4594 | 2.991 | 7.4955 | 4.991 | 3.991 | 5.4965 | 7.4865 | 7.4955 | 11.4865 | 16.9829 | 24.4694 | 0.01
5.3673 | 8.6836 | 7.3673 | 6.3673 | 9.0509 | 11.0509 | 8.6836 | 15.0509 | 24.1019 | 35.1528 | 5.3673 | 8.6836 | 7.3673 | 6.3673 | 9.0609 | 11.0509 | 8.6836 | 15.0509 | 24.1119 | 35.1628 | 0.01
6.8222 | 9.4111 | 8.8222 | 7.8222 | 11.2333 | 13.2333 | 9.4111 | 17.2333 | 28.4667 | 41.7 | 6.8222 | 9.4111 | 8.8222 | 7.8222 | 11.2433 | 13.2333 | 9.4111 | 17.2333 | 28.4767 | 41.71 | 0.01
5.639 | 8.8195 | 7.639 | 6.639 | 9.4586 | 11.4586 | 8.8195 | 15.4586 | 24.9171 | 36.3757 | 5.639 | 8.8195 | 7.639 | 6.639 | 9.4686 | 11.4586 | 8.8195 | 15.4586 | 24.9271 | 36.3857 | 0.01
10.6751 | 11.3376 | 12.6751 | 11.6751 | 17.0127 | 19.0127 | 11.3376 | 23.0127 | 40.0254 | 59.0381 | 10.6751 | 11.3376 | 12.6751 | 11.6751 | 17.0227 | 19.0127 | 11.3376 | 23.0127 | 40.0354 | 59.0481 | 0.01
1.6411 | 6.8205 | 3.6411 | 2.6411 | 3.4616 | 5.4616 | 6.8205 | 9.4616 | 12.9232 | 18.3849 | 1.6411 | 6.8205 | 3.6411 | 2.6411 | 3.4716 | 5.4616 | 6.8205 | 9.4616 | 12.9332 | 18.3949 | 0.01
5.3028 | 8.6514 | 7.3028 | 6.3028 | 8.9542 | 10.9542 | 8.6514 | 14.9542 | 23.9083 | 34.8625 | 5.3028 | 8.6514 | 7.3028 | 6.3028 | 8.9642 | 10.9542 | 8.6514 | 14.9542 | 23.9183 | 34.8725 | 0.01
8.489 | 10.2445 | 10.489 | 9.489 | 13.7334 | 15.7334 | 10.2445 | 19.7334 | 33.4669 | 49.2003 | 8.489 | 10.2445 | 10.489 | 9.489 | 13.7434 | 15.7334 | 10.2445 | 19.7334 | 33.4769 | 49.2103 | 0.01
6.2238 | 9.1119 | 8.2238 | 7.2238 | 10.3356 | 12.3356 | 9.1119 | 16.3356 | 26.6713 | 39.0069 | 6.2238 | 9.1119 | 8.2238 | 7.2238 | 10.3456 | 12.3356 | 9.1119 | 16.3356 | 26.6813 | 39.0169 | 0.01
5.7985 | 8.8993 | 7.7985 | 6.7985 | 9.6978 | 11.6978 | 8.8993 | 15.6978 | 25.3956 | 37.0935 | 5.7985 | 8.8993 | 7.7985 | 6.7985 | 9.7078 | 11.6978 | 8.8993 | 15.6978 | 25.4056 | 37.1035 | 0.01
7.9791 | 9.9895 | 9.9791 | 8.9791 | 12.9686 | 14.9686 | 9.9895 | 18.9686 | 31.9373 | 46.9059 | 7.9791 | 9.9895 | 9.9791 | 8.9791 | 12.9786 | 14.9686 | 9.9895 | 18.9686 | 31.9473 | 46.9159 | 0.01
6.6718 | 9.3359 | 8.6718 | 7.6718 | 11.0076 | 13.0076 | 9.3359 | 17.0076 | 28.0153 | 41.0229 | 6.6718 | 9.3359 | 8.6718 | 7.6718 | 11.0176 | 13.0076 | 9.3359 | 17.0076 | 28.0253 | 41.0329 | 0.01
2.7548 | 7.3774 | 4.7548 | 3.7548 | 5.1322 | 7.1322 | 7.3774 | 11.1322 | 16.2645 | 23.3967 | 2.7548 | 7.3774 | 4.7548 | 3.7548 | 5.1422 | 7.1322 | 7.3774 | 11.1322 | 16.2745 | 23.4067 | 0.01
3.7539 | 7.877 | 5.7539 | 4.7539 | 6.6309 | 8.6309 | 7.877 | 12.6309 | 19.2618 | 27.8927 | 3.7539 | 7.877 | 5.7539 | 4.7539 | 6.6409 | 8.6309 | 7.877 | 12.6309 | 19.2718 | 27.9027 | 0.01
4.0079 | 8.0039 | 6.0079 | 5.0079 | 7.0118 | 9.0118 | 8.0039 | 13.0118 | 20.0237 | 29.0355 | 4.0079 | 8.0039 | 6.0079 | 5.0079 | 7.0218 | 9.0118 | 8.0039 | 13.0118 | 20.0337 | 29.0455 | 0.01
8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2446 | 16.2346 | 10.4115 | 20.2346 | 34.4792 | 50.7139 | 0.01
6.8933 | 9.4467 | 8.8933 | 7.8933 | 11.34 | 13.34 | 9.4467 | 17.34 | 28.68 | 42.0201 | 6.8933 | 9.4467 | 8.8933 | 7.8933 | 11.35 | 13.34 | 9.4467 | 17.34 | 28.69 | 42.0301 | 0.01
3.0902 | 7.5451 | 5.0902 | 4.0902 | 5.6353 | 7.6353 | 7.5451 | 11.6353 | 17.2706 | 24.9059 | 3.0902 | 7.5451 | 5.0902 | 4.0902 | 5.6453 | 7.6353 | 7.5451 | 11.6353 | 17.2806 | 24.9159 | 0.01
3.6821 | 7.841 | 5.6821 | 4.6821 | 6.5231 | 8.5231 | 7.841 | 12.5231 | 19.0462 | 27.5692 | 3.6821 | 7.841 | 5.6821 | 4.6821 | 6.5331 | 8.5231 | 7.841 | 12.5231 | 19.0562 | 27.5792 | 0.01
3.021 | 7.5105 | 5.021 | 4.021 | 5.5315 | 7.5315 | 7.5105 | 11.5315 | 17.063 | 24.5945 | 3.021 | 7.5105 | 5.021 | 4.021 | 5.5415 | 7.5315 | 7.5105 | 11.5315 | 17.073 | 24.6045 | 0.01
8.4728 | 10.2364 | 10.4728 | 9.4728 | 13.7092 | 15.7092 | 10.2364 | 19.7092 | 33.4183 | 49.1275 | 8.4728 | 10.2364 | 10.4728 | 9.4728 | 13.7192 | 15.7092 | 10.2364 | 19.7092 | 33.4283 | 49.1375 | 0.01
3.493 | 7.7465 | 5.493 | 4.493 | 6.2395 | 8.2395 | 7.7465 | 12.2395 | 18.4791 | 26.7186 | 3.493 | 7.7465 | 5.493 | 4.493 | 6.2495 | 8.2395 | 7.7465 | 12.2395 | 18.4891 | 26.7286 | 0.01
9.0142 | 10.5071 | 11.0142 | 10.0142 | 14.5214 | 16.5214 | 10.5071 | 20.5214 | 35.0427 | 51.5641 | 9.0142 | 10.5071 | 11.0142 | 10.0142 | 14.5314 | 16.5214 | 10.5071 | 20.5214 | 35.0527 | 51.5741 | 0.01
10.0246 | 11.0123 | 12.0246 | 11.0246 | 16.0368 | 18.0368 | 11.0123 | 22.0368 | 38.0737 | 56.1105 | 10.0246 | 11.0123 | 12.0246 | 11.0246 | 16.0468 | 18.0368 | 11.0123 | 22.0368 | 38.0837 | 56.1205 | 0.01
9.1517 | 10.5759 | 11.1517 | 10.1517 | 14.7276 | 16.7276 | 10.5759 | 20.7276 | 35.4552 | 52.1829 | 9.1517 | 10.5759 | 11.1517 | 10.1517 | 14.7376 | 16.7276 | 10.5759 | 20.7276 | 35.4652 | 52.1929 | 0.01
4.2742 | 8.1371 | 6.2742 | 5.2742 | 7.4113 | 9.4113 | 8.1371 | 13.4113 | 20.8226 | 30.2339 | 4.2742 | 8.1371 | 6.2742 | 5.2742 | 7.4213 | 9.4113 | 8.1371 | 13.4113 | 20.8326 | 30.2439 | 0.01
4.3436 | 8.1718 | 6.3436 | 5.3436 | 7.5153 | 9.5153 | 8.1718 | 13.5153 | 21.0307 | 30.546 | 4.3436 | 8.1718 | 6.3436 | 5.3436 | 7.5253 | 9.5153 | 8.1718 | 13.5153 | 21.0407 | 30.556 | 0.01
7.5365 | 9.7683 | 9.5365 | 8.5365 | 12.3048 | 14.3048 | 9.7683 | 18.3048 | 30.6095 | 44.9143 | 7.5365 | 9.7683 | 9.5365 | 8.5365 | 12.3148 | 14.3048 | 9.7683 | 18.3048 | 30.6195 | 44.9243 | 0.01
2.6661 | 7.333 | 4.6661 | 3.6661 | 4.9991 | 6.9991 | 7.333 | 10.9991 | 15.9983 | 22.9974 | 2.6661 | 7.333 | 4.6661 | 3.6661 | 5.0091 | 6.9991 | 7.333 | 10.9991 | 16.0083 | 23.0074 | 0.01
5.1754 | 8.5877 | 7.1754 | 6.1754 | 8.7632 | 10.7632 | 8.5877 | 14.7632 | 23.5263 | 34.2895 | 5.1754 | 8.5877 | 7.1754 | 6.1754 | 8.7732 | 10.7632 | 8.5877 | 14.7632 | 23.5363 | 34.2995 | 0.01
5.602 | 8.801 | 7.602 | 6.602 | 9.4029 | 11.4029 | 8.801 | 15.4029 | 24.8059 | 36.2088 | 5.602 | 8.801 | 7.602 | 6.602 | 9.4129 | 11.4029 | 8.801 | 15.4029 | 24.8159 | 36.2188 | 0.01
2.4497 | 7.2248 | 4.4497 | 3.4497 | 4.6745 | 6.6745 | 7.2248 | 10.6745 | 15.349 | 22.0234 | 2.4497 | 7.2248 | 4.4497 | 3.4497 | 4.6845 | 6.6745 | 7.2248 | 10.6745 | 15.359 | 22.0334 | 0.01
8.632 | 10.316 | 10.632 | 9.632 | 13.948 | 15.948 | 10.316 | 19.948 | 33.8959 | 49.8439 | 8.632 | 10.316 | 10.632 | 9.632 | 13.958 | 15.948 | 10.316 | 19.948 | 33.9059 | 49.8539 | 0.01
7.3605 | 9.6802 | 9.3605 | 8.3605 | 12.0407 | 14.0407 | 9.6802 | 18.0407 | 30.0814 | 44.1221 | 7.3605 | 9.6802 | 9.3605 | 8.3605 | 12.0507 | 14.0407 | 9.6802 | 18.0407 | 30.0914 | 44.1321 | 0.01
6.2503 | 9.1251 | 8.2503 | 7.2503 | 10.3754 | 12.3754 | 9.1251 | 16.3754 | 26.7508 | 39.1262 | 6.2503 | 9.1251 | 8.2503 | 7.2503 | 10.3854 | 12.3754 | 9.1251 | 16.3754 | 26.7608 | 39.1362 | 0.01
6.4729 | 9.2365 | 8.4729 | 7.4729 | 10.7094 | 12.7094 | 9.2365 | 16.7094 | 27.4188 | 40.1282 | 6.4729 | 9.2365 | 8.4729 | 7.4729 | 10.7194 | 12.7094 | 9.2365 | 16.7094 | 27.4288 | 40.1382 | 0.01
5.0375 | 8.5187 | 7.0375 | 6.0375 | 8.5562 | 10.5562 | 8.5187 | 14.5562 | 23.1124 | 33.6686 | 5.0375 | 8.5187 | 7.0375 | 6.0375 | 8.5662 | 10.5562 | 8.5187 | 14.5562 | 23.1224 | 33.6786 | 0.01
6.4828 | 9.2414 | 8.4828 | 7.4828 | 10.7243 | 12.7243 | 9.2414 | 16.7243 | 27.4485 | 40.1728 | 6.4828 | 9.2414 | 8.4828 | 7.4828 | 10.7343 | 12.7243 | 9.2414 | 16.7243 | 27.4585 | 40.1828 | 0.01
8.6636 | 10.3318 | 10.6636 | 9.6636 | 13.9954 | 15.9954 | 10.3318 | 19.9954 | 33.9908 | 49.9862 | 8.6636 | 10.3318 | 10.6636 | 9.6636 | 14.0054 | 15.9954 | 10.3318 | 19.9954 | 34.0008 | 49.9962 | 0.01
6.1928 | 9.0964 | 8.1928 | 7.1928 | 10.2893 | 12.2893 | 9.0964 | 16.2893 | 26.5785 | 38.8678 | 6.1928 | 9.0964 | 8.1928 | 7.1928 | 10.2993 | 12.2893 | 9.0964 | 16.2893 | 26.5885 | 38.8778 | 0.01
5.2215 | 8.6108 | 7.2215 | 6.2215 | 8.8323 | 10.8323 | 8.6108 | 14.8323 | 23.6646 | 34.4969 | 5.2215 | 8.6108 | 7.2215 | 6.2215 | 8.8423 | 10.8323 | 8.6108 | 14.8323 | 23.6746 | 34.5069 | 0.01
3.3861 | 7.693 | 5.3861 | 4.3861 | 6.0791 | 8.0791 | 7.693 | 12.0791 | 18.1583 | 26.2374 | 3.3861 | 7.693 | 5.3861 | 4.3861 | 6.0891 | 8.0791 | 7.693 | 12.0791 | 18.1683 | 26.2474 | 0.01
10.7513 | 11.3757 | 12.7513 | 11.7513 | 17.127 | 19.127 | 11.3757 | 23.127 | 40.2539 | 59.3809 | 10.7513 | 11.3757 | 12.7513 | 11.7513 | 17.137 | 19.127 | 11.3757 | 23.127 | 40.2639 | 59.3909 | 0.01
5.4192 | 8.7096 | 7.4192 | 6.4192 | 9.1288 | 11.1288 | 8.7096 | 15.1288 | 24.2576 | 35.3864 | 5.4192 | 8.7096 | 7.4192 | 6.4192 | 9.1388 | 11.1288 | 8.7096 | 15.1288 | 24.2676 | 35.3964 | 0.01
10.2533 | 11.1267 | 12.2533 | 11.2533 | 16.38 | 18.38 | 11.1267 | 22.38 | 38.7599 | 57.1399 | 10.2533 | 11.1267 | 12.2533 | 11.2533 | 16.39 | 18.38 | 11.1267 | 22.38 | 38.7699 | 57.1499 | 0.01
4.7906 | 8.3953 | 6.7906 | 5.7906 | 8.1858 | 10.1858 | 8.3953 | 14.1858 | 22.3717 | 32.5575 | 4.7906 | 8.3953 | 6.7906 | 5.7906 | 8.1958 | 10.1858 | 8.3953 | 14.1858 | 22.3817 | 32.5675 | 0.01
5.4023 | 8.7011 | 7.4023 | 6.4023 | 9.1034 | 11.1034 | 8.7011 | 15.1034 | 24.2068 | 35.3102 | 5.4023 | 8.7011 | 7.4023 | 6.4023 | 9.1134 | 11.1034 | 8.7011 | 15.1034 | 24.2168 | 35.3202 | 0.01
9.2231 | 10.6116 | 11.2231 | 10.2231 | 14.8347 | 16.8347 | 10.6116 | 20.8347 | 35.6693 | 52.504 | 9.2231 | 10.6116 | 11.2231 | 10.2231 | 14.8447 | 16.8347 | 10.6116 | 20.8347 | 35.6793 | 52.514 | 0.01
6.4629 | 9.2314 | 8.4629 | 7.4629 | 10.6943 | 12.6943 | 9.2314 | 16.6943 | 27.3886 | 40.0829 | 6.4629 | 9.2314 | 8.4629 | 7.4629 | 10.7043 | 12.6943 | 9.2314 | 16.6943 | 27.3986 | 40.0929 | 0.01
3.3717 | 7.6858 | 5.3717 | 4.3717 | 6.0575 | 8.0575 | 7.6858 | 12.0575 | 18.115 | 26.1724 | 3.3717 | 7.6858 | 5.3717 | 4.3717 | 6.0675 | 8.0575 | 7.6858 | 12.0575 | 18.125 | 26.1824 | 0.01
5.6239 | 8.812 | 7.6239 | 6.6239 | 9.4359 | 11.4359 | 8.812 | 15.4359 | 24.8718 | 36.3078 | 5.6239 | 8.812 | 7.6239 | 6.6239 | 9.4459 | 11.4359 | 8.812 | 15.4359 | 24.8818 | 36.3178 | 0.01
9.3247 | 10.6624 | 11.3247 | 10.3247 | 14.9871 | 16.9871 | 10.6624 | 20.9871 | 35.9742 | 52.9613 | 9.3247 | 10.6624 | 11.3247 | 10.3247 | 14.9971 | 16.9871 | 10.6624 | 20.9871 | 35.9842 | 52.9713 | 0.01
4.3088 | 8.1544 | 6.3088 | 5.3088 | 7.4632 | 9.4632 | 8.1544 | 13.4632 | 20.9264 | 30.3896 | 4.3088 | 8.1544 | 6.3088 | 5.3088 | 7.4732 | 9.4632 | 8.1544 | 13.4632 | 20.9364 | 30.3996 | 0.01
5.0985 | 8.5493 | 7.0985 | 6.0985 | 8.6478 | 10.6478 | 8.5493 | 14.6478 | 23.2956 | 33.9434 | 5.0985 | 8.5493 | 7.0985 | 6.0985 | 8.6578 | 10.6478 | 8.5493 | 14.6478 | 23.3056 | 33.9534 | 0.01
7.6629 | 9.8315 | 9.6629 | 8.6629 | 12.4944 | 14.4944 | 9.8315 | 18.4944 | 30.9888 | 45.4832 | 7.6629 | 9.8315 | 9.6629 | 8.6629 | 12.5044 | 14.4944 | 9.8315 | 18.4944 | 30.9988 | 45.4932 | 0.01
9.3024 | 10.6512 | 11.3024 | 10.3024 | 14.9536 | 16.9536 | 10.6512 | 20.9536 | 35.9072 | 52.8609 | 9.3024 | 10.6512 | 11.3024 | 10.3024 | 14.9636 | 16.9536 | 10.6512 | 20.9536 | 35.9172 | 52.8709 | 0.01
8.7686 | 10.3843 | 10.7686 | 9.7686 | 14.1529 | 16.1529 | 10.3843 | 20.1529 | 34.3058 | 50.4587 | 8.7686 | 10.3843 | 10.7686 | 9.7686 | 14.1629 | 16.1529 | 10.3843 | 20.1529 | 34.3158 | 50.4687 | 0.01
8.1501 | 10.075 | 10.1501 | 9.1501 | 13.2251 | 15.2251 | 10.075 | 19.2251 | 32.4502 | 47.6753 | 8.1501 | 10.075 | 10.1501 | 9.1501 | 13.2351 | 15.2251 | 10.075 | 19.2251 | 32.4602 | 47.6853 | 0.01
6.7669 | 9.3835 | 8.7669 | 7.7669 | 11.1504 | 13.1504 | 9.3835 | 17.1504 | 28.3008 | 41.4512 | 6.7669 | 9.3835 | 8.7669 | 7.7669 | 11.1604 | 13.1504 | 9.3835 | 17.1504 | 28.3108 | 41.4612 | 0.01
6.0705 | 9.0352 | 8.0705 | 7.0705 | 10.1057 | 12.1057 | 9.0352 | 16.1057 | 26.2114 | 38.3171 | 6.0705 | 9.0352 | 8.0705 | 7.0705 | 10.1157 | 12.1057 | 9.0352 | 16.1057 | 26.2214 | 38.3271 | 0.01
5.7724 | 8.8862 | 7.7724 | 6.7724 | 9.6586 | 11.6586 | 8.8862 | 15.6586 | 25.3172 | 36.9757 | 5.7724 | 8.8862 | 7.7724 | 6.7724 | 9.6686 | 11.6586 | 8.8862 | 15.6586 | 25.3272 | 36.9857 | 0.01
7.6638 | 9.8319 | 9.6638 | 8.6638 | 12.4957 | 14.4957 | 9.8319 | 18.4957 | 30.9914 | 45.487 | 7.6638 | 9.8319 | 9.6638 | 8.6638 | 12.5057 | 14.4957 | 9.8319 | 18.4957 | 31.0014 | 45.497 | 0.01
5.8442 | 8.9221 | 7.8442 | 6.8442 | 9.7663 | 11.7663 | 8.9221 | 15.7663 | 25.5325 | 37.2988 | 5.8442 | 8.9221 | 7.8442 | 6.8442 | 9.7763 | 11.7663 | 8.9221 | 15.7663 | 25.5425 | 37.3088 | 0.01
4.8173 | 8.4086 | 6.8173 | 5.8173 | 8.2259 | 10.2259 | 8.4086 | 14.2259 | 22.4518 | 32.6777 | 4.8173 | 8.4086 | 6.8173 | 5.8173 | 8.2359 | 10.2259 | 8.4086 | 14.2259 | 22.4618 | 32.6877 | 0.01
3.6353 | 7.8177 | 5.6353 | 4.6353 | 6.453 | 8.453 | 7.8177 | 12.453 | 18.9059 | 27.3589 | 3.6353 | 7.8177 | 5.6353 | 4.6353 | 6.463 | 8.453 | 7.8177 | 12.453 | 18.9159 | 27.3689 | 0.01
3.3053 | 7.6526 | 5.3053 | 4.3053 | 5.9579 | 7.9579 | 7.6526 | 11.9579 | 17.9158 | 25.8737 | 3.3053 | 7.6526 | 5.3053 | 4.3053 | 5.9679 | 7.9579 | 7.6526 | 11.9579 | 17.9258 | 25.8837 | 0.01
5.0443 | 8.5222 | 7.0443 | 6.0443 | 8.5665 | 10.5665 | 8.5222 | 14.5665 | 23.133 | 33.6995 | 5.0443 | 8.5222 | 7.0443 | 6.0443 | 8.5765 | 10.5665 | 8.5222 | 14.5665 | 23.143 | 33.7095 | 0.01
8.0763 | 10.0381 | 10.0763 | 9.0763 | 13.1144 | 15.1144 | 10.0381 | 19.1144 | 32.2289 | 47.3433 | 8.0763 | 10.0381 | 10.0763 | 9.0763 | 13.1244 | 15.1144 | 10.0381 | 19.1144 | 32.2389 | 47.3533 | 0.01
4.3336 | 8.1668 | 6.3336 | 5.3336 | 7.5004 | 9.5004 | 8.1668 | 13.5004 | 21.0008 | 30.5013 | 4.3336 | 8.1668 | 6.3336 | 5.3336 | 7.5104 | 9.5004 | 8.1668 | 13.5004 | 21.0108 | 30.5113 | 0.01
9.9359 | 10.9679 | 11.9359 | 10.9359 | 15.9038 | 17.9038 | 10.9679 | 21.9038 | 37.8077 | 55.7115 | 9.9359 | 10.9679 | 11.9359 | 10.9359 | 15.9138 | 17.9038 | 10.9679 | 21.9038 | 37.8177 | 55.7215 | 0.01
6.4882 | 9.2441 | 8.4882 | 7.4882 | 10.7323 | 12.7323 | 9.2441 | 16.7323 | 27.4646 | 40.1969 | 6.4882 | 9.2441 | 8.4882 | 7.4882 | 10.7423 | 12.7323 | 9.2441 | 16.7323 | 27.4746 | 40.2069 | 0.01
3.7597 | 7.8798 | 5.7597 | 4.7597 | 6.6395 | 8.6395 | 7.8798 | 12.6395 | 19.279 | 27.9185 | 3.7597 | 7.8798 | 5.7597 | 4.7597 | 6.6495 | 8.6395 | 7.8798 | 12.6395 | 19.289 | 27.9285 | 0.01
4.1555 | 8.0777 | 6.1555 | 5.1555 | 7.2332 | 9.2332 | 8.0777 | 13.2332 | 20.4665 | 29.6997 | 4.1555 | 8.0777 | 6.1555 | 5.1555 | 7.2432 | 9.2332 | 8.0777 | 13.2332 | 20.4765 | 29.7097 | 0.01
2.6525 | 7.3263 | 4.6525 | 3.6525 | 4.9788 | 6.9788 | 7.3263 | 10.9788 | 15.9575 | 22.9363 | 2.6525 | 7.3263 | 4.6525 | 3.6525 | 4.9888 | 6.9788 | 7.3263 | 10.9788 | 15.9675 | 22.9463 | 0.01
1.8403 | 6.9201 | 3.8403 | 2.8403 | 3.7604 | 5.7604 | 6.9201 | 9.7604 | 13.5208 | 19.2812 | 1.8403 | 6.9201 | 3.8403 | 2.8403 | 3.7704 | 5.7604 | 6.9201 | 9.7604 | 13.5308 | 19.2912 | 0.01
2.6667 | 7.3334 | 4.6667 | 3.6667 | 5.0001 | 7.0001 | 7.3334 | 11.0001 | 16.0001 | 23.0002 | 2.6667 | 7.3334 | 4.6667 | 3.6667 | 5.0101 | 7.0001 | 7.3334 | 11.0001 | 16.0101 | 23.0102 | 0.01
6.4608 | 9.2304 | 8.4608 | 7.4608 | 10.6912 | 12.6912 | 9.2304 | 16.6912 | 27.3825 | 40.0737 | 6.4608 | 9.2304 | 8.4608 | 7.4608 | 10.7012 | 12.6912 | 9.2304 | 16.6912 | 27.3925 | 40.0837 | 0.01
4.1906 | 8.0953 | 6.1906 | 5.1906 | 7.2858 | 9.2858 | 8.0953 | 13.2858 | 20.5717 | 29.8575 | 4.1906 | 8.0953 | 6.1906 | 5.1906 | 7.2958 | 9.2858 | 8.0953 | 13.2858 | 20.5817 | 29.8675 | 0.01
8.6153 | 10.3077 | 10.6153 | 9.6153 | 13.923 | 15.923 | 10.3077 | 19.923 | 33.846 | 49.769 | 8.6153 | 10.3077 | 10.6153 | 9.6153 | 13.933 | 15.923 | 10.3077 | 19.923 | 33.856 | 49.779 | 0.01
4.7385 | 8.3693 | 6.7385 | 5.7385 | 8.1078 | 10.1078 | 8.3693 | 14.1078 | 22.2156 | 32.3234 | 4.7385 | 8.3693 | 6.7385 | 5.7385 | 8.1178 | 10.1078 | 8.3693 | 14.1078 | 22.2256 | 32.3334 | 0.01
2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4858 | 7.4758 | 7.4919 | 11.4758 | 16.9615 | 24.4373 | 0.01
3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.969 | 8.959 | 7.9863 | 12.959 | 19.928 | 28.8869 | 0.01
5.9707 | 8.9854 | 7.9707 | 6.9707 | 9.9561 | 11.9561 | 8.9854 | 15.9561 | 25.9121 | 37.8682 | 5.9707 | 8.9854 | 7.9707 | 6.9707 | 9.9661 | 11.9561 | 8.9854 | 15.9561 | 25.9221 | 37.8782 | 0.01
8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5566 | 15.5466 | 10.1822 | 19.5466 | 33.1032 | 48.6497 | 0.01
5.1237 | 8.5618 | 7.1237 | 6.1237 | 8.6855 | 10.6855 | 8.5618 | 14.6855 | 23.3711 | 34.0566 | 5.1237 | 8.5618 | 7.1237 | 6.1237 | 8.6955 | 10.6855 | 8.5618 | 14.6855 | 23.3811 | 34.0666 | 0.01
4.2034 | 8.1017 | 6.2034 | 5.2034 | 7.3051 | 9.3051 | 8.1017 | 13.3051 | 20.6102 | 29.9154 | 4.2034 | 8.1017 | 6.2034 | 5.2034 | 7.3151 | 9.3051 | 8.1017 | 13.3051 | 20.6202 | 29.9254 | 0.01
5.5663 | 8.7832 | 7.5663 | 6.5663 | 9.3495 | 11.3495 | 8.7832 | 15.3495 | 24.699 | 36.0484 | 5.5663 | 8.7832 | 7.5663 | 6.5663 | 9.3595 | 11.3495 | 8.7832 | 15.3495 | 24.709 | 36.0584 | 0.01
6.8431 | 9.4215 | 8.8431 | 7.8431 | 11.2646 | 13.2646 | 9.4215 | 17.2646 | 28.5292 | 41.7939 | 6.8431 | 9.4215 | 8.8431 | 7.8431 | 11.2746 | 13.2646 | 9.4215 | 17.2646 | 28.5392 | 41.8039 | 0.01
6.8551 | 9.4276 | 8.8551 | 7.8551 | 11.2827 | 13.2827 | 9.4276 | 17.2827 | 28.5654 | 41.8481 | 6.8551 | 9.4276 | 8.8551 | 7.8551 | 11.2927 | 13.2827 | 9.4276 | 17.2827 | 28.5754 | 41.8581 | 0.01
4.4435 | 8.2217 | 6.4435 | 5.4435 | 7.6652 | 9.6652 | 8.2217 | 13.6652 | 21.3304 | 30.9956 | 4.4435 | 8.2217 | 6.4435 | 5.4435 | 7.6752 | 9.6652 | 8.2217 | 13.6652 | 21.3404 | 31.0056 | 0.01
9.454 | 10.727 | 11.454 | 10.454 | 15.181 | 17.181 | 10.727 | 21.181 | 36.3619 | 53.5429 | 9.454 | 10.727 | 11.454 | 10.454 | 15.191 | 17.181 | 10.727 | 21.181 | 36.3719 | 53.5529 | 0.01
7.8182 | 9.9091 | 9.8182 | 8.8182 | 12.7273 | 14.7273 | 9.9091 | 18.7273 | 31.4547 | 46.182 | 7.8182 | 9.9091 | 9.8182 | 8.8182 | 12.7373 | 14.7273 | 9.9091 | 18.7273 | 31.4647 | 46.192 | 0.01
6.9341 | 9.4671 | 8.9341 | 7.9341 | 11.4012 | 13.4012 | 9.4671 | 17.4012 | 28.8023 | 42.2035 | 6.9341 | 9.4671 | 8.9341 | 7.9341 | 11.4112 | 13.4012 | 9.4671 | 17.4012 | 28.8123 | 42.2135 | 0.01
4.4815 | 8.2408 | 6.4815 | 5.4815 | 7.7223 | 9.7223 | 8.2408 | 13.7223 | 21.4445 | 31.1668 | 4.4815 | 8.2408 | 6.4815 | 5.4815 | 7.7323 | 9.7223 | 8.2408 | 13.7223 | 21.4545 | 31.1768 | 0.01
5.1586 | 8.5793 | 7.1586 | 6.1586 | 8.7379 | 10.7379 | 8.5793 | 14.7379 | 23.4758 | 34.2137 | 5.1586 | 8.5793 | 7.1586 | 6.1586 | 8.7479 | 10.7379 | 8.5793 | 14.7379 | 23.4858 | 34.2237 | 0.01
8.2539 | 10.1269 | 10.2539 | 9.2539 | 13.3808 | 15.3808 | 10.1269 | 19.3808 | 32.7616 | 48.1423 | 8.2539 | 10.1269 | 10.2539 | 9.2539 | 13.3908 | 15.3808 | 10.1269 | 19.3808 | 32.7716 | 48.1523 | 0.01
7.8806 | 9.9403 | 9.8806 | 8.8806 | 12.8209 | 14.8209 | 9.9403 | 18.8209 | 31.6419 | 46.4628 | 7.8806 | 9.9403 | 9.8806 | 8.8806 | 12.8309 | 14.8209 | 9.9403 | 18.8209 | 31.6519 | 46.4728 | 0.01
4.776 | 8.388 | 6.776 | 5.776 | 8.164 | 10.164 | 8.388 | 14.164 | 22.3281 | 32.4921 | 4.776 | 8.388 | 6.776 | 5.776 | 8.174 | 10.164 | 8.388 | 14.164 | 22.3381 | 32.5021 | 0.01
6.3025 | 9.1512 | 8.3025 | 7.3025 | 10.4537 | 12.4537 | 9.1512 | 16.4537 | 26.9074 | 39.3611 | 6.3025 | 9.1512 | 8.3025 | 7.3025 | 10.4637 | 12.4537 | 9.1512 | 16.4537 | 26.9174 | 39.3711 | 0.01
6.7528 | 9.3764 | 8.7528 | 7.7528 | 11.1292 | 13.1292 | 9.3764 | 17.1292 | 28.2584 | 41.3875 | 6.7528 | 9.3764 | 8.7528 | 7.7528 | 11.1392 | 13.1292 | 9.3764 | 17.1292 | 28.2684 | 41.3975 | 0.01
6.2989 | 9.1495 | 8.2989 | 7.2989 | 10.4484 | 12.4484 | 9.1495 | 16.4484 | 26.8968 | 39.3451 | 6.2989 | 9.1495 | 8.2989 | 7.2989 | 10.4584 | 12.4484 | 9.1495 | 16.4484 | 26.9068 | 39.3551 | 0.01
6.9488 | 9.4744 | 8.9488 | 7.9488 | 11.4232 | 13.4232 | 9.4744 | 17.4232 | 28.8464 | 42.2696 | 6.9488 | 9.4744 | 8.9488 | 7.9488 | 11.4332 | 13.4232 | 9.4744 | 17.4232 | 28.8564 | 42.2796 | 0.01
3.3735 | 7.6867 | 5.3735 | 4.3735 | 6.0602 | 8.0602 | 7.6867 | 12.0602 | 18.1204 | 26.1806 | 3.3735 | 7.6867 | 5.3735 | 4.3735 | 6.0702 | 8.0602 | 7.6867 | 12.0602 | 18.1304 | 26.1906 | 0.01
8.8156 | 10.4078 | 10.8156 | 9.8156 | 14.2235 | 16.2235 | 10.4078 | 20.2235 | 34.4469 | 50.6704 | 8.8156 | 10.4078 | 10.8156 | 9.8156 | 14.2335 | 16.2235 | 10.4078 | 20.2235 | 34.4569 | 50.6804 | 0.01
6.1938 | 9.0969 | 8.1938 | 7.1938 | 10.2907 | 12.2907 | 9.0969 | 16.2907 | 26.5813 | 38.872 | 6.1938 | 9.0969 | 8.1938 | 7.1938 | 10.3007 | 12.2907 | 9.0969 | 16.2907 | 26.5913 | 38.882 | 0.01
2.6892 | 7.3446 | 4.6892 | 3.6892 | 5.0338 | 7.0338 | 7.3446 | 11.0338 | 16.0676 | 23.1013 | 2.6892 | 7.3446 | 4.6892 | 3.6892 | 5.0438 | 7.0338 | 7.3446 | 11.0338 | 16.0776 | 23.1113 | 0.01
9.693 | 10.8465 | 11.693 | 10.693 | 15.5395 | 17.5395 | 10.8465 | 21.5395 | 37.0789 | 54.6184 | 9.693 | 10.8465 | 11.693 | 10.693 | 15.5495 | 17.5395 | 10.8465 | 21.5395 | 37.0889 | 54.6284 | 0.01
7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8418 | 13.8318 | 9.6106 | 17.8318 | 29.6736 | 43.5055 | 0.01
7.6207 | 9.8104 | 9.6207 | 8.6207 | 12.4311 | 14.4311 | 9.8104 | 18.4311 | 30.8621 | 45.2932 | 7.6207 | 9.8104 | 9.6207 | 8.6207 | 12.4411 | 14.4311 | 9.8104 | 18.4311 | 30.8721 | 45.3032 | 0.01
5.3109 | 8.6554 | 7.3109 | 6.3109 | 8.9663 | 10.9663 | 8.6554 | 14.9663 | 23.9327 | 34.899 | 5.3109 | 8.6554 | 7.3109 | 6.3109 | 8.9763 | 10.9663 | 8.6554 | 14.9663 | 23.9427 | 34.909 | 0.01
5.815 | 8.9075 | 7.815 | 6.815 | 9.7225 | 11.7225 | 8.9075 | 15.7225 | 25.445 | 37.1675 | 5.815 | 8.9075 | 7.815 | 6.815 | 9.7325 | 11.7225 | 8.9075 | 15.7225 | 25.455 | 37.1775 | 0.01
8.6974 | 10.3487 | 10.6974 | 9.6974 | 14.0461 | 16.0461 | 10.3487 | 20.0461 | 34.0922 | 50.1383 | 8.6974 | 10.3487 | 10.6974 | 9.6974 | 14.0561 | 16.0461 | 10.3487 | 20.0461 | 34.1022 | 50.1483 | 0.01
4.5436 | 8.2718 | 6.5436 | 5.5436 | 7.8155 | 9.8155 | 8.2718 | 13.8155 | 21.6309 | 31.4464 | 4.5436 | 8.2718 | 6.5436 | 5.5436 | 7.8255 | 9.8155 | 8.2718 | 13.8155 | 21.6409 | 31.4564 | 0.01
3.342 | 7.671 | 5.342 | 4.342 | 6.013 | 8.013 | 7.671 | 12.013 | 18.0259 | 26.0389 | 3.342 | 7.671 | 5.342 | 4.342 | 6.023 | 8.013 | 7.671 | 12.013 | 18.0359 | 26.0489 | 0.01
3.0612 | 7.5306 | 5.0612 | 4.0612 | 5.5918 | 7.5918 | 7.5306 | 11.5918 | 17.1837 | 24.7755 | 3.0612 | 7.5306 | 5.0612 | 4.0612 | 5.6018 | 7.5918 | 7.5306 | 11.5918 | 17.1937 | 24.7855 | 0.01
8.378 | 10.189 | 10.378 | 9.378 | 13.567 | 15.567 | 10.189 | 19.567 | 33.1339 | 48.7009 | 8.378 | 10.189 | 10.378 | 9.378 | 13.577 | 15.567 | 10.189 | 19.567 | 33.1439 | 48.7109 | 0.01
5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.7097 | 11.6997 | 8.8999 | 15.6997 | 25.4093 | 37.109 | 0.01
5.55 | 8.775 | 7.55 | 6.55 | 9.325 | 11.325 | 8.775 | 15.325 | 24.65 | 35.9751 | 5.55 | 8.775 | 7.55 | 6.55 | 9.335 | 11.325 | 8.775 | 15.325 | 24.66 | 35.9851 | 0.01
8.0143 | 10.0072 | 10.0143 | 9.0143 | 13.0215 | 15.0215 | 10.0072 | 19.0215 | 32.043 | 47.0645 | 8.0143 | 10.0072 | 10.0143 | 9.0143 | 13.0315 | 15.0215 | 10.0072 | 19.0215 | 32.053 | 47.0745 | 0.01
4.2615 | 8.1308 | 6.2615 | 5.2615 | 7.3923 | 9.3923 | 8.1308 | 13.3923 | 20.7846 | 30.1769 | 4.2615 | 8.1308 | 6.2615 | 5.2615 | 7.4023 | 9.3923 | 8.1308 | 13.3923 | 20.7946 | 30.1869 | 0.01
4.3816 | 8.1908 | 6.3816 | 5.3816 | 7.5724 | 9.5724 | 8.1908 | 13.5724 | 21.1449 | 30.7173 | 4.3816 | 8.1908 | 6.3816 | 5.3816 | 7.5824 | 9.5724 | 8.1908 | 13.5724 | 21.1549 | 30.7273 | 0.01
5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.7097 | 11.6997 | 8.8999 | 15.6997 | 25.4093 | 37.109 | 0.01
7.8028 | 9.9014 | 9.8028 | 8.8028 | 12.7042 | 14.7042 | 9.9014 | 18.7042 | 31.4083 | 46.1125 | 7.8028 | 9.9014 | 9.8028 | 8.8028 | 12.7142 | 14.7042 | 9.9014 | 18.7042 | 31.4183 | 46.1225 | 0.01
8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5566 | 15.5466 | 10.1822 | 19.5466 | 33.1032 | 48.6497 | 0.01
5.5132 | 8.7566 | 7.5132 | 6.5132 | 9.2698 | 11.2698 | 8.7566 | 15.2698 | 24.5397 | 35.8095 | 5.5132 | 8.7566 | 7.5132 | 6.5132 | 9.2798 | 11.2698 | 8.7566 | 15.2698 | 24.5497 | 35.8195 | 0.01
7.8861 | 9.9431 | 9.8861 | 8.8861 | 12.8292 | 14.8292 | 9.9431 | 18.8292 | 31.6583 | 46.4875 | 7.8861 | 9.9431 | 9.8861 | 8.8861 | 12.8392 | 14.8292 | 9.9431 | 18.8292 | 31.6683 | 46.4975 | 0.01
6.7892 | 9.3946 | 8.7892 | 7.7892 | 11.1838 | 13.1838 | 9.3946 | 17.1838 | 28.3676 | 41.5514 | 6.7892 | 9.3946 | 8.7892 | 7.7892 | 11.1938 | 13.1838 | 9.3946 | 17.1838 | 28.3776 | 41.5614 | 0.01
4.1869 | 8.0934 | 6.1869 | 5.1869 | 7.2803 | 9.2803 | 8.0934 | 13.2803 | 20.5606 | 29.8409 | 4.1869 | 8.0934 | 6.1869 | 5.1869 | 7.2903 | 9.2803 | 8.0934 | 13.2803 | 20.5706 | 29.8509 | 0.01
4.1938 | 8.0969 | 6.1938 | 5.1938 | 7.2907 | 9.2907 | 8.0969 | 13.2907 | 20.5813 | 29.872 | 4.1938 | 8.0969 | 6.1938 | 5.1938 | 7.3007 | 9.2907 | 8.0969 | 13.2907 | 20.5913 | 29.882 | 0.01
3.2575 | 7.6287 | 5.2575 | 4.2575 | 5.8862 | 7.8862 | 7.6287 | 11.8862 | 17.7724 | 25.6586 | 3.2575 | 7.6287 | 5.2575 | 4.2575 | 5.8962 | 7.8862 | 7.6287 | 11.8862 | 17.7824 | 25.6686 | 0.01
4.0356 | 8.0178 | 6.0356 | 5.0356 | 7.0534 | 9.0534 | 8.0178 | 13.0534 | 20.1068 | 29.1602 | 4.0356 | 8.0178 | 6.0356 | 5.0356 | 7.0634 | 9.0534 | 8.0178 | 13.0534 | 20.1168 | 29.1702 | 0.01
6.4349 | 9.2175 | 8.4349 | 7.4349 | 10.6524 | 12.6524 | 9.2175 | 16.6524 | 27.3048 | 39.9572 | 6.4349 | 9.2175 | 8.4349 | 7.4349 | 10.6624 | 12.6524 | 9.2175 | 16.6524 | 27.3148 | 39.9672 | 0.01
7.869 | 9.9345 | 9.869 | 8.869 | 12.8035 | 14.8035 | 9.9345 | 18.8035 | 31.607 | 46.4105 | 7.869 | 9.9345 | 9.869 | 8.869 | 12.8135 | 14.8035 | 9.9345 | 18.8035 | 31.617 | 46.4205 | 0.01
6.7712 | 9.3856 | 8.7712 | 7.7712 | 11.1568 | 13.1568 | 9.3856 | 17.1568 | 28.3136 | 41.4704 | 6.7712 | 9.3856 | 8.7712 | 7.7712 | 11.1668 | 13.1568 | 9.3856 | 17.1568 | 28.3236 | 41.4804 | 0.01
8.0857 | 10.0429 | 10.0857 | 9.0857 | 13.1286 | 15.1286 | 10.0429 | 19.1286 | 32.2572 | 47.3859 | 8.0857 | 10.0429 | 10.0857 | 9.0857 | 13.1386 | 15.1286 | 10.0429 | 19.1286 | 32.2672 | 47.3959 | 0.01
7.7566 | 9.8783 | 9.7566 | 8.7566 | 12.6349 | 14.6349 | 9.8783 | 18.6349 | 31.2699 | 45.9048 | 7.7566 | 9.8783 | 9.7566 | 8.7566 | 12.6449 | 14.6349 | 9.8783 | 18.6349 | 31.2799 | 45.9148 | 0.01
9.6525 | 10.8263 | 11.6525 | 10.6525 | 15.4788 | 17.4788 | 10.8263 | 21.4788 | 36.9575 | 54.4363 | 9.6525 | 10.8263 | 11.6525 | 10.6525 | 15.4888 | 17.4788 | 10.8263 | 21.4788 | 36.9675 | 54.4463 | 0.01
7.2986 | 9.6493 | 9.2986 | 8.2986 | 11.948 | 13.948 | 9.6493 | 17.948 | 29.8959 | 43.8439 | 7.2986 | 9.6493 | 9.2986 | 8.2986 | 11.958 | 13.948 | 9.6493 | 17.948 | 29.9059 | 43.8539 | 0.01
4.0521 | 8.0261 | 6.0521 | 5.0521 | 7.0782 | 9.0782 | 8.0261 | 13.0782 | 20.1564 | 29.2346 | 4.0521 | 8.0261 | 6.0521 | 5.0521 | 7.0882 | 9.0782 | 8.0261 | 13.0782 | 20.1664 | 29.2446 | 0.01
7.0371 | 9.5185 | 9.0371 | 8.0371 | 11.5556 | 13.5556 | 9.5185 | 17.5556 | 29.1112 | 42.6668 | 7.0371 | 9.5185 | 9.0371 | 8.0371 | 11.5656 | 13.5556 | 9.5185 | 17.5556 | 29.1212 | 42.6768 | 0.01
2.233 | 7.1165 | 4.233 | 3.233 | 4.3495 | 6.3495 | 7.1165 | 10.3495 | 14.6991 | 21.0486 | 2.233 | 7.1165 | 4.233 | 3.233 | 4.3595 | 6.3495 | 7.1165 | 10.3495 | 14.7091 | 21.0586 | 0.01
7.2275 | 9.6137 | 9.2275 | 8.2275 | 11.8412 | 13.8412 | 9.6137 | 17.8412 | 29.6825 | 43.5237 | 7.2275 | 9.6137 | 9.2275 | 8.2275 | 11.8512 | 13.8412 | 9.6137 | 17.8412 | 29.6925 | 43.5337 | 0.01
6.3896 | 9.1948 | 8.3896 | 7.3896 | 10.5844 | 12.5844 | 9.1948 | 16.5844 | 27.1688 | 39.7532 | 6.3896 | 9.1948 | 8.3896 | 7.3896 | 10.5944 | 12.5844 | 9.1948 | 16.5844 | 27.1788 | 39.7632 | 0.01
6.4116 | 9.2058 | 8.4116 | 7.4116 | 10.6174 | 12.6174 | 9.2058 | 16.6174 | 27.2349 | 39.8523 | 6.4116 | 9.2058 | 8.4116 | 7.4116 | 10.6274 | 12.6174 | 9.2058 | 16.6174 | 27.2449 | 39.8623 | 0.01
4.7322 | 8.3661 | 6.7322 | 5.7322 | 8.0983 | 10.0983 | 8.3661 | 14.0983 | 22.1965 | 32.2948 | 4.7322 | 8.3661 | 6.7322 | 5.7322 | 8.1083 | 10.0983 | 8.3661 | 14.0983 | 22.2065 | 32.3048 | 0.01
6.7518 | 9.3759 | 8.7518 | 7.7518 | 11.1277 | 13.1277 | 9.3759 | 17.1277 | 28.2554 | 41.3831 | 6.7518 | 9.3759 | 8.7518 | 7.7518 | 11.1377 | 13.1277 | 9.3759 | 17.1277 | 28.2654 | 41.3931 | 0.01
4.1562 | 8.0781 | 6.1562 | 5.1562 | 7.2343 | 9.2343 | 8.0781 | 13.2343 | 20.4686 | 29.7029 | 4.1562 | 8.0781 | 6.1562 | 5.1562 | 7.2443 | 9.2343 | 8.0781 | 13.2343 | 20.4786 | 29.7129 | 0.01
3.8186 | 7.9093 | 5.8186 | 4.8186 | 6.7279 | 8.7279 | 7.9093 | 12.7279 | 19.4557 | 28.1836 | 3.8186 | 7.9093 | 5.8186 | 4.8186 | 6.7379 | 8.7279 | 7.9093 | 12.7279 | 19.4657 | 28.1936 | 0.01
4.9033 | 8.4517 | 6.9033 | 5.9033 | 8.355 | 10.355 | 8.4517 | 14.355 | 22.7099 | 33.0649 | 4.9033 | 8.4517 | 6.9033 | 5.9033 | 8.365 | 10.355 | 8.4517 | 14.355 | 22.7199 | 33.0749 | 0.01
3.8613 | 7.9307 | 5.8613 | 4.8613 | 6.792 | 8.792 | 7.9307 | 12.792 | 19.584 | 28.376 | 3.8613 | 7.9307 | 5.8613 | 4.8613 | 6.802 | 8.792 | 7.9307 | 12.792 | 19.594 | 28.386 | 0.01
8.8507 | 10.4253 | 10.8507 | 9.8507 | 14.276 | 16.276 | 10.4253 | 20.276 | 34.5521 | 50.8281 | 8.8507 | 10.4253 | 10.8507 | 9.8507 | 14.286 | 16.276 | 10.4253 | 20.276 | 34.5621 | 50.8381 | 0.01
4.7771 | 8.3886 | 6.7771 | 5.7771 | 8.1657 | 10.1657 | 8.3886 | 14.1657 | 22.3314 | 32.4971 | 4.7771 | 8.3886 | 6.7771 | 5.7771 | 8.1757 | 10.1657 | 8.3886 | 14.1657 | 22.3414 | 32.5071 | 0.01
6.5063 | 9.2532 | 8.5063 | 7.5063 | 10.7595 | 12.7595 | 9.2532 | 16.7595 | 27.519 | 40.2786 | 6.5063 | 9.2532 | 8.5063 | 7.5063 | 10.7695 | 12.7595 | 9.2532 | 16.7595 | 27.529 | 40.2886 | 0.01
6.9271 | 9.4636 | 8.9271 | 7.9271 | 11.3907 | 13.3907 | 9.4636 | 17.3907 | 28.7813 | 42.172 | 6.9271 | 9.4636 | 8.9271 | 7.9271 | 11.4007 | 13.3907 | 9.4636 | 17.3907 | 28.7913 | 42.182 | 0.01
4.2626 | 8.1313 | 6.2626 | 5.2626 | 7.394 | 9.394 | 8.1313 | 13.394 | 20.7879 | 30.1819 | 4.2626 | 8.1313 | 6.2626 | 5.2626 | 7.404 | 9.394 | 8.1313 | 13.394 | 20.7979 | 30.1919 | 0.01
2.6952 | 7.3476 | 4.6952 | 3.6952 | 5.0428 | 7.0428 | 7.3476 | 11.0428 | 16.0856 | 23.1284 | 2.6952 | 7.3476 | 4.6952 | 3.6952 | 5.0528 | 7.0428 | 7.3476 | 11.0428 | 16.0956 | 23.1384 | 0.01
7.9818 | 9.9909 | 9.9818 | 8.9818 | 12.9728 | 14.9728 | 9.9909 | 18.9728 | 31.9455 | 46.9183 | 7.9818 | 9.9909 | 9.9818 | 8.9818 | 12.9828 | 14.9728 | 9.9909 | 18.9728 | 31.9555 | 46.9283 | 0.01
4.4602 | 8.2301 | 6.4602 | 5.4602 | 7.6903 | 9.6903 | 8.2301 | 13.6903 | 21.3806 | 31.0709 | 4.4602 | 8.2301 | 6.4602 | 5.4602 | 7.7003 | 9.6903 | 8.2301 | 13.6903 | 21.3906 | 31.0809 | 0.01
7.8904 | 9.9452 | 9.8904 | 8.8904 | 12.8356 | 14.8356 | 9.9452 | 18.8356 | 31.6712 | 46.5069 | 7.8904 | 9.9452 | 9.8904 | 8.8904 | 12.8456 | 14.8356 | 9.9452 | 18.8356 | 31.6812 | 46.5169 | 0.01
4.5586 | 8.2793 | 6.5586 | 5.5586 | 7.8379 | 9.8379 | 8.2793 | 13.8379 | 21.6757 | 31.5136 | 4.5586 | 8.2793 | 6.5586 | 5.5586 | 7.8479 | 9.8379 | 8.2793 | 13.8379 | 21.6857 | 31.5236 | 0.01
5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0438 | 11.0338 | 8.6779 | 15.0338 | 24.0776 | 35.1113 | 0.01
4.5162 | 8.2581 | 6.5162 | 5.5162 | 7.7743 | 9.7743 | 8.2581 | 13.7743 | 21.5486 | 31.3228 | 4.5162 | 8.2581 | 6.5162 | 5.5162 | 7.7843 | 9.7743 | 8.2581 | 13.7743 | 21.5586 | 31.3328 | 0.01
4.8841 | 8.442 | 6.8841 | 5.8841 | 8.3261 | 10.3261 | 8.442 | 14.3261 | 22.6522 | 32.9782 | 4.8841 | 8.442 | 6.8841 | 5.8841 | 8.3361 | 10.3261 | 8.442 | 14.3261 | 22.6622 | 32.9882 | 0.01
5.6401 | 8.8201 | 7.6401 | 6.6401 | 9.4602 | 11.4602 | 8.8201 | 15.4602 | 24.9204 | 36.3806 | 5.6401 | 8.8201 | 7.6401 | 6.6401 | 9.4702 | 11.4602 | 8.8201 | 15.4602 | 24.9304 | 36.3906 | 0.01
9.7333 | 10.8666 | 11.7333 | 10.7333 | 15.5999 | 17.5999 | 10.8666 | 21.5999 | 37.1998 | 54.7997 | 9.7333 | 10.8666 | 11.7333 | 10.7333 | 15.6099 | 17.5999 | 10.8666 | 21.5999 | 37.2098 | 54.8097 | 0.01
4.4464 | 8.2232 | 6.4464 | 5.4464 | 7.6696 | 9.6696 | 8.2232 | 13.6696 | 21.3391 | 31.0087 | 4.4464 | 8.2232 | 6.4464 | 5.4464 | 7.6796 | 9.6696 | 8.2232 | 13.6696 | 21.3491 | 31.0187 | 0.01
3.4011 | 7.7006 | 5.4011 | 4.4011 | 6.1017 | 8.1017 | 7.7006 | 12.1017 | 18.2034 | 26.305 | 3.4011 | 7.7006 | 5.4011 | 4.4011 | 6.1117 | 8.1017 | 7.7006 | 12.1017 | 18.2134 | 26.315 | 0.01
5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9451 | 10.9351 | 8.645 | 14.9351 | 23.8802 | 34.8153 | 0.01
2.1888 | 7.0944 | 4.1888 | 3.1888 | 4.2832 | 6.2832 | 7.0944 | 10.2832 | 14.5665 | 20.8497 | 2.1888 | 7.0944 | 4.1888 | 3.1888 | 4.2932 | 6.2832 | 7.0944 | 10.2832 | 14.5765 | 20.8597 | 0.01
6.8979 | 9.449 | 8.8979 | 7.8979 | 11.3469 | 13.3469 | 9.449 | 17.3469 | 28.6937 | 42.0406 | 6.8979 | 9.449 | 8.8979 | 7.8979 | 11.3569 | 13.3469 | 9.449 | 17.3469 | 28.7037 | 42.0506 | 0.01
4.4544 | 8.2272 | 6.4544 | 5.4544 | 7.6816 | 9.6816 | 8.2272 | 13.6816 | 21.3633 | 31.0449 | 4.4544 | 8.2272 | 6.4544 | 5.4544 | 7.6916 | 9.6816 | 8.2272 | 13.6816 | 21.3733 | 31.0549 | 0.01
5.3782 | 8.6891 | 7.3782 | 6.3782 | 9.0673 | 11.0673 | 8.6891 | 15.0673 | 24.1346 | 35.202 | 5.3782 | 8.6891 | 7.3782 | 6.3782 | 9.0773 | 11.0673 | 8.6891 | 15.0673 | 24.1446 | 35.212 | 0.01
4.8642 | 8.4321 | 6.8642 | 5.8642 | 8.2962 | 10.2962 | 8.4321 | 14.2962 | 22.5925 | 32.8887 | 4.8642 | 8.4321 | 6.8642 | 5.8642 | 8.3062 | 10.2962 | 8.4321 | 14.2962 | 22.6025 | 32.8987 | 0.01
6.4795 | 9.2398 | 8.4795 | 7.4795 | 10.7193 | 12.7193 | 9.2398 | 16.7193 | 27.4386 | 40.1579 | 6.4795 | 9.2398 | 8.4795 | 7.4795 | 10.7293 | 12.7193 | 9.2398 | 16.7193 | 27.4486 | 40.1679 | 0.01
6.2353 | 9.1177 | 8.2353 | 7.2353 | 10.353 | 12.353 | 9.1177 | 16.353 | 26.7059 | 39.0589 | 6.2353 | 9.1177 | 8.2353 | 7.2353 | 10.363 | 12.353 | 9.1177 | 16.353 | 26.7159 | 39.0689 | 0.01
6.6358 | 9.3179 | 8.6358 | 7.6358 | 10.9537 | 12.9537 | 9.3179 | 16.9537 | 27.9073 | 40.861 | 6.6358 | 9.3179 | 8.6358 | 7.6358 | 10.9637 | 12.9537 | 9.3179 | 16.9537 | 27.9173 | 40.871 | 0.01
5.2598 | 8.6299 | 7.2598 | 6.2598 | 8.8898 | 10.8898 | 8.6299 | 14.8898 | 23.7795 | 34.6693 | 5.2598 | 8.6299 | 7.2598 | 6.2598 | 8.8998 | 10.8898 | 8.6299 | 14.8898 | 23.7895 | 34.6793 | 0.01
5.8382 | 8.9191 | 7.8382 | 6.8382 | 9.7573 | 11.7573 | 8.9191 | 15.7573 | 25.5145 | 37.2718 | 5.8382 | 8.9191 | 7.8382 | 6.8382 | 9.7673 | 11.7573 | 8.9191 | 15.7573 | 25.5245 | 37.2818 | 0.01
3.6537 | 7.8268 | 5.6537 | 4.6537 | 6.4805 | 8.4805 | 7.8268 | 12.4805 | 18.961 | 27.4415 | 3.6537 | 7.8268 | 5.6537 | 4.6537 | 6.4905 | 8.4805 | 7.8268 | 12.4805 | 18.971 | 27.4515 | 0.01
10.3093 | 11.1546 | 12.3093 | 11.3093 | 16.4639 | 18.4639 | 11.1546 | 22.4639 | 38.9278 | 57.3917 | 10.3093 | 11.1546 | 12.3093 | 11.3093 | 16.4739 | 18.4639 | 11.1546 | 22.4639 | 38.9378 | 57.4017 | 0.01
2.9072 | 7.4536 | 4.9072 | 3.9072 | 5.3609 | 7.3609 | 7.4536 | 11.3609 | 16.7217 | 24.0826 | 2.9072 | 7.4536 | 4.9072 | 3.9072 | 5.3709 | 7.3609 | 7.4536 | 11.3609 | 16.7317 | 24.0926 | 0.01
8.8398 | 10.4199 | 10.8398 | 9.8398 | 14.2596 | 16.2596 | 10.4199 | 20.2596 | 34.5193 | 50.7789 | 8.8398 | 10.4199 | 10.8398 | 9.8398 | 14.2696 | 16.2596 | 10.4199 | 20.2596 | 34.5293 | 50.7889 | 0.01
4.7994 | 8.3997 | 6.7994 | 5.7994 | 8.1991 | 10.1991 | 8.3997 | 14.1991 | 22.3981 | 32.5972 | 4.7994 | 8.3997 | 6.7994 | 5.7994 | 8.2091 | 10.1991 | 8.3997 | 14.1991 | 22.4081 | 32.6072 | 0.01
4.8728 | 8.4364 | 6.8728 | 5.8728 | 8.3092 | 10.3092 | 8.4364 | 14.3092 | 22.6183 | 32.9275 | 4.8728 | 8.4364 | 6.8728 | 5.8728 | 8.3192 | 10.3092 | 8.4364 | 14.3092 | 22.6283 | 32.9375 | 0.01
8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2446 | 16.2346 | 10.4115 | 20.2346 | 34.4792 | 50.7139 | 0.01
8.2877 | 10.1438 | 10.2877 | 9.2877 | 13.4315 | 15.4315 | 10.1438 | 19.4315 | 32.863 | 48.2945 | 8.2877 | 10.1438 | 10.2877 | 9.2877 | 13.4415 | 15.4315 | 10.1438 | 19.4315 | 32.873 | 48.3045 | 0.01
5.1521 | 8.576 | 7.1521 | 6.1521 | 8.7281 | 10.7281 | 8.576 | 14.7281 | 23.4562 | 34.1843 | 5.1521 | 8.576 | 7.1521 | 6.1521 | 8.7381 | 10.7281 | 8.576 | 14.7281 | 23.4662 | 34.1943 | 0.01
7.8614 | 9.9307 | 9.8614 | 8.8614 | 12.7921 | 14.7921 | 9.9307 | 18.7921 | 31.5843 | 46.3764 | 7.8614 | 9.9307 | 9.8614 | 8.8614 | 12.8021 | 14.7921 | 9.9307 | 18.7921 | 31.5943 | 46.3864 | 0.01
7.2199 | 9.61 | 9.2199 | 8.2199 | 11.8299 | 13.8299 | 9.61 | 17.8299 | 29.6598 | 43.4897 | 7.2199 | 9.61 | 9.2199 | 8.2199 | 11.8399 | 13.8299 | 9.61 | 17.8299 | 29.6698 | 43.4997 | 0.01
5.6179 | 8.8089 | 7.6179 | 6.6179 | 9.4268 | 11.4268 | 8.8089 | 15.4268 | 24.8536 | 36.2804 | 5.6179 | 8.8089 | 7.6179 | 6.6179 | 9.4368 | 11.4268 | 8.8089 | 15.4268 | 24.8636 | 36.2904 | 0.01
2.7189 | 7.3595 | 4.7189 | 3.7189 | 5.0784 | 7.0784 | 7.3595 | 11.0784 | 16.1568 | 23.2352 | 2.7189 | 7.3595 | 4.7189 | 3.7189 | 5.0884 | 7.0784 | 7.3595 | 11.0784 | 16.1668 | 23.2452 | 0.01
7.0937 | 9.5468 | 9.0937 | 8.0937 | 11.6405 | 13.6405 | 9.5468 | 17.6405 | 29.281 | 42.9215 | 7.0937 | 9.5468 | 9.0937 | 8.0937 | 11.6505 | 13.6405 | 9.5468 | 17.6405 | 29.291 | 42.9315 | 0.01
6.5789 | 9.2894 | 8.5789 | 7.5789 | 10.8683 | 12.8683 | 9.2894 | 16.8683 | 27.7367 | 40.605 | 6.5789 | 9.2894 | 8.5789 | 7.5789 | 10.8783 | 12.8683 | 9.2894 | 16.8683 | 27.7467 | 40.615 | 0.01
4.9738 | 8.4869 | 6.9738 | 5.9738 | 8.4606 | 10.4606 | 8.4869 | 14.4606 | 22.9213 | 33.3819 | 4.9738 | 8.4869 | 6.9738 | 5.9738 | 8.4706 | 10.4606 | 8.4869 | 14.4606 | 22.9313 | 33.3919 | 0.01
5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.1014 | 11.0914 | 8.6971 | 15.0914 | 24.1928 | 35.2841 | 0.01
3.3249 | 7.6624 | 5.3249 | 4.3249 | 5.9873 | 7.9873 | 7.6624 | 11.9873 | 17.9746 | 25.9618 | 3.3249 | 7.6624 | 5.3249 | 4.3249 | 5.9973 | 7.9873 | 7.6624 | 11.9873 | 17.9846 | 25.9718 | 0.01
5.9637 | 8.9818 | 7.9637 | 6.9637 | 9.9455 | 11.9455 | 8.9818 | 15.9455 | 25.891 | 37.8365 | 5.9637 | 8.9818 | 7.9637 | 6.9637 | 9.9555 | 11.9455 | 8.9818 | 15.9455 | 25.901 | 37.8465 | 0.01
3.7881 | 7.894 | 5.7881 | 4.7881 | 6.6821 | 8.6821 | 7.894 | 12.6821 | 19.3643 | 28.0464 | 3.7881 | 7.894 | 5.7881 | 4.7881 | 6.6921 | 8.6821 | 7.894 | 12.6821 | 19.3743 | 28.0564 | 0.01
8.004 | 10.002 | 10.004 | 9.004 | 13.0059 | 15.0059 | 10.002 | 19.0059 | 32.0119 | 47.0178 | 8.004 | 10.002 | 10.004 | 9.004 | 13.0159 | 15.0059 | 10.002 | 19.0059 | 32.0219 | 47.0278 | 0.01
7.6199 | 9.8099 | 9.6199 | 8.6199 | 12.4298 | 14.4298 | 9.8099 | 18.4298 | 30.8596 | 45.2893 | 7.6199 | 9.8099 | 9.6199 | 8.6199 | 12.4398 | 14.4298 | 9.8099 | 18.4298 | 30.8696 | 45.2993 | 0.01
5.0882 | 8.5441 | 7.0882 | 6.0882 | 8.6323 | 10.6323 | 8.5441 | 14.6323 | 23.2646 | 33.8968 | 5.0882 | 8.5441 | 7.0882 | 6.0882 | 8.6423 | 10.6323 | 8.5441 | 14.6323 | 23.2746 | 33.9068 | 0.01
4.9297 | 8.4649 | 6.9297 | 5.9297 | 8.3946 | 10.3946 | 8.4649 | 14.3946 | 22.7891 | 33.1837 | 4.9297 | 8.4649 | 6.9297 | 5.9297 | 8.4046 | 10.3946 | 8.4649 | 14.3946 | 22.7991 | 33.1937 | 0.01
1.9638 | 6.9819 | 3.9638 | 2.9638 | 3.9457 | 5.9457 | 6.9819 | 9.9457 | 13.8914 | 19.8371 | 1.9638 | 6.9819 | 3.9638 | 2.9638 | 3.9557 | 5.9457 | 6.9819 | 9.9457 | 13.9014 | 19.8471 | 0.01
5.227 | 8.6135 | 7.227 | 6.227 | 8.8405 | 10.8405 | 8.6135 | 14.8405 | 23.6809 | 34.5214 | 5.227 | 8.6135 | 7.227 | 6.227 | 8.8505 | 10.8405 | 8.6135 | 14.8405 | 23.6909 | 34.5314 | 0.01
2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4858 | 7.4758 | 7.4919 | 11.4758 | 16.9615 | 24.4373 | 0.01
6.9433 | 9.4717 | 8.9433 | 7.9433 | 11.415 | 13.415 | 9.4717 | 17.415 | 28.83 | 42.245 | 6.9433 | 9.4717 | 8.9433 | 7.9433 | 11.425 | 13.415 | 9.4717 | 17.415 | 28.84 | 42.255 | 0.01
5.765 | 8.8825 | 7.765 | 6.765 | 9.6475 | 11.6475 | 8.8825 | 15.6475 | 25.295 | 36.9425 | 5.765 | 8.8825 | 7.765 | 6.765 | 9.6575 | 11.6475 | 8.8825 | 15.6475 | 25.305 | 36.9525 | 0.01
2.6494 | 7.3247 | 4.6494 | 3.6494 | 4.9741 | 6.9741 | 7.3247 | 10.9741 | 15.9482 | 22.9223 | 2.6494 | 7.3247 | 4.6494 | 3.6494 | 4.9841 | 6.9741 | 7.3247 | 10.9741 | 15.9582 | 22.9323 | 0.01
7.3038 | 9.6519 | 9.3038 | 8.3038 | 11.9556 | 13.9556 | 9.6519 | 17.9556 | 29.9113 | 43.8669 | 7.3038 | 9.6519 | 9.3038 | 8.3038 | 11.9656 | 13.9556 | 9.6519 | 17.9556 | 29.9213 | 43.8769 | 0.01
3.554 | 7.777 | 5.554 | 4.554 | 6.3309 | 8.3309 | 7.777 | 12.3309 | 18.6619 | 26.9928 | 3.554 | 7.777 | 5.554 | 4.554 | 6.3409 | 8.3309 | 7.777 | 12.3309 | 18.6719 | 27.0028 | 0.01
5.9113 | 8.9557 | 7.9113 | 6.9113 | 9.867 | 11.867 | 8.9557 | 15.867 | 25.7339 | 37.6009 | 5.9113 | 8.9557 | 7.9113 | 6.9113 | 9.877 | 11.867 | 8.9557 | 15.867 | 25.7439 | 37.6109 | 0.01
8.773 | 10.3865 | 10.773 | 9.773 | 14.1595 | 16.1595 | 10.3865 | 20.1595 | 34.319 | 50.4785 | 8.773 | 10.3865 | 10.773 | 9.773 | 14.1695 | 16.1595 | 10.3865 | 20.1595 | 34.329 | 50.4885 | 0.01
6.175 | 9.0875 | 8.175 | 7.175 | 10.2625 | 12.2625 | 9.0875 | 16.2625 | 26.5251 | 38.7876 | 6.175 | 9.0875 | 8.175 | 7.175 | 10.2725 | 12.2625 | 9.0875 | 16.2625 | 26.5351 | 38.7976 | 0.01
7.0464 | 9.5232 | 9.0464 | 8.0464 | 11.5695 | 13.5695 | 9.5232 | 17.5695 | 29.1391 | 42.7086 | 7.0464 | 9.5232 | 9.0464 | 8.0464 | 11.5795 | 13.5695 | 9.5232 | 17.5695 | 29.1491 | 42.7186 | 0.01
4.9413 | 8.4707 | 6.9413 | 5.9413 | 8.412 | 10.412 | 8.4707 | 14.412 | 22.824 | 33.236 | 4.9413 | 8.4707 | 6.9413 | 5.9413 | 8.422 | 10.412 | 8.4707 | 14.412 | 22.834 | 33.246 | 0.01
4.8679 | 8.434 | 6.8679 | 5.8679 | 8.3019 | 10.3019 | 8.434 | 14.3019 | 22.6038 | 32.9057 | 4.8679 | 8.434 | 6.8679 | 5.8679 | 8.3119 | 10.3019 | 8.434 | 14.3019 | 22.6138 | 32.9157 | 0.01
4.8742 | 8.4371 | 6.8742 | 5.8742 | 8.3113 | 10.3113 | 8.4371 | 14.3113 | 22.6226 | 32.9339 | 4.8742 | 8.4371 | 6.8742 | 5.8742 | 8.3213 | 10.3113 | 8.4371 | 14.3113 | 22.6326 | 32.9439 | 0.01
9.329 | 10.6645 | 11.329 | 10.329 | 14.9935 | 16.9935 | 10.6645 | 20.9935 | 35.987 | 52.9806 | 9.329 | 10.6645 | 11.329 | 10.329 | 15.0035 | 16.9935 | 10.6645 | 20.9935 | 35.997 | 52.9906 | 0.01
7.5224 | 9.7612 | 9.5224 | 8.5224 | 12.2836 | 14.2836 | 9.7612 | 18.2836 | 30.5671 | 44.8507 | 7.5224 | 9.7612 | 9.5224 | 8.5224 | 12.2936 | 14.2836 | 9.7612 | 18.2836 | 30.5771 | 44.8607 | 0.01
8.1979 | 10.0989 | 10.1979 | 9.1979 | 13.2968 | 15.2968 | 10.0989 | 19.2968 | 32.5936 | 47.8904 | 8.1979 | 10.0989 | 10.1979 | 9.1979 | 13.3068 | 15.2968 | 10.0989 | 19.2968 | 32.6036 | 47.9004 | 0.01
5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8393 | 10.8293 | 8.6098 | 14.8293 | 23.6687 | 34.498 | 0.01
8.1953 | 10.0977 | 10.1953 | 9.1953 | 13.293 | 15.293 | 10.0977 | 19.293 | 32.586 | 47.8791 | 8.1953 | 10.0977 | 10.1953 | 9.1953 | 13.303 | 15.293 | 10.0977 | 19.293 | 32.596 | 47.8891 | 0.01
4.9143 | 8.4572 | 6.9143 | 5.9143 | 8.3715 | 10.3715 | 8.4572 | 14.3715 | 22.7429 | 33.1144 | 4.9143 | 8.4572 | 6.9143 | 5.9143 | 8.3815 | 10.3715 | 8.4572 | 14.3715 | 22.7529 | 33.1244 | 0.01
8.9991 | 10.4995 | 10.9991 | 9.9991 | 14.4986 | 16.4986 | 10.4995 | 20.4986 | 34.9973 | 51.4959 | 8.9991 | 10.4995 | 10.9991 | 9.9991 | 14.5086 | 16.4986 | 10.4995 | 20.4986 | 35.0073 | 51.5059 | 0.01
3.9365 | 7.9683 | 5.9365 | 4.9365 | 6.9048 | 8.9048 | 7.9683 | 12.9048 | 19.8096 | 28.7143 | 3.9365 | 7.9683 | 5.9365 | 4.9365 | 6.9148 | 8.9048 | 7.9683 | 12.9048 | 19.8196 | 28.7243 | 0.01
7.8134 | 9.9067 | 9.8134 | 8.8134 | 12.7201 | 14.7201 | 9.9067 | 18.7201 | 31.4401 | 46.1602 | 7.8134 | 9.9067 | 9.8134 | 8.8134 | 12.7301 | 14.7201 | 9.9067 | 18.7201 | 31.4501 | 46.1702 | 0.01
4.0634 | 8.0317 | 6.0634 | 5.0634 | 7.0951 | 9.0951 | 8.0317 | 13.0951 | 20.1902 | 29.2853 | 4.0634 | 8.0317 | 6.0634 | 5.0634 | 7.1051 | 9.0951 | 8.0317 | 13.0951 | 20.2002 | 29.2953 | 0.01
6.7403 | 9.3702 | 8.7403 | 7.7403 | 11.1105 | 13.1105 | 9.3702 | 17.1105 | 28.221 | 41.3314 | 6.7403 | 9.3702 | 8.7403 | 7.7403 | 11.1205 | 13.1105 | 9.3702 | 17.1105 | 28.231 | 41.3414 | 0.01
5.6408 | 8.8204 | 7.6408 | 6.6408 | 9.4611 | 11.4611 | 8.8204 | 15.4611 | 24.9223 | 36.3834 | 5.6408 | 8.8204 | 7.6408 | 6.6408 | 9.4711 | 11.4611 | 8.8204 | 15.4611 | 24.9323 | 36.3934 | 0.01
6.2507 | 9.1254 | 8.2507 | 7.2507 | 10.3761 | 12.3761 | 9.1254 | 16.3761 | 26.7522 | 39.1283 | 6.2507 | 9.1254 | 8.2507 | 7.2507 | 10.3861 | 12.3761 | 9.1254 | 16.3761 | 26.7622 | 39.1383 | 0.01
8.3342 | 10.1671 | 10.3342 | 9.3342 | 13.5013 | 15.5013 | 10.1671 | 19.5013 | 33.0026 | 48.5039 | 8.3342 | 10.1671 | 10.3342 | 9.3342 | 13.5113 | 15.5013 | 10.1671 | 19.5013 | 33.0126 | 48.5139 | 0.01
9.8378 | 10.9189 | 11.8378 | 10.8378 | 15.7567 | 17.7567 | 10.9189 | 21.7567 | 37.5135 | 55.2702 | 9.8378 | 10.9189 | 11.8378 | 10.8378 | 15.7667 | 17.7567 | 10.9189 | 21.7567 | 37.5235 | 55.2802 | 0.01
5.9193 | 8.9596 | 7.9193 | 6.9193 | 9.8789 | 11.8789 | 8.9596 | 15.8789 | 25.7578 | 37.6367 | 5.9193 | 8.9596 | 7.9193 | 6.9193 | 9.8889 | 11.8789 | 8.9596 | 15.8789 | 25.7678 | 37.6467 | 0.01
9.7806 | 10.8903 | 11.7806 | 10.7806 | 15.6709 | 17.6709 | 10.8903 | 21.6709 | 37.3418 | 55.0127 | 9.7806 | 10.8903 | 11.7806 | 10.7806 | 15.6809 | 17.6709 | 10.8903 | 21.6709 | 37.3518 | 55.0227 | 0.01
7.2998 | 9.6499 | 9.2998 | 8.2998 | 11.9497 | 13.9497 | 9.6499 | 17.9497 | 29.8993 | 43.849 | 7.2998 | 9.6499 | 9.2998 | 8.2998 | 11.9597 | 13.9497 | 9.6499 | 17.9497 | 29.9093 | 43.859 | 0.01
5.2258 | 8.6129 | 7.2258 | 6.2258 | 8.8387 | 10.8387 | 8.6129 | 14.8387 | 23.6775 | 34.5162 | 5.2258 | 8.6129 | 7.2258 | 6.2258 | 8.8487 | 10.8387 | 8.6129 | 14.8387 | 23.6875 | 34.5262 | 0.01
5.5571 | 8.7785 | 7.5571 | 6.5571 | 9.3356 | 11.3356 | 8.7785 | 15.3356 | 24.6712 | 36.0068 | 5.5571 | 8.7785 | 7.5571 | 6.5571 | 9.3456 | 11.3356 | 8.7785 | 15.3356 | 24.6812 | 36.0168 | 0.01
3.6445 | 7.8223 | 5.6445 | 4.6445 | 6.4668 | 8.4668 | 7.8223 | 12.4668 | 18.9335 | 27.4003 | 3.6445 | 7.8223 | 5.6445 | 4.6445 | 6.4768 | 8.4668 | 7.8223 | 12.4668 | 18.9435 | 27.4103 | 0.01
4.0026 | 8.0013 | 6.0026 | 5.0026 | 7.0039 | 9.0039 | 8.0013 | 13.0039 | 20.0078 | 29.0117 | 4.0026 | 8.0013 | 6.0026 | 5.0026 | 7.0139 | 9.0039 | 8.0013 | 13.0039 | 20.0178 | 29.0217 | 0.01
6.0532 | 9.0266 | 8.0532 | 7.0532 | 10.0798 | 12.0798 | 9.0266 | 16.0798 | 26.1595 | 38.2393 | 6.0532 | 9.0266 | 8.0532 | 7.0532 | 10.0898 | 12.0798 | 9.0266 | 16.0798 | 26.1695 | 38.2493 | 0.01
6.9761 | 9.4881 | 8.9761 | 7.9761 | 11.4642 | 13.4642 | 9.4881 | 17.4642 | 28.9284 | 42.3925 | 6.9761 | 9.4881 | 8.9761 | 7.9761 | 11.4742 | 13.4642 | 9.4881 | 17.4642 | 28.9384 | 42.4025 | 0.01
2.4113 | 7.2056 | 4.4113 | 3.4113 | 4.6169 | 6.6169 | 7.2056 | 10.6169 | 15.2338 | 21.8508 | 2.4113 | 7.2056 | 4.4113 | 3.4113 | 4.6269 | 6.6169 | 7.2056 | 10.6169 | 15.2438 | 21.8608 | 0.01
3.7525 | 7.8762 | 5.7525 | 4.7525 | 6.6287 | 8.6287 | 7.8762 | 12.6287 | 19.2575 | 27.8862 | 3.7525 | 7.8762 | 5.7525 | 4.7525 | 6.6387 | 8.6287 | 7.8762 | 12.6287 | 19.2675 | 27.8962 | 0.01
6.4384 | 9.2192 | 8.4384 | 7.4384 | 10.6576 | 12.6576 | 9.2192 | 16.6576 | 27.3151 | 39.9727 | 6.4384 | 9.2192 | 8.4384 | 7.4384 | 10.6676 | 12.6576 | 9.2192 | 16.6576 | 27.3251 | 39.9827 | 0.01
1.4433 | 6.7216 | 3.4433 | 2.4433 | 3.1649 | 5.1649 | 6.7216 | 9.1649 | 12.3299 | 17.4948 | 1.4433 | 6.7216 | 3.4433 | 2.4433 | 3.1749 | 5.1649 | 6.7216 | 9.1649 | 12.3399 | 17.5048 | 0.01
7.9113 | 9.9557 | 9.9113 | 8.9113 | 12.867 | 14.867 | 9.9557 | 18.867 | 31.734 | 46.6009 | 7.9113 | 9.9557 | 9.9113 | 8.9113 | 12.877 | 14.867 | 9.9557 | 18.867 | 31.744 | 46.6109 | 0.01
4.1557 | 8.0779 | 6.1557 | 5.1557 | 7.2336 | 9.2336 | 8.0779 | 13.2336 | 20.4672 | 29.7007 | 4.1557 | 8.0779 | 6.1557 | 5.1557 | 7.2436 | 9.2336 | 8.0779 | 13.2336 | 20.4772 | 29.7107 | 0.01
9.7438 | 10.8719 | 11.7438 | 10.7438 | 15.6157 | 17.6157 | 10.8719 | 21.6157 | 37.2314 | 54.8471 | 9.7438 | 10.8719 | 11.7438 | 10.7438 | 15.6257 | 17.6157 | 10.8719 | 21.6157 | 37.2414 | 54.8571 | 0.01
8.0146 | 10.0073 | 10.0146 | 9.0146 | 13.0219 | 15.0219 | 10.0073 | 19.0219 | 32.0438 | 47.0657 | 8.0146 | 10.0073 | 10.0146 | 9.0146 | 13.0319 | 15.0219 | 10.0073 | 19.0219 | 32.0538 | 47.0757 | 0.01
7.2032 | 9.6016 | 9.2032 | 8.2032 | 11.8048 | 13.8048 | 9.6016 | 17.8048 | 29.6096 | 43.4144 | 7.2032 | 9.6016 | 9.2032 | 8.2032 | 11.8148 | 13.8048 | 9.6016 | 17.8048 | 29.6196 | 43.4244 | 0.01
5.1038 | 8.5519 | 7.1038 | 6.1038 | 8.6557 | 10.6557 | 8.5519 | 14.6557 | 23.3113 | 33.967 | 5.1038 | 8.5519 | 7.1038 | 6.1038 | 8.6657 | 10.6557 | 8.5519 | 14.6557 | 23.3213 | 33.977 | 0.01
10.3046 | 11.1523 | 12.3046 | 11.3046 | 16.4569 | 18.4569 | 11.1523 | 22.4569 | 38.9138 | 57.3707 | 10.3046 | 11.1523 | 12.3046 | 11.3046 | 16.4669 | 18.4569 | 11.1523 | 22.4569 | 38.9238 | 57.3807 | 0.01
6.0128 | 9.0064 | 8.0128 | 7.0128 | 10.0192 | 12.0192 | 9.0064 | 16.0192 | 26.0383 | 38.0575 | 6.0128 | 9.0064 | 8.0128 | 7.0128 | 10.0292 | 12.0192 | 9.0064 | 16.0192 | 26.0483 | 38.0675 | 0.01
5.3452 | 8.6726 | 7.3452 | 6.3452 | 9.0178 | 11.0178 | 8.6726 | 15.0178 | 24.0356 | 35.0535 | 5.3452 | 8.6726 | 7.3452 | 6.3452 | 9.0278 | 11.0178 | 8.6726 | 15.0178 | 24.0456 | 35.0635 | 0.01
5.0104 | 8.5052 | 7.0104 | 6.0104 | 8.5156 | 10.5156 | 8.5052 | 14.5156 | 23.0312 | 33.5469 | 5.0104 | 8.5052 | 7.0104 | 6.0104 | 8.5256 | 10.5156 | 8.5052 | 14.5156 | 23.0412 | 33.5569 | 0.01
8.5886 | 10.2943 | 10.5886 | 9.5886 | 13.8829 | 15.8829 | 10.2943 | 19.8829 | 33.7658 | 49.6487 | 8.5886 | 10.2943 | 10.5886 | 9.5886 | 13.8929 | 15.8829 | 10.2943 | 19.8829 | 33.7758 | 49.6587 | 0.01
4.7374 | 8.3687 | 6.7374 | 5.7374 | 8.1061 | 10.1061 | 8.3687 | 14.1061 | 22.2122 | 32.3184 | 4.7374 | 8.3687 | 6.7374 | 5.7374 | 8.1161 | 10.1061 | 8.3687 | 14.1061 | 22.2222 | 32.3284 | 0.01
4.205 | 8.1025 | 6.205 | 5.205 | 7.3075 | 9.3075 | 8.1025 | 13.3075 | 20.6151 | 29.9226 | 4.205 | 8.1025 | 6.205 | 5.205 | 7.3175 | 9.3075 | 8.1025 | 13.3075 | 20.6251 | 29.9326 | 0.01
6.7811 | 9.3906 | 8.7811 | 7.7811 | 11.1717 | 13.1717 | 9.3906 | 17.1717 | 28.3433 | 41.515 | 6.7811 | 9.3906 | 8.7811 | 7.7811 | 11.1817 | 13.1717 | 9.3906 | 17.1717 | 28.3533 | 41.525 | 0.01
5.058 | 8.529 | 7.058 | 6.058 | 8.5871 | 10.5871 | 8.529 | 14.5871 | 23.1741 | 33.7612 | 5.058 | 8.529 | 7.058 | 6.058 | 8.5971 | 10.5871 | 8.529 | 14.5871 | 23.1841 | 33.7712 | 0.01
5.1781 | 8.5891 | 7.1781 | 6.1781 | 8.7672 | 10.7672 | 8.5891 | 14.7672 | 23.5343 | 34.3015 | 5.1781 | 8.5891 | 7.1781 | 6.1781 | 8.7772 | 10.7672 | 8.5891 | 14.7672 | 23.5443 | 34.3115 | 0.01
2.0437 | 7.0219 | 4.0437 | 3.0437 | 4.0656 | 6.0656 | 7.0219 | 10.0656 | 14.1312 | 20.1968 | 2.0437 | 7.0219 | 4.0437 | 3.0437 | 4.0756 | 6.0656 | 7.0219 | 10.0656 | 14.1412 | 20.2068 | 0.01
7.546 | 9.773 | 9.546 | 8.546 | 12.319 | 14.319 | 9.773 | 18.319 | 30.6379 | 44.9569 | 7.546 | 9.773 | 9.546 | 8.546 | 12.329 | 14.319 | 9.773 | 18.319 | 30.6479 | 44.9669 | 0.01
5.6743 | 8.8371 | 7.6743 | 6.6743 | 9.5114 | 11.5114 | 8.8371 | 15.5114 | 25.0229 | 36.5343 | 5.6743 | 8.8371 | 7.6743 | 6.6743 | 9.5214 | 11.5114 | 8.8371 | 15.5114 | 25.0329 | 36.5443 | 0.01
4.0812 | 8.0406 | 6.0812 | 5.0812 | 7.1218 | 9.1218 | 8.0406 | 13.1218 | 20.2435 | 29.3653 | 4.0812 | 8.0406 | 6.0812 | 5.0812 | 7.1318 | 9.1218 | 8.0406 | 13.1218 | 20.2535 | 29.3753 | 0.01
9.5518 | 10.7759 | 11.5518 | 10.5518 | 15.3277 | 17.3277 | 10.7759 | 21.3277 | 36.6555 | 53.9832 | 9.5518 | 10.7759 | 11.5518 | 10.5518 | 15.3377 | 17.3277 | 10.7759 | 21.3277 | 36.6655 | 53.9932 | 0.01
7.9334 | 9.9667 | 9.9334 | 8.9334 | 12.9001 | 14.9001 | 9.9667 | 18.9001 | 31.8003 | 46.7004 | 7.9334 | 9.9667 | 9.9334 | 8.9334 | 12.9101 | 14.9001 | 9.9667 | 18.9001 | 31.8103 | 46.7104 | 0.01
4.7753 | 8.3876 | 6.7753 | 5.7753 | 8.1629 | 10.1629 | 8.3876 | 14.1629 | 22.3258 | 32.4888 | 4.7753 | 8.3876 | 6.7753 | 5.7753 | 8.1729 | 10.1629 | 8.3876 | 14.1629 | 22.3358 | 32.4988 | 0.01
8.5211 | 10.2606 | 10.5211 | 9.5211 | 13.7817 | 15.7817 | 10.2606 | 19.7817 | 33.5634 | 49.3451 | 8.5211 | 10.2606 | 10.5211 | 9.5211 | 13.7917 | 15.7817 | 10.2606 | 19.7817 | 33.5734 | 49.3551 | 0.01
5.7198 | 8.8599 | 7.7198 | 6.7198 | 9.5797 | 11.5797 | 8.8599 | 15.5797 | 25.1594 | 36.7391 | 5.7198 | 8.8599 | 7.7198 | 6.7198 | 9.5897 | 11.5797 | 8.8599 | 15.5797 | 25.1694 | 36.7491 | 0.01
4.9962 | 8.4981 | 6.9962 | 5.9962 | 8.4943 | 10.4943 | 8.4981 | 14.4943 | 22.9886 | 33.4829 | 4.9962 | 8.4981 | 6.9962 | 5.9962 | 8.5043 | 10.4943 | 8.4981 | 14.4943 | 22.9986 | 33.4929 | 0.01
5.1437 | 8.5718 | 7.1437 | 6.1437 | 8.7155 | 10.7155 | 8.5718 | 14.7155 | 23.4311 | 34.1466 | 5.1437 | 8.5718 | 7.1437 | 6.1437 | 8.7255 | 10.7155 | 8.5718 | 14.7155 | 23.4411 | 34.1566 | 0.01
5.9165 | 8.9583 | 7.9165 | 6.9165 | 9.8748 | 11.8748 | 8.9583 | 15.8748 | 25.7496 | 37.6243 | 5.9165 | 8.9583 | 7.9165 | 6.9165 | 9.8848 | 11.8748 | 8.9583 | 15.8748 | 25.7596 | 37.6343 | 0.01
6.5709 | 9.2855 | 8.5709 | 7.5709 | 10.8564 | 12.8564 | 9.2855 | 16.8564 | 27.7128 | 40.5691 | 6.5709 | 9.2855 | 8.5709 | 7.5709 | 10.8664 | 12.8564 | 9.2855 | 16.8564 | 27.7228 | 40.5791 | 0.01
4.407 | 8.2035 | 6.407 | 5.407 | 7.6105 | 9.6105 | 8.2035 | 13.6105 | 21.2209 | 30.8314 | 4.407 | 8.2035 | 6.407 | 5.407 | 7.6205 | 9.6105 | 8.2035 | 13.6105 | 21.2309 | 30.8414 | 0.01
7.6827 | 9.8413 | 9.6827 | 8.6827 | 12.524 | 14.524 | 9.8413 | 18.524 | 31.048 | 45.572 | 7.6827 | 9.8413 | 9.6827 | 8.6827 | 12.534 | 14.524 | 9.8413 | 18.524 | 31.058 | 45.582 | 0.01
5.0637 | 8.5318 | 7.0637 | 6.0637 | 8.5955 | 10.5955 | 8.5318 | 14.5955 | 23.191 | 33.7865 | 5.0637 | 8.5318 | 7.0637 | 6.0637 | 8.6055 | 10.5955 | 8.5318 | 14.5955 | 23.201 | 33.7965 | 0.01
3.1421 | 7.5711 | 5.1421 | 4.1421 | 5.7132 | 7.7132 | 7.5711 | 11.7132 | 17.4263 | 25.1395 | 3.1421 | 7.5711 | 5.1421 | 4.1421 | 5.7232 | 7.7132 | 7.5711 | 11.7132 | 17.4363 | 25.1495 | 0.01
8.3315 | 10.1657 | 10.3315 | 9.3315 | 13.4972 | 15.4972 | 10.1657 | 19.4972 | 32.9944 | 48.4916 | 8.3315 | 10.1657 | 10.3315 | 9.3315 | 13.5072 | 15.4972 | 10.1657 | 19.4972 | 33.0044 | 48.5016 | 0.01
7.0219 | 9.5109 | 9.0219 | 8.0219 | 11.5328 | 13.5328 | 9.5109 | 17.5328 | 29.0656 | 42.5985 | 7.0219 | 9.5109 | 9.0219 | 8.0219 | 11.5428 | 13.5328 | 9.5109 | 17.5328 | 29.0756 | 42.6085 | 0.01
7.4577 | 9.7289 | 9.4577 | 8.4577 | 12.1866 | 14.1866 | 9.7289 | 18.1866 | 30.3732 | 44.5599 | 7.4577 | 9.7289 | 9.4577 | 8.4577 | 12.1966 | 14.1866 | 9.7289 | 18.1866 | 30.3832 | 44.5699 | 0.01
8.7512 | 10.3756 | 10.7512 | 9.7512 | 14.1268 | 16.1268 | 10.3756 | 20.1268 | 34.2535 | 50.3803 | 8.7512 | 10.3756 | 10.7512 | 9.7512 | 14.1368 | 16.1268 | 10.3756 | 20.1268 | 34.2635 | 50.3903 | 0.01
3.186 | 7.593 | 5.186 | 4.186 | 5.779 | 7.779 | 7.593 | 11.779 | 17.558 | 25.337 | 3.186 | 7.593 | 5.186 | 4.186 | 5.789 | 7.779 | 7.593 | 11.779 | 17.568 | 25.347 | 0.01
3.9737 | 7.9868 | 5.9737 | 4.9737 | 6.9605 | 8.9605 | 7.9868 | 12.9605 | 19.921 | 28.8815 | 3.9737 | 7.9868 | 5.9737 | 4.9737 | 6.9705 | 8.9605 | 7.9868 | 12.9605 | 19.931 | 28.8915 | 0.01
6.1466 | 9.0733 | 8.1466 | 7.1466 | 10.2199 | 12.2199 | 9.0733 | 16.2199 | 26.4399 | 38.6598 | 6.1466 | 9.0733 | 8.1466 | 7.1466 | 10.2299 | 12.2199 | 9.0733 | 16.2199 | 26.4499 | 38.6698 | 0.01
4.2176 | 8.1088 | 6.2176 | 5.2176 | 7.3264 | 9.3264 | 8.1088 | 13.3264 | 20.6527 | 29.9791 | 4.2176 | 8.1088 | 6.2176 | 5.2176 | 7.3364 | 9.3264 | 8.1088 | 13.3264 | 20.6627 | 29.9891 | 0.01
6.6912 | 9.3456 | 8.6912 | 7.6912 | 11.0368 | 13.0368 | 9.3456 | 17.0368 | 28.0737 | 41.1105 | 6.6912 | 9.3456 | 8.6912 | 7.6912 | 11.0468 | 13.0368 | 9.3456 | 17.0368 | 28.0837 | 41.1205 | 0.01
4.7236 | 8.3618 | 6.7236 | 5.7236 | 8.0853 | 10.0853 | 8.3618 | 14.0853 | 22.1707 | 32.256 | 4.7236 | 8.3618 | 6.7236 | 5.7236 | 8.0953 | 10.0853 | 8.3618 | 14.0853 | 22.1807 | 32.266 | 0.01
4.7267 | 8.3634 | 6.7267 | 5.7267 | 8.0901 | 10.0901 | 8.3634 | 14.0901 | 22.1802 | 32.2704 | 4.7267 | 8.3634 | 6.7267 | 5.7267 | 8.1001 | 10.0901 | 8.3634 | 14.0901 | 22.1902 | 32.2804 | 0.01
7.199 | 9.5995 | 9.199 | 8.199 | 11.7985 | 13.7985 | 9.5995 | 17.7985 | 29.5969 | 43.3954 | 7.199 | 9.5995 | 9.199 | 8.199 | 11.8085 | 13.7985 | 9.5995 | 17.7985 | 29.6069 | 43.4054 | 0.01
3.7067 | 7.8534 | 5.7067 | 4.7067 | 6.5601 | 8.5601 | 7.8534 | 12.5601 | 19.1202 | 27.6803 | 3.7067 | 7.8534 | 5.7067 | 4.7067 | 6.5701 | 8.5601 | 7.8534 | 12.5601 | 19.1302 | 27.6903 | 0.01
5.995 | 8.9975 | 7.995 | 6.995 | 9.9925 | 11.9925 | 8.9975 | 15.9925 | 25.9851 | 37.9776 | 5.995 | 8.9975 | 7.995 | 6.995 | 10.0025 | 11.9925 | 8.9975 | 15.9925 | 25.9951 | 37.9876 | 0.01
5.0831 | 8.5415 | 7.0831 | 6.0831 | 8.6246 | 10.6246 | 8.5415 | 14.6246 | 23.2493 | 33.8739 | 5.0831 | 8.5415 | 7.0831 | 6.0831 | 8.6346 | 10.6246 | 8.5415 | 14.6246 | 23.2593 | 33.8839 | 0.01
6.1092 | 9.0546 | 8.1092 | 7.1092 | 10.1638 | 12.1638 | 9.0546 | 16.1638 | 26.3277 | 38.4915 | 6.1092 | 9.0546 | 8.1092 | 7.1092 | 10.1738 | 12.1638 | 9.0546 | 16.1638 | 26.3377 | 38.5015 | 0.01
8.5861 | 10.2931 | 10.5861 | 9.5861 | 13.8792 | 15.8792 | 10.2931 | 19.8792 | 33.7584 | 49.6375 | 8.5861 | 10.2931 | 10.5861 | 9.5861 | 13.8892 | 15.8792 | 10.2931 | 19.8792 | 33.7684 | 49.6475 | 0.01
5.3112 | 8.6556 | 7.3112 | 6.3112 | 8.9668 | 10.9668 | 8.6556 | 14.9668 | 23.9337 | 34.9005 | 5.3112 | 8.6556 | 7.3112 | 6.3112 | 8.9768 | 10.9668 | 8.6556 | 14.9668 | 23.9437 | 34.9105 | 0.01
3.0662 | 7.5331 | 5.0662 | 4.0662 | 5.5993 | 7.5993 | 7.5331 | 11.5993 | 17.1985 | 24.7978 | 3.0662 | 7.5331 | 5.0662 | 4.0662 | 5.6093 | 7.5993 | 7.5331 | 11.5993 | 17.2085 | 24.8078 | 0.01
5.713 | 8.8565 | 7.713 | 6.713 | 9.5695 | 11.5695 | 8.8565 | 15.5695 | 25.139 | 36.7085 | 5.713 | 8.8565 | 7.713 | 6.713 | 9.5795 | 11.5695 | 8.8565 | 15.5695 | 25.149 | 36.7185 | 0.01
2.1945 | 7.0972 | 4.1945 | 3.1945 | 4.2917 | 6.2917 | 7.0972 | 10.2917 | 14.5834 | 20.8751 | 2.1945 | 7.0972 | 4.1945 | 3.1945 | 4.3017 | 6.2917 | 7.0972 | 10.2917 | 14.5934 | 20.8851 | 0.01
4.0199 | 8.01 | 6.0199 | 5.0199 | 7.0299 | 9.0299 | 8.01 | 13.0299 | 20.0597 | 29.0896 | 4.0199 | 8.01 | 6.0199 | 5.0199 | 7.0399 | 9.0299 | 8.01 | 13.0299 | 20.0697 | 29.0996 | 0.01
6.6125 | 9.3062 | 8.6125 | 7.6125 | 10.9187 | 12.9187 | 9.3062 | 16.9187 | 27.8374 | 40.7562 | 6.6125 | 9.3062 | 8.6125 | 7.6125 | 10.9287 | 12.9187 | 9.3062 | 16.9187 | 27.8474 | 40.7662 | 0.01
6.4942 | 9.2471 | 8.4942 | 7.4942 | 10.7413 | 12.7413 | 9.2471 | 16.7413 | 27.4826 | 40.2239 | 6.4942 | 9.2471 | 8.4942 | 7.4942 | 10.7513 | 12.7413 | 9.2471 | 16.7413 | 27.4926 | 40.2339 | 0.01
5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6481 | 10.6381 | 8.546 | 14.6381 | 23.2863 | 33.9244 | 0.01
5.964 | 8.982 | 7.964 | 6.964 | 9.946 | 11.946 | 8.982 | 15.946 | 25.8919 | 37.8379 | 5.964 | 8.982 | 7.964 | 6.964 | 9.956 | 11.946 | 8.982 | 15.946 | 25.9019 | 37.8479 | 0.01
5.7816 | 8.8908 | 7.7816 | 6.7816 | 9.6724 | 11.6724 | 8.8908 | 15.6724 | 25.3449 | 37.0173 | 5.7816 | 8.8908 | 7.7816 | 6.7816 | 9.6824 | 11.6724 | 8.8908 | 15.6724 | 25.3549 | 37.0273 | 0.01
3.5707 | 7.7853 | 5.5707 | 4.5707 | 6.356 | 8.356 | 7.7853 | 12.356 | 18.712 | 27.068 | 3.5707 | 7.7853 | 5.5707 | 4.5707 | 6.366 | 8.356 | 7.7853 | 12.356 | 18.722 | 27.078 | 0.01
3.9955 | 7.9978 | 5.9955 | 4.9955 | 6.9933 | 8.9933 | 7.9978 | 12.9933 | 19.9866 | 28.9799 | 3.9955 | 7.9978 | 5.9955 | 4.9955 | 7.0033 | 8.9933 | 7.9978 | 12.9933 | 19.9966 | 28.9899 | 0.01
6.0997 | 9.0499 | 8.0997 | 7.0997 | 10.1496 | 12.1496 | 9.0499 | 16.1496 | 26.2992 | 38.4487 | 6.0997 | 9.0499 | 8.0997 | 7.0997 | 10.1596 | 12.1496 | 9.0499 | 16.1496 | 26.3092 | 38.4587 | 0.01
7.8375 | 9.9188 | 9.8375 | 8.8375 | 12.7563 | 14.7563 | 9.9188 | 18.7563 | 31.5125 | 46.2688 | 7.8375 | 9.9188 | 9.8375 | 8.8375 | 12.7663 | 14.7563 | 9.9188 | 18.7563 | 31.5225 | 46.2788 | 0.01
6.5393 | 9.2696 | 8.5393 | 7.5393 | 10.8089 | 12.8089 | 9.2696 | 16.8089 | 27.6178 | 40.4267 | 6.5393 | 9.2696 | 8.5393 | 7.5393 | 10.8189 | 12.8089 | 9.2696 | 16.8089 | 27.6278 | 40.4367 | 0.01
3.8684 | 7.9342 | 5.8684 | 4.8684 | 6.8026 | 8.8026 | 7.9342 | 12.8026 | 19.6051 | 28.4077 | 3.8684 | 7.9342 | 5.8684 | 4.8684 | 6.8126 | 8.8026 | 7.9342 | 12.8026 | 19.6151 | 28.4177 | 0.01
5.8862 | 8.9431 | 7.8862 | 6.8862 | 9.8293 | 11.8293 | 8.9431 | 15.8293 | 25.6586 | 37.4878 | 5.8862 | 8.9431 | 7.8862 | 6.8862 | 9.8393 | 11.8293 | 8.9431 | 15.8293 | 25.6686 | 37.4978 | 0.01
4.754 | 8.377 | 6.754 | 5.754 | 8.131 | 10.131 | 8.377 | 14.131 | 22.262 | 32.3929 | 4.754 | 8.377 | 6.754 | 5.754 | 8.141 | 10.131 | 8.377 | 14.131 | 22.272 | 32.4029 | 0.01
3.8834 | 7.9417 | 5.8834 | 4.8834 | 6.8251 | 8.8251 | 7.9417 | 12.8251 | 19.6503 | 28.4754 | 3.8834 | 7.9417 | 5.8834 | 4.8834 | 6.8351 | 8.8251 | 7.9417 | 12.8251 | 19.6603 | 28.4854 | 0.01
5.5401 | 8.7701 | 7.5401 | 6.5401 | 9.3102 | 11.3102 | 8.7701 | 15.3102 | 24.6204 | 35.9306 | 5.5401 | 8.7701 | 7.5401 | 6.5401 | 9.3202 | 11.3102 | 8.7701 | 15.3102 | 24.6304 | 35.9406 | 0.01
6.0247 | 9.0124 | 8.0247 | 7.0247 | 10.0371 | 12.0371 | 9.0124 | 16.0371 | 26.0741 | 38.1112 | 6.0247 | 9.0124 | 8.0247 | 7.0247 | 10.0471 | 12.0371 | 9.0124 | 16.0371 | 26.0841 | 38.1212 | 0.01
4.9316 | 8.4658 | 6.9316 | 5.9316 | 8.3975 | 10.3975 | 8.4658 | 14.3975 | 22.7949 | 33.1924 | 4.9316 | 8.4658 | 6.9316 | 5.9316 | 8.4075 | 10.3975 | 8.4658 | 14.3975 | 22.8049 | 33.2024 | 0.01
9.3444 | 10.6722 | 11.3444 | 10.3444 | 15.0166 | 17.0166 | 10.6722 | 21.0166 | 36.0332 | 53.0498 | 9.3444 | 10.6722 | 11.3444 | 10.3444 | 15.0266 | 17.0166 | 10.6722 | 21.0166 | 36.0432 | 53.0598 | 0.01
6.4224 | 9.2112 | 8.4224 | 7.4224 | 10.6336 | 12.6336 | 9.2112 | 16.6336 | 27.2672 | 39.9008 | 6.4224 | 9.2112 | 8.4224 | 7.4224 | 10.6436 | 12.6336 | 9.2112 | 16.6336 | 27.2772 | 39.9108 | 0.01
5.0339 | 8.5169 | 7.0339 | 6.0339 | 8.5508 | 10.5508 | 8.5169 | 14.5508 | 23.1016 | 33.6524 | 5.0339 | 8.5169 | 7.0339 | 6.0339 | 8.5608 | 10.5508 | 8.5169 | 14.5508 | 23.1116 | 33.6624 | 0.01
5.9344 | 8.9672 | 7.9344 | 6.9344 | 9.9016 | 11.9016 | 8.9672 | 15.9016 | 25.8033 | 37.7049 | 5.9344 | 8.9672 | 7.9344 | 6.9344 | 9.9116 | 11.9016 | 8.9672 | 15.9016 | 25.8133 | 37.7149 | 0.01
6.8634 | 9.4317 | 8.8634 | 7.8634 | 11.295 | 13.295 | 9.4317 | 17.295 | 28.5901 | 41.8851 | 6.8634 | 9.4317 | 8.8634 | 7.8634 | 11.305 | 13.295 | 9.4317 | 17.295 | 28.6001 | 41.8951 | 0.01
3.9905 | 7.9952 | 5.9905 | 4.9905 | 6.9857 | 8.9857 | 7.9952 | 12.9857 | 19.9714 | 28.9572 | 3.9905 | 7.9952 | 5.9905 | 4.9905 | 6.9957 | 8.9857 | 7.9952 | 12.9857 | 19.9814 | 28.9672 | 0.01
7.2021 | 9.601 | 9.2021 | 8.2021 | 11.8031 | 13.8031 | 9.601 | 17.8031 | 29.6063 | 43.4094 | 7.2021 | 9.601 | 9.2021 | 8.2021 | 11.8131 | 13.8031 | 9.601 | 17.8031 | 29.6163 | 43.4194 | 0.01
0.53517 | 6.2676 | 2.5352 | 1.5352 | 1.8028 | 3.8028 | 6.2676 | 7.8028 | 9.6055 | 13.4083 | 0.53517 | 6.2676 | 2.5352 | 1.5352 | 1.8128 | 3.8028 | 6.2676 | 7.8028 | 9.6155 | 13.4183 | 0.01
5.5684 | 8.7842 | 7.5684 | 6.5684 | 9.3525 | 11.3525 | 8.7842 | 15.3525 | 24.7051 | 36.0576 | 5.5684 | 8.7842 | 7.5684 | 6.5684 | 9.3625 | 11.3525 | 8.7842 | 15.3525 | 24.7151 | 36.0676 | 0.01
5.3874 | 8.6937 | 7.3874 | 6.3874 | 9.081 | 11.081 | 8.6937 | 15.081 | 24.1621 | 35.2431 | 5.3874 | 8.6937 | 7.3874 | 6.3874 | 9.091 | 11.081 | 8.6937 | 15.081 | 24.1721 | 35.2531 | 0.01
6.5294 | 9.2647 | 8.5294 | 7.5294 | 10.7942 | 12.7942 | 9.2647 | 16.7942 | 27.5883 | 40.3825 | 6.5294 | 9.2647 | 8.5294 | 7.5294 | 10.8042 | 12.7942 | 9.2647 | 16.7942 | 27.5983 | 40.3925 | 0.01
8.7496 | 10.3748 | 10.7496 | 9.7496 | 14.1244 | 16.1244 | 10.3748 | 20.1244 | 34.2488 | 50.3732 | 8.7496 | 10.3748 | 10.7496 | 9.7496 | 14.1344 | 16.1244 | 10.3748 | 20.1244 | 34.2588 | 50.3832 | 0.01
5.9569 | 8.9785 | 7.9569 | 6.9569 | 9.9354 | 11.9354 | 8.9785 | 15.9354 | 25.8708 | 37.8062 | 5.9569 | 8.9785 | 7.9569 | 6.9569 | 9.9454 | 11.9354 | 8.9785 | 15.9354 | 25.8808 | 37.8162 | 0.01
5.1926 | 8.5963 | 7.1926 | 6.1926 | 8.7889 | 10.7889 | 8.5963 | 14.7889 | 23.5777 | 34.3666 | 5.1926 | 8.5963 | 7.1926 | 6.1926 | 8.7989 | 10.7889 | 8.5963 | 14.7889 | 23.5877 | 34.3766 | 0.01
4.5049 | 8.2524 | 6.5049 | 5.5049 | 7.7573 | 9.7573 | 8.2524 | 13.7573 | 21.5146 | 31.272 | 4.5049 | 8.2524 | 6.5049 | 5.5049 | 7.7673 | 9.7573 | 8.2524 | 13.7573 | 21.5246 | 31.282 | 0.01
4.4453 | 8.2227 | 6.4453 | 5.4453 | 7.668 | 9.668 | 8.2227 | 13.668 | 21.336 | 31.004 | 4.4453 | 8.2227 | 6.4453 | 5.4453 | 7.678 | 9.668 | 8.2227 | 13.668 | 21.346 | 31.014 | 0.01
8.9107 | 10.4553 | 10.9107 | 9.9107 | 14.366 | 16.366 | 10.4553 | 20.366 | 34.7321 | 51.0981 | 8.9107 | 10.4553 | 10.9107 | 9.9107 | 14.376 | 16.366 | 10.4553 | 20.366 | 34.7421 | 51.1081 | 0.01
5.5784 | 8.7892 | 7.5784 | 6.5784 | 9.3676 | 11.3676 | 8.7892 | 15.3676 | 24.7351 | 36.1027 | 5.5784 | 8.7892 | 7.5784 | 6.5784 | 9.3776 | 11.3676 | 8.7892 | 15.3676 | 24.7451 | 36.1127 | 0.01
6.5968 | 9.2984 | 8.5968 | 7.5968 | 10.8952 | 12.8952 | 9.2984 | 16.8952 | 27.7903 | 40.6855 | 6.5968 | 9.2984 | 8.5968 | 7.5968 | 10.9052 | 12.8952 | 9.2984 | 16.8952 | 27.8003 | 40.6955 | 0.01
9.5841 | 10.7921 | 11.5841 | 10.5841 | 15.3762 | 17.3762 | 10.7921 | 21.3762 | 36.7524 | 54.1286 | 9.5841 | 10.7921 | 11.5841 | 10.5841 | 15.3862 | 17.3762 | 10.7921 | 21.3762 | 36.7624 | 54.1386 | 0.01
7.1421 | 9.5711 | 9.1421 | 8.1421 | 11.7132 | 13.7132 | 9.5711 | 17.7132 | 29.4264 | 43.1397 | 7.1421 | 9.5711 | 9.1421 | 8.1421 | 11.7232 | 13.7132 | 9.5711 | 17.7132 | 29.4364 | 43.1497 | 0.01
6.9164 | 9.4582 | 8.9164 | 7.9164 | 11.3746 | 13.3746 | 9.4582 | 17.3746 | 28.7492 | 42.1238 | 6.9164 | 9.4582 | 8.9164 | 7.9164 | 11.3846 | 13.3746 | 9.4582 | 17.3746 | 28.7592 | 42.1338 | 0.01
8.2153 | 10.1076 | 10.2153 | 9.2153 | 13.3229 | 15.3229 | 10.1076 | 19.3229 | 32.6459 | 47.9688 | 8.2153 | 10.1076 | 10.2153 | 9.2153 | 13.3329 | 15.3229 | 10.1076 | 19.3229 | 32.6559 | 47.9788 | 0.01
5.5263 | 8.7631 | 7.5263 | 6.5263 | 9.2894 | 11.2894 | 8.7631 | 15.2894 | 24.5789 | 35.8683 | 5.5263 | 8.7631 | 7.5263 | 6.5263 | 9.2994 | 11.2894 | 8.7631 | 15.2894 | 24.5889 | 35.8783 | 0.01
11.0337 | 11.5168 | 13.0337 | 12.0337 | 17.5505 | 19.5505 | 11.5168 | 23.5505 | 41.101 | 60.6514 | 11.0337 | 11.5168 | 13.0337 | 12.0337 | 17.5605 | 19.5505 | 11.5168 | 23.5505 | 41.111 | 60.6614 | 0.01
6.0016 | 9.0008 | 8.0016 | 7.0016 | 10.0024 | 12.0024 | 9.0008 | 16.0024 | 26.0048 | 38.0072 | 6.0016 | 9.0008 | 8.0016 | 7.0016 | 10.0124 | 12.0024 | 9.0008 | 16.0024 | 26.0148 | 38.0172 | 0.01
10.3738 | 11.1869 | 12.3738 | 11.3738 | 16.5607 | 18.5607 | 11.1869 | 22.5607 | 39.1215 | 57.6822 | 10.3738 | 11.1869 | 12.3738 | 11.3738 | 16.5707 | 18.5607 | 11.1869 | 22.5607 | 39.1315 | 57.6922 | 0.01
6.4121 | 9.206 | 8.4121 | 7.4121 | 10.6181 | 12.6181 | 9.206 | 16.6181 | 27.2363 | 39.8544 | 6.4121 | 9.206 | 8.4121 | 7.4121 | 10.6281 | 12.6181 | 9.206 | 16.6181 | 27.2463 | 39.8644 | 0.01
9.217 | 10.6085 | 11.217 | 10.217 | 14.8254 | 16.8254 | 10.6085 | 20.8254 | 35.6509 | 52.4763 | 9.217 | 10.6085 | 11.217 | 10.217 | 14.8354 | 16.8254 | 10.6085 | 20.8254 | 35.6609 | 52.4863 | 0.01
9.7797 | 10.8898 | 11.7797 | 10.7797 | 15.6695 | 17.6695 | 10.8898 | 21.6695 | 37.3391 | 55.0086 | 9.7797 | 10.8898 | 11.7797 | 10.7797 | 15.6795 | 17.6695 | 10.8898 | 21.6695 | 37.3491 | 55.0186 | 0.01
5.0423 | 8.5211 | 7.0423 | 6.0423 | 8.5634 | 10.5634 | 8.5211 | 14.5634 | 23.1268 | 33.6903 | 5.0423 | 8.5211 | 7.0423 | 6.0423 | 8.5734 | 10.5634 | 8.5211 | 14.5634 | 23.1368 | 33.7003 | 0.01
4.3481 | 8.174 | 6.3481 | 5.3481 | 7.5221 | 9.5221 | 8.174 | 13.5221 | 21.0442 | 30.5663 | 4.3481 | 8.174 | 6.3481 | 5.3481 | 7.5321 | 9.5221 | 8.174 | 13.5221 | 21.0542 | 30.5763 | 0.01
7.1758 | 9.5879 | 9.1758 | 8.1758 | 11.7637 | 13.7637 | 9.5879 | 17.7637 | 29.5274 | 43.2911 | 7.1758 | 9.5879 | 9.1758 | 8.1758 | 11.7737 | 13.7637 | 9.5879 | 17.7637 | 29.5374 | 43.3011 | 0.01
4.6681 | 8.3341 | 6.6681 | 5.6681 | 8.0022 | 10.0022 | 8.3341 | 14.0022 | 22.0043 | 32.0065 | 4.6681 | 8.3341 | 6.6681 | 5.6681 | 8.0122 | 10.0022 | 8.3341 | 14.0022 | 22.0143 | 32.0165 | 0.01
1.8921 | 6.946 | 3.8921 | 2.8921 | 3.8381 | 5.8381 | 6.946 | 9.8381 | 13.6762 | 19.5143 | 1.8921 | 6.946 | 3.8921 | 2.8921 | 3.8481 | 5.8381 | 6.946 | 9.8381 | 13.6862 | 19.5243 | 0.01
5.0109 | 8.5055 | 7.0109 | 6.0109 | 8.5164 | 10.5164 | 8.5055 | 14.5164 | 23.0328 | 33.5492 | 5.0109 | 8.5055 | 7.0109 | 6.0109 | 8.5264 | 10.5164 | 8.5055 | 14.5164 | 23.0428 | 33.5592 | 0.01
3.8584 | 7.9292 | 5.8584 | 4.8584 | 6.7875 | 8.7875 | 7.9292 | 12.7875 | 19.5751 | 28.3626 | 3.8584 | 7.9292 | 5.8584 | 4.8584 | 6.7975 | 8.7875 | 7.9292 | 12.7875 | 19.5851 | 28.3726 | 0.01
6.4966 | 9.2483 | 8.4966 | 7.4966 | 10.7448 | 12.7448 | 9.2483 | 16.7448 | 27.4897 | 40.2345 | 6.4966 | 9.2483 | 8.4966 | 7.4966 | 10.7548 | 12.7448 | 9.2483 | 16.7448 | 27.4997 | 40.2445 | 0.01
7.0352 | 9.5176 | 9.0352 | 8.0352 | 11.5527 | 13.5527 | 9.5176 | 17.5527 | 29.1055 | 42.6582 | 7.0352 | 9.5176 | 9.0352 | 8.0352 | 11.5627 | 13.5527 | 9.5176 | 17.5527 | 29.1155 | 42.6682 | 0.01
6.1885 | 9.0943 | 8.1885 | 7.1885 | 10.2828 | 12.2828 | 9.0943 | 16.2828 | 26.5656 | 38.8484 | 6.1885 | 9.0943 | 8.1885 | 7.1885 | 10.2928 | 12.2828 | 9.0943 | 16.2828 | 26.5756 | 38.8584 | 0.01
5.8998 | 8.9499 | 7.8998 | 6.8998 | 9.8497 | 11.8497 | 8.9499 | 15.8497 | 25.6995 | 37.5492 | 5.8998 | 8.9499 | 7.8998 | 6.8998 | 9.8597 | 11.8497 | 8.9499 | 15.8497 | 25.7095 | 37.5592 | 0.01
3.7522 | 7.8761 | 5.7522 | 4.7522 | 6.6283 | 8.6283 | 7.8761 | 12.6283 | 19.2566 | 27.8849 | 3.7522 | 7.8761 | 5.7522 | 4.7522 | 6.6383 | 8.6283 | 7.8761 | 12.6283 | 19.2666 | 27.8949 | 0.01
6.776 | 9.388 | 8.776 | 7.776 | 11.164 | 13.164 | 9.388 | 17.164 | 28.328 | 41.492 | 6.776 | 9.388 | 8.776 | 7.776 | 11.174 | 13.164 | 9.388 | 17.164 | 28.338 | 41.502 | 0.01
5.7807 | 8.8903 | 7.7807 | 6.7807 | 9.671 | 11.671 | 8.8903 | 15.671 | 25.3421 | 37.0131 | 5.7807 | 8.8903 | 7.7807 | 6.7807 | 9.681 | 11.671 | 8.8903 | 15.671 | 25.3521 | 37.0231 | 0.01
3.3449 | 7.6725 | 5.3449 | 4.3449 | 6.0174 | 8.0174 | 7.6725 | 12.0174 | 18.0348 | 26.0522 | 3.3449 | 7.6725 | 5.3449 | 4.3449 | 6.0274 | 8.0174 | 7.6725 | 12.0174 | 18.0448 | 26.0622 | 0.01
3.0968 | 7.5484 | 5.0968 | 4.0968 | 5.6452 | 7.6452 | 7.5484 | 11.6452 | 17.2904 | 24.9355 | 3.0968 | 7.5484 | 5.0968 | 4.0968 | 5.6552 | 7.6452 | 7.5484 | 11.6452 | 17.3004 | 24.9455 | 0.01
7.9137 | 9.9569 | 9.9137 | 8.9137 | 12.8706 | 14.8706 | 9.9569 | 18.8706 | 31.7412 | 46.6118 | 7.9137 | 9.9569 | 9.9137 | 8.9137 | 12.8806 | 14.8706 | 9.9569 | 18.8706 | 31.7512 | 46.6218 | 0.01
8.1265 | 10.0633 | 10.1265 | 9.1265 | 13.1898 | 15.1898 | 10.0633 | 19.1898 | 32.3795 | 47.5693 | 8.1265 | 10.0633 | 10.1265 | 9.1265 | 13.1998 | 15.1898 | 10.0633 | 19.1898 | 32.3895 | 47.5793 | 0.01
4.2244 | 8.1122 | 6.2244 | 5.2244 | 7.3366 | 9.3366 | 8.1122 | 13.3366 | 20.6732 | 30.0098 | 4.2244 | 8.1122 | 6.2244 | 5.2244 | 7.3466 | 9.3366 | 8.1122 | 13.3366 | 20.6832 | 30.0198 | 0.01
6.3537 | 9.1768 | 8.3537 | 7.3537 | 10.5305 | 12.5305 | 9.1768 | 16.5305 | 27.061 | 39.5914 | 6.3537 | 9.1768 | 8.3537 | 7.3537 | 10.5405 | 12.5305 | 9.1768 | 16.5305 | 27.071 | 39.6014 | 0.01
11.168 | 11.584 | 13.168 | 12.168 | 17.7521 | 19.7521 | 11.584 | 23.7521 | 41.5041 | 61.2562 | 11.168 | 11.584 | 13.168 | 12.168 | 17.7621 | 19.7521 | 11.584 | 23.7521 | 41.5141 | 61.2662 | 0.01
5.4518 | 8.7259 | 7.4518 | 6.4518 | 9.1778 | 11.1778 | 8.7259 | 15.1778 | 24.3555 | 35.5333 | 5.4518 | 8.7259 | 7.4518 | 6.4518 | 9.1878 | 11.1778 | 8.7259 | 15.1778 | 24.3655 | 35.5433 | 0.01
6.0492 | 9.0246 | 8.0492 | 7.0492 | 10.0738 | 12.0738 | 9.0246 | 16.0738 | 26.1476 | 38.2214 | 6.0492 | 9.0246 | 8.0492 | 7.0492 | 10.0838 | 12.0738 | 9.0246 | 16.0738 | 26.1576 | 38.2314 | 0.01
7.4105 | 9.7052 | 9.4105 | 8.4105 | 12.1157 | 14.1157 | 9.7052 | 18.1157 | 30.2314 | 44.3471 | 7.4105 | 9.7052 | 9.4105 | 8.4105 | 12.1257 | 14.1157 | 9.7052 | 18.1157 | 30.2414 | 44.3571 | 0.01
3.5875 | 7.7938 | 5.5875 | 4.5875 | 6.3813 | 8.3813 | 7.7938 | 12.3813 | 18.7626 | 27.1439 | 3.5875 | 7.7938 | 5.5875 | 4.5875 | 6.3913 | 8.3813 | 7.7938 | 12.3813 | 18.7726 | 27.1539 | 0.01
5.9969 | 8.9984 | 7.9969 | 6.9969 | 9.9953 | 11.9953 | 8.9984 | 15.9953 | 25.9906 | 37.9859 | 5.9969 | 8.9984 | 7.9969 | 6.9969 | 10.0053 | 11.9953 | 8.9984 | 15.9953 | 26.0006 | 37.9959 | 0.01
4.4596 | 8.2298 | 6.4596 | 5.4596 | 7.6894 | 9.6894 | 8.2298 | 13.6894 | 21.3787 | 31.0681 | 4.4596 | 8.2298 | 6.4596 | 5.4596 | 7.6994 | 9.6894 | 8.2298 | 13.6894 | 21.3887 | 31.0781 | 0.01
4.6953 | 8.3477 | 6.6953 | 5.6953 | 8.043 | 10.043 | 8.3477 | 14.043 | 22.0859 | 32.1289 | 4.6953 | 8.3477 | 6.6953 | 5.6953 | 8.053 | 10.043 | 8.3477 | 14.043 | 22.0959 | 32.1389 | 0.01
6.2341 | 9.117 | 8.2341 | 7.2341 | 10.3511 | 12.3511 | 9.117 | 16.3511 | 26.7023 | 39.0534 | 6.2341 | 9.117 | 8.2341 | 7.2341 | 10.3611 | 12.3511 | 9.117 | 16.3511 | 26.7123 | 39.0634 | 0.01
10.223 | 11.1115 | 12.223 | 11.223 | 16.3345 | 18.3345 | 11.1115 | 22.3345 | 38.669 | 57.0034 | 10.223 | 11.1115 | 12.223 | 11.223 | 16.3445 | 18.3345 | 11.1115 | 22.3345 | 38.679 | 57.0134 | 0.01
7.3917 | 9.6958 | 9.3917 | 8.3917 | 12.0875 | 14.0875 | 9.6958 | 18.0875 | 30.1751 | 44.2626 | 7.3917 | 9.6958 | 9.3917 | 8.3917 | 12.0975 | 14.0875 | 9.6958 | 18.0875 | 30.1851 | 44.2726 | 0.01
7.055 | 9.5275 | 9.055 | 8.055 | 11.5825 | 13.5825 | 9.5275 | 17.5825 | 29.1649 | 42.7474 | 7.055 | 9.5275 | 9.055 | 8.055 | 11.5925 | 13.5825 | 9.5275 | 17.5825 | 29.1749 | 42.7574 | 0.01
2.1916 | 7.0958 | 4.1916 | 3.1916 | 4.2875 | 6.2875 | 7.0958 | 10.2875 | 14.5749 | 20.8624 | 2.1916 | 7.0958 | 4.1916 | 3.1916 | 4.2975 | 6.2875 | 7.0958 | 10.2875 | 14.5849 | 20.8724 | 0.01
4.1961 | 8.098 | 6.1961 | 5.1961 | 7.2941 | 9.2941 | 8.098 | 13.2941 | 20.5882 | 29.8823 | 4.1961 | 8.098 | 6.1961 | 5.1961 | 7.3041 | 9.2941 | 8.098 | 13.2941 | 20.5982 | 29.8923 | 0.01
9.3012 | 10.6506 | 11.3012 | 10.3012 | 14.9518 | 16.9518 | 10.6506 | 20.9518 | 35.9036 | 52.8554 | 9.3012 | 10.6506 | 11.3012 | 10.3012 | 14.9618 | 16.9518 | 10.6506 | 20.9518 | 35.9136 | 52.8654 | 0.01
6.1032 | 9.0516 | 8.1032 | 7.1032 | 10.1549 | 12.1549 | 9.0516 | 16.1549 | 26.3097 | 38.4646 | 6.1032 | 9.0516 | 8.1032 | 7.1032 | 10.1649 | 12.1549 | 9.0516 | 16.1549 | 26.3197 | 38.4746 | 0.01
10.9776 | 11.4888 | 12.9776 | 11.9776 | 17.4663 | 19.4663 | 11.4888 | 23.4663 | 40.9327 | 60.399 | 10.9776 | 11.4888 | 12.9776 | 11.9776 | 17.4763 | 19.4663 | 11.4888 | 23.4663 | 40.9427 | 60.409 | 0.01
3.8066 | 7.9033 | 5.8066 | 4.8066 | 6.7099 | 8.7099 | 7.9033 | 12.7099 | 19.4198 | 28.1297 | 3.8066 | 7.9033 | 5.8066 | 4.8066 | 6.7199 | 8.7099 | 7.9033 | 12.7099 | 19.4298 | 28.1397 | 0.01
4.2458 | 8.1229 | 6.2458 | 5.2458 | 7.3688 | 9.3688 | 8.1229 | 13.3688 | 20.7375 | 30.1063 | 4.2458 | 8.1229 | 6.2458 | 5.2458 | 7.3788 | 9.3688 | 8.1229 | 13.3688 | 20.7475 | 30.1163 | 0.01
6.4005 | 9.2003 | 8.4005 | 7.4005 | 10.6008 | 12.6008 | 9.2003 | 16.6008 | 27.2016 | 39.8024 | 6.4005 | 9.2003 | 8.4005 | 7.4005 | 10.6108 | 12.6008 | 9.2003 | 16.6008 | 27.2116 | 39.8124 | 0.01
4.7583 | 8.3791 | 6.7583 | 5.7583 | 8.1374 | 10.1374 | 8.3791 | 14.1374 | 22.2748 | 32.4122 | 4.7583 | 8.3791 | 6.7583 | 5.7583 | 8.1474 | 10.1374 | 8.3791 | 14.1374 | 22.2848 | 32.4222 | 0.01
6.5861 | 9.293 | 8.5861 | 7.5861 | 10.8791 | 12.8791 | 9.293 | 16.8791 | 27.7582 | 40.6373 | 6.5861 | 9.293 | 8.5861 | 7.5861 | 10.8891 | 12.8791 | 9.293 | 16.8791 | 27.7682 | 40.6473 | 0.01
8.5851 | 10.2925 | 10.5851 | 9.5851 | 13.8776 | 15.8776 | 10.2925 | 19.8776 | 33.7552 | 49.6328 | 8.5851 | 10.2925 | 10.5851 | 9.5851 | 13.8876 | 15.8776 | 10.2925 | 19.8776 | 33.7652 | 49.6428 | 0.01
8.0992 | 10.0496 | 10.0992 | 9.0992 | 13.1489 | 15.1489 | 10.0496 | 19.1489 | 32.2977 | 47.4466 | 8.0992 | 10.0496 | 10.0992 | 9.0992 | 13.1589 | 15.1489 | 10.0496 | 19.1489 | 32.3077 | 47.4566 | 0.01
6.8226 | 9.4113 | 8.8226 | 7.8226 | 11.2338 | 13.2338 | 9.4113 | 17.2338 | 28.4677 | 41.7015 | 6.8226 | 9.4113 | 8.8226 | 7.8226 | 11.2438 | 13.2338 | 9.4113 | 17.2338 | 28.4777 | 41.7115 | 0.01
5.9018 | 8.9509 | 7.9018 | 6.9018 | 9.8527 | 11.8527 | 8.9509 | 15.8527 | 25.7054 | 37.5582 | 5.9018 | 8.9509 | 7.9018 | 6.9018 | 9.8627 | 11.8527 | 8.9509 | 15.8527 | 25.7154 | 37.5682 | 0.01
3.8038 | 7.9019 | 5.8038 | 4.8038 | 6.7057 | 8.7057 | 7.9019 | 12.7057 | 19.4114 | 28.1172 | 3.8038 | 7.9019 | 5.8038 | 4.8038 | 6.7157 | 8.7057 | 7.9019 | 12.7057 | 19.4214 | 28.1272 | 0.01
7.6562 | 9.8281 | 9.6562 | 8.6562 | 12.4843 | 14.4843 | 9.8281 | 18.4843 | 30.9687 | 45.453 | 7.6562 | 9.8281 | 9.6562 | 8.6562 | 12.4943 | 14.4843 | 9.8281 | 18.4843 | 30.9787 | 45.463 | 0.01
5.9438 | 8.9719 | 7.9438 | 6.9438 | 9.9156 | 11.9156 | 8.9719 | 15.9156 | 25.8313 | 37.7469 | 5.9438 | 8.9719 | 7.9438 | 6.9438 | 9.9256 | 11.9156 | 8.9719 | 15.9156 | 25.8413 | 37.7569 | 0.01
4.5206 | 8.2603 | 6.5206 | 5.5206 | 7.7809 | 9.7809 | 8.2603 | 13.7809 | 21.5618 | 31.3428 | 4.5206 | 8.2603 | 6.5206 | 5.5206 | 7.7909 | 9.7809 | 8.2603 | 13.7809 | 21.5718 | 31.3528 | 0.01
6.1925 | 9.0963 | 8.1925 | 7.1925 | 10.2888 | 12.2888 | 9.0963 | 16.2888 | 26.5776 | 38.8664 | 6.1925 | 9.0963 | 8.1925 | 7.1925 | 10.2988 | 12.2888 | 9.0963 | 16.2888 | 26.5876 | 38.8764 | 0.01
6.2748 | 9.1374 | 8.2748 | 7.2748 | 10.4122 | 12.4122 | 9.1374 | 16.4122 | 26.8244 | 39.2366 | 6.2748 | 9.1374 | 8.2748 | 7.2748 | 10.4222 | 12.4122 | 9.1374 | 16.4122 | 26.8344 | 39.2466 | 0.01
6.3519 | 9.176 | 8.3519 | 7.3519 | 10.5279 | 12.5279 | 9.176 | 16.5279 | 27.0558 | 39.5837 | 6.3519 | 9.176 | 8.3519 | 7.3519 | 10.5379 | 12.5279 | 9.176 | 16.5279 | 27.0658 | 39.5937 | 0.01
4.0229 | 8.0115 | 6.0229 | 5.0229 | 7.0344 | 9.0344 | 8.0115 | 13.0344 | 20.0687 | 29.1031 | 4.0229 | 8.0115 | 6.0229 | 5.0229 | 7.0444 | 9.0344 | 8.0115 | 13.0344 | 20.0787 | 29.1131 | 0.01
5.9303 | 8.9651 | 7.9303 | 6.9303 | 9.8954 | 11.8954 | 8.9651 | 15.8954 | 25.7909 | 37.6863 | 5.9303 | 8.9651 | 7.9303 | 6.9303 | 9.9054 | 11.8954 | 8.9651 | 15.8954 | 25.8009 | 37.6963 | 0.01
6.936 | 9.468 | 8.936 | 7.936 | 11.404 | 13.404 | 9.468 | 17.404 | 28.808 | 42.2119 | 6.936 | 9.468 | 8.936 | 7.936 | 11.414 | 13.404 | 9.468 | 17.404 | 28.818 | 42.2219 | 0.01
7.0226 | 9.5113 | 9.0226 | 8.0226 | 11.5339 | 13.5339 | 9.5113 | 17.5339 | 29.0677 | 42.6016 | 7.0226 | 9.5113 | 9.0226 | 8.0226 | 11.5439 | 13.5339 | 9.5113 | 17.5339 | 29.0777 | 42.6116 | 0.01
2.7903 | 7.3951 | 4.7903 | 3.7903 | 5.1854 | 7.1854 | 7.3951 | 11.1854 | 16.3708 | 23.5562 | 2.7903 | 7.3951 | 4.7903 | 3.7903 | 5.1954 | 7.1854 | 7.3951 | 11.1854 | 16.3808 | 23.5662 | 0.01
6.8957 | 9.4479 | 8.8957 | 7.8957 | 11.3436 | 13.3436 | 9.4479 | 17.3436 | 28.6871 | 42.0307 | 6.8957 | 9.4479 | 8.8957 | 7.8957 | 11.3536 | 13.3436 | 9.4479 | 17.3436 | 28.6971 | 42.0407 | 0.01
6.0138 | 9.0069 | 8.0138 | 7.0138 | 10.0208 | 12.0208 | 9.0069 | 16.0208 | 26.0415 | 38.0623 | 6.0138 | 9.0069 | 8.0138 | 7.0138 | 10.0308 | 12.0208 | 9.0069 | 16.0208 | 26.0515 | 38.0723 | 0.01
3.8657 | 7.9328 | 5.8657 | 4.8657 | 6.7985 | 8.7985 | 7.9328 | 12.7985 | 19.597 | 28.3955 | 3.8657 | 7.9328 | 5.8657 | 4.8657 | 6.8085 | 8.7985 | 7.9328 | 12.7985 | 19.607 | 28.4055 | 0.01
7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2433 | 14.2333 | 9.7444 | 18.2333 | 30.4766 | 44.7098 | 0.01
8.8202 | 10.4101 | 10.8202 | 9.8202 | 14.2303 | 16.2303 | 10.4101 | 20.2303 | 34.4605 | 50.6908 | 8.8202 | 10.4101 | 10.8202 | 9.8202 | 14.2403 | 16.2303 | 10.4101 | 20.2303 | 34.4705 | 50.7008 | 0.01
7.8196 | 9.9098 | 9.8196 | 8.8196 | 12.7294 | 14.7294 | 9.9098 | 18.7294 | 31.4588 | 46.1882 | 7.8196 | 9.9098 | 9.8196 | 8.8196 | 12.7394 | 14.7294 | 9.9098 | 18.7294 | 31.4688 | 46.1982 | 0.01
4.576 | 8.288 | 6.576 | 5.576 | 7.864 | 9.864 | 8.288 | 13.864 | 21.7279 | 31.5919 | 4.576 | 8.288 | 6.576 | 5.576 | 7.874 | 9.864 | 8.288 | 13.864 | 21.7379 | 31.6019 | 0.01
7.0266 | 9.5133 | 9.0266 | 8.0266 | 11.5399 | 13.5399 | 9.5133 | 17.5399 | 29.0798 | 42.6196 | 7.0266 | 9.5133 | 9.0266 | 8.0266 | 11.5499 | 13.5399 | 9.5133 | 17.5399 | 29.0898 | 42.6296 | 0.01
6.0145 | 9.0072 | 8.0145 | 7.0145 | 10.0217 | 12.0217 | 9.0072 | 16.0217 | 26.0434 | 38.0651 | 6.0145 | 9.0072 | 8.0145 | 7.0145 | 10.0317 | 12.0217 | 9.0072 | 16.0217 | 26.0534 | 38.0751 | 0.01
2.6438 | 7.3219 | 4.6438 | 3.6438 | 4.9657 | 6.9657 | 7.3219 | 10.9657 | 15.9313 | 22.897 | 2.6438 | 7.3219 | 4.6438 | 3.6438 | 4.9757 | 6.9657 | 7.3219 | 10.9657 | 15.9413 | 22.907 | 0.01
6.0348 | 9.0174 | 8.0348 | 7.0348 | 10.0522 | 12.0522 | 9.0174 | 16.0522 | 26.1044 | 38.1566 | 6.0348 | 9.0174 | 8.0348 | 7.0348 | 10.0622 | 12.0522 | 9.0174 | 16.0522 | 26.1144 | 38.1666 | 0.01
5.4907 | 8.7453 | 7.4907 | 6.4907 | 9.236 | 11.236 | 8.7453 | 15.236 | 24.472 | 35.7079 | 5.4907 | 8.7453 | 7.4907 | 6.4907 | 9.246 | 11.236 | 8.7453 | 15.236 | 24.482 | 35.7179 | 0.01
7.3925 | 9.6962 | 9.3925 | 8.3925 | 12.0887 | 14.0887 | 9.6962 | 18.0887 | 30.1774 | 44.2661 | 7.3925 | 9.6962 | 9.3925 | 8.3925 | 12.0987 | 14.0887 | 9.6962 | 18.0887 | 30.1874 | 44.2761 | 0.01
6.0746 | 9.0373 | 8.0746 | 7.0746 | 10.1119 | 12.1119 | 9.0373 | 16.1119 | 26.2238 | 38.3357 | 6.0746 | 9.0373 | 8.0746 | 7.0746 | 10.1219 | 12.1119 | 9.0373 | 16.1119 | 26.2338 | 38.3457 | 0.01
5.7247 | 8.8624 | 7.7247 | 6.7247 | 9.5871 | 11.5871 | 8.8624 | 15.5871 | 25.1742 | 36.7613 | 5.7247 | 8.8624 | 7.7247 | 6.7247 | 9.5971 | 11.5871 | 8.8624 | 15.5871 | 25.1842 | 36.7713 | 0.01
5.7801 | 8.89 | 7.7801 | 6.7801 | 9.6701 | 11.6701 | 8.89 | 15.6701 | 25.3403 | 37.0104 | 5.7801 | 8.89 | 7.7801 | 6.7801 | 9.6801 | 11.6701 | 8.89 | 15.6701 | 25.3503 | 37.0204 | 0.01
4.7764 | 8.3882 | 6.7764 | 5.7764 | 8.1646 | 10.1646 | 8.3882 | 14.1646 | 22.3292 | 32.4937 | 4.7764 | 8.3882 | 6.7764 | 5.7764 | 8.1746 | 10.1646 | 8.3882 | 14.1646 | 22.3392 | 32.5037 | 0.01
2.1447 | 7.0723 | 4.1447 | 3.1447 | 4.217 | 6.217 | 7.0723 | 10.217 | 14.434 | 20.6509 | 2.1447 | 7.0723 | 4.1447 | 3.1447 | 4.227 | 6.217 | 7.0723 | 10.217 | 14.444 | 20.6609 | 0.01
5.7028 | 8.8514 | 7.7028 | 6.7028 | 9.5542 | 11.5542 | 8.8514 | 15.5542 | 25.1084 | 36.6625 | 5.7028 | 8.8514 | 7.7028 | 6.7028 | 9.5642 | 11.5542 | 8.8514 | 15.5542 | 25.1184 | 36.6725 | 0.01
7.7214 | 9.8607 | 9.7214 | 8.7214 | 12.582 | 14.582 | 9.8607 | 18.582 | 31.1641 | 45.7461 | 7.7214 | 9.8607 | 9.7214 | 8.7214 | 12.592 | 14.582 | 9.8607 | 18.582 | 31.1741 | 45.7561 | 0.01
5.5976 | 8.7988 | 7.5976 | 6.5976 | 9.3964 | 11.3964 | 8.7988 | 15.3964 | 24.7928 | 36.1892 | 5.5976 | 8.7988 | 7.5976 | 6.5976 | 9.4064 | 11.3964 | 8.7988 | 15.3964 | 24.8028 | 36.1992 | 0.01
5.3389 | 8.6695 | 7.3389 | 6.3389 | 9.0084 | 11.0084 | 8.6695 | 15.0084 | 24.0167 | 35.0251 | 5.3389 | 8.6695 | 7.3389 | 6.3389 | 9.0184 | 11.0084 | 8.6695 | 15.0084 | 24.0267 | 35.0351 | 0.01
8.3081 | 10.154 | 10.3081 | 9.3081 | 13.4621 | 15.4621 | 10.154 | 19.4621 | 32.9243 | 48.3864 | 8.3081 | 10.154 | 10.3081 | 9.3081 | 13.4721 | 15.4621 | 10.154 | 19.4621 | 32.9343 | 48.3964 | 0.01
6.3383 | 9.1691 | 8.3383 | 7.3383 | 10.5074 | 12.5074 | 9.1691 | 16.5074 | 27.0148 | 39.5222 | 6.3383 | 9.1691 | 8.3383 | 7.3383 | 10.5174 | 12.5074 | 9.1691 | 16.5074 | 27.0248 | 39.5322 | 0.01
6.2356 | 9.1178 | 8.2356 | 7.2356 | 10.3534 | 12.3534 | 9.1178 | 16.3534 | 26.7069 | 39.0603 | 6.2356 | 9.1178 | 8.2356 | 7.2356 | 10.3634 | 12.3534 | 9.1178 | 16.3534 | 26.7169 | 39.0703 | 0.01
8.8103 | 10.4051 | 10.8103 | 9.8103 | 14.2154 | 16.2154 | 10.4051 | 20.2154 | 34.4309 | 50.6463 | 8.8103 | 10.4051 | 10.8103 | 9.8103 | 14.2254 | 16.2154 | 10.4051 | 20.2154 | 34.4409 | 50.6563 | 0.01
9.1328 | 10.5664 | 11.1328 | 10.1328 | 14.6992 | 16.6992 | 10.5664 | 20.6992 | 35.3985 | 52.0977 | 9.1328 | 10.5664 | 11.1328 | 10.1328 | 14.7092 | 16.6992 | 10.5664 | 20.6992 | 35.4085 | 52.1077 | 0.01
7.1789 | 9.5895 | 9.1789 | 8.1789 | 11.7684 | 13.7684 | 9.5895 | 17.7684 | 29.5367 | 43.3051 | 7.1789 | 9.5895 | 9.1789 | 8.1789 | 11.7784 | 13.7684 | 9.5895 | 17.7684 | 29.5467 | 43.3151 | 0.01
6.2187 | 9.1093 | 8.2187 | 7.2187 | 10.328 | 12.328 | 9.1093 | 16.328 | 26.6561 | 38.9841 | 6.2187 | 9.1093 | 8.2187 | 7.2187 | 10.338 | 12.328 | 9.1093 | 16.328 | 26.6661 | 38.9941 | 0.01
10.8017 | 11.4008 | 12.8017 | 11.8017 | 17.2025 | 19.2025 | 11.4008 | 23.2025 | 40.405 | 59.6075 | 10.8017 | 11.4008 | 12.8017 | 11.8017 | 17.2125 | 19.2025 | 11.4008 | 23.2025 | 40.415 | 59.6175 | 0.01
4.3082 | 8.1541 | 6.3082 | 5.3082 | 7.4622 | 9.4622 | 8.1541 | 13.4622 | 20.9245 | 30.3867 | 4.3082 | 8.1541 | 6.3082 | 5.3082 | 7.4722 | 9.4622 | 8.1541 | 13.4622 | 20.9345 | 30.3967 | 0.01
6.2847 | 9.1423 | 8.2847 | 7.2847 | 10.427 | 12.427 | 9.1423 | 16.427 | 26.8541 | 39.2811 | 6.2847 | 9.1423 | 8.2847 | 7.2847 | 10.437 | 12.427 | 9.1423 | 16.427 | 26.8641 | 39.2911 | 0.01
3.8754 | 7.9377 | 5.8754 | 4.8754 | 6.8131 | 8.8131 | 7.9377 | 12.8131 | 19.6261 | 28.4392 | 3.8754 | 7.9377 | 5.8754 | 4.8754 | 6.8231 | 8.8131 | 7.9377 | 12.8131 | 19.6361 | 28.4492 | 0.01
3.5216 | 7.7608 | 5.5216 | 4.5216 | 6.2824 | 8.2824 | 7.7608 | 12.2824 | 18.5649 | 26.8473 | 3.5216 | 7.7608 | 5.5216 | 4.5216 | 6.2924 | 8.2824 | 7.7608 | 12.2824 | 18.5749 | 26.8573 | 0.01
5.5633 | 8.7817 | 7.5633 | 6.5633 | 9.345 | 11.345 | 8.7817 | 15.345 | 24.69 | 36.0351 | 5.5633 | 8.7817 | 7.5633 | 6.5633 | 9.355 | 11.345 | 8.7817 | 15.345 | 24.7 | 36.0451 | 0.01
4.8463 | 8.4232 | 6.8463 | 5.8463 | 8.2695 | 10.2695 | 8.4232 | 14.2695 | 22.5389 | 32.8084 | 4.8463 | 8.4232 | 6.8463 | 5.8463 | 8.2795 | 10.2695 | 8.4232 | 14.2695 | 22.5489 | 32.8184 | 0.01
6.9828 | 9.4914 | 8.9828 | 7.9828 | 11.4743 | 13.4743 | 9.4914 | 17.4743 | 28.9485 | 42.4228 | 6.9828 | 9.4914 | 8.9828 | 7.9828 | 11.4843 | 13.4743 | 9.4914 | 17.4743 | 28.9585 | 42.4328 | 0.01
7.8476 | 9.9238 | 9.8476 | 8.8476 | 12.7713 | 14.7713 | 9.9238 | 18.7713 | 31.5427 | 46.314 | 7.8476 | 9.9238 | 9.8476 | 8.8476 | 12.7813 | 14.7713 | 9.9238 | 18.7713 | 31.5527 | 46.324 | 0.01
7.0345 | 9.5172 | 9.0345 | 8.0345 | 11.5517 | 13.5517 | 9.5172 | 17.5517 | 29.1034 | 42.655 | 7.0345 | 9.5172 | 9.0345 | 8.0345 | 11.5617 | 13.5517 | 9.5172 | 17.5517 | 29.1134 | 42.665 | 0.01
7.2596 | 9.6298 | 9.2596 | 8.2596 | 11.8894 | 13.8894 | 9.6298 | 17.8894 | 29.7788 | 43.6682 | 7.2596 | 9.6298 | 9.2596 | 8.2596 | 11.8994 | 13.8894 | 9.6298 | 17.8894 | 29.7888 | 43.6782 | 0.01
6.762 | 9.381 | 8.762 | 7.762 | 11.143 | 13.143 | 9.381 | 17.143 | 28.286 | 41.4289 | 6.762 | 9.381 | 8.762 | 7.762 | 11.153 | 13.143 | 9.381 | 17.143 | 28.296 | 41.4389 | 0.01
4.7843 | 8.3922 | 6.7843 | 5.7843 | 8.1765 | 10.1765 | 8.3922 | 14.1765 | 22.3529 | 32.5294 | 4.7843 | 8.3922 | 6.7843 | 5.7843 | 8.1865 | 10.1765 | 8.3922 | 14.1765 | 22.3629 | 32.5394 | 0.01
5.9404 | 8.9702 | 7.9404 | 6.9404 | 9.9106 | 11.9106 | 8.9702 | 15.9106 | 25.8212 | 37.7318 | 5.9404 | 8.9702 | 7.9404 | 6.9404 | 9.9206 | 11.9106 | 8.9702 | 15.9106 | 25.8312 | 37.7418 | 0.01
6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.5072 | 12.4972 | 9.1657 | 16.4972 | 27.0043 | 39.5015 | 0.01
7.0135 | 9.5068 | 9.0135 | 8.0135 | 11.5203 | 13.5203 | 9.5068 | 17.5203 | 29.0406 | 42.5608 | 7.0135 | 9.5068 | 9.0135 | 8.0135 | 11.5303 | 13.5203 | 9.5068 | 17.5203 | 29.0506 | 42.5708 | 0.01
3.4265 | 7.7133 | 5.4265 | 4.4265 | 6.1398 | 8.1398 | 7.7133 | 12.1398 | 18.2796 | 26.4194 | 3.4265 | 7.7133 | 5.4265 | 4.4265 | 6.1498 | 8.1398 | 7.7133 | 12.1398 | 18.2896 | 26.4294 | 0.01
5.4813 | 8.7407 | 7.4813 | 6.4813 | 9.222 | 11.222 | 8.7407 | 15.222 | 24.444 | 35.6659 | 5.4813 | 8.7407 | 7.4813 | 6.4813 | 9.232 | 11.222 | 8.7407 | 15.222 | 24.454 | 35.6759 | 0.01
7.7681 | 9.8841 | 9.7681 | 8.7681 | 12.6522 | 14.6522 | 9.8841 | 18.6522 | 31.3044 | 45.9566 | 7.7681 | 9.8841 | 9.7681 | 8.7681 | 12.6622 | 14.6522 | 9.8841 | 18.6522 | 31.3144 | 45.9666 | 0.01
6.4122 | 9.2061 | 8.4122 | 7.4122 | 10.6184 | 12.6184 | 9.2061 | 16.6184 | 27.2367 | 39.8551 | 6.4122 | 9.2061 | 8.4122 | 7.4122 | 10.6284 | 12.6184 | 9.2061 | 16.6184 | 27.2467 | 39.8651 | 0.01
8.7219 | 10.361 | 10.7219 | 9.7219 | 14.0829 | 16.0829 | 10.361 | 20.0829 | 34.1657 | 50.2486 | 8.7219 | 10.361 | 10.7219 | 9.7219 | 14.0929 | 16.0829 | 10.361 | 20.0829 | 34.1757 | 50.2586 | 0.01
5.8098 | 8.9049 | 7.8098 | 6.8098 | 9.7147 | 11.7147 | 8.9049 | 15.7147 | 25.4293 | 37.144 | 5.8098 | 8.9049 | 7.8098 | 6.8098 | 9.7247 | 11.7147 | 8.9049 | 15.7147 | 25.4393 | 37.154 | 0.01
4.8329 | 8.4165 | 6.8329 | 5.8329 | 8.2494 | 10.2494 | 8.4165 | 14.2494 | 22.4987 | 32.7481 | 4.8329 | 8.4165 | 6.8329 | 5.8329 | 8.2594 | 10.2494 | 8.4165 | 14.2494 | 22.5087 | 32.7581 | 0.01
6.7605 | 9.3803 | 8.7605 | 7.7605 | 11.1408 | 13.1408 | 9.3803 | 17.1408 | 28.2815 | 41.4223 | 6.7605 | 9.3803 | 8.7605 | 7.7605 | 11.1508 | 13.1408 | 9.3803 | 17.1408 | 28.2915 | 41.4323 | 0.01
9.047 | 10.5235 | 11.047 | 10.047 | 14.5706 | 16.5706 | 10.5235 | 20.5706 | 35.1411 | 51.7117 | 9.047 | 10.5235 | 11.047 | 10.047 | 14.5806 | 16.5706 | 10.5235 | 20.5706 | 35.1511 | 51.7217 | 0.01
7.8454 | 9.9227 | 9.8454 | 8.8454 | 12.7682 | 14.7682 | 9.9227 | 18.7682 | 31.5363 | 46.3045 | 7.8454 | 9.9227 | 9.8454 | 8.8454 | 12.7782 | 14.7682 | 9.9227 | 18.7682 | 31.5463 | 46.3145 | 0.01
6.6496 | 9.3248 | 8.6496 | 7.6496 | 10.9744 | 12.9744 | 9.3248 | 16.9744 | 27.9489 | 40.9233 | 6.6496 | 9.3248 | 8.6496 | 7.6496 | 10.9844 | 12.9744 | 9.3248 | 16.9744 | 27.9589 | 40.9333 | 0.01
4.2135 | 8.1067 | 6.2135 | 5.2135 | 7.3202 | 9.3202 | 8.1067 | 13.3202 | 20.6404 | 29.9606 | 4.2135 | 8.1067 | 6.2135 | 5.2135 | 7.3302 | 9.3202 | 8.1067 | 13.3202 | 20.6504 | 29.9706 | 0.01
11.6293 | 11.8146 | 13.6293 | 12.6293 | 18.4439 | 20.4439 | 11.8146 | 24.4439 | 42.8878 | 63.3317 | 11.6293 | 11.8146 | 13.6293 | 12.6293 | 18.4539 | 20.4439 | 11.8146 | 24.4439 | 42.8978 | 63.3417 | 0.01
5.3138 | 8.6569 | 7.3138 | 6.3138 | 8.9707 | 10.9707 | 8.6569 | 14.9707 | 23.9414 | 34.9122 | 5.3138 | 8.6569 | 7.3138 | 6.3138 | 8.9807 | 10.9707 | 8.6569 | 14.9707 | 23.9514 | 34.9222 | 0.01
6.2814 | 9.1407 | 8.2814 | 7.2814 | 10.4222 | 12.4222 | 9.1407 | 16.4222 | 26.8443 | 39.2665 | 6.2814 | 9.1407 | 8.2814 | 7.2814 | 10.4322 | 12.4222 | 9.1407 | 16.4222 | 26.8543 | 39.2765 | 0.01
5.935 | 8.9675 | 7.935 | 6.935 | 9.9026 | 11.9026 | 8.9675 | 15.9026 | 25.8051 | 37.7077 | 5.935 | 8.9675 | 7.935 | 6.935 | 9.9126 | 11.9026 | 8.9675 | 15.9026 | 25.8151 | 37.7177 | 0.01
6.1508 | 9.0754 | 8.1508 | 7.1508 | 10.2262 | 12.2262 | 9.0754 | 16.2262 | 26.4523 | 38.6785 | 6.1508 | 9.0754 | 8.1508 | 7.1508 | 10.2362 | 12.2262 | 9.0754 | 16.2262 | 26.4623 | 38.6885 | 0.01
5.3276 | 8.6638 | 7.3276 | 6.3276 | 8.9914 | 10.9914 | 8.6638 | 14.9914 | 23.9828 | 34.9742 | 5.3276 | 8.6638 | 7.3276 | 6.3276 | 9.0014 | 10.9914 | 8.6638 | 14.9914 | 23.9928 | 34.9842 | 0.01
2.0185 | 7.0093 | 4.0185 | 3.0185 | 4.0278 | 6.0278 | 7.0093 | 10.0278 | 14.0556 | 20.0834 | 2.0185 | 7.0093 | 4.0185 | 3.0185 | 4.0378 | 6.0278 | 7.0093 | 10.0278 | 14.0656 | 20.0934 | 0.01
7.9373 | 9.9687 | 9.9373 | 8.9373 | 12.906 | 14.906 | 9.9687 | 18.906 | 31.812 | 46.718 | 7.9373 | 9.9687 | 9.9373 | 8.9373 | 12.916 | 14.906 | 9.9687 | 18.906 | 31.822 | 46.728 | 0.01
7.1858 | 9.5929 | 9.1858 | 8.1858 | 11.7787 | 13.7787 | 9.5929 | 17.7787 | 29.5575 | 43.3362 | 7.1858 | 9.5929 | 9.1858 | 8.1858 | 11.7887 | 13.7787 | 9.5929 | 17.7787 | 29.5675 | 43.3462 | 0.01
6.7905 | 9.3953 | 8.7905 | 7.7905 | 11.1858 | 13.1858 | 9.3953 | 17.1858 | 28.3716 | 41.5574 | 6.7905 | 9.3953 | 8.7905 | 7.7905 | 11.1958 | 13.1858 | 9.3953 | 17.1858 | 28.3816 | 41.5674 | 0.01
8.3321 | 10.166 | 10.3321 | 9.3321 | 13.4981 | 15.4981 | 10.166 | 19.4981 | 32.9962 | 48.4944 | 8.3321 | 10.166 | 10.3321 | 9.3321 | 13.5081 | 15.4981 | 10.166 | 19.4981 | 33.0062 | 48.5044 | 0.01
4.4306 | 8.2153 | 6.4306 | 5.4306 | 7.6459 | 9.6459 | 8.2153 | 13.6459 | 21.2918 | 30.9377 | 4.4306 | 8.2153 | 6.4306 | 5.4306 | 7.6559 | 9.6459 | 8.2153 | 13.6459 | 21.3018 | 30.9477 | 0.01
5.963 | 8.9815 | 7.963 | 6.963 | 9.9446 | 11.9446 | 8.9815 | 15.9446 | 25.8891 | 37.8337 | 5.963 | 8.9815 | 7.963 | 6.963 | 9.9546 | 11.9446 | 8.9815 | 15.9446 | 25.8991 | 37.8437 | 0.01
5.0349 | 8.5174 | 7.0349 | 6.0349 | 8.5523 | 10.5523 | 8.5174 | 14.5523 | 23.1047 | 33.657 | 5.0349 | 8.5174 | 7.0349 | 6.0349 | 8.5623 | 10.5523 | 8.5174 | 14.5523 | 23.1147 | 33.667 | 0.01
7.8813 | 9.9407 | 9.8813 | 8.8813 | 12.822 | 14.822 | 9.9407 | 18.822 | 31.644 | 46.466 | 7.8813 | 9.9407 | 9.8813 | 8.8813 | 12.832 | 14.822 | 9.9407 | 18.822 | 31.654 | 46.476 | 0.01
2.9422 | 7.4711 | 4.9422 | 3.9422 | 5.4133 | 7.4133 | 7.4711 | 11.4133 | 16.8265 | 24.2398 | 2.9422 | 7.4711 | 4.9422 | 3.9422 | 5.4233 | 7.4133 | 7.4711 | 11.4133 | 16.8365 | 24.2498 | 0.01
5.5831 | 8.7915 | 7.5831 | 6.5831 | 9.3746 | 11.3746 | 8.7915 | 15.3746 | 24.7492 | 36.1238 | 5.5831 | 8.7915 | 7.5831 | 6.5831 | 9.3846 | 11.3746 | 8.7915 | 15.3746 | 24.7592 | 36.1338 | 0.01
6.1071 | 9.0535 | 8.1071 | 7.1071 | 10.1606 | 12.1606 | 9.0535 | 16.1606 | 26.3212 | 38.4818 | 6.1071 | 9.0535 | 8.1071 | 7.1071 | 10.1706 | 12.1606 | 9.0535 | 16.1606 | 26.3312 | 38.4918 | 0.01
3.7728 | 7.8864 | 5.7728 | 4.7728 | 6.6592 | 8.6592 | 7.8864 | 12.6592 | 19.3184 | 27.9776 | 3.7728 | 7.8864 | 5.7728 | 4.7728 | 6.6692 | 8.6592 | 7.8864 | 12.6592 | 19.3284 | 27.9876 | 0.01
7.4075 | 9.7038 | 9.4075 | 8.4075 | 12.1113 | 14.1113 | 9.7038 | 18.1113 | 30.2226 | 44.3338 | 7.4075 | 9.7038 | 9.4075 | 8.4075 | 12.1213 | 14.1113 | 9.7038 | 18.1113 | 30.2326 | 44.3438 | 0.01
4.9966 | 8.4983 | 6.9966 | 5.9966 | 8.4948 | 10.4948 | 8.4983 | 14.4948 | 22.9897 | 33.4845 | 4.9966 | 8.4983 | 6.9966 | 5.9966 | 8.5048 | 10.4948 | 8.4983 | 14.4948 | 22.9997 | 33.4945 | 0.01
5.7338 | 8.8669 | 7.7338 | 6.7338 | 9.6008 | 11.6008 | 8.8669 | 15.6008 | 25.2015 | 36.8023 | 5.7338 | 8.8669 | 7.7338 | 6.7338 | 9.6108 | 11.6008 | 8.8669 | 15.6008 | 25.2115 | 36.8123 | 0.01
9.5995 | 10.7997 | 11.5995 | 10.5995 | 15.3992 | 17.3992 | 10.7997 | 21.3992 | 36.7984 | 54.1977 | 9.5995 | 10.7997 | 11.5995 | 10.5995 | 15.4092 | 17.3992 | 10.7997 | 21.3992 | 36.8084 | 54.2077 | 0.01
4.5772 | 8.2886 | 6.5772 | 5.5772 | 7.8657 | 9.8657 | 8.2886 | 13.8657 | 21.7315 | 31.5972 | 4.5772 | 8.2886 | 6.5772 | 5.5772 | 7.8757 | 9.8657 | 8.2886 | 13.8657 | 21.7415 | 31.6072 | 0.01
6.272 | 9.136 | 8.272 | 7.272 | 10.408 | 12.408 | 9.136 | 16.408 | 26.8161 | 39.2241 | 6.272 | 9.136 | 8.272 | 7.272 | 10.418 | 12.408 | 9.136 | 16.408 | 26.8261 | 39.2341 | 0.01
8.0427 | 10.0214 | 10.0427 | 9.0427 | 13.0641 | 15.0641 | 10.0214 | 19.0641 | 32.1282 | 47.1924 | 8.0427 | 10.0214 | 10.0427 | 9.0427 | 13.0741 | 15.0641 | 10.0214 | 19.0641 | 32.1382 | 47.2024 | 0.01
7.5719 | 9.7859 | 9.5719 | 8.5719 | 12.3578 | 14.3578 | 9.7859 | 18.3578 | 30.7157 | 45.0735 | 7.5719 | 9.7859 | 9.5719 | 8.5719 | 12.3678 | 14.3578 | 9.7859 | 18.3578 | 30.7257 | 45.0835 | 0.01
5.6432 | 8.8216 | 7.6432 | 6.6432 | 9.4649 | 11.4649 | 8.8216 | 15.4649 | 24.9297 | 36.3946 | 5.6432 | 8.8216 | 7.6432 | 6.6432 | 9.4749 | 11.4649 | 8.8216 | 15.4649 | 24.9397 | 36.4046 | 0.01
8.7355 | 10.3677 | 10.7355 | 9.7355 | 14.1032 | 16.1032 | 10.3677 | 20.1032 | 34.2065 | 50.3097 | 8.7355 | 10.3677 | 10.7355 | 9.7355 | 14.1132 | 16.1032 | 10.3677 | 20.1032 | 34.2165 | 50.3197 | 0.01
5.0301 | 8.515 | 7.0301 | 6.0301 | 8.5451 | 10.5451 | 8.515 | 14.5451 | 23.0902 | 33.6354 | 5.0301 | 8.515 | 7.0301 | 6.0301 | 8.5551 | 10.5451 | 8.515 | 14.5451 | 23.1002 | 33.6454 | 0.01
7.0523 | 9.5262 | 9.0523 | 8.0523 | 11.5785 | 13.5785 | 9.5262 | 17.5785 | 29.157 | 42.7355 | 7.0523 | 9.5262 | 9.0523 | 8.0523 | 11.5885 | 13.5785 | 9.5262 | 17.5785 | 29.167 | 42.7455 | 0.01
7.9439 | 9.972 | 9.9439 | 8.9439 | 12.9159 | 14.9159 | 9.972 | 18.9159 | 31.8318 | 46.7478 | 7.9439 | 9.972 | 9.9439 | 8.9439 | 12.9259 | 14.9159 | 9.972 | 18.9159 | 31.8418 | 46.7578 | 0.01
8.5616 | 10.2808 | 10.5616 | 9.5616 | 13.8424 | 15.8424 | 10.2808 | 19.8424 | 33.6848 | 49.5272 | 8.5616 | 10.2808 | 10.5616 | 9.5616 | 13.8524 | 15.8424 | 10.2808 | 19.8424 | 33.6948 | 49.5372 | 0.01
7.3831 | 9.6916 | 9.3831 | 8.3831 | 12.0747 | 14.0747 | 9.6916 | 18.0747 | 30.1494 | 44.2241 | 7.3831 | 9.6916 | 9.3831 | 8.3831 | 12.0847 | 14.0747 | 9.6916 | 18.0747 | 30.1594 | 44.2341 | 0.01
4.1357 | 8.0679 | 6.1357 | 5.1357 | 7.2036 | 9.2036 | 8.0679 | 13.2036 | 20.4072 | 29.6108 | 4.1357 | 8.0679 | 6.1357 | 5.1357 | 7.2136 | 9.2036 | 8.0679 | 13.2036 | 20.4172 | 29.6208 | 0.01
2.1727 | 7.0864 | 4.1727 | 3.1727 | 4.2591 | 6.2591 | 7.0864 | 10.2591 | 14.5182 | 20.7772 | 2.1727 | 7.0864 | 4.1727 | 3.1727 | 4.2691 | 6.2591 | 7.0864 | 10.2591 | 14.5282 | 20.7872 | 0.01
5.5513 | 8.7756 | 7.5513 | 6.5513 | 9.3269 | 11.3269 | 8.7756 | 15.3269 | 24.6538 | 35.9807 | 5.5513 | 8.7756 | 7.5513 | 6.5513 | 9.3369 | 11.3269 | 8.7756 | 15.3269 | 24.6638 | 35.9907 | 0.01
3.49 | 7.745 | 5.49 | 4.49 | 6.235 | 8.235 | 7.745 | 12.235 | 18.47 | 26.705 | 3.49 | 7.745 | 5.49 | 4.49 | 6.245 | 8.235 | 7.745 | 12.235 | 18.48 | 26.715 | 0.01
0.33785 | 6.1689 | 2.3378 | 1.3378 | 1.5068 | 3.5068 | 6.1689 | 7.5068 | 9.0135 | 12.5203 | 0.33785 | 6.1689 | 2.3378 | 1.3378 | 1.5168 | 3.5068 | 6.1689 | 7.5068 | 9.0235 | 12.5303 | 0.01
5.2149 | 8.6075 | 7.2149 | 6.2149 | 8.8224 | 10.8224 | 8.6075 | 14.8224 | 23.6448 | 34.4672 | 5.2149 | 8.6075 | 7.2149 | 6.2149 | 8.8324 | 10.8224 | 8.6075 | 14.8224 | 23.6548 | 34.4772 | 0.01
7.5632 | 9.7816 | 9.5632 | 8.5632 | 12.3447 | 14.3447 | 9.7816 | 18.3447 | 30.6895 | 45.0342 | 7.5632 | 9.7816 | 9.5632 | 8.5632 | 12.3547 | 14.3447 | 9.7816 | 18.3447 | 30.6995 | 45.0442 | 0.01
7.7902 | 9.8951 | 9.7902 | 8.7902 | 12.6853 | 14.6853 | 9.8951 | 18.6853 | 31.3705 | 46.0558 | 7.7902 | 9.8951 | 9.7902 | 8.7902 | 12.6953 | 14.6853 | 9.8951 | 18.6853 | 31.3805 | 46.0658 | 0.01
9.4106 | 10.7053 | 11.4106 | 10.4106 | 15.1159 | 17.1159 | 10.7053 | 21.1159 | 36.2318 | 53.3477 | 9.4106 | 10.7053 | 11.4106 | 10.4106 | 15.1259 | 17.1159 | 10.7053 | 21.1159 | 36.2418 | 53.3577 | 0.01
6.338 | 9.169 | 8.338 | 7.338 | 10.5069 | 12.5069 | 9.169 | 16.5069 | 27.0139 | 39.5208 | 6.338 | 9.169 | 8.338 | 7.338 | 10.5169 | 12.5069 | 9.169 | 16.5069 | 27.0239 | 39.5308 | 0.01
8.4698 | 10.2349 | 10.4698 | 9.4698 | 13.7047 | 15.7047 | 10.2349 | 19.7047 | 33.4094 | 49.1142 | 8.4698 | 10.2349 | 10.4698 | 9.4698 | 13.7147 | 15.7047 | 10.2349 | 19.7047 | 33.4194 | 49.1242 | 0.01
3.966 | 7.983 | 5.966 | 4.966 | 6.949 | 8.949 | 7.983 | 12.949 | 19.898 | 28.847 | 3.966 | 7.983 | 5.966 | 4.966 | 6.959 | 8.949 | 7.983 | 12.949 | 19.908 | 28.857 | 0.01
2.0788 | 7.0394 | 4.0788 | 3.0788 | 4.1183 | 6.1183 | 7.0394 | 10.1183 | 14.2365 | 20.3548 | 2.0788 | 7.0394 | 4.0788 | 3.0788 | 4.1283 | 6.1183 | 7.0394 | 10.1183 | 14.2465 | 20.3648 | 0.01
7.9038 | 9.9519 | 9.9038 | 8.9038 | 12.8558 | 14.8558 | 9.9519 | 18.8558 | 31.7115 | 46.5673 | 7.9038 | 9.9519 | 9.9038 | 8.9038 | 12.8658 | 14.8558 | 9.9519 | 18.8558 | 31.7215 | 46.5773 | 0.01
5.9358 | 8.9679 | 7.9358 | 6.9358 | 9.9037 | 11.9037 | 8.9679 | 15.9037 | 25.8074 | 37.7111 | 5.9358 | 8.9679 | 7.9358 | 6.9358 | 9.9137 | 11.9037 | 8.9679 | 15.9037 | 25.8174 | 37.7211 | 0.01
8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0815 | 15.0715 | 10.0238 | 19.0715 | 32.153 | 47.2244 | 0.01
6.657 | 9.3285 | 8.657 | 7.657 | 10.9856 | 12.9856 | 9.3285 | 16.9856 | 27.9711 | 40.9567 | 6.657 | 9.3285 | 8.657 | 7.657 | 10.9956 | 12.9856 | 9.3285 | 16.9856 | 27.9811 | 40.9667 | 0.01
6.5966 | 9.2983 | 8.5966 | 7.5966 | 10.8949 | 12.8949 | 9.2983 | 16.8949 | 27.7899 | 40.6848 | 6.5966 | 9.2983 | 8.5966 | 7.5966 | 10.9049 | 12.8949 | 9.2983 | 16.8949 | 27.7999 | 40.6948 | 0.01
5.4851 | 8.7426 | 7.4851 | 6.4851 | 9.2277 | 11.2277 | 8.7426 | 15.2277 | 24.4554 | 35.683 | 5.4851 | 8.7426 | 7.4851 | 6.4851 | 9.2377 | 11.2277 | 8.7426 | 15.2277 | 24.4654 | 35.693 | 0.01
3.0805 | 7.5402 | 5.0805 | 4.0805 | 5.6207 | 7.6207 | 7.5402 | 11.6207 | 17.2414 | 24.8621 | 3.0805 | 7.5402 | 5.0805 | 4.0805 | 5.6307 | 7.6207 | 7.5402 | 11.6207 | 17.2514 | 24.8721 | 0.01
7.2083 | 9.6042 | 9.2083 | 8.2083 | 11.8125 | 13.8125 | 9.6042 | 17.8125 | 29.625 | 43.4375 | 7.2083 | 9.6042 | 9.2083 | 8.2083 | 11.8225 | 13.8125 | 9.6042 | 17.8125 | 29.635 | 43.4475 | 0.01
2.7006 | 7.3503 | 4.7006 | 3.7006 | 5.0509 | 7.0509 | 7.3503 | 11.0509 | 16.1017 | 23.1526 | 2.7006 | 7.3503 | 4.7006 | 3.7006 | 5.0609 | 7.0509 | 7.3503 | 11.0509 | 16.1117 | 23.1626 | 0.01
7.4982 | 9.7491 | 9.4982 | 8.4982 | 12.2472 | 14.2472 | 9.7491 | 18.2472 | 30.4945 | 44.7417 | 7.4982 | 9.7491 | 9.4982 | 8.4982 | 12.2572 | 14.2472 | 9.7491 | 18.2472 | 30.5045 | 44.7517 | 0.01
5.3544 | 8.6772 | 7.3544 | 6.3544 | 9.0316 | 11.0316 | 8.6772 | 15.0316 | 24.0632 | 35.0948 | 5.3544 | 8.6772 | 7.3544 | 6.3544 | 9.0416 | 11.0316 | 8.6772 | 15.0316 | 24.0732 | 35.1048 | 0.01
4.5186 | 8.2593 | 6.5186 | 5.5186 | 7.7779 | 9.7779 | 8.2593 | 13.7779 | 21.5558 | 31.3337 | 4.5186 | 8.2593 | 6.5186 | 5.5186 | 7.7879 | 9.7779 | 8.2593 | 13.7779 | 21.5658 | 31.3437 | 0.01
4.8309 | 8.4155 | 6.8309 | 5.8309 | 8.2464 | 10.2464 | 8.4155 | 14.2464 | 22.4927 | 32.7391 | 4.8309 | 8.4155 | 6.8309 | 5.8309 | 8.2564 | 10.2464 | 8.4155 | 14.2464 | 22.5027 | 32.7491 | 0.01
1.1151 | 6.5575 | 3.1151 | 2.1151 | 2.6726 | 4.6726 | 6.5575 | 8.6726 | 11.3452 | 16.0178 | 1.1151 | 6.5575 | 3.1151 | 2.1151 | 2.6826 | 4.6726 | 6.5575 | 8.6726 | 11.3552 | 16.0278 | 0.01
5.9719 | 8.986 | 7.9719 | 6.9719 | 9.9579 | 11.9579 | 8.986 | 15.9579 | 25.9158 | 37.8737 | 5.9719 | 8.986 | 7.9719 | 6.9719 | 9.9679 | 11.9579 | 8.986 | 15.9579 | 25.9258 | 37.8837 | 0.01
6.5507 | 9.2754 | 8.5507 | 7.5507 | 10.8261 | 12.8261 | 9.2754 | 16.8261 | 27.6521 | 40.4782 | 6.5507 | 9.2754 | 8.5507 | 7.5507 | 10.8361 | 12.8261 | 9.2754 | 16.8261 | 27.6621 | 40.4882 | 0.01
4.8226 | 8.4113 | 6.8226 | 5.8226 | 8.2338 | 10.2338 | 8.4113 | 14.2338 | 22.4677 | 32.7015 | 4.8226 | 8.4113 | 6.8226 | 5.8226 | 8.2438 | 10.2338 | 8.4113 | 14.2338 | 22.4777 | 32.7115 | 0.01
6.1037 | 9.0519 | 8.1037 | 7.1037 | 10.1556 | 12.1556 | 9.0519 | 16.1556 | 26.3111 | 38.4667 | 6.1037 | 9.0519 | 8.1037 | 7.1037 | 10.1656 | 12.1556 | 9.0519 | 16.1556 | 26.3211 | 38.4767 | 0.01
6.9292 | 9.4646 | 8.9292 | 7.9292 | 11.3937 | 13.3937 | 9.4646 | 17.3937 | 28.7875 | 42.1812 | 6.9292 | 9.4646 | 8.9292 | 7.9292 | 11.4037 | 13.3937 | 9.4646 | 17.3937 | 28.7975 | 42.1912 | 0.01
3.7038 | 7.8519 | 5.7038 | 4.7038 | 6.5557 | 8.5557 | 7.8519 | 12.5557 | 19.1113 | 27.667 | 3.7038 | 7.8519 | 5.7038 | 4.7038 | 6.5657 | 8.5557 | 7.8519 | 12.5557 | 19.1213 | 27.677 | 0.01
7.5671 | 9.7836 | 9.5671 | 8.5671 | 12.3507 | 14.3507 | 9.7836 | 18.3507 | 30.7013 | 45.052 | 7.5671 | 9.7836 | 9.5671 | 8.5671 | 12.3607 | 14.3507 | 9.7836 | 18.3507 | 30.7113 | 45.062 | 0.01
2.3254 | 7.1627 | 4.3254 | 3.3254 | 4.4881 | 6.4881 | 7.1627 | 10.4881 | 14.9762 | 21.4642 | 2.3254 | 7.1627 | 4.3254 | 3.3254 | 4.4981 | 6.4881 | 7.1627 | 10.4881 | 14.9862 | 21.4742 | 0.01
5.8236 | 8.9118 | 7.8236 | 6.8236 | 9.7354 | 11.7354 | 8.9118 | 15.7354 | 25.4708 | 37.2062 | 5.8236 | 8.9118 | 7.8236 | 6.8236 | 9.7454 | 11.7354 | 8.9118 | 15.7354 | 25.4808 | 37.2162 | 0.01
6.3687 | 9.1844 | 8.3687 | 7.3687 | 10.5531 | 12.5531 | 9.1844 | 16.5531 | 27.1062 | 39.6593 | 6.3687 | 9.1844 | 8.3687 | 7.3687 | 10.5631 | 12.5531 | 9.1844 | 16.5531 | 27.1162 | 39.6693 | 0.01
7.032 | 9.516 | 9.032 | 8.032 | 11.548 | 13.548 | 9.516 | 17.548 | 29.096 | 42.644 | 7.032 | 9.516 | 9.032 | 8.032 | 11.558 | 13.548 | 9.516 | 17.548 | 29.106 | 42.654 | 0.01
5.9999 | 9 | 7.9999 | 6.9999 | 9.9999 | 11.9999 | 9 | 15.9999 | 25.9998 | 37.9997 | 5.9999 | 9 | 7.9999 | 6.9999 | 10.0099 | 11.9999 | 9 | 15.9999 | 26.0098 | 38.0097 | 0.01
6.0206 | 9.0103 | 8.0206 | 7.0206 | 10.0309 | 12.0309 | 9.0103 | 16.0309 | 26.0617 | 38.0926 | 6.0206 | 9.0103 | 8.0206 | 7.0206 | 10.0409 | 12.0309 | 9.0103 | 16.0309 | 26.0717 | 38.1026 | 0.01
9.147 | 10.5735 | 11.147 | 10.147 | 14.7205 | 16.7205 | 10.5735 | 20.7205 | 35.441 | 52.1614 | 9.147 | 10.5735 | 11.147 | 10.147 | 14.7305 | 16.7205 | 10.5735 | 20.7205 | 35.451 | 52.1714 | 0.01
7.1056 | 9.5528 | 9.1056 | 8.1056 | 11.6584 | 13.6584 | 9.5528 | 17.6584 | 29.3168 | 42.9752 | 7.1056 | 9.5528 | 9.1056 | 8.1056 | 11.6684 | 13.6584 | 9.5528 | 17.6584 | 29.3268 | 42.9852 | 0.01
[8 empty] | Average | 37.4427 | [8 empty] | Average |  | 100%

## test activity F
A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | diff
1.4288 | 6.7144 | 3.4288 | 2.4288 | 3.1433 | 5.1433 | 6.7144 | 9.1433 | 12.2865 | 17.4298 | 1.4288 | 6.7144 | 3.4288 | 2.4288 | 3.1433 | 5.1533 | 6.7144 | 9.1433 | 12.2865 | 17.4398 | 0.01
2.4295 | 7.2148 | 4.4295 | 3.4295 | 4.6443 | 6.6443 | 7.2148 | 10.6443 | 15.2885 | 21.9328 | 2.4295 | 7.2148 | 4.4295 | 3.4295 | 4.6443 | 6.6543 | 7.2148 | 10.6443 | 15.2885 | 21.9428 | 0.01
4.0538 | 8.0269 | 6.0538 | 5.0538 | 7.0808 | 9.0808 | 8.0269 | 13.0808 | 20.1615 | 29.2423 | 4.0538 | 8.0269 | 6.0538 | 5.0538 | 7.0808 | 9.0908 | 8.0269 | 13.0808 | 20.1615 | 29.2523 | 0.01
6.049 | 9.0245 | 8.049 | 7.049 | 10.0736 | 12.0736 | 9.0245 | 16.0736 | 26.1471 | 38.2207 | 6.049 | 9.0245 | 8.049 | 7.049 | 10.0736 | 12.0836 | 9.0245 | 16.0736 | 26.1471 | 38.2307 | 0.01
7.3353 | 9.6677 | 9.3353 | 8.3353 | 12.003 | 14.003 | 9.6677 | 18.003 | 30.006 | 44.009 | 7.3353 | 9.6677 | 9.3353 | 8.3353 | 12.003 | 14.013 | 9.6677 | 18.003 | 30.006 | 44.019 | 0.01
5.1939 | 8.5969 | 7.1939 | 6.1939 | 8.7908 | 10.7908 | 8.5969 | 14.7908 | 23.5817 | 34.3725 | 5.1939 | 8.5969 | 7.1939 | 6.1939 | 8.7908 | 10.8008 | 8.5969 | 14.7908 | 23.5817 | 34.3825 | 0.01
7.3727 | 9.6863 | 9.3727 | 8.3727 | 12.059 | 14.059 | 9.6863 | 18.059 | 30.118 | 44.1769 | 7.3727 | 9.6863 | 9.3727 | 8.3727 | 12.059 | 14.069 | 9.6863 | 18.059 | 30.118 | 44.1869 | 0.01
2.7474 | 7.3737 | 4.7474 | 3.7474 | 5.1211 | 7.1211 | 7.3737 | 11.1211 | 16.2422 | 23.3633 | 2.7474 | 7.3737 | 4.7474 | 3.7474 | 5.1211 | 7.1311 | 7.3737 | 11.1211 | 16.2422 | 23.3733 | 0.01
7.0969 | 9.5484 | 9.0969 | 8.0969 | 11.6453 | 13.6453 | 9.5484 | 17.6453 | 29.2906 | 42.9359 | 7.0969 | 9.5484 | 9.0969 | 8.0969 | 11.6453 | 13.6553 | 9.5484 | 17.6453 | 29.2906 | 42.9459 | 0.01
4.1058 | 8.0529 | 6.1058 | 5.1058 | 7.1586 | 9.1586 | 8.0529 | 13.1586 | 20.3173 | 29.4759 | 4.1058 | 8.0529 | 6.1058 | 5.1058 | 7.1586 | 9.1686 | 8.0529 | 13.1586 | 20.3173 | 29.4859 | 0.01
7.2091 | 9.6045 | 9.2091 | 8.2091 | 11.8136 | 13.8136 | 9.6045 | 17.8136 | 29.6272 | 43.4408 | 7.2091 | 9.6045 | 9.2091 | 8.2091 | 11.8136 | 13.8236 | 9.6045 | 17.8136 | 29.6272 | 43.4508 | 0.01
10.8182 | 11.4091 | 12.8182 | 11.8182 | 17.2273 | 19.2273 | 11.4091 | 23.2273 | 40.4546 | 59.682 | 10.8182 | 11.4091 | 12.8182 | 11.8182 | 17.2273 | 19.2373 | 11.4091 | 23.2273 | 40.4546 | 59.692 | 0.01
6.4931 | 9.2465 | 8.4931 | 7.4931 | 10.7396 | 12.7396 | 9.2465 | 16.7396 | 27.4793 | 40.2189 | 6.4931 | 9.2465 | 8.4931 | 7.4931 | 10.7396 | 12.7496 | 9.2465 | 16.7396 | 27.4793 | 40.2289 | 0.01
6.0198 | 9.0099 | 8.0198 | 7.0198 | 10.0297 | 12.0297 | 9.0099 | 16.0297 | 26.0594 | 38.0892 | 6.0198 | 9.0099 | 8.0198 | 7.0198 | 10.0297 | 12.0397 | 9.0099 | 16.0297 | 26.0594 | 38.0992 | 0.01
5.2393 | 8.6197 | 7.2393 | 6.2393 | 8.859 | 10.859 | 8.6197 | 14.859 | 23.718 | 34.577 | 5.2393 | 8.6197 | 7.2393 | 6.2393 | 8.859 | 10.869 | 8.6197 | 14.859 | 23.718 | 34.587 | 0.01
5.4805 | 8.7403 | 7.4805 | 6.4805 | 9.2208 | 11.2208 | 8.7403 | 15.2208 | 24.4416 | 35.6624 | 5.4805 | 8.7403 | 7.4805 | 6.4805 | 9.2208 | 11.2308 | 8.7403 | 15.2208 | 24.4416 | 35.6724 | 0.01
3.5992 | 7.7996 | 5.5992 | 4.5992 | 6.3988 | 8.3988 | 7.7996 | 12.3988 | 18.7976 | 27.1965 | 3.5992 | 7.7996 | 5.5992 | 4.5992 | 6.3988 | 8.4088 | 7.7996 | 12.3988 | 18.7976 | 27.2065 | 0.01
2.2806 | 7.1403 | 4.2806 | 3.2806 | 4.4209 | 6.4209 | 7.1403 | 10.4209 | 14.8419 | 21.2628 | 2.2806 | 7.1403 | 4.2806 | 3.2806 | 4.4209 | 6.4309 | 7.1403 | 10.4209 | 14.8419 | 21.2728 | 0.01
6.9264 | 9.4632 | 8.9264 | 7.9264 | 11.3897 | 13.3897 | 9.4632 | 17.3897 | 28.7793 | 42.169 | 6.9264 | 9.4632 | 8.9264 | 7.9264 | 11.3897 | 13.3997 | 9.4632 | 17.3897 | 28.7793 | 42.179 | 0.01
4.5848 | 8.2924 | 6.5848 | 5.5848 | 7.8772 | 9.8772 | 8.2924 | 13.8772 | 21.7545 | 31.6317 | 4.5848 | 8.2924 | 6.5848 | 5.5848 | 7.8772 | 9.8872 | 8.2924 | 13.8772 | 21.7545 | 31.6417 | 0.01
5.8871 | 8.9436 | 7.8871 | 6.8871 | 9.8307 | 11.8307 | 8.9436 | 15.8307 | 25.6613 | 37.492 | 5.8871 | 8.9436 | 7.8871 | 6.8871 | 9.8307 | 11.8407 | 8.9436 | 15.8307 | 25.6613 | 37.502 | 0.01
4.4375 | 8.2187 | 6.4375 | 5.4375 | 7.6562 | 9.6562 | 8.2187 | 13.6562 | 21.3124 | 30.9686 | 4.4375 | 8.2187 | 6.4375 | 5.4375 | 7.6562 | 9.6662 | 8.2187 | 13.6562 | 21.3124 | 30.9786 | 0.01
5.9122 | 8.9561 | 7.9122 | 6.9122 | 9.8683 | 11.8683 | 8.9561 | 15.8683 | 25.7367 | 37.605 | 5.9122 | 8.9561 | 7.9122 | 6.9122 | 9.8683 | 11.8783 | 8.9561 | 15.8683 | 25.7367 | 37.615 | 0.01
4.2985 | 8.1493 | 6.2985 | 5.2985 | 7.4478 | 9.4478 | 8.1493 | 13.4478 | 20.8955 | 30.3433 | 4.2985 | 8.1493 | 6.2985 | 5.2985 | 7.4478 | 9.4578 | 8.1493 | 13.4478 | 20.8955 | 30.3533 | 0.01
3.7284 | 7.8642 | 5.7284 | 4.7284 | 6.5927 | 8.5927 | 7.8642 | 12.5927 | 19.1853 | 27.778 | 3.7284 | 7.8642 | 5.7284 | 4.7284 | 6.5927 | 8.6027 | 7.8642 | 12.5927 | 19.1853 | 27.788 | 0.01
7.6067 | 9.8034 | 9.6067 | 8.6067 | 12.4101 | 14.4101 | 9.8034 | 18.4101 | 30.8202 | 45.2303 | 7.6067 | 9.8034 | 9.6067 | 8.6067 | 12.4101 | 14.4201 | 9.8034 | 18.4101 | 30.8202 | 45.2403 | 0.01
8.6808 | 10.3404 | 10.6808 | 9.6808 | 14.0212 | 16.0212 | 10.3404 | 20.0212 | 34.0423 | 50.0635 | 8.6808 | 10.3404 | 10.6808 | 9.6808 | 14.0212 | 16.0312 | 10.3404 | 20.0212 | 34.0423 | 50.0735 | 0.01
5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8393 | 8.6098 | 14.8293 | 23.6587 | 34.498 | 0.01
7.6331 | 9.8165 | 9.6331 | 8.6331 | 12.4496 | 14.4496 | 9.8165 | 18.4496 | 30.8992 | 45.3488 | 7.6331 | 9.8165 | 9.6331 | 8.6331 | 12.4496 | 14.4596 | 9.8165 | 18.4496 | 30.8992 | 45.3588 | 0.01
4.2833 | 8.1416 | 6.2833 | 5.2833 | 7.4249 | 9.4249 | 8.1416 | 13.4249 | 20.8499 | 30.2748 | 4.2833 | 8.1416 | 6.2833 | 5.2833 | 7.4249 | 9.4349 | 8.1416 | 13.4249 | 20.8499 | 30.2848 | 0.01
4.5407 | 8.2703 | 6.5407 | 5.5407 | 7.811 | 9.811 | 8.2703 | 13.811 | 21.622 | 31.433 | 4.5407 | 8.2703 | 6.5407 | 5.5407 | 7.811 | 9.821 | 8.2703 | 13.811 | 21.622 | 31.443 | 0.01
6.1115 | 9.0558 | 8.1115 | 7.1115 | 10.1673 | 12.1673 | 9.0558 | 16.1673 | 26.3345 | 38.5018 | 6.1115 | 9.0558 | 8.1115 | 7.1115 | 10.1673 | 12.1773 | 9.0558 | 16.1673 | 26.3345 | 38.5118 | 0.01
6.1999 | 9.1 | 8.1999 | 7.1999 | 10.2999 | 12.2999 | 9.1 | 16.2999 | 26.5997 | 38.8996 | 6.1999 | 9.1 | 8.1999 | 7.1999 | 10.2999 | 12.3099 | 9.1 | 16.2999 | 26.5997 | 38.9096 | 0.01
2.8161 | 7.408 | 4.8161 | 3.8161 | 5.2241 | 7.2241 | 7.408 | 11.2241 | 16.4482 | 23.6723 | 2.8161 | 7.408 | 4.8161 | 3.8161 | 5.2241 | 7.2341 | 7.408 | 11.2241 | 16.4482 | 23.6823 | 0.01
6.6314 | 9.3157 | 8.6314 | 7.6314 | 10.9471 | 12.9471 | 9.3157 | 16.9471 | 27.8943 | 40.8414 | 6.6314 | 9.3157 | 8.6314 | 7.6314 | 10.9471 | 12.9571 | 9.3157 | 16.9471 | 27.8943 | 40.8514 | 0.01
6.5394 | 9.2697 | 8.5394 | 7.5394 | 10.8092 | 12.8092 | 9.2697 | 16.8092 | 27.6183 | 40.4275 | 6.5394 | 9.2697 | 8.5394 | 7.5394 | 10.8092 | 12.8192 | 9.2697 | 16.8092 | 27.6183 | 40.4375 | 0.01
11.0521 | 11.526 | 13.0521 | 12.0521 | 17.5781 | 19.5781 | 11.526 | 23.5781 | 41.1562 | 60.7343 | 11.0521 | 11.526 | 13.0521 | 12.0521 | 17.5781 | 19.5881 | 11.526 | 23.5781 | 41.1562 | 60.7443 | 0.01
3.8102 | 7.9051 | 5.8102 | 4.8102 | 6.7153 | 8.7153 | 7.9051 | 12.7153 | 19.4307 | 28.146 | 3.8102 | 7.9051 | 5.8102 | 4.8102 | 6.7153 | 8.7253 | 7.9051 | 12.7153 | 19.4307 | 28.156 | 0.01
5.2518 | 8.6259 | 7.2518 | 6.2518 | 8.8777 | 10.8777 | 8.6259 | 14.8777 | 23.7554 | 34.6332 | 5.2518 | 8.6259 | 7.2518 | 6.2518 | 8.8777 | 10.8877 | 8.6259 | 14.8777 | 23.7554 | 34.6432 | 0.01
6.3771 | 9.1886 | 8.3771 | 7.3771 | 10.5657 | 12.5657 | 9.1886 | 16.5657 | 27.1314 | 39.6971 | 6.3771 | 9.1886 | 8.3771 | 7.3771 | 10.5657 | 12.5757 | 9.1886 | 16.5657 | 27.1314 | 39.7071 | 0.01
5.3383 | 8.6691 | 7.3383 | 6.3383 | 9.0074 | 11.0074 | 8.6691 | 15.0074 | 24.0148 | 35.0222 | 5.3383 | 8.6691 | 7.3383 | 6.3383 | 9.0074 | 11.0174 | 8.6691 | 15.0074 | 24.0148 | 35.0322 | 0.01
8.3948 | 10.1974 | 10.3948 | 9.3948 | 13.5922 | 15.5922 | 10.1974 | 19.5922 | 33.1845 | 48.7767 | 8.3948 | 10.1974 | 10.3948 | 9.3948 | 13.5922 | 15.6022 | 10.1974 | 19.5922 | 33.1845 | 48.7867 | 0.01
5.0712 | 8.5356 | 7.0712 | 6.0712 | 8.6068 | 10.6068 | 8.5356 | 14.6068 | 23.2135 | 33.8203 | 5.0712 | 8.5356 | 7.0712 | 6.0712 | 8.6068 | 10.6168 | 8.5356 | 14.6068 | 23.2135 | 33.8303 | 0.01
6.1543 | 9.0771 | 8.1543 | 7.1543 | 10.2314 | 12.2314 | 9.0771 | 16.2314 | 26.4629 | 38.6943 | 6.1543 | 9.0771 | 8.1543 | 7.1543 | 10.2314 | 12.2414 | 9.0771 | 16.2314 | 26.4629 | 38.7043 | 0.01
5.863 | 8.9315 | 7.863 | 6.863 | 9.7946 | 11.7946 | 8.9315 | 15.7946 | 25.5891 | 37.3837 | 5.863 | 8.9315 | 7.863 | 6.863 | 9.7946 | 11.8046 | 8.9315 | 15.7946 | 25.5891 | 37.3937 | 0.01
2.5835 | 7.2917 | 4.5835 | 3.5835 | 4.8752 | 6.8752 | 7.2917 | 10.8752 | 15.7504 | 22.6257 | 2.5835 | 7.2917 | 4.5835 | 3.5835 | 4.8752 | 6.8852 | 7.2917 | 10.8752 | 15.7504 | 22.6357 | 0.01
5.0249 | 8.5125 | 7.0249 | 6.0249 | 8.5374 | 10.5374 | 8.5125 | 14.5374 | 23.0747 | 33.6121 | 5.0249 | 8.5125 | 7.0249 | 6.0249 | 8.5374 | 10.5474 | 8.5125 | 14.5374 | 23.0747 | 33.6221 | 0.01
6.1918 | 9.0959 | 8.1918 | 7.1918 | 10.2877 | 12.2877 | 9.0959 | 16.2877 | 26.5753 | 38.863 | 6.1918 | 9.0959 | 8.1918 | 7.1918 | 10.2877 | 12.2977 | 9.0959 | 16.2877 | 26.5753 | 38.873 | 0.01
5.0897 | 8.5449 | 7.0897 | 6.0897 | 8.6346 | 10.6346 | 8.5449 | 14.6346 | 23.2691 | 33.9037 | 5.0897 | 8.5449 | 7.0897 | 6.0897 | 8.6346 | 10.6446 | 8.5449 | 14.6346 | 23.2691 | 33.9137 | 0.01
5.4889 | 8.7445 | 7.4889 | 6.4889 | 9.2334 | 11.2334 | 8.7445 | 15.2334 | 24.4667 | 35.7001 | 5.4889 | 8.7445 | 7.4889 | 6.4889 | 9.2334 | 11.2434 | 8.7445 | 15.2334 | 24.4667 | 35.7101 | 0.01
8.7445 | 10.3722 | 10.7445 | 9.7445 | 14.1167 | 16.1167 | 10.3722 | 20.1167 | 34.2334 | 50.3502 | 8.7445 | 10.3722 | 10.7445 | 9.7445 | 14.1167 | 16.1267 | 10.3722 | 20.1167 | 34.2334 | 50.3602 | 0.01
6.1328 | 9.0664 | 8.1328 | 7.1328 | 10.1992 | 12.1992 | 9.0664 | 16.1992 | 26.3985 | 38.5977 | 6.1328 | 9.0664 | 8.1328 | 7.1328 | 10.1992 | 12.2092 | 9.0664 | 16.1992 | 26.3985 | 38.6077 | 0.01
6.4019 | 9.201 | 8.4019 | 7.4019 | 10.6029 | 12.6029 | 9.201 | 16.6029 | 27.2058 | 39.8087 | 6.4019 | 9.201 | 8.4019 | 7.4019 | 10.6029 | 12.6129 | 9.201 | 16.6029 | 27.2058 | 39.8187 | 0.01
4.0371 | 8.0185 | 6.0371 | 5.0371 | 7.0556 | 9.0556 | 8.0185 | 13.0556 | 20.1112 | 29.1668 | 4.0371 | 8.0185 | 6.0371 | 5.0371 | 7.0556 | 9.0656 | 8.0185 | 13.0556 | 20.1112 | 29.1768 | 0.01
5.83 | 8.915 | 7.83 | 6.83 | 9.7451 | 11.7451 | 8.915 | 15.7451 | 25.4901 | 37.2352 | 5.83 | 8.915 | 7.83 | 6.83 | 9.7451 | 11.7551 | 8.915 | 15.7451 | 25.4901 | 37.2452 | 0.01
2.6753 | 7.3376 | 4.6753 | 3.6753 | 5.0129 | 7.0129 | 7.3376 | 11.0129 | 16.0258 | 23.0387 | 2.6753 | 7.3376 | 4.6753 | 3.6753 | 5.0129 | 7.0229 | 7.3376 | 11.0129 | 16.0258 | 23.0487 | 0.01
5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0438 | 8.6779 | 15.0338 | 24.0676 | 35.1113 | 0.01
2.6862 | 7.3431 | 4.6862 | 3.6862 | 5.0293 | 7.0293 | 7.3431 | 11.0293 | 16.0585 | 23.0878 | 2.6862 | 7.3431 | 4.6862 | 3.6862 | 5.0293 | 7.0393 | 7.3431 | 11.0293 | 16.0585 | 23.0978 | 0.01
9.7341 | 10.8671 | 11.7341 | 10.7341 | 15.6012 | 17.6012 | 10.8671 | 21.6012 | 37.2024 | 54.8037 | 9.7341 | 10.8671 | 11.7341 | 10.7341 | 15.6012 | 17.6112 | 10.8671 | 21.6012 | 37.2024 | 54.8137 | 0.01
4.1077 | 8.0538 | 6.1077 | 5.1077 | 7.1615 | 9.1615 | 8.0538 | 13.1615 | 20.323 | 29.4845 | 4.1077 | 8.0538 | 6.1077 | 5.1077 | 7.1615 | 9.1715 | 8.0538 | 13.1615 | 20.323 | 29.4945 | 0.01
7.484 | 9.742 | 9.484 | 8.484 | 12.226 | 14.226 | 9.742 | 18.226 | 30.452 | 44.6781 | 7.484 | 9.742 | 9.484 | 8.484 | 12.226 | 14.236 | 9.742 | 18.226 | 30.452 | 44.6881 | 0.01
6.2666 | 9.1333 | 8.2666 | 7.2666 | 10.3999 | 12.3999 | 9.1333 | 16.3999 | 26.7999 | 39.1998 | 6.2666 | 9.1333 | 8.2666 | 7.2666 | 10.3999 | 12.4099 | 9.1333 | 16.3999 | 26.7999 | 39.2098 | 0.01
5.2959 | 8.648 | 7.2959 | 6.2959 | 8.9439 | 10.9439 | 8.648 | 14.9439 | 23.8878 | 34.8317 | 5.2959 | 8.648 | 7.2959 | 6.2959 | 8.9439 | 10.9539 | 8.648 | 14.9439 | 23.8878 | 34.8417 | 0.01
4.8999 | 8.45 | 6.8999 | 5.8999 | 8.3499 | 10.3499 | 8.45 | 14.3499 | 22.6998 | 33.0497 | 4.8999 | 8.45 | 6.8999 | 5.8999 | 8.3499 | 10.3599 | 8.45 | 14.3499 | 22.6998 | 33.0597 | 0.01
5.8151 | 8.9076 | 7.8151 | 6.8151 | 9.7227 | 11.7227 | 8.9076 | 15.7227 | 25.4454 | 37.1682 | 5.8151 | 8.9076 | 7.8151 | 6.8151 | 9.7227 | 11.7327 | 8.9076 | 15.7227 | 25.4454 | 37.1782 | 0.01
5.9292 | 8.9646 | 7.9292 | 6.9292 | 9.8938 | 11.8938 | 8.9646 | 15.8938 | 25.7877 | 37.6815 | 5.9292 | 8.9646 | 7.9292 | 6.9292 | 9.8938 | 11.9038 | 8.9646 | 15.8938 | 25.7877 | 37.6915 | 0.01
2.9022 | 7.4511 | 4.9022 | 3.9022 | 5.3533 | 7.3533 | 7.4511 | 11.3533 | 16.7065 | 24.0598 | 2.9022 | 7.4511 | 4.9022 | 3.9022 | 5.3533 | 7.3633 | 7.4511 | 11.3533 | 16.7065 | 24.0698 | 0.01
3.7424 | 7.8712 | 5.7424 | 4.7424 | 6.6136 | 8.6136 | 7.8712 | 12.6136 | 19.2272 | 27.8407 | 3.7424 | 7.8712 | 5.7424 | 4.7424 | 6.6136 | 8.6236 | 7.8712 | 12.6136 | 19.2272 | 27.8507 | 0.01
8.3173 | 10.1587 | 10.3173 | 9.3173 | 13.476 | 15.476 | 10.1587 | 19.476 | 32.952 | 48.4281 | 8.3173 | 10.1587 | 10.3173 | 9.3173 | 13.476 | 15.486 | 10.1587 | 19.476 | 32.952 | 48.4381 | 0.01
4.7975 | 8.3988 | 6.7975 | 5.7975 | 8.1963 | 10.1963 | 8.3988 | 14.1963 | 22.3926 | 32.5889 | 4.7975 | 8.3988 | 6.7975 | 5.7975 | 8.1963 | 10.2063 | 8.3988 | 14.1963 | 22.3926 | 32.5989 | 0.01
4.0727 | 8.0363 | 6.0727 | 5.0727 | 7.109 | 9.109 | 8.0363 | 13.109 | 20.218 | 29.327 | 4.0727 | 8.0363 | 6.0727 | 5.0727 | 7.109 | 9.119 | 8.0363 | 13.109 | 20.218 | 29.337 | 0.01
7.2028 | 9.6014 | 9.2028 | 8.2028 | 11.8042 | 13.8042 | 9.6014 | 17.8042 | 29.6085 | 43.4127 | 7.2028 | 9.6014 | 9.2028 | 8.2028 | 11.8042 | 13.8142 | 9.6014 | 17.8042 | 29.6085 | 43.4227 | 0.01
5.1967 | 8.5984 | 7.1967 | 6.1967 | 8.7951 | 10.7951 | 8.5984 | 14.7951 | 23.5902 | 34.3852 | 5.1967 | 8.5984 | 7.1967 | 6.1967 | 8.7951 | 10.8051 | 8.5984 | 14.7951 | 23.5902 | 34.3952 | 0.01
3.0576 | 7.5288 | 5.0576 | 4.0576 | 5.5864 | 7.5864 | 7.5288 | 11.5864 | 17.1729 | 24.7593 | 3.0576 | 7.5288 | 5.0576 | 4.0576 | 5.5864 | 7.5964 | 7.5288 | 11.5864 | 17.1729 | 24.7693 | 0.01
4.772 | 8.386 | 6.772 | 5.772 | 8.1579 | 10.1579 | 8.386 | 14.1579 | 22.3159 | 32.4738 | 4.772 | 8.386 | 6.772 | 5.772 | 8.1579 | 10.1679 | 8.386 | 14.1579 | 22.3159 | 32.4838 | 0.01
6.9343 | 9.4671 | 8.9343 | 7.9343 | 11.4014 | 13.4014 | 9.4671 | 17.4014 | 28.8028 | 42.2043 | 6.9343 | 9.4671 | 8.9343 | 7.9343 | 11.4014 | 13.4114 | 9.4671 | 17.4014 | 28.8028 | 42.2143 | 0.01
5.9782 | 8.9891 | 7.9782 | 6.9782 | 9.9673 | 11.9673 | 8.9891 | 15.9673 | 25.9346 | 37.9019 | 5.9782 | 8.9891 | 7.9782 | 6.9782 | 9.9673 | 11.9773 | 8.9891 | 15.9673 | 25.9346 | 37.9119 | 0.01
4.3539 | 8.1769 | 6.3539 | 5.3539 | 7.5308 | 9.5308 | 8.1769 | 13.5308 | 21.0616 | 30.5925 | 4.3539 | 8.1769 | 6.3539 | 5.3539 | 7.5308 | 9.5408 | 8.1769 | 13.5308 | 21.0616 | 30.6025 | 0.01
4.4273 | 8.2136 | 6.4273 | 5.4273 | 7.6409 | 9.6409 | 8.2136 | 13.6409 | 21.2818 | 30.9227 | 4.4273 | 8.2136 | 6.4273 | 5.4273 | 7.6409 | 9.6509 | 8.2136 | 13.6409 | 21.2818 | 30.9327 | 0.01
5.6648 | 8.8324 | 7.6648 | 6.6648 | 9.4972 | 11.4972 | 8.8324 | 15.4972 | 24.9945 | 36.4917 | 5.6648 | 8.8324 | 7.6648 | 6.6648 | 9.4972 | 11.5072 | 8.8324 | 15.4972 | 24.9945 | 36.5017 | 0.01
6.1502 | 9.0751 | 8.1502 | 7.1502 | 10.2252 | 12.2252 | 9.0751 | 16.2252 | 26.4505 | 38.6757 | 6.1502 | 9.0751 | 8.1502 | 7.1502 | 10.2252 | 12.2352 | 9.0751 | 16.2252 | 26.4505 | 38.6857 | 0.01
13.0455 | 12.5227 | 15.0455 | 14.0455 | 20.5682 | 22.5682 | 13.0455 | 27.0909 | 47.6591 | 70.2273 | 13.0455 | 12.5227 | 15.0455 | 14.0455 | 20.5682 | 22.5782 | 13.0455 | 27.0909 | 47.6591 | 70.2373 | 0.01
7.6173 | 9.8087 | 9.6173 | 8.6173 | 12.426 | 14.426 | 9.8087 | 18.426 | 30.8519 | 45.2779 | 7.6173 | 9.8087 | 9.6173 | 8.6173 | 12.426 | 14.436 | 9.8087 | 18.426 | 30.8519 | 45.2879 | 0.01
8.3774 | 10.1887 | 10.3774 | 9.3774 | 13.566 | 15.566 | 10.1887 | 19.566 | 33.1321 | 48.6981 | 8.3774 | 10.1887 | 10.3774 | 9.3774 | 13.566 | 15.576 | 10.1887 | 19.566 | 33.1321 | 48.7081 | 0.01
6.074 | 9.037 | 8.074 | 7.074 | 10.111 | 12.111 | 9.037 | 16.111 | 26.222 | 38.333 | 6.074 | 9.037 | 8.074 | 7.074 | 10.111 | 12.121 | 9.037 | 16.111 | 26.222 | 38.343 | 0.01
5.9353 | 8.9677 | 7.9353 | 6.9353 | 9.903 | 11.903 | 8.9677 | 15.903 | 25.806 | 37.7091 | 5.9353 | 8.9677 | 7.9353 | 6.9353 | 9.903 | 11.913 | 8.9677 | 15.903 | 25.806 | 37.7191 | 0.01
6.9629 | 9.4814 | 8.9629 | 7.9629 | 11.4443 | 13.4443 | 9.4814 | 17.4443 | 28.8886 | 42.3329 | 6.9629 | 9.4814 | 8.9629 | 7.9629 | 11.4443 | 13.4543 | 9.4814 | 17.4443 | 28.8886 | 42.3429 | 0.01
3.2723 | 7.6361 | 5.2723 | 4.2723 | 5.9084 | 7.9084 | 7.6361 | 11.9084 | 17.8169 | 25.7253 | 3.2723 | 7.6361 | 5.2723 | 4.2723 | 5.9084 | 7.9184 | 7.6361 | 11.9084 | 17.8169 | 25.7353 | 0.01
5.3875 | 8.6938 | 7.3875 | 6.3875 | 9.0813 | 11.0813 | 8.6938 | 15.0813 | 24.1626 | 35.2438 | 5.3875 | 8.6938 | 7.3875 | 6.3875 | 9.0813 | 11.0913 | 8.6938 | 15.0813 | 24.1626 | 35.2538 | 0.01
2.8991 | 7.4496 | 4.8991 | 3.8991 | 5.3487 | 7.3487 | 7.4496 | 11.3487 | 16.6974 | 24.0461 | 2.8991 | 7.4496 | 4.8991 | 3.8991 | 5.3487 | 7.3587 | 7.4496 | 11.3487 | 16.6974 | 24.0561 | 0.01
6.8927 | 9.4463 | 8.8927 | 7.8927 | 11.339 | 13.339 | 9.4463 | 17.339 | 28.678 | 42.017 | 6.8927 | 9.4463 | 8.8927 | 7.8927 | 11.339 | 13.349 | 9.4463 | 17.339 | 28.678 | 42.027 | 0.01
5.2946 | 8.6473 | 7.2946 | 6.2946 | 8.942 | 10.942 | 8.6473 | 14.942 | 23.8839 | 34.8259 | 5.2946 | 8.6473 | 7.2946 | 6.2946 | 8.942 | 10.952 | 8.6473 | 14.942 | 23.8839 | 34.8359 | 0.01
7.3723 | 9.6861 | 9.3723 | 8.3723 | 12.0584 | 14.0584 | 9.6861 | 18.0584 | 30.1168 | 44.1752 | 7.3723 | 9.6861 | 9.3723 | 8.3723 | 12.0584 | 14.0684 | 9.6861 | 18.0584 | 30.1168 | 44.1852 | 0.01
6.4354 | 9.2177 | 8.4354 | 7.4354 | 10.6531 | 12.6531 | 9.2177 | 16.6531 | 27.3062 | 39.9593 | 6.4354 | 9.2177 | 8.4354 | 7.4354 | 10.6531 | 12.6631 | 9.2177 | 16.6531 | 27.3062 | 39.9693 | 0.01
5.4793 | 8.7396 | 7.4793 | 6.4793 | 9.2189 | 11.2189 | 8.7396 | 15.2189 | 24.4378 | 35.6567 | 5.4793 | 8.7396 | 7.4793 | 6.4793 | 9.2189 | 11.2289 | 8.7396 | 15.2189 | 24.4378 | 35.6667 | 0.01
6.2472 | 9.1236 | 8.2472 | 7.2472 | 10.3708 | 12.3708 | 9.1236 | 16.3708 | 26.7415 | 39.1123 | 6.2472 | 9.1236 | 8.2472 | 7.2472 | 10.3708 | 12.3808 | 9.1236 | 16.3708 | 26.7415 | 39.1223 | 0.01
4.9739 | 8.487 | 6.9739 | 5.9739 | 8.4609 | 10.4609 | 8.487 | 14.4609 | 22.9218 | 33.3827 | 4.9739 | 8.487 | 6.9739 | 5.9739 | 8.4609 | 10.4709 | 8.487 | 14.4609 | 22.9218 | 33.3927 | 0.01
1.3058 | 6.6529 | 3.3058 | 2.3058 | 2.9588 | 4.9588 | 6.6529 | 8.9588 | 11.9175 | 16.8763 | 1.3058 | 6.6529 | 3.3058 | 2.3058 | 2.9588 | 4.9688 | 6.6529 | 8.9588 | 11.9175 | 16.8863 | 0.01
6.9362 | 9.4681 | 8.9362 | 7.9362 | 11.4042 | 13.4042 | 9.4681 | 17.4042 | 28.8085 | 42.2127 | 6.9362 | 9.4681 | 8.9362 | 7.9362 | 11.4042 | 13.4142 | 9.4681 | 17.4042 | 28.8085 | 42.2227 | 0.01
7.1438 | 9.5719 | 9.1438 | 8.1438 | 11.7157 | 13.7157 | 9.5719 | 17.7157 | 29.4313 | 43.147 | 7.1438 | 9.5719 | 9.1438 | 8.1438 | 11.7157 | 13.7257 | 9.5719 | 17.7157 | 29.4313 | 43.157 | 0.01
7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8885 | 9.6262 | 17.8785 | 29.757 | 43.6455 | 0.01
10.4708 | 11.2354 | 12.4708 | 11.4708 | 16.7062 | 18.7062 | 11.2354 | 22.7062 | 39.4124 | 58.1185 | 10.4708 | 11.2354 | 12.4708 | 11.4708 | 16.7062 | 18.7162 | 11.2354 | 22.7062 | 39.4124 | 58.1285 | 0.01
7.3244 | 9.6622 | 9.3244 | 8.3244 | 11.9867 | 13.9867 | 9.6622 | 17.9867 | 29.9733 | 43.96 | 7.3244 | 9.6622 | 9.3244 | 8.3244 | 11.9867 | 13.9967 | 9.6622 | 17.9867 | 29.9733 | 43.97 | 0.01
3.4391 | 7.7195 | 5.4391 | 4.4391 | 6.1586 | 8.1586 | 7.7195 | 12.1586 | 18.3173 | 26.4759 | 3.4391 | 7.7195 | 5.4391 | 4.4391 | 6.1586 | 8.1686 | 7.7195 | 12.1586 | 18.3173 | 26.4859 | 0.01
3.4033 | 7.7016 | 5.4033 | 4.4033 | 6.1049 | 8.1049 | 7.7016 | 12.1049 | 18.2098 | 26.3146 | 3.4033 | 7.7016 | 5.4033 | 4.4033 | 6.1049 | 8.1149 | 7.7016 | 12.1049 | 18.2098 | 26.3246 | 0.01
6.3856 | 9.1928 | 8.3856 | 7.3856 | 10.5783 | 12.5783 | 9.1928 | 16.5783 | 27.1567 | 39.735 | 6.3856 | 9.1928 | 8.3856 | 7.3856 | 10.5783 | 12.5883 | 9.1928 | 16.5783 | 27.1567 | 39.745 | 0.01
4.8622 | 8.4311 | 6.8622 | 5.8622 | 8.2933 | 10.2933 | 8.4311 | 14.2933 | 22.5865 | 32.8798 | 4.8622 | 8.4311 | 6.8622 | 5.8622 | 8.2933 | 10.3033 | 8.4311 | 14.2933 | 22.5865 | 32.8898 | 0.01
6.2649 | 9.1325 | 8.2649 | 7.2649 | 10.3974 | 12.3974 | 9.1325 | 16.3974 | 26.7948 | 39.1921 | 6.2649 | 9.1325 | 8.2649 | 7.2649 | 10.3974 | 12.4074 | 9.1325 | 16.3974 | 26.7948 | 39.2021 | 0.01
6.3815 | 9.1908 | 8.3815 | 7.3815 | 10.5723 | 12.5723 | 9.1908 | 16.5723 | 27.1445 | 39.7168 | 6.3815 | 9.1908 | 8.3815 | 7.3815 | 10.5723 | 12.5823 | 9.1908 | 16.5723 | 27.1445 | 39.7268 | 0.01
6.0503 | 9.0251 | 8.0503 | 7.0503 | 10.0754 | 12.0754 | 9.0251 | 16.0754 | 26.1508 | 38.2262 | 6.0503 | 9.0251 | 8.0503 | 7.0503 | 10.0754 | 12.0854 | 9.0251 | 16.0754 | 26.1508 | 38.2362 | 0.01
7.3199 | 9.6599 | 9.3199 | 8.3199 | 11.9798 | 13.9798 | 9.6599 | 17.9798 | 29.9596 | 43.9394 | 7.3199 | 9.6599 | 9.3199 | 8.3199 | 11.9798 | 13.9898 | 9.6599 | 17.9798 | 29.9596 | 43.9494 | 0.01
4.8278 | 8.4139 | 6.8278 | 5.8278 | 8.2417 | 10.2417 | 8.4139 | 14.2417 | 22.4835 | 32.7252 | 4.8278 | 8.4139 | 6.8278 | 5.8278 | 8.2417 | 10.2517 | 8.4139 | 14.2417 | 22.4835 | 32.7352 | 0.01
5.4652 | 8.7326 | 7.4652 | 6.4652 | 9.1977 | 11.1977 | 8.7326 | 15.1977 | 24.3955 | 35.5932 | 5.4652 | 8.7326 | 7.4652 | 6.4652 | 9.1977 | 11.2077 | 8.7326 | 15.1977 | 24.3955 | 35.6032 | 0.01
3.3593 | 7.6796 | 5.3593 | 4.3593 | 6.0389 | 8.0389 | 7.6796 | 12.0389 | 18.0778 | 26.1167 | 3.3593 | 7.6796 | 5.3593 | 4.3593 | 6.0389 | 8.0489 | 7.6796 | 12.0389 | 18.0778 | 26.1267 | 0.01
7.5124 | 9.7562 | 9.5124 | 8.5124 | 12.2686 | 14.2686 | 9.7562 | 18.2686 | 30.5371 | 44.8057 | 7.5124 | 9.7562 | 9.5124 | 8.5124 | 12.2686 | 14.2786 | 9.7562 | 18.2686 | 30.5371 | 44.8157 | 0.01
3.9132 | 7.9566 | 5.9132 | 4.9132 | 6.8698 | 8.8698 | 7.9566 | 12.8698 | 19.7396 | 28.6094 | 3.9132 | 7.9566 | 5.9132 | 4.9132 | 6.8698 | 8.8798 | 7.9566 | 12.8698 | 19.7396 | 28.6194 | 0.01
1.5199 | 6.7599 | 3.5199 | 2.5199 | 3.2798 | 5.2798 | 6.7599 | 9.2798 | 12.5596 | 17.8394 | 1.5199 | 6.7599 | 3.5199 | 2.5199 | 3.2798 | 5.2898 | 6.7599 | 9.2798 | 12.5596 | 17.8494 | 0.01
4.6499 | 8.325 | 6.6499 | 5.6499 | 7.9749 | 9.9749 | 8.325 | 13.9749 | 21.9497 | 31.9246 | 4.6499 | 8.325 | 6.6499 | 5.6499 | 7.9749 | 9.9849 | 8.325 | 13.9749 | 21.9497 | 31.9346 | 0.01
4.3616 | 8.1808 | 6.3616 | 5.3616 | 7.5424 | 9.5424 | 8.1808 | 13.5424 | 21.0848 | 30.6272 | 4.3616 | 8.1808 | 6.3616 | 5.3616 | 7.5424 | 9.5524 | 8.1808 | 13.5424 | 21.0848 | 30.6372 | 0.01
5.2767 | 8.6383 | 7.2767 | 6.2767 | 8.915 | 10.915 | 8.6383 | 14.915 | 23.8301 | 34.7451 | 5.2767 | 8.6383 | 7.2767 | 6.2767 | 8.915 | 10.925 | 8.6383 | 14.915 | 23.8301 | 34.7551 | 0.01
4.6809 | 8.3404 | 6.6809 | 5.6809 | 8.0213 | 10.0213 | 8.3404 | 14.0213 | 22.0426 | 32.064 | 4.6809 | 8.3404 | 6.6809 | 5.6809 | 8.0213 | 10.0313 | 8.3404 | 14.0213 | 22.0426 | 32.074 | 0.01
7.3392 | 9.6696 | 9.3392 | 8.3392 | 12.0087 | 14.0087 | 9.6696 | 18.0087 | 30.0175 | 44.0262 | 7.3392 | 9.6696 | 9.3392 | 8.3392 | 12.0087 | 14.0187 | 9.6696 | 18.0087 | 30.0175 | 44.0362 | 0.01
5.9878 | 8.9939 | 7.9878 | 6.9878 | 9.9818 | 11.9818 | 8.9939 | 15.9818 | 25.9635 | 37.9453 | 5.9878 | 8.9939 | 7.9878 | 6.9878 | 9.9818 | 11.9918 | 8.9939 | 15.9818 | 25.9635 | 37.9553 | 0.01
7.2575 | 9.6288 | 9.2575 | 8.2575 | 11.8863 | 13.8863 | 9.6288 | 17.8863 | 29.7726 | 43.659 | 7.2575 | 9.6288 | 9.2575 | 8.2575 | 11.8863 | 13.8963 | 9.6288 | 17.8863 | 29.7726 | 43.669 | 0.01
6.2064 | 9.1032 | 8.2064 | 7.2064 | 10.3096 | 12.3096 | 9.1032 | 16.3096 | 26.6191 | 38.9287 | 6.2064 | 9.1032 | 8.2064 | 7.2064 | 10.3096 | 12.3196 | 9.1032 | 16.3096 | 26.6191 | 38.9387 | 0.01
3.8799 | 7.94 | 5.8799 | 4.8799 | 6.8199 | 8.8199 | 7.94 | 12.8199 | 19.6398 | 28.4598 | 3.8799 | 7.94 | 5.8799 | 4.8799 | 6.8199 | 8.8299 | 7.94 | 12.8199 | 19.6398 | 28.4698 | 0.01
2.4504 | 7.2252 | 4.4504 | 3.4504 | 4.6756 | 6.6756 | 7.2252 | 10.6756 | 15.3512 | 22.0267 | 2.4504 | 7.2252 | 4.4504 | 3.4504 | 4.6756 | 6.6856 | 7.2252 | 10.6756 | 15.3512 | 22.0367 | 0.01
5.7233 | 8.8617 | 7.7233 | 6.7233 | 9.585 | 11.585 | 8.8617 | 15.585 | 25.17 | 36.755 | 5.7233 | 8.8617 | 7.7233 | 6.7233 | 9.585 | 11.595 | 8.8617 | 15.585 | 25.17 | 36.765 | 0.01
8.2167 | 10.1084 | 10.2167 | 9.2167 | 13.3251 | 15.3251 | 10.1084 | 19.3251 | 32.6501 | 47.9752 | 8.2167 | 10.1084 | 10.2167 | 9.2167 | 13.3251 | 15.3351 | 10.1084 | 19.3251 | 32.6501 | 47.9852 | 0.01
5.8225 | 8.9113 | 7.8225 | 6.8225 | 9.7338 | 11.7338 | 8.9113 | 15.7338 | 25.4676 | 37.2013 | 5.8225 | 8.9113 | 7.8225 | 6.8225 | 9.7338 | 11.7438 | 8.9113 | 15.7338 | 25.4676 | 37.2113 | 0.01
4.44 | 8.22 | 6.44 | 5.44 | 7.6599 | 9.6599 | 8.22 | 13.6599 | 21.3199 | 30.9798 | 4.44 | 8.22 | 6.44 | 5.44 | 7.6599 | 9.6699 | 8.22 | 13.6599 | 21.3199 | 30.9898 | 0.01
5.5445 | 8.7723 | 7.5445 | 6.5445 | 9.3168 | 11.3168 | 8.7723 | 15.3168 | 24.6336 | 35.9503 | 5.5445 | 8.7723 | 7.5445 | 6.5445 | 9.3168 | 11.3268 | 8.7723 | 15.3168 | 24.6336 | 35.9603 | 0.01
6.9782 | 9.4891 | 8.9782 | 7.9782 | 11.4673 | 13.4673 | 9.4891 | 17.4673 | 28.9346 | 42.4018 | 6.9782 | 9.4891 | 8.9782 | 7.9782 | 11.4673 | 13.4773 | 9.4891 | 17.4673 | 28.9346 | 42.4118 | 0.01
4.06 | 8.03 | 6.06 | 5.06 | 7.09 | 9.09 | 8.03 | 13.09 | 20.1799 | 29.2699 | 4.06 | 8.03 | 6.06 | 5.06 | 7.09 | 9.1 | 8.03 | 13.09 | 20.1799 | 29.2799 | 0.01
6.8952 | 9.4476 | 8.8952 | 7.8952 | 11.3428 | 13.3428 | 9.4476 | 17.3428 | 28.6856 | 42.0284 | 6.8952 | 9.4476 | 8.8952 | 7.8952 | 11.3428 | 13.3528 | 9.4476 | 17.3428 | 28.6856 | 42.0384 | 0.01
4.2954 | 8.1477 | 6.2954 | 5.2954 | 7.4431 | 9.4431 | 8.1477 | 13.4431 | 20.8863 | 30.3294 | 4.2954 | 8.1477 | 6.2954 | 5.2954 | 7.4431 | 9.4531 | 8.1477 | 13.4431 | 20.8863 | 30.3394 | 0.01
5.384 | 8.692 | 7.384 | 6.384 | 9.076 | 11.076 | 8.692 | 15.076 | 24.152 | 35.228 | 5.384 | 8.692 | 7.384 | 6.384 | 9.076 | 11.086 | 8.692 | 15.076 | 24.152 | 35.238 | 0.01
5.5138 | 8.7569 | 7.5138 | 6.5138 | 9.2708 | 11.2708 | 8.7569 | 15.2708 | 24.5415 | 35.8123 | 5.5138 | 8.7569 | 7.5138 | 6.5138 | 9.2708 | 11.2808 | 8.7569 | 15.2708 | 24.5415 | 35.8223 | 0.01
6.558 | 9.279 | 8.558 | 7.558 | 10.837 | 12.837 | 9.279 | 16.837 | 27.6741 | 40.5111 | 6.558 | 9.279 | 8.558 | 7.558 | 10.837 | 12.847 | 9.279 | 16.837 | 27.6741 | 40.5211 | 0.01
6.8751 | 9.4376 | 8.8751 | 7.8751 | 11.3127 | 13.3127 | 9.4376 | 17.3127 | 28.6254 | 41.9381 | 6.8751 | 9.4376 | 8.8751 | 7.8751 | 11.3127 | 13.3227 | 9.4376 | 17.3127 | 28.6254 | 41.9481 | 0.01
5.5105 | 8.7553 | 7.5105 | 6.5105 | 9.2658 | 11.2658 | 8.7553 | 15.2658 | 24.5316 | 35.7974 | 5.5105 | 8.7553 | 7.5105 | 6.5105 | 9.2658 | 11.2758 | 8.7553 | 15.2658 | 24.5316 | 35.8074 | 0.01
3.8041 | 7.902 | 5.8041 | 4.8041 | 6.7061 | 8.7061 | 7.902 | 12.7061 | 19.4123 | 28.1184 | 3.8041 | 7.902 | 5.8041 | 4.8041 | 6.7061 | 8.7161 | 7.902 | 12.7061 | 19.4123 | 28.1284 | 0.01
6.5984 | 9.2992 | 8.5984 | 7.5984 | 10.8976 | 12.8976 | 9.2992 | 16.8976 | 27.7952 | 40.6927 | 6.5984 | 9.2992 | 8.5984 | 7.5984 | 10.8976 | 12.9076 | 9.2992 | 16.8976 | 27.7952 | 40.7027 | 0.01
4.1412 | 8.0706 | 6.1412 | 5.1412 | 7.2117 | 9.2117 | 8.0706 | 13.2117 | 20.4235 | 29.6352 | 4.1412 | 8.0706 | 6.1412 | 5.1412 | 7.2117 | 9.2217 | 8.0706 | 13.2117 | 20.4235 | 29.6452 | 0.01
8.1884 | 10.0942 | 10.1884 | 9.1884 | 13.2826 | 15.2826 | 10.0942 | 19.2826 | 32.5651 | 47.8477 | 8.1884 | 10.0942 | 10.1884 | 9.1884 | 13.2826 | 15.2926 | 10.0942 | 19.2826 | 32.5651 | 47.8577 | 0.01
3.3929 | 7.6965 | 5.3929 | 4.3929 | 6.0894 | 8.0894 | 7.6965 | 12.0894 | 18.1787 | 26.2681 | 3.3929 | 7.6965 | 5.3929 | 4.3929 | 6.0894 | 8.0994 | 7.6965 | 12.0894 | 18.1787 | 26.2781 | 0.01
8.253 | 10.1265 | 10.253 | 9.253 | 13.3795 | 15.3795 | 10.1265 | 19.3795 | 32.759 | 48.1384 | 8.253 | 10.1265 | 10.253 | 9.253 | 13.3795 | 15.3895 | 10.1265 | 19.3795 | 32.759 | 48.1484 | 0.01
6.3518 | 9.1759 | 8.3518 | 7.3518 | 10.5277 | 12.5277 | 9.1759 | 16.5277 | 27.0554 | 39.583 | 6.3518 | 9.1759 | 8.3518 | 7.3518 | 10.5277 | 12.5377 | 9.1759 | 16.5277 | 27.0554 | 39.593 | 0.01
6.4248 | 9.2124 | 8.4248 | 7.4248 | 10.6371 | 12.6371 | 9.2124 | 16.6371 | 27.2743 | 39.9114 | 6.4248 | 9.2124 | 8.4248 | 7.4248 | 10.6371 | 12.6471 | 9.2124 | 16.6371 | 27.2743 | 39.9214 | 0.01
4.0788 | 8.0394 | 6.0788 | 5.0788 | 7.1181 | 9.1181 | 8.0394 | 13.1181 | 20.2363 | 29.3544 | 4.0788 | 8.0394 | 6.0788 | 5.0788 | 7.1181 | 9.1281 | 8.0394 | 13.1181 | 20.2363 | 29.3644 | 0.01
3.7415 | 7.8708 | 5.7415 | 4.7415 | 6.6123 | 8.6123 | 7.8708 | 12.6123 | 19.2246 | 27.8368 | 3.7415 | 7.8708 | 5.7415 | 4.7415 | 6.6123 | 8.6223 | 7.8708 | 12.6123 | 19.2246 | 27.8468 | 0.01
7.8238 | 9.9119 | 9.8238 | 8.8238 | 12.7357 | 14.7357 | 9.9119 | 18.7357 | 31.4713 | 46.207 | 7.8238 | 9.9119 | 9.8238 | 8.8238 | 12.7357 | 14.7457 | 9.9119 | 18.7357 | 31.4713 | 46.217 | 0.01
5.4348 | 8.7174 | 7.4348 | 6.4348 | 9.1522 | 11.1522 | 8.7174 | 15.1522 | 24.3044 | 35.4567 | 5.4348 | 8.7174 | 7.4348 | 6.4348 | 9.1522 | 11.1622 | 8.7174 | 15.1522 | 24.3044 | 35.4667 | 0.01
4.2646 | 8.1323 | 6.2646 | 5.2646 | 7.397 | 9.397 | 8.1323 | 13.397 | 20.7939 | 30.1909 | 4.2646 | 8.1323 | 6.2646 | 5.2646 | 7.397 | 9.407 | 8.1323 | 13.397 | 20.7939 | 30.2009 | 0.01
5.7679 | 8.884 | 7.7679 | 6.7679 | 9.6519 | 11.6519 | 8.884 | 15.6519 | 25.3038 | 36.9556 | 5.7679 | 8.884 | 7.7679 | 6.7679 | 9.6519 | 11.6619 | 8.884 | 15.6519 | 25.3038 | 36.9656 | 0.01
6.0709 | 9.0355 | 8.0709 | 7.0709 | 10.1064 | 12.1064 | 9.0355 | 16.1064 | 26.2128 | 38.3192 | 6.0709 | 9.0355 | 8.0709 | 7.0709 | 10.1064 | 12.1164 | 9.0355 | 16.1064 | 26.2128 | 38.3292 | 0.01
7.1335 | 9.5668 | 9.1335 | 8.1335 | 11.7003 | 13.7003 | 9.5668 | 17.7003 | 29.4005 | 43.1008 | 7.1335 | 9.5668 | 9.1335 | 8.1335 | 11.7003 | 13.7103 | 9.5668 | 17.7003 | 29.4005 | 43.1108 | 0.01
7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8785 | 9.6262 | 17.8785 | 29.757 | 43.6355 | 7.2523 | 9.6262 | 9.2523 | 8.2523 | 11.8785 | 13.8885 | 9.6262 | 17.8785 | 29.757 | 43.6455 | 0.01
1.7153 | 6.8577 | 3.7153 | 2.7153 | 3.573 | 5.573 | 6.8577 | 9.573 | 13.146 | 18.719 | 1.7153 | 6.8577 | 3.7153 | 2.7153 | 3.573 | 5.583 | 6.8577 | 9.573 | 13.146 | 18.729 | 0.01
2.3377 | 7.1689 | 4.3377 | 3.3377 | 4.5066 | 6.5066 | 7.1689 | 10.5066 | 15.0132 | 21.5197 | 2.3377 | 7.1689 | 4.3377 | 3.3377 | 4.5066 | 6.5166 | 7.1689 | 10.5066 | 15.0132 | 21.5297 | 0.01
4.5542 | 8.2771 | 6.5542 | 5.5542 | 7.8313 | 9.8313 | 8.2771 | 13.8313 | 21.6626 | 31.4939 | 4.5542 | 8.2771 | 6.5542 | 5.5542 | 7.8313 | 9.8413 | 8.2771 | 13.8313 | 21.6626 | 31.5039 | 0.01
8.0371 | 10.0185 | 10.0371 | 9.0371 | 13.0556 | 15.0556 | 10.0185 | 19.0556 | 32.1113 | 47.1669 | 8.0371 | 10.0185 | 10.0371 | 9.0371 | 13.0556 | 15.0656 | 10.0185 | 19.0556 | 32.1113 | 47.1769 | 0.01
9.1147 | 10.5573 | 11.1147 | 10.1147 | 14.672 | 16.672 | 10.5573 | 20.672 | 35.3441 | 52.0161 | 9.1147 | 10.5573 | 11.1147 | 10.1147 | 14.672 | 16.682 | 10.5573 | 20.672 | 35.3441 | 52.0261 | 0.01
6.8241 | 9.412 | 8.8241 | 7.8241 | 11.2361 | 13.2361 | 9.412 | 17.2361 | 28.4722 | 41.7083 | 6.8241 | 9.412 | 8.8241 | 7.8241 | 11.2361 | 13.2461 | 9.412 | 17.2361 | 28.4722 | 41.7183 | 0.01
6.7062 | 9.3531 | 8.7062 | 7.7062 | 11.0593 | 13.0593 | 9.3531 | 17.0593 | 28.1185 | 41.1778 | 6.7062 | 9.3531 | 8.7062 | 7.7062 | 11.0593 | 13.0693 | 9.3531 | 17.0593 | 28.1185 | 41.1878 | 0.01
5.2576 | 8.6288 | 7.2576 | 6.2576 | 8.8863 | 10.8863 | 8.6288 | 14.8863 | 23.7727 | 34.659 | 5.2576 | 8.6288 | 7.2576 | 6.2576 | 8.8863 | 10.8963 | 8.6288 | 14.8863 | 23.7727 | 34.669 | 0.01
6.3132 | 9.1566 | 8.3132 | 7.3132 | 10.4697 | 12.4697 | 9.1566 | 16.4697 | 26.9395 | 39.4092 | 6.3132 | 9.1566 | 8.3132 | 7.3132 | 10.4697 | 12.4797 | 9.1566 | 16.4697 | 26.9395 | 39.4192 | 0.01
5.6124 | 8.8062 | 7.6124 | 6.6124 | 9.4186 | 11.4186 | 8.8062 | 15.4186 | 24.8373 | 36.2559 | 5.6124 | 8.8062 | 7.6124 | 6.6124 | 9.4186 | 11.4286 | 8.8062 | 15.4186 | 24.8373 | 36.2659 | 0.01
4.4577 | 8.2289 | 6.4577 | 5.4577 | 7.6866 | 9.6866 | 8.2289 | 13.6866 | 21.3732 | 31.0598 | 4.4577 | 8.2289 | 6.4577 | 5.4577 | 7.6866 | 9.6966 | 8.2289 | 13.6866 | 21.3732 | 31.0698 | 0.01
7.1172 | 9.5586 | 9.1172 | 8.1172 | 11.6758 | 13.6758 | 9.5586 | 17.6758 | 29.3516 | 43.0274 | 7.1172 | 9.5586 | 9.1172 | 8.1172 | 11.6758 | 13.6858 | 9.5586 | 17.6758 | 29.3516 | 43.0374 | 0.01
1.8832 | 6.9416 | 3.8832 | 2.8832 | 3.8248 | 5.8248 | 6.9416 | 9.8248 | 13.6496 | 19.4744 | 1.8832 | 6.9416 | 3.8832 | 2.8832 | 3.8248 | 5.8348 | 6.9416 | 9.8248 | 13.6496 | 19.4844 | 0.01
9.3963 | 10.6981 | 11.3963 | 10.3963 | 15.0944 | 17.0944 | 10.6981 | 21.0944 | 36.1889 | 53.2833 | 9.3963 | 10.6981 | 11.3963 | 10.3963 | 15.0944 | 17.1044 | 10.6981 | 21.0944 | 36.1889 | 53.2933 | 0.01
5.7522 | 8.8761 | 7.7522 | 6.7522 | 9.6283 | 11.6283 | 8.8761 | 15.6283 | 25.2566 | 36.8849 | 5.7522 | 8.8761 | 7.7522 | 6.7522 | 9.6283 | 11.6383 | 8.8761 | 15.6283 | 25.2566 | 36.8949 | 0.01
8.7802 | 10.3901 | 10.7802 | 9.7802 | 14.1703 | 16.1703 | 10.3901 | 20.1703 | 34.3407 | 50.511 | 8.7802 | 10.3901 | 10.7802 | 9.7802 | 14.1703 | 16.1803 | 10.3901 | 20.1703 | 34.3407 | 50.521 | 0.01
6.4029 | 9.2014 | 8.4029 | 7.4029 | 10.6043 | 12.6043 | 9.2014 | 16.6043 | 27.2086 | 39.8129 | 6.4029 | 9.2014 | 8.4029 | 7.4029 | 10.6043 | 12.6143 | 9.2014 | 16.6043 | 27.2086 | 39.8229 | 0.01
3.783 | 7.8915 | 5.783 | 4.783 | 6.6745 | 8.6745 | 7.8915 | 12.6745 | 19.349 | 28.0235 | 3.783 | 7.8915 | 5.783 | 4.783 | 6.6745 | 8.6845 | 7.8915 | 12.6745 | 19.349 | 28.0335 | 0.01
4.0209 | 8.0105 | 6.0209 | 5.0209 | 7.0314 | 9.0314 | 8.0105 | 13.0314 | 20.0627 | 29.0941 | 4.0209 | 8.0105 | 6.0209 | 5.0209 | 7.0314 | 9.0414 | 8.0105 | 13.0314 | 20.0627 | 29.1041 | 0.01
6.4079 | 9.2039 | 8.4079 | 7.4079 | 10.6118 | 12.6118 | 9.2039 | 16.6118 | 27.2236 | 39.8354 | 6.4079 | 9.2039 | 8.4079 | 7.4079 | 10.6118 | 12.6218 | 9.2039 | 16.6118 | 27.2236 | 39.8454 | 0.01
6.5453 | 9.2727 | 8.5453 | 7.5453 | 10.818 | 12.818 | 9.2727 | 16.818 | 27.6359 | 40.4539 | 6.5453 | 9.2727 | 8.5453 | 7.5453 | 10.818 | 12.828 | 9.2727 | 16.818 | 27.6359 | 40.4639 | 0.01
7.6805 | 9.8402 | 9.6805 | 8.6805 | 12.5207 | 14.5207 | 9.8402 | 18.5207 | 31.0415 | 45.5622 | 7.6805 | 9.8402 | 9.6805 | 8.6805 | 12.5207 | 14.5307 | 9.8402 | 18.5207 | 31.0415 | 45.5722 | 0.01
6.1081 | 9.0541 | 8.1081 | 7.1081 | 10.1622 | 12.1622 | 9.0541 | 16.1622 | 26.3244 | 38.4866 | 6.1081 | 9.0541 | 8.1081 | 7.1081 | 10.1622 | 12.1722 | 9.0541 | 16.1622 | 26.3244 | 38.4966 | 0.01
6.5904 | 9.2952 | 8.5904 | 7.5904 | 10.8856 | 12.8856 | 9.2952 | 16.8856 | 27.7712 | 40.6568 | 6.5904 | 9.2952 | 8.5904 | 7.5904 | 10.8856 | 12.8956 | 9.2952 | 16.8856 | 27.7712 | 40.6668 | 0.01
6.4252 | 9.2126 | 8.4252 | 7.4252 | 10.6378 | 12.6378 | 9.2126 | 16.6378 | 27.2757 | 39.9135 | 6.4252 | 9.2126 | 8.4252 | 7.4252 | 10.6378 | 12.6478 | 9.2126 | 16.6378 | 27.2757 | 39.9235 | 0.01
5.1021 | 8.551 | 7.1021 | 6.1021 | 8.6531 | 10.6531 | 8.551 | 14.6531 | 23.3063 | 33.9594 | 5.1021 | 8.551 | 7.1021 | 6.1021 | 8.6531 | 10.6631 | 8.551 | 14.6531 | 23.3063 | 33.9694 | 0.01
5.7627 | 8.8813 | 7.7627 | 6.7627 | 9.644 | 11.644 | 8.8813 | 15.644 | 25.288 | 36.9321 | 5.7627 | 8.8813 | 7.7627 | 6.7627 | 9.644 | 11.654 | 8.8813 | 15.644 | 25.288 | 36.9421 | 0.01
6.6646 | 9.3323 | 8.6646 | 7.6646 | 10.997 | 12.997 | 9.3323 | 16.997 | 27.9939 | 40.9909 | 6.6646 | 9.3323 | 8.6646 | 7.6646 | 10.997 | 13.007 | 9.3323 | 16.997 | 27.9939 | 41.0009 | 0.01
3.2081 | 7.604 | 5.2081 | 4.2081 | 5.8121 | 7.8121 | 7.604 | 11.8121 | 17.6242 | 25.4363 | 3.2081 | 7.604 | 5.2081 | 4.2081 | 5.8121 | 7.8221 | 7.604 | 11.8121 | 17.6242 | 25.4463 | 0.01
5.1092 | 8.5546 | 7.1092 | 6.1092 | 8.6638 | 10.6638 | 8.5546 | 14.6638 | 23.3276 | 33.9913 | 5.1092 | 8.5546 | 7.1092 | 6.1092 | 8.6638 | 10.6738 | 8.5546 | 14.6638 | 23.3276 | 34.0013 | 0.01
6.6987 | 9.3493 | 8.6987 | 7.6987 | 11.048 | 13.048 | 9.3493 | 17.048 | 28.0961 | 41.1441 | 6.6987 | 9.3493 | 8.6987 | 7.6987 | 11.048 | 13.058 | 9.3493 | 17.048 | 28.0961 | 41.1541 | 0.01
6.0901 | 9.045 | 8.0901 | 7.0901 | 10.1351 | 12.1351 | 9.045 | 16.1351 | 26.2702 | 38.4053 | 6.0901 | 9.045 | 8.0901 | 7.0901 | 10.1351 | 12.1451 | 9.045 | 16.1351 | 26.2702 | 38.4153 | 0.01
3.3738 | 7.6869 | 5.3738 | 4.3738 | 6.0607 | 8.0607 | 7.6869 | 12.0607 | 18.1215 | 26.1822 | 3.3738 | 7.6869 | 5.3738 | 4.3738 | 6.0607 | 8.0707 | 7.6869 | 12.0607 | 18.1215 | 26.1922 | 0.01
4.8105 | 8.4053 | 6.8105 | 5.8105 | 8.2158 | 10.2158 | 8.4053 | 14.2158 | 22.4316 | 32.6474 | 4.8105 | 8.4053 | 6.8105 | 5.8105 | 8.2158 | 10.2258 | 8.4053 | 14.2158 | 22.4316 | 32.6574 | 0.01
7.522 | 9.761 | 9.522 | 8.522 | 12.2829 | 14.2829 | 9.761 | 18.2829 | 30.5659 | 44.8488 | 7.522 | 9.761 | 9.522 | 8.522 | 12.2829 | 14.2929 | 9.761 | 18.2829 | 30.5659 | 44.8588 | 0.01
4.9713 | 8.4857 | 6.9713 | 5.9713 | 8.457 | 10.457 | 8.4857 | 14.457 | 22.9139 | 33.3709 | 4.9713 | 8.4857 | 6.9713 | 5.9713 | 8.457 | 10.467 | 8.4857 | 14.457 | 22.9139 | 33.3809 | 0.01
6.749 | 9.3745 | 8.749 | 7.749 | 11.1235 | 13.1235 | 9.3745 | 17.1235 | 28.247 | 41.3705 | 6.749 | 9.3745 | 8.749 | 7.749 | 11.1235 | 13.1335 | 9.3745 | 17.1235 | 28.247 | 41.3805 | 0.01
5.0742 | 8.5371 | 7.0742 | 6.0742 | 8.6114 | 10.6114 | 8.5371 | 14.6114 | 23.2227 | 33.8341 | 5.0742 | 8.5371 | 7.0742 | 6.0742 | 8.6114 | 10.6214 | 8.5371 | 14.6114 | 23.2227 | 33.8441 | 0.01
4.7646 | 8.3823 | 6.7646 | 5.7646 | 8.1468 | 10.1468 | 8.3823 | 14.1468 | 22.2937 | 32.4405 | 4.7646 | 8.3823 | 6.7646 | 5.7646 | 8.1468 | 10.1568 | 8.3823 | 14.1468 | 22.2937 | 32.4505 | 0.01
7.389 | 9.6945 | 9.389 | 8.389 | 12.0834 | 14.0834 | 9.6945 | 18.0834 | 30.1669 | 44.2503 | 7.389 | 9.6945 | 9.389 | 8.389 | 12.0834 | 14.0934 | 9.6945 | 18.0834 | 30.1669 | 44.2603 | 0.01
2.893 | 7.4465 | 4.893 | 3.893 | 5.3395 | 7.3395 | 7.4465 | 11.3395 | 16.679 | 24.0185 | 2.893 | 7.4465 | 4.893 | 3.893 | 5.3395 | 7.3495 | 7.4465 | 11.3395 | 16.679 | 24.0285 | 0.01
3.3349 | 7.6675 | 5.3349 | 4.3349 | 6.0024 | 8.0024 | 7.6675 | 12.0024 | 18.0048 | 26.0072 | 3.3349 | 7.6675 | 5.3349 | 4.3349 | 6.0024 | 8.0124 | 7.6675 | 12.0024 | 18.0048 | 26.0172 | 0.01
8.9925 | 10.4963 | 10.9925 | 9.9925 | 14.4888 | 16.4888 | 10.4963 | 20.4888 | 34.9775 | 51.4663 | 8.9925 | 10.4963 | 10.9925 | 9.9925 | 14.4888 | 16.4988 | 10.4963 | 20.4888 | 34.9775 | 51.4763 | 0.01
7.789 | 9.8945 | 9.789 | 8.789 | 12.6836 | 14.6836 | 9.8945 | 18.6836 | 31.3671 | 46.0507 | 7.789 | 9.8945 | 9.789 | 8.789 | 12.6836 | 14.6936 | 9.8945 | 18.6836 | 31.3671 | 46.0607 | 0.01
7.8333 | 9.9167 | 9.8333 | 8.8333 | 12.75 | 14.75 | 9.9167 | 18.75 | 31.4999 | 46.2499 | 7.8333 | 9.9167 | 9.8333 | 8.8333 | 12.75 | 14.76 | 9.9167 | 18.75 | 31.4999 | 46.2599 | 0.01
7.307 | 9.6535 | 9.307 | 8.307 | 11.9605 | 13.9605 | 9.6535 | 17.9605 | 29.9209 | 43.8814 | 7.307 | 9.6535 | 9.307 | 8.307 | 11.9605 | 13.9705 | 9.6535 | 17.9605 | 29.9209 | 43.8914 | 0.01
9.787 | 10.8935 | 11.787 | 10.787 | 15.6805 | 17.6805 | 10.8935 | 21.6805 | 37.361 | 55.0415 | 9.787 | 10.8935 | 11.787 | 10.787 | 15.6805 | 17.6905 | 10.8935 | 21.6805 | 37.361 | 55.0515 | 0.01
5.2045 | 8.6023 | 7.2045 | 6.2045 | 8.8068 | 10.8068 | 8.6023 | 14.8068 | 23.6135 | 34.4203 | 5.2045 | 8.6023 | 7.2045 | 6.2045 | 8.8068 | 10.8168 | 8.6023 | 14.8068 | 23.6135 | 34.4303 | 0.01
5.5481 | 8.7741 | 7.5481 | 6.5481 | 9.3222 | 11.3222 | 8.7741 | 15.3222 | 24.6444 | 35.9666 | 5.5481 | 8.7741 | 7.5481 | 6.5481 | 9.3222 | 11.3322 | 8.7741 | 15.3222 | 24.6444 | 35.9766 | 0.01
2.9819 | 7.491 | 4.9819 | 3.9819 | 5.4729 | 7.4729 | 7.491 | 11.4729 | 16.9458 | 24.4187 | 2.9819 | 7.491 | 4.9819 | 3.9819 | 5.4729 | 7.4829 | 7.491 | 11.4729 | 16.9458 | 24.4287 | 0.01
7.6554 | 9.8277 | 9.6554 | 8.6554 | 12.4831 | 14.4831 | 9.8277 | 18.4831 | 30.9661 | 45.4492 | 7.6554 | 9.8277 | 9.6554 | 8.6554 | 12.4831 | 14.4931 | 9.8277 | 18.4831 | 30.9661 | 45.4592 | 0.01
4.8098 | 8.4049 | 6.8098 | 5.8098 | 8.2147 | 10.2147 | 8.4049 | 14.2147 | 22.4294 | 32.6441 | 4.8098 | 8.4049 | 6.8098 | 5.8098 | 8.2147 | 10.2247 | 8.4049 | 14.2147 | 22.4294 | 32.6541 | 0.01
2.7341 | 7.3671 | 4.7341 | 3.7341 | 5.1012 | 7.1012 | 7.3671 | 11.1012 | 16.2023 | 23.3035 | 2.7341 | 7.3671 | 4.7341 | 3.7341 | 5.1012 | 7.1112 | 7.3671 | 11.1012 | 16.2023 | 23.3135 | 0.01
8.5249 | 10.2624 | 10.5249 | 9.5249 | 13.7873 | 15.7873 | 10.2624 | 19.7873 | 33.5746 | 49.3619 | 8.5249 | 10.2624 | 10.5249 | 9.5249 | 13.7873 | 15.7973 | 10.2624 | 19.7873 | 33.5746 | 49.3719 | 0.01
8.5457 | 10.2729 | 10.5457 | 9.5457 | 13.8186 | 15.8186 | 10.2729 | 19.8186 | 33.6371 | 49.4557 | 8.5457 | 10.2729 | 10.5457 | 9.5457 | 13.8186 | 15.8286 | 10.2729 | 19.8186 | 33.6371 | 49.4657 | 0.01
6.6239 | 9.3119 | 8.6239 | 7.6239 | 10.9358 | 12.9358 | 9.3119 | 16.9358 | 27.8716 | 40.8074 | 6.6239 | 9.3119 | 8.6239 | 7.6239 | 10.9358 | 12.9458 | 9.3119 | 16.9358 | 27.8716 | 40.8174 | 0.01
7.2382 | 9.6191 | 9.2382 | 8.2382 | 11.8573 | 13.8573 | 9.6191 | 17.8573 | 29.7147 | 43.572 | 7.2382 | 9.6191 | 9.2382 | 8.2382 | 11.8573 | 13.8673 | 9.6191 | 17.8573 | 29.7147 | 43.582 | 0.01
6.7582 | 9.3791 | 8.7582 | 7.7582 | 11.1373 | 13.1373 | 9.3791 | 17.1373 | 28.2746 | 41.4119 | 6.7582 | 9.3791 | 8.7582 | 7.7582 | 11.1373 | 13.1473 | 9.3791 | 17.1373 | 28.2746 | 41.4219 | 0.01
5.4894 | 8.7447 | 7.4894 | 6.4894 | 9.2341 | 11.2341 | 8.7447 | 15.2341 | 24.4682 | 35.7022 | 5.4894 | 8.7447 | 7.4894 | 6.4894 | 9.2341 | 11.2441 | 8.7447 | 15.2341 | 24.4682 | 35.7122 | 0.01
5.7659 | 8.883 | 7.7659 | 6.7659 | 9.6489 | 11.6489 | 8.883 | 15.6489 | 25.2977 | 36.9466 | 5.7659 | 8.883 | 7.7659 | 6.7659 | 9.6489 | 11.6589 | 8.883 | 15.6489 | 25.2977 | 36.9566 | 0.01
5.7573 | 8.8786 | 7.7573 | 6.7573 | 9.6359 | 11.6359 | 8.8786 | 15.6359 | 25.2719 | 36.9078 | 5.7573 | 8.8786 | 7.7573 | 6.7573 | 9.6359 | 11.6459 | 8.8786 | 15.6359 | 25.2719 | 36.9178 | 0.01
4.4028 | 8.2014 | 6.4028 | 5.4028 | 7.6042 | 9.6042 | 8.2014 | 13.6042 | 21.2083 | 30.8125 | 4.4028 | 8.2014 | 6.4028 | 5.4028 | 7.6042 | 9.6142 | 8.2014 | 13.6042 | 21.2083 | 30.8225 | 0.01
5.7536 | 8.8768 | 7.7536 | 6.7536 | 9.6304 | 11.6304 | 8.8768 | 15.6304 | 25.2608 | 36.8911 | 5.7536 | 8.8768 | 7.7536 | 6.7536 | 9.6304 | 11.6404 | 8.8768 | 15.6304 | 25.2608 | 36.9011 | 0.01
5.0303 | 8.5151 | 7.0303 | 6.0303 | 8.5454 | 10.5454 | 8.5151 | 14.5454 | 23.0908 | 33.6361 | 5.0303 | 8.5151 | 7.0303 | 6.0303 | 8.5454 | 10.5554 | 8.5151 | 14.5454 | 23.0908 | 33.6461 | 0.01
3.0131 | 7.5066 | 5.0131 | 4.0131 | 5.5197 | 7.5197 | 7.5066 | 11.5197 | 17.0393 | 24.559 | 3.0131 | 7.5066 | 5.0131 | 4.0131 | 5.5197 | 7.5297 | 7.5066 | 11.5197 | 17.0393 | 24.569 | 0.01
2.4946 | 7.2473 | 4.4946 | 3.4946 | 4.7419 | 6.7419 | 7.2473 | 10.7419 | 15.4838 | 22.2257 | 2.4946 | 7.2473 | 4.4946 | 3.4946 | 4.7419 | 6.7519 | 7.2473 | 10.7419 | 15.4838 | 22.2357 | 0.01
3.8321 | 7.9161 | 5.8321 | 4.8321 | 6.7482 | 8.7482 | 7.9161 | 12.7482 | 19.4963 | 28.2445 | 3.8321 | 7.9161 | 5.8321 | 4.8321 | 6.7482 | 8.7582 | 7.9161 | 12.7482 | 19.4963 | 28.2545 | 0.01
3.881 | 7.9405 | 5.881 | 4.881 | 6.8215 | 8.8215 | 7.9405 | 12.8215 | 19.6431 | 28.4646 | 3.881 | 7.9405 | 5.881 | 4.881 | 6.8215 | 8.8315 | 7.9405 | 12.8215 | 19.6431 | 28.4746 | 0.01
6.8478 | 9.4239 | 8.8478 | 7.8478 | 11.2716 | 13.2716 | 9.4239 | 17.2716 | 28.5433 | 41.8149 | 6.8478 | 9.4239 | 8.8478 | 7.8478 | 11.2716 | 13.2816 | 9.4239 | 17.2716 | 28.5433 | 41.8249 | 0.01
6.8117 | 9.4059 | 8.8117 | 7.8117 | 11.2176 | 13.2176 | 9.4059 | 17.2176 | 28.4352 | 41.6529 | 6.8117 | 9.4059 | 8.8117 | 7.8117 | 11.2176 | 13.2276 | 9.4059 | 17.2176 | 28.4352 | 41.6629 | 0.01
2.5649 | 7.2825 | 4.5649 | 3.5649 | 4.8474 | 6.8474 | 7.2825 | 10.8474 | 15.6947 | 22.5421 | 2.5649 | 7.2825 | 4.5649 | 3.5649 | 4.8474 | 6.8574 | 7.2825 | 10.8474 | 15.6947 | 22.5521 | 0.01
4.502 | 8.251 | 6.502 | 5.502 | 7.7531 | 9.7531 | 8.251 | 13.7531 | 21.5061 | 31.2592 | 4.502 | 8.251 | 6.502 | 5.502 | 7.7531 | 9.7631 | 8.251 | 13.7531 | 21.5061 | 31.2692 | 0.01
8.0192 | 10.0096 | 10.0192 | 9.0192 | 13.0288 | 15.0288 | 10.0096 | 19.0288 | 32.0575 | 47.0863 | 8.0192 | 10.0096 | 10.0192 | 9.0192 | 13.0288 | 15.0388 | 10.0096 | 19.0288 | 32.0575 | 47.0963 | 0.01
5.5992 | 8.7996 | 7.5992 | 6.5992 | 9.3987 | 11.3987 | 8.7996 | 15.3987 | 24.7975 | 36.1962 | 5.5992 | 8.7996 | 7.5992 | 6.5992 | 9.3987 | 11.4087 | 8.7996 | 15.3987 | 24.7975 | 36.2062 | 0.01
3.538 | 7.769 | 5.538 | 4.538 | 6.3071 | 8.3071 | 7.769 | 12.3071 | 18.6141 | 26.9212 | 3.538 | 7.769 | 5.538 | 4.538 | 6.3071 | 8.3171 | 7.769 | 12.3071 | 18.6141 | 26.9312 | 0.01
4.1922 | 8.0961 | 6.1922 | 5.1922 | 7.2882 | 9.2882 | 8.0961 | 13.2882 | 20.5765 | 29.8647 | 4.1922 | 8.0961 | 6.1922 | 5.1922 | 7.2882 | 9.2982 | 8.0961 | 13.2882 | 20.5765 | 29.8747 | 0.01
8.0617 | 10.0308 | 10.0617 | 9.0617 | 13.0925 | 15.0925 | 10.0308 | 19.0925 | 32.185 | 47.2775 | 8.0617 | 10.0308 | 10.0617 | 9.0617 | 13.0925 | 15.1025 | 10.0308 | 19.0925 | 32.185 | 47.2875 | 0.01
7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2433 | 9.7444 | 18.2333 | 30.4666 | 44.7098 | 0.01
11.8438 | 11.9219 | 13.8438 | 12.8438 | 18.7656 | 20.7656 | 11.9219 | 24.7656 | 43.5313 | 64.2969 | 11.8438 | 11.9219 | 13.8438 | 12.8438 | 18.7656 | 20.7756 | 11.9219 | 24.7656 | 43.5313 | 64.3069 | 0.01
6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.5072 | 9.1657 | 16.4972 | 26.9943 | 39.5015 | 0.01
8.8082 | 10.4041 | 10.8082 | 9.8082 | 14.2124 | 16.2124 | 10.4041 | 20.2124 | 34.4247 | 50.6371 | 8.8082 | 10.4041 | 10.8082 | 9.8082 | 14.2124 | 16.2224 | 10.4041 | 20.2124 | 34.4247 | 50.6471 | 0.01
7.6294 | 9.8147 | 9.6294 | 8.6294 | 12.4441 | 14.4441 | 9.8147 | 18.4441 | 30.8883 | 45.3324 | 7.6294 | 9.8147 | 9.6294 | 8.6294 | 12.4441 | 14.4541 | 9.8147 | 18.4441 | 30.8883 | 45.3424 | 0.01
6.2816 | 9.1408 | 8.2816 | 7.2816 | 10.4224 | 12.4224 | 9.1408 | 16.4224 | 26.8448 | 39.2672 | 6.2816 | 9.1408 | 8.2816 | 7.2816 | 10.4224 | 12.4324 | 9.1408 | 16.4224 | 26.8448 | 39.2772 | 0.01
2.9948 | 7.4974 | 4.9948 | 3.9948 | 5.4922 | 7.4922 | 7.4974 | 11.4922 | 16.9843 | 24.4765 | 2.9948 | 7.4974 | 4.9948 | 3.9948 | 5.4922 | 7.5022 | 7.4974 | 11.4922 | 16.9843 | 24.4865 | 0.01
7.6577 | 9.8289 | 9.6577 | 8.6577 | 12.4866 | 14.4866 | 9.8289 | 18.4866 | 30.9732 | 45.4598 | 7.6577 | 9.8289 | 9.6577 | 8.6577 | 12.4866 | 14.4966 | 9.8289 | 18.4866 | 30.9732 | 45.4698 | 0.01
5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.656 | 8.5487 | 14.646 | 23.292 | 33.9481 | 0.01
6.3502 | 9.1751 | 8.3502 | 7.3502 | 10.5253 | 12.5253 | 9.1751 | 16.5253 | 27.0507 | 39.576 | 6.3502 | 9.1751 | 8.3502 | 7.3502 | 10.5253 | 12.5353 | 9.1751 | 16.5253 | 27.0507 | 39.586 | 0.01
8.2841 | 10.1421 | 10.2841 | 9.2841 | 13.4262 | 15.4262 | 10.1421 | 19.4262 | 32.8524 | 48.2786 | 8.2841 | 10.1421 | 10.2841 | 9.2841 | 13.4262 | 15.4362 | 10.1421 | 19.4262 | 32.8524 | 48.2886 | 0.01
7.4494 | 9.7247 | 9.4494 | 8.4494 | 12.1741 | 14.1741 | 9.7247 | 18.1741 | 30.3481 | 44.5222 | 7.4494 | 9.7247 | 9.4494 | 8.4494 | 12.1741 | 14.1841 | 9.7247 | 18.1741 | 30.3481 | 44.5322 | 0.01
5.769 | 8.8845 | 7.769 | 6.769 | 9.6535 | 11.6535 | 8.8845 | 15.6535 | 25.307 | 36.9605 | 5.769 | 8.8845 | 7.769 | 6.769 | 9.6535 | 11.6635 | 8.8845 | 15.6535 | 25.307 | 36.9705 | 0.01
5.8084 | 8.9042 | 7.8084 | 6.8084 | 9.7126 | 11.7126 | 8.9042 | 15.7126 | 25.4252 | 37.1377 | 5.8084 | 8.9042 | 7.8084 | 6.8084 | 9.7126 | 11.7226 | 8.9042 | 15.7126 | 25.4252 | 37.1477 | 0.01
4.3983 | 8.1992 | 6.3983 | 5.3983 | 7.5975 | 9.5975 | 8.1992 | 13.5975 | 21.195 | 30.7925 | 4.3983 | 8.1992 | 6.3983 | 5.3983 | 7.5975 | 9.6075 | 8.1992 | 13.5975 | 21.195 | 30.8025 | 0.01
4.0729 | 8.0365 | 6.0729 | 5.0729 | 7.1094 | 9.1094 | 8.0365 | 13.1094 | 20.2188 | 29.3281 | 4.0729 | 8.0365 | 6.0729 | 5.0729 | 7.1094 | 9.1194 | 8.0365 | 13.1094 | 20.2188 | 29.3381 | 0.01
6.5512 | 9.2756 | 8.5512 | 7.5512 | 10.8268 | 12.8268 | 9.2756 | 16.8268 | 27.6536 | 40.4803 | 6.5512 | 9.2756 | 8.5512 | 7.5512 | 10.8268 | 12.8368 | 9.2756 | 16.8268 | 27.6536 | 40.4903 | 0.01
3.2266 | 7.6133 | 5.2266 | 4.2266 | 5.8399 | 7.8399 | 7.6133 | 11.8399 | 17.6798 | 25.5197 | 3.2266 | 7.6133 | 5.2266 | 4.2266 | 5.8399 | 7.8499 | 7.6133 | 11.8399 | 17.6798 | 25.5297 | 0.01
6.4914 | 9.2457 | 8.4914 | 7.4914 | 10.737 | 12.737 | 9.2457 | 16.737 | 27.4741 | 40.2111 | 6.4914 | 9.2457 | 8.4914 | 7.4914 | 10.737 | 12.747 | 9.2457 | 16.737 | 27.4741 | 40.2211 | 0.01
7.4177 | 9.7089 | 9.4177 | 8.4177 | 12.1266 | 14.1266 | 9.7089 | 18.1266 | 30.2532 | 44.3798 | 7.4177 | 9.7089 | 9.4177 | 8.4177 | 12.1266 | 14.1366 | 9.7089 | 18.1266 | 30.2532 | 44.3898 | 0.01
3.4213 | 7.7106 | 5.4213 | 4.4213 | 6.1319 | 8.1319 | 7.7106 | 12.1319 | 18.2638 | 26.3957 | 3.4213 | 7.7106 | 5.4213 | 4.4213 | 6.1319 | 8.1419 | 7.7106 | 12.1319 | 18.2638 | 26.4057 | 0.01
4.6599 | 8.3299 | 6.6599 | 5.6599 | 7.9898 | 9.9898 | 8.3299 | 13.9898 | 21.9797 | 31.9695 | 4.6599 | 8.3299 | 6.6599 | 5.6599 | 7.9898 | 9.9998 | 8.3299 | 13.9898 | 21.9797 | 31.9795 | 0.01
7.9283 | 9.9641 | 9.9283 | 8.9283 | 12.8924 | 14.8924 | 9.9641 | 18.8924 | 31.7849 | 46.6773 | 7.9283 | 9.9641 | 9.9283 | 8.9283 | 12.8924 | 14.9024 | 9.9641 | 18.8924 | 31.7849 | 46.6873 | 0.01
8.1195 | 10.0598 | 10.1195 | 9.1195 | 13.1793 | 15.1793 | 10.0598 | 19.1793 | 32.3586 | 47.5378 | 8.1195 | 10.0598 | 10.1195 | 9.1195 | 13.1793 | 15.1893 | 10.0598 | 19.1793 | 32.3586 | 47.5478 | 0.01
5.1511 | 8.5755 | 7.1511 | 6.1511 | 8.7266 | 10.7266 | 8.5755 | 14.7266 | 23.4532 | 34.1798 | 5.1511 | 8.5755 | 7.1511 | 6.1511 | 8.7266 | 10.7366 | 8.5755 | 14.7266 | 23.4532 | 34.1898 | 0.01
4.3661 | 8.183 | 6.3661 | 5.3661 | 7.5491 | 9.5491 | 8.183 | 13.5491 | 21.0983 | 30.6474 | 4.3661 | 8.183 | 6.3661 | 5.3661 | 7.5491 | 9.5591 | 8.183 | 13.5491 | 21.0983 | 30.6574 | 0.01
4.8403 | 8.4202 | 6.8403 | 5.8403 | 8.2605 | 10.2605 | 8.4202 | 14.2605 | 22.521 | 32.7815 | 4.8403 | 8.4202 | 6.8403 | 5.8403 | 8.2605 | 10.2705 | 8.4202 | 14.2605 | 22.521 | 32.7915 | 0.01
6.6155 | 9.3078 | 8.6155 | 7.6155 | 10.9233 | 12.9233 | 9.3078 | 16.9233 | 27.8466 | 40.7699 | 6.6155 | 9.3078 | 8.6155 | 7.6155 | 10.9233 | 12.9333 | 9.3078 | 16.9233 | 27.8466 | 40.7799 | 0.01
6.1813 | 9.0907 | 8.1813 | 7.1813 | 10.272 | 12.272 | 9.0907 | 16.272 | 26.544 | 38.8159 | 6.1813 | 9.0907 | 8.1813 | 7.1813 | 10.272 | 12.282 | 9.0907 | 16.272 | 26.544 | 38.8259 | 0.01
6.6324 | 9.3162 | 8.6324 | 7.6324 | 10.9486 | 12.9486 | 9.3162 | 16.9486 | 27.8972 | 40.8458 | 6.6324 | 9.3162 | 8.6324 | 7.6324 | 10.9486 | 12.9586 | 9.3162 | 16.9486 | 27.8972 | 40.8558 | 0.01
5.7216 | 8.8608 | 7.7216 | 6.7216 | 9.5825 | 11.5825 | 8.8608 | 15.5825 | 25.1649 | 36.7474 | 5.7216 | 8.8608 | 7.7216 | 6.7216 | 9.5825 | 11.5925 | 8.8608 | 15.5825 | 25.1649 | 36.7574 | 0.01
5.8658 | 8.9329 | 7.8658 | 6.8658 | 9.7987 | 11.7987 | 8.9329 | 15.7987 | 25.5974 | 37.3961 | 5.8658 | 8.9329 | 7.8658 | 6.8658 | 9.7987 | 11.8087 | 8.9329 | 15.7987 | 25.5974 | 37.4061 | 0.01
4.2094 | 8.1047 | 6.2094 | 5.2094 | 7.314 | 9.314 | 8.1047 | 13.314 | 20.6281 | 29.9421 | 4.2094 | 8.1047 | 6.2094 | 5.2094 | 7.314 | 9.324 | 8.1047 | 13.314 | 20.6281 | 29.9521 | 0.01
5.2214 | 8.6107 | 7.2214 | 6.2214 | 8.8321 | 10.8321 | 8.6107 | 14.8321 | 23.6641 | 34.4962 | 5.2214 | 8.6107 | 7.2214 | 6.2214 | 8.8321 | 10.8421 | 8.6107 | 14.8321 | 23.6641 | 34.5062 | 0.01
5.3992 | 8.6996 | 7.3992 | 6.3992 | 9.0988 | 11.0988 | 8.6996 | 15.0988 | 24.1976 | 35.2965 | 5.3992 | 8.6996 | 7.3992 | 6.3992 | 9.0988 | 11.1088 | 8.6996 | 15.0988 | 24.1976 | 35.3065 | 0.01
9.2618 | 10.6309 | 11.2618 | 10.2618 | 14.8927 | 16.8927 | 10.6309 | 20.8927 | 35.7855 | 52.6782 | 9.2618 | 10.6309 | 11.2618 | 10.2618 | 14.8927 | 16.9027 | 10.6309 | 20.8927 | 35.7855 | 52.6882 | 0.01
2.5164 | 7.2582 | 4.5164 | 3.5164 | 4.7746 | 6.7746 | 7.2582 | 10.7746 | 15.5493 | 22.3239 | 2.5164 | 7.2582 | 4.5164 | 3.5164 | 4.7746 | 6.7846 | 7.2582 | 10.7746 | 15.5493 | 22.3339 | 0.01
6.053 | 9.0265 | 8.053 | 7.053 | 10.0795 | 12.0795 | 9.0265 | 16.0795 | 26.1591 | 38.2386 | 6.053 | 9.0265 | 8.053 | 7.053 | 10.0795 | 12.0895 | 9.0265 | 16.0795 | 26.1591 | 38.2486 | 0.01
11.0086 | 11.5043 | 13.0086 | 12.0086 | 17.5129 | 19.5129 | 11.5043 | 23.5129 | 41.0259 | 60.5388 | 11.0086 | 11.5043 | 13.0086 | 12.0086 | 17.5129 | 19.5229 | 11.5043 | 23.5129 | 41.0259 | 60.5488 | 0.01
9.7368 | 10.8684 | 11.7368 | 10.7368 | 15.6052 | 17.6052 | 10.8684 | 21.6052 | 37.2103 | 54.8155 | 9.7368 | 10.8684 | 11.7368 | 10.7368 | 15.6052 | 17.6152 | 10.8684 | 21.6052 | 37.2103 | 54.8255 | 0.01
9.4739 | 10.7369 | 11.4739 | 10.4739 | 15.2108 | 17.2108 | 10.7369 | 21.2108 | 36.4216 | 53.6323 | 9.4739 | 10.7369 | 11.4739 | 10.4739 | 15.2108 | 17.2208 | 10.7369 | 21.2108 | 36.4216 | 53.6423 | 0.01
4.0971 | 8.0486 | 6.0971 | 5.0971 | 7.1457 | 9.1457 | 8.0486 | 13.1457 | 20.2913 | 29.437 | 4.0971 | 8.0486 | 6.0971 | 5.0971 | 7.1457 | 9.1557 | 8.0486 | 13.1457 | 20.2913 | 29.447 | 0.01
7.1106 | 9.5553 | 9.1106 | 8.1106 | 11.6659 | 13.6659 | 9.5553 | 17.6659 | 29.3318 | 42.9977 | 7.1106 | 9.5553 | 9.1106 | 8.1106 | 11.6659 | 13.6759 | 9.5553 | 17.6659 | 29.3318 | 43.0077 | 0.01
8.668 | 10.334 | 10.668 | 9.668 | 14.0021 | 16.0021 | 10.334 | 20.0021 | 34.0041 | 50.0062 | 8.668 | 10.334 | 10.668 | 9.668 | 14.0021 | 16.0121 | 10.334 | 20.0021 | 34.0041 | 50.0162 | 0.01
5.0877 | 8.5438 | 7.0877 | 6.0877 | 8.6315 | 10.6315 | 8.5438 | 14.6315 | 23.263 | 33.8945 | 5.0877 | 8.5438 | 7.0877 | 6.0877 | 8.6315 | 10.6415 | 8.5438 | 14.6315 | 23.263 | 33.9045 | 0.01
3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.969 | 7.9863 | 12.959 | 19.918 | 28.8869 | 0.01
6.5588 | 9.2794 | 8.5588 | 7.5588 | 10.8382 | 12.8382 | 9.2794 | 16.8382 | 27.6765 | 40.5147 | 6.5588 | 9.2794 | 8.5588 | 7.5588 | 10.8382 | 12.8482 | 9.2794 | 16.8382 | 27.6765 | 40.5247 | 0.01
5.3003 | 8.6502 | 7.3003 | 6.3003 | 8.9505 | 10.9505 | 8.6502 | 14.9505 | 23.901 | 34.8515 | 5.3003 | 8.6502 | 7.3003 | 6.3003 | 8.9505 | 10.9605 | 8.6502 | 14.9505 | 23.901 | 34.8615 | 0.01
5.3086 | 8.6543 | 7.3086 | 6.3086 | 8.9629 | 10.9629 | 8.6543 | 14.9629 | 23.9259 | 34.8888 | 5.3086 | 8.6543 | 7.3086 | 6.3086 | 8.9629 | 10.9729 | 8.6543 | 14.9629 | 23.9259 | 34.8988 | 0.01
4.5764 | 8.2882 | 6.5764 | 5.5764 | 7.8645 | 9.8645 | 8.2882 | 13.8645 | 21.7291 | 31.5936 | 4.5764 | 8.2882 | 6.5764 | 5.5764 | 7.8645 | 9.8745 | 8.2882 | 13.8645 | 21.7291 | 31.6036 | 0.01
5.9923 | 8.9961 | 7.9923 | 6.9923 | 9.9884 | 11.9884 | 8.9961 | 15.9884 | 25.9768 | 37.9652 | 5.9923 | 8.9961 | 7.9923 | 6.9923 | 9.9884 | 11.9984 | 8.9961 | 15.9884 | 25.9768 | 37.9752 | 0.01
2.2553 | 7.1277 | 4.2553 | 3.2553 | 4.383 | 6.383 | 7.1277 | 10.383 | 14.766 | 21.1489 | 2.2553 | 7.1277 | 4.2553 | 3.2553 | 4.383 | 6.393 | 7.1277 | 10.383 | 14.766 | 21.1589 | 0.01
3.77 | 7.885 | 5.77 | 4.77 | 6.6549 | 8.6549 | 7.885 | 12.6549 | 19.3099 | 27.9648 | 3.77 | 7.885 | 5.77 | 4.77 | 6.6549 | 8.6649 | 7.885 | 12.6549 | 19.3099 | 27.9748 | 0.01
5.0845 | 8.5422 | 7.0845 | 6.0845 | 8.6267 | 10.6267 | 8.5422 | 14.6267 | 23.2534 | 33.88 | 5.0845 | 8.5422 | 7.0845 | 6.0845 | 8.6267 | 10.6367 | 8.5422 | 14.6267 | 23.2534 | 33.89 | 0.01
10.4131 | 11.2066 | 12.4131 | 11.4131 | 16.6197 | 18.6197 | 11.2066 | 22.6197 | 39.2394 | 57.8591 | 10.4131 | 11.2066 | 12.4131 | 11.4131 | 16.6197 | 18.6297 | 11.2066 | 22.6197 | 39.2394 | 57.8691 | 0.01
6.5663 | 9.2831 | 8.5663 | 7.5663 | 10.8494 | 12.8494 | 9.2831 | 16.8494 | 27.6989 | 40.5483 | 6.5663 | 9.2831 | 8.5663 | 7.5663 | 10.8494 | 12.8594 | 9.2831 | 16.8494 | 27.6989 | 40.5583 | 0.01
5.6487 | 8.8243 | 7.6487 | 6.6487 | 9.473 | 11.473 | 8.8243 | 15.473 | 24.946 | 36.4191 | 5.6487 | 8.8243 | 7.6487 | 6.6487 | 9.473 | 11.483 | 8.8243 | 15.473 | 24.946 | 36.4291 | 0.01
7.5932 | 9.7966 | 9.5932 | 8.5932 | 12.3899 | 14.3899 | 9.7966 | 18.3899 | 30.7797 | 45.1696 | 7.5932 | 9.7966 | 9.5932 | 8.5932 | 12.3899 | 14.3999 | 9.7966 | 18.3899 | 30.7797 | 45.1796 | 0.01
3.3026 | 7.6513 | 5.3026 | 4.3026 | 5.9539 | 7.9539 | 7.6513 | 11.9539 | 17.9078 | 25.8617 | 3.3026 | 7.6513 | 5.3026 | 4.3026 | 5.9539 | 7.9639 | 7.6513 | 11.9539 | 17.9078 | 25.8717 | 0.01
3.76 | 7.88 | 5.76 | 4.76 | 6.6399 | 8.6399 | 7.88 | 12.6399 | 19.2799 | 27.9198 | 3.76 | 7.88 | 5.76 | 4.76 | 6.6399 | 8.6499 | 7.88 | 12.6399 | 19.2799 | 27.9298 | 0.01
5.8466 | 8.9233 | 7.8466 | 6.8466 | 9.7699 | 11.7699 | 8.9233 | 15.7699 | 25.5399 | 37.3098 | 5.8466 | 8.9233 | 7.8466 | 6.8466 | 9.7699 | 11.7799 | 8.9233 | 15.7699 | 25.5399 | 37.3198 | 0.01
6.6787 | 9.3394 | 8.6787 | 7.6787 | 11.0181 | 13.0181 | 9.3394 | 17.0181 | 28.0362 | 41.0543 | 6.6787 | 9.3394 | 8.6787 | 7.6787 | 11.0181 | 13.0281 | 9.3394 | 17.0181 | 28.0362 | 41.0643 | 0.01
5.4037 | 8.7018 | 7.4037 | 6.4037 | 9.1055 | 11.1055 | 8.7018 | 15.1055 | 24.2111 | 35.3166 | 5.4037 | 8.7018 | 7.4037 | 6.4037 | 9.1055 | 11.1155 | 8.7018 | 15.1055 | 24.2111 | 35.3266 | 0.01
6.474 | 9.237 | 8.474 | 7.474 | 10.711 | 12.711 | 9.237 | 16.711 | 27.4221 | 40.1331 | 6.474 | 9.237 | 8.474 | 7.474 | 10.711 | 12.721 | 9.237 | 16.711 | 27.4221 | 40.1431 | 0.01
6.1767 | 9.0884 | 8.1767 | 7.1767 | 10.2651 | 12.2651 | 9.0884 | 16.2651 | 26.5301 | 38.7952 | 6.1767 | 9.0884 | 8.1767 | 7.1767 | 10.2651 | 12.2751 | 9.0884 | 16.2651 | 26.5301 | 38.8052 | 0.01
6.604 | 9.302 | 8.604 | 7.604 | 10.906 | 12.906 | 9.302 | 16.906 | 27.812 | 40.7179 | 6.604 | 9.302 | 8.604 | 7.604 | 10.906 | 12.916 | 9.302 | 16.906 | 27.812 | 40.7279 | 0.01
4.67 | 8.335 | 6.67 | 5.67 | 8.005 | 10.005 | 8.335 | 14.005 | 22.0101 | 32.0151 | 4.67 | 8.335 | 6.67 | 5.67 | 8.005 | 10.015 | 8.335 | 14.005 | 22.0101 | 32.0251 | 0.01
5.3308 | 8.6654 | 7.3308 | 6.3308 | 8.9962 | 10.9962 | 8.6654 | 14.9962 | 23.9925 | 34.9887 | 5.3308 | 8.6654 | 7.3308 | 6.3308 | 8.9962 | 11.0062 | 8.6654 | 14.9962 | 23.9925 | 34.9987 | 0.01
5.7182 | 8.8591 | 7.7182 | 6.7182 | 9.5774 | 11.5774 | 8.8591 | 15.5774 | 25.1547 | 36.7321 | 5.7182 | 8.8591 | 7.7182 | 6.7182 | 9.5774 | 11.5874 | 8.8591 | 15.5774 | 25.1547 | 36.7421 | 0.01
1.3905 | 6.6952 | 3.3905 | 2.3905 | 3.0857 | 5.0857 | 6.6952 | 9.0857 | 12.1714 | 17.2571 | 1.3905 | 6.6952 | 3.3905 | 2.3905 | 3.0857 | 5.0957 | 6.6952 | 9.0857 | 12.1714 | 17.2671 | 0.01
4.6854 | 8.3427 | 6.6854 | 5.6854 | 8.0282 | 10.0282 | 8.3427 | 14.0282 | 22.0563 | 32.0845 | 4.6854 | 8.3427 | 6.6854 | 5.6854 | 8.0282 | 10.0382 | 8.3427 | 14.0282 | 22.0563 | 32.0945 | 0.01
4.5016 | 8.2508 | 6.5016 | 5.5016 | 7.7525 | 9.7525 | 8.2508 | 13.7525 | 21.5049 | 31.2574 | 4.5016 | 8.2508 | 6.5016 | 5.5016 | 7.7525 | 9.7625 | 8.2508 | 13.7525 | 21.5049 | 31.2674 | 0.01
3.0906 | 7.5453 | 5.0906 | 4.0906 | 5.6359 | 7.6359 | 7.5453 | 11.6359 | 17.2719 | 24.9078 | 3.0906 | 7.5453 | 5.0906 | 4.0906 | 5.6359 | 7.6459 | 7.5453 | 11.6359 | 17.2719 | 24.9178 | 0.01
3.6427 | 7.8213 | 5.6427 | 4.6427 | 6.464 | 8.464 | 7.8213 | 12.464 | 18.928 | 27.392 | 3.6427 | 7.8213 | 5.6427 | 4.6427 | 6.464 | 8.474 | 7.8213 | 12.464 | 18.928 | 27.402 | 0.01
3.7734 | 7.8867 | 5.7734 | 4.7734 | 6.66 | 8.66 | 7.8867 | 12.66 | 19.3201 | 27.9801 | 3.7734 | 7.8867 | 5.7734 | 4.7734 | 6.66 | 8.67 | 7.8867 | 12.66 | 19.3201 | 27.9901 | 0.01
5.5801 | 8.79 | 7.5801 | 6.5801 | 9.3701 | 11.3701 | 8.79 | 15.3701 | 24.7403 | 36.1104 | 5.5801 | 8.79 | 7.5801 | 6.5801 | 9.3701 | 11.3801 | 8.79 | 15.3701 | 24.7403 | 36.1204 | 0.01
7.3028 | 9.6514 | 9.3028 | 8.3028 | 11.9542 | 13.9542 | 9.6514 | 17.9542 | 29.9084 | 43.8626 | 7.3028 | 9.6514 | 9.3028 | 8.3028 | 11.9542 | 13.9642 | 9.6514 | 17.9542 | 29.9084 | 43.8726 | 0.01
4.8107 | 8.4054 | 6.8107 | 5.8107 | 8.2161 | 10.2161 | 8.4054 | 14.2161 | 22.4321 | 32.6482 | 4.8107 | 8.4054 | 6.8107 | 5.8107 | 8.2161 | 10.2261 | 8.4054 | 14.2161 | 22.4321 | 32.6582 | 0.01
6.0516 | 9.0258 | 8.0516 | 7.0516 | 10.0775 | 12.0775 | 9.0258 | 16.0775 | 26.1549 | 38.2324 | 6.0516 | 9.0258 | 8.0516 | 7.0516 | 10.0775 | 12.0875 | 9.0258 | 16.0775 | 26.1549 | 38.2424 | 0.01
7.0705 | 9.5352 | 9.0705 | 8.0705 | 11.6057 | 13.6057 | 9.5352 | 17.6057 | 29.2114 | 42.8171 | 7.0705 | 9.5352 | 9.0705 | 8.0705 | 11.6057 | 13.6157 | 9.5352 | 17.6057 | 29.2114 | 42.8271 | 0.01
7.2568 | 9.6284 | 9.2568 | 8.2568 | 11.8852 | 13.8852 | 9.6284 | 17.8852 | 29.7704 | 43.6556 | 7.2568 | 9.6284 | 9.2568 | 8.2568 | 11.8852 | 13.8952 | 9.6284 | 17.8852 | 29.7704 | 43.6656 | 0.01
5.5195 | 8.7598 | 7.5195 | 6.5195 | 9.2793 | 11.2793 | 8.7598 | 15.2793 | 24.5586 | 35.8378 | 5.5195 | 8.7598 | 7.5195 | 6.5195 | 9.2793 | 11.2893 | 8.7598 | 15.2793 | 24.5586 | 35.8478 | 0.01
7.7236 | 9.8618 | 9.7236 | 8.7236 | 12.5854 | 14.5854 | 9.8618 | 18.5854 | 31.1707 | 45.7561 | 7.7236 | 9.8618 | 9.7236 | 8.7236 | 12.5854 | 14.5954 | 9.8618 | 18.5854 | 31.1707 | 45.7661 | 0.01
7.4454 | 9.7227 | 9.4454 | 8.4454 | 12.1681 | 14.1681 | 9.7227 | 18.1681 | 30.3362 | 44.5043 | 7.4454 | 9.7227 | 9.4454 | 8.4454 | 12.1681 | 14.1781 | 9.7227 | 18.1681 | 30.3362 | 44.5143 | 0.01
7.2098 | 9.6049 | 9.2098 | 8.2098 | 11.8147 | 13.8147 | 9.6049 | 17.8147 | 29.6294 | 43.4441 | 7.2098 | 9.6049 | 9.2098 | 8.2098 | 11.8147 | 13.8247 | 9.6049 | 17.8147 | 29.6294 | 43.4541 | 0.01
8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0815 | 10.0238 | 19.0715 | 32.143 | 47.2244 | 0.01
5.3983 | 8.6991 | 7.3983 | 6.3983 | 9.0974 | 11.0974 | 8.6991 | 15.0974 | 24.1948 | 35.2922 | 5.3983 | 8.6991 | 7.3983 | 6.3983 | 9.0974 | 11.1074 | 8.6991 | 15.0974 | 24.1948 | 35.3022 | 0.01
8.1214 | 10.0607 | 10.1214 | 9.1214 | 13.1821 | 15.1821 | 10.0607 | 19.1821 | 32.3642 | 47.5463 | 8.1214 | 10.0607 | 10.1214 | 9.1214 | 13.1821 | 15.1921 | 10.0607 | 19.1821 | 32.3642 | 47.5563 | 0.01
5.6079 | 8.8039 | 7.6079 | 6.6079 | 9.4118 | 11.4118 | 8.8039 | 15.4118 | 24.8237 | 36.2355 | 5.6079 | 8.8039 | 7.6079 | 6.6079 | 9.4118 | 11.4218 | 8.8039 | 15.4118 | 24.8237 | 36.2455 | 0.01
6.4616 | 9.2308 | 8.4616 | 7.4616 | 10.6924 | 12.6924 | 9.2308 | 16.6924 | 27.3848 | 40.0772 | 6.4616 | 9.2308 | 8.4616 | 7.4616 | 10.6924 | 12.7024 | 9.2308 | 16.6924 | 27.3848 | 40.0872 | 0.01
5.8819 | 8.9409 | 7.8819 | 6.8819 | 9.8228 | 11.8228 | 8.9409 | 15.8228 | 25.6457 | 37.4685 | 5.8819 | 8.9409 | 7.8819 | 6.8819 | 9.8228 | 11.8328 | 8.9409 | 15.8228 | 25.6457 | 37.4785 | 0.01
3.8915 | 7.9457 | 5.8915 | 4.8915 | 6.8372 | 8.8372 | 7.9457 | 12.8372 | 19.6744 | 28.5115 | 3.8915 | 7.9457 | 5.8915 | 4.8915 | 6.8372 | 8.8472 | 7.9457 | 12.8372 | 19.6744 | 28.5215 | 0.01
3.9971 | 7.9985 | 5.9971 | 4.9971 | 6.9956 | 8.9956 | 7.9985 | 12.9956 | 19.9912 | 28.9868 | 3.9971 | 7.9985 | 5.9971 | 4.9971 | 6.9956 | 9.0056 | 7.9985 | 12.9956 | 19.9912 | 28.9968 | 0.01
6.3642 | 9.1821 | 8.3642 | 7.3642 | 10.5463 | 12.5463 | 9.1821 | 16.5463 | 27.0927 | 39.639 | 6.3642 | 9.1821 | 8.3642 | 7.3642 | 10.5463 | 12.5563 | 9.1821 | 16.5463 | 27.0927 | 39.649 | 0.01
9.0628 | 10.5314 | 11.0628 | 10.0628 | 14.5941 | 16.5941 | 10.5314 | 20.5941 | 35.1883 | 51.7824 | 9.0628 | 10.5314 | 11.0628 | 10.0628 | 14.5941 | 16.6041 | 10.5314 | 20.5941 | 35.1883 | 51.7924 | 0.01
6.7215 | 9.3608 | 8.7215 | 7.7215 | 11.0823 | 13.0823 | 9.3608 | 17.0823 | 28.1645 | 41.2468 | 6.7215 | 9.3608 | 8.7215 | 7.7215 | 11.0823 | 13.0923 | 9.3608 | 17.0823 | 28.1645 | 41.2568 | 0.01
7.5347 | 9.7673 | 9.5347 | 8.5347 | 12.302 | 14.302 | 9.7673 | 18.302 | 30.604 | 44.906 | 7.5347 | 9.7673 | 9.5347 | 8.5347 | 12.302 | 14.312 | 9.7673 | 18.302 | 30.604 | 44.916 | 0.01
4.2203 | 8.1102 | 6.2203 | 5.2203 | 7.3305 | 9.3305 | 8.1102 | 13.3305 | 20.6609 | 29.9914 | 4.2203 | 8.1102 | 6.2203 | 5.2203 | 7.3305 | 9.3405 | 8.1102 | 13.3305 | 20.6609 | 30.0014 | 0.01
4.9198 | 8.4599 | 6.9198 | 5.9198 | 8.3797 | 10.3797 | 8.4599 | 14.3797 | 22.7594 | 33.1391 | 4.9198 | 8.4599 | 6.9198 | 5.9198 | 8.3797 | 10.3897 | 8.4599 | 14.3797 | 22.7594 | 33.1491 | 0.01
3.252 | 7.626 | 5.252 | 4.252 | 5.878 | 7.878 | 7.626 | 11.878 | 17.7559 | 25.6339 | 3.252 | 7.626 | 5.252 | 4.252 | 5.878 | 7.888 | 7.626 | 11.878 | 17.7559 | 25.6439 | 0.01
6.2071 | 9.1036 | 8.2071 | 7.2071 | 10.3107 | 12.3107 | 9.1036 | 16.3107 | 26.6214 | 38.9322 | 6.2071 | 9.1036 | 8.2071 | 7.2071 | 10.3107 | 12.3207 | 9.1036 | 16.3107 | 26.6214 | 38.9422 | 0.01
6.9816 | 9.4908 | 8.9816 | 7.9816 | 11.4725 | 13.4725 | 9.4908 | 17.4725 | 28.9449 | 42.4174 | 6.9816 | 9.4908 | 8.9816 | 7.9816 | 11.4725 | 13.4825 | 9.4908 | 17.4725 | 28.9449 | 42.4274 | 0.01
4.3537 | 8.1768 | 6.3537 | 5.3537 | 7.5305 | 9.5305 | 8.1768 | 13.5305 | 21.061 | 30.5915 | 4.3537 | 8.1768 | 6.3537 | 5.3537 | 7.5305 | 9.5405 | 8.1768 | 13.5305 | 21.061 | 30.6015 | 0.01
7.4024 | 9.7012 | 9.4024 | 8.4024 | 12.1036 | 14.1036 | 9.7012 | 18.1036 | 30.2073 | 44.3109 | 7.4024 | 9.7012 | 9.4024 | 8.4024 | 12.1036 | 14.1136 | 9.7012 | 18.1036 | 30.2073 | 44.3209 | 0.01
5.2403 | 8.6202 | 7.2403 | 6.2403 | 8.8605 | 10.8605 | 8.6202 | 14.8605 | 23.7209 | 34.5814 | 5.2403 | 8.6202 | 7.2403 | 6.2403 | 8.8605 | 10.8705 | 8.6202 | 14.8605 | 23.7209 | 34.5914 | 0.01
6.5781 | 9.289 | 8.5781 | 7.5781 | 10.8671 | 12.8671 | 9.289 | 16.8671 | 27.7343 | 40.6014 | 6.5781 | 9.289 | 8.5781 | 7.5781 | 10.8671 | 12.8771 | 9.289 | 16.8671 | 27.7343 | 40.6114 | 0.01
7.6429 | 9.8215 | 9.6429 | 8.6429 | 12.4644 | 14.4644 | 9.8215 | 18.4644 | 30.9287 | 45.3931 | 7.6429 | 9.8215 | 9.6429 | 8.6429 | 12.4644 | 14.4744 | 9.8215 | 18.4644 | 30.9287 | 45.4031 | 0.01
6.3829 | 9.1915 | 8.3829 | 7.3829 | 10.5744 | 12.5744 | 9.1915 | 16.5744 | 27.1487 | 39.7231 | 6.3829 | 9.1915 | 8.3829 | 7.3829 | 10.5744 | 12.5844 | 9.1915 | 16.5744 | 27.1487 | 39.7331 | 0.01
3.4405 | 7.7202 | 5.4405 | 4.4405 | 6.1607 | 8.1607 | 7.7202 | 12.1607 | 18.3214 | 26.4821 | 3.4405 | 7.7202 | 5.4405 | 4.4405 | 6.1607 | 8.1707 | 7.7202 | 12.1607 | 18.3214 | 26.4921 | 0.01
8.5773 | 10.2887 | 10.5773 | 9.5773 | 13.866 | 15.866 | 10.2887 | 19.866 | 33.732 | 49.598 | 8.5773 | 10.2887 | 10.5773 | 9.5773 | 13.866 | 15.876 | 10.2887 | 19.866 | 33.732 | 49.608 | 0.01
8.9551 | 10.4775 | 10.9551 | 9.9551 | 14.4326 | 16.4326 | 10.4775 | 20.4326 | 34.8653 | 51.2979 | 8.9551 | 10.4775 | 10.9551 | 9.9551 | 14.4326 | 16.4426 | 10.4775 | 20.4326 | 34.8653 | 51.3079 | 0.01
5.4187 | 8.7094 | 7.4187 | 6.4187 | 9.1281 | 11.1281 | 8.7094 | 15.1281 | 24.2561 | 35.3842 | 5.4187 | 8.7094 | 7.4187 | 6.4187 | 9.1281 | 11.1381 | 8.7094 | 15.1281 | 24.2561 | 35.3942 | 0.01
5.3886 | 8.6943 | 7.3886 | 6.3886 | 9.083 | 11.083 | 8.6943 | 15.083 | 24.1659 | 35.2489 | 5.3886 | 8.6943 | 7.3886 | 6.3886 | 9.083 | 11.093 | 8.6943 | 15.083 | 24.1659 | 35.2589 | 0.01
8.0894 | 10.0447 | 10.0894 | 9.0894 | 13.1342 | 15.1342 | 10.0447 | 19.1342 | 32.2683 | 47.4025 | 8.0894 | 10.0447 | 10.0894 | 9.0894 | 13.1342 | 15.1442 | 10.0447 | 19.1342 | 32.2683 | 47.4125 | 0.01
9.5481 | 10.7741 | 11.5481 | 10.5481 | 15.3222 | 17.3222 | 10.7741 | 21.3222 | 36.6444 | 53.9666 | 9.5481 | 10.7741 | 11.5481 | 10.5481 | 15.3222 | 17.3322 | 10.7741 | 21.3222 | 36.6444 | 53.9766 | 0.01
8.3839 | 10.1919 | 10.3839 | 9.3839 | 13.5758 | 15.5758 | 10.1919 | 19.5758 | 33.1517 | 48.7275 | 8.3839 | 10.1919 | 10.3839 | 9.3839 | 13.5758 | 15.5858 | 10.1919 | 19.5758 | 33.1517 | 48.7375 | 0.01
5.3671 | 8.6836 | 7.3671 | 6.3671 | 9.0507 | 11.0507 | 8.6836 | 15.0507 | 24.1014 | 35.1521 | 5.3671 | 8.6836 | 7.3671 | 6.3671 | 9.0507 | 11.0607 | 8.6836 | 15.0507 | 24.1014 | 35.1621 | 0.01
6.4787 | 9.2394 | 8.4787 | 7.4787 | 10.7181 | 12.7181 | 9.2394 | 16.7181 | 27.4362 | 40.1544 | 6.4787 | 9.2394 | 8.4787 | 7.4787 | 10.7181 | 12.7281 | 9.2394 | 16.7181 | 27.4362 | 40.1644 | 0.01
9.3042 | 10.6521 | 11.3042 | 10.3042 | 14.9563 | 16.9563 | 10.6521 | 20.9563 | 35.9126 | 52.8689 | 9.3042 | 10.6521 | 11.3042 | 10.3042 | 14.9563 | 16.9663 | 10.6521 | 20.9563 | 35.9126 | 52.8789 | 0.01
2.544 | 7.272 | 4.544 | 3.544 | 4.816 | 6.816 | 7.272 | 10.816 | 15.632 | 22.448 | 2.544 | 7.272 | 4.544 | 3.544 | 4.816 | 6.826 | 7.272 | 10.816 | 15.632 | 22.458 | 0.01
4.3068 | 8.1534 | 6.3068 | 5.3068 | 7.4603 | 9.4603 | 8.1534 | 13.4603 | 20.9205 | 30.3808 | 4.3068 | 8.1534 | 6.3068 | 5.3068 | 7.4603 | 9.4703 | 8.1534 | 13.4603 | 20.9205 | 30.3908 | 0.01
4.3765 | 8.1883 | 6.3765 | 5.3765 | 7.5648 | 9.5648 | 8.1883 | 13.5648 | 21.1296 | 30.6944 | 4.3765 | 8.1883 | 6.3765 | 5.3765 | 7.5648 | 9.5748 | 8.1883 | 13.5648 | 21.1296 | 30.7044 | 0.01
8.9067 | 10.4534 | 10.9067 | 9.9067 | 14.3601 | 16.3601 | 10.4534 | 20.3601 | 34.7202 | 51.0803 | 8.9067 | 10.4534 | 10.9067 | 9.9067 | 14.3601 | 16.3701 | 10.4534 | 20.3601 | 34.7202 | 51.0903 | 0.01
5.8313 | 8.9156 | 7.8313 | 6.8313 | 9.7469 | 11.7469 | 8.9156 | 15.7469 | 25.4938 | 37.2407 | 5.8313 | 8.9156 | 7.8313 | 6.8313 | 9.7469 | 11.7569 | 8.9156 | 15.7469 | 25.4938 | 37.2507 | 0.01
5.7318 | 8.8659 | 7.7318 | 6.7318 | 9.5978 | 11.5978 | 8.8659 | 15.5978 | 25.1955 | 36.7933 | 5.7318 | 8.8659 | 7.7318 | 6.7318 | 9.5978 | 11.6078 | 8.8659 | 15.5978 | 25.1955 | 36.8033 | 0.01
4.0139 | 8.007 | 6.0139 | 5.0139 | 7.0209 | 9.0209 | 8.007 | 13.0209 | 20.0417 | 29.0626 | 4.0139 | 8.007 | 6.0139 | 5.0139 | 7.0209 | 9.0309 | 8.007 | 13.0209 | 20.0417 | 29.0726 | 0.01
4.3425 | 8.1712 | 6.3425 | 5.3425 | 7.5137 | 9.5137 | 8.1712 | 13.5137 | 21.0274 | 30.5411 | 4.3425 | 8.1712 | 6.3425 | 5.3425 | 7.5137 | 9.5237 | 8.1712 | 13.5137 | 21.0274 | 30.5511 | 0.01
6.3885 | 9.1943 | 8.3885 | 7.3885 | 10.5828 | 12.5828 | 9.1943 | 16.5828 | 27.1656 | 39.7483 | 6.3885 | 9.1943 | 8.3885 | 7.3885 | 10.5828 | 12.5928 | 9.1943 | 16.5828 | 27.1656 | 39.7583 | 0.01
4.828 | 8.414 | 6.828 | 5.828 | 8.242 | 10.242 | 8.414 | 14.242 | 22.484 | 32.726 | 4.828 | 8.414 | 6.828 | 5.828 | 8.242 | 10.252 | 8.414 | 14.242 | 22.484 | 32.736 | 0.01
4.4034 | 8.2017 | 6.4034 | 5.4034 | 7.6051 | 9.6051 | 8.2017 | 13.6051 | 21.2102 | 30.8153 | 4.4034 | 8.2017 | 6.4034 | 5.4034 | 7.6051 | 9.6151 | 8.2017 | 13.6051 | 21.2102 | 30.8253 | 0.01
4.8238 | 8.4119 | 6.8238 | 5.8238 | 8.2357 | 10.2357 | 8.4119 | 14.2357 | 22.4715 | 32.7072 | 4.8238 | 8.4119 | 6.8238 | 5.8238 | 8.2357 | 10.2457 | 8.4119 | 14.2357 | 22.4715 | 32.7172 | 0.01
2.2571 | 7.1285 | 4.2571 | 3.2571 | 4.3856 | 6.3856 | 7.1285 | 10.3856 | 14.7713 | 21.1569 | 2.2571 | 7.1285 | 4.2571 | 3.2571 | 4.3856 | 6.3956 | 7.1285 | 10.3856 | 14.7713 | 21.1669 | 0.01
7.5318 | 9.7659 | 9.5318 | 8.5318 | 12.2977 | 14.2977 | 9.7659 | 18.2977 | 30.5954 | 44.8931 | 7.5318 | 9.7659 | 9.5318 | 8.5318 | 12.2977 | 14.3077 | 9.7659 | 18.2977 | 30.5954 | 44.9031 | 0.01
5.7824 | 8.8912 | 7.7824 | 6.7824 | 9.6736 | 11.6736 | 8.8912 | 15.6736 | 25.3472 | 37.0208 | 5.7824 | 8.8912 | 7.7824 | 6.7824 | 9.6736 | 11.6836 | 8.8912 | 15.6736 | 25.3472 | 37.0308 | 0.01
5.2454 | 8.6227 | 7.2454 | 6.2454 | 8.8681 | 10.8681 | 8.6227 | 14.8681 | 23.7362 | 34.6043 | 5.2454 | 8.6227 | 7.2454 | 6.2454 | 8.8681 | 10.8781 | 8.6227 | 14.8681 | 23.7362 | 34.6143 | 0.01
4.8561 | 8.428 | 6.8561 | 5.8561 | 8.2841 | 10.2841 | 8.428 | 14.2841 | 22.5682 | 32.8522 | 4.8561 | 8.428 | 6.8561 | 5.8561 | 8.2841 | 10.2941 | 8.428 | 14.2841 | 22.5682 | 32.8622 | 0.01
8.4147 | 10.2073 | 10.4147 | 9.4147 | 13.622 | 15.622 | 10.2073 | 19.622 | 33.244 | 48.866 | 8.4147 | 10.2073 | 10.4147 | 9.4147 | 13.622 | 15.632 | 10.2073 | 19.622 | 33.244 | 48.876 | 0.01
6.6838 | 9.3419 | 8.6838 | 7.6838 | 11.0256 | 13.0256 | 9.3419 | 17.0256 | 28.0513 | 41.0769 | 6.6838 | 9.3419 | 8.6838 | 7.6838 | 11.0256 | 13.0356 | 9.3419 | 17.0256 | 28.0513 | 41.0869 | 0.01
0.96635 | 6.4832 | 2.9663 | 1.9663 | 2.4495 | 4.4495 | 6.4832 | 8.4495 | 10.899 | 15.3486 | 0.96635 | 6.4832 | 2.9663 | 1.9663 | 2.4495 | 4.4595 | 6.4832 | 8.4495 | 10.899 | 15.3586 | 0.01
7.0703 | 9.5351 | 9.0703 | 8.0703 | 11.6054 | 13.6054 | 9.5351 | 17.6054 | 29.2109 | 42.8163 | 7.0703 | 9.5351 | 9.0703 | 8.0703 | 11.6054 | 13.6154 | 9.5351 | 17.6054 | 29.2109 | 42.8263 | 0.01
7.017 | 9.5085 | 9.017 | 8.017 | 11.5255 | 13.5255 | 9.5085 | 17.5255 | 29.051 | 42.5765 | 7.017 | 9.5085 | 9.017 | 8.017 | 11.5255 | 13.5355 | 9.5085 | 17.5255 | 29.051 | 42.5865 | 0.01
5.4393 | 8.7196 | 7.4393 | 6.4393 | 9.1589 | 11.1589 | 8.7196 | 15.1589 | 24.3178 | 35.4767 | 5.4393 | 8.7196 | 7.4393 | 6.4393 | 9.1589 | 11.1689 | 8.7196 | 15.1589 | 24.3178 | 35.4867 | 0.01
2.5841 | 7.2921 | 4.5841 | 3.5841 | 4.8762 | 6.8762 | 7.2921 | 10.8762 | 15.7524 | 22.6286 | 2.5841 | 7.2921 | 4.5841 | 3.5841 | 4.8762 | 6.8862 | 7.2921 | 10.8762 | 15.7524 | 22.6386 | 0.01
3.8108 | 7.9054 | 5.8108 | 4.8108 | 6.7162 | 8.7162 | 7.9054 | 12.7162 | 19.4324 | 28.1486 | 3.8108 | 7.9054 | 5.8108 | 4.8108 | 6.7162 | 8.7262 | 7.9054 | 12.7162 | 19.4324 | 28.1586 | 0.01
5.3143 | 8.6572 | 7.3143 | 6.3143 | 8.9715 | 10.9715 | 8.6572 | 14.9715 | 23.9429 | 34.9144 | 5.3143 | 8.6572 | 7.3143 | 6.3143 | 8.9715 | 10.9815 | 8.6572 | 14.9715 | 23.9429 | 34.9244 | 0.01
6.6577 | 9.3288 | 8.6577 | 7.6577 | 10.9865 | 12.9865 | 9.3288 | 16.9865 | 27.9731 | 40.9596 | 6.6577 | 9.3288 | 8.6577 | 7.6577 | 10.9865 | 12.9965 | 9.3288 | 16.9865 | 27.9731 | 40.9696 | 0.01
3.0098 | 7.5049 | 5.0098 | 4.0098 | 5.5147 | 7.5147 | 7.5049 | 11.5147 | 17.0295 | 24.5442 | 3.0098 | 7.5049 | 5.0098 | 4.0098 | 5.5147 | 7.5247 | 7.5049 | 11.5147 | 17.0295 | 24.5542 | 0.01
5.1527 | 8.5764 | 7.1527 | 6.1527 | 8.7291 | 10.7291 | 8.5764 | 14.7291 | 23.4582 | 34.1873 | 5.1527 | 8.5764 | 7.1527 | 6.1527 | 8.7291 | 10.7391 | 8.5764 | 14.7291 | 23.4582 | 34.1973 | 0.01
5.8825 | 8.9413 | 7.8825 | 6.8825 | 9.8238 | 11.8238 | 8.9413 | 15.8238 | 25.6475 | 37.4713 | 5.8825 | 8.9413 | 7.8825 | 6.8825 | 9.8238 | 11.8338 | 8.9413 | 15.8238 | 25.6475 | 37.4813 | 0.01
6.6117 | 9.3058 | 8.6117 | 7.6117 | 10.9175 | 12.9175 | 9.3058 | 16.9175 | 27.835 | 40.7525 | 6.6117 | 9.3058 | 8.6117 | 7.6117 | 10.9175 | 12.9275 | 9.3058 | 16.9175 | 27.835 | 40.7625 | 0.01
7.5536 | 9.7768 | 9.5536 | 8.5536 | 12.3304 | 14.3304 | 9.7768 | 18.3304 | 30.6609 | 44.9913 | 7.5536 | 9.7768 | 9.5536 | 8.5536 | 12.3304 | 14.3404 | 9.7768 | 18.3304 | 30.6609 | 45.0013 | 0.01
3.9811 | 7.9905 | 5.9811 | 4.9811 | 6.9716 | 8.9716 | 7.9905 | 12.9716 | 19.9432 | 28.9148 | 3.9811 | 7.9905 | 5.9811 | 4.9811 | 6.9716 | 8.9816 | 7.9905 | 12.9716 | 19.9432 | 28.9248 | 0.01
2.7565 | 7.3783 | 4.7565 | 3.7565 | 5.1348 | 7.1348 | 7.3783 | 11.1348 | 16.2696 | 23.4044 | 2.7565 | 7.3783 | 4.7565 | 3.7565 | 5.1348 | 7.1448 | 7.3783 | 11.1348 | 16.2696 | 23.4144 | 0.01
1.279 | 6.6395 | 3.279 | 2.279 | 2.9185 | 4.9185 | 6.6395 | 8.9185 | 11.837 | 16.7555 | 1.279 | 6.6395 | 3.279 | 2.279 | 2.9185 | 4.9285 | 6.6395 | 8.9185 | 11.837 | 16.7655 | 0.01
6.3987 | 9.1993 | 8.3987 | 7.3987 | 10.598 | 12.598 | 9.1993 | 16.598 | 27.196 | 39.794 | 6.3987 | 9.1993 | 8.3987 | 7.3987 | 10.598 | 12.608 | 9.1993 | 16.598 | 27.196 | 39.804 | 0.01
8.8962 | 10.4481 | 10.8962 | 9.8962 | 14.3443 | 16.3443 | 10.4481 | 20.3443 | 34.6886 | 51.033 | 8.8962 | 10.4481 | 10.8962 | 9.8962 | 14.3443 | 16.3543 | 10.4481 | 20.3443 | 34.6886 | 51.043 | 0.01
3.2532 | 7.6266 | 5.2532 | 4.2532 | 5.8797 | 7.8797 | 7.6266 | 11.8797 | 17.7595 | 25.6392 | 3.2532 | 7.6266 | 5.2532 | 4.2532 | 5.8797 | 7.8897 | 7.6266 | 11.8797 | 17.7595 | 25.6492 | 0.01
5.4748 | 8.7374 | 7.4748 | 6.4748 | 9.2122 | 11.2122 | 8.7374 | 15.2122 | 24.4245 | 35.6367 | 5.4748 | 8.7374 | 7.4748 | 6.4748 | 9.2122 | 11.2222 | 8.7374 | 15.2122 | 24.4245 | 35.6467 | 0.01
5.6701 | 8.8351 | 7.6701 | 6.6701 | 9.5052 | 11.5052 | 8.8351 | 15.5052 | 25.0103 | 36.5155 | 5.6701 | 8.8351 | 7.6701 | 6.6701 | 9.5052 | 11.5152 | 8.8351 | 15.5052 | 25.0103 | 36.5255 | 0.01
8.5124 | 10.2562 | 10.5124 | 9.5124 | 13.7685 | 15.7685 | 10.2562 | 19.7685 | 33.5371 | 49.3056 | 8.5124 | 10.2562 | 10.5124 | 9.5124 | 13.7685 | 15.7785 | 10.2562 | 19.7685 | 33.5371 | 49.3156 | 0.01
7.7278 | 9.8639 | 9.7278 | 8.7278 | 12.5917 | 14.5917 | 9.8639 | 18.5917 | 31.1834 | 45.7751 | 7.7278 | 9.8639 | 9.7278 | 8.7278 | 12.5917 | 14.6017 | 9.8639 | 18.5917 | 31.1834 | 45.7851 | 0.01
6.6958 | 9.3479 | 8.6958 | 7.6958 | 11.0437 | 13.0437 | 9.3479 | 17.0437 | 28.0873 | 41.131 | 6.6958 | 9.3479 | 8.6958 | 7.6958 | 11.0437 | 13.0537 | 9.3479 | 17.0437 | 28.0873 | 41.141 | 0.01
6.6747 | 9.3373 | 8.6747 | 7.6747 | 11.012 | 13.012 | 9.3373 | 17.012 | 28.024 | 41.036 | 6.6747 | 9.3373 | 8.6747 | 7.6747 | 11.012 | 13.022 | 9.3373 | 17.012 | 28.024 | 41.046 | 0.01
4.1136 | 8.0568 | 6.1136 | 5.1136 | 7.1705 | 9.1705 | 8.0568 | 13.1705 | 20.3409 | 29.5114 | 4.1136 | 8.0568 | 6.1136 | 5.1136 | 7.1705 | 9.1805 | 8.0568 | 13.1705 | 20.3409 | 29.5214 | 0.01
6.0322 | 9.0161 | 8.0322 | 7.0322 | 10.0483 | 12.0483 | 9.0161 | 16.0483 | 26.0966 | 38.1449 | 6.0322 | 9.0161 | 8.0322 | 7.0322 | 10.0483 | 12.0583 | 9.0161 | 16.0483 | 26.0966 | 38.1549 | 0.01
6.0533 | 9.0267 | 8.0533 | 7.0533 | 10.08 | 12.08 | 9.0267 | 16.08 | 26.16 | 38.24 | 6.0533 | 9.0267 | 8.0533 | 7.0533 | 10.08 | 12.09 | 9.0267 | 16.08 | 26.16 | 38.25 | 0.01
5.3099 | 8.655 | 7.3099 | 6.3099 | 8.9649 | 10.9649 | 8.655 | 14.9649 | 23.9298 | 34.8946 | 5.3099 | 8.655 | 7.3099 | 6.3099 | 8.9649 | 10.9749 | 8.655 | 14.9649 | 23.9298 | 34.9046 | 0.01
2.783 | 7.3915 | 4.783 | 3.783 | 5.1746 | 7.1746 | 7.3915 | 11.1746 | 16.3491 | 23.5237 | 2.783 | 7.3915 | 4.783 | 3.783 | 5.1746 | 7.1846 | 7.3915 | 11.1746 | 16.3491 | 23.5337 | 0.01
4.1082 | 8.0541 | 6.1082 | 5.1082 | 7.1622 | 9.1622 | 8.0541 | 13.1622 | 20.3245 | 29.4867 | 4.1082 | 8.0541 | 6.1082 | 5.1082 | 7.1622 | 9.1722 | 8.0541 | 13.1622 | 20.3245 | 29.4967 | 0.01
9.1167 | 10.5584 | 11.1167 | 10.1167 | 14.6751 | 16.6751 | 10.5584 | 20.6751 | 35.3502 | 52.0254 | 9.1167 | 10.5584 | 11.1167 | 10.1167 | 14.6751 | 16.6851 | 10.5584 | 20.6751 | 35.3502 | 52.0354 | 0.01
7.2546 | 9.6273 | 9.2546 | 8.2546 | 11.8819 | 13.8819 | 9.6273 | 17.8819 | 29.7637 | 43.6456 | 7.2546 | 9.6273 | 9.2546 | 8.2546 | 11.8819 | 13.8919 | 9.6273 | 17.8819 | 29.7637 | 43.6556 | 0.01
3.9195 | 7.9598 | 5.9195 | 4.9195 | 6.8793 | 8.8793 | 7.9598 | 12.8793 | 19.7585 | 28.6378 | 3.9195 | 7.9598 | 5.9195 | 4.9195 | 6.8793 | 8.8893 | 7.9598 | 12.8793 | 19.7585 | 28.6478 | 0.01
7.2151 | 9.6076 | 9.2151 | 8.2151 | 11.8227 | 13.8227 | 9.6076 | 17.8227 | 29.6454 | 43.4681 | 7.2151 | 9.6076 | 9.2151 | 8.2151 | 11.8227 | 13.8327 | 9.6076 | 17.8227 | 29.6454 | 43.4781 | 0.01
5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.1014 | 8.6971 | 15.0914 | 24.1828 | 35.2841 | 0.01
4.1806 | 8.0903 | 6.1806 | 5.1806 | 7.2709 | 9.2709 | 8.0903 | 13.2709 | 20.5419 | 29.8128 | 4.1806 | 8.0903 | 6.1806 | 5.1806 | 7.2709 | 9.2809 | 8.0903 | 13.2709 | 20.5419 | 29.8228 | 0.01
4.4304 | 8.2152 | 6.4304 | 5.4304 | 7.6456 | 9.6456 | 8.2152 | 13.6456 | 21.2912 | 30.9368 | 4.4304 | 8.2152 | 6.4304 | 5.4304 | 7.6456 | 9.6556 | 8.2152 | 13.6456 | 21.2912 | 30.9468 | 0.01
4.0583 | 8.0291 | 6.0583 | 5.0583 | 7.0874 | 9.0874 | 8.0291 | 13.0874 | 20.1748 | 29.2622 | 4.0583 | 8.0291 | 6.0583 | 5.0583 | 7.0874 | 9.0974 | 8.0291 | 13.0874 | 20.1748 | 29.2722 | 0.01
6.3386 | 9.1693 | 8.3386 | 7.3386 | 10.5079 | 12.5079 | 9.1693 | 16.5079 | 27.0158 | 39.5236 | 6.3386 | 9.1693 | 8.3386 | 7.3386 | 10.5079 | 12.5179 | 9.1693 | 16.5079 | 27.0158 | 39.5336 | 0.01
8.3318 | 10.1659 | 10.3318 | 9.3318 | 13.4977 | 15.4977 | 10.1659 | 19.4977 | 32.9953 | 48.493 | 8.3318 | 10.1659 | 10.3318 | 9.3318 | 13.4977 | 15.5077 | 10.1659 | 19.4977 | 32.9953 | 48.503 | 0.01
3.4866 | 7.7433 | 5.4866 | 4.4866 | 6.23 | 8.23 | 7.7433 | 12.23 | 18.4599 | 26.6899 | 3.4866 | 7.7433 | 5.4866 | 4.4866 | 6.23 | 8.24 | 7.7433 | 12.23 | 18.4599 | 26.6999 | 0.01
5.145 | 8.5725 | 7.145 | 6.145 | 8.7175 | 10.7175 | 8.5725 | 14.7175 | 23.4351 | 34.1526 | 5.145 | 8.5725 | 7.145 | 6.145 | 8.7175 | 10.7275 | 8.5725 | 14.7175 | 23.4351 | 34.1626 | 0.01
4.7066 | 8.3533 | 6.7066 | 5.7066 | 8.06 | 10.06 | 8.3533 | 14.06 | 22.1199 | 32.1799 | 4.7066 | 8.3533 | 6.7066 | 5.7066 | 8.06 | 10.07 | 8.3533 | 14.06 | 22.1199 | 32.1899 | 0.01
3.6298 | 7.8149 | 5.6298 | 4.6298 | 6.4446 | 8.4446 | 7.8149 | 12.4446 | 18.8893 | 27.3339 | 3.6298 | 7.8149 | 5.6298 | 4.6298 | 6.4446 | 8.4546 | 7.8149 | 12.4446 | 18.8893 | 27.3439 | 0.01
7.1394 | 9.5697 | 9.1394 | 8.1394 | 11.7092 | 13.7092 | 9.5697 | 17.7092 | 29.4183 | 43.1275 | 7.1394 | 9.5697 | 9.1394 | 8.1394 | 11.7092 | 13.7192 | 9.5697 | 17.7092 | 29.4183 | 43.1375 | 0.01
6.9539 | 9.477 | 8.9539 | 7.9539 | 11.4309 | 13.4309 | 9.477 | 17.4309 | 28.8618 | 42.2928 | 6.9539 | 9.477 | 8.9539 | 7.9539 | 11.4309 | 13.4409 | 9.477 | 17.4309 | 28.8618 | 42.3028 | 0.01
3.8824 | 7.9412 | 5.8824 | 4.8824 | 6.8235 | 8.8235 | 7.9412 | 12.8235 | 19.6471 | 28.4706 | 3.8824 | 7.9412 | 5.8824 | 4.8824 | 6.8235 | 8.8335 | 7.9412 | 12.8235 | 19.6471 | 28.4806 | 0.01
4.5081 | 8.2541 | 6.5081 | 5.5081 | 7.7622 | 9.7622 | 8.2541 | 13.7622 | 21.5243 | 31.2865 | 4.5081 | 8.2541 | 6.5081 | 5.5081 | 7.7622 | 9.7722 | 8.2541 | 13.7622 | 21.5243 | 31.2965 | 0.01
5.4401 | 8.72 | 7.4401 | 6.4401 | 9.1601 | 11.1601 | 8.72 | 15.1601 | 24.3202 | 35.4803 | 5.4401 | 8.72 | 7.4401 | 6.4401 | 9.1601 | 11.1701 | 8.72 | 15.1601 | 24.3202 | 35.4903 | 0.01
7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8418 | 9.6106 | 17.8318 | 29.6636 | 43.5055 | 0.01
6.3068 | 9.1534 | 8.3068 | 7.3068 | 10.4602 | 12.4602 | 9.1534 | 16.4602 | 26.9204 | 39.3807 | 6.3068 | 9.1534 | 8.3068 | 7.3068 | 10.4602 | 12.4702 | 9.1534 | 16.4602 | 26.9204 | 39.3907 | 0.01
2.4541 | 7.227 | 4.4541 | 3.4541 | 4.6811 | 6.6811 | 7.227 | 10.6811 | 15.3622 | 22.0434 | 2.4541 | 7.227 | 4.4541 | 3.4541 | 4.6811 | 6.6911 | 7.227 | 10.6811 | 15.3622 | 22.0534 | 0.01
6.616 | 9.308 | 8.616 | 7.616 | 10.924 | 12.924 | 9.308 | 16.924 | 27.848 | 40.772 | 6.616 | 9.308 | 8.616 | 7.616 | 10.924 | 12.934 | 9.308 | 16.924 | 27.848 | 40.782 | 0.01
6.1816 | 9.0908 | 8.1816 | 7.1816 | 10.2724 | 12.2724 | 9.0908 | 16.2724 | 26.5449 | 38.8173 | 6.1816 | 9.0908 | 8.1816 | 7.1816 | 10.2724 | 12.2824 | 9.0908 | 16.2724 | 26.5449 | 38.8273 | 0.01
4.1669 | 8.0835 | 6.1669 | 5.1669 | 7.2504 | 9.2504 | 8.0835 | 13.2504 | 20.5008 | 29.7512 | 4.1669 | 8.0835 | 6.1669 | 5.1669 | 7.2504 | 9.2604 | 8.0835 | 13.2504 | 20.5008 | 29.7612 | 0.01
5.6994 | 8.8497 | 7.6994 | 6.6994 | 9.5491 | 11.5491 | 8.8497 | 15.5491 | 25.0981 | 36.6472 | 5.6994 | 8.8497 | 7.6994 | 6.6994 | 9.5491 | 11.5591 | 8.8497 | 15.5491 | 25.0981 | 36.6572 | 0.01
6.0425 | 9.0212 | 8.0425 | 7.0425 | 10.0637 | 12.0637 | 9.0212 | 16.0637 | 26.1274 | 38.1911 | 6.0425 | 9.0212 | 8.0425 | 7.0425 | 10.0637 | 12.0737 | 9.0212 | 16.0637 | 26.1274 | 38.2011 | 0.01
10.3015 | 11.1508 | 12.3015 | 11.3015 | 16.4523 | 18.4523 | 11.1508 | 22.4523 | 38.9045 | 57.3568 | 10.3015 | 11.1508 | 12.3015 | 11.3015 | 16.4523 | 18.4623 | 11.1508 | 22.4523 | 38.9045 | 57.3668 | 0.01
5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.646 | 8.5487 | 14.646 | 23.292 | 33.9381 | 5.0973 | 8.5487 | 7.0973 | 6.0973 | 8.646 | 10.656 | 8.5487 | 14.646 | 23.292 | 33.9481 | 0.01
2.9544 | 7.4772 | 4.9544 | 3.9544 | 5.4316 | 7.4316 | 7.4772 | 11.4316 | 16.8633 | 24.2949 | 2.9544 | 7.4772 | 4.9544 | 3.9544 | 5.4316 | 7.4416 | 7.4772 | 11.4316 | 16.8633 | 24.3049 | 0.01
8.086 | 10.043 | 10.086 | 9.086 | 13.129 | 15.129 | 10.043 | 19.129 | 32.258 | 47.3871 | 8.086 | 10.043 | 10.086 | 9.086 | 13.129 | 15.139 | 10.043 | 19.129 | 32.258 | 47.3971 | 0.01
3.5671 | 7.7836 | 5.5671 | 4.5671 | 6.3507 | 8.3507 | 7.7836 | 12.3507 | 18.7014 | 27.0522 | 3.5671 | 7.7836 | 5.5671 | 4.5671 | 6.3507 | 8.3607 | 7.7836 | 12.3507 | 18.7014 | 27.0622 | 0.01
3.1336 | 7.5668 | 5.1336 | 4.1336 | 5.7004 | 7.7004 | 7.5668 | 11.7004 | 17.4008 | 25.1012 | 3.1336 | 7.5668 | 5.1336 | 4.1336 | 5.7004 | 7.7104 | 7.5668 | 11.7004 | 17.4008 | 25.1112 | 0.01
6.5277 | 9.2639 | 8.5277 | 7.5277 | 10.7916 | 12.7916 | 9.2639 | 16.7916 | 27.5831 | 40.3747 | 6.5277 | 9.2639 | 8.5277 | 7.5277 | 10.7916 | 12.8016 | 9.2639 | 16.7916 | 27.5831 | 40.3847 | 0.01
4.9065 | 8.4533 | 6.9065 | 5.9065 | 8.3598 | 10.3598 | 8.4533 | 14.3598 | 22.7195 | 33.0793 | 4.9065 | 8.4533 | 6.9065 | 5.9065 | 8.3598 | 10.3698 | 8.4533 | 14.3598 | 22.7195 | 33.0893 | 0.01
5.0165 | 8.5082 | 7.0165 | 6.0165 | 8.5247 | 10.5247 | 8.5082 | 14.5247 | 23.0494 | 33.5741 | 5.0165 | 8.5082 | 7.0165 | 6.0165 | 8.5247 | 10.5347 | 8.5082 | 14.5247 | 23.0494 | 33.5841 | 0.01
7.6593 | 9.8296 | 9.6593 | 8.6593 | 12.4889 | 14.4889 | 9.8296 | 18.4889 | 30.9778 | 45.4666 | 7.6593 | 9.8296 | 9.6593 | 8.6593 | 12.4889 | 14.4989 | 9.8296 | 18.4889 | 30.9778 | 45.4766 | 0.01
7.9067 | 9.9534 | 9.9067 | 8.9067 | 12.8601 | 14.8601 | 9.9534 | 18.8601 | 31.7202 | 46.5803 | 7.9067 | 9.9534 | 9.9067 | 8.9067 | 12.8601 | 14.8701 | 9.9534 | 18.8601 | 31.7202 | 46.5903 | 0.01
5.5669 | 8.7835 | 7.5669 | 6.5669 | 9.3504 | 11.3504 | 8.7835 | 15.3504 | 24.7008 | 36.0513 | 5.5669 | 8.7835 | 7.5669 | 6.5669 | 9.3504 | 11.3604 | 8.7835 | 15.3504 | 24.7008 | 36.0613 | 0.01
6.8194 | 9.4097 | 8.8194 | 7.8194 | 11.2291 | 13.2291 | 9.4097 | 17.2291 | 28.4582 | 41.6873 | 6.8194 | 9.4097 | 8.8194 | 7.8194 | 11.2291 | 13.2391 | 9.4097 | 17.2291 | 28.4582 | 41.6973 | 0.01
4.8316 | 8.4158 | 6.8316 | 5.8316 | 8.2475 | 10.2475 | 8.4158 | 14.2475 | 22.4949 | 32.7424 | 4.8316 | 8.4158 | 6.8316 | 5.8316 | 8.2475 | 10.2575 | 8.4158 | 14.2475 | 22.4949 | 32.7524 | 0.01
7.73 | 9.865 | 9.73 | 8.73 | 12.595 | 14.595 | 9.865 | 18.595 | 31.19 | 45.785 | 7.73 | 9.865 | 9.73 | 8.73 | 12.595 | 14.605 | 9.865 | 18.595 | 31.19 | 45.795 | 0.01
4.3301 | 8.1651 | 6.3301 | 5.3301 | 7.4952 | 9.4952 | 8.1651 | 13.4952 | 20.9904 | 30.4857 | 4.3301 | 8.1651 | 6.3301 | 5.3301 | 7.4952 | 9.5052 | 8.1651 | 13.4952 | 20.9904 | 30.4957 | 0.01
4.0174 | 8.0087 | 6.0174 | 5.0174 | 7.0261 | 9.0261 | 8.0087 | 13.0261 | 20.0522 | 29.0784 | 4.0174 | 8.0087 | 6.0174 | 5.0174 | 7.0261 | 9.0361 | 8.0087 | 13.0261 | 20.0522 | 29.0884 | 0.01
3.7223 | 7.8612 | 5.7223 | 4.7223 | 6.5835 | 8.5835 | 7.8612 | 12.5835 | 19.1669 | 27.7504 | 3.7223 | 7.8612 | 5.7223 | 4.7223 | 6.5835 | 8.5935 | 7.8612 | 12.5835 | 19.1669 | 27.7604 | 0.01
5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9451 | 8.645 | 14.9351 | 23.8702 | 34.8153 | 0.01
7.4619 | 9.731 | 9.4619 | 8.4619 | 12.1929 | 14.1929 | 9.731 | 18.1929 | 30.3858 | 44.5787 | 7.4619 | 9.731 | 9.4619 | 8.4619 | 12.1929 | 14.2029 | 9.731 | 18.1929 | 30.3858 | 44.5887 | 0.01
4.2939 | 8.1469 | 6.2939 | 5.2939 | 7.4408 | 9.4408 | 8.1469 | 13.4408 | 20.8817 | 30.3225 | 4.2939 | 8.1469 | 6.2939 | 5.2939 | 7.4408 | 9.4508 | 8.1469 | 13.4408 | 20.8817 | 30.3325 | 0.01
6.2435 | 9.1217 | 8.2435 | 7.2435 | 10.3652 | 12.3652 | 9.1217 | 16.3652 | 26.7304 | 39.0957 | 6.2435 | 9.1217 | 8.2435 | 7.2435 | 10.3652 | 12.3752 | 9.1217 | 16.3652 | 26.7304 | 39.1057 | 0.01
5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6481 | 8.546 | 14.6381 | 23.2763 | 33.9244 | 0.01
7.367 | 9.6835 | 9.367 | 8.367 | 12.0506 | 14.0506 | 9.6835 | 18.0506 | 30.1011 | 44.1517 | 7.367 | 9.6835 | 9.367 | 8.367 | 12.0506 | 14.0606 | 9.6835 | 18.0506 | 30.1011 | 44.1617 | 0.01
9.1555 | 10.5777 | 11.1555 | 10.1555 | 14.7332 | 16.7332 | 10.5777 | 20.7332 | 35.4664 | 52.1996 | 9.1555 | 10.5777 | 11.1555 | 10.1555 | 14.7332 | 16.7432 | 10.5777 | 20.7332 | 35.4664 | 52.2096 | 0.01
4.4266 | 8.2133 | 6.4266 | 5.4266 | 7.64 | 9.64 | 8.2133 | 13.64 | 21.2799 | 30.9199 | 4.4266 | 8.2133 | 6.4266 | 5.4266 | 7.64 | 9.65 | 8.2133 | 13.64 | 21.2799 | 30.9299 | 0.01
6.4001 | 9.2 | 8.4001 | 7.4001 | 10.6001 | 12.6001 | 9.2 | 16.6001 | 27.2002 | 39.8003 | 6.4001 | 9.2 | 8.4001 | 7.4001 | 10.6001 | 12.6101 | 9.2 | 16.6001 | 27.2002 | 39.8103 | 0.01
5.0045 | 8.5023 | 7.0045 | 6.0045 | 8.5068 | 10.5068 | 8.5023 | 14.5068 | 23.0136 | 33.5204 | 5.0045 | 8.5023 | 7.0045 | 6.0045 | 8.5068 | 10.5168 | 8.5023 | 14.5068 | 23.0136 | 33.5304 | 0.01
2.7353 | 7.3676 | 4.7353 | 3.7353 | 5.1029 | 7.1029 | 7.3676 | 11.1029 | 16.2058 | 23.3088 | 2.7353 | 7.3676 | 4.7353 | 3.7353 | 5.1029 | 7.1129 | 7.3676 | 11.1029 | 16.2058 | 23.3188 | 0.01
5.211 | 8.6055 | 7.211 | 6.211 | 8.8164 | 10.8164 | 8.6055 | 14.8164 | 23.6329 | 34.4493 | 5.211 | 8.6055 | 7.211 | 6.211 | 8.8164 | 10.8264 | 8.6055 | 14.8164 | 23.6329 | 34.4593 | 0.01
5.7148 | 8.8574 | 7.7148 | 6.7148 | 9.5723 | 11.5723 | 8.8574 | 15.5723 | 25.1445 | 36.7168 | 5.7148 | 8.8574 | 7.7148 | 6.7148 | 9.5723 | 11.5823 | 8.8574 | 15.5723 | 25.1445 | 36.7268 | 0.01
2.991 | 7.4955 | 4.991 | 3.991 | 5.4865 | 7.4865 | 7.4955 | 11.4865 | 16.9729 | 24.4594 | 2.991 | 7.4955 | 4.991 | 3.991 | 5.4865 | 7.4965 | 7.4955 | 11.4865 | 16.9729 | 24.4694 | 0.01
5.3673 | 8.6836 | 7.3673 | 6.3673 | 9.0509 | 11.0509 | 8.6836 | 15.0509 | 24.1019 | 35.1528 | 5.3673 | 8.6836 | 7.3673 | 6.3673 | 9.0509 | 11.0609 | 8.6836 | 15.0509 | 24.1019 | 35.1628 | 0.01
6.8222 | 9.4111 | 8.8222 | 7.8222 | 11.2333 | 13.2333 | 9.4111 | 17.2333 | 28.4667 | 41.7 | 6.8222 | 9.4111 | 8.8222 | 7.8222 | 11.2333 | 13.2433 | 9.4111 | 17.2333 | 28.4667 | 41.71 | 0.01
5.639 | 8.8195 | 7.639 | 6.639 | 9.4586 | 11.4586 | 8.8195 | 15.4586 | 24.9171 | 36.3757 | 5.639 | 8.8195 | 7.639 | 6.639 | 9.4586 | 11.4686 | 8.8195 | 15.4586 | 24.9171 | 36.3857 | 0.01
10.6751 | 11.3376 | 12.6751 | 11.6751 | 17.0127 | 19.0127 | 11.3376 | 23.0127 | 40.0254 | 59.0381 | 10.6751 | 11.3376 | 12.6751 | 11.6751 | 17.0127 | 19.0227 | 11.3376 | 23.0127 | 40.0254 | 59.0481 | 0.01
1.6411 | 6.8205 | 3.6411 | 2.6411 | 3.4616 | 5.4616 | 6.8205 | 9.4616 | 12.9232 | 18.3849 | 1.6411 | 6.8205 | 3.6411 | 2.6411 | 3.4616 | 5.4716 | 6.8205 | 9.4616 | 12.9232 | 18.3949 | 0.01
5.3028 | 8.6514 | 7.3028 | 6.3028 | 8.9542 | 10.9542 | 8.6514 | 14.9542 | 23.9083 | 34.8625 | 5.3028 | 8.6514 | 7.3028 | 6.3028 | 8.9542 | 10.9642 | 8.6514 | 14.9542 | 23.9083 | 34.8725 | 0.01
8.489 | 10.2445 | 10.489 | 9.489 | 13.7334 | 15.7334 | 10.2445 | 19.7334 | 33.4669 | 49.2003 | 8.489 | 10.2445 | 10.489 | 9.489 | 13.7334 | 15.7434 | 10.2445 | 19.7334 | 33.4669 | 49.2103 | 0.01
6.2238 | 9.1119 | 8.2238 | 7.2238 | 10.3356 | 12.3356 | 9.1119 | 16.3356 | 26.6713 | 39.0069 | 6.2238 | 9.1119 | 8.2238 | 7.2238 | 10.3356 | 12.3456 | 9.1119 | 16.3356 | 26.6713 | 39.0169 | 0.01
5.7985 | 8.8993 | 7.7985 | 6.7985 | 9.6978 | 11.6978 | 8.8993 | 15.6978 | 25.3956 | 37.0935 | 5.7985 | 8.8993 | 7.7985 | 6.7985 | 9.6978 | 11.7078 | 8.8993 | 15.6978 | 25.3956 | 37.1035 | 0.01
7.9791 | 9.9895 | 9.9791 | 8.9791 | 12.9686 | 14.9686 | 9.9895 | 18.9686 | 31.9373 | 46.9059 | 7.9791 | 9.9895 | 9.9791 | 8.9791 | 12.9686 | 14.9786 | 9.9895 | 18.9686 | 31.9373 | 46.9159 | 0.01
6.6718 | 9.3359 | 8.6718 | 7.6718 | 11.0076 | 13.0076 | 9.3359 | 17.0076 | 28.0153 | 41.0229 | 6.6718 | 9.3359 | 8.6718 | 7.6718 | 11.0076 | 13.0176 | 9.3359 | 17.0076 | 28.0153 | 41.0329 | 0.01
2.7548 | 7.3774 | 4.7548 | 3.7548 | 5.1322 | 7.1322 | 7.3774 | 11.1322 | 16.2645 | 23.3967 | 2.7548 | 7.3774 | 4.7548 | 3.7548 | 5.1322 | 7.1422 | 7.3774 | 11.1322 | 16.2645 | 23.4067 | 0.01
3.7539 | 7.877 | 5.7539 | 4.7539 | 6.6309 | 8.6309 | 7.877 | 12.6309 | 19.2618 | 27.8927 | 3.7539 | 7.877 | 5.7539 | 4.7539 | 6.6309 | 8.6409 | 7.877 | 12.6309 | 19.2618 | 27.9027 | 0.01
4.0079 | 8.0039 | 6.0079 | 5.0079 | 7.0118 | 9.0118 | 8.0039 | 13.0118 | 20.0237 | 29.0355 | 4.0079 | 8.0039 | 6.0079 | 5.0079 | 7.0118 | 9.0218 | 8.0039 | 13.0118 | 20.0237 | 29.0455 | 0.01
8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2446 | 10.4115 | 20.2346 | 34.4692 | 50.7139 | 0.01
6.8933 | 9.4467 | 8.8933 | 7.8933 | 11.34 | 13.34 | 9.4467 | 17.34 | 28.68 | 42.0201 | 6.8933 | 9.4467 | 8.8933 | 7.8933 | 11.34 | 13.35 | 9.4467 | 17.34 | 28.68 | 42.0301 | 0.01
3.0902 | 7.5451 | 5.0902 | 4.0902 | 5.6353 | 7.6353 | 7.5451 | 11.6353 | 17.2706 | 24.9059 | 3.0902 | 7.5451 | 5.0902 | 4.0902 | 5.6353 | 7.6453 | 7.5451 | 11.6353 | 17.2706 | 24.9159 | 0.01
3.6821 | 7.841 | 5.6821 | 4.6821 | 6.5231 | 8.5231 | 7.841 | 12.5231 | 19.0462 | 27.5692 | 3.6821 | 7.841 | 5.6821 | 4.6821 | 6.5231 | 8.5331 | 7.841 | 12.5231 | 19.0462 | 27.5792 | 0.01
3.021 | 7.5105 | 5.021 | 4.021 | 5.5315 | 7.5315 | 7.5105 | 11.5315 | 17.063 | 24.5945 | 3.021 | 7.5105 | 5.021 | 4.021 | 5.5315 | 7.5415 | 7.5105 | 11.5315 | 17.063 | 24.6045 | 0.01
8.4728 | 10.2364 | 10.4728 | 9.4728 | 13.7092 | 15.7092 | 10.2364 | 19.7092 | 33.4183 | 49.1275 | 8.4728 | 10.2364 | 10.4728 | 9.4728 | 13.7092 | 15.7192 | 10.2364 | 19.7092 | 33.4183 | 49.1375 | 0.01
3.493 | 7.7465 | 5.493 | 4.493 | 6.2395 | 8.2395 | 7.7465 | 12.2395 | 18.4791 | 26.7186 | 3.493 | 7.7465 | 5.493 | 4.493 | 6.2395 | 8.2495 | 7.7465 | 12.2395 | 18.4791 | 26.7286 | 0.01
9.0142 | 10.5071 | 11.0142 | 10.0142 | 14.5214 | 16.5214 | 10.5071 | 20.5214 | 35.0427 | 51.5641 | 9.0142 | 10.5071 | 11.0142 | 10.0142 | 14.5214 | 16.5314 | 10.5071 | 20.5214 | 35.0427 | 51.5741 | 0.01
10.0246 | 11.0123 | 12.0246 | 11.0246 | 16.0368 | 18.0368 | 11.0123 | 22.0368 | 38.0737 | 56.1105 | 10.0246 | 11.0123 | 12.0246 | 11.0246 | 16.0368 | 18.0468 | 11.0123 | 22.0368 | 38.0737 | 56.1205 | 0.01
9.1517 | 10.5759 | 11.1517 | 10.1517 | 14.7276 | 16.7276 | 10.5759 | 20.7276 | 35.4552 | 52.1829 | 9.1517 | 10.5759 | 11.1517 | 10.1517 | 14.7276 | 16.7376 | 10.5759 | 20.7276 | 35.4552 | 52.1929 | 0.01
4.2742 | 8.1371 | 6.2742 | 5.2742 | 7.4113 | 9.4113 | 8.1371 | 13.4113 | 20.8226 | 30.2339 | 4.2742 | 8.1371 | 6.2742 | 5.2742 | 7.4113 | 9.4213 | 8.1371 | 13.4113 | 20.8226 | 30.2439 | 0.01
4.3436 | 8.1718 | 6.3436 | 5.3436 | 7.5153 | 9.5153 | 8.1718 | 13.5153 | 21.0307 | 30.546 | 4.3436 | 8.1718 | 6.3436 | 5.3436 | 7.5153 | 9.5253 | 8.1718 | 13.5153 | 21.0307 | 30.556 | 0.01
7.5365 | 9.7683 | 9.5365 | 8.5365 | 12.3048 | 14.3048 | 9.7683 | 18.3048 | 30.6095 | 44.9143 | 7.5365 | 9.7683 | 9.5365 | 8.5365 | 12.3048 | 14.3148 | 9.7683 | 18.3048 | 30.6095 | 44.9243 | 0.01
2.6661 | 7.333 | 4.6661 | 3.6661 | 4.9991 | 6.9991 | 7.333 | 10.9991 | 15.9983 | 22.9974 | 2.6661 | 7.333 | 4.6661 | 3.6661 | 4.9991 | 7.0091 | 7.333 | 10.9991 | 15.9983 | 23.0074 | 0.01
5.1754 | 8.5877 | 7.1754 | 6.1754 | 8.7632 | 10.7632 | 8.5877 | 14.7632 | 23.5263 | 34.2895 | 5.1754 | 8.5877 | 7.1754 | 6.1754 | 8.7632 | 10.7732 | 8.5877 | 14.7632 | 23.5263 | 34.2995 | 0.01
5.602 | 8.801 | 7.602 | 6.602 | 9.4029 | 11.4029 | 8.801 | 15.4029 | 24.8059 | 36.2088 | 5.602 | 8.801 | 7.602 | 6.602 | 9.4029 | 11.4129 | 8.801 | 15.4029 | 24.8059 | 36.2188 | 0.01
2.4497 | 7.2248 | 4.4497 | 3.4497 | 4.6745 | 6.6745 | 7.2248 | 10.6745 | 15.349 | 22.0234 | 2.4497 | 7.2248 | 4.4497 | 3.4497 | 4.6745 | 6.6845 | 7.2248 | 10.6745 | 15.349 | 22.0334 | 0.01
8.632 | 10.316 | 10.632 | 9.632 | 13.948 | 15.948 | 10.316 | 19.948 | 33.8959 | 49.8439 | 8.632 | 10.316 | 10.632 | 9.632 | 13.948 | 15.958 | 10.316 | 19.948 | 33.8959 | 49.8539 | 0.01
7.3605 | 9.6802 | 9.3605 | 8.3605 | 12.0407 | 14.0407 | 9.6802 | 18.0407 | 30.0814 | 44.1221 | 7.3605 | 9.6802 | 9.3605 | 8.3605 | 12.0407 | 14.0507 | 9.6802 | 18.0407 | 30.0814 | 44.1321 | 0.01
6.2503 | 9.1251 | 8.2503 | 7.2503 | 10.3754 | 12.3754 | 9.1251 | 16.3754 | 26.7508 | 39.1262 | 6.2503 | 9.1251 | 8.2503 | 7.2503 | 10.3754 | 12.3854 | 9.1251 | 16.3754 | 26.7508 | 39.1362 | 0.01
6.4729 | 9.2365 | 8.4729 | 7.4729 | 10.7094 | 12.7094 | 9.2365 | 16.7094 | 27.4188 | 40.1282 | 6.4729 | 9.2365 | 8.4729 | 7.4729 | 10.7094 | 12.7194 | 9.2365 | 16.7094 | 27.4188 | 40.1382 | 0.01
5.0375 | 8.5187 | 7.0375 | 6.0375 | 8.5562 | 10.5562 | 8.5187 | 14.5562 | 23.1124 | 33.6686 | 5.0375 | 8.5187 | 7.0375 | 6.0375 | 8.5562 | 10.5662 | 8.5187 | 14.5562 | 23.1124 | 33.6786 | 0.01
6.4828 | 9.2414 | 8.4828 | 7.4828 | 10.7243 | 12.7243 | 9.2414 | 16.7243 | 27.4485 | 40.1728 | 6.4828 | 9.2414 | 8.4828 | 7.4828 | 10.7243 | 12.7343 | 9.2414 | 16.7243 | 27.4485 | 40.1828 | 0.01
8.6636 | 10.3318 | 10.6636 | 9.6636 | 13.9954 | 15.9954 | 10.3318 | 19.9954 | 33.9908 | 49.9862 | 8.6636 | 10.3318 | 10.6636 | 9.6636 | 13.9954 | 16.0054 | 10.3318 | 19.9954 | 33.9908 | 49.9962 | 0.01
6.1928 | 9.0964 | 8.1928 | 7.1928 | 10.2893 | 12.2893 | 9.0964 | 16.2893 | 26.5785 | 38.8678 | 6.1928 | 9.0964 | 8.1928 | 7.1928 | 10.2893 | 12.2993 | 9.0964 | 16.2893 | 26.5785 | 38.8778 | 0.01
5.2215 | 8.6108 | 7.2215 | 6.2215 | 8.8323 | 10.8323 | 8.6108 | 14.8323 | 23.6646 | 34.4969 | 5.2215 | 8.6108 | 7.2215 | 6.2215 | 8.8323 | 10.8423 | 8.6108 | 14.8323 | 23.6646 | 34.5069 | 0.01
3.3861 | 7.693 | 5.3861 | 4.3861 | 6.0791 | 8.0791 | 7.693 | 12.0791 | 18.1583 | 26.2374 | 3.3861 | 7.693 | 5.3861 | 4.3861 | 6.0791 | 8.0891 | 7.693 | 12.0791 | 18.1583 | 26.2474 | 0.01
10.7513 | 11.3757 | 12.7513 | 11.7513 | 17.127 | 19.127 | 11.3757 | 23.127 | 40.2539 | 59.3809 | 10.7513 | 11.3757 | 12.7513 | 11.7513 | 17.127 | 19.137 | 11.3757 | 23.127 | 40.2539 | 59.3909 | 0.01
5.4192 | 8.7096 | 7.4192 | 6.4192 | 9.1288 | 11.1288 | 8.7096 | 15.1288 | 24.2576 | 35.3864 | 5.4192 | 8.7096 | 7.4192 | 6.4192 | 9.1288 | 11.1388 | 8.7096 | 15.1288 | 24.2576 | 35.3964 | 0.01
10.2533 | 11.1267 | 12.2533 | 11.2533 | 16.38 | 18.38 | 11.1267 | 22.38 | 38.7599 | 57.1399 | 10.2533 | 11.1267 | 12.2533 | 11.2533 | 16.38 | 18.39 | 11.1267 | 22.38 | 38.7599 | 57.1499 | 0.01
4.7906 | 8.3953 | 6.7906 | 5.7906 | 8.1858 | 10.1858 | 8.3953 | 14.1858 | 22.3717 | 32.5575 | 4.7906 | 8.3953 | 6.7906 | 5.7906 | 8.1858 | 10.1958 | 8.3953 | 14.1858 | 22.3717 | 32.5675 | 0.01
5.4023 | 8.7011 | 7.4023 | 6.4023 | 9.1034 | 11.1034 | 8.7011 | 15.1034 | 24.2068 | 35.3102 | 5.4023 | 8.7011 | 7.4023 | 6.4023 | 9.1034 | 11.1134 | 8.7011 | 15.1034 | 24.2068 | 35.3202 | 0.01
9.2231 | 10.6116 | 11.2231 | 10.2231 | 14.8347 | 16.8347 | 10.6116 | 20.8347 | 35.6693 | 52.504 | 9.2231 | 10.6116 | 11.2231 | 10.2231 | 14.8347 | 16.8447 | 10.6116 | 20.8347 | 35.6693 | 52.514 | 0.01
6.4629 | 9.2314 | 8.4629 | 7.4629 | 10.6943 | 12.6943 | 9.2314 | 16.6943 | 27.3886 | 40.0829 | 6.4629 | 9.2314 | 8.4629 | 7.4629 | 10.6943 | 12.7043 | 9.2314 | 16.6943 | 27.3886 | 40.0929 | 0.01
3.3717 | 7.6858 | 5.3717 | 4.3717 | 6.0575 | 8.0575 | 7.6858 | 12.0575 | 18.115 | 26.1724 | 3.3717 | 7.6858 | 5.3717 | 4.3717 | 6.0575 | 8.0675 | 7.6858 | 12.0575 | 18.115 | 26.1824 | 0.01
5.6239 | 8.812 | 7.6239 | 6.6239 | 9.4359 | 11.4359 | 8.812 | 15.4359 | 24.8718 | 36.3078 | 5.6239 | 8.812 | 7.6239 | 6.6239 | 9.4359 | 11.4459 | 8.812 | 15.4359 | 24.8718 | 36.3178 | 0.01
9.3247 | 10.6624 | 11.3247 | 10.3247 | 14.9871 | 16.9871 | 10.6624 | 20.9871 | 35.9742 | 52.9613 | 9.3247 | 10.6624 | 11.3247 | 10.3247 | 14.9871 | 16.9971 | 10.6624 | 20.9871 | 35.9742 | 52.9713 | 0.01
4.3088 | 8.1544 | 6.3088 | 5.3088 | 7.4632 | 9.4632 | 8.1544 | 13.4632 | 20.9264 | 30.3896 | 4.3088 | 8.1544 | 6.3088 | 5.3088 | 7.4632 | 9.4732 | 8.1544 | 13.4632 | 20.9264 | 30.3996 | 0.01
5.0985 | 8.5493 | 7.0985 | 6.0985 | 8.6478 | 10.6478 | 8.5493 | 14.6478 | 23.2956 | 33.9434 | 5.0985 | 8.5493 | 7.0985 | 6.0985 | 8.6478 | 10.6578 | 8.5493 | 14.6478 | 23.2956 | 33.9534 | 0.01
7.6629 | 9.8315 | 9.6629 | 8.6629 | 12.4944 | 14.4944 | 9.8315 | 18.4944 | 30.9888 | 45.4832 | 7.6629 | 9.8315 | 9.6629 | 8.6629 | 12.4944 | 14.5044 | 9.8315 | 18.4944 | 30.9888 | 45.4932 | 0.01
9.3024 | 10.6512 | 11.3024 | 10.3024 | 14.9536 | 16.9536 | 10.6512 | 20.9536 | 35.9072 | 52.8609 | 9.3024 | 10.6512 | 11.3024 | 10.3024 | 14.9536 | 16.9636 | 10.6512 | 20.9536 | 35.9072 | 52.8709 | 0.01
8.7686 | 10.3843 | 10.7686 | 9.7686 | 14.1529 | 16.1529 | 10.3843 | 20.1529 | 34.3058 | 50.4587 | 8.7686 | 10.3843 | 10.7686 | 9.7686 | 14.1529 | 16.1629 | 10.3843 | 20.1529 | 34.3058 | 50.4687 | 0.01
8.1501 | 10.075 | 10.1501 | 9.1501 | 13.2251 | 15.2251 | 10.075 | 19.2251 | 32.4502 | 47.6753 | 8.1501 | 10.075 | 10.1501 | 9.1501 | 13.2251 | 15.2351 | 10.075 | 19.2251 | 32.4502 | 47.6853 | 0.01
6.7669 | 9.3835 | 8.7669 | 7.7669 | 11.1504 | 13.1504 | 9.3835 | 17.1504 | 28.3008 | 41.4512 | 6.7669 | 9.3835 | 8.7669 | 7.7669 | 11.1504 | 13.1604 | 9.3835 | 17.1504 | 28.3008 | 41.4612 | 0.01
6.0705 | 9.0352 | 8.0705 | 7.0705 | 10.1057 | 12.1057 | 9.0352 | 16.1057 | 26.2114 | 38.3171 | 6.0705 | 9.0352 | 8.0705 | 7.0705 | 10.1057 | 12.1157 | 9.0352 | 16.1057 | 26.2114 | 38.3271 | 0.01
5.7724 | 8.8862 | 7.7724 | 6.7724 | 9.6586 | 11.6586 | 8.8862 | 15.6586 | 25.3172 | 36.9757 | 5.7724 | 8.8862 | 7.7724 | 6.7724 | 9.6586 | 11.6686 | 8.8862 | 15.6586 | 25.3172 | 36.9857 | 0.01
7.6638 | 9.8319 | 9.6638 | 8.6638 | 12.4957 | 14.4957 | 9.8319 | 18.4957 | 30.9914 | 45.487 | 7.6638 | 9.8319 | 9.6638 | 8.6638 | 12.4957 | 14.5057 | 9.8319 | 18.4957 | 30.9914 | 45.497 | 0.01
5.8442 | 8.9221 | 7.8442 | 6.8442 | 9.7663 | 11.7663 | 8.9221 | 15.7663 | 25.5325 | 37.2988 | 5.8442 | 8.9221 | 7.8442 | 6.8442 | 9.7663 | 11.7763 | 8.9221 | 15.7663 | 25.5325 | 37.3088 | 0.01
4.8173 | 8.4086 | 6.8173 | 5.8173 | 8.2259 | 10.2259 | 8.4086 | 14.2259 | 22.4518 | 32.6777 | 4.8173 | 8.4086 | 6.8173 | 5.8173 | 8.2259 | 10.2359 | 8.4086 | 14.2259 | 22.4518 | 32.6877 | 0.01
3.6353 | 7.8177 | 5.6353 | 4.6353 | 6.453 | 8.453 | 7.8177 | 12.453 | 18.9059 | 27.3589 | 3.6353 | 7.8177 | 5.6353 | 4.6353 | 6.453 | 8.463 | 7.8177 | 12.453 | 18.9059 | 27.3689 | 0.01
3.3053 | 7.6526 | 5.3053 | 4.3053 | 5.9579 | 7.9579 | 7.6526 | 11.9579 | 17.9158 | 25.8737 | 3.3053 | 7.6526 | 5.3053 | 4.3053 | 5.9579 | 7.9679 | 7.6526 | 11.9579 | 17.9158 | 25.8837 | 0.01
5.0443 | 8.5222 | 7.0443 | 6.0443 | 8.5665 | 10.5665 | 8.5222 | 14.5665 | 23.133 | 33.6995 | 5.0443 | 8.5222 | 7.0443 | 6.0443 | 8.5665 | 10.5765 | 8.5222 | 14.5665 | 23.133 | 33.7095 | 0.01
8.0763 | 10.0381 | 10.0763 | 9.0763 | 13.1144 | 15.1144 | 10.0381 | 19.1144 | 32.2289 | 47.3433 | 8.0763 | 10.0381 | 10.0763 | 9.0763 | 13.1144 | 15.1244 | 10.0381 | 19.1144 | 32.2289 | 47.3533 | 0.01
4.3336 | 8.1668 | 6.3336 | 5.3336 | 7.5004 | 9.5004 | 8.1668 | 13.5004 | 21.0008 | 30.5013 | 4.3336 | 8.1668 | 6.3336 | 5.3336 | 7.5004 | 9.5104 | 8.1668 | 13.5004 | 21.0008 | 30.5113 | 0.01
9.9359 | 10.9679 | 11.9359 | 10.9359 | 15.9038 | 17.9038 | 10.9679 | 21.9038 | 37.8077 | 55.7115 | 9.9359 | 10.9679 | 11.9359 | 10.9359 | 15.9038 | 17.9138 | 10.9679 | 21.9038 | 37.8077 | 55.7215 | 0.01
6.4882 | 9.2441 | 8.4882 | 7.4882 | 10.7323 | 12.7323 | 9.2441 | 16.7323 | 27.4646 | 40.1969 | 6.4882 | 9.2441 | 8.4882 | 7.4882 | 10.7323 | 12.7423 | 9.2441 | 16.7323 | 27.4646 | 40.2069 | 0.01
3.7597 | 7.8798 | 5.7597 | 4.7597 | 6.6395 | 8.6395 | 7.8798 | 12.6395 | 19.279 | 27.9185 | 3.7597 | 7.8798 | 5.7597 | 4.7597 | 6.6395 | 8.6495 | 7.8798 | 12.6395 | 19.279 | 27.9285 | 0.01
4.1555 | 8.0777 | 6.1555 | 5.1555 | 7.2332 | 9.2332 | 8.0777 | 13.2332 | 20.4665 | 29.6997 | 4.1555 | 8.0777 | 6.1555 | 5.1555 | 7.2332 | 9.2432 | 8.0777 | 13.2332 | 20.4665 | 29.7097 | 0.01
2.6525 | 7.3263 | 4.6525 | 3.6525 | 4.9788 | 6.9788 | 7.3263 | 10.9788 | 15.9575 | 22.9363 | 2.6525 | 7.3263 | 4.6525 | 3.6525 | 4.9788 | 6.9888 | 7.3263 | 10.9788 | 15.9575 | 22.9463 | 0.01
1.8403 | 6.9201 | 3.8403 | 2.8403 | 3.7604 | 5.7604 | 6.9201 | 9.7604 | 13.5208 | 19.2812 | 1.8403 | 6.9201 | 3.8403 | 2.8403 | 3.7604 | 5.7704 | 6.9201 | 9.7604 | 13.5208 | 19.2912 | 0.01
2.6667 | 7.3334 | 4.6667 | 3.6667 | 5.0001 | 7.0001 | 7.3334 | 11.0001 | 16.0001 | 23.0002 | 2.6667 | 7.3334 | 4.6667 | 3.6667 | 5.0001 | 7.0101 | 7.3334 | 11.0001 | 16.0001 | 23.0102 | 0.01
6.4608 | 9.2304 | 8.4608 | 7.4608 | 10.6912 | 12.6912 | 9.2304 | 16.6912 | 27.3825 | 40.0737 | 6.4608 | 9.2304 | 8.4608 | 7.4608 | 10.6912 | 12.7012 | 9.2304 | 16.6912 | 27.3825 | 40.0837 | 0.01
4.1906 | 8.0953 | 6.1906 | 5.1906 | 7.2858 | 9.2858 | 8.0953 | 13.2858 | 20.5717 | 29.8575 | 4.1906 | 8.0953 | 6.1906 | 5.1906 | 7.2858 | 9.2958 | 8.0953 | 13.2858 | 20.5717 | 29.8675 | 0.01
8.6153 | 10.3077 | 10.6153 | 9.6153 | 13.923 | 15.923 | 10.3077 | 19.923 | 33.846 | 49.769 | 8.6153 | 10.3077 | 10.6153 | 9.6153 | 13.923 | 15.933 | 10.3077 | 19.923 | 33.846 | 49.779 | 0.01
4.7385 | 8.3693 | 6.7385 | 5.7385 | 8.1078 | 10.1078 | 8.3693 | 14.1078 | 22.2156 | 32.3234 | 4.7385 | 8.3693 | 6.7385 | 5.7385 | 8.1078 | 10.1178 | 8.3693 | 14.1078 | 22.2156 | 32.3334 | 0.01
2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4858 | 7.4919 | 11.4758 | 16.9515 | 24.4373 | 0.01
3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.959 | 7.9863 | 12.959 | 19.918 | 28.8769 | 3.9727 | 7.9863 | 5.9727 | 4.9727 | 6.959 | 8.969 | 7.9863 | 12.959 | 19.918 | 28.8869 | 0.01
5.9707 | 8.9854 | 7.9707 | 6.9707 | 9.9561 | 11.9561 | 8.9854 | 15.9561 | 25.9121 | 37.8682 | 5.9707 | 8.9854 | 7.9707 | 6.9707 | 9.9561 | 11.9661 | 8.9854 | 15.9561 | 25.9121 | 37.8782 | 0.01
8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5566 | 10.1822 | 19.5466 | 33.0932 | 48.6497 | 0.01
5.1237 | 8.5618 | 7.1237 | 6.1237 | 8.6855 | 10.6855 | 8.5618 | 14.6855 | 23.3711 | 34.0566 | 5.1237 | 8.5618 | 7.1237 | 6.1237 | 8.6855 | 10.6955 | 8.5618 | 14.6855 | 23.3711 | 34.0666 | 0.01
4.2034 | 8.1017 | 6.2034 | 5.2034 | 7.3051 | 9.3051 | 8.1017 | 13.3051 | 20.6102 | 29.9154 | 4.2034 | 8.1017 | 6.2034 | 5.2034 | 7.3051 | 9.3151 | 8.1017 | 13.3051 | 20.6102 | 29.9254 | 0.01
5.5663 | 8.7832 | 7.5663 | 6.5663 | 9.3495 | 11.3495 | 8.7832 | 15.3495 | 24.699 | 36.0484 | 5.5663 | 8.7832 | 7.5663 | 6.5663 | 9.3495 | 11.3595 | 8.7832 | 15.3495 | 24.699 | 36.0584 | 0.01
6.8431 | 9.4215 | 8.8431 | 7.8431 | 11.2646 | 13.2646 | 9.4215 | 17.2646 | 28.5292 | 41.7939 | 6.8431 | 9.4215 | 8.8431 | 7.8431 | 11.2646 | 13.2746 | 9.4215 | 17.2646 | 28.5292 | 41.8039 | 0.01
6.8551 | 9.4276 | 8.8551 | 7.8551 | 11.2827 | 13.2827 | 9.4276 | 17.2827 | 28.5654 | 41.8481 | 6.8551 | 9.4276 | 8.8551 | 7.8551 | 11.2827 | 13.2927 | 9.4276 | 17.2827 | 28.5654 | 41.8581 | 0.01
4.4435 | 8.2217 | 6.4435 | 5.4435 | 7.6652 | 9.6652 | 8.2217 | 13.6652 | 21.3304 | 30.9956 | 4.4435 | 8.2217 | 6.4435 | 5.4435 | 7.6652 | 9.6752 | 8.2217 | 13.6652 | 21.3304 | 31.0056 | 0.01
9.454 | 10.727 | 11.454 | 10.454 | 15.181 | 17.181 | 10.727 | 21.181 | 36.3619 | 53.5429 | 9.454 | 10.727 | 11.454 | 10.454 | 15.181 | 17.191 | 10.727 | 21.181 | 36.3619 | 53.5529 | 0.01
7.8182 | 9.9091 | 9.8182 | 8.8182 | 12.7273 | 14.7273 | 9.9091 | 18.7273 | 31.4547 | 46.182 | 7.8182 | 9.9091 | 9.8182 | 8.8182 | 12.7273 | 14.7373 | 9.9091 | 18.7273 | 31.4547 | 46.192 | 0.01
6.9341 | 9.4671 | 8.9341 | 7.9341 | 11.4012 | 13.4012 | 9.4671 | 17.4012 | 28.8023 | 42.2035 | 6.9341 | 9.4671 | 8.9341 | 7.9341 | 11.4012 | 13.4112 | 9.4671 | 17.4012 | 28.8023 | 42.2135 | 0.01
4.4815 | 8.2408 | 6.4815 | 5.4815 | 7.7223 | 9.7223 | 8.2408 | 13.7223 | 21.4445 | 31.1668 | 4.4815 | 8.2408 | 6.4815 | 5.4815 | 7.7223 | 9.7323 | 8.2408 | 13.7223 | 21.4445 | 31.1768 | 0.01
5.1586 | 8.5793 | 7.1586 | 6.1586 | 8.7379 | 10.7379 | 8.5793 | 14.7379 | 23.4758 | 34.2137 | 5.1586 | 8.5793 | 7.1586 | 6.1586 | 8.7379 | 10.7479 | 8.5793 | 14.7379 | 23.4758 | 34.2237 | 0.01
8.2539 | 10.1269 | 10.2539 | 9.2539 | 13.3808 | 15.3808 | 10.1269 | 19.3808 | 32.7616 | 48.1423 | 8.2539 | 10.1269 | 10.2539 | 9.2539 | 13.3808 | 15.3908 | 10.1269 | 19.3808 | 32.7616 | 48.1523 | 0.01
7.8806 | 9.9403 | 9.8806 | 8.8806 | 12.8209 | 14.8209 | 9.9403 | 18.8209 | 31.6419 | 46.4628 | 7.8806 | 9.9403 | 9.8806 | 8.8806 | 12.8209 | 14.8309 | 9.9403 | 18.8209 | 31.6419 | 46.4728 | 0.01
4.776 | 8.388 | 6.776 | 5.776 | 8.164 | 10.164 | 8.388 | 14.164 | 22.3281 | 32.4921 | 4.776 | 8.388 | 6.776 | 5.776 | 8.164 | 10.174 | 8.388 | 14.164 | 22.3281 | 32.5021 | 0.01
6.3025 | 9.1512 | 8.3025 | 7.3025 | 10.4537 | 12.4537 | 9.1512 | 16.4537 | 26.9074 | 39.3611 | 6.3025 | 9.1512 | 8.3025 | 7.3025 | 10.4537 | 12.4637 | 9.1512 | 16.4537 | 26.9074 | 39.3711 | 0.01
6.7528 | 9.3764 | 8.7528 | 7.7528 | 11.1292 | 13.1292 | 9.3764 | 17.1292 | 28.2584 | 41.3875 | 6.7528 | 9.3764 | 8.7528 | 7.7528 | 11.1292 | 13.1392 | 9.3764 | 17.1292 | 28.2584 | 41.3975 | 0.01
6.2989 | 9.1495 | 8.2989 | 7.2989 | 10.4484 | 12.4484 | 9.1495 | 16.4484 | 26.8968 | 39.3451 | 6.2989 | 9.1495 | 8.2989 | 7.2989 | 10.4484 | 12.4584 | 9.1495 | 16.4484 | 26.8968 | 39.3551 | 0.01
6.9488 | 9.4744 | 8.9488 | 7.9488 | 11.4232 | 13.4232 | 9.4744 | 17.4232 | 28.8464 | 42.2696 | 6.9488 | 9.4744 | 8.9488 | 7.9488 | 11.4232 | 13.4332 | 9.4744 | 17.4232 | 28.8464 | 42.2796 | 0.01
3.3735 | 7.6867 | 5.3735 | 4.3735 | 6.0602 | 8.0602 | 7.6867 | 12.0602 | 18.1204 | 26.1806 | 3.3735 | 7.6867 | 5.3735 | 4.3735 | 6.0602 | 8.0702 | 7.6867 | 12.0602 | 18.1204 | 26.1906 | 0.01
8.8156 | 10.4078 | 10.8156 | 9.8156 | 14.2235 | 16.2235 | 10.4078 | 20.2235 | 34.4469 | 50.6704 | 8.8156 | 10.4078 | 10.8156 | 9.8156 | 14.2235 | 16.2335 | 10.4078 | 20.2235 | 34.4469 | 50.6804 | 0.01
6.1938 | 9.0969 | 8.1938 | 7.1938 | 10.2907 | 12.2907 | 9.0969 | 16.2907 | 26.5813 | 38.872 | 6.1938 | 9.0969 | 8.1938 | 7.1938 | 10.2907 | 12.3007 | 9.0969 | 16.2907 | 26.5813 | 38.882 | 0.01
2.6892 | 7.3446 | 4.6892 | 3.6892 | 5.0338 | 7.0338 | 7.3446 | 11.0338 | 16.0676 | 23.1013 | 2.6892 | 7.3446 | 4.6892 | 3.6892 | 5.0338 | 7.0438 | 7.3446 | 11.0338 | 16.0676 | 23.1113 | 0.01
9.693 | 10.8465 | 11.693 | 10.693 | 15.5395 | 17.5395 | 10.8465 | 21.5395 | 37.0789 | 54.6184 | 9.693 | 10.8465 | 11.693 | 10.693 | 15.5395 | 17.5495 | 10.8465 | 21.5395 | 37.0789 | 54.6284 | 0.01
7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8318 | 9.6106 | 17.8318 | 29.6636 | 43.4955 | 7.2212 | 9.6106 | 9.2212 | 8.2212 | 11.8318 | 13.8418 | 9.6106 | 17.8318 | 29.6636 | 43.5055 | 0.01
7.6207 | 9.8104 | 9.6207 | 8.6207 | 12.4311 | 14.4311 | 9.8104 | 18.4311 | 30.8621 | 45.2932 | 7.6207 | 9.8104 | 9.6207 | 8.6207 | 12.4311 | 14.4411 | 9.8104 | 18.4311 | 30.8621 | 45.3032 | 0.01
5.3109 | 8.6554 | 7.3109 | 6.3109 | 8.9663 | 10.9663 | 8.6554 | 14.9663 | 23.9327 | 34.899 | 5.3109 | 8.6554 | 7.3109 | 6.3109 | 8.9663 | 10.9763 | 8.6554 | 14.9663 | 23.9327 | 34.909 | 0.01
5.815 | 8.9075 | 7.815 | 6.815 | 9.7225 | 11.7225 | 8.9075 | 15.7225 | 25.445 | 37.1675 | 5.815 | 8.9075 | 7.815 | 6.815 | 9.7225 | 11.7325 | 8.9075 | 15.7225 | 25.445 | 37.1775 | 0.01
8.6974 | 10.3487 | 10.6974 | 9.6974 | 14.0461 | 16.0461 | 10.3487 | 20.0461 | 34.0922 | 50.1383 | 8.6974 | 10.3487 | 10.6974 | 9.6974 | 14.0461 | 16.0561 | 10.3487 | 20.0461 | 34.0922 | 50.1483 | 0.01
4.5436 | 8.2718 | 6.5436 | 5.5436 | 7.8155 | 9.8155 | 8.2718 | 13.8155 | 21.6309 | 31.4464 | 4.5436 | 8.2718 | 6.5436 | 5.5436 | 7.8155 | 9.8255 | 8.2718 | 13.8155 | 21.6309 | 31.4564 | 0.01
3.342 | 7.671 | 5.342 | 4.342 | 6.013 | 8.013 | 7.671 | 12.013 | 18.0259 | 26.0389 | 3.342 | 7.671 | 5.342 | 4.342 | 6.013 | 8.023 | 7.671 | 12.013 | 18.0259 | 26.0489 | 0.01
3.0612 | 7.5306 | 5.0612 | 4.0612 | 5.5918 | 7.5918 | 7.5306 | 11.5918 | 17.1837 | 24.7755 | 3.0612 | 7.5306 | 5.0612 | 4.0612 | 5.5918 | 7.6018 | 7.5306 | 11.5918 | 17.1837 | 24.7855 | 0.01
8.378 | 10.189 | 10.378 | 9.378 | 13.567 | 15.567 | 10.189 | 19.567 | 33.1339 | 48.7009 | 8.378 | 10.189 | 10.378 | 9.378 | 13.567 | 15.577 | 10.189 | 19.567 | 33.1339 | 48.7109 | 0.01
5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.7097 | 8.8999 | 15.6997 | 25.3993 | 37.109 | 0.01
5.55 | 8.775 | 7.55 | 6.55 | 9.325 | 11.325 | 8.775 | 15.325 | 24.65 | 35.9751 | 5.55 | 8.775 | 7.55 | 6.55 | 9.325 | 11.335 | 8.775 | 15.325 | 24.65 | 35.9851 | 0.01
8.0143 | 10.0072 | 10.0143 | 9.0143 | 13.0215 | 15.0215 | 10.0072 | 19.0215 | 32.043 | 47.0645 | 8.0143 | 10.0072 | 10.0143 | 9.0143 | 13.0215 | 15.0315 | 10.0072 | 19.0215 | 32.043 | 47.0745 | 0.01
4.2615 | 8.1308 | 6.2615 | 5.2615 | 7.3923 | 9.3923 | 8.1308 | 13.3923 | 20.7846 | 30.1769 | 4.2615 | 8.1308 | 6.2615 | 5.2615 | 7.3923 | 9.4023 | 8.1308 | 13.3923 | 20.7846 | 30.1869 | 0.01
4.3816 | 8.1908 | 6.3816 | 5.3816 | 7.5724 | 9.5724 | 8.1908 | 13.5724 | 21.1449 | 30.7173 | 4.3816 | 8.1908 | 6.3816 | 5.3816 | 7.5724 | 9.5824 | 8.1908 | 13.5724 | 21.1449 | 30.7273 | 0.01
5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.6997 | 8.8999 | 15.6997 | 25.3993 | 37.099 | 5.7998 | 8.8999 | 7.7998 | 6.7998 | 9.6997 | 11.7097 | 8.8999 | 15.6997 | 25.3993 | 37.109 | 0.01
7.8028 | 9.9014 | 9.8028 | 8.8028 | 12.7042 | 14.7042 | 9.9014 | 18.7042 | 31.4083 | 46.1125 | 7.8028 | 9.9014 | 9.8028 | 8.8028 | 12.7042 | 14.7142 | 9.9014 | 18.7042 | 31.4083 | 46.1225 | 0.01
8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5466 | 10.1822 | 19.5466 | 33.0932 | 48.6397 | 8.3644 | 10.1822 | 10.3644 | 9.3644 | 13.5466 | 15.5566 | 10.1822 | 19.5466 | 33.0932 | 48.6497 | 0.01
5.5132 | 8.7566 | 7.5132 | 6.5132 | 9.2698 | 11.2698 | 8.7566 | 15.2698 | 24.5397 | 35.8095 | 5.5132 | 8.7566 | 7.5132 | 6.5132 | 9.2698 | 11.2798 | 8.7566 | 15.2698 | 24.5397 | 35.8195 | 0.01
7.8861 | 9.9431 | 9.8861 | 8.8861 | 12.8292 | 14.8292 | 9.9431 | 18.8292 | 31.6583 | 46.4875 | 7.8861 | 9.9431 | 9.8861 | 8.8861 | 12.8292 | 14.8392 | 9.9431 | 18.8292 | 31.6583 | 46.4975 | 0.01
6.7892 | 9.3946 | 8.7892 | 7.7892 | 11.1838 | 13.1838 | 9.3946 | 17.1838 | 28.3676 | 41.5514 | 6.7892 | 9.3946 | 8.7892 | 7.7892 | 11.1838 | 13.1938 | 9.3946 | 17.1838 | 28.3676 | 41.5614 | 0.01
4.1869 | 8.0934 | 6.1869 | 5.1869 | 7.2803 | 9.2803 | 8.0934 | 13.2803 | 20.5606 | 29.8409 | 4.1869 | 8.0934 | 6.1869 | 5.1869 | 7.2803 | 9.2903 | 8.0934 | 13.2803 | 20.5606 | 29.8509 | 0.01
4.1938 | 8.0969 | 6.1938 | 5.1938 | 7.2907 | 9.2907 | 8.0969 | 13.2907 | 20.5813 | 29.872 | 4.1938 | 8.0969 | 6.1938 | 5.1938 | 7.2907 | 9.3007 | 8.0969 | 13.2907 | 20.5813 | 29.882 | 0.01
3.2575 | 7.6287 | 5.2575 | 4.2575 | 5.8862 | 7.8862 | 7.6287 | 11.8862 | 17.7724 | 25.6586 | 3.2575 | 7.6287 | 5.2575 | 4.2575 | 5.8862 | 7.8962 | 7.6287 | 11.8862 | 17.7724 | 25.6686 | 0.01
4.0356 | 8.0178 | 6.0356 | 5.0356 | 7.0534 | 9.0534 | 8.0178 | 13.0534 | 20.1068 | 29.1602 | 4.0356 | 8.0178 | 6.0356 | 5.0356 | 7.0534 | 9.0634 | 8.0178 | 13.0534 | 20.1068 | 29.1702 | 0.01
6.4349 | 9.2175 | 8.4349 | 7.4349 | 10.6524 | 12.6524 | 9.2175 | 16.6524 | 27.3048 | 39.9572 | 6.4349 | 9.2175 | 8.4349 | 7.4349 | 10.6524 | 12.6624 | 9.2175 | 16.6524 | 27.3048 | 39.9672 | 0.01
7.869 | 9.9345 | 9.869 | 8.869 | 12.8035 | 14.8035 | 9.9345 | 18.8035 | 31.607 | 46.4105 | 7.869 | 9.9345 | 9.869 | 8.869 | 12.8035 | 14.8135 | 9.9345 | 18.8035 | 31.607 | 46.4205 | 0.01
6.7712 | 9.3856 | 8.7712 | 7.7712 | 11.1568 | 13.1568 | 9.3856 | 17.1568 | 28.3136 | 41.4704 | 6.7712 | 9.3856 | 8.7712 | 7.7712 | 11.1568 | 13.1668 | 9.3856 | 17.1568 | 28.3136 | 41.4804 | 0.01
8.0857 | 10.0429 | 10.0857 | 9.0857 | 13.1286 | 15.1286 | 10.0429 | 19.1286 | 32.2572 | 47.3859 | 8.0857 | 10.0429 | 10.0857 | 9.0857 | 13.1286 | 15.1386 | 10.0429 | 19.1286 | 32.2572 | 47.3959 | 0.01
7.7566 | 9.8783 | 9.7566 | 8.7566 | 12.6349 | 14.6349 | 9.8783 | 18.6349 | 31.2699 | 45.9048 | 7.7566 | 9.8783 | 9.7566 | 8.7566 | 12.6349 | 14.6449 | 9.8783 | 18.6349 | 31.2699 | 45.9148 | 0.01
9.6525 | 10.8263 | 11.6525 | 10.6525 | 15.4788 | 17.4788 | 10.8263 | 21.4788 | 36.9575 | 54.4363 | 9.6525 | 10.8263 | 11.6525 | 10.6525 | 15.4788 | 17.4888 | 10.8263 | 21.4788 | 36.9575 | 54.4463 | 0.01
7.2986 | 9.6493 | 9.2986 | 8.2986 | 11.948 | 13.948 | 9.6493 | 17.948 | 29.8959 | 43.8439 | 7.2986 | 9.6493 | 9.2986 | 8.2986 | 11.948 | 13.958 | 9.6493 | 17.948 | 29.8959 | 43.8539 | 0.01
4.0521 | 8.0261 | 6.0521 | 5.0521 | 7.0782 | 9.0782 | 8.0261 | 13.0782 | 20.1564 | 29.2346 | 4.0521 | 8.0261 | 6.0521 | 5.0521 | 7.0782 | 9.0882 | 8.0261 | 13.0782 | 20.1564 | 29.2446 | 0.01
7.0371 | 9.5185 | 9.0371 | 8.0371 | 11.5556 | 13.5556 | 9.5185 | 17.5556 | 29.1112 | 42.6668 | 7.0371 | 9.5185 | 9.0371 | 8.0371 | 11.5556 | 13.5656 | 9.5185 | 17.5556 | 29.1112 | 42.6768 | 0.01
2.233 | 7.1165 | 4.233 | 3.233 | 4.3495 | 6.3495 | 7.1165 | 10.3495 | 14.6991 | 21.0486 | 2.233 | 7.1165 | 4.233 | 3.233 | 4.3495 | 6.3595 | 7.1165 | 10.3495 | 14.6991 | 21.0586 | 0.01
7.2275 | 9.6137 | 9.2275 | 8.2275 | 11.8412 | 13.8412 | 9.6137 | 17.8412 | 29.6825 | 43.5237 | 7.2275 | 9.6137 | 9.2275 | 8.2275 | 11.8412 | 13.8512 | 9.6137 | 17.8412 | 29.6825 | 43.5337 | 0.01
6.3896 | 9.1948 | 8.3896 | 7.3896 | 10.5844 | 12.5844 | 9.1948 | 16.5844 | 27.1688 | 39.7532 | 6.3896 | 9.1948 | 8.3896 | 7.3896 | 10.5844 | 12.5944 | 9.1948 | 16.5844 | 27.1688 | 39.7632 | 0.01
6.4116 | 9.2058 | 8.4116 | 7.4116 | 10.6174 | 12.6174 | 9.2058 | 16.6174 | 27.2349 | 39.8523 | 6.4116 | 9.2058 | 8.4116 | 7.4116 | 10.6174 | 12.6274 | 9.2058 | 16.6174 | 27.2349 | 39.8623 | 0.01
4.7322 | 8.3661 | 6.7322 | 5.7322 | 8.0983 | 10.0983 | 8.3661 | 14.0983 | 22.1965 | 32.2948 | 4.7322 | 8.3661 | 6.7322 | 5.7322 | 8.0983 | 10.1083 | 8.3661 | 14.0983 | 22.1965 | 32.3048 | 0.01
6.7518 | 9.3759 | 8.7518 | 7.7518 | 11.1277 | 13.1277 | 9.3759 | 17.1277 | 28.2554 | 41.3831 | 6.7518 | 9.3759 | 8.7518 | 7.7518 | 11.1277 | 13.1377 | 9.3759 | 17.1277 | 28.2554 | 41.3931 | 0.01
4.1562 | 8.0781 | 6.1562 | 5.1562 | 7.2343 | 9.2343 | 8.0781 | 13.2343 | 20.4686 | 29.7029 | 4.1562 | 8.0781 | 6.1562 | 5.1562 | 7.2343 | 9.2443 | 8.0781 | 13.2343 | 20.4686 | 29.7129 | 0.01
3.8186 | 7.9093 | 5.8186 | 4.8186 | 6.7279 | 8.7279 | 7.9093 | 12.7279 | 19.4557 | 28.1836 | 3.8186 | 7.9093 | 5.8186 | 4.8186 | 6.7279 | 8.7379 | 7.9093 | 12.7279 | 19.4557 | 28.1936 | 0.01
4.9033 | 8.4517 | 6.9033 | 5.9033 | 8.355 | 10.355 | 8.4517 | 14.355 | 22.7099 | 33.0649 | 4.9033 | 8.4517 | 6.9033 | 5.9033 | 8.355 | 10.365 | 8.4517 | 14.355 | 22.7099 | 33.0749 | 0.01
3.8613 | 7.9307 | 5.8613 | 4.8613 | 6.792 | 8.792 | 7.9307 | 12.792 | 19.584 | 28.376 | 3.8613 | 7.9307 | 5.8613 | 4.8613 | 6.792 | 8.802 | 7.9307 | 12.792 | 19.584 | 28.386 | 0.01
8.8507 | 10.4253 | 10.8507 | 9.8507 | 14.276 | 16.276 | 10.4253 | 20.276 | 34.5521 | 50.8281 | 8.8507 | 10.4253 | 10.8507 | 9.8507 | 14.276 | 16.286 | 10.4253 | 20.276 | 34.5521 | 50.8381 | 0.01
4.7771 | 8.3886 | 6.7771 | 5.7771 | 8.1657 | 10.1657 | 8.3886 | 14.1657 | 22.3314 | 32.4971 | 4.7771 | 8.3886 | 6.7771 | 5.7771 | 8.1657 | 10.1757 | 8.3886 | 14.1657 | 22.3314 | 32.5071 | 0.01
6.5063 | 9.2532 | 8.5063 | 7.5063 | 10.7595 | 12.7595 | 9.2532 | 16.7595 | 27.519 | 40.2786 | 6.5063 | 9.2532 | 8.5063 | 7.5063 | 10.7595 | 12.7695 | 9.2532 | 16.7595 | 27.519 | 40.2886 | 0.01
6.9271 | 9.4636 | 8.9271 | 7.9271 | 11.3907 | 13.3907 | 9.4636 | 17.3907 | 28.7813 | 42.172 | 6.9271 | 9.4636 | 8.9271 | 7.9271 | 11.3907 | 13.4007 | 9.4636 | 17.3907 | 28.7813 | 42.182 | 0.01
4.2626 | 8.1313 | 6.2626 | 5.2626 | 7.394 | 9.394 | 8.1313 | 13.394 | 20.7879 | 30.1819 | 4.2626 | 8.1313 | 6.2626 | 5.2626 | 7.394 | 9.404 | 8.1313 | 13.394 | 20.7879 | 30.1919 | 0.01
2.6952 | 7.3476 | 4.6952 | 3.6952 | 5.0428 | 7.0428 | 7.3476 | 11.0428 | 16.0856 | 23.1284 | 2.6952 | 7.3476 | 4.6952 | 3.6952 | 5.0428 | 7.0528 | 7.3476 | 11.0428 | 16.0856 | 23.1384 | 0.01
7.9818 | 9.9909 | 9.9818 | 8.9818 | 12.9728 | 14.9728 | 9.9909 | 18.9728 | 31.9455 | 46.9183 | 7.9818 | 9.9909 | 9.9818 | 8.9818 | 12.9728 | 14.9828 | 9.9909 | 18.9728 | 31.9455 | 46.9283 | 0.01
4.4602 | 8.2301 | 6.4602 | 5.4602 | 7.6903 | 9.6903 | 8.2301 | 13.6903 | 21.3806 | 31.0709 | 4.4602 | 8.2301 | 6.4602 | 5.4602 | 7.6903 | 9.7003 | 8.2301 | 13.6903 | 21.3806 | 31.0809 | 0.01
7.8904 | 9.9452 | 9.8904 | 8.8904 | 12.8356 | 14.8356 | 9.9452 | 18.8356 | 31.6712 | 46.5069 | 7.8904 | 9.9452 | 9.8904 | 8.8904 | 12.8356 | 14.8456 | 9.9452 | 18.8356 | 31.6712 | 46.5169 | 0.01
4.5586 | 8.2793 | 6.5586 | 5.5586 | 7.8379 | 9.8379 | 8.2793 | 13.8379 | 21.6757 | 31.5136 | 4.5586 | 8.2793 | 6.5586 | 5.5586 | 7.8379 | 9.8479 | 8.2793 | 13.8379 | 21.6757 | 31.5236 | 0.01
5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0338 | 8.6779 | 15.0338 | 24.0676 | 35.1013 | 5.3559 | 8.6779 | 7.3559 | 6.3559 | 9.0338 | 11.0438 | 8.6779 | 15.0338 | 24.0676 | 35.1113 | 0.01
4.5162 | 8.2581 | 6.5162 | 5.5162 | 7.7743 | 9.7743 | 8.2581 | 13.7743 | 21.5486 | 31.3228 | 4.5162 | 8.2581 | 6.5162 | 5.5162 | 7.7743 | 9.7843 | 8.2581 | 13.7743 | 21.5486 | 31.3328 | 0.01
4.8841 | 8.442 | 6.8841 | 5.8841 | 8.3261 | 10.3261 | 8.442 | 14.3261 | 22.6522 | 32.9782 | 4.8841 | 8.442 | 6.8841 | 5.8841 | 8.3261 | 10.3361 | 8.442 | 14.3261 | 22.6522 | 32.9882 | 0.01
5.6401 | 8.8201 | 7.6401 | 6.6401 | 9.4602 | 11.4602 | 8.8201 | 15.4602 | 24.9204 | 36.3806 | 5.6401 | 8.8201 | 7.6401 | 6.6401 | 9.4602 | 11.4702 | 8.8201 | 15.4602 | 24.9204 | 36.3906 | 0.01
9.7333 | 10.8666 | 11.7333 | 10.7333 | 15.5999 | 17.5999 | 10.8666 | 21.5999 | 37.1998 | 54.7997 | 9.7333 | 10.8666 | 11.7333 | 10.7333 | 15.5999 | 17.6099 | 10.8666 | 21.5999 | 37.1998 | 54.8097 | 0.01
4.4464 | 8.2232 | 6.4464 | 5.4464 | 7.6696 | 9.6696 | 8.2232 | 13.6696 | 21.3391 | 31.0087 | 4.4464 | 8.2232 | 6.4464 | 5.4464 | 7.6696 | 9.6796 | 8.2232 | 13.6696 | 21.3391 | 31.0187 | 0.01
3.4011 | 7.7006 | 5.4011 | 4.4011 | 6.1017 | 8.1017 | 7.7006 | 12.1017 | 18.2034 | 26.305 | 3.4011 | 7.7006 | 5.4011 | 4.4011 | 6.1017 | 8.1117 | 7.7006 | 12.1017 | 18.2034 | 26.315 | 0.01
5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9351 | 8.645 | 14.9351 | 23.8702 | 34.8053 | 5.2901 | 8.645 | 7.2901 | 6.2901 | 8.9351 | 10.9451 | 8.645 | 14.9351 | 23.8702 | 34.8153 | 0.01
2.1888 | 7.0944 | 4.1888 | 3.1888 | 4.2832 | 6.2832 | 7.0944 | 10.2832 | 14.5665 | 20.8497 | 2.1888 | 7.0944 | 4.1888 | 3.1888 | 4.2832 | 6.2932 | 7.0944 | 10.2832 | 14.5665 | 20.8597 | 0.01
6.8979 | 9.449 | 8.8979 | 7.8979 | 11.3469 | 13.3469 | 9.449 | 17.3469 | 28.6937 | 42.0406 | 6.8979 | 9.449 | 8.8979 | 7.8979 | 11.3469 | 13.3569 | 9.449 | 17.3469 | 28.6937 | 42.0506 | 0.01
4.4544 | 8.2272 | 6.4544 | 5.4544 | 7.6816 | 9.6816 | 8.2272 | 13.6816 | 21.3633 | 31.0449 | 4.4544 | 8.2272 | 6.4544 | 5.4544 | 7.6816 | 9.6916 | 8.2272 | 13.6816 | 21.3633 | 31.0549 | 0.01
5.3782 | 8.6891 | 7.3782 | 6.3782 | 9.0673 | 11.0673 | 8.6891 | 15.0673 | 24.1346 | 35.202 | 5.3782 | 8.6891 | 7.3782 | 6.3782 | 9.0673 | 11.0773 | 8.6891 | 15.0673 | 24.1346 | 35.212 | 0.01
4.8642 | 8.4321 | 6.8642 | 5.8642 | 8.2962 | 10.2962 | 8.4321 | 14.2962 | 22.5925 | 32.8887 | 4.8642 | 8.4321 | 6.8642 | 5.8642 | 8.2962 | 10.3062 | 8.4321 | 14.2962 | 22.5925 | 32.8987 | 0.01
6.4795 | 9.2398 | 8.4795 | 7.4795 | 10.7193 | 12.7193 | 9.2398 | 16.7193 | 27.4386 | 40.1579 | 6.4795 | 9.2398 | 8.4795 | 7.4795 | 10.7193 | 12.7293 | 9.2398 | 16.7193 | 27.4386 | 40.1679 | 0.01
6.2353 | 9.1177 | 8.2353 | 7.2353 | 10.353 | 12.353 | 9.1177 | 16.353 | 26.7059 | 39.0589 | 6.2353 | 9.1177 | 8.2353 | 7.2353 | 10.353 | 12.363 | 9.1177 | 16.353 | 26.7059 | 39.0689 | 0.01
6.6358 | 9.3179 | 8.6358 | 7.6358 | 10.9537 | 12.9537 | 9.3179 | 16.9537 | 27.9073 | 40.861 | 6.6358 | 9.3179 | 8.6358 | 7.6358 | 10.9537 | 12.9637 | 9.3179 | 16.9537 | 27.9073 | 40.871 | 0.01
5.2598 | 8.6299 | 7.2598 | 6.2598 | 8.8898 | 10.8898 | 8.6299 | 14.8898 | 23.7795 | 34.6693 | 5.2598 | 8.6299 | 7.2598 | 6.2598 | 8.8898 | 10.8998 | 8.6299 | 14.8898 | 23.7795 | 34.6793 | 0.01
5.8382 | 8.9191 | 7.8382 | 6.8382 | 9.7573 | 11.7573 | 8.9191 | 15.7573 | 25.5145 | 37.2718 | 5.8382 | 8.9191 | 7.8382 | 6.8382 | 9.7573 | 11.7673 | 8.9191 | 15.7573 | 25.5145 | 37.2818 | 0.01
3.6537 | 7.8268 | 5.6537 | 4.6537 | 6.4805 | 8.4805 | 7.8268 | 12.4805 | 18.961 | 27.4415 | 3.6537 | 7.8268 | 5.6537 | 4.6537 | 6.4805 | 8.4905 | 7.8268 | 12.4805 | 18.961 | 27.4515 | 0.01
10.3093 | 11.1546 | 12.3093 | 11.3093 | 16.4639 | 18.4639 | 11.1546 | 22.4639 | 38.9278 | 57.3917 | 10.3093 | 11.1546 | 12.3093 | 11.3093 | 16.4639 | 18.4739 | 11.1546 | 22.4639 | 38.9278 | 57.4017 | 0.01
2.9072 | 7.4536 | 4.9072 | 3.9072 | 5.3609 | 7.3609 | 7.4536 | 11.3609 | 16.7217 | 24.0826 | 2.9072 | 7.4536 | 4.9072 | 3.9072 | 5.3609 | 7.3709 | 7.4536 | 11.3609 | 16.7217 | 24.0926 | 0.01
8.8398 | 10.4199 | 10.8398 | 9.8398 | 14.2596 | 16.2596 | 10.4199 | 20.2596 | 34.5193 | 50.7789 | 8.8398 | 10.4199 | 10.8398 | 9.8398 | 14.2596 | 16.2696 | 10.4199 | 20.2596 | 34.5193 | 50.7889 | 0.01
4.7994 | 8.3997 | 6.7994 | 5.7994 | 8.1991 | 10.1991 | 8.3997 | 14.1991 | 22.3981 | 32.5972 | 4.7994 | 8.3997 | 6.7994 | 5.7994 | 8.1991 | 10.2091 | 8.3997 | 14.1991 | 22.3981 | 32.6072 | 0.01
4.8728 | 8.4364 | 6.8728 | 5.8728 | 8.3092 | 10.3092 | 8.4364 | 14.3092 | 22.6183 | 32.9275 | 4.8728 | 8.4364 | 6.8728 | 5.8728 | 8.3092 | 10.3192 | 8.4364 | 14.3092 | 22.6183 | 32.9375 | 0.01
8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2346 | 10.4115 | 20.2346 | 34.4692 | 50.7039 | 8.8231 | 10.4115 | 10.8231 | 9.8231 | 14.2346 | 16.2446 | 10.4115 | 20.2346 | 34.4692 | 50.7139 | 0.01
8.2877 | 10.1438 | 10.2877 | 9.2877 | 13.4315 | 15.4315 | 10.1438 | 19.4315 | 32.863 | 48.2945 | 8.2877 | 10.1438 | 10.2877 | 9.2877 | 13.4315 | 15.4415 | 10.1438 | 19.4315 | 32.863 | 48.3045 | 0.01
5.1521 | 8.576 | 7.1521 | 6.1521 | 8.7281 | 10.7281 | 8.576 | 14.7281 | 23.4562 | 34.1843 | 5.1521 | 8.576 | 7.1521 | 6.1521 | 8.7281 | 10.7381 | 8.576 | 14.7281 | 23.4562 | 34.1943 | 0.01
7.8614 | 9.9307 | 9.8614 | 8.8614 | 12.7921 | 14.7921 | 9.9307 | 18.7921 | 31.5843 | 46.3764 | 7.8614 | 9.9307 | 9.8614 | 8.8614 | 12.7921 | 14.8021 | 9.9307 | 18.7921 | 31.5843 | 46.3864 | 0.01
7.2199 | 9.61 | 9.2199 | 8.2199 | 11.8299 | 13.8299 | 9.61 | 17.8299 | 29.6598 | 43.4897 | 7.2199 | 9.61 | 9.2199 | 8.2199 | 11.8299 | 13.8399 | 9.61 | 17.8299 | 29.6598 | 43.4997 | 0.01
5.6179 | 8.8089 | 7.6179 | 6.6179 | 9.4268 | 11.4268 | 8.8089 | 15.4268 | 24.8536 | 36.2804 | 5.6179 | 8.8089 | 7.6179 | 6.6179 | 9.4268 | 11.4368 | 8.8089 | 15.4268 | 24.8536 | 36.2904 | 0.01
2.7189 | 7.3595 | 4.7189 | 3.7189 | 5.0784 | 7.0784 | 7.3595 | 11.0784 | 16.1568 | 23.2352 | 2.7189 | 7.3595 | 4.7189 | 3.7189 | 5.0784 | 7.0884 | 7.3595 | 11.0784 | 16.1568 | 23.2452 | 0.01
7.0937 | 9.5468 | 9.0937 | 8.0937 | 11.6405 | 13.6405 | 9.5468 | 17.6405 | 29.281 | 42.9215 | 7.0937 | 9.5468 | 9.0937 | 8.0937 | 11.6405 | 13.6505 | 9.5468 | 17.6405 | 29.281 | 42.9315 | 0.01
6.5789 | 9.2894 | 8.5789 | 7.5789 | 10.8683 | 12.8683 | 9.2894 | 16.8683 | 27.7367 | 40.605 | 6.5789 | 9.2894 | 8.5789 | 7.5789 | 10.8683 | 12.8783 | 9.2894 | 16.8683 | 27.7367 | 40.615 | 0.01
4.9738 | 8.4869 | 6.9738 | 5.9738 | 8.4606 | 10.4606 | 8.4869 | 14.4606 | 22.9213 | 33.3819 | 4.9738 | 8.4869 | 6.9738 | 5.9738 | 8.4606 | 10.4706 | 8.4869 | 14.4606 | 22.9213 | 33.3919 | 0.01
5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.0914 | 8.6971 | 15.0914 | 24.1828 | 35.2741 | 5.3943 | 8.6971 | 7.3943 | 6.3943 | 9.0914 | 11.1014 | 8.6971 | 15.0914 | 24.1828 | 35.2841 | 0.01
3.3249 | 7.6624 | 5.3249 | 4.3249 | 5.9873 | 7.9873 | 7.6624 | 11.9873 | 17.9746 | 25.9618 | 3.3249 | 7.6624 | 5.3249 | 4.3249 | 5.9873 | 7.9973 | 7.6624 | 11.9873 | 17.9746 | 25.9718 | 0.01
5.9637 | 8.9818 | 7.9637 | 6.9637 | 9.9455 | 11.9455 | 8.9818 | 15.9455 | 25.891 | 37.8365 | 5.9637 | 8.9818 | 7.9637 | 6.9637 | 9.9455 | 11.9555 | 8.9818 | 15.9455 | 25.891 | 37.8465 | 0.01
3.7881 | 7.894 | 5.7881 | 4.7881 | 6.6821 | 8.6821 | 7.894 | 12.6821 | 19.3643 | 28.0464 | 3.7881 | 7.894 | 5.7881 | 4.7881 | 6.6821 | 8.6921 | 7.894 | 12.6821 | 19.3643 | 28.0564 | 0.01
8.004 | 10.002 | 10.004 | 9.004 | 13.0059 | 15.0059 | 10.002 | 19.0059 | 32.0119 | 47.0178 | 8.004 | 10.002 | 10.004 | 9.004 | 13.0059 | 15.0159 | 10.002 | 19.0059 | 32.0119 | 47.0278 | 0.01
7.6199 | 9.8099 | 9.6199 | 8.6199 | 12.4298 | 14.4298 | 9.8099 | 18.4298 | 30.8596 | 45.2893 | 7.6199 | 9.8099 | 9.6199 | 8.6199 | 12.4298 | 14.4398 | 9.8099 | 18.4298 | 30.8596 | 45.2993 | 0.01
5.0882 | 8.5441 | 7.0882 | 6.0882 | 8.6323 | 10.6323 | 8.5441 | 14.6323 | 23.2646 | 33.8968 | 5.0882 | 8.5441 | 7.0882 | 6.0882 | 8.6323 | 10.6423 | 8.5441 | 14.6323 | 23.2646 | 33.9068 | 0.01
4.9297 | 8.4649 | 6.9297 | 5.9297 | 8.3946 | 10.3946 | 8.4649 | 14.3946 | 22.7891 | 33.1837 | 4.9297 | 8.4649 | 6.9297 | 5.9297 | 8.3946 | 10.4046 | 8.4649 | 14.3946 | 22.7891 | 33.1937 | 0.01
1.9638 | 6.9819 | 3.9638 | 2.9638 | 3.9457 | 5.9457 | 6.9819 | 9.9457 | 13.8914 | 19.8371 | 1.9638 | 6.9819 | 3.9638 | 2.9638 | 3.9457 | 5.9557 | 6.9819 | 9.9457 | 13.8914 | 19.8471 | 0.01
5.227 | 8.6135 | 7.227 | 6.227 | 8.8405 | 10.8405 | 8.6135 | 14.8405 | 23.6809 | 34.5214 | 5.227 | 8.6135 | 7.227 | 6.227 | 8.8405 | 10.8505 | 8.6135 | 14.8405 | 23.6809 | 34.5314 | 0.01
2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4758 | 7.4919 | 11.4758 | 16.9515 | 24.4273 | 2.9838 | 7.4919 | 4.9838 | 3.9838 | 5.4758 | 7.4858 | 7.4919 | 11.4758 | 16.9515 | 24.4373 | 0.01
6.9433 | 9.4717 | 8.9433 | 7.9433 | 11.415 | 13.415 | 9.4717 | 17.415 | 28.83 | 42.245 | 6.9433 | 9.4717 | 8.9433 | 7.9433 | 11.415 | 13.425 | 9.4717 | 17.415 | 28.83 | 42.255 | 0.01
5.765 | 8.8825 | 7.765 | 6.765 | 9.6475 | 11.6475 | 8.8825 | 15.6475 | 25.295 | 36.9425 | 5.765 | 8.8825 | 7.765 | 6.765 | 9.6475 | 11.6575 | 8.8825 | 15.6475 | 25.295 | 36.9525 | 0.01
2.6494 | 7.3247 | 4.6494 | 3.6494 | 4.9741 | 6.9741 | 7.3247 | 10.9741 | 15.9482 | 22.9223 | 2.6494 | 7.3247 | 4.6494 | 3.6494 | 4.9741 | 6.9841 | 7.3247 | 10.9741 | 15.9482 | 22.9323 | 0.01
7.3038 | 9.6519 | 9.3038 | 8.3038 | 11.9556 | 13.9556 | 9.6519 | 17.9556 | 29.9113 | 43.8669 | 7.3038 | 9.6519 | 9.3038 | 8.3038 | 11.9556 | 13.9656 | 9.6519 | 17.9556 | 29.9113 | 43.8769 | 0.01
3.554 | 7.777 | 5.554 | 4.554 | 6.3309 | 8.3309 | 7.777 | 12.3309 | 18.6619 | 26.9928 | 3.554 | 7.777 | 5.554 | 4.554 | 6.3309 | 8.3409 | 7.777 | 12.3309 | 18.6619 | 27.0028 | 0.01
5.9113 | 8.9557 | 7.9113 | 6.9113 | 9.867 | 11.867 | 8.9557 | 15.867 | 25.7339 | 37.6009 | 5.9113 | 8.9557 | 7.9113 | 6.9113 | 9.867 | 11.877 | 8.9557 | 15.867 | 25.7339 | 37.6109 | 0.01
8.773 | 10.3865 | 10.773 | 9.773 | 14.1595 | 16.1595 | 10.3865 | 20.1595 | 34.319 | 50.4785 | 8.773 | 10.3865 | 10.773 | 9.773 | 14.1595 | 16.1695 | 10.3865 | 20.1595 | 34.319 | 50.4885 | 0.01
6.175 | 9.0875 | 8.175 | 7.175 | 10.2625 | 12.2625 | 9.0875 | 16.2625 | 26.5251 | 38.7876 | 6.175 | 9.0875 | 8.175 | 7.175 | 10.2625 | 12.2725 | 9.0875 | 16.2625 | 26.5251 | 38.7976 | 0.01
7.0464 | 9.5232 | 9.0464 | 8.0464 | 11.5695 | 13.5695 | 9.5232 | 17.5695 | 29.1391 | 42.7086 | 7.0464 | 9.5232 | 9.0464 | 8.0464 | 11.5695 | 13.5795 | 9.5232 | 17.5695 | 29.1391 | 42.7186 | 0.01
4.9413 | 8.4707 | 6.9413 | 5.9413 | 8.412 | 10.412 | 8.4707 | 14.412 | 22.824 | 33.236 | 4.9413 | 8.4707 | 6.9413 | 5.9413 | 8.412 | 10.422 | 8.4707 | 14.412 | 22.824 | 33.246 | 0.01
4.8679 | 8.434 | 6.8679 | 5.8679 | 8.3019 | 10.3019 | 8.434 | 14.3019 | 22.6038 | 32.9057 | 4.8679 | 8.434 | 6.8679 | 5.8679 | 8.3019 | 10.3119 | 8.434 | 14.3019 | 22.6038 | 32.9157 | 0.01
4.8742 | 8.4371 | 6.8742 | 5.8742 | 8.3113 | 10.3113 | 8.4371 | 14.3113 | 22.6226 | 32.9339 | 4.8742 | 8.4371 | 6.8742 | 5.8742 | 8.3113 | 10.3213 | 8.4371 | 14.3113 | 22.6226 | 32.9439 | 0.01
9.329 | 10.6645 | 11.329 | 10.329 | 14.9935 | 16.9935 | 10.6645 | 20.9935 | 35.987 | 52.9806 | 9.329 | 10.6645 | 11.329 | 10.329 | 14.9935 | 17.0035 | 10.6645 | 20.9935 | 35.987 | 52.9906 | 0.01
7.5224 | 9.7612 | 9.5224 | 8.5224 | 12.2836 | 14.2836 | 9.7612 | 18.2836 | 30.5671 | 44.8507 | 7.5224 | 9.7612 | 9.5224 | 8.5224 | 12.2836 | 14.2936 | 9.7612 | 18.2836 | 30.5671 | 44.8607 | 0.01
8.1979 | 10.0989 | 10.1979 | 9.1979 | 13.2968 | 15.2968 | 10.0989 | 19.2968 | 32.5936 | 47.8904 | 8.1979 | 10.0989 | 10.1979 | 9.1979 | 13.2968 | 15.3068 | 10.0989 | 19.2968 | 32.5936 | 47.9004 | 0.01
5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8293 | 8.6098 | 14.8293 | 23.6587 | 34.488 | 5.2196 | 8.6098 | 7.2196 | 6.2196 | 8.8293 | 10.8393 | 8.6098 | 14.8293 | 23.6587 | 34.498 | 0.01
8.1953 | 10.0977 | 10.1953 | 9.1953 | 13.293 | 15.293 | 10.0977 | 19.293 | 32.586 | 47.8791 | 8.1953 | 10.0977 | 10.1953 | 9.1953 | 13.293 | 15.303 | 10.0977 | 19.293 | 32.586 | 47.8891 | 0.01
4.9143 | 8.4572 | 6.9143 | 5.9143 | 8.3715 | 10.3715 | 8.4572 | 14.3715 | 22.7429 | 33.1144 | 4.9143 | 8.4572 | 6.9143 | 5.9143 | 8.3715 | 10.3815 | 8.4572 | 14.3715 | 22.7429 | 33.1244 | 0.01
8.9991 | 10.4995 | 10.9991 | 9.9991 | 14.4986 | 16.4986 | 10.4995 | 20.4986 | 34.9973 | 51.4959 | 8.9991 | 10.4995 | 10.9991 | 9.9991 | 14.4986 | 16.5086 | 10.4995 | 20.4986 | 34.9973 | 51.5059 | 0.01
3.9365 | 7.9683 | 5.9365 | 4.9365 | 6.9048 | 8.9048 | 7.9683 | 12.9048 | 19.8096 | 28.7143 | 3.9365 | 7.9683 | 5.9365 | 4.9365 | 6.9048 | 8.9148 | 7.9683 | 12.9048 | 19.8096 | 28.7243 | 0.01
7.8134 | 9.9067 | 9.8134 | 8.8134 | 12.7201 | 14.7201 | 9.9067 | 18.7201 | 31.4401 | 46.1602 | 7.8134 | 9.9067 | 9.8134 | 8.8134 | 12.7201 | 14.7301 | 9.9067 | 18.7201 | 31.4401 | 46.1702 | 0.01
4.0634 | 8.0317 | 6.0634 | 5.0634 | 7.0951 | 9.0951 | 8.0317 | 13.0951 | 20.1902 | 29.2853 | 4.0634 | 8.0317 | 6.0634 | 5.0634 | 7.0951 | 9.1051 | 8.0317 | 13.0951 | 20.1902 | 29.2953 | 0.01
6.7403 | 9.3702 | 8.7403 | 7.7403 | 11.1105 | 13.1105 | 9.3702 | 17.1105 | 28.221 | 41.3314 | 6.7403 | 9.3702 | 8.7403 | 7.7403 | 11.1105 | 13.1205 | 9.3702 | 17.1105 | 28.221 | 41.3414 | 0.01
5.6408 | 8.8204 | 7.6408 | 6.6408 | 9.4611 | 11.4611 | 8.8204 | 15.4611 | 24.9223 | 36.3834 | 5.6408 | 8.8204 | 7.6408 | 6.6408 | 9.4611 | 11.4711 | 8.8204 | 15.4611 | 24.9223 | 36.3934 | 0.01
6.2507 | 9.1254 | 8.2507 | 7.2507 | 10.3761 | 12.3761 | 9.1254 | 16.3761 | 26.7522 | 39.1283 | 6.2507 | 9.1254 | 8.2507 | 7.2507 | 10.3761 | 12.3861 | 9.1254 | 16.3761 | 26.7522 | 39.1383 | 0.01
8.3342 | 10.1671 | 10.3342 | 9.3342 | 13.5013 | 15.5013 | 10.1671 | 19.5013 | 33.0026 | 48.5039 | 8.3342 | 10.1671 | 10.3342 | 9.3342 | 13.5013 | 15.5113 | 10.1671 | 19.5013 | 33.0026 | 48.5139 | 0.01
9.8378 | 10.9189 | 11.8378 | 10.8378 | 15.7567 | 17.7567 | 10.9189 | 21.7567 | 37.5135 | 55.2702 | 9.8378 | 10.9189 | 11.8378 | 10.8378 | 15.7567 | 17.7667 | 10.9189 | 21.7567 | 37.5135 | 55.2802 | 0.01
5.9193 | 8.9596 | 7.9193 | 6.9193 | 9.8789 | 11.8789 | 8.9596 | 15.8789 | 25.7578 | 37.6367 | 5.9193 | 8.9596 | 7.9193 | 6.9193 | 9.8789 | 11.8889 | 8.9596 | 15.8789 | 25.7578 | 37.6467 | 0.01
9.7806 | 10.8903 | 11.7806 | 10.7806 | 15.6709 | 17.6709 | 10.8903 | 21.6709 | 37.3418 | 55.0127 | 9.7806 | 10.8903 | 11.7806 | 10.7806 | 15.6709 | 17.6809 | 10.8903 | 21.6709 | 37.3418 | 55.0227 | 0.01
7.2998 | 9.6499 | 9.2998 | 8.2998 | 11.9497 | 13.9497 | 9.6499 | 17.9497 | 29.8993 | 43.849 | 7.2998 | 9.6499 | 9.2998 | 8.2998 | 11.9497 | 13.9597 | 9.6499 | 17.9497 | 29.8993 | 43.859 | 0.01
5.2258 | 8.6129 | 7.2258 | 6.2258 | 8.8387 | 10.8387 | 8.6129 | 14.8387 | 23.6775 | 34.5162 | 5.2258 | 8.6129 | 7.2258 | 6.2258 | 8.8387 | 10.8487 | 8.6129 | 14.8387 | 23.6775 | 34.5262 | 0.01
5.5571 | 8.7785 | 7.5571 | 6.5571 | 9.3356 | 11.3356 | 8.7785 | 15.3356 | 24.6712 | 36.0068 | 5.5571 | 8.7785 | 7.5571 | 6.5571 | 9.3356 | 11.3456 | 8.7785 | 15.3356 | 24.6712 | 36.0168 | 0.01
3.6445 | 7.8223 | 5.6445 | 4.6445 | 6.4668 | 8.4668 | 7.8223 | 12.4668 | 18.9335 | 27.4003 | 3.6445 | 7.8223 | 5.6445 | 4.6445 | 6.4668 | 8.4768 | 7.8223 | 12.4668 | 18.9335 | 27.4103 | 0.01
4.0026 | 8.0013 | 6.0026 | 5.0026 | 7.0039 | 9.0039 | 8.0013 | 13.0039 | 20.0078 | 29.0117 | 4.0026 | 8.0013 | 6.0026 | 5.0026 | 7.0039 | 9.0139 | 8.0013 | 13.0039 | 20.0078 | 29.0217 | 0.01
6.0532 | 9.0266 | 8.0532 | 7.0532 | 10.0798 | 12.0798 | 9.0266 | 16.0798 | 26.1595 | 38.2393 | 6.0532 | 9.0266 | 8.0532 | 7.0532 | 10.0798 | 12.0898 | 9.0266 | 16.0798 | 26.1595 | 38.2493 | 0.01
6.9761 | 9.4881 | 8.9761 | 7.9761 | 11.4642 | 13.4642 | 9.4881 | 17.4642 | 28.9284 | 42.3925 | 6.9761 | 9.4881 | 8.9761 | 7.9761 | 11.4642 | 13.4742 | 9.4881 | 17.4642 | 28.9284 | 42.4025 | 0.01
2.4113 | 7.2056 | 4.4113 | 3.4113 | 4.6169 | 6.6169 | 7.2056 | 10.6169 | 15.2338 | 21.8508 | 2.4113 | 7.2056 | 4.4113 | 3.4113 | 4.6169 | 6.6269 | 7.2056 | 10.6169 | 15.2338 | 21.8608 | 0.01
3.7525 | 7.8762 | 5.7525 | 4.7525 | 6.6287 | 8.6287 | 7.8762 | 12.6287 | 19.2575 | 27.8862 | 3.7525 | 7.8762 | 5.7525 | 4.7525 | 6.6287 | 8.6387 | 7.8762 | 12.6287 | 19.2575 | 27.8962 | 0.01
6.4384 | 9.2192 | 8.4384 | 7.4384 | 10.6576 | 12.6576 | 9.2192 | 16.6576 | 27.3151 | 39.9727 | 6.4384 | 9.2192 | 8.4384 | 7.4384 | 10.6576 | 12.6676 | 9.2192 | 16.6576 | 27.3151 | 39.9827 | 0.01
1.4433 | 6.7216 | 3.4433 | 2.4433 | 3.1649 | 5.1649 | 6.7216 | 9.1649 | 12.3299 | 17.4948 | 1.4433 | 6.7216 | 3.4433 | 2.4433 | 3.1649 | 5.1749 | 6.7216 | 9.1649 | 12.3299 | 17.5048 | 0.01
7.9113 | 9.9557 | 9.9113 | 8.9113 | 12.867 | 14.867 | 9.9557 | 18.867 | 31.734 | 46.6009 | 7.9113 | 9.9557 | 9.9113 | 8.9113 | 12.867 | 14.877 | 9.9557 | 18.867 | 31.734 | 46.6109 | 0.01
4.1557 | 8.0779 | 6.1557 | 5.1557 | 7.2336 | 9.2336 | 8.0779 | 13.2336 | 20.4672 | 29.7007 | 4.1557 | 8.0779 | 6.1557 | 5.1557 | 7.2336 | 9.2436 | 8.0779 | 13.2336 | 20.4672 | 29.7107 | 0.01
9.7438 | 10.8719 | 11.7438 | 10.7438 | 15.6157 | 17.6157 | 10.8719 | 21.6157 | 37.2314 | 54.8471 | 9.7438 | 10.8719 | 11.7438 | 10.7438 | 15.6157 | 17.6257 | 10.8719 | 21.6157 | 37.2314 | 54.8571 | 0.01
8.0146 | 10.0073 | 10.0146 | 9.0146 | 13.0219 | 15.0219 | 10.0073 | 19.0219 | 32.0438 | 47.0657 | 8.0146 | 10.0073 | 10.0146 | 9.0146 | 13.0219 | 15.0319 | 10.0073 | 19.0219 | 32.0438 | 47.0757 | 0.01
7.2032 | 9.6016 | 9.2032 | 8.2032 | 11.8048 | 13.8048 | 9.6016 | 17.8048 | 29.6096 | 43.4144 | 7.2032 | 9.6016 | 9.2032 | 8.2032 | 11.8048 | 13.8148 | 9.6016 | 17.8048 | 29.6096 | 43.4244 | 0.01
5.1038 | 8.5519 | 7.1038 | 6.1038 | 8.6557 | 10.6557 | 8.5519 | 14.6557 | 23.3113 | 33.967 | 5.1038 | 8.5519 | 7.1038 | 6.1038 | 8.6557 | 10.6657 | 8.5519 | 14.6557 | 23.3113 | 33.977 | 0.01
10.3046 | 11.1523 | 12.3046 | 11.3046 | 16.4569 | 18.4569 | 11.1523 | 22.4569 | 38.9138 | 57.3707 | 10.3046 | 11.1523 | 12.3046 | 11.3046 | 16.4569 | 18.4669 | 11.1523 | 22.4569 | 38.9138 | 57.3807 | 0.01
6.0128 | 9.0064 | 8.0128 | 7.0128 | 10.0192 | 12.0192 | 9.0064 | 16.0192 | 26.0383 | 38.0575 | 6.0128 | 9.0064 | 8.0128 | 7.0128 | 10.0192 | 12.0292 | 9.0064 | 16.0192 | 26.0383 | 38.0675 | 0.01
5.3452 | 8.6726 | 7.3452 | 6.3452 | 9.0178 | 11.0178 | 8.6726 | 15.0178 | 24.0356 | 35.0535 | 5.3452 | 8.6726 | 7.3452 | 6.3452 | 9.0178 | 11.0278 | 8.6726 | 15.0178 | 24.0356 | 35.0635 | 0.01
5.0104 | 8.5052 | 7.0104 | 6.0104 | 8.5156 | 10.5156 | 8.5052 | 14.5156 | 23.0312 | 33.5469 | 5.0104 | 8.5052 | 7.0104 | 6.0104 | 8.5156 | 10.5256 | 8.5052 | 14.5156 | 23.0312 | 33.5569 | 0.01
8.5886 | 10.2943 | 10.5886 | 9.5886 | 13.8829 | 15.8829 | 10.2943 | 19.8829 | 33.7658 | 49.6487 | 8.5886 | 10.2943 | 10.5886 | 9.5886 | 13.8829 | 15.8929 | 10.2943 | 19.8829 | 33.7658 | 49.6587 | 0.01
4.7374 | 8.3687 | 6.7374 | 5.7374 | 8.1061 | 10.1061 | 8.3687 | 14.1061 | 22.2122 | 32.3184 | 4.7374 | 8.3687 | 6.7374 | 5.7374 | 8.1061 | 10.1161 | 8.3687 | 14.1061 | 22.2122 | 32.3284 | 0.01
4.205 | 8.1025 | 6.205 | 5.205 | 7.3075 | 9.3075 | 8.1025 | 13.3075 | 20.6151 | 29.9226 | 4.205 | 8.1025 | 6.205 | 5.205 | 7.3075 | 9.3175 | 8.1025 | 13.3075 | 20.6151 | 29.9326 | 0.01
6.7811 | 9.3906 | 8.7811 | 7.7811 | 11.1717 | 13.1717 | 9.3906 | 17.1717 | 28.3433 | 41.515 | 6.7811 | 9.3906 | 8.7811 | 7.7811 | 11.1717 | 13.1817 | 9.3906 | 17.1717 | 28.3433 | 41.525 | 0.01
5.058 | 8.529 | 7.058 | 6.058 | 8.5871 | 10.5871 | 8.529 | 14.5871 | 23.1741 | 33.7612 | 5.058 | 8.529 | 7.058 | 6.058 | 8.5871 | 10.5971 | 8.529 | 14.5871 | 23.1741 | 33.7712 | 0.01
5.1781 | 8.5891 | 7.1781 | 6.1781 | 8.7672 | 10.7672 | 8.5891 | 14.7672 | 23.5343 | 34.3015 | 5.1781 | 8.5891 | 7.1781 | 6.1781 | 8.7672 | 10.7772 | 8.5891 | 14.7672 | 23.5343 | 34.3115 | 0.01
2.0437 | 7.0219 | 4.0437 | 3.0437 | 4.0656 | 6.0656 | 7.0219 | 10.0656 | 14.1312 | 20.1968 | 2.0437 | 7.0219 | 4.0437 | 3.0437 | 4.0656 | 6.0756 | 7.0219 | 10.0656 | 14.1312 | 20.2068 | 0.01
7.546 | 9.773 | 9.546 | 8.546 | 12.319 | 14.319 | 9.773 | 18.319 | 30.6379 | 44.9569 | 7.546 | 9.773 | 9.546 | 8.546 | 12.319 | 14.329 | 9.773 | 18.319 | 30.6379 | 44.9669 | 0.01
5.6743 | 8.8371 | 7.6743 | 6.6743 | 9.5114 | 11.5114 | 8.8371 | 15.5114 | 25.0229 | 36.5343 | 5.6743 | 8.8371 | 7.6743 | 6.6743 | 9.5114 | 11.5214 | 8.8371 | 15.5114 | 25.0229 | 36.5443 | 0.01
4.0812 | 8.0406 | 6.0812 | 5.0812 | 7.1218 | 9.1218 | 8.0406 | 13.1218 | 20.2435 | 29.3653 | 4.0812 | 8.0406 | 6.0812 | 5.0812 | 7.1218 | 9.1318 | 8.0406 | 13.1218 | 20.2435 | 29.3753 | 0.01
9.5518 | 10.7759 | 11.5518 | 10.5518 | 15.3277 | 17.3277 | 10.7759 | 21.3277 | 36.6555 | 53.9832 | 9.5518 | 10.7759 | 11.5518 | 10.5518 | 15.3277 | 17.3377 | 10.7759 | 21.3277 | 36.6555 | 53.9932 | 0.01
7.9334 | 9.9667 | 9.9334 | 8.9334 | 12.9001 | 14.9001 | 9.9667 | 18.9001 | 31.8003 | 46.7004 | 7.9334 | 9.9667 | 9.9334 | 8.9334 | 12.9001 | 14.9101 | 9.9667 | 18.9001 | 31.8003 | 46.7104 | 0.01
4.7753 | 8.3876 | 6.7753 | 5.7753 | 8.1629 | 10.1629 | 8.3876 | 14.1629 | 22.3258 | 32.4888 | 4.7753 | 8.3876 | 6.7753 | 5.7753 | 8.1629 | 10.1729 | 8.3876 | 14.1629 | 22.3258 | 32.4988 | 0.01
8.5211 | 10.2606 | 10.5211 | 9.5211 | 13.7817 | 15.7817 | 10.2606 | 19.7817 | 33.5634 | 49.3451 | 8.5211 | 10.2606 | 10.5211 | 9.5211 | 13.7817 | 15.7917 | 10.2606 | 19.7817 | 33.5634 | 49.3551 | 0.01
5.7198 | 8.8599 | 7.7198 | 6.7198 | 9.5797 | 11.5797 | 8.8599 | 15.5797 | 25.1594 | 36.7391 | 5.7198 | 8.8599 | 7.7198 | 6.7198 | 9.5797 | 11.5897 | 8.8599 | 15.5797 | 25.1594 | 36.7491 | 0.01
4.9962 | 8.4981 | 6.9962 | 5.9962 | 8.4943 | 10.4943 | 8.4981 | 14.4943 | 22.9886 | 33.4829 | 4.9962 | 8.4981 | 6.9962 | 5.9962 | 8.4943 | 10.5043 | 8.4981 | 14.4943 | 22.9886 | 33.4929 | 0.01
5.1437 | 8.5718 | 7.1437 | 6.1437 | 8.7155 | 10.7155 | 8.5718 | 14.7155 | 23.4311 | 34.1466 | 5.1437 | 8.5718 | 7.1437 | 6.1437 | 8.7155 | 10.7255 | 8.5718 | 14.7155 | 23.4311 | 34.1566 | 0.01
5.9165 | 8.9583 | 7.9165 | 6.9165 | 9.8748 | 11.8748 | 8.9583 | 15.8748 | 25.7496 | 37.6243 | 5.9165 | 8.9583 | 7.9165 | 6.9165 | 9.8748 | 11.8848 | 8.9583 | 15.8748 | 25.7496 | 37.6343 | 0.01
6.5709 | 9.2855 | 8.5709 | 7.5709 | 10.8564 | 12.8564 | 9.2855 | 16.8564 | 27.7128 | 40.5691 | 6.5709 | 9.2855 | 8.5709 | 7.5709 | 10.8564 | 12.8664 | 9.2855 | 16.8564 | 27.7128 | 40.5791 | 0.01
4.407 | 8.2035 | 6.407 | 5.407 | 7.6105 | 9.6105 | 8.2035 | 13.6105 | 21.2209 | 30.8314 | 4.407 | 8.2035 | 6.407 | 5.407 | 7.6105 | 9.6205 | 8.2035 | 13.6105 | 21.2209 | 30.8414 | 0.01
7.6827 | 9.8413 | 9.6827 | 8.6827 | 12.524 | 14.524 | 9.8413 | 18.524 | 31.048 | 45.572 | 7.6827 | 9.8413 | 9.6827 | 8.6827 | 12.524 | 14.534 | 9.8413 | 18.524 | 31.048 | 45.582 | 0.01
5.0637 | 8.5318 | 7.0637 | 6.0637 | 8.5955 | 10.5955 | 8.5318 | 14.5955 | 23.191 | 33.7865 | 5.0637 | 8.5318 | 7.0637 | 6.0637 | 8.5955 | 10.6055 | 8.5318 | 14.5955 | 23.191 | 33.7965 | 0.01
3.1421 | 7.5711 | 5.1421 | 4.1421 | 5.7132 | 7.7132 | 7.5711 | 11.7132 | 17.4263 | 25.1395 | 3.1421 | 7.5711 | 5.1421 | 4.1421 | 5.7132 | 7.7232 | 7.5711 | 11.7132 | 17.4263 | 25.1495 | 0.01
8.3315 | 10.1657 | 10.3315 | 9.3315 | 13.4972 | 15.4972 | 10.1657 | 19.4972 | 32.9944 | 48.4916 | 8.3315 | 10.1657 | 10.3315 | 9.3315 | 13.4972 | 15.5072 | 10.1657 | 19.4972 | 32.9944 | 48.5016 | 0.01
7.0219 | 9.5109 | 9.0219 | 8.0219 | 11.5328 | 13.5328 | 9.5109 | 17.5328 | 29.0656 | 42.5985 | 7.0219 | 9.5109 | 9.0219 | 8.0219 | 11.5328 | 13.5428 | 9.5109 | 17.5328 | 29.0656 | 42.6085 | 0.01
7.4577 | 9.7289 | 9.4577 | 8.4577 | 12.1866 | 14.1866 | 9.7289 | 18.1866 | 30.3732 | 44.5599 | 7.4577 | 9.7289 | 9.4577 | 8.4577 | 12.1866 | 14.1966 | 9.7289 | 18.1866 | 30.3732 | 44.5699 | 0.01
8.7512 | 10.3756 | 10.7512 | 9.7512 | 14.1268 | 16.1268 | 10.3756 | 20.1268 | 34.2535 | 50.3803 | 8.7512 | 10.3756 | 10.7512 | 9.7512 | 14.1268 | 16.1368 | 10.3756 | 20.1268 | 34.2535 | 50.3903 | 0.01
3.186 | 7.593 | 5.186 | 4.186 | 5.779 | 7.779 | 7.593 | 11.779 | 17.558 | 25.337 | 3.186 | 7.593 | 5.186 | 4.186 | 5.779 | 7.789 | 7.593 | 11.779 | 17.558 | 25.347 | 0.01
3.9737 | 7.9868 | 5.9737 | 4.9737 | 6.9605 | 8.9605 | 7.9868 | 12.9605 | 19.921 | 28.8815 | 3.9737 | 7.9868 | 5.9737 | 4.9737 | 6.9605 | 8.9705 | 7.9868 | 12.9605 | 19.921 | 28.8915 | 0.01
6.1466 | 9.0733 | 8.1466 | 7.1466 | 10.2199 | 12.2199 | 9.0733 | 16.2199 | 26.4399 | 38.6598 | 6.1466 | 9.0733 | 8.1466 | 7.1466 | 10.2199 | 12.2299 | 9.0733 | 16.2199 | 26.4399 | 38.6698 | 0.01
4.2176 | 8.1088 | 6.2176 | 5.2176 | 7.3264 | 9.3264 | 8.1088 | 13.3264 | 20.6527 | 29.9791 | 4.2176 | 8.1088 | 6.2176 | 5.2176 | 7.3264 | 9.3364 | 8.1088 | 13.3264 | 20.6527 | 29.9891 | 0.01
6.6912 | 9.3456 | 8.6912 | 7.6912 | 11.0368 | 13.0368 | 9.3456 | 17.0368 | 28.0737 | 41.1105 | 6.6912 | 9.3456 | 8.6912 | 7.6912 | 11.0368 | 13.0468 | 9.3456 | 17.0368 | 28.0737 | 41.1205 | 0.01
4.7236 | 8.3618 | 6.7236 | 5.7236 | 8.0853 | 10.0853 | 8.3618 | 14.0853 | 22.1707 | 32.256 | 4.7236 | 8.3618 | 6.7236 | 5.7236 | 8.0853 | 10.0953 | 8.3618 | 14.0853 | 22.1707 | 32.266 | 0.01
4.7267 | 8.3634 | 6.7267 | 5.7267 | 8.0901 | 10.0901 | 8.3634 | 14.0901 | 22.1802 | 32.2704 | 4.7267 | 8.3634 | 6.7267 | 5.7267 | 8.0901 | 10.1001 | 8.3634 | 14.0901 | 22.1802 | 32.2804 | 0.01
7.199 | 9.5995 | 9.199 | 8.199 | 11.7985 | 13.7985 | 9.5995 | 17.7985 | 29.5969 | 43.3954 | 7.199 | 9.5995 | 9.199 | 8.199 | 11.7985 | 13.8085 | 9.5995 | 17.7985 | 29.5969 | 43.4054 | 0.01
3.7067 | 7.8534 | 5.7067 | 4.7067 | 6.5601 | 8.5601 | 7.8534 | 12.5601 | 19.1202 | 27.6803 | 3.7067 | 7.8534 | 5.7067 | 4.7067 | 6.5601 | 8.5701 | 7.8534 | 12.5601 | 19.1202 | 27.6903 | 0.01
5.995 | 8.9975 | 7.995 | 6.995 | 9.9925 | 11.9925 | 8.9975 | 15.9925 | 25.9851 | 37.9776 | 5.995 | 8.9975 | 7.995 | 6.995 | 9.9925 | 12.0025 | 8.9975 | 15.9925 | 25.9851 | 37.9876 | 0.01
5.0831 | 8.5415 | 7.0831 | 6.0831 | 8.6246 | 10.6246 | 8.5415 | 14.6246 | 23.2493 | 33.8739 | 5.0831 | 8.5415 | 7.0831 | 6.0831 | 8.6246 | 10.6346 | 8.5415 | 14.6246 | 23.2493 | 33.8839 | 0.01
6.1092 | 9.0546 | 8.1092 | 7.1092 | 10.1638 | 12.1638 | 9.0546 | 16.1638 | 26.3277 | 38.4915 | 6.1092 | 9.0546 | 8.1092 | 7.1092 | 10.1638 | 12.1738 | 9.0546 | 16.1638 | 26.3277 | 38.5015 | 0.01
8.5861 | 10.2931 | 10.5861 | 9.5861 | 13.8792 | 15.8792 | 10.2931 | 19.8792 | 33.7584 | 49.6375 | 8.5861 | 10.2931 | 10.5861 | 9.5861 | 13.8792 | 15.8892 | 10.2931 | 19.8792 | 33.7584 | 49.6475 | 0.01
5.3112 | 8.6556 | 7.3112 | 6.3112 | 8.9668 | 10.9668 | 8.6556 | 14.9668 | 23.9337 | 34.9005 | 5.3112 | 8.6556 | 7.3112 | 6.3112 | 8.9668 | 10.9768 | 8.6556 | 14.9668 | 23.9337 | 34.9105 | 0.01
3.0662 | 7.5331 | 5.0662 | 4.0662 | 5.5993 | 7.5993 | 7.5331 | 11.5993 | 17.1985 | 24.7978 | 3.0662 | 7.5331 | 5.0662 | 4.0662 | 5.5993 | 7.6093 | 7.5331 | 11.5993 | 17.1985 | 24.8078 | 0.01
5.713 | 8.8565 | 7.713 | 6.713 | 9.5695 | 11.5695 | 8.8565 | 15.5695 | 25.139 | 36.7085 | 5.713 | 8.8565 | 7.713 | 6.713 | 9.5695 | 11.5795 | 8.8565 | 15.5695 | 25.139 | 36.7185 | 0.01
2.1945 | 7.0972 | 4.1945 | 3.1945 | 4.2917 | 6.2917 | 7.0972 | 10.2917 | 14.5834 | 20.8751 | 2.1945 | 7.0972 | 4.1945 | 3.1945 | 4.2917 | 6.3017 | 7.0972 | 10.2917 | 14.5834 | 20.8851 | 0.01
4.0199 | 8.01 | 6.0199 | 5.0199 | 7.0299 | 9.0299 | 8.01 | 13.0299 | 20.0597 | 29.0896 | 4.0199 | 8.01 | 6.0199 | 5.0199 | 7.0299 | 9.0399 | 8.01 | 13.0299 | 20.0597 | 29.0996 | 0.01
6.6125 | 9.3062 | 8.6125 | 7.6125 | 10.9187 | 12.9187 | 9.3062 | 16.9187 | 27.8374 | 40.7562 | 6.6125 | 9.3062 | 8.6125 | 7.6125 | 10.9187 | 12.9287 | 9.3062 | 16.9187 | 27.8374 | 40.7662 | 0.01
6.4942 | 9.2471 | 8.4942 | 7.4942 | 10.7413 | 12.7413 | 9.2471 | 16.7413 | 27.4826 | 40.2239 | 6.4942 | 9.2471 | 8.4942 | 7.4942 | 10.7413 | 12.7513 | 9.2471 | 16.7413 | 27.4826 | 40.2339 | 0.01
5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6381 | 8.546 | 14.6381 | 23.2763 | 33.9144 | 5.0921 | 8.546 | 7.0921 | 6.0921 | 8.6381 | 10.6481 | 8.546 | 14.6381 | 23.2763 | 33.9244 | 0.01
5.964 | 8.982 | 7.964 | 6.964 | 9.946 | 11.946 | 8.982 | 15.946 | 25.8919 | 37.8379 | 5.964 | 8.982 | 7.964 | 6.964 | 9.946 | 11.956 | 8.982 | 15.946 | 25.8919 | 37.8479 | 0.01
5.7816 | 8.8908 | 7.7816 | 6.7816 | 9.6724 | 11.6724 | 8.8908 | 15.6724 | 25.3449 | 37.0173 | 5.7816 | 8.8908 | 7.7816 | 6.7816 | 9.6724 | 11.6824 | 8.8908 | 15.6724 | 25.3449 | 37.0273 | 0.01
3.5707 | 7.7853 | 5.5707 | 4.5707 | 6.356 | 8.356 | 7.7853 | 12.356 | 18.712 | 27.068 | 3.5707 | 7.7853 | 5.5707 | 4.5707 | 6.356 | 8.366 | 7.7853 | 12.356 | 18.712 | 27.078 | 0.01
3.9955 | 7.9978 | 5.9955 | 4.9955 | 6.9933 | 8.9933 | 7.9978 | 12.9933 | 19.9866 | 28.9799 | 3.9955 | 7.9978 | 5.9955 | 4.9955 | 6.9933 | 9.0033 | 7.9978 | 12.9933 | 19.9866 | 28.9899 | 0.01
6.0997 | 9.0499 | 8.0997 | 7.0997 | 10.1496 | 12.1496 | 9.0499 | 16.1496 | 26.2992 | 38.4487 | 6.0997 | 9.0499 | 8.0997 | 7.0997 | 10.1496 | 12.1596 | 9.0499 | 16.1496 | 26.2992 | 38.4587 | 0.01
7.8375 | 9.9188 | 9.8375 | 8.8375 | 12.7563 | 14.7563 | 9.9188 | 18.7563 | 31.5125 | 46.2688 | 7.8375 | 9.9188 | 9.8375 | 8.8375 | 12.7563 | 14.7663 | 9.9188 | 18.7563 | 31.5125 | 46.2788 | 0.01
6.5393 | 9.2696 | 8.5393 | 7.5393 | 10.8089 | 12.8089 | 9.2696 | 16.8089 | 27.6178 | 40.4267 | 6.5393 | 9.2696 | 8.5393 | 7.5393 | 10.8089 | 12.8189 | 9.2696 | 16.8089 | 27.6178 | 40.4367 | 0.01
3.8684 | 7.9342 | 5.8684 | 4.8684 | 6.8026 | 8.8026 | 7.9342 | 12.8026 | 19.6051 | 28.4077 | 3.8684 | 7.9342 | 5.8684 | 4.8684 | 6.8026 | 8.8126 | 7.9342 | 12.8026 | 19.6051 | 28.4177 | 0.01
5.8862 | 8.9431 | 7.8862 | 6.8862 | 9.8293 | 11.8293 | 8.9431 | 15.8293 | 25.6586 | 37.4878 | 5.8862 | 8.9431 | 7.8862 | 6.8862 | 9.8293 | 11.8393 | 8.9431 | 15.8293 | 25.6586 | 37.4978 | 0.01
4.754 | 8.377 | 6.754 | 5.754 | 8.131 | 10.131 | 8.377 | 14.131 | 22.262 | 32.3929 | 4.754 | 8.377 | 6.754 | 5.754 | 8.131 | 10.141 | 8.377 | 14.131 | 22.262 | 32.4029 | 0.01
3.8834 | 7.9417 | 5.8834 | 4.8834 | 6.8251 | 8.8251 | 7.9417 | 12.8251 | 19.6503 | 28.4754 | 3.8834 | 7.9417 | 5.8834 | 4.8834 | 6.8251 | 8.8351 | 7.9417 | 12.8251 | 19.6503 | 28.4854 | 0.01
5.5401 | 8.7701 | 7.5401 | 6.5401 | 9.3102 | 11.3102 | 8.7701 | 15.3102 | 24.6204 | 35.9306 | 5.5401 | 8.7701 | 7.5401 | 6.5401 | 9.3102 | 11.3202 | 8.7701 | 15.3102 | 24.6204 | 35.9406 | 0.01
6.0247 | 9.0124 | 8.0247 | 7.0247 | 10.0371 | 12.0371 | 9.0124 | 16.0371 | 26.0741 | 38.1112 | 6.0247 | 9.0124 | 8.0247 | 7.0247 | 10.0371 | 12.0471 | 9.0124 | 16.0371 | 26.0741 | 38.1212 | 0.01
4.9316 | 8.4658 | 6.9316 | 5.9316 | 8.3975 | 10.3975 | 8.4658 | 14.3975 | 22.7949 | 33.1924 | 4.9316 | 8.4658 | 6.9316 | 5.9316 | 8.3975 | 10.4075 | 8.4658 | 14.3975 | 22.7949 | 33.2024 | 0.01
9.3444 | 10.6722 | 11.3444 | 10.3444 | 15.0166 | 17.0166 | 10.6722 | 21.0166 | 36.0332 | 53.0498 | 9.3444 | 10.6722 | 11.3444 | 10.3444 | 15.0166 | 17.0266 | 10.6722 | 21.0166 | 36.0332 | 53.0598 | 0.01
6.4224 | 9.2112 | 8.4224 | 7.4224 | 10.6336 | 12.6336 | 9.2112 | 16.6336 | 27.2672 | 39.9008 | 6.4224 | 9.2112 | 8.4224 | 7.4224 | 10.6336 | 12.6436 | 9.2112 | 16.6336 | 27.2672 | 39.9108 | 0.01
5.0339 | 8.5169 | 7.0339 | 6.0339 | 8.5508 | 10.5508 | 8.5169 | 14.5508 | 23.1016 | 33.6524 | 5.0339 | 8.5169 | 7.0339 | 6.0339 | 8.5508 | 10.5608 | 8.5169 | 14.5508 | 23.1016 | 33.6624 | 0.01
5.9344 | 8.9672 | 7.9344 | 6.9344 | 9.9016 | 11.9016 | 8.9672 | 15.9016 | 25.8033 | 37.7049 | 5.9344 | 8.9672 | 7.9344 | 6.9344 | 9.9016 | 11.9116 | 8.9672 | 15.9016 | 25.8033 | 37.7149 | 0.01
6.8634 | 9.4317 | 8.8634 | 7.8634 | 11.295 | 13.295 | 9.4317 | 17.295 | 28.5901 | 41.8851 | 6.8634 | 9.4317 | 8.8634 | 7.8634 | 11.295 | 13.305 | 9.4317 | 17.295 | 28.5901 | 41.8951 | 0.01
3.9905 | 7.9952 | 5.9905 | 4.9905 | 6.9857 | 8.9857 | 7.9952 | 12.9857 | 19.9714 | 28.9572 | 3.9905 | 7.9952 | 5.9905 | 4.9905 | 6.9857 | 8.9957 | 7.9952 | 12.9857 | 19.9714 | 28.9672 | 0.01
7.2021 | 9.601 | 9.2021 | 8.2021 | 11.8031 | 13.8031 | 9.601 | 17.8031 | 29.6063 | 43.4094 | 7.2021 | 9.601 | 9.2021 | 8.2021 | 11.8031 | 13.8131 | 9.601 | 17.8031 | 29.6063 | 43.4194 | 0.01
0.53517 | 6.2676 | 2.5352 | 1.5352 | 1.8028 | 3.8028 | 6.2676 | 7.8028 | 9.6055 | 13.4083 | 0.53517 | 6.2676 | 2.5352 | 1.5352 | 1.8028 | 3.8128 | 6.2676 | 7.8028 | 9.6055 | 13.4183 | 0.01
5.5684 | 8.7842 | 7.5684 | 6.5684 | 9.3525 | 11.3525 | 8.7842 | 15.3525 | 24.7051 | 36.0576 | 5.5684 | 8.7842 | 7.5684 | 6.5684 | 9.3525 | 11.3625 | 8.7842 | 15.3525 | 24.7051 | 36.0676 | 0.01
5.3874 | 8.6937 | 7.3874 | 6.3874 | 9.081 | 11.081 | 8.6937 | 15.081 | 24.1621 | 35.2431 | 5.3874 | 8.6937 | 7.3874 | 6.3874 | 9.081 | 11.091 | 8.6937 | 15.081 | 24.1621 | 35.2531 | 0.01
6.5294 | 9.2647 | 8.5294 | 7.5294 | 10.7942 | 12.7942 | 9.2647 | 16.7942 | 27.5883 | 40.3825 | 6.5294 | 9.2647 | 8.5294 | 7.5294 | 10.7942 | 12.8042 | 9.2647 | 16.7942 | 27.5883 | 40.3925 | 0.01
8.7496 | 10.3748 | 10.7496 | 9.7496 | 14.1244 | 16.1244 | 10.3748 | 20.1244 | 34.2488 | 50.3732 | 8.7496 | 10.3748 | 10.7496 | 9.7496 | 14.1244 | 16.1344 | 10.3748 | 20.1244 | 34.2488 | 50.3832 | 0.01
5.9569 | 8.9785 | 7.9569 | 6.9569 | 9.9354 | 11.9354 | 8.9785 | 15.9354 | 25.8708 | 37.8062 | 5.9569 | 8.9785 | 7.9569 | 6.9569 | 9.9354 | 11.9454 | 8.9785 | 15.9354 | 25.8708 | 37.8162 | 0.01
5.1926 | 8.5963 | 7.1926 | 6.1926 | 8.7889 | 10.7889 | 8.5963 | 14.7889 | 23.5777 | 34.3666 | 5.1926 | 8.5963 | 7.1926 | 6.1926 | 8.7889 | 10.7989 | 8.5963 | 14.7889 | 23.5777 | 34.3766 | 0.01
4.5049 | 8.2524 | 6.5049 | 5.5049 | 7.7573 | 9.7573 | 8.2524 | 13.7573 | 21.5146 | 31.272 | 4.5049 | 8.2524 | 6.5049 | 5.5049 | 7.7573 | 9.7673 | 8.2524 | 13.7573 | 21.5146 | 31.282 | 0.01
4.4453 | 8.2227 | 6.4453 | 5.4453 | 7.668 | 9.668 | 8.2227 | 13.668 | 21.336 | 31.004 | 4.4453 | 8.2227 | 6.4453 | 5.4453 | 7.668 | 9.678 | 8.2227 | 13.668 | 21.336 | 31.014 | 0.01
8.9107 | 10.4553 | 10.9107 | 9.9107 | 14.366 | 16.366 | 10.4553 | 20.366 | 34.7321 | 51.0981 | 8.9107 | 10.4553 | 10.9107 | 9.9107 | 14.366 | 16.376 | 10.4553 | 20.366 | 34.7321 | 51.1081 | 0.01
5.5784 | 8.7892 | 7.5784 | 6.5784 | 9.3676 | 11.3676 | 8.7892 | 15.3676 | 24.7351 | 36.1027 | 5.5784 | 8.7892 | 7.5784 | 6.5784 | 9.3676 | 11.3776 | 8.7892 | 15.3676 | 24.7351 | 36.1127 | 0.01
6.5968 | 9.2984 | 8.5968 | 7.5968 | 10.8952 | 12.8952 | 9.2984 | 16.8952 | 27.7903 | 40.6855 | 6.5968 | 9.2984 | 8.5968 | 7.5968 | 10.8952 | 12.9052 | 9.2984 | 16.8952 | 27.7903 | 40.6955 | 0.01
9.5841 | 10.7921 | 11.5841 | 10.5841 | 15.3762 | 17.3762 | 10.7921 | 21.3762 | 36.7524 | 54.1286 | 9.5841 | 10.7921 | 11.5841 | 10.5841 | 15.3762 | 17.3862 | 10.7921 | 21.3762 | 36.7524 | 54.1386 | 0.01
7.1421 | 9.5711 | 9.1421 | 8.1421 | 11.7132 | 13.7132 | 9.5711 | 17.7132 | 29.4264 | 43.1397 | 7.1421 | 9.5711 | 9.1421 | 8.1421 | 11.7132 | 13.7232 | 9.5711 | 17.7132 | 29.4264 | 43.1497 | 0.01
6.9164 | 9.4582 | 8.9164 | 7.9164 | 11.3746 | 13.3746 | 9.4582 | 17.3746 | 28.7492 | 42.1238 | 6.9164 | 9.4582 | 8.9164 | 7.9164 | 11.3746 | 13.3846 | 9.4582 | 17.3746 | 28.7492 | 42.1338 | 0.01
8.2153 | 10.1076 | 10.2153 | 9.2153 | 13.3229 | 15.3229 | 10.1076 | 19.3229 | 32.6459 | 47.9688 | 8.2153 | 10.1076 | 10.2153 | 9.2153 | 13.3229 | 15.3329 | 10.1076 | 19.3229 | 32.6459 | 47.9788 | 0.01
5.5263 | 8.7631 | 7.5263 | 6.5263 | 9.2894 | 11.2894 | 8.7631 | 15.2894 | 24.5789 | 35.8683 | 5.5263 | 8.7631 | 7.5263 | 6.5263 | 9.2894 | 11.2994 | 8.7631 | 15.2894 | 24.5789 | 35.8783 | 0.01
11.0337 | 11.5168 | 13.0337 | 12.0337 | 17.5505 | 19.5505 | 11.5168 | 23.5505 | 41.101 | 60.6514 | 11.0337 | 11.5168 | 13.0337 | 12.0337 | 17.5505 | 19.5605 | 11.5168 | 23.5505 | 41.101 | 60.6614 | 0.01
6.0016 | 9.0008 | 8.0016 | 7.0016 | 10.0024 | 12.0024 | 9.0008 | 16.0024 | 26.0048 | 38.0072 | 6.0016 | 9.0008 | 8.0016 | 7.0016 | 10.0024 | 12.0124 | 9.0008 | 16.0024 | 26.0048 | 38.0172 | 0.01
10.3738 | 11.1869 | 12.3738 | 11.3738 | 16.5607 | 18.5607 | 11.1869 | 22.5607 | 39.1215 | 57.6822 | 10.3738 | 11.1869 | 12.3738 | 11.3738 | 16.5607 | 18.5707 | 11.1869 | 22.5607 | 39.1215 | 57.6922 | 0.01
6.4121 | 9.206 | 8.4121 | 7.4121 | 10.6181 | 12.6181 | 9.206 | 16.6181 | 27.2363 | 39.8544 | 6.4121 | 9.206 | 8.4121 | 7.4121 | 10.6181 | 12.6281 | 9.206 | 16.6181 | 27.2363 | 39.8644 | 0.01
9.217 | 10.6085 | 11.217 | 10.217 | 14.8254 | 16.8254 | 10.6085 | 20.8254 | 35.6509 | 52.4763 | 9.217 | 10.6085 | 11.217 | 10.217 | 14.8254 | 16.8354 | 10.6085 | 20.8254 | 35.6509 | 52.4863 | 0.01
9.7797 | 10.8898 | 11.7797 | 10.7797 | 15.6695 | 17.6695 | 10.8898 | 21.6695 | 37.3391 | 55.0086 | 9.7797 | 10.8898 | 11.7797 | 10.7797 | 15.6695 | 17.6795 | 10.8898 | 21.6695 | 37.3391 | 55.0186 | 0.01
5.0423 | 8.5211 | 7.0423 | 6.0423 | 8.5634 | 10.5634 | 8.5211 | 14.5634 | 23.1268 | 33.6903 | 5.0423 | 8.5211 | 7.0423 | 6.0423 | 8.5634 | 10.5734 | 8.5211 | 14.5634 | 23.1268 | 33.7003 | 0.01
4.3481 | 8.174 | 6.3481 | 5.3481 | 7.5221 | 9.5221 | 8.174 | 13.5221 | 21.0442 | 30.5663 | 4.3481 | 8.174 | 6.3481 | 5.3481 | 7.5221 | 9.5321 | 8.174 | 13.5221 | 21.0442 | 30.5763 | 0.01
7.1758 | 9.5879 | 9.1758 | 8.1758 | 11.7637 | 13.7637 | 9.5879 | 17.7637 | 29.5274 | 43.2911 | 7.1758 | 9.5879 | 9.1758 | 8.1758 | 11.7637 | 13.7737 | 9.5879 | 17.7637 | 29.5274 | 43.3011 | 0.01
4.6681 | 8.3341 | 6.6681 | 5.6681 | 8.0022 | 10.0022 | 8.3341 | 14.0022 | 22.0043 | 32.0065 | 4.6681 | 8.3341 | 6.6681 | 5.6681 | 8.0022 | 10.0122 | 8.3341 | 14.0022 | 22.0043 | 32.0165 | 0.01
1.8921 | 6.946 | 3.8921 | 2.8921 | 3.8381 | 5.8381 | 6.946 | 9.8381 | 13.6762 | 19.5143 | 1.8921 | 6.946 | 3.8921 | 2.8921 | 3.8381 | 5.8481 | 6.946 | 9.8381 | 13.6762 | 19.5243 | 0.01
5.0109 | 8.5055 | 7.0109 | 6.0109 | 8.5164 | 10.5164 | 8.5055 | 14.5164 | 23.0328 | 33.5492 | 5.0109 | 8.5055 | 7.0109 | 6.0109 | 8.5164 | 10.5264 | 8.5055 | 14.5164 | 23.0328 | 33.5592 | 0.01
3.8584 | 7.9292 | 5.8584 | 4.8584 | 6.7875 | 8.7875 | 7.9292 | 12.7875 | 19.5751 | 28.3626 | 3.8584 | 7.9292 | 5.8584 | 4.8584 | 6.7875 | 8.7975 | 7.9292 | 12.7875 | 19.5751 | 28.3726 | 0.01
6.4966 | 9.2483 | 8.4966 | 7.4966 | 10.7448 | 12.7448 | 9.2483 | 16.7448 | 27.4897 | 40.2345 | 6.4966 | 9.2483 | 8.4966 | 7.4966 | 10.7448 | 12.7548 | 9.2483 | 16.7448 | 27.4897 | 40.2445 | 0.01
7.0352 | 9.5176 | 9.0352 | 8.0352 | 11.5527 | 13.5527 | 9.5176 | 17.5527 | 29.1055 | 42.6582 | 7.0352 | 9.5176 | 9.0352 | 8.0352 | 11.5527 | 13.5627 | 9.5176 | 17.5527 | 29.1055 | 42.6682 | 0.01
6.1885 | 9.0943 | 8.1885 | 7.1885 | 10.2828 | 12.2828 | 9.0943 | 16.2828 | 26.5656 | 38.8484 | 6.1885 | 9.0943 | 8.1885 | 7.1885 | 10.2828 | 12.2928 | 9.0943 | 16.2828 | 26.5656 | 38.8584 | 0.01
5.8998 | 8.9499 | 7.8998 | 6.8998 | 9.8497 | 11.8497 | 8.9499 | 15.8497 | 25.6995 | 37.5492 | 5.8998 | 8.9499 | 7.8998 | 6.8998 | 9.8497 | 11.8597 | 8.9499 | 15.8497 | 25.6995 | 37.5592 | 0.01
3.7522 | 7.8761 | 5.7522 | 4.7522 | 6.6283 | 8.6283 | 7.8761 | 12.6283 | 19.2566 | 27.8849 | 3.7522 | 7.8761 | 5.7522 | 4.7522 | 6.6283 | 8.6383 | 7.8761 | 12.6283 | 19.2566 | 27.8949 | 0.01
6.776 | 9.388 | 8.776 | 7.776 | 11.164 | 13.164 | 9.388 | 17.164 | 28.328 | 41.492 | 6.776 | 9.388 | 8.776 | 7.776 | 11.164 | 13.174 | 9.388 | 17.164 | 28.328 | 41.502 | 0.01
5.7807 | 8.8903 | 7.7807 | 6.7807 | 9.671 | 11.671 | 8.8903 | 15.671 | 25.3421 | 37.0131 | 5.7807 | 8.8903 | 7.7807 | 6.7807 | 9.671 | 11.681 | 8.8903 | 15.671 | 25.3421 | 37.0231 | 0.01
3.3449 | 7.6725 | 5.3449 | 4.3449 | 6.0174 | 8.0174 | 7.6725 | 12.0174 | 18.0348 | 26.0522 | 3.3449 | 7.6725 | 5.3449 | 4.3449 | 6.0174 | 8.0274 | 7.6725 | 12.0174 | 18.0348 | 26.0622 | 0.01
3.0968 | 7.5484 | 5.0968 | 4.0968 | 5.6452 | 7.6452 | 7.5484 | 11.6452 | 17.2904 | 24.9355 | 3.0968 | 7.5484 | 5.0968 | 4.0968 | 5.6452 | 7.6552 | 7.5484 | 11.6452 | 17.2904 | 24.9455 | 0.01
7.9137 | 9.9569 | 9.9137 | 8.9137 | 12.8706 | 14.8706 | 9.9569 | 18.8706 | 31.7412 | 46.6118 | 7.9137 | 9.9569 | 9.9137 | 8.9137 | 12.8706 | 14.8806 | 9.9569 | 18.8706 | 31.7412 | 46.6218 | 0.01
8.1265 | 10.0633 | 10.1265 | 9.1265 | 13.1898 | 15.1898 | 10.0633 | 19.1898 | 32.3795 | 47.5693 | 8.1265 | 10.0633 | 10.1265 | 9.1265 | 13.1898 | 15.1998 | 10.0633 | 19.1898 | 32.3795 | 47.5793 | 0.01
4.2244 | 8.1122 | 6.2244 | 5.2244 | 7.3366 | 9.3366 | 8.1122 | 13.3366 | 20.6732 | 30.0098 | 4.2244 | 8.1122 | 6.2244 | 5.2244 | 7.3366 | 9.3466 | 8.1122 | 13.3366 | 20.6732 | 30.0198 | 0.01
6.3537 | 9.1768 | 8.3537 | 7.3537 | 10.5305 | 12.5305 | 9.1768 | 16.5305 | 27.061 | 39.5914 | 6.3537 | 9.1768 | 8.3537 | 7.3537 | 10.5305 | 12.5405 | 9.1768 | 16.5305 | 27.061 | 39.6014 | 0.01
11.168 | 11.584 | 13.168 | 12.168 | 17.7521 | 19.7521 | 11.584 | 23.7521 | 41.5041 | 61.2562 | 11.168 | 11.584 | 13.168 | 12.168 | 17.7521 | 19.7621 | 11.584 | 23.7521 | 41.5041 | 61.2662 | 0.01
5.4518 | 8.7259 | 7.4518 | 6.4518 | 9.1778 | 11.1778 | 8.7259 | 15.1778 | 24.3555 | 35.5333 | 5.4518 | 8.7259 | 7.4518 | 6.4518 | 9.1778 | 11.1878 | 8.7259 | 15.1778 | 24.3555 | 35.5433 | 0.01
6.0492 | 9.0246 | 8.0492 | 7.0492 | 10.0738 | 12.0738 | 9.0246 | 16.0738 | 26.1476 | 38.2214 | 6.0492 | 9.0246 | 8.0492 | 7.0492 | 10.0738 | 12.0838 | 9.0246 | 16.0738 | 26.1476 | 38.2314 | 0.01
7.4105 | 9.7052 | 9.4105 | 8.4105 | 12.1157 | 14.1157 | 9.7052 | 18.1157 | 30.2314 | 44.3471 | 7.4105 | 9.7052 | 9.4105 | 8.4105 | 12.1157 | 14.1257 | 9.7052 | 18.1157 | 30.2314 | 44.3571 | 0.01
3.5875 | 7.7938 | 5.5875 | 4.5875 | 6.3813 | 8.3813 | 7.7938 | 12.3813 | 18.7626 | 27.1439 | 3.5875 | 7.7938 | 5.5875 | 4.5875 | 6.3813 | 8.3913 | 7.7938 | 12.3813 | 18.7626 | 27.1539 | 0.01
5.9969 | 8.9984 | 7.9969 | 6.9969 | 9.9953 | 11.9953 | 8.9984 | 15.9953 | 25.9906 | 37.9859 | 5.9969 | 8.9984 | 7.9969 | 6.9969 | 9.9953 | 12.0053 | 8.9984 | 15.9953 | 25.9906 | 37.9959 | 0.01
4.4596 | 8.2298 | 6.4596 | 5.4596 | 7.6894 | 9.6894 | 8.2298 | 13.6894 | 21.3787 | 31.0681 | 4.4596 | 8.2298 | 6.4596 | 5.4596 | 7.6894 | 9.6994 | 8.2298 | 13.6894 | 21.3787 | 31.0781 | 0.01
4.6953 | 8.3477 | 6.6953 | 5.6953 | 8.043 | 10.043 | 8.3477 | 14.043 | 22.0859 | 32.1289 | 4.6953 | 8.3477 | 6.6953 | 5.6953 | 8.043 | 10.053 | 8.3477 | 14.043 | 22.0859 | 32.1389 | 0.01
6.2341 | 9.117 | 8.2341 | 7.2341 | 10.3511 | 12.3511 | 9.117 | 16.3511 | 26.7023 | 39.0534 | 6.2341 | 9.117 | 8.2341 | 7.2341 | 10.3511 | 12.3611 | 9.117 | 16.3511 | 26.7023 | 39.0634 | 0.01
10.223 | 11.1115 | 12.223 | 11.223 | 16.3345 | 18.3345 | 11.1115 | 22.3345 | 38.669 | 57.0034 | 10.223 | 11.1115 | 12.223 | 11.223 | 16.3345 | 18.3445 | 11.1115 | 22.3345 | 38.669 | 57.0134 | 0.01
7.3917 | 9.6958 | 9.3917 | 8.3917 | 12.0875 | 14.0875 | 9.6958 | 18.0875 | 30.1751 | 44.2626 | 7.3917 | 9.6958 | 9.3917 | 8.3917 | 12.0875 | 14.0975 | 9.6958 | 18.0875 | 30.1751 | 44.2726 | 0.01
7.055 | 9.5275 | 9.055 | 8.055 | 11.5825 | 13.5825 | 9.5275 | 17.5825 | 29.1649 | 42.7474 | 7.055 | 9.5275 | 9.055 | 8.055 | 11.5825 | 13.5925 | 9.5275 | 17.5825 | 29.1649 | 42.7574 | 0.01
2.1916 | 7.0958 | 4.1916 | 3.1916 | 4.2875 | 6.2875 | 7.0958 | 10.2875 | 14.5749 | 20.8624 | 2.1916 | 7.0958 | 4.1916 | 3.1916 | 4.2875 | 6.2975 | 7.0958 | 10.2875 | 14.5749 | 20.8724 | 0.01
4.1961 | 8.098 | 6.1961 | 5.1961 | 7.2941 | 9.2941 | 8.098 | 13.2941 | 20.5882 | 29.8823 | 4.1961 | 8.098 | 6.1961 | 5.1961 | 7.2941 | 9.3041 | 8.098 | 13.2941 | 20.5882 | 29.8923 | 0.01
9.3012 | 10.6506 | 11.3012 | 10.3012 | 14.9518 | 16.9518 | 10.6506 | 20.9518 | 35.9036 | 52.8554 | 9.3012 | 10.6506 | 11.3012 | 10.3012 | 14.9518 | 16.9618 | 10.6506 | 20.9518 | 35.9036 | 52.8654 | 0.01
6.1032 | 9.0516 | 8.1032 | 7.1032 | 10.1549 | 12.1549 | 9.0516 | 16.1549 | 26.3097 | 38.4646 | 6.1032 | 9.0516 | 8.1032 | 7.1032 | 10.1549 | 12.1649 | 9.0516 | 16.1549 | 26.3097 | 38.4746 | 0.01
10.9776 | 11.4888 | 12.9776 | 11.9776 | 17.4663 | 19.4663 | 11.4888 | 23.4663 | 40.9327 | 60.399 | 10.9776 | 11.4888 | 12.9776 | 11.9776 | 17.4663 | 19.4763 | 11.4888 | 23.4663 | 40.9327 | 60.409 | 0.01
3.8066 | 7.9033 | 5.8066 | 4.8066 | 6.7099 | 8.7099 | 7.9033 | 12.7099 | 19.4198 | 28.1297 | 3.8066 | 7.9033 | 5.8066 | 4.8066 | 6.7099 | 8.7199 | 7.9033 | 12.7099 | 19.4198 | 28.1397 | 0.01
4.2458 | 8.1229 | 6.2458 | 5.2458 | 7.3688 | 9.3688 | 8.1229 | 13.3688 | 20.7375 | 30.1063 | 4.2458 | 8.1229 | 6.2458 | 5.2458 | 7.3688 | 9.3788 | 8.1229 | 13.3688 | 20.7375 | 30.1163 | 0.01
6.4005 | 9.2003 | 8.4005 | 7.4005 | 10.6008 | 12.6008 | 9.2003 | 16.6008 | 27.2016 | 39.8024 | 6.4005 | 9.2003 | 8.4005 | 7.4005 | 10.6008 | 12.6108 | 9.2003 | 16.6008 | 27.2016 | 39.8124 | 0.01
4.7583 | 8.3791 | 6.7583 | 5.7583 | 8.1374 | 10.1374 | 8.3791 | 14.1374 | 22.2748 | 32.4122 | 4.7583 | 8.3791 | 6.7583 | 5.7583 | 8.1374 | 10.1474 | 8.3791 | 14.1374 | 22.2748 | 32.4222 | 0.01
6.5861 | 9.293 | 8.5861 | 7.5861 | 10.8791 | 12.8791 | 9.293 | 16.8791 | 27.7582 | 40.6373 | 6.5861 | 9.293 | 8.5861 | 7.5861 | 10.8791 | 12.8891 | 9.293 | 16.8791 | 27.7582 | 40.6473 | 0.01
8.5851 | 10.2925 | 10.5851 | 9.5851 | 13.8776 | 15.8776 | 10.2925 | 19.8776 | 33.7552 | 49.6328 | 8.5851 | 10.2925 | 10.5851 | 9.5851 | 13.8776 | 15.8876 | 10.2925 | 19.8776 | 33.7552 | 49.6428 | 0.01
8.0992 | 10.0496 | 10.0992 | 9.0992 | 13.1489 | 15.1489 | 10.0496 | 19.1489 | 32.2977 | 47.4466 | 8.0992 | 10.0496 | 10.0992 | 9.0992 | 13.1489 | 15.1589 | 10.0496 | 19.1489 | 32.2977 | 47.4566 | 0.01
6.8226 | 9.4113 | 8.8226 | 7.8226 | 11.2338 | 13.2338 | 9.4113 | 17.2338 | 28.4677 | 41.7015 | 6.8226 | 9.4113 | 8.8226 | 7.8226 | 11.2338 | 13.2438 | 9.4113 | 17.2338 | 28.4677 | 41.7115 | 0.01
5.9018 | 8.9509 | 7.9018 | 6.9018 | 9.8527 | 11.8527 | 8.9509 | 15.8527 | 25.7054 | 37.5582 | 5.9018 | 8.9509 | 7.9018 | 6.9018 | 9.8527 | 11.8627 | 8.9509 | 15.8527 | 25.7054 | 37.5682 | 0.01
3.8038 | 7.9019 | 5.8038 | 4.8038 | 6.7057 | 8.7057 | 7.9019 | 12.7057 | 19.4114 | 28.1172 | 3.8038 | 7.9019 | 5.8038 | 4.8038 | 6.7057 | 8.7157 | 7.9019 | 12.7057 | 19.4114 | 28.1272 | 0.01
7.6562 | 9.8281 | 9.6562 | 8.6562 | 12.4843 | 14.4843 | 9.8281 | 18.4843 | 30.9687 | 45.453 | 7.6562 | 9.8281 | 9.6562 | 8.6562 | 12.4843 | 14.4943 | 9.8281 | 18.4843 | 30.9687 | 45.463 | 0.01
5.9438 | 8.9719 | 7.9438 | 6.9438 | 9.9156 | 11.9156 | 8.9719 | 15.9156 | 25.8313 | 37.7469 | 5.9438 | 8.9719 | 7.9438 | 6.9438 | 9.9156 | 11.9256 | 8.9719 | 15.9156 | 25.8313 | 37.7569 | 0.01
4.5206 | 8.2603 | 6.5206 | 5.5206 | 7.7809 | 9.7809 | 8.2603 | 13.7809 | 21.5618 | 31.3428 | 4.5206 | 8.2603 | 6.5206 | 5.5206 | 7.7809 | 9.7909 | 8.2603 | 13.7809 | 21.5618 | 31.3528 | 0.01
6.1925 | 9.0963 | 8.1925 | 7.1925 | 10.2888 | 12.2888 | 9.0963 | 16.2888 | 26.5776 | 38.8664 | 6.1925 | 9.0963 | 8.1925 | 7.1925 | 10.2888 | 12.2988 | 9.0963 | 16.2888 | 26.5776 | 38.8764 | 0.01
6.2748 | 9.1374 | 8.2748 | 7.2748 | 10.4122 | 12.4122 | 9.1374 | 16.4122 | 26.8244 | 39.2366 | 6.2748 | 9.1374 | 8.2748 | 7.2748 | 10.4122 | 12.4222 | 9.1374 | 16.4122 | 26.8244 | 39.2466 | 0.01
6.3519 | 9.176 | 8.3519 | 7.3519 | 10.5279 | 12.5279 | 9.176 | 16.5279 | 27.0558 | 39.5837 | 6.3519 | 9.176 | 8.3519 | 7.3519 | 10.5279 | 12.5379 | 9.176 | 16.5279 | 27.0558 | 39.5937 | 0.01
4.0229 | 8.0115 | 6.0229 | 5.0229 | 7.0344 | 9.0344 | 8.0115 | 13.0344 | 20.0687 | 29.1031 | 4.0229 | 8.0115 | 6.0229 | 5.0229 | 7.0344 | 9.0444 | 8.0115 | 13.0344 | 20.0687 | 29.1131 | 0.01
5.9303 | 8.9651 | 7.9303 | 6.9303 | 9.8954 | 11.8954 | 8.9651 | 15.8954 | 25.7909 | 37.6863 | 5.9303 | 8.9651 | 7.9303 | 6.9303 | 9.8954 | 11.9054 | 8.9651 | 15.8954 | 25.7909 | 37.6963 | 0.01
6.936 | 9.468 | 8.936 | 7.936 | 11.404 | 13.404 | 9.468 | 17.404 | 28.808 | 42.2119 | 6.936 | 9.468 | 8.936 | 7.936 | 11.404 | 13.414 | 9.468 | 17.404 | 28.808 | 42.2219 | 0.01
7.0226 | 9.5113 | 9.0226 | 8.0226 | 11.5339 | 13.5339 | 9.5113 | 17.5339 | 29.0677 | 42.6016 | 7.0226 | 9.5113 | 9.0226 | 8.0226 | 11.5339 | 13.5439 | 9.5113 | 17.5339 | 29.0677 | 42.6116 | 0.01
2.7903 | 7.3951 | 4.7903 | 3.7903 | 5.1854 | 7.1854 | 7.3951 | 11.1854 | 16.3708 | 23.5562 | 2.7903 | 7.3951 | 4.7903 | 3.7903 | 5.1854 | 7.1954 | 7.3951 | 11.1854 | 16.3708 | 23.5662 | 0.01
6.8957 | 9.4479 | 8.8957 | 7.8957 | 11.3436 | 13.3436 | 9.4479 | 17.3436 | 28.6871 | 42.0307 | 6.8957 | 9.4479 | 8.8957 | 7.8957 | 11.3436 | 13.3536 | 9.4479 | 17.3436 | 28.6871 | 42.0407 | 0.01
6.0138 | 9.0069 | 8.0138 | 7.0138 | 10.0208 | 12.0208 | 9.0069 | 16.0208 | 26.0415 | 38.0623 | 6.0138 | 9.0069 | 8.0138 | 7.0138 | 10.0208 | 12.0308 | 9.0069 | 16.0208 | 26.0415 | 38.0723 | 0.01
3.8657 | 7.9328 | 5.8657 | 4.8657 | 6.7985 | 8.7985 | 7.9328 | 12.7985 | 19.597 | 28.3955 | 3.8657 | 7.9328 | 5.8657 | 4.8657 | 6.7985 | 8.8085 | 7.9328 | 12.7985 | 19.597 | 28.4055 | 0.01
7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2333 | 9.7444 | 18.2333 | 30.4666 | 44.6998 | 7.4889 | 9.7444 | 9.4889 | 8.4889 | 12.2333 | 14.2433 | 9.7444 | 18.2333 | 30.4666 | 44.7098 | 0.01
8.8202 | 10.4101 | 10.8202 | 9.8202 | 14.2303 | 16.2303 | 10.4101 | 20.2303 | 34.4605 | 50.6908 | 8.8202 | 10.4101 | 10.8202 | 9.8202 | 14.2303 | 16.2403 | 10.4101 | 20.2303 | 34.4605 | 50.7008 | 0.01
7.8196 | 9.9098 | 9.8196 | 8.8196 | 12.7294 | 14.7294 | 9.9098 | 18.7294 | 31.4588 | 46.1882 | 7.8196 | 9.9098 | 9.8196 | 8.8196 | 12.7294 | 14.7394 | 9.9098 | 18.7294 | 31.4588 | 46.1982 | 0.01
4.576 | 8.288 | 6.576 | 5.576 | 7.864 | 9.864 | 8.288 | 13.864 | 21.7279 | 31.5919 | 4.576 | 8.288 | 6.576 | 5.576 | 7.864 | 9.874 | 8.288 | 13.864 | 21.7279 | 31.6019 | 0.01
7.0266 | 9.5133 | 9.0266 | 8.0266 | 11.5399 | 13.5399 | 9.5133 | 17.5399 | 29.0798 | 42.6196 | 7.0266 | 9.5133 | 9.0266 | 8.0266 | 11.5399 | 13.5499 | 9.5133 | 17.5399 | 29.0798 | 42.6296 | 0.01
6.0145 | 9.0072 | 8.0145 | 7.0145 | 10.0217 | 12.0217 | 9.0072 | 16.0217 | 26.0434 | 38.0651 | 6.0145 | 9.0072 | 8.0145 | 7.0145 | 10.0217 | 12.0317 | 9.0072 | 16.0217 | 26.0434 | 38.0751 | 0.01
2.6438 | 7.3219 | 4.6438 | 3.6438 | 4.9657 | 6.9657 | 7.3219 | 10.9657 | 15.9313 | 22.897 | 2.6438 | 7.3219 | 4.6438 | 3.6438 | 4.9657 | 6.9757 | 7.3219 | 10.9657 | 15.9313 | 22.907 | 0.01
6.0348 | 9.0174 | 8.0348 | 7.0348 | 10.0522 | 12.0522 | 9.0174 | 16.0522 | 26.1044 | 38.1566 | 6.0348 | 9.0174 | 8.0348 | 7.0348 | 10.0522 | 12.0622 | 9.0174 | 16.0522 | 26.1044 | 38.1666 | 0.01
5.4907 | 8.7453 | 7.4907 | 6.4907 | 9.236 | 11.236 | 8.7453 | 15.236 | 24.472 | 35.7079 | 5.4907 | 8.7453 | 7.4907 | 6.4907 | 9.236 | 11.246 | 8.7453 | 15.236 | 24.472 | 35.7179 | 0.01
7.3925 | 9.6962 | 9.3925 | 8.3925 | 12.0887 | 14.0887 | 9.6962 | 18.0887 | 30.1774 | 44.2661 | 7.3925 | 9.6962 | 9.3925 | 8.3925 | 12.0887 | 14.0987 | 9.6962 | 18.0887 | 30.1774 | 44.2761 | 0.01
6.0746 | 9.0373 | 8.0746 | 7.0746 | 10.1119 | 12.1119 | 9.0373 | 16.1119 | 26.2238 | 38.3357 | 6.0746 | 9.0373 | 8.0746 | 7.0746 | 10.1119 | 12.1219 | 9.0373 | 16.1119 | 26.2238 | 38.3457 | 0.01
5.7247 | 8.8624 | 7.7247 | 6.7247 | 9.5871 | 11.5871 | 8.8624 | 15.5871 | 25.1742 | 36.7613 | 5.7247 | 8.8624 | 7.7247 | 6.7247 | 9.5871 | 11.5971 | 8.8624 | 15.5871 | 25.1742 | 36.7713 | 0.01
5.7801 | 8.89 | 7.7801 | 6.7801 | 9.6701 | 11.6701 | 8.89 | 15.6701 | 25.3403 | 37.0104 | 5.7801 | 8.89 | 7.7801 | 6.7801 | 9.6701 | 11.6801 | 8.89 | 15.6701 | 25.3403 | 37.0204 | 0.01
4.7764 | 8.3882 | 6.7764 | 5.7764 | 8.1646 | 10.1646 | 8.3882 | 14.1646 | 22.3292 | 32.4937 | 4.7764 | 8.3882 | 6.7764 | 5.7764 | 8.1646 | 10.1746 | 8.3882 | 14.1646 | 22.3292 | 32.5037 | 0.01
2.1447 | 7.0723 | 4.1447 | 3.1447 | 4.217 | 6.217 | 7.0723 | 10.217 | 14.434 | 20.6509 | 2.1447 | 7.0723 | 4.1447 | 3.1447 | 4.217 | 6.227 | 7.0723 | 10.217 | 14.434 | 20.6609 | 0.01
5.7028 | 8.8514 | 7.7028 | 6.7028 | 9.5542 | 11.5542 | 8.8514 | 15.5542 | 25.1084 | 36.6625 | 5.7028 | 8.8514 | 7.7028 | 6.7028 | 9.5542 | 11.5642 | 8.8514 | 15.5542 | 25.1084 | 36.6725 | 0.01
7.7214 | 9.8607 | 9.7214 | 8.7214 | 12.582 | 14.582 | 9.8607 | 18.582 | 31.1641 | 45.7461 | 7.7214 | 9.8607 | 9.7214 | 8.7214 | 12.582 | 14.592 | 9.8607 | 18.582 | 31.1641 | 45.7561 | 0.01
5.5976 | 8.7988 | 7.5976 | 6.5976 | 9.3964 | 11.3964 | 8.7988 | 15.3964 | 24.7928 | 36.1892 | 5.5976 | 8.7988 | 7.5976 | 6.5976 | 9.3964 | 11.4064 | 8.7988 | 15.3964 | 24.7928 | 36.1992 | 0.01
5.3389 | 8.6695 | 7.3389 | 6.3389 | 9.0084 | 11.0084 | 8.6695 | 15.0084 | 24.0167 | 35.0251 | 5.3389 | 8.6695 | 7.3389 | 6.3389 | 9.0084 | 11.0184 | 8.6695 | 15.0084 | 24.0167 | 35.0351 | 0.01
8.3081 | 10.154 | 10.3081 | 9.3081 | 13.4621 | 15.4621 | 10.154 | 19.4621 | 32.9243 | 48.3864 | 8.3081 | 10.154 | 10.3081 | 9.3081 | 13.4621 | 15.4721 | 10.154 | 19.4621 | 32.9243 | 48.3964 | 0.01
6.3383 | 9.1691 | 8.3383 | 7.3383 | 10.5074 | 12.5074 | 9.1691 | 16.5074 | 27.0148 | 39.5222 | 6.3383 | 9.1691 | 8.3383 | 7.3383 | 10.5074 | 12.5174 | 9.1691 | 16.5074 | 27.0148 | 39.5322 | 0.01
6.2356 | 9.1178 | 8.2356 | 7.2356 | 10.3534 | 12.3534 | 9.1178 | 16.3534 | 26.7069 | 39.0603 | 6.2356 | 9.1178 | 8.2356 | 7.2356 | 10.3534 | 12.3634 | 9.1178 | 16.3534 | 26.7069 | 39.0703 | 0.01
8.8103 | 10.4051 | 10.8103 | 9.8103 | 14.2154 | 16.2154 | 10.4051 | 20.2154 | 34.4309 | 50.6463 | 8.8103 | 10.4051 | 10.8103 | 9.8103 | 14.2154 | 16.2254 | 10.4051 | 20.2154 | 34.4309 | 50.6563 | 0.01
9.1328 | 10.5664 | 11.1328 | 10.1328 | 14.6992 | 16.6992 | 10.5664 | 20.6992 | 35.3985 | 52.0977 | 9.1328 | 10.5664 | 11.1328 | 10.1328 | 14.6992 | 16.7092 | 10.5664 | 20.6992 | 35.3985 | 52.1077 | 0.01
7.1789 | 9.5895 | 9.1789 | 8.1789 | 11.7684 | 13.7684 | 9.5895 | 17.7684 | 29.5367 | 43.3051 | 7.1789 | 9.5895 | 9.1789 | 8.1789 | 11.7684 | 13.7784 | 9.5895 | 17.7684 | 29.5367 | 43.3151 | 0.01
6.2187 | 9.1093 | 8.2187 | 7.2187 | 10.328 | 12.328 | 9.1093 | 16.328 | 26.6561 | 38.9841 | 6.2187 | 9.1093 | 8.2187 | 7.2187 | 10.328 | 12.338 | 9.1093 | 16.328 | 26.6561 | 38.9941 | 0.01
10.8017 | 11.4008 | 12.8017 | 11.8017 | 17.2025 | 19.2025 | 11.4008 | 23.2025 | 40.405 | 59.6075 | 10.8017 | 11.4008 | 12.8017 | 11.8017 | 17.2025 | 19.2125 | 11.4008 | 23.2025 | 40.405 | 59.6175 | 0.01
4.3082 | 8.1541 | 6.3082 | 5.3082 | 7.4622 | 9.4622 | 8.1541 | 13.4622 | 20.9245 | 30.3867 | 4.3082 | 8.1541 | 6.3082 | 5.3082 | 7.4622 | 9.4722 | 8.1541 | 13.4622 | 20.9245 | 30.3967 | 0.01
6.2847 | 9.1423 | 8.2847 | 7.2847 | 10.427 | 12.427 | 9.1423 | 16.427 | 26.8541 | 39.2811 | 6.2847 | 9.1423 | 8.2847 | 7.2847 | 10.427 | 12.437 | 9.1423 | 16.427 | 26.8541 | 39.2911 | 0.01
3.8754 | 7.9377 | 5.8754 | 4.8754 | 6.8131 | 8.8131 | 7.9377 | 12.8131 | 19.6261 | 28.4392 | 3.8754 | 7.9377 | 5.8754 | 4.8754 | 6.8131 | 8.8231 | 7.9377 | 12.8131 | 19.6261 | 28.4492 | 0.01
3.5216 | 7.7608 | 5.5216 | 4.5216 | 6.2824 | 8.2824 | 7.7608 | 12.2824 | 18.5649 | 26.8473 | 3.5216 | 7.7608 | 5.5216 | 4.5216 | 6.2824 | 8.2924 | 7.7608 | 12.2824 | 18.5649 | 26.8573 | 0.01
5.5633 | 8.7817 | 7.5633 | 6.5633 | 9.345 | 11.345 | 8.7817 | 15.345 | 24.69 | 36.0351 | 5.5633 | 8.7817 | 7.5633 | 6.5633 | 9.345 | 11.355 | 8.7817 | 15.345 | 24.69 | 36.0451 | 0.01
4.8463 | 8.4232 | 6.8463 | 5.8463 | 8.2695 | 10.2695 | 8.4232 | 14.2695 | 22.5389 | 32.8084 | 4.8463 | 8.4232 | 6.8463 | 5.8463 | 8.2695 | 10.2795 | 8.4232 | 14.2695 | 22.5389 | 32.8184 | 0.01
6.9828 | 9.4914 | 8.9828 | 7.9828 | 11.4743 | 13.4743 | 9.4914 | 17.4743 | 28.9485 | 42.4228 | 6.9828 | 9.4914 | 8.9828 | 7.9828 | 11.4743 | 13.4843 | 9.4914 | 17.4743 | 28.9485 | 42.4328 | 0.01
7.8476 | 9.9238 | 9.8476 | 8.8476 | 12.7713 | 14.7713 | 9.9238 | 18.7713 | 31.5427 | 46.314 | 7.8476 | 9.9238 | 9.8476 | 8.8476 | 12.7713 | 14.7813 | 9.9238 | 18.7713 | 31.5427 | 46.324 | 0.01
7.0345 | 9.5172 | 9.0345 | 8.0345 | 11.5517 | 13.5517 | 9.5172 | 17.5517 | 29.1034 | 42.655 | 7.0345 | 9.5172 | 9.0345 | 8.0345 | 11.5517 | 13.5617 | 9.5172 | 17.5517 | 29.1034 | 42.665 | 0.01
7.2596 | 9.6298 | 9.2596 | 8.2596 | 11.8894 | 13.8894 | 9.6298 | 17.8894 | 29.7788 | 43.6682 | 7.2596 | 9.6298 | 9.2596 | 8.2596 | 11.8894 | 13.8994 | 9.6298 | 17.8894 | 29.7788 | 43.6782 | 0.01
6.762 | 9.381 | 8.762 | 7.762 | 11.143 | 13.143 | 9.381 | 17.143 | 28.286 | 41.4289 | 6.762 | 9.381 | 8.762 | 7.762 | 11.143 | 13.153 | 9.381 | 17.143 | 28.286 | 41.4389 | 0.01
4.7843 | 8.3922 | 6.7843 | 5.7843 | 8.1765 | 10.1765 | 8.3922 | 14.1765 | 22.3529 | 32.5294 | 4.7843 | 8.3922 | 6.7843 | 5.7843 | 8.1765 | 10.1865 | 8.3922 | 14.1765 | 22.3529 | 32.5394 | 0.01
5.9404 | 8.9702 | 7.9404 | 6.9404 | 9.9106 | 11.9106 | 8.9702 | 15.9106 | 25.8212 | 37.7318 | 5.9404 | 8.9702 | 7.9404 | 6.9404 | 9.9106 | 11.9206 | 8.9702 | 15.9106 | 25.8212 | 37.7418 | 0.01
6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.4972 | 9.1657 | 16.4972 | 26.9943 | 39.4915 | 6.3314 | 9.1657 | 8.3314 | 7.3314 | 10.4972 | 12.5072 | 9.1657 | 16.4972 | 26.9943 | 39.5015 | 0.01
7.0135 | 9.5068 | 9.0135 | 8.0135 | 11.5203 | 13.5203 | 9.5068 | 17.5203 | 29.0406 | 42.5608 | 7.0135 | 9.5068 | 9.0135 | 8.0135 | 11.5203 | 13.5303 | 9.5068 | 17.5203 | 29.0406 | 42.5708 | 0.01
3.4265 | 7.7133 | 5.4265 | 4.4265 | 6.1398 | 8.1398 | 7.7133 | 12.1398 | 18.2796 | 26.4194 | 3.4265 | 7.7133 | 5.4265 | 4.4265 | 6.1398 | 8.1498 | 7.7133 | 12.1398 | 18.2796 | 26.4294 | 0.01
5.4813 | 8.7407 | 7.4813 | 6.4813 | 9.222 | 11.222 | 8.7407 | 15.222 | 24.444 | 35.6659 | 5.4813 | 8.7407 | 7.4813 | 6.4813 | 9.222 | 11.232 | 8.7407 | 15.222 | 24.444 | 35.6759 | 0.01
7.7681 | 9.8841 | 9.7681 | 8.7681 | 12.6522 | 14.6522 | 9.8841 | 18.6522 | 31.3044 | 45.9566 | 7.7681 | 9.8841 | 9.7681 | 8.7681 | 12.6522 | 14.6622 | 9.8841 | 18.6522 | 31.3044 | 45.9666 | 0.01
6.4122 | 9.2061 | 8.4122 | 7.4122 | 10.6184 | 12.6184 | 9.2061 | 16.6184 | 27.2367 | 39.8551 | 6.4122 | 9.2061 | 8.4122 | 7.4122 | 10.6184 | 12.6284 | 9.2061 | 16.6184 | 27.2367 | 39.8651 | 0.01
8.7219 | 10.361 | 10.7219 | 9.7219 | 14.0829 | 16.0829 | 10.361 | 20.0829 | 34.1657 | 50.2486 | 8.7219 | 10.361 | 10.7219 | 9.7219 | 14.0829 | 16.0929 | 10.361 | 20.0829 | 34.1657 | 50.2586 | 0.01
5.8098 | 8.9049 | 7.8098 | 6.8098 | 9.7147 | 11.7147 | 8.9049 | 15.7147 | 25.4293 | 37.144 | 5.8098 | 8.9049 | 7.8098 | 6.8098 | 9.7147 | 11.7247 | 8.9049 | 15.7147 | 25.4293 | 37.154 | 0.01
4.8329 | 8.4165 | 6.8329 | 5.8329 | 8.2494 | 10.2494 | 8.4165 | 14.2494 | 22.4987 | 32.7481 | 4.8329 | 8.4165 | 6.8329 | 5.8329 | 8.2494 | 10.2594 | 8.4165 | 14.2494 | 22.4987 | 32.7581 | 0.01
6.7605 | 9.3803 | 8.7605 | 7.7605 | 11.1408 | 13.1408 | 9.3803 | 17.1408 | 28.2815 | 41.4223 | 6.7605 | 9.3803 | 8.7605 | 7.7605 | 11.1408 | 13.1508 | 9.3803 | 17.1408 | 28.2815 | 41.4323 | 0.01
9.047 | 10.5235 | 11.047 | 10.047 | 14.5706 | 16.5706 | 10.5235 | 20.5706 | 35.1411 | 51.7117 | 9.047 | 10.5235 | 11.047 | 10.047 | 14.5706 | 16.5806 | 10.5235 | 20.5706 | 35.1411 | 51.7217 | 0.01
7.8454 | 9.9227 | 9.8454 | 8.8454 | 12.7682 | 14.7682 | 9.9227 | 18.7682 | 31.5363 | 46.3045 | 7.8454 | 9.9227 | 9.8454 | 8.8454 | 12.7682 | 14.7782 | 9.9227 | 18.7682 | 31.5363 | 46.3145 | 0.01
6.6496 | 9.3248 | 8.6496 | 7.6496 | 10.9744 | 12.9744 | 9.3248 | 16.9744 | 27.9489 | 40.9233 | 6.6496 | 9.3248 | 8.6496 | 7.6496 | 10.9744 | 12.9844 | 9.3248 | 16.9744 | 27.9489 | 40.9333 | 0.01
4.2135 | 8.1067 | 6.2135 | 5.2135 | 7.3202 | 9.3202 | 8.1067 | 13.3202 | 20.6404 | 29.9606 | 4.2135 | 8.1067 | 6.2135 | 5.2135 | 7.3202 | 9.3302 | 8.1067 | 13.3202 | 20.6404 | 29.9706 | 0.01
11.6293 | 11.8146 | 13.6293 | 12.6293 | 18.4439 | 20.4439 | 11.8146 | 24.4439 | 42.8878 | 63.3317 | 11.6293 | 11.8146 | 13.6293 | 12.6293 | 18.4439 | 20.4539 | 11.8146 | 24.4439 | 42.8878 | 63.3417 | 0.01
5.3138 | 8.6569 | 7.3138 | 6.3138 | 8.9707 | 10.9707 | 8.6569 | 14.9707 | 23.9414 | 34.9122 | 5.3138 | 8.6569 | 7.3138 | 6.3138 | 8.9707 | 10.9807 | 8.6569 | 14.9707 | 23.9414 | 34.9222 | 0.01
6.2814 | 9.1407 | 8.2814 | 7.2814 | 10.4222 | 12.4222 | 9.1407 | 16.4222 | 26.8443 | 39.2665 | 6.2814 | 9.1407 | 8.2814 | 7.2814 | 10.4222 | 12.4322 | 9.1407 | 16.4222 | 26.8443 | 39.2765 | 0.01
5.935 | 8.9675 | 7.935 | 6.935 | 9.9026 | 11.9026 | 8.9675 | 15.9026 | 25.8051 | 37.7077 | 5.935 | 8.9675 | 7.935 | 6.935 | 9.9026 | 11.9126 | 8.9675 | 15.9026 | 25.8051 | 37.7177 | 0.01
6.1508 | 9.0754 | 8.1508 | 7.1508 | 10.2262 | 12.2262 | 9.0754 | 16.2262 | 26.4523 | 38.6785 | 6.1508 | 9.0754 | 8.1508 | 7.1508 | 10.2262 | 12.2362 | 9.0754 | 16.2262 | 26.4523 | 38.6885 | 0.01
5.3276 | 8.6638 | 7.3276 | 6.3276 | 8.9914 | 10.9914 | 8.6638 | 14.9914 | 23.9828 | 34.9742 | 5.3276 | 8.6638 | 7.3276 | 6.3276 | 8.9914 | 11.0014 | 8.6638 | 14.9914 | 23.9828 | 34.9842 | 0.01
2.0185 | 7.0093 | 4.0185 | 3.0185 | 4.0278 | 6.0278 | 7.0093 | 10.0278 | 14.0556 | 20.0834 | 2.0185 | 7.0093 | 4.0185 | 3.0185 | 4.0278 | 6.0378 | 7.0093 | 10.0278 | 14.0556 | 20.0934 | 0.01
7.9373 | 9.9687 | 9.9373 | 8.9373 | 12.906 | 14.906 | 9.9687 | 18.906 | 31.812 | 46.718 | 7.9373 | 9.9687 | 9.9373 | 8.9373 | 12.906 | 14.916 | 9.9687 | 18.906 | 31.812 | 46.728 | 0.01
7.1858 | 9.5929 | 9.1858 | 8.1858 | 11.7787 | 13.7787 | 9.5929 | 17.7787 | 29.5575 | 43.3362 | 7.1858 | 9.5929 | 9.1858 | 8.1858 | 11.7787 | 13.7887 | 9.5929 | 17.7787 | 29.5575 | 43.3462 | 0.01
6.7905 | 9.3953 | 8.7905 | 7.7905 | 11.1858 | 13.1858 | 9.3953 | 17.1858 | 28.3716 | 41.5574 | 6.7905 | 9.3953 | 8.7905 | 7.7905 | 11.1858 | 13.1958 | 9.3953 | 17.1858 | 28.3716 | 41.5674 | 0.01
8.3321 | 10.166 | 10.3321 | 9.3321 | 13.4981 | 15.4981 | 10.166 | 19.4981 | 32.9962 | 48.4944 | 8.3321 | 10.166 | 10.3321 | 9.3321 | 13.4981 | 15.5081 | 10.166 | 19.4981 | 32.9962 | 48.5044 | 0.01
4.4306 | 8.2153 | 6.4306 | 5.4306 | 7.6459 | 9.6459 | 8.2153 | 13.6459 | 21.2918 | 30.9377 | 4.4306 | 8.2153 | 6.4306 | 5.4306 | 7.6459 | 9.6559 | 8.2153 | 13.6459 | 21.2918 | 30.9477 | 0.01
5.963 | 8.9815 | 7.963 | 6.963 | 9.9446 | 11.9446 | 8.9815 | 15.9446 | 25.8891 | 37.8337 | 5.963 | 8.9815 | 7.963 | 6.963 | 9.9446 | 11.9546 | 8.9815 | 15.9446 | 25.8891 | 37.8437 | 0.01
5.0349 | 8.5174 | 7.0349 | 6.0349 | 8.5523 | 10.5523 | 8.5174 | 14.5523 | 23.1047 | 33.657 | 5.0349 | 8.5174 | 7.0349 | 6.0349 | 8.5523 | 10.5623 | 8.5174 | 14.5523 | 23.1047 | 33.667 | 0.01
7.8813 | 9.9407 | 9.8813 | 8.8813 | 12.822 | 14.822 | 9.9407 | 18.822 | 31.644 | 46.466 | 7.8813 | 9.9407 | 9.8813 | 8.8813 | 12.822 | 14.832 | 9.9407 | 18.822 | 31.644 | 46.476 | 0.01
2.9422 | 7.4711 | 4.9422 | 3.9422 | 5.4133 | 7.4133 | 7.4711 | 11.4133 | 16.8265 | 24.2398 | 2.9422 | 7.4711 | 4.9422 | 3.9422 | 5.4133 | 7.4233 | 7.4711 | 11.4133 | 16.8265 | 24.2498 | 0.01
5.5831 | 8.7915 | 7.5831 | 6.5831 | 9.3746 | 11.3746 | 8.7915 | 15.3746 | 24.7492 | 36.1238 | 5.5831 | 8.7915 | 7.5831 | 6.5831 | 9.3746 | 11.3846 | 8.7915 | 15.3746 | 24.7492 | 36.1338 | 0.01
6.1071 | 9.0535 | 8.1071 | 7.1071 | 10.1606 | 12.1606 | 9.0535 | 16.1606 | 26.3212 | 38.4818 | 6.1071 | 9.0535 | 8.1071 | 7.1071 | 10.1606 | 12.1706 | 9.0535 | 16.1606 | 26.3212 | 38.4918 | 0.01
3.7728 | 7.8864 | 5.7728 | 4.7728 | 6.6592 | 8.6592 | 7.8864 | 12.6592 | 19.3184 | 27.9776 | 3.7728 | 7.8864 | 5.7728 | 4.7728 | 6.6592 | 8.6692 | 7.8864 | 12.6592 | 19.3184 | 27.9876 | 0.01
7.4075 | 9.7038 | 9.4075 | 8.4075 | 12.1113 | 14.1113 | 9.7038 | 18.1113 | 30.2226 | 44.3338 | 7.4075 | 9.7038 | 9.4075 | 8.4075 | 12.1113 | 14.1213 | 9.7038 | 18.1113 | 30.2226 | 44.3438 | 0.01
4.9966 | 8.4983 | 6.9966 | 5.9966 | 8.4948 | 10.4948 | 8.4983 | 14.4948 | 22.9897 | 33.4845 | 4.9966 | 8.4983 | 6.9966 | 5.9966 | 8.4948 | 10.5048 | 8.4983 | 14.4948 | 22.9897 | 33.4945 | 0.01
5.7338 | 8.8669 | 7.7338 | 6.7338 | 9.6008 | 11.6008 | 8.8669 | 15.6008 | 25.2015 | 36.8023 | 5.7338 | 8.8669 | 7.7338 | 6.7338 | 9.6008 | 11.6108 | 8.8669 | 15.6008 | 25.2015 | 36.8123 | 0.01
9.5995 | 10.7997 | 11.5995 | 10.5995 | 15.3992 | 17.3992 | 10.7997 | 21.3992 | 36.7984 | 54.1977 | 9.5995 | 10.7997 | 11.5995 | 10.5995 | 15.3992 | 17.4092 | 10.7997 | 21.3992 | 36.7984 | 54.2077 | 0.01
4.5772 | 8.2886 | 6.5772 | 5.5772 | 7.8657 | 9.8657 | 8.2886 | 13.8657 | 21.7315 | 31.5972 | 4.5772 | 8.2886 | 6.5772 | 5.5772 | 7.8657 | 9.8757 | 8.2886 | 13.8657 | 21.7315 | 31.6072 | 0.01
6.272 | 9.136 | 8.272 | 7.272 | 10.408 | 12.408 | 9.136 | 16.408 | 26.8161 | 39.2241 | 6.272 | 9.136 | 8.272 | 7.272 | 10.408 | 12.418 | 9.136 | 16.408 | 26.8161 | 39.2341 | 0.01
8.0427 | 10.0214 | 10.0427 | 9.0427 | 13.0641 | 15.0641 | 10.0214 | 19.0641 | 32.1282 | 47.1924 | 8.0427 | 10.0214 | 10.0427 | 9.0427 | 13.0641 | 15.0741 | 10.0214 | 19.0641 | 32.1282 | 47.2024 | 0.01
7.5719 | 9.7859 | 9.5719 | 8.5719 | 12.3578 | 14.3578 | 9.7859 | 18.3578 | 30.7157 | 45.0735 | 7.5719 | 9.7859 | 9.5719 | 8.5719 | 12.3578 | 14.3678 | 9.7859 | 18.3578 | 30.7157 | 45.0835 | 0.01
5.6432 | 8.8216 | 7.6432 | 6.6432 | 9.4649 | 11.4649 | 8.8216 | 15.4649 | 24.9297 | 36.3946 | 5.6432 | 8.8216 | 7.6432 | 6.6432 | 9.4649 | 11.4749 | 8.8216 | 15.4649 | 24.9297 | 36.4046 | 0.01
8.7355 | 10.3677 | 10.7355 | 9.7355 | 14.1032 | 16.1032 | 10.3677 | 20.1032 | 34.2065 | 50.3097 | 8.7355 | 10.3677 | 10.7355 | 9.7355 | 14.1032 | 16.1132 | 10.3677 | 20.1032 | 34.2065 | 50.3197 | 0.01
5.0301 | 8.515 | 7.0301 | 6.0301 | 8.5451 | 10.5451 | 8.515 | 14.5451 | 23.0902 | 33.6354 | 5.0301 | 8.515 | 7.0301 | 6.0301 | 8.5451 | 10.5551 | 8.515 | 14.5451 | 23.0902 | 33.6454 | 0.01
7.0523 | 9.5262 | 9.0523 | 8.0523 | 11.5785 | 13.5785 | 9.5262 | 17.5785 | 29.157 | 42.7355 | 7.0523 | 9.5262 | 9.0523 | 8.0523 | 11.5785 | 13.5885 | 9.5262 | 17.5785 | 29.157 | 42.7455 | 0.01
7.9439 | 9.972 | 9.9439 | 8.9439 | 12.9159 | 14.9159 | 9.972 | 18.9159 | 31.8318 | 46.7478 | 7.9439 | 9.972 | 9.9439 | 8.9439 | 12.9159 | 14.9259 | 9.972 | 18.9159 | 31.8318 | 46.7578 | 0.01
8.5616 | 10.2808 | 10.5616 | 9.5616 | 13.8424 | 15.8424 | 10.2808 | 19.8424 | 33.6848 | 49.5272 | 8.5616 | 10.2808 | 10.5616 | 9.5616 | 13.8424 | 15.8524 | 10.2808 | 19.8424 | 33.6848 | 49.5372 | 0.01
7.3831 | 9.6916 | 9.3831 | 8.3831 | 12.0747 | 14.0747 | 9.6916 | 18.0747 | 30.1494 | 44.2241 | 7.3831 | 9.6916 | 9.3831 | 8.3831 | 12.0747 | 14.0847 | 9.6916 | 18.0747 | 30.1494 | 44.2341 | 0.01
4.1357 | 8.0679 | 6.1357 | 5.1357 | 7.2036 | 9.2036 | 8.0679 | 13.2036 | 20.4072 | 29.6108 | 4.1357 | 8.0679 | 6.1357 | 5.1357 | 7.2036 | 9.2136 | 8.0679 | 13.2036 | 20.4072 | 29.6208 | 0.01
2.1727 | 7.0864 | 4.1727 | 3.1727 | 4.2591 | 6.2591 | 7.0864 | 10.2591 | 14.5182 | 20.7772 | 2.1727 | 7.0864 | 4.1727 | 3.1727 | 4.2591 | 6.2691 | 7.0864 | 10.2591 | 14.5182 | 20.7872 | 0.01
5.5513 | 8.7756 | 7.5513 | 6.5513 | 9.3269 | 11.3269 | 8.7756 | 15.3269 | 24.6538 | 35.9807 | 5.5513 | 8.7756 | 7.5513 | 6.5513 | 9.3269 | 11.3369 | 8.7756 | 15.3269 | 24.6538 | 35.9907 | 0.01
3.49 | 7.745 | 5.49 | 4.49 | 6.235 | 8.235 | 7.745 | 12.235 | 18.47 | 26.705 | 3.49 | 7.745 | 5.49 | 4.49 | 6.235 | 8.245 | 7.745 | 12.235 | 18.47 | 26.715 | 0.01
0.33785 | 6.1689 | 2.3378 | 1.3378 | 1.5068 | 3.5068 | 6.1689 | 7.5068 | 9.0135 | 12.5203 | 0.33785 | 6.1689 | 2.3378 | 1.3378 | 1.5068 | 3.5168 | 6.1689 | 7.5068 | 9.0135 | 12.5303 | 0.01
5.2149 | 8.6075 | 7.2149 | 6.2149 | 8.8224 | 10.8224 | 8.6075 | 14.8224 | 23.6448 | 34.4672 | 5.2149 | 8.6075 | 7.2149 | 6.2149 | 8.8224 | 10.8324 | 8.6075 | 14.8224 | 23.6448 | 34.4772 | 0.01
7.5632 | 9.7816 | 9.5632 | 8.5632 | 12.3447 | 14.3447 | 9.7816 | 18.3447 | 30.6895 | 45.0342 | 7.5632 | 9.7816 | 9.5632 | 8.5632 | 12.3447 | 14.3547 | 9.7816 | 18.3447 | 30.6895 | 45.0442 | 0.01
7.7902 | 9.8951 | 9.7902 | 8.7902 | 12.6853 | 14.6853 | 9.8951 | 18.6853 | 31.3705 | 46.0558 | 7.7902 | 9.8951 | 9.7902 | 8.7902 | 12.6853 | 14.6953 | 9.8951 | 18.6853 | 31.3705 | 46.0658 | 0.01
9.4106 | 10.7053 | 11.4106 | 10.4106 | 15.1159 | 17.1159 | 10.7053 | 21.1159 | 36.2318 | 53.3477 | 9.4106 | 10.7053 | 11.4106 | 10.4106 | 15.1159 | 17.1259 | 10.7053 | 21.1159 | 36.2318 | 53.3577 | 0.01
6.338 | 9.169 | 8.338 | 7.338 | 10.5069 | 12.5069 | 9.169 | 16.5069 | 27.0139 | 39.5208 | 6.338 | 9.169 | 8.338 | 7.338 | 10.5069 | 12.5169 | 9.169 | 16.5069 | 27.0139 | 39.5308 | 0.01
8.4698 | 10.2349 | 10.4698 | 9.4698 | 13.7047 | 15.7047 | 10.2349 | 19.7047 | 33.4094 | 49.1142 | 8.4698 | 10.2349 | 10.4698 | 9.4698 | 13.7047 | 15.7147 | 10.2349 | 19.7047 | 33.4094 | 49.1242 | 0.01
3.966 | 7.983 | 5.966 | 4.966 | 6.949 | 8.949 | 7.983 | 12.949 | 19.898 | 28.847 | 3.966 | 7.983 | 5.966 | 4.966 | 6.949 | 8.959 | 7.983 | 12.949 | 19.898 | 28.857 | 0.01
2.0788 | 7.0394 | 4.0788 | 3.0788 | 4.1183 | 6.1183 | 7.0394 | 10.1183 | 14.2365 | 20.3548 | 2.0788 | 7.0394 | 4.0788 | 3.0788 | 4.1183 | 6.1283 | 7.0394 | 10.1183 | 14.2365 | 20.3648 | 0.01
7.9038 | 9.9519 | 9.9038 | 8.9038 | 12.8558 | 14.8558 | 9.9519 | 18.8558 | 31.7115 | 46.5673 | 7.9038 | 9.9519 | 9.9038 | 8.9038 | 12.8558 | 14.8658 | 9.9519 | 18.8558 | 31.7115 | 46.5773 | 0.01
5.9358 | 8.9679 | 7.9358 | 6.9358 | 9.9037 | 11.9037 | 8.9679 | 15.9037 | 25.8074 | 37.7111 | 5.9358 | 8.9679 | 7.9358 | 6.9358 | 9.9037 | 11.9137 | 8.9679 | 15.9037 | 25.8074 | 37.7211 | 0.01
8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0715 | 10.0238 | 19.0715 | 32.143 | 47.2144 | 8.0477 | 10.0238 | 10.0477 | 9.0477 | 13.0715 | 15.0815 | 10.0238 | 19.0715 | 32.143 | 47.2244 | 0.01
6.657 | 9.3285 | 8.657 | 7.657 | 10.9856 | 12.9856 | 9.3285 | 16.9856 | 27.9711 | 40.9567 | 6.657 | 9.3285 | 8.657 | 7.657 | 10.9856 | 12.9956 | 9.3285 | 16.9856 | 27.9711 | 40.9667 | 0.01
6.5966 | 9.2983 | 8.5966 | 7.5966 | 10.8949 | 12.8949 | 9.2983 | 16.8949 | 27.7899 | 40.6848 | 6.5966 | 9.2983 | 8.5966 | 7.5966 | 10.8949 | 12.9049 | 9.2983 | 16.8949 | 27.7899 | 40.6948 | 0.01
5.4851 | 8.7426 | 7.4851 | 6.4851 | 9.2277 | 11.2277 | 8.7426 | 15.2277 | 24.4554 | 35.683 | 5.4851 | 8.7426 | 7.4851 | 6.4851 | 9.2277 | 11.2377 | 8.7426 | 15.2277 | 24.4554 | 35.693 | 0.01
3.0805 | 7.5402 | 5.0805 | 4.0805 | 5.6207 | 7.6207 | 7.5402 | 11.6207 | 17.2414 | 24.8621 | 3.0805 | 7.5402 | 5.0805 | 4.0805 | 5.6207 | 7.6307 | 7.5402 | 11.6207 | 17.2414 | 24.8721 | 0.01
7.2083 | 9.6042 | 9.2083 | 8.2083 | 11.8125 | 13.8125 | 9.6042 | 17.8125 | 29.625 | 43.4375 | 7.2083 | 9.6042 | 9.2083 | 8.2083 | 11.8125 | 13.8225 | 9.6042 | 17.8125 | 29.625 | 43.4475 | 0.01
2.7006 | 7.3503 | 4.7006 | 3.7006 | 5.0509 | 7.0509 | 7.3503 | 11.0509 | 16.1017 | 23.1526 | 2.7006 | 7.3503 | 4.7006 | 3.7006 | 5.0509 | 7.0609 | 7.3503 | 11.0509 | 16.1017 | 23.1626 | 0.01
7.4982 | 9.7491 | 9.4982 | 8.4982 | 12.2472 | 14.2472 | 9.7491 | 18.2472 | 30.4945 | 44.7417 | 7.4982 | 9.7491 | 9.4982 | 8.4982 | 12.2472 | 14.2572 | 9.7491 | 18.2472 | 30.4945 | 44.7517 | 0.01
5.3544 | 8.6772 | 7.3544 | 6.3544 | 9.0316 | 11.0316 | 8.6772 | 15.0316 | 24.0632 | 35.0948 | 5.3544 | 8.6772 | 7.3544 | 6.3544 | 9.0316 | 11.0416 | 8.6772 | 15.0316 | 24.0632 | 35.1048 | 0.01
4.5186 | 8.2593 | 6.5186 | 5.5186 | 7.7779 | 9.7779 | 8.2593 | 13.7779 | 21.5558 | 31.3337 | 4.5186 | 8.2593 | 6.5186 | 5.5186 | 7.7779 | 9.7879 | 8.2593 | 13.7779 | 21.5558 | 31.3437 | 0.01
4.8309 | 8.4155 | 6.8309 | 5.8309 | 8.2464 | 10.2464 | 8.4155 | 14.2464 | 22.4927 | 32.7391 | 4.8309 | 8.4155 | 6.8309 | 5.8309 | 8.2464 | 10.2564 | 8.4155 | 14.2464 | 22.4927 | 32.7491 | 0.01
1.1151 | 6.5575 | 3.1151 | 2.1151 | 2.6726 | 4.6726 | 6.5575 | 8.6726 | 11.3452 | 16.0178 | 1.1151 | 6.5575 | 3.1151 | 2.1151 | 2.6726 | 4.6826 | 6.5575 | 8.6726 | 11.3452 | 16.0278 | 0.01
5.9719 | 8.986 | 7.9719 | 6.9719 | 9.9579 | 11.9579 | 8.986 | 15.9579 | 25.9158 | 37.8737 | 5.9719 | 8.986 | 7.9719 | 6.9719 | 9.9579 | 11.9679 | 8.986 | 15.9579 | 25.9158 | 37.8837 | 0.01
6.5507 | 9.2754 | 8.5507 | 7.5507 | 10.8261 | 12.8261 | 9.2754 | 16.8261 | 27.6521 | 40.4782 | 6.5507 | 9.2754 | 8.5507 | 7.5507 | 10.8261 | 12.8361 | 9.2754 | 16.8261 | 27.6521 | 40.4882 | 0.01
4.8226 | 8.4113 | 6.8226 | 5.8226 | 8.2338 | 10.2338 | 8.4113 | 14.2338 | 22.4677 | 32.7015 | 4.8226 | 8.4113 | 6.8226 | 5.8226 | 8.2338 | 10.2438 | 8.4113 | 14.2338 | 22.4677 | 32.7115 | 0.01
6.1037 | 9.0519 | 8.1037 | 7.1037 | 10.1556 | 12.1556 | 9.0519 | 16.1556 | 26.3111 | 38.4667 | 6.1037 | 9.0519 | 8.1037 | 7.1037 | 10.1556 | 12.1656 | 9.0519 | 16.1556 | 26.3111 | 38.4767 | 0.01
6.9292 | 9.4646 | 8.9292 | 7.9292 | 11.3937 | 13.3937 | 9.4646 | 17.3937 | 28.7875 | 42.1812 | 6.9292 | 9.4646 | 8.9292 | 7.9292 | 11.3937 | 13.4037 | 9.4646 | 17.3937 | 28.7875 | 42.1912 | 0.01
3.7038 | 7.8519 | 5.7038 | 4.7038 | 6.5557 | 8.5557 | 7.8519 | 12.5557 | 19.1113 | 27.667 | 3.7038 | 7.8519 | 5.7038 | 4.7038 | 6.5557 | 8.5657 | 7.8519 | 12.5557 | 19.1113 | 27.677 | 0.01
7.5671 | 9.7836 | 9.5671 | 8.5671 | 12.3507 | 14.3507 | 9.7836 | 18.3507 | 30.7013 | 45.052 | 7.5671 | 9.7836 | 9.5671 | 8.5671 | 12.3507 | 14.3607 | 9.7836 | 18.3507 | 30.7013 | 45.062 | 0.01
2.3254 | 7.1627 | 4.3254 | 3.3254 | 4.4881 | 6.4881 | 7.1627 | 10.4881 | 14.9762 | 21.4642 | 2.3254 | 7.1627 | 4.3254 | 3.3254 | 4.4881 | 6.4981 | 7.1627 | 10.4881 | 14.9762 | 21.4742 | 0.01
5.8236 | 8.9118 | 7.8236 | 6.8236 | 9.7354 | 11.7354 | 8.9118 | 15.7354 | 25.4708 | 37.2062 | 5.8236 | 8.9118 | 7.8236 | 6.8236 | 9.7354 | 11.7454 | 8.9118 | 15.7354 | 25.4708 | 37.2162 | 0.01
6.3687 | 9.1844 | 8.3687 | 7.3687 | 10.5531 | 12.5531 | 9.1844 | 16.5531 | 27.1062 | 39.6593 | 6.3687 | 9.1844 | 8.3687 | 7.3687 | 10.5531 | 12.5631 | 9.1844 | 16.5531 | 27.1062 | 39.6693 | 0.01
7.032 | 9.516 | 9.032 | 8.032 | 11.548 | 13.548 | 9.516 | 17.548 | 29.096 | 42.644 | 7.032 | 9.516 | 9.032 | 8.032 | 11.548 | 13.558 | 9.516 | 17.548 | 29.096 | 42.654 | 0.01
5.9999 | 9 | 7.9999 | 6.9999 | 9.9999 | 11.9999 | 9 | 15.9999 | 25.9998 | 37.9997 | 5.9999 | 9 | 7.9999 | 6.9999 | 9.9999 | 12.0099 | 9 | 15.9999 | 25.9998 | 38.0097 | 0.01
6.0206 | 9.0103 | 8.0206 | 7.0206 | 10.0309 | 12.0309 | 9.0103 | 16.0309 | 26.0617 | 38.0926 | 6.0206 | 9.0103 | 8.0206 | 7.0206 | 10.0309 | 12.0409 | 9.0103 | 16.0309 | 26.0617 | 38.1026 | 0.01
9.147 | 10.5735 | 11.147 | 10.147 | 14.7205 | 16.7205 | 10.5735 | 20.7205 | 35.441 | 52.1614 | 9.147 | 10.5735 | 11.147 | 10.147 | 14.7205 | 16.7305 | 10.5735 | 20.7205 | 35.441 | 52.1714 | 0.01
7.1056 | 9.5528 | 9.1056 | 8.1056 | 11.6584 | 13.6584 | 9.5528 | 17.6584 | 29.3168 | 42.9752 | 7.1056 | 9.5528 | 9.1056 | 8.1056 | 11.6584 | 13.6684 | 9.5528 | 17.6584 | 29.3168 | 42.9852 | 0.01
[8 empty] | Average | 37.4427 | [8 empty] | Average |  | 100%