## Project Management
Activity | Mean | Standard Deviation | Variance
A | 6 | 2
B | 9 | 1 | 1
C | 8 | 2
D | 7 | 2 | 4
E | 10 | 3 | 9
F | 12 | 3 | 9
Prove that Activities B, D, E and F are critical; but A and C not critical!
| Variance of the Project= |  | 23
| STD of the project (stdp) = |  | 4.7958
| Project Expected Time = |  | 38
check three different ways
P(T<40days) = P( (T-meanp)/std < (40-38)/4.80 ) = P(Z <.42)
40 |  |  |  | 0.41703 | 66.17% | 66.17% | 66.17%
P(T>45 days)=1-P(T<=45days)
| = | 1-P(Z<=(45-38)/4.80 ) = 1- P(Z<=1.46)
45 |  |  |  | 1.4596 | 7.22% | 7.22% | 7.22%
Reference: Wayne W.L., 2001, Simulation Modeling, pg 111-119
Note on F18: Ozdogru, Unsal: Z value
Note on F22: Ozdogru, Unsal: Z value
by the property of Normal distribution

## critical path
A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4
-7.7551 | 10.6172 | 9.951 | 11.4327 | 11.4836 | 11.4968 | 10.6172 | 22.0499 | 33.5335 | 45.0303
7.4367 | 9.1492 | 8.1533 | 9.6422 | 14.8066 | 8.745 | 9.1492 | 18.7914 | 33.598 | 42.343
6.8651 | 7.7647 | 11.4096 | 10.5908 | 6.3737 | 12.5465 | 7.7647 | 18.3555 | 24.7292 | 37.2757
11.0288 | 7.8306 | 8.3418 | 11.2048 | 10.3992 | 10.4727 | 11.0288 | 22.2336 | 32.6328 | 43.1055
3.1602 | 9.7531 | 9.356 | 7.1589 | 5.8983 | 17.1026 | 9.7531 | 16.912 | 22.8103 | 39.9129
11.4248 | 9.0225 | 4.4877 | 8.8016 | 11.0903 | 10.7888 | 11.4248 | 20.2264 | 31.3167 | 42.1055
-1.5576 | 8.8854 | 7.367 | 3.9729 | 11.2123 | 9.7199 | 8.8854 | 12.8583 | 24.0706 | 33.7905
-7.7023 | 9.3515 | 6.9936 | 7.8158 | 17.5153 | 11.1727 | 9.3515 | 17.1673 | 34.6826 | 45.8553
4.4741 | 8.6752 | 9.0763 | 7.7107 | 6.6338 | 13.2586 | 8.6752 | 16.3859 | 23.0197 | 36.2783
10.5441 | 8.6537 | 10.3992 | 3.5911 | 8.2745 | 8.8554 | 10.5441 | 14.1353 | 22.4097 | 31.2652
-3.9182 | 7.3989 | 9.1769 | 3.4307 | 9.2799 | 10.1396 | 7.3989 | 10.8296 | 20.1095 | 30.2491
-0.98948 | 10.5609 | 8.5522 | 7.0728 | 9.2645 | 10.6446 | 10.5609 | 17.6337 | 26.8981 | 37.5427
12.885 | 9.593 | 7.4143 | 7.0937 | 14.0836 | 8.1594 | 12.885 | 19.9788 | 34.0623 | 42.2217
4.9281 | 8.5642 | 8.1642 | 7.7995 | 9.0851 | 13.1297 | 8.5642 | 16.3637 | 25.4487 | 38.5784
-0.84741 | 8.2044 | 7.2375 | 5.3049 | 13.0524 | 15.3449 | 8.2044 | 13.5092 | 26.5617 | 41.9066
-10.0415 | 10.2783 | 10.8756 | 6.9861 | 14.6188 | 9.7177 | 10.2783 | 17.2644 | 31.8832 | 41.601
-4.9238 | 9.8972 | 7.5314 | 8.7201 | 13.2095 | 13.533 | 9.8972 | 18.6173 | 31.8269 | 45.3598
-0.041984 | 7.9722 | 9.2455 | 7.2884 | 11.0179 | 10.291 | 7.9722 | 15.2606 | 26.2785 | 36.5694
8.7577 | 10.1366 | 5.8852 | 3.5285 | 10.6993 | 14.079 | 10.1366 | 13.665 | 24.3644 | 38.4433
5.6091 | 7.3573 | 9.8547 | 5.1702 | 9.7925 | 11.6195 | 7.3573 | 12.5275 | 22.32 | 33.9395
-3.9008 | 8.004 | 6.8482 | 6.1112 | 6.2971 | 10.7133 | 8.004 | 14.1152 | 20.4123 | 31.1256
-0.72996 | 9.4083 | 6.1784 | 4.3465 | 8.6411 | 12.2235 | 9.4083 | 13.7548 | 22.3959 | 34.6194
7.6841 | 7.832 | 8.1915 | 5.2397 | 6.6767 | 12.6943 | 7.832 | 13.0717 | 19.7485 | 32.4428
5.7811 | 8.9705 | 7.6556 | 4.6549 | 13.2615 | 12.8435 | 8.9705 | 13.6254 | 26.8869 | 39.7304
-5.7588 | 9.9283 | 9.0112 | 2.4531 | 10.5313 | 8.1427 | 9.9283 | 12.3814 | 22.9127 | 31.0554
6.8917 | 9.3308 | 8.707 | 5.7676 | 11.9391 | 10.4419 | 9.3308 | 15.0984 | 27.0375 | 37.4794
-0.48741 | 10.6471 | 5.7716 | 3.4442 | 10.585 | 12.0816 | 10.6471 | 14.0914 | 24.6763 | 36.7579
0.87552 | 9.2638 | 8.2461 | 8.7599 | 11.6839 | 14.2868 | 9.2638 | 18.0237 | 29.7076 | 43.9944
-2.8158 | 11.1924 | 8.4708 | 13.0938 | 8.7867 | 16.0224 | 11.1924 | 24.2862 | 33.0729 | 49.0953
7.4043 | 9.7713 | 8.3368 | 7.3393 | 15.4377 | 11.8642 | 9.7713 | 17.1106 | 32.5483 | 44.4124
5.0162 | 6.9768 | 6.1202 | 6.933 | 10.7846 | 4.3207 | 6.9768 | 13.9098 | 24.6945 | 29.0152
-0.2309 | 9.9054 | 7.2445 | 9.5354 | 9.1073 | 6.2056 | 9.9054 | 19.4408 | 28.5481 | 34.7537
5.7831 | 9.907 | 8.8985 | 3.0197 | 9.1803 | 17.1948 | 9.907 | 12.9267 | 22.1071 | 39.3018
12.4673 | 9.3865 | 7.0642 | 6.492 | 6.1196 | 12.7007 | 12.4673 | 18.9594 | 25.079 | 37.7796
6.8883 | 9.4987 | 4.7384 | 7.9926 | 13.0417 | 10.792 | 9.4987 | 17.4913 | 30.533 | 41.3251
2.8132 | 9.0969 | 11.3215 | 7.4152 | 11.2881 | 16.4266 | 9.0969 | 16.5122 | 27.8002 | 44.2269
1.1283 | 8.9683 | 9.9785 | 7.4813 | 8.5081 | 16.6191 | 8.9683 | 16.4496 | 24.9577 | 41.5768
7.7959 | 9.4408 | 8.2851 | 8.189 | 11.0351 | 7.4033 | 9.4408 | 17.6297 | 28.6648 | 36.0681
7.5077 | 10.6633 | 11.2462 | 7.7463 | 13.0236 | 10.5756 | 10.6633 | 18.4096 | 31.4332 | 42.0088
-3.9596 | 8.0538 | 6.5376 | 6.815 | 8.6503 | 13.7345 | 8.0538 | 14.8689 | 23.5192 | 37.2537
13.3018 | 8.7446 | 9.2964 | 5.3957 | 11.8794 | 11.8634 | 13.3018 | 18.6974 | 30.5769 | 42.4402
-9.5268 | 9.0063 | 8.0017 | 4.8714 | 12.0338 | 9.5648 | 9.0063 | 13.8777 | 25.9115 | 35.4763
6.9514 | 9.3514 | 7.1901 | 6.7595 | 11.5085 | 13.6852 | 9.3514 | 16.111 | 27.6195 | 41.3047
17.2594 | 8.4916 | 8.3801 | 6.0115 | 7.4865 | 15.0339 | 17.2594 | 23.271 | 30.7575 | 45.7913
5.132 | 9.9254 | 3.2408 | 8.5529 | 7.8208 | 8.9379 | 9.9254 | 18.4783 | 26.2991 | 35.237
9.2923 | 6.4792 | 8.7745 | 7.2143 | 9.2865 | 9.1846 | 9.2923 | 16.5066 | 25.7931 | 34.9777
5.866 | 8.7253 | 8.0823 | 7.6472 | 12.4083 | 11.9919 | 8.7253 | 16.3726 | 28.7808 | 40.7728
2.9614 | 10.0054 | 6.4161 | 3.8604 | 12.0977 | 11.8664 | 10.0054 | 13.8658 | 25.9635 | 37.8299
-1.2875 | 8.781 | 12.9762 | 7.8395 | 8.9902 | 18.1549 | 8.781 | 16.6205 | 25.6107 | 43.7656
2.1338 | 10.6134 | 5.1675 | 6.66 | 9.6236 | 8.5911 | 10.6134 | 17.2734 | 26.897 | 35.4881
-9.7037 | 9.4429 | 10.1096 | 5.7841 | 9.6556 | 15.215 | 9.4429 | 15.227 | 24.8827 | 40.0976
1.1107 | 10.2077 | 6.3874 | 4.1365 | 9.7014 | 11.6865 | 10.2077 | 14.3442 | 24.0456 | 35.7321
-1.3727 | 10.8056 | 5.7818 | 5.0618 | 6.7809 | 8.4325 | 10.8056 | 15.8674 | 22.6483 | 31.0808
9.8007 | 8.9808 | 11.9067 | 4.9246 | 8.996 | 12.1478 | 9.8007 | 14.7253 | 23.7213 | 35.8692
0.54161 | 9.2874 | 6.779 | 4.7108 | 11.9675 | 14.6726 | 9.2874 | 13.9982 | 25.9657 | 40.6383
4.4236 | 7.848 | 8.981 | 9.0156 | 3.0602 | 11.8871 | 7.848 | 16.8637 | 19.9238 | 31.8109
-9.9669 | 8.4938 | 5.3968 | 5.1713 | 3.3619 | 8.6675 | 8.4938 | 13.665 | 17.0269 | 25.6944
0.39351 | 10.029 | 7.0946 | 7.83 | 7.4489 | 13.5258 | 10.029 | 17.859 | 25.3079 | 38.8337
1.4697 | 10.2713 | 9.1875 | 4.3002 | 9.1669 | 8.7637 | 10.2713 | 14.5714 | 23.7383 | 32.502
4.9902 | 9.6154 | 8.2714 | 8.5255 | 6.9464 | 14.5058 | 9.6154 | 18.141 | 25.0873 | 39.5931
6.2075 | 9.3605 | 8.5697 | 6.3427 | 9.8586 | 12.4063 | 9.3605 | 15.7032 | 25.5617 | 37.968
9.7598 | 8.5078 | 9.9764 | 8.8916 | 10.057 | 15.0524 | 9.7598 | 18.6513 | 28.7083 | 43.7607
4.8689 | 9.3381 | 6.2664 | 11.5762 | 12.5801 | 15.321 | 9.3381 | 20.9144 | 33.4945 | 48.8155
0.36889 | 8.4642 | 6.7422 | 3.1447 | 10.0744 | 11.6116 | 8.4642 | 11.6089 | 21.6833 | 33.2949
11.1425 | 9.7194 | 11.3153 | 10.0331 | 12.4273 | 14.9788 | 11.1425 | 21.1756 | 33.6029 | 48.5817
11.4664 | 8.5147 | 8.5514 | 8.561 | 9.6705 | 13.278 | 11.4664 | 20.0274 | 29.6979 | 42.9758
5.7516 | 7.8035 | 10.9594 | 8.0447 | 9.6225 | 13.6005 | 7.8035 | 15.8482 | 25.4707 | 39.0712
-6.9054 | 8.9378 | 7.1458 | 9.7039 | 16.9868 | 16.3327 | 8.9378 | 18.6417 | 35.6285 | 51.9612
2.6798 | 9.9038 | 8.3391 | 7.9098 | 5.7392 | 13.0197 | 9.9038 | 17.8136 | 23.5528 | 36.5725
3.158 | 8.6627 | 10.7137 | 7.5648 | 16.365 | 11.425 | 8.6627 | 16.2275 | 32.5925 | 44.0175
3.8851 | 7.9431 | 10.1956 | 4.778 | 9.3363 | 9.0501 | 7.9431 | 12.7211 | 22.0574 | 31.1075
11.525 | 9.1026 | 10.3916 | 5.1847 | 5.1607 | 4.7629 | 11.525 | 16.7097 | 21.9167 | 26.6795
1.4733 | 7.4822 | 7.1195 | 6.0029 | 13.2963 | 9.2742 | 7.4822 | 13.4852 | 26.7815 | 36.0557
4.168 | 9.4725 | 6.8274 | 5.792 | 9.2746 | 9.1378 | 9.4725 | 15.2645 | 24.5391 | 33.6769
2.9539 | 9.2805 | 7.3035 | 3.8993 | 12.7031 | 12.705 | 9.2805 | 13.1798 | 25.8828 | 38.5879
-7.0796 | 9.3911 | 11.6656 | 6.0217 | 5.91 | 15.7881 | 9.3911 | 15.4128 | 21.3228 | 37.1109
-2.094 | 9.3496 | 7.2544 | 9.1273 | 14.7966 | 18.1332 | 9.3496 | 18.4769 | 33.2735 | 51.4067
11.0881 | 10.5845 | 8.5727 | 3.909 | 13.331 | 9.1773 | 11.0881 | 14.9971 | 28.3281 | 37.5054
6.4017 | 9.4727 | 8.5515 | 4.8003 | 10.0783 | 17.3491 | 9.4727 | 14.273 | 24.3513 | 41.7005
4.7683 | 10.0145 | 5.4466 | 8.0195 | 10.4783 | 10.0801 | 10.0145 | 18.034 | 28.5123 | 38.5924
6.3333 | 7.4033 | 12.7768 | 9.3672 | 4.4206 | 10.7406 | 7.4033 | 16.7705 | 21.1911 | 31.9317
15.0521 | 8.2255 | 9.7261 | 10.9774 | 11.573 | 9.7078 | 15.0521 | 26.0295 | 37.6025 | 47.3103
-2.6112 | 8.0037 | 8.0773 | 5.8805 | 9.7311 | 8.0818 | 8.0037 | 13.8842 | 23.6154 | 31.6972
7.3361 | 9.8275 | 7.8859 | 6.8749 | 8.7742 | 12.223 | 9.8275 | 16.7024 | 25.4765 | 37.6996
3.6751 | 9.0643 | 5.3536 | 6.7491 | 6.4153 | 11.9307 | 9.0643 | 15.8133 | 22.2286 | 34.1593
0.80419 | 7.059 | 6.0263 | 6.7334 | 11.3673 | 12.8382 | 7.059 | 13.7924 | 25.1597 | 37.9979
13.9973 | 7.826 | 7.5535 | 6.8621 | 12.93 | 13.9702 | 13.9973 | 20.8594 | 33.7894 | 47.7596
-2.5283 | 7.9519 | 10.4693 | 7.7742 | 10.1962 | 16.0707 | 7.9519 | 15.726 | 25.9222 | 41.993
-6.3369 | 8.8209 | 8.9808 | 7.1559 | 11.9008 | 19.8377 | 8.8209 | 15.9768 | 27.8776 | 47.7154
11.9535 | 8.2946 | 8.052 | 7.5413 | 14.0477 | 11.859 | 11.9535 | 19.4948 | 33.5425 | 45.4014
5.8166 | 8.7857 | 8.8865 | 5.8551 | 9.0711 | 10.9806 | 8.7857 | 14.6408 | 23.712 | 34.6926
2.7486 | 9.3492 | 10.6504 | 3.138 | 7.1442 | 9.8101 | 9.3492 | 12.4872 | 19.9996 | 29.8097
10.3216 | 10.4736 | 7.9684 | 6.7943 | 11.6662 | 6.8006 | 10.4736 | 17.2679 | 28.9341 | 35.7347
2.5823 | 9.0124 | 7.8851 | 5.6414 | 10.7886 | 7.7657 | 9.0124 | 14.6538 | 25.4425 | 33.2081
-3.4357 | 9.2902 | 8.8867 | 5.4319 | 16.183 | 13.5058 | 9.2902 | 14.7222 | 30.9051 | 44.4109
15.5802 | 8.8448 | 9.2833 | 9.6421 | 11.6158 | 14.4833 | 15.5802 | 25.2223 | 36.8381 | 51.3214
3.0918 | 9.8773 | 3.54 | 9.1011 | 10.6765 | 7.1635 | 9.8773 | 18.9784 | 29.6549 | 36.8184
11.1037 | 6.7729 | 7.3241 | 9.0945 | 11.4351 | 12.5295 | 11.1037 | 20.1983 | 31.6334 | 44.1629
-0.83974 | 11.6811 | 10.0684 | 5.2068 | 11.9171 | 15.5247 | 11.6811 | 16.888 | 28.8051 | 44.3298
4.7459 | 8.5794 | 6.0023 | 8.713 | 11.8144 | 15.9991 | 8.5794 | 17.2924 | 29.1069 | 45.106
-3.3289 | 9.2639 | 5.7095 | 5.2189 | 10.1673 | 9.2936 | 9.2639 | 14.4828 | 24.65 | 33.9437
6.0204 | 8.7048 | 8.4384 | 9.8827 | 7.0854 | 5.4672 | 8.7048 | 18.5875 | 25.6728 | 31.1401
3.6555 | 8.5261 | 8.5056 | 8.6286 | 13.2759 | 11.0128 | 8.5261 | 17.1547 | 30.4307 | 41.4434
-0.093682 | 7.8766 | 9.6921 | 7.4249 | 8.9105 | 9.9653 | 7.8766 | 15.3016 | 24.212 | 34.1773
0.93895 | 9.2474 | 7.7912 | 6.9277 | 13.1253 | 14.6946 | 9.2474 | 16.1751 | 29.3003 | 43.9949
10.6048 | 8.9763 | 10.8877 | 3.9409 | 11.8613 | 11.1048 | 10.6048 | 14.5457 | 26.407 | 37.5118
3.3089 | 9.8081 | 9.1389 | 9.822 | 8.2647 | 8.5158 | 9.8081 | 19.6301 | 27.8948 | 36.4106
4.7409 | 9.1722 | 4.9758 | 5.0988 | 15.8188 | 15.2905 | 9.1722 | 14.271 | 30.0899 | 45.3803
-3.3347 | 8.5143 | 9.3513 | 6.7302 | 9.5456 | 9.5048 | 8.5143 | 15.2444 | 24.79 | 34.2948
0.28161 | 8.2269 | 7.0931 | 7.7716 | 11.4784 | 8.3402 | 8.2269 | 15.9984 | 27.4768 | 35.817
-4.9328 | 10.2253 | 5.2379 | 6.5345 | 11.7969 | 13.3181 | 10.2253 | 16.7598 | 28.5568 | 41.8749
-1.9918 | 8.7506 | 8.5794 | 10.4537 | 13.6376 | 10.839 | 8.7506 | 19.2043 | 32.8419 | 43.6809
13.7191 | 9.727 | 5.7391 | 6.7605 | 10.8361 | 6.8985 | 13.7191 | 20.4796 | 31.3156 | 38.2141
-5.0786 | 9.307 | 7.8802 | 7.2565 | 7.3325 | 9.5643 | 9.307 | 16.5635 | 23.8959 | 33.4602
7.6798 | 11.0206 | 11.2556 | 10.2923 | 6.8016 | 17.0642 | 11.0206 | 21.3128 | 28.1144 | 45.1786
4.9302 | 10.3406 | 9.1241 | 9.3648 | 9.7013 | 16.6284 | 10.3406 | 19.7055 | 29.4067 | 46.0351
0.36434 | 10.9811 | 8.3154 | 3.6051 | 14.2752 | 11.0414 | 10.9811 | 14.5862 | 28.8614 | 39.9028
-9.2182 | 8.0255 | 7.5194 | 4.0594 | 11.3779 | 15.6153 | 8.0255 | 12.0849 | 23.4628 | 39.0781
-9.272 | 9.1672 | 9.6205 | 10.551 | 6.303 | 13.0174 | 9.1672 | 19.7182 | 26.0212 | 39.0386
4.3481 | 8.8628 | 3.9999 | 9.345 | 9.9328 | 12.1503 | 8.8628 | 18.2078 | 28.1407 | 40.291
-8.1137 | 9.5424 | 6.992 | 8.5223 | 8.9708 | 10.6103 | 9.5424 | 18.0647 | 27.0355 | 37.6459
-9.0961 | 8.798 | 3.2406 | 6.0566 | 10.776 | 9.4947 | 8.798 | 14.8546 | 25.6306 | 35.1253
-2.1816 | 10.684 | 8.549 | 5.8478 | 12.2749 | 8.011 | 10.684 | 16.5318 | 28.8067 | 36.8177
6.3063 | 8.692 | 5.2215 | 4.6185 | 15.2081 | 8.9357 | 8.692 | 13.3105 | 28.5186 | 37.4543
5.537 | 9.2748 | 7.8839 | 6.063 | 7.708 | 10.6706 | 9.2748 | 15.3378 | 23.0458 | 33.7164
4.5947 | 8.7395 | 7.47 | 6.4781 | 9.6176 | 13.124 | 8.7395 | 15.2176 | 24.8352 | 37.9592
-4.1091 | 8.15 | 7.2689 | 6.93 | 7.7143 | 19.0045 | 8.15 | 15.0801 | 22.7944 | 41.7988
-2.7655 | 8.5191 | 11.0318 | 3.0172 | 14.6342 | 13.4611 | 8.5191 | 11.5362 | 26.1704 | 39.6316
4.7116 | 7.4348 | 7.1443 | 5.4282 | 8.3847 | 12.1861 | 7.4348 | 12.863 | 21.2477 | 33.4338
4.0396 | 9.5176 | 9.6024 | 8.7593 | 9.0299 | 8.0206 | 9.5176 | 18.277 | 27.3069 | 35.3275
4.3895 | 8.182 | 6.843 | 8.3091 | 10.1354 | 22.4198 | 8.182 | 16.491 | 26.6265 | 49.0462
7.435 | 8.8918 | 7.8801 | 2.401 | 5.0023 | 13.358 | 8.8918 | 11.2928 | 16.7719 | 30.1299
2.6337 | 8.0535 | 9.8331 | 6.9129 | 9.8448 | 8.7881 | 8.0535 | 14.9665 | 24.8113 | 33.5994
0.45225 | 7.3535 | 12.7213 | 8.3793 | 13.3085 | 10.9421 | 7.3535 | 15.7328 | 29.0413 | 39.9834
8.9771 | 9.1163 | 9.0769 | 7.9504 | 7.9339 | 10.3419 | 9.1163 | 17.0668 | 25.0006 | 35.3426
-8.339 | 9.5283 | 8.9688 | 9.0696 | 7.6209 | 7.4259 | 9.5283 | 18.5979 | 26.2187 | 33.6446
-5.6469 | 9.2578 | 9.5184 | 6.932 | 11.0434 | 6.928 | 9.2578 | 16.1898 | 27.2332 | 34.1612
4.5314 | 8.4529 | 8.3668 | 7.2184 | 7.7616 | 15.8276 | 8.4529 | 15.6713 | 23.4329 | 39.2606
3.3113 | 8.6858 | 7.7839 | 6.0665 | 9.645 | 12.1188 | 8.6858 | 14.7523 | 24.3974 | 36.5162
-2.0068 | 8.298 | 7.0791 | 10.0843 | 15.5981 | 16.5348 | 8.298 | 18.3823 | 33.9803 | 50.5151
3.3169 | 7.4565 | 10.2245 | 3.6764 | 11.2168 | 9.6004 | 7.4565 | 11.1329 | 22.3497 | 31.9501
-0.024904 | 8.1684 | 7.4745 | 6.4295 | 8.995 | 10.3428 | 8.1684 | 14.598 | 23.593 | 33.9358
9.6071 | 9.8622 | 10.5907 | 7.8532 | 11.1036 | 13.3452 | 9.8622 | 17.7154 | 28.8189 | 42.1641
2.355 | 9.1102 | 8.3718 | 6.1214 | 9.6371 | 9.6132 | 9.1102 | 15.2317 | 24.8687 | 34.4819
12.0396 | 8.2679 | 10.4605 | 3.9117 | 8.8069 | 7.487 | 12.0396 | 15.9513 | 24.7582 | 32.2452
6.2452 | 10.3125 | 10.8542 | 9.2984 | 10.9956 | 11.3299 | 10.3125 | 19.6109 | 30.6065 | 41.9364
6.8785 | 9.7603 | 8.5632 | 4.9982 | 9.6912 | 8.5321 | 9.7603 | 14.7585 | 24.4497 | 32.9818
5.8738 | 7.5864 | 10.5432 | 9.318 | 9.845 | 12.3092 | 7.5864 | 16.9044 | 26.7494 | 39.0586
4.9732 | 8.7351 | 8.9752 | 9.4654 | 6.6153 | 11.6315 | 8.7351 | 18.2005 | 24.8157 | 36.4473
13.5194 | 9.6949 | 8.8503 | 7.6786 | 8.6583 | 7.2246 | 13.5194 | 21.198 | 29.8563 | 37.0808
9.3649 | 9.1845 | 8.8158 | 7.4661 | 12.1524 | 10.984 | 9.3649 | 16.831 | 28.9833 | 39.9674
-2.3549 | 9.4459 | 8.4458 | 4.1602 | 8.8348 | 11.5774 | 9.4459 | 13.6061 | 22.4409 | 34.0182
0.27666 | 8.1343 | 9.2352 | 9.0032 | 8.2931 | 5.2124 | 8.1343 | 17.1375 | 25.4306 | 30.643
7.5486 | 8.2073 | 9.4095 | 10.2769 | 12.2838 | 15.3477 | 8.2073 | 18.4842 | 30.768 | 46.1157
-15.1261 | 7.6006 | 5.7554 | 7.1791 | 12.8592 | 12.705 | 7.6006 | 14.7797 | 27.6389 | 40.3439
-2.2184 | 9.8908 | 7.7443 | 5.3497 | 6.8486 | 14.4275 | 9.8908 | 15.2405 | 22.0891 | 36.5165
2.9794 | 6.9087 | 8.2588 | 6.6429 | 9.669 | 14.5187 | 6.9087 | 13.5516 | 23.2206 | 37.7393
-3.9199 | 9.6613 | 9.199 | 8.0741 | 7.668 | 15.1848 | 9.6613 | 17.7354 | 25.4033 | 40.5881
-4.3993 | 8.7865 | 10.3984 | 7.1979 | 15.1874 | 10.0794 | 8.7865 | 15.9845 | 31.1719 | 41.2513
9.2657 | 7.6021 | 7.487 | 9.6646 | 14.4155 | 7.1071 | 9.2657 | 18.9303 | 33.3458 | 40.4529
2.5885 | 9.4994 | 6.4886 | 5.2622 | 10.4084 | 13.5333 | 9.4994 | 14.7615 | 25.17 | 38.7033
-5.1379 | 9.5355 | 3.704 | 6.5284 | 10.3731 | 15.7928 | 9.5355 | 16.0639 | 26.437 | 42.2299
12.9614 | 8.4548 | 8.0871 | 4.5498 | 8.7466 | 14.2324 | 12.9614 | 17.5112 | 26.2578 | 40.4902
12.3123 | 7.6568 | 7.0683 | 5.8302 | 9.7843 | 10.9761 | 12.3123 | 18.1424 | 27.9268 | 38.9029
-5.8513 | 10.4613 | 7.1838 | 5.5352 | 14.1151 | 14.9184 | 10.4613 | 15.9965 | 30.1116 | 45.03
1.3684 | 8.9852 | 6.2122 | 7.0442 | 5.8895 | 10.9321 | 8.9852 | 16.0294 | 21.9189 | 32.851
17.9931 | 7.8972 | 10.5727 | 8.9182 | 14.4841 | 8.4521 | 17.9931 | 26.9112 | 41.3954 | 49.8475
0.4603 | 9.8008 | 7.135 | 7.7334 | 10.9306 | 10.2096 | 9.8008 | 17.5342 | 28.4648 | 38.6744
3.2579 | 8.9405 | 7.7296 | 5.0049 | 9.8681 | 11.0294 | 8.9405 | 13.9454 | 23.8135 | 34.8428
11.5443 | 10.23 | 8.361 | 6.6698 | 11.891 | 10.918 | 11.5443 | 18.2141 | 30.1051 | 41.0231
2.7064 | 8.107 | 6.3704 | 7.4591 | 16.2185 | 13.0929 | 8.107 | 15.5661 | 31.7847 | 44.8776
-4.7558 | 10.7744 | 4.2271 | 5.7506 | 6.0961 | 10.1264 | 10.7744 | 16.525 | 22.6211 | 32.7474
1.0427 | 8.5964 | 9.5066 | 10.6925 | 7.4542 | 16.1334 | 8.5964 | 19.2889 | 26.743 | 42.8764
-2.0843 | 7.676 | 8.6627 | 10.4965 | 10.6184 | 21.2389 | 7.676 | 18.1724 | 28.7908 | 50.0297
2.5518 | 9.8213 | 5.5738 | 4.9608 | 12.6806 | 12.6367 | 9.8213 | 14.7822 | 27.4627 | 40.0994
-2.1814 | 8.7187 | 8.6699 | 7.6124 | 9.8328 | 15.5371 | 8.7187 | 16.3311 | 26.1639 | 41.701
11.957 | 9.5333 | 5.6168 | 10.4537 | 16.4142 | 14.1748 | 11.957 | 22.4107 | 38.8249 | 52.9997
5.7453 | 9.2587 | 7.9669 | 6.7196 | 12.5161 | 7.6164 | 9.2587 | 15.9783 | 28.4944 | 36.1109
-1.4135 | 10.7781 | 7.5896 | 7.2056 | 13.5332 | 14.4818 | 10.7781 | 17.9837 | 31.5169 | 45.9987
-5.833 | 8.8792 | 6.6337 | 7.7935 | 9.2697 | 13.1996 | 8.8792 | 16.6727 | 25.9424 | 39.142
-4.1802 | 8.3331 | 8.6024 | 7.7022 | 7.4293 | 16.7905 | 8.3331 | 16.0353 | 23.4646 | 40.2552
-3.0893 | 8.7795 | 4.6919 | 5.0395 | 17.2973 | 8.1141 | 8.7795 | 13.819 | 31.1163 | 39.2303
1.3453 | 9.8567 | 8.0875 | 7.863 | 15.5073 | 11.7226 | 9.8567 | 17.7197 | 33.2269 | 44.9495
-1.6802 | 11.1578 | 8.5871 | 6.0532 | 5.0958 | 11.5586 | 11.1578 | 17.211 | 22.3068 | 33.8654
7.0491 | 11.4082 | 11.3547 | 10.003 | 4.8019 | 12.0863 | 11.4082 | 21.4112 | 26.2131 | 38.2994
-4.8543 | 8.4422 | 8.1515 | 6.4112 | 12.0987 | 11.1084 | 8.4422 | 14.8535 | 26.9521 | 38.0605
3.2746 | 9.5739 | 12.0537 | 9.0399 | 3.626 | 13.0119 | 9.5739 | 18.6138 | 22.2398 | 35.2517
-3.4661 | 8.4814 | 7.1993 | 8.2936 | 9.9288 | 16.3069 | 8.4814 | 16.7751 | 26.7039 | 43.0108
2.093 | 8.3746 | 4.7856 | 3.5066 | 9.6125 | 9.4511 | 8.3746 | 11.8813 | 21.4937 | 30.9449
0.24659 | 8.7512 | 8.6792 | 4.4544 | 11.8812 | 15.3464 | 8.7512 | 13.2056 | 25.0868 | 40.4332
3.4902 | 9.005 | 8.4363 | 7.768 | 15.3191 | 17.8125 | 9.005 | 16.7729 | 32.092 | 49.9046
8.6555 | 9.8088 | 9.8847 | 5.3643 | 9.7339 | 10.2525 | 9.8088 | 15.1731 | 24.907 | 35.1595
3.146 | 8.155 | 7.3207 | 6.0265 | 10.3869 | 14.9379 | 8.155 | 14.1815 | 24.5684 | 39.5064
1.4956 | 9.6613 | 6.4114 | 5.6353 | 12.8197 | 11.5223 | 9.6613 | 15.2966 | 28.1163 | 39.6387
1.6711 | 9.1854 | 7.2678 | 9.0776 | 12.1524 | 11.1106 | 9.1854 | 18.263 | 30.4154 | 41.5261
-3.4751 | 8.6286 | 8.191 | 5.9039 | 9.6383 | 11.9293 | 8.6286 | 14.5326 | 24.1708 | 36.1001
8.667 | 8.7079 | 9.2056 | 9.5167 | 15.016 | 11.236 | 8.7079 | 18.2246 | 33.2406 | 44.4766
1.7943 | 9.4806 | 6.2167 | 8.6986 | 11.1957 | 9.2692 | 9.4806 | 18.1792 | 29.3749 | 38.6441
3.8872 | 11.5359 | 3.837 | 7.6733 | 12.9645 | 13.946 | 11.5359 | 19.2092 | 32.1736 | 46.1196
-4.097 | 9.6789 | 6.3264 | 7.9401 | 3.7716 | 7.7795 | 9.6789 | 17.619 | 21.3906 | 29.1701
-1.4121 | 10.6166 | 6.3614 | 8.5328 | 8.7474 | 9.1653 | 10.6166 | 19.1494 | 27.8968 | 37.0621
0.65651 | 8.9704 | 7.144 | 7.2507 | 8.1299 | 13.6657 | 8.9704 | 16.221 | 24.3509 | 38.0166
3.5415 | 10.0223 | 10.5317 | 8.0438 | 9.2017 | 12.3255 | 10.0223 | 18.066 | 27.2677 | 39.5932
0.60349 | 10.9905 | 7.9753 | 5.5133 | 5.2348 | 11.8384 | 10.9905 | 16.5038 | 21.7386 | 33.577
8.8883 | 10.3867 | 8.6679 | 8.5871 | 12.5954 | 11.4568 | 10.3867 | 18.9738 | 31.5692 | 43.026
-3.4856 | 11.1667 | 9.8769 | 9.6205 | 6.27 | 6.665 | 11.1667 | 20.7871 | 27.0572 | 33.7222
-6.1371 | 9.5248 | 7.4536 | 6.2652 | 7.9369 | 9.3704 | 9.5248 | 15.79 | 23.7269 | 33.0973
11.8853 | 7.7798 | 6.2794 | 6.4592 | 10.7182 | 12.3762 | 11.8853 | 18.3445 | 29.0627 | 41.4389
-0.93943 | 10.6212 | 5.9354 | 5.4383 | 10.5699 | 8.6881 | 10.6212 | 16.0595 | 26.6295 | 35.3176
1.5875 | 10.0734 | 6.9767 | 7.9628 | 11.6572 | 13.3549 | 10.0734 | 18.0362 | 29.6934 | 43.0483
9.8438 | 11.1684 | 11.1008 | 8.6581 | 9.0919 | 14.7846 | 11.1684 | 19.8265 | 28.9184 | 43.703
-10.8273 | 10.0211 | 9.4164 | 3.7058 | 9.0098 | 6.7648 | 10.0211 | 13.7269 | 22.7367 | 29.5015
-0.5587 | 8.7434 | 7.1696 | 6.9126 | 14.7827 | 11.5717 | 8.7434 | 15.656 | 30.4387 | 42.0103
1.8992 | 8.7833 | 9.0013 | 8.3045 | 6.9422 | 11.3436 | 8.7833 | 17.0877 | 24.03 | 35.3736
8.7852 | 9.4512 | 7.4976 | 7.0219 | 15.3086 | 8.106 | 9.4512 | 16.4731 | 31.7816 | 39.8877
11.3115 | 7.92 | 9.421 | 9.156 | 10.466 | 13.8017 | 11.3115 | 20.4675 | 30.9335 | 44.7352
8.0423 | 7.3227 | 6.6874 | 6.0513 | 13.2734 | 15.3619 | 8.0423 | 14.0936 | 27.367 | 42.7289
-9.9703 | 9.3781 | 8.3695 | 6.5115 | 8.3731 | 12.2552 | 9.3781 | 15.8896 | 24.2627 | 36.5179
8.7659 | 8.4709 | 5.3069 | 11.8497 | 15.524 | 10.2178 | 8.7659 | 20.6157 | 36.1397 | 46.3574
3.3636 | 9.7867 | 10.8937 | 5.9789 | 15.1636 | 12.8652 | 9.7867 | 15.7655 | 30.9291 | 43.7943
-1.6981 | 7.8783 | 9.394 | 5.5531 | 13.9323 | 13.4304 | 7.8783 | 13.4314 | 27.3638 | 40.7942
-2.8972 | 9.0703 | 8.2988 | 8.4058 | 13.7846 | 11.3923 | 9.0703 | 17.4761 | 31.2607 | 42.653
-1.4339 | 8.7673 | 8.135 | 7.2371 | 10.2445 | 11.3938 | 8.7673 | 16.0044 | 26.2488 | 37.6426
4.6936 | 7.9414 | 8.5498 | 6.6427 | 8.2099 | 14.0603 | 7.9414 | 14.5842 | 22.7941 | 36.8544
2.4916 | 8.4311 | 9.3499 | 4.6645 | 13.6445 | 12.273 | 8.4311 | 13.0956 | 26.7401 | 39.0131
-1.269 | 8.2578 | 9.43 | 5.3895 | 3.9022 | 15.0768 | 8.2578 | 13.6473 | 17.6878 | 32.7645
0.27099 | 8.9442 | 8.4124 | 4.9897 | 11.9021 | 9.6545 | 8.9442 | 13.9338 | 25.8359 | 35.4904
5.9102 | 8.4439 | 7.6361 | 7.2749 | 7.2711 | 13.8623 | 8.4439 | 15.7189 | 22.99 | 36.8522
4.0505 | 9.3495 | 6.9709 | 5.9779 | 10.947 | 8.972 | 9.3495 | 15.3274 | 26.2744 | 35.2463
-5.2279 | 7.7615 | 11.3335 | 6.3532 | 8.5729 | 13.5086 | 7.7615 | 14.1146 | 22.6875 | 36.196
8.0039 | 7.5729 | 10.4196 | 5.6833 | 6.8112 | 10.1906 | 8.0039 | 13.6872 | 20.4984 | 30.6889
-5.0012 | 8.5 | 10.5348 | 6.2361 | 11.2938 | 14.0152 | 8.5 | 14.7361 | 26.0299 | 40.0451
-1.1925 | 8.7313 | 6.6 | 6.8727 | 14.6346 | 12.574 | 8.7313 | 15.604 | 30.2386 | 42.8127
-1.7703 | 8.5703 | 8.4435 | 4.44 | 10.8179 | 12.9627 | 8.5703 | 13.0103 | 23.8282 | 36.7909
5.8587 | 9.5176 | 7.197 | 5.6999 | 6.5572 | 14.5919 | 9.5176 | 15.2176 | 21.7748 | 36.3667
13.236 | 8.6731 | 6.0406 | 6.8475 | 9.5256 | 13.8747 | 13.236 | 20.0834 | 29.609 | 43.4837
0.76532 | 8.6178 | 10.0177 | 7.7306 | 10.484 | 8.2778 | 8.6178 | 16.3484 | 26.8324 | 35.1101
0.81644 | 9.6932 | 7.344 | 7.2831 | 9.9282 | 9.7762 | 9.6932 | 16.9763 | 26.9044 | 36.6806
0.39352 | 9.2865 | 4.5056 | 5.8528 | 17.4291 | 9.6285 | 9.2865 | 15.1393 | 32.5684 | 42.197
1.6874 | 9.8255 | 7.2931 | 5.9973 | 9.7503 | 8.7691 | 9.8255 | 15.8228 | 25.5731 | 34.3421
0.13726 | 7.9581 | 3.5563 | 8.288 | 15.0141 | 11.933 | 7.9581 | 16.2461 | 31.2602 | 43.1932
8.225 | 9.7083 | 11.2462 | 8.4774 | 10.7638 | 13.7857 | 9.7083 | 18.1857 | 28.9495 | 42.7352
-5.3103 | 9.8603 | 6.8888 | 7.8929 | 8.2373 | 15.0954 | 9.8603 | 17.7532 | 25.9906 | 41.0859
4.1392 | 6.2658 | 7.5752 | 6.216 | 8.7323 | 13.5661 | 6.2658 | 12.4817 | 21.214 | 34.7801
0.049625 | 9.1081 | 3.7996 | 8.9597 | 7.8857 | 4.6145 | 9.1081 | 18.0678 | 25.9535 | 30.568
5.7412 | 8.0604 | 5.4946 | 7.7653 | 11.3006 | 9.1018 | 8.0604 | 15.8257 | 27.1264 | 36.2281
1.2171 | 9.2581 | 7.449 | 9.6443 | 13.8402 | 14.627 | 9.2581 | 18.9024 | 32.7426 | 47.3696
-8.7968 | 8.5186 | 7.9941 | 10.041 | 14.2794 | 11.5705 | 8.5186 | 18.5596 | 32.839 | 44.4095
3.1694 | 8.7356 | 9.728 | 4.5991 | 5.7578 | 14.8988 | 8.7356 | 13.3346 | 19.0924 | 33.9912
-5.4742 | 10.0831 | 10.5573 | 6.6513 | 7.6763 | 17.146 | 10.0831 | 16.7344 | 24.4108 | 41.5568
9.6801 | 8.7624 | 9.268 | 6.985 | 12.6417 | 15.7707 | 9.6801 | 16.665 | 29.3068 | 45.0775
6.1299 | 8.7753 | 3.6604 | 4.285 | 13.7396 | 11.711 | 8.7753 | 13.0604 | 26.8 | 38.511
5.665 | 9.2408 | 6.8872 | 7.0208 | 11.4468 | 13.0991 | 9.2408 | 16.2616 | 27.7084 | 40.8075
-5.6302 | 9.4771 | 8.3503 | 4.0041 | 5.6266 | 9.6174 | 9.4771 | 13.4812 | 19.1078 | 28.7251
11.2259 | 10.0935 | 9.8384 | 6.0349 | 10.9077 | 17.1332 | 11.2259 | 17.2608 | 28.1685 | 45.3017
7.8152 | 7.823 | 8.3867 | 5.6115 | 11.5597 | 10.4889 | 7.823 | 13.4345 | 24.9942 | 35.4831
-1.7085 | 7.8779 | 9.691 | 8.7946 | 10.4249 | 13.708 | 7.8779 | 16.6724 | 27.0973 | 40.8052
4.302 | 7.5897 | 9.5462 | 6.2301 | 13.557 | 9.8564 | 7.5897 | 13.8198 | 27.3768 | 37.2331
-1.8786 | 9.4092 | 11.4466 | 7.6094 | 12.698 | 13.888 | 9.4092 | 17.0186 | 29.7166 | 43.6046
-9.2818 | 9.0253 | 5.2612 | 6.7151 | 10.0358 | 11.5392 | 9.0253 | 15.7403 | 25.7761 | 37.3153
6.5004 | 9.8665 | 10.65 | 6.6424 | 9.8127 | 13.9474 | 9.8665 | 16.509 | 26.3216 | 40.2691
0.89322 | 8.9726 | 10.227 | 4.7314 | 5.7524 | 14.0972 | 8.9726 | 13.7039 | 19.4564 | 33.5536
4.1593 | 9.3292 | 10.9436 | 9.1097 | 12.8244 | 11.0685 | 9.3292 | 18.4389 | 31.2633 | 42.3317
0.46438 | 9.1965 | 8.0504 | 6.3662 | 9.9264 | 11.7965 | 9.1965 | 15.5627 | 25.4891 | 37.2856
18.2893 | 10.3768 | 7.8273 | 7.5317 | 14.1722 | 7.5589 | 18.2893 | 25.821 | 39.9932 | 47.552
-1.4053 | 8.9355 | 6.6988 | 6.1687 | 7.6422 | 9.1789 | 8.9355 | 15.1042 | 22.7464 | 31.9253
9.7408 | 8.9163 | 7.6803 | 8.4528 | 10.1955 | 9.7403 | 9.7408 | 18.1936 | 28.3892 | 38.1295
1.9404 | 10.5378 | 6.9759 | 7.3814 | 7.6168 | 12.9426 | 10.5378 | 17.9192 | 25.536 | 38.4786
10.506 | 7.789 | 7.8457 | 6.9592 | 1.197 | 7.8365 | 10.506 | 17.4652 | 18.6623 | 26.4987
3.9004 | 8.622 | 10.3816 | 8.9604 | 6.0088 | 8.9689 | 8.622 | 17.5824 | 23.5912 | 32.5601
-2.9051 | 10.023 | 10.5402 | 5.1688 | 6.6622 | 12.3456 | 10.023 | 15.1917 | 21.8539 | 34.1995
12.7506 | 9.7318 | 7.1009 | 4.8857 | 8.4035 | 10.1123 | 12.7506 | 17.6363 | 26.0398 | 36.1521
-4.9999 | 8.6686 | 8.913 | 7.7625 | 11.8454 | 9.0079 | 8.6686 | 16.431 | 28.2765 | 37.2844
15.6101 | 8.3767 | 7.1213 | 4.7083 | 5.6838 | 10.159 | 15.6101 | 20.3185 | 26.0023 | 36.1613
-4.7356 | 9.1391 | 9.0762 | 7.3165 | 9.5458 | 9.7267 | 9.1391 | 16.4557 | 26.0015 | 35.7282
0.48987 | 8.8079 | 8.1973 | 6.078 | 8.4171 | 14.0738 | 8.8079 | 14.8859 | 23.303 | 37.3768
2.9902 | 9.2047 | 9.7003 | 7.1593 | 8.0185 | 10.5986 | 9.2047 | 16.364 | 24.3824 | 34.981
-8.7815 | 8.8159 | 8.5657 | 9.6848 | 11.9647 | 12.8281 | 8.8159 | 18.5008 | 30.4655 | 43.2936
15.0605 | 8.1139 | 5.9002 | 9.7614 | 15.4925 | 5.1331 | 15.0605 | 24.8219 | 40.3145 | 45.4475
-5.5297 | 6.2419 | 9.2142 | 7.1343 | 14.5274 | 12.3848 | 6.2419 | 13.3762 | 27.9037 | 40.2885
1.7243 | 10.0844 | 7.635 | 6.8426 | 14.8307 | 8.9232 | 10.0844 | 16.927 | 31.7577 | 40.6809
1.9348 | 7.9358 | 9.1466 | 6.3425 | 14.4173 | 13.6756 | 7.9358 | 14.2783 | 28.6956 | 42.3712
4.977 | 9.3968 | 9.7904 | 6.0221 | 14.2871 | 12.0726 | 9.3968 | 15.419 | 29.7061 | 41.7787
4.4824 | 7.9305 | 5.1868 | 5.9788 | 8.6109 | 13.4069 | 7.9305 | 13.9093 | 22.5202 | 35.9271
1.5336 | 9.0831 | 9.1363 | 4.721 | 8.717 | 11.1494 | 9.0831 | 13.804 | 22.5211 | 33.6705
6.9618 | 9.5938 | 8.8931 | 7.5773 | 6.3041 | 12.7754 | 9.5938 | 17.1711 | 23.4751 | 36.2506
-2.8618 | 9.8706 | 11.8171 | 6.1229 | 10.7612 | 11.5819 | 9.8706 | 15.9936 | 26.7548 | 38.3367
5.7906 | 8.9002 | 9.2702 | 8.0728 | 11.7243 | 8.4431 | 8.9002 | 16.973 | 28.6972 | 37.1403
8.3525 | 9.1076 | 4.5254 | 8.0174 | 7.3427 | 9.9378 | 9.1076 | 17.1249 | 24.4676 | 34.4055
0.0062421 | 8.8362 | 10.4174 | 7.9452 | 10.3369 | 8.8197 | 8.8362 | 16.7814 | 27.1184 | 35.9381
7.1012 | 8.8032 | 7.0145 | 5.2278 | 14.583 | 11.6264 | 8.8032 | 14.031 | 28.614 | 40.2404
7.4417 | 9.2159 | 9.0964 | 3.9438 | 6.8608 | 12.3261 | 9.2159 | 13.1596 | 20.0204 | 32.3465
1.3376 | 9.5945 | 6.5017 | 9.408 | 7.3541 | 16.0563 | 9.5945 | 19.0025 | 26.3566 | 42.4129
7.4577 | 9.1462 | 6.417 | 4.4933 | 12.757 | 8.58 | 9.1462 | 13.6394 | 26.3964 | 34.9764
-0.72537 | 10.9649 | 6.5932 | 6.4316 | 11.6756 | 14.993 | 10.9649 | 17.3965 | 29.0721 | 44.065
1.2863 | 9.3409 | 10.4652 | 5.6197 | 10.4538 | 16.1532 | 9.3409 | 14.9606 | 25.4144 | 41.5675
8.569 | 9.7505 | 7.5516 | 6.9472 | 12.9358 | 4.902 | 9.7505 | 16.6977 | 29.6335 | 34.5354
9.0958 | 9.355 | 8.9249 | 6.4446 | 10.2371 | 8.1763 | 9.355 | 15.7996 | 26.0368 | 34.2131
6.4716 | 10.0374 | 6.1722 | 5.1395 | 16.0439 | 11.0694 | 10.0374 | 15.1769 | 31.2208 | 42.2902
-5.1991 | 9.1895 | 8.8635 | 4.98 | 11.8179 | 11.4612 | 9.1895 | 14.1695 | 25.9874 | 37.4486
1.9545 | 9.5157 | 4.4565 | 4.323 | 15.5037 | 13.6161 | 9.5157 | 13.8387 | 29.3425 | 42.9586
3.5918 | 10.7721 | 7.1413 | 9.0942 | 10.6796 | 9.0837 | 10.7721 | 19.8663 | 30.5459 | 39.6296
4.2792 | 7.9495 | 9.0538 | 7.5213 | 9.7308 | 12.7629 | 7.9495 | 15.4708 | 25.2015 | 37.9645
3.4831 | 8.3112 | 8.1057 | 6.9865 | 10.4048 | 11.9407 | 8.3112 | 15.2977 | 25.7025 | 37.6431
-4.2053 | 9.4348 | 8.3946 | 5.5893 | 9.5705 | 15.6552 | 9.4348 | 15.0241 | 24.5945 | 40.2497
6.2157 | 8.68 | 10.8987 | 8.0135 | 11.8678 | 11.0086 | 8.68 | 16.6936 | 28.5614 | 39.57
-6.878 | 7.7896 | 8.767 | 6.668 | 8.6296 | 11.5796 | 7.7896 | 14.4576 | 23.0872 | 34.6668
6.6197 | 8.5339 | 5.9345 | 7.1205 | 13.9376 | 6.7458 | 8.5339 | 15.6543 | 29.5919 | 36.3377
-1.487 | 9.1936 | 8.4788 | 4.6384 | 12.957 | 9.8862 | 9.1936 | 13.832 | 26.789 | 36.6751
1.683 | 8.7839 | 8.5891 | 6.4412 | 11.8349 | 12.1608 | 8.7839 | 15.2251 | 27.06 | 39.2209
0.093103 | 10.2854 | 5.9666 | 4.8124 | 10.8229 | 14.3024 | 10.2854 | 15.0979 | 25.9208 | 40.2232
8.7782 | 9.6066 | 5.7223 | 10.9042 | 14.9181 | 14.9891 | 9.6066 | 20.5108 | 35.4288 | 50.4179
7.2822 | 8.8343 | 11.699 | 3.172 | 5.4961 | 13.7286 | 8.8343 | 12.0062 | 20.5333 | 34.2619
10.6799 | 8.4025 | 11.2796 | 6.4035 | 15.6019 | 11.2712 | 10.6799 | 17.0833 | 32.6852 | 43.9564
-1.1332 | 9.3763 | 9.9076 | 9.3668 | 7.0686 | 11.5536 | 9.3763 | 18.7431 | 25.8117 | 37.3652
15.1121 | 7.2004 | 7.0836 | 6.2079 | 10.3765 | 11.4431 | 15.1121 | 21.32 | 31.6965 | 43.1396
1.2063 | 8.8359 | 7.1141 | 8.426 | 12.5524 | 15.6921 | 8.8359 | 17.262 | 29.8144 | 45.5065
-5.8613 | 8.6992 | 10.1851 | 6.1303 | 10.8368 | 10.971 | 8.6992 | 14.8295 | 25.6663 | 36.6373
4.9894 | 8.7313 | 7.7999 | 5.1258 | 12.8043 | 7.0826 | 8.7313 | 13.857 | 26.6613 | 33.744
10.023 | 8.2914 | 9.8573 | 5.7108 | 10.2137 | 10.7466 | 10.023 | 15.7338 | 25.9475 | 36.6941
2.7729 | 8.8266 | 10.5437 | 3.8044 | 11.3754 | 11.6635 | 8.8266 | 12.6309 | 24.0064 | 35.6698
8.5571 | 8.956 | 7.9437 | 4.1592 | 7.7849 | 16.2181 | 8.956 | 13.1152 | 20.9001 | 37.1182
3.0263 | 9.9154 | 9.2742 | 7.9655 | 17.0779 | 15.4139 | 9.9154 | 17.8809 | 34.9588 | 50.3727
7.3459 | 10.0523 | 5.3125 | 11.0307 | 6.7918 | 19.3696 | 10.0523 | 21.0829 | 27.8748 | 47.2444
-9.1811 | 8.8294 | 7.5678 | 6.1648 | 6.436 | 8.3646 | 8.8294 | 14.9942 | 21.4302 | 29.7948
-1.3714 | 7.7631 | 9.3087 | 8.2277 | 9.7476 | 13.6683 | 7.7631 | 15.9909 | 25.7385 | 39.4068
-4.335 | 8.4413 | 10.0201 | 1.7428 | 5.2582 | 12.2222 | 8.4413 | 10.1841 | 18.4614 | 30.6836
6.8741 | 9.4984 | 5.8936 | 3.6442 | 11.9093 | 13.5953 | 9.4984 | 13.1426 | 25.0519 | 38.6473
-4.0542 | 10.1078 | 11.4208 | 7.5237 | 9.8311 | 16.5525 | 10.1078 | 17.6315 | 27.4626 | 44.015
11.0582 | 8.4277 | 6.8273 | 5.8872 | 6.8489 | 14.0336 | 11.0582 | 16.9454 | 23.7943 | 37.828
-4.5814 | 9.661 | 12.8532 | 8.6121 | 12.7472 | 10.5961 | 9.661 | 18.2731 | 31.0202 | 41.6163
2.2002 | 10.3714 | 10.8112 | 7.8361 | 8.4619 | 12.8202 | 10.3714 | 18.2075 | 26.6694 | 39.4897
-2.5534 | 8.7986 | 9.7918 | 9.6978 | 11.3434 | 8.9372 | 8.7986 | 18.4964 | 29.8398 | 38.777
16.3283 | 8.1352 | 6.0122 | 6.857 | 11.2735 | 10.285 | 16.3283 | 23.1852 | 34.4588 | 44.7438
4.4491 | 9.0087 | 7.5449 | 6.6988 | 10.9472 | 11.7752 | 9.0087 | 15.7075 | 26.6547 | 38.4299
-1.2997 | 7.7241 | 10.1602 | 6.5467 | 12.3082 | 13.1047 | 7.7241 | 14.2708 | 26.579 | 39.6837
7.6809 | 9.0303 | 6.0108 | 8.4628 | 9.8287 | 15.9025 | 9.0303 | 17.4932 | 27.3218 | 43.2243
1.3248 | 9.6263 | 8.1443 | 6.3896 | 12.8278 | 11.6454 | 9.6263 | 16.016 | 28.8438 | 40.4892
2.9815 | 6.6687 | 9.3452 | 6.9772 | 8.8388 | 15.9765 | 6.6687 | 13.6459 | 22.4847 | 38.4612
1.5321 | 10.1754 | 5.2299 | 2.4876 | 10.1602 | 10.2016 | 10.1754 | 12.663 | 22.8232 | 33.0247
-3.1667 | 9.1932 | 7.0494 | 5.0238 | 9.0925 | 10.3594 | 9.1932 | 14.217 | 23.3095 | 33.6689
1.1837 | 10.5419 | 8.6215 | 5.2574 | 11.7138 | 12.6933 | 10.5419 | 15.7993 | 27.5131 | 40.2064
-4.7102 | 9.1351 | 5.7884 | 7.4031 | 8.7842 | 10.4325 | 9.1351 | 16.5382 | 25.3224 | 35.7549
3.2037 | 8.7033 | 4.2386 | 9.7834 | 12.0592 | 10.1993 | 8.7033 | 18.4867 | 30.5459 | 40.7452
4.4796 | 8.191 | 6.9046 | 7.9188 | 10.6709 | 7.7695 | 8.191 | 16.1097 | 26.7806 | 34.5501
2.5106 | 9.738 | 10.3478 | 8.46 | 10.09 | 15.5138 | 9.738 | 18.198 | 28.288 | 43.8019
1.1285 | 10.8354 | 8.3994 | 4.5201 | 11.5577 | 13.2907 | 10.8354 | 15.3555 | 26.9132 | 40.2039
-7.5296 | 9.3182 | 8.1814 | 7.8441 | 11.0729 | 13.5526 | 9.3182 | 17.1623 | 28.2351 | 41.7878
-5.8792 | 8.6471 | 9.8313 | 7.2231 | 7.9096 | 13.9856 | 8.6471 | 15.8702 | 23.7798 | 37.7654
-2.56 | 9.6324 | 3.4072 | 8.8285 | 9.5769 | 12.8892 | 9.6324 | 18.461 | 28.0379 | 40.9271
2.6647 | 8.9297 | 11.3278 | 9.5662 | 6.0032 | 9.6861 | 8.9297 | 18.4959 | 24.4991 | 34.1853
6.124 | 8.8845 | 5.7752 | 9.0795 | 15.7137 | 7.5381 | 8.8845 | 17.964 | 33.6777 | 41.2158
2.6138 | 9.5603 | 2.5968 | 10.1714 | 8.9419 | 13.8899 | 9.5603 | 19.7317 | 28.6736 | 42.5635
-1.4338 | 9.3527 | 12.7135 | 3.3286 | 13.3241 | 15.6448 | 9.3527 | 12.6813 | 26.0053 | 41.6502
7.2919 | 8.5057 | 5.1422 | 11.0538 | 6.323 | 10.9841 | 8.5057 | 19.5595 | 25.8825 | 36.8666
-1.014 | 8.4845 | 4.9763 | 6.5316 | 10.0286 | 12.7559 | 8.4845 | 15.0161 | 25.0447 | 37.8006
6.4227 | 8.2985 | 6.8839 | 5.8075 | 9.5304 | 10.1893 | 8.2985 | 14.1061 | 23.6364 | 33.8257
3.3866 | 10.4032 | 6.8637 | 6.8884 | 6.6184 | 11.8398 | 10.4032 | 17.2916 | 23.91 | 35.7498
0.041535 | 9.9479 | 7.6896 | 6.6303 | 1.9546 | 12.7218 | 9.9479 | 16.5782 | 18.5328 | 31.2546
-3.9206 | 8.3201 | 10.488 | 10.0999 | 10.2622 | 10.2291 | 8.3201 | 18.42 | 28.6823 | 38.9114
5.3378 | 7.8301 | 9.7645 | 9.4931 | 13.2312 | 15.2623 | 7.8301 | 17.3232 | 30.5544 | 45.8167
4.9032 | 7.6002 | 7.911 | 7.9772 | 13.0552 | 11.9337 | 7.6002 | 15.5774 | 28.6327 | 40.5663
3.0465 | 9.9791 | 6.1034 | 8.8598 | 11.2558 | 10.1284 | 9.9791 | 18.8389 | 30.0947 | 40.2231
-8.2811 | 9.1316 | 6.977 | 6.8877 | 9.2722 | 13.0206 | 9.1316 | 16.0193 | 25.2915 | 38.312
9.2633 | 7.642 | 9.9238 | 6.1258 | 10.7795 | 9.8726 | 9.2633 | 15.3891 | 26.1686 | 36.0412
-2.6233 | 7.4997 | 8.8924 | 6.8017 | 8.3834 | 16.4888 | 7.4997 | 14.3013 | 22.6847 | 39.1735
6.2781 | 7.7183 | 9.6262 | 8.186 | 12.939 | 5.616 | 7.7183 | 15.9043 | 28.8433 | 34.4594
-0.52293 | 8.6213 | 10.1561 | 6.051 | 17.0834 | 8.954 | 8.6213 | 14.6722 | 31.7556 | 40.7096
-8.3951 | 8.9444 | 8.0639 | 6.1692 | 13.7497 | 13.393 | 8.9444 | 15.1136 | 28.8634 | 42.2564
-13.9365 | 10.0361 | 9.4917 | 6.6634 | 5.8692 | 11.8739 | 10.0361 | 16.6995 | 22.5687 | 34.4425
0.99258 | 9.6554 | 12.5556 | 6.1492 | 7.7376 | 13.3382 | 9.6554 | 15.8046 | 23.5422 | 36.8803
12.9709 | 8.999 | 10.6972 | 9.473 | 4.5174 | 1.0861 | 12.9709 | 22.4439 | 26.9612 | 28.0473
11.8752 | 9.018 | 8.7961 | 7.3157 | 7.6735 | 10.5379 | 11.8752 | 19.1909 | 26.8644 | 37.4023
0.53992 | 8.1927 | 8.6659 | 6.5186 | 6.2482 | 13.3856 | 8.1927 | 14.7113 | 20.9595 | 34.3451
7.4864 | 8.4769 | 7.5783 | 4.8227 | 12.2175 | 12.7362 | 8.4769 | 13.2995 | 25.517 | 38.2532
2.0053 | 9.3311 | 6.3548 | 9.2478 | 4.4563 | 11.6986 | 9.3311 | 18.5789 | 23.0351 | 34.7338
0.15358 | 8.7559 | 8.8257 | 5.5709 | 16.8799 | 6.3285 | 8.7559 | 14.3268 | 31.2067 | 37.5352 | #REF! | chance that the project will take less than 40 days
-2.5111 | 8.0509 | 4.4735 | 7.6191 | 10.4078 | 9.4529 | 8.0509 | 15.67 | 26.0778 | 35.5306
3.1104 | 10.2489 | 6.6365 | 5.9574 | 6.0233 | 12.4977 | 10.2489 | 16.2063 | 22.2296 | 34.7272
0.06957 | 7.7694 | 5.6919 | 5.117 | 9.8057 | 13.3899 | 7.7694 | 12.8864 | 22.6921 | 36.082
9.1731 | 10.2675 | 5.4562 | 6.9048 | 9.6301 | 10.0679 | 10.2675 | 17.1723 | 26.8024 | 36.8704
0.078861 | 9.0961 | 6.896 | 7.2475 | 13.1673 | 8.7383 | 9.0961 | 16.3436 | 29.5109 | 38.2492
6.0667 | 6.2549 | 5.5166 | 5.1607 | 14.6592 | 9.5176 | 6.2549 | 11.4156 | 26.0748 | 35.5924
7.0344 | 9.9477 | 6.99 | 6.8803 | 7.2151 | 10.5514 | 9.9477 | 16.8279 | 24.043 | 34.5944
3.2502 | 7.1691 | 10.5622 | 6.1431 | 10.1036 | 11.9879 | 7.1691 | 13.3122 | 23.4157 | 35.4036
2.4819 | 6.6501 | 4.0364 | 4.4858 | 15.0419 | 11.5588 | 6.6501 | 11.1359 | 26.1778 | 37.7366
0.76335 | 9.9273 | 6.2693 | 10.8313 | 12.9967 | 7.112 | 9.9273 | 20.7586 | 33.7553 | 40.8673
-1.8464 | 8.4484 | 10.7243 | 6.285 | 14.7477 | 12.7223 | 8.4484 | 14.7334 | 29.4811 | 42.2035
-1.8671 | 8.2164 | 12.3611 | 7.554 | 5.0308 | 11.917 | 8.2164 | 15.7704 | 20.8013 | 32.7183
1.2222 | 8.2038 | 7.9336 | 6.1649 | 10.2237 | 8.5042 | 8.2038 | 14.3687 | 24.5925 | 33.0966
5.0284 | 8.244 | 4.8871 | 5.1015 | 5.9221 | 13.2491 | 8.244 | 13.3456 | 19.2677 | 32.5167
0.96134 | 9.9479 | 3.9057 | 5.2114 | 11.2594 | 12.414 | 9.9479 | 15.1593 | 26.4187 | 38.8327
3.0322 | 7.5813 | 8.1353 | 4.0853 | 11.921 | 14.5777 | 7.5813 | 11.6666 | 23.5876 | 38.1653
-0.30321 | 10.0747 | 8.6707 | 7.8165 | 12.7182 | 14.6052 | 10.0747 | 17.8913 | 30.6095 | 45.2147
1.9232 | 7.768 | 7.7439 | 8.2335 | 10.783 | 8.9798 | 7.768 | 16.0015 | 26.7844 | 35.7642
4.3911 | 9.2777 | 6.3251 | 9.122 | 11.9302 | 9.4928 | 9.2777 | 18.3996 | 30.3298 | 39.8226
2.0423 | 9.0935 | 5.6135 | 9.8168 | 9.5911 | 9.0512 | 9.0935 | 18.9103 | 28.5014 | 37.5526
6.1959 | 9.0887 | 4.2878 | 8.3815 | 9.5757 | 12.2328 | 9.0887 | 17.4702 | 27.0459 | 39.2787
5.021 | 8.6838 | 5.6051 | 7.6877 | 8.4145 | 10.4596 | 8.6838 | 16.3715 | 24.786 | 35.2456
-4.5276 | 6.3254 | 6.9231 | 6.3067 | 7.8621 | 9.582 | 6.3254 | 12.6321 | 20.4942 | 30.0761
3.6223 | 10.0923 | 7.1233 | 14.3737 | 10.9588 | 11.6224 | 10.0923 | 24.466 | 35.4248 | 47.0472
2.8066 | 9.152 | 9.4684 | 4.3068 | 9.2485 | 15.3549 | 9.152 | 13.4589 | 22.7073 | 38.0623
-2.9632 | 10.0141 | 9.3772 | 8.7771 | 8.0006 | 9.6656 | 10.0141 | 18.7912 | 26.7918 | 36.4574
4.0829 | 8.3053 | 6.9212 | 4.6023 | 12.4611 | 4.859 | 8.3053 | 12.9077 | 25.3688 | 30.2278
-1.844 | 9.5062 | 9.8025 | 8.4991 | 12.0679 | 10.9065 | 9.5062 | 18.0053 | 30.0733 | 40.9798
0.79447 | 8.2212 | 5.8113 | 8.8456 | 15.6903 | 13.2569 | 8.2212 | 17.0668 | 32.7572 | 46.0141
-0.77702 | 10.1982 | 10.2318 | 6.4536 | 12.508 | 13.0767 | 10.1982 | 16.6518 | 29.1598 | 42.2365
1.9958 | 7.0269 | 8.0108 | 5.696 | 6.3785 | 10.7887 | 7.0269 | 12.7228 | 19.1013 | 29.89
6.4381 | 8.7958 | 9.297 | 7.7098 | 11.3774 | 3.5207 | 8.7958 | 16.5057 | 27.8831 | 31.4038
4.7488 | 10.2322 | 7.0157 | 5.5516 | 7.3779 | 12.4151 | 10.2322 | 15.7838 | 23.1617 | 35.5768
-4.6069 | 7.3226 | 6.7511 | 8.9863 | 1.519 | 9.3544 | 7.3226 | 16.3088 | 17.8278 | 27.1822
9.753 | 8.7649 | 7.2706 | 6.7398 | 9.8857 | 9.3746 | 9.753 | 16.4928 | 26.3784 | 35.753
0.13497 | 9.2909 | 7.6912 | 7.8396 | 4.4387 | 15.4113 | 9.2909 | 17.1305 | 21.5691 | 36.9804
0.62871 | 9.5927 | 6.7138 | 7.9597 | 13.8412 | 16.0518 | 9.5927 | 17.5524 | 31.3935 | 47.4453
-0.88391 | 8.7635 | 5.834 | 7.6716 | 13.2853 | 7.2012 | 8.7635 | 16.4351 | 29.7205 | 36.9217
4.0033 | 9.5385 | 3.275 | 6.6623 | 14.2961 | 14.3519 | 9.5385 | 16.2008 | 30.497 | 44.8489
-2.1185 | 8.2834 | 8.1858 | 8.0081 | 10.3999 | 14.5204 | 8.2834 | 16.2915 | 26.6915 | 41.2119
-0.53914 | 7.4728 | 8.0581 | 6.8411 | 11.5661 | 12.6506 | 7.4728 | 14.3139 | 25.88 | 38.5306
1.4541 | 10.051 | 6.6353 | 6.2668 | 4.1376 | 10.6353 | 10.051 | 16.3178 | 20.4554 | 31.0907
-1.7407 | 9.1168 | 10.6361 | 7.2554 | 14.6267 | 10.8016 | 9.1168 | 16.3722 | 30.999 | 41.8006
13.5648 | 7.9401 | 7.7298 | 6.1279 | 8.0693 | 13.6042 | 13.5648 | 19.6927 | 27.762 | 41.3661
9.0761 | 8.5022 | 8.1955 | 8.0608 | 10.4844 | 6.2111 | 9.0761 | 17.1369 | 27.6213 | 33.8324
6.8285 | 9.3363 | 3.6668 | 8.4589 | 9.9992 | 15.3321 | 9.3363 | 17.7953 | 27.7944 | 43.1265
0.45678 | 9.8256 | 7.1544 | 6.1753 | 10.8047 | 15.0561 | 9.8256 | 16.0009 | 26.8056 | 41.8618
6.4836 | 10.0419 | 3.569 | 4.5722 | 11.4509 | 15.1893 | 10.0419 | 14.6141 | 26.065 | 41.2542
-2.6233 | 8.3261 | 8.4799 | 10.7282 | 7.3446 | 17.5392 | 8.3261 | 19.0542 | 26.3988 | 43.938
5.0503 | 9.5738 | 4.2402 | 6.3951 | 9.1307 | 9.1609 | 9.5738 | 15.9689 | 25.0996 | 34.2606
10.8463 | 9.6195 | 6.6614 | 5.3769 | 9.3583 | 12.2863 | 10.8463 | 16.2231 | 25.5814 | 37.8677
-0.76651 | 8.7314 | 7.6878 | 7.3463 | 6.2204 | 10.8228 | 8.7314 | 16.0777 | 22.2981 | 33.1208
-7.5217 | 7.3054 | 6.0961 | 7.9637 | 10.2469 | 10.7538 | 7.3054 | 15.269 | 25.5159 | 36.2697
3.443 | 9.1556 | 8.4616 | 6.4732 | 11.0659 | 10.9435 | 9.1556 | 15.6288 | 26.6947 | 37.6383
3.9305 | 9.2701 | 7.1588 | 8.0132 | 11.1947 | 9.2695 | 9.2701 | 17.2833 | 28.4779 | 37.7474
-4.0836 | 8.8429 | 7.7139 | 6.4478 | 11.056 | 9.1952 | 8.8429 | 15.2908 | 26.3468 | 35.542
-1.8478 | 9.1724 | 9.0713 | 7.7164 | 13.5692 | 13.5415 | 9.1724 | 16.8887 | 30.4579 | 43.9994
11.5211 | 8.925 | 8.3078 | 8.2382 | 8.4154 | 16.36 | 11.5211 | 19.7593 | 28.1747 | 44.5347
-2.8203 | 9.9221 | 7.3184 | 4.3728 | 13.6317 | 19.8206 | 9.9221 | 14.2948 | 27.9265 | 47.7471
-2.3022 | 8.1564 | 9.9706 | 3.3422 | 8.6132 | 9.5785 | 8.1564 | 11.4986 | 20.1118 | 29.6903
7.7894 | 7.3438 | 6.6621 | 7.1948 | 13.6233 | 15.3718 | 7.7894 | 14.9842 | 28.6075 | 43.9793
-2.7133 | 10.0219 | 7.7945 | 7.1047 | 7.9657 | 10.8251 | 10.0219 | 17.1266 | 25.0923 | 35.9174
0.9232 | 9.4055 | 9.3619 | 6.3611 | 10.1749 | 9.4725 | 9.4055 | 15.7666 | 25.9415 | 35.414
3.5403 | 10.0597 | 8.6156 | 6.2444 | 8.1219 | 9.9427 | 10.0597 | 16.3041 | 24.426 | 34.3688
-7.4912 | 7.7569 | 4.9623 | 5.6912 | 12.5384 | 14.543 | 7.7569 | 13.4481 | 25.9865 | 40.5295
-0.76732 | 10.808 | 7.0649 | 7.7398 | 12.5856 | 17.8694 | 10.808 | 18.5477 | 31.1333 | 49.0027
-2.3727 | 9.2625 | 6.0283 | 5.1534 | 5.6478 | 11.0078 | 9.2625 | 14.4159 | 20.0637 | 31.0715
-3.3252 | 8.8373 | 7.7837 | 6.3142 | 6.5223 | 14.0734 | 8.8373 | 15.1516 | 21.6738 | 35.7472
2.7112 | 9.3627 | 9.3417 | 7.8477 | 7.9172 | 12.813 | 9.3627 | 17.2104 | 25.1276 | 37.9406
0.74458 | 7.8116 | 9.0499 | 7.0302 | 12.9561 | 12.3371 | 7.8116 | 14.8418 | 27.7979 | 40.135
5.8065 | 8.1931 | 6.4189 | 7.7479 | 10.5564 | 10.5894 | 8.1931 | 15.941 | 26.4974 | 37.0869
0.14488 | 7.6383 | 9.7017 | 8.1334 | 4.3511 | 9.6381 | 7.6383 | 15.7717 | 20.1228 | 29.7609
12.799 | 8.2808 | 10.2988 | 5.4928 | 11.8537 | 14.7524 | 12.799 | 18.2918 | 30.1455 | 44.8978
9.2966 | 9.5103 | 9.5028 | 8.2641 | 9.2166 | 16.3196 | 9.5103 | 17.7743 | 26.991 | 43.3105
-6.506 | 10.9366 | 4.3856 | 5.7718 | 9.1438 | 9.993 | 10.9366 | 16.7083 | 25.8521 | 35.8451
-0.34621 | 8.4618 | 7.281 | 7.8695 | 9.8787 | 8.5477 | 8.4618 | 16.3313 | 26.2101 | 34.7578
10.1671 | 9.602 | 14.507 | 6.1194 | 10.3212 | 11.8729 | 10.1671 | 16.2864 | 26.6076 | 38.4805
-0.33699 | 9.8281 | 7.5767 | 8.8424 | 3.5939 | 12.3046 | 9.8281 | 18.6704 | 22.2643 | 34.5689
1.3945 | 8.937 | 9.3105 | 6.2175 | 5.2963 | 7.779 | 8.937 | 15.1545 | 20.4508 | 28.2298
12.4074 | 8.9075 | 9.1936 | 6.6798 | 9.2608 | 14.0931 | 12.4074 | 19.0871 | 28.348 | 42.4411
-9.166 | 10.3957 | 8.9787 | 7.0508 | 5.1513 | 10.0859 | 10.3957 | 17.4466 | 22.5979 | 32.6838
-1.8294 | 10.6045 | 6.4257 | 10.4443 | 7.0772 | 14.4502 | 10.6045 | 21.0489 | 28.1261 | 42.5762
5.3671 | 8.6659 | 7.6655 | 6.4176 | 10.0594 | 10.0886 | 8.6659 | 15.0835 | 25.1429 | 35.2315
5.2593 | 8.7001 | 6.8343 | 5.243 | 8.511 | 14.3324 | 8.7001 | 13.9431 | 22.4541 | 36.7865
-0.93912 | 9.2904 | 9.8052 | 7.3446 | 8.1695 | 13.0117 | 9.2904 | 16.635 | 24.8045 | 37.8162
6.6001 | 9.4089 | 6.2424 | 4.9976 | 10.5456 | 11.3511 | 9.4089 | 14.4064 | 24.9521 | 36.3032
12.1278 | 9.3284 | 5.8466 | 7.2014 | 8.5953 | 10.8761 | 12.1278 | 19.3292 | 27.9244 | 38.8005
6.2493 | 8.4941 | 8.5769 | 7.957 | 14.9404 | 6.9577 | 8.4941 | 16.4511 | 31.3915 | 38.3492
-0.52573 | 9.739 | 5.2492 | 7.2788 | 4.2932 | 16.0215 | 9.739 | 17.0178 | 21.311 | 37.3326
-3.5728 | 8.3724 | 6.5262 | 5.279 | 6.8098 | 13.6442 | 8.3724 | 13.6514 | 20.4612 | 34.1055
0.28329 | 7.8686 | 8.2472 | 5.9171 | 13.4657 | 11.1642 | 7.8686 | 13.7857 | 27.2514 | 38.4156
10.6699 | 7.7067 | 6.8786 | 2.9431 | 14.5656 | 10.8516 | 10.6699 | 13.613 | 28.1786 | 39.0301
0.61413 | 8.6733 | 12.0972 | 5.6282 | 15.8895 | 7.1887 | 8.6733 | 14.3015 | 30.191 | 37.3797
1.3111 | 8.9962 | 8.8577 | 9.676 | 15.5474 | 6.202 | 8.9962 | 18.6722 | 34.2197 | 40.4217
0.27742 | 8.1428 | 5.9063 | 9.0796 | 10.0514 | 13.7905 | 8.1428 | 17.2224 | 27.2738 | 41.0643
4.0318 | 8.6228 | 7.7375 | 5.0449 | 9.602 | 14.7113 | 8.6228 | 13.6676 | 23.2696 | 37.9809
-0.35947 | 10.3093 | 2.6676 | 8.465 | 10.4012 | 10.4189 | 10.3093 | 18.7743 | 29.1755 | 39.5944
-3.2167 | 9.9375 | 7.812 | 10.0544 | 9.6487 | 13.9697 | 9.9375 | 19.9918 | 29.6405 | 43.6103
14.4933 | 8.0744 | 4.5265 | 5.0768 | 6.8395 | 17.6257 | 14.4933 | 19.5701 | 26.4096 | 44.0353
-0.05667 | 9.1154 | 9.0899 | 7.8046 | 12.3722 | 11.2557 | 9.1154 | 16.92 | 29.2922 | 40.5479
0.31636 | 9.178 | 7.1652 | 8.334 | 6.4915 | 15.2789 | 9.178 | 17.5119 | 24.0034 | 39.2823
0.9146 | 8.7367 | 5.4751 | 4.8745 | 8.8156 | 18.8262 | 8.7367 | 13.6112 | 22.4268 | 41.253
-4.2951 | 7.9732 | 9.2302 | 6.2139 | 10.1651 | 13.6302 | 7.9732 | 14.1871 | 24.3522 | 37.9824
0.61564 | 6.5113 | 11.0001 | 6.8315 | 8.5282 | 10.4788 | 6.5113 | 13.3429 | 21.8711 | 32.3498
-5.9311 | 9.6912 | 6.7447 | 6.1381 | 8.9448 | 14.6825 | 9.6912 | 15.8293 | 24.774 | 39.4565
8.8645 | 10.3752 | 10.6519 | 9.7106 | 12.344 | 10.5885 | 10.3752 | 20.0857 | 32.4298 | 43.0183
-0.077127 | 7.8831 | 8.2595 | 7.6689 | 12.9402 | 11.3177 | 7.8831 | 15.552 | 28.4922 | 39.8099
8.221 | 10.184 | 5.1269 | 10.0199 | 10.3687 | 13.6646 | 10.184 | 20.204 | 30.5727 | 44.2373
2.3121 | 8.8982 | 8.4013 | 8.0637 | 10.1236 | 12.4168 | 8.8982 | 16.9619 | 27.0855 | 39.5022
-3.9885 | 7.6886 | 10.2943 | 5.7882 | 11.5954 | 17.2369 | 7.6886 | 13.4767 | 25.0721 | 42.3091
-0.8005 | 8.2854 | 5.348 | 5.7684 | 5.8464 | 11.1392 | 8.2854 | 14.0538 | 19.9002 | 31.0394
11.6303 | 9.2464 | 6.6373 | 6.1123 | 10.8072 | 13.5184 | 11.6303 | 17.7426 | 28.5499 | 42.0682 | #REF!
0.1422 | 8.1281 | 5.8142 | 6.326 | 5.8073 | 12.6264 | 8.1281 | 14.4541 | 20.2614 | 32.8878
-5.6659 | 9.1885 | 6.8254 | 11.5343 | 9.3822 | 11.1139 | 9.1885 | 20.7228 | 30.105 | 41.2189
-2.8431 | 10.7377 | 9.3958 | 7.0307 | 9.2855 | 11.7966 | 10.7377 | 17.7683 | 27.0539 | 38.8505
7.1306 | 9.3442 | 6.4172 | 6.0504 | 10.8044 | 10.2878 | 9.3442 | 15.3946 | 26.199 | 36.4869
5.0317 | 9.0005 | 9.0723 | 7.8246 | 6.2876 | 14.3287 | 9.0005 | 16.8251 | 23.1127 | 37.4414
3.9317 | 10.1409 | 6.9365 | 6.9997 | 9.7224 | 12.0155 | 10.1409 | 17.1406 | 26.863 | 38.8785
2.0395 | 8.3187 | 5.7871 | 7.3522 | 13.3499 | 9.7937 | 8.3187 | 15.671 | 29.0209 | 38.8146
3.8712 | 9.4733 | 8.4702 | 5.4584 | 7.8668 | 5.7745 | 9.4733 | 14.9317 | 22.7984 | 28.5729
-4.0776 | 7.7057 | 7.205 | 6.8721 | 12.8002 | 7.8342 | 7.7057 | 14.5778 | 27.378 | 35.2121
-1.3249 | 8.8018 | 8.8892 | 9.2689 | 10.9364 | 9.112 | 8.8018 | 18.0707 | 29.0071 | 38.1191
4.3016 | 6.8414 | 5.8268 | 7.5565 | 14.8323 | 9.8738 | 6.8414 | 14.3979 | 29.2302 | 39.104
8.9192 | 9.001 | 8.2401 | 6.1909 | 13.81 | 17.9803 | 9.001 | 15.1919 | 29.0019 | 46.9822
17.0008 | 8.0481 | 7.81 | 4.4391 | 3.4734 | 13.0324 | 17.0008 | 21.4399 | 24.9133 | 37.9457
4.6173 | 9.5883 | 8.7526 | 2.8878 | 11.2163 | 9.6864 | 9.5883 | 12.476 | 23.6924 | 33.3787
-4.0446 | 9.3864 | 6.5299 | 5.4345 | 8.6456 | 11.4254 | 9.3864 | 14.8209 | 23.4665 | 34.8919
0.065518 | 8.8772 | 12.4692 | 5.7103 | 6.6014 | 6.0414 | 8.8772 | 14.5875 | 21.3463 | 27.3877
3.3415 | 10.313 | 6.1578 | 7.7942 | 15.0236 | 7.3361 | 10.313 | 18.1072 | 33.1309 | 40.4669
-1.4804 | 8.1006 | 5.7317 | 8.4113 | 13.4796 | 13.3825 | 8.1006 | 16.5119 | 29.9915 | 43.374
5.193 | 7.2915 | 7.7697 | 0.72696 | 13.3983 | 10.8127 | 7.2915 | 8.0184 | 21.4167 | 32.2294
-3.7113 | 9.3479 | 6.7941 | 6.3042 | 11.1081 | 11.7345 | 9.3479 | 15.6521 | 26.7602 | 38.4948
9.3933 | 7.546 | 9.5121 | 11.3745 | 4.4253 | 15.9105 | 9.3933 | 20.7678 | 25.193 | 41.1035
-4.0893 | 8.9542 | 9.0837 | 7.5314 | 10.3334 | 8.6855 | 8.9542 | 16.4856 | 26.8191 | 35.5045
0.73038 | 8.4725 | 8.0302 | 6.6438 | 7.607 | 11.4739 | 8.4725 | 15.1163 | 22.7233 | 34.1972
-2.7452 | 8.1674 | 8.8969 | 7.6547 | 16.1602 | 13.5612 | 8.1674 | 15.8221 | 31.9823 | 45.5435
-1.5736 | 10.8566 | 8.77 | 9.8865 | 10.4605 | 12.1849 | 10.8566 | 20.7431 | 31.2036 | 43.3885
-8.7816 | 8.9598 | 8.1632 | 5.9592 | 11.9527 | 11.4694 | 8.9598 | 14.919 | 26.8717 | 38.3411
13.8509 | 10.2484 | 11.6668 | 6.612 | 8.8354 | 13.6837 | 13.8509 | 20.4629 | 29.2983 | 42.9819
2.3382 | 8.4869 | 5.3725 | 8.1298 | 10.3228 | 18.8096 | 8.4869 | 16.6167 | 26.9395 | 45.7491
-1.7406 | 8.1847 | 8.5938 | 3.5732 | 10.2145 | 15.9972 | 8.1847 | 11.758 | 21.9724 | 37.9696
-9.046 | 9.8936 | 7.842 | 4.4468 | 9.4717 | 11.3578 | 9.8936 | 14.3404 | 23.8121 | 35.1699
1.0174 | 9.3471 | 7.3918 | 6.5517 | 12.7998 | 8.968 | 9.3471 | 15.8988 | 28.6986 | 37.6666
-0.35472 | 10.5758 | 7.5601 | 10.6701 | 5.1121 | 11.5333 | 10.5758 | 21.2458 | 26.3579 | 37.8912
-5.373 | 10.5301 | 8.4033 | 5.0313 | 11.2321 | 12.6819 | 10.5301 | 15.5614 | 26.7935 | 39.4754
2.2398 | 8.4017 | 8.2457 | 7.6941 | 12.0855 | 12.6244 | 8.4017 | 16.0958 | 28.1813 | 40.8057
0.66236 | 9.7646 | 6.3253 | 7.4883 | 13.2902 | 7.2821 | 9.7646 | 17.2529 | 30.5431 | 37.8252
13.673 | 9.4343 | 8.6296 | 5.6934 | 13.6128 | 8.818 | 13.673 | 19.3664 | 32.9792 | 41.7972
0.78331 | 9.103 | 9.7701 | 8.0299 | 14.0234 | 9.9071 | 9.103 | 17.1329 | 31.1563 | 41.0633
-5.3905 | 8.0547 | 5.3912 | 6.897 | 8.9647 | 7.0249 | 8.0547 | 14.9517 | 23.9165 | 30.9414
-1.0449 | 10.8765 | 6.8482 | 6.6478 | 12.617 | 9.544 | 10.8765 | 17.5243 | 30.1413 | 39.6853
0.48602 | 10.1901 | 6.1717 | 8.0404 | 7.9007 | 12.0859 | 10.1901 | 18.2304 | 26.1311 | 38.217
0.61946 | 8.6518 | 8.2151 | 5.2341 | 12.8467 | 12.2316 | 8.6518 | 13.8859 | 26.7325 | 38.9642
-2.2832 | 10.3843 | 6.9086 | 6.0868 | 8.5804 | 13.7486 | 10.3843 | 16.4711 | 25.0515 | 38.8001
-1.3577 | 9.5103 | 7.5311 | 4.9357 | 7.0834 | 9.4015 | 9.5103 | 14.446 | 21.5293 | 30.9309
-2.4285 | 8.3321 | 10.5938 | 8.5909 | 6.4012 | 8.9322 | 8.3321 | 16.923 | 23.3242 | 32.2564
2.4706 | 9.8572 | 6.1015 | 4.8349 | 8.2584 | 13.1972 | 9.8572 | 14.6921 | 22.9506 | 36.1478
7.1473 | 8.8251 | 6.2137 | 8.2807 | 6.3848 | 16.017 | 8.8251 | 17.1058 | 23.4906 | 39.5077
3.8921 | 10.5878 | 6.3344 | 8.5528 | 10.158 | 12.7905 | 10.5878 | 19.1405 | 29.2985 | 42.089
-0.12846 | 10.487 | 5.7193 | 5.7599 | 9.3045 | 2.8192 | 10.487 | 16.2469 | 25.5514 | 28.3706
9.7914 | 9.4898 | 8.6039 | 8.2336 | 12.4125 | 12.651 | 9.7914 | 18.025 | 30.4375 | 43.0884
11.4146 | 10.3236 | 8.6827 | 6.0037 | 10.1607 | 6.928 | 11.4146 | 17.4182 | 27.579 | 34.507
11.3309 | 11.2876 | 7.7986 | 6.5128 | 10.6656 | 15.7745 | 11.3309 | 17.8438 | 28.5094 | 44.2839
-0.52495 | 9.7493 | 8.4545 | 6.1089 | 5.7994 | 9.9098 | 9.7493 | 15.8582 | 21.6576 | 31.5675
13.9264 | 9.1496 | 5.5495 | 10.3095 | 12.6963 | 16.1075 | 13.9264 | 24.2359 | 36.9322 | 53.0397
-0.08772 | 9.7345 | 10.1338 | 8.0092 | 15.7546 | 11.688 | 9.7345 | 17.7436 | 33.4983 | 45.1863
5.1853 | 7.3691 | 7.7634 | 6.8282 | 6.2943 | 12.1475 | 7.3691 | 14.1973 | 20.4916 | 32.6391
6.1038 | 10.1198 | 4.6226 | 5.8196 | 9.3971 | 19.6464 | 10.1198 | 15.9394 | 25.3364 | 44.9828
5.4297 | 8.9646 | 5.0502 | 6.1988 | 16.9884 | 9.0174 | 8.9646 | 15.1634 | 32.1518 | 41.1692
-0.05993 | 7.6919 | 8.1151 | 7.8398 | 8.6209 | 8.564 | 7.6919 | 15.5316 | 24.1526 | 32.7166
12.2768 | 9.2201 | 5.6655 | 5.9041 | 9.876 | 10.3972 | 12.2768 | 18.1809 | 28.057 | 38.4541
-12.3967 | 9.3517 | 10.6444 | 6.4091 | 9.6982 | 12.5538 | 9.3517 | 15.7608 | 25.459 | 38.0128
14.9535 | 6.9957 | 4.723 | 3.7428 | 5.2897 | 9.7108 | 14.9535 | 18.6963 | 23.9859 | 33.6967
5.1706 | 8.877 | 7.6575 | 9.2343 | 5.5368 | 7.931 | 8.877 | 18.1113 | 23.6481 | 31.5791
0.47622 | 10.6057 | 11.0913 | 3.8549 | 12.1994 | 12.1109 | 10.6057 | 14.4606 | 26.66 | 38.7709
7.1753 | 9.251 | 6.2271 | 5.8507 | 7.0105 | 10.9704 | 9.251 | 15.1017 | 22.1122 | 33.0826
-3.388 | 9.7941 | 7.7311 | 6.6787 | 12.2323 | 14.4403 | 9.7941 | 16.4728 | 28.7051 | 43.1454
0.7784 | 8.9013 | 9.2268 | 9.3895 | 6.8896 | 11.874 | 8.9013 | 18.2907 | 25.1803 | 37.0543
5.8278 | 9.1194 | 7.7326 | 8.4441 | 10.5956 | 7.1303 | 9.1194 | 17.5636 | 28.1592 | 35.2894
7.3603 | 8.5706 | 8.7946 | 5.5737 | 4.2891 | 11.8129 | 8.5706 | 14.1443 | 18.4334 | 30.2463
7.1379 | 8.3338 | 10.7903 | 4.0824 | 11.1178 | 12.056 | 8.3338 | 12.4162 | 23.534 | 35.59
-0.43424 | 10.7205 | 7.6649 | 6.1074 | 7.5195 | 13.8232 | 10.7205 | 16.8279 | 24.3474 | 38.1705
-7.9482 | 9.8224 | 6.6074 | 6.9238 | 9.4658 | 14.256 | 9.8224 | 16.7462 | 26.212 | 40.468
5.7835 | 9.4053 | 4.8031 | 4.1324 | 12.274 | 8.446 | 9.4053 | 13.5377 | 25.8117 | 34.2578
-0.59313 | 8.9281 | 10.1589 | 5.4651 | 9.9403 | 12.1197 | 8.9281 | 14.3931 | 24.3335 | 36.4531
0.60309 | 9.5284 | 9.5093 | 4.1342 | 7.1667 | 15.3591 | 9.5284 | 13.6625 | 20.8292 | 36.1883
1.0787 | 8.1877 | 8.9233 | 6.1043 | 12.1921 | 9.4681 | 8.1877 | 14.292 | 26.484 | 35.9521
13.3597 | 11.7365 | 6.3493 | 10.9382 | 11.1316 | 10.9682 | 13.3597 | 24.2978 | 35.4294 | 46.3977
9.5457 | 9.8838 | 7.9642 | 8.1484 | 13.6999 | 8.485 | 9.8838 | 18.0322 | 31.7321 | 40.2171
3.7039 | 8.9025 | 8.3819 | 4.2782 | 10.4725 | 20.4188 | 8.9025 | 13.1807 | 23.6532 | 44.072
-1.4513 | 9.3943 | 11.5859 | 6.5251 | 8.0623 | 15.5428 | 9.3943 | 15.9194 | 23.9817 | 39.5246
-3.6095 | 8.7868 | 8.9133 | 4.9327 | 14.9035 | 8.7086 | 8.7868 | 13.7195 | 28.6231 | 37.3316
7.5961 | 10.661 | 6.1867 | 12.2038 | 10.6111 | 12.7243 | 10.661 | 22.8648 | 33.476 | 46.2002
2.2393 | 8.402 | 10.3643 | 4.4029 | 15.4501 | 13.4278 | 8.402 | 12.8049 | 28.255 | 41.6827
7.2808 | 8.7998 | 5.0295 | 4.3165 | 15.2221 | 7.4745 | 8.7998 | 13.1163 | 28.3384 | 35.8129
9.6534 | 8.5972 | 7.1504 | 9.498 | 6.7155 | 11.3871 | 9.6534 | 19.1514 | 25.8669 | 37.254
3.4709 | 9.5872 | 8.7401 | 5.5957 | 6.7453 | 8.9287 | 9.5872 | 15.183 | 21.9282 | 30.8569
9.6599 | 10.4412 | 7.1108 | 6.8301 | 13.2016 | 18.225 | 10.4412 | 17.2713 | 30.4729 | 48.6979
6.8503 | 9.0846 | 9.1109 | 7.6241 | 10.5356 | 14.3201 | 9.0846 | 16.7087 | 27.2443 | 41.5643
-7.8404 | 8.272 | 9.8587 | 5.7461 | 7.0942 | 9.8597 | 8.272 | 14.0181 | 21.1123 | 30.972
4.7529 | 7.476 | 5.5781 | 8.3035 | 7.9344 | 12.0802 | 7.476 | 15.7795 | 23.7138 | 35.7941
-2.1527 | 9.1407 | 8.0186 | 8.3544 | 4.1246 | 14.5636 | 9.1407 | 17.4952 | 21.6198 | 36.1834
-4.6334 | 10.6974 | 10.2383 | 8.9909 | 11.2315 | 5.9132 | 10.6974 | 19.6883 | 30.9198 | 36.833
6.9525 | 10.0546 | 6.1117 | 11.4149 | 9.8122 | 15.2829 | 10.0546 | 21.4695 | 31.2817 | 46.5646
7.4733 | 8.553 | 4.0612 | 8.2754 | 18.5133 | 18.0375 | 8.553 | 16.8284 | 35.3417 | 53.3792
7.8665 | 8.6261 | 3.375 | 5.4863 | 12.8143 | 14.9313 | 8.6261 | 14.1125 | 26.9268 | 41.858
-10.2385 | 10.0417 | 7.3513 | 6.632 | 17.984 | 9.8089 | 10.0417 | 16.6737 | 34.6577 | 44.4666
5.2282 | 8.6895 | 5.9247 | 9.1312 | 10.6852 | 6.1397 | 8.6895 | 17.8207 | 28.5059 | 34.6456
-2.0951 | 8.9026 | 6.8093 | 7.1891 | 11.1582 | 12.9912 | 8.9026 | 16.0917 | 27.2499 | 40.2411
-10.1614 | 9.3349 | 7.7544 | 6.7375 | 7.5137 | 9.5293 | 9.3349 | 16.0724 | 23.5861 | 33.1154
3.5217 | 6.6708 | 5.2837 | 10.773 | 7.4621 | 16.5569 | 6.6708 | 17.4438 | 24.9059 | 41.4628
-17.0077 | 9.8127 | 8.9103 | 5.7746 | 2.0016 | 15.6078 | 9.8127 | 15.5873 | 18.723 | 34.3308
9.8058 | 10.5522 | 15.0781 | 7.4246 | 9.8901 | 11.9554 | 10.5522 | 17.9768 | 27.8669 | 39.8223
8.9744 | 8.8105 | 8.6108 | 6.68 | 13.3577 | 13.7166 | 8.9744 | 15.6544 | 29.0121 | 42.7287
2.2576 | 9.1059 | 9.1843 | 5.8992 | 10.4791 | 12.5217 | 9.1059 | 15.0052 | 25.4842 | 38.0059
-1.0245 | 9.1762 | 8.9615 | 5.7854 | 11.3971 | 13.0465 | 9.1762 | 14.9616 | 26.3587 | 39.4051
1.6296 | 9.3603 | 5.4177 | 7.8363 | 11.7324 | 14.2943 | 9.3603 | 17.1966 | 28.929 | 43.2233
9.2436 | 8.1045 | 8.2566 | 6.8263 | 11.1857 | 11.2467 | 9.2436 | 16.0699 | 27.2557 | 38.5024
4.2623 | 9.3401 | 7.1997 | 10.3348 | 7.5744 | 11.2182 | 9.3401 | 19.6749 | 27.2493 | 38.4675
13.6747 | 9.2027 | 7.8255 | 3.2423 | 7.3924 | 14.894 | 13.6747 | 16.917 | 24.3094 | 39.2034
5.1721 | 8.9406 | 6.7367 | 6.818 | 6.0591 | 10.0821 | 8.9406 | 15.7586 | 21.8176 | 31.8997
10.284 | 8.8172 | 9.8835 | 4.3166 | 16.5497 | 15.3925 | 10.284 | 14.6006 | 31.1503 | 46.5427
0.62186 | 8.6491 | 9.0574 | 3.34 | 6.6836 | 14.4911 | 8.6491 | 11.989 | 18.6727 | 33.1638
8.2262 | 10.4837 | 10.4507 | 4.58 | 7.8471 | 11.317 | 10.4837 | 15.0637 | 22.9107 | 34.2277
9.3591 | 7.9881 | 7.9803 | 7.4932 | 11.0053 | 18.2569 | 9.3591 | 16.8523 | 27.8576 | 46.1144
-3.5631 | 9.247 | 7.2199 | 6.0037 | 15.8212 | 17.3977 | 9.247 | 15.2508 | 31.072 | 48.4697
0.65855 | 8.1756 | 4.9883 | 7.7424 | 7.9659 | 8.4836 | 8.1756 | 15.918 | 23.8839 | 32.3675
7.6672 | 8.0825 | 5.3904 | 6.3704 | 12.5505 | 11.8694 | 8.0825 | 14.4529 | 27.0034 | 38.8728
4.708 | 7.1751 | 5.8385 | 3.4724 | 11.508 | 13.4875 | 7.1751 | 10.6475 | 22.1555 | 35.643
-9.2498 | 9.1068 | 7.2094 | 7.1537 | 7.6903 | 13.4143 | 9.1068 | 16.2606 | 23.9509 | 37.3652
10.3135 | 9.1207 | 7.0799 | 6.3311 | 3.9128 | 9.401 | 10.3135 | 16.6445 | 20.5574 | 29.9584
-7.1147 | 10.0777 | 6.4256 | 3.2637 | 12.0208 | 10.6136 | 10.0777 | 13.3414 | 25.3622 | 35.9758
6.9652 | 6.9739 | 6.9978 | 9.0566 | 10.1619 | 14.1531 | 6.9739 | 16.0305 | 26.1924 | 40.3455
10.3489 | 8.5485 | 12.8478 | 9.6492 | 6.7188 | 12.4319 | 10.3489 | 19.9981 | 26.7169 | 39.1488
-4.2967 | 7.7478 | 11.904 | 8.8942 | 7.7514 | 11.6692 | 7.7478 | 16.642 | 24.3934 | 36.0626
0.018473 | 10.3923 | 11.2043 | 7.3941 | 8.9181 | 13.8139 | 10.3923 | 17.7863 | 26.7044 | 40.5183
5.8056 | 7.8653 | 11.2427 | 4.1987 | 12.3849 | 11.9458 | 7.8653 | 12.064 | 24.4489 | 36.3947
3.2624 | 8.8102 | 5.8 | 8.0381 | 11.7199 | 10.7845 | 8.8102 | 16.8483 | 28.5682 | 39.3527
9.1484 | 9.6298 | 4.7744 | 6.9043 | 13.8674 | 10.5677 | 9.6298 | 16.534 | 30.4015 | 40.9692
7.2413 | 9.7773 | 7.4252 | 8.4001 | 10.7422 | 14.6685 | 9.7773 | 18.1774 | 28.9196 | 43.5881
7.1281 | 10.9589 | 9.588 | 7.0999 | 10.2467 | 10.5351 | 10.9589 | 18.0588 | 28.3055 | 38.8406
5.8199 | 9.7217 | 4.2314 | 6.2448 | 8.4724 | 16.5646 | 9.7217 | 15.9664 | 24.4389 | 41.0034
3.435 | 8.3011 | 6.3764 | 6.7709 | 8.4566 | 10.1424 | 8.3011 | 15.0721 | 23.5287 | 33.6711
12.2896 | 9.5205 | 7.801 | 5.7442 | 8.1832 | 12.0245 | 12.2896 | 18.0338 | 26.217 | 38.2414
-1.1384 | 9.9873 | 7.6728 | 6.6991 | 15.4831 | 9.3336 | 9.9873 | 16.6863 | 32.1694 | 41.503
11.0193 | 8.5678 | 7.098 | 6.4943 | 15.106 | 15.2256 | 11.0193 | 17.5135 | 32.6196 | 47.8451
-4.2848 | 9.3012 | 5.6575 | 9.3297 | 7.0192 | 14.313 | 9.3012 | 18.6309 | 25.6501 | 39.963
-6.368 | 8.2513 | 7.6363 | 8.7384 | 10.4732 | 11.6597 | 8.2513 | 16.9897 | 27.4629 | 39.1226
5.8127 | 9.4866 | 10.1507 | 8.7723 | 11.9801 | 12.6284 | 9.4866 | 18.259 | 30.2391 | 42.8675
17.0136 | 7.5982 | 7.0678 | 5.4258 | 11.6761 | 13.9709 | 17.0136 | 22.4395 | 34.1156 | 48.0864
-1.1175 | 9.405 | 11.3321 | 8.7242 | 10.1518 | 7.5048 | 9.405 | 18.1292 | 28.281 | 35.7859
-0.67631 | 9.4048 | 9.3871 | 4.5743 | 11.6437 | 10.8068 | 9.4048 | 13.979 | 25.6227 | 36.4295
20.283 | 7.7764 | 6.7474 | 6.0426 | 9.1775 | 10.3284 | 20.283 | 26.3256 | 35.5031 | 45.8315
3.3203 | 7.9152 | 7.176 | 5.6612 | 5.0172 | 8.0871 | 7.9152 | 13.5765 | 18.5936 | 26.6807
-5.9206 | 8.8431 | 5.9055 | 3.1252 | 12.7178 | 12.2355 | 8.8431 | 11.9683 | 24.686 | 36.9216
6.6041 | 9.9669 | 10.2664 | 8.7488 | 14.005 | 11.2194 | 9.9669 | 18.7157 | 32.7207 | 43.9401
-1.4922 | 9.007 | 6.2346 | 8.5024 | 10.7579 | 10.8288 | 9.007 | 17.5094 | 28.2673 | 39.0962
2.0897 | 9.4241 | 7.804 | 5.1284 | 9.8339 | 17.0343 | 9.4241 | 14.5525 | 24.3864 | 41.4207
4.9119 | 10.2556 | 8.3336 | 2.7838 | 10.1735 | 13.8671 | 10.2556 | 13.0394 | 23.2129 | 37.08
-3.4532 | 8.6561 | 10.1716 | 6.101 | 6.9583 | 19.6067 | 8.6561 | 14.7572 | 21.7154 | 41.3221
-11.3494 | 9.0676 | 7.7725 | 5.3347 | 8.5681 | 13.2414 | 9.0676 | 14.4023 | 22.9704 | 36.2118
-2.4303 | 8.3431 | 8.3272 | 8.6688 | 11.1534 | 15.4153 | 8.3431 | 17.0119 | 28.1653 | 43.5806
-12.9816 | 7.7685 | 8.075 | 7.3222 | 8.0263 | 12.9255 | 7.7685 | 15.0907 | 23.117 | 36.0426
-1.6426 | 7.8413 | 9.4667 | 4.8768 | 12.9009 | 13.6434 | 7.8413 | 12.7181 | 25.619 | 39.2624
4.4732 | 7.5636 | 6.0176 | 8.5703 | 14.2528 | 14.7431 | 7.5636 | 16.1339 | 30.3867 | 45.1297
-12.672 | 7.548 | 7.7645 | 7.1432 | 9.7024 | 10.1467 | 7.548 | 14.6912 | 24.3937 | 34.5404
3.6516 | 8.154 | 9.569 | 5.0721 | 10.1168 | 11.7558 | 8.154 | 13.2261 | 23.3429 | 35.0987
-6.1434 | 10.8168 | 7.2792 | 8.1049 | 9.3238 | 10.6696 | 10.8168 | 18.9217 | 28.2455 | 38.9151
-4.0802 | 7.7665 | 6.3402 | 6.7583 | 14.9452 | 13.792 | 7.7665 | 14.5248 | 29.4699 | 43.2619
2.1544 | 9.9304 | 10.036 | 3.7244 | 12.2005 | 12.9176 | 9.9304 | 13.6549 | 25.8553 | 38.7729
-8.949 | 9.6957 | 13.8493 | 7.9574 | 15.7289 | 13.7025 | 9.6957 | 17.6531 | 33.3821 | 47.0846
4.2971 | 9.4154 | 4.0266 | 9.1165 | 13.81 | 16.3174 | 9.4154 | 18.532 | 32.3419 | 48.6593
-3.679 | 9.6832 | 8.5033 | 7.356 | 15.3826 | 12.1653 | 9.6832 | 17.0391 | 32.4218 | 44.5871
10.22 | 8.9409 | 6.5341 | 7.4052 | 9.2422 | 14.2614 | 10.22 | 17.6252 | 26.8674 | 41.1288
3.9217 | 8.3816 | 8.8318 | 8.1083 | 11.2951 | 10.8473 | 8.3816 | 16.4899 | 27.785 | 38.6323
9.2402 | 7.8728 | 10.1546 | 6.3744 | 10.4284 | 8.8509 | 9.2402 | 15.6146 | 26.043 | 34.8939
6.9783 | 6.7912 | 8.9999 | 10.4621 | 11.1987 | 11.2218 | 6.9783 | 17.4404 | 28.6391 | 39.8609
-0.53323 | 8.8902 | 12.0261 | 8.6654 | 13.5837 | 12.8922 | 8.8902 | 17.5556 | 31.1392 | 44.0314
2.2051 | 9.5901 | 7.16 | 6.3142 | 7.4703 | 12.0579 | 9.5901 | 15.9043 | 23.3746 | 35.4325
4.9195 | 10.1396 | 4.5554 | 7.7893 | 13.3626 | 14.4412 | 10.1396 | 17.9289 | 31.2915 | 45.7327
5.3197 | 9.6553 | 7.7932 | 6.6513 | 9.4943 | 15.1054 | 9.6553 | 16.3066 | 25.8009 | 40.9063
0.4068 | 8.367 | 7.8558 | 5.4698 | 11.1779 | 15.718 | 8.367 | 13.8367 | 25.0147 | 40.7327
6.8387 | 8.4817 | 7.4772 | 8.8499 | 6.3035 | 11.1335 | 8.4817 | 17.3316 | 23.6351 | 34.7686
5.0778 | 9.7531 | 8.6179 | 9.2265 | 18.2138 | 12.205 | 9.7531 | 18.9796 | 37.1934 | 49.3984
8.8286 | 10.0963 | 7.786 | 11.158 | 4.9954 | 9.725 | 10.0963 | 21.2542 | 26.2496 | 35.9746
1.5765 | 7.8057 | 7.8306 | 9.2106 | 11.0822 | 17.0273 | 7.8057 | 17.0163 | 28.0985 | 45.1258
4.263 | 9.1471 | 7.2336 | 5.9646 | 11.6588 | 15.4198 | 9.1471 | 15.1117 | 26.7705 | 42.1903
4.9646 | 8.24 | 9.3813 | 6.3525 | 8.4576 | 15.8644 | 8.24 | 14.5926 | 23.0502 | 38.9146
0.69325 | 9.5841 | 4.9877 | 5.5021 | 7.5966 | 12.9524 | 9.5841 | 15.0862 | 22.6828 | 35.6352
4.5451 | 10.3154 | 7.7966 | 6.1392 | 5.8634 | 15.9408 | 10.3154 | 16.4546 | 22.3181 | 38.2589
3.6778 | 7.4605 | 9.9027 | 6.2583 | 8.3074 | 16.0347 | 7.4605 | 13.7188 | 22.0262 | 38.0608
-0.85575 | 8.4614 | 9.3082 | 9.7912 | 13.9034 | 12.9334 | 8.4614 | 18.2526 | 32.156 | 45.0893
5.0467 | 8.8962 | 8.5106 | 7.6545 | 8.4361 | 11.1784 | 8.8962 | 16.5507 | 24.9868 | 36.1653
0.42102 | 9.8463 | 10.8102 | 5.2914 | 8.0975 | 21.1271 | 9.8463 | 15.1377 | 23.2352 | 44.3623
-4.4133 | 9.1094 | 7.7604 | 3.2464 | 15.1303 | 10.1657 | 9.1094 | 12.3557 | 27.4861 | 37.6518
-12.2194 | 8.6863 | 5.305 | 8.4443 | 12.8753 | 12.765 | 8.6863 | 17.1305 | 30.0059 | 42.7709
2.2876 | 10.186 | 6.9594 | 7.6086 | 16.0767 | 4.9805 | 10.186 | 17.7946 | 33.8713 | 38.8518
6.0706 | 11.2817 | 6.0536 | 7.7388 | 7.9842 | 8.6284 | 11.2817 | 19.0205 | 27.0047 | 35.6331
-1.1181 | 10.0907 | 4.6662 | 5.145 | 8.9094 | 15.4453 | 10.0907 | 15.2357 | 24.1451 | 39.5903
4.532 | 9.1977 | 9.9021 | 2.7663 | 10.8537 | 11.8001 | 9.1977 | 11.964 | 22.8178 | 34.6178
-2.9873 | 9.5995 | 8.0849 | 1.4856 | 7.3979 | 16.787 | 9.5995 | 11.0851 | 18.4829 | 35.2699
2.9506 | 10.0332 | 5.7485 | 11.3445 | 10.2375 | 15.2688 | 10.0332 | 21.3776 | 31.6151 | 46.8839
-0.6585 | 8.2184 | 6.3838 | 5.6742 | 11.2969 | 12.8751 | 8.2184 | 13.8926 | 25.1895 | 38.0646
-9.446 | 9.7612 | 6.7274 | 9.0213 | 8.7623 | 7.583 | 9.7612 | 18.7825 | 27.5449 | 35.1279
-2.1706 | 9.6565 | 7.1763 | 7.2213 | 12.9613 | 10.5281 | 9.6565 | 16.8778 | 29.8392 | 40.3673
0.57263 | 9.6875 | 6.5661 | 10.3063 | 11.5403 | 8.9055 | 9.6875 | 19.9938 | 31.534 | 40.4396
-0.67316 | 8.3127 | 7.3892 | 10.2721 | 10.3427 | 11.7983 | 8.3127 | 18.5848 | 28.9275 | 40.7258
-3.4448 | 9.7032 | 4.675 | 5.7437 | 12.0852 | 17.2223 | 9.7032 | 15.4469 | 27.5321 | 44.7544
-2.7407 | 7.9191 | 6.1369 | 2.0562 | 8.706 | 9.9142 | 7.9191 | 9.9753 | 18.6813 | 28.5955
12.3216 | 10.2544 | 7.3942 | 10.0913 | 10.7351 | 12.7944 | 12.3216 | 22.4129 | 33.148 | 45.9424
1.4581 | 9.9421 | 5.0191 | 5.3673 | 7.5103 | 11.9307 | 9.9421 | 15.3094 | 22.8197 | 34.7503
6.3208 | 8.606 | 9.6485 | 6.746 | 12.1755 | 12.7305 | 8.606 | 15.352 | 27.5274 | 40.2579
-2.7612 | 8.8014 | 6.3467 | 5.052 | 7.2687 | 9.3164 | 8.8014 | 13.8534 | 21.1221 | 30.4385
-2.2937 | 9.3184 | 6.5462 | 7.7763 | 6.043 | 3.5338 | 9.3184 | 17.0947 | 23.1377 | 26.6716
-3.3624 | 7.5407 | 9.5629 | 4.5866 | 14.0103 | 8.1905 | 7.5407 | 12.1273 | 26.1376 | 34.3281
3.5012 | 7.4328 | 6.9248 | 5.6576 | 9.7983 | 12.3677 | 7.4328 | 13.0904 | 22.8887 | 35.2564
5.8803 | 9.8096 | 6.2285 | 6.4225 | 5.3002 | 9.9497 | 9.8096 | 16.2321 | 21.5323 | 31.482
3.1079 | 7.6855 | 9.188 | 9.5723 | 15.1571 | 7.28 | 7.6855 | 17.2578 | 32.4149 | 39.695
2.4778 | 9.4716 | 10.1933 | 8.5841 | 10.7016 | 14.6195 | 9.4716 | 18.0557 | 28.7574 | 43.3769
8.4032 | 8.7716 | 8.608 | 7.0318 | 9.8142 | 7.8447 | 8.7716 | 15.8034 | 25.6176 | 33.4623
3.3791 | 7.1138 | 9.7607 | 5.0188 | 10.2636 | 8.9556 | 7.1138 | 12.1326 | 22.3962 | 31.3518
-3.8161 | 7.1532 | 10.2671 | 10.2315 | 14.6101 | 14.1618 | 7.1532 | 17.3847 | 31.9948 | 46.1566
-5.4758 | 8.4731 | 7.5096 | 11.3109 | 13.7184 | 13.7961 | 8.4731 | 19.7841 | 33.5025 | 47.2986
-6.1672 | 9.4245 | 9.0818 | 6.6937 | 12.4586 | 11.4198 | 9.4245 | 16.1182 | 28.5768 | 39.9966
3.6593 | 10.1141 | 10.2201 | 6.9064 | 11.8095 | 14.0852 | 10.1141 | 17.0204 | 28.8299 | 42.9151
1.2229 | 10.4034 | 7.6818 | 8.6703 | 8.0623 | 11.1508 | 10.4034 | 19.0738 | 27.1361 | 38.287
2.3918 | 8.6383 | 5.163 | 4.9561 | 16.5689 | 13.3492 | 8.6383 | 13.5945 | 30.1634 | 43.5126
-6.5404 | 8.8304 | 7.1628 | 6.0645 | 5.6034 | 11.4143 | 8.8304 | 14.8949 | 20.4984 | 31.9127
-0.25533 | 9.6375 | 8.5912 | 3.7621 | 12.7644 | 14.1253 | 9.6375 | 13.3996 | 26.164 | 40.2893
-1.6131 | 8.5918 | 10.8359 | 5.578 | 10.2413 | 11.004 | 8.5918 | 14.1699 | 24.4111 | 35.4151
-3.433 | 10.5476 | 6.9585 | 5.3566 | 7.5635 | 13.0624 | 10.5476 | 15.9042 | 23.4677 | 36.5301
11.7751 | 8.1492 | 7.9427 | 10.5319 | 11.4458 | 10.1388 | 11.7751 | 22.307 | 33.7528 | 43.8916
-4.7018 | 8.3375 | 7.1477 | 7.1216 | 5.3568 | 15.9962 | 8.3375 | 15.4591 | 20.8159 | 36.8121
3.1743 | 7.3528 | 6.8068 | 8.5164 | 10.7038 | 12.3992 | 7.3528 | 15.8692 | 26.573 | 38.9723
1.3081 | 8.5824 | 7.5958 | 6.465 | 7.6639 | 9.378 | 8.5824 | 15.0474 | 22.7112 | 32.0892
12.5304 | 9.1391 | 8.1925 | 3.8547 | 7.1558 | 7.9439 | 12.5304 | 16.3851 | 23.541 | 31.4848
-7.9778 | 7.1209 | 10.1078 | 4.7323 | 7.994 | 7.3287 | 7.1209 | 11.8532 | 19.8473 | 27.1759
0.51152 | 8.0772 | 9.1733 | 7.0551 | 15.088 | 14.0753 | 8.0772 | 15.1323 | 30.2204 | 44.2956
-9.3661 | 8.8349 | 8.17 | 6.2129 | 11.3538 | 16.1319 | 8.8349 | 15.0477 | 26.4015 | 42.5335
9.8099 | 8.7903 | 9.6138 | 5.2016 | 10.4209 | 13.7624 | 9.8099 | 15.0115 | 25.4324 | 39.1948
7.2333 | 9.1224 | 9.6937 | 4.0177 | 7.502 | 9.9702 | 9.1224 | 13.1401 | 20.6421 | 30.6123
5.2166 | 8.905 | 4.4191 | 5.2964 | 11.127 | 11.9348 | 8.905 | 14.2013 | 25.3283 | 37.2632
-7.7185 | 8.8059 | 8.8251 | 7.5475 | 8.7194 | 14.6174 | 8.8059 | 16.3534 | 25.0728 | 39.6902
6.3113 | 8.5548 | 6.6309 | 5.79 | 13.0728 | 15.3654 | 8.5548 | 14.3448 | 27.4176 | 42.783
-11.1744 | 7.7117 | 6.3083 | 6.2331 | 4.0683 | 13.7084 | 7.7117 | 13.9448 | 18.0131 | 31.7215
-2.4724 | 6.2395 | 8.4816 | 4.1557 | 9.9322 | 8.581 | 6.2395 | 10.3952 | 20.3274 | 28.9084
-2.1366 | 9.0029 | 8.3014 | 6.5705 | 4.0077 | 3.9073 | 9.0029 | 15.5734 | 19.581 | 23.4884
-0.9036 | 6.6416 | 5.6237 | 6.6791 | 11.4933 | 13.546 | 6.6416 | 13.3208 | 24.8141 | 38.3601
-8.5585 | 8.3431 | 11.4306 | 6.1691 | 7.8487 | 14.1004 | 8.3431 | 14.5122 | 22.3609 | 36.4613
-1.9963 | 8.444 | 10.0085 | 10.3922 | 9.8182 | 21.7597 | 8.444 | 18.8362 | 28.6544 | 50.4141
11.055 | 10.2109 | 9.2966 | 8.8563 | 8.8925 | 11.3178 | 11.055 | 19.9112 | 28.8037 | 40.1216
13.4719 | 8.371 | 3.6888 | 8.1558 | 8.7405 | 15.5444 | 13.4719 | 21.6277 | 30.3682 | 45.9126
0.87747 | 8.7524 | 7.8763 | 4.253 | 5.6296 | 14.9997 | 8.7524 | 13.0054 | 18.635 | 33.6347
-0.25044 | 8.858 | 5.1027 | 5.223 | 14.5745 | 6.0302 | 8.858 | 14.081 | 28.6555 | 34.6857
-0.097822 | 9.4776 | 11.2301 | 4.8431 | 7.697 | 12.6951 | 9.4776 | 14.3207 | 22.0177 | 34.7128
-6.7173 | 8.4052 | 9.1535 | 10.5228 | 6.0263 | 9.5546 | 8.4052 | 18.928 | 24.9543 | 34.509
-8.0613 | 9.6714 | 8.5048 | 4.0595 | 8.5467 | 11.9331 | 9.6714 | 13.7309 | 22.2776 | 34.2107
-1.4464 | 9.2843 | 6.0216 | 4.235 | 16.9418 | 16.7792 | 9.2843 | 13.5193 | 30.4611 | 47.2403
7.595 | 8.7512 | 8.8134 | 9.0452 | 8.3439 | 18.1588 | 8.7512 | 17.7964 | 26.1403 | 44.2992
5.3987 | 8.877 | 6.0172 | 6.5697 | 12.6267 | 9.5908 | 8.877 | 15.4466 | 28.0733 | 37.6641
7.3777 | 9.2825 | 8.978 | 9.1098 | 4.395 | 13.703 | 9.2825 | 18.3924 | 22.7873 | 36.4904
9.4083 | 10.7995 | 5.9425 | 8.0905 | 10.8083 | 15.8601 | 10.7995 | 18.89 | 29.6983 | 45.5584
15.6847 | 8.7261 | 7.0279 | 5.3397 | 9.7661 | 11.3612 | 15.6847 | 21.0243 | 30.7905 | 42.1517
0.52579 | 9.8119 | 7.6133 | 7.2934 | 8.7175 | 12.1038 | 9.8119 | 17.1053 | 25.8228 | 37.9266
1.9105 | 7.9628 | 5.951 | 6.8949 | 5.7537 | 11.8533 | 7.9628 | 14.8577 | 20.6114 | 32.4647
1.904 | 8.0526 | 5.0114 | 5.7111 | 13.0288 | 14.0633 | 8.0526 | 13.7636 | 26.7924 | 40.8557
-2.7485 | 10.6865 | 6.7149 | 8.0362 | 8.6517 | 14.829 | 10.6865 | 18.7227 | 27.3744 | 42.2034
3.1391 | 8.8847 | 5.3103 | 9.3668 | 9.7965 | 8.5866 | 8.8847 | 18.2514 | 28.048 | 36.6346
8.0447 | 9.9755 | 7.9762 | 5.856 | 5.9072 | 12.8909 | 9.9755 | 15.8315 | 21.7388 | 34.6297
4.2907 | 9.6189 | 9.7284 | 7.188 | 10.0444 | 13.8676 | 9.6189 | 16.8069 | 26.8513 | 40.7189
2.0753 | 9.2715 | 9.9613 | 9.7192 | 12.5197 | 18.8219 | 9.2715 | 18.9908 | 31.5105 | 50.3324
4.4846 | 7.6789 | 11.1124 | 5.2548 | 10.4202 | 18.5067 | 7.6789 | 12.9337 | 23.354 | 41.8606
5.1168 | 10.6152 | 7.7015 | 7.7035 | 11.2638 | 8.5833 | 10.6152 | 18.3186 | 29.5825 | 38.1658
-10.392 | 10.5177 | 8.4917 | 5.086 | 12.4637 | 13.9011 | 10.5177 | 15.6037 | 28.0674 | 41.9685
7.698 | 8.0312 | 8.4333 | 5.1632 | 13.5244 | 11.2468 | 8.0312 | 13.1943 | 26.7187 | 37.9656
4.1477 | 8.1176 | 9.5109 | 8.7738 | 10.2953 | 13.3401 | 8.1176 | 16.8915 | 27.1867 | 40.5269
-1.5857 | 6.3223 | 8.7812 | 7.8523 | 8.9547 | 5.6149 | 6.3223 | 14.1746 | 23.1293 | 28.7442
5.2238 | 8.4613 | 7.407 | 8.4805 | 10.7462 | 15.8531 | 8.4613 | 16.9418 | 27.688 | 43.5411
16.1631 | 9.7801 | 4.7598 | 7.5186 | 8.3203 | 12.7296 | 16.1631 | 23.6817 | 32.002 | 44.7316
4.2108 | 9.1731 | 5.9293 | 8.5123 | 10.5916 | 9.6892 | 9.1731 | 17.6854 | 28.277 | 37.9663
-2.1555 | 9.366 | 6.5918 | 4.2406 | 7.6789 | 9.5234 | 9.366 | 13.6066 | 21.2855 | 30.8089
5.9151 | 9.6737 | 6.9764 | 4.4154 | 5.7246 | 12.3062 | 9.6737 | 14.0892 | 19.8138 | 32.12
-7.5047 | 8.1693 | 9.8834 | 5.6711 | 7.1066 | 13.0442 | 8.1693 | 13.8404 | 20.947 | 33.9911
-11.5274 | 10.9395 | 8.2989 | 7.5537 | 10.19 | 17.8885 | 10.9395 | 18.4932 | 28.6832 | 46.5717
-9.0805 | 8.6433 | 11.3447 | 5.7901 | 12.6151 | 13.0098 | 8.6433 | 14.4333 | 27.0484 | 40.0582
0.50299 | 8.8674 | 6.5683 | 7.3246 | 8.3717 | 11.684 | 8.8674 | 16.1921 | 24.5638 | 36.2478
6.7161 | 8.4431 | 3.5917 | 3.3005 | 9.1383 | 12.416 | 8.4431 | 11.7436 | 20.8818 | 33.2978
10.3572 | 9.1473 | 6.3845 | 8.5065 | 11.2262 | 9.9231 | 10.3572 | 18.8637 | 30.0899 | 40.013
4.9332 | 9.627 | 5.5566 | 6.8224 | 11.1817 | 9.7149 | 9.627 | 16.4494 | 27.6312 | 37.3461
-0.21554 | 10.0481 | 5.3422 | 9.3104 | 14.0297 | 4.9311 | 10.0481 | 19.3585 | 33.3881 | 38.3192
6.2754 | 8.6971 | 6.5631 | 8.8711 | 6.16 | 8.3684 | 8.6971 | 17.5681 | 23.7281 | 32.0965
11.3565 | 7.7267 | 7.3669 | 9.0475 | 8.2344 | 14.316 | 11.3565 | 20.404 | 28.6385 | 42.9545
8.3614 | 8.1526 | 9.6886 | 9.658 | 13.67 | 11.793 | 8.3614 | 18.0195 | 31.6895 | 43.4825
-5.7498 | 7.8628 | 6.3971 | 3.9894 | 6.8796 | 9.6958 | 7.8628 | 11.8522 | 18.7318 | 28.4276
-3.5743 | 9.6821 | 8.0376 | 6.0846 | 10.3226 | 9.3012 | 9.6821 | 15.7667 | 26.0893 | 35.3905
-0.96672 | 9.3406 | 8.6618 | 6.9983 | 5.8781 | 10.4116 | 9.3406 | 16.3389 | 22.217 | 32.6286
1.362 | 9.8899 | 7.0833 | 8.824 | 15.8516 | 12.8335 | 9.8899 | 18.7139 | 34.5655 | 47.399
8.8136 | 10.9482 | 7.5192 | 9.4443 | 9.9374 | 12.9258 | 10.9482 | 20.3925 | 30.33 | 43.2558
4.3898 | 7.8167 | 11.4637 | 6.5993 | 11.335 | 11.1421 | 7.8167 | 14.416 | 25.7511 | 36.8932
-4.2724 | 7.7222 | 3.1328 | 4.9384 | 11.5 | 17.165 | 7.7222 | 12.6606 | 24.1606 | 41.3255
-6.9692 | 10.2197 | 8.6851 | 5.1355 | 8.7029 | 12.67 | 10.2197 | 15.3552 | 24.0581 | 36.7281
-7.5933 | 9.247 | 6.7051 | 5.9494 | 8.7609 | 12.7001 | 9.247 | 15.1964 | 23.9573 | 36.6575
-6.1901 | 9.6451 | 8.3822 | 11.2484 | 13.8205 | 9.3526 | 9.6451 | 20.8936 | 34.7141 | 44.0667
1.6267 | 10.7896 | 6.0764 | 5.329 | 9.587 | 11.8271 | 10.7896 | 16.1187 | 25.7057 | 37.5328
2.8768 | 8.355 | 9.6028 | 6.251 | 9.3052 | 10.6641 | 8.355 | 14.6061 | 23.9113 | 34.5754
9.2689 | 7.2582 | 5.9531 | 4.5302 | 9.802 | 12.5029 | 9.2689 | 13.7991 | 23.6011 | 36.104
-1.956 | 8.1484 | 6.1835 | 6.7803 | 8.3826 | 9.9714 | 8.1484 | 14.9287 | 23.3114 | 33.2827
-4.3123 | 9.1095 | 9.7339 | 7.4798 | 9.4831 | 12.2923 | 9.1095 | 16.5893 | 26.0724 | 38.3647
-0.79064 | 8.1353 | 8.3162 | 8.3776 | 3.0456 | 13.3393 | 8.1353 | 16.5129 | 19.5585 | 32.8978
7.6212 | 7.178 | 7.1106 | 6.1327 | 12.3557 | 10.3274 | 7.6212 | 13.754 | 26.1097 | 36.437
4.4225 | 8.1746 | 5.1313 | 7.4912 | 5.1996 | 8.0468 | 8.1746 | 15.6658 | 20.8654 | 28.9122
9.065 | 7.8803 | 10.5611 | 10.0128 | 12.2008 | 11.4688 | 9.065 | 19.0777 | 31.2786 | 42.7473
3.3247 | 9.3438 | 7.1858 | 11.508 | 10.85 | 10.8775 | 9.3438 | 20.8518 | 31.7017 | 42.5793
10.0674 | 7.6425 | 6.9581 | 7.8245 | 5.9172 | 8.6627 | 10.0674 | 17.8918 | 23.8091 | 32.4717
5.7512 | 8.6902 | 7.4775 | 5.247 | 8.595 | 16.1048 | 8.6902 | 13.9371 | 22.5322 | 38.637
4.6021 | 10.0812 | 8.3825 | 7.4689 | 9.9972 | 7.9916 | 10.0812 | 17.5502 | 27.5473 | 35.5389
5.2733 | 8.9256 | 6.3214 | 5.6629 | 6.6912 | 10.3219 | 8.9256 | 14.5885 | 21.2798 | 31.6016
6.6603 | 8.642 | 7.2733 | 7.3453 | 9.5029 | 12.9701 | 8.642 | 15.9873 | 25.4902 | 38.4602
13.2363 | 9.3783 | 9.0306 | 5.7356 | 9.7788 | 11.2186 | 13.2363 | 18.9719 | 28.7506 | 39.9692
1.8769 | 6.9279 | 8.7474 | 7.9297 | 9.7031 | 12.2215 | 6.9279 | 14.8575 | 24.5607 | 36.7821
10.8946 | 8.9287 | 12.3537 | 6.9654 | 5.2563 | 7.5858 | 10.8946 | 17.86 | 23.2483 | 30.834
0.73205 | 7.3625 | 6.0277 | 7.5395 | 10.1139 | 11.3387 | 7.3625 | 14.9019 | 25.0158 | 36.3545
-9.2009 | 7.7065 | 6.3645 | 6.7515 | 13.974 | 11.3796 | 7.7065 | 14.458 | 28.432 | 39.8116
0.59027 | 9.8757 | 9.4844 | 6.695 | 17.6378 | 13.3788 | 9.8757 | 16.5707 | 34.2085 | 47.5873 | 20% chance that the project will take 30 days or less
1.9673 | 9.936 | 8.2535 | 8.9469 | 9.3465 | 16.1723 | 9.936 | 18.8829 | 28.2294 | 44.4018
10.414 | 9.8285 | 12.2827 | 4.8372 | 9.7877 | 10.8131 | 10.414 | 15.2512 | 25.0389 | 35.852
3.5461 | 8.997 | 4.2761 | 9.8867 | 8.4842 | 11.5951 | 8.997 | 18.8837 | 27.3679 | 38.963
0.16537 | 9.416 | 5.6036 | 7.0051 | 9.612 | 9.897 | 9.416 | 16.4211 | 26.0331 | 35.9301
7.1787 | 8.9432 | 9.8288 | 7.9859 | 11.8891 | 11.2284 | 8.9432 | 16.9291 | 28.8182 | 40.0466
8.5512 | 9.5371 | 8.0332 | 8.0172 | 9.6476 | 15.3976 | 9.5371 | 17.5544 | 27.2019 | 42.5995
13.0615 | 7.7618 | 10.2761 | 5.8984 | 10.9355 | 14.8954 | 13.0615 | 18.9599 | 29.8954 | 44.7907
5.5428 | 7.7385 | 6.466 | 9.9158 | 13.8364 | 9.0988 | 7.7385 | 17.6543 | 31.4907 | 40.5895
-8.0411 | 9.1009 | 7.5491 | 7.6227 | 7.0478 | 13.7354 | 9.1009 | 16.7236 | 23.7714 | 37.5068
7.8507 | 9.8062 | 8.7877 | 11.142 | 12.2848 | 9.9443 | 9.8062 | 20.9482 | 33.233 | 43.1774
-8.1608 | 8.7374 | 7.9465 | 7.7366 | 10.7226 | 13.2728 | 8.7374 | 16.4739 | 27.1965 | 40.4694
0.46553 | 9.3269 | 5.484 | 4.7324 | 4.9572 | 8.9788 | 9.3269 | 14.0593 | 19.0165 | 27.9953
-2.3594 | 10.5658 | 6.3207 | 8.3041 | 11.0581 | 15.2723 | 10.5658 | 18.8699 | 29.928 | 45.2002
2.6416 | 8.7894 | 8.4809 | 7.6519 | 6.7494 | 14.9596 | 8.7894 | 16.4414 | 23.1908 | 38.1503
-4.3345 | 7.6672 | 6.3609 | 10.7476 | 17.4065 | 10.2598 | 7.6672 | 18.4149 | 35.8214 | 46.0811
-5.3008 | 9.2122 | 5.4445 | 8.3085 | 5.8996 | 12.6783 | 9.2122 | 17.5207 | 23.4202 | 36.0985
5.3151 | 9.7213 | 12.6742 | 5.9252 | 11.9073 | 13.4642 | 9.7213 | 15.6465 | 27.5538 | 41.018
13.2975 | 7.6424 | 9.0198 | 6.4825 | 12.6976 | 12.199 | 13.2975 | 19.78 | 32.4777 | 44.6767
-2.6334 | 7.7786 | 12.4204 | 8.5523 | 16.3876 | 6.3138 | 7.7786 | 16.3309 | 32.7185 | 39.0323
-0.1964 | 7.8958 | 7.0906 | 1.3782 | 11.4938 | 13.9441 | 7.8958 | 9.2739 | 20.7677 | 34.7118
6.0369 | 9.6 | 8.0636 | 7.0819 | 7.0541 | 13.2057 | 9.6 | 16.6819 | 23.7359 | 36.9417
-0.28672 | 8.9893 | 9.0092 | 10.3543 | 9.7914 | 11.948 | 8.9893 | 19.3436 | 29.135 | 41.0829
3.8278 | 9.5837 | 9.3005 | 4.9383 | 10.7786 | 9.309 | 9.5837 | 14.522 | 25.3005 | 34.6095
10.0689 | 9.5723 | 10.0719 | 10.7993 | 8.3815 | 15.489 | 10.0689 | 20.8683 | 29.2497 | 44.7387
1.1101 | 8.436 | 5.4636 | 11.0905 | 7.4505 | 12.6178 | 8.436 | 19.5265 | 26.977 | 39.5948
3.6397 | 11.6072 | 7.8928 | 9.3886 | 14.1413 | 12.8218 | 11.6072 | 20.9958 | 35.1371 | 47.959
-1.2911 | 8.4606 | 6.9196 | 5.9823 | 13.0522 | 12.4414 | 8.4606 | 14.4429 | 27.4951 | 39.9365
-5.4752 | 10.2591 | 5.6207 | 6.1434 | 10.9982 | 12.2668 | 10.2591 | 16.4026 | 27.4008 | 39.6676
-0.04253 | 8.3061 | 10.5949 | 5.9686 | 14.9432 | 7.1878 | 8.3061 | 14.2748 | 29.218 | 36.4058
-1.2491 | 10.9563 | 9.4395 | 5.0789 | 11.1808 | 11.7459 | 10.9563 | 16.0352 | 27.216 | 38.9619
2.2725 | 8.2602 | 6.3412 | 4.6086 | 5.0025 | 9.7282 | 8.2602 | 12.8687 | 17.8712 | 27.5994
11.5922 | 9.1873 | 7.0044 | 1.8008 | 10.806 | 9.5709 | 11.5922 | 13.393 | 24.199 | 33.7699
2.8237 | 7.5054 | 8.7548 | 6.675 | 10.5132 | 12.5573 | 7.5054 | 14.1804 | 24.6935 | 37.2509
-4.1902 | 9.1426 | 6.7577 | 8.2945 | 13.4128 | 5.2065 | 9.1426 | 17.4372 | 30.8499 | 36.0564
3.8958 | 9.3356 | 8.5885 | 6.9597 | 11.3132 | 14.9224 | 9.3356 | 16.2953 | 27.6085 | 42.5308
-0.8079 | 7.7757 | 7.9884 | 6.0291 | 9.3689 | 15.3282 | 7.7757 | 13.8048 | 23.1737 | 38.502
2.4872 | 10.3488 | 8.5304 | 2.7446 | 8.9239 | 8.3595 | 10.3488 | 13.0934 | 22.0174 | 30.3769
-0.92071 | 8.3522 | 12.4536 | 6.286 | 5.5784 | 10.6638 | 8.3522 | 14.6382 | 20.8058 | 31.4696
-7.9324 | 9.9271 | 9.9627 | 7.7725 | 13.1576 | 15.6979 | 9.9271 | 17.6996 | 30.8572 | 46.5551
-2.8236 | 8.7775 | 3.6189 | 5.4053 | 10.1638 | 11.2926 | 8.7775 | 14.1828 | 24.3466 | 35.6392
2.9422 | 9.6196 | 7.3852 | 7.3863 | 9.8763 | 6.8784 | 9.6196 | 17.006 | 26.8823 | 33.7607
-5.4423 | 10.3699 | 6.8223 | 7.849 | 6.2409 | 13.6367 | 10.3699 | 18.2189 | 24.4598 | 38.0966
-0.050626 | 8.9795 | 3.8577 | 6.9749 | 9.0501 | 16.7472 | 8.9795 | 15.9544 | 25.0045 | 41.7517
6.265 | 7.8058 | 6.4664 | 6.2391 | 9.1866 | 13.5479 | 7.8058 | 14.0449 | 23.2315 | 36.7793
13.3509 | 10.8531 | 7.0478 | 7.8117 | 10.6972 | 11.4884 | 13.3509 | 21.1626 | 31.8598 | 43.3482
-1.7689 | 8.3374 | 9.3867 | 9.1551 | 12.8238 | 13.1577 | 8.3374 | 17.4925 | 30.3163 | 43.474
-6.3161 | 8.5461 | 6.6608 | 7.8961 | 11.3373 | 9.1829 | 8.5461 | 16.4422 | 27.7795 | 36.9624
7.0838 | 8.6428 | 10.6781 | 5.7348 | 8.1874 | 18.3442 | 8.6428 | 14.3776 | 22.5649 | 40.9092
-2.1051 | 8.8369 | 8.7984 | 7.2832 | 12.4362 | 11.8342 | 8.8369 | 16.1201 | 28.5563 | 40.3905
-5.1945 | 9.0604 | 9.5742 | 8.787 | 12.8353 | 8.6995 | 9.0604 | 17.8474 | 30.6827 | 39.3822
16.0149 | 9.097 | 6.7569 | 6.1248 | 5.1825 | 11.8981 | 16.0149 | 22.1397 | 27.3222 | 39.2203
-4.9334 | 8.1082 | 7.7583 | 6.2925 | 7.4528 | 14.4144 | 8.1082 | 14.4008 | 21.8536 | 36.2681
8.4254 | 9.0525 | 7.0904 | 6.0041 | 10.1351 | 13.9011 | 9.0525 | 15.0566 | 25.1917 | 39.0928
3.5939 | 9.0742 | 5.5671 | 8.1915 | 9.2716 | 11.3498 | 9.0742 | 17.2657 | 26.5373 | 37.8871
11.3493 | 8.9082 | 9.5075 | 8.0428 | 9.5775 | 12.3753 | 11.3493 | 19.3921 | 28.9696 | 41.3448
1.4379 | 9.3707 | 11.2761 | 5.5682 | 8.2725 | 7.2563 | 9.3707 | 14.9389 | 23.2114 | 30.4677
-1.8407 | 8.833 | 9.9505 | 8.2246 | 10.783 | 12.1732 | 8.833 | 17.0576 | 27.8406 | 40.0138
0.90578 | 10.3394 | 8.6368 | 5.8447 | 13.0641 | 10.9719 | 10.3394 | 16.184 | 29.2482 | 40.2201
1.303 | 9.3591 | 9.6665 | 5.7197 | 9.9342 | 15.6654 | 9.3591 | 15.0788 | 25.013 | 40.6784
-0.5806 | 9.5501 | 6.2203 | 5.1879 | 9.4842 | 10.2019 | 9.5501 | 14.738 | 24.2222 | 34.4241
-3.817 | 9.9163 | 5.7828 | 7.0321 | 9.2324 | 17.5731 | 9.9163 | 16.9483 | 26.1807 | 43.7538
0.81951 | 9.4161 | 9.7789 | 10.9003 | 9.2805 | 14.5097 | 9.4161 | 20.3164 | 29.5969 | 44.1067
6.3318 | 9.85 | 5.1301 | 4.6112 | 11.4812 | 14.7745 | 9.85 | 14.4612 | 25.9424 | 40.717
5.173 | 10.577 | 7.7262 | 6.2683 | 8.0228 | 10.8628 | 10.577 | 16.8453 | 24.8681 | 35.7309
6.7906 | 8.6799 | 8.0818 | 11.8641 | 9.9366 | 12.0355 | 8.6799 | 20.544 | 30.4806 | 42.5161
5.0597 | 6.6319 | 9.3031 | 8.9952 | 13.9214 | 15.2163 | 6.6319 | 15.627 | 29.5484 | 44.7647
-3.2395 | 8.2693 | 10.1973 | 7.6901 | 10.096 | 7.9046 | 8.2693 | 15.9594 | 26.0554 | 33.96
2.5578 | 8.444 | 10.5501 | 2.7999 | 16.348 | 9.6306 | 8.444 | 11.2439 | 27.5919 | 37.2225
11.775 | 10.898 | 5.1964 | 5.299 | 9.0875 | 12.445 | 11.775 | 17.074 | 26.1615 | 38.6065
-5.4108 | 8.0233 | 9.1406 | 8.6865 | 5.6463 | 11.3119 | 8.0233 | 16.7098 | 22.356 | 33.6679
5.642 | 8.7566 | 9.4817 | 4.9513 | 13.715 | 15.559 | 8.7566 | 13.708 | 27.423 | 42.982
6.8978 | 8.9343 | 8.0237 | 8.6482 | 8.6199 | 6.9431 | 8.9343 | 17.5825 | 26.2025 | 33.1456
-2.7778 | 8.743 | 5.3197 | 7.6027 | 9.6585 | 18.6535 | 8.743 | 16.3457 | 26.0041 | 44.6576
4.965 | 10.1184 | 7.1751 | 9.4882 | 12.3941 | 13.9793 | 10.1184 | 19.6066 | 32.0007 | 45.98
7.0964 | 8.8277 | 7.1431 | 5.5588 | 11.8832 | 9.3151 | 8.8277 | 14.3864 | 26.2697 | 35.5848
-5.8464 | 9.609 | 5.5917 | 5.6532 | 11.8937 | 6.9964 | 9.609 | 15.2623 | 27.156 | 34.1524
6.4061 | 8.0007 | 7.9957 | 7.6409 | 16.4743 | 9.7248 | 8.0007 | 15.6417 | 32.1159 | 41.8407
0.02792 | 8.9121 | 11.4272 | 3.9962 | 6.8993 | 12.4796 | 8.9121 | 12.9083 | 20.3393 | 32.8189
5.7788 | 10.1507 | 6.7144 | 7.8697 | 8.8334 | 14.4215 | 10.1507 | 18.0204 | 26.8538 | 41.2753
-9.5731 | 8.0482 | 9.8419 | 10.3515 | 9.0084 | 8.3616 | 8.0482 | 18.3997 | 27.4081 | 35.7697
4.8835 | 8.8455 | 7.3552 | 8.9344 | 13.7134 | 12.4707 | 8.8455 | 17.7799 | 31.4933 | 43.964
16.3479 | 8.7652 | 9.3119 | 11.0142 | 11.1914 | 9.68 | 16.3479 | 27.3621 | 38.5535 | 48.2336
10.5932 | 9.874 | 8.0764 | 3.4905 | 3.7247 | 15.9038 | 10.5932 | 14.0837 | 18.6696 | 34.5734
11.9587 | 10.399 | 8.7583 | 6.6426 | 9.0727 | 13.5226 | 11.9587 | 18.6013 | 27.674 | 41.1966
-2.8649 | 7.9146 | 4.7578 | 8.4928 | 9.6358 | 14.8345 | 7.9146 | 16.4074 | 26.0433 | 40.8778
-3.4572 | 8.1651 | 7.3325 | 8.5679 | 10.8614 | 16.7797 | 8.1651 | 16.733 | 27.5944 | 44.3741
-9.536 | 8.0465 | 8.0081 | 7.4118 | 10.5976 | 10.6254 | 8.0465 | 15.4583 | 26.056 | 36.6814
-3.7404 | 8.2251 | 9.3951 | 6.1624 | 9.7112 | 11.8776 | 8.2251 | 14.3875 | 24.0987 | 35.9763
-0.99161 | 8.0209 | 7.5078 | 6.6326 | 4.8005 | 16.7474 | 8.0209 | 14.6535 | 19.454 | 36.2014
8.7757 | 8.2043 | 4.6478 | 8.2139 | 4.6941 | 15.0411 | 8.7757 | 16.9896 | 21.6836 | 36.7248
-0.14226 | 10.066 | 8.5084 | 6.5276 | 11.309 | 14.9879 | 10.066 | 16.5937 | 27.9027 | 42.8907
0.80052 | 8.1488 | 9.4396 | 6.9036 | 16.3254 | 8.1515 | 8.1488 | 15.0524 | 31.3778 | 39.5293
11.6557 | 9.2903 | 8.2958 | 6.2011 | 15.0097 | 16.6491 | 11.6557 | 17.8568 | 32.8664 | 49.5155
-3.9354 | 7.9472 | 8.0978 | 8.115 | 7.1603 | 11.0407 | 7.9472 | 16.0622 | 23.2225 | 34.2632
2.5833 | 9.0861 | 7.47 | 8.0267 | 10.5796 | 11.1725 | 9.0861 | 17.1129 | 27.6925 | 38.865
-0.048655 | 8.3871 | 7.2787 | 5.5063 | 16.3185 | 10.0324 | 8.3871 | 13.8934 | 30.2119 | 40.2443
7.9901 | 8.64 | 10.044 | 10.3826 | 8.161 | 14.9639 | 8.64 | 19.0226 | 27.1836 | 42.1475
5.951 | 9.4301 | 10.5817 | 4.9791 | 13.2797 | 10.268 | 9.4301 | 14.4091 | 27.6888 | 37.9569
0.47229 | 9.4717 | 8.3593 | 4.8901 | 16.8089 | 9.8888 | 9.4717 | 14.3618 | 31.1707 | 41.0595
2.7657 | 9.2963 | 7.9085 | 5.7357 | 12.4249 | 8.3659 | 9.2963 | 15.032 | 27.4569 | 35.8228
8.2566 | 8.505 | 10.9743 | 4.2111 | 11.088 | 9.3027 | 8.505 | 12.7161 | 23.8041 | 33.1068
4.6954 | 8.0452 | 10.3085 | 6.0818 | 12.8316 | 12.5325 | 8.0452 | 14.127 | 26.9586 | 39.4911
-1.2647 | 9.0121 | 8.1208 | 10.6638 | 13.3278 | 11.6178 | 9.0121 | 19.6759 | 33.0037 | 44.6215
1.3264 | 9.3504 | 7.1725 | 5.638 | 11.279 | 11.9396 | 9.3504 | 14.9884 | 26.2673 | 38.2069
-1.2744 | 9.052 | 7.1684 | 4.6213 | 11.6363 | 11.5901 | 9.052 | 13.6733 | 25.3097 | 36.8997
-3.6641 | 8.2104 | 10.5532 | 10.7981 | 7.4932 | 8.7374 | 8.2104 | 19.0085 | 26.5016 | 35.2391
2.8792 | 8.7351 | 8.6935 | 5.9684 | 12.0681 | 8.6643 | 8.7351 | 14.7035 | 26.7716 | 35.4359
2.6815 | 10.1654 | 9.2489 | 6.7084 | 8.7563 | 15.3441 | 10.1654 | 16.8738 | 25.6301 | 40.9742
1.0002 | 9.8486 | 7.7337 | 5.4913 | 9.7555 | 10.1301 | 9.8486 | 15.34 | 25.0954 | 35.2256
0.19803 | 9.0865 | 7.6496 | 3.2478 | 10.3289 | 15.6064 | 9.0865 | 12.3343 | 22.6632 | 38.2696
4.5607 | 7.5606 | 10.3097 | 7.3801 | 4.6691 | 18.0285 | 7.5606 | 14.9407 | 19.6099 | 37.6384
2.9428 | 10.641 | 8.6241 | 4.8989 | 6.0623 | 9.3742 | 10.641 | 15.5399 | 21.6022 | 30.9764
6.3399 | 10.4435 | 7.4038 | 4.5345 | 5.3714 | 10.6561 | 10.4435 | 14.978 | 20.3494 | 31.0055
4.2071 | 10.5051 | 12.9538 | 4.9262 | 10.0797 | 11.1141 | 10.5051 | 15.4313 | 25.511 | 36.6251
0.65261 | 8.3406 | 8.6698 | 5.7205 | 10.0529 | 15.1733 | 8.3406 | 14.0611 | 24.114 | 39.2873
-0.32925 | 9.4993 | 9.1661 | 7.203 | 11.4201 | 12.6921 | 9.4993 | 16.7023 | 28.1224 | 40.8145
1.7341 | 8.9443 | 6.8922 | 8.2704 | 12.0403 | 14.8878 | 8.9443 | 17.2147 | 29.2551 | 44.1429
1.6737 | 7.6397 | 5.3975 | 8.4666 | 7.9306 | 12.3452 | 7.6397 | 16.1063 | 24.0369 | 36.3821
-6.0535 | 10.5639 | 7.049 | 3.9319 | 9.3834 | 10.7442 | 10.5639 | 14.4958 | 23.8793 | 34.6235
2.6304 | 9.6319 | 8.0379 | 7.5149 | 6.7593 | 13.2801 | 9.6319 | 17.1468 | 23.9061 | 37.1862
5.0664 | 9.1967 | 7.5781 | 9.4743 | 8.6968 | 17.0497 | 9.1967 | 18.671 | 27.3678 | 44.4175
4.5886 | 10.529 | 7.1932 | 7.6685 | 12.8303 | 8.531 | 10.529 | 18.1976 | 31.0278 | 39.5589
-12.58 | 12.021 | 7.6496 | 8.1204 | 13.6278 | 10.0925 | 12.021 | 20.1414 | 33.7692 | 43.8617
9.0991 | 9.9411 | 10.4607 | 4.9796 | 6.1946 | 15.2356 | 9.9411 | 14.9207 | 21.1153 | 36.3508
2.9964 | 9.7473 | 6.5152 | 5.4009 | 10.9977 | 10.4528 | 9.7473 | 15.1482 | 26.1459 | 36.5986
8.607 | 8.8769 | 7.884 | 8.9919 | 13.2595 | 14.2972 | 8.8769 | 17.8688 | 31.1283 | 45.4255
-4.8455 | 8.3917 | 10.0064 | 12.1632 | 3.167 | 9.4198 | 8.3917 | 20.5549 | 23.7219 | 33.1417
4.8246 | 7.2514 | 8.3082 | 6.2745 | 6.8357 | 9.5978 | 7.2514 | 13.5259 | 20.3616 | 29.9594
-2.6743 | 8.5341 | 8.2662 | 7.7286 | 13.2566 | 8.0634 | 8.5341 | 16.2627 | 29.5193 | 37.5827
2.2573 | 8.3192 | 6.3462 | 3.1942 | 9.7407 | 8.2618 | 8.3192 | 11.5134 | 21.2541 | 29.5159
12.0279 | 8.3468 | 5.9348 | 6.6402 | 12.1871 | 14.3002 | 12.0279 | 18.6681 | 30.8551 | 45.1553
2.3548 | 8.6745 | 6.2252 | 8.8413 | 5.5612 | 8.9115 | 8.6745 | 17.5158 | 23.0769 | 31.9885
6.7993 | 9.8218 | 5.1506 | 10.6508 | 13.7681 | 10.8795 | 9.8218 | 20.4726 | 34.2407 | 45.1202
6.2071 | 9.2939 | 6.5575 | 4.0104 | 12.2682 | 9.1314 | 9.2939 | 13.3043 | 25.5725 | 34.7039
2.6673 | 8.3495 | 4.5051 | 5.0506 | 11.0713 | 12.6128 | 8.3495 | 13.4001 | 24.4714 | 37.0842
5.0916 | 9.3801 | 11.3902 | 8.665 | 13.9978 | 12.6097 | 9.3801 | 18.0451 | 32.0429 | 44.6526
0.5849 | 8.0272 | 6.5355 | 6.815 | 2.3588 | 14.145 | 8.0272 | 14.8422 | 17.2011 | 31.346
4.5196 | 9.668 | 6.7829 | 5.4318 | 8.3325 | 12.6951 | 9.668 | 15.0999 | 23.4323 | 36.1275
2.8141 | 9.1819 | 8.5599 | 7.8717 | 13.5239 | 10.8381 | 9.1819 | 17.0536 | 30.5774 | 41.4156
1.2887 | 8.1393 | 7.0335 | 10.9041 | 14.6074 | 9.0969 | 8.1393 | 19.0434 | 33.6508 | 42.7477
2.2758 | 8.8748 | 5.5554 | 11.1989 | 4.2217 | 18.1145 | 8.8748 | 20.0737 | 24.2954 | 42.4098
3.5559 | 8.8315 | 6.3768 | 6.14 | 10.386 | 17.5755 | 8.8315 | 14.9715 | 25.3575 | 42.933
9.6867 | 7.5956 | 8.1806 | 9.5884 | 11.8555 | 14.0872 | 9.6867 | 19.2751 | 31.1306 | 45.2178
-12.7572 | 7.8471 | 6.3124 | 5.881 | 12.0437 | 16.7044 | 7.8471 | 13.7281 | 25.7718 | 42.4762
10.1694 | 7.6735 | 6.2283 | 10.0154 | 6.3409 | 7.5063 | 10.1694 | 20.1848 | 26.5257 | 34.032
0.23643 | 6.8039 | 6.6065 | 8.9016 | 9.722 | 11.0137 | 6.8039 | 15.7055 | 25.4275 | 36.4412
5.5365 | 11.5209 | 9.4149 | 6.9039 | 3.8129 | 10.3302 | 11.5209 | 18.4248 | 22.2377 | 32.5679
-3.7661 | 9.34 | 6.9264 | 6.3284 | 7.4749 | 12.0573 | 9.34 | 15.6685 | 23.1433 | 35.2006
-3.6453 | 8.521 | 10.076 | 7.7347 | 16.5747 | 12.0815 | 8.521 | 16.2558 | 32.8304 | 44.9119
-7.2011 | 9.4015 | 4.6228 | 6.5239 | 7.8954 | 12.266 | 9.4015 | 15.9255 | 23.8209 | 36.0869
4.8613 | 7.7303 | 6.1559 | 6.5795 | 11.0889 | 9.8216 | 7.7303 | 14.3098 | 25.3987 | 35.2204
8.515 | 11.6491 | 10.0645 | 4.5024 | 12.7115 | 15.187 | 11.6491 | 16.1515 | 28.863 | 44.0501
3.4905 | 8.1029 | 8.3257 | 6.1282 | 10.8663 | 8.7219 | 8.1029 | 14.2312 | 25.0975 | 33.8194
-2.9283 | 9.2284 | 8.5961 | 9.1951 | 6.4211 | 18.0319 | 9.2284 | 18.4235 | 24.8445 | 42.8764
1.2286 | 9.3018 | 9.4307 | 9.0038 | 17.215 | 9.3094 | 9.3018 | 18.3056 | 35.5206 | 44.83
6.6349 | 10.1273 | 8.3636 | 4.7211 | 6.0176 | 12.5468 | 10.1273 | 14.8484 | 20.866 | 33.4128
10.5873 | 8.3691 | 10.6489 | 8.4257 | 7.9319 | 16.3822 | 10.5873 | 19.0129 | 26.9449 | 43.3271
3.0043 | 10.0226 | 7.4028 | 6.1711 | 11.9235 | 9.2673 | 10.0226 | 16.1937 | 28.1172 | 37.3845
3.4263 | 8.685 | 8.5361 | 3.1106 | 9.1044 | 5.3568 | 8.685 | 11.7955 | 20.9 | 26.2567
1.7294 | 9.6454 | 7.7348 | 6.3374 | 7.4768 | 9.6587 | 9.6454 | 15.9828 | 23.4596 | 33.1183
-2.3513 | 8.061 | 10.7003 | 5.3921 | 5.2752 | 12.9433 | 8.061 | 13.4531 | 18.7614 | 31.7047
1.7716 | 8.5148 | 10.6941 | 6.5224 | 11.5028 | 12.1711 | 8.5148 | 15.0372 | 26.54 | 38.7111
0.053854 | 9.268 | 8.1794 | 6.5218 | 15.8821 | 13.4674 | 9.268 | 15.7898 | 31.6719 | 45.1393
-2.797 | 10.6598 | 5.2131 | 7.4636 | 10.2642 | 19.2838 | 10.6598 | 18.1234 | 28.3876 | 47.6714
-7.6697 | 8.0711 | 10.244 | 13.3609 | 7.699 | 11.183 | 8.0711 | 21.4321 | 29.131 | 40.314
2.8797 | 7.7961 | 7.4561 | 7.7329 | 9.0687 | 13.786 | 7.7961 | 15.5289 | 24.5976 | 38.3836
-9.7643 | 8.0759 | 7.7976 | 7.0624 | 15.1419 | 11.1426 | 8.0759 | 15.1384 | 30.2803 | 41.4229
1.0511 | 7.5401 | 5.7746 | 8.539 | 12.6859 | 20.7418 | 7.5401 | 16.0791 | 28.765 | 49.5069
1.6539 | 9.7562 | 11.2601 | 4.8511 | 9.281 | 4.9728 | 9.7562 | 14.6073 | 23.8883 | 28.8611
-16.5074 | 9.0999 | 9.0312 | 10.1082 | 12.1798 | 5.0686 | 9.0999 | 19.2081 | 31.3879 | 36.4565
-4.7997 | 8.9741 | 7.8951 | 5.4322 | 10.4876 | 10.5793 | 8.9741 | 14.4063 | 24.8939 | 35.4732
2.3832 | 9.9126 | 4.1624 | 6.7165 | 10.8128 | 19.7966 | 9.9126 | 16.6291 | 27.4419 | 47.2385
0.23619 | 9.1655 | 6.7428 | 5.4147 | 6.5492 | 11.2126 | 9.1655 | 14.5803 | 21.1295 | 32.3421
1.4061 | 8.452 | 8.4379 | 7.6215 | 7.587 | 14.0028 | 8.452 | 16.0735 | 23.6606 | 37.6634
8.4823 | 7.8577 | 9.8619 | 4.7029 | 10.8641 | 11.2008 | 8.4823 | 13.1852 | 24.0493 | 35.2501
-1.3649 | 10.043 | 10.9429 | 4.4803 | 8.6908 | 8.0151 | 10.043 | 14.5232 | 23.214 | 31.2291
0.30318 | 8.8306 | 8.8014 | 7.3416 | 11.4337 | 15.4139 | 8.8306 | 16.1722 | 27.6059 | 43.0198
-1.595 | 8.3969 | 10.3487 | 4.8293 | 13.9948 | 16.4018 | 8.3969 | 13.2262 | 27.221 | 43.6228
-7.5556 | 7.6221 | 5.3362 | 5.5418 | 7.6451 | 9.0242 | 7.6221 | 13.1639 | 20.809 | 29.8333
9.5737 | 9.4023 | 12.0112 | 7.7077 | 8.6476 | 12.1905 | 9.5737 | 17.2814 | 25.929 | 38.1195
6.2037 | 7.3031 | 9.0678 | 6.9175 | 7.8109 | 15.7067 | 7.3031 | 14.2206 | 22.0314 | 37.7382
3.0582 | 10.6366 | 7.2389 | 9.8384 | 8.9972 | 13.3617 | 10.6366 | 20.475 | 29.4722 | 42.8339
18.2247 | 8.2849 | 6.0398 | 6.3075 | 8.4946 | 12.4902 | 18.2247 | 24.5322 | 33.0268 | 45.517
1.2364 | 11.9563 | 6.7951 | 7.3156 | 0.16523 | 9.6879 | 11.9563 | 19.2719 | 19.4371 | 29.125
1.6561 | 9.9658 | 8.3822 | 3.8659 | 12.351 | 6.0437 | 9.9658 | 13.8317 | 26.1826 | 32.2264
0.82587 | 11.1022 | 4.8323 | 3.9698 | 7.7724 | 14.2531 | 11.1022 | 15.072 | 22.8443 | 37.0975
5.793 | 8.709 | 8.2964 | 6.017 | 11.9392 | 10.8064 | 8.709 | 14.726 | 26.6652 | 37.4716
-11.6014 | 8.2157 | 8.3918 | 4.7893 | 13.38 | 11.8816 | 8.2157 | 13.0049 | 26.3849 | 38.2664
3.6346 | 8.6947 | 8.2278 | 7.202 | 3.5057 | 15.1478 | 8.6947 | 15.8967 | 19.4024 | 34.5502
8.191 | 10.3314 | 8.8732 | 6.9059 | 10.1176 | 15.5649 | 10.3314 | 17.2373 | 27.3549 | 42.9198
8.5261 | 9.4619 | 7.31 | 5.7181 | 7.802 | 12.6433 | 9.4619 | 15.18 | 22.9821 | 35.6254
1.523 | 9.714 | 7.3144 | 1.192 | 8.3787 | 10.7204 | 9.714 | 10.906 | 19.2847 | 30.0051
-10.0526 | 8.8285 | 7.3007 | 10.6527 | 12.2199 | 5.4423 | 8.8285 | 19.4812 | 31.7011 | 37.1434
1.5307 | 7.2142 | 4.4918 | 5.8311 | 6.8026 | 9.5307 | 7.2142 | 13.0453 | 19.8479 | 29.3786
3.9181 | 11.0338 | 7.3913 | 10.9266 | 11.6735 | 9.5346 | 11.0338 | 21.9604 | 33.634 | 43.1686
15.5109 | 8.5623 | 10.0568 | 4.2168 | 10.8071 | 12.0009 | 15.5109 | 19.7277 | 30.5348 | 42.5357
2.1354 | 10.3629 | 7.433 | 7.3219 | 12.4051 | 12.2147 | 10.3629 | 17.6848 | 30.0899 | 42.3046
6.4212 | 10.1604 | 9.6715 | 2.8114 | 10.6688 | 17.9651 | 10.1604 | 12.9718 | 23.6405 | 41.6057
-1.2083 | 9.5138 | 10.1537 | 6.8453 | 14.2928 | 17.9789 | 9.5138 | 16.3591 | 30.6519 | 48.6308
[6 empty] | 0 | 0 | Average | #VALUE!

## test activity A
A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | diff
-7.7551 | 10.6172 | 9.951 | 11.4327 | 11.4836 | 11.4968 | 10.6172 | 22.0499 | 33.5335 | 45.0303 | -7.7451 | 10.6172 | 9.951 | 11.4327 | 11.4836 | 11.4968 | 10.6172 | 22.0499 | 33.5335 | 45.0303 | 0
7.4367 | 9.1492 | 8.1533 | 9.6422 | 14.8066 | 8.745 | 9.1492 | 18.7914 | 33.598 | 42.343 | 7.4467 | 9.1492 | 8.1533 | 9.6422 | 14.8066 | 8.745 | 9.1492 | 18.7914 | 33.598 | 42.343 | 0
6.8651 | 7.7647 | 11.4096 | 10.5908 | 6.3737 | 12.5465 | 7.7647 | 18.3555 | 24.7292 | 37.2757 | 6.8751 | 7.7647 | 11.4096 | 10.5908 | 6.3737 | 12.5465 | 7.7647 | 18.3555 | 24.7292 | 37.2757 | 0
11.0288 | 7.8306 | 8.3418 | 11.2048 | 10.3992 | 10.4727 | 11.0288 | 22.2336 | 32.6328 | 43.1055 | 11.0388 | 7.8306 | 8.3418 | 11.2048 | 10.3992 | 10.4727 | 11.0288 | 22.2336 | 32.6328 | 43.1055 | 0
3.1602 | 9.7531 | 9.356 | 7.1589 | 5.8983 | 17.1026 | 9.7531 | 16.912 | 22.8103 | 39.9129 | 3.1702 | 9.7531 | 9.356 | 7.1589 | 5.8983 | 17.1026 | 9.7531 | 16.912 | 22.8103 | 39.9129 | 0
11.4248 | 9.0225 | 4.4877 | 8.8016 | 11.0903 | 10.7888 | 11.4248 | 20.2264 | 31.3167 | 42.1055 | 11.4348 | 9.0225 | 4.4877 | 8.8016 | 11.0903 | 10.7888 | 11.4248 | 20.2264 | 31.3167 | 42.1055 | 0
-1.5576 | 8.8854 | 7.367 | 3.9729 | 11.2123 | 9.7199 | 8.8854 | 12.8583 | 24.0706 | 33.7905 | -1.5476 | 8.8854 | 7.367 | 3.9729 | 11.2123 | 9.7199 | 8.8854 | 12.8583 | 24.0706 | 33.7905 | 0
-7.7023 | 9.3515 | 6.9936 | 7.8158 | 17.5153 | 11.1727 | 9.3515 | 17.1673 | 34.6826 | 45.8553 | -7.6923 | 9.3515 | 6.9936 | 7.8158 | 17.5153 | 11.1727 | 9.3515 | 17.1673 | 34.6826 | 45.8553 | 0
4.4741 | 8.6752 | 9.0763 | 7.7107 | 6.6338 | 13.2586 | 8.6752 | 16.3859 | 23.0197 | 36.2783 | 4.4841 | 8.6752 | 9.0763 | 7.7107 | 6.6338 | 13.2586 | 8.6752 | 16.3859 | 23.0197 | 36.2783 | 0
10.5441 | 8.6537 | 10.3992 | 3.5911 | 8.2745 | 8.8554 | 10.5441 | 14.1353 | 22.4097 | 31.2652 | 10.5541 | 8.6537 | 10.3992 | 3.5911 | 8.2745 | 8.8554 | 10.5441 | 14.1353 | 22.4097 | 31.2652 | 0
-3.9182 | 7.3989 | 9.1769 | 3.4307 | 9.2799 | 10.1396 | 7.3989 | 10.8296 | 20.1095 | 30.2491 | -3.9082 | 7.3989 | 9.1769 | 3.4307 | 9.2799 | 10.1396 | 7.3989 | 10.8296 | 20.1095 | 30.2491 | 0
-0.98948 | 10.5609 | 8.5522 | 7.0728 | 9.2645 | 10.6446 | 10.5609 | 17.6337 | 26.8981 | 37.5427 | -0.97948 | 10.5609 | 8.5522 | 7.0728 | 9.2645 | 10.6446 | 10.5609 | 17.6337 | 26.8981 | 37.5427 | 0
12.885 | 9.593 | 7.4143 | 7.0937 | 14.0836 | 8.1594 | 12.885 | 19.9788 | 34.0623 | 42.2217 | 12.895 | 9.593 | 7.4143 | 7.0937 | 14.0836 | 8.1594 | 12.885 | 19.9788 | 34.0623 | 42.2217 | 0
4.9281 | 8.5642 | 8.1642 | 7.7995 | 9.0851 | 13.1297 | 8.5642 | 16.3637 | 25.4487 | 38.5784 | 4.9381 | 8.5642 | 8.1642 | 7.7995 | 9.0851 | 13.1297 | 8.5642 | 16.3637 | 25.4487 | 38.5784 | 0
-0.84741 | 8.2044 | 7.2375 | 5.3049 | 13.0524 | 15.3449 | 8.2044 | 13.5092 | 26.5617 | 41.9066 | -0.83741 | 8.2044 | 7.2375 | 5.3049 | 13.0524 | 15.3449 | 8.2044 | 13.5092 | 26.5617 | 41.9066 | 0
-10.0415 | 10.2783 | 10.8756 | 6.9861 | 14.6188 | 9.7177 | 10.2783 | 17.2644 | 31.8832 | 41.601 | -10.0315 | 10.2783 | 10.8756 | 6.9861 | 14.6188 | 9.7177 | 10.2783 | 17.2644 | 31.8832 | 41.601 | 0
-4.9238 | 9.8972 | 7.5314 | 8.7201 | 13.2095 | 13.533 | 9.8972 | 18.6173 | 31.8269 | 45.3598 | -4.9138 | 9.8972 | 7.5314 | 8.7201 | 13.2095 | 13.533 | 9.8972 | 18.6173 | 31.8269 | 45.3598 | 0
-0.041984 | 7.9722 | 9.2455 | 7.2884 | 11.0179 | 10.291 | 7.9722 | 15.2606 | 26.2785 | 36.5694 | -0.031984 | 7.9722 | 9.2455 | 7.2884 | 11.0179 | 10.291 | 7.9722 | 15.2606 | 26.2785 | 36.5694 | 0
8.7577 | 10.1366 | 5.8852 | 3.5285 | 10.6993 | 14.079 | 10.1366 | 13.665 | 24.3644 | 38.4433 | 8.7677 | 10.1366 | 5.8852 | 3.5285 | 10.6993 | 14.079 | 10.1366 | 13.665 | 24.3644 | 38.4433 | 0
5.6091 | 7.3573 | 9.8547 | 5.1702 | 9.7925 | 11.6195 | 7.3573 | 12.5275 | 22.32 | 33.9395 | 5.6191 | 7.3573 | 9.8547 | 5.1702 | 9.7925 | 11.6195 | 7.3573 | 12.5275 | 22.32 | 33.9395 | 0
-3.9008 | 8.004 | 6.8482 | 6.1112 | 6.2971 | 10.7133 | 8.004 | 14.1152 | 20.4123 | 31.1256 | -3.8908 | 8.004 | 6.8482 | 6.1112 | 6.2971 | 10.7133 | 8.004 | 14.1152 | 20.4123 | 31.1256 | 0
-0.72996 | 9.4083 | 6.1784 | 4.3465 | 8.6411 | 12.2235 | 9.4083 | 13.7548 | 22.3959 | 34.6194 | -0.71996 | 9.4083 | 6.1784 | 4.3465 | 8.6411 | 12.2235 | 9.4083 | 13.7548 | 22.3959 | 34.6194 | 0
7.6841 | 7.832 | 8.1915 | 5.2397 | 6.6767 | 12.6943 | 7.832 | 13.0717 | 19.7485 | 32.4428 | 7.6941 | 7.832 | 8.1915 | 5.2397 | 6.6767 | 12.6943 | 7.832 | 13.0717 | 19.7485 | 32.4428 | 0
5.7811 | 8.9705 | 7.6556 | 4.6549 | 13.2615 | 12.8435 | 8.9705 | 13.6254 | 26.8869 | 39.7304 | 5.7911 | 8.9705 | 7.6556 | 4.6549 | 13.2615 | 12.8435 | 8.9705 | 13.6254 | 26.8869 | 39.7304 | 0
-5.7588 | 9.9283 | 9.0112 | 2.4531 | 10.5313 | 8.1427 | 9.9283 | 12.3814 | 22.9127 | 31.0554 | -5.7488 | 9.9283 | 9.0112 | 2.4531 | 10.5313 | 8.1427 | 9.9283 | 12.3814 | 22.9127 | 31.0554 | 0
6.8917 | 9.3308 | 8.707 | 5.7676 | 11.9391 | 10.4419 | 9.3308 | 15.0984 | 27.0375 | 37.4794 | 6.9017 | 9.3308 | 8.707 | 5.7676 | 11.9391 | 10.4419 | 9.3308 | 15.0984 | 27.0375 | 37.4794 | 0
-0.48741 | 10.6471 | 5.7716 | 3.4442 | 10.585 | 12.0816 | 10.6471 | 14.0914 | 24.6763 | 36.7579 | -0.47741 | 10.6471 | 5.7716 | 3.4442 | 10.585 | 12.0816 | 10.6471 | 14.0914 | 24.6763 | 36.7579 | 0
0.87552 | 9.2638 | 8.2461 | 8.7599 | 11.6839 | 14.2868 | 9.2638 | 18.0237 | 29.7076 | 43.9944 | 0.88552 | 9.2638 | 8.2461 | 8.7599 | 11.6839 | 14.2868 | 9.2638 | 18.0237 | 29.7076 | 43.9944 | 0
-2.8158 | 11.1924 | 8.4708 | 13.0938 | 8.7867 | 16.0224 | 11.1924 | 24.2862 | 33.0729 | 49.0953 | -2.8058 | 11.1924 | 8.4708 | 13.0938 | 8.7867 | 16.0224 | 11.1924 | 24.2862 | 33.0729 | 49.0953 | 0
7.4043 | 9.7713 | 8.3368 | 7.3393 | 15.4377 | 11.8642 | 9.7713 | 17.1106 | 32.5483 | 44.4124 | 7.4143 | 9.7713 | 8.3368 | 7.3393 | 15.4377 | 11.8642 | 9.7713 | 17.1106 | 32.5483 | 44.4124 | 0
5.0162 | 6.9768 | 6.1202 | 6.933 | 10.7846 | 4.3207 | 6.9768 | 13.9098 | 24.6945 | 29.0152 | 5.0262 | 6.9768 | 6.1202 | 6.933 | 10.7846 | 4.3207 | 6.9768 | 13.9098 | 24.6945 | 29.0152 | 0
-0.2309 | 9.9054 | 7.2445 | 9.5354 | 9.1073 | 6.2056 | 9.9054 | 19.4408 | 28.5481 | 34.7537 | -0.2209 | 9.9054 | 7.2445 | 9.5354 | 9.1073 | 6.2056 | 9.9054 | 19.4408 | 28.5481 | 34.7537 | 0
5.7831 | 9.907 | 8.8985 | 3.0197 | 9.1803 | 17.1948 | 9.907 | 12.9267 | 22.1071 | 39.3018 | 5.7931 | 9.907 | 8.8985 | 3.0197 | 9.1803 | 17.1948 | 9.907 | 12.9267 | 22.1071 | 39.3018 | 0
12.4673 | 9.3865 | 7.0642 | 6.492 | 6.1196 | 12.7007 | 12.4673 | 18.9594 | 25.079 | 37.7796 | 12.4773 | 9.3865 | 7.0642 | 6.492 | 6.1196 | 12.7007 | 12.4673 | 18.9594 | 25.079 | 37.7796 | 0
6.8883 | 9.4987 | 4.7384 | 7.9926 | 13.0417 | 10.792 | 9.4987 | 17.4913 | 30.533 | 41.3251 | 6.8983 | 9.4987 | 4.7384 | 7.9926 | 13.0417 | 10.792 | 9.4987 | 17.4913 | 30.533 | 41.3251 | 0
2.8132 | 9.0969 | 11.3215 | 7.4152 | 11.2881 | 16.4266 | 9.0969 | 16.5122 | 27.8002 | 44.2269 | 2.8232 | 9.0969 | 11.3215 | 7.4152 | 11.2881 | 16.4266 | 9.0969 | 16.5122 | 27.8002 | 44.2269 | 0
1.1283 | 8.9683 | 9.9785 | 7.4813 | 8.5081 | 16.6191 | 8.9683 | 16.4496 | 24.9577 | 41.5768 | 1.1383 | 8.9683 | 9.9785 | 7.4813 | 8.5081 | 16.6191 | 8.9683 | 16.4496 | 24.9577 | 41.5768 | 0
7.7959 | 9.4408 | 8.2851 | 8.189 | 11.0351 | 7.4033 | 9.4408 | 17.6297 | 28.6648 | 36.0681 | 7.8059 | 9.4408 | 8.2851 | 8.189 | 11.0351 | 7.4033 | 9.4408 | 17.6297 | 28.6648 | 36.0681 | 0
7.5077 | 10.6633 | 11.2462 | 7.7463 | 13.0236 | 10.5756 | 10.6633 | 18.4096 | 31.4332 | 42.0088 | 7.5177 | 10.6633 | 11.2462 | 7.7463 | 13.0236 | 10.5756 | 10.6633 | 18.4096 | 31.4332 | 42.0088 | 0
-3.9596 | 8.0538 | 6.5376 | 6.815 | 8.6503 | 13.7345 | 8.0538 | 14.8689 | 23.5192 | 37.2537 | -3.9496 | 8.0538 | 6.5376 | 6.815 | 8.6503 | 13.7345 | 8.0538 | 14.8689 | 23.5192 | 37.2537 | 0
13.3018 | 8.7446 | 9.2964 | 5.3957 | 11.8794 | 11.8634 | 13.3018 | 18.6974 | 30.5769 | 42.4402 | 13.3118 | 8.7446 | 9.2964 | 5.3957 | 11.8794 | 11.8634 | 13.3018 | 18.6974 | 30.5769 | 42.4402 | 0
-9.5268 | 9.0063 | 8.0017 | 4.8714 | 12.0338 | 9.5648 | 9.0063 | 13.8777 | 25.9115 | 35.4763 | -9.5168 | 9.0063 | 8.0017 | 4.8714 | 12.0338 | 9.5648 | 9.0063 | 13.8777 | 25.9115 | 35.4763 | 0
6.9514 | 9.3514 | 7.1901 | 6.7595 | 11.5085 | 13.6852 | 9.3514 | 16.111 | 27.6195 | 41.3047 | 6.9614 | 9.3514 | 7.1901 | 6.7595 | 11.5085 | 13.6852 | 9.3514 | 16.111 | 27.6195 | 41.3047 | 0
17.2594 | 8.4916 | 8.3801 | 6.0115 | 7.4865 | 15.0339 | 17.2594 | 23.271 | 30.7575 | 45.7913 | 17.2694 | 8.4916 | 8.3801 | 6.0115 | 7.4865 | 15.0339 | 17.2594 | 23.271 | 30.7575 | 45.7913 | 0
5.132 | 9.9254 | 3.2408 | 8.5529 | 7.8208 | 8.9379 | 9.9254 | 18.4783 | 26.2991 | 35.237 | 5.142 | 9.9254 | 3.2408 | 8.5529 | 7.8208 | 8.9379 | 9.9254 | 18.4783 | 26.2991 | 35.237 | 0
9.2923 | 6.4792 | 8.7745 | 7.2143 | 9.2865 | 9.1846 | 9.2923 | 16.5066 | 25.7931 | 34.9777 | 9.3023 | 6.4792 | 8.7745 | 7.2143 | 9.2865 | 9.1846 | 9.2923 | 16.5066 | 25.7931 | 34.9777 | 0
5.866 | 8.7253 | 8.0823 | 7.6472 | 12.4083 | 11.9919 | 8.7253 | 16.3726 | 28.7808 | 40.7728 | 5.876 | 8.7253 | 8.0823 | 7.6472 | 12.4083 | 11.9919 | 8.7253 | 16.3726 | 28.7808 | 40.7728 | 0
2.9614 | 10.0054 | 6.4161 | 3.8604 | 12.0977 | 11.8664 | 10.0054 | 13.8658 | 25.9635 | 37.8299 | 2.9714 | 10.0054 | 6.4161 | 3.8604 | 12.0977 | 11.8664 | 10.0054 | 13.8658 | 25.9635 | 37.8299 | 0
-1.2875 | 8.781 | 12.9762 | 7.8395 | 8.9902 | 18.1549 | 8.781 | 16.6205 | 25.6107 | 43.7656 | -1.2775 | 8.781 | 12.9762 | 7.8395 | 8.9902 | 18.1549 | 8.781 | 16.6205 | 25.6107 | 43.7656 | 0
2.1338 | 10.6134 | 5.1675 | 6.66 | 9.6236 | 8.5911 | 10.6134 | 17.2734 | 26.897 | 35.4881 | 2.1438 | 10.6134 | 5.1675 | 6.66 | 9.6236 | 8.5911 | 10.6134 | 17.2734 | 26.897 | 35.4881 | 0
-9.7037 | 9.4429 | 10.1096 | 5.7841 | 9.6556 | 15.215 | 9.4429 | 15.227 | 24.8827 | 40.0976 | -9.6937 | 9.4429 | 10.1096 | 5.7841 | 9.6556 | 15.215 | 9.4429 | 15.227 | 24.8827 | 40.0976 | 0
1.1107 | 10.2077 | 6.3874 | 4.1365 | 9.7014 | 11.6865 | 10.2077 | 14.3442 | 24.0456 | 35.7321 | 1.1207 | 10.2077 | 6.3874 | 4.1365 | 9.7014 | 11.6865 | 10.2077 | 14.3442 | 24.0456 | 35.7321 | 0
-1.3727 | 10.8056 | 5.7818 | 5.0618 | 6.7809 | 8.4325 | 10.8056 | 15.8674 | 22.6483 | 31.0808 | -1.3627 | 10.8056 | 5.7818 | 5.0618 | 6.7809 | 8.4325 | 10.8056 | 15.8674 | 22.6483 | 31.0808 | 0
9.8007 | 8.9808 | 11.9067 | 4.9246 | 8.996 | 12.1478 | 9.8007 | 14.7253 | 23.7213 | 35.8692 | 9.8107 | 8.9808 | 11.9067 | 4.9246 | 8.996 | 12.1478 | 9.8007 | 14.7253 | 23.7213 | 35.8692 | 0
0.54161 | 9.2874 | 6.779 | 4.7108 | 11.9675 | 14.6726 | 9.2874 | 13.9982 | 25.9657 | 40.6383 | 0.55161 | 9.2874 | 6.779 | 4.7108 | 11.9675 | 14.6726 | 9.2874 | 13.9982 | 25.9657 | 40.6383 | 0
4.4236 | 7.848 | 8.981 | 9.0156 | 3.0602 | 11.8871 | 7.848 | 16.8637 | 19.9238 | 31.8109 | 4.4336 | 7.848 | 8.981 | 9.0156 | 3.0602 | 11.8871 | 7.848 | 16.8637 | 19.9238 | 31.8109 | 0
-9.9669 | 8.4938 | 5.3968 | 5.1713 | 3.3619 | 8.6675 | 8.4938 | 13.665 | 17.0269 | 25.6944 | -9.9569 | 8.4938 | 5.3968 | 5.1713 | 3.3619 | 8.6675 | 8.4938 | 13.665 | 17.0269 | 25.6944 | 0
0.39351 | 10.029 | 7.0946 | 7.83 | 7.4489 | 13.5258 | 10.029 | 17.859 | 25.3079 | 38.8337 | 0.40351 | 10.029 | 7.0946 | 7.83 | 7.4489 | 13.5258 | 10.029 | 17.859 | 25.3079 | 38.8337 | 0
1.4697 | 10.2713 | 9.1875 | 4.3002 | 9.1669 | 8.7637 | 10.2713 | 14.5714 | 23.7383 | 32.502 | 1.4797 | 10.2713 | 9.1875 | 4.3002 | 9.1669 | 8.7637 | 10.2713 | 14.5714 | 23.7383 | 32.502 | 0
4.9902 | 9.6154 | 8.2714 | 8.5255 | 6.9464 | 14.5058 | 9.6154 | 18.141 | 25.0873 | 39.5931 | 5.0002 | 9.6154 | 8.2714 | 8.5255 | 6.9464 | 14.5058 | 9.6154 | 18.141 | 25.0873 | 39.5931 | 0
6.2075 | 9.3605 | 8.5697 | 6.3427 | 9.8586 | 12.4063 | 9.3605 | 15.7032 | 25.5617 | 37.968 | 6.2175 | 9.3605 | 8.5697 | 6.3427 | 9.8586 | 12.4063 | 9.3605 | 15.7032 | 25.5617 | 37.968 | 0
9.7598 | 8.5078 | 9.9764 | 8.8916 | 10.057 | 15.0524 | 9.7598 | 18.6513 | 28.7083 | 43.7607 | 9.7698 | 8.5078 | 9.9764 | 8.8916 | 10.057 | 15.0524 | 9.7598 | 18.6513 | 28.7083 | 43.7607 | 0
4.8689 | 9.3381 | 6.2664 | 11.5762 | 12.5801 | 15.321 | 9.3381 | 20.9144 | 33.4945 | 48.8155 | 4.8789 | 9.3381 | 6.2664 | 11.5762 | 12.5801 | 15.321 | 9.3381 | 20.9144 | 33.4945 | 48.8155 | 0
0.36889 | 8.4642 | 6.7422 | 3.1447 | 10.0744 | 11.6116 | 8.4642 | 11.6089 | 21.6833 | 33.2949 | 0.37889 | 8.4642 | 6.7422 | 3.1447 | 10.0744 | 11.6116 | 8.4642 | 11.6089 | 21.6833 | 33.2949 | 0
11.1425 | 9.7194 | 11.3153 | 10.0331 | 12.4273 | 14.9788 | 11.1425 | 21.1756 | 33.6029 | 48.5817 | 11.1525 | 9.7194 | 11.3153 | 10.0331 | 12.4273 | 14.9788 | 11.1425 | 21.1756 | 33.6029 | 48.5817 | 0
11.4664 | 8.5147 | 8.5514 | 8.561 | 9.6705 | 13.278 | 11.4664 | 20.0274 | 29.6979 | 42.9758 | 11.4764 | 8.5147 | 8.5514 | 8.561 | 9.6705 | 13.278 | 11.4664 | 20.0274 | 29.6979 | 42.9758 | 0
5.7516 | 7.8035 | 10.9594 | 8.0447 | 9.6225 | 13.6005 | 7.8035 | 15.8482 | 25.4707 | 39.0712 | 5.7616 | 7.8035 | 10.9594 | 8.0447 | 9.6225 | 13.6005 | 7.8035 | 15.8482 | 25.4707 | 39.0712 | 0
-6.9054 | 8.9378 | 7.1458 | 9.7039 | 16.9868 | 16.3327 | 8.9378 | 18.6417 | 35.6285 | 51.9612 | -6.8954 | 8.9378 | 7.1458 | 9.7039 | 16.9868 | 16.3327 | 8.9378 | 18.6417 | 35.6285 | 51.9612 | 0
2.6798 | 9.9038 | 8.3391 | 7.9098 | 5.7392 | 13.0197 | 9.9038 | 17.8136 | 23.5528 | 36.5725 | 2.6898 | 9.9038 | 8.3391 | 7.9098 | 5.7392 | 13.0197 | 9.9038 | 17.8136 | 23.5528 | 36.5725 | 0
3.158 | 8.6627 | 10.7137 | 7.5648 | 16.365 | 11.425 | 8.6627 | 16.2275 | 32.5925 | 44.0175 | 3.168 | 8.6627 | 10.7137 | 7.5648 | 16.365 | 11.425 | 8.6627 | 16.2275 | 32.5925 | 44.0175 | 0
3.8851 | 7.9431 | 10.1956 | 4.778 | 9.3363 | 9.0501 | 7.9431 | 12.7211 | 22.0574 | 31.1075 | 3.8951 | 7.9431 | 10.1956 | 4.778 | 9.3363 | 9.0501 | 7.9431 | 12.7211 | 22.0574 | 31.1075 | 0
11.525 | 9.1026 | 10.3916 | 5.1847 | 5.1607 | 4.7629 | 11.525 | 16.7097 | 21.9167 | 26.6795 | 11.535 | 9.1026 | 10.3916 | 5.1847 | 5.1607 | 4.7629 | 11.525 | 16.7097 | 21.9167 | 26.6795 | 0
1.4733 | 7.4822 | 7.1195 | 6.0029 | 13.2963 | 9.2742 | 7.4822 | 13.4852 | 26.7815 | 36.0557 | 1.4833 | 7.4822 | 7.1195 | 6.0029 | 13.2963 | 9.2742 | 7.4822 | 13.4852 | 26.7815 | 36.0557 | 0
4.168 | 9.4725 | 6.8274 | 5.792 | 9.2746 | 9.1378 | 9.4725 | 15.2645 | 24.5391 | 33.6769 | 4.178 | 9.4725 | 6.8274 | 5.792 | 9.2746 | 9.1378 | 9.4725 | 15.2645 | 24.5391 | 33.6769 | 0
2.9539 | 9.2805 | 7.3035 | 3.8993 | 12.7031 | 12.705 | 9.2805 | 13.1798 | 25.8828 | 38.5879 | 2.9639 | 9.2805 | 7.3035 | 3.8993 | 12.7031 | 12.705 | 9.2805 | 13.1798 | 25.8828 | 38.5879 | 0
-7.0796 | 9.3911 | 11.6656 | 6.0217 | 5.91 | 15.7881 | 9.3911 | 15.4128 | 21.3228 | 37.1109 | -7.0696 | 9.3911 | 11.6656 | 6.0217 | 5.91 | 15.7881 | 9.3911 | 15.4128 | 21.3228 | 37.1109 | 0
-2.094 | 9.3496 | 7.2544 | 9.1273 | 14.7966 | 18.1332 | 9.3496 | 18.4769 | 33.2735 | 51.4067 | -2.084 | 9.3496 | 7.2544 | 9.1273 | 14.7966 | 18.1332 | 9.3496 | 18.4769 | 33.2735 | 51.4067 | 0
11.0881 | 10.5845 | 8.5727 | 3.909 | 13.331 | 9.1773 | 11.0881 | 14.9971 | 28.3281 | 37.5054 | 11.0981 | 10.5845 | 8.5727 | 3.909 | 13.331 | 9.1773 | 11.0881 | 14.9971 | 28.3281 | 37.5054 | 0
6.4017 | 9.4727 | 8.5515 | 4.8003 | 10.0783 | 17.3491 | 9.4727 | 14.273 | 24.3513 | 41.7005 | 6.4117 | 9.4727 | 8.5515 | 4.8003 | 10.0783 | 17.3491 | 9.4727 | 14.273 | 24.3513 | 41.7005 | 0
4.7683 | 10.0145 | 5.4466 | 8.0195 | 10.4783 | 10.0801 | 10.0145 | 18.034 | 28.5123 | 38.5924 | 4.7783 | 10.0145 | 5.4466 | 8.0195 | 10.4783 | 10.0801 | 10.0145 | 18.034 | 28.5123 | 38.5924 | 0
6.3333 | 7.4033 | 12.7768 | 9.3672 | 4.4206 | 10.7406 | 7.4033 | 16.7705 | 21.1911 | 31.9317 | 6.3433 | 7.4033 | 12.7768 | 9.3672 | 4.4206 | 10.7406 | 7.4033 | 16.7705 | 21.1911 | 31.9317 | 0
15.0521 | 8.2255 | 9.7261 | 10.9774 | 11.573 | 9.7078 | 15.0521 | 26.0295 | 37.6025 | 47.3103 | 15.0621 | 8.2255 | 9.7261 | 10.9774 | 11.573 | 9.7078 | 15.0521 | 26.0295 | 37.6025 | 47.3103 | 0
-2.6112 | 8.0037 | 8.0773 | 5.8805 | 9.7311 | 8.0818 | 8.0037 | 13.8842 | 23.6154 | 31.6972 | -2.6012 | 8.0037 | 8.0773 | 5.8805 | 9.7311 | 8.0818 | 8.0037 | 13.8842 | 23.6154 | 31.6972 | 0
7.3361 | 9.8275 | 7.8859 | 6.8749 | 8.7742 | 12.223 | 9.8275 | 16.7024 | 25.4765 | 37.6996 | 7.3461 | 9.8275 | 7.8859 | 6.8749 | 8.7742 | 12.223 | 9.8275 | 16.7024 | 25.4765 | 37.6996 | 0
3.6751 | 9.0643 | 5.3536 | 6.7491 | 6.4153 | 11.9307 | 9.0643 | 15.8133 | 22.2286 | 34.1593 | 3.6851 | 9.0643 | 5.3536 | 6.7491 | 6.4153 | 11.9307 | 9.0643 | 15.8133 | 22.2286 | 34.1593 | 0
0.80419 | 7.059 | 6.0263 | 6.7334 | 11.3673 | 12.8382 | 7.059 | 13.7924 | 25.1597 | 37.9979 | 0.81419 | 7.059 | 6.0263 | 6.7334 | 11.3673 | 12.8382 | 7.059 | 13.7924 | 25.1597 | 37.9979 | 0
13.9973 | 7.826 | 7.5535 | 6.8621 | 12.93 | 13.9702 | 13.9973 | 20.8594 | 33.7894 | 47.7596 | 14.0073 | 7.826 | 7.5535 | 6.8621 | 12.93 | 13.9702 | 13.9973 | 20.8594 | 33.7894 | 47.7596 | 0
-2.5283 | 7.9519 | 10.4693 | 7.7742 | 10.1962 | 16.0707 | 7.9519 | 15.726 | 25.9222 | 41.993 | -2.5183 | 7.9519 | 10.4693 | 7.7742 | 10.1962 | 16.0707 | 7.9519 | 15.726 | 25.9222 | 41.993 | 0
-6.3369 | 8.8209 | 8.9808 | 7.1559 | 11.9008 | 19.8377 | 8.8209 | 15.9768 | 27.8776 | 47.7154 | -6.3269 | 8.8209 | 8.9808 | 7.1559 | 11.9008 | 19.8377 | 8.8209 | 15.9768 | 27.8776 | 47.7154 | 0
11.9535 | 8.2946 | 8.052 | 7.5413 | 14.0477 | 11.859 | 11.9535 | 19.4948 | 33.5425 | 45.4014 | 11.9635 | 8.2946 | 8.052 | 7.5413 | 14.0477 | 11.859 | 11.9535 | 19.4948 | 33.5425 | 45.4014 | 0
5.8166 | 8.7857 | 8.8865 | 5.8551 | 9.0711 | 10.9806 | 8.7857 | 14.6408 | 23.712 | 34.6926 | 5.8266 | 8.7857 | 8.8865 | 5.8551 | 9.0711 | 10.9806 | 8.7857 | 14.6408 | 23.712 | 34.6926 | 0
2.7486 | 9.3492 | 10.6504 | 3.138 | 7.1442 | 9.8101 | 9.3492 | 12.4872 | 19.9996 | 29.8097 | 2.7586 | 9.3492 | 10.6504 | 3.138 | 7.1442 | 9.8101 | 9.3492 | 12.4872 | 19.9996 | 29.8097 | 0
10.3216 | 10.4736 | 7.9684 | 6.7943 | 11.6662 | 6.8006 | 10.4736 | 17.2679 | 28.9341 | 35.7347 | 10.3316 | 10.4736 | 7.9684 | 6.7943 | 11.6662 | 6.8006 | 10.4736 | 17.2679 | 28.9341 | 35.7347 | 0
2.5823 | 9.0124 | 7.8851 | 5.6414 | 10.7886 | 7.7657 | 9.0124 | 14.6538 | 25.4425 | 33.2081 | 2.5923 | 9.0124 | 7.8851 | 5.6414 | 10.7886 | 7.7657 | 9.0124 | 14.6538 | 25.4425 | 33.2081 | 0
-3.4357 | 9.2902 | 8.8867 | 5.4319 | 16.183 | 13.5058 | 9.2902 | 14.7222 | 30.9051 | 44.4109 | -3.4257 | 9.2902 | 8.8867 | 5.4319 | 16.183 | 13.5058 | 9.2902 | 14.7222 | 30.9051 | 44.4109 | 0
15.5802 | 8.8448 | 9.2833 | 9.6421 | 11.6158 | 14.4833 | 15.5802 | 25.2223 | 36.8381 | 51.3214 | 15.5902 | 8.8448 | 9.2833 | 9.6421 | 11.6158 | 14.4833 | 15.5802 | 25.2223 | 36.8381 | 51.3214 | 0
3.0918 | 9.8773 | 3.54 | 9.1011 | 10.6765 | 7.1635 | 9.8773 | 18.9784 | 29.6549 | 36.8184 | 3.1018 | 9.8773 | 3.54 | 9.1011 | 10.6765 | 7.1635 | 9.8773 | 18.9784 | 29.6549 | 36.8184 | 0
11.1037 | 6.7729 | 7.3241 | 9.0945 | 11.4351 | 12.5295 | 11.1037 | 20.1983 | 31.6334 | 44.1629 | 11.1137 | 6.7729 | 7.3241 | 9.0945 | 11.4351 | 12.5295 | 11.1037 | 20.1983 | 31.6334 | 44.1629 | 0
-0.83974 | 11.6811 | 10.0684 | 5.2068 | 11.9171 | 15.5247 | 11.6811 | 16.888 | 28.8051 | 44.3298 | -0.82974 | 11.6811 | 10.0684 | 5.2068 | 11.9171 | 15.5247 | 11.6811 | 16.888 | 28.8051 | 44.3298 | 0
4.7459 | 8.5794 | 6.0023 | 8.713 | 11.8144 | 15.9991 | 8.5794 | 17.2924 | 29.1069 | 45.106 | 4.7559 | 8.5794 | 6.0023 | 8.713 | 11.8144 | 15.9991 | 8.5794 | 17.2924 | 29.1069 | 45.106 | 0
-3.3289 | 9.2639 | 5.7095 | 5.2189 | 10.1673 | 9.2936 | 9.2639 | 14.4828 | 24.65 | 33.9437 | -3.3189 | 9.2639 | 5.7095 | 5.2189 | 10.1673 | 9.2936 | 9.2639 | 14.4828 | 24.65 | 33.9437 | 0
6.0204 | 8.7048 | 8.4384 | 9.8827 | 7.0854 | 5.4672 | 8.7048 | 18.5875 | 25.6728 | 31.1401 | 6.0304 | 8.7048 | 8.4384 | 9.8827 | 7.0854 | 5.4672 | 8.7048 | 18.5875 | 25.6728 | 31.1401 | 0
3.6555 | 8.5261 | 8.5056 | 8.6286 | 13.2759 | 11.0128 | 8.5261 | 17.1547 | 30.4307 | 41.4434 | 3.6655 | 8.5261 | 8.5056 | 8.6286 | 13.2759 | 11.0128 | 8.5261 | 17.1547 | 30.4307 | 41.4434 | 0
-0.093682 | 7.8766 | 9.6921 | 7.4249 | 8.9105 | 9.9653 | 7.8766 | 15.3016 | 24.212 | 34.1773 | -0.083682 | 7.8766 | 9.6921 | 7.4249 | 8.9105 | 9.9653 | 7.8766 | 15.3016 | 24.212 | 34.1773 | 0
0.93895 | 9.2474 | 7.7912 | 6.9277 | 13.1253 | 14.6946 | 9.2474 | 16.1751 | 29.3003 | 43.9949 | 0.94895 | 9.2474 | 7.7912 | 6.9277 | 13.1253 | 14.6946 | 9.2474 | 16.1751 | 29.3003 | 43.9949 | 0
10.6048 | 8.9763 | 10.8877 | 3.9409 | 11.8613 | 11.1048 | 10.6048 | 14.5457 | 26.407 | 37.5118 | 10.6148 | 8.9763 | 10.8877 | 3.9409 | 11.8613 | 11.1048 | 10.6048 | 14.5457 | 26.407 | 37.5118 | 0
3.3089 | 9.8081 | 9.1389 | 9.822 | 8.2647 | 8.5158 | 9.8081 | 19.6301 | 27.8948 | 36.4106 | 3.3189 | 9.8081 | 9.1389 | 9.822 | 8.2647 | 8.5158 | 9.8081 | 19.6301 | 27.8948 | 36.4106 | 0
4.7409 | 9.1722 | 4.9758 | 5.0988 | 15.8188 | 15.2905 | 9.1722 | 14.271 | 30.0899 | 45.3803 | 4.7509 | 9.1722 | 4.9758 | 5.0988 | 15.8188 | 15.2905 | 9.1722 | 14.271 | 30.0899 | 45.3803 | 0
-3.3347 | 8.5143 | 9.3513 | 6.7302 | 9.5456 | 9.5048 | 8.5143 | 15.2444 | 24.79 | 34.2948 | -3.3247 | 8.5143 | 9.3513 | 6.7302 | 9.5456 | 9.5048 | 8.5143 | 15.2444 | 24.79 | 34.2948 | 0
0.28161 | 8.2269 | 7.0931 | 7.7716 | 11.4784 | 8.3402 | 8.2269 | 15.9984 | 27.4768 | 35.817 | 0.29161 | 8.2269 | 7.0931 | 7.7716 | 11.4784 | 8.3402 | 8.2269 | 15.9984 | 27.4768 | 35.817 | 0
-4.9328 | 10.2253 | 5.2379 | 6.5345 | 11.7969 | 13.3181 | 10.2253 | 16.7598 | 28.5568 | 41.8749 | -4.9228 | 10.2253 | 5.2379 | 6.5345 | 11.7969 | 13.3181 | 10.2253 | 16.7598 | 28.5568 | 41.8749 | 0
-1.9918 | 8.7506 | 8.5794 | 10.4537 | 13.6376 | 10.839 | 8.7506 | 19.2043 | 32.8419 | 43.6809 | -1.9818 | 8.7506 | 8.5794 | 10.4537 | 13.6376 | 10.839 | 8.7506 | 19.2043 | 32.8419 | 43.6809 | 0
13.7191 | 9.727 | 5.7391 | 6.7605 | 10.8361 | 6.8985 | 13.7191 | 20.4796 | 31.3156 | 38.2141 | 13.7291 | 9.727 | 5.7391 | 6.7605 | 10.8361 | 6.8985 | 13.7191 | 20.4796 | 31.3156 | 38.2141 | 0
-5.0786 | 9.307 | 7.8802 | 7.2565 | 7.3325 | 9.5643 | 9.307 | 16.5635 | 23.8959 | 33.4602 | -5.0686 | 9.307 | 7.8802 | 7.2565 | 7.3325 | 9.5643 | 9.307 | 16.5635 | 23.8959 | 33.4602 | 0
7.6798 | 11.0206 | 11.2556 | 10.2923 | 6.8016 | 17.0642 | 11.0206 | 21.3128 | 28.1144 | 45.1786 | 7.6898 | 11.0206 | 11.2556 | 10.2923 | 6.8016 | 17.0642 | 11.0206 | 21.3128 | 28.1144 | 45.1786 | 0
4.9302 | 10.3406 | 9.1241 | 9.3648 | 9.7013 | 16.6284 | 10.3406 | 19.7055 | 29.4067 | 46.0351 | 4.9402 | 10.3406 | 9.1241 | 9.3648 | 9.7013 | 16.6284 | 10.3406 | 19.7055 | 29.4067 | 46.0351 | 0
0.36434 | 10.9811 | 8.3154 | 3.6051 | 14.2752 | 11.0414 | 10.9811 | 14.5862 | 28.8614 | 39.9028 | 0.37434 | 10.9811 | 8.3154 | 3.6051 | 14.2752 | 11.0414 | 10.9811 | 14.5862 | 28.8614 | 39.9028 | 0
-9.2182 | 8.0255 | 7.5194 | 4.0594 | 11.3779 | 15.6153 | 8.0255 | 12.0849 | 23.4628 | 39.0781 | -9.2082 | 8.0255 | 7.5194 | 4.0594 | 11.3779 | 15.6153 | 8.0255 | 12.0849 | 23.4628 | 39.0781 | 0
-9.272 | 9.1672 | 9.6205 | 10.551 | 6.303 | 13.0174 | 9.1672 | 19.7182 | 26.0212 | 39.0386 | -9.262 | 9.1672 | 9.6205 | 10.551 | 6.303 | 13.0174 | 9.1672 | 19.7182 | 26.0212 | 39.0386 | 0
4.3481 | 8.8628 | 3.9999 | 9.345 | 9.9328 | 12.1503 | 8.8628 | 18.2078 | 28.1407 | 40.291 | 4.3581 | 8.8628 | 3.9999 | 9.345 | 9.9328 | 12.1503 | 8.8628 | 18.2078 | 28.1407 | 40.291 | 0
-8.1137 | 9.5424 | 6.992 | 8.5223 | 8.9708 | 10.6103 | 9.5424 | 18.0647 | 27.0355 | 37.6459 | -8.1037 | 9.5424 | 6.992 | 8.5223 | 8.9708 | 10.6103 | 9.5424 | 18.0647 | 27.0355 | 37.6459 | 0
-9.0961 | 8.798 | 3.2406 | 6.0566 | 10.776 | 9.4947 | 8.798 | 14.8546 | 25.6306 | 35.1253 | -9.0861 | 8.798 | 3.2406 | 6.0566 | 10.776 | 9.4947 | 8.798 | 14.8546 | 25.6306 | 35.1253 | 0
-2.1816 | 10.684 | 8.549 | 5.8478 | 12.2749 | 8.011 | 10.684 | 16.5318 | 28.8067 | 36.8177 | -2.1716 | 10.684 | 8.549 | 5.8478 | 12.2749 | 8.011 | 10.684 | 16.5318 | 28.8067 | 36.8177 | 0
6.3063 | 8.692 | 5.2215 | 4.6185 | 15.2081 | 8.9357 | 8.692 | 13.3105 | 28.5186 | 37.4543 | 6.3163 | 8.692 | 5.2215 | 4.6185 | 15.2081 | 8.9357 | 8.692 | 13.3105 | 28.5186 | 37.4543 | 0
5.537 | 9.2748 | 7.8839 | 6.063 | 7.708 | 10.6706 | 9.2748 | 15.3378 | 23.0458 | 33.7164 | 5.547 | 9.2748 | 7.8839 | 6.063 | 7.708 | 10.6706 | 9.2748 | 15.3378 | 23.0458 | 33.7164 | 0
4.5947 | 8.7395 | 7.47 | 6.4781 | 9.6176 | 13.124 | 8.7395 | 15.2176 | 24.8352 | 37.9592 | 4.6047 | 8.7395 | 7.47 | 6.4781 | 9.6176 | 13.124 | 8.7395 | 15.2176 | 24.8352 | 37.9592 | 0
-4.1091 | 8.15 | 7.2689 | 6.93 | 7.7143 | 19.0045 | 8.15 | 15.0801 | 22.7944 | 41.7988 | -4.0991 | 8.15 | 7.2689 | 6.93 | 7.7143 | 19.0045 | 8.15 | 15.0801 | 22.7944 | 41.7988 | 0
-2.7655 | 8.5191 | 11.0318 | 3.0172 | 14.6342 | 13.4611 | 8.5191 | 11.5362 | 26.1704 | 39.6316 | -2.7555 | 8.5191 | 11.0318 | 3.0172 | 14.6342 | 13.4611 | 8.5191 | 11.5362 | 26.1704 | 39.6316 | 0
4.7116 | 7.4348 | 7.1443 | 5.4282 | 8.3847 | 12.1861 | 7.4348 | 12.863 | 21.2477 | 33.4338 | 4.7216 | 7.4348 | 7.1443 | 5.4282 | 8.3847 | 12.1861 | 7.4348 | 12.863 | 21.2477 | 33.4338 | 0
4.0396 | 9.5176 | 9.6024 | 8.7593 | 9.0299 | 8.0206 | 9.5176 | 18.277 | 27.3069 | 35.3275 | 4.0496 | 9.5176 | 9.6024 | 8.7593 | 9.0299 | 8.0206 | 9.5176 | 18.277 | 27.3069 | 35.3275 | 0
4.3895 | 8.182 | 6.843 | 8.3091 | 10.1354 | 22.4198 | 8.182 | 16.491 | 26.6265 | 49.0462 | 4.3995 | 8.182 | 6.843 | 8.3091 | 10.1354 | 22.4198 | 8.182 | 16.491 | 26.6265 | 49.0462 | 0
7.435 | 8.8918 | 7.8801 | 2.401 | 5.0023 | 13.358 | 8.8918 | 11.2928 | 16.7719 | 30.1299 | 7.445 | 8.8918 | 7.8801 | 2.401 | 5.0023 | 13.358 | 8.8918 | 11.2928 | 16.7719 | 30.1299 | 0
2.6337 | 8.0535 | 9.8331 | 6.9129 | 9.8448 | 8.7881 | 8.0535 | 14.9665 | 24.8113 | 33.5994 | 2.6437 | 8.0535 | 9.8331 | 6.9129 | 9.8448 | 8.7881 | 8.0535 | 14.9665 | 24.8113 | 33.5994 | 0
0.45225 | 7.3535 | 12.7213 | 8.3793 | 13.3085 | 10.9421 | 7.3535 | 15.7328 | 29.0413 | 39.9834 | 0.46225 | 7.3535 | 12.7213 | 8.3793 | 13.3085 | 10.9421 | 7.3535 | 15.7328 | 29.0413 | 39.9834 | 0
8.9771 | 9.1163 | 9.0769 | 7.9504 | 7.9339 | 10.3419 | 9.1163 | 17.0668 | 25.0006 | 35.3426 | 8.9871 | 9.1163 | 9.0769 | 7.9504 | 7.9339 | 10.3419 | 9.1163 | 17.0668 | 25.0006 | 35.3426 | 0
-8.339 | 9.5283 | 8.9688 | 9.0696 | 7.6209 | 7.4259 | 9.5283 | 18.5979 | 26.2187 | 33.6446 | -8.329 | 9.5283 | 8.9688 | 9.0696 | 7.6209 | 7.4259 | 9.5283 | 18.5979 | 26.2187 | 33.6446 | 0
-5.6469 | 9.2578 | 9.5184 | 6.932 | 11.0434 | 6.928 | 9.2578 | 16.1898 | 27.2332 | 34.1612 | -5.6369 | 9.2578 | 9.5184 | 6.932 | 11.0434 | 6.928 | 9.2578 | 16.1898 | 27.2332 | 34.1612 | 0
4.5314 | 8.4529 | 8.3668 | 7.2184 | 7.7616 | 15.8276 | 8.4529 | 15.6713 | 23.4329 | 39.2606 | 4.5414 | 8.4529 | 8.3668 | 7.2184 | 7.7616 | 15.8276 | 8.4529 | 15.6713 | 23.4329 | 39.2606 | 0
3.3113 | 8.6858 | 7.7839 | 6.0665 | 9.645 | 12.1188 | 8.6858 | 14.7523 | 24.3974 | 36.5162 | 3.3213 | 8.6858 | 7.7839 | 6.0665 | 9.645 | 12.1188 | 8.6858 | 14.7523 | 24.3974 | 36.5162 | 0
-2.0068 | 8.298 | 7.0791 | 10.0843 | 15.5981 | 16.5348 | 8.298 | 18.3823 | 33.9803 | 50.5151 | -1.9968 | 8.298 | 7.0791 | 10.0843 | 15.5981 | 16.5348 | 8.298 | 18.3823 | 33.9803 | 50.5151 | 0
3.3169 | 7.4565 | 10.2245 | 3.6764 | 11.2168 | 9.6004 | 7.4565 | 11.1329 | 22.3497 | 31.9501 | 3.3269 | 7.4565 | 10.2245 | 3.6764 | 11.2168 | 9.6004 | 7.4565 | 11.1329 | 22.3497 | 31.9501 | 0
-0.024904 | 8.1684 | 7.4745 | 6.4295 | 8.995 | 10.3428 | 8.1684 | 14.598 | 23.593 | 33.9358 | -0.014904 | 8.1684 | 7.4745 | 6.4295 | 8.995 | 10.3428 | 8.1684 | 14.598 | 23.593 | 33.9358 | 0
9.6071 | 9.8622 | 10.5907 | 7.8532 | 11.1036 | 13.3452 | 9.8622 | 17.7154 | 28.8189 | 42.1641 | 9.6171 | 9.8622 | 10.5907 | 7.8532 | 11.1036 | 13.3452 | 9.8622 | 17.7154 | 28.8189 | 42.1641 | 0
2.355 | 9.1102 | 8.3718 | 6.1214 | 9.6371 | 9.6132 | 9.1102 | 15.2317 | 24.8687 | 34.4819 | 2.365 | 9.1102 | 8.3718 | 6.1214 | 9.6371 | 9.6132 | 9.1102 | 15.2317 | 24.8687 | 34.4819 | 0
12.0396 | 8.2679 | 10.4605 | 3.9117 | 8.8069 | 7.487 | 12.0396 | 15.9513 | 24.7582 | 32.2452 | 12.0496 | 8.2679 | 10.4605 | 3.9117 | 8.8069 | 7.487 | 12.0396 | 15.9513 | 24.7582 | 32.2452 | 0
6.2452 | 10.3125 | 10.8542 | 9.2984 | 10.9956 | 11.3299 | 10.3125 | 19.6109 | 30.6065 | 41.9364 | 6.2552 | 10.3125 | 10.8542 | 9.2984 | 10.9956 | 11.3299 | 10.3125 | 19.6109 | 30.6065 | 41.9364 | 0
6.8785 | 9.7603 | 8.5632 | 4.9982 | 9.6912 | 8.5321 | 9.7603 | 14.7585 | 24.4497 | 32.9818 | 6.8885 | 9.7603 | 8.5632 | 4.9982 | 9.6912 | 8.5321 | 9.7603 | 14.7585 | 24.4497 | 32.9818 | 0
5.8738 | 7.5864 | 10.5432 | 9.318 | 9.845 | 12.3092 | 7.5864 | 16.9044 | 26.7494 | 39.0586 | 5.8838 | 7.5864 | 10.5432 | 9.318 | 9.845 | 12.3092 | 7.5864 | 16.9044 | 26.7494 | 39.0586 | 0
4.9732 | 8.7351 | 8.9752 | 9.4654 | 6.6153 | 11.6315 | 8.7351 | 18.2005 | 24.8157 | 36.4473 | 4.9832 | 8.7351 | 8.9752 | 9.4654 | 6.6153 | 11.6315 | 8.7351 | 18.2005 | 24.8157 | 36.4473 | 0
13.5194 | 9.6949 | 8.8503 | 7.6786 | 8.6583 | 7.2246 | 13.5194 | 21.198 | 29.8563 | 37.0808 | 13.5294 | 9.6949 | 8.8503 | 7.6786 | 8.6583 | 7.2246 | 13.5194 | 21.198 | 29.8563 | 37.0808 | 0
9.3649 | 9.1845 | 8.8158 | 7.4661 | 12.1524 | 10.984 | 9.3649 | 16.831 | 28.9833 | 39.9674 | 9.3749 | 9.1845 | 8.8158 | 7.4661 | 12.1524 | 10.984 | 9.3649 | 16.831 | 28.9833 | 39.9674 | 0
-2.3549 | 9.4459 | 8.4458 | 4.1602 | 8.8348 | 11.5774 | 9.4459 | 13.6061 | 22.4409 | 34.0182 | -2.3449 | 9.4459 | 8.4458 | 4.1602 | 8.8348 | 11.5774 | 9.4459 | 13.6061 | 22.4409 | 34.0182 | 0
0.27666 | 8.1343 | 9.2352 | 9.0032 | 8.2931 | 5.2124 | 8.1343 | 17.1375 | 25.4306 | 30.643 | 0.28666 | 8.1343 | 9.2352 | 9.0032 | 8.2931 | 5.2124 | 8.1343 | 17.1375 | 25.4306 | 30.643 | 0
7.5486 | 8.2073 | 9.4095 | 10.2769 | 12.2838 | 15.3477 | 8.2073 | 18.4842 | 30.768 | 46.1157 | 7.5586 | 8.2073 | 9.4095 | 10.2769 | 12.2838 | 15.3477 | 8.2073 | 18.4842 | 30.768 | 46.1157 | 0
-15.1261 | 7.6006 | 5.7554 | 7.1791 | 12.8592 | 12.705 | 7.6006 | 14.7797 | 27.6389 | 40.3439 | -15.1161 | 7.6006 | 5.7554 | 7.1791 | 12.8592 | 12.705 | 7.6006 | 14.7797 | 27.6389 | 40.3439 | 0
-2.2184 | 9.8908 | 7.7443 | 5.3497 | 6.8486 | 14.4275 | 9.8908 | 15.2405 | 22.0891 | 36.5165 | -2.2084 | 9.8908 | 7.7443 | 5.3497 | 6.8486 | 14.4275 | 9.8908 | 15.2405 | 22.0891 | 36.5165 | 0
2.9794 | 6.9087 | 8.2588 | 6.6429 | 9.669 | 14.5187 | 6.9087 | 13.5516 | 23.2206 | 37.7393 | 2.9894 | 6.9087 | 8.2588 | 6.6429 | 9.669 | 14.5187 | 6.9087 | 13.5516 | 23.2206 | 37.7393 | 0
-3.9199 | 9.6613 | 9.199 | 8.0741 | 7.668 | 15.1848 | 9.6613 | 17.7354 | 25.4033 | 40.5881 | -3.9099 | 9.6613 | 9.199 | 8.0741 | 7.668 | 15.1848 | 9.6613 | 17.7354 | 25.4033 | 40.5881 | 0
-4.3993 | 8.7865 | 10.3984 | 7.1979 | 15.1874 | 10.0794 | 8.7865 | 15.9845 | 31.1719 | 41.2513 | -4.3893 | 8.7865 | 10.3984 | 7.1979 | 15.1874 | 10.0794 | 8.7865 | 15.9845 | 31.1719 | 41.2513 | 0
9.2657 | 7.6021 | 7.487 | 9.6646 | 14.4155 | 7.1071 | 9.2657 | 18.9303 | 33.3458 | 40.4529 | 9.2757 | 7.6021 | 7.487 | 9.6646 | 14.4155 | 7.1071 | 9.2657 | 18.9303 | 33.3458 | 40.4529 | 0
2.5885 | 9.4994 | 6.4886 | 5.2622 | 10.4084 | 13.5333 | 9.4994 | 14.7615 | 25.17 | 38.7033 | 2.5985 | 9.4994 | 6.4886 | 5.2622 | 10.4084 | 13.5333 | 9.4994 | 14.7615 | 25.17 | 38.7033 | 0
-5.1379 | 9.5355 | 3.704 | 6.5284 | 10.3731 | 15.7928 | 9.5355 | 16.0639 | 26.437 | 42.2299 | -5.1279 | 9.5355 | 3.704 | 6.5284 | 10.3731 | 15.7928 | 9.5355 | 16.0639 | 26.437 | 42.2299 | 0
12.9614 | 8.4548 | 8.0871 | 4.5498 | 8.7466 | 14.2324 | 12.9614 | 17.5112 | 26.2578 | 40.4902 | 12.9714 | 8.4548 | 8.0871 | 4.5498 | 8.7466 | 14.2324 | 12.9614 | 17.5112 | 26.2578 | 40.4902 | 0
12.3123 | 7.6568 | 7.0683 | 5.8302 | 9.7843 | 10.9761 | 12.3123 | 18.1424 | 27.9268 | 38.9029 | 12.3223 | 7.6568 | 7.0683 | 5.8302 | 9.7843 | 10.9761 | 12.3123 | 18.1424 | 27.9268 | 38.9029 | 0
-5.8513 | 10.4613 | 7.1838 | 5.5352 | 14.1151 | 14.9184 | 10.4613 | 15.9965 | 30.1116 | 45.03 | -5.8413 | 10.4613 | 7.1838 | 5.5352 | 14.1151 | 14.9184 | 10.4613 | 15.9965 | 30.1116 | 45.03 | 0
1.3684 | 8.9852 | 6.2122 | 7.0442 | 5.8895 | 10.9321 | 8.9852 | 16.0294 | 21.9189 | 32.851 | 1.3784 | 8.9852 | 6.2122 | 7.0442 | 5.8895 | 10.9321 | 8.9852 | 16.0294 | 21.9189 | 32.851 | 0
17.9931 | 7.8972 | 10.5727 | 8.9182 | 14.4841 | 8.4521 | 17.9931 | 26.9112 | 41.3954 | 49.8475 | 18.0031 | 7.8972 | 10.5727 | 8.9182 | 14.4841 | 8.4521 | 17.9931 | 26.9112 | 41.3954 | 49.8475 | 0
0.4603 | 9.8008 | 7.135 | 7.7334 | 10.9306 | 10.2096 | 9.8008 | 17.5342 | 28.4648 | 38.6744 | 0.4703 | 9.8008 | 7.135 | 7.7334 | 10.9306 | 10.2096 | 9.8008 | 17.5342 | 28.4648 | 38.6744 | 0
3.2579 | 8.9405 | 7.7296 | 5.0049 | 9.8681 | 11.0294 | 8.9405 | 13.9454 | 23.8135 | 34.8428 | 3.2679 | 8.9405 | 7.7296 | 5.0049 | 9.8681 | 11.0294 | 8.9405 | 13.9454 | 23.8135 | 34.8428 | 0
11.5443 | 10.23 | 8.361 | 6.6698 | 11.891 | 10.918 | 11.5443 | 18.2141 | 30.1051 | 41.0231 | 11.5543 | 10.23 | 8.361 | 6.6698 | 11.891 | 10.918 | 11.5443 | 18.2141 | 30.1051 | 41.0231 | 0
2.7064 | 8.107 | 6.3704 | 7.4591 | 16.2185 | 13.0929 | 8.107 | 15.5661 | 31.7847 | 44.8776 | 2.7164 | 8.107 | 6.3704 | 7.4591 | 16.2185 | 13.0929 | 8.107 | 15.5661 | 31.7847 | 44.8776 | 0
-4.7558 | 10.7744 | 4.2271 | 5.7506 | 6.0961 | 10.1264 | 10.7744 | 16.525 | 22.6211 | 32.7474 | -4.7458 | 10.7744 | 4.2271 | 5.7506 | 6.0961 | 10.1264 | 10.7744 | 16.525 | 22.6211 | 32.7474 | 0
1.0427 | 8.5964 | 9.5066 | 10.6925 | 7.4542 | 16.1334 | 8.5964 | 19.2889 | 26.743 | 42.8764 | 1.0527 | 8.5964 | 9.5066 | 10.6925 | 7.4542 | 16.1334 | 8.5964 | 19.2889 | 26.743 | 42.8764 | 0
-2.0843 | 7.676 | 8.6627 | 10.4965 | 10.6184 | 21.2389 | 7.676 | 18.1724 | 28.7908 | 50.0297 | -2.0743 | 7.676 | 8.6627 | 10.4965 | 10.6184 | 21.2389 | 7.676 | 18.1724 | 28.7908 | 50.0297 | 0
2.5518 | 9.8213 | 5.5738 | 4.9608 | 12.6806 | 12.6367 | 9.8213 | 14.7822 | 27.4627 | 40.0994 | 2.5618 | 9.8213 | 5.5738 | 4.9608 | 12.6806 | 12.6367 | 9.8213 | 14.7822 | 27.4627 | 40.0994 | 0
-2.1814 | 8.7187 | 8.6699 | 7.6124 | 9.8328 | 15.5371 | 8.7187 | 16.3311 | 26.1639 | 41.701 | -2.1714 | 8.7187 | 8.6699 | 7.6124 | 9.8328 | 15.5371 | 8.7187 | 16.3311 | 26.1639 | 41.701 | 0
11.957 | 9.5333 | 5.6168 | 10.4537 | 16.4142 | 14.1748 | 11.957 | 22.4107 | 38.8249 | 52.9997 | 11.967 | 9.5333 | 5.6168 | 10.4537 | 16.4142 | 14.1748 | 11.957 | 22.4107 | 38.8249 | 52.9997 | 0
5.7453 | 9.2587 | 7.9669 | 6.7196 | 12.5161 | 7.6164 | 9.2587 | 15.9783 | 28.4944 | 36.1109 | 5.7553 | 9.2587 | 7.9669 | 6.7196 | 12.5161 | 7.6164 | 9.2587 | 15.9783 | 28.4944 | 36.1109 | 0
-1.4135 | 10.7781 | 7.5896 | 7.2056 | 13.5332 | 14.4818 | 10.7781 | 17.9837 | 31.5169 | 45.9987 | -1.4035 | 10.7781 | 7.5896 | 7.2056 | 13.5332 | 14.4818 | 10.7781 | 17.9837 | 31.5169 | 45.9987 | 0
-5.833 | 8.8792 | 6.6337 | 7.7935 | 9.2697 | 13.1996 | 8.8792 | 16.6727 | 25.9424 | 39.142 | -5.823 | 8.8792 | 6.6337 | 7.7935 | 9.2697 | 13.1996 | 8.8792 | 16.6727 | 25.9424 | 39.142 | 0
-4.1802 | 8.3331 | 8.6024 | 7.7022 | 7.4293 | 16.7905 | 8.3331 | 16.0353 | 23.4646 | 40.2552 | -4.1702 | 8.3331 | 8.6024 | 7.7022 | 7.4293 | 16.7905 | 8.3331 | 16.0353 | 23.4646 | 40.2552 | 0
-3.0893 | 8.7795 | 4.6919 | 5.0395 | 17.2973 | 8.1141 | 8.7795 | 13.819 | 31.1163 | 39.2303 | -3.0793 | 8.7795 | 4.6919 | 5.0395 | 17.2973 | 8.1141 | 8.7795 | 13.819 | 31.1163 | 39.2303 | 0
1.3453 | 9.8567 | 8.0875 | 7.863 | 15.5073 | 11.7226 | 9.8567 | 17.7197 | 33.2269 | 44.9495 | 1.3553 | 9.8567 | 8.0875 | 7.863 | 15.5073 | 11.7226 | 9.8567 | 17.7197 | 33.2269 | 44.9495 | 0
-1.6802 | 11.1578 | 8.5871 | 6.0532 | 5.0958 | 11.5586 | 11.1578 | 17.211 | 22.3068 | 33.8654 | -1.6702 | 11.1578 | 8.5871 | 6.0532 | 5.0958 | 11.5586 | 11.1578 | 17.211 | 22.3068 | 33.8654 | 0
7.0491 | 11.4082 | 11.3547 | 10.003 | 4.8019 | 12.0863 | 11.4082 | 21.4112 | 26.2131 | 38.2994 | 7.0591 | 11.4082 | 11.3547 | 10.003 | 4.8019 | 12.0863 | 11.4082 | 21.4112 | 26.2131 | 38.2994 | 0
-4.8543 | 8.4422 | 8.1515 | 6.4112 | 12.0987 | 11.1084 | 8.4422 | 14.8535 | 26.9521 | 38.0605 | -4.8443 | 8.4422 | 8.1515 | 6.4112 | 12.0987 | 11.1084 | 8.4422 | 14.8535 | 26.9521 | 38.0605 | 0
3.2746 | 9.5739 | 12.0537 | 9.0399 | 3.626 | 13.0119 | 9.5739 | 18.6138 | 22.2398 | 35.2517 | 3.2846 | 9.5739 | 12.0537 | 9.0399 | 3.626 | 13.0119 | 9.5739 | 18.6138 | 22.2398 | 35.2517 | 0
-3.4661 | 8.4814 | 7.1993 | 8.2936 | 9.9288 | 16.3069 | 8.4814 | 16.7751 | 26.7039 | 43.0108 | -3.4561 | 8.4814 | 7.1993 | 8.2936 | 9.9288 | 16.3069 | 8.4814 | 16.7751 | 26.7039 | 43.0108 | 0
2.093 | 8.3746 | 4.7856 | 3.5066 | 9.6125 | 9.4511 | 8.3746 | 11.8813 | 21.4937 | 30.9449 | 2.103 | 8.3746 | 4.7856 | 3.5066 | 9.6125 | 9.4511 | 8.3746 | 11.8813 | 21.4937 | 30.9449 | 0
0.24659 | 8.7512 | 8.6792 | 4.4544 | 11.8812 | 15.3464 | 8.7512 | 13.2056 | 25.0868 | 40.4332 | 0.25659 | 8.7512 | 8.6792 | 4.4544 | 11.8812 | 15.3464 | 8.7512 | 13.2056 | 25.0868 | 40.4332 | 0
3.4902 | 9.005 | 8.4363 | 7.768 | 15.3191 | 17.8125 | 9.005 | 16.7729 | 32.092 | 49.9046 | 3.5002 | 9.005 | 8.4363 | 7.768 | 15.3191 | 17.8125 | 9.005 | 16.7729 | 32.092 | 49.9046 | 0
8.6555 | 9.8088 | 9.8847 | 5.3643 | 9.7339 | 10.2525 | 9.8088 | 15.1731 | 24.907 | 35.1595 | 8.6655 | 9.8088 | 9.8847 | 5.3643 | 9.7339 | 10.2525 | 9.8088 | 15.1731 | 24.907 | 35.1595 | 0
3.146 | 8.155 | 7.3207 | 6.0265 | 10.3869 | 14.9379 | 8.155 | 14.1815 | 24.5684 | 39.5064 | 3.156 | 8.155 | 7.3207 | 6.0265 | 10.3869 | 14.9379 | 8.155 | 14.1815 | 24.5684 | 39.5064 | 0
1.4956 | 9.6613 | 6.4114 | 5.6353 | 12.8197 | 11.5223 | 9.6613 | 15.2966 | 28.1163 | 39.6387 | 1.5056 | 9.6613 | 6.4114 | 5.6353 | 12.8197 | 11.5223 | 9.6613 | 15.2966 | 28.1163 | 39.6387 | 0
1.6711 | 9.1854 | 7.2678 | 9.0776 | 12.1524 | 11.1106 | 9.1854 | 18.263 | 30.4154 | 41.5261 | 1.6811 | 9.1854 | 7.2678 | 9.0776 | 12.1524 | 11.1106 | 9.1854 | 18.263 | 30.4154 | 41.5261 | 0
-3.4751 | 8.6286 | 8.191 | 5.9039 | 9.6383 | 11.9293 | 8.6286 | 14.5326 | 24.1708 | 36.1001 | -3.4651 | 8.6286 | 8.191 | 5.9039 | 9.6383 | 11.9293 | 8.6286 | 14.5326 | 24.1708 | 36.1001 | 0
8.667 | 8.7079 | 9.2056 | 9.5167 | 15.016 | 11.236 | 8.7079 | 18.2246 | 33.2406 | 44.4766 | 8.677 | 8.7079 | 9.2056 | 9.5167 | 15.016 | 11.236 | 8.7079 | 18.2246 | 33.2406 | 44.4766 | 0
1.7943 | 9.4806 | 6.2167 | 8.6986 | 11.1957 | 9.2692 | 9.4806 | 18.1792 | 29.3749 | 38.6441 | 1.8043 | 9.4806 | 6.2167 | 8.6986 | 11.1957 | 9.2692 | 9.4806 | 18.1792 | 29.3749 | 38.6441 | 0
3.8872 | 11.5359 | 3.837 | 7.6733 | 12.9645 | 13.946 | 11.5359 | 19.2092 | 32.1736 | 46.1196 | 3.8972 | 11.5359 | 3.837 | 7.6733 | 12.9645 | 13.946 | 11.5359 | 19.2092 | 32.1736 | 46.1196 | 0
-4.097 | 9.6789 | 6.3264 | 7.9401 | 3.7716 | 7.7795 | 9.6789 | 17.619 | 21.3906 | 29.1701 | -4.087 | 9.6789 | 6.3264 | 7.9401 | 3.7716 | 7.7795 | 9.6789 | 17.619 | 21.3906 | 29.1701 | 0
-1.4121 | 10.6166 | 6.3614 | 8.5328 | 8.7474 | 9.1653 | 10.6166 | 19.1494 | 27.8968 | 37.0621 | -1.4021 | 10.6166 | 6.3614 | 8.5328 | 8.7474 | 9.1653 | 10.6166 | 19.1494 | 27.8968 | 37.0621 | 0
0.65651 | 8.9704 | 7.144 | 7.2507 | 8.1299 | 13.6657 | 8.9704 | 16.221 | 24.3509 | 38.0166 | 0.66651 | 8.9704 | 7.144 | 7.2507 | 8.1299 | 13.6657 | 8.9704 | 16.221 | 24.3509 | 38.0166 | 0
3.5415 | 10.0223 | 10.5317 | 8.0438 | 9.2017 | 12.3255 | 10.0223 | 18.066 | 27.2677 | 39.5932 | 3.5515 | 10.0223 | 10.5317 | 8.0438 | 9.2017 | 12.3255 | 10.0223 | 18.066 | 27.2677 | 39.5932 | 0
0.60349 | 10.9905 | 7.9753 | 5.5133 | 5.2348 | 11.8384 | 10.9905 | 16.5038 | 21.7386 | 33.577 | 0.61349 | 10.9905 | 7.9753 | 5.5133 | 5.2348 | 11.8384 | 10.9905 | 16.5038 | 21.7386 | 33.577 | 0
8.8883 | 10.3867 | 8.6679 | 8.5871 | 12.5954 | 11.4568 | 10.3867 | 18.9738 | 31.5692 | 43.026 | 8.8983 | 10.3867 | 8.6679 | 8.5871 | 12.5954 | 11.4568 | 10.3867 | 18.9738 | 31.5692 | 43.026 | 0
-3.4856 | 11.1667 | 9.8769 | 9.6205 | 6.27 | 6.665 | 11.1667 | 20.7871 | 27.0572 | 33.7222 | -3.4756 | 11.1667 | 9.8769 | 9.6205 | 6.27 | 6.665 | 11.1667 | 20.7871 | 27.0572 | 33.7222 | 0
-6.1371 | 9.5248 | 7.4536 | 6.2652 | 7.9369 | 9.3704 | 9.5248 | 15.79 | 23.7269 | 33.0973 | -6.1271 | 9.5248 | 7.4536 | 6.2652 | 7.9369 | 9.3704 | 9.5248 | 15.79 | 23.7269 | 33.0973 | 0
11.8853 | 7.7798 | 6.2794 | 6.4592 | 10.7182 | 12.3762 | 11.8853 | 18.3445 | 29.0627 | 41.4389 | 11.8953 | 7.7798 | 6.2794 | 6.4592 | 10.7182 | 12.3762 | 11.8853 | 18.3445 | 29.0627 | 41.4389 | 0
-0.93943 | 10.6212 | 5.9354 | 5.4383 | 10.5699 | 8.6881 | 10.6212 | 16.0595 | 26.6295 | 35.3176 | -0.92943 | 10.6212 | 5.9354 | 5.4383 | 10.5699 | 8.6881 | 10.6212 | 16.0595 | 26.6295 | 35.3176 | 0
1.5875 | 10.0734 | 6.9767 | 7.9628 | 11.6572 | 13.3549 | 10.0734 | 18.0362 | 29.6934 | 43.0483 | 1.5975 | 10.0734 | 6.9767 | 7.9628 | 11.6572 | 13.3549 | 10.0734 | 18.0362 | 29.6934 | 43.0483 | 0
9.8438 | 11.1684 | 11.1008 | 8.6581 | 9.0919 | 14.7846 | 11.1684 | 19.8265 | 28.9184 | 43.703 | 9.8538 | 11.1684 | 11.1008 | 8.6581 | 9.0919 | 14.7846 | 11.1684 | 19.8265 | 28.9184 | 43.703 | 0
-10.8273 | 10.0211 | 9.4164 | 3.7058 | 9.0098 | 6.7648 | 10.0211 | 13.7269 | 22.7367 | 29.5015 | -10.8173 | 10.0211 | 9.4164 | 3.7058 | 9.0098 | 6.7648 | 10.0211 | 13.7269 | 22.7367 | 29.5015 | 0
-0.5587 | 8.7434 | 7.1696 | 6.9126 | 14.7827 | 11.5717 | 8.7434 | 15.656 | 30.4387 | 42.0103 | -0.5487 | 8.7434 | 7.1696 | 6.9126 | 14.7827 | 11.5717 | 8.7434 | 15.656 | 30.4387 | 42.0103 | 0
1.8992 | 8.7833 | 9.0013 | 8.3045 | 6.9422 | 11.3436 | 8.7833 | 17.0877 | 24.03 | 35.3736 | 1.9092 | 8.7833 | 9.0013 | 8.3045 | 6.9422 | 11.3436 | 8.7833 | 17.0877 | 24.03 | 35.3736 | 0
8.7852 | 9.4512 | 7.4976 | 7.0219 | 15.3086 | 8.106 | 9.4512 | 16.4731 | 31.7816 | 39.8877 | 8.7952 | 9.4512 | 7.4976 | 7.0219 | 15.3086 | 8.106 | 9.4512 | 16.4731 | 31.7816 | 39.8877 | 0
11.3115 | 7.92 | 9.421 | 9.156 | 10.466 | 13.8017 | 11.3115 | 20.4675 | 30.9335 | 44.7352 | 11.3215 | 7.92 | 9.421 | 9.156 | 10.466 | 13.8017 | 11.3115 | 20.4675 | 30.9335 | 44.7352 | 0
8.0423 | 7.3227 | 6.6874 | 6.0513 | 13.2734 | 15.3619 | 8.0423 | 14.0936 | 27.367 | 42.7289 | 8.0523 | 7.3227 | 6.6874 | 6.0513 | 13.2734 | 15.3619 | 8.0423 | 14.0936 | 27.367 | 42.7289 | 0
-9.9703 | 9.3781 | 8.3695 | 6.5115 | 8.3731 | 12.2552 | 9.3781 | 15.8896 | 24.2627 | 36.5179 | -9.9603 | 9.3781 | 8.3695 | 6.5115 | 8.3731 | 12.2552 | 9.3781 | 15.8896 | 24.2627 | 36.5179 | 0
8.7659 | 8.4709 | 5.3069 | 11.8497 | 15.524 | 10.2178 | 8.7659 | 20.6157 | 36.1397 | 46.3574 | 8.7759 | 8.4709 | 5.3069 | 11.8497 | 15.524 | 10.2178 | 8.7659 | 20.6157 | 36.1397 | 46.3574 | 0
3.3636 | 9.7867 | 10.8937 | 5.9789 | 15.1636 | 12.8652 | 9.7867 | 15.7655 | 30.9291 | 43.7943 | 3.3736 | 9.7867 | 10.8937 | 5.9789 | 15.1636 | 12.8652 | 9.7867 | 15.7655 | 30.9291 | 43.7943 | 0
-1.6981 | 7.8783 | 9.394 | 5.5531 | 13.9323 | 13.4304 | 7.8783 | 13.4314 | 27.3638 | 40.7942 | -1.6881 | 7.8783 | 9.394 | 5.5531 | 13.9323 | 13.4304 | 7.8783 | 13.4314 | 27.3638 | 40.7942 | 0
-2.8972 | 9.0703 | 8.2988 | 8.4058 | 13.7846 | 11.3923 | 9.0703 | 17.4761 | 31.2607 | 42.653 | -2.8872 | 9.0703 | 8.2988 | 8.4058 | 13.7846 | 11.3923 | 9.0703 | 17.4761 | 31.2607 | 42.653 | 0
-1.4339 | 8.7673 | 8.135 | 7.2371 | 10.2445 | 11.3938 | 8.7673 | 16.0044 | 26.2488 | 37.6426 | -1.4239 | 8.7673 | 8.135 | 7.2371 | 10.2445 | 11.3938 | 8.7673 | 16.0044 | 26.2488 | 37.6426 | 0
4.6936 | 7.9414 | 8.5498 | 6.6427 | 8.2099 | 14.0603 | 7.9414 | 14.5842 | 22.7941 | 36.8544 | 4.7036 | 7.9414 | 8.5498 | 6.6427 | 8.2099 | 14.0603 | 7.9414 | 14.5842 | 22.7941 | 36.8544 | 0
2.4916 | 8.4311 | 9.3499 | 4.6645 | 13.6445 | 12.273 | 8.4311 | 13.0956 | 26.7401 | 39.0131 | 2.5016 | 8.4311 | 9.3499 | 4.6645 | 13.6445 | 12.273 | 8.4311 | 13.0956 | 26.7401 | 39.0131 | 0
-1.269 | 8.2578 | 9.43 | 5.3895 | 3.9022 | 15.0768 | 8.2578 | 13.6473 | 17.6878 | 32.7645 | -1.259 | 8.2578 | 9.43 | 5.3895 | 3.9022 | 15.0768 | 8.2578 | 13.6473 | 17.6878 | 32.7645 | 0
0.27099 | 8.9442 | 8.4124 | 4.9897 | 11.9021 | 9.6545 | 8.9442 | 13.9338 | 25.8359 | 35.4904 | 0.28099 | 8.9442 | 8.4124 | 4.9897 | 11.9021 | 9.6545 | 8.9442 | 13.9338 | 25.8359 | 35.4904 | 0
5.9102 | 8.4439 | 7.6361 | 7.2749 | 7.2711 | 13.8623 | 8.4439 | 15.7189 | 22.99 | 36.8522 | 5.9202 | 8.4439 | 7.6361 | 7.2749 | 7.2711 | 13.8623 | 8.4439 | 15.7189 | 22.99 | 36.8522 | 0
4.0505 | 9.3495 | 6.9709 | 5.9779 | 10.947 | 8.972 | 9.3495 | 15.3274 | 26.2744 | 35.2463 | 4.0605 | 9.3495 | 6.9709 | 5.9779 | 10.947 | 8.972 | 9.3495 | 15.3274 | 26.2744 | 35.2463 | 0
-5.2279 | 7.7615 | 11.3335 | 6.3532 | 8.5729 | 13.5086 | 7.7615 | 14.1146 | 22.6875 | 36.196 | -5.2179 | 7.7615 | 11.3335 | 6.3532 | 8.5729 | 13.5086 | 7.7615 | 14.1146 | 22.6875 | 36.196 | 0
8.0039 | 7.5729 | 10.4196 | 5.6833 | 6.8112 | 10.1906 | 8.0039 | 13.6872 | 20.4984 | 30.6889 | 8.0139 | 7.5729 | 10.4196 | 5.6833 | 6.8112 | 10.1906 | 8.0039 | 13.6872 | 20.4984 | 30.6889 | 0
-5.0012 | 8.5 | 10.5348 | 6.2361 | 11.2938 | 14.0152 | 8.5 | 14.7361 | 26.0299 | 40.0451 | -4.9912 | 8.5 | 10.5348 | 6.2361 | 11.2938 | 14.0152 | 8.5 | 14.7361 | 26.0299 | 40.0451 | 0
-1.1925 | 8.7313 | 6.6 | 6.8727 | 14.6346 | 12.574 | 8.7313 | 15.604 | 30.2386 | 42.8127 | -1.1825 | 8.7313 | 6.6 | 6.8727 | 14.6346 | 12.574 | 8.7313 | 15.604 | 30.2386 | 42.8127 | 0
-1.7703 | 8.5703 | 8.4435 | 4.44 | 10.8179 | 12.9627 | 8.5703 | 13.0103 | 23.8282 | 36.7909 | -1.7603 | 8.5703 | 8.4435 | 4.44 | 10.8179 | 12.9627 | 8.5703 | 13.0103 | 23.8282 | 36.7909 | 0
5.8587 | 9.5176 | 7.197 | 5.6999 | 6.5572 | 14.5919 | 9.5176 | 15.2176 | 21.7748 | 36.3667 | 5.8687 | 9.5176 | 7.197 | 5.6999 | 6.5572 | 14.5919 | 9.5176 | 15.2176 | 21.7748 | 36.3667 | 0
13.236 | 8.6731 | 6.0406 | 6.8475 | 9.5256 | 13.8747 | 13.236 | 20.0834 | 29.609 | 43.4837 | 13.246 | 8.6731 | 6.0406 | 6.8475 | 9.5256 | 13.8747 | 13.236 | 20.0834 | 29.609 | 43.4837 | 0
0.76532 | 8.6178 | 10.0177 | 7.7306 | 10.484 | 8.2778 | 8.6178 | 16.3484 | 26.8324 | 35.1101 | 0.77532 | 8.6178 | 10.0177 | 7.7306 | 10.484 | 8.2778 | 8.6178 | 16.3484 | 26.8324 | 35.1101 | 0
0.81644 | 9.6932 | 7.344 | 7.2831 | 9.9282 | 9.7762 | 9.6932 | 16.9763 | 26.9044 | 36.6806 | 0.82644 | 9.6932 | 7.344 | 7.2831 | 9.9282 | 9.7762 | 9.6932 | 16.9763 | 26.9044 | 36.6806 | 0
0.39352 | 9.2865 | 4.5056 | 5.8528 | 17.4291 | 9.6285 | 9.2865 | 15.1393 | 32.5684 | 42.197 | 0.40352 | 9.2865 | 4.5056 | 5.8528 | 17.4291 | 9.6285 | 9.2865 | 15.1393 | 32.5684 | 42.197 | 0
1.6874 | 9.8255 | 7.2931 | 5.9973 | 9.7503 | 8.7691 | 9.8255 | 15.8228 | 25.5731 | 34.3421 | 1.6974 | 9.8255 | 7.2931 | 5.9973 | 9.7503 | 8.7691 | 9.8255 | 15.8228 | 25.5731 | 34.3421 | 0
0.13726 | 7.9581 | 3.5563 | 8.288 | 15.0141 | 11.933 | 7.9581 | 16.2461 | 31.2602 | 43.1932 | 0.14726 | 7.9581 | 3.5563 | 8.288 | 15.0141 | 11.933 | 7.9581 | 16.2461 | 31.2602 | 43.1932 | 0
8.225 | 9.7083 | 11.2462 | 8.4774 | 10.7638 | 13.7857 | 9.7083 | 18.1857 | 28.9495 | 42.7352 | 8.235 | 9.7083 | 11.2462 | 8.4774 | 10.7638 | 13.7857 | 9.7083 | 18.1857 | 28.9495 | 42.7352 | 0
-5.3103 | 9.8603 | 6.8888 | 7.8929 | 8.2373 | 15.0954 | 9.8603 | 17.7532 | 25.9906 | 41.0859 | -5.3003 | 9.8603 | 6.8888 | 7.8929 | 8.2373 | 15.0954 | 9.8603 | 17.7532 | 25.9906 | 41.0859 | 0
4.1392 | 6.2658 | 7.5752 | 6.216 | 8.7323 | 13.5661 | 6.2658 | 12.4817 | 21.214 | 34.7801 | 4.1492 | 6.2658 | 7.5752 | 6.216 | 8.7323 | 13.5661 | 6.2658 | 12.4817 | 21.214 | 34.7801 | 0
0.049625 | 9.1081 | 3.7996 | 8.9597 | 7.8857 | 4.6145 | 9.1081 | 18.0678 | 25.9535 | 30.568 | 0.059625 | 9.1081 | 3.7996 | 8.9597 | 7.8857 | 4.6145 | 9.1081 | 18.0678 | 25.9535 | 30.568 | 0
5.7412 | 8.0604 | 5.4946 | 7.7653 | 11.3006 | 9.1018 | 8.0604 | 15.8257 | 27.1264 | 36.2281 | 5.7512 | 8.0604 | 5.4946 | 7.7653 | 11.3006 | 9.1018 | 8.0604 | 15.8257 | 27.1264 | 36.2281 | 0
1.2171 | 9.2581 | 7.449 | 9.6443 | 13.8402 | 14.627 | 9.2581 | 18.9024 | 32.7426 | 47.3696 | 1.2271 | 9.2581 | 7.449 | 9.6443 | 13.8402 | 14.627 | 9.2581 | 18.9024 | 32.7426 | 47.3696 | 0
-8.7968 | 8.5186 | 7.9941 | 10.041 | 14.2794 | 11.5705 | 8.5186 | 18.5596 | 32.839 | 44.4095 | -8.7868 | 8.5186 | 7.9941 | 10.041 | 14.2794 | 11.5705 | 8.5186 | 18.5596 | 32.839 | 44.4095 | 0
3.1694 | 8.7356 | 9.728 | 4.5991 | 5.7578 | 14.8988 | 8.7356 | 13.3346 | 19.0924 | 33.9912 | 3.1794 | 8.7356 | 9.728 | 4.5991 | 5.7578 | 14.8988 | 8.7356 | 13.3346 | 19.0924 | 33.9912 | 0
-5.4742 | 10.0831 | 10.5573 | 6.6513 | 7.6763 | 17.146 | 10.0831 | 16.7344 | 24.4108 | 41.5568 | -5.4642 | 10.0831 | 10.5573 | 6.6513 | 7.6763 | 17.146 | 10.0831 | 16.7344 | 24.4108 | 41.5568 | 0
9.6801 | 8.7624 | 9.268 | 6.985 | 12.6417 | 15.7707 | 9.6801 | 16.665 | 29.3068 | 45.0775 | 9.6901 | 8.7624 | 9.268 | 6.985 | 12.6417 | 15.7707 | 9.6801 | 16.665 | 29.3068 | 45.0775 | 0
6.1299 | 8.7753 | 3.6604 | 4.285 | 13.7396 | 11.711 | 8.7753 | 13.0604 | 26.8 | 38.511 | 6.1399 | 8.7753 | 3.6604 | 4.285 | 13.7396 | 11.711 | 8.7753 | 13.0604 | 26.8 | 38.511 | 0
5.665 | 9.2408 | 6.8872 | 7.0208 | 11.4468 | 13.0991 | 9.2408 | 16.2616 | 27.7084 | 40.8075 | 5.675 | 9.2408 | 6.8872 | 7.0208 | 11.4468 | 13.0991 | 9.2408 | 16.2616 | 27.7084 | 40.8075 | 0
-5.6302 | 9.4771 | 8.3503 | 4.0041 | 5.6266 | 9.6174 | 9.4771 | 13.4812 | 19.1078 | 28.7251 | -5.6202 | 9.4771 | 8.3503 | 4.0041 | 5.6266 | 9.6174 | 9.4771 | 13.4812 | 19.1078 | 28.7251 | 0
11.2259 | 10.0935 | 9.8384 | 6.0349 | 10.9077 | 17.1332 | 11.2259 | 17.2608 | 28.1685 | 45.3017 | 11.2359 | 10.0935 | 9.8384 | 6.0349 | 10.9077 | 17.1332 | 11.2259 | 17.2608 | 28.1685 | 45.3017 | 0
7.8152 | 7.823 | 8.3867 | 5.6115 | 11.5597 | 10.4889 | 7.823 | 13.4345 | 24.9942 | 35.4831 | 7.8252 | 7.823 | 8.3867 | 5.6115 | 11.5597 | 10.4889 | 7.823 | 13.4345 | 24.9942 | 35.4831 | 0
-1.7085 | 7.8779 | 9.691 | 8.7946 | 10.4249 | 13.708 | 7.8779 | 16.6724 | 27.0973 | 40.8052 | -1.6985 | 7.8779 | 9.691 | 8.7946 | 10.4249 | 13.708 | 7.8779 | 16.6724 | 27.0973 | 40.8052 | 0
4.302 | 7.5897 | 9.5462 | 6.2301 | 13.557 | 9.8564 | 7.5897 | 13.8198 | 27.3768 | 37.2331 | 4.312 | 7.5897 | 9.5462 | 6.2301 | 13.557 | 9.8564 | 7.5897 | 13.8198 | 27.3768 | 37.2331 | 0
-1.8786 | 9.4092 | 11.4466 | 7.6094 | 12.698 | 13.888 | 9.4092 | 17.0186 | 29.7166 | 43.6046 | -1.8686 | 9.4092 | 11.4466 | 7.6094 | 12.698 | 13.888 | 9.4092 | 17.0186 | 29.7166 | 43.6046 | 0
-9.2818 | 9.0253 | 5.2612 | 6.7151 | 10.0358 | 11.5392 | 9.0253 | 15.7403 | 25.7761 | 37.3153 | -9.2718 | 9.0253 | 5.2612 | 6.7151 | 10.0358 | 11.5392 | 9.0253 | 15.7403 | 25.7761 | 37.3153 | 0
6.5004 | 9.8665 | 10.65 | 6.6424 | 9.8127 | 13.9474 | 9.8665 | 16.509 | 26.3216 | 40.2691 | 6.5104 | 9.8665 | 10.65 | 6.6424 | 9.8127 | 13.9474 | 9.8665 | 16.509 | 26.3216 | 40.2691 | 0
0.89322 | 8.9726 | 10.227 | 4.7314 | 5.7524 | 14.0972 | 8.9726 | 13.7039 | 19.4564 | 33.5536 | 0.90322 | 8.9726 | 10.227 | 4.7314 | 5.7524 | 14.0972 | 8.9726 | 13.7039 | 19.4564 | 33.5536 | 0
4.1593 | 9.3292 | 10.9436 | 9.1097 | 12.8244 | 11.0685 | 9.3292 | 18.4389 | 31.2633 | 42.3317 | 4.1693 | 9.3292 | 10.9436 | 9.1097 | 12.8244 | 11.0685 | 9.3292 | 18.4389 | 31.2633 | 42.3317 | 0
0.46438 | 9.1965 | 8.0504 | 6.3662 | 9.9264 | 11.7965 | 9.1965 | 15.5627 | 25.4891 | 37.2856 | 0.47438 | 9.1965 | 8.0504 | 6.3662 | 9.9264 | 11.7965 | 9.1965 | 15.5627 | 25.4891 | 37.2856 | 0
18.2893 | 10.3768 | 7.8273 | 7.5317 | 14.1722 | 7.5589 | 18.2893 | 25.821 | 39.9932 | 47.552 | 18.2993 | 10.3768 | 7.8273 | 7.5317 | 14.1722 | 7.5589 | 18.2893 | 25.821 | 39.9932 | 47.552 | 0
-1.4053 | 8.9355 | 6.6988 | 6.1687 | 7.6422 | 9.1789 | 8.9355 | 15.1042 | 22.7464 | 31.9253 | -1.3953 | 8.9355 | 6.6988 | 6.1687 | 7.6422 | 9.1789 | 8.9355 | 15.1042 | 22.7464 | 31.9253 | 0
9.7408 | 8.9163 | 7.6803 | 8.4528 | 10.1955 | 9.7403 | 9.7408 | 18.1936 | 28.3892 | 38.1295 | 9.7508 | 8.9163 | 7.6803 | 8.4528 | 10.1955 | 9.7403 | 9.7408 | 18.1936 | 28.3892 | 38.1295 | 0
1.9404 | 10.5378 | 6.9759 | 7.3814 | 7.6168 | 12.9426 | 10.5378 | 17.9192 | 25.536 | 38.4786 | 1.9504 | 10.5378 | 6.9759 | 7.3814 | 7.6168 | 12.9426 | 10.5378 | 17.9192 | 25.536 | 38.4786 | 0
10.506 | 7.789 | 7.8457 | 6.9592 | 1.197 | 7.8365 | 10.506 | 17.4652 | 18.6623 | 26.4987 | 10.516 | 7.789 | 7.8457 | 6.9592 | 1.197 | 7.8365 | 10.506 | 17.4652 | 18.6623 | 26.4987 | 0
3.9004 | 8.622 | 10.3816 | 8.9604 | 6.0088 | 8.9689 | 8.622 | 17.5824 | 23.5912 | 32.5601 | 3.9104 | 8.622 | 10.3816 | 8.9604 | 6.0088 | 8.9689 | 8.622 | 17.5824 | 23.5912 | 32.5601 | 0
-2.9051 | 10.023 | 10.5402 | 5.1688 | 6.6622 | 12.3456 | 10.023 | 15.1917 | 21.8539 | 34.1995 | -2.8951 | 10.023 | 10.5402 | 5.1688 | 6.6622 | 12.3456 | 10.023 | 15.1917 | 21.8539 | 34.1995 | 0
12.7506 | 9.7318 | 7.1009 | 4.8857 | 8.4035 | 10.1123 | 12.7506 | 17.6363 | 26.0398 | 36.1521 | 12.7606 | 9.7318 | 7.1009 | 4.8857 | 8.4035 | 10.1123 | 12.7506 | 17.6363 | 26.0398 | 36.1521 | 0
-4.9999 | 8.6686 | 8.913 | 7.7625 | 11.8454 | 9.0079 | 8.6686 | 16.431 | 28.2765 | 37.2844 | -4.9899 | 8.6686 | 8.913 | 7.7625 | 11.8454 | 9.0079 | 8.6686 | 16.431 | 28.2765 | 37.2844 | 0
15.6101 | 8.3767 | 7.1213 | 4.7083 | 5.6838 | 10.159 | 15.6101 | 20.3185 | 26.0023 | 36.1613 | 15.6201 | 8.3767 | 7.1213 | 4.7083 | 5.6838 | 10.159 | 15.6101 | 20.3185 | 26.0023 | 36.1613 | 0
-4.7356 | 9.1391 | 9.0762 | 7.3165 | 9.5458 | 9.7267 | 9.1391 | 16.4557 | 26.0015 | 35.7282 | -4.7256 | 9.1391 | 9.0762 | 7.3165 | 9.5458 | 9.7267 | 9.1391 | 16.4557 | 26.0015 | 35.7282 | 0
0.48987 | 8.8079 | 8.1973 | 6.078 | 8.4171 | 14.0738 | 8.8079 | 14.8859 | 23.303 | 37.3768 | 0.49987 | 8.8079 | 8.1973 | 6.078 | 8.4171 | 14.0738 | 8.8079 | 14.8859 | 23.303 | 37.3768 | 0
2.9902 | 9.2047 | 9.7003 | 7.1593 | 8.0185 | 10.5986 | 9.2047 | 16.364 | 24.3824 | 34.981 | 3.0002 | 9.2047 | 9.7003 | 7.1593 | 8.0185 | 10.5986 | 9.2047 | 16.364 | 24.3824 | 34.981 | 0
-8.7815 | 8.8159 | 8.5657 | 9.6848 | 11.9647 | 12.8281 | 8.8159 | 18.5008 | 30.4655 | 43.2936 | -8.7715 | 8.8159 | 8.5657 | 9.6848 | 11.9647 | 12.8281 | 8.8159 | 18.5008 | 30.4655 | 43.2936 | 0
15.0605 | 8.1139 | 5.9002 | 9.7614 | 15.4925 | 5.1331 | 15.0605 | 24.8219 | 40.3145 | 45.4475 | 15.0705 | 8.1139 | 5.9002 | 9.7614 | 15.4925 | 5.1331 | 15.0605 | 24.8219 | 40.3145 | 45.4475 | 0
-5.5297 | 6.2419 | 9.2142 | 7.1343 | 14.5274 | 12.3848 | 6.2419 | 13.3762 | 27.9037 | 40.2885 | -5.5197 | 6.2419 | 9.2142 | 7.1343 | 14.5274 | 12.3848 | 6.2419 | 13.3762 | 27.9037 | 40.2885 | 0
1.7243 | 10.0844 | 7.635 | 6.8426 | 14.8307 | 8.9232 | 10.0844 | 16.927 | 31.7577 | 40.6809 | 1.7343 | 10.0844 | 7.635 | 6.8426 | 14.8307 | 8.9232 | 10.0844 | 16.927 | 31.7577 | 40.6809 | 0
1.9348 | 7.9358 | 9.1466 | 6.3425 | 14.4173 | 13.6756 | 7.9358 | 14.2783 | 28.6956 | 42.3712 | 1.9448 | 7.9358 | 9.1466 | 6.3425 | 14.4173 | 13.6756 | 7.9358 | 14.2783 | 28.6956 | 42.3712 | 0
4.977 | 9.3968 | 9.7904 | 6.0221 | 14.2871 | 12.0726 | 9.3968 | 15.419 | 29.7061 | 41.7787 | 4.987 | 9.3968 | 9.7904 | 6.0221 | 14.2871 | 12.0726 | 9.3968 | 15.419 | 29.7061 | 41.7787 | 0
4.4824 | 7.9305 | 5.1868 | 5.9788 | 8.6109 | 13.4069 | 7.9305 | 13.9093 | 22.5202 | 35.9271 | 4.4924 | 7.9305 | 5.1868 | 5.9788 | 8.6109 | 13.4069 | 7.9305 | 13.9093 | 22.5202 | 35.9271 | 0
1.5336 | 9.0831 | 9.1363 | 4.721 | 8.717 | 11.1494 | 9.0831 | 13.804 | 22.5211 | 33.6705 | 1.5436 | 9.0831 | 9.1363 | 4.721 | 8.717 | 11.1494 | 9.0831 | 13.804 | 22.5211 | 33.6705 | 0
6.9618 | 9.5938 | 8.8931 | 7.5773 | 6.3041 | 12.7754 | 9.5938 | 17.1711 | 23.4751 | 36.2506 | 6.9718 | 9.5938 | 8.8931 | 7.5773 | 6.3041 | 12.7754 | 9.5938 | 17.1711 | 23.4751 | 36.2506 | 0
-2.8618 | 9.8706 | 11.8171 | 6.1229 | 10.7612 | 11.5819 | 9.8706 | 15.9936 | 26.7548 | 38.3367 | -2.8518 | 9.8706 | 11.8171 | 6.1229 | 10.7612 | 11.5819 | 9.8706 | 15.9936 | 26.7548 | 38.3367 | 0
5.7906 | 8.9002 | 9.2702 | 8.0728 | 11.7243 | 8.4431 | 8.9002 | 16.973 | 28.6972 | 37.1403 | 5.8006 | 8.9002 | 9.2702 | 8.0728 | 11.7243 | 8.4431 | 8.9002 | 16.973 | 28.6972 | 37.1403 | 0
8.3525 | 9.1076 | 4.5254 | 8.0174 | 7.3427 | 9.9378 | 9.1076 | 17.1249 | 24.4676 | 34.4055 | 8.3625 | 9.1076 | 4.5254 | 8.0174 | 7.3427 | 9.9378 | 9.1076 | 17.1249 | 24.4676 | 34.4055 | 0
0.0062421 | 8.8362 | 10.4174 | 7.9452 | 10.3369 | 8.8197 | 8.8362 | 16.7814 | 27.1184 | 35.9381 | 0.016242 | 8.8362 | 10.4174 | 7.9452 | 10.3369 | 8.8197 | 8.8362 | 16.7814 | 27.1184 | 35.9381 | 0
7.1012 | 8.8032 | 7.0145 | 5.2278 | 14.583 | 11.6264 | 8.8032 | 14.031 | 28.614 | 40.2404 | 7.1112 | 8.8032 | 7.0145 | 5.2278 | 14.583 | 11.6264 | 8.8032 | 14.031 | 28.614 | 40.2404 | 0
7.4417 | 9.2159 | 9.0964 | 3.9438 | 6.8608 | 12.3261 | 9.2159 | 13.1596 | 20.0204 | 32.3465 | 7.4517 | 9.2159 | 9.0964 | 3.9438 | 6.8608 | 12.3261 | 9.2159 | 13.1596 | 20.0204 | 32.3465 | 0
1.3376 | 9.5945 | 6.5017 | 9.408 | 7.3541 | 16.0563 | 9.5945 | 19.0025 | 26.3566 | 42.4129 | 1.3476 | 9.5945 | 6.5017 | 9.408 | 7.3541 | 16.0563 | 9.5945 | 19.0025 | 26.3566 | 42.4129 | 0
7.4577 | 9.1462 | 6.417 | 4.4933 | 12.757 | 8.58 | 9.1462 | 13.6394 | 26.3964 | 34.9764 | 7.4677 | 9.1462 | 6.417 | 4.4933 | 12.757 | 8.58 | 9.1462 | 13.6394 | 26.3964 | 34.9764 | 0
-0.72537 | 10.9649 | 6.5932 | 6.4316 | 11.6756 | 14.993 | 10.9649 | 17.3965 | 29.0721 | 44.065 | -0.71537 | 10.9649 | 6.5932 | 6.4316 | 11.6756 | 14.993 | 10.9649 | 17.3965 | 29.0721 | 44.065 | 0
1.2863 | 9.3409 | 10.4652 | 5.6197 | 10.4538 | 16.1532 | 9.3409 | 14.9606 | 25.4144 | 41.5675 | 1.2963 | 9.3409 | 10.4652 | 5.6197 | 10.4538 | 16.1532 | 9.3409 | 14.9606 | 25.4144 | 41.5675 | 0
8.569 | 9.7505 | 7.5516 | 6.9472 | 12.9358 | 4.902 | 9.7505 | 16.6977 | 29.6335 | 34.5354 | 8.579 | 9.7505 | 7.5516 | 6.9472 | 12.9358 | 4.902 | 9.7505 | 16.6977 | 29.6335 | 34.5354 | 0
9.0958 | 9.355 | 8.9249 | 6.4446 | 10.2371 | 8.1763 | 9.355 | 15.7996 | 26.0368 | 34.2131 | 9.1058 | 9.355 | 8.9249 | 6.4446 | 10.2371 | 8.1763 | 9.355 | 15.7996 | 26.0368 | 34.2131 | 0
6.4716 | 10.0374 | 6.1722 | 5.1395 | 16.0439 | 11.0694 | 10.0374 | 15.1769 | 31.2208 | 42.2902 | 6.4816 | 10.0374 | 6.1722 | 5.1395 | 16.0439 | 11.0694 | 10.0374 | 15.1769 | 31.2208 | 42.2902 | 0
-5.1991 | 9.1895 | 8.8635 | 4.98 | 11.8179 | 11.4612 | 9.1895 | 14.1695 | 25.9874 | 37.4486 | -5.1891 | 9.1895 | 8.8635 | 4.98 | 11.8179 | 11.4612 | 9.1895 | 14.1695 | 25.9874 | 37.4486 | 0
1.9545 | 9.5157 | 4.4565 | 4.323 | 15.5037 | 13.6161 | 9.5157 | 13.8387 | 29.3425 | 42.9586 | 1.9645 | 9.5157 | 4.4565 | 4.323 | 15.5037 | 13.6161 | 9.5157 | 13.8387 | 29.3425 | 42.9586 | 0
3.5918 | 10.7721 | 7.1413 | 9.0942 | 10.6796 | 9.0837 | 10.7721 | 19.8663 | 30.5459 | 39.6296 | 3.6018 | 10.7721 | 7.1413 | 9.0942 | 10.6796 | 9.0837 | 10.7721 | 19.8663 | 30.5459 | 39.6296 | 0
4.2792 | 7.9495 | 9.0538 | 7.5213 | 9.7308 | 12.7629 | 7.9495 | 15.4708 | 25.2015 | 37.9645 | 4.2892 | 7.9495 | 9.0538 | 7.5213 | 9.7308 | 12.7629 | 7.9495 | 15.4708 | 25.2015 | 37.9645 | 0
3.4831 | 8.3112 | 8.1057 | 6.9865 | 10.4048 | 11.9407 | 8.3112 | 15.2977 | 25.7025 | 37.6431 | 3.4931 | 8.3112 | 8.1057 | 6.9865 | 10.4048 | 11.9407 | 8.3112 | 15.2977 | 25.7025 | 37.6431 | 0
-4.2053 | 9.4348 | 8.3946 | 5.5893 | 9.5705 | 15.6552 | 9.4348 | 15.0241 | 24.5945 | 40.2497 | -4.1953 | 9.4348 | 8.3946 | 5.5893 | 9.5705 | 15.6552 | 9.4348 | 15.0241 | 24.5945 | 40.2497 | 0
6.2157 | 8.68 | 10.8987 | 8.0135 | 11.8678 | 11.0086 | 8.68 | 16.6936 | 28.5614 | 39.57 | 6.2257 | 8.68 | 10.8987 | 8.0135 | 11.8678 | 11.0086 | 8.68 | 16.6936 | 28.5614 | 39.57 | 0
-6.878 | 7.7896 | 8.767 | 6.668 | 8.6296 | 11.5796 | 7.7896 | 14.4576 | 23.0872 | 34.6668 | -6.868 | 7.7896 | 8.767 | 6.668 | 8.6296 | 11.5796 | 7.7896 | 14.4576 | 23.0872 | 34.6668 | 0
6.6197 | 8.5339 | 5.9345 | 7.1205 | 13.9376 | 6.7458 | 8.5339 | 15.6543 | 29.5919 | 36.3377 | 6.6297 | 8.5339 | 5.9345 | 7.1205 | 13.9376 | 6.7458 | 8.5339 | 15.6543 | 29.5919 | 36.3377 | 0
-1.487 | 9.1936 | 8.4788 | 4.6384 | 12.957 | 9.8862 | 9.1936 | 13.832 | 26.789 | 36.6751 | -1.477 | 9.1936 | 8.4788 | 4.6384 | 12.957 | 9.8862 | 9.1936 | 13.832 | 26.789 | 36.6751 | 0
1.683 | 8.7839 | 8.5891 | 6.4412 | 11.8349 | 12.1608 | 8.7839 | 15.2251 | 27.06 | 39.2209 | 1.693 | 8.7839 | 8.5891 | 6.4412 | 11.8349 | 12.1608 | 8.7839 | 15.2251 | 27.06 | 39.2209 | 0
0.093103 | 10.2854 | 5.9666 | 4.8124 | 10.8229 | 14.3024 | 10.2854 | 15.0979 | 25.9208 | 40.2232 | 0.1031 | 10.2854 | 5.9666 | 4.8124 | 10.8229 | 14.3024 | 10.2854 | 15.0979 | 25.9208 | 40.2232 | 0
8.7782 | 9.6066 | 5.7223 | 10.9042 | 14.9181 | 14.9891 | 9.6066 | 20.5108 | 35.4288 | 50.4179 | 8.7882 | 9.6066 | 5.7223 | 10.9042 | 14.9181 | 14.9891 | 9.6066 | 20.5108 | 35.4288 | 50.4179 | 0
7.2822 | 8.8343 | 11.699 | 3.172 | 5.4961 | 13.7286 | 8.8343 | 12.0062 | 20.5333 | 34.2619 | 7.2922 | 8.8343 | 11.699 | 3.172 | 5.4961 | 13.7286 | 8.8343 | 12.0062 | 20.5333 | 34.2619 | 0
10.6799 | 8.4025 | 11.2796 | 6.4035 | 15.6019 | 11.2712 | 10.6799 | 17.0833 | 32.6852 | 43.9564 | 10.6899 | 8.4025 | 11.2796 | 6.4035 | 15.6019 | 11.2712 | 10.6799 | 17.0833 | 32.6852 | 43.9564 | 0
-1.1332 | 9.3763 | 9.9076 | 9.3668 | 7.0686 | 11.5536 | 9.3763 | 18.7431 | 25.8117 | 37.3652 | -1.1232 | 9.3763 | 9.9076 | 9.3668 | 7.0686 | 11.5536 | 9.3763 | 18.7431 | 25.8117 | 37.3652 | 0
15.1121 | 7.2004 | 7.0836 | 6.2079 | 10.3765 | 11.4431 | 15.1121 | 21.32 | 31.6965 | 43.1396 | 15.1221 | 7.2004 | 7.0836 | 6.2079 | 10.3765 | 11.4431 | 15.1121 | 21.32 | 31.6965 | 43.1396 | 0
1.2063 | 8.8359 | 7.1141 | 8.426 | 12.5524 | 15.6921 | 8.8359 | 17.262 | 29.8144 | 45.5065 | 1.2163 | 8.8359 | 7.1141 | 8.426 | 12.5524 | 15.6921 | 8.8359 | 17.262 | 29.8144 | 45.5065 | 0
-5.8613 | 8.6992 | 10.1851 | 6.1303 | 10.8368 | 10.971 | 8.6992 | 14.8295 | 25.6663 | 36.6373 | -5.8513 | 8.6992 | 10.1851 | 6.1303 | 10.8368 | 10.971 | 8.6992 | 14.8295 | 25.6663 | 36.6373 | 0
4.9894 | 8.7313 | 7.7999 | 5.1258 | 12.8043 | 7.0826 | 8.7313 | 13.857 | 26.6613 | 33.744 | 4.9994 | 8.7313 | 7.7999 | 5.1258 | 12.8043 | 7.0826 | 8.7313 | 13.857 | 26.6613 | 33.744 | 0
10.023 | 8.2914 | 9.8573 | 5.7108 | 10.2137 | 10.7466 | 10.023 | 15.7338 | 25.9475 | 36.6941 | 10.033 | 8.2914 | 9.8573 | 5.7108 | 10.2137 | 10.7466 | 10.023 | 15.7338 | 25.9475 | 36.6941 | 0
2.7729 | 8.8266 | 10.5437 | 3.8044 | 11.3754 | 11.6635 | 8.8266 | 12.6309 | 24.0064 | 35.6698 | 2.7829 | 8.8266 | 10.5437 | 3.8044 | 11.3754 | 11.6635 | 8.8266 | 12.6309 | 24.0064 | 35.6698 | 0
8.5571 | 8.956 | 7.9437 | 4.1592 | 7.7849 | 16.2181 | 8.956 | 13.1152 | 20.9001 | 37.1182 | 8.5671 | 8.956 | 7.9437 | 4.1592 | 7.7849 | 16.2181 | 8.956 | 13.1152 | 20.9001 | 37.1182 | 0
3.0263 | 9.9154 | 9.2742 | 7.9655 | 17.0779 | 15.4139 | 9.9154 | 17.8809 | 34.9588 | 50.3727 | 3.0363 | 9.9154 | 9.2742 | 7.9655 | 17.0779 | 15.4139 | 9.9154 | 17.8809 | 34.9588 | 50.3727 | 0
7.3459 | 10.0523 | 5.3125 | 11.0307 | 6.7918 | 19.3696 | 10.0523 | 21.0829 | 27.8748 | 47.2444 | 7.3559 | 10.0523 | 5.3125 | 11.0307 | 6.7918 | 19.3696 | 10.0523 | 21.0829 | 27.8748 | 47.2444 | 0
-9.1811 | 8.8294 | 7.5678 | 6.1648 | 6.436 | 8.3646 | 8.8294 | 14.9942 | 21.4302 | 29.7948 | -9.1711 | 8.8294 | 7.5678 | 6.1648 | 6.436 | 8.3646 | 8.8294 | 14.9942 | 21.4302 | 29.7948 | 0
-1.3714 | 7.7631 | 9.3087 | 8.2277 | 9.7476 | 13.6683 | 7.7631 | 15.9909 | 25.7385 | 39.4068 | -1.3614 | 7.7631 | 9.3087 | 8.2277 | 9.7476 | 13.6683 | 7.7631 | 15.9909 | 25.7385 | 39.4068 | 0
-4.335 | 8.4413 | 10.0201 | 1.7428 | 5.2582 | 12.2222 | 8.4413 | 10.1841 | 18.4614 | 30.6836 | -4.325 | 8.4413 | 10.0201 | 1.7428 | 5.2582 | 12.2222 | 8.4413 | 10.1841 | 18.4614 | 30.6836 | 0
6.8741 | 9.4984 | 5.8936 | 3.6442 | 11.9093 | 13.5953 | 9.4984 | 13.1426 | 25.0519 | 38.6473 | 6.8841 | 9.4984 | 5.8936 | 3.6442 | 11.9093 | 13.5953 | 9.4984 | 13.1426 | 25.0519 | 38.6473 | 0
-4.0542 | 10.1078 | 11.4208 | 7.5237 | 9.8311 | 16.5525 | 10.1078 | 17.6315 | 27.4626 | 44.015 | -4.0442 | 10.1078 | 11.4208 | 7.5237 | 9.8311 | 16.5525 | 10.1078 | 17.6315 | 27.4626 | 44.015 | 0
11.0582 | 8.4277 | 6.8273 | 5.8872 | 6.8489 | 14.0336 | 11.0582 | 16.9454 | 23.7943 | 37.828 | 11.0682 | 8.4277 | 6.8273 | 5.8872 | 6.8489 | 14.0336 | 11.0582 | 16.9454 | 23.7943 | 37.828 | 0
-4.5814 | 9.661 | 12.8532 | 8.6121 | 12.7472 | 10.5961 | 9.661 | 18.2731 | 31.0202 | 41.6163 | -4.5714 | 9.661 | 12.8532 | 8.6121 | 12.7472 | 10.5961 | 9.661 | 18.2731 | 31.0202 | 41.6163 | 0
2.2002 | 10.3714 | 10.8112 | 7.8361 | 8.4619 | 12.8202 | 10.3714 | 18.2075 | 26.6694 | 39.4897 | 2.2102 | 10.3714 | 10.8112 | 7.8361 | 8.4619 | 12.8202 | 10.3714 | 18.2075 | 26.6694 | 39.4897 | 0
-2.5534 | 8.7986 | 9.7918 | 9.6978 | 11.3434 | 8.9372 | 8.7986 | 18.4964 | 29.8398 | 38.777 | -2.5434 | 8.7986 | 9.7918 | 9.6978 | 11.3434 | 8.9372 | 8.7986 | 18.4964 | 29.8398 | 38.777 | 0
16.3283 | 8.1352 | 6.0122 | 6.857 | 11.2735 | 10.285 | 16.3283 | 23.1852 | 34.4588 | 44.7438 | 16.3383 | 8.1352 | 6.0122 | 6.857 | 11.2735 | 10.285 | 16.3283 | 23.1852 | 34.4588 | 44.7438 | 0
4.4491 | 9.0087 | 7.5449 | 6.6988 | 10.9472 | 11.7752 | 9.0087 | 15.7075 | 26.6547 | 38.4299 | 4.4591 | 9.0087 | 7.5449 | 6.6988 | 10.9472 | 11.7752 | 9.0087 | 15.7075 | 26.6547 | 38.4299 | 0
-1.2997 | 7.7241 | 10.1602 | 6.5467 | 12.3082 | 13.1047 | 7.7241 | 14.2708 | 26.579 | 39.6837 | -1.2897 | 7.7241 | 10.1602 | 6.5467 | 12.3082 | 13.1047 | 7.7241 | 14.2708 | 26.579 | 39.6837 | 0
7.6809 | 9.0303 | 6.0108 | 8.4628 | 9.8287 | 15.9025 | 9.0303 | 17.4932 | 27.3218 | 43.2243 | 7.6909 | 9.0303 | 6.0108 | 8.4628 | 9.8287 | 15.9025 | 9.0303 | 17.4932 | 27.3218 | 43.2243 | 0
1.3248 | 9.6263 | 8.1443 | 6.3896 | 12.8278 | 11.6454 | 9.6263 | 16.016 | 28.8438 | 40.4892 | 1.3348 | 9.6263 | 8.1443 | 6.3896 | 12.8278 | 11.6454 | 9.6263 | 16.016 | 28.8438 | 40.4892 | 0
2.9815 | 6.6687 | 9.3452 | 6.9772 | 8.8388 | 15.9765 | 6.6687 | 13.6459 | 22.4847 | 38.4612 | 2.9915 | 6.6687 | 9.3452 | 6.9772 | 8.8388 | 15.9765 | 6.6687 | 13.6459 | 22.4847 | 38.4612 | 0
1.5321 | 10.1754 | 5.2299 | 2.4876 | 10.1602 | 10.2016 | 10.1754 | 12.663 | 22.8232 | 33.0247 | 1.5421 | 10.1754 | 5.2299 | 2.4876 | 10.1602 | 10.2016 | 10.1754 | 12.663 | 22.8232 | 33.0247 | 0
-3.1667 | 9.1932 | 7.0494 | 5.0238 | 9.0925 | 10.3594 | 9.1932 | 14.217 | 23.3095 | 33.6689 | -3.1567 | 9.1932 | 7.0494 | 5.0238 | 9.0925 | 10.3594 | 9.1932 | 14.217 | 23.3095 | 33.6689 | 0
1.1837 | 10.5419 | 8.6215 | 5.2574 | 11.7138 | 12.6933 | 10.5419 | 15.7993 | 27.5131 | 40.2064 | 1.1937 | 10.5419 | 8.6215 | 5.2574 | 11.7138 | 12.6933 | 10.5419 | 15.7993 | 27.5131 | 40.2064 | 0
-4.7102 | 9.1351 | 5.7884 | 7.4031 | 8.7842 | 10.4325 | 9.1351 | 16.5382 | 25.3224 | 35.7549 | -4.7002 | 9.1351 | 5.7884 | 7.4031 | 8.7842 | 10.4325 | 9.1351 | 16.5382 | 25.3224 | 35.7549 | 0
3.2037 | 8.7033 | 4.2386 | 9.7834 | 12.0592 | 10.1993 | 8.7033 | 18.4867 | 30.5459 | 40.7452 | 3.2137 | 8.7033 | 4.2386 | 9.7834 | 12.0592 | 10.1993 | 8.7033 | 18.4867 | 30.5459 | 40.7452 | 0
4.4796 | 8.191 | 6.9046 | 7.9188 | 10.6709 | 7.7695 | 8.191 | 16.1097 | 26.7806 | 34.5501 | 4.4896 | 8.191 | 6.9046 | 7.9188 | 10.6709 | 7.7695 | 8.191 | 16.1097 | 26.7806 | 34.5501 | 0
2.5106 | 9.738 | 10.3478 | 8.46 | 10.09 | 15.5138 | 9.738 | 18.198 | 28.288 | 43.8019 | 2.5206 | 9.738 | 10.3478 | 8.46 | 10.09 | 15.5138 | 9.738 | 18.198 | 28.288 | 43.8019 | 0
1.1285 | 10.8354 | 8.3994 | 4.5201 | 11.5577 | 13.2907 | 10.8354 | 15.3555 | 26.9132 | 40.2039 | 1.1385 | 10.8354 | 8.3994 | 4.5201 | 11.5577 | 13.2907 | 10.8354 | 15.3555 | 26.9132 | 40.2039 | 0
-7.5296 | 9.3182 | 8.1814 | 7.8441 | 11.0729 | 13.5526 | 9.3182 | 17.1623 | 28.2351 | 41.7878 | -7.5196 | 9.3182 | 8.1814 | 7.8441 | 11.0729 | 13.5526 | 9.3182 | 17.1623 | 28.2351 | 41.7878 | 0
-5.8792 | 8.6471 | 9.8313 | 7.2231 | 7.9096 | 13.9856 | 8.6471 | 15.8702 | 23.7798 | 37.7654 | -5.8692 | 8.6471 | 9.8313 | 7.2231 | 7.9096 | 13.9856 | 8.6471 | 15.8702 | 23.7798 | 37.7654 | 0
-2.56 | 9.6324 | 3.4072 | 8.8285 | 9.5769 | 12.8892 | 9.6324 | 18.461 | 28.0379 | 40.9271 | -2.55 | 9.6324 | 3.4072 | 8.8285 | 9.5769 | 12.8892 | 9.6324 | 18.461 | 28.0379 | 40.9271 | 0
2.6647 | 8.9297 | 11.3278 | 9.5662 | 6.0032 | 9.6861 | 8.9297 | 18.4959 | 24.4991 | 34.1853 | 2.6747 | 8.9297 | 11.3278 | 9.5662 | 6.0032 | 9.6861 | 8.9297 | 18.4959 | 24.4991 | 34.1853 | 0
6.124 | 8.8845 | 5.7752 | 9.0795 | 15.7137 | 7.5381 | 8.8845 | 17.964 | 33.6777 | 41.2158 | 6.134 | 8.8845 | 5.7752 | 9.0795 | 15.7137 | 7.5381 | 8.8845 | 17.964 | 33.6777 | 41.2158 | 0
2.6138 | 9.5603 | 2.5968 | 10.1714 | 8.9419 | 13.8899 | 9.5603 | 19.7317 | 28.6736 | 42.5635 | 2.6238 | 9.5603 | 2.5968 | 10.1714 | 8.9419 | 13.8899 | 9.5603 | 19.7317 | 28.6736 | 42.5635 | 0
-1.4338 | 9.3527 | 12.7135 | 3.3286 | 13.3241 | 15.6448 | 9.3527 | 12.6813 | 26.0053 | 41.6502 | -1.4238 | 9.3527 | 12.7135 | 3.3286 | 13.3241 | 15.6448 | 9.3527 | 12.6813 | 26.0053 | 41.6502 | 0
7.2919 | 8.5057 | 5.1422 | 11.0538 | 6.323 | 10.9841 | 8.5057 | 19.5595 | 25.8825 | 36.8666 | 7.3019 | 8.5057 | 5.1422 | 11.0538 | 6.323 | 10.9841 | 8.5057 | 19.5595 | 25.8825 | 36.8666 | 0
-1.014 | 8.4845 | 4.9763 | 6.5316 | 10.0286 | 12.7559 | 8.4845 | 15.0161 | 25.0447 | 37.8006 | -1.004 | 8.4845 | 4.9763 | 6.5316 | 10.0286 | 12.7559 | 8.4845 | 15.0161 | 25.0447 | 37.8006 | 0
6.4227 | 8.2985 | 6.8839 | 5.8075 | 9.5304 | 10.1893 | 8.2985 | 14.1061 | 23.6364 | 33.8257 | 6.4327 | 8.2985 | 6.8839 | 5.8075 | 9.5304 | 10.1893 | 8.2985 | 14.1061 | 23.6364 | 33.8257 | 0
3.3866 | 10.4032 | 6.8637 | 6.8884 | 6.6184 | 11.8398 | 10.4032 | 17.2916 | 23.91 | 35.7498 | 3.3966 | 10.4032 | 6.8637 | 6.8884 | 6.6184 | 11.8398 | 10.4032 | 17.2916 | 23.91 | 35.7498 | 0
0.041535 | 9.9479 | 7.6896 | 6.6303 | 1.9546 | 12.7218 | 9.9479 | 16.5782 | 18.5328 | 31.2546 | 0.051535 | 9.9479 | 7.6896 | 6.6303 | 1.9546 | 12.7218 | 9.9479 | 16.5782 | 18.5328 | 31.2546 | 0
-3.9206 | 8.3201 | 10.488 | 10.0999 | 10.2622 | 10.2291 | 8.3201 | 18.42 | 28.6823 | 38.9114 | -3.9106 | 8.3201 | 10.488 | 10.0999 | 10.2622 | 10.2291 | 8.3201 | 18.42 | 28.6823 | 38.9114 | 0
5.3378 | 7.8301 | 9.7645 | 9.4931 | 13.2312 | 15.2623 | 7.8301 | 17.3232 | 30.5544 | 45.8167 | 5.3478 | 7.8301 | 9.7645 | 9.4931 | 13.2312 | 15.2623 | 7.8301 | 17.3232 | 30.5544 | 45.8167 | 0
4.9032 | 7.6002 | 7.911 | 7.9772 | 13.0552 | 11.9337 | 7.6002 | 15.5774 | 28.6327 | 40.5663 | 4.9132 | 7.6002 | 7.911 | 7.9772 | 13.0552 | 11.9337 | 7.6002 | 15.5774 | 28.6327 | 40.5663 | 0
3.0465 | 9.9791 | 6.1034 | 8.8598 | 11.2558 | 10.1284 | 9.9791 | 18.8389 | 30.0947 | 40.2231 | 3.0565 | 9.9791 | 6.1034 | 8.8598 | 11.2558 | 10.1284 | 9.9791 | 18.8389 | 30.0947 | 40.2231 | 0
-8.2811 | 9.1316 | 6.977 | 6.8877 | 9.2722 | 13.0206 | 9.1316 | 16.0193 | 25.2915 | 38.312 | -8.2711 | 9.1316 | 6.977 | 6.8877 | 9.2722 | 13.0206 | 9.1316 | 16.0193 | 25.2915 | 38.312 | 0
9.2633 | 7.642 | 9.9238 | 6.1258 | 10.7795 | 9.8726 | 9.2633 | 15.3891 | 26.1686 | 36.0412 | 9.2733 | 7.642 | 9.9238 | 6.1258 | 10.7795 | 9.8726 | 9.2633 | 15.3891 | 26.1686 | 36.0412 | 0
-2.6233 | 7.4997 | 8.8924 | 6.8017 | 8.3834 | 16.4888 | 7.4997 | 14.3013 | 22.6847 | 39.1735 | -2.6133 | 7.4997 | 8.8924 | 6.8017 | 8.3834 | 16.4888 | 7.4997 | 14.3013 | 22.6847 | 39.1735 | 0
6.2781 | 7.7183 | 9.6262 | 8.186 | 12.939 | 5.616 | 7.7183 | 15.9043 | 28.8433 | 34.4594 | 6.2881 | 7.7183 | 9.6262 | 8.186 | 12.939 | 5.616 | 7.7183 | 15.9043 | 28.8433 | 34.4594 | 0
-0.52293 | 8.6213 | 10.1561 | 6.051 | 17.0834 | 8.954 | 8.6213 | 14.6722 | 31.7556 | 40.7096 | -0.51293 | 8.6213 | 10.1561 | 6.051 | 17.0834 | 8.954 | 8.6213 | 14.6722 | 31.7556 | 40.7096 | 0
-8.3951 | 8.9444 | 8.0639 | 6.1692 | 13.7497 | 13.393 | 8.9444 | 15.1136 | 28.8634 | 42.2564 | -8.3851 | 8.9444 | 8.0639 | 6.1692 | 13.7497 | 13.393 | 8.9444 | 15.1136 | 28.8634 | 42.2564 | 0
-13.9365 | 10.0361 | 9.4917 | 6.6634 | 5.8692 | 11.8739 | 10.0361 | 16.6995 | 22.5687 | 34.4425 | -13.9265 | 10.0361 | 9.4917 | 6.6634 | 5.8692 | 11.8739 | 10.0361 | 16.6995 | 22.5687 | 34.4425 | 0
0.99258 | 9.6554 | 12.5556 | 6.1492 | 7.7376 | 13.3382 | 9.6554 | 15.8046 | 23.5422 | 36.8803 | 1.0026 | 9.6554 | 12.5556 | 6.1492 | 7.7376 | 13.3382 | 9.6554 | 15.8046 | 23.5422 | 36.8803 | 0
12.9709 | 8.999 | 10.6972 | 9.473 | 4.5174 | 1.0861 | 12.9709 | 22.4439 | 26.9612 | 28.0473 | 12.9809 | 8.999 | 10.6972 | 9.473 | 4.5174 | 1.0861 | 12.9709 | 22.4439 | 26.9612 | 28.0473 | 0
11.8752 | 9.018 | 8.7961 | 7.3157 | 7.6735 | 10.5379 | 11.8752 | 19.1909 | 26.8644 | 37.4023 | 11.8852 | 9.018 | 8.7961 | 7.3157 | 7.6735 | 10.5379 | 11.8752 | 19.1909 | 26.8644 | 37.4023 | 0
0.53992 | 8.1927 | 8.6659 | 6.5186 | 6.2482 | 13.3856 | 8.1927 | 14.7113 | 20.9595 | 34.3451 | 0.54992 | 8.1927 | 8.6659 | 6.5186 | 6.2482 | 13.3856 | 8.1927 | 14.7113 | 20.9595 | 34.3451 | 0
7.4864 | 8.4769 | 7.5783 | 4.8227 | 12.2175 | 12.7362 | 8.4769 | 13.2995 | 25.517 | 38.2532 | 7.4964 | 8.4769 | 7.5783 | 4.8227 | 12.2175 | 12.7362 | 8.4769 | 13.2995 | 25.517 | 38.2532 | 0
2.0053 | 9.3311 | 6.3548 | 9.2478 | 4.4563 | 11.6986 | 9.3311 | 18.5789 | 23.0351 | 34.7338 | 2.0153 | 9.3311 | 6.3548 | 9.2478 | 4.4563 | 11.6986 | 9.3311 | 18.5789 | 23.0351 | 34.7338 | 0
0.15358 | 8.7559 | 8.8257 | 5.5709 | 16.8799 | 6.3285 | 8.7559 | 14.3268 | 31.2067 | 37.5352 | 0.16358 | 8.7559 | 8.8257 | 5.5709 | 16.8799 | 6.3285 | 8.7559 | 14.3268 | 31.2067 | 37.5352 | 0
-2.5111 | 8.0509 | 4.4735 | 7.6191 | 10.4078 | 9.4529 | 8.0509 | 15.67 | 26.0778 | 35.5306 | -2.5011 | 8.0509 | 4.4735 | 7.6191 | 10.4078 | 9.4529 | 8.0509 | 15.67 | 26.0778 | 35.5306 | 0
3.1104 | 10.2489 | 6.6365 | 5.9574 | 6.0233 | 12.4977 | 10.2489 | 16.2063 | 22.2296 | 34.7272 | 3.1204 | 10.2489 | 6.6365 | 5.9574 | 6.0233 | 12.4977 | 10.2489 | 16.2063 | 22.2296 | 34.7272 | 0
0.06957 | 7.7694 | 5.6919 | 5.117 | 9.8057 | 13.3899 | 7.7694 | 12.8864 | 22.6921 | 36.082 | 0.07957 | 7.7694 | 5.6919 | 5.117 | 9.8057 | 13.3899 | 7.7694 | 12.8864 | 22.6921 | 36.082 | 0
9.1731 | 10.2675 | 5.4562 | 6.9048 | 9.6301 | 10.0679 | 10.2675 | 17.1723 | 26.8024 | 36.8704 | 9.1831 | 10.2675 | 5.4562 | 6.9048 | 9.6301 | 10.0679 | 10.2675 | 17.1723 | 26.8024 | 36.8704 | 0
0.078861 | 9.0961 | 6.896 | 7.2475 | 13.1673 | 8.7383 | 9.0961 | 16.3436 | 29.5109 | 38.2492 | 0.088861 | 9.0961 | 6.896 | 7.2475 | 13.1673 | 8.7383 | 9.0961 | 16.3436 | 29.5109 | 38.2492 | 0
6.0667 | 6.2549 | 5.5166 | 5.1607 | 14.6592 | 9.5176 | 6.2549 | 11.4156 | 26.0748 | 35.5924 | 6.0767 | 6.2549 | 5.5166 | 5.1607 | 14.6592 | 9.5176 | 6.2549 | 11.4156 | 26.0748 | 35.5924 | 0
7.0344 | 9.9477 | 6.99 | 6.8803 | 7.2151 | 10.5514 | 9.9477 | 16.8279 | 24.043 | 34.5944 | 7.0444 | 9.9477 | 6.99 | 6.8803 | 7.2151 | 10.5514 | 9.9477 | 16.8279 | 24.043 | 34.5944 | 0
3.2502 | 7.1691 | 10.5622 | 6.1431 | 10.1036 | 11.9879 | 7.1691 | 13.3122 | 23.4157 | 35.4036 | 3.2602 | 7.1691 | 10.5622 | 6.1431 | 10.1036 | 11.9879 | 7.1691 | 13.3122 | 23.4157 | 35.4036 | 0
2.4819 | 6.6501 | 4.0364 | 4.4858 | 15.0419 | 11.5588 | 6.6501 | 11.1359 | 26.1778 | 37.7366 | 2.4919 | 6.6501 | 4.0364 | 4.4858 | 15.0419 | 11.5588 | 6.6501 | 11.1359 | 26.1778 | 37.7366 | 0
0.76335 | 9.9273 | 6.2693 | 10.8313 | 12.9967 | 7.112 | 9.9273 | 20.7586 | 33.7553 | 40.8673 | 0.77335 | 9.9273 | 6.2693 | 10.8313 | 12.9967 | 7.112 | 9.9273 | 20.7586 | 33.7553 | 40.8673 | 0
-1.8464 | 8.4484 | 10.7243 | 6.285 | 14.7477 | 12.7223 | 8.4484 | 14.7334 | 29.4811 | 42.2035 | -1.8364 | 8.4484 | 10.7243 | 6.285 | 14.7477 | 12.7223 | 8.4484 | 14.7334 | 29.4811 | 42.2035 | 0
-1.8671 | 8.2164 | 12.3611 | 7.554 | 5.0308 | 11.917 | 8.2164 | 15.7704 | 20.8013 | 32.7183 | -1.8571 | 8.2164 | 12.3611 | 7.554 | 5.0308 | 11.917 | 8.2164 | 15.7704 | 20.8013 | 32.7183 | 0
1.2222 | 8.2038 | 7.9336 | 6.1649 | 10.2237 | 8.5042 | 8.2038 | 14.3687 | 24.5925 | 33.0966 | 1.2322 | 8.2038 | 7.9336 | 6.1649 | 10.2237 | 8.5042 | 8.2038 | 14.3687 | 24.5925 | 33.0966 | 0
5.0284 | 8.244 | 4.8871 | 5.1015 | 5.9221 | 13.2491 | 8.244 | 13.3456 | 19.2677 | 32.5167 | 5.0384 | 8.244 | 4.8871 | 5.1015 | 5.9221 | 13.2491 | 8.244 | 13.3456 | 19.2677 | 32.5167 | 0
0.96134 | 9.9479 | 3.9057 | 5.2114 | 11.2594 | 12.414 | 9.9479 | 15.1593 | 26.4187 | 38.8327 | 0.97134 | 9.9479 | 3.9057 | 5.2114 | 11.2594 | 12.414 | 9.9479 | 15.1593 | 26.4187 | 38.8327 | 0
3.0322 | 7.5813 | 8.1353 | 4.0853 | 11.921 | 14.5777 | 7.5813 | 11.6666 | 23.5876 | 38.1653 | 3.0422 | 7.5813 | 8.1353 | 4.0853 | 11.921 | 14.5777 | 7.5813 | 11.6666 | 23.5876 | 38.1653 | 0
-0.30321 | 10.0747 | 8.6707 | 7.8165 | 12.7182 | 14.6052 | 10.0747 | 17.8913 | 30.6095 | 45.2147 | -0.29321 | 10.0747 | 8.6707 | 7.8165 | 12.7182 | 14.6052 | 10.0747 | 17.8913 | 30.6095 | 45.2147 | 0
1.9232 | 7.768 | 7.7439 | 8.2335 | 10.783 | 8.9798 | 7.768 | 16.0015 | 26.7844 | 35.7642 | 1.9332 | 7.768 | 7.7439 | 8.2335 | 10.783 | 8.9798 | 7.768 | 16.0015 | 26.7844 | 35.7642 | 0
4.3911 | 9.2777 | 6.3251 | 9.122 | 11.9302 | 9.4928 | 9.2777 | 18.3996 | 30.3298 | 39.8226 | 4.4011 | 9.2777 | 6.3251 | 9.122 | 11.9302 | 9.4928 | 9.2777 | 18.3996 | 30.3298 | 39.8226 | 0
2.0423 | 9.0935 | 5.6135 | 9.8168 | 9.5911 | 9.0512 | 9.0935 | 18.9103 | 28.5014 | 37.5526 | 2.0523 | 9.0935 | 5.6135 | 9.8168 | 9.5911 | 9.0512 | 9.0935 | 18.9103 | 28.5014 | 37.5526 | 0
6.1959 | 9.0887 | 4.2878 | 8.3815 | 9.5757 | 12.2328 | 9.0887 | 17.4702 | 27.0459 | 39.2787 | 6.2059 | 9.0887 | 4.2878 | 8.3815 | 9.5757 | 12.2328 | 9.0887 | 17.4702 | 27.0459 | 39.2787 | 0
5.021 | 8.6838 | 5.6051 | 7.6877 | 8.4145 | 10.4596 | 8.6838 | 16.3715 | 24.786 | 35.2456 | 5.031 | 8.6838 | 5.6051 | 7.6877 | 8.4145 | 10.4596 | 8.6838 | 16.3715 | 24.786 | 35.2456 | 0
-4.5276 | 6.3254 | 6.9231 | 6.3067 | 7.8621 | 9.582 | 6.3254 | 12.6321 | 20.4942 | 30.0761 | -4.5176 | 6.3254 | 6.9231 | 6.3067 | 7.8621 | 9.582 | 6.3254 | 12.6321 | 20.4942 | 30.0761 | 0
3.6223 | 10.0923 | 7.1233 | 14.3737 | 10.9588 | 11.6224 | 10.0923 | 24.466 | 35.4248 | 47.0472 | 3.6323 | 10.0923 | 7.1233 | 14.3737 | 10.9588 | 11.6224 | 10.0923 | 24.466 | 35.4248 | 47.0472 | 0
2.8066 | 9.152 | 9.4684 | 4.3068 | 9.2485 | 15.3549 | 9.152 | 13.4589 | 22.7073 | 38.0623 | 2.8166 | 9.152 | 9.4684 | 4.3068 | 9.2485 | 15.3549 | 9.152 | 13.4589 | 22.7073 | 38.0623 | 0
-2.9632 | 10.0141 | 9.3772 | 8.7771 | 8.0006 | 9.6656 | 10.0141 | 18.7912 | 26.7918 | 36.4574 | -2.9532 | 10.0141 | 9.3772 | 8.7771 | 8.0006 | 9.6656 | 10.0141 | 18.7912 | 26.7918 | 36.4574 | 0
4.0829 | 8.3053 | 6.9212 | 4.6023 | 12.4611 | 4.859 | 8.3053 | 12.9077 | 25.3688 | 30.2278 | 4.0929 | 8.3053 | 6.9212 | 4.6023 | 12.4611 | 4.859 | 8.3053 | 12.9077 | 25.3688 | 30.2278 | 0
-1.844 | 9.5062 | 9.8025 | 8.4991 | 12.0679 | 10.9065 | 9.5062 | 18.0053 | 30.0733 | 40.9798 | -1.834 | 9.5062 | 9.8025 | 8.4991 | 12.0679 | 10.9065 | 9.5062 | 18.0053 | 30.0733 | 40.9798 | 0
0.79447 | 8.2212 | 5.8113 | 8.8456 | 15.6903 | 13.2569 | 8.2212 | 17.0668 | 32.7572 | 46.0141 | 0.80447 | 8.2212 | 5.8113 | 8.8456 | 15.6903 | 13.2569 | 8.2212 | 17.0668 | 32.7572 | 46.0141 | 0
-0.77702 | 10.1982 | 10.2318 | 6.4536 | 12.508 | 13.0767 | 10.1982 | 16.6518 | 29.1598 | 42.2365 | -0.76702 | 10.1982 | 10.2318 | 6.4536 | 12.508 | 13.0767 | 10.1982 | 16.6518 | 29.1598 | 42.2365 | 0
1.9958 | 7.0269 | 8.0108 | 5.696 | 6.3785 | 10.7887 | 7.0269 | 12.7228 | 19.1013 | 29.89 | 2.0058 | 7.0269 | 8.0108 | 5.696 | 6.3785 | 10.7887 | 7.0269 | 12.7228 | 19.1013 | 29.89 | 0
6.4381 | 8.7958 | 9.297 | 7.7098 | 11.3774 | 3.5207 | 8.7958 | 16.5057 | 27.8831 | 31.4038 | 6.4481 | 8.7958 | 9.297 | 7.7098 | 11.3774 | 3.5207 | 8.7958 | 16.5057 | 27.8831 | 31.4038 | 0
4.7488 | 10.2322 | 7.0157 | 5.5516 | 7.3779 | 12.4151 | 10.2322 | 15.7838 | 23.1617 | 35.5768 | 4.7588 | 10.2322 | 7.0157 | 5.5516 | 7.3779 | 12.4151 | 10.2322 | 15.7838 | 23.1617 | 35.5768 | 0
-4.6069 | 7.3226 | 6.7511 | 8.9863 | 1.519 | 9.3544 | 7.3226 | 16.3088 | 17.8278 | 27.1822 | -4.5969 | 7.3226 | 6.7511 | 8.9863 | 1.519 | 9.3544 | 7.3226 | 16.3088 | 17.8278 | 27.1822 | 0
9.753 | 8.7649 | 7.2706 | 6.7398 | 9.8857 | 9.3746 | 9.753 | 16.4928 | 26.3784 | 35.753 | 9.763 | 8.7649 | 7.2706 | 6.7398 | 9.8857 | 9.3746 | 9.753 | 16.4928 | 26.3784 | 35.753 | 0
0.13497 | 9.2909 | 7.6912 | 7.8396 | 4.4387 | 15.4113 | 9.2909 | 17.1305 | 21.5691 | 36.9804 | 0.14497 | 9.2909 | 7.6912 | 7.8396 | 4.4387 | 15.4113 | 9.2909 | 17.1305 | 21.5691 | 36.9804 | 0
0.62871 | 9.5927 | 6.7138 | 7.9597 | 13.8412 | 16.0518 | 9.5927 | 17.5524 | 31.3935 | 47.4453 | 0.63871 | 9.5927 | 6.7138 | 7.9597 | 13.8412 | 16.0518 | 9.5927 | 17.5524 | 31.3935 | 47.4453 | 0
-0.88391 | 8.7635 | 5.834 | 7.6716 | 13.2853 | 7.2012 | 8.7635 | 16.4351 | 29.7205 | 36.9217 | -0.87391 | 8.7635 | 5.834 | 7.6716 | 13.2853 | 7.2012 | 8.7635 | 16.4351 | 29.7205 | 36.9217 | 0
4.0033 | 9.5385 | 3.275 | 6.6623 | 14.2961 | 14.3519 | 9.5385 | 16.2008 | 30.497 | 44.8489 | 4.0133 | 9.5385 | 3.275 | 6.6623 | 14.2961 | 14.3519 | 9.5385 | 16.2008 | 30.497 | 44.8489 | 0
-2.1185 | 8.2834 | 8.1858 | 8.0081 | 10.3999 | 14.5204 | 8.2834 | 16.2915 | 26.6915 | 41.2119 | -2.1085 | 8.2834 | 8.1858 | 8.0081 | 10.3999 | 14.5204 | 8.2834 | 16.2915 | 26.6915 | 41.2119 | 0
-0.53914 | 7.4728 | 8.0581 | 6.8411 | 11.5661 | 12.6506 | 7.4728 | 14.3139 | 25.88 | 38.5306 | -0.52914 | 7.4728 | 8.0581 | 6.8411 | 11.5661 | 12.6506 | 7.4728 | 14.3139 | 25.88 | 38.5306 | 0
1.4541 | 10.051 | 6.6353 | 6.2668 | 4.1376 | 10.6353 | 10.051 | 16.3178 | 20.4554 | 31.0907 | 1.4641 | 10.051 | 6.6353 | 6.2668 | 4.1376 | 10.6353 | 10.051 | 16.3178 | 20.4554 | 31.0907 | 0
-1.7407 | 9.1168 | 10.6361 | 7.2554 | 14.6267 | 10.8016 | 9.1168 | 16.3722 | 30.999 | 41.8006 | -1.7307 | 9.1168 | 10.6361 | 7.2554 | 14.6267 | 10.8016 | 9.1168 | 16.3722 | 30.999 | 41.8006 | 0
13.5648 | 7.9401 | 7.7298 | 6.1279 | 8.0693 | 13.6042 | 13.5648 | 19.6927 | 27.762 | 41.3661 | 13.5748 | 7.9401 | 7.7298 | 6.1279 | 8.0693 | 13.6042 | 13.5648 | 19.6927 | 27.762 | 41.3661 | 0
9.0761 | 8.5022 | 8.1955 | 8.0608 | 10.4844 | 6.2111 | 9.0761 | 17.1369 | 27.6213 | 33.8324 | 9.0861 | 8.5022 | 8.1955 | 8.0608 | 10.4844 | 6.2111 | 9.0761 | 17.1369 | 27.6213 | 33.8324 | 0
6.8285 | 9.3363 | 3.6668 | 8.4589 | 9.9992 | 15.3321 | 9.3363 | 17.7953 | 27.7944 | 43.1265 | 6.8385 | 9.3363 | 3.6668 | 8.4589 | 9.9992 | 15.3321 | 9.3363 | 17.7953 | 27.7944 | 43.1265 | 0
0.45678 | 9.8256 | 7.1544 | 6.1753 | 10.8047 | 15.0561 | 9.8256 | 16.0009 | 26.8056 | 41.8618 | 0.46678 | 9.8256 | 7.1544 | 6.1753 | 10.8047 | 15.0561 | 9.8256 | 16.0009 | 26.8056 | 41.8618 | 0
6.4836 | 10.0419 | 3.569 | 4.5722 | 11.4509 | 15.1893 | 10.0419 | 14.6141 | 26.065 | 41.2542 | 6.4936 | 10.0419 | 3.569 | 4.5722 | 11.4509 | 15.1893 | 10.0419 | 14.6141 | 26.065 | 41.2542 | 0
-2.6233 | 8.3261 | 8.4799 | 10.7282 | 7.3446 | 17.5392 | 8.3261 | 19.0542 | 26.3988 | 43.938 | -2.6133 | 8.3261 | 8.4799 | 10.7282 | 7.3446 | 17.5392 | 8.3261 | 19.0542 | 26.3988 | 43.938 | 0
5.0503 | 9.5738 | 4.2402 | 6.3951 | 9.1307 | 9.1609 | 9.5738 | 15.9689 | 25.0996 | 34.2606 | 5.0603 | 9.5738 | 4.2402 | 6.3951 | 9.1307 | 9.1609 | 9.5738 | 15.9689 | 25.0996 | 34.2606 | 0
10.8463 | 9.6195 | 6.6614 | 5.3769 | 9.3583 | 12.2863 | 10.8463 | 16.2231 | 25.5814 | 37.8677 | 10.8563 | 9.6195 | 6.6614 | 5.3769 | 9.3583 | 12.2863 | 10.8463 | 16.2231 | 25.5814 | 37.8677 | 0
-0.76651 | 8.7314 | 7.6878 | 7.3463 | 6.2204 | 10.8228 | 8.7314 | 16.0777 | 22.2981 | 33.1208 | -0.75651 | 8.7314 | 7.6878 | 7.3463 | 6.2204 | 10.8228 | 8.7314 | 16.0777 | 22.2981 | 33.1208 | 0
-7.5217 | 7.3054 | 6.0961 | 7.9637 | 10.2469 | 10.7538 | 7.3054 | 15.269 | 25.5159 | 36.2697 | -7.5117 | 7.3054 | 6.0961 | 7.9637 | 10.2469 | 10.7538 | 7.3054 | 15.269 | 25.5159 | 36.2697 | 0
3.443 | 9.1556 | 8.4616 | 6.4732 | 11.0659 | 10.9435 | 9.1556 | 15.6288 | 26.6947 | 37.6383 | 3.453 | 9.1556 | 8.4616 | 6.4732 | 11.0659 | 10.9435 | 9.1556 | 15.6288 | 26.6947 | 37.6383 | 0
3.9305 | 9.2701 | 7.1588 | 8.0132 | 11.1947 | 9.2695 | 9.2701 | 17.2833 | 28.4779 | 37.7474 | 3.9405 | 9.2701 | 7.1588 | 8.0132 | 11.1947 | 9.2695 | 9.2701 | 17.2833 | 28.4779 | 37.7474 | 0
-4.0836 | 8.8429 | 7.7139 | 6.4478 | 11.056 | 9.1952 | 8.8429 | 15.2908 | 26.3468 | 35.542 | -4.0736 | 8.8429 | 7.7139 | 6.4478 | 11.056 | 9.1952 | 8.8429 | 15.2908 | 26.3468 | 35.542 | 0
-1.8478 | 9.1724 | 9.0713 | 7.7164 | 13.5692 | 13.5415 | 9.1724 | 16.8887 | 30.4579 | 43.9994 | -1.8378 | 9.1724 | 9.0713 | 7.7164 | 13.5692 | 13.5415 | 9.1724 | 16.8887 | 30.4579 | 43.9994 | 0
11.5211 | 8.925 | 8.3078 | 8.2382 | 8.4154 | 16.36 | 11.5211 | 19.7593 | 28.1747 | 44.5347 | 11.5311 | 8.925 | 8.3078 | 8.2382 | 8.4154 | 16.36 | 11.5211 | 19.7593 | 28.1747 | 44.5347 | 0
-2.8203 | 9.9221 | 7.3184 | 4.3728 | 13.6317 | 19.8206 | 9.9221 | 14.2948 | 27.9265 | 47.7471 | -2.8103 | 9.9221 | 7.3184 | 4.3728 | 13.6317 | 19.8206 | 9.9221 | 14.2948 | 27.9265 | 47.7471 | 0
-2.3022 | 8.1564 | 9.9706 | 3.3422 | 8.6132 | 9.5785 | 8.1564 | 11.4986 | 20.1118 | 29.6903 | -2.2922 | 8.1564 | 9.9706 | 3.3422 | 8.6132 | 9.5785 | 8.1564 | 11.4986 | 20.1118 | 29.6903 | 0
7.7894 | 7.3438 | 6.6621 | 7.1948 | 13.6233 | 15.3718 | 7.7894 | 14.9842 | 28.6075 | 43.9793 | 7.7994 | 7.3438 | 6.6621 | 7.1948 | 13.6233 | 15.3718 | 7.7894 | 14.9842 | 28.6075 | 43.9793 | 0
-2.7133 | 10.0219 | 7.7945 | 7.1047 | 7.9657 | 10.8251 | 10.0219 | 17.1266 | 25.0923 | 35.9174 | -2.7033 | 10.0219 | 7.7945 | 7.1047 | 7.9657 | 10.8251 | 10.0219 | 17.1266 | 25.0923 | 35.9174 | 0
0.9232 | 9.4055 | 9.3619 | 6.3611 | 10.1749 | 9.4725 | 9.4055 | 15.7666 | 25.9415 | 35.414 | 0.9332 | 9.4055 | 9.3619 | 6.3611 | 10.1749 | 9.4725 | 9.4055 | 15.7666 | 25.9415 | 35.414 | 0
3.5403 | 10.0597 | 8.6156 | 6.2444 | 8.1219 | 9.9427 | 10.0597 | 16.3041 | 24.426 | 34.3688 | 3.5503 | 10.0597 | 8.6156 | 6.2444 | 8.1219 | 9.9427 | 10.0597 | 16.3041 | 24.426 | 34.3688 | 0
-7.4912 | 7.7569 | 4.9623 | 5.6912 | 12.5384 | 14.543 | 7.7569 | 13.4481 | 25.9865 | 40.5295 | -7.4812 | 7.7569 | 4.9623 | 5.6912 | 12.5384 | 14.543 | 7.7569 | 13.4481 | 25.9865 | 40.5295 | 0
-0.76732 | 10.808 | 7.0649 | 7.7398 | 12.5856 | 17.8694 | 10.808 | 18.5477 | 31.1333 | 49.0027 | -0.75732 | 10.808 | 7.0649 | 7.7398 | 12.5856 | 17.8694 | 10.808 | 18.5477 | 31.1333 | 49.0027 | 0
-2.3727 | 9.2625 | 6.0283 | 5.1534 | 5.6478 | 11.0078 | 9.2625 | 14.4159 | 20.0637 | 31.0715 | -2.3627 | 9.2625 | 6.0283 | 5.1534 | 5.6478 | 11.0078 | 9.2625 | 14.4159 | 20.0637 | 31.0715 | 0
-3.3252 | 8.8373 | 7.7837 | 6.3142 | 6.5223 | 14.0734 | 8.8373 | 15.1516 | 21.6738 | 35.7472 | -3.3152 | 8.8373 | 7.7837 | 6.3142 | 6.5223 | 14.0734 | 8.8373 | 15.1516 | 21.6738 | 35.7472 | 0
2.7112 | 9.3627 | 9.3417 | 7.8477 | 7.9172 | 12.813 | 9.3627 | 17.2104 | 25.1276 | 37.9406 | 2.7212 | 9.3627 | 9.3417 | 7.8477 | 7.9172 | 12.813 | 9.3627 | 17.2104 | 25.1276 | 37.9406 | 0
0.74458 | 7.8116 | 9.0499 | 7.0302 | 12.9561 | 12.3371 | 7.8116 | 14.8418 | 27.7979 | 40.135 | 0.75458 | 7.8116 | 9.0499 | 7.0302 | 12.9561 | 12.3371 | 7.8116 | 14.8418 | 27.7979 | 40.135 | 0
5.8065 | 8.1931 | 6.4189 | 7.7479 | 10.5564 | 10.5894 | 8.1931 | 15.941 | 26.4974 | 37.0869 | 5.8165 | 8.1931 | 6.4189 | 7.7479 | 10.5564 | 10.5894 | 8.1931 | 15.941 | 26.4974 | 37.0869 | 0
0.14488 | 7.6383 | 9.7017 | 8.1334 | 4.3511 | 9.6381 | 7.6383 | 15.7717 | 20.1228 | 29.7609 | 0.15488 | 7.6383 | 9.7017 | 8.1334 | 4.3511 | 9.6381 | 7.6383 | 15.7717 | 20.1228 | 29.7609 | 0
12.799 | 8.2808 | 10.2988 | 5.4928 | 11.8537 | 14.7524 | 12.799 | 18.2918 | 30.1455 | 44.8978 | 12.809 | 8.2808 | 10.2988 | 5.4928 | 11.8537 | 14.7524 | 12.799 | 18.2918 | 30.1455 | 44.8978 | 0
9.2966 | 9.5103 | 9.5028 | 8.2641 | 9.2166 | 16.3196 | 9.5103 | 17.7743 | 26.991 | 43.3105 | 9.3066 | 9.5103 | 9.5028 | 8.2641 | 9.2166 | 16.3196 | 9.5103 | 17.7743 | 26.991 | 43.3105 | 0
-6.506 | 10.9366 | 4.3856 | 5.7718 | 9.1438 | 9.993 | 10.9366 | 16.7083 | 25.8521 | 35.8451 | -6.496 | 10.9366 | 4.3856 | 5.7718 | 9.1438 | 9.993 | 10.9366 | 16.7083 | 25.8521 | 35.8451 | 0
-0.34621 | 8.4618 | 7.281 | 7.8695 | 9.8787 | 8.5477 | 8.4618 | 16.3313 | 26.2101 | 34.7578 | -0.33621 | 8.4618 | 7.281 | 7.8695 | 9.8787 | 8.5477 | 8.4618 | 16.3313 | 26.2101 | 34.7578 | 0
10.1671 | 9.602 | 14.507 | 6.1194 | 10.3212 | 11.8729 | 10.1671 | 16.2864 | 26.6076 | 38.4805 | 10.1771 | 9.602 | 14.507 | 6.1194 | 10.3212 | 11.8729 | 10.1671 | 16.2864 | 26.6076 | 38.4805 | 0
-0.33699 | 9.8281 | 7.5767 | 8.8424 | 3.5939 | 12.3046 | 9.8281 | 18.6704 | 22.2643 | 34.5689 | -0.32699 | 9.8281 | 7.5767 | 8.8424 | 3.5939 | 12.3046 | 9.8281 | 18.6704 | 22.2643 | 34.5689 | 0
1.3945 | 8.937 | 9.3105 | 6.2175 | 5.2963 | 7.779 | 8.937 | 15.1545 | 20.4508 | 28.2298 | 1.4045 | 8.937 | 9.3105 | 6.2175 | 5.2963 | 7.779 | 8.937 | 15.1545 | 20.4508 | 28.2298 | 0
12.4074 | 8.9075 | 9.1936 | 6.6798 | 9.2608 | 14.0931 | 12.4074 | 19.0871 | 28.348 | 42.4411 | 12.4174 | 8.9075 | 9.1936 | 6.6798 | 9.2608 | 14.0931 | 12.4074 | 19.0871 | 28.348 | 42.4411 | 0
-9.166 | 10.3957 | 8.9787 | 7.0508 | 5.1513 | 10.0859 | 10.3957 | 17.4466 | 22.5979 | 32.6838 | -9.156 | 10.3957 | 8.9787 | 7.0508 | 5.1513 | 10.0859 | 10.3957 | 17.4466 | 22.5979 | 32.6838 | 0
-1.8294 | 10.6045 | 6.4257 | 10.4443 | 7.0772 | 14.4502 | 10.6045 | 21.0489 | 28.1261 | 42.5762 | -1.8194 | 10.6045 | 6.4257 | 10.4443 | 7.0772 | 14.4502 | 10.6045 | 21.0489 | 28.1261 | 42.5762 | 0
5.3671 | 8.6659 | 7.6655 | 6.4176 | 10.0594 | 10.0886 | 8.6659 | 15.0835 | 25.1429 | 35.2315 | 5.3771 | 8.6659 | 7.6655 | 6.4176 | 10.0594 | 10.0886 | 8.6659 | 15.0835 | 25.1429 | 35.2315 | 0
5.2593 | 8.7001 | 6.8343 | 5.243 | 8.511 | 14.3324 | 8.7001 | 13.9431 | 22.4541 | 36.7865 | 5.2693 | 8.7001 | 6.8343 | 5.243 | 8.511 | 14.3324 | 8.7001 | 13.9431 | 22.4541 | 36.7865 | 0
-0.93912 | 9.2904 | 9.8052 | 7.3446 | 8.1695 | 13.0117 | 9.2904 | 16.635 | 24.8045 | 37.8162 | -0.92912 | 9.2904 | 9.8052 | 7.3446 | 8.1695 | 13.0117 | 9.2904 | 16.635 | 24.8045 | 37.8162 | 0
6.6001 | 9.4089 | 6.2424 | 4.9976 | 10.5456 | 11.3511 | 9.4089 | 14.4064 | 24.9521 | 36.3032 | 6.6101 | 9.4089 | 6.2424 | 4.9976 | 10.5456 | 11.3511 | 9.4089 | 14.4064 | 24.9521 | 36.3032 | 0
12.1278 | 9.3284 | 5.8466 | 7.2014 | 8.5953 | 10.8761 | 12.1278 | 19.3292 | 27.9244 | 38.8005 | 12.1378 | 9.3284 | 5.8466 | 7.2014 | 8.5953 | 10.8761 | 12.1278 | 19.3292 | 27.9244 | 38.8005 | 0
6.2493 | 8.4941 | 8.5769 | 7.957 | 14.9404 | 6.9577 | 8.4941 | 16.4511 | 31.3915 | 38.3492 | 6.2593 | 8.4941 | 8.5769 | 7.957 | 14.9404 | 6.9577 | 8.4941 | 16.4511 | 31.3915 | 38.3492 | 0
-0.52573 | 9.739 | 5.2492 | 7.2788 | 4.2932 | 16.0215 | 9.739 | 17.0178 | 21.311 | 37.3326 | -0.51573 | 9.739 | 5.2492 | 7.2788 | 4.2932 | 16.0215 | 9.739 | 17.0178 | 21.311 | 37.3326 | 0
-3.5728 | 8.3724 | 6.5262 | 5.279 | 6.8098 | 13.6442 | 8.3724 | 13.6514 | 20.4612 | 34.1055 | -3.5628 | 8.3724 | 6.5262 | 5.279 | 6.8098 | 13.6442 | 8.3724 | 13.6514 | 20.4612 | 34.1055 | 0
0.28329 | 7.8686 | 8.2472 | 5.9171 | 13.4657 | 11.1642 | 7.8686 | 13.7857 | 27.2514 | 38.4156 | 0.29329 | 7.8686 | 8.2472 | 5.9171 | 13.4657 | 11.1642 | 7.8686 | 13.7857 | 27.2514 | 38.4156 | 0
10.6699 | 7.7067 | 6.8786 | 2.9431 | 14.5656 | 10.8516 | 10.6699 | 13.613 | 28.1786 | 39.0301 | 10.6799 | 7.7067 | 6.8786 | 2.9431 | 14.5656 | 10.8516 | 10.6699 | 13.613 | 28.1786 | 39.0301 | 0
0.61413 | 8.6733 | 12.0972 | 5.6282 | 15.8895 | 7.1887 | 8.6733 | 14.3015 | 30.191 | 37.3797 | 0.62413 | 8.6733 | 12.0972 | 5.6282 | 15.8895 | 7.1887 | 8.6733 | 14.3015 | 30.191 | 37.3797 | 0
1.3111 | 8.9962 | 8.8577 | 9.676 | 15.5474 | 6.202 | 8.9962 | 18.6722 | 34.2197 | 40.4217 | 1.3211 | 8.9962 | 8.8577 | 9.676 | 15.5474 | 6.202 | 8.9962 | 18.6722 | 34.2197 | 40.4217 | 0
0.27742 | 8.1428 | 5.9063 | 9.0796 | 10.0514 | 13.7905 | 8.1428 | 17.2224 | 27.2738 | 41.0643 | 0.28742 | 8.1428 | 5.9063 | 9.0796 | 10.0514 | 13.7905 | 8.1428 | 17.2224 | 27.2738 | 41.0643 | 0
4.0318 | 8.6228 | 7.7375 | 5.0449 | 9.602 | 14.7113 | 8.6228 | 13.6676 | 23.2696 | 37.9809 | 4.0418 | 8.6228 | 7.7375 | 5.0449 | 9.602 | 14.7113 | 8.6228 | 13.6676 | 23.2696 | 37.9809 | 0
-0.35947 | 10.3093 | 2.6676 | 8.465 | 10.4012 | 10.4189 | 10.3093 | 18.7743 | 29.1755 | 39.5944 | -0.34947 | 10.3093 | 2.6676 | 8.465 | 10.4012 | 10.4189 | 10.3093 | 18.7743 | 29.1755 | 39.5944 | 0
-3.2167 | 9.9375 | 7.812 | 10.0544 | 9.6487 | 13.9697 | 9.9375 | 19.9918 | 29.6405 | 43.6103 | -3.2067 | 9.9375 | 7.812 | 10.0544 | 9.6487 | 13.9697 | 9.9375 | 19.9918 | 29.6405 | 43.6103 | 0
14.4933 | 8.0744 | 4.5265 | 5.0768 | 6.8395 | 17.6257 | 14.4933 | 19.5701 | 26.4096 | 44.0353 | 14.5033 | 8.0744 | 4.5265 | 5.0768 | 6.8395 | 17.6257 | 14.4933 | 19.5701 | 26.4096 | 44.0353 | 0
-0.05667 | 9.1154 | 9.0899 | 7.8046 | 12.3722 | 11.2557 | 9.1154 | 16.92 | 29.2922 | 40.5479 | -0.04667 | 9.1154 | 9.0899 | 7.8046 | 12.3722 | 11.2557 | 9.1154 | 16.92 | 29.2922 | 40.5479 | 0
0.31636 | 9.178 | 7.1652 | 8.334 | 6.4915 | 15.2789 | 9.178 | 17.5119 | 24.0034 | 39.2823 | 0.32636 | 9.178 | 7.1652 | 8.334 | 6.4915 | 15.2789 | 9.178 | 17.5119 | 24.0034 | 39.2823 | 0
0.9146 | 8.7367 | 5.4751 | 4.8745 | 8.8156 | 18.8262 | 8.7367 | 13.6112 | 22.4268 | 41.253 | 0.9246 | 8.7367 | 5.4751 | 4.8745 | 8.8156 | 18.8262 | 8.7367 | 13.6112 | 22.4268 | 41.253 | 0
-4.2951 | 7.9732 | 9.2302 | 6.2139 | 10.1651 | 13.6302 | 7.9732 | 14.1871 | 24.3522 | 37.9824 | -4.2851 | 7.9732 | 9.2302 | 6.2139 | 10.1651 | 13.6302 | 7.9732 | 14.1871 | 24.3522 | 37.9824 | 0
0.61564 | 6.5113 | 11.0001 | 6.8315 | 8.5282 | 10.4788 | 6.5113 | 13.3429 | 21.8711 | 32.3498 | 0.62564 | 6.5113 | 11.0001 | 6.8315 | 8.5282 | 10.4788 | 6.5113 | 13.3429 | 21.8711 | 32.3498 | 0
-5.9311 | 9.6912 | 6.7447 | 6.1381 | 8.9448 | 14.6825 | 9.6912 | 15.8293 | 24.774 | 39.4565 | -5.9211 | 9.6912 | 6.7447 | 6.1381 | 8.9448 | 14.6825 | 9.6912 | 15.8293 | 24.774 | 39.4565 | 0
8.8645 | 10.3752 | 10.6519 | 9.7106 | 12.344 | 10.5885 | 10.3752 | 20.0857 | 32.4298 | 43.0183 | 8.8745 | 10.3752 | 10.6519 | 9.7106 | 12.344 | 10.5885 | 10.3752 | 20.0857 | 32.4298 | 43.0183 | 0
-0.077127 | 7.8831 | 8.2595 | 7.6689 | 12.9402 | 11.3177 | 7.8831 | 15.552 | 28.4922 | 39.8099 | -0.067127 | 7.8831 | 8.2595 | 7.6689 | 12.9402 | 11.3177 | 7.8831 | 15.552 | 28.4922 | 39.8099 | 0
8.221 | 10.184 | 5.1269 | 10.0199 | 10.3687 | 13.6646 | 10.184 | 20.204 | 30.5727 | 44.2373 | 8.231 | 10.184 | 5.1269 | 10.0199 | 10.3687 | 13.6646 | 10.184 | 20.204 | 30.5727 | 44.2373 | 0
2.3121 | 8.8982 | 8.4013 | 8.0637 | 10.1236 | 12.4168 | 8.8982 | 16.9619 | 27.0855 | 39.5022 | 2.3221 | 8.8982 | 8.4013 | 8.0637 | 10.1236 | 12.4168 | 8.8982 | 16.9619 | 27.0855 | 39.5022 | 0
-3.9885 | 7.6886 | 10.2943 | 5.7882 | 11.5954 | 17.2369 | 7.6886 | 13.4767 | 25.0721 | 42.3091 | -3.9785 | 7.6886 | 10.2943 | 5.7882 | 11.5954 | 17.2369 | 7.6886 | 13.4767 | 25.0721 | 42.3091 | 0
-0.8005 | 8.2854 | 5.348 | 5.7684 | 5.8464 | 11.1392 | 8.2854 | 14.0538 | 19.9002 | 31.0394 | -0.7905 | 8.2854 | 5.348 | 5.7684 | 5.8464 | 11.1392 | 8.2854 | 14.0538 | 19.9002 | 31.0394 | 0
11.6303 | 9.2464 | 6.6373 | 6.1123 | 10.8072 | 13.5184 | 11.6303 | 17.7426 | 28.5499 | 42.0682 | 11.6403 | 9.2464 | 6.6373 | 6.1123 | 10.8072 | 13.5184 | 11.6303 | 17.7426 | 28.5499 | 42.0682 | 0
0.1422 | 8.1281 | 5.8142 | 6.326 | 5.8073 | 12.6264 | 8.1281 | 14.4541 | 20.2614 | 32.8878 | 0.1522 | 8.1281 | 5.8142 | 6.326 | 5.8073 | 12.6264 | 8.1281 | 14.4541 | 20.2614 | 32.8878 | 0
-5.6659 | 9.1885 | 6.8254 | 11.5343 | 9.3822 | 11.1139 | 9.1885 | 20.7228 | 30.105 | 41.2189 | -5.6559 | 9.1885 | 6.8254 | 11.5343 | 9.3822 | 11.1139 | 9.1885 | 20.7228 | 30.105 | 41.2189 | 0
-2.8431 | 10.7377 | 9.3958 | 7.0307 | 9.2855 | 11.7966 | 10.7377 | 17.7683 | 27.0539 | 38.8505 | -2.8331 | 10.7377 | 9.3958 | 7.0307 | 9.2855 | 11.7966 | 10.7377 | 17.7683 | 27.0539 | 38.8505 | 0
7.1306 | 9.3442 | 6.4172 | 6.0504 | 10.8044 | 10.2878 | 9.3442 | 15.3946 | 26.199 | 36.4869 | 7.1406 | 9.3442 | 6.4172 | 6.0504 | 10.8044 | 10.2878 | 9.3442 | 15.3946 | 26.199 | 36.4869 | 0
5.0317 | 9.0005 | 9.0723 | 7.8246 | 6.2876 | 14.3287 | 9.0005 | 16.8251 | 23.1127 | 37.4414 | 5.0417 | 9.0005 | 9.0723 | 7.8246 | 6.2876 | 14.3287 | 9.0005 | 16.8251 | 23.1127 | 37.4414 | 0
3.9317 | 10.1409 | 6.9365 | 6.9997 | 9.7224 | 12.0155 | 10.1409 | 17.1406 | 26.863 | 38.8785 | 3.9417 | 10.1409 | 6.9365 | 6.9997 | 9.7224 | 12.0155 | 10.1409 | 17.1406 | 26.863 | 38.8785 | 0
2.0395 | 8.3187 | 5.7871 | 7.3522 | 13.3499 | 9.7937 | 8.3187 | 15.671 | 29.0209 | 38.8146 | 2.0495 | 8.3187 | 5.7871 | 7.3522 | 13.3499 | 9.7937 | 8.3187 | 15.671 | 29.0209 | 38.8146 | 0
3.8712 | 9.4733 | 8.4702 | 5.4584 | 7.8668 | 5.7745 | 9.4733 | 14.9317 | 22.7984 | 28.5729 | 3.8812 | 9.4733 | 8.4702 | 5.4584 | 7.8668 | 5.7745 | 9.4733 | 14.9317 | 22.7984 | 28.5729 | 0
-4.0776 | 7.7057 | 7.205 | 6.8721 | 12.8002 | 7.8342 | 7.7057 | 14.5778 | 27.378 | 35.2121 | -4.0676 | 7.7057 | 7.205 | 6.8721 | 12.8002 | 7.8342 | 7.7057 | 14.5778 | 27.378 | 35.2121 | 0
-1.3249 | 8.8018 | 8.8892 | 9.2689 | 10.9364 | 9.112 | 8.8018 | 18.0707 | 29.0071 | 38.1191 | -1.3149 | 8.8018 | 8.8892 | 9.2689 | 10.9364 | 9.112 | 8.8018 | 18.0707 | 29.0071 | 38.1191 | 0
4.3016 | 6.8414 | 5.8268 | 7.5565 | 14.8323 | 9.8738 | 6.8414 | 14.3979 | 29.2302 | 39.104 | 4.3116 | 6.8414 | 5.8268 | 7.5565 | 14.8323 | 9.8738 | 6.8414 | 14.3979 | 29.2302 | 39.104 | 0
8.9192 | 9.001 | 8.2401 | 6.1909 | 13.81 | 17.9803 | 9.001 | 15.1919 | 29.0019 | 46.9822 | 8.9292 | 9.001 | 8.2401 | 6.1909 | 13.81 | 17.9803 | 9.001 | 15.1919 | 29.0019 | 46.9822 | 0
17.0008 | 8.0481 | 7.81 | 4.4391 | 3.4734 | 13.0324 | 17.0008 | 21.4399 | 24.9133 | 37.9457 | 17.0108 | 8.0481 | 7.81 | 4.4391 | 3.4734 | 13.0324 | 17.0008 | 21.4399 | 24.9133 | 37.9457 | 0
4.6173 | 9.5883 | 8.7526 | 2.8878 | 11.2163 | 9.6864 | 9.5883 | 12.476 | 23.6924 | 33.3787 | 4.6273 | 9.5883 | 8.7526 | 2.8878 | 11.2163 | 9.6864 | 9.5883 | 12.476 | 23.6924 | 33.3787 | 0
-4.0446 | 9.3864 | 6.5299 | 5.4345 | 8.6456 | 11.4254 | 9.3864 | 14.8209 | 23.4665 | 34.8919 | -4.0346 | 9.3864 | 6.5299 | 5.4345 | 8.6456 | 11.4254 | 9.3864 | 14.8209 | 23.4665 | 34.8919 | 0
0.065518 | 8.8772 | 12.4692 | 5.7103 | 6.6014 | 6.0414 | 8.8772 | 14.5875 | 21.3463 | 27.3877 | 0.075518 | 8.8772 | 12.4692 | 5.7103 | 6.6014 | 6.0414 | 8.8772 | 14.5875 | 21.3463 | 27.3877 | 0
3.3415 | 10.313 | 6.1578 | 7.7942 | 15.0236 | 7.3361 | 10.313 | 18.1072 | 33.1309 | 40.4669 | 3.3515 | 10.313 | 6.1578 | 7.7942 | 15.0236 | 7.3361 | 10.313 | 18.1072 | 33.1309 | 40.4669 | 0
-1.4804 | 8.1006 | 5.7317 | 8.4113 | 13.4796 | 13.3825 | 8.1006 | 16.5119 | 29.9915 | 43.374 | -1.4704 | 8.1006 | 5.7317 | 8.4113 | 13.4796 | 13.3825 | 8.1006 | 16.5119 | 29.9915 | 43.374 | 0
5.193 | 7.2915 | 7.7697 | 0.72696 | 13.3983 | 10.8127 | 7.2915 | 8.0184 | 21.4167 | 32.2294 | 5.203 | 7.2915 | 7.7697 | 0.72696 | 13.3983 | 10.8127 | 7.2915 | 8.0184 | 21.4167 | 32.2294 | 0
-3.7113 | 9.3479 | 6.7941 | 6.3042 | 11.1081 | 11.7345 | 9.3479 | 15.6521 | 26.7602 | 38.4948 | -3.7013 | 9.3479 | 6.7941 | 6.3042 | 11.1081 | 11.7345 | 9.3479 | 15.6521 | 26.7602 | 38.4948 | 0
9.3933 | 7.546 | 9.5121 | 11.3745 | 4.4253 | 15.9105 | 9.3933 | 20.7678 | 25.193 | 41.1035 | 9.4033 | 7.546 | 9.5121 | 11.3745 | 4.4253 | 15.9105 | 9.3933 | 20.7678 | 25.193 | 41.1035 | 0
-4.0893 | 8.9542 | 9.0837 | 7.5314 | 10.3334 | 8.6855 | 8.9542 | 16.4856 | 26.8191 | 35.5045 | -4.0793 | 8.9542 | 9.0837 | 7.5314 | 10.3334 | 8.6855 | 8.9542 | 16.4856 | 26.8191 | 35.5045 | 0
0.73038 | 8.4725 | 8.0302 | 6.6438 | 7.607 | 11.4739 | 8.4725 | 15.1163 | 22.7233 | 34.1972 | 0.74038 | 8.4725 | 8.0302 | 6.6438 | 7.607 | 11.4739 | 8.4725 | 15.1163 | 22.7233 | 34.1972 | 0
-2.7452 | 8.1674 | 8.8969 | 7.6547 | 16.1602 | 13.5612 | 8.1674 | 15.8221 | 31.9823 | 45.5435 | -2.7352 | 8.1674 | 8.8969 | 7.6547 | 16.1602 | 13.5612 | 8.1674 | 15.8221 | 31.9823 | 45.5435 | 0
-1.5736 | 10.8566 | 8.77 | 9.8865 | 10.4605 | 12.1849 | 10.8566 | 20.7431 | 31.2036 | 43.3885 | -1.5636 | 10.8566 | 8.77 | 9.8865 | 10.4605 | 12.1849 | 10.8566 | 20.7431 | 31.2036 | 43.3885 | 0
-8.7816 | 8.9598 | 8.1632 | 5.9592 | 11.9527 | 11.4694 | 8.9598 | 14.919 | 26.8717 | 38.3411 | -8.7716 | 8.9598 | 8.1632 | 5.9592 | 11.9527 | 11.4694 | 8.9598 | 14.919 | 26.8717 | 38.3411 | 0
13.8509 | 10.2484 | 11.6668 | 6.612 | 8.8354 | 13.6837 | 13.8509 | 20.4629 | 29.2983 | 42.9819 | 13.8609 | 10.2484 | 11.6668 | 6.612 | 8.8354 | 13.6837 | 13.8509 | 20.4629 | 29.2983 | 42.9819 | 0
2.3382 | 8.4869 | 5.3725 | 8.1298 | 10.3228 | 18.8096 | 8.4869 | 16.6167 | 26.9395 | 45.7491 | 2.3482 | 8.4869 | 5.3725 | 8.1298 | 10.3228 | 18.8096 | 8.4869 | 16.6167 | 26.9395 | 45.7491 | 0
-1.7406 | 8.1847 | 8.5938 | 3.5732 | 10.2145 | 15.9972 | 8.1847 | 11.758 | 21.9724 | 37.9696 | -1.7306 | 8.1847 | 8.5938 | 3.5732 | 10.2145 | 15.9972 | 8.1847 | 11.758 | 21.9724 | 37.9696 | 0
-9.046 | 9.8936 | 7.842 | 4.4468 | 9.4717 | 11.3578 | 9.8936 | 14.3404 | 23.8121 | 35.1699 | -9.036 | 9.8936 | 7.842 | 4.4468 | 9.4717 | 11.3578 | 9.8936 | 14.3404 | 23.8121 | 35.1699 | 0
1.0174 | 9.3471 | 7.3918 | 6.5517 | 12.7998 | 8.968 | 9.3471 | 15.8988 | 28.6986 | 37.6666 | 1.0274 | 9.3471 | 7.3918 | 6.5517 | 12.7998 | 8.968 | 9.3471 | 15.8988 | 28.6986 | 37.6666 | 0
-0.35472 | 10.5758 | 7.5601 | 10.6701 | 5.1121 | 11.5333 | 10.5758 | 21.2458 | 26.3579 | 37.8912 | -0.34472 | 10.5758 | 7.5601 | 10.6701 | 5.1121 | 11.5333 | 10.5758 | 21.2458 | 26.3579 | 37.8912 | 0
-5.373 | 10.5301 | 8.4033 | 5.0313 | 11.2321 | 12.6819 | 10.5301 | 15.5614 | 26.7935 | 39.4754 | -5.363 | 10.5301 | 8.4033 | 5.0313 | 11.2321 | 12.6819 | 10.5301 | 15.5614 | 26.7935 | 39.4754 | 0
2.2398 | 8.4017 | 8.2457 | 7.6941 | 12.0855 | 12.6244 | 8.4017 | 16.0958 | 28.1813 | 40.8057 | 2.2498 | 8.4017 | 8.2457 | 7.6941 | 12.0855 | 12.6244 | 8.4017 | 16.0958 | 28.1813 | 40.8057 | 0
0.66236 | 9.7646 | 6.3253 | 7.4883 | 13.2902 | 7.2821 | 9.7646 | 17.2529 | 30.5431 | 37.8252 | 0.67236 | 9.7646 | 6.3253 | 7.4883 | 13.2902 | 7.2821 | 9.7646 | 17.2529 | 30.5431 | 37.8252 | 0
13.673 | 9.4343 | 8.6296 | 5.6934 | 13.6128 | 8.818 | 13.673 | 19.3664 | 32.9792 | 41.7972 | 13.683 | 9.4343 | 8.6296 | 5.6934 | 13.6128 | 8.818 | 13.673 | 19.3664 | 32.9792 | 41.7972 | 0
0.78331 | 9.103 | 9.7701 | 8.0299 | 14.0234 | 9.9071 | 9.103 | 17.1329 | 31.1563 | 41.0633 | 0.79331 | 9.103 | 9.7701 | 8.0299 | 14.0234 | 9.9071 | 9.103 | 17.1329 | 31.1563 | 41.0633 | 0
-5.3905 | 8.0547 | 5.3912 | 6.897 | 8.9647 | 7.0249 | 8.0547 | 14.9517 | 23.9165 | 30.9414 | -5.3805 | 8.0547 | 5.3912 | 6.897 | 8.9647 | 7.0249 | 8.0547 | 14.9517 | 23.9165 | 30.9414 | 0
-1.0449 | 10.8765 | 6.8482 | 6.6478 | 12.617 | 9.544 | 10.8765 | 17.5243 | 30.1413 | 39.6853 | -1.0349 | 10.8765 | 6.8482 | 6.6478 | 12.617 | 9.544 | 10.8765 | 17.5243 | 30.1413 | 39.6853 | 0
0.48602 | 10.1901 | 6.1717 | 8.0404 | 7.9007 | 12.0859 | 10.1901 | 18.2304 | 26.1311 | 38.217 | 0.49602 | 10.1901 | 6.1717 | 8.0404 | 7.9007 | 12.0859 | 10.1901 | 18.2304 | 26.1311 | 38.217 | 0
0.61946 | 8.6518 | 8.2151 | 5.2341 | 12.8467 | 12.2316 | 8.6518 | 13.8859 | 26.7325 | 38.9642 | 0.62946 | 8.6518 | 8.2151 | 5.2341 | 12.8467 | 12.2316 | 8.6518 | 13.8859 | 26.7325 | 38.9642 | 0
-2.2832 | 10.3843 | 6.9086 | 6.0868 | 8.5804 | 13.7486 | 10.3843 | 16.4711 | 25.0515 | 38.8001 | -2.2732 | 10.3843 | 6.9086 | 6.0868 | 8.5804 | 13.7486 | 10.3843 | 16.4711 | 25.0515 | 38.8001 | 0
-1.3577 | 9.5103 | 7.5311 | 4.9357 | 7.0834 | 9.4015 | 9.5103 | 14.446 | 21.5293 | 30.9309 | -1.3477 | 9.5103 | 7.5311 | 4.9357 | 7.0834 | 9.4015 | 9.5103 | 14.446 | 21.5293 | 30.9309 | 0
-2.4285 | 8.3321 | 10.5938 | 8.5909 | 6.4012 | 8.9322 | 8.3321 | 16.923 | 23.3242 | 32.2564 | -2.4185 | 8.3321 | 10.5938 | 8.5909 | 6.4012 | 8.9322 | 8.3321 | 16.923 | 23.3242 | 32.2564 | 0
2.4706 | 9.8572 | 6.1015 | 4.8349 | 8.2584 | 13.1972 | 9.8572 | 14.6921 | 22.9506 | 36.1478 | 2.4806 | 9.8572 | 6.1015 | 4.8349 | 8.2584 | 13.1972 | 9.8572 | 14.6921 | 22.9506 | 36.1478 | 0
7.1473 | 8.8251 | 6.2137 | 8.2807 | 6.3848 | 16.017 | 8.8251 | 17.1058 | 23.4906 | 39.5077 | 7.1573 | 8.8251 | 6.2137 | 8.2807 | 6.3848 | 16.017 | 8.8251 | 17.1058 | 23.4906 | 39.5077 | 0
3.8921 | 10.5878 | 6.3344 | 8.5528 | 10.158 | 12.7905 | 10.5878 | 19.1405 | 29.2985 | 42.089 | 3.9021 | 10.5878 | 6.3344 | 8.5528 | 10.158 | 12.7905 | 10.5878 | 19.1405 | 29.2985 | 42.089 | 0
-0.12846 | 10.487 | 5.7193 | 5.7599 | 9.3045 | 2.8192 | 10.487 | 16.2469 | 25.5514 | 28.3706 | -0.11846 | 10.487 | 5.7193 | 5.7599 | 9.3045 | 2.8192 | 10.487 | 16.2469 | 25.5514 | 28.3706 | 0
9.7914 | 9.4898 | 8.6039 | 8.2336 | 12.4125 | 12.651 | 9.7914 | 18.025 | 30.4375 | 43.0884 | 9.8014 | 9.4898 | 8.6039 | 8.2336 | 12.4125 | 12.651 | 9.7914 | 18.025 | 30.4375 | 43.0884 | 0
11.4146 | 10.3236 | 8.6827 | 6.0037 | 10.1607 | 6.928 | 11.4146 | 17.4182 | 27.579 | 34.507 | 11.4246 | 10.3236 | 8.6827 | 6.0037 | 10.1607 | 6.928 | 11.4146 | 17.4182 | 27.579 | 34.507 | 0
11.3309 | 11.2876 | 7.7986 | 6.5128 | 10.6656 | 15.7745 | 11.3309 | 17.8438 | 28.5094 | 44.2839 | 11.3409 | 11.2876 | 7.7986 | 6.5128 | 10.6656 | 15.7745 | 11.3309 | 17.8438 | 28.5094 | 44.2839 | 0
-0.52495 | 9.7493 | 8.4545 | 6.1089 | 5.7994 | 9.9098 | 9.7493 | 15.8582 | 21.6576 | 31.5675 | -0.51495 | 9.7493 | 8.4545 | 6.1089 | 5.7994 | 9.9098 | 9.7493 | 15.8582 | 21.6576 | 31.5675 | 0
13.9264 | 9.1496 | 5.5495 | 10.3095 | 12.6963 | 16.1075 | 13.9264 | 24.2359 | 36.9322 | 53.0397 | 13.9364 | 9.1496 | 5.5495 | 10.3095 | 12.6963 | 16.1075 | 13.9264 | 24.2359 | 36.9322 | 53.0397 | 0
-0.08772 | 9.7345 | 10.1338 | 8.0092 | 15.7546 | 11.688 | 9.7345 | 17.7436 | 33.4983 | 45.1863 | -0.07772 | 9.7345 | 10.1338 | 8.0092 | 15.7546 | 11.688 | 9.7345 | 17.7436 | 33.4983 | 45.1863 | 0
5.1853 | 7.3691 | 7.7634 | 6.8282 | 6.2943 | 12.1475 | 7.3691 | 14.1973 | 20.4916 | 32.6391 | 5.1953 | 7.3691 | 7.7634 | 6.8282 | 6.2943 | 12.1475 | 7.3691 | 14.1973 | 20.4916 | 32.6391 | 0
6.1038 | 10.1198 | 4.6226 | 5.8196 | 9.3971 | 19.6464 | 10.1198 | 15.9394 | 25.3364 | 44.9828 | 6.1138 | 10.1198 | 4.6226 | 5.8196 | 9.3971 | 19.6464 | 10.1198 | 15.9394 | 25.3364 | 44.9828 | 0
5.4297 | 8.9646 | 5.0502 | 6.1988 | 16.9884 | 9.0174 | 8.9646 | 15.1634 | 32.1518 | 41.1692 | 5.4397 | 8.9646 | 5.0502 | 6.1988 | 16.9884 | 9.0174 | 8.9646 | 15.1634 | 32.1518 | 41.1692 | 0
-0.05993 | 7.6919 | 8.1151 | 7.8398 | 8.6209 | 8.564 | 7.6919 | 15.5316 | 24.1526 | 32.7166 | -0.04993 | 7.6919 | 8.1151 | 7.8398 | 8.6209 | 8.564 | 7.6919 | 15.5316 | 24.1526 | 32.7166 | 0
12.2768 | 9.2201 | 5.6655 | 5.9041 | 9.876 | 10.3972 | 12.2768 | 18.1809 | 28.057 | 38.4541 | 12.2868 | 9.2201 | 5.6655 | 5.9041 | 9.876 | 10.3972 | 12.2768 | 18.1809 | 28.057 | 38.4541 | 0
-12.3967 | 9.3517 | 10.6444 | 6.4091 | 9.6982 | 12.5538 | 9.3517 | 15.7608 | 25.459 | 38.0128 | -12.3867 | 9.3517 | 10.6444 | 6.4091 | 9.6982 | 12.5538 | 9.3517 | 15.7608 | 25.459 | 38.0128 | 0
14.9535 | 6.9957 | 4.723 | 3.7428 | 5.2897 | 9.7108 | 14.9535 | 18.6963 | 23.9859 | 33.6967 | 14.9635 | 6.9957 | 4.723 | 3.7428 | 5.2897 | 9.7108 | 14.9535 | 18.6963 | 23.9859 | 33.6967 | 0
5.1706 | 8.877 | 7.6575 | 9.2343 | 5.5368 | 7.931 | 8.877 | 18.1113 | 23.6481 | 31.5791 | 5.1806 | 8.877 | 7.6575 | 9.2343 | 5.5368 | 7.931 | 8.877 | 18.1113 | 23.6481 | 31.5791 | 0
0.47622 | 10.6057 | 11.0913 | 3.8549 | 12.1994 | 12.1109 | 10.6057 | 14.4606 | 26.66 | 38.7709 | 0.48622 | 10.6057 | 11.0913 | 3.8549 | 12.1994 | 12.1109 | 10.6057 | 14.4606 | 26.66 | 38.7709 | 0
7.1753 | 9.251 | 6.2271 | 5.8507 | 7.0105 | 10.9704 | 9.251 | 15.1017 | 22.1122 | 33.0826 | 7.1853 | 9.251 | 6.2271 | 5.8507 | 7.0105 | 10.9704 | 9.251 | 15.1017 | 22.1122 | 33.0826 | 0
-3.388 | 9.7941 | 7.7311 | 6.6787 | 12.2323 | 14.4403 | 9.7941 | 16.4728 | 28.7051 | 43.1454 | -3.378 | 9.7941 | 7.7311 | 6.6787 | 12.2323 | 14.4403 | 9.7941 | 16.4728 | 28.7051 | 43.1454 | 0
0.7784 | 8.9013 | 9.2268 | 9.3895 | 6.8896 | 11.874 | 8.9013 | 18.2907 | 25.1803 | 37.0543 | 0.7884 | 8.9013 | 9.2268 | 9.3895 | 6.8896 | 11.874 | 8.9013 | 18.2907 | 25.1803 | 37.0543 | 0
5.8278 | 9.1194 | 7.7326 | 8.4441 | 10.5956 | 7.1303 | 9.1194 | 17.5636 | 28.1592 | 35.2894 | 5.8378 | 9.1194 | 7.7326 | 8.4441 | 10.5956 | 7.1303 | 9.1194 | 17.5636 | 28.1592 | 35.2894 | 0
7.3603 | 8.5706 | 8.7946 | 5.5737 | 4.2891 | 11.8129 | 8.5706 | 14.1443 | 18.4334 | 30.2463 | 7.3703 | 8.5706 | 8.7946 | 5.5737 | 4.2891 | 11.8129 | 8.5706 | 14.1443 | 18.4334 | 30.2463 | 0
7.1379 | 8.3338 | 10.7903 | 4.0824 | 11.1178 | 12.056 | 8.3338 | 12.4162 | 23.534 | 35.59 | 7.1479 | 8.3338 | 10.7903 | 4.0824 | 11.1178 | 12.056 | 8.3338 | 12.4162 | 23.534 | 35.59 | 0
-0.43424 | 10.7205 | 7.6649 | 6.1074 | 7.5195 | 13.8232 | 10.7205 | 16.8279 | 24.3474 | 38.1705 | -0.42424 | 10.7205 | 7.6649 | 6.1074 | 7.5195 | 13.8232 | 10.7205 | 16.8279 | 24.3474 | 38.1705 | 0
-7.9482 | 9.8224 | 6.6074 | 6.9238 | 9.4658 | 14.256 | 9.8224 | 16.7462 | 26.212 | 40.468 | -7.9382 | 9.8224 | 6.6074 | 6.9238 | 9.4658 | 14.256 | 9.8224 | 16.7462 | 26.212 | 40.468 | 0
5.7835 | 9.4053 | 4.8031 | 4.1324 | 12.274 | 8.446 | 9.4053 | 13.5377 | 25.8117 | 34.2578 | 5.7935 | 9.4053 | 4.8031 | 4.1324 | 12.274 | 8.446 | 9.4053 | 13.5377 | 25.8117 | 34.2578 | 0
-0.59313 | 8.9281 | 10.1589 | 5.4651 | 9.9403 | 12.1197 | 8.9281 | 14.3931 | 24.3335 | 36.4531 | -0.58313 | 8.9281 | 10.1589 | 5.4651 | 9.9403 | 12.1197 | 8.9281 | 14.3931 | 24.3335 | 36.4531 | 0
0.60309 | 9.5284 | 9.5093 | 4.1342 | 7.1667 | 15.3591 | 9.5284 | 13.6625 | 20.8292 | 36.1883 | 0.61309 | 9.5284 | 9.5093 | 4.1342 | 7.1667 | 15.3591 | 9.5284 | 13.6625 | 20.8292 | 36.1883 | 0
1.0787 | 8.1877 | 8.9233 | 6.1043 | 12.1921 | 9.4681 | 8.1877 | 14.292 | 26.484 | 35.9521 | 1.0887 | 8.1877 | 8.9233 | 6.1043 | 12.1921 | 9.4681 | 8.1877 | 14.292 | 26.484 | 35.9521 | 0
13.3597 | 11.7365 | 6.3493 | 10.9382 | 11.1316 | 10.9682 | 13.3597 | 24.2978 | 35.4294 | 46.3977 | 13.3697 | 11.7365 | 6.3493 | 10.9382 | 11.1316 | 10.9682 | 13.3597 | 24.2978 | 35.4294 | 46.3977 | 0
9.5457 | 9.8838 | 7.9642 | 8.1484 | 13.6999 | 8.485 | 9.8838 | 18.0322 | 31.7321 | 40.2171 | 9.5557 | 9.8838 | 7.9642 | 8.1484 | 13.6999 | 8.485 | 9.8838 | 18.0322 | 31.7321 | 40.2171 | 0
3.7039 | 8.9025 | 8.3819 | 4.2782 | 10.4725 | 20.4188 | 8.9025 | 13.1807 | 23.6532 | 44.072 | 3.7139 | 8.9025 | 8.3819 | 4.2782 | 10.4725 | 20.4188 | 8.9025 | 13.1807 | 23.6532 | 44.072 | 0
-1.4513 | 9.3943 | 11.5859 | 6.5251 | 8.0623 | 15.5428 | 9.3943 | 15.9194 | 23.9817 | 39.5246 | -1.4413 | 9.3943 | 11.5859 | 6.5251 | 8.0623 | 15.5428 | 9.3943 | 15.9194 | 23.9817 | 39.5246 | 0
-3.6095 | 8.7868 | 8.9133 | 4.9327 | 14.9035 | 8.7086 | 8.7868 | 13.7195 | 28.6231 | 37.3316 | -3.5995 | 8.7868 | 8.9133 | 4.9327 | 14.9035 | 8.7086 | 8.7868 | 13.7195 | 28.6231 | 37.3316 | 0
7.5961 | 10.661 | 6.1867 | 12.2038 | 10.6111 | 12.7243 | 10.661 | 22.8648 | 33.476 | 46.2002 | 7.6061 | 10.661 | 6.1867 | 12.2038 | 10.6111 | 12.7243 | 10.661 | 22.8648 | 33.476 | 46.2002 | 0
2.2393 | 8.402 | 10.3643 | 4.4029 | 15.4501 | 13.4278 | 8.402 | 12.8049 | 28.255 | 41.6827 | 2.2493 | 8.402 | 10.3643 | 4.4029 | 15.4501 | 13.4278 | 8.402 | 12.8049 | 28.255 | 41.6827 | 0
7.2808 | 8.7998 | 5.0295 | 4.3165 | 15.2221 | 7.4745 | 8.7998 | 13.1163 | 28.3384 | 35.8129 | 7.2908 | 8.7998 | 5.0295 | 4.3165 | 15.2221 | 7.4745 | 8.7998 | 13.1163 | 28.3384 | 35.8129 | 0
9.6534 | 8.5972 | 7.1504 | 9.498 | 6.7155 | 11.3871 | 9.6534 | 19.1514 | 25.8669 | 37.254 | 9.6634 | 8.5972 | 7.1504 | 9.498 | 6.7155 | 11.3871 | 9.6534 | 19.1514 | 25.8669 | 37.254 | 0
3.4709 | 9.5872 | 8.7401 | 5.5957 | 6.7453 | 8.9287 | 9.5872 | 15.183 | 21.9282 | 30.8569 | 3.4809 | 9.5872 | 8.7401 | 5.5957 | 6.7453 | 8.9287 | 9.5872 | 15.183 | 21.9282 | 30.8569 | 0
9.6599 | 10.4412 | 7.1108 | 6.8301 | 13.2016 | 18.225 | 10.4412 | 17.2713 | 30.4729 | 48.6979 | 9.6699 | 10.4412 | 7.1108 | 6.8301 | 13.2016 | 18.225 | 10.4412 | 17.2713 | 30.4729 | 48.6979 | 0
6.8503 | 9.0846 | 9.1109 | 7.6241 | 10.5356 | 14.3201 | 9.0846 | 16.7087 | 27.2443 | 41.5643 | 6.8603 | 9.0846 | 9.1109 | 7.6241 | 10.5356 | 14.3201 | 9.0846 | 16.7087 | 27.2443 | 41.5643 | 0
-7.8404 | 8.272 | 9.8587 | 5.7461 | 7.0942 | 9.8597 | 8.272 | 14.0181 | 21.1123 | 30.972 | -7.8304 | 8.272 | 9.8587 | 5.7461 | 7.0942 | 9.8597 | 8.272 | 14.0181 | 21.1123 | 30.972 | 0
4.7529 | 7.476 | 5.5781 | 8.3035 | 7.9344 | 12.0802 | 7.476 | 15.7795 | 23.7138 | 35.7941 | 4.7629 | 7.476 | 5.5781 | 8.3035 | 7.9344 | 12.0802 | 7.476 | 15.7795 | 23.7138 | 35.7941 | 0
-2.1527 | 9.1407 | 8.0186 | 8.3544 | 4.1246 | 14.5636 | 9.1407 | 17.4952 | 21.6198 | 36.1834 | -2.1427 | 9.1407 | 8.0186 | 8.3544 | 4.1246 | 14.5636 | 9.1407 | 17.4952 | 21.6198 | 36.1834 | 0
-4.6334 | 10.6974 | 10.2383 | 8.9909 | 11.2315 | 5.9132 | 10.6974 | 19.6883 | 30.9198 | 36.833 | -4.6234 | 10.6974 | 10.2383 | 8.9909 | 11.2315 | 5.9132 | 10.6974 | 19.6883 | 30.9198 | 36.833 | 0
6.9525 | 10.0546 | 6.1117 | 11.4149 | 9.8122 | 15.2829 | 10.0546 | 21.4695 | 31.2817 | 46.5646 | 6.9625 | 10.0546 | 6.1117 | 11.4149 | 9.8122 | 15.2829 | 10.0546 | 21.4695 | 31.2817 | 46.5646 | 0
7.4733 | 8.553 | 4.0612 | 8.2754 | 18.5133 | 18.0375 | 8.553 | 16.8284 | 35.3417 | 53.3792 | 7.4833 | 8.553 | 4.0612 | 8.2754 | 18.5133 | 18.0375 | 8.553 | 16.8284 | 35.3417 | 53.3792 | 0
7.8665 | 8.6261 | 3.375 | 5.4863 | 12.8143 | 14.9313 | 8.6261 | 14.1125 | 26.9268 | 41.858 | 7.8765 | 8.6261 | 3.375 | 5.4863 | 12.8143 | 14.9313 | 8.6261 | 14.1125 | 26.9268 | 41.858 | 0
-10.2385 | 10.0417 | 7.3513 | 6.632 | 17.984 | 9.8089 | 10.0417 | 16.6737 | 34.6577 | 44.4666 | -10.2285 | 10.0417 | 7.3513 | 6.632 | 17.984 | 9.8089 | 10.0417 | 16.6737 | 34.6577 | 44.4666 | 0
5.2282 | 8.6895 | 5.9247 | 9.1312 | 10.6852 | 6.1397 | 8.6895 | 17.8207 | 28.5059 | 34.6456 | 5.2382 | 8.6895 | 5.9247 | 9.1312 | 10.6852 | 6.1397 | 8.6895 | 17.8207 | 28.5059 | 34.6456 | 0
-2.0951 | 8.9026 | 6.8093 | 7.1891 | 11.1582 | 12.9912 | 8.9026 | 16.0917 | 27.2499 | 40.2411 | -2.0851 | 8.9026 | 6.8093 | 7.1891 | 11.1582 | 12.9912 | 8.9026 | 16.0917 | 27.2499 | 40.2411 | 0
-10.1614 | 9.3349 | 7.7544 | 6.7375 | 7.5137 | 9.5293 | 9.3349 | 16.0724 | 23.5861 | 33.1154 | -10.1514 | 9.3349 | 7.7544 | 6.7375 | 7.5137 | 9.5293 | 9.3349 | 16.0724 | 23.5861 | 33.1154 | 0
3.5217 | 6.6708 | 5.2837 | 10.773 | 7.4621 | 16.5569 | 6.6708 | 17.4438 | 24.9059 | 41.4628 | 3.5317 | 6.6708 | 5.2837 | 10.773 | 7.4621 | 16.5569 | 6.6708 | 17.4438 | 24.9059 | 41.4628 | 0
-17.0077 | 9.8127 | 8.9103 | 5.7746 | 2.0016 | 15.6078 | 9.8127 | 15.5873 | 18.723 | 34.3308 | -16.9977 | 9.8127 | 8.9103 | 5.7746 | 2.0016 | 15.6078 | 9.8127 | 15.5873 | 18.723 | 34.3308 | 0
9.8058 | 10.5522 | 15.0781 | 7.4246 | 9.8901 | 11.9554 | 10.5522 | 17.9768 | 27.8669 | 39.8223 | 9.8158 | 10.5522 | 15.0781 | 7.4246 | 9.8901 | 11.9554 | 10.5522 | 17.9768 | 27.8669 | 39.8223 | 0
8.9744 | 8.8105 | 8.6108 | 6.68 | 13.3577 | 13.7166 | 8.9744 | 15.6544 | 29.0121 | 42.7287 | 8.9844 | 8.8105 | 8.6108 | 6.68 | 13.3577 | 13.7166 | 8.9744 | 15.6544 | 29.0121 | 42.7287 | 0
2.2576 | 9.1059 | 9.1843 | 5.8992 | 10.4791 | 12.5217 | 9.1059 | 15.0052 | 25.4842 | 38.0059 | 2.2676 | 9.1059 | 9.1843 | 5.8992 | 10.4791 | 12.5217 | 9.1059 | 15.0052 | 25.4842 | 38.0059 | 0
-1.0245 | 9.1762 | 8.9615 | 5.7854 | 11.3971 | 13.0465 | 9.1762 | 14.9616 | 26.3587 | 39.4051 | -1.0145 | 9.1762 | 8.9615 | 5.7854 | 11.3971 | 13.0465 | 9.1762 | 14.9616 | 26.3587 | 39.4051 | 0
1.6296 | 9.3603 | 5.4177 | 7.8363 | 11.7324 | 14.2943 | 9.3603 | 17.1966 | 28.929 | 43.2233 | 1.6396 | 9.3603 | 5.4177 | 7.8363 | 11.7324 | 14.2943 | 9.3603 | 17.1966 | 28.929 | 43.2233 | 0
9.2436 | 8.1045 | 8.2566 | 6.8263 | 11.1857 | 11.2467 | 9.2436 | 16.0699 | 27.2557 | 38.5024 | 9.2536 | 8.1045 | 8.2566 | 6.8263 | 11.1857 | 11.2467 | 9.2436 | 16.0699 | 27.2557 | 38.5024 | 0
4.2623 | 9.3401 | 7.1997 | 10.3348 | 7.5744 | 11.2182 | 9.3401 | 19.6749 | 27.2493 | 38.4675 | 4.2723 | 9.3401 | 7.1997 | 10.3348 | 7.5744 | 11.2182 | 9.3401 | 19.6749 | 27.2493 | 38.4675 | 0
13.6747 | 9.2027 | 7.8255 | 3.2423 | 7.3924 | 14.894 | 13.6747 | 16.917 | 24.3094 | 39.2034 | 13.6847 | 9.2027 | 7.8255 | 3.2423 | 7.3924 | 14.894 | 13.6747 | 16.917 | 24.3094 | 39.2034 | 0
5.1721 | 8.9406 | 6.7367 | 6.818 | 6.0591 | 10.0821 | 8.9406 | 15.7586 | 21.8176 | 31.8997 | 5.1821 | 8.9406 | 6.7367 | 6.818 | 6.0591 | 10.0821 | 8.9406 | 15.7586 | 21.8176 | 31.8997 | 0
10.284 | 8.8172 | 9.8835 | 4.3166 | 16.5497 | 15.3925 | 10.284 | 14.6006 | 31.1503 | 46.5427 | 10.294 | 8.8172 | 9.8835 | 4.3166 | 16.5497 | 15.3925 | 10.284 | 14.6006 | 31.1503 | 46.5427 | 0
0.62186 | 8.6491 | 9.0574 | 3.34 | 6.6836 | 14.4911 | 8.6491 | 11.989 | 18.6727 | 33.1638 | 0.63186 | 8.6491 | 9.0574 | 3.34 | 6.6836 | 14.4911 | 8.6491 | 11.989 | 18.6727 | 33.1638 | 0
8.2262 | 10.4837 | 10.4507 | 4.58 | 7.8471 | 11.317 | 10.4837 | 15.0637 | 22.9107 | 34.2277 | 8.2362 | 10.4837 | 10.4507 | 4.58 | 7.8471 | 11.317 | 10.4837 | 15.0637 | 22.9107 | 34.2277 | 0
9.3591 | 7.9881 | 7.9803 | 7.4932 | 11.0053 | 18.2569 | 9.3591 | 16.8523 | 27.8576 | 46.1144 | 9.3691 | 7.9881 | 7.9803 | 7.4932 | 11.0053 | 18.2569 | 9.3591 | 16.8523 | 27.8576 | 46.1144 | 0
-3.5631 | 9.247 | 7.2199 | 6.0037 | 15.8212 | 17.3977 | 9.247 | 15.2508 | 31.072 | 48.4697 | -3.5531 | 9.247 | 7.2199 | 6.0037 | 15.8212 | 17.3977 | 9.247 | 15.2508 | 31.072 | 48.4697 | 0
0.65855 | 8.1756 | 4.9883 | 7.7424 | 7.9659 | 8.4836 | 8.1756 | 15.918 | 23.8839 | 32.3675 | 0.66855 | 8.1756 | 4.9883 | 7.7424 | 7.9659 | 8.4836 | 8.1756 | 15.918 | 23.8839 | 32.3675 | 0
7.6672 | 8.0825 | 5.3904 | 6.3704 | 12.5505 | 11.8694 | 8.0825 | 14.4529 | 27.0034 | 38.8728 | 7.6772 | 8.0825 | 5.3904 | 6.3704 | 12.5505 | 11.8694 | 8.0825 | 14.4529 | 27.0034 | 38.8728 | 0
4.708 | 7.1751 | 5.8385 | 3.4724 | 11.508 | 13.4875 | 7.1751 | 10.6475 | 22.1555 | 35.643 | 4.718 | 7.1751 | 5.8385 | 3.4724 | 11.508 | 13.4875 | 7.1751 | 10.6475 | 22.1555 | 35.643 | 0
-9.2498 | 9.1068 | 7.2094 | 7.1537 | 7.6903 | 13.4143 | 9.1068 | 16.2606 | 23.9509 | 37.3652 | -9.2398 | 9.1068 | 7.2094 | 7.1537 | 7.6903 | 13.4143 | 9.1068 | 16.2606 | 23.9509 | 37.3652 | 0
10.3135 | 9.1207 | 7.0799 | 6.3311 | 3.9128 | 9.401 | 10.3135 | 16.6445 | 20.5574 | 29.9584 | 10.3235 | 9.1207 | 7.0799 | 6.3311 | 3.9128 | 9.401 | 10.3135 | 16.6445 | 20.5574 | 29.9584 | 0
-7.1147 | 10.0777 | 6.4256 | 3.2637 | 12.0208 | 10.6136 | 10.0777 | 13.3414 | 25.3622 | 35.9758 | -7.1047 | 10.0777 | 6.4256 | 3.2637 | 12.0208 | 10.6136 | 10.0777 | 13.3414 | 25.3622 | 35.9758 | 0
6.9652 | 6.9739 | 6.9978 | 9.0566 | 10.1619 | 14.1531 | 6.9739 | 16.0305 | 26.1924 | 40.3455 | 6.9752 | 6.9739 | 6.9978 | 9.0566 | 10.1619 | 14.1531 | 6.9739 | 16.0305 | 26.1924 | 40.3455 | 0
10.3489 | 8.5485 | 12.8478 | 9.6492 | 6.7188 | 12.4319 | 10.3489 | 19.9981 | 26.7169 | 39.1488 | 10.3589 | 8.5485 | 12.8478 | 9.6492 | 6.7188 | 12.4319 | 10.3489 | 19.9981 | 26.7169 | 39.1488 | 0
-4.2967 | 7.7478 | 11.904 | 8.8942 | 7.7514 | 11.6692 | 7.7478 | 16.642 | 24.3934 | 36.0626 | -4.2867 | 7.7478 | 11.904 | 8.8942 | 7.7514 | 11.6692 | 7.7478 | 16.642 | 24.3934 | 36.0626 | 0
0.018473 | 10.3923 | 11.2043 | 7.3941 | 8.9181 | 13.8139 | 10.3923 | 17.7863 | 26.7044 | 40.5183 | 0.028473 | 10.3923 | 11.2043 | 7.3941 | 8.9181 | 13.8139 | 10.3923 | 17.7863 | 26.7044 | 40.5183 | 0
5.8056 | 7.8653 | 11.2427 | 4.1987 | 12.3849 | 11.9458 | 7.8653 | 12.064 | 24.4489 | 36.3947 | 5.8156 | 7.8653 | 11.2427 | 4.1987 | 12.3849 | 11.9458 | 7.8653 | 12.064 | 24.4489 | 36.3947 | 0
3.2624 | 8.8102 | 5.8 | 8.0381 | 11.7199 | 10.7845 | 8.8102 | 16.8483 | 28.5682 | 39.3527 | 3.2724 | 8.8102 | 5.8 | 8.0381 | 11.7199 | 10.7845 | 8.8102 | 16.8483 | 28.5682 | 39.3527 | 0
9.1484 | 9.6298 | 4.7744 | 6.9043 | 13.8674 | 10.5677 | 9.6298 | 16.534 | 30.4015 | 40.9692 | 9.1584 | 9.6298 | 4.7744 | 6.9043 | 13.8674 | 10.5677 | 9.6298 | 16.534 | 30.4015 | 40.9692 | 0
7.2413 | 9.7773 | 7.4252 | 8.4001 | 10.7422 | 14.6685 | 9.7773 | 18.1774 | 28.9196 | 43.5881 | 7.2513 | 9.7773 | 7.4252 | 8.4001 | 10.7422 | 14.6685 | 9.7773 | 18.1774 | 28.9196 | 43.5881 | 0
7.1281 | 10.9589 | 9.588 | 7.0999 | 10.2467 | 10.5351 | 10.9589 | 18.0588 | 28.3055 | 38.8406 | 7.1381 | 10.9589 | 9.588 | 7.0999 | 10.2467 | 10.5351 | 10.9589 | 18.0588 | 28.3055 | 38.8406 | 0
5.8199 | 9.7217 | 4.2314 | 6.2448 | 8.4724 | 16.5646 | 9.7217 | 15.9664 | 24.4389 | 41.0034 | 5.8299 | 9.7217 | 4.2314 | 6.2448 | 8.4724 | 16.5646 | 9.7217 | 15.9664 | 24.4389 | 41.0034 | 0
3.435 | 8.3011 | 6.3764 | 6.7709 | 8.4566 | 10.1424 | 8.3011 | 15.0721 | 23.5287 | 33.6711 | 3.445 | 8.3011 | 6.3764 | 6.7709 | 8.4566 | 10.1424 | 8.3011 | 15.0721 | 23.5287 | 33.6711 | 0
12.2896 | 9.5205 | 7.801 | 5.7442 | 8.1832 | 12.0245 | 12.2896 | 18.0338 | 26.217 | 38.2414 | 12.2996 | 9.5205 | 7.801 | 5.7442 | 8.1832 | 12.0245 | 12.2896 | 18.0338 | 26.217 | 38.2414 | 0
-1.1384 | 9.9873 | 7.6728 | 6.6991 | 15.4831 | 9.3336 | 9.9873 | 16.6863 | 32.1694 | 41.503 | -1.1284 | 9.9873 | 7.6728 | 6.6991 | 15.4831 | 9.3336 | 9.9873 | 16.6863 | 32.1694 | 41.503 | 0
11.0193 | 8.5678 | 7.098 | 6.4943 | 15.106 | 15.2256 | 11.0193 | 17.5135 | 32.6196 | 47.8451 | 11.0293 | 8.5678 | 7.098 | 6.4943 | 15.106 | 15.2256 | 11.0193 | 17.5135 | 32.6196 | 47.8451 | 0
-4.2848 | 9.3012 | 5.6575 | 9.3297 | 7.0192 | 14.313 | 9.3012 | 18.6309 | 25.6501 | 39.963 | -4.2748 | 9.3012 | 5.6575 | 9.3297 | 7.0192 | 14.313 | 9.3012 | 18.6309 | 25.6501 | 39.963 | 0
-6.368 | 8.2513 | 7.6363 | 8.7384 | 10.4732 | 11.6597 | 8.2513 | 16.9897 | 27.4629 | 39.1226 | -6.358 | 8.2513 | 7.6363 | 8.7384 | 10.4732 | 11.6597 | 8.2513 | 16.9897 | 27.4629 | 39.1226 | 0
5.8127 | 9.4866 | 10.1507 | 8.7723 | 11.9801 | 12.6284 | 9.4866 | 18.259 | 30.2391 | 42.8675 | 5.8227 | 9.4866 | 10.1507 | 8.7723 | 11.9801 | 12.6284 | 9.4866 | 18.259 | 30.2391 | 42.8675 | 0
17.0136 | 7.5982 | 7.0678 | 5.4258 | 11.6761 | 13.9709 | 17.0136 | 22.4395 | 34.1156 | 48.0864 | 17.0236 | 7.5982 | 7.0678 | 5.4258 | 11.6761 | 13.9709 | 17.0136 | 22.4395 | 34.1156 | 48.0864 | 0
-1.1175 | 9.405 | 11.3321 | 8.7242 | 10.1518 | 7.5048 | 9.405 | 18.1292 | 28.281 | 35.7859 | -1.1075 | 9.405 | 11.3321 | 8.7242 | 10.1518 | 7.5048 | 9.405 | 18.1292 | 28.281 | 35.7859 | 0
-0.67631 | 9.4048 | 9.3871 | 4.5743 | 11.6437 | 10.8068 | 9.4048 | 13.979 | 25.6227 | 36.4295 | -0.66631 | 9.4048 | 9.3871 | 4.5743 | 11.6437 | 10.8068 | 9.4048 | 13.979 | 25.6227 | 36.4295 | 0
20.283 | 7.7764 | 6.7474 | 6.0426 | 9.1775 | 10.3284 | 20.283 | 26.3256 | 35.5031 | 45.8315 | 20.293 | 7.7764 | 6.7474 | 6.0426 | 9.1775 | 10.3284 | 20.283 | 26.3256 | 35.5031 | 45.8315 | 0
3.3203 | 7.9152 | 7.176 | 5.6612 | 5.0172 | 8.0871 | 7.9152 | 13.5765 | 18.5936 | 26.6807 | 3.3303 | 7.9152 | 7.176 | 5.6612 | 5.0172 | 8.0871 | 7.9152 | 13.5765 | 18.5936 | 26.6807 | 0
-5.9206 | 8.8431 | 5.9055 | 3.1252 | 12.7178 | 12.2355 | 8.8431 | 11.9683 | 24.686 | 36.9216 | -5.9106 | 8.8431 | 5.9055 | 3.1252 | 12.7178 | 12.2355 | 8.8431 | 11.9683 | 24.686 | 36.9216 | 0
6.6041 | 9.9669 | 10.2664 | 8.7488 | 14.005 | 11.2194 | 9.9669 | 18.7157 | 32.7207 | 43.9401 | 6.6141 | 9.9669 | 10.2664 | 8.7488 | 14.005 | 11.2194 | 9.9669 | 18.7157 | 32.7207 | 43.9401 | 0
-1.4922 | 9.007 | 6.2346 | 8.5024 | 10.7579 | 10.8288 | 9.007 | 17.5094 | 28.2673 | 39.0962 | -1.4822 | 9.007 | 6.2346 | 8.5024 | 10.7579 | 10.8288 | 9.007 | 17.5094 | 28.2673 | 39.0962 | 0
2.0897 | 9.4241 | 7.804 | 5.1284 | 9.8339 | 17.0343 | 9.4241 | 14.5525 | 24.3864 | 41.4207 | 2.0997 | 9.4241 | 7.804 | 5.1284 | 9.8339 | 17.0343 | 9.4241 | 14.5525 | 24.3864 | 41.4207 | 0
4.9119 | 10.2556 | 8.3336 | 2.7838 | 10.1735 | 13.8671 | 10.2556 | 13.0394 | 23.2129 | 37.08 | 4.9219 | 10.2556 | 8.3336 | 2.7838 | 10.1735 | 13.8671 | 10.2556 | 13.0394 | 23.2129 | 37.08 | 0
-3.4532 | 8.6561 | 10.1716 | 6.101 | 6.9583 | 19.6067 | 8.6561 | 14.7572 | 21.7154 | 41.3221 | -3.4432 | 8.6561 | 10.1716 | 6.101 | 6.9583 | 19.6067 | 8.6561 | 14.7572 | 21.7154 | 41.3221 | 0
-11.3494 | 9.0676 | 7.7725 | 5.3347 | 8.5681 | 13.2414 | 9.0676 | 14.4023 | 22.9704 | 36.2118 | -11.3394 | 9.0676 | 7.7725 | 5.3347 | 8.5681 | 13.2414 | 9.0676 | 14.4023 | 22.9704 | 36.2118 | 0
-2.4303 | 8.3431 | 8.3272 | 8.6688 | 11.1534 | 15.4153 | 8.3431 | 17.0119 | 28.1653 | 43.5806 | -2.4203 | 8.3431 | 8.3272 | 8.6688 | 11.1534 | 15.4153 | 8.3431 | 17.0119 | 28.1653 | 43.5806 | 0
-12.9816 | 7.7685 | 8.075 | 7.3222 | 8.0263 | 12.9255 | 7.7685 | 15.0907 | 23.117 | 36.0426 | -12.9716 | 7.7685 | 8.075 | 7.3222 | 8.0263 | 12.9255 | 7.7685 | 15.0907 | 23.117 | 36.0426 | 0
-1.6426 | 7.8413 | 9.4667 | 4.8768 | 12.9009 | 13.6434 | 7.8413 | 12.7181 | 25.619 | 39.2624 | -1.6326 | 7.8413 | 9.4667 | 4.8768 | 12.9009 | 13.6434 | 7.8413 | 12.7181 | 25.619 | 39.2624 | 0
4.4732 | 7.5636 | 6.0176 | 8.5703 | 14.2528 | 14.7431 | 7.5636 | 16.1339 | 30.3867 | 45.1297 | 4.4832 | 7.5636 | 6.0176 | 8.5703 | 14.2528 | 14.7431 | 7.5636 | 16.1339 | 30.3867 | 45.1297 | 0
-12.672 | 7.548 | 7.7645 | 7.1432 | 9.7024 | 10.1467 | 7.548 | 14.6912 | 24.3937 | 34.5404 | -12.662 | 7.548 | 7.7645 | 7.1432 | 9.7024 | 10.1467 | 7.548 | 14.6912 | 24.3937 | 34.5404 | 0
3.6516 | 8.154 | 9.569 | 5.0721 | 10.1168 | 11.7558 | 8.154 | 13.2261 | 23.3429 | 35.0987 | 3.6616 | 8.154 | 9.569 | 5.0721 | 10.1168 | 11.7558 | 8.154 | 13.2261 | 23.3429 | 35.0987 | 0
-6.1434 | 10.8168 | 7.2792 | 8.1049 | 9.3238 | 10.6696 | 10.8168 | 18.9217 | 28.2455 | 38.9151 | -6.1334 | 10.8168 | 7.2792 | 8.1049 | 9.3238 | 10.6696 | 10.8168 | 18.9217 | 28.2455 | 38.9151 | 0
-4.0802 | 7.7665 | 6.3402 | 6.7583 | 14.9452 | 13.792 | 7.7665 | 14.5248 | 29.4699 | 43.2619 | -4.0702 | 7.7665 | 6.3402 | 6.7583 | 14.9452 | 13.792 | 7.7665 | 14.5248 | 29.4699 | 43.2619 | 0
2.1544 | 9.9304 | 10.036 | 3.7244 | 12.2005 | 12.9176 | 9.9304 | 13.6549 | 25.8553 | 38.7729 | 2.1644 | 9.9304 | 10.036 | 3.7244 | 12.2005 | 12.9176 | 9.9304 | 13.6549 | 25.8553 | 38.7729 | 0
-8.949 | 9.6957 | 13.8493 | 7.9574 | 15.7289 | 13.7025 | 9.6957 | 17.6531 | 33.3821 | 47.0846 | -8.939 | 9.6957 | 13.8493 | 7.9574 | 15.7289 | 13.7025 | 9.6957 | 17.6531 | 33.3821 | 47.0846 | 0
4.2971 | 9.4154 | 4.0266 | 9.1165 | 13.81 | 16.3174 | 9.4154 | 18.532 | 32.3419 | 48.6593 | 4.3071 | 9.4154 | 4.0266 | 9.1165 | 13.81 | 16.3174 | 9.4154 | 18.532 | 32.3419 | 48.6593 | 0
-3.679 | 9.6832 | 8.5033 | 7.356 | 15.3826 | 12.1653 | 9.6832 | 17.0391 | 32.4218 | 44.5871 | -3.669 | 9.6832 | 8.5033 | 7.356 | 15.3826 | 12.1653 | 9.6832 | 17.0391 | 32.4218 | 44.5871 | 0
10.22 | 8.9409 | 6.5341 | 7.4052 | 9.2422 | 14.2614 | 10.22 | 17.6252 | 26.8674 | 41.1288 | 10.23 | 8.9409 | 6.5341 | 7.4052 | 9.2422 | 14.2614 | 10.22 | 17.6252 | 26.8674 | 41.1288 | 0
3.9217 | 8.3816 | 8.8318 | 8.1083 | 11.2951 | 10.8473 | 8.3816 | 16.4899 | 27.785 | 38.6323 | 3.9317 | 8.3816 | 8.8318 | 8.1083 | 11.2951 | 10.8473 | 8.3816 | 16.4899 | 27.785 | 38.6323 | 0
9.2402 | 7.8728 | 10.1546 | 6.3744 | 10.4284 | 8.8509 | 9.2402 | 15.6146 | 26.043 | 34.8939 | 9.2502 | 7.8728 | 10.1546 | 6.3744 | 10.4284 | 8.8509 | 9.2402 | 15.6146 | 26.043 | 34.8939 | 0
6.9783 | 6.7912 | 8.9999 | 10.4621 | 11.1987 | 11.2218 | 6.9783 | 17.4404 | 28.6391 | 39.8609 | 6.9883 | 6.7912 | 8.9999 | 10.4621 | 11.1987 | 11.2218 | 6.9783 | 17.4404 | 28.6391 | 39.8609 | 0
-0.53323 | 8.8902 | 12.0261 | 8.6654 | 13.5837 | 12.8922 | 8.8902 | 17.5556 | 31.1392 | 44.0314 | -0.52323 | 8.8902 | 12.0261 | 8.6654 | 13.5837 | 12.8922 | 8.8902 | 17.5556 | 31.1392 | 44.0314 | 0
2.2051 | 9.5901 | 7.16 | 6.3142 | 7.4703 | 12.0579 | 9.5901 | 15.9043 | 23.3746 | 35.4325 | 2.2151 | 9.5901 | 7.16 | 6.3142 | 7.4703 | 12.0579 | 9.5901 | 15.9043 | 23.3746 | 35.4325 | 0
4.9195 | 10.1396 | 4.5554 | 7.7893 | 13.3626 | 14.4412 | 10.1396 | 17.9289 | 31.2915 | 45.7327 | 4.9295 | 10.1396 | 4.5554 | 7.7893 | 13.3626 | 14.4412 | 10.1396 | 17.9289 | 31.2915 | 45.7327 | 0
5.3197 | 9.6553 | 7.7932 | 6.6513 | 9.4943 | 15.1054 | 9.6553 | 16.3066 | 25.8009 | 40.9063 | 5.3297 | 9.6553 | 7.7932 | 6.6513 | 9.4943 | 15.1054 | 9.6553 | 16.3066 | 25.8009 | 40.9063 | 0
0.4068 | 8.367 | 7.8558 | 5.4698 | 11.1779 | 15.718 | 8.367 | 13.8367 | 25.0147 | 40.7327 | 0.4168 | 8.367 | 7.8558 | 5.4698 | 11.1779 | 15.718 | 8.367 | 13.8367 | 25.0147 | 40.7327 | 0
6.8387 | 8.4817 | 7.4772 | 8.8499 | 6.3035 | 11.1335 | 8.4817 | 17.3316 | 23.6351 | 34.7686 | 6.8487 | 8.4817 | 7.4772 | 8.8499 | 6.3035 | 11.1335 | 8.4817 | 17.3316 | 23.6351 | 34.7686 | 0
5.0778 | 9.7531 | 8.6179 | 9.2265 | 18.2138 | 12.205 | 9.7531 | 18.9796 | 37.1934 | 49.3984 | 5.0878 | 9.7531 | 8.6179 | 9.2265 | 18.2138 | 12.205 | 9.7531 | 18.9796 | 37.1934 | 49.3984 | 0
8.8286 | 10.0963 | 7.786 | 11.158 | 4.9954 | 9.725 | 10.0963 | 21.2542 | 26.2496 | 35.9746 | 8.8386 | 10.0963 | 7.786 | 11.158 | 4.9954 | 9.725 | 10.0963 | 21.2542 | 26.2496 | 35.9746 | 0
1.5765 | 7.8057 | 7.8306 | 9.2106 | 11.0822 | 17.0273 | 7.8057 | 17.0163 | 28.0985 | 45.1258 | 1.5865 | 7.8057 | 7.8306 | 9.2106 | 11.0822 | 17.0273 | 7.8057 | 17.0163 | 28.0985 | 45.1258 | 0
4.263 | 9.1471 | 7.2336 | 5.9646 | 11.6588 | 15.4198 | 9.1471 | 15.1117 | 26.7705 | 42.1903 | 4.273 | 9.1471 | 7.2336 | 5.9646 | 11.6588 | 15.4198 | 9.1471 | 15.1117 | 26.7705 | 42.1903 | 0
4.9646 | 8.24 | 9.3813 | 6.3525 | 8.4576 | 15.8644 | 8.24 | 14.5926 | 23.0502 | 38.9146 | 4.9746 | 8.24 | 9.3813 | 6.3525 | 8.4576 | 15.8644 | 8.24 | 14.5926 | 23.0502 | 38.9146 | 0
0.69325 | 9.5841 | 4.9877 | 5.5021 | 7.5966 | 12.9524 | 9.5841 | 15.0862 | 22.6828 | 35.6352 | 0.70325 | 9.5841 | 4.9877 | 5.5021 | 7.5966 | 12.9524 | 9.5841 | 15.0862 | 22.6828 | 35.6352 | 0
4.5451 | 10.3154 | 7.7966 | 6.1392 | 5.8634 | 15.9408 | 10.3154 | 16.4546 | 22.3181 | 38.2589 | 4.5551 | 10.3154 | 7.7966 | 6.1392 | 5.8634 | 15.9408 | 10.3154 | 16.4546 | 22.3181 | 38.2589 | 0
3.6778 | 7.4605 | 9.9027 | 6.2583 | 8.3074 | 16.0347 | 7.4605 | 13.7188 | 22.0262 | 38.0608 | 3.6878 | 7.4605 | 9.9027 | 6.2583 | 8.3074 | 16.0347 | 7.4605 | 13.7188 | 22.0262 | 38.0608 | 0
-0.85575 | 8.4614 | 9.3082 | 9.7912 | 13.9034 | 12.9334 | 8.4614 | 18.2526 | 32.156 | 45.0893 | -0.84575 | 8.4614 | 9.3082 | 9.7912 | 13.9034 | 12.9334 | 8.4614 | 18.2526 | 32.156 | 45.0893 | 0
5.0467 | 8.8962 | 8.5106 | 7.6545 | 8.4361 | 11.1784 | 8.8962 | 16.5507 | 24.9868 | 36.1653 | 5.0567 | 8.8962 | 8.5106 | 7.6545 | 8.4361 | 11.1784 | 8.8962 | 16.5507 | 24.9868 | 36.1653 | 0
0.42102 | 9.8463 | 10.8102 | 5.2914 | 8.0975 | 21.1271 | 9.8463 | 15.1377 | 23.2352 | 44.3623 | 0.43102 | 9.8463 | 10.8102 | 5.2914 | 8.0975 | 21.1271 | 9.8463 | 15.1377 | 23.2352 | 44.3623 | 0
-4.4133 | 9.1094 | 7.7604 | 3.2464 | 15.1303 | 10.1657 | 9.1094 | 12.3557 | 27.4861 | 37.6518 | -4.4033 | 9.1094 | 7.7604 | 3.2464 | 15.1303 | 10.1657 | 9.1094 | 12.3557 | 27.4861 | 37.6518 | 0
-12.2194 | 8.6863 | 5.305 | 8.4443 | 12.8753 | 12.765 | 8.6863 | 17.1305 | 30.0059 | 42.7709 | -12.2094 | 8.6863 | 5.305 | 8.4443 | 12.8753 | 12.765 | 8.6863 | 17.1305 | 30.0059 | 42.7709 | 0
2.2876 | 10.186 | 6.9594 | 7.6086 | 16.0767 | 4.9805 | 10.186 | 17.7946 | 33.8713 | 38.8518 | 2.2976 | 10.186 | 6.9594 | 7.6086 | 16.0767 | 4.9805 | 10.186 | 17.7946 | 33.8713 | 38.8518 | 0
6.0706 | 11.2817 | 6.0536 | 7.7388 | 7.9842 | 8.6284 | 11.2817 | 19.0205 | 27.0047 | 35.6331 | 6.0806 | 11.2817 | 6.0536 | 7.7388 | 7.9842 | 8.6284 | 11.2817 | 19.0205 | 27.0047 | 35.6331 | 0
-1.1181 | 10.0907 | 4.6662 | 5.145 | 8.9094 | 15.4453 | 10.0907 | 15.2357 | 24.1451 | 39.5903 | -1.1081 | 10.0907 | 4.6662 | 5.145 | 8.9094 | 15.4453 | 10.0907 | 15.2357 | 24.1451 | 39.5903 | 0
4.532 | 9.1977 | 9.9021 | 2.7663 | 10.8537 | 11.8001 | 9.1977 | 11.964 | 22.8178 | 34.6178 | 4.542 | 9.1977 | 9.9021 | 2.7663 | 10.8537 | 11.8001 | 9.1977 | 11.964 | 22.8178 | 34.6178 | 0
-2.9873 | 9.5995 | 8.0849 | 1.4856 | 7.3979 | 16.787 | 9.5995 | 11.0851 | 18.4829 | 35.2699 | -2.9773 | 9.5995 | 8.0849 | 1.4856 | 7.3979 | 16.787 | 9.5995 | 11.0851 | 18.4829 | 35.2699 | 0
2.9506 | 10.0332 | 5.7485 | 11.3445 | 10.2375 | 15.2688 | 10.0332 | 21.3776 | 31.6151 | 46.8839 | 2.9606 | 10.0332 | 5.7485 | 11.3445 | 10.2375 | 15.2688 | 10.0332 | 21.3776 | 31.6151 | 46.8839 | 0
-0.6585 | 8.2184 | 6.3838 | 5.6742 | 11.2969 | 12.8751 | 8.2184 | 13.8926 | 25.1895 | 38.0646 | -0.6485 | 8.2184 | 6.3838 | 5.6742 | 11.2969 | 12.8751 | 8.2184 | 13.8926 | 25.1895 | 38.0646 | 0
-9.446 | 9.7612 | 6.7274 | 9.0213 | 8.7623 | 7.583 | 9.7612 | 18.7825 | 27.5449 | 35.1279 | -9.436 | 9.7612 | 6.7274 | 9.0213 | 8.7623 | 7.583 | 9.7612 | 18.7825 | 27.5449 | 35.1279 | 0
-2.1706 | 9.6565 | 7.1763 | 7.2213 | 12.9613 | 10.5281 | 9.6565 | 16.8778 | 29.8392 | 40.3673 | -2.1606 | 9.6565 | 7.1763 | 7.2213 | 12.9613 | 10.5281 | 9.6565 | 16.8778 | 29.8392 | 40.3673 | 0
0.57263 | 9.6875 | 6.5661 | 10.3063 | 11.5403 | 8.9055 | 9.6875 | 19.9938 | 31.534 | 40.4396 | 0.58263 | 9.6875 | 6.5661 | 10.3063 | 11.5403 | 8.9055 | 9.6875 | 19.9938 | 31.534 | 40.4396 | 0
-0.67316 | 8.3127 | 7.3892 | 10.2721 | 10.3427 | 11.7983 | 8.3127 | 18.5848 | 28.9275 | 40.7258 | -0.66316 | 8.3127 | 7.3892 | 10.2721 | 10.3427 | 11.7983 | 8.3127 | 18.5848 | 28.9275 | 40.7258 | 0
-3.4448 | 9.7032 | 4.675 | 5.7437 | 12.0852 | 17.2223 | 9.7032 | 15.4469 | 27.5321 | 44.7544 | -3.4348 | 9.7032 | 4.675 | 5.7437 | 12.0852 | 17.2223 | 9.7032 | 15.4469 | 27.5321 | 44.7544 | 0
-2.7407 | 7.9191 | 6.1369 | 2.0562 | 8.706 | 9.9142 | 7.9191 | 9.9753 | 18.6813 | 28.5955 | -2.7307 | 7.9191 | 6.1369 | 2.0562 | 8.706 | 9.9142 | 7.9191 | 9.9753 | 18.6813 | 28.5955 | 0
12.3216 | 10.2544 | 7.3942 | 10.0913 | 10.7351 | 12.7944 | 12.3216 | 22.4129 | 33.148 | 45.9424 | 12.3316 | 10.2544 | 7.3942 | 10.0913 | 10.7351 | 12.7944 | 12.3216 | 22.4129 | 33.148 | 45.9424 | 0
1.4581 | 9.9421 | 5.0191 | 5.3673 | 7.5103 | 11.9307 | 9.9421 | 15.3094 | 22.8197 | 34.7503 | 1.4681 | 9.9421 | 5.0191 | 5.3673 | 7.5103 | 11.9307 | 9.9421 | 15.3094 | 22.8197 | 34.7503 | 0
6.3208 | 8.606 | 9.6485 | 6.746 | 12.1755 | 12.7305 | 8.606 | 15.352 | 27.5274 | 40.2579 | 6.3308 | 8.606 | 9.6485 | 6.746 | 12.1755 | 12.7305 | 8.606 | 15.352 | 27.5274 | 40.2579 | 0
-2.7612 | 8.8014 | 6.3467 | 5.052 | 7.2687 | 9.3164 | 8.8014 | 13.8534 | 21.1221 | 30.4385 | -2.7512 | 8.8014 | 6.3467 | 5.052 | 7.2687 | 9.3164 | 8.8014 | 13.8534 | 21.1221 | 30.4385 | 0
-2.2937 | 9.3184 | 6.5462 | 7.7763 | 6.043 | 3.5338 | 9.3184 | 17.0947 | 23.1377 | 26.6716 | -2.2837 | 9.3184 | 6.5462 | 7.7763 | 6.043 | 3.5338 | 9.3184 | 17.0947 | 23.1377 | 26.6716 | 0
-3.3624 | 7.5407 | 9.5629 | 4.5866 | 14.0103 | 8.1905 | 7.5407 | 12.1273 | 26.1376 | 34.3281 | -3.3524 | 7.5407 | 9.5629 | 4.5866 | 14.0103 | 8.1905 | 7.5407 | 12.1273 | 26.1376 | 34.3281 | 0
3.5012 | 7.4328 | 6.9248 | 5.6576 | 9.7983 | 12.3677 | 7.4328 | 13.0904 | 22.8887 | 35.2564 | 3.5112 | 7.4328 | 6.9248 | 5.6576 | 9.7983 | 12.3677 | 7.4328 | 13.0904 | 22.8887 | 35.2564 | 0
5.8803 | 9.8096 | 6.2285 | 6.4225 | 5.3002 | 9.9497 | 9.8096 | 16.2321 | 21.5323 | 31.482 | 5.8903 | 9.8096 | 6.2285 | 6.4225 | 5.3002 | 9.9497 | 9.8096 | 16.2321 | 21.5323 | 31.482 | 0
3.1079 | 7.6855 | 9.188 | 9.5723 | 15.1571 | 7.28 | 7.6855 | 17.2578 | 32.4149 | 39.695 | 3.1179 | 7.6855 | 9.188 | 9.5723 | 15.1571 | 7.28 | 7.6855 | 17.2578 | 32.4149 | 39.695 | 0
2.4778 | 9.4716 | 10.1933 | 8.5841 | 10.7016 | 14.6195 | 9.4716 | 18.0557 | 28.7574 | 43.3769 | 2.4878 | 9.4716 | 10.1933 | 8.5841 | 10.7016 | 14.6195 | 9.4716 | 18.0557 | 28.7574 | 43.3769 | 0
8.4032 | 8.7716 | 8.608 | 7.0318 | 9.8142 | 7.8447 | 8.7716 | 15.8034 | 25.6176 | 33.4623 | 8.4132 | 8.7716 | 8.608 | 7.0318 | 9.8142 | 7.8447 | 8.7716 | 15.8034 | 25.6176 | 33.4623 | 0
3.3791 | 7.1138 | 9.7607 | 5.0188 | 10.2636 | 8.9556 | 7.1138 | 12.1326 | 22.3962 | 31.3518 | 3.3891 | 7.1138 | 9.7607 | 5.0188 | 10.2636 | 8.9556 | 7.1138 | 12.1326 | 22.3962 | 31.3518 | 0
-3.8161 | 7.1532 | 10.2671 | 10.2315 | 14.6101 | 14.1618 | 7.1532 | 17.3847 | 31.9948 | 46.1566 | -3.8061 | 7.1532 | 10.2671 | 10.2315 | 14.6101 | 14.1618 | 7.1532 | 17.3847 | 31.9948 | 46.1566 | 0
-5.4758 | 8.4731 | 7.5096 | 11.3109 | 13.7184 | 13.7961 | 8.4731 | 19.7841 | 33.5025 | 47.2986 | -5.4658 | 8.4731 | 7.5096 | 11.3109 | 13.7184 | 13.7961 | 8.4731 | 19.7841 | 33.5025 | 47.2986 | 0
-6.1672 | 9.4245 | 9.0818 | 6.6937 | 12.4586 | 11.4198 | 9.4245 | 16.1182 | 28.5768 | 39.9966 | -6.1572 | 9.4245 | 9.0818 | 6.6937 | 12.4586 | 11.4198 | 9.4245 | 16.1182 | 28.5768 | 39.9966 | 0
3.6593 | 10.1141 | 10.2201 | 6.9064 | 11.8095 | 14.0852 | 10.1141 | 17.0204 | 28.8299 | 42.9151 | 3.6693 | 10.1141 | 10.2201 | 6.9064 | 11.8095 | 14.0852 | 10.1141 | 17.0204 | 28.8299 | 42.9151 | 0
1.2229 | 10.4034 | 7.6818 | 8.6703 | 8.0623 | 11.1508 | 10.4034 | 19.0738 | 27.1361 | 38.287 | 1.2329 | 10.4034 | 7.6818 | 8.6703 | 8.0623 | 11.1508 | 10.4034 | 19.0738 | 27.1361 | 38.287 | 0
2.3918 | 8.6383 | 5.163 | 4.9561 | 16.5689 | 13.3492 | 8.6383 | 13.5945 | 30.1634 | 43.5126 | 2.4018 | 8.6383 | 5.163 | 4.9561 | 16.5689 | 13.3492 | 8.6383 | 13.5945 | 30.1634 | 43.5126 | 0
-6.5404 | 8.8304 | 7.1628 | 6.0645 | 5.6034 | 11.4143 | 8.8304 | 14.8949 | 20.4984 | 31.9127 | -6.5304 | 8.8304 | 7.1628 | 6.0645 | 5.6034 | 11.4143 | 8.8304 | 14.8949 | 20.4984 | 31.9127 | 0
-0.25533 | 9.6375 | 8.5912 | 3.7621 | 12.7644 | 14.1253 | 9.6375 | 13.3996 | 26.164 | 40.2893 | -0.24533 | 9.6375 | 8.5912 | 3.7621 | 12.7644 | 14.1253 | 9.6375 | 13.3996 | 26.164 | 40.2893 | 0
-1.6131 | 8.5918 | 10.8359 | 5.578 | 10.2413 | 11.004 | 8.5918 | 14.1699 | 24.4111 | 35.4151 | -1.6031 | 8.5918 | 10.8359 | 5.578 | 10.2413 | 11.004 | 8.5918 | 14.1699 | 24.4111 | 35.4151 | 0
-3.433 | 10.5476 | 6.9585 | 5.3566 | 7.5635 | 13.0624 | 10.5476 | 15.9042 | 23.4677 | 36.5301 | -3.423 | 10.5476 | 6.9585 | 5.3566 | 7.5635 | 13.0624 | 10.5476 | 15.9042 | 23.4677 | 36.5301 | 0
11.7751 | 8.1492 | 7.9427 | 10.5319 | 11.4458 | 10.1388 | 11.7751 | 22.307 | 33.7528 | 43.8916 | 11.7851 | 8.1492 | 7.9427 | 10.5319 | 11.4458 | 10.1388 | 11.7751 | 22.307 | 33.7528 | 43.8916 | 0
-4.7018 | 8.3375 | 7.1477 | 7.1216 | 5.3568 | 15.9962 | 8.3375 | 15.4591 | 20.8159 | 36.8121 | -4.6918 | 8.3375 | 7.1477 | 7.1216 | 5.3568 | 15.9962 | 8.3375 | 15.4591 | 20.8159 | 36.8121 | 0
3.1743 | 7.3528 | 6.8068 | 8.5164 | 10.7038 | 12.3992 | 7.3528 | 15.8692 | 26.573 | 38.9723 | 3.1843 | 7.3528 | 6.8068 | 8.5164 | 10.7038 | 12.3992 | 7.3528 | 15.8692 | 26.573 | 38.9723 | 0
1.3081 | 8.5824 | 7.5958 | 6.465 | 7.6639 | 9.378 | 8.5824 | 15.0474 | 22.7112 | 32.0892 | 1.3181 | 8.5824 | 7.5958 | 6.465 | 7.6639 | 9.378 | 8.5824 | 15.0474 | 22.7112 | 32.0892 | 0
12.5304 | 9.1391 | 8.1925 | 3.8547 | 7.1558 | 7.9439 | 12.5304 | 16.3851 | 23.541 | 31.4848 | 12.5404 | 9.1391 | 8.1925 | 3.8547 | 7.1558 | 7.9439 | 12.5304 | 16.3851 | 23.541 | 31.4848 | 0
-7.9778 | 7.1209 | 10.1078 | 4.7323 | 7.994 | 7.3287 | 7.1209 | 11.8532 | 19.8473 | 27.1759 | -7.9678 | 7.1209 | 10.1078 | 4.7323 | 7.994 | 7.3287 | 7.1209 | 11.8532 | 19.8473 | 27.1759 | 0
0.51152 | 8.0772 | 9.1733 | 7.0551 | 15.088 | 14.0753 | 8.0772 | 15.1323 | 30.2204 | 44.2956 | 0.52152 | 8.0772 | 9.1733 | 7.0551 | 15.088 | 14.0753 | 8.0772 | 15.1323 | 30.2204 | 44.2956 | 0
-9.3661 | 8.8349 | 8.17 | 6.2129 | 11.3538 | 16.1319 | 8.8349 | 15.0477 | 26.4015 | 42.5335 | -9.3561 | 8.8349 | 8.17 | 6.2129 | 11.3538 | 16.1319 | 8.8349 | 15.0477 | 26.4015 | 42.5335 | 0
9.8099 | 8.7903 | 9.6138 | 5.2016 | 10.4209 | 13.7624 | 9.8099 | 15.0115 | 25.4324 | 39.1948 | 9.8199 | 8.7903 | 9.6138 | 5.2016 | 10.4209 | 13.7624 | 9.8099 | 15.0115 | 25.4324 | 39.1948 | 0
7.2333 | 9.1224 | 9.6937 | 4.0177 | 7.502 | 9.9702 | 9.1224 | 13.1401 | 20.6421 | 30.6123 | 7.2433 | 9.1224 | 9.6937 | 4.0177 | 7.502 | 9.9702 | 9.1224 | 13.1401 | 20.6421 | 30.6123 | 0
5.2166 | 8.905 | 4.4191 | 5.2964 | 11.127 | 11.9348 | 8.905 | 14.2013 | 25.3283 | 37.2632 | 5.2266 | 8.905 | 4.4191 | 5.2964 | 11.127 | 11.9348 | 8.905 | 14.2013 | 25.3283 | 37.2632 | 0
-7.7185 | 8.8059 | 8.8251 | 7.5475 | 8.7194 | 14.6174 | 8.8059 | 16.3534 | 25.0728 | 39.6902 | -7.7085 | 8.8059 | 8.8251 | 7.5475 | 8.7194 | 14.6174 | 8.8059 | 16.3534 | 25.0728 | 39.6902 | 0
6.3113 | 8.5548 | 6.6309 | 5.79 | 13.0728 | 15.3654 | 8.5548 | 14.3448 | 27.4176 | 42.783 | 6.3213 | 8.5548 | 6.6309 | 5.79 | 13.0728 | 15.3654 | 8.5548 | 14.3448 | 27.4176 | 42.783 | 0
-11.1744 | 7.7117 | 6.3083 | 6.2331 | 4.0683 | 13.7084 | 7.7117 | 13.9448 | 18.0131 | 31.7215 | -11.1644 | 7.7117 | 6.3083 | 6.2331 | 4.0683 | 13.7084 | 7.7117 | 13.9448 | 18.0131 | 31.7215 | 0
-2.4724 | 6.2395 | 8.4816 | 4.1557 | 9.9322 | 8.581 | 6.2395 | 10.3952 | 20.3274 | 28.9084 | -2.4624 | 6.2395 | 8.4816 | 4.1557 | 9.9322 | 8.581 | 6.2395 | 10.3952 | 20.3274 | 28.9084 | 0
-2.1366 | 9.0029 | 8.3014 | 6.5705 | 4.0077 | 3.9073 | 9.0029 | 15.5734 | 19.581 | 23.4884 | -2.1266 | 9.0029 | 8.3014 | 6.5705 | 4.0077 | 3.9073 | 9.0029 | 15.5734 | 19.581 | 23.4884 | 0
-0.9036 | 6.6416 | 5.6237 | 6.6791 | 11.4933 | 13.546 | 6.6416 | 13.3208 | 24.8141 | 38.3601 | -0.8936 | 6.6416 | 5.6237 | 6.6791 | 11.4933 | 13.546 | 6.6416 | 13.3208 | 24.8141 | 38.3601 | 0
-8.5585 | 8.3431 | 11.4306 | 6.1691 | 7.8487 | 14.1004 | 8.3431 | 14.5122 | 22.3609 | 36.4613 | -8.5485 | 8.3431 | 11.4306 | 6.1691 | 7.8487 | 14.1004 | 8.3431 | 14.5122 | 22.3609 | 36.4613 | 0
-1.9963 | 8.444 | 10.0085 | 10.3922 | 9.8182 | 21.7597 | 8.444 | 18.8362 | 28.6544 | 50.4141 | -1.9863 | 8.444 | 10.0085 | 10.3922 | 9.8182 | 21.7597 | 8.444 | 18.8362 | 28.6544 | 50.4141 | 0
11.055 | 10.2109 | 9.2966 | 8.8563 | 8.8925 | 11.3178 | 11.055 | 19.9112 | 28.8037 | 40.1216 | 11.065 | 10.2109 | 9.2966 | 8.8563 | 8.8925 | 11.3178 | 11.055 | 19.9112 | 28.8037 | 40.1216 | 0
13.4719 | 8.371 | 3.6888 | 8.1558 | 8.7405 | 15.5444 | 13.4719 | 21.6277 | 30.3682 | 45.9126 | 13.4819 | 8.371 | 3.6888 | 8.1558 | 8.7405 | 15.5444 | 13.4719 | 21.6277 | 30.3682 | 45.9126 | 0
0.87747 | 8.7524 | 7.8763 | 4.253 | 5.6296 | 14.9997 | 8.7524 | 13.0054 | 18.635 | 33.6347 | 0.88747 | 8.7524 | 7.8763 | 4.253 | 5.6296 | 14.9997 | 8.7524 | 13.0054 | 18.635 | 33.6347 | 0
-0.25044 | 8.858 | 5.1027 | 5.223 | 14.5745 | 6.0302 | 8.858 | 14.081 | 28.6555 | 34.6857 | -0.24044 | 8.858 | 5.1027 | 5.223 | 14.5745 | 6.0302 | 8.858 | 14.081 | 28.6555 | 34.6857 | 0
-0.097822 | 9.4776 | 11.2301 | 4.8431 | 7.697 | 12.6951 | 9.4776 | 14.3207 | 22.0177 | 34.7128 | -0.087822 | 9.4776 | 11.2301 | 4.8431 | 7.697 | 12.6951 | 9.4776 | 14.3207 | 22.0177 | 34.7128 | 0
-6.7173 | 8.4052 | 9.1535 | 10.5228 | 6.0263 | 9.5546 | 8.4052 | 18.928 | 24.9543 | 34.509 | -6.7073 | 8.4052 | 9.1535 | 10.5228 | 6.0263 | 9.5546 | 8.4052 | 18.928 | 24.9543 | 34.509 | 0
-8.0613 | 9.6714 | 8.5048 | 4.0595 | 8.5467 | 11.9331 | 9.6714 | 13.7309 | 22.2776 | 34.2107 | -8.0513 | 9.6714 | 8.5048 | 4.0595 | 8.5467 | 11.9331 | 9.6714 | 13.7309 | 22.2776 | 34.2107 | 0
-1.4464 | 9.2843 | 6.0216 | 4.235 | 16.9418 | 16.7792 | 9.2843 | 13.5193 | 30.4611 | 47.2403 | -1.4364 | 9.2843 | 6.0216 | 4.235 | 16.9418 | 16.7792 | 9.2843 | 13.5193 | 30.4611 | 47.2403 | 0
7.595 | 8.7512 | 8.8134 | 9.0452 | 8.3439 | 18.1588 | 8.7512 | 17.7964 | 26.1403 | 44.2992 | 7.605 | 8.7512 | 8.8134 | 9.0452 | 8.3439 | 18.1588 | 8.7512 | 17.7964 | 26.1403 | 44.2992 | 0
5.3987 | 8.877 | 6.0172 | 6.5697 | 12.6267 | 9.5908 | 8.877 | 15.4466 | 28.0733 | 37.6641 | 5.4087 | 8.877 | 6.0172 | 6.5697 | 12.6267 | 9.5908 | 8.877 | 15.4466 | 28.0733 | 37.6641 | 0
7.3777 | 9.2825 | 8.978 | 9.1098 | 4.395 | 13.703 | 9.2825 | 18.3924 | 22.7873 | 36.4904 | 7.3877 | 9.2825 | 8.978 | 9.1098 | 4.395 | 13.703 | 9.2825 | 18.3924 | 22.7873 | 36.4904 | 0
9.4083 | 10.7995 | 5.9425 | 8.0905 | 10.8083 | 15.8601 | 10.7995 | 18.89 | 29.6983 | 45.5584 | 9.4183 | 10.7995 | 5.9425 | 8.0905 | 10.8083 | 15.8601 | 10.7995 | 18.89 | 29.6983 | 45.5584 | 0
15.6847 | 8.7261 | 7.0279 | 5.3397 | 9.7661 | 11.3612 | 15.6847 | 21.0243 | 30.7905 | 42.1517 | 15.6947 | 8.7261 | 7.0279 | 5.3397 | 9.7661 | 11.3612 | 15.6847 | 21.0243 | 30.7905 | 42.1517 | 0
0.52579 | 9.8119 | 7.6133 | 7.2934 | 8.7175 | 12.1038 | 9.8119 | 17.1053 | 25.8228 | 37.9266 | 0.53579 | 9.8119 | 7.6133 | 7.2934 | 8.7175 | 12.1038 | 9.8119 | 17.1053 | 25.8228 | 37.9266 | 0
1.9105 | 7.9628 | 5.951 | 6.8949 | 5.7537 | 11.8533 | 7.9628 | 14.8577 | 20.6114 | 32.4647 | 1.9205 | 7.9628 | 5.951 | 6.8949 | 5.7537 | 11.8533 | 7.9628 | 14.8577 | 20.6114 | 32.4647 | 0
1.904 | 8.0526 | 5.0114 | 5.7111 | 13.0288 | 14.0633 | 8.0526 | 13.7636 | 26.7924 | 40.8557 | 1.914 | 8.0526 | 5.0114 | 5.7111 | 13.0288 | 14.0633 | 8.0526 | 13.7636 | 26.7924 | 40.8557 | 0
-2.7485 | 10.6865 | 6.7149 | 8.0362 | 8.6517 | 14.829 | 10.6865 | 18.7227 | 27.3744 | 42.2034 | -2.7385 | 10.6865 | 6.7149 | 8.0362 | 8.6517 | 14.829 | 10.6865 | 18.7227 | 27.3744 | 42.2034 | 0
3.1391 | 8.8847 | 5.3103 | 9.3668 | 9.7965 | 8.5866 | 8.8847 | 18.2514 | 28.048 | 36.6346 | 3.1491 | 8.8847 | 5.3103 | 9.3668 | 9.7965 | 8.5866 | 8.8847 | 18.2514 | 28.048 | 36.6346 | 0
8.0447 | 9.9755 | 7.9762 | 5.856 | 5.9072 | 12.8909 | 9.9755 | 15.8315 | 21.7388 | 34.6297 | 8.0547 | 9.9755 | 7.9762 | 5.856 | 5.9072 | 12.8909 | 9.9755 | 15.8315 | 21.7388 | 34.6297 | 0
4.2907 | 9.6189 | 9.7284 | 7.188 | 10.0444 | 13.8676 | 9.6189 | 16.8069 | 26.8513 | 40.7189 | 4.3007 | 9.6189 | 9.7284 | 7.188 | 10.0444 | 13.8676 | 9.6189 | 16.8069 | 26.8513 | 40.7189 | 0
2.0753 | 9.2715 | 9.9613 | 9.7192 | 12.5197 | 18.8219 | 9.2715 | 18.9908 | 31.5105 | 50.3324 | 2.0853 | 9.2715 | 9.9613 | 9.7192 | 12.5197 | 18.8219 | 9.2715 | 18.9908 | 31.5105 | 50.3324 | 0
4.4846 | 7.6789 | 11.1124 | 5.2548 | 10.4202 | 18.5067 | 7.6789 | 12.9337 | 23.354 | 41.8606 | 4.4946 | 7.6789 | 11.1124 | 5.2548 | 10.4202 | 18.5067 | 7.6789 | 12.9337 | 23.354 | 41.8606 | 0
5.1168 | 10.6152 | 7.7015 | 7.7035 | 11.2638 | 8.5833 | 10.6152 | 18.3186 | 29.5825 | 38.1658 | 5.1268 | 10.6152 | 7.7015 | 7.7035 | 11.2638 | 8.5833 | 10.6152 | 18.3186 | 29.5825 | 38.1658 | 0
-10.392 | 10.5177 | 8.4917 | 5.086 | 12.4637 | 13.9011 | 10.5177 | 15.6037 | 28.0674 | 41.9685 | -10.382 | 10.5177 | 8.4917 | 5.086 | 12.4637 | 13.9011 | 10.5177 | 15.6037 | 28.0674 | 41.9685 | 0
7.698 | 8.0312 | 8.4333 | 5.1632 | 13.5244 | 11.2468 | 8.0312 | 13.1943 | 26.7187 | 37.9656 | 7.708 | 8.0312 | 8.4333 | 5.1632 | 13.5244 | 11.2468 | 8.0312 | 13.1943 | 26.7187 | 37.9656 | 0
4.1477 | 8.1176 | 9.5109 | 8.7738 | 10.2953 | 13.3401 | 8.1176 | 16.8915 | 27.1867 | 40.5269 | 4.1577 | 8.1176 | 9.5109 | 8.7738 | 10.2953 | 13.3401 | 8.1176 | 16.8915 | 27.1867 | 40.5269 | 0
-1.5857 | 6.3223 | 8.7812 | 7.8523 | 8.9547 | 5.6149 | 6.3223 | 14.1746 | 23.1293 | 28.7442 | -1.5757 | 6.3223 | 8.7812 | 7.8523 | 8.9547 | 5.6149 | 6.3223 | 14.1746 | 23.1293 | 28.7442 | 0
5.2238 | 8.4613 | 7.407 | 8.4805 | 10.7462 | 15.8531 | 8.4613 | 16.9418 | 27.688 | 43.5411 | 5.2338 | 8.4613 | 7.407 | 8.4805 | 10.7462 | 15.8531 | 8.4613 | 16.9418 | 27.688 | 43.5411 | 0
16.1631 | 9.7801 | 4.7598 | 7.5186 | 8.3203 | 12.7296 | 16.1631 | 23.6817 | 32.002 | 44.7316 | 16.1731 | 9.7801 | 4.7598 | 7.5186 | 8.3203 | 12.7296 | 16.1631 | 23.6817 | 32.002 | 44.7316 | 0
4.2108 | 9.1731 | 5.9293 | 8.5123 | 10.5916 | 9.6892 | 9.1731 | 17.6854 | 28.277 | 37.9663 | 4.2208 | 9.1731 | 5.9293 | 8.5123 | 10.5916 | 9.6892 | 9.1731 | 17.6854 | 28.277 | 37.9663 | 0
-2.1555 | 9.366 | 6.5918 | 4.2406 | 7.6789 | 9.5234 | 9.366 | 13.6066 | 21.2855 | 30.8089 | -2.1455 | 9.366 | 6.5918 | 4.2406 | 7.6789 | 9.5234 | 9.366 | 13.6066 | 21.2855 | 30.8089 | 0
5.9151 | 9.6737 | 6.9764 | 4.4154 | 5.7246 | 12.3062 | 9.6737 | 14.0892 | 19.8138 | 32.12 | 5.9251 | 9.6737 | 6.9764 | 4.4154 | 5.7246 | 12.3062 | 9.6737 | 14.0892 | 19.8138 | 32.12 | 0
-7.5047 | 8.1693 | 9.8834 | 5.6711 | 7.1066 | 13.0442 | 8.1693 | 13.8404 | 20.947 | 33.9911 | -7.4947 | 8.1693 | 9.8834 | 5.6711 | 7.1066 | 13.0442 | 8.1693 | 13.8404 | 20.947 | 33.9911 | 0
-11.5274 | 10.9395 | 8.2989 | 7.5537 | 10.19 | 17.8885 | 10.9395 | 18.4932 | 28.6832 | 46.5717 | -11.5174 | 10.9395 | 8.2989 | 7.5537 | 10.19 | 17.8885 | 10.9395 | 18.4932 | 28.6832 | 46.5717 | 0
-9.0805 | 8.6433 | 11.3447 | 5.7901 | 12.6151 | 13.0098 | 8.6433 | 14.4333 | 27.0484 | 40.0582 | -9.0705 | 8.6433 | 11.3447 | 5.7901 | 12.6151 | 13.0098 | 8.6433 | 14.4333 | 27.0484 | 40.0582 | 0
0.50299 | 8.8674 | 6.5683 | 7.3246 | 8.3717 | 11.684 | 8.8674 | 16.1921 | 24.5638 | 36.2478 | 0.51299 | 8.8674 | 6.5683 | 7.3246 | 8.3717 | 11.684 | 8.8674 | 16.1921 | 24.5638 | 36.2478 | 0
6.7161 | 8.4431 | 3.5917 | 3.3005 | 9.1383 | 12.416 | 8.4431 | 11.7436 | 20.8818 | 33.2978 | 6.7261 | 8.4431 | 3.5917 | 3.3005 | 9.1383 | 12.416 | 8.4431 | 11.7436 | 20.8818 | 33.2978 | 0
10.3572 | 9.1473 | 6.3845 | 8.5065 | 11.2262 | 9.9231 | 10.3572 | 18.8637 | 30.0899 | 40.013 | 10.3672 | 9.1473 | 6.3845 | 8.5065 | 11.2262 | 9.9231 | 10.3572 | 18.8637 | 30.0899 | 40.013 | 0
4.9332 | 9.627 | 5.5566 | 6.8224 | 11.1817 | 9.7149 | 9.627 | 16.4494 | 27.6312 | 37.3461 | 4.9432 | 9.627 | 5.5566 | 6.8224 | 11.1817 | 9.7149 | 9.627 | 16.4494 | 27.6312 | 37.3461 | 0
-0.21554 | 10.0481 | 5.3422 | 9.3104 | 14.0297 | 4.9311 | 10.0481 | 19.3585 | 33.3881 | 38.3192 | -0.20554 | 10.0481 | 5.3422 | 9.3104 | 14.0297 | 4.9311 | 10.0481 | 19.3585 | 33.3881 | 38.3192 | 0
6.2754 | 8.6971 | 6.5631 | 8.8711 | 6.16 | 8.3684 | 8.6971 | 17.5681 | 23.7281 | 32.0965 | 6.2854 | 8.6971 | 6.5631 | 8.8711 | 6.16 | 8.3684 | 8.6971 | 17.5681 | 23.7281 | 32.0965 | 0
11.3565 | 7.7267 | 7.3669 | 9.0475 | 8.2344 | 14.316 | 11.3565 | 20.404 | 28.6385 | 42.9545 | 11.3665 | 7.7267 | 7.3669 | 9.0475 | 8.2344 | 14.316 | 11.3565 | 20.404 | 28.6385 | 42.9545 | 0
8.3614 | 8.1526 | 9.6886 | 9.658 | 13.67 | 11.793 | 8.3614 | 18.0195 | 31.6895 | 43.4825 | 8.3714 | 8.1526 | 9.6886 | 9.658 | 13.67 | 11.793 | 8.3614 | 18.0195 | 31.6895 | 43.4825 | 0
-5.7498 | 7.8628 | 6.3971 | 3.9894 | 6.8796 | 9.6958 | 7.8628 | 11.8522 | 18.7318 | 28.4276 | -5.7398 | 7.8628 | 6.3971 | 3.9894 | 6.8796 | 9.6958 | 7.8628 | 11.8522 | 18.7318 | 28.4276 | 0
-3.5743 | 9.6821 | 8.0376 | 6.0846 | 10.3226 | 9.3012 | 9.6821 | 15.7667 | 26.0893 | 35.3905 | -3.5643 | 9.6821 | 8.0376 | 6.0846 | 10.3226 | 9.3012 | 9.6821 | 15.7667 | 26.0893 | 35.3905 | 0
-0.96672 | 9.3406 | 8.6618 | 6.9983 | 5.8781 | 10.4116 | 9.3406 | 16.3389 | 22.217 | 32.6286 | -0.95672 | 9.3406 | 8.6618 | 6.9983 | 5.8781 | 10.4116 | 9.3406 | 16.3389 | 22.217 | 32.6286 | 0
1.362 | 9.8899 | 7.0833 | 8.824 | 15.8516 | 12.8335 | 9.8899 | 18.7139 | 34.5655 | 47.399 | 1.372 | 9.8899 | 7.0833 | 8.824 | 15.8516 | 12.8335 | 9.8899 | 18.7139 | 34.5655 | 47.399 | 0
8.8136 | 10.9482 | 7.5192 | 9.4443 | 9.9374 | 12.9258 | 10.9482 | 20.3925 | 30.33 | 43.2558 | 8.8236 | 10.9482 | 7.5192 | 9.4443 | 9.9374 | 12.9258 | 10.9482 | 20.3925 | 30.33 | 43.2558 | 0
4.3898 | 7.8167 | 11.4637 | 6.5993 | 11.335 | 11.1421 | 7.8167 | 14.416 | 25.7511 | 36.8932 | 4.3998 | 7.8167 | 11.4637 | 6.5993 | 11.335 | 11.1421 | 7.8167 | 14.416 | 25.7511 | 36.8932 | 0
-4.2724 | 7.7222 | 3.1328 | 4.9384 | 11.5 | 17.165 | 7.7222 | 12.6606 | 24.1606 | 41.3255 | -4.2624 | 7.7222 | 3.1328 | 4.9384 | 11.5 | 17.165 | 7.7222 | 12.6606 | 24.1606 | 41.3255 | 0
-6.9692 | 10.2197 | 8.6851 | 5.1355 | 8.7029 | 12.67 | 10.2197 | 15.3552 | 24.0581 | 36.7281 | -6.9592 | 10.2197 | 8.6851 | 5.1355 | 8.7029 | 12.67 | 10.2197 | 15.3552 | 24.0581 | 36.7281 | 0
-7.5933 | 9.247 | 6.7051 | 5.9494 | 8.7609 | 12.7001 | 9.247 | 15.1964 | 23.9573 | 36.6575 | -7.5833 | 9.247 | 6.7051 | 5.9494 | 8.7609 | 12.7001 | 9.247 | 15.1964 | 23.9573 | 36.6575 | 0
-6.1901 | 9.6451 | 8.3822 | 11.2484 | 13.8205 | 9.3526 | 9.6451 | 20.8936 | 34.7141 | 44.0667 | -6.1801 | 9.6451 | 8.3822 | 11.2484 | 13.8205 | 9.3526 | 9.6451 | 20.8936 | 34.7141 | 44.0667 | 0
1.6267 | 10.7896 | 6.0764 | 5.329 | 9.587 | 11.8271 | 10.7896 | 16.1187 | 25.7057 | 37.5328 | 1.6367 | 10.7896 | 6.0764 | 5.329 | 9.587 | 11.8271 | 10.7896 | 16.1187 | 25.7057 | 37.5328 | 0
2.8768 | 8.355 | 9.6028 | 6.251 | 9.3052 | 10.6641 | 8.355 | 14.6061 | 23.9113 | 34.5754 | 2.8868 | 8.355 | 9.6028 | 6.251 | 9.3052 | 10.6641 | 8.355 | 14.6061 | 23.9113 | 34.5754 | 0
9.2689 | 7.2582 | 5.9531 | 4.5302 | 9.802 | 12.5029 | 9.2689 | 13.7991 | 23.6011 | 36.104 | 9.2789 | 7.2582 | 5.9531 | 4.5302 | 9.802 | 12.5029 | 9.2689 | 13.7991 | 23.6011 | 36.104 | 0
-1.956 | 8.1484 | 6.1835 | 6.7803 | 8.3826 | 9.9714 | 8.1484 | 14.9287 | 23.3114 | 33.2827 | -1.946 | 8.1484 | 6.1835 | 6.7803 | 8.3826 | 9.9714 | 8.1484 | 14.9287 | 23.3114 | 33.2827 | 0
-4.3123 | 9.1095 | 9.7339 | 7.4798 | 9.4831 | 12.2923 | 9.1095 | 16.5893 | 26.0724 | 38.3647 | -4.3023 | 9.1095 | 9.7339 | 7.4798 | 9.4831 | 12.2923 | 9.1095 | 16.5893 | 26.0724 | 38.3647 | 0
-0.79064 | 8.1353 | 8.3162 | 8.3776 | 3.0456 | 13.3393 | 8.1353 | 16.5129 | 19.5585 | 32.8978 | -0.78064 | 8.1353 | 8.3162 | 8.3776 | 3.0456 | 13.3393 | 8.1353 | 16.5129 | 19.5585 | 32.8978 | 0
7.6212 | 7.178 | 7.1106 | 6.1327 | 12.3557 | 10.3274 | 7.6212 | 13.754 | 26.1097 | 36.437 | 7.6312 | 7.178 | 7.1106 | 6.1327 | 12.3557 | 10.3274 | 7.6212 | 13.754 | 26.1097 | 36.437 | 0
4.4225 | 8.1746 | 5.1313 | 7.4912 | 5.1996 | 8.0468 | 8.1746 | 15.6658 | 20.8654 | 28.9122 | 4.4325 | 8.1746 | 5.1313 | 7.4912 | 5.1996 | 8.0468 | 8.1746 | 15.6658 | 20.8654 | 28.9122 | 0
9.065 | 7.8803 | 10.5611 | 10.0128 | 12.2008 | 11.4688 | 9.065 | 19.0777 | 31.2786 | 42.7473 | 9.075 | 7.8803 | 10.5611 | 10.0128 | 12.2008 | 11.4688 | 9.065 | 19.0777 | 31.2786 | 42.7473 | 0
3.3247 | 9.3438 | 7.1858 | 11.508 | 10.85 | 10.8775 | 9.3438 | 20.8518 | 31.7017 | 42.5793 | 3.3347 | 9.3438 | 7.1858 | 11.508 | 10.85 | 10.8775 | 9.3438 | 20.8518 | 31.7017 | 42.5793 | 0
10.0674 | 7.6425 | 6.9581 | 7.8245 | 5.9172 | 8.6627 | 10.0674 | 17.8918 | 23.8091 | 32.4717 | 10.0774 | 7.6425 | 6.9581 | 7.8245 | 5.9172 | 8.6627 | 10.0674 | 17.8918 | 23.8091 | 32.4717 | 0
5.7512 | 8.6902 | 7.4775 | 5.247 | 8.595 | 16.1048 | 8.6902 | 13.9371 | 22.5322 | 38.637 | 5.7612 | 8.6902 | 7.4775 | 5.247 | 8.595 | 16.1048 | 8.6902 | 13.9371 | 22.5322 | 38.637 | 0
4.6021 | 10.0812 | 8.3825 | 7.4689 | 9.9972 | 7.9916 | 10.0812 | 17.5502 | 27.5473 | 35.5389 | 4.6121 | 10.0812 | 8.3825 | 7.4689 | 9.9972 | 7.9916 | 10.0812 | 17.5502 | 27.5473 | 35.5389 | 0
5.2733 | 8.9256 | 6.3214 | 5.6629 | 6.6912 | 10.3219 | 8.9256 | 14.5885 | 21.2798 | 31.6016 | 5.2833 | 8.9256 | 6.3214 | 5.6629 | 6.6912 | 10.3219 | 8.9256 | 14.5885 | 21.2798 | 31.6016 | 0
6.6603 | 8.642 | 7.2733 | 7.3453 | 9.5029 | 12.9701 | 8.642 | 15.9873 | 25.4902 | 38.4602 | 6.6703 | 8.642 | 7.2733 | 7.3453 | 9.5029 | 12.9701 | 8.642 | 15.9873 | 25.4902 | 38.4602 | 0
13.2363 | 9.3783 | 9.0306 | 5.7356 | 9.7788 | 11.2186 | 13.2363 | 18.9719 | 28.7506 | 39.9692 | 13.2463 | 9.3783 | 9.0306 | 5.7356 | 9.7788 | 11.2186 | 13.2363 | 18.9719 | 28.7506 | 39.9692 | 0
1.8769 | 6.9279 | 8.7474 | 7.9297 | 9.7031 | 12.2215 | 6.9279 | 14.8575 | 24.5607 | 36.7821 | 1.8869 | 6.9279 | 8.7474 | 7.9297 | 9.7031 | 12.2215 | 6.9279 | 14.8575 | 24.5607 | 36.7821 | 0
10.8946 | 8.9287 | 12.3537 | 6.9654 | 5.2563 | 7.5858 | 10.8946 | 17.86 | 23.2483 | 30.834 | 10.9046 | 8.9287 | 12.3537 | 6.9654 | 5.2563 | 7.5858 | 10.8946 | 17.86 | 23.2483 | 30.834 | 0
0.73205 | 7.3625 | 6.0277 | 7.5395 | 10.1139 | 11.3387 | 7.3625 | 14.9019 | 25.0158 | 36.3545 | 0.74205 | 7.3625 | 6.0277 | 7.5395 | 10.1139 | 11.3387 | 7.3625 | 14.9019 | 25.0158 | 36.3545 | 0
-9.2009 | 7.7065 | 6.3645 | 6.7515 | 13.974 | 11.3796 | 7.7065 | 14.458 | 28.432 | 39.8116 | -9.1909 | 7.7065 | 6.3645 | 6.7515 | 13.974 | 11.3796 | 7.7065 | 14.458 | 28.432 | 39.8116 | 0
0.59027 | 9.8757 | 9.4844 | 6.695 | 17.6378 | 13.3788 | 9.8757 | 16.5707 | 34.2085 | 47.5873 | 0.60027 | 9.8757 | 9.4844 | 6.695 | 17.6378 | 13.3788 | 9.8757 | 16.5707 | 34.2085 | 47.5873 | 0
1.9673 | 9.936 | 8.2535 | 8.9469 | 9.3465 | 16.1723 | 9.936 | 18.8829 | 28.2294 | 44.4018 | 1.9773 | 9.936 | 8.2535 | 8.9469 | 9.3465 | 16.1723 | 9.936 | 18.8829 | 28.2294 | 44.4018 | 0
10.414 | 9.8285 | 12.2827 | 4.8372 | 9.7877 | 10.8131 | 10.414 | 15.2512 | 25.0389 | 35.852 | 10.424 | 9.8285 | 12.2827 | 4.8372 | 9.7877 | 10.8131 | 10.414 | 15.2512 | 25.0389 | 35.852 | 0
3.5461 | 8.997 | 4.2761 | 9.8867 | 8.4842 | 11.5951 | 8.997 | 18.8837 | 27.3679 | 38.963 | 3.5561 | 8.997 | 4.2761 | 9.8867 | 8.4842 | 11.5951 | 8.997 | 18.8837 | 27.3679 | 38.963 | 0
0.16537 | 9.416 | 5.6036 | 7.0051 | 9.612 | 9.897 | 9.416 | 16.4211 | 26.0331 | 35.9301 | 0.17537 | 9.416 | 5.6036 | 7.0051 | 9.612 | 9.897 | 9.416 | 16.4211 | 26.0331 | 35.9301 | 0
7.1787 | 8.9432 | 9.8288 | 7.9859 | 11.8891 | 11.2284 | 8.9432 | 16.9291 | 28.8182 | 40.0466 | 7.1887 | 8.9432 | 9.8288 | 7.9859 | 11.8891 | 11.2284 | 8.9432 | 16.9291 | 28.8182 | 40.0466 | 0
8.5512 | 9.5371 | 8.0332 | 8.0172 | 9.6476 | 15.3976 | 9.5371 | 17.5544 | 27.2019 | 42.5995 | 8.5612 | 9.5371 | 8.0332 | 8.0172 | 9.6476 | 15.3976 | 9.5371 | 17.5544 | 27.2019 | 42.5995 | 0
13.0615 | 7.7618 | 10.2761 | 5.8984 | 10.9355 | 14.8954 | 13.0615 | 18.9599 | 29.8954 | 44.7907 | 13.0715 | 7.7618 | 10.2761 | 5.8984 | 10.9355 | 14.8954 | 13.0615 | 18.9599 | 29.8954 | 44.7907 | 0
5.5428 | 7.7385 | 6.466 | 9.9158 | 13.8364 | 9.0988 | 7.7385 | 17.6543 | 31.4907 | 40.5895 | 5.5528 | 7.7385 | 6.466 | 9.9158 | 13.8364 | 9.0988 | 7.7385 | 17.6543 | 31.4907 | 40.5895 | 0
-8.0411 | 9.1009 | 7.5491 | 7.6227 | 7.0478 | 13.7354 | 9.1009 | 16.7236 | 23.7714 | 37.5068 | -8.0311 | 9.1009 | 7.5491 | 7.6227 | 7.0478 | 13.7354 | 9.1009 | 16.7236 | 23.7714 | 37.5068 | 0
7.8507 | 9.8062 | 8.7877 | 11.142 | 12.2848 | 9.9443 | 9.8062 | 20.9482 | 33.233 | 43.1774 | 7.8607 | 9.8062 | 8.7877 | 11.142 | 12.2848 | 9.9443 | 9.8062 | 20.9482 | 33.233 | 43.1774 | 0
-8.1608 | 8.7374 | 7.9465 | 7.7366 | 10.7226 | 13.2728 | 8.7374 | 16.4739 | 27.1965 | 40.4694 | -8.1508 | 8.7374 | 7.9465 | 7.7366 | 10.7226 | 13.2728 | 8.7374 | 16.4739 | 27.1965 | 40.4694 | 0
0.46553 | 9.3269 | 5.484 | 4.7324 | 4.9572 | 8.9788 | 9.3269 | 14.0593 | 19.0165 | 27.9953 | 0.47553 | 9.3269 | 5.484 | 4.7324 | 4.9572 | 8.9788 | 9.3269 | 14.0593 | 19.0165 | 27.9953 | 0
-2.3594 | 10.5658 | 6.3207 | 8.3041 | 11.0581 | 15.2723 | 10.5658 | 18.8699 | 29.928 | 45.2002 | -2.3494 | 10.5658 | 6.3207 | 8.3041 | 11.0581 | 15.2723 | 10.5658 | 18.8699 | 29.928 | 45.2002 | 0
2.6416 | 8.7894 | 8.4809 | 7.6519 | 6.7494 | 14.9596 | 8.7894 | 16.4414 | 23.1908 | 38.1503 | 2.6516 | 8.7894 | 8.4809 | 7.6519 | 6.7494 | 14.9596 | 8.7894 | 16.4414 | 23.1908 | 38.1503 | 0
-4.3345 | 7.6672 | 6.3609 | 10.7476 | 17.4065 | 10.2598 | 7.6672 | 18.4149 | 35.8214 | 46.0811 | -4.3245 | 7.6672 | 6.3609 | 10.7476 | 17.4065 | 10.2598 | 7.6672 | 18.4149 | 35.8214 | 46.0811 | 0
-5.3008 | 9.2122 | 5.4445 | 8.3085 | 5.8996 | 12.6783 | 9.2122 | 17.5207 | 23.4202 | 36.0985 | -5.2908 | 9.2122 | 5.4445 | 8.3085 | 5.8996 | 12.6783 | 9.2122 | 17.5207 | 23.4202 | 36.0985 | 0
5.3151 | 9.7213 | 12.6742 | 5.9252 | 11.9073 | 13.4642 | 9.7213 | 15.6465 | 27.5538 | 41.018 | 5.3251 | 9.7213 | 12.6742 | 5.9252 | 11.9073 | 13.4642 | 9.7213 | 15.6465 | 27.5538 | 41.018 | 0
13.2975 | 7.6424 | 9.0198 | 6.4825 | 12.6976 | 12.199 | 13.2975 | 19.78 | 32.4777 | 44.6767 | 13.3075 | 7.6424 | 9.0198 | 6.4825 | 12.6976 | 12.199 | 13.2975 | 19.78 | 32.4777 | 44.6767 | 0
-2.6334 | 7.7786 | 12.4204 | 8.5523 | 16.3876 | 6.3138 | 7.7786 | 16.3309 | 32.7185 | 39.0323 | -2.6234 | 7.7786 | 12.4204 | 8.5523 | 16.3876 | 6.3138 | 7.7786 | 16.3309 | 32.7185 | 39.0323 | 0
-0.1964 | 7.8958 | 7.0906 | 1.3782 | 11.4938 | 13.9441 | 7.8958 | 9.2739 | 20.7677 | 34.7118 | -0.1864 | 7.8958 | 7.0906 | 1.3782 | 11.4938 | 13.9441 | 7.8958 | 9.2739 | 20.7677 | 34.7118 | 0
6.0369 | 9.6 | 8.0636 | 7.0819 | 7.0541 | 13.2057 | 9.6 | 16.6819 | 23.7359 | 36.9417 | 6.0469 | 9.6 | 8.0636 | 7.0819 | 7.0541 | 13.2057 | 9.6 | 16.6819 | 23.7359 | 36.9417 | 0
-0.28672 | 8.9893 | 9.0092 | 10.3543 | 9.7914 | 11.948 | 8.9893 | 19.3436 | 29.135 | 41.0829 | -0.27672 | 8.9893 | 9.0092 | 10.3543 | 9.7914 | 11.948 | 8.9893 | 19.3436 | 29.135 | 41.0829 | 0
3.8278 | 9.5837 | 9.3005 | 4.9383 | 10.7786 | 9.309 | 9.5837 | 14.522 | 25.3005 | 34.6095 | 3.8378 | 9.5837 | 9.3005 | 4.9383 | 10.7786 | 9.309 | 9.5837 | 14.522 | 25.3005 | 34.6095 | 0
10.0689 | 9.5723 | 10.0719 | 10.7993 | 8.3815 | 15.489 | 10.0689 | 20.8683 | 29.2497 | 44.7387 | 10.0789 | 9.5723 | 10.0719 | 10.7993 | 8.3815 | 15.489 | 10.0689 | 20.8683 | 29.2497 | 44.7387 | 0
1.1101 | 8.436 | 5.4636 | 11.0905 | 7.4505 | 12.6178 | 8.436 | 19.5265 | 26.977 | 39.5948 | 1.1201 | 8.436 | 5.4636 | 11.0905 | 7.4505 | 12.6178 | 8.436 | 19.5265 | 26.977 | 39.5948 | 0
3.6397 | 11.6072 | 7.8928 | 9.3886 | 14.1413 | 12.8218 | 11.6072 | 20.9958 | 35.1371 | 47.959 | 3.6497 | 11.6072 | 7.8928 | 9.3886 | 14.1413 | 12.8218 | 11.6072 | 20.9958 | 35.1371 | 47.959 | 0
-1.2911 | 8.4606 | 6.9196 | 5.9823 | 13.0522 | 12.4414 | 8.4606 | 14.4429 | 27.4951 | 39.9365 | -1.2811 | 8.4606 | 6.9196 | 5.9823 | 13.0522 | 12.4414 | 8.4606 | 14.4429 | 27.4951 | 39.9365 | 0
-5.4752 | 10.2591 | 5.6207 | 6.1434 | 10.9982 | 12.2668 | 10.2591 | 16.4026 | 27.4008 | 39.6676 | -5.4652 | 10.2591 | 5.6207 | 6.1434 | 10.9982 | 12.2668 | 10.2591 | 16.4026 | 27.4008 | 39.6676 | 0
-0.04253 | 8.3061 | 10.5949 | 5.9686 | 14.9432 | 7.1878 | 8.3061 | 14.2748 | 29.218 | 36.4058 | -0.03253 | 8.3061 | 10.5949 | 5.9686 | 14.9432 | 7.1878 | 8.3061 | 14.2748 | 29.218 | 36.4058 | 0
-1.2491 | 10.9563 | 9.4395 | 5.0789 | 11.1808 | 11.7459 | 10.9563 | 16.0352 | 27.216 | 38.9619 | -1.2391 | 10.9563 | 9.4395 | 5.0789 | 11.1808 | 11.7459 | 10.9563 | 16.0352 | 27.216 | 38.9619 | 0
2.2725 | 8.2602 | 6.3412 | 4.6086 | 5.0025 | 9.7282 | 8.2602 | 12.8687 | 17.8712 | 27.5994 | 2.2825 | 8.2602 | 6.3412 | 4.6086 | 5.0025 | 9.7282 | 8.2602 | 12.8687 | 17.8712 | 27.5994 | 0
11.5922 | 9.1873 | 7.0044 | 1.8008 | 10.806 | 9.5709 | 11.5922 | 13.393 | 24.199 | 33.7699 | 11.6022 | 9.1873 | 7.0044 | 1.8008 | 10.806 | 9.5709 | 11.5922 | 13.393 | 24.199 | 33.7699 | 0
2.8237 | 7.5054 | 8.7548 | 6.675 | 10.5132 | 12.5573 | 7.5054 | 14.1804 | 24.6935 | 37.2509 | 2.8337 | 7.5054 | 8.7548 | 6.675 | 10.5132 | 12.5573 | 7.5054 | 14.1804 | 24.6935 | 37.2509 | 0
-4.1902 | 9.1426 | 6.7577 | 8.2945 | 13.4128 | 5.2065 | 9.1426 | 17.4372 | 30.8499 | 36.0564 | -4.1802 | 9.1426 | 6.7577 | 8.2945 | 13.4128 | 5.2065 | 9.1426 | 17.4372 | 30.8499 | 36.0564 | 0
3.8958 | 9.3356 | 8.5885 | 6.9597 | 11.3132 | 14.9224 | 9.3356 | 16.2953 | 27.6085 | 42.5308 | 3.9058 | 9.3356 | 8.5885 | 6.9597 | 11.3132 | 14.9224 | 9.3356 | 16.2953 | 27.6085 | 42.5308 | 0
-0.8079 | 7.7757 | 7.9884 | 6.0291 | 9.3689 | 15.3282 | 7.7757 | 13.8048 | 23.1737 | 38.502 | -0.7979 | 7.7757 | 7.9884 | 6.0291 | 9.3689 | 15.3282 | 7.7757 | 13.8048 | 23.1737 | 38.502 | 0
2.4872 | 10.3488 | 8.5304 | 2.7446 | 8.9239 | 8.3595 | 10.3488 | 13.0934 | 22.0174 | 30.3769 | 2.4972 | 10.3488 | 8.5304 | 2.7446 | 8.9239 | 8.3595 | 10.3488 | 13.0934 | 22.0174 | 30.3769 | 0
-0.92071 | 8.3522 | 12.4536 | 6.286 | 5.5784 | 10.6638 | 8.3522 | 14.6382 | 20.8058 | 31.4696 | -0.91071 | 8.3522 | 12.4536 | 6.286 | 5.5784 | 10.6638 | 8.3522 | 14.6382 | 20.8058 | 31.4696 | 0
-7.9324 | 9.9271 | 9.9627 | 7.7725 | 13.1576 | 15.6979 | 9.9271 | 17.6996 | 30.8572 | 46.5551 | -7.9224 | 9.9271 | 9.9627 | 7.7725 | 13.1576 | 15.6979 | 9.9271 | 17.6996 | 30.8572 | 46.5551 | 0
-2.8236 | 8.7775 | 3.6189 | 5.4053 | 10.1638 | 11.2926 | 8.7775 | 14.1828 | 24.3466 | 35.6392 | -2.8136 | 8.7775 | 3.6189 | 5.4053 | 10.1638 | 11.2926 | 8.7775 | 14.1828 | 24.3466 | 35.6392 | 0
2.9422 | 9.6196 | 7.3852 | 7.3863 | 9.8763 | 6.8784 | 9.6196 | 17.006 | 26.8823 | 33.7607 | 2.9522 | 9.6196 | 7.3852 | 7.3863 | 9.8763 | 6.8784 | 9.6196 | 17.006 | 26.8823 | 33.7607 | 0
-5.4423 | 10.3699 | 6.8223 | 7.849 | 6.2409 | 13.6367 | 10.3699 | 18.2189 | 24.4598 | 38.0966 | -5.4323 | 10.3699 | 6.8223 | 7.849 | 6.2409 | 13.6367 | 10.3699 | 18.2189 | 24.4598 | 38.0966 | 0
-0.050626 | 8.9795 | 3.8577 | 6.9749 | 9.0501 | 16.7472 | 8.9795 | 15.9544 | 25.0045 | 41.7517 | -0.040626 | 8.9795 | 3.8577 | 6.9749 | 9.0501 | 16.7472 | 8.9795 | 15.9544 | 25.0045 | 41.7517 | 0
6.265 | 7.8058 | 6.4664 | 6.2391 | 9.1866 | 13.5479 | 7.8058 | 14.0449 | 23.2315 | 36.7793 | 6.275 | 7.8058 | 6.4664 | 6.2391 | 9.1866 | 13.5479 | 7.8058 | 14.0449 | 23.2315 | 36.7793 | 0
13.3509 | 10.8531 | 7.0478 | 7.8117 | 10.6972 | 11.4884 | 13.3509 | 21.1626 | 31.8598 | 43.3482 | 13.3609 | 10.8531 | 7.0478 | 7.8117 | 10.6972 | 11.4884 | 13.3509 | 21.1626 | 31.8598 | 43.3482 | 0
-1.7689 | 8.3374 | 9.3867 | 9.1551 | 12.8238 | 13.1577 | 8.3374 | 17.4925 | 30.3163 | 43.474 | -1.7589 | 8.3374 | 9.3867 | 9.1551 | 12.8238 | 13.1577 | 8.3374 | 17.4925 | 30.3163 | 43.474 | 0
-6.3161 | 8.5461 | 6.6608 | 7.8961 | 11.3373 | 9.1829 | 8.5461 | 16.4422 | 27.7795 | 36.9624 | -6.3061 | 8.5461 | 6.6608 | 7.8961 | 11.3373 | 9.1829 | 8.5461 | 16.4422 | 27.7795 | 36.9624 | 0
7.0838 | 8.6428 | 10.6781 | 5.7348 | 8.1874 | 18.3442 | 8.6428 | 14.3776 | 22.5649 | 40.9092 | 7.0938 | 8.6428 | 10.6781 | 5.7348 | 8.1874 | 18.3442 | 8.6428 | 14.3776 | 22.5649 | 40.9092 | 0
-2.1051 | 8.8369 | 8.7984 | 7.2832 | 12.4362 | 11.8342 | 8.8369 | 16.1201 | 28.5563 | 40.3905 | -2.0951 | 8.8369 | 8.7984 | 7.2832 | 12.4362 | 11.8342 | 8.8369 | 16.1201 | 28.5563 | 40.3905 | 0
-5.1945 | 9.0604 | 9.5742 | 8.787 | 12.8353 | 8.6995 | 9.0604 | 17.8474 | 30.6827 | 39.3822 | -5.1845 | 9.0604 | 9.5742 | 8.787 | 12.8353 | 8.6995 | 9.0604 | 17.8474 | 30.6827 | 39.3822 | 0
16.0149 | 9.097 | 6.7569 | 6.1248 | 5.1825 | 11.8981 | 16.0149 | 22.1397 | 27.3222 | 39.2203 | 16.0249 | 9.097 | 6.7569 | 6.1248 | 5.1825 | 11.8981 | 16.0149 | 22.1397 | 27.3222 | 39.2203 | 0
-4.9334 | 8.1082 | 7.7583 | 6.2925 | 7.4528 | 14.4144 | 8.1082 | 14.4008 | 21.8536 | 36.2681 | -4.9234 | 8.1082 | 7.7583 | 6.2925 | 7.4528 | 14.4144 | 8.1082 | 14.4008 | 21.8536 | 36.2681 | 0
8.4254 | 9.0525 | 7.0904 | 6.0041 | 10.1351 | 13.9011 | 9.0525 | 15.0566 | 25.1917 | 39.0928 | 8.4354 | 9.0525 | 7.0904 | 6.0041 | 10.1351 | 13.9011 | 9.0525 | 15.0566 | 25.1917 | 39.0928 | 0
3.5939 | 9.0742 | 5.5671 | 8.1915 | 9.2716 | 11.3498 | 9.0742 | 17.2657 | 26.5373 | 37.8871 | 3.6039 | 9.0742 | 5.5671 | 8.1915 | 9.2716 | 11.3498 | 9.0742 | 17.2657 | 26.5373 | 37.8871 | 0
11.3493 | 8.9082 | 9.5075 | 8.0428 | 9.5775 | 12.3753 | 11.3493 | 19.3921 | 28.9696 | 41.3448 | 11.3593 | 8.9082 | 9.5075 | 8.0428 | 9.5775 | 12.3753 | 11.3493 | 19.3921 | 28.9696 | 41.3448 | 0
1.4379 | 9.3707 | 11.2761 | 5.5682 | 8.2725 | 7.2563 | 9.3707 | 14.9389 | 23.2114 | 30.4677 | 1.4479 | 9.3707 | 11.2761 | 5.5682 | 8.2725 | 7.2563 | 9.3707 | 14.9389 | 23.2114 | 30.4677 | 0
-1.8407 | 8.833 | 9.9505 | 8.2246 | 10.783 | 12.1732 | 8.833 | 17.0576 | 27.8406 | 40.0138 | -1.8307 | 8.833 | 9.9505 | 8.2246 | 10.783 | 12.1732 | 8.833 | 17.0576 | 27.8406 | 40.0138 | 0
0.90578 | 10.3394 | 8.6368 | 5.8447 | 13.0641 | 10.9719 | 10.3394 | 16.184 | 29.2482 | 40.2201 | 0.91578 | 10.3394 | 8.6368 | 5.8447 | 13.0641 | 10.9719 | 10.3394 | 16.184 | 29.2482 | 40.2201 | 0
1.303 | 9.3591 | 9.6665 | 5.7197 | 9.9342 | 15.6654 | 9.3591 | 15.0788 | 25.013 | 40.6784 | 1.313 | 9.3591 | 9.6665 | 5.7197 | 9.9342 | 15.6654 | 9.3591 | 15.0788 | 25.013 | 40.6784 | 0
-0.5806 | 9.5501 | 6.2203 | 5.1879 | 9.4842 | 10.2019 | 9.5501 | 14.738 | 24.2222 | 34.4241 | -0.5706 | 9.5501 | 6.2203 | 5.1879 | 9.4842 | 10.2019 | 9.5501 | 14.738 | 24.2222 | 34.4241 | 0
-3.817 | 9.9163 | 5.7828 | 7.0321 | 9.2324 | 17.5731 | 9.9163 | 16.9483 | 26.1807 | 43.7538 | -3.807 | 9.9163 | 5.7828 | 7.0321 | 9.2324 | 17.5731 | 9.9163 | 16.9483 | 26.1807 | 43.7538 | 0
0.81951 | 9.4161 | 9.7789 | 10.9003 | 9.2805 | 14.5097 | 9.4161 | 20.3164 | 29.5969 | 44.1067 | 0.82951 | 9.4161 | 9.7789 | 10.9003 | 9.2805 | 14.5097 | 9.4161 | 20.3164 | 29.5969 | 44.1067 | 0
6.3318 | 9.85 | 5.1301 | 4.6112 | 11.4812 | 14.7745 | 9.85 | 14.4612 | 25.9424 | 40.717 | 6.3418 | 9.85 | 5.1301 | 4.6112 | 11.4812 | 14.7745 | 9.85 | 14.4612 | 25.9424 | 40.717 | 0
5.173 | 10.577 | 7.7262 | 6.2683 | 8.0228 | 10.8628 | 10.577 | 16.8453 | 24.8681 | 35.7309 | 5.183 | 10.577 | 7.7262 | 6.2683 | 8.0228 | 10.8628 | 10.577 | 16.8453 | 24.8681 | 35.7309 | 0
6.7906 | 8.6799 | 8.0818 | 11.8641 | 9.9366 | 12.0355 | 8.6799 | 20.544 | 30.4806 | 42.5161 | 6.8006 | 8.6799 | 8.0818 | 11.8641 | 9.9366 | 12.0355 | 8.6799 | 20.544 | 30.4806 | 42.5161 | 0
5.0597 | 6.6319 | 9.3031 | 8.9952 | 13.9214 | 15.2163 | 6.6319 | 15.627 | 29.5484 | 44.7647 | 5.0697 | 6.6319 | 9.3031 | 8.9952 | 13.9214 | 15.2163 | 6.6319 | 15.627 | 29.5484 | 44.7647 | 0
-3.2395 | 8.2693 | 10.1973 | 7.6901 | 10.096 | 7.9046 | 8.2693 | 15.9594 | 26.0554 | 33.96 | -3.2295 | 8.2693 | 10.1973 | 7.6901 | 10.096 | 7.9046 | 8.2693 | 15.9594 | 26.0554 | 33.96 | 0
2.5578 | 8.444 | 10.5501 | 2.7999 | 16.348 | 9.6306 | 8.444 | 11.2439 | 27.5919 | 37.2225 | 2.5678 | 8.444 | 10.5501 | 2.7999 | 16.348 | 9.6306 | 8.444 | 11.2439 | 27.5919 | 37.2225 | 0
11.775 | 10.898 | 5.1964 | 5.299 | 9.0875 | 12.445 | 11.775 | 17.074 | 26.1615 | 38.6065 | 11.785 | 10.898 | 5.1964 | 5.299 | 9.0875 | 12.445 | 11.775 | 17.074 | 26.1615 | 38.6065 | 0
-5.4108 | 8.0233 | 9.1406 | 8.6865 | 5.6463 | 11.3119 | 8.0233 | 16.7098 | 22.356 | 33.6679 | -5.4008 | 8.0233 | 9.1406 | 8.6865 | 5.6463 | 11.3119 | 8.0233 | 16.7098 | 22.356 | 33.6679 | 0
5.642 | 8.7566 | 9.4817 | 4.9513 | 13.715 | 15.559 | 8.7566 | 13.708 | 27.423 | 42.982 | 5.652 | 8.7566 | 9.4817 | 4.9513 | 13.715 | 15.559 | 8.7566 | 13.708 | 27.423 | 42.982 | 0
6.8978 | 8.9343 | 8.0237 | 8.6482 | 8.6199 | 6.9431 | 8.9343 | 17.5825 | 26.2025 | 33.1456 | 6.9078 | 8.9343 | 8.0237 | 8.6482 | 8.6199 | 6.9431 | 8.9343 | 17.5825 | 26.2025 | 33.1456 | 0
-2.7778 | 8.743 | 5.3197 | 7.6027 | 9.6585 | 18.6535 | 8.743 | 16.3457 | 26.0041 | 44.6576 | -2.7678 | 8.743 | 5.3197 | 7.6027 | 9.6585 | 18.6535 | 8.743 | 16.3457 | 26.0041 | 44.6576 | 0
4.965 | 10.1184 | 7.1751 | 9.4882 | 12.3941 | 13.9793 | 10.1184 | 19.6066 | 32.0007 | 45.98 | 4.975 | 10.1184 | 7.1751 | 9.4882 | 12.3941 | 13.9793 | 10.1184 | 19.6066 | 32.0007 | 45.98 | 0
7.0964 | 8.8277 | 7.1431 | 5.5588 | 11.8832 | 9.3151 | 8.8277 | 14.3864 | 26.2697 | 35.5848 | 7.1064 | 8.8277 | 7.1431 | 5.5588 | 11.8832 | 9.3151 | 8.8277 | 14.3864 | 26.2697 | 35.5848 | 0
-5.8464 | 9.609 | 5.5917 | 5.6532 | 11.8937 | 6.9964 | 9.609 | 15.2623 | 27.156 | 34.1524 | -5.8364 | 9.609 | 5.5917 | 5.6532 | 11.8937 | 6.9964 | 9.609 | 15.2623 | 27.156 | 34.1524 | 0
6.4061 | 8.0007 | 7.9957 | 7.6409 | 16.4743 | 9.7248 | 8.0007 | 15.6417 | 32.1159 | 41.8407 | 6.4161 | 8.0007 | 7.9957 | 7.6409 | 16.4743 | 9.7248 | 8.0007 | 15.6417 | 32.1159 | 41.8407 | 0
0.02792 | 8.9121 | 11.4272 | 3.9962 | 6.8993 | 12.4796 | 8.9121 | 12.9083 | 20.3393 | 32.8189 | 0.03792 | 8.9121 | 11.4272 | 3.9962 | 6.8993 | 12.4796 | 8.9121 | 12.9083 | 20.3393 | 32.8189 | 0
5.7788 | 10.1507 | 6.7144 | 7.8697 | 8.8334 | 14.4215 | 10.1507 | 18.0204 | 26.8538 | 41.2753 | 5.7888 | 10.1507 | 6.7144 | 7.8697 | 8.8334 | 14.4215 | 10.1507 | 18.0204 | 26.8538 | 41.2753 | 0
-9.5731 | 8.0482 | 9.8419 | 10.3515 | 9.0084 | 8.3616 | 8.0482 | 18.3997 | 27.4081 | 35.7697 | -9.5631 | 8.0482 | 9.8419 | 10.3515 | 9.0084 | 8.3616 | 8.0482 | 18.3997 | 27.4081 | 35.7697 | 0
4.8835 | 8.8455 | 7.3552 | 8.9344 | 13.7134 | 12.4707 | 8.8455 | 17.7799 | 31.4933 | 43.964 | 4.8935 | 8.8455 | 7.3552 | 8.9344 | 13.7134 | 12.4707 | 8.8455 | 17.7799 | 31.4933 | 43.964 | 0
16.3479 | 8.7652 | 9.3119 | 11.0142 | 11.1914 | 9.68 | 16.3479 | 27.3621 | 38.5535 | 48.2336 | 16.3579 | 8.7652 | 9.3119 | 11.0142 | 11.1914 | 9.68 | 16.3479 | 27.3621 | 38.5535 | 48.2336 | 0
10.5932 | 9.874 | 8.0764 | 3.4905 | 3.7247 | 15.9038 | 10.5932 | 14.0837 | 18.6696 | 34.5734 | 10.6032 | 9.874 | 8.0764 | 3.4905 | 3.7247 | 15.9038 | 10.5932 | 14.0837 | 18.6696 | 34.5734 | 0
11.9587 | 10.399 | 8.7583 | 6.6426 | 9.0727 | 13.5226 | 11.9587 | 18.6013 | 27.674 | 41.1966 | 11.9687 | 10.399 | 8.7583 | 6.6426 | 9.0727 | 13.5226 | 11.9587 | 18.6013 | 27.674 | 41.1966 | 0
-2.8649 | 7.9146 | 4.7578 | 8.4928 | 9.6358 | 14.8345 | 7.9146 | 16.4074 | 26.0433 | 40.8778 | -2.8549 | 7.9146 | 4.7578 | 8.4928 | 9.6358 | 14.8345 | 7.9146 | 16.4074 | 26.0433 | 40.8778 | 0
-3.4572 | 8.1651 | 7.3325 | 8.5679 | 10.8614 | 16.7797 | 8.1651 | 16.733 | 27.5944 | 44.3741 | -3.4472 | 8.1651 | 7.3325 | 8.5679 | 10.8614 | 16.7797 | 8.1651 | 16.733 | 27.5944 | 44.3741 | 0
-9.536 | 8.0465 | 8.0081 | 7.4118 | 10.5976 | 10.6254 | 8.0465 | 15.4583 | 26.056 | 36.6814 | -9.526 | 8.0465 | 8.0081 | 7.4118 | 10.5976 | 10.6254 | 8.0465 | 15.4583 | 26.056 | 36.6814 | 0
-3.7404 | 8.2251 | 9.3951 | 6.1624 | 9.7112 | 11.8776 | 8.2251 | 14.3875 | 24.0987 | 35.9763 | -3.7304 | 8.2251 | 9.3951 | 6.1624 | 9.7112 | 11.8776 | 8.2251 | 14.3875 | 24.0987 | 35.9763 | 0
-0.99161 | 8.0209 | 7.5078 | 6.6326 | 4.8005 | 16.7474 | 8.0209 | 14.6535 | 19.454 | 36.2014 | -0.98161 | 8.0209 | 7.5078 | 6.6326 | 4.8005 | 16.7474 | 8.0209 | 14.6535 | 19.454 | 36.2014 | 0
8.7757 | 8.2043 | 4.6478 | 8.2139 | 4.6941 | 15.0411 | 8.7757 | 16.9896 | 21.6836 | 36.7248 | 8.7857 | 8.2043 | 4.6478 | 8.2139 | 4.6941 | 15.0411 | 8.7757 | 16.9896 | 21.6836 | 36.7248 | 0
-0.14226 | 10.066 | 8.5084 | 6.5276 | 11.309 | 14.9879 | 10.066 | 16.5937 | 27.9027 | 42.8907 | -0.13226 | 10.066 | 8.5084 | 6.5276 | 11.309 | 14.9879 | 10.066 | 16.5937 | 27.9027 | 42.8907 | 0
0.80052 | 8.1488 | 9.4396 | 6.9036 | 16.3254 | 8.1515 | 8.1488 | 15.0524 | 31.3778 | 39.5293 | 0.81052 | 8.1488 | 9.4396 | 6.9036 | 16.3254 | 8.1515 | 8.1488 | 15.0524 | 31.3778 | 39.5293 | 0
11.6557 | 9.2903 | 8.2958 | 6.2011 | 15.0097 | 16.6491 | 11.6557 | 17.8568 | 32.8664 | 49.5155 | 11.6657 | 9.2903 | 8.2958 | 6.2011 | 15.0097 | 16.6491 | 11.6557 | 17.8568 | 32.8664 | 49.5155 | 0
-3.9354 | 7.9472 | 8.0978 | 8.115 | 7.1603 | 11.0407 | 7.9472 | 16.0622 | 23.2225 | 34.2632 | -3.9254 | 7.9472 | 8.0978 | 8.115 | 7.1603 | 11.0407 | 7.9472 | 16.0622 | 23.2225 | 34.2632 | 0
2.5833 | 9.0861 | 7.47 | 8.0267 | 10.5796 | 11.1725 | 9.0861 | 17.1129 | 27.6925 | 38.865 | 2.5933 | 9.0861 | 7.47 | 8.0267 | 10.5796 | 11.1725 | 9.0861 | 17.1129 | 27.6925 | 38.865 | 0
-0.048655 | 8.3871 | 7.2787 | 5.5063 | 16.3185 | 10.0324 | 8.3871 | 13.8934 | 30.2119 | 40.2443 | -0.038655 | 8.3871 | 7.2787 | 5.5063 | 16.3185 | 10.0324 | 8.3871 | 13.8934 | 30.2119 | 40.2443 | 0
7.9901 | 8.64 | 10.044 | 10.3826 | 8.161 | 14.9639 | 8.64 | 19.0226 | 27.1836 | 42.1475 | 8.0001 | 8.64 | 10.044 | 10.3826 | 8.161 | 14.9639 | 8.64 | 19.0226 | 27.1836 | 42.1475 | 0
5.951 | 9.4301 | 10.5817 | 4.9791 | 13.2797 | 10.268 | 9.4301 | 14.4091 | 27.6888 | 37.9569 | 5.961 | 9.4301 | 10.5817 | 4.9791 | 13.2797 | 10.268 | 9.4301 | 14.4091 | 27.6888 | 37.9569 | 0
0.47229 | 9.4717 | 8.3593 | 4.8901 | 16.8089 | 9.8888 | 9.4717 | 14.3618 | 31.1707 | 41.0595 | 0.48229 | 9.4717 | 8.3593 | 4.8901 | 16.8089 | 9.8888 | 9.4717 | 14.3618 | 31.1707 | 41.0595 | 0
2.7657 | 9.2963 | 7.9085 | 5.7357 | 12.4249 | 8.3659 | 9.2963 | 15.032 | 27.4569 | 35.8228 | 2.7757 | 9.2963 | 7.9085 | 5.7357 | 12.4249 | 8.3659 | 9.2963 | 15.032 | 27.4569 | 35.8228 | 0
8.2566 | 8.505 | 10.9743 | 4.2111 | 11.088 | 9.3027 | 8.505 | 12.7161 | 23.8041 | 33.1068 | 8.2666 | 8.505 | 10.9743 | 4.2111 | 11.088 | 9.3027 | 8.505 | 12.7161 | 23.8041 | 33.1068 | 0
4.6954 | 8.0452 | 10.3085 | 6.0818 | 12.8316 | 12.5325 | 8.0452 | 14.127 | 26.9586 | 39.4911 | 4.7054 | 8.0452 | 10.3085 | 6.0818 | 12.8316 | 12.5325 | 8.0452 | 14.127 | 26.9586 | 39.4911 | 0
-1.2647 | 9.0121 | 8.1208 | 10.6638 | 13.3278 | 11.6178 | 9.0121 | 19.6759 | 33.0037 | 44.6215 | -1.2547 | 9.0121 | 8.1208 | 10.6638 | 13.3278 | 11.6178 | 9.0121 | 19.6759 | 33.0037 | 44.6215 | 0
1.3264 | 9.3504 | 7.1725 | 5.638 | 11.279 | 11.9396 | 9.3504 | 14.9884 | 26.2673 | 38.2069 | 1.3364 | 9.3504 | 7.1725 | 5.638 | 11.279 | 11.9396 | 9.3504 | 14.9884 | 26.2673 | 38.2069 | 0
-1.2744 | 9.052 | 7.1684 | 4.6213 | 11.6363 | 11.5901 | 9.052 | 13.6733 | 25.3097 | 36.8997 | -1.2644 | 9.052 | 7.1684 | 4.6213 | 11.6363 | 11.5901 | 9.052 | 13.6733 | 25.3097 | 36.8997 | 0
-3.6641 | 8.2104 | 10.5532 | 10.7981 | 7.4932 | 8.7374 | 8.2104 | 19.0085 | 26.5016 | 35.2391 | -3.6541 | 8.2104 | 10.5532 | 10.7981 | 7.4932 | 8.7374 | 8.2104 | 19.0085 | 26.5016 | 35.2391 | 0
2.8792 | 8.7351 | 8.6935 | 5.9684 | 12.0681 | 8.6643 | 8.7351 | 14.7035 | 26.7716 | 35.4359 | 2.8892 | 8.7351 | 8.6935 | 5.9684 | 12.0681 | 8.6643 | 8.7351 | 14.7035 | 26.7716 | 35.4359 | 0
2.6815 | 10.1654 | 9.2489 | 6.7084 | 8.7563 | 15.3441 | 10.1654 | 16.8738 | 25.6301 | 40.9742 | 2.6915 | 10.1654 | 9.2489 | 6.7084 | 8.7563 | 15.3441 | 10.1654 | 16.8738 | 25.6301 | 40.9742 | 0
1.0002 | 9.8486 | 7.7337 | 5.4913 | 9.7555 | 10.1301 | 9.8486 | 15.34 | 25.0954 | 35.2256 | 1.0102 | 9.8486 | 7.7337 | 5.4913 | 9.7555 | 10.1301 | 9.8486 | 15.34 | 25.0954 | 35.2256 | 0
0.19803 | 9.0865 | 7.6496 | 3.2478 | 10.3289 | 15.6064 | 9.0865 | 12.3343 | 22.6632 | 38.2696 | 0.20803 | 9.0865 | 7.6496 | 3.2478 | 10.3289 | 15.6064 | 9.0865 | 12.3343 | 22.6632 | 38.2696 | 0
4.5607 | 7.5606 | 10.3097 | 7.3801 | 4.6691 | 18.0285 | 7.5606 | 14.9407 | 19.6099 | 37.6384 | 4.5707 | 7.5606 | 10.3097 | 7.3801 | 4.6691 | 18.0285 | 7.5606 | 14.9407 | 19.6099 | 37.6384 | 0
2.9428 | 10.641 | 8.6241 | 4.8989 | 6.0623 | 9.3742 | 10.641 | 15.5399 | 21.6022 | 30.9764 | 2.9528 | 10.641 | 8.6241 | 4.8989 | 6.0623 | 9.3742 | 10.641 | 15.5399 | 21.6022 | 30.9764 | 0
6.3399 | 10.4435 | 7.4038 | 4.5345 | 5.3714 | 10.6561 | 10.4435 | 14.978 | 20.3494 | 31.0055 | 6.3499 | 10.4435 | 7.4038 | 4.5345 | 5.3714 | 10.6561 | 10.4435 | 14.978 | 20.3494 | 31.0055 | 0
4.2071 | 10.5051 | 12.9538 | 4.9262 | 10.0797 | 11.1141 | 10.5051 | 15.4313 | 25.511 | 36.6251 | 4.2171 | 10.5051 | 12.9538 | 4.9262 | 10.0797 | 11.1141 | 10.5051 | 15.4313 | 25.511 | 36.6251 | 0
0.65261 | 8.3406 | 8.6698 | 5.7205 | 10.0529 | 15.1733 | 8.3406 | 14.0611 | 24.114 | 39.2873 | 0.66261 | 8.3406 | 8.6698 | 5.7205 | 10.0529 | 15.1733 | 8.3406 | 14.0611 | 24.114 | 39.2873 | 0
-0.32925 | 9.4993 | 9.1661 | 7.203 | 11.4201 | 12.6921 | 9.4993 | 16.7023 | 28.1224 | 40.8145 | -0.31925 | 9.4993 | 9.1661 | 7.203 | 11.4201 | 12.6921 | 9.4993 | 16.7023 | 28.1224 | 40.8145 | 0
1.7341 | 8.9443 | 6.8922 | 8.2704 | 12.0403 | 14.8878 | 8.9443 | 17.2147 | 29.2551 | 44.1429 | 1.7441 | 8.9443 | 6.8922 | 8.2704 | 12.0403 | 14.8878 | 8.9443 | 17.2147 | 29.2551 | 44.1429 | 0
1.6737 | 7.6397 | 5.3975 | 8.4666 | 7.9306 | 12.3452 | 7.6397 | 16.1063 | 24.0369 | 36.3821 | 1.6837 | 7.6397 | 5.3975 | 8.4666 | 7.9306 | 12.3452 | 7.6397 | 16.1063 | 24.0369 | 36.3821 | 0
-6.0535 | 10.5639 | 7.049 | 3.9319 | 9.3834 | 10.7442 | 10.5639 | 14.4958 | 23.8793 | 34.6235 | -6.0435 | 10.5639 | 7.049 | 3.9319 | 9.3834 | 10.7442 | 10.5639 | 14.4958 | 23.8793 | 34.6235 | 0
2.6304 | 9.6319 | 8.0379 | 7.5149 | 6.7593 | 13.2801 | 9.6319 | 17.1468 | 23.9061 | 37.1862 | 2.6404 | 9.6319 | 8.0379 | 7.5149 | 6.7593 | 13.2801 | 9.6319 | 17.1468 | 23.9061 | 37.1862 | 0
5.0664 | 9.1967 | 7.5781 | 9.4743 | 8.6968 | 17.0497 | 9.1967 | 18.671 | 27.3678 | 44.4175 | 5.0764 | 9.1967 | 7.5781 | 9.4743 | 8.6968 | 17.0497 | 9.1967 | 18.671 | 27.3678 | 44.4175 | 0
4.5886 | 10.529 | 7.1932 | 7.6685 | 12.8303 | 8.531 | 10.529 | 18.1976 | 31.0278 | 39.5589 | 4.5986 | 10.529 | 7.1932 | 7.6685 | 12.8303 | 8.531 | 10.529 | 18.1976 | 31.0278 | 39.5589 | 0
-12.58 | 12.021 | 7.6496 | 8.1204 | 13.6278 | 10.0925 | 12.021 | 20.1414 | 33.7692 | 43.8617 | -12.57 | 12.021 | 7.6496 | 8.1204 | 13.6278 | 10.0925 | 12.021 | 20.1414 | 33.7692 | 43.8617 | 0
9.0991 | 9.9411 | 10.4607 | 4.9796 | 6.1946 | 15.2356 | 9.9411 | 14.9207 | 21.1153 | 36.3508 | 9.1091 | 9.9411 | 10.4607 | 4.9796 | 6.1946 | 15.2356 | 9.9411 | 14.9207 | 21.1153 | 36.3508 | 0
2.9964 | 9.7473 | 6.5152 | 5.4009 | 10.9977 | 10.4528 | 9.7473 | 15.1482 | 26.1459 | 36.5986 | 3.0064 | 9.7473 | 6.5152 | 5.4009 | 10.9977 | 10.4528 | 9.7473 | 15.1482 | 26.1459 | 36.5986 | 0
8.607 | 8.8769 | 7.884 | 8.9919 | 13.2595 | 14.2972 | 8.8769 | 17.8688 | 31.1283 | 45.4255 | 8.617 | 8.8769 | 7.884 | 8.9919 | 13.2595 | 14.2972 | 8.8769 | 17.8688 | 31.1283 | 45.4255 | 0
-4.8455 | 8.3917 | 10.0064 | 12.1632 | 3.167 | 9.4198 | 8.3917 | 20.5549 | 23.7219 | 33.1417 | -4.8355 | 8.3917 | 10.0064 | 12.1632 | 3.167 | 9.4198 | 8.3917 | 20.5549 | 23.7219 | 33.1417 | 0
4.8246 | 7.2514 | 8.3082 | 6.2745 | 6.8357 | 9.5978 | 7.2514 | 13.5259 | 20.3616 | 29.9594 | 4.8346 | 7.2514 | 8.3082 | 6.2745 | 6.8357 | 9.5978 | 7.2514 | 13.5259 | 20.3616 | 29.9594 | 0
-2.6743 | 8.5341 | 8.2662 | 7.7286 | 13.2566 | 8.0634 | 8.5341 | 16.2627 | 29.5193 | 37.5827 | -2.6643 | 8.5341 | 8.2662 | 7.7286 | 13.2566 | 8.0634 | 8.5341 | 16.2627 | 29.5193 | 37.5827 | 0
2.2573 | 8.3192 | 6.3462 | 3.1942 | 9.7407 | 8.2618 | 8.3192 | 11.5134 | 21.2541 | 29.5159 | 2.2673 | 8.3192 | 6.3462 | 3.1942 | 9.7407 | 8.2618 | 8.3192 | 11.5134 | 21.2541 | 29.5159 | 0
12.0279 | 8.3468 | 5.9348 | 6.6402 | 12.1871 | 14.3002 | 12.0279 | 18.6681 | 30.8551 | 45.1553 | 12.0379 | 8.3468 | 5.9348 | 6.6402 | 12.1871 | 14.3002 | 12.0279 | 18.6681 | 30.8551 | 45.1553 | 0
2.3548 | 8.6745 | 6.2252 | 8.8413 | 5.5612 | 8.9115 | 8.6745 | 17.5158 | 23.0769 | 31.9885 | 2.3648 | 8.6745 | 6.2252 | 8.8413 | 5.5612 | 8.9115 | 8.6745 | 17.5158 | 23.0769 | 31.9885 | 0
6.7993 | 9.8218 | 5.1506 | 10.6508 | 13.7681 | 10.8795 | 9.8218 | 20.4726 | 34.2407 | 45.1202 | 6.8093 | 9.8218 | 5.1506 | 10.6508 | 13.7681 | 10.8795 | 9.8218 | 20.4726 | 34.2407 | 45.1202 | 0
6.2071 | 9.2939 | 6.5575 | 4.0104 | 12.2682 | 9.1314 | 9.2939 | 13.3043 | 25.5725 | 34.7039 | 6.2171 | 9.2939 | 6.5575 | 4.0104 | 12.2682 | 9.1314 | 9.2939 | 13.3043 | 25.5725 | 34.7039 | 0
2.6673 | 8.3495 | 4.5051 | 5.0506 | 11.0713 | 12.6128 | 8.3495 | 13.4001 | 24.4714 | 37.0842 | 2.6773 | 8.3495 | 4.5051 | 5.0506 | 11.0713 | 12.6128 | 8.3495 | 13.4001 | 24.4714 | 37.0842 | 0
5.0916 | 9.3801 | 11.3902 | 8.665 | 13.9978 | 12.6097 | 9.3801 | 18.0451 | 32.0429 | 44.6526 | 5.1016 | 9.3801 | 11.3902 | 8.665 | 13.9978 | 12.6097 | 9.3801 | 18.0451 | 32.0429 | 44.6526 | 0
0.5849 | 8.0272 | 6.5355 | 6.815 | 2.3588 | 14.145 | 8.0272 | 14.8422 | 17.2011 | 31.346 | 0.5949 | 8.0272 | 6.5355 | 6.815 | 2.3588 | 14.145 | 8.0272 | 14.8422 | 17.2011 | 31.346 | 0
4.5196 | 9.668 | 6.7829 | 5.4318 | 8.3325 | 12.6951 | 9.668 | 15.0999 | 23.4323 | 36.1275 | 4.5296 | 9.668 | 6.7829 | 5.4318 | 8.3325 | 12.6951 | 9.668 | 15.0999 | 23.4323 | 36.1275 | 0
2.8141 | 9.1819 | 8.5599 | 7.8717 | 13.5239 | 10.8381 | 9.1819 | 17.0536 | 30.5774 | 41.4156 | 2.8241 | 9.1819 | 8.5599 | 7.8717 | 13.5239 | 10.8381 | 9.1819 | 17.0536 | 30.5774 | 41.4156 | 0
1.2887 | 8.1393 | 7.0335 | 10.9041 | 14.6074 | 9.0969 | 8.1393 | 19.0434 | 33.6508 | 42.7477 | 1.2987 | 8.1393 | 7.0335 | 10.9041 | 14.6074 | 9.0969 | 8.1393 | 19.0434 | 33.6508 | 42.7477 | 0
2.2758 | 8.8748 | 5.5554 | 11.1989 | 4.2217 | 18.1145 | 8.8748 | 20.0737 | 24.2954 | 42.4098 | 2.2858 | 8.8748 | 5.5554 | 11.1989 | 4.2217 | 18.1145 | 8.8748 | 20.0737 | 24.2954 | 42.4098 | 0
3.5559 | 8.8315 | 6.3768 | 6.14 | 10.386 | 17.5755 | 8.8315 | 14.9715 | 25.3575 | 42.933 | 3.5659 | 8.8315 | 6.3768 | 6.14 | 10.386 | 17.5755 | 8.8315 | 14.9715 | 25.3575 | 42.933 | 0
9.6867 | 7.5956 | 8.1806 | 9.5884 | 11.8555 | 14.0872 | 9.6867 | 19.2751 | 31.1306 | 45.2178 | 9.6967 | 7.5956 | 8.1806 | 9.5884 | 11.8555 | 14.0872 | 9.6867 | 19.2751 | 31.1306 | 45.2178 | 0
-12.7572 | 7.8471 | 6.3124 | 5.881 | 12.0437 | 16.7044 | 7.8471 | 13.7281 | 25.7718 | 42.4762 | -12.7472 | 7.8471 | 6.3124 | 5.881 | 12.0437 | 16.7044 | 7.8471 | 13.7281 | 25.7718 | 42.4762 | 0
10.1694 | 7.6735 | 6.2283 | 10.0154 | 6.3409 | 7.5063 | 10.1694 | 20.1848 | 26.5257 | 34.032 | 10.1794 | 7.6735 | 6.2283 | 10.0154 | 6.3409 | 7.5063 | 10.1694 | 20.1848 | 26.5257 | 34.032 | 0
0.23643 | 6.8039 | 6.6065 | 8.9016 | 9.722 | 11.0137 | 6.8039 | 15.7055 | 25.4275 | 36.4412 | 0.24643 | 6.8039 | 6.6065 | 8.9016 | 9.722 | 11.0137 | 6.8039 | 15.7055 | 25.4275 | 36.4412 | 0
5.5365 | 11.5209 | 9.4149 | 6.9039 | 3.8129 | 10.3302 | 11.5209 | 18.4248 | 22.2377 | 32.5679 | 5.5465 | 11.5209 | 9.4149 | 6.9039 | 3.8129 | 10.3302 | 11.5209 | 18.4248 | 22.2377 | 32.5679 | 0
-3.7661 | 9.34 | 6.9264 | 6.3284 | 7.4749 | 12.0573 | 9.34 | 15.6685 | 23.1433 | 35.2006 | -3.7561 | 9.34 | 6.9264 | 6.3284 | 7.4749 | 12.0573 | 9.34 | 15.6685 | 23.1433 | 35.2006 | 0
-3.6453 | 8.521 | 10.076 | 7.7347 | 16.5747 | 12.0815 | 8.521 | 16.2558 | 32.8304 | 44.9119 | -3.6353 | 8.521 | 10.076 | 7.7347 | 16.5747 | 12.0815 | 8.521 | 16.2558 | 32.8304 | 44.9119 | 0
-7.2011 | 9.4015 | 4.6228 | 6.5239 | 7.8954 | 12.266 | 9.4015 | 15.9255 | 23.8209 | 36.0869 | -7.1911 | 9.4015 | 4.6228 | 6.5239 | 7.8954 | 12.266 | 9.4015 | 15.9255 | 23.8209 | 36.0869 | 0
4.8613 | 7.7303 | 6.1559 | 6.5795 | 11.0889 | 9.8216 | 7.7303 | 14.3098 | 25.3987 | 35.2204 | 4.8713 | 7.7303 | 6.1559 | 6.5795 | 11.0889 | 9.8216 | 7.7303 | 14.3098 | 25.3987 | 35.2204 | 0
8.515 | 11.6491 | 10.0645 | 4.5024 | 12.7115 | 15.187 | 11.6491 | 16.1515 | 28.863 | 44.0501 | 8.525 | 11.6491 | 10.0645 | 4.5024 | 12.7115 | 15.187 | 11.6491 | 16.1515 | 28.863 | 44.0501 | 0
3.4905 | 8.1029 | 8.3257 | 6.1282 | 10.8663 | 8.7219 | 8.1029 | 14.2312 | 25.0975 | 33.8194 | 3.5005 | 8.1029 | 8.3257 | 6.1282 | 10.8663 | 8.7219 | 8.1029 | 14.2312 | 25.0975 | 33.8194 | 0
-2.9283 | 9.2284 | 8.5961 | 9.1951 | 6.4211 | 18.0319 | 9.2284 | 18.4235 | 24.8445 | 42.8764 | -2.9183 | 9.2284 | 8.5961 | 9.1951 | 6.4211 | 18.0319 | 9.2284 | 18.4235 | 24.8445 | 42.8764 | 0
1.2286 | 9.3018 | 9.4307 | 9.0038 | 17.215 | 9.3094 | 9.3018 | 18.3056 | 35.5206 | 44.83 | 1.2386 | 9.3018 | 9.4307 | 9.0038 | 17.215 | 9.3094 | 9.3018 | 18.3056 | 35.5206 | 44.83 | 0
6.6349 | 10.1273 | 8.3636 | 4.7211 | 6.0176 | 12.5468 | 10.1273 | 14.8484 | 20.866 | 33.4128 | 6.6449 | 10.1273 | 8.3636 | 4.7211 | 6.0176 | 12.5468 | 10.1273 | 14.8484 | 20.866 | 33.4128 | 0
10.5873 | 8.3691 | 10.6489 | 8.4257 | 7.9319 | 16.3822 | 10.5873 | 19.0129 | 26.9449 | 43.3271 | 10.5973 | 8.3691 | 10.6489 | 8.4257 | 7.9319 | 16.3822 | 10.5873 | 19.0129 | 26.9449 | 43.3271 | 0
3.0043 | 10.0226 | 7.4028 | 6.1711 | 11.9235 | 9.2673 | 10.0226 | 16.1937 | 28.1172 | 37.3845 | 3.0143 | 10.0226 | 7.4028 | 6.1711 | 11.9235 | 9.2673 | 10.0226 | 16.1937 | 28.1172 | 37.3845 | 0
3.4263 | 8.685 | 8.5361 | 3.1106 | 9.1044 | 5.3568 | 8.685 | 11.7955 | 20.9 | 26.2567 | 3.4363 | 8.685 | 8.5361 | 3.1106 | 9.1044 | 5.3568 | 8.685 | 11.7955 | 20.9 | 26.2567 | 0
1.7294 | 9.6454 | 7.7348 | 6.3374 | 7.4768 | 9.6587 | 9.6454 | 15.9828 | 23.4596 | 33.1183 | 1.7394 | 9.6454 | 7.7348 | 6.3374 | 7.4768 | 9.6587 | 9.6454 | 15.9828 | 23.4596 | 33.1183 | 0
-2.3513 | 8.061 | 10.7003 | 5.3921 | 5.2752 | 12.9433 | 8.061 | 13.4531 | 18.7614 | 31.7047 | -2.3413 | 8.061 | 10.7003 | 5.3921 | 5.2752 | 12.9433 | 8.061 | 13.4531 | 18.7614 | 31.7047 | 0
1.7716 | 8.5148 | 10.6941 | 6.5224 | 11.5028 | 12.1711 | 8.5148 | 15.0372 | 26.54 | 38.7111 | 1.7816 | 8.5148 | 10.6941 | 6.5224 | 11.5028 | 12.1711 | 8.5148 | 15.0372 | 26.54 | 38.7111 | 0
0.053854 | 9.268 | 8.1794 | 6.5218 | 15.8821 | 13.4674 | 9.268 | 15.7898 | 31.6719 | 45.1393 | 0.063854 | 9.268 | 8.1794 | 6.5218 | 15.8821 | 13.4674 | 9.268 | 15.7898 | 31.6719 | 45.1393 | 0
-2.797 | 10.6598 | 5.2131 | 7.4636 | 10.2642 | 19.2838 | 10.6598 | 18.1234 | 28.3876 | 47.6714 | -2.787 | 10.6598 | 5.2131 | 7.4636 | 10.2642 | 19.2838 | 10.6598 | 18.1234 | 28.3876 | 47.6714 | 0
-7.6697 | 8.0711 | 10.244 | 13.3609 | 7.699 | 11.183 | 8.0711 | 21.4321 | 29.131 | 40.314 | -7.6597 | 8.0711 | 10.244 | 13.3609 | 7.699 | 11.183 | 8.0711 | 21.4321 | 29.131 | 40.314 | 0
2.8797 | 7.7961 | 7.4561 | 7.7329 | 9.0687 | 13.786 | 7.7961 | 15.5289 | 24.5976 | 38.3836 | 2.8897 | 7.7961 | 7.4561 | 7.7329 | 9.0687 | 13.786 | 7.7961 | 15.5289 | 24.5976 | 38.3836 | 0
-9.7643 | 8.0759 | 7.7976 | 7.0624 | 15.1419 | 11.1426 | 8.0759 | 15.1384 | 30.2803 | 41.4229 | -9.7543 | 8.0759 | 7.7976 | 7.0624 | 15.1419 | 11.1426 | 8.0759 | 15.1384 | 30.2803 | 41.4229 | 0
1.0511 | 7.5401 | 5.7746 | 8.539 | 12.6859 | 20.7418 | 7.5401 | 16.0791 | 28.765 | 49.5069 | 1.0611 | 7.5401 | 5.7746 | 8.539 | 12.6859 | 20.7418 | 7.5401 | 16.0791 | 28.765 | 49.5069 | 0
1.6539 | 9.7562 | 11.2601 | 4.8511 | 9.281 | 4.9728 | 9.7562 | 14.6073 | 23.8883 | 28.8611 | 1.6639 | 9.7562 | 11.2601 | 4.8511 | 9.281 | 4.9728 | 9.7562 | 14.6073 | 23.8883 | 28.8611 | 0
-16.5074 | 9.0999 | 9.0312 | 10.1082 | 12.1798 | 5.0686 | 9.0999 | 19.2081 | 31.3879 | 36.4565 | -16.4974 | 9.0999 | 9.0312 | 10.1082 | 12.1798 | 5.0686 | 9.0999 | 19.2081 | 31.3879 | 36.4565 | 0
-4.7997 | 8.9741 | 7.8951 | 5.4322 | 10.4876 | 10.5793 | 8.9741 | 14.4063 | 24.8939 | 35.4732 | -4.7897 | 8.9741 | 7.8951 | 5.4322 | 10.4876 | 10.5793 | 8.9741 | 14.4063 | 24.8939 | 35.4732 | 0
2.3832 | 9.9126 | 4.1624 | 6.7165 | 10.8128 | 19.7966 | 9.9126 | 16.6291 | 27.4419 | 47.2385 | 2.3932 | 9.9126 | 4.1624 | 6.7165 | 10.8128 | 19.7966 | 9.9126 | 16.6291 | 27.4419 | 47.2385 | 0
0.23619 | 9.1655 | 6.7428 | 5.4147 | 6.5492 | 11.2126 | 9.1655 | 14.5803 | 21.1295 | 32.3421 | 0.24619 | 9.1655 | 6.7428 | 5.4147 | 6.5492 | 11.2126 | 9.1655 | 14.5803 | 21.1295 | 32.3421 | 0
1.4061 | 8.452 | 8.4379 | 7.6215 | 7.587 | 14.0028 | 8.452 | 16.0735 | 23.6606 | 37.6634 | 1.4161 | 8.452 | 8.4379 | 7.6215 | 7.587 | 14.0028 | 8.452 | 16.0735 | 23.6606 | 37.6634 | 0
8.4823 | 7.8577 | 9.8619 | 4.7029 | 10.8641 | 11.2008 | 8.4823 | 13.1852 | 24.0493 | 35.2501 | 8.4923 | 7.8577 | 9.8619 | 4.7029 | 10.8641 | 11.2008 | 8.4823 | 13.1852 | 24.0493 | 35.2501 | 0
-1.3649 | 10.043 | 10.9429 | 4.4803 | 8.6908 | 8.0151 | 10.043 | 14.5232 | 23.214 | 31.2291 | -1.3549 | 10.043 | 10.9429 | 4.4803 | 8.6908 | 8.0151 | 10.043 | 14.5232 | 23.214 | 31.2291 | 0
0.30318 | 8.8306 | 8.8014 | 7.3416 | 11.4337 | 15.4139 | 8.8306 | 16.1722 | 27.6059 | 43.0198 | 0.31318 | 8.8306 | 8.8014 | 7.3416 | 11.4337 | 15.4139 | 8.8306 | 16.1722 | 27.6059 | 43.0198 | 0
-1.595 | 8.3969 | 10.3487 | 4.8293 | 13.9948 | 16.4018 | 8.3969 | 13.2262 | 27.221 | 43.6228 | -1.585 | 8.3969 | 10.3487 | 4.8293 | 13.9948 | 16.4018 | 8.3969 | 13.2262 | 27.221 | 43.6228 | 0
-7.5556 | 7.6221 | 5.3362 | 5.5418 | 7.6451 | 9.0242 | 7.6221 | 13.1639 | 20.809 | 29.8333 | -7.5456 | 7.6221 | 5.3362 | 5.5418 | 7.6451 | 9.0242 | 7.6221 | 13.1639 | 20.809 | 29.8333 | 0
9.5737 | 9.4023 | 12.0112 | 7.7077 | 8.6476 | 12.1905 | 9.5737 | 17.2814 | 25.929 | 38.1195 | 9.5837 | 9.4023 | 12.0112 | 7.7077 | 8.6476 | 12.1905 | 9.5737 | 17.2814 | 25.929 | 38.1195 | 0
6.2037 | 7.3031 | 9.0678 | 6.9175 | 7.8109 | 15.7067 | 7.3031 | 14.2206 | 22.0314 | 37.7382 | 6.2137 | 7.3031 | 9.0678 | 6.9175 | 7.8109 | 15.7067 | 7.3031 | 14.2206 | 22.0314 | 37.7382 | 0
3.0582 | 10.6366 | 7.2389 | 9.8384 | 8.9972 | 13.3617 | 10.6366 | 20.475 | 29.4722 | 42.8339 | 3.0682 | 10.6366 | 7.2389 | 9.8384 | 8.9972 | 13.3617 | 10.6366 | 20.475 | 29.4722 | 42.8339 | 0
18.2247 | 8.2849 | 6.0398 | 6.3075 | 8.4946 | 12.4902 | 18.2247 | 24.5322 | 33.0268 | 45.517 | 18.2347 | 8.2849 | 6.0398 | 6.3075 | 8.4946 | 12.4902 | 18.2247 | 24.5322 | 33.0268 | 45.517 | 0
1.2364 | 11.9563 | 6.7951 | 7.3156 | 0.16523 | 9.6879 | 11.9563 | 19.2719 | 19.4371 | 29.125 | 1.2464 | 11.9563 | 6.7951 | 7.3156 | 0.16523 | 9.6879 | 11.9563 | 19.2719 | 19.4371 | 29.125 | 0
1.6561 | 9.9658 | 8.3822 | 3.8659 | 12.351 | 6.0437 | 9.9658 | 13.8317 | 26.1826 | 32.2264 | 1.6661 | 9.9658 | 8.3822 | 3.8659 | 12.351 | 6.0437 | 9.9658 | 13.8317 | 26.1826 | 32.2264 | 0
0.82587 | 11.1022 | 4.8323 | 3.9698 | 7.7724 | 14.2531 | 11.1022 | 15.072 | 22.8443 | 37.0975 | 0.83587 | 11.1022 | 4.8323 | 3.9698 | 7.7724 | 14.2531 | 11.1022 | 15.072 | 22.8443 | 37.0975 | 0
5.793 | 8.709 | 8.2964 | 6.017 | 11.9392 | 10.8064 | 8.709 | 14.726 | 26.6652 | 37.4716 | 5.803 | 8.709 | 8.2964 | 6.017 | 11.9392 | 10.8064 | 8.709 | 14.726 | 26.6652 | 37.4716 | 0
-11.6014 | 8.2157 | 8.3918 | 4.7893 | 13.38 | 11.8816 | 8.2157 | 13.0049 | 26.3849 | 38.2664 | -11.5914 | 8.2157 | 8.3918 | 4.7893 | 13.38 | 11.8816 | 8.2157 | 13.0049 | 26.3849 | 38.2664 | 0
3.6346 | 8.6947 | 8.2278 | 7.202 | 3.5057 | 15.1478 | 8.6947 | 15.8967 | 19.4024 | 34.5502 | 3.6446 | 8.6947 | 8.2278 | 7.202 | 3.5057 | 15.1478 | 8.6947 | 15.8967 | 19.4024 | 34.5502 | 0
8.191 | 10.3314 | 8.8732 | 6.9059 | 10.1176 | 15.5649 | 10.3314 | 17.2373 | 27.3549 | 42.9198 | 8.201 | 10.3314 | 8.8732 | 6.9059 | 10.1176 | 15.5649 | 10.3314 | 17.2373 | 27.3549 | 42.9198 | 0
8.5261 | 9.4619 | 7.31 | 5.7181 | 7.802 | 12.6433 | 9.4619 | 15.18 | 22.9821 | 35.6254 | 8.5361 | 9.4619 | 7.31 | 5.7181 | 7.802 | 12.6433 | 9.4619 | 15.18 | 22.9821 | 35.6254 | 0
1.523 | 9.714 | 7.3144 | 1.192 | 8.3787 | 10.7204 | 9.714 | 10.906 | 19.2847 | 30.0051 | 1.533 | 9.714 | 7.3144 | 1.192 | 8.3787 | 10.7204 | 9.714 | 10.906 | 19.2847 | 30.0051 | 0
-10.0526 | 8.8285 | 7.3007 | 10.6527 | 12.2199 | 5.4423 | 8.8285 | 19.4812 | 31.7011 | 37.1434 | -10.0426 | 8.8285 | 7.3007 | 10.6527 | 12.2199 | 5.4423 | 8.8285 | 19.4812 | 31.7011 | 37.1434 | 0
1.5307 | 7.2142 | 4.4918 | 5.8311 | 6.8026 | 9.5307 | 7.2142 | 13.0453 | 19.8479 | 29.3786 | 1.5407 | 7.2142 | 4.4918 | 5.8311 | 6.8026 | 9.5307 | 7.2142 | 13.0453 | 19.8479 | 29.3786 | 0
3.9181 | 11.0338 | 7.3913 | 10.9266 | 11.6735 | 9.5346 | 11.0338 | 21.9604 | 33.634 | 43.1686 | 3.9281 | 11.0338 | 7.3913 | 10.9266 | 11.6735 | 9.5346 | 11.0338 | 21.9604 | 33.634 | 43.1686 | 0
15.5109 | 8.5623 | 10.0568 | 4.2168 | 10.8071 | 12.0009 | 15.5109 | 19.7277 | 30.5348 | 42.5357 | 15.5209 | 8.5623 | 10.0568 | 4.2168 | 10.8071 | 12.0009 | 15.5109 | 19.7277 | 30.5348 | 42.5357 | 0
2.1354 | 10.3629 | 7.433 | 7.3219 | 12.4051 | 12.2147 | 10.3629 | 17.6848 | 30.0899 | 42.3046 | 2.1454 | 10.3629 | 7.433 | 7.3219 | 12.4051 | 12.2147 | 10.3629 | 17.6848 | 30.0899 | 42.3046 | 0
6.4212 | 10.1604 | 9.6715 | 2.8114 | 10.6688 | 17.9651 | 10.1604 | 12.9718 | 23.6405 | 41.6057 | 6.4312 | 10.1604 | 9.6715 | 2.8114 | 10.6688 | 17.9651 | 10.1604 | 12.9718 | 23.6405 | 41.6057 | 0
-1.2083 | 9.5138 | 10.1537 | 6.8453 | 14.2928 | 17.9789 | 9.5138 | 16.3591 | 30.6519 | 48.6308 | -1.1983 | 9.5138 | 10.1537 | 6.8453 | 14.2928 | 17.9789 | 9.5138 | 16.3591 | 30.6519 | 48.6308 | 0
[8 empty] | Average | 38.5845 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!

## test activity B
A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | A~N(6,2) | B~N(9,1) | C~N(8,2) | D~N(7,2) | E~N(10,3) | F~(12,3) | Event 1 | Event 2 | Event 3 | Event 4 | diff
-7.7551 | 10.6172 | 9.951 | 11.4327 | 11.4836 | 11.4968 | 10.6172 | 22.0499 | 33.5335 | 45.0303 | -7.7551 | 10.6272 | 9.951 | 11.4327 | 11.4836 | 11.4968 | 10.6272 | 22.0599 | 33.5435 | 45.0403 | 0.01
7.4367 | 9.1492 | 8.1533 | 9.6422 | 14.8066 | 8.745 | 9.1492 | 18.7914 | 33.598 | 42.343 | 7.4367 | 9.1592 | 8.1533 | 9.6422 | 14.8066 | 8.745 | 9.1592 | 18.8014 | 33.608 | 42.353 | 0.01
6.8651 | 7.7647 | 11.4096 | 10.5908 | 6.3737 | 12.5465 | 7.7647 | 18.3555 | 24.7292 | 37.2757 | 6.8651 | 7.7747 | 11.4096 | 10.5908 | 6.3737 | 12.5465 | 7.7747 | 18.3655 | 24.7392 | 37.2857 | 0.01
11.0288 | 7.8306 | 8.3418 | 11.2048 | 10.3992 | 10.4727 | 11.0288 | 22.2336 | 32.6328 | 43.1055 | 11.0288 | 7.8406 | 8.3418 | 11.2048 | 10.3992 | 10.4727 | 11.0288 | 22.2336 | 32.6328 | 43.1055 | 0
3.1602 | 9.7531 | 9.356 | 7.1589 | 5.8983 | 17.1026 | 9.7531 | 16.912 | 22.8103 | 39.9129 | 3.1602 | 9.7631 | 9.356 | 7.1589 | 5.8983 | 17.1026 | 9.7631 | 16.922 | 22.8203 | 39.9229 | 0.01
11.4248 | 9.0225 | 4.4877 | 8.8016 | 11.0903 | 10.7888 | 11.4248 | 20.2264 | 31.3167 | 42.1055 | 11.4248 | 9.0325 | 4.4877 | 8.8016 | 11.0903 | 10.7888 | 11.4248 | 20.2264 | 31.3167 | 42.1055 | 0
-1.5576 | 8.8854 | 7.367 | 3.9729 | 11.2123 | 9.7199 | 8.8854 | 12.8583 | 24.0706 | 33.7905 | -1.5576 | 8.8954 | 7.367 | 3.9729 | 11.2123 | 9.7199 | 8.8954 | 12.8683 | 24.0806 | 33.8005 | 0.01
-7.7023 | 9.3515 | 6.9936 | 7.8158 | 17.5153 | 11.1727 | 9.3515 | 17.1673 | 34.6826 | 45.8553 | -7.7023 | 9.3615 | 6.9936 | 7.8158 | 17.5153 | 11.1727 | 9.3615 | 17.1773 | 34.6926 | 45.8653 | 0.01
4.4741 | 8.6752 | 9.0763 | 7.7107 | 6.6338 | 13.2586 | 8.6752 | 16.3859 | 23.0197 | 36.2783 | 4.4741 | 8.6852 | 9.0763 | 7.7107 | 6.6338 | 13.2586 | 8.6852 | 16.3959 | 23.0297 | 36.2883 | 0.01
10.5441 | 8.6537 | 10.3992 | 3.5911 | 8.2745 | 8.8554 | 10.5441 | 14.1353 | 22.4097 | 31.2652 | 10.5441 | 8.6637 | 10.3992 | 3.5911 | 8.2745 | 8.8554 | 10.5441 | 14.1353 | 22.4097 | 31.2652 | 0
-3.9182 | 7.3989 | 9.1769 | 3.4307 | 9.2799 | 10.1396 | 7.3989 | 10.8296 | 20.1095 | 30.2491 | -3.9182 | 7.4089 | 9.1769 | 3.4307 | 9.2799 | 10.1396 | 7.4089 | 10.8396 | 20.1195 | 30.2591 | 0.01
-0.98948 | 10.5609 | 8.5522 | 7.0728 | 9.2645 | 10.6446 | 10.5609 | 17.6337 | 26.8981 | 37.5427 | -0.98948 | 10.5709 | 8.5522 | 7.0728 | 9.2645 | 10.6446 | 10.5709 | 17.6437 | 26.9081 | 37.5527 | 0.01
12.885 | 9.593 | 7.4143 | 7.0937 | 14.0836 | 8.1594 | 12.885 | 19.9788 | 34.0623 | 42.2217 | 12.885 | 9.603 | 7.4143 | 7.0937 | 14.0836 | 8.1594 | 12.885 | 19.9788 | 34.0623 | 42.2217 | 0
4.9281 | 8.5642 | 8.1642 | 7.7995 | 9.0851 | 13.1297 | 8.5642 | 16.3637 | 25.4487 | 38.5784 | 4.9281 | 8.5742 | 8.1642 | 7.7995 | 9.0851 | 13.1297 | 8.5742 | 16.3737 | 25.4587 | 38.5884 | 0.01
-0.84741 | 8.2044 | 7.2375 | 5.3049 | 13.0524 | 15.3449 | 8.2044 | 13.5092 | 26.5617 | 41.9066 | -0.84741 | 8.2144 | 7.2375 | 5.3049 | 13.0524 | 15.3449 | 8.2144 | 13.5192 | 26.5717 | 41.9166 | 0.01
-10.0415 | 10.2783 | 10.8756 | 6.9861 | 14.6188 | 9.7177 | 10.2783 | 17.2644 | 31.8832 | 41.601 | -10.0415 | 10.2883 | 10.8756 | 6.9861 | 14.6188 | 9.7177 | 10.2883 | 17.2744 | 31.8932 | 41.611 | 0.01
-4.9238 | 9.8972 | 7.5314 | 8.7201 | 13.2095 | 13.533 | 9.8972 | 18.6173 | 31.8269 | 45.3598 | -4.9238 | 9.9072 | 7.5314 | 8.7201 | 13.2095 | 13.533 | 9.9072 | 18.6273 | 31.8369 | 45.3698 | 0.01
-0.041984 | 7.9722 | 9.2455 | 7.2884 | 11.0179 | 10.291 | 7.9722 | 15.2606 | 26.2785 | 36.5694 | -0.041984 | 7.9822 | 9.2455 | 7.2884 | 11.0179 | 10.291 | 7.9822 | 15.2706 | 26.2885 | 36.5794 | 0.01
8.7577 | 10.1366 | 5.8852 | 3.5285 | 10.6993 | 14.079 | 10.1366 | 13.665 | 24.3644 | 38.4433 | 8.7577 | 10.1466 | 5.8852 | 3.5285 | 10.6993 | 14.079 | 10.1466 | 13.675 | 24.3744 | 38.4533 | 0.01
5.6091 | 7.3573 | 9.8547 | 5.1702 | 9.7925 | 11.6195 | 7.3573 | 12.5275 | 22.32 | 33.9395 | 5.6091 | 7.3673 | 9.8547 | 5.1702 | 9.7925 | 11.6195 | 7.3673 | 12.5375 | 22.33 | 33.9495 | 0.01
-3.9008 | 8.004 | 6.8482 | 6.1112 | 6.2971 | 10.7133 | 8.004 | 14.1152 | 20.4123 | 31.1256 | -3.9008 | 8.014 | 6.8482 | 6.1112 | 6.2971 | 10.7133 | 8.014 | 14.1252 | 20.4223 | 31.1356 | 0.01
-0.72996 | 9.4083 | 6.1784 | 4.3465 | 8.6411 | 12.2235 | 9.4083 | 13.7548 | 22.3959 | 34.6194 | -0.72996 | 9.4183 | 6.1784 | 4.3465 | 8.6411 | 12.2235 | 9.4183 | 13.7648 | 22.4059 | 34.6294 | 0.01
7.6841 | 7.832 | 8.1915 | 5.2397 | 6.6767 | 12.6943 | 7.832 | 13.0717 | 19.7485 | 32.4428 | 7.6841 | 7.842 | 8.1915 | 5.2397 | 6.6767 | 12.6943 | 7.842 | 13.0817 | 19.7585 | 32.4528 | 0.01
5.7811 | 8.9705 | 7.6556 | 4.6549 | 13.2615 | 12.8435 | 8.9705 | 13.6254 | 26.8869 | 39.7304 | 5.7811 | 8.9805 | 7.6556 | 4.6549 | 13.2615 | 12.8435 | 8.9805 | 13.6354 | 26.8969 | 39.7404 | 0.01
-5.7588 | 9.9283 | 9.0112 | 2.4531 | 10.5313 | 8.1427 | 9.9283 | 12.3814 | 22.9127 | 31.0554 | -5.7588 | 9.9383 | 9.0112 | 2.4531 | 10.5313 | 8.1427 | 9.9383 | 12.3914 | 22.9227 | 31.0654 | 0.01
6.8917 | 9.3308 | 8.707 | 5.7676 | 11.9391 | 10.4419 | 9.3308 | 15.0984 | 27.0375 | 37.4794 | 6.8917 | 9.3408 | 8.707 | 5.7676 | 11.9391 | 10.4419 | 9.3408 | 15.1084 | 27.0475 | 37.4894 | 0.01
-0.48741 | 10.6471 | 5.7716 | 3.4442 | 10.585 | 12.0816 | 10.6471 | 14.0914 | 24.6763 | 36.7579 | -0.48741 | 10.6571 | 5.7716 | 3.4442 | 10.585 | 12.0816 | 10.6571 | 14.1014 | 24.6863 | 36.7679 | 0.01
0.87552 | 9.2638 | 8.2461 | 8.7599 | 11.6839 | 14.2868 | 9.2638 | 18.0237 | 29.7076 | 43.9944 | 0.87552 | 9.2738 | 8.2461 | 8.7599 | 11.6839 | 14.2868 | 9.2738 | 18.0337 | 29.7176 | 44.0044 | 0.01
-2.8158 | 11.1924 | 8.4708 | 13.0938 | 8.7867 | 16.0224 | 11.1924 | 24.2862 | 33.0729 | 49.0953 | -2.8158 | 11.2024 | 8.4708 | 13.0938 | 8.7867 | 16.0224 | 11.2024 | 24.2962 | 33.0829 | 49.1053 | 0.01
7.4043 | 9.7713 | 8.3368 | 7.3393 | 15.4377 | 11.8642 | 9.7713 | 17.1106 | 32.5483 | 44.4124 | 7.4043 | 9.7813 | 8.3368 | 7.3393 | 15.4377 | 11.8642 | 9.7813 | 17.1206 | 32.5583 | 44.4224 | 0.01
5.0162 | 6.9768 | 6.1202 | 6.933 | 10.7846 | 4.3207 | 6.9768 | 13.9098 | 24.6945 | 29.0152 | 5.0162 | 6.9868 | 6.1202 | 6.933 | 10.7846 | 4.3207 | 6.9868 | 13.9198 | 24.7045 | 29.0252 | 0.01
-0.2309 | 9.9054 | 7.2445 | 9.5354 | 9.1073 | 6.2056 | 9.9054 | 19.4408 | 28.5481 | 34.7537 | -0.2309 | 9.9154 | 7.2445 | 9.5354 | 9.1073 | 6.2056 | 9.9154 | 19.4508 | 28.5581 | 34.7637 | 0.01
5.7831 | 9.907 | 8.8985 | 3.0197 | 9.1803 | 17.1948 | 9.907 | 12.9267 | 22.1071 | 39.3018 | 5.7831 | 9.917 | 8.8985 | 3.0197 | 9.1803 | 17.1948 | 9.917 | 12.9367 | 22.1171 | 39.3118 | 0.01
12.4673 | 9.3865 | 7.0642 | 6.492 | 6.1196 | 12.7007 | 12.4673 | 18.9594 | 25.079 | 37.7796 | 12.4673 | 9.3965 | 7.0642 | 6.492 | 6.1196 | 12.7007 | 12.4673 | 18.9594 | 25.079 | 37.7796 | 0
6.8883 | 9.4987 | 4.7384 | 7.9926 | 13.0417 | 10.792 | 9.4987 | 17.4913 | 30.533 | 41.3251 | 6.8883 | 9.5087 | 4.7384 | 7.9926 | 13.0417 | 10.792 | 9.5087 | 17.5013 | 30.543 | 41.3351 | 0.01
2.8132 | 9.0969 | 11.3215 | 7.4152 | 11.2881 | 16.4266 | 9.0969 | 16.5122 | 27.8002 | 44.2269 | 2.8132 | 9.1069 | 11.3215 | 7.4152 | 11.2881 | 16.4266 | 9.1069 | 16.5222 | 27.8102 | 44.2369 | 0.01
0.86111